## Summary
Magnolia Oil & Gas / Bighorn Pass H06 ST01 / LTX1148421 / Patterson 248
Report Date: | 11/19/2021 | Current Depth: | 19363
Start Date: | 11/12/2021 | Casing Depth: | 0
Daily Cost: | 9400 | Distance to TD:
Well Cost: | 80000 | Average ROP: | 0
Drilling Hours: | 25.45 | Svy MD: | 19276
24Hr Forcast: |  | Svy Inc: | 86.17
Current BHA: | BHA 6 | Svy Azi: | 149.47
Current BRT Hrs: | 84.25 | Svy TVD: | 10634.14
Bit Make / Model: | Security / GTD64M | Svy NS: | -7467.65
POOH in last 24Hrs: | No | Svy EW: | 4638.52
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | H2O | Svy Left/Right: | 0
Directional Driller Day: | Jesse Taylor | MWD Day: | Danny Veronie
Directional Driller Night: | Marshall Adams | MWD Night: | Jason Smetters
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 217
24Hr Summary: | POOH after TD | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
PPM250023 | 6/7 8.8 2.12 T/S HS88 .003 | PDCI |  | In Hole |  | 39.20 | 39.20
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
500037 | UBHO Sub |  |  | Clean
500029 | UBHO Sub |  |  | Clean
775213 | UBHO Sub |  |  | Clean
775186 | UBHO Sub |  |  | Clean
500048 | UBHO |  |  | In Hole |  | 90.17 | 90.17
500046 | UBHO |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31181 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Total Drilled (Usft): |  | 4463 |  |  | Total Days: |  | 8
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
4 | 4 | 6.75 | 14900 | 14906 | 6 |  | 0.88 |  | 100 | 6.8 | 3 | 34.5
5 | 5 | 6.75 | 14906 | 16460 | 1554 |  | 45.86 |  | 13.13 | 33.88 | 7.28 | 60.75
6 | 6 | 6.75 | 16460 | 19363 | 2903 |  | 114.07 |  | 7.27 | 25.45 | 13.75 | 84.25
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
4 | Security |  | GTD64M |  | 6.75 | New |  | 1-1-WT-C-X-I-NO-DMF |  | 1.491 | 6 | 6.8 | 0.88
5 | Security |  | GTD64M |  | 6.75 | New |  | 4-6-RO-A-X-I-BT-HP |  | 1.491 | 1554 | 33.8833 | 45.86
6 | Security |  | GTD64M |  | 6.75 | New |  | 1-3-LT-S-X-I-WT-TD |  | 1.491 | 2903 | 25.45 | 114.07
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.25 | 2.12 | 4.11 | 6 |  | 0.88
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.25 | 2.12 | 4.01 | 1554 |  | 45.86
6 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.25 | 2.12 | 4.11 | 2903 |  | 114.07
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | Jesse Taylor |  | Danny Veronie |  | Jason Smetters |  | Brandon Parks |  | Jim Harrison |  | Pete Langille
Josh Ray |  | Marshall Adams
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
ST: SIDETRACK |  |  | 2.42 / 1.68 |  | 38 |  | 2.31 |  | 1.50 / 0.00 |  | 2 |  | 16.47
LAT: LATERAL |  |  | 5.28 / 3.63 |  | 4425 |  | 89.03 |  | 2.75 / 0.00 |  | 2 |  | 49.7
Total |  |  | 7.71 |  | 4463 |  | 67.45 |  | 4.25 / 0.00 |  | 3 |  | 66.17
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
ST: SIDETRACK-BHA 5 |  |  | 14906.00 | 14938.00 | 0.00 | 0.00 | 3.31 | 32.00 | 100.00 | 32.00 | 3.31 | 9.67 | 9.67
ST: SIDETRACK-BHA 4 |  |  | 14900.00 | 14906.00 | 0.00 | 0.00 | 0.88 | 6.00 | 100.00 | 6.00 | 0.88 | 6.80 | 6.80
LAT: LATERAL-BHA 5 |  |  | 14938.00 | 16460.00 | 78.95 | 1350.00 | 24.09 | 172.00 | 11.30 | 1522.00 | 62.79 | 24.24 | 7.14
LAT: LATERAL-BHA 6 |  |  | 16460.00 | 19363.00 | 148.07 | 2692.00 | 28.98 | 211.00 | 7.27 | 2903.00 | 114.02 | 25.46 | 7.28
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1148421 | Total Drilled(Usft) | 4463.00
Operator | Magnolia Oil & Gas | Drilling Hours | 66.13
Well Name | Bighorn Pass H06 ST01 | Avg ROP(Usft/hr) | 67.48
Rig | Patterson 248 | Rotary Drilled(Usft) | 4042.00
State | Texas | Rotary Hours | 35.27
County | Washington | Rotary ROP(Usft/hr) | 114.61
Formation | Austin Chalk | Rotary % | 90.57
Start Date | 11/12/2021 | Slide Drilled(Usft) | 421.00
End Date | 11/19/2021 | Slide Hours | 30.87
Days On Well | 8 | Slide ROP(Usft/hr) | 13.64
Start Depth (Usft) | 14900.00 | Slide % | 9.43
End Depth (Usft) | 19363.00
Total Drilled (Usft) | 4463.00
# BHA's | 3
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 6.50 / 0.00
Phase Data
Phase | ST | LAT
Start Date | 11/12/2021 | 11/14/2021
End Date | 11/14/2021 | 11/19/2021
Total Days | 2.42 | 5.28
Start Depth (Usft) | 14900.00 | 14938.00
End Depth (Usft) | 14938.00 | 19363.00
Total Drilled(Usft) | 38.00 | 4425.00
Drilling Hours | 16.47 | 49.67
Circulating Hours | 4.92 | 19.12
Total D&C Hours | 21.38 | 68.78
Avg ROP(Usft/hr) | 2.31 | 89.09
Rotary Drilled(Usft) | 0.00 | 4042.00
Rotary Hours | 0.00 | 35.27
Rotary ROP(Usft/hr) | 0.00 | 114.61
Rotary % | 0.00 | 91.34
Slide Drilled(Usft) | 38.00 | 383.00
Slide Hours | 16.47 | 14.40
Slide ROP(Usft/hr) | 2.31 | 26.60
Slide % | 100.00 | 8.66
# BHA | 2 | 2
# Motor Failures | 0 | 0
# MWD Failures | 0 | 0
NPT hrs (Rig/Dir) | 2.00 / 0.00 | 4.50 / 0.00
Total Phase Hrs | 40.42 | 87.22
Phase ROP (Usft/hr) | 0.94 | 50.74
Avg Motor Yield (°/100ft) | 10.12 | 11.44
Avg Rotary DLS (°/100ft) | 0.00 | 1.75
Avg Rotary TF | 0.00 | -42.72
Avg Slide Length (Usft) | 6.33 | 15.96
# Slides | 6 | 24
BHA Data
BHA# | 4 | 5 | 6
Description | BHA 4 | BHA 5 | BHA 6
Bit Size | 6.750 | 6.750 | 6.750
Bit Make/Model | Security / GTD64M | Security / GTD64M | Security / GTD64M
Bit TFA | 1.491 | 1.491 | 1.491
Grade In | New | New | New
Grade Out | 1-1-WT-C-X-I-NO-DMF | 4-6-RO-A-X-I-BT-HP | 1-3-LT-S-X-I-WT-TD
Motor SN | PPM250007 | PPM250012 | PPM250023
Motor Make/Model | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 15.00 / 15.00 / 15.00 | 10.00 / 25.60 / 45.00 | 10.71 / 22.16 / 35.00
Diff P (psi) | 100.00 / 100.00 / 100.00 | 32.72 / 535.91 / 1843.07 | 43.99 / 726.95 / 1900.01
Bend | 2.120 | 2.120 | 2.120
Date In | 11/12/2021 | 11/13/2021 | 11/16/2021
Date Out | 11/13/2021 | 11/16/2021 | 11/19/2021
Time In | 03:00 | 14:15 | 06:45
Time Out | 13:30 | 03:00 | 19:00
BRT Hrs | 34.50 | 60.75 | 84.25
Start Depth (Usft) | 14900.00 | 14906.00 | 16460.00
End Depth (Usft) | 14906.00 | 16460.00 | 19363.00
Total Drilled(Usft) | 6.00 | 1554.00 | 2903.00
Drilling Hours | 6.80 | 33.88 | 25.45
Circulating Hours | 3.00 | 7.28 | 13.75
Total D&C Hours | 9.80 | 41.17 | 39.20
Avg ROP(Usft/hr) | 0.88 | 45.86 | 114.07
Rotary Drilled(Usft) | 0.00 | 1350.00 | 2692.00
Rotary Hours | 0.00 | 17.08 | 18.18
Rotary ROP(Usft/hr) | 0.00 | 79.02 | 148.05
Rotary % | 0.00 | 86.87 | 92.73
Slide Drilled(Usft) | 6.00 | 204.00 | 211.00
Slide Hours | 6.80 | 16.80 | 7.27
Slide ROP(Usft/hr) | 0.88 | 12.14 | 29.04
Slide % | 100.00 | 13.13 | 7.27
Motor Failure | NO | NO | NO
MWD Failure | NO | NO | NO
Unplanned Trip | YES | YES | NO
LIH | NO | NO | NO
Avg Motor Yield (°/100ft) | 0.00 | 13.16 | 10.95
Avg Rotary DLS (°/100ft) | 0.00 | 2.13 | 1.35
Avg Rotary TF | 0.00 | -51.82 | -36.81
Avg Slide Length (Usft) | 3.00 | 13.60 | 16.23
# Slides | 2 | 15 | 13

## Personnel Report
|  | Job # | LTX1148421 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31181 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Bighorn Pass H06
|  | Date: | 11/19/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Bighorn Pass H06 ST01 - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Danny Veronie | Day MWD |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
Jason Smetters | Night MWD |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
Jesse Taylor | Day DD |  | 11/18/2021 - 00:00 | 11/19/2021 - 00:00 |  | 2.00 / 0.00
Jesse Taylor | Night DD |  | 11/12/2021 - 00:00 | 11/17/2021 - 00:00 |  | 6.00 / 0.00
Josh Ray | Day DD |  | 11/12/2021 - 00:00 | 11/17/2021 - 00:00 |  | 6.00 / 0.00
Marshall Adams | Night DD |  | 11/18/2021 - 00:00 | 11/19/2021 - 00:00 |  | 2.00 / 0.00
NA | Trainee 1 |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
NA | Trainee 2 |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
NA | Rss Eng. 1 |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
NA | Rss Eng. 2 |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
NA | Third Man |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
NA | Fourth Man |  | 11/12/2021 - 00:00 | 11/19/2021 - 00:00 |  | 8.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1148421 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Bighorn Pass H06 ST01 | [7 empty] | Day DD: |  |  |  |  | Jesse Taylor | [5 empty] | API #: |  |  |  | 42-477-31181
|  |  |  | AFE #: |  |  | 21DD0218MG | [7 empty] | Night DD: |  |  |  |  | Marshall Adams | [5 empty] | Company Man: |  |  |  | Brandon Parks
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Jason Smetters | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 11/12/2021 | 11/13/2021 | 11/14/2021 | 11/15/2021 | 11/16/2021 | 11/17/2021 | 11/18/2021 | 11/19/2021 | 11/20/2021 | 11/21/2021 | 11/22/2021 | 11/23/2021 | 11/24/2021 | 11/25/2021 | 11/26/2021 | 11/27/2021 | 11/28/2021 | 11/29/2021 | 11/30/2021 | 12/01/2021 | 12/02/2021 | 12/03/2021 | 12/04/2021 | 12/05/2021 | 12/06/2021 | 12/07/2021 | 12/08/2021 | 12/09/2021 | 12/10/2021 | 12/11/2021 | 12/12/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 13.5 | U616S |  | Steel | 47424 | 0 | 8 | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13673682 | 4 | 5 |  |  |  | O | X | X | X | X
Bit |  | 6.75 | GTD64M |  | Steel | 13601237 | 4 | 8 | O | X | X | X | X | O | O | O
Cross Over |  | 7.75 | Crossover Sub |  | Steel | GT7746830 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 7.812 | Crossover Sub |  | Steel | GT8046864 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 6.75 | Crossover Sub |  | Steel | GT6744705 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 6.75 | Crossover Sub |  | Steel | GT6744706 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 6.625 | Crossover Sub |  | Steel | GT8046498 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 7.875 | Crossover Sub |  | Steel | GT80461428 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 6.688 | Crossover Sub |  | Steel | GT6744908 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 6.688 | Crossover Sub |  | Steel | GT6744416 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 5.188 | Crossover |  | Steel | GT52331432 | 0 | 8 | O | O | O | O | O | O | O | O
Cross Over |  | 5.25 | Crossover |  | Steel | GT52331430 | 8 | 8 | X | X | X | X | X | X | X | X
MWD / LWD |  | 5.188 | UBHO Sub |  | Steel | 500037 | 0 | 8 | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.188 | UBHO Sub |  | Steel | 500029 | 0 | 8 | O | O | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO Sub |  | Steel | 775213 | 0 | 8 | O | O | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO Sub |  | Steel | 775186 | 0 | 8 | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500048 | 8 | 8 | X | X | X | X | X | X | X | X
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500046 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 |  | Steel | PPM800023 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 |  | Steel | PPM800055 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.0 TS HPW .003 |  | Steel | PPM800034 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.0 TS HPW .015 |  | Steel | MTR775015 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 5.25 | 6/7 8.8 2.12 T/S HS88 +.022 |  | Steel | PPM250017 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI |  | 7/8 3.8 2.12 T/S HS88 -.004 |  | Steel | MTR500028 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 5.25 | 6/7 8.8 2.12 T/S HS88 +.001 |  | Steel | PPM250007 | 2 | 8 | X | X | O | O | O | O | O | O
Motor | PDCI | 5.25 | 6/7 11.7 2.12 T/S HS88 +.014 |  | Steel | PPM250010 | 0 | 8 | O | O | O | O | O | O | O | O
Motor | PDCI | 5.25 | 6/7 8.8 2.12 T/S HS88 -.001 |  | Steel | PPM250012 | 4 | 8 | O | X | X | X | X | O | O | O
Motor | PDCI | 5.25 | 6/7 8.8 2.12 T/S HS88 .003 |  | Steel | PPM250023 | 4 | 8 | O | O | O | O | X | X | X | X
Motor | Pro Power | 5.25 | 6/7 8.8 2.12 T/S HS88 .006 |  | Steel | PPM250015 | 0 | 4 |  |  |  |  | O | O | O | O
Stab |  | 13 | Nortrak Stabilizer |  | Steel | GT801171 | 0 | 8 | O | O | O | O | O | O | O | O
Stab |  | 13 | Nortrak Stabilizer |  | Steel | GT801173 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 7.938 | NMDC |  | Non-Mag | GT8030122 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 7.875 | NMDC |  | Non-Mag | GT8030218 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 8 | NMDC |  | Non-Mag | GT8030629 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 7.938 | NMDC |  | Non-Mag | GT8030626 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 8 | Pony NMDC |  | Non-Mag | GT8010518 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 8 | Pony NMDC |  | Non-Mag | GT8010255 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-592 | 8 | 8 | X | X | X | X | X | X | X | X
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-458 | 8 | 8 | X | X | X | X | X | X | X | X
Collar |  | 4.938 | Pony Collar |  | Steel | GT50-10-479 | 8 | 8 | X | X | X | X | X | X | X | X
Collar |  |  | Pony Collar |  | Steel | GT50-10-652 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  |  | Pony Collar |  | Steel | GT50-10-585 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-578 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-580 | 0 | 8 | O | O | O | O | O | O | O | O
Collar |  | 5.25 | Ponny Collar |  | Steel | GT50-10-533 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  | 8 | Float Sub |  | Steel | GT8066579F | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  | 8 | Float Sub |  | Steel | GT8066297F | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | GT5003313FF | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | GT50331377FF | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | GT551232 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | GT551251 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  |  | Lift Cap |  | Steel | GT126 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  | 5 | Filter Sub With Filter |  | Steel | GT50331343 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  | 5 | Filter Sub With Filter |  | Steel | GT5033740 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  | 4.812 | BTI Sub |  | Steel | BTI 3 | 8 | 8 | X | X | X | X | X | X | X | X
Sub |  | 5 | Tomax |  | Steel | A52165 | 0 | 8 | O | O | O | O | O | O | O | O
Sub |  | 5 | Tomax |  | Steel | A52042 | 8 | 8 | X | X | X | X | X | X | X | X
Agitator | DWS | 6.75 | Agitator |  | Steel | PG675-0008 | 0 | 8 | O | O | O | O | O | O | O | O
Agitator | DWS | 6.75 | Agitator |  | Steel | PG675-0023 | 0 | 8 | O | O | O | O | O | O | O | O
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0049 | 8 | 8 | X | X | X | X | X | X | X | X
Agitator |  | 5.25 | Agitator (Ball Drop) |  | Steel | PG525-0035 | 8 | 8 | X | X | X | X | X | X | X | X
Agitator |  | 5.35 | Agitator |  | Steel | PG525-0033 | 0 | 8 | O | O | O | O | O | O | O | O
Reamer |  |  | Reamer |  | Steel | 579 | 8 | 8 | X | X | X | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 2 | [7 empty] | 1 | 1
Day DD |  |  | Josh Ray |  |  |  | 6 |  | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Jesse Taylor |  |  |  | 6 |  | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Marshall Adams |  |  |  | 2 | [7 empty] | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smetters |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31181 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Bighorn Pass H06
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0218MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
GT7746830 | Crossover Sub | 7.75 | 3.33 |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8046864 | Crossover Sub | 7.812 | 3.37 |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT6744705 | Crossover Sub | 6.75 | 3.22 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 10/08/2021 |  | 11/19/2021
GT6744706 | Crossover Sub | 6.75 | 3.55 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 10/08/2021 |  | 11/19/2021
500037 | UBHO Sub | 5.188 | 4 |  | XT39 / XT39 | Clean |  | 10/08/2021 |  | 11/19/2021
500029 | UBHO Sub | 5.188 | 2.88 |  | XT39 / XT39 | Clean |  | 10/08/2021 |  | 11/19/2021
775213 | UBHO Sub | 7.75 | 3.63 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
775186 | UBHO Sub | 7.75 | 2.44 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8046498 | Crossover Sub | 6.625 | 3.3 |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT80461428 | Crossover Sub | 7.875 | 3.36 |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT80663 | Lift Sub | 8 | 2.98 |  | 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT80301 | Lift Sub | 8 | 3.58 |  | 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT120 | Lift Cap |  |  |  | 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8066579F | Float Sub | 8 | 3.61 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8066297F | Float Sub | 8 | 3.55 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT6744908 | Crossover Sub | 6.688 | 3.49 |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 10/08/2021 |  | 11/19/2021
GT6744416 | Crossover Sub | 6.688 | 3.52 |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 10/08/2021 |  | 11/19/2021
GT801171 | Nortrak Stabilizer | 13 | 7.97 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT801173 | Nortrak Stabilizer | 13 | 7.95 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8030122 | NMDC | 7.938 | 30.27 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8030218 | NMDC | 7.875 | 30 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8030629 | NMDC | 8 | 31.17 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8030626 | NMDC | 7.938 | 30.95 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8010518 | Pony NMDC | 8 | 9.43 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
GT8010255 | Pony NMDC | 8 | 9.98 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
PPM800023 | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 | 8 | 37.55 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 10/08/2021 |  | 11/19/2021
PPM800055 | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 | 8 | 37.53 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 10/08/2021 |  | 11/19/2021
47424 | U616S | 13.5 | 1.5 |  | 6 5/8 REG | Clean |  | 10/08/2021 |  | 11/19/2021
PG675-0008 | Agitator | 6.75 | 24.67 |  | 4 1/2 IF / 4 1/2 IF | Clean | DWS / Power Glide | 10/08/2021 |  | 11/19/2021
PG675-0023 | Agitator | 6.75 | 24.61 |  | 4 1/2 IF / 4 1/2 IF | Clean | DWS / Power Glide | 10/08/2021 |  | 11/19/2021
PPM800034 | 7/8 5.9 2.0 TS HPW .003 | 8 | 37.73 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 10/08/2021 |  | 11/19/2021
MTR775015 | 7/8 5.9 2.0 TS HPW .015 | 8 | 38.06 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 10/08/2021 |  | 11/19/2021
PPM250017 | 6/7 8.8 2.12 T/S HS88 +.022 | 5.25 | 33.08 |  | XT39 / 3 1/2REG | Clean | PDCI / Pro Power | 11/07/2021 |  | 11/19/2021
MTR500028 | 7/8 3.8 2.12 T/S HS88 -.004 |  |  |  | XT39 / 3 1/2REG | Clean | PDCI / Pro Power | 11/07/2021 |  | 11/19/2021
GT52-30-592 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 31.11 |  | XT39 / XT39 | In Hole |  | 11/07/2021
GT52-30-458 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 30.53 |  | XT39 / XT39 | In Hole |  | 11/07/2021
GT5003313FF | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT50331377FF | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT551232 | Lift Sub |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT551251 | Lift Sub |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT126 | Lift Cap |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT50331343 | Filter Sub With Filter | 5 | 5.55 |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT5033740 | Filter Sub With Filter | 5 | 4.92 |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
579 | Reamer |  |  |  | CET43 / CET43 | In Hole |  | 11/07/2021
500048 | UBHO | 5.25 | 3.9 |  | XT39 / XT39 | In Hole |  | 11/07/2021
PG525-0049 | Agitator | 5.25 | 21.4 |  | CET43 / CET43 | In Hole |  | 11/07/2021
PG525-0035 | Agitator (Ball Drop) | 5.25 | 21.25 |  | CET43 / CET43 | In Hole |  | 11/11/2021
GT50-10-479 | Pony Collar | 4.938 | 9.86 |  | XT39 / XT39 | In Hole |  | 11/07/2021
GT50-10-652 | Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT50-10-585 | Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT52331432 | Crossover | 5.188 | 3.37 |  | CET43 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
BTI 3 | BTI Sub | 4.812 | 1.65 |  | XT39 / XT39 | In Hole |  | 11/07/2021
PG525-0033 | Agitator | 5.35 | 21.24 |  | CET43 / CET43 | Clean |  | 11/07/2021 |  | 11/19/2021
A52165 | Tomax | 5 | 18 |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
A52042 | Tomax | 5 | 20.64 |  | XT39 / XT39 | In Hole |  | 11/11/2021
GT52-30-578 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT52-30-580 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT50-10-533 | Ponny Collar | 5.25 |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
GT52331430 | Crossover | 5.25 | 3.33 |  | CET43 / XT39 | In Hole |  | 11/07/2021
PPM250007 | 6/7 8.8 2.12 T/S HS88 +.001 | 5.25 | 33.27 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 11/07/2021 |  | 11/19/2021
PPM250010 | 6/7 11.7 2.12 T/S HS88 +.014 | 5.25 | 33.23 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 11/07/2021 |  | 11/19/2021
500046 | UBHO | 5.25 |  |  | XT39 / XT39 | Clean |  | 11/07/2021 |  | 11/19/2021
13673682 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | In Hole |  | 11/15/2021
13601237 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Dirty |  | 11/11/2021 |  | 11/19/2021
PPM250012 | 6/7 8.8 2.12 T/S HS88 -.001 | 5.25 | 32.97 |  | XT39 / 3 1/2REG | Dirty | PDCI / Pro Power | 11/11/2021 |  | 11/19/2021
PPM250023 | 6/7 8.8 2.12 T/S HS88 .003 | 5.25 | 32.95 |  | XT39 / 3 1/2REG | In Hole | PDCI / Pro Power | 11/11/2021
PPM250015 | 6/7 8.8 2.12 T/S HS88 .006 | 5.25 |  |  | XT39 / 3 1/2REG | Clean | Pro Power / 0 | 11/16/2021 |  | 11/19/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31181 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Bighorn Pass H06
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
GTD64M | 13618580 | 11/12/2021 | 11/19/2021 | 8 | 1 | 4 |  | 3 | 6.8 | 34.5
6/7 8.8 2.12 T/S HS88 +.001 | PPM250007 | 11/07/2021 | 11/19/2021 | 13 | 1 | 4 |  | 3 | 6.8 | 34.5
BTI Sub | BTI 3 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Pony Collar | GT50-10-479 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
UBHO | 500048 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Non Mag Drill Collar (NO HARDBANDING) | GT52-30-592 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Non Mag Drill Collar (NO HARDBANDING) | GT52-30-458 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Tomax | A52042 | 11/11/2021 | 11/19/2021 | 9 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Crossover | GT52331430 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Drill N Ream | 579 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Agitator | PG525-0049 | 11/07/2021 | 11/19/2021 | 13 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
Agitator (Ball Drop) | PG525-0035 | 11/11/2021 | 11/19/2021 | 9 | 7 | 4 ,5 ,6 |  | 24.03 | 66.13 | 179.5
GTD64M | 13601237 | 11/11/2021 | 11/19/2021 | 9 | 3 | 5 |  | 7.28 | 33.88 | 60.75
6/7 8.8 2.12 T/S HS88 -.001 | PPM250012 | 11/11/2021 | 11/19/2021 | 9 | 3 | 5 |  | 7.28 | 33.88 | 60.75
GTD64M | 13673682 | 11/15/2021 | 11/19/2021 | 5 | 4 | 6 |  | 13.75 | 25.45 | 84.25
6/7 8.8 2.12 T/S HS88 .003 | PPM250023 | 11/11/2021 | 11/19/2021 | 9 | 4 | 6 |  | 13.75 | 25.45 | 84.25
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | well
Facility |  |  | Bighorn - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Bighorn Pass H06 |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Bighorn Pass H06 ST01
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 292.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Bighorn - Washington County, TX
Map Northing |  |  | 233699.79 US survey foot |  |  | Map Easting |  |  | 3155230.66 US survey foot
Latitude |  |  | 30° 15' 25.17043" N |  |  | Longitude |  |  | 96° 40' 25.60169" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.885
Well: |  |  | Bighorn Pass H06
Local North |  |  | 6.78 Usft |  |  | Local East |  |  | 39.54 Usft
Map Northing |  |  | 233706.57 US survey foot |  |  | Map Easting |  |  | 3155270.20 US survey foot
Latitude |  |  | 30° 15' 25.225" N |  |  | Longitude |  |  | 96° 40' 25.149" W
Depth Datum |  |  | well |  |  | Datum Elevation |  |  | 292.00 Usft
GL Elevation |  |  | 264.00 Usft
Grid Convergence |  |  | 1.885
Well bore: |  |  | Bighorn Pass H06 ST01
Magnetic Model |  |  | User defined |  |  | Date |  |  | 20/10/2021
Total Field (nT) |  |  | 46629.4 |  |  | Dip Angle (°) |  |  | 58.85
Declination (°) |  |  | 2.917
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 149.5
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Bighorn Pass H06 ST01
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2915 |  |  | BH Pass H06 S1 |  |  | MWD+HDGM
2915 |  |  | 9726 |  |  | BH Pass H06 S2 |  |  | MWD+HDGM
9726 |  |  | 14822 |  |  | BH Pass H06 S3 |  |  | MWD+HDGM
14822 |  |  | 16350 |  |  | BH Pass H06 S4 |  |  | MWD+HDGM
16350 |  |  | 19276 |  |  | BH Pass H06 S5 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -292 | 233706.57 | 3155270.2 | 30.257 | -96.6737 | 0
200 | 0.13 | 317.66 | 200 | 0.17 | -0.15 | -0.22 | 0.07 | 0.07 | 21.17 | 317.66 | 200 | -92 | 233706.74 | 3155270.05 | 30.257 | -96.6737 | 317.66
293 | 0.42 | 300.68 | 293 | 0.42 | -0.52 | -0.62 | 0.32 | 0.31 | -18.26 | -24.3 | 93 | 1 | 233706.99 | 3155269.68 | 30.257 | -96.6737 | 309.06
384 | 0.61 | 337.22 | 384 | 1.04 | -0.99 | -1.4 | 0.41 | 0.21 | 40.15 | 79.07 | 91 | 92 | 233707.61 | 3155269.21 | 30.257 | -96.6737 | 316.27
478 | 0.52 | 352.95 | 477.99 | 1.92 | -1.24 | -2.28 | 0.19 | -0.1 | 16.73 | 127.83 | 94 | 185.99 | 233708.49 | 3155268.96 | 30.257 | -96.6737 | 327.21
572 | 0.46 | 351.06 | 571.99 | 2.72 | -1.35 | -3.03 | 0.07 | -0.06 | -2.01 | -165.87 | 94 | 279.99 | 233709.29 | 3155268.85 | 30.257 | -96.6737 | 333.6
665 | 0.59 | 12 | 664.98 | 3.55 | -1.31 | -3.73 | 0.25 | 0.14 | 22.52 | 66.65 | 93 | 372.98 | 233710.12 | 3155268.89 | 30.257 | -96.6737 | 339.81
759 | 0.5 | 15.9 | 758.98 | 4.42 | -1.09 | -4.37 | 0.1 | -0.1 | 4.15 | 159.54 | 94 | 466.98 | 233710.99 | 3155269.11 | 30.257 | -96.6737 | 346.1
852 | 0.61 | 358.25 | 851.97 | 5.31 | -1 | -5.08 | 0.22 | 0.12 | 18.98 | -66.27 | 93 | 559.97 | 233711.88 | 3155269.2 | 30.257 | -96.6737 | 349.35
946 | 0.64 | 348.73 | 945.97 | 6.32 | -1.12 | -6.01 | 0.11 | 0.03 | -10.13 | -78.68 | 94 | 653.97 | 233712.89 | 3155269.08 | 30.257 | -96.6737 | 349.99
1040 | 0.4 | 354.67 | 1039.97 | 7.16 | -1.25 | -6.81 | 0.26 | -0.26 | 6.32 | 170.3 | 94 | 747.97 | 233713.73 | 3155268.95 | 30.257 | -96.6737 | 350.11
1133 | 1.05 | 342.34 | 1132.96 | 8.3 | -1.54 | -7.93 | 0.71 | 0.7 | -13.26 | -19.71 | 93 | 840.96 | 233714.87 | 3155268.66 | 30.257 | -96.6737 | 349.5
1228 | 1.8 | 336.69 | 1227.93 | 10.5 | -2.39 | -10.26 | 0.8 | 0.79 | -5.95 | -13.44 | 95 | 935.93 | 233717.07 | 3155267.81 | 30.257 | -96.6737 | 347.16
1322 | 3.02 | 339.99 | 1321.84 | 14.18 | -3.82 | -14.16 | 1.31 | 1.3 | 3.51 | 8.14 | 94 | 1029.84 | 233720.75 | 3155266.38 | 30.257 | -96.6737 | 344.91
1415 | 4.05 | 339.31 | 1414.66 | 19.56 | -5.82 | -19.8 | 1.11 | 1.11 | -0.73 | -2.67 | 93 | 1122.66 | 233726.13 | 3155264.38 | 30.2571 | -96.6737 | 343.42
1509 | 4.71 | 340.95 | 1508.39 | 26.31 | -8.25 | -26.86 | 0.71 | 0.7 | 1.74 | 11.56 | 94 | 1216.39 | 233732.88 | 3155261.95 | 30.2571 | -96.6737 | 342.58
1602 | 5.07 | 343.62 | 1601.05 | 33.86 | -10.66 | -34.59 | 0.46 | 0.39 | 2.87 | 33.64 | 93 | 1309.05 | 233740.43 | 3155259.54 | 30.2571 | -96.6737 | 342.53
1696 | 5.81 | 342.66 | 1694.63 | 42.39 | -13.25 | -43.25 | 0.79 | 0.79 | -1.02 | -7.49 | 94 | 1402.63 | 233748.96 | 3155256.95 | 30.2571 | -96.6737 | 342.64
1790 | 6.36 | 345.21 | 1788.1 | 51.96 | -16 | -52.89 | 0.65 | 0.59 | 2.71 | 27.44 | 94 | 1496.1 | 233758.53 | 3155254.2 | 30.2572 | -96.6737 | 342.89
1883 | 6.96 | 348.55 | 1880.47 | 62.47 | -18.43 | -63.18 | 0.77 | 0.65 | 3.59 | 34.51 | 93 | 1588.47 | 233769.04 | 3155251.77 | 30.2572 | -96.6737 | 343.56
1977 | 7.52 | 348.77 | 1973.72 | 74.08 | -20.76 | -74.37 | 0.6 | 0.6 | 0.23 | 2.94 | 94 | 1681.72 | 233780.65 | 3155249.44 | 30.2572 | -96.6737 | 344.35
2070 | 8.75 | 348.34 | 2065.78 | 86.98 | -23.37 | -86.81 | 1.32 | 1.32 | -0.46 | -3.05 | 93 | 1773.78 | 233793.55 | 3155246.83 | 30.2572 | -96.6737 | 344.96
2164 | 9.5 | 346.7 | 2158.59 | 101.53 | -26.6 | -100.98 | 0.84 | 0.8 | -1.74 | -19.94 | 94 | 1866.59 | 233808.1 | 3155243.6 | 30.2573 | -96.6737 | 345.32
2258 | 10.12 | 344.64 | 2251.22 | 117.04 | -30.57 | -116.37 | 0.76 | 0.66 | -2.19 | -30.53 | 94 | 1959.22 | 233823.61 | 3155239.62 | 30.2573 | -96.6737 | 345.36
2352 | 10.05 | 342.94 | 2343.77 | 132.85 | -35.17 | -132.31 | 0.33 | -0.07 | -1.81 | -104.07 | 94 | 2051.77 | 233839.42 | 3155235.03 | 30.2574 | -96.6737 | 345.17
2446 | 9.62 | 340.32 | 2436.38 | 148.08 | -40.22 | -148.01 | 0.66 | -0.46 | -2.79 | -135.14 | 94 | 2144.38 | 233854.65 | 3155229.98 | 30.2574 | -96.6738 | 344.8
2540 | 9.86 | 341.05 | 2529.03 | 163.09 | -45.48 | -163.61 | 0.29 | 0.26 | 0.78 | 27.59 | 94 | 2237.03 | 233869.66 | 3155224.72 | 30.2575 | -96.6738 | 344.42
2634 | 10.29 | 342.94 | 2621.58 | 178.73 | -50.56 | -179.66 | 0.58 | 0.46 | 2.01 | 38.49 | 94 | 2329.58 | 233885.3 | 3155219.64 | 30.2575 | -96.6738 | 344.21
2728 | 9.92 | 343.14 | 2714.12 | 194.51 | -55.37 | -195.69 | 0.4 | -0.39 | 0.21 | 174.68 | 94 | 2422.12 | 233901.08 | 3155214.83 | 30.2575 | -96.6738 | 344.11
2822 | 9.69 | 342.7 | 2806.75 | 209.81 | -60.07 | -211.26 | 0.26 | -0.24 | -0.47 | -162.17 | 94 | 2514.75 | 233916.38 | 3155210.13 | 30.2576 | -96.6738 | 344.02
2915 | 9.56 | 340.07 | 2898.44 | 224.54 | -65.03 | -226.47 | 0.49 | -0.14 | -2.83 | -107.76 | 93 | 2606.44 | 233931.11 | 3155205.17 | 30.2576 | -96.6738 | 343.85
3071 | 9.67 | 337.8 | 3052.25 | 248.85 | -74.39 | -252.17 | 0.25 | 0.07 | -1.46 | -74.94 | 156 | 2760.25 | 233955.42 | 3155195.81 | 30.2577 | -96.6739 | 343.36
3165 | 11.09 | 341.7 | 3144.71 | 264.74 | -80.22 | -268.82 | 1.68 | 1.51 | 4.15 | 28.26 | 94 | 2852.71 | 233971.31 | 3155189.98 | 30.2577 | -96.6739 | 343.14
3259 | 11.67 | 343.13 | 3236.86 | 282.42 | -85.81 | -286.9 | 0.69 | 0.62 | 1.52 | 26.64 | 94 | 2944.86 | 233988.99 | 3155184.39 | 30.2578 | -96.6739 | 343.1
3353 | 11.7 | 343.35 | 3328.91 | 300.65 | -91.3 | -305.39 | 0.06 | 0.03 | 0.23 | 56.16 | 94 | 3036.91 | 234007.22 | 3155178.9 | 30.2578 | -96.6739 | 343.11
3446 | 11.41 | 343.68 | 3420.03 | 318.52 | -96.59 | -323.47 | 0.32 | -0.31 | 0.35 | 167.32 | 93 | 3128.03 | 234025.09 | 3155173.61 | 30.2579 | -96.6739 | 343.13
3540 | 11.57 | 343.54 | 3512.14 | 336.48 | -101.87 | -341.63 | 0.17 | 0.17 | -0.15 | -9.96 | 94 | 3220.14 | 234043.05 | 3155168.33 | 30.2579 | -96.6739 | 343.16
3633 | 11.62 | 342.42 | 3603.25 | 354.35 | -107.35 | -359.8 | 0.25 | 0.05 | -1.2 | -78.03 | 93 | 3311.25 | 234060.92 | 3155162.85 | 30.258 | -96.674 | 343.15
3727 | 11.71 | 342.14 | 3695.3 | 372.46 | -113.13 | -378.34 | 0.11 | 0.1 | -0.3 | -32.31 | 94 | 3403.3 | 234079.03 | 3155157.07 | 30.258 | -96.674 | 343.1
3820 | 12.21 | 346.22 | 3786.29 | 390.99 | -118.37 | -396.97 | 1.06 | 0.54 | 4.39 | 61.41 | 93 | 3494.29 | 234097.56 | 3155151.83 | 30.2581 | -96.674 | 343.16
3913 | 12.87 | 347.87 | 3877.07 | 410.67 | -122.89 | -416.21 | 0.81 | 0.71 | 1.77 | 29.3 | 93 | 3585.07 | 234117.24 | 3155147.31 | 30.2581 | -96.674 | 343.34
4007 | 12.78 | 347.6 | 3968.72 | 431.06 | -127.32 | -436.03 | 0.12 | -0.1 | -0.29 | -146.47 | 94 | 3676.72 | 234137.63 | 3155142.88 | 30.2582 | -96.674 | 343.54
4100 | 12.95 | 347.73 | 4059.39 | 451.29 | -131.74 | -455.71 | 0.19 | 0.18 | 0.14 | 9.73 | 93 | 3767.39 | 234157.86 | 3155138.46 | 30.2583 | -96.674 | 343.73
4194 | 11.56 | 350.79 | 4151.25 | 470.88 | -135.49 | -474.49 | 1.63 | -1.48 | 3.26 | 156.44 | 94 | 3859.25 | 234177.45 | 3155134.71 | 30.2583 | -96.674 | 343.95
4288 | 11.09 | 350.19 | 4243.41 | 489.08 | -138.54 | -491.72 | 0.52 | -0.5 | -0.64 | -166.22 | 94 | 3951.41 | 234195.65 | 3155131.66 | 30.2584 | -96.674 | 344.18
4381 | 11.13 | 348.28 | 4334.67 | 506.69 | -141.88 | -508.59 | 0.4 | 0.04 | -2.05 | -84.73 | 93 | 4042.67 | 234213.26 | 3155128.32 | 30.2584 | -96.674 | 344.36
4474 | 10.29 | 352.43 | 4426.05 | 523.71 | -144.8 | -524.74 | 1.23 | -0.9 | 4.46 | 139.47 | 93 | 4134.05 | 234230.28 | 3155125.4 | 30.2585 | -96.6741 | 344.54
4568 | 10.32 | 352.16 | 4518.54 | 540.37 | -147.06 | -540.24 | 0.06 | 0.03 | -0.29 | -58.29 | 94 | 4226.54 | 234246.94 | 3155123.14 | 30.2585 | -96.6741 | 344.78
4663 | 9.11 | 349.12 | 4612.17 | 556.19 | -149.64 | -555.17 | 1.38 | -1.27 | -3.2 | -158.52 | 95 | 4320.17 | 234262.76 | 3155120.56 | 30.2585 | -96.6741 | 344.94
4758 | 8.92 | 347.86 | 4706 | 570.77 | -152.6 | -569.25 | 0.29 | -0.2 | -1.33 | -134.52 | 95 | 4414 | 234277.34 | 3155117.6 | 30.2586 | -96.6741 | 345.03
4851 | 8.72 | 344.01 | 4797.9 | 584.6 | -156.06 | -582.92 | 0.67 | -0.22 | -4.14 | -110.61 | 93 | 4505.9 | 234291.17 | 3155114.14 | 30.2586 | -96.6741 | 345.05
4944 | 6.28 | 342.33 | 4890.1 | 596.23 | -159.55 | -594.7 | 2.63 | -2.62 | -1.81 | -175.7 | 93 | 4598.1 | 234302.8 | 3155110.65 | 30.2587 | -96.6741 | 345.02
5038 | 6.21 | 339.84 | 4983.54 | 605.9 | -162.86 | -604.72 | 0.3 | -0.07 | -2.65 | -105.73 | 94 | 4691.54 | 234312.47 | 3155107.34 | 30.2587 | -96.6741 | 344.95
5131 | 5.89 | 339.39 | 5076.02 | 615.09 | -166.27 | -614.37 | 0.35 | -0.34 | -0.48 | -171.79 | 93 | 4784.02 | 234321.66 | 3155103.93 | 30.2587 | -96.6741 | 344.87
5225 | 5.95 | 336.77 | 5169.52 | 624.08 | -169.89 | -623.95 | 0.29 | 0.06 | -2.79 | -78.79 | 94 | 4877.52 | 234330.65 | 3155100.31 | 30.2587 | -96.6741 | 344.77
5319 | 5.43 | 329.03 | 5263.06 | 632.37 | -174.1 | -633.23 | 0.98 | -0.55 | -8.23 | -127.93 | 94 | 4971.06 | 234338.94 | 3155096.1 | 30.2588 | -96.6741 | 344.61
5413 | 4.98 | 318.81 | 5356.67 | 639.25 | -179.08 | -641.69 | 1.09 | -0.48 | -10.87 | -120.92 | 94 | 5064.67 | 234345.82 | 3155091.12 | 30.2588 | -96.6742 | 344.35
5506 | 3.77 | 326.36 | 5449.4 | 644.84 | -183.43 | -648.71 | 1.44 | -1.3 | 8.12 | 158.28 | 93 | 5157.4 | 234351.41 | 3155086.77 | 30.2588 | -96.6742 | 344.12
5599 | 3.59 | 332.41 | 5542.21 | 649.96 | -186.48 | -654.67 | 0.46 | -0.19 | 6.51 | 117.87 | 93 | 5250.21 | 234356.53 | 3155083.72 | 30.2588 | -96.6742 | 343.99
5693 | 1.68 | 356.24 | 5636.11 | 653.94 | -187.93 | -658.84 | 2.3 | -2.03 | 25.35 | 161.7 | 94 | 5344.11 | 234360.51 | 3155082.27 | 30.2588 | -96.6742 | 343.97
5787 | 1.05 | 351.54 | 5730.08 | 656.17 | -188.15 | -660.87 | 0.68 | -0.67 | -5 | -172.27 | 94 | 5438.08 | 234362.74 | 3155082.05 | 30.2588 | -96.6742 | 344
5881 | 0.66 | 88.97 | 5824.07 | 657.03 | -187.73 | -661.4 | 1.39 | -0.41 | 103.65 | 150.04 | 94 | 5532.07 | 234363.6 | 3155082.47 | 30.2588 | -96.6742 | 344.05
5974 | 0.81 | 84.64 | 5917.07 | 657.1 | -186.54 | -660.86 | 0.17 | 0.16 | -4.66 | -22.49 | 93 | 5625.07 | 234363.67 | 3155083.66 | 30.2588 | -96.6742 | 344.15
6067 | 0.68 | 61.74 | 6010.06 | 657.43 | -185.4 | -660.56 | 0.35 | -0.14 | -24.62 | -124.75 | 93 | 5718.06 | 234364 | 3155084.8 | 30.2588 | -96.6742 | 344.25
6161 | 0.52 | 47.85 | 6104.05 | 657.98 | -184.59 | -660.62 | 0.23 | -0.17 | -14.78 | -144.53 | 94 | 5812.05 | 234364.55 | 3155085.61 | 30.2588 | -96.6742 | 344.33
6255 | 0.75 | 4.54 | 6198.05 | 658.88 | -184.23 | -661.21 | 0.55 | 0.24 | -46.07 | -87.13 | 94 | 5906.05 | 234365.45 | 3155085.97 | 30.2588 | -96.6742 | 344.38
6349 | 0.89 | 0.96 | 6292.04 | 660.22 | -184.17 | -662.34 | 0.16 | 0.15 | -3.81 | -21.9 | 94 | 6000.04 | 234366.79 | 3155086.03 | 30.2588 | -96.6742 | 344.41
6442 | 0.74 | 359.22 | 6385.03 | 661.54 | -184.16 | -663.47 | 0.16 | -0.16 | 1.87 | -171.5 | 93 | 6093.03 | 234368.11 | 3155086.04 | 30.2588 | -96.6742 | 344.44
6536 | 0.14 | 181.47 | 6479.03 | 662.04 | -184.17 | -663.9 | 0.94 | -0.64 | -189.1 | -179.64 | 94 | 6187.03 | 234368.61 | 3155086.03 | 30.2588 | -96.6742 | 344.45
6629 | 0.4 | 62.89 | 6572.03 | 662.07 | -183.89 | -663.79 | 0.52 | 0.28 | -127.51 | -133.33 | 93 | 6280.03 | 234368.64 | 3155086.31 | 30.2588 | -96.6742 | 344.48
6723 | 1.45 | 171.47 | 6666.02 | 661.04 | -183.42 | -662.67 | 1.73 | 1.12 | 115.51 | 122.09 | 94 | 6374.02 | 234367.61 | 3155086.78 | 30.2588 | -96.6742 | 344.49
6817 | 1.57 | 202.08 | 6759.99 | 658.67 | -183.73 | -660.78 | 0.86 | 0.13 | 32.56 | 97.04 | 94 | 6467.99 | 234365.24 | 3155086.47 | 30.2588 | -96.6742 | 344.41
6910 | 1.3 | 281.46 | 6852.96 | 657.7 | -185.24 | -660.71 | 1.98 | -0.29 | 85.35 | 136.15 | 93 | 6560.96 | 234364.27 | 3155084.96 | 30.2588 | -96.6742 | 344.27
7005 | 2.51 | 312.3 | 6947.91 | 659.32 | -187.84 | -663.42 | 1.63 | 1.27 | 32.46 | 56.38 | 95 | 6655.91 | 234365.89 | 3155082.36 | 30.2588 | -96.6742 | 344.1
7098 | 1.65 | 332.35 | 7040.85 | 661.87 | -189.96 | -666.7 | 1.2 | -0.92 | 21.56 | 149.49 | 93 | 6748.85 | 234368.44 | 3155080.24 | 30.2588 | -96.6742 | 343.99
7193 | 0.43 | 80.15 | 7135.84 | 663.15 | -190.25 | -667.94 | 1.92 | -1.28 | 113.47 | 167.05 | 95 | 6843.84 | 234369.72 | 3155079.95 | 30.2588 | -96.6742 | 343.99
7286 | 0.17 | 76.65 | 7228.84 | 663.24 | -189.77 | -667.78 | 0.28 | -0.28 | -3.76 | -177.72 | 93 | 6936.84 | 234369.81 | 3155080.43 | 30.2588 | -96.6742 | 344.03
7379 | 0.29 | 337.05 | 7321.84 | 663.49 | -189.73 | -667.97 | 0.39 | 0.13 | 107.1 | -127.37 | 93 | 7029.84 | 234370.06 | 3155080.47 | 30.2588 | -96.6742 | 344.04
7472 | 0.83 | 37.17 | 7414.83 | 664.24 | -189.41 | -668.46 | 0.79 | 0.58 | 64.65 | 80.26 | 93 | 7122.83 | 234370.81 | 3155080.79 | 30.2588 | -96.6742 | 344.08
7566 | 1.24 | 55.46 | 7508.82 | 665.36 | -188.16 | -668.79 | 0.55 | 0.44 | 19.46 | 48.24 | 94 | 7216.82 | 234371.93 | 3155082.04 | 30.2589 | -96.6742 | 344.21
7659 | 1.25 | 24.23 | 7601.8 | 666.85 | -186.92 | -669.45 | 0.72 | 0.01 | -33.58 | -104.79 | 93 | 7309.8 | 234373.42 | 3155083.28 | 30.2589 | -96.6742 | 344.34
7750 | 0.25 | 53.14 | 7692.79 | 667.88 | -186.35 | -670.04 | 1.14 | -1.1 | 31.77 | 173.31 | 91 | 7400.79 | 234374.45 | 3155083.85 | 30.2589 | -96.6742 | 344.41
7844 | 0.05 | 203.33 | 7786.79 | 667.96 | -186.2 | -670.04 | 0.31 | -0.21 | 159.78 | 175.16 | 94 | 7494.79 | 234374.53 | 3155084 | 30.2589 | -96.6742 | 344.42
7937 | 0.37 | 355.66 | 7879.79 | 668.23 | -186.24 | -670.29 | 0.45 | 0.34 | 163.8 | 155.54 | 93 | 7587.79 | 234374.8 | 3155083.96 | 30.2589 | -96.6742 | 344.43
8031 | 0.5 | 13.66 | 7973.78 | 668.93 | -186.17 | -670.85 | 0.2 | 0.14 | 19.15 | 55.67 | 94 | 7681.78 | 234375.5 | 3155084.03 | 30.2589 | -96.6742 | 344.45
8125 | 0.73 | 19.09 | 8067.78 | 669.89 | -185.87 | -671.54 | 0.25 | 0.24 | 5.78 | 16.94 | 94 | 7775.78 | 234376.46 | 3155084.33 | 30.2589 | -96.6742 | 344.49
8218 | 1.41 | 3.87 | 8160.76 | 671.59 | -185.6 | -672.86 | 0.79 | 0.73 | -16.37 | -30.41 | 93 | 7868.76 | 234378.16 | 3155084.6 | 30.2589 | -96.6742 | 344.55
8312 | 1.74 | 25.25 | 8254.73 | 674.04 | -184.92 | -674.62 | 0.71 | 0.35 | 22.74 | 71.65 | 94 | 7962.73 | 234380.61 | 3155085.28 | 30.2589 | -96.6742 | 344.66
8406 | 1.81 | 81.42 | 8348.69 | 675.55 | -182.84 | -674.87 | 1.78 | 0.07 | 59.76 | 115.96 | 94 | 8056.69 | 234382.12 | 3155087.36 | 30.2589 | -96.6742 | 344.86
8500 | 1.59 | 86.7 | 8442.65 | 675.85 | -180.07 | -673.72 | 0.29 | -0.23 | 5.62 | 147.17 | 94 | 8150.65 | 234382.42 | 3155090.13 | 30.2589 | -96.6742 | 345.08
8593 | 1.18 | 74.22 | 8535.62 | 676.18 | -177.86 | -672.89 | 0.54 | -0.44 | -13.42 | -149.79 | 93 | 8243.62 | 234382.75 | 3155092.34 | 30.2589 | -96.6741 | 345.26
8687 | 0.72 | 21.14 | 8629.61 | 677 | -176.72 | -673.01 | 1 | -0.49 | -56.47 | -142.4 | 94 | 8337.61 | 234383.57 | 3155093.48 | 30.2589 | -96.6741 | 345.37
8781 | 1.1 | 8.3 | 8723.6 | 678.44 | -176.37 | -674.08 | 0.46 | 0.4 | -13.66 | -34.74 | 94 | 8431.6 | 234385.01 | 3155093.83 | 30.2589 | -96.6741 | 345.43
8875 | 1.3 | 358.23 | 8817.58 | 680.4 | -176.28 | -675.72 | 0.31 | 0.21 | 10.71 | -51.63 | 94 | 8525.58 | 234386.97 | 3155093.92 | 30.2589 | -96.6741 | 345.48
8969 | 1.61 | 349.45 | 8911.55 | 682.76 | -176.55 | -677.89 | 0.41 | 0.33 | -9.34 | -40.16 | 94 | 8619.55 | 234389.33 | 3155093.65 | 30.2589 | -96.6741 | 345.5
9062 | 0.72 | 18.39 | 9004.53 | 684.6 | -176.6 | -679.51 | 1.12 | -0.96 | 31.12 | 160.43 | 93 | 8712.53 | 234391.17 | 3155093.6 | 30.2589 | -96.6741 | 345.53
9156 | 0.67 | 25.41 | 9098.52 | 685.66 | -176.18 | -680.2 | 0.1 | -0.05 | 7.47 | 123.9 | 94 | 8806.52 | 234392.23 | 3155094.02 | 30.2589 | -96.6741 | 345.59
9250 | 4.46 | 157.33 | 9192.43 | 682.78 | -174.54 | -676.89 | 5.25 | 4.03 | 140.34 | 137.71 | 94 | 8900.43 | 234389.35 | 3155095.66 | 30.2589 | -96.6741 | 345.66
9344 | 10.74 | 164.62 | 9285.56 | 670.95 | -170.8 | -664.8 | 6.75 | 6.68 | 7.76 | 12.36 | 94 | 8993.56 | 234377.52 | 3155099.4 | 30.2589 | -96.6741 | 345.72
9437 | 17.54 | 157.99 | 9375.7 | 649.58 | -163.24 | -642.55 | 7.5 | 7.31 | -7.13 | -16.64 | 93 | 9083.7 | 234356.15 | 3155106.96 | 30.2588 | -96.6741 | 345.89
9530 | 23.14 | 153.66 | 9462.87 | 620.18 | -149.87 | -610.43 | 6.23 | 6.02 | -4.66 | -17.09 | 93 | 9170.87 | 234326.75 | 3155120.33 | 30.2587 | -96.6741 | 346.41
9625 | 26.87 | 150.95 | 9548.95 | 584.67 | -131.16 | -570.34 | 4.11 | 3.93 | -2.85 | -18.31 | 95 | 9256.95 | 234291.24 | 3155139.04 | 30.2586 | -96.674 | 347.36
9726 | 25.46 | 151.42 | 9639.6 | 545.65 | -109.69 | -525.82 | 1.41 | -1.4 | 0.47 | 171.85 | 101 | 9347.6 | 234252.22 | 3155160.51 | 30.2585 | -96.6739 | 348.63
9828 | 26.23 | 149.63 | 9731.4 | 506.95 | -87.8 | -481.37 | 1.07 | 0.75 | -1.75 | -46.19 | 102 | 9439.4 | 234213.52 | 3155182.4 | 30.2584 | -96.6739 | 350.17
9922 | 37.73 | 145.78 | 9811.01 | 465.1 | -61.03 | -431.72 | 12.42 | 12.23 | -4.1 | -11.72 | 94 | 9519.01 | 234171.67 | 3155209.17 | 30.2583 | -96.6738 | 352.52
10017 | 44.36 | 140.09 | 9882.64 | 415.52 | -23.32 | -369.86 | 8.01 | 6.98 | -5.99 | -31.59 | 95 | 9590.64 | 234122.09 | 3155246.88 | 30.2582 | -96.6737 | 356.79
10112 | 50.12 | 140.3 | 9947.11 | 361.96 | 21.3 | -301.06 | 6.07 | 6.06 | 0.22 | 1.61 | 95 | 9655.11 | 234068.53 | 3155291.5 | 30.258 | -96.6735 | 3.37
10207 | 56.83 | 145.75 | 10003.65 | 300.95 | 67.04 | -225.28 | 8.43 | 7.06 | 5.74 | 34.79 | 95 | 9711.65 | 234007.52 | 3155337.24 | 30.2578 | -96.6734 | 12.56
10302 | 64.46 | 148.98 | 10050.19 | 231.23 | 111.58 | -142.61 | 8.56 | 8.03 | 3.4 | 21.07 | 95 | 9758.19 | 233937.8 | 3155381.78 | 30.2576 | -96.6733 | 25.76
10396 | 71.03 | 151.2 | 10085.78 | 155.85 | 154.9 | -55.67 | 7.32 | 6.99 | 2.36 | 17.8 | 94 | 9793.78 | 233862.42 | 3155425.1 | 30.2574 | -96.6731 | 44.82
10490 | 75.04 | 147.83 | 10113.21 | 78.41 | 200.52 | 34.21 | 5.47 | 4.27 | -3.59 | -39.3 | 94 | 9821.21 | 233784.98 | 3155470.72 | 30.2572 | -96.673 | 68.64
10584 | 85.45 | 149.85 | 10129.11 | -0.76 | 248.36 | 126.71 | 11.27 | 11.07 | 2.15 | 11.01 | 94 | 9837.11 | 233705.81 | 3155518.56 | 30.257 | -96.6729 | 90.18
10678 | 87.53 | 151.29 | 10134.87 | -82.47 | 294.46 | 220.51 | 2.69 | 2.21 | 1.53 | 34.69 | 94 | 9842.87 | 233624.1 | 3155564.66 | 30.2568 | -96.6727 | 105.65
10773 | 87.83 | 151.07 | 10138.71 | -165.64 | 340.22 | 315.39 | 0.39 | 0.32 | -0.23 | -36.24 | 95 | 9846.71 | 233540.93 | 3155610.42 | 30.2565 | -96.6726 | 115.96
10866 | 86.26 | 152.16 | 10143.51 | -247.34 | 384.37 | 408.2 | 2.05 | -1.69 | 1.17 | 145.29 | 93 | 9851.51 | 233459.23 | 3155654.57 | 30.2563 | -96.6725 | 122.76
10961 | 86.1 | 152.1 | 10149.84 | -331.14 | 428.68 | 502.89 | 0.18 | -0.17 | -0.06 | -159.49 | 95 | 9857.84 | 233375.43 | 3155698.88 | 30.2561 | -96.6723 | 127.68
11054 | 87.1 | 152.88 | 10155.35 | -413.47 | 471.56 | 595.59 | 1.36 | 1.08 | 0.84 | 37.93 | 93 | 9863.35 | 233293.1 | 3155741.76 | 30.2558 | -96.6722 | 131.25
11148 | 86.42 | 149.6 | 10160.67 | -495.73 | 516.71 | 689.39 | 3.56 | -0.72 | -3.49 | -101.82 | 94 | 9868.67 | 233210.84 | 3155786.91 | 30.2556 | -96.6721 | 133.81
11243 | 86.73 | 149.44 | 10166.34 | -577.46 | 564.81 | 784.22 | 0.37 | 0.33 | -0.17 | -27.26 | 95 | 9874.34 | 233129.11 | 3155835.01 | 30.2554 | -96.6719 | 135.63
11337 | 86.76 | 153.36 | 10171.68 | -659.84 | 609.72 | 878 | 4.16 | 0.03 | 4.17 | 89.67 | 94 | 9879.68 | 233046.73 | 3155879.92 | 30.2551 | -96.6718 | 137.26
11432 | 86.44 | 148.64 | 10177.32 | -742.76 | 655.68 | 972.77 | 4.97 | -0.34 | -4.97 | -94.02 | 95 | 9885.32 | 232963.81 | 3155925.88 | 30.2549 | -96.6717 | 138.56
11526 | 85.9 | 147.48 | 10183.6 | -822.35 | 705.3 | 1066.53 | 1.36 | -0.57 | -1.23 | -115.05 | 94 | 9891.6 | 232884.22 | 3155975.5 | 30.2547 | -96.6715 | 139.38
11621 | 83.67 | 142.46 | 10192.24 | -899.79 | 759.58 | 1160.8 | 5.76 | -2.35 | -5.28 | -114.25 | 95 | 9900.24 | 232806.78 | 3156029.78 | 30.2545 | -96.6713 | 139.83
11716 | 83.89 | 138.86 | 10202.54 | -972.82 | 819.44 | 1254.11 | 3.77 | 0.23 | -3.79 | -86.68 | 95 | 9910.54 | 232733.75 | 3156089.64 | 30.2543 | -96.6712 | 139.89
11810 | 86.16 | 142.71 | 10210.69 | -1045.36 | 878.62 | 1346.65 | 4.74 | 2.41 | 4.1 | 59.56 | 94 | 9918.69 | 232661.21 | 3156148.82 | 30.2541 | -96.671 | 139.95
11904 | 87.54 | 146.04 | 10215.86 | -1121.64 | 933.28 | 1440.12 | 3.83 | 1.47 | 3.54 | 67.56 | 94 | 9923.86 | 232584.93 | 3156203.48 | 30.2538 | -96.6708 | 140.24
11998 | 87.52 | 148.95 | 10219.91 | -1200.83 | 983.74 | 1533.96 | 3.09 | -0.02 | 3.1 | 90.46 | 94 | 9927.91 | 232505.74 | 3156253.94 | 30.2536 | -96.6707 | 140.68
12092 | 87.8 | 151.54 | 10223.75 | -1282.36 | 1030.35 | 1627.87 | 2.77 | 0.3 | 2.76 | 83.88 | 94 | 9931.75 | 232424.21 | 3156300.55 | 30.2534 | -96.6705 | 141.22
12186 | 88.6 | 151.73 | 10226.7 | -1365.04 | 1074.99 | 1721.75 | 0.87 | 0.85 | 0.2 | 13.36 | 94 | 9934.7 | 232341.53 | 3156345.19 | 30.2532 | -96.6704 | 141.78
12280 | 89.06 | 151.48 | 10228.62 | -1447.71 | 1119.68 | 1815.67 | 0.56 | 0.49 | -0.27 | -28.52 | 94 | 9936.62 | 232258.86 | 3156389.88 | 30.2529 | -96.6703 | 142.28
12373 | 87.9 | 151.18 | 10231.09 | -1529.28 | 1164.28 | 1908.59 | 1.29 | -1.25 | -0.32 | -165.51 | 93 | 9939.09 | 232177.29 | 3156434.48 | 30.2527 | -96.6701 | 142.72
12466 | 86.39 | 148.33 | 10235.72 | -1609.51 | 1211.06 | 2001.46 | 3.46 | -1.62 | -3.06 | -118.01 | 93 | 9943.72 | 232097.06 | 3156481.26 | 30.2525 | -96.67 | 143.04
12561 | 86.82 | 154.62 | 10241.35 | -1692.79 | 1256.32 | 2096.19 | 6.62 | 0.45 | 6.62 | 86.27 | 95 | 9949.35 | 232013.78 | 3156526.52 | 30.2522 | -96.6699 | 143.42
12653 | 86.83 | 158.18 | 10246.45 | -1776.95 | 1293.09 | 2187.37 | 3.86 | 0.01 | 3.87 | 89.94 | 92 | 9954.45 | 231929.62 | 3156563.29 | 30.252 | -96.6697 | 143.96
12747 | 86.11 | 159.84 | 10252.24 | -1864.54 | 1326.7 | 2279.9 | 1.92 | -0.77 | 1.77 | 113.54 | 94 | 9960.24 | 231842.03 | 3156596.9 | 30.2518 | -96.6696 | 144.57
12841 | 86.81 | 156.36 | 10258.04 | -1951.58 | 1361.69 | 2372.65 | 3.77 | 0.74 | -3.7 | -78.72 | 94 | 9966.04 | 231754.99 | 3156631.89 | 30.2515 | -96.6695 | 145.1
12935 | 87.99 | 154.66 | 10262.31 | -2037.03 | 1400.61 | 2466.03 | 2.2 | 1.26 | -1.81 | -55.25 | 94 | 9970.31 | 231669.54 | 3156670.81 | 30.2513 | -96.6694 | 145.49
13028 | 89.32 | 157.17 | 10264.49 | -2121.9 | 1438.55 | 2558.41 | 3.05 | 1.43 | 2.7 | 62.11 | 93 | 9972.49 | 231584.67 | 3156708.75 | 30.251 | -96.6693 | 145.86
13122 | 88.31 | 155.59 | 10266.43 | -2208 | 1476.2 | 2651.71 | 1.99 | -1.07 | -1.68 | -122.61 | 94 | 9974.43 | 231498.57 | 3156746.4 | 30.2508 | -96.6692 | 146.23
13217 | 88.66 | 154.79 | 10268.94 | -2294.2 | 1516.05 | 2746.21 | 0.92 | 0.37 | -0.84 | -66.37 | 95 | 9976.94 | 231412.37 | 3156786.25 | 30.2506 | -96.6691 | 146.54
13311 | 86.09 | 153.44 | 10273.25 | -2378.68 | 1557.04 | 2839.8 | 3.09 | -2.73 | -1.44 | -152.34 | 94 | 9981.25 | 231327.89 | 3156827.24 | 30.2503 | -96.669 | 146.79
13406 | 84.79 | 149.91 | 10280.8 | -2462.02 | 1601.96 | 2934.41 | 3.95 | -1.37 | -3.72 | -110.41 | 95 | 9988.8 | 231244.55 | 3156872.16 | 30.2501 | -96.6688 | 146.95
13500 | 84.8 | 149.22 | 10289.33 | -2542.74 | 1649.38 | 3028.02 | 0.73 | 0.01 | -0.73 | -89.2 | 94 | 9997.33 | 231163.83 | 3156919.58 | 30.2499 | -96.6687 | 147.03
13594 | 85.26 | 149.31 | 10297.48 | -2623.23 | 1697.24 | 3121.67 | 0.5 | 0.49 | 0.1 | 11.03 | 94 | 10005.48 | 231083.34 | 3156967.44 | 30.2496 | -96.6686 | 147.1
13687 | 85.73 | 149.36 | 10304.78 | -2702.98 | 1744.53 | 3214.38 | 0.51 | 0.51 | 0.05 | 6.06 | 93 | 10012.78 | 231003.59 | 3157014.73 | 30.2494 | -96.6684 | 147.16
13782 | 85.59 | 148.04 | 10311.97 | -2783.92 | 1793.74 | 3309.09 | 1.39 | -0.15 | -1.39 | -96.12 | 95 | 10019.97 | 230922.65 | 3157063.94 | 30.2492 | -96.6683 | 147.21
13877 | 86.01 | 147.42 | 10318.93 | -2864.03 | 1844.32 | 3403.79 | 0.79 | 0.44 | -0.65 | -55.84 | 95 | 10026.93 | 230842.54 | 3157114.52 | 30.249 | -96.6681 | 147.22
13971 | 85.95 | 146.71 | 10325.52 | -2942.72 | 1895.3 | 3497.48 | 0.76 | -0.06 | -0.76 | -94.87 | 94 | 10033.52 | 230763.85 | 3157165.5 | 30.2487 | -96.668 | 147.22
14066 | 87.35 | 149.35 | 10331.07 | -3023.17 | 1945.51 | 3592.27 | 3.14 | 1.47 | 2.78 | 62.1 | 95 | 10039.07 | 230683.4 | 3157215.71 | 30.2485 | -96.6678 | 147.24
14161 | 87.72 | 148.97 | 10335.16 | -3104.66 | 1994.17 | 3687.18 | 0.56 | 0.39 | -0.4 | -45.75 | 95 | 10043.16 | 230601.91 | 3157264.37 | 30.2483 | -96.6677 | 147.29
14255 | 88.48 | 149.37 | 10338.27 | -3185.33 | 2042.31 | 3781.13 | 0.91 | 0.81 | 0.43 | 27.75 | 94 | 10046.27 | 230521.24 | 3157312.51 | 30.2481 | -96.6675 | 147.33
14349 | 86.05 | 149.76 | 10342.76 | -3266.28 | 2089.87 | 3875.01 | 2.62 | -2.59 | 0.41 | 170.9 | 94 | 10050.76 | 230440.29 | 3157360.07 | 30.2478 | -96.6674 | 147.39
14444 | 87.12 | 150.17 | 10348.42 | -3348.38 | 2137.34 | 3969.84 | 1.21 | 1.13 | 0.43 | 20.94 | 95 | 10056.42 | 230358.19 | 3157407.54 | 30.2476 | -96.6672 | 147.45
14538 | 86.92 | 150.37 | 10353.3 | -3429.89 | 2183.89 | 4063.7 | 0.3 | -0.21 | 0.21 | 135.04 | 94 | 10061.3 | 230276.68 | 3157454.09 | 30.2474 | -96.6671 | 147.51
14633 | 84.69 | 148.78 | 10360.25 | -3511.59 | 2231.87 | 4158.44 | 2.88 | -2.35 | -1.67 | -144.64 | 95 | 10068.25 | 230194.98 | 3157502.07 | 30.2472 | -96.667 | 147.56
14728 | 85.08 | 148.95 | 10368.72 | -3592.58 | 2280.79 | 4253.06 | 0.45 | 0.41 | 0.18 | 23.48 | 95 | 10076.72 | 230113.99 | 3157550.99 | 30.2469 | -96.6668 | 147.59
14822 | 84.77 | 148.9 | 10377.04 | -3672.77 | 2329.12 | 4346.68 | 0.33 | -0.33 | -0.05 | -170.88 | 94 | 10085.04 | 230033.8 | 3157599.32 | 30.2467 | -96.6667 | 147.62
14909 | 84.31 | 148.11 | 10385.32 | -3746.62 | 2374.36 | 4433.27 | 1.05 | -0.53 | -0.91 | -120.36 | 87 | 10093.32 | 229959.95 | 3157644.56 | 30.2465 | -96.6665 | 147.64
14940 | 83.55 | 146.46 | 10388.59 | -3772.55 | 2391.02 | 4464.08 | 5.83 | -2.45 | -5.32 | -114.94 | 31 | 10096.59 | 229934.02 | 3157661.22 | 30.2464 | -96.6665 | 147.63
15034 | 84.64 | 145.92 | 10398.26 | -3850.24 | 2443.05 | 4557.42 | 1.29 | 1.16 | -0.57 | -26.26 | 94 | 10106.26 | 229856.33 | 3157713.25 | 30.2462 | -96.6663 | 147.6
15129 | 86.61 | 145.55 | 10405.51 | -3928.52 | 2496.38 | 4651.93 | 2.11 | 2.07 | -0.39 | -10.62 | 95 | 10113.51 | 229778.05 | 3157766.58 | 30.246 | -96.6662 | 147.57
15223 | 87.27 | 143.97 | 10410.53 | -4005.18 | 2550.54 | 4745.48 | 1.82 | 0.7 | -1.68 | -67.34 | 94 | 10118.53 | 229701.39 | 3157820.74 | 30.2458 | -96.666 | 147.51
15318 | 88.17 | 144.86 | 10414.31 | -4082.38 | 2605.77 | 4840.02 | 1.33 | 0.95 | 0.94 | 44.68 | 95 | 10122.31 | 229624.19 | 3157875.97 | 30.2456 | -96.6658 | 147.45
15411 | 89.23 | 145.36 | 10416.42 | -4158.64 | 2658.96 | 4932.73 | 1.26 | 1.14 | 0.54 | 25.25 | 93 | 10124.42 | 229547.93 | 3157929.16 | 30.2453 | -96.6657 | 147.41
15506 | 88.64 | 145.4 | 10418.18 | -4236.8 | 2712.92 | 5027.46 | 0.62 | -0.62 | 0.04 | 176.12 | 95 | 10126.18 | 229469.77 | 3157983.12 | 30.2451 | -96.6655 | 147.37
15600 | 86.88 | 145.7 | 10421.86 | -4314.26 | 2766.05 | 5121.17 | 1.9 | -1.87 | 0.32 | 170.34 | 94 | 10129.86 | 229392.31 | 3158036.25 | 30.2449 | -96.6653 | 147.33
15695 | 85.67 | 142.26 | 10428.03 | -4390.92 | 2821.79 | 5215.51 | 3.83 | -1.27 | -3.62 | -109.52 | 95 | 10136.03 | 229315.65 | 3158091.99 | 30.2447 | -96.6652 | 147.27
15788 | 88.25 | 145.43 | 10432.96 | -4465.89 | 2876.56 | 5307.91 | 4.39 | 2.77 | 3.41 | 50.91 | 93 | 10140.96 | 229240.68 | 3158146.76 | 30.2445 | -96.665 | 147.21
15882 | 86.56 | 147.97 | 10437.22 | -4544.37 | 2928.11 | 5401.69 | 3.24 | -1.8 | 2.7 | 123.72 | 94 | 10145.22 | 229162.2 | 3158198.31 | 30.2443 | -96.6649 | 147.2
15976 | 87.13 | 150.03 | 10442.39 | -4624.81 | 2976.45 | 5495.54 | 2.27 | 0.61 | 2.19 | 74.57 | 94 | 10150.39 | 229081.76 | 3158246.65 | 30.244 | -96.6647 | 147.24
16071 | 86.4 | 147.47 | 10447.76 | -4705.89 | 3025.65 | 5590.37 | 2.8 | -0.77 | -2.69 | -106.01 | 95 | 10155.76 | 229000.68 | 3158295.85 | 30.2438 | -96.6646 | 147.26
16163 | 86.27 | 148.88 | 10453.64 | -4783.9 | 3074.06 | 5682.15 | 1.54 | -0.14 | 1.53 | 95.32 | 92 | 10161.64 | 228922.67 | 3158344.26 | 30.2436 | -96.6644 | 147.28
16257 | 86.81 | 150.81 | 10459.31 | -4865.03 | 3121.2 | 5775.97 | 2.13 | 0.57 | 2.05 | 74.4 | 94 | 10167.31 | 228841.54 | 3158391.4 | 30.2434 | -96.6643 | 147.32
16350 | 88.38 | 150.29 | 10463.21 | -4945.94 | 3166.88 | 5868.87 | 1.78 | 1.69 | -0.56 | -18.32 | 93 | 10171.21 | 228760.63 | 3158437.08 | 30.2431 | -96.6641 | 147.37
16445 | 87.63 | 151.32 | 10466.52 | -5028.81 | 3213.19 | 5963.79 | 1.34 | -0.79 | 1.08 | 126.09 | 95 | 10174.52 | 228677.76 | 3158483.39 | 30.2429 | -96.664 | 147.42
16539 | 89.26 | 150.73 | 10469.07 | -5111.02 | 3258.71 | 6057.72 | 1.84 | 1.73 | -0.63 | -19.9 | 94 | 10177.07 | 228595.55 | 3158528.91 | 30.2427 | -96.6639 | 147.48
16634 | 88.71 | 150.86 | 10470.75 | -5193.93 | 3305.05 | 6152.68 | 0.59 | -0.58 | 0.14 | 166.7 | 95 | 10178.75 | 228512.64 | 3158575.25 | 30.2424 | -96.6637 | 147.53
16729 | 86.66 | 151.46 | 10474.59 | -5277.07 | 3350.84 | 6247.56 | 2.25 | -2.16 | 0.63 | 163.71 | 95 | 10182.59 | 228429.5 | 3158621.04 | 30.2422 | -96.6636 | 147.59
16824 | 85.16 | 151.42 | 10481.37 | -5360.29 | 3396.14 | 6342.26 | 1.58 | -1.58 | -0.04 | -178.48 | 95 | 10189.37 | 228346.28 | 3158666.34 | 30.242 | -96.6635 | 147.64
16918 | 84.65 | 150.96 | 10489.72 | -5442.33 | 3441.26 | 6435.84 | 0.73 | -0.54 | -0.49 | -138.08 | 94 | 10197.72 | 228264.24 | 3158711.46 | 30.2417 | -96.6633 | 147.69
17013 | 85.25 | 150.03 | 10498.08 | -5524.69 | 3487.86 | 6530.46 | 1.16 | 0.63 | -0.98 | -57.11 | 95 | 10206.08 | 228181.88 | 3158758.06 | 30.2415 | -96.6632 | 147.73
17108 | 86.08 | 148.9 | 10505.26 | -5606.28 | 3535.99 | 6625.19 | 1.47 | 0.87 | -1.19 | -53.67 | 95 | 10213.26 | 228100.29 | 3158806.19 | 30.2413 | -96.663 | 147.76
17202 | 86.44 | 149.93 | 10511.39 | -5687.03 | 3583.72 | 6718.98 | 1.16 | 0.38 | 1.1 | 70.73 | 94 | 10219.39 | 228019.54 | 3158853.92 | 30.2411 | -96.6629 | 147.78
17296 | 87.25 | 149.15 | 10516.56 | -5767.93 | 3631.3 | 6812.84 | 1.2 | 0.86 | -0.83 | -43.9 | 94 | 10224.56 | 227938.64 | 3158901.5 | 30.2408 | -96.6628 | 147.81
17390 | 87.81 | 147.96 | 10520.62 | -5848.05 | 3680.29 | 6906.74 | 1.4 | 0.6 | -1.27 | -64.8 | 94 | 10228.62 | 227858.52 | 3158950.49 | 30.2406 | -96.6626 | 147.82
17484 | 88.12 | 150.25 | 10523.95 | -5928.66 | 3728.52 | 7000.67 | 2.46 | 0.33 | 2.44 | 82.33 | 94 | 10231.95 | 227777.91 | 3158998.72 | 30.2404 | -96.6625 | 147.83
17578 | 87.04 | 151.59 | 10527.92 | -6010.73 | 3774.16 | 7094.55 | 1.83 | -1.15 | 1.43 | 128.92 | 94 | 10235.92 | 227695.84 | 3159044.36 | 30.2401 | -96.6623 | 147.88
17671 | 84.93 | 150.87 | 10534.43 | -6092.05 | 3818.81 | 7187.28 | 2.4 | -2.27 | -0.77 | -161.23 | 93 | 10242.43 | 227614.52 | 3159089.01 | 30.2399 | -96.6622 | 147.92
17765 | 84.88 | 150.97 | 10542.78 | -6173.87 | 3864.32 | 7280.88 | 0.12 | -0.05 | 0.11 | 116.66 | 94 | 10250.78 | 227532.7 | 3159134.52 | 30.2397 | -96.6621 | 147.96
17860 | 85.55 | 150.68 | 10550.71 | -6256.53 | 3910.47 | 7375.52 | 0.77 | 0.71 | -0.31 | -23.34 | 95 | 10258.71 | 227450.04 | 3159180.67 | 30.2395 | -96.6619 | 147.99
17954 | 87.38 | 150.04 | 10556.5 | -6338.07 | 3956.86 | 7469.33 | 2.06 | 1.95 | -0.68 | -19.26 | 94 | 10264.5 | 227368.5 | 3159227.06 | 30.2392 | -96.6618 | 148.02
18049 | 86.82 | 150.05 | 10561.31 | -6420.27 | 4004.24 | 7564.2 | 0.59 | -0.59 | 0.01 | 178.98 | 95 | 10269.31 | 227286.3 | 3159274.44 | 30.239 | -96.6616 | 148.05
18143 | 86.12 | 150.26 | 10567.1 | -6501.65 | 4050.93 | 7658.01 | 0.78 | -0.74 | 0.22 | 163.34 | 94 | 10275.1 | 227204.92 | 3159321.13 | 30.2388 | -96.6615 | 148.07
18238 | 85.6 | 150.69 | 10573.95 | -6584.1 | 4097.62 | 7752.75 | 0.71 | -0.55 | 0.45 | 140.5 | 95 | 10281.95 | 227122.47 | 3159367.82 | 30.2385 | -96.6614 | 148.1
18332 | 85.89 | 149.59 | 10580.93 | -6665.39 | 4144.29 | 7846.49 | 1.21 | 0.31 | -1.17 | -75.23 | 94 | 10288.93 | 227041.18 | 3159414.49 | 30.2383 | -96.6612 | 148.13
18427 | 87.38 | 148.99 | 10586.51 | -6746.93 | 4192.73 | 7941.32 | 1.69 | 1.57 | -0.63 | -21.92 | 95 | 10294.51 | 226959.64 | 3159462.93 | 30.2381 | -96.6611 | 148.14
18521 | 86.56 | 148.69 | 10591.47 | -6827.25 | 4241.3 | 8035.18 | 0.93 | -0.87 | -0.32 | -159.94 | 94 | 10299.47 | 226879.32 | 3159511.5 | 30.2379 | -96.6609 | 148.15
18616 | 88.5 | 147.71 | 10595.57 | -6907.91 | 4291.31 | 8130.06 | 2.29 | 2.04 | -1.03 | -26.8 | 95 | 10303.57 | 226798.66 | 3159561.51 | 30.2376 | -96.6608 | 148.15
18709 | 87.04 | 147.62 | 10599.19 | -6986.43 | 4341.01 | 8222.94 | 1.57 | -1.57 | -0.1 | -176.48 | 93 | 10307.19 | 226720.14 | 3159611.21 | 30.2374 | -96.6606 | 148.15
18804 | 87.9 | 146.03 | 10603.38 | -7065.86 | 4392.94 | 8317.74 | 1.9 | 0.91 | -1.67 | -61.61 | 95 | 10311.38 | 226640.71 | 3159663.14 | 30.2372 | -96.6605 | 148.13
18898 | 85.58 | 147.95 | 10608.73 | -7144.55 | 4444.06 | 8411.49 | 3.2 | -2.47 | 2.04 | 140.48 | 94 | 10316.73 | 226562.02 | 3159714.26 | 30.237 | -96.6603 | 148.12
18992 | 85.83 | 148.63 | 10615.77 | -7224.29 | 4493.33 | 8505.2 | 0.77 | 0.27 | 0.72 | 69.79 | 94 | 10323.77 | 226482.28 | 3159763.53 | 30.2367 | -96.6602 | 148.12
19087 | 87.42 | 148.53 | 10621.36 | -7305.22 | 4542.77 | 8600.02 | 1.68 | 1.67 | -0.11 | -3.6 | 95 | 10329.36 | 226401.35 | 3159812.97 | 30.2365 | -96.66 | 148.12
19181 | 85.45 | 149.96 | 10627.2 | -7385.84 | 4590.74 | 8693.83 | 2.59 | -2.1 | 1.52 | 144.12 | 94 | 10335.2 | 226320.73 | 3159860.94 | 30.2363 | -96.6599 | 148.14
19276 | 86.17 | 149.47 | 10634.14 | -7467.65 | 4638.52 | 8788.58 | 0.92 | 0.76 | -0.52 | -34.18 | 95 | 10342.14 | 226238.92 | 3159908.72 | 30.2361 | -96.6598 | 148.15

## 11_12_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/12/2021 |  |  | Report Time: |  | 01:59-24:00
|  |  |  | Daily Cost($): |  | 9400 |  |  | Well Cost($): |  | 9400
|  |  |  | 24hr Summary: |  | POOH, L/D BHA #3, M/U BHA 4, TIH for open hole ST
|  |  |  | 24hr Lookahead: |  | Time Drill
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14900 |  | 14900 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 14904 |  | 14904 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 4 |  | 4 |  | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  | 4 |  | 4 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 4.50 / 3.00 |  | 4.50 / 3.00 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  | 4.5 |  | 4.5 |  | SN: |  | 13618580 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  | 0.00 / 0.89 |  | 0.00 / 0.89 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 21 |  | 21 |  | Grade In: |  | New
% Slide: |  | 100 |  | 100 |  | Grade Out: |  | 1-1-WT-C-X-I-NO-DMF
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 +.001 |  |  |  | 5.25 | 2 |  |  |  |  | 33.27 |  | 34.27
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.92
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.78
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.68
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.79
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.42
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 132.06
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.39
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.75
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.38
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.37
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.77
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.5
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.75
5948.75
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250007 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0.89 | 15 | 0 | 197 | 290 | 3900 | 3800 | 0 | 270 | 220 | 170 | 0 | 0
Run | 0.89 | 15 | 0 | 197 | 290 | 3900 | 3800 | 0 | 270 | 220 | 170 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 11/12/2021 |  | 23 |  | 2000 |  | 1 | 2000
Perdiem Per Hand |  |  |  |  | 11/12/2021 |  | 7 |  | 100 |  | 4 | 400
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/12/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/12/2021 |  | 3 |  | -400 |  | 1 | -400
Total | [11 empty] | 9400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/12/2021 | 01:59 | 02:00 | 0.02 | 14900 | 14900 | 0 | ST |  | 24B | Dailies in OH
11/12/2021 | 02:00 | 03:00 | 1 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 6O | M/U BHA #4
11/12/2021 | 03:00 | 08:45 | 5.75 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 6A | TIH t/ 9723
11/12/2021 | 08:45 | 10:15 | 1.5 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 9A | Slip and cut
11/12/2021 | 10:15 | 10:45 | 0.5 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 8P | Service rig
11/12/2021 | 10:45 | 11:00 | 0.25 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 6A | TIH t/ 10290
11/12/2021 | 11:00 | 11:30 | 0.5 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 8K | Check torque on ST80
11/12/2021 | 11:30 | 11:45 | 0.25 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 6A | TIH t/ 10514
11/12/2021 | 11:45 | 12:30 | 0.75 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 5D | Pump kill mud down the backside
11/12/2021 | 12:30 | 13:30 | 1 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 8O | Swap rotating head
11/12/2021 | 13:30 | 14:30 | 1 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 3C | W/R 10514 - 11050
11/12/2021 | 14:30 | 18:15 | 3.75 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 6A | TIH
11/12/2021 | 18:15 | 19:30 | 1.25 | 14900 | 14900 | 0 | ST | 1: BHA 4 | 5A | Working Trough @ 160L
11/12/2021 | 19:30 | 24:00 | 4.5 | 14900 | 14904 | 4 | ST | 1: BHA 4 | 2J | Slide Drill f/14900.00 t/14904.00, TF -150G, w/WOB 15,Flow 290, Press 3900, Tq 0, ROP 0.89, Diff 100.00, Temp 144.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_13_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/13/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 11200 |  |  | Well Cost($): |  | 20600
|  |  |  | 24hr Summary: |  | Attempt to Sidetrack. Motor Stalled and held pressure
|  |  |  | 24hr Lookahead: |  | POOH t/ inspect BHA, TIH, continue sidetrack
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14904 |  | 14906 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 14906 |  | 14906 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): | [9 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 0.00 / 0.75 |  | 0.00 / 0.75 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: | [5 empty] | SN: |  | 13618580 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 9.75 |  | 9.75 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-WT-C-X-I-NO-DMF
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 +.001 |  |  |  | 5.25 | 2 |  |  |  |  | 33.27 |  | 34.27
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.92
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.78
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.68
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.79
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.42
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 132.06
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.39
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.75
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.38
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.37
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.77
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.5
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.75
5948.75
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250007 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0.87 | 15 | 0 | 197 | 290 | 3900 | 3800 | 0 | 270 | 220 | 170 | 0 | 0
Run | 0.88 | 15 | 0 | 197 | 290 | 3900 | 3800 | 0 | 270 | 220 | 170 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/13/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/13/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 11/13/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 11/13/2021 |  | 23 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 11/13/2021 |  | 9 |  | 1000 |  | 1 | 1000
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 11/13/2021 |  | 24 |  | 800 |  | 1 | 800
Total | [11 empty] | 11200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/13/2021 | 00:00 | 02:18 | 2.3 | 14904 | 14906 | 2 | ST | 1: BHA 4 | 2J | Slide Drill f/14904.00 t/14906.00, TF -150G, w/WOB 15.00,Flow 290.00, Press 3900.00, Tq 0.00, ROP 0.87, Diff 100.00, Temp 144.00
11/13/2021 | 02:18 | 02:45 | 0.45 | 14906 | 14906 | 0 | ST | 1: BHA 4 | 3B | Working Stuck Pipe
11/13/2021 | 02:45 | 12:45 | 10 | 14906 | 14906 | 0 | ST | 1: BHA 4 | 6B | POOH
11/13/2021 | 12:45 | 13:30 | 0.75 | 14906 | 14906 | 0 | ST | 1: BHA 4 | 6P | L/D BHA #4
11/13/2021 | 13:30 | 14:15 | 0.75 | 14906 | 14906 | 0 | ST | 2: BHA 5 | 6O | P/U BHA #5 and test MWD
11/13/2021 | 14:15 | 23:15 | 9 | 14906 | 14906 | 0 | ST | 2: BHA 5 | 6A | TIH
11/13/2021 | 23:15 | 24:00 | 0.75 | 14906 | 14906 | 0 | ST | 2: BHA 5 | 5A | Work TF for ST
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_14_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/14/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 30600
|  |  |  | 24hr Summary: |  | St and cont drilling
|  |  |  | 24hr Lookahead: |  | St and cont drilling
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14906 |  | 14906 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 15646 |  | 15646 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 740 |  | 740 |  | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  | 85 |  | 85 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): |  | 655 |  | 655 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 20.62 / 2.05 |  | 20.62 / 2.80 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  | 11.62 |  | 11.62 |  | SN: |  | 13601237 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 9 |  | 9 |  | Bit # |  | 5 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  | 72.78 / 7.32 |  | 72.78 / 7.32 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 33.75 |  | Grade In: |  | New
% Slide: |  | 11.49 |  | 11.49 |  | Grade Out: |  | 4-6-RO-A-X-I-BT-HP
% Rotary: |  | 88.51 |  | 88.51 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 -.001 |  |  |  | 5.25 | 2 |  |  |  |  | 32.97 |  | 33.97
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.62
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.48
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.38
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.49
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.12
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 131.76
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.09
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.45
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.08
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.07
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.47
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.2
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.45
5948.45
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14909 | 84.31 | 148.11 | 10385.32 | -3746.62 | 2374.36 | 1.05 |  | -120.36 | 4433.27 | -0.53 |  | -0.91 | 87
14940 | 83.55 | 146.46 | 10388.59 | -3772.55 | 2391.02 | 5.83 |  | -114.94 | 4464.08 | -2.45 |  | -5.32 | 31
15034 | 84.64 | 145.92 | 10398.26 | -3850.24 | 2443.05 | 1.29 |  | -26.26 | 4557.42 | 1.16 |  | -0.57 | 94
15129 | 86.61 | 145.55 | 10405.51 | -3928.52 | 2496.38 | 2.11 |  | -10.62 | 4651.93 | 2.07 |  | -0.39 | 95
15223 | 87.27 | 143.97 | 10410.53 | -4005.18 | 2550.54 | 1.82 |  | -67.34 | 4745.48 | 0.7 |  | -1.68 | 94
15318 | 88.17 | 144.86 | 10414.31 | -4082.38 | 2605.77 | 1.33 |  | 44.68 | 4840.02 | 0.95 |  | 0.94 | 95
15411 | 89.23 | 145.36 | 10416.42 | -4158.64 | 2658.96 | 1.26 |  | 25.25 | 4932.73 | 1.14 |  | 0.54 | 93
15506 | 88.64 | 145.4 | 10418.18 | -4236.8 | 2712.92 | 0.62 |  | 176.12 | 5027.46 | -0.62 |  | 0.04 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 35.89 | 18.11 | 45.41 | 291 | 361.57 | 4548.04 | 4309.38 | 0 | 318 | 188.1 | 105 | 13.9 | 0
Run | 35.89 | 18.11 | 45.41 | 291 | 361.57 | 4548.04 | 4309.38 | 0 | 318 | 188.1 | 105 | 13.9 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/14/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 11/14/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 11/14/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 11/14/2021 |  | 19 |  | 600 |  | 1 | 600
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/14/2021 |  | 2 |  | 7400 |  | 1 | 7400
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/14/2021 | 00:00 | 06:00 | 6 | 14906 | 14916 | 10 | ST | 2: BHA 5 | 2J | Slide Drill f/14906.00 t/14916.00, TF 130G, w/WOB 20,Flow 290, Press 4100, Tq 0, ROP 1.67, Diff 180.00, Temp 217.00
11/14/2021 | 06:00 | 07:20 | 1.33 | 14916 | 14916 | 0 | ST | 2: BHA 5 | 3B | Work tight hole and free string
11/14/2021 | 07:20 | 08:15 | 0.92 | 14916 | 14916 | 0 | ST | 2: BHA 5 | 5A | Work string back to bottom and maintain orientation for sidetrack
11/14/2021 | 08:15 | 09:10 | 0.92 | 14916 | 14920 | 4 | ST | 2: BHA 5 | 2J | Slide Drill f/14916.00 t/14920.00, TF -120.00G, w/WOB 10.00,Flow 370.00, Press 4450.00, Tq 0.00, ROP 4.36, Diff 100.00, Temp 217.00
11/14/2021 | 09:10 | 10:45 | 1.58 | 14920 | 14930 | 10 | ST | 2: BHA 5 | 2J | Slide Drill f/14920.00 t/14930.00, TF -90.00G, w/WOB 10.00,Flow 370.00, Press 4450.00, Tq 0.00, ROP 6.32, Diff 100.00, Temp 217.00
11/14/2021 | 10:45 | 11:55 | 1.17 | 14930 | 14938 | 8 | ST | 2: BHA 5 | 2J | Slide Drill f/14930.00 t/14938.00, TF -60.00G, w/WOB 10.00,Flow 370.00, Press 4450.00, Tq 0.00, ROP 6.86, Diff 100.00, Temp 217.00
11/14/2021 | 11:55 | 12:10 | 0.25 | 14938 | 14938 | 0 | ST | 2: BHA 5 | 5A | Work string free and begin rotating
11/14/2021 | 12:10 | 13:00 | 0.83 | 14938 | 14974 | 36 | LAT | 2: BHA 5 | 2K | Rotary Drill f/14938.00 t/14974.00, w/WOB 25.00,Flow 370.00, RPM 35.00, Press 4650.00, Tq 12.00, ROP 43.20, Diff 300.00, Temp 217.00
11/14/2021 | 13:00 | 13:10 | 0.17 | 14974 | 14974 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 13:10 | 13:50 | 0.67 | 14974 | 15006 | 32 | LAT | 2: BHA 5 | 2K | Rotary Drill f/14974.00 t/15006.00, w/WOB 30.00,Flow 370.00, RPM 40.00, Press 4900.00, Tq 15.00, ROP 48.00, Diff 400.00, Temp 217.00
11/14/2021 | 13:50 | 13:55 | 0.08 | 15006 | 15006 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 13:55 | 15:29 | 1.57 | 15006 | 15099 | 93 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15006.00 t/15099.00, w/WOB 27.51,Flow 368.80, RPM 48.24, Press 4937.82, Tq 14.37, ROP 59.36, Diff 691.41, Temp 141.80
11/14/2021 | 15:29 | 15:38 | 0.15 | 15099 | 15099 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 15:38 | 16:03 | 0.42 | 15099 | 15115 | 16 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15099.00 t/15115.00, w/WOB 15.43,Flow 368.90, RPM 52.92, Press 4232.26, Tq 13.42, ROP 38.40, Diff 32.72, Temp 145.40
11/14/2021 | 16:03 | 16:26 | 0.38 | 15115 | 15123 | 8 | LAT | 2: BHA 5 | 2J | Slide Drill f/15115.00 t/15123.00, TF -3.41G, w/WOB 13.15,Flow 369.18, Press 4619.81, Tq 0, ROP 20.87, Diff 205.90, Temp 134.60
11/14/2021 | 16:26 | 17:31 | 1.08 | 15123 | 15194 | 71 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15123.00 t/15194.00, w/WOB 23.66,Flow 368.86, RPM 57.80, Press 4944.94, Tq 15.51, ROP 65.54, Diff 444.94, Temp 143.60
11/14/2021 | 17:31 | 17:40 | 0.15 | 15194 | 15194 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 17:40 | 18:41 | 1.02 | 15194 | 15288 | 94 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15194.00 t/15288.00, w/WOB 29.26,Flow 368.95, RPM 59.25, Press 5219.71, Tq 19.32, ROP 92.46, Diff 719.71, Temp 145.40
11/14/2021 | 18:41 | 18:46 | 0.08 | 15288 | 15288 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 18:46 | 19:20 | 0.57 | 15288 | 15303 | 15 | LAT | 2: BHA 5 | 2J | Slide Drill f/15288.00 t/15303.00, TF 90.00G, w/WOB 35.00,Flow 368.95, Press 5219.71, Tq 19.32, ROP 26.47, Diff 719.71, Temp 145.40
11/14/2021 | 19:20 | 20:12 | 0.87 | 15303 | 15383 | 80 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15303.00 t/15383.00, w/WOB 30.00,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 92.31, Diff 719.71, Temp 145.40
11/14/2021 | 20:12 | 20:17 | 0.08 | 15383 | 15383 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 20:17 | 21:05 | 0.8 | 15383 | 15476 | 93 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15383.00 t/15476.00, w/WOB 30.00,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 116.25, Diff 719.71, Temp 145.40
11/14/2021 | 21:05 | 21:10 | 0.08 | 15476 | 15476 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 21:10 | 21:36 | 0.43 | 15476 | 15491 | 15 | LAT | 2: BHA 5 | 2J | Slide Drill f/15476.00 t/15491.00, TF 140.00G, w/WOB 35.00,Flow 368.95, Press 5219.71, Tq 22.00, ROP 34.62, Diff 719.71, Temp 145.40
11/14/2021 | 21:36 | 22:43 | 1.12 | 15491 | 15571 | 80 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15491.00 t/15571.00, w/WOB 30.00,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 71.64, Diff 719.71, Temp 145.40
11/14/2021 | 22:43 | 22:48 | 0.08 | 15571 | 15571 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/14/2021 | 22:48 | 23:22 | 0.57 | 15571 | 15586 | 15 | LAT | 2: BHA 5 | 2J | Slide Drill f/15571.00 t/15586.00, TF 140.00G, w/WOB 35.00,Flow 368.95, Press 5219.71, Tq 22.00, ROP 26.47, Diff 719.71, Temp 145.40
11/14/2021 | 23:22 | 24:00 | 0.63 | 15586 | 15646 | 60 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15586.00 t/15646.00, w/WOB 30.00,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 94.74, Diff 719.71, Temp 145.40
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_15_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/15/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 40600
|  |  |  | 24hr Summary: |  | St and cont drilling ahead
|  |  |  | 24hr Lookahead: |  | Drilling ahead
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15646 |  | 14906 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 16460 |  | 16460 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 814 |  | 1554 |  | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  | 119 |  | 204 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): |  | 695 |  | 1350 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 13.27 / 4.48 |  | 33.88 / 7.28 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  | 5.18 |  | 16.8 |  | SN: |  | 13601237 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 8.08 |  | 17.08 |  | Bit # |  | 5 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  | 85.98 / 22.96 |  | 79.02 / 12.14 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 57.75 |  | Grade In: |  | New
% Slide: |  | 14.62 |  | 13.13 |  | Grade Out: |  | 4-6-RO-A-X-I-BT-HP
% Rotary: |  | 85.38 |  | 86.87 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 -.001 |  |  |  | 5.25 | 2 |  |  |  |  | 32.97 |  | 33.97
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.62
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.48
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.38
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.49
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.12
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 131.76
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.09
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.45
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.08
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.07
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.47
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.2
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.45
5948.45
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15600 | 86.88 | 145.7 | 10421.86 | -4314.26 | 2766.05 | 1.9 |  | 170.34 | 5121.17 | -1.87 |  | 0.32 | 94
15695 | 85.67 | 142.26 | 10428.03 | -4390.92 | 2821.79 | 3.83 |  | -109.52 | 5215.51 | -1.27 |  | -3.62 | 95
15788 | 88.25 | 145.43 | 10432.96 | -4465.89 | 2876.56 | 4.39 |  | 50.91 | 5307.91 | 2.77 |  | 3.41 | 93
15882 | 86.56 | 147.97 | 10437.22 | -4544.37 | 2928.11 | 3.24 |  | 123.72 | 5401.69 | -1.8 |  | 2.7 | 94
15976 | 87.13 | 150.03 | 10442.39 | -4624.81 | 2976.45 | 2.27 |  | 74.57 | 5495.54 | 0.61 |  | 2.19 | 94
16071 | 86.4 | 147.47 | 10447.76 | -4705.89 | 3025.65 | 2.8 |  | -106.01 | 5590.37 | -0.77 |  | -2.69 | 95
16163 | 86.27 | 148.88 | 10453.64 | -4783.9 | 3074.06 | 1.54 |  | 95.32 | 5682.15 | -0.14 |  | 1.53 | 92
16257 | 86.81 | 150.81 | 10459.31 | -4865.03 | 3121.2 | 2.13 |  | 74.4 | 5775.97 | 0.57 |  | 2.05 | 94
16350 | 88.38 | 150.29 | 10463.21 | -4945.94 | 3166.88 | 1.78 |  | -18.32 | 5868.87 | 1.69 |  | -0.56 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 61.36 | 26.63 | 66.76 | 321 | 373.22 | 5004.02 | 4427.16 | 0 | 330 | 176.88 | 0 | 18.15 | 0
Run | 45.86 | 25.62 | 61.69 | 313 | 369.46 | 4939.52 | 4414.11 | 0 | 327 | 177.86 | 105 | 17.99 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/15/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/15/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 11/15/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 11/15/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 11/15/2021 |  | 19 |  | 600 |  | 1 | 600
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/15/2021 | 00:00 | 00:14 | 0.23 | 15646 | 15665 | 19 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15646.00 t/15665.00, w/WOB 30.00,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 81.43, Diff 719.71, Temp 145.40
11/15/2021 | 00:14 | 01:18 | 1.07 | 15665 | 15665 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 01:18 | 02:08 | 0.83 | 15665 | 15760 | 95 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15665.00 t/15760.00, w/WOB 25,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 114.00, Diff 719.71, Temp 145.40
11/15/2021 | 02:08 | 02:13 | 0.08 | 15760 | 15760 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 02:13 | 02:50 | 0.62 | 15760 | 15780 | 20 | LAT | 2: BHA 5 | 2J | Slide Drill f/15760.00 t/15780.00, TF 90G, w/WOB 35,Flow 368.95, Press 5219.71, Tq 22.00, ROP 32.43, Diff 719.71, Temp 145.40
11/15/2021 | 02:50 | 03:11 | 0.35 | 15780 | 15820 | 40 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15780.00 t/15820.00, w/WOB 25,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 114.29, Diff 719.71, Temp 145.40
11/15/2021 | 03:11 | 04:03 | 0.87 | 15820 | 15835 | 15 | LAT | 2: BHA 5 | 2J | Slide Drill f/15820.00 t/15835.00, TF 120G, w/WOB 45,Flow 368.95, Press 5219.71, Tq 22.00, ROP 17.31, Diff 719.71, Temp 145.40
11/15/2021 | 04:03 | 04:19 | 0.27 | 15835 | 15853 | 18 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15835.00 t/15853.00, w/WOB 30.00,Flow 368.95, RPM 59.25, Press 5219.71, Tq 22.00, ROP 67.50, Diff 719.71, Temp 145.40
11/15/2021 | 04:19 | 04:25 | 0.1 | 15853 | 15853 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 04:25 | 05:05 | 0.67 | 15853 | 15873 | 20 | LAT | 2: BHA 5 | 2J | Slide Drill f/15853.00 t/15873.00, TF 120.00G, w/WOB 30.00,Flow 368.95, Press 5219.71, Tq 22.00, ROP 30.00, Diff 719.71, Temp 138.00
11/15/2021 | 05:05 | 06:05 | 1 | 15873 | 15947 | 74 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15873.00 t/15947.00, w/WOB 30.00,Flow 368.95, RPM 70.00, Press 5219.71, Tq 22.00, ROP 74.00, Diff 719.71, Temp 145.40
11/15/2021 | 06:05 | 06:13 | 0.13 | 15947 | 15947 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 06:13 | 06:22 | 0.15 | 15947 | 15957 | 10 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15947.00 t/15957.00, w/WOB 14.33,Flow 369.30, RPM 50.00, Press 4240.65, Tq 15.06, ROP 66.67, Diff -108.42, Temp 145.40
11/15/2021 | 06:22 | 07:00 | 0.63 | 15957 | 15972 | 15 | LAT | 2: BHA 5 | 2J | Slide Drill f/15957.00 t/15972.00, TF 94.22G, w/WOB 16.33,Flow 368.86, Press 4539.90, Tq 0.00, ROP 23.68, Diff 251.76, Temp 141.80
11/15/2021 | 07:00 | 07:43 | 0.72 | 15972 | 16041 | 69 | LAT | 2: BHA 5 | 2K | Rotary Drill f/15972.00 t/16041.00, w/WOB 33.97,Flow 368.95, RPM 70, Press 4747.67, Tq 18.49, ROP 96.28, Diff 680.89, Temp 141.80
11/15/2021 | 07:43 | 08:06 | 0.38 | 16041 | 16041 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection Recycle x 2
11/15/2021 | 08:06 | 08:59 | 0.88 | 16041 | 16137 | 96 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16041.00 t/16137.00, w/WOB 27.41,Flow 368.89, RPM 70, Press 4969.56, Tq 17.43, ROP 108.68, Diff 1341.45, Temp 141.80
11/15/2021 | 08:59 | 09:07 | 0.13 | 16137 | 16137 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 09:07 | 09:14 | 0.12 | 16137 | 16146 | 9 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16137.00 t/16146.00, w/WOB 15.60,Flow 368.90, RPM 50, Press 4888.76, Tq 16.31, ROP 77.14, Diff 448.42, Temp 141.80
11/15/2021 | 09:14 | 10:08 | 0.9 | 16146 | 16168 | 22 | LAT | 2: BHA 5 | 2J | Slide Drill f/16146.00 t/16168.00, TF 95.63G, w/WOB 17.11,Flow 368.50, Press 4873.25, Tq 0, ROP 24.44, Diff 121.45, Temp 136.40
11/15/2021 | 10:08 | 10:45 | 0.62 | 16168 | 16228 | 60 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16168.00 t/16228.00, w/WOB 30.70,Flow 368.76, RPM 67.18, Press 4973.06, Tq 17.46, ROP 97.30, Diff 1843.07, Temp 140.00
11/15/2021 | 10:45 | 10:53 | 0.13 | 16228 | 16228 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 10:53 | 11:00 | 0.12 | 16228 | 16238 | 10 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16228.00 t/16238.00, w/WOB 28.66,Flow 368.80, RPM 65.51, Press 5173.43, Tq 17.42, ROP 85.71, Diff 414.53, Temp 136.40
11/15/2021 | 11:00 | 11:30 | 0.5 | 16238 | 16250 | 12 | LAT | 2: BHA 5 | 2J | Slide Drill f/16238.00 t/16250.00, TF 103.32G, w/WOB 18.2,Flow 368.80, Press 5173.43, Tq 0, ROP 24.00, Diff 414.53, Temp 136.40
11/15/2021 | 11:30 | 12:13 | 0.72 | 16250 | 16323 | 73 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16250.00 t/16323.00, w/WOB 30.79,Flow 368.82, RPM 67.17, Press 5238.93, Tq 17.97, ROP 101.86, Diff 515.17, Temp 143.60
11/15/2021 | 12:13 | 12:22 | 0.15 | 16323 | 16323 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 12:22 | 13:32 | 1.17 | 16323 | 16415 | 92 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16323.00 t/16415.00, w/WOB 26.27,Flow 376.83, RPM 67.59, Press 5116.99, Tq 18.45, ROP 78.86, Diff 336.87, Temp 143.60
11/15/2021 | 13:32 | 13:49 | 0.28 | 16415 | 16415 | 0 | LAT | 2: BHA 5 | 5A | Survey & Connection
11/15/2021 | 13:49 | 14:00 | 0.18 | 16415 | 16425 | 10 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16415.00 t/16425.00, w/WOB 22.22,Flow 397.96, RPM 79.53, Press 4953.61, Tq 5.51, ROP 54.55, Diff 282.84, Temp 145.40
11/15/2021 | 14:00 | 15:00 | 1 | 16425 | 16440 | 15 | LAT | 2: BHA 5 | 2J | Slide Drill f/16425.00 t/16440.00, TF 153.30G, w/WOB 25.34,Flow 397.99, Press 4713.55, Tq 0, ROP 15.00, Diff 89.78, Temp 140.00
11/15/2021 | 15:00 | 15:44 | 0.73 | 16440 | 16460 | 20 | LAT | 2: BHA 5 | 2K | Rotary Drill f/16440.00 t/16460.00, w/WOB 27.86,Flow 397.93, RPM 70, Press 5225.59, Tq 17.36, ROP 27.27, Diff 89.37, Temp 138.20
11/15/2021 | 15:44 | 17:45 | 2.02 | 16460 | 16460 | 0 | LAT | 2: BHA 5 | 5A | Circulate
11/15/2021 | 17:45 | 24:00 | 6.25 | 16460 | 16460 | 0 | LAT | 2: BHA 5 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_16_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/16/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 11200 |  |  | Well Cost($): |  | 51800
|  |  |  | 24hr Summary: |  | POOH for bit
|  |  |  | 24hr Lookahead: |  | TIH and cont drilling
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16460 |  | 16460 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 16794 |  | 16794 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 334 |  | 334 |  | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  | 40 |  | 40 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): |  | 294 |  | 294 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 3.13 / 1.15 |  | 3.13 / 1.15 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  | 1.1 |  | 1.1 |  | SN: |  | 13601237 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 2.03 |  | 2.03 |  | Bit # |  | 5 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  | 144.59 / 36.36 |  | 144.59 / 36.36 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 17.25 |  | 17.25 |  | Grade In: |  | New
% Slide: |  | 11.98 |  | 11.98 |  | Grade Out: |  | 4-6-RO-A-X-I-BT-HP
% Rotary: |  | 88.02 |  | 88.02 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 -.001 |  |  |  | 5.25 | 2 |  |  |  |  | 32.97 |  | 33.97
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.62
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.48
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.38
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.49
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.12
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 131.76
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.09
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.45
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.08
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.07
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.47
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.2
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.45
5948.45
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16445 | 87.63 | 151.32 | 10466.52 | -5028.81 | 3213.19 | 1.34 |  | 126.09 | 5963.79 | -0.79 |  | 1.08 | 95
16539 | 89.26 | 150.73 | 10469.07 | -5111.02 | 3258.71 | 1.84 |  | -19.9 | 6057.72 | 1.73 |  | -0.63 | 94
16634 | 88.71 | 150.86 | 10470.75 | -5193.93 | 3305.05 | 0.59 |  | 166.7 | 6152.68 | -0.58 |  | 0.14 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 26.63 | 66.76 | 321 | 373.22 | 5004.02 | 4427.16 | 0 | 330 | 176.88 | 0 | 18.15 | 0
Run | 45.86 | 25.62 | 61.69 | 313 | 369.46 | 4939.52 | 4414.11 | 0 | 327 | 177.86 | 105 | 17.99 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/16/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/16/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 11/16/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 11/16/2021 |  | 23 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 11/16/2021 |  | 9 |  | 1000 |  | 1 | 1000
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 11/16/2021 |  | 24 |  | 800 |  | 1 | 800
Total | [11 empty] | 11200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/16/2021 | 00:00 | 02:30 | 2.5 | 16460 | 16460 | 0 | LAT | 2: BHA 5 | 6B | POOH
11/16/2021 | 02:30 | 03:00 | 0.5 | 16460 | 16460 | 0 | LAT | 2: BHA 5 | 6P | L/D BHA
11/16/2021 | 03:00 | 05:45 | 2.75 | 16460 | 16460 | 0 | LAT |  | 8A | Change saver sub
11/16/2021 | 05:45 | 06:45 | 1 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 6O | M/U BHA #6
11/16/2021 | 06:45 | 07:00 | 0.25 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 5A | Test MWD & Motor
11/16/2021 | 07:00 | 07:30 | 0.5 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 8P | Rig service
11/16/2021 | 07:30 | 07:45 | 0.25 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 6L | Swap bits
11/16/2021 | 07:45 | 13:00 | 5.25 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 6A | TIH t/ 9727
11/16/2021 | 13:00 | 14:30 | 1.5 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 9A | Slip & cut
11/16/2021 | 14:30 | 18:20 | 3.83 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 6A | TIH
11/16/2021 | 18:20 | 18:52 | 0.53 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 5A | Orient thur ST @ 150L
11/16/2021 | 18:52 | 20:30 | 1.63 | 16460 | 16460 | 0 | LAT | 3: BHA 6 | 6A | TIH
11/16/2021 | 20:30 | 20:52 | 0.37 | 16460 | 16510 | 50 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16460.00 t/16510.00, w/WOB 19.00,Flow 350.00, RPM 70.00, Press 4750.00, Tq 14.50, ROP 136.36, Diff 550.00, Temp 171.00
11/16/2021 | 20:52 | 20:56 | 0.07 | 16510 | 16510 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/16/2021 | 20:56 | 21:30 | 0.57 | 16510 | 16604 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16510.00 t/16604.00, w/WOB 22.00,Flow 350.00, RPM 70.00, Press 4750.00, Tq 16.00, ROP 165.88, Diff 550.00, Temp 165.00
11/16/2021 | 21:30 | 21:43 | 0.22 | 16604 | 16604 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/16/2021 | 21:43 | 22:17 | 0.57 | 16604 | 16624 | 20 | LAT | 3: BHA 6 | 2J | Slide Drill f/16604.00 t/16624.00, TF 150.00G, w/WOB 35.00,Flow 350.00, Press 4750.00, Tq 16.00, ROP 35.29, Diff 550.00, Temp 160.00
11/16/2021 | 22:17 | 22:52 | 0.58 | 16624 | 16699 | 75 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16624.00 t/16699.00, w/WOB 29.00,Flow 350.00, RPM 70.00, Press 4600.00, Tq 16.00, ROP 128.57, Diff 600.00, Temp 150.00
11/16/2021 | 22:52 | 22:57 | 0.08 | 16699 | 16699 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/16/2021 | 22:57 | 23:29 | 0.53 | 16699 | 16719 | 20 | LAT | 3: BHA 6 | 2J | Slide Drill f/16699.00 t/16719.00, TF 150.00G, w/WOB 35.00,Flow 350.00, Press 4600.00, Tq 16.00, ROP 37.50, Diff 600.00, Temp 145.00
11/16/2021 | 23:29 | 24:00 | 0.52 | 16719 | 16794 | 75 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16719.00 t/16794.00, w/WOB 22.00,Flow 350.00, RPM 70.00, Press 4600.00, Tq 16.00, ROP 145.16, Diff 600.00, Temp 145.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_17_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/17/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9400 |  |  | Well Cost($): |  | 61200
|  |  |  | 24hr Summary: |  | TIH and cont Drilling
|  |  |  | 24hr Lookahead: |  | Drill ahead
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16794 |  | 16460 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 18963 |  | 18963 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 2169 |  | 2503 |  | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  | 151 |  | 191 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): |  | 2018 |  | 2312 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 19.48 / 3.27 |  | 22.62 / 4.42 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  | 5.72 |  | 6.82 |  | SN: |  | 13673682 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 13.77 |  | 15.8 |  | Bit # |  | 6 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  | 146.59 / 26.41 |  | 146.33 / 28.02 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 41.25 |  | Grade In: |  | New
% Slide: |  | 6.96 |  | 7.63 |  | Grade Out: |  | 1-3-LT-S-X-I-WT-TD
% Rotary: |  | 93.04 |  | 92.37 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 .003 |  |  |  | 5.25 | 2 |  |  |  |  | 32.95 |  | 33.95
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.6
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.46
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.36
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.47
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.1
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 131.74
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.07
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.43
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.06
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.05
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.45
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.18
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.43
5948.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250023 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16729 | 86.66 | 151.46 | 10474.59 | -5277.07 | 3350.84 | 2.25 |  | 163.71 | 6247.56 | -2.16 |  | 0.63 | 95
16824 | 85.16 | 151.42 | 10481.37 | -5360.29 | 3396.14 | 1.58 |  | -178.48 | 6342.26 | -1.58 |  | -0.04 | 95
16918 | 84.65 | 150.96 | 10489.72 | -5442.33 | 3441.26 | 0.73 |  | -138.08 | 6435.84 | -0.54 |  | -0.49 | 94
17013 | 85.25 | 150.03 | 10498.08 | -5524.69 | 3487.86 | 1.16 |  | -57.11 | 6530.46 | 0.63 |  | -0.98 | 95
17108 | 86.08 | 148.9 | 10505.26 | -5606.28 | 3535.99 | 1.47 |  | -53.67 | 6625.19 | 0.87 |  | -1.19 | 95
17202 | 86.44 | 149.93 | 10511.39 | -5687.03 | 3583.72 | 1.16 |  | 70.73 | 6718.98 | 0.38 |  | 1.1 | 94
17296 | 87.25 | 149.15 | 10516.56 | -5767.93 | 3631.3 | 1.2 |  | -43.9 | 6812.84 | 0.86 |  | -0.83 | 94
17390 | 87.81 | 147.96 | 10520.62 | -5848.05 | 3680.29 | 1.4 |  | -64.8 | 6906.74 | 0.6 |  | -1.27 | 94
17484 | 88.12 | 150.25 | 10523.95 | -5928.66 | 3728.52 | 2.46 |  | 82.33 | 7000.67 | 0.33 |  | 2.44 | 94
17578 | 87.04 | 151.59 | 10527.92 | -6010.73 | 3774.16 | 1.83 |  | 128.92 | 7094.55 | -1.15 |  | 1.43 | 94
17671 | 84.93 | 150.87 | 10534.43 | -6092.05 | 3818.81 | 2.4 |  | -161.23 | 7187.28 | -2.27 |  | -0.77 | 93
17765 | 84.88 | 150.97 | 10542.78 | -6173.87 | 3864.32 | 0.12 |  | 116.66 | 7280.88 | -0.05 |  | 0.11 | 94
17860 | 85.55 | 150.68 | 10550.71 | -6256.53 | 3910.47 | 0.77 |  | -23.34 | 7375.52 | 0.71 |  | -0.31 | 95
17954 | 87.38 | 150.04 | 10556.5 | -6338.07 | 3956.86 | 2.06 |  | -19.26 | 7469.33 | 1.95 |  | -0.68 | 94
18049 | 86.82 | 150.05 | 10561.31 | -6420.27 | 4004.24 | 0.59 |  | 178.98 | 7564.2 | -0.59 |  | 0.01 | 95
18143 | 86.12 | 150.26 | 10567.1 | -6501.65 | 4050.93 | 0.78 |  | 163.34 | 7658.01 | -0.74 |  | 0.22 | 94
18238 | 85.6 | 150.69 | 10573.95 | -6584.1 | 4097.62 | 0.71 |  | 140.5 | 7752.75 | -0.55 |  | 0.45 | 95
18332 | 85.89 | 149.59 | 10580.93 | -6665.39 | 4144.29 | 1.21 |  | -75.23 | 7846.49 | 0.31 |  | -1.17 | 94
18427 | 87.38 | 148.99 | 10586.51 | -6746.93 | 4192.73 | 1.69 |  | -21.92 | 7941.32 | 1.57 |  | -0.63 | 95
18521 | 86.56 | 148.69 | 10591.47 | -6827.25 | 4241.3 | 0.93 |  | -159.94 | 8035.18 | -0.87 |  | -0.32 | 94
18616 | 88.5 | 147.71 | 10595.57 | -6907.91 | 4291.31 | 2.29 |  | -26.8 | 8130.06 | 2.04 |  | -1.03 | 95
18709 | 87.04 | 147.62 | 10599.19 | -6986.43 | 4341.01 | 1.57 |  | -176.48 | 8222.94 | -1.57 |  | -0.1 | 93
18804 | 87.9 | 146.03 | 10603.38 | -7065.86 | 4392.94 | 1.9 |  | -61.61 | 8317.74 | 0.91 |  | -1.67 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 113.18 | 21.62 | 66.55 | 321 | 374.24 | 5109.33 | 4342.59 | 0 | 350 | 158.76 | 50 | 16.43 | 0
Run | 111.92 | 22.33 | 66.97 | 319 | 371 | 5051.42 | 4310.25 | 0 | 350 | 154.26 | 50 | 16.33 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/17/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/17/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 11/17/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 11/17/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/17/2021 | 00:00 | 00:05 | 0.08 | 16794 | 16794 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 00:05 | 01:06 | 1.02 | 16794 | 16889 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16794.00 t/16889.00, w/WOB 24.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 16.00, ROP 93.44, Diff 750.00, Temp 145.00
11/17/2021 | 01:06 | 01:11 | 0.08 | 16889 | 16889 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 01:11 | 01:50 | 0.65 | 16889 | 16983 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16889.00 t/16983.00, w/WOB 24.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 16.00, ROP 144.62, Diff 750.00, Temp 145.00
11/17/2021 | 01:50 | 01:55 | 0.08 | 16983 | 16983 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 01:55 | 02:26 | 0.52 | 16983 | 17078 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/16983.00 t/17078.00, w/WOB 24.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 16.00, ROP 183.87, Diff 750.00, Temp 151.00
11/17/2021 | 02:26 | 02:31 | 0.08 | 17078 | 17078 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 02:31 | 03:03 | 0.53 | 17078 | 17173 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17078.00 t/17173.00, w/WOB 24.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 16.00, ROP 178.13, Diff 750.00, Temp 151.00
11/17/2021 | 03:03 | 03:08 | 0.08 | 17173 | 17173 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 03:08 | 03:40 | 0.53 | 17173 | 17188 | 15 | LAT | 3: BHA 6 | 2J | Slide Drill f/17173.00 t/17188.00, TF 110G, w/WOB 35,Flow 375.00, Press 5400.00, Tq 16.00, ROP 28.13, Diff 750.00, Temp 138.00
11/17/2021 | 03:40 | 04:18 | 0.63 | 17188 | 17267 | 79 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17188.00 t/17267.00, w/WOB 24.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 16.00, ROP 124.74, Diff 750.00, Temp 135.00
11/17/2021 | 04:18 | 05:00 | 0.7 | 17267 | 17267 | 0 | LAT | 3: BHA 6 | 8P | Service Rig
11/17/2021 | 05:00 | 05:05 | 0.08 | 17267 | 17267 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 05:05 | 05:44 | 0.65 | 17267 | 17361 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17267.00 t/17361.00, w/WOB 24.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 16.00, ROP 144.62, Diff 750.00, Temp 135.00
11/17/2021 | 05:44 | 05:49 | 0.08 | 17361 | 17361 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 05:49 | 06:17 | 0.47 | 17361 | 17455 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17361.00 t/17455.00, w/WOB 24.52,Flow 374.22, RPM 69.85, Press 4834.95, Tq 15.99, ROP 201.43, Diff 1728.03, Temp 140.00
11/17/2021 | 06:17 | 06:25 | 0.13 | 17455 | 17455 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 06:25 | 06:30 | 0.08 | 17455 | 17465 | 10 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17455.00 t/17465.00, w/WOB 20.41,Flow 374.13, RPM 50, Press 5131.06, Tq 16.10, ROP 120.00, Diff 760.58, Temp 136.40
11/17/2021 | 06:30 | 06:54 | 0.4 | 17465 | 17480 | 15 | LAT | 3: BHA 6 | 2J | Slide Drill f/17465.00 t/17480.00, TF 135G, w/WOB 20.41,Flow 374.13, Press 5131.06, Tq 0, ROP 37.50, Diff 760.58, Temp 136.40
11/17/2021 | 06:54 | 07:23 | 0.48 | 17480 | 17549 | 69 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17480.00 t/17549.00, w/WOB 21.24,Flow 374.15, RPM 70, Press 5133.80, Tq 16.26, ROP 142.76, Diff 1425.73, Temp 138.20
11/17/2021 | 07:23 | 07:29 | 0.1 | 17549 | 17549 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 07:29 | 07:34 | 0.08 | 17549 | 17559 | 10 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17549.00 t/17559.00, w/WOB 15,Flow 374.32, RPM 50, Press 4598.46, Tq 14.24, ROP 120.00, Diff 311.33, Temp 141.80
11/17/2021 | 07:34 | 07:56 | 0.37 | 17559 | 17571 | 12 | LAT | 3: BHA 6 | 2J | Slide Drill f/17559.00 t/17571.00, TF 160G, w/WOB 11.72,Flow 374.32, Press 4598.46, Tq 0, ROP 32.73, Diff 311.33, Temp 141.80
11/17/2021 | 07:56 | 08:27 | 0.52 | 17571 | 17643 | 72 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17571.00 t/17643.00, w/WOB 18.90,Flow 374.15, RPM 70, Press 5020.78, Tq 16.37, ROP 139.35, Diff 701.35, Temp 136.40
11/17/2021 | 08:27 | 08:49 | 0.37 | 17643 | 17643 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection Recycle x 1
11/17/2021 | 08:49 | 08:54 | 0.08 | 17643 | 17653 | 10 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17643.00 t/17653.00, w/WOB 20.08,Flow 374.02, RPM 50, Press 5349.90, Tq 15.52, ROP 120.00, Diff 421.72, Temp 136.40
11/17/2021 | 08:54 | 09:20 | 0.43 | 17653 | 17661 | 8 | LAT | 3: BHA 6 | 2J | Slide Drill f/17653.00 t/17661.00, TF 180G, w/WOB 20.08,Flow 374.02, Press 5349.90, Tq 0, ROP 18.46, Diff 421.72, Temp 136.40
11/17/2021 | 09:20 | 09:50 | 0.5 | 17661 | 17736 | 75 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17661.00 t/17736.00, w/WOB 24.03,Flow 374.03, RPM 68.01, Press 5413.65, Tq 16.40, ROP 150.00, Diff 1340.66, Temp 141.80
11/17/2021 | 09:50 | 09:56 | 0.1 | 17736 | 17736 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 09:56 | 10:27 | 0.52 | 17736 | 17830 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17736.00 t/17830.00, w/WOB 16.55,Flow 373.99, RPM 67.70, Press 5439.30, Tq 16.57, ROP 181.94, Diff 1837.28, Temp 150.80
11/17/2021 | 10:27 | 10:40 | 0.22 | 17830 | 17830 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection Recycle x 1
11/17/2021 | 10:40 | 11:10 | 0.5 | 17830 | 17925 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17830.00 t/17925.00, w/WOB 20.42,Flow 374.05, RPM 66.46, Press 5058.48, Tq 16.86, ROP 194.00, Diff 1900.01, Temp 154.40
11/17/2021 | 11:10 | 11:17 | 0.12 | 17925 | 17925 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 11:17 | 11:48 | 0.52 | 17925 | 18019 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/17927.00 t/18019.00, w/WOB 21.40,Flow 374.11, RPM 67.66, Press 4864.97, Tq 17.55, ROP 178.06, Diff 1187.85, Temp 156.20
11/17/2021 | 11:48 | 12:00 | 0.2 | 18019 | 18019 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection Recycle x 1
11/17/2021 | 12:00 | 12:08 | 0.13 | 18019 | 18029 | 10 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18019.00 t/18029.00, w/WOB 22.11,Flow 374.27, RPM 49.97, Press 4640.06, Tq 14.95, ROP 75.00, Diff 119.87, Temp 156.20
11/17/2021 | 12:08 | 12:48 | 0.67 | 18029 | 18046 | 17 | LAT | 3: BHA 6 | 2J | Slide Drill f/18029.00 t/18046.00, TF 164.00G, w/WOB 19.56,Flow 374.04, Press 5339.02, Tq 0, ROP 25.50, Diff 335.17, Temp 152.60
11/17/2021 | 12:48 | 13:17 | 0.48 | 18046 | 18114 | 68 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18046.00 t/18114.00, w/WOB 23.99,Flow 373.94, RPM 64.77, Press 5320.15, Tq 17.51, ROP 140.69, Diff 1399.55, Temp 154.40
11/17/2021 | 13:17 | 13:24 | 0.12 | 18114 | 18114 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 13:24 | 13:31 | 0.12 | 18114 | 18124 | 10 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18114.00 t/18124.00, w/WOB 21.55,Flow 374.24, RPM 49.96, Press 4398.58, Tq 15.51, ROP 85.71, Diff 177.59, Temp 156.20
11/17/2021 | 13:31 | 14:08 | 0.62 | 18124 | 18134 | 10 | LAT | 3: BHA 6 | 2J | Slide Drill f/18124.00 t/18134.00, TF 162.44G, w/WOB 10.71,Flow 373.73, Press 5305.68, Tq 0, ROP 16.22, Diff 334.09, Temp 152.60
11/17/2021 | 14:08 | 14:37 | 0.48 | 18134 | 18208 | 74 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18134.00 t/18208.00, w/WOB 16.24,Flow 373.93, RPM 68.02, Press 5299.92, Tq 17.61, ROP 153.10, Diff 1376.49, Temp 152.60
11/17/2021 | 14:37 | 15:00 | 0.38 | 18208 | 18208 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection Recycle x 2
11/17/2021 | 15:00 | 15:15 | 0.25 | 18208 | 18232 | 24 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18208.00 t/18232.00, w/WOB 15.53,Flow 374.19, RPM 65.76, Press 4690.29, Tq 17.18, ROP 96.00, Diff 43.99, Temp 154.40
11/17/2021 | 15:15 | 15:55 | 0.67 | 18232 | 18246 | 14 | LAT | 3: BHA 6 | 2J | Slide Drill f/18232.00 t/18246.00, TF 174.38G, w/WOB 19.47,Flow 373.92, Press 5260.65, Tq 0, ROP 21.00, Diff 377.66, Temp 143.60
11/17/2021 | 15:55 | 16:21 | 0.43 | 18246 | 18303 | 57 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18246.00 t/18303.00, w/WOB 22.97,Flow 373.89, RPM 66.14, Press 5280.57, Tq 16.85, ROP 131.54, Diff 1177.03, Temp 147.20
11/17/2021 | 16:21 | 16:54 | 0.55 | 18303 | 18303 | 0 | LAT | 3: BHA 6 | 8P | Service Rig
11/17/2021 | 16:54 | 16:59 | 0.08 | 18303 | 18303 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 16:59 | 17:34 | 0.58 | 18303 | 18397 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18303.00 t/18397.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 161.14, Diff 620.29, Temp 150.80
11/17/2021 | 17:34 | 17:41 | 0.12 | 18397 | 18397 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 17:41 | 18:17 | 0.6 | 18397 | 18492 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18397.00 t/18492.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 158.33, Diff 620.29, Temp 150.80
11/17/2021 | 18:17 | 18:22 | 0.08 | 18492 | 18492 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 18:22 | 19:02 | 0.67 | 18492 | 18512 | 20 | LAT | 3: BHA 6 | 2J | Slide Drill f/18492.00 t/18512.00, TF 150.00G, w/WOB 35.00,Flow 374.04, Press 5000.40, Tq 16.99, ROP 30.00, Diff 620.29, Temp 150.80
11/17/2021 | 19:02 | 19:34 | 0.53 | 18512 | 18586 | 74 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18512.00 t/18586.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 138.75, Diff 620.29, Temp 150.80
11/17/2021 | 19:34 | 19:39 | 0.08 | 18586 | 18586 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 19:39 | 20:19 | 0.67 | 18586 | 18681 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18586.00 t/18681.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 142.50, Diff 620.29, Temp 150.80
11/17/2021 | 20:19 | 20:33 | 0.23 | 18681 | 18681 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 20:33 | 21:13 | 0.67 | 18681 | 18701 | 20 | LAT | 3: BHA 6 | 2J | Slide Drill f/18681.00 t/18701.00, TF 180.00G, w/WOB 35.00,Flow 374.04, Press 5000.40, Tq 16.99, ROP 30.00, Diff 620.29, Temp 150.80
11/17/2021 | 21:13 | 21:56 | 0.72 | 18701 | 18774 | 73 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18701.00 t/18774.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 101.86, Diff 620.29, Temp 150.80
11/17/2021 | 21:56 | 22:05 | 0.15 | 18774 | 18774 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 22:05 | 22:35 | 0.5 | 18774 | 18869 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18774.00 t/18869.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 190.00, Diff 620.29, Temp 150.80
11/17/2021 | 22:35 | 22:40 | 0.08 | 18869 | 18869 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/17/2021 | 22:40 | 23:22 | 0.7 | 18869 | 18889 | 20 | LAT | 3: BHA 6 | 2J | Slide Drill f/18869.00 t/18889.00, TF 150.00G, w/WOB 20.89,Flow 374.04, Press 5000.40, Tq 16.99, ROP 28.57, Diff 620.29, Temp 150.80
11/17/2021 | 23:22 | 23:53 | 0.52 | 18889 | 18963 | 74 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18889.00 t/18963.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 143.23, Diff 620.29, Temp 150.80
11/17/2021 | 23:53 | 24:00 | 0.12 | 18963 | 18963 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_18_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/18/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9400 |  |  | Well Cost($): |  | 70600
|  |  |  | 24hr Summary: |  | TD Well
|  |  |  | 24hr Lookahead: |  | Circulate after TD - Standby for POOH
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18963 |  | 16460 |  | Csg Shoe MD(Usft): |  | 9774 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 19363 |  | 19363 |  | OD (in): |  | 7.625 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 400 |  | 2903 |  | Weight (ft/lbs): |  | 44 |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  | 20 |  | 211 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): |  | 380 |  | 2692 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  | 2.83 / 9.33 |  | 25.45 / 13.75 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  | 0.45 |  | 7.27 |  | SN: |  | 13673682 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 2.38 |  | 18.18 |  | Bit # |  | 6 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  | 159.44 / 44.44 |  | 148.05 / 29.04 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 65.25 |  | Grade In: |  | New
% Slide: |  | 5 |  | 7.27 |  | Grade Out: |  | 1-3-LT-S-X-I-WT-TD
% Rotary: |  | 95 |  | 92.73 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 .003 |  |  |  | 5.25 | 2 |  |  |  |  | 32.95 |  | 33.95
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.6
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.46
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.36
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.47
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.1
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 131.74
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.07
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.43
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.06
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.05
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.45
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.18
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.43
5948.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250023 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18898 | 85.58 | 147.95 | 10608.73 | -7144.55 | 4444.06 | 3.2 |  | 140.48 | 8411.49 | -2.47 |  | 2.04 | 94
18992 | 85.83 | 148.63 | 10615.77 | -7224.29 | 4493.33 | 0.77 |  | 69.79 | 8505.2 | 0.27 |  | 0.72 | 94
19087 | 87.42 | 148.53 | 10621.36 | -7305.22 | 4542.77 | 1.68 |  | -3.6 | 8600.02 | 1.67 |  | -0.11 | 95
19181 | 85.45 | 149.96 | 10627.2 | -7385.84 | 4590.74 | 2.59 |  | 144.12 | 8693.83 | -2.1 |  | 1.52 | 94
19276 | 86.17 | 149.47 | 10634.14 | -7467.65 | 4638.52 | 0.92 |  | -34.18 | 8788.58 | 0.76 |  | -0.52 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 141.18 | 21.62 | 66.55 | 321 | 374.24 | 5109.33 | 4342.59 | 0 | 350 | 158.76 | 50 | 16.43 | 0
Run | 114.07 | 22.33 | 66.97 | 319 | 371 | 5051.42 | 4310.25 | 0 | 350 | 154.26 | 50 | 16.33 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 11/18/2021 |  | 23 |  | 2000 |  | 1 | 2000
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/18/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/18/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 11/18/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 9400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/18/2021 | 00:00 | 00:43 | 0.72 | 18963 | 19057 | 94 | LAT | 3: BHA 6 | 2K | Rotary Drill f/18963.00 t/19057.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 131.16, Diff 620.29, Temp 150.80
11/18/2021 | 00:43 | 00:50 | 0.12 | 19057 | 19057 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/18/2021 | 00:50 | 01:21 | 0.52 | 19057 | 19152 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/19057.00 t/19152.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 183.87, Diff 620.29, Temp 150.80
11/18/2021 | 01:21 | 01:32 | 0.18 | 19152 | 19152 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/18/2021 | 01:32 | 01:59 | 0.45 | 19152 | 19172 | 20 | LAT | 3: BHA 6 | 2J | Slide Drill f/19152.00 t/19172.00, TF 150.00G, w/WOB 20.89,Flow 374.04, Press 5000.40, Tq 16.99, ROP 44.44, Diff 620.29, Temp 150.80
11/18/2021 | 01:59 | 02:31 | 0.53 | 19172 | 19246 | 74 | LAT | 3: BHA 6 | 2K | Rotary Drill f/19172.00 t/19246.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 138.75, Diff 620.29, Temp 150.80
11/18/2021 | 02:31 | 02:38 | 0.12 | 19246 | 19246 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/18/2021 | 02:38 | 03:07 | 0.48 | 19246 | 19341 | 95 | LAT | 3: BHA 6 | 2K | Rotary Drill f/19246.00 t/19341.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 196.55, Diff 620.29, Temp 150.80
11/18/2021 | 03:07 | 03:15 | 0.13 | 19341 | 19341 | 0 | LAT | 3: BHA 6 | 5A | Survey & Connection
11/18/2021 | 03:15 | 03:23 | 0.13 | 19341 | 19363 | 22 | LAT | 3: BHA 6 | 2K | Rotary Drill f/19341.00 t/19363.00, w/WOB 20.89,Flow 374.04, RPM 70.00, Press 5000.40, Tq 16.99, ROP 165.00, Diff 620.29, Temp 150.80
11/18/2021 | 03:23 | 05:45 | 2.37 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 5A | Circulate
11/18/2021 | 05:45 | 12:10 | 6.42 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 3D | Backream out of hole to 14,900
11/18/2021 | 12:10 | 15:15 | 3.08 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 6B | POOH to Shoe
11/18/2021 | 15:15 | 23:25 | 8.17 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 6K | Lay down DP to 3000ft
11/18/2021 | 23:25 | 24:00 | 0.58 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_19_2021_DDR
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31181 / 21DD0218MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 17 |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Longitude: |  | 96° 40' 25.149" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/19/2021 |  |  | Report Time: |  | 00:00-19:00
|  |  |  | Daily Cost($): |  | 9400 |  |  | Well Cost($): |  | 80000
|  |  |  | 24hr Summary: |  | POOH after TD
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 19363 |  | 16460 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 19363 |  | 19363 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  |  |  | 2903 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 27
Slide Drilled (Usft): |  |  |  | 211 | [5 empty] | 100: | 1 | Chlorides: | 4000
Rotary Drilled (Usft): |  |  |  | 2692 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.50
Drlg/Circ Hrs: |  |  |  | 25.45 / 13.75 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 2/98
Slide Drilling Hrs: |  |  |  | 7.27 |  | SN: |  | 13673682 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  |  |  | 18.18 |  | Bit # |  | 6 |  | PH / Temp(F) | 7.0 / 0.00 | Fluid Loss / Mud Type: | 100 / H2O
ROP Rot/Slide (Usft/hr): |  |  |  | 148.05 / 29.04 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 19 |  | 84.25 |  | Grade In: |  | New
% Slide: |  |  |  | 7.27 |  | Grade Out: |  | 1-3-LT-S-X-I-WT-TD
% Rotary: |  |  |  | 92.73 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Pete Langille |  | Nick Chris |  | Bill Trey |  | Bobby Lewis
Jim Harrison |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 .003 |  |  |  | 5.25 | 2 |  |  |  |  | 32.95 |  | 33.95
BTI Sub |  |  |  | 4.812 | 2.188 |  |  |  |  | 1.65 |  | 35.6
Pony Collar |  |  |  | 4.938 | 2.75 |  |  |  |  | 9.86 |  | 45.46
UBHO |  |  |  | 5.25 | 2.562 |  |  |  |  | 3.9 |  | 49.36
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 31.11 |  | 80.47
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  |  |  | 30.63 |  | 111.1
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 20.64 |  | 131.74
Crossover |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.33 |  | 135.07
2 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 189.36 |  | 324.43
Drill N Ream |  |  |  | 5.375 | 2.625 |  |  |  |  | 8.63 |  | 333.06
26 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 2453.99 |  | 2787.05
Agitator |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.4 |  | 2808.45
33 Stands 4 1/2" DP |  |  |  | 4.5 | 3.8 |  |  |  |  | 3118.73 |  | 5927.18
Agitator (Ball Drop) |  |  |  | 5.25 | 2.688 |  |  |  |  | 21.25 |  | 5948.43
5948.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250023 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 21.62 | 66.55 | 321 | 374.24 | 5109.33 | 4342.59 | 0 | 350 | 158.76 | 50 | 16.43 | 0
Run | 114.07 | 22.33 | 66.97 | 319 | 371 | 5051.42 | 4310.25 | 0 | 350 | 154.26 | 50 | 16.33 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 11/19/2021 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 11/19/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 11/19/2021 |  | 23 |  | 2000 |  | 1 | 2000
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 11/19/2021 |  | 3 |  | -400 |  | 1 | -400
Total | [11 empty] | 9400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/19/2021 | 00:00 | 01:45 | 1.75 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 6A | TIH to 9700
11/19/2021 | 01:45 | 18:00 | 16.25 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 6K | Lay down DP
11/19/2021 | 18:00 | 19:00 | 1 | 19363 | 19363 | 0 | LAT | 3: BHA 6 | 6P | Lay Down BHA for EOW
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5948.75 (Usft)
Well: |  |  | Bighorn Pass H06 | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1148421 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 11/12/2021 | Depth In: |  | 14900 | Total Drilled: |  | 6.00 (Usft)
Date Out: |  |  | 11/13/2021 | Depth Out: |  | 14906 | Drilling / Circ Hours: |  | 6.80 / 3.00
Survey Offset: |  |  | 65 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618580 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 1 | 1
| 2 | PPM250007 | 6/7 8.8 2.12 T/S HS88 +.001 | 5.25 | 2 | 5.250 / 2.09 | XT39 / 3 1/2 Reg |  | 33.27 | 34.27
| 3 | BTI 3 | BTI Sub | 4.812 | 2.188 |  | XT39 / XT39 |  | 1.65 | 35.92
| 4 | GT50-10-479 | Pony Collar | 4.938 | 2.75 |  | XT39 / XT39 |  | 9.86 | 45.78
| 5 | 500048 | UBHO | 5.25 | 2.562 |  | XT39 / XT39 |  | 3.9 | 49.68
| 6 | GT52-30-592 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 | 4.938 / 1.30 | XT39 / XT39 |  | 31.11 | 80.79
| 7 | GT52-30-458 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 | 4.938 / 1.38 | XT39 / XT39 |  | 30.63 | 111.42
| 8 | A52042 | Tomax | 5 | 2.25 | 5.000 / 2.58 | XT39 / XT39 |  | 20.64 | 132.06
| 9 | GT52331430 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 |  | 3.33 | 135.39
| 10 |  | 2 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 189.36 | 324.75
| 11 | 579 | Drill N Ream | 5.375 | 2.625 |  | CET43 / CET43 |  | 8.63 | 333.38
| 12 |  | 26 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 2453.99 | 2787.37
| 13 | PG525-0049 | Agitator | 5.25 | 2.688 | 5.250 / 1.82 | CET43 / CET43 |  | 21.4 | 2808.77
| 14 |  | 33 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 3118.73 | 5927.5
| 15 | PG525-0035 | Agitator (Ball Drop) | 5.25 | 2.688 | 5.250 / 1.84 | CET43 / CET43 |  | 21.25 | 5948.75
| 16 | [8 empty] | 5948.75
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 1-1-WT-C-X-I-NO-DMF | 6
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 T/S HS88 +.001 |  |  | PDCI / 6/7 8.8 | 4.11 / 2.12 |  | 0 | 5.5 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1000 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.001
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5948.45 (Usft)
Well: |  |  | Bighorn Pass H06 | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1148421 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 11/13/2021 | Depth In: |  | 14906 | Total Drilled: |  | 1554.00 (Usft)
Date Out: |  |  | 11/16/2021 | Depth Out: |  | 16460 | Drilling / Circ Hours: |  | 33.88 / 7.28
Survey Offset: |  |  | 65 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13601237 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 1 | 1
| 2 | PPM250012 | 6/7 8.8 2.12 T/S HS88 -.001 | 5.25 | 2 | 5.250 / 2.00 | XT39 / 3 1/2REG |  | 32.97 | 33.97
| 3 | BTI 3 | BTI Sub | 4.812 | 2.188 |  | XT39 / XT39 |  | 1.65 | 35.62
| 4 | GT50-10-479 | Pony Collar | 4.938 | 2.75 |  | XT39 / XT39 |  | 9.86 | 45.48
| 5 | 500048 | UBHO | 5.25 | 2.562 |  | XT39 / XT39 |  | 3.9 | 49.38
| 6 | GT52-30-592 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 | 4.938 / 1.30 | XT39 / XT39 |  | 31.11 | 80.49
| 7 | GT52-30-458 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 | 4.938 / 1.38 | XT39 / XT39 |  | 30.63 | 111.12
| 8 | A52042 | Tomax | 5 | 2.25 | 5.000 / 2.58 | XT39 / XT39 |  | 20.64 | 131.76
| 9 | GT52331430 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 |  | 3.33 | 135.09
| 10 |  | 2 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 189.36 | 324.45
| 11 | 579 | Drill N Ream | 5.375 | 2.625 |  | CET43 / CET43 |  | 8.63 | 333.08
| 12 |  | 26 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 2453.99 | 2787.07
| 13 | PG525-0049 | Agitator | 5.25 | 2.688 | 5.250 / 1.82 | CET43 / CET43 |  | 21.4 | 2808.47
| 14 |  | 33 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 3118.73 | 5927.2
| 15 | PG525-0035 | Agitator (Ball Drop) | 5.25 | 2.688 | 5.250 / 1.84 | CET43 / CET43 |  | 21.25 | 5948.45
| 16 | [8 empty] | 5948.45
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 4-6-RO-A-X-I-BT-HP | 1554
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 T/S HS88 -.001 |  |  | PDCI / 6/7 8.8 | 4.01 / 2.12 |  | 0 | 5.5 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1000 | 70 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | -0.001
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_6
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5948.43 (Usft)
Well: |  |  | Bighorn Pass H06 | BHA #: |  | 6 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1148421 | Bit #: |  | 6 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 11/16/2021 | Depth In: |  | 16460 | Total Drilled: |  | 2903.00 (Usft)
Date Out: |  |  | 11/19/2021 | Depth Out: |  | 19363 | Drilling / Circ Hours: |  | 25.45 / 13.75
Survey Offset: |  |  | 65 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13673682 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 1 | 1
| 2 | PPM250023 | 6/7 8.8 2.12 T/S HS88 .003 | 5.25 | 2 | 5.000 / 1.97 | XT39 / 3 1/2REG |  | 32.95 | 33.95
| 3 | BTI 3 | BTI Sub | 4.812 | 2.188 |  | XT39 / XT39 |  | 1.65 | 35.6
| 4 | GT50-10-479 | Pony Collar | 4.938 | 2.75 |  | XT39 / XT39 |  | 9.86 | 45.46
| 5 | 500048 | UBHO | 5.25 | 2.562 |  | XT39 / XT39 |  | 3.9 | 49.36
| 6 | GT52-30-592 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 | 4.938 / 1.30 | XT39 / XT39 |  | 31.11 | 80.47
| 7 | GT52-30-458 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 | 4.938 / 1.38 | XT39 / XT39 |  | 30.63 | 111.1
| 8 | A52042 | Tomax | 5 | 2.25 | 5.000 / 2.58 | XT39 / XT39 |  | 20.64 | 131.74
| 9 | GT52331430 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 |  | 3.33 | 135.07
| 10 |  | 2 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 189.36 | 324.43
| 11 | 579 | Drill N Ream | 5.375 | 2.625 |  | CET43 / CET43 |  | 8.63 | 333.06
| 12 |  | 26 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 2453.99 | 2787.05
| 13 | PG525-0049 | Agitator | 5.25 | 2.688 | 5.250 / 1.82 | CET43 / CET43 |  | 21.4 | 2808.45
| 14 |  | 33 Stands 4 1/2" DP | 4.5 | 3.8 |  | CET43 / CET43 |  | 3118.73 | 5927.18
| 15 | PG525-0035 | Agitator (Ball Drop) | 5.25 | 2.688 | 5.250 / 1.84 | CET43 / CET43 |  | 21.25 | 5948.43
| 16 | [8 empty] | 5948.43
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 1-3-LT-S-X-I-WT-TD | 2903
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 T/S HS88 .003 |  |  | PDCI / 6/7 8.8 | 4.11 / 2.12 |  | 0 | 5.5 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1000 | 70 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.003
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31181 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Longitude: |  | 96° 40' 25.149" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 144.00/144.00/144.00
Date In: |  | 11/12/2021 03:00 |  | SN: |  | PPM250007 |  |  |  | WOB Rotate (klbs):
Date Out: |  | 11/13/2021 13:30 |  | Description: |  | 6/7 8.8 2.12 T/S HS88 +.001 |  |  |  | WOB Slide (klbs): |  | 15.00
Depth In/Out(Usft): |  | 14900.00 / 14906.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 84.36 / 84.33 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 290
Azi In/Out: |  | 148.19 / 148.14 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3800
Total Drilled (Usft): |  | 6 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 3900
%Slide (Ftg): |  | 100.00 |  | Bit to Bend (Usft): |  | 4.11 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 100.00 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 6 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 6.8 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 0.00 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 0.00 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 0 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0 |  | Length (Usft): |  | 33.27 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 6.80 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 3.00 / 34.50 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 0.88 |  | # Stalls / Pressure: |  | 1 / 3000.00 |  |  |  | Grade Out: |  | 1-1-WT-C-X-I-NO-DMF
Rot ROP (Usft/hr): |  | 0 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.001 |  |  |  | Drill Hrs: |  | 6.80
Avg ROP (Usft/hr): |  | 0.88 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.00
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  | 2.00 |  | 1 | 1 | 8.4 | 4000 | H2O | 0.5
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
65 | 56
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618580 |  | 6.75 | 2 |  |  |  | 1 | 1
6/7 8.8 2.12 T/S HS88 +.001 0.00 |  |  |  | PPM250007 |  | 5.25 | 2 |  |  |  | 33.27 | 34.27
BTI Sub 0.00 |  |  |  | BTI 3 |  | 4.812 | 2.188 |  |  |  | 1.65 | 35.92
Pony Collar 0.00 |  |  |  | GT50-10-479 |  | 4.938 | 2.75 |  |  |  | 9.86 | 45.78
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.562 |  |  |  | 3.9 | 49.68
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-592 |  | 5.25 | 2.688 |  |  |  | 31.11 | 80.79
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-458 |  | 5.25 | 2.688 |  |  |  | 30.63 | 111.42
Tomax 0.00 |  |  |  | A52042 |  | 5 | 2.25 |  |  |  | 20.64 | 132.06
Crossover 0.00 |  |  |  | GT52331430 |  | 5.25 | 2.688 |  |  |  | 3.33 | 135.39
2 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 189.36 | 324.75
Drill N Ream 0.00 |  |  |  | 579 |  | 5.375 | 2.625 |  |  |  | 8.63 | 333.38
26 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 2453.99 | 2787.37
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.688 |  |  |  | 21.4 | 2808.77
33 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 3118.73 | 5927.5
Agitator (Ball Drop) 0.00 |  |  |  | PG525-0035 |  | 5.25 | 2.688 |  |  |  | 21.25 | 5948.75
-1.00 | [11 empty] | 5948.75
Additional Comments
Reason POOH ? While time drilling @ 1/hr for 6 feet. Motor stalled with 3000 psi of Diff. Pumps cut off and it held 4200 psi. Pressure was released and attempted to free pipe and pump on it. Was not able to pump on it until after the drill string was freed. Max over pull was 100k. After freeing pipe we attempted to pump on it and still was pressuring up. Decision was made to POOH. How did motor drain ? Motor was parted at the extension sub and stator tube Visual wear ? Broked Run Description ? Attempting sidetrack @ 14900 @ 160L. Max temp on run- 149 How Many Stalls and what pressure was seen on stalls ? 1- 3000 Motor Yields ? NA Max Drilling Diff - 100 Average Drilling Diff - 100 Condition of bit on surface - 1-1-WT-C-X-I-NO-DMF
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31181 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Longitude: |  | 96° 40' 25.149" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | ROP / Formation |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/154.00/217.00
Date In: |  | 11/13/2021 14:15 |  | SN: |  | PPM250012 |  |  |  | WOB Rotate (klbs): |  | 26.00
Date Out: |  | 11/16/2021 03:00 |  | Description: |  | 6/7 8.8 2.12 T/S HS88 -.001 |  |  |  | WOB Slide (klbs): |  | 23.68
Depth In/Out(Usft): |  | 14906.00 / 16460.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 70.00 / 61.69
Inc In/Out: |  | 84.33 / 87.89 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 369.46
Azi In/Out: |  | 148.14 / 151.23 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4414.11
Total Drilled (Usft): |  | 1554 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4939.52
%Slide (Ftg): |  | 13.13 |  | Bit to Bend (Usft): |  | 4.01 |  |  |  | Tq On Btm (kftlbs): |  | 17.99
%Slide (Time): |  | 49.58 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 204 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 16.8 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 86.87 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 50.41 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 1350 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 17.08 |  | Length (Usft): |  | 32.97 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 33.88 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 7.28 / 60.75 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 12.14 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 4-6-RO-A-X-I-BT-HP
Rot ROP (Usft/hr): |  | 79.04 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / -0.001 |  |  |  | Drill Hrs: |  | 33.88
Avg ROP (Usft/hr): |  | 45.87 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 7.28
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  | 2.00 |  | 1 | 1 | 8.4 | 4000 | H2O | 0.5
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
65 | 56 | [10 empty] | 0.00 / 5.83
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13601237 |  | 6.75 | 2 |  |  |  | 1 | 1
6/7 8.8 2.12 T/S HS88 -.001 0.00 |  |  |  | PPM250012 |  | 5.25 | 2 |  |  |  | 32.97 | 33.97
BTI Sub 0.00 |  |  |  | BTI 3 |  | 4.812 | 2.188 |  |  |  | 1.65 | 35.62
Pony Collar 0.00 |  |  |  | GT50-10-479 |  | 4.938 | 2.75 |  |  |  | 9.86 | 45.48
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.562 |  |  |  | 3.9 | 49.38
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-592 |  | 5.25 | 2.688 |  |  |  | 31.11 | 80.49
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-458 |  | 5.25 | 2.688 |  |  |  | 30.63 | 111.12
Tomax 0.00 |  |  |  | A52042 |  | 5 | 2.25 |  |  |  | 20.64 | 131.76
Crossover 0.00 |  |  |  | GT52331430 |  | 5.25 | 2.688 |  |  |  | 3.33 | 135.09
2 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 189.36 | 324.45
Drill N Ream 0.00 |  |  |  | 579 |  | 5.375 | 2.625 |  |  |  | 8.63 | 333.08
26 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 2453.99 | 2787.07
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.688 |  |  |  | 21.4 | 2808.47
33 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 3118.73 | 5927.2
Agitator (Ball Drop) 0.00 |  |  |  | PG525-0035 |  | 5.25 | 2.688 |  |  |  | 21.25 | 5948.45
-1.00 | [11 empty] | 5948.45
Additional Comments
Reason POOH ? While drilling, ROP slowed from 120/hr down to 30/hr How did motor drain ? Motor drained Visual wear ? None Run Description ? Side track and cont drilling Max temp on run- 149 How Many Stalls and what pressure was seen on stalls ? 0 Motor Yields ? 7-12 Max Drilling Diff - 800 Average Drilling Diff - 55 Condition of bit on surface - 4-6-RO-A-X-I-BT-HP
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 6
|  |  |  | Job # |  | LTX1148421 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31181 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.225" N |  |  | Well: |  | Bighorn Pass H06
|  |  |  | Longitude: |  | 96° 40' 25.149" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 6
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/148.00/171.00
Date In: |  | 11/16/2021 06:45 |  | SN: |  | PPM250023 |  |  |  | WOB Rotate (klbs): |  | 21.00
Date Out: |  | 11/19/2021 19:00 |  | Description: |  | 6/7 8.8 2.12 T/S HS88 .003 |  |  |  | WOB Slide (klbs): |  | 24.52
Depth In/Out(Usft): |  | 16460.00 / 19363.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 70.00 / 66.97
Inc In/Out: |  | 87.89 / 86.17 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 371
Azi In/Out: |  | 151.23 / 149.47 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4310.25
Total Drilled (Usft): |  | 2903 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5051.42
%Slide (Ftg): |  | 7.27 |  | Bit to Bend (Usft): |  | 4.11 |  |  |  | Tq On Btm (kftlbs): |  | 16.33
%Slide (Time): |  | 28.57 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 211 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 7.27 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.73 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 71.43 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2692 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 18.18 |  | Length (Usft): |  | 32.95 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 25.45 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 6
Circ/BRT Hrs: |  | 13.75 / 84.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 29.02 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-3-LT-S-X-I-WT-TD
Rot ROP (Usft/hr): |  | 148.07 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.003 |  |  |  | Drill Hrs: |  | 25.45
Avg ROP (Usft/hr): |  | 114.07 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 13.75
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  | 2.00 |  | 1 | 1 | 8.4 | 4000 | H2O | 0.5
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
65 | 56 | [10 empty] | 0.00 / 3.20
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13673682 |  | 6.75 | 2 |  |  |  | 1 | 1
6/7 8.8 2.12 T/S HS88 .003 0.00 |  |  |  | PPM250023 |  | 5.25 | 2 |  |  |  | 32.95 | 33.95
BTI Sub 0.00 |  |  |  | BTI 3 |  | 4.812 | 2.188 |  |  |  | 1.65 | 35.6
Pony Collar 0.00 |  |  |  | GT50-10-479 |  | 4.938 | 2.75 |  |  |  | 9.86 | 45.46
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.562 |  |  |  | 3.9 | 49.36
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-592 |  | 5.25 | 2.688 |  |  |  | 31.11 | 80.47
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-458 |  | 5.25 | 2.688 |  |  |  | 30.63 | 111.1
Tomax 0.00 |  |  |  | A52042 |  | 5 | 2.25 |  |  |  | 20.64 | 131.74
Crossover 0.00 |  |  |  | GT52331430 |  | 5.25 | 2.688 |  |  |  | 3.33 | 135.07
2 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 189.36 | 324.43
Drill N Ream 0.00 |  |  |  | 579 |  | 5.375 | 2.625 |  |  |  | 8.63 | 333.06
26 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 2453.99 | 2787.05
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.688 |  |  |  | 21.4 | 2808.45
33 Stands 4 1/2" DP 0.00 | [5 empty] | 4.5 | 3.8 |  |  |  | 3118.73 | 5927.18
Agitator (Ball Drop) 0.00 |  |  |  | PG525-0035 |  | 5.25 | 2.688 |  |  |  | 21.25 | 5948.43
-1.00 | [11 empty] | 5948.43
Additional Comments
Reason POOH ? TD well How did motor drain ? Motor drained as it should Visual wear ? No visible wear to motor Run Description ? Drilled well to TD Max temp on run- 152 while drilling on mudcap How Many Stalls and what pressure was seen on stalls ?0 Motor Yields ? 10/100 Max Drilling Diff - 1000 Average Drilling Diff - 800 Condition of bit on surface - 1-3-LT-S-X-I-WT-TD
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 6
Well Name: |  |  |  |  | Bighorn Pass H06 ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 65.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 149.5 |  | Rotate: |  | 0
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
11/12/2021 | 19:30 | 24:00 | 4.5 | 14900 | 14904 | 4 | Slide | TTF: -150; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 290; Drilling Parameters ROP: 0.89 | 3900 | 3800 | 100 | 144 | 270 | 220 | 170
11/13/2021 | 00:00 | 02:18 | 2.3 | 14904 | 14906 | 2 | Slide | TTF: -150; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 290; Drilling Parameters ROP: 0.87 | 3900 | 3800 | 100 | 144 | 270 | 220 | 170

## BHA_5_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 1554
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 204
Well Name: |  |  |  |  | Bighorn Pass H06 ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 65.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 149.5 |  | Rotate: |  | 1350
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
11/14/2021 | 00:00 | 06:00 | 6 | 14906 | 14916 | 10 | Slide | 130 | 14909 | 84.31 | 148.11 | 10385.32 | -3746.62 | 2374.36 | -3746.62 | 1.05 |  |  | 20 |  | 290 |  | 1.67 | 4100 | 3920 | 180 | 217 | 270 | 220 | 150
11/14/2021 | 08:15 | 09:10 | 0.91667 | 14916 | 14920 | 4 | Slide | TTF: -120; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 4.36 | 4450 | 4350 | 100 | 217 | 320 | 190 | 100
11/14/2021 | 09:10 | 10:45 | 1.5833 | 14920 | 14930 | 10 | Slide | TTF: -90; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 6.32 | 4450 | 4350 | 100 | 217 | 320 | 190 | 100
11/14/2021 | 10:45 | 11:55 | 1.1667 | 14930 | 14938 | 8 | Slide | TTF: -60; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 6.86 | 4450 | 4350 | 100 | 217 | 320 | 190 | 100
11/14/2021 | 12:10 | 13:00 | 0.83333 | 14938 | 14974 | 36 | Rotate |  | 14940 | 83.55 | 146.46 | 10388.59 | -3772.55 | 2391.02 | -3772.55 | 5.83 |  |  | 25 | 35 | 370 | 12 | 43.2 | 4650 | 4350 | 300 | 217 | 320 | 185 | 100
11/14/2021 | 13:10 | 13:50 | 0.66667 | 14974 | 15006 | 32 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 15; Drilling Parameters ROP: 48 | 4900 | 4500 | 400 | 217 | 320 | 185 | 100
11/14/2021 | 13:55 | 15:29 | 1.5667 | 15006 | 15099 | 93 | Rotate |  | 15034 | 84.64 | 145.92 | 10398.26 | -3850.24 | 2443.05 | -3850.24 | 1.29 |  |  | 27.51 | 48.24 | 368.8 | 14.37 | 59.36 | 4937.82 | 4246.41 | 691.41 | 141.8 | 320 | 174.65 | 100
11/14/2021 | 15:38 | 16:03 | 0.41667 | 15099 | 15115 | 16 | Rotate | Drilling Parameters WOB: 15.43; Drilling Parameters RPM: 52.92; Drilling Parameters FLOW: 368.9; Drilling Parameters Tq: 13.42; Drilling Parameters ROP: 38.4 | 4232.26 | 4199.54 | 32.72 | 145.4 | 330 | 184.72 | 100
11/14/2021 | 16:03 | 16:26 | 0.38333 | 15115 | 15123 | 8 | Slide | TTF: -3.41; Drilling Parameters WOB: 13.15; Drilling Parameters FLOW: 369.18; Drilling Parameters ROP: 20.87 | 4619.81 | 4413.91 | 205.9 | 134.6 | 330 | 180.82 | 100
11/14/2021 | 16:26 | 17:31 | 1.0833 | 15123 | 15194 | 71 | Rotate |  | 15129 | 86.61 | 145.55 | 10405.51 | -3928.52 | 2496.38 | -3928.52 | 2.11 |  |  | 23.66 | 57.8 | 368.86 | 15.51 | 65.54 | 4944.94 | 4500 | 444.94 | 143.6 | 330 | 169.26 | 100
11/14/2021 | 17:40 | 18:41 | 1.0167 | 15194 | 15288 | 94 | Rotate |  | 15223 | 87.27 | 143.97 | 10410.53 | -4005.18 | 2550.54 | -4005.18 | 1.82 |  |  | 29.26 | 59.25 | 368.95 | 19.32 | 92.46 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 18:46 | 19:20 | 0.56667 | 15288 | 15303 | 15 | Slide | TTF: 90; Drilling Parameters WOB: 35; Drilling Parameters RPM: 59.25; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 19.32; Drilling Parameters ROP: 26.47 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 19:20 | 20:12 | 0.86667 | 15303 | 15383 | 80 | Rotate |  | 15318 | 88.17 | 144.86 | 10414.31 | -4082.38 | 2605.77 | -4082.38 | 1.33 |  |  | 30 | 59.25 | 368.95 | 22 | 92.31 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 20:17 | 21:05 | 0.8 | 15383 | 15476 | 93 | Rotate |  | 15411 | 89.23 | 145.36 | 10416.42 | -4158.64 | 2658.96 | -4158.64 | 1.26 |  |  | 30 | 59.25 | 368.95 | 22 | 116.25 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 21:10 | 21:36 | 0.43333 | 15476 | 15491 | 15 | Slide | TTF: 140; Drilling Parameters WOB: 35; Drilling Parameters RPM: 59.25; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 34.62 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 21:36 | 22:43 | 1.1167 | 15491 | 15571 | 80 | Rotate |  | 15506 | 88.64 | 145.4 | 10418.18 | -4236.8 | 2712.92 | -4236.8 | 0.62 |  |  | 30 | 59.25 | 368.95 | 22 | 71.64 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 22:48 | 23:22 | 0.56667 | 15571 | 15586 | 15 | Slide | TTF: 140; Drilling Parameters WOB: 35; Drilling Parameters RPM: 59.25; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 26.47 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/14/2021 | 23:22 | 24:00 | 0.63333 | 15586 | 15646 | 60 | Rotate |  | 15600 | 86.88 | 145.7 | 10421.86 | -4314.26 | 2766.05 | -4314.26 | 1.9 |  |  | 30 | 70 | 368.95 | 22 | 94.74 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 00:00 | 00:14 | 0.23333 | 15646 | 15665 | 19 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 81.43 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 01:18 | 02:08 | 0.83333 | 15665 | 15760 | 95 | Rotate |  | 15695 | 85.67 | 142.26 | 10428.03 | -4390.92 | 2821.79 | -4390.92 | 3.83 |  |  | 25 | 70 | 368.95 | 22 | 114 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 02:13 | 02:50 | 0.61667 | 15760 | 15780 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 35; Drilling Parameters RPM: 59.25; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 32.43 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 02:50 | 03:11 | 0.35 | 15780 | 15820 | 40 | Rotate |  | 15788 | 88.25 | 145.43 | 10432.96 | -4465.89 | 2876.56 | -4465.89 | 4.39 |  |  | 25 | 70 | 368.95 | 22 | 114.29 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 03:11 | 04:03 | 0.86667 | 15820 | 15835 | 15 | Slide | TTF: 120; Drilling Parameters WOB: 45; Drilling Parameters RPM: 59.25; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 17.31 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 04:03 | 04:19 | 0.26667 | 15835 | 15853 | 18 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 67.5 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 04:25 | 05:05 | 0.66667 | 15853 | 15873 | 20 | Slide | TTF: 120; Drilling Parameters WOB: 30; Drilling Parameters RPM: 59.25; Drilling Parameters FLOW: 368.95; Drilling Parameters Tq: 22; Drilling Parameters ROP: 30 | 5219.71 | 4500 | 719.71 | 138 | 330 | 169.2
11/15/2021 | 05:05 | 06:05 | 1 | 15873 | 15947 | 74 | Rotate |  | 15882 | 86.56 | 147.97 | 10437.22 | -4544.37 | 2928.11 | -4544.37 | 3.24 |  |  | 30 | 70 | 368.95 | 22 | 74 | 5219.71 | 4500 | 719.71 | 145.4 | 330 | 169.2
11/15/2021 | 06:13 | 06:22 | 0.15 | 15947 | 15957 | 10 | Rotate | Drilling Parameters WOB: 14.33; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 369.3; Drilling Parameters Tq: 15.06; Drilling Parameters ROP: 66.67 | 4240.65 | 4349.07 | -108.42 | 145.4 | 330 | 194.29
11/15/2021 | 06:22 | 07:00 | 0.63333 | 15957 | 15972 | 15 | Slide | TTF: 94.22; Drilling Parameters WOB: 16.33; Drilling Parameters FLOW: 368.86; Drilling Parameters ROP: 23.68 | 4539.9 | 4288.14 | 251.76 | 141.8 | 330 | 194.29
11/15/2021 | 07:00 | 07:43 | 0.71667 | 15972 | 16041 | 69 | Rotate |  | 15976 | 87.13 | 150.03 | 10442.39 | -4624.81 | 2976.45 | -4624.81 | 2.27 |  |  | 33.97 | 70 | 368.95 | 18.49 | 96.28 | 4747.67 | 4066.78 | 680.89 | 141.8 | 330 | 178.91
11/15/2021 | 08:06 | 08:59 | 0.88333 | 16041 | 16137 | 96 | Rotate |  | 16071 | 86.4 | 147.47 | 10447.76 | -4705.89 | 3025.65 | -4705.89 | 2.8 |  |  | 27.41 | 70 | 368.89 | 17.43 | 108.68 | 4969.56 | 3628.11 | 1341.45 | 141.8 | 330 | 172.4
11/15/2021 | 09:07 | 09:14 | 0.11667 | 16137 | 16146 | 9 | Rotate | Drilling Parameters WOB: 15.6; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 368.9; Drilling Parameters Tq: 16.31; Drilling Parameters ROP: 77.14 | 4888.76 | 4440.34 | 448.42 | 141.8 | 330 | 177.31
11/15/2021 | 09:14 | 10:08 | 0.9 | 16146 | 16168 | 22 | Slide | 95.63 | 16163 | 86.27 | 148.88 | 10453.64 | -4783.9 | 3074.06 | -4783.9 | 1.54 |  |  | 17.11 |  | 368.5 |  | 24.44 | 4873.25 | 4751.8 | 121.45 | 136.4 | 330 | 177.44
11/15/2021 | 10:08 | 10:45 | 0.61667 | 16168 | 16228 | 60 | Rotate | Drilling Parameters WOB: 30.7; Drilling Parameters RPM: 67.18; Drilling Parameters FLOW: 368.76; Drilling Parameters Tq: 17.46; Drilling Parameters ROP: 97.3 | 4973.06 | 3129.99 | 1843.07 | 140 | 330 | 167.89
11/15/2021 | 10:53 | 11:00 | 0.11667 | 16228 | 16238 | 10 | Rotate | Drilling Parameters WOB: 28.66; Drilling Parameters RPM: 65.51; Drilling Parameters FLOW: 368.8; Drilling Parameters Tq: 17.42; Drilling Parameters ROP: 85.71 | 5173.43 | 4758.9 | 414.53 | 136.4 | 330 | 187.88
11/15/2021 | 11:00 | 11:30 | 0.5 | 16238 | 16250 | 12 | Slide | TTF: 103.32; Drilling Parameters WOB: 18.2; Drilling Parameters FLOW: 368.8; Drilling Parameters ROP: 24 | 5173.43 | 4758.9 | 414.53 | 136.4 | 330 | 187.88
11/15/2021 | 11:30 | 12:13 | 0.71667 | 16250 | 16323 | 73 | Rotate |  | 16257 | 86.81 | 150.81 | 10459.31 | -4865.03 | 3121.2 | -4865.03 | 2.13 |  |  | 30.79 | 67.17 | 368.82 | 17.97 | 101.86 | 5238.93 | 4723.76 | 515.17 | 143.6 | 330 | 170.28
11/15/2021 | 12:22 | 13:32 | 1.1667 | 16323 | 16415 | 92 | Rotate |  | 16350 | 88.38 | 150.29 | 10463.21 | -4945.94 | 3166.88 | -4945.94 | 1.78 |  |  | 26.27 | 67.59 | 376.83 | 18.45 | 78.86 | 5116.99 | 4780.12 | 336.87 | 143.6 | 330 | 176.68
11/15/2021 | 13:49 | 14:00 | 0.18333 | 16415 | 16425 | 10 | Rotate | Drilling Parameters WOB: 22.22; Drilling Parameters RPM: 79.53; Drilling Parameters FLOW: 397.96; Drilling Parameters Tq: 5.51; Drilling Parameters ROP: 54.55 | 4953.61 | 4670.77 | 282.84 | 145.4 | 330 | 184.15
11/15/2021 | 14:00 | 15:00 | 1 | 16425 | 16440 | 15 | Slide | TTF: 153.3; Drilling Parameters WOB: 25.34; Drilling Parameters FLOW: 397.99; Drilling Parameters ROP: 15 | 4713.55 | 4623.77 | 89.78 | 140 | 330 | 184.15
11/15/2021 | 15:00 | 15:44 | 0.73333 | 16440 | 16460 | 20 | Rotate |  | 16445 | 87.63 | 151.32 | 10466.52 | -5028.81 | 3213.19 | -5028.81 | 1.34 |  |  | 27.86 | 70 | 397.93 | 17.36 | 27.27 | 5225.59 | 5136.22 | 89.37 | 138.2 | 330 | 181.5

## BHA_6_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 6 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2903
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 211
Well Name: |  |  |  |  | Bighorn Pass H06 ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 65.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 149.5 |  | Rotate: |  | 2692
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
11/16/2021 | 20:30 | 20:52 | 0.36667 | 16460 | 16510 | 50 | Rotate | Drilling Parameters WOB: 19; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 136.36 | 4750 | 4200 | 550 | 171 | 350 | 125 | 50
11/16/2021 | 20:56 | 21:30 | 0.56667 | 16510 | 16604 | 94 | Rotate |  | 16539 | 89.26 | 150.73 | 10469.07 | -5111.02 | 3258.71 | -5111.02 | 1.84 |  |  | 22 | 70 | 350 | 16 | 165.88 | 4750 | 4200 | 550 | 165 | 350 | 125 | 50
11/16/2021 | 21:43 | 22:17 | 0.56667 | 16604 | 16624 | 20 | Slide | TTF: 150; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16; Drilling Parameters ROP: 35.29 | 4750 | 4200 | 550 | 160 | 350 | 125 | 50
11/16/2021 | 22:17 | 22:52 | 0.58333 | 16624 | 16699 | 75 | Rotate |  | 16634 | 88.71 | 150.86 | 10470.75 | -5193.93 | 3305.05 | -5193.93 | 0.59 |  |  | 29 | 70 | 350 | 16 | 128.57 | 4600 | 4000 | 600 | 150 | 350 | 125 | 50
11/16/2021 | 22:57 | 23:29 | 0.53333 | 16699 | 16719 | 20 | Slide | TTF: 150; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16; Drilling Parameters ROP: 37.5 | 4600 | 4000 | 600 | 145 | 350 | 125 | 50
11/16/2021 | 23:29 | 24:00 | 0.51667 | 16719 | 16794 | 75 | Rotate |  | 16729 | 86.66 | 151.46 | 10474.59 | -5277.07 | 3350.84 | -5277.07 | 2.25 |  |  | 22 | 70 | 350 | 16 | 145.16 | 4600 | 4000 | 600 | 145 | 350 | 125 | 50
11/17/2021 | 00:05 | 01:06 | 1.0167 | 16794 | 16889 | 95 | Rotate |  | 16824 | 85.16 | 151.42 | 10481.37 | -5360.29 | 3396.14 | -5360.29 | 1.58 |  |  | 24 | 70 | 375 | 16 | 93.44 | 5400 | 4650 | 750 | 145 | 350 | 125 | 50
11/17/2021 | 01:11 | 01:50 | 0.65 | 16889 | 16983 | 94 | Rotate |  | 16918 | 84.65 | 150.96 | 10489.72 | -5442.33 | 3441.26 | -5442.33 | 0.73 |  |  | 24 | 70 | 375 | 16 | 144.62 | 5400 | 4650 | 750 | 145 | 350 | 125 | 50
11/17/2021 | 01:55 | 02:26 | 0.51667 | 16983 | 17078 | 95 | Rotate |  | 17013 | 85.25 | 150.03 | 10498.08 | -5524.69 | 3487.86 | -5524.69 | 1.16 |  |  | 24 | 70 | 375 | 16 | 183.87 | 5400 | 4650 | 750 | 151 | 350 | 125 | 50
11/17/2021 | 02:31 | 03:03 | 0.53333 | 17078 | 17173 | 95 | Rotate |  | 17108 | 86.08 | 148.9 | 10505.26 | -5606.28 | 3535.99 | -5606.28 | 1.47 |  |  | 24 | 70 | 375 | 16 | 178.13 | 5400 | 4650 | 750 | 151 | 350 | 125 | 50
11/17/2021 | 03:08 | 03:40 | 0.53333 | 17173 | 17188 | 15 | Slide | TTF: 110; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 16; Drilling Parameters ROP: 28.13 | 5400 | 4650 | 750 | 138 | 350 | 125 | 50
11/17/2021 | 03:40 | 04:18 | 0.63333 | 17188 | 17267 | 79 | Rotate |  | 17202 | 86.44 | 149.93 | 10511.39 | -5687.03 | 3583.72 | -5687.03 | 1.16 |  |  | 24 | 70 | 375 | 16 | 124.74 | 5400 | 4650 | 750 | 135 | 350 | 125 | 50
11/17/2021 | 05:05 | 05:44 | 0.65 | 17267 | 17361 | 94 | Rotate |  | 17296 | 87.25 | 149.15 | 10516.56 | -5767.93 | 3631.3 | -5767.93 | 1.2 |  |  | 24 | 70 | 375 | 16 | 144.62 | 5400 | 4650 | 750 | 135 | 350 | 125 | 50
11/17/2021 | 05:49 | 06:17 | 0.46667 | 17361 | 17455 | 94 | Rotate |  | 17390 | 87.81 | 147.96 | 10520.62 | -5848.05 | 3680.29 | -5848.05 | 1.4 |  |  | 24.52 | 69.85 | 374.22 | 15.99 | 201.04 | 4834.95 | 3106.92 | 1728.03 | 140 | 350 | 163.63 | 50
11/17/2021 | 06:25 | 06:30 | 0.083333 | 17455 | 17465 | 10 | Rotate | Drilling Parameters WOB: 20.41; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 374.13; Drilling Parameters Tq: 16.1; Drilling Parameters ROP: 120 | 5131.06 | 4370.48 | 760.58 | 136.4 | 350 | 167.55 | 50
11/17/2021 | 06:30 | 06:54 | 0.4 | 17465 | 17480 | 15 | Slide | TTF: 135; Drilling Parameters WOB: 20.41; Drilling Parameters FLOW: 374.13; Drilling Parameters ROP: 37.5 | 5131.06 | 4370.48 | 760.58 | 136.4 | 350 | 167.55 | 50
11/17/2021 | 06:54 | 07:23 | 0.48333 | 17480 | 17549 | 69 | Rotate |  | 17484 | 88.12 | 150.25 | 10523.95 | -5928.66 | 3728.52 | -5928.66 | 2.46 |  |  | 21.24 | 70 | 374.15 | 16.26 | 142.76 | 5133.8 | 3708.07 | 1425.73 | 138.2 | 350 | 158.19 | 50
11/17/2021 | 07:29 | 07:34 | 0.083333 | 17549 | 17559 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 374.32; Drilling Parameters Tq: 14.24; Drilling Parameters ROP: 120 | 4598.46 | 4287.13 | 311.33 | 141.8 | 350 | 180.09 | 50
11/17/2021 | 07:34 | 07:56 | 0.36667 | 17559 | 17571 | 12 | Slide | TTF: 160; Drilling Parameters WOB: 11.72; Drilling Parameters FLOW: 374.32; Drilling Parameters ROP: 32.73 | 4598.46 | 4287.13 | 311.33 | 136.4 | 350 | 180.09 | 50
11/17/2021 | 07:56 | 08:27 | 0.51667 | 17571 | 17643 | 72 | Rotate |  | 17578 | 87.04 | 151.59 | 10527.92 | -6010.73 | 3774.16 | -6010.73 | 1.83 |  |  | 18.9 | 70 | 374.15 | 16.37 | 139.35 | 5020.78 | 4319.43 | 701.35 | 136.4 | 350 | 161.19 | 50
11/17/2021 | 08:49 | 08:54 | 0.083333 | 17643 | 17653 | 10 | Rotate | Drilling Parameters WOB: 20.08; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 374.02; Drilling Parameters Tq: 15.52; Drilling Parameters ROP: 120 | 5349.9 | 4928.18 | 421.72 | 136.4 | 350 | 183.8 | 50
11/17/2021 | 08:54 | 09:20 | 0.43333 | 17653 | 17661 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 20.08; Drilling Parameters FLOW: 374.02; Drilling Parameters ROP: 18.46 | 5349.9 | 4928.18 | 421.72 | 136.4 | 350 | 183.8 | 50
11/17/2021 | 09:20 | 09:50 | 0.5 | 17661 | 17736 | 75 | Rotate |  | 17671 | 84.93 | 150.87 | 10534.43 | -6092.05 | 3818.81 | -6092.05 | 2.4 |  |  | 24.03 | 70 | 374.03 | 16.4 | 150 | 5413.65 | 4072.99 | 1340.66 | 141.8 | 350 | 154.59 | 50
11/17/2021 | 09:56 | 10:27 | 0.51667 | 17736 | 17830 | 94 | Rotate |  | 17765 | 84.88 | 150.97 | 10542.78 | -6173.87 | 3864.32 | -6173.87 | 0.12 |  |  | 16.55 | 70 | 373.99 | 16.57 | 181.94 | 5439.3 | 3602.02 | 1837.28 | 150.8 | 350 | 158.64 | 50
11/17/2021 | 10:40 | 11:10 | 0.5 | 17830 | 17925 | 95 | Rotate |  | 17860 | 85.55 | 150.68 | 10550.71 | -6256.53 | 3910.47 | -6256.53 | 0.77 |  |  | 20.42 | 70 | 374.05 | 16.86 | 190 | 5058.48 | 3158.47 | 1900.01 | 154.4 | 350 | 158.53 | 50
11/17/2021 | 11:17 | 11:48 | 0.51667 | 17925 | 18019 | 94 | Rotate |  | 17954 | 87.38 | 150.04 | 10556.5 | -6338.07 | 3956.86 | -6338.07 | 2.06 |  |  | 21.4 | 70 | 374.11 | 17.55 | 181.94 | 4864.97 | 3677.12 | 1187.85 | 156.2 | 350 | 156.38 | 50
11/17/2021 | 12:00 | 12:08 | 0.13333 | 18019 | 18029 | 10 | Rotate | Drilling Parameters WOB: 22.11; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 374.27; Drilling Parameters Tq: 14.95; Drilling Parameters ROP: 75 | 4640.06 | 4520.19 | 119.87 | 156.2 | 350 | 172.49 | 50
11/17/2021 | 12:08 | 12:48 | 0.66667 | 18029 | 18046 | 17 | Slide | TTF: 164; Drilling Parameters WOB: 19.56; Drilling Parameters FLOW: 374.04; Drilling Parameters ROP: 25.5 | 5339.02 | 5003.85 | 335.17 | 152.6 | 350 | 172.49 | 50
11/17/2021 | 12:48 | 13:17 | 0.48333 | 18046 | 18114 | 68 | Rotate |  | 18049 | 86.82 | 150.05 | 10561.31 | -6420.27 | 4004.24 | -6420.27 | 0.59 |  |  | 23.99 | 70 | 373.94 | 17.51 | 140.69 | 5320.15 | 3920.6 | 1399.55 | 154.4 | 350 | 159.69 | 50
11/17/2021 | 13:24 | 13:31 | 0.11667 | 18114 | 18124 | 10 | Rotate | Drilling Parameters WOB: 21.55; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 374.24; Drilling Parameters Tq: 15.51; Drilling Parameters ROP: 85.71 | 4398.58 | 4220.99 | 177.59 | 156.2 | 350 | 173.27 | 50
11/17/2021 | 13:31 | 14:08 | 0.61667 | 18124 | 18134 | 10 | Slide | TTF: 162.44; Drilling Parameters WOB: 10.71; Drilling Parameters FLOW: 373.73; Drilling Parameters ROP: 16.22 | 5305.68 | 4971.59 | 334.09 | 152.6 | 350 | 167.66 | 50
11/17/2021 | 14:08 | 14:37 | 0.48333 | 18134 | 18208 | 74 | Rotate |  | 18143 | 86.12 | 150.26 | 10567.1 | -6501.65 | 4050.93 | -6501.65 | 0.78 |  |  | 16.24 | 70 | 373.93 | 17.61 | 153.1 | 5299.92 | 3923.43 | 1376.49 | 152.6 | 350 | 157.77 | 50
11/17/2021 | 15:00 | 15:15 | 0.25 | 18208 | 18232 | 24 | Rotate | Drilling Parameters WOB: 15.53; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 374.19; Drilling Parameters Tq: 17.18; Drilling Parameters ROP: 96 | 4690.29 | 4646.3 | 43.99 | 154.4 | 350 | 177.86 | 50
11/17/2021 | 15:15 | 15:55 | 0.66667 | 18232 | 18246 | 14 | Slide | 174.38 | 18238 | 85.6 | 150.69 | 10573.95 | -6584.1 | 4097.62 | -6584.1 | 0.71 |  |  | 19.47 |  | 373.92 |  | 21 | 5260.65 | 4882.99 | 377.66 | 143.6 | 350 | 177.86 | 50
11/17/2021 | 15:55 | 16:21 | 0.43333 | 18246 | 18303 | 57 | Rotate | Drilling Parameters WOB: 22.97; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 373.89; Drilling Parameters Tq: 16.85; Drilling Parameters ROP: 131.54 | 5280.57 | 4103.54 | 1177.03 | 147.2 | 350 | 162.67 | 50
11/17/2021 | 16:59 | 17:34 | 0.58333 | 18303 | 18397 | 94 | Rotate |  | 18332 | 85.89 | 149.59 | 10580.93 | -6665.39 | 4144.29 | -6665.39 | 1.21 |  |  | 20.89 | 70 | 374.04 | 16.99 | 161.14 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 17:41 | 18:17 | 0.6 | 18397 | 18492 | 95 | Rotate |  | 18427 | 87.38 | 148.99 | 10586.51 | -6746.93 | 4192.73 | -6746.93 | 1.69 |  |  | 20.89 | 70 | 374.04 | 16.99 | 158.33 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 18:22 | 19:02 | 0.66667 | 18492 | 18512 | 20 | Slide | TTF: 150; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 374.04; Drilling Parameters Tq: 16.99; Drilling Parameters ROP: 30 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 19:02 | 19:34 | 0.53333 | 18512 | 18586 | 74 | Rotate |  | 18521 | 86.56 | 148.69 | 10591.47 | -6827.25 | 4241.3 | -6827.25 | 0.93 |  |  | 20.89 | 70 | 374.04 | 16.99 | 138.75 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 19:39 | 20:19 | 0.66667 | 18586 | 18681 | 95 | Rotate |  | 18616 | 88.5 | 147.71 | 10595.57 | -6907.91 | 4291.31 | -6907.91 | 2.29 |  |  | 20.89 | 70 | 374.04 | 16.99 | 142.5 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 20:33 | 21:13 | 0.66667 | 18681 | 18701 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 374.04; Drilling Parameters Tq: 16.99; Drilling Parameters ROP: 30 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 21:13 | 21:56 | 0.71667 | 18701 | 18774 | 73 | Rotate |  | 18709 | 87.04 | 147.62 | 10599.19 | -6986.43 | 4341.01 | -6986.43 | 1.57 |  |  | 20.89 | 70 | 374.04 | 16.99 | 101.86 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 22:05 | 22:35 | 0.5 | 18774 | 18869 | 95 | Rotate |  | 18804 | 87.9 | 146.03 | 10603.38 | -7065.86 | 4392.94 | -7065.86 | 1.9 |  |  | 20.89 | 70 | 374.04 | 16.99 | 190 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 22:40 | 23:22 | 0.7 | 18869 | 18889 | 20 | Slide | TTF: 150; Drilling Parameters WOB: 20.89; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 374.04; Drilling Parameters Tq: 16.99; Drilling Parameters ROP: 28.57 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/17/2021 | 23:22 | 23:53 | 0.51667 | 18889 | 18963 | 74 | Rotate |  | 18898 | 85.58 | 147.95 | 10608.73 | -7144.55 | 4444.06 | -7144.55 | 3.2 |  |  | 20.89 | 70 | 374.04 | 16.99 | 143.23 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/18/2021 | 00:00 | 00:43 | 0.71667 | 18963 | 19057 | 94 | Rotate |  | 18992 | 85.83 | 148.63 | 10615.77 | -7224.29 | 4493.33 | -7224.29 | 0.77 |  |  | 20.89 | 70 | 374.04 | 16.99 | 131.16 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/18/2021 | 00:50 | 01:21 | 0.51667 | 19057 | 19152 | 95 | Rotate |  | 19087 | 87.42 | 148.53 | 10621.36 | -7305.22 | 4542.77 | -7305.22 | 1.68 |  |  | 20.89 | 70 | 374.04 | 16.99 | 183.87 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/18/2021 | 01:32 | 01:59 | 0.45 | 19152 | 19172 | 20 | Slide | TTF: 150; Drilling Parameters WOB: 20.89; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 374.04; Drilling Parameters Tq: 16.99; Drilling Parameters ROP: 44.44 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/18/2021 | 01:59 | 02:31 | 0.53333 | 19172 | 19246 | 74 | Rotate |  | 19181 | 85.45 | 149.96 | 10627.2 | -7385.84 | 4590.74 | -7385.84 | 2.59 |  |  | 20.89 | 70 | 374.04 | 16.99 | 138.75 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/18/2021 | 02:38 | 03:07 | 0.48333 | 19246 | 19341 | 95 | Rotate |  | 19276 | 86.17 | 149.47 | 10634.14 | -7467.65 | 4638.52 | -7467.65 | 0.92 |  |  | 20.89 | 70 | 374.04 | 16.99 | 196.55 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50
11/18/2021 | 03:15 | 03:23 | 0.13333 | 19341 | 19363 | 22 | Rotate | Drilling Parameters WOB: 20.89; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 374.04; Drilling Parameters Tq: 16.99; Drilling Parameters ROP: 165 | 5000.4 | 4380.11 | 620.29 | 150.8 | 350 | 162.08 | 50