## Summary
Magnolia Oil & Gas / Bighorn Plains H02 / LTX1148621 / Patterson 248
Report Date: | 10/29/2021 | Current Depth: | 18929
Start Date: | 10/04/2021 | Casing Depth: | 0
Daily Cost: | 4750 | Distance to TD:
Well Cost: | 166640 | Average ROP: | 0
Drilling Hours: | 0 | Svy MD: | 18929
24Hr Forcast: | Land Casing and Cement | Svy Inc: | 84.52
Current BHA: |  | Svy Azi: | 154.4
Current BRT Hrs: | 0 | Svy TVD: | 10548.44
Bit Make / Model: |  | Svy NS: | -8003.74
POOH in last 24Hrs: | No | Svy EW: | 1965.43
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | WBM | Svy Left/Right: | 0
Directional Driller Day: | Jesse Taylor | MWD Day: | Danny Veronie
Directional Driller Night: | Robert E Wallace | MWD Night: | Jason Smetters
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 279
24Hr Summary: | Running Casing | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
500037 | UBHO |  |  | Clean
500029 | UBHO |  |  | Dirty |  | 116.93 | 116.93

## Well Summary
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Total Drilled (Usft): |  | 18821 |  |  | Total Days: |  | 17
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 3020 | 2912 |  | 405.38 |  | 12.71 | 7.18 | 2.58 | 11.75
2 | 2 | 9.875 | 3020 | 9928 | 6908 |  | 196.53 |  | 12.62 | 35.15 | 6.62 | 56.25
3 | 3 | 6.75 | 9928 | 17088 | 7160 |  | 133.92 |  | 14.57 | 53.47 | 18.63 | 100.75
4 | 4 | 6.75 | 17088 | 18929 | 1841 |  | 106.42 |  | 2.5 | 17.3 | 27.53 | 52.33 | YES
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | New |  | 0-1-NO-A-X-I-NO-TD |  | 1.353 | 2912 | 7.1833 | 405.38
2 | Ulterra |  | SPL613 |  | 9.875 | New |  |  |  | 1.491 | 6908 | 35.15 | 196.53
3 | Halliburton |  | GTD64M |  | 6.75 | New |  | 2-3-BT-N-X-I-CT-DMF |  | 1.491 | 7160 | 53.4667 | 133.92
4 | Halliburton |  | GTD64M |  | 6.75 |  |  | 1-2-BT-S-X-I-NO-TD |  | 1.491 | 1841 | 17.3 | 106.42
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.9 | 2912 |  | 405.38
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 5.97 | 6908 |  | 196.53
3 | PDCI |  | 6/7 11.7 |  | 6/7 | 11.7 | 5.25 | 2.12 | 4.14 | 7160 |  | 133.92
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.25 | 2.12 | 4.02 | 1841 |  | 106.42
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | Jesse Taylor |  | Danny Veronie |  | Jason Smetters |  | Brandon Parks |  | Chris Mayeaux |  | Peter Langille
Josh Ray |  | Marshall Adams | [5 empty] | Kevin Burt |  | Jim Harrison
Robert E Wallace
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 3.00 / 0.39 |  | 2912 |  | 408.99 |  | 0.45 / 0.00 |  | 1 |  | 7.12
INT: INTERMEDIATE |  |  | 4.58 / 1.65 |  | 6908 |  | 196.59 |  |  |  | 1 |  | 35.14
CRV: CURVE |  |  | 1.42 / 0.46 |  | 1004 |  | 103.72 |  |  |  | 1 |  | 9.68
LAT: LATERAL |  |  | 6.25 / 4.59 |  | 7997 |  | 130.88 |  |  |  | 2 |  | 61.1
Total |  |  | 15.24 |  | 18821 |  | 166.5 |  | 0.45 / 0.00 |  | 4 |  | 113.04
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 3020.00 | 469.00 | 2542.00 | 217.65 | 370.00 | 12.71 | 2912.00 | 408.99 | 7.12 | 1.70
INT: INTERMEDIATE-BHA 2 |  |  | 3020.00 | 9928.00 | 401.86 | 6036.00 | 43.34 | 872.00 | 12.62 | 6908.00 | 196.59 | 35.14 | 20.12
CRV: CURVE-BHA 3 |  |  | 9928.00 | 10932.00 | 108.97 | 401.00 | 100.50 | 603.00 | 60.06 | 1004.00 | 103.72 | 9.68 | 6.00
LAT: LATERAL-BHA 3 |  |  | 10932.00 | 17088.00 | 172.69 | 5716.00 | 41.20 | 440.00 | 7.15 | 6156.00 | 140.61 | 43.78 | 10.68
LAT: LATERAL-BHA 4 |  |  | 17088.00 | 18929.00 | 131.02 | 1795.00 | 12.71 | 46.00 | 2.50 | 1841.00 | 106.29 | 17.32 | 3.62
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1148621 | Total Drilled(Usft) | 18821.00
Operator | Magnolia Oil & Gas | Drilling Hours | 113.10
Well Name | Bighorn Plains H02 | Avg ROP(Usft/hr) | 166.41
Rig | Patterson 248 | Rotary Drilled(Usft) | 16490.00
State | Texas | Rotary Hours | 70.98
County | Washington | Rotary ROP(Usft/hr) | 232.31
Formation | Austin Chalk | Rotary % | 87.61
Start Date | 10/04/2021 | Slide Drilled(Usft) | 2331.00
End Date | 10/29/2021 | Slide Hours | 42.12
Days On Well | 17 | Slide ROP(Usft/hr) | 55.35
Start Depth (Usft) | 108.00 | Slide % | 12.39
End Depth (Usft) | 18929.00
Total Drilled (Usft) | 18821.00
# BHA's | 4
# Motor Failures | 1
# MWD Failures | 0
NPT hrs (Rig/Dir) | 2.20 / 0.00
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 10/04/2021 | 10/17/2021 | 10/21/2021 | 10/23/2021
End Date | 10/07/2021 | 10/21/2021 | 10/22/2021 | 10/29/2021
Total Days | 3.00 | 4.58 | 1.42 | 6.25
Start Depth (Usft) | 108.00 | 3020.00 | 9928.00 | 10932.00
End Depth (Usft) | 3020.00 | 9928.00 | 10932.00 | 18929.00
Total Drilled(Usft) | 2912.00 | 6908.00 | 1004.00 | 7997.00
Drilling Hours | 7.18 | 35.15 | 9.68 | 61.08
Circulating Hours | 2.58 | 6.62 | 4.32 | 41.85
Total D&C Hours | 9.77 | 41.77 | 14.00 | 102.93
Avg ROP(Usft/hr) | 405.38 | 196.53 | 103.68 | 130.92
Rotary Drilled(Usft) | 2542.00 | 6036.00 | 401.00 | 7511.00
Rotary Hours | 5.47 | 15.03 | 3.68 | 46.80
Rotary ROP(Usft/hr) | 465.00 | 401.51 | 108.87 | 160.49
Rotary % | 87.29 | 87.38 | 39.94 | 93.92
Slide Drilled(Usft) | 370.00 | 872.00 | 603.00 | 486.00
Slide Hours | 1.72 | 20.12 | 6.00 | 14.28
Slide ROP(Usft/hr) | 215.53 | 43.35 | 100.50 | 34.03
Slide % | 12.71 | 12.62 | 60.06 | 6.08
# BHA | 1 | 1 | 1 | 2
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.45 / 0.00 | 1.00 / 0.00 | 0.00 / 0.00 | 0.75 / 0.00
Total Phase Hrs | 9.42 | 39.70 | 11.08 | 110.05
Phase ROP (Usft/hr) | 309.24 | 174.01 | 90.59 | 72.67
Avg Motor Yield (°/100ft) | 7.52 | 8.30 | 14.67 | 19.50
Avg Rotary DLS (°/100ft) | 0.21 | 0.68 | 0.00 | 0.99
Avg Rotary TF | -35.02 | 178.97 | 0.00 | -19.27
Avg Slide Length (Usft) | 21.76 | 30.07 | 60.30 | 13.50
# Slides | 17 | 29 | 10 | 36
BHA Data
BHA# | 1 | 2 | 3 | 4
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4
Bit Size | 13.500 | 9.875 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Halliburton / GTD64M | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491
Grade In | New | New | New
Grade Out | 0-1-NO-A-X-I-NO-TD |  | 2-3-BT-N-X-I-CT-DMF | 1-2-BT-S-X-I-NO-TD
Motor SN | PPM800023 | PPM800035 | PPM250018 | PPM250010
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 11.7 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 11.7 | 6/7 / 8.8
WOB (klbs) | 5.00 / 9.75 / 10.00 | 6.44 / 24.11 / 39.22 | 10.00 / 26.41 / 50.00 | 20.00 / 24.77 / 37.00
Diff P (psi) | 100.00 / 493.75 / 500.00 | 10.56 / 313.79 / 869.47 | 455.00 / 832.84 / 1100.00 | 850.00 / 948.06 / 1040.00
Bend | 1.500 | 2.000 | 2.120 | 2.120
Date In | 10/06/2021 | 10/17/2021 | 10/21/2021 | 10/25/2021
Date Out | 10/07/2021 | 10/19/2021 | 10/25/2021 | 10/28/2021
Time In | 15:40 | 09:30 | 15:30 | 22:40
Time Out | 03:25 | 17:45 | 20:15 | 03:00
BRT Hrs | 11.75 | 56.25 | 100.75 | 52.33
Start Depth (Usft) | 108.00 | 3020.00 | 9928.00 | 17088.00
End Depth (Usft) | 3020.00 | 9928.00 | 17088.00 | 18929.00
Total Drilled(Usft) | 2912.00 | 6908.00 | 7160.00 | 1841.00
Drilling Hours | 7.18 | 35.15 | 53.47 | 17.30
Circulating Hours | 2.58 | 6.62 | 18.63 | 27.53
Total D&C Hours | 9.77 | 41.77 | 72.10 | 44.83
Avg ROP(Usft/hr) | 405.38 | 196.53 | 133.92 | 106.42
Rotary Drilled(Usft) | 2542.00 | 6036.00 | 6117.00 | 1795.00
Rotary Hours | 5.47 | 15.03 | 36.80 | 13.68
Rotary ROP(Usft/hr) | 465.00 | 401.51 | 166.22 | 131.18
Rotary % | 87.29 | 87.38 | 85.43 | 97.50
Slide Drilled(Usft) | 370.00 | 872.00 | 1043.00 | 46.00
Slide Hours | 1.72 | 20.12 | 16.67 | 3.62
Slide ROP(Usft/hr) | 215.53 | 43.35 | 62.58 | 12.72
Slide % | 12.71 | 12.62 | 14.57 | 2.50
Motor Failure | NO | NO | NO | YES
MWD Failure | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | NO
LIH | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 7.52 | 8.30 | 18.82 | 14.59
Avg Rotary DLS (°/100ft) | 0.21 | 0.68 | 1.12 | 0.70
Avg Rotary TF | -35.02 | 178.97 | -12.84 | -64.53
Avg Slide Length (Usft) | 20.56 | 30.07 | 24.83 | 11.50
# Slides | 18 | 29 | 42 | 4

## Personnel Report
|  | Job # | LTX1148621 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31179 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Bighorn Plains H02
|  | Date: | 10/29/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Bighorn Plains H02 - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Danny Veronie | Day MWD |  | 10/04/2021 - 06:00 | 10/07/2021 - 18:00 |  | 4.00 / 48.00
Danny Veronie | Day MWD |  | 10/17/2021 - 06:00 | 10/29/2021 - 18:00 |  | 13.00 / 156.00
Jason Smetters | Night MWD |  | 10/04/2021 - 18:00 | 10/07/2021 - 18:00 |  | 4.00 / 0.00
Jason Smetters | Night MWD |  | 10/17/2021 - 18:00 | 10/29/2021 - 18:00 |  | 13.00 / 0.00
Jesse Taylor | Day DD |  | 10/19/2021 - 06:00 | 10/29/2021 - 18:00 |  | 11.00 / 132.00
Jesse Taylor | Night DD |  | 10/17/2021 - 18:00 | 10/18/2021 - 18:00 |  | 2.00 / 0.00
Josh Ray | Day DD |  | 10/04/2021 - 06:00 | 10/07/2021 - 18:00 |  | 4.00 / 48.00
Josh Ray | Day DD |  | 10/17/2021 - 06:00 | 10/18/2021 - 18:00 |  | 2.00 / 24.00
Marshall Adams | Night DD |  | 10/04/2021 - 18:00 | 10/07/2021 - 18:00 |  | 4.00 / 0.00
NA | Trainee 1 |  | 10/04/2021 - 00:00 | 10/07/2021 - 00:00 |  | 4.00 / 0.00
NA | Trainee 1 |  | 10/17/2021 - 00:00 | 10/29/2021 - 00:00 |  | 13.00 / 0.00
NA | Trainee 2 |  | 10/04/2021 - 00:00 | 10/07/2021 - 00:00 |  | 4.00 / 0.00
NA | Trainee 2 |  | 10/17/2021 - 00:00 | 10/29/2021 - 00:00 |  | 13.00 / 0.00
NA | Rss Eng. 1 |  | 10/04/2021 - 00:00 | 10/07/2021 - 00:00 |  | 4.00 / 0.00
NA | Rss Eng. 1 |  | 10/17/2021 - 00:00 | 10/29/2021 - 00:00 |  | 13.00 / 0.00
NA | Rss Eng. 2 |  | 10/04/2021 - 00:00 | 10/07/2021 - 00:00 |  | 4.00 / 0.00
NA | Rss Eng. 2 |  | 10/17/2021 - 00:00 | 10/29/2021 - 00:00 |  | 13.00 / 0.00
NA | Third Man |  | 10/04/2021 - 00:00 | 10/07/2021 - 00:00 |  | 4.00 / 0.00
NA | Third Man |  | 10/17/2021 - 00:00 | 10/29/2021 - 00:00 |  | 13.00 / 0.00
NA | Fourth Man |  | 10/04/2021 - 00:00 | 10/07/2021 - 00:00 |  | 4.00 / 0.00
NA | Fourth Man |  | 10/17/2021 - 00:00 | 10/29/2021 - 00:00 |  | 13.00 / 0.00
Robert E Wallace | Night DD |  | 10/19/2021 - 18:00 | 10/29/2021 - 18:00 |  | 11.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1148621 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Bighorn Plains H02 | [7 empty] | Day DD: |  |  |  |  | Jesse Taylor | [5 empty] | API #: |  |  |  | 42-477-31179
|  |  |  | AFE #: |  |  | 21DD0216MG | [7 empty] | Night DD: |  |  |  |  | Robert E Wallace | [5 empty] | Company Man: |  |  |  | Brandon Parks
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Jason Smetters | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 10/04/2021 | 10/05/2021 | 10/06/2021 | 10/07/2021 | 10/08/2021 | 10/09/2021 | 10/10/2021 | 10/11/2021 | 10/12/2021 | 10/13/2021 | 10/14/2021 | 10/15/2021 | 10/16/2021 | 10/17/2021 | 10/18/2021 | 10/19/2021 | 10/20/2021 | 10/21/2021 | 10/22/2021 | 10/23/2021 | 10/24/2021 | 10/25/2021 | 10/26/2021 | 10/27/2021 | 10/28/2021 | 10/29/2021 | 10/30/2021 | 10/31/2021 | 11/01/2021 | 11/02/2021 | 11/03/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Cross Over |  | 5.25 | Crossover |  | Steel | GT52331430 | 8 | 10 | [16 empty] | O | X | X | X | X | X | X | X | X | O
Cross Over |  | 5.25 | Crossover |  | Steel | GT52331431 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | GT52331432 | 0 | 3 | [22 empty] | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500037 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500029 | 9 | 10 | [16 empty] | O | X | X | X | X | X | X | X | X | O
Motor | PDCI | 5.25 | 6/7 8.8 2.12 T/S HS88 +.005 |  | Steel | PPM250010 | 4 | 10 | [16 empty] | O | O | O | O | O | X | X | X | X | O
Motor | PDCI | 5.25 | 6/7 11.7 2.12 T/S HS88 -.003 |  | Steel | PPM250018 | 5 | 9 | [16 empty] | O | X | X | X | X | X | O | O | O
Motor | PDCI | 5 | 6/7 8.8 2.12 T/S HS88 +.016 |  | Steel | PPM250021 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Motor | PDCI |  | 6/7 8.8 2.12 T/S HS88 +.022 |  | Steel | PPM250017 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Motor | PDCI |  | 7/8 3.8 2.12 T/S HS88 -.004 |  | Steel | MTR500028 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Motor | PDCI |  | 6/7 8.8 2.12 T/S HS88 +.005 |  | Steel | PPM250024 | 0 | 3 | [22 empty] | O | O | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-592 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-589 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-588 | 8 | 10 | [16 empty] | O | X | X | X | X | X | X | X | X | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-458 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-618 | 8 | 10 | [16 empty] | O | X | X | X | X | X | X | X | X | O
Collar |  | 5.25 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT52-30-579 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5.25 | Pony Collar |  | Steel | GT52-10-654 | 8 | 10 | [16 empty] | O | X | X | X | X | X | X | X | X | O
Collar |  | 5.25 | Pony Collar |  | Steel | GT52-10-465 | 5 | 10 | [16 empty] | O | X | X | X | X | X | O | O | O | O
Collar |  |  | Pony Collar |  | Steel | GT50-10-479 | 0 | 3 | [22 empty] | O | O | O
Collar |  | 5.25 | Pony Collar |  | Steel | GT50-10-637 | 0 | 3 | [22 empty] | O | O | O
Collar |  |  | Pony Collar |  | Steel | GT50-10-652 | 0 | 3 | [22 empty] | O | O | O
Collar |  |  | Pony Collar |  | Steel | GT50-10-585 | 0 | 3 | [22 empty] | O | O | O
Sub |  |  | Float Sub |  | Steel | GT5003313FF | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | GT50331377FF | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | GT551232 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | GT551251 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Cap |  | Steel | GT126 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  | 5 | Filter Sub With Filter |  | Steel | GT50331343 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  | 5 | Filter Sub With Filter |  | Steel | GT5033740 | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Sub |  |  | Tomax |  | Steel | A52068 | 8 | 9 | [16 empty] | O | X | X | X | X | X | X | X | X
Sub |  | 4.875 | BTI |  | Steel | BTI 1 | 8 | 10 | [16 empty] | O | X | X | X | X | X | X | X | X | O
Sub |  | 4.875 | BTI |  | Steel | BTI 2 | 0 | 1 | [24 empty] | O
Agitator |  | 5 | Agitator |  | Steel | PG525-0050 | 5 | 9 | [16 empty] | O | X | X | X | X | X | O | O | O
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0055 | 4 | 9 | [16 empty] | O | O | O | O | O | X | X | X | X
Reamer |  |  | Reamer |  | Steel |  | 0 | 9 | [16 empty] | O | O | O | O | O | O | O | O | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 11 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Josh Ray |  |  |  | 6 |  | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1
Night DD |  |  | Jesse Taylor |  |  |  | 2 | [14 empty] | 1 | 1
Night DD |  |  | Marshall Adams |  |  |  | 4 |  | 1 | 1 | 1 | 1
Night DD |  |  | Robert E Wallace |  |  |  | 11 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 17 |  | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smetters |  |  |  | 17 |  | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 17 |  | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 17 |  | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Bighorn Plains H02
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0216MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
PPM250010 | 6/7 8.8 2.12 T/S HS88 +.005 | 5.25 | 33.29 |  | XT39 / 3 1/2REG | Dirty / Failed | PDCI / Pro Power | 10/20/2021 |  | 10/29/2021
PPM250018 | 6/7 11.7 2.12 T/S HS88 -.003 | 5.25 | 33.39 |  | XT39 / 3 1/2REG | Dirty | PDCI / Pro Power | 10/20/2021 |  | 10/28/2021
PPM250021 | 6/7 8.8 2.12 T/S HS88 +.016 | 5 | 33.02 |  | XT39 / 3 1/2REG | Clean | PDCI / Pro Power | 10/20/2021 |  | 10/28/2021
PPM250017 | 6/7 8.8 2.12 T/S HS88 +.022 |  |  |  | XT39 / 3 1/2REG | Clean | PDCI / Pro Power | 10/20/2021 |  | 10/28/2021
MTR500028 | 7/8 3.8 2.12 T/S HS88 -.004 |  |  |  | XT39 / 3 1/2REG | Clean | PDCI / Pro Power | 10/20/2021 |  | 10/28/2021
GT52-30-592 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 31.19 |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT52-30-589 | Non Mag Drill Collar (NO HARDBANDING) | 5 | 30.78 |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT52-30-588 | Non Mag Drill Collar (NO HARDBANDING) | 5 | 30.77 |  | XT39 / XT39 | Dirty |  | 10/20/2021 |  | 10/29/2021
GT52-30-458 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 30.61 |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT52-30-618 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 31.32 |  | XT39 / XT39 | Dirty |  | 10/20/2021 |  | 10/29/2021
GT52-30-579 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 30.17 |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT52-10-654 | Pony Collar | 5.25 | 5.59 |  | XT39 / XT39 | Dirty |  | 10/20/2021 |  | 10/29/2021
GT52-10-465 | Pony Collar | 5.25 | 5.59 |  | XT39 / XT39 | Dirty |  | 10/20/2021 |  | 10/29/2021
GT5003313FF | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT50331377FF | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT52331430 | Crossover | 5.25 | 3.33 |  | CET43 / XT39 | Dirty |  | 10/20/2021 |  | 10/29/2021
GT52331431 | Crossover | 5.25 | 3.38 |  | CET43 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT551232 | Lift Sub |  |  |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT551251 | Lift Sub |  |  |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT126 | Lift Cap |  |  |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT50331343 | Filter Sub With Filter | 5 | 5.55 |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
GT5033740 | Filter Sub With Filter | 5 | 4.92 |  | XT39 / XT39 | Clean |  | 10/20/2021 |  | 10/28/2021
A52068 | Tomax |  | 17.47 |  | XT39 / XT39 | Dirty |  | 10/20/2021 |  | 10/28/2021
PG525-0050 | Agitator | 5 | 22.01 |  | CET43 / CET43 | Dirty |  | 10/20/2021 |  | 10/28/2021
0 | Reamer |  |  |  | CET43 / CET43 | Clean |  | 10/20/2021 |  | 10/28/2021
500037 | UBHO | 5.25 | 4 |  |  | Clean |  | 10/20/2021 |  | 10/28/2021
500029 | UBHO | 5.25 | 2.99 |  |  | Dirty |  | 10/20/2021 |  | 10/29/2021
BTI 1 | BTI | 4.875 | 1.64 |  |  | Dirty |  | 10/20/2021
PG525-0055 | Agitator | 5.25 | 21.41 |  | CET43 / CET43 | Dirty | 0 | 10/20/2021 |  | 10/28/2021
GT50-10-479 | Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 10/26/2021 |  | 10/28/2021
GT50-10-637 | Pony Collar | 5.25 | 8.89 |  | XT39 / XT39 | Clean |  | 10/26/2021 |  | 10/28/2021
GT50-10-652 | Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 10/26/2021 |  | 10/28/2021
GT50-10-585 | Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 10/26/2021 |  | 10/28/2021
GT52331432 | Crossover |  |  |  | CET43 / XT39 | Clean |  | 10/26/2021 |  | 10/28/2021
PPM250024 | 6/7 8.8 2.12 T/S HS88 +.005 |  |  |  | XT39 / 3 1/2REG | Clean | PDCI / Pro Power | 10/26/2021 |  | 10/28/2021
BTI 2 | BTI | 4.875 | 1.65 |  |  | Clean |  | 10/28/2021 |  | 10/28/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Bighorn Plains H02
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 47424 | 10/04/2021 | 10/29/2021 | 26 |  | 1 |  | 2.58 | 7.18 | 11.75
7/8 5.9 1.50 NBS HPW -.014 NBS 13 | PPM800023 | 10/04/2021 | 10/29/2021 | 26 |  | 1 |  | 2.58 | 7.18 | 11.75
Nortrak Stabilizer | GT801171 | 10/04/2021 | 10/29/2021 | 26 |  | 1 |  | 2.58 | 7.18 | 11.75
Pony NMDC | GT8010518 | 10/04/2021 | 10/29/2021 | 26 | 3 | 1 ,2 |  | 9.2 | 42.33 | 68
UBHO Sub | 775213 | 10/04/2021 | 10/29/2021 | 26 | 3 | 1 ,2 |  | 9.2 | 42.33 | 68
NMDC | GT8030122 | 10/04/2021 | 10/29/2021 | 26 | 3 | 1 ,2 |  | 9.2 | 42.33 | 68
NMDC | GT8030218 | 10/04/2021 | 10/29/2021 | 26 | 3 | 1 ,2 |  | 9.2 | 42.33 | 68
Crossover Sub | GT7746830 | 10/04/2021 | 10/29/2021 | 26 |  | 1 |  | 2.58 | 7.18 | 11.75
SPL613 | 56410 | 10/04/2021 | 10/29/2021 | 26 | 2 | 2 |  | 6.62 | 35.15 | 56.25
7/8 5.9 2.0 TS HPW .001 | PPM800035 | 10/04/2021 | 10/29/2021 | 26 | 2 | 2 |  | 6.62 | 35.15 | 56.25
Crossover Sub | GT80461428 | 10/04/2021 | 10/29/2021 | 26 | 2 | 2 |  | 6.62 | 35.15 | 56.25
6 Jts 6 1/2 DC | RIG | 10/04/2021 | 10/29/2021 | 26 | 2 | 2 |  | 6.62 | 35.15 | 56.25
Crossover Sub | GT6744416 | 10/04/2021 | 10/29/2021 | 26 | 2 | 2 |  | 6.62 | 35.15 | 56.25
Agitator | PG675-0014 | 10/04/2021 | 10/29/2021 | 26 | 2 | 2 |  | 6.62 | 35.15 | 56.25
GTD64M | 13635755 | 10/04/2021 | 10/29/2021 | 26 | 4 | 3 |  | 18.63 | 53.47 | 100.75
6/7 11.7 2.12 T/S HS88 -.013 | PPM250018 | 10/20/2021 | 10/28/2021 | 9 | 4 | 3 |  | 18.63 | 53.47 | 100.75
BTI | BTI 1 | 10/20/2021 | 10/29/2021 | 10 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
Pony Collar | GT52-10-654 | 10/20/2021 | 10/29/2021 | 10 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
UHBO | 500029 | 10/20/2021 | 10/29/2021 | 10 | 4 | 3 |  | 18.63 | 53.47 | 100.75
Non Mag Drill Collar (NO HARDBANDING) | GT52-30-588 | 10/20/2021 | 10/29/2021 | 10 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
Pony Collar | GT52-10-465 | 10/20/2021 | 10/29/2021 | 10 | 4 | 3 |  | 18.63 | 53.47 | 100.75
Non Mag Drill Collar (NO HARDBANDING) | GT52-30-618 | 10/20/2021 | 10/29/2021 | 10 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
Tomax | A52068 | 10/20/2021 | 10/28/2021 | 9 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
Crossover | GT52331430 | 10/20/2021 | 10/29/2021 | 10 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
Drill-N-Ream | 579 | 10/04/2021 | 10/29/2021 | 26 | 6 | 3 ,4 |  | 46.17 | 70.77 | 153.08
Agitator | PG525-0050 | 10/20/2021 | 10/28/2021 | 9 | 4 | 3 |  | 18.63 | 53.47 | 100.75
GTD64M | 13618580 | 10/04/2021 | 10/29/2021 | 26 | 2 | 4 |  | 27.53 | 17.3 | 52.33
6/7 8.8 2.12 T/S HS88 +.005 | PPM250010 | 10/20/2021 | 10/29/2021 | 10 | 2 | 4 |  | 27.53 | 17.3 | 52.33
UBHO | 500029 | 10/20/2021 | 10/29/2021 | 10 | 2 | 4 |  | 27.53 | 17.3 | 52.33
Agitator | PG525-0055 | 10/20/2021 | 10/28/2021 | 9 | 2 | 4 |  | 27.53 | 17.3 | 52.33
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | well
Facility |  |  | Bighorn - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Bighorn Plains H02 |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Bighorn Plains H02
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 292.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Bighorn - Washington County, TX
Map Northing |  |  | 233699.79 US survey foot |  |  | Map Easting |  |  | 3155230.66 US survey foot
Latitude |  |  | 30° 15' 25.17043" N |  |  | Longitude |  |  | 96° 40' 25.60169" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.885
Well: |  |  | Bighorn Plains H02
Local North |  |  | 0.47 Usft |  |  | Local East |  |  | 6.31 Usft
Map Northing |  |  | 233699.80 US survey foot |  |  | Map Easting |  |  | 3155230.66 US survey foot
Latitude |  |  | 30° 15' 25.17307" N |  |  | Longitude |  |  | 96° 40' 25.52961" W
Depth Datum |  |  | well |  |  | Datum Elevation |  |  | 292.00 Usft
GL Elevation |  |  | 264.00 Usft
Grid Convergence |  |  | 1.885
Well bore: |  |  | Bighorn Plains H02
Magnetic Model |  |  | User defined |  |  | Date |  |  | 20/10/2021
Total Field (nT) |  |  | 46629.4 |  |  | Dip Angle (°) |  |  | 58.85
Declination (°) |  |  | 2.917
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 153.98
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Bighorn Plains H02
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2915 |  |  | BH Plains H02 S1 |  |  | MWD+HDGM
2915 |  |  | 9859 |  |  | BH Plains H02 S2 |  |  | MWD+HDGM
9859 |  |  | 16991 |  |  | BH Plains H02 S3 |  |  | MWD+HDGM
16991 |  |  | 18929 |  |  | BH Plains H02 S4 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -292 | 233699.8 | 3155230.66 | 30.257 | -96.6738 | 0
200 | 0.54 | 334.68 | 200 | 0.85 | -0.4 | -0.94 | 0.27 | 0.27 | 12.66 | 334.68 | 200 | -92 | 233700.65 | 3155230.26 | 30.257 | -96.6738 | 334.68
293 | 0.85 | 329.26 | 292.99 | 1.84 | -0.94 | -2.07 | 0.34 | 0.33 | -5.83 | -14.69 | 93 | 0.99 | 233701.64 | 3155229.72 | 30.257 | -96.6738 | 332.87
384 | 0.94 | 332.3 | 383.98 | 3.08 | -1.64 | -3.49 | 0.11 | 0.1 | 3.34 | 29.34 | 91 | 91.98 | 233702.88 | 3155229.02 | 30.257 | -96.6738 | 332.05
478 | 0.94 | 322.09 | 477.97 | 4.37 | -2.47 | -5.01 | 0.18 | 0 | -10.86 | -95.1 | 94 | 185.97 | 233704.17 | 3155228.19 | 30.257 | -96.6738 | 330.57
572 | 0.9 | 332.51 | 571.95 | 5.64 | -3.28 | -6.5 | 0.18 | -0.04 | 11.09 | 108.62 | 94 | 279.95 | 233705.44 | 3155227.38 | 30.257 | -96.6738 | 329.79
665 | 1.16 | 332.39 | 664.94 | 7.12 | -4.06 | -8.18 | 0.28 | 0.28 | -0.13 | -0.54 | 93 | 372.94 | 233706.92 | 3155226.6 | 30.257 | -96.6738 | 330.33
759 | 1.22 | 323.7 | 758.92 | 8.77 | -5.09 | -10.11 | 0.2 | 0.06 | -9.24 | -75.99 | 94 | 466.92 | 233708.57 | 3155225.57 | 30.257 | -96.6738 | 329.87
852 | 1.22 | 331.07 | 851.9 | 10.43 | -6.15 | -12.07 | 0.17 | 0 | 7.92 | 93.68 | 93 | 559.9 | 233710.23 | 3155224.51 | 30.257 | -96.6738 | 329.47
946 | 1.29 | 298.46 | 945.88 | 11.81 | -7.57 | -13.94 | 0.75 | 0.07 | -34.69 | -100.85 | 94 | 653.88 | 233711.61 | 3155223.09 | 30.257 | -96.6738 | 327.35
1040 | 1.88 | 277.23 | 1039.84 | 12.51 | -10.03 | -15.64 | 0.88 | 0.63 | -22.59 | -55.81 | 94 | 747.84 | 233712.31 | 3155220.63 | 30.257 | -96.6738 | 321.29
1133 | 3.03 | 273.04 | 1132.75 | 12.83 | -14 | -17.67 | 1.25 | 1.24 | -4.51 | -10.97 | 93 | 840.75 | 233712.63 | 3155216.66 | 30.257 | -96.6738 | 312.52
1228 | 3.7 | 265.72 | 1227.59 | 12.74 | -19.56 | -20.03 | 0.84 | 0.71 | -7.71 | -36.36 | 95 | 935.59 | 233712.54 | 3155211.1 | 30.257 | -96.6738 | 303.07
1322 | 3.88 | 262.8 | 1321.38 | 12.11 | -25.74 | -22.18 | 0.28 | 0.19 | -3.11 | -48.46 | 94 | 1029.38 | 233711.91 | 3155204.92 | 30.257 | -96.6739 | 295.2
1415 | 3.75 | 260.36 | 1414.18 | 11.21 | -31.86 | -24.05 | 0.22 | -0.14 | -2.62 | -129.9 | 93 | 1122.18 | 233711.01 | 3155198.8 | 30.257 | -96.6739 | 289.38
1509 | 3.69 | 259.33 | 1507.98 | 10.13 | -37.86 | -25.72 | 0.1 | -0.06 | -1.1 | -132.43 | 94 | 1215.98 | 233709.93 | 3155192.8 | 30.257 | -96.6739 | 284.98
1602 | 3.84 | 258.28 | 1600.78 | 8.95 | -43.85 | -27.28 | 0.18 | 0.16 | -1.13 | -25.21 | 93 | 1308.78 | 233708.75 | 3155186.81 | 30.257 | -96.6739 | 281.53
1696 | 4.76 | 254.48 | 1694.51 | 7.26 | -50.69 | -28.77 | 1.02 | 0.98 | -4.04 | -19.11 | 94 | 1402.51 | 233707.06 | 3155179.97 | 30.257 | -96.6739 | 278.16
1790 | 5.94 | 255.04 | 1788.1 | 4.97 | -59.15 | -30.41 | 1.26 | 1.26 | 0.6 | 2.81 | 94 | 1496.1 | 233704.77 | 3155171.51 | 30.257 | -96.674 | 274.8
1883 | 7.23 | 257.83 | 1880.49 | 2.49 | -69.52 | -32.73 | 1.43 | 1.39 | 3 | 15.32 | 93 | 1588.49 | 233702.29 | 3155161.14 | 30.257 | -96.674 | 272.05
1977 | 8.45 | 259.7 | 1973.61 | 0.01 | -82.1 | -36.02 | 1.33 | 1.3 | 1.99 | 12.74 | 94 | 1681.61 | 233699.81 | 3155148.56 | 30.257 | -96.674 | 270.01
2070 | 8.97 | 262.33 | 2065.54 | -2.18 | -96.01 | -40.16 | 0.7 | 0.56 | 2.83 | 38.75 | 93 | 1773.54 | 233697.62 | 3155134.65 | 30.257 | -96.6741 | 268.7
2164 | 10.26 | 265.97 | 2158.21 | -3.75 | -111.62 | -45.6 | 1.52 | 1.37 | 3.87 | 27.04 | 94 | 1866.21 | 233696.05 | 3155119.04 | 30.257 | -96.6741 | 268.08
2258 | 11.5 | 268.61 | 2250.52 | -4.56 | -129.34 | -52.64 | 1.42 | 1.32 | 2.81 | 23.19 | 94 | 1958.52 | 233695.24 | 3155101.32 | 30.257 | -96.6742 | 267.98
2352 | 12.32 | 268.45 | 2342.5 | -5.06 | -148.73 | -60.7 | 0.87 | 0.87 | -0.17 | -2.38 | 94 | 2050.5 | 233694.74 | 3155081.93 | 30.257 | -96.6743 | 268.05
2446 | 14.38 | 265.37 | 2433.95 | -6.28 | -170.39 | -69.11 | 2.32 | 2.19 | -3.28 | -20.55 | 94 | 2141.95 | 233693.52 | 3155060.27 | 30.257 | -96.6743 | 267.89
2540 | 15.6 | 264.38 | 2524.75 | -8.46 | -194.61 | -77.77 | 1.33 | 1.3 | -1.05 | -12.33 | 94 | 2232.75 | 233691.34 | 3155036.05 | 30.257 | -96.6744 | 267.51
2634 | 16.66 | 265.47 | 2615.05 | -10.76 | -220.62 | -87.11 | 1.17 | 1.13 | 1.16 | 16.47 | 94 | 2323.05 | 233689.04 | 3155010.04 | 30.257 | -96.6745 | 267.21
2728 | 17.17 | 268.08 | 2704.99 | -12.29 | -247.92 | -97.72 | 0.97 | 0.54 | 2.78 | 57.37 | 94 | 2412.99 | 233687.51 | 3154982.74 | 30.257 | -96.6746 | 267.16
2822 | 16.77 | 269.2 | 2794.89 | -12.94 | -275.35 | -109.16 | 0.55 | -0.43 | 1.19 | 141.28 | 94 | 2502.89 | 233686.86 | 3154955.31 | 30.257 | -96.6747 | 267.31
2915 | 17.27 | 269.74 | 2883.82 | -13.19 | -302.57 | -120.88 | 0.56 | 0.54 | 0.58 | 17.8 | 93 | 2591.82 | 233686.61 | 3154928.09 | 30.257 | -96.6747 | 267.5
3038 | 17.1 | 270.83 | 3001.33 | -13.01 | -338.91 | -136.98 | 0.3 | -0.14 | 0.89 | 118.35 | 123 | 2709.33 | 233686.79 | 3154891.75 | 30.257 | -96.6749 | 267.8
3131 | 17.42 | 268.2 | 3090.14 | -13.25 | -366.49 | -148.87 | 0.91 | 0.34 | -2.83 | -68.96 | 93 | 2798.14 | 233686.55 | 3154864.17 | 30.257 | -96.6749 | 267.93
3225 | 19.16 | 266.17 | 3179.39 | -14.72 | -395.95 | -160.46 | 1.97 | 1.85 | -2.16 | -21.08 | 94 | 2887.39 | 233685.08 | 3154834.71 | 30.257 | -96.675 | 267.87
3320 | 19.61 | 265.91 | 3269.01 | -16.9 | -427.41 | -172.31 | 0.48 | 0.47 | -0.27 | -10.98 | 95 | 2977.01 | 233682.9 | 3154803.25 | 30.257 | -96.6751 | 267.74
3413 | 19.7 | 264.13 | 3356.59 | -19.62 | -458.57 | -183.54 | 0.65 | 0.1 | -1.91 | -82.29 | 93 | 3064.59 | 233680.18 | 3154772.09 | 30.257 | -96.6752 | 267.55
3507 | 18.98 | 266.39 | 3445.28 | -22.2 | -489.58 | -194.82 | 1.1 | -0.77 | 2.4 | 134.95 | 94 | 3153.28 | 233677.6 | 3154741.08 | 30.257 | -96.6753 | 267.4
3600 | 18.98 | 264.93 | 3533.23 | -24.49 | -519.74 | -205.99 | 0.51 | 0 | -1.57 | -90.69 | 93 | 3241.23 | 233675.31 | 3154710.92 | 30.257 | -96.6754 | 267.3
3694 | 18.46 | 268.22 | 3622.26 | -26.3 | -549.84 | -217.57 | 1.25 | -0.55 | 3.5 | 117.77 | 94 | 3330.26 | 233673.5 | 3154680.82 | 30.257 | -96.6755 | 267.26
3787 | 18.66 | 268.57 | 3710.42 | -27.13 | -579.43 | -229.81 | 0.25 | 0.22 | 0.38 | 29.28 | 93 | 3418.42 | 233672.67 | 3154651.23 | 30.257 | -96.6756 | 267.32
3881 | 18.55 | 268.47 | 3799.51 | -27.91 | -609.41 | -242.26 | 0.12 | -0.12 | -0.11 | -163.87 | 94 | 3507.51 | 233671.89 | 3154621.25 | 30.257 | -96.6757 | 267.38
3974 | 18.19 | 267.72 | 3887.77 | -28.88 | -638.71 | -254.24 | 0.46 | -0.39 | -0.81 | -147.07 | 93 | 3595.77 | 233670.92 | 3154591.95 | 30.257 | -96.6758 | 267.41
4068 | 17.92 | 272.29 | 3977.15 | -28.89 | -667.82 | -267 | 1.53 | -0.29 | 4.86 | 102.96 | 94 | 3685.15 | 233670.91 | 3154562.84 | 30.257 | -96.6759 | 267.52
4161 | 17.99 | 272.59 | 4065.62 | -27.66 | -696.46 | -280.67 | 0.12 | 0.08 | 0.32 | 53.02 | 93 | 3773.62 | 233672.14 | 3154534.2 | 30.257 | -96.676 | 267.73
4255 | 18.01 | 273.03 | 4155.02 | -26.24 | -725.47 | -294.67 | 0.15 | 0.02 | 0.47 | 81.84 | 94 | 3863.02 | 233673.56 | 3154505.19 | 30.257 | -96.6761 | 267.93
4348 | 17.76 | 273.64 | 4243.52 | -24.58 | -753.98 | -308.67 | 0.34 | -0.27 | 0.66 | 143.44 | 93 | 3951.52 | 233675.22 | 3154476.68 | 30.257 | -96.6762 | 268.13
4442 | 17.79 | 273.27 | 4333.03 | -22.85 | -782.63 | -322.79 | 0.12 | 0.03 | -0.39 | -75.3 | 94 | 4041.03 | 233676.95 | 3154448.03 | 30.257 | -96.6763 | 268.33
4535 | 17.92 | 272.58 | 4421.56 | -21.4 | -811.11 | -336.59 | 0.27 | 0.14 | -0.74 | -58.76 | 93 | 4129.56 | 233678.4 | 3154419.55 | 30.257 | -96.6763 | 268.49
4629 | 18.55 | 269.28 | 4510.84 | -20.93 | -840.5 | -349.9 | 1.29 | 0.67 | -3.51 | -60.19 | 94 | 4218.84 | 233678.87 | 3154390.16 | 30.257 | -96.6764 | 268.57
4724 | 17.98 | 269.64 | 4601.05 | -21.22 | -870.28 | -362.71 | 0.61 | -0.6 | 0.38 | 168.97 | 95 | 4309.05 | 233678.58 | 3154360.38 | 30.257 | -96.6765 | 268.6
4818 | 17.62 | 269.7 | 4690.55 | -21.38 | -899.01 | -375.17 | 0.38 | -0.38 | 0.06 | 177.11 | 94 | 4398.55 | 233678.42 | 3154331.65 | 30.257 | -96.6766 | 268.64
4912 | 17.87 | 269.41 | 4780.08 | -21.6 | -927.66 | -387.54 | 0.28 | 0.27 | -0.31 | -19.61 | 94 | 4488.08 | 233678.2 | 3154303 | 30.257 | -96.6767 | 268.67
5005 | 16.55 | 269.18 | 4868.91 | -21.94 | -955.17 | -399.3 | 1.42 | -1.42 | -0.25 | -177.16 | 93 | 4576.91 | 233677.86 | 3154275.49 | 30.257 | -96.6768 | 268.68
5098 | 17.89 | 272.73 | 4957.74 | -21.45 | -982.69 | -411.81 | 1.83 | 1.44 | 3.82 | 39.81 | 93 | 4665.74 | 233678.35 | 3154247.97 | 30.257 | -96.6769 | 268.75
5192 | 18.72 | 273.71 | 5046.99 | -19.79 | -1012.16 | -426.24 | 0.94 | 0.88 | 1.04 | 20.81 | 94 | 4754.99 | 233680.01 | 3154218.5 | 30.257 | -96.677 | 268.88
5286 | 18.96 | 273.17 | 5135.95 | -17.97 | -1042.46 | -441.17 | 0.32 | 0.26 | -0.57 | -36.26 | 94 | 4843.95 | 233681.83 | 3154188.2 | 30.257 | -96.6771 | 269.01
5380 | 17.81 | 272.01 | 5225.15 | -16.62 | -1072.08 | -455.37 | 1.28 | -1.22 | -1.23 | -162.9 | 94 | 4933.15 | 233683.18 | 3154158.58 | 30.257 | -96.6772 | 269.11
5473 | 16.69 | 272.4 | 5313.97 | -15.56 | -1099.64 | -468.41 | 1.21 | -1.2 | 0.42 | 174.29 | 93 | 5021.97 | 233684.24 | 3154131.02 | 30.257 | -96.6773 | 269.19
5567 | 18.1 | 270.27 | 5403.67 | -14.92 | -1127.73 | -481.3 | 1.65 | 1.5 | -2.27 | -25.32 | 94 | 5111.67 | 233684.88 | 3154102.93 | 30.2571 | -96.6774 | 269.24
5660 | 17.36 | 269.21 | 5492.25 | -15.05 | -1156.05 | -493.62 | 0.87 | -0.8 | -1.14 | -156.94 | 93 | 5200.25 | 233684.75 | 3154074.61 | 30.2571 | -96.6774 | 269.25
5754 | 18.55 | 271.09 | 5581.67 | -14.96 | -1185.02 | -506.41 | 1.41 | 1.27 | 2 | 26.86 | 94 | 5289.67 | 233684.84 | 3154045.64 | 30.2571 | -96.6775 | 269.28
5848 | 19.21 | 270.97 | 5670.61 | -14.41 | -1215.43 | -520.24 | 0.7 | 0.7 | -0.13 | -3.42 | 94 | 5378.61 | 233685.39 | 3154015.23 | 30.2571 | -96.6776 | 269.32
5941 | 18.44 | 270.41 | 5758.64 | -14.05 | -1245.44 | -533.73 | 0.85 | -0.83 | -0.6 | -167.06 | 93 | 5466.64 | 233685.75 | 3153985.22 | 30.2571 | -96.6777 | 269.35
6035 | 18.09 | 271.22 | 5847.9 | -13.63 | -1274.89 | -547.03 | 0.46 | -0.37 | 0.86 | 144.43 | 94 | 5555.9 | 233686.17 | 3153955.77 | 30.2571 | -96.6778 | 269.39
6128 | 17.22 | 271.02 | 5936.52 | -13.08 | -1303.09 | -559.9 | 0.94 | -0.94 | -0.22 | -176.11 | 93 | 5644.52 | 233686.72 | 3153927.57 | 30.2571 | -96.6779 | 269.43
6222 | 18.91 | 272.13 | 6025.88 | -12.26 | -1332.23 | -573.41 | 1.83 | 1.8 | 1.18 | 12.04 | 94 | 5733.88 | 233687.54 | 3153898.43 | 30.2571 | -96.678 | 269.47
6316 | 19.4 | 274.04 | 6114.68 | -10.6 | -1363.02 | -588.42 | 0.85 | 0.52 | 2.03 | 52.88 | 94 | 5822.68 | 233689.2 | 3153867.64 | 30.2571 | -96.6781 | 269.55
6410 | 19.05 | 273.76 | 6203.44 | -8.49 | -1393.9 | -603.85 | 0.39 | -0.37 | -0.3 | -165.37 | 94 | 5911.44 | 233691.31 | 3153836.76 | 30.2571 | -96.6782 | 269.65
6503 | 18.51 | 273.87 | 6291.49 | -6.5 | -1423.78 | -618.75 | 0.58 | -0.58 | 0.12 | 176.3 | 93 | 5999.49 | 233693.3 | 3153806.88 | 30.2571 | -96.6783 | 269.74
6597 | 17.43 | 273.91 | 6380.9 | -4.53 | -1452.71 | -633.21 | 1.15 | -1.15 | 0.04 | 179.36 | 94 | 6088.9 | 233695.27 | 3153777.95 | 30.2571 | -96.6784 | 269.82
6690 | 17.66 | 272.79 | 6469.57 | -2.9 | -1480.7 | -646.96 | 0.44 | 0.25 | -1.2 | -56.27 | 93 | 6177.57 | 233696.9 | 3153749.96 | 30.2571 | -96.6785 | 269.89
6783 | 17.65 | 273.46 | 6558.19 | -1.36 | -1508.86 | -660.69 | 0.22 | -0.01 | 0.72 | 93.14 | 93 | 6266.19 | 233698.44 | 3153721.8 | 30.2571 | -96.6786 | 269.95
6878 | 16.3 | 273.53 | 6649.05 | 0.33 | -1536.54 | -674.36 | 1.42 | -1.42 | 0.07 | 179.17 | 95 | 6357.05 | 233700.13 | 3153694.12 | 30.2571 | -96.6786 | 270.01
6971 | 15.94 | 271.26 | 6738.4 | 1.42 | -1562.34 | -686.65 | 0.78 | -0.39 | -2.44 | -120.82 | 93 | 6446.4 | 233701.22 | 3153668.32 | 30.2571 | -96.6787 | 270.05
7065 | 15.17 | 271.34 | 6828.95 | 1.99 | -1587.54 | -698.22 | 0.82 | -0.82 | 0.09 | 178.44 | 94 | 6536.95 | 233701.79 | 3153643.12 | 30.2571 | -96.6788 | 270.07
7159 | 14.23 | 266.29 | 6919.88 | 1.53 | -1611.36 | -708.25 | 1.69 | -1 | -5.37 | -128.69 | 94 | 6627.88 | 233701.33 | 3153619.3 | 30.2571 | -96.6789 | 270.05
7253 | 12.95 | 266.63 | 7011.24 | 0.16 | -1633.41 | -716.7 | 1.36 | -1.36 | 0.36 | 176.59 | 94 | 6719.24 | 233699.96 | 3153597.25 | 30.2571 | -96.6789 | 270.01
7347 | 12.44 | 270.19 | 7102.95 | -0.42 | -1654.05 | -725.22 | 0.99 | -0.54 | 3.79 | 124.83 | 94 | 6810.95 | 233699.38 | 3153576.61 | 30.2571 | -96.679 | 269.99
7440 | 11.62 | 276.56 | 7193.91 | 0.68 | -1673.37 | -734.69 | 1.68 | -0.88 | 6.85 | 124.79 | 93 | 6901.91 | 233700.48 | 3153557.29 | 30.2571 | -96.6791 | 270.02
7533 | 11.82 | 277.5 | 7284.97 | 2.99 | -1692.12 | -745 | 0.3 | 0.22 | 1.01 | 44.13 | 93 | 6992.97 | 233702.79 | 3153538.54 | 30.2572 | -96.6791 | 270.1
7627 | 13.01 | 279 | 7376.77 | 5.9 | -1712.12 | -756.38 | 1.31 | 1.27 | 1.6 | 15.9 | 94 | 7084.77 | 233705.7 | 3153518.54 | 30.2572 | -96.6792 | 270.2
7720 | 12.45 | 278.94 | 7467.48 | 9.1 | -1732.36 | -768.14 | 0.6 | -0.6 | -0.06 | -178.68 | 93 | 7175.48 | 233708.9 | 3153498.3 | 30.2572 | -96.6793 | 270.3
7811 | 11.06 | 282.31 | 7556.57 | 12.48 | -1750.58 | -779.17 | 1.7 | -1.53 | 3.7 | 155.36 | 91 | 7264.57 | 233712.28 | 3153480.08 | 30.2572 | -96.6793 | 270.41
7904 | 10.93 | 279.07 | 7647.87 | 15.78 | -1768 | -789.77 | 0.68 | -0.14 | -3.48 | -103.47 | 93 | 7355.87 | 233715.58 | 3153462.66 | 30.2572 | -96.6794 | 270.51
7998 | 10.67 | 278.23 | 7740.2 | 18.43 | -1785.41 | -799.79 | 0.32 | -0.28 | -0.89 | -149.22 | 94 | 7448.2 | 233718.23 | 3153445.25 | 30.2572 | -96.6794 | 270.59
8092 | 11.12 | 273.51 | 7832.51 | 20.23 | -1803.07 | -809.16 | 1.06 | 0.48 | -5.02 | -65.56 | 94 | 7540.51 | 233720.03 | 3153427.59 | 30.2572 | -96.6795 | 270.64
8186 | 11.19 | 272.9 | 7924.73 | 21.24 | -1821.23 | -818.04 | 0.15 | 0.07 | -0.65 | -59.62 | 94 | 7632.73 | 233721.04 | 3153409.43 | 30.2572 | -96.6795 | 270.67
8279 | 10.76 | 276.46 | 8016.03 | 22.68 | -1838.87 | -827.06 | 0.86 | -0.46 | 3.83 | 124.13 | 93 | 7724.03 | 233722.48 | 3153391.79 | 30.2572 | -96.6796 | 270.71
8372 | 10.58 | 272.33 | 8107.43 | 24 | -1856.03 | -835.78 | 0.84 | -0.19 | -4.44 | -105.27 | 93 | 7815.43 | 233723.8 | 3153374.63 | 30.2572 | -96.6797 | 270.74
8467 | 10.01 | 260.87 | 8200.91 | 23.05 | -1872.89 | -842.32 | 2.23 | -0.6 | -12.06 | -111.14 | 95 | 7908.91 | 233722.85 | 3153357.77 | 30.2572 | -96.6797 | 270.7
8561 | 7.96 | 253.13 | 8293.75 | 19.86 | -1887.19 | -845.73 | 2.53 | -2.18 | -8.23 | -153.26 | 94 | 8001.75 | 233719.66 | 3153343.47 | 30.2572 | -96.6797 | 270.6
8654 | 5.25 | 249.63 | 8386.13 | 16.51 | -1897.34 | -847.17 | 2.94 | -2.91 | -3.76 | -173.29 | 93 | 8094.13 | 233716.31 | 3153333.32 | 30.2572 | -96.6798 | 270.5
8748 | 4.17 | 253.43 | 8479.81 | 14.04 | -1904.65 | -848.16 | 1.2 | -1.15 | 4.04 | 165.77 | 94 | 8187.81 | 233713.84 | 3153326.01 | 30.2572 | -96.6798 | 270.42
8841 | 3.7 | 254.2 | 8572.59 | 12.26 | -1910.78 | -849.24 | 0.51 | -0.51 | 0.83 | 173.97 | 93 | 8280.59 | 233712.06 | 3153319.88 | 30.2572 | -96.6798 | 270.37
8936 | 2.44 | 253.87 | 8667.45 | 10.86 | -1915.67 | -850.14 | 1.33 | -1.33 | -0.35 | -179.36 | 95 | 8375.45 | 233710.66 | 3153314.99 | 30.2572 | -96.6798 | 270.32
9029 | 2.11 | 243.5 | 8760.38 | 9.55 | -1919.11 | -850.46 | 0.57 | -0.35 | -11.15 | -133.82 | 93 | 8468.38 | 233709.35 | 3153311.55 | 30.2572 | -96.6799 | 270.29
9123 | 2.24 | 251.17 | 8854.31 | 8.18 | -1922.39 | -850.68 | 0.34 | 0.14 | 8.16 | 69.8 | 94 | 8562.31 | 233707.98 | 3153308.27 | 30.2572 | -96.6799 | 270.24
9217 | 1.69 | 247.14 | 8948.25 | 7.05 | -1925.41 | -850.98 | 0.6 | -0.59 | -4.29 | -167.9 | 94 | 8656.25 | 233706.85 | 3153305.25 | 30.2572 | -96.6799 | 270.21
9311 | 1.83 | 244.67 | 9042.21 | 5.87 | -1928.04 | -851.08 | 0.17 | 0.15 | -2.63 | -29.69 | 94 | 8750.21 | 233705.67 | 3153302.62 | 30.2572 | -96.6799 | 270.17
9404 | 1.96 | 266.72 | 9135.16 | 5.14 | -1930.97 | -851.71 | 0.79 | 0.14 | 23.71 | 91.03 | 93 | 8843.16 | 233704.94 | 3153299.69 | 30.2572 | -96.6799 | 270.15
9498 | 4.84 | 200.49 | 9229.01 | 1.33 | -1933.97 | -849.6 | 4.71 | 3.06 | -70.46 | -90.07 | 94 | 8937.01 | 233701.13 | 3153296.69 | 30.2572 | -96.6799 | 270.04
9591 | 10.11 | 187.12 | 9321.2 | -10.45 | -1936.35 | -840.06 | 5.93 | 5.67 | -14.38 | -24.98 | 93 | 9029.2 | 233689.35 | 3153294.31 | 30.2571 | -96.6799 | 269.69
9686 | 14.15 | 181.49 | 9414.06 | -30.34 | -1937.69 | -822.77 | 4.43 | 4.25 | -5.93 | -19.09 | 95 | 9122.06 | 233669.46 | 3153292.97 | 30.2571 | -96.6799 | 269.1
9779 | 17.86 | 175.99 | 9503.44 | -55.94 | -1936.99 | -799.46 | 4.31 | 3.99 | -5.91 | -24.9 | 93 | 9211.44 | 233643.86 | 3153293.67 | 30.257 | -96.6799 | 268.35
9859 | 21.15 | 166.02 | 9578.86 | -82.2 | -1932.64 | -773.95 | 5.84 | 4.11 | -12.46 | -50.12 | 80 | 9286.86 | 233617.6 | 3153298.02 | 30.2569 | -96.6799 | 267.56
10019 | 26.21 | 154.14 | 9725.43 | -142.08 | -1910.23 | -710.31 | 4.33 | 3.16 | -7.42 | -48.88 | 160 | 9433.43 | 233557.72 | 3153320.43 | 30.2568 | -96.6798 | 265.75
10114 | 36.44 | 144.67 | 9806.52 | -184.11 | -1884.68 | -661.33 | 11.92 | 10.77 | -9.97 | -29.84 | 95 | 9514.52 | 233515.69 | 3153345.98 | 30.2567 | -96.6798 | 264.42
10209 | 48.38 | 147.42 | 9876.54 | -237.25 | -1849.11 | -597.98 | 12.72 | 12.57 | 2.89 | 9.87 | 95 | 9584.54 | 233462.55 | 3153381.55 | 30.2565 | -96.6797 | 262.69
10304 | 55.66 | 154.12 | 9935.01 | -302.59 | -1812.8 | -523.33 | 9.46 | 7.66 | 7.05 | 38.07 | 95 | 9643.01 | 233397.21 | 3153417.86 | 30.2563 | -96.6795 | 260.52
10398 | 60.92 | 153.06 | 9984.4 | -374.17 | -1777.22 | -443.39 | 5.68 | 5.6 | -1.13 | -10.01 | 94 | 9692.4 | 233325.63 | 3153453.44 | 30.2561 | -96.6794 | 258.11
10492 | 69.77 | 152.97 | 10023.57 | -450.23 | -1738.49 | -358.06 | 9.42 | 9.41 | -0.1 | -0.55 | 94 | 9731.57 | 233249.57 | 3153492.17 | 30.2559 | -96.6793 | 255.48
10586 | 78.57 | 155.69 | 10049.19 | -531.67 | -1699.4 | -267.72 | 9.77 | 9.36 | 2.89 | 16.95 | 94 | 9757.19 | 233168.13 | 3153531.26 | 30.2557 | -96.6792 | 252.63
10680 | 85.36 | 154.17 | 10062.32 | -615.92 | -1659.98 | -174.72 | 7.4 | 7.22 | -1.62 | -12.61 | 94 | 9770.32 | 233083.88 | 3153570.68 | 30.2554 | -96.6791 | 249.64
10775 | 87.65 | 151.62 | 10068.12 | -700.32 | -1616.78 | -79.92 | 3.6 | 2.41 | -2.68 | -48.11 | 95 | 9776.12 | 232999.48 | 3153613.88 | 30.2552 | -96.679 | 246.58
10868 | 85.7 | 151.95 | 10073.51 | -782.12 | -1572.89 | 12.85 | 2.13 | -2.1 | 0.35 | 170.42 | 93 | 9781.51 | 232917.68 | 3153657.77 | 30.255 | -96.6788 | 243.56
10963 | 84.17 | 152.81 | 10081.9 | -865.96 | -1529.02 | 107.43 | 1.85 | -1.61 | 0.91 | 150.79 | 95 | 9789.9 | 232833.84 | 3153701.64 | 30.2548 | -96.6787 | 240.47
11056 | 86.06 | 152.13 | 10089.82 | -948.13 | -1486.19 | 200.06 | 2.16 | 2.03 | -0.73 | -19.75 | 93 | 9797.82 | 232751.67 | 3153744.47 | 30.2545 | -96.6786 | 237.46
11150 | 86.94 | 151.86 | 10095.55 | -1030.97 | -1442.13 | 293.83 | 0.98 | 0.94 | -0.29 | -17.04 | 94 | 9803.55 | 232668.83 | 3153788.53 | 30.2543 | -96.6785 | 234.44
11245 | 87.87 | 152.91 | 10099.86 | -1115.06 | -1398.15 | 388.69 | 1.48 | 0.98 | 1.11 | 48.46 | 95 | 9807.86 | 232584.74 | 3153832.51 | 30.2541 | -96.6783 | 231.43
11339 | 86.23 | 156.09 | 10104.69 | -1199.77 | -1357.74 | 482.55 | 3.8 | -1.74 | 3.38 | 117.39 | 94 | 9812.69 | 232500.03 | 3153872.92 | 30.2538 | -96.6782 | 228.53
11434 | 85.81 | 156.17 | 10111.29 | -1286.44 | -1319.39 | 577.25 | 0.45 | -0.44 | 0.08 | 169.24 | 95 | 9819.29 | 232413.36 | 3153911.27 | 30.2536 | -96.6781 | 225.72
11528 | 87.79 | 157.03 | 10116.53 | -1372.57 | -1282.11 | 671 | 2.3 | 2.11 | 0.91 | 23.47 | 94 | 9824.53 | 232327.23 | 3153948.55 | 30.2533 | -96.678 | 223.05
11623 | 86.78 | 154.69 | 10121.04 | -1459.15 | -1243.31 | 765.83 | 2.68 | -1.06 | -2.46 | -113.42 | 95 | 9829.04 | 232240.65 | 3153987.35 | 30.2531 | -96.6779 | 220.43
11718 | 86.5 | 153.27 | 10126.6 | -1544.38 | -1201.71 | 860.67 | 1.52 | -0.29 | -1.49 | -101.21 | 95 | 9834.6 | 232155.42 | 3154028.95 | 30.2529 | -96.6777 | 217.89
11812 | 86.82 | 152.78 | 10132.08 | -1628.01 | -1159.14 | 954.5 | 0.62 | 0.34 | -0.52 | -56.82 | 94 | 9840.08 | 232071.79 | 3154071.52 | 30.2526 | -96.6776 | 215.45
11906 | 86.87 | 150.95 | 10137.25 | -1710.77 | -1114.89 | 1048.29 | 1.94 | 0.05 | -1.95 | -88.48 | 94 | 9845.25 | 231989.03 | 3154115.77 | 30.2524 | -96.6775 | 213.09
12000 | 86.13 | 150.07 | 10142.99 | -1792.44 | -1068.7 | 1141.94 | 1.22 | -0.79 | -0.94 | -130.14 | 94 | 9850.99 | 231907.36 | 3154161.96 | 30.2522 | -96.6773 | 210.8
12094 | 85.78 | 151.76 | 10149.62 | -1874.38 | -1023.12 | 1235.56 | 1.83 | -0.37 | 1.8 | 101.79 | 94 | 9857.62 | 231825.42 | 3154207.54 | 30.2519 | -96.6772 | 208.63
12188 | 86.77 | 152.64 | 10155.73 | -1957.35 | -979.37 | 1329.32 | 1.41 | 1.05 | 0.94 | 41.6 | 94 | 9863.73 | 231742.45 | 3154251.29 | 30.2517 | -96.6771 | 206.58
12283 | 85.98 | 153.61 | 10161.74 | -2041.92 | -936.52 | 1424.12 | 1.32 | -0.83 | 1.02 | 129.25 | 95 | 9869.74 | 231657.88 | 3154294.14 | 30.2515 | -96.677 | 204.64
12375 | 86.66 | 153.42 | 10167.64 | -2124.09 | -895.57 | 1515.92 | 0.77 | 0.74 | -0.21 | -15.59 | 92 | 9875.64 | 231575.71 | 3154335.09 | 30.2512 | -96.6768 | 202.86
12468 | 85.39 | 154.48 | 10174.09 | -2207.44 | -854.83 | 1608.7 | 1.78 | -1.37 | 1.14 | 140.25 | 93 | 9882.09 | 231492.36 | 3154375.83 | 30.251 | -96.6767 | 201.17
12563 | 85.54 | 154.91 | 10181.6 | -2293.06 | -814.35 | 1703.39 | 0.48 | 0.16 | 0.45 | 70.73 | 95 | 9889.6 | 231406.74 | 3154416.31 | 30.2508 | -96.6766 | 199.55
12655 | 86.78 | 155.01 | 10187.76 | -2376.22 | -775.5 | 1795.17 | 1.35 | 1.35 | 0.11 | 4.6 | 92 | 9895.76 | 231323.58 | 3154455.16 | 30.2505 | -96.6765 | 198.07
12749 | 86.23 | 154.45 | 10193.49 | -2461.07 | -735.45 | 1888.99 | 0.83 | -0.59 | -0.6 | -134.55 | 94 | 9901.49 | 231238.73 | 3154495.21 | 30.2503 | -96.6764 | 196.64
12843 | 85.28 | 153.98 | 10200.45 | -2545.47 | -694.67 | 1982.73 | 1.13 | -1.01 | -0.5 | -153.76 | 94 | 9908.45 | 231154.33 | 3154535.99 | 30.2501 | -96.6762 | 195.26
12937 | 86.55 | 154.78 | 10207.15 | -2630.01 | -654.13 | 2076.48 | 1.6 | 1.35 | 0.85 | 32.17 | 94 | 9915.15 | 231069.79 | 3154576.53 | 30.2498 | -96.6761 | 193.97
13030 | 85.58 | 155.2 | 10213.53 | -2714.09 | -614.91 | 2169.25 | 1.14 | -1.04 | 0.45 | 156.65 | 93 | 9921.53 | 230985.71 | 3154615.75 | 30.2496 | -96.676 | 192.77
13124 | 85.67 | 155.19 | 10220.7 | -2799.17 | -575.58 | 2262.95 | 0.1 | 0.1 | -0.01 | -6.32 | 94 | 9928.7 | 230900.63 | 3154655.08 | 30.2494 | -96.6759 | 191.62
13219 | 86.05 | 155.34 | 10227.56 | -2885.23 | -535.94 | 2357.68 | 0.43 | 0.4 | 0.16 | 21.5 | 95 | 9935.56 | 230814.57 | 3154694.72 | 30.2491 | -96.6758 | 190.52
13313 | 86.68 | 155.67 | 10233.52 | -2970.6 | -497.04 | 2451.46 | 0.76 | 0.67 | 0.35 | 27.61 | 94 | 9941.52 | 230729.2 | 3154733.62 | 30.2489 | -96.6757 | 189.5
13408 | 85.14 | 154.72 | 10240.29 | -3056.61 | -457.29 | 2546.19 | 1.9 | -1.62 | -1 | -148.43 | 95 | 9948.29 | 230643.19 | 3154773.37 | 30.2486 | -96.6755 | 188.51
13502 | 84.89 | 154.46 | 10248.46 | -3141.2 | -417.11 | 2639.83 | 0.38 | -0.27 | -0.28 | -134 | 94 | 9956.46 | 230558.6 | 3154813.55 | 30.2484 | -96.6754 | 187.56
13596 | 86.42 | 154.63 | 10255.58 | -3225.83 | -376.83 | 2733.55 | 1.64 | 1.63 | 0.18 | 6.33 | 94 | 9963.58 | 230473.97 | 3154853.83 | 30.2482 | -96.6753 | 186.66
13690 | 88.11 | 154.5 | 10260.07 | -3310.61 | -336.5 | 2827.44 | 1.8 | 1.8 | -0.14 | -4.4 | 94 | 9968.07 | 230389.19 | 3154894.16 | 30.2479 | -96.6752 | 185.8
13784 | 88.35 | 154.12 | 10262.97 | -3395.28 | -295.77 | 2921.39 | 0.48 | 0.26 | -0.4 | -57.72 | 94 | 9970.97 | 230304.52 | 3154934.89 | 30.2477 | -96.6751 | 184.98
13879 | 90.19 | 154.41 | 10264.18 | -3480.85 | -254.53 | 3016.38 | 1.96 | 1.94 | 0.31 | 8.96 | 95 | 9972.18 | 230218.95 | 3154976.13 | 30.2474 | -96.6749 | 184.18
13973 | 89.85 | 152.78 | 10264.15 | -3565.04 | -212.73 | 3110.37 | 1.77 | -0.36 | -1.73 | -101.78 | 94 | 9972.15 | 230134.76 | 3155017.93 | 30.2472 | -96.6748 | 183.41
14068 | 89.01 | 154.55 | 10265.09 | -3650.17 | -170.59 | 3205.36 | 2.06 | -0.88 | 1.86 | 115.4 | 95 | 9973.09 | 230049.63 | 3155060.07 | 30.247 | -96.6747 | 182.68
14163 | 86.13 | 154.82 | 10269.12 | -3735.96 | -130 | 3300.26 | 3.04 | -3.03 | 0.28 | 174.65 | 95 | 9977.12 | 229963.84 | 3155100.66 | 30.2467 | -96.6746 | 181.99
14258 | 86.56 | 154.77 | 10275.18 | -3821.74 | -89.63 | 3395.05 | 0.46 | 0.45 | -0.05 | -6.62 | 95 | 9983.18 | 229878.06 | 3155141.03 | 30.2465 | -96.6745 | 181.34
14351 | 85.11 | 153.69 | 10281.93 | -3905.27 | -49.31 | 3487.8 | 1.94 | -1.56 | -1.16 | -143.43 | 93 | 9989.93 | 229794.53 | 3155181.35 | 30.2463 | -96.6743 | 180.72
14446 | 85.09 | 153.22 | 10290.05 | -3989.94 | -7.01 | 3582.45 | 0.49 | -0.02 | -0.49 | -92.47 | 95 | 9998.05 | 229709.86 | 3155223.65 | 30.246 | -96.6742 | 180.1
14540 | 86.28 | 154.24 | 10297.12 | -4073.99 | 34.48 | 3676.18 | 1.67 | 1.27 | 1.09 | 40.56 | 94 | 10005.12 | 229625.81 | 3155265.14 | 30.2458 | -96.6741 | 179.52
14635 | 87.74 | 154.11 | 10302.07 | -4159.39 | 75.8 | 3771.05 | 1.54 | 1.54 | -0.14 | -5.08 | 95 | 10010.07 | 229540.41 | 3155306.46 | 30.2456 | -96.674 | 178.96
14730 | 86.92 | 153.26 | 10306.5 | -4244.45 | 117.87 | 3865.94 | 1.24 | -0.86 | -0.89 | -134.02 | 95 | 10014.5 | 229455.35 | 3155348.53 | 30.2453 | -96.6738 | 178.41
14824 | 86.53 | 152.49 | 10311.87 | -4327.97 | 160.66 | 3959.77 | 0.92 | -0.41 | -0.82 | -116.92 | 94 | 10019.87 | 229371.83 | 3155391.32 | 30.2451 | -96.6737 | 177.87
14919 | 86.49 | 149.41 | 10317.65 | -4410.86 | 206.7 | 4054.45 | 3.24 | -0.04 | -3.24 | -90.84 | 95 | 10025.65 | 229288.94 | 3155437.36 | 30.2449 | -96.6736 | 177.32
15013 | 86.95 | 154.45 | 10323.04 | -4493.64 | 250.84 | 4148.21 | 5.38 | 0.49 | 5.36 | 84.92 | 94 | 10031.04 | 229206.16 | 3155481.5 | 30.2446 | -96.6735 | 176.8
15107 | 86.81 | 152.55 | 10328.15 | -4577.63 | 292.72 | 4242.06 | 2.02 | -0.15 | -2.02 | -94.27 | 94 | 10036.15 | 229122.17 | 3155523.38 | 30.2444 | -96.6733 | 176.34
15202 | 84.67 | 147.25 | 10335.21 | -4659.56 | 340.21 | 4336.52 | 6 | -2.25 | -5.58 | -112.22 | 95 | 10043.21 | 229040.24 | 3155570.87 | 30.2442 | -96.6732 | 175.82
15296 | 83.38 | 148.28 | 10345 | -4738.64 | 390.07 | 4429.45 | 1.75 | -1.37 | 1.1 | 141.6 | 94 | 10053 | 228961.16 | 3155620.73 | 30.2439 | -96.673 | 175.29
15390 | 84.35 | 152.31 | 10355.05 | -4819.8 | 436.37 | 4522.7 | 4.39 | 1.03 | 4.29 | 76.61 | 94 | 10063.05 | 228880 | 3155667.03 | 30.2437 | -96.6729 | 174.83
15484 | 85.06 | 152.15 | 10363.72 | -4902.62 | 479.98 | 4616.26 | 0.77 | 0.76 | -0.17 | -12.65 | 94 | 10071.72 | 228797.18 | 3155710.64 | 30.2435 | -96.6728 | 174.41
15579 | 85.52 | 153.97 | 10371.52 | -4987.02 | 522.88 | 4710.92 | 1.97 | 0.48 | 1.92 | 75.85 | 95 | 10079.52 | 228712.78 | 3155753.54 | 30.2432 | -96.6726 | 174.01
15673 | 86.71 | 154.82 | 10377.89 | -5071.59 | 563.4 | 4804.7 | 1.55 | 1.27 | 0.9 | 35.51 | 94 | 10085.89 | 228628.21 | 3155794.06 | 30.243 | -96.6725 | 173.66
15766 | 87.62 | 154.45 | 10382.49 | -5155.52 | 603.19 | 4897.58 | 1.06 | 0.98 | -0.4 | -22.11 | 93 | 10090.49 | 228544.28 | 3155833.85 | 30.2428 | -96.6724 | 173.33
15861 | 86.55 | 155.93 | 10387.32 | -5241.64 | 643 | 4992.43 | 1.92 | -1.13 | 1.56 | 125.94 | 95 | 10095.32 | 228458.16 | 3155873.66 | 30.2425 | -96.6723 | 173.01
15955 | 86.61 | 156.46 | 10392.93 | -5327.49 | 680.88 | 5086.19 | 0.57 | 0.06 | 0.56 | 83.55 | 94 | 10100.93 | 228372.31 | 3155911.54 | 30.2423 | -96.6722 | 172.72
16049 | 88.33 | 156.51 | 10397.08 | -5413.6 | 718.34 | 5180.01 | 1.83 | 1.83 | 0.05 | 1.66 | 94 | 10105.08 | 228286.2 | 3155949 | 30.242 | -96.6721 | 172.44
16142 | 85.55 | 156.4 | 10402.05 | -5498.72 | 755.44 | 5272.78 | 2.99 | -2.99 | -0.12 | -177.74 | 93 | 10110.05 | 228201.08 | 3155986.1 | 30.2418 | -96.672 | 172.18
16235 | 86.6 | 156.35 | 10408.41 | -5583.73 | 792.62 | 5365.48 | 1.13 | 1.13 | -0.05 | -2.72 | 93 | 10116.41 | 228116.07 | 3156023.28 | 30.2416 | -96.6719 | 171.92
16329 | 85.7 | 156.84 | 10414.72 | -5669.8 | 829.87 | 5459.17 | 1.09 | -0.96 | 0.52 | 151.5 | 94 | 10122.72 | 228030 | 3156060.53 | 30.2413 | -96.6717 | 171.67
16424 | 85.21 | 156.57 | 10422.25 | -5756.78 | 867.33 | 5553.76 | 0.59 | -0.52 | -0.28 | -151.23 | 95 | 10130.25 | 227943.02 | 3156097.99 | 30.2411 | -96.6716 | 171.43
16518 | 86.19 | 156.35 | 10429.3 | -5842.71 | 904.76 | 5647.41 | 1.07 | 1.04 | -0.23 | -12.63 | 94 | 10137.3 | 227857.09 | 3156135.42 | 30.2409 | -96.6715 | 171.2
16612 | 87.7 | 156.4 | 10434.31 | -5928.71 | 942.38 | 5741.19 | 1.61 | 1.61 | 0.05 | 1.9 | 94 | 10142.31 | 227771.09 | 3156173.04 | 30.2406 | -96.6714 | 170.97
16707 | 86.93 | 154.43 | 10438.76 | -6015 | 981.86 | 5836.05 | 2.22 | -0.81 | -2.07 | -111.41 | 95 | 10146.76 | 227684.8 | 3156212.52 | 30.2404 | -96.6713 | 170.73
16802 | 86.91 | 154.71 | 10443.86 | -6100.67 | 1022.59 | 5930.91 | 0.3 | -0.02 | 0.29 | 94.1 | 95 | 10151.86 | 227599.13 | 3156253.25 | 30.2401 | -96.6712 | 170.48
16897 | 87.07 | 155.05 | 10448.85 | -6186.57 | 1062.86 | 6025.76 | 0.4 | 0.17 | 0.36 | 64.78 | 95 | 10156.85 | 227513.23 | 3156293.52 | 30.2399 | -96.6711 | 170.25
16991 | 86.76 | 153.18 | 10453.91 | -6271.01 | 1103.84 | 6119.62 | 2.01 | -0.33 | -1.99 | -99.48 | 94 | 10161.91 | 227428.79 | 3156334.5 | 30.2397 | -96.6709 | 170.02
17084 | 87.33 | 152.01 | 10458.71 | -6353.46 | 1146.59 | 6212.47 | 1.4 | 0.61 | -1.26 | -64.03 | 93 | 10166.71 | 227346.34 | 3156377.25 | 30.2394 | -96.6708 | 169.77
17178 | 87.63 | 151.43 | 10462.84 | -6436.16 | 1191.08 | 6306.31 | 0.69 | 0.32 | -0.62 | -62.64 | 94 | 10170.84 | 227263.64 | 3156421.74 | 30.2392 | -96.6707 | 169.52
17273 | 87.74 | 151.84 | 10466.68 | -6519.69 | 1236.18 | 6401.15 | 0.45 | 0.12 | 0.43 | 74.98 | 95 | 10174.68 | 227180.11 | 3156466.84 | 30.239 | -96.6705 | 169.26
17366 | 88.89 | 151.85 | 10469.41 | -6601.64 | 1280.04 | 6494.04 | 1.24 | 1.24 | 0.01 | 0.5 | 93 | 10177.41 | 227098.16 | 3156510.7 | 30.2387 | -96.6704 | 169.03
17460 | 86.78 | 152.9 | 10472.96 | -6684.86 | 1323.59 | 6587.93 | 2.51 | -2.24 | 1.12 | 153.58 | 94 | 10180.96 | 227014.94 | 3156554.25 | 30.2385 | -96.6703 | 168.8
17555 | 86.8 | 154.11 | 10478.28 | -6769.75 | 1365.91 | 6682.78 | 1.27 | 0.02 | 1.27 | 89.09 | 95 | 10186.28 | 226930.05 | 3156596.57 | 30.2383 | -96.6702 | 168.59
17647 | 87.06 | 153.51 | 10483.21 | -6852.19 | 1406.45 | 6774.64 | 0.71 | 0.28 | -0.65 | -66.56 | 92 | 10191.21 | 226847.61 | 3156637.11 | 30.238 | -96.67 | 168.4
17741 | 87.2 | 153.31 | 10487.92 | -6936.14 | 1448.47 | 6868.52 | 0.26 | 0.15 | -0.21 | -54.98 | 94 | 10195.92 | 226763.66 | 3156679.13 | 30.2378 | -96.6699 | 168.2
17836 | 87.64 | 154.3 | 10492.19 | -7021.29 | 1490.37 | 6963.42 | 1.14 | 0.46 | 1.04 | 66.04 | 95 | 10200.19 | 226678.51 | 3156721.03 | 30.2376 | -96.6698 | 168.02
17930 | 87.77 | 154.98 | 10495.96 | -7106.17 | 1530.59 | 7057.34 | 0.74 | 0.14 | 0.72 | 79.18 | 94 | 10203.96 | 226593.63 | 3156761.25 | 30.2373 | -96.6697 | 167.84
18025 | 87.77 | 153.69 | 10499.65 | -7191.73 | 1571.71 | 7152.27 | 1.36 | 0 | -1.36 | -90.03 | 95 | 10207.65 | 226508.07 | 3156802.37 | 30.2371 | -96.6696 | 167.67
18120 | 87.13 | 153.76 | 10503.88 | -7276.83 | 1613.72 | 7247.17 | 0.68 | -0.67 | 0.07 | 173.77 | 95 | 10211.88 | 226422.97 | 3156844.38 | 30.2368 | -96.6694 | 167.5
18214 | 87.58 | 154.42 | 10508.22 | -7361.29 | 1654.75 | 7341.07 | 0.85 | 0.48 | 0.7 | 55.7 | 94 | 10216.22 | 226338.51 | 3156885.41 | 30.2366 | -96.6693 | 167.33
18309 | 88.11 | 154.43 | 10511.79 | -7446.92 | 1695.73 | 7436 | 0.56 | 0.56 | 0.01 | 1.08 | 95 | 10219.79 | 226252.88 | 3156926.39 | 30.2364 | -96.6692 | 167.17
18403 | 87.89 | 154.09 | 10515.07 | -7531.54 | 1736.53 | 7529.94 | 0.43 | -0.23 | -0.36 | -122.93 | 94 | 10223.07 | 226168.26 | 3156967.19 | 30.2361 | -96.6691 | 167.02
18497 | 87.83 | 153.96 | 10518.58 | -7615.99 | 1777.67 | 7623.87 | 0.15 | -0.06 | -0.14 | -114.79 | 94 | 10226.58 | 226083.81 | 3157008.33 | 30.2359 | -96.6689 | 166.86
18592 | 88.37 | 153.75 | 10521.73 | -7701.22 | 1819.51 | 7718.82 | 0.61 | 0.57 | -0.22 | -21.24 | 95 | 10229.73 | 225998.58 | 3157050.17 | 30.2357 | -96.6688 | 166.71
18686 | 85.6 | 154.05 | 10526.67 | -7785.51 | 1860.8 | 7812.68 | 2.96 | -2.95 | 0.32 | 173.83 | 94 | 10234.67 | 225914.29 | 3157091.46 | 30.2354 | -96.6687 | 166.56
18780 | 84.87 | 154.54 | 10534.48 | -7869.91 | 1901.43 | 7906.36 | 0.93 | -0.78 | 0.52 | 146.24 | 94 | 10242.48 | 225829.89 | 3157132.09 | 30.2352 | -96.6686 | 166.42
18869 | 84.52 | 154.4 | 10542.71 | -7949.88 | 1939.63 | 7994.97 | 0.42 | -0.39 | -0.16 | -158.29 | 89 | 10250.71 | 225749.92 | 3157170.29 | 30.235 | -96.6685 | 166.29
18929 | 84.52 | 154.4 | 10548.44 | -8003.74 | 1965.43 | 8054.69 | 0 | 0 | 0 | 0 | 60 | 10256.44 | 225696.06 | 3157196.09 | 30.2348 | -96.6684 | 166.2

## 10_4_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/04/2021 |  |  | Report Time: |  | 12:00-24:00
|  |  |  | Daily Cost($): |  | 12510 |  |  | Well Cost($): |  | 12510
|  |  |  | 24hr Summary: |  | Standby on location
|  |  |  | 24hr Lookahead: |  | Standby on location
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  |  |  | Csg Shoe MD(Usft): |  | 80 |  | 600: |  | PV:
End Depth (Usft): |  | 108 |  | 108 |  | OD (in): |  | 20 |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 40 |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley
Chris Mayeaux |  | Marshall Adams |  | Jason Smetters | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma (Standby) |  |  |  |  | 10/04/2021 |  | 4 |  | 4350 |  | 1 | 4350
Job Start-Up Incidentals |  |  |  |  | 10/04/2021 |  | 1 |  | 6000 |  | 1 | 6000
Personnel Mileage |  |  |  |  | 10/04/2021 |  | 8 |  | 2 |  | 880 | 1760
Perdiem Per Hand |  |  |  |  | 10/04/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 12510
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/04/2021 | 12:00 | 24:00 | 12 | 108 | 108 | 0 | SUR |  | 24B | Arrive location, strap tools set up job
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_5_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/05/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4750 |  |  | Well Cost($): |  | 17260
|  |  |  | 24hr Summary: |  | Standby on location
|  |  |  | 24hr Lookahead: |  | Standby on location
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  |  |  | Csg Shoe MD(Usft): |  | 80 |  | 600: |  | PV:
End Depth (Usft): |  | 108 |  | 108 |  | OD (in): |  | 20 |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 40 |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley
Chris Mayeaux |  | Marshall Adams |  | Jason Smetters | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma (Standby) |  |  |  |  | 10/05/2021 |  | 4 |  | 4350 |  | 1 | 4350
Perdiem Per Hand |  |  |  |  | 10/05/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 4750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/05/2021 | 00:00 | 24:00 | 24 | 108 | 108 | 0 | SUR |  | 24B | Standby on location for rig up
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_6_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/06/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 8780 |  |  | Well Cost($): |  | 26040
|  |  |  | 24hr Summary: |  | Standby
|  |  |  | 24hr Lookahead: |  | Pick Up BHA #1 - Drill Surface - POOH for Surface Casing
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 80 |  | 600: | 1 | PV: | 1
End Depth (Usft): |  | 2629 |  | 2629 |  | OD (in): |  | 20 |  | 300: | 1 | YP: | 1
Total Drilled (Usft): |  | 2521 |  | 2521 |  | Weight (ft/lbs): |  | 40 |  | 200: | 1 | Viscosity: | 24
Slide Drilled (Usft): |  | 334 |  | 334 | [5 empty] | 100: | 1 | Chlorides: | 460
Rotary Drilled (Usft): |  | 2187 |  | 2187 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.01 / 0.40
Drlg/Circ Hrs: |  | 6.30 / 1.58 |  | 6.30 / 1.58 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0/100
Slide Drilling Hrs: |  | 1.47 |  | 1.47 |  | SN: |  | 47424 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 4.83 |  | 4.83 |  | Bit # |  | 1 |  | PH / Temp(F) | 6.2 / 75.00 | Fluid Loss / Mud Type: | 100 / WBM
ROP Rot/Slide (Usft/hr): |  | 452.48 / 227.73 |  | 452.48 / 227.73 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 8.33 |  | 8.33 |  | Grade In: |  | New
% Slide: |  | 13.25 |  | 13.25 |  | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
% Rotary: |  | 86.75 |  | 86.75 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley
Chris Mayeaux |  | Marshall Adams |  | Jason Smetters | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | 2 |  |  | 133.33 |  | 1.5 |  | 1.5
7/8 5.9 1.50 NBS HPW -.014 NBS 13 |  |  |  | 8 | 2 |  |  | 133.16 |  | 37.55 |  | 39.05
Nortrak Stabilizer |  |  |  | 13 | 2.875 |  |  | 150.56 |  | 7.97 |  | 47.02
Pony NMDC |  |  |  | 8 | 3.25 |  |  | 153.76 |  | 9.43 |  | 56.45
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.63 |  | 60.08
NMDC |  |  |  | 7.938 | 3.25 |  |  | 148.66 |  | 30.27 |  | 90.35
NMDC |  |  |  | 7.875 | 3.25 |  |  | 150 |  | 30 |  | 120.35
Crossover Sub |  |  |  | 7.75 | 3.25 |  |  | 120.12 |  | 3.33 |  | 123.68
11 Jts - HWDP |  |  |  | 5 | 3.8 |  |  | 43 |  | 334.43 |  | 458.11
458.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800023 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 1.5 |  | 0.16 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
200 | 0.54 | 334.68 | 200 | 0.85 | -0.4 | 0.27 |  | 334.68 | -0.94 | 0.27 |  | 0 | 200
293 | 0.85 | 329.26 | 292.99 | 1.84 | -0.94 | 0.34 |  | -14.69 | -2.07 | 0.33 |  | 0 | 93
384 | 0.94 | 332.3 | 383.98 | 3.08 | -1.64 | 0.11 |  | 29.34 | -3.49 | 0.1 |  | 0 | 91
478 | 0.94 | 322.09 | 477.97 | 4.37 | -2.47 | 0.18 |  | -95.1 | -5.01 | 0 |  | 0 | 94
572 | 0.9 | 332.51 | 571.95 | 5.64 | -3.28 | 0.18 |  | 108.62 | -6.5 | -0.04 |  | 0 | 94
665 | 1.16 | 332.39 | 664.94 | 7.12 | -4.06 | 0.28 |  | -0.54 | -8.18 | 0.28 |  | 0 | 93
759 | 1.22 | 323.7 | 758.92 | 8.77 | -5.09 | 0.2 |  | -75.99 | -10.11 | 0.06 |  | 0 | 94
852 | 1.22 | 331.07 | 851.9 | 10.43 | -6.15 | 0.17 |  | 93.68 | -12.07 | 0 |  | 0 | 93
946 | 1.29 | 298.46 | 945.88 | 11.81 | -7.57 | 0.75 |  | -100.85 | -13.94 | 0.07 |  | 0 | 94
1040 | 1.88 | 277.23 | 1039.84 | 12.51 | -10.03 | 0.88 |  | -55.81 | -15.64 | 0.63 |  | 0 | 94
1133 | 3.03 | 273.04 | 1132.75 | 12.83 | -14 | 1.25 |  | -10.97 | -17.67 | 1.24 |  | -4.51 | 93
1228 | 3.7 | 265.72 | 1227.59 | 12.74 | -19.56 | 0.84 |  | -36.36 | -20.03 | 0.71 |  | -7.71 | 95
1322 | 3.88 | 262.8 | 1321.38 | 12.11 | -25.74 | 0.28 |  | -48.46 | -22.18 | 0.19 |  | -3.11 | 94
1415 | 3.75 | 260.36 | 1414.18 | 11.21 | -31.86 | 0.22 |  | -129.9 | -24.05 | -0.14 |  | -2.62 | 93
1509 | 3.69 | 259.33 | 1507.98 | 10.13 | -37.86 | 0.1 |  | -132.43 | -25.72 | -0.06 |  | -1.1 | 94
1602 | 3.84 | 258.28 | 1600.78 | 8.95 | -43.85 | 0.18 |  | -25.21 | -27.28 | 0.16 |  | -1.13 | 93
1696 | 4.76 | 254.48 | 1694.51 | 7.26 | -50.69 | 1.02 |  | -19.11 | -28.77 | 0.98 |  | -4.04 | 94
1790 | 5.94 | 255.04 | 1788.1 | 4.97 | -59.15 | 1.26 |  | 2.81 | -30.41 | 1.26 |  | 0.6 | 94
1883 | 7.23 | 257.83 | 1880.49 | 2.49 | -69.52 | 1.43 |  | 15.32 | -32.73 | 1.39 |  | 3 | 93
1977 | 8.45 | 259.7 | 1973.61 | 0.01 | -82.1 | 1.33 |  | 12.74 | -36.02 | 1.3 |  | 1.99 | 94
2070 | 8.97 | 262.33 | 2065.54 | -2.18 | -96.01 | 0.7 |  | 38.75 | -40.16 | 0.56 |  | 2.83 | 93
2164 | 10.26 | 265.97 | 2158.21 | -3.75 | -111.62 | 1.52 |  | 27.04 | -45.6 | 1.37 |  | 3.87 | 94
2258 | 11.5 | 268.61 | 2250.52 | -4.56 | -129.34 | 1.42 |  | 23.19 | -52.64 | 1.32 |  | 2.81 | 94
2352 | 12.32 | 268.45 | 2342.5 | -5.06 | -148.73 | 0.87 |  | -2.38 | -60.7 | 0.87 |  | -0.17 | 94
2446 | 14.38 | 265.37 | 2433.95 | -6.28 | -170.39 | 2.32 |  | -20.55 | -69.11 | 2.19 |  | -3.28 | 94
2540 | 15.6 | 264.38 | 2524.75 | -8.46 | -194.61 | 1.33 |  | -12.33 | -77.77 | 1.3 |  | -1.05 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 400.16 | 9.71 | 87.91 | 227 | 872.2 | 1908.47 | 1440.68 | 0 | 59.32 | 59.32 | 59.32 | 4.72 | 0
Run | 400.16 | 9.71 | 87.91 | 227 | 872.2 | 1908.47 | 1440.68 | 0 | 59.32 | 59.32 | 59.32 | 4.72 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/06/2021 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 10/06/2021 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/06/2021 |  | 3 |  | -400 |  | 1 | -400
Stabilizer Rental 13 Used |  |  |  |  | 10/06/2021 |  | 17 |  | 1150 |  | 1 | 1150
Stabilizer Rental 13 Not Used |  |  |  |  | 10/06/2021 |  | 18 |  | 230 |  | 1 | 230
Total | [11 empty] | 8780
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/06/2021 | 00:00 | 13:30 | 13.5 | 108 | 108 | 0 | SUR |  | 24B | Standby for Rig Up
10/06/2021 | 13:30 | 15:40 | 2.17 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | M/U BHA #1
10/06/2021 | 15:40 | 16:28 | 0.8 | 108 | 215 | 107 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/215.00, w/WOB 5.00,Flow 400.00, RPM 30.00, Press 400.00, Tq 1.00, ROP 133.75, Diff 0.00, Temp 100.00
10/06/2021 | 16:28 | 16:40 | 0.2 | 215 | 274 | 59 | SUR | 1: BHA 1 | 2K | Rotary Drill f/215.00 t/274.00, w/WOB 7.00,Flow 460.00, RPM 40.00, Press 500.00, Tq 2.00, ROP 295.00, Diff 0.00, Temp 100.00
10/06/2021 | 16:40 | 16:44 | 0.07 | 274 | 274 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 16:44 | 17:00 | 0.27 | 274 | 367 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/274.00 t/367.00, w/WOB 8.00,Flow 500.00, RPM 60.00, Press 800.00, Tq 2.00, ROP 348.75, Diff 100.00, Temp 100.00
10/06/2021 | 17:00 | 17:05 | 0.08 | 367 | 367 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 17:05 | 17:17 | 0.2 | 367 | 458 | 91 | SUR | 1: BHA 1 | 2K | Rotary Drill f/367.00 t/458.00, w/WOB 8.00,Flow 600.00, RPM 70.00, Press 900.00, Tq 3.00, ROP 455.00, Diff 0.00, Temp 100.00
10/06/2021 | 17:17 | 17:22 | 0.08 | 458 | 458 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 17:22 | 17:36 | 0.23 | 458 | 552 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/458.00 t/552.00, w/WOB 10,Flow 900, RPM 100, Press 2000, Tq 5, ROP 402.86, Diff 500.00, Temp 100.00
10/06/2021 | 17:36 | 17:42 | 0.1 | 552 | 552 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 17:42 | 17:51 | 0.15 | 552 | 646 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/552.00 t/646.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 626.67, Diff 500.00, Temp 100.00
10/06/2021 | 17:51 | 17:57 | 0.1 | 646 | 646 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 17:57 | 18:08 | 0.18 | 646 | 740 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/646.00 t/740.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 512.73, Diff 500.00, Temp 100.00
10/06/2021 | 18:08 | 18:35 | 0.45 | 740 | 740 | 0 | SUR | 1: BHA 1 | 8B | Repair Drawworks
10/06/2021 | 18:35 | 18:38 | 0.05 | 740 | 740 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 18:38 | 18:46 | 0.13 | 740 | 833 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/740.00 t/833.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 697.50, Diff 500.00, Temp 100.00
10/06/2021 | 18:46 | 18:50 | 0.07 | 833 | 833 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 18:50 | 18:56 | 0.1 | 833 | 926 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/833.00 t/926.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 930.00, Diff 500.00, Temp 100.00
10/06/2021 | 18:56 | 19:00 | 0.07 | 926 | 926 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 19:00 | 19:02 | 0.03 | 926 | 930 | 4 | SUR | 1: BHA 1 | 2K | Rotary Drill f/926.00 t/930.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:02 | 19:05 | 0.05 | 930 | 945 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/930.00 t/945.00, TF 240.00M, w/WOB 5.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 300.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:05 | 19:10 | 0.08 | 945 | 1020 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/945.00 t/1020.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 900.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:10 | 19:14 | 0.07 | 1020 | 1020 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 19:14 | 19:16 | 0.03 | 1020 | 1026 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1020.00 t/1026.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 180.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:16 | 19:21 | 0.08 | 1026 | 1046 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1026.00 t/1046.00, TF 260.00M, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 240.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:21 | 19:26 | 0.08 | 1046 | 1114 | 68 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1046.00 t/1114.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 816.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:26 | 19:29 | 0.05 | 1114 | 1114 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 19:29 | 19:32 | 0.05 | 1114 | 1120 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1114.00 t/1120.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:32 | 19:36 | 0.07 | 1120 | 1145 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/1120.00 t/1145.00, TF 270.00M, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 375.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:36 | 19:42 | 0.1 | 1145 | 1207 | 62 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1145.00 t/1207.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 620.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:42 | 19:45 | 0.05 | 1207 | 1207 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 19:45 | 19:47 | 0.03 | 1207 | 1214 | 7 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1207.00 t/1214.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 210.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:47 | 19:50 | 0.05 | 1214 | 1229 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1214.00 t/1229.00, TF 270.00M, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 300.00, Diff 500.00, Temp 100.00
10/06/2021 | 19:50 | 19:57 | 0.12 | 1229 | 1302 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1229.00 t/1302.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 625.71, Diff 500.00, Temp 100.00
10/06/2021 | 19:57 | 20:00 | 0.05 | 1302 | 1302 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 20:00 | 20:08 | 0.13 | 1302 | 1396 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1302.00 t/1396.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 705.00, Diff 500.00, Temp 100.00
10/06/2021 | 20:08 | 20:11 | 0.05 | 1396 | 1396 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 20:11 | 20:19 | 0.13 | 1396 | 1489 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1396.00 t/1489.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 697.50, Diff 500.00, Temp 100.00
10/06/2021 | 20:19 | 20:21 | 0.03 | 1489 | 1489 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 20:21 | 20:30 | 0.15 | 1489 | 1583 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1489.00 t/1583.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 626.67, Diff 500.00, Temp 100.00
10/06/2021 | 20:30 | 20:33 | 0.05 | 1583 | 1583 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 20:33 | 20:36 | 0.05 | 1583 | 1600 | 17 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1583.00 t/1600.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 340.00, Diff 500.00, Temp 100.00
10/06/2021 | 20:36 | 20:38 | 0.03 | 1600 | 1610 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1600.00 t/1610.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 300.00, Diff 500.00, Temp 100.00
10/06/2021 | 20:38 | 20:45 | 0.12 | 1610 | 1676 | 66 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1610.00 t/1676.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 565.71, Diff 500.00, Temp 100.00
10/06/2021 | 20:45 | 20:48 | 0.05 | 1676 | 1676 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 20:48 | 20:51 | 0.05 | 1676 | 1685 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1676.00 t/1685.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 180.00, Diff 500.00, Temp 100.00
10/06/2021 | 20:51 | 21:00 | 0.15 | 1685 | 1710 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/1685.00 t/1710.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 166.67, Diff 500.00, Temp 100.00
10/06/2021 | 21:00 | 21:06 | 0.1 | 1710 | 1770 | 60 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1710.00 t/1770.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 600.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:06 | 21:10 | 0.07 | 1770 | 1770 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 21:10 | 21:12 | 0.03 | 1770 | 1784 | 14 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1770.00 t/1784.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 420.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:12 | 21:18 | 0.1 | 1784 | 1809 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/1784.00 t/1809.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 250.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:18 | 21:23 | 0.08 | 1809 | 1864 | 55 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1809.00 t/1864.00, w/WOB 10.00,Flow 900.00, RPM 80.00, Press 2000.00, Tq 5.00, ROP 660.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:23 | 21:27 | 0.07 | 1864 | 1864 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 21:27 | 21:30 | 0.05 | 1864 | 1874 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1864.00 t/1874.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 200.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:30 | 21:35 | 0.08 | 1874 | 1874 | 0 | SUR | 1: BHA 1 | 2J | Slide Drill f/1874.00 t/1874.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 0.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:35 | 21:41 | 0.1 | 1874 | 1957 | 83 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1874.00 t/1957.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 830.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:41 | 21:44 | 0.05 | 1957 | 1957 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 21:44 | 21:47 | 0.05 | 1957 | 1965 | 8 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1957.00 t/1965.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 160.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:47 | 21:51 | 0.07 | 1965 | 1980 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1965.00 t/1980.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 225.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:51 | 21:57 | 0.1 | 1980 | 2051 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1980.00 t/2051.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 710.00, Diff 500.00, Temp 100.00
10/06/2021 | 21:57 | 22:00 | 0.05 | 2051 | 2051 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 22:00 | 22:02 | 0.03 | 2051 | 2058 | 7 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2051.00 t/2058.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 210.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:02 | 22:07 | 0.08 | 2058 | 2083 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/2058.00 t/2083.00, TF 20.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 300.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:07 | 22:12 | 0.08 | 2083 | 2144 | 61 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2083.00 t/2144.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 732.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:12 | 22:16 | 0.07 | 2144 | 2144 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 22:16 | 22:19 | 0.05 | 2144 | 2151 | 7 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2144.00 t/2151.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 140.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:19 | 22:27 | 0.13 | 2151 | 2181 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2151.00 t/2181.00, TF 20.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 225.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:27 | 22:33 | 0.1 | 2181 | 2238 | 57 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2181.00 t/2238.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 570.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:33 | 22:36 | 0.05 | 2238 | 2238 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 22:36 | 22:39 | 0.05 | 2238 | 2244 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2238.00 t/2244.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:39 | 22:45 | 0.1 | 2244 | 2274 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2244.00 t/2274.00, TF 20.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 300.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:45 | 22:50 | 0.08 | 2274 | 2332 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2274.00 t/2332.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 696.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:50 | 22:52 | 0.03 | 2332 | 2332 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 22:52 | 22:55 | 0.05 | 2332 | 2338 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2332.00 t/2338.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 22:55 | 23:03 | 0.13 | 2338 | 2368 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2338.00 t/2368.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 225.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:03 | 23:10 | 0.12 | 2368 | 2426 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2368.00 t/2426.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 497.14, Diff 500.00, Temp 100.00
10/06/2021 | 23:10 | 23:13 | 0.05 | 2426 | 2426 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 23:13 | 23:16 | 0.05 | 2426 | 2432 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2426.00 t/2432.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:16 | 23:25 | 0.15 | 2432 | 2462 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2432.00 t/2462.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 200.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:25 | 23:30 | 0.08 | 2462 | 2520 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2462.00 t/2520.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 696.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:30 | 23:34 | 0.07 | 2520 | 2520 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 23:34 | 23:37 | 0.05 | 2520 | 2526 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2520.00 t/2526.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:37 | 23:45 | 0.13 | 2526 | 2556 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2526.00 t/2556.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 225.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:45 | 23:50 | 0.08 | 2556 | 2614 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2556.00 t/2614.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 696.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:50 | 23:54 | 0.07 | 2614 | 2614 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/06/2021 | 23:54 | 23:57 | 0.05 | 2614 | 2620 | 6 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2614.00 t/2620.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 120.00, Diff 500.00, Temp 100.00
10/06/2021 | 23:57 | 24:00 | 0.05 | 2620 | 2629 | 9 | SUR | 1: BHA 1 | 2J | Slide Drill f/2620.00 t/2629.00, TF 20.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 180.00, Diff 500.00, Temp 100.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_7_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/07/2021 |  |  | Report Time: |  | 00:00-12:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 26040
|  |  |  | 24hr Summary: |  | Drill Surface - POOH for Casing Ops
|  |  |  | 24hr Lookahead: |  | Standby for Casing Ops
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2629 |  | 108 |  | Csg Shoe MD(Usft): |  | 80 |  | 600: | 1 | PV: | 1
End Depth (Usft): |  | 3020 |  | 3020 |  | OD (in): |  | 20 |  | 300: | 1 | YP: | 1
Total Drilled (Usft): |  | 391 |  | 2912 |  | Weight (ft/lbs): |  | 40 |  | 200: | 1 | Viscosity: | 24
Slide Drilled (Usft): |  | 36 |  | 370 | [5 empty] | 100: | 1 | Chlorides: | 460
Rotary Drilled (Usft): |  | 355 |  | 2542 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.01 / 0.40
Drlg/Circ Hrs: |  | 0.88 / 1.00 |  | 7.18 / 2.58 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0/100
Slide Drilling Hrs: |  | 0.25 |  | 1.72 |  | SN: |  | 47424 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 0.63 |  | 5.47 |  | Bit # |  | 1 |  | PH / Temp(F) | 6.2 / 75.00 | Fluid Loss / Mud Type: | 100 / WBM
ROP Rot/Slide (Usft/hr): |  | 560.53 / 144.00 |  | 465.00 / 215.53 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 3.42 |  | 11.75 |  | Grade In: |  | New
% Slide: |  | 9.21 |  | 12.71 |  | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
% Rotary: |  | 90.79 |  | 87.29 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley
Chris Mayeaux |  | Marshall Adams |  | Jason Smetters | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | 2 |  |  | 133.33 |  | 1.5 |  | 1.5
7/8 5.9 1.50 NBS HPW -.014 NBS 13 |  |  |  | 8 | 2 |  |  | 133.16 |  | 37.55 |  | 39.05
Nortrak Stabilizer |  |  |  | 13 | 2.875 |  |  | 150.56 |  | 7.97 |  | 47.02
Pony NMDC |  |  |  | 8 | 3.25 |  |  | 153.76 |  | 9.43 |  | 56.45
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.63 |  | 60.08
NMDC |  |  |  | 7.938 | 3.25 |  |  | 148.66 |  | 30.27 |  | 90.35
NMDC |  |  |  | 7.875 | 3.25 |  |  | 150 |  | 30 |  | 120.35
Crossover Sub |  |  |  | 7.75 | 3.25 |  |  | 120.12 |  | 3.33 |  | 123.68
11 Jts - HWDP |  |  |  | 5 | 3.8 |  |  | 43 |  | 334.43 |  | 458.11
458.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800023 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 1.5 |  | 0.16 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2634 | 16.66 | 265.47 | 2615.05 | -10.76 | -220.62 | 1.17 |  | 16.47 | -87.11 | 1.13 |  | 1.16 | 94
2728 | 17.17 | 268.08 | 2704.99 | -12.29 | -247.92 | 0.97 |  | 57.37 | -97.72 | 0.54 |  | 2.78 | 94
2822 | 16.77 | 269.2 | 2794.89 | -12.94 | -275.35 | 0.55 |  | 141.28 | -109.16 | -0.43 |  | 1.19 | 94
2915 | 17.27 | 269.74 | 2883.82 | -13.19 | -302.57 | 0.56 |  | 17.8 | -120.88 | 0.54 |  | 0.58 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 442.64 | 10 | 100 | 244 | 900 | 2000 | 1500 | 0 | 60 | 60 | 60 | 5 | 0
Run | 405.38 | 9.75 | 89.39 | 229 | 875.52 | 1919.4 | 1447.76 | 0 | 59.4 | 59.4 | 59.4 | 4.76 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/07/2021 | 00:00 | 00:09 | 0.15 | 2629 | 2650 | 21 | SUR | 1: BHA 1 | 2J | Slide Drill f/2629.00 t/2650.00, TF 20.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 140.00, Diff 500.00, Temp 100.00
10/07/2021 | 00:09 | 00:14 | 0.08 | 2650 | 2708 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2650.00 t/2708.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 696.00, Diff 500.00, Temp 100.00
10/07/2021 | 00:14 | 00:17 | 0.05 | 2708 | 2708 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/07/2021 | 00:17 | 00:27 | 0.17 | 2708 | 2802 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2708.00 t/2802.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 564.00, Diff 500.00, Temp 100.00
10/07/2021 | 00:27 | 00:30 | 0.05 | 2802 | 2802 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/07/2021 | 00:30 | 00:33 | 0.05 | 2802 | 2820 | 18 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2802.00 t/2820.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 360.00, Diff 500.00, Temp 100.00
10/07/2021 | 00:33 | 00:39 | 0.1 | 2820 | 2835 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2820.00 t/2835.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2000.00, Tq 5.00, ROP 150.00, Diff 500.00, Temp 100.00
10/07/2021 | 00:39 | 00:47 | 0.13 | 2835 | 2896 | 61 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2835.00 t/2896.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 457.50, Diff 500.00, Temp 100.00
10/07/2021 | 00:47 | 00:50 | 0.05 | 2896 | 2896 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/07/2021 | 00:50 | 00:59 | 0.15 | 2896 | 2989 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2896.00 t/2989.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 620.00, Diff 500.00, Temp 100.00
10/07/2021 | 00:59 | 01:02 | 0.05 | 2989 | 2989 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
10/07/2021 | 01:02 | 01:05 | 0.05 | 2989 | 3020 | 31 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2989.00 t/3020.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5.00, ROP 620.00, Diff 500.00, Temp 100.00
10/07/2021 | 01:05 | 01:53 | 0.8 | 3020 | 3020 | 0 | SUR | 1: BHA 1 | 5A | Circulate Bottoms Up before POOH for Casing Ops
10/07/2021 | 01:53 | 03:05 | 1.2 | 3020 | 3020 | 0 | SUR | 1: BHA 1 | 6B | POOH after surface section TD
10/07/2021 | 03:05 | 03:25 | 0.33 | 3020 | 3020 | 0 | SUR | 1: BHA 1 | 6P | Pill MWD Tool & Rack Back BHA
10/07/2021 | 03:25 | 12:00 | 8.58 | 3020 | 3020 | 0 | SUR |  | 24B | Standby for Casing Ops & rig skid
10/07/2021 | 12:00 | 12:00 | 0 | 3020 | 3020 | 0 | SUR |  | 1G
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_17_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/17/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17900 |  |  | Well Cost($): |  | 43940
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Drill to KOP and build curve
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3020 |  | 3020 |  | Csg Shoe MD(Usft): |  | 3010 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 6676 |  | 6676 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  | 3656 |  | 3656 |  | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): |  | 152 |  | 152 | [5 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 3504 |  | 3504 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: |  | 9.20 / 3.07 |  | 9.20 / 3.07 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: |  | 1.5 |  | 1.5 |  | SN: |  | 56410 |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 7.7 |  | 7.7 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 455.06 / 101.33 |  | 455.06 / 101.33 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 14.5 |  | 14.5 |  | Grade In: |  | New
% Slide: |  | 4.16 |  | 4.16 |  | Grade Out:
% Rotary: |  | 95.84 |  | 95.84 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 250 |  | 1 |  | 1
7/8 5.9 2.0 TS HPW .001 |  |  |  | 8 | 2 |  |  | 131.75 |  | 37.95 |  | 38.95
Pony NMDC |  |  |  | 8 | 3.25 |  |  | 153.76 |  | 9.43 |  | 48.38
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.63 |  | 52.01
NMDC |  |  |  | 7.938 | 3.25 |  |  | 148.66 |  | 30.27 |  | 82.28
NMDC |  |  |  | 7.875 | 3.25 |  |  | 150 |  | 30 |  | 112.28
Crossover Sub |  |  |  | 7.875 | 3.25 |  |  | 119.05 |  | 3.36 |  | 115.64
6 Jts 6 1/2 DC |  |  |  | 6.5 | 2.75 |  |  | 95 |  | 186.2 |  | 301.84
Crossover Sub |  |  |  | 6.688 | 2.875 |  |  | 78.12 |  | 3.52 |  | 305.36
11 Jts - HWDP |  |  |  | 5 | 3.8 |  |  | 43 |  | 334.06 |  | 639.42
22 Stds 5 DP |  |  |  | 5 | 3.8 |  |  | 19.9 |  | 2062.46 |  | 2701.88
Agitator |  |  |  | 6.75 | 2.5 |  |  | 81.1 |  | 24.66 |  | 2726.54
2726.54
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800035 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.97 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3038 | 17.1 | 270.83 | 3001.33 | -13.01 | -338.91 | 0.3 |  | 118.35 | -136.98 | -0.14 |  | 0.89 | 123
3131 | 17.42 | 268.2 | 3090.14 | -13.25 | -366.49 | 0.91 |  | -68.96 | -148.87 | 0.34 |  | -2.83 | 93
3225 | 19.16 | 266.17 | 3179.39 | -14.72 | -395.95 | 1.97 |  | -21.08 | -160.46 | 1.85 |  | -2.16 | 94
3320 | 19.61 | 265.91 | 3269.01 | -16.9 | -427.41 | 0.48 |  | -10.98 | -172.31 | 0.47 |  | -0.27 | 95
3413 | 19.7 | 264.13 | 3356.59 | -19.62 | -458.57 | 0.65 |  | -82.29 | -183.54 | 0.1 |  | -1.91 | 93
3507 | 18.98 | 266.39 | 3445.28 | -22.2 | -489.58 | 1.1 |  | 134.95 | -194.82 | -0.77 |  | 2.4 | 94
3600 | 18.98 | 264.93 | 3533.23 | -24.49 | -519.74 | 0.51 |  | -90.69 | -205.99 | 0 |  | -1.57 | 93
3694 | 18.46 | 268.22 | 3622.26 | -26.3 | -549.84 | 1.25 |  | 117.77 | -217.57 | -0.55 |  | 3.5 | 94
3787 | 18.66 | 268.57 | 3710.42 | -27.13 | -579.43 | 0.25 |  | 29.28 | -229.81 | 0.22 |  | 0.38 | 93
3881 | 18.55 | 268.47 | 3799.51 | -27.91 | -609.41 | 0.12 |  | -163.87 | -242.26 | -0.12 |  | -0.11 | 94
3974 | 18.19 | 267.72 | 3887.77 | -28.88 | -638.71 | 0.46 |  | -147.07 | -254.24 | -0.39 |  | -0.81 | 93
4068 | 17.92 | 272.29 | 3977.15 | -28.89 | -667.82 | 1.53 |  | 102.96 | -267 | -0.29 |  | 4.86 | 94
4161 | 17.99 | 272.59 | 4065.62 | -27.66 | -696.46 | 0.12 |  | 53.02 | -280.67 | 0.08 |  | 0.32 | 93
4255 | 18.01 | 273.03 | 4155.02 | -26.24 | -725.47 | 0.15 |  | 81.84 | -294.67 | 0.02 |  | 0.47 | 94
4348 | 17.76 | 273.64 | 4243.52 | -24.58 | -753.98 | 0.34 |  | 143.44 | -308.67 | -0.27 |  | 0.66 | 93
4442 | 17.79 | 273.27 | 4333.03 | -22.85 | -782.63 | 0.12 |  | -75.3 | -322.79 | 0.03 |  | -0.39 | 94
4535 | 17.92 | 272.58 | 4421.56 | -21.4 | -811.11 | 0.27 |  | -58.76 | -336.59 | 0.14 |  | -0.74 | 93
4629 | 18.55 | 269.28 | 4510.84 | -20.93 | -840.5 | 1.29 |  | -60.19 | -349.9 | 0.67 |  | -3.51 | 94
4724 | 17.98 | 269.64 | 4601.05 | -21.22 | -870.28 | 0.61 |  | 168.97 | -362.71 | -0.6 |  | 0.38 | 95
4818 | 17.62 | 269.7 | 4690.55 | -21.38 | -899.01 | 0.38 |  | 177.11 | -375.17 | -0.38 |  | 0.06 | 94
4912 | 17.87 | 269.41 | 4780.08 | -21.6 | -927.66 | 0.28 |  | -19.61 | -387.54 | 0.27 |  | -0.31 | 94
5005 | 16.55 | 269.18 | 4868.91 | -21.94 | -955.17 | 1.42 |  | -177.16 | -399.3 | -1.42 |  | -0.25 | 93
5098 | 17.89 | 272.73 | 4957.74 | -21.45 | -982.69 | 1.83 |  | 39.81 | -411.81 | 1.44 |  | 3.82 | 93
5192 | 18.72 | 273.71 | 5046.99 | -19.79 | -1012.16 | 0.94 |  | 20.81 | -426.24 | 0.88 |  | 1.04 | 94
5286 | 18.96 | 273.17 | 5135.95 | -17.97 | -1042.46 | 0.32 |  | -36.26 | -441.17 | 0.26 |  | -0.57 | 94
5380 | 17.81 | 272.01 | 5225.15 | -16.62 | -1072.08 | 1.28 |  | -162.9 | -455.37 | -1.22 |  | -1.23 | 94
5473 | 16.69 | 272.4 | 5313.97 | -15.56 | -1099.64 | 1.21 |  | 174.29 | -468.41 | -1.2 |  | 0.42 | 93
5567 | 18.1 | 270.27 | 5403.67 | -14.92 | -1127.73 | 1.65 |  | -25.32 | -481.3 | 1.5 |  | -2.27 | 94
5660 | 17.36 | 269.21 | 5492.25 | -15.05 | -1156.05 | 0.87 |  | -156.94 | -493.62 | -0.8 |  | -1.14 | 93
5754 | 18.55 | 271.09 | 5581.67 | -14.96 | -1185.02 | 1.41 |  | 26.86 | -506.41 | 1.27 |  | 2 | 94
5848 | 19.21 | 270.97 | 5670.61 | -14.41 | -1215.43 | 0.7 |  | -3.42 | -520.24 | 0.7 |  | -0.13 | 94
5941 | 18.44 | 270.41 | 5758.64 | -14.05 | -1245.44 | 0.85 |  | -167.06 | -533.73 | -0.83 |  | -0.6 | 93
6035 | 18.09 | 271.22 | 5847.9 | -13.63 | -1274.89 | 0.46 |  | 144.43 | -547.03 | -0.37 |  | 0.86 | 94
6128 | 17.22 | 271.02 | 5936.52 | -13.08 | -1303.09 | 0.94 |  | -176.11 | -559.9 | -0.94 |  | -0.22 | 93
6222 | 18.91 | 272.13 | 6025.88 | -12.26 | -1332.23 | 1.83 |  | 12.04 | -573.41 | 1.8 |  | 1.18 | 94
6316 | 19.4 | 274.04 | 6114.68 | -10.6 | -1363.02 | 0.85 |  | 52.88 | -588.42 | 0.52 |  | 2.03 | 94
6410 | 19.05 | 273.76 | 6203.44 | -8.49 | -1393.9 | 0.39 |  | -165.37 | -603.85 | -0.37 |  | -0.3 | 94
6503 | 18.51 | 273.87 | 6291.49 | -6.5 | -1423.78 | 0.58 |  | 176.3 | -618.75 | -0.58 |  | 0.12 | 93
6597 | 17.43 | 273.91 | 6380.9 | -4.53 | -1452.71 | 1.15 |  | 179.36 | -633.21 | -1.15 |  | 0.04 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 397.39 | 22.55 | 76.42 | 209 | 798.38 | 3751.74 | 3510.72 | 0 | 157.56 | 148.24 | 139.18 | 6.38 | 0
Run | 397.39 | 22.55 | 76.42 | 209 | 798.38 | 3751.74 | 3510.72 | 0 | 157.56 | 148.24 | 139.18 | 6.38 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem Per Hand |  |  |  |  | 10/17/2021 |  | 7 |  | 100 |  | 4 | 400
8 Motor Reline |  |  |  |  | 10/17/2021 |  | 15 |  | 10500 |  | 1 | 10500
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/17/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/17/2021 |  | 3 |  | -400 |  | 1 | -400
Total | [11 empty] | 17900
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/17/2021 | 00:00 | 09:00 | 9 | 3020 | 3020 | 0 | INT |  | 24B | Standby on Location
10/17/2021 | 09:00 | 09:30 | 0.5 | 3020 | 3020 | 0 | INT | 2: BHA 2 | 6O | M/U BHA #2 out of derrick
10/17/2021 | 09:30 | 09:35 | 0.08 | 3020 | 3020 | 0 | INT | 2: BHA 2 | 5A | Test MWD and motor
10/17/2021 | 09:35 | 11:35 | 2 | 3020 | 3020 | 0 | INT | 2: BHA 2 | 6A | TIH t/2927
10/17/2021 | 11:35 | 12:14 | 0.65 | 3020 | 3020 | 0 | INT | 2: BHA 2 | 5A | Drill float collar and shoe track
10/17/2021 | 12:14 | 12:17 | 0.05 | 3020 | 3030 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3020.00 t/3030.00, w/WOB 15,Flow 420, RPM 30, Press 1250, Tq 3, ROP 200.00, Diff 100.00, Temp 104.00
10/17/2021 | 12:17 | 12:38 | 0.35 | 3030 | 3030 | 0 | INT | 2: BHA 2 | 5A | Circulate F/ FIT
10/17/2021 | 12:38 | 12:52 | 0.23 | 3030 | 3030 | 0 | INT | 2: BHA 2 | 15D | Perform FIT
10/17/2021 | 12:52 | 13:06 | 0.23 | 3030 | 3102 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/3030.00 t/3102.00, w/WOB 21.04,Flow 525.37, RPM 40.18, Press 1822.84, Tq 5.07, ROP 308.57, Diff 133.15, Temp 105.80
10/17/2021 | 13:06 | 13:10 | 0.07 | 3102 | 3102 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 13:10 | 13:24 | 0.23 | 3102 | 3195 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3102.00 t/3195.00, w/WOB 23.59,Flow 639.72, RPM 50.36, Press 2644.54, Tq 7.22, ROP 398.57, Diff 314.64, Temp 107.60
10/17/2021 | 13:24 | 13:28 | 0.07 | 3195 | 3195 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 13:28 | 13:30 | 0.03 | 3195 | 3205 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3195.00 t/3205.00, w/WOB 17.31,Flow 742.95, RPM 60.18, Press 3372.28, Tq 4.86, ROP 300.00, Diff 413.95, Temp 109.40
10/17/2021 | 13:30 | 13:34 | 0.07 | 3205 | 3215 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/3205.00 t/3215.00, TF 30G, w/WOB 11.24,Flow 743.39, Press 3217.5, Tq , ROP 150.00, Diff 261.22, Temp 111.20
10/17/2021 | 13:34 | 13:45 | 0.18 | 3215 | 3289 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/3215.00 t/3289.00, w/WOB 21.78,Flow 745.60, RPM 60.60, Press 3310.99, Tq 5.74, ROP 403.64, Diff 354.71, Temp 114.80
10/17/2021 | 13:45 | 13:49 | 0.07 | 3289 | 3289 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 13:49 | 14:00 | 0.18 | 3289 | 3384 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/3289.00 t/3384.00, w/WOB 27.93,Flow 814.03, RPM 70.12, Press 3760.51, Tq 5.42, ROP 518.18, Diff 312.19, Temp 118.40
10/17/2021 | 14:00 | 14:04 | 0.07 | 3384 | 3384 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 14:04 | 14:13 | 0.15 | 3384 | 3477 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3384.00 t/3477.00, w/WOB 24.23,Flow 818.02, RPM 80.17, Press 3812.94, Tq 5.18, ROP 620.00, Diff 446.06, Temp 122.00
10/17/2021 | 14:13 | 14:17 | 0.07 | 3477 | 3477 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 14:17 | 14:20 | 0.05 | 3477 | 3490 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/3477.00 t/3490.00, w/WOB 17.02,Flow 818.67, RPM 80.29, Press 3629.08, Tq 4.10, ROP 260.00, Diff 228.30, Temp 123.80
10/17/2021 | 14:20 | 14:26 | 0.1 | 3490 | 3502 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3490.00 t/3502.00, TF 90G, w/WOB 8.87,Flow 818.91, Press 3551.40, Tq 0, ROP 120.00, Diff -42.76, Temp 125.60
10/17/2021 | 14:26 | 14:27 | 0.02 | 3502 | 3502 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 14:27 | 14:34 | 0.12 | 3502 | 3571 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/3502.00 t/3571.00, w/WOB 20.63,Flow 817.60, RPM 80.29, Press 3764.54, Tq 5.78, ROP 591.43, Diff 265.14, Temp 127.40
10/17/2021 | 14:34 | 14:36 | 0.03 | 3571 | 3571 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 14:36 | 14:46 | 0.17 | 3571 | 3664 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3571.00 t/3664.00, w/WOB 26.00,Flow 817.78, RPM 80.30, Press 3924.98, Tq 6.76, ROP 558.00, Diff 236.92, Temp 131.00
10/17/2021 | 14:46 | 14:49 | 0.05 | 3664 | 3664 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 14:49 | 14:54 | 0.08 | 3664 | 3679 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/3664.00 t/3679.00, w/WOB 15.08,Flow 818.47, RPM 80.12, Press 3881.82, Tq 3.88, ROP 180.00, Diff 193.76, Temp 132.80
10/17/2021 | 14:54 | 14:59 | 0.08 | 3679 | 3691 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3679.00 t/3691.00, TF 108.03G, w/WOB 6.44,Flow 817.95, Press 3682.59, Tq 0, ROP 144.00, Diff 10.56, Temp 132.80
10/17/2021 | 14:59 | 15:06 | 0.12 | 3691 | 3758 | 67 | INT | 2: BHA 2 | 2K | Rotary Drill f/3691.00 t/3758.00, w/WOB 21.34,Flow 818.46, RPM 80.24, Press 3878.56, Tq 6.02, ROP 574.29, Diff 360.54, Temp 134.60
10/17/2021 | 15:06 | 15:09 | 0.05 | 3758 | 3758 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 15:09 | 15:20 | 0.18 | 3758 | 3851 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3758.00 t/3851.00, w/WOB 19.49,Flow 818.33, RPM 80.16, Press 3915.07, Tq 5.41, ROP 507.27, Diff 397.05, Temp 138.20
10/17/2021 | 15:20 | 15:22 | 0.03 | 3851 | 3851 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 15:22 | 15:34 | 0.2 | 3851 | 3944 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3851.00 t/3944.00, w/WOB 13.75,Flow 818.16, RPM 80.28, Press 3872.07, Tq 5.39, ROP 465.00, Diff 354.05, Temp 141.80
10/17/2021 | 15:34 | 15:37 | 0.05 | 3944 | 3944 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 15:37 | 15:46 | 0.15 | 3944 | 4038 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3944.00 t/4038.00, w/WOB 28.01,Flow 818.27, RPM 80.16, Press 4054.17, Tq 7.83, ROP 626.67, Diff 458.02, Temp 143.60
10/17/2021 | 15:46 | 15:49 | 0.05 | 4038 | 4038 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 15:49 | 15:54 | 0.08 | 4038 | 4054 | 16 | INT | 2: BHA 2 | 2K | Rotary Drill f/4038.00 t/4054.00, w/WOB 16.18,Flow 818.40, RPM 80.14, Press 3970.03, Tq 5.58, ROP 192.00, Diff 295.66, Temp 145.40
10/17/2021 | 15:54 | 15:59 | 0.08 | 4054 | 4068 | 14 | INT | 2: BHA 2 | 2J | Slide Drill f/4054.00 t/4068.00, TF 91.84G, w/WOB 8.37,Flow 818.07, Press 3820.02, Tq 0, ROP 168.00, Diff 116.69, Temp 147.20
10/17/2021 | 15:59 | 16:05 | 0.1 | 4068 | 4133 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/4068.00 t/4133.00, w/WOB 24.73,Flow 818.47, RPM 80.15, Press 3887.99, Tq 6.52, ROP 650.00, Diff 366.04, Temp 147.20
10/17/2021 | 16:05 | 16:08 | 0.05 | 4133 | 4133 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 16:08 | 16:16 | 0.13 | 4133 | 4225 | 92 | INT | 2: BHA 2 | 2K | Rotary Drill f/4133.00 t/4225.00, w/WOB 28.24,Flow 818.54, RPM 80.19, Press 3852.58, Tq 7.37, ROP 690.00, Diff 230.63, Temp 149.00
10/17/2021 | 16:16 | 16:19 | 0.05 | 4225 | 4225 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 16:19 | 16:27 | 0.13 | 4225 | 4319 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4225.00 t/4319.00, w/WOB 27.91,Flow 818.49, RPM 80.13, Press 3921.08, Tq 7.52, ROP 705.00, Diff 299.13, Temp 150.80
10/17/2021 | 16:27 | 16:30 | 0.05 | 4319 | 4319 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 16:30 | 16:37 | 0.12 | 4319 | 4412 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4319.00 t/4412.00, w/WOB 23.10,Flow 818.52, RPM 80.23, Press 3934.43, Tq 7.39, ROP 797.14, Diff 312.48, Temp 152.60
10/17/2021 | 16:37 | 16:40 | 0.05 | 4412 | 4412 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 16:40 | 16:51 | 0.18 | 4412 | 4506 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4412.00 t/4506.00, w/WOB 25.96,Flow 816.61, RPM 80.16, Press 3948.51, Tq 7.03, ROP 512.73, Diff 294.11, Temp 154.40
10/17/2021 | 16:51 | 16:54 | 0.05 | 4506 | 4506 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 16:54 | 17:01 | 0.12 | 4506 | 4599 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4506.00 t/4599.00, w/WOB 29.63,Flow 818.29, RPM 80.13, Press 3983.04, Tq 8.13, ROP 797.14, Diff 328.64, Temp 156.20
10/17/2021 | 17:01 | 17:04 | 0.05 | 4599 | 4599 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 17:04 | 17:09 | 0.08 | 4599 | 4614 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/4599.00 t/4614.00, w/WOB 9.30,Flow 818.73, RPM 80.16, Press 3803.12, Tq 4.78, ROP 180.00, Diff 193.95, Temp 156.20
10/17/2021 | 17:09 | 17:14 | 0.08 | 4614 | 4628 | 14 | INT | 2: BHA 2 | 2J | Slide Drill f/4614.00 t/4628.00, TF -62.52G, w/WOB 8.69,Flow 818.30, Press 3736.94, Tq 0, ROP 168.00, Diff 54.74, Temp 158.00
10/17/2021 | 17:14 | 17:20 | 0.1 | 4628 | 4693 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/4628.00 t/4693.00, w/WOB 25.47,Flow 818.33, RPM 80.18, Press 3978.55, Tq 8.44, ROP 650.00, Diff 192.21, Temp 158.00
10/17/2021 | 17:20 | 17:23 | 0.05 | 4693 | 4693 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 17:23 | 17:32 | 0.15 | 4693 | 4787 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4693.00 t/4787.00, w/WOB 23.95,Flow 818.41, RPM 80.17, Press 3996.79, Tq 8.41, ROP 626.67, Diff 85.66, Temp 159.80
10/17/2021 | 17:32 | 17:35 | 0.05 | 4787 | 4787 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 17:35 | 17:44 | 0.15 | 4787 | 4882 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4787.00 t/4882.00, w/WOB 26,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 633.33, Diff 215.53, Temp 161.60
10/17/2021 | 17:44 | 17:47 | 0.05 | 4882 | 4882 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 17:47 | 17:57 | 0.17 | 4882 | 4976 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4882.00 t/4976.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 564.00, Diff 215.53, Temp 161.60
10/17/2021 | 17:57 | 18:00 | 0.05 | 4976 | 4976 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 18:00 | 18:10 | 0.17 | 4976 | 5059 | 83 | INT | 2: BHA 2 | 2K | Rotary Drill f/4976.00 t/5059.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 498.00, Diff 215.53, Temp 161.60
10/17/2021 | 18:10 | 18:13 | 0.05 | 5059 | 5059 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 18:13 | 18:23 | 0.17 | 5059 | 5084 | 25 | INT | 2: BHA 2 | 2J | Slide Drill f/5059.00 t/5084.00, TF 0.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 150.00, Diff 215.53, Temp 161.60
10/17/2021 | 18:23 | 18:33 | 0.17 | 5084 | 5162 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/5084.00 t/5162.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 468.00, Diff 215.53, Temp 161.60
10/17/2021 | 18:33 | 18:36 | 0.05 | 5162 | 5162 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 18:36 | 18:48 | 0.2 | 5162 | 5256 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5162.00 t/5256.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 470.00, Diff 215.53, Temp 161.60
10/17/2021 | 18:48 | 18:51 | 0.05 | 5256 | 5256 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 18:51 | 19:03 | 0.2 | 5256 | 5350 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5256.00 t/5350.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 470.00, Diff 215.53, Temp 161.60
10/17/2021 | 19:03 | 19:05 | 0.03 | 5350 | 5350 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 19:05 | 19:19 | 0.23 | 5350 | 5444 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5350.00 t/5444.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 402.86, Diff 215.53, Temp 167.00
10/17/2021 | 19:19 | 19:22 | 0.05 | 5444 | 5444 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 19:22 | 19:39 | 0.28 | 5444 | 5537 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5444.00 t/5537.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 328.24, Diff 215.53, Temp 167.00
10/17/2021 | 19:39 | 19:42 | 0.05 | 5537 | 5537 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 19:42 | 19:52 | 0.17 | 5537 | 5557 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/5537.00 t/5557.00, TF 0.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 120.00, Diff 215.53, Temp 167.00
10/17/2021 | 19:52 | 20:06 | 0.23 | 5557 | 5631 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/5557.00 t/5631.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 317.14, Diff 215.53, Temp 167.00
10/17/2021 | 20:06 | 20:09 | 0.05 | 5631 | 5631 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 20:09 | 20:21 | 0.2 | 5631 | 5724 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5631.00 t/5724.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 465.00, Diff 215.53, Temp 167.00
10/17/2021 | 20:21 | 20:23 | 0.03 | 5724 | 5724 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 20:23 | 20:31 | 0.13 | 5724 | 5739 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5724.00 t/5739.00, TF 0.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 112.50, Diff 215.53, Temp 178.00
10/17/2021 | 20:31 | 20:47 | 0.27 | 5739 | 5818 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5739.00 t/5818.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 296.25, Diff 215.53, Temp 178.00
10/17/2021 | 20:47 | 20:50 | 0.05 | 5818 | 5818 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 20:50 | 21:04 | 0.23 | 5818 | 5912 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5818.00 t/5912.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 402.86, Diff 215.53, Temp 178.00
10/17/2021 | 21:04 | 21:07 | 0.05 | 5912 | 5912 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 21:07 | 21:20 | 0.22 | 5912 | 6005 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5912.00 t/6005.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 429.23, Diff 215.53, Temp 178.00
10/17/2021 | 21:20 | 21:23 | 0.05 | 6005 | 6005 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 21:23 | 21:36 | 0.22 | 6005 | 6099 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6005.00 t/6099.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 433.85, Diff 215.53, Temp 178.00
10/17/2021 | 21:36 | 21:39 | 0.05 | 6099 | 6099 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 21:39 | 21:53 | 0.23 | 6099 | 6192 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6099.00 t/6192.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 398.57, Diff 215.53, Temp 178.00
10/17/2021 | 21:53 | 21:56 | 0.05 | 6192 | 6192 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 21:56 | 22:05 | 0.15 | 6192 | 6207 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6192.00 t/6207.00, TF 0.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 100.00, Diff 215.53, Temp 178.00
10/17/2021 | 22:05 | 22:20 | 0.25 | 6207 | 6286 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/6207.00 t/6286.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 316.00, Diff 215.53, Temp 178.00
10/17/2021 | 22:20 | 22:23 | 0.05 | 6286 | 6286 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 22:23 | 22:36 | 0.22 | 6286 | 6380 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6286.00 t/6380.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 433.85, Diff 215.53, Temp 187.00
10/17/2021 | 22:36 | 22:39 | 0.05 | 6380 | 6380 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 22:39 | 22:55 | 0.27 | 6380 | 6474 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6380.00 t/6474.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 352.50, Diff 215.53, Temp 187.00
10/17/2021 | 22:55 | 22:58 | 0.05 | 6474 | 6474 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 22:58 | 23:13 | 0.25 | 6474 | 6567 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6474.00 t/6567.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 372.00, Diff 215.53, Temp 187.00
10/17/2021 | 23:13 | 23:16 | 0.05 | 6567 | 6567 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 23:16 | 23:29 | 0.22 | 6567 | 6661 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6567.00 t/6661.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 433.85, Diff 215.53, Temp 187.00
10/17/2021 | 23:29 | 23:32 | 0.05 | 6661 | 6661 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/17/2021 | 23:32 | 24:00 | 0.47 | 6661 | 6676 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6661.00 t/6676.00, TF -40.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 32.14, Diff 215.53, Temp 187.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_18_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/18/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7400 |  |  | Well Cost($): |  | 51340
|  |  |  | 24hr Summary: |  | P/U BHA and drill intermediate
|  |  |  | 24hr Lookahead: |  | Drill to KOP and build curve
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 6676 |  | 3020 |  | Csg Shoe MD(Usft): |  | 3009 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 9789 |  | 9789 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  | 3113 |  | 6769 |  | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): |  | 586 |  | 738 | [5 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 2527 |  | 6031 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: |  | 22.10 / 1.90 |  | 31.30 / 4.97 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: |  | 14.83 |  | 16.33 |  | SN: |  | 56410 |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 7.27 |  | 14.97 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 347.75 / 39.51 |  | 402.96 / 45.18 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 38.5 |  | Grade In: |  | New
% Slide: |  | 18.82 |  | 10.9 |  | Grade Out:
% Rotary: |  | 81.18 |  | 89.1 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 250 |  | 1 |  | 1
7/8 5.9 2.0 TS HPW .001 |  |  |  | 8 | 2 |  |  | 131.75 |  | 37.95 |  | 38.95
Pony NMDC |  |  |  | 8 | 3.25 |  |  | 153.76 |  | 9.43 |  | 48.38
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.63 |  | 52.01
NMDC |  |  |  | 7.938 | 3.25 |  |  | 148.66 |  | 30.27 |  | 82.28
NMDC |  |  |  | 7.875 | 3.25 |  |  | 150 |  | 30 |  | 112.28
Crossover Sub |  |  |  | 7.875 | 3.25 |  |  | 119.05 |  | 3.36 |  | 115.64
6 Jts 6 1/2 DC |  |  |  | 6.5 | 2.75 |  |  | 95 |  | 186.2 |  | 301.84
Crossover Sub |  |  |  | 6.688 | 2.875 |  |  | 78.12 |  | 3.52 |  | 305.36
11 Jts - HWDP |  |  |  | 5 | 3.8 |  |  | 43 |  | 334.06 |  | 639.42
22 Stds 5 DP |  |  |  | 5 | 3.8 |  |  | 19.9 |  | 2062.46 |  | 2701.88
Agitator |  |  |  | 6.75 | 2.5 |  |  | 81.1 |  | 24.66 |  | 2726.54
2726.54
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800035 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.97 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
6690 | 17.66 | 272.79 | 6469.57 | -2.9 | -1480.7 | 0.44 |  | -56.27 | -646.96 | 0.25 |  | -1.2 | 93
6783 | 17.65 | 273.46 | 6558.19 | -1.36 | -1508.86 | 0.22 |  | 93.14 | -660.69 | -0.01 |  | 0.72 | 93
6878 | 16.3 | 273.53 | 6649.05 | 0.33 | -1536.54 | 1.42 |  | 179.17 | -674.36 | -1.42 |  | 0.07 | 95
6971 | 15.94 | 271.26 | 6738.4 | 1.42 | -1562.34 | 0.78 |  | -120.82 | -686.65 | -0.39 |  | -2.44 | 93
7065 | 15.17 | 271.34 | 6828.95 | 1.99 | -1587.54 | 0.82 |  | 178.44 | -698.22 | -0.82 |  | 0.09 | 94
7159 | 14.23 | 266.29 | 6919.88 | 1.53 | -1611.36 | 1.69 |  | -128.69 | -708.25 | -1 |  | -5.37 | 94
7253 | 12.95 | 266.63 | 7011.24 | 0.16 | -1633.41 | 1.36 |  | 176.59 | -716.7 | -1.36 |  | 0.36 | 94
7347 | 12.44 | 270.19 | 7102.95 | -0.42 | -1654.05 | 0.99 |  | 124.83 | -725.22 | -0.54 |  | 3.79 | 94
7440 | 11.62 | 276.56 | 7193.91 | 0.68 | -1673.37 | 1.68 |  | 124.79 | -734.69 | -0.88 |  | 6.85 | 93
7533 | 11.82 | 277.5 | 7284.97 | 2.99 | -1692.12 | 0.3 |  | 44.13 | -745 | 0.22 |  | 1.01 | 93
7627 | 13.01 | 279 | 7376.77 | 5.9 | -1712.12 | 1.31 |  | 15.9 | -756.38 | 1.27 |  | 1.6 | 94
7720 | 12.45 | 278.94 | 7467.48 | 9.1 | -1732.36 | 0.6 |  | -178.68 | -768.14 | -0.6 |  | -0.06 | 93
7811 | 11.06 | 282.31 | 7556.57 | 12.48 | -1750.58 | 1.7 |  | 155.36 | -779.17 | -1.53 |  | 3.7 | 91
7904 | 10.93 | 279.07 | 7647.87 | 15.78 | -1768 | 0.68 |  | -103.47 | -789.77 | -0.14 |  | -3.48 | 93
7998 | 10.67 | 278.23 | 7740.2 | 18.43 | -1785.41 | 0.32 |  | -149.22 | -799.79 | -0.28 |  | -0.89 | 94
8092 | 11.12 | 273.51 | 7832.51 | 20.23 | -1803.07 | 1.06 |  | -65.56 | -809.16 | 0.48 |  | -5.02 | 94
8186 | 11.19 | 272.9 | 7924.73 | 21.24 | -1821.23 | 0.15 |  | -59.62 | -818.04 | 0.07 |  | -0.65 | 94
8279 | 10.76 | 276.46 | 8016.03 | 22.68 | -1838.87 | 0.86 |  | 124.13 | -827.06 | -0.46 |  | 3.83 | 93
8372 | 10.58 | 272.33 | 8107.43 | 24 | -1856.03 | 0.84 |  | -105.27 | -835.78 | -0.19 |  | -4.44 | 93
8467 | 10.01 | 260.87 | 8200.91 | 23.05 | -1872.89 | 2.23 |  | -111.14 | -842.32 | -0.6 |  | -12.06 | 95
8561 | 7.96 | 253.13 | 8293.75 | 19.86 | -1887.19 | 2.53 |  | -153.26 | -845.73 | -2.18 |  | -8.23 | 94
8654 | 5.25 | 249.63 | 8386.13 | 16.51 | -1897.34 | 2.94 |  | -173.29 | -847.17 | -2.91 |  | -3.76 | 93
8748 | 4.17 | 253.43 | 8479.81 | 14.04 | -1904.65 | 1.2 |  | 165.77 | -848.16 | -1.15 |  | 4.04 | 94
8841 | 3.7 | 254.2 | 8572.59 | 12.26 | -1910.78 | 0.51 |  | 173.97 | -849.24 | -0.51 |  | 0.83 | 93
8936 | 2.44 | 253.87 | 8667.45 | 10.86 | -1915.67 | 1.33 |  | -179.36 | -850.14 | -1.33 |  | -0.35 | 95
9029 | 2.11 | 243.5 | 8760.38 | 9.55 | -1919.11 | 0.57 |  | -133.82 | -850.46 | -0.35 |  | -11.15 | 93
9123 | 2.24 | 251.17 | 8854.31 | 8.18 | -1922.39 | 0.34 |  | 69.8 | -850.68 | 0.14 |  | 8.16 | 94
9217 | 1.69 | 247.14 | 8948.25 | 7.05 | -1925.41 | 0.6 |  | -167.9 | -850.98 | -0.59 |  | -4.29 | 94
9311 | 1.83 | 244.67 | 9042.21 | 5.87 | -1928.04 | 0.17 |  | -29.69 | -851.08 | 0.15 |  | -2.63 | 94
9404 | 1.96 | 266.72 | 9135.16 | 5.14 | -1930.97 | 0.79 |  | 91.03 | -851.71 | 0.14 |  | 23.71 | 93
9498 | 4.84 | 200.49 | 9229.01 | 1.33 | -1933.97 | 4.71 |  | -90.07 | -849.6 | 3.06 |  | -70.46 | 94
9591 | 10.11 | 187.12 | 9321.2 | -10.45 | -1936.35 | 5.93 |  | -24.98 | -840.06 | 5.67 |  | -14.38 | 93
9686 | 14.15 | 181.49 | 9414.06 | -30.34 | -1937.69 | 4.43 |  | -19.09 | -822.77 | 4.25 |  | -5.93 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 213.25 | 26.25 | 80.22 | 210 | 778.88 | 4266.98 | 3858.45 | 0 | 214.49 | 195.11 | 173.35 | 12.91 | 0
Run | 287.77 | 24.29 | 78.08 | 209 | 789.19 | 3994.49 | 3674.55 | 0 | 184.38 | 170.33 | 155.28 | 9.23 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/18/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/18/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/18/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 7400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/18/2021 | 00:00 | 00:10 | 0.17 | 6676 | 6754 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/6676.00 t/6754.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 468.00, Diff 215.53, Temp 190.00
10/18/2021 | 00:10 | 00:13 | 0.05 | 6754 | 6754 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 00:13 | 00:27 | 0.23 | 6754 | 6847 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6754.00 t/6847.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 398.57, Diff 215.53, Temp 190.00
10/18/2021 | 00:27 | 00:30 | 0.05 | 6847 | 6847 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 00:30 | 00:43 | 0.22 | 6847 | 6942 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6847.00 t/6942.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 438.46, Diff 215.53, Temp 190.00
10/18/2021 | 00:43 | 00:46 | 0.05 | 6942 | 6942 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 00:46 | 01:06 | 0.33 | 6942 | 6957 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6942.00 t/6957.00, TF -60.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 45.00, Diff 215.53, Temp 190.00
10/18/2021 | 01:06 | 01:19 | 0.22 | 6957 | 7035 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/6957.00 t/7035.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 360.00, Diff 215.53, Temp 194.00
10/18/2021 | 01:19 | 01:22 | 0.05 | 7035 | 7035 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 01:22 | 01:36 | 0.23 | 7035 | 7129 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7035.00 t/7129.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 402.86, Diff 215.53, Temp 194.00
10/18/2021 | 01:36 | 01:39 | 0.05 | 7129 | 7129 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 01:39 | 01:55 | 0.27 | 7129 | 7144 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7129.00 t/7144.00, TF -60.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 56.25, Diff 215.53, Temp 194.00
10/18/2021 | 01:55 | 02:10 | 0.25 | 7144 | 7223 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/7144.00 t/7223.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 316.00, Diff 215.53, Temp 199.00
10/18/2021 | 02:10 | 02:13 | 0.05 | 7223 | 7223 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 02:13 | 02:28 | 0.25 | 7223 | 7317 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7223.00 t/7317.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 376.00, Diff 215.53, Temp 199.00
10/18/2021 | 02:28 | 02:31 | 0.05 | 7317 | 7317 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 02:31 | 02:48 | 0.28 | 7317 | 7332 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7317.00 t/7332.00, TF -30.00G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 52.94, Diff 215.53, Temp 199.00
10/18/2021 | 02:48 | 03:02 | 0.23 | 7332 | 7411 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/7332.00 t/7411.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 338.57, Diff 215.53, Temp 201.00
10/18/2021 | 03:02 | 03:05 | 0.05 | 7411 | 7411 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 03:05 | 03:21 | 0.27 | 7411 | 7504 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7411.00 t/7504.00, w/WOB 26.00,Flow 818.40, RPM 80.18, Press 3926.66, Tq 6.71, ROP 348.75, Diff 215.53, Temp 201.00
10/18/2021 | 03:21 | 03:24 | 0.05 | 7504 | 7504 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 03:24 | 03:39 | 0.25 | 7504 | 7519 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7504.00 t/7519.00, TF -30G, w/WOB 26.00,Flow 818.40, Press 3926.66, Tq 6.71, ROP 60.00, Diff 215.53, Temp 203.00
10/18/2021 | 03:39 | 03:51 | 0.2 | 7519 | 7597 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/7519.00 t/7597.00, w/WOB 30,Flow 818.40, RPM 80.18, Press 4700, Tq 15, ROP 390.00, Diff 600.00, Temp 203.00
10/18/2021 | 03:51 | 03:54 | 0.05 | 7597 | 7597 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 03:54 | 04:10 | 0.27 | 7597 | 7612 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7597.00 t/7612.00, TF -30.00G, w/WOB 30.00,Flow 818.40, Press 4700.00, Tq 15.00, ROP 56.25, Diff 600.00, Temp 203.00
10/18/2021 | 04:10 | 04:30 | 0.33 | 7612 | 7691 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/7612.00 t/7691.00, w/WOB 30.00,Flow 818.40, RPM 80.18, Press 4700.00, Tq 15.00, ROP 237.00, Diff 600.00, Temp 203.00
10/18/2021 | 04:30 | 04:33 | 0.05 | 7691 | 7691 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 04:33 | 04:49 | 0.27 | 7691 | 7784 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7691.00 t/7784.00, w/WOB 30.00,Flow 818.40, RPM 80.18, Press 4700.00, Tq 15.00, ROP 348.75, Diff 600.00, Temp 203.00
10/18/2021 | 04:49 | 04:52 | 0.05 | 7784 | 7784 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 04:52 | 05:10 | 0.3 | 7784 | 7875 | 91 | INT | 2: BHA 2 | 2K | Rotary Drill f/7784.00 t/7875.00, w/WOB 30.00,Flow 818.40, RPM 80.18, Press 4700.00, Tq 15.00, ROP 303.33, Diff 600.00, Temp 208.00
10/18/2021 | 05:10 | 05:13 | 0.05 | 7875 | 7875 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 05:13 | 05:33 | 0.33 | 7875 | 7895 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7875.00 t/7895.00, TF -60.00G, w/WOB 30.00,Flow 700.00, Press 3800.00, Tq 15.00, ROP 60.00, Diff 600.00, Temp 208.00
10/18/2021 | 05:33 | 05:47 | 0.23 | 7895 | 7968 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/7895.00 t/7968.00, w/WOB 30.00,Flow 700.00, RPM 80.18, Press 3800.00, Tq 15.00, ROP 312.86, Diff 600.00, Temp 208.00
10/18/2021 | 05:47 | 05:50 | 0.05 | 7968 | 7968 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 05:50 | 05:55 | 0.08 | 7968 | 7989 | 21 | INT | 2: BHA 2 | 2K | Rotary Drill f/7968.00 t/7989.00, w/WOB 30.00,Flow 700.00, RPM 80.18, Press 3800.00, Tq 15.00, ROP 252.00, Diff 600.00, Temp 208.00
10/18/2021 | 05:55 | 06:14 | 0.32 | 7989 | 8009 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7989.00 t/8009.00, TF -70.00G, w/WOB 15.00,Flow 700.00, Press 3800.00, Tq 0.00, ROP 63.16, Diff 600.00, Temp 208.00
10/18/2021 | 06:14 | 06:23 | 0.15 | 8009 | 8062 | 53 | INT | 2: BHA 2 | 2K | Rotary Drill f/8009.00 t/8062.00, w/WOB 32.00,Flow 700.00, RPM 80.18, Press 3800.00, Tq 15.00, ROP 353.33, Diff 600.00, Temp 208.00
10/18/2021 | 06:23 | 06:26 | 0.05 | 8062 | 8062 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 06:26 | 06:30 | 0.07 | 8062 | 8072 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/8062.00 t/8072.00, w/WOB 30.00,Flow 810.00, RPM 80.18, Press 4600.00, Tq 15.00, ROP 150.00, Diff 400.00, Temp 208.00
10/18/2021 | 06:30 | 06:41 | 0.18 | 8072 | 8087 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8072.00 t/8087.00, TF -80.00G, w/WOB 12.00,Flow 810.00, Press 4400.00, Tq 0.00, ROP 81.82, Diff 200.00, Temp 208.00
10/18/2021 | 06:41 | 06:50 | 0.15 | 8087 | 8156 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/8087.00 t/8156.00, w/WOB 36.95,Flow 806.91, RPM 80.12, Press 4747.77, Tq 14.62, ROP 460.00, Diff 501.62, Temp 206.60
10/18/2021 | 06:50 | 06:53 | 0.05 | 8156 | 8156 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 06:53 | 07:02 | 0.15 | 8156 | 8250 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8156.00 t/8250.00, w/WOB 31.64,Flow 807.17, RPM 80.18, Press 4723.24, Tq 14.07, ROP 626.67, Diff 477.09, Temp 210.20
10/18/2021 | 07:02 | 07:06 | 0.07 | 8250 | 8250 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 07:06 | 07:20 | 0.23 | 8250 | 8343 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8250.00 t/8343.00, w/WOB 39.22,Flow 806.86, RPM 79.36, Press 4900.11, Tq 16.80, ROP 398.57, Diff 583.27, Temp 213.80
10/18/2021 | 07:20 | 07:25 | 0.08 | 8343 | 8343 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 07:25 | 07:40 | 0.25 | 8343 | 8363 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8343.00 t/8363.00, TF -84.17G, w/WOB 11.55,Flow 807.78, Press 4440.33, Tq 0.00, ROP 80.00, Diff 69.85, Temp 212.00
10/18/2021 | 07:40 | 07:51 | 0.18 | 8363 | 8436 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/8363.00 t/8436.00, w/WOB 25.97,Flow 807.14, RPM 80.43, Press 4790.29, Tq 14.88, ROP 398.18, Diff 502.60, Temp 213.80
10/18/2021 | 07:51 | 07:59 | 0.13 | 8436 | 8436 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 07:59 | 08:04 | 0.08 | 8436 | 8446 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/8436.00 t/8446.00, w/WOB 13.98,Flow 685.28, RPM 80.58, Press 3571.55, Tq 11.99, ROP 120.00, Diff 247.34, Temp 213.80
10/18/2021 | 08:04 | 08:21 | 0.28 | 8446 | 8466 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8446.00 t/8466.00, TF -122.83G, w/WOB 8.28,Flow 687.25, Press 3399.63, Tq 0.00, ROP 70.59, Diff 105.14, Temp 212.00
10/18/2021 | 08:21 | 08:32 | 0.18 | 8466 | 8531 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/8466.00 t/8531.00, w/WOB 32.35,Flow 684.99, RPM 80.38, Press 3704.18, Tq 14.56, ROP 354.55, Diff 396.99, Temp 212.00
10/18/2021 | 08:32 | 08:35 | 0.05 | 8531 | 8531 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 08:35 | 08:39 | 0.07 | 8531 | 8541 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/8531.00 t/8541.00, w/WOB 14.37,Flow 685.59, RPM 80.46, Press 3699.97, Tq 12.34, ROP 150.00, Diff 398.58, Temp 212.00
10/18/2021 | 08:39 | 08:50 | 0.18 | 8541 | 8556 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8541.00 t/8556.00, TF 173.68G, w/WOB 16.10,Flow 685.50, Press 3416.97, Tq 0.00, ROP 81.82, Diff 106.09, Temp 212.00
10/18/2021 | 08:50 | 09:01 | 0.18 | 8556 | 8625 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/8556.00 t/8625.00, w/WOB 34.95,Flow 685.34, RPM 80.33, Press 3775.25, Tq 14.32, ROP 376.36, Diff 869.47, Temp 212.00
10/18/2021 | 09:01 | 09:04 | 0.05 | 8625 | 8625 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 09:04 | 09:08 | 0.07 | 8625 | 8635 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/8625.00 t/8635.00, w/WOB 21.56,Flow 798.05, RPM 80.51, Press 4718.33, Tq 12.18, ROP 150.00, Diff 355.37, Temp 212.00
10/18/2021 | 09:08 | 09:17 | 0.15 | 8635 | 8647 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/8635.00 t/8647.00, TF 163.22G, w/WOB 13.08,Flow 798.49, Press 4475.12, Tq 0.00, ROP 80.00, Diff 137.29, Temp 212.00
10/18/2021 | 09:17 | 09:29 | 0.2 | 8647 | 8718 | 71 | INT | 2: BHA 2 | 2K | Rotary Drill f/8647.00 t/8718.00, w/WOB 31.59,Flow 797.38, RPM 80.38, Press 4767.64, Tq 15.14, ROP 355.00, Diff 424.82, Temp 213.80
10/18/2021 | 09:29 | 09:32 | 0.05 | 8718 | 8718 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 09:32 | 09:44 | 0.2 | 8718 | 8812 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8718.00 t/8812.00, w/WOB 34.10,Flow 797.57, RPM 80.16, Press 4863.29, Tq 15.84, ROP 470.00, Diff 482.52, Temp 215.60
10/18/2021 | 09:44 | 09:47 | 0.05 | 8812 | 8812 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 09:47 | 09:58 | 0.18 | 8812 | 8905 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8812.00 t/8905.00, w/WOB 37.97,Flow 797.58, RPM 80.12, Press 4981.27, Tq 17.19, ROP 507.27, Diff 663.42, Temp 219.20
10/18/2021 | 09:58 | 10:01 | 0.05 | 8905 | 8905 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 10:01 | 10:14 | 0.22 | 8905 | 9000 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8905.00 t/9000.00, w/WOB 34.33,Flow 797.48, RPM 80.39, Press 4903.33, Tq 16.06, ROP 438.46, Diff 601.10, Temp 221.00
10/18/2021 | 10:14 | 10:17 | 0.05 | 9000 | 9000 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 10:17 | 10:42 | 0.42 | 9000 | 9093 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9000.00 t/9093.00, w/WOB 35.58,Flow 694.66, RPM 80.04, Press 4156.10, Tq 16.65, ROP 223.20, Diff 702.34, Temp 224.60
10/18/2021 | 10:42 | 10:45 | 0.05 | 9093 | 9093 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 10:45 | 11:09 | 0.4 | 9093 | 9187 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9093.00 t/9187.00, w/WOB 27.87,Flow 695.50, RPM 80.07, Press 4087.08, Tq 15.78, ROP 235.00, Diff 488.54, Temp 224.60
10/18/2021 | 11:09 | 11:13 | 0.07 | 9187 | 9187 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 11:13 | 11:30 | 0.28 | 9187 | 9281 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9187.00 t/9281.00, w/WOB 36.14,Flow 797.54, RPM 80.35, Press 5037.23, Tq 15.74, ROP 331.76, Diff 735.00, Temp 224.60
10/18/2021 | 11:30 | 11:33 | 0.05 | 9281 | 9281 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 11:33 | 11:46 | 0.22 | 9281 | 9375 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9281.00 t/9375.00, w/WOB 30.91,Flow 797.51, RPM 80.33, Press 5138.35, Tq 16.59, ROP 433.85, Diff 736.12, Temp 226.40
10/18/2021 | 11:46 | 11:55 | 0.15 | 9375 | 9400 | 25 | INT | 2: BHA 2 | 2K | Rotary Drill f/9375.00 t/9400.00, w/WOB 30.91,Flow 797.51, RPM 80.33, Press 5138.35, Tq 16.59, ROP 166.67, Diff 736.12, Temp 226.40
10/18/2021 | 11:55 | 12:50 | 0.92 | 9400 | 9468 | 68 | INT | 2: BHA 2 | 2J | Slide Drill f/9400.00 t/9468.00, TF 155M, w/WOB 10,Flow 797.51, Press 4550, Tq 0, ROP 74.18, Diff 147.77, Temp 226.40
10/18/2021 | 12:50 | 12:55 | 0.08 | 9468 | 9468 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 12:55 | 15:10 | 2.25 | 9468 | 9562 | 94 | INT | 2: BHA 2 | 2J | Slide Drill f/9468.00 t/9562.00, TF 150M, w/WOB 10,Flow 797.51, Press 4550, Tq 0, ROP 41.78, Diff 147.77, Temp 226.40
10/18/2021 | 15:10 | 15:16 | 0.1 | 9562 | 9562 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 15:16 | 19:25 | 4.15 | 9562 | 9655 | 93 | INT | 2: BHA 2 | 2J | Slide Drill f/9562.00 t/9655.00, TF -60.00G, w/WOB 10.00,Flow 797.51, Press 4550.00, Tq 0.00, ROP 22.41, Diff 147.77, Temp 226.40
10/18/2021 | 19:25 | 19:30 | 0.08 | 9655 | 9655 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 19:30 | 22:42 | 3.2 | 9655 | 9750 | 95 | INT | 2: BHA 2 | 2J | Slide Drill f/9655.00 t/9750.00, TF -60.00G, w/WOB 20.00,Flow 797.51, Press 4550.00, Tq 0.00, ROP 29.69, Diff 147.77, Temp 230.00
10/18/2021 | 22:42 | 22:47 | 0.08 | 9750 | 9750 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/18/2021 | 22:47 | 24:00 | 1.22 | 9750 | 9789 | 39 | INT | 2: BHA 2 | 2J | Slide Drill f/9750.00 t/9789.00, TF -60.00G, w/WOB 20.00,Flow 797.51, Press 4550.00, Tq 0.00, ROP 32.05, Diff 147.77, Temp 230.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_19_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7400 |  |  | Well Cost($): |  | 58740
|  |  |  | 24hr Summary: |  | TD curve @ 9928
|  |  |  | 24hr Lookahead: |  | L/D DP and run casing
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9789 |  | 3020 |  | Csg Shoe MD(Usft): |  | 3009 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 9928 |  | 9928 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  | 139 |  | 6908 |  | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): |  | 134 |  | 872 | [5 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 5 |  | 6036 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: |  | 3.85 / 1.65 |  | 35.15 / 6.62 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: |  | 3.78 |  | 20.12 |  | SN: |  | 56410 |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 0.07 |  | 15.03 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 75.00 / 35.42 |  | 401.51 / 43.35 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 17.75 |  | 56.25 |  | Grade In: |  | New
% Slide: |  | 96.4 |  | 12.62 |  | Grade Out:
% Rotary: |  | 3.6 |  | 87.38 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 250 |  | 1 |  | 1
7/8 5.9 2.0 TS HPW .001 |  |  |  | 8 | 2 |  |  | 131.75 |  | 37.95 |  | 38.95
Pony NMDC |  |  |  | 8 | 3.25 |  |  | 153.76 |  | 9.43 |  | 48.38
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.63 |  | 52.01
NMDC |  |  |  | 7.938 | 3.25 |  |  | 148.66 |  | 30.27 |  | 82.28
NMDC |  |  |  | 7.875 | 3.25 |  |  | 150 |  | 30 |  | 112.28
Crossover Sub |  |  |  | 7.875 | 3.25 |  |  | 119.05 |  | 3.36 |  | 115.64
6 Jts 6 1/2 DC |  |  |  | 6.5 | 2.75 |  |  | 95 |  | 186.2 |  | 301.84
Crossover Sub |  |  |  | 6.688 | 2.875 |  |  | 78.12 |  | 3.52 |  | 305.36
11 Jts - HWDP |  |  |  | 5 | 3.8 |  |  | 43 |  | 334.06 |  | 639.42
22 Stds 5 DP |  |  |  | 5 | 3.8 |  |  | 19.9 |  | 2062.46 |  | 2701.88
Agitator |  |  |  | 6.75 | 2.5 |  |  | 81.1 |  | 24.66 |  | 2726.54
2726.54
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800035 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.97 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9779 | 17.86 | 175.99 | 9503.44 | -55.94 | -1936.99 | 4.31 |  | -24.9 | -799.46 | 3.99 |  | -5.91 | 93
9859 | 21.15 | 166.02 | 9578.86 | -82.2 | -1932.64 | 5.84 |  | -50.12 | -773.95 | 4.11 |  | -12.46 | 80
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 36.1 | 26.25 | 80.22 | 210 | 778.88 | 4266.98 | 3858.45 | 0 | 214.49 | 195.11 | 173.35 | 12.91 | 0
Run | 196.53 | 24.29 | 78.08 | 209 | 789.19 | 3994.49 | 3674.55 | 0 | 184.38 | 170.33 | 155.28 | 9.23 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/19/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/19/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/19/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 7400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/19/2021 | 00:00 | 01:19 | 1.32 | 9789 | 9843 | 54 | INT | 2: BHA 2 | 2J | Slide Drill f/9789.00 t/9843.00, TF -60.00G, w/WOB 25.00,Flow 797.51, Press 4550.00, Tq 0.00, ROP 41.01, Diff 147.77, Temp 236.00
10/19/2021 | 01:19 | 01:24 | 0.08 | 9843 | 9843 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
10/19/2021 | 01:24 | 03:52 | 2.47 | 9843 | 9923 | 80 | INT | 2: BHA 2 | 2J | Slide Drill f/9843.00 t/9923.00, TF -60G, w/WOB 30,Flow 797.51, Press 4550.00, Tq 0.00, ROP 32.43, Diff 147.77, Temp 244.00
10/19/2021 | 03:52 | 03:56 | 0.07 | 9923 | 9928 | 5 | INT | 2: BHA 2 | 2K | Rotary Drill f/9923.00 t/9928.00, w/WOB 20,Flow 797.51, RPM 30, Press 4550.00, Tq 10, ROP 75.00, Diff 147.77, Temp 244.00
10/19/2021 | 03:56 | 05:30 | 1.57 | 9928 | 9928 | 0 | INT | 2: BHA 2 | 5A | Circulate
10/19/2021 | 05:30 | 16:00 | 10.5 | 9928 | 9928 | 0 | INT | 2: BHA 2 | 6B | POOH L/D 5 Drill Pipe
10/19/2021 | 16:00 | 17:45 | 1.75 | 9928 | 9928 | 0 | INT | 2: BHA 2 | 6P | L/D BHA #2
10/19/2021 | 17:45 | 18:30 | 0.75 | 9928 | 9928 | 0 | INT |  | 7B | Clean Rig Floor
10/19/2021 | 18:30 | 20:00 | 1.5 | 9928 | 9928 | 0 | INT |  | 14G | Change Rams tO 7 5/8 rAMs Test Same 1500psi
10/19/2021 | 20:00 | 21:00 | 1 | 9928 | 9928 | 0 | INT |  | 12A | Safety Meeting , R/U Casing Tools
10/19/2021 | 21:00 | 21:30 | 0.5 | 9928 | 9928 | 0 | INT |  | 24A | M/U Shoe Track Test Shoe Track
10/19/2021 | 21:30 | 24:00 | 2.5 | 9928 | 9928 | 0 | INT |  | 12B | Run Casing Same
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_20_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4350 |  |  | Well Cost($): |  | 63090
|  |  |  | 24hr Summary: |  | Layed Down 5 DP & BHA #2
|  |  |  | 24hr Lookahead: |  | Run Casing / Cement Casing
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9928 |  |  |  | Csg Shoe MD(Usft): |  | 3009 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 9928 |  | 9928 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma (Standby) |  |  |  |  | 10/20/2021 |  | 4 |  | 4350 |  | 1 | 4350
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/20/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/20/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 4350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/20/2021 | 00:00 | 07:00 | 7 | 9928 | 9928 | 0 | INT |  | 24B | Run Casing
10/20/2021 | 07:00 | 10:45 | 3.75 | 9928 | 9928 | 0 | INT |  | 24B | Circulate B/U
10/20/2021 | 10:45 | 13:45 | 3 | 9928 | 9928 | 0 | INT |  | 24B | Cement Casing Same
10/20/2021 | 13:45 | 22:30 | 8.75 | 9928 | 9928 | 0 | INT |  | 24B | Wait on Cement/Bleed off psi/R/D Casing Equipment,M/u Pack off set same /test same over pull 25k/R/D setting tool
10/20/2021 | 22:30 | 24:00 | 1.5 | 9928 | 9928 | 0 | INT |  | 24B | R/U Change Ram BOPs
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_21_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/21/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19000 |  |  | Well Cost($): |  | 82090
|  |  |  | 24hr Summary: |  | Run Casing/Cement Same/Test BOPs
|  |  |  | 24hr Lookahead: |  | P/U BHA #3 TIH P/U 4 DP TIH W/ Same
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9928 |  | 9928 |  | Csg Shoe MD(Usft): |  | 3009 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 9928 |  | 9928 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: |  | 0.00 / 0.33 |  | 0.00 / 0.33 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: | [5 empty] | SN: |  | 13635755 |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 8.5 |  | 8.5 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 2-3-BT-N-X-I-CT-DMF
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 T/S HS88 -.013 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.39 |  | 34.39
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 36.03
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.62
UHBO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.61
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.38
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 50.66 |  | 5.59 |  | 80.97
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 112.29
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 129.76
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 133.09
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 322.45
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 331.08
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2785.07
Agitator |  |  |  | 5 | 2.5 |  |  | 55.38 |  | 22.01 |  | 2807.08
2807.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250018 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.14 |  | 2.12 |  | 0.89 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/21/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/21/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/21/2021 |  | 7 |  | 100 |  | 4 | 400
5.5 Premium Motor Stator Reline |  |  |  |  | 10/21/2021 |  | 12 |  | 9000 |  | 1 | 9000
Real Time Survey Management |  |  |  |  | 10/21/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 10/21/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 19000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/21/2021 | 00:00 | 02:30 | 2.5 | 9928 | 9928 | 0 | INT |  | 24B | Change Rams BOPs
10/21/2021 | 02:30 | 12:00 | 9.5 | 9928 | 9928 | 0 | INT |  | 24B | Test BOPs
10/21/2021 | 12:00 | 13:00 | 1 | 9928 | 9928 | 0 | INT |  | 8P | Rig Service
10/21/2021 | 13:00 | 14:00 | 1 | 9928 | 9928 | 0 | INT |  | 9A | Slip and Cut Drill line
10/21/2021 | 14:00 | 15:30 | 1.5 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 6O | P/U BHA #3 /Rack Back In Derrick
10/21/2021 | 15:30 | 18:00 | 2.5 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 6J | Pick Up Drill Pipe
10/21/2021 | 18:00 | 20:30 | 2.5 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 15A | Install New Choke line test same
10/21/2021 | 20:30 | 21:30 | 1 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 24A | Remove rotating head install trip nipple/install wear bushing
10/21/2021 | 21:30 | 22:15 | 0.75 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 24A | Make up Bit /install MWD TOOL,M/U Last monel
10/21/2021 | 22:15 | 22:35 | 0.33 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 5A | Test MWD Tool and Motor (Good Test)
10/21/2021 | 22:35 | 24:00 | 1.42 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 6A | TIH Picking up DP
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_22_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/22/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 92090
|  |  |  | 24hr Summary: |  | P/U BHA #3 Test Same /P/U DP TIH
|  |  |  | 24hr Lookahead: |  | Start Curve Land Same Drill and Slide as Needed
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9928 |  | 9928 |  | Csg Shoe MD(Usft): |  | 3009 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 10932 |  | 10932 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  | 1004 |  | 1004 |  | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): |  | 603 |  | 603 | [5 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 401 |  | 401 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: |  | 9.68 / 3.98 |  | 9.68 / 4.32 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: |  | 6 |  | 6 |  | SN: |  | 13635755 |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 3.68 |  | 3.68 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 108.87 / 100.50 |  | 108.87 / 100.50 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 32.5 |  | Grade In: |  | New
% Slide: |  | 60.06 |  | 60.06 |  | Grade Out: |  | 2-3-BT-N-X-I-CT-DMF
% Rotary: |  | 39.94 |  | 39.94 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 T/S HS88 -.013 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.39 |  | 34.39
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 36.03
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.62
UHBO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.61
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.38
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 50.66 |  | 5.59 |  | 80.97
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 112.29
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 129.76
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 133.09
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 322.45
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 331.08
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2785.07
Agitator |  |  |  | 5 | 2.5 |  |  | 55.38 |  | 22.01 |  | 2807.08
2807.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250018 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.14 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10019 | 26.21 | 154.14 | 9725.43 | -142.08 | -1910.23 | 4.33 |  | -48.88 | -710.31 | 3.16 |  | -7.43 | 160
10114 | 36.44 | 144.67 | 9806.52 | -184.11 | -1884.68 | 11.92 |  | -29.84 | -661.33 | 10.77 |  | -9.97 | 95
10209 | 48.38 | 147.42 | 9876.54 | -237.25 | -1849.11 | 12.72 |  | 9.87 | -597.98 | 12.57 |  | 2.89 | 95
10304 | 55.66 | 154.12 | 9935 | -302.59 | -1812.8 | 9.46 |  | 38.07 | -523.33 | 7.66 |  | 7.05 | 95
10398 | 60.92 | 153.06 | 9984.4 | -374.17 | -1777.22 | 5.68 |  | -10.01 | -443.39 | 5.6 |  | -1.13 | 94
10492 | 69.77 | 152.97 | 10023.57 | -450.23 | -1738.49 | 9.42 |  | -0.55 | -358.06 | 9.41 |  | -0.1 | 94
10586 | 78.57 | 155.69 | 10049.19 | -531.67 | -1699.4 | 9.77 |  | 16.95 | -267.72 | 9.36 |  | 2.89 | 94
10680 | 85.36 | 154.17 | 10062.32 | -615.92 | -1659.98 | 7.4 |  | -12.61 | -174.72 | 7.22 |  | -1.62 | 94
10775 | 87.65 | 151.62 | 10068.12 | -700.32 | -1616.78 | 3.6 |  | -48.11 | -79.92 | 2.41 |  | -2.68 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 17.62 | 43.64 | 349 | 342.86 | 3700 | 2857.14 | 0 | 235.71 | 198.33 | 192.86 | 7.5 | 0
Run | 0 | 17.62 | 43.64 | 349 | 342.86 | 3700 | 2857.14 | 0 | 235.71 | 198.33 | 192.86 | 7.5 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/22/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/22/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/22/2021 |  | 7 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 10/22/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 10/22/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/22/2021 | 00:00 | 01:35 | 1.58 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 6A | TIH
10/22/2021 | 01:35 | 01:45 | 0.17 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 5A | Get Presure before and after P/U Agitator 1205psi before/after 1470psi
10/22/2021 | 01:45 | 10:30 | 8.75 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 6A | TIH
10/22/2021 | 10:30 | 12:45 | 2.25 | 9928 | 9928 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 12:45 | 13:13 | 0.47 | 9928 | 9988 | 60 | CRV | 3: BHA 3 | 2J | Slide Drill f/9939.00 t/9988.00, TF -40.00G, w/WOB 25.00,Flow 300.00, Press 3100.00, Tq 0.00, ROP 105.00, Diff 800.00, Temp 224.00
10/22/2021 | 13:13 | 13:23 | 0.17 | 9988 | 9988 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 13:23 | 14:10 | 0.78 | 9988 | 10083 | 95 | CRV | 3: BHA 3 | 2J | Slide Drill f/9988.00 t/10083.00, TF -30.00G, w/WOB 25.00,Flow 300.00, Press 3100.00, Tq 0.00, ROP 121.28, Diff 800.00, Temp 224.00
10/22/2021 | 14:10 | 14:20 | 0.17 | 10083 | 10083 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 14:20 | 15:10 | 0.83 | 10083 | 10178 | 95 | CRV | 3: BHA 3 | 2J | Slide Drill f/10083.00 t/10178.00, TF 0.00G, w/WOB 25.00,Flow 300.00, Press 3100.00, Tq 0.00, ROP 114.00, Diff 800.00, Temp 224.00
10/22/2021 | 15:10 | 15:25 | 0.25 | 10178 | 10178 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 15:25 | 16:00 | 0.58 | 10178 | 10273 | 95 | CRV | 3: BHA 3 | 2J | Slide Drill f/10178.00 t/10273.00, TF 30.00G, w/WOB 30.00,Flow 350.00, Press 3800.00, Tq 0.00, ROP 162.86, Diff 850.00, Temp 228.00
10/22/2021 | 16:00 | 16:10 | 0.17 | 10273 | 10273 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 16:10 | 16:31 | 0.35 | 10273 | 10308 | 35 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10273.00 t/10308.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 100.00, Diff 850.00, Temp 228.00
10/22/2021 | 16:31 | 16:59 | 0.47 | 10308 | 10368 | 60 | CRV | 3: BHA 3 | 2J | Slide Drill f/10308.00 t/10368.00, TF 0.00G, w/WOB 30.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 128.57, Diff 850.00, Temp 228.00
10/22/2021 | 16:59 | 17:09 | 0.17 | 10368 | 10368 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 17:09 | 17:28 | 0.32 | 10368 | 10414 | 46 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10368.00 t/10414.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 145.26, Diff 850.00, Temp 228.00
10/22/2021 | 17:28 | 18:20 | 0.87 | 10414 | 10462 | 48 | CRV | 3: BHA 3 | 2J | Slide Drill f/10414.00 t/10462.00, TF 0.00G, w/WOB 10.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 55.38, Diff 850.00, Temp 228.00
10/22/2021 | 18:20 | 18:30 | 0.17 | 10462 | 10462 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 18:30 | 18:35 | 0.08 | 10462 | 10472 | 10 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10462.00 t/10472.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 120.00, Diff 850.00, Temp 228.00
10/22/2021 | 18:35 | 19:35 | 1 | 10472 | 10556 | 84 | CRV | 3: BHA 3 | 2J | Slide Drill f/10472.00 t/10556.00, TF G, w/WOB 10.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 84.00, Diff 850.00, Temp 228.00
10/22/2021 | 19:35 | 19:42 | 0.12 | 10556 | 10556 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 19:42 | 20:15 | 0.55 | 10556 | 10596 | 40 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10556.00 t/10596.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 72.73, Diff 850.00, Temp 228.00
10/22/2021 | 20:15 | 20:50 | 0.58 | 10596 | 10640 | 44 | CRV | 3: BHA 3 | 2J | Slide Drill f/10596.00 t/10640.00, TF 20.00G, w/WOB 10.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 75.43, Diff 850.00, Temp 228.00
10/22/2021 | 20:50 | 20:55 | 0.08 | 10640 | 10640 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 20:55 | 21:00 | 0.08 | 10640 | 10650 | 10 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10640.00 t/10650.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 120.00, Diff 850.00, Temp 228.00
10/22/2021 | 21:00 | 21:06 | 0.1 | 10650 | 10650 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 21:06 | 21:35 | 0.48 | 10650 | 10690 | 40 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10650.00 t/10690.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 82.76, Diff 850.00, Temp 228.00
10/22/2021 | 21:35 | 21:45 | 0.17 | 10690 | 10702 | 12 | CRV | 3: BHA 3 | 2J | Slide Drill f/10690.00 t/10702.00, TF G, w/WOB 10.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 72.00, Diff 850.00, Temp 228.00
10/22/2021 | 21:45 | 22:00 | 0.25 | 10702 | 10744 | 42 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10702.00 t/10744.00, w/WOB 10.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 168.00, Diff 850.00, Temp 228.00
10/22/2021 | 22:00 | 22:06 | 0.1 | 10744 | 10744 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 22:06 | 22:55 | 0.82 | 10744 | 10839 | 95 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10744.00 t/10839.00, w/WOB 25.00,Flow 350.00, RPM 30.00, Press 3800.00, Tq 7.50, ROP 116.33, Diff 850.00, Temp 235.00
10/22/2021 | 22:55 | 23:00 | 0.08 | 10839 | 10839 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
10/22/2021 | 23:00 | 23:05 | 0.08 | 10839 | 10849 | 10 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10839.00 t/10849.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 120.00, Diff 850.00, Temp 235.00
10/22/2021 | 23:05 | 23:20 | 0.25 | 10849 | 10859 | 10 | CRV | 3: BHA 3 | 2J | Slide Drill f/10849.00 t/10859.00, TF 170.00G, w/WOB 25.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 40.00, Diff 850.00, Temp 239.00
10/22/2021 | 23:20 | 23:50 | 0.5 | 10859 | 10932 | 73 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10859.00 t/10932.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 146.00, Diff 850.00, Temp 239.00
10/22/2021 | 23:50 | 24:00 | 0.17 | 10932 | 10932 | 0 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10932.00 t/10932.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 0.00, Diff 850.00, Temp 239.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_23_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/23/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 102090
|  |  |  | 24hr Summary: |  | Land Curve Rotate Slide As Needed
|  |  |  | 24hr Lookahead: |  | Rotate Slide as Needed
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10932 |  | 9928 |  | Csg Shoe MD(Usft): |  | 9920 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 14150 |  | 14150 |  | OD (in): |  | 7.875 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  | 3218 |  | 4222 |  | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 46
Slide Drilled (Usft): |  | 251 |  | 854 | [5 empty] | 100: | 12 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 2967 |  | 3368 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 9.60
Drlg/Circ Hrs: |  | 20.05 / 3.95 |  | 29.73 / 8.27 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: |  | 5.52 |  | 11.52 |  | SN: |  | 13635755 |  | 10s Gel: | 6 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 14.53 |  | 18.22 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 132.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 204.15 / 45.50 |  | 184.89 / 74.15 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 56.5 |  | Grade In: |  | New
% Slide: |  | 7.8 |  | 20.23 |  | Grade Out: |  | 2-3-BT-N-X-I-CT-DMF
% Rotary: |  | 92.2 |  | 79.77 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 T/S HS88 -.013 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.39 |  | 34.39
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 36.03
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.62
UHBO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.61
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.38
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 50.66 |  | 5.59 |  | 80.97
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 112.29
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 129.76
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 133.09
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 322.45
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 331.08
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2785.07
Agitator |  |  |  | 5 | 2.5 |  |  | 55.38 |  | 22.01 |  | 2807.08
2807.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250018 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.14 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10868 | 85.7 | 151.95 | 10073.51 | -782.12 | -1572.89 | 2.13 |  | 170.42 | 12.85 | -2.1 |  | 0.35 | 93
10963 | 84.17 | 152.81 | 10081.9 | -865.96 | -1529.02 | 1.85 |  | 150.79 | 107.43 | -1.61 |  | 0.91 | 95
11056 | 86.06 | 152.13 | 10089.82 | -948.13 | -1486.19 | 2.16 |  | -19.75 | 200.06 | 2.03 |  | -0.73 | 93
11150 | 86.94 | 151.86 | 10095.55 | -1030.97 | -1442.13 | 0.98 |  | -17.04 | 293.83 | 0.94 |  | -0.29 | 94
11245 | 87.87 | 152.91 | 10099.86 | -1115.06 | -1398.15 | 1.48 |  | 48.46 | 388.69 | 0.98 |  | 1.11 | 95
11339 | 86.23 | 156.09 | 10104.69 | -1199.77 | -1357.74 | 3.8 |  | 117.39 | 482.55 | -1.74 |  | 3.38 | 94
11434 | 85.81 | 156.17 | 10111.29 | -1286.44 | -1319.39 | 0.45 |  | 169.24 | 577.25 | -0.44 |  | 0.08 | 95
11528 | 87.79 | 157.03 | 10116.53 | -1372.57 | -1282.11 | 2.3 |  | 23.47 | 671 | 2.11 |  | 0.91 | 94
11623 | 86.78 | 154.69 | 10121.04 | -1459.15 | -1243.31 | 2.68 |  | -113.42 | 765.83 | -1.06 |  | -2.46 | 95
11718 | 86.5 | 153.27 | 10126.6 | -1544.38 | -1201.71 | 1.52 |  | -101.21 | 860.67 | -0.29 |  | -1.49 | 95
11812 | 86.82 | 152.78 | 10132.08 | -1628.01 | -1159.14 | 0.62 |  | -56.82 | 954.5 | 0.34 |  | -0.52 | 94
11906 | 86.87 | 150.95 | 10137.25 | -1710.77 | -1114.89 | 1.94 |  | -88.48 | 1048.29 | 0.05 |  | -1.95 | 94
12000 | 86.13 | 150.07 | 10142.99 | -1792.44 | -1068.7 | 1.22 |  | -130.14 | 1141.94 | -0.79 |  | -0.94 | 94
12094 | 85.78 | 151.76 | 10149.62 | -1874.38 | -1023.12 | 1.83 |  | 101.79 | 1235.56 | -0.37 |  | 1.8 | 94
12188 | 86.77 | 152.64 | 10155.73 | -1957.35 | -979.37 | 1.41 |  | 41.6 | 1329.32 | 1.05 |  | 0.94 | 94
12283 | 85.98 | 153.61 | 10161.74 | -2041.92 | -936.52 | 1.32 |  | 129.25 | 1424.12 | -0.83 |  | 1.02 | 95
12375 | 86.66 | 153.42 | 10167.64 | -2124.09 | -895.57 | 0.77 |  | -15.59 | 1515.92 | 0.74 |  | -0.21 | 92
12468 | 85.39 | 154.48 | 10174.09 | -2207.44 | -854.83 | 1.78 |  | 140.25 | 1608.7 | -1.37 |  | 1.14 | 93
12563 | 85.54 | 154.91 | 10181.6 | -2293.06 | -814.35 | 0.48 |  | 70.73 | 1703.39 | 0.16 |  | 0.45 | 95
12655 | 86.78 | 155.01 | 10187.76 | -2376.22 | -775.5 | 1.35 |  | 4.6 | 1795.17 | 1.35 |  | 0.11 | 92
12749 | 86.23 | 154.45 | 10193.49 | -2461.07 | -735.45 | 0.83 |  | -134.55 | 1888.99 | -0.59 |  | -0.6 | 94
12843 | 85.28 | 153.98 | 10200.45 | -2545.47 | -694.67 | 1.13 |  | -153.76 | 1982.73 | -1.01 |  | -0.5 | 94
12937 | 86.55 | 154.78 | 10207.15 | -2630.01 | -654.13 | 1.6 |  | 32.17 | 2076.48 | 1.35 |  | 0.85 | 94
13030 | 85.58 | 155.2 | 10213.53 | -2714.09 | -614.91 | 1.14 |  | 156.65 | 2169.25 | -1.04 |  | 0.45 | 93
13124 | 85.67 | 155.19 | 10220.7 | -2799.17 | -575.58 | 0.1 |  | -6.32 | 2262.95 | 0.1 |  | -0.01 | 94
13219 | 86.05 | 155.34 | 10227.56 | -2885.23 | -535.94 | 0.43 |  | 21.5 | 2357.68 | 0.4 |  | 0.16 | 95
13313 | 86.68 | 155.67 | 10233.52 | -2970.6 | -497.04 | 0.76 |  | 27.61 | 2451.46 | 0.67 |  | 0.35 | 94
13408 | 85.14 | 154.72 | 10240.29 | -3056.61 | -457.29 | 1.9 |  | -148.43 | 2546.19 | -1.62 |  | -1 | 95
13502 | 84.89 | 154.46 | 10248.46 | -3141.2 | -417.11 | 0.38 |  | -134 | 2639.83 | -0.27 |  | -0.28 | 94
13596 | 86.42 | 154.63 | 10255.58 | -3225.83 | -376.83 | 1.64 |  | 6.33 | 2733.55 | 1.63 |  | 0.18 | 94
13690 | 88.11 | 154.5 | 10260.07 | -3310.61 | -336.5 | 1.8 |  | -4.4 | 2827.44 | 1.8 |  | -0.14 | 94
13784 | 88.35 | 154.12 | 10262.97 | -3395.28 | -295.77 | 0.48 |  | -57.72 | 2921.39 | 0.26 |  | -0.4 | 94
13879 | 90.19 | 154.41 | 10264.18 | -3480.85 | -254.53 | 1.96 |  | 8.96 | 3016.38 | 1.94 |  | 0.31 | 95
13973 | 89.85 | 152.78 | 10264.15 | -3565.04 | -212.73 | 1.77 |  | -101.78 | 3110.37 | -0.36 |  | -1.73 | 94
14068 | 89.01 | 154.55 | 10265.09 | -3650.17 | -170.59 | 2.06 |  | 115.4 | 3205.36 | -0.88 |  | 1.86 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 160.23 | 17.62 | 43.64 | 349 | 342.86 | 3700 | 2857.14 | 0 | 235.71 | 198.33 | 192.86 | 7.5 | 0
Run | 141.84 | 17.62 | 43.64 | 349 | 342.86 | 3700 | 2857.14 | 0 | 235.71 | 198.33 | 192.86 | 7.5 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Real Time Survey Management |  |  |  |  | 10/23/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 10/23/2021 |  | 23 |  | 2000 |  | 1 | 2000
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/23/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/23/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/23/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/23/2021 | 00:00 | 00:05 | 0.08 | 10932 | 10943 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/10932.00 t/10943.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 132.00, Diff 850.00, Temp 239.00
10/23/2021 | 00:05 | 00:10 | 0.08 | 10943 | 10949 | 6 | LAT | 3: BHA 3 | 2J | Slide Drill f/10943.00 t/10949.00, TF G, w/WOB 25.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 72.00, Diff 850.00, Temp 239.00
10/23/2021 | 00:10 | 00:30 | 0.33 | 10949 | 11027 | 78 | LAT | 3: BHA 3 | 2K | Rotary Drill f/10949.00 t/11027.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 234.00, Diff 850.00, Temp 243.00
10/23/2021 | 00:30 | 00:36 | 0.1 | 11027 | 11027 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 00:36 | 00:40 | 0.07 | 11027 | 11037 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11027.00 t/11037.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 150.00, Diff 850.00, Temp 243.00
10/23/2021 | 00:40 | 01:00 | 0.33 | 11037 | 11052 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/11037.00 t/11052.00, TF G, w/WOB 25.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 45.00, Diff 850.00, Temp 243.00
10/23/2021 | 01:00 | 01:15 | 0.25 | 11052 | 11120 | 68 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11052.00 t/11120.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 272.00, Diff 850.00, Temp 243.00
10/23/2021 | 01:15 | 01:26 | 0.18 | 11120 | 11120 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 01:26 | 01:50 | 0.4 | 11120 | 11214 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11120.00 t/11214.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 235.00, Diff 850.00, Temp 243.00
10/23/2021 | 01:50 | 01:56 | 0.1 | 11214 | 11214 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 01:56 | 02:00 | 0.07 | 11214 | 11224 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11214.00 t/11224.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 150.00, Diff 850.00, Temp 243.00
10/23/2021 | 02:00 | 02:25 | 0.42 | 11224 | 11241 | 17 | LAT | 3: BHA 3 | 2J | Slide Drill f/11224.00 t/11241.00, TF 115.00G, w/WOB 25.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 40.80, Diff 850.00, Temp 243.00
10/23/2021 | 02:25 | 02:45 | 0.33 | 11241 | 11309 | 68 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11241.00 t/11309.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 204.00, Diff 850.00, Temp 243.00
10/23/2021 | 02:45 | 02:56 | 0.18 | 11309 | 11309 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 02:56 | 03:00 | 0.07 | 11309 | 11319 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11309.00 t/11319.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 7.50, ROP 150.00, Diff 850.00, Temp 243.00
10/23/2021 | 03:00 | 03:25 | 0.42 | 11319 | 11340 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/11319.00 t/11340.00, TF 130.00G, w/WOB 25.00,Flow 350.00, Press 3800.00, Tq 7.50, ROP 50.40, Diff 850.00, Temp 243.00
10/23/2021 | 03:25 | 03:45 | 0.33 | 11340 | 11403 | 63 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11340.00 t/11403.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 189.00, Diff 850.00, Temp 243.00
10/23/2021 | 03:45 | 03:51 | 0.1 | 11403 | 11403 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 03:51 | 04:15 | 0.4 | 11403 | 11498 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11403.00 t/11498.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 237.50, Diff 850.00, Temp 243.00
10/23/2021 | 04:15 | 04:21 | 0.1 | 11498 | 11498 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 04:21 | 04:45 | 0.4 | 11498 | 11592 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11498.00 t/11592.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 235.00, Diff 850.00, Temp 243.00
10/23/2021 | 04:45 | 04:50 | 0.08 | 11592 | 11592 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 04:50 | 04:55 | 0.08 | 11592 | 11602 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11592.00 t/11602.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 120.00, Diff 850.00, Temp 243.00
10/23/2021 | 04:55 | 05:15 | 0.33 | 11602 | 11624 | 22 | LAT | 3: BHA 3 | 2J | Slide Drill f/11602.00 t/11624.00, TF -130.00G, w/WOB 25.00,Flow 350.00, Press 3800.00, Tq 10.20, ROP 66.00, Diff 850.00, Temp 243.00
10/23/2021 | 05:15 | 05:35 | 0.33 | 11624 | 11687 | 63 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11624.00 t/11687.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 189.00, Diff 850.00, Temp 245.00
10/23/2021 | 05:35 | 05:40 | 0.08 | 11687 | 11687 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 05:40 | 06:04 | 0.4 | 11687 | 11782 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11687.00 t/11782.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 237.50, Diff 850.00, Temp 245.00
10/23/2021 | 06:04 | 06:09 | 0.08 | 11782 | 11782 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 06:09 | 06:31 | 0.37 | 11782 | 11876 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11782.00 t/11876.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 256.36, Diff 850.00, Temp 245.00
10/23/2021 | 06:31 | 06:36 | 0.08 | 11876 | 11876 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 06:36 | 06:59 | 0.38 | 11876 | 11970 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11876.00 t/11970.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 245.22, Diff 850.00, Temp 245.00
10/23/2021 | 06:59 | 07:04 | 0.08 | 11970 | 11970 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 07:04 | 07:21 | 0.28 | 11970 | 11985 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/11970.00 t/11985.00, TF 120.00G, w/WOB 40.00,Flow 350.00, Press 3800.00, Tq 10.20, ROP 52.94, Diff 850.00, Temp 245.00
10/23/2021 | 07:21 | 07:45 | 0.4 | 11985 | 12064 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11985.00 t/12064.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 197.50, Diff 850.00, Temp 245.00
10/23/2021 | 07:45 | 07:50 | 0.08 | 12064 | 12064 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 07:50 | 08:04 | 0.23 | 12064 | 12079 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12064.00 t/12079.00, TF 120.00G, w/WOB 40.00,Flow 350.00, Press 3800.00, Tq 10.20, ROP 64.29, Diff 850.00, Temp 245.00
10/23/2021 | 08:04 | 08:28 | 0.4 | 12079 | 12158 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12079.00 t/12158.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 197.50, Diff 850.00, Temp 245.00
10/23/2021 | 08:28 | 08:33 | 0.08 | 12158 | 12158 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 08:33 | 08:57 | 0.4 | 12158 | 12252 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12158.00 t/12252.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3800.00, Tq 10.20, ROP 235.00, Diff 850.00, Temp 245.00
10/23/2021 | 08:57 | 09:02 | 0.08 | 12252 | 12252 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 09:02 | 09:16 | 0.23 | 12252 | 12266 | 14 | LAT | 3: BHA 3 | 2J | Slide Drill f/12252.00 t/12266.00, TF 120.00G, w/WOB 40.00,Flow 350.00, Press 3800.00, Tq 10.20, ROP 60.00, Diff 850.00, Temp 245.00
10/23/2021 | 09:16 | 09:41 | 0.42 | 12266 | 12347 | 81 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12266.00 t/12347.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3950.00, Tq 10.20, ROP 194.40, Diff 750.00, Temp 262.00
10/23/2021 | 09:41 | 09:46 | 0.08 | 12347 | 12347 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 09:46 | 10:10 | 0.4 | 12347 | 12439 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12347.00 t/12439.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3950.00, Tq 10.20, ROP 230.00, Diff 750.00, Temp 262.00
10/23/2021 | 10:10 | 10:15 | 0.08 | 12439 | 12439 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 10:15 | 10:29 | 0.23 | 12439 | 12454 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12439.00 t/12454.00, TF 140.00G, w/WOB 45.00,Flow 350.00, Press 3950.00, Tq 10.20, ROP 64.29, Diff 750.00, Temp 262.00
10/23/2021 | 10:29 | 10:55 | 0.43 | 12454 | 12532 | 78 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12454.00 t/12532.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 3950.00, Tq 10.20, ROP 180.00, Diff 750.00, Temp 268.00
10/23/2021 | 10:55 | 10:59 | 0.07 | 12532 | 12532 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 10:59 | 11:24 | 0.42 | 12532 | 12627 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12532.00 t/12627.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.20, ROP 228.00, Diff 900.00, Temp 268.00
10/23/2021 | 11:24 | 11:29 | 0.08 | 12627 | 12627 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 11:29 | 11:59 | 0.5 | 12627 | 12719 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12627.00 t/12719.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.80, ROP 184.00, Diff 900.00, Temp 268.00
10/23/2021 | 11:59 | 12:04 | 0.08 | 12719 | 12719 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 12:04 | 12:20 | 0.27 | 12719 | 12734 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12719.00 t/12734.00, TF -150.00G, w/WOB 45.00,Flow 350.00, Press 4200.00, Tq 10.80, ROP 56.25, Diff 900.00, Temp 268.00
10/23/2021 | 12:20 | 12:46 | 0.43 | 12734 | 12813 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12734.00 t/12813.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.80, ROP 182.31, Diff 900.00, Temp 268.00
10/23/2021 | 12:46 | 12:50 | 0.07 | 12813 | 12813 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 12:50 | 13:17 | 0.45 | 12813 | 12907 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12813.00 t/12907.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.80, ROP 208.89, Diff 900.00, Temp 268.00
10/23/2021 | 13:17 | 13:22 | 0.08 | 12907 | 12907 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 13:22 | 13:47 | 0.42 | 12907 | 13001 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12907.00 t/13001.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.80, ROP 225.60, Diff 900.00, Temp 268.00
10/23/2021 | 13:47 | 13:52 | 0.08 | 13001 | 13001 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 13:52 | 14:12 | 0.33 | 13001 | 13016 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/13001.00 t/13016.00, TF 180.00G, w/WOB 50.00,Flow 350.00, Press 4200.00, Tq 10.80, ROP 45.00, Diff 900.00, Temp 268.00
10/23/2021 | 14:12 | 14:44 | 0.53 | 13016 | 13094 | 78 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13016.00 t/13094.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.80, ROP 146.25, Diff 900.00, Temp 268.00
10/23/2021 | 14:44 | 15:25 | 0.68 | 13094 | 13094 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 15:25 | 15:51 | 0.43 | 13094 | 13188 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13094.00 t/13188.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 10.80, ROP 216.92, Diff 900.00, Temp 264.00
10/23/2021 | 15:51 | 15:56 | 0.08 | 13188 | 13188 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 15:56 | 16:24 | 0.47 | 13188 | 13283 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13188.00 t/13283.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 11, ROP 203.57, Diff 850.00, Temp 264.00
10/23/2021 | 16:24 | 16:29 | 0.08 | 13283 | 13283 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 16:29 | 16:55 | 0.43 | 13283 | 13377 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13283.00 t/13377.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 11.00, ROP 216.92, Diff 850.00, Temp 268.00
10/23/2021 | 16:55 | 17:00 | 0.08 | 13377 | 13377 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 17:00 | 17:14 | 0.23 | 13377 | 13387 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/13377.00 t/13387.00, TF 150.00G, w/WOB 50.00,Flow 350.00, Press 4200.00, Tq 11.00, ROP 42.86, Diff 850.00, Temp 268.00
10/23/2021 | 17:14 | 17:58 | 0.73 | 13387 | 13472 | 85 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13387.00 t/13472.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 11.00, ROP 115.91, Diff 850.00, Temp 268.00
10/23/2021 | 17:58 | 18:03 | 0.08 | 13472 | 13472 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 18:03 | 18:25 | 0.37 | 13472 | 13566 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13472.00 t/13566.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 11.00, ROP 256.36, Diff 850.00, Temp 268.00
10/23/2021 | 18:25 | 18:36 | 0.18 | 13566 | 13566 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 18:36 | 18:40 | 0.07 | 13566 | 13576 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13566.00 t/13576.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 150.00, Diff 850.00, Temp 268.00
10/23/2021 | 18:40 | 18:55 | 0.25 | 13576 | 13587 | 11 | LAT | 3: BHA 3 | 2J | Slide Drill f/13576.00 t/13587.00, TF 20.00G, w/WOB 25.00,Flow 350.00, Press 4200.00, Tq 12.5, ROP 44.00, Diff 850.00, Temp 268.00
10/23/2021 | 18:55 | 19:20 | 0.42 | 13587 | 13660 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13587.00 t/13660.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 175.20, Diff 850.00, Temp 268.00
10/23/2021 | 19:20 | 19:26 | 0.1 | 13660 | 13660 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 19:26 | 19:30 | 0.07 | 13660 | 13670 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13660.00 t/13670.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 150.00, Diff 850.00, Temp 268.00
10/23/2021 | 19:30 | 19:40 | 0.17 | 13670 | 13675 | 5 | LAT | 3: BHA 3 | 2J | Slide Drill f/13670.00 t/13675.00, TF G, w/WOB 25.00,Flow 350.00, Press 4200.00, Tq 12.5, ROP 30.00, Diff 850.00, Temp 268.00
10/23/2021 | 19:40 | 20:05 | 0.42 | 13675 | 13754 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13675.00 t/13754.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 189.60, Diff 850.00, Temp 268.00
10/23/2021 | 20:05 | 20:11 | 0.1 | 13754 | 13754 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 20:11 | 20:35 | 0.4 | 13754 | 13848 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13754.00 t/13848.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 235.00, Diff 850.00, Temp 268.00
10/23/2021 | 20:35 | 20:40 | 0.08 | 13848 | 13848 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 20:40 | 21:10 | 0.5 | 13848 | 13943 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13848.00 t/13943.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 190.00, Diff 850.00, Temp 268.00
10/23/2021 | 21:10 | 21:15 | 0.08 | 13943 | 13943 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 21:15 | 21:20 | 0.08 | 13943 | 13953 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13943.00 t/13953.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 120.00, Diff 850.00, Temp 268.00
10/23/2021 | 21:20 | 21:45 | 0.42 | 13953 | 13970 | 17 | LAT | 3: BHA 3 | 2J | Slide Drill f/13953.00 t/13970.00, TF -165.00G, w/WOB 25.00,Flow 350.00, Press 4200.00, Tq 12.5, ROP 40.80, Diff 850.00, Temp 268.00
10/23/2021 | 21:45 | 21:54 | 0.15 | 13970 | 13970 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 21:54 | 22:05 | 0.18 | 13970 | 14037 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13970.00 t/14037.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 365.45, Diff 850.00, Temp 268.00
10/23/2021 | 22:05 | 22:10 | 0.08 | 14037 | 14037 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 22:10 | 22:13 | 0.05 | 14037 | 14047 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14037.00 t/14047.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 120.00, Diff 850.00, Temp 268.00
10/23/2021 | 22:13 | 23:05 | 0.87 | 14047 | 14077 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/14047.00 t/14077.00, TF 175.00G, w/WOB 25.00,Flow 350.00, Press 4200.00, Tq 12.5, ROP 34.62, Diff 850.00, Temp 268.00
10/23/2021 | 23:05 | 23:25 | 0.33 | 14077 | 14132 | 55 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14077.00 t/14132.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 165.00, Diff 850.00, Temp 268.00
10/23/2021 | 23:25 | 23:30 | 0.08 | 14132 | 14132 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/23/2021 | 23:30 | 23:35 | 0.08 | 14132 | 14142 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14132.00 t/14142.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 120.00, Diff 850.00, Temp 268.00
10/23/2021 | 23:35 | 24:00 | 0.42 | 14142 | 14150 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/14142.00 t/14150.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 4200.00, Tq 12.5, ROP 19.20, Diff 850.00, Temp 268.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_24_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/24/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 112090
|  |  |  | 24hr Summary: |  | Rotate Slide As Needed
|  |  |  | 24hr Lookahead: |  | Rotate Slide As Needed
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14150 |  | 9928 |  | Csg Shoe MD(Usft): |  | 9920 |  | 600: | 39 | PV: | 14
End Depth (Usft): |  | 16488 |  | 16488 |  | OD (in): |  | 7.875 |  | 300: | 25 | YP: | 11
Total Drilled (Usft): |  | 2338 |  | 6560 |  | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 50
Slide Drilled (Usft): |  | 169 |  | 1023 | [5 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 2169 |  | 5537 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 7.80
Drlg/Circ Hrs: |  | 17.92 / 3.68 |  | 47.65 / 11.95 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 4.65 |  | 16.17 |  | SN: |  | 13635755 |  | 10s Gel: | 10 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 13.27 |  | 31.48 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 238.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 163.49 / 36.34 |  | 175.87 / 63.28 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 80.5 |  | Grade In: |  | New
% Slide: |  | 7.23 |  | 15.59 |  | Grade Out: |  | 2-3-BT-N-X-I-CT-DMF
% Rotary: |  | 92.77 |  | 84.41 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 T/S HS88 -.013 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.39 |  | 34.39
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 36.03
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.62
UHBO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.61
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.38
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 50.66 |  | 5.59 |  | 80.97
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 112.29
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 129.76
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 133.09
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 322.45
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 331.08
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2785.07
Agitator |  |  |  | 5 | 2.5 |  |  | 55.38 |  | 22.01 |  | 2807.08
2807.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250018 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.14 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14163 | 86.13 | 154.82 | 10269.12 | -3735.96 | -130 | 3.04 |  | 174.65 | 3300.26 | -3.03 |  | 0.28 | 95
14258 | 86.56 | 154.77 | 10275.18 | -3821.74 | -89.63 | 0.46 |  | -6.62 | 3395.05 | 0.45 |  | -0.05 | 95
14351 | 85.11 | 153.69 | 10281.93 | -3905.27 | -49.31 | 1.94 |  | -143.43 | 3487.8 | -1.56 |  | -1.16 | 93
14446 | 85.09 | 153.22 | 10290.05 | -3989.94 | -7.01 | 0.49 |  | -92.47 | 3582.45 | -0.02 |  | -0.49 | 95
14540 | 86.28 | 154.24 | 10297.12 | -4073.99 | 34.48 | 1.67 |  | 40.56 | 3676.18 | 1.27 |  | 1.09 | 94
14635 | 87.74 | 154.11 | 10302.07 | -4159.39 | 75.8 | 1.54 |  | -5.08 | 3771.05 | 1.54 |  | -0.14 | 95
14730 | 86.92 | 153.26 | 10306.5 | -4244.45 | 117.87 | 1.24 |  | -134.02 | 3865.94 | -0.86 |  | -0.89 | 95
14824 | 86.53 | 152.49 | 10311.87 | -4327.97 | 160.66 | 0.92 |  | -116.92 | 3959.77 | -0.41 |  | -0.82 | 94
14919 | 86.49 | 149.41 | 10317.65 | -4410.86 | 206.7 | 3.24 |  | -90.84 | 4054.45 | -0.04 |  | -3.24 | 95
15013 | 86.95 | 154.45 | 10323.04 | -4493.64 | 250.84 | 5.38 |  | 84.92 | 4148.21 | 0.49 |  | 5.36 | 94
15107 | 86.81 | 152.55 | 10328.15 | -4577.63 | 292.72 | 2.02 |  | -94.27 | 4242.06 | -0.15 |  | -2.02 | 94
15202 | 84.67 | 147.25 | 10335.21 | -4659.56 | 340.21 | 6 |  | -112.22 | 4336.52 | -2.25 |  | -5.58 | 95
15296 | 83.38 | 148.28 | 10345 | -4738.64 | 390.07 | 1.75 |  | 141.6 | 4429.45 | -1.37 |  | 1.1 | 94
15390 | 84.35 | 152.31 | 10355.05 | -4819.8 | 436.37 | 4.39 |  | 76.61 | 4522.7 | 1.03 |  | 4.29 | 94
15484 | 85.06 | 152.15 | 10363.72 | -4902.62 | 479.98 | 0.77 |  | -12.65 | 4616.26 | 0.76 |  | -0.17 | 94
15579 | 85.52 | 153.97 | 10371.52 | -4987.02 | 522.88 | 1.97 |  | 75.85 | 4710.92 | 0.48 |  | 1.92 | 95
15673 | 86.71 | 154.82 | 10377.89 | -5071.59 | 563.4 | 1.55 |  | 35.51 | 4804.7 | 1.27 |  | 0.9 | 94
15766 | 87.62 | 154.45 | 10382.49 | -5155.52 | 603.19 | 1.06 |  | -22.11 | 4897.58 | 0.98 |  | -0.4 | 93
15861 | 86.55 | 155.93 | 10387.32 | -5241.64 | 643 | 1.92 |  | 125.94 | 4992.43 | -1.13 |  | 1.56 | 95
15955 | 86.61 | 156.46 | 10392.93 | -5327.49 | 680.88 | 0.57 |  | 83.55 | 5086.19 | 0.06 |  | 0.56 | 94
16049 | 88.33 | 156.51 | 10397.08 | -5413.6 | 718.34 | 1.83 |  | 1.66 | 5180.01 | 1.83 |  | 0.05 | 94
16142 | 85.55 | 156.4 | 10402.05 | -5498.72 | 755.44 | 2.99 |  | -177.74 | 5272.78 | -2.99 |  | -0.12 | 93
16235 | 86.6 | 156.35 | 10408.41 | -5583.73 | 792.62 | 1.13 |  | -2.72 | 5365.48 | 1.13 |  | -0.05 | 93
16329 | 85.7 | 156.84 | 10414.72 | -5669.8 | 829.87 | 1.09 |  | 151.5 | 5459.17 | -0.96 |  | 0.52 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 135.93 | 25 | 80 | 392 | 350 | 4392.31 | 3361.54 | 68 | 298.46 | 172.69 | 196.15 | 13.13 | 7.2
Run | 139.97 | 24.84 | 73.85 | 384 | 348.42 | 3991.58 | 3117.89 | 68 | 260.11 | 177 | 199.89 | 10.36 | 6.3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/24/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/24/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/24/2021 |  | 7 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 10/24/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 10/24/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/24/2021 | 00:00 | 00:15 | 0.25 | 14150 | 14158 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/14150.00 t/14158.00, TF -175.00G, w/WOB 25.00,Flow 350.00, Press 4200.00, Tq 12.5, ROP 32.00, Diff 850.00, Temp 268.00
10/24/2021 | 00:15 | 00:40 | 0.42 | 14158 | 14227 | 69 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14158.00 t/14227.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.5, ROP 165.60, Diff 850.00, Temp 268.00
10/24/2021 | 00:40 | 00:45 | 0.08 | 14227 | 14227 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 00:45 | 01:15 | 0.5 | 14227 | 14322 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14227.00 t/14322.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4200.00, Tq 12.50, ROP 190.00, Diff 850.00, Temp 277.00
10/24/2021 | 01:15 | 01:20 | 0.08 | 14322 | 14322 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 01:20 | 01:23 | 0.05 | 14322 | 14332 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14322.00 t/14332.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 12.50, ROP 200.00, Diff 950.00, Temp 277.00
10/24/2021 | 01:23 | 01:45 | 0.37 | 14332 | 14349 | 17 | LAT | 3: BHA 3 | 2J | Slide Drill f/14332.00 t/14349.00, TF -160.00G, w/WOB 25.00,Flow 350.00, Press 4450.00, Tq 12.50, ROP 46.36, Diff 1100.00, Temp 277.00
10/24/2021 | 01:45 | 02:10 | 0.42 | 14349 | 14415 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14349.00 t/14415.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 12.50, ROP 158.40, Diff 1100.00, Temp 277.00
10/24/2021 | 02:10 | 02:15 | 0.08 | 14415 | 14415 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 02:15 | 02:45 | 0.5 | 14415 | 14510 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14415.00 t/14510.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 12.50, ROP 190.00, Diff 1100.00, Temp 277.00
10/24/2021 | 02:45 | 02:50 | 0.08 | 14510 | 14510 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 02:50 | 02:55 | 0.08 | 14510 | 14520 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14510.00 t/14520.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 12.50, ROP 120.00, Diff 1100.00, Temp 277.00
10/24/2021 | 02:55 | 03:05 | 0.17 | 14520 | 14530 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/14520.00 t/14530.00, TF 35.00G, w/WOB 25.00,Flow 350.00, Press 4450.00, Tq 12.50, ROP 60.00, Diff 1100.00, Temp 277.00
10/24/2021 | 03:05 | 03:40 | 0.58 | 14530 | 14604 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14530.00 t/14604.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 12.50, ROP 126.86, Diff 1100.00, Temp 277.00
10/24/2021 | 03:40 | 03:45 | 0.08 | 14604 | 14604 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 03:45 | 04:10 | 0.42 | 14604 | 14699 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14604.00 t/14699.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 14.60, ROP 228.00, Diff 1100.00, Temp 277.00
10/24/2021 | 04:10 | 04:15 | 0.08 | 14699 | 14699 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 04:15 | 04:20 | 0.08 | 14699 | 14709 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14699.00 t/14709.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 14.60, ROP 120.00, Diff 1100.00, Temp 277.00
10/24/2021 | 04:20 | 04:35 | 0.25 | 14709 | 14719 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/14709.00 t/14719.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 4450.00, Tq 14.60, ROP 40.00, Diff 1100.00, Temp 277.00
10/24/2021 | 04:35 | 05:05 | 0.5 | 14719 | 14794 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14719.00 t/14794.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 14.60, ROP 150.00, Diff 1100.00, Temp 277.00
10/24/2021 | 05:05 | 05:08 | 0.05 | 14794 | 14794 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 05:08 | 05:38 | 0.5 | 14794 | 14888 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14794.00 t/14888.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 14.60, ROP 188.00, Diff 1100.00, Temp 277.00
10/24/2021 | 05:38 | 05:42 | 0.07 | 14888 | 14888 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 05:42 | 06:07 | 0.42 | 14888 | 14983 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14888.00 t/14983.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 14.60, ROP 228.00, Diff 1100.00, Temp 277.00
10/24/2021 | 06:07 | 06:12 | 0.08 | 14983 | 14983 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 06:12 | 06:27 | 0.25 | 14983 | 14998 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/14983.00 t/14998.00, TF 120.00G, w/WOB 40.00,Flow 350.00, Press 4450.00, Tq 14.60, ROP 60.00, Diff 1100.00, Temp 277.00
10/24/2021 | 06:27 | 06:55 | 0.47 | 14998 | 15077 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14998.00 t/15077.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 14.60, ROP 169.29, Diff 1100.00, Temp 277.00
10/24/2021 | 06:55 | 06:59 | 0.07 | 15077 | 15077 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 06:59 | 07:25 | 0.43 | 15077 | 15171 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15077.00 t/15171.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 216.92, Diff 1000.00, Temp 279.00
10/24/2021 | 07:25 | 07:29 | 0.07 | 15171 | 15171 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 07:29 | 07:44 | 0.25 | 15171 | 15186 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/15171.00 t/15186.00, TF 180.00G, w/WOB 50.00,Flow 350.00, Press 4450.00, Tq 11.50, ROP 60.00, Diff 1000.00, Temp 277.00
10/24/2021 | 07:44 | 08:15 | 0.52 | 15186 | 15266 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15186.00 t/15266.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 154.84, Diff 1000.00, Temp 275.00
10/24/2021 | 08:15 | 08:19 | 0.07 | 15266 | 15266 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 08:19 | 08:53 | 0.57 | 15266 | 15286 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15266.00 t/15286.00, TF 90.00G, w/WOB 50.00,Flow 350.00, Press 4450.00, Tq 11.50, ROP 35.29, Diff 1000.00, Temp 272.00
10/24/2021 | 08:53 | 09:28 | 0.58 | 15286 | 15360 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15286.00 t/15360.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 126.86, Diff 1000.00, Temp 279.00
10/24/2021 | 09:28 | 09:32 | 0.07 | 15360 | 15360 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 09:32 | 10:12 | 0.67 | 15360 | 15380 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15360.00 t/15380.00, TF 60.00G, w/WOB 50.00,Flow 350.00, Press 4450.00, Tq 11.50, ROP 30.00, Diff 1000.00, Temp 268.00
10/24/2021 | 10:12 | 10:42 | 0.5 | 15380 | 15454 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15380.00 t/15454.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 148.00, Diff 1000.00, Temp 264.00
10/24/2021 | 10:42 | 10:46 | 0.07 | 15454 | 15454 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 10:46 | 11:17 | 0.52 | 15454 | 15548 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15454.00 t/15548.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 181.94, Diff 1000.00, Temp 271.00
10/24/2021 | 11:17 | 11:21 | 0.07 | 15548 | 15548 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 11:21 | 11:38 | 0.28 | 15548 | 15563 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/15548.00 t/15563.00, TF 60.00G, w/WOB 50.00,Flow 350.00, Press 4450.00, Tq 11.50, ROP 52.94, Diff 1000.00, Temp 271.00
10/24/2021 | 11:38 | 12:17 | 0.65 | 15563 | 15643 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15563.00 t/15643.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 123.08, Diff 1000.00, Temp 271.00
10/24/2021 | 12:17 | 12:22 | 0.08 | 15643 | 15643 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 12:22 | 12:53 | 0.52 | 15643 | 15737 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15643.00 t/15737.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4450.00, Tq 11.50, ROP 181.94, Diff 1000.00, Temp 275.00
10/24/2021 | 12:53 | 12:57 | 0.07 | 15737 | 15737 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 12:57 | 13:27 | 0.5 | 15737 | 15830 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15737.00 t/15830.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4500.00, Tq 15.00, ROP 186.00, Diff 900.00, Temp 275.00
10/24/2021 | 13:27 | 13:31 | 0.07 | 15830 | 15830 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 13:31 | 13:37 | 0.1 | 15830 | 15846 | 16 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15830.00 t/15846.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4500.00, Tq 15.00, ROP 160.00, Diff 900.00, Temp 275.00
10/24/2021 | 13:37 | 13:53 | 0.27 | 15846 | 15855 | 9 | LAT | 3: BHA 3 | 2J | Slide Drill f/15846.00 t/15855.00, TF 140.00G, w/WOB 45.00,Flow 350.00, Press 4500.00, Tq 15.00, ROP 33.75, Diff 900.00, Temp 275.00
10/24/2021 | 13:53 | 16:17 | 2.4 | 15855 | 15855 | 0 | LAT | 3: BHA 3 | 6F | Short Trip
10/24/2021 | 16:17 | 16:27 | 0.17 | 15855 | 15861 | 6 | LAT | 3: BHA 3 | 2J | Slide Drill f/15855.00 t/15861.00, TF 140.00G, w/WOB 45.00,Flow 350.00, Press 4500.00, Tq 15.00, ROP 36.00, Diff 900.00, Temp 271.00
10/24/2021 | 16:27 | 16:54 | 0.45 | 15861 | 15925 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15861.00 t/15925.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4500.00, Tq 15.00, ROP 142.22, Diff 900.00, Temp 271.00
10/24/2021 | 16:54 | 16:58 | 0.07 | 15925 | 15925 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 16:58 | 17:32 | 0.57 | 15925 | 16019 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15925.00 t/16019.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4500.00, Tq 15.00, ROP 165.88, Diff 900.00, Temp 271.00
10/24/2021 | 17:32 | 17:35 | 0.05 | 16019 | 16019 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 17:35 | 18:00 | 0.42 | 16019 | 16113 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16019.00 t/16113.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 225.60, Diff 455.00, Temp 271.00
10/24/2021 | 18:00 | 19:55 | 1.92 | 16113 | 16113 | 0 | LAT | 3: BHA 3 | 5A | Circulate spot mud cap
10/24/2021 | 19:55 | 20:00 | 0.08 | 16113 | 16113 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 20:00 | 20:15 | 0.25 | 16113 | 16123 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16113.00 t/16123.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 40.00, Diff 455.00, Temp 271.00
10/24/2021 | 20:15 | 20:55 | 0.67 | 16123 | 16139 | 16 | LAT | 3: BHA 3 | 2J | Slide Drill f/16123.00 t/16139.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 4055.00, Tq 15.00, ROP 24.00, Diff 455.00, Temp 271.00
10/24/2021 | 20:55 | 21:35 | 0.67 | 16139 | 16206 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16139.00 t/16206.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 100.50, Diff 455.00, Temp 271.00
10/24/2021 | 21:35 | 21:40 | 0.08 | 16206 | 16206 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 21:40 | 22:05 | 0.42 | 16206 | 16299 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16206.00 t/16299.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 223.20, Diff 455.00, Temp 271.00
10/24/2021 | 22:05 | 22:10 | 0.08 | 16299 | 16299 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 22:10 | 22:15 | 0.08 | 16299 | 16309 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16299.00 t/16309.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 120.00, Diff 455.00, Temp 271.00
10/24/2021 | 22:15 | 22:45 | 0.5 | 16309 | 16317 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/16309.00 t/16317.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 4055.00, Tq 15.00, ROP 16.00, Diff 455.00, Temp 271.00
10/24/2021 | 22:45 | 23:20 | 0.58 | 16317 | 16393 | 76 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16317.00 t/16393.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 130.29, Diff 455.00, Temp 271.00
10/24/2021 | 23:20 | 23:25 | 0.08 | 16393 | 16393 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/24/2021 | 23:25 | 23:55 | 0.5 | 16393 | 16488 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16393.00 t/16488.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 190.00, Diff 455.00, Temp 271.00
10/24/2021 | 23:55 | 24:00 | 0.08 | 16488 | 16488 | 0 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16488.00 t/16488.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4055.00, Tq 15.00, ROP 0.00, Diff 455.00, Temp 271.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_25_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/25/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19800 |  |  | Well Cost($): |  | 131890
|  |  |  | 24hr Summary: |  | Rotate Slide / Set Mud Cap @16,113 / Contine Rotate Slide
|  |  |  | 24hr Lookahead: |  | Rotate Slide As Needed
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16488 |  | 17088 |  | Csg Shoe MD(Usft): |  | 9920 |  | 600: | 39 | PV: | 14
End Depth (Usft): |  | 17088 |  | 17088 |  | OD (in): |  | 7.875 |  | 300: | 25 | YP: | 11
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45 |  | 200: | 16 | Viscosity: | 26
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.01 / 7.80
Drlg/Circ Hrs: |  | 0.00 / 0.50 |  | 0.00 / 0.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: | [5 empty] | SN: |  | 13635755 |  | 10s Gel: | 10 | Weight (ppg): | 8.3
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 238.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 1.33 |  | 1.33 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 2-3-BT-N-X-I-CT-DMF
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 T/S HS88 -.013 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.39 |  | 34.39
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 36.03
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.62
UHBO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.61
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.38
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 50.66 |  | 5.59 |  | 80.97
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 112.29
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 129.76
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 133.09
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 322.45
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 331.08
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2785.07
Agitator |  |  |  | 5 | 2.5 |  |  | 55.38 |  | 22.01 |  | 2807.08
2807.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250018 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.14 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16424 | 85.21 | 156.57 | 10422.25 | -5756.78 | 867.33 | 0.59 |  | -151.23 | 5553.76 | -0.52 |  | -0.28 | 95
16518 | 86.19 | 156.35 | 10429.3 | -5842.71 | 904.76 | 1.07 |  | -12.63 | 5647.41 | 1.04 |  | -0.23 | 94
16612 | 87.7 | 156.4 | 10434.31 | -5928.71 | 942.38 | 1.61 |  | 1.9 | 5741.19 | 1.61 |  | 0.05 | 94
16707 | 86.93 | 154.43 | 10438.76 | -6015 | 981.86 | 2.22 |  | -111.41 | 5836.05 | -0.81 |  | -2.07 | 95
16802 | 86.91 | 154.71 | 10443.86 | -6100.67 | 1022.59 | 0.3 |  | 94.1 | 5930.91 | -0.02 |  | 0.29 | 95
16897 | 87.07 | 155.05 | 10448.85 | -6186.57 | 1062.86 | 0.4 |  | 64.78 | 6025.76 | 0.17 |  | 0.36 | 95
16991 | 86.76 | 153.18 | 10453.91 | -6271.01 | 1103.84 | 2.01 |  | -99.48 | 6119.62 | -0.33 |  | -1.99 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 103.15 | 25 | 80 | 318 | 350 | 4392.31 | 3361.54 | 68 | 298.46 | 172.69 | 196.15 | 13.13 | 7.2
Run | 133.92 | 24.84 | 73.85 | 311 | 348.42 | 3991.58 | 3117.89 | 68 | 260.11 | 177 | 199.89 | 10.36 | 6.3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/25/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/25/2021 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 10/25/2021 |  | 19 |  | 600 |  | 1 | 600
Perdiem Per Hand |  |  |  |  | 10/25/2021 |  | 7 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 10/25/2021 |  | 23 |  | 2000 |  | 1 | 2000
5.5 Premium Motor Stator Reline |  |  |  |  | 10/25/2021 |  | 12 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 10/25/2021 |  | 24 |  | 800 |  | 1 | 800
Total | [11 empty] | 19800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/25/2021 | 00:00 | 00:35 | 0.58 | 16488 | 16582 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16488.00 t/16582.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 161.14, Diff 550.00, Temp 237.00
10/25/2021 | 00:35 | 00:40 | 0.08 | 16582 | 16582 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/25/2021 | 00:40 | 01:15 | 0.58 | 16582 | 16676 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16582.00 t/16676.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 161.14, Diff 550.00, Temp 237.00
10/25/2021 | 01:15 | 01:20 | 0.08 | 16676 | 16676 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/25/2021 | 01:20 | 01:25 | 0.08 | 16676 | 16686 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/16676.00 t/16686.00, TF -155.00G, w/WOB 26.50,Flow 350.00, Press 4150.00, Tq 18.50, ROP 120.00, Diff 550.00, Temp 237.00
10/25/2021 | 01:25 | 03:30 | 2.08 | 16686 | 16771 | 85 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16686.00 t/16771.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 40.80, Diff 550.00, Temp 237.00
10/25/2021 | 03:30 | 03:35 | 0.08 | 16771 | 16771 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/25/2021 | 03:35 | 04:00 | 0.42 | 16771 | 16866 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16771.00 t/16866.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 228.00, Diff 550.00, Temp 237.00
10/25/2021 | 04:00 | 04:05 | 0.08 | 16866 | 16866 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/25/2021 | 04:05 | 04:40 | 0.58 | 16866 | 16961 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16866.00 t/16961.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 162.86, Diff 550.00, Temp 237.00
10/25/2021 | 04:40 | 04:43 | 0.05 | 16961 | 16961 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/25/2021 | 04:43 | 05:15 | 0.53 | 16961 | 17055 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16961.00 t/17055.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 176.25, Diff 550.00, Temp 237.00
10/25/2021 | 05:15 | 05:18 | 0.05 | 17055 | 17055 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
10/25/2021 | 05:18 | 05:20 | 0.03 | 17055 | 17065 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17055.00 t/17065.00, w/WOB 26.50,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 300.00, Diff 550.00, Temp 237.00
10/25/2021 | 05:20 | 05:45 | 0.42 | 17065 | 17075 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/17065.00 t/17075.00, TF 20G, w/WOB 50,Flow 350.00, Press 4150.00, Tq 18.50, ROP 24.00, Diff 550.00, Temp 233.00
10/25/2021 | 05:45 | 06:15 | 0.5 | 17075 | 17088 | 13 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17075.00 t/17088.00, w/WOB 50.00,Flow 350.00, RPM 80.00, Press 4150.00, Tq 18.50, ROP 26.00, Diff 550.00, Temp 230.00
10/25/2021 | 06:15 | 06:30 | 0.25 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 5A | Circulate B/U @ 17,088
10/25/2021 | 06:30 | 08:45 | 2.25 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 3D | Back Reaming 17,088/14,747
10/25/2021 | 08:45 | 09:15 | 0.5 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 24A | Tight Conn.
10/25/2021 | 09:15 | 09:45 | 0.5 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 24A | Change Dies St-80
10/25/2021 | 09:45 | 13:30 | 3.75 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 3D | Back Reaming 14,4747/10,744
10/25/2021 | 13:30 | 16:45 | 3.25 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 6B | POOH F/ 10,744
10/25/2021 | 16:45 | 17:15 | 0.5 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 24A | Flow Check Well -No Flow
10/25/2021 | 17:15 | 17:35 | 0.33 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 24A | Remove Rotating Head /Install Truip Nipple ,L/D Agitator
10/25/2021 | 17:35 | 19:15 | 1.67 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 6B | POOH
10/25/2021 | 19:15 | 20:15 | 1 | 17088 | 17088 | 0 | LAT | 3: BHA 3 | 6P | L/D BHA #3
10/25/2021 | 20:15 | 22:40 | 2.42 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 6O | P/U BHA #4
10/25/2021 | 22:40 | 22:55 | 0.25 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 5A | Test MWD Motor (Good Test @80 STRS 55 RPM )
10/25/2021 | 22:55 | 23:45 | 0.83 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 6A | TIH
10/25/2021 | 23:45 | 24:00 | 0.25 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 5D | Sut well in due to Casin PSI of 268
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_26_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/26/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 141890
|  |  |  | 24hr Summary: |  | POOH Change BHA - P/U BHA #4-TIH 2795 Pump 135 bbls Kill Mud Down Back Side Mointor Casing PSI -TIH
|  |  |  | 24hr Lookahead: |  | TIH - Rotate Slide As Needed
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17088 |  | 17088 |  | Csg Shoe MD(Usft): |  | 9920 |  | 600: | 5 | PV: | 2
End Depth (Usft): |  | 17745 |  | 17745 |  | OD (in): |  | 7.875 |  | 300: | 3 | YP: | 1
Total Drilled (Usft): |  | 657 |  | 657 |  | Weight (ft/lbs): |  | 45 |  | 200: | 2 | Viscosity: | 26
Slide Drilled (Usft): |  | 12 |  | 12 | [5 empty] | 100: | 1 | Chlorides: | 180
Rotary Drilled (Usft): |  | 645 |  | 645 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.01 / 2.60
Drlg/Circ Hrs: |  | 6.93 / 11.40 |  | 6.93 / 11.90 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 99.9
Slide Drilling Hrs: |  | 1.37 |  | 1.37 |  | SN: |  | 13618580 |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: |  | 5.57 |  | 5.57 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 238.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 115.87 / 8.78 |  | 115.87 / 8.78 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 25.33 |  | Grade In:
% Slide: |  | 1.83 |  | 1.83 |  | Grade Out: |  | 1-2-BT-S-X-I-NO-TD
% Rotary: |  | 98.17 |  | 98.17 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 +.005 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.29 |  | 34.29
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.93
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.52
UBHO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.51
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.28
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 106.6
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 124.07
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 127.4
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 316.76
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 325.39
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2779.38
Agitator |  |  |  | 5.25 | 2.5 |  |  | 55.38 |  | 21.41 |  | 2800.79
2800.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.02 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17084 | 87.33 | 152.01 | 10458.71 | -6353.46 | 1146.59 | 1.4 |  | -64.03 | 6212.47 | 0.61 |  | -1.26 | 93
17178 | 87.63 | 151.43 | 10462.84 | -6436.16 | 1191.08 | 0.69 |  | -62.64 | 6306.31 | 0.32 |  | -0.62 | 94
17273 | 87.74 | 151.84 | 10466.68 | -6519.69 | 1236.18 | 0.45 |  | 74.98 | 6401.15 | 0.12 |  | 0.43 | 95
17366 | 88.89 | 151.85 | 10469.41 | -6601.64 | 1280.04 | 1.24 |  | 0.5 | 6494.04 | 1.24 |  | 0.01 | 93
17460 | 86.78 | 152.9 | 10472.96 | -6684.86 | 1323.59 | 2.51 |  | 153.58 | 6587.93 | -2.24 |  | 1.12 | 94
17555 | 86.8 | 154.11 | 10478.28 | -6769.75 | 1365.91 | 1.27 |  | 89.09 | 6682.78 | 0.02 |  | 1.27 | 95
17647 | 87.06 | 153.51 | 10483.21 | -6852.19 | 1406.45 | 0.71 |  | -66.56 | 6774.64 | 0.28 |  | -0.65 | 92
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 88.82 | 25 | 80 | 318 | 350 | 4392.31 | 3361.54 | 68 | 298.46 | 172.69 | 196.15 | 13.13 | 7.2
Run | 88.82 | 24.84 | 73.85 | 311 | 348.42 | 3991.58 | 3117.89 | 68 | 260.11 | 177 | 199.89 | 10.36 | 6.3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 10/26/2021 |  | 23 |  | 2000 |  | 1 | 2000
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/26/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/26/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/26/2021 |  | 7 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 10/26/2021 |  | 19 |  | 600 |  | 1 | 600
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/26/2021 | 00:00 | 00:30 | 0.5 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 5D | Pumped 135 BBLS Kill MUD Down back side -Kill Well
10/26/2021 | 00:30 | 01:15 | 0.75 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 8P | Monitor Well Perform Rig Service
10/26/2021 | 01:15 | 01:45 | 0.5 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 5A | Get Presures before and after 1618/1950
10/26/2021 | 01:45 | 06:40 | 4.92 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 6A | TIH
10/26/2021 | 06:40 | 16:07 | 9.45 | 17088 | 17088 | 0 | LAT | 4: BHA 4 | 3C | Reaming to Bottom 17,088
10/26/2021 | 16:07 | 16:39 | 0.53 | 17088 | 17144 | 56 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17088.00 t/17144.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 105.00, Diff 850.00, Temp 212.00
10/26/2021 | 16:39 | 16:52 | 0.22 | 17144 | 17144 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/26/2021 | 16:52 | 17:38 | 0.77 | 17144 | 17238 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17144.00 t/17238.00, w/WOB 22,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 122.61, Diff 850.00, Temp 212.00
10/26/2021 | 17:38 | 17:42 | 0.07 | 17238 | 17238 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/26/2021 | 17:42 | 18:25 | 0.72 | 17238 | 17333 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17238.00 t/17333.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 132.56, Diff 850.00, Temp 212.00
10/26/2021 | 18:25 | 18:30 | 0.08 | 17333 | 17333 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/26/2021 | 18:30 | 19:15 | 0.75 | 17333 | 17426 | 93 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17333.00 t/17426.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 124.00, Diff 850.00, Temp 212.00
10/26/2021 | 19:15 | 19:20 | 0.08 | 17426 | 17426 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/26/2021 | 19:20 | 19:23 | 0.05 | 17426 | 17436 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17426.00 t/17436.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 200.00, Diff 850.00, Temp 212.00
10/26/2021 | 19:23 | 20:45 | 1.37 | 17436 | 17448 | 12 | LAT | 4: BHA 4 | 2J | Slide Drill f/17436.00 t/17448.00, TF 130.00G, w/WOB 22.00,Flow 350.00, Press 4300.00, Tq 21.00, ROP 8.78, Diff 850.00, Temp 212.00
10/26/2021 | 20:45 | 21:50 | 1.08 | 17448 | 17520 | 72 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17448.00 t/17520.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 66.46, Diff 850.00, Temp 212.00
10/26/2021 | 21:50 | 22:10 | 0.33 | 17520 | 17520 | 0 | LAT | 4: BHA 4 | 10C | Survey & Connection
10/26/2021 | 22:10 | 22:50 | 0.67 | 17520 | 17615 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17520.00 t/17615.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 142.50, Diff 850.00, Temp 212.00
10/26/2021 | 22:50 | 22:55 | 0.08 | 17615 | 17615 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/26/2021 | 22:55 | 23:30 | 0.58 | 17615 | 17707 | 92 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17615.00 t/17707.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 157.71, Diff 850.00, Temp 212.00
10/26/2021 | 23:30 | 23:35 | 0.08 | 17707 | 17707 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/26/2021 | 23:35 | 24:00 | 0.42 | 17707 | 17745 | 38 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17707.00 t/17745.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 91.20, Diff 850.00, Temp 212.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_27_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/27/2021 |  |  | Report Time: |  | 00:00-18:50
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 151890
|  |  |  | 24hr Summary: |  | Rotate Slide As Needed
|  |  |  | 24hr Lookahead: |  | Rotate Slide As Needed
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17745 |  | 17088 |  | Csg Shoe MD(Usft): |  | 9920 |  | 600: | 5 | PV: | 2
End Depth (Usft): |  | 18929 |  | 18929 |  | OD (in): |  | 7.875 |  | 300: | 3 | YP: | 1
Total Drilled (Usft): |  | 1184 |  | 1841 |  | Weight (ft/lbs): |  | 45 |  | 200: | 2 | Viscosity: | 26
Slide Drilled (Usft): |  | 34 |  | 46 | [5 empty] | 100: | 1 | Chlorides: | 180
Rotary Drilled (Usft): |  | 1150 |  | 1795 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.01 / 2.60
Drlg/Circ Hrs: |  | 10.37 / 13.63 |  | 17.30 / 25.53 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 99.9
Slide Drilling Hrs: |  | 2.25 |  | 3.62 |  | SN: |  | 13618580 |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: |  | 8.12 |  | 13.68 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 238.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 141.68 / 15.11 |  | 131.18 / 12.72 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 44.17 |  | Grade In:
% Slide: |  | 2.87 |  | 2.5 |  | Grade Out: |  | 1-2-BT-S-X-I-NO-TD
% Rotary: |  | 97.13 |  | 97.5 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 +.005 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.29 |  | 34.29
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.93
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.52
UBHO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.51
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.28
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 106.6
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 124.07
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 127.4
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 316.76
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 325.39
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2779.38
Agitator |  |  |  | 5.25 | 2.5 |  |  | 55.38 |  | 21.41 |  | 2800.79
2800.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.02 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17741 | 87.2 | 153.31 | 10487.92 | -6936.14 | 1448.47 | 0.26 |  | -54.98 | 6868.52 | 0.15 |  | -0.21 | 94
17836 | 87.64 | 154.3 | 10492.19 | -7021.29 | 1490.37 | 1.14 |  | 66.04 | 6963.42 | 0.46 |  | 1.04 | 95
17930 | 87.77 | 154.98 | 10495.96 | -7106.17 | 1530.59 | 0.74 |  | 79.18 | 7057.34 | 0.14 |  | 0.72 | 94
18025 | 87.77 | 153.69 | 10499.65 | -7191.73 | 1571.71 | 1.36 |  | -90.03 | 7152.27 | 0 |  | -1.36 | 95
18120 | 87.13 | 153.76 | 10503.88 | -7276.83 | 1613.72 | 0.68 |  | 173.77 | 7247.17 | -0.67 |  | 0.07 | 95
18214 | 87.58 | 154.42 | 10508.22 | -7361.29 | 1654.75 | 0.85 |  | 55.7 | 7341.07 | 0.48 |  | 0.7 | 94
18309 | 88.11 | 154.43 | 10511.79 | -7446.92 | 1695.73 | 0.56 |  | 1.08 | 7436 | 0.56 |  | 0.01 | 95
18403 | 87.89 | 154.09 | 10515.07 | -7531.54 | 1736.53 | 0.43 |  | -122.93 | 7529.94 | -0.23 |  | -0.36 | 94
18497 | 87.83 | 153.96 | 10518.58 | -7615.99 | 1777.67 | 0.15 |  | -114.79 | 7623.87 | -0.06 |  | -0.14 | 94
18592 | 88.37 | 153.75 | 10521.73 | -7701.22 | 1819.51 | 0.61 |  | -21.24 | 7718.82 | 0.57 |  | -0.22 | 95
18686 | 85.6 | 154.05 | 10526.67 | -7785.51 | 1860.8 | 2.96 |  | 173.83 | 7812.68 | -2.95 |  | 0.32 | 94
18780 | 84.87 | 154.54 | 10534.48 | -7869.91 | 1901.43 | 0.93 |  | 146.24 | 7906.36 | -0.78 |  | 0.52 | 94
18869 | 84.52 | 154.4 | 10542.71 | -7949.88 | 1939.63 | 0.42 |  | -158.29 | 7994.97 | -0.39 |  | -0.16 | 89
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 101.49 | 25 | 80 | 318 | 350 | 4392.31 | 3361.54 | 68 | 298.46 | 172.69 | 196.15 | 13.13 | 7.2
Run | 97.4 | 24.84 | 73.85 | 311 | 348.42 | 3991.58 | 3117.89 | 68 | 260.11 | 177 | 199.89 | 10.36 | 6.3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/27/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/27/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/27/2021 |  | 7 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 10/27/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 10/27/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/27/2021 | 00:00 | 00:15 | 0.25 | 17745 | 17801 | 56 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17745.00 t/17801.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 224.00, Diff 850.00, Temp 212.00
10/27/2021 | 00:15 | 00:55 | 0.67 | 17801 | 17801 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 00:55 | 01:00 | 0.08 | 17801 | 17811 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17801.00 t/17811.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 4300.00, Tq 21.00, ROP 120.00, Diff 850.00, Temp 212.00
10/27/2021 | 01:00 | 01:20 | 0.33 | 17811 | 17811 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 01:20 | 02:10 | 0.83 | 17811 | 17821 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/17811.00 t/17821.00, TF 65.00G, w/WOB 22.00,Flow 350.00, Press 4300.00, Tq 21.00, ROP 12.00, Diff 850.00, Temp 212.00
10/27/2021 | 02:10 | 02:50 | 0.67 | 17821 | 17896 | 75 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17821.00 t/17896.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 112.50, Diff 1040.00, Temp 212.00
10/27/2021 | 02:50 | 02:55 | 0.08 | 17896 | 17896 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 02:55 | 03:25 | 0.5 | 17896 | 17990 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17896.00 t/17990.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 188.00, Diff 1040.00, Temp 210.00
10/27/2021 | 03:25 | 03:30 | 0.08 | 17990 | 17990 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 03:30 | 04:10 | 0.67 | 17990 | 18085 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17990.00 t/18085.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 142.50, Diff 1040.00, Temp 210.00
10/27/2021 | 04:10 | 04:13 | 0.05 | 18085 | 18085 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 04:13 | 04:50 | 0.62 | 18085 | 18180 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18085.00 t/18180.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 154.05, Diff 1040.00, Temp 210.00
10/27/2021 | 04:50 | 04:54 | 0.07 | 18180 | 18180 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 04:54 | 05:00 | 0.1 | 18180 | 18190 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18180.00 t/18190.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 100.00, Diff 1040.00, Temp 210.00
10/27/2021 | 05:00 | 05:40 | 0.67 | 18190 | 18200 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/18190.00 t/18200.00, TF 65.00G, w/WOB 35.00,Flow 350.00, Press 4890.00, Tq 21.00, ROP 15.00, Diff 1040.00, Temp 210.00
10/27/2021 | 05:40 | 06:25 | 0.75 | 18200 | 18274 | 74 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18200.00 t/18274.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 98.67, Diff 1040.00, Temp 210.00
10/27/2021 | 06:25 | 06:30 | 0.08 | 18274 | 18274 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 06:30 | 07:07 | 0.62 | 18274 | 18369 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18274.00 t/18369.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 154.05, Diff 1040.00, Temp 210.00
10/27/2021 | 07:07 | 07:12 | 0.08 | 18369 | 18369 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 07:12 | 07:48 | 0.6 | 18369 | 18463 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18369.00 t/18463.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 156.67, Diff 1040.00, Temp 210.00
10/27/2021 | 07:48 | 08:17 | 0.48 | 18463 | 18463 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 08:17 | 08:52 | 0.58 | 18463 | 18557 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18463.00 t/18557.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 161.14, Diff 1040.00, Temp 210.00
10/27/2021 | 08:52 | 09:28 | 0.6 | 18557 | 18557 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 09:28 | 10:05 | 0.62 | 18557 | 18652 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18557.00 t/18652.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 154.05, Diff 1040.00, Temp 210.00
10/27/2021 | 10:05 | 10:31 | 0.43 | 18652 | 18652 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 10:31 | 10:45 | 0.23 | 18652 | 18672 | 20 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18652.00 t/18672.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 85.71, Diff 1040.00, Temp 210.00
10/27/2021 | 10:45 | 11:30 | 0.75 | 18672 | 18686 | 14 | LAT | 4: BHA 4 | 2J | Slide Drill f/18672.00 t/18686.00, TF 180.00G, w/WOB 37.00,Flow 350.00, Press 4890.00, Tq 21.00, ROP 18.67, Diff 1040.00, Temp 210.00
10/27/2021 | 11:30 | 11:58 | 0.47 | 18686 | 18746 | 60 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18686.00 t/18746.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 128.57, Diff 1040.00, Temp 210.00
10/27/2021 | 11:58 | 12:12 | 0.23 | 18746 | 18746 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 12:12 | 13:00 | 0.8 | 18746 | 18840 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18746.00 t/18840.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 117.50, Diff 1040.00, Temp 210.00
10/27/2021 | 13:00 | 13:29 | 0.48 | 18840 | 18840 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 13:29 | 14:03 | 0.57 | 18840 | 18929 | 89 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18840.00 t/18929.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 4890.00, Tq 21.00, ROP 157.06, Diff 1040.00, Temp 207.00
10/27/2021 | 14:03 | 14:05 | 0.03 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
10/27/2021 | 14:05 | 17:30 | 3.42 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 5A | Circulate
10/27/2021 | 17:30 | 18:50 | 1.33 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 3D | Back Ream out of Hole to 18,141
10/27/2021 | 18:50 | 24:00 | 5.17 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 3D | Back reaming out of Hole
10/27/2021 | 18:50 | 18:50 | 0 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 24A | Reset then try and pump presure at 7500psi Pop Off no popping ,Bleeded off manaully presure @ 0
10/27/2021 | 18:50 | 18:50 | 0 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 24A | Presure hit Pop off At 7600
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_28_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 161890
|  |  |  | 24hr Summary: |  | Reamed out, POOH and L/D BHA
|  |  |  | 24hr Lookahead: |  | Casing Ops
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18929 |  | 17088 |  | Csg Shoe MD(Usft): |  | 9920 |  | 600: | 5 | PV: | 2
End Depth (Usft): |  | 18929 |  | 18929 |  | OD (in): |  | 7.875 |  | 300: | 3 | YP: | 1
Total Drilled (Usft): |  |  |  | 1841 |  | Weight (ft/lbs): |  | 45 |  | 200: | 2 | Viscosity: | 26
Slide Drilled (Usft): |  |  |  | 46 | [5 empty] | 100: | 1 | Chlorides: | 180
Rotary Drilled (Usft): |  |  |  | 1795 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.01 / 2.60
Drlg/Circ Hrs: |  | 0.00 / 2.00 |  | 17.30 / 27.53 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 99.9
Slide Drilling Hrs: |  |  |  | 3.62 |  | SN: |  | 13618580 |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: |  |  |  | 13.68 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 238.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  |  |  | 131.18 / 12.72 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 3 |  | 52.33 |  | Grade In:
% Slide: |  |  |  | 2.5 |  | Grade Out: |  | 1-2-BT-S-X-I-NO-TD
% Rotary: |  |  |  | 97.5 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 T/S HS88 +.005 |  |  |  | 5.25 |  |  |  | 45.34 |  | 33.29 |  | 34.29
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.93
Pony Collar |  |  |  | 5.25 | 2.688 |  |  | 54.53 |  | 5.59 |  | 41.52
UBHO |  |  |  | 5.25 | 2.375 |  |  | 12.5 |  | 2.99 |  | 44.51
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.69 |  | 30.77 |  | 75.28
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.7 |  | 31.32 |  | 106.6
Tomax |  |  |  | 5 | 2.5 |  |  | 54.67 |  | 17.47 |  | 124.07
Crossover |  |  |  | 5.25 | 2.625 |  |  | 57.69 |  | 3.33 |  | 127.4
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 189.36 |  | 316.76
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 325.39
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2453.99 |  | 2779.38
Agitator |  |  |  | 5.25 | 2.5 |  |  | 55.38 |  | 21.41 |  | 2800.79
2800.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.02 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 25 | 80 | 318 | 350 | 4392.31 | 3361.54 | 68 | 298.46 | 172.69 | 196.15 | 13.13 | 7.2
Run | 106.42 | 24.84 | 73.85 | 311 | 348.42 | 3991.58 | 3117.89 | 68 | 260.11 | 177 | 199.89 | 10.36 | 6.3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 10/28/2021 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 10/28/2021 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 10/28/2021 |  | 7 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 10/28/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 10/28/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/28/2021 | 00:00 | 02:00 | 2 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 3D | Back Reaming
10/28/2021 | 02:00 | 03:00 | 1 | 18929 | 18929 | 0 | LAT | 4: BHA 4 | 6P | L/D BHA #4
10/28/2021 | 03:00 | 24:00 | 21 | 18929 | 18929 | 0 | LAT |  | 24B | Standby for casing ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 10_29_2021_DDR
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31179 / 21DD0216MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 17 |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Longitude: |  | 96° 40' 25.530" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 10/29/2021 |  |  | Report Time: |  | 00:00-06:00
|  |  |  | Daily Cost($): |  | 4750 |  |  | Well Cost($): |  | 166640
|  |  |  | 24hr Summary: |  | Running Casing
|  |  |  | 24hr Lookahead: |  | Land Casing and Cement
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18929 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV: | 2
End Depth (Usft): |  | 18929 |  | 18929 |  | OD (in): |  |  |  | 300: | 3 | YP: | 1
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 26
Slide Drilled (Usft): | [9 empty] | 100: | 1 | Chlorides: | 180
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids: | 0.01 / 2.60
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 99.9
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 7.0 / 238.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Christopher Beasley |  |  |  | Bobby Lewis
Jim Harrison |  | Robert E Wallace |  | Jason Smetters | [7 empty] | Casey Golan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 25 | 80 | 318 | 350 | 4392.31 | 3361.54 | 68 | 298.46 | 172.69 | 196.15 | 13.13 | 7.2
Run | 0 | 24.84 | 73.85 | 311 | 348.42 | 3991.58 | 3117.89 | 68 | 260.11 | 177 | 199.89 | 10.36 | 6.3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.5 | 5500 |  | 5200 |  | 0.0840 / 3.5280
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma (Standby) |  |  |  |  | 10/29/2021 |  | 4 |  | 4350 |  | 1 | 4350
Perdiem Per Hand |  |  |  |  | 10/29/2021 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 4750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
10/29/2021 | 00:00 | 06:00 | 6 | 18929 | 18929 | 0 | LAT |  | 24B | Casing Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 458.11 (Usft)
Well: |  |  | Bighorn Plains H02 | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 32.18 / 27.75 (klbs)
Job #: |  |  | LTX1148621 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 32.18 / 27.75 (klbs)
Date In: |  |  | 10/06/2021 | Depth In: |  | 108 | Total Drilled: |  | 2912.00 (Usft)
Date Out: |  |  | 10/07/2021 | Depth Out: |  | 3020 | Drilling / Circ Hours: |  | 7.18 / 2.58
Survey Offset: |  |  | 74
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47424 | U616S | 13.5 | 2 |  | 6 5/8 REG | 133.33 / 0.20 / 0.20 | 1.5 | 1.5
| 2 | PPM800023 | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 | 8 | 2 | 7.875 / 1.93 | 6 5/8 REG / 6 5/8 REG | 133.16 / 5.00 / 5.20 | 37.55 | 39.05
| 3 | GT801171 | Nortrak Stabilizer | 13 | 2.875 | 8.000 / 3.17 | 6 5/8 REG / 6 5/8 REG | 150.56 / 1.20 / 6.40 | 7.97 | 47.02
| 4 | GT8010518 | Pony NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 153.76 / 1.45 / 7.85 | 9.43 | 56.45
| 5 | 775213 | UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 0.54 / 8.39 | 3.63 | 60.08
| 6 | GT8030122 | NMDC | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 148.66 / 4.50 / 12.89 | 30.27 | 90.35
| 7 | GT8030218 | NMDC | 7.875 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 4.50 / 17.39 | 30 | 120.35
| 8 | GT7746830 | Crossover Sub | 7.75 | 3.25 | 6.750 / 1.69 | 4 1/2 IF / 6 5/8 REG | 120.12 / 0.40 / 17.79 | 3.33 | 123.68
| 9 |  | 11 Jts - HWDP | 5 | 3.8 |  | 4 1/2 IF / 4 1/2 IF | 43.00 / 14.38 / 32.18 | 334.43 | 458.11
| 10 | [8 empty] | 458.11
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | U616S | New | 0-1-NO-A-X-I-NO-TD | 2912
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.50 NBS HPW -.014 NBS 13 |  |  | PDCI / 7/8 5.9 | 5.90 / 1.50 |  | 13 | 8.38 | 200 | 1390
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
21870 |  |  | 900 | 100 |  | 400-900 | 0.16 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPW |  | -0.014
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 | 13 |  | 4 |  |  | 3.83
3 |  |  | Nortrak Stabilizer | 13 |  | 5.5 |  |  | 42.75

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2726.54 (Usft)
Well: |  |  | Bighorn Plains H02 | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 48.97 / 42.24 (klbs)
Job #: |  |  | LTX1148621 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 48.97 / 42.24 (klbs)
Date In: |  |  | 10/17/2021 | Depth In: |  | 3020 | Total Drilled: |  | 6908.00 (Usft)
Date Out: |  |  | 10/19/2021 | Depth Out: |  | 9928 | Drilling / Circ Hours: |  | 35.15 / 6.62
Survey Offset: |  |  | 64 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 56410 | SPL613 | 9.875 | 2 |  | 6 5/8 REG | 250.00 / 0.25 / 0.25 | 1 | 1
| 2 | PPM800035 | 7/8 5.9 2.0 TS HPW .001 | 8 | 2 | 8.000 / 1.93 | 6 5/8 REG / 6 5/8 REG | 131.75 / 5.00 / 5.25 | 37.95 | 38.95
| 3 | GT8010518 | Pony NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 153.76 / 1.45 / 6.70 | 9.43 | 48.38
| 4 | 775213 | UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 0.54 / 7.24 | 3.63 | 52.01
| 5 | GT8030122 | NMDC | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 148.66 / 4.50 / 11.74 | 30.27 | 82.28
| 6 | GT8030218 | NMDC | 7.875 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 4.50 / 16.24 | 30 | 112.28
| 7 | GT80461428 | Crossover Sub | 7.875 | 3.25 | 6.500 / 1.59 | 4 1/2 XH / 6 5/8 REG | 119.05 / 0.40 / 16.64 | 3.36 | 115.64
| 8 | RIG | 6 Jts 6 1/2 DC | 6.5 | 2.75 |  | 4 1/2 XH / 4 1/2 XH | 95.00 / 17.69 / 34.33 | 186.2 | 301.84
| 9 | GT6744416 | Crossover Sub | 6.688 | 2.875 | 6.750 / 1.69 | 4 1/2 IF / 4 1/2 XH | 78.12 / 0.27 / 34.61 | 3.52 | 305.36
| 10 |  | 11 Jts - HWDP | 5 | 3.8 |  | 4 1/2 IF / 4 1/2 IF | 43.00 / 14.36 / 48.97 | 334.06 | 639.42
| 11 |  | 22 Stds 5 DP | 5 | 3.8 |  | 4 1/2 IF / 4 1/2 IF | 19.90 / 41.04 / 90.02 | 2062.46 | 2701.88
| 12 | PG675-0014 | Agitator | 6.75 | 2.5 | 6.625 / 1.86 | 4 1/2 IF / 4 1/2 IF | 81.10 / 2.00 / 92.02 | 24.66 | 2726.54
| 13 | [8 empty] | 2726.54
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New |  | 6908
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.0 TS HPW .001 |  |  | PDCI / 7/8 5.9 | 5.97 / 2.00 |  | 0 | 8.38 | 200 | 1390
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
21870 |  |  | 900 | 80 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPW |  | 0.001
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2807.08 (Usft)
Well: |  |  | Bighorn Plains H02 | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 9.97 / 8.37 (klbs)
Job #: |  |  | LTX1148621 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 9.97 / 8.37 (klbs)
Date In: |  |  | 10/21/2021 | Depth In: |  | 9928 | Total Drilled: |  | 7160.00 (Usft)
Date Out: |  |  | 10/25/2021 | Depth Out: |  | 17088 | Drilling / Circ Hours: |  | 53.47 / 18.63
Survey Offset: |  |  | 64 | Gamma Offset: |  | 51
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13635755 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250018 | 6/7 11.7 2.12 T/S HS88 -.013 | 5.25 |  | 5.250 / 2.04 | XT39 / 3 1/2REG | 45.34 / 1.51 / 1.56 | 33.39 | 34.39
| 3 | BTI 1 | BTI | 4.875 | 2.125 |  |  | 42.13 / 0.07 / 1.63 | 1.64 | 36.03
| 4 | GT52-10-654 | Pony Collar | 5.25 | 2.688 | 5.250 / 1.77 | XT39 / XT39 | 54.53 / 0.30 / 1.94 | 5.59 | 41.62
| 5 | 500029 | UHBO | 5.25 | 2.375 |  |  | 12.50 / 0.04 / 1.98 | 2.99 | 44.61
| 6 | GT52-30-588 | Non Mag Drill Collar (NO HARDBANDING) | 5 | 2.688 |  | XT39 / XT39 | 48.69 / 1.50 / 3.47 | 30.77 | 75.38
| 7 | GT52-10-465 | Pony Collar | 5.25 | 2.688 |  | XT39 / XT39 | 50.66 / 0.28 / 3.76 | 5.59 | 80.97
| 8 | GT52-30-618 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 |  | XT39 / XT39 | 48.70 / 1.53 / 5.28 | 31.32 | 112.29
| 9 | A52068 | Tomax | 5 | 2.5 |  | XT39 / XT39 | 54.67 / 0.96 / 6.24 | 17.47 | 129.76
| 10 | GT52331430 | Crossover | 5.25 | 2.625 |  | CET43 / XT39 | 57.69 / 0.19 / 6.43 | 3.33 | 133.09
| 11 | Rig | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.14 / 9.57 | 189.36 | 322.45
| 12 | 579 | Drill-N-Ream | 5.375 | 2.625 | 5.375 / 1.09 | CET43 / CET43 | 46.35 / 0.40 / 9.97 | 8.63 | 331.08
| 13 | Rig 26 | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 17.84 / 43.78 / 53.75 | 2453.99 | 2785.07
| 14 | PG525-0050 | Agitator | 5 | 2.5 |  | CET43 / CET43 | 55.38 / 1.22 / 54.97 | 22.01 | 2807.08
| 15 | [8 empty] | 2807.08
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 2-3-BT-N-X-I-CT-DMF | 7160
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 11.7 2.12 T/S HS88 -.013 |  |  | PDCI / 6/7 11.7 | 4.14 / 2.12 |  | 0 | 5.56 | 200 | 2905
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
7623 |  |  | 1000 | 80 |  | 150-350 | 0.89 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluid | HS88 |  | 0.013
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2800.79 (Usft)
Well: |  |  | Bighorn Plains H02 | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 9.68 / 8.46 (klbs)
Job #: |  |  | LTX1148621 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 9.68 / 8.46 (klbs)
Date In: |  |  | 10/25/2021 | Depth In: |  | 17088 | Total Drilled: |  | 1841.00 (Usft)
Date Out: |  |  | 10/28/2021 | Depth Out: |  | 18929 | Drilling / Circ Hours: |  | 17.30 / 27.53
Survey Offset: |  |  | 60 | Gamma Offset: |  | 51
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618580 | GTD64M | 6.75 | 2 |  | 3 1/2 IF | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250010 | 6/7 8.8 2.12 T/S HS88 +.005 | 5.25 |  | 5.250 | XT39 / 3 1/2REG | 45.34 / 1.51 / 1.56 | 33.29 | 34.29
| 3 | BTI 1 | BTI | 4.875 | 2.125 |  |  | 42.13 / 0.07 / 1.63 | 1.64 | 35.93
| 4 | GT52-10-654 | Pony Collar | 5.25 | 2.688 | 5.250 / 1.77 | XT39 / XT39 | 54.53 / 0.30 / 1.93 | 5.59 | 41.52
| 5 | 500029 | UBHO | 5.25 | 2.375 |  |  | 12.50 / 0.04 / 1.97 | 2.99 | 44.51
| 6 | GT52-30-588 | Non Mag Drill Collar (NO HARDBANDING) | 5 | 2.688 |  | XT39 / XT39 | 48.69 / 1.50 / 3.47 | 30.77 | 75.28
| 7 | GT52-30-618 | Non Mag Drill Collar (NO HARDBANDING) | 5.25 | 2.688 |  | XT39 / XT39 | 48.70 / 1.53 / 4.99 | 31.32 | 106.6
| 8 | A52068 | Tomax | 5 | 2.5 |  | XT39 / XT39 | 54.67 / 0.96 / 5.95 | 17.47 | 124.07
| 9 | GT52331430 | Crossover | 5.25 | 2.625 |  | CET43 / XT39 | 57.69 / 0.19 / 6.14 | 3.33 | 127.4
| 10 | Rig | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.14 / 9.28 | 189.36 | 316.76
| 11 | 579 | Drill-N-Ream | 5.375 | 2.625 | 5.375 / 1.09 | CET43 / CET43 | 46.35 / 0.40 / 9.68 | 8.63 | 325.39
| 12 | Rig 26 | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 17.84 / 43.78 / 53.46 | 2453.99 | 2779.38
| 13 | PG525-0055 | Agitator | 5.25 | 2.5 |  | CET43 / CET43 | 55.38 / 1.19 / 54.65 | 21.41 | 2800.79
| 14 | [8 empty] | 2800.79
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M |  | 1-2-BT-S-X-I-NO-TD | 1841
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 T/S HS88 +.005 |  |  | PDCI / 6/7 8.8 | 4.02 / 2.12 |  | 0 | 5.62 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 800 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluid | HS88 |  | 0.005
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31-179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Longitude: |  | 96° 40' 25.530" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 100.00/100.00/100.00
Date In: |  | 10/06/2021 15:40 |  | SN: |  | PPM800023 |  |  |  | WOB Rotate (klbs): |  | 9.00
Date Out: |  | 10/07/2021 03:25 |  | Description: |  | 7/8 5.9 1.50 NBS HPW -.014 NBS 13 |  |  |  | WOB Slide (klbs): |  | 9.72
Depth In/Out(Usft): |  | 108.00 / 3020.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 89.39
Inc In/Out: |  | 0.29 / 17.12 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 875.52
Azi In/Out: |  | 334.68 / 270.67 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1447.76
Total Drilled (Usft): |  | 2912 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1919.4
%Slide (Ftg): |  | 12.71 |  | Bit to Bend (Usft): |  | 5.9 |  |  |  | Tq On Btm (kftlbs): |  | 4.76
%Slide (Time): |  | 23.94 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 370 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 900
Slide Hours: |  | 1.72 |  | Stab to Bit (Usft): |  | 2.33 |  |  |  | Bit Data
%Rotary (Ftg): |  | 87.29 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 76.01 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2542 |  | Fishneck OD (in): |  | 7.875 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 5.46 |  | Length (Usft): |  | 37.55 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 7.18 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 2.58 / 11.75 |  | Rev per Gal: |  | 0.16 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 215.12 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
Rot ROP (Usft/hr): |  | 465.57 |  | Stator Vendor/Type/Fit: |  | Abaco / HPW / -0.014 |  |  |  | Drill Hrs: |  | 7.18
Avg ROP (Usft/hr): |  | 405.57 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.58
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
1 / 1 | 1 / 1 | 1 / 1 |  | 0/100 |  | 1 | 1 | 8.4 | 460 | WBM | 0.4 | 0.01 | 100
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
74 | [11 empty] | 0.00 / 2.32
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 47424 |  | 13.5 | 2 |  |  | 133.33 | 1.5 | 1.5
7/8 5.9 1.50 NBS HPW -.014 NBS 13 0.00 |  |  |  | PPM800023 |  | 8 | 2 |  |  | 133.16 | 37.55 | 39.05
Nortrak Stabilizer 0.00 |  |  |  | GT801171 |  | 13 | 2.875 |  |  | 150.56 | 7.97 | 47.02
Pony NMDC 0.00 |  |  |  | GT8010518 |  | 8 | 3.25 |  |  | 153.76 | 9.43 | 56.45
UBHO Sub 0.00 |  |  |  | 775213 |  | 7.75 | 2.875 |  |  | 150 | 3.63 | 60.08
NMDC 0.00 |  |  |  | GT8030122 |  | 7.938 | 3.25 |  |  | 148.66 | 30.27 | 90.35
NMDC 0.00 |  |  |  | GT8030218 |  | 7.875 | 3.25 |  |  | 150 | 30 | 120.35
Crossover Sub 0.00 |  |  |  | GT7746830 |  | 7.75 | 3.25 |  |  | 120.12 | 3.33 | 123.68
11 Jts - HWDP 0.00 | [5 empty] | 5 | 3.8 |  |  | 43 | 334.43 | 458.11
0.00 | [11 empty] | 458.11
Additional Comments
Reason POOH ? TD Surface Section How did motor drain - Drained well with no abnormal play Visual wear - None Run Description - Drilled and slid well. Built up to tangent and held well with no abnormal slides required Max temp on run - 115 How Many Stalls and what pressure was seen on stalls - 0 Motor Yields - 7.5 Max Drilling Diff - 650 Average Drilling Diff - 525 Condition of bit on surface - Worn Cutters, no abnormal wear. Will Re-Run Bit on upcoming surface section
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Longitude: |  | 96° 40' 25.530" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 104.00/181.99/244.00
Date In: |  | 10/17/2021 09:30 |  | SN: |  | PPM800035 |  |  |  | WOB Rotate (klbs): |  | 24.00
Date Out: |  | 10/19/2021 17:45 |  | Description: |  | 7/8 5.9 2.0 TS HPW .001 |  |  |  | WOB Slide (klbs): |  | 18.57
Depth In/Out(Usft): |  | 3020.00 / 9928.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 77.48
Inc In/Out: |  | 17.12 / 23.22 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 789.65
Azi In/Out: |  | 270.67 / 160.31 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 3714.25
Total Drilled (Usft): |  | 6908 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4024.79
%Slide (Ftg): |  | 12.62 |  | Bit to Bend (Usft): |  | 5.97 |  |  |  | Tq On Btm (kftlbs): |  | 9.24
%Slide (Time): |  | 57.24 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 872 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 900
Slide Hours: |  | 20.12 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 87.38 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 42.76 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6036 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 15.03 |  | Length (Usft): |  | 37.95 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 35.15 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 6.62 / 56.25 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 43.34 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 401.6 |  | Stator Vendor/Type/Fit: |  | Abaco / HPW / 0.001 |  |  |  | Drill Hrs: |  | 35.15
Avg ROP (Usft/hr): |  | 196.53 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 6.62
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
31 / 20 | 16 / 12 | 6 / 5 |  | 70/30 |  | 11 | 9 | 9.2 | 58000 | OBM | 9.6 | 0.01 | 244
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
64 | 60 | [8 empty] | 5 |  | 4.60 / 5.93
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 56410 |  | 9.875 | 2 |  |  | 250 | 1 | 1
7/8 5.9 2.0 TS HPW .001 0.00 |  |  |  | PPM800035 |  | 8 | 2 |  |  | 131.75 | 37.95 | 38.95
Pony NMDC 0.00 |  |  |  | GT8010518 |  | 8 | 3.25 |  |  | 153.76 | 9.43 | 48.38
UBHO Sub 0.00 |  |  |  | 775213 |  | 7.75 | 2.875 |  |  | 150 | 3.63 | 52.01
NMDC 0.00 |  |  |  | GT8030122 |  | 7.938 | 3.25 |  |  | 148.66 | 30.27 | 82.28
NMDC 0.00 |  |  |  | GT8030218 |  | 7.875 | 3.25 |  |  | 150 | 30 | 112.28
Crossover Sub 0.00 |  |  |  | GT80461428 |  | 7.875 | 3.25 |  |  | 119.05 | 3.36 | 115.64
6 Jts 6 1/2 DC 0.00 |  |  |  | RIG |  | 6.5 | 2.75 |  |  | 95 | 186.2 | 301.84
Crossover Sub 0.00 |  |  |  | GT6744416 |  | 6.688 | 2.875 |  |  | 78.12 | 3.52 | 305.36
11 Jts - HWDP 0.00 | [5 empty] | 5 | 3.8 |  |  | 43 | 334.06 | 639.42
22 Stds 5 DP 0.00 | [5 empty] | 5 | 3.8 |  |  | 19.9 | 2062.46 | 2701.88
Agitator 0.00 |  |  |  | PG675-0014 |  | 6.75 | 2.5 |  |  | 81.1 | 24.66 | 2726.54
-1.00 | [11 empty] | 2726.54
Additional Comments
? Reason POOH - TD of intermediate Curve ? How did motor drain - Drained good, no problems seen ? Visual wear - 70% of kick pad missing. Pics attached ? Run Description - Hold 18* and drop to verticle. Build curve to 25 and chalk @ 5*/100 ? Max temp on run- 244 ? How Many Stalls and what pressure was seen on stalls - none ? Motor Yields - Hold 18* (8-12) Curve (4.1-5.90 ? Max Drilling Diff - 700 ? Average Drilling Diff ?500 ? Condition of bit on surface - Bit was green
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Longitude: |  | 96° 40' 25.530" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 224.00/257.00/279.00
Date In: |  | 10/21/2021 15:30 |  | SN: |  | PPM250018 |  |  |  | WOB Rotate (klbs): |  | 26.00
Date Out: |  | 10/25/2021 20:15 |  | Description: |  | 6/7 11.7 2.12 T/S HS88 -.013 |  |  |  | WOB Slide (klbs): |  | 31.46
Depth In/Out(Usft): |  | 9928.00 / 17088.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 76.00
Inc In/Out: |  | 23.22 / 87.34 |  | Model: |  | 6/7 11.7 |  |  |  | Flow Rate (gpm): |  | 348.92
Azi In/Out: |  | 160.29 / 151.99 |  | Lobes / Stages: |  | 6/7 / 11.7 |  |  |  | Off Btm Press (psi): |  | 3247.12
Total Drilled (Usft): |  | 7160 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4079.96
%Slide (Ftg): |  | 14.57 |  | Bit to Bend (Usft): |  | 4.14 |  |  |  | Tq On Btm (kftlbs): |  | 11.92
%Slide (Time): |  | 31.18 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1043 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 16.67 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 85.43 |  | Kickpad OD (in): |  | 5.562 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 68.83 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 6117 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 36.8 |  | Length (Usft): |  | 33.39 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 53.47 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 18.63 / 100.75 |  | Rev per Gal: |  | 0.89 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 62.57 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 2-3-BT-N-X-I-CT-DMF
Rot ROP (Usft/hr): |  | 166.22 |  | Stator Vendor/Type/Fit: |  | PV Fluid / HS88 / 0.013 |  |  |  | Drill Hrs: |  | 53.47
Avg ROP (Usft/hr): |  | 133.91 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 18.63
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
31 / 20 | 16 / 12 | 6 / 5 |  | 70/30 |  | 11 | 9 | 9.2 | 58000 | OBM | 9.6 | 0.01 | 279
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
64 | 51 | [8 empty] | 8 |  | 12.00 / 12.72
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13635755 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 11.7 2.12 T/S HS88 -.013 0.00 |  |  |  | PPM250018 |  | 5.25 |  |  |  | 45.34 | 33.39 | 34.39
BTI 0.00 |  |  |  | BTI 1 |  | 4.875 | 2.125 |  |  | 42.13 | 1.64 | 36.03
Pony Collar 0.00 |  |  |  | GT52-10-654 |  | 5.25 | 2.688 |  |  | 54.53 | 5.59 | 41.62
UHBO 0.00 |  |  |  | 500029 |  | 5.25 | 2.375 |  |  | 12.5 | 2.99 | 44.61
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-588 |  | 5 | 2.688 |  |  | 48.69 | 30.77 | 75.38
Pony Collar 0.00 |  |  |  | GT52-10-465 |  | 5.25 | 2.688 |  |  | 50.66 | 5.59 | 80.97
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-618 |  | 5.25 | 2.688 |  |  | 48.7 | 31.32 | 112.29
Tomax 0.00 |  |  |  | A52068 |  | 5 | 2.5 |  |  | 54.67 | 17.47 | 129.76
Crossover 0.00 |  |  |  | GT52331430 |  | 5.25 | 2.625 |  |  | 57.69 | 3.33 | 133.09
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3.8 |  |  | 16.6 | 189.36 | 322.45
Drill-N-Ream 0.00 |  |  |  | 579 |  | 5.375 | 2.625 |  |  | 46.35 | 8.63 | 331.08
26 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig 26 |  | 4.5 | 3.8 |  |  | 17.84 | 2453.99 | 2785.07
Agitator 0.00 |  |  |  | PG525-0050 |  | 5 | 2.5 |  |  | 55.38 | 22.01 | 2807.08
0.00 | [11 empty] | 2807.08
Additional Comments
Reason POOH ? ROP Went from 180 to Zero and Torque climbed to 22k, Attempted To get it drill no Luck. How did motor drain ? Motor did not drain at all when pulled above the table rotated bit box With chain tongs freely left and to the right Visual wear ? No abnormal wear observed on surface. Run Description -. Motor did great in curve ,held good in the Lateral with minimal slides to maintain dip and hole Azi. In the curve the motor yielded 16/100. Motor performed was good in the lateral as well keeping slides to 6 to 15 ft motor yielding 15s Max temp on run- 237 How Many Stalls and what pressure was seen on stalls - 0 Motor Yields ? 8/100 Max Drilling Diff - 855 Average Drilling Diff - 550 Condition of bit on surface ,1 Plugged Jet with rubber -- 2-3-BT-N-X-I-CT-DMF
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1148621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31179 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 15' 25.173" N |  |  | Well: |  | Bighorn Plains H02
|  |  |  | Longitude: |  | 96° 40' 25.530" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 207.00/211.00/212.00
Date In: |  | 10/25/2021 22:40 |  | SN: |  | PPM250010 |  |  |  | WOB Rotate (klbs): |  | 24.00
Date Out: |  | 10/28/2021 03:00 |  | Description: |  | 6/7 8.8 2.12 T/S HS88 +.005 |  |  |  | WOB Slide (klbs): |  | 30.00
Depth In/Out(Usft): |  | 17088.00 / 18929.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 87.34 / 84.52 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 350
Azi In/Out: |  | 151.98 / 154.40 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3656.45
Total Drilled (Usft): |  | 1841 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4604.52
%Slide (Ftg): |  | 2.50 |  | Bit to Bend (Usft): |  | 4.02 |  |  |  | Tq On Btm (kftlbs): |  | 21
%Slide (Time): |  | 20.92 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 46 |  | Bearing Gap (in): |  | 0.9 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 3.62 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 97.50 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 79.08 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 1795 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 13.68 |  | Length (Usft): |  | 33.29 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 17.30 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 27.53 / 52.33 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In:
Slide ROP (Usft/hr): |  | 12.71 |  | # Stalls / Pressure: |  | 1 / 7600.00 |  |  |  | Grade Out: |  | 1-2-BT-S-X-I-NO-TD
Rot ROP (Usft/hr): |  | 131.21 |  | Stator Vendor/Type/Fit: |  | PV Fluid / HS88 / 0.005 |  |  |  | Drill Hrs: |  | 17.30
Avg ROP (Usft/hr): |  | 106.42 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 27.53
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
39 / 25 | 16 / 12 | 6 / 5 |  | 75/25 |  | 14 | 11 | 8.3 | 54000 | WBM | 7.8 | 0.01 | 212
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
60 | 51 | [8 empty] | 8 |  | 12.00 / 2.96
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618580 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 8.8 2.12 T/S HS88 +.005 0.00 |  |  |  | PPM250010 |  | 5.25 |  |  |  | 45.34 | 33.29 | 34.29
BTI 0.00 |  |  |  | BTI 1 |  | 4.875 | 2.125 |  |  | 42.13 | 1.64 | 35.93
Pony Collar 0.00 |  |  |  | GT52-10-654 |  | 5.25 | 2.688 |  |  | 54.53 | 5.59 | 41.52
UBHO 0.00 |  |  |  | 500029 |  | 5.25 | 2.375 |  |  | 12.5 | 2.99 | 44.51
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-588 |  | 5 | 2.688 |  |  | 48.69 | 30.77 | 75.28
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT52-30-618 |  | 5.25 | 2.688 |  |  | 48.7 | 31.32 | 106.6
Tomax 0.00 |  |  |  | A52068 |  | 5 | 2.5 |  |  | 54.67 | 17.47 | 124.07
Crossover 0.00 |  |  |  | GT52331430 |  | 5.25 | 2.625 |  |  | 57.69 | 3.33 | 127.4
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3.8 |  |  | 16.6 | 189.36 | 316.76
Drill-N-Ream 0.00 |  |  |  | 579 |  | 5.375 | 2.625 |  |  | 46.35 | 8.63 | 325.39
26 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig 26 |  | 4.5 | 3.8 |  |  | 17.84 | 2453.99 | 2779.38
Agitator 0.00 |  |  |  | PG525-0055 |  | 5.25 | 2.5 |  |  | 55.38 | 21.41 | 2800.79
0.00 | [11 empty] | 2800.79
Failure Information
Incident | YES | Hrs Before Incident |  |  | Tripped For Incident |  | NO | BHA SN | PPM250010: 6/7 8.8 2.12 T/S HS88 +.005 |  | MWD SN
LIH | NO | NPT |  |  | Catastrophic Inci. |  | NO | MOTOR Inci. | YES |  | MWD Inci. | NO
Closed | NO | EDR Review |  | NO | Surface Fail |  | NO | MTBF Attrib. | NO |  | Motor Cat
Operations at Time of Incident
Troubleshooting Performed
Surface Findings
Additional Comments
? Reason POOH - TD of Well ? How did motor drain - Was not able to drain ? Visual wear ? Motor was parted 3.30 from the bit box ? Run Description - was on a mud cap and water. Tripped in to 15915. From there reamed to 16764 with 65 RPMs and 10-14k tor. 16764 to bottom (17088) reaming was ratty and tight. BHA got hung up and was stalling out top drive. Max tor was 22-28k max overpull was 120k. Driling tor was 16-22k and WOB was 18-24. Drilled to Td with some top drive stalls of 22k. No pressure stalls. After TD a 7 hour clean up cycle was preformed with 24k of tor. Back reamed out with 22-28k tor to 18173 where the motor presured up to 7600. Was able to be presure bled off and dry reamed out of the hole to 14096. ? Max temp on run- 212 ? How Many Stalls and what pressure was seen on stalls - 1 stall and held 6900-7600 psi for 30 minutes untill it was able to get bled off ? Motor Yields - 12-19 ? Max Drilling Diff - 800 ? Average Drilling Diff ? 600 ? Condition of bit on surface -
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2912
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 370
Well Name: |  |  |  |  | Bighorn Plains H02 |  |  | Survey / Gamma Offset: |  |  |  |  | 74.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 153.98 |  | Rotate: |  | 2542
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
10/06/2021 | 15:40 | 16:28 | 0.8 | 108 | 215 | 107 | Rotate |  | 200 | 0.54 | 334.68 | 200 | 0.85 | -0.4 | 0.85 | 0.27 |  |  | 5 | 30 | 400 | 1 | 133.75 | 400 | 400 | 0 | 100 | 45 | 45 | 45
10/06/2021 | 16:28 | 16:40 | 0.2 | 215 | 274 | 59 | Rotate | Drilling Parameters WOB: 7; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 460; Drilling Parameters Tq: 2; Drilling Parameters ROP: 295 | 500 | 500 | 0 | 100 | 50 | 50 | 50
10/06/2021 | 16:44 | 17:00 | 0.26667 | 274 | 367 | 93 | Rotate |  | 293 | 0.85 | 329.26 | 292.99 | 1.84 | -0.94 | 1.84 | 0.34 |  |  | 8 | 60 | 500 | 2 | 348.75 | 800 | 700 | 100 | 100 | 50 | 50 | 50
10/06/2021 | 17:05 | 17:17 | 0.2 | 367 | 458 | 91 | Rotate |  | 384 | 0.94 | 332.3 | 383.98 | 3.08 | -1.64 | 3.08 | 0.11 |  |  | 8 | 70 | 600 | 3 | 455 | 900 | 900 | 0 | 100 | 55 | 55 | 55
10/06/2021 | 17:22 | 17:36 | 0.23333 | 458 | 552 | 94 | Rotate |  | 478 | 0.94 | 322.09 | 477.97 | 4.37 | -2.47 | 4.37 | 0.18 |  |  | 10 | 100 | 900 | 5 | 402.86 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 17:42 | 17:51 | 0.15 | 552 | 646 | 94 | Rotate |  | 572 | 0.9 | 332.51 | 571.95 | 5.64 | -3.28 | 5.64 | 0.18 |  |  | 10 | 100 | 900 | 5 | 626.67 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 17:57 | 18:08 | 0.18333 | 646 | 740 | 94 | Rotate |  | 665 | 1.16 | 332.39 | 664.94 | 7.12 | -4.06 | 7.12 | 0.28 |  |  | 10 | 100 | 900 | 5 | 512.73 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 18:38 | 18:46 | 0.13333 | 740 | 833 | 93 | Rotate |  | 759 | 1.22 | 323.7 | 758.92 | 8.77 | -5.09 | 8.77 | 0.2 |  |  | 10 | 100 | 900 | 5 | 697.5 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 18:50 | 18:56 | 0.1 | 833 | 926 | 93 | Rotate |  | 852 | 1.22 | 331.07 | 851.9 | 10.43 | -6.15 | 10.43 | 0.17 |  |  | 10 | 100 | 900 | 5 | 930 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:00 | 19:02 | 0.033333 | 926 | 930 | 4 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:02 | 19:05 | 0.05 | 930 | 945 | 15 | Slide | TTF: 240; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 300 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:05 | 19:10 | 0.083333 | 945 | 1020 | 75 | Rotate |  | 946 | 1.29 | 298.46 | 945.88 | 11.81 | -7.57 | 11.81 | 0.75 |  |  | 10 | 80 | 900 | 5 | 900 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:14 | 19:16 | 0.033333 | 1020 | 1026 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 180 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:16 | 19:21 | 0.083333 | 1026 | 1046 | 20 | Slide | 260 | 1040 | 1.88 | 277.23 | 1039.84 | 12.51 | -10.03 | 12.51 | 0.88 |  |  | 10 |  | 900 | 5 | 240 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:21 | 19:26 | 0.083333 | 1046 | 1114 | 68 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 816 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:29 | 19:32 | 0.05 | 1114 | 1120 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:32 | 19:36 | 0.066667 | 1120 | 1145 | 25 | Slide | 270 | 1133 | 3.03 | 273.04 | 1132.75 | 12.83 | -14 | 12.83 | 1.25 |  |  | 10 |  | 900 | 5 | 375 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:36 | 19:42 | 0.1 | 1145 | 1207 | 62 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 620 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:45 | 19:47 | 0.033333 | 1207 | 1214 | 7 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 210 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:47 | 19:50 | 0.05 | 1214 | 1229 | 15 | Slide | 270 | 1228 | 3.7 | 265.72 | 1227.59 | 12.74 | -19.56 | 12.74 | 0.84 |  |  | 10 |  | 900 | 5 | 300 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 19:50 | 19:57 | 0.11667 | 1229 | 1302 | 73 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 625.71 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:00 | 20:08 | 0.13333 | 1302 | 1396 | 94 | Rotate |  | 1322 | 3.88 | 262.8 | 1321.38 | 12.11 | -25.74 | 12.11 | 0.28 |  |  | 10 | 80 | 900 | 5 | 705 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:11 | 20:19 | 0.13333 | 1396 | 1489 | 93 | Rotate |  | 1415 | 3.75 | 260.36 | 1414.18 | 11.21 | -31.86 | 11.21 | 0.22 |  |  | 10 | 80 | 900 | 5 | 697.5 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:21 | 20:30 | 0.15 | 1489 | 1583 | 94 | Rotate |  | 1509 | 3.69 | 259.33 | 1507.98 | 10.13 | -37.86 | 10.13 | 0.1 |  |  | 10 | 80 | 900 | 5 | 626.67 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:33 | 20:36 | 0.05 | 1583 | 1600 | 17 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 340 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:36 | 20:38 | 0.033333 | 1600 | 1610 | 10 | Slide | 0 | 1602 | 3.84 | 258.28 | 1600.78 | 8.95 | -43.85 | 8.95 | 0.18 |  |  | 10 |  | 900 | 5 | 300 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:38 | 20:45 | 0.11667 | 1610 | 1676 | 66 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 565.71 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:48 | 20:51 | 0.05 | 1676 | 1685 | 9 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 180 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 20:51 | 21:00 | 0.15 | 1685 | 1710 | 25 | Slide | 0 | 1696 | 4.76 | 254.48 | 1694.51 | 7.26 | -50.69 | 7.26 | 1.02 |  |  | 10 |  | 900 | 5 | 166.67 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:00 | 21:06 | 0.1 | 1710 | 1770 | 60 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 600 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:10 | 21:12 | 0.033333 | 1770 | 1784 | 14 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 420 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:12 | 21:18 | 0.1 | 1784 | 1809 | 25 | Slide | 0 | 1790 | 5.94 | 255.04 | 1788.1 | 4.97 | -59.15 | 4.97 | 1.26 |  |  | 10 |  | 900 | 5 | 250 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:18 | 21:23 | 0.083333 | 1809 | 1864 | 55 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 660 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:27 | 21:30 | 0.05 | 1864 | 1874 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 200 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:35 | 21:41 | 0.1 | 1874 | 1957 | 83 | Rotate |  | 1883 | 7.23 | 257.83 | 1880.49 | 2.49 | -69.52 | 2.49 | 1.43 |  |  | 10 | 100 | 900 | 5 | 830 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:30 | 21:35 | 0.083333 | 1874 | 1874 |  | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:44 | 21:47 | 0.05 | 1957 | 1965 | 8 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 160 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:47 | 21:51 | 0.066667 | 1965 | 1980 | 15 | Slide | 0 | 1977 | 8.45 | 259.7 | 1973.61 | 0.01 | -82.1 | 0.01 | 1.33 |  |  | 10 |  | 900 | 5 | 225 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 21:51 | 21:57 | 0.1 | 1980 | 2051 | 71 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 710 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:00 | 22:02 | 0.033333 | 2051 | 2058 | 7 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:02 | 22:07 | 0.083333 | 2058 | 2083 | 25 | Slide | 20 | 2070 | 8.97 | 262.33 | 2065.54 | -2.18 | -96.01 | -2.18 | 0.7 |  |  | 10 |  | 900 | 5 | 300 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:07 | 22:12 | 0.083333 | 2083 | 2144 | 61 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 732 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:16 | 22:19 | 0.05 | 2144 | 2151 | 7 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 140 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:19 | 22:27 | 0.13333 | 2151 | 2181 | 30 | Slide | 20 | 2164 | 10.26 | 265.97 | 2158.21 | -3.75 | -111.62 | -3.75 | 1.52 |  |  | 10 |  | 900 | 5 | 225 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:27 | 22:33 | 0.1 | 2181 | 2238 | 57 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 570 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:36 | 22:39 | 0.05 | 2238 | 2244 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:39 | 22:45 | 0.1 | 2244 | 2274 | 30 | Slide | 20 | 2258 | 11.5 | 268.61 | 2250.52 | -4.56 | -129.34 | -4.56 | 1.42 |  |  | 10 |  | 900 | 5 | 300 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:45 | 22:50 | 0.083333 | 2274 | 2332 | 58 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 696 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:52 | 22:55 | 0.05 | 2332 | 2338 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 22:55 | 23:03 | 0.13333 | 2338 | 2368 | 30 | Slide | 0 | 2352 | 12.32 | 268.45 | 2342.5 | -5.06 | -148.73 | -5.06 | 0.87 |  |  | 10 |  | 900 | 5 | 225 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:03 | 23:10 | 0.11667 | 2368 | 2426 | 58 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 497.14 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:13 | 23:16 | 0.05 | 2426 | 2432 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:16 | 23:25 | 0.15 | 2432 | 2462 | 30 | Slide | 0 | 2446 | 14.38 | 265.37 | 2433.95 | -6.28 | -170.39 | -6.28 | 2.32 |  |  | 10 |  | 900 | 5 | 200 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:25 | 23:30 | 0.083333 | 2462 | 2520 | 58 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 696 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:34 | 23:37 | 0.05 | 2520 | 2526 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:37 | 23:45 | 0.13333 | 2526 | 2556 | 30 | Slide | 0 | 2540 | 15.6 | 264.38 | 2524.75 | -8.46 | -194.61 | -8.46 | 1.33 |  |  | 10 |  | 900 | 5 | 225 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:45 | 23:50 | 0.083333 | 2556 | 2614 | 58 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 696 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:54 | 23:57 | 0.05 | 2614 | 2620 | 6 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 120 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/06/2021 | 23:57 | 24:00 | 0.05 | 2620 | 2629 | 9 | Slide | TTF: 20; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 180 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:00 | 00:09 | 0.15 | 2629 | 2650 | 21 | Slide | 20 | 2634 | 16.66 | 265.47 | 2615.05 | -10.76 | -220.62 | -10.76 | 1.17 |  |  | 10 |  | 900 | 5 | 140 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:09 | 00:14 | 0.083333 | 2650 | 2708 | 58 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 696 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:17 | 00:27 | 0.16667 | 2708 | 2802 | 94 | Rotate |  | 2728 | 17.17 | 268.08 | 2704.99 | -12.29 | -247.92 | -12.29 | 0.97 |  |  | 10 | 100 | 900 | 5 | 564 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:30 | 00:33 | 0.05 | 2802 | 2820 | 18 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 360 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:33 | 00:39 | 0.1 | 2820 | 2835 | 15 | Slide | 0 | 2822 | 16.77 | 269.2 | 2794.89 | -12.94 | -275.35 | -12.94 | 0.55 |  |  | 10 |  | 900 | 5 | 150 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:39 | 00:47 | 0.13333 | 2835 | 2896 | 61 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 457.5 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 00:50 | 00:59 | 0.15 | 2896 | 2989 | 93 | Rotate |  | 2915 | 17.27 | 269.74 | 2883.82 | -13.19 | -302.57 | -13.19 | 0.56 |  |  | 10 | 100 | 900 | 5 | 620 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60
10/07/2021 | 01:02 | 01:05 | 0.05 | 2989 | 3020 | 31 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5; Drilling Parameters ROP: 372 | 2000 | 1500 | 500 | 100 | 60 | 60 | 60

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6908
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 872
Well Name: |  |  |  |  | Bighorn Plains H02 |  |  | Survey / Gamma Offset: |  |  |  |  | 64.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 153.98 |  | Rotate: |  | 6036
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
10/17/2021 | 12:14 | 12:17 | 0.05 | 3020 | 3030 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 3; Drilling Parameters ROP: 200 | 1250 | 1150 | 100 | 104 | 135 | 132 | 130
10/17/2021 | 12:52 | 13:06 | 0.23333 | 3030 | 3102 | 72 | Rotate |  | 3038 | 17.1 | 270.83 | 3001.33 | -13.01 | -338.91 | -13.01 | 0.3 |  |  | 21.04 | 40.18 | 525.37 | 5.07 | 308.57 | 1822.84 | 1689.69 | 133.15 | 105.8 | 135 | 132.24 | 130
10/17/2021 | 13:10 | 13:24 | 0.23333 | 3102 | 3195 | 93 | Rotate |  | 3131 | 17.42 | 268.2 | 3090.14 | -13.25 | -366.49 | -13.25 | 0.91 |  |  | 23.59 | 50.36 | 639.72 | 7.22 | 398.57 | 2644.54 | 2329.9 | 314.64 | 107.6 | 138 | 132.16 | 130
10/17/2021 | 13:28 | 13:30 | 0.033333 | 3195 | 3205 | 10 | Rotate | Drilling Parameters WOB: 17.31; Drilling Parameters RPM: 60.18; Drilling Parameters FLOW: 742.95; Drilling Parameters Tq: 4.86; Drilling Parameters ROP: 300 | 3372.28 | 2958.33 | 413.95 | 109.4 | 138 | 132.69 | 129
10/17/2021 | 13:30 | 13:34 | 0.066667 | 3205 | 3215 | 10 | Slide | TTF: 30; Drilling Parameters WOB: 11.24; Drilling Parameters FLOW: 743.39; Drilling Parameters ROP: 150 | 3217.5 | 2956.28 | 261.22 | 111.2 | 140 | 132.77 | 129
10/17/2021 | 13:34 | 13:45 | 0.18333 | 3215 | 3289 | 74 | Rotate |  | 3225 | 19.16 | 266.17 | 3179.39 | -14.72 | -395.95 | -14.72 | 1.97 |  |  | 21.78 | 60.6 | 745.6 | 5.74 | 403.64 | 3310.99 | 2956.28 | 354.71 | 114.8 | 140 | 133.02 | 129
10/17/2021 | 13:49 | 14:00 | 0.18333 | 3289 | 3384 | 95 | Rotate |  | 3320 | 19.61 | 265.91 | 3269.01 | -16.9 | -427.41 | -16.9 | 0.48 |  |  | 27.93 | 70.12 | 814.03 | 5.42 | 518.18 | 3760.51 | 3448.32 | 312.19 | 118.4 | 140 | 133.03 | 130
10/17/2021 | 14:04 | 14:13 | 0.15 | 3384 | 3477 | 93 | Rotate |  | 3413 | 19.7 | 264.13 | 3356.59 | -19.62 | -458.57 | -19.62 | 0.65 |  |  | 24.23 | 80.17 | 818.02 | 5.18 | 620 | 3812.94 | 3366.88 | 446.06 | 122 | 145 | 132.98 | 132
10/17/2021 | 14:17 | 14:20 | 0.05 | 3477 | 3490 | 13 | Rotate | Drilling Parameters WOB: 17.02; Drilling Parameters RPM: 80.29; Drilling Parameters FLOW: 818.67; Drilling Parameters Tq: 4.1; Drilling Parameters ROP: 260 | 3629.08 | 3400.78 | 228.3 | 123.8 | 145 | 140.26 | 132
10/17/2021 | 14:20 | 14:26 | 0.1 | 3490 | 3502 | 12 | Slide | TTF: 90; Drilling Parameters WOB: 8.87; Drilling Parameters FLOW: 818.91; Drilling Parameters ROP: 120 | 3551.4 | 3594.16 | -42.76 | 125.6 | 145 | 137.67 | 132
10/17/2021 | 14:27 | 14:34 | 0.11667 | 3502 | 3571 | 69 | Rotate |  | 3507 | 18.98 | 266.39 | 3445.28 | -22.2 | -489.58 | -22.2 | 1.1 |  |  | 20.63 | 80.29 | 817.6 | 5.78 | 591.43 | 3764.54 | 3499.4 | 265.14 | 127.4 | 145 | 137.67 | 132
10/17/2021 | 14:36 | 14:46 | 0.16667 | 3571 | 3664 | 93 | Rotate |  | 3600 | 18.98 | 264.93 | 3533.23 | -24.49 | -519.74 | -24.49 | 0.51 |  |  | 26 | 80.3 | 817.78 | 6.76 | 558 | 3924.98 | 3688.06 | 236.92 | 131 | 150 | 138.58 | 132
10/17/2021 | 14:49 | 14:54 | 0.083333 | 3664 | 3679 | 15 | Rotate | Drilling Parameters WOB: 15.08; Drilling Parameters RPM: 80.12; Drilling Parameters FLOW: 818.47; Drilling Parameters Tq: 3.88; Drilling Parameters ROP: 180 | 3881.82 | 3688.06 | 193.76 | 132.8 | 150 | 141.19 | 135
10/17/2021 | 14:54 | 14:59 | 0.083333 | 3679 | 3691 | 12 | Slide | TTF: 108.03; Drilling Parameters WOB: 6.44; Drilling Parameters FLOW: 817.95; Drilling Parameters ROP: 144 | 3682.59 | 3672.03 | 10.56 | 132.8 | 150 | 141.19 | 135
10/17/2021 | 14:59 | 15:06 | 0.11667 | 3691 | 3758 | 67 | Rotate |  | 3694 | 18.46 | 268.22 | 3622.26 | -26.3 | -549.84 | -26.3 | 1.25 |  |  | 21.34 | 80.24 | 818.46 | 6.02 | 574.29 | 3878.56 | 3518.02 | 360.54 | 134.6 | 150 | 140.57 | 135
10/17/2021 | 15:09 | 15:20 | 0.18333 | 3758 | 3851 | 93 | Rotate |  | 3787 | 18.66 | 268.57 | 3710.42 | -27.13 | -579.43 | -27.13 | 0.25 |  |  | 19.49 | 80.16 | 818.33 | 5.41 | 507.27 | 3915.07 | 3518.02 | 397.05 | 138.2 | 150 | 140.56 | 135
10/17/2021 | 15:22 | 15:34 | 0.2 | 3851 | 3944 | 93 | Rotate |  | 3881 | 18.55 | 268.47 | 3799.51 | -27.91 | -609.41 | -27.91 | 0.12 |  |  | 13.75 | 80.28 | 818.16 | 5.39 | 465 | 3872.07 | 3518.02 | 354.05 | 141.8 | 155 | 146.6 | 140
10/17/2021 | 15:37 | 15:46 | 0.15 | 3944 | 4038 | 94 | Rotate |  | 3974 | 18.19 | 267.72 | 3887.77 | -28.88 | -638.71 | -28.88 | 0.46 |  |  | 28.01 | 80.16 | 818.27 | 7.83 | 626.67 | 4054.17 | 3596.15 | 458.02 | 143.6 | 155 | 148.04 | 140
10/17/2021 | 15:49 | 15:54 | 0.083333 | 4038 | 4054 | 16 | Rotate | Drilling Parameters WOB: 16.18; Drilling Parameters RPM: 80.14; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 5.58; Drilling Parameters ROP: 192 | 3970.03 | 3674.37 | 295.66 | 145.4 | 155 | 148.36 | 140
10/17/2021 | 15:54 | 15:59 | 0.083333 | 4054 | 4068 | 14 | Slide | TTF: 91.84; Drilling Parameters WOB: 8.37; Drilling Parameters FLOW: 818.07; Drilling Parameters ROP: 168 | 3820.02 | 3703.33 | 116.69 | 147.2 | 155 | 146.6 | 138
10/17/2021 | 15:59 | 16:05 | 0.1 | 4068 | 4133 | 65 | Rotate |  | 4068 | 17.92 | 272.29 | 3977.15 | -28.89 | -667.82 | -28.89 | 1.53 |  |  | 24.73 | 80.15 | 818.47 | 6.52 | 650 | 3887.99 | 3521.95 | 366.04 | 147.2 | 155 | 146.6 | 138
10/17/2021 | 16:08 | 16:16 | 0.13333 | 4133 | 4225 | 92 | Rotate |  | 4161 | 17.99 | 272.59 | 4065.62 | -27.66 | -696.46 | -27.66 | 0.12 |  |  | 28.24 | 80.19 | 818.54 | 7.37 | 690 | 3852.58 | 3621.95 | 230.63 | 149 | 160 | 145.97 | 142
10/17/2021 | 16:19 | 16:27 | 0.13333 | 4225 | 4319 | 94 | Rotate |  | 4255 | 18.01 | 273.03 | 4155.02 | -26.24 | -725.47 | -26.24 | 0.15 |  |  | 27.91 | 80.13 | 818.49 | 7.52 | 705 | 3921.08 | 3621.95 | 299.13 | 150.8 | 160 | 151.99 | 142
10/17/2021 | 16:30 | 16:37 | 0.11667 | 4319 | 4412 | 93 | Rotate |  | 4348 | 17.76 | 273.64 | 4243.52 | -24.58 | -753.98 | -24.58 | 0.34 |  |  | 23.1 | 80.23 | 818.52 | 7.39 | 797.14 | 3934.43 | 3621.95 | 312.48 | 152.6 | 160 | 151.99 | 142
10/17/2021 | 16:40 | 16:51 | 0.18333 | 4412 | 4506 | 94 | Rotate |  | 4442 | 17.79 | 273.27 | 4333.03 | -22.85 | -782.63 | -22.85 | 0.12 |  |  | 25.96 | 80.16 | 816.61 | 7.03 | 512.73 | 3948.51 | 3654.4 | 294.11 | 154.4 | 165 | 152.36 | 142
10/17/2021 | 16:54 | 17:01 | 0.11667 | 4506 | 4599 | 93 | Rotate |  | 4535 | 17.92 | 272.58 | 4421.56 | -21.4 | -811.11 | -21.4 | 0.27 |  |  | 29.63 | 80.13 | 818.29 | 8.13 | 797.14 | 3983.04 | 3654.4 | 328.64 | 156.2 | 165 | 152.36 | 142
10/17/2021 | 17:04 | 17:09 | 0.083333 | 4599 | 4614 | 15 | Rotate | Drilling Parameters WOB: 9.3; Drilling Parameters RPM: 80.16; Drilling Parameters FLOW: 818.73; Drilling Parameters Tq: 4.78; Drilling Parameters ROP: 180 | 3803.12 | 3609.17 | 193.95 | 156.2 | 165 | 152 | 142
10/17/2021 | 17:09 | 17:14 | 0.083333 | 4614 | 4628 | 14 | Slide | TTF: -62.52; Drilling Parameters WOB: 8.69; Drilling Parameters FLOW: 818.3; Drilling Parameters ROP: 168 | 3736.94 | 3682.2 | 54.74 | 158 | 165 | 150 | 141
10/17/2021 | 17:14 | 17:20 | 0.1 | 4628 | 4693 | 65 | Rotate |  | 4629 | 18.55 | 269.28 | 4510.84 | -20.93 | -840.5 | -20.93 | 1.29 |  |  | 25.47 | 80.18 | 818.33 | 8.44 | 650 | 3978.55 | 3686.34 | 292.21 | 158 | 165 | 152 | 141
10/17/2021 | 17:23 | 17:32 | 0.15 | 4693 | 4787 | 94 | Rotate |  | 4724 | 17.98 | 269.64 | 4601.05 | -21.22 | -870.28 | -21.22 | 0.61 |  |  | 23.95 | 80.17 | 818.41 | 8.41 | 626.67 | 3996.79 | 3711.13 | 285.66 | 159.8 | 165 | 155 | 143
10/17/2021 | 17:35 | 17:44 | 0.15 | 4787 | 4882 | 95 | Rotate |  | 4818 | 17.62 | 269.7 | 4690.55 | -21.38 | -899.01 | -21.38 | 0.38 |  |  | 26 | 80.18 | 818.4 | 6.71 | 633.33 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 17:47 | 17:57 | 0.16667 | 4882 | 4976 | 94 | Rotate |  | 4912 | 17.87 | 269.41 | 4780.08 | -21.6 | -927.66 | -21.6 | 0.28 |  |  | 26 | 80.18 | 818.4 | 6.71 | 564 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 18:00 | 18:10 | 0.16667 | 4976 | 5059 | 83 | Rotate |  | 5005 | 16.55 | 269.18 | 4868.91 | -21.94 | -955.17 | -21.94 | 1.42 |  |  | 26 | 80.18 | 818.4 | 6.71 | 498 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 18:13 | 18:23 | 0.16667 | 5059 | 5084 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 150 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 18:23 | 18:33 | 0.16667 | 5084 | 5162 | 78 | Rotate |  | 5098 | 17.89 | 272.73 | 4957.74 | -21.45 | -982.69 | -21.45 | 1.83 |  |  | 26 | 80.18 | 818.4 | 6.71 | 468 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 18:36 | 18:48 | 0.2 | 5162 | 5256 | 94 | Rotate |  | 5192 | 18.72 | 273.71 | 5046.99 | -19.79 | -1012.16 | -19.79 | 0.94 |  |  | 26 | 80.18 | 818.4 | 6.71 | 470 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 18:51 | 19:03 | 0.2 | 5256 | 5350 | 94 | Rotate |  | 5286 | 18.96 | 273.17 | 5135.95 | -17.97 | -1042.46 | -17.97 | 0.32 |  |  | 26 | 80.18 | 818.4 | 6.71 | 470 | 3926.66 | 3711.13 | 215.53 | 161.6 | 165 | 155 | 143
10/17/2021 | 19:05 | 19:19 | 0.23333 | 5350 | 5444 | 94 | Rotate |  | 5380 | 17.81 | 272.01 | 5225.15 | -16.62 | -1072.08 | -16.62 | 1.28 |  |  | 26 | 80.18 | 818.4 | 6.71 | 402.86 | 3926.66 | 3711.13 | 215.53 | 167 | 165 | 155 | 143
10/17/2021 | 19:22 | 19:39 | 0.28333 | 5444 | 5537 | 93 | Rotate |  | 5473 | 16.69 | 272.4 | 5313.97 | -15.56 | -1099.64 | -15.56 | 1.21 |  |  | 26 | 80.18 | 818.4 | 6.71 | 328.24 | 3926.66 | 3711.13 | 215.53 | 167 | 165 | 155 | 143
10/17/2021 | 19:42 | 19:52 | 0.16667 | 5537 | 5557 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 120 | 3926.66 | 3711.13 | 215.53 | 167 | 165 | 155 | 143
10/17/2021 | 19:52 | 20:06 | 0.23333 | 5557 | 5631 | 74 | Rotate |  | 5567 | 18.1 | 270.27 | 5403.67 | -14.92 | -1127.73 | -14.92 | 1.65 |  |  | 26 | 80.18 | 818.4 | 6.71 | 317.14 | 3926.66 | 3711.13 | 215.53 | 167 | 165 | 155 | 143
10/17/2021 | 20:09 | 20:21 | 0.2 | 5631 | 5724 | 93 | Rotate |  | 5660 | 17.36 | 269.21 | 5492.25 | -15.05 | -1156.05 | -15.05 | 0.87 |  |  | 26 | 80.18 | 818.4 | 6.71 | 465 | 3926.66 | 3711.13 | 215.53 | 167 | 165 | 155 | 143
10/17/2021 | 20:23 | 20:31 | 0.13333 | 5724 | 5739 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 112.5 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 20:31 | 20:47 | 0.26667 | 5739 | 5818 | 79 | Rotate |  | 5754 | 18.55 | 271.09 | 5581.67 | -14.96 | -1185.02 | -14.96 | 1.41 |  |  | 26 | 80.18 | 818.4 | 6.71 | 296.25 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 20:50 | 21:04 | 0.23333 | 5818 | 5912 | 94 | Rotate |  | 5848 | 19.21 | 270.97 | 5670.61 | -14.41 | -1215.43 | -14.41 | 0.7 |  |  | 26 | 80.18 | 818.4 | 6.71 | 402.86 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 21:07 | 21:20 | 0.21667 | 5912 | 6005 | 93 | Rotate |  | 5941 | 18.44 | 270.41 | 5758.64 | -14.05 | -1245.44 | -14.05 | 0.85 |  |  | 26 | 80.18 | 818.4 | 6.71 | 429.23 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 21:23 | 21:36 | 0.21667 | 6005 | 6099 | 94 | Rotate |  | 6035 | 18.09 | 271.22 | 5847.9 | -13.63 | -1274.89 | -13.63 | 0.46 |  |  | 26 | 80.18 | 818.4 | 6.71 | 433.85 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 21:39 | 21:53 | 0.23333 | 6099 | 6192 | 93 | Rotate |  | 6128 | 17.22 | 271.02 | 5936.52 | -13.08 | -1303.09 | -13.08 | 0.94 |  |  | 26 | 80.18 | 818.4 | 6.71 | 398.57 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 21:56 | 22:05 | 0.15 | 6192 | 6207 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 100 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 22:05 | 22:20 | 0.25 | 6207 | 6286 | 79 | Rotate |  | 6222 | 18.91 | 272.13 | 6025.88 | -12.26 | -1332.23 | -12.26 | 1.83 |  |  | 26 | 80.18 | 818.4 | 6.71 | 316 | 3926.66 | 3711.13 | 215.53 | 178 | 165 | 155 | 143
10/17/2021 | 22:23 | 22:36 | 0.21667 | 6286 | 6380 | 94 | Rotate |  | 6316 | 19.4 | 274.04 | 6114.68 | -10.6 | -1363.02 | -10.6 | 0.85 |  |  | 26 | 80.18 | 818.4 | 6.71 | 433.85 | 3926.66 | 3711.13 | 215.53 | 187 | 165 | 155 | 143
10/17/2021 | 22:39 | 22:55 | 0.26667 | 6380 | 6474 | 94 | Rotate |  | 6410 | 19.05 | 273.76 | 6203.44 | -8.49 | -1393.9 | -8.49 | 0.39 |  |  | 26 | 80.18 | 818.4 | 6.71 | 352.5 | 3926.66 | 3711.13 | 215.53 | 187 | 165 | 155 | 143
10/17/2021 | 22:58 | 23:13 | 0.25 | 6474 | 6567 | 93 | Rotate |  | 6503 | 18.51 | 273.87 | 6291.49 | -6.5 | -1423.78 | -6.5 | 0.58 |  |  | 26 | 80.18 | 818.4 | 6.71 | 372 | 3926.66 | 3711.13 | 215.53 | 187 | 165 | 155 | 143
10/17/2021 | 23:16 | 23:29 | 0.21667 | 6567 | 6661 | 94 | Rotate |  | 6597 | 17.43 | 273.91 | 6380.9 | -4.53 | -1452.71 | -4.53 | 1.15 |  |  | 26 | 80.18 | 818.4 | 6.71 | 433.85 | 3926.66 | 3711.13 | 215.53 | 187 | 165 | 155 | 143
10/17/2021 | 23:32 | 24:00 | 0.46667 | 6661 | 6676 | 15 | Slide | TTF: -40; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 32.14 | 3926.66 | 3711.13 | 215.53 | 187 | 165 | 155 | 143
10/18/2021 | 00:00 | 00:10 | 0.16667 | 6676 | 6754 | 78 | Rotate |  | 6690 | 17.66 | 272.79 | 6469.57 | -2.9 | -1480.7 | -2.9 | 0.44 |  |  | 26 | 80.18 | 818.4 | 6.71 | 468 | 3926.66 | 3711.13 | 215.53 | 190 | 165 | 155 | 143
10/18/2021 | 00:13 | 00:27 | 0.23333 | 6754 | 6847 | 93 | Rotate |  | 6783 | 17.65 | 273.46 | 6558.19 | -1.36 | -1508.86 | -1.36 | 0.22 |  |  | 26 | 80.18 | 818.4 | 6.71 | 398.57 | 3926.66 | 3711.13 | 215.53 | 190 | 165 | 155 | 143
10/18/2021 | 00:30 | 00:43 | 0.21667 | 6847 | 6942 | 95 | Rotate |  | 6878 | 16.3 | 273.53 | 6649.05 | 0.33 | -1536.54 | 0.33 | 1.42 |  |  | 26 | 80.18 | 818.4 | 6.71 | 438.46 | 3926.66 | 3711.13 | 215.53 | 190 | 165 | 155 | 143
10/18/2021 | 00:46 | 01:06 | 0.33333 | 6942 | 6957 | 15 | Slide | TTF: -60; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 45 | 3926.66 | 3711.13 | 215.53 | 190 | 165 | 155 | 143
10/18/2021 | 01:06 | 01:19 | 0.21667 | 6957 | 7035 | 78 | Rotate |  | 6971 | 15.94 | 271.26 | 6738.4 | 1.42 | -1562.34 | 1.42 | 0.78 |  |  | 26 | 80.18 | 818.4 | 6.71 | 360 | 3926.66 | 3711.13 | 215.53 | 194 | 165 | 155 | 143
10/18/2021 | 01:22 | 01:36 | 0.23333 | 7035 | 7129 | 94 | Rotate |  | 7065 | 15.17 | 271.34 | 6828.95 | 1.99 | -1587.54 | 1.99 | 0.82 |  |  | 26 | 80.18 | 818.4 | 6.71 | 402.86 | 3926.66 | 3711.13 | 215.53 | 194 | 165 | 155 | 143
10/18/2021 | 01:39 | 01:55 | 0.26667 | 7129 | 7144 | 15 | Slide | TTF: -60; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 56.25 | 3926.66 | 3711.13 | 215.53 | 194 | 165 | 155 | 143
10/18/2021 | 01:55 | 02:10 | 0.25 | 7144 | 7223 | 79 | Rotate |  | 7159 | 14.23 | 266.29 | 6919.88 | 1.53 | -1611.36 | 1.53 | 1.69 |  |  | 26 | 80.18 | 818.4 | 6.71 | 316 | 3926.66 | 3711.13 | 215.53 | 199 | 165 | 155 | 143
10/18/2021 | 02:13 | 02:28 | 0.25 | 7223 | 7317 | 94 | Rotate |  | 7253 | 12.95 | 266.63 | 7011.24 | 0.16 | -1633.41 | 0.16 | 1.36 |  |  | 26 | 80.18 | 818.4 | 6.71 | 376 | 3926.66 | 3711.13 | 215.53 | 199 | 165 | 155 | 143
10/18/2021 | 02:31 | 02:48 | 0.28333 | 7317 | 7332 | 15 | Slide | TTF: -30; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 52.94 | 3926.66 | 3711.13 | 215.53 | 199 | 165 | 155 | 143
10/18/2021 | 02:48 | 03:02 | 0.23333 | 7332 | 7411 | 79 | Rotate |  | 7347 | 12.44 | 270.19 | 7102.95 | -0.42 | -1654.05 | -0.42 | 0.99 |  |  | 26 | 80.18 | 818.4 | 6.71 | 338.57 | 3926.66 | 3711.13 | 215.53 | 201 | 165 | 155 | 143
10/18/2021 | 03:05 | 03:21 | 0.26667 | 7411 | 7504 | 93 | Rotate |  | 7440 | 11.62 | 276.56 | 7193.91 | 0.68 | -1673.37 | 0.68 | 1.68 |  |  | 26 | 80.18 | 818.4 | 6.71 | 348.75 | 3926.66 | 3711.13 | 215.53 | 201 | 165 | 155 | 143
10/18/2021 | 03:24 | 03:39 | 0.25 | 7504 | 7519 | 15 | Slide | TTF: -30; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 6.71; Drilling Parameters ROP: 60 | 3926.66 | 3711.13 | 215.53 | 203 | 165 | 155 | 143
10/18/2021 | 03:39 | 03:51 | 0.2 | 7519 | 7597 | 78 | Rotate |  | 7533 | 11.82 | 277.5 | 7284.97 | 2.99 | -1692.12 | 2.99 | 0.3 |  |  | 30 | 80.18 | 818.4 | 15 | 390 | 4700 | 4100 | 600 | 203 | 165 | 155 | 143
10/18/2021 | 03:54 | 04:10 | 0.26667 | 7597 | 7612 | 15 | Slide | TTF: -30; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 818.4; Drilling Parameters Tq: 15; Drilling Parameters ROP: 56.25 | 4700 | 4100 | 600 | 203 | 165 | 155 | 143
10/18/2021 | 04:10 | 04:30 | 0.33333 | 7612 | 7691 | 79 | Rotate |  | 7627 | 13.01 | 279 | 7376.77 | 5.9 | -1712.12 | 5.9 | 1.31 |  |  | 30 | 80.18 | 818.4 | 15 | 237 | 4700 | 4100 | 600 | 203 | 165 | 155 | 143
10/18/2021 | 04:33 | 04:49 | 0.26667 | 7691 | 7784 | 93 | Rotate |  | 7720 | 12.45 | 278.94 | 7467.48 | 9.1 | -1732.36 | 9.1 | 0.6 |  |  | 30 | 80.18 | 818.4 | 15 | 348.75 | 4700 | 4100 | 600 | 203 | 165 | 155 | 143
10/18/2021 | 04:52 | 05:10 | 0.3 | 7784 | 7875 | 91 | Rotate |  | 7811 | 11.06 | 282.31 | 7556.57 | 12.48 | -1750.58 | 12.48 | 1.7 |  |  | 30 | 80.18 | 818.4 | 15 | 546 | 4700 | 4100 | 600 | 208 | 165 | 155 | 143
10/18/2021 | 05:13 | 05:33 | 0.33333 | 7875 | 7895 | 20 | Slide | TTF: -60; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 15; Drilling Parameters ROP: 60 | 3800 | 3200 | 600 | 208 | 165 | 155 | 143
10/18/2021 | 05:33 | 05:47 | 0.23333 | 7895 | 7968 | 73 | Rotate |  | 7904 | 10.93 | 279.07 | 7647.87 | 15.78 | -1768 | 15.78 | 0.68 |  |  | 30 | 80.18 | 700 | 15 | 312.86 | 3800 | 3200 | 600 | 208 | 165 | 155 | 143
10/18/2021 | 05:50 | 05:55 | 0.083333 | 7968 | 7989 | 21 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 15; Drilling Parameters ROP: 252 | 3800 | 3200 | 600 | 208 | 165 | 155 | 143
10/18/2021 | 05:55 | 06:14 | 0.31667 | 7989 | 8009 | 20 | Slide | -70 | 7998 | 10.67 | 278.23 | 7740.2 | 18.43 | -1785.41 | 18.43 | 0.32 |  |  | 15 |  | 700 |  | 63.16 | 3800 | 3200 | 600 | 208 | 165 | 155 | 143
10/18/2021 | 06:14 | 06:23 | 0.15 | 8009 | 8062 | 53 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 15; Drilling Parameters ROP: 353.33 | 3800 | 3200 | 600 | 208 | 165 | 155 | 143
10/18/2021 | 06:26 | 06:30 | 0.066667 | 8062 | 8072 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80.18; Drilling Parameters FLOW: 810; Drilling Parameters Tq: 15; Drilling Parameters ROP: 150 | 4600 | 4200 | 400 | 208 | 165 | 155 | 143
10/18/2021 | 06:30 | 06:41 | 0.18333 | 8072 | 8087 | 15 | Slide | TTF: -80; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 810; Drilling Parameters ROP: 81.82 | 4400 | 4200 | 200 | 208 | 165 | 155 | 143
10/18/2021 | 06:41 | 06:50 | 0.15 | 8087 | 8156 | 69 | Rotate |  | 8092 | 11.12 | 273.51 | 7832.51 | 20.23 | -1803.07 | 20.23 | 1.06 |  |  | 36.95 | 80.12 | 806.91 | 14.62 | 460 | 4747.77 | 4246.15 | 501.62 | 206.6 | 260 | 234.21 | 200
10/18/2021 | 06:53 | 07:02 | 0.15 | 8156 | 8250 | 94 | Rotate |  | 8186 | 11.19 | 272.9 | 7924.73 | 21.24 | -1821.23 | 21.24 | 0.15 |  |  | 31.64 | 80.18 | 807.17 | 14.07 | 626.67 | 4723.24 | 4246.15 | 477.09 | 210.2 | 260 | 234.21 | 200
10/18/2021 | 07:06 | 07:20 | 0.23333 | 8250 | 8343 | 93 | Rotate |  | 8279 | 10.76 | 276.46 | 8016.03 | 22.68 | -1838.87 | 22.68 | 0.86 |  |  | 39.22 | 79.36 | 806.86 | 16.8 | 398.57 | 4900.11 | 4316.84 | 583.27 | 213.8 | 260 | 221.42 | 200
10/18/2021 | 07:25 | 07:40 | 0.25 | 8343 | 8363 | 20 | Slide | TTF: -84.17; Drilling Parameters WOB: 11.55; Drilling Parameters FLOW: 807.78; Drilling Parameters ROP: 80 | 4440.33 | 4370.48 | 69.85 | 212 | 260 | 225.02 | 200
10/18/2021 | 07:40 | 07:51 | 0.18333 | 8363 | 8436 | 73 | Rotate |  | 8372 | 10.58 | 272.33 | 8107.43 | 24 | -1856.03 | 24 | 0.84 |  |  | 25.97 | 80.43 | 807.14 | 14.88 | 398.18 | 4790.29 | 4287.69 | 502.6 | 213.8 | 260 | 229.03 | 200
10/18/2021 | 07:59 | 08:04 | 0.083333 | 8436 | 8446 | 10 | Rotate | Drilling Parameters WOB: 13.98; Drilling Parameters RPM: 80.58; Drilling Parameters FLOW: 685.28; Drilling Parameters Tq: 11.99; Drilling Parameters ROP: 120 | 3571.55 | 3324.21 | 247.34 | 213.8 | 260 | 231.12 | 200
10/18/2021 | 08:04 | 08:21 | 0.28333 | 8446 | 8466 | 20 | Slide | TTF: -122.83; Drilling Parameters WOB: 8.28; Drilling Parameters FLOW: 687.25; Drilling Parameters ROP: 70.59 | 3399.63 | 3294.49 | 105.14 | 212 | 265 | 232.57 | 200
10/18/2021 | 08:21 | 08:32 | 0.18333 | 8466 | 8531 | 65 | Rotate |  | 8467 | 10.01 | 260.87 | 8200.91 | 23.05 | -1872.89 | 23.05 | 2.23 |  |  | 32.35 | 80.38 | 684.99 | 14.56 | 354.55 | 3704.18 | 3307.19 | 396.99 | 212 | 265 | 231.67 | 200
10/18/2021 | 08:35 | 08:39 | 0.066667 | 8531 | 8541 | 10 | Rotate | Drilling Parameters WOB: 14.37; Drilling Parameters RPM: 80.46; Drilling Parameters FLOW: 685.59; Drilling Parameters Tq: 12.34; Drilling Parameters ROP: 150 | 3699.97 | 3301.39 | 398.58 | 212 | 265 | 233.51 | 200
10/18/2021 | 08:39 | 08:50 | 0.18333 | 8541 | 8556 | 15 | Slide | TTF: 173.68; Drilling Parameters WOB: 16.1; Drilling Parameters FLOW: 685.5; Drilling Parameters ROP: 81.82 | 3416.97 | 3310.88 | 106.09 | 212 | 265 | 233.11 | 202
10/18/2021 | 08:50 | 09:01 | 0.18333 | 8556 | 8625 | 69 | Rotate |  | 8561 | 7.96 | 253.13 | 8293.75 | 19.86 | -1887.19 | 19.86 | 2.53 |  |  | 34.95 | 80.33 | 685.34 | 14.32 | 375.65 | 3775.25 | 2905.78 | 869.47 | 212 | 265 | 231.41 | 202
10/18/2021 | 09:04 | 09:08 | 0.066667 | 8625 | 8635 | 10 | Rotate | Drilling Parameters WOB: 21.56; Drilling Parameters RPM: 80.51; Drilling Parameters FLOW: 798.05; Drilling Parameters Tq: 12.18; Drilling Parameters ROP: 150 | 4718.33 | 4362.96 | 355.37 | 212 | 268 | 233.66 | 205
10/18/2021 | 09:08 | 09:17 | 0.15 | 8635 | 8647 | 12 | Slide | TTF: 163.22; Drilling Parameters WOB: 13.08; Drilling Parameters FLOW: 798.49; Drilling Parameters ROP: 80 | 4475.12 | 4337.83 | 137.29 | 212 | 268 | 233.38 | 205
10/18/2021 | 09:17 | 09:29 | 0.2 | 8647 | 8718 | 71 | Rotate |  | 8654 | 5.25 | 249.63 | 8386.13 | 16.51 | -1897.34 | 16.51 | 2.94 |  |  | 31.59 | 80.38 | 797.38 | 15.14 | 355 | 4767.64 | 4342.82 | 424.82 | 213.8 | 268 | 233.51 | 205
10/18/2021 | 09:32 | 09:44 | 0.2 | 8718 | 8812 | 94 | Rotate |  | 8748 | 4.17 | 253.43 | 8479.81 | 14.04 | -1904.65 | 14.04 | 1.2 |  |  | 34.1 | 80.16 | 797.57 | 15.84 | 470 | 4863.29 | 4380.77 | 482.52 | 215.6 | 268 | 241.42 | 205
10/18/2021 | 09:47 | 09:58 | 0.18333 | 8812 | 8905 | 93 | Rotate |  | 8841 | 3.7 | 254.2 | 8572.59 | 12.26 | -1910.78 | 12.26 | 0.51 |  |  | 37.97 | 80.12 | 797.58 | 17.19 | 507.27 | 4981.27 | 4317.85 | 663.42 | 219.2 | 268 | 241.42 | 205
10/18/2021 | 10:01 | 10:14 | 0.21667 | 8905 | 9000 | 95 | Rotate |  | 8936 | 2.44 | 253.87 | 8667.45 | 10.86 | -1915.67 | 10.86 | 1.33 |  |  | 34.33 | 80.39 | 797.48 | 16.06 | 438.46 | 4903.33 | 4302.23 | 601.1 | 221 | 270 | 239.77 | 205
10/18/2021 | 10:17 | 10:42 | 0.41667 | 9000 | 9093 | 93 | Rotate |  | 9029 | 2.11 | 243.5 | 8760.38 | 9.55 | -1919.11 | 9.55 | 0.57 |  |  | 35.58 | 80.04 | 694.66 | 16.65 | 223.2 | 4156.1 | 3453.76 | 702.34 | 224.6 | 270 | 239.77 | 205
10/18/2021 | 10:45 | 11:09 | 0.4 | 9093 | 9187 | 94 | Rotate |  | 9123 | 2.24 | 251.17 | 8854.31 | 8.18 | -1922.39 | 8.18 | 0.34 |  |  | 27.87 | 80.07 | 695.5 | 15.78 | 235 | 4087.08 | 3598.54 | 488.54 | 224.6 | 270 | 242.68 | 205
10/18/2021 | 11:13 | 11:30 | 0.28333 | 9187 | 9281 | 94 | Rotate |  | 9217 | 1.69 | 247.14 | 8948.25 | 7.05 | -1925.41 | 7.05 | 0.6 |  |  | 36.14 | 80.35 | 797.54 | 15.74 | 331.76 | 5037.23 | 4302.23 | 735 | 224.6 | 270 | 242.59 | 205
10/18/2021 | 11:33 | 11:46 | 0.21667 | 9281 | 9375 | 94 | Rotate |  | 9311 | 1.83 | 244.67 | 9042.21 | 5.87 | -1928.04 | 5.87 | 0.17 |  |  | 30.91 | 80.33 | 797.51 | 16.59 | 433.85 | 5138.35 | 4402.23 | 736.12 | 226.4 | 270 | 250 | 215
10/18/2021 | 11:46 | 11:55 | 0.15 | 9375 | 9400 | 25 | Rotate | Drilling Parameters WOB: 30.91; Drilling Parameters RPM: 80.33; Drilling Parameters FLOW: 797.51; Drilling Parameters Tq: 16.59; Drilling Parameters ROP: 166.67 | 5138.35 | 4402.23 | 736.12 | 226.4 | 270 | 250 | 215
10/18/2021 | 11:55 | 12:50 | 0.91667 | 9400 | 9468 | 68 | Slide | 155 | 9404 | 1.96 | 266.72 | 9135.16 | 5.14 | -1930.97 | 5.14 | 0.79 |  |  | 10 |  | 797.51 |  | 74.18 | 4550 | 4402.23 | 147.77 | 226.4 | 270 | 250 | 220
10/18/2021 | 12:55 | 15:10 | 2.25 | 9468 | 9562 | 94 | Slide | 150 | 9498 | 4.84 | 200.49 | 9229.01 | 1.33 | -1933.97 | 1.33 | 4.71 |  |  | 10 |  | 797.51 |  | 41.78 | 4550 | 4402.23 | 147.77 | 226.4 | 270 | 250 | 220
10/18/2021 | 15:16 | 19:25 | 4.15 | 9562 | 9655 | 93 | Slide | -60 | 9591 | 10.11 | 187.12 | 9321.2 | -10.45 | -1936.35 | -10.45 | 5.93 |  |  | 10 |  | 797.51 |  | 22.41 | 4550 | 4402.23 | 147.77 | 226.4 | 270 | 250 | 220
10/18/2021 | 19:30 | 22:42 | 3.2 | 9655 | 9750 | 95 | Slide | -60 | 9686 | 14.15 | 181.49 | 9414.06 | -30.34 | -1937.69 | -30.34 | 4.43 |  |  | 20 |  | 797.51 |  | 29.69 | 4550 | 4402.23 | 147.77 | 230 | 270 | 250 | 220
10/18/2021 | 22:47 | 24:00 | 1.2167 | 9750 | 9789 | 39 | Slide | -60 | 9779 | 17.86 | 175.99 | 9503.44 | -55.94 | -1936.99 | -55.94 | 4.31 |  |  | 20 |  | 797.51 |  | 32.05 | 4550 | 4402.23 | 147.77 | 230 | 270 | 250 | 220
10/19/2021 | 00:00 | 01:19 | 1.3167 | 9789 | 9843 | 54 | Slide | TTF: -60; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 797.51; Drilling Parameters ROP: 41.01 | 4550 | 4402.23 | 147.77 | 236 | 270 | 250 | 220
10/19/2021 | 01:24 | 03:52 | 2.4667 | 9843 | 9923 | 80 | Slide | -60 | 9859 | 21.15 | 166.02 | 9578.86 | -82.2 | -1932.64 | -82.2 | 5.84 |  |  | 30 |  | 797.51 |  | 32.43 | 4550 | 4402.23 | 147.77 | 244 | 270 | 250 | 220
10/19/2021 | 03:52 | 03:56 | 0.066667 | 9923 | 9928 | 5 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 797.51; Drilling Parameters Tq: 10; Drilling Parameters ROP: 75 | 4550 | 4402.23 | 147.77 | 244 | 270 | 250 | 220

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7160
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1043
Well Name: |  |  |  |  | Bighorn Plains H02 |  |  | Survey / Gamma Offset: |  |  |  |  | 64.00 / 51.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 153.98 |  | Rotate: |  | 6117
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
10/22/2021 | 12:45 | 13:13 | 0.46667 | 9928 | 9988 | 60 | Slide | TTF: -40; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 300; Drilling Parameters ROP: 128.57 | 3100 | 2300 | 800 | 224 | 230 | 205 | 190
10/22/2021 | 13:23 | 14:10 | 0.78333 | 9988 | 10083 | 95 | Slide | -30 | 10019 | 26.21 | 154.14 | 9725.43 | -142.08 | -1910.23 | -142.08 | 4.33 |  |  | 25 |  | 300 |  | 121.28 | 3100 | 2300 | 800 | 224 | 230 | 205 | 190
10/22/2021 | 14:20 | 15:10 | 0.83333 | 10083 | 10178 | 95 | Slide | 0 | 10114 | 36.44 | 144.67 | 9806.52 | -184.11 | -1884.68 | -184.11 | 11.92 |  |  | 25 |  | 300 |  | 114 | 3100 | 2300 | 800 | 224 | 230 | 205 | 190
10/22/2021 | 15:25 | 16:00 | 0.58333 | 10178 | 10273 | 95 | Slide | 30 | 10209 | 48.38 | 147.42 | 9876.54 | -237.25 | -1849.11 | -237.25 | 12.72 |  |  | 30 |  | 350 |  | 162.86 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 16:10 | 16:31 | 0.35 | 10273 | 10308 | 35 | Rotate |  | 10304 | 55.66 | 154.12 | 9935 | -302.59 | -1812.8 | -302.59 | 9.46 |  |  | 10 | 30 | 350 | 7.5 | 100 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 16:31 | 16:59 | 0.46667 | 10308 | 10368 | 60 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 128.57 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 17:09 | 17:28 | 0.31667 | 10368 | 10414 | 46 | Rotate |  | 10398 | 60.92 | 153.06 | 9984.4 | -374.17 | -1777.22 | -374.17 | 5.68 |  |  | 10 | 30 | 350 | 7.5 | 145.26 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 17:28 | 18:20 | 0.86667 | 10414 | 10462 | 48 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 55.38 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 18:30 | 18:35 | 0.083333 | 10462 | 10472 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 120 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 18:35 | 19:35 | 1 | 10472 | 10556 | 84 | Slide | 0 | 10492 | 69.77 | 152.97 | 10023.57 | -450.23 | -1738.49 | -450.23 | 9.42 |  |  | 10 | 30 | 350 | 7.5 | 84 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 19:42 | 20:15 | 0.55 | 10556 | 10596 | 40 | Rotate |  | 10586 | 78.57 | 155.69 | 10049.19 | -531.67 | -1699.4 | -531.67 | 9.77 |  |  | 10 | 30 | 350 | 7.5 | 72.73 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 20:15 | 20:50 | 0.58333 | 10596 | 10640 | 44 | Slide | TTF: 20; Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 75.43 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 20:55 | 21:00 | 0.083333 | 10640 | 10650 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 120 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 21:06 | 21:35 | 0.48333 | 10650 | 10690 | 40 | Rotate |  | 10680 | 85.36 | 154.17 | 10062.32 | -615.92 | -1659.98 | -615.92 | 7.4 |  |  | 10 | 30 | 350 | 7.5 | 82.76 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 21:35 | 21:45 | 0.16667 | 10690 | 10702 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 72 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 21:45 | 22:00 | 0.25 | 10702 | 10744 | 42 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 168 | 3800 | 2950 | 850 | 228 | 230 | 205 | 190
10/22/2021 | 22:06 | 22:55 | 0.81667 | 10744 | 10839 | 95 | Rotate |  | 10775 | 87.65 | 151.62 | 10068.12 | -700.32 | -1616.78 | -700.32 | 3.6 |  |  | 25 | 30 | 350 | 7.5 | 116.33 | 3800 | 2950 | 850 | 235 | 230 | 205 | 190
10/22/2021 | 23:00 | 23:05 | 0.083333 | 10839 | 10849 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 120 | 3800 | 2950 | 850 | 235 | 260 | 170 | 205
10/22/2021 | 23:05 | 23:20 | 0.25 | 10849 | 10859 | 10 | Slide | TTF: 170; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 40 | 3800 | 2950 | 850 | 239 | 260 | 170 | 205
10/22/2021 | 23:20 | 23:50 | 0.5 | 10859 | 10932 | 73 | Rotate |  | 10868 | 85.7 | 151.95 | 10073.51 | -782.12 | -1572.89 | -782.12 | 2.13 |  |  | 25 | 80 | 350 | 7.5 | 146 | 3800 | 2950 | 850 | 239 | 260 | 170 | 205
10/22/2021 | 23:50 | 24:00 | 0.16667 | 10932 | 10932 |  | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5 | 3800 | 2950 | 850 | 239 | 260 | 170 | 205
10/23/2021 | 00:00 | 00:05 | 0.083333 | 10932 | 10943 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 132 | 3800 | 2950 | 850 | 239 | 260 | 170 | 205
10/23/2021 | 00:05 | 00:10 | 0.083333 | 10943 | 10949 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 72 | 3800 | 2950 | 850 | 239 | 260 | 170 | 205
10/23/2021 | 00:10 | 00:30 | 0.33333 | 10949 | 11027 | 78 | Rotate |  | 10963 | 84.17 | 152.81 | 10081.9 | -865.96 | -1529.02 | -865.96 | 1.85 |  |  | 25 | 80 | 350 | 7.5 | 234 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 00:36 | 00:40 | 0.066667 | 11027 | 11037 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 150 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 00:40 | 01:00 | 0.33333 | 11037 | 11052 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 45 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 01:00 | 01:15 | 0.25 | 11052 | 11120 | 68 | Rotate |  | 11056 | 86.06 | 152.13 | 10089.82 | -948.13 | -1486.19 | -948.13 | 2.16 |  |  | 25 | 80 | 350 | 7.5 | 272 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 01:26 | 01:50 | 0.4 | 11120 | 11214 | 94 | Rotate |  | 11150 | 86.94 | 151.86 | 10095.55 | -1030.97 | -1442.13 | -1030.97 | 0.98 |  |  | 25 | 80 | 350 | 7.5 | 235 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 01:56 | 02:00 | 0.066667 | 11214 | 11224 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 150 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 02:00 | 02:25 | 0.41667 | 11224 | 11241 | 17 | Slide | TTF: 115; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 40.8 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 02:25 | 02:45 | 0.33333 | 11241 | 11309 | 68 | Rotate |  | 11245 | 87.87 | 152.91 | 10099.86 | -1115.06 | -1398.15 | -1115.06 | 1.48 |  |  | 25 | 80 | 350 | 7.5 | 204 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 02:56 | 03:00 | 0.066667 | 11309 | 11319 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 150 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 03:00 | 03:25 | 0.41667 | 11319 | 11340 | 21 | Slide | 130 | 11339 | 86.23 | 156.09 | 10104.69 | -1199.77 | -1357.74 | -1199.77 | 3.8 |  |  | 25 | 80 | 350 | 10.2 | 50.4 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 03:25 | 03:45 | 0.33333 | 11340 | 11403 | 63 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 189 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 03:51 | 04:15 | 0.4 | 11403 | 11498 | 95 | Rotate |  | 11434 | 85.81 | 156.17 | 10111.29 | -1286.44 | -1319.39 | -1286.44 | 0.45 |  |  | 25 | 80 | 350 | 10.2 | 237.5 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 04:21 | 04:45 | 0.4 | 11498 | 11592 | 94 | Rotate |  | 11528 | 87.79 | 157.03 | 10116.53 | -1372.57 | -1282.11 | -1372.57 | 2.3 |  |  | 25 | 80 | 350 | 10.2 | 235 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 04:50 | 04:55 | 0.083333 | 11592 | 11602 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 120 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 04:55 | 05:15 | 0.33333 | 11602 | 11624 | 22 | Slide | -130 | 11623 | 86.78 | 154.69 | 10121.04 | -1459.15 | -1243.31 | -1459.15 | 2.68 |  |  | 30 | 80 | 350 | 10.2 | 66 | 3800 | 2950 | 850 | 243 | 260 | 170 | 205
10/23/2021 | 05:15 | 05:35 | 0.33333 | 11624 | 11687 | 63 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 189 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 05:40 | 06:04 | 0.4 | 11687 | 11782 | 95 | Rotate |  | 11718 | 86.5 | 153.27 | 10126.6 | -1544.38 | -1201.71 | -1544.38 | 1.52 |  |  | 25 | 80 | 350 | 10.2 | 237.5 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 06:09 | 06:31 | 0.36667 | 11782 | 11876 | 94 | Rotate |  | 11812 | 86.82 | 152.78 | 10132.08 | -1628.01 | -1159.14 | -1628.01 | 0.62 |  |  | 25 | 80 | 350 | 10.2 | 256.36 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 06:36 | 06:59 | 0.38333 | 11876 | 11970 | 94 | Rotate |  | 11906 | 86.87 | 150.95 | 10137.25 | -1710.77 | -1114.89 | -1710.77 | 1.94 |  |  | 25 | 80 | 350 | 10.2 | 245.22 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 07:04 | 07:21 | 0.28333 | 11970 | 11985 | 15 | Slide | TTF: 120; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 52.94 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 07:21 | 07:45 | 0.4 | 11985 | 12064 | 79 | Rotate |  | 12000 | 86.13 | 150.07 | 10142.99 | -1792.44 | -1068.7 | -1792.44 | 1.22 |  |  | 25 | 80 | 350 | 10.2 | 197.5 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 07:50 | 08:04 | 0.23333 | 12064 | 12079 | 15 | Slide | TTF: 120; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 64.29 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 08:04 | 08:28 | 0.4 | 12079 | 12158 | 79 | Rotate |  | 12094 | 85.78 | 151.76 | 10149.62 | -1874.38 | -1023.12 | -1874.38 | 1.83 |  |  | 25 | 80 | 350 | 10.2 | 197.5 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 08:33 | 08:57 | 0.4 | 12158 | 12252 | 94 | Rotate |  | 12188 | 86.77 | 152.64 | 10155.73 | -1957.35 | -979.37 | -1957.35 | 1.41 |  |  | 25 | 80 | 350 | 10.2 | 235 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 09:02 | 09:16 | 0.23333 | 12252 | 12266 | 14 | Slide | TTF: 120; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 60 | 3800 | 2950 | 850 | 245 | 260 | 170 | 205
10/23/2021 | 09:16 | 09:41 | 0.41667 | 12266 | 12347 | 81 | Rotate |  | 12283 | 85.98 | 153.61 | 10161.74 | -2041.92 | -936.52 | -2041.92 | 1.32 |  |  | 25 | 80 | 350 | 10.2 | 194.4 | 3950 | 3200 | 750 | 262 | 260 | 170 | 205
10/23/2021 | 09:46 | 10:10 | 0.4 | 12347 | 12439 | 92 | Rotate |  | 12375 | 86.66 | 153.42 | 10167.64 | -2124.09 | -895.57 | -2124.09 | 0.77 |  |  | 25 | 80 | 350 | 10.2 | 230 | 3950 | 3200 | 750 | 262 | 260 | 170 | 205
10/23/2021 | 10:15 | 10:29 | 0.23333 | 12439 | 12454 | 15 | Slide | TTF: 140; Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.2; Drilling Parameters ROP: 64.29 | 3950 | 3200 | 750 | 262 | 260 | 170 | 205
10/23/2021 | 10:29 | 10:55 | 0.43333 | 12454 | 12532 | 78 | Rotate |  | 12468 | 85.39 | 154.48 | 10174.09 | -2207.44 | -854.83 | -2207.44 | 1.78 |  |  | 25 | 80 | 350 | 10.2 | 180 | 3950 | 3200 | 750 | 268 | 260 | 170 | 205
10/23/2021 | 10:59 | 11:24 | 0.41667 | 12532 | 12627 | 95 | Rotate |  | 12563 | 85.54 | 154.91 | 10181.6 | -2293.06 | -814.35 | -2293.06 | 0.48 |  |  | 25 | 80 | 350 | 10.2 | 228 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 11:29 | 11:59 | 0.5 | 12627 | 12719 | 92 | Rotate |  | 12655 | 86.78 | 155.01 | 10187.76 | -2376.22 | -775.5 | -2376.22 | 1.35 |  |  | 25 | 80 | 350 | 10.8 | 184 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 12:04 | 12:20 | 0.26667 | 12719 | 12734 | 15 | Slide | TTF: -150; Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.8; Drilling Parameters ROP: 56.25 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 12:20 | 12:46 | 0.43333 | 12734 | 12813 | 79 | Rotate |  | 12749 | 86.23 | 154.45 | 10193.49 | -2461.07 | -735.45 | -2461.07 | 0.83 |  |  | 25 | 80 | 350 | 10.8 | 182.31 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 12:50 | 13:17 | 0.45 | 12813 | 12907 | 94 | Rotate |  | 12843 | 85.28 | 153.98 | 10200.45 | -2545.47 | -694.67 | -2545.47 | 1.13 |  |  | 25 | 80 | 350 | 10.8 | 208.89 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 13:22 | 13:47 | 0.41667 | 12907 | 13001 | 94 | Rotate |  | 12937 | 86.55 | 154.78 | 10207.15 | -2630.01 | -654.13 | -2630.01 | 1.6 |  |  | 25 | 80 | 350 | 10.8 | 225.6 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 13:52 | 14:12 | 0.33333 | 13001 | 13016 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 10.8; Drilling Parameters ROP: 45 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 14:12 | 14:44 | 0.53333 | 13016 | 13094 | 78 | Rotate |  | 13030 | 85.58 | 155.2 | 10213.53 | -2714.09 | -614.91 | -2714.09 | 1.14 |  |  | 25 | 80 | 350 | 10.8 | 146.25 | 4200 | 3300 | 900 | 268 | 260 | 170 | 205
10/23/2021 | 15:25 | 15:51 | 0.43333 | 13094 | 13188 | 94 | Rotate |  | 13124 | 85.67 | 155.19 | 10220.7 | -2799.17 | -575.58 | -2799.17 | 0.1 |  |  | 25 | 80 | 350 | 10.8 | 216.92 | 4200 | 3300 | 900 | 264 | 260 | 170 | 205
10/23/2021 | 15:56 | 16:24 | 0.46667 | 13188 | 13283 | 95 | Rotate |  | 13219 | 86.05 | 155.34 | 10227.56 | -2885.23 | -535.94 | -2885.23 | 0.43 |  |  | 25 | 80 | 350 | 11 | 203.57 | 4200 | 3350 | 850 | 264 | 260 | 170 | 205
10/23/2021 | 16:29 | 16:55 | 0.43333 | 13283 | 13377 | 94 | Rotate |  | 13313 | 86.68 | 155.67 | 10233.52 | -2970.6 | -497.04 | -2970.6 | 0.76 |  |  | 25 | 80 | 350 | 11 | 216.92 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 17:00 | 17:14 | 0.23333 | 13377 | 13387 | 10 | Slide | TTF: 150; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11; Drilling Parameters ROP: 42.86 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 17:14 | 17:58 | 0.73333 | 13387 | 13472 | 85 | Rotate |  | 13408 | 85.14 | 154.72 | 10240.29 | -3056.61 | -457.29 | -3056.61 | 1.9 |  |  | 25 | 80 | 350 | 11 | 115.91 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 18:03 | 18:25 | 0.36667 | 13472 | 13566 | 94 | Rotate |  | 13502 | 84.89 | 154.46 | 10248.46 | -3141.2 | -417.11 | -3141.2 | 0.38 |  |  | 25 | 80 | 350 | 11 | 256.36 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 18:36 | 18:40 | 0.066667 | 13566 | 13576 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 150 | 4200 | 3350 | 850 | 268 | 280 | 205 | 90
10/23/2021 | 18:40 | 18:55 | 0.25 | 13576 | 13587 | 11 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 44 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 18:55 | 19:20 | 0.41667 | 13587 | 13660 | 73 | Rotate |  | 13596 | 86.42 | 154.63 | 10255.58 | -3225.83 | -376.83 | -3225.83 | 1.64 |  |  | 25 | 80 | 350 | 12.5 | 175.2 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 19:26 | 19:30 | 0.066667 | 13660 | 13670 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 150 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 19:30 | 19:40 | 0.16667 | 13670 | 13675 | 5 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 30 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 19:40 | 20:05 | 0.41667 | 13675 | 13754 | 79 | Rotate |  | 13690 | 88.11 | 154.5 | 10260.07 | -3310.61 | -336.5 | -3310.61 | 1.8 |  |  | 25 | 80 | 350 | 12.5 | 189.6 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 20:11 | 20:35 | 0.4 | 13754 | 13848 | 94 | Rotate |  | 13784 | 88.35 | 154.12 | 10262.97 | -3395.28 | -295.77 | -3395.28 | 0.48 |  |  | 25 | 80 | 350 | 12.5 | 235 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 20:40 | 21:10 | 0.5 | 13848 | 13943 | 95 | Rotate |  | 13879 | 90.19 | 154.41 | 10264.18 | -3480.85 | -254.53 | -3480.85 | 1.96 |  |  | 25 | 80 | 350 | 12.5 | 190 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 21:15 | 21:20 | 0.083333 | 13943 | 13953 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 120 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 21:20 | 21:45 | 0.41667 | 13953 | 13970 | 17 | Slide | TTF: -165; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 40.8 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 21:54 | 22:05 | 0.18333 | 13970 | 14037 | 67 | Rotate |  | 13973 | 89.85 | 152.78 | 10264.15 | -3565.04 | -212.73 | -3565.04 | 1.77 |  |  | 25 | 80 | 350 | 12.5 | 365.45 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 22:10 | 22:13 | 0.05 | 14037 | 14047 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 200 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 22:13 | 23:05 | 0.86667 | 14047 | 14077 | 30 | Slide | 175 | 14068 | 89.01 | 154.55 | 10265.09 | -3650.17 | -170.59 | -3650.17 | 2.06 |  |  | 25 | 80 | 350 | 12.5 | 34.62 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 23:05 | 23:25 | 0.33333 | 14077 | 14132 | 55 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 165 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 23:30 | 23:35 | 0.083333 | 14132 | 14142 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 120 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/23/2021 | 23:35 | 24:00 | 0.41667 | 14142 | 14150 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 19.2 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/24/2021 | 00:00 | 00:15 | 0.25 | 14150 | 14158 | 8 | Slide | TTF: -175; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 32 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/24/2021 | 00:15 | 00:40 | 0.41667 | 14158 | 14227 | 69 | Rotate |  | 14163 | 86.13 | 154.82 | 10269.12 | -3735.96 | -130 | -3735.96 | 3.04 |  |  | 25 | 80 | 350 | 12.5 | 165.6 | 4200 | 3350 | 850 | 268 | 260 | 170 | 205
10/24/2021 | 00:45 | 01:15 | 0.5 | 14227 | 14322 | 95 | Rotate |  | 14258 | 86.56 | 154.77 | 10275.18 | -3821.74 | -89.63 | -3821.74 | 0.46 |  |  | 25 | 80 | 350 | 12.5 | 190 | 4200 | 3350 | 850 | 277 | 260 | 170 | 205
10/24/2021 | 01:20 | 01:23 | 0.05 | 14322 | 14332 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 200 | 4450 | 3500 | 950 | 277 | 310 | 205 | 90
10/24/2021 | 01:23 | 01:45 | 0.36667 | 14332 | 14349 | 17 | Slide | TTF: -160; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 46.36 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 01:45 | 02:10 | 0.41667 | 14349 | 14415 | 66 | Rotate |  | 14351 | 85.11 | 153.69 | 10281.93 | -3905.27 | -49.31 | -3905.27 | 1.94 |  |  | 25 | 80 | 350 | 12.5 | 158.4 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 02:15 | 02:45 | 0.5 | 14415 | 14510 | 95 | Rotate |  | 14446 | 85.09 | 153.22 | 10290.05 | -3989.94 | -7.01 | -3989.94 | 0.49 |  |  | 25 | 80 | 350 | 12.5 | 190 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 02:50 | 02:55 | 0.083333 | 14510 | 14520 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 120 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 02:55 | 03:05 | 0.16667 | 14520 | 14530 | 10 | Slide | TTF: 35; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12.5; Drilling Parameters ROP: 60 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 03:05 | 03:40 | 0.58333 | 14530 | 14604 | 74 | Rotate |  | 14540 | 86.28 | 154.24 | 10297.12 | -4073.99 | 34.48 | -4073.99 | 1.67 |  |  | 25 | 80 | 350 | 12.5 | 126.86 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 03:45 | 04:10 | 0.41667 | 14604 | 14699 | 95 | Rotate |  | 14635 | 87.74 | 154.11 | 10302.07 | -4159.39 | 75.8 | -4159.39 | 1.54 |  |  | 25 | 80 | 350 | 14.6 | 228 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 04:15 | 04:20 | 0.083333 | 14699 | 14709 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 14.6; Drilling Parameters ROP: 120 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 04:20 | 04:35 | 0.25 | 14709 | 14719 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 14.6; Drilling Parameters ROP: 40 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 04:35 | 05:05 | 0.5 | 14719 | 14794 | 75 | Rotate |  | 14730 | 86.92 | 153.26 | 10306.5 | -4244.45 | 117.87 | -4244.45 | 1.24 |  |  | 25 | 80 | 350 | 14.6 | 150 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 05:08 | 05:38 | 0.5 | 14794 | 14888 | 94 | Rotate |  | 14824 | 86.53 | 152.49 | 10311.87 | -4327.97 | 160.66 | -4327.97 | 0.92 |  |  | 25 | 80 | 350 | 14.6 | 188 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 05:42 | 06:07 | 0.41667 | 14888 | 14983 | 95 | Rotate |  | 14919 | 86.49 | 149.41 | 10317.65 | -4410.86 | 206.7 | -4410.86 | 3.24 |  |  | 25 | 80 | 350 | 14.6 | 228 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 06:12 | 06:27 | 0.25 | 14983 | 14998 | 15 | Slide | TTF: 120; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 14.6; Drilling Parameters ROP: 60 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 06:27 | 06:55 | 0.46667 | 14998 | 15077 | 79 | Rotate |  | 15013 | 86.95 | 154.45 | 10323.04 | -4493.64 | 250.84 | -4493.64 | 5.38 |  |  | 25 | 80 | 350 | 14.6 | 169.29 | 4450 | 3350 | 1100 | 277 | 310 | 170 | 205
10/24/2021 | 06:59 | 07:25 | 0.43333 | 15077 | 15171 | 94 | Rotate |  | 15107 | 86.81 | 152.55 | 10328.15 | -4577.63 | 292.72 | -4577.63 | 2.02 |  |  | 25 | 80 | 350 | 11.5 | 216.92 | 4450 | 3450 | 1000 | 279 | 310 | 170 | 205
10/24/2021 | 07:29 | 07:44 | 0.25 | 15171 | 15186 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11.5; Drilling Parameters ROP: 60 | 4450 | 3450 | 1000 | 277 | 310 | 170 | 205
10/24/2021 | 07:44 | 08:15 | 0.51667 | 15186 | 15266 | 80 | Rotate |  | 15202 | 84.67 | 147.25 | 10335.21 | -4659.56 | 340.21 | -4659.56 | 6 |  |  | 25 | 80 | 350 | 11.5 | 154.84 | 4450 | 3450 | 1000 | 275 | 310 | 170 | 205
10/24/2021 | 08:19 | 08:53 | 0.56667 | 15266 | 15286 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11.5; Drilling Parameters ROP: 35.29 | 4450 | 3450 | 1000 | 272 | 310 | 170 | 205
10/24/2021 | 08:53 | 09:28 | 0.58333 | 15286 | 15360 | 74 | Rotate |  | 15296 | 83.38 | 148.28 | 10345 | -4738.64 | 390.07 | -4738.64 | 1.75 |  |  | 25 | 80 | 350 | 11.5 | 126.86 | 4450 | 3450 | 1000 | 279 | 310 | 170 | 205
10/24/2021 | 09:32 | 10:12 | 0.66667 | 15360 | 15380 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11.5; Drilling Parameters ROP: 30 | 4450 | 3450 | 1000 | 268 | 310 | 170 | 205
10/24/2021 | 10:12 | 10:42 | 0.5 | 15380 | 15454 | 74 | Rotate |  | 15390 | 84.35 | 152.31 | 10355.05 | -4819.8 | 436.37 | -4819.8 | 4.39 |  |  | 25 | 80 | 350 | 11.5 | 148 | 4450 | 3450 | 1000 | 264 | 310 | 170 | 205
10/24/2021 | 10:46 | 11:17 | 0.51667 | 15454 | 15548 | 94 | Rotate |  | 15484 | 85.06 | 152.15 | 10363.72 | -4902.62 | 479.98 | -4902.62 | 0.77 |  |  | 25 | 80 | 350 | 11.5 | 181.94 | 4450 | 3450 | 1000 | 271 | 310 | 170 | 205
10/24/2021 | 11:21 | 11:38 | 0.28333 | 15548 | 15563 | 15 | Slide | TTF: 60; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11.5; Drilling Parameters ROP: 52.94 | 4450 | 3450 | 1000 | 271 | 310 | 170 | 205
10/24/2021 | 11:38 | 12:17 | 0.65 | 15563 | 15643 | 80 | Rotate |  | 15579 | 85.52 | 153.97 | 10371.52 | -4987.02 | 522.88 | -4987.02 | 1.97 |  |  | 25 | 80 | 350 | 11.5 | 123.08 | 4450 | 3450 | 1000 | 271 | 310 | 170 | 205
10/24/2021 | 12:22 | 12:53 | 0.51667 | 15643 | 15737 | 94 | Rotate |  | 15673 | 86.71 | 154.82 | 10377.89 | -5071.59 | 563.4 | -5071.59 | 1.55 |  |  | 25 | 80 | 350 | 11.5 | 181.94 | 4450 | 3450 | 1000 | 275 | 310 | 170 | 205
10/24/2021 | 12:57 | 13:27 | 0.5 | 15737 | 15830 | 93 | Rotate |  | 15766 | 87.62 | 154.45 | 10382.49 | -5155.52 | 603.19 | -5155.52 | 1.06 |  |  | 25 | 80 | 350 | 15 | 186 | 4500 | 3600 | 900 | 275 | 310 | 170 | 205
10/24/2021 | 13:31 | 13:37 | 0.1 | 15830 | 15846 | 16 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 160 | 4500 | 3600 | 900 | 275 | 310 | 170 | 205
10/24/2021 | 13:37 | 13:53 | 0.26667 | 15846 | 15855 | 9 | Slide | TTF: 140; Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 33.75 | 4500 | 3600 | 900 | 275 | 310 | 170 | 205
10/24/2021 | 16:17 | 16:27 | 0.16667 | 15855 | 15861 | 6 | Slide | 140 | 15861 | 86.55 | 155.93 | 10387.32 | -5241.64 | 643 | -5241.64 | 1.92 |  |  | 45 | 80 | 350 | 15 | 36 | 4500 | 3600 | 900 | 271 | 310 | 170 | 205
10/24/2021 | 16:27 | 16:54 | 0.45 | 15861 | 15925 | 64 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 142.22 | 4500 | 3600 | 900 | 271 | 310 | 170 | 205
10/24/2021 | 16:58 | 17:32 | 0.56667 | 15925 | 16019 | 94 | Rotate |  | 15955 | 86.61 | 156.46 | 10392.93 | -5327.49 | 680.88 | -5327.49 | 0.57 |  |  | 19 | 80 | 350 | 16.2 | 165.88 | 4055 | 3250 | 805 | 271 | 310 | 170 | 205
10/24/2021 | 17:35 | 18:00 | 0.41667 | 16019 | 16113 | 94 | Rotate |  | 16049 | 88.33 | 156.51 | 10397.08 | -5413.6 | 718.34 | -5413.6 | 1.83 |  |  | 25 | 80 | 350 | 15 | 225.6 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 18:00 | 19:55 | 1.9167 | 16113 | 16113 |  | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 19:55 | 20:00 | 0.083333 | 16113 | 16113 |  | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 20:00 | 20:15 | 0.25 | 16113 | 16123 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 40 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 20:15 | 20:55 | 0.66667 | 16123 | 16139 | 16 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 24 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 20:55 | 21:35 | 0.66667 | 16139 | 16206 | 67 | Rotate |  | 16142 | 85.55 | 156.4 | 10402.05 | -5498.72 | 755.44 | -5498.72 | 2.99 |  |  | 25 | 80 | 350 | 15 | 100.5 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 21:40 | 22:05 | 0.41667 | 16206 | 16299 | 93 | Rotate |  | 16235 | 86.6 | 156.35 | 10408.41 | -5583.73 | 792.62 | -5583.73 | 1.13 |  |  | 25 | 80 | 350 | 15 | 223.2 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 22:10 | 22:15 | 0.083333 | 16299 | 16309 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 120 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 22:15 | 22:45 | 0.5 | 16309 | 16317 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15; Drilling Parameters ROP: 16 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 22:45 | 23:20 | 0.58333 | 16317 | 16393 | 76 | Rotate |  | 16329 | 85.7 | 156.84 | 10414.72 | -5669.8 | 829.87 | -5669.8 | 1.09 |  |  | 25 | 80 | 350 | 15 | 130.29 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 23:25 | 23:55 | 0.5 | 16393 | 16488 | 95 | Rotate |  | 16424 | 85.21 | 156.57 | 10422.25 | -5756.78 | 867.33 | -5756.78 | 0.59 |  |  | 25 | 80 | 350 | 15 | 190 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/24/2021 | 23:55 | 24:00 | 0.083333 | 16488 | 16488 |  | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 15 | 4055 | 3600 | 455 | 271 | 310 | 170 | 205
10/25/2021 | 00:00 | 00:35 | 0.58333 | 16488 | 16582 | 94 | Rotate |  | 16518 | 86.19 | 156.35 | 10429.3 | -5842.71 | 904.76 | -5842.71 | 1.07 |  |  | 26.5 | 80 | 350 | 18.5 | 161.14 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 00:40 | 01:15 | 0.58333 | 16582 | 16676 | 94 | Rotate |  | 16612 | 87.7 | 156.4 | 10434.31 | -5928.71 | 942.38 | -5928.71 | 1.61 |  |  | 26.5 | 80 | 350 | 18.5 | 161.14 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 01:20 | 01:25 | 0.083333 | 16676 | 16686 | 10 | Slide | TTF: -155; Drilling Parameters WOB: 26.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18.5; Drilling Parameters ROP: 120 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 01:25 | 03:30 | 2.0833 | 16686 | 16771 | 85 | Rotate |  | 16707 | 86.93 | 154.43 | 10438.76 | -6015 | 981.86 | -6015 | 2.22 |  |  | 26.5 | 80 | 350 | 18.5 | 40.8 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 03:35 | 04:00 | 0.41667 | 16771 | 16866 | 95 | Rotate |  | 16802 | 86.91 | 154.71 | 10443.86 | -6100.67 | 1022.59 | -6100.67 | 0.3 |  |  | 26.5 | 80 | 350 | 18.5 | 228 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 04:05 | 04:40 | 0.58333 | 16866 | 16961 | 95 | Rotate |  | 16897 | 87.07 | 155.05 | 10448.85 | -6186.57 | 1062.86 | -6186.57 | 0.4 |  |  | 26.5 | 80 | 350 | 18.5 | 162.86 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 04:43 | 05:15 | 0.53333 | 16961 | 17055 | 94 | Rotate |  | 16991 | 86.76 | 153.18 | 10453.91 | -6271.01 | 1103.84 | -6271.01 | 2.01 |  |  | 26.5 | 80 | 350 | 18.5 | 176.25 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 05:18 | 05:20 | 0.033333 | 17055 | 17065 | 10 | Rotate | Drilling Parameters WOB: 26.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18.5; Drilling Parameters ROP: 300 | 4150 | 3600 | 550 | 237 | 320 | 190
10/25/2021 | 05:20 | 05:45 | 0.41667 | 17065 | 17075 | 10 | Slide | TTF: 20; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18.5; Drilling Parameters ROP: 24 | 4150 | 3600 | 550 | 233 | 320 | 190
10/25/2021 | 05:45 | 06:15 | 0.5 | 17075 | 17088 | 13 | Rotate |  | 17084 | 87.33 | 152.01 | 10458.71 | -6353.46 | 1146.59 | -6353.46 | 1.4 |  |  | 50 | 80 | 350 | 18.5 | 26 | 4150 | 3600 | 550 | 230 | 320 | 190

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 292 |  | North Reference: |  | GRID |  | Total Drilled: |  | 1841
Site: |  |  |  |  | Bighorn - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 46
Well Name: |  |  |  |  | Bighorn Plains H02 |  |  | Survey / Gamma Offset: |  |  |  |  | 60.00 / 51.00 |  |  |  |  | Grid Conv: |  |  |  | 292 |  | VS Azimuth: |  | 153.98 |  | Rotate: |  | 1795
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
10/26/2021 | 16:07 | 16:39 | 0.53333 | 17088 | 17144 | 56 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 105 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 16:52 | 17:38 | 0.76667 | 17144 | 17238 | 94 | Rotate |  | 17178 | 87.63 | 151.43 | 10462.84 | -6436.16 | 1191.08 | -6436.16 | 0.69 |  |  | 22 | 80 | 350 | 21 | 122.61 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 17:42 | 18:25 | 0.71667 | 17238 | 17333 | 95 | Rotate |  | 17273 | 87.74 | 151.84 | 10466.68 | -6519.69 | 1236.18 | -6519.69 | 0.45 |  |  | 22 | 80 | 350 | 21 | 132.56 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 18:30 | 19:15 | 0.75 | 17333 | 17426 | 93 | Rotate |  | 17366 | 88.89 | 151.85 | 10469.41 | -6601.64 | 1280.04 | -6601.64 | 1.24 |  |  | 22 | 80 | 350 | 21 | 124 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 19:20 | 19:23 | 0.05 | 17426 | 17436 | 10 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 200 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 19:23 | 20:45 | 1.3667 | 17436 | 17448 | 12 | Slide | TTF: 130; Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 8.78 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 20:45 | 21:50 | 1.0833 | 17448 | 17520 | 72 | Rotate |  | 17460 | 86.78 | 152.9 | 10472.96 | -6684.86 | 1323.59 | -6684.86 | 2.51 |  |  | 22 | 80 | 350 | 21 | 66.46 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 22:10 | 22:50 | 0.66667 | 17520 | 17615 | 95 | Rotate |  | 17555 | 86.8 | 154.11 | 10478.28 | -6769.75 | 1365.91 | -6769.75 | 1.27 |  |  | 22 | 80 | 350 | 21 | 142.5 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 22:55 | 23:30 | 0.58333 | 17615 | 17707 | 92 | Rotate |  | 17647 | 87.06 | 153.51 | 10483.21 | -6852.19 | 1406.45 | -6852.19 | 0.71 |  |  | 22 | 80 | 350 | 21 | 157.71 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/26/2021 | 23:35 | 24:00 | 0.41667 | 17707 | 17745 | 38 | Rotate |  | 17741 | 87.2 | 153.31 | 10487.92 | -6936.14 | 1448.47 | -6936.14 | 0.26 |  |  | 22 | 80 | 350 | 21 | 91.2 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/27/2021 | 00:00 | 00:15 | 0.25 | 17745 | 17801 | 56 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 224 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/27/2021 | 00:15 | 00:20 | 0.083333 | 17801 | 17801 |  | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/27/2021 | 00:20 | 00:55 | 0.58333 | 17801 | 17801 |  | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/27/2021 | 00:55 | 01:00 | 0.083333 | 17801 | 17811 | 10 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 120 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/27/2021 | 01:20 | 02:10 | 0.83333 | 17811 | 17821 | 10 | Slide | TTF: 65; Drilling Parameters WOB: 26; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 12 | 4300 | 3450 | 850 | 212 | 250 | 177 | 120
10/27/2021 | 02:10 | 02:50 | 0.66667 | 17821 | 17896 | 75 | Rotate |  | 17836 | 87.64 | 154.3 | 10492.19 | -7021.29 | 1490.37 | -7021.29 | 1.14 |  |  | 26 | 80 | 350 | 21 | 112.5 | 4890 | 3850 | 1040 | 212 | 250 | 177 | 120
10/27/2021 | 02:55 | 03:25 | 0.5 | 17896 | 17990 | 94 | Rotate |  | 17930 | 87.77 | 154.98 | 10495.96 | -7106.17 | 1530.59 | -7106.17 | 0.74 |  |  | 26 | 80 | 350 | 21 | 188 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 03:30 | 04:10 | 0.66667 | 17990 | 18085 | 95 | Rotate |  | 18025 | 87.77 | 153.69 | 10499.65 | -7191.73 | 1571.71 | -7191.73 | 1.36 |  |  | 26 | 80 | 350 | 21 | 142.5 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 04:13 | 04:50 | 0.61667 | 18085 | 18180 | 95 | Rotate |  | 18120 | 87.13 | 153.76 | 10503.88 | -7276.83 | 1613.72 | -7276.83 | 0.68 |  |  | 26 | 80 | 350 | 21 | 154.05 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 04:54 | 05:00 | 0.1 | 18180 | 18190 | 10 | Rotate | Drilling Parameters WOB: 26; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 100 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 05:00 | 05:40 | 0.66667 | 18190 | 18200 | 10 | Slide | TTF: 65; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 15 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 05:40 | 06:25 | 0.75 | 18200 | 18274 | 74 | Rotate |  | 18214 | 87.58 | 154.42 | 10508.22 | -7361.29 | 1654.75 | -7361.29 | 0.85 |  |  | 26 | 80 | 350 | 21 | 98.67 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 06:30 | 07:07 | 0.61667 | 18274 | 18369 | 95 | Rotate |  | 18309 | 88.11 | 154.43 | 10511.79 | -7446.92 | 1695.73 | -7446.92 | 0.56 |  |  | 26 | 80 | 350 | 21 | 154.05 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 07:12 | 07:48 | 0.6 | 18369 | 18463 | 94 | Rotate |  | 18403 | 87.89 | 154.09 | 10515.07 | -7531.54 | 1736.53 | -7531.54 | 0.43 |  |  | 26 | 80 | 350 | 21 | 156.67 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 08:17 | 08:52 | 0.58333 | 18463 | 18557 | 94 | Rotate |  | 18497 | 87.83 | 153.96 | 10518.58 | -7615.99 | 1777.67 | -7615.99 | 0.15 |  |  | 26 | 80 | 350 | 21 | 161.14 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 09:28 | 10:05 | 0.61667 | 18557 | 18652 | 95 | Rotate |  | 18592 | 88.37 | 153.75 | 10521.73 | -7701.22 | 1819.51 | -7701.22 | 0.61 |  |  | 26 | 80 | 350 | 21 | 154.05 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 10:31 | 10:45 | 0.23333 | 18652 | 18672 | 20 | Rotate | Drilling Parameters WOB: 26; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 85.71 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 10:45 | 11:30 | 0.75 | 18672 | 18686 | 14 | Slide | 180 | 18686 | 85.6 | 154.05 | 10526.67 | -7785.51 | 1860.8 | -7785.51 | 2.96 |  |  | 37 | 80 | 350 | 21 | 18.67 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 11:30 | 11:58 | 0.46667 | 18686 | 18746 | 60 | Rotate | Drilling Parameters WOB: 26; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21; Drilling Parameters ROP: 128.57 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 12:12 | 13:00 | 0.8 | 18746 | 18840 | 94 | Rotate |  | 18780 | 84.87 | 154.54 | 10534.48 | -7869.91 | 1901.43 | -7869.91 | 0.93 |  |  | 26 | 80 | 350 | 21 | 117.5 | 4890 | 3850 | 1040 | 210 | 310 | 198
10/27/2021 | 13:29 | 14:03 | 0.56667 | 18840 | 18929 | 89 | Rotate |  | 18869 | 84.52 | 154.4 | 10542.71 | -7949.88 | 1939.63 | -7949.88 | 0.42 |  |  | 26 | 80 | 350 | 21 | 157.06 | 4890 | 3850 | 1040 | 207 | 310 | 198