## Summary
Magnolia Oil & Gas / Boone C1H / LTX1124621 / Patterson 285
Report Date: | 08/04/2021 | Current Depth: | 19102
Start Date: | 06/19/2021 | Casing Depth: | 0
Daily Cost: | 7450 | Distance to TD:
Well Cost: | 190450 | Average ROP: | 0
Drilling Hours: | 0 | Svy MD: | 19102
24Hr Forcast: | Continue POOH | Svy Inc: | 88.6
Current BHA: |  | Svy Azi: | 140.28
Current BRT Hrs: | 59.25 | Svy TVD: | 10707.51
Bit Make / Model: |  | Svy NS: | -7348.76
POOH in last 24Hrs: | Yes | Svy EW: | 3863.28
Rig Down Time: | Yes | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Douglas Ferguson | MWD Day: | Jeff Campbell
Directional Driller Night: | Nathan Marks | MWD Night: | Charlie Mckirahan
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 309
24Hr Summary: | Drill to TD of well, POOH | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MTR500030 | 7/8 3.8 2.5 HS 88 -.005 Slick |  |  | Clean
PPM250019 | 6/7 8.8 2.12 HS 88 .001 Slick |  |  | Clean
PPM50011 | 6/7 8.8 2.12 HS 88 .025 Slick |  |  | Clean
PPM25006 | 6/7 8.8 2.12 HS 88 .002 Slick |  |  | Clean
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
ZSB775208 | UBHO |  |  | Dirty |  | 44.85 | 44.85
ZSB775209 | UBHO |  |  | Clean
ZSB500042 | UBHO |  |  | Clean
ZSB500050 | UBHO |  |  | Dirty |  | 62.37 | 62.37
ZSB500043 | UBHO |  |  | Clean
| UBHO |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 285 |  |  | Well: |  | Boone C1H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Total Drilled (Usft): |  | 18997 |  |  | Total Days: |  | 17
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 105 | 2725 | 2620 |  | 421.45 |  | 7.82 | 6.22 | 3.7 | 26.17
2 | 2 | 9.875 | 2725 | 10030 | 7305 |  | 229.24 |  | 7.62 | 31.87 | 12.98 | 64.83
3 | 0 | 9.875 | 10030 | 10030 | 0 |  | 0 |  | 0 | 0 | 6.25 | 18
4 | 3 | 6.75 | 10030 | 14855 | 4825 |  | 94.15 |  | 31.19 | 51.25 | 11.12 | 83.25
5 | 0 | 6.75 | 14855 | 17632 | 2777 |  | 97.21 |  | 8.71 | 28.57 | 18.77 | 68.25
6 | 5 | 6.75 | 17632 | 19102 | 1470 |  | 128.38 |  | 3.88 | 11.45 | 20.32 | 49.25
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | New |  | 1-1-RR-X-I-RR-TD |  | 1.178 | 2620 | 6.2167 | 421.45
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 0-1-CT-S-X-I-NO-TD |  | 1.491 | 7305 | 31.8667 | 229.24
0 |  |  |  |  | 9.875 | 0-1-CT-S-N-I-NO-TD |  |  |  | 0 | 0 | 0 | 0
3 | Halliburton |  | GTD64M |  | 6.75 | New |  | 1-1-WT-S-X-I- |  | 1.491 | 4825 | 51.25 | 94.15
0 | Halliburton |  | GTD64M |  | 6.75 | New |  | 1-1-RR-N-X-I-RR-PP |  | 1.491 | 2777 | 28.5667 | 97.21
5 | Halliburton |  | GTD64M |  | 6.75 | New |  | 1-1-BT-S-X-I-NO-TD |  | 1.491 | 1470 | 11.45 | 128.38
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.51 | 2620 |  | 421.45
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 5.92 | 7305 |  | 229.24
3 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 0 | 5.92 | 0 |  | 0
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5 | 2.12 | 4.03 | 4825 |  | 94.15
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5 | 2.12 | 4.04 | 2777 |  | 97.21
6 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5 | 2.12 | 4.01 | 1470 |  | 128.38
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Doug Ferguson |  | Chris Day |  | Jeff Campbell |  | Charlie Mckirahan |  | Bobby Guin |  | Greg Johnson |  | Pete Langille
Douglas Ferguson |  | Donny Klein
Nathan Marks |  | Donny Klein Nathan Marks
Doug Ferguson
Nathan Marks
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.75 |  | 2620 |  | 418.53 |  | 8.76 / 0.00 |  | 1 |  | 6.26
INT: INTERMEDIATE |  |  | 4.99 / 2.06 |  | 7305 |  | 229.5 |  | 2.05 / 0.00 |  | 2 |  | 31.83
CRV: CURVE |  |  | 1.44 / 0.63 |  | 839 |  | 64.49 |  |  |  | 1 |  | 13.01
LAT: LATERAL |  |  | 8.56 / 7.02 |  | 8233 |  | 105.27 |  | 1.79 / 0.00 |  | 3 |  | 78.21
Total |  |  | 16.99 |  | 18997 |  | 146.91 |  | 12.60 / 0.00 |  | 6 |  | 129.31
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 105.00 | 2725.00 | 502.08 | 2415.00 | 141.38 | 205.00 | 7.82 | 2620.00 | 418.53 | 6.26 | 1.45
INT: INTERMEDIATE-BHA 2 |  |  | 2725.00 | 10030.00 | 363.58 | 6748.00 | 41.97 | 557.00 | 7.62 | 7305.00 | 229.50 | 31.83 | 13.27
INT: INTERMEDIATE-BHA 3 |  |  | 10030.00 | 10030.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
CRV: CURVE-BHA 4 |  |  | 10030.00 | 10869.00 | 66.67 | 106.00 | 64.19 | 733.00 | 87.37 | 839.00 | 64.49 | 13.01 | 11.42
LAT: LATERAL-BHA 6 |  |  | 17632.00 | 19102.00 | 167.81 | 1413.00 | 18.75 | 57.00 | 3.88 | 1470.00 | 128.27 | 11.46 | 3.04
LAT: LATERAL-BHA 5 |  |  | 14855.00 | 17632.00 | 180.56 | 2535.00 | 16.68 | 242.00 | 8.71 | 2777.00 | 97.27 | 28.55 | 14.51
LAT: LATERAL-BHA 4 |  |  | 10869.00 | 14855.00 | 174.39 | 3214.00 | 39.05 | 772.00 | 19.37 | 3986.00 | 104.35 | 38.20 | 19.77
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1124621 | Total Drilled(Usft) | 18997.00
Operator | Magnolia Oil & Gas | Drilling Hours | 129.35
Well Name | Boone C1H | Avg ROP(Usft/hr) | 146.87
Rig | Patterson 285 | Rotary Drilled(Usft) | 16431.00
State | Texas | Rotary Hours | 65.90
County | Washington | Rotary ROP(Usft/hr) | 249.33
Formation | Austin Chalk | Rotary % | 86.49
Start Date | 06/19/2021 | Slide Drilled(Usft) | 2566.00
End Date | 08/04/2021 | Slide Hours | 63.45
Days On Well | 17 | Slide ROP(Usft/hr) | 40.44
Start Depth (Usft) | 105.00 | Slide % | 13.51
End Depth (Usft) | 19102.00
Total Drilled (Usft) | 18997.00
# BHA's | 6
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 17.37 / 0.00
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 06/19/2021 | 07/06/2021 | 07/26/2021 | 07/27/2021
End Date | 06/20/2021 | 07/10/2021 | 07/27/2021 | 08/04/2021
Total Days | 2.00 | 5.00 | 1.44 | 8.56
Start Depth (Usft) | 105.00 | 2725.00 | 10030.00 | 10869.00
End Depth (Usft) | 2725.00 | 10030.00 | 10869.00 | 19102.00
Total Drilled(Usft) | 2620.00 | 7305.00 | 839.00 | 8233.00
Drilling Hours | 6.22 | 31.87 | 13.02 | 78.25
Circulating Hours | 3.70 | 19.23 | 2.27 | 50.68
Total D&C Hours | 9.92 | 51.10 | 15.28 | 128.93
Avg ROP(Usft/hr) | 421.45 | 229.24 | 64.46 | 105.21
Rotary Drilled(Usft) | 2415.00 | 6748.00 | 106.00 | 7162.00
Rotary Hours | 4.78 | 18.60 | 1.58 | 40.93
Rotary ROP(Usft/hr) | 504.88 | 362.80 | 66.95 | 174.97
Rotary % | 92.18 | 92.38 | 12.63 | 86.99
Slide Drilled(Usft) | 205.00 | 557.00 | 733.00 | 1071.00
Slide Hours | 1.43 | 13.27 | 11.43 | 37.32
Slide ROP(Usft/hr) | 143.02 | 41.98 | 64.11 | 28.70
Slide % | 7.82 | 7.62 | 87.37 | 13.01
# BHA | 1 | 2 | 1 | 3
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 8.77 / 0.00 | 3.30 / 0.00 | 0.00 / 0.00 | 5.30 / 0.00
Total Phase Hrs | 17.97 | 49.45 | 15.17 | 168.58
Phase ROP (Usft/hr) | 145.83 | 147.72 | 55.32 | 48.84
Avg Motor Yield (°/100ft) | 6.56 | 11.65 | 10.30 | 18.72
Avg Rotary DLS (°/100ft) | 0.27 | 0.62 | 0.00 | 1.95
Avg Rotary TF | 44.94 | -163.84 | 0.00 | -6.32
Avg Slide Length (Usft) | 12.06 | 24.22 | 56.38 | 20.21
# Slides | 17 | 23 | 13 | 53
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5 | 6
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4 | BHA 5 | BHA 6
Bit Size | 13.500 | 9.875 | 9.875 | 6.750 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 |  | Halliburton / GTD64M | Halliburton / GTD64M | Halliburton / GTD64M
Bit TFA | 1.178 | 1.491 | 0.000 | 1.491 | 1.491 | 1.491
Grade In | New | New | 0-1-CT-S-N-I-NO-TD | New | New | New
Grade Out | 1-1-RR-X-I-RR-TD | 0-1-CT-S-X-I-NO-TD |  | 1-1-WT-S-X-I- | 1-1-RR-N-X-I-RR-PP | 1-1-BT-S-X-I-NO-TD
Motor SN | PPM800001 | 800033 | PPM800033 | PPM250007 | PPM250015 | PPM250021
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 3.00 / 7.08 / 15.00 | 8.00 / 31.78 / 42.00 | 999999.00 / 0.00 / -999999.00 | 11.68 / 31.97 / 51.57 | 24.00 / 31.36 / 41.00 | 27.00 / 27.00 / 27.00
Diff P (psi) | 100.00 / 260.76 / 500.00 | 200.00 / 656.03 / 1000.00 | 999999.00 / 0.00 / -999999.00 | 15.26 / 729.02 / 3678.46 | 290.00 / 1110.72 / 1126.00 | 600.00 / 600.00 / 600.00
Bend | 1.500 | 2.000 | 0.000 | 2.120 | 2.120 | 2.120
Date In | 06/19/2021 | 07/06/2021 | 07/08/2021 | 07/26/2021 | 07/30/2021 | 08/01/2021
Date Out | 06/20/2021 | 07/08/2021 | 07/09/2021 | 07/29/2021 | 08/01/2021 | 08/03/2021
Time In | 21:50 | 02:00 | 24:00 | 12:15 | 01:30 | 22:45
Time Out | 24:00 | 18:50 | 18:00 | 23:30 | 21:45 | 24:00
BRT Hrs | 26.17 | 64.83 | 18.00 | 83.25 | 68.25 | 49.25
Start Depth (Usft) | 105.00 | 2725.00 | 10030.00 | 10030.00 | 14855.00 | 17632.00
End Depth (Usft) | 2725.00 | 10030.00 | 10030.00 | 14855.00 | 17632.00 | 19102.00
Total Drilled(Usft) | 2620.00 | 7305.00 | 0.00 | 4825.00 | 2777.00 | 1470.00
Drilling Hours | 6.22 | 31.87 | 0.00 | 51.25 | 28.57 | 11.45
Circulating Hours | 3.70 | 12.98 | 6.25 | 11.12 | 18.77 | 20.32
Total D&C Hours | 9.92 | 44.85 | 6.25 | 62.37 | 47.33 | 31.77
Avg ROP(Usft/hr) | 421.45 | 229.24 | 0.00 | 94.15 | 97.21 | 128.38
Rotary Drilled(Usft) | 2415.00 | 6748.00 | 0.00 | 3320.00 | 2535.00 | 1413.00
Rotary Hours | 4.78 | 18.60 | 0.00 | 20.05 | 14.05 | 8.42
Rotary ROP(Usft/hr) | 504.88 | 362.80 | 0.00 | 165.59 | 180.43 | 167.88
Rotary % | 92.18 | 92.38 | 0.00 | 68.81 | 91.29 | 96.12
Slide Drilled(Usft) | 205.00 | 557.00 | 0.00 | 1505.00 | 242.00 | 57.00
Slide Hours | 1.43 | 13.27 | 0.00 | 31.20 | 14.52 | 3.03
Slide ROP(Usft/hr) | 143.02 | 41.98 | 0.00 | 48.24 | 16.67 | 18.79
Slide % | 7.82 | 7.62 | 0.00 | 31.19 | 8.71 | 3.88
Motor Failure | NO | NO | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | YES | YES | NO
LIH | NO | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 6.56 | 11.65 | 0.00 | 15.59 | 22.90 | 14.46
Avg Rotary DLS (°/100ft) | 0.27 | 0.62 | 0.00 | 3.65 | 0.92 | 0.47
Avg Rotary TF | 44.94 | -163.84 | 0.00 | 58.04 | -24.02 | -18.85
Avg Slide Length (Usft) | 12.06 | 24.22 | 0.00 | 33.44 | 16.13 | 9.50
# Slides | 17 | 23 | 0 | 45 | 15 | 6

## Personnel Report
|  | Job # | LTX1124621 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31153 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 285 |  | Well: |  | Boone C1H
|  | Date: | 08/04/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Boone C1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Charlie Mckirahan | Night MWD |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
Charlie Mckirahan | Night MWD |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
Charlie Mckirahan | Night MWD |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
Chris Day | Night DD |  | 07/26/2021 - 00:00 | 07/29/2021 - 00:00 |  | 4.00 / 0.00
Donny Klein | Night DD |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
Donny Klein | Night DD |  | 07/30/2021 - 00:00 | 08/02/2021 - 00:00 |  | 4.00 / 0.00
Donny Klein Nathan Marks | Night DD |  | 08/03/2021 - 00:00 | 08/03/2021 - 00:00 |  | 1.00 / 0.00
Doug Ferguson | Day DD |  | 07/26/2021 - 00:00 | 08/03/2021 - 00:00 |  | 9.00 / 0.00
Doug Ferguson | Night DD |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
Douglas Ferguson | Day DD |  | 08/04/2021 - 00:00 | 08/04/2021 - 00:00 |  | 1.00 / 0.00
Jeff Campbell | Day MWD |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
Jeff Campbell | Day MWD |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
Jeff Campbell | Day MWD |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
NA | Fourth Man |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
NA | Fourth Man |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
NA | Fourth Man |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
NA | Trainee 1 |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
NA | Trainee 1 |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
NA | Trainee 1 |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
NA | Trainee 2 |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
NA | Trainee 2 |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
NA | Trainee 2 |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
NA | Rss Eng. 1 |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
NA | Rss Eng. 1 |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
NA | Rss Eng. 1 |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
NA | Rss Eng. 2 |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
NA | Rss Eng. 2 |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
NA | Rss Eng. 2 |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
NA | Third Man |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
NA | Third Man |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
NA | Third Man |  | 07/26/2021 - 00:00 | 08/04/2021 - 00:00 |  | 10.00 / 0.00
Nathan Marks | Day DD |  | 06/19/2021 - 00:00 | 06/20/2021 - 00:00 |  | 2.00 / 0.00
Nathan Marks | Day DD |  | 07/06/2021 - 00:00 | 07/10/2021 - 00:00 |  | 5.00 / 0.00
Nathan Marks | Night DD |  | 08/04/2021 - 00:00 | 08/04/2021 - 00:00 |  | 1.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1124621 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Boone C1H | [7 empty] | Day DD: |  |  |  |  | Douglas Ferguson | [5 empty] | API #: |  |  |  | 42-477-31153
|  |  |  | AFE #: |  |  | 21DD0167MG | [7 empty] | Night DD: |  |  |  |  | Nathan Marks | [5 empty] | Company Man: |  |  |  | Bobby Guin
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Jeff Campbell | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 285 | [7 empty] | Night DD: |  |  |  |  | Charlie Mckirahan | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 06/19/2021 | 06/20/2021 | 06/21/2021 | 06/22/2021 | 06/23/2021 | 06/24/2021 | 06/25/2021 | 06/26/2021 | 06/27/2021 | 06/28/2021 | 06/29/2021 | 06/30/2021 | 07/01/2021 | 07/02/2021 | 07/03/2021 | 07/04/2021 | 07/05/2021 | 07/06/2021 | 07/07/2021 | 07/08/2021 | 07/09/2021 | 07/10/2021 | 07/11/2021 | 07/12/2021 | 07/13/2021 | 07/14/2021 | 07/15/2021 | 07/16/2021 | 07/17/2021 | 07/18/2021 | 07/19/2021 | 07/20/2021 | 07/21/2021 | 07/22/2021 | 07/23/2021 | 07/24/2021 | 07/25/2021 | 07/26/2021 | 07/27/2021 | 07/28/2021 | 07/29/2021 | 07/30/2021 | 07/31/2021 | 08/01/2021 | 08/02/2021 | 08/03/2021 | 08/04/2021 | 08/05/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 9.875 | SPL613 |  | Steel | 56211 | 0 | 31 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 9.875 | SPL613 |  | Steel | 56410 | 4 | 31 | [16 empty] | O | X | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13601237 | 4 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13618579 | 0 | 16 | [31 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13571904 | 0 | 7 | [40 empty] | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13601236 | 3 | 4 | [43 empty] | X | X | X | O
Bit |  | 6.75 | GTD64M |  | Steel | 13618580 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.75 | Crossover |  | Steel | 118447 | 4 | 10 | [16 empty] | O | X | X | X | X | O | O | O | O | O
Cross Over |  | 6.562 | Crossover |  | Steel | 4555 | 4 | 10 | [16 empty] | O | X | X | X | X | O | O | O | O | O
Cross Over |  | 6.5 | Crossover |  | Steel | SD115443 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.375 | Crossover |  | Steel | SD112143 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.688 | Crossover |  | Steel | SD113731 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.625 | Crossover |  | Steel | SD39491 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover |  | Steel | SD104622 | 2 | 10 | X | X | [14 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover |  | Steel | SD118446 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | SD119105 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | SD119312 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | X/O- XT39P x CET43B |  | Steel | SD119784 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.5 | X/O- XT39P x CET43B |  | Steel | SD119787 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | SD119767 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | SD119769 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO |  | Steel | ZSB775208 | 3 | 10 | [16 empty] | O | X | X | X | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO |  | Steel | ZSB775209 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | ZSB500042 | 0 | 31 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | ZSB500050 | 4 | 28 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | O | O | O
MWD / LWD |  | 5.188 | UBHO |  | Steel | ZSB500043 | 0 | 3 | [44 empty] | O | O | O
MWD / LWD |  |  | UBHO |  | Steel |  | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 8 | 7/8 5.9 2.0 HPO -.014 Slick |  | Steel | PPM800032 | 0 | 5 | [16 empty] | O | O | O | O | O
Motor |  | 8 | 7/8 5.9 2.0 HPO -.020 Slick |  | Steel | 800033 | 3 | 10 | [16 empty] | O | X | X | X | O | O | O | O | O | O
Motor |  | 8 | 7/8 5.9 2.0 HPO -.023 Slick |  | Steel | 800040 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Motor |  |  | 7/8 5.9 2.0 HPO -.007 Slick |  | Steel | PPM800077 | 0 | 6 | [20 empty] | O | O | O | O | O | O
Motor |  |  | 7/8 3.8 2.5 HS 88 -.005 Slick |  | Steel | MTR500030 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  |  | 6/7 8.8 2.12 HS 88 .001 Slick |  | Steel | PPM250019 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 6/7 8.8 2.12 HS 88 .025 Slick |  | Steel | PPM50011 | 0 | 4 | [43 empty] | O | O | O | O
Motor |  |  | 6/7 8.8 2.12 HS 88 .002 Slick |  | Steel | PPM25006 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 6.5 | 6 Joints of 6 1/2 in DC |  | Steel | Rig-3 | 4 | 31 | [16 empty] | O | X | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 6.5 | 6 Joints of 6 1/2 in DC |  | Steel | Rig-3 | 4 | 31 | [16 empty] | O | X | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 7.75 | NM Drill Collar |  | Non-Mag | 53215 | 4 | 10 | [16 empty] | O | X | X | X | X | O | O | O | O | O
Collar |  | 8.062 | NM Drill Collar |  | Non-Mag | 55727 | 3 | 10 | [16 empty] | O | X | X | X | O | O | O | O | O | O
Collar |  | 7.625 | NM Pony Drill Collar |  | Non-Mag | 54384 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Collar |  | 7.938 | NM Pony Drill Collar |  | Non-Mag | SD51725 | 3 | 10 | [16 empty] | O | X | X | X | O | O | O | O | O | O
Collar |  | 7.875 | NM Drill Collar |  | Non-Mag | SD56047 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Collar |  | 7.875 | NM Drill Collar |  | Non-Mag | SD56224 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD55850 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD56785 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5" Non Mag Drill Collar |  | Non-Mag | SD56709 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5" Non Mag Drill Collar |  | Non-Mag | SD56772 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 4.938 | 5" Non Mag Pony Collar |  | Non-Mag | SD56927 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | 5" Non Mag Pony Collar |  | Non-Mag | SD6928 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | 5" Non Mag Pony Collar |  | Non-Mag | SD56653 | 0 | 12 | [35 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | NM Drill Collar |  | Non-Mag | SD56627 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | NM Drill Collar |  | Non-Mag | SD56775 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | NM Pony Drill Collar |  | Non-Mag | SD56679 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | NM Pony Drill Collar |  | Non-Mag | SD56870 | 0 | 47 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 5 | 21 Stands 5 in DP |  | Steel | Rig-2 | 0 | 31 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 5 | 21 Stands 5 in DP |  | Steel | Rig-2 | 0 | 31 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 5 | 9- Joints of 5 HWDP |  | Steel | Rig-1 | 0 | 31 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 2 Stands Drill Pipe |  | Steel | Rig-4 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 26 Stands Drill Pipe |  | Steel | Rig-5 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 33 Stands Drill Pipe |  | Steel | Rig-6 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax |  | Steel | A52100 | 4 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | O | O | O | O | O | O
Accelerator |  | 5 | Tomax |  | Steel | A52123 | 5 | 7 | [40 empty] | O | X | X | X | X | X | O
Accelerator |  | 5.75 | Tomax |  | Steel | A52139 | 0 | 4 | [43 empty] | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD104811 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD109537 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD101160 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD118523 | 0 | 10 | [16 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD118436 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119563 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119697 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119699 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI |  | Steel | 41015 | 0 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.812 | BTI |  | Steel | 41015 | 0 | 7 | [40 empty] | O | O | O | O | O | O | O
Sub |  |  | Crossover |  | Steel | GT5033445 | 0 | 4 | [43 empty] | O | O | O | O
Sub |  |  | Crossover |  | Steel | GT5033442 | 0 | 4 | [43 empty] | O | O | O | O
Agitator |  | 6.625 | Agitator |  | Steel | PG6750030 | 0 | 31 | [16 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator |  | 6.688 | Agitator |  | Steel | P6675-0022 | 0 | 27 | [20 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0049 | 4 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | O | O | O | O | O | O
Agitator |  | 5.25 | Agitator- Ball Drop |  | Steel | PG525-0037 | 4 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | O | O | O | O | O | O
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0037 | 4 | 7 | [37 empty] | X | X | X | X | O | O | O | O | O | O
Agitator |  | 5.25 | Agitator / Ball Drop |  | Steel | PG525-0049 | 4 | 7 | [37 empty] | X | X | X | X | O | O | O | O | O | O
Reamer |  | 5.375 | Reamer |  | Steel | DTI-DNR-363 | 9 | 22 | [25 empty] | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Doug Ferguson |  |  |  | 9 | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Douglas Ferguson |  |  |  | 1 | [47 empty] | 1
Day DD |  |  | Nathan Marks |  |  |  | 7 |  | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Chris Day |  |  |  | 4 | [38 empty] | 1 | 1 | 1 | 1
Night DD |  |  | Donny Klein |  |  |  | 6 |  | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1
Night DD |  |  | Donny Klein Nathan Marks |  |  |  | 1 | [46 empty] | 1
Night DD |  |  | Doug Ferguson |  |  |  | 5 | [18 empty] | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Nathan Marks |  |  |  | 1 | [47 empty] | 1
Day MWD |  |  | Jeff Campbell |  |  |  | 17 |  | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Charlie Mckirahan |  |  |  | 17 |  | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 17 |  | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 17 |  | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 285 |  |  | Well: |  | Boone C1H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0167MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
Rig-2 | 21 Stands 5 in DP | 5 | 1971.19 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 07/05/2021
Rig-3 | 6 Joints of 6 1/2 in DC | 6.5 | 184.12 |  | 4 1/2 XH / 4 1/2 XH | Dirty |  | 07/05/2021
PPM800032 | 7/8 5.9 2.0 HPO -.014 Slick | 8 | 37.91 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/09/2021
Rig-2 | 21 Stands 5 in DP | 5 | 1971.19 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 07/05/2021
Rig-3 | 6 Joints of 6 1/2 in DC | 6.5 | 184.12 |  | 4 1/2 XH / 4 1/2 XH | Dirty |  | 07/05/2021
800033 | 7/8 5.9 2.0 HPO -.020 Slick | 8 | 37.58 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
800040 | 7/8 5.9 2.0 HPO -.023 Slick | 8 |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
PPM800077 | 7/8 5.9 2.0 HPO -.007 Slick |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/09/2021 |  | 07/14/2021
ZSB775208 | UBHO | 7.75 | 3.83 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
53215 | NM Drill Collar | 7.75 | 28.03 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
55727 | NM Drill Collar | 8.062 | 28.76 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
54384 | NM Pony Drill Collar | 7.625 | 10.68 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
118447 | Crossover | 6.75 | 2.9 |  | 4 1/2 XH / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
4555 | Crossover | 6.562 | 3 |  | 4 1/2 IF / 4 1/2 XH | Dirty |  | 07/05/2021 |  | 07/14/2021
56211 | SPL613 | 9.875 | 1.5 |  | 6 5/8 REG | Clean |  | 07/05/2021
PG6750030 | Agitator | 6.625 | 24.71 |  | 4 1/2 IF / 4 1/2 IF | Clean |  | 07/05/2021
Rig-1 | 9- Joints of 5 HWDP | 5 | 271.04 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 07/05/2021
ZSB775209 | UBHO | 7.75 | 3.78 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
ZSB500042 | UBHO | 5.25 | 3.66 |  | XT39 / XT39 | Clean |  | 07/05/2021
ZSB500050 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Dirty |  | 07/05/2021 |  | 08/01/2021
SD115443 | Crossover | 6.5 | 3.06 |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 07/05/2021 |  | 07/14/2021
SD112143 | Crossover | 6.375 | 2.9 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 07/05/2021 |  | 07/14/2021
SD113731 | Crossover | 6.688 | 2.2 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 07/05/2021 |  | 07/14/2021
SD104811 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD109537 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD101160 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD118523 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SDLC3332 | Lift Cap |  |  |  | 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD39491 | Crossover | 6.625 | 3.56 |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD104622 | Crossover | 6.5 | 2.08 |  | 4 1/2 IF / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
SD118446 | Crossover | 6.5 | 2.63 |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD51725 | NM Pony Drill Collar | 7.938 | 8.33 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/05/2021 |  | 07/14/2021
SD56047 | NM Drill Collar | 7.875 | 29.19 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
SD56224 | NM Drill Collar | 7.875 | 29.83 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/05/2021 |  | 07/14/2021
56410 | SPL613 | 9.875 | 1.5 |  | 6 5/8 REG | Dirty |  | 07/05/2021
P6675-0022 | Agitator | 6.688 | 24.61 |  | 4 1/2 IF / 4 1/2 IF | Clean |  | 07/09/2021
SD55850 | NM Drill Collar | 5 | 30.35 |  | XT39 / XT39 | Clean |  | 07/14/2021
SD56785 | NM Drill Collar | 5 | 30.84 |  | XT39 / XT39 | Clean |  | 07/14/2021
SD118436 | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 07/14/2021
SD119563 | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 07/14/2021
SD119105 | Crossover |  |  |  | DS 42 / XT39 | Clean |  | 07/14/2021
SD119312 | Crossover |  |  |  | DS 42 / XT39 | Clean |  | 07/14/2021
SD119697 | Lift Sub |  |  |  | XT39 | Clean |  | 07/14/2021
SD119699 | Lift Sub |  |  |  | XT39 | Clean |  | 07/14/2021
SDLC3356 | Lift Cap |  |  |  | XT39 | Clean |  | 07/14/2021
MTR500030 | 7/8 3.8 2.5 HS 88 -.005 Slick |  |  |  | XT39 / 3 1/2 Reg | Clean |  | 07/14/2021
PG525-0049 | Agitator | 5.25 | 23.46 |  | CET43 / CET43 | Dirty |  | 07/14/2021
PG525-0037 | Agitator- Ball Drop | 5.25 | 20.9 |  | CET43 / CET43 | Dirty |  | 07/14/2021
A52100 | Tomax | 5 | 18.35 |  | XT39 / XT39 | Dirty |  | 07/14/2021
41015 | BTI | 4.875 | 1.65 |  | XT39 / XT39 | Clean |  | 07/14/2021
13601237 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 07/14/2021
Rig-4 | 2 Stands Drill Pipe | 4.5 | 188.77 |  | CET43 / CET43 | Dirty |  | 07/14/2021
DTI-DNR-363 | Reamer | 5.375 | 8.58 |  | CET43 / CET43 | Dirty |  | 07/14/2021
Rig-5 | 26 Stands Drill Pipe | 4.5 | 2453.38 |  | CET43 / CET43 | Dirty |  | 07/14/2021
Rig-6 | 33 Stands Drill Pipe | 4.5 | 3114.93 |  | CET43 / CET43 | Dirty |  | 07/14/2021
13618579 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Clean |  | 07/20/2021
PPM250019 | 6/7 8.8 2.12 HS 88 .001 Slick |  |  |  | XT39 / 3 1/2 Reg | Clean |  | 07/24/2021
SD56709 | 5" Non Mag Drill Collar | 5 | 29.96 |  | XT39 / XT39 | Clean |  | 07/24/2021
SD56772 | 5" Non Mag Drill Collar | 5 | 29.91 |  | XT39 / XT39 | Clean |  | 07/24/2021
SD56927 | 5" Non Mag Pony Collar | 4.938 | 10.04 |  | XT39 / XT39 | Clean |  | 07/24/2021
SD6928 | 5" Non Mag Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 07/24/2021
SD119784 | X/O- XT39P x CET43B |  |  |  | XT39 / CET43 | Clean |  | 07/24/2021
SD119787 | X/O- XT39P x CET43B | 5.5 | 3.67 |  | XT39 / CET43 | Clean |  | 07/24/2021
SD56653 | 5" Non Mag Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 07/24/2021
A52123 | Tomax | 5 | 17.92 |  | XT39 / XT39 | Dirty |  | 07/29/2021
41015 | BTI | 4.812 | 1.65 |  | XT39 / XT39 | Clean |  | 07/29/2021
PG525-0037 | Agitator | 5.25 | 20.9 |  | CET43 / CET43 | Dirty |  | 07/29/2021
PG525-0049 | Agitator / Ball Drop | 5.25 | 21.44 |  | CET43 / CET43 | Dirty |  | 07/29/2021
13571904 | GTD64M | 6.75 | 0.75 |  | 3 1/2 REG / N/A | Clean |  | 07/29/2021
A52139 | Tomax | 5.75 | 18.35 |  |  | Clean |  | 08/01/2021
13601236 | GTD64M | 6.75 | 0.75 |  | 3 1/2 REG / NA | Dirty |  | 08/01/2021
GT5033445 | Crossover |  |  |  | XT39 / 3 1/2 IF | Clean |  | 08/01/2021
GT5033442 | Crossover |  |  |  | XT39 / 3 1/2 IF | Clean |  | 08/01/2021
PPM50011 | 6/7 8.8 2.12 HS 88 .025 Slick | 5 | 33.16 |  | XT39 / 3 1/2 Reg | Clean |  | 08/01/2021
ZSB500043 | UBHO | 5.188 | 4 |  | XT39 / XT39 | Clean |  | 08/02/2021
13618580 | GTD64M | 6.75 | 0.75 |  | 3 1/2 REG / NA | Clean |  | 08/05/2021
PPM25006 | 6/7 8.8 2.12 HS 88 .002 Slick |  |  |  | XT39 / 3 1/2 Reg | Clean |  | 08/05/2021
SD56627 | NM Drill Collar |  |  |  | XT39 / XT39 | Clean |  | 08/05/2021
SD56775 | NM Drill Collar |  |  |  | XT39 / XT39 | Clean |  | 08/05/2021
SD56679 | NM Pony Drill Collar |  |  |  | XT39 / XT39 | Clean |  | 08/05/2021
SD56870 | NM Pony Drill Collar |  |  |  | XT39 / XT39 | Clean |  | 08/05/2021
SD119767 | Crossover |  |  |  | XT39 / CET43 | Clean |  | 08/05/2021
SD119769 | Crossover |  |  |  | XT39 / CET43 | Clean |  | 08/05/2021
0 | UBHO |  |  |  | XT39 / XT39 | Clean |  | 08/05/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 285 |  |  | Well: |  | Boone C1H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 38426 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
7/8 5.9 1.5 Stab HPO -.022 NBS 13 | PPM800001 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
Stabalizer | SD610174 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
NM Pony Drill Collar | SD49205 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
UBHO | ZSB775210 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
NM Drill Collar | SD50132 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
NM Drill Collar | SD55726 | 06/19/2021 | 08/04/2021 | 47 | 1 | 1 |  | 3.7 | 6.22 | 26.17
Crossover | SD104622 | 07/05/2021 | 07/14/2021 | 10 | 1 | 1 |  | 3.7 | 6.22 | 26.17
SPL613 | 56410 | 07/05/2021 | 08/04/2021 | 31 | 3 | 2 ,3 |  | 19.23 | 31.87 | 82.83
7/8 5.9 2.0 HPO -.020 Slick | 800033 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 |  | 12.98 | 31.87 | 64.83
NM Pony Drill Collar | SD51725 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 |  | 12.98 | 31.87 | 64.83
UBHO | ZSB775208 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 |  | 12.98 | 31.87 | 64.83
NM Drill Collar | 55727 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 |  | 12.98 | 31.87 | 64.83
NM Drill Collar | 53215 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 ,3 |  | 19.23 | 31.87 | 82.83
Crossover | 118447 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 ,3 |  | 19.23 | 31.87 | 82.83
6 Joints of 6 1/2 in DC | Rig-3 | 07/05/2021 | 08/04/2021 | 31 | 3 | 2 ,3 |  | 19.23 | 31.87 | 82.83
Crossover | 4555 | 07/05/2021 | 07/14/2021 | 10 | 3 | 2 ,3 |  | 19.23 | 31.87 | 82.83
Agitator | PG675-0016 | 06/19/2021 | 08/04/2021 | 47 | 3 | 2 |  | 12.98 | 31.87 | 64.83
7/8 5.9 2.0 HPO -.020 Slick | PPM800033 | 06/19/2021 | 08/04/2021 | 47 | 1 | 3 |  | 6.25 | 0 | 18
GTD64M | 13601237 | 07/14/2021 | 08/04/2021 | 22 | 3 | 4 |  | 11.12 | 51.25 | 83.25
6/7 8.8 2.12 HS 88 .005 Slick | PPM250007 | 06/19/2021 | 08/04/2021 | 47 | 3 | 4 |  | 11.12 | 51.25 | 83.25
BTI | 41014 | 06/19/2021 | 08/04/2021 | 47 | 3 | 4 |  | 11.12 | 51.25 | 83.25
NM Pony Drill Collar | SD56841 | 06/19/2021 | 08/04/2021 | 47 | 8 | 4 ,5 ,6 |  | 50.2 | 91.27 | 200.75
UBHO | ZSB500050 | 07/05/2021 | 08/01/2021 | 28 | 3 | 4 |  | 11.12 | 51.25 | 83.25
NM Drill Collar | SD56784 | 06/19/2021 | 08/04/2021 | 47 | 8 | 4 ,5 ,6 |  | 50.2 | 91.27 | 200.75
NM Drill Collar | SD56786 | 06/19/2021 | 08/04/2021 | 47 | 8 | 4 ,5 ,6 |  | 50.2 | 91.27 | 200.75
Tomax | A52100 | 07/14/2021 | 08/04/2021 | 22 | 3 | 4 |  | 11.12 | 51.25 | 83.25
Crossover | GT52331431 | 06/19/2021 | 08/04/2021 | 47 | 8 | 4 ,5 ,6 |  | 50.2 | 91.27 | 200.75
Reamer | DTI-DNR-363 | 07/14/2021 | 08/04/2021 | 22 | 8 | 4 ,5 ,6 |  | 50.2 | 91.27 | 200.75
Agitator | PG525-0049 | 07/29/2021 | 08/04/2021 | 7 | 3 | 4 |  | 11.12 | 51.25 | 83.25
Agitator- Ball Drop | PG525-0037 | 07/29/2021 | 08/04/2021 | 7 | 3 | 4 |  | 11.12 | 51.25 | 83.25
GTD64M | 13594950 | 06/19/2021 | 08/04/2021 | 47 | 3 | 5 |  | 18.77 | 28.57 | 68.25
6/7 8.8 2.12 HS 88 .012 Slick | PPM250015 | 06/19/2021 | 08/04/2021 | 47 | 3 | 5 |  | 18.77 | 28.57 | 68.25
BTI | 41016 | 06/19/2021 | 08/04/2021 | 47 | 5 | 5 ,6 |  | 39.08 | 40.02 | 117.5
UBHO | ZSB500025 | 06/19/2021 | 08/04/2021 | 47 | 5 | 5 ,6 |  | 39.08 | 40.02 | 117.5
Tomax | A52123 | 07/29/2021 | 08/04/2021 | 7 | 5 | 5 ,6 |  | 39.08 | 40.02 | 117.5
Agitator | PG525-0055 | 06/19/2021 | 08/04/2021 | 47 | 3 | 5 |  | 18.77 | 28.57 | 68.25
Agitator | PG525-0054 | 06/19/2021 | 08/04/2021 | 47 | 3 | 5 |  | 18.77 | 28.57 | 68.25
GTD64M | 13601236 | 08/01/2021 | 08/04/2021 | 4 | 2 | 6 |  | 20.32 | 11.45 | 49.25
6/7 8.8 2.12 HS 88 .010 Slick | PPM250021 | 06/19/2021 | 08/04/2021 | 47 | 2 | 6 |  | 20.32 | 11.45 | 49.25
Agitator | PG525-0051 | 06/19/2021 | 08/04/2021 | 47 | 2 | 6 |  | 20.32 | 11.45 | 49.25
Agitator | PG525-0057 | 06/19/2021 | 08/04/2021 | 47 | 2 | 6 |  | 20.32 | 11.45 | 49.25
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | well
Facility |  |  | Boone-Borgstedt - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Boone C1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Boone C1H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 365.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Boone-Borgstedt - Washington County, TX
Map Northing |  |  | 205767.59 US survey foot |  |  | Map Easting |  |  | 3134092.38 US survey foot
Latitude |  |  | 30° 10' 55.63700" N |  |  | Longitude |  |  | 96° 44' 36.77222" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.849
Well: |  |  | Boone C1H
Local North |  |  | -59.23 Usft |  |  | Local East |  |  | -46.99 Usft
Map Northing |  |  | 205707.94 US survey foot |  |  | Map Easting |  |  | 3134039.12 US survey foot
Latitude |  |  | 30° 10' 55.06592" N |  |  | Longitude |  |  | 96° 44' 37.32910" W
Depth Datum |  |  | well |  |  | Datum Elevation |  |  | 365.00 Usft
GL Elevation |  |  | 337.00 Usft
Grid Convergence |  |  | 1.849
Well bore: |  |  | Boone C1H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 30/06/2021
Total Field (nT) |  |  | 46596.4 |  |  | Dip Angle (°) |  |  | 58.817
Declination (°) |  |  | 2.883
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 141.38
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Boone C1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2652 |  |  | Boone C1H S1 |  |  | MWD+HDGM
2652 |  |  | 9961 |  |  | Boone C 1H S2 |  |  | MWD+HDGM
9961 |  |  | 19102 |  |  | Boone C1H S3 |  |  | MWD+HRGM+FDIR
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -365 | 205707.94 | 3134039.12 | 30.182 | -96.7437 | 0
135 | 0.5 | 210 | 135 | -0.51 | -0.29 | 0.21 | 0.37 | 0.37 | 111.11 | 210 | 135 | -230 | 205707.43 | 3134038.83 | 30.182 | -96.7437 | 210
227 | 0.5 | 233.2 | 226.99 | -1.1 | -0.82 | 0.35 | 0.22 | 0 | 25.22 | 101.6 | 92 | -138.01 | 205706.84 | 3134038.3 | 30.182 | -96.7437 | 216.64
316 | 0.6 | 222.9 | 315.99 | -1.67 | -1.44 | 0.4 | 0.16 | 0.11 | -11.57 | -49.9 | 89 | -49.01 | 205706.27 | 3134037.68 | 30.182 | -96.7437 | 220.83
410 | 0.6 | 227.5 | 409.99 | -2.37 | -2.14 | 0.51 | 0.05 | 0 | 4.89 | 92.3 | 94 | 44.99 | 205705.57 | 3134036.98 | 30.182 | -96.7437 | 222.17
504 | 0.6 | 232.2 | 503.98 | -3 | -2.89 | 0.54 | 0.05 | 0 | 5 | 92.35 | 94 | 138.98 | 205704.94 | 3134036.23 | 30.182 | -96.7437 | 223.98
598 | 0.74 | 242 | 597.97 | -3.59 | -3.82 | 0.42 | 0.19 | 0.15 | 10.43 | 44.27 | 94 | 232.97 | 205704.35 | 3134035.3 | 30.182 | -96.7437 | 226.8
692 | 0.79 | 245.28 | 691.97 | -4.14 | -4.94 | 0.15 | 0.07 | 0.05 | 3.49 | 42.86 | 94 | 326.97 | 205703.8 | 3134034.18 | 30.182 | -96.7437 | 230.04
785 | 1.05 | 255.66 | 784.95 | -4.62 | -6.35 | -0.35 | 0.33 | 0.28 | 11.16 | 37.92 | 93 | 419.95 | 205703.32 | 3134032.77 | 30.182 | -96.7437 | 233.96
879 | 1.23 | 271.06 | 878.94 | -4.82 | -8.2 | -1.35 | 0.38 | 0.19 | 16.38 | 67.42 | 94 | 513.94 | 205703.12 | 3134030.92 | 30.182 | -96.7437 | 239.56
973 | 1.53 | 262.63 | 972.91 | -4.96 | -10.45 | -2.65 | 0.38 | 0.32 | -8.97 | -38.35 | 94 | 607.91 | 205702.98 | 3134028.67 | 30.1819 | -96.7438 | 244.61
1067 | 2.08 | 254.14 | 1066.86 | -5.59 | -13.33 | -3.96 | 0.65 | 0.59 | -9.03 | -30.21 | 94 | 701.86 | 205702.35 | 3134025.79 | 30.1819 | -96.7438 | 247.27
1161 | 3.03 | 251.07 | 1160.77 | -6.86 | -17.32 | -5.46 | 1.02 | 1.01 | -3.27 | -9.73 | 94 | 795.77 | 205701.08 | 3134021.8 | 30.1819 | -96.7438 | 248.41
1255 | 3.46 | 248.01 | 1254.62 | -8.73 | -22.31 | -7.1 | 0.49 | 0.46 | -3.26 | -23.47 | 94 | 889.62 | 205699.21 | 3134016.81 | 30.1819 | -96.7438 | 248.63
1349 | 4.18 | 251.96 | 1348.41 | -10.85 | -28.19 | -9.12 | 0.82 | 0.77 | 4.2 | 22.06 | 94 | 983.41 | 205697.09 | 3134010.93 | 30.1819 | -96.7438 | 248.95
1443 | 4.62 | 246.97 | 1442.13 | -13.39 | -34.93 | -11.34 | 0.62 | 0.47 | -5.31 | -43.53 | 94 | 1077.13 | 205694.55 | 3134004.19 | 30.1819 | -96.7438 | 249.03
1536 | 4.99 | 250.6 | 1534.8 | -16.2 | -42.2 | -13.68 | 0.51 | 0.4 | 3.9 | 41.23 | 93 | 1169.8 | 205691.74 | 3133996.92 | 30.1819 | -96.7439 | 249
1630 | 6.09 | 249.78 | 1628.36 | -19.28 | -50.73 | -16.6 | 1.17 | 1.17 | -0.87 | -4.52 | 94 | 1263.36 | 205688.66 | 3133988.39 | 30.1819 | -96.7439 | 249.19
1724 | 7.01 | 251.05 | 1721.75 | -22.87 | -60.84 | -20.1 | 0.99 | 0.98 | 1.35 | 9.58 | 94 | 1356.75 | 205685.07 | 3133978.28 | 30.1819 | -96.7439 | 249.4
1818 | 7.77 | 252.11 | 1814.97 | -26.68 | -72.31 | -24.28 | 0.82 | 0.81 | 1.13 | 10.7 | 94 | 1449.97 | 205681.26 | 3133966.81 | 30.1819 | -96.744 | 249.75
1912 | 8.52 | 252.27 | 1908.02 | -30.75 | -84.99 | -29.02 | 0.8 | 0.8 | 0.17 | 1.81 | 94 | 1543.02 | 205677.19 | 3133954.13 | 30.1819 | -96.744 | 250.11
2006 | 9.31 | 253.26 | 2000.88 | -35.06 | -98.9 | -34.33 | 0.86 | 0.84 | 1.05 | 11.48 | 94 | 1635.88 | 205672.88 | 3133940.22 | 30.1819 | -96.744 | 250.48
2099 | 10.05 | 252.88 | 2092.56 | -39.62 | -113.86 | -40.11 | 0.8 | 0.8 | -0.41 | -5.12 | 93 | 1727.56 | 205668.32 | 3133925.26 | 30.1819 | -96.7441 | 250.81
2194 | 10.63 | 252.81 | 2186.01 | -44.65 | -130.15 | -46.35 | 0.61 | 0.61 | -0.07 | -1.28 | 95 | 1821.01 | 205663.29 | 3133908.97 | 30.1819 | -96.7441 | 251.07
2288 | 11.3 | 252.94 | 2278.3 | -49.91 | -147.24 | -52.9 | 0.71 | 0.71 | 0.14 | 2.18 | 94 | 1913.3 | 205658.03 | 3133891.88 | 30.1818 | -96.7442 | 251.27
2381 | 11.91 | 251.52 | 2369.4 | -55.63 | -165.05 | -59.55 | 0.72 | 0.66 | -1.53 | -25.79 | 93 | 2004.4 | 205652.31 | 3133874.07 | 30.1818 | -96.7442 | 251.37
2475 | 12.9 | 251.53 | 2461.2 | -62.03 | -184.21 | -66.51 | 1.05 | 1.05 | 0.01 | 0.13 | 94 | 2096.2 | 205645.91 | 3133854.91 | 30.1818 | -96.7443 | 251.39
2569 | 13.86 | 250.85 | 2552.65 | -69.05 | -204.79 | -73.88 | 1.03 | 1.02 | -0.72 | -9.64 | 94 | 2187.65 | 205638.89 | 3133834.33 | 30.1818 | -96.7444 | 251.37
2652 | 14.62 | 249.67 | 2633.1 | -75.95 | -224.01 | -80.48 | 0.98 | 0.92 | -1.42 | -21.48 | 83 | 2268.1 | 205631.99 | 3133815.11 | 30.1818 | -96.7444 | 251.27
2777 | 14.82 | 248.42 | 2753.99 | -87.31 | -253.67 | -90.11 | 0.3 | 0.16 | -1 | -58.41 | 125 | 2388.99 | 205620.63 | 3133785.45 | 30.1817 | -96.7445 | 251.01
2871 | 14.39 | 249.45 | 2844.96 | -95.83 | -275.78 | -97.26 | 0.53 | -0.46 | 1.1 | 149.37 | 94 | 2479.96 | 205612.11 | 3133763.34 | 30.1817 | -96.7446 | 250.84
2965 | 14.99 | 254.15 | 2935.89 | -103.25 | -298.42 | -105.59 | 1.42 | 0.64 | 5 | 65.57 | 94 | 2570.89 | 205604.69 | 3133740.7 | 30.1817 | -96.7447 | 250.91
3059 | 14.93 | 255.99 | 3026.7 | -109.5 | -321.86 | -115.34 | 0.51 | -0.06 | 1.96 | 98.09 | 94 | 2661.7 | 205598.44 | 3133717.26 | 30.1817 | -96.7448 | 251.21
3153 | 14.68 | 255.04 | 3117.58 | -115.51 | -345.11 | -125.16 | 0.37 | -0.27 | -1.01 | -136.3 | 94 | 2752.58 | 205592.43 | 3133694.01 | 30.1817 | -96.7448 | 251.49
3246 | 14.64 | 253.78 | 3207.55 | -121.83 | -367.78 | -134.37 | 0.35 | -0.04 | -1.35 | -97.76 | 93 | 2842.55 | 205586.11 | 3133671.34 | 30.1817 | -96.7449 | 251.67
3340 | 16.19 | 257.78 | 3298.17 | -127.92 | -392 | -144.72 | 2 | 1.65 | 4.26 | 36.39 | 94 | 2933.17 | 205580.02 | 3133647.12 | 30.1816 | -96.745 | 251.93
3434 | 16.62 | 257.57 | 3388.34 | -133.59 | -417.94 | -156.48 | 0.46 | 0.46 | -0.22 | -7.95 | 94 | 3023.34 | 205574.35 | 3133621.18 | 30.1816 | -96.7451 | 252.27
3527 | 16.54 | 257.34 | 3477.48 | -139.36 | -443.84 | -168.14 | 0.11 | -0.09 | -0.25 | -140.74 | 93 | 3112.48 | 205568.58 | 3133595.28 | 30.1816 | -96.7451 | 252.57
3622 | 16.44 | 256.89 | 3568.57 | -145.37 | -470.13 | -179.85 | 0.17 | -0.11 | -0.47 | -128.27 | 95 | 3203.57 | 205562.57 | 3133568.99 | 30.1816 | -96.7452 | 252.82
3715 | 16.51 | 255.54 | 3657.75 | -151.65 | -495.74 | -190.93 | 0.42 | 0.08 | -1.45 | -80.29 | 93 | 3292.75 | 205556.29 | 3133543.38 | 30.1816 | -96.7453 | 252.99
3809 | 16.46 | 255.34 | 3747.89 | -158.36 | -521.56 | -201.8 | 0.08 | -0.05 | -0.21 | -131.48 | 94 | 3382.89 | 205549.58 | 3133517.56 | 30.1816 | -96.7454 | 253.11
3903 | 16.61 | 255.43 | 3838 | -165.11 | -547.44 | -212.69 | 0.16 | 0.16 | 0.1 | 9.73 | 94 | 3473 | 205542.83 | 3133491.68 | 30.1816 | -96.7455 | 253.22
3998 | 16.72 | 255.4 | 3929.01 | -171.97 | -573.81 | -223.78 | 0.12 | 0.12 | -0.03 | -4.49 | 95 | 3564.01 | 205535.97 | 3133465.31 | 30.1815 | -96.7456 | 253.32
4093 | 15.02 | 255.15 | 4020.39 | -178.57 | -598.93 | -234.31 | 1.79 | -1.79 | -0.26 | -177.82 | 95 | 3655.39 | 205529.37 | 3133440.19 | 30.1815 | -96.7456 | 253.4
4188 | 14.31 | 255.08 | 4112.29 | -184.75 | -622.18 | -243.99 | 0.75 | -0.75 | -0.07 | -178.6 | 95 | 3747.29 | 205523.19 | 3133416.94 | 30.1815 | -96.7457 | 253.46
4283 | 14.11 | 254.32 | 4204.38 | -190.9 | -644.67 | -253.22 | 0.29 | -0.21 | -0.8 | -137.36 | 95 | 3839.38 | 205517.04 | 3133394.45 | 30.1815 | -96.7458 | 253.5
4378 | 14.11 | 252.99 | 4296.52 | -197.42 | -666.89 | -262 | 0.34 | 0 | -1.4 | -90.64 | 95 | 3931.52 | 205510.52 | 3133372.23 | 30.1815 | -96.7459 | 253.51
4471 | 14.67 | 254.69 | 4386.6 | -203.84 | -689.09 | -270.84 | 0.75 | 0.6 | 1.83 | 37.86 | 93 | 4021.6 | 205504.1 | 3133350.03 | 30.1815 | -96.7459 | 253.52
4565 | 14.95 | 255.51 | 4477.48 | -210.02 | -712.31 | -280.5 | 0.37 | 0.3 | 0.87 | 37.21 | 94 | 4112.48 | 205497.92 | 3133326.81 | 30.1814 | -96.746 | 253.57
4659 | 14.98 | 255.81 | 4568.29 | -216.03 | -735.83 | -290.48 | 0.09 | 0.03 | 0.32 | 68.98 | 94 | 4203.29 | 205491.91 | 3133303.29 | 30.1814 | -96.7461 | 253.64
4753 | 14.77 | 255.5 | 4659.14 | -222.01 | -759.21 | -300.4 | 0.24 | -0.22 | -0.33 | -159.4 | 94 | 4294.14 | 205485.93 | 3133279.91 | 30.1814 | -96.7461 | 253.7
4847 | 14.6 | 255.97 | 4750.07 | -227.88 | -782.3 | -310.23 | 0.22 | -0.18 | 0.5 | 145.2 | 94 | 4385.07 | 205480.06 | 3133256.82 | 30.1814 | -96.7462 | 253.76
4941 | 14.33 | 255.06 | 4841.09 | -233.75 | -805.04 | -319.83 | 0.38 | -0.29 | -0.97 | -140.35 | 94 | 4476.09 | 205474.19 | 3133234.08 | 30.1814 | -96.7463 | 253.81
5034 | 13.91 | 256.96 | 4931.28 | -239.24 | -827.05 | -329.28 | 0.67 | -0.45 | 2.04 | 133.1 | 93 | 4566.28 | 205468.7 | 3133212.07 | 30.1814 | -96.7464 | 253.87
5128 | 13.66 | 256.41 | 5022.57 | -244.4 | -848.84 | -338.86 | 0.3 | -0.27 | -0.59 | -152.6 | 94 | 4657.57 | 205463.54 | 3133190.28 | 30.1814 | -96.7464 | 253.94
5222 | 15 | 256.69 | 5113.65 | -249.81 | -871.47 | -348.75 | 1.43 | 1.43 | 0.3 | 3.1 | 94 | 4748.65 | 205458.13 | 3133167.65 | 30.1814 | -96.7465 | 254
5316 | 16 | 255.9 | 5204.23 | -255.77 | -895.87 | -359.33 | 1.09 | 1.06 | -0.84 | -12.3 | 94 | 4839.23 | 205452.17 | 3133143.25 | 30.1813 | -96.7466 | 254.07
5412 | 15.71 | 254.9 | 5296.57 | -262.37 | -921.25 | -370.01 | 0.42 | -0.3 | -1.04 | -137.19 | 96 | 4931.57 | 205445.57 | 3133117.87 | 30.1813 | -96.7467 | 254.1
5506 | 15.32 | 253.82 | 5387.15 | -269.15 | -945.47 | -379.83 | 0.52 | -0.41 | -1.15 | -143.99 | 94 | 5022.15 | 205438.79 | 3133093.65 | 30.1813 | -96.7467 | 254.11
5601 | 15.34 | 252.81 | 5478.77 | -276.36 | -969.52 | -389.21 | 0.28 | 0.02 | -1.06 | -86.2 | 95 | 5113.77 | 205431.58 | 3133069.6 | 30.1813 | -96.7468 | 254.09
5694 | 16.56 | 253.29 | 5568.19 | -283.81 | -993.97 | -398.65 | 1.32 | 1.31 | 0.52 | 6.4 | 93 | 5203.19 | 205424.13 | 3133045.15 | 30.1813 | -96.7469 | 254.06
5788 | 17.14 | 253.08 | 5658.15 | -291.69 | -1020.05 | -408.77 | 0.62 | 0.62 | -0.22 | -6.09 | 94 | 5293.15 | 205416.25 | 3133019.07 | 30.1813 | -96.747 | 254.04
5882 | 16.03 | 256.46 | 5748.24 | -298.76 | -1045.92 | -419.39 | 1.56 | -1.18 | 3.6 | 140.61 | 94 | 5383.24 | 205409.18 | 3132993.2 | 30.1812 | -96.7471 | 254.06
5976 | 14.81 | 257.44 | 5838.86 | -304.41 | -1070.27 | -430.17 | 1.33 | -1.3 | 1.04 | 168.42 | 94 | 5473.86 | 205403.53 | 3132968.85 | 30.1812 | -96.7471 | 254.12
6070 | 14.26 | 257.43 | 5929.85 | -309.54 | -1093.29 | -440.53 | 0.59 | -0.59 | -0.01 | -179.74 | 94 | 5564.85 | 205398.4 | 3132945.83 | 30.1812 | -96.7472 | 254.19
6164 | 14.27 | 257.01 | 6020.95 | -314.67 | -1115.88 | -450.63 | 0.11 | 0.01 | -0.45 | -84.68 | 94 | 5655.95 | 205393.27 | 3132923.24 | 30.1812 | -96.7473 | 254.25
6258 | 14.09 | 257.39 | 6112.08 | -319.77 | -1138.34 | -460.66 | 0.22 | -0.19 | 0.4 | 152.84 | 94 | 5747.08 | 205388.17 | 3132900.78 | 30.1812 | -96.7474 | 254.31
6353 | 13.55 | 256.75 | 6204.33 | -324.85 | -1160.46 | -470.5 | 0.59 | -0.57 | -0.67 | -164.5 | 95 | 5839.33 | 205383.09 | 3132878.66 | 30.1812 | -96.7474 | 254.36
6447 | 14.01 | 259.27 | 6295.63 | -329.49 | -1182.35 | -480.54 | 0.8 | 0.49 | 2.68 | 53.76 | 94 | 5930.63 | 205378.45 | 3132856.77 | 30.1812 | -96.7475 | 254.43
6540 | 14.18 | 260.62 | 6385.83 | -333.44 | -1204.65 | -491.37 | 0.4 | 0.18 | 1.45 | 63.31 | 93 | 6020.83 | 205374.5 | 3132834.47 | 30.1812 | -96.7476 | 254.53
6634 | 14.27 | 260.54 | 6476.95 | -337.22 | -1227.44 | -502.64 | 0.1 | 0.1 | -0.09 | -12.36 | 94 | 6111.95 | 205370.72 | 3132811.68 | 30.1811 | -96.7476 | 254.64
6729 | 13.43 | 261.18 | 6569.18 | -340.84 | -1249.89 | -513.83 | 0.9 | -0.88 | 0.67 | 169.97 | 95 | 6204.18 | 205367.1 | 3132789.23 | 30.1811 | -96.7477 | 254.75
6822 | 13.92 | 256.86 | 6659.55 | -345.04 | -1271.46 | -524.01 | 1.22 | 0.53 | -4.65 | -66.48 | 93 | 6294.55 | 205362.9 | 3132767.66 | 30.1811 | -96.7478 | 254.82
6916 | 14.59 | 255.21 | 6750.66 | -350.63 | -1293.92 | -533.65 | 0.83 | 0.71 | -1.76 | -32.03 | 94 | 6385.66 | 205357.31 | 3132745.2 | 30.1811 | -96.7479 | 254.84
7010 | 13.64 | 255.37 | 6841.82 | -356.45 | -1316.09 | -542.94 | 1.01 | -1.01 | 0.17 | 177.73 | 94 | 6476.82 | 205351.49 | 3132723.03 | 30.1811 | -96.7479 | 254.85
7103 | 14.41 | 252.18 | 6932.04 | -362.76 | -1337.71 | -551.51 | 1.17 | 0.83 | -3.43 | -46.67 | 93 | 6567.04 | 205345.18 | 3132701.41 | 30.1811 | -96.748 | 254.83
7197 | 14.64 | 253.2 | 7023.04 | -369.77 | -1360.22 | -560.08 | 0.37 | 0.24 | 1.09 | 48.54 | 94 | 6658.04 | 205338.17 | 3132678.9 | 30.1811 | -96.7481 | 254.79
7291 | 13.01 | 255.21 | 7114.31 | -375.91 | -1381.83 | -568.77 | 1.81 | -1.73 | 2.14 | 164.56 | 94 | 6749.31 | 205332.03 | 3132657.29 | 30.1811 | -96.7481 | 254.78
7385 | 13.82 | 256.1 | 7205.75 | -381.31 | -1402.95 | -577.74 | 0.89 | 0.86 | 0.95 | 14.73 | 94 | 6840.75 | 205326.63 | 3132636.17 | 30.181 | -96.7482 | 254.79
7479 | 14.6 | 258.01 | 7296.87 | -386.47 | -1425.44 | -587.75 | 0.97 | 0.83 | 2.03 | 31.94 | 94 | 6931.87 | 205321.47 | 3132613.68 | 30.181 | -96.7483 | 254.83
7573 | 12.73 | 261.27 | 7388.21 | -390.5 | -1447.27 | -598.22 | 2.15 | -1.99 | 3.47 | 159.19 | 94 | 7023.21 | 205317.44 | 3132591.85 | 30.181 | -96.7483 | 254.9
7667 | 12.9 | 258.18 | 7479.87 | -394.22 | -1467.78 | -608.11 | 0.75 | 0.18 | -3.29 | -77.58 | 94 | 7114.87 | 205313.72 | 3132571.34 | 30.181 | -96.7484 | 254.97
7761 | 11.64 | 259.86 | 7571.72 | -398.04 | -1487.38 | -617.36 | 1.39 | -1.34 | 1.79 | 165 | 94 | 7206.72 | 205309.9 | 3132551.74 | 30.181 | -96.7485 | 255.02
7855 | 10.02 | 261.84 | 7664.04 | -400.87 | -1504.81 | -626.03 | 1.77 | -1.72 | 2.11 | 168.04 | 94 | 7299.04 | 205307.07 | 3132534.31 | 30.181 | -96.7485 | 255.08
7949 | 10.88 | 253.64 | 7756.49 | -404.53 | -1521.42 | -633.54 | 1.83 | 0.91 | -8.72 | -64.04 | 94 | 7391.49 | 205303.41 | 3132517.7 | 30.181 | -96.7486 | 255.11
8043 | 10.65 | 252.25 | 7848.83 | -409.68 | -1538.21 | -639.99 | 0.37 | -0.24 | -1.48 | -132.22 | 94 | 7483.83 | 205298.26 | 3132500.91 | 30.181 | -96.7486 | 255.09
8136 | 9.42 | 253.02 | 7940.41 | -414.52 | -1553.67 | -645.86 | 1.33 | -1.32 | 0.83 | 174.15 | 93 | 7575.41 | 205293.42 | 3132485.45 | 30.181 | -96.7487 | 255.06
8230 | 8.2 | 252.88 | 8033.3 | -418.74 | -1567.44 | -651.16 | 1.3 | -1.3 | -0.15 | -179.06 | 94 | 7668.3 | 205289.2 | 3132471.68 | 30.1809 | -96.7487 | 255.04
8324 | 6.86 | 253.13 | 8126.49 | -422.34 | -1579.21 | -655.69 | 1.43 | -1.43 | 0.27 | 178.72 | 94 | 7761.49 | 205285.6 | 3132459.91 | 30.1809 | -96.7488 | 255.03
8418 | 6.31 | 251.12 | 8219.87 | -425.64 | -1589.47 | -659.52 | 0.63 | -0.59 | -2.14 | -158.26 | 94 | 7854.87 | 205282.3 | 3132449.65 | 30.1809 | -96.7488 | 255.01
8511 | 8.43 | 251.8 | 8312.09 | -429.43 | -1600.79 | -663.62 | 2.28 | 2.28 | 0.73 | 2.69 | 93 | 7947.09 | 205278.51 | 3132438.33 | 30.1809 | -96.7488 | 254.98
8605 | 9.57 | 254.2 | 8404.93 | -433.71 | -1614.85 | -669.06 | 1.28 | 1.21 | 2.55 | 19.42 | 94 | 8039.93 | 205274.23 | 3132424.27 | 30.1809 | -96.7489 | 254.97
8699 | 8.8 | 256.01 | 8497.73 | -437.57 | -1629.35 | -675.09 | 0.87 | -0.82 | 1.93 | 160.32 | 94 | 8132.73 | 205270.37 | 3132409.77 | 30.1809 | -96.7489 | 254.97
8793 | 8.09 | 258.44 | 8590.71 | -440.64 | -1642.81 | -681.09 | 0.85 | -0.76 | 2.59 | 154.51 | 94 | 8225.71 | 205267.3 | 3132396.31 | 30.1809 | -96.749 | 254.99
8887 | 6.92 | 258.57 | 8683.9 | -443.08 | -1654.84 | -686.69 | 1.24 | -1.24 | 0.14 | 179.23 | 94 | 8318.9 | 205264.86 | 3132384.28 | 30.1809 | -96.749 | 255.01
8981 | 5.76 | 257.38 | 8777.32 | -445.24 | -1664.99 | -691.34 | 1.24 | -1.23 | -1.27 | -174.13 | 94 | 8412.32 | 205262.7 | 3132374.13 | 30.1809 | -96.749 | 255.03
9075 | 4.63 | 255.17 | 8870.94 | -447.24 | -1673.26 | -694.94 | 1.22 | -1.2 | -2.35 | -171.06 | 94 | 8505.94 | 205260.7 | 3132365.86 | 30.1809 | -96.7491 | 255.04
9169 | 2.6 | 241.43 | 8964.75 | -449.23 | -1678.8 | -696.84 | 2.33 | -2.16 | -14.62 | -163.65 | 94 | 8599.75 | 205258.71 | 3132360.32 | 30.1809 | -96.7491 | 255.02
9262 | 1.41 | 221.94 | 9057.69 | -451.09 | -1681.42 | -697.02 | 1.46 | -1.28 | -20.96 | -159.69 | 93 | 8692.69 | 205256.85 | 3132357.7 | 30.1809 | -96.7491 | 254.98
9356 | 0.4 | 339.27 | 9151.68 | -451.64 | -1682.31 | -697.15 | 1.74 | -1.07 | 124.82 | 167.43 | 94 | 8786.68 | 205256.3 | 3132356.81 | 30.1809 | -96.7491 | 254.97
9450 | 0.63 | 356.15 | 9245.68 | -450.82 | -1682.46 | -697.88 | 0.29 | 0.24 | 17.96 | 42.04 | 94 | 8880.68 | 205257.12 | 3132356.66 | 30.1809 | -96.7491 | 255
9544 | 0.41 | 41.44 | 9339.67 | -450.05 | -1682.27 | -698.37 | 0.48 | -0.23 | 48.18 | 139.53 | 94 | 8974.67 | 205257.89 | 3132356.85 | 30.1809 | -96.7491 | 255.02
9638 | 0.32 | 46.31 | 9433.67 | -449.62 | -1681.86 | -698.45 | 0.1 | -0.1 | 5.18 | 163.4 | 94 | 9068.67 | 205258.32 | 3132357.26 | 30.1809 | -96.7491 | 255.03
9732 | 3.43 | 142.55 | 9527.62 | -451.67 | -1679.96 | -695.66 | 3.7 | 3.31 | 102.38 | 101.48 | 94 | 9162.62 | 205256.27 | 3132359.16 | 30.1809 | -96.7491 | 254.95
9826 | 10.04 | 149.79 | 9620.92 | -460.99 | -1674.12 | -684.73 | 7.08 | 7.03 | 7.7 | 10.93 | 94 | 9255.92 | 205246.95 | 3132365 | 30.1808 | -96.7491 | 254.6
9961 | 14.48 | 143.86 | 9752.81 | -484.81 | -1658.24 | -656.21 | 3.41 | 3.29 | -4.39 | -18.75 | 135 | 9387.81 | 205223.13 | 3132380.88 | 30.1808 | -96.749 | 253.7
10124 | 20.75 | 143.45 | 9908.09 | -524.5 | -1628.99 | -606.95 | 3.85 | 3.85 | -0.25 | -1.33 | 163 | 9543.09 | 205183.44 | 3132410.13 | 30.1807 | -96.7489 | 252.15
10219 | 27.56 | 142.72 | 9994.72 | -555.54 | -1605.63 | -568.11 | 7.18 | 7.17 | -0.77 | -2.85 | 95 | 9629.72 | 205152.4 | 3132433.49 | 30.1806 | -96.7489 | 250.91
10314 | 35.39 | 139.67 | 10075.68 | -594.06 | -1574.47 | -518.56 | 8.41 | 8.24 | -3.21 | -12.81 | 95 | 9710.68 | 205113.88 | 3132464.65 | 30.1805 | -96.7488 | 249.33
10408 | 45.6 | 142.05 | 10147.08 | -641.42 | -1536.09 | -457.61 | 10.98 | 10.86 | 2.53 | 9.53 | 94 | 9782.08 | 205066.52 | 3132503.03 | 30.1803 | -96.7486 | 247.34
10502 | 56.34 | 136.52 | 10206.21 | -696.47 | -1488.36 | -384.81 | 12.3 | 11.43 | -5.88 | -23.59 | 94 | 9841.21 | 205011.47 | 3132550.76 | 30.1802 | -96.7485 | 244.92
10597 | 61.37 | 137.15 | 10255.33 | -755.77 | -1432.77 | -303.78 | 5.33 | 5.29 | 0.66 | 6.28 | 95 | 9890.33 | 204952.17 | 3132606.35 | 30.18 | -96.7483 | 242.19
10691 | 69.86 | 143.09 | 10294.14 | -821.46 | -1378.07 | -218.32 | 10.71 | 9.03 | 6.32 | 33.78 | 94 | 9929.14 | 204886.48 | 3132661.05 | 30.1798 | -96.7482 | 239.2
10785 | 78.82 | 139.58 | 10319.49 | -892.01 | -1321.54 | -127.91 | 10.19 | 9.53 | -3.73 | -21.17 | 94 | 9954.49 | 204815.93 | 3132717.58 | 30.1796 | -96.748 | 235.98
10879 | 90.51 | 138.15 | 10328.22 | -962.37 | -1260.07 | -34.58 | 12.53 | 12.44 | -1.52 | -7.02 | 94 | 9963.22 | 204745.57 | 3132779.05 | 30.1794 | -96.7478 | 232.63
10974 | 89.54 | 140.19 | 10328.17 | -1034.25 | -1197.97 | 60.35 | 2.38 | -1.02 | 2.15 | 115.43 | 95 | 9963.17 | 204673.69 | 3132841.15 | 30.1792 | -96.7476 | 229.19
11068 | 89.41 | 140.88 | 10329.03 | -1106.81 | -1138.22 | 154.33 | 0.75 | -0.14 | 0.73 | 100.67 | 94 | 9964.03 | 204601.13 | 3132900.9 | 30.179 | -96.7474 | 225.8
11163 | 82.7 | 139.4 | 10335.57 | -1179.52 | -1077.52 | 249.03 | 7.23 | -7.06 | -1.56 | -167.63 | 95 | 9970.57 | 204528.42 | 3132961.6 | 30.1788 | -96.7473 | 222.41
11257 | 82.99 | 140.07 | 10347.28 | -1250.69 | -1017.24 | 342.26 | 0.77 | 0.31 | 0.71 | 66.47 | 94 | 9982.28 | 204457.25 | 3133021.88 | 30.1786 | -96.7471 | 219.12
11351 | 86.96 | 140.73 | 10355.51 | -1322.83 | -957.56 | 435.86 | 4.28 | 4.22 | 0.7 | 9.43 | 94 | 9990.51 | 204385.11 | 3133081.56 | 30.1784 | -96.7469 | 215.9
11446 | 87.51 | 153.79 | 10360.11 | -1402.47 | -906.36 | 530.05 | 13.74 | 0.58 | 13.75 | 87.91 | 95 | 9995.11 | 204305.47 | 3133132.76 | 30.1782 | -96.7467 | 212.87
11540 | 86.91 | 139.19 | 10364.71 | -1480.54 | -854.67 | 623.31 | 15.53 | -0.64 | -15.53 | -92.7 | 94 | 9999.71 | 204227.4 | 3133184.45 | 30.178 | -96.7466 | 210
11634 | 88.78 | 140.55 | 10368.25 | -1552.36 | -794.13 | 717.2 | 2.46 | 1.99 | 1.45 | 36.04 | 94 | 10003.25 | 204155.58 | 3133244.99 | 30.1778 | -96.7464 | 207.09
11730 | 89.9 | 140.19 | 10369.35 | -1626.29 | -732.9 | 813.18 | 1.23 | 1.17 | -0.38 | -17.82 | 96 | 10004.35 | 204081.65 | 3133306.22 | 30.1776 | -96.7462 | 204.26
11824 | 88.97 | 140.59 | 10370.28 | -1698.7 | -672.98 | 907.16 | 1.08 | -0.99 | 0.43 | 156.73 | 94 | 10005.28 | 204009.24 | 3133366.14 | 30.1774 | -96.746 | 201.61
11916 | 90.59 | 141.16 | 10370.63 | -1770.07 | -614.93 | 999.15 | 1.87 | 1.76 | 0.62 | 19.39 | 92 | 10005.63 | 203937.87 | 3133424.19 | 30.1772 | -96.7458 | 199.16
12010 | 89.82 | 141.87 | 10370.29 | -1843.65 | -556.43 | 1093.15 | 1.11 | -0.82 | 0.76 | 137.32 | 94 | 10005.29 | 203864.29 | 3133482.69 | 30.1769 | -96.7457 | 196.79
12105 | 86.86 | 140.87 | 10373.05 | -1917.82 | -497.16 | 1188.1 | 3.29 | -3.12 | -1.05 | -161.35 | 95 | 10008.05 | 203790.12 | 3133541.96 | 30.1767 | -96.7455 | 194.53
12199 | 87.56 | 141.6 | 10377.62 | -1991.03 | -438.37 | 1281.99 | 1.08 | 0.74 | 0.78 | 46.19 | 94 | 10012.62 | 203716.91 | 3133600.75 | 30.1765 | -96.7453 | 192.42
12294 | 85.94 | 140.92 | 10383.01 | -2065.01 | -379.02 | 1376.83 | 1.85 | -1.71 | -0.72 | -157.28 | 95 | 10018.01 | 203642.93 | 3133660.1 | 30.1763 | -96.7451 | 190.4
12388 | 84.67 | 140.85 | 10390.7 | -2137.69 | -319.92 | 1470.51 | 1.35 | -1.35 | -0.07 | -176.86 | 94 | 10025.7 | 203570.25 | 3133719.2 | 30.1761 | -96.745 | 188.51
12482 | 83.24 | 140.81 | 10400.6 | -2210.16 | -260.88 | 1563.98 | 1.52 | -1.52 | -0.04 | -178.41 | 94 | 10035.6 | 203497.78 | 3133778.24 | 30.1759 | -96.7448 | 186.73
12576 | 83.82 | 141.57 | 10411.19 | -2282.94 | -202.34 | 1657.38 | 1.01 | 0.62 | 0.81 | 52.52 | 94 | 10046.19 | 203425 | 3133836.78 | 30.1757 | -96.7446 | 185.06
12670 | 87.28 | 140.87 | 10418.49 | -2355.99 | -143.65 | 1751.08 | 3.75 | 3.68 | -0.74 | -11.43 | 94 | 10053.49 | 203351.95 | 3133895.47 | 30.1755 | -96.7444 | 183.49
12764 | 89.08 | 140.62 | 10421.47 | -2428.73 | -84.2 | 1845.02 | 1.93 | 1.91 | -0.27 | -7.91 | 94 | 10056.47 | 203279.21 | 3133954.92 | 30.1753 | -96.7442 | 181.99
12858 | 89.2 | 141.45 | 10422.88 | -2501.81 | -25.1 | 1939.01 | 0.89 | 0.13 | 0.88 | 81.78 | 94 | 10057.88 | 203206.13 | 3134014.02 | 30.1751 | -96.7441 | 180.57
12953 | 88.41 | 140.6 | 10424.86 | -2575.65 | 34.64 | 2033.99 | 1.22 | -0.83 | -0.89 | -132.92 | 95 | 10059.86 | 203132.29 | 3134073.76 | 30.1749 | -96.7439 | 179.23
13047 | 86.54 | 139.92 | 10429 | -2647.86 | 94.68 | 2127.87 | 2.12 | -1.99 | -0.72 | -160.05 | 94 | 10064 | 203060.08 | 3134133.8 | 30.1747 | -96.7437 | 177.95
13141 | 88.76 | 141.79 | 10432.86 | -2720.69 | 153.96 | 2221.78 | 3.09 | 2.36 | 1.99 | 40.13 | 94 | 10067.86 | 202987.25 | 3134193.08 | 30.1745 | -96.7435 | 176.76
13236 | 86.61 | 140.79 | 10436.7 | -2794.76 | 213.32 | 2316.69 | 2.5 | -2.26 | -1.05 | -155.09 | 95 | 10071.7 | 202913.18 | 3134252.44 | 30.1743 | -96.7433 | 175.64
13330 | 87.54 | 145.05 | 10441.49 | -2869.64 | 269.9 | 2410.51 | 4.63 | 0.99 | 4.53 | 77.78 | 94 | 10076.49 | 202838.3 | 3134309.02 | 30.1741 | -96.7432 | 174.63
13425 | 86.73 | 152.07 | 10446.25 | -2950.53 | 319.36 | 2504.59 | 7.43 | -0.85 | 7.39 | 96.76 | 95 | 10081.25 | 202757.41 | 3134358.48 | 30.1738 | -96.743 | 173.82
13519 | 87.83 | 148.95 | 10450.71 | -3032.25 | 365.58 | 2597.28 | 3.52 | 1.17 | -3.32 | -70.64 | 94 | 10085.71 | 202675.69 | 3134404.7 | 30.1736 | -96.7429 | 173.13
13613 | 87.95 | 152.83 | 10454.17 | -3114.31 | 411.27 | 2689.91 | 4.13 | 0.13 | 4.13 | 88.3 | 94 | 10089.17 | 202593.63 | 3134450.39 | 30.1734 | -96.7427 | 172.48
13706 | 87.52 | 154.69 | 10457.85 | -3197.65 | 452.35 | 2780.67 | 2.05 | -0.46 | 2 | 103.06 | 93 | 10092.85 | 202510.29 | 3134491.47 | 30.1731 | -96.7426 | 171.95
13801 | 87.86 | 157.38 | 10461.68 | -3284.39 | 490.91 | 2872.5 | 2.85 | 0.36 | 2.83 | 82.85 | 95 | 10096.68 | 202423.55 | 3134530.03 | 30.1729 | -96.7425 | 171.5
13896 | 87.14 | 153.54 | 10465.82 | -3370.71 | 530.32 | 2964.54 | 4.11 | -0.76 | -4.04 | -100.71 | 95 | 10100.82 | 202337.23 | 3134569.44 | 30.1727 | -96.7424 | 171.06
13989 | 87.38 | 145.88 | 10470.28 | -3450.86 | 577.14 | 3056.38 | 8.23 | 0.26 | -8.24 | -88.39 | 93 | 10105.28 | 202257.08 | 3134616.26 | 30.1724 | -96.7422 | 170.51
14083 | 87.35 | 148.95 | 10474.6 | -3529.97 | 627.7 | 3149.75 | 3.26 | -0.03 | 3.27 | 90.63 | 94 | 10109.6 | 202177.97 | 3134666.82 | 30.1722 | -96.7421 | 169.92
14178 | 87.3 | 138.23 | 10479.05 | -3606.23 | 683.94 | 3244.44 | 11.27 | -0.05 | -11.28 | -90.52 | 95 | 10114.05 | 202101.71 | 3134723.06 | 30.172 | -96.7419 | 169.26
14272 | 86.8 | 136.62 | 10483.88 | -3675.36 | 747.45 | 3338.09 | 1.79 | -0.53 | -1.71 | -107.31 | 94 | 10118.88 | 202032.58 | 3134786.57 | 30.1718 | -96.7417 | 168.5
14367 | 89.67 | 129.29 | 10486.81 | -3740.01 | 816.9 | 3431.94 | 8.28 | 3.02 | -7.72 | -68.75 | 95 | 10121.81 | 201967.93 | 3134856.02 | 30.1716 | -96.7415 | 167.68
14461 | 89.1 | 131.54 | 10487.82 | -3800.94 | 888.46 | 3524.22 | 2.47 | -0.61 | 2.39 | 104.23 | 94 | 10122.82 | 201907 | 3134927.58 | 30.1714 | -96.7413 | 166.84
14556 | 90.58 | 131.96 | 10488.09 | -3864.2 | 959.33 | 3617.88 | 1.62 | 1.56 | 0.44 | 15.84 | 95 | 10123.09 | 201843.74 | 3134998.45 | 30.1713 | -96.7411 | 166.06
14650 | 88.24 | 133.34 | 10489.06 | -3927.87 | 1028.46 | 3710.77 | 2.89 | -2.49 | 1.47 | 149.48 | 94 | 10124.06 | 201780.07 | 3135067.58 | 30.1711 | -96.7409 | 165.33
14745 | 88.07 | 136.76 | 10492.11 | -3995.06 | 1095.53 | 3805.13 | 3.6 | -0.18 | 3.6 | 92.9 | 95 | 10127.11 | 201712.88 | 3135134.65 | 30.1709 | -96.7407 | 164.67
14841 | 86.41 | 135.7 | 10496.74 | -4064.3 | 1161.86 | 3900.63 | 2.05 | -1.73 | -1.1 | -147.49 | 96 | 10131.74 | 201643.64 | 3135200.98 | 30.1707 | -96.7405 | 164.05
14936 | 87.8 | 136.87 | 10501.54 | -4132.88 | 1227.42 | 3995.13 | 1.91 | 1.46 | 1.23 | 40.08 | 95 | 10136.54 | 201575.06 | 3135266.54 | 30.1705 | -96.7403 | 163.46
15030 | 86.32 | 137.99 | 10506.36 | -4202.01 | 1290.93 | 4088.78 | 1.97 | -1.57 | 1.19 | 142.95 | 94 | 10141.36 | 201505.93 | 3135330.05 | 30.1703 | -96.7401 | 162.92
15125 | 84.92 | 138.73 | 10513.61 | -4272.8 | 1353.86 | 4183.36 | 1.67 | -1.47 | 0.78 | 152.24 | 95 | 10148.61 | 201435.14 | 3135392.98 | 30.1701 | -96.7399 | 162.42
15220 | 84.14 | 138.46 | 10522.67 | -4343.73 | 1416.41 | 4277.82 | 0.87 | -0.82 | -0.28 | -161 | 95 | 10157.67 | 201364.21 | 3135455.53 | 30.1699 | -96.7397 | 161.94
15314 | 87.49 | 138.82 | 10529.53 | -4414.08 | 1478.35 | 4371.45 | 3.58 | 3.56 | 0.38 | 6.13 | 94 | 10164.53 | 201293.86 | 3135517.47 | 30.1697 | -96.7395 | 161.48
15408 | 88.69 | 138.92 | 10532.66 | -4484.84 | 1540.14 | 4465.3 | 1.28 | 1.28 | 0.11 | 4.76 | 94 | 10167.66 | 201223.1 | 3135579.26 | 30.1695 | -96.7393 | 161.05
15502 | 87.69 | 139.46 | 10535.63 | -4555.95 | 1601.54 | 4559.19 | 1.21 | -1.06 | 0.57 | 151.65 | 94 | 10170.63 | 201151.99 | 3135640.66 | 30.1693 | -96.7391 | 160.63
15596 | 86.67 | 139.33 | 10540.25 | -4627.23 | 1662.65 | 4653.02 | 1.09 | -1.09 | -0.14 | -172.75 | 94 | 10175.25 | 201080.71 | 3135701.77 | 30.1691 | -96.7389 | 160.24
15690 | 87.39 | 140.69 | 10545.12 | -4699.15 | 1722.97 | 4746.86 | 1.64 | 0.77 | 1.45 | 62.11 | 94 | 10180.12 | 201008.79 | 3135762.09 | 30.1689 | -96.7388 | 159.86
15784 | 84.75 | 137.85 | 10551.57 | -4770.21 | 1784.15 | 4840.56 | 4.12 | -2.81 | -3.02 | -133.07 | 94 | 10186.57 | 200937.73 | 3135823.27 | 30.1687 | -96.7386 | 159.49
15878 | 86.24 | 139.1 | 10558.95 | -4840.36 | 1846.27 | 4934.14 | 2.07 | 1.59 | 1.33 | 39.96 | 94 | 10193.95 | 200867.58 | 3135885.39 | 30.1685 | -96.7384 | 159.12
15972 | 86.65 | 141.05 | 10564.78 | -4912.31 | 1906.48 | 5027.93 | 2.12 | 0.44 | 2.07 | 78.17 | 94 | 10199.78 | 200795.63 | 3135945.6 | 30.1683 | -96.7382 | 158.79
16066 | 87.17 | 140.27 | 10569.85 | -4984.9 | 1965.98 | 5121.79 | 1 | 0.55 | -0.83 | -56.29 | 94 | 10204.85 | 200723.04 | 3136005.1 | 30.1681 | -96.738 | 158.48
16161 | 87.47 | 139.84 | 10574.29 | -5057.65 | 2026.91 | 5216.66 | 0.55 | 0.32 | -0.45 | -55.08 | 95 | 10209.29 | 200650.29 | 3136066.03 | 30.1679 | -96.7378 | 158.16
16256 | 87.93 | 139.39 | 10578.1 | -5129.96 | 2088.41 | 5311.53 | 0.68 | 0.48 | -0.47 | -44.36 | 95 | 10213.1 | 200577.98 | 3136127.53 | 30.1677 | -96.7376 | 157.85
16350 | 88.12 | 139.01 | 10581.34 | -5201.07 | 2149.8 | 5405.41 | 0.45 | 0.2 | -0.4 | -63.43 | 94 | 10216.34 | 200506.87 | 3136188.92 | 30.1675 | -96.7375 | 157.54
16444 | 88.64 | 139.05 | 10584 | -5272.02 | 2211.4 | 5499.29 | 0.55 | 0.55 | 0.04 | 4.4 | 94 | 10219 | 200435.92 | 3136250.52 | 30.1673 | -96.7373 | 157.24
16539 | 87.73 | 140.1 | 10587.01 | -5344.3 | 2272.97 | 5594.2 | 1.46 | -0.96 | 1.11 | 130.94 | 95 | 10222.01 | 200363.64 | 3136312.09 | 30.1671 | -96.7371 | 156.96
16633 | 87.58 | 143 | 10590.85 | -5417.84 | 2331.37 | 5688.11 | 3.09 | -0.16 | 3.09 | 93.02 | 94 | 10225.85 | 200290.1 | 3136370.49 | 30.1669 | -96.7369 | 156.72
16728 | 84.3 | 138.4 | 10597.58 | -5491.15 | 2391.36 | 5782.82 | 5.94 | -3.45 | -4.84 | -125.7 | 95 | 10232.58 | 200216.79 | 3136430.48 | 30.1667 | -96.7367 | 156.47
16822 | 83.4 | 139.35 | 10607.65 | -5561.55 | 2452.83 | 5876.19 | 1.39 | -0.96 | 1.01 | 133.67 | 94 | 10242.65 | 200146.39 | 3136491.95 | 30.1665 | -96.7365 | 156.2
16917 | 85.32 | 140.99 | 10616.99 | -5634.15 | 2513.38 | 5970.7 | 2.65 | 2.02 | 1.73 | 40.45 | 95 | 10251.99 | 200073.79 | 3136552.5 | 30.1663 | -96.7363 | 155.96
17012 | 88.99 | 142.23 | 10621.7 | -5708.5 | 2572.29 | 6065.57 | 4.08 | 3.86 | 1.31 | 18.68 | 95 | 10256.7 | 199999.44 | 3136611.41 | 30.166 | -96.7362 | 155.74
17106 | 88.39 | 142.52 | 10623.85 | -5782.93 | 2629.66 | 6159.53 | 0.71 | -0.64 | 0.31 | 154.21 | 94 | 10258.85 | 199925.01 | 3136668.78 | 30.1658 | -96.736 | 155.55
17201 | 89.64 | 142.43 | 10625.49 | -5858.26 | 2687.51 | 6254.49 | 1.32 | 1.32 | -0.09 | -4.12 | 95 | 10260.49 | 199849.68 | 3136726.63 | 30.1656 | -96.7358 | 155.36
17296 | 90.34 | 142.38 | 10625.5 | -5933.54 | 2745.47 | 6349.48 | 0.74 | 0.74 | -0.05 | -4.09 | 95 | 10260.5 | 199774.4 | 3136784.59 | 30.1654 | -96.7356 | 155.17
17392 | 89.57 | 141.54 | 10625.58 | -6009.14 | 2804.63 | 6445.47 | 1.19 | -0.8 | -0.88 | -132.51 | 96 | 10260.58 | 199698.8 | 3136843.75 | 30.1652 | -96.7355 | 154.98
17486 | 86.01 | 140.98 | 10629.2 | -6082.4 | 2863.4 | 6539.39 | 3.83 | -3.79 | -0.6 | -171.08 | 94 | 10264.2 | 199625.54 | 3136902.52 | 30.165 | -96.7353 | 154.79
17578 | 86.78 | 141.75 | 10634.99 | -6154.12 | 2920.72 | 6631.2 | 1.18 | 0.84 | 0.84 | 44.97 | 92 | 10269.99 | 199553.82 | 3136959.84 | 30.1648 | -96.7351 | 154.61
17674 | 85.74 | 143.3 | 10641.25 | -6230.14 | 2979 | 6726.98 | 1.94 | -1.08 | 1.61 | 123.97 | 96 | 10276.25 | 199477.8 | 3137018.12 | 30.1646 | -96.7349 | 154.44
17768 | 86.44 | 143.58 | 10647.66 | -6305.47 | 3034.87 | 6820.7 | 0.8 | 0.74 | 0.3 | 21.77 | 94 | 10282.66 | 199402.47 | 3137073.99 | 30.1644 | -96.7348 | 154.3
17863 | 86.73 | 143.44 | 10653.32 | -6381.71 | 3091.26 | 6915.46 | 0.34 | 0.31 | -0.15 | -25.73 | 95 | 10288.32 | 199326.23 | 3137130.38 | 30.1641 | -96.7346 | 154.15
17957 | 86.96 | 143.44 | 10658.49 | -6457.1 | 3147.17 | 7009.26 | 0.24 | 0.24 | 0 | 0 | 94 | 10293.49 | 199250.84 | 3137186.29 | 30.1639 | -96.7344 | 154.02
18051 | 87.28 | 143.44 | 10663.22 | -6532.5 | 3203.09 | 7103.08 | 0.34 | 0.34 | 0 | 0 | 94 | 10298.22 | 199175.44 | 3137242.21 | 30.1637 | -96.7343 | 153.88
18146 | 87.27 | 141.51 | 10667.73 | -6607.76 | 3260.89 | 7197.95 | 2.03 | -0.01 | -2.03 | -90.34 | 95 | 10302.73 | 199100.18 | 3137300.01 | 30.1635 | -96.7341 | 153.73
18240 | 85.77 | 140.43 | 10673.44 | -6680.64 | 3319.97 | 7291.77 | 1.97 | -1.6 | -1.15 | -144.33 | 94 | 10308.44 | 199027.3 | 3137359.09 | 30.1633 | -96.7339 | 153.57
18335 | 85.92 | 140.48 | 10680.32 | -6753.71 | 3380.29 | 7386.51 | 0.17 | 0.16 | 0.05 | 18.39 | 95 | 10315.32 | 198954.23 | 3137419.41 | 30.1631 | -96.7337 | 153.41
18430 | 86.14 | 140.39 | 10686.9 | -6826.77 | 3440.66 | 7481.27 | 0.25 | 0.23 | -0.09 | -22.2 | 95 | 10321.9 | 198881.17 | 3137479.78 | 30.1629 | -96.7335 | 153.25
18525 | 87.79 | 141 | 10691.93 | -6900.17 | 3500.75 | 7576.12 | 1.85 | 1.74 | 0.64 | 20.28 | 95 | 10326.93 | 198807.77 | 3137539.87 | 30.1627 | -96.7334 | 153.1
18620 | 89 | 141.41 | 10694.59 | -6974.18 | 3560.25 | 7671.08 | 1.34 | 1.27 | 0.43 | 18.72 | 95 | 10329.59 | 198733.76 | 3137599.37 | 30.1625 | -96.7332 | 152.96
18714 | 88.46 | 141.39 | 10696.67 | -7047.63 | 3618.88 | 7765.06 | 0.57 | -0.57 | -0.02 | -177.88 | 94 | 10331.67 | 198660.31 | 3137658 | 30.1623 | -96.733 | 152.82
18808 | 88.24 | 141.38 | 10699.38 | -7121.04 | 3677.52 | 7859.02 | 0.23 | -0.23 | -0.01 | -177.4 | 94 | 10334.38 | 198586.9 | 3137716.64 | 30.1621 | -96.7328 | 152.69
18902 | 88.27 | 141.16 | 10702.24 | -7194.34 | 3736.3 | 7952.98 | 0.24 | 0.03 | -0.23 | -82.23 | 94 | 10337.24 | 198513.6 | 3137775.42 | 30.1619 | -96.7326 | 152.56
19034 | 88.6 | 140.28 | 10705.85 | -7296.48 | 3819.84 | 8084.92 | 0.71 | 0.25 | -0.67 | -69.45 | 132 | 10340.85 | 198411.46 | 3137858.96 | 30.1616 | -96.7324 | 152.37
19102 | 88.6 | 140.28 | 10707.51 | -7348.76 | 3863.28 | 8152.88 | 0 | 0 | 0 | 0 | 68 | 10342.51 | 198359.18 | 3137902.4 | 30.1614 | -96.7323 | 152.27

## 6_19_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 17350
|  |  |  | 24hr Summary: |  | Standby
|  |  |  | 24hr Lookahead: |  | P/U BHA & Drill Surface
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 105 |  | 105 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 0.00 / 0.17 |  | 0.00 / 0.17 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 38426 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 13.500 / 1.178
BRT Hrs: |  | 2.17 |  | 2.17 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-RR-X-I-RR-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.18 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  |  | 8 | 2 |  |  |  |  | 38.19 |  | 39.69
Stabalizer |  |  |  | 13 | 2.875 |  |  |  |  | 7.86 |  | 47.55
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.95 |  | 55.5
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.74 |  | 59.24
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.74 |  | 87.98
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.8 |  | 116.78
Crossover |  |  |  | 6.5 | 3.062 |  |  |  |  | 2.08 |  | 118.86
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 389.9
389.9
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.51 |  | 1.5 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem Per Hand |  |  |  |  | 06/19/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD / Gamma Services |  |  |  |  | 06/19/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 06/19/2021 | PPM800001 | 15 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/19/2021 | 00:00 | 20:55 | 20.92 | 105 | 105 | 0 | SUR |  | 24B | Standby Rig-up
06/19/2021 | 20:55 | 21:50 | 0.92 | 105 | 105 | 0 | SUR | 1: BHA 1 | 6O | P/U BHA # !
06/19/2021 | 21:50 | 22:00 | 0.17 | 105 | 105 | 0 | SUR | 1: BHA 1 | 5A | Test Lines (NoTest)
06/19/2021 | 22:00 | 24:00 | 2 | 105 | 105 | 0 | SUR | 1: BHA 1 | 8D | Work On Mud Pumps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_20_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 24200
|  |  |  | 24hr Summary: |  | Drill Surface
|  |  |  | 24hr Lookahead: |  | Drill & TD Surface
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 2725 |  | 2725 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 2620 |  | 2620 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 205 |  | 205 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2415 |  | 2415 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 6.22 / 3.53 |  | 6.22 / 3.70 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: |  | 1.43 |  | 1.43 |  | SN: |  | 38426 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 4.78 |  | 4.78 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 504.88 / 143.02 |  | 504.88 / 143.02 |  | OD (in) / TFA: |  | 13.500 / 1.178
BRT Hrs: |  | 24 |  | 26.17 |  | Grade In: |  | New
% Slide: |  | 7.82 |  | 7.82 |  | Grade Out: |  | 1-1-RR-X-I-RR-TD
% Rotary: |  | 92.18 |  | 92.18 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.18 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  |  | 8 | 2 |  |  |  |  | 38.19 |  | 39.69
Stabalizer |  |  |  | 13 | 2.875 |  |  |  |  | 7.86 |  | 47.55
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.95 |  | 55.5
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.74 |  | 59.24
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.74 |  | 87.98
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.8 |  | 116.78
Crossover |  |  |  | 6.5 | 3.062 |  |  |  |  | 2.08 |  | 118.86
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 389.9
389.9
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.51 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
135 | 0.5 | 210 | 135 | -0.51 | -0.29 | 0.37 |  | 210 | 0.21 | 0.37 |  | 0 | 135
227 | 0.5 | 233.2 | 226.99 | -1.1 | -0.82 | 0.22 |  | 101.6 | 0.35 | 0 |  | 0 | 92
316 | 0.6 | 222.9 | 315.99 | -1.67 | -1.44 | 0.16 |  | -49.9 | 0.4 | 0.11 |  | 0 | 89
410 | 0.6 | 227.5 | 409.99 | -2.37 | -2.14 | 0.05 |  | 92.3 | 0.51 | 0 |  | 0 | 94
504 | 0.6 | 232.2 | 503.98 | -3 | -2.89 | 0.05 |  | 92.35 | 0.54 | 0 |  | 0 | 94
598 | 0.74 | 242 | 597.97 | -3.59 | -3.82 | 0.19 |  | 44.27 | 0.42 | 0.15 |  | 0 | 94
692 | 0.79 | 245.28 | 691.97 | -4.14 | -4.94 | 0.07 |  | 42.86 | 0.15 | 0.05 |  | 0 | 94
785 | 1.05 | 255.66 | 784.95 | -4.62 | -6.35 | 0.33 |  | 37.92 | -0.35 | 0.28 |  | 0 | 93
879 | 1.23 | 271.06 | 878.94 | -4.82 | -8.2 | 0.38 |  | 67.42 | -1.35 | 0.19 |  | 0 | 94
973 | 1.53 | 262.63 | 972.91 | -4.96 | -10.45 | 0.38 |  | -38.35 | -2.65 | 0.32 |  | 0 | 94
1067 | 2.08 | 254.14 | 1066.86 | -5.59 | -13.33 | 0.65 |  | -30.21 | -3.96 | 0.59 |  | -9.03 | 94
1161 | 3.03 | 251.07 | 1160.77 | -6.86 | -17.32 | 1.02 |  | -9.73 | -5.46 | 1.01 |  | -3.27 | 94
1255 | 3.46 | 248.01 | 1254.62 | -8.73 | -22.31 | 0.49 |  | -23.47 | -7.1 | 0.46 |  | -3.26 | 94
1349 | 4.18 | 251.96 | 1348.41 | -10.85 | -28.19 | 0.82 |  | 22.06 | -9.12 | 0.77 |  | 4.2 | 94
1443 | 4.62 | 246.97 | 1442.13 | -13.39 | -34.93 | 0.62 |  | -43.53 | -11.34 | 0.47 |  | -5.31 | 94
1536 | 4.99 | 250.6 | 1534.8 | -16.2 | -42.2 | 0.51 |  | 41.23 | -13.68 | 0.4 |  | 3.9 | 93
1630 | 6.09 | 249.78 | 1628.36 | -19.28 | -50.73 | 1.17 |  | -4.52 | -16.6 | 1.17 |  | -0.87 | 94
1724 | 7.01 | 251.05 | 1721.75 | -22.87 | -60.84 | 0.99 |  | 9.58 | -20.1 | 0.98 |  | 1.35 | 94
1818 | 7.77 | 252.11 | 1814.97 | -26.68 | -72.31 | 0.82 |  | 10.7 | -24.28 | 0.81 |  | 1.13 | 94
1912 | 8.52 | 252.27 | 1908.02 | -30.75 | -84.99 | 0.8 |  | 1.81 | -29.02 | 0.8 |  | 0.17 | 94
2006 | 9.31 | 253.26 | 2000.88 | -35.06 | -98.9 | 0.86 |  | 11.48 | -34.33 | 0.84 |  | 1.05 | 94
2099 | 10.05 | 252.88 | 2092.56 | -39.62 | -113.86 | 0.8 |  | -5.12 | -40.11 | 0.8 |  | -0.41 | 93
2194 | 10.63 | 252.81 | 2186.01 | -44.65 | -130.15 | 0.61 |  | -1.28 | -46.35 | 0.61 |  | -0.07 | 95
2288 | 11.3 | 252.94 | 2278.3 | -49.91 | -147.24 | 0.71 |  | 2.18 | -52.9 | 0.71 |  | 0.14 | 94
2381 | 11.91 | 251.52 | 2369.4 | -55.63 | -165.05 | 0.72 |  | -25.79 | -59.55 | 0.66 |  | -1.53 | 93
2475 | 12.9 | 251.53 | 2461.2 | -62.03 | -184.21 | 1.05 |  | 0.13 | -66.51 | 1.05 |  | 0.01 | 94
2569 | 13.86 | 250.85 | 2552.65 | -69.05 | -204.79 | 1.03 |  | -9.64 | -73.88 | 1.02 |  | -0.72 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 438.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 438.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/20/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 06/20/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/20/2021 | 00:00 | 01:30 | 1.5 | 105 | 105 | 0 | SUR | 1: BHA 1 | 8D | Work On Mud Pumps ans Swivel Packing on Top Drive.
06/20/2021 | 01:30 | 02:00 | 0.5 | 105 | 105 | 0 | SUR | 1: BHA 1 | 5A | Test Lines (Test Good)
06/20/2021 | 02:00 | 02:15 | 0.25 | 105 | 178 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/0.00 t/178.00, w/WOB 3.00,Flow 400.00, RPM 40.00, Press 1980.00, Tq 6.00, ROP 712.00, Diff 200.00, Temp 100.00
06/20/2021 | 02:15 | 02:50 | 0.58 | 178 | 178 | 0 | SUR | 1: BHA 1 | 6L | P/U NMDC
06/20/2021 | 02:50 | 03:05 | 0.25 | 178 | 208 | 30 | SUR | 1: BHA 1 | 2K | Rotary Drill f/178.00 t/208.00, w/WOB 3.00,Flow 400.00, RPM 40.00, Press 1980.00, Tq 6.00, ROP 120.00, Diff 200.00
06/20/2021 | 03:05 | 03:15 | 0.17 | 208 | 208 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 03:15 | 03:19 | 0.07 | 208 | 211 | 3 | SUR | 1: BHA 1 | 2K | Rotary Drill f/208.00 t/211.00, w/WOB 3.00,Flow 400.00, RPM 40.00, Press 1980.00, Tq 6.00, ROP 45.00, Diff 200.00
06/20/2021 | 03:19 | 03:30 | 0.18 | 211 | 211 | 0 | SUR | 1: BHA 1 | 8D | Pump Of Line
06/20/2021 | 03:30 | 03:50 | 0.33 | 211 | 300 | 89 | SUR | 1: BHA 1 | 2K | Rotary Drill f/211.00 t/300.00, w/WOB 8.00,Flow 600.00, RPM 60.00, Press 1600.00, Tq 6.00, ROP 267.00, Diff 500.00, Temp 100.00
06/20/2021 | 03:50 | 03:58 | 0.13 | 300 | 300 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 03:58 | 04:05 | 0.12 | 300 | 380 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/300.00 t/380.00, w/WOB 3.00,Flow 400.00, RPM 40.00, Press 1980.00, Tq 6.00, ROP 685.71, Diff 200.00
06/20/2021 | 04:05 | 04:10 | 0.08 | 380 | 380 | 0 | SUR | 1: BHA 1 | 5A | M/U Stand On Mouse Hole
06/20/2021 | 04:10 | 04:14 | 0.07 | 380 | 389 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/380.00 t/389.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 2070.00, Tq 8.00, ROP 135.00, Diff 470.00, Temp 102.20
06/20/2021 | 04:14 | 04:20 | 0.1 | 389 | 389 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 04:20 | 04:40 | 0.33 | 389 | 483 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/389.00 t/483.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 2070.00, Tq 8.00, ROP 282.00, Diff 470.00, Temp 102.20
06/20/2021 | 04:40 | 04:48 | 0.13 | 483 | 483 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 04:48 | 05:02 | 0.23 | 483 | 577 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/483.00 t/577.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 2070.00, Tq 8.00, ROP 402.86, Diff 470.00, Temp 102.20
06/20/2021 | 05:02 | 05:08 | 0.1 | 577 | 577 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 05:08 | 05:18 | 0.17 | 577 | 640 | 63 | SUR | 1: BHA 1 | 2K | Rotary Drill f/577.00 t/640.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 2070.00, Tq 8.00, ROP 378.00, Diff 470.00, Temp 102.20
06/20/2021 | 05:18 | 05:25 | 0.12 | 640 | 640 | 0 | SUR | 1: BHA 1 | 5A | M/U Stand In Mouse Hole
06/20/2021 | 05:25 | 05:30 | 0.08 | 640 | 671 | 31 | SUR | 1: BHA 1 | 2K | Rotary Drill f/640.00 t/671.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 2070.00, Tq 8.00, ROP 372.00, Diff 470.00, Temp 102.20
06/20/2021 | 05:30 | 05:35 | 0.08 | 671 | 671 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 05:35 | 05:38 | 0.05 | 671 | 676 | 5 | SUR | 1: BHA 1 | 2K | Rotary Drill f/671.00 t/676.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 2070.00, Tq 8.00, ROP 100.00, Diff 470.00, Temp 102.20
06/20/2021 | 05:38 | 06:37 | 0.98 | 676 | 676 | 0 | SUR | 1: BHA 1 | 20C | Troubleshoot MWD tool
06/20/2021 | 06:37 | 07:18 | 0.68 | 676 | 676 | 0 | SUR | 1: BHA 1 | 6B | POOH to inspect MWD tool
06/20/2021 | 07:18 | 08:30 | 1.2 | 676 | 676 | 0 | SUR | 1: BHA 1 | 24A | Replace sala block in derrick
06/20/2021 | 08:30 | 09:00 | 0.5 | 676 | 676 | 0 | SUR | 1: BHA 1 | 6L | C/O Muleshoe sleeve, scribe motor, set MWD tool
06/20/2021 | 09:00 | 09:10 | 0.17 | 676 | 676 | 0 | SUR | 1: BHA 1 | 5A | Surface test MWD (OK)
06/20/2021 | 09:10 | 09:33 | 0.38 | 676 | 676 | 0 | SUR | 1: BHA 1 | 6A | TIH
06/20/2021 | 09:33 | 09:37 | 0.07 | 676 | 765 | 89 | SUR | 1: BHA 1 | 2K | Rotary Drill f/676.00 t/765.00, w/WOB 8.00,Flow 900, RPM 100, Press 2070.00, Tq 4500, ROP 1335.00, Diff 470.00, Temp 102.20
06/20/2021 | 09:37 | 09:43 | 0.1 | 765 | 765 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 09:43 | 09:56 | 0.22 | 765 | 858 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/765.00 t/858.00, w/WOB 8,Flow 900, RPM 100, Press 2070.00, Tq 4500, ROP 429.23, Diff 470.00, Temp 102.20
06/20/2021 | 09:56 | 10:03 | 0.12 | 858 | 858 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 10:03 | 10:09 | 0.1 | 858 | 952 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/858.00 t/952.00, w/WOB 8.00,Flow 900, RPM 100, Press 2070.00, Tq 4500, ROP 940.00, Diff 470.00, Temp 102.20
06/20/2021 | 10:09 | 10:15 | 0.1 | 952 | 952 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 10:15 | 10:17 | 0.03 | 952 | 965 | 13 | SUR | 1: BHA 1 | 2K | Rotary Drill f/952.00 t/965.00, w/WOB 8.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 390.00, Diff 300.00, Temp 102.20
06/20/2021 | 10:17 | 10:21 | 0.07 | 965 | 975 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/965.00 t/975.00, TF 255.00M, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 150.00, Diff 100.00, Temp 102.20
06/20/2021 | 10:21 | 10:26 | 0.08 | 975 | 1046 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/975.00 t/1046.00, w/WOB 8.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 852.00, Diff 300.00, Temp 102.20
06/20/2021 | 10:26 | 10:32 | 0.1 | 1046 | 1046 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 10:32 | 10:33 | 0.02 | 1046 | 1055 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1046.00 t/1055.00, w/WOB 10.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 540.00, Diff 300.00, Temp 102.20
06/20/2021 | 10:33 | 10:37 | 0.07 | 1055 | 1065 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1055.00 t/1065.00, TF 255.00M, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 150.00, Diff 100.00, Temp 102.20
06/20/2021 | 10:37 | 10:47 | 0.17 | 1065 | 1140 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1065.00 t/1140.00, w/WOB 10.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 450.00, Diff 300.00, Temp 102.20
06/20/2021 | 10:47 | 10:53 | 0.1 | 1140 | 1140 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 10:53 | 10:54 | 0.02 | 1140 | 1150 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1140.00 t/1150.00, w/WOB 10.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 600.00, Diff 300.00, Temp 102.20
06/20/2021 | 10:54 | 10:57 | 0.05 | 1150 | 1160 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1150.00 t/1160.00, TF 255.00M, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 200.00, Diff 100.00, Temp 102.20
06/20/2021 | 10:57 | 11:04 | 0.12 | 1160 | 1234 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1160.00 t/1234.00, w/WOB 10.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 634.29, Diff 300.00, Temp 102.20
06/20/2021 | 11:04 | 11:10 | 0.1 | 1234 | 1234 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 11:10 | 11:15 | 0.08 | 1234 | 1328 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1234.00 t/1328.00, w/WOB 10.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 1128.00, Diff 300.00, Temp 102.20
06/20/2021 | 11:15 | 11:20 | 0.08 | 1328 | 1328 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 11:20 | 11:21 | 0.02 | 1328 | 1335 | 7 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1328.00 t/1335.00, w/WOB 10.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 420.00, Diff 300.00, Temp 102.20
06/20/2021 | 11:21 | 11:26 | 0.08 | 1335 | 1345 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1335.00 t/1345.00, TF 255.00M, w/WOB 5.00,Flow 900.00, Press 1900.00, Tq 0.00, ROP 120.00, Diff 100.00, Temp 104.00
06/20/2021 | 11:26 | 11:31 | 0.08 | 1345 | 1422 | 77 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1345.00 t/1422.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2300.00, Tq 5500.00, ROP 924.00, Diff 500.00, Temp 104.00
06/20/2021 | 11:31 | 11:36 | 0.08 | 1422 | 1422 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 11:36 | 11:44 | 0.13 | 1422 | 1516 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1422.00 t/1516.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2300.00, Tq 5500.00, ROP 705.00, Diff 500.00, Temp 104.00
06/20/2021 | 11:44 | 11:58 | 0.23 | 1516 | 1516 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 11:58 | 11:59 | 0.02 | 1516 | 1525 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1516.00 t/1525.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2300.00, Tq 5500.00, ROP 540.00, Diff 500.00, Temp 104.00
06/20/2021 | 11:59 | 16:00 | 4.02 | 1525 | 1525 | 0 | SUR | 1: BHA 1 | 8A | Troubleshoot top top drive
06/20/2021 | 16:00 | 16:06 | 0.1 | 1525 | 1535 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1525.00 t/1535.00, TF 255.00M, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 100.00, Diff 100.00, Temp 105.00
06/20/2021 | 16:06 | 16:14 | 0.13 | 1535 | 1609 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1535.00 t/1609.00, w/WOB 15.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 555.00, Diff 300.00, Temp 105.00
06/20/2021 | 16:14 | 16:20 | 0.1 | 1609 | 1609 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 16:20 | 16:21 | 0.02 | 1609 | 1620 | 11 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1609.00 t/1620.00, w/WOB 15.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 660.00, Diff 300.00, Temp 105.00
06/20/2021 | 16:21 | 16:26 | 0.08 | 1620 | 1638 | 18 | SUR | 1: BHA 1 | 2J | Slide Drill f/1620.00 t/1638.00, TF 255M, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 216.00, Diff 100.00, Temp 105.00
06/20/2021 | 16:26 | 16:31 | 0.08 | 1638 | 1703 | 65 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1638.00 t/1703.00, w/WOB 15.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 780.00, Diff 300.00, Temp 105.00
06/20/2021 | 16:31 | 16:36 | 0.08 | 1703 | 1703 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 16:36 | 16:37 | 0.02 | 1703 | 1720 | 17 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1703.00 t/1720.00, w/WOB 15.00,Flow 700.00, RPM 100.00, Press 1400.00, Tq 4500.00, ROP 1020.00, Diff 300.00, Temp 105.00
06/20/2021 | 16:37 | 16:42 | 0.08 | 1720 | 1730 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1720.00 t/1730.00, TF 10G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 120.00, Diff 100.00, Temp 105.00
06/20/2021 | 16:42 | 16:48 | 0.1 | 1730 | 1797 | 67 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1730.00 t/1797.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 670.00, Diff 100.00, Temp 105.00
06/20/2021 | 16:48 | 16:53 | 0.08 | 1797 | 1797 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 16:53 | 16:54 | 0.02 | 1797 | 1805 | 8 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1797.00 t/1805.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 480.00, Diff 100.00, Temp 105.00
06/20/2021 | 16:54 | 16:57 | 0.05 | 1805 | 1815 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1805.00 t/1815.00, TF 10.00G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 200.00, Diff 100.00, Temp 105.00
06/20/2021 | 16:57 | 17:02 | 0.08 | 1815 | 1891 | 76 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1815.00 t/1891.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 912.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:02 | 17:07 | 0.08 | 1891 | 1891 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 17:07 | 17:08 | 0.02 | 1891 | 1900 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1891.00 t/1900.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 540.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:08 | 17:14 | 0.1 | 1900 | 1913 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/1900.00 t/1913.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 130.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:14 | 17:18 | 0.07 | 1913 | 1985 | 72 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1913.00 t/1985.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 1080.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:18 | 17:23 | 0.08 | 1985 | 1985 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 17:23 | 17:24 | 0.02 | 1985 | 1995 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1985.00 t/1995.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 600.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:24 | 17:27 | 0.05 | 1995 | 2008 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/1995.00 t/2008.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 260.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:27 | 17:30 | 0.05 | 2008 | 2079 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2008.00 t/2079.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 5000.00, ROP 1420.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:30 | 17:35 | 0.08 | 2079 | 2079 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 17:35 | 17:38 | 0.05 | 2079 | 2090 | 11 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2079.00 t/2090.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 6000.00, ROP 220.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:38 | 17:41 | 0.05 | 2090 | 2103 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/2090.00 t/2103.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 260.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:41 | 17:45 | 0.07 | 2103 | 2171 | 68 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2103.00 t/2171.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 6000.00, ROP 1020.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:45 | 17:48 | 0.05 | 2171 | 2171 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 17:48 | 17:50 | 0.03 | 2171 | 2180 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2171.00 t/2180.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 6000.00, ROP 270.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:50 | 17:54 | 0.07 | 2180 | 2190 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/2180.00 t/2190.00, TF 10.00G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 150.00, Diff 100.00, Temp 105.00
06/20/2021 | 17:54 | 18:00 | 0.1 | 2190 | 2265 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2190.00 t/2265.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 6000.00, ROP 750.00, Diff 100.00, Temp 105.00
06/20/2021 | 18:00 | 18:02 | 0.03 | 2265 | 2265 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 18:02 | 18:04 | 0.03 | 2265 | 2275 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2265.00 t/2275.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1200.00, Tq 6000.00, ROP 300.00, Diff 100.00, Temp 105.00
06/20/2021 | 18:04 | 18:14 | 0.17 | 2275 | 2288 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/2275.00 t/2288.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 1200.00, Tq 0.00, ROP 78.00, Diff 100.00, Temp 105.00
06/20/2021 | 18:14 | 18:20 | 0.1 | 2288 | 2360 | 72 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2288.00 t/2360.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 6000.00, ROP 720.00, Diff 445.00, Temp 116.00
06/20/2021 | 18:20 | 18:24 | 0.07 | 2360 | 2360 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 18:24 | 18:28 | 0.07 | 2360 | 2370 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2360.00 t/2370.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 6000.00, ROP 150.00, Diff 445.00, Temp 116.00
06/20/2021 | 18:28 | 18:32 | 0.07 | 2370 | 2383 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/2370.00 t/2383.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 2150.00, Tq 0.00, ROP 195.00, Diff 200.00, Temp 116.00
06/20/2021 | 18:32 | 18:39 | 0.12 | 2383 | 2453 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2383.00 t/2453.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 7000.00, ROP 600.00, Diff 445.00, Temp 116.00
06/20/2021 | 18:39 | 18:42 | 0.05 | 2453 | 2453 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 18:42 | 18:45 | 0.05 | 2453 | 2465 | 12 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2453.00 t/2465.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 7000.00, ROP 240.00, Diff 445.00, Temp 116.00
06/20/2021 | 18:45 | 18:49 | 0.07 | 2465 | 2479 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/2465.00 t/2479.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 2150.00, Tq 0.00, ROP 210.00, Diff 200.00, Temp 116.00
06/20/2021 | 18:49 | 18:55 | 0.1 | 2479 | 2547 | 68 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2479.00 t/2547.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 7000.00, ROP 680.00, Diff 445.00, Temp 116.00
06/20/2021 | 18:55 | 18:59 | 0.07 | 2547 | 2547 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/20/2021 | 18:59 | 19:03 | 0.07 | 2547 | 2560 | 13 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2547.00 t/2560.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 7000.00, ROP 195.00, Diff 445.00, Temp 116.00
06/20/2021 | 19:03 | 19:10 | 0.12 | 2560 | 2574 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/2560.00 t/2574.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 2150.00, Tq 0.00, ROP 120.00, Diff 200.00, Temp 116.00
06/20/2021 | 19:10 | 19:20 | 0.17 | 2574 | 2642 | 68 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2574.00 t/2642.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 10000.00, ROP 408.00, Diff 445.00, Temp 116.00
06/20/2021 | 19:20 | 19:34 | 0.23 | 2642 | 2642 | 0 | SUR | 1: BHA 1 | 8A | Work On Top Drive (Leak)
06/20/2021 | 19:34 | 19:40 | 0.1 | 2642 | 2642 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
06/20/2021 | 19:40 | 19:50 | 0.17 | 2642 | 2656 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/2642.00 t/2656.00, TF 20.00G, w/WOB 5.00,Flow 700.00, Press 2150.00, Tq 0.00, ROP 84.00, Diff 200.00, Temp 116.00
06/20/2021 | 19:50 | 19:58 | 0.13 | 2656 | 2725 | 69 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2656.00 t/2725.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 2395.00, Tq 10000.00, ROP 517.50, Diff 445.00, Temp 116.00
06/20/2021 | 19:58 | 20:04 | 0.1 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 5A | Final Survey
06/20/2021 | 20:04 | 20:50 | 0.77 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 5A | Circulate and Pump Sweeps
06/20/2021 | 20:50 | 21:00 | 0.17 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 6I | Flow Check (No Flow)
06/20/2021 | 21:00 | 22:25 | 1.42 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 6B | POOH
06/20/2021 | 22:25 | 23:15 | 0.83 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 8K | Work On Iron Roghneck (Leak)
06/20/2021 | 23:15 | 23:30 | 0.25 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 6B | POOH
06/20/2021 | 23:30 | 24:00 | 0.5 | 2725 | 2725 | 0 | SUR | 1: BHA 1 | 6P | Rack BHA #1 Back On Derrick
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_6_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/06/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 41550
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2725 |  | 2725 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 4067 |  | 4067 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 1342 |  | 1342 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): |  | 28 |  | 28 | [5 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): |  | 1314 |  | 1314 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: |  | 4.50 / 7.55 |  | 4.50 / 7.55 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 0.28 |  | 0.28 |  | SN: |  | 56410 |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 4.22 |  | 4.22 |  | Bit # |  | 2 |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 311.62 / 98.82 |  | 311.62 / 98.82 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 22 |  | 22 |  | Grade In: |  | New
% Slide: |  | 2.09 |  | 2.09 |  | Grade Out: |  | 0-1-CT-S-X-I-NO-TD
% Rotary: |  | 97.91 |  | 97.91 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.020 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.58 |  | 39.08
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.41
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.24
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.03
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 110.93
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.05
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.05
9- Joints of 5 HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.09
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.28
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.63 |  | 2564.91
2564.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
800033 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.92 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2777 | 14.82 | 248.42 | 2753.99 | -87.31 | -253.67 | 0.3 |  | -58.41 | -90.11 | 0.16 |  | -1 | 125
2871 | 14.39 | 249.45 | 2844.96 | -95.83 | -275.78 | 0.53 |  | 149.37 | -97.26 | -0.46 |  | 1.1 | 94
2965 | 14.99 | 254.15 | 2935.89 | -103.25 | -298.42 | 1.42 |  | 65.57 | -105.59 | 0.64 |  | 5 | 94
3059 | 14.93 | 255.99 | 3026.7 | -109.5 | -321.86 | 0.51 |  | 98.09 | -115.34 | -0.06 |  | 1.96 | 94
3153 | 14.68 | 255.04 | 3117.58 | -115.51 | -345.11 | 0.37 |  | -136.3 | -125.16 | -0.27 |  | -1.01 | 94
3246 | 14.64 | 253.78 | 3207.55 | -121.83 | -367.78 | 0.35 |  | -97.76 | -134.37 | -0.04 |  | -1.35 | 93
3340 | 16.19 | 257.78 | 3298.17 | -127.92 | -392 | 2 |  | 36.39 | -144.72 | 1.65 |  | 4.26 | 94
3434 | 16.62 | 257.57 | 3388.34 | -133.59 | -417.94 | 0.46 |  | -7.95 | -156.48 | 0.46 |  | -0.22 | 94
3527 | 16.54 | 257.34 | 3477.48 | -139.36 | -443.84 | 0.11 |  | -140.74 | -168.14 | -0.09 |  | -0.25 | 93
3622 | 16.44 | 256.89 | 3568.57 | -145.37 | -470.13 | 0.17 |  | -128.27 | -179.85 | -0.11 |  | -0.47 | 95
3715 | 16.51 | 255.54 | 3657.75 | -151.65 | -495.74 | 0.42 |  | -80.29 | -190.93 | 0.08 |  | -1.45 | 93
3809 | 16.46 | 255.34 | 3747.89 | -158.36 | -521.56 | 0.08 |  | -131.48 | -201.8 | -0.05 |  | -0.21 | 94
3903 | 16.61 | 255.43 | 3838 | -165.11 | -547.44 | 0.16 |  | 9.73 | -212.69 | 0.16 |  | 0.1 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 298.22 | 30.9 | 75.56 | 186 | 662.85 | 3345 | 2785 | 0 | 130 | 117.5 | 105 | 9166.67 | 0
Run | 298.22 | 30.9 | 75.56 | 186 | 662.85 | 3345 | 2785 | 0 | 130 | 117.5 | 105 | 9166.67 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/06/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/06/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD Standby |  |  |  |  | 07/06/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/06/2021 |  | 15 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/06/2021 | 00:00 | 01:30 | 1.5 | 2725 | 2725 | 0 | INT |  | 24B | Standby for rig skid and nipple up BOPs / Test
07/06/2021 | 01:30 | 02:00 | 0.5 | 2725 | 2725 | 0 | INT | 2: BHA 2 | 6O | P/U BHA Make Up Bit
07/06/2021 | 02:00 | 02:30 | 0.5 | 2725 | 2725 | 0 | INT | 2: BHA 2 | 8I | HCR Dead Headed
07/06/2021 | 02:30 | 04:00 | 1.5 | 2725 | 2725 | 0 | INT | 2: BHA 2 | 6L | Scribe & Test
07/06/2021 | 04:00 | 07:54 | 3.9 | 2725 | 2725 | 0 | INT | 2: BHA 2 | 6A | TIH to 2605
07/06/2021 | 07:54 | 08:10 | 0.27 | 2725 | 2725 | 0 | INT | 2: BHA 2 | 5A | Drill out float and shoe track
07/06/2021 | 08:10 | 08:13 | 0.05 | 2725 | 2735 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/2725.00 t/2735.00, w/WOB 18,Flow 500, RPM 40, Press 2000, Tq 3500, ROP 200.00, Diff 250.00, Temp 111.00
07/06/2021 | 08:13 | 08:42 | 0.48 | 2735 | 2735 | 0 | INT | 2: BHA 2 | 5A | Circulate bottoms up
07/06/2021 | 08:42 | 09:02 | 0.33 | 2735 | 2735 | 0 | INT | 2: BHA 2 | 15D | Perform FIT
07/06/2021 | 09:02 | 09:04 | 0.03 | 2735 | 2750 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/2735.00 t/2750.00, w/WOB 18.00,Flow 500.00, RPM 40.00, Press 2000.00, Tq 3500.00, ROP 450.00, Diff 250.00, Temp 111.00
07/06/2021 | 09:04 | 09:40 | 0.6 | 2750 | 2750 | 0 | INT | 2: BHA 2 | 8P | Rig Service
07/06/2021 | 09:40 | 10:00 | 0.33 | 2750 | 2846 | 96 | INT | 2: BHA 2 | 2K | Rotary Drill f/2750.00 t/2846.00, w/WOB 30,Flow 680, RPM 80, Press 3600, Tq 8000, ROP 288.00, Diff 700.00, Temp 111.00
07/06/2021 | 10:00 | 10:08 | 0.13 | 2846 | 2846 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 10:08 | 10:13 | 0.08 | 2846 | 2940 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/2846.00 t/2940.00, w/WOB 30,Flow 680, RPM 80, Press 3600, Tq 8000, ROP 1128.00, Diff 700.00, Temp 111.00
07/06/2021 | 10:13 | 10:18 | 0.08 | 2940 | 2940 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 10:18 | 10:20 | 0.03 | 2940 | 2950 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/2940.00 t/2950.00, w/WOB 30.00,Flow 680.00, RPM 80.00, Press 3600.00, Tq 8000.00, ROP 300.00, Diff 700.00, Temp 111.00
07/06/2021 | 10:20 | 10:28 | 0.13 | 2950 | 2963 | 13 | INT | 2: BHA 2 | 2J | Slide Drill f/2950.00 t/2963.00, TF 60G, w/WOB 8,Flow 680.00, Press 3100, Tq 0, ROP 97.50, Diff 200.00, Temp 118.00
07/06/2021 | 10:28 | 10:33 | 0.08 | 2963 | 3034 | 71 | INT | 2: BHA 2 | 2K | Rotary Drill f/2963.00 t/3034.00, w/WOB 30.00,Flow 680.00, RPM 80.00, Press 3600.00, Tq 8000.00, ROP 852.00, Diff 700.00, Temp 118.00
07/06/2021 | 10:33 | 10:38 | 0.08 | 3034 | 3034 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 10:38 | 10:51 | 0.22 | 3034 | 3128 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3034.00 t/3128.00, w/WOB 30.00,Flow 680.00, RPM 80.00, Press 3600.00, Tq 8000.00, ROP 433.85, Diff 700.00, Temp 118.00
07/06/2021 | 10:51 | 10:56 | 0.08 | 3128 | 3128 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 10:56 | 11:11 | 0.25 | 3128 | 3222 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3128.00 t/3222.00, w/WOB 30.00,Flow 680.00, RPM 80.00, Press 3600.00, Tq 8000.00, ROP 376.00, Diff 700.00, Temp 129.00
07/06/2021 | 11:11 | 11:16 | 0.08 | 3222 | 3222 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 11:16 | 11:38 | 0.37 | 3222 | 3315 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3222.00 t/3315.00, w/WOB 30.00,Flow 680.00, RPM 80.00, Press 3600.00, Tq 11000, ROP 253.64, Diff 700.00, Temp 132.00
07/06/2021 | 11:38 | 11:50 | 0.2 | 3315 | 3315 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 11:50 | 11:59 | 0.15 | 3315 | 3330 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3315.00 t/3330.00, TF 40G, w/WOB 14,Flow 680.00, Press 3100, Tq 0, ROP 100.00, Diff 200.00, Temp 132.00
07/06/2021 | 11:59 | 12:20 | 0.35 | 3330 | 3330 | 0 | INT | 2: BHA 2 | 8E | Troubleshoot Gens
07/06/2021 | 12:20 | 13:33 | 1.22 | 3330 | 3330 | 0 | INT | 2: BHA 2 | 6B | P\1tooh to Shoe 2620
07/06/2021 | 13:33 | 14:45 | 1.2 | 3330 | 3330 | 0 | INT | 2: BHA 2 | 8D | Make repairs to #3 mud pump
07/06/2021 | 14:45 | 15:06 | 0.35 | 3330 | 3330 | 0 | INT | 2: BHA 2 | 6A | TIH
07/06/2021 | 15:06 | 15:15 | 0.15 | 3330 | 3409 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/3330.00 t/3409.00, w/WOB 30.00,Flow 673.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 526.67, Diff 600.00, Temp 132.00
07/06/2021 | 15:15 | 15:20 | 0.08 | 3409 | 3409 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 15:20 | 15:26 | 0.1 | 3409 | 3423 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/3409.00 t/3423.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 140.00, Diff 600.00, Temp 132.00
07/06/2021 | 15:26 | 20:45 | 5.32 | 3423 | 3423 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 20:45 | 21:07 | 0.37 | 3423 | 3503 | 80 | INT | 2: BHA 2 | 2K | Rotary Drill f/3423.00 t/3503.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 218.18, Diff 600.00, Temp 132.00
07/06/2021 | 21:07 | 21:12 | 0.08 | 3503 | 3503 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 21:12 | 21:33 | 0.35 | 3503 | 3596 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3503.00 t/3596.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 265.71, Diff 600.00, Temp 132.00
07/06/2021 | 21:33 | 21:38 | 0.08 | 3596 | 3596 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 21:38 | 22:02 | 0.4 | 3596 | 3691 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/3596.00 t/3691.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 237.50, Diff 600.00, Temp 132.00
07/06/2021 | 22:02 | 22:07 | 0.08 | 3691 | 3691 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 22:07 | 22:26 | 0.32 | 3691 | 3784 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3691.00 t/3784.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 293.68, Diff 600.00, Temp 132.00
07/06/2021 | 22:26 | 22:31 | 0.08 | 3784 | 3784 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 22:31 | 22:50 | 0.32 | 3784 | 3878 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3784.00 t/3878.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 296.84, Diff 600.00, Temp 132.00
07/06/2021 | 22:50 | 23:00 | 0.17 | 3878 | 3878 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 23:00 | 23:23 | 0.38 | 3878 | 3972 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3878.00 t/3972.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 245.22, Diff 600.00, Temp 132.00
07/06/2021 | 23:23 | 23:33 | 0.17 | 3972 | 3972 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/06/2021 | 23:33 | 23:56 | 0.38 | 3972 | 4067 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/3972.00 t/4067.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 247.83, Diff 600.00, Temp 132.00
07/06/2021 | 23:56 | 24:00 | 0.07 | 4067 | 4067 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_7_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/07/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 48400
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 4067 |  | 2725 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 9688 |  | 9688 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 5621 |  | 6963 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): |  | 322 |  | 350 | [5 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): |  | 5299 |  | 6613 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: |  | 18.65 / 5.18 |  | 23.15 / 12.73 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 5.55 |  | 5.83 |  | SN: |  | 56410 |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 13.1 |  | 17.32 |  | Bit # |  | 2 |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 404.50 / 58.02 |  | 381.89 / 60.00 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 46 |  | Grade In: |  | New
% Slide: |  | 5.73 |  | 5.03 |  | Grade Out: |  | 0-1-CT-S-X-I-NO-TD
% Rotary: |  | 94.27 |  | 94.97 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.020 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.58 |  | 39.08
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.41
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.24
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.03
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 110.93
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.05
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.05
9- Joints of 5 HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.09
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.28
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.63 |  | 2564.91
2564.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
800033 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.92 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3998 | 16.72 | 255.4 | 3929.01 | -171.97 | -573.81 | 0.12 |  | -4.49 | -223.78 | 0.12 |  | -0.03 | 95
4093 | 15.02 | 255.15 | 4020.39 | -178.57 | -598.93 | 1.79 |  | -177.82 | -234.31 | -1.79 |  | -0.26 | 95
4188 | 14.31 | 255.08 | 4112.29 | -184.75 | -622.18 | 0.75 |  | -178.6 | -243.99 | -0.75 |  | -0.07 | 95
4283 | 14.11 | 254.32 | 4204.38 | -190.9 | -644.67 | 0.29 |  | -137.36 | -253.22 | -0.21 |  | -0.8 | 95
4378 | 14.11 | 252.99 | 4296.52 | -197.42 | -666.89 | 0.34 |  | -90.64 | -262 | 0 |  | -1.4 | 95
4471 | 14.67 | 254.69 | 4386.6 | -203.84 | -689.09 | 0.75 |  | 37.86 | -270.84 | 0.6 |  | 1.83 | 93
4565 | 14.95 | 255.51 | 4477.48 | -210.02 | -712.31 | 0.37 |  | 37.21 | -280.5 | 0.3 |  | 0.87 | 94
4659 | 14.98 | 255.81 | 4568.29 | -216.03 | -735.83 | 0.09 |  | 68.98 | -290.48 | 0.03 |  | 0.32 | 94
4753 | 14.77 | 255.5 | 4659.14 | -222.01 | -759.21 | 0.24 |  | -159.4 | -300.4 | -0.22 |  | -0.33 | 94
4847 | 14.6 | 255.97 | 4750.07 | -227.88 | -782.3 | 0.22 |  | 145.2 | -310.23 | -0.18 |  | 0.5 | 94
4941 | 14.33 | 255.06 | 4841.09 | -233.75 | -805.04 | 0.38 |  | -140.35 | -319.83 | -0.29 |  | -0.97 | 94
5034 | 13.91 | 256.96 | 4931.28 | -239.24 | -827.05 | 0.67 |  | 133.1 | -329.28 | -0.45 |  | 2.04 | 93
5128 | 13.66 | 256.41 | 5022.57 | -244.4 | -848.84 | 0.3 |  | -152.6 | -338.86 | -0.27 |  | -0.59 | 94
5222 | 15 | 256.69 | 5113.65 | -249.81 | -871.47 | 1.43 |  | 3.1 | -348.75 | 1.43 |  | 0.3 | 94
5316 | 16 | 255.9 | 5204.23 | -255.77 | -895.87 | 1.09 |  | -12.3 | -359.33 | 1.06 |  | -0.84 | 94
5412 | 15.71 | 254.9 | 5296.57 | -262.37 | -921.25 | 0.42 |  | -137.19 | -370.01 | -0.3 |  | -1.04 | 96
5506 | 15.32 | 253.82 | 5387.15 | -269.15 | -945.47 | 0.52 |  | -143.99 | -379.83 | -0.41 |  | -1.15 | 94
5601 | 15.34 | 252.81 | 5478.77 | -276.36 | -969.52 | 0.28 |  | -86.2 | -389.21 | 0.02 |  | -1.06 | 95
5694 | 16.56 | 253.29 | 5568.19 | -283.81 | -993.97 | 1.32 |  | 6.4 | -398.65 | 1.31 |  | 0.52 | 93
5788 | 17.14 | 253.08 | 5658.15 | -291.69 | -1020.05 | 0.62 |  | -6.09 | -408.77 | 0.62 |  | -0.22 | 94
5882 | 16.03 | 256.46 | 5748.24 | -298.76 | -1045.92 | 1.56 |  | 140.61 | -419.39 | -1.18 |  | 3.6 | 94
5976 | 14.81 | 257.44 | 5838.86 | -304.41 | -1070.27 | 1.33 |  | 168.42 | -430.17 | -1.3 |  | 1.04 | 94
6070 | 14.26 | 257.43 | 5929.85 | -309.54 | -1093.29 | 0.59 |  | -179.74 | -440.53 | -0.59 |  | -0.01 | 94
6164 | 14.27 | 257.01 | 6020.95 | -314.67 | -1115.88 | 0.11 |  | -84.68 | -450.63 | 0.01 |  | -0.45 | 94
6258 | 14.09 | 257.39 | 6112.08 | -319.77 | -1138.34 | 0.22 |  | 152.84 | -460.66 | -0.19 |  | 0.4 | 94
6353 | 13.55 | 256.75 | 6204.33 | -324.85 | -1160.46 | 0.59 |  | -164.5 | -470.5 | -0.57 |  | -0.67 | 95
6447 | 14.01 | 259.27 | 6295.63 | -329.49 | -1182.35 | 0.8 |  | 53.76 | -480.54 | 0.49 |  | 2.68 | 94
6540 | 14.18 | 260.62 | 6385.83 | -333.44 | -1204.65 | 0.4 |  | 63.31 | -491.37 | 0.18 |  | 1.45 | 93
6634 | 14.27 | 260.54 | 6476.95 | -337.22 | -1227.44 | 0.1 |  | -12.36 | -502.64 | 0.1 |  | -0.09 | 94
6729 | 13.43 | 261.18 | 6569.18 | -340.84 | -1249.89 | 0.9 |  | 169.97 | -513.83 | -0.88 |  | 0.67 | 95
6822 | 13.92 | 256.86 | 6659.55 | -345.04 | -1271.46 | 1.22 |  | -66.48 | -524.01 | 0.53 |  | -4.65 | 93
6916 | 14.59 | 255.21 | 6750.65 | -350.63 | -1293.92 | 0.83 |  | -32.03 | -533.65 | 0.71 |  | -1.76 | 94
7010 | 13.64 | 255.37 | 6841.82 | -356.45 | -1316.09 | 1.01 |  | 177.73 | -542.94 | -1.01 |  | 0.17 | 94
7103 | 14.41 | 252.18 | 6932.04 | -362.76 | -1337.71 | 1.17 |  | -46.67 | -551.51 | 0.83 |  | -3.43 | 93
7197 | 14.64 | 253.2 | 7023.04 | -369.77 | -1360.22 | 0.37 |  | 48.54 | -560.08 | 0.24 |  | 1.09 | 94
7291 | 13.01 | 255.21 | 7114.31 | -375.91 | -1381.83 | 1.81 |  | 164.56 | -568.77 | -1.73 |  | 2.14 | 94
7385 | 13.82 | 256.1 | 7205.75 | -381.31 | -1402.95 | 0.89 |  | 14.73 | -577.74 | 0.86 |  | 0.95 | 94
7479 | 14.6 | 258.01 | 7296.87 | -386.47 | -1425.44 | 0.97 |  | 31.94 | -587.75 | 0.83 |  | 2.03 | 94
7573 | 12.73 | 261.27 | 7388.21 | -390.5 | -1447.27 | 2.15 |  | 159.19 | -598.22 | -1.99 |  | 3.47 | 94
7667 | 12.9 | 258.18 | 7479.87 | -394.22 | -1467.78 | 0.75 |  | -77.58 | -608.11 | 0.18 |  | -3.29 | 94
7761 | 11.64 | 259.86 | 7571.72 | -398.04 | -1487.38 | 1.39 |  | 165 | -617.36 | -1.34 |  | 1.79 | 94
7855 | 10.02 | 261.84 | 7664.04 | -400.87 | -1504.81 | 1.77 |  | 168.04 | -626.03 | -1.72 |  | 2.11 | 94
7949 | 10.88 | 253.64 | 7756.49 | -404.53 | -1521.42 | 1.83 |  | -64.04 | -633.54 | 0.91 |  | -8.72 | 94
8043 | 10.65 | 252.25 | 7848.83 | -409.68 | -1538.21 | 0.37 |  | -132.22 | -639.99 | -0.24 |  | -1.48 | 94
8136 | 9.42 | 253.02 | 7940.41 | -414.52 | -1553.67 | 1.33 |  | 174.15 | -645.86 | -1.32 |  | 0.83 | 93
8230 | 8.2 | 252.88 | 8033.3 | -418.74 | -1567.44 | 1.3 |  | -179.06 | -651.16 | -1.3 |  | -0.15 | 94
8324 | 6.86 | 253.13 | 8126.49 | -422.34 | -1579.21 | 1.43 |  | 178.72 | -655.69 | -1.43 |  | 0.27 | 94
8418 | 6.31 | 251.12 | 8219.87 | -425.64 | -1589.47 | 0.63 |  | -158.26 | -659.52 | -0.59 |  | -2.14 | 94
8511 | 8.43 | 251.8 | 8312.09 | -429.43 | -1600.79 | 2.28 |  | 2.69 | -663.62 | 2.28 |  | 0.73 | 93
8605 | 9.57 | 254.2 | 8404.93 | -433.71 | -1614.85 | 1.28 |  | 19.42 | -669.06 | 1.21 |  | 2.55 | 94
8699 | 8.8 | 256.01 | 8497.73 | -437.57 | -1629.35 | 0.87 |  | 160.32 | -675.09 | -0.82 |  | 1.93 | 94
8793 | 8.09 | 258.44 | 8590.71 | -440.64 | -1642.81 | 0.85 |  | 154.51 | -681.09 | -0.76 |  | 2.59 | 94
8887 | 6.92 | 258.57 | 8683.9 | -443.08 | -1654.84 | 1.24 |  | 179.23 | -686.69 | -1.24 |  | 0.14 | 94
8981 | 5.76 | 257.38 | 8777.32 | -445.24 | -1664.99 | 1.24 |  | -174.13 | -691.34 | -1.23 |  | -1.27 | 94
9075 | 4.63 | 255.17 | 8870.94 | -447.24 | -1673.26 | 1.22 |  | -171.06 | -694.94 | -1.2 |  | -2.35 | 94
9169 | 2.6 | 241.43 | 8964.75 | -449.23 | -1678.8 | 2.33 |  | -163.65 | -696.84 | -2.16 |  | -14.62 | 94
9262 | 1.41 | 221.94 | 9057.69 | -451.09 | -1681.42 | 1.46 |  | -159.69 | -697.02 | -1.28 |  | -20.96 | 93
9356 | 0.4 | 339.27 | 9151.68 | -451.64 | -1682.31 | 1.74 |  | 167.43 | -697.15 | -1.07 |  | 0 | 94
9450 | 0.63 | 356.15 | 9245.68 | -450.82 | -1682.46 | 0.29 |  | 42.04 | -697.88 | 0.24 |  | 0 | 94
9544 | 0.41 | 41.44 | 9339.67 | -450.05 | -1682.27 | 0.48 |  | 139.53 | -698.37 | -0.23 |  | 0 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 301.88 | 32.82 | 80 | 196 | 701.09 | 3979.57 | 3304.3 | 0 | 192.15 | 168.39 | 144.62 | 18613.33 | 0
Run | 301.17 | 32.48 | 79.14 | 194 | 694.32 | 3867.26 | 3212.39 | 0 | 181.15 | 159.38 | 137.61 | 16784.95 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/07/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/07/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD Standby |  |  |  |  | 07/07/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/07/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/07/2021 | 00:00 | 00:05 | 0.08 | 4067 | 4080 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/4067.00 t/4080.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 156.00, Diff 600.00, Temp 132.00
07/07/2021 | 00:05 | 00:09 | 0.07 | 4080 | 4090 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4080.00 t/4090.00, TF 180.00G, w/WOB 10.00,Flow 683.00, Press 3500.00, Tq 0.00, ROP 150.00, Diff 600.00, Temp 132.00
07/07/2021 | 00:09 | 00:20 | 0.18 | 4090 | 4162 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/4090.00 t/4162.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 392.73, Diff 600.00, Temp 132.00
07/07/2021 | 00:20 | 00:25 | 0.08 | 4162 | 4162 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 00:25 | 00:39 | 0.23 | 4162 | 4257 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4162.00 t/4257.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 407.14, Diff 600.00, Temp 132.00
07/07/2021 | 00:39 | 00:44 | 0.08 | 4257 | 4257 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 00:44 | 00:56 | 0.2 | 4257 | 4352 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4257.00 t/4352.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 475.00, Diff 600.00, Temp 132.00
07/07/2021 | 00:56 | 00:59 | 0.05 | 4352 | 4352 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 00:59 | 01:13 | 0.23 | 4352 | 4447 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4352.00 t/4447.00, w/WOB 40,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 407.14, Diff 600.00, Temp 132.00
07/07/2021 | 01:13 | 01:18 | 0.08 | 4447 | 4447 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 01:18 | 01:20 | 0.03 | 4447 | 4460 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/4447.00 t/4460.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3500.00, Tq 11000.00, ROP 390.00, Diff 600.00, Temp 132.00
07/07/2021 | 01:20 | 01:25 | 0.08 | 4460 | 4470 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4460.00 t/4470.00, TF 50G, w/WOB 10,Flow 683.00, Press 3500.00, Tq 0, ROP 120.00, Diff 600.00, Temp 132.00
07/07/2021 | 01:25 | 01:35 | 0.17 | 4470 | 4540 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/4470.00 t/4540.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 420.00, Diff 700.00, Temp 159.00
07/07/2021 | 01:35 | 01:40 | 0.08 | 4540 | 4540 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 01:40 | 01:50 | 0.17 | 4540 | 4634 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4540.00 t/4634.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 564.00, Diff 700.00, Temp 159.00
07/07/2021 | 01:50 | 01:55 | 0.08 | 4634 | 4634 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 01:55 | 02:06 | 0.18 | 4634 | 4728 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4634.00 t/4728.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 512.73, Diff 700.00, Temp 159.00
07/07/2021 | 02:06 | 02:15 | 0.15 | 4728 | 4728 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 02:15 | 02:27 | 0.2 | 4728 | 4822 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4728.00 t/4822.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 470.00, Diff 700.00, Temp 159.00
07/07/2021 | 02:27 | 02:32 | 0.08 | 4822 | 4822 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 02:32 | 02:48 | 0.27 | 4822 | 4916 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4822.00 t/4916.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 352.50, Diff 700.00, Temp 159.00
07/07/2021 | 02:48 | 02:53 | 0.08 | 4916 | 4916 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 02:53 | 03:03 | 0.17 | 4916 | 5010 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4916.00 t/5010.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 564.00, Diff 700.00, Temp 159.00
07/07/2021 | 03:03 | 03:08 | 0.08 | 5010 | 5010 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 03:08 | 03:10 | 0.03 | 5010 | 5020 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/5010.00 t/5020.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 300.00, Diff 700.00, Temp 159.00
07/07/2021 | 03:10 | 03:30 | 0.33 | 5020 | 5030 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5020.00 t/5030.00, TF 20G, w/WOB 18,Flow 683.00, Press 3600.00, Tq 0, ROP 30.00, Diff 700.00, Temp 159.00
07/07/2021 | 03:30 | 03:42 | 0.2 | 5030 | 5103 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/5030.00 t/5103.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 365.00, Diff 700.00, Temp 159.00
07/07/2021 | 03:42 | 03:47 | 0.08 | 5103 | 5103 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 03:47 | 03:58 | 0.18 | 5103 | 5197 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5103.00 t/5197.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3600.00, Tq 15000.00, ROP 512.73, Diff 700.00, Temp 159.00
07/07/2021 | 03:58 | 04:03 | 0.08 | 5197 | 5197 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 04:03 | 04:06 | 0.05 | 5197 | 5210 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/5197.00 t/5210.00, w/WOB 40.00,Flow 683.00, RPM 80.00, Press 3900, Tq 19000, ROP 260.00, Diff 700.00, Temp 170.00
07/07/2021 | 04:06 | 04:19 | 0.22 | 5210 | 5220 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5210.00 t/5220.00, TF 0G, w/WOB 18,Flow 683.00, Press 3900, Tq 0, ROP 46.15, Diff 700.00, Temp 170.00
07/07/2021 | 04:19 | 04:30 | 0.18 | 5220 | 5289 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/5220.00 t/5289.00, w/WOB 42,Flow 683.00, RPM 80, Press 3900.00, Tq 19000, ROP 376.36, Diff 700.00, Temp 170.00
07/07/2021 | 04:30 | 04:35 | 0.08 | 5289 | 5289 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 04:35 | 04:46 | 0.18 | 5289 | 5385 | 96 | INT | 2: BHA 2 | 2K | Rotary Drill f/5289.00 t/5385.00, w/WOB 42.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 19000.00, ROP 523.64, Diff 700.00, Temp 170.00
07/07/2021 | 04:46 | 04:51 | 0.08 | 5385 | 5385 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 04:51 | 05:02 | 0.18 | 5385 | 5481 | 96 | INT | 2: BHA 2 | 2K | Rotary Drill f/5385.00 t/5481.00, w/WOB 42.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 19000.00, ROP 523.64, Diff 700.00, Temp 170.00
07/07/2021 | 05:02 | 05:08 | 0.1 | 5481 | 5481 | 0 | INT | 2: BHA 2 | 24A | BOP Drill
07/07/2021 | 05:08 | 05:12 | 0.07 | 5481 | 5481 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
07/07/2021 | 05:12 | 05:25 | 0.22 | 5481 | 5575 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5481.00 t/5575.00, w/WOB 42.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 19000.00, ROP 433.85, Diff 700.00, Temp 170.00
07/07/2021 | 05:25 | 05:30 | 0.08 | 5575 | 5575 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 05:30 | 05:42 | 0.2 | 5575 | 5670 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5575.00 t/5670.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 475.00, Diff 700.00, Temp 170.00
07/07/2021 | 05:42 | 05:47 | 0.08 | 5670 | 5670 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 05:47 | 05:50 | 0.05 | 5670 | 5680 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/5670.00 t/5680.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 200.00, Diff 700.00, Temp 170.00
07/07/2021 | 05:50 | 06:00 | 0.17 | 5680 | 5695 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5680.00 t/5695.00, TF 90.00G, w/WOB 18.00,Flow 683.00, Press 3500.00, Tq 0.00, ROP 90.00, Diff 300.00, Temp 170.00
07/07/2021 | 06:00 | 06:08 | 0.13 | 5695 | 5763 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/5695.00 t/5763.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 510.00, Diff 700.00, Temp 170.00
07/07/2021 | 06:08 | 06:13 | 0.08 | 5763 | 5763 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 06:13 | 06:24 | 0.18 | 5763 | 5857 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5763.00 t/5857.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 512.73, Diff 700.00, Temp 170.00
07/07/2021 | 06:24 | 06:30 | 0.1 | 5857 | 5857 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 06:30 | 06:32 | 0.03 | 5857 | 5865 | 8 | INT | 2: BHA 2 | 2K | Rotary Drill f/5857.00 t/5865.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 240.00, Diff 700.00, Temp 170.00
07/07/2021 | 06:32 | 06:42 | 0.17 | 5865 | 5885 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/5865.00 t/5885.00, TF 130.00G, w/WOB 18.00,Flow 683.00, Press 3500.00, Tq 0.00, ROP 120.00, Diff 300.00, Temp 170.00
07/07/2021 | 06:42 | 06:52 | 0.17 | 5885 | 5951 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/5885.00 t/5951.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 396.00, Diff 700.00, Temp 183.00
07/07/2021 | 06:52 | 06:57 | 0.08 | 5951 | 5951 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 06:57 | 07:06 | 0.15 | 5951 | 6045 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5951.00 t/6045.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 626.67, Diff 700.00, Temp 183.00
07/07/2021 | 07:06 | 07:10 | 0.07 | 6045 | 6045 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 07:10 | 07:19 | 0.15 | 6045 | 6139 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6045.00 t/6139.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 626.67, Diff 700.00, Temp 183.00
07/07/2021 | 07:19 | 07:25 | 0.1 | 6139 | 6139 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 07:25 | 07:39 | 0.23 | 6139 | 6233 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6139.00 t/6233.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 402.86, Diff 700.00, Temp 183.00
07/07/2021 | 07:39 | 07:44 | 0.08 | 6233 | 6233 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 07:44 | 07:54 | 0.17 | 6233 | 6327 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6233.00 t/6327.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 3900.00, Tq 20000.00, ROP 564.00, Diff 700.00, Temp 183.00
07/07/2021 | 07:54 | 08:00 | 0.1 | 6327 | 6327 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 08:00 | 08:11 | 0.18 | 6327 | 6422 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6327.00 t/6422.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000, Tq 20000.00, ROP 518.18, Diff 700.00, Temp 183.00
07/07/2021 | 08:11 | 08:15 | 0.07 | 6422 | 6422 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 08:15 | 08:18 | 0.05 | 6422 | 6435 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/6422.00 t/6435.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000, Tq 20000.00, ROP 260.00, Diff 700.00, Temp 183.00
07/07/2021 | 08:18 | 08:36 | 0.3 | 6435 | 6455 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/6435.00 t/6455.00, TF 30G, w/WOB 18.00,Flow 683.00, Press 3500, Tq 0.00, ROP 66.67, Diff 200.00, Temp 183.00
07/07/2021 | 08:36 | 08:46 | 0.17 | 6455 | 6516 | 61 | INT | 2: BHA 2 | 2K | Rotary Drill f/6455.00 t/6516.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000, Tq 20000.00, ROP 366.00, Diff 700.00, Temp 183.00
07/07/2021 | 08:46 | 08:50 | 0.07 | 6516 | 6516 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 08:50 | 09:02 | 0.2 | 6516 | 6609 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6516.00 t/6609.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000, Tq 20000.00, ROP 465.00, Diff 700.00, Temp 183.00
07/07/2021 | 09:02 | 09:07 | 0.08 | 6609 | 6609 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 09:07 | 09:19 | 0.2 | 6609 | 6703 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6609.00 t/6703.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000, Tq 20000.00, ROP 470.00, Diff 700.00, Temp 183.00
07/07/2021 | 09:19 | 09:25 | 0.1 | 6703 | 6703 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 09:25 | 09:33 | 0.13 | 6703 | 6798 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6703.00 t/6798.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000, Tq 20000.00, ROP 712.50, Diff 700.00, Temp 183.00
07/07/2021 | 09:33 | 09:39 | 0.1 | 6798 | 6798 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 09:39 | 09:42 | 0.05 | 6798 | 6815 | 17 | INT | 2: BHA 2 | 2K | Rotary Drill f/6798.00 t/6815.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 340.00, Diff 700.00, Temp 190.00
07/07/2021 | 09:42 | 09:59 | 0.28 | 6815 | 6835 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/6815.00 t/6835.00, TF -30.00G, w/WOB 18.00,Flow 683.00, Press 3500.00, Tq 0.00, ROP 70.59, Diff 200.00, Temp 190.00
07/07/2021 | 09:59 | 10:07 | 0.13 | 6835 | 6891 | 56 | INT | 2: BHA 2 | 2K | Rotary Drill f/6835.00 t/6891.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 420.00, Diff 700.00, Temp 190.00
07/07/2021 | 10:07 | 10:12 | 0.08 | 6891 | 6891 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 10:12 | 10:22 | 0.17 | 6891 | 6985 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6891.00 t/6985.00, w/WOB 35.00,Flow 683.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 564.00, Diff 700.00, Temp 190.00
07/07/2021 | 10:22 | 10:27 | 0.08 | 6985 | 6985 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 10:27 | 10:37 | 0.17 | 6985 | 7079 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6985.00 t/7079.00, w/WOB 35.00,Flow 700, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 564.00, Diff 700.00, Temp 190.00
07/07/2021 | 10:37 | 10:42 | 0.08 | 7079 | 7079 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 10:42 | 10:45 | 0.05 | 7079 | 7090 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/7079.00 t/7090.00, w/WOB 35.00,Flow 700, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 220.00, Diff 700.00, Temp 190.00
07/07/2021 | 10:45 | 11:02 | 0.28 | 7090 | 7110 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7090.00 t/7110.00, TF 0G, w/WOB 18,Flow 700, Press 4000.00, Tq 0, ROP 70.59, Diff 700.00, Temp 190.00
07/07/2021 | 11:02 | 11:11 | 0.15 | 7110 | 7172 | 62 | INT | 2: BHA 2 | 2K | Rotary Drill f/7110.00 t/7172.00, w/WOB 35.00,Flow 700, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 413.33, Diff 700.00, Temp 197.00
07/07/2021 | 11:11 | 11:15 | 0.07 | 7172 | 7172 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 11:15 | 11:27 | 0.2 | 7172 | 7266 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7172.00 t/7266.00, w/WOB 35.00,Flow 700, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 470.00, Diff 700.00, Temp 197.00
07/07/2021 | 11:27 | 11:33 | 0.1 | 7266 | 7266 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 11:33 | 11:58 | 0.42 | 7266 | 7360 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7266.00 t/7360.00, w/WOB 35.00,Flow 850, RPM 80.00, Press 5800, Tq 20000.00, ROP 225.60, Diff 1000.00, Temp 197.00
07/07/2021 | 11:58 | 12:03 | 0.08 | 7360 | 7360 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 12:03 | 12:07 | 0.07 | 7360 | 7370 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7360.00 t/7370.00, w/WOB 35.00,Flow 850, RPM 80.00, Press 5800, Tq 20000.00, ROP 150.00, Diff 1000.00, Temp 197.00
07/07/2021 | 12:07 | 12:32 | 0.42 | 7370 | 7410 | 40 | INT | 2: BHA 2 | 2J | Slide Drill f/7370.00 t/7410.00, TF 0G, w/WOB 18,Flow 850, Press 5100, Tq 0, ROP 96.00, Diff 300.00, Temp 190.00
07/07/2021 | 12:32 | 12:38 | 0.1 | 7410 | 7454 | 44 | INT | 2: BHA 2 | 2K | Rotary Drill f/7410.00 t/7454.00, w/WOB 35.00,Flow 850, RPM 80.00, Press 5800, Tq 20000.00, ROP 440.00, Diff 1000.00, Temp 197.00
07/07/2021 | 12:38 | 12:44 | 0.1 | 7454 | 7454 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 12:44 | 12:53 | 0.15 | 7454 | 7548 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7454.00 t/7548.00, w/WOB 35.00,Flow 850, RPM 80.00, Press 5800, Tq 20000.00, ROP 626.67, Diff 1000.00, Temp 197.00
07/07/2021 | 12:53 | 12:59 | 0.1 | 7548 | 7548 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 12:59 | 13:07 | 0.13 | 7548 | 7642 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7548.00 t/7642.00, w/WOB 35.00,Flow 850, RPM 80.00, Press 5800, Tq 20000.00, ROP 705.00, Diff 1000.00, Temp 197.00
07/07/2021 | 13:07 | 13:17 | 0.17 | 7642 | 7642 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 13:17 | 13:20 | 0.05 | 7642 | 7650 | 8 | INT | 2: BHA 2 | 2K | Rotary Drill f/7642.00 t/7650.00, w/WOB 35.00,Flow 700, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 160.00, Diff 700.00, Temp 203.00
07/07/2021 | 13:20 | 13:39 | 0.32 | 7650 | 7680 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/7650.00 t/7680.00, TF -30G, w/WOB 18,Flow 700, Press 3800, Tq 0, ROP 94.74, Diff 300.00, Temp 203.00
07/07/2021 | 13:39 | 13:47 | 0.13 | 7680 | 7736 | 56 | INT | 2: BHA 2 | 2K | Rotary Drill f/7680.00 t/7736.00, w/WOB 35.00,Flow 700, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 420.00, Diff 700.00, Temp 203.00
07/07/2021 | 13:47 | 13:52 | 0.08 | 7736 | 7736 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 13:52 | 14:03 | 0.18 | 7736 | 7830 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7736.00 t/7830.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 512.73, Diff 700.00, Temp 203.00
07/07/2021 | 14:03 | 14:07 | 0.07 | 7830 | 7830 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 14:07 | 14:19 | 0.2 | 7830 | 7924 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7830.00 t/7924.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 470.00, Diff 700.00, Temp 203.00
07/07/2021 | 14:19 | 14:25 | 0.1 | 7924 | 7924 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 14:25 | 14:28 | 0.05 | 7924 | 7935 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/7924.00 t/7935.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 220.00, Diff 700.00, Temp 203.00
07/07/2021 | 14:28 | 14:52 | 0.4 | 7935 | 7965 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/7935.00 t/7965.00, TF -50.00G, w/WOB 18.00,Flow 700.00, Press 3800.00, Tq 0.00, ROP 75.00, Diff 300.00, Temp 203.00
07/07/2021 | 14:52 | 15:02 | 0.17 | 7965 | 8018 | 53 | INT | 2: BHA 2 | 2K | Rotary Drill f/7965.00 t/8018.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 318.00, Diff 700.00, Temp 203.00
07/07/2021 | 15:02 | 15:07 | 0.08 | 8018 | 8018 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 15:07 | 15:17 | 0.17 | 8018 | 8112 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8018.00 t/8112.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 564.00, Diff 700.00, Temp 203.00
07/07/2021 | 15:17 | 15:22 | 0.08 | 8112 | 8112 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 15:22 | 15:39 | 0.28 | 8112 | 8205 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8112.00 t/8205.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 328.24, Diff 700.00, Temp 203.00
07/07/2021 | 15:39 | 15:45 | 0.1 | 8205 | 8205 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 15:45 | 15:56 | 0.18 | 8205 | 8299 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8205.00 t/8299.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 512.73, Diff 700.00, Temp 203.00
07/07/2021 | 15:56 | 16:00 | 0.07 | 8299 | 8299 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 16:00 | 16:11 | 0.18 | 8299 | 8393 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8299.00 t/8393.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 512.73, Diff 700.00, Temp 203.00
07/07/2021 | 16:11 | 16:16 | 0.08 | 8393 | 8393 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 16:16 | 16:20 | 0.07 | 8393 | 8405 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/8393.00 t/8405.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 180.00, Diff 700.00, Temp 203.00
07/07/2021 | 16:20 | 16:55 | 0.58 | 8405 | 8420 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8405.00 t/8420.00, TF 0G, w/WOB 18,Flow 700.00, Press 4000.00, Tq 0, ROP 25.71, Diff 700.00, Temp 203.00
07/07/2021 | 16:55 | 17:04 | 0.15 | 8420 | 8420 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 17:04 | 17:09 | 0.08 | 8420 | 8425 | 5 | INT | 2: BHA 2 | 2J | Slide Drill f/8420.00 t/8425.00, TF 30G, w/WOB 18,Flow 700.00, Press 4000.00, Tq 0, ROP 60.00, Diff 700.00, Temp 203.00
07/07/2021 | 17:09 | 17:19 | 0.17 | 8425 | 8487 | 62 | INT | 2: BHA 2 | 2K | Rotary Drill f/8425.00 t/8487.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 372.00, Diff 700.00, Temp 203.00
07/07/2021 | 17:19 | 17:27 | 0.13 | 8487 | 8487 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 17:27 | 17:33 | 0.1 | 8487 | 8500 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/8487.00 t/8500.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 130.00, Diff 700.00, Temp 203.00
07/07/2021 | 17:33 | 17:57 | 0.4 | 8500 | 8530 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/8500.00 t/8530.00, TF 30G, w/WOB 16,Flow 700.00, Press 4000.00, Tq 20000.00, ROP 75.00, Diff 700.00, Temp 203.00
07/07/2021 | 17:57 | 18:05 | 0.13 | 8530 | 8580 | 50 | INT | 2: BHA 2 | 2K | Rotary Drill f/8530.00 t/8580.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 375.00, Diff 700.00, Temp 203.00
07/07/2021 | 18:05 | 18:10 | 0.08 | 8580 | 8580 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 18:10 | 18:22 | 0.2 | 8580 | 8674 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8580.00 t/8674.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 470.00, Diff 700.00, Temp 203.00
07/07/2021 | 18:22 | 18:26 | 0.07 | 8674 | 8674 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 18:26 | 18:40 | 0.23 | 8674 | 8768 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8674.00 t/8768.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 402.86, Diff 700.00, Temp 203.00
07/07/2021 | 18:40 | 18:45 | 0.08 | 8768 | 8768 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 18:45 | 18:58 | 0.22 | 8768 | 8862 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8768.00 t/8862.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 433.85, Diff 700.00, Temp 219.00
07/07/2021 | 18:58 | 19:02 | 0.07 | 8862 | 8862 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 19:02 | 19:16 | 0.23 | 8862 | 8956 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8862.00 t/8956.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 402.86, Diff 700.00, Temp 219.00
07/07/2021 | 19:16 | 19:21 | 0.08 | 8956 | 8956 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 19:21 | 19:35 | 0.23 | 8956 | 9050 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8956.00 t/9050.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 402.86, Diff 700.00, Temp 219.00
07/07/2021 | 19:35 | 19:40 | 0.08 | 9050 | 9050 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 19:40 | 19:54 | 0.23 | 9050 | 9144 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9050.00 t/9144.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 402.86, Diff 700.00, Temp 219.00
07/07/2021 | 19:54 | 19:59 | 0.08 | 9144 | 9144 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 19:59 | 20:05 | 0.1 | 9144 | 9155 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/9144.00 t/9155.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 110.00, Diff 700.00, Temp 219.00
07/07/2021 | 20:05 | 20:42 | 0.62 | 9155 | 9175 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9155.00 t/9175.00, TF 50M, w/WOB 16,Flow 700.00, Press 4000.00, Tq 0, ROP 32.43, Diff 700.00, Temp 219.00
07/07/2021 | 20:42 | 20:55 | 0.22 | 9175 | 9238 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/9175.00 t/9238.00, w/WOB 35.00,Flow 700.00, RPM 80, Press 4000.00, Tq 20000, ROP 290.77, Diff 700.00, Temp 219.00
07/07/2021 | 20:55 | 21:00 | 0.08 | 9238 | 9238 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 21:00 | 21:18 | 0.3 | 9238 | 9331 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9175.00 t/9331.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 520.00, Diff 700.00, Temp 219.00
07/07/2021 | 21:18 | 21:23 | 0.08 | 9331 | 9331 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 21:23 | 21:25 | 0.03 | 9331 | 9340 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/9331.00 t/9340.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 270.00, Diff 700.00, Temp 219.00
07/07/2021 | 21:25 | 22:00 | 0.58 | 9340 | 9355 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/9340.00 t/9355.00, TF 15M, w/WOB 16,Flow 700.00, Press 4000.00, Tq 0, ROP 25.71, Diff 700.00, Temp 219.00
07/07/2021 | 22:00 | 22:31 | 0.52 | 9355 | 9425 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/9355.00 t/9425.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 135.48, Diff 700.00, Temp 219.00
07/07/2021 | 22:31 | 22:36 | 0.08 | 9425 | 9425 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 22:36 | 23:01 | 0.42 | 9425 | 9519 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9425.00 t/9519.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 225.60, Diff 700.00, Temp 219.00
07/07/2021 | 23:01 | 23:06 | 0.08 | 9519 | 9519 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 23:06 | 23:25 | 0.32 | 9519 | 9613 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9519.00 t/9613.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 296.84, Diff 700.00, Temp 219.00
07/07/2021 | 23:25 | 23:30 | 0.08 | 9613 | 9613 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/07/2021 | 23:30 | 23:45 | 0.25 | 9613 | 9686 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/9613.00 t/9686.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 4000.00, Tq 20000.00, ROP 292.00, Diff 700.00, Temp 219.00
07/07/2021 | 23:45 | 24:00 | 0.25 | 9686 | 9688 | 2 | INT | 2: BHA 2 | 2J | Slide Drill f/9686.00 t/9688.00, TF 140M, w/WOB 35.00,Flow 700.00, Press 4000.00, Tq 20000.00, ROP 8.00, Diff 700.00, Temp 219.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_8_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/08/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 55250
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9688 |  | 10030 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10030 |  | 10030 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: | [5 empty] | SN: |  | 56410 |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: | [5 empty] | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-CT-S-X-I-NO-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.020 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.58 |  | 39.08
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.41
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.24
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.03
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 110.93
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.05
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.05
9- Joints of 5 HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.09
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.28
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.63 |  | 2564.91
2564.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
800033 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.92 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9638 | 0.32 | 46.31 | 9433.67 | -449.62 | -1681.86 | 0.1 |  | 163.4 | -698.45 | -0.1 |  | 0 | 94
9732 | 3.43 | 142.55 | 9527.62 | -451.67 | -1679.96 | 3.7 |  | 101.48 | -695.66 | 3.31 |  | 0 | 94
9826 | 10.04 | 149.79 | 9620.92 | -460.99 | -1674.12 | 7.08 |  | 10.93 | -684.73 | 7.03 |  | 7.7 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 39.24 | 12 | 0 | 116 | 700 | 4000 | 3300 | 0 | 220 | 190 | 150 | 0 | 0
Run | 229.24 | 31.92 | 79.14 | 194 | 694.42 | 3869.57 | 3213.91 | 0 | 181.83 | 159.91 | 137.83 | 16784.95 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/08/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/08/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD Standby |  |  |  |  | 07/08/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/08/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/08/2021 | 00:00 | 00:45 | 0.75 | 9688 | 9707 | 19 | INT | 2: BHA 2 | 2J | Slide Drill f/9688.00 t/9707.00, TF 140.00M, w/WOB 12,Flow 700.00, Press 4000.00, Tq 0, ROP 25.33, Diff 700.00, Temp 219.00
07/08/2021 | 00:45 | 00:50 | 0.08 | 9707 | 9707 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/08/2021 | 00:50 | 04:06 | 3.27 | 9707 | 9801 | 94 | INT | 2: BHA 2 | 2J | Slide Drill f/9707.00 t/9801.00, TF 140.0M, w/WOB 12,Flow 700.00, Press 4000.00, Tq 0, ROP 28.78, Diff 700.00, Temp 219.00
07/08/2021 | 04:06 | 04:45 | 0.65 | 9801 | 9801 | 0 | INT | 2: BHA 2 | 8P | Rig Service
07/08/2021 | 04:45 | 04:50 | 0.08 | 9801 | 9801 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
07/08/2021 | 04:50 | 08:15 | 3.42 | 9801 | 9895 | 94 | INT | 2: BHA 2 | 2J | Slide Drill f/9801.00 t/9895.00, TF 140M, w/WOB 12.00,Flow 700.00, Press 4000.00, Tq 0.00, ROP 27.51, Diff 700.00, Temp 219.00
07/08/2021 | 08:15 | 08:20 | 0.08 | 9895 | 9895 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/08/2021 | 08:20 | 09:37 | 1.28 | 9895 | 10030 | 135 | INT | 2: BHA 2 | 2K | Rotary Drill f/9895.00 t/10030.00, w/WOB 35,Flow 850, RPM 30, Press 5200, Tq 18000, ROP 105.19, Diff -41800.00, Temp 219.00
07/08/2021 | 09:37 | 09:42 | 0.08 | 10030 | 10030 | 0 | INT | 2: BHA 2 | 5A | MWD Survey @ TD section
07/08/2021 | 09:42 | 17:20 | 7.63 | 10030 | 10030 | 0 | INT | 2: BHA 2 | 6B | POOH to run intermediate casing and rig skid
07/08/2021 | 17:20 | 18:50 | 1.5 | 10030 | 10030 | 0 | INT | 2: BHA 2 | 6P | Lay down swap out mud motors, and pull MWD, rack back in derrick.
07/08/2021 | 18:50 | 22:30 | 3.67 | 10030 | 10030 | 0 | INT |  | 24B | Standby for intermediate casing opps
07/08/2021 | 22:30 | 24:00 | 1.5 | 10030 | 10030 | 0 | INT | 3: BHA 3 | 6O | P/U BHA Due To Well Controle Issues
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_9_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/09/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 62100
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10030 |  | 10030 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10030 |  | 10030 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: |  | 0.00 / 6.25 |  | 0.00 / 6.25 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: | [5 empty] | SN: |  | 56410 |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 0.000
BRT Hrs: |  | 18 |  | 18 |  | Grade In: |  | 0-1-CT-S-N-I-NO-TD
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | /
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.020 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.58 |  | 39.08
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 67.11
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 70.01
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 254.13
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 257.13
9- Joints of 5 HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 528.17
528.17
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800033 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.92 |  | 0 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 12 | 0 | 116 | 700 | 4000 | 3300 | 0 | 220 | 190 | 150 | 0 | 0
Run | 0 | 31.92 | 79.14 | 194 | 694.42 | 3869.57 | 3213.91 | 0 | 181.83 | 159.91 | 137.83 | 16784.95 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/09/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/09/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD Standby |  |  |  |  | 07/09/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/09/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/09/2021 | 00:00 | 05:30 | 5.5 | 10030 | 10030 | 0 | INT | 3: BHA 3 | 6A | TIH
07/09/2021 | 05:30 | 11:45 | 6.25 | 10030 | 10030 | 0 | INT | 3: BHA 3 | 5D | Circulate & Condiction Mud (WT /UP - 10.0)
07/09/2021 | 11:45 | 17:00 | 5.25 | 10030 | 10030 | 0 | INT | 3: BHA 3 | 6B | POOH
07/09/2021 | 17:00 | 18:00 | 1 | 10030 | 10030 | 0 | INT | 3: BHA 3 | 6P | Work BHA (Rack Back In Derrick)
07/09/2021 | 18:00 | 24:00 | 6 | 10030 | 10030 | 0 | INT |  | 24B | Standby For CSG Ops.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_10_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/10/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 68950
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10030 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10030 |  | 10030 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 12 | 0 | 476 | 700 | 4000 | 3300 | 0 | 220 | 190 | 150 | 0 | 0
Run | 0 | 31.92 | 79.14 | 551 | 694.42 | 3869.57 | 3213.91 | 0 | 181.83 | 159.91 | 137.83 | 16784.95 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/10/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/10/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD Standby |  |  |  |  | 07/10/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/10/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/10/2021 | 00:00 | 24:00 | 24 | 10030 | 10030 | 0 | INT |  | 24B | Standby For CSG Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_26_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/26/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 24450 |  |  | Well Cost($): |  | 93400
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10030 |  | 10030 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10255 |  | 10255 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 225 |  | 225 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): |  | 180 |  | 180 | [5 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): |  | 45 |  | 45 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: |  | 3.28 / 1.50 |  | 3.28 / 1.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 2.55 |  | 2.55 |  | SN: |  | 13601237 |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 0.73 |  | 0.73 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 61.36 / 70.59 |  | 61.36 / 70.59 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 11.75 |  | 11.75 |  | Grade In: |  | New
% Slide: |  | 80 |  | 80 |  | Grade Out: |  | 1-1-WT-S-X-I-
% Rotary: |  | 20 |  | 20 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Chris Day |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .005 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.15 |  | 33.9
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.65 |  | 35.55
NM Pony Drill Collar |  |  |  | 5.25 | 2.75 |  |  |  |  | 10.51 |  | 46.06
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 50.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.87
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 111.69
Tomax |  |  |  | 5.25 | 2.562 |  |  |  |  | 18.35 |  | 130.04
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 133.42
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 322.19
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 330.77
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2784.15
Agitator |  |  |  | 5.25 | 2.812 |  |  |  |  | 23.46 |  | 2807.61
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.54
Agitator- Ball Drop |  |  |  | 5.25 | 2.812 |  |  |  |  | 20.9 |  | 5943.44
5943.44
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250007 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9961 | 14.48 | 143.86 | 9752.81 | -484.81 | -1658.24 | 3.41 |  | -18.75 | -656.21 | 3.29 |  | -4.39 | 135
10124 | 20.75 | 143.45 | 9908.09 | -524.5 | -1628.99 | 3.85 |  | -1.33 | -606.95 | 3.85 |  | -0.25 | 163
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 68.53 | 21.72 | 44.67 | 306 | 383.69 | 3864.33 | 2914.25 | 0 | 250 | 158.72 | 165 | 10.92 | 0
Run | 68.53 | 21.72 | 44.67 | 306 | 383.69 | 3864.33 | 2914.25 | 0 | 250 | 158.72 | 165 | 10.92 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/26/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/26/2021 |  | 6 |  | 100 |  | 4 | 400
Job Start-Up Incidentals |  |  |  |  | 07/26/2021 |  | 1 |  | 6000 |  | 1 | 6000
5.5 Premium Motor Stator Reline |  |  |  |  | 07/26/2021 |  | 12 |  | 9000 |  | 1 | 9000
Real Time Survey Management |  |  |  |  | 07/26/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 07/26/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 24450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/26/2021 | 00:00 | 10:15 | 10.25 | 10030 | 10030 | 0 | CRV |  | 24B | Standby / Rig Skid / N/U / Test BOP
07/26/2021 | 10:15 | 12:15 | 2 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 6O | P/U BHA #4 / SPT
07/26/2021 | 12:15 | 13:35 | 1.33 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 6A | TIH T/ 2,784
07/26/2021 | 13:35 | 14:10 | 0.58 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 6A | P/U Agitator & Presure Test 2,807
07/26/2021 | 14:10 | 15:25 | 1.25 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 6A | TIH F/ 2,807 T/ 5,922
07/26/2021 | 15:25 | 15:40 | 0.25 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 6A | P/U Agitator 5,943
07/26/2021 | 15:40 | 17:30 | 1.83 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 6A | TIH F/ 5,943 T/ 9,720
07/26/2021 | 17:30 | 18:00 | 0.5 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 24A | Remove Trip Nipple & Install Rotating Head
07/26/2021 | 18:00 | 18:45 | 0.75 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 5A | Drill Cement and Float
07/26/2021 | 18:45 | 19:20 | 0.58 | 10030 | 10030 | 0 | CRV | 4: BHA 4 | 5A | Drill Shoe Track and Shoe
07/26/2021 | 19:20 | 19:30 | 0.17 | 10030 | 10041 | 11 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10030.00 t/10041.00, w/WOB 20.01,Flow 375.82, RPM 44.69, Press 3575.18, Tq 10.7, ROP 66.00, Diff 557.10, Temp 217.40
07/26/2021 | 19:30 | 20:43 | 1.22 | 10041 | 10041 | 0 | CRV | 4: BHA 4 | 15D | FIT
07/26/2021 | 20:43 | 21:51 | 1.13 | 10041 | 10080 | 39 | CRV | 4: BHA 4 | 2J | Slide Drill f/10041.00 t/10080.00, TF 5.96G, w/WOB 13.94,Flow 375.75, Press 3678.46, Tq 3, ROP 34.41, Temp 217.40
07/26/2021 | 21:51 | 21:54 | 0.05 | 10080 | 10080 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/26/2021 | 21:54 | 22:10 | 0.27 | 10080 | 10093 | 13 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10080.00 t/10093.00, w/WOB 23.55,Flow 375.82, RPM 44.7, Press 3582.42, Tq 11.25, ROP 48.75, Diff 396.19, Temp 217.40
07/26/2021 | 22:10 | 22:14 | 0.07 | 10093 | 10093 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/26/2021 | 22:14 | 23:04 | 0.83 | 10093 | 10172 | 79 | CRV | 4: BHA 4 | 2J | Slide Drill f/10093.00 t/10172.00, TF 99.47G, w/WOB 17.46,Flow 375.81, Press 3917.6, Tq 3, ROP 94.80, Diff 2184.18, Temp 219.20
07/26/2021 | 23:04 | 23:22 | 0.3 | 10172 | 10193 | 21 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10172.00 t/10193.00, w/WOB 27.54,Flow 399.47, RPM 44.62, Press 4211.65, Tq 10.8, ROP 70.00, Diff 894.90, Temp 222.80
07/26/2021 | 23:22 | 23:25 | 0.05 | 10193 | 10193 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/26/2021 | 23:25 | 24:00 | 0.58 | 10193 | 10255 | 62 | CRV | 4: BHA 4 | 2J | Slide Drill f/10193.00 t/10255.00, TF -11G, w/WOB 27.85,Flow 399.47, Press 4220.65, Tq 3.2, ROP 106.29, Diff 903.90, Temp 222.80
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_27_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/27/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 102850
|  |  |  | 24hr Summary: |  | Begin Curve
|  |  |  | 24hr Lookahead: |  | Land Curve and drill lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10255 |  | 10030 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 12267 |  | 12267 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 2012 |  | 2237 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 48
Slide Drilled (Usft): |  | 739 |  | 919 | [5 empty] | 100: | 12 | Chlorides: | 68000
Rotary Drilled (Usft): |  | 1273 |  | 1318 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.30
Drlg/Circ Hrs: |  | 20.77 / 2.42 |  | 24.05 / 3.92 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 13.27 |  | 15.82 |  | SN: |  | 13601237 |  | 10s Gel: | 11 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 7.5 |  | 8.23 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.0 / 0.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 169.73 / 55.70 |  | 160.08 / 58.10 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 35.75 |  | Grade In: |  | New
% Slide: |  | 36.73 |  | 41.08 |  | Grade Out: |  | 1-1-WT-S-X-I-
% Rotary: |  | 63.27 |  | 58.92 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Chris Day |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .005 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.15 |  | 33.9
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.65 |  | 35.55
NM Pony Drill Collar |  |  |  | 5.25 | 2.75 |  |  |  |  | 10.51 |  | 46.06
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 50.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.87
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 111.69
Tomax |  |  |  | 5.25 | 2.562 |  |  |  |  | 18.35 |  | 130.04
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 133.42
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 322.19
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 330.77
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2784.15
Agitator |  |  |  | 5.25 | 2.812 |  |  |  |  | 23.46 |  | 2807.61
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.54
Agitator- Ball Drop |  |  |  | 5.25 | 2.812 |  |  |  |  | 20.9 |  | 5943.44
5943.44
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250007 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10219 | 27.56 | 142.72 | 9994.72 | -555.54 | -1605.63 | 7.18 |  | -2.85 | -568.11 | 7.17 |  | -0.77 | 95
10314 | 35.39 | 139.67 | 10075.68 | -594.06 | -1574.47 | 8.41 |  | -12.81 | -518.56 | 8.24 |  | -3.21 | 95
10408 | 45.6 | 142.05 | 10147.08 | -641.42 | -1536.09 | 10.98 |  | 9.53 | -457.61 | 10.86 |  | 2.53 | 94
10502 | 56.34 | 136.52 | 10206.21 | -696.47 | -1488.36 | 12.3 |  | -23.59 | -384.81 | 11.43 |  | -5.88 | 94
10597 | 61.37 | 137.15 | 10255.33 | -755.77 | -1432.77 | 5.33 |  | 6.28 | -303.78 | 5.29 |  | 0.66 | 95
10691 | 69.86 | 143.09 | 10294.14 | -821.46 | -1378.07 | 10.71 |  | 33.78 | -218.32 | 9.03 |  | 6.32 | 94
10785 | 78.82 | 139.58 | 10319.49 | -892.01 | -1321.54 | 10.19 |  | -21.17 | -127.91 | 9.53 |  | -3.73 | 94
10879 | 90.51 | 138.15 | 10328.22 | -962.37 | -1260.07 | 12.53 |  | -7.02 | -34.58 | 12.44 |  | -1.52 | 94
10974 | 89.54 | 140.19 | 10328.17 | -1034.25 | -1197.97 | 2.38 |  | 115.43 | 60.35 | -1.02 |  | 2.15 | 95
11068 | 89.41 | 140.88 | 10329.03 | -1106.81 | -1138.22 | 0.75 |  | 100.67 | 154.33 | -0.14 |  | 0.73 | 94
11163 | 82.7 | 139.4 | 10335.57 | -1179.52 | -1077.52 | 7.23 |  | -167.63 | 249.03 | -7.06 |  | -1.56 | 95
11257 | 82.99 | 140.07 | 10347.28 | -1250.69 | -1017.24 | 0.77 |  | 66.47 | 342.26 | 0.31 |  | 0.71 | 94
11351 | 86.96 | 140.73 | 10355.51 | -1322.83 | -957.56 | 4.28 |  | 9.43 | 435.86 | 4.22 |  | 0.7 | 94
11446 | 87.51 | 153.79 | 10360.11 | -1402.47 | -906.36 | 13.74 |  | 87.91 | 530.05 | 0.58 |  | 13.75 | 95
11540 | 86.91 | 139.19 | 10364.71 | -1480.54 | -854.67 | 15.53 |  | -92.7 | 623.31 | -0.64 |  | -15.53 | 94
11634 | 88.78 | 140.55 | 10368.25 | -1552.36 | -794.13 | 2.46 |  | 36.04 | 717.2 | 1.99 |  | 1.45 | 94
11730 | 89.9 | 140.19 | 10369.35 | -1626.29 | -732.9 | 1.23 |  | -17.82 | 813.18 | 1.17 |  | -0.38 | 96
11824 | 88.97 | 140.59 | 10370.28 | -1698.7 | -672.98 | 1.08 |  | 156.73 | 907.16 | -0.99 |  | 0.43 | 94
11916 | 90.59 | 141.16 | 10370.63 | -1770.07 | -614.93 | 1.87 |  | 19.39 | 999.15 | 1.76 |  | 0.62 | 92
12010 | 89.82 | 141.87 | 10370.29 | -1843.65 | -556.43 | 1.11 |  | 137.32 | 1093.15 | -0.82 |  | 0.76 | 94
12105 | 86.86 | 140.87 | 10373.05 | -1917.82 | -497.16 | 3.29 |  | -161.35 | 1188.1 | -3.12 |  | -1.05 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 96.89 | 29.94 | 72.93 | 345 | 399.45 | 4213.62 | 3752.41 | 0 | 249.02 | 164.68 | 155.88 | 12136.95 | 0
Run | 93.01 | 29.07 | 70.36 | 341 | 397.79 | 4176.85 | 3677.57 | 0 | 249.12 | 164.06 | 156.84 | 11034.59 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/27/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/27/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 07/27/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 07/27/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/27/2021 | 00:00 | 00:20 | 0.33 | 10255 | 10275 | 20 | CRV | 4: BHA 4 | 2J | Slide Drill f/10255.00 t/10275.00, TF -7.29G, w/WOB 17.31,Flow 399.36, Press 4228.44, Tq 3.2, ROP 60.00, Diff 911.69, Temp 222.80
07/27/2021 | 00:20 | 00:24 | 0.07 | 10275 | 10288 | 13 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10275.00 t/10288.00, w/WOB 22.53,Flow 399.47, RPM 44.71, Press 4200, Tq 11.6, ROP 195.00, Diff 626.37, Temp 224.60
07/27/2021 | 00:24 | 00:27 | 0.05 | 10288 | 10288 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 00:27 | 01:38 | 1.18 | 10288 | 10383 | 95 | CRV | 4: BHA 4 | 2J | Slide Drill f/10288.00 t/10383.00, TF -15G, w/WOB 11.68,Flow 399.42, Press 4087.28, Tq 3.2, ROP 80.28, Diff 185.38, Temp 228.20
07/27/2021 | 01:38 | 01:41 | 0.05 | 10383 | 10383 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 01:41 | 02:40 | 0.98 | 10383 | 10477 | 94 | CRV | 4: BHA 4 | 2J | Slide Drill f/10383.00 t/10477.00, TF -10G, w/WOB 19.99,Flow 399.52, Press 3848.89, Tq 3.2, ROP 95.59, Diff 82.06, Temp 230.00
07/27/2021 | 02:40 | 02:43 | 0.05 | 10477 | 10477 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 02:43 | 03:20 | 0.62 | 10477 | 10522 | 45 | CRV | 4: BHA 4 | 2J | Slide Drill f/10477.00 t/10522.00, TF 20G, w/WOB 25.79,Flow 399.45, Press 4037.65, Tq 4.5, ROP 72.97, Diff 287.65, Temp 230.00
07/27/2021 | 03:20 | 03:31 | 0.18 | 10522 | 10532 | 10 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10522.00 t/10532.00, w/WOB 25.79,Flow 399.45, RPM 45, Press 4200, Tq 13.5, ROP 54.55, Diff 450.00, Temp 232.00
07/27/2021 | 03:31 | 03:36 | 0.08 | 10532 | 10532 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 03:36 | 03:55 | 0.32 | 10532 | 10552 | 20 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10532.00 t/10552.00, w/WOB 25.79,Flow 399.45, RPM 45, Press 4200, Tq 13.5, ROP 63.16, Diff 450.00, Temp 232.00
07/27/2021 | 03:55 | 04:17 | 0.37 | 10552 | 10571 | 19 | CRV | 4: BHA 4 | 2J | Slide Drill f/10552.00 t/10571.00, TF 20G, w/WOB 25.79,Flow 399.45, Press 4037.65, Tq 4.5, ROP 51.82, Diff 287.65, Temp 232.00
07/27/2021 | 04:17 | 04:20 | 0.05 | 10571 | 10571 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 04:20 | 05:10 | 0.83 | 10571 | 10648 | 77 | CRV | 4: BHA 4 | 2J | Slide Drill f/10571.00 t/10648.00, TF 30G, w/WOB 25.79,Flow 399.45, Press 4037.65, Tq 4.5, ROP 92.40, Diff 287.65, Temp 234.00
07/27/2021 | 05:10 | 05:27 | 0.28 | 10648 | 10666 | 18 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10648.00 t/10666.00, w/WOB 32,Flow 399.45, RPM 45, Press 4200, Tq 13.5, ROP 63.53, Diff 450.00, Temp 234.00
07/27/2021 | 05:27 | 05:30 | 0.05 | 10666 | 10666 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 05:30 | 07:00 | 1.5 | 10666 | 10760 | 94 | CRV | 4: BHA 4 | 2J | Slide Drill f/10666.00 t/10760.00, TF 0G, w/WOB 25,Flow 399.45, Press 4200, Tq 3.8, ROP 62.67, Diff 450.00, Temp 237.00
07/27/2021 | 07:00 | 07:10 | 0.17 | 10760 | 10760 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 07:10 | 08:58 | 1.8 | 10760 | 10822 | 62 | CRV | 4: BHA 4 | 2J | Slide Drill f/10760.00 t/10822.00, TF 0G, w/WOB 25,Flow 399.45, Press 4200, Tq 3.8, ROP 34.44, Diff 450.00, Temp 237.00
07/27/2021 | 08:58 | 09:00 | 0.03 | 10822 | 10822 | 0 | CRV | 4: BHA 4 | 5A | Check Shot
07/27/2021 | 09:00 | 09:46 | 0.77 | 10822 | 10854 | 32 | CRV | 4: BHA 4 | 2J | Slide Drill f/10822.00 t/10854.00, TF 0G, w/WOB 25,Flow 399.45, Press 4200, Tq 3.8, ROP 41.74, Diff 450.00, Temp 237.00
07/27/2021 | 09:46 | 10:00 | 0.23 | 10854 | 10854 | 0 | CRV | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 10:00 | 10:30 | 0.5 | 10854 | 10869 | 15 | CRV | 4: BHA 4 | 2J | Slide Drill f/10854.00 t/10869.00, TF 0G, w/WOB 25,Flow 399.45, Press 4200, Tq 3.8, ROP 30.00, Diff 450.00, Temp 237.00
07/27/2021 | 10:30 | 11:00 | 0.5 | 10869 | 10948 | 79 | LAT | 4: BHA 4 | 2K | Rotary Drill f/10869.00 t/10948.00, w/WOB 27.00,Flow 399.45, RPM 45.00, Press 4200.00, Tq 15000.00, ROP 158.00, Diff 450.00, Temp 237.00
07/27/2021 | 11:00 | 11:07 | 0.12 | 10948 | 10948 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 11:07 | 11:13 | 0.1 | 10948 | 10958 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/10948.00 t/10958.00, w/WOB 25.00,Flow 399.45, RPM 45.00, Press 4200.00, Tq 15000.00, ROP 100.00, Diff 450.00, Temp 237.00
07/27/2021 | 11:13 | 11:38 | 0.42 | 10958 | 10978 | 20 | LAT | 4: BHA 4 | 2J | Slide Drill f/10958.00 t/10978.00, TF 140G, w/WOB 25.00,Flow 399.45, Press 4200.00, Tq 15000.00, ROP 48.00, Diff 450.00, Temp 237.00
07/27/2021 | 11:38 | 11:53 | 0.25 | 10978 | 11043 | 65 | LAT | 4: BHA 4 | 2K | Rotary Drill f/10978.00 t/11043.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 18000.00, ROP 260.00, Diff 450.00, Temp 237.00
07/27/2021 | 11:53 | 11:58 | 0.08 | 11043 | 11043 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 11:58 | 12:04 | 0.1 | 11043 | 11053 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11043.00 t/11053.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 18000.00, ROP 100.00, Diff 450.00, Temp 237.00
07/27/2021 | 12:04 | 12:42 | 0.63 | 11053 | 11065 | 12 | LAT | 4: BHA 4 | 2J | Slide Drill f/11053.00 t/11065.00, TF 180.00G, w/WOB 27.00,Flow 399.45, Press 4200.00, Tq 18000.00, ROP 18.95, Diff 450.00, Temp 237.00
07/27/2021 | 12:42 | 12:55 | 0.22 | 11065 | 11085 | 20 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11065.00 t/11085.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 18000.00, ROP 92.31, Diff 450.00, Temp 237.00
07/27/2021 | 12:55 | 13:50 | 0.92 | 11085 | 11110 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/11085.00 t/11110.00, TF 180.00G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 0, ROP 27.27, Diff 450.00, Temp 237.00
07/27/2021 | 13:50 | 13:57 | 0.12 | 11110 | 11137 | 27 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11110.00 t/11137.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 18000.00, ROP 231.43, Diff 450.00, Temp 237.00
07/27/2021 | 13:57 | 14:00 | 0.05 | 11137 | 11137 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 14:00 | 14:10 | 0.17 | 11137 | 11147 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11137.00 t/11147.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 18000.00, ROP 60.00, Diff 450.00, Temp 237.00
07/27/2021 | 14:10 | 14:30 | 0.33 | 11147 | 11162 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/11147.00 t/11162.00, TF 170G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 0, ROP 45.00, Diff 450.00, Temp 237.00
07/27/2021 | 14:30 | 14:44 | 0.23 | 11162 | 11232 | 70 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11162.00 t/11232.00, w/WOB 35.00,Flow 399.45, RPM 80, Press 4200.00, Tq 18000, ROP 300.00, Diff 450.00, Temp 237.00
07/27/2021 | 14:44 | 14:50 | 0.1 | 11232 | 11232 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 14:50 | 14:55 | 0.08 | 11232 | 11242 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11232.00 t/11242.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 18000.00, ROP 120.00, Diff 450.00, Temp 237.00
07/27/2021 | 14:55 | 15:12 | 0.28 | 11242 | 11242 | 0 | LAT | 4: BHA 4 | 5A | Reshoot Survey
07/27/2021 | 15:12 | 15:25 | 0.22 | 11242 | 11262 | 20 | LAT | 4: BHA 4 | 2J | Slide Drill f/11242.00 t/11262.00, TF 0G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 0, ROP 92.31, Diff 450.00, Temp 237.00
07/27/2021 | 15:25 | 15:44 | 0.32 | 11262 | 11326 | 64 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11262.00 t/11326.00, w/WOB 35.00,Flow 399.45, RPM 80, Press 4200.00, Tq 16000, ROP 202.11, Diff 450.00, Temp 237.00
07/27/2021 | 15:44 | 15:52 | 0.13 | 11326 | 11326 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 15:52 | 16:10 | 0.3 | 11326 | 11344 | 18 | LAT | 4: BHA 4 | 2J | Slide Drill f/11326.00 t/11344.00, TF 0G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 0, ROP 60.00, Diff 450.00, Temp 237.00
07/27/2021 | 16:10 | 16:29 | 0.32 | 11344 | 11420 | 76 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11344.00 t/11420.00, w/WOB 35.00,Flow 399.45, RPM 80, Press 4200.00, Tq 16000, ROP 240.00, Diff 450.00, Temp 237.00
07/27/2021 | 16:29 | 17:10 | 0.68 | 11420 | 11420 | 0 | LAT | 4: BHA 4 | 8P | Rig Service
07/27/2021 | 17:10 | 17:18 | 0.13 | 11420 | 11420 | 0 | LAT | 4: BHA 4 | 10D | Survey & Connection
07/27/2021 | 17:18 | 17:35 | 0.28 | 11420 | 11515 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11420.00 t/11515.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 335.29, Diff 450.00, Temp 237.00
07/27/2021 | 17:35 | 17:52 | 0.28 | 11515 | 11515 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 17:52 | 18:00 | 0.13 | 11515 | 11525 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11515.00 t/11525.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 75.00, Diff 450.00, Temp 237.00
07/27/2021 | 18:00 | 18:05 | 0.08 | 11525 | 11525 | 0 | LAT | 4: BHA 4 | 5A | Reshoot SVY
07/27/2021 | 18:05 | 18:40 | 0.58 | 11525 | 11550 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/11525.00 t/11550.00, TF -90.00G, w/WOB 35.00,Flow 399.45, Press 4150.00, Tq 7500.00, ROP 42.86, Diff 400.00, Temp 237.00
07/27/2021 | 18:40 | 18:57 | 0.28 | 11550 | 11575 | 25 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11550.00 t/11575.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 88.24, Diff 450.00, Temp 237.00
07/27/2021 | 18:57 | 19:00 | 0.05 | 11575 | 11575 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 19:00 | 19:18 | 0.3 | 11575 | 11609 | 34 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11575.00 t/11609.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 113.33, Diff 450.00, Temp 237.00
07/27/2021 | 19:18 | 19:21 | 0.05 | 11609 | 11609 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 19:21 | 19:25 | 0.07 | 11609 | 11619 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11609.00 t/11619.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 150.00, Diff 450.00, Temp 237.00
07/27/2021 | 19:25 | 19:37 | 0.2 | 11619 | 11631 | 12 | LAT | 4: BHA 4 | 2J | Slide Drill f/11619.00 t/11631.00, TF 20.00G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 7500.00, ROP 60.00, Diff 450.00, Temp 237.00
07/27/2021 | 19:37 | 20:01 | 0.4 | 11631 | 11703 | 72 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11631.00 t/11703.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 180.00, Diff 450.00, Temp 237.00
07/27/2021 | 20:01 | 20:04 | 0.05 | 11703 | 11703 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 20:04 | 20:38 | 0.57 | 11703 | 11799 | 96 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11703.00 t/11799.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 169.41, Diff 450.00, Temp 237.00
07/27/2021 | 20:38 | 20:40 | 0.03 | 11799 | 11799 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 20:40 | 20:45 | 0.08 | 11799 | 11814 | 15 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11799.00 t/11814.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 180.00, Diff 450.00, Temp 237.00
07/27/2021 | 20:45 | 20:55 | 0.17 | 11814 | 11822 | 8 | LAT | 4: BHA 4 | 2J | Slide Drill f/11814.00 t/11822.00, TF 0.00G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 7500.00, ROP 48.00, Diff 450.00, Temp 237.00
07/27/2021 | 20:55 | 21:13 | 0.3 | 11822 | 11893 | 71 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11822.00 t/11893.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 236.67, Diff 450.00, Temp 237.00
07/27/2021 | 21:13 | 21:16 | 0.05 | 11893 | 11893 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 21:16 | 21:37 | 0.35 | 11893 | 11985 | 92 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11893.00 t/11985.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4200.00, Tq 16000.00, ROP 262.86, Diff 450.00, Temp 237.00
07/27/2021 | 21:37 | 21:40 | 0.05 | 11985 | 11985 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 21:40 | 21:50 | 0.17 | 11985 | 11990 | 5 | LAT | 4: BHA 4 | 2K | Rotary Drill f/11985.00 t/11990.00, w/WOB 35.00,Flow 399.45, RPM 80.00, Press 4750.00, Tq 16000.00, ROP 30.00, Diff 1000.00, Temp 262.00
07/27/2021 | 21:50 | 22:08 | 0.3 | 11990 | 12005 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/11990.00 t/12005.00, TF -170.00G, w/WOB 35.00,Flow 399.45, Press 4200.00, Tq 755.00, ROP 50.00, Diff 450.00, Temp 262.00
07/27/2021 | 22:08 | 22:30 | 0.37 | 12005 | 12079 | 74 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12005.00 t/12079.00, w/WOB 22.33,Flow 399.51, RPM 79.56, Press 4547.19, Tq 13.99, ROP 201.82, Diff 641.42, Temp 264.20
07/27/2021 | 22:30 | 22:37 | 0.12 | 12079 | 12079 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 22:37 | 22:48 | 0.18 | 12079 | 12085 | 6 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12079.00 t/12085.00, w/WOB 16.05,Flow 399.44, RPM 79.55, Press 3861.53, Tq 12.00, ROP 32.73, Diff 43.60, Temp 266.00
07/27/2021 | 22:48 | 23:07 | 0.32 | 12085 | 12101 | 16 | LAT | 4: BHA 4 | 2J | Slide Drill f/12085.00 t/12101.00, TF -156G, w/WOB 14.63,Flow 399.52, Press 4289.29, Tq 13.03, ROP 50.53, Diff 376.42, Temp 262.40
07/27/2021 | 23:07 | 23:20 | 0.22 | 12101 | 12174 | 73 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12101.00 t/12174.00, w/WOB 27.68,Flow 399.47, RPM 79.56, Press 4651.04, Tq 15.37, ROP 336.92, Diff 601.32, Temp 264.20
07/27/2021 | 23:20 | 23:27 | 0.12 | 12174 | 12174 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/27/2021 | 23:27 | 24:00 | 0.55 | 12174 | 12267 | 93 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12174.00 t/12267.00, w/WOB 29.55,Flow 399.46, RPM 79.56, Press 4767.93, Tq 15.11, ROP 169.09, Diff 1140.53, Temp 266.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_28_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 112300
|  |  |  | 24hr Summary: |  | Land Curve and drill lateral
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12267 |  | 10030 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 39 | PV: | 15
End Depth (Usft): |  | 14456 |  | 14456 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): |  | 2189 |  | 4426 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 516 |  | 1435 | [5 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): |  | 1673 |  | 2991 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 19.67 / 3.58 |  | 43.72 / 7.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: |  | 11.55 |  | 27.37 |  | SN: |  | 13601237 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 8.12 |  | 16.35 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.0 / 170.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 206.12 / 44.68 |  | 182.94 / 52.44 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 59.75 |  | Grade In: |  | New
% Slide: |  | 23.57 |  | 32.42 |  | Grade Out: |  | 1-1-WT-S-X-I-
% Rotary: |  | 76.43 |  | 67.58 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Chris Day |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .005 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.15 |  | 33.9
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.65 |  | 35.55
NM Pony Drill Collar |  |  |  | 5.25 | 2.75 |  |  |  |  | 10.51 |  | 46.06
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 50.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.87
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 111.69
Tomax |  |  |  | 5.25 | 2.562 |  |  |  |  | 18.35 |  | 130.04
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 133.42
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 322.19
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 330.77
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2784.15
Agitator |  |  |  | 5.25 | 2.812 |  |  |  |  | 23.46 |  | 2807.61
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.54
Agitator- Ball Drop |  |  |  | 5.25 | 2.812 |  |  |  |  | 20.9 |  | 5943.44
5943.44
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250007 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12199 | 87.56 | 141.6 | 10377.62 | -1991.03 | -438.37 | 1.08 |  | 46.19 | 1281.99 | 0.74 |  | 0.78 | 94
12294 | 85.94 | 140.92 | 10383.01 | -2065.01 | -379.02 | 1.85 |  | -157.28 | 1376.83 | -1.71 |  | -0.72 | 95
12388 | 84.67 | 140.85 | 10390.7 | -2137.69 | -319.92 | 1.35 |  | -176.86 | 1470.51 | -1.35 |  | -0.07 | 94
12482 | 83.24 | 140.81 | 10400.6 | -2210.16 | -260.88 | 1.52 |  | -178.41 | 1563.98 | -1.52 |  | -0.04 | 94
12576 | 83.82 | 141.57 | 10411.19 | -2282.94 | -202.34 | 1.01 |  | 52.52 | 1657.38 | 0.62 |  | 0.81 | 94
12670 | 87.28 | 140.87 | 10418.49 | -2355.99 | -143.65 | 3.75 |  | -11.43 | 1751.08 | 3.68 |  | -0.74 | 94
12764 | 89.08 | 140.62 | 10421.47 | -2428.73 | -84.2 | 1.93 |  | -7.91 | 1845.02 | 1.91 |  | -0.27 | 94
12858 | 89.2 | 141.45 | 10422.88 | -2501.81 | -25.1 | 0.89 |  | 81.78 | 1939.01 | 0.13 |  | 0.88 | 94
12953 | 88.41 | 140.6 | 10424.86 | -2575.65 | 34.64 | 1.22 |  | -132.92 | 2033.99 | -0.83 |  | -0.89 | 95
13047 | 86.54 | 139.92 | 10429 | -2647.86 | 94.68 | 2.12 |  | -160.05 | 2127.87 | -1.99 |  | -0.72 | 94
13141 | 88.76 | 141.79 | 10432.86 | -2720.69 | 153.96 | 3.09 |  | 40.13 | 2221.78 | 2.36 |  | 1.99 | 94
13236 | 86.61 | 140.79 | 10436.7 | -2794.76 | 213.32 | 2.5 |  | -155.09 | 2316.69 | -2.26 |  | -1.05 | 95
13330 | 87.54 | 145.05 | 10441.49 | -2869.64 | 269.9 | 4.63 |  | 77.78 | 2410.51 | 0.99 |  | 4.53 | 94
13425 | 86.73 | 152.07 | 10446.25 | -2950.53 | 319.36 | 7.43 |  | 96.76 | 2504.59 | -0.85 |  | 7.39 | 95
13519 | 87.83 | 148.95 | 10450.71 | -3032.25 | 365.58 | 3.52 |  | -70.64 | 2597.28 | 1.17 |  | -3.32 | 94
13613 | 87.95 | 152.83 | 10454.17 | -3114.31 | 411.27 | 4.13 |  | 88.3 | 2689.91 | 0.13 |  | 4.13 | 94
13706 | 87.52 | 154.69 | 10457.85 | -3197.65 | 452.35 | 2.05 |  | 103.06 | 2780.67 | -0.46 |  | 2 | 93
13801 | 87.86 | 157.38 | 10461.68 | -3284.39 | 490.91 | 2.85 |  | 82.85 | 2872.5 | 0.36 |  | 2.83 | 95
13896 | 87.14 | 153.54 | 10465.82 | -3370.71 | 530.32 | 4.11 |  | -100.71 | 2964.54 | -0.76 |  | -4.04 | 95
13989 | 87.38 | 145.88 | 10470.28 | -3450.86 | 577.14 | 8.23 |  | -88.39 | 3056.38 | 0.26 |  | -8.24 | 93
14083 | 87.35 | 148.95 | 10474.6 | -3529.97 | 627.7 | 3.26 |  | 90.63 | 3149.75 | -0.03 |  | 3.27 | 94
14178 | 87.3 | 138.23 | 10479.05 | -3606.23 | 683.94 | 11.27 |  | -90.52 | 3244.44 | -0.05 |  | -11.28 | 95
14272 | 86.8 | 136.62 | 10483.88 | -3675.36 | 747.45 | 1.79 |  | -107.31 | 3338.09 | -0.53 |  | -1.71 | 94
14367 | 89.67 | 129.29 | 10486.81 | -3740.01 | 816.9 | 8.28 |  | -68.75 | 3431.94 | 3.02 |  | -7.72 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 111.31 | 32.31 | 79.27 | 351 | 399.46 | 4452.52 | 3645.29 | 0 | 238.29 | 185 | 151.34 | 15.51 | 0
Run | 101.24 | 30.43 | 74.45 | 345 | 398.49 | 4292.18 | 3663.93 | 0 | 244.59 | 172.82 | 154.54 | 5976.65 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/28/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/28/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 07/28/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 07/28/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/28/2021 | 00:00 | 00:11 | 0.18 | 12267 | 12274 | 7 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12267.00 t/12274.00, w/WOB 16.51,Flow 399.47, RPM 79.57, Press 3876.53, Tq 11.61, ROP 38.18
07/28/2021 | 00:11 | 00:12 | 0.02 | 12274 | 12274 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 00:12 | 00:28 | 0.27 | 12274 | 12287 | 13 | LAT | 4: BHA 4 | 2J | Slide Drill f/12274.00 t/12287.00, TF -164G, w/WOB 17.26,Flow 399.38, Press 4347.32, Tq 13.10, ROP 48.75, Diff 445.08, Temp 264.20
07/28/2021 | 00:28 | 00:42 | 0.23 | 12287 | 12363 | 76 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12287.00 t/12363.00, w/WOB 33.19,Flow 399.48, RPM 79.55, Press 4750.25, Tq 16.71, ROP 325.71, Diff 258.91, Temp 266.00
07/28/2021 | 00:42 | 00:48 | 0.1 | 12363 | 12363 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 00:48 | 01:03 | 0.25 | 12363 | 12380 | 17 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12363.00 t/12380.00, w/WOB 30.42,Flow 399.41, RPM 79.54, Press 3917.72, Tq 12.69, ROP 68.00, Diff 15.26, Temp 267.80
07/28/2021 | 01:03 | 01:11 | 0.13 | 12380 | 12388 | 8 | LAT | 4: BHA 4 | 2J | Slide Drill f/12380.00 t/12388.00, TF -160.38G, w/WOB 40.80,Flow 399.42, Press 3979.46, Tq 12.69, ROP 60.00, Diff -33.38, Temp 266.00
07/28/2021 | 01:11 | 01:28 | 0.28 | 12388 | 12457 | 69 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12388.00 t/12457.00, w/WOB 27.60,Flow 399.48, RPM 71.55, Press 4622.95, Tq 15.63, ROP 243.53, Diff 1026.58, Temp 266.00
07/28/2021 | 01:28 | 01:33 | 0.08 | 12457 | 12457 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 01:33 | 01:53 | 0.33 | 12457 | 12551 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12457.00 t/12551.00, w/WOB 29.22,Flow 399.51, RPM 79.56, Press 4693.94, Tq 15.80, ROP 282.00, Diff 1097.57, Temp 269.60
07/28/2021 | 01:53 | 01:58 | 0.08 | 12551 | 12551 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 01:58 | 02:12 | 0.23 | 12551 | 12565 | 14 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12551.00 t/12565.00, w/WOB 18.74,Flow 399.44, RPM 79.57, Press 3876.99, Tq 12.83, ROP 60.00, Diff 280.62, Temp 271.40
07/28/2021 | 02:12 | 02:45 | 0.55 | 12565 | 12590 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/12565.00 t/12590.00, TF 20G, w/WOB 19.44,Flow 399.44, Press 4354.19, Tq 14.88, ROP 45.45, Diff 529.38, Temp 266.00
07/28/2021 | 02:45 | 02:52 | 0.12 | 12590 | 12590 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 02:52 | 02:58 | 0.1 | 12590 | 12645 | 55 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12590.00 t/12645.00, w/WOB 26.63,Flow 399.46, RPM 79.55, Press 4600.34, Tq 16.17, ROP 550.00, Diff 1003.97, Temp 266.00
07/28/2021 | 02:58 | 03:06 | 0.13 | 12645 | 12645 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 03:06 | 03:24 | 0.3 | 12645 | 12660 | 15 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12645.00 t/12660.00, w/WOB 17.18,Flow 399.39, RPM 79.57, Press 3806.15, Tq 13.94, ROP 50.00, Diff 209.78, Temp 267.80
07/28/2021 | 03:24 | 03:45 | 0.35 | 12660 | 12676 | 16 | LAT | 4: BHA 4 | 2J | Slide Drill f/12660.00 t/12676.00, TF -8.11G, w/WOB 16.15,Flow 399.39, Press 4226.71, Tq 13.90, ROP 45.71, Diff 630.34, Temp 266.00
07/28/2021 | 03:45 | 03:59 | 0.23 | 12676 | 12739 | 63 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12676.00 t/12739.00, w/WOB 37.22,Flow 399.42, RPM 79.55, Press 4820.56, Tq 19.21, ROP 270.00, Diff 470.95, Temp 267.80
07/28/2021 | 03:59 | 04:05 | 0.1 | 12739 | 12739 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 04:05 | 04:27 | 0.37 | 12739 | 12833 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12739.00 t/12833.00, w/WOB 23.82,Flow 399.48, RPM 79.57, Press 4523.01, Tq 15.56, ROP 256.36, Diff 427.70, Temp 273.20
07/28/2021 | 04:27 | 04:33 | 0.1 | 12833 | 12833 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 04:33 | 04:43 | 0.17 | 12833 | 12840 | 7 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12833.00 t/12840.00, w/WOB 18.99,Flow 399.41, RPM 79.57, Press 4523.01, Tq 12.27, ROP 42.00, Diff 652.32, Temp 273.20
07/28/2021 | 04:43 | 04:58 | 0.25 | 12840 | 12850 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/12840.00 t/12850.00, TF 165G, w/WOB 19.74,Flow 399.32, Press 4331.29, Tq 14.78, ROP 40.00, Diff 462.17, Temp 271.40
07/28/2021 | 04:58 | 05:12 | 0.23 | 12850 | 12927 | 77 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12850.00 t/12927.00, w/WOB 17.45,Flow 399.33, RPM 79.55, Press 4523.01, Tq 15.49, ROP 330.00, Diff 732.19, Temp 273.20
07/28/2021 | 05:12 | 05:15 | 0.05 | 12927 | 12927 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 05:15 | 05:27 | 0.2 | 12927 | 12940 | 13 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12927.00 t/12940.00, w/WOB ,Flow , RPM , Press 4523.01, Tq , ROP 65.00, Diff 732.19
07/28/2021 | 05:27 | 05:45 | 0.3 | 12940 | 12955 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/12940.00 t/12955.00, TF -160G, w/WOB 16.95,Flow 399.55, Press 3917.72, Tq 15.49, ROP 50.00, Diff 23.42, Temp 271.40
07/28/2021 | 05:45 | 06:05 | 0.33 | 12955 | 13022 | 67 | LAT | 4: BHA 4 | 2K | Rotary Drill f/12955.00 t/12979.14, w/WOB 23.30,Flow 399.45, RPM 79.56, Press 4454.83, Tq 16.39, ROP 131.67, Diff 560.53, Temp 271.40
07/28/2021 | 06:05 | 06:12 | 0.12 | 13022 | 13022 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 06:12 | 06:20 | 0.13 | 13022 | 13032 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13022.00 t/13032.00, w/WOB 51.57,Flow 399.45, RPM 79.33, Press 3823.01, Tq 0.90, ROP 75.00, Diff 129.80, Temp 271.40
07/28/2021 | 06:20 | 06:45 | 0.42 | 13032 | 13042 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/13032.00 t/13042.00, TF 180G, w/WOB 37.58,Flow 399.53, Press 4664.47, Tq 19.55, ROP 24.00, Diff 1259.21, Temp 273.20
07/28/2021 | 06:45 | 07:02 | 0.28 | 13042 | 13116 | 74 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13042.00 t/13116.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 261.18, Diff 1184.59, Temp 276.80
07/28/2021 | 07:02 | 07:09 | 0.12 | 13116 | 13116 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 07:09 | 07:26 | 0.28 | 13116 | 13210 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13116.00 t/13210.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 331.76, Diff 1184.59, Temp 276.80
07/28/2021 | 07:26 | 07:30 | 0.07 | 13210 | 13210 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 07:30 | 07:35 | 0.08 | 13210 | 13220 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13210.00 t/13220.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 120.00, Diff 1184.59, Temp 276.80
07/28/2021 | 07:35 | 07:54 | 0.32 | 13220 | 13235 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/13220.00 t/13235.00, TF G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 47.37, Diff 1184.59, Temp 276.80
07/28/2021 | 07:54 | 08:08 | 0.23 | 13235 | 13305 | 70 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13235.00 t/13305.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 300.00, Diff 1184.59, Temp 276.80
07/28/2021 | 08:08 | 08:12 | 0.07 | 13305 | 13305 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 08:12 | 08:29 | 0.28 | 13305 | 13399 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13305.00 t/13399.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 331.76, Diff 1184.59, Temp 276.80
07/28/2021 | 08:29 | 08:34 | 0.08 | 13399 | 13399 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 08:34 | 08:45 | 0.18 | 13399 | 13409 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13399.00 t/13409.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 54.55, Diff 1184.59, Temp 276.80
07/28/2021 | 08:45 | 08:56 | 0.18 | 13409 | 13424 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/13409.00 t/13424.00, TF 120G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 81.82, Diff 1184.59, Temp 276.80
07/28/2021 | 08:56 | 09:12 | 0.27 | 13424 | 13424 | 0 | LAT | 4: BHA 4 | 8L | Replace 2 Valve On Stand Pipe
07/28/2021 | 09:12 | 09:24 | 0.2 | 13424 | 13494 | 70 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13424.00 t/13494.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 350.00, Diff 1184.59, Temp 276.80
07/28/2021 | 09:24 | 09:30 | 0.1 | 13494 | 13494 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 09:30 | 09:34 | 0.07 | 13494 | 13498 | 4 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13494.00 t/13498.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 60.00, Diff 1184.59, Temp 276.80
07/28/2021 | 09:34 | 10:00 | 0.43 | 13498 | 13528 | 30 | LAT | 4: BHA 4 | 2J | Slide Drill f/13498.00 t/13528.00, TF -90G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 69.23, Diff 1184.59, Temp 276.80
07/28/2021 | 10:00 | 10:15 | 0.25 | 13528 | 13588 | 60 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13528.00 t/13588.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 240.00, Diff 1184.59, Temp 276.80
07/28/2021 | 10:15 | 10:20 | 0.08 | 13588 | 13588 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 10:20 | 10:35 | 0.25 | 13588 | 13682 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13588.00 t/13682.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 376.00, Diff 1184.59, Temp 276.80
07/28/2021 | 10:35 | 10:40 | 0.08 | 13682 | 13682 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 10:40 | 10:52 | 0.2 | 13682 | 13682 | 0 | LAT | 4: BHA 4 | 23E | Talking To Engineer About Hole
07/28/2021 | 10:52 | 11:18 | 0.43 | 13682 | 13712 | 30 | LAT | 4: BHA 4 | 2J | Slide Drill f/13682.00 t/13712.00, TF -90.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 69.23, Diff 1184.59, Temp 276.80
07/28/2021 | 11:18 | 11:33 | 0.25 | 13712 | 13775 | 63 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13712.00 t/13775.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 252.00, Diff 1184.59, Temp 276.80
07/28/2021 | 11:33 | 11:38 | 0.08 | 13775 | 13775 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 11:38 | 11:45 | 0.12 | 13775 | 13775 | 0 | LAT | 4: BHA 4 | 23E | Talking To Engineer About Hole
07/28/2021 | 11:45 | 12:28 | 0.72 | 13775 | 13815 | 40 | LAT | 4: BHA 4 | 2J | Slide Drill f/13775.00 t/13815.00, TF -90G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 55.81, Diff 1184.59, Temp 276.80
07/28/2021 | 12:28 | 12:45 | 0.28 | 13815 | 13870 | 55 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13815.00 t/13870.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 194.12, Diff 1184.59, Temp 276.80
07/28/2021 | 12:45 | 12:50 | 0.08 | 13870 | 13870 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 12:50 | 13:00 | 0.17 | 13870 | 13870 | 0 | LAT | 4: BHA 4 | 23E | Talking To Engineer About Hole
07/28/2021 | 13:00 | 14:04 | 1.07 | 13870 | 13965 | 95 | LAT | 4: BHA 4 | 2J | Slide Drill f/13870.00 t/13965.00, TF -90.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 89.06, Diff 1184.59, Temp 276.80
07/28/2021 | 14:04 | 14:07 | 0.05 | 13965 | 13965 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 14:07 | 14:12 | 0.08 | 13965 | 13996 | 31 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13965.00 t/13996.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 372.00, Diff 1184.59, Temp 276.80
07/28/2021 | 14:12 | 14:27 | 0.25 | 13996 | 13996 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 14:27 | 14:46 | 0.32 | 13996 | 14027 | 31 | LAT | 4: BHA 4 | 2K | Rotary Drill f/13996.00 t/14027.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 97.89, Diff 1184.59, Temp 276.80
07/28/2021 | 14:46 | 14:51 | 0.08 | 14027 | 14027 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 14:51 | 15:03 | 0.2 | 14027 | 14058 | 31 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14027.00 t/14058.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 155.00, Diff 1184.59, Temp 276.80
07/28/2021 | 15:03 | 15:10 | 0.12 | 14058 | 14058 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 15:10 | 17:38 | 2.47 | 14058 | 14152 | 94 | LAT | 4: BHA 4 | 2J | Slide Drill f/14058.00 t/14152.00, TF -80.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 38.11, Diff 1184.59, Temp 276.80
07/28/2021 | 17:38 | 17:49 | 0.18 | 14152 | 14152 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 17:49 | 18:30 | 0.68 | 14152 | 14247 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14152.00 t/14247.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 139.02, Diff 1184.59, Temp 276.80
07/28/2021 | 18:30 | 18:34 | 0.07 | 14247 | 14247 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 18:34 | 20:16 | 1.7 | 14247 | 14307 | 60 | LAT | 4: BHA 4 | 2J | Slide Drill f/14247.00 t/14307.00, TF -70.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 35.29, Diff 1184.59, Temp 276.80
07/28/2021 | 20:16 | 20:28 | 0.2 | 14307 | 14341 | 34 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14307.00 t/14341.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 170.00, Diff 1184.59, Temp 276.80
07/28/2021 | 20:28 | 21:14 | 0.77 | 14341 | 14341 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 21:14 | 21:52 | 0.63 | 14341 | 14361 | 20 | LAT | 4: BHA 4 | 2J | Slide Drill f/14341.00 t/14361.00, TF -10.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 31.58, Diff 1184.59, Temp 277.00
07/28/2021 | 21:52 | 22:16 | 0.4 | 14361 | 14436 | 75 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14361.00 t/14436.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 187.50, Diff 1184.59, Temp 277.00
07/28/2021 | 22:16 | 22:30 | 0.23 | 14436 | 14436 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/28/2021 | 22:30 | 23:00 | 0.5 | 14436 | 14443 | 7 | LAT | 4: BHA 4 | 2J | Slide Drill f/14436.00 t/14443.00, TF 130.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 14.00, Diff 1184.59, Temp 277.00
07/28/2021 | 23:00 | 23:10 | 0.17 | 14443 | 14443 | 0 | LAT | 4: BHA 4 | 5A | Shut Inn Well (Gas)
07/28/2021 | 23:10 | 24:00 | 0.83 | 14443 | 14456 | 13 | LAT | 4: BHA 4 | 2J | Slide Drill f/14443.00 t/14456.00, TF 130.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 15.60, Diff 1184.59, Temp 277.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_29_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/29/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 121750
|  |  |  | 24hr Summary: |  | Drill Lateral
|  |  |  | 24hr Lookahead: |  | POOH & C/O BHA #4
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14456 |  | 10030 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 39 | PV: | 15
End Depth (Usft): |  | 14855 |  | 14855 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): |  | 399 |  | 4825 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 70 |  | 1505 | [5 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): |  | 329 |  | 3320 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 7.53 / 3.62 |  | 51.25 / 11.12 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: |  | 3.83 |  | 31.2 |  | SN: |  | 13601237 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 3.7 |  | 20.05 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.0 / 170.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 88.92 / 18.26 |  | 165.59 / 48.24 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 23.5 |  | 83.25 |  | Grade In: |  | New
% Slide: |  | 17.54 |  | 31.19 |  | Grade Out: |  | 1-1-WT-S-X-I-
% Rotary: |  | 82.46 |  | 68.81 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Chris Day |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .005 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.15 |  | 33.9
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.65 |  | 35.55
NM Pony Drill Collar |  |  |  | 5.25 | 2.75 |  |  |  |  | 10.51 |  | 46.06
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 50.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.87
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 111.69
Tomax |  |  |  | 5.25 | 2.562 |  |  |  |  | 18.35 |  | 130.04
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 133.42
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 322.19
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 330.77
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2784.15
Agitator |  |  |  | 5.25 | 2.812 |  |  |  |  | 23.46 |  | 2807.61
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.54
Agitator- Ball Drop |  |  |  | 5.25 | 2.812 |  |  |  |  | 20.9 |  | 5943.44
5943.44
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250007 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14461 | 89.1 | 131.54 | 10487.82 | -3800.94 | 888.46 | 2.47 |  | 104.23 | 3524.22 | -0.61 |  | 2.39 | 94
14556 | 90.58 | 131.96 | 10488.09 | -3864.2 | 959.33 | 1.62 |  | 15.84 | 3617.88 | 1.56 |  | 0.44 | 95
14650 | 88.24 | 133.34 | 10489.06 | -3927.87 | 1028.46 | 2.89 |  | 149.48 | 3710.77 | -2.49 |  | 1.47 | 94
14745 | 88.07 | 136.76 | 10492.11 | -3995.06 | 1095.53 | 3.6 |  | 92.9 | 3805.13 | -0.18 |  | 3.6 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 52.96 | 39.91 | 79.57 | 351 | 399.49 | 4113.2 | 3285 | 0 | 238 | 189.49 | 149 | 17.09 | 0
Run | 94.15 | 31.97 | 75.23 | 346 | 398.65 | 4303.83 | 3612.21 | 0 | 243.52 | 175.53 | 153.64 | 5066.16 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/29/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/29/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 07/29/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 07/29/2021 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/29/2021 | 00:00 | 00:30 | 0.5 | 14456 | 14530 | 74 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14456.00 t/14530.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 148.00, Diff 1184.59, Temp 277.00
07/29/2021 | 00:30 | 00:34 | 0.07 | 14530 | 14530 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/29/2021 | 00:34 | 01:00 | 0.43 | 14530 | 14545 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/14530.00 t/14545.00, TF 110.00G, w/WOB 39.91,Flow 399.49, Press 4589.59, Tq 17.09, ROP 34.62, Diff 1184.59, Temp 277.00
07/29/2021 | 01:00 | 01:46 | 0.77 | 14545 | 14624 | 79 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14545.00 t/14624.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 4589.59, Tq 17.09, ROP 103.04, Diff 1184.59, Temp 277.00
07/29/2021 | 01:46 | 01:50 | 0.07 | 14624 | 14624 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/29/2021 | 01:50 | 03:52 | 2.03 | 14624 | 14654 | 30 | LAT | 4: BHA 4 | 2J | Slide Drill f/14624.00 t/14654.00, TF 150.00G, w/WOB 39.91,Flow 399.49, Press 3850, Tq 17.09, ROP 14.75, Diff 600.00, Temp 277.00
07/29/2021 | 03:52 | 04:16 | 0.4 | 14654 | 14693 | 39 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14654.00 t/14693.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 3850, Tq 17.09, ROP 97.50, Diff 600.00, Temp 277.00
07/29/2021 | 04:16 | 04:22 | 0.1 | 14693 | 14693 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/29/2021 | 04:22 | 04:37 | 0.25 | 14693 | 14719 | 26 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14693.00 t/14719.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 3850, Tq 17.09, ROP 104.00, Diff 600.00, Temp 277.00
07/29/2021 | 04:37 | 04:48 | 0.18 | 14719 | 14719 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/29/2021 | 04:48 | 06:10 | 1.37 | 14719 | 14744 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/14719.00 t/14744.00, TF 110.00G, w/WOB 39.91,Flow 399.49, Press 3900, Tq 17.09, ROP 18.29, Diff 700.00, Temp 277.00
07/29/2021 | 06:10 | 07:15 | 1.08 | 14744 | 14813 | 69 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14744.00 t/14813.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 3900, Tq 17.09, ROP 63.69, Diff 700.00, Temp 277.00
07/29/2021 | 07:15 | 07:42 | 0.45 | 14813 | 14813 | 0 | LAT | 4: BHA 4 | 20B | Relog Gamma F/14,763 T/14,813
07/29/2021 | 07:42 | 07:48 | 0.1 | 14813 | 14813 | 0 | LAT | 4: BHA 4 | 10D | Survey & Connection
07/29/2021 | 07:48 | 08:30 | 0.7 | 14813 | 14855 | 42 | LAT | 4: BHA 4 | 2K | Rotary Drill f/14813.00 t/14855.00, w/WOB 39.91,Flow 399.49, RPM 79.57, Press 3900.00, Tq 17.09, ROP 60.00, Diff 700.00, Temp 282.00
07/29/2021 | 08:30 | 09:15 | 0.75 | 14855 | 14855 | 0 | LAT | 4: BHA 4 | 5A | Circulate And Condiction
07/29/2021 | 09:15 | 13:45 | 4.5 | 14855 | 14855 | 0 | LAT | 4: BHA 4 | 6B | POOH T/ 9,812
07/29/2021 | 13:45 | 15:45 | 2 | 14855 | 14855 | 0 | LAT | 4: BHA 4 | 5A | Circulate Bottoms Up Spot / Mud Cap
07/29/2021 | 15:45 | 22:40 | 6.92 | 14855 | 14855 | 0 | LAT | 4: BHA 4 | 6B | POOH F/ 9,812 T/BHA
07/29/2021 | 22:40 | 23:30 | 0.83 | 14855 | 14855 | 0 | LAT | 4: BHA 4 | 6P | L/D BHA #4
07/29/2021 | 23:30 | 24:00 | 0.5 | 14855 | 14855 | 0 | LAT |  | 7B | Clean Rig Floor of OBM
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_30_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/30/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18450 |  |  | Well Cost($): |  | 140200
|  |  |  | 24hr Summary: |  | P/U BHA #5 and TIH
|  |  |  | 24hr Lookahead: |  | TIH and Drill Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14855 |  | 14855 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 39 | PV: | 15
End Depth (Usft): |  | 15840 |  | 15840 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): |  | 985 |  | 985 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 90 |  | 90 | [5 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): |  | 895 |  | 895 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 8.68 / 4.40 |  | 8.68 / 4.40 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: |  | 4.43 |  | 4.43 |  | SN: |  | 13594950 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 4.25 |  | 4.25 |  | Bit # |  |  |  | PH / Temp(F) | 2.0 / 170.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 210.59 / 20.30 |  | 210.59 / 20.30 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 22.5 |  | 22.5 |  | Grade In: |  | New
% Slide: |  | 9.14 |  | 9.14 |  | Grade Out: |  | 1-1-RR-N-X-I-RR-PP
% Rotary: |  | 90.86 |  | 90.86 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .012 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.02 |  | 33.77
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.64 |  | 35.41
NM Pony Drill Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 10.51 |  | 45.92
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.33 |  | 49.25
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 110.88
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 128.8
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 132.18
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 320.95
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 329.53
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2782.91
Agitator |  |  |  | 5.562 | 2.625 |  |  |  |  | 24.2 |  | 2807.11
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.04
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.95 |  | 5943.99
5943.99
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250015 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.04 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14841 | 86.41 | 135.7 | 10496.74 | -4064.3 | 1161.86 | 2.05 |  | -147.49 | 3900.63 | -1.73 |  | -1.1 | 96
14936 | 87.8 | 136.87 | 10501.54 | -4132.88 | 1227.42 | 1.91 |  | 40.08 | 3995.13 | 1.46 |  | 1.23 | 95
15030 | 86.32 | 137.99 | 10506.36 | -4202.01 | 1290.93 | 1.97 |  | 142.95 | 4088.78 | -1.57 |  | 1.19 | 94
15125 | 84.92 | 138.73 | 10513.61 | -4272.8 | 1353.86 | 1.67 |  | 152.24 | 4183.36 | -1.47 |  | 0.78 | 95
15220 | 84.14 | 138.46 | 10522.67 | -4343.73 | 1416.41 | 0.87 |  | -161 | 4277.82 | -0.82 |  | -0.28 | 95
15314 | 87.49 | 138.82 | 10529.53 | -4414.08 | 1478.35 | 3.58 |  | 6.13 | 4371.45 | 3.56 |  | 0.38 | 94
15408 | 88.69 | 138.92 | 10532.66 | -4484.84 | 1540.14 | 1.28 |  | 4.76 | 4465.3 | 1.28 |  | 0.11 | 94
15502 | 87.69 | 139.46 | 10535.63 | -4555.95 | 1601.54 | 1.21 |  | 151.65 | 4559.19 | -1.06 |  | 0.57 | 94
15596 | 86.67 | 139.33 | 10540.25 | -4627.23 | 1662.65 | 1.09 |  | -172.75 | 4653.02 | -1.09 |  | -0.14 | 94
15690 | 87.39 | 140.69 | 10545.12 | -4699.15 | 1722.97 | 1.64 |  | 62.11 | 4746.86 | 0.77 |  | 1.45 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 113.22 | 26.83 | 80 | 339 | 381.33 | 5316.67 | 4343.33 | 0 | 250 | 185 | 152.5 | 19 | 0
Run | 113.22 | 26.83 | 80 | 339 | 381.33 | 5316.67 | 4343.33 | 0 | 250 | 185 | 152.5 | 19 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Real Time Survey Management |  |  |  |  | 07/30/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 07/30/2021 |  | 23 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 07/30/2021 |  | 8 |  | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 07/30/2021 |  | 12 |  | 9000 |  | 1 | 9000
Directional & MWD / Gamma Services |  |  |  |  | 07/30/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/30/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 18450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/30/2021 | 00:00 | 01:30 | 1.5 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 6O | P/U BHA #5
07/30/2021 | 01:30 | 01:40 | 0.17 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 5A | Test MWD Tool (Test Good)
07/30/2021 | 01:40 | 02:45 | 1.08 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 8P | Rig Service
07/30/2021 | 02:45 | 04:00 | 1.25 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 6A | TIH T/2,782
07/30/2021 | 04:00 | 04:20 | 0.33 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 24A | P/U and Test Agitator
07/30/2021 | 04:20 | 05:40 | 1.33 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 6A | TIH F/2,807 T/5,922
07/30/2021 | 05:40 | 06:00 | 0.33 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 24A | P/U Agitator #2
07/30/2021 | 06:00 | 08:00 | 2 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 6A | TIH F/5,943 T/10,040
07/30/2021 | 08:00 | 08:30 | 0.5 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 24A | Pull Trip Nipple & Install Trip Nipple
07/30/2021 | 08:30 | 10:40 | 2.17 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 5A | Circulate Out Mud Cap
07/30/2021 | 10:40 | 10:55 | 0.25 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 6A | TIH F/10,040 T/10,275
07/30/2021 | 10:55 | 11:00 | 0.08 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 5A | Test MWD Tool (Test Good)
07/30/2021 | 11:00 | 13:20 | 2.33 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 6A | TIH F/10,275 T/14,720
07/30/2021 | 13:20 | 13:50 | 0.5 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 5A | W/R F/14,720 T14,855
07/30/2021 | 13:50 | 14:10 | 0.33 | 14855 | 14855 | 0 | LAT | 5: BHA 5 | 5A | Check Shot @ 14,787
07/30/2021 | 14:10 | 14:58 | 0.8 | 14855 | 14865 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/14855.00 t/14865.00, TF 45.00G, w/WOB 41.00,Flow 288.00, Press 3500.00, Tq 0.00, ROP 12.50, Diff 290.00, Temp 282.00
07/30/2021 | 14:58 | 15:22 | 0.4 | 14865 | 14909 | 44 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14865.00 t/14909.00, w/WOB 24.00,Flow 400.00, RPM 80, Press 5680.00, Tq 19, ROP 110.00, Diff 1110.00, Temp 282.00
07/30/2021 | 15:22 | 15:27 | 0.08 | 14909 | 14909 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 15:27 | 15:55 | 0.47 | 14909 | 15004 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14909.00 t/15004.00, w/WOB 24.00,Flow 400.00, RPM 80.00, Press 5680.00, Tq 19.00, ROP 203.57, Diff 1110.00, Temp 282.00
07/30/2021 | 15:55 | 16:02 | 0.12 | 15004 | 15004 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 16:02 | 16:08 | 0.1 | 15004 | 15014 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15004.00 t/15014.00, w/WOB 24.00,Flow 400.00, RPM 80.00, Press 5680.00, Tq 19.00, ROP 100.00, Diff 1110.00, Temp 282.00
07/30/2021 | 16:08 | 17:14 | 1.1 | 15014 | 15034 | 20 | LAT | 5: BHA 5 | 2J | Slide Drill f/15014.00 t/15034.00, TF 150G, w/WOB 24.00,Flow 400.00, Press 5680.00, Tq 0, ROP 18.18, Diff 1110.00, Temp 282.00
07/30/2021 | 17:14 | 17:33 | 0.32 | 15034 | 15098 | 64 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15034.00 t/15098.00, w/WOB 24.00,Flow 400.00, RPM 80.00, Press 5680.00, Tq 19.00, ROP 202.11, Diff 1110.00, Temp 282.00
07/30/2021 | 17:33 | 17:38 | 0.08 | 15098 | 15098 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 17:38 | 18:05 | 0.45 | 15098 | 15193 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15098.00 t/15193.00, w/WOB 24.00,Flow 400.00, RPM 80.00, Press 5680.00, Tq 19.00, ROP 211.11, Diff 1110.00, Temp 282.00
07/30/2021 | 18:05 | 18:10 | 0.08 | 15193 | 15193 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 18:10 | 18:35 | 0.42 | 15193 | 15286 | 93 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15193.00 t/15286.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 223.20, Diff 1126.00, Temp 293.00
07/30/2021 | 18:35 | 18:45 | 0.17 | 15286 | 15286 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 18:45 | 19:55 | 1.17 | 15286 | 15316 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/15286.00 t/15316.00, TF 10.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 25.71, Diff 1126.00, Temp 293.00
07/30/2021 | 19:55 | 20:23 | 0.47 | 15316 | 15380 | 64 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15316.00 t/15380.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 137.14, Diff 1126.00, Temp 293.00
07/30/2021 | 20:23 | 20:35 | 0.2 | 15380 | 15380 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 20:35 | 20:52 | 0.28 | 15380 | 15475 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15380.00 t/15475.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 335.29, Diff 1126.00, Temp 293.00
07/30/2021 | 20:52 | 20:58 | 0.1 | 15475 | 15475 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 20:58 | 21:05 | 0.12 | 15475 | 15485 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15475.00 t/15485.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 85.71, Diff 1126.00, Temp 293.00
07/30/2021 | 21:05 | 22:00 | 0.92 | 15485 | 15505 | 20 | LAT | 5: BHA 5 | 2J | Slide Drill f/15485.00 t/15505.00, TF 135.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 21.82, Diff 1126.00, Temp 293.00
07/30/2021 | 22:00 | 22:18 | 0.3 | 15505 | 15570 | 65 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15505.00 t/15570.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 216.67, Diff 1126.00, Temp 293.00
07/30/2021 | 22:18 | 22:24 | 0.1 | 15570 | 15570 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 22:24 | 22:45 | 0.35 | 15570 | 15664 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15570.00 t/15664.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 268.57, Diff 1126.00, Temp 293.00
07/30/2021 | 22:45 | 22:52 | 0.12 | 15664 | 15664 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 22:52 | 23:12 | 0.33 | 15664 | 15758 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15664.00 t/15758.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 282.00, Diff 1126.00, Temp 293.00
07/30/2021 | 23:12 | 23:18 | 0.1 | 15758 | 15758 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/30/2021 | 23:18 | 23:23 | 0.08 | 15758 | 15768 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15758.00 t/15768.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 120.00, Diff 1126.00, Temp 298.00
07/30/2021 | 23:23 | 23:50 | 0.45 | 15768 | 15778 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/15768.00 t/15778.00, TF 180.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 22.22, Diff 1126.00, Temp 298.00
07/30/2021 | 23:50 | 24:00 | 0.17 | 15778 | 15840 | 62 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15778.00 t/15840.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 372.00, Diff 1126.00, Temp 298.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_31_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/31/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 149650
|  |  |  | 24hr Summary: |  | Drill Lateral Section
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15840 |  | 14855 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 39 | PV: | 15
End Depth (Usft): |  | 17378 |  | 17378 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): |  | 1538 |  | 2523 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 131 |  | 221 | [5 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): |  | 1407 |  | 2302 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 17.08 / 6.67 |  | 25.77 / 11.07 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: |  | 8.87 |  | 13.3 |  | SN: |  | 13594950 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 8.22 |  | 12.47 |  | Bit # |  |  |  | PH / Temp(F) | 2.0 / 170.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 171.24 / 14.77 |  | 184.65 / 16.62 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 46.5 |  | Grade In: |  | New
% Slide: |  | 8.52 |  | 8.76 |  | Grade Out: |  | 1-1-RR-N-X-I-RR-PP
% Rotary: |  | 91.48 |  | 91.24 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .012 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.02 |  | 33.77
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.64 |  | 35.41
NM Pony Drill Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 10.51 |  | 45.92
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.33 |  | 49.25
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 110.88
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 128.8
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 132.18
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 320.95
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 329.53
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2782.91
Agitator |  |  |  | 5.562 | 2.625 |  |  |  |  | 24.2 |  | 2807.11
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.04
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.95 |  | 5943.99
5943.99
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250015 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.04 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15784 | 84.75 | 137.85 | 10551.57 | -4770.21 | 1784.15 | 4.12 |  | -133.07 | 4840.56 | -2.81 |  | -3.02 | 94
15878 | 86.24 | 139.1 | 10558.95 | -4840.36 | 1846.27 | 2.07 |  | 39.96 | 4934.14 | 1.59 |  | 1.33 | 94
15972 | 86.65 | 141.05 | 10564.78 | -4912.31 | 1906.48 | 2.12 |  | 78.17 | 5027.93 | 0.44 |  | 2.07 | 94
16066 | 87.17 | 140.27 | 10569.85 | -4984.9 | 1965.98 | 1 |  | -56.29 | 5121.79 | 0.55 |  | -0.83 | 94
16161 | 87.47 | 139.84 | 10574.29 | -5057.65 | 2026.91 | 0.55 |  | -55.08 | 5216.66 | 0.32 |  | -0.45 | 95
16256 | 87.93 | 139.39 | 10578.1 | -5129.96 | 2088.41 | 0.68 |  | -44.36 | 5311.53 | 0.48 |  | -0.47 | 95
16350 | 88.12 | 139.01 | 10581.34 | -5201.07 | 2149.8 | 0.45 |  | -63.43 | 5405.41 | 0.2 |  | -0.4 | 94
16444 | 88.64 | 139.05 | 10584 | -5272.02 | 2211.4 | 0.55 |  | 4.4 | 5499.29 | 0.55 |  | 0.04 | 94
16539 | 87.73 | 140.1 | 10587.01 | -5344.3 | 2272.97 | 1.46 |  | 130.94 | 5594.2 | -0.96 |  | 1.11 | 95
16633 | 87.58 | 143 | 10590.85 | -5417.84 | 2331.37 | 3.09 |  | 93.02 | 5688.11 | -0.16 |  | 3.09 | 94
16728 | 84.3 | 138.4 | 10597.58 | -5491.15 | 2391.36 | 5.94 |  | -125.7 | 5782.82 | -3.45 |  | -4.84 | 95
16822 | 83.4 | 139.35 | 10607.65 | -5561.55 | 2452.83 | 1.39 |  | 133.67 | 5876.19 | -0.96 |  | 1.01 | 94
16917 | 85.32 | 140.99 | 10616.99 | -5634.15 | 2513.38 | 2.65 |  | 40.45 | 5970.7 | 2.02 |  | 1.73 | 95
17012 | 88.99 | 142.23 | 10621.7 | -5708.5 | 2572.29 | 4.08 |  | 18.68 | 6065.57 | 3.86 |  | 1.31 | 95
17106 | 88.39 | 142.52 | 10623.85 | -5782.93 | 2629.66 | 0.71 |  | 154.21 | 6159.53 | -0.64 |  | 0.31 | 94
17201 | 89.64 | 142.43 | 10625.49 | -5858.26 | 2687.51 | 1.32 |  | -4.12 | 6254.49 | 1.32 |  | -0.09 | 95
17296 | 90.34 | 142.38 | 10625.5 | -5933.54 | 2745.47 | 0.74 |  | -4.09 | 6349.48 | 0.74 |  | -0.05 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 90.03 | 32 | 80 | 352 | 400 | 5756 | 4630 | 0 | 253.08 | 185.19 | 149.42 | 22 | 0
Run | 97.92 | 31.13 | 80 | 350 | 397.51 | 5695.73 | 4590.44 | 0 | 251.78 | 185.11 | 150 | 21.56 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/31/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/31/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 07/31/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 07/31/2021 |  | 23 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 07/31/2021 |  | 8 |  | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 07/31/2021 |  | 12 |  | 9000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/31/2021 | 00:00 | 00:12 | 0.2 | 15840 | 15851 | 11 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15840.00 t/15851.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 55.00, Diff 1126.00, Temp 298.00
07/31/2021 | 00:12 | 00:16 | 0.07 | 15851 | 15851 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 00:16 | 00:25 | 0.15 | 15851 | 15862 | 11 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15851.00 t/15862.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 73.33, Diff 1126.00, Temp 298.00
07/31/2021 | 00:25 | 01:30 | 1.08 | 15862 | 15887 | 25 | LAT | 5: BHA 5 | 2J | Slide Drill f/15862.00 t/15887.00, TF 30.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 23.08, Diff 1126.00, Temp 298.00
07/31/2021 | 01:30 | 01:48 | 0.3 | 15887 | 15946 | 59 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15887.00 t/15946.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 196.67, Diff 1126.00, Temp 298.00
07/31/2021 | 01:48 | 01:52 | 0.07 | 15946 | 15946 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 01:52 | 02:14 | 0.37 | 15946 | 16039 | 93 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15946.00 t/16039.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 253.64, Diff 1126.00, Temp 298.00
07/31/2021 | 02:14 | 02:18 | 0.07 | 16039 | 16039 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 02:18 | 02:42 | 0.4 | 16039 | 16134 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16039.00 t/16134.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 237.50, Diff 1126.00, Temp 298.00
07/31/2021 | 02:42 | 02:46 | 0.07 | 16134 | 16134 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 02:46 | 03:11 | 0.42 | 16134 | 16228 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16134.00 t/16228.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 225.60, Diff 1126.00, Temp 298.00
07/31/2021 | 03:11 | 03:15 | 0.07 | 16228 | 16228 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 03:15 | 03:38 | 0.38 | 16228 | 16324 | 96 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16228.00 t/16324.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 250.43, Diff 1126.00, Temp 298.00
07/31/2021 | 03:38 | 03:42 | 0.07 | 16324 | 16324 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 03:42 | 04:05 | 0.38 | 16324 | 16418 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16324.00 t/16418.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 245.22, Diff 1126.00, Temp 298.00
07/31/2021 | 04:05 | 04:08 | 0.05 | 16418 | 16418 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 04:08 | 04:34 | 0.43 | 16418 | 16512 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16418.00 t/16512.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 216.92, Diff 1126.00, Temp 307.00
07/31/2021 | 04:34 | 04:37 | 0.05 | 16512 | 16512 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 04:37 | 04:45 | 0.13 | 16512 | 16522 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16512.00 t/16522.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 75.00, Diff 1126.00, Temp 307.00
07/31/2021 | 04:45 | 06:20 | 1.58 | 16522 | 16547 | 25 | LAT | 5: BHA 5 | 2J | Slide Drill f/16522.00 t/16547.00, TF 135G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 15.79, Diff 1126.00, Temp 298.00
07/31/2021 | 06:20 | 06:38 | 0.3 | 16547 | 16607 | 60 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16547.00 t/16607.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 200.00, Diff 1126.00, Temp 307.00
07/31/2021 | 06:38 | 06:43 | 0.08 | 16607 | 16607 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 06:43 | 07:05 | 0.37 | 16607 | 16701 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16607.00 t/16701.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 256.36, Diff 1126.00, Temp 307.00
07/31/2021 | 07:05 | 07:10 | 0.08 | 16701 | 16701 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 07:10 | 07:15 | 0.08 | 16701 | 16711 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16701.00 t/16711.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 120.00, Diff 1126.00, Temp 307.00
07/31/2021 | 07:15 | 08:35 | 1.33 | 16711 | 16723 | 12 | LAT | 5: BHA 5 | 2J | Slide Drill f/16711.00 t/16723.00, TF 180G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 9.00, Diff 1126.00, Temp 307.00
07/31/2021 | 08:35 | 09:00 | 0.42 | 16723 | 16796 | 73 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16723.00 t/16796.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 175.20, Diff 1126.00, Temp 307.00
07/31/2021 | 09:00 | 09:05 | 0.08 | 16796 | 16796 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 09:05 | 09:10 | 0.08 | 16796 | 16815 | 19 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16796.00 t/16815.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 228.00, Diff 1126.00, Temp 307.00
07/31/2021 | 09:10 | 09:49 | 0.65 | 16815 | 16819 | 4 | LAT | 5: BHA 5 | 2J | Slide Drill f/16815.00 t/16819.00, TF 90G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 6.15, Diff 1126.00, Temp 307.00
07/31/2021 | 09:49 | 10:30 | 0.68 | 16819 | 16819 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 10:30 | 11:33 | 1.05 | 16819 | 16825 | 6 | LAT | 5: BHA 5 | 2J | Slide Drill f/16819.00 t/16825.00, TF 60G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 5.71, Diff 1126.00, Temp 307.00
07/31/2021 | 11:33 | 12:02 | 0.48 | 16825 | 16890 | 65 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16825.00 t/16890.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 134.48, Diff 1126.00, Temp 307.00
07/31/2021 | 12:02 | 12:07 | 0.08 | 16890 | 16890 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 12:07 | 12:22 | 0.25 | 16890 | 16890 | 0 | LAT | 5: BHA 5 | 8L | C/O 2 On Stand Pipe
07/31/2021 | 12:22 | 12:30 | 0.13 | 16890 | 16900 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16890.00 t/16900.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 75.00, Diff 1126.00, Temp 307.00
07/31/2021 | 12:30 | 12:38 | 0.13 | 16900 | 16900 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 12:38 | 14:25 | 1.78 | 16900 | 16930 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/16900.00 t/16930.00, TF 35.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 16.82, Diff 1126.00, Temp 307.00
07/31/2021 | 14:25 | 14:45 | 0.33 | 16930 | 16985 | 55 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16930.00 t/16985.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 165.00, Diff 1126.00, Temp 307.00
07/31/2021 | 14:45 | 14:50 | 0.08 | 16985 | 16985 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 14:50 | 14:55 | 0.08 | 16985 | 17000 | 15 | LAT | 5: BHA 5 | 2K | Rotary Drill f/16985.00 t/17000.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 180.00, Diff 1126.00, Temp 307.00
07/31/2021 | 14:55 | 15:00 | 0.08 | 17000 | 17000 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 15:00 | 15:30 | 0.5 | 17000 | 17080 | 80 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17000.00 t/17080.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 160.00, Diff 1126.00, Temp 307.00
07/31/2021 | 15:30 | 20:09 | 4.65 | 17080 | 17080 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 20:09 | 20:18 | 0.15 | 17080 | 17090 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17080.00 t/17090.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 66.67, Diff 1126.00, Temp 307.00
07/31/2021 | 20:18 | 20:48 | 0.5 | 17090 | 17100 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/17090.00 t/17100.00, TF 170.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 20.00, Diff 1126.00, Temp 307.00
07/31/2021 | 20:48 | 21:14 | 0.43 | 17100 | 17174 | 74 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17100.00 t/17174.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 170.77, Diff 1126.00, Temp 307.00
07/31/2021 | 21:14 | 21:18 | 0.07 | 17174 | 17174 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 21:18 | 21:46 | 0.47 | 17174 | 17269 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17174.00 t/17269.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 203.57, Diff 1126.00, Temp 307.00
07/31/2021 | 21:46 | 21:50 | 0.07 | 17269 | 17269 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 21:50 | 22:28 | 0.63 | 17269 | 17279 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17269.00 t/17279.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 15.79, Diff 1126.00, Temp 307.00
07/31/2021 | 22:28 | 22:58 | 0.5 | 17279 | 17294 | 15 | LAT | 5: BHA 5 | 2J | Slide Drill f/17279.00 t/17294.00, TF 170.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 30.00, Diff 1126.00, Temp 307.00
07/31/2021 | 22:58 | 23:26 | 0.47 | 17294 | 17362 | 68 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17294.00 t/17362.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 145.71, Diff 1126.00, Temp 302.00
07/31/2021 | 23:26 | 23:30 | 0.07 | 17362 | 17362 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/31/2021 | 23:30 | 23:37 | 0.12 | 17362 | 17374 | 12 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17362.00 t/17374.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 102.86, Diff 1126.00, Temp 302.00
07/31/2021 | 23:37 | 24:00 | 0.38 | 17374 | 17378 | 4 | LAT | 5: BHA 5 | 2J | Slide Drill f/17374.00 t/17378.00, TF 170.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 10.43, Diff 1126.00, Temp 302.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_1_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 17 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/01/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 159100
|  |  |  | 24hr Summary: |  | Drill Lateral Section
|  |  |  | 24hr Lookahead: |  | POOH to C/O Mud Motor and BHA
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17378 |  | 17632 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 39 | PV: | 15
End Depth (Usft): |  | 17632 |  | 17632 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): | [9 empty] | 100: | 13 | Chlorides: | 67000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 0.00 / 0.58 |  | 0.00 / 0.58 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: | [5 empty] | SN: |  | 13594950 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 2.0 / 170.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 1.25 |  | 1.25 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-RR-N-X-I-RR-PP
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .012 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.02 |  | 33.77
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.64 |  | 35.41
NM Pony Drill Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 10.51 |  | 45.92
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.33 |  | 49.25
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.06
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 110.88
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 128.8
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 132.18
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 320.95
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 329.53
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2782.91
Agitator |  |  |  | 5.562 | 2.625 |  |  |  |  | 24.2 |  | 2807.11
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5922.04
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.95 |  | 5943.99
5943.99
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250015 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.04 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17392 | 89.57 | 141.54 | 10625.58 | -6009.14 | 2804.63 | 1.19 |  | -132.51 | 6445.47 | -0.8 |  | -0.88 | 96
17486 | 86.01 | 140.98 | 10629.2 | -6082.4 | 2863.4 | 3.83 |  | -171.08 | 6539.39 | -3.79 |  | -0.6 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 90.71 | 32 | 80 | 352 | 400 | 5756 | 4630 | 0 | 253.08 | 185.19 | 149.42 | 22 | 0
Run | 97.21 | 31.13 | 80 | 350 | 397.51 | 5695.73 | 4590.44 | 0 | 251.78 | 185.11 | 150 | 21.56 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 08/01/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 08/01/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 08/01/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 08/01/2021 |  | 23 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 08/01/2021 |  | 8 |  | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 08/01/2021 |  | 12 |  | 9000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/01/2021 | 00:00 | 00:10 | 0.17 | 17378 | 17378 | 0 | LAT | 5: BHA 5 | 20C | Trouble Shot PSI Increase
08/01/2021 | 00:10 | 01:45 | 1.58 | 17378 | 17378 | 0 | LAT | 5: BHA 5 | 5A | Circulate
08/01/2021 | 01:45 | 01:52 | 0.12 | 17378 | 17383 | 5 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17378.00 t/17383.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 42.86, Diff 1126.00, Temp 302.00
08/01/2021 | 01:52 | 03:05 | 1.22 | 17383 | 17404 | 21 | LAT | 5: BHA 5 | 2J | Slide Drill f/17383.00 t/17404.00, TF 180.00G, w/WOB 32.00,Flow 400.00, Press 5756.00, Tq 22.00, ROP 17.26, Diff 1126.00, Temp 302.00
08/01/2021 | 03:05 | 03:26 | 0.35 | 17404 | 17460 | 56 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17404.00 t/17460.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 160.00, Diff 1126.00, Temp 302.00
08/01/2021 | 03:26 | 03:42 | 0.27 | 17460 | 17460 | 0 | LAT | 5: BHA 5 | 8A | Check TopDrive For Leaks
08/01/2021 | 03:42 | 03:45 | 0.05 | 17460 | 17460 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
08/01/2021 | 03:45 | 03:50 | 0.08 | 17460 | 17472 | 12 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17460.00 t/17472.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 144.00, Diff 1126.00, Temp 302.00
08/01/2021 | 03:50 | 04:00 | 0.17 | 17472 | 17472 | 0 | LAT | 5: BHA 5 | 5A | Check Shot
08/01/2021 | 04:00 | 04:30 | 0.5 | 17472 | 17554 | 82 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17472.00 t/17554.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 164.00, Diff 1126.00, Temp 302.00
08/01/2021 | 04:30 | 04:34 | 0.07 | 17554 | 17554 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
08/01/2021 | 04:34 | 05:00 | 0.43 | 17554 | 17627 | 73 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17554.00 t/17627.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 168.46, Diff 1126.00, Temp 302.00
08/01/2021 | 05:00 | 05:25 | 0.42 | 17627 | 17627 | 0 | LAT | 5: BHA 5 | 5A | Connection
08/01/2021 | 05:25 | 05:31 | 0.1 | 17627 | 17632 | 5 | LAT | 5: BHA 5 | 2K | Rotary Drill f/17627.00 t/17632.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5756.00, Tq 22.00, ROP 50.00, Diff 1126.00, Temp 302.00
08/01/2021 | 05:31 | 05:40 | 0.15 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 5A | Recycle Mud Pumps
08/01/2021 | 05:40 | 07:00 | 1.33 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 5A | Circulate Bottoms Up
08/01/2021 | 07:00 | 08:45 | 1.75 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 3D | Back Ream F/17,632 - T/16,478
08/01/2021 | 08:45 | 12:49 | 4.07 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 6B | POOH F/16,478 T/10,040
08/01/2021 | 12:49 | 15:00 | 2.18 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 5A | Circulate Out Gas
08/01/2021 | 15:00 | 21:15 | 6.25 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 6B | POOH
08/01/2021 | 21:15 | 21:45 | 0.5 | 17632 | 17632 | 0 | LAT | 5: BHA 5 | 6P | L/D BHA #5
08/01/2021 | 21:45 | 21:55 | 0.17 | 17632 | 17632 | 0 | LAT |  | 7B | Clean Rig Floor
08/01/2021 | 21:55 | 22:45 | 0.83 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6O | P/U BHA #6
08/01/2021 | 22:45 | 23:10 | 0.42 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Test MWD Tool
08/01/2021 | 23:10 | 23:30 | 0.33 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6A | TIH
08/01/2021 | 23:30 | 23:40 | 0.17 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Test MWD Tool
08/01/2021 | 23:40 | 24:00 | 0.33 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6B | POOH to Check MWD Tool
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_2_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 18 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/02/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 16450 |  |  | Well Cost($): |  | 175550
|  |  |  | 24hr Summary: |  | TIH with BHA #6
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17632 |  | 17632 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 38 | PV: | 15
End Depth (Usft): |  | 18133 |  | 18133 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): |  | 501 |  | 501 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 45
Slide Drilled (Usft): |  | 19 |  | 19 | [5 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): |  | 482 |  | 482 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 3.90 / 7.67 |  | 3.90 / 8.25 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: |  | 0.95 |  | 0.95 |  | SN: |  | 13601236 |  | 10s Gel: | 6 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 2.95 |  | 2.95 |  | Bit # |  | 5 |  | PH / Temp(F) | 2.0 / 178.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 163.39 / 20.00 |  | 163.39 / 20.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 25.25 |  | Grade In: |  | New
% Slide: |  | 3.79 |  | 3.79 |  | Grade Out: |  | 1-1-BT-S-X-I-NO-TD
% Rotary: |  | 96.21 |  | 96.21 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .010 Slick |  |  |  | 5 | 2 |  |  |  |  | 32.98 |  | 33.73
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.64 |  | 35.37
NM Pony Drill Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 10.51 |  | 45.88
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.33 |  | 49.21
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.02
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 110.84
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 128.76
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 132.14
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 320.91
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 329.49
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2782.87
Agitator |  |  |  | 5.562 | 2.625 |  |  |  |  | 21.55 |  | 2804.42
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5919.35
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.95 |  | 5941.3
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250021 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17578 | 86.78 | 141.75 | 10634.99 | -6154.12 | 2920.72 | 1.18 |  | 44.97 | 6631.2 | 0.84 |  | 0.84 | 92
17674 | 85.74 | 143.3 | 10641.25 | -6230.14 | 2979 | 1.94 |  | 123.97 | 6726.98 | -1.08 |  | 1.61 | 96
17768 | 86.44 | 143.58 | 10647.66 | -6305.47 | 3034.87 | 0.8 |  | 21.77 | 6820.7 | 0.74 |  | 0.3 | 94
17863 | 86.73 | 143.44 | 10653.32 | -6381.71 | 3091.26 | 0.34 |  | -25.73 | 6915.46 | 0.31 |  | -0.15 | 95
17957 | 86.96 | 143.44 | 10658.49 | -6457.1 | 3147.17 | 0.24 |  | 0 | 7009.26 | 0.24 |  | 0 | 94
18051 | 87.28 | 143.44 | 10663.22 | -6532.5 | 3203.09 | 0.34 |  | 0 | 7103.08 | 0.34 |  | 0 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 128.46 | 32 | 80 | 352 | 400 | 5756 | 4630 | 0 | 253.08 | 185.19 | 149.42 | 22 | 0
Run | 128.46 | 31.13 | 80 | 350 | 397.51 | 5695.73 | 4590.44 | 0 | 251.78 | 185.11 | 150 | 21.56 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 08/02/2021 |  | 8 |  | 1000
Directional & MWD / Gamma Services |  |  |  |  | 08/02/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 08/02/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 08/02/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 08/02/2021 |  | 23 |  | 2000
5.5 Premium Motor Stator Reline |  |  |  |  | 08/02/2021 |  | 12 |  | 9000 |  | 1 | 9000
Total | [11 empty] | 16450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/02/2021 | 00:00 | 03:45 | 3.75 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6A | TIH
08/02/2021 | 03:45 | 04:30 | 0.75 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 24A | Remove Trip Nipple & Install Rotating Head
08/02/2021 | 04:30 | 05:30 | 1 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 9A | Slip & Cut Drill Line
08/02/2021 | 05:30 | 06:30 | 1 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 8P | Rig Service
08/02/2021 | 06:30 | 07:15 | 0.75 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 8A | C/O Swivel Packing
08/02/2021 | 07:15 | 08:30 | 1.25 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6A | TIH F/6,132 T/8,746
08/02/2021 | 08:30 | 09:00 | 0.5 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 23K | Waiting On Weather To Pass
08/02/2021 | 09:00 | 11:00 | 2 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Circulate
08/02/2021 | 11:00 | 11:45 | 0.75 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6A | TIH F/8,746 T/10,096
08/02/2021 | 11:45 | 13:00 | 1.25 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Circulate Bottoms Up
08/02/2021 | 13:00 | 14:24 | 1.4 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6A | TIH F/10,096 T/12,919
08/02/2021 | 14:24 | 14:30 | 0.1 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Fill Pipe & Test MWD
08/02/2021 | 14:30 | 15:47 | 1.28 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 6A | TIH F/12,919 T/15,557
08/02/2021 | 15:47 | 17:30 | 1.72 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Circulate
08/02/2021 | 17:30 | 19:25 | 1.92 | 17632 | 17632 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 19:25 | 19:35 | 0.17 | 17632 | 17646 | 14 | LAT | 6: BHA 6 | 2K | Rotary Drill f/17632.00 t/17646.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 84.00, Diff 600.00, Temp 300.00
08/02/2021 | 19:35 | 19:40 | 0.08 | 17646 | 17646 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 19:40 | 19:48 | 0.13 | 17646 | 17656 | 10 | LAT | 6: BHA 6 | 2K | Rotary Drill f/17646.00 t/17656.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 75.00, Diff 600.00, Temp 306.00
08/02/2021 | 19:48 | 20:23 | 0.58 | 17656 | 17671 | 15 | LAT | 6: BHA 6 | 2J | Slide Drill f/17656.00 t/17671.00, TF 160.00G, w/WOB 27.00,Flow 371.00, Press 5980.00, Tq 24.00, ROP 25.71, Diff 600.00, Temp 306.00
08/02/2021 | 20:23 | 21:00 | 0.62 | 17671 | 17739 | 68 | LAT | 6: BHA 6 | 2K | Rotary Drill f/17671.00 t/17739.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 110.27, Diff 600.00, Temp 306.00
08/02/2021 | 21:00 | 21:05 | 0.08 | 17739 | 17739 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 21:05 | 21:32 | 0.45 | 17739 | 17834 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/17739.00 t/17834.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 211.11, Diff 600.00, Temp 306.00
08/02/2021 | 21:32 | 21:35 | 0.05 | 17834 | 17834 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 21:35 | 22:05 | 0.5 | 17834 | 17928 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/17834.00 t/17928.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 188.00, Diff 600.00, Temp 306.00
08/02/2021 | 22:05 | 22:10 | 0.08 | 17928 | 17928 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 22:10 | 22:36 | 0.43 | 17928 | 18023 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/17928.00 t/18023.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 219.23, Diff 600.00, Temp 306.00
08/02/2021 | 22:36 | 22:40 | 0.07 | 18023 | 18023 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 22:40 | 22:56 | 0.27 | 18023 | 18023 | 0 | LAT | 6: BHA 6 | 10C | Recycle Mud Pumps
08/02/2021 | 22:56 | 23:23 | 0.45 | 18023 | 18117 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18023.00 t/18117.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 208.89, Diff 600.00, Temp 306.00
08/02/2021 | 23:23 | 23:26 | 0.05 | 18117 | 18117 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/02/2021 | 23:26 | 23:38 | 0.2 | 18117 | 18129 | 12 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18117.00 t/18129.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 60.00, Diff 600.00
08/02/2021 | 23:38 | 24:00 | 0.37 | 18129 | 18133 | 4 | LAT | 6: BHA 6 | 2J | Slide Drill f/18129.00 t/18133.00, TF -160.00G, w/WOB 27.00,Flow 371.00, Press 5980.00, Tq 24.00, ROP 10.91, Diff 600.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_3_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 19 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/03/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7450 |  |  | Well Cost($): |  | 183000
|  |  |  | 24hr Summary: |  | Drill Lateral Section
|  |  |  | 24hr Lookahead: |  | Drill & TD Lateral
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18133 |  | 17632 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 38 | PV: | 15
End Depth (Usft): |  | 19102 |  | 19102 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): |  | 969 |  | 1470 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 45
Slide Drilled (Usft): |  | 38 |  | 57 | [5 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): |  | 931 |  | 1413 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  | 7.55 / 12.07 |  | 11.45 / 20.32 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: |  | 2.08 |  | 3.03 |  | SN: |  | 13601236 |  | 10s Gel: | 6 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 5.47 |  | 8.42 |  | Bit # |  | 5 |  | PH / Temp(F) | 2.0 / 178.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 170.30 / 18.24 |  | 167.88 / 18.79 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 49.25 |  | Grade In: |  | New
% Slide: |  | 3.92 |  | 3.88 |  | Grade Out: |  | 1-1-BT-S-X-I-NO-TD
% Rotary: |  | 96.08 |  | 96.12 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Doug Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein Nathan Marks |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .010 Slick |  |  |  | 5 | 2 |  |  |  |  | 32.98 |  | 33.73
BTI |  |  |  | 4.875 | 2.125 |  |  |  |  | 1.64 |  | 35.37
NM Pony Drill Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 10.51 |  | 45.88
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.33 |  | 49.21
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.81 |  | 80.02
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.82 |  | 110.84
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 128.76
Crossover |  |  |  | 5.312 | 2.562 |  |  |  |  | 3.38 |  | 132.14
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 320.91
Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.58 |  | 329.49
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2782.87
Agitator |  |  |  | 5.562 | 2.625 |  |  |  |  | 21.55 |  | 2804.42
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5919.35
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.95 |  | 5941.3
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250021 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18146 | 87.27 | 141.51 | 10667.73 | -6607.76 | 3260.89 | 2.03 |  | -90.34 | 7197.95 | -0.01 |  | -2.03 | 95
18240 | 85.77 | 140.43 | 10673.44 | -6680.64 | 3319.97 | 1.97 |  | -144.33 | 7291.77 | -1.6 |  | -1.15 | 94
18335 | 85.92 | 140.48 | 10680.32 | -6753.71 | 3380.29 | 0.17 |  | 18.39 | 7386.51 | 0.16 |  | 0.05 | 95
18430 | 86.14 | 140.39 | 10686.9 | -6826.77 | 3440.66 | 0.25 |  | -22.2 | 7481.27 | 0.23 |  | -0.09 | 95
18525 | 87.79 | 141 | 10691.93 | -6900.17 | 3500.75 | 1.85 |  | 20.28 | 7576.12 | 1.74 |  | 0.64 | 95
18620 | 89 | 141.41 | 10694.59 | -6974.18 | 3560.25 | 1.34 |  | 18.72 | 7671.08 | 1.27 |  | 0.43 | 95
18714 | 88.46 | 141.39 | 10696.67 | -7047.63 | 3618.88 | 0.57 |  | -177.88 | 7765.06 | -0.57 |  | -0.02 | 94
18808 | 88.24 | 141.38 | 10699.38 | -7121.04 | 3677.52 | 0.23 |  | -177.4 | 7859.02 | -0.23 |  | -0.01 | 94
18902 | 88.27 | 141.16 | 10702.24 | -7194.34 | 3736.3 | 0.24 |  | -82.23 | 7952.98 | 0.03 |  | -0.23 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 128.34 | 27 | 80 | 332 | 371 | 5980 | 5380 | 0 | 280 | 260 | 150 | 25.2 | 0
Run | 128.38 | 27 | 80 | 332 | 371 | 5980 | 5380 | 0 | 280 | 260 | 150 | 24.78 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 08/03/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 08/03/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 08/03/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 08/03/2021 |  | 23 |  | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 08/03/2021 |  | 8 |  | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 08/03/2021 |  | 12 |  | 9000
Total | [11 empty] | 7450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/03/2021 | 00:00 | 00:30 | 0.5 | 18133 | 18133 | 0 | LAT | 6: BHA 6 | 10C | C/O Transducer Down Link MWD Tool
08/03/2021 | 00:30 | 00:35 | 0.08 | 18133 | 18133 | 0 | LAT | 6: BHA 6 | 5A | Circulate
08/03/2021 | 00:35 | 00:50 | 0.25 | 18133 | 18133 | 0 | LAT | 6: BHA 6 | 10C | Down Link MWD Tool
08/03/2021 | 00:50 | 01:21 | 0.52 | 18133 | 18143 | 10 | LAT | 6: BHA 6 | 2J | Slide Drill f/18133.00 t/18143.00, TF -160.00G, w/WOB 27.00,Flow 371.00, Press 5980.00, Tq 24.00, ROP 19.35, Diff 600.00, Temp 306.00
08/03/2021 | 01:21 | 01:46 | 0.42 | 18143 | 18212 | 69 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18143.00 t/18143.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 0.00, Diff 600.00, Temp 306.00
08/03/2021 | 01:46 | 01:50 | 0.07 | 18212 | 18212 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 01:50 | 02:20 | 0.5 | 18212 | 18212 | 0 | LAT | 6: BHA 6 | 10C | Trouble Shot MWD Tool
08/03/2021 | 02:20 | 02:28 | 0.13 | 18212 | 18226 | 14 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18212.00 t/18226.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 105.00, Diff 600.00, Temp 306.00
08/03/2021 | 02:28 | 02:52 | 0.4 | 18226 | 18234 | 8 | LAT | 6: BHA 6 | 2J | Slide Drill f/18226.00 t/18234.00, TF 180.00G, w/WOB 27.00,Flow 371.00, Press 5980.00, Tq 24.00, ROP 20.00, Diff 600.00, Temp 306.00
08/03/2021 | 02:52 | 03:13 | 0.35 | 18234 | 18308 | 74 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18234.00 t/18308.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 211.43, Diff 600.00, Temp 309.00
08/03/2021 | 03:13 | 03:16 | 0.05 | 18308 | 18308 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 03:16 | 03:45 | 0.48 | 18308 | 18401 | 93 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18308.00 t/18401.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 192.41, Diff 600.00, Temp 309.00
08/03/2021 | 03:45 | 03:50 | 0.08 | 18401 | 18401 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 03:50 | 04:24 | 0.57 | 18401 | 18496 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18401.00 t/18496.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 167.65, Diff 600.00, Temp 309.00
08/03/2021 | 04:24 | 04:28 | 0.07 | 18496 | 18496 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 04:28 | 04:42 | 0.23 | 18496 | 18508 | 12 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18496.00 t/18508.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 51.43, Diff 600.00, Temp 309.00
08/03/2021 | 04:42 | 05:12 | 0.5 | 18508 | 18518 | 10 | LAT | 6: BHA 6 | 2J | Slide Drill f/18508.00 t/18518.00, TF G, w/WOB 27.00,Flow 371.00, Press 5980.00, Tq 24.00, ROP 20.00, Diff 600.00, Temp 304.00
08/03/2021 | 05:12 | 05:40 | 0.47 | 18518 | 18593 | 75 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18518.00 t/18593.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 160.71, Diff 600.00, Temp 309.00
08/03/2021 | 05:40 | 06:30 | 0.83 | 18593 | 18593 | 0 | LAT | 6: BHA 6 | 5A | Touble Shoot MWD
08/03/2021 | 06:30 | 06:35 | 0.08 | 18593 | 18593 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
08/03/2021 | 06:35 | 07:03 | 0.47 | 18593 | 18688 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18593.00 t/18688.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 203.57, Diff 600.00, Temp 309.00
08/03/2021 | 07:03 | 07:08 | 0.08 | 18688 | 18688 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 07:08 | 07:20 | 0.2 | 18688 | 18698 | 10 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18688.00 t/18698.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 24.00, ROP 50.00, Diff 600.00, Temp 309.00
08/03/2021 | 07:20 | 08:00 | 0.67 | 18698 | 18708 | 10 | LAT | 6: BHA 6 | 2J | Slide Drill f/18698.00 t/18708.00, TF 180.00G, w/WOB 27.00,Flow 371.00, Press 5980.00, Tq 27, ROP 15.00, Diff 600.00, Temp 309.00
08/03/2021 | 08:00 | 08:20 | 0.33 | 18708 | 18782 | 74 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18708.00 t/18782.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 27, ROP 222.00, Diff 600.00, Temp 309.00
08/03/2021 | 08:20 | 08:25 | 0.08 | 18782 | 18782 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 08:25 | 08:58 | 0.55 | 18782 | 18876 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18782.00 t/18876.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 27.00, ROP 170.91, Diff 600.00, Temp 309.00
08/03/2021 | 08:58 | 09:18 | 0.33 | 18876 | 18876 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 09:18 | 09:43 | 0.42 | 18876 | 18970 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18876.00 t/18970.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 27.00, ROP 225.60, Diff 600.00, Temp 309.00
08/03/2021 | 09:43 | 09:55 | 0.2 | 18970 | 18970 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 09:55 | 10:02 | 0.12 | 18970 | 18993 | 23 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18970.00 t/18993.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 27.00, ROP 197.14, Diff 600.00, Temp 309.00
08/03/2021 | 10:02 | 10:15 | 0.22 | 18993 | 18993 | 0 | LAT | 6: BHA 6 | 5A | Pump Issues / Psi Loss
08/03/2021 | 10:15 | 10:39 | 0.4 | 18993 | 19064 | 71 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18993.00 t/19064.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 27.00, ROP 177.50, Diff 600.00, Temp 309.00
08/03/2021 | 10:39 | 10:45 | 0.1 | 19064 | 19064 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
08/03/2021 | 10:45 | 11:05 | 0.33 | 19064 | 19102 | 38 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19064.00 t/19102.00, w/WOB 27.00,Flow 371.00, RPM 80.00, Press 5980.00, Tq 27.00, ROP 114.00, Diff 600.00, Temp 309.00
08/03/2021 | 11:05 | 11:17 | 0.2 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 5A | Pump Issues
08/03/2021 | 11:17 | 11:20 | 0.05 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 10D | MWD Survey @ TD
08/03/2021 | 11:20 | 14:00 | 2.67 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 5A | Circulate Bottoms Up
08/03/2021 | 14:00 | 16:45 | 2.75 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 3D | Back Ream F/19,102 T/17,578
08/03/2021 | 16:45 | 17:30 | 0.75 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 5A | Circulate Gas Out Of Hole CSG Psi
08/03/2021 | 17:30 | 19:45 | 2.25 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 3D | Back Ream F/17,578 T/15,280
08/03/2021 | 19:45 | 20:30 | 0.75 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 8P | Rig Service
08/03/2021 | 20:30 | 24:00 | 3.5 | 19102 | 19102 | 0 | LAT | 6: BHA 6 | 6B | POOH F/15,280 T/10,056
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_4_2021_DDR
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31153 / 21DD0167MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 20 |  |  | Well: |  | Boone C1H
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Longitude: |  | 96° 44' 37.329" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/04/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7450 |  |  | Well Cost($): |  | 190450
|  |  |  | 24hr Summary: |  | Drill to TD of well, POOH
|  |  |  | 24hr Lookahead: |  | Continue POOH
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 19102 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 38 | PV: | 15
End Depth (Usft): |  | 19102 |  | 19102 |  | OD (in): |  |  |  | 300: | 24 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 13 | Chlorides: | 66000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.40
Drlg/Circ Hrs: |  |  |  | 0.00 / 2.75 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69:31
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 6 | Weight (ppg): | 9.6
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 2.0 / 178.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: |  |  |  | 59.25 |  | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Douglas Ferguson |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Nathan Marks |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 27 | 80 | 332 | 371 | 5980 | 5380 | 0 | 280 | 260 | 150 | 25.2 | 0
Run | 128.38 | 27 | 80 | 332 | 371 | 5980 | 5380 | 0 | 280 | 260 | 150 | 24.78 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 08/04/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 08/04/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 08/04/2021 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 08/04/2021 |  | 23 |  | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 08/04/2021 |  | 8 |  | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 08/04/2021 |  | 12 |  | 9000
Total | [11 empty] | 7450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/04/2021 | 00:00 | 00:15 | 0.25 | 19102 | 19102 | 0 | LAT |  | 8A | C/O Ring Gasket On Top Drive
08/04/2021 | 00:15 | 01:30 | 1.25 | 19102 | 19102 | 0 | LAT |  | 5A | Circulate Bottoms Up
08/04/2021 | 01:30 | 03:00 | 1.5 | 19102 | 19102 | 0 | LAT |  | 5A | Circulate & Spot Mud Cap
08/04/2021 | 03:00 | 04:45 | 1.75 | 19102 | 19102 | 0 | LAT |  | 6B | POOH F/10,056 T/5,941
08/04/2021 | 04:45 | 05:15 | 0.5 | 19102 | 19102 | 0 | LAT |  | 6B | L/D Agitator @ 5,941
08/04/2021 | 05:15 | 07:00 | 1.75 | 19102 | 19102 | 0 | LAT |  | 6B | POOH F/5,919 T/2,804
08/04/2021 | 07:00 | 07:15 | 0.25 | 19102 | 19102 | 0 | LAT |  | 6B | L/D Agitator @ 2,804
08/04/2021 | 07:15 | 08:15 | 1 | 19102 | 19102 | 0 | LAT |  | 6B | POOH F/2,804 T/BHA
08/04/2021 | 08:15 | 10:00 | 1.75 | 19102 | 19102 | 0 | LAT |  | 6P | L/D BHA
08/04/2021 | 10:00 | 24:00 | 14 | 19102 | 19102 | 0 | LAT |  | 24B | CSG Opps.
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 389.90 (Usft)
Well: |  |  | Boone C1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124621 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/19/2021 | Depth In: |  | 105 | Total Drilled: |  | 2620.00 (Usft)
Date Out: |  |  | 06/20/2021 | Depth Out: |  | 2725 | Drilling / Circ Hours: |  | 6.22 / 3.70
Survey Offset: |  |  | 73
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 38426 | U616S | 13.5 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800001 | 7/8 5.9 1.5 Stab HPO -.022 NBS 13 | 8 | 2 | 8.188 / 2.08 | 6 5/8 REG / 6 5/8 REG |  | 38.19 | 39.69
| 3 | SD610174 | Stabalizer | 13 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 7.86 | 47.55
| 4 | SD49205 | NM Pony Drill Collar | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 7.95 | 55.5
| 5 | ZSB775210 | UBHO | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.74 | 59.24
| 6 | SD50132 | NM Drill Collar | 7.875 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.74 | 87.98
| 7 | SD55726 | NM Drill Collar | 7.875 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.8 | 116.78
| 8 | SD104622 | Crossover | 6.5 | 3.062 |  | 4 1/2 IF / 6 5/8 REG |  | 2.08 | 118.86
| 9 | Rig-1 | 9- Joints of 5" HWDP | 5 | 2.5 |  | 4 1/2 IF / 4 1/2 IF |  | 271.04 | 389.9
| 10 | [8 empty] | 389.9
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.18 | Ulterra | U616S | New | 1-1-RR-X-I-RR-TD | 2620
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  | PDCI / 7/8 5.9 | 5.51 / 1.50 |  | 13 | 8.31 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 100 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HPO (Minus) |  | 0.022
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7/8 5.9 1.5 Stab HPO -.022 NBS 13 | 13 |  | 0.4 |  |  | 1.5
3 |  |  | Stabalizer | 13 |  | 0 |  |  | 39.69

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 2564.91 (Usft)
Well: |  |  | Boone C1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124621 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/06/2021 | Depth In: |  | 2725 | Total Drilled: |  | 7305.00 (Usft)
Date Out: |  |  | 07/08/2021 | Depth Out: |  | 10030 | Drilling / Circ Hours: |  | 31.87 / 12.98
Survey Offset: |  |  | 69 | Gamma Offset: |  | 59
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 56410 | SPL613 | 9.875 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | 800033 | 7/8 5.9 2.0 HPO -.020 Slick | 8 | 2 | 7.938 / 1.75 | 6 5/8 REG / 6 5/8 REG |  | 37.58 | 39.08
| 3 | SD51725 | NM Pony Drill Collar | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 8.33 | 47.41
| 4 | ZSB775208 | UBHO | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.83 | 51.24
| 5 | 55727 | NM Drill Collar | 8.062 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 28.76 | 80
| 6 | 53215 | NM Drill Collar | 7.75 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 28.03 | 108.03
| 7 | 118447 | Crossover | 6.75 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.9 | 110.93
| 8 | Rig-3 | 6 Joints of 6 1/2 in DC | 6.5 | 2.75 |  | 4 1/2 XH / 4 1/2 XH |  | 184.12 | 295.05
| 9 | 4555 | Crossover | 6.562 | 2.562 |  | 4 1/2 IF / 4 1/2 XH |  | 3 | 298.05
| 10 | Rig-1 | 9- Joints of 5 HWDP | 5 | 2.5 |  | 4 1/2 IF / 4 1/2 IF |  | 271.04 | 569.09
| 11 | Rig-2 | 21 Stands 5 in DP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 1971.19 | 2540.28
| 12 | PG675-0016 | Agitator | 6.75 | 3.75 |  | 4 1/2 IF / 4 1/2 IF |  | 24.63 | 2564.91
| 13 | [8 empty] | 2564.91
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 0-1-CT-S-X-I-NO-TD | 7305
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.0 HPO -.020 Slick |  |  | PDCI / 7/8 5.9 | 5.92 / 2.00 |  | 0 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 80 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids |  |  | -0.02
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 528.17 (Usft)
Well: |  |  | Boone C1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124621 | Bit #: |  |  | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/08/2021 | Depth In: |  | 10030 | Total Drilled: |  | 0.00 (Usft)
Date Out: |  |  | 07/09/2021 | Depth Out: |  | 10030 | Drilling / Circ Hours: |  | 0.00 / 6.25
Survey Offset: |  |  | 0
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 56410 | SPL613 | 9.875 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800033 | 7/8 5.9 2.0 HPO -.020 Slick | 8 | 2 | 7.938 / 2.07 | 6 5/8 REG / 6 5/8 REG |  | 37.58 | 39.08
| 3 | 53215 | NM Drill Collar | 7.75 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 28.03 | 67.11
| 4 | 118447 | Crossover | 6.75 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.9 | 70.01
| 5 | Rig-3 | 6 Joints of 6 1/2 in DC | 6.5 | 2.75 |  | 4 1/2 XH / 4 1/2 XH |  | 184.12 | 254.13
| 6 | 4555 | Crossover | 6.562 | 2.562 |  | 4 1/2 IF / 4 1/2 XH |  | 3 | 257.13
| 7 | Rig-1 | 9- Joints of 5 HWDP | 5 | 2.5 |  | 4 1/2 IF / 4 1/2 IF |  | 271.04 | 528.17
| 8 | [8 empty] | 528.17
9
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 0.00 |  |  | 0-1-CT-S-N-I-NO-TD |  | 0
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.0 HPO -.020 Slick |  |  | PDCI / 7/8 5.9 | 5.92 / 0.00 |  | 0 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 80 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids |  |  | -0.02

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 5943.44 (Usft)
Well: |  |  | Boone C1H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124621 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/26/2021 | Depth In: |  | 10030 | Total Drilled: |  | 4825.00 (Usft)
Date Out: |  |  | 07/29/2021 | Depth Out: |  | 14855 | Drilling / Circ Hours: |  | 51.25 / 11.12
Survey Offset: |  |  | 69 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13601237 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250007 | 6/7 8.8 2.12 HS 88 .005 Slick | 5 | 2 | 1.97 | XT39 / 3 1/2 Reg |  | 33.15 | 33.9
| 3 | 41014 | BTI | 4.875 | 2.125 |  | XT39 / XT39 |  | 1.65 | 35.55
| 4 | SD56841 | NM Pony Drill Collar | 5.25 | 2.75 |  | XT39 / XT39 |  | 10.51 | 46.06
| 5 | ZSB500050 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 4 | 50.06
| 6 | SD56784 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.81 | 80.87
| 7 | SD56786 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.82 | 111.69
| 8 | A52100 | Tomax | 5.25 | 2.562 | 2.04 | XT39 / XT39 |  | 18.35 | 130.04
| 9 | GT52331431 | Crossover | 5.312 | 2.562 |  | CET43 / XT39 |  | 3.38 | 133.42
| 10 | Rig-4 | 2 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 188.77 | 322.19
| 11 | DTI-DNR-363 | Reamer | 5.375 | 2.562 |  | CET43 / CET43 |  | 8.58 | 330.77
| 12 | Rig-5 | 26 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 2453.38 | 2784.15
| 13 | PG525-0049 | Agitator | 5.25 | 2.812 | 5.250 / 1.82 | CET43 / CET43 |  | 23.46 | 2807.61
| 14 | Rig-6 | 33 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 3114.93 | 5922.54
| 15 | PG525-0037 | Agitator- Ball Drop | 5.25 | 2.812 | 5.250 / 1.75 | CET43 / CET43 |  | 20.9 | 5943.44
| 16 | [8 empty] | 5943.44
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 1-1-WT-S-X-I- | 4825
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 HS 88 .005 Slick |  |  | PDCI / 6/7 8.8 | 4.03 / 2.12 |  | 0 | 5.5 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.005
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
UBHO
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 5943.99 (Usft)
Well: |  |  | Boone C1H | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124621 | Bit #: |  |  | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/30/2021 | Depth In: |  | 14855 | Total Drilled: |  | 2777.00 (Usft)
Date Out: |  |  | 08/01/2021 | Depth Out: |  | 17632 | Drilling / Circ Hours: |  | 28.57 / 18.77
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13594950 | GTD64M | 6.75 | 2 |  | 3 1/2 REG |  | 0.75 | 0.75
| 2 | PPM250015 | 6/7 8.8 2.12 HS 88 .012 Slick | 5 | 2 | 5.000 / 1.75 | XT39 / 3 1/2 Reg |  | 33.02 | 33.77
| 3 | 41016 | BTI | 4.875 | 2.125 |  | XT39 / XT39 |  | 1.64 | 35.41
| 4 | SD56841 | NM Pony Drill Collar | 5.062 | 2.75 |  | XT39 / XT39 |  | 10.51 | 45.92
| 5 | ZSB500025 | UBHO | 5.188 | 2.5 |  | XT39 / XT39 |  | 3.33 | 49.25
| 6 | SD56784 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.81 | 80.06
| 7 | SD56786 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.82 | 110.88
| 8 | A52123 | Tomax | 5 | 2.625 |  | XT39 / XT39 |  | 17.92 | 128.8
| 9 | GT52331431 | Crossover | 5.312 | 2.562 |  | CET43 / XT39 |  | 3.38 | 132.18
| 10 | Rig-4 | 2 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 188.77 | 320.95
| 11 | DTI-DNR-363 | Reamer | 5.375 | 2.562 |  | CET43 / CET43 |  | 8.58 | 329.53
| 12 | Rig-5 | 26 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 2453.38 | 2782.91
| 13 | PG525-0055 | Agitator | 5.562 | 2.625 |  | CET43 / CET43 |  | 24.2 | 2807.11
| 14 | Rig-6 | 33 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 3114.93 | 5922.04
| 15 | PG525-0054 | Agitator | 5.312 | 2.5 |  | CET43 / CET43 |  | 21.95 | 5943.99
| 16 | [8 empty] | 5943.99
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 1-1-RR-N-X-I-RR-PP | 2777
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 HS 88 .012 Slick |  |  | PDCI / 6/7 8.8 | 4.04 / 2.12 |  | 0 | 5.56 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.12
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_6
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 5941.30 (Usft)
Well: |  |  | Boone C1H | BHA #: |  | 6 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124621 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 08/01/2021 | Depth In: |  | 17632 | Total Drilled: |  | 1470.00 (Usft)
Date Out: |  |  | 08/03/2021 | Depth Out: |  | 19102 | Drilling / Circ Hours: |  | 11.45 / 20.32
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13601236 | GTD64M | 6.75 | 2 |  | 3 1/2 REG |  | 0.75 | 0.75
| 2 | PPM250021 | 6/7 8.8 2.12 HS 88 .010 Slick | 5 | 2 | 5.000 / 1.73 | XT39 / 3 1/2 Reg |  | 32.98 | 33.73
| 3 | 41016 | BTI | 4.875 | 2.125 |  | XT39 / XT39 |  | 1.64 | 35.37
| 4 | SD56841 | NM Pony Drill Collar | 5.062 | 2.75 |  | XT39 / XT39 |  | 10.51 | 45.88
| 5 | ZSB500025 | UBHO | 5.188 | 2.5 |  | XT39 / XT39 |  | 3.33 | 49.21
| 6 | SD56784 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.81 | 80.02
| 7 | SD56786 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.82 | 110.84
| 8 | A52123 | Tomax | 5 | 2.625 |  | XT39 / XT39 |  | 17.92 | 128.76
| 9 | GT52331431 | Crossover | 5.312 | 2.562 |  | CET43 / XT39 |  | 3.38 | 132.14
| 10 | Rig-4 | 2 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 188.77 | 320.91
| 11 | DTI-DNR-363 | Reamer | 5.375 | 2.562 |  | CET43 / CET43 |  | 8.58 | 329.49
| 12 | Rig-5 | 26 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 2453.38 | 2782.87
| 13 | PG525-0051 | Agitator | 5.562 | 2.625 |  | CET43 / CET43 |  | 21.55 | 2804.42
| 14 | Rig-6 | 33 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 3114.93 | 5919.35
| 15 | PG525-0057 | Agitator | 5.312 | 2.5 |  | CET43 / CET43 |  | 21.95 | 5941.3
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 1-1-BT-S-X-I-NO-TD | 1470
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 HS 88 .010 Slick |  |  | PDCI / 6/7 8.8 | 4.01 / 2.12 |  | 0 | 5.56 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.12
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Well: |  | Boone C1H
|  |  |  | Longitude: |  | 96° 44' 37.329" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 100.00/105.66/116.00
Date In: |  | 06/19/2021 21:50 |  | SN: |  | PPM800001 |  |  |  | WOB Rotate (klbs): |  | 7.00
Date Out: |  | 06/20/2021 24:00 |  | Description: |  | 7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  |  | WOB Slide (klbs): |  | 5.00
Depth In/Out(Usft): |  | 105.00 / 2725.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 91.43
Inc In/Out: |  | 0.39 / 14.74 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 692.42
Azi In/Out: |  | 210.00 / 248.94 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1308.18
Total Drilled (Usft): |  | 2620 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1568.94
%Slide (Ftg): |  | 7.82 |  | Bit to Bend (Usft): |  | 5.51 |  |  |  | Tq On Btm (kftlbs): |  | 4205.71
%Slide (Time): |  | 23.00 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 205 |  | Bearing Gap (in): |  | 1.14 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 1.43 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.18 |  | Kickpad OD (in): |  | 8.312 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 77.05 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2415 |  | Fishneck OD (in): |  | 8.188 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 4.79 |  | Length (Usft): |  | 38.19 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 6.22 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 3.70 / 26.17 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 143.36 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-RR-X-I-RR-TD
Rot ROP (Usft/hr): |  | 504.18 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HPO (Minus) / 0.022 |  |  |  | Drill Hrs: |  | 6.22
Avg ROP (Usft/hr): |  | 421.22 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.70
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
[10 empty] | WBM |  |  | 116
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
73 | [9 empty] | 1 |  | 0.80 / 1.17
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.18 |  |  |  | 38426 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
7/8 5.9 1.5 Stab HPO -.022 NBS 13 0.00 |  |  |  | PPM800001 |  | 8 | 2 |  |  |  | 38.19 | 39.69
Stabalizer 0.00 |  |  |  | SD610174 |  | 13 | 2.875 |  |  |  | 7.86 | 47.55
NM Pony Drill Collar 0.00 |  |  |  | SD49205 |  | 7.938 | 3.25 |  |  |  | 7.95 | 55.5
UBHO 0.00 |  |  |  | ZSB775210 |  | 7.75 | 2.875 |  |  |  | 3.74 | 59.24
NM Drill Collar 0.00 |  |  |  | SD50132 |  | 7.875 | 3.25 |  |  |  | 28.74 | 87.98
NM Drill Collar 0.00 |  |  |  | SD55726 |  | 7.875 | 3.25 |  |  |  | 28.8 | 116.78
Crossover 0.00 |  |  |  | SD104622 |  | 6.5 | 3.062 |  |  |  | 2.08 | 118.86
9- Joints of 5" HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 2.5 |  |  |  | 271.04 | 389.9
-1.00 | [11 empty] | 389.9
Additional Comments
Did motor drain - Yes Visual Wear ? NO wear on pad and no visible damage to motor. Build/Drop Tendency and Magnitude - Start to 1K build 1 degree /100? to 15 degree to 2725?. Motor performed well with no issues. Start Temp & Max Temp ? 97 - 116 Bit Grade 1-1-RR-X-I-RR-TD Number of Stalls ? No Stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Well: |  | Boone C1H
|  |  |  | Longitude: |  | 96° 44' 37.329" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 111.00/176.46/219.00
Date In: |  | 07/06/2021 02:00 |  | SN: |  | 800033 |  |  |  | WOB Rotate (klbs): |  | 31.00
Date Out: |  | 07/08/2021 18:50 |  | Description: |  | 7/8 5.9 2.0 HPO -.020 Slick |  |  |  | WOB Slide (klbs): |  | 15.39
Depth In/Out(Usft): |  | 2725.00 / 10030.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 78.62
Inc In/Out: |  | 14.74 / 17.13 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 695.79
Azi In/Out: |  | 248.93 / 143.65 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 3588.89
Total Drilled (Usft): |  | 7305 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 3882.05
%Slide (Ftg): |  | 7.62 |  | Bit to Bend (Usft): |  | 5.92 |  |  |  | Tq On Btm (kftlbs): |  | 16797.87
%Slide (Time): |  | 41.64 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 557 |  | Bearing Gap (in): |  | 1.2 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 13.27 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.38 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 58.37 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6748 |  | Fishneck OD (in): |  | 7.938 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 18.6 |  | Length (Usft): |  | 37.58 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 31.87 |  | Integral Float: |  | NO |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 12.98 / 64.83 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 41.97 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-CT-S-X-I-NO-TD
Rot ROP (Usft/hr): |  | 362.8 |  | Stator Vendor/Type/Fit: |  | PV Fluids / / -0.020 |  |  |  | Drill Hrs: |  | 31.87
Avg ROP (Usft/hr): |  | 229.21 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 12.98
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
33 / 21 | 16 / 12 | 6 / 5 |  | 70:30 |  | 12 | 9 | 9.4 | 68000 | OBM | 7.3 |  | 219
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 59 | [10 empty] | 0.00 / 7.08
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 56410 |  | 9.875 | 2 |  |  |  | 1.5 | 1.5
7/8 5.9 2.0 HPO -.020 Slick 0.00 |  |  |  | 800033 |  | 8 | 2 |  |  |  | 37.58 | 39.08
NM Pony Drill Collar 0.00 |  |  |  | SD51725 |  | 7.938 | 3.25 |  |  |  | 8.33 | 47.41
UBHO 0.00 |  |  |  | ZSB775208 |  | 7.75 | 2.875 |  |  |  | 3.83 | 51.24
NM Drill Collar 0.00 |  |  |  | 55727 |  | 8.062 | 3.188 |  |  |  | 28.76 | 80
NM Drill Collar 0.00 |  |  |  | 53215 |  | 7.75 | 3.188 |  |  |  | 28.03 | 108.03
Crossover 0.00 |  |  |  | 118447 |  | 6.75 | 2.875 |  |  |  | 2.9 | 110.93
6 Joints of 6 1/2 in DC 0.00 |  |  |  | Rig-3 |  | 6.5 | 2.75 |  |  |  | 184.12 | 295.05
Crossover 0.00 |  |  |  | 4555 |  | 6.562 | 2.562 |  |  |  | 3 | 298.05
9- Joints of 5 HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 2.5 |  |  |  | 271.04 | 569.09
21 Stands 5 in DP 0.00 |  |  |  | Rig-2 |  | 5 | 3 |  |  |  | 1971.19 | 2540.28
Agitator 0.00 |  |  |  | PG675-0016 |  | 6.75 | 3.75 |  |  |  | 24.63 | 2564.91
-1.00 | [11 empty] | 2564.91
Additional Comments
Did motor drain - Yes Visual Wear ? NO wear on pad and no visible damage to motor. Build/Drop Tendency and Magnitude - Drill intermediate section of well until KOP, began drilling curve section to 14.5?, or until we saw gamma chalk indicator. Pulled out of hole to run intermediate casing. Max Temp ? 233 Bit Grade- 0-1-CT-S-X-I-NO-TD Number of Stalls ? No Stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected ? No Comments ? This BHA Drilled 7,305 With No Stalls Max RPM:80 / Max TQ: 22k / Max Diff: 900 / Max WOB: 42k / Max GPM: 800. With Avrage Motor yields.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Well: |  | Boone C1H
|  |  |  | Longitude: |  | 96° 44' 37.329" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Hole Conditions |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 07/08/2021 24:00 |  | SN: |  | PPM800033 |  |  |  | WOB Rotate (klbs):
Date Out: |  | 07/09/2021 18:00 |  | Description: |  | 7/8 5.9 2.0 HPO -.020 Slick |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10030.00 / 10030.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 17.14 / 17.13 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm):
Azi In/Out: |  | 143.65 / 143.65 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi):
Total Drilled (Usft): |  | 0 |  | Bend Angle: | [5 empty] | On Btm Press (psi):
%Slide (Ftg): |  | 0 |  | Bit to Bend (Usft): |  | 5.92 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 0 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 0 |  | Bearing Gap (in): |  | 2 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 0 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 0 |  | Kickpad OD (in): |  | 8.38 |  |  |  | Make:
%Rotary (Time): |  | 0 |  | Body OD (in): |  | 8 |  |  |  | Model:
Rotary Drilled (Usft): |  | 0 |  | Fishneck OD (in): |  | 7.938 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 0 |  | Length (Usft): |  | 37.58 |  |  |  | TFA: |  | 0.00
Total Drlg Hrs: |  | 0.00 |  | Integral Float: |  | NO |  |  |  | Bit #
Circ/BRT Hrs: |  | 6.25 / 18.00 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | 0-1-CT-S-N-I-NO-TD
Slide ROP (Usft/hr): |  | 0 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 0 |  | Stator Vendor/Type/Fit: |  | PV Fluids / / -0.020 |  |  |  | Drill Hrs: |  | 0.00
Avg ROP (Usft/hr): |  | 0 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 6.25
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
33 / 21 | 16 / 12 | 6 / 5 |  | 70:30 |  | 12 | 9 | 9.4 | 68000 | OBM | 7.3
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 0.00 |  |  |  | 56410 |  | 9.875 | 2 |  |  |  | 1.5 | 1.5
7/8 5.9 2.0 HPO -.020 Slick 0.00 |  |  |  | PPM800033 |  | 8 | 2 |  |  |  | 37.58 | 39.08
NM Drill Collar 0.00 |  |  |  | 53215 |  | 7.75 | 3.188 |  |  |  | 28.03 | 67.11
Crossover 0.00 |  |  |  | 118447 |  | 6.75 | 2.875 |  |  |  | 2.9 | 70.01
6 Joints of 6 1/2 in DC 0.00 |  |  |  | Rig-3 |  | 6.5 | 2.75 |  |  |  | 184.12 | 254.13
Crossover 0.00 |  |  |  | 4555 |  | 6.562 | 2.562 |  |  |  | 3 | 257.13
9- Joints of 5 HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 2.5 |  |  |  | 271.04 | 528.17
-1.00 | [11 empty] | 528.17
Additional Comments
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Well: |  | Boone C1H
|  |  |  | Longitude: |  | 96° 44' 37.329" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Wash Out |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Doug Ferguson |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 217.40/256.18/282.00
Date In: |  | 07/26/2021 12:15 |  | SN: |  | PPM250007 |  |  |  | WOB Rotate (klbs): |  | 31.00
Date Out: |  | 07/29/2021 23:30 |  | Description: |  | 6/7 8.8 2.12 HS 88 .005 Slick |  |  |  | WOB Slide (klbs): |  | 30.20
Depth In/Out(Usft): |  | 10030.00 / 14855.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 75.23
Inc In/Out: |  | 17.14 / 86.61 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 398.65
Azi In/Out: |  | 143.65 / 135.87 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3612.21
Total Drilled (Usft): |  | 4825 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4303.83
%Slide (Ftg): |  | 31.19 |  | Bit to Bend (Usft): |  | 4.03 |  |  |  | Tq On Btm (kftlbs): |  | 5066.16
%Slide (Time): |  | 60.88 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1505 |  | Bearing Gap (in): |  | 1.76 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 31.2 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 68.81 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 39.12 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 3320 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 6.75
Rotary Hours: |  | 20.05 |  | Length (Usft): |  | 33.15 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 51.25 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 11.12 / 83.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 48.24 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-WT-S-X-I-
Rot ROP (Usft/hr): |  | 165.59 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.005 |  |  |  | Drill Hrs: |  | 51.25
Avg ROP (Usft/hr): |  | 94.15 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 11.12
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
33 / 21 | 16 / 12 | 6 / 5 |  | 70:30 |  | 12 | 9 | 9.4 | 68000 | OBM | 7.3 |  | 282
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 56 | [10 empty] | 0.00 / 15.53
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13601237 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 HS 88 .005 Slick 0.00 |  |  |  | PPM250007 |  | 5 | 2 |  |  |  | 33.15 | 33.9
BTI 0.00 |  |  |  | 41014 |  | 4.875 | 2.125 |  |  |  | 1.65 | 35.55
NM Pony Drill Collar 0.00 |  |  |  | SD56841 |  | 5.25 | 2.75 |  |  |  | 10.51 | 46.06
UBHO 0.00 |  |  |  | ZSB500050 |  | 5.25 | 2.5 |  |  |  | 4 | 50.06
NM Drill Collar 0.00 |  |  |  | SD56784 |  | 5 | 2.75 |  |  |  | 30.81 | 80.87
NM Drill Collar 0.00 |  |  |  | SD56786 |  | 5 | 2.75 |  |  |  | 30.82 | 111.69
Tomax 0.00 |  |  |  | A52100 |  | 5.25 | 2.562 |  |  |  | 18.35 | 130.04
Crossover 0.00 |  |  |  | GT52331431 |  | 5.312 | 2.562 |  |  |  | 3.38 | 133.42
2 Stands Drill Pipe 0.00 |  |  |  | Rig-4 |  | 4.5 | 2.5 |  |  |  | 188.77 | 322.19
Reamer 0.00 |  |  |  | DTI-DNR-363 |  | 5.375 | 2.562 |  |  |  | 8.58 | 330.77
26 Stands Drill Pipe 0.00 |  |  |  | Rig-5 |  | 4.5 | 2.5 |  |  |  | 2453.38 | 2784.15
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.812 |  |  |  | 23.46 | 2807.61
33 Stands Drill Pipe 0.00 |  |  |  | Rig-6 |  | 4.5 | 2.5 |  |  |  | 3114.93 | 5922.54
Agitator- Ball Drop 0.00 |  |  |  | PG525-0037 |  | 5.25 | 2.812 |  |  |  | 20.9 | 5943.44
0.00 | [11 empty] | 5943.44
Additional Comments
Did motor drain ? yes Visual Wear ? NO wear on pad and no visible damage to motor. Build/Drop Tendency and Magnitude ? Motor performed as expected yielding 18?s. Max Temp ? 282 Bit Grade ? 1-1-WT-S-X-I-BHA Number of Stalls ? No Stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected ? No Comments ? Once at surface motor drained well with no visible signs of damage. Max TQ:22K, Max Diff:900, Max WOB:35k, Max GPM:400, Max RPM:80. Bit was green with no damage to be seen with one plugged jet. POOH due to pressure loss washout was found on agitator.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Well: |  | Boone C1H
|  |  |  | Longitude: |  | 96° 44' 37.329" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Doug Ferguson |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 282.00/299.48/307.00
Date In: |  | 07/30/2021 01:30 |  | SN: |  | PPM250015 |  |  |  | WOB Rotate (klbs): |  | 31.00
Date Out: |  | 08/01/2021 21:45 |  | Description: |  | 6/7 8.8 2.12 HS 88 .012 Slick |  |  |  | WOB Slide (klbs): |  | 32.07
Depth In/Out(Usft): |  | 14855.00 / 17632.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 86.62 / 86.20 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 398.16
Azi In/Out: |  | 135.87 / 142.62 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4600.82
Total Drilled (Usft): |  | 2777 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5711.54
%Slide (Ftg): |  | 8.71 |  | Bit to Bend (Usft): |  | 4.04 |  |  |  | Tq On Btm (kftlbs): |  | 21.67
%Slide (Time): |  | 50.83 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 242 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 14.52 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 91.29 |  | Kickpad OD (in): |  | 5.562 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 49.18 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2535 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 14.05 |  | Length (Usft): |  | 33.02 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 28.57 |  | Integral Float: |  | NO |  |  |  | Bit #
Circ/BRT Hrs: |  | 18.77 / 68.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 16.67 |  | # Stalls / Pressure: |  | 1 / 0.00 |  |  |  | Grade Out: |  | 1-1-RR-N-X-I-RR-PP
Rot ROP (Usft/hr): |  | 180.43 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.120 |  |  |  | Drill Hrs: |  | 28.57
Avg ROP (Usft/hr): |  | 97.2 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 18.77
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
39 / 24 | 19 / 13 | 6 / 5 |  | 69:31 |  | 15 | 9 | 9.4 | 66000 | OBM | 7.4 |  | 307
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [10 empty] | 0.00 / 5.94
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13594950 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 HS 88 .012 Slick 0.00 |  |  |  | PPM250015 |  | 5 | 2 |  |  |  | 33.02 | 33.77
BTI 0.00 |  |  |  | 41016 |  | 4.875 | 2.125 |  |  |  | 1.64 | 35.41
NM Pony Drill Collar 0.00 |  |  |  | SD56841 |  | 5.062 | 2.75 |  |  |  | 10.51 | 45.92
UBHO 0.00 |  |  |  | ZSB500025 |  | 5.188 | 2.5 |  |  |  | 3.33 | 49.25
NM Drill Collar 0.00 |  |  |  | SD56784 |  | 5 | 2.75 |  |  |  | 30.81 | 80.06
NM Drill Collar 0.00 |  |  |  | SD56786 |  | 5 | 2.75 |  |  |  | 30.82 | 110.88
Tomax 0.00 |  |  |  | A52123 |  | 5 | 2.625 |  |  |  | 17.92 | 128.8
Crossover 0.00 |  |  |  | GT52331431 |  | 5.312 | 2.562 |  |  |  | 3.38 | 132.18
2 Stands Drill Pipe 0.00 |  |  |  | Rig-4 |  | 4.5 | 2.5 |  |  |  | 188.77 | 320.95
Reamer 0.00 |  |  |  | DTI-DNR-363 |  | 5.375 | 2.562 |  |  |  | 8.58 | 329.53
26 Stands Drill Pipe 0.00 |  |  |  | Rig-5 |  | 4.5 | 2.5 |  |  |  | 2453.38 | 2782.91
Agitator 0.00 |  |  |  | PG525-0055 |  | 5.562 | 2.625 |  |  |  | 24.2 | 2807.11
33 Stands Drill Pipe 0.00 |  |  |  | Rig-6 |  | 4.5 | 2.5 |  |  |  | 3114.93 | 5922.04
Agitator 0.00 |  |  |  | PG525-0054 |  | 5.312 | 2.5 |  |  |  | 21.95 | 5943.99
-1.00 | [11 empty] | 5943.99
Additional Comments
Did motor drain ? No Visual Wear ? NO wear on pad and no visible damage to motor. Build/Drop Tendency and Magnitude ? Motor performed as expected yielding 18?s up to the time of the pressure spike. Max Temp ? 306 Bit Grade ? 1-1-RR-N-X-I-RR-PP Number of Stalls ? 1 Reaming - No Back Reaming - Yes Jarring - No Mud Sample Collected ? No Comments ? While sliding at 17,378 Motor stalled presure increased 1,200 Psi and lost MWD pulses. Bled stand pipe pressure off three time slowed GPM From 400 GPM to 377 GPM. Rubber was found at shakers. While circulating pressure came back down to normal. Slacked back down to bottom and drilled 5 feet with no problems continued drilling. After putting in a 21 slide pressure started building and dropping in rotation and MWD stopped pulsing. This BHA slid: 242 / Rotated: 2,535 / Max TQ: 22k / Max Diff: 1,100 Psi / Max WOB: 32k / Max RPM: 80 / Max GPM: 400 / Max Temp: 307?.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 6
|  |  |  | Job # |  | LTX1124621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31153 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.066" N |  |  | Well: |  | Boone C1H
|  |  |  | Longitude: |  | 96° 44' 37.329" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 6
|  |  |  | Lead DD: |  | Doug Ferguson |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 300.00/307.17/309.00
Date In: |  | 08/01/2021 22:45 |  | SN: |  | PPM250021 |  |  |  | WOB Rotate (klbs): |  | 27.00
Date Out: |  | 08/03/2021 24:00 |  | Description: |  | 6/7 8.8 2.12 HS 88 .010 Slick |  |  |  | WOB Slide (klbs): |  | 27.00
Depth In/Out(Usft): |  | 17632.00 / 19102.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 86.19 / 88.60 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 371
Azi In/Out: |  | 142.62 / 140.28 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 5380
Total Drilled (Usft): |  | 1470 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5980
%Slide (Ftg): |  | 3.88 |  | Bit to Bend (Usft): |  | 4.01 |  |  |  | Tq On Btm (kftlbs): |  | 24.78
%Slide (Time): |  | 26.46 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 57 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 3.03 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 96.12 |  | Kickpad OD (in): |  | 5.562 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 73.54 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 1413 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 8.42 |  | Length (Usft): |  | 32.98 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 11.45 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 20.32 / 49.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 18.81 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-BT-S-X-I-NO-TD
Rot ROP (Usft/hr): |  | 167.81 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.120 |  |  |  | Drill Hrs: |  | 11.45
Avg ROP (Usft/hr): |  | 128.38 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 20.32
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
39 / 24 | 19 / 13 | 6 / 5 |  | 69:31 |  | 15 | 9 | 9.4 | 67000 | OBM | 7.4 |  | 309
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [10 empty] | 0.00 / 2.03
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13601236 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 HS 88 .010 Slick 0.00 |  |  |  | PPM250021 |  | 5 | 2 |  |  |  | 32.98 | 33.73
BTI 0.00 |  |  |  | 41016 |  | 4.875 | 2.125 |  |  |  | 1.64 | 35.37
NM Pony Drill Collar 0.00 |  |  |  | SD56841 |  | 5.062 | 2.75 |  |  |  | 10.51 | 45.88
UBHO 0.00 |  |  |  | ZSB500025 |  | 5.188 | 2.5 |  |  |  | 3.33 | 49.21
NM Drill Collar 0.00 |  |  |  | SD56784 |  | 5 | 2.75 |  |  |  | 30.81 | 80.02
NM Drill Collar 0.00 |  |  |  | SD56786 |  | 5 | 2.75 |  |  |  | 30.82 | 110.84
Tomax 0.00 |  |  |  | A52123 |  | 5 | 2.625 |  |  |  | 17.92 | 128.76
Crossover 0.00 |  |  |  | GT52331431 |  | 5.312 | 2.562 |  |  |  | 3.38 | 132.14
2 Stands Drill Pipe 0.00 |  |  |  | Rig-4 |  | 4.5 | 2.5 |  |  |  | 188.77 | 320.91
Reamer 0.00 |  |  |  | DTI-DNR-363 |  | 5.375 | 2.562 |  |  |  | 8.58 | 329.49
26 Stands Drill Pipe 0.00 |  |  |  | Rig-5 |  | 4.5 | 2.5 |  |  |  | 2453.38 | 2782.87
Agitator 0.00 |  |  |  | PG525-0051 |  | 5.562 | 2.625 |  |  |  | 21.55 | 2804.42
33 Stands Drill Pipe 0.00 |  |  |  | Rig-6 |  | 4.5 | 2.5 |  |  |  | 3114.93 | 5919.35
Agitator 0.00 |  |  |  | PG525-0057 |  | 5.312 | 2.5 |  |  |  | 21.95 | 5941.3
Additional Comments
Did motor drain - Yes Visual Wear ? There was no visual wear to be seen. Build/Drop Tendency and Magnitude ? This assembly tracked well and drilled 1,470? of lateral with 4 slides. Start Temp & Max Temp ? Starting temp 302?-309? Bit Grade 1-1-BT-S-X-I-NO-TD Number of Stalls ? No Stalls Reaming ? NO Back Reaming - Back Ream Out F/17,578? ? T/15,280?Jarring - No Mud Sample Collected - No Misc. Comments ? This BHA was used to finish drilling 1,470? of lateral section. Motor had good yield 18?s-20?s and we were able to put four small 10? slides in to keep us in the target window. Max GPM: 378 / Max TQ: 25k / Max RPM: 80 / Max WOB: 27k / Max Diff: 900 Psi. Once at surface motor had no squat and drained with no visible signs of damage. Bit was graded a 1-1 by company man and had two chipped cutters.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2620
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 205
Well Name: |  |  |  |  | Boone C1H |  |  | Survey / Gamma Offset: |  |  |  |  | 73.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.38 |  | Rotate: |  | 2415
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/20/2021 | 02:00 | 02:15 | 0.25 | 105 | 178 | 73 | Rotate |  | 135 | 0.5 | 210 | 135 | -0.51 | -0.29 | -0.51 | 0.37 |  |  | 3 | 40 | 400 | 6 | 292 | 980 | 780 | 200 | 100 | 115 | 110 | 98
06/20/2021 | 02:50 | 03:05 | 0.25 | 178 | 208 | 30 | Rotate | Drilling Parameters WOB: 3; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6; Drilling Parameters ROP: 120 | 980 | 780 | 200 | 100 | 115 | 110 | 98
06/20/2021 | 03:15 | 03:19 | 0.066667 | 208 | 211 | 3 | Rotate | Drilling Parameters WOB: 7; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 500; Drilling Parameters Tq: 6; Drilling Parameters ROP: 45 | 1200 | 780 | 420 | 100 | 115 | 110 | 98
06/20/2021 | 03:30 | 03:50 | 0.33333 | 211 | 300 | 89 | Rotate |  | 227 | 0.5 | 233.2 | 226.99 | -1.1 | -0.82 | -1.1 | 0.22 |  |  | 8 | 60 | 600 | 6 | 267 | 1600 | 1100 | 500 | 100 | 115 | 110 | 98
06/20/2021 | 03:58 | 04:05 | 0.11667 | 300 | 380 | 80 | Rotate |  | 316 | 0.6 | 222.9 | 315.99 | -1.67 | -1.44 | -1.67 | 0.16 |  |  | 8 | 70 | 700 | 8 | 685.71 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 04:10 | 04:14 | 0.066667 | 380 | 389 | 9 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 8; Drilling Parameters ROP: 135 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 04:20 | 04:40 | 0.33333 | 389 | 483 | 94 | Rotate |  | 410 | 0.6 | 227.5 | 409.99 | -2.37 | -2.14 | -2.37 | 0.05 |  |  | 8 | 70 | 700 | 8 | 282 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 04:48 | 05:02 | 0.23333 | 483 | 577 | 94 | Rotate |  | 504 | 0.6 | 232.2 | 503.98 | -3 | -2.89 | -3 | 0.05 |  |  | 8 | 70 | 700 | 8 | 402.86 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 05:08 | 05:18 | 0.16667 | 577 | 640 | 63 | Rotate |  | 598 | 0.74 | 242 | 597.97 | -3.59 | -3.82 | -3.59 | 0.19 |  |  | 8 | 70 | 700 | 8 | 378 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 05:25 | 05:30 | 0.083333 | 640 | 671 | 31 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 8; Drilling Parameters ROP: 372 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 05:35 | 05:38 | 0.05 | 671 | 676 | 5 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 8; Drilling Parameters ROP: 100 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 09:33 | 09:37 | 0.066667 | 676 | 765 | 89 | Rotate |  | 692 | 0.79 | 245.28 | 691.97 | -4.14 | -4.94 | -4.14 | 0.07 |  |  | 8 | 100 | 900 | 4500 | 1335 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 09:43 | 09:56 | 0.21667 | 765 | 858 | 93 | Rotate |  | 785 | 1.05 | 255.66 | 784.95 | -4.62 | -6.35 | -4.62 | 0.33 |  |  | 8 | 100 | 900 | 4500 | 429.23 | 2070 | 1600 | 470 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:03 | 10:09 | 0.1 | 858 | 952 | 94 | Rotate |  | 879 | 1.23 | 271.06 | 878.94 | -4.82 | -8.2 | -4.82 | 0.38 |  |  | 8 | 100 | 700 | 4500 | 940 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:15 | 10:17 | 0.033333 | 952 | 965 | 13 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 390 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:17 | 10:21 | 0.066667 | 965 | 975 | 10 | Slide | 255 | 973 | 1.53 | 262.63 | 972.91 | -4.96 | -10.45 | -4.96 | 0.38 |  |  | 5 |  | 700 |  | 150 | 1200 | 1100 | 100 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:21 | 10:26 | 0.083333 | 975 | 1046 | 71 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 852 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:32 | 10:33 | 0.016667 | 1046 | 1055 | 9 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 540 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:33 | 10:37 | 0.066667 | 1055 | 1065 | 10 | Slide | TTF: 255; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 150 | 1200 | 1100 | 100 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:37 | 10:47 | 0.16667 | 1065 | 1140 | 75 | Rotate |  | 1067 | 2.08 | 254.14 | 1066.86 | -5.59 | -13.33 | -5.59 | 0.65 |  |  | 10 | 100 | 700 | 4500 | 450 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:53 | 10:54 | 0.016667 | 1140 | 1150 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 600 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:54 | 10:57 | 0.05 | 1150 | 1160 | 10 | Slide | TTF: 255; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 200 | 1200 | 1100 | 100 | 102.2 | 125 | 115 | 110
06/20/2021 | 10:57 | 11:04 | 0.11667 | 1160 | 1234 | 74 | Rotate |  | 1161 | 3.03 | 251.07 | 1160.77 | -6.86 | -17.32 | -6.86 | 1.02 |  |  | 10 | 100 | 700 | 4500 | 634.29 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 11:10 | 11:15 | 0.083333 | 1234 | 1328 | 94 | Rotate |  | 1255 | 3.46 | 248.01 | 1254.62 | -8.73 | -22.31 | -8.73 | 0.49 |  |  | 10 | 100 | 700 | 4500 | 1128 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 11:20 | 11:21 | 0.016667 | 1328 | 1335 | 7 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 420 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 11:21 | 11:26 | 0.083333 | 1335 | 1345 | 10 | Slide | TTF: 255; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 120 | 1200 | 1100 | 100 | 104 | 125 | 115 | 110
06/20/2021 | 11:26 | 11:31 | 0.083333 | 1345 | 1422 | 77 | Rotate |  | 1349 | 4.18 | 251.96 | 1348.41 | -10.85 | -28.19 | -10.85 | 0.82 |  |  | 15 | 100 | 700 | 4500 | 924 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 11:36 | 11:44 | 0.13333 | 1422 | 1516 | 94 | Rotate |  | 1443 | 4.62 | 246.97 | 1442.13 | -13.39 | -34.93 | -13.39 | 0.62 |  |  | 15 | 100 | 700 | 4500 | 705 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 11:58 | 11:59 | 0.016667 | 1516 | 1525 | 9 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 540 | 1400 | 1100 | 300 | 102.2 | 125 | 115 | 110
06/20/2021 | 16:00 | 16:06 | 0.1 | 1525 | 1535 | 10 | Slide | TTF: 255; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 100 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 16:06 | 16:14 | 0.13333 | 1535 | 1609 | 74 | Rotate |  | 1536 | 4.99 | 250.6 | 1534.8 | -16.2 | -42.2 | -16.2 | 0.51 |  |  | 15 | 100 | 700 | 4500 | 555 | 1400 | 1100 | 300 | 105 | 125 | 115 | 110
06/20/2021 | 16:20 | 16:21 | 0.016667 | 1609 | 1620 | 11 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 660 | 1400 | 1100 | 300 | 105 | 125 | 115 | 110
06/20/2021 | 16:21 | 16:26 | 0.083333 | 1620 | 1638 | 18 | Slide | 255 | 1630 | 6.09 | 249.78 | 1628.36 | -19.28 | -50.73 | -19.28 | 1.17 |  |  | 5 |  | 700 |  | 216 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 16:26 | 16:31 | 0.083333 | 1638 | 1703 | 65 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 780 | 1400 | 1100 | 300 | 105 | 125 | 115 | 110
06/20/2021 | 16:36 | 16:37 | 0.016667 | 1703 | 1720 | 17 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 1020 | 1400 | 1100 | 300 | 105 | 125 | 115 | 110
06/20/2021 | 16:37 | 16:42 | 0.083333 | 1720 | 1730 | 10 | Slide | 10 | 1724 | 7.01 | 251.05 | 1721.75 | -22.87 | -60.84 | -22.87 | 0.99 |  |  | 5 |  | 700 |  | 120 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 16:42 | 16:48 | 0.1 | 1730 | 1797 | 67 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 670 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 16:53 | 16:54 | 0.016667 | 1797 | 1805 | 8 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 480 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 16:54 | 16:57 | 0.05 | 1805 | 1815 | 10 | Slide | TTF: 10; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 200 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 16:57 | 17:02 | 0.083333 | 1815 | 1891 | 76 | Rotate |  | 1818 | 7.77 | 252.11 | 1814.97 | -26.68 | -72.31 | -26.68 | 0.82 |  |  | 5 | 100 | 700 | 5000 | 912 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:07 | 17:08 | 0.016667 | 1891 | 1900 | 9 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 540 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:08 | 17:14 | 0.1 | 1900 | 1913 | 13 | Slide | 20 | 1912 | 8.52 | 252.27 | 1908.02 | -30.75 | -84.99 | -30.75 | 0.8 |  |  | 5 |  | 700 |  | 130 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:14 | 17:18 | 0.066667 | 1913 | 1985 | 72 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 1080 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:23 | 17:24 | 0.016667 | 1985 | 1995 | 10 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 600 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:24 | 17:27 | 0.05 | 1995 | 2008 | 13 | Slide | 20 | 2006 | 9.31 | 253.26 | 2000.88 | -35.06 | -98.9 | -35.06 | 0.86 |  |  | 5 |  | 700 |  | 260 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:27 | 17:30 | 0.05 | 2008 | 2079 | 71 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 1420 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:35 | 17:38 | 0.05 | 2079 | 2090 | 11 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 220 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:38 | 17:41 | 0.05 | 2090 | 2103 | 13 | Slide | 20 | 2099 | 10.05 | 252.88 | 2092.56 | -39.62 | -113.86 | -39.62 | 0.8 |  |  | 5 |  | 700 |  | 260 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:41 | 17:45 | 0.066667 | 2103 | 2171 | 68 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1020 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:48 | 17:50 | 0.033333 | 2171 | 2180 | 9 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 270 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:50 | 17:54 | 0.066667 | 2180 | 2190 | 10 | Slide | TTF: 10; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 150 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 17:54 | 18:00 | 0.1 | 2190 | 2265 | 75 | Rotate |  | 2194 | 10.63 | 252.81 | 2186.01 | -44.65 | -130.15 | -44.65 | 0.61 |  |  | 5 | 100 | 700 | 6000 | 750 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 18:02 | 18:04 | 0.033333 | 2265 | 2275 | 10 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 300 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 18:04 | 18:14 | 0.16667 | 2275 | 2288 | 13 | Slide | TTF: 20; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 78 | 1200 | 1100 | 100 | 105 | 125 | 115 | 110
06/20/2021 | 18:14 | 18:20 | 0.1 | 2288 | 2360 | 72 | Rotate |  | 2288 | 11.3 | 252.94 | 2278.3 | -49.91 | -147.24 | -49.91 | 0.71 |  |  | 5 | 100 | 700 | 6000 | 720 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 18:24 | 18:28 | 0.066667 | 2360 | 2370 | 10 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 150 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 18:28 | 18:32 | 0.066667 | 2370 | 2383 | 13 | Slide | 20 | 2381 | 11.91 | 251.52 | 2369.4 | -55.63 | -165.05 | -55.63 | 0.72 |  |  | 5 |  | 700 |  | 195 | 2150 | 1950 | 200 | 116 | 125 | 115 | 110
06/20/2021 | 18:32 | 18:39 | 0.11667 | 2383 | 2453 | 70 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 600 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 18:42 | 18:45 | 0.05 | 2453 | 2465 | 12 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 240 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 18:45 | 18:49 | 0.066667 | 2465 | 2479 | 14 | Slide | 20 | 2475 | 12.9 | 251.53 | 2461.2 | -62.03 | -184.21 | -62.03 | 1.05 |  |  | 5 |  | 700 |  | 210 | 2150 | 1950 | 200 | 116 | 125 | 115 | 110
06/20/2021 | 18:49 | 18:55 | 0.1 | 2479 | 2547 | 68 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 680 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 18:59 | 19:03 | 0.066667 | 2547 | 2560 | 13 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 195 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 19:03 | 19:10 | 0.11667 | 2560 | 2574 | 14 | Slide | 20 | 2569 | 13.86 | 250.85 | 2552.65 | -69.05 | -204.79 | -69.05 | 1.03 |  |  | 5 |  | 700 |  | 120 | 2150 | 1950 | 200 | 116 | 125 | 115 | 110
06/20/2021 | 19:10 | 19:20 | 0.16667 | 2574 | 2642 | 68 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 408 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110
06/20/2021 | 19:40 | 19:50 | 0.16667 | 2642 | 2656 | 14 | Slide | 20 | 2652 | 14.62 | 249.67 | 2633.1 | -75.95 | -224.01 | -75.95 | 0.98 |  |  | 5 |  | 700 |  | 84 | 2150 | 1950 | 200 | 116 | 125 | 115 | 110
06/20/2021 | 19:50 | 19:58 | 0.13333 | 2656 | 2725 | 69 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 517.5 | 2395 | 1950 | 445 | 116 | 125 | 115 | 110

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7305
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 557
Well Name: |  |  |  |  | Boone C1H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 59.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.38 |  | Rotate: |  | 6748
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/06/2021 | 08:10 | 08:13 | 0.05 | 2725 | 2735 | 10 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 500; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 200 | 2000 | 1750 | 250 | 111 | 120 | 110 | 100
07/06/2021 | 09:02 | 09:04 | 0.033333 | 2735 | 2750 | 15 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 500; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 450 | 2000 | 1750 | 250 | 111 | 120 | 110 | 100
07/06/2021 | 09:40 | 10:00 | 0.33333 | 2750 | 2846 | 96 | Rotate |  | 2777 | 14.82 | 248.42 | 2753.99 | -87.31 | -253.67 | -87.31 | 0.3 |  |  | 30 | 80 | 680 | 8000 | 288 | 3600 | 2900 | 700 | 111 | 120 | 110 | 100
07/06/2021 | 10:08 | 10:13 | 0.083333 | 2846 | 2940 | 94 | Rotate |  | 2871 | 14.39 | 249.45 | 2844.96 | -95.83 | -275.78 | -95.83 | 0.53 |  |  | 30 | 80 | 680 | 8000 | 1128 | 3600 | 2900 | 700 | 111 | 120 | 110 | 100
07/06/2021 | 10:18 | 10:20 | 0.033333 | 2940 | 2950 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 300 | 3600 | 2900 | 700 | 111 | 120 | 110 | 100
07/06/2021 | 10:20 | 10:28 | 0.13333 | 2950 | 2963 | 13 | Slide | TTF: 60; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 97.5 | 3100 | 2900 | 200 | 118 | 120 | 110 | 100
07/06/2021 | 10:28 | 10:33 | 0.083333 | 2963 | 3034 | 71 | Rotate |  | 2965 | 14.99 | 254.15 | 2935.89 | -103.25 | -298.42 | -103.25 | 1.42 |  |  | 30 | 80 | 680 | 8000 | 852 | 3600 | 2900 | 700 | 118 | 120 | 110 | 100
07/06/2021 | 10:38 | 10:51 | 0.21667 | 3034 | 3128 | 94 | Rotate |  | 3059 | 14.93 | 255.99 | 3026.7 | -109.5 | -321.86 | -109.5 | 0.51 |  |  | 30 | 80 | 680 | 8000 | 433.85 | 3600 | 2900 | 700 | 118 | 120 | 110 | 100
07/06/2021 | 10:56 | 11:11 | 0.25 | 3128 | 3222 | 94 | Rotate |  | 3153 | 14.68 | 255.04 | 3117.58 | -115.51 | -345.11 | -115.51 | 0.37 |  |  | 30 | 80 | 680 | 8000 | 376 | 3600 | 2900 | 700 | 129 | 120 | 110 | 100
07/06/2021 | 11:16 | 11:38 | 0.36667 | 3222 | 3315 | 93 | Rotate |  | 3246 | 14.64 | 253.78 | 3207.55 | -121.83 | -367.78 | -121.83 | 0.35 |  |  | 30 | 80 | 680 | 11000 | 253.64 | 3600 | 2900 | 700 | 132 | 120 | 110 | 100
07/06/2021 | 11:50 | 11:59 | 0.15 | 3315 | 3330 | 15 | Slide | TTF: 40; Drilling Parameters WOB: 14; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 100 | 3100 | 2900 | 200 | 132 | 140 | 125 | 110
07/06/2021 | 15:06 | 15:15 | 0.15 | 3330 | 3409 | 79 | Rotate |  | 3340 | 16.19 | 257.78 | 3298.17 | -127.92 | -392 | -127.92 | 2 |  |  | 30 | 80 | 673 | 11000 | 526.67 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 15:20 | 15:26 | 0.1 | 3409 | 3423 | 14 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 140 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 20:45 | 21:07 | 0.36667 | 3423 | 3503 | 80 | Rotate |  | 3434 | 16.62 | 257.57 | 3388.34 | -133.59 | -417.94 | -133.59 | 0.46 |  |  | 40 | 80 | 683 | 11000 | 218.18 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 21:12 | 21:33 | 0.35 | 3503 | 3596 | 93 | Rotate |  | 3527 | 16.54 | 257.34 | 3477.48 | -139.36 | -443.84 | -139.36 | 0.11 |  |  | 40 | 80 | 683 | 11000 | 265.71 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 21:38 | 22:02 | 0.4 | 3596 | 3691 | 95 | Rotate |  | 3622 | 16.44 | 256.89 | 3568.57 | -145.37 | -470.13 | -145.37 | 0.17 |  |  | 40 | 80 | 683 | 11000 | 237.5 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 22:07 | 22:26 | 0.31667 | 3691 | 3784 | 93 | Rotate |  | 3715 | 16.51 | 255.54 | 3657.75 | -151.65 | -495.74 | -151.65 | 0.42 |  |  | 40 | 80 | 683 | 11000 | 293.68 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 22:31 | 22:50 | 0.31667 | 3784 | 3878 | 94 | Rotate |  | 3809 | 16.46 | 255.34 | 3747.89 | -158.36 | -521.56 | -158.36 | 0.08 |  |  | 40 | 80 | 683 | 11000 | 296.84 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 23:00 | 23:23 | 0.38333 | 3878 | 3972 | 94 | Rotate |  | 3903 | 16.61 | 255.43 | 3838 | -165.11 | -547.44 | -165.11 | 0.16 |  |  | 40 | 80 | 683 | 11000 | 245.22 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/06/2021 | 23:33 | 23:56 | 0.38333 | 3972 | 4067 | 95 | Rotate |  | 3998 | 16.72 | 255.4 | 3929.01 | -171.97 | -573.81 | -171.97 | 0.12 |  |  | 40 | 80 | 683 | 11000 | 247.83 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 00:00 | 00:05 | 0.083333 | 4067 | 4080 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 156 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 00:05 | 00:09 | 0.066667 | 4080 | 4090 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 683; Drilling Parameters ROP: 150 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 00:09 | 00:20 | 0.18333 | 4090 | 4162 | 72 | Rotate |  | 4093 | 15.02 | 255.15 | 4020.39 | -178.57 | -598.93 | -178.57 | 1.79 |  |  | 40 | 80 | 683 | 11000 | 392.73 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 00:25 | 00:39 | 0.23333 | 4162 | 4257 | 95 | Rotate |  | 4188 | 14.31 | 255.08 | 4112.29 | -184.75 | -622.18 | -184.75 | 0.75 |  |  | 40 | 80 | 683 | 11000 | 407.14 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 00:44 | 00:56 | 0.2 | 4257 | 4352 | 95 | Rotate |  | 4283 | 14.11 | 254.32 | 4204.38 | -190.9 | -644.67 | -190.9 | 0.29 |  |  | 40 | 80 | 683 | 11000 | 475 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 00:59 | 01:13 | 0.23333 | 4352 | 4447 | 95 | Rotate |  | 4378 | 14.11 | 252.99 | 4296.52 | -197.42 | -666.89 | -197.42 | 0.34 |  |  | 40 | 80 | 683 | 11000 | 407.14 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 01:18 | 01:20 | 0.033333 | 4447 | 4460 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 390 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 01:20 | 01:25 | 0.083333 | 4460 | 4470 | 10 | Slide | TTF: 50; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 683; Drilling Parameters ROP: 120 | 3500 | 2900 | 600 | 132 | 140 | 125 | 110
07/07/2021 | 01:25 | 01:35 | 0.16667 | 4470 | 4540 | 70 | Rotate |  | 4471 | 14.67 | 254.69 | 4386.6 | -203.84 | -689.09 | -203.84 | 0.75 |  |  | 40 | 80 | 683 | 15000 | 420 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 01:40 | 01:50 | 0.16667 | 4540 | 4634 | 94 | Rotate |  | 4565 | 14.95 | 255.51 | 4477.48 | -210.02 | -712.31 | -210.02 | 0.37 |  |  | 40 | 80 | 683 | 15000 | 564 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 01:55 | 02:06 | 0.18333 | 4634 | 4728 | 94 | Rotate |  | 4659 | 14.98 | 255.81 | 4568.29 | -216.03 | -735.83 | -216.03 | 0.09 |  |  | 40 | 80 | 683 | 15000 | 512.73 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 02:15 | 02:27 | 0.2 | 4728 | 4822 | 94 | Rotate |  | 4753 | 14.77 | 255.5 | 4659.14 | -222.01 | -759.21 | -222.01 | 0.24 |  |  | 40 | 80 | 683 | 15000 | 470 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 02:32 | 02:48 | 0.26667 | 4822 | 4916 | 94 | Rotate |  | 4847 | 14.6 | 255.97 | 4750.07 | -227.88 | -782.3 | -227.88 | 0.22 |  |  | 40 | 80 | 683 | 15000 | 352.5 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 02:53 | 03:03 | 0.16667 | 4916 | 5010 | 94 | Rotate |  | 4941 | 14.33 | 255.06 | 4841.09 | -233.75 | -805.04 | -233.75 | 0.38 |  |  | 40 | 80 | 683 | 15000 | 564 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 03:08 | 03:10 | 0.033333 | 5010 | 5020 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 300 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 03:10 | 03:30 | 0.33333 | 5020 | 5030 | 10 | Slide | TTF: 20; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 683; Drilling Parameters ROP: 30 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 03:30 | 03:42 | 0.2 | 5030 | 5103 | 73 | Rotate |  | 5034 | 13.91 | 256.96 | 4931.28 | -239.24 | -827.05 | -239.24 | 0.67 |  |  | 40 | 80 | 683 | 15000 | 365 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 03:47 | 03:58 | 0.18333 | 5103 | 5197 | 94 | Rotate |  | 5128 | 13.66 | 256.41 | 5022.57 | -244.4 | -848.84 | -244.4 | 0.3 |  |  | 40 | 80 | 683 | 15000 | 512.73 | 3600 | 2900 | 700 | 159 | 145 | 140 | 135
07/07/2021 | 04:03 | 04:06 | 0.05 | 5197 | 5210 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 260 | 3900 | 3200 | 700 | 170 | 155 | 150 | 145
07/07/2021 | 04:06 | 04:19 | 0.21667 | 5210 | 5220 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 683; Drilling Parameters ROP: 46.15 | 3900 | 3200 | 700 | 170 | 155 | 150 | 145
07/07/2021 | 04:19 | 04:30 | 0.18333 | 5220 | 5289 | 69 | Rotate |  | 5222 | 15 | 256.69 | 5113.65 | -249.81 | -871.47 | -249.81 | 1.43 |  |  | 42 | 80 | 683 | 19000 | 376.36 | 3900 | 3200 | 700 | 170 | 155 | 150 | 145
07/07/2021 | 04:35 | 04:46 | 0.18333 | 5289 | 5385 | 96 | Rotate |  | 5316 | 16 | 255.9 | 5204.23 | -255.77 | -895.87 | -255.77 | 1.09 |  |  | 42 | 80 | 683 | 19000 | 523.64 | 3900 | 3200 | 700 | 170 | 155 | 150 | 145
07/07/2021 | 04:51 | 05:02 | 0.18333 | 5385 | 5481 | 96 | Rotate |  | 5412 | 15.71 | 254.9 | 5296.57 | -262.37 | -921.25 | -262.37 | 0.42 |  |  | 42 | 80 | 683 | 19000 | 523.64 | 3900 | 3200 | 700 | 170 | 155 | 150 | 145
07/07/2021 | 05:12 | 05:25 | 0.21667 | 5481 | 5575 | 94 | Rotate |  | 5506 | 15.32 | 253.82 | 5387.15 | -269.15 | -945.47 | -269.15 | 0.52 |  |  | 42 | 80 | 683 | 19000 | 433.85 | 3900 | 3200 | 700 | 170 | 155 | 150 | 145
07/07/2021 | 05:30 | 05:42 | 0.2 | 5575 | 5670 | 95 | Rotate |  | 5601 | 15.34 | 252.81 | 5478.77 | -276.36 | -969.52 | -276.36 | 0.28 |  |  | 35 | 80 | 683 | 20000 | 475 | 3900 | 3200 | 700 | 170 | 175 | 150 | 140
07/07/2021 | 05:47 | 05:50 | 0.05 | 5670 | 5680 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 200 | 3900 | 3200 | 700 | 170 | 175 | 150 | 140
07/07/2021 | 05:50 | 06:00 | 0.16667 | 5680 | 5695 | 15 | Slide | 90 | 5694 | 16.56 | 253.29 | 5568.19 | -283.81 | -993.97 | -283.81 | 1.32 |  |  | 18 |  | 683 |  | 90 | 3500 | 3200 | 300 | 170 | 175 | 150 | 140
07/07/2021 | 06:00 | 06:08 | 0.13333 | 5695 | 5763 | 68 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 510 | 3900 | 3200 | 700 | 170 | 175 | 150 | 140
07/07/2021 | 06:13 | 06:24 | 0.18333 | 5763 | 5857 | 94 | Rotate |  | 5788 | 17.14 | 253.08 | 5658.15 | -291.69 | -1020.05 | -291.69 | 0.62 |  |  | 35 | 80 | 683 | 20000 | 512.73 | 3900 | 3200 | 700 | 170 | 175 | 150 | 140
07/07/2021 | 06:30 | 06:32 | 0.033333 | 5857 | 5865 | 8 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 240 | 3900 | 3200 | 700 | 170 | 175 | 150 | 140
07/07/2021 | 06:32 | 06:42 | 0.16667 | 5865 | 5885 | 20 | Slide | 130 | 5882 | 16.03 | 256.46 | 5748.24 | -298.76 | -1045.92 | -298.76 | 1.56 |  |  | 18 |  | 683 |  | 120 | 3500 | 3200 | 300 | 170 | 175 | 150 | 140
07/07/2021 | 06:42 | 06:52 | 0.16667 | 5885 | 5951 | 66 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 396 | 3900 | 3200 | 700 | 183 | 175 | 150 | 140
07/07/2021 | 06:57 | 07:06 | 0.15 | 5951 | 6045 | 94 | Rotate |  | 5976 | 14.81 | 257.44 | 5838.86 | -304.41 | -1070.27 | -304.41 | 1.33 |  |  | 35 | 80 | 683 | 20000 | 626.67 | 3900 | 3200 | 700 | 183 | 175 | 150 | 140
07/07/2021 | 07:10 | 07:19 | 0.15 | 6045 | 6139 | 94 | Rotate |  | 6070 | 14.26 | 257.43 | 5929.85 | -309.54 | -1093.29 | -309.54 | 0.59 |  |  | 35 | 80 | 683 | 20000 | 626.67 | 3900 | 3200 | 700 | 183 | 175 | 150 | 140
07/07/2021 | 07:25 | 07:39 | 0.23333 | 6139 | 6233 | 94 | Rotate |  | 6164 | 14.27 | 257.01 | 6020.95 | -314.67 | -1115.88 | -314.67 | 0.11 |  |  | 35 | 80 | 683 | 20000 | 402.86 | 3900 | 3200 | 700 | 183 | 175 | 150 | 140
07/07/2021 | 07:44 | 07:54 | 0.16667 | 6233 | 6327 | 94 | Rotate |  | 6258 | 14.09 | 257.39 | 6112.08 | -319.77 | -1138.34 | -319.77 | 0.22 |  |  | 35 | 80 | 683 | 20000 | 564 | 3900 | 3200 | 700 | 183 | 175 | 150 | 140
07/07/2021 | 08:00 | 08:11 | 0.18333 | 6327 | 6422 | 95 | Rotate |  | 6353 | 13.55 | 256.75 | 6204.33 | -324.85 | -1160.46 | -324.85 | 0.59 |  |  | 35 | 80 | 683 | 20000 | 518.18 | 4000 | 3300 | 700 | 183 | 210 | 180 | 150
07/07/2021 | 08:15 | 08:18 | 0.05 | 6422 | 6435 | 13 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 260 | 4000 | 3300 | 700 | 183 | 210 | 180 | 150
07/07/2021 | 08:18 | 08:36 | 0.3 | 6435 | 6455 | 20 | Slide | 30 | 6447 | 14.01 | 259.27 | 6295.63 | -329.49 | -1182.35 | -329.49 | 0.8 |  |  | 18 |  | 683 |  | 66.67 | 3500 | 3300 | 200 | 183 | 210 | 200 | 150
07/07/2021 | 08:36 | 08:46 | 0.16667 | 6455 | 6516 | 61 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 366 | 4000 | 3300 | 700 | 183 | 210 | 180 | 150
07/07/2021 | 08:50 | 09:02 | 0.2 | 6516 | 6609 | 93 | Rotate |  | 6540 | 14.18 | 260.62 | 6385.83 | -333.44 | -1204.65 | -333.44 | 0.4 |  |  | 35 | 80 | 683 | 20000 | 465 | 4000 | 3300 | 700 | 183 | 210 | 180 | 150
07/07/2021 | 09:07 | 09:19 | 0.2 | 6609 | 6703 | 94 | Rotate |  | 6634 | 14.27 | 260.54 | 6476.95 | -337.22 | -1227.44 | -337.22 | 0.1 |  |  | 35 | 80 | 683 | 20000 | 470 | 4000 | 3300 | 700 | 183 | 210 | 180 | 150
07/07/2021 | 09:25 | 09:33 | 0.13333 | 6703 | 6798 | 95 | Rotate |  | 6729 | 13.43 | 261.18 | 6569.18 | -340.84 | -1249.89 | -340.84 | 0.9 |  |  | 35 | 80 | 683 | 20000 | 712.5 | 4000 | 3300 | 700 | 183 | 210 | 180 | 150
07/07/2021 | 09:39 | 09:42 | 0.05 | 6798 | 6815 | 17 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 340 | 4000 | 3300 | 700 | 190 | 210 | 180 | 150
07/07/2021 | 09:42 | 09:59 | 0.28333 | 6815 | 6835 | 20 | Slide | -30 | 6822 | 13.92 | 256.86 | 6659.55 | -345.04 | -1271.46 | -345.04 | 1.22 |  |  | 18 |  | 683 |  | 70.59 | 3500 | 3300 | 200 | 190 | 210 | 200 | 150
07/07/2021 | 09:59 | 10:07 | 0.13333 | 6835 | 6891 | 56 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 683; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 420 | 4000 | 3300 | 700 | 190 | 210 | 180 | 150
07/07/2021 | 10:12 | 10:22 | 0.16667 | 6891 | 6985 | 94 | Rotate |  | 6916 | 14.59 | 255.21 | 6750.65 | -350.63 | -1293.92 | -350.63 | 0.83 |  |  | 35 | 80 | 683 | 20000 | 564 | 4000 | 3300 | 700 | 190 | 210 | 180 | 150
07/07/2021 | 10:27 | 10:37 | 0.16667 | 6985 | 7079 | 94 | Rotate |  | 7010 | 13.64 | 255.37 | 6841.82 | -356.45 | -1316.09 | -356.45 | 1.01 |  |  | 35 | 80 | 700 | 20000 | 564 | 4000 | 3300 | 700 | 190 | 210 | 180 | 150
07/07/2021 | 10:42 | 10:45 | 0.05 | 7079 | 7090 | 11 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 220 | 4000 | 3300 | 700 | 190 | 210 | 180 | 150
07/07/2021 | 10:45 | 11:02 | 0.28333 | 7090 | 7110 | 20 | Slide | 0 | 7103 | 14.41 | 252.18 | 6932.04 | -362.76 | -1337.71 | -362.76 | 1.17 |  |  | 18 |  | 700 |  | 70.59 | 4000 | 3300 | 700 | 190 | 210 | 180 | 150
07/07/2021 | 11:02 | 11:11 | 0.15 | 7110 | 7172 | 62 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 413.33 | 4000 | 3300 | 700 | 197 | 210 | 180 | 150
07/07/2021 | 11:15 | 11:27 | 0.2 | 7172 | 7266 | 94 | Rotate |  | 7197 | 14.64 | 253.2 | 7023.04 | -369.77 | -1360.22 | -369.77 | 0.37 |  |  | 35 | 80 | 700 | 20000 | 470 | 4000 | 3300 | 700 | 197 | 210 | 180 | 150
07/07/2021 | 11:33 | 11:58 | 0.41667 | 7266 | 7360 | 94 | Rotate |  | 7291 | 13.01 | 255.21 | 7114.31 | -375.91 | -1381.83 | -375.91 | 1.81 |  |  | 35 | 80 | 850 | 20000 | 225.6 | 5800 | 4800 | 1000 | 197 | 230 | 195 | 170
07/07/2021 | 12:03 | 12:07 | 0.066667 | 7360 | 7370 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 850; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 150 | 5800 | 4800 | 1000 | 197 | 230 | 195 | 170
07/07/2021 | 12:07 | 12:32 | 0.41667 | 7370 | 7410 | 40 | Slide | 0 | 7385 | 13.82 | 256.1 | 7205.75 | -381.31 | -1402.95 | -381.31 | 0.89 |  |  | 18 |  | 850 |  | 96 | 5100 | 4800 | 300 | 190 | 230 | 195 | 170
07/07/2021 | 12:32 | 12:38 | 0.1 | 7410 | 7454 | 44 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 850; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 440 | 5800 | 4800 | 1000 | 197 | 230 | 195 | 170
07/07/2021 | 12:44 | 12:53 | 0.15 | 7454 | 7548 | 94 | Rotate |  | 7479 | 14.6 | 258.01 | 7296.87 | -386.47 | -1425.44 | -386.47 | 0.97 |  |  | 35 | 80 | 850 | 20000 | 626.67 | 5800 | 4800 | 1000 | 197 | 230 | 195 | 170
07/07/2021 | 12:59 | 13:07 | 0.13333 | 7548 | 7642 | 94 | Rotate |  | 7573 | 12.73 | 261.27 | 7388.21 | -390.5 | -1447.27 | -390.5 | 2.15 |  |  | 35 | 80 | 850 | 20000 | 705 | 5800 | 4800 | 1000 | 197 | 230 | 195 | 170
07/07/2021 | 13:17 | 13:20 | 0.05 | 7642 | 7650 | 8 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 160 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 13:20 | 13:39 | 0.31667 | 7650 | 7680 | 30 | Slide | -30 | 7667 | 12.9 | 258.18 | 7479.87 | -394.22 | -1467.78 | -394.22 | 0.75 |  |  | 18 |  | 700 |  | 94.74 | 3800 | 3500 | 300 | 203 | 230 | 195 | 150
07/07/2021 | 13:39 | 13:47 | 0.13333 | 7680 | 7736 | 56 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 420 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 13:52 | 14:03 | 0.18333 | 7736 | 7830 | 94 | Rotate |  | 7761 | 11.64 | 259.86 | 7571.72 | -398.04 | -1487.38 | -398.04 | 1.39 |  |  | 35 | 80 | 700 | 20000 | 512.73 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 14:07 | 14:19 | 0.2 | 7830 | 7924 | 94 | Rotate |  | 7855 | 10.02 | 261.84 | 7664.04 | -400.87 | -1504.81 | -400.87 | 1.77 |  |  | 35 | 80 | 700 | 20000 | 470 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 14:25 | 14:28 | 0.05 | 7924 | 7935 | 11 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 220 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 14:28 | 14:52 | 0.4 | 7935 | 7965 | 30 | Slide | -50 | 7949 | 10.88 | 253.64 | 7756.49 | -404.53 | -1521.42 | -404.53 | 1.83 |  |  | 18 |  | 700 |  | 75 | 3800 | 3500 | 300 | 203 | 230 | 195 | 150
07/07/2021 | 14:52 | 15:02 | 0.16667 | 7965 | 8018 | 53 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 318 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 15:07 | 15:17 | 0.16667 | 8018 | 8112 | 94 | Rotate |  | 8043 | 10.65 | 252.25 | 7848.83 | -409.68 | -1538.21 | -409.68 | 0.37 |  |  | 35 | 80 | 700 | 20000 | 564 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 15:22 | 15:39 | 0.28333 | 8112 | 8205 | 93 | Rotate |  | 8136 | 9.42 | 253.02 | 7940.41 | -414.52 | -1553.67 | -414.52 | 1.33 |  |  | 35 | 80 | 700 | 20000 | 328.24 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 15:45 | 15:56 | 0.18333 | 8205 | 8299 | 94 | Rotate |  | 8230 | 8.2 | 252.88 | 8033.3 | -418.74 | -1567.44 | -418.74 | 1.3 |  |  | 35 | 80 | 700 | 20000 | 512.73 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 16:00 | 16:11 | 0.18333 | 8299 | 8393 | 94 | Rotate |  | 8324 | 6.86 | 253.13 | 8126.49 | -422.34 | -1579.21 | -422.34 | 1.43 |  |  | 35 | 80 | 700 | 20000 | 512.73 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 16:16 | 16:20 | 0.066667 | 8393 | 8405 | 12 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 180 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 16:20 | 16:55 | 0.58333 | 8405 | 8420 | 15 | Slide | 0 | 8418 | 6.31 | 251.12 | 8219.87 | -425.64 | -1589.47 | -425.64 | 0.63 |  |  | 18 |  | 700 |  | 25.71 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 17:04 | 17:09 | 0.083333 | 8420 | 8425 | 5 | Slide | TTF: 30; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 60 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 17:09 | 17:19 | 0.16667 | 8425 | 8487 | 62 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 372 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 17:27 | 17:33 | 0.1 | 8487 | 8500 | 13 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 130 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 17:33 | 17:57 | 0.4 | 8500 | 8530 | 30 | Slide | 30 | 8511 | 8.43 | 251.8 | 8312.09 | -429.43 | -1600.79 | -429.43 | 2.28 |  |  | 16 |  | 700 | 20000 | 75 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 17:57 | 18:05 | 0.13333 | 8530 | 8580 | 50 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 375 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 18:10 | 18:22 | 0.2 | 8580 | 8674 | 94 | Rotate |  | 8605 | 9.57 | 254.2 | 8404.93 | -433.71 | -1614.85 | -433.71 | 1.28 |  |  | 35 | 80 | 700 | 20000 | 470 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 18:26 | 18:40 | 0.23333 | 8674 | 8768 | 94 | Rotate |  | 8699 | 8.8 | 256.01 | 8497.73 | -437.57 | -1629.35 | -437.57 | 0.87 |  |  | 35 | 80 | 700 | 20000 | 402.86 | 4000 | 3300 | 700 | 203 | 210 | 180 | 150
07/07/2021 | 18:45 | 18:58 | 0.21667 | 8768 | 8862 | 94 | Rotate |  | 8793 | 8.09 | 258.44 | 8590.71 | -440.64 | -1642.81 | -440.64 | 0.85 |  |  | 35 | 80 | 700 | 20000 | 433.85 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 19:02 | 19:16 | 0.23333 | 8862 | 8956 | 94 | Rotate |  | 8887 | 6.92 | 258.57 | 8683.9 | -443.08 | -1654.84 | -443.08 | 1.24 |  |  | 35 | 80 | 700 | 20000 | 402.86 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 19:21 | 19:35 | 0.23333 | 8956 | 9050 | 94 | Rotate |  | 8981 | 5.76 | 257.38 | 8777.32 | -445.24 | -1664.99 | -445.24 | 1.24 |  |  | 35 | 80 | 700 | 20000 | 402.86 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 19:40 | 19:54 | 0.23333 | 9050 | 9144 | 94 | Rotate |  | 9075 | 4.63 | 255.17 | 8870.94 | -447.24 | -1673.26 | -447.24 | 1.22 |  |  | 35 | 80 | 700 | 20000 | 402.86 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 19:59 | 20:05 | 0.1 | 9144 | 9155 | 11 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 110 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 20:05 | 20:42 | 0.61667 | 9155 | 9175 | 20 | Slide | 50 | 9169 | 2.6 | 241.43 | 8964.75 | -449.23 | -1678.8 | -449.23 | 2.33 |  |  | 16 |  | 700 |  | 32.43 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 21:00 | 21:18 | 0.3 | 9175 | 9331 | 156 | Rotate |  | 9262 | 1.41 | 221.94 | 9057.69 | -451.09 | -1681.42 | -451.09 | 1.46 |  |  | 35 | 80 | 700 | 20000 | 520 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 21:23 | 21:25 | 0.033333 | 9331 | 9340 | 9 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 270 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 21:25 | 22:00 | 0.58333 | 9340 | 9355 | 15 | Slide | TTF: 15; Drilling Parameters WOB: 16; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 25.71 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 22:00 | 22:31 | 0.51667 | 9355 | 9425 | 70 | Rotate |  | 9356 | 0.4 | 339.27 | 9151.68 | -451.64 | -1682.31 | -451.64 | 1.74 |  |  | 35 | 80 | 700 | 20000 | 135.48 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 22:36 | 23:01 | 0.41667 | 9425 | 9519 | 94 | Rotate |  | 9450 | 0.63 | 356.15 | 9245.68 | -450.82 | -1682.46 | -450.82 | 0.29 |  |  | 35 | 80 | 700 | 20000 | 225.6 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 23:06 | 23:25 | 0.31667 | 9519 | 9613 | 94 | Rotate |  | 9544 | 0.41 | 41.44 | 9339.67 | -450.05 | -1682.27 | -450.05 | 0.48 |  |  | 35 | 80 | 700 | 20000 | 296.84 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 23:30 | 23:45 | 0.25 | 9613 | 9686 | 73 | Rotate |  | 9638 | 0.32 | 46.31 | 9433.67 | -449.62 | -1681.86 | -449.62 | 0.1 |  |  | 35 | 80 | 700 | 20000 | 292 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/07/2021 | 23:45 | 24:00 | 0.25 | 9686 | 9688 | 2 | Slide | TTF: 140; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 8 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/08/2021 | 00:00 | 00:45 | 0.75 | 9688 | 9707 | 19 | Slide | TTF: 140; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 700; Drilling Parameters ROP: 25.33 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/08/2021 | 00:50 | 04:06 | 3.2667 | 9707 | 9801 | 94 | Slide | 140 | 9732 | 3.43 | 142.55 | 9527.62 | -451.67 | -1679.96 | -451.67 | 3.7 |  |  | 12 |  | 700 |  | 28.78 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/08/2021 | 04:50 | 08:15 | 3.4167 | 9801 | 9895 | 94 | Slide | 140 | 9826 | 10.04 | 149.79 | 9620.92 | -460.99 | -1674.12 | -460.99 | 7.08 |  |  | 12 |  | 700 |  | 27.51 | 4000 | 3300 | 700 | 219 | 220 | 190 | 150
07/08/2021 | 08:20 | 09:37 | 1.2833 | 9895 | 10030 | 135 | Rotate |  | 9961 | 14.48 | 143.86 | 9752.81 | -484.81 | -1658.24 | -484.81 | 3.41 |  |  | 35 | 30 | 850 | 18000 | 105.19 | 5200 | 47000 | -41800 | 219 | 220 | 190 | 150

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 4825
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1505
Well Name: |  |  |  |  | Boone C1H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.38 |  | Rotate: |  | 3320
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/26/2021 | 19:20 | 19:30 | 0.16667 | 10030 | 10041 | 11 | Rotate | Drilling Parameters WOB: 20.01; Drilling Parameters RPM: 44.69; Drilling Parameters FLOW: 375.82; Drilling Parameters Tq: 10.7; Drilling Parameters ROP: 66 | 3575.18 | 3018.08 | 557.1 | 217.4 | 250 | 157.34 | 165
07/26/2021 | 20:43 | 21:51 | 1.1333 | 10041 | 10080 | 39 | Slide | TTF: 5.96; Drilling Parameters WOB: 13.94; Drilling Parameters RPM: 20; Drilling Parameters FLOW: 375.75; Drilling Parameters Tq: 3; Drilling Parameters ROP: 34.41 | 3678.46 |  |  | 217.4 | 250 | 157.34 | 165
07/26/2021 | 21:54 | 22:10 | 0.26667 | 10080 | 10093 | 13 | Rotate | Drilling Parameters WOB: 23.55; Drilling Parameters RPM: 44.7; Drilling Parameters FLOW: 375.82; Drilling Parameters Tq: 11.25; Drilling Parameters ROP: 48.75 | 3582.42 | 3186.23 | 396.19 | 217.4 | 250 | 157.35 | 165
07/26/2021 | 22:14 | 23:04 | 0.83333 | 10093 | 10172 | 79 | Slide | 99.47 | 10124 | 20.75 | 143.45 | 9908.09 | -524.5 | -1628.99 | -524.5 | 3.85 |  |  | 17.46 | 20 | 375.81 | 3 | 94.8 | 3917.6 | 1733.42 | 2184.18 | 219.2 | 250 | 157.35 | 165
07/26/2021 | 23:04 | 23:22 | 0.3 | 10172 | 10193 | 21 | Rotate | Drilling Parameters WOB: 27.54; Drilling Parameters RPM: 44.62; Drilling Parameters FLOW: 399.47; Drilling Parameters Tq: 10.8; Drilling Parameters ROP: 70 | 4211.65 | 3316.75 | 894.9 | 222.8 | 250 | 161.48 | 165
07/26/2021 | 23:25 | 00:00 | 0 | 10193 | 10255 | 62 | Slide | -11 | 10219 | 27.56 | 142.72 | 9994.72 | -555.54 | -1605.63 | -555.54 | 7.18 |  |  | 27.85 | 20 | 399.47 | 3.2 | 106.29 | 4220.65 | 3316.75 | 903.9 | 222.8 | 250 | 161.48 | 165
07/27/2021 | 00:00 | 00:20 | 0.33333 | 10255 | 10275 | 20 | Slide | TTF: -7.29; Drilling Parameters WOB: 17.31; Drilling Parameters RPM: 20; Drilling Parameters FLOW: 399.36; Drilling Parameters Tq: 3.2; Drilling Parameters ROP: 60 | 4228.44 | 3316.75 | 911.69 | 222.8 | 250 | 161.48 | 165
07/27/2021 | 00:20 | 00:24 | 0.066667 | 10275 | 10288 | 13 | Rotate | Drilling Parameters WOB: 22.53; Drilling Parameters RPM: 44.71; Drilling Parameters FLOW: 399.47; Drilling Parameters Tq: 11.6; Drilling Parameters ROP: 195 | 4200 | 3573.63 | 626.37 | 224.6 | 250 | 157.4 | 165
07/27/2021 | 00:27 | 01:38 | 1.1833 | 10288 | 10383 | 95 | Slide | -15 | 10314 | 35.39 | 139.67 | 10075.68 | -594.06 | -1574.47 | -594.06 | 8.41 |  |  | 11.68 | 20 | 399.42 | 3.2 | 80.28 | 4087.28 | 3901.9 | 185.38 | 228.2 | 250 | 160.94 | 165
07/27/2021 | 01:41 | 02:40 | 0.98333 | 10383 | 10477 | 94 | Slide | -10 | 10408 | 45.6 | 142.05 | 10147.08 | -641.42 | -1536.09 | -641.42 | 10.98 |  |  | 19.99 | 20 | 399.52 | 3.2 | 95.59 | 3848.89 | 3766.83 | 82.06 | 230 | 250 | 157.14 | 165
07/27/2021 | 02:43 | 03:20 | 0.61667 | 10477 | 10522 | 45 | Slide | 20 | 10502 | 56.34 | 136.52 | 10206.21 | -696.47 | -1488.36 | -696.47 | 12.3 |  |  | 25.79 | 30 | 399.45 | 4.5 | 72.97 | 4037.65 | 3750 | 287.65 | 230 | 250 | 157.14 | 165
07/27/2021 | 03:20 | 03:31 | 0.18333 | 10522 | 10532 | 10 | Rotate | Drilling Parameters WOB: 25.79; Drilling Parameters RPM: 45; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 13.5; Drilling Parameters ROP: 54.55 | 4200 | 3750 | 450 | 232 | 250 | 157.14 | 165
07/27/2021 | 03:36 | 03:55 | 0.31667 | 10532 | 10552 | 20 | Rotate | Drilling Parameters WOB: 25.79; Drilling Parameters RPM: 45; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 13.5; Drilling Parameters ROP: 63.16 | 4200 | 3750 | 450 | 232 | 250 | 157.14 | 165
07/27/2021 | 03:55 | 04:17 | 0.36667 | 10552 | 10571 | 19 | Slide | TTF: 20; Drilling Parameters WOB: 25.79; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 4.5; Drilling Parameters ROP: 51.82 | 4037.65 | 3750 | 287.65 | 232 | 250 | 157.14 | 165
07/27/2021 | 04:20 | 05:10 | 0.83333 | 10571 | 10648 | 77 | Slide | 30 | 10597 | 61.37 | 137.15 | 10255.33 | -755.77 | -1432.77 | -755.77 | 5.33 |  |  | 25.79 | 30 | 399.45 | 4.5 | 92.4 | 4037.65 | 3750 | 287.65 | 234 | 250 | 157.14 | 165
07/27/2021 | 05:10 | 05:27 | 0.28333 | 10648 | 10666 | 18 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 45; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 13.5; Drilling Parameters ROP: 63.53 | 4200 | 3750 | 450 | 234 | 250 | 157.14 | 165
07/27/2021 | 05:30 | 07:00 | 1.5 | 10666 | 10760 | 94 | Slide | 0 | 10691 | 69.86 | 143.09 | 10294.14 | -821.46 | -1378.07 | -821.46 | 10.71 |  |  | 25 | 30 | 399.45 | 3.8 | 62.67 | 4200 | 3750 | 450 | 237 | 250 | 157.14 | 165
07/27/2021 | 07:10 | 08:58 | 1.8 | 10760 | 10822 | 62 | Slide | 0 | 10785 | 78.82 | 139.58 | 10319.49 | -892.01 | -1321.54 | -892.01 | 10.19 |  |  | 25 | 30 | 399.45 | 3.8 | 34.44 | 4200 | 3750 | 450 | 237 | 250 | 157.14 | 165
07/27/2021 | 09:00 | 09:46 | 0.76667 | 10822 | 10854 | 32 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 3.8; Drilling Parameters ROP: 41.74 | 4200 | 3750 | 450 | 237 | 250 | 157.14 | 165
07/27/2021 | 10:00 | 10:30 | 0.5 | 10854 | 10869 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 3.8; Drilling Parameters ROP: 30 | 4200 | 3750 | 450 | 237 | 250 | 157.14 | 165
07/27/2021 | 10:30 | 11:00 | 0.5 | 10869 | 10948 | 79 | Rotate |  | 10879 | 90.51 | 138.15 | 10328.22 | -962.37 | -1260.07 | -962.37 | 12.53 |  |  | 27 | 45 | 399.45 | 15000 | 158 | 4200 | 3750 | 450 | 237 | 250 | 157.14 | 165
07/27/2021 | 11:07 | 11:13 | 0.1 | 10948 | 10958 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 45; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 100 | 4200 | 3750 | 450 | 237 | 250 | 157.14 | 165
07/27/2021 | 11:13 | 11:38 | 0.41667 | 10958 | 10978 | 20 | Slide | 140 | 10974 | 89.54 | 140.19 | 10328.17 | -1034.25 | -1197.97 | -1034.25 | 2.38 |  |  | 25 |  | 399.45 | 15000 | 48 | 4200 | 3750 | 450 | 237 | 240 | 165 | 150
07/27/2021 | 11:38 | 11:53 | 0.25 | 10978 | 11043 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 260 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 11:58 | 12:04 | 0.1 | 11043 | 11053 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 100 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 12:04 | 12:42 | 0.63333 | 11053 | 11065 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 27; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 18.95 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 12:42 | 12:55 | 0.21667 | 11065 | 11085 | 20 | Rotate |  | 11068 | 89.41 | 140.88 | 10329.03 | -1106.81 | -1138.22 | -1106.81 | 0.75 |  |  | 35 | 80 | 399.45 | 18000 | 92.31 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 12:55 | 13:50 | 0.91667 | 11085 | 11110 | 25 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 399.45; Drilling Parameters ROP: 27.27 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 13:50 | 13:57 | 0.11667 | 11110 | 11137 | 27 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 231.43 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 14:00 | 14:10 | 0.16667 | 11137 | 11147 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 60 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 14:10 | 14:30 | 0.33333 | 11147 | 11162 | 15 | Slide | TTF: 170; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 399.45; Drilling Parameters ROP: 45 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 14:30 | 14:44 | 0.23333 | 11162 | 11232 | 70 | Rotate |  | 11163 | 82.7 | 139.4 | 10335.57 | -1179.52 | -1077.52 | -1179.52 | 7.23 |  |  | 35 | 80 | 399.45 | 18000 | 300 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 14:50 | 14:55 | 0.083333 | 11232 | 11242 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 120 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 15:12 | 15:25 | 0.21667 | 11242 | 11262 | 20 | Slide | 0 | 11257 | 82.99 | 140.07 | 10347.28 | -1250.69 | -1017.24 | -1250.69 | 0.77 |  |  | 35 |  | 399.45 |  | 92.31 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 15:25 | 15:44 | 0.31667 | 11262 | 11326 | 64 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 202.11 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 15:52 | 16:10 | 0.3 | 11326 | 11344 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 399.45; Drilling Parameters ROP: 60 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 16:10 | 16:29 | 0.31667 | 11344 | 11420 | 76 | Rotate |  | 11351 | 86.96 | 140.73 | 10355.51 | -1322.83 | -957.56 | -1322.83 | 4.28 |  |  | 35 | 80 | 399.45 | 16000 | 240 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 17:18 | 17:35 | 0.28333 | 11420 | 11515 | 95 | Rotate |  | 11446 | 87.51 | 153.79 | 10360.11 | -1402.47 | -906.36 | -1402.47 | 13.74 |  |  | 35 | 80 | 399.45 | 16000 | 335.29 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 17:52 | 18:00 | 0.13333 | 11515 | 11525 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 75 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 18:05 | 18:40 | 0.58333 | 11525 | 11550 | 25 | Slide | -90 | 11540 | 86.91 | 139.19 | 10364.71 | -1480.54 | -854.67 | -1480.54 | 15.53 |  |  | 35 | 70 | 399.45 | 7500 | 42.86 | 4150 | 3750 | 400 | 237 | 250 | 165 | 150
07/27/2021 | 18:40 | 18:57 | 0.28333 | 11550 | 11575 | 25 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 88.24 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 19:00 | 19:18 | 0.3 | 11575 | 11609 | 34 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 113.33 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 19:21 | 19:25 | 0.066667 | 11609 | 11619 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 150 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 19:25 | 19:37 | 0.2 | 11619 | 11631 | 12 | Slide | TTF: 20; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 60 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150 | 2.5 Osc 70 RPM
07/27/2021 | 19:37 | 20:01 | 0.4 | 11631 | 11703 | 72 | Rotate |  | 11634 | 88.78 | 140.55 | 10368.25 | -1552.36 | -794.13 | -1552.36 | 2.46 |  |  | 35 | 80 | 399.45 | 16000 | 180 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 20:04 | 20:38 | 0.56667 | 11703 | 11799 | 96 | Rotate |  | 11730 | 89.9 | 140.19 | 10369.35 | -1626.29 | -732.9 | -1626.29 | 1.23 |  |  | 35 | 80 | 399.45 | 16000 | 169.41 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 20:40 | 20:45 | 0.083333 | 11799 | 11814 | 15 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 180 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 20:45 | 20:55 | 0.16667 | 11814 | 11822 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 48 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150 | 2.7 Osc 70 RPM
07/27/2021 | 20:55 | 21:13 | 0.3 | 11822 | 11893 | 71 | Rotate |  | 11824 | 88.97 | 140.59 | 10370.28 | -1698.7 | -672.98 | -1698.7 | 1.08 |  |  | 35 | 80 | 399.45 | 16000 | 236.67 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 21:16 | 21:37 | 0.35 | 11893 | 11985 | 92 | Rotate |  | 11916 | 90.59 | 141.16 | 10370.63 | -1770.07 | -614.93 | -1770.07 | 1.87 |  |  | 35 | 80 | 399.45 | 16000 | 262.86 | 4200 | 3750 | 450 | 237 | 250 | 165 | 150
07/27/2021 | 21:40 | 21:50 | 0.16667 | 11985 | 11990 | 5 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 30 | 4750 | 3750 | 1000 | 262 | 250 | 165 | 150
07/27/2021 | 21:50 | 22:08 | 0.3 | 11990 | 12005 | 15 | Slide | TTF: -170; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 755; Drilling Parameters ROP: 50 | 4200 | 3750 | 450 | 262 | 250 | 165 | 150 | 2.9 Osc 70 RPM
07/27/2021 | 22:08 | 22:30 | 0.36667 | 12005 | 12079 | 74 | Rotate |  | 12010 | 89.82 | 141.87 | 10370.29 | -1843.65 | -556.43 | -1843.65 | 1.11 |  |  | 22.33 | 79.56 | 399.51 | 13.99 | 201.44 | 4547.19 | 3905.77 | 641.42 | 264.2 | 250 | 185.8 | 150
07/27/2021 | 22:37 | 22:48 | 0.18333 | 12079 | 12085 | 6 | Rotate | Drilling Parameters WOB: 16.05; Drilling Parameters RPM: 79.55; Drilling Parameters FLOW: 399.44; Drilling Parameters Tq: 12; Drilling Parameters ROP: 32.73 | 3861.53 | 3817.93 | 43.6 | 266 | 240 | 185.1 | 165
07/27/2021 | 22:48 | 23:07 | 0.31667 | 12085 | 12101 | 16 | Slide | TTF: -156; Drilling Parameters WOB: 14.63; Drilling Parameters RPM: 79.47; Drilling Parameters FLOW: 399.52; Drilling Parameters Tq: 13.03; Drilling Parameters ROP: 50.53 | 4289.29 | 3912.87 | 376.42 | 262.4 | 240 | 185.1 | 165 | 3.3 osc 70 RPM 1.8 Pipe Squat
07/27/2021 | 23:07 | 23:20 | 0.21667 | 12101 | 12174 | 73 | Rotate |  | 12105 | 86.86 | 140.87 | 10373.05 | -1917.82 | -497.16 | -1917.82 | 3.29 |  |  | 27.68 | 79.56 | 399.47 | 15.37 | 336.92 | 4651.04 | 4049.72 | 601.32 | 264.2 | 240 | 185.1 | 165 | Check Shot 12,114 86.22 140.00 Showed .5 drop in rotation from survey. Rotated down and midway down well built again.
07/27/2021 | 23:27 | 00:00 | 0 | 12174 | 12267 | 93 | Rotate |  | 12199 | 87.56 | 141.6 | 10377.62 | -1991.03 | -438.37 | -1991.03 | 1.08 |  |  | 29.55 | 79.56 | 399.46 | 15.11 | 169.09 | 4767.93 | 3627.4 | 1140.53 | 266 | 240 | 185.1 | 165
07/28/2021 | 00:00 | 00:11 | 0.18333 | 12267 | 12274 | 7 | Rotate | Drilling Parameters WOB: 16.51; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.47; Drilling Parameters Tq: 11.61; Drilling Parameters ROP: 38.18 | 3876.53 | 3829.27 | 47.26 | 267.8 | 240 | 185.1 | 165
07/28/2021 | 00:12 | 00:28 | 0.26667 | 12274 | 12287 | 13 | Slide | TTF: -164; Drilling Parameters WOB: 17.26; Drilling Parameters RPM: 79.58; Drilling Parameters FLOW: 399.38; Drilling Parameters Tq: 13.1; Drilling Parameters ROP: 48.75 | 4347.32 | 3902.24 | 445.08 | 264.2 | 240 | 185.1 | 165
07/28/2021 | 00:28 | 00:42 | 0.23333 | 12287 | 12363 | 76 | Rotate |  | 12294 | 85.94 | 140.92 | 10383.01 | -2065.01 | -379.02 | -2065.01 | 1.85 |  |  | 33.19 | 79.55 | 399.48 | 16.71 | 325.71 | 4750.25 | 4491.34 | 258.91 | 266 | 240 | 179.56 | 165
07/28/2021 | 00:48 | 01:03 | 0.25 | 12363 | 12380 | 17 | Rotate | Drilling Parameters WOB: 30.42; Drilling Parameters RPM: 79.54; Drilling Parameters FLOW: 399.41; Drilling Parameters Tq: 12.69; Drilling Parameters ROP: 68 | 3917.72 | 3902.46 | 15.26 | 267.8 | 240 | 179.56 | 165
07/28/2021 | 01:03 | 01:11 | 0.13333 | 12380 | 12388 | 8 | Slide | TTF: -160.38; Drilling Parameters WOB: 40.8; Drilling Parameters RPM: 79.54; Drilling Parameters FLOW: 399.42; Drilling Parameters Tq: 12.69; Drilling Parameters ROP: 60 | 3979.46 | 4012.84 | -33.38 | 266 | 240 | 179.56 | 165
07/28/2021 | 01:11 | 01:28 | 0.28333 | 12388 | 12457 | 69 | Rotate |  | 12388 | 84.67 | 140.85 | 10390.7 | -2137.69 | -319.92 | -2137.69 | 1.35 |  |  | 27.6 | 71.55 | 399.48 | 15.63 | 243.53 | 4622.95 | 3596.37 | 1026.58 | 266 | 240 | 177.47 | 165
07/28/2021 | 01:33 | 01:53 | 0.33333 | 12457 | 12551 | 94 | Rotate |  | 12482 | 83.24 | 140.81 | 10400.6 | -2210.16 | -260.88 | -2210.16 | 1.52 |  |  | 29.22 | 79.56 | 399.51 | 15.8 | 282 | 4693.94 | 3596.37 | 1097.57 | 269.6 | 238 | 181.29 | 149
07/28/2021 | 01:58 | 02:12 | 0.23333 | 12551 | 12565 | 14 | Rotate | Drilling Parameters WOB: 18.74; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.44; Drilling Parameters Tq: 12.83; Drilling Parameters ROP: 60 | 3876.99 | 3596.37 | 280.62 | 271.4 | 238 | 181.29 | 149
07/28/2021 | 02:12 | 02:45 | 0.55 | 12565 | 12590 | 25 | Slide | 20 | 12576 | 83.82 | 141.57 | 10411.19 | -2282.94 | -202.34 | -2282.94 | 1.01 |  |  | 19.44 | 79.63 | 399.44 | 14.88 | 45.45 | 4354.19 | 3824.81 | 529.38 | 266 | 238 | 181.29 | 149
07/28/2021 | 02:52 | 02:58 | 0.1 | 12590 | 12645 | 55 | Rotate | Drilling Parameters WOB: 26.63; Drilling Parameters RPM: 79.55; Drilling Parameters FLOW: 399.46; Drilling Parameters Tq: 16.17; Drilling Parameters ROP: 550 | 4600.34 | 3596.37 | 1003.97 | 266 | 238 | 181.29 | 149
07/28/2021 | 03:06 | 03:24 | 0.3 | 12645 | 12660 | 15 | Rotate | Drilling Parameters WOB: 17.18; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.39; Drilling Parameters Tq: 13.94; Drilling Parameters ROP: 50 | 3806.15 | 3596.37 | 209.78 | 267.8 | 238 | 178.92 | 149 | Check Shot 12,66012,591 85.3 140.9
07/28/2021 | 03:24 | 03:45 | 0.35 | 12660 | 12676 | 16 | Slide | -8.11 | 12670 | 87.28 | 140.87 | 10418.49 | -2355.99 | -143.65 | -2355.99 | 3.75 |  |  | 16.15 | 44.72 | 399.39 | 13.9 | 45.71 | 4226.71 | 3596.37 | 630.34 | 266 | 238 | 178.92 | 149
07/28/2021 | 03:45 | 03:59 | 0.23333 | 12676 | 12739 | 63 | Rotate | Drilling Parameters WOB: 37.22; Drilling Parameters RPM: 79.55; Drilling Parameters FLOW: 399.42; Drilling Parameters Tq: 19.21; Drilling Parameters ROP: 269.87 | 4820.56 | 4349.61 | 470.95 | 267.8 | 238 | 185.45 | 149
07/28/2021 | 04:05 | 04:27 | 0.36667 | 12739 | 12833 | 94 | Rotate |  | 12764 | 89.08 | 140.62 | 10421.47 | -2428.73 | -84.2 | -2428.73 | 1.93 |  |  | 23.82 | 79.57 | 399.48 | 15.56 | 255.82 | 4523.01 | 4095.31 | 427.7 | 273.2 | 238 | 179.93 | 149
07/28/2021 | 04:33 | 04:43 | 0.16667 | 12833 | 12840 | 7 | Rotate | Drilling Parameters WOB: 18.99; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.41; Drilling Parameters Tq: 12.27; Drilling Parameters ROP: 54.48 | 4523.01 | 3870.69 | 652.32 | 273.2 | 238 | 180.25 | 149
07/28/2021 | 04:43 | 04:58 | 0.25 | 12840 | 12850 | 10 | Slide | TTF: 165; Drilling Parameters WOB: 19.74; Drilling Parameters RPM: 79.48; Drilling Parameters FLOW: 399.32; Drilling Parameters Tq: 14.78; Drilling Parameters ROP: 40 | 4331.29 | 3869.12 | 462.17 | 271.4 | 238 | 180.25 | 149
07/28/2021 | 04:58 | 05:12 | 0.23333 | 12850 | 12927 | 77 | Rotate |  | 12858 | 89.2 | 141.45 | 10422.88 | -2501.81 | -25.1 | -2501.81 | 0.89 |  |  | 17.45 | 79.55 | 399.33 | 15.49 | 330 | 4523.01 | 3790.82 | 732.19 | 273.2 | 238 | 179.15 | 149
07/28/2021 | 05:15 | 05:27 | 0.2 | 12927 | 12940 | 13 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 79.55; Drilling Parameters FLOW: 399.33; Drilling Parameters Tq: 15.49; Drilling Parameters ROP: 65 | 4523.01 | 3790.82 | 732.19 | 273 | 238 | 179.15 | 149
07/28/2021 | 05:27 | 05:45 | 0.3 | 12940 | 12955 | 15 | Slide | 180 | 12953 | 88.41 | 140.6 | 10424.86 | -2575.65 | 34.64 | -2575.65 | 1.22 |  |  | 16.95 | 79.55 | 399.55 | 15.49 | 50 | 3917.72 | 3894.3 | 23.42 | 271.4 | 238 | 179.15 | 149
07/28/2021 | 05:45 | 06:05 | 0.33333 | 12955 | 13022 | 67 | Rotate | Drilling Parameters WOB: 30.06; Drilling Parameters RPM: 79.56; Drilling Parameters FLOW: 399.51; Drilling Parameters Tq: 17.68; Drilling Parameters ROP: 201 | 4649.51 | 4461.68 | 187.83 | 273.2 | 238 | 180.78 | 149
07/28/2021 | 06:12 | 06:20 | 0.13333 | 13022 | 13032 | 10 | Rotate | Drilling Parameters WOB: 51.57; Drilling Parameters RPM: 79.33; Drilling Parameters FLOW: 399.45; Drilling Parameters Tq: 0.9; Drilling Parameters ROP: 75 | 3823.01 | 3693.21 | 129.8 | 271.4 | 238 | 181.91 | 149
07/28/2021 | 06:20 | 06:45 | 0.41667 | 13032 | 13042 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 37.58; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.53; Drilling Parameters Tq: 19.55; Drilling Parameters ROP: 24 | 4664.47 | 3405.26 | 1259.21 | 273.2 | 238 | 189.49 | 149
07/28/2021 | 06:45 | 07:02 | 0.28333 | 13042 | 13116 | 74 | Rotate |  | 13047 | 86.54 | 139.92 | 10429 | -2647.86 | 94.68 | -2647.86 | 2.12 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 261.18 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 07:09 | 07:26 | 0.28333 | 13116 | 13210 | 94 | Rotate |  | 13141 | 88.76 | 141.79 | 10432.86 | -2720.69 | 153.96 | -2720.69 | 3.09 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 331.76 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 07:30 | 07:35 | 0.083333 | 13210 | 13220 | 10 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 120 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 07:35 | 07:54 | 0.31667 | 13220 | 13235 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 47.37 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 07:54 | 08:08 | 0.23333 | 13235 | 13305 | 70 | Rotate |  | 13236 | 86.61 | 140.79 | 10436.7 | -2794.76 | 213.32 | -2794.76 | 2.5 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 300 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 08:12 | 08:29 | 0.28333 | 13305 | 13399 | 94 | Rotate |  | 13330 | 87.54 | 145.05 | 10441.49 | -2869.64 | 269.9 | -2869.64 | 4.63 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 331.76 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 08:34 | 08:45 | 0.18333 | 13399 | 13409 | 10 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 54.55 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 08:45 | 08:56 | 0.18333 | 13409 | 13424 | 15 | Slide | TTF: -120; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 81.82 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 09:12 | 09:24 | 0.2 | 13424 | 13494 | 70 | Rotate |  | 13425 | 86.73 | 152.07 | 10446.25 | -2950.53 | 319.36 | -2950.53 | 7.43 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 350 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 09:30 | 09:34 | 0.066667 | 13494 | 13498 | 4 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 60 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 09:34 | 10:00 | 0.43333 | 13498 | 13528 | 30 | Slide | -90 | 13519 | 87.83 | 148.95 | 10450.71 | -3032.25 | 365.58 | -3032.25 | 3.52 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 69.23 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 10:00 | 10:15 | 0.25 | 13528 | 13588 | 60 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 240 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 10:20 | 10:35 | 0.25 | 13588 | 13682 | 94 | Rotate |  | 13613 | 87.95 | 152.83 | 10454.17 | -3114.31 | 411.27 | -3114.31 | 4.13 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 376 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 10:52 | 11:18 | 0.43333 | 13682 | 13712 | 30 | Slide | -90 | 13706 | 87.52 | 154.69 | 10457.85 | -3197.65 | 452.35 | -3197.65 | 2.05 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 69.23 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 11:18 | 11:33 | 0.25 | 13712 | 13775 | 63 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 252 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 11:45 | 12:28 | 0.71667 | 13775 | 13815 | 40 | Slide | -90 | 13801 | 87.86 | 157.38 | 10461.68 | -3284.39 | 490.91 | -3284.39 | 2.85 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 55.81 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 12:28 | 12:45 | 0.28333 | 13815 | 13870 | 55 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 194.12 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 13:00 | 14:04 | 1.0667 | 13870 | 13965 | 95 | Slide | -90 | 13896 | 87.14 | 153.54 | 10465.82 | -3370.71 | 530.32 | -3370.71 | 4.11 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 89.06 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 14:07 | 14:12 | 0.083333 | 13965 | 13996 | 31 | Rotate |  | 13989 | 87.38 | 145.88 | 10470.28 | -3450.86 | 577.14 | -3450.86 | 8.23 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 372 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 14:27 | 14:46 | 0.31667 | 13996 | 14027 | 31 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 97.89 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 14:51 | 15:03 | 0.2 | 14027 | 14058 | 31 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 155 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 15:10 | 17:38 | 2.4667 | 14058 | 14152 | 94 | Slide | -80 | 14083 | 87.35 | 148.95 | 10474.6 | -3529.97 | 627.7 | -3529.97 | 3.26 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 38.11 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 17:49 | 18:30 | 0.68333 | 14152 | 14247 | 95 | Rotate |  | 14178 | 87.3 | 138.23 | 10479.05 | -3606.23 | 683.94 | -3606.23 | 11.27 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 139.02 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 18:34 | 20:16 | 1.7 | 14247 | 14307 | 60 | Slide | -70 | 14272 | 86.8 | 136.62 | 10483.88 | -3675.36 | 747.45 | -3675.36 | 1.79 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 35.29 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 20:16 | 20:28 | 0.2 | 14307 | 14341 | 34 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 170 | 4589.59 | 3405 | 1184.59 | 276.8 | 238 | 189.49 | 149
07/28/2021 | 21:14 | 21:52 | 0.63333 | 14341 | 14361 | 20 | Slide | TTF: -10; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 31.58 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/28/2021 | 21:52 | 22:16 | 0.4 | 14361 | 14436 | 75 | Rotate |  | 14367 | 89.67 | 129.29 | 10486.81 | -3740.01 | 816.9 | -3740.01 | 8.28 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 187.5 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/28/2021 | 22:30 | 23:00 | 0.5 | 14436 | 14443 | 7 | Slide | TTF: 130; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 14 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/28/2021 | 23:10 | 00:00 | 0 | 14443 | 14456 | 13 | Slide | TTF: 130; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 15.6 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/29/2021 | 00:00 | 00:30 | 0.5 | 14456 | 14530 | 74 | Rotate |  | 14461 | 89.1 | 131.54 | 10487.82 | -3800.94 | 888.46 | -3800.94 | 2.47 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 148 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/29/2021 | 00:34 | 01:00 | 0.43333 | 14530 | 14545 | 15 | Slide | TTF: 110; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 34.62 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/29/2021 | 01:00 | 01:46 | 0.76667 | 14545 | 14624 | 79 | Rotate |  | 14556 | 90.58 | 131.96 | 10488.09 | -3864.2 | 959.33 | -3864.2 | 1.62 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 103.04 | 4589.59 | 3405 | 1184.59 | 277 | 238 | 189.49 | 149
07/29/2021 | 01:50 | 03:52 | 2.0333 | 14624 | 14654 | 30 | Slide | 150 | 14650 | 88.24 | 133.34 | 10489.06 | -3927.87 | 1028.46 | -3927.87 | 2.89 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 14.75 | 3850 | 3250 | 600 | 277 | 238 | 189.49 | 149
07/29/2021 | 03:52 | 04:16 | 0.4 | 14654 | 14693 | 39 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 97.5 | 3850 | 3250 | 600 | 277 | 238 | 189.49 | 149
07/29/2021 | 04:22 | 04:37 | 0.25 | 14693 | 14719 | 26 | Rotate | Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 104 | 3850 | 3250 | 600 | 277 | 238 | 189.49 | 149
07/29/2021 | 04:48 | 06:10 | 1.3667 | 14719 | 14744 | 25 | Slide | TTF: 110; Drilling Parameters WOB: 39.91; Drilling Parameters RPM: 79.57; Drilling Parameters FLOW: 399.49; Drilling Parameters Tq: 17.09; Drilling Parameters ROP: 18.29 | 3900 | 3200 | 700 | 277 | 238 | 189.49 | 149
07/29/2021 | 06:10 | 07:15 | 1.0833 | 14744 | 14813 | 69 | Rotate |  | 14745 | 88.07 | 136.76 | 10492.11 | -3995.06 | 1095.53 | -3995.06 | 3.6 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 63.69 | 3900 | 3200 | 700 | 277 | 238 | 189.49 | 149
07/29/2021 | 07:48 | 08:30 | 0.7 | 14813 | 14855 | 42 | Rotate |  | 14841 | 86.41 | 135.7 | 10496.74 | -4064.3 | 1161.86 | -4064.3 | 2.05 |  |  | 39.91 | 79.57 | 399.49 | 17.09 | 60 | 3900 | 3200 | 700 | 282 | 238 | 189.49 | 149

## BHA_5_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2777
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 242
Well Name: |  |  |  |  | Boone C1H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.38 |  | Rotate: |  | 2535
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/30/2021 | 14:10 | 14:58 | 0.8 | 14855 | 14865 | 10 | Slide | TTF: 45; Drilling Parameters WOB: 41; Drilling Parameters FLOW: 288; Drilling Parameters ROP: 12.5 | 3500 | 3210 | 290 | 282 | 250 | 185 | 150
07/30/2021 | 14:58 | 15:22 | 0.4 | 14865 | 14909 | 44 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19; Drilling Parameters ROP: 110 | 5680 | 4570 | 1110 | 282 | 250 | 185 | 150
07/30/2021 | 15:27 | 15:55 | 0.46667 | 14909 | 15004 | 95 | Rotate |  | 14936 | 87.8 | 136.87 | 10501.54 | -4132.88 | 1227.42 | -4132.88 | 1.91 |  |  | 24 | 80 | 400 | 19 | 203.57 | 5680 | 4570 | 1110 | 282 | 250 | 185 | 150
07/30/2021 | 16:02 | 16:08 | 0.1 | 15004 | 15014 | 10 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19; Drilling Parameters ROP: 100 | 5680 | 4570 | 1110 | 282 | 250 | 185 | 150
07/30/2021 | 16:08 | 17:14 | 1.1 | 15014 | 15034 | 20 | Slide | 150 | 15030 | 86.32 | 137.99 | 10506.36 | -4202.01 | 1290.93 | -4202.01 | 1.97 |  |  | 24 |  | 400 |  | 18.18 | 5680 | 4570 | 1110 | 282 | 250 | 185 | 165
07/30/2021 | 17:14 | 17:33 | 0.31667 | 15034 | 15098 | 64 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19; Drilling Parameters ROP: 202.11 | 5680 | 4570 | 1110 | 282 | 250 | 185 | 150
07/30/2021 | 17:38 | 18:05 | 0.45 | 15098 | 15193 | 95 | Rotate |  | 15125 | 84.92 | 138.73 | 10513.61 | -4272.8 | 1353.86 | -4272.8 | 1.67 |  |  | 24 | 80 | 400 | 19 | 211.11 | 5680 | 4570 | 1110 | 282 | 250 | 185 | 150
07/30/2021 | 18:10 | 18:35 | 0.41667 | 15193 | 15286 | 93 | Rotate |  | 15220 | 84.14 | 138.46 | 10522.67 | -4343.73 | 1416.41 | -4343.73 | 0.87 |  |  | 32 | 80 | 400 | 22 | 223.2 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 18:45 | 19:55 | 1.1667 | 15286 | 15316 | 30 | Slide | 10 | 15314 | 87.49 | 138.82 | 10529.53 | -4414.08 | 1478.35 | -4414.08 | 3.58 |  |  | 32 | 80 | 400 | 22 | 25.71 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 19:55 | 20:23 | 0.46667 | 15316 | 15380 | 64 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 137.14 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 20:35 | 20:52 | 0.28333 | 15380 | 15475 | 95 | Rotate |  | 15408 | 88.69 | 138.92 | 10532.66 | -4484.84 | 1540.14 | -4484.84 | 1.28 |  |  | 32 | 80 | 400 | 22 | 335.29 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 20:58 | 21:05 | 0.11667 | 15475 | 15485 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 85.71 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 21:05 | 22:00 | 0.91667 | 15485 | 15505 | 20 | Slide | 135 | 15502 | 87.69 | 139.46 | 10535.63 | -4555.95 | 1601.54 | -4555.95 | 1.21 |  |  | 32 | 80 | 400 | 22 | 21.82 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 22:00 | 22:18 | 0.3 | 15505 | 15570 | 65 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 216.67 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 22:24 | 22:45 | 0.35 | 15570 | 15664 | 94 | Rotate |  | 15596 | 86.67 | 139.33 | 10540.25 | -4627.23 | 1662.65 | -4627.23 | 1.09 |  |  | 32 | 80 | 400 | 22 | 268.57 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 22:52 | 23:12 | 0.33333 | 15664 | 15758 | 94 | Rotate |  | 15690 | 87.39 | 140.69 | 10545.12 | -4699.15 | 1722.97 | -4699.15 | 1.64 |  |  | 32 | 80 | 400 | 22 | 282 | 5756 | 4630 | 1126 | 293 | 250 | 185 | 150
07/30/2021 | 23:18 | 23:23 | 0.083333 | 15758 | 15768 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 120 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/30/2021 | 23:23 | 23:50 | 0.45 | 15768 | 15778 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 22.22 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/30/2021 | 23:50 | 24:00 | 0.16667 | 15778 | 15840 | 62 | Rotate |  | 15784 | 84.75 | 137.85 | 10551.57 | -4770.21 | 1784.15 | -4770.21 | 4.12 |  |  | 32 | 80 | 400 | 22 | 372 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 00:00 | 00:12 | 0.2 | 15840 | 15851 | 11 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 55 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 00:16 | 00:25 | 0.15 | 15851 | 15862 | 11 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 73.33 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 00:25 | 01:30 | 1.0833 | 15862 | 15887 | 25 | Slide | 30 | 15878 | 86.24 | 139.1 | 10558.95 | -4840.36 | 1846.27 | -4840.36 | 2.07 |  |  | 32 | 80 | 400 | 22 | 23.08 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 01:30 | 01:48 | 0.3 | 15887 | 15946 | 59 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 196.67 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 01:52 | 02:14 | 0.36667 | 15946 | 16039 | 93 | Rotate |  | 15972 | 86.65 | 141.05 | 10564.78 | -4912.31 | 1906.48 | -4912.31 | 2.12 |  |  | 32 | 80 | 400 | 22 | 253.64 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 02:18 | 02:42 | 0.4 | 16039 | 16134 | 95 | Rotate |  | 16066 | 87.17 | 140.27 | 10569.85 | -4984.9 | 1965.98 | -4984.9 | 1 |  |  | 32 | 80 | 400 | 22 | 237.5 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 02:46 | 03:11 | 0.41667 | 16134 | 16228 | 94 | Rotate |  | 16161 | 87.47 | 139.84 | 10574.29 | -5057.65 | 2026.91 | -5057.65 | 0.55 |  |  | 32 | 80 | 400 | 22 | 225.6 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 03:15 | 03:38 | 0.38333 | 16228 | 16324 | 96 | Rotate |  | 16256 | 87.93 | 139.39 | 10578.1 | -5129.96 | 2088.41 | -5129.96 | 0.68 |  |  | 32 | 80 | 400 | 22 | 250.43 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 03:42 | 04:05 | 0.38333 | 16324 | 16418 | 94 | Rotate |  | 16350 | 88.12 | 139.01 | 10581.34 | -5201.07 | 2149.8 | -5201.07 | 0.45 |  |  | 32 | 80 | 400 | 22 | 245.22 | 5756 | 4630 | 1126 | 298 | 250 | 185 | 150
07/31/2021 | 04:08 | 04:34 | 0.43333 | 16418 | 16512 | 94 | Rotate |  | 16444 | 88.64 | 139.05 | 10584 | -5272.02 | 2211.4 | -5272.02 | 0.55 |  |  | 32 | 80 | 400 | 22 | 216.92 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 04:37 | 04:45 | 0.13333 | 16512 | 16522 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 75 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 04:45 | 06:20 | 1.5833 | 16522 | 16547 | 25 | Slide | 135 | 16539 | 87.73 | 140.1 | 10587.01 | -5344.3 | 2272.97 | -5344.3 | 1.46 |  |  | 32 | 80 | 400 | 22 | 15.79 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 06:20 | 06:38 | 0.3 | 16547 | 16607 | 60 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 200 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 06:43 | 07:05 | 0.36667 | 16607 | 16701 | 94 | Rotate |  | 16633 | 87.58 | 143 | 10590.85 | -5417.84 | 2331.37 | -5417.84 | 3.09 |  |  | 32 | 80 | 400 | 22 | 256.36 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 07:10 | 07:15 | 0.083333 | 16701 | 16711 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 120 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 07:15 | 08:35 | 1.3333 | 16711 | 16723 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 9 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 08:35 | 09:00 | 0.41667 | 16723 | 16796 | 73 | Rotate |  | 16728 | 84.3 | 138.4 | 10597.58 | -5491.15 | 2391.36 | -5491.15 | 5.94 |  |  | 32 | 80 | 400 | 22 | 175.2 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 09:05 | 09:10 | 0.083333 | 16796 | 16815 | 19 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 228 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 09:10 | 09:49 | 0.65 | 16815 | 16819 | 4 | Slide | TTF: 90; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 6.15 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 10:30 | 11:33 | 1.05 | 16819 | 16825 | 6 | Slide | 60 | 16822 | 83.4 | 139.35 | 10607.65 | -5561.55 | 2452.83 | -5561.55 | 1.39 |  |  | 32 | 80 | 400 | 22 | 5.71 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 11:33 | 12:02 | 0.48333 | 16825 | 16890 | 65 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 134.48 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 12:22 | 12:30 | 0.13333 | 16890 | 16900 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 75 | 5756 | 4630 | 1126 | 307 | 330 | 185 | 150
07/31/2021 | 12:38 | 14:25 | 1.7833 | 16900 | 16930 | 30 | Slide | 35 | 16917 | 85.32 | 140.99 | 10616.99 | -5634.15 | 2513.38 | -5634.15 | 2.65 |  |  | 32 | 80 | 400 | 22 | 16.82 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 14:25 | 14:45 | 0.33333 | 16930 | 16985 | 55 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 165 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 14:50 | 14:55 | 0.083333 | 16985 | 17000 | 15 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 180 | 5756 | 4630 | 1126 | 307 | 250 | 185 | 150
07/31/2021 | 15:00 | 15:30 | 0.5 | 17000 | 17080 | 80 | Rotate |  | 17012 | 88.99 | 142.23 | 10621.7 | -5708.5 | 2572.29 | -5708.5 | 4.08 |  |  | 32 | 80 | 400 | 22 | 160 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 20:09 | 20:18 | 0.15 | 17080 | 17090 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 66.67 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 20:18 | 20:48 | 0.5 | 17090 | 17100 | 10 | Slide | TTF: 170; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 20 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 20:48 | 21:14 | 0.43333 | 17100 | 17174 | 74 | Rotate |  | 17106 | 88.39 | 142.52 | 10623.85 | -5782.93 | 2629.66 | -5782.93 | 0.71 |  |  | 32 | 80 | 400 | 22 | 170.77 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 21:18 | 21:46 | 0.46667 | 17174 | 17269 | 95 | Rotate |  | 17201 | 89.64 | 142.43 | 10625.49 | -5858.26 | 2687.51 | -5858.26 | 1.32 |  |  | 32 | 80 | 400 | 22 | 203.57 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 21:50 | 22:28 | 0.63333 | 17269 | 17279 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 15.79 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 22:28 | 22:58 | 0.5 | 17279 | 17294 | 15 | Slide | TTF: 170; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 30 | 5756 | 4630 | 1126 | 307 | 250 | 190 | 135
07/31/2021 | 22:58 | 23:26 | 0.46667 | 17294 | 17362 | 68 | Rotate |  | 17296 | 90.34 | 142.38 | 10625.5 | -5933.54 | 2745.47 | -5933.54 | 0.74 |  |  | 32 | 80 | 400 | 22 | 145.71 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
07/31/2021 | 23:30 | 23:37 | 0.11667 | 17362 | 17374 | 12 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 102.86 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
07/31/2021 | 23:37 | 24:00 | 0.38333 | 17374 | 17378 | 4 | Slide | TTF: 170; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 10.43 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 01:45 | 01:52 | 0.11667 | 17378 | 17383 | 5 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 42.86 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 01:52 | 03:05 | 1.2167 | 17383 | 17404 | 21 | Slide | 180 | 17392 | 89.57 | 141.54 | 10625.58 | -6009.14 | 2804.63 | -6009.14 | 1.19 |  |  | 32 | 80 | 400 | 22 | 17.26 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 03:05 | 03:26 | 0.35 | 17404 | 17460 | 56 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 160 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 03:45 | 03:50 | 0.083333 | 17460 | 17472 | 12 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 144 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 04:00 | 04:30 | 0.5 | 17472 | 17554 | 82 | Rotate |  | 17486 | 86.01 | 140.98 | 10629.2 | -6082.4 | 2863.4 | -6082.4 | 3.83 |  |  | 32 | 80 | 400 | 22 | 164 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 04:34 | 05:00 | 0.43333 | 17554 | 17627 | 73 | Rotate |  | 17578 | 86.78 | 141.75 | 10634.99 | -6154.12 | 2920.72 | -6154.12 | 1.18 |  |  | 32 | 80 | 400 | 22 | 168.46 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135
08/01/2021 | 05:25 | 05:31 | 0.1 | 17627 | 17632 | 5 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22; Drilling Parameters ROP: 50 | 5756 | 4630 | 1126 | 302 | 250 | 190 | 135

## BHA_6_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 6 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 1470
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 57
Well Name: |  |  |  |  | Boone C1H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.38 |  | Rotate: |  | 1413
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/02/2021 | 19:25 | 19:35 | 0.16667 | 17632 | 17646 | 14 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 84 | 5980 | 5380 | 600 | 300 | 280 | 260 | 150
08/02/2021 | 19:40 | 19:48 | 0.13333 | 17646 | 17656 | 10 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 75 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 19:48 | 20:23 | 0.58333 | 17656 | 17671 | 15 | Slide | TTF: 160; Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 25.71 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 20:23 | 21:00 | 0.61667 | 17671 | 17739 | 68 | Rotate |  | 17674 | 85.74 | 143.3 | 10641.25 | -6230.14 | 2979 | -6230.14 | 1.94 |  |  | 27 | 80 | 371 | 24 | 110.27 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 21:05 | 21:32 | 0.45 | 17739 | 17834 | 95 | Rotate |  | 17768 | 86.44 | 143.58 | 10647.66 | -6305.47 | 3034.87 | -6305.47 | 0.8 |  |  | 27 | 80 | 371 | 24 | 211.11 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 21:35 | 22:05 | 0.5 | 17834 | 17928 | 94 | Rotate |  | 17863 | 86.73 | 143.44 | 10653.32 | -6381.71 | 3091.26 | -6381.71 | 0.34 |  |  | 27 | 80 | 371 | 24 | 188 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 22:10 | 22:36 | 0.43333 | 17928 | 18023 | 95 | Rotate |  | 17957 | 86.96 | 143.44 | 10658.49 | -6457.1 | 3147.17 | -6457.1 | 0.24 |  |  | 27 | 80 | 371 | 24 | 219.23 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 22:56 | 23:23 | 0.45 | 18023 | 18117 | 94 | Rotate |  | 18051 | 87.28 | 143.44 | 10663.22 | -6532.5 | 3203.09 | -6532.5 | 0.34 |  |  | 27 | 80 | 371 | 24 | 208.89 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 23:26 | 23:38 | 0.2 | 18117 | 18129 | 12 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 60 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/02/2021 | 23:38 | 24:00 | 0.36667 | 18129 | 18133 | 4 | Slide | TTF: -160; Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 10.91 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/03/2021 | 00:50 | 01:21 | 0.51667 | 18133 | 18143 | 10 | Slide | TTF: -160; Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 19.35 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/03/2021 | 01:21 | 01:46 | 0.41667 | 18143 | 18212 | 69 | Rotate |  | 18146 | 87.27 | 141.51 | 10667.73 | -6607.76 | 3260.89 | -6607.76 | 2.03 |  |  | 27 | 80 | 371 | 24 | 165.6 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/03/2021 | 02:20 | 02:28 | 0.13333 | 18212 | 18226 | 14 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 105 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/03/2021 | 02:28 | 02:52 | 0.4 | 18226 | 18234 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 20 | 5980 | 5380 | 600 | 306 | 280 | 260 | 150
08/03/2021 | 02:52 | 03:13 | 0.35 | 18234 | 18308 | 74 | Rotate |  | 18240 | 85.77 | 140.43 | 10673.44 | -6680.64 | 3319.97 | -6680.64 | 1.97 |  |  | 27 | 80 | 371 | 24 | 211.43 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 03:16 | 03:45 | 0.48333 | 18308 | 18401 | 93 | Rotate |  | 18335 | 85.92 | 140.48 | 10680.32 | -6753.71 | 3380.29 | -6753.71 | 0.17 |  |  | 27 | 80 | 371 | 24 | 192.41 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 03:50 | 04:24 | 0.56667 | 18401 | 18496 | 95 | Rotate |  | 18430 | 86.14 | 140.39 | 10686.9 | -6826.77 | 3440.66 | -6826.77 | 0.25 |  |  | 27 | 80 | 371 | 24 | 167.65 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 04:28 | 04:42 | 0.23333 | 18496 | 18508 | 12 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 51.43 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 04:42 | 05:12 | 0.5 | 18508 | 18518 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 20 | 5980 | 5380 | 600 | 304 | 280 | 260 | 150
08/03/2021 | 05:12 | 05:40 | 0.46667 | 18518 | 18593 | 75 | Rotate |  | 18525 | 87.79 | 141 | 10691.93 | -6900.17 | 3500.75 | -6900.17 | 1.85 |  |  | 27 | 80 | 371 | 24 | 160.71 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 06:35 | 07:03 | 0.46667 | 18593 | 18688 | 95 | Rotate |  | 18620 | 89 | 141.41 | 10694.59 | -6974.18 | 3560.25 | -6974.18 | 1.34 |  |  | 27 | 80 | 371 | 24 | 203.57 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 07:08 | 07:20 | 0.2 | 18688 | 18698 | 10 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 24; Drilling Parameters ROP: 50 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 07:20 | 08:00 | 0.66667 | 18698 | 18708 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 27; Drilling Parameters ROP: 15 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 08:00 | 08:20 | 0.33333 | 18708 | 18782 | 74 | Rotate |  | 18714 | 88.46 | 141.39 | 10696.67 | -7047.63 | 3618.88 | -7047.63 | 0.57 |  |  | 27 | 80 | 371 | 27 | 222 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 08:25 | 08:58 | 0.55 | 18782 | 18876 | 94 | Rotate |  | 18808 | 88.24 | 141.38 | 10699.38 | -7121.04 | 3677.52 | -7121.04 | 0.23 |  |  | 27 | 80 | 371 | 27 | 170.91 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 09:18 | 09:43 | 0.41667 | 18876 | 18970 | 94 | Rotate |  | 18902 | 88.27 | 141.16 | 10702.24 | -7194.34 | 3736.3 | -7194.34 | 0.24 |  |  | 27 | 80 | 371 | 27 | 225.6 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 09:55 | 10:02 | 0.11667 | 18970 | 18993 | 23 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 27; Drilling Parameters ROP: 197.14 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 10:15 | 10:39 | 0.4 | 18993 | 19064 | 71 | Rotate |  | 19034 | 88.6 | 140.28 | 10705.85 | -7296.48 | 3819.84 | -7296.48 | 0.71 |  |  | 27 | 80 | 371 | 27 | 177.5 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150
08/03/2021 | 10:45 | 11:05 | 0.33333 | 19064 | 19102 | 38 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 371; Drilling Parameters Tq: 27; Drilling Parameters ROP: 114 | 5980 | 5380 | 600 | 309 | 280 | 260 | 150 | TD