## Summary
Magnolia Oil & Gas / Borgstedt 2H / LTX1124821 / Patterson 285
Report Date: | 08/12/2021 | Current Depth: | 18092
Start Date: | 06/22/2021 | Casing Depth: | 0
Daily Cost: | 9450 | Distance to TD:
Well Cost: | 142050 | Average ROP: | 115.81
Drilling Hours: | 4.73 | Svy MD: | 18092
24Hr Forcast: | Circ. & POOH to Run Casing. | Svy Inc: | 88.52
Current BHA: | BHA 4 | Svy Azi: | 140.28
Current BRT Hrs: | 32.33 | Svy TVD: | 10685.5
Bit Make / Model: | Halliburton / GTD64M | Svy NS: | -5432.54
POOH in last 24Hrs: | Yes | Svy EW: | 4390.39
Rig Down Time: | Yes | Svy Hi/Lo: | 0
Mud Type: | WBM | Svy Left/Right: | 0
Directional Driller Day: | Nathan Marks | MWD Day: | Jeff Campbell
Directional Driller Night: | Donny Klein | MWD Night: | Charlie Mckirahan
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 262
24Hr Summary: | Drill and TD Lateral Section | Max BHT 24Hrs: | 198
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MTR500030 | 7/8 3.8 2.5 HS 88 -.005 Slick | PDCI |  | Clean
PPM250019 | 6/7 8.8 2.12 HS 88 .001 Slick | PDCI |  | Clean
PPM250001 | 6/7 8.8 2.12 HS 88 -.004 Slick | PDCI |  | Clean
PPM250017 | 6/7 8.8 2.12 HS 88 -.004 Slick | PDCI |  | Clean
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
ZSB500043 | UBHO |  |  | Dirty |  | 89.82 | 89.82
ZSB500033 | UBHO |  |  | Clean
ZSB500050 | UBHO |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 285 |  |  | Well: |  | Borgstedt 2H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Total Drilled (Usft): |  | 17984 |  |  | Total Days: |  | 14
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 2732 | 2624 |  | 600.92 |  | 6.82 | 4.37 | 2.13 | 9.17
2 | 2 | 9.875 | 2732 | 9906 | 7174 |  | 142.34 |  | 6.89 | 50.4 | 10.07 | 79.25
3 | 3 | 6.75 | 9906 | 17489 | 7583 |  | 130.78 |  | 21.61 | 57.98 | 21.12 | 105.83
4 | 4 | 6.75 | 17489 | 18092 | 603 |  | 127.39 |  | 5.8 | 4.73 | 5.98 | 32.33
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | New |  | 1-2-CT-S-X-I-CT-TD |  | 1.178 | 2624 | 4.3667 | 600.92
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 1-2-CT-S-X-I-NO-TD |  | 1.491 | 7174 | 50.4 | 142.34
3 | Halliburton |  | GTD64M |  | 6.75 | New |  | 2-2-BT-S-X-I-CT-BHA |  | 1.491 | 7583 | 57.9833 | 130.78
4 | Halliburton |  | GTD64M |  | 6.75 | New |  | 1-1-RR-X-I-RR-TD |  | 1.491 | 603 | 4.7333 | 127.39
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.57 | 2624 |  | 600.92
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 5.78 | 7174 |  | 142.34
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5 | 2.12 | 4.01 | 7583 |  | 130.78
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.25 | 2.12 | 4.03 | 603 |  | 127.39
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Nathan Marks |  | Donny Klein |  | Jeff Campbell |  | Charlie Mckirahan |  | Bobby Guin |  | Greg Johnson |  | Pete Langille
Doug Ferguson
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.26 |  | 2624 |  | 595.01 |  |  |  | 1 |  | 4.41
INT: INTERMEDIATE |  |  | 5.00 / 2.71 |  | 7174 |  | 142.37 |  | 6.39 / 0.00 |  | 1 |  | 50.39
CRV: CURVE |  |  | 1.92 / 0.53 |  | 943 |  | 96.72 |  | 0.25 / 0.00 |  | 1 |  | 9.75
LAT: LATERAL |  |  | 5.08 / 4.23 |  | 7243 |  | 136.76 |  | 0.88 / 0.00 |  | 2 |  | 52.96
Total |  |  | 14 |  | 17984 |  | 153.04 |  | 7.52 / 0.00 |  | 4 |  | 117.51
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 2732.00 | 747.71 | 2445.00 | 157.02 | 179.00 | 6.82 | 2624.00 | 595.01 | 4.41 | 1.14
INT: INTERMEDIATE-BHA 2 |  |  | 2732.00 | 9906.00 | 321.62 | 6680.00 | 16.68 | 494.00 | 6.89 | 7174.00 | 142.37 | 50.39 | 29.62
CRV: CURVE-BHA 3 |  |  | 9906.00 | 10849.00 | 107.37 | 204.00 | 94.14 | 739.00 | 78.37 | 943.00 | 96.72 | 9.75 | 7.85
LAT: LATERAL-BHA 3 |  |  | 10849.00 | 17489.00 | 208.50 | 5740.00 | 43.48 | 900.00 | 13.55 | 6640.00 | 137.67 | 48.23 | 20.70
LAT: LATERAL-BHA 4 |  |  | 17489.00 | 18092.00 | 174.23 | 568.00 | 23.81 | 35.00 | 5.80 | 603.00 | 127.48 | 4.73 | 1.47
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1124821 | Total Drilled(Usft) | 17984.00
Operator | Magnolia Oil & Gas | Drilling Hours | 117.48
Well Name | Borgstedt 2H | Avg ROP(Usft/hr) | 153.08
Rig | Patterson 285 | Rotary Drilled(Usft) | 15637.00
State | Texas | Rotary Hours | 56.72
County | Washington | Rotary ROP(Usft/hr) | 275.70
Formation | Austin Chalk | Rotary % | 86.95
Start Date | 06/22/2021 | Slide Drilled(Usft) | 2347.00
End Date | 08/12/2021 | Slide Hours | 60.77
Days On Well | 14 | Slide ROP(Usft/hr) | 38.62
Start Depth (Usft) | 108.00 | Slide % | 13.05
End Depth (Usft) | 18092.00
Total Drilled (Usft) | 17984.00
# BHA's | 4
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 9.52 / 0.00
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 06/22/2021 | 07/01/2021 | 08/06/2021 | 08/07/2021
End Date | 06/23/2021 | 07/05/2021 | 08/07/2021 | 08/12/2021
Total Days | 2.00 | 5.00 | 1.92 | 5.08
Start Depth (Usft) | 108.00 | 2732.00 | 9906.00 | 10849.00
End Depth (Usft) | 2732.00 | 9906.00 | 10849.00 | 18092.00
Total Drilled(Usft) | 2624.00 | 7174.00 | 943.00 | 7243.00
Drilling Hours | 4.37 | 50.40 | 9.73 | 52.98
Circulating Hours | 2.13 | 10.07 | 3.08 | 24.02
Total D&C Hours | 6.50 | 60.47 | 12.82 | 77.00
Avg ROP(Usft/hr) | 600.92 | 142.34 | 96.88 | 136.70
Rotary Drilled(Usft) | 2445.00 | 6680.00 | 204.00 | 6308.00
Rotary Hours | 3.23 | 20.77 | 1.90 | 30.82
Rotary ROP(Usft/hr) | 756.19 | 321.67 | 107.37 | 204.69
Rotary % | 93.18 | 93.11 | 21.63 | 87.09
Slide Drilled(Usft) | 179.00 | 494.00 | 739.00 | 935.00
Slide Hours | 1.13 | 29.63 | 7.83 | 22.17
Slide ROP(Usft/hr) | 157.94 | 16.67 | 94.34 | 42.18
Slide % | 6.82 | 6.89 | 78.37 | 12.91
# BHA | 1 | 1 | 1 | 2
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 6.40 / 0.00 | 0.25 / 0.00 | 2.87 / 0.00
Total Phase Hrs | 6.25 | 65.03 | 12.75 | 101.45
Phase ROP (Usft/hr) | 419.84 | 110.31 | 73.96 | 71.39
Avg Motor Yield (°/100ft) | 6.71 | 10.55 | 11.41 | 14.90
Avg Rotary DLS (°/100ft) | 0.26 | 0.36 | 0.00 | 1.57
Avg Rotary TF | -47.28 | -114.06 | 0.00 | -69.55
Avg Slide Length (Usft) | 12.79 | 18.30 | 73.90 | 19.48
# Slides | 14 | 27 | 10 | 48
BHA Data
BHA# | 1 | 2 | 3 | 4
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4
Bit Size | 13.500 | 9.875 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Halliburton / GTD64M | Halliburton / GTD64M
Bit TFA | 1.178 | 1.491 | 1.491 | 1.491
Grade In | New | New | New | New
Grade Out | 1-2-CT-S-X-I-CT-TD | 1-2-CT-S-X-I-NO-TD | 2-2-BT-S-X-I-CT-BHA | 1-1-RR-X-I-RR-TD
Motor SN | PPM800067 | PPM800032 | PPM250011 | PPM250006
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 3.00 / 6.13 / 15.00 | 15.00 / 34.48 / 47.00 | 15.00 / 36.72 / 40.00 | 18.50 / 18.50 / 18.50
Diff P (psi) | 15.00 / 190.00 / 431.00 | 110.00 / 682.68 / 900.00 | 300.00 / 904.64 / 1215.00 | 720.00 / 869.09 / 1000.00
Bend | 1.500 | 2.000 | 2.120 | 2.120
Date In | 06/22/2021 | 07/01/2021 | 08/06/2021 | 08/11/2021
Date Out | 06/23/2021 | 07/04/2021 | 08/11/2021 | 08/12/2021
Time In | 15:30 | 10:45 | 23:00 | 09:50
Time Out | 00:40 | 18:00 | 08:50 | 18:10
BRT Hrs | 9.17 | 79.25 | 105.83 | 32.33
Start Depth (Usft) | 108.00 | 2732.00 | 9906.00 | 17489.00
End Depth (Usft) | 2732.00 | 9906.00 | 17489.00 | 18092.00
Total Drilled(Usft) | 2624.00 | 7174.00 | 7583.00 | 603.00
Drilling Hours | 4.37 | 50.40 | 57.98 | 4.73
Circulating Hours | 2.13 | 10.07 | 21.12 | 5.98
Total D&C Hours | 6.50 | 60.47 | 79.10 | 10.72
Avg ROP(Usft/hr) | 600.92 | 142.34 | 130.78 | 127.39
Rotary Drilled(Usft) | 2445.00 | 6680.00 | 5944.00 | 568.00
Rotary Hours | 3.23 | 20.77 | 29.45 | 3.27
Rotary ROP(Usft/hr) | 756.19 | 321.67 | 201.83 | 173.88
Rotary % | 93.18 | 93.11 | 78.39 | 94.20
Slide Drilled(Usft) | 179.00 | 494.00 | 1639.00 | 35.00
Slide Hours | 1.13 | 29.63 | 28.53 | 1.47
Slide ROP(Usft/hr) | 157.94 | 16.67 | 57.44 | 23.86
Slide % | 6.82 | 6.89 | 21.61 | 5.80
Motor Failure | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | NO
LIH | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 6.71 | 10.55 | 14.48 | 6.22
Avg Rotary DLS (°/100ft) | 0.26 | 0.36 | 1.35 | 0.00
Avg Rotary TF | -47.28 | -114.06 | -83.16 | 0.00
Avg Slide Length (Usft) | 12.79 | 18.30 | 29.80 | 11.67
# Slides | 14 | 27 | 55 | 3

## Personnel Report
|  | Job # | LTX1124821 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31158 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 285 |  | Well: |  | Borgstedt 2H
|  | Date: | 08/12/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Borgstedt 2H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Charlie Mckirahan | Night MWD |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
Charlie Mckirahan | Night MWD |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
Charlie Mckirahan | Night MWD |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
Donny Klein | Night DD |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
Donny Klein | Night DD |  | 08/10/2021 - 00:00 | 08/12/2021 - 00:00 |  | 3.00 / 0.00
Doug Ferguson | Night DD |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
Doug Ferguson | Night DD |  | 08/06/2021 - 00:00 | 08/09/2021 - 00:00 |  | 4.00 / 0.00
Jeff Campbell | Day MWD |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
Jeff Campbell | Day MWD |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
Jeff Campbell | Day MWD |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
NA | Trainee 1 |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
NA | Trainee 1 |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
NA | Trainee 1 |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
NA | Trainee 2 |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
NA | Trainee 2 |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
NA | Trainee 2 |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
NA | Rss Eng. 1 |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
NA | Rss Eng. 1 |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
NA | Rss Eng. 1 |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
NA | Rss Eng. 2 |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
NA | Rss Eng. 2 |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
NA | Rss Eng. 2 |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
NA | Third Man |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
NA | Third Man |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
NA | Third Man |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
NA | Fourth Man |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
NA | Fourth Man |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
NA | Fourth Man |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
Nathan Marks | Day DD |  | 06/22/2021 - 00:00 | 06/23/2021 - 00:00 |  | 2.00 / 0.00
Nathan Marks | Day DD |  | 07/01/2021 - 00:00 | 07/05/2021 - 00:00 |  | 5.00 / 0.00
Nathan Marks | Day DD |  | 08/06/2021 - 00:00 | 08/12/2021 - 00:00 |  | 7.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1124821 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Borgstedt 2H | [7 empty] | Day DD: |  |  |  |  | Nathan Marks | [5 empty] | API #: |  |  |  | 42-477-31158
|  |  |  | AFE #: |  |  | 21DD0169MG | [7 empty] | Night DD: |  |  |  |  | Donny Klein | [5 empty] | Company Man: |  |  |  | Bobby Guin
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Jeff Campbell | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 285 | [7 empty] | Night DD: |  |  |  |  | Charlie Mckirahan | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 06/22/2021 | 06/23/2021 | 06/24/2021 | 06/25/2021 | 06/26/2021 | 06/27/2021 | 06/28/2021 | 06/29/2021 | 06/30/2021 | 07/01/2021 | 07/02/2021 | 07/03/2021 | 07/04/2021 | 07/05/2021 | 07/06/2021 | 07/07/2021 | 07/08/2021 | 07/09/2021 | 07/10/2021 | 07/11/2021 | 07/12/2021 | 07/13/2021 | 07/14/2021 | 07/15/2021 | 07/16/2021 | 07/17/2021 | 07/18/2021 | 07/19/2021 | 07/20/2021 | 07/21/2021 | 07/22/2021 | 07/23/2021 | 07/24/2021 | 07/25/2021 | 07/26/2021 | 07/27/2021 | 07/28/2021 | 07/29/2021 | 07/30/2021 | 07/31/2021 | 08/01/2021 | 08/02/2021 | 08/03/2021 | 08/04/2021 | 08/05/2021 | 08/06/2021 | 08/07/2021 | 08/08/2021 | 08/09/2021 | 08/10/2021 | 08/11/2021 | 08/12/2021 | 08/13/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | GTD64M |  | Steel | 13601237 | 2 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X
Bit |  | 6.75 | GTD64M |  | Steel | 13618579 | 0 | 24 | [28 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13571904 | 0 | 15 | [37 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13601236 | 0 | 12 | [40 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13618580 | 6 | 8 | [44 empty] | O | X | X | X | X | X | X | O
Bit |  | 6.75 | GTD64M |  | Steel | 13618580 | 6 | 7 | [45 empty] | X | X | X | X | X | X | O
Bit |  | 6.75 | GTD64M |  | Steel | 13601237 | 2 | 3 | [49 empty] | O | X | X
Bit |  | 6.75 | GTD64M |  | Steel | 13571905 | 0 | 1 | [51 empty] | O
Cross Over |  |  | Crossover |  | Steel | SD119105 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | SD119312 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | X/O- XT39P x CET43B |  | Steel | SD119784 | 0 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.5 | X/O- XT39P x CET43B |  | Steel | SD119787 | 7 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Cross Over |  |  | Crossover |  | Steel | SD119767 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
Cross Over |  | 5.5 | Crossover |  | Steel | SD119769 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.188 | UBHO |  | Steel | ZSB500043 | 7 | 11 | [41 empty] | O | O | O | O | X | X | X | X | X | X | X
MWD / LWD |  |  | UBHO |  | Steel | ZSB500033 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | ZSB500050 | 0 | 2 | [50 empty] | O | O
Motor | PDCI |  | 7/8 3.8 2.5 HS 88 -.005 Slick |  | Steel | MTR500030 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor | PDCI |  | 6/7 8.8 2.12 HS 88 .001 Slick |  | Steel | PPM250019 | 0 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor | PDCI | 5 | 6/7 8.8 2.12 HS 88 .025 Slick |  | Steel | PPM250011 | 6 | 11 | [40 empty] | O | O | O | O | O | X | X | X | X | X | X
Motor | PDCI | 5.25 | 6/7 8.8 2.12 HS 88 .002 Slick |  | Steel | PPM250006 | 2 | 8 | [44 empty] | O | O | O | O | O | O | X | X
Motor | PDCI | 5.25 | 6/7 8.8 2.12 HS 88 -.004 Slick |  | Steel | PPM250001 | 0 | 2 | [50 empty] | O | O
Motor | PDCI | 5.25 | 6/7 8.8 2.12 HS 88 -.004 Slick |  | Steel | PPM250017 | 0 | 1 | [51 empty] | O
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD55850 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD56785 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5" Non Mag Drill Collar |  | Non-Mag | SD56709 | 7 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Collar |  | 5 | 5" Non Mag Drill Collar |  | Non-Mag | SD56772 | 7 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Collar |  | 4.938 | 5" Non Mag Pony Collar |  | Non-Mag | SD56927 | 7 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Collar |  |  | 5" Non Mag Pony Collar |  | Non-Mag | SD6928 | 0 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  |  | 5" Non Mag Pony Collar |  | Non-Mag | SD56653 | 0 | 20 | [32 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD56627 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
Collar |  | 5.062 | NM Drill Collar |  | Non-Mag | SD56775 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Pony Drill Collar |  | Non-Mag | SD56679 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Pony Drill Collar |  | Non-Mag | SD56870 | 0 | 8 | [44 empty] | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 2 Stands Drill Pipe |  | Steel | Rig-4 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 26 Stands Drill Pipe |  | Steel | Rig-5 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 33 Stands Drill Pipe |  | Steel | Rig-6 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax |  | Steel | A52100 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax |  | Steel | A521239 | 7 | 15 | [37 empty] | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Accelerator |  | 5.75 | Tomax |  | Steel | A52139 | 0 | 12 | [40 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax |  | Steel | A52127 | 0 | 1 | [51 empty] | O
Sub |  |  | Float Sub |  | Steel | SD118436 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119563 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119697 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119699 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI |  | Steel | 41015 | 7 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Sub |  | 4.812 | BTI |  | Steel | 41015 | 7 | 15 | [37 empty] | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Sub |  |  | Crossover |  | Steel | GT5033445 | 0 | 12 | [40 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Crossover |  | Steel | GT5033442 | 0 | 12 | [40 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI |  | Steel | XXX | 0 | 1 | [51 empty] | O
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0049 | 6 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | O
Agitator |  | 5.25 | Agitator- Ball Drop |  | Steel | PG525-0037 | 7 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0037 | 7 | 15 | [37 empty] | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X
Agitator |  | 5.25 | Agitator / Ball Drop |  | Steel | PG525-0049 | 6 | 15 | [37 empty] | O | O | O | O | O | O | O | O | X | X | X | X | X | X | O
Agitator |  | 5.25 | Agitator / Ball Drop |  | Steel | PG525-0056 | 0 | 1 | [51 empty] | O
Agitator |  | 5.25 | Agitator |  | Steel | PG5250035 | 0 | 1 | [51 empty] | O
Reamer |  | 5.375 | Reamer |  | Steel | DTI-DNR-363 | 0 | 30 | [22 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Reamer |  | 5.312 | Reamer |  | Steel | DTI-DNR-521 | 7 | 7 | [45 empty] | X | X | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Nathan Marks |  |  |  | 14 |  | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Donny Klein |  |  |  | 5 |  | 1 | 1 | [47 empty] | 1 | 1 | 1
Night DD |  |  | Doug Ferguson |  |  |  | 9 | [10 empty] | 1 | 1 | 1 | 1 | 1 | [31 empty] | 1 | 1 | 1 | 1
Day MWD |  |  | Jeff Campbell |  |  |  | 14 |  | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Charlie Mckirahan |  |  |  | 14 |  | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 14 |  | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 14 |  | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 285 |  |  | Well: |  | Borgstedt 2H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0169MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
SD55850 | NM Drill Collar | 5 | 30.35 |  | XT39 / XT39 | Clean |  | 07/14/2021
SD56785 | NM Drill Collar | 5 | 29.84 |  | XT39 / XT39 | Clean |  | 07/14/2021
SD118436 | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 07/14/2021
SD119563 | Float Sub |  |  |  | XT39 / XT39 | Clean |  | 07/14/2021
SD119105 | Crossover |  |  |  | DS 42 / XT39 | Clean |  | 07/14/2021
SD119312 | Crossover |  |  |  | DS 42 / XT39 | Clean |  | 07/14/2021
SD119697 | Lift Sub |  |  |  | XT39 | Clean |  | 07/14/2021
SD119699 | Lift Sub |  |  |  | XT39 | Clean |  | 07/14/2021
SDLC3356 | Lift Cap |  |  |  | XT39 | Clean |  | 07/14/2021
MTR500030 | 7/8 3.8 2.5 HS 88 -.005 Slick |  |  |  | XT39 / 3 1/2 Reg | Clean | PDCI | 07/14/2021
PG525-0049 | Agitator | 5.25 | 23.46 |  | CET43 / CET43 | Dirty |  | 07/14/2021
PG525-0037 | Agitator- Ball Drop | 5.25 | 20.9 |  | CET43 / CET43 | Dirty |  | 07/14/2021
A52100 | Tomax | 5 | 18.35 |  | XT39 / XT39 | Clean |  | 07/14/2021
41015 | BTI | 4.875 | 1.65 |  | XT39 / XT39 | Dirty |  | 07/14/2021
13601237 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 07/14/2021
Rig-4 | 2 Stands Drill Pipe | 4.5 | 188.77 |  | CET43 / CET43 | Dirty |  | 07/14/2021
DTI-DNR-363 | Reamer | 5.375 | 8.58 |  | CET43 / CET43 | Clean |  | 07/14/2021
Rig-5 | 26 Stands Drill Pipe | 4.5 | 2453.38 |  | CET43 / CET43 | Dirty |  | 07/14/2021
Rig-6 | 33 Stands Drill Pipe | 4.5 | 3114.93 |  | CET43 / CET43 | Dirty |  | 07/14/2021
13618579 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Clean |  | 07/20/2021
PPM250019 | 6/7 8.8 2.12 HS 88 .001 Slick |  |  |  | XT39 / 3 1/2 Reg | Clean | PDCI | 07/24/2021
SD56709 | 5" Non Mag Drill Collar | 5 | 29.96 |  | XT39 / XT39 | Dirty |  | 07/24/2021 |  | 08/12/2021
SD56772 | 5" Non Mag Drill Collar | 5 | 29.91 |  | XT39 / XT39 | Dirty |  | 07/24/2021 |  | 08/12/2021
SD56927 | 5" Non Mag Pony Collar | 4.938 | 10.04 |  | XT39 / XT39 | Dirty |  | 07/24/2021 |  | 08/12/2021
SD6928 | 5" Non Mag Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 07/24/2021 |  | 08/12/2021
SD119784 | X/O- XT39P x CET43B |  |  |  | XT39 / CET43 | Clean |  | 07/24/2021
SD119787 | X/O- XT39P x CET43B | 5.5 | 3.67 |  | XT39 / CET43 | Dirty |  | 07/24/2021 |  | 08/12/2021
SD56653 | 5" Non Mag Pony Collar |  |  |  | XT39 / XT39 | Clean |  | 07/24/2021 |  | 08/12/2021
A521239 | Tomax | 5 | 17.92 |  | XT39 / XT39 | Dirty |  | 07/29/2021
41015 | BTI | 4.812 | 1.65 |  | XT39 / XT39 | Dirty |  | 07/29/2021
PG525-0037 | Agitator | 5.25 | 20.9 |  | CET43 / CET43 | Dirty |  | 07/29/2021
PG525-0049 | Agitator / Ball Drop | 5.25 | 21.44 |  | CET43 / CET43 | Dirty |  | 07/29/2021
13571904 | GTD64M | 6.75 | 0.75 |  | 3 1/2 REG / N/A | Clean |  | 07/29/2021
A52139 | Tomax | 5.75 | 18.35 |  |  | Clean |  | 08/01/2021
13601236 | GTD64M | 6.75 | 0.75 |  | 3 1/2 REG / NA | Clean |  | 08/01/2021
GT5033445 | Crossover |  |  |  | XT39 / 3 1/2 IF | Clean |  | 08/01/2021 |  | 08/12/2021
GT5033442 | Crossover |  |  |  | XT39 / 3 1/2 IF | Clean |  | 08/01/2021 |  | 08/12/2021
PPM250011 | 6/7 8.8 2.12 HS 88 .025 Slick | 5 | 33.16 |  | XT39 / 3 1/2 Reg | Dirty | PDCI | 08/01/2021 |  | 08/11/2021
ZSB500043 | UBHO | 5.188 | 4 |  | XT39 / XT39 | Dirty |  | 08/02/2021 |  | 08/12/2021
13618580 | GTD64M | 6.75 | 0.75 |  | 3 1/2 REG / NA | Dirty |  | 08/05/2021
PPM250006 | 6/7 8.8 2.12 HS 88 .002 Slick | 5.25 | 33.04 |  | XT39 / 3 1/2 Reg | Dirty | PDCI | 08/05/2021 |  | 08/12/2021
SD56627 | NM Drill Collar | 5 | 30.24 |  | XT39 / XT39 | Clean |  | 08/05/2021
SD56775 | NM Drill Collar | 5.062 | 30.46 |  | XT39 / XT39 | Clean |  | 08/05/2021
SD56679 | NM Pony Drill Collar | 5 | 9.11 |  | XT39 / XT39 | Clean |  | 08/05/2021
SD56870 | NM Pony Drill Collar | 5 | 9.93 |  | XT39 / XT39 | Clean |  | 08/05/2021
SD119767 | Crossover |  |  |  | XT39 / CET43 | Clean |  | 08/05/2021
SD119769 | Crossover | 5.5 | 3.69 |  | XT39 / CET43 | Clean |  | 08/05/2021
ZSB500033 | UBHO |  |  |  | XT39 / XT39 | Clean |  | 08/05/2021
DTI-DNR-521 | Reamer | 5.312 | 8.64 |  | CET43 / CET43 | Dirty |  | 08/06/2021
13618580 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 08/06/2021
13601237 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 08/10/2021
PPM250001 | 6/7 8.8 2.12 HS 88 -.004 Slick | 5.25 | 33.1 |  | XT39 / 3 1/2 Reg | Clean | PDCI | 08/11/2021
ZSB500050 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Clean |  | 08/11/2021
XXX | BTI | 4.875 | 1.65 |  | XT39 / XT39 | Clean |  | 08/12/2021
A52127 | Tomax | 5 | 18.36 |  | XT39 / XT39 | Clean |  | 08/12/2021
PG525-0056 | Agitator / Ball Drop | 5.25 | 21.38 |  | CET43 / CET43 | Clean |  | 08/12/2021
PG5250035 | Agitator | 5.25 | 21.23 |  | CET43 / CET43 | Clean |  | 08/12/2021
13571905 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Clean |  | 08/12/2021
PPM250017 | 6/7 8.8 2.12 HS 88 -.004 Slick | 5.25 | 33.08 |  | XT39 / 3 1/2 Reg | Clean | PDCI | 08/12/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 285 |  |  | Well: |  | Borgstedt 2H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 38426 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
Stabalizer | SD610174 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
7/8 5.9 1.5 Stab HPO -.022 NBS 13 | PPM800067 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
NM Pony Drill Collar | SD49205 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
UBHO | ZSB775210 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
NM Drill Collar | SD50132 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
NM Drill Collar | SD55726 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
Crossover | SD104622 | 06/22/2021 | 08/12/2021 | 52 |  | 1 |  | 2.13 | 4.37 | 9.17
SPL613 | 56211 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
7/8 5.9 2.0 HPO -.014 Slick | PPM800032 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
NM Pony Drill Collar | SD51725 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
UBHO | ZSB775208 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
NM Drill Collar | 55727 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
NM Drill Collar | 53215 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
Crossover | 118447 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
6 Joints of 6 1/2 in DC | Rig-3 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
Crossover | 4555 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
Agitator | PG6750030 | 06/22/2021 | 08/12/2021 | 52 | 3 | 2 |  | 10.07 | 50.4 | 79.25
GTD64M | 13618580 | 08/05/2021 | 08/12/2021 | 8 | 4 | 3 |  | 21.12 | 57.98 | 105.83
6/7 8.8 2.12 HS 88 .025 Slick | PPM250011 | 08/01/2021 | 08/11/2021 | 11 | 4 | 3 |  | 21.12 | 57.98 | 105.83
BTI | 41015 | 07/29/2021 | 08/12/2021 | 15 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
5" Non Mag Pony Collar | SD56927 | 07/24/2021 | 08/12/2021 | 20 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
UBHO | ZSB500043 | 08/02/2021 | 08/12/2021 | 11 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
5" Non Mag Drill Collar | SD56772 | 07/24/2021 | 08/12/2021 | 20 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
5" Non Mag Drill Collar | SD56709 | 07/24/2021 | 08/12/2021 | 20 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
Tomax | A521239 | 07/29/2021 | 08/12/2021 | 15 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
X/O- XT39P x CET43B | SD119787 | 07/24/2021 | 08/12/2021 | 20 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
Reamer | DTI-DNR-521 | 08/06/2021 | 08/12/2021 | 7 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
Agitator | PG525-0037 | 07/14/2021 | 08/12/2021 | 30 | 6 | 3 ,4 |  | 27.1 | 62.72 | 138.17
Agitator / Ball Drop | PG525-0049 | 07/14/2021 | 08/12/2021 | 30 | 4 | 3 |  | 21.12 | 57.98 | 105.83
GTD64M | 13601237 | 07/14/2021 | 08/12/2021 | 30 | 1 | 4 |  | 5.98 | 4.73 | 32.33
6/7 8.8 2.12 HS 88 .002 Slick | PPM250006 | 08/05/2021 | 08/12/2021 | 8 | 1 | 4 |  | 5.98 | 4.73 | 32.33
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | well
Facility |  |  | Boone-Borgstedt - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Borgstedt 2H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Borgstedt 2H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 365.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Boone-Borgstedt - Washington County, TX
Map Northing |  |  | 205767.59 US survey foot |  |  | Map Easting |  |  | 3134092.38 US survey foot
Latitude |  |  | 30° 10' 55.63700" N |  |  | Longitude |  |  | 96° 44' 36.77222" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.849
Well: |  |  | Borgstedt 2H
Local North |  |  | -29.41 Usft |  |  | Local East |  |  | -20.34 Usft
Map Northing |  |  | 205737.76 US survey foot |  |  | Map Easting |  |  | 3134065.77 US survey foot
Latitude |  |  | 30° 10' 55.35244" N |  |  | Longitude |  |  | 96° 44' 37.01467" W
Depth Datum |  |  | well |  |  | Datum Elevation |  |  | 365.00 Usft
GL Elevation |  |  | 337.00 Usft
Grid Convergence |  |  | 1.849
Well bore: |  |  | Borgstedt 2H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 30/06/2021
Total Field (nT) |  |  | 46596.4 |  |  | Dip Angle (°) |  |  | 58.817
Declination (°) |  |  | 2.883
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 141.66
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Borgstedt 2H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2659 |  |  | Borgstedt 2H S1 |  |  | MWD+HDGM
2659 |  |  | 9836 |  |  | Borgstedt 2H S2 |  |  | MWD+HDGM
9836 |  |  | 17386 |  |  | Borgstedt 2H S3 |  |  | MWD+HDGM
18023 |  |  | 18092 |  |  | Borgstedt 2H S4 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -365 | 205737.76 | 3134065.77 | 30.182 | -96.7436 | 0
135 | 0.2 | 115.2 | 135 | -0.1 | 0.21 | 0.21 | 0.15 | 0.15 | 85.33 | 115.2 | 135 | -230 | 205737.66 | 3134065.98 | 30.182 | -96.7436 | 115.2
226 | 0.2 | 130.5 | 226 | -0.27 | 0.48 | 0.51 | 0.06 | 0 | 16.81 | 97.65 | 91 | -139 | 205737.49 | 3134066.25 | 30.182 | -96.7436 | 119.58
316 | 0.5 | 93.3 | 316 | -0.4 | 0.99 | 0.92 | 0.4 | 0.33 | -41.33 | -56.74 | 90 | -49 | 205737.36 | 3134066.76 | 30.182 | -96.7436 | 111.8
409 | 0.6 | 83.9 | 408.99 | -0.37 | 1.88 | 1.45 | 0.14 | 0.11 | -10.11 | -46.82 | 93 | 43.99 | 205737.39 | 3134067.65 | 30.182 | -96.7436 | 101.06
503 | 0.7 | 83.4 | 502.99 | -0.25 | 2.94 | 2.02 | 0.11 | 0.11 | -0.53 | -3.5 | 94 | 137.99 | 205737.51 | 3134068.71 | 30.182 | -96.7436 | 94.84
597 | 0.1 | 10.2 | 596.98 | -0.1 | 3.52 | 2.27 | 0.72 | -0.64 | -77.87 | -171.88 | 94 | 231.98 | 205737.66 | 3134069.29 | 30.182 | -96.7436 | 91.66
691 | 0.4 | 292.5 | 690.98 | 0.1 | 3.23 | 1.92 | 0.42 | 0.32 | 82.66 | -92.17 | 94 | 325.98 | 205737.86 | 3134069 | 30.182 | -96.7436 | 88.16
785 | 0.6 | 293.9 | 784.98 | 0.43 | 2.48 | 1.2 | 0.21 | 0.21 | 1.49 | 4.2 | 94 | 419.98 | 205738.19 | 3134068.25 | 30.182 | -96.7436 | 80.19
878 | 0.6 | 291.3 | 877.98 | 0.8 | 1.58 | 0.35 | 0.03 | 0 | -2.8 | -91.3 | 93 | 512.98 | 205738.56 | 3134067.35 | 30.182 | -96.7436 | 63.09
972 | 0.9 | 301.2 | 971.97 | 1.36 | 0.49 | -0.76 | 0.35 | 0.32 | 10.53 | 28.36 | 94 | 606.97 | 205739.12 | 3134066.26 | 30.182 | -96.7436 | 19.85
1066 | 1.8 | 313.5 | 1065.94 | 2.76 | -1.21 | -2.92 | 1 | 0.96 | 13.09 | 24.06 | 94 | 700.94 | 205740.52 | 3134064.56 | 30.182 | -96.7436 | 336.35
1160 | 2.1 | 318.8 | 1159.89 | 5.08 | -3.42 | -6.1 | 0.37 | 0.32 | 5.64 | 33.68 | 94 | 794.89 | 205742.84 | 3134062.35 | 30.1821 | -96.7436 | 326.06
1254 | 2.2 | 315.4 | 1253.82 | 7.66 | -5.82 | -9.61 | 0.17 | 0.11 | -3.62 | -53.61 | 94 | 888.82 | 205745.42 | 3134059.95 | 30.1821 | -96.7437 | 322.77
1348 | 2.4 | 318.4 | 1347.74 | 10.41 | -8.39 | -13.37 | 0.25 | 0.21 | 3.19 | 32.55 | 94 | 982.74 | 205748.17 | 3134057.38 | 30.1821 | -96.7437 | 321.14
1442 | 3.1 | 323.7 | 1441.64 | 13.93 | -11.2 | -17.88 | 0.79 | 0.74 | 5.64 | 22.62 | 94 | 1076.64 | 205751.69 | 3134054.57 | 30.1821 | -96.7437 | 321.2
1536 | 3.8 | 323.1 | 1535.46 | 18.47 | -14.58 | -23.53 | 0.75 | 0.74 | -0.64 | -3.25 | 94 | 1170.46 | 205756.23 | 3134051.19 | 30.1821 | -96.7437 | 321.72
1629 | 4.8 | 322.4 | 1628.2 | 24.02 | -18.8 | -30.5 | 1.08 | 1.08 | -0.75 | -3.35 | 93 | 1263.2 | 205761.78 | 3134046.97 | 30.1821 | -96.7437 | 321.95
1723 | 6 | 324.1 | 1721.78 | 31.11 | -24.08 | -39.34 | 1.29 | 1.28 | 1.81 | 8.44 | 94 | 1356.78 | 205768.87 | 3134041.69 | 30.1821 | -96.7437 | 322.26
1817 | 6.9 | 323.3 | 1815.19 | 39.62 | -30.34 | -49.9 | 0.96 | 0.96 | -0.85 | -6.1 | 94 | 1450.19 | 205777.38 | 3134035.43 | 30.1822 | -96.7437 | 322.56
1911 | 7.6 | 327.5 | 1908.43 | 49.39 | -37.05 | -61.72 | 0.93 | 0.74 | 4.47 | 39.23 | 94 | 1543.43 | 205787.15 | 3134028.72 | 30.1822 | -96.7437 | 323.12
2005 | 8.2 | 328.2 | 2001.54 | 60.33 | -43.92 | -74.57 | 0.65 | 0.64 | 0.74 | 9.46 | 94 | 1636.54 | 205798.09 | 3134021.85 | 30.1822 | -96.7438 | 323.94
2099 | 9 | 327 | 2094.48 | 72.2 | -51.46 | -88.55 | 0.87 | 0.85 | -1.28 | -13.24 | 94 | 1729.48 | 205809.96 | 3134014.31 | 30.1822 | -96.7438 | 324.52
2193 | 9.8 | 326.4 | 2187.22 | 85.03 | -59.89 | -103.84 | 0.86 | 0.85 | -0.64 | -7.28 | 94 | 1822.22 | 205822.79 | 3134005.88 | 30.1823 | -96.7438 | 324.84
2287 | 10.9 | 326.3 | 2279.69 | 99.08 | -69.25 | -120.67 | 1.17 | 1.17 | -0.11 | -0.98 | 94 | 1914.69 | 205836.84 | 3133996.52 | 30.1823 | -96.7438 | 325.05
2381 | 11.4 | 324.9 | 2371.92 | 114.08 | -79.52 | -138.81 | 0.6 | 0.53 | -1.49 | -29.12 | 94 | 2006.92 | 205851.84 | 3133986.25 | 30.1824 | -96.7439 | 325.12
2475 | 11.6 | 323.8 | 2464.03 | 129.3 | -90.45 | -157.53 | 0.32 | 0.21 | -1.17 | -48.18 | 94 | 2099.03 | 205867.06 | 3133975.32 | 30.1824 | -96.7439 | 325.03
2569 | 11.2 | 322.5 | 2556.17 | 144.17 | -101.59 | -176.1 | 0.51 | -0.43 | -1.38 | -147.92 | 94 | 2191.17 | 205881.93 | 3133964.18 | 30.1824 | -96.7439 | 324.83
2659 | 11.1 | 320.2 | 2644.48 | 157.76 | -112.45 | -193.5 | 0.51 | -0.11 | -2.56 | -103.8 | 90 | 2279.48 | 205895.52 | 3133953.32 | 30.1825 | -96.744 | 324.52
2777 | 10.78 | 320.94 | 2760.33 | 175.06 | -126.68 | -215.89 | 0.3 | -0.27 | 0.63 | 156.67 | 118 | 2395.33 | 205912.82 | 3133939.09 | 30.1825 | -96.744 | 324.11
2871 | 10.59 | 320.95 | 2852.7 | 188.59 | -137.66 | -233.32 | 0.2 | -0.2 | 0.01 | 179.45 | 94 | 2487.7 | 205926.35 | 3133928.11 | 30.1826 | -96.7441 | 323.87
2965 | 10.62 | 320.15 | 2945.1 | 201.95 | -148.65 | -250.61 | 0.16 | 0.03 | -0.85 | -78.88 | 94 | 2580.1 | 205939.71 | 3133917.12 | 30.1826 | -96.7441 | 323.64
3058 | 11 | 318.52 | 3036.45 | 215.18 | -160.02 | -268.04 | 0.52 | 0.41 | -1.75 | -39.62 | 93 | 2671.45 | 205952.94 | 3133905.75 | 30.1826 | -96.7441 | 323.36
3152 | 11.25 | 316.79 | 3128.68 | 228.58 | -172.24 | -286.13 | 0.44 | 0.27 | -1.84 | -54.02 | 94 | 2763.68 | 205966.34 | 3133893.53 | 30.1827 | -96.7442 | 323
3246 | 11.32 | 315.48 | 3220.86 | 241.84 | -184.98 | -304.44 | 0.28 | 0.07 | -1.39 | -75.37 | 94 | 2855.86 | 205979.6 | 3133880.79 | 30.1827 | -96.7442 | 322.59
3339 | 11.37 | 315.97 | 3312.05 | 254.94 | -197.75 | -322.63 | 0.12 | 0.05 | 0.53 | 62.82 | 93 | 2947.05 | 205992.7 | 3133868.02 | 30.1828 | -96.7442 | 322.2
3433 | 10.94 | 319.88 | 3404.27 | 268.42 | -209.94 | -340.77 | 0.93 | -0.46 | 4.16 | 121.52 | 94 | 3039.27 | 206006.18 | 3133855.83 | 30.1828 | -96.7443 | 321.97
3527 | 10.52 | 319.04 | 3496.63 | 281.72 | -221.32 | -358.26 | 0.48 | -0.45 | -0.89 | -159.99 | 94 | 3131.63 | 206019.48 | 3133844.45 | 30.1828 | -96.7443 | 321.85
3621 | 11.09 | 323.65 | 3588.96 | 295.49 | -232.3 | -375.86 | 1.1 | 0.61 | 4.9 | 58.87 | 94 | 3223.96 | 206033.25 | 3133833.47 | 30.1829 | -96.7443 | 321.83
3715 | 11.2 | 324.6 | 3681.19 | 310.21 | -242.95 | -394.02 | 0.23 | 0.12 | 1.01 | 59.54 | 94 | 3316.19 | 206047.97 | 3133822.82 | 30.1829 | -96.7444 | 321.93
3809 | 10.97 | 325.02 | 3773.44 | 324.98 | -253.36 | -412.06 | 0.26 | -0.24 | 0.45 | 160.86 | 94 | 3408.44 | 206062.74 | 3133812.41 | 30.183 | -96.7444 | 322.06
3902 | 10.68 | 324.25 | 3864.78 | 339.22 | -263.47 | -429.5 | 0.35 | -0.31 | -0.83 | -153.87 | 93 | 3499.78 | 206076.98 | 3133802.3 | 30.183 | -96.7444 | 322.16
3997 | 10.76 | 324.32 | 3958.12 | 353.57 | -273.79 | -447.16 | 0.09 | 0.08 | 0.07 | 9.28 | 95 | 3593.12 | 206091.33 | 3133791.98 | 30.183 | -96.7445 | 322.25
4092 | 10.84 | 323.91 | 4051.44 | 367.99 | -284.22 | -464.94 | 0.12 | 0.08 | -0.43 | -44.04 | 95 | 3686.44 | 206105.75 | 3133781.55 | 30.1831 | -96.7445 | 322.32
4187 | 10.13 | 326.55 | 4144.85 | 382.18 | -294.09 | -482.19 | 0.9 | -0.75 | 2.78 | 147.21 | 95 | 3779.85 | 206119.94 | 3133771.68 | 30.1831 | -96.7445 | 322.42
4282 | 9.81 | 326.83 | 4238.42 | 395.93 | -303.12 | -498.58 | 0.34 | -0.34 | 0.29 | 171.52 | 95 | 3873.42 | 206133.69 | 3133762.65 | 30.1832 | -96.7446 | 322.56
4377 | 10.02 | 326.35 | 4332 | 409.58 | -312.13 | -514.87 | 0.24 | 0.22 | -0.51 | -21.72 | 95 | 3967 | 206147.34 | 3133753.64 | 30.1832 | -96.7446 | 322.69
4471 | 10.23 | 325.39 | 4424.54 | 423.26 | -321.4 | -531.35 | 0.29 | 0.22 | -1.02 | -39.26 | 94 | 4059.54 | 206161.02 | 3133744.37 | 30.1832 | -96.7446 | 322.79
4564 | 9.98 | 325.39 | 4516.09 | 436.69 | -330.67 | -547.64 | 0.27 | -0.27 | 0 | 180 | 93 | 4151.09 | 206174.45 | 3133735.1 | 30.1833 | -96.7446 | 322.87
4659 | 9.89 | 323.23 | 4609.67 | 450 | -340.23 | -564.01 | 0.4 | -0.09 | -2.27 | -104.64 | 95 | 4244.67 | 206187.76 | 3133725.54 | 30.1833 | -96.7447 | 322.91
4753 | 9.75 | 322.34 | 4702.29 | 462.77 | -349.92 | -580.03 | 0.22 | -0.15 | -0.95 | -133.12 | 94 | 4337.29 | 206200.53 | 3133715.85 | 30.1833 | -96.7447 | 322.91
4847 | 9.63 | 320.71 | 4794.95 | 475.15 | -359.76 | -595.85 | 0.32 | -0.13 | -1.73 | -114.43 | 94 | 4429.95 | 206212.91 | 3133706.01 | 30.1834 | -96.7447 | 322.87
4940 | 9.19 | 320.22 | 4886.7 | 486.88 | -369.44 | -611.06 | 0.48 | -0.47 | -0.53 | -169.92 | 93 | 4521.7 | 206224.64 | 3133696.33 | 30.1834 | -96.7448 | 322.81
5034 | 8.97 | 318.89 | 4979.52 | 498.17 | -379.06 | -625.88 | 0.32 | -0.23 | -1.41 | -137 | 94 | 4614.52 | 206235.93 | 3133686.71 | 30.1834 | -96.7448 | 322.73
5128 | 10.18 | 324.4 | 5072.21 | 510.45 | -388.72 | -641.5 | 1.61 | 1.29 | 5.86 | 39.88 | 94 | 4707.21 | 206248.21 | 3133677.05 | 30.1835 | -96.7448 | 322.71
5221 | 10.93 | 325.37 | 5163.64 | 524.38 | -398.51 | -658.5 | 0.83 | 0.81 | 1.04 | 13.81 | 93 | 4798.64 | 206262.14 | 3133667.26 | 30.1835 | -96.7448 | 322.77
5316 | 11.14 | 323.04 | 5256.88 | 539.13 | -409.15 | -676.67 | 0.52 | 0.22 | -2.45 | -65.93 | 95 | 4891.88 | 206276.89 | 3133656.62 | 30.1836 | -96.7449 | 322.8
5411 | 10.6 | 325.74 | 5350.18 | 553.68 | -419.59 | -694.56 | 0.78 | -0.57 | 2.84 | 138 | 95 | 4985.18 | 206291.44 | 3133646.18 | 30.1836 | -96.7449 | 322.84
5506 | 10.06 | 325.18 | 5443.64 | 567.72 | -429.24 | -711.55 | 0.58 | -0.57 | -0.59 | -169.74 | 95 | 5078.64 | 206305.48 | 3133636.53 | 30.1836 | -96.7449 | 322.91
5600 | 10.4 | 324.81 | 5536.14 | 581.39 | -438.82 | -728.22 | 0.37 | 0.36 | -0.39 | -11.12 | 94 | 5171.14 | 206319.15 | 3133626.95 | 30.1837 | -96.745 | 322.96
5694 | 10.52 | 324.11 | 5628.58 | 595.28 | -448.74 | -745.27 | 0.19 | 0.13 | -0.74 | -46.99 | 94 | 5263.58 | 206333.04 | 3133617.03 | 30.1837 | -96.745 | 322.99
5788 | 10.16 | 323.93 | 5721.05 | 608.93 | -458.65 | -762.12 | 0.38 | -0.38 | -0.19 | -174.96 | 94 | 5356.05 | 206346.69 | 3133607.12 | 30.1838 | -96.745 | 323.01
5881 | 9.47 | 323.91 | 5812.69 | 621.74 | -467.99 | -777.96 | 0.74 | -0.74 | -0.02 | -179.73 | 93 | 5447.69 | 206359.5 | 3133597.78 | 30.1838 | -96.7451 | 323.03
5976 | 9.22 | 322.82 | 5906.43 | 634.12 | -477.19 | -793.38 | 0.32 | -0.26 | -1.15 | -145.24 | 95 | 5541.43 | 206371.88 | 3133588.58 | 30.1838 | -96.7451 | 323.04
6069 | 9.53 | 322.12 | 5998.19 | 646.13 | -486.42 | -808.53 | 0.36 | 0.33 | -0.75 | -20.54 | 93 | 5633.19 | 206383.89 | 3133579.35 | 30.1839 | -96.7451 | 323.03
6163 | 9.46 | 322.46 | 6090.9 | 658.4 | -495.91 | -824.04 | 0.1 | -0.07 | 0.36 | 141.46 | 94 | 5725.9 | 206396.16 | 3133569.86 | 30.1839 | -96.7451 | 323.01
6258 | 9.35 | 320.2 | 6184.62 | 670.52 | -505.6 | -839.56 | 0.41 | -0.12 | -2.38 | -107.7 | 95 | 5819.62 | 206408.28 | 3133560.17 | 30.1839 | -96.7452 | 322.98
6352 | 8.79 | 323.9 | 6277.45 | 682.19 | -514.72 | -854.37 | 0.86 | -0.6 | 3.94 | 135.65 | 94 | 5912.45 | 206419.95 | 3133551.05 | 30.184 | -96.7452 | 322.96
6446 | 7.16 | 319.57 | 6370.54 | 692.45 | -522.75 | -867.4 | 1.85 | -1.73 | -4.61 | -161.9 | 94 | 6005.54 | 206430.21 | 3133543.02 | 30.184 | -96.7452 | 322.95
6540 | 6.63 | 317.8 | 6463.86 | 700.93 | -530.2 | -878.67 | 0.61 | -0.56 | -1.88 | -159.03 | 94 | 6098.86 | 206438.69 | 3133535.57 | 30.184 | -96.7452 | 322.9
6634 | 6.42 | 315.72 | 6557.25 | 708.71 | -537.51 | -889.31 | 0.34 | -0.22 | -2.21 | -132.65 | 94 | 6192.25 | 206446.47 | 3133528.26 | 30.184 | -96.7453 | 322.82
6728 | 6.05 | 330.51 | 6650.7 | 716.79 | -543.62 | -899.43 | 1.75 | -0.39 | 15.73 | 110.25 | 94 | 6285.7 | 206454.55 | 3133522.15 | 30.1841 | -96.7453 | 322.82
6822 | 5.78 | 333.87 | 6744.2 | 725.35 | -548.14 | -908.95 | 0.47 | -0.29 | 3.57 | 129.61 | 94 | 6379.2 | 206463.11 | 3133517.63 | 30.1841 | -96.7453 | 322.92
6915 | 5.54 | 331.22 | 6836.75 | 733.49 | -552.37 | -917.96 | 0.38 | -0.26 | -2.85 | -133.87 | 93 | 6471.75 | 206471.25 | 3133513.4 | 30.1841 | -96.7453 | 323.02
7009 | 4.29 | 338.64 | 6930.4 | 740.74 | -555.83 | -925.79 | 1.49 | -1.33 | 7.89 | 156.71 | 94 | 6565.4 | 206478.5 | 3133509.94 | 30.1841 | -96.7453 | 323.12
7103 | 4.15 | 341.24 | 7024.14 | 747.24 | -558.21 | -932.36 | 0.25 | -0.15 | 2.77 | 127.49 | 94 | 6659.14 | 206485 | 3133507.56 | 30.1841 | -96.7453 | 323.24
7197 | 3.84 | 336.77 | 7117.92 | 753.35 | -560.54 | -938.6 | 0.47 | -0.33 | -4.76 | -137.08 | 94 | 6752.92 | 206491.11 | 3133505.23 | 30.1842 | -96.7453 | 323.35
7290 | 3.9 | 327.38 | 7210.71 | 758.88 | -563.47 | -944.76 | 0.68 | 0.06 | -10.1 | -89.29 | 93 | 6845.71 | 206496.64 | 3133502.3 | 30.1842 | -96.7453 | 323.41
7385 | 2.48 | 334.1 | 7305.56 | 763.45 | -566.11 | -949.98 | 1.54 | -1.49 | 7.07 | 168.58 | 95 | 6940.56 | 206501.21 | 3133499.66 | 30.1842 | -96.7453 | 323.44
7478 | 2.02 | 335.64 | 7398.48 | 766.75 | -567.67 | -953.53 | 0.5 | -0.49 | 1.66 | 173.28 | 93 | 7033.48 | 206504.51 | 3133498.1 | 30.1842 | -96.7454 | 323.49
7572 | 2.15 | 336.37 | 7492.42 | 769.87 | -569.06 | -956.85 | 0.14 | 0.14 | 0.78 | 11.91 | 94 | 7127.42 | 206507.63 | 3133496.71 | 30.1842 | -96.7454 | 323.53
7666 | 2.1 | 334.86 | 7586.36 | 773.05 | -570.5 | -960.23 | 0.08 | -0.05 | -1.61 | -132.52 | 94 | 7221.36 | 206510.81 | 3133495.27 | 30.1842 | -96.7454 | 323.57
7760 | 1.88 | 337.05 | 7680.3 | 776.03 | -571.83 | -963.39 | 0.25 | -0.23 | 2.33 | 162.02 | 94 | 7315.3 | 206513.79 | 3133493.94 | 30.1842 | -96.7454 | 323.61
7854 | 1.67 | 326.74 | 7774.26 | 778.59 | -573.18 | -966.24 | 0.41 | -0.22 | -10.97 | -128.41 | 94 | 7409.26 | 206516.35 | 3133492.59 | 30.1842 | -96.7454 | 323.64
7948 | 1.81 | 323.15 | 7868.21 | 780.93 | -574.82 | -969.09 | 0.19 | 0.15 | -3.82 | -39.71 | 94 | 7503.21 | 206518.69 | 3133490.95 | 30.1842 | -96.7454 | 323.64
8042 | 1.97 | 322.66 | 7962.16 | 783.4 | -576.69 | -972.19 | 0.17 | 0.17 | -0.52 | -6.01 | 94 | 7597.16 | 206521.16 | 3133489.07 | 30.1842 | -96.7454 | 323.64
8136 | 1.8 | 326.62 | 8056.11 | 785.92 | -578.49 | -975.28 | 0.23 | -0.18 | 4.21 | 144.51 | 94 | 7691.11 | 206523.68 | 3133487.28 | 30.1843 | -96.7454 | 323.64
8230 | 1.38 | 311.19 | 8150.07 | 787.89 | -580.15 | -977.86 | 0.63 | -0.45 | -16.41 | -141.99 | 94 | 7785.07 | 206525.65 | 3133485.62 | 30.1843 | -96.7454 | 323.63
8324 | 1.3 | 314.75 | 8244.05 | 789.39 | -581.76 | -980.03 | 0.12 | -0.09 | 3.79 | 135.63 | 94 | 7879.05 | 206527.15 | 3133484.01 | 30.1843 | -96.7454 | 323.61
8417 | 1.27 | 297.67 | 8337.03 | 790.61 | -583.42 | -982.02 | 0.41 | -0.03 | -18.37 | -102.98 | 93 | 7972.03 | 206528.37 | 3133482.35 | 30.1843 | -96.7454 | 323.57
8511 | 0.44 | 136.68 | 8431.02 | 790.83 | -584.1 | -982.62 | 1.8 | -0.88 | -171.27 | -175.14 | 94 | 8066.02 | 206528.59 | 3133481.67 | 30.1843 | -96.7454 | 323.55
8605 | 1.5 | 119.46 | 8525 | 789.96 | -582.78 | -981.12 | 1.16 | 1.13 | -18.32 | -24.1 | 94 | 8160 | 206527.72 | 3133482.99 | 30.1843 | -96.7454 | 323.58
8699 | 1.17 | 87.76 | 8618.98 | 789.4 | -580.75 | -979.41 | 0.85 | -0.35 | -33.72 | -129.37 | 94 | 8253.98 | 206527.16 | 3133485.02 | 30.1843 | -96.7454 | 323.66
8793 | 1.95 | 60.05 | 8712.95 | 790.23 | -578.4 | -978.61 | 1.13 | 0.83 | -29.48 | -58.46 | 94 | 8347.95 | 206527.99 | 3133487.37 | 30.1843 | -96.7454 | 323.8
8887 | 1.79 | 59.07 | 8806.9 | 791.79 | -575.76 | -978.19 | 0.17 | -0.17 | -1.04 | -169.19 | 94 | 8441.9 | 206529.55 | 3133490.01 | 30.1843 | -96.7454 | 323.98
8980 | 1.11 | 120.58 | 8899.87 | 792.07 | -573.74 | -977.16 | 1.71 | -0.73 | 66.14 | 142.26 | 93 | 8534.87 | 206529.83 | 3133492.03 | 30.1843 | -96.7454 | 324.08
9074 | 1.43 | 119.92 | 8993.85 | 791.03 | -571.94 | -975.22 | 0.34 | 0.34 | -0.7 | -2.95 | 94 | 8628.85 | 206528.79 | 3133493.83 | 30.1843 | -96.7454 | 324.13
9168 | 0.13 | 151.14 | 9087.84 | 790.35 | -570.87 | -974.03 | 1.4 | -1.38 | 33.21 | 177.07 | 94 | 8722.84 | 206528.11 | 3133494.9 | 30.1843 | -96.7454 | 324.16
9262 | 0.28 | 327.35 | 9181.84 | 790.45 | -570.94 | -974.15 | 0.44 | 0.16 | 187.46 | 177.41 | 94 | 8816.84 | 206528.21 | 3133494.83 | 30.1843 | -96.7454 | 324.16
9356 | 0.86 | 312.83 | 9275.83 | 791.12 | -571.58 | -975.08 | 0.63 | 0.62 | -15.45 | -21.32 | 94 | 8910.83 | 206528.88 | 3133494.19 | 30.1843 | -96.7454 | 324.15
9449 | 1.2 | 308.16 | 9368.82 | 792.2 | -572.86 | -976.71 | 0.38 | 0.37 | -5.02 | -16.21 | 93 | 9003.82 | 206529.96 | 3133492.91 | 30.1843 | -96.7454 | 324.13
9543 | 1.69 | 303.68 | 9462.79 | 793.57 | -574.79 | -978.99 | 0.53 | 0.52 | -4.77 | -15.23 | 94 | 9097.79 | 206531.33 | 3133490.98 | 30.1843 | -96.7454 | 324.08
9637 | 2.21 | 195.41 | 9556.75 | 792.59 | -576.42 | -979.24 | 3.38 | 0.55 | -115.18 | -138.61 | 94 | 9191.75 | 206530.35 | 3133489.35 | 30.1843 | -96.7454 | 323.97
9731 | 7.98 | 158.1 | 9650.36 | 784.78 | -574.47 | -971.9 | 6.77 | 6.14 | -39.69 | -49.39 | 94 | 9285.36 | 206522.54 | 3133491.3 | 30.1842 | -96.7454 | 323.8
9836 | 15.18 | 154.92 | 9753.16 | 765.55 | -565.91 | -951.5 | 6.88 | 6.86 | -3.03 | -6.63 | 105 | 9388.16 | 206503.31 | 3133499.86 | 30.1842 | -96.7453 | 323.53
9931 | 15.45 | 149.38 | 9844.79 | 743.39 | -554.19 | -926.85 | 1.57 | 0.28 | -5.83 | -82.23 | 95 | 9479.79 | 206481.15 | 3133511.58 | 30.1841 | -96.7453 | 323.3
10025 | 20.33 | 132.4 | 9934.28 | 721.58 | -535.73 | -898.29 | 7.55 | 5.19 | -18.06 | -55.22 | 94 | 9569.28 | 206459.34 | 3133530.04 | 30.1841 | -96.7453 | 323.41
10120 | 28.7 | 133.16 | 10020.64 | 694.8 | -506.86 | -859.38 | 8.82 | 8.81 | 0.8 | 2.51 | 95 | 9655.64 | 206432.56 | 3133558.91 | 30.184 | -96.7452 | 323.89
10214 | 38.54 | 138.64 | 10098.83 | 657.28 | -470.95 | -807.67 | 10.95 | 10.47 | 5.83 | 19.46 | 94 | 9733.83 | 206395.04 | 3133594.82 | 30.1839 | -96.7451 | 324.38
10309 | 48.53 | 138.01 | 10167.62 | 608.49 | -427.47 | -742.43 | 10.53 | 10.52 | -0.66 | -2.72 | 95 | 9802.62 | 206346.25 | 3133638.3 | 30.1838 | -96.7449 | 324.91
10403 | 57.43 | 140.19 | 10224.16 | 551.77 | -378.45 | -667.53 | 9.65 | 9.47 | 2.32 | 11.74 | 94 | 9859.16 | 206289.53 | 3133687.32 | 30.1836 | -96.7448 | 325.55
10498 | 66.13 | 140.46 | 10269.04 | 487.39 | -325.06 | -583.93 | 9.16 | 9.16 | 0.28 | 1.63 | 95 | 9904.04 | 206225.15 | 3133740.71 | 30.1834 | -96.7446 | 326.3
10592 | 74.72 | 139.79 | 10300.51 | 419.5 | -268.32 | -495.48 | 9.16 | 9.14 | -0.71 | -4.32 | 94 | 9935.51 | 206157.26 | 3133797.45 | 30.1832 | -96.7444 | 327.4
10686 | 78.45 | 138.65 | 10322.31 | 350.28 | -208.61 | -404.14 | 4.14 | 3.97 | -1.21 | -16.69 | 94 | 9957.31 | 206088.04 | 3133857.16 | 30.183 | -96.7443 | 329.22
10780 | 85.55 | 137.42 | 10335.38 | 281.12 | -146.4 | -311.31 | 7.66 | 7.55 | -1.31 | -9.83 | 94 | 9970.38 | 206018.88 | 3133919.37 | 30.1828 | -96.7441 | 332.49
10875 | 91.81 | 140.92 | 10337.57 | 209.3 | -84.35 | -216.48 | 7.55 | 6.59 | 3.68 | 29.26 | 95 | 9972.57 | 205947.06 | 3133981.42 | 30.1826 | -96.7439 | 338.05
10970 | 89.38 | 143.08 | 10336.59 | 134.45 | -25.87 | -121.5 | 3.42 | -2.56 | 2.27 | 138.35 | 95 | 9971.59 | 205872.21 | 3134039.9 | 30.1824 | -96.7437 | 349.11
11063 | 87.55 | 143.78 | 10339.08 | 59.79 | 29.52 | -28.59 | 2.11 | -1.97 | 0.75 | 159.08 | 93 | 9974.08 | 205797.55 | 3134095.29 | 30.1822 | -96.7435 | 26.28
11158 | 87.71 | 145.13 | 10343.01 | -17.44 | 84.7 | 66.22 | 1.43 | 0.17 | 1.42 | 83.26 | 95 | 9978.01 | 205720.32 | 3134150.47 | 30.182 | -96.7434 | 101.63
11252 | 85.83 | 144.17 | 10348.3 | -93.98 | 138.99 | 159.94 | 2.24 | -2 | -1.02 | -153.01 | 94 | 9983.3 | 205643.78 | 3134204.76 | 30.1818 | -96.7432 | 124.07
11346 | 84.2 | 143.3 | 10356.47 | -169.49 | 194.38 | 253.51 | 1.96 | -1.73 | -0.93 | -152.04 | 94 | 9991.47 | 205568.27 | 3134260.15 | 30.1816 | -96.743 | 131.09
11441 | 84.99 | 142.28 | 10365.42 | -244.81 | 251.58 | 348.07 | 1.35 | 0.83 | -1.07 | -52.17 | 95 | 10000.42 | 205492.95 | 3134317.35 | 30.1813 | -96.7429 | 134.22
11535 | 87.76 | 142.01 | 10371.36 | -318.87 | 309.14 | 441.87 | 2.96 | 2.95 | -0.29 | -5.57 | 94 | 10006.36 | 205418.89 | 3134374.91 | 30.1811 | -96.7427 | 135.89
11630 | 86.57 | 138.61 | 10376.06 | -391.87 | 369.72 | 536.71 | 3.79 | -1.25 | -3.58 | -109.39 | 95 | 10011.06 | 205345.89 | 3134435.49 | 30.1809 | -96.7425 | 136.67
11726 | 89.9 | 142.78 | 10379.02 | -466.1 | 430.48 | 632.62 | 5.56 | 3.47 | 4.34 | 51.46 | 96 | 10014.02 | 205271.66 | 3134496.25 | 30.1807 | -96.7423 | 137.27
11820 | 92.43 | 143.14 | 10377.11 | -541.11 | 487.09 | 726.57 | 2.72 | 2.69 | 0.38 | 8.09 | 94 | 10012.11 | 205196.65 | 3134552.86 | 30.1805 | -96.7421 | 138.01
11912 | 93.12 | 143.6 | 10372.65 | -614.85 | 541.92 | 818.42 | 0.9 | 0.75 | 0.5 | 33.65 | 92 | 10007.65 | 205122.91 | 3134607.69 | 30.1803 | -96.742 | 138.61
12006 | 89.81 | 144.36 | 10370.25 | -690.84 | 597.17 | 912.3 | 3.61 | -3.52 | 0.81 | 167.06 | 94 | 10005.25 | 205046.92 | 3134662.94 | 30.1801 | -96.7418 | 139.16
12100 | 85.59 | 143.53 | 10374.02 | -766.76 | 652.43 | 1006.12 | 4.58 | -4.49 | -0.88 | -168.9 | 94 | 10009.02 | 204971 | 3134718.2 | 30.1799 | -96.7417 | 139.61
12195 | 84.34 | 143.54 | 10382.36 | -842.86 | 708.68 | 1100.71 | 1.32 | -1.32 | 0.01 | 179.54 | 95 | 10017.36 | 204894.9 | 3134774.45 | 30.1797 | -96.7415 | 139.94
12289 | 83.31 | 142.79 | 10392.47 | -917.66 | 764.7 | 1194.13 | 1.35 | -1.1 | -0.8 | -144.14 | 94 | 10027.47 | 204820.1 | 3134830.47 | 30.1795 | -96.7413 | 140.19
12383 | 86.03 | 143.54 | 10401.2 | -992.56 | 820.81 | 1287.68 | 3 | 2.89 | 0.8 | 15.39 | 94 | 10036.2 | 204745.2 | 3134886.58 | 30.1792 | -96.7411 | 140.41
12477 | 87.8 | 143.32 | 10406.26 | -1067.94 | 876.73 | 1381.49 | 1.9 | 1.88 | -0.23 | -7.08 | 94 | 10041.26 | 204669.82 | 3134942.5 | 30.179 | -96.741 | 140.62
12572 | 88.69 | 142.73 | 10409.17 | -1143.8 | 933.84 | 1476.42 | 1.12 | 0.94 | -0.62 | -33.54 | 95 | 10044.17 | 204593.96 | 3134999.61 | 30.1788 | -96.7408 | 140.77
12666 | 88.31 | 142.72 | 10411.63 | -1218.58 | 990.75 | 1570.37 | 0.4 | -0.4 | -0.01 | -178.49 | 94 | 10046.63 | 204519.18 | 3135056.52 | 30.1786 | -96.7406 | 140.89
12759 | 86.86 | 143.9 | 10415.55 | -1293.08 | 1046.27 | 1663.25 | 2.01 | -1.56 | 1.27 | 140.91 | 93 | 10050.55 | 204444.68 | 3135112.03 | 30.1784 | -96.7405 | 141.02
12854 | 86.82 | 145.12 | 10420.79 | -1370.31 | 1101.33 | 1757.98 | 1.28 | -0.04 | 1.28 | 91.91 | 95 | 10055.79 | 204367.45 | 3135167.1 | 30.1782 | -96.7403 | 141.21
12948 | 85.83 | 144.19 | 10426.81 | -1446.83 | 1155.6 | 1851.66 | 1.44 | -1.05 | -0.99 | -136.88 | 94 | 10061.81 | 204290.93 | 3135221.37 | 30.178 | -96.7401 | 141.39
13043 | 82.82 | 140.86 | 10436.21 | -1521.84 | 1213.09 | 1946.16 | 4.71 | -3.17 | -3.51 | -132.4 | 95 | 10071.21 | 204215.92 | 3135278.86 | 30.1778 | -96.74 | 141.44
13137 | 84.51 | 140.19 | 10446.58 | -1593.95 | 1272.49 | 2039.56 | 1.93 | 1.8 | -0.71 | -21.54 | 94 | 10081.58 | 204143.81 | 3135338.26 | 30.1775 | -96.7398 | 141.4
13231 | 88.43 | 137.8 | 10452.37 | -1664.73 | 1334.03 | 2133.26 | 4.88 | 4.17 | -2.54 | -31.4 | 94 | 10087.37 | 204073.03 | 3135399.8 | 30.1773 | -96.7396 | 141.29
13326 | 88.99 | 136.87 | 10454.51 | -1734.57 | 1398.4 | 2227.96 | 1.14 | 0.59 | -0.98 | -58.95 | 95 | 10089.51 | 204003.19 | 3135464.17 | 30.1772 | -96.7394 | 141.12
13421 | 90.68 | 140.11 | 10454.78 | -1805.7 | 1461.35 | 2322.8 | 3.85 | 1.78 | 3.41 | 62.46 | 95 | 10089.78 | 203932.06 | 3135527.12 | 30.177 | -96.7392 | 141.02
13515 | 89.73 | 142.15 | 10454.44 | -1878.88 | 1520.33 | 2416.79 | 2.39 | -1.01 | 2.17 | 114.96 | 94 | 10089.44 | 203858.88 | 3135586.1 | 30.1767 | -96.739 | 141.02
13609 | 87.84 | 142.45 | 10456.44 | -1953.23 | 1577.8 | 2510.76 | 2.04 | -2.01 | 0.32 | 170.99 | 94 | 10091.44 | 203784.53 | 3135643.57 | 30.1765 | -96.7388 | 141.07
13702 | 86.85 | 140.93 | 10460.74 | -2026.12 | 1635.39 | 2603.65 | 1.95 | -1.06 | -1.63 | -123.14 | 93 | 10095.74 | 203711.64 | 3135701.16 | 30.1763 | -96.7387 | 141.09
13797 | 87.62 | 141.31 | 10465.33 | -2099.99 | 1694.95 | 2698.54 | 0.9 | 0.81 | 0.4 | 26.25 | 95 | 10100.33 | 203637.77 | 3135760.72 | 30.1761 | -96.7385 | 141.09
13891 | 87.03 | 141.3 | 10469.71 | -2173.28 | 1753.65 | 2792.43 | 0.63 | -0.63 | -0.01 | -179.03 | 94 | 10104.71 | 203564.48 | 3135819.42 | 30.1759 | -96.7383 | 141.1
13985 | 86.82 | 140.18 | 10474.76 | -2245.95 | 1813.05 | 2886.28 | 1.21 | -0.22 | -1.19 | -100.66 | 94 | 10109.76 | 203491.81 | 3135878.82 | 30.1757 | -96.7381 | 141.09
14079 | 88.03 | 140.48 | 10478.98 | -2318.23 | 1873 | 2980.16 | 1.33 | 1.29 | 0.32 | 13.92 | 94 | 10113.98 | 203419.53 | 3135938.77 | 30.1755 | -96.7379 | 141.06
14173 | 88.08 | 141.38 | 10482.17 | -2391.17 | 1932.21 | 3074.1 | 0.96 | 0.05 | 0.96 | 86.83 | 94 | 10117.17 | 203346.59 | 3135997.98 | 30.1753 | -96.7378 | 141.06
14268 | 86.9 | 141.05 | 10486.33 | -2465.15 | 1991.66 | 3169 | 1.29 | -1.24 | -0.35 | -164.4 | 95 | 10121.33 | 203272.61 | 3136057.43 | 30.1751 | -96.7376 | 141.06
14363 | 86.34 | 140.77 | 10491.93 | -2538.76 | 2051.45 | 3263.83 | 0.66 | -0.59 | -0.29 | -153.48 | 95 | 10126.93 | 203199 | 3136117.22 | 30.1749 | -96.7374 | 141.06
14457 | 88.43 | 141.59 | 10496.22 | -2611.91 | 2110.32 | 3357.72 | 2.39 | 2.22 | 0.87 | 21.42 | 94 | 10131.22 | 203125.85 | 3136176.09 | 30.1747 | -96.7372 | 141.06
14551 | 87.9 | 141.23 | 10499.23 | -2685.35 | 2168.92 | 3451.67 | 0.68 | -0.56 | -0.38 | -145.83 | 94 | 10134.23 | 203052.41 | 3136234.69 | 30.1745 | -96.737 | 141.07
14646 | 89.41 | 141 | 10501.46 | -2759.27 | 2228.54 | 3546.64 | 1.61 | 1.59 | -0.24 | -8.66 | 95 | 10136.46 | 202978.49 | 3136294.31 | 30.1743 | -96.7369 | 141.07
14740 | 87.1 | 140.33 | 10504.32 | -2831.94 | 2288.09 | 3640.57 | 2.56 | -2.46 | -0.71 | -163.84 | 94 | 10139.32 | 202905.82 | 3136353.86 | 30.1741 | -96.7367 | 141.06
14835 | 87.38 | 138.27 | 10508.9 | -2903.88 | 2349.96 | 3735.38 | 2.19 | 0.29 | -2.17 | -82.3 | 95 | 10143.9 | 202833.88 | 3136415.73 | 30.1739 | -96.7365 | 141.02
14930 | 87.55 | 138 | 10513.1 | -2974.55 | 2413.3 | 3830.11 | 0.34 | 0.18 | -0.28 | -57.78 | 95 | 10148.1 | 202763.21 | 3136479.07 | 30.1737 | -96.7363 | 140.95
15024 | 87.8 | 140.2 | 10516.91 | -3045.54 | 2474.79 | 3923.93 | 2.35 | 0.27 | 2.34 | 83.56 | 94 | 10151.91 | 202692.22 | 3136540.56 | 30.1735 | -96.7361 | 140.9
15119 | 87.75 | 138.8 | 10520.6 | -3117.72 | 2536.44 | 4018.79 | 1.47 | -0.05 | -1.47 | -92.07 | 95 | 10155.6 | 202620.04 | 3136602.21 | 30.1732 | -96.7359 | 140.87
15214 | 87.61 | 142.62 | 10524.45 | -3191.18 | 2596.54 | 4113.68 | 4.02 | -0.15 | 4.02 | 92.18 | 95 | 10159.45 | 202546.58 | 3136662.31 | 30.173 | -96.7357 | 140.87
15308 | 85.21 | 143.42 | 10530.33 | -3266.11 | 2652.97 | 4207.46 | 2.69 | -2.55 | 0.85 | 161.62 | 94 | 10165.33 | 202471.65 | 3136718.74 | 30.1728 | -96.7356 | 140.91
15402 | 84.91 | 143.48 | 10538.43 | -3341.35 | 2708.74 | 4301.07 | 0.33 | -0.32 | 0.06 | 168.73 | 94 | 10173.43 | 202396.41 | 3136774.51 | 30.1726 | -96.7354 | 140.97
15496 | 85.01 | 143.32 | 10546.69 | -3416.52 | 2764.57 | 4394.66 | 0.2 | 0.11 | -0.17 | -57.9 | 94 | 10181.69 | 202321.24 | 3136830.34 | 30.1724 | -96.7352 | 141.02
15590 | 84.83 | 142.89 | 10555.01 | -3491.4 | 2820.78 | 4488.26 | 0.49 | -0.19 | -0.46 | -112.81 | 94 | 10190.01 | 202246.36 | 3136886.55 | 30.1722 | -96.7351 | 141.06
15684 | 87.08 | 144.09 | 10561.64 | -3566.76 | 2876.56 | 4581.97 | 2.71 | 2.39 | 1.28 | 28.06 | 94 | 10196.64 | 202171 | 3136942.33 | 30.172 | -96.7349 | 141.11
15778 | 87.93 | 144.51 | 10565.73 | -3643.02 | 2931.36 | 4675.78 | 1.01 | 0.9 | 0.45 | 26.28 | 94 | 10200.73 | 202094.74 | 3136997.13 | 30.1718 | -96.7347 | 141.18
15872 | 88.13 | 143.4 | 10568.96 | -3718.98 | 2986.64 | 4769.65 | 1.2 | 0.21 | -1.18 | -79.8 | 94 | 10203.96 | 202018.78 | 3137052.41 | 30.1716 | -96.7346 | 141.23
15967 | 84.8 | 141.89 | 10574.82 | -3794.34 | 3044.16 | 4864.44 | 3.85 | -3.51 | -1.59 | -155.69 | 95 | 10209.82 | 201943.42 | 3137109.93 | 30.1713 | -96.7344 | 141.26
16060 | 83.79 | 141.72 | 10584.07 | -3867.06 | 3101.38 | 4956.97 | 1.1 | -1.09 | -0.18 | -170.5 | 93 | 10219.07 | 201870.7 | 3137167.15 | 30.1711 | -96.7342 | 141.27
16155 | 86.49 | 142.06 | 10592.11 | -3941.54 | 3159.79 | 5051.62 | 2.86 | 2.84 | 0.36 | 7.17 | 95 | 10227.11 | 201796.22 | 3137225.56 | 30.1709 | -96.734 | 141.28
16250 | 90.2 | 141.71 | 10594.86 | -4016.24 | 3218.4 | 5146.57 | 3.92 | 3.91 | -0.37 | -5.39 | 95 | 10229.86 | 201721.52 | 3137284.17 | 30.1707 | -96.7339 | 141.29
16344 | 90.21 | 141.51 | 10594.52 | -4089.91 | 3276.77 | 5240.57 | 0.21 | 0.01 | -0.21 | -87.14 | 94 | 10229.52 | 201647.85 | 3137342.54 | 30.1705 | -96.7337 | 141.3
16438 | 89.87 | 141.21 | 10594.45 | -4163.34 | 3335.47 | 5334.56 | 0.48 | -0.36 | -0.32 | -138.58 | 94 | 10229.45 | 201574.42 | 3137401.24 | 30.1703 | -96.7335 | 141.3
16534 | 88.36 | 141.97 | 10595.94 | -4238.55 | 3395.1 | 5430.55 | 1.76 | -1.57 | 0.79 | 153.29 | 96 | 10230.94 | 201499.21 | 3137460.87 | 30.1701 | -96.7333 | 141.31
16627 | 84.7 | 141.85 | 10601.57 | -4311.6 | 3452.36 | 5523.36 | 3.94 | -3.94 | -0.13 | -178.13 | 93 | 10236.57 | 201426.16 | 3137518.13 | 30.1699 | -96.7332 | 141.32
16722 | 81.85 | 141.76 | 10612.69 | -4385.74 | 3510.69 | 5617.7 | 3 | -3 | -0.09 | -178.21 | 95 | 10247.69 | 201352.02 | 3137576.46 | 30.1697 | -96.733 | 141.32
16816 | 83.76 | 142.32 | 10624.46 | -4459.26 | 3568.05 | 5710.95 | 2.12 | 2.03 | 0.6 | 16.25 | 94 | 10259.46 | 201278.5 | 3137633.82 | 30.1695 | -96.7328 | 141.34
16911 | 86.79 | 141.77 | 10632.29 | -4533.91 | 3626.27 | 5805.61 | 3.24 | 3.19 | -0.58 | -10.28 | 95 | 10267.29 | 201203.85 | 3137692.04 | 30.1693 | -96.7326 | 141.35
17006 | 86.92 | 141.51 | 10637.5 | -4608.29 | 3685.14 | 5900.47 | 0.31 | 0.14 | -0.27 | -63.41 | 95 | 10272.5 | 201129.47 | 3137750.91 | 30.169 | -96.7325 | 141.35
17100 | 86.57 | 139.61 | 10642.84 | -4680.76 | 3744.76 | 5994.3 | 2.05 | -0.37 | -2.02 | -100.51 | 94 | 10277.84 | 201057 | 3137810.53 | 30.1688 | -96.7323 | 141.34
17196 | 86.91 | 137.53 | 10648.3 | -4752.62 | 3808.18 | 6090 | 2.19 | 0.35 | -2.17 | -80.76 | 96 | 10283.3 | 200985.14 | 3137873.95 | 30.1686 | -96.7321 | 141.3
17290 | 86.77 | 139.53 | 10653.48 | -4822.94 | 3870.33 | 6183.71 | 2.13 | -0.15 | 2.13 | 94.06 | 94 | 10288.48 | 200914.82 | 3137936.1 | 30.1684 | -96.7319 | 141.25
17386 | 86.98 | 138.74 | 10658.71 | -4895.43 | 3933.04 | 6279.47 | 0.85 | 0.22 | -0.82 | -75.11 | 96 | 10293.71 | 200842.33 | 3137998.81 | 30.1682 | -96.7317 | 141.22
18023 | 88.52 | 140.28 | 10683.72 | -5379.48 | 4346.31 | 6915.5 | 0.34 | 0.24 | 0.24 | 45.01 | 637 | 10318.72 | 200358.28 | 3138412.08 | 30.1669 | -96.7304 | 141.06
18092 | 88.52 | 140.28 | 10685.5 | -5432.54 | 4390.39 | 6984.45 | 0 | 0 | 0 | 0 | 69 | 10320.5 | 200305.22 | 3138456.16 | 30.1667 | -96.7303 | 141.06

## 6_22_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/22/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 14000 |  |  | Well Cost($): |  | 14000
|  |  |  | 24hr Summary: |  | Drill Surface
|  |  |  | 24hr Lookahead: |  | Drill & TD Surface
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 2732 |  | 2732 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 2624 |  | 2624 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 179 |  | 179 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2445 |  | 2445 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.37 / 2.13 |  | 4.37 / 2.13 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: |  | 1.13 |  | 1.13 |  | SN: |  | 38426 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 3.23 |  | 3.23 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 756.19 / 157.94 |  | 756.19 / 157.94 |  | OD (in) / TFA: |  | 13.500 / 1.178
BRT Hrs: |  | 8.5 |  | 8.5 |  | Grade In: |  | New
% Slide: |  | 6.82 |  | 6.82 |  | Grade Out: |  | 1-2-CT-S-X-I-CT-TD
% Rotary: |  | 93.18 |  | 93.18 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.18 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
Stabalizer |  |  |  | 13 | 2.875 |  |  |  |  | 7.86 |  | 9.36
7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  |  | 8 | 2 |  |  |  |  | 37.43 |  | 46.79
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.95 |  | 54.74
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.74 |  | 58.48
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.74 |  | 87.22
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.8 |  | 116.02
Crossover |  |  |  | 6.5 | 3.062 |  |  |  |  | 2.08 |  | 118.1
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 389.14
389.14
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800067 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.57 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
135 | 0.2 | 115.2 | 135 | -0.1 | 0.21 | 0.15 |  | 115.2 | 0.21 | 0.15 |  | 0 | 135
226 | 0.2 | 130.5 | 226 | -0.27 | 0.48 | 0.06 |  | 97.65 | 0.51 | 0 |  | 0 | 91
316 | 0.5 | 93.3 | 316 | -0.4 | 0.99 | 0.4 |  | -56.74 | 0.92 | 0.33 |  | 0 | 90
409 | 0.6 | 83.9 | 408.99 | -0.37 | 1.88 | 0.14 |  | -46.82 | 1.45 | 0.11 |  | 0 | 93
503 | 0.7 | 83.4 | 502.99 | -0.25 | 2.94 | 0.11 |  | -3.5 | 2.02 | 0.11 |  | 0 | 94
597 | 0.1 | 10.2 | 596.98 | -0.1 | 3.52 | 0.72 |  | -171.88 | 2.27 | -0.64 |  | 0 | 94
691 | 0.4 | 292.5 | 690.98 | 0.1 | 3.23 | 0.42 |  | -92.17 | 1.92 | 0.32 |  | 0 | 94
785 | 0.6 | 293.9 | 784.98 | 0.43 | 2.48 | 0.21 |  | 4.2 | 1.2 | 0.21 |  | 0 | 94
878 | 0.6 | 291.3 | 877.98 | 0.8 | 1.58 | 0.03 |  | -91.3 | 0.35 | 0 |  | 0 | 93
972 | 0.9 | 301.2 | 971.97 | 1.36 | 0.49 | 0.35 |  | 28.36 | -0.76 | 0.32 |  | 0 | 94
1066 | 1.8 | 313.5 | 1065.94 | 2.76 | -1.21 | 1 |  | 24.06 | -2.92 | 0.96 |  | 0 | 94
1160 | 2.1 | 318.8 | 1159.89 | 5.08 | -3.42 | 0.37 |  | 33.68 | -6.1 | 0.32 |  | 5.64 | 94
1254 | 2.2 | 315.4 | 1253.82 | 7.66 | -5.82 | 0.17 |  | -53.61 | -9.61 | 0.11 |  | -3.62 | 94
1348 | 2.4 | 318.4 | 1347.74 | 10.41 | -8.39 | 0.25 |  | 32.55 | -13.37 | 0.21 |  | 3.19 | 94
1442 | 3.1 | 323.7 | 1441.64 | 13.93 | -11.2 | 0.79 |  | 22.62 | -17.88 | 0.74 |  | 5.64 | 94
1536 | 3.8 | 323.1 | 1535.46 | 18.47 | -14.58 | 0.75 |  | -3.25 | -23.53 | 0.74 |  | -0.64 | 94
1629 | 4.8 | 322.4 | 1628.2 | 24.02 | -18.8 | 1.08 |  | -3.35 | -30.5 | 1.08 |  | -0.75 | 93
1723 | 6 | 324.1 | 1721.78 | 31.11 | -24.08 | 1.29 |  | 8.44 | -39.34 | 1.28 |  | 1.81 | 94
1817 | 6.9 | 323.3 | 1815.19 | 39.62 | -30.34 | 0.96 |  | -6.1 | -49.9 | 0.96 |  | -0.85 | 94
1911 | 7.6 | 327.5 | 1908.43 | 49.39 | -37.05 | 0.93 |  | 39.23 | -61.72 | 0.74 |  | 4.47 | 94
2005 | 8.2 | 328.2 | 2001.54 | 60.33 | -43.92 | 0.65 |  | 9.46 | -74.57 | 0.64 |  | 0.74 | 94
2099 | 9 | 327 | 2094.48 | 72.2 | -51.46 | 0.87 |  | -13.24 | -88.55 | 0.85 |  | -1.28 | 94
2193 | 9.8 | 326.4 | 2187.22 | 85.03 | -59.89 | 0.86 |  | -7.28 | -103.84 | 0.85 |  | -0.64 | 94
2287 | 10.9 | 326.3 | 2279.69 | 99.08 | -69.25 | 1.17 |  | -0.98 | -120.67 | 1.17 |  | -0.11 | 94
2381 | 11.4 | 324.9 | 2371.92 | 114.08 | -79.52 | 0.6 |  | -29.12 | -138.81 | 0.53 |  | -1.49 | 94
2475 | 11.6 | 323.8 | 2464.03 | 129.3 | -90.45 | 0.32 |  | -48.18 | -157.53 | 0.21 |  | -1.17 | 94
2569 | 11.2 | 322.5 | 2556.17 | 144.17 | -101.59 | 0.51 |  | -147.92 | -176.1 | -0.43 |  | -1.38 | 94
2659 | 11.1 | 320.2 | 2644.48 | 157.76 | -112.45 | 0.51 |  | -103.8 | -193.5 | -0.11 |  | -2.56 | 90
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 600.92 | 7.8 | 88.89 | 222 | 801 | 1571.5 | 1392 | 0 | 60 | 60 | 60 | 3677.78 | 0
Run | 600.92 | 7.8 | 88.89 | 222 | 801 | 1571.5 | 1392 | 0 | 60 | 60 | 60 | 3677.78 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 06/22/2021 |  | 1 |  | 6000 |  | 1 | 6000
Directional & MWD / Gamma Services |  |  |  |  | 06/22/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 06/22/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 06/22/2021 |  | 17 |  | 1150 |  | 1 | 1150
Total | [11 empty] | 14000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/22/2021 | 00:00 | 14:50 | 14.83 | 108 | 108 | 0 | SUR |  | 24B | Standby for rig skid opps.
06/22/2021 | 14:50 | 15:30 | 0.67 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | Latch up BHA 1 out of derrick, scribe motor, set MWD
06/22/2021 | 15:30 | 15:45 | 0.25 | 108 | 208 | 100 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/208.00, w/WOB 5,Flow 416, RPM 40, Press 215, Tq 1700, ROP 400.00, Diff 15.00, Temp 95.00
06/22/2021 | 15:45 | 15:50 | 0.08 | 208 | 208 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 15:50 | 15:59 | 0.15 | 208 | 299 | 91 | SUR | 1: BHA 1 | 2K | Rotary Drill f/208.00 t/299.00, w/WOB 5,Flow 544, RPM 70, Press 900, Tq 1700, ROP 606.67, Diff 200.00, Temp 95.00
06/22/2021 | 15:59 | 16:05 | 0.1 | 299 | 299 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:05 | 16:11 | 0.1 | 299 | 389 | 90 | SUR | 1: BHA 1 | 2K | Rotary Drill f/299.00 t/389.00, w/WOB 5,Flow 750, RPM 90, Press 1450, Tq 2700, ROP 900.00, Diff 330.00, Temp 95.00
06/22/2021 | 16:11 | 16:14 | 0.05 | 389 | 389 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:14 | 16:20 | 0.1 | 389 | 482 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/389.00 t/482.00, w/WOB 10,Flow 900, RPM 100, Press 1900, Tq 4500, ROP 930.00, Diff 200.00, Temp 96.80
06/22/2021 | 16:20 | 16:23 | 0.05 | 482 | 482 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:23 | 16:28 | 0.08 | 482 | 576 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/482.00 t/576.00, w/WOB 10,Flow 900, RPM 100, Press 1900, Tq 4500, ROP 1128.00, Diff 200.00, Temp 96.80
06/22/2021 | 16:28 | 16:31 | 0.05 | 576 | 576 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:31 | 16:32 | 0.02 | 576 | 585 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/576.00 t/585.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 4500.00, ROP 540.00, Diff 200.00, Temp 96.80
06/22/2021 | 16:32 | 16:36 | 0.07 | 585 | 595 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/585.00 t/595.00, TF 270.00M, w/WOB 3.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 150.00, Diff 50.00, Temp 96.80
06/22/2021 | 16:36 | 16:39 | 0.05 | 595 | 670 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/595.00 t/670.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 4500.00, ROP 1500.00, Diff 200.00, Temp 96.80
06/22/2021 | 16:39 | 16:42 | 0.05 | 670 | 670 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:42 | 16:46 | 0.07 | 670 | 764 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/670.00 t/764.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 4500.00, ROP 1410.00, Diff 200.00, Temp 96.80
06/22/2021 | 16:46 | 16:49 | 0.05 | 764 | 764 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:49 | 16:53 | 0.07 | 764 | 858 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/764.00 t/858.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 4500.00, ROP 1410.00, Diff 200.00, Temp 96.80
06/22/2021 | 16:53 | 16:56 | 0.05 | 858 | 858 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 16:56 | 17:00 | 0.07 | 858 | 951 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/858.00 t/951.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 1395.00, Diff 200.00, Temp 96.80
06/22/2021 | 17:00 | 17:03 | 0.05 | 951 | 951 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 17:03 | 17:04 | 0.02 | 951 | 960 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/951.00 t/960.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 540.00, Diff 200.00, Temp 96.80
06/22/2021 | 17:04 | 17:08 | 0.07 | 960 | 970 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/960.00 t/970.00, TF 325.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 150.00, Diff 50.00, Temp 96.80
06/22/2021 | 17:08 | 17:12 | 0.07 | 970 | 1045 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/970.00 t/1045.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 1125.00, Diff 200.00, Temp 96.80
06/22/2021 | 17:12 | 17:15 | 0.05 | 1045 | 1045 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 17:15 | 17:17 | 0.03 | 1045 | 1055 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1045.00 t/1055.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 300.00, Diff 200.00, Temp 96.80
06/22/2021 | 17:17 | 17:20 | 0.05 | 1055 | 1065 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/1055.00 t/1065.00, TF 325.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 200.00, Diff 50.00, Temp 96.80
06/22/2021 | 17:20 | 17:24 | 0.07 | 1065 | 1139 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1065.00 t/1139.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 1110.00, Diff 200.00, Temp 96.80
06/22/2021 | 17:24 | 17:27 | 0.05 | 1139 | 1139 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 17:27 | 17:34 | 0.12 | 1139 | 1233 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1139.00 t/1233.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 805.71, Diff 200.00, Temp 96.80
06/22/2021 | 17:34 | 17:38 | 0.07 | 1233 | 1233 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 17:38 | 17:41 | 0.05 | 1233 | 1327 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1233.00 t/1327.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6500.00, ROP 1880.00, Diff 200.00, Temp 96.80
06/22/2021 | 17:41 | 17:44 | 0.05 | 1327 | 1327 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 17:44 | 17:45 | 0.02 | 1327 | 1335 | 8 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1327.00 t/1335.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 480.00, Diff 50.00, Temp 96.80
06/22/2021 | 17:45 | 17:49 | 0.07 | 1335 | 1347 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/1335.00 t/1347.00, TF 325.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 180.00, Diff 50.00, Temp 96.80
06/22/2021 | 17:49 | 17:53 | 0.07 | 1347 | 1419 | 72 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1347.00 t/1419.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 1080.00, Diff 50.00, Temp 96.80
06/22/2021 | 17:53 | 17:55 | 0.03 | 1419 | 1419 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 17:55 | 17:57 | 0.03 | 1419 | 1430 | 11 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1419.00 t/1430.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 330.00, Diff 50.00, Temp 96.80
06/22/2021 | 17:57 | 18:02 | 0.08 | 1430 | 1443 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/1430.00 t/1443.00, TF 325.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 156.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:02 | 18:07 | 0.08 | 1443 | 1513 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1443.00 t/1513.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 840.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:07 | 18:11 | 0.07 | 1513 | 1513 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 18:11 | 18:14 | 0.05 | 1513 | 1523 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1513.00 t/1523.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 200.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:14 | 18:22 | 0.13 | 1523 | 1537 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/1523.00 t/1537.00, TF 330.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 105.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:22 | 18:28 | 0.1 | 1537 | 1607 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1537.00 t/1607.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 700.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:28 | 18:30 | 0.03 | 1607 | 1607 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 18:30 | 18:33 | 0.05 | 1607 | 1617 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1607.00 t/1617.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 200.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:33 | 18:40 | 0.12 | 1617 | 1631 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/1617.00 t/1631.00, TF 330.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 120.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:40 | 18:44 | 0.07 | 1631 | 1700 | 69 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1631.00 t/1700.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 1035.00, Diff 50.00, Temp 96.80
06/22/2021 | 18:44 | 18:47 | 0.05 | 1700 | 1700 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 18:47 | 19:11 | 0.4 | 1700 | 1700 | 0 | SUR | 1: BHA 1 | 5A | Circulate Work On Celler Pumps
06/22/2021 | 19:11 | 19:16 | 0.08 | 1700 | 1700 | 0 | SUR | 1: BHA 1 | 5A | Recycle Mud Pumps for MWD Tool
06/22/2021 | 19:16 | 19:21 | 0.08 | 1700 | 1714 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/1700.00 t/1714.00, TF 330.00M, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 168.00, Diff 50.00, Temp 96.80
06/22/2021 | 19:21 | 19:26 | 0.08 | 1714 | 1794 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1714.00 t/1794.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 960.00, Diff 50.00, Temp 96.80
06/22/2021 | 19:26 | 19:28 | 0.03 | 1794 | 1794 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 19:28 | 19:32 | 0.07 | 1794 | 1804 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1794.00 t/1804.00, w/WOB 4.00,Flow 900.00, RPM 0.00, Press 1750.00, Tq 0.00, ROP 150.00, Diff 50.00, Temp 96.80
06/22/2021 | 19:32 | 19:38 | 0.1 | 1804 | 1817 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/1804.00 t/1817.00, TF 30.00G, w/WOB 4.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 130.00, Diff 50.00, Temp 105.00
06/22/2021 | 19:38 | 19:41 | 0.05 | 1817 | 1888 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1817.00 t/1888.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 1420.00, Diff 300.00, Temp 105.00
06/22/2021 | 19:41 | 19:45 | 0.07 | 1888 | 1888 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 19:45 | 19:49 | 0.07 | 1888 | 1898 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1888.00 t/1898.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 150.00, Diff 300.00, Temp 105.00
06/22/2021 | 19:49 | 19:53 | 0.07 | 1898 | 1911 | 13 | SUR | 1: BHA 1 | 2J | Slide Drill f/1898.00 t/1911.00, TF 20.00G, w/WOB 4.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 195.00, Diff 230.00, Temp 105.00
06/22/2021 | 19:53 | 20:00 | 0.12 | 1911 | 1982 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1911.00 t/1982.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 608.57, Diff 300.00, Temp 110.00
06/22/2021 | 20:00 | 20:02 | 0.03 | 1982 | 1982 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 20:02 | 20:03 | 0.02 | 1982 | 1992 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1982.00 t/1992.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 600.00, Diff 300.00, Temp 110.00
06/22/2021 | 20:03 | 20:09 | 0.1 | 1992 | 1992 | 0 | SUR | 1: BHA 1 | 5A | Recycle Mud Pumps for MWD Tool
06/22/2021 | 20:09 | 20:13 | 0.07 | 1992 | 2006 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/1992.00 t/2006.00, TF 20.00G, w/WOB 4.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 210.00, Diff 230.00, Temp 110.00
06/22/2021 | 20:13 | 20:17 | 0.07 | 2006 | 2076 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2006.00 t/2076.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 1050.00, Diff 300.00, Temp 110.00
06/22/2021 | 20:17 | 20:20 | 0.05 | 2076 | 2076 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 20:20 | 20:23 | 0.05 | 2076 | 2086 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2076.00 t/2086.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 200.00, Diff 300.00, Temp 110.00
06/22/2021 | 20:23 | 20:27 | 0.07 | 2086 | 2100 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/2086.00 t/2100.00, TF G, w/WOB 4.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 210.00, Diff 230.00, Temp 110.00
06/22/2021 | 20:27 | 20:33 | 0.1 | 2100 | 2169 | 69 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2100.00 t/2169.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 690.00, Diff 300.00, Temp 110.00
06/22/2021 | 20:33 | 20:34 | 0.02 | 2169 | 2169 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 20:34 | 20:37 | 0.05 | 2169 | 2180 | 11 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2169.00 t/2180.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2120.00, Tq 7500.00, ROP 220.00, Diff 300.00, Temp 110.00
06/22/2021 | 20:37 | 20:42 | 0.08 | 2180 | 2194 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/2180.00 t/2194.00, TF G, w/WOB 4.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 168.00, Diff 230.00, Temp 118.00
06/22/2021 | 20:42 | 20:47 | 0.08 | 2194 | 2264 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2194.00 t/2264.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2340.00, Tq 7500.00, ROP 840.00, Diff 390.00, Temp 118.00
06/22/2021 | 20:47 | 20:49 | 0.03 | 2264 | 2264 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 20:49 | 20:53 | 0.07 | 2264 | 2281 | 17 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2264.00 t/2281.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2340.00, Tq 7500.00, ROP 255.00, Diff 390.00, Temp 118.00
06/22/2021 | 20:53 | 20:58 | 0.08 | 2281 | 2295 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/2281.00 t/2295.00, TF G, w/WOB 4.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 168.00, Diff 100.00, Temp 118.00
06/22/2021 | 20:58 | 21:02 | 0.07 | 2295 | 2358 | 63 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2295.00 t/2358.00, w/WOB 5.00,Flow 900.00, RPM 100.00, Press 2612.00, Tq 7500.00, ROP 945.00, Diff 431.00, Temp 118.00
06/22/2021 | 21:02 | 21:04 | 0.03 | 2358 | 2358 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 21:04 | 21:12 | 0.13 | 2358 | 2451 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2358.00 t/2451.00, w/WOB 5.00,Flow 900.00, RPM 100.00, Press 2612.00, Tq 7500.00, ROP 697.50, Diff 431.00, Temp 118.00
06/22/2021 | 21:12 | 21:14 | 0.03 | 2451 | 2451 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 21:14 | 21:22 | 0.13 | 2451 | 2545 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2451.00 t/2545.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2612.00, Tq 7500.00, ROP 705.00, Diff 431.00, Temp 118.00
06/22/2021 | 21:22 | 21:24 | 0.03 | 2545 | 2545 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 21:24 | 21:33 | 0.15 | 2545 | 2639 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2545.00 t/2639.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2612.00, Tq 7500.00, ROP 626.67, Diff 431.00, Temp 118.00
06/22/2021 | 21:33 | 21:35 | 0.03 | 2639 | 2639 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/22/2021 | 21:35 | 21:45 | 0.17 | 2639 | 2732 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2639.00 t/2732.00, w/WOB 4.00,Flow 900.00, RPM 100.00, Press 2612.00, Tq 7500.00, ROP 558.00, Diff 431.00, Temp 118.00
06/22/2021 | 21:45 | 21:49 | 0.07 | 2732 | 2732 | 0 | SUR | 1: BHA 1 | 5A | Final Survey
06/22/2021 | 21:49 | 22:00 | 0.18 | 2732 | 2732 | 0 | SUR | 1: BHA 1 | 5A | Circulate and pump Sweeps - Prep to POOH
06/22/2021 | 22:00 | 22:12 | 0.2 | 2732 | 2732 | 0 | SUR | 1: BHA 1 | 6I | Flow Check
06/22/2021 | 22:12 | 24:00 | 1.8 | 2732 | 2732 | 0 | SUR | 1: BHA 1 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_23_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/23/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 14000
|  |  |  | 24hr Summary: |  | Run Casing and Cement.
|  |  |  | 24hr Lookahead: |  | Run Casing
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2732 |  | 108 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 2732 |  | 2732 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  |  |  | 2624 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  |  |  | 179 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  |  |  | 2445 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  |  |  | 4.37 / 2.13 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: |  |  |  | 1.13 |  | SN: |  | 38426 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  |  |  | 3.23 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  |  |  | 756.19 / 157.94 |  | OD (in) / TFA: |  | 13.500 / 1.178
BRT Hrs: |  | 0.67 |  | 9.17 |  | Grade In: |  | New
% Slide: |  |  |  | 6.82 |  | Grade Out: |  | 1-2-CT-S-X-I-CT-TD
% Rotary: |  |  |  | 93.18 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.18 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
Stabalizer |  |  |  | 13 | 2.875 |  |  |  |  | 7.86 |  | 9.36
7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  |  | 8 | 2 |  |  |  |  | 37.43 |  | 46.79
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.95 |  | 54.74
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.74 |  | 58.48
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.74 |  | 87.22
NM Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 28.8 |  | 116.02
Crossover |  |  |  | 6.5 | 3.062 |  |  |  |  | 2.08 |  | 118.1
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 389.14
389.14
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800067 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.57 |  | 1.5 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 7.8 | 88.89 | 222 | 801 | 1571.5 | 1392 | 0 | 60 | 60 | 60 | 3677.78 | 0
Run | 600.92 | 7.8 | 88.89 | 222 | 801 | 1571.5 | 1392 | 0 | 60 | 60 | 60 | 3677.78 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/23/2021 |  | 2 |  | 6450
Perdiem Per Hand |  |  |  |  | 06/23/2021 |  | 6 |  | 100
Stabilizer Rental 13 Used |  |  |  |  | 06/23/2021 |  | 17 |  | 1150
Job Start-Up Incidentals |  |  |  |  | 06/23/2021 |  | 1 |  | 6000
Total | [11 empty] | 0
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/23/2021 | 00:00 | 00:40 | 0.67 | 2732 | 2732 | 0 | SUR | 1: BHA 1 | 6P | C/O Bit & Rack Back BHA in Derrick
06/23/2021 | 00:40 | 24:00 | 23.33 | 2732 | 2732 | 0 | SUR |  | 24B | Standby - Run Casing & Cement.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_1_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/01/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 31350
|  |  |  | 24hr Summary: |  | Ran intermediate casing on 3H - skid to 2H. Test BOPs
|  |  |  | 24hr Lookahead: |  | Finish up testing. Pick up BHA 2, TIH, Drill out float equipment, begin drilling intermediate section
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2732 |  | 2732 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 11
End Depth (Usft): |  | 3680 |  | 3680 |  | OD (in): |  |  |  | 300: | 18 | YP: | 7
Total Drilled (Usft): |  | 948 |  | 948 |  | Weight (ft/lbs): |  |  |  | 200: | 14 | Viscosity: | 51
Slide Drilled (Usft): |  | 17 |  | 17 | [5 empty] | 100: | 9 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 931 |  | 931 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.20
Drlg/Circ Hrs: |  | 3.22 / 1.38 |  | 3.22 / 1.38 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 0.28 |  | 0.28 |  | SN: |  | 56211 |  | 10s Gel: | 9 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 2.93 |  | 2.93 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 100.00 | Fluid Loss / Mud Type: | 6 / WBM
ROP Rot/Slide (Usft/hr): |  | 317.39 / 60.00 |  | 317.39 / 60.00 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 13.25 |  | 13.25 |  | Grade In: |  | New
% Slide: |  | 1.79 |  | 1.79 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 98.21 |  | 98.21 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.014 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.91 |  | 39.41
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.74
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.57
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80.33
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.36
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 111.26
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.38
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.38
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.42
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.61
Agitator |  |  |  | 6.625 | 3.75 |  |  |  |  | 24.71 |  | 2565.32
2565.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800032 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.78 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2777 | 10.78 | 320.94 | 2760.33 | 175.06 | -126.68 | 0.3 |  | 156.67 | -215.89 | -0.27 |  | 0.63 | 118
2871 | 10.59 | 320.95 | 2852.7 | 188.59 | -137.66 | 0.2 |  | 179.45 | -233.32 | -0.2 |  | 0.01 | 94
2965 | 10.62 | 320.15 | 2945.1 | 201.95 | -148.65 | 0.16 |  | -78.88 | -250.61 | 0.03 |  | -0.85 | 94
3058 | 11 | 318.52 | 3036.45 | 215.18 | -160.02 | 0.52 |  | -39.62 | -268.04 | 0.41 |  | -1.75 | 93
3152 | 11.25 | 316.79 | 3128.68 | 228.58 | -172.24 | 0.44 |  | -54.02 | -286.13 | 0.27 |  | -1.84 | 94
3246 | 11.32 | 315.48 | 3220.86 | 241.84 | -184.98 | 0.28 |  | -75.37 | -304.44 | 0.07 |  | -1.39 | 94
3339 | 11.37 | 315.97 | 3312.05 | 254.94 | -197.75 | 0.12 |  | 62.82 | -322.63 | 0.05 |  | 0.53 | 93
3433 | 10.94 | 319.88 | 3404.27 | 268.42 | -209.94 | 0.93 |  | 121.52 | -340.77 | -0.46 |  | 4.16 | 94
3527 | 10.52 | 319.04 | 3496.63 | 281.72 | -221.32 | 0.48 |  | -159.99 | -358.26 | -0.45 |  | -0.89 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 294.72 | 27.89 | 74.29 | 192 | 706.67 | 3427.78 | 2795.56 | 0 | 150 | 135 | 120 | 7000 | 0
Run | 294.72 | 27.89 | 74.29 | 192 | 706.67 | 3427.78 | 2795.56 | 0 | 150 | 135 | 120 | 7000 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 07/01/2021 |  | 1 |  | 6000
Directional & MWD / Gamma Services |  |  |  |  | 07/01/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/01/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 07/01/2021 |  | 17 |  | 1150
Directional & MWD Standby |  |  |  |  | 07/01/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/01/2021 |  | 15 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/01/2021 | 00:00 | 09:15 | 9.25 | 2732 | 2732 | 0 | INT |  | 24B | Standby for rig skid
07/01/2021 | 09:15 | 10:45 | 1.5 | 2732 | 2732 | 0 | INT | 2: BHA 2 | 6O | Pick up BHA 2
07/01/2021 | 10:45 | 10:50 | 0.08 | 2732 | 2732 | 0 | INT | 2: BHA 2 | 5A | Surface test MWD tool
07/01/2021 | 10:50 | 14:04 | 3.23 | 2732 | 2732 | 0 | INT | 2: BHA 2 | 6A | TIH to 2600
07/01/2021 | 14:04 | 14:51 | 0.78 | 2732 | 2732 | 0 | INT | 2: BHA 2 | 5A | Driill out float equipment and shoe track
07/01/2021 | 14:51 | 14:54 | 0.05 | 2732 | 2742 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/2732.00 t/2742.00, w/WOB 20,Flow 430, RPM 40, Press 900, Tq 3500, ROP 200.00, Diff 110.00, Temp 129.00
07/01/2021 | 14:54 | 15:10 | 0.27 | 2742 | 2742 | 0 | INT | 2: BHA 2 | 5A | Circulate bottoms up
07/01/2021 | 15:10 | 15:54 | 0.73 | 2742 | 2742 | 0 | INT | 2: BHA 2 | 15D | FIT
07/01/2021 | 15:54 | 16:14 | 0.33 | 2742 | 2847 | 105 | INT | 2: BHA 2 | 2K | Rotary Drill f/2742.00 t/2847.00, w/WOB 20.00,Flow 700, RPM 80, Press 3500, Tq 6500, ROP 315.00, Diff 780.00, Temp 129.00
07/01/2021 | 16:14 | 16:19 | 0.08 | 2847 | 2847 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/01/2021 | 16:19 | 16:24 | 0.08 | 2847 | 2941 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/2847.00 t/2941.00, w/WOB 32,Flow 900, RPM 80, Press 5000, Tq 7000, ROP 1128.00, Diff 800.00, Temp 129.00
07/01/2021 | 16:24 | 16:29 | 0.08 | 2941 | 2941 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/01/2021 | 16:29 | 16:44 | 0.25 | 2941 | 3035 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/2941.00 t/3035.00, w/WOB 32,Flow 900, RPM 80, Press 5000, Tq 7000, ROP 376.00, Diff 800.00, Temp 129.00
07/01/2021 | 16:44 | 16:49 | 0.08 | 3035 | 3035 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/01/2021 | 16:49 | 21:30 | 4.68 | 3035 | 3035 | 0 | INT | 2: BHA 2 | 8O | Repair Leak On Stand Pipe
07/01/2021 | 21:30 | 22:54 | 1.4 | 3035 | 3420 | 385 | INT | 2: BHA 2 | 2K | Rotary Drill f/3035.00 t/3420.00, w/WOB 37,Flow 686, RPM 80, Press 3450, Tq 1000, ROP 275.00, Diff 800.00, Temp 134.00
07/01/2021 | 22:54 | 22:59 | 0.08 | 3420 | 3430 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/3420.00 t/3430.00, TF 135G, w/WOB 15,Flow 686, Press 900.00, Tq 0, ROP 120.00, Diff 110.00, Temp 129.00
07/01/2021 | 22:59 | 23:38 | 0.65 | 3430 | 3601 | 171 | INT | 2: BHA 2 | 2K | Rotary Drill f/3430.00 t/3601.00, w/WOB 40,Flow 686.00, RPM 80, Press 3350, Tq 12000, ROP 263.08, Diff 700.00, Temp 134.00
07/01/2021 | 23:38 | 23:50 | 0.2 | 3601 | 3608 | 7 | INT | 2: BHA 2 | 2J | Slide Drill f/3601.00 t/3608.00, TF 90G, w/WOB 15.00,Flow 686.00, Press 3150, Tq 0.00, ROP 35.00, Diff 500.00, Temp 134.00
07/01/2021 | 23:50 | 24:00 | 0.17 | 3608 | 3680 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/3608.00 t/3680.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3350.00, Tq 12000.00, ROP 432.00, Diff 700.00, Temp 134.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_2_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/02/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 38200
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3680 |  | 2732 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 11
End Depth (Usft): |  | 8966 |  | 8966 |  | OD (in): |  |  |  | 300: | 18 | YP: | 7
Total Drilled (Usft): |  | 5286 |  | 6234 |  | Weight (ft/lbs): |  |  |  | 200: | 14 | Viscosity: | 51
Slide Drilled (Usft): |  | 165 |  | 182 | [5 empty] | 100: | 9 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 5121 |  | 6052 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.20
Drlg/Circ Hrs: |  | 18.47 / 5.13 |  | 21.68 / 6.52 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 3.42 |  | 3.7 |  | SN: |  | 56211 |  | 10s Gel: | 9 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 15.05 |  | 17.98 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 100.00 | Fluid Loss / Mud Type: | 6 / WBM
ROP Rot/Slide (Usft/hr): |  | 340.27 / 48.29 |  | 336.53 / 49.19 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 37.25 |  | Grade In: |  | New
% Slide: |  | 3.12 |  | 2.92 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 96.88 |  | 97.08 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.014 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.91 |  | 39.41
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.74
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.57
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80.33
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.36
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 111.26
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.38
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.38
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.42
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.61
Agitator |  |  |  | 6.625 | 3.75 |  |  |  |  | 24.71 |  | 2565.32
2565.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800032 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.78 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3621 | 11.09 | 323.65 | 3588.96 | 295.49 | -232.3 | 1.1 |  | 58.87 | -375.86 | 0.61 |  | 4.9 | 94
3715 | 11.2 | 324.6 | 3681.19 | 310.21 | -242.95 | 0.23 |  | 59.54 | -394.02 | 0.12 |  | 1.01 | 94
3809 | 10.97 | 325.02 | 3773.44 | 324.98 | -253.36 | 0.26 |  | 160.86 | -412.06 | -0.24 |  | 0.45 | 94
3902 | 10.68 | 324.25 | 3864.78 | 339.22 | -263.47 | 0.35 |  | -153.87 | -429.5 | -0.31 |  | -0.83 | 93
3997 | 10.76 | 324.32 | 3958.12 | 353.57 | -273.79 | 0.09 |  | 9.28 | -447.16 | 0.08 |  | 0.07 | 95
4092 | 10.84 | 323.91 | 4051.44 | 367.99 | -284.22 | 0.12 |  | -44.04 | -464.94 | 0.08 |  | -0.43 | 95
4187 | 10.13 | 326.55 | 4144.85 | 382.18 | -294.09 | 0.9 |  | 147.21 | -482.19 | -0.75 |  | 2.78 | 95
4282 | 9.81 | 326.83 | 4238.42 | 395.93 | -303.12 | 0.34 |  | 171.52 | -498.58 | -0.34 |  | 0.29 | 95
4377 | 10.02 | 326.35 | 4332 | 409.58 | -312.13 | 0.24 |  | -21.72 | -514.87 | 0.22 |  | -0.51 | 95
4471 | 10.23 | 325.39 | 4424.54 | 423.26 | -321.4 | 0.29 |  | -39.26 | -531.35 | 0.22 |  | -1.02 | 94
4564 | 9.98 | 325.39 | 4516.09 | 436.69 | -330.67 | 0.27 |  | 180 | -547.64 | -0.27 |  | 0 | 93
4659 | 9.89 | 323.23 | 4609.67 | 450 | -340.23 | 0.4 |  | -104.64 | -564.01 | -0.09 |  | -2.27 | 95
4753 | 9.75 | 322.34 | 4702.29 | 462.77 | -349.92 | 0.22 |  | -133.12 | -580.03 | -0.15 |  | -0.95 | 94
4847 | 9.63 | 320.71 | 4794.95 | 475.15 | -359.76 | 0.32 |  | -114.43 | -595.85 | -0.13 |  | -1.73 | 94
4940 | 9.19 | 320.22 | 4886.7 | 486.88 | -369.44 | 0.48 |  | -169.92 | -611.06 | -0.47 |  | -0.53 | 93
5034 | 8.97 | 318.89 | 4979.52 | 498.17 | -379.06 | 0.32 |  | -137 | -625.88 | -0.23 |  | -1.41 | 94
5128 | 10.18 | 324.4 | 5072.21 | 510.45 | -388.72 | 1.61 |  | 39.88 | -641.5 | 1.29 |  | 5.86 | 94
5221 | 10.93 | 325.37 | 5163.64 | 524.38 | -398.51 | 0.83 |  | 13.81 | -658.5 | 0.81 |  | 1.04 | 93
5316 | 11.14 | 323.04 | 5256.88 | 539.13 | -409.15 | 0.52 |  | -65.93 | -676.67 | 0.22 |  | -2.45 | 95
5411 | 10.6 | 325.74 | 5350.18 | 553.68 | -419.59 | 0.78 |  | 138 | -694.56 | -0.57 |  | 2.84 | 95
5506 | 10.06 | 325.18 | 5443.64 | 567.72 | -429.24 | 0.58 |  | -169.74 | -711.55 | -0.57 |  | -0.59 | 95
5600 | 10.4 | 324.81 | 5536.14 | 581.39 | -438.82 | 0.37 |  | -11.12 | -728.22 | 0.36 |  | -0.39 | 94
5694 | 10.52 | 324.11 | 5628.58 | 595.28 | -448.74 | 0.19 |  | -46.99 | -745.27 | 0.13 |  | -0.74 | 94
5788 | 10.16 | 323.93 | 5721.05 | 608.93 | -458.65 | 0.38 |  | -174.96 | -762.12 | -0.38 |  | -0.19 | 94
5881 | 9.47 | 323.91 | 5812.69 | 621.74 | -467.99 | 0.74 |  | -179.73 | -777.96 | -0.74 |  | -0.02 | 93
5976 | 9.22 | 322.82 | 5906.43 | 634.12 | -477.19 | 0.32 |  | -145.24 | -793.38 | -0.26 |  | -1.15 | 95
6069 | 9.53 | 322.12 | 5998.19 | 646.13 | -486.42 | 0.36 |  | -20.54 | -808.53 | 0.33 |  | -0.75 | 93
6163 | 9.46 | 322.46 | 6090.9 | 658.4 | -495.91 | 0.1 |  | 141.46 | -824.04 | -0.07 |  | 0.36 | 94
6258 | 9.35 | 320.2 | 6184.62 | 670.52 | -505.6 | 0.41 |  | -107.7 | -839.56 | -0.12 |  | -2.38 | 95
6352 | 8.79 | 323.9 | 6277.45 | 682.19 | -514.72 | 0.86 |  | 135.65 | -854.37 | -0.6 |  | 3.94 | 94
6446 | 7.16 | 319.57 | 6370.54 | 692.45 | -522.75 | 1.85 |  | -161.9 | -867.4 | -1.73 |  | -4.61 | 94
6540 | 6.63 | 317.8 | 6463.86 | 700.93 | -530.2 | 0.61 |  | -159.03 | -878.67 | -0.56 |  | -1.88 | 94
6634 | 6.42 | 315.72 | 6557.25 | 708.71 | -537.51 | 0.34 |  | -132.65 | -889.31 | -0.22 |  | -2.21 | 94
6728 | 6.05 | 330.51 | 6650.7 | 716.79 | -543.62 | 1.75 |  | 110.25 | -899.43 | -0.39 |  | 15.73 | 94
6822 | 5.78 | 333.87 | 6744.2 | 725.35 | -548.14 | 0.47 |  | 129.61 | -908.95 | -0.29 |  | 3.57 | 94
6915 | 5.54 | 331.22 | 6836.75 | 733.49 | -552.37 | 0.38 |  | -133.87 | -917.96 | -0.26 |  | -2.85 | 93
7009 | 4.29 | 338.64 | 6930.4 | 740.74 | -555.83 | 1.49 |  | 156.71 | -925.79 | -1.33 |  | 7.89 | 94
7103 | 4.15 | 341.24 | 7024.14 | 747.24 | -558.21 | 0.25 |  | 127.49 | -932.36 | -0.15 |  | 2.77 | 94
7197 | 3.84 | 336.77 | 7117.92 | 753.35 | -560.54 | 0.47 |  | -137.08 | -938.6 | -0.33 |  | -4.76 | 94
7290 | 3.9 | 327.38 | 7210.71 | 758.88 | -563.47 | 0.68 |  | -89.29 | -944.76 | 0.06 |  | -10.1 | 93
7385 | 2.48 | 334.1 | 7305.56 | 763.45 | -566.11 | 1.54 |  | 168.58 | -949.98 | -1.49 |  | 7.07 | 95
7478 | 2.02 | 335.64 | 7398.48 | 766.75 | -567.67 | 0.5 |  | 173.28 | -953.53 | -0.49 |  | 1.66 | 93
7572 | 2.15 | 336.37 | 7492.42 | 769.87 | -569.06 | 0.14 |  | 11.91 | -956.85 | 0.14 |  | 0.78 | 94
7666 | 2.1 | 334.86 | 7586.36 | 773.05 | -570.5 | 0.08 |  | -132.52 | -960.23 | -0.05 |  | -1.61 | 94
7760 | 1.88 | 337.05 | 7680.3 | 776.03 | -571.83 | 0.25 |  | 162.02 | -963.39 | -0.23 |  | 2.33 | 94
7854 | 1.67 | 326.74 | 7774.26 | 778.59 | -573.18 | 0.41 |  | -128.41 | -966.24 | -0.22 |  | -10.97 | 94
7948 | 1.81 | 323.15 | 7868.21 | 780.93 | -574.82 | 0.19 |  | -39.71 | -969.09 | 0.15 |  | -3.82 | 94
8042 | 1.97 | 322.66 | 7962.16 | 783.4 | -576.69 | 0.17 |  | -6.01 | -972.19 | 0.17 |  | -0.52 | 94
8136 | 1.8 | 326.62 | 8056.11 | 785.92 | -578.49 | 0.23 |  | 144.51 | -975.28 | -0.18 |  | 4.21 | 94
8230 | 1.38 | 311.19 | 8150.07 | 787.89 | -580.15 | 0.63 |  | -141.99 | -977.86 | -0.45 |  | -16.41 | 94
8324 | 1.3 | 314.75 | 8244.05 | 789.39 | -581.76 | 0.12 |  | 135.63 | -980.03 | -0.09 |  | 0 | 94
8417 | 1.27 | 297.67 | 8337.03 | 790.61 | -583.42 | 0.41 |  | -102.98 | -982.02 | -0.03 |  | 0 | 93
8511 | 0.44 | 136.68 | 8431.02 | 790.83 | -584.1 | 1.8 |  | -175.14 | -982.62 | -0.88 |  | 0 | 94
8605 | 1.5 | 119.46 | 8525 | 789.96 | -582.78 | 1.16 |  | -24.1 | -981.12 | 1.13 |  | 0 | 94
8699 | 1.17 | 87.76 | 8618.98 | 789.4 | -580.75 | 0.85 |  | -129.37 | -979.41 | -0.35 |  | -33.72 | 94
8793 | 1.95 | 60.05 | 8712.95 | 790.23 | -578.4 | 1.13 |  | -58.46 | -978.61 | 0.83 |  | 0 | 94
8887 | 1.79 | 59.07 | 8806.9 | 791.79 | -575.76 | 0.17 |  | -169.19 | -978.19 | -0.17 |  | -1.04 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 286.25 | 37.48 | 80 | 204 | 746.62 | 4411.25 | 3702.7 | 0 | 206.09 | 183.28 | 161.64 | 21538.46 | 0
Run | 287.5 | 36.3 | 79.32 | 202 | 741.7 | 4290 | 3590.86 | 0 | 199.18 | 177.33 | 156.51 | 19813.56 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 07/02/2021 |  | 1 |  | 6000
Directional & MWD / Gamma Services |  |  |  |  | 07/02/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/02/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 07/02/2021 |  | 17 |  | 1150
Directional & MWD Standby |  |  |  |  | 07/02/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/02/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/02/2021 | 00:00 | 01:38 | 1.63 | 3680 | 4170 | 490 | INT | 2: BHA 2 | 2K | Rotary Drill f/3680.00 t/4170.00, w/WOB 47,Flow 686.00, RPM 80.00, Press 3370.00, Tq 15000.00, ROP 300.00, Diff 720.00, Temp 152.00
07/02/2021 | 01:38 | 01:45 | 0.12 | 4170 | 4178 | 8 | INT | 2: BHA 2 | 2J | Slide Drill f/4170.00 t/4178.00, TF 0.00G, w/WOB 15,Flow 686.00, Press 3150, Tq 15000.00, ROP 68.57, Diff 500.00, Temp 152.00
07/02/2021 | 01:45 | 04:27 | 2.7 | 4178 | 5115 | 937 | INT | 2: BHA 2 | 2K | Rotary Drill f/4178.00 t/5115.00, w/WOB 47,Flow 686.00, RPM 80, Press 3450, Tq 17000, ROP 347.04, Diff 800.00, Temp 165.00
07/02/2021 | 04:27 | 04:30 | 0.05 | 5115 | 5125 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5115.00 t/5125.00, TF 60G, w/WOB 15.00,Flow 686.00, Press 3250, Tq 0, ROP 200.00, Diff 227.00, Temp 152.00
07/02/2021 | 04:30 | 05:21 | 0.85 | 5125 | 5396 | 271 | INT | 2: BHA 2 | 2K | Rotary Drill f/5125.00 t/5396.00, w/WOB 40,Flow 686.00, RPM 80, Press 4100, Tq 22000, ROP 318.82, Diff 800.00, Temp 168.00
07/02/2021 | 05:21 | 05:29 | 0.13 | 5396 | 5404 | 8 | INT | 2: BHA 2 | 2J | Slide Drill f/5396.00 t/5404.00, TF 160G, w/WOB 15.00,Flow 686.00, Press 3700, Tq 0.00, ROP 60.00, Diff 400.00, Temp 168.00
07/02/2021 | 05:29 | 05:41 | 0.2 | 5404 | 5481 | 77 | INT | 2: BHA 2 | 2K | Rotary Drill f/5404.00 t/5481.00, w/WOB 40,Flow 686.00, RPM 80, Press 4100, Tq 22000, ROP 385.00, Diff 800.00, Temp 168.00
07/02/2021 | 05:41 | 05:46 | 0.08 | 5481 | 5481 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 05:46 | 05:57 | 0.18 | 5481 | 5576 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5481.00 t/5576.00, w/WOB 40,Flow 686.00, RPM 80, Press 4100, Tq 22000, ROP 518.18, Diff 800.00, Temp 168.00
07/02/2021 | 05:57 | 06:03 | 0.1 | 5576 | 5576 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 06:03 | 06:17 | 0.23 | 5576 | 5670 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5576.00 t/5670.00, w/WOB 40,Flow 686.00, RPM 80, Press 4100, Tq 22000, ROP 402.86, Diff 800.00, Temp 168.00
07/02/2021 | 06:17 | 06:22 | 0.08 | 5670 | 5670 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 06:22 | 06:54 | 0.53 | 5670 | 5858 | 188 | INT | 2: BHA 2 | 2K | Rotary Drill f/5670.00 t/5858.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 352.50, Diff 800.00, Temp 168.00
07/02/2021 | 06:54 | 07:00 | 0.1 | 5858 | 5858 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 07:00 | 07:13 | 0.22 | 5858 | 5951 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5858.00 t/5951.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 429.23, Diff 800.00, Temp 168.00
07/02/2021 | 07:13 | 07:18 | 0.08 | 5951 | 5951 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 07:18 | 07:30 | 0.2 | 5951 | 6046 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5951.00 t/6046.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 475.00, Diff 800.00, Temp 168.00
07/02/2021 | 07:30 | 07:35 | 0.08 | 6046 | 6046 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 07:35 | 07:47 | 0.2 | 6046 | 6111 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/6046.00 t/6111.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 325.00, Diff 800.00, Temp 168.00
07/02/2021 | 07:47 | 09:49 | 2.03 | 6111 | 6111 | 0 | INT | 2: BHA 2 | 5A | Circulte while making repairs to mud pump
07/02/2021 | 09:49 | 09:54 | 0.08 | 6111 | 6139 | 28 | INT | 2: BHA 2 | 2K | Rotary Drill f/6111.00 t/6139.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 336.00, Diff 800.00, Temp 168.00
07/02/2021 | 09:54 | 10:00 | 0.1 | 6139 | 6139 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 10:00 | 10:11 | 0.18 | 6139 | 6233 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6139.00 t/6233.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 512.73, Diff 800.00, Temp 168.00
07/02/2021 | 10:11 | 10:15 | 0.07 | 6233 | 6233 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 10:15 | 10:34 | 0.32 | 6233 | 6328 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6233.00 t/6328.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 300.00, Diff 800.00, Temp 168.00
07/02/2021 | 10:34 | 10:44 | 0.17 | 6328 | 6328 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 10:44 | 10:49 | 0.08 | 6328 | 6340 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6328.00 t/6340.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 144.00, Diff 800.00, Temp 168.00
07/02/2021 | 10:49 | 11:00 | 0.18 | 6340 | 6355 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6340.00 t/6355.00, TF 140.00G, w/WOB 15,Flow 686.00, Press 3600.00, Tq 0.00, ROP 81.82, Diff 300.00, Temp 177.00
07/02/2021 | 11:00 | 11:12 | 0.2 | 6355 | 6422 | 67 | INT | 2: BHA 2 | 2K | Rotary Drill f/6355.00 t/6422.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 335.00, Diff 800.00, Temp 177.00
07/02/2021 | 11:12 | 11:17 | 0.08 | 6422 | 6422 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 11:17 | 11:19 | 0.03 | 6422 | 6435 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/6422.00 t/6435.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 390.00, Diff 800.00, Temp 177.00
07/02/2021 | 11:19 | 11:29 | 0.17 | 6435 | 6450 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6435.00 t/6450.00, TF 140.00G, w/WOB 15,Flow 686.00, Press 3600.00, Tq 0.00, ROP 90.00, Diff 300.00, Temp 177.00
07/02/2021 | 11:29 | 11:39 | 0.17 | 6450 | 6516 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/6450.00 t/6516.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 396.00, Diff 600.00, Temp 177.00
07/02/2021 | 11:39 | 11:45 | 0.1 | 6516 | 6516 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 11:45 | 12:00 | 0.25 | 6516 | 6610 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6516.00 t/6610.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 376.00, Diff 600.00, Temp 177.00
07/02/2021 | 12:00 | 12:05 | 0.08 | 6610 | 6610 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 12:05 | 12:19 | 0.23 | 6610 | 6704 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6610.00 t/6704.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 402.86, Diff 600.00, Temp 177.00
07/02/2021 | 12:19 | 12:25 | 0.1 | 6704 | 6704 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 12:25 | 12:28 | 0.05 | 6704 | 6715 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/6704.00 t/6715.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 220.00, Diff 600.00, Temp 177.00
07/02/2021 | 12:28 | 12:36 | 0.13 | 6715 | 6730 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6715.00 t/6730.00, TF 130G, w/WOB 40.00,Flow 686.00, Press 3600.00, Tq 0.00, ROP 112.50, Diff 300.00, Temp 188.00
07/02/2021 | 12:36 | 13:09 | 0.55 | 6730 | 6892 | 162 | INT | 2: BHA 2 | 2K | Rotary Drill f/6730.00 t/6892.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 294.55, Diff 600.00, Temp 188.00
07/02/2021 | 13:09 | 13:15 | 0.1 | 6892 | 6892 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 13:15 | 13:28 | 0.22 | 6892 | 6985 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6892.00 t/6985.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 429.23, Diff 600.00, Temp 188.00
07/02/2021 | 13:28 | 13:33 | 0.08 | 6985 | 6985 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 13:33 | 13:36 | 0.05 | 6985 | 6995 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/6985.00 t/6995.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 200.00, Diff 600.00, Temp 188.00
07/02/2021 | 13:36 | 13:47 | 0.18 | 6995 | 7010 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6995.00 t/7010.00, TF 180G, w/WOB 15,Flow 686.00, Press 3600.00, Tq 0.00, ROP 81.82, Diff 300.00, Temp 188.00
07/02/2021 | 13:47 | 14:00 | 0.22 | 7010 | 7079 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/7010.00 t/7079.00, w/WOB 40.00,Flow 686.00, RPM 80, Press 3900, Tq 22000, ROP 318.46, Diff 600.00, Temp 188.00
07/02/2021 | 14:00 | 14:05 | 0.08 | 7079 | 7079 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 14:05 | 14:23 | 0.3 | 7079 | 7173 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7079.00 t/7173.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 313.33, Diff 600.00, Temp 188.00
07/02/2021 | 14:23 | 14:29 | 0.1 | 7173 | 7173 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 14:29 | 14:46 | 0.28 | 7173 | 7267 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7173.00 t/7267.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 331.76, Diff 600.00, Temp 188.00
07/02/2021 | 14:46 | 14:51 | 0.08 | 7267 | 7267 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 14:51 | 15:10 | 0.32 | 7267 | 7360 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7267.00 t/7360.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 293.68, Diff 600.00, Temp 188.00
07/02/2021 | 15:10 | 15:15 | 0.08 | 7360 | 7360 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 15:15 | 15:18 | 0.05 | 7360 | 7370 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7360.00 t/7370.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 200.00, Diff 600.00, Temp 188.00
07/02/2021 | 15:18 | 15:35 | 0.28 | 7370 | 7390 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7370.00 t/7390.00, TF 120M, w/WOB 15,Flow 686.00, Press 3600, Tq 0, ROP 70.59, Diff 300.00, Temp 188.00
07/02/2021 | 15:35 | 15:50 | 0.25 | 7390 | 7455 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/7390.00 t/7455.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 260.00, Diff 600.00, Temp 188.00
07/02/2021 | 15:50 | 15:55 | 0.08 | 7455 | 7455 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 15:55 | 16:16 | 0.35 | 7455 | 7548 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7455.00 t/7548.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 265.71, Diff 600.00, Temp 188.00
07/02/2021 | 16:16 | 16:20 | 0.07 | 7548 | 7548 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 16:20 | 16:39 | 0.32 | 7548 | 7642 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7548.00 t/7642.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 296.84, Diff 600.00, Temp 188.00
07/02/2021 | 16:39 | 16:45 | 0.1 | 7642 | 7642 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 16:45 | 16:58 | 0.22 | 7642 | 7736 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7642.00 t/7736.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 433.85, Diff 600.00, Temp 188.00
07/02/2021 | 16:58 | 17:03 | 0.08 | 7736 | 7736 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 17:03 | 17:23 | 0.33 | 7736 | 7830 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7736.00 t/7830.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 282.00, Diff 600.00, Temp 203.00
07/02/2021 | 17:23 | 17:28 | 0.08 | 7830 | 7830 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 17:28 | 17:45 | 0.28 | 7830 | 7924 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7830.00 t/7924.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 331.76, Diff 600.00, Temp 203.00
07/02/2021 | 17:45 | 17:49 | 0.07 | 7924 | 7924 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 17:49 | 18:00 | 0.18 | 7924 | 8018 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7924.00 t/8018.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 512.73, Diff 600.00, Temp 203.00
07/02/2021 | 18:00 | 18:05 | 0.08 | 8018 | 8018 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 18:05 | 18:20 | 0.25 | 8018 | 8112 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8018.00 t/8112.00, w/WOB 40.00,Flow 686.00, RPM 80.00, Press 3900.00, Tq 22000.00, ROP 376.00, Diff 600.00, Temp 203.00
07/02/2021 | 18:20 | 18:30 | 0.17 | 8112 | 8112 | 0 | INT | 2: BHA 2 | 10D | Recycle For Survey
07/02/2021 | 18:30 | 18:36 | 0.1 | 8112 | 8136 | 24 | INT | 2: BHA 2 | 2K | Rotary Drill f/8112.00 t/8136.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 20000.00, ROP 240.00, Diff 900.00, Temp 203.00
07/02/2021 | 18:36 | 18:50 | 0.23 | 8136 | 8136 | 0 | INT | 2: BHA 2 | 8L | 2 On Stand Pipe Leaking
07/02/2021 | 18:50 | 19:03 | 0.22 | 8136 | 8206 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/8136.00 t/8206.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 20000.00, ROP 323.08, Diff 900.00, Temp 206.00
07/02/2021 | 19:03 | 19:06 | 0.05 | 8206 | 8206 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 19:06 | 19:12 | 0.1 | 8206 | 8212 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/8206.00 t/8212.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 20000.00, ROP 60.00, Diff 900.00, Temp 206.00
07/02/2021 | 19:12 | 19:34 | 0.37 | 8212 | 8227 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8212.00 t/8227.00, TF M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0, ROP 40.91, Diff 900.00, Temp 206.00
07/02/2021 | 19:34 | 19:44 | 0.17 | 8227 | 8300 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/8227.00 t/8300.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 20000, ROP 438.00, Diff 900.00, Temp 206.00
07/02/2021 | 19:44 | 19:49 | 0.08 | 8300 | 8300 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 19:49 | 19:58 | 0.15 | 8300 | 8394 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8300.00 t/8394.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 20000, ROP 626.67, Diff 900.00, Temp 206.00
07/02/2021 | 19:58 | 20:03 | 0.08 | 8394 | 8394 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 20:03 | 20:07 | 0.07 | 8394 | 8405 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/8394.00 t/8405.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 20000, ROP 165.00, Diff 900.00, Temp 206.00
07/02/2021 | 20:07 | 20:30 | 0.38 | 8405 | 8422 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/8405.00 t/8422.00, TF 135M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0, ROP 44.35, Diff 900.00, Temp 206.00
07/02/2021 | 20:30 | 20:46 | 0.27 | 8422 | 8487 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/8422.00 t/8487.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 243.75, Diff 900.00, Temp 206.00
07/02/2021 | 20:46 | 20:50 | 0.07 | 8487 | 8487 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 20:50 | 20:55 | 0.08 | 8487 | 8502 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/8487.00 t/8502.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 180.00, Diff 900.00, Temp 206.00
07/02/2021 | 20:55 | 21:35 | 0.67 | 8502 | 8522 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8502.00 t/8522.00, TF 135M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0.00, ROP 30.00, Diff 900.00, Temp 206.00
07/02/2021 | 21:35 | 21:49 | 0.23 | 8522 | 8581 | 59 | INT | 2: BHA 2 | 2K | Rotary Drill f/8522.00 t/8581.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 252.86, Diff 900.00, Temp 206.00
07/02/2021 | 21:49 | 21:53 | 0.07 | 8581 | 8581 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 21:53 | 21:55 | 0.03 | 8581 | 8586 | 5 | INT | 2: BHA 2 | 2K | Rotary Drill f/8581.00 t/8586.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 150.00, Diff 900.00, Temp 206.00
07/02/2021 | 21:55 | 22:00 | 0.08 | 8586 | 8586 | 0 | INT | 2: BHA 2 | 5A | Recycle For SVY
07/02/2021 | 22:00 | 22:10 | 0.17 | 8586 | 8675 | 89 | INT | 2: BHA 2 | 2K | Rotary Drill f/8586.00 t/8675.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 534.00, Diff 900.00, Temp 206.00
07/02/2021 | 22:10 | 22:15 | 0.08 | 8675 | 8675 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 22:15 | 22:27 | 0.2 | 8675 | 8769 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8675.00 t/8769.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 470.00, Diff 900.00, Temp 206.00
07/02/2021 | 22:27 | 22:32 | 0.08 | 8769 | 8769 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 22:32 | 22:45 | 0.22 | 8769 | 8863 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8769.00 t/8863.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 433.85, Diff 900.00, Temp 206.00
07/02/2021 | 22:45 | 22:50 | 0.08 | 8863 | 8863 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 22:50 | 22:55 | 0.08 | 8863 | 8892 | 29 | INT | 2: BHA 2 | 2K | Rotary Drill f/8863.00 t/8892.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 348.00, Diff 900.00, Temp 206.00
07/02/2021 | 22:55 | 23:40 | 0.75 | 8892 | 8899 | 7 | INT | 2: BHA 2 | 2J | Slide Drill f/8892.00 t/8899.00, TF 215M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0, ROP 9.33, Diff 900.00, Temp 206.00
07/02/2021 | 23:40 | 23:50 | 0.17 | 8899 | 8957 | 58 | INT | 2: BHA 2 | 2K | Rotary Drill f/8899.00 t/8957.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 348.00, Diff 900.00, Temp 206.00
07/02/2021 | 23:50 | 23:55 | 0.08 | 8957 | 8957 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/02/2021 | 23:55 | 24:00 | 0.08 | 8957 | 8966 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/8957.00 t/8966.00, w/WOB 40.00,Flow 880.00, RPM 80, Press 5600.00, Tq 22000, ROP 108.00, Diff 900.00, Temp 206.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_3_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/03/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 45050
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 8966 |  | 2732 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 11
End Depth (Usft): |  | 9810 |  | 9810 |  | OD (in): |  |  |  | 300: | 18 | YP: | 7
Total Drilled (Usft): |  | 844 |  | 7078 |  | Weight (ft/lbs): |  |  |  | 200: | 14 | Viscosity: | 51
Slide Drilled (Usft): |  | 269 |  | 451 | [5 empty] | 100: | 9 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 575 |  | 6627 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.20
Drlg/Circ Hrs: |  | 22.03 / 0.98 |  | 43.72 / 7.50 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 20.2 |  | 23.9 |  | SN: |  | 56211 |  | 10s Gel: | 9 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 1.83 |  | 19.82 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 100.00 | Fluid Loss / Mud Type: | 6 / WBM
ROP Rot/Slide (Usft/hr): |  | 313.64 / 13.32 |  | 334.42 / 18.87 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 61.25 |  | Grade In: |  | New
% Slide: |  | 31.87 |  | 6.37 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 68.13 |  | 93.63 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.014 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.91 |  | 39.41
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.74
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.57
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80.33
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.36
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 111.26
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.38
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.38
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.42
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.61
Agitator |  |  |  | 6.625 | 3.75 |  |  |  |  | 24.71 |  | 2565.32
2565.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800032 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.78 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
8980 | 1.11 | 120.58 | 8899.87 | 792.07 | -573.74 | 1.71 |  | 142.26 | -977.16 | -0.73 |  | 66.14 | 93
9074 | 1.43 | 119.92 | 8993.85 | 791.03 | -571.94 | 0.34 |  | -2.95 | -975.22 | 0.34 |  | 0 | 94
9168 | 0.13 | 151.14 | 9087.84 | 790.35 | -570.87 | 1.4 |  | 177.07 | -974.03 | -1.38 |  | 0 | 94
9262 | 0.28 | 327.35 | 9181.84 | 790.45 | -570.94 | 0.44 |  | 177.41 | -974.15 | 0.16 |  | 0 | 94
9356 | 0.86 | 312.83 | 9275.83 | 791.12 | -571.58 | 0.63 |  | -21.32 | -975.08 | 0.62 |  | 0 | 94
9449 | 1.2 | 308.16 | 9368.82 | 792.2 | -572.86 | 0.38 |  | -16.21 | -976.71 | 0.37 |  | 0 | 93
9543 | 1.69 | 303.68 | 9462.79 | 793.57 | -574.79 | 0.53 |  | -15.23 | -978.99 | 0.52 |  | 0 | 94
9637 | 2.21 | 195.41 | 9556.75 | 792.59 | -576.42 | 3.38 |  | -138.61 | -979.24 | 0.55 |  | -115.18 | 94
9731 | 7.98 | 158.1 | 9650.36 | 784.78 | -574.47 | 6.77 |  | -49.39 | -971.9 | 6.14 |  | -39.69 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 38.31 | 32.65 | 80 | 222 | 857.18 | 4982.35 | 4258.82 | 0 | 244.41 | 215.29 | 212.65 | 22000 | 0
Run | 161.91 | 35.61 | 79.41 | 206 | 763.51 | 4420.78 | 3717.03 | 0 | 207.72 | 184.5 | 167.11 | 20102.94 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 07/03/2021 |  | 1 |  | 6000
Directional & MWD / Gamma Services |  |  |  |  | 07/03/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/03/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 07/03/2021 |  | 17 |  | 1150
Directional & MWD Standby |  |  |  |  | 07/03/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/03/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/03/2021 | 00:00 | 00:05 | 0.08 | 8966 | 8966 | 0 | INT | 2: BHA 2 | 5A | Swab Out On MP
07/03/2021 | 00:05 | 00:57 | 0.87 | 8966 | 8986 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8966.00 t/8986.00, TF 215M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0, ROP 23.08, Diff 900.00, Temp 206.00
07/03/2021 | 00:57 | 01:10 | 0.22 | 8986 | 9050 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/8986.00 t/9050.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 295.38, Diff 900.00, Temp 224.00
07/03/2021 | 01:10 | 01:15 | 0.08 | 9050 | 9050 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 01:15 | 01:21 | 0.1 | 9050 | 9086 | 36 | INT | 2: BHA 2 | 2K | Rotary Drill f/9050.00 t/9086.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 360.00, Diff 900.00, Temp 224.00
07/03/2021 | 01:21 | 01:25 | 0.07 | 9086 | 9086 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 01:25 | 01:34 | 0.15 | 9086 | 9144 | 58 | INT | 2: BHA 2 | 2K | Rotary Drill f/9086.00 t/9144.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 386.67, Diff 900.00, Temp 224.00
07/03/2021 | 01:34 | 01:39 | 0.08 | 9144 | 9144 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 01:39 | 01:45 | 0.1 | 9144 | 9153 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/9144.00 t/9153.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 90.00, Diff 900.00, Temp 224.00
07/03/2021 | 01:45 | 02:24 | 0.65 | 9153 | 9163 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/9153.00 t/9163.00, TF 285M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0, ROP 15.38, Diff 900.00, Temp 224.00
07/03/2021 | 02:24 | 02:42 | 0.3 | 9163 | 9238 | 75 | INT | 2: BHA 2 | 2K | Rotary Drill f/9163.00 t/9238.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 250.00, Diff 900.00, Temp 224.00
07/03/2021 | 02:42 | 02:47 | 0.08 | 9238 | 9238 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 02:47 | 03:03 | 0.27 | 9238 | 9332 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9238.00 t/9332.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 352.50, Diff 900.00, Temp 224.00
07/03/2021 | 03:03 | 03:08 | 0.08 | 9332 | 9332 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 03:08 | 03:24 | 0.27 | 9332 | 9426 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9332.00 t/9426.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 352.50, Diff 900.00, Temp 224.00
07/03/2021 | 03:24 | 03:29 | 0.08 | 9426 | 9426 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 03:29 | 03:42 | 0.22 | 9426 | 9519 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9426.00 t/9519.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 429.23, Diff 900.00, Temp 224.00
07/03/2021 | 03:42 | 03:55 | 0.22 | 9519 | 9571 | 52 | INT | 2: BHA 2 | 2K | Rotary Drill f/9519.00 t/9571.00, w/WOB 40.00,Flow 880.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 240.00, Diff 900.00, Temp 224.00
07/03/2021 | 03:55 | 05:00 | 1.08 | 9571 | 9593 | 22 | INT | 2: BHA 2 | 2J | Slide Drill f/9571.00 t/9593.00, TF 145M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0, ROP 20.31, Diff 900.00, Temp 224.00
07/03/2021 | 05:00 | 06:10 | 1.17 | 9593 | 9613 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9571.00 t/9613.00, TF 145.00M, w/WOB 40.00,Flow 880.00, Press 5600.00, Tq 0.00, ROP 36.00, Diff 900.00, Temp 224.00
07/03/2021 | 06:10 | 06:20 | 0.17 | 9613 | 9613 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 06:20 | 14:00 | 7.67 | 9613 | 9707 | 94 | INT | 2: BHA 2 | 2J | Slide Drill f/9613.00 t/9707.00, TF 140.00M, w/WOB 15.00,Flow 686.00, Press 3500.00, Tq 0.00, ROP 12.26, Diff 300.00, Temp 224.00
07/03/2021 | 14:00 | 14:10 | 0.17 | 9707 | 9707 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 14:10 | 17:46 | 3.6 | 9707 | 9766 | 59 | INT | 2: BHA 2 | 2J | Slide Drill f/9707.00 t/9766.00, TF 140.00M, w/WOB 15.00,Flow 686.00, Press 3500.00, Tq 0.00, ROP 16.39, Diff 300.00, Temp 224.00
07/03/2021 | 17:46 | 18:00 | 0.23 | 9766 | 9766 | 0 | INT | 2: BHA 2 | 8D | Working On Mud Pumps
07/03/2021 | 18:00 | 19:50 | 1.83 | 9766 | 9782 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/9766.00 t/9782.00, TF -35.00G, w/WOB 15.00,Flow 880.00, Press 3500.00, Tq 0.00, ROP 8.73, Diff 300.00, Temp 233.50
07/03/2021 | 19:50 | 20:35 | 0.75 | 9782 | 9782 | 0 | INT | 2: BHA 2 | 8L | C/O Rotating Head
07/03/2021 | 20:35 | 22:46 | 2.18 | 9782 | 9801 | 19 | INT | 2: BHA 2 | 2J | Slide Drill f/9782.00 t/9801.00, TF -35.00G, w/WOB 15.00,Flow 880.00, Press 3500.00, Tq 0.00, ROP 8.70, Diff 300.00, Temp 233.50
07/03/2021 | 22:46 | 22:51 | 0.08 | 9801 | 9801 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/03/2021 | 22:51 | 24:00 | 1.15 | 9801 | 9810 | 9 | INT | 2: BHA 2 | 2J | Slide Drill f/9801.00 t/9810.00, TF -35.00G, w/WOB 15.00,Flow 880.00, Press 3500.00, Tq 0.00, ROP 7.83, Diff 300.00, Temp 233.50
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_4_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/04/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 51900
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9810 |  | 2732 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 9906 |  | 9906 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 96 |  | 7174 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): |  | 43 |  | 494 | [5 empty] | 100: | 11 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 53 |  | 6680 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.20
Drlg/Circ Hrs: |  | 6.68 / 2.57 |  | 50.40 / 10.07 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 5.73 |  | 29.63 |  | SN: |  | 56211 |  | 10s Gel: | 14 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 0.95 |  | 20.77 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 55.79 / 7.50 |  | 321.67 / 16.67 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 18 |  | 79.25 |  | Grade In: |  | New
% Slide: |  | 44.79 |  | 6.89 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 55.21 |  | 93.11 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 HPO -.014 Slick |  |  |  | 8 | 2 |  |  |  |  | 37.91 |  | 39.41
NM Pony Drill Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 8.33 |  | 47.74
UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.83 |  | 51.57
NM Drill Collar |  |  |  | 8.062 | 3.188 |  |  |  |  | 28.76 |  | 80.33
NM Drill Collar |  |  |  | 7.75 | 3.188 |  |  |  |  | 28.03 |  | 108.36
Crossover |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.9 |  | 111.26
6 Joints of 6 1/2 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 184.12 |  | 295.38
Crossover |  |  |  | 6.562 | 2.562 |  |  |  |  | 3 |  | 298.38
9- Joints of 5" HWDP |  |  |  | 5 | 2.5 |  |  |  |  | 271.04 |  | 569.42
21 Stands 5 in DP |  |  |  | 5 | 3 |  |  |  |  | 1971.19 |  | 2540.61
Agitator |  |  |  | 6.625 | 3.75 |  |  |  |  | 24.71 |  | 2565.32
2565.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800032 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.78 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9836 | 15.18 | 154.92 | 9753.16 | 765.55 | -565.91 | 6.88 |  | -6.63 | -951.5 | 6.86 |  | -3.03 | 105
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 14.36 | 15 | 0 | 130 | 783 | 3500 | 3200 | 0 | 270 | 230 | 200 | 0 | 0
Run | 142.34 | 34.73 | 79.41 | 206 | 764.34 | 4381.6 | 3695.03 | 0 | 210.37 | 186.44 | 168.51 | 20102.94 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 07/04/2021 |  | 1 |  | 6000
Directional & MWD / Gamma Services |  |  |  |  | 07/04/2021 |  | 2 |  | 6450 |  | 1 | 6450
Perdiem Per Hand |  |  |  |  | 07/04/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 07/04/2021 |  | 17 |  | 1150
Directional & MWD Standby |  |  |  |  | 07/04/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/04/2021 |  | 15 |  | 10500
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/04/2021 | 00:00 | 01:54 | 1.9 | 9810 | 9826 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/9810.00 t/9826.00, TF -35G, w/WOB 15.00,Flow 686, Press 3500.00, Tq 0.00, ROP 8.42, Diff 300.00, Temp 233.50
07/04/2021 | 01:54 | 02:01 | 0.12 | 9826 | 9826 | 0 | INT | 2: BHA 2 | 8D | Working On Mp
07/04/2021 | 02:01 | 02:45 | 0.73 | 9826 | 9830 | 4 | INT | 2: BHA 2 | 2J | Slide Drill f/9826.00 t/9830.00, TF -35G, w/WOB 15.00,Flow 880, Press 3500.00, Tq 0.00, ROP 5.45, Diff 300.00, Temp 233.50
07/04/2021 | 02:45 | 02:53 | 0.13 | 9830 | 9830 | 0 | INT | 2: BHA 2 | 8D | Working On MP
07/04/2021 | 02:53 | 05:00 | 2.12 | 9830 | 9844 | 14 | INT | 2: BHA 2 | 2J | Slide Drill f/9830.00 t/9844.00, TF -35G, w/WOB 15.00,Flow 686, Press 3500.00, Tq 0.00, ROP 6.61, Diff 300.00, Temp 233.50
07/04/2021 | 05:00 | 05:15 | 0.25 | 9844 | 9844 | 0 | INT | 2: BHA 2 | 8D | Working On MP
07/04/2021 | 05:15 | 05:18 | 0.05 | 9844 | 9845 | 1 | INT | 2: BHA 2 | 2J | Slide Drill f/9844.00 t/9845.00, TF -35G, w/WOB 15.00,Flow 880, Press 3500.00, Tq 0.00, ROP 20.00, Diff 300.00, Temp 233.50
07/04/2021 | 05:18 | 06:00 | 0.7 | 9845 | 9845 | 0 | INT | 2: BHA 2 | 5A | Circulate with one pump while making repairs to other pump
07/04/2021 | 06:00 | 06:56 | 0.93 | 9845 | 9853 | 8 | INT | 2: BHA 2 | 2J | Slide Drill f/9845.00 t/9853.00, TF -20G, w/WOB 15.00,Flow 686, Press 3500.00, Tq 0.00, ROP 8.57, Diff 300.00, Temp 233.50
07/04/2021 | 06:56 | 07:53 | 0.95 | 9853 | 9906 | 53 | INT | 2: BHA 2 | 2K | Rotary Drill f/9853.00 t/9906.00, w/WOB 30,Flow 880.00, RPM 30, Press 3900, Tq 21000, ROP 55.79, Diff 700.00, Temp 233.50
07/04/2021 | 07:53 | 08:00 | 0.12 | 9906 | 9906 | 0 | INT | 2: BHA 2 | 10C | Svy at TD of section
07/04/2021 | 08:00 | 09:45 | 1.75 | 9906 | 9906 | 0 | INT | 2: BHA 2 | 5A | Circulate out TD sweeps in preparation of TOOH to run intermediate casing
07/04/2021 | 09:45 | 16:30 | 6.75 | 9906 | 9906 | 0 | INT | 2: BHA 2 | 6B | POOH T/ BHA
07/04/2021 | 16:30 | 18:00 | 1.5 | 9906 | 9906 | 0 | INT | 2: BHA 2 | 6P | Working BHA (BHA Racked Back In Derrick)
07/04/2021 | 18:00 | 24:00 | 6 | 9906 | 9906 | 0 | INT |  | 24B | Standby For CSG Opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_5_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/05/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4200 |  |  | Well Cost($): |  | 56100
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9906 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 9906 |  | 9906 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): | [9 empty] | 100: | 11 | Chlorides: | 270666
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.20
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 14 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 15 | 0 | 130 | 783 | 3500 | 3200 | 0 | 270 | 230 | 200 | 0 | 0
Run | 0 | 34.73 | 79.41 | 206 | 764.34 | 4381.6 | 3695.03 | 0 | 210.37 | 186.44 | 168.51 | 20102.94 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 07/05/2021 |  | 1 |  | 6000
Directional & MWD Standby |  |  |  |  | 07/05/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 07/05/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 07/05/2021 |  | 17 |  | 1150
Directional & MWD Standby |  |  |  |  | 07/05/2021 |  | 4 |  | 3800
8 Motor Reline |  |  |  |  | 07/05/2021 |  | 15 |  | 10500
Directional & MWD Standby |  |  |  |  | 07/05/2021 |  | 4 |  | 3800 |  | 1 | 3800
Total | [11 empty] | 4200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/05/2021 | 00:00 | 24:00 | 24 | 9906 | 9906 | 0 | INT |  | 24B | Standby For CSG Ops /Rig Skid
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_6_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/06/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18450 |  |  | Well Cost($): |  | 74550
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9906 |  | 9906 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 9906 |  | 9906 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): | [9 empty] | 100: | 11 | Chlorides: | 270666
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.20
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: | [5 empty] | SN: |  | 13618580 |  | 10s Gel: | 14 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 1 |  | 1 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 33.91
BTI |  |  |  | 4.812 | 2.062 |  |  |  |  | 1.65 |  | 35.56
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.6
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.6
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.51
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.47
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.39
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 131.06
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.83
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.47
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.85
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.75
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5917.68
Agitator / Ball Drop |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.44 |  | 5939.12
5939.12
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 15 | 0 | 532 | 783 | 3500 | 3200 | 0 | 270 | 230 | 200 | 0 | 0
Run | 0 | 34.73 | 79.41 | 599 | 764.34 | 4381.6 | 3695.03 | 0 | 210.37 | 186.44 | 168.51 | 20102.94 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Stabilizer Rental 13 Used |  |  |  |  | 08/06/2021 |  | 17 |  | 1150
Job Start-Up Incidentals |  |  |  |  | 08/06/2021 |  | 1 |  | 6000
Directional & MWD Standby |  |  |  |  | 08/06/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 08/06/2021 |  | 6 |  | 100 |  | 4 | 400
Directional & MWD / Gamma Services |  |  |  |  | 08/06/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/06/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/06/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/06/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/06/2021 |  | 12 |  | 9000 |  | 1 | 9000
Total | [11 empty] | 18450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/06/2021 | 00:00 | 22:00 | 22 | 9906 | 9906 | 0 | CRV |  | 24B | Standby for rig skid
08/06/2021 | 22:00 | 23:00 | 1 | 9906 | 9906 | 0 | CRV | 3: BHA 3 | 6O | P/U BHA
08/06/2021 | 23:00 | 23:15 | 0.25 | 9906 | 9906 | 0 | CRV | 3: BHA 3 | 8K | C/O Dies On IR
08/06/2021 | 23:15 | 24:00 | 0.75 | 9906 | 9906 | 0 | CRV | 3: BHA 3 | 6L | P/U BHA
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_7_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/07/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 84000
|  |  |  | 24hr Summary: |  | Rig Skid / BOP Test / P/U BHA For Curve & Lateral Section / TIH
|  |  |  | 24hr Lookahead: |  | Continue TIH Drill Out / FIT / Drill Curve & In TO The Lateral Section
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9906 |  | 9906 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 11039 |  | 11039 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 1133 |  | 1133 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): |  | 764 |  | 764 | [5 empty] | 100: | 11 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 369 |  | 369 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.20
Drlg/Circ Hrs: |  | 10.98 / 3.45 |  | 10.98 / 3.45 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 8.2 |  | 8.2 |  | SN: |  | 13618580 |  | 10s Gel: | 14 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 2.78 |  | 2.78 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 132.57 / 93.17 |  | 132.57 / 93.17 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 25 |  | Grade In: |  | New
% Slide: |  | 67.43 |  | 67.43 |  | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
% Rotary: |  | 32.57 |  | 32.57 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 33.91
BTI |  |  |  | 4.812 | 2.062 |  |  |  |  | 1.65 |  | 35.56
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.6
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.6
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.51
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.47
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.39
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 131.06
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.83
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.47
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.85
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.75
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5917.68
Agitator / Ball Drop |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.44 |  | 5939.12
5939.12
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9931 | 15.45 | 149.38 | 9844.79 | 743.39 | -554.19 | 1.57 |  | -82.23 | -926.85 | 0.28 |  | -5.83 | 95
10025 | 20.33 | 132.4 | 9934.28 | 721.58 | -535.73 | 7.55 |  | -55.22 | -898.29 | 5.19 |  | -18.06 | 94
10120 | 28.7 | 133.16 | 10020.64 | 694.8 | -506.86 | 8.82 |  | 2.51 | -859.38 | 8.81 |  | 0.8 | 95
10214 | 38.54 | 138.64 | 10098.83 | 657.28 | -470.95 | 10.95 |  | 19.46 | -807.67 | 10.47 |  | 5.83 | 94
10309 | 48.53 | 138.01 | 10167.62 | 608.49 | -427.47 | 10.53 |  | -2.72 | -742.43 | 10.52 |  | -0.66 | 95
10403 | 57.43 | 140.19 | 10224.16 | 551.77 | -378.45 | 9.65 |  | 11.74 | -667.53 | 9.47 |  | 2.32 | 94
10498 | 66.13 | 140.46 | 10269.04 | 487.39 | -325.06 | 9.16 |  | 1.63 | -583.93 | 9.16 |  | 0.28 | 95
10592 | 74.72 | 139.79 | 10300.51 | 419.5 | -268.32 | 9.16 |  | -4.32 | -495.48 | 9.14 |  | -0.71 | 94
10686 | 78.45 | 138.65 | 10322.31 | 350.28 | -208.61 | 4.14 |  | -16.69 | -404.14 | 3.97 |  | -1.21 | 94
10780 | 85.55 | 137.42 | 10335.38 | 281.12 | -146.4 | 7.66 |  | -9.83 | -311.31 | 7.55 |  | -1.31 | 94
10875 | 91.81 | 140.92 | 10337.57 | 209.3 | -84.35 | 7.55 |  | 29.26 | -216.48 | 6.59 |  | 3.68 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 103.16 | 27.41 | 63.33 | 297 | 343.18 | 3533.64 | 2962.95 | 0 | 215 | 185 | 170 | 13625 | 0
Run | 103.16 | 27.41 | 63.33 | 297 | 343.18 | 3533.64 | 2962.95 | 0 | 215 | 185 | 170 | 13625 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 08/07/2021 |  | 1 |  | 6000
Directional & MWD Standby |  |  |  |  | 08/07/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 08/07/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 08/07/2021 |  | 17 |  | 1150
Directional & MWD / Gamma Services |  |  |  |  | 08/07/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/07/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/07/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/07/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/07/2021 |  | 12 |  | 9000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/07/2021 | 00:00 | 01:00 | 1 | 9906 | 9906 | 0 | CRV | 3: BHA 3 | 6L | Work BHA
08/07/2021 | 01:00 | 08:30 | 7.5 | 9906 | 9906 | 0 | CRV | 3: BHA 3 | 6A | TIH
08/07/2021 | 08:30 | 09:20 | 0.83 | 9906 | 9906 | 0 | CRV | 3: BHA 3 | 5A | Drill out float and shoe track
08/07/2021 | 09:20 | 09:23 | 0.05 | 9906 | 9916 | 10 | CRV | 3: BHA 3 | 2K | Rotary Drill f/9906.00 t/9916.00, w/WOB 15,Flow 200, RPM 30, Press 1600, Tq 6500, ROP 200.00, Diff 150.00
08/07/2021 | 09:23 | 10:05 | 0.7 | 9916 | 9916 | 0 | CRV | 3: BHA 3 | 5A | Circulate bottoms up
08/07/2021 | 10:05 | 10:54 | 0.82 | 9916 | 9916 | 0 | CRV | 3: BHA 3 | 15D | Perform FIT
08/07/2021 | 10:54 | 11:51 | 0.95 | 9916 | 10000 | 84 | CRV | 3: BHA 3 | 2J | Slide Drill f/9916.00 t/10000.00, TF -20G, w/WOB 28,Flow 350, Press 34560, Tq 0, ROP 88.42, Diff 31525.00, Temp 222.00
08/07/2021 | 11:51 | 12:01 | 0.17 | 10000 | 10000 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 12:01 | 13:13 | 1.2 | 10000 | 10094 | 94 | CRV | 3: BHA 3 | 2J | Slide Drill f/10000.00 t/10094.00, TF 0G, w/WOB 28.00,Flow 350.00, Press 34560.00, Tq 0.00, ROP 78.33, Diff 31525.00, Temp 222.00
08/07/2021 | 13:13 | 13:23 | 0.17 | 10094 | 10094 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 13:23 | 14:26 | 1.05 | 10094 | 10189 | 95 | CRV | 3: BHA 3 | 2J | Slide Drill f/10094.00 t/10189.00, TF 30G, w/WOB 28.00,Flow 350.00, Press 34560.00, Tq 0.00, ROP 90.48, Diff 31525.00, Temp 222.00
08/07/2021 | 14:26 | 14:36 | 0.17 | 10189 | 10189 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 14:36 | 15:31 | 0.92 | 10189 | 10283 | 94 | CRV | 3: BHA 3 | 2J | Slide Drill f/10189.00 t/10283.00, TF 30G, w/WOB 28.00,Flow 350.00, Press 34560.00, Tq 0.00, ROP 102.55, Diff 31525.00, Temp 222.00
08/07/2021 | 15:31 | 15:40 | 0.15 | 10283 | 10283 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 15:40 | 16:36 | 0.93 | 10283 | 10378 | 95 | CRV | 3: BHA 3 | 2J | Slide Drill f/10283.00 t/10378.00, TF 10G, w/WOB 28.00,Flow 350.00, Press 34560.00, Tq 0.00, ROP 101.79, Diff 31525.00, Temp 222.00
08/07/2021 | 16:36 | 16:46 | 0.17 | 10378 | 10378 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 16:46 | 16:54 | 0.13 | 10378 | 10388 | 10 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10378.00 t/10388.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 75.00, Diff 525.00, Temp 222.00
08/07/2021 | 16:54 | 17:37 | 0.72 | 10388 | 10472 | 84 | CRV | 3: BHA 3 | 2J | Slide Drill f/10388.00 t/10472.00, TF 10G, w/WOB 28.00,Flow 350.00, Press 3560, Tq 0.00, ROP 117.21, Diff 525.00, Temp 222.00
08/07/2021 | 17:37 | 17:47 | 0.17 | 10472 | 10472 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 17:47 | 17:58 | 0.18 | 10472 | 10502 | 30 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10472.00 t/10502.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 163.64, Diff 525.00, Temp 222.00
08/07/2021 | 17:58 | 18:44 | 0.77 | 10502 | 10567 | 65 | CRV | 3: BHA 3 | 2J | Slide Drill f/10502.00 t/10567.00, TF 20G, w/WOB 28.00,Flow 350.00, Press 3560, Tq 0.00, ROP 84.78, Diff 525.00, Temp 222.00
08/07/2021 | 18:44 | 18:55 | 0.18 | 10567 | 10567 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 18:55 | 19:35 | 0.67 | 10567 | 10630 | 63 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10567.00 t/10630.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 94.50, Diff 525.00, Temp 222.00
08/07/2021 | 19:35 | 19:54 | 0.32 | 10630 | 10661 | 31 | CRV | 3: BHA 3 | 2J | Slide Drill f/10630.00 t/10661.00, TF 20G, w/WOB 28.00,Flow 350.00, Press 3560, Tq 0.00, ROP 97.89, Diff 525.00, Temp 222.00
08/07/2021 | 19:54 | 20:04 | 0.17 | 10661 | 10661 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 20:04 | 20:30 | 0.43 | 10661 | 10717 | 56 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10661.00 t/10717.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 129.23, Diff 525.00, Temp 222.00
08/07/2021 | 20:30 | 20:52 | 0.37 | 10717 | 10755 | 38 | CRV | 3: BHA 3 | 2J | Slide Drill f/10717.00 t/10755.00, TF 20G, w/WOB 28.00,Flow 350.00, Press 3560, Tq 0.00, ROP 103.64, Diff 525.00, Temp 222.00
08/07/2021 | 20:52 | 21:02 | 0.17 | 10755 | 10755 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 21:02 | 21:15 | 0.22 | 10755 | 10776 | 21 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10755.00 t/10776.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 96.92, Diff 525.00, Temp 222.00
08/07/2021 | 21:15 | 21:52 | 0.62 | 10776 | 10835 | 59 | CRV | 3: BHA 3 | 2J | Slide Drill f/10776.00 t/10835.00, TF 20-90G, w/WOB 28.00,Flow 350.00, Press 3560, Tq 0.00, ROP 95.68, Diff 525.00, Temp 222.00
08/07/2021 | 21:52 | 22:05 | 0.22 | 10835 | 10849 | 14 | CRV | 3: BHA 3 | 2K | Rotary Drill f/10835.00 t/10849.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 64.62, Diff 525.00, Temp 222.00
08/07/2021 | 22:05 | 22:08 | 0.05 | 10849 | 10849 | 0 | CRV | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 22:08 | 22:28 | 0.33 | 10849 | 10900 | 51 | LAT | 3: BHA 3 | 2K | Rotary Drill f/10849.00 t/10900.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 3560, Tq 0.00, ROP 153.00, Diff 525.00, Temp 222.00
08/07/2021 | 22:28 | 22:38 | 0.17 | 10900 | 10900 | 0 | LAT | 3: BHA 3 | 5A | Check Shot
08/07/2021 | 22:38 | 23:00 | 0.37 | 10900 | 10925 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/10900.00 t/10925.00, TF 140G, w/WOB 28.00,Flow 350.00, Press 3560, Tq 0.00, ROP 68.18, Diff 525.00, Temp 222.00
08/07/2021 | 23:00 | 23:08 | 0.13 | 10925 | 10944 | 19 | LAT | 3: BHA 3 | 2K | Rotary Drill f/10925.00 t/10944.00, w/WOB 28.00,Flow 350.00, RPM 80, Press 3560, Tq 16000, ROP 142.50, Diff 525.00, Temp 222.00
08/07/2021 | 23:08 | 23:12 | 0.07 | 10944 | 10944 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 23:12 | 23:25 | 0.22 | 10944 | 10994 | 50 | LAT | 3: BHA 3 | 2K | Rotary Drill f/10944.00 t/10994.00, w/WOB 28.00,Flow 350.00, RPM 80, Press 4250, Tq 16000, ROP 230.77, Diff 1215.00, Temp 222.00
08/07/2021 | 23:25 | 23:30 | 0.08 | 10994 | 10994 | 0 | LAT | 3: BHA 3 | 5A | Check Shot
08/07/2021 | 23:30 | 23:42 | 0.2 | 10994 | 11039 | 45 | LAT | 3: BHA 3 | 2K | Rotary Drill f/10994.00 t/11039.00, w/WOB 28.00,Flow 350.00, RPM 0.00, Press 4250, Tq 16000, ROP 225.00, Diff 1215.00, Temp 222.00
08/07/2021 | 23:42 | 23:45 | 0.05 | 11039 | 11039 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/07/2021 | 23:45 | 24:00 | 0.25 | 11039 | 11039 | 0 | LAT | 3: BHA 3 | 8P | RIg Service
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_8_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/08/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 93450
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11039 |  | 9906 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 14242 |  | 14242 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 3203 |  | 4336 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): |  | 454 |  | 1218 | [5 empty] | 100: | 11 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 2749 |  | 3118 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.20
Drlg/Circ Hrs: |  | 15.80 / 6.52 |  | 26.78 / 9.97 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 6.22 |  | 14.42 |  | SN: |  | 13618580 |  | 10s Gel: | 14 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 9.58 |  | 12.37 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 286.85 / 73.03 |  | 252.13 / 84.49 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 49 |  | Grade In: |  | New
% Slide: |  | 14.17 |  | 28.09 |  | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
% Rotary: |  | 85.83 |  | 71.91 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 33.91
BTI |  |  |  | 4.812 | 2.062 |  |  |  |  | 1.65 |  | 35.56
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.6
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.6
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.51
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.47
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.39
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 131.06
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.83
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.47
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.85
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.75
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5917.68
Agitator / Ball Drop |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.44 |  | 5939.12
5939.12
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10970 | 89.38 | 143.08 | 10336.59 | 134.45 | -25.87 | 3.42 |  | 138.35 | -121.5 | -2.56 |  | 2.27 | 95
11063 | 87.55 | 143.78 | 10339.08 | 59.79 | 29.52 | 2.11 |  | 159.08 | -28.59 | -1.97 |  | 0.75 | 93
11158 | 87.71 | 145.13 | 10343.01 | -17.44 | 84.7 | 1.43 |  | 83.26 | 66.22 | 0.17 |  | 1.42 | 95
11252 | 85.83 | 144.17 | 10348.3 | -93.98 | 138.99 | 2.24 |  | -153.01 | 159.94 | -2 |  | -1.02 | 94
11346 | 84.2 | 143.3 | 10356.47 | -169.49 | 194.38 | 1.96 |  | -152.04 | 253.51 | -1.73 |  | -0.93 | 94
11441 | 84.99 | 142.28 | 10365.42 | -244.81 | 251.58 | 1.35 |  | -52.17 | 348.07 | 0.83 |  | -1.07 | 95
11535 | 87.76 | 142.01 | 10371.36 | -318.87 | 309.14 | 2.96 |  | -5.57 | 441.87 | 2.95 |  | -0.29 | 94
11630 | 86.57 | 138.61 | 10376.06 | -391.87 | 369.72 | 3.79 |  | -109.39 | 536.71 | -1.25 |  | -3.58 | 95
11726 | 89.9 | 142.78 | 10379.02 | -466.1 | 430.48 | 5.56 |  | 51.46 | 632.62 | 3.47 |  | 4.34 | 96
11820 | 92.43 | 143.14 | 10377.11 | -541.11 | 487.09 | 2.72 |  | 8.09 | 726.57 | 2.69 |  | 0.38 | 94
11912 | 93.12 | 143.6 | 10372.65 | -614.85 | 541.92 | 0.9 |  | 33.65 | 818.42 | 0.75 |  | 0.5 | 92
12006 | 89.81 | 144.36 | 10370.25 | -690.84 | 597.17 | 3.61 |  | 167.06 | 912.3 | -3.52 |  | 0.81 | 94
12100 | 85.59 | 143.53 | 10374.02 | -766.76 | 652.43 | 4.58 |  | -168.9 | 1006.12 | -4.49 |  | -0.88 | 94
12195 | 84.34 | 143.54 | 10382.36 | -842.86 | 708.68 | 1.32 |  | 179.54 | 1100.71 | -1.32 |  | 0.01 | 95
12289 | 83.31 | 142.79 | 10392.47 | -917.66 | 764.7 | 1.35 |  | -144.14 | 1194.13 | -1.1 |  | -0.8 | 94
12383 | 86.03 | 143.54 | 10401.2 | -992.56 | 820.81 | 3 |  | 15.39 | 1287.68 | 2.89 |  | 0.8 | 94
12477 | 87.8 | 143.32 | 10406.26 | -1067.94 | 876.73 | 1.9 |  | -7.08 | 1381.49 | 1.88 |  | -0.23 | 94
12572 | 88.69 | 142.73 | 10409.17 | -1143.8 | 933.84 | 1.12 |  | -33.54 | 1476.42 | 0.94 |  | -0.62 | 95
12666 | 88.31 | 142.72 | 10411.63 | -1218.58 | 990.75 | 0.4 |  | -178.49 | 1570.37 | -0.4 |  | -0.01 | 94
12759 | 86.86 | 143.9 | 10415.55 | -1293.08 | 1046.27 | 2.01 |  | 140.91 | 1663.25 | -1.56 |  | 1.27 | 93
12854 | 86.82 | 145.12 | 10420.79 | -1370.31 | 1101.33 | 1.28 |  | 91.91 | 1757.98 | -0.04 |  | 1.28 | 95
12948 | 85.83 | 144.19 | 10426.81 | -1446.83 | 1155.6 | 1.44 |  | -136.88 | 1851.66 | -1.05 |  | -0.99 | 94
13043 | 82.82 | 140.86 | 10436.21 | -1521.84 | 1213.09 | 4.71 |  | -132.4 | 1946.16 | -3.17 |  | -3.51 | 95
13137 | 84.51 | 140.19 | 10446.58 | -1593.95 | 1272.49 | 1.93 |  | -21.54 | 2039.56 | 1.8 |  | -0.71 | 94
13231 | 88.43 | 137.8 | 10452.37 | -1664.73 | 1334.03 | 4.88 |  | -31.4 | 2133.26 | 4.17 |  | -2.54 | 94
13326 | 88.99 | 136.87 | 10454.51 | -1734.57 | 1398.4 | 1.14 |  | -58.95 | 2227.96 | 0.59 |  | -0.98 | 95
13421 | 90.68 | 140.11 | 10454.78 | -1805.7 | 1461.35 | 3.85 |  | 62.46 | 2322.8 | 1.78 |  | 3.41 | 95
13515 | 89.73 | 142.15 | 10454.44 | -1878.88 | 1520.33 | 2.39 |  | 114.96 | 2416.79 | -1.01 |  | 2.17 | 94
13609 | 87.84 | 142.45 | 10456.44 | -1953.23 | 1577.8 | 2.04 |  | 170.99 | 2510.76 | -2.01 |  | 0.32 | 94
13702 | 86.85 | 140.93 | 10460.74 | -2026.12 | 1635.39 | 1.95 |  | -123.14 | 2603.65 | -1.06 |  | -1.63 | 93
13797 | 87.62 | 141.31 | 10465.33 | -2099.99 | 1694.95 | 0.9 |  | 26.25 | 2698.54 | 0.81 |  | 0.4 | 95
13891 | 87.03 | 141.3 | 10469.71 | -2173.28 | 1753.65 | 0.63 |  | -179.03 | 2792.43 | -0.63 |  | -0.01 | 94
13985 | 86.82 | 140.18 | 10474.76 | -2245.95 | 1813.05 | 1.21 |  | -100.66 | 2886.28 | -0.22 |  | -1.19 | 94
14079 | 88.03 | 140.48 | 10478.98 | -2318.23 | 1873 | 1.33 |  | 13.92 | 2980.16 | 1.29 |  | 0.32 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 202.72 | 36.52 | 80 | 341 | 384.42 | 4797.4 | 3821.3 | 0 | 233.9 | 188.96 | 165.71 | 16796.3 | 0
Run | 161.89 | 34.49 | 79.14 | 334 | 375.25 | 4516.57 | 3646.57 | 0 | 229.7 | 188.08 | 166.67 | 16577.59 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem Per Hand |  |  |  |  | 08/08/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 08/08/2021 |  | 17 |  | 1150
Directional & MWD / Gamma Services |  |  |  |  | 08/08/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/08/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/08/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/08/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/08/2021 |  | 12 |  | 9000
Job Start-Up Incidentals |  |  |  |  | 08/08/2021 |  | 1 |  | 6000
Directional & MWD Standby |  |  |  |  | 08/08/2021 |  | 4 |  | 3800
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/08/2021 | 00:00 | 00:25 | 0.42 | 11039 | 11039 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 00:25 | 00:38 | 0.22 | 11039 | 11059 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/11039.00 t/11059.00, TF 180.00G, w/WOB 28.00,Flow 350.00, Press 4250.00, Tq 16000.00, ROP 92.31, Diff 1215.00, Temp 222.00
08/08/2021 | 00:38 | 00:53 | 0.25 | 11059 | 11132 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11059.00 t/11132.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 292.00, Diff 1215.00, Temp 235.00
08/08/2021 | 00:53 | 00:58 | 0.08 | 11132 | 11132 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 00:58 | 01:15 | 0.28 | 11132 | 11227 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11132.00 t/11227.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 335.29, Diff 1215.00, Temp 235.00
08/08/2021 | 01:15 | 01:18 | 0.05 | 11227 | 11227 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 01:18 | 01:26 | 0.13 | 11227 | 11239 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11227.00 t/11239.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 90.00, Diff 1215.00, Temp 235.00
08/08/2021 | 01:26 | 01:41 | 0.25 | 11239 | 11258 | 19 | LAT | 3: BHA 3 | 2J | Slide Drill f/11239.00 t/11258.00, TF -170.00G, w/WOB 28.00,Flow 350.00, Press 4250.00, Tq 16000.00, ROP 76.00, Diff 1215.00, Temp 235.00
08/08/2021 | 01:41 | 01:55 | 0.23 | 11258 | 11321 | 63 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11258.00 t/11321.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 270.00, Diff 1215.00, Temp 235.00
08/08/2021 | 01:55 | 02:00 | 0.08 | 11321 | 11321 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 02:00 | 02:15 | 0.25 | 11321 | 11415 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11321.00 t/11415.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 376.00, Diff 1215.00, Temp 235.00
08/08/2021 | 02:15 | 02:18 | 0.05 | 11415 | 11415 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 02:18 | 02:25 | 0.12 | 11415 | 11430 | 15 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11415.00 t/11430.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 128.57, Diff 1215.00, Temp 235.00
08/08/2021 | 02:25 | 02:43 | 0.3 | 11430 | 11445 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/11430.00 t/11445.00, TF 0.00G, w/WOB 28.00,Flow 350.00, Press 4250.00, Tq 16000.00, ROP 50.00, Diff 1215.00, Temp 235.00
08/08/2021 | 02:43 | 02:55 | 0.2 | 11445 | 11510 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11445.00 t/11510.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 325.00, Diff 1215.00, Temp 235.00
08/08/2021 | 02:55 | 03:00 | 0.08 | 11510 | 11510 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 03:00 | 03:05 | 0.08 | 11510 | 11520 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11510.00 t/11520.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 120.00, Diff 1215.00, Temp 235.00
08/08/2021 | 03:05 | 03:15 | 0.17 | 11520 | 11530 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/11520.00 t/11530.00, TF 0.00G, w/WOB 28.00,Flow 350.00, Press 4250.00, Tq 16000.00, ROP 60.00, Diff 1215.00, Temp 235.00
08/08/2021 | 03:15 | 03:32 | 0.28 | 11530 | 11604 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11530.00 t/11604.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 261.18, Diff 1215.00, Temp 235.00
08/08/2021 | 03:32 | 03:37 | 0.08 | 11604 | 11604 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 03:37 | 03:51 | 0.23 | 11604 | 11699 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11604.00 t/11699.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 407.14, Diff 1215.00, Temp 235.00
08/08/2021 | 03:51 | 03:54 | 0.05 | 11699 | 11699 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 03:54 | 03:57 | 0.05 | 11699 | 11704 | 5 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11699.00 t/11704.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 16000.00, ROP 100.00, Diff 1215.00, Temp 235.00
08/08/2021 | 03:57 | 04:05 | 0.13 | 11704 | 11704 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 04:05 | 04:25 | 0.33 | 11704 | 11729 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/11704.00 t/11729.00, TF 70.00G, w/WOB 28.00,Flow 350.00, Press 4250.00, Tq 16000.00, ROP 75.00, Diff 1215.00, Temp 235.00
08/08/2021 | 04:25 | 04:38 | 0.22 | 11729 | 11795 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11729.00 t/11795.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 17000.00, ROP 304.62, Diff 1215.00, Temp 239.00
08/08/2021 | 04:38 | 04:42 | 0.07 | 11795 | 11795 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 04:42 | 05:00 | 0.3 | 11795 | 11889 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11795.00 t/11889.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 17000.00, ROP 313.33, Diff 1215.00, Temp 239.00
08/08/2021 | 05:00 | 05:05 | 0.08 | 11889 | 11889 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 05:05 | 05:11 | 0.1 | 11889 | 11898 | 9 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11889.00 t/11898.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 17000.00, ROP 90.00, Diff 1215.00, Temp 239.00
08/08/2021 | 05:11 | 05:29 | 0.3 | 11898 | 11928 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/11898.00 t/11928.00, TF 180.00G, w/WOB 28.00,Flow 350.00, Press 4250.00, Tq 17000.00, ROP 100.00, Diff 1215.00, Temp 239.00
08/08/2021 | 05:29 | 05:42 | 0.22 | 11928 | 11981 | 53 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11928.00 t/11981.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 17000.00, ROP 244.62, Diff 1215.00, Temp 239.00
08/08/2021 | 05:42 | 05:52 | 0.17 | 11981 | 11981 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 05:52 | 05:58 | 0.1 | 11981 | 11988 | 7 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11981.00 t/11988.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 17000.00, ROP 70.00, Diff 1215.00, Temp 239.00
08/08/2021 | 05:58 | 06:20 | 0.37 | 11988 | 12018 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/11988.00 t/12018.00, TF 180.00G, w/WOB 38.00,Flow 350.00, Press 4250.00, Tq 0.00, ROP 81.82, Diff 1215.00, Temp 239.00
08/08/2021 | 06:20 | 06:34 | 0.23 | 12018 | 12075 | 57 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12018.00 t/12075.00, w/WOB 40.00,Flow 350.00, RPM 80.00, Press 4250.00, Tq 17000.00, ROP 244.29, Diff 1215.00, Temp 239.00
08/08/2021 | 06:34 | 06:44 | 0.17 | 12075 | 12075 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 06:44 | 07:00 | 0.27 | 12075 | 12097 | 22 | LAT | 3: BHA 3 | 2J | Slide Drill f/12075.00 t/12097.00, TF -140.00G, w/WOB 38.00,Flow 400.00, Press 5000.00, Tq 0.00, ROP 82.50, Diff 1000.00, Temp 240.00
08/08/2021 | 07:00 | 07:20 | 0.33 | 12097 | 12169 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12097.00 t/12169.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5100.00, Tq 17000.00, ROP 216.00, Diff 1100.00, Temp 239.00
08/08/2021 | 07:20 | 07:30 | 0.17 | 12169 | 12169 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 07:30 | 07:43 | 0.22 | 12169 | 12264 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12169.00 t/12264.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5100.00, Tq 17000.00, ROP 438.46, Diff 1100.00, Temp 239.00
08/08/2021 | 07:43 | 07:53 | 0.17 | 12264 | 12264 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 07:53 | 08:08 | 0.25 | 12264 | 12358 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12264.00 t/12358.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5100.00, Tq 17000.00, ROP 376.00, Diff 1100.00, Temp 239.00
08/08/2021 | 08:08 | 08:18 | 0.17 | 12358 | 12358 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 08:18 | 08:23 | 0.08 | 12358 | 12365 | 7 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12358.00 t/12365.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5100.00, Tq 17000.00, ROP 84.00, Diff 1100.00, Temp 239.00
08/08/2021 | 08:23 | 08:34 | 0.18 | 12365 | 12390 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/12365.00 t/12390.00, TF 0.00G, w/WOB 40.00,Flow 400.00, Press 4600.00, Tq 0.00, ROP 136.36, Diff 600.00, Temp 239.00
08/08/2021 | 08:34 | 08:49 | 0.25 | 12390 | 12452 | 62 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12390.00 t/12452.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 248.00, Diff 1000.00, Temp 247.00
08/08/2021 | 08:49 | 08:58 | 0.15 | 12452 | 12452 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 08:58 | 09:11 | 0.22 | 12452 | 12546 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12452.00 t/12546.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 433.85, Diff 1000.00, Temp 247.00
08/08/2021 | 09:11 | 09:21 | 0.17 | 12546 | 12546 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 09:21 | 09:25 | 0.07 | 12546 | 12556 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12546.00 t/12556.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 150.00, Diff 1000.00, Temp 247.00
08/08/2021 | 09:25 | 09:31 | 0.1 | 12556 | 12571 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12556.00 t/12571.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 150.00, Diff 300.00, Temp 251.00
08/08/2021 | 09:31 | 09:48 | 0.28 | 12571 | 12641 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12571.00 t/12641.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 247.06, Diff 1000.00, Temp 251.00
08/08/2021 | 09:48 | 09:58 | 0.17 | 12641 | 12641 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 09:58 | 10:00 | 0.03 | 12641 | 12651 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12641.00 t/12651.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 300.00, Diff 1000.00, Temp 251.00
08/08/2021 | 10:00 | 10:18 | 0.3 | 12651 | 12679 | 28 | LAT | 3: BHA 3 | 2J | Slide Drill f/12651.00 t/12679.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 93.33, Diff 300.00, Temp 251.00
08/08/2021 | 10:18 | 10:30 | 0.2 | 12679 | 12735 | 56 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12679.00 t/12735.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 280.00, Diff 1000.00, Temp 251.00
08/08/2021 | 10:30 | 10:40 | 0.17 | 12735 | 12735 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 10:40 | 10:42 | 0.03 | 12735 | 12745 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12735.00 t/12745.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 300.00, Diff 1000.00, Temp 251.00
08/08/2021 | 10:42 | 10:48 | 0.1 | 12745 | 12757 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/12745.00 t/12757.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 120.00, Diff 300.00, Temp 251.00
08/08/2021 | 10:48 | 11:02 | 0.23 | 12757 | 12828 | 71 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12757.00 t/12828.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 304.29, Diff 1000.00, Temp 251.00
08/08/2021 | 11:02 | 11:09 | 0.12 | 12828 | 12828 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 11:09 | 11:12 | 0.05 | 12828 | 12838 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12828.00 t/12838.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 200.00, Diff 1000.00, Temp 251.00
08/08/2021 | 11:12 | 11:21 | 0.15 | 12838 | 12850 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/12838.00 t/12850.00, TF -130.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 80.00, Diff 300.00, Temp 251.00
08/08/2021 | 11:21 | 11:35 | 0.23 | 12850 | 12923 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12850.00 t/12923.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 312.86, Diff 1000.00, Temp 251.00
08/08/2021 | 11:35 | 11:42 | 0.12 | 12923 | 12923 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 11:42 | 11:44 | 0.03 | 12923 | 12933 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12923.00 t/12933.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 300.00, Diff 1000.00, Temp 251.00
08/08/2021 | 11:44 | 12:06 | 0.37 | 12933 | 12963 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/12933.00 t/12963.00, TF -120.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 81.82, Diff 300.00, Temp 251.00
08/08/2021 | 12:06 | 12:12 | 0.1 | 12963 | 12986 | 23 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12963.00 t/12986.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 230.00, Diff 1000.00, Temp 251.00
08/08/2021 | 12:12 | 12:18 | 0.1 | 12986 | 12986 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 12:18 | 12:41 | 0.38 | 12986 | 13006 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/12986.00 t/13006.00, TF -90.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 52.17, Diff 300.00, Temp 251.00
08/08/2021 | 12:41 | 12:47 | 0.1 | 13006 | 13017 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13006.00 t/13017.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 110.00, Diff 1000.00, Temp 255.00
08/08/2021 | 12:47 | 12:53 | 0.1 | 13017 | 13017 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 12:53 | 13:07 | 0.23 | 13017 | 13112 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13017.00 t/13112.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 407.14, Diff 1000.00, Temp 255.00
08/08/2021 | 13:07 | 13:14 | 0.12 | 13112 | 13112 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 13:14 | 13:20 | 0.1 | 13112 | 13118 | 6 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13112.00 t/13118.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 60.00, Diff 1000.00, Temp 255.00
08/08/2021 | 13:20 | 13:40 | 0.33 | 13118 | 13146 | 28 | LAT | 3: BHA 3 | 2J | Slide Drill f/13118.00 t/13146.00, TF -20.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 84.00, Diff 300.00, Temp 255.00
08/08/2021 | 13:40 | 13:54 | 0.23 | 13146 | 13206 | 60 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13146.00 t/13206.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 257.14, Diff 1000.00, Temp 255.00
08/08/2021 | 13:54 | 14:01 | 0.12 | 13206 | 13206 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 14:01 | 14:15 | 0.23 | 13206 | 13224 | 18 | LAT | 3: BHA 3 | 2J | Slide Drill f/13206.00 t/13224.00, TF -20.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 77.14, Diff 300.00, Temp 255.00
08/08/2021 | 14:15 | 14:30 | 0.25 | 13224 | 13300 | 76 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13224.00 t/13300.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 304.00, Diff 1000.00, Temp 255.00
08/08/2021 | 14:30 | 14:38 | 0.13 | 13300 | 13300 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 14:38 | 14:53 | 0.25 | 13300 | 13395 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13300.00 t/13395.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 380.00, Diff 1000.00, Temp 255.00
08/08/2021 | 14:53 | 15:00 | 0.12 | 13395 | 13395 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 15:00 | 15:04 | 0.07 | 13395 | 13400 | 5 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13395.00 t/13400.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 75.00, Diff 1000.00, Temp 255.00
08/08/2021 | 15:04 | 15:27 | 0.38 | 13400 | 13430 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/13400.00 t/13430.00, TF 90.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 78.26, Diff 300.00, Temp 255.00
08/08/2021 | 15:27 | 15:41 | 0.23 | 13430 | 13490 | 60 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13430.00 t/13490.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 257.14, Diff 1000.00, Temp 255.00
08/08/2021 | 15:41 | 15:48 | 0.12 | 13490 | 13490 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 15:48 | 15:52 | 0.07 | 13490 | 13500 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13490.00 t/13500.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 150.00, Diff 1000.00, Temp 258.00
08/08/2021 | 15:52 | 16:16 | 0.4 | 13500 | 13518 | 18 | LAT | 3: BHA 3 | 2J | Slide Drill f/13500.00 t/13518.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 45.00, Diff 300.00, Temp 258.00
08/08/2021 | 16:16 | 16:24 | 0.13 | 13518 | 13584 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13518.00 t/13584.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 495.00, Diff 1000.00, Temp 258.00
08/08/2021 | 16:24 | 16:31 | 0.12 | 13584 | 13584 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 16:31 | 16:34 | 0.05 | 13584 | 13594 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13584.00 t/13594.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 200.00, Diff 1000.00, Temp 258.00
08/08/2021 | 16:34 | 16:47 | 0.22 | 13594 | 13609 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/13594.00 t/13609.00, TF 180G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 69.23
08/08/2021 | 16:47 | 17:00 | 0.22 | 13609 | 13678 | 69 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13609.00 t/13678.00, w/WOB 40,Flow 400, RPM 80, Press 5200, Tq 17000, ROP 318.46, Diff 1000.00, Temp 262.00
08/08/2021 | 17:00 | 18:00 | 1 | 13678 | 13678 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
08/08/2021 | 18:00 | 18:05 | 0.08 | 13678 | 13678 | 0 | LAT | 3: BHA 3 | 10D | Survey & Connection
08/08/2021 | 18:05 | 18:09 | 0.07 | 13678 | 13686 | 8 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13678.00 t/13686.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 120.00, Diff 1000.00, Temp 262.00
08/08/2021 | 18:09 | 18:45 | 0.6 | 13686 | 13686 | 0 | LAT | 3: BHA 3 | 8E | Rig Blacked Out
08/08/2021 | 18:45 | 18:57 | 0.2 | 13686 | 13696 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/13686.00 t/13696.00, TF 180G, w/WOB 40.00,Flow 400.00, Press 5200.00, Tq 17000.00, ROP 50.00, Diff 1000.00, Temp 262.00
08/08/2021 | 18:57 | 19:11 | 0.23 | 13696 | 13771 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13696.00 t/13771.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 321.43, Diff 1000.00, Temp 262.00
08/08/2021 | 19:11 | 19:21 | 0.17 | 13771 | 13771 | 0 | LAT | 3: BHA 3 | 5A | Circulate Out Gas
08/08/2021 | 19:21 | 19:26 | 0.08 | 13771 | 13771 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 19:26 | 19:41 | 0.25 | 13771 | 13866 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13771.00 t/13866.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 380.00, Diff 1000.00, Temp 262.00
08/08/2021 | 19:41 | 19:46 | 0.08 | 13866 | 13866 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 19:46 | 19:50 | 0.07 | 13866 | 13876 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13866.00 t/13876.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 150.00, Diff 1000.00, Temp 262.00
08/08/2021 | 19:50 | 20:03 | 0.22 | 13876 | 13886 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/13876.00 t/13886.00, TF 180G, w/WOB 40.00,Flow 400.00, Press 5200.00, Tq 17000.00, ROP 46.15, Diff 1000.00, Temp 262.00
08/08/2021 | 20:03 | 20:18 | 0.25 | 13886 | 13960 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13886.00 t/13960.00, w/WOB 40.00,Flow 400.00, RPM 80, Press 5200.00, Tq 17000.00, ROP 296.00, Diff 1000.00, Temp 262.00
08/08/2021 | 20:18 | 20:23 | 0.08 | 13960 | 13960 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 20:23 | 20:41 | 0.3 | 13960 | 14054 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13960.00 t/14054.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 313.33, Diff 1000.00, Temp 262.00
08/08/2021 | 20:41 | 20:46 | 0.08 | 14054 | 14054 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 20:46 | 21:02 | 0.27 | 14054 | 14148 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14054.00 t/14148.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 352.50, Diff 1000.00, Temp 262.00
08/08/2021 | 21:02 | 21:07 | 0.08 | 14148 | 14148 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/08/2021 | 21:07 | 21:11 | 0.07 | 14148 | 14159 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14148.00 t/14159.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 165.00, Diff 1000.00, Temp 262.00
08/08/2021 | 21:11 | 21:38 | 0.45 | 14159 | 14171 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/14159.00 t/14171.00, TF -170G, w/WOB 40.00,Flow 400.00, Press 5200.00, Tq 17000.00, ROP 26.67, Diff 1000.00, Temp 262.00
08/08/2021 | 21:38 | 21:53 | 0.25 | 14171 | 14242 | 71 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14171.00 t/14242.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5200.00, Tq 17000.00, ROP 284.00, Diff 1000.00, Temp 262.00
08/08/2021 | 21:53 | 24:00 | 2.12 | 14242 | 14242 | 0 | LAT | 3: BHA 3 | 5A | Lost Full Returns Spot Mud Cap And Drill With Water
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_9_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/09/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 102900
|  |  |  | 24hr Summary: |  | Drilling Ahead in lateral section
|  |  |  | 24hr Lookahead: |  | Continue drilling in lateral section
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14242 |  | 9906 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 16337 |  | 16337 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 2095 |  | 6431 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): |  | 248 |  | 1466 | [5 empty] | 100: | 11 | Chlorides: | 270666
Rotary Drilled (Usft): |  | 1847 |  | 4965 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 7.20
Drlg/Circ Hrs: |  | 18.38 / 4.88 |  | 45.17 / 14.85 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67:33
Slide Drilling Hrs: |  | 7.33 |  | 21.75 |  | SN: |  | 13618580 |  | 10s Gel: | 14 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 11.05 |  | 23.42 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 167.15 / 33.82 |  | 212.03 / 67.40 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 73 |  | Grade In: |  | New
% Slide: |  | 11.84 |  | 22.8 |  | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
% Rotary: |  | 88.16 |  | 77.2 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Doug Ferguson |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 33.91
BTI |  |  |  | 4.812 | 2.062 |  |  |  |  | 1.65 |  | 35.56
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.6
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.6
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.51
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.47
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.39
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 131.06
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.83
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.47
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.85
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.75
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5917.68
Agitator / Ball Drop |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.44 |  | 5939.12
5939.12
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14173 | 88.08 | 141.38 | 10482.17 | -2391.17 | 1932.21 | 0.96 |  | 86.83 | 3074.1 | 0.05 |  | 0.96 | 94
14268 | 86.9 | 141.05 | 10486.33 | -2465.15 | 1991.66 | 1.29 |  | -164.4 | 3169 | -1.24 |  | -0.35 | 95
14363 | 86.34 | 140.77 | 10491.93 | -2538.76 | 2051.45 | 0.66 |  | -153.48 | 3263.83 | -0.59 |  | -0.29 | 95
14457 | 88.43 | 141.59 | 10496.22 | -2611.91 | 2110.32 | 2.39 |  | 21.42 | 3357.72 | 2.22 |  | 0.87 | 94
14551 | 87.9 | 141.23 | 10499.23 | -2685.35 | 2168.92 | 0.68 |  | -145.83 | 3451.67 | -0.56 |  | -0.38 | 94
14646 | 89.41 | 141 | 10501.46 | -2759.27 | 2228.54 | 1.61 |  | -8.66 | 3546.64 | 1.59 |  | -0.24 | 95
14740 | 87.1 | 140.33 | 10504.32 | -2831.94 | 2288.09 | 2.56 |  | -163.84 | 3640.57 | -2.46 |  | -0.71 | 94
14835 | 87.38 | 138.27 | 10508.9 | -2903.88 | 2349.96 | 2.19 |  | -82.3 | 3735.38 | 0.29 |  | -2.17 | 95
14930 | 87.55 | 138 | 10513.1 | -2974.55 | 2413.3 | 0.34 |  | -57.78 | 3830.11 | 0.18 |  | -0.28 | 95
15024 | 87.8 | 140.2 | 10516.91 | -3045.54 | 2474.79 | 2.35 |  | 83.56 | 3923.93 | 0.27 |  | 2.34 | 94
15119 | 87.75 | 138.8 | 10520.6 | -3117.72 | 2536.44 | 1.47 |  | -92.07 | 4018.79 | -0.05 |  | -1.47 | 95
15214 | 87.61 | 142.62 | 10524.45 | -3191.18 | 2596.54 | 4.02 |  | 92.18 | 4113.68 | -0.15 |  | 4.02 | 95
15308 | 85.21 | 143.42 | 10530.33 | -3266.11 | 2652.97 | 2.69 |  | 161.62 | 4207.46 | -2.55 |  | 0.85 | 94
15402 | 84.91 | 143.48 | 10538.43 | -3341.35 | 2708.74 | 0.33 |  | 168.73 | 4301.07 | -0.32 |  | 0.06 | 94
15496 | 85.01 | 143.32 | 10546.69 | -3416.52 | 2764.57 | 0.2 |  | -57.9 | 4394.66 | 0.11 |  | -0.17 | 94
15590 | 84.83 | 142.89 | 10555.01 | -3491.4 | 2820.78 | 0.49 |  | -112.81 | 4488.26 | -0.19 |  | -0.46 | 94
15684 | 87.08 | 144.09 | 10561.64 | -3566.76 | 2876.56 | 2.71 |  | 28.06 | 4581.97 | 2.39 |  | 1.28 | 94
15778 | 87.93 | 144.51 | 10565.73 | -3643.02 | 2931.36 | 1.01 |  | 26.28 | 4675.78 | 0.9 |  | 0.45 | 94
15872 | 88.13 | 143.4 | 10568.96 | -3718.98 | 2986.64 | 1.2 |  | -79.8 | 4769.65 | 0.21 |  | -1.18 | 94
15967 | 84.8 | 141.89 | 10574.82 | -3794.34 | 3044.16 | 3.85 |  | -155.69 | 4864.44 | -3.51 |  | -1.59 | 95
16060 | 83.79 | 141.72 | 10584.07 | -3867.06 | 3101.38 | 1.1 |  | -170.5 | 4956.97 | -1.09 |  | -0.18 | 93
16155 | 86.49 | 142.06 | 10592.11 | -3941.54 | 3159.79 | 2.86 |  | 7.17 | 5051.62 | 2.84 |  | 0.36 | 95
16250 | 90.2 | 141.71 | 10594.86 | -4016.24 | 3218.4 | 3.92 |  | -5.39 | 5146.57 | 3.91 |  | -0.37 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 113.96 | 40 | 80 | 284 | 300 | 4450 | 3350 | 0 | 245 | 190 | 160 | 17000 | 0
Run | 142.38 | 35.05 | 79.22 | 329 | 367.73 | 4509.91 | 3616.91 | 0 | 231.23 | 188.27 | 166 | 16628.79 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 08/09/2021 |  | 1 |  | 6000
Directional & MWD Standby |  |  |  |  | 08/09/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 08/09/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 08/09/2021 |  | 17 |  | 1150
Directional & MWD / Gamma Services |  |  |  |  | 08/09/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/09/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/09/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/09/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/09/2021 |  | 12 |  | 9000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/09/2021 | 00:00 | 00:25 | 0.42 | 14242 | 14242 | 0 | LAT | 3: BHA 3 | 5A | MWD Survey
08/09/2021 | 00:25 | 00:31 | 0.1 | 14242 | 14252 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14242.00 t/14252.00, w/WOB 40.00,Flow 300, RPM 80.00, Press 4450, Tq 17000.00, ROP 100.00, Diff 1100.00, Temp 142.00
08/09/2021 | 00:31 | 00:39 | 0.13 | 14252 | 14255 | 3 | LAT | 3: BHA 3 | 2J | Slide Drill f/14252.00 t/14255.00, TF 180.00G, w/WOB 40.00,Flow 300, Press 4450, Tq 17000.00, ROP 22.50, Diff 1100.00, Temp 142.00
08/09/2021 | 00:39 | 01:12 | 0.55 | 14255 | 14337 | 82 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14255.00 t/14337.00, w/WOB 40.00,Flow 300, RPM 80.00, Press 4450, Tq 17000.00, ROP 149.09, Diff 1100.00, Temp 142.00
08/09/2021 | 01:12 | 01:17 | 0.08 | 14337 | 14337 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 01:17 | 01:49 | 0.53 | 14337 | 14432 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14337.00 t/14432.00, w/WOB 40.00,Flow 300, RPM 80.00, Press 4450, Tq 17000.00, ROP 178.13, Diff 1100.00, Temp 142.00
08/09/2021 | 01:49 | 01:53 | 0.07 | 14432 | 14432 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 01:53 | 02:31 | 0.63 | 14432 | 14526 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14432.00 t/14526.00, w/WOB 40.00,Flow 300, RPM 80.00, Press 4450, Tq 17000.00, ROP 148.42, Diff 1100.00, Temp 142.00
08/09/2021 | 02:31 | 02:36 | 0.08 | 14526 | 14526 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 02:36 | 03:00 | 0.4 | 14526 | 14536 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/14526.00 t/14536.00, TF 180.00G, w/WOB 40.00,Flow 300, Press 4450, Tq 17000.00, ROP 25.00, Diff 1100.00, Temp 142.00
08/09/2021 | 03:00 | 03:28 | 0.47 | 14536 | 14620 | 84 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14536.00 t/14620.00, w/WOB 40.00,Flow 300, RPM 80.00, Press 4450, Tq 17000.00, ROP 180.00, Diff 1100.00, Temp 142.00
08/09/2021 | 03:28 | 03:33 | 0.08 | 14620 | 14620 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 03:33 | 04:03 | 0.5 | 14620 | 14715 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14620.00 t/14715.00, w/WOB 40.00,Flow 300, RPM 80.00, Press 4450, Tq 17000.00, ROP 190.00, Diff 1100.00, Temp 142.00
08/09/2021 | 04:03 | 04:08 | 0.08 | 14715 | 14715 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 04:08 | 04:35 | 0.45 | 14715 | 14735 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/14715.00 t/14735.00, TF 150G, w/WOB 40.00,Flow 300, Press 4450, Tq 17000.00, ROP 44.44, Diff 1100.00, Temp 142.00
08/09/2021 | 04:35 | 05:08 | 0.55 | 14735 | 14809 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14735.00 t/14809.00, w/WOB 40.00,Flow 300.00, RPM 0.00, Press 4450.00, Tq 17000.00, ROP 134.55, Diff 1100.00, Temp 142.00
08/09/2021 | 05:08 | 05:45 | 0.62 | 14809 | 14904 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14809.00 t/14904.00, w/WOB 40.00,Flow 300.00, RPM 0.00, Press 4450.00, Tq 17000.00, ROP 154.05, Diff 1100.00, Temp 142.00
08/09/2021 | 05:45 | 06:00 | 0.25 | 14904 | 14904 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 06:00 | 06:05 | 0.08 | 14904 | 14915 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14904.00 t/14915.00, w/WOB 40.00,Flow 300.00, RPM 0.00, Press 4450.00, Tq 17000.00, ROP 132.00, Diff 1100.00, Temp 142.00
08/09/2021 | 06:05 | 06:33 | 0.47 | 14915 | 14940 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/14915.00 t/14940.00, TF 110G, w/WOB 40.00,Flow 300.00, Press 4450.00, Tq 17000.00, ROP 53.57, Diff 1100.00, Temp 142.00
08/09/2021 | 06:33 | 06:50 | 0.28 | 14940 | 14999 | 59 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14940.00 t/14999.00, w/WOB 40.00,Flow 300.00, RPM 0.00, Press 4450.00, Tq 17000.00, ROP 208.24, Diff 1100.00, Temp 142.00
08/09/2021 | 06:50 | 07:16 | 0.43 | 14999 | 14999 | 0 | LAT | 3: BHA 3 | 5A | Circulate while wait on orders from geologist
08/09/2021 | 07:16 | 07:26 | 0.17 | 14999 | 14999 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 07:26 | 07:43 | 0.28 | 14999 | 15024 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/14999.00 t/15024.00, TF 120G, w/WOB 40.00,Flow 375, Press 5000, Tq 0, ROP 88.24, Diff 400.00, Temp 158.00
08/09/2021 | 07:43 | 07:47 | 0.07 | 15024 | 15031 | 7 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15024.00 t/15031.00, w/WOB 40.00,Flow 375, RPM 80.00, Press 5600, Tq 23000, ROP 105.00, Diff 1000.00, Temp 158.00
08/09/2021 | 07:47 | 09:34 | 1.78 | 15031 | 15031 | 0 | LAT | 3: BHA 3 | 5A | Circulate with 1 pump while making repairs to other 2 pumps
08/09/2021 | 09:34 | 09:52 | 0.3 | 15031 | 15093 | 62 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15031.00 t/15093.00, w/WOB 40.00,Flow 375, RPM 80.00, Press 5600, Tq 23000, ROP 206.67, Diff 1000.00, Temp 158.00
08/09/2021 | 09:52 | 10:00 | 0.13 | 15093 | 15093 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 10:00 | 10:05 | 0.08 | 15093 | 15103 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15093.00 t/15103.00, w/WOB 40.00,Flow 375, RPM 80.00, Press 5600, Tq 23000, ROP 120.00, Diff 1000.00, Temp 158.00
08/09/2021 | 10:05 | 10:26 | 0.35 | 15103 | 15123 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15103.00 t/15123.00, TF 130G, w/WOB 40.00,Flow 375, Press 5000, Tq 0, ROP 57.14, Diff 400.00, Temp 158.00
08/09/2021 | 10:26 | 10:45 | 0.32 | 15123 | 15188 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15123.00 t/15188.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 205.26, Diff 1000.00, Temp 158.00
08/09/2021 | 10:45 | 10:55 | 0.17 | 15188 | 15188 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 10:55 | 11:58 | 1.05 | 15188 | 15238 | 50 | LAT | 3: BHA 3 | 2J | Slide Drill f/15188.00 t/15238.00, TF 130.00G, w/WOB 40.00,Flow 375.00, Press 5000.00, Tq 0.00, ROP 47.62, Diff 400.00, Temp 158.00
08/09/2021 | 11:58 | 12:15 | 0.28 | 15238 | 15283 | 45 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15238.00 t/15283.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 158.82, Diff 1000.00, Temp 158.00
08/09/2021 | 12:15 | 12:23 | 0.13 | 15283 | 15283 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 12:23 | 13:09 | 0.77 | 15283 | 15303 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15283.00 t/15303.00, TF 180.00G, w/WOB 40.00,Flow 375.00, Press 5000.00, Tq 0.00, ROP 26.09, Diff 400.00, Temp 158.00
08/09/2021 | 13:09 | 13:36 | 0.45 | 15303 | 15377 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15303.00 t/15377.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 164.44, Diff 1000.00, Temp 158.00
08/09/2021 | 13:36 | 13:43 | 0.12 | 15377 | 15377 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 13:43 | 14:17 | 0.57 | 15377 | 15471 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15377.00 t/15471.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 165.88, Diff 1000.00, Temp 158.00
08/09/2021 | 14:17 | 14:23 | 0.1 | 15471 | 15471 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 14:23 | 14:52 | 0.48 | 15471 | 15535 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15471.00 t/15535.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 132.41, Diff 1000.00, Temp 158.00
08/09/2021 | 14:52 | 15:00 | 0.13 | 15535 | 15535 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 15:00 | 15:24 | 0.4 | 15535 | 15659 | 124 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15535.00 t/15659.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 310.00, Diff 1000.00, Temp 158.00
08/09/2021 | 15:24 | 15:32 | 0.13 | 15659 | 15659 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 15:32 | 16:12 | 0.67 | 15659 | 15674 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/15659.00 t/15674.00, TF 30.00G, w/WOB 40.00,Flow 375.00, Press 5000.00, Tq 0.00, ROP 22.50, Diff 400.00, Temp 158.00
08/09/2021 | 16:12 | 16:36 | 0.4 | 15674 | 15753 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15674.00 t/15753.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 197.50, Diff 1000.00, Temp 158.00
08/09/2021 | 16:36 | 16:43 | 0.12 | 15753 | 15753 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 16:43 | 17:16 | 0.55 | 15753 | 15847 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15753.00 t/15847.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 170.91, Diff 1000.00, Temp 158.00
08/09/2021 | 17:16 | 18:00 | 0.73 | 15847 | 15847 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
08/09/2021 | 18:00 | 18:04 | 0.07 | 15847 | 15847 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 18:04 | 18:08 | 0.07 | 15847 | 15857 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15847.00 t/15857.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 150.00, Diff 1000.00, Temp 158.00
08/09/2021 | 18:08 | 18:55 | 0.78 | 15857 | 15869 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/15857.00 t/15869.00, TF -140.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 15.32, Diff 1000.00, Temp 158.00
08/09/2021 | 18:55 | 19:21 | 0.43 | 15869 | 15941 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15869.00 t/15941.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 166.15, Diff 1000.00, Temp 158.00
08/09/2021 | 19:21 | 19:25 | 0.07 | 15941 | 15941 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 19:25 | 19:35 | 0.17 | 15941 | 15951 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15941.00 t/15951.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 60.00, Diff 1000.00, Temp 158.00
08/09/2021 | 19:35 | 20:19 | 0.73 | 15951 | 15966 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/15951.00 t/15966.00, TF 150.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 20.45, Diff 1000.00, Temp 158.00
08/09/2021 | 20:19 | 20:44 | 0.42 | 15966 | 16036 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15966.00 t/16036.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 168.00, Diff 1000.00, Temp 158.00
08/09/2021 | 20:44 | 20:48 | 0.07 | 16036 | 16036 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 20:48 | 21:26 | 0.63 | 16036 | 16129 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16036.00 t/16129.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 146.84, Diff 1000.00, Temp 158.00
08/09/2021 | 21:26 | 21:30 | 0.07 | 16129 | 16129 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 21:30 | 21:37 | 0.12 | 16129 | 16139 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16129.00 t/16139.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 85.71, Diff 1000.00, Temp 158.00
08/09/2021 | 21:37 | 22:34 | 0.95 | 16139 | 16164 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/16139.00 t/16164.00, TF 20.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 26.32, Diff 1000.00, Temp 176.00
08/09/2021 | 22:34 | 22:56 | 0.37 | 16164 | 16224 | 60 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16164.00 t/16224.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 163.64, Diff 1000.00, Temp 176.00
08/09/2021 | 22:56 | 23:00 | 0.07 | 16224 | 16224 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 23:00 | 23:30 | 0.5 | 16224 | 16319 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16224.00 t/16319.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 190.00, Diff 1000.00, Temp 176.00
08/09/2021 | 23:30 | 23:34 | 0.07 | 16319 | 16319 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/09/2021 | 23:34 | 23:42 | 0.13 | 16319 | 16329 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16319.00 t/16329.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 75.00, Diff 1000.00, Temp 176.00
08/09/2021 | 23:42 | 24:00 | 0.3 | 16329 | 16337 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/16329.00 t/16337.00, TF -160.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 26.67, Diff 1000.00, Temp 176.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_10_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/10/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 112350
|  |  |  | 24hr Summary: |  | Drill Lateral Section
|  |  |  | 24hr Lookahead: |  | POOH & P/U BHA #4
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16337 |  | 9906 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV: | 1
End Depth (Usft): |  | 17489 |  | 17489 |  | OD (in): |  |  |  | 300: | 4 | YP: | 3
Total Drilled (Usft): |  | 1152 |  | 7583 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 29
Slide Drilled (Usft): |  | 173 |  | 1639 | [5 empty] | 100: | 2 | Chlorides: | 3500
Rotary Drilled (Usft): |  | 979 |  | 5944 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 2.60
Drlg/Circ Hrs: |  | 12.82 / 6.27 |  | 57.98 / 21.12 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0
Slide Drilling Hrs: |  | 6.78 |  | 28.53 |  | SN: |  | 13618580 |  | 10s Gel: | 0.5 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 6.03 |  | 29.45 |  | Bit # |  | 3 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 162.27 / 25.50 |  | 201.83 / 57.44 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 97 |  | Grade In: |  | New
% Slide: |  | 15.02 |  | 21.61 |  | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
% Rotary: |  | 84.98 |  | 78.39 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 33.91
BTI |  |  |  | 4.812 | 2.062 |  |  |  |  | 1.65 |  | 35.56
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.6
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.6
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.51
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.47
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.39
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 131.06
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.83
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.47
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.85
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.75
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5917.68
Agitator / Ball Drop |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.44 |  | 5939.12
5939.12
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16344 | 90.21 | 141.51 | 10594.52 | -4089.91 | 3276.77 | 0.21 |  | -87.14 | 5240.57 | 0.01 |  | -0.21 | 94
16438 | 89.87 | 141.21 | 10594.45 | -4163.34 | 3335.47 | 0.48 |  | -138.58 | 5334.56 | -0.36 |  | -0.32 | 94
16534 | 88.36 | 141.97 | 10595.94 | -4238.55 | 3395.1 | 1.76 |  | 153.29 | 5430.55 | -1.57 |  | 0.79 | 96
16627 | 84.7 | 141.85 | 10601.57 | -4311.6 | 3452.36 | 3.94 |  | -178.13 | 5523.36 | -3.94 |  | -0.13 | 93
16722 | 81.85 | 141.76 | 10612.69 | -4385.74 | 3510.69 | 3 |  | -178.21 | 5617.7 | -3 |  | -0.09 | 95
16816 | 83.76 | 142.32 | 10624.46 | -4459.26 | 3568.05 | 2.12 |  | 16.25 | 5710.95 | 2.03 |  | 0.6 | 94
16911 | 86.79 | 141.77 | 10632.29 | -4533.91 | 3626.27 | 3.24 |  | -10.28 | 5805.61 | 3.19 |  | -0.58 | 95
17006 | 86.92 | 141.51 | 10637.5 | -4608.29 | 3685.14 | 0.31 |  | -63.41 | 5900.47 | 0.14 |  | -0.27 | 95
17100 | 86.57 | 139.61 | 10642.84 | -4680.76 | 3744.76 | 2.05 |  | -100.51 | 5994.3 | -0.37 |  | -2.02 | 94
17196 | 86.91 | 137.53 | 10648.3 | -4752.62 | 3808.18 | 2.19 |  | -80.76 | 6090 | 0.35 |  | -2.17 | 96
17290 | 86.77 | 139.53 | 10653.48 | -4822.94 | 3870.33 | 2.13 |  | 94.06 | 6183.71 | -0.15 |  | 2.13 | 94
17386 | 86.98 | 138.74 | 10658.71 | -4895.43 | 3933.04 | 0.85 |  | -75.11 | 6279.47 | 0.22 |  | -0.82 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 89.88 | 40 | 80 | 284 | 300 | 4450 | 3350 | 0 | 245 | 190 | 160 | 17000 | 0
Run | 130.78 | 35.05 | 79.22 | 329 | 367.73 | 4509.91 | 3616.91 | 0 | 231.23 | 188.27 | 166 | 16628.79 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 08/10/2021 |  | 1 |  | 6000
Directional & MWD Standby |  |  |  |  | 08/10/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 08/10/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 08/10/2021 |  | 17 |  | 1150
Directional & MWD / Gamma Services |  |  |  |  | 08/10/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/10/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/10/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/10/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/10/2021 |  | 12 |  | 9000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/10/2021 | 00:00 | 00:20 | 0.33 | 16337 | 16346 | 9 | LAT | 3: BHA 3 | 2J | Slide Drill f/16337.00 t/16346.00, TF -160.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 27.00, Diff 1000.00, Temp 176.00
08/10/2021 | 00:20 | 00:47 | 0.45 | 16346 | 16412 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16346.00 t/16412.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 146.67, Diff 1000.00, Temp 176.00
08/10/2021 | 00:47 | 00:51 | 0.07 | 16412 | 16412 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 00:51 | 00:56 | 0.08 | 16412 | 16427 | 15 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16412.00 t/16427.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 180.00, Diff 1000.00, Temp 176.00
08/10/2021 | 00:56 | 01:40 | 0.73 | 16427 | 16443 | 16 | LAT | 3: BHA 3 | 2J | Slide Drill f/16427.00 t/16443.00, TF -160.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 21.82, Diff 1000.00, Temp 176.00
08/10/2021 | 01:40 | 02:08 | 0.47 | 16443 | 16507 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16443.00 t/16507.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 137.14, Diff 1000.00, Temp 176.00
08/10/2021 | 02:08 | 02:12 | 0.07 | 16507 | 16507 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 02:12 | 03:12 | 1 | 16507 | 16537 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/16507.00 t/16537.00, TF -160.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 30.00, Diff 1000.00, Temp 176.00
08/10/2021 | 03:12 | 03:40 | 0.47 | 16537 | 16603 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16537.00 t/16603.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 141.43, Diff 1000.00, Temp 176.00
08/10/2021 | 03:40 | 03:44 | 0.07 | 16603 | 16603 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 03:44 | 03:54 | 0.17 | 16603 | 16613 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16603.00 t/16613.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 60.00, Diff 1000.00, Temp 176.00
08/10/2021 | 03:54 | 05:00 | 1.1 | 16613 | 16638 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/16613.00 t/16638.00, TF -160.00G, w/WOB 40.00,Flow 375.00, Press 5600.00, Tq 23000.00, ROP 22.73, Diff 1000.00, Temp 176.00
08/10/2021 | 05:00 | 05:30 | 0.5 | 16638 | 16696 | 58 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16638.00 t/16696.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 116.00, Diff 1000.00, Temp 176.00
08/10/2021 | 05:30 | 05:34 | 0.07 | 16696 | 16696 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 05:34 | 06:08 | 0.57 | 16696 | 16791 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16696.00 t/16791.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 167.65, Diff 1000.00, Temp 176.00
08/10/2021 | 06:08 | 06:18 | 0.17 | 16791 | 16791 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 06:18 | 06:25 | 0.12 | 16791 | 16800 | 9 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16791.00 t/16800.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 23000.00, ROP 77.14, Diff 1000.00, Temp 176.00
08/10/2021 | 06:25 | 07:19 | 0.9 | 16800 | 16825 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/16800.00 t/16825.00, TF 20.00G, w/WOB 40.00,Flow 375.00, Press 4900.00, Tq 0.00, ROP 27.78, Diff 300.00, Temp 176.00
08/10/2021 | 07:19 | 07:43 | 0.4 | 16825 | 16885 | 60 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16825.00 t/16885.00, w/WOB 40.00,Flow 375.00, RPM 80, Press 5600, Tq 27000, ROP 150.00, Diff 1000.00, Temp 182.00
08/10/2021 | 07:43 | 07:53 | 0.17 | 16885 | 16885 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 07:53 | 08:14 | 0.35 | 16885 | 16893 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/16885.00 t/16893.00, TF 0G, w/WOB 40.00,Flow 375.00, Press 4900.00, Tq 0.00, ROP 22.86, Diff 300.00, Temp 182.00
08/10/2021 | 08:14 | 08:46 | 0.53 | 16893 | 16980 | 87 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16893.00 t/16980.00, w/WOB 40.00,Flow 375.00, RPM 80, Press 5600, Tq 27000, ROP 163.13, Diff 1000.00, Temp 182.00
08/10/2021 | 08:46 | 08:56 | 0.17 | 16980 | 16980 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 08:56 | 09:24 | 0.47 | 16980 | 17075 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16980.00 t/17075.00, w/WOB 40.00,Flow 375.00, RPM 80, Press 5600, Tq 27000, ROP 203.57, Diff 1000.00, Temp 182.00
08/10/2021 | 09:24 | 09:34 | 0.17 | 17075 | 17075 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 09:34 | 09:58 | 0.4 | 17075 | 17169 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17075.00 t/17169.00, w/WOB 40.00,Flow 375.00, RPM 80, Press 5600, Tq 27000, ROP 235.00, Diff 1000.00, Temp 182.00
08/10/2021 | 09:58 | 10:08 | 0.17 | 17169 | 17169 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 10:08 | 10:32 | 0.4 | 17169 | 17265 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17169.00 t/17265.00, w/WOB 40.00,Flow 375.00, RPM 80, Press 5600, Tq 27000, ROP 240.00, Diff 1000.00, Temp 190.00
08/10/2021 | 10:32 | 10:42 | 0.17 | 17265 | 17265 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 10:42 | 11:52 | 1.17 | 17265 | 17295 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/17265.00 t/17295.00, TF 90.00G, w/WOB 40.00,Flow 375.00, Press 4900.00, Tq 0.00, ROP 25.71, Diff 300.00, Temp 190.00
08/10/2021 | 11:52 | 12:18 | 0.43 | 17295 | 17359 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17295.00 t/17359.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 27000.00, ROP 147.69, Diff 1000.00, Temp 190.00
08/10/2021 | 12:18 | 12:28 | 0.17 | 17359 | 17359 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 12:28 | 12:57 | 0.48 | 17359 | 17455 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17359.00 t/17455.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 27000.00, ROP 198.62, Diff 1000.00, Temp 190.00
08/10/2021 | 12:57 | 13:07 | 0.17 | 17455 | 17455 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
08/10/2021 | 13:07 | 14:19 | 1.2 | 17455 | 17485 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/17455.00 t/17485.00, TF 90.00G, w/WOB 40.00,Flow 375.00, Press 4900.00, Tq 0.00, ROP 25.00, Diff 300.00, Temp 172.00
08/10/2021 | 14:19 | 14:25 | 0.1 | 17485 | 17489 | 4 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17485.00 t/17489.00, w/WOB 40.00,Flow 375.00, RPM 80.00, Press 5600.00, Tq 27000.00, ROP 40.00, Diff 1000.00, Temp 172.00
08/10/2021 | 14:25 | 15:00 | 0.58 | 17489 | 17489 | 0 | LAT | 3: BHA 3 | 3B | Touble Shoot Hole Problems
08/10/2021 | 15:00 | 19:40 | 4.67 | 17489 | 17489 | 0 | LAT | 3: BHA 3 | 3D | BackReam Out Of Hole
08/10/2021 | 19:40 | 24:00 | 4.33 | 17489 | 17489 | 0 | LAT | 3: BHA 3 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_11_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/11/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 20250 |  |  | Well Cost($): |  | 132600
|  |  |  | 24hr Summary: |  | POOH & P/U BHA #4
|  |  |  | 24hr Lookahead: |  | TIH With BHA #4 & Drill Lateral Section.
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17489 |  | 17489 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV: | 1
End Depth (Usft): |  | 17733 |  | 17733 |  | OD (in): |  |  |  | 300: | 4 | YP: | 3
Total Drilled (Usft): |  | 244 |  | 244 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 29
Slide Drilled (Usft): |  | 5 |  | 5 | [5 empty] | 100: | 2 | Chlorides: | 3500
Rotary Drilled (Usft): |  | 239 |  | 239 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 2.60
Drlg/Circ Hrs: |  | 1.63 / 0.37 |  | 1.63 / 0.37 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0
Slide Drilling Hrs: |  | 0.25 |  | 0.25 |  | SN: |  | 13618580 |  | 10s Gel: |  | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 1.38 |  | 1.38 |  | Bit # |  | 3 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 172.77 / 20.00 |  | 172.77 / 20.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 14.17 |  | 14.17 |  | Grade In: |  | New
% Slide: |  | 2.05 |  | 2.05 |  | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
% Rotary: |  | 97.95 |  | 97.95 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 33.91
BTI |  |  |  | 4.812 | 2.062 |  |  |  |  | 1.65 |  | 35.56
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.6
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.6
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.51
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.47
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.39
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 131.06
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.83
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.47
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.85
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.75
33 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3114.93 |  | 5917.68
Agitator / Ball Drop |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.44 |  | 5939.12
5939.12
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 149.69 | 40 | 80 | 284 | 300 | 4450 | 3350 | 0 | 245 | 190 | 160 | 17000 | 0
Run | 149.69 | 35.05 | 79.22 | 329 | 367.73 | 4509.91 | 3616.91 | 0 | 231.23 | 188.27 | 166 | 16628.79 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 08/11/2021 |  | 24 |  | 800 |  | 1 | 800
Directional & MWD Standby |  |  |  |  | 08/11/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 08/11/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 08/11/2021 |  | 17 |  | 1150
Directional & MWD / Gamma Services |  |  |  |  | 08/11/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/11/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/11/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/11/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/11/2021 |  | 12 |  | 9000 |  | 1 | 9000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 08/11/2021 |  | 8 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 20250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/11/2021 | 00:00 | 08:20 | 8.33 | 17489 | 17489 | 0 | LAT | 3: BHA 3 | 6B | POOH
08/11/2021 | 08:20 | 08:50 | 0.5 | 17489 | 17489 | 0 | LAT | 3: BHA 3 | 6P | Lay down BHA #3
08/11/2021 | 08:50 | 09:50 | 1 | 17489 | 17489 | 0 | LAT | 4: BHA 4 | 6O | Pick up BHA #4
08/11/2021 | 09:50 | 10:00 | 0.17 | 17489 | 17489 | 0 | LAT | 4: BHA 4 | 5A | Surface test MWD (OK)
08/11/2021 | 10:00 | 22:10 | 12.17 | 17489 | 17489 | 0 | LAT | 4: BHA 4 | 6A | TIH
08/11/2021 | 22:10 | 22:18 | 0.13 | 17489 | 17527 | 38 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17489.00 t/17527.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5600.00, Tq 25.00, ROP 285.00, Diff 1000.00, Temp 172.00
08/11/2021 | 22:18 | 22:22 | 0.07 | 17527 | 17527 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
08/11/2021 | 22:22 | 22:56 | 0.57 | 17527 | 17622 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17527.00 t/17622.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5600.00, Tq 25.00, ROP 167.65, Diff 1000.00, Temp 198.00
08/11/2021 | 22:56 | 23:00 | 0.07 | 17622 | 17622 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
08/11/2021 | 23:00 | 23:30 | 0.5 | 17622 | 17718 | 96 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17622.00 t/17718.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5600.00, Tq 25.00, ROP 192.00, Diff 1000.00, Temp 198.00
08/11/2021 | 23:30 | 23:34 | 0.07 | 17718 | 17718 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
08/11/2021 | 23:34 | 23:45 | 0.18 | 17718 | 17728 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17718.00 t/17728.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5600.00, Tq 25.00, ROP 54.55, Diff 1000.00, Temp 198.00
08/11/2021 | 23:45 | 24:00 | 0.25 | 17728 | 17733 | 5 | LAT | 4: BHA 4 | 2J | Slide Drill f/17728.00 t/17733.00, TF 90.00G, w/WOB 18.50,Flow 375.00, Press 5600.00, Tq 25.00, ROP 20.00, Diff 720.00, Temp 198.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_12_2021_DDR
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31158 / 21DD0169MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Borgstedt 2H
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Longitude: |  | 96° 44' 37.015" W
|  |  |  | Rig: |  | Patterson 285 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/12/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 142050
|  |  |  | 24hr Summary: |  | Drill and TD Lateral Section
|  |  |  | 24hr Lookahead: |  | Circ. & POOH to Run Casing.
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17733 |  | 17489 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV: | 1
End Depth (Usft): |  | 18092 |  | 18092 |  | OD (in): |  |  |  | 300: | 4 | YP: | 3
Total Drilled (Usft): |  | 359 |  | 603 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 29
Slide Drilled (Usft): |  | 30 |  | 35 | [5 empty] | 100: | 2 | Chlorides: | 3500
Rotary Drilled (Usft): |  | 329 |  | 568 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 2.60
Drlg/Circ Hrs: |  | 3.10 / 5.62 |  | 4.73 / 5.98 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0
Slide Drilling Hrs: |  | 1.22 |  | 1.47 |  | SN: |  | 13601237 |  | 10s Gel: |  | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 1.88 |  | 3.27 |  | Bit # |  | 4 |  | PH / Temp(F) |  | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 174.69 / 24.66 |  | 173.88 / 23.86 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 18.17 |  | 32.33 |  | Grade In: |  | New
% Slide: |  | 8.36 |  | 5.8 |  | Grade Out: |  | 1-1-RR-X-I-RR-TD
% Rotary: |  | 91.64 |  | 94.2 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Bobby Guin |  | Nathan Marks |  | Jeff Campbell |  | Pete Langille |  | Robert Bowlin |  | Bill Paul |  | Jason
Greg Johnson |  | Donny Klein |  | Charlie Mckirahan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 HS 88 .002 Slick |  |  |  | 5.25 | 2 |  |  |  |  | 33.04 |  | 33.79
BTI |  |  |  | 4.875 | 2.188 |  |  |  |  | 1.65 |  | 35.44
5" Non Mag Pony Collar |  |  |  | 4.938 | 2.688 |  |  |  |  | 10.04 |  | 45.48
UBHO |  |  |  | 5.188 | 2.5 |  |  |  |  | 4 |  | 49.48
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.91 |  | 79.39
5" Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 29.96 |  | 109.35
Tomax |  |  |  | 5 | 2.625 |  |  |  |  | 17.92 |  | 127.27
X/O- XT39P x CET43B |  |  |  | 5.5 | 2.625 |  |  |  |  | 3.67 |  | 130.94
2 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.77 |  | 319.71
Reamer |  |  |  | 5.312 | 2.562 |  |  |  |  | 8.64 |  | 328.35
26 Stands Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453.38 |  | 2781.73
Agitator |  |  |  | 5.25 | 2.625 |  |  |  |  | 20.9 |  | 2802.63
2802.63
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250006 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18023 | 88.52 | 140.28 | 10683.72 | -5379.48 | 4346.31 | 0.34 |  | 45.01 | 6915.5 | 0.24 |  | 0.24 | 637
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 115.81 | 40 | 80 | 284 | 300 | 4450 | 3350 | 0 | 245 | 190 | 160 | 17000 | 0
Run | 127.39 | 35.05 | 79.22 | 329 | 367.73 | 4509.91 | 3616.91 | 0 | 231.23 | 188.27 | 166 | 16628.79 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 08/12/2021 |  | 24 |  | 800
Directional & MWD Standby |  |  |  |  | 08/12/2021 |  | 4 |  | 3800
Perdiem Per Hand |  |  |  |  | 08/12/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Used |  |  |  |  | 08/12/2021 |  | 17 |  | 1150
Directional & MWD / Gamma Services |  |  |  |  | 08/12/2021 |  | 2 |  | 6450 |  | 1 | 6450
8 Motor Reline |  |  |  |  | 08/12/2021 |  | 15 |  | 10500
Pro Azimuthal Gamma Ray |  |  |  |  | 08/12/2021 |  | 23 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/12/2021 |  | 19 |  | 600 |  | 1 | 600
5.5 Premium Motor Stator Reline |  |  |  |  | 08/12/2021 |  | 12 |  | 9000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 08/12/2021 |  | 8 |  | 1000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/12/2021 | 00:00 | 00:28 | 0.47 | 17733 | 17744 | 11 | LAT | 4: BHA 4 | 2J | Slide Drill f/17733.00 t/17744.00, TF 90.00G, w/WOB 18.50,Flow 375.00, Press 5600.00, Tq 25.00, ROP 23.57, Diff 720.00, Temp 198.00
08/12/2021 | 00:28 | 00:45 | 0.28 | 17744 | 17744 | 0 | LAT | 4: BHA 4 | 8D | Mud Pump Off Line
08/12/2021 | 00:45 | 01:30 | 0.75 | 17744 | 17763 | 19 | LAT | 4: BHA 4 | 2J | Slide Drill f/17744.00 t/17763.00, TF 90.00G, w/WOB 18.50,Flow 375.00, Press 5600.00, Tq 25.00, ROP 25.33, Diff 720.00, Temp 198.00
08/12/2021 | 01:30 | 01:50 | 0.33 | 17763 | 17813 | 50 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17763.00 t/17813.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5730.00, Tq 25.00, ROP 150.00, Diff 850.00, Temp 198.00
08/12/2021 | 01:50 | 01:54 | 0.07 | 17813 | 17813 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
08/12/2021 | 01:54 | 02:26 | 0.53 | 17813 | 17907 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17813.00 t/17907.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5730.00, Tq 25.00, ROP 176.25, Diff 850.00, Temp 198.00
08/12/2021 | 02:26 | 02:30 | 0.07 | 17907 | 17907 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
08/12/2021 | 02:30 | 03:00 | 0.5 | 17907 | 18001 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17907.00 t/18001.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5730.00, Tq 25.00, ROP 188.00, Diff 850.00, Temp 198.00
08/12/2021 | 03:00 | 03:04 | 0.07 | 18001 | 18001 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
08/12/2021 | 03:04 | 03:35 | 0.52 | 18001 | 18092 | 91 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18001.00 t/18092.00, w/WOB 18.50,Flow 375.00, RPM 80.00, Press 5730.00, Tq 25.00, ROP 176.13, Diff 850.00, Temp 196.00
08/12/2021 | 03:35 | 03:44 | 0.15 | 18092 | 18092 | 0 | LAT | 4: BHA 4 | 5A | Final Survey (EOW)
08/12/2021 | 03:44 | 05:00 | 1.27 | 18092 | 18092 | 0 | LAT | 4: BHA 4 | 5A | CIrculate
08/12/2021 | 05:00 | 09:00 | 4 | 18092 | 18092 | 0 | LAT | 4: BHA 4 | 3D | Back Ream Out Of Hole
08/12/2021 | 09:00 | 17:00 | 8 | 18092 | 18092 | 0 | LAT | 4: BHA 4 | 6B | POOH
08/12/2021 | 17:00 | 18:10 | 1.17 | 18092 | 18092 | 0 | LAT | 4: BHA 4 | 6P | L/D BHA
08/12/2021 | 18:10 | 24:00 | 5.83 | 18092 | 18092 | 0 | LAT |  | 24B | Standby - Run Casing
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 389.14 (Usft)
Well: |  |  | Borgstedt 2H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124821 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/22/2021 | Depth In: |  | 108 | Total Drilled: |  | 2624.00 (Usft)
Date Out: |  |  | 06/23/2021 | Depth Out: |  | 2732 | Drilling / Circ Hours: |  | 4.37 / 2.13
Survey Offset: |  |  | 73
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 38426 | U616S | 13.5 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | SD610174 | Stabalizer | 13 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 7.86 | 9.36
| 3 | PPM800067 | 7/8 5.9 1.5 Stab HPO -.022 NBS 13 | 8 | 2 | 8.938 / 1.87 | 6 5/8 REG / 6 5/8 REG |  | 37.43 | 46.79
| 4 | SD49205 | NM Pony Drill Collar | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 7.95 | 54.74
| 5 | ZSB775210 | UBHO | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.74 | 58.48
| 6 | SD50132 | NM Drill Collar | 7.875 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.74 | 87.22
| 7 | SD55726 | NM Drill Collar | 7.875 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.8 | 116.02
| 8 | SD104622 | Crossover | 6.5 | 3.062 |  | 4 1/2 IF / 6 5/8 REG |  | 2.08 | 118.1
| 9 | Rig-1 | 9- Joints of 5" HWDP | 5 | 2.5 |  | 4 1/2 IF / 4 1/2 IF |  | 271.04 | 389.14
| 10 | [8 empty] | 389.14
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.18 | Ulterra | U616S | New | 1-2-CT-S-X-I-CT-TD | 2624
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  | PDCI / 7/8 5.9 | 5.57 / 1.50 |  | 13 | 8.75 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 100 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HPO (Minus) |  | -0.022
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | Stabalizer | 13 |  | 0 |  |  | 1.5
3 |  |  | 7/8 5.9 1.5 Stab HPO -.022 NBS 13 | 13 |  | 0.4 |  |  | 9.36

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 2565.32 (Usft)
Well: |  |  | Borgstedt 2H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124821 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/01/2021 | Depth In: |  | 2732 | Total Drilled: |  | 7174.00 (Usft)
Date Out: |  |  | 07/04/2021 | Depth Out: |  | 9906 | Drilling / Circ Hours: |  | 50.40 / 10.07
Survey Offset: |  |  | 70 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 56211 | SPL613 | 9.875 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800032 | 7/8 5.9 2.0 HPO -.014 Slick | 8 | 2 | 1.75 | 6 5/8 REG / 6 5/8 REG |  | 37.91 | 39.41
| 3 | SD51725 | NM Pony Drill Collar | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 8.33 | 47.74
| 4 | ZSB775208 | UBHO | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.83 | 51.57
| 5 | 55727 | NM Drill Collar | 8.062 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 28.76 | 80.33
| 6 | 53215 | NM Drill Collar | 7.75 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 28.03 | 108.36
| 7 | 118447 | Crossover | 6.75 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.9 | 111.26
| 8 | Rig-3 | 6 Joints of 6 1/2 in DC | 6.5 | 2.75 |  | 4 1/2 XH / 4 1/2 XH |  | 184.12 | 295.38
| 9 | 4555 | Crossover | 6.562 | 2.562 |  | 4 1/2 IF / 4 1/2 XH |  | 3 | 298.38
| 10 | Rig-1 | 9- Joints of 5" HWDP | 5 | 2.5 |  | 4 1/2 IF / 4 1/2 IF |  | 271.04 | 569.42
| 11 | Rig-2 | 21 Stands 5 in DP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 1971.19 | 2540.61
| 12 | PG6750030 | Agitator | 6.625 | 3.75 |  | 4 1/2 IF / 4 1/2 IF |  | 24.71 | 2565.32
| 13 | [8 empty] | 2565.32
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 1-2-CT-S-X-I-NO-TD | 7174
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.0 HPO -.014 Slick |  |  | PDCI / 7/8 5.9 | 5.78 / 2.00 |  | 0 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 80 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HPO (Minus) |  | 0.014
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
UBHO
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 5939.12 (Usft)
Well: |  |  | Borgstedt 2H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124821 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 08/06/2021 | Depth In: |  | 9906 | Total Drilled: |  | 7583.00 (Usft)
Date Out: |  |  | 08/11/2021 | Depth Out: |  | 17489 | Drilling / Circ Hours: |  | 57.98 / 21.12
Survey Offset: |  |  | 69 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618580 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250011 | 6/7 8.8 2.12 HS 88 .025 Slick | 5 | 2 | 5.000 / 1.72 | XT39 / 3 1/2 Reg |  | 33.16 | 33.91
| 3 | 41015 | BTI | 4.812 | 2.062 |  | XT39 / XT39 |  | 1.65 | 35.56
| 4 | SD56927 | 5" Non Mag Pony Collar | 4.938 | 2.688 |  | XT39 / XT39 |  | 10.04 | 45.6
| 5 | ZSB500043 | UBHO | 5.188 | 2.5 |  | XT39 / XT39 |  | 4 | 49.6
| 6 | SD56772 | 5" Non Mag Drill Collar | 5 | 2.688 |  | XT39 / XT39 |  | 29.91 | 79.51
| 7 | SD56709 | 5" Non Mag Drill Collar | 5 | 2.688 |  | XT39 / XT39 |  | 29.96 | 109.47
| 8 | A521239 | Tomax | 5 | 2.625 |  | XT39 / XT39 |  | 17.92 | 127.39
| 9 | SD119787 | X/O- XT39P x CET43B | 5.5 | 2.625 |  | XT39 / CET43 |  | 3.67 | 131.06
| 10 | Rig-4 | 2 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 188.77 | 319.83
| 11 | DTI-DNR-521 | Reamer | 5.312 | 2.562 |  | CET43 / CET43 |  | 8.64 | 328.47
| 12 | Rig-5 | 26 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 2453.38 | 2781.85
| 13 | PG525-0037 | Agitator | 5.25 | 2.625 |  | CET43 / CET43 |  | 20.9 | 2802.75
| 14 | Rig-6 | 33 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 3114.93 | 5917.68
| 15 | PG525-0049 | Agitator / Ball Drop | 5.25 | 2.5 |  | CET43 / CET43 |  | 21.44 | 5939.12
| 16 | [8 empty] | 5939.12
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 2-2-BT-S-X-I-CT-BHA | 7583
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 HS 88 .025 Slick |  |  | PDCI / 6/7 8.8 | 4.01 / 2.12 |  | 0 | 5.5 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Plus) |  | 0.025
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 285 | Total Length: |  | 2802.63 (Usft)
Well: |  |  | Borgstedt 2H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124821 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 08/11/2021 | Depth In: |  | 17489 | Total Drilled: |  | 603.00 (Usft)
Date Out: |  |  | 08/12/2021 | Depth Out: |  | 18092 | Drilling / Circ Hours: |  | 4.73 / 5.98
Survey Offset: |  |  | 69 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13601237 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250006 | 6/7 8.8 2.12 HS 88 .002 Slick | 5.25 | 2 |  | XT39 / 3 1/2 Reg |  | 33.04 | 33.79
| 3 | 41015 | BTI | 4.875 | 2.188 |  | XT39 / XT39 |  | 1.65 | 35.44
| 4 | SD56927 | 5" Non Mag Pony Collar | 4.938 | 2.688 |  | XT39 / XT39 |  | 10.04 | 45.48
| 5 | ZSB500043 | UBHO | 5.188 | 2.5 |  | XT39 / XT39 |  | 4 | 49.48
| 6 | SD56772 | 5" Non Mag Drill Collar | 5 | 2.688 |  | XT39 / XT39 |  | 29.91 | 79.39
| 7 | SD56709 | 5" Non Mag Drill Collar | 5 | 2.688 |  | XT39 / XT39 |  | 29.96 | 109.35
| 8 | A521239 | Tomax | 5 | 2.625 |  | XT39 / XT39 |  | 17.92 | 127.27
| 9 | SD119787 | X/O- XT39P x CET43B | 5.5 | 2.625 |  | XT39 / CET43 |  | 3.67 | 130.94
| 10 | Rig-4 | 2 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 188.77 | 319.71
| 11 | DTI-DNR-521 | Reamer | 5.312 | 2.562 |  | CET43 / CET43 |  | 8.64 | 328.35
| 12 | Rig-5 | 26 Stands Drill Pipe | 4.5 | 2.5 |  | CET43 / CET43 |  | 2453.38 | 2781.73
| 13 | PG525-0037 | Agitator | 5.25 | 2.625 |  | CET43 / CET43 |  | 20.9 | 2802.63
| 14 | [8 empty] | 2802.63
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 1-1-RR-X-I-RR-TD | 603
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 HS 88 .002 Slick |  |  | PDCI / 6/7 8.8 | 4.03 / 2.12 |  | 0 | 5.5 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Plus) |  | 0.002
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Well: |  | Borgstedt 2H
|  |  |  | Longitude: |  | 96° 44' 37.015" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 95.00/103.33/118.00
Date In: |  | 06/22/2021 15:30 |  | SN: |  | PPM800067 |  |  |  | WOB Rotate (klbs): |  | 6.00
Date Out: |  | 06/23/2021 00:40 |  | Description: |  | 7/8 5.9 1.5 Stab HPO -.022 NBS 13 |  |  |  | WOB Slide (klbs): |  | 3.93
Depth In/Out(Usft): |  | 108.00 / 2732.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 97.56
Inc In/Out: |  | 0.16 / 10.90 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 882
Azi In/Out: |  | 115.20 / 320.65 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1727.55
Total Drilled (Usft): |  | 2624 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1917.55
%Slide (Ftg): |  | 6.82 |  | Bit to Bend (Usft): |  | 5.57 |  |  |  | Tq On Btm (kftlbs): |  | 6343.9
%Slide (Time): |  | 25.88 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 179 |  | Bearing Gap (in): |  | 1.14 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 1.13 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 93.18 |  | Kickpad OD (in): |  | 8.75 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 74.20 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2445 |  | Fishneck OD (in): |  | 8.938 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 3.24 |  | Length (Usft): |  | 37.43 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 4.37 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 2.13 / 9.17 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 158.41 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-2-CT-S-X-I-CT-TD
Rot ROP (Usft/hr): |  | 754.63 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HPO (Minus) / -0.022 |  |  |  | Drill Hrs: |  | 4.37
Avg ROP (Usft/hr): |  | 600.46 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.13
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
[10 empty] | WBM |  |  | 118
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
73 | [9 empty] | 1 |  | 0.70 / 1.29
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.18 |  |  |  | 38426 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
Stabalizer 0.00 |  |  |  | SD610174 |  | 13 | 2.875 |  |  |  | 7.86 | 9.36
7/8 5.9 1.5 Stab HPO -.022 NBS 13 0.00 |  |  |  | PPM800067 |  | 8 | 2 |  |  |  | 37.43 | 46.79
NM Pony Drill Collar 0.00 |  |  |  | SD49205 |  | 7.938 | 3.25 |  |  |  | 7.95 | 54.74
UBHO 0.00 |  |  |  | ZSB775210 |  | 7.75 | 2.875 |  |  |  | 3.74 | 58.48
NM Drill Collar 0.00 |  |  |  | SD50132 |  | 7.875 | 3.25 |  |  |  | 28.74 | 87.22
NM Drill Collar 0.00 |  |  |  | SD55726 |  | 7.875 | 3.25 |  |  |  | 28.8 | 116.02
Crossover 0.00 |  |  |  | SD104622 |  | 6.5 | 3.062 |  |  |  | 2.08 | 118.1
9- Joints of 5" HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 2.5 |  |  |  | 271.04 | 389.14
-1.00 | [11 empty] | 389.14
Additional Comments
Did motor drain - Yes Visual Wear ? NO wear on pad and no visible damage to motor. Build/Drop Tendency and Magnitude - Start to 1000? build 1 degree /100? to 10 Degree to 2000?. Motor performed well with no issues. Start Temp & Max Temp ? 97 - 118 Bit Grade 1-2-CT-S-X-I-CT-TD Number of Stalls ? No Stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Well: |  | Borgstedt 2H
|  |  |  | Longitude: |  | 96° 44' 37.015" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 129.00/191.72/233.50
Date In: |  | 07/01/2021 10:45 |  | SN: |  | PPM800032 |  |  |  | WOB Rotate (klbs): |  | 34.00
Date Out: |  | 07/04/2021 18:00 |  | Description: |  | 7/8 5.9 2.0 HPO -.014 Slick |  |  |  | WOB Slide (klbs): |  | 22.41
Depth In/Out(Usft): |  | 2732.00 / 9906.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 78.70
Inc In/Out: |  | 10.90 / 15.37 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 762.71
Azi In/Out: |  | 320.65 / 150.82 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 3684.72
Total Drilled (Usft): |  | 7174 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4367.4
%Slide (Ftg): |  | 6.89 |  | Bit to Bend (Usft): |  | 5.78 |  |  |  | Tq On Btm (kftlbs): |  | 20115.94
%Slide (Time): |  | 58.79 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 494 |  | Bearing Gap (in): |  | 1.2 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 29.63 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 93.11 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 41.21 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6680 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 9.875
Rotary Hours: |  | 20.77 |  | Length (Usft): |  | 37.91 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 50.40 |  | Integral Float: |  | NO |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 10.07 / 79.25 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 16.67 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
Rot ROP (Usft/hr): |  | 321.62 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HPO (Minus) / 0.014 |  |  |  | Drill Hrs: |  | 50.40
Avg ROP (Usft/hr): |  | 142.34 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 10.07
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
29 / 18 | 14 / 9 | 5 / 4 |  | 67:33 |  | 11 | 7 | 9.1 | 270666 | WBM | 5.2 |  | 233.5
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
70 | 60 | [10 empty] | 0.00 / 6.88
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 56211 |  | 9.875 | 2 |  |  |  | 1.5 | 1.5
7/8 5.9 2.0 HPO -.014 Slick 0.00 |  |  |  | PPM800032 |  | 8 | 2 |  |  |  | 37.91 | 39.41
NM Pony Drill Collar 0.00 |  |  |  | SD51725 |  | 7.938 | 3.25 |  |  |  | 8.33 | 47.74
UBHO 0.00 |  |  |  | ZSB775208 |  | 7.75 | 2.875 |  |  |  | 3.83 | 51.57
NM Drill Collar 0.00 |  |  |  | 55727 |  | 8.062 | 3.188 |  |  |  | 28.76 | 80.33
NM Drill Collar 0.00 |  |  |  | 53215 |  | 7.75 | 3.188 |  |  |  | 28.03 | 108.36
Crossover 0.00 |  |  |  | 118447 |  | 6.75 | 2.875 |  |  |  | 2.9 | 111.26
6 Joints of 6 1/2 in DC 0.00 |  |  |  | Rig-3 |  | 6.5 | 2.75 |  |  |  | 184.12 | 295.38
Crossover 0.00 |  |  |  | 4555 |  | 6.562 | 2.562 |  |  |  | 3 | 298.38
9- Joints of 5" HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 2.5 |  |  |  | 271.04 | 569.42
21 Stands 5 in DP 0.00 |  |  |  | Rig-2 |  | 5 | 3 |  |  |  | 1971.19 | 2540.61
Agitator 0.00 |  |  |  | PG6750030 |  | 6.625 | 3.75 |  |  |  | 24.71 | 2565.32
-1.00 | [11 empty] | 2565.32
Additional Comments
Did motor drain - Yes Visual Wear ? NO wear on pad and no visible damage to motor. Build/Drop Tendency and Magnitude - Drill intermediate section of well until KOP, begin drilling curve section to 14.5?, or until we seen gamma chalk indicator. Pull out to run intermediate casing Max Temp ? 230 Bit Grade- 1-2-CT-S-I-NO-TD Number of Stalls ? No Stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected ? No Comments ?Drilled entire intermediat at reduced GPMs due to 1 pump being down. ROP was not as expected due to flow rate and agitator not working as it should.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Well: |  | Borgstedt 2H
|  |  |  | Longitude: |  | 96° 44' 37.015" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 142.00/210.77/262.00
Date In: |  | 08/06/2021 23:00 |  | SN: |  | PPM250011 |  |  |  | WOB Rotate (klbs): |  | 36.00
Date Out: |  | 08/11/2021 08:50 |  | Description: |  | 6/7 8.8 2.12 HS 88 .025 Slick |  |  |  | WOB Slide (klbs): |  | 36.22
Depth In/Out(Usft): |  | 9906.00 / 17489.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 79.52
Inc In/Out: |  | 15.37 / 87.23 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 370.18
Azi In/Out: |  | 150.81 / 138.99 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3948.55
Total Drilled (Usft): |  | 7583 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4839.1
%Slide (Ftg): |  | 21.61 |  | Bit to Bend (Usft): |  | 4.01 |  |  |  | Tq On Btm (kftlbs): |  | 19264.42
%Slide (Time): |  | 49.20 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1639 |  | Bearing Gap (in): |  | 0.3 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 28.53 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 78.39 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 50.79 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 5944 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 29.45 |  | Length (Usft): |  | 33.16 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 57.98 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 21.12 / 105.83 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 57.45 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 2-2-BT-S-X-I-CT-BHA
Rot ROP (Usft/hr): |  | 201.83 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Plus) / 0.025 |  |  |  | Drill Hrs: |  | 57.98
Avg ROP (Usft/hr): |  | 130.79 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 21.12
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
33 / 21 | 18 / 11 | 6 / 4 |  | 67:33 |  | 12 | 9 | 9.4 | 270666 | OBM | 7.2 |  | 262
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 56 | [10 empty] | 0.00 / 10.95
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618580 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 HS 88 .025 Slick 0.00 |  |  |  | PPM250011 |  | 5 | 2 |  |  |  | 33.16 | 33.91
BTI 0.00 |  |  |  | 41015 |  | 4.812 | 2.062 |  |  |  | 1.65 | 35.56
5" Non Mag Pony Collar 0.00 |  |  |  | SD56927 |  | 4.938 | 2.688 |  |  |  | 10.04 | 45.6
UBHO 0.00 |  |  |  | ZSB500043 |  | 5.188 | 2.5 |  |  |  | 4 | 49.6
5" Non Mag Drill Collar 0.00 |  |  |  | SD56772 |  | 5 | 2.688 |  |  |  | 29.91 | 79.51
5" Non Mag Drill Collar 0.00 |  |  |  | SD56709 |  | 5 | 2.688 |  |  |  | 29.96 | 109.47
Tomax 0.00 |  |  |  | A521239 |  | 5 | 2.625 |  |  |  | 17.92 | 127.39
X/O- XT39P x CET43B 0.00 |  |  |  | SD119787 |  | 5.5 | 2.625 |  |  |  | 3.67 | 131.06
2 Stands Drill Pipe 0.00 |  |  |  | Rig-4 |  | 4.5 | 2.5 |  |  |  | 188.77 | 319.83
Reamer 0.00 |  |  |  | DTI-DNR-521 |  | 5.312 | 2.562 |  |  |  | 8.64 | 328.47
26 Stands Drill Pipe 0.00 |  |  |  | Rig-5 |  | 4.5 | 2.5 |  |  |  | 2453.38 | 2781.85
Agitator 0.00 |  |  |  | PG525-0037 |  | 5.25 | 2.625 |  |  |  | 20.9 | 2802.75
33 Stands Drill Pipe 0.00 |  |  |  | Rig-6 |  | 4.5 | 2.5 |  |  |  | 3114.93 | 5917.68
Agitator / Ball Drop 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.5 |  |  |  | 21.44 | 5939.12
-1.00 | [11 empty] | 5939.12
Additional Comments
Did motor drain ? NO Visual Wear ? Mandrel spun freely by hand. No other visual signs of damage to motor Build/Drop Tendency and Magnitude ? BHA was ran in to build curve and and continue on into lateral until TD. Unfortunately we made it 603? from TD. In curve, motor yields averaged 12? - 15?. Once landed, motor yields average anywhere between 6? - 19?. Max Temp ? 271?- Lost returns @ 14,242? and went on fresh water from then on Bit Grade - 2-2-BT-S-X-I-CT-BHA Number of Stalls ? 0 Reaming ? No Back Reaming - Yes Back ream out of hole F/17489? T/ 14,242 Jarring - No Mud Sample Collected ? No Comments ? BHA performed as expected. @ 17,455?, we put in a 30? slide, slide went well, nothing out of ordinary. After slide we did our normal protocal when picking up out of slide. Which is break over, keep RPM?s @ 45 until get bit to bend buried then go back to max RPM. But after breaking over and attempting to get back to bottom, it would just stack weight without drilling off. Off bottom torque originally was 14-16k. When the above took place, off bottom torque was reading 22-24k. Decision was made by Magnolia to POOH to inspect BHA. Once we got out of hole, motor did not drain, mandrel spun freely by hand. Bit graded 2-2. With chipped cutters on shoulder.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1124821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31158 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 10' 55.352" N |  |  | Well: |  | Borgstedt 2H
|  |  |  | Longitude: |  | 96° 44' 37.015" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 285 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Bobby Guin
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 172.00/195.45/198.00
Date In: |  | 08/11/2021 09:50 |  | SN: |  | PPM250006 |  |  |  | WOB Rotate (klbs): |  | 18.00
Date Out: |  | 08/12/2021 18:10 |  | Description: |  | 6/7 8.8 2.12 HS 88 .002 Slick |  |  |  | WOB Slide (klbs): |  | 18.50
Depth In/Out(Usft): |  | 17489.00 / 18092.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 87.23 / 88.52 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 375
Azi In/Out: |  | 138.99 / 140.28 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4778.18
Total Drilled (Usft): |  | 603 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5647.27
%Slide (Ftg): |  | 5.80 |  | Bit to Bend (Usft): |  | 4.03 |  |  |  | Tq On Btm (kftlbs): |  | 25
%Slide (Time): |  | 31.06 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 35 |  | Bearing Gap (in): |  | 0.25 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 1.47 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 94.20 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 68.87 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 568 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 6.75
Rotary Hours: |  | 3.26 |  | Length (Usft): |  | 33.04 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 4.73 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 5.98 / 32.33 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 23.81 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-RR-X-I-RR-TD
Rot ROP (Usft/hr): |  | 174.23 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Plus) / 0.002 |  |  |  | Drill Hrs: |  | 4.73
Avg ROP (Usft/hr): |  | 127.48 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 5.98
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
5 / 4 | 3 / 2 | 1 / 1 |  | 0 |  | 1 | 3 | 8.4 | 3500 | WBM | 2.6 |  | 198
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 56 | [10 empty] | 0.00 / 0.34
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13601237 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 HS 88 .002 Slick 0.00 |  |  |  | PPM250006 |  | 5.25 | 2 |  |  |  | 33.04 | 33.79
BTI 0.00 |  |  |  | 41015 |  | 4.875 | 2.188 |  |  |  | 1.65 | 35.44
5" Non Mag Pony Collar 0.00 |  |  |  | SD56927 |  | 4.938 | 2.688 |  |  |  | 10.04 | 45.48
UBHO 0.00 |  |  |  | ZSB500043 |  | 5.188 | 2.5 |  |  |  | 4 | 49.48
5" Non Mag Drill Collar 0.00 |  |  |  | SD56772 |  | 5 | 2.688 |  |  |  | 29.91 | 79.39
5" Non Mag Drill Collar 0.00 |  |  |  | SD56709 |  | 5 | 2.688 |  |  |  | 29.96 | 109.35
Tomax 0.00 |  |  |  | A521239 |  | 5 | 2.625 |  |  |  | 17.92 | 127.27
X/O- XT39P x CET43B 0.00 |  |  |  | SD119787 |  | 5.5 | 2.625 |  |  |  | 3.67 | 130.94
2 Stands Drill Pipe 0.00 |  |  |  | Rig-4 |  | 4.5 | 2.5 |  |  |  | 188.77 | 319.71
Reamer 0.00 |  |  |  | DTI-DNR-521 |  | 5.312 | 2.562 |  |  |  | 8.64 | 328.35
26 Stands Drill Pipe 0.00 |  |  |  | Rig-5 |  | 4.5 | 2.5 |  |  |  | 2453.38 | 2781.73
Agitator 0.00 |  |  |  | PG525-0037 |  | 5.25 | 2.625 |  |  |  | 20.9 | 2802.63
0.00 | [11 empty] | 2802.63
Additional Comments
Did motor drain ? Yes Visual Wear ? No wear or damage to motor. Max Temp ? 198 Bit Grade - 1-1-RR-X-I-RR-TD Number of Stalls ? 0 Reaming ? No Back Reaming ? Back ream out of hole F/18092? T/14029? Jarring - No Mud Sample Collected ? No Comments ? TD well @ 18092?
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2624
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 179
Well Name: |  |  |  |  | Borgstedt 2H |  |  | Survey / Gamma Offset: |  |  |  |  | 73.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.66 |  | Rotate: |  | 2445
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/22/2021 | 15:30 | 15:45 | 0.25 | 108 | 208 | 100 | Rotate |  | 135 | 0.2 | 115.2 | 135 | -0.1 | 0.21 | -0.1 | 0.15 |  |  | 5 | 40 | 416 | 1700 | 400 | 215 | 200 | 15 | 95 | 60 | 60 | 60
06/22/2021 | 15:50 | 15:59 | 0.15 | 208 | 299 | 91 | Rotate |  | 226 | 0.2 | 130.5 | 226 | -0.27 | 0.48 | -0.27 | 0.06 |  |  | 5 | 70 | 544 | 1700 | 606.67 | 900 | 700 | 200 | 95 | 60 | 60 | 60
06/22/2021 | 16:05 | 16:11 | 0.1 | 299 | 389 | 90 | Rotate |  | 316 | 0.5 | 93.3 | 316 | -0.4 | 0.99 | -0.4 | 0.4 |  |  | 5 | 90 | 750 | 2700 | 900 | 1450 | 1120 | 330 | 95 | 60 | 60 | 60
06/22/2021 | 16:14 | 16:20 | 0.1 | 389 | 482 | 93 | Rotate |  | 409 | 0.6 | 83.9 | 408.99 | -0.37 | 1.88 | -0.37 | 0.14 |  |  | 10 | 100 | 900 | 4500 | 930 | 1900 | 1700 | 200 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:23 | 16:28 | 0.083333 | 482 | 576 | 94 | Rotate |  | 503 | 0.7 | 83.4 | 502.99 | -0.25 | 2.94 | -0.25 | 0.11 |  |  | 10 | 100 | 900 | 4500 | 1128 | 1900 | 1700 | 200 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:31 | 16:32 | 0.016667 | 576 | 585 | 9 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 540 | 1900 | 1700 | 200 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:32 | 16:36 | 0.066667 | 585 | 595 | 10 | Slide | TTF: 270; Drilling Parameters WOB: 3; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 1750 | 1700 | 50 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:36 | 16:39 | 0.05 | 595 | 670 | 75 | Rotate |  | 597 | 0.1 | 10.2 | 596.98 | -0.1 | 3.52 | -0.1 | 0.72 |  |  | 10 | 100 | 900 | 4500 | 1500 | 1900 | 1700 | 200 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:42 | 16:46 | 0.066667 | 670 | 764 | 94 | Rotate |  | 691 | 0.4 | 292.5 | 690.98 | 0.1 | 3.23 | 0.1 | 0.42 |  |  | 10 | 100 | 900 | 4500 | 1410 | 1900 | 1700 | 200 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:49 | 16:53 | 0.066667 | 764 | 858 | 94 | Rotate |  | 785 | 0.6 | 293.9 | 784.98 | 0.43 | 2.48 | 0.43 | 0.21 |  |  | 10 | 100 | 900 | 4500 | 1410 | 1900 | 1700 | 200 | 96.8 | 60 | 60 | 60
06/22/2021 | 16:56 | 17:00 | 0.066667 | 858 | 951 | 93 | Rotate |  | 878 | 0.6 | 291.3 | 877.98 | 0.8 | 1.58 | 0.8 | 0.03 |  |  | 15 | 100 | 900 | 6500 | 1395 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:03 | 17:04 | 0.016667 | 951 | 960 | 9 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 540 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:04 | 17:08 | 0.066667 | 960 | 970 | 10 | Slide | TTF: 325; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 1750 | 1700 | 50 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:08 | 17:12 | 0.066667 | 970 | 1045 | 75 | Rotate |  | 972 | 0.9 | 301.2 | 971.97 | 1.36 | 0.49 | 1.36 | 0.35 |  |  | 15 | 100 | 900 | 6500 | 1125 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:15 | 17:17 | 0.033333 | 1045 | 1055 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 300 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:17 | 17:20 | 0.05 | 1055 | 1065 | 10 | Slide | TTF: 325; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 200 | 1750 | 1700 | 50 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:20 | 17:24 | 0.066667 | 1065 | 1139 | 74 | Rotate |  | 1066 | 1.8 | 313.5 | 1065.94 | 2.76 | -1.21 | 2.76 | 1 |  |  | 15 | 100 | 900 | 6500 | 1110 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:27 | 17:34 | 0.11667 | 1139 | 1233 | 94 | Rotate |  | 1160 | 2.1 | 318.8 | 1159.89 | 5.08 | -3.42 | 5.08 | 0.37 |  |  | 15 | 100 | 900 | 6500 | 805.71 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:38 | 17:41 | 0.05 | 1233 | 1327 | 94 | Rotate |  | 1254 | 2.2 | 315.4 | 1253.82 | 7.66 | -5.82 | 7.66 | 0.17 |  |  | 15 | 100 | 900 | 6500 | 1880 | 1900 | 1700 | 200 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:44 | 17:45 | 0.016667 | 1327 | 1335 | 8 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 480 | 1750 | 1700 | 50 | 96.8 | 75 | 70 | 65
06/22/2021 | 17:45 | 17:49 | 0.066667 | 1335 | 1347 | 12 | Slide | TTF: 325; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 1750 | 1700 | 50 | 96.8 | 120 | 110 | 100
06/22/2021 | 17:49 | 17:53 | 0.066667 | 1347 | 1419 | 72 | Rotate |  | 1348 | 2.4 | 318.4 | 1347.74 | 10.41 | -8.39 | 10.41 | 0.25 |  |  | 4 | 100 | 900 | 6500 | 1080 | 1750 | 1700 | 50 | 96.8 | 120 | 110 | 100
06/22/2021 | 17:55 | 17:57 | 0.033333 | 1419 | 1430 | 11 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 330 | 1750 | 1700 | 50 | 96.8 | 120 | 110 | 100
06/22/2021 | 17:57 | 18:02 | 0.083333 | 1430 | 1443 | 13 | Slide | 325 | 1442 | 3.1 | 323.7 | 1441.64 | 13.93 | -11.2 | 13.93 | 0.79 |  |  | 4 |  | 900 |  | 156 | 1750 | 1700 | 50 | 96.8 | 120 | 110 | 100
06/22/2021 | 18:02 | 18:07 | 0.083333 | 1443 | 1513 | 70 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 840 | 1750 | 1700 | 50 | 96.8 | 120 | 110 | 100
06/22/2021 | 18:11 | 18:14 | 0.05 | 1513 | 1523 | 10 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 200 | 1750 | 1700 | 50 | 96.8 | 120 | 110 | 100
06/22/2021 | 18:14 | 18:22 | 0.13333 | 1523 | 1537 | 14 | Slide | 330 | 1536 | 3.8 | 323.1 | 1535.46 | 18.47 | -14.58 | 18.47 | 0.75 |  |  | 4 |  | 900 |  | 105 | 1750 | 1700 | 50 | 100 | 120 | 110 | 100
06/22/2021 | 18:22 | 18:28 | 0.1 | 1537 | 1607 | 70 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 700 | 1750 | 1700 | 50 | 100 | 120 | 110 | 100
06/22/2021 | 18:30 | 18:33 | 0.05 | 1607 | 1617 | 10 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 200 | 1750 | 1700 | 50 | 100 | 120 | 110 | 100
06/22/2021 | 18:33 | 18:40 | 0.11667 | 1617 | 1631 | 14 | Slide | 330 | 1629 | 4.8 | 322.4 | 1628.2 | 24.02 | -18.8 | 24.02 | 1.08 |  |  | 4 |  | 900 |  | 120 | 1750 | 1700 | 50 | 100 | 120 | 110 | 100
06/22/2021 | 18:40 | 18:44 | 0.066667 | 1631 | 1700 | 69 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 1035 | 1750 | 1700 | 50 | 100 | 120 | 110 | 100
06/22/2021 | 19:16 | 19:21 | 0.083333 | 1700 | 1714 | 14 | Slide | TTF: 330; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 168 | 1750 | 1700 | 50 | 100 | 120 | 110 | 100
06/22/2021 | 19:21 | 19:26 | 0.083333 | 1714 | 1794 | 80 | Rotate |  | 1723 | 6 | 324.1 | 1721.78 | 31.11 | -24.08 | 31.11 | 1.29 |  |  | 4 | 100 | 900 | 7500 | 960 | 1750 | 1700 | 50 | 105 | 120 | 110 | 100
06/22/2021 | 19:28 | 19:32 | 0.066667 | 1794 | 1804 | 10 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 150 | 1750 | 1700 | 50 | 105 | 120 | 110 | 100
06/22/2021 | 19:32 | 19:38 | 0.1 | 1804 | 1817 | 13 | Slide | TTF: 30; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 130 | 1750 | 1700 | 50 | 105 | 120 | 110 | 100
06/22/2021 | 19:38 | 19:41 | 0.05 | 1817 | 1888 | 71 | Rotate |  | 1817 | 6.9 | 323.3 | 1815.19 | 39.62 | -30.34 | 39.62 | 0.96 |  |  | 4 | 100 | 900 | 7500 | 1420 | 2120 | 1820 | 300 | 105 | 120 | 110 | 100
06/22/2021 | 19:45 | 19:49 | 0.066667 | 1888 | 1898 | 10 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 150 | 2120 | 1820 | 300 | 105 | 120 | 110 | 100
06/22/2021 | 19:49 | 19:53 | 0.066667 | 1898 | 1911 | 13 | Slide | TTF: 20; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 195 | 2050 | 1820 | 230 | 105 | 120 | 110 | 100
06/22/2021 | 19:53 | 20:00 | 0.11667 | 1911 | 1982 | 71 | Rotate |  | 1911 | 7.6 | 327.5 | 1908.43 | 49.39 | -37.05 | 49.39 | 0.93 |  |  | 4 | 100 | 900 | 7500 | 608.57 | 2120 | 1820 | 300 | 110 | 120 | 110 | 100
06/22/2021 | 20:02 | 20:03 | 0.016667 | 1982 | 1992 | 10 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 600 | 2120 | 1820 | 300 | 110 | 120 | 110 | 100
06/22/2021 | 20:09 | 20:13 | 0.066667 | 1992 | 2006 | 14 | Slide | 20 | 2005 | 8.2 | 328.2 | 2001.54 | 60.33 | -43.92 | 60.33 | 0.65 |  |  | 4 |  | 900 |  | 210 | 2050 | 1820 | 230 | 110 | 120 | 110 | 100
06/22/2021 | 20:13 | 20:17 | 0.066667 | 2006 | 2076 | 70 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 1050 | 2120 | 1820 | 300 | 110 | 120 | 110 | 100
06/22/2021 | 20:20 | 20:23 | 0.05 | 2076 | 2086 | 10 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 200 | 2120 | 1820 | 300 | 110 | 120 | 110 | 100
06/22/2021 | 20:23 | 20:27 | 0.066667 | 2086 | 2100 | 14 | Slide | 0 | 2099 | 9 | 327 | 2094.48 | 72.2 | -51.46 | 72.2 | 0.87 |  |  | 4 |  | 900 |  | 210 | 2050 | 1820 | 230 | 110 | 120 | 110 | 100
06/22/2021 | 20:27 | 20:33 | 0.1 | 2100 | 2169 | 69 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 690 | 2120 | 1820 | 300 | 110 | 120 | 110 | 100
06/22/2021 | 20:34 | 20:37 | 0.05 | 2169 | 2180 | 11 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 220 | 2120 | 1820 | 300 | 110 | 120 | 110 | 100
06/22/2021 | 20:37 | 20:42 | 0.083333 | 2180 | 2194 | 14 | Slide | 0 | 2193 | 9.8 | 326.4 | 2187.22 | 85.03 | -59.89 | 85.03 | 0.86 |  |  | 4 |  | 900 |  | 168 | 2050 | 1820 | 230 | 118 | 120 | 110 | 100
06/22/2021 | 20:42 | 20:47 | 0.083333 | 2194 | 2264 | 70 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 840 | 2340 | 1950 | 390 | 118 | 120 | 110 | 100
06/22/2021 | 20:49 | 20:53 | 0.066667 | 2264 | 2281 | 17 | Rotate | Drilling Parameters WOB: 4; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 255 | 2340 | 1950 | 390 | 118 | 120 | 110 | 100
06/22/2021 | 20:53 | 20:58 | 0.083333 | 2281 | 2295 | 14 | Slide | 0 | 2287 | 10.9 | 326.3 | 2279.69 | 99.08 | -69.25 | 99.08 | 1.17 |  |  | 4 |  | 900 |  | 168 | 2050 | 1950 | 100 | 118 | 120 | 110 | 100
06/22/2021 | 20:58 | 21:02 | 0.066667 | 2295 | 2358 | 63 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 945 | 2612 | 2181 | 431 | 118 | 120 | 110 | 100
06/22/2021 | 21:04 | 21:12 | 0.13333 | 2358 | 2451 | 93 | Rotate |  | 2381 | 11.4 | 324.9 | 2371.92 | 114.08 | -79.52 | 114.08 | 0.6 |  |  | 5 | 100 | 900 | 7500 | 697.5 | 2612 | 2181 | 431 | 118 | 120 | 110 | 100
06/22/2021 | 21:14 | 21:22 | 0.13333 | 2451 | 2545 | 94 | Rotate |  | 2475 | 11.6 | 323.8 | 2464.03 | 129.3 | -90.45 | 129.3 | 0.32 |  |  | 4 | 100 | 900 | 7500 | 705 | 2612 | 2181 | 431 | 118 | 120 | 110 | 100
06/22/2021 | 21:24 | 21:33 | 0.15 | 2545 | 2639 | 94 | Rotate |  | 2569 | 11.2 | 322.5 | 2556.17 | 144.17 | -101.59 | 144.17 | 0.51 |  |  | 4 | 100 | 900 | 7500 | 626.67 | 2612 | 2181 | 431 | 118 | 120 | 110 | 100
06/22/2021 | 21:35 | 21:45 | 0.16667 | 2639 | 2732 | 93 | Rotate |  | 2659 | 11.1 | 320.2 | 2644.48 | 157.76 | -112.45 | 157.76 | 0.51 |  |  | 4 | 100 | 900 | 7500 | 558 | 2612 | 2181 | 431 | 118 | 120 | 110 | 100

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7174
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 494
Well Name: |  |  |  |  | Borgstedt 2H |  |  | Survey / Gamma Offset: |  |  |  |  | 70.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.66 |  | Rotate: |  | 6680
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/01/2021 | 14:51 | 14:54 | 0.05 | 2732 | 2742 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 430; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 200 | 900 | 790 | 110 | 129 | 150 | 135 | 120
07/01/2021 | 15:54 | 16:14 | 0.33333 | 2742 | 2847 | 105 | Rotate |  | 2777 | 10.78 | 320.94 | 2760.33 | 175.06 | -126.68 | 175.06 | 0.3 |  |  | 20 | 80 | 700 | 6500 | 315 | 3500 | 2720 | 780 | 129 | 150 | 135 | 120
07/01/2021 | 16:19 | 16:24 | 0.083333 | 2847 | 2941 | 94 | Rotate |  | 2871 | 10.59 | 320.95 | 2852.7 | 188.59 | -137.66 | 188.59 | 0.2 |  |  | 32 | 80 | 900 | 7000 | 1128 | 5000 | 4200 | 800 | 129 | 150 | 135 | 120
07/01/2021 | 16:29 | 16:44 | 0.25 | 2941 | 3035 | 94 | Rotate |  | 2965 | 10.62 | 320.15 | 2945.1 | 201.95 | -148.65 | 201.95 | 0.16 |  |  | 32 | 80 | 900 | 7000 | 376 | 5000 | 4200 | 800 | 129 | 150 | 135 | 120
07/01/2021 | 21:30 | 22:54 | 1.4 | 3035 | 3420 | 385 | Rotate |  | 3058 | 11 | 318.52 | 3036.45 | 215.18 | -160.02 | 215.18 | 0.52 |  |  | 37 | 80 | 686 | 1000 | 275 | 3450 | 2650 | 800 | 134 | 150 | 135 | 120
07/01/2021 | 22:54 | 22:59 | 0.083333 | 3420 | 3430 | 10 | Slide | TTF: 135; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 120 | 3150 | 2650 | 500 | 134 | 150 | 135 | 120
07/01/2021 | 22:59 | 23:38 | 0.65 | 3430 | 3601 | 171 | Rotate |  | 3433 | 10.94 | 319.88 | 3404.27 | 268.42 | -209.94 | 268.42 | 0.93 |  |  | 40 | 80 | 686 | 12000 | 263.08 | 3350 | 2650 | 700 | 134 | 150 | 135 | 120
07/01/2021 | 23:38 | 23:50 | 0.2 | 3601 | 3608 | 7 | Slide | TTF: 90; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 35 | 3150 | 2650 | 500 | 134 | 150 | 135 | 120
07/01/2021 | 23:50 | 24:00 | 0.16667 | 3608 | 3680 | 72 | Rotate |  | 3621 | 11.09 | 323.65 | 3588.96 | 295.49 | -232.3 | 295.49 | 1.1 |  |  | 40 | 80 | 686 | 12000 | 432 | 3350 | 2650 | 700 | 134 | 150 | 135 | 120
07/02/2021 | 00:00 | 01:38 | 1.6333 | 3680 | 4170 | 490 | Rotate |  | 3715 | 11.2 | 324.6 | 3681.19 | 310.21 | -242.95 | 310.21 | 0.23 |  |  | 47 | 80 | 686 | 15000 | 300 | 3370 | 2650 | 720 | 152 | 150 | 135 | 120
07/02/2021 | 01:38 | 01:45 | 0.11667 | 4170 | 4178 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 68.57 | 3150 | 2650 | 500 | 152 | 150 | 135 | 120
07/02/2021 | 01:45 | 04:27 | 2.7 | 4178 | 5115 | 937 | Rotate |  | 4187 | 10.13 | 326.55 | 4144.85 | 382.18 | -294.09 | 382.18 | 0.9 |  |  | 47 | 80 | 686 | 17000 | 347.04 | 3450 | 2650 | 800 | 165 | 155 | 135 | 120
07/02/2021 | 04:27 | 04:30 | 0.05 | 5115 | 5125 | 10 | Slide | TTF: 60; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 200 | 3250 | 3023 | 227 | 152 | 155 | 135 | 120
07/02/2021 | 04:30 | 05:21 | 0.85 | 5125 | 5396 | 271 | Rotate |  | 5128 | 10.18 | 324.4 | 5072.21 | 510.45 | -388.72 | 510.45 | 1.61 |  |  | 40 | 80 | 686 | 22000 | 318.82 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 05:21 | 05:29 | 0.13333 | 5396 | 5404 | 8 | Slide | TTF: 160; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 60 | 3700 | 3300 | 400 | 168 | 200 | 170 | 130
07/02/2021 | 05:29 | 05:41 | 0.2 | 5404 | 5481 | 77 | Rotate |  | 5411 | 10.6 | 325.74 | 5350.18 | 553.68 | -419.59 | 553.68 | 0.78 |  |  | 40 | 80 | 686 | 22000 | 385 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 05:46 | 05:57 | 0.18333 | 5481 | 5576 | 95 | Rotate |  | 5506 | 10.06 | 325.18 | 5443.64 | 567.72 | -429.24 | 567.72 | 0.58 |  |  | 40 | 80 | 686 | 22000 | 518.18 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 06:03 | 06:17 | 0.23333 | 5576 | 5670 | 94 | Rotate |  | 5600 | 10.4 | 324.81 | 5536.14 | 581.39 | -438.82 | 581.39 | 0.37 |  |  | 40 | 80 | 686 | 22000 | 402.86 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 06:22 | 06:54 | 0.53333 | 5670 | 5858 | 188 | Rotate |  | 5694 | 10.52 | 324.11 | 5628.58 | 595.28 | -448.74 | 595.28 | 0.19 |  |  | 40 | 80 | 686 | 22000 | 352.5 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 07:00 | 07:13 | 0.21667 | 5858 | 5951 | 93 | Rotate |  | 5881 | 9.47 | 323.91 | 5812.69 | 621.74 | -467.99 | 621.74 | 0.74 |  |  | 40 | 80 | 686 | 22000 | 429.23 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 07:18 | 07:30 | 0.2 | 5951 | 6046 | 95 | Rotate |  | 5976 | 9.22 | 322.82 | 5906.43 | 634.12 | -477.19 | 634.12 | 0.32 |  |  | 40 | 80 | 686 | 22000 | 475 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 07:35 | 07:47 | 0.2 | 6046 | 6111 | 65 | Rotate |  | 6069 | 9.53 | 322.12 | 5998.19 | 646.13 | -486.42 | 646.13 | 0.36 |  |  | 40 | 80 | 686 | 22000 | 325 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 09:49 | 09:54 | 0.083333 | 6111 | 6139 | 28 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 336 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 10:00 | 10:11 | 0.18333 | 6139 | 6233 | 94 | Rotate |  | 6163 | 9.46 | 322.46 | 6090.9 | 658.4 | -495.91 | 658.4 | 0.1 |  |  | 40 | 80 | 686 | 22000 | 512.73 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 10:15 | 10:34 | 0.31667 | 6233 | 6328 | 95 | Rotate |  | 6258 | 9.35 | 320.2 | 6184.62 | 670.52 | -505.6 | 670.52 | 0.41 |  |  | 40 | 80 | 686 | 22000 | 300 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 10:44 | 10:49 | 0.083333 | 6328 | 6340 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 144 | 4100 | 3300 | 800 | 168 | 200 | 170 | 130
07/02/2021 | 10:49 | 11:00 | 0.18333 | 6340 | 6355 | 15 | Slide | 140 | 6352 | 8.79 | 323.9 | 6277.45 | 682.19 | -514.72 | 682.19 | 0.86 |  |  | 15 |  | 686 |  | 81.82 | 3600 | 3300 | 300 | 177 | 200 | 170 | 130
07/02/2021 | 11:00 | 11:12 | 0.2 | 6355 | 6422 | 67 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 335 | 4100 | 3300 | 800 | 177 | 200 | 170 | 130
07/02/2021 | 11:17 | 11:19 | 0.033333 | 6422 | 6435 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 390 | 4100 | 3300 | 800 | 177 | 200 | 170 | 130
07/02/2021 | 11:19 | 11:29 | 0.16667 | 6435 | 6450 | 15 | Slide | 140 | 6446 | 7.16 | 319.57 | 6370.54 | 692.45 | -522.75 | 692.45 | 1.85 |  |  | 15 |  | 686 |  | 90 | 3600 | 3300 | 300 | 177 | 200 | 170 | 130
07/02/2021 | 11:29 | 11:39 | 0.16667 | 6450 | 6516 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 396 | 3900 | 3300 | 600 | 177 | 210 | 190 | 170
07/02/2021 | 11:45 | 12:00 | 0.25 | 6516 | 6610 | 94 | Rotate |  | 6540 | 6.63 | 317.8 | 6463.86 | 700.93 | -530.2 | 700.93 | 0.61 |  |  | 40 | 80 | 686 | 22000 | 376 | 3900 | 3300 | 600 | 177 | 210 | 190 | 170
07/02/2021 | 12:05 | 12:19 | 0.23333 | 6610 | 6704 | 94 | Rotate |  | 6634 | 6.42 | 315.72 | 6557.25 | 708.71 | -537.51 | 708.71 | 0.34 |  |  | 40 | 80 | 686 | 22000 | 402.86 | 3900 | 3300 | 600 | 177 | 210 | 190 | 170
07/02/2021 | 12:25 | 12:28 | 0.05 | 6704 | 6715 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 220 | 3900 | 3300 | 600 | 177 | 210 | 190 | 170
07/02/2021 | 12:28 | 12:36 | 0.13333 | 6715 | 6730 | 15 | Slide | 130 | 6728 | 6.05 | 330.51 | 6650.7 | 716.79 | -543.62 | 716.79 | 1.75 |  |  | 40 |  | 686 |  | 112.5 | 3600 | 3300 | 300 | 188 | 200 | 170 | 130
07/02/2021 | 12:36 | 13:09 | 0.55 | 6730 | 6892 | 162 | Rotate |  | 6822 | 5.78 | 333.87 | 6744.2 | 725.35 | -548.14 | 725.35 | 0.47 |  |  | 40 | 80 | 686 | 22000 | 294.55 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 13:15 | 13:28 | 0.21667 | 6892 | 6985 | 93 | Rotate |  | 6915 | 5.54 | 331.22 | 6836.75 | 733.49 | -552.37 | 733.49 | 0.38 |  |  | 40 | 80 | 686 | 22000 | 429.23 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 13:33 | 13:36 | 0.05 | 6985 | 6995 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 200 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 13:36 | 13:47 | 0.18333 | 6995 | 7010 | 15 | Slide | 180 | 7009 | 4.29 | 338.64 | 6930.4 | 740.74 | -555.83 | 740.74 | 1.49 |  |  | 15 |  | 686 |  | 81.82 | 3600 | 3300 | 300 | 188 | 200 | 170 | 130
07/02/2021 | 13:47 | 14:00 | 0.21667 | 7010 | 7079 | 69 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 318.46 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 14:05 | 14:23 | 0.3 | 7079 | 7173 | 94 | Rotate |  | 7103 | 4.15 | 341.24 | 7024.14 | 747.24 | -558.21 | 747.24 | 0.25 |  |  | 40 | 80 | 686 | 22000 | 313.33 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 14:29 | 14:46 | 0.28333 | 7173 | 7267 | 94 | Rotate |  | 7197 | 3.84 | 336.77 | 7117.92 | 753.35 | -560.54 | 753.35 | 0.47 |  |  | 40 | 80 | 686 | 22000 | 331.76 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 14:51 | 15:10 | 0.31667 | 7267 | 7360 | 93 | Rotate |  | 7290 | 3.9 | 327.38 | 7210.71 | 758.88 | -563.47 | 758.88 | 0.68 |  |  | 40 | 80 | 686 | 22000 | 293.68 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 15:15 | 15:18 | 0.05 | 7360 | 7370 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 200 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 15:18 | 15:35 | 0.28333 | 7370 | 7390 | 20 | Slide | 120 | 7385 | 2.48 | 334.1 | 7305.56 | 763.45 | -566.11 | 763.45 | 1.54 |  |  | 15 |  | 686 |  | 70.59 | 3600 | 3300 | 300 | 188 | 210 | 190 | 170
07/02/2021 | 15:35 | 15:50 | 0.25 | 7390 | 7455 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 686; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 260 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 15:55 | 16:16 | 0.35 | 7455 | 7548 | 93 | Rotate |  | 7478 | 2.02 | 335.64 | 7398.48 | 766.75 | -567.67 | 766.75 | 0.5 |  |  | 40 | 80 | 686 | 22000 | 265.71 | 3900 | 3300 | 600 | 188 | 210 | 190 | 170
07/02/2021 | 16:20 | 16:39 | 0.31667 | 7548 | 7642 | 94 | Rotate |  | 7572 | 2.15 | 336.37 | 7492.42 | 769.87 | -569.06 | 769.87 | 0.14 |  |  | 40 | 80 | 686 | 22000 | 296.84 | 3900 | 3300 | 600 | 203 | 210 | 190 | 170
07/02/2021 | 16:45 | 16:58 | 0.21667 | 7642 | 7736 | 94 | Rotate |  | 7666 | 2.1 | 334.86 | 7586.36 | 773.05 | -570.5 | 773.05 | 0.08 |  |  | 40 | 80 | 686 | 22000 | 433.85 | 3900 | 3300 | 600 | 203 | 210 | 190 | 170
07/02/2021 | 17:03 | 17:23 | 0.33333 | 7736 | 7830 | 94 | Rotate |  | 7760 | 1.88 | 337.05 | 7680.3 | 776.03 | -571.83 | 776.03 | 0.25 |  |  | 40 | 80 | 686 | 22000 | 282 | 3900 | 3300 | 600 | 203 | 210 | 190 | 170
07/02/2021 | 17:28 | 17:45 | 0.28333 | 7830 | 7924 | 94 | Rotate |  | 7854 | 1.67 | 326.74 | 7774.26 | 778.59 | -573.18 | 778.59 | 0.41 |  |  | 40 | 80 | 686 | 22000 | 331.76 | 3900 | 3300 | 600 | 203 | 210 | 190 | 170
07/02/2021 | 17:49 | 18:00 | 0.18333 | 7924 | 8018 | 94 | Rotate |  | 7948 | 1.81 | 323.15 | 7868.21 | 780.93 | -574.82 | 780.93 | 0.19 |  |  | 40 | 80 | 686 | 22000 | 512.73 | 3900 | 3300 | 600 | 203 | 210 | 190 | 170
07/02/2021 | 18:05 | 18:20 | 0.25 | 8018 | 8112 | 94 | Rotate |  | 8042 | 1.97 | 322.66 | 7962.16 | 783.4 | -576.69 | 783.4 | 0.17 |  |  | 40 | 80 | 686 | 22000 | 376 | 3900 | 3300 | 600 | 203 | 210 | 190 | 170
07/02/2021 | 18:30 | 18:36 | 0.1 | 8112 | 8136 | 24 | Rotate |  | 8136 | 1.8 | 326.62 | 8056.11 | 785.92 | -578.49 | 785.92 | 0.23 |  |  | 40 | 80 | 880 | 20000 | 240 | 5600 | 4700 | 900 | 203 | 210 | 190 | 170
07/02/2021 | 18:50 | 19:03 | 0.21667 | 8136 | 8206 | 70 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 323.08 | 5600 | 4700 | 900 | 206 | 210 | 190 | 170
07/02/2021 | 19:06 | 19:12 | 0.1 | 8206 | 8212 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 60 | 5600 | 4700 | 900 | 206 | 210 | 190 | 170
07/02/2021 | 19:12 | 19:34 | 0.36667 | 8212 | 8227 | 15 | Slide | TTF: 160; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 40.91 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 19:34 | 19:44 | 0.16667 | 8227 | 8300 | 73 | Rotate |  | 8230 | 1.38 | 311.19 | 8150.07 | 787.89 | -580.15 | 787.89 | 0.63 |  |  | 40 | 80 | 880 | 20000 | 438 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 19:49 | 19:58 | 0.15 | 8300 | 8394 | 94 | Rotate |  | 8324 | 1.3 | 314.75 | 8244.05 | 789.39 | -581.76 | 789.39 | 0.12 |  |  | 40 | 80 | 880 | 20000 | 626.67 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 20:03 | 20:07 | 0.066667 | 8394 | 8405 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 165 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 20:07 | 20:30 | 0.38333 | 8405 | 8422 | 17 | Slide | 135 | 8417 | 1.27 | 297.67 | 8337.03 | 790.61 | -583.42 | 790.61 | 0.41 |  |  | 40 |  | 880 |  | 44.35 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 20:30 | 20:46 | 0.26667 | 8422 | 8487 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 243.75 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 20:50 | 20:55 | 0.083333 | 8487 | 8502 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 180 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 20:55 | 21:35 | 0.66667 | 8502 | 8522 | 20 | Slide | 135 | 8511 | 0.44 | 136.68 | 8431.02 | 790.83 | -584.1 | 790.83 | 1.8 |  |  | 40 |  | 880 |  | 30 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 21:35 | 21:49 | 0.23333 | 8522 | 8581 | 59 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 252.86 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 21:53 | 21:55 | 0.033333 | 8581 | 8586 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 150 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 22:00 | 22:10 | 0.16667 | 8586 | 8675 | 89 | Rotate |  | 8605 | 1.5 | 119.46 | 8525 | 789.96 | -582.78 | 789.96 | 1.16 |  |  | 40 | 80 | 880 | 22000 | 534 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 22:15 | 22:27 | 0.2 | 8675 | 8769 | 94 | Rotate |  | 8699 | 1.17 | 87.76 | 8618.98 | 789.4 | -580.75 | 789.4 | 0.85 |  |  | 40 | 80 | 880 | 22000 | 470 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 22:32 | 22:45 | 0.21667 | 8769 | 8863 | 94 | Rotate |  | 8793 | 1.95 | 60.05 | 8712.95 | 790.23 | -578.4 | 790.23 | 1.13 |  |  | 40 | 80 | 880 | 22000 | 433.85 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 22:50 | 22:55 | 0.083333 | 8863 | 8892 | 29 | Rotate |  | 8887 | 1.79 | 59.07 | 8806.9 | 791.79 | -575.76 | 791.79 | 0.17 |  |  | 40 | 80 | 880 | 22000 | 348 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 22:55 | 23:40 | 0.75 | 8892 | 8899 | 7 | Slide | TTF: 215; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 9.33 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 23:40 | 23:50 | 0.16667 | 8899 | 8957 | 58 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 348 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/02/2021 | 23:55 | 24:00 | 0.083333 | 8957 | 8966 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 108 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/03/2021 | 00:05 | 00:57 | 0.86667 | 8966 | 8986 | 20 | Slide | 215 | 8980 | 1.11 | 120.58 | 8899.87 | 792.07 | -573.74 | 792.07 | 1.71 |  |  | 40 |  | 880 |  | 23.08 | 5600 | 4700 | 900 | 206 | 220 | 200 | 195
07/03/2021 | 00:57 | 01:10 | 0.21667 | 8986 | 9050 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 295.38 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 01:15 | 01:21 | 0.1 | 9050 | 9086 | 36 | Rotate |  | 9074 | 1.43 | 119.92 | 8993.85 | 791.03 | -571.94 | 791.03 | 0.34 |  |  | 40 | 80 | 880 | 22000 | 360 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 01:25 | 01:34 | 0.15 | 9086 | 9144 | 58 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 386.67 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 01:39 | 01:45 | 0.1 | 9144 | 9153 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 01:45 | 02:24 | 0.65 | 9153 | 9163 | 10 | Slide | TTF: 285; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 15.38 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 02:24 | 02:42 | 0.3 | 9163 | 9238 | 75 | Rotate |  | 9168 | 0.13 | 151.14 | 9087.84 | 790.35 | -570.87 | 790.35 | 1.4 |  |  | 40 | 80 | 880 | 22000 | 250 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 02:47 | 03:03 | 0.26667 | 9238 | 9332 | 94 | Rotate |  | 9262 | 0.28 | 327.35 | 9181.84 | 790.45 | -570.94 | 790.45 | 0.44 |  |  | 40 | 80 | 880 | 22000 | 352.5 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 03:08 | 03:24 | 0.26667 | 9332 | 9426 | 94 | Rotate |  | 9356 | 0.86 | 312.83 | 9275.83 | 791.12 | -571.58 | 791.12 | 0.63 |  |  | 40 | 80 | 880 | 22000 | 352.5 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 03:29 | 03:42 | 0.21667 | 9426 | 9519 | 93 | Rotate |  | 9449 | 1.2 | 308.16 | 9368.82 | 792.2 | -572.86 | 792.2 | 0.38 |  |  | 40 | 80 | 880 | 22000 | 429.23 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 03:42 | 03:55 | 0.21667 | 9519 | 9571 | 52 | Rotate |  | 9543 | 1.69 | 303.68 | 9462.79 | 793.57 | -574.79 | 793.57 | 0.53 |  |  | 40 | 80 | 880 | 22000 | 240 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 03:55 | 06:10 | 2.25 | 9571 | 9613 | 42 | Slide | TTF: 145; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 18.67 | 5600 | 4700 | 900 | 224 | 235 | 210 | 220
07/03/2021 | 06:20 | 14:00 | 7.6667 | 9613 | 9707 | 94 | Slide | 140 | 9637 | 2.21 | 195.41 | 9556.75 | 792.59 | -576.42 | 792.59 | 3.38 |  |  | 15 |  | 686 |  | 12.26 | 3500 | 3200 | 300 | 224 | 270 | 230 | 200
07/03/2021 | 14:10 | 17:46 | 3.6 | 9707 | 9766 | 59 | Slide | 140 | 9731 | 7.98 | 158.1 | 9650.36 | 784.78 | -574.47 | 784.78 | 6.77 |  |  | 15 |  | 686 |  | 16.39 | 3500 | 3200 | 300 | 224 | 270 | 230 | 200
07/03/2021 | 18:00 | 19:50 | 1.8333 | 9766 | 9782 | 16 | Slide | TTF: -35; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 8.73 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/03/2021 | 20:35 | 22:46 | 2.1833 | 9782 | 9801 | 19 | Slide | TTF: -35; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 8.7 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/03/2021 | 22:51 | 24:00 | 1.15 | 9801 | 9810 | 9 | Slide | TTF: -35; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 7.83 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/04/2021 | 00:00 | 01:54 | 1.9 | 9810 | 9826 | 16 | Slide | TTF: -35; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 8.42 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/04/2021 | 02:01 | 02:45 | 0.73333 | 9826 | 9830 | 4 | Slide | TTF: -35; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 880; Drilling Parameters ROP: 5.45 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/04/2021 | 02:53 | 05:00 | 2.1167 | 9830 | 9844 | 14 | Slide | -35 | 9836 | 15.18 | 154.92 | 9753.16 | 765.55 | -565.91 | 765.55 | 6.88 |  |  | 15 |  | 686 |  | 6.61 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/04/2021 | 05:15 | 05:18 | 0.05 | 9844 | 9845 | 1 | Slide | TTF: -35; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 20 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/04/2021 | 06:00 | 06:56 | 0.93333 | 9845 | 9853 | 8 | Slide | TTF: -20; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 686; Drilling Parameters ROP: 8.57 | 3500 | 3200 | 300 | 233.5 | 270 | 230 | 200
07/04/2021 | 06:56 | 07:53 | 0.95 | 9853 | 9906 | 53 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 55.79 | 3900 | 3200 | 700 | 233.5 | 270 | 230 | 200

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7583
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1639
Well Name: |  |  |  |  | Borgstedt 2H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.66 |  | Rotate: |  | 5944
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/07/2021 | 09:20 | 09:23 | 0.05 | 9906 | 9916 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 200; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 200 | 1600 | 3035 | -1435 |  | 215 | 185 | 170
08/07/2021 | 10:54 | 11:51 | 0.95 | 9916 | 10000 | 84 | Slide | -20 | 9931 | 15.45 | 149.38 | 9844.79 | 743.39 | -554.19 | 743.39 | 1.57 |  |  | 28 |  | 350 |  | 88.42 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 12:01 | 13:13 | 1.2 | 10000 | 10094 | 94 | Slide | 0 | 10025 | 20.33 | 132.4 | 9934.28 | 721.58 | -535.73 | 721.58 | 7.55 |  |  | 28 |  | 350 |  | 78.33 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 13:23 | 14:26 | 1.05 | 10094 | 10189 | 95 | Slide | 30 | 10120 | 28.7 | 133.16 | 10020.64 | 694.8 | -506.86 | 694.8 | 8.82 |  |  | 28 |  | 350 |  | 90.48 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 14:36 | 15:31 | 0.91667 | 10189 | 10283 | 94 | Slide | 30 | 10214 | 38.54 | 138.64 | 10098.83 | 657.28 | -470.95 | 657.28 | 10.95 |  |  | 28 |  | 350 |  | 102.55 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 15:40 | 16:36 | 0.93333 | 10283 | 10378 | 95 | Slide | 10 | 10309 | 48.53 | 138.01 | 10167.62 | 608.49 | -427.47 | 608.49 | 10.53 |  |  | 28 |  | 350 |  | 101.79 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 16:46 | 16:54 | 0.13333 | 10378 | 10388 | 10 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 75 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 16:54 | 17:37 | 0.71667 | 10388 | 10472 | 84 | Slide | 10 | 10403 | 57.43 | 140.19 | 10224.16 | 551.77 | -378.45 | 551.77 | 9.65 |  |  | 28 |  | 350 |  | 117.21 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 17:47 | 17:58 | 0.18333 | 10472 | 10502 | 30 | Rotate |  | 10498 | 66.13 | 140.46 | 10269.04 | 487.39 | -325.06 | 487.39 | 9.16 |  |  | 28 |  | 350 |  | 163.64 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 17:58 | 18:44 | 0.76667 | 10502 | 10567 | 65 | Slide | TTF: 20; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 84.78 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 18:55 | 19:35 | 0.66667 | 10567 | 10630 | 63 | Rotate |  | 10592 | 74.72 | 139.79 | 10300.51 | 419.5 | -268.32 | 419.5 | 9.16 |  |  | 28 |  | 350 |  | 94.5 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 19:35 | 19:54 | 0.31667 | 10630 | 10661 | 31 | Slide | TTF: 20; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 97.89 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 20:04 | 20:30 | 0.43333 | 10661 | 10717 | 56 | Rotate |  | 10686 | 78.45 | 138.65 | 10322.31 | 350.28 | -208.61 | 350.28 | 4.14 |  |  | 28 |  | 350 |  | 129.23 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 20:30 | 20:52 | 0.36667 | 10717 | 10755 | 38 | Slide | TTF: 20; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 103.64 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 21:02 | 21:15 | 0.21667 | 10755 | 10776 | 21 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 96.92 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 21:15 | 21:52 | 0.61667 | 10776 | 10835 | 59 | Slide | 20 | 10780 | 85.55 | 137.42 | 10335.38 | 281.12 | -146.4 | 281.12 | 7.66 |  |  | 28 |  | 350 |  | 95.68 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170 | 30 @ 20R 25 @ 90 R
08/07/2021 | 21:52 | 22:05 | 0.21667 | 10835 | 10849 | 14 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 64.62 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 22:08 | 22:28 | 0.33333 | 10849 | 10900 | 51 | Rotate |  | 10875 | 91.81 | 140.92 | 10337.57 | 209.3 | -84.35 | 209.3 | 7.55 |  |  | 28 |  | 350 |  | 153 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 22:38 | 23:00 | 0.36667 | 10900 | 10925 | 25 | Slide | TTF: 140; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 68.18 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 23:00 | 23:08 | 0.13333 | 10925 | 10944 | 19 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 142.5 | 3560 | 3035 | 525 | 222 | 215 | 185 | 170
08/07/2021 | 23:12 | 23:25 | 0.21667 | 10944 | 10994 | 50 | Rotate |  | 10970 | 89.38 | 143.08 | 10336.59 | 134.45 | -25.87 | 134.45 | 3.42 |  |  | 28 | 80 | 350 | 16000 | 230.77 | 4250 | 3035 | 1215 | 222 | 215 | 185 | 170
08/07/2021 | 23:30 | 23:42 | 0.2 | 10994 | 11039 | 45 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 225 | 4250 | 3035 | 1215 | 222 | 215 | 185 | 170
08/08/2021 | 00:25 | 00:38 | 0.21667 | 11039 | 11059 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 92.31 | 4250 | 3035 | 1215 | 222 | 215 | 185 | 170
08/08/2021 | 00:38 | 00:53 | 0.25 | 11059 | 11132 | 73 | Rotate |  | 11063 | 87.55 | 143.78 | 10339.08 | 59.79 | 29.52 | 59.79 | 2.11 |  |  | 28 | 80 | 350 | 16000 | 292 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 00:58 | 01:15 | 0.28333 | 11132 | 11227 | 95 | Rotate |  | 11158 | 87.71 | 145.13 | 10343.01 | -17.44 | 84.7 | -17.44 | 1.43 |  |  | 28 | 80 | 350 | 16000 | 335.29 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 01:18 | 01:26 | 0.13333 | 11227 | 11239 | 12 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 90 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 01:26 | 01:41 | 0.25 | 11239 | 11258 | 19 | Slide | -170 | 11252 | 85.83 | 144.17 | 10348.3 | -93.98 | 138.99 | -93.98 | 2.24 |  |  | 28 |  | 350 | 16000 | 76 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 01:41 | 01:55 | 0.23333 | 11258 | 11321 | 63 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 270 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 02:00 | 02:15 | 0.25 | 11321 | 11415 | 94 | Rotate |  | 11346 | 84.2 | 143.3 | 10356.47 | -169.49 | 194.38 | -169.49 | 1.96 |  |  | 28 | 80 | 350 | 16000 | 376 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 02:18 | 02:25 | 0.11667 | 11415 | 11430 | 15 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 128.57 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 02:25 | 02:43 | 0.3 | 11430 | 11445 | 15 | Slide | 0 | 11441 | 84.99 | 142.28 | 10365.42 | -244.81 | 251.58 | -244.81 | 1.35 |  |  | 28 | 80 | 350 | 16000 | 50 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 02:43 | 02:55 | 0.2 | 11445 | 11510 | 65 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 325 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 03:00 | 03:05 | 0.083333 | 11510 | 11520 | 10 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 120 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 03:05 | 03:15 | 0.16667 | 11520 | 11530 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 60 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 03:15 | 03:32 | 0.28333 | 11530 | 11604 | 74 | Rotate |  | 11535 | 87.76 | 142.01 | 10371.36 | -318.87 | 309.14 | -318.87 | 2.96 |  |  | 28 | 80 | 350 | 16000 | 261.18 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 03:37 | 03:51 | 0.23333 | 11604 | 11699 | 95 | Rotate |  | 11630 | 86.57 | 138.61 | 10376.06 | -391.87 | 369.72 | -391.87 | 3.79 |  |  | 28 | 80 | 350 | 16000 | 407.14 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 03:54 | 03:57 | 0.05 | 11699 | 11704 | 5 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 100 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 04:05 | 04:25 | 0.33333 | 11704 | 11729 | 25 | Slide | 70 | 11726 | 89.9 | 142.78 | 10379.02 | -466.1 | 430.48 | -466.1 | 5.56 |  |  | 28 |  | 350 | 16000 | 75 | 4250 | 3035 | 1215 | 235 | 215 | 185 | 170
08/08/2021 | 04:25 | 04:38 | 0.21667 | 11729 | 11795 | 66 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 304.62 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 04:42 | 05:00 | 0.3 | 11795 | 11889 | 94 | Rotate |  | 11820 | 92.43 | 143.14 | 10377.11 | -541.11 | 487.09 | -541.11 | 2.72 |  |  | 28 | 80 | 350 | 17000 | 313.33 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 05:05 | 05:11 | 0.1 | 11889 | 11898 | 9 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 90 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 05:11 | 05:29 | 0.3 | 11898 | 11928 | 30 | Slide | 180 | 11912 | 93.12 | 143.6 | 10372.65 | -614.85 | 541.92 | -614.85 | 0.9 |  |  | 28 | 80 | 350 | 17000 | 100 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 05:29 | 05:42 | 0.21667 | 11928 | 11981 | 53 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 244.62 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 05:52 | 05:58 | 0.1 | 11981 | 11988 | 7 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 70 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 05:58 | 06:20 | 0.36667 | 11988 | 12018 | 30 | Slide | 180 | 12006 | 89.81 | 144.36 | 10370.25 | -690.84 | 597.17 | -690.84 | 3.61 |  |  | 38 |  | 350 |  | 81.82 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 06:20 | 06:34 | 0.23333 | 12018 | 12075 | 57 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 244.29 | 4250 | 3035 | 1215 | 239 | 220 | 190 | 180
08/08/2021 | 06:44 | 07:00 | 0.26667 | 12075 | 12097 | 22 | Slide | TTF: -140; Drilling Parameters WOB: 38; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 82.5 | 5000 | 4000 | 1000 | 240 | 220 | 190 | 180
08/08/2021 | 07:00 | 07:20 | 0.33333 | 12097 | 12169 | 72 | Rotate |  | 12100 | 85.59 | 143.53 | 10374.02 | -766.76 | 652.43 | -766.76 | 4.58 |  |  | 40 | 80 | 400 | 17000 | 216 | 5100 | 4000 | 1100 | 239 | 220 | 190 | 180
08/08/2021 | 07:30 | 07:43 | 0.21667 | 12169 | 12264 | 95 | Rotate |  | 12195 | 84.34 | 143.54 | 10382.36 | -842.86 | 708.68 | -842.86 | 1.32 |  |  | 40 | 80 | 400 | 17000 | 438.46 | 5100 | 4000 | 1100 | 239 | 220 | 190 | 180
08/08/2021 | 07:53 | 08:08 | 0.25 | 12264 | 12358 | 94 | Rotate |  | 12289 | 83.31 | 142.79 | 10392.47 | -917.66 | 764.7 | -917.66 | 1.35 |  |  | 40 | 80 | 400 | 17000 | 376 | 5100 | 4000 | 1100 | 239 | 220 | 190 | 180
08/08/2021 | 08:18 | 08:23 | 0.083333 | 12358 | 12365 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 84 | 5100 | 4000 | 1100 | 239 | 220 | 190 | 180
08/08/2021 | 08:23 | 08:34 | 0.18333 | 12365 | 12390 | 25 | Slide | 0 | 12383 | 86.03 | 143.54 | 10401.2 | -992.56 | 820.81 | -992.56 | 3 |  |  | 40 |  | 400 |  | 136.36 | 4600 | 4000 | 600 | 239 | 220 | 190 | 180
08/08/2021 | 08:34 | 08:49 | 0.25 | 12390 | 12452 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 248 | 5200 | 4200 | 1000 | 247 | 245 | 190 | 160
08/08/2021 | 08:58 | 09:11 | 0.21667 | 12452 | 12546 | 94 | Rotate |  | 12477 | 87.8 | 143.32 | 10406.26 | -1067.94 | 876.73 | -1067.94 | 1.9 |  |  | 40 | 80 | 400 | 17000 | 433.85 | 5200 | 4200 | 1000 | 247 | 245 | 190 | 160
08/08/2021 | 09:21 | 09:25 | 0.066667 | 12546 | 12556 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 150 | 5200 | 4200 | 1000 | 247 | 245 | 190 | 160
08/08/2021 | 09:25 | 09:31 | 0.1 | 12556 | 12571 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 150 | 4500 | 4200 | 300 | 251 | 245 | 190 | 160
08/08/2021 | 09:31 | 09:48 | 0.28333 | 12571 | 12641 | 70 | Rotate |  | 12572 | 88.69 | 142.73 | 10409.17 | -1143.8 | 933.84 | -1143.8 | 1.12 |  |  | 40 | 80 | 400 | 17000 | 247.06 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 09:58 | 10:00 | 0.033333 | 12641 | 12651 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 300 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 10:00 | 10:18 | 0.3 | 12651 | 12679 | 28 | Slide | 180 | 12666 | 88.31 | 142.72 | 10411.63 | -1218.58 | 990.75 | -1218.58 | 0.4 |  |  | 40 |  | 400 |  | 93.33 | 4500 | 4200 | 300 | 251 | 245 | 190 | 160
08/08/2021 | 10:18 | 10:30 | 0.2 | 12679 | 12735 | 56 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 280 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 10:40 | 10:42 | 0.033333 | 12735 | 12745 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 300 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 10:42 | 10:48 | 0.1 | 12745 | 12757 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 120 | 4500 | 4200 | 300 | 251 | 245 | 190 | 160
08/08/2021 | 10:48 | 11:02 | 0.23333 | 12757 | 12828 | 71 | Rotate |  | 12759 | 86.86 | 143.9 | 10415.55 | -1293.08 | 1046.27 | -1293.08 | 2.01 |  |  | 40 | 80 | 400 | 17000 | 304.29 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 11:09 | 11:12 | 0.05 | 12828 | 12838 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 200 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 11:12 | 11:21 | 0.15 | 12838 | 12850 | 12 | Slide | TTF: -130; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 80 | 4500 | 4200 | 300 | 251 | 245 | 190 | 160
08/08/2021 | 11:21 | 11:35 | 0.23333 | 12850 | 12923 | 73 | Rotate |  | 12854 | 86.82 | 145.12 | 10420.79 | -1370.31 | 1101.33 | -1370.31 | 1.28 |  |  | 40 | 80 | 400 | 17000 | 312.86 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 11:42 | 11:44 | 0.033333 | 12923 | 12933 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 300 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 11:44 | 12:06 | 0.36667 | 12933 | 12963 | 30 | Slide | -120 | 12948 | 85.83 | 144.19 | 10426.81 | -1446.83 | 1155.6 | -1446.83 | 1.44 |  |  | 40 |  | 400 |  | 81.82 | 4500 | 4200 | 300 | 251 | 245 | 190 | 160
08/08/2021 | 12:06 | 12:12 | 0.1 | 12963 | 12986 | 23 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 230 | 5200 | 4200 | 1000 | 251 | 245 | 190 | 160
08/08/2021 | 12:18 | 12:41 | 0.38333 | 12986 | 13006 | 20 | Slide | TTF: -90; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 52.17 | 4500 | 4200 | 300 | 251 | 245 | 190 | 160
08/08/2021 | 12:41 | 12:47 | 0.1 | 13006 | 13017 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 110 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 12:53 | 13:07 | 0.23333 | 13017 | 13112 | 95 | Rotate |  | 13043 | 82.82 | 140.86 | 10436.21 | -1521.84 | 1213.09 | -1521.84 | 4.71 |  |  | 40 | 80 | 400 | 17000 | 407.14 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 13:14 | 13:20 | 0.1 | 13112 | 13118 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 60 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 13:20 | 13:40 | 0.33333 | 13118 | 13146 | 28 | Slide | -20 | 13137 | 84.51 | 140.19 | 10446.58 | -1593.95 | 1272.49 | -1593.95 | 1.93 |  |  | 40 |  | 400 |  | 84 | 4500 | 4200 | 300 | 255 | 245 | 190 | 160
08/08/2021 | 13:40 | 13:54 | 0.23333 | 13146 | 13206 | 60 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 257.14 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 14:01 | 14:15 | 0.23333 | 13206 | 13224 | 18 | Slide | TTF: -20; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 77.14 | 4500 | 4200 | 300 | 255 | 245 | 190 | 160
08/08/2021 | 14:15 | 14:30 | 0.25 | 13224 | 13300 | 76 | Rotate |  | 13231 | 88.43 | 137.8 | 10452.37 | -1664.73 | 1334.03 | -1664.73 | 4.88 |  |  | 40 | 80 | 400 | 17000 | 304 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 14:38 | 14:53 | 0.25 | 13300 | 13395 | 95 | Rotate |  | 13326 | 88.99 | 136.87 | 10454.51 | -1734.57 | 1398.4 | -1734.57 | 1.14 |  |  | 40 | 80 | 400 | 17000 | 380 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 15:00 | 15:04 | 0.066667 | 13395 | 13400 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 75 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 15:04 | 15:27 | 0.38333 | 13400 | 13430 | 30 | Slide | 90 | 13421 | 90.68 | 140.11 | 10454.78 | -1805.7 | 1461.35 | -1805.7 | 3.85 |  |  | 40 |  | 400 |  | 78.26 | 4500 | 4200 | 300 | 255 | 245 | 190 | 160
08/08/2021 | 15:27 | 15:41 | 0.23333 | 13430 | 13490 | 60 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 257.14 | 5200 | 4200 | 1000 | 255 | 245 | 190 | 160
08/08/2021 | 15:48 | 15:52 | 0.066667 | 13490 | 13500 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 150 | 5200 | 4200 | 1000 | 258 | 245 | 190 | 160
08/08/2021 | 15:52 | 16:11 | 0.31667 | 13500 | 13518 | 18 | Slide | 180 | 13515 | 89.73 | 142.15 | 10454.44 | -1878.88 | 1520.33 | -1878.88 | 2.39 |  |  | 40 |  | 400 |  | 56.84 | 4500 | 4200 | 300 | 258 | 245 | 190 | 160
08/08/2021 | 16:11 | 16:24 | 0.21667 | 13518 | 13584 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 304.62 | 5200 | 4200 | 1000 | 258 | 245 | 190 | 160
08/08/2021 | 16:31 | 16:34 | 0.05 | 13584 | 13594 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 200 | 5200 | 4200 | 1000 | 258 | 245 | 190 | 160
08/08/2021 | 16:34 | 16:47 | 0.21667 | 13594 | 13609 | 15 | Slide | 180 | 13609 | 87.84 | 142.45 | 10456.44 | -1953.23 | 1577.8 | -1953.23 | 2.04 |  |  | 40 |  | 400 | 17000 | 69.23 | 5200 | 4200 | 1000 | 262 | 220 | 190 | 160
08/08/2021 | 16:47 | 17:00 | 0.21667 | 13609 | 13678 | 69 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 318.46 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 18:05 | 18:09 | 0.066667 | 13678 | 13686 | 8 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 120 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 18:45 | 18:57 | 0.2 | 13686 | 13696 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 50 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 18:57 | 19:11 | 0.23333 | 13696 | 13771 | 75 | Rotate |  | 13702 | 86.85 | 140.93 | 10460.74 | -2026.12 | 1635.39 | -2026.12 | 1.95 |  |  | 40 | 80 | 400 | 17000 | 321.43 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 19:26 | 19:41 | 0.25 | 13771 | 13866 | 95 | Rotate |  | 13797 | 87.62 | 141.31 | 10465.33 | -2099.99 | 1694.95 | -2099.99 | 0.9 |  |  | 40 | 80 | 400 | 17000 | 380 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 19:46 | 19:50 | 0.066667 | 13866 | 13876 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 150 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 19:50 | 20:03 | 0.21667 | 13876 | 13886 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 46.15 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 20:03 | 20:18 | 0.25 | 13886 | 13960 | 74 | Rotate |  | 13891 | 87.03 | 141.3 | 10469.71 | -2173.28 | 1753.65 | -2173.28 | 0.63 |  |  | 40 | 80 | 400 | 17000 | 296 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 20:23 | 20:41 | 0.3 | 13960 | 14054 | 94 | Rotate |  | 13985 | 86.82 | 140.18 | 10474.76 | -2245.95 | 1813.05 | -2245.95 | 1.21 |  |  | 40 | 80 | 400 | 17000 | 313.33 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 20:46 | 21:02 | 0.26667 | 14054 | 14148 | 94 | Rotate |  | 14079 | 88.03 | 140.48 | 10478.98 | -2318.23 | 1873 | -2318.23 | 1.33 |  |  | 40 | 80 | 400 | 17000 | 352.5 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 21:07 | 21:11 | 0.066667 | 14148 | 14159 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 165 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 21:11 | 21:38 | 0.45 | 14159 | 14171 | 12 | Slide | TTF: -170; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 26.67 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/08/2021 | 21:38 | 21:53 | 0.25 | 14171 | 14242 | 71 | Rotate |  | 14173 | 88.08 | 141.38 | 10482.17 | -2391.17 | 1932.21 | -2391.17 | 0.96 |  |  | 40 | 80 | 400 | 17000 | 284 | 5200 | 4200 | 1000 | 262 | 245 | 190 | 160
08/09/2021 | 00:25 | 00:31 | 0.1 | 14242 | 14252 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 100 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160 | Drilling with Reduced GPM On Mud Cap Controle Drilling @ 180 - 200 An Hr
08/09/2021 | 00:31 | 00:39 | 0.13333 | 14252 | 14255 | 3 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 22.5 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 00:39 | 01:12 | 0.55 | 14255 | 14337 | 82 | Rotate |  | 14268 | 86.9 | 141.05 | 10486.33 | -2465.15 | 1991.66 | -2465.15 | 1.29 |  |  | 40 | 80 | 300 | 17000 | 149.09 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 01:17 | 01:49 | 0.53333 | 14337 | 14432 | 95 | Rotate |  | 14363 | 86.34 | 140.77 | 10491.93 | -2538.76 | 2051.45 | -2538.76 | 0.66 |  |  | 40 | 80 | 300 | 17000 | 178.12 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 01:53 | 02:31 | 0.63333 | 14432 | 14526 | 94 | Rotate |  | 14457 | 88.43 | 141.59 | 10496.22 | -2611.91 | 2110.32 | -2611.91 | 2.39 |  |  | 40 | 80 | 300 | 17000 | 148.42 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 02:36 | 03:00 | 0.4 | 14526 | 14536 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 25 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 03:00 | 03:28 | 0.46667 | 14536 | 14620 | 84 | Rotate |  | 14551 | 87.9 | 141.23 | 10499.23 | -2685.35 | 2168.92 | -2685.35 | 0.68 |  |  | 40 | 80 | 300 | 17000 | 180 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 03:33 | 04:03 | 0.5 | 14620 | 14715 | 95 | Rotate |  | 14646 | 89.41 | 141 | 10501.46 | -2759.27 | 2228.54 | -2759.27 | 1.61 |  |  | 40 | 80 | 300 | 17000 | 190 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 04:08 | 04:35 | 0.45 | 14715 | 14735 | 20 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 44.44 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 04:35 | 05:08 | 0.55 | 14735 | 14809 | 74 | Rotate |  | 14740 | 87.1 | 140.33 | 10504.32 | -2831.94 | 2288.09 | -2831.94 | 2.56 |  |  | 40 | 80 | 300 | 17000 | 120 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 05:08 | 05:45 | 0.61667 | 14809 | 14904 | 95 | Rotate |  | 14835 | 87.38 | 138.27 | 10508.9 | -2903.88 | 2349.96 | -2903.88 | 2.19 |  |  | 40 | 80 | 300 | 17000 | 154.05 | 4450 | 3350 | 1100 | 142 | 245 | 190 | 160
08/09/2021 | 06:00 | 06:05 | 0.083333 | 14904 | 14915 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 132 | 5600 | 4600 | 1000 | 158 | 245 | 190 | 160
08/09/2021 | 06:05 | 06:33 | 0.46667 | 14915 | 14940 | 25 | Slide | 110 | 14930 | 87.55 | 138 | 10513.1 | -2974.55 | 2413.3 | -2974.55 | 0.34 |  |  | 40 |  | 375 |  | 53.57 | 5000 | 4600 | 400 | 158 | 245 | 190 | 160
08/09/2021 | 06:33 | 06:50 | 0.28333 | 14940 | 14999 | 59 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 208.24 | 5600 | 4600 | 1000 | 158 | 245 | 190 | 160
08/09/2021 | 07:26 | 07:43 | 0.28333 | 14999 | 15024 | 25 | Slide | 120 | 15024 | 87.8 | 140.2 | 10516.91 | -3045.54 | 2474.79 | -3045.54 | 2.35 |  |  | 40 |  | 375 |  | 88.24 | 5000 | 4600 | 400 | 158 | 245 | 190 | 160
08/09/2021 | 07:43 | 07:47 | 0.066667 | 15024 | 15031 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 105 | 5600 | 4600 | 1000 | 158 | 245 | 190 | 160
08/09/2021 | 09:34 | 09:52 | 0.3 | 15031 | 15093 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 206.67 | 5600 | 4600 | 1000 | 158 | 245 | 190 | 160
08/09/2021 | 10:00 | 10:05 | 0.083333 | 15093 | 15103 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 120 | 5600 | 4600 | 1000 | 158 | 245 | 190 | 160
08/09/2021 | 10:05 | 10:26 | 0.35 | 15103 | 15123 | 20 | Slide | 130 | 15119 | 87.75 | 138.8 | 10520.6 | -3117.72 | 2536.44 | -3117.72 | 1.47 |  |  | 40 |  | 375 |  | 57.14 | 5000 | 4600 | 400 | 158 | 245 | 190 | 160
08/09/2021 | 10:26 | 10:45 | 0.31667 | 15123 | 15188 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 205.26 | 5600 | 4600 | 1000 | 158 | 245 | 190 | 160
08/09/2021 | 10:55 | 11:58 | 1.05 | 15188 | 15238 | 50 | Slide | 130 | 15214 | 87.61 | 142.62 | 10524.45 | -3191.18 | 2596.54 | -3191.18 | 4.02 |  |  | 40 |  | 375 |  | 47.62 | 5000 | 4600 | 400 | 158 | 235 | 170 | 130
08/09/2021 | 11:58 | 12:15 | 0.28333 | 15238 | 15283 | 45 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 158.82 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 12:23 | 13:09 | 0.76667 | 15283 | 15303 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 26.09 | 5000 | 4600 | 400 | 158 | 235 | 170 | 130
08/09/2021 | 13:09 | 13:36 | 0.45 | 15303 | 15377 | 74 | Rotate |  | 15308 | 85.21 | 143.42 | 10530.33 | -3266.11 | 2652.97 | -3266.11 | 2.69 |  |  | 40 | 80 | 375 | 23000 | 164.44 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 13:43 | 14:17 | 0.56667 | 15377 | 15471 | 94 | Rotate |  | 15402 | 84.91 | 143.48 | 10538.43 | -3341.35 | 2708.74 | -3341.35 | 0.33 |  |  | 40 | 80 | 375 | 23000 | 165.88 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 14:23 | 14:52 | 0.48333 | 15471 | 15535 | 64 | Rotate |  | 15496 | 85.01 | 143.32 | 10546.69 | -3416.52 | 2764.57 | -3416.52 | 0.2 |  |  | 40 | 80 | 375 | 23000 | 132.41 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 15:00 | 15:24 | 0.4 | 15535 | 15659 | 124 | Rotate |  | 15590 | 84.83 | 142.89 | 10555.01 | -3491.4 | 2820.78 | -3491.4 | 0.49 |  |  | 40 | 80 | 375 | 23000 | 310 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 15:32 | 16:12 | 0.66667 | 15659 | 15674 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 22.5 | 5000 | 4600 | 400 | 158 | 235 | 170 | 130
08/09/2021 | 16:12 | 16:36 | 0.4 | 15674 | 15753 | 79 | Rotate |  | 15684 | 87.08 | 144.09 | 10561.64 | -3566.76 | 2876.56 | -3566.76 | 2.71 |  |  | 40 | 80 | 375 | 23000 | 175.56 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 16:43 | 17:16 | 0.55 | 15753 | 15847 | 94 | Rotate |  | 15778 | 87.93 | 144.51 | 10565.73 | -3643.02 | 2931.36 | -3643.02 | 1.01 |  |  | 40 | 80 | 375 | 23000 | 170.91 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 18:04 | 18:08 | 0.066667 | 15847 | 15857 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 150 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 18:08 | 18:55 | 0.78333 | 15857 | 15869 | 12 | Slide | TTF: -140; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 15.32 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 18:55 | 19:21 | 0.43333 | 15869 | 15941 | 72 | Rotate |  | 15872 | 88.13 | 143.4 | 10568.96 | -3718.98 | 2986.64 | -3718.98 | 1.2 |  |  | 40 | 80 | 375 | 23000 | 166.15 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 19:25 | 19:35 | 0.16667 | 15941 | 15951 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 60 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 19:35 | 20:19 | 0.73333 | 15951 | 15966 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 20.45 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 20:19 | 20:44 | 0.41667 | 15966 | 16036 | 70 | Rotate |  | 15967 | 84.8 | 141.89 | 10574.82 | -3794.34 | 3044.16 | -3794.34 | 3.85 |  |  | 40 | 80 | 375 | 23000 | 168 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 20:48 | 21:26 | 0.63333 | 16036 | 16129 | 93 | Rotate |  | 16060 | 83.79 | 141.72 | 10584.07 | -3867.06 | 3101.38 | -3867.06 | 1.1 |  |  | 40 | 80 | 375 | 23000 | 146.84 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 21:30 | 21:37 | 0.11667 | 16129 | 16139 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 85.71 | 5600 | 4600 | 1000 | 158 | 235 | 170 | 130
08/09/2021 | 21:37 | 22:34 | 0.95 | 16139 | 16164 | 25 | Slide | 20 | 16155 | 86.49 | 142.06 | 10592.11 | -3941.54 | 3159.79 | -3941.54 | 2.86 |  |  | 40 | 80 | 375 | 23000 | 26.32 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/09/2021 | 22:34 | 22:56 | 0.36667 | 16164 | 16224 | 60 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 163.64 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/09/2021 | 23:00 | 23:30 | 0.5 | 16224 | 16319 | 95 | Rotate |  | 16250 | 90.2 | 141.71 | 10594.86 | -4016.24 | 3218.4 | -4016.24 | 3.92 |  |  | 40 | 80 | 375 | 23000 | 190 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/09/2021 | 23:34 | 23:42 | 0.13333 | 16319 | 16329 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 75 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/09/2021 | 23:42 | 24:00 | 0.3 | 16329 | 16337 | 8 | Slide | TTF: -160; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 26.67 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 00:00 | 00:20 | 0.33333 | 16337 | 16346 | 9 | Slide | -160 | 16344 | 90.21 | 141.51 | 10594.52 | -4089.91 | 3276.77 | -4089.91 | 0.21 |  |  | 40 | 80 | 375 | 23000 | 27 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 00:20 | 00:47 | 0.45 | 16346 | 16412 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 146.67 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 00:51 | 00:56 | 0.083333 | 16412 | 16427 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 180 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 00:56 | 01:40 | 0.73333 | 16427 | 16443 | 16 | Slide | -160 | 16438 | 89.87 | 141.21 | 10594.45 | -4163.34 | 3335.47 | -4163.34 | 0.48 |  |  | 40 | 80 | 375 | 23000 | 21.82 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 01:40 | 02:08 | 0.46667 | 16443 | 16507 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 137.14 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 02:12 | 03:12 | 1 | 16507 | 16537 | 30 | Slide | -160 | 16534 | 88.36 | 141.97 | 10595.94 | -4238.55 | 3395.1 | -4238.55 | 1.76 |  |  | 40 | 80 | 375 | 23000 | 30 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 03:12 | 03:40 | 0.46667 | 16537 | 16603 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 141.43 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 03:44 | 03:54 | 0.16667 | 16603 | 16613 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 60 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 03:54 | 05:00 | 1.1 | 16613 | 16638 | 25 | Slide | -160 | 16627 | 84.7 | 141.85 | 10601.57 | -4311.6 | 3452.36 | -4311.6 | 3.94 |  |  | 40 | 80 | 375 | 23000 | 22.73 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 05:00 | 05:30 | 0.5 | 16638 | 16696 | 58 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 116 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 05:34 | 06:08 | 0.56667 | 16696 | 16791 | 95 | Rotate |  | 16722 | 81.85 | 141.76 | 10612.69 | -4385.74 | 3510.69 | -4385.74 | 3 |  |  | 40 | 80 | 375 | 23000 | 167.65 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 06:18 | 06:25 | 0.11667 | 16791 | 16800 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 77.14 | 5600 | 4600 | 1000 | 176 | 235 | 170 | 130
08/10/2021 | 06:25 | 07:19 | 0.9 | 16800 | 16825 | 25 | Slide | 20 | 16816 | 83.76 | 142.32 | 10624.46 | -4459.26 | 3568.05 | -4459.26 | 2.12 |  |  | 40 |  | 375 |  | 27.78 | 4900 | 4600 | 300 | 176 | 235 | 170 | 130
08/10/2021 | 07:19 | 07:43 | 0.4 | 16825 | 16885 | 60 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 27000; Drilling Parameters ROP: 150 | 5600 | 4600 | 1000 | 182 | 235 | 170 | 130
08/10/2021 | 07:53 | 08:14 | 0.35 | 16885 | 16893 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 22.86 | 4900 | 4600 | 300 | 182 | 235 | 170 | 130
08/10/2021 | 08:14 | 08:46 | 0.53333 | 16893 | 16980 | 87 | Rotate |  | 16911 | 86.79 | 141.77 | 10632.29 | -4533.91 | 3626.27 | -4533.91 | 3.24 |  |  | 40 | 80 | 375 | 27000 | 163.12 | 5600 | 4600 | 1000 | 182 | 235 | 170 | 130
08/10/2021 | 08:56 | 09:24 | 0.46667 | 16980 | 17075 | 95 | Rotate |  | 17006 | 86.92 | 141.51 | 10637.5 | -4608.29 | 3685.14 | -4608.29 | 0.31 |  |  | 40 | 80 | 375 | 27000 | 203.57 | 5600 | 4600 | 1000 | 182 | 235 | 170 | 130
08/10/2021 | 09:34 | 09:58 | 0.4 | 17075 | 17169 | 94 | Rotate |  | 17100 | 86.57 | 139.61 | 10642.84 | -4680.76 | 3744.76 | -4680.76 | 2.05 |  |  | 40 | 80 | 375 | 27000 | 235 | 5600 | 4600 | 1000 | 182 | 235 | 170 | 130
08/10/2021 | 10:08 | 10:32 | 0.4 | 17169 | 17265 | 96 | Rotate |  | 17196 | 86.91 | 137.53 | 10648.3 | -4752.62 | 3808.18 | -4752.62 | 2.19 |  |  | 40 | 80 | 375 | 27000 | 240 | 5600 | 4600 | 1000 | 190 | 235 | 170 | 130
08/10/2021 | 10:42 | 11:52 | 1.1667 | 17265 | 17295 | 30 | Slide | 90 | 17290 | 86.77 | 139.53 | 10653.48 | -4822.94 | 3870.33 | -4822.94 | 2.13 |  |  | 40 |  | 375 |  | 25.71 | 4900 | 4600 | 300 | 190 | 235 | 170 | 130
08/10/2021 | 11:52 | 12:18 | 0.43333 | 17295 | 17359 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 27000; Drilling Parameters ROP: 147.69 | 5600 | 4600 | 1000 | 190 | 235 | 170 | 130
08/10/2021 | 12:28 | 12:57 | 0.48333 | 17359 | 17455 | 96 | Rotate |  | 17386 | 86.98 | 138.74 | 10658.71 | -4895.43 | 3933.04 | -4895.43 | 0.85 |  |  | 40 | 80 | 375 | 27000 | 198.62 | 5600 | 4600 | 1000 | 190 | 235 | 170 | 130
08/10/2021 | 13:07 | 14:19 | 1.2 | 17455 | 17485 | 30 | Slide | TTF: 90; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 25 | 4900 | 4600 | 300 | 172 | 235 | 170 | 130
08/10/2021 | 14:19 | 14:25 | 0.1 | 17485 | 17489 | 4 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 27000; Drilling Parameters ROP: 40 | 5600 | 4600 | 1000 | 172 | 235 | 170 | 130

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 365 |  | North Reference: |  | GRID |  | Total Drilled: |  | 603
Site: |  |  |  |  | Boone-Borgstedt - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 35
Well Name: |  |  |  |  | Borgstedt 2H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 365 |  | VS Azimuth: |  | 141.66 |  | Rotate: |  | 568
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/11/2021 | 22:10 | 22:18 | 0.13333 | 17489 | 17527 | 38 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 285 | 5600 | 4600 | 1000 | 172 | 235 | 175 | 130
08/11/2021 | 22:22 | 22:56 | 0.56667 | 17527 | 17622 | 95 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 167.65 | 5600 | 4600 | 1000 | 198 | 235 | 175 | 130
08/11/2021 | 23:00 | 23:30 | 0.5 | 17622 | 17718 | 96 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 192 | 5600 | 4600 | 1000 | 198 | 235 | 175 | 130
08/11/2021 | 23:34 | 23:45 | 0.18333 | 17718 | 17728 | 10 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 54.55 | 5600 | 4600 | 1000 | 198 | 235 | 175 | 130
08/11/2021 | 23:45 | 24:00 | 0.25 | 17728 | 17733 | 5 | Slide | TTF: 90; Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 20 | 5600 | 4880 | 720 | 198 | 235 | 175 | 130
08/12/2021 | 00:00 | 00:28 | 0.46667 | 17733 | 17744 | 11 | Slide | TTF: 90; Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 23.57 | 5600 | 4880 | 720 | 198 | 235 | 175 | 130
08/12/2021 | 00:45 | 01:30 | 0.75 | 17744 | 17763 | 19 | Slide | TTF: 90; Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 25.33 | 5600 | 4880 | 720 | 198 | 235 | 175 | 130
08/12/2021 | 01:30 | 01:50 | 0.33333 | 17763 | 17813 | 50 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 150 | 5730 | 4880 | 850 | 198 | 235 | 175 | 130
08/12/2021 | 01:54 | 02:26 | 0.53333 | 17813 | 17907 | 94 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 176.25 | 5730 | 4880 | 850 | 198 | 235 | 175 | 130
08/12/2021 | 02:30 | 03:00 | 0.5 | 17907 | 18001 | 94 | Rotate | Drilling Parameters WOB: 18.5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25; Drilling Parameters ROP: 188 | 5730 | 4880 | 850 | 198 | 235 | 175 | 130
08/12/2021 | 03:04 | 03:35 | 0.51667 | 18001 | 18092 | 91 | Rotate |  | 18023 | 88.52 | 140.28 | 10683.72 | -5379.48 | 4346.31 | -5379.48 | 0.34 |  |  | 18.5 | 80 | 375 | 25 |  | 5730 | 4880 | 850 | 196 | 235 | 175 | 130