## Summary
Magnolia Oil & Gas / Dietz 3H / LTX1129020 / Patterson 248
Report Date: | 08/02/2020 | Current Depth: | 17841
Start Date: | 07/09/2020 | Casing Depth: | 0
Daily Cost: | 7250 | Distance to TD:
Well Cost: | 135850 | Average ROP: | 0
Drilling Hours: | 60 | Svy MD: | 17841
24Hr Forcast: | Running casing & Cement | Svy Inc: | 92
Current BHA: | BHA 5 (Lateral) | Svy Azi: | 336
Current BRT Hrs: | 98.47 | Svy TVD: | 10202.41
Bit Make / Model: | Halliburton / GTD64M | Svy NS: | 5678.53
POOH in last 24Hrs: | Yes | Svy EW: | -1796.55
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | WBM | Svy Left/Right: | 0
Directional Driller Day: | Jeff Wells | MWD Day: | Kyle Novasod
Directional Driller Night: | Leo Douet | MWD Night: | Blake Goodrum
RSS Engineer 1: |  | Third Man:
RSS Engineer 2: |  | Fourth Man:
Principal Plan: |  | Max BHT Well: | 285
24Hr Summary: | Running casing | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MTR500048 | 5" 6/7 8.8 Stg 2? FBH TS |  |  | Dirty |  | 15.72 | 15.72
MTR500017 | 5" 6/7 8.8 Stg 2? FBH TS (Lateral)** |  |  | Clean
MTR475035 | 5" 7/8 3.8 Stg 2.5? FBH TS |  |  | Clean
PPM250013 | 5" 6/7 8.8 Stg 2? FBH TS |  |  | Clean
PPM250012 | 5" 6/7 8.8 Stg 2? FBH TS |  |  | Clean
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
775199 | 7 3/4" UBHO |  |  | Dirty |  | 33.68 | 33.68
ZSB775210 | 7 3/4" UBHO |  |  | Clean
675105 | 6 3/4" UBHO |  |  | Clean
775218 | 7 3/4" UBHO |  |  | Clean
ZSB500031 | UBHO |  |  | Clean
ZSB500029 | UBHO |  |  | Dirty |  | 107.75 | 107.75

## Well Summary
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Dietz 3H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Total Drilled (Usft): |  | 17736 |  |  | Total Days: |  | 16
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 105 | 2769 | 2664 |  | 485.84 |  | 11.79 | 5.48 | 6.86 | 11.5
2 | 2 | 9.875 | 2769 | 10249 | 7480 |  | 242.99 |  | 7.18 | 30.78 | 33.75 | 56.67
3 | 3 | 6.75 | 10249 | 12413 | 2164 |  | 86.56 |  | 32.95 | 25 | 27.52 | 58
4 | 3 | 6.75 | 12413 | 12820 | 407 |  | 76.07 |  | 13.02 | 5.35 | 15.73 | 62 | YES
5 | 5 | 6.75 | 12820 | 17841 | 5021 |  | 83.68 |  | 7.13 | 60 | 64.52 | 98.47
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | SPL616 |  | 13.5 | Rerun |  | Green |  | 1.353 | 2664 | 5.4833 | 485.84
2 | Ulterra |  | SPL613 |  | 9.875 | Green |  |  |  | 1.491 | 7480 | 30.7833 | 242.99
3 | Ulterra |  | RPS613 |  | 6.75 | Green |  | Green |  | 1.178 | 2164 | 25 | 86.56
3 | Baker Hughes |  | RPS613 |  | 6.75 | Green |  |  |  | 1.178 | 407 | 5.35 | 76.07
5 | Halliburton |  | GTD64M |  | 6.75 | Green |  | 02 |  | 1.178 | 5021 | 60 | 83.68
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 1.5 | 5.7 | 2664 |  | 485.84
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 2 | 5.65 | 7480 |  | 242.99
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5 | 2 | 4.44 | 2164 |  | 86.56
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 4.875 | 2 | 4.3 | 407 |  | 76.07
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5 | 2 | 4.3 | 5021 |  | 83.68
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jeff Wells |  | Jeff Wells |  | Kyle Novasod |  | Blake Goodrum |  | Jim |  | James |  | David LeBlanc
Nathan Marks |  | Leo Douet |  | Russell Arnold | [5 empty] | Kevin Burt
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 1.00 / 0.32 |  | 2664 |  | 481.74 |  | 0.00 / 1.00 |  | 1 |  | 5.53
INT: INTERMEDIATE |  |  | 5.00 / 1.67 |  | 7480 |  | 242.54 |  | 0.00 / 24.00 |  | 1 |  | 30.84
CRV: CURVE |  |  | 1.68 / 0.72 |  | 947 |  | 63.81 |  |  |  | 1 |  | 14.84
LAT: LATERAL |  |  | 8.32 / 7.13 |  | 6645 |  | 88 |  | 1.47 / 0.00 |  | 3 |  | 75.51
Total |  |  | 15.99 |  | 17736 |  | 139.96 |  | 1.47 / 25.00 |  | 5 |  | 126.72
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA #1 (Surface) |  |  | 105.00 | 2769.00 | 613.58 | 2350.00 | 184.71 | 314.00 | 11.79 | 2664.00 | 481.74 | 5.53 | 1.70
INT: INTERMEDIATE-BHA #2 (Intermediate) |  |  | 2769.00 | 10249.00 | 353.15 | 6943.00 | 48.03 | 537.00 | 7.18 | 7480.00 | 242.54 | 30.84 | 11.18
CRV: CURVE-BHA 3 (Curve-Lateral) |  |  | 10249.00 | 11196.00 | 95.41 | 353.00 | 53.32 | 594.00 | 62.72 | 947.00 | 63.81 | 14.84 | 11.14
LAT: LATERAL-BHA 3 (Curve-Lateral) |  |  | 11196.00 | 12413.00 | 186.10 | 1098.00 | 27.93 | 119.00 | 9.78 | 1217.00 | 119.78 | 10.16 | 4.26
LAT: LATERAL-BHA 4 Lateral |  |  | 12413.00 | 12820.00 | 132.58 | 354.00 | 19.78 | 53.00 | 13.02 | 407.00 | 76.07 | 5.35 | 2.68
LAT: LATERAL-BHA 5 (Lateral) |  |  | 12820.00 | 17841.00 | 108.72 | 4663.00 | 20.92 | 358.00 | 7.13 | 5021.00 | 83.68 | 60.00 | 17.11
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1129020 | Total Drilled(Usft) | 17736.00
Operator | Magnolia Oil & Gas | Drilling Hours | 126.62
Well Name | Dietz 3H | Avg ROP(Usft/hr) | 140.08
Rig | Patterson 248 | Rotary Drilled(Usft) | 15761.00
State | Texas | Rotary Hours | 78.55
County | Washington | Rotary ROP(Usft/hr) | 200.65
Formation | Austin Chalk | Rotary % | 88.86
Start Date | 07/09/2020 | Slide Drilled(Usft) | 1975.00
End Date | 08/02/2020 | Slide Hours | 48.07
Days On Well | 16 | Slide ROP(Usft/hr) | 41.09
Start Depth (Usft) | 105.00 | Slide % | 11.14
End Depth (Usft) | 17841.00
Total Drilled (Usft) | 17736.00
# BHA's | 5
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 4.05 / 25.00
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 07/09/2020 | 07/19/2020 | 07/24/2020 | 07/25/2020
End Date | 07/09/2020 | 07/23/2020 | 07/25/2020 | 08/02/2020
Total Days | 1.00 | 5.00 | 1.68 | 8.32
Start Depth (Usft) | 105.00 | 2769.00 | 10249.00 | 11196.00
End Depth (Usft) | 2769.00 | 10249.00 | 11196.00 | 17841.00
Total Drilled(Usft) | 2664.00 | 7480.00 | 947.00 | 6645.00
Drilling Hours | 5.48 | 30.78 | 14.83 | 75.52
Circulating Hours | 1.33 | 2.90 | 1.52 | 15.88
Total D&C Hours | 6.82 | 33.68 | 16.35 | 91.40
Avg ROP(Usft/hr) | 485.84 | 242.99 | 63.84 | 87.99
Rotary Drilled(Usft) | 2350.00 | 6943.00 | 353.00 | 6115.00
Rotary Hours | 3.80 | 19.62 | 3.68 | 51.45
Rotary ROP(Usft/hr) | 618.42 | 353.93 | 95.84 | 118.85
Rotary % | 88.21 | 92.82 | 37.28 | 92.02
Slide Drilled(Usft) | 314.00 | 537.00 | 594.00 | 530.00
Slide Hours | 1.68 | 11.17 | 11.15 | 24.07
Slide ROP(Usft/hr) | 186.53 | 48.09 | 53.27 | 22.02
Slide % | 11.79 | 7.18 | 62.72 | 7.98
# BHA | 1 | 1 | 1 | 3
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 1.00 | 0.73 / 24.00 | 0.00 / 0.00 | 3.32 / 0.00
Total Phase Hrs | 7.67 | 40.17 | 17.17 | 171.08
Phase ROP (Usft/hr) | 347.48 | 186.22 | 55.17 | 38.84
Avg Motor Yield (°/100ft) | 0.00 | 19.67 | 15.09 | 18.24
Avg Rotary DLS (°/100ft) | 0.00 | 0.77 | 3.97 | 1.20
Avg Rotary TF | 0.00 | -147.60 | 14.10 | -24.84
Avg Slide Length (Usft) | 0.00 | 21.48 | 45.69 | 16.35
# Slides | 0 | 25 | 13 | 34
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5
Description | BHA #1 (Surface) | BHA #2 (Intermediate) | BHA 3 (Curve-Lateral) | BHA 4 Lateral | BHA 5 (Lateral)
Bit Size | 13.500 | 9.875 | 6.750 | 6.750 | 6.750
Bit Make/Model | Ulterra / SPL616 | Ulterra / SPL613 | Ulterra / RPS613 | Baker Hughes / RPS613 | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.178 | 1.178 | 1.178
Grade In | Rerun | Green | Green | Green | Green
Grade Out | Green |  | Green |  | 02
Motor SN | PPM800019 | PPM800015 | MTR475113 | MTR500048 | PPM250009
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.90 | 7/8 / 5.90 | 6/7 / 8.80 | 6/7 / 8.80 | 6/7 / 8.80
WOB (klbs) | 999999.00 / 0.00 / -999999.00 | 8.00 / 29.62 / 40.00 | 15.00 / 29.52 / 30.00 | 30.00 / 30.00 / 30.00 | 32000.00 / 32000.00 / 32000.00
Diff P (psi) | 999999.00 / 0.00 / -999999.00 | 150.00 / 640.77 / 800.00 | 250.00 / 966.35 / 1000.00 | 700.00 / 700.00 / 700.00 | 650.00 / 668.95 / 700.00
Bend | 1.500 | 2.000 | 2.000 | 2.000 | 2.000
Date In | 07/09/2020 | 07/20/2020 | 07/24/2020 | 07/26/2020 | 07/29/2020
Date Out | 07/09/2020 | 07/22/2020 | 07/26/2020 | 07/29/2020 | 08/02/2020
Time In | 11:30 | 04:50 | 07:30 | 18:30 | 09:17
Time Out | 23:00 | 13:30 | 17:30 | 08:30 | 11:45
BRT Hrs | 11.50 | 56.67 | 58.00 | 62.00 | 98.47
Start Depth (Usft) | 105.00 | 2769.00 | 10249.00 | 12413.00 | 12820.00
End Depth (Usft) | 2769.00 | 10249.00 | 12413.00 | 12820.00 | 17841.00
Total Drilled(Usft) | 2664.00 | 7480.00 | 2164.00 | 407.00 | 5021.00
Drilling Hours | 5.48 | 30.78 | 25.00 | 5.35 | 60.00
Circulating Hours | 1.33 | 2.90 | 2.52 | 10.37 | 4.52
Total D&C Hours | 6.82 | 33.68 | 27.52 | 15.72 | 64.52
Avg ROP(Usft/hr) | 485.84 | 242.99 | 86.56 | 76.07 | 83.68
Rotary Drilled(Usft) | 2350.00 | 6943.00 | 1451.00 | 354.00 | 4663.00
Rotary Hours | 3.80 | 19.62 | 9.58 | 2.67 | 42.88
Rotary ROP(Usft/hr) | 618.42 | 353.93 | 151.41 | 132.75 | 108.74
Rotary % | 88.21 | 92.82 | 67.05 | 86.98 | 92.87
Slide Drilled(Usft) | 314.00 | 537.00 | 713.00 | 53.00 | 358.00
Slide Hours | 1.68 | 11.17 | 15.42 | 2.68 | 17.12
Slide ROP(Usft/hr) | 186.53 | 48.09 | 46.25 | 19.75 | 20.92
Slide % | 11.79 | 7.18 | 32.95 | 13.02 | 7.13
Motor Failure | NO | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | YES | NO
LIH | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 0.00 | 19.67 | 14.61 | 21.01 | 15.49
Avg Rotary DLS (°/100ft) | 0.00 | 0.77 | 1.85 | 1.94 | 0.95
Avg Rotary TF | 0.00 | -147.60 | -24.97 | -9.44 | -28.68
Avg Slide Length (Usft) | 0.00 | 21.48 | 39.61 | 10.75 | 15.76
# Slides | 0 | 25 | 18 | 4 | 25

## Personnel Report
|  | Job # | LTX1129020 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31131 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Dietz 3H
|  | Date: | 08/02/2020 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Dietz 3H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Blake Goodrum | Night MWD |  | 07/09/2020 - 00:00 | 07/09/2020 - 00:00 |  | 1.00 / 0.00
Blake Goodrum | Night MWD |  | 07/19/2020 - 00:00 | 08/02/2020 - 24:00 |  | 15.00 / 360.00
Jeff Wells | Day DD |  | 07/26/2020 - 00:00 | 08/02/2020 - 24:00 |  | 8.00 / 192.00
Jeff Wells | Night DD |  | 07/09/2020 - 00:00 | 07/09/2020 - 00:00 |  | 1.00 / 0.00
Jeff Wells | Night DD |  | 07/19/2020 - 00:00 | 07/25/2020 - 24:00 |  | 7.00 / 168.00
Kyle Novasod | Day MWD |  | 07/26/2020 - 00:00 | 08/02/2020 - 24:00 |  | 8.00 / 192.00
Leo Douet | Night DD |  | 07/26/2020 - 00:00 | 08/02/2020 - 24:00 |  | 8.00 / 192.00
Nathan Marks | Day DD |  | 07/09/2020 - 00:00 | 07/09/2020 - 00:00 |  | 1.00 / 0.00
Nathan Marks | Day DD |  | 07/19/2020 - 00:00 | 07/25/2020 - 24:00 |  | 7.00 / 168.00
Russell Arnold | Day MWD |  | 07/09/2020 - 00:00 | 07/09/2020 - 00:00 |  | 1.00 / 0.00
Russell Arnold | Day MWD |  | 07/19/2020 - 00:00 | 07/25/2020 - 24:00 |  | 7.00 / 168.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1129020 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Dietz 3H | [7 empty] | Day DD: |  |  |  |  | Jeff Wells | [5 empty] | API #: |  |  |  | 42-477-31131
|  |  |  | AFE #: |  |  | 20DD0153Mc | [7 empty] | Night DD: |  |  |  |  | Leo Douet | [5 empty] | Company Man: |  |  |  | Jim
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Kyle Novasod | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Blake Goodrum | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 07/09/2020 | 07/10/2020 | 07/11/2020 | 07/12/2020 | 07/13/2020 | 07/14/2020 | 07/15/2020 | 07/16/2020 | 07/17/2020 | 07/18/2020 | 07/19/2020 | 07/20/2020 | 07/21/2020 | 07/22/2020 | 07/23/2020 | 07/24/2020 | 07/25/2020 | 07/26/2020 | 07/27/2020 | 07/28/2020 | 07/29/2020 | 07/30/2020 | 07/31/2020 | 08/01/2020 | 08/02/2020 | 08/03/2020 | 08/04/2020 | 08/05/2020 | 08/06/2020 | 08/07/2020 | 08/08/2020
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | Ulterra RPS 613 6x16s |  | Steel | 50597 | 4 | 11 | [14 empty] | O | O | O | X | X | X | X | O | O | O | O
Bit |  | 6.75 | Halliburton GTD64M (Jetted 6x16s) |  | Steel | 1138553 | 5 | 5 | [20 empty] | X | X | X | X | X
Cross Over |  | 6.75 | X/O 4 1/2 IFB x 6 5/8 RegP |  | Steel | SD109674 | 1 | 15 | X | [9 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.75 | X/O 4 1/2 IFB x 6 5/8 RegP |  | Steel | SD118773 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.438 | X/O 4 1/2 XHB x 6 5/8 RegP |  | Steel | SD115528 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.813 | X/O 4 1/2 XHB x 6 5/8 RegP |  | Steel | SD117717 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.5 | X/O 4 1/2 IFB x 4 1/2 XHP |  | Steel | SD107702 | 3 | 15 | [10 empty] | O | X | X | X | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.625 | X/O 4 1/2 IFB x 4 1/2 XHP |  | Steel | SD4555 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.563 | X/O 4 1/2 XHB x 4 1/2 IFP |  | Steel | SD108613 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.75 | X/O 4 1/2 XHB x 4 1/2 IFP |  | Steel | SD112037 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5 | DS42 Box X XT39 Pin |  | Steel | SD119312 | 3 | 11 | [14 empty] | O | X | X | X | O | O | O | O | O | O | O
Cross Over |  | 5 | DS42 Box X XT39 Pin |  | Steel | SD119313 | 8 | 11 | [14 empty] | O | O | O | X | X | X | X | X | X | X | X
Cross Over |  | 5.313 | DS42 Box x Delta 425 Pin |  | Steel | DR38852 | 10 | 10 | [15 empty] | X | X | X | X | X | X | X | X | X | X
Cross Over |  | 5.313 | Delta 425 Box x DS42 Pin |  | Steel | DR38846 | 10 | 10 | [15 empty] | X | X | X | X | X | X | X | X | X | X
MWD / LWD |  | 7.75 | 7 3/4" UBHO |  | Steel | 775199 | 3 | 15 | [10 empty] | O | X | X | X | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 7.75 | 7 3/4" UBHO |  | Steel | ZSB775210 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  |  | 6 3/4" UBHO |  | Steel | 675105 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  |  | 7 3/4" UBHO |  | Steel | 775218 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5 | UBHO |  | Steel | ZSB500031 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5 | UBHO |  | Steel | ZSB500029 | 10 | 11 | [14 empty] | O | X | X | X | X | X | X | X | X | X | X
Motor |  | 8 | 7 3/4" - 7/8, 5.9 Stg. @ 2.0? FBH TS |  | Steel | MTR775039 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 8 | 7 3/4" - 7/8, 5.9 Stg. @ 2.0? FBH TS |  | Steel | PPM800015 | 3 | 15 | [10 empty] | O | X | X | X | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 5" 6/7 8.8 Stg 2? FBH TS |  | Steel | MTR475113 | 3 | 5 | [14 empty] | O | X | X | X | O
Motor |  | 5 | 5" 6/7 8.8 Stg 2? FBH TS |  | Steel | MTR500002 | 0 | 2 | [14 empty] | O | O
Motor |  | 4.875 | 5" 6/7 8.8 Stg 2? FBH TS |  | Steel | MTR500048 | 4 | 11 | [14 empty] | O | O | O | X | X | X | X | O | O | O | O
Motor |  | 5 | 5" 6/7 8.8 Stg 2? FBH TS (Lateral)** |  | Steel | MTR500017 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 4.875 | 5" 7/8 3.8 Stg 2.5? FBH TS |  | Steel | MTR475035 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Motor |  |  | 5" 6/7 8.8 Stg 2? FBH TS |  | Steel | PPM250013 | 0 | 10 | [15 empty] | O | O | O | O | O | O | O | O | O | O
Motor |  |  | 5" 6/7 8.8 Stg 2? FBH TS |  | Steel | PPM250012 | 0 | 8 | [17 empty] | O | O | O | O | O | O | O | O
Motor |  | 5 | 5" 6/7 8.8 Stg 2? FBH TS |  | Steel | PPM250009 | 5 | 7 | [18 empty] | O | O | X | X | X | X | X
Stab |  | 8.125 | 13" Nortrak Stabalizer |  | Steel | SD600317 | 1 | 15 | X | [9 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Stab |  | 8.313 | 13" Nortrak Stabalizer |  | Steel | SD603255 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 8 | 8" Drill Collar |  | Steel | SD55685 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 8 | 8" Pony Collar |  | Steel | SD47955 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill collar |  | Non-Mag | SD55909 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill collar |  | Non-Mag | SD56284 | 10 | 11 | [14 empty] | O | X | X | X | X | X | X | X | X | X | X
Collar |  | 5 | NM Drill collar |  | Non-Mag | SD56633 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill collar |  | Non-Mag | SD56699 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill collar |  | Non-Mag | SD56703 | 10 | 11 | [14 empty] | O | X | X | X | X | X | X | X | X | X | X
Collar |  | 5 | NM Drill collar |  | Non-Mag | SD56709 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Pony collar |  | Non-Mag | SD56727 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Pony collar |  | Non-Mag | SD56841 | 10 | 11 | [14 empty] | O | X | X | X | X | X | X | X | X | X | X
Drill Pipe |  | 4.5 | 27 stands of 4 1/2" DP |  | Steel | Rig 1 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 8 | Float Sub |  | Steel | SD109205 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 8 | Float Sub |  | Steel | SD116259 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD105542 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift sub |  | Steel | SD118523 | 0 | 15 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 5 | Float sub w/Restrictor sub jetted 20/32 |  | Steel | SD119029 | 8 | 11 | [14 empty] | O | O | O | X | X | X | X | X | X | X | X
Sub |  | 5 | Float sub |  | Steel | SD119067 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift sub |  | Steel | SD115393 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift sub |  | Steel | SD118935 | 0 | 11 | [14 empty] | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.75 | BTI Valve |  | Steel | 30-10063 | 10 | 11 | [14 empty] | O | X | X | X | X | X | X | X | X | X | X
Agitator |  | 5.188 | Agitator |  | Steel | AGHF0525-0004 | 5 | 11 | [14 empty] | O | O | O | O | O | O | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jeff Wells |  |  |  | 8 | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Nathan Marks |  |  |  | 8 |  | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Jeff Wells |  |  |  | 8 |  | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Leo Douet |  |  |  | 8 | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Kyle Novasod |  |  |  | 8 | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Russell Arnold |  |  |  | 8 |  | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Blake Goodrum |  |  |  | 16 |  | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Dietz 3H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0153Mc |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
775199 | 7 3/4" UBHO | 7.75 | 3.86 |  | 6 5/8 Reg / 6 5/8 Reg | Dirty |  | 07/19/2020
ZSB775210 | 7 3/4" UBHO | 7.75 | 3.99 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
SD55685 | 8" Drill Collar | 8 | 28.67 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
SD47955 | 8" Pony Collar | 8 | 9.55 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
SD600317 | 13" Nortrak Stabalizer | 8.125 | 6.97 |  | 6 5/8 Reg / 6 5/8 Reg | Dirty |  | 07/19/2020
SD603255 | 13" Nortrak Stabalizer | 8.313 | 7.26 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
SD109674 | X/O 4 1/2 IFB x 6 5/8 RegP | 6.75 | 2.22 |  | 4 1/2 IF / 6 5/8 Reg | Dirty |  | 07/19/2020
SD118773 | X/O 4 1/2 IFB x 6 5/8 RegP | 6.75 | 4.03 |  | 4 1/2 IF / 6 5/8 Reg | Clean |  | 07/19/2020
SD115528 | X/O 4 1/2 XHB x 6 5/8 RegP | 6.438 | 3.03 |  | 4 1/2 XH / 6 5/8 Reg | Clean |  | 07/19/2020
SD117717 | X/O 4 1/2 XHB x 6 5/8 RegP | 6.813 | 3.58 |  | 4 1/2 XH / 6 5/8 Reg | Clean |  | 07/19/2020
SD107702 | X/O 4 1/2 IFB x 4 1/2 XHP | 6.5 | 3 |  | 4 1/2 IF / 4 1/2 XH | Dirty |  | 07/19/2020
SD4555 | X/O 4 1/2 IFB x 4 1/2 XHP | 6.625 | 3.07 |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 07/19/2020
SD108613 | X/O 4 1/2 XHB x 4 1/2 IFP | 6.563 | 2.22 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 07/19/2020
SD112037 | X/O 4 1/2 XHB x 4 1/2 IFP | 6.75 | 2.63 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 07/19/2020
SD109205 | Float Sub | 8 | 2.1 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
SD116259 | Float Sub | 8 | 2.15 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
LC3332 | 6 5/8 Reg. Lift Cap |  |  |  |  | Clean |  | 07/19/2020
MTR775039 | 7 3/4" - 7/8, 5.9 Stg. @ 2.0? FBH TS | 8 | 37.44 |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
PPM800015 | 7 3/4" - 7/8, 5.9 Stg. @ 2.0? FBH TS | 8 | 37.32 |  | 6 5/8 Reg / 6 5/8 Reg | Dirty |  | 07/19/2020
SD105542 | Lift Sub |  |  |  | 6 5/8 Reg | Clean |  | 07/19/2020
SD118523 | Lift sub |  |  |  | 6 5/8 Reg | Clean |  | 07/19/2020
675105 | 6 3/4" UBHO |  |  |  | 4 1/2 IF / 4 1/2 IF | Clean |  | 07/19/2020
775218 | 7 3/4" UBHO |  |  |  | 6 5/8 Reg / 6 5/8 Reg | Clean |  | 07/19/2020
MTR475113 | 5" 6/7 8.8 Stg 2? FBH TS | 5 | 33.39 |  | XT39 / 3 1/2 Reg | Dirty |  | 07/23/2020 |  | 07/27/2020
MTR500002 | 5" 6/7 8.8 Stg 2? FBH TS | 5 | 33.27 |  | XT39 / 3 1/2 Reg | Clean |  | 07/23/2020 |  | 07/24/2020
MTR500048 | 5" 6/7 8.8 Stg 2? FBH TS | 4.875 | 33.33 |  | XT39 / 3 1/2 Reg | Dirty |  | 07/23/2020
MTR500017 | 5" 6/7 8.8 Stg 2? FBH TS (Lateral)** | 5 | 33.32 |  | XT39 / 3 1/2 Reg | Clean |  | 07/23/2020
MTR475035 | 5" 7/8 3.8 Stg 2.5? FBH TS | 4.875 | 26.09 |  | XT39 / 3 1/2 Reg | Clean |  | 07/23/2020
ZSB500031 | UBHO | 5 | 4 |  | XT39 / XT39 | Clean |  | 07/23/2020
ZSB500029 | UBHO | 5 | 3.49 |  | XT39 / XT39 | Dirty |  | 07/23/2020 |  | 08/02/2020
SD55909 | NM Drill collar | 5 | 30.3 |  | XT39 / XT39 | Clean |  | 07/23/2020
SD56284 | NM Drill collar | 5 | 30.87 |  | XT39 / XT39 | Dirty |  | 07/23/2020 |  | 08/03/2020
SD56633 | NM Drill collar | 5 | 31.12 |  | XT39 / XT39 | Clean |  | 07/23/2020
SD56699 | NM Drill collar | 5 | 30.85 |  | XT39 / XT39 | Clean |  | 07/23/2020
SD56703 | NM Drill collar | 5 | 30.78 |  | XT39 / XT39 | Dirty |  | 07/23/2020 |  | 08/03/2020
SD56709 | NM Drill collar | 5 | 30.43 |  | XT39 / XT39 | Clean |  | 07/23/2020
SD56727 | NM Pony collar | 5 | 11.95 |  | XT39 / XT39 | Clean |  | 07/23/2020
SD56841 | NM Pony collar | 5 | 11.9 |  | XT39 / XT39 | Dirty |  | 07/23/2020 |  | 08/03/2020
SD119029 | Float sub w/Restrictor sub jetted 20/32 | 5 | 3.55 |  | XT39 / XT39 | Dirty |  | 07/23/2020 |  | 08/03/2020
SD119067 | Float sub | 5 | 3.55 |  | XT39 / XT39 | Clean |  | 07/23/2020
SD115393 | Lift sub |  |  |  | XT39 / XT39 | Clean |  | 07/23/2020
SD118935 | Lift sub |  |  |  | XT39 / XT39 | Clean |  | 07/23/2020
SD119312 | DS42 Box X XT39 Pin | 5 | 3.52 |  | DS42 / XT39 | Dirty |  | 07/23/2020 |  | 08/03/2020
SD119313 | DS42 Box X XT39 Pin | 5 | 3.52 |  | DS42 / XT39 | Dirty |  | 07/23/2020 |  | 08/02/2020
LC1115 | Lift cap |  |  |  | XT39 | Clean |  | 07/23/2020
30-10063 | BTI Valve | 4.75 | 2.25 |  | XT39 / XT39 | Dirty |  | 07/23/2020
50597 | Ulterra RPS 613 6x16s | 6.75 | 0.85 |  | 3 1/2 Reg | Dirty |  | 07/23/2020
Rig 1 | 27 stands of 4 1/2" DP | 4.5 | 2593.2 |  | DS42 / DS42 | Dirty |  | 07/23/2020
AGHF0525-0004 | Agitator | 5.188 | 27.99 |  | Delta 425 / Delta 425 | Dirty |  | 07/23/2020
DR38852 | DS42 Box x Delta 425 Pin | 5.313 | 3.31 |  | DS42 / Delta 425 | Dirty |  | 07/24/2020
DR38846 | Delta 425 Box x DS42 Pin | 5.313 | 3.22 |  | Delta 425 / DS42 | Dirty |  | 07/24/2020
PPM250013 | 5" 6/7 8.8 Stg 2? FBH TS |  |  |  | XT39 / 3 1/2 Reg | Clean |  | 07/24/2020
PPM250012 | 5" 6/7 8.8 Stg 2? FBH TS |  |  |  | XT39 / 3 1/2 Reg | Clean |  | 07/26/2020
PPM250009 | 5" 6/7 8.8 Stg 2? FBH TS | 5 | 33.1 |  | XT39 / 3 1/2 Reg | Dirty |  | 07/27/2020 |  | 08/02/2020
1138553 | Halliburton GTD64M (Jetted 6x16s) | 6.75 | 0.74 |  | 3 1/2 Reg | Dirty |  | 07/29/2020
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Dietz 3H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
13 1/2 - Ulterra - SPL616 | 49142 | 07/09/2020 | 08/02/2020 | 25 |  | 1 |  | 1.33 | 5.48 | 11.5
7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | PPM800019 | 07/09/2020 | 08/02/2020 | 25 |  | 1 |  | 1.33 | 5.48 | 11.5
13 Nortrak Stabalizer | SD600317 | 07/19/2020 | 08/02/2020 | 15 |  | 1 |  | 1.33 | 5.48 | 11.5
8" Pony Collar | SD54383 | 07/09/2020 | 08/02/2020 | 25 |  | 1 |  | 1.33 | 5.48 | 11.5
7 3/4" UBHO | ZSB775211 | 07/09/2020 | 08/02/2020 | 25 |  | 1 |  | 1.33 | 5.48 | 11.5
8" Drill Collar | SD43280 | 07/09/2020 | 08/02/2020 | 25 |  | 1 |  | 1.33 | 5.48 | 11.5
8" Drill Collar | SD56210 | 07/09/2020 | 08/02/2020 | 25 |  | 1 |  | 1.33 | 5.48 | 11.5
X/O 4 1/2 IFB x 6 5/8 RegP | SD109674 | 07/19/2020 | 08/02/2020 | 15 |  | 1 |  | 1.33 | 5.48 | 11.5
9 7/8 - Ulterra - SPL613 | 43215 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS | PPM800015 | 07/19/2020 | 08/02/2020 | 15 | 2 | 2 |  | 2.9 | 30.78 | 56.67
8 Pony Collar | SD43935 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
7 3/4 UBHO | 775199 | 07/19/2020 | 08/02/2020 | 15 | 2 | 2 |  | 2.9 | 30.78 | 56.67
8 Drill Collar | SD51948 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
8 Drill Collar | SD51886 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
X/O 4 1/2 XHB x 6 5/8 RegP | SD118447 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
2 Stands 6 1/2in Collars | Rig 3 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
X/O 4 1/2 IFB x 4 1/2 XHP | SD107702 | 07/19/2020 | 08/02/2020 | 15 | 2 | 2 |  | 2.9 | 30.78 | 56.67
Safety Joint / Agitator/Shocksub | AGHF0675-0059 | 07/09/2020 | 08/02/2020 | 25 | 2 | 2 |  | 2.9 | 30.78 | 56.67
Ulterra RPS 613 6x16s | 48479 | 07/09/2020 | 08/02/2020 | 25 | 2 | 3 |  | 2.52 | 25 | 58
5" 6/7 8.8 Stg 2? FBH TS | MTR475113 | 07/23/2020 | 07/27/2020 | 5 | 2 | 3 |  | 2.52 | 25 | 58
BTI Valve | 30-10063 | 07/23/2020 | 08/02/2020 | 11 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
NM Pony collar | SD56841 | 07/23/2020 | 08/03/2020 | 12 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
UBHO | ZSB500029 | 07/23/2020 | 08/02/2020 | 11 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
NM Drill collar | SD56703 | 07/23/2020 | 08/03/2020 | 12 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
NM Drill collar | SD56284 | 07/23/2020 | 08/03/2020 | 12 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
DS42 Box X XT39 Pin | SD119312 | 07/23/2020 | 08/03/2020 | 12 | 2 | 3 |  | 2.52 | 25 | 58
Delta 425 Box x DS42 Pin | DR38846 | 07/24/2020 | 08/02/2020 | 10 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
Agitator | 0525-00035 | 07/09/2020 | 08/02/2020 | 25 | 2 | 3 |  | 2.52 | 25 | 58
DS42 Box x Delta 425 Pin | DR38852 | 07/24/2020 | 08/02/2020 | 10 | 9 | 3 ,4 ,5 |  | 17.4 | 90.35 | 218.47
Ulterra RPS 613 6x16s | 50597 | 07/23/2020 | 08/02/2020 | 11 | 3 | 4 |  | 10.37 | 5.35 | 62
5" 6/7 8.8 Stg 2? FBH TS | MTR500048 | 07/23/2020 | 08/02/2020 | 11 | 3 | 4 |  | 10.37 | 5.35 | 62
Float sub w/Restrictor sub jetted 20/32 | SD119029 | 07/23/2020 | 08/03/2020 | 12 | 7 | 4 ,5 |  | 14.88 | 65.35 | 160.47
DS42 Box X XT39 Pin | SD119313 | 07/23/2020 | 08/02/2020 | 11 | 7 | 4 ,5 |  | 14.88 | 65.35 | 160.47
Agitator | 525005 | 07/09/2020 | 08/02/2020 | 25 | 3 | 4 |  | 10.37 | 5.35 | 62
Halliburton GTD64M (Jetted 6x16s) | 1138553 | 07/29/2020 | 08/02/2020 | 5 | 4 | 5 |  | 4.52 | 60 | 98.47
5" 6/7 8.8 Stg 2? FBH TS | PPM250009 | 07/27/2020 | 08/02/2020 | 7 | 4 | 5 |  | 4.52 | 60 | 98.47
Agitator | AGHF0525-0004 | 07/23/2020 | 08/02/2020 | 11 | 4 | 5 |  | 4.52 | 60 | 98.47
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well
Facility |  |  | Dietz-Palo-Acadia - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Dietz 3H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Dietz 3H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 367.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Dietz-Palo-Acadia - Washington County, TX
Map Northing |  |  | 216277.80 US survey foot |  |  | Map Easting |  |  | 3143523.74 US survey foot
Latitude |  |  | 30° 12' 36.59611" N |  |  | Longitude |  |  | 96° 42' 45.47858" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.865
Well: |  |  | Dietz 3H
Local North |  |  | 0.01 Usft |  |  | Local East |  |  | -0.00 Usft
Map Northing |  |  | 216277.81 US survey foot |  |  | Map Easting |  |  | 3143523.74 US survey foot
Latitude |  |  | 30° 12' 36.596" N |  |  | Longitude |  |  | 96° 42' 45.479" W
Depth Datum |  |  | Well |  |  | Datum Elevation |  |  | 367.00 Usft
GL Elevation |  |  | 339.00 Usft
Grid Convergence |  |  | 1.865
Well bore: |  |  | Dietz 3H
Magnetic Model |  |  | User Defined |  |  | Date |  |  | 15/07/2020
Total Field (nT) |  |  | 46697.3 |  |  | Dip Angle (°) |  |  | 58.85
Declination (°) |  |  | 3.017
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 336.31
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Dietz 3H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2695 |  |  | Dietz 3H S1 |  |  | MWD+HDGM
2695 |  |  | 10181 |  |  | Dietz 3H S2 |  |  | MWD+HDGM
10181 |  |  | 17841 |  |  | Dietz 3H S3 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -367 | 216277.81 | 3143523.74 | 30.2102 | -96.7126 | 0
139 | 0.6 | 125.1 | 139 | -0.42 | 0.6 | -0.62 | 0.43 | 0.43 | 90 | 125.1 | 139 | -228 | 216277.39 | 3143524.34 | 30.2102 | -96.7126 | 125.1
231 | 0.6 | 137.2 | 230.99 | -1.05 | 1.32 | -1.49 | 0.14 | 0 | 13.15 | 96.05 | 92 | -136.01 | 216276.76 | 3143525.06 | 30.2102 | -96.7126 | 128.54
324 | 0.5 | 141 | 323.99 | -1.72 | 1.9 | -2.34 | 0.11 | -0.11 | 4.09 | 161.85 | 93 | -43.01 | 216276.09 | 3143525.64 | 30.2102 | -96.7126 | 132.13
418 | 0.6 | 136.2 | 417.98 | -2.4 | 2.5 | -3.2 | 0.12 | 0.11 | -5.11 | -27.15 | 94 | 50.98 | 216275.41 | 3143526.24 | 30.2102 | -96.7126 | 133.76
512 | 1.1 | 129.3 | 511.97 | -3.32 | 3.54 | -4.46 | 0.54 | 0.53 | -7.34 | -15.03 | 94 | 144.97 | 216274.49 | 3143527.28 | 30.2102 | -96.7126 | 133.18
606 | 2.1 | 103.2 | 605.94 | -4.29 | 5.92 | -6.3 | 1.29 | 1.06 | -27.77 | -49.61 | 94 | 238.94 | 216273.52 | 3143529.66 | 30.2102 | -96.7126 | 125.93
701 | 2.9 | 94.1 | 700.84 | -4.86 | 10.01 | -8.47 | 0.94 | 0.84 | -9.58 | -30.98 | 95 | 333.84 | 216272.95 | 3143533.75 | 30.2102 | -96.7126 | 115.89
794 | 3.8 | 89.3 | 793.68 | -4.99 | 15.44 | -10.77 | 1.01 | 0.97 | -5.16 | -19.72 | 93 | 426.68 | 216272.82 | 3143539.18 | 30.2102 | -96.7126 | 107.9
888 | 4 | 85.4 | 887.47 | -4.69 | 21.82 | -13.06 | 0.35 | 0.21 | -4.15 | -54.94 | 94 | 520.47 | 216273.12 | 3143545.56 | 30.2102 | -96.7126 | 102.12
982 | 4.6 | 90.6 | 981.2 | -4.46 | 28.86 | -15.68 | 0.76 | 0.64 | 5.53 | 35.63 | 94 | 614.2 | 216273.35 | 3143552.6 | 30.2102 | -96.7125 | 98.79
1077 | 5.2 | 99.6 | 1075.86 | -5.22 | 36.91 | -19.61 | 1.02 | 0.63 | 9.47 | 56.57 | 95 | 708.86 | 216272.59 | 3143560.65 | 30.2101 | -96.7125 | 98.05
1170 | 6 | 108.5 | 1168.41 | -7.47 | 45.67 | -25.19 | 1.27 | 0.86 | 9.57 | 51.84 | 93 | 801.41 | 216270.34 | 3143569.41 | 30.2101 | -96.7125 | 99.28
1266 | 7.3 | 117.3 | 1263.77 | -11.86 | 55.85 | -33.3 | 1.72 | 1.35 | 9.17 | 42.52 | 96 | 896.77 | 216265.95 | 3143579.59 | 30.2101 | -96.7125 | 101.98
1359 | 8.1 | 127.1 | 1355.93 | -18.52 | 66.33 | -43.61 | 1.65 | 0.86 | 10.54 | 63.57 | 93 | 988.93 | 216259.29 | 3143590.07 | 30.2101 | -96.7124 | 105.6
1454 | 9.9 | 134.8 | 1449.76 | -28.31 | 77.46 | -57.05 | 2.28 | 1.89 | 8.11 | 37.63 | 95 | 1082.76 | 216249.5 | 3143601.2 | 30.2101 | -96.7124 | 110.08
1547 | 11.4 | 137 | 1541.16 | -40.67 | 89.41 | -73.16 | 1.67 | 1.61 | 2.37 | 16.25 | 93 | 1174.16 | 216237.14 | 3143613.15 | 30.21 | -96.7124 | 114.46
1641 | 13.1 | 137 | 1633.01 | -55.25 | 103.01 | -91.98 | 1.81 | 1.81 | 0 | 0 | 94 | 1266.01 | 216222.56 | 3143626.75 | 30.21 | -96.7123 | 118.21
1734 | 14.1 | 138.6 | 1723.41 | -71.46 | 117.69 | -112.72 | 1.15 | 1.08 | 1.72 | 21.4 | 93 | 1356.41 | 216206.35 | 3143641.43 | 30.21 | -96.7123 | 121.27
1829 | 14.3 | 137 | 1815.5 | -88.72 | 133.34 | -134.82 | 0.46 | 0.21 | -1.68 | -63.78 | 95 | 1448.5 | 216189.09 | 3143657.08 | 30.2099 | -96.7122 | 123.64
1924 | 14.9 | 135.9 | 1907.44 | -106.07 | 149.84 | -157.34 | 0.7 | 0.63 | -1.16 | -25.34 | 95 | 1540.44 | 216171.74 | 3143673.58 | 30.2099 | -96.7122 | 125.29
2018 | 14.6 | 136 | 1998.34 | -123.27 | 166.48 | -179.77 | 0.32 | -0.32 | 0.11 | 175.2 | 94 | 1631.34 | 216154.54 | 3143690.22 | 30.2098 | -96.7121 | 126.52
2112 | 13.9 | 135.6 | 2089.45 | -139.86 | 182.61 | -201.45 | 0.75 | -0.74 | -0.43 | -172.19 | 94 | 1722.45 | 216137.95 | 3143706.35 | 30.2098 | -96.7121 | 127.45
2207 | 14.1 | 135.3 | 2181.62 | -156.24 | 198.74 | -222.92 | 0.22 | 0.21 | -0.32 | -20.09 | 95 | 1814.62 | 216121.57 | 3143722.48 | 30.2097 | -96.712 | 128.17
2300 | 15 | 135.6 | 2271.64 | -172.89 | 215.13 | -244.76 | 0.97 | 0.97 | 0.32 | 4.93 | 93 | 1904.64 | 216104.92 | 3143738.87 | 30.2097 | -96.712 | 128.79
2394 | 14.7 | 134.1 | 2362.5 | -189.88 | 232.2 | -267.18 | 0.52 | -0.32 | -1.6 | -128.69 | 94 | 1995.5 | 216087.93 | 3143755.94 | 30.2096 | -96.7119 | 129.27
2488 | 14.5 | 133.5 | 2453.47 | -206.28 | 249.3 | -289.07 | 0.27 | -0.21 | -0.64 | -143.19 | 94 | 2086.47 | 216071.53 | 3143773.04 | 30.2096 | -96.7119 | 129.61
2582 | 14.4 | 130.4 | 2544.49 | -221.96 | 266.74 | -310.43 | 0.83 | -0.11 | -3.3 | -98.87 | 94 | 2177.49 | 216055.85 | 3143790.48 | 30.2095 | -96.7118 | 129.76
2695 | 14.1 | 128.4 | 2654.02 | -239.61 | 288.23 | -335.23 | 0.51 | -0.27 | -1.77 | -122.32 | 113 | 2287.02 | 216038.2 | 3143811.97 | 30.2095 | -96.7117 | 129.74
2797 | 13.8 | 127.4 | 2753.01 | -254.72 | 307.63 | -356.86 | 0.38 | -0.29 | -0.98 | -141.7 | 102 | 2386.01 | 216023.09 | 3143831.37 | 30.2094 | -96.7117 | 129.63
2891 | 13 | 128.2 | 2844.45 | -268.07 | 324.84 | -376 | 0.87 | -0.85 | 0.85 | 167.34 | 94 | 2477.45 | 216009.74 | 3143848.58 | 30.2094 | -96.7116 | 129.53
2985 | 14.3 | 133.2 | 2935.79 | -282.55 | 341.62 | -396 | 1.87 | 1.38 | 5.32 | 44.68 | 94 | 2568.79 | 215995.26 | 3143865.36 | 30.2094 | -96.7116 | 129.59
3079 | 14.7 | 130.7 | 3026.8 | -298.28 | 359.12 | -417.43 | 0.79 | 0.43 | -2.66 | -58.63 | 94 | 2659.8 | 215979.53 | 3143882.86 | 30.2093 | -96.7115 | 129.71
3173 | 14.6 | 127.8 | 3117.75 | -313.32 | 377.52 | -438.6 | 0.79 | -0.11 | -3.09 | -99.17 | 94 | 2750.75 | 215964.49 | 3143901.26 | 30.2093 | -96.7115 | 129.69
3266 | 15.4 | 131 | 3207.58 | -328.6 | 396.11 | -460.06 | 1.24 | 0.86 | 3.44 | 47.55 | 93 | 2840.58 | 215949.21 | 3143919.85 | 30.2092 | -96.7114 | 129.68
3360 | 15.6 | 132.1 | 3298.16 | -345.27 | 414.9 | -482.87 | 0.38 | 0.21 | 1.17 | 56.3 | 94 | 2931.16 | 215932.54 | 3143938.64 | 30.2092 | -96.7114 | 129.77
3454 | 14.9 | 136.9 | 3388.85 | -362.56 | 432.54 | -505.8 | 1.54 | -0.74 | 5.11 | 121.31 | 94 | 3021.85 | 215915.25 | 3143956.28 | 30.2091 | -96.7113 | 129.97
3548 | 14.2 | 136.1 | 3479.84 | -379.7 | 448.79 | -528.02 | 0.77 | -0.74 | -0.85 | -164.37 | 94 | 3112.84 | 215898.11 | 3143972.53 | 30.2091 | -96.7113 | 130.23
3642 | 14.2 | 135.9 | 3570.97 | -396.28 | 464.81 | -549.65 | 0.05 | 0 | -0.21 | -90.1 | 94 | 3203.97 | 215881.53 | 3143988.55 | 30.209 | -96.7112 | 130.45
3736 | 14.2 | 140.8 | 3662.1 | -413.5 | 480.12 | -571.56 | 1.28 | 0 | 5.21 | 92.38 | 94 | 3295.1 | 215864.31 | 3144003.86 | 30.209 | -96.7112 | 130.74
3830 | 14.2 | 142.2 | 3753.23 | -431.54 | 494.47 | -593.85 | 0.37 | 0 | 1.49 | 90.68 | 94 | 3386.23 | 215846.27 | 3144018.21 | 30.2089 | -96.7111 | 131.11
3925 | 14.5 | 142.3 | 3845.26 | -450.16 | 508.89 | -616.69 | 0.32 | 0.32 | 0.11 | 4.77 | 95 | 3478.26 | 215827.65 | 3144032.63 | 30.2089 | -96.7111 | 131.5
4018 | 15 | 141.2 | 3935.2 | -468.75 | 523.55 | -639.61 | 0.62 | 0.54 | -1.18 | -29.79 | 93 | 3568.2 | 215809.06 | 3144047.29 | 30.2088 | -96.711 | 131.84
4112 | 14.9 | 141 | 4026.01 | -487.62 | 538.78 | -663.01 | 0.12 | -0.11 | -0.21 | -152.81 | 94 | 3659.01 | 215790.19 | 3144062.52 | 30.2088 | -96.711 | 132.15
4206 | 15.2 | 140.1 | 4116.79 | -506.47 | 554.29 | -686.5 | 0.4 | 0.32 | -0.96 | -38.35 | 94 | 3749.79 | 215771.34 | 3144078.03 | 30.2087 | -96.7109 | 132.42
4301 | 14.9 | 139.4 | 4208.53 | -525.3 | 570.23 | -710.14 | 0.37 | -0.32 | -0.74 | -149.13 | 95 | 3841.53 | 215752.51 | 3144093.97 | 30.2087 | -96.7109 | 132.65
4395 | 14.6 | 137.6 | 4299.43 | -543.22 | 586.08 | -732.93 | 0.58 | -0.32 | -1.91 | -124.08 | 94 | 3932.43 | 215734.59 | 3144109.82 | 30.2086 | -96.7108 | 132.83
4490 | 14.9 | 136.1 | 4391.3 | -560.87 | 602.62 | -755.73 | 0.51 | 0.32 | -1.58 | -52.58 | 95 | 4024.3 | 215716.94 | 3144126.36 | 30.2086 | -96.7108 | 132.94
4584 | 14.5 | 135.3 | 4482.23 | -577.94 | 619.28 | -778.06 | 0.48 | -0.43 | -0.85 | -153.48 | 94 | 4115.23 | 215699.87 | 3144143.02 | 30.2085 | -96.7107 | 133.02
4677 | 14.1 | 136 | 4572.35 | -594.36 | 635.34 | -799.55 | 0.47 | -0.43 | 0.75 | 156.96 | 93 | 4205.35 | 215683.45 | 3144159.08 | 30.2085 | -96.7107 | 133.09
4772 | 13.6 | 134.7 | 4664.58 | -610.54 | 651.32 | -820.78 | 0.62 | -0.53 | -1.37 | -148.73 | 95 | 4297.58 | 215667.27 | 3144175.06 | 30.2084 | -96.7106 | 133.15
4867 | 13.8 | 131.5 | 4756.88 | -625.91 | 667.74 | -841.45 | 0.82 | 0.21 | -3.37 | -76.78 | 95 | 4389.88 | 215651.9 | 3144191.48 | 30.2084 | -96.7106 | 133.15
4961 | 13.2 | 132.1 | 4848.28 | -640.53 | 684.1 | -861.42 | 0.66 | -0.64 | 0.64 | 167.15 | 94 | 4481.28 | 215637.28 | 3144207.84 | 30.2083 | -96.7105 | 133.12
5055 | 12.6 | 130 | 4939.91 | -654.32 | 699.92 | -880.4 | 0.81 | -0.64 | -2.23 | -143.02 | 94 | 4572.91 | 215623.49 | 3144223.66 | 30.2083 | -96.7105 | 133.07
5149 | 14.5 | 134 | 5031.29 | -669.08 | 716.24 | -900.48 | 2.25 | 2.02 | 4.26 | 28.21 | 94 | 4664.29 | 215608.73 | 3144239.98 | 30.2083 | -96.7104 | 133.05
5243 | 15.6 | 136.9 | 5122.07 | -686.49 | 733.34 | -923.29 | 1.42 | 1.17 | 3.09 | 35.8 | 94 | 4755.07 | 215591.32 | 3144257.08 | 30.2082 | -96.7104 | 133.11
5336 | 15.4 | 136.9 | 5211.69 | -704.64 | 750.32 | -946.73 | 0.22 | -0.22 | 0 | 180 | 93 | 4844.69 | 215573.17 | 3144274.06 | 30.2082 | -96.7103 | 133.2
5430 | 15.1 | 133.7 | 5302.38 | -722.21 | 767.7 | -969.8 | 0.95 | -0.32 | -3.4 | -111.16 | 94 | 4935.38 | 215555.6 | 3144291.44 | 30.2081 | -96.7103 | 133.25
5523 | 15.4 | 133.8 | 5392.1 | -739.12 | 785.37 | -992.39 | 0.32 | 0.32 | 0.11 | 5.06 | 93 | 5025.1 | 215538.69 | 3144309.11 | 30.2081 | -96.7102 | 133.26
5617 | 14.2 | 137.3 | 5482.98 | -756.24 | 802.2 | -1014.83 | 1.59 | -1.28 | 3.72 | 145 | 94 | 5115.98 | 215521.57 | 3144325.94 | 30.208 | -96.7102 | 133.31
5712 | 14.5 | 137.6 | 5575.02 | -773.58 | 818.12 | -1037.11 | 0.33 | 0.32 | 0.32 | 14.07 | 95 | 5208.02 | 215504.23 | 3144341.86 | 30.208 | -96.7101 | 133.4
5806 | 13.6 | 136.6 | 5666.21 | -790.3 | 833.65 | -1058.66 | 0.99 | -0.96 | -1.06 | -165.39 | 94 | 5299.21 | 215487.51 | 3144357.39 | 30.2079 | -96.7101 | 133.47
5900 | 12.6 | 135.4 | 5757.76 | -805.63 | 848.44 | -1078.64 | 1.1 | -1.06 | -1.28 | -165.37 | 94 | 5390.76 | 215472.18 | 3144372.18 | 30.2079 | -96.71 | 133.52
5994 | 12.3 | 134.7 | 5849.55 | -819.98 | 862.76 | -1097.53 | 0.36 | -0.32 | -0.74 | -153.64 | 94 | 5482.55 | 215457.83 | 3144386.5 | 30.2078 | -96.71 | 133.54
6087 | 11.6 | 132.7 | 5940.53 | -833.28 | 876.67 | -1115.3 | 0.87 | -0.75 | -2.15 | -150.37 | 93 | 5573.53 | 215444.53 | 3144400.41 | 30.2078 | -96.7099 | 133.55
6181 | 13.7 | 136.4 | 6032.25 | -847.76 | 891.3 | -1134.43 | 2.39 | 2.23 | 3.94 | 22.91 | 94 | 5665.25 | 215430.05 | 3144415.04 | 30.2078 | -96.7099 | 133.57
6275 | 14.5 | 138.4 | 6123.42 | -864.62 | 906.79 | -1156.1 | 1 | 0.85 | 2.13 | 32.32 | 94 | 5756.42 | 215413.19 | 3144430.53 | 30.2077 | -96.7099 | 133.64
6368 | 13.2 | 138.6 | 6213.71 | -881.29 | 921.54 | -1177.29 | 1.4 | -1.4 | 0.22 | 177.99 | 93 | 5846.71 | 215396.52 | 3144445.28 | 30.2077 | -96.7098 | 133.72
6462 | 14.2 | 138.2 | 6305.04 | -897.94 | 936.32 | -1198.47 | 1.07 | 1.06 | -0.43 | -5.61 | 94 | 5938.04 | 215379.87 | 3144460.06 | 30.2076 | -96.7098 | 133.8
6556 | 14.5 | 138.5 | 6396.1 | -915.34 | 951.8 | -1220.63 | 0.33 | 0.32 | 0.32 | 14.07 | 94 | 6029.1 | 215362.47 | 3144475.54 | 30.2076 | -96.7097 | 133.88
6650 | 14.4 | 136.7 | 6487.13 | -932.66 | 967.62 | -1242.85 | 0.49 | -0.11 | -1.91 | -103.42 | 94 | 6120.13 | 215345.15 | 3144491.36 | 30.2075 | -96.7097 | 133.95
6744 | 13.2 | 137.6 | 6578.41 | -949.1 | 982.87 | -1264.03 | 1.3 | -1.28 | 0.96 | 170.29 | 94 | 6211.41 | 215328.71 | 3144506.61 | 30.2075 | -96.7096 | 134
6837 | 12.7 | 136.3 | 6669.05 | -964.33 | 997.09 | -1283.69 | 0.62 | -0.54 | -1.4 | -150.4 | 93 | 6302.05 | 215313.48 | 3144520.83 | 30.2074 | -96.7096 | 134.04
6932 | 12.1 | 134.4 | 6761.83 | -978.85 | 1011.42 | -1302.74 | 0.76 | -0.63 | -2 | -146.71 | 95 | 6394.83 | 215298.96 | 3144535.16 | 30.2074 | -96.7095 | 134.06
7026 | 12.1 | 137.3 | 6853.75 | -992.98 | 1025.14 | -1321.19 | 0.65 | 0 | 3.09 | 91.42 | 94 | 6486.75 | 215284.83 | 3144548.88 | 30.2073 | -96.7095 | 134.09
7120 | 13.7 | 137.8 | 6945.37 | -1008.47 | 1039.3 | -1341.07 | 1.71 | 1.7 | 0.53 | 4.23 | 94 | 6578.37 | 215269.34 | 3144563.04 | 30.2073 | -96.7094 | 134.14
7214 | 12.9 | 137.9 | 7036.85 | -1024.5 | 1053.82 | -1361.58 | 0.85 | -0.85 | 0.11 | 178.4 | 94 | 6669.85 | 215253.31 | 3144577.56 | 30.2073 | -96.7094 | 134.19
7308 | 11.8 | 135.2 | 7128.67 | -1039.1 | 1067.62 | -1380.5 | 1.32 | -1.17 | -2.87 | -153.62 | 94 | 6761.67 | 215238.71 | 3144591.36 | 30.2072 | -96.7094 | 134.22
7402 | 10.2 | 133.7 | 7220.94 | -1051.68 | 1080.41 | -1397.15 | 1.73 | -1.7 | -1.6 | -170.59 | 94 | 6853.94 | 215226.13 | 3144604.15 | 30.2072 | -96.7093 | 134.23
7496 | 10.6 | 137.6 | 7313.4 | -1063.81 | 1092.26 | -1413.02 | 0.86 | 0.43 | 4.15 | 62.32 | 94 | 6946.4 | 215214 | 3144616 | 30.2071 | -96.7093 | 134.24
7589 | 8.5 | 142.7 | 7405.11 | -1075.6 | 1102.19 | -1427.81 | 2.43 | -2.26 | 5.48 | 160.56 | 93 | 7038.11 | 215202.21 | 3144625.93 | 30.2071 | -96.7093 | 134.3
7682 | 9.4 | 138.5 | 7496.97 | -1086.75 | 1111.39 | -1441.72 | 1.2 | 0.97 | -4.52 | -38.07 | 93 | 7129.97 | 215191.06 | 3144635.13 | 30.2071 | -96.7092 | 134.36
7776 | 11.3 | 141.3 | 7589.44 | -1099.69 | 1122.24 | -1457.92 | 2.09 | 2.02 | 2.98 | 16.21 | 94 | 7222.44 | 215178.12 | 3144645.98 | 30.207 | -96.7092 | 134.42
7870 | 11.5 | 136.5 | 7681.59 | -1113.67 | 1134.45 | -1475.64 | 1.03 | 0.21 | -5.11 | -80.46 | 94 | 7314.59 | 215164.14 | 3144658.19 | 30.207 | -96.7092 | 134.47
7964 | 12 | 136.2 | 7773.62 | -1127.52 | 1147.66 | -1493.63 | 0.54 | 0.53 | -0.32 | -7.11 | 94 | 7406.62 | 215150.29 | 3144671.4 | 30.207 | -96.7091 | 134.49
8058 | 11.3 | 135.4 | 7865.68 | -1141.13 | 1160.89 | -1511.41 | 0.76 | -0.74 | -0.85 | -167.4 | 94 | 7498.68 | 215136.68 | 3144684.63 | 30.2069 | -96.7091 | 134.51
8153 | 9 | 138.3 | 7959.19 | -1153.31 | 1172.37 | -1527.17 | 2.48 | -2.42 | 3.05 | 168.9 | 95 | 7592.19 | 215124.5 | 3144696.11 | 30.2069 | -96.709 | 134.53
8247 | 7.2 | 136.7 | 8052.25 | -1163.09 | 1181.3 | -1539.71 | 1.93 | -1.91 | -1.7 | -173.65 | 94 | 7685.25 | 215114.72 | 3144705.04 | 30.2069 | -96.709 | 134.55
8340 | 5.4 | 136.7 | 8144.68 | -1170.52 | 1188.3 | -1549.32 | 1.94 | -1.94 | 0 | 180 | 93 | 7777.68 | 215107.29 | 3144712.04 | 30.2068 | -96.709 | 134.57
8434 | 4 | 139.9 | 8238.36 | -1176.24 | 1193.45 | -1556.64 | 1.51 | -1.49 | 3.4 | 170.98 | 94 | 7871.36 | 215101.57 | 3144717.19 | 30.2068 | -96.709 | 134.58
8529 | 2.9 | 139.2 | 8333.19 | -1180.6 | 1197.15 | -1562.11 | 1.16 | -1.16 | -0.74 | -178.16 | 95 | 7966.19 | 215097.21 | 3144720.89 | 30.2068 | -96.709 | 134.6
8623 | 2.9 | 135.8 | 8427.07 | -1184.1 | 1200.36 | -1566.61 | 0.18 | 0 | -3.62 | -91.7 | 94 | 8060.07 | 215093.71 | 3144724.1 | 30.2068 | -96.709 | 134.61
8717 | 2.6 | 136.9 | 8520.96 | -1187.36 | 1203.48 | -1570.85 | 0.32 | -0.32 | 1.17 | 170.57 | 94 | 8153.96 | 215090.45 | 3144727.22 | 30.2068 | -96.7089 | 134.61
8812 | 2 | 143.6 | 8615.88 | -1190.27 | 1205.93 | -1574.5 | 0.69 | -0.63 | 7.05 | 159.18 | 95 | 8248.88 | 215087.54 | 3144729.67 | 30.2068 | -96.7089 | 134.63
8906 | 2.5 | 89.3 | 8709.82 | -1191.57 | 1208.96 | -1576.9 | 2.23 | 0.53 | -57.77 | -104.9 | 94 | 8342.82 | 215086.24 | 3144732.7 | 30.2068 | -96.7089 | 134.58
8997 | 2.7 | 62.3 | 8800.73 | -1190.55 | 1212.84 | -1577.53 | 1.35 | 0.22 | -29.67 | -94.38 | 91 | 8433.73 | 215087.26 | 3144736.58 | 30.2068 | -96.7089 | 134.47
9090 | 2.5 | 45.2 | 8893.64 | -1188.1 | 1216.22 | -1576.64 | 0.86 | -0.22 | -18.39 | -112.9 | 93 | 8526.64 | 215089.71 | 3144739.96 | 30.2068 | -96.7089 | 134.33
9184 | 1.4 | 23.5 | 8987.58 | -1185.6 | 1218.13 | -1575.12 | 1.39 | -1.17 | -23.09 | -156.65 | 94 | 8620.58 | 215092.21 | 3144741.87 | 30.2068 | -96.7089 | 134.22
9278 | 0.4 | 45.4 | 9081.57 | -1184.32 | 1218.82 | -1574.23 | 1.11 | -1.06 | 23.3 | 171.75 | 94 | 8714.57 | 215093.49 | 3144742.56 | 30.2068 | -96.7089 | 134.18
9372 | 0.7 | 55.7 | 9175.57 | -1183.76 | 1219.53 | -1574 | 0.33 | 0.32 | 10.96 | 23.44 | 94 | 8808.57 | 215094.05 | 3144743.27 | 30.2068 | -96.7089 | 134.15
9465 | 1.3 | 56.9 | 9268.55 | -1182.87 | 1220.88 | -1573.73 | 0.65 | 0.65 | 1.29 | 2.6 | 93 | 8901.55 | 215094.94 | 3144744.62 | 30.2068 | -96.7089 | 134.09
9559 | 2.6 | 355.7 | 9362.5 | -1180.16 | 1221.62 | -1571.54 | 2.42 | 1.38 | 65.11 | -91.18 | 94 | 8995.5 | 215097.65 | 3144745.36 | 30.2068 | -96.7089 | 134.01
9653 | 5.5 | 332.8 | 9456.26 | -1174.02 | 1219.4 | -1565.03 | 3.47 | 3.09 | -24.36 | -40.91 | 94 | 9089.26 | 215103.79 | 3144743.14 | 30.2068 | -96.7089 | 133.91
9747 | 7.7 | 331.5 | 9549.63 | -1164.48 | 1214.33 | -1554.26 | 2.35 | 2.34 | -1.38 | -4.53 | 94 | 9182.63 | 215113.33 | 3144738.07 | 30.2069 | -96.7089 | 133.8
9841 | 9.1 | 333.2 | 9642.62 | -1152.31 | 1207.98 | -1540.56 | 1.51 | 1.49 | 1.81 | 10.9 | 94 | 9275.62 | 215125.5 | 3144731.72 | 30.2069 | -96.7089 | 133.65
9935 | 10.4 | 341.5 | 9735.27 | -1137.63 | 1201.93 | -1524.69 | 2.03 | 1.38 | 8.83 | 51.38 | 94 | 9368.27 | 215140.18 | 3144725.67 | 30.2069 | -96.7089 | 133.43
10028 | 13.5 | 338.8 | 9826.24 | -1119.54 | 1195.34 | -1505.48 | 3.39 | 3.33 | -2.9 | -11.55 | 93 | 9459.24 | 215158.27 | 3144719.08 | 30.207 | -96.709 | 133.12
10121 | 16.4 | 337.6 | 9916.09 | -1097.28 | 1186.41 | -1481.5 | 3.14 | 3.12 | -1.29 | -6.67 | 93 | 9549.09 | 215180.53 | 3144710.15 | 30.207 | -96.709 | 132.76
10181 | 17.3 | 336 | 9973.51 | -1081.3 | 1179.55 | -1464.11 | 1.69 | 1.5 | -2.67 | -28.03 | 60 | 9606.51 | 215196.51 | 3144703.29 | 30.2071 | -96.709 | 132.51
10256 | 20.2 | 338.1 | 10044.52 | -1059.09 | 1170.19 | -1440.01 | 3.97 | 3.87 | 2.8 | 14.1 | 75 | 9677.52 | 215218.72 | 3144693.93 | 30.2071 | -96.709 | 132.15
10351 | 28 | 336.6 | 10131.18 | -1023.35 | 1155.19 | -1401.26 | 8.24 | 8.21 | -1.58 | -5.18 | 95 | 9764.18 | 215254.46 | 3144678.93 | 30.2072 | -96.7091 | 131.54
10447 | 30.5 | 332.1 | 10214.94 | -981.13 | 1134.83 | -1354.42 | 3.47 | 2.6 | -4.69 | -43.31 | 96 | 9847.94 | 215296.68 | 3144658.57 | 30.2074 | -96.7091 | 130.85
10542 | 43.6 | 334.3 | 10290.6 | -930.08 | 1109.24 | -1297.38 | 13.86 | 13.79 | 2.32 | 6.67 | 95 | 9923.6 | 215347.73 | 3144632.98 | 30.2075 | -96.7092 | 129.98
10638 | 46 | 332.9 | 10358.71 | -869.51 | 1079.15 | -1229.82 | 2.7 | 2.5 | -1.46 | -22.84 | 96 | 9991.71 | 215408.3 | 3144602.89 | 30.2077 | -96.7093 | 128.86
10685 | 49.9 | 334.2 | 10390.19 | -838.26 | 1063.62 | -1194.97 | 8.55 | 8.3 | 2.77 | 14.34 | 47 | 10023.19 | 215439.55 | 3144587.36 | 30.2078 | -96.7094 | 128.24
10732 | 57.7 | 335.1 | 10417.93 | -804.01 | 1047.4 | -1157.09 | 16.67 | 16.6 | 1.91 | 5.59 | 47 | 10050.93 | 215473.8 | 3144571.14 | 30.2079 | -96.7094 | 127.51
10779 | 62.1 | 338.3 | 10441.49 | -766.67 | 1031.35 | -1116.45 | 11.06 | 9.36 | 6.81 | 32.99 | 47 | 10074.49 | 215511.14 | 3144555.09 | 30.208 | -96.7094 | 126.63
10826 | 67.7 | 340.8 | 10461.43 | -726.8 | 1016.51 | -1073.98 | 12.85 | 11.91 | 5.32 | 22.55 | 47 | 10094.43 | 215551.01 | 3144540.25 | 30.2081 | -96.7095 | 125.56
10873 | 72.6 | 338.6 | 10477.38 | -685.36 | 1001.16 | -1029.86 | 11.32 | 10.43 | -4.68 | -23.28 | 47 | 10110.38 | 215592.45 | 3144524.9 | 30.2082 | -96.7095 | 124.39
10921 | 78.9 | 337 | 10489.19 | -642.31 | 983.59 | -983.38 | 13.52 | 13.12 | -3.33 | -14.03 | 48 | 10122.19 | 215635.5 | 3144507.33 | 30.2083 | -96.7096 | 123.15
10968 | 81.5 | 335.3 | 10497.19 | -599.96 | 964.86 | -937.07 | 6.58 | 5.53 | -3.62 | -32.94 | 47 | 10130.19 | 215677.85 | 3144488.6 | 30.2084 | -96.7096 | 121.87
11017 | 84.2 | 334.1 | 10503.29 | -556.01 | 944.08 | -888.48 | 6.02 | 5.51 | -2.45 | -23.87 | 49 | 10136.29 | 215721.8 | 3144467.82 | 30.2086 | -96.7097 | 120.5
11064 | 85.1 | 332.8 | 10507.67 | -514.15 | 923.17 | -841.74 | 3.35 | 1.91 | -2.77 | -55.25 | 47 | 10140.67 | 215763.66 | 3144446.91 | 30.2087 | -96.7098 | 119.12
11111 | 85.9 | 331.5 | 10511.36 | -472.72 | 901.28 | -795.01 | 3.24 | 1.7 | -2.77 | -58.37 | 47 | 10144.36 | 215805.09 | 3144425.02 | 30.2088 | -96.7098 | 117.68
11206 | 92.7 | 333.5 | 10512.52 | -388.52 | 857.44 | -700.29 | 7.46 | 7.16 | 2.11 | 16.41 | 95 | 10145.52 | 215889.29 | 3144381.18 | 30.209 | -96.71 | 114.38
11301 | 93.7 | 332.3 | 10507.22 | -304.08 | 814.24 | -605.61 | 1.64 | 1.05 | -1.26 | -50.12 | 95 | 10140.22 | 215973.73 | 3144337.98 | 30.2093 | -96.7101 | 110.48
11397 | 93.9 | 335 | 10500.85 | -218.25 | 771.72 | -509.93 | 2.81 | 0.21 | 2.81 | 85.67 | 96 | 10133.85 | 216059.56 | 3144295.46 | 30.2095 | -96.7102 | 105.79
11491 | 91.9 | 337.5 | 10496.1 | -132.33 | 733.92 | -416.06 | 3.4 | -2.13 | 2.66 | 128.63 | 94 | 10129.1 | 216145.48 | 3144257.66 | 30.2097 | -96.7103 | 100.22
11585 | 92.5 | 337.2 | 10492.49 | -45.65 | 697.75 | -322.15 | 0.71 | 0.64 | -0.32 | -26.54 | 94 | 10125.49 | 216232.16 | 3144221.49 | 30.21 | -96.7104 | 93.74
11680 | 91.3 | 341.2 | 10489.34 | 43.09 | 664.04 | -227.34 | 4.39 | -1.26 | 4.21 | 106.63 | 95 | 10122.34 | 216320.9 | 3144187.78 | 30.2102 | -96.7105 | 86.29
11774 | 91.7 | 341.4 | 10486.88 | 132.1 | 633.91 | -133.73 | 0.48 | 0.43 | 0.21 | 26.55 | 94 | 10119.88 | 216409.91 | 3144157.65 | 30.2105 | -96.7106 | 78.23
11868 | 91.2 | 340 | 10484.5 | 220.79 | 602.86 | -40.04 | 1.58 | -0.53 | -1.49 | -109.64 | 94 | 10117.5 | 216498.6 | 3144126.6 | 30.2107 | -96.7107 | 69.89
11964 | 90.6 | 338.5 | 10482.99 | 310.54 | 568.85 | 55.82 | 1.68 | -0.62 | -1.56 | -111.79 | 96 | 10115.99 | 216588.35 | 3144092.59 | 30.211 | -96.7108 | 61.37
12059 | 90.9 | 338.2 | 10481.75 | 398.83 | 533.8 | 150.75 | 0.45 | 0.32 | -0.32 | -45 | 95 | 10114.75 | 216676.64 | 3144057.54 | 30.2112 | -96.7109 | 53.23
12154 | 92.3 | 335.7 | 10479.1 | 486.21 | 496.63 | 245.7 | 3.02 | 1.47 | -2.63 | -60.71 | 95 | 10112.1 | 216764.02 | 3144020.37 | 30.2115 | -96.711 | 45.61
12249 | 93.5 | 334.2 | 10474.29 | 572.16 | 456.46 | 340.54 | 2.02 | 1.26 | -1.58 | -51.27 | 95 | 10107.29 | 216849.97 | 3143980.2 | 30.2117 | -96.7111 | 38.58
12342 | 94.5 | 334.6 | 10467.8 | 655.82 | 416.37 | 433.27 | 1.16 | 1.08 | 0.43 | 21.74 | 93 | 10100.8 | 216933.63 | 3143940.11 | 30.2119 | -96.7112 | 32.41
12437 | 92.4 | 336.3 | 10462.08 | 742.07 | 376.98 | 528.07 | 2.84 | -2.21 | 1.79 | 141.01 | 95 | 10095.08 | 217019.88 | 3143900.72 | 30.2122 | -96.7114 | 26.93
12531 | 92.2 | 334.8 | 10458.31 | 827.57 | 338.1 | 621.99 | 1.61 | -0.21 | -1.6 | -97.57 | 94 | 10091.31 | 217105.38 | 3143861.84 | 30.2124 | -96.7115 | 22.22
12625 | 94 | 334.5 | 10453.23 | 912.39 | 297.92 | 715.81 | 1.94 | 1.91 | -0.32 | -9.44 | 94 | 10086.23 | 217190.2 | 3143821.66 | 30.2126 | -96.7116 | 18.08
12722 | 94.1 | 335.2 | 10446.38 | 999.97 | 256.8 | 812.53 | 0.73 | 0.1 | 0.72 | 81.83 | 97 | 10079.38 | 217277.78 | 3143780.54 | 30.2129 | -96.7117 | 14.4
12818 | 89.9 | 335.2 | 10443.03 | 1087.05 | 216.56 | 908.43 | 4.38 | -4.38 | 0 | 180 | 96 | 10076.03 | 217364.86 | 3143740.3 | 30.2131 | -96.7118 | 11.27
12914 | 87.8 | 334.3 | 10444.96 | 1173.85 | 175.62 | 1004.37 | 2.38 | -2.19 | -0.94 | -156.81 | 96 | 10077.96 | 217451.66 | 3143699.36 | 30.2134 | -96.712 | 8.51
13009 | 92.3 | 334.8 | 10444.87 | 1259.61 | 134.81 | 1099.3 | 4.77 | 4.74 | 0.53 | 6.34 | 95 | 10077.87 | 217537.42 | 3143658.55 | 30.2136 | -96.7121 | 6.11
13104 | 94.8 | 336.8 | 10438.99 | 1346.08 | 95.94 | 1194.1 | 3.37 | 2.63 | 2.11 | 38.55 | 95 | 10071.99 | 217623.89 | 3143619.68 | 30.2139 | -96.7122 | 4.08
13199 | 95.4 | 336.2 | 10430.54 | 1432.86 | 58.21 | 1288.73 | 0.89 | 0.63 | -0.63 | -44.86 | 95 | 10063.54 | 217710.67 | 3143581.95 | 30.2141 | -96.7123 | 2.33
13294 | 94.9 | 336.4 | 10422.02 | 1519.5 | 20.18 | 1383.34 | 0.57 | -0.53 | 0.21 | 158.27 | 95 | 10055.02 | 217797.31 | 3143543.92 | 30.2143 | -96.7124 | 0.76
13390 | 95.3 | 335.8 | 10413.48 | 1606.92 | -18.56 | 1478.96 | 0.75 | 0.42 | -0.62 | -56.18 | 96 | 10046.48 | 217884.73 | 3143505.18 | 30.2146 | -96.7125 | 359.34
13485 | 95.6 | 335.2 | 10404.46 | 1692.97 | -57.77 | 1573.52 | 0.7 | 0.32 | -0.63 | -63.3 | 95 | 10037.46 | 217970.78 | 3143465.97 | 30.2148 | -96.7126 | 358.05
13580 | 96.4 | 334.9 | 10394.53 | 1778.63 | -97.63 | 1667.98 | 0.9 | 0.84 | -0.32 | -20.44 | 95 | 10027.53 | 218056.44 | 3143426.11 | 30.2151 | -96.7128 | 356.86
13676 | 95.3 | 335.2 | 10384.75 | 1865.22 | -137.91 | 1763.45 | 1.19 | -1.15 | 0.31 | 164.81 | 96 | 10017.75 | 218143.03 | 3143385.83 | 30.2153 | -96.7129 | 355.77
13771 | 96.6 | 335 | 10374.9 | 1950.92 | -177.69 | 1857.92 | 1.38 | 1.37 | -0.21 | -8.69 | 95 | 10007.9 | 218228.73 | 3143346.05 | 30.2155 | -96.713 | 354.8
13866 | 92.7 | 336.8 | 10367.2 | 2037.34 | -216.34 | 1952.58 | 4.52 | -4.11 | 1.89 | 155.22 | 95 | 10000.2 | 218315.15 | 3143307.4 | 30.2158 | -96.7131 | 353.94
13961 | 92.2 | 336.5 | 10363.14 | 2124.48 | -253.96 | 2047.49 | 0.61 | -0.53 | -0.32 | -149.05 | 95 | 9996.14 | 218402.29 | 3143269.78 | 30.216 | -96.7132 | 353.18
14055 | 92.3 | 336.7 | 10359.45 | 2210.68 | -291.26 | 2141.42 | 0.24 | 0.11 | 0.21 | 63.41 | 94 | 9992.45 | 218488.49 | 3143232.48 | 30.2163 | -96.7133 | 352.49
14150 | 92.8 | 335.7 | 10355.22 | 2297.51 | -329.56 | 2236.32 | 1.18 | 0.53 | -1.05 | -63.39 | 95 | 9988.22 | 218575.32 | 3143194.18 | 30.2165 | -96.7134 | 351.84
14245 | 91.5 | 335.9 | 10351.66 | 2384.1 | -368.48 | 2331.25 | 1.38 | -1.37 | 0.21 | 171.26 | 95 | 9984.66 | 218661.91 | 3143155.26 | 30.2168 | -96.7136 | 351.21
14340 | 91.7 | 335.5 | 10349 | 2470.65 | -407.56 | 2426.21 | 0.47 | 0.21 | -0.42 | -63.42 | 95 | 9982 | 218748.46 | 3143116.18 | 30.217 | -96.7137 | 350.63
14435 | 91.9 | 335 | 10346.02 | 2556.88 | -447.31 | 2521.14 | 0.57 | 0.21 | -0.53 | -68.18 | 95 | 9979.02 | 218834.69 | 3143076.43 | 30.2172 | -96.7138 | 350.08
14530 | 94.2 | 335.9 | 10340.96 | 2643.16 | -486.72 | 2615.99 | 2.6 | 2.42 | 0.95 | 21.32 | 95 | 9973.96 | 218920.97 | 3143037.02 | 30.2175 | -96.7139 | 349.57
14624 | 95.5 | 335.7 | 10333.02 | 2728.6 | -525.12 | 2709.65 | 1.4 | 1.38 | -0.21 | -8.71 | 94 | 9966.02 | 219006.41 | 3142998.62 | 30.2177 | -96.714 | 349.11
14719 | 94.4 | 336 | 10324.82 | 2814.96 | -563.84 | 2804.29 | 1.2 | -1.16 | 0.32 | 164.79 | 95 | 9957.82 | 219092.77 | 3142959.9 | 30.218 | -96.7141 | 348.67
14815 | 95.3 | 335.9 | 10316.7 | 2902.31 | -602.82 | 2899.94 | 0.94 | 0.94 | -0.1 | -6.31 | 96 | 9949.7 | 219180.12 | 3142920.92 | 30.2182 | -96.7142 | 348.27
14910 | 94.8 | 336.5 | 10308.34 | 2988.89 | -641.01 | 2994.57 | 0.82 | -0.53 | 0.63 | 129.89 | 95 | 9941.34 | 219266.7 | 3142882.73 | 30.2184 | -96.7144 | 347.9
15005 | 93.6 | 336.9 | 10301.38 | 3075.91 | -678.48 | 3089.31 | 1.33 | -1.26 | 0.42 | 161.6 | 95 | 9934.38 | 219353.72 | 3142845.26 | 30.2187 | -96.7145 | 347.56
15100 | 88.9 | 335.4 | 10299.31 | 3162.75 | -716.87 | 3184.26 | 5.19 | -4.95 | -1.58 | -162.28 | 95 | 9932.31 | 219440.56 | 3142806.87 | 30.2189 | -96.7146 | 347.23
15194 | 87.3 | 335.3 | 10302.43 | 3248.13 | -756.06 | 3278.19 | 1.71 | -1.7 | -0.11 | -176.43 | 94 | 9935.43 | 219525.94 | 3142767.68 | 30.2192 | -96.7147 | 346.9
15289 | 89.5 | 336.3 | 10305.08 | 3334.74 | -794.98 | 3373.15 | 2.54 | 2.32 | 1.05 | 24.45 | 95 | 9938.08 | 219612.55 | 3142728.76 | 30.2194 | -96.7148 | 346.59
15383 | 91.7 | 338.1 | 10304.1 | 3421.38 | -831.4 | 3467.12 | 3.02 | 2.34 | 1.91 | 39.28 | 94 | 9937.1 | 219699.19 | 3142692.34 | 30.2196 | -96.7149 | 346.34
15478 | 92.2 | 337.2 | 10300.86 | 3509.2 | -867.51 | 3562.04 | 1.08 | 0.53 | -0.95 | -60.92 | 95 | 9933.86 | 219787.01 | 3142656.23 | 30.2199 | -96.715 | 346.11
15572 | 92.8 | 336.5 | 10296.76 | 3595.54 | -904.42 | 3655.94 | 0.98 | 0.64 | -0.74 | -49.36 | 94 | 9929.76 | 219873.35 | 3142619.32 | 30.2201 | -96.7151 | 345.88
15667 | 91.5 | 337.4 | 10293.2 | 3682.89 | -941.59 | 3750.87 | 1.66 | -1.37 | 0.95 | 145.31 | 95 | 9926.2 | 219960.7 | 3142582.15 | 30.2204 | -96.7152 | 345.66
15761 | 91 | 336.8 | 10291.15 | 3769.46 | -978.16 | 3844.84 | 0.83 | -0.53 | -0.64 | -129.81 | 94 | 9924.15 | 220047.27 | 3142545.58 | 30.2206 | -96.7153 | 345.45
15855 | 90.9 | 336.3 | 10289.59 | 3855.69 | -1015.56 | 3938.82 | 0.54 | -0.11 | -0.53 | -101.31 | 94 | 9922.59 | 220133.5 | 3142508.18 | 30.2209 | -96.7154 | 345.24
15950 | 93.2 | 335.2 | 10286.19 | 3942.24 | -1054.55 | 4033.75 | 2.68 | 2.42 | -1.16 | -25.53 | 95 | 9919.19 | 220220.05 | 3142469.19 | 30.2211 | -96.7156 | 345.02
16044 | 94.9 | 334.9 | 10279.55 | 4027.26 | -1094.1 | 4127.49 | 1.84 | 1.81 | -0.32 | -9.97 | 94 | 9912.55 | 220305.07 | 3142429.64 | 30.2213 | -96.7157 | 344.8
16139 | 94.3 | 336.3 | 10271.93 | 4113.49 | -1133.22 | 4222.17 | 1.6 | -0.63 | 1.47 | 113.21 | 95 | 9904.93 | 220391.3 | 3142390.52 | 30.2216 | -96.7158 | 344.6
16234 | 92 | 336.6 | 10266.71 | 4200.44 | -1171.12 | 4317.02 | 2.44 | -2.42 | 0.32 | 172.57 | 95 | 9899.71 | 220478.25 | 3142352.62 | 30.2218 | -96.7159 | 344.42
16329 | 89 | 337.2 | 10265.88 | 4287.81 | -1208.38 | 4412 | 3.22 | -3.16 | 0.63 | 168.69 | 95 | 9898.88 | 220565.62 | 3142315.36 | 30.2221 | -96.716 | 344.26
16423 | 90.9 | 337.7 | 10265.97 | 4374.62 | -1244.43 | 4505.98 | 2.09 | 2.02 | 0.53 | 14.74 | 94 | 9898.97 | 220652.43 | 3142279.31 | 30.2223 | -96.7161 | 344.12
16520 | 92 | 337.3 | 10263.51 | 4464.2 | -1281.54 | 4602.92 | 1.21 | 1.13 | -0.41 | -19.97 | 97 | 9896.51 | 220742.01 | 3142242.2 | 30.2225 | -96.7162 | 343.98
16614 | 92.7 | 337.3 | 10259.66 | 4550.85 | -1317.78 | 4696.83 | 0.74 | 0.74 | 0 | 0 | 94 | 9892.66 | 220828.66 | 3142205.96 | 30.2228 | -96.7163 | 343.85
16709 | 94 | 337 | 10254.11 | 4638.24 | -1354.61 | 4791.66 | 1.4 | 1.37 | -0.32 | -12.96 | 95 | 9887.11 | 220916.05 | 3142169.13 | 30.223 | -96.7164 | 343.72
16803 | 95.4 | 336.8 | 10246.4 | 4724.41 | -1391.36 | 4885.33 | 1.5 | 1.49 | -0.21 | -8.1 | 94 | 9879.4 | 221002.22 | 3142132.38 | 30.2233 | -96.7165 | 343.59
16899 | 93 | 337.6 | 10239.37 | 4812.67 | -1428.46 | 4981.06 | 2.63 | -2.5 | 0.83 | 161.58 | 96 | 9872.37 | 221090.48 | 3142095.28 | 30.2235 | -96.7167 | 343.47
16993 | 93.9 | 337.8 | 10233.72 | 4899.48 | -1464.06 | 5074.86 | 0.98 | 0.96 | 0.21 | 12.5 | 94 | 9866.72 | 221177.29 | 3142059.68 | 30.2238 | -96.7168 | 343.36
17087 | 95.1 | 337.9 | 10226.34 | 4986.27 | -1499.4 | 5168.53 | 1.28 | 1.28 | 0.11 | 4.75 | 94 | 9859.34 | 221264.08 | 3142024.34 | 30.224 | -96.7169 | 343.26
17181 | 92.8 | 337.4 | 10219.87 | 5073 | -1535.05 | 5262.28 | 2.5 | -2.45 | -0.53 | -167.75 | 94 | 9852.87 | 221350.81 | 3141988.69 | 30.2242 | -96.717 | 343.16
17276 | 93 | 339.2 | 10215.06 | 5161.15 | -1570.13 | 5357.09 | 1.9 | 0.21 | 1.89 | 83.61 | 95 | 9848.06 | 221438.96 | 3141953.61 | 30.2245 | -96.7171 | 343.08
17370 | 90.4 | 337.2 | 10212.27 | 5248.37 | -1605.02 | 5450.99 | 3.49 | -2.77 | -2.13 | -142.41 | 94 | 9845.27 | 221526.18 | 3141918.72 | 30.2247 | -96.7172 | 343
17464 | 90.6 | 336 | 10211.45 | 5334.64 | -1642.35 | 5544.98 | 1.29 | 0.21 | -1.28 | -80.53 | 94 | 9844.45 | 221612.45 | 3141881.39 | 30.225 | -96.7173 | 342.89
17558 | 90.9 | 335.8 | 10210.22 | 5420.44 | -1680.73 | 5638.97 | 0.38 | 0.32 | -0.21 | -33.69 | 94 | 9843.22 | 221698.25 | 3141843.01 | 30.2252 | -96.7174 | 342.77
17653 | 91.3 | 335.6 | 10208.4 | 5507 | -1719.82 | 5733.95 | 0.47 | 0.42 | -0.21 | -26.56 | 95 | 9841.4 | 221784.81 | 3141803.92 | 30.2255 | -96.7175 | 342.66
17747 | 92 | 336 | 10205.69 | 5592.71 | -1758.34 | 5827.9 | 0.86 | 0.74 | 0.43 | 29.73 | 94 | 9838.69 | 221870.52 | 3141765.4 | 30.2257 | -96.7176 | 342.55
17841 | 92 | 336 | 10202.41 | 5678.53 | -1796.55 | 5921.84 | 0 | 0 | 0 | 0 | 94 | 9835.41 | 221956.34 | 3141727.19 | 30.2259 | -96.7177 | 342.44

## 7_9_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/09/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 13250 |  |  | Well Cost($): |  | 13250
|  |  |  | 24hr Summary: |  | P/U BHA, drill lateral
|  |  |  | 24hr Lookahead: |  | Standby, run casing cement same
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 6 | PV: | 2
End Depth (Usft): |  | 2769 |  | 2769 |  | OD (in): |  |  |  | 300: | 5 | YP: | 1
Total Drilled (Usft): |  | 2664 |  | 2664 |  | Weight (ft/lbs): |  |  |  | 200: | 4 | Viscosity: | 25
Slide Drilled (Usft): |  | 314 |  | 314 | [5 empty] | 100: | 3 | Chlorides: | 500
Rotary Drilled (Usft): |  | 2350 |  | 2350 | [5 empty] | 6: | 2 | % Sand/Solids: | 0.25 / 0.25
Drlg/Circ Hrs: |  | 5.48 / 1.33 |  | 5.48 / 1.33 |  | Bit Details |  |  |  | 3: | 2 | Oil/Water:
Slide Drilling Hrs: |  | 1.68 |  | 1.68 |  | SN: |  | 49142 |  | 10s Gel: | 1 | Weight (ppg): | 8.7
Rotary Drilling Hrs: |  | 3.8 |  | 3.8 |  | Bit # |  | 1 |  | PH / Temp(F) | 1.9 / 113.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 618.42 / 186.53 |  | 618.42 / 186.53 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 11.5 |  | 11.5 |  | Grade In: |  | Rerun
% Slide: |  | 11.79 |  | 11.79 |  | Grade Out: |  | Green
% Rotary: |  | 88.21 |  | 88.21 |  | Make / Model: |  | Ulterra / SPL616
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2 - Ulterra - SPL616 - TFA 1.35 |  |  |  | 13.5 | 2.5 |  |  |  |  | 1.5 |  | 1.5
7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  |  | 8 | 2.5 |  |  |  |  | 37.65 |  | 39.15
13 Nortrak Stabalizer |  |  |  | 8.125 | 2.875 |  |  |  |  | 6.97 |  | 46.12
8" Pony Collar |  |  |  | 7.688 | 3.25 |  |  |  |  | 9.55 |  | 55.67
7 3/4" UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.56 |  | 59.23
8" Drill Collar |  |  |  | 7.75 | 3.25 |  |  |  |  | 28.55 |  | 87.78
8" Drill Collar |  |  |  | 8 | 3.25 |  |  |  |  | 30.02 |  | 117.8
X/O 4 1/2 IFB x 6 5/8 RegP |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.22 |  | 120.02
9 joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.99 |  | 398.01
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800019 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.7 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
139 | 0.6 | 125.1 | 139 | -0.42 | 0.6 | 0.43 |  | 125.1 | -0.62 | 0.43 |  | 0 | 139
231 | 0.6 | 137.2 | 230.99 | -1.05 | 1.32 | 0.14 |  | 96.05 | -1.49 | 0 |  | 0 | 92
324 | 0.5 | 141 | 323.99 | -1.72 | 1.9 | 0.11 |  | 161.85 | -2.34 | -0.11 |  | 0 | 93
418 | 0.6 | 136.2 | 417.98 | -2.4 | 2.5 | 0.12 |  | -27.15 | -3.2 | 0.11 |  | 0 | 94
512 | 1.1 | 129.3 | 511.97 | -3.32 | 3.54 | 0.54 |  | -15.03 | -4.46 | 0.53 |  | 0 | 94
606 | 2.1 | 103.2 | 605.94 | -4.29 | 5.92 | 1.29 |  | -49.61 | -6.3 | 1.06 |  | 0 | 94
701 | 2.9 | 94.1 | 700.84 | -4.86 | 10.01 | 0.94 |  | -30.98 | -8.47 | 0.84 |  | -9.58 | 95
794 | 3.8 | 89.3 | 793.68 | -4.99 | 15.44 | 1.01 |  | -19.72 | -10.77 | 0.97 |  | -5.16 | 93
888 | 4 | 85.4 | 887.47 | -4.69 | 21.82 | 0.35 |  | -54.94 | -13.06 | 0.21 |  | -4.15 | 94
982 | 4.6 | 90.6 | 981.2 | -4.46 | 28.86 | 0.76 |  | 35.63 | -15.68 | 0.64 |  | 5.53 | 94
1077 | 5.2 | 99.6 | 1075.86 | -5.22 | 36.91 | 1.02 |  | 56.57 | -19.61 | 0.63 |  | 9.47 | 95
1170 | 6 | 108.5 | 1168.41 | -7.47 | 45.67 | 1.27 |  | 51.84 | -25.19 | 0.86 |  | 9.57 | 93
1266 | 7.3 | 117.3 | 1263.77 | -11.86 | 55.85 | 1.72 |  | 42.52 | -33.3 | 1.35 |  | 9.17 | 96
1359 | 8.1 | 127.1 | 1355.93 | -18.52 | 66.33 | 1.65 |  | 63.57 | -43.61 | 0.86 |  | 10.54 | 93
1454 | 9.9 | 134.8 | 1449.76 | -28.31 | 77.46 | 2.28 |  | 37.63 | -57.05 | 1.89 |  | 8.11 | 95
1547 | 11.4 | 137 | 1541.16 | -40.67 | 89.41 | 1.67 |  | 16.25 | -73.16 | 1.61 |  | 2.37 | 93
1641 | 13.1 | 137 | 1633.01 | -55.25 | 103.01 | 1.81 |  | 0 | -91.98 | 1.81 |  | 0 | 94
1734 | 14.1 | 138.6 | 1723.41 | -71.46 | 117.69 | 1.15 |  | 21.4 | -112.72 | 1.08 |  | 1.72 | 93
1829 | 14.3 | 137 | 1815.5 | -88.72 | 133.34 | 0.46 |  | -63.78 | -134.82 | 0.21 |  | -1.68 | 95
1924 | 14.9 | 135.9 | 1907.44 | -106.07 | 149.84 | 0.7 |  | -25.34 | -157.34 | 0.63 |  | -1.16 | 95
2018 | 14.6 | 136 | 1998.34 | -123.27 | 166.48 | 0.32 |  | 175.2 | -179.77 | -0.32 |  | 0.11 | 94
2112 | 13.9 | 135.6 | 2089.45 | -139.86 | 182.61 | 0.75 |  | -172.19 | -201.45 | -0.74 |  | -0.43 | 94
2207 | 14.1 | 135.3 | 2181.62 | -156.24 | 198.74 | 0.22 |  | -20.09 | -222.92 | 0.21 |  | -0.32 | 95
2300 | 15 | 135.6 | 2271.64 | -172.89 | 215.13 | 0.97 |  | 4.93 | -244.76 | 0.97 |  | 0.32 | 93
2394 | 14.7 | 134.1 | 2362.5 | -189.88 | 232.2 | 0.52 |  | -128.69 | -267.18 | -0.32 |  | -1.6 | 94
2488 | 14.5 | 133.5 | 2453.47 | -206.28 | 249.3 | 0.27 |  | -143.19 | -289.07 | -0.21 |  | -0.64 | 94
2582 | 14.4 | 130.4 | 2544.49 | -221.96 | 266.74 | 0.83 |  | -98.87 | -310.43 | -0.11 |  | -3.3 | 94
2695 | 14.1 | 128.4 | 2654.02 | -239.61 | 288.23 | 0.51 |  | -122.32 | -335.23 | -0.27 |  | -1.77 | 113
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 481.74 | 25 | 100 | 249 | 900 | 2100 | 1350 | 208 | 120 | 120 | 120 | 12000 | 2000
Run | 481.74 | 25 | 100 | 249 | 900 | 2100 | 1350 | 208 | 120 | 120 | 120 | 12000 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem Per Hand |  |  |  |  | 07/09/2020 |  | 4 |  | 100 |  | 4 | 400
Mob/DeMob |  |  |  |  | 07/09/2020 |  | 1 |  | 6000 |  | 1 | 6000
Directional & MWD / Gamma Services |  |  |  |  | 07/09/2020 |  | 2 |  | 6850 |  | 1 | 6850
Total | [11 empty] | 13250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/09/2020 | 00:00 | 11:00 | 11 | 105 | 105 | 0 | SUR |  | 24B | Attended Standby
07/09/2020 | 11:00 | 11:30 | 0.5 | 105 | 105 | 0 | SUR | 1: BHA #1 (Surface) | 6O | Latch up
07/09/2020 | 11:30 | 11:32 | 0.03 | 105 | 213 | 108 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/108.00 t/213.00, w/WOB 5,Flow 461, RPM 40, Press 575, Tq 3000, ROP 3150.00
07/09/2020 | 11:32 | 11:34 | 0.03 | 213 | 213 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 11:34 | 11:39 | 0.08 | 213 | 305 | 92 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/213.00 t/305.00, w/WOB 5,Flow 516, RPM 40, Press 800, Tq 3000, ROP 1104.00
07/09/2020 | 11:39 | 11:44 | 0.08 | 305 | 305 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 11:44 | 11:51 | 0.12 | 305 | 398 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/305.00 t/398.00, w/WOB 5,Flow 620, RPM 40, Press 1100, Tq 3000, ROP 797.14
07/09/2020 | 11:51 | 11:55 | 0.07 | 398 | 398 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 11:55 | 12:00 | 0.08 | 398 | 492 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/398.00 t/492.00, w/WOB 8,Flow 800, RPM 80, Press 1300, Tq 6000, ROP 1128.00
07/09/2020 | 12:00 | 12:05 | 0.08 | 492 | 492 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 12:05 | 12:07 | 0.03 | 492 | 510 | 18 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/492.00 t/510.00, w/WOB 8,Flow 800, RPM 80, Press 1300, Tq 6000, ROP 540.00
07/09/2020 | 12:07 | 12:11 | 0.07 | 510 | 525 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/510.00 t/525.00, TF , w/WOB 3,Flow 800, Press 1150, Tq 0, ROP 225.00
07/09/2020 | 12:11 | 12:15 | 0.07 | 525 | 586 | 61 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/525.00 t/586.00, w/WOB 8,Flow 800, RPM 80, Press 1300, Tq 6000, ROP 915.00
07/09/2020 | 12:15 | 12:20 | 0.08 | 586 | 586 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 12:20 | 12:21 | 0.02 | 586 | 600 | 14 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/586.00 t/600.00, w/WOB 12,Flow 800.00, RPM 100, Press 1300.00, Tq 6000.00, ROP 840.00
07/09/2020 | 12:21 | 12:24 | 0.05 | 600 | 615 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/600.00 t/615.00, TF , w/WOB 3.00,Flow 800.00, Press 1150.00, Tq 0.00, ROP 300.00
07/09/2020 | 12:24 | 12:27 | 0.05 | 615 | 680 | 65 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/615.00 t/680.00, w/WOB 12,Flow 800.00, RPM 100, Press 1300.00, Tq 6000.00, ROP 1300.00
07/09/2020 | 12:27 | 12:37 | 0.17 | 680 | 680 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 12:37 | 12:38 | 0.02 | 680 | 695 | 15 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/680.00 t/695.00, w/WOB 12,Flow 800.00, RPM 100, Press 1300.00, Tq 6000.00, ROP 900.00
07/09/2020 | 12:38 | 12:41 | 0.05 | 695 | 710 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/695.00 t/710.00, TF , w/WOB 3.00,Flow 800.00, Press 1150.00, Tq 0.00, ROP 300.00
07/09/2020 | 12:41 | 12:45 | 0.07 | 710 | 775 | 65 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/710.00 t/775.00, w/WOB 12.00,Flow 800.00, RPM 100.00, Press 1300.00, Tq 6000.00, ROP 975.00
07/09/2020 | 12:45 | 12:50 | 0.08 | 775 | 775 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 12:50 | 12:51 | 0.02 | 775 | 785 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/775.00 t/785.00, w/WOB 7,Flow 442, RPM 100.00, Press 800, Tq 6000.00, ROP 600.00
07/09/2020 | 12:51 | 12:58 | 0.12 | 785 | 800 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/785.00 t/800.00, TF , w/WOB 3.00,Flow 442, Press 675, Tq 0, ROP 128.57
07/09/2020 | 12:58 | 13:16 | 0.3 | 800 | 868 | 68 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/800.00 t/868.00, w/WOB 7,Flow 442, RPM 100.00, Press 800, Tq 6000.00, ROP 226.67
07/09/2020 | 13:16 | 13:20 | 0.07 | 868 | 868 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 13:20 | 13:42 | 0.37 | 868 | 962 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/868.00 t/962.00, w/WOB 7,Flow 442, RPM 100.00, Press 800, Tq 6000.00, ROP 256.36
07/09/2020 | 13:42 | 13:47 | 0.08 | 962 | 962 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 13:47 | 13:49 | 0.03 | 962 | 975 | 13 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/962.00 t/975.00, w/WOB 7,Flow 442, RPM 100.00, Press 800, Tq 6000.00, ROP 390.00
07/09/2020 | 13:49 | 13:55 | 0.1 | 975 | 993 | 18 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/975.00 t/993.00, TF , w/WOB 3.00,Flow 442, Press 675, Tq 0, ROP 180.00
07/09/2020 | 13:55 | 14:01 | 0.1 | 993 | 1056 | 63 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/993.00 t/1056.00, w/WOB 15,Flow 800.00, RPM 100, Press 1500, Tq 7500, ROP 630.00
07/09/2020 | 14:01 | 14:06 | 0.08 | 1056 | 1056 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 14:06 | 14:09 | 0.05 | 1056 | 1070 | 14 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1056.00 t/1070.00, w/WOB 15.00,Flow 800.00, RPM 100.00, Press 1500.00, Tq 7500.00, ROP 280.00
07/09/2020 | 14:09 | 14:18 | 0.15 | 1070 | 1088 | 18 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1070.00 t/1088.00, TF 50.00, w/WOB 3.00,Flow 442.00, Press 675.00, Tq 0.00, ROP 120.00
07/09/2020 | 14:18 | 14:21 | 0.05 | 1088 | 1151 | 63 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1088.00 t/1151.00, w/WOB 15.00,Flow 800.00, RPM 100.00, Press 1500.00, Tq 7500.00, ROP 1260.00
07/09/2020 | 14:21 | 14:26 | 0.08 | 1151 | 1151 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 14:26 | 14:27 | 0.02 | 1151 | 1165 | 14 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1151.00 t/1165.00, w/WOB 15.00,Flow 800.00, RPM 100.00, Press 1500.00, Tq 7500.00, ROP 840.00
07/09/2020 | 14:27 | 14:33 | 0.1 | 1165 | 1190 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1165.00 t/1190.00, TF 50.00, w/WOB 15.00,Flow 800.00, Press 1500.00, Tq 7500.00, ROP 250.00
07/09/2020 | 14:33 | 14:36 | 0.05 | 1190 | 1244 | 54 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1190.00 t/1244.00, w/WOB 15.00,Flow 800.00, RPM 100.00, Press 1500.00, Tq 7500.00, ROP 1080.00
07/09/2020 | 14:36 | 14:41 | 0.08 | 1244 | 1244 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 14:41 | 14:42 | 0.02 | 1244 | 1255 | 11 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1244.00 t/1255.00, w/WOB 20,Flow 800.00, RPM 100.00, Press 1700, Tq 9000, ROP 660.00
07/09/2020 | 14:42 | 14:48 | 0.1 | 1255 | 1280 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1255.00 t/1280.00, TF , w/WOB 12,Flow 800.00, Press 1300, Tq 0, ROP 250.00
07/09/2020 | 14:48 | 14:51 | 0.05 | 1280 | 1340 | 60 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1280.00 t/1340.00, w/WOB 20,Flow 800.00, RPM 100.00, Press 1700, Tq 9000, ROP 1200.00
07/09/2020 | 14:51 | 14:55 | 0.07 | 1340 | 1340 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 14:55 | 14:56 | 0.02 | 1340 | 1350 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1340.00 t/1350.00, w/WOB 20,Flow 800.00, RPM 100.00, Press 1700, Tq 9000, ROP 600.00
07/09/2020 | 14:56 | 15:05 | 0.15 | 1350 | 1375 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1350.00 t/1375.00, TF , w/WOB 12,Flow 800.00, Press 1300, Tq 0, ROP 166.67
07/09/2020 | 15:05 | 15:08 | 0.05 | 1375 | 1433 | 58 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1375.00 t/1433.00, w/WOB 20,Flow 800.00, RPM 100.00, Press 1700, Tq 9000, ROP 1160.00
07/09/2020 | 15:08 | 15:14 | 0.1 | 1433 | 1433 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 15:14 | 15:15 | 0.02 | 1433 | 1445 | 12 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1433.00 t/1445.00, w/WOB 20,Flow 800.00, RPM 100.00, Press 1700, Tq 9000, ROP 720.00
07/09/2020 | 15:15 | 15:25 | 0.17 | 1445 | 1475 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1445.00 t/1475.00, TF , w/WOB 12,Flow 800.00, Press 1300, Tq 0, ROP 180.00
07/09/2020 | 15:25 | 15:28 | 0.05 | 1475 | 1528 | 53 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1475.00 t/1528.00, w/WOB 20,Flow 800.00, RPM 100.00, Press 1700, Tq 9000, ROP 1060.00
07/09/2020 | 15:28 | 15:33 | 0.08 | 1528 | 1528 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 15:33 | 15:34 | 0.02 | 1528 | 1540 | 12 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1528.00 t/1540.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1700.00, Tq 9000.00, ROP 720.00
07/09/2020 | 15:34 | 15:43 | 0.15 | 1540 | 1570 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1540.00 t/1570.00, TF , w/WOB 12.00,Flow 800.00, Press 1300.00, Tq 0.00, ROP 200.00
07/09/2020 | 15:43 | 15:47 | 0.07 | 1570 | 1621 | 51 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1570.00 t/1621.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800, Tq 9000.00, ROP 765.00
07/09/2020 | 15:47 | 15:53 | 0.1 | 1621 | 1621 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 15:53 | 15:54 | 0.02 | 1621 | 1635 | 14 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1621.00 t/1635.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800, Tq 9000.00, ROP 840.00
07/09/2020 | 15:54 | 16:00 | 0.1 | 1635 | 1665 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1635.00 t/1665.00, TF , w/WOB 12.00,Flow 800.00, Press 1400, Tq 0.00, ROP 300.00
07/09/2020 | 16:00 | 16:03 | 0.05 | 1665 | 1715 | 50 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1665.00 t/1715.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800, Tq 9000.00, ROP 1000.00
07/09/2020 | 16:03 | 16:08 | 0.08 | 1715 | 1715 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 16:08 | 16:40 | 0.53 | 1715 | 1808 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1715.00 t/1808.00, w/WOB 20.00,Flow 442, RPM 100.00, Press 1800, Tq 9000.00, ROP 174.38
07/09/2020 | 16:40 | 16:50 | 0.17 | 1808 | 1808 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 16:50 | 16:53 | 0.05 | 1808 | 1825 | 17 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1808.00 t/1825.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800, Tq 9000.00, ROP 340.00
07/09/2020 | 16:53 | 17:06 | 0.22 | 1825 | 1850 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1825.00 t/1850.00, TF , w/WOB 12.00,Flow 800.00, Press 1400, Tq 0.00, ROP 115.38
07/09/2020 | 17:06 | 17:10 | 0.07 | 1850 | 1903 | 53 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1850.00 t/1903.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800, Tq 9000.00, ROP 795.00
07/09/2020 | 17:10 | 17:15 | 0.08 | 1903 | 1903 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 17:15 | 17:21 | 0.1 | 1903 | 1998 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1903.00 t/1998.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 950.00
07/09/2020 | 17:21 | 17:26 | 0.08 | 1998 | 1998 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 17:26 | 17:30 | 0.07 | 1998 | 2092 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1998.00 t/2092.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 1410.00
07/09/2020 | 17:30 | 17:35 | 0.08 | 2092 | 2092 | 0 | SUR | 1: BHA #1 (Surface) | 1G | Survey & Connection
07/09/2020 | 17:35 | 17:40 | 0.08 | 2092 | 2186 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2092.00 t/2186.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 1128.00
07/09/2020 | 17:40 | 17:45 | 0.08 | 2186 | 2186 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 17:45 | 17:47 | 0.03 | 2186 | 2210 | 24 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2186.00 t/2210.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 720.00
07/09/2020 | 17:47 | 17:57 | 0.17 | 2210 | 2238 | 28 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2210.00 t/2238.00, TF , w/WOB 20.00,Flow 800.00, Press 1800.00, Tq 9000.00, ROP 168.00
07/09/2020 | 17:57 | 18:05 | 0.13 | 2238 | 2281 | 43 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2238.00 t/2281.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 322.50
07/09/2020 | 18:05 | 18:10 | 0.08 | 2281 | 2281 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 18:10 | 18:20 | 0.17 | 2281 | 2374 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2281.00 t/2374.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 558.00
07/09/2020 | 18:20 | 18:25 | 0.08 | 2374 | 2374 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 18:25 | 18:31 | 0.1 | 2374 | 2468 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2374.00 t/2468.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 940.00
07/09/2020 | 18:31 | 18:36 | 0.08 | 2468 | 2468 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
07/09/2020 | 18:36 | 18:42 | 0.1 | 2468 | 2562 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2468.00 t/2562.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 940.00
07/09/2020 | 18:42 | 19:10 | 0.47 | 2562 | 2769 | 207 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2562.00 t/2769.00, w/WOB 20.00,Flow 800.00, RPM 100.00, Press 1800.00, Tq 9000.00, ROP 443.57
07/09/2020 | 19:10 | 20:30 | 1.33 | 2769 | 2769 | 0 | SUR | 1: BHA #1 (Surface) | 5A | Circulate
07/09/2020 | 20:30 | 22:00 | 1.5 | 2769 | 2769 | 0 | SUR | 1: BHA #1 (Surface) | 6B | POOH
07/09/2020 | 22:00 | 23:00 | 1 | 2769 | 2769 | 0 | SUR | 1: BHA #1 (Surface) | 6P | L/D BHA
07/09/2020 | 23:00 | 24:00 | 1 | 2769 | 2769 | 0 | SUR |  | 26A | Attended standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_19_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/19/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 18050
|  |  |  | 24hr Summary: |  | Skid rig, Nipple up
|  |  |  | 24hr Lookahead: |  | P/U BHA, TIH, Drill float equipment
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2769 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 6 | PV: | 2
End Depth (Usft): |  | 2769 |  | 2769 |  | OD (in): |  |  |  | 300: | 5 | YP: | 1
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 4 | Viscosity: | 25
Slide Drilled (Usft): | [9 empty] | 100: | 3 | Chlorides: | 500
Rotary Drilled (Usft): | [9 empty] | 6: | 2 | % Sand/Solids: | 0.25 / 0.25
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 2 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 1 | Weight (ppg): | 9.3
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 1.9 / 190.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 25 | 100 | 249 | 900 | 2100 | 1350 | 208 | 120 | 120 | 120 | 12000 | 2000
Run | 0 | 25 | 100 | 249 | 900 | 2100 | 1350 | 208 | 120 | 120 | 120 | 12000 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 07/19/2020 |  | 3 |  | 4400 |  | 1 | 4400
Perdiem Per Hand |  |  |  |  | 07/19/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/19/2020 | 00:00 | 24:00 | 24 | 2769 | 2769 | 0 | INT |  | 26B | Standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_20_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/20/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 25300
|  |  |  | 24hr Summary: |  | TIH< Drill float equipment, drill vertical
|  |  |  | 24hr Lookahead: |  | TD section, POOH
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2769 |  | 2769 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 6 | PV: | 2
End Depth (Usft): |  | 7129 |  | 7129 |  | OD (in): |  |  |  | 300: | 5 | YP: | 1
Total Drilled (Usft): |  | 4360 |  | 4360 |  | Weight (ft/lbs): |  |  |  | 200: | 4 | Viscosity: | 25
Slide Drilled (Usft): |  | 189 |  | 189 | [5 empty] | 100: | 3 | Chlorides: | 500
Rotary Drilled (Usft): |  | 4171 |  | 4171 | [5 empty] | 6: | 2 | % Sand/Solids: | 0.25 / 0.25
Drlg/Circ Hrs: |  | 11.75 / 1.15 |  | 11.75 / 1.15 |  | Bit Details |  |  |  | 3: | 2 | Oil/Water:
Slide Drilling Hrs: |  | 2.3 |  | 2.3 |  | SN: |  | 43215 |  | 10s Gel: | 1 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 9.45 |  | 9.45 |  | Bit # |  | 2 |  | PH / Temp(F) | 1.9 / 190.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 441.38 / 82.17 |  | 441.38 / 82.17 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 19.17 |  | 19.17 |  | Grade In: |  | Green
% Slide: |  | 4.33 |  | 4.33 |  | Grade Out:
% Rotary: |  | 95.67 |  | 95.67 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.49 |  |  |  | 9.875 | 2.5 |  |  |  |  | 1.3 |  | 1.3
7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS |  |  |  | 8 | 2.5 |  |  |  |  | 37.32 |  | 38.62
8 Pony Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.81 |  | 46.43
7 3/4 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.86 |  | 50.29
8 Drill Collar |  |  |  | 7.75 | 3.313 |  |  |  |  | 27.12 |  | 77.41
8 Drill Collar |  |  |  | 7.875 | 3.313 |  |  |  |  | 27.4 |  | 104.81
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.75 | 2.875 |  |  |  |  | 3.47 |  | 108.28
2 Stands 6 1/2in Collars |  |  |  | 6.5 | 2.375 |  |  |  |  | 187.21 |  | 295.49
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 3 |  | 298.49
3 Stands of HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.99 |  | 576.48
22 stands of Drillpipe |  |  |  | 6 | 2.75 |  |  |  |  | 2070.98 |  | 2647.46
Safety Joint / Agitator/Shocksub |  |  |  | 7 | 2.625 |  |  |  |  | 30.78 |  | 2678.24
2678.24
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800015 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.65 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2797 | 13.8 | 127.4 | 2753.01 | -254.72 | 307.63 | 0.38 |  | -141.7 | -356.86 | -0.29 |  | -0.98 | 102
2891 | 13 | 128.2 | 2844.45 | -268.07 | 324.84 | 0.87 |  | 167.34 | -376 | -0.85 |  | 0.85 | 94
2985 | 14.3 | 133.2 | 2935.79 | -282.55 | 341.62 | 1.87 |  | 44.68 | -396 | 1.38 |  | 5.32 | 94
3079 | 14.7 | 130.7 | 3026.8 | -298.28 | 359.12 | 0.79 |  | -58.63 | -417.43 | 0.43 |  | -2.66 | 94
3173 | 14.6 | 127.8 | 3117.75 | -313.32 | 377.52 | 0.79 |  | -99.17 | -438.6 | -0.11 |  | -3.09 | 94
3266 | 15.4 | 131 | 3207.58 | -328.6 | 396.11 | 1.24 |  | 47.55 | -460.06 | 0.86 |  | 3.44 | 93
3360 | 15.6 | 132.1 | 3298.16 | -345.27 | 414.9 | 0.38 |  | 56.3 | -482.87 | 0.21 |  | 1.17 | 94
3454 | 14.9 | 136.9 | 3388.85 | -362.56 | 432.54 | 1.54 |  | 121.31 | -505.8 | -0.74 |  | 5.11 | 94
3548 | 14.2 | 136.1 | 3479.84 | -379.7 | 448.79 | 0.77 |  | -164.37 | -528.02 | -0.74 |  | -0.85 | 94
3642 | 14.2 | 135.9 | 3570.97 | -396.28 | 464.81 | 0.05 |  | -90.1 | -549.65 | 0 |  | -0.21 | 94
3736 | 14.2 | 140.8 | 3662.1 | -413.5 | 480.12 | 1.28 |  | 92.38 | -571.56 | 0 |  | 5.21 | 94
3830 | 14.2 | 142.2 | 3753.23 | -431.54 | 494.47 | 0.37 |  | 90.68 | -593.85 | 0 |  | 1.49 | 94
3925 | 14.5 | 142.3 | 3845.26 | -450.16 | 508.89 | 0.32 |  | 4.77 | -616.69 | 0.32 |  | 0.11 | 95
4018 | 15 | 141.2 | 3935.2 | -468.75 | 523.55 | 0.62 |  | -29.79 | -639.61 | 0.54 |  | -1.18 | 93
4112 | 14.9 | 141 | 4026.01 | -487.62 | 538.78 | 0.12 |  | -152.81 | -663.01 | -0.11 |  | -0.21 | 94
4206 | 15.2 | 140.1 | 4116.79 | -506.47 | 554.29 | 0.4 |  | -38.35 | -686.5 | 0.32 |  | -0.96 | 94
4301 | 14.9 | 139.4 | 4208.53 | -525.3 | 570.23 | 0.37 |  | -149.13 | -710.14 | -0.32 |  | -0.74 | 95
4395 | 14.6 | 137.6 | 4299.43 | -543.22 | 586.08 | 0.58 |  | -124.08 | -732.93 | -0.32 |  | -1.91 | 94
4490 | 14.9 | 136.1 | 4391.3 | -560.87 | 602.62 | 0.51 |  | -52.58 | -755.73 | 0.32 |  | -1.58 | 95
4584 | 14.5 | 135.3 | 4482.23 | -577.94 | 619.28 | 0.48 |  | -153.48 | -778.06 | -0.43 |  | -0.85 | 94
4677 | 14.1 | 136 | 4572.35 | -594.36 | 635.34 | 0.47 |  | 156.96 | -799.55 | -0.43 |  | 0.75 | 93
4772 | 13.6 | 134.7 | 4664.58 | -610.54 | 651.32 | 0.62 |  | -148.73 | -820.78 | -0.53 |  | -1.37 | 95
4867 | 13.8 | 131.5 | 4756.88 | -625.91 | 667.74 | 0.82 |  | -76.78 | -841.45 | 0.21 |  | -3.37 | 95
4961 | 13.2 | 132.1 | 4848.28 | -640.53 | 684.1 | 0.66 |  | 167.15 | -861.42 | -0.64 |  | 0.64 | 94
5055 | 12.6 | 130 | 4939.91 | -654.32 | 699.92 | 0.81 |  | -143.02 | -880.4 | -0.64 |  | -2.23 | 94
5149 | 14.5 | 134 | 5031.29 | -669.08 | 716.24 | 2.25 |  | 28.21 | -900.48 | 2.02 |  | 4.26 | 94
5243 | 15.6 | 136.9 | 5122.07 | -686.49 | 733.34 | 1.42 |  | 35.8 | -923.29 | 1.17 |  | 3.09 | 94
5336 | 15.4 | 136.9 | 5211.69 | -704.64 | 750.32 | 0.22 |  | 180 | -946.73 | -0.22 |  | 0 | 93
5430 | 15.1 | 133.7 | 5302.38 | -722.21 | 767.7 | 0.95 |  | -111.16 | -969.8 | -0.32 |  | -3.4 | 94
5523 | 15.4 | 133.8 | 5392.1 | -739.12 | 785.37 | 0.32 |  | 5.06 | -992.39 | 0.32 |  | 0.11 | 93
5617 | 14.2 | 137.3 | 5482.98 | -756.24 | 802.2 | 1.59 |  | 145 | -1014.83 | -1.28 |  | 3.72 | 94
5712 | 14.5 | 137.6 | 5575.02 | -773.58 | 818.12 | 0.33 |  | 14.07 | -1037.11 | 0.32 |  | 0.32 | 95
5806 | 13.6 | 136.6 | 5666.21 | -790.3 | 833.65 | 0.99 |  | -165.39 | -1058.66 | -0.96 |  | -1.06 | 94
5900 | 12.6 | 135.4 | 5757.76 | -805.63 | 848.44 | 1.1 |  | -165.37 | -1078.64 | -1.06 |  | -1.28 | 94
5994 | 12.3 | 134.7 | 5849.55 | -819.98 | 862.76 | 0.36 |  | -153.64 | -1097.53 | -0.32 |  | -0.74 | 94
6087 | 11.6 | 132.7 | 5940.53 | -833.28 | 876.67 | 0.87 |  | -150.37 | -1115.3 | -0.75 |  | -2.15 | 93
6181 | 13.7 | 136.4 | 6032.25 | -847.76 | 891.3 | 2.39 |  | 22.91 | -1134.43 | 2.23 |  | 3.94 | 94
6275 | 14.5 | 138.4 | 6123.42 | -864.62 | 906.79 | 1 |  | 32.32 | -1156.1 | 0.85 |  | 2.13 | 94
6368 | 13.2 | 138.6 | 6213.71 | -881.29 | 921.54 | 1.4 |  | 177.99 | -1177.29 | -1.4 |  | 0.22 | 93
6462 | 14.2 | 138.2 | 6305.04 | -897.94 | 936.32 | 1.07 |  | -5.61 | -1198.47 | 1.06 |  | -0.43 | 94
6556 | 14.5 | 138.5 | 6396.1 | -915.34 | 951.8 | 0.33 |  | 14.07 | -1220.63 | 0.32 |  | 0.32 | 94
6650 | 14.4 | 136.7 | 6487.13 | -932.66 | 967.62 | 0.49 |  | -103.42 | -1242.85 | -0.11 |  | -1.91 | 94
6744 | 13.2 | 137.6 | 6578.41 | -949.1 | 982.87 | 1.3 |  | 170.29 | -1264.03 | -1.28 |  | 0.96 | 94
6837 | 12.7 | 136.3 | 6669.05 | -964.33 | 997.09 | 0.62 |  | -150.4 | -1283.69 | -0.54 |  | -1.4 | 93
6932 | 12.1 | 134.4 | 6761.83 | -978.85 | 1011.42 | 0.76 |  | -146.71 | -1302.74 | -0.63 |  | -2 | 95
7026 | 12.1 | 137.3 | 6853.75 | -992.98 | 1025.14 | 0.65 |  | 91.42 | -1321.19 | 0 |  | 3.09 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 401.49 | 27.33 | 78.6 | 200 | 733 | 3685.07 | 3089.55 | 208 | 160.6 | 142.84 | 129.1 | 14543.86 | 2000
Run | 401.49 | 27.33 | 78.6 | 200 | 733 | 3685.07 | 3089.55 | 208 | 160.6 | 142.84 | 129.1 | 14543.86 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/20/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/20/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/20/2020 | 00:00 | 02:30 | 2.5 | 2769 | 2769 | 0 | INT |  | 24B | Attended standby
07/20/2020 | 02:30 | 04:50 | 2.33 | 2769 | 2769 | 0 | INT | 2: BHA #2 (Intermediate) | 6O | P/U BHA
07/20/2020 | 04:50 | 05:00 | 0.17 | 2769 | 2769 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Shallow test
07/20/2020 | 05:00 | 06:58 | 1.97 | 2769 | 2769 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH to 2680
07/20/2020 | 06:58 | 07:50 | 0.87 | 2769 | 2769 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Drill out float and shoe track
07/20/2020 | 07:50 | 07:53 | 0.05 | 2769 | 2786 | 17 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/2769.00 t/2786.00, w/WOB 15,Flow 498, RPM 40, Press 1300, Tq 4000, ROP 340.00
07/20/2020 | 07:53 | 08:00 | 0.12 | 2786 | 2786 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate
07/20/2020 | 08:00 | 08:26 | 0.43 | 2786 | 2786 | 0 | INT | 2: BHA #2 (Intermediate) | 15D | Perform FIT
07/20/2020 | 08:26 | 08:43 | 0.28 | 2786 | 2865 | 79 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/2786.00 t/2865.00, w/WOB 25.00,Flow 498.00, RPM 40.00, Press 1300.00, Tq 4000.00, ROP 278.82
07/20/2020 | 08:43 | 08:48 | 0.08 | 2865 | 2865 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 08:48 | 08:58 | 0.17 | 2865 | 2959 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/2865.00 t/2959.00, w/WOB 35,Flow 623, RPM 80, Press 2900, Tq 7500, ROP 564.00
07/20/2020 | 08:58 | 09:03 | 0.08 | 2959 | 2959 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 09:03 | 09:06 | 0.05 | 2959 | 2970 | 11 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/2959.00 t/2970.00, w/WOB 35,Flow 623, RPM 80, Press 2900, Tq 7500, ROP 220.00
07/20/2020 | 09:06 | 09:15 | 0.15 | 2970 | 2988 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/2970.00 t/2988.00, TF , w/WOB 12,Flow 623, Press 2450, Tq 0, ROP 120.00
07/20/2020 | 09:15 | 09:24 | 0.15 | 2988 | 3053 | 65 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/2988.00 t/3053.00, w/WOB 35,Flow 623, RPM 80, Press 2900, Tq 7500, ROP 433.33
07/20/2020 | 09:24 | 09:30 | 0.1 | 3053 | 3053 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 09:30 | 09:37 | 0.12 | 3053 | 3147 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3053.00 t/3147.00, w/WOB 35,Flow 623, RPM 80, Press 2900, Tq 7500, ROP 805.71
07/20/2020 | 09:37 | 09:43 | 0.1 | 3147 | 3147 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 09:43 | 09:47 | 0.07 | 3147 | 3241 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3147.00 t/3241.00, w/WOB 35,Flow 750, RPM 80, Press 3650, Tq 13000, ROP 1410.00
07/20/2020 | 09:47 | 09:52 | 0.08 | 3241 | 3241 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 09:52 | 09:54 | 0.03 | 3241 | 3250 | 9 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3241.00 t/3250.00, w/WOB 35,Flow 750, RPM 80, Press 3650, Tq 13000, ROP 270.00
07/20/2020 | 09:54 | 10:00 | 0.1 | 3250 | 3265 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3250.00 t/3265.00, TF , w/WOB 8,Flow 750, Press 3250, Tq 0, ROP 150.00
07/20/2020 | 10:00 | 10:07 | 0.12 | 3265 | 3335 | 70 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3265.00 t/3335.00, w/WOB 35,Flow 750, RPM 80, Press 3650, Tq 13000, ROP 600.00
07/20/2020 | 10:07 | 10:12 | 0.08 | 3335 | 3335 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 10:12 | 10:32 | 0.33 | 3335 | 3428 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3335.00 t/3428.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 279.00
07/20/2020 | 10:32 | 10:37 | 0.08 | 3428 | 3428 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 10:37 | 10:39 | 0.03 | 3428 | 3435 | 7 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3428.00 t/3435.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 210.00
07/20/2020 | 10:39 | 10:48 | 0.15 | 3435 | 3450 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3435.00 t/3450.00, TF 90.00, w/WOB 8.00,Flow 750.00, Press 3250.00, Tq 0.00, ROP 100.00
07/20/2020 | 10:48 | 11:01 | 0.22 | 3450 | 3522 | 72 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3450.00 t/3522.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 332.31
07/20/2020 | 11:01 | 11:05 | 0.07 | 3522 | 3522 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 11:05 | 11:20 | 0.25 | 3522 | 3616 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3522.00 t/3616.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 376.00
07/20/2020 | 11:20 | 11:25 | 0.08 | 3616 | 3616 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 11:25 | 11:35 | 0.17 | 3616 | 3710 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3616.00 t/3710.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 564.00
07/20/2020 | 11:35 | 11:40 | 0.08 | 3710 | 3710 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 11:40 | 11:41 | 0.02 | 3710 | 3720 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3710.00 t/3720.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 600.00
07/20/2020 | 11:41 | 11:50 | 0.15 | 3720 | 3738 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3720.00 t/3738.00, TF , w/WOB 8.00,Flow 750.00, Press 3250.00, Tq 0.00, ROP 120.00
07/20/2020 | 11:50 | 12:00 | 0.17 | 3738 | 3804 | 66 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3738.00 t/3804.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 396.00
07/20/2020 | 12:00 | 12:05 | 0.08 | 3804 | 3804 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 12:05 | 12:15 | 0.17 | 3804 | 3898 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3804.00 t/3898.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 564.00
07/20/2020 | 12:15 | 12:20 | 0.08 | 3898 | 3898 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 12:20 | 12:28 | 0.13 | 3898 | 3993 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3898.00 t/3993.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 712.50
07/20/2020 | 12:28 | 12:33 | 0.08 | 3993 | 3993 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 12:33 | 12:43 | 0.17 | 3993 | 4086 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3993.00 t/4086.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 13000.00, ROP 558.00
07/20/2020 | 12:43 | 12:47 | 0.07 | 4086 | 4086 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 12:47 | 12:57 | 0.17 | 4086 | 4180 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4086.00 t/4180.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 15000, ROP 564.00
07/20/2020 | 12:57 | 13:03 | 0.1 | 4180 | 4180 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 13:03 | 13:12 | 0.15 | 4180 | 4274 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4180.00 t/4274.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 15000, ROP 626.67
07/20/2020 | 13:12 | 13:17 | 0.08 | 4274 | 4274 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 13:17 | 13:28 | 0.18 | 4274 | 4369 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4274.00 t/4369.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 15000.00, ROP 518.18
07/20/2020 | 13:28 | 13:32 | 0.07 | 4369 | 4369 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 13:32 | 13:43 | 0.18 | 4369 | 4463 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4369.00 t/4463.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3650.00, Tq 15000.00, ROP 512.73
07/20/2020 | 13:43 | 13:48 | 0.08 | 4463 | 4463 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 13:48 | 13:59 | 0.18 | 4463 | 4558 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4463.00 t/4558.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3800, Tq 15000.00, ROP 518.18
07/20/2020 | 13:59 | 14:05 | 0.1 | 4558 | 4558 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 14:05 | 14:14 | 0.15 | 4558 | 4652 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4558.00 t/4652.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3800, Tq 15000.00, ROP 626.67
07/20/2020 | 14:14 | 14:20 | 0.1 | 4652 | 4652 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 14:20 | 14:31 | 0.18 | 4652 | 4745 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4652.00 t/4745.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3800, Tq 15000.00, ROP 507.27
07/20/2020 | 14:31 | 14:35 | 0.07 | 4745 | 4745 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 14:35 | 14:48 | 0.22 | 4745 | 4840 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4745.00 t/4840.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 3800, Tq 15000.00, ROP 438.46
07/20/2020 | 14:48 | 14:53 | 0.08 | 4840 | 4840 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 14:53 | 15:05 | 0.2 | 4840 | 4935 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4840.00 t/4935.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 475.00
07/20/2020 | 15:05 | 15:10 | 0.08 | 4935 | 4935 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 15:10 | 15:22 | 0.2 | 4935 | 5029 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4935.00 t/5029.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 470.00
07/20/2020 | 15:22 | 15:27 | 0.08 | 5029 | 5029 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 15:27 | 15:39 | 0.2 | 5029 | 5123 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5029.00 t/5123.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 470.00
07/20/2020 | 15:39 | 15:45 | 0.1 | 5123 | 5123 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 15:45 | 15:47 | 0.03 | 5123 | 5135 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5123.00 t/5135.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 360.00
07/20/2020 | 15:47 | 15:59 | 0.2 | 5135 | 5165 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5135.00 t/5165.00, TF , w/WOB 15,Flow 750.00, Press 3500, Tq 0, ROP 150.00
07/20/2020 | 15:59 | 16:06 | 0.12 | 5165 | 5217 | 52 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5165.00 t/5217.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 445.71
07/20/2020 | 16:06 | 16:11 | 0.08 | 5217 | 5217 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 16:11 | 16:23 | 0.2 | 5217 | 5311 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5217.00 t/5311.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 470.00
07/20/2020 | 16:23 | 16:28 | 0.08 | 5311 | 5311 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 16:28 | 16:40 | 0.2 | 5311 | 5404 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5311.00 t/5404.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 465.00
07/20/2020 | 16:40 | 16:45 | 0.08 | 5404 | 5404 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 16:45 | 16:55 | 0.17 | 5404 | 5498 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5404.00 t/5498.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000, Tq 15000.00, ROP 564.00
07/20/2020 | 16:55 | 17:00 | 0.08 | 5498 | 5498 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 17:00 | 17:11 | 0.18 | 5498 | 5591 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5498.00 t/5591.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 15000.00, ROP 507.27
07/20/2020 | 17:11 | 17:16 | 0.08 | 5591 | 5591 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 17:16 | 17:18 | 0.03 | 5591 | 5600 | 9 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5591.00 t/5600.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 15000.00, ROP 270.00
07/20/2020 | 17:18 | 17:25 | 0.12 | 5600 | 5615 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5600.00 t/5615.00, TF , w/WOB 15.00,Flow 750.00, Press 3500.00, Tq 0.00, ROP 128.57
07/20/2020 | 17:25 | 17:35 | 0.17 | 5615 | 5685 | 70 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5615.00 t/5685.00, w/WOB 15.00,Flow 750.00, RPM 0.00, Press 3500.00, Tq 0.00, ROP 420.00
07/20/2020 | 17:35 | 17:40 | 0.08 | 5685 | 5685 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 17:40 | 17:52 | 0.2 | 5685 | 5780 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5685.00 t/5780.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 16000, ROP 475.00
07/20/2020 | 17:52 | 17:57 | 0.08 | 5780 | 5780 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 17:57 | 18:08 | 0.18 | 5780 | 5874 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5780.00 t/5874.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 17000, ROP 512.73
07/20/2020 | 18:08 | 18:13 | 0.08 | 5874 | 5874 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 18:13 | 18:28 | 0.25 | 5874 | 5968 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5874.00 t/5968.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 17000, ROP 376.00
07/20/2020 | 18:28 | 18:33 | 0.08 | 5968 | 5968 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 18:33 | 18:45 | 0.2 | 5968 | 6062 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5968.00 t/6062.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 17000, ROP 470.00
07/20/2020 | 18:45 | 18:50 | 0.08 | 6062 | 6062 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 18:50 | 19:02 | 0.2 | 6062 | 6155 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6062.00 t/6155.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 17000, ROP 465.00
07/20/2020 | 19:02 | 19:07 | 0.08 | 6155 | 6155 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 19:07 | 19:10 | 0.05 | 6155 | 6165 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6155.00 t/6165.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 200.00
07/20/2020 | 19:10 | 19:25 | 0.25 | 6165 | 6187 | 22 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6165.00 t/6187.00, TF , w/WOB 15.00,Flow 750.00, Press 4000, Tq 0.00, ROP 88.00
07/20/2020 | 19:25 | 19:43 | 0.3 | 6187 | 6249 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6187.00 t/6249.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 206.67
07/20/2020 | 19:43 | 19:48 | 0.08 | 6249 | 6249 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 19:48 | 20:01 | 0.22 | 6249 | 6343 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6249.00 t/6343.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 433.85
07/20/2020 | 20:01 | 20:06 | 0.08 | 6343 | 6343 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 20:06 | 20:20 | 0.23 | 6343 | 6436 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6343.00 t/6436.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 398.57
07/20/2020 | 20:20 | 20:25 | 0.08 | 6436 | 6436 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 20:25 | 20:30 | 0.08 | 6436 | 6450 | 14 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6436.00 t/6450.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 168.00
07/20/2020 | 20:30 | 20:46 | 0.27 | 6450 | 6470 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6450.00 t/6470.00, TF , w/WOB 15.00,Flow 750.00, Press 4000, Tq 0.00, ROP 75.00
07/20/2020 | 20:46 | 21:02 | 0.27 | 6470 | 6530 | 60 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6470.00 t/6530.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 225.00
07/20/2020 | 21:02 | 21:07 | 0.08 | 6530 | 6530 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 21:07 | 21:20 | 0.22 | 6530 | 6624 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6530.00 t/6624.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 433.85
07/20/2020 | 21:20 | 21:25 | 0.08 | 6624 | 6624 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 21:25 | 21:40 | 0.25 | 6624 | 6718 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6624.00 t/6718.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 376.00
07/20/2020 | 21:40 | 21:45 | 0.08 | 6718 | 6718 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 21:45 | 21:58 | 0.22 | 6718 | 6812 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6718.00 t/6812.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000, Tq 18000, ROP 433.85
07/20/2020 | 21:58 | 22:03 | 0.08 | 6812 | 6812 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 22:03 | 22:15 | 0.2 | 6812 | 6905 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6812.00 t/6905.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 465.00
07/20/2020 | 22:15 | 22:20 | 0.08 | 6905 | 6905 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 22:20 | 22:33 | 0.22 | 6905 | 7000 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6905.00 t/7000.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 438.46
07/20/2020 | 22:33 | 22:38 | 0.08 | 7000 | 7000 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 22:38 | 22:43 | 0.08 | 7000 | 7010 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7000.00 t/7010.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 120.00
07/20/2020 | 22:43 | 23:13 | 0.5 | 7010 | 7027 | 17 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7010.00 t/7027.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 0, ROP 34.00
07/20/2020 | 23:13 | 23:25 | 0.2 | 7027 | 7094 | 67 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7027.00 t/7094.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 335.00
07/20/2020 | 23:25 | 23:30 | 0.08 | 7094 | 7094 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/20/2020 | 23:30 | 23:35 | 0.08 | 7094 | 7110 | 16 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7094.00 t/7110.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 192.00
07/20/2020 | 23:35 | 24:00 | 0.42 | 7110 | 7129 | 19 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7110.00 t/7129.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 18000.00, ROP 45.60
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_21_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/21/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 32550
|  |  |  | 24hr Summary: |  | Drill & TD intermediate
|  |  |  | 24hr Lookahead: |  | POOH laying down DP
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 7129 |  | 2769 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 37 | PV: | 14
End Depth (Usft): |  | 10249 |  | 10249 |  | OD (in): |  |  |  | 300: | 23 | YP: | 9
Total Drilled (Usft): |  | 3120 |  | 7480 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 43
Slide Drilled (Usft): |  | 348 |  | 537 | [5 empty] | 100: | 12 | Chlorides: | 38000
Rotary Drilled (Usft): |  | 2772 |  | 6943 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.60
Drlg/Circ Hrs: |  | 19.03 / 0.00 |  | 30.78 / 1.15 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 8.87 |  | 11.17 |  | SN: |  | 43215 |  | 10s Gel: | 6 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 10.17 |  | 19.62 |  | Bit # |  | 2 |  | PH / Temp(F) | 1.4 / 234.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 272.66 / 39.25 |  | 353.93 / 48.09 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 43.17 |  | Grade In: |  | Green
% Slide: |  | 11.15 |  | 7.18 |  | Grade Out:
% Rotary: |  | 88.85 |  | 92.82 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.49 |  |  |  | 9.875 | 2.5 |  |  |  |  | 1.3 |  | 1.3
7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS |  |  |  | 8 | 2.5 |  |  |  |  | 37.32 |  | 38.62
8 Pony Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.81 |  | 46.43
7 3/4 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.86 |  | 50.29
8 Drill Collar |  |  |  | 7.75 | 3.313 |  |  |  |  | 27.12 |  | 77.41
8 Drill Collar |  |  |  | 7.875 | 3.313 |  |  |  |  | 27.4 |  | 104.81
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.75 | 2.875 |  |  |  |  | 3.47 |  | 108.28
2 Stands 6 1/2in Collars |  |  |  | 6.5 | 2.375 |  |  |  |  | 187.21 |  | 295.49
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 3 |  | 298.49
3 Stands of HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.99 |  | 576.48
22 stands of Drillpipe |  |  |  | 6 | 2.75 |  |  |  |  | 2070.98 |  | 2647.46
Safety Joint / Agitator/Shocksub |  |  |  | 7 | 2.625 |  |  |  |  | 30.78 |  | 2678.24
2678.24
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800015 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.65 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
7120 | 13.7 | 137.8 | 6945.37 | -1008.47 | 1039.3 | 1.71 |  | 4.23 | -1341.07 | 1.7 |  | 0.53 | 94
7214 | 12.9 | 137.9 | 7036.85 | -1024.5 | 1053.82 | 0.85 |  | 178.4 | -1361.58 | -0.85 |  | 0.11 | 94
7308 | 11.8 | 135.2 | 7128.67 | -1039.1 | 1067.62 | 1.32 |  | -153.62 | -1380.5 | -1.17 |  | -2.87 | 94
7402 | 10.2 | 133.7 | 7220.94 | -1051.68 | 1080.41 | 1.73 |  | -170.59 | -1397.15 | -1.7 |  | -1.6 | 94
7496 | 10.6 | 137.6 | 7313.4 | -1063.81 | 1092.26 | 0.86 |  | 62.32 | -1413.02 | 0.43 |  | 4.15 | 94
7589 | 8.5 | 142.7 | 7405.11 | -1075.6 | 1102.19 | 2.43 |  | 160.56 | -1427.81 | -2.26 |  | 5.48 | 93
7682 | 9.4 | 138.5 | 7496.97 | -1086.75 | 1111.39 | 1.2 |  | -38.07 | -1441.72 | 0.97 |  | -4.52 | 93
7776 | 11.3 | 141.3 | 7589.44 | -1099.69 | 1122.24 | 2.09 |  | 16.21 | -1457.92 | 2.02 |  | 2.98 | 94
7870 | 11.5 | 136.5 | 7681.59 | -1113.67 | 1134.45 | 1.03 |  | -80.46 | -1475.64 | 0.21 |  | -5.11 | 94
7964 | 12 | 136.2 | 7773.62 | -1127.52 | 1147.66 | 0.54 |  | -7.11 | -1493.63 | 0.53 |  | -0.32 | 94
8058 | 11.3 | 135.4 | 7865.68 | -1141.13 | 1160.89 | 0.76 |  | -167.4 | -1511.41 | -0.74 |  | -0.85 | 94
8153 | 9 | 138.3 | 7959.19 | -1153.31 | 1172.37 | 2.48 |  | 168.9 | -1527.17 | -2.42 |  | 3.05 | 95
8247 | 7.2 | 136.7 | 8052.25 | -1163.09 | 1181.3 | 1.93 |  | -173.65 | -1539.71 | -1.91 |  | -1.7 | 94
8340 | 5.4 | 136.7 | 8144.68 | -1170.52 | 1188.3 | 1.94 |  | 180 | -1549.32 | -1.94 |  | 0 | 93
8434 | 4 | 139.9 | 8238.36 | -1176.24 | 1193.45 | 1.51 |  | 170.98 | -1556.64 | -1.49 |  | 3.4 | 94
8529 | 2.9 | 139.2 | 8333.19 | -1180.6 | 1197.15 | 1.16 |  | -178.16 | -1562.11 | -1.16 |  | -0.74 | 95
8623 | 2.9 | 135.8 | 8427.07 | -1184.1 | 1200.36 | 0.18 |  | -91.7 | -1566.61 | 0 |  | -3.62 | 94
8717 | 2.6 | 136.9 | 8520.96 | -1187.36 | 1203.48 | 0.32 |  | 170.57 | -1570.85 | -0.32 |  | 1.17 | 94
8812 | 2 | 143.6 | 8615.88 | -1190.27 | 1205.93 | 0.69 |  | 159.18 | -1574.5 | -0.63 |  | 7.05 | 95
8906 | 2.5 | 89.3 | 8709.82 | -1191.57 | 1208.96 | 2.23 |  | -104.9 | -1576.9 | 0.53 |  | -57.77 | 94
8997 | 2.7 | 62.3 | 8800.73 | -1190.55 | 1212.84 | 1.35 |  | -94.38 | -1577.53 | 0.22 |  | -29.67 | 91
9090 | 2.5 | 45.2 | 8893.64 | -1188.1 | 1216.22 | 0.86 |  | -112.9 | -1576.64 | -0.22 |  | -18.39 | 93
9184 | 1.4 | 23.5 | 8987.58 | -1185.6 | 1218.13 | 1.39 |  | -156.65 | -1575.12 | -1.17 |  | -23.09 | 94
9278 | 0.4 | 45.4 | 9081.57 | -1184.32 | 1218.82 | 1.11 |  | 171.75 | -1574.23 | -1.06 |  | 0 | 94
9372 | 0.7 | 55.7 | 9175.57 | -1183.76 | 1219.53 | 0.33 |  | 23.44 | -1574 | 0.32 |  | 0 | 94
9465 | 1.3 | 56.9 | 9268.55 | -1182.87 | 1220.88 | 0.65 |  | 2.6 | -1573.73 | 0.65 |  | 0 | 93
9559 | 2.6 | 355.7 | 9362.5 | -1180.16 | 1221.62 | 2.42 |  | -91.18 | -1571.54 | 1.38 |  | 0 | 94
9653 | 5.5 | 332.8 | 9456.26 | -1174.02 | 1219.4 | 3.47 |  | -40.91 | -1565.03 | 3.09 |  | -24.36 | 94
9747 | 7.7 | 331.5 | 9549.63 | -1164.48 | 1214.33 | 2.35 |  | -4.53 | -1554.26 | 2.34 |  | -1.38 | 94
9841 | 9.1 | 333.2 | 9642.62 | -1152.31 | 1207.98 | 1.51 |  | 10.9 | -1540.56 | 1.49 |  | 1.81 | 94
9935 | 10.4 | 341.5 | 9735.27 | -1137.63 | 1201.93 | 2.03 |  | 51.38 | -1524.69 | 1.38 |  | 8.83 | 94
10028 | 13.5 | 338.8 | 9826.24 | -1119.54 | 1195.34 | 3.39 |  | -11.55 | -1505.48 | 3.33 |  | -2.9 | 93
10121 | 16.4 | 337.6 | 9916.09 | -1097.28 | 1186.41 | 3.14 |  | -6.67 | -1481.5 | 3.12 |  | -1.29 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 163.61 | 30.74 | 80 | 205 | 750 | 4142.59 | 3455.56 | 208 | 247.78 | 202.78 | 173.33 | 18785.71 | 2000
Run | 242.54 | 28.85 | 79.19 | 202 | 740.59 | 3889.26 | 3252.89 | 208 | 199.5 | 169.59 | 148.84 | 16343.43 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/21/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/21/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/21/2020 | 00:00 | 00:13 | 0.22 | 7129 | 7188 | 59 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7129.00 t/7188.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 272.31
07/21/2020 | 00:13 | 00:18 | 0.08 | 7188 | 7188 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 00:18 | 00:33 | 0.25 | 7188 | 7282 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7188.00 t/7282.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 376.00
07/21/2020 | 00:33 | 00:38 | 0.08 | 7282 | 7282 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 00:38 | 00:50 | 0.2 | 7282 | 7376 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7282.00 t/7376.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 470.00
07/21/2020 | 00:50 | 00:55 | 0.08 | 7376 | 7376 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 00:55 | 01:07 | 0.2 | 7376 | 7470 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7376.00 t/7470.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 470.00
07/21/2020 | 01:07 | 01:12 | 0.08 | 7470 | 7470 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 01:12 | 01:16 | 0.07 | 7470 | 7477 | 7 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7470.00 t/7477.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 105.00
07/21/2020 | 01:16 | 01:43 | 0.45 | 7477 | 7497 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7477.00 t/7497.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 0, ROP 44.44
07/21/2020 | 01:43 | 01:59 | 0.27 | 7497 | 7564 | 67 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7497.00 t/7564.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 251.25
07/21/2020 | 01:59 | 02:04 | 0.08 | 7564 | 7564 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 02:04 | 02:17 | 0.22 | 7564 | 7657 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7564.00 t/7657.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 429.23
07/21/2020 | 02:17 | 02:20 | 0.05 | 7657 | 7657 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 02:20 | 02:27 | 0.12 | 7657 | 7665 | 8 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7657.00 t/7665.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 68.57
07/21/2020 | 02:27 | 02:55 | 0.47 | 7665 | 7689 | 24 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7665.00 t/7689.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 0, ROP 51.43
07/21/2020 | 02:55 | 03:06 | 0.18 | 7689 | 7750 | 61 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7689.00 t/7750.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 18000.00, ROP 332.73
07/21/2020 | 03:06 | 03:11 | 0.08 | 7750 | 7750 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 03:11 | 03:48 | 0.62 | 7750 | 7778 | 28 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7750.00 t/7778.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 0, ROP 45.41
07/21/2020 | 03:48 | 04:07 | 0.32 | 7778 | 7844 | 66 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7778.00 t/7844.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000.00, Tq 19000, ROP 208.42
07/21/2020 | 04:07 | 04:12 | 0.08 | 7844 | 7844 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 04:12 | 04:17 | 0.08 | 7844 | 7860 | 16 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7844.00 t/7860.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000.00, Tq 19000, ROP 192.00
07/21/2020 | 04:17 | 04:35 | 0.3 | 7860 | 7880 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7860.00 t/7880.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 0.00, ROP 66.67
07/21/2020 | 04:35 | 04:49 | 0.23 | 7880 | 7938 | 58 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7880.00 t/7938.00, w/WOB 15.00,Flow 750.00, RPM 80, Press 4000.00, Tq 19000, ROP 248.57
07/21/2020 | 04:49 | 04:54 | 0.08 | 7938 | 7938 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 04:54 | 05:00 | 0.1 | 7938 | 7955 | 17 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7938.00 t/7955.00, w/WOB 15.00,Flow 750.00, RPM 80.00, Press 4000.00, Tq 19000.00, ROP 170.00
07/21/2020 | 05:00 | 05:12 | 0.2 | 7955 | 7970 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7955.00 t/7970.00, TF , w/WOB 15.00,Flow 750.00, Press 4000.00, Tq 0, ROP 75.00
07/21/2020 | 05:12 | 05:35 | 0.38 | 7970 | 8032 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7970.00 t/8032.00, w/WOB 40,Flow 750.00, RPM 80, Press 4200, Tq 19000, ROP 161.74
07/21/2020 | 05:35 | 05:40 | 0.08 | 8032 | 8032 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 05:40 | 05:55 | 0.25 | 8032 | 8126 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8032.00 t/8126.00, w/WOB 40,Flow 750.00, RPM 80, Press 4200, Tq 19000, ROP 376.00
07/21/2020 | 05:55 | 06:00 | 0.08 | 8126 | 8126 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 06:00 | 06:11 | 0.18 | 8126 | 8221 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8126.00 t/8221.00, w/WOB 40,Flow 750.00, RPM 80, Press 4200, Tq 19000, ROP 518.18
07/21/2020 | 06:11 | 06:15 | 0.07 | 8221 | 8221 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 06:15 | 06:30 | 0.25 | 8221 | 8315 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8221.00 t/8315.00, w/WOB 40,Flow 750.00, RPM 80, Press 4200, Tq 19000, ROP 376.00
07/21/2020 | 06:30 | 06:35 | 0.08 | 8315 | 8315 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 06:35 | 06:47 | 0.2 | 8315 | 8408 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8315.00 t/8408.00, w/WOB 40,Flow 750.00, RPM 80, Press 4200, Tq 19000, ROP 465.00
07/21/2020 | 06:47 | 06:52 | 0.08 | 8408 | 8408 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 06:52 | 07:06 | 0.23 | 8408 | 8502 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8408.00 t/8502.00, w/WOB 40,Flow 750.00, RPM 80, Press 4200, Tq 19000, ROP 402.86
07/21/2020 | 07:06 | 07:10 | 0.07 | 8502 | 8502 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 07:10 | 07:24 | 0.23 | 8502 | 8597 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8502.00 t/8597.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 407.14
07/21/2020 | 07:24 | 07:30 | 0.1 | 8597 | 8597 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 07:30 | 07:42 | 0.2 | 8597 | 8691 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8597.00 t/8691.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 470.00
07/21/2020 | 07:42 | 07:47 | 0.08 | 8691 | 8691 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 07:47 | 08:00 | 0.22 | 8691 | 8785 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8691.00 t/8785.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 433.85
07/21/2020 | 08:00 | 08:05 | 0.08 | 8785 | 8785 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 08:05 | 08:18 | 0.22 | 8785 | 8880 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8785.00 t/8880.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 438.46
07/21/2020 | 08:18 | 08:23 | 0.08 | 8880 | 8880 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 08:23 | 08:27 | 0.07 | 8880 | 8890 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8880.00 t/8890.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 150.00
07/21/2020 | 08:27 | 08:45 | 0.3 | 8890 | 8910 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8890.00 t/8910.00, TF , w/WOB 30,Flow 750.00, Press 3600, Tq 0, ROP 66.67
07/21/2020 | 08:45 | 09:00 | 0.25 | 8910 | 8974 | 64 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8910.00 t/8974.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 256.00
07/21/2020 | 09:00 | 09:05 | 0.08 | 8974 | 8974 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 09:05 | 09:20 | 0.25 | 8974 | 9065 | 91 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8974.00 t/9065.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 364.00
07/21/2020 | 09:20 | 09:25 | 0.08 | 9065 | 9065 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 09:25 | 09:38 | 0.22 | 9065 | 9158 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9065.00 t/9158.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 429.23
07/21/2020 | 09:38 | 09:43 | 0.08 | 9158 | 9158 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 09:43 | 09:46 | 0.05 | 9158 | 9170 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9158.00 t/9170.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 240.00
07/21/2020 | 09:46 | 10:01 | 0.25 | 9170 | 9185 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9170.00 t/9185.00, TF , w/WOB 30.00,Flow 750.00, Press 3600.00, Tq 0.00, ROP 60.00
07/21/2020 | 10:01 | 10:13 | 0.2 | 9185 | 9252 | 67 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9185.00 t/9252.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 335.00
07/21/2020 | 10:13 | 10:18 | 0.08 | 9252 | 9252 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 10:18 | 10:40 | 0.37 | 9252 | 9346 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9252.00 t/9346.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 256.36
07/21/2020 | 10:40 | 10:45 | 0.08 | 9346 | 9346 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 10:45 | 11:15 | 0.5 | 9346 | 9440 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9346.00 t/9440.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4200.00, Tq 19000.00, ROP 188.00
07/21/2020 | 11:15 | 11:59 | 0.73 | 9440 | 9440 | 0 | INT | 2: BHA #2 (Intermediate) | 8P | Rig Service
07/21/2020 | 11:59 | 12:05 | 0.1 | 9440 | 9440 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 12:05 | 12:32 | 0.45 | 9440 | 9533 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9440.00 t/9533.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400, Tq 19000.00, ROP 206.67
07/21/2020 | 12:32 | 12:37 | 0.08 | 9533 | 9533 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 12:37 | 12:41 | 0.07 | 9533 | 9545 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9533.00 t/9545.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400, Tq 19000.00, ROP 180.00
07/21/2020 | 12:41 | 13:34 | 0.88 | 9545 | 9580 | 35 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9545.00 t/9580.00, TF , w/WOB 30,Flow 750.00, Press 3900, Tq 0, ROP 39.62
07/21/2020 | 13:34 | 14:50 | 1.27 | 9580 | 9580 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | Survey & Connection
07/21/2020 | 14:50 | 15:09 | 0.32 | 9580 | 9627 | 47 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9580.00 t/9627.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 148.42
07/21/2020 | 15:09 | 15:18 | 0.15 | 9627 | 9627 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 15:18 | 15:25 | 0.12 | 9627 | 9650 | 23 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9627.00 t/9650.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 197.14
07/21/2020 | 15:25 | 15:58 | 0.55 | 9650 | 9670 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9650.00 t/9670.00, TF , w/WOB 30.00,Flow 750.00, Press 3900.00, Tq 0.00, ROP 36.36
07/21/2020 | 15:58 | 16:16 | 0.3 | 9670 | 9721 | 51 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9670.00 t/9721.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 170.00
07/21/2020 | 16:16 | 16:23 | 0.12 | 9721 | 9721 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 16:23 | 16:30 | 0.12 | 9721 | 9750 | 29 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9721.00 t/9750.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 248.57
07/21/2020 | 16:30 | 16:50 | 0.33 | 9750 | 9766 | 16 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9750.00 t/9766.00, TF 0.00, w/WOB 30.00,Flow 750.00, Press 3900.00, Tq 0.00, ROP 48.00
07/21/2020 | 16:50 | 17:05 | 0.25 | 9766 | 9815 | 49 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9766.00 t/9815.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 196.00
07/21/2020 | 17:05 | 17:12 | 0.12 | 9815 | 9815 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 17:12 | 17:17 | 0.08 | 9815 | 9840 | 25 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9815.00 t/9840.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 300.00
07/21/2020 | 17:17 | 17:45 | 0.47 | 9840 | 9860 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9840.00 t/9860.00, TF , w/WOB 40.00,Flow 750.00, Press 4400.00, Tq 0, ROP 42.86
07/21/2020 | 17:45 | 18:02 | 0.28 | 9860 | 9909 | 49 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9860.00 t/9909.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 172.94
07/21/2020 | 18:02 | 18:07 | 0.08 | 9909 | 9909 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 18:07 | 18:13 | 0.1 | 9909 | 9930 | 21 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9909.00 t/9930.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 210.00
07/21/2020 | 18:13 | 19:25 | 1.2 | 9930 | 9955 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9930.00 t/9955.00, TF , w/WOB 40.00,Flow 750.00, Press 4400.00, Tq 0, ROP 20.83
07/21/2020 | 19:25 | 19:38 | 0.22 | 9955 | 10003 | 48 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9955.00 t/10003.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 221.54
07/21/2020 | 19:38 | 19:45 | 0.12 | 10003 | 10003 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | BOP Drill
07/21/2020 | 19:45 | 19:50 | 0.08 | 10003 | 10003 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 19:50 | 19:57 | 0.12 | 10003 | 10017 | 14 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10003.00 t/10017.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 120.00
07/21/2020 | 19:57 | 20:45 | 0.8 | 10017 | 10047 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10017.00 t/10047.00, TF , w/WOB 40.00,Flow 750.00, Press 4400.00, Tq 19000.00, ROP 37.50
07/21/2020 | 20:45 | 21:00 | 0.25 | 10047 | 10096 | 49 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10047.00 t/10096.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 196.00
07/21/2020 | 21:00 | 21:05 | 0.08 | 10096 | 10096 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 21:05 | 21:09 | 0.07 | 10096 | 10111 | 15 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10096.00 t/10111.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 225.00
07/21/2020 | 21:09 | 21:50 | 0.68 | 10111 | 10141 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10111.00 t/10141.00, TF , w/WOB 40.00,Flow 750.00, Press 4400.00, Tq 19000.00, ROP 43.90
07/21/2020 | 21:50 | 22:08 | 0.3 | 10141 | 10189 | 48 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10141.00 t/10189.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 160.00
07/21/2020 | 22:08 | 22:13 | 0.08 | 10189 | 10189 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
07/21/2020 | 22:13 | 22:23 | 0.17 | 10189 | 10205 | 16 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10189.00 t/10205.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 96.00
07/21/2020 | 22:23 | 23:45 | 1.37 | 10205 | 10235 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10205.00 t/10235.00, TF , w/WOB 40.00,Flow 750.00, Press 4400.00, Tq 19000.00, ROP 21.95
07/21/2020 | 23:45 | 24:00 | 0.25 | 10235 | 10249 | 14 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10235.00 t/10249.00, w/WOB 40.00,Flow 750.00, RPM 80.00, Press 4400.00, Tq 19000.00, ROP 56.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_22_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/22/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 32550
|  |  |  | 24hr Summary: |  | TDed well
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10249 |  | 2769 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 37 | PV: | 14
End Depth (Usft): |  | 10249 |  | 10249 |  | OD (in): |  |  |  | 300: | 23 | YP: | 9
Total Drilled (Usft): |  |  |  | 7480 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 43
Slide Drilled (Usft): |  |  |  | 537 | [5 empty] | 100: | 12 | Chlorides: | 38000
Rotary Drilled (Usft): |  |  |  | 6943 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.60
Drlg/Circ Hrs: |  | 0.00 / 1.75 |  | 30.78 / 2.90 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  |  |  | 11.17 |  | SN: |  | 43215 |  | 10s Gel: | 6 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  |  |  | 19.62 |  | Bit # |  | 2 |  | PH / Temp(F) | 1.4 / 234.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 353.93 / 48.09 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 13.5 |  | 56.67 |  | Grade In: |  | Green
% Slide: |  |  |  | 7.18 |  | Grade Out:
% Rotary: |  |  |  | 92.82 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.49 |  |  |  | 9.875 | 2.5 |  |  |  |  | 1.3 |  | 1.3
7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS |  |  |  | 8 | 2.5 |  |  |  |  | 37.32 |  | 38.62
8 Pony Collar |  |  |  | 7.938 | 3.25 |  |  |  |  | 7.81 |  | 46.43
7 3/4 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.86 |  | 50.29
8 Drill Collar |  |  |  | 7.75 | 3.313 |  |  |  |  | 27.12 |  | 77.41
8 Drill Collar |  |  |  | 7.875 | 3.313 |  |  |  |  | 27.4 |  | 104.81
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.75 | 2.875 |  |  |  |  | 3.47 |  | 108.28
2 Stands 6 1/2in Collars |  |  |  | 6.5 | 2.375 |  |  |  |  | 187.21 |  | 295.49
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 3 |  | 298.49
3 Stands of HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.99 |  | 576.48
22 stands of Drillpipe |  |  |  | 6 | 2.75 |  |  |  |  | 2070.98 |  | 2647.46
Safety Joint / Agitator/Shocksub |  |  |  | 7 | 2.625 |  |  |  |  | 30.78 |  | 2678.24
2678.24
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800015 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.65 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30.74 | 80 | 205 | 750 | 4142.59 | 3455.56 | 208 | 247.78 | 202.78 | 173.33 | 18785.71 | 2000
Run | 242.54 | 28.85 | 79.19 | 202 | 740.59 | 3889.26 | 3252.89 | 208 | 199.5 | 169.59 | 148.84 | 16343.43 | 2000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/22/2020 | 00:00 | 01:45 | 1.75 | 10249 | 10249 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate
07/22/2020 | 01:45 | 11:30 | 9.75 | 10249 | 10249 | 0 | INT | 2: BHA #2 (Intermediate) | 6K | POOH, L/D drillpipe
07/22/2020 | 11:30 | 13:30 | 2 | 10249 | 10249 | 0 | INT | 2: BHA #2 (Intermediate) | 6P | Lay down BHA #2
07/22/2020 | 13:30 | 24:00 | 10.5 | 10249 | 10249 | 0 | INT |  | 24B | Standby for intermediate casing opps.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_23_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/23/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 37350
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10249 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 37 | PV: | 14
End Depth (Usft): |  | 10249 |  | 10249 |  | OD (in): |  |  |  | 300: | 23 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 43
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 38000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.60
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 6 | Weight (ppg): | 9.3
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 1.4 / 234.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30.74 | 80 | 205 | 750 | 4142.59 | 3455.56 | 208 | 247.78 | 202.78 | 173.33 | 18785.71 | 2000
Run | 0 | 28.85 | 79.19 | 202 | 740.59 | 3889.26 | 3252.89 | 208 | 199.5 | 169.59 | 148.84 | 16343.43 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 07/23/2020 |  | 3 |  | 4400 |  | 1 | 4400
Perdiem Per Hand |  |  |  |  | 07/23/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/23/2020 | 00:00 | 24:00 | 24 | 10249 | 10249 | 0 | INT |  | 24B | Standby for intermediate casing opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_24_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/24/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 44600
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10249 |  | 10249 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 37 | PV: | 14
End Depth (Usft): |  | 10259 |  | 10259 |  | OD (in): |  |  |  | 300: | 23 | YP: | 9
Total Drilled (Usft): |  | 10 |  | 10 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 43
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 38000
Rotary Drilled (Usft): |  | 10 |  | 10 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.60
Drlg/Circ Hrs: |  | 0.07 / 1.43 |  | 0.07 / 1.43 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 48479 |  | 10s Gel: | 6 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 0.07 |  | 0.07 |  | Bit # |  | 3 |  | PH / Temp(F) | 1.4 / 234.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 150.00 / 0.00 |  | 150.00 / 0.00 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 16.5 |  | 16.5 |  | Grade In: |  | Green
% Slide: | [5 empty] | Grade Out: |  | Green
% Rotary: |  | 100 |  | 100 |  | Make / Model: |  | Ulterra / RPS613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Ulterra RPS 613 6x16s - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.85 |  | 0.85
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | [5 empty] | 33.39 |  | 34.24
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.49
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 48.39
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 51.88
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 82.66
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 113.53
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 117.05
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2710.25
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2713.47
Agitator |  |  |  | 5 | 3 |  |  |  |  | 29.01 |  | 2742.48
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2745.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475113 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.44 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10181 | 17.3 | 336 | 9973.51 | -1081.3 | 1179.55 | 1.69 |  | -28.03 | -1464.11 | 1.5 |  | -2.67 | 60
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30.74 | 80 | 590 | 750 | 4142.59 | 3455.56 | 208 | 247.78 | 202.78 | 173.33 | 18785.71 | 2000
Run | 0 | 28.85 | 79.19 | 583 | 740.59 | 3889.26 | 3252.89 | 208 | 199.5 | 169.59 | 148.84 | 16343.43 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/24/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/24/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/24/2020 | 00:00 | 05:00 | 5 | 10249 | 10249 | 0 | CRV |  | 24B | Standby
07/24/2020 | 05:00 | 05:30 | 0.5 | 10249 | 10249 | 0 | CRV |  | 24A | Gather BHA #3 tools to prepare to pick up.
07/24/2020 | 05:30 | 07:30 | 2 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 6O | Pick up BHA #3
07/24/2020 | 07:30 | 07:45 | 0.25 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 5A | Shallow test MWD, No bit
07/24/2020 | 07:45 | 08:35 | 0.83 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 6L | L/D motor
07/24/2020 | 08:35 | 08:45 | 0.17 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 5A | Shallow test MWD, No bit
07/24/2020 | 08:45 | 09:00 | 0.25 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 6L | Make up bit
07/24/2020 | 09:00 | 22:30 | 13.5 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 6A | TIH, picking up 4 1/2" Drill Pipe
07/24/2020 | 22:30 | 23:10 | 0.67 | 10249 | 10249 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 5A | Drill out float and shoe track
07/24/2020 | 23:10 | 23:14 | 0.07 | 10249 | 10259 | 10 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10249.00 t/10259.00, w/WOB 15,Flow 260, RPM 30, Press 2750, Tq 5000, ROP 150.00
07/24/2020 | 23:14 | 23:35 | 0.35 | 10259 | 10259 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 5A | Circulate
07/24/2020 | 23:35 | 24:00 | 0.42 | 10259 | 10259 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 15D | Perform FIT
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_25_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/25/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 51850
|  |  |  | 24hr Summary: |  | TIH, Drill curve
|  |  |  | 24hr Lookahead: |  | Drill lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10259 |  | 10249 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 11878 |  | 11878 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 1619 |  | 1629 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): |  | 698 |  | 698 | [5 empty] | 100: | 14 | Chlorides: | 43000
Rotary Drilled (Usft): |  | 921 |  | 931 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 4.90
Drlg/Circ Hrs: |  | 21.27 / 0.08 |  | 21.33 / 1.52 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 14.75 |  | 14.75 |  | SN: |  | 48479 |  | 10s Gel: | 6 | Weight (ppg): | 9
Rotary Drilling Hrs: |  | 6.52 |  | 6.58 |  | Bit # |  | 3 |  | PH / Temp(F) | 1.4 / 278.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): |  | 141.33 / 47.32 |  | 141.42 / 47.32 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 40.5 |  | Grade In: |  | Green
% Slide: |  | 43.11 |  | 42.85 |  | Grade Out: |  | Green
% Rotary: |  | 56.89 |  | 57.15 |  | Make / Model: |  | Ulterra / RPS613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
Kevin Burt |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Ulterra RPS 613 6x16s - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.85 |  | 0.85
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | [5 empty] | 33.39 |  | 34.24
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.49
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 48.39
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 51.88
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 82.66
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 113.53
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 117.05
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2710.25
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2713.47
Agitator |  |  |  | 5 | 3 |  |  |  |  | 29.01 |  | 2742.48
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2745.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475113 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.44 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10256 | 20.2 | 338.1 | 10044.52 | -1059.09 | 1170.19 | 3.97 |  | 14.1 | -1440.01 | 3.87 |  | 2.8 | 75
10351 | 28 | 336.6 | 10131.18 | -1023.35 | 1155.19 | 8.24 |  | -5.18 | -1401.26 | 8.21 |  | -1.58 | 95
10447 | 30.5 | 332.1 | 10214.94 | -981.13 | 1134.83 | 3.47 |  | -43.31 | -1354.42 | 2.6 |  | -4.69 | 96
10542 | 43.6 | 334.3 | 10290.6 | -930.08 | 1109.24 | 13.86 |  | 6.67 | -1297.38 | 13.79 |  | 2.32 | 95
10638 | 46 | 332.9 | 10358.71 | -869.51 | 1079.15 | 2.7 |  | -22.84 | -1229.82 | 2.5 |  | -1.46 | 96
10685 | 49.9 | 334.2 | 10390.19 | -838.26 | 1063.62 | 8.55 |  | 14.34 | -1194.97 | 8.3 |  | 2.77 | 47
10732 | 57.7 | 335.1 | 10417.93 | -804.01 | 1047.4 | 16.67 |  | 5.59 | -1157.09 | 16.6 |  | 1.91 | 47
10779 | 62.1 | 338.3 | 10441.49 | -766.67 | 1031.35 | 11.06 |  | 32.99 | -1116.45 | 9.36 |  | 6.81 | 47
10826 | 67.7 | 340.8 | 10461.43 | -726.8 | 1016.51 | 12.85 |  | 22.55 | -1073.98 | 11.91 |  | 5.32 | 47
10873 | 72.6 | 338.6 | 10477.38 | -685.36 | 1001.16 | 11.32 |  | -23.28 | -1029.86 | 10.43 |  | -4.68 | 47
10921 | 78.9 | 337 | 10489.19 | -642.31 | 983.59 | 13.52 |  | -14.03 | -983.38 | 13.13 |  | -3.33 | 48
10968 | 81.5 | 335.3 | 10497.19 | -599.96 | 964.86 | 6.58 |  | -32.94 | -937.07 | 5.53 |  | -3.62 | 47
11017 | 84.2 | 334.1 | 10503.29 | -556.01 | 944.08 | 6.02 |  | -23.87 | -888.48 | 5.51 |  | -2.45 | 49
11064 | 85.1 | 332.8 | 10507.67 | -514.15 | 923.17 | 3.35 |  | -55.25 | -841.74 | 1.91 |  | -2.77 | 47
11111 | 85.9 | 331.5 | 10511.36 | -472.72 | 901.28 | 3.24 |  | -58.37 | -795.01 | 1.7 |  | -2.77 | 47
11206 | 92.7 | 333.5 | 10512.52 | -388.52 | 857.44 | 7.46 |  | 16.41 | -700.29 | 7.16 |  | 2.11 | 95
11301 | 93.7 | 332.3 | 10507.22 | -304.08 | 814.24 | 1.64 |  | -50.12 | -605.61 | 1.05 |  | -1.26 | 95
11397 | 93.9 | 335 | 10500.85 | -218.25 | 771.72 | 2.81 |  | 85.67 | -509.93 | 0.21 |  | 2.81 | 96
11491 | 91.9 | 337.5 | 10496.1 | -132.33 | 733.92 | 3.4 |  | 128.63 | -416.06 | -2.13 |  | 2.66 | 94
11585 | 92.5 | 337.2 | 10492.49 | -45.65 | 697.75 | 0.71 |  | -26.54 | -322.15 | 0.64 |  | -0.32 | 94
11680 | 91.3 | 341.2 | 10489.34 | 43.09 | 664.04 | 4.39 |  | 106.63 | -227.34 | -1.26 |  | 4.21 | 95
11774 | 91.7 | 341.4 | 10486.88 | 132.1 | 633.91 | 0.48 |  | 26.55 | -133.73 | 0.43 |  | 0.21 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 76.15 | 28.33 | 30 | 302 | 400 | 4533.33 | 3700 | 208 | 240 | 200 | 180 | 12000 | 2000
Run | 76.37 | 26.43 | 30 | 288 | 380 | 4278.57 | 3528.57 | 208 | 240 | 200 | 180 | 10250 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/25/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/25/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/25/2020 | 00:00 | 01:00 | 1 | 10259 | 10314 | 55 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10259.00 t/10314.00, TF 0.00, w/WOB 25.00,Flow 400.00, Press 4200.00, Tq 0.00, ROP 55.00
07/25/2020 | 01:00 | 01:14 | 0.23 | 10314 | 10326 | 12 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10314.00 t/10326.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 51.43
07/25/2020 | 01:14 | 01:24 | 0.17 | 10326 | 10326 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 01:24 | 01:37 | 0.22 | 10326 | 10341 | 15 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10326.00 t/10341.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 69.23
07/25/2020 | 01:37 | 02:24 | 0.78 | 10341 | 10381 | 40 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10341.00 t/10381.00, TF 0.00, w/WOB 25.00,Flow 400.00, Press 4200.00, Tq 0.00, ROP 51.06
07/25/2020 | 02:24 | 02:40 | 0.27 | 10381 | 10421 | 40 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10381.00 t/10421.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 150.00
07/25/2020 | 02:40 | 02:50 | 0.17 | 10421 | 10421 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 02:50 | 04:35 | 1.75 | 10421 | 10517 | 96 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10421.00 t/10517.00, TF 0.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 54.86
07/25/2020 | 04:35 | 04:45 | 0.17 | 10517 | 10517 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 04:45 | 05:44 | 0.98 | 10517 | 10580 | 63 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10517.00 t/10580.00, TF , w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 64.07
07/25/2020 | 05:44 | 05:49 | 0.08 | 10580 | 10580 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 5A | Check shot
07/25/2020 | 05:49 | 06:00 | 0.18 | 10580 | 10612 | 32 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10580.00 t/10612.00, w/WOB 30.00,Flow 400.00, RPM 30, Press 4700.00, Tq 12000, ROP 174.55
07/25/2020 | 06:00 | 06:05 | 0.08 | 10612 | 10612 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 06:05 | 06:24 | 0.32 | 10612 | 10644 | 32 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10612.00 t/10644.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 101.05
07/25/2020 | 06:24 | 07:24 | 1 | 10644 | 10708 | 64 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10644.00 t/10708.00, TF 0.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 12000.00, ROP 64.00
07/25/2020 | 07:24 | 07:29 | 0.08 | 10708 | 10708 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 07:29 | 07:40 | 0.18 | 10708 | 10711 | 3 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10708.00 t/10711.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 16.36
07/25/2020 | 07:40 | 08:32 | 0.87 | 10711 | 10755 | 44 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10711.00 t/10755.00, TF , w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 12000.00, ROP 50.77
07/25/2020 | 08:32 | 08:37 | 0.08 | 10755 | 10755 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 08:37 | 09:26 | 0.82 | 10755 | 10802 | 47 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10755.00 t/10802.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 57.55
07/25/2020 | 09:26 | 09:32 | 0.1 | 10802 | 10802 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 09:32 | 10:20 | 0.8 | 10802 | 10849 | 47 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10802.00 t/10849.00, TF , w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 12000.00, ROP 58.75
07/25/2020 | 10:20 | 10:25 | 0.08 | 10849 | 10849 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 10:25 | 10:33 | 0.13 | 10849 | 10854 | 5 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10849.00 t/10854.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 37.50
07/25/2020 | 10:33 | 11:17 | 0.73 | 10854 | 10896 | 42 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10854.00 t/10896.00, TF , w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 12000.00, ROP 57.27
07/25/2020 | 11:17 | 11:25 | 0.13 | 10896 | 10896 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 11:25 | 11:29 | 0.07 | 10896 | 10901 | 5 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10896.00 t/10901.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 75.00
07/25/2020 | 11:29 | 12:05 | 0.6 | 10901 | 10936 | 35 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10901.00 t/10936.00, TF 0.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 58.33
07/25/2020 | 12:05 | 12:17 | 0.2 | 10936 | 10943 | 7 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10936.00 t/10943.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 35.00
07/25/2020 | 12:17 | 12:22 | 0.08 | 10943 | 10943 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 12:22 | 12:31 | 0.15 | 10943 | 10960 | 17 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10943.00 t/10960.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 113.33
07/25/2020 | 12:31 | 13:07 | 0.6 | 10960 | 10991 | 31 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/10960.00 t/10991.00, TF 0.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 51.67
07/25/2020 | 13:07 | 13:12 | 0.08 | 10991 | 10991 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 13:12 | 13:30 | 0.3 | 10991 | 11038 | 47 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/10991.00 t/11038.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 156.67
07/25/2020 | 13:30 | 13:35 | 0.08 | 11038 | 11038 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 13:35 | 13:42 | 0.12 | 11038 | 11058 | 20 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11038.00 t/11058.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 171.43
07/25/2020 | 13:42 | 14:07 | 0.42 | 11058 | 11073 | 15 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11058.00 t/11073.00, TF 0.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 36.00
07/25/2020 | 14:07 | 14:14 | 0.12 | 11073 | 11087 | 14 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11073.00 t/11087.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 120.00
07/25/2020 | 14:14 | 14:33 | 0.32 | 11087 | 11134 | 47 | CRV | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11087.00 t/11134.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 148.42
07/25/2020 | 14:33 | 14:38 | 0.08 | 11134 | 11134 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 14:38 | 15:40 | 1.03 | 11134 | 11181 | 47 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11134.00 t/11181.00, TF 20.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 45.48
07/25/2020 | 15:40 | 15:45 | 0.08 | 11181 | 11181 | 0 | CRV | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 15:45 | 16:20 | 0.58 | 11181 | 11196 | 15 | CRV | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11181.00 t/11196.00, TF 90.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 25.71
07/25/2020 | 16:20 | 16:48 | 0.47 | 11196 | 11276 | 80 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11196.00 t/11276.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 171.43
07/25/2020 | 16:48 | 16:54 | 0.1 | 11276 | 11276 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 16:54 | 17:22 | 0.47 | 11276 | 11371 | 95 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11276.00 t/11371.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 203.57
07/25/2020 | 17:22 | 17:52 | 0.5 | 11371 | 11371 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 8P | Rig service
07/25/2020 | 17:52 | 17:58 | 0.1 | 11371 | 11371 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 17:58 | 18:03 | 0.08 | 11371 | 11380 | 9 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11371.00 t/11380.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 108.00
07/25/2020 | 18:03 | 19:15 | 1.2 | 11380 | 11405 | 25 | LAT | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11380.00 t/11405.00, TF 140.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 20.83
07/25/2020 | 19:15 | 19:31 | 0.27 | 11405 | 11467 | 62 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11405.00 t/11467.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 232.50
07/25/2020 | 19:31 | 19:37 | 0.1 | 11467 | 11467 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 19:37 | 19:43 | 0.1 | 11467 | 11475 | 8 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11467.00 t/11475.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 80.00
07/25/2020 | 19:43 | 20:30 | 0.78 | 11475 | 11495 | 20 | LAT | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11475.00 t/11495.00, TF 170.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 0.00, ROP 25.53
07/25/2020 | 20:30 | 20:47 | 0.28 | 11495 | 11561 | 66 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11495.00 t/11561.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 232.94
07/25/2020 | 20:47 | 20:53 | 0.1 | 11561 | 11561 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 20:53 | 21:15 | 0.37 | 11561 | 11657 | 96 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11561.00 t/11657.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 12000.00, ROP 261.82
07/25/2020 | 21:15 | 21:22 | 0.12 | 11657 | 11657 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 21:22 | 22:24 | 1.03 | 11657 | 11688 | 31 | LAT | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11657.00 t/11688.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 12000.00, ROP 30.00
07/25/2020 | 22:24 | 22:48 | 0.4 | 11688 | 11750 | 62 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11688.00 t/11750.00, w/WOB 30.00,Flow 400.00, RPM 70, Press 4700.00, Tq 12000.00, ROP 155.00
07/25/2020 | 22:48 | 22:52 | 0.07 | 11750 | 11750 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 22:52 | 23:12 | 0.33 | 11750 | 11844 | 94 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11750.00 t/11844.00, w/WOB 30.00,Flow 400.00, RPM 70, Press 4700.00, Tq 12000.00, ROP 282.00
07/25/2020 | 23:12 | 23:17 | 0.08 | 11844 | 11844 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/25/2020 | 23:17 | 23:25 | 0.13 | 11844 | 11850 | 6 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11844.00 t/11850.00, w/WOB 30.00,Flow 400.00, RPM 70, Press 4700.00, Tq 12000.00, ROP 45.00
07/25/2020 | 23:25 | 24:00 | 0.58 | 11850 | 11878 | 28 | LAT | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/11850.00 t/11878.00, TF , w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 12000.00, ROP 48.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_26_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/26/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19250 |  |  | Well Cost($): |  | 71100
|  |  |  | 24hr Summary: |  | Drilling lateral maintaing a 0-15 window
|  |  |  | 24hr Lookahead: |  | Drilling lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11878 |  | 12413 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 12413 |  | 12413 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 41
Slide Drilled (Usft): | [9 empty] | 100: | 14 | Chlorides: | 43000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 4.90
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 48479 |  | 10s Gel: | 6 | Weight (ppg): | 9
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 1.4 / 278.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 5.5 |  | 5.5 |  | Grade In: |  | Green
% Slide: | [5 empty] | Grade Out: |  | Green
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / RPS613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Ulterra RPS 613 6x16s - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.85 |  | 0.85
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | [5 empty] | 33.39 |  | 34.24
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.49
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 48.39
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 51.88
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 82.66
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 113.53
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 117.05
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2710.25
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2713.47
Agitator |  |  |  | 5 | 3 |  |  |  |  | 29.01 |  | 2742.48
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2745.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475113 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.44 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11868 | 91.2 | 340 | 10484.5 | 220.79 | 602.86 | 1.58 |  | -109.64 | -40.04 | -0.53 |  | -1.49 | 94
11964 | 90.6 | 338.5 | 10482.99 | 310.54 | 568.85 | 1.68 |  | -111.79 | 55.82 | -0.63 |  | -1.56 | 96
12059 | 90.9 | 338.2 | 10481.75 | 398.83 | 533.8 | 0.45 |  | -45 | 150.75 | 0.32 |  | -0.32 | 95
12154 | 92.3 | 335.7 | 10479.1 | 486.21 | 496.63 | 3.02 |  | -60.71 | 245.7 | 1.47 |  | -2.63 | 95
12249 | 93.5 | 334.2 | 10474.29 | 572.16 | 456.46 | 2.02 |  | -51.27 | 340.54 | 1.26 |  | -1.58 | 95
12342 | 94.5 | 334.6 | 10467.8 | 655.82 | 416.37 | 1.16 |  | 21.74 | 433.27 | 1.08 |  | 0.43 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 145.78 | 28.33 | 30 | 302 | 400 | 4533.33 | 3700 | 208 | 240 | 200 | 180 | 12000 | 2000
Run | 86.56 | 26.43 | 30 | 288 | 380 | 4278.57 | 3528.57 | 208 | 240 | 200 | 180 | 10250 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/26/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/26/2020 |  | 4 |  | 100 |  | 4 | 400
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 07/26/2020 |  | 6 |  | 1500 |  | 1 | 1500
5 Premium Motor Stator Reline |  |  |  |  | 07/26/2020 |  | 9 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 19250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/26/2020 | 00:00 | 00:45 | 0.75 | 11878 | 11938 | 60 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11878.00 t/11938.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 12000.00, ROP 80.00
07/26/2020 | 00:45 | 00:50 | 0.08 | 11938 | 11938 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/26/2020 | 00:50 | 01:10 | 0.33 | 11938 | 12034 | 96 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/11938.00 t/12034.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 12000.00, ROP 288.00
07/26/2020 | 01:10 | 01:15 | 0.08 | 12034 | 12034 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/26/2020 | 01:15 | 01:34 | 0.32 | 12034 | 12129 | 95 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/12034.00 t/12129.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 12000.00, ROP 300.00
07/26/2020 | 01:34 | 01:39 | 0.08 | 12129 | 12129 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/26/2020 | 01:39 | 01:45 | 0.1 | 12129 | 12139 | 10 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/12129.00 t/12139.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 12000.00, ROP 100.00
07/26/2020 | 01:45 | 02:25 | 0.67 | 12139 | 12154 | 15 | LAT | 3: BHA 3 (Curve-Lateral) | 2J | Slide Drill f/12139.00 t/12154.00, TF , w/WOB 30.00,Flow 400.00, Press 4700.00, Tq 15500, ROP 22.50
07/26/2020 | 02:25 | 02:41 | 0.27 | 12154 | 12224 | 70 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/12154.00 t/12224.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 15500.00, ROP 262.50
07/26/2020 | 02:41 | 02:46 | 0.08 | 12224 | 12224 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/26/2020 | 02:46 | 03:10 | 0.4 | 12224 | 12319 | 95 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/12224.00 t/12319.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 15500.00, ROP 237.50
07/26/2020 | 03:10 | 03:15 | 0.08 | 12319 | 12319 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/26/2020 | 03:15 | 03:20 | 0.08 | 12319 | 12342 | 23 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/12319.00 t/12342.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 15500.00, ROP 276.00
07/26/2020 | 03:20 | 04:05 | 0.75 | 12342 | 12342 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 5C | Circulate for losses
07/26/2020 | 04:05 | 04:50 | 0.75 | 12342 | 12413 | 71 | LAT | 3: BHA 3 (Curve-Lateral) | 2K | Rotary Drill f/12342.00 t/12413.00, w/WOB 30.00,Flow 400.00, RPM 70.00, Press 4700.00, Tq 15500.00, ROP 94.67
07/26/2020 | 04:50 | 06:35 | 1.75 | 12413 | 12413 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 10D | Survey & Connection
07/26/2020 | 06:35 | 06:50 | 0.25 | 12413 | 12413 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 5A | Circulate
07/26/2020 | 06:50 | 16:45 | 9.92 | 12413 | 12413 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 6B | POOH
07/26/2020 | 16:45 | 17:30 | 0.75 | 12413 | 12413 | 0 | LAT | 3: BHA 3 (Curve-Lateral) | 6P | L/D BHA
07/26/2020 | 17:30 | 18:30 | 1 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 6O | P/U BHA
07/26/2020 | 18:30 | 24:00 | 5.5 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 6A | Tripping in the hole...(5407md @ midnight)
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_27_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/27/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 8250 |  |  | Well Cost($): |  | 79350
|  |  |  | 24hr Summary: |  | Drill lateral. Gamma failure
|  |  |  | 24hr Lookahead: |  | POOH to change out mwd
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12413 |  | 12413 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 12795 |  | 12795 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  | 382 |  | 382 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  | 28 |  | 28 | [5 empty] | 100: | 1 | Chlorides: | 250
Rotary Drilled (Usft): |  | 354 |  | 354 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  | 4.93 / 3.45 |  | 4.93 / 3.45 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 2.27 |  | 2.27 |  | SN: |  | 50597 |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: |  | 2.67 |  | 2.67 |  | Bit # |  | 3 |  | PH / Temp(F) | 1.4 / 135.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 132.75 / 12.35 |  | 132.75 / 12.35 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 29.5 |  | Grade In: |  | Green
% Slide: |  | 7.33 |  | 7.33 |  | Grade Out:
% Rotary: |  | 92.67 |  | 92.67 |  | Make / Model: |  | Baker Hughes / RPS613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Ulterra RPS 613 6x16s - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.85 |  | 0.85
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 4.875 | [5 empty] | 33.33 |  | 34.18
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.43
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 48.33
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.88
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.37
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 86.15
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 117.02
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.54
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.74
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.96
Agitator |  |  |  | 5.063 | 2.5 |  |  |  |  | 27.95 |  | 2744.91
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2748.22
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR500048 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12342 | 94.5 | 334.6 | 10467.8 | 655.82 | 416.37 | 1.16 |  | 21.74 | 433.27 | 1.08 |  | 0.43 | 93
12437 | 92.4 | 336.3 | 10462.08 | 742.07 | 376.98 | 2.84 |  | 141.01 | 528.07 | -2.21 |  | 1.79 | 95
12531 | 92.2 | 334.8 | 10458.31 | 827.57 | 338.1 | 1.61 |  | -97.57 | 621.99 | -0.21 |  | -1.6 | 94
12625 | 94 | 334.5 | 10453.23 | 912.39 | 297.92 | 1.94 |  | -9.44 | 715.81 | 1.91 |  | -0.32 | 94
12722 | 94.1 | 335.2 | 10446.38 | 999.97 | 256.8 | 0.73 |  | 81.83 | 812.53 | 0.1 |  | 0.72 | 97
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 77.48 | 30 | 70 | 335 | 390 | 4300 | 3600 | 104 | 320 | 185 | 0 | 16000 | 2000
Run | 77.48 | 30 | 70 | 335 | 390 | 4300 | 3600 | 104 | 320 | 185 | 0 | 16000 | 2000
Comments
POOH for MWD/Gamma
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/27/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/27/2020 |  | 4 |  | 100 |  | 4 | 400
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 07/27/2020 |  | 13 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 8250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/27/2020 | 00:00 | 01:50 | 1.83 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 6A | Trip in the hole.
07/27/2020 | 01:50 | 02:05 | 0.25 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 5A | Test MWD outside the shoe.
07/27/2020 | 02:05 | 02:40 | 0.58 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 6A | Trip in the hole pass the bottom of the curve. 11,383.
07/27/2020 | 02:40 | 02:50 | 0.17 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 5A | Test MWD.
07/27/2020 | 02:50 | 03:20 | 0.5 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 5A | Circulate
07/27/2020 | 03:20 | 03:40 | 0.33 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 6A | TIH to 12,322
07/27/2020 | 03:40 | 04:00 | 0.33 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 20B | Relog F/ 12,322 to 12,413
07/27/2020 | 04:00 | 04:05 | 0.08 | 12413 | 12413 | 0 | LAT | 4: BHA 4 Lateral | 10D | Survey taken at 12,342
07/27/2020 | 04:05 | 04:15 | 0.17 | 12413 | 12425 | 12 | LAT | 4: BHA 4 Lateral | 2K | Rotary Drill f/12413.00 t/12425.00, w/WOB 30.00,Flow 390.00, RPM 70.00, Press 4300.00, Tq 16000.00, ROP 72.00
07/27/2020 | 04:15 | 04:50 | 0.58 | 12425 | 12436 | 11 | LAT | 4: BHA 4 Lateral | 2J | Slide Drill f/12425.00 t/12436.00, TF , w/WOB 30.00,Flow 390.00, Press 4300.00, Tq 16000.00, ROP 18.86
07/27/2020 | 04:50 | 05:20 | 0.5 | 12436 | 12436 | 0 | LAT | 4: BHA 4 Lateral | 5A | Pumping kill mud down the backside.
07/27/2020 | 05:20 | 06:10 | 0.83 | 12436 | 12443 | 7 | LAT | 4: BHA 4 Lateral | 2J | Slide Drill f/12436.00 t/12443.00, TF , w/WOB 30.00,Flow 390.00, Press 4300.00, Tq 0, ROP 8.40
07/27/2020 | 06:10 | 06:35 | 0.42 | 12443 | 12510 | 67 | LAT | 4: BHA 4 Lateral | 2K | Rotary Drill f/12443.00 t/12510.00, w/WOB 30.00,Flow 390.00, RPM 70, Press 4300.00, Tq 16000.00, ROP 160.80
07/27/2020 | 06:35 | 06:40 | 0.08 | 12510 | 12510 | 0 | LAT | 4: BHA 4 Lateral | 10D | Survey & Connection
07/27/2020 | 06:40 | 07:18 | 0.63 | 12510 | 12604 | 94 | LAT | 4: BHA 4 Lateral | 2K | Rotary Drill f/12510.00 t/12604.00, w/WOB 30.00,Flow 390.00, RPM 70, Press 4300.00, Tq 16000.00, ROP 148.42
07/27/2020 | 07:18 | 07:30 | 0.2 | 12604 | 12604 | 0 | LAT | 4: BHA 4 Lateral | 5D | Pumping kill mud down the backside.
07/27/2020 | 07:30 | 08:15 | 0.75 | 12604 | 12698 | 94 | LAT | 4: BHA 4 Lateral | 2K | Rotary Drill f/12604.00 t/12698.00, w/WOB 30.00,Flow 390.00, RPM 70.00, Press 4300.00, Tq 16000.00, ROP 125.33
07/27/2020 | 08:15 | 08:20 | 0.08 | 12698 | 12698 | 0 | LAT | 4: BHA 4 Lateral | 10D | Survey & Connection
07/27/2020 | 08:20 | 08:31 | 0.18 | 12698 | 12715 | 17 | LAT | 4: BHA 4 Lateral | 2K | Rotary Drill f/12698.00 t/12715.00, w/WOB 30.00,Flow 390.00, RPM 70.00, Press 4300.00, Tq 16000.00, ROP 92.73
07/27/2020 | 08:31 | 09:22 | 0.85 | 12715 | 12725 | 10 | LAT | 4: BHA 4 Lateral | 2J | Slide Drill f/12715.00 t/12725.00, TF , w/WOB 30.00,Flow 390.00, Press 4300.00, Tq 16000.00, ROP 11.76
07/27/2020 | 09:22 | 09:53 | 0.52 | 12725 | 12795 | 70 | LAT | 4: BHA 4 Lateral | 2K | Rotary Drill f/12725.00 t/12795.00, w/WOB 30.00,Flow 390.00, RPM 70.00, Press 4300.00, Tq 16000.00, ROP 135.48
07/27/2020 | 09:53 | 10:19 | 0.43 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Relog 45
07/27/2020 | 10:19 | 11:23 | 1.07 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Circulate
07/27/2020 | 11:23 | 17:30 | 6.12 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6B | POOH
07/27/2020 | 17:30 | 19:10 | 1.67 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6L | Change out MWD.
07/27/2020 | 19:10 | 24:00 | 4.83 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_28_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/28/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 8250 |  |  | Well Cost($): |  | 87600
|  |  |  | 24hr Summary: |  | TIH, Slide, POOH
|  |  |  | 24hr Lookahead: |  | POOH, TIH Drill Lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12795 |  | 12413 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 12820 |  | 12820 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  | 25 |  | 407 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  | 25 |  | 53 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  |  |  | 354 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  | 0.42 / 6.22 |  | 5.35 / 9.67 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 0.42 |  | 2.68 |  | SN: |  | 50597 |  | 10s Gel: | 2 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  |  |  | 2.67 |  | Bit # |  | 3 |  | PH / Temp(F) | 8.4 / 201.00 | Fluid Loss / Mud Type: | 25 / WBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 60.00 |  | 132.75 / 19.75 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 53.5 |  | Grade In: |  | Green
% Slide: |  | 100 |  | 13.02 |  | Grade Out:
% Rotary: |  |  |  | 86.98 |  | Make / Model: |  | Baker Hughes / RPS613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Ulterra RPS 613 6x16s - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.85 |  | 0.85
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 4.875 | [5 empty] | 33.33 |  | 34.18
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.43
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 48.33
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.88
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.37
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 86.15
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 117.02
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.54
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.74
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.96
Agitator |  |  |  | 5.063 | 2.5 |  |  |  |  | 27.95 |  | 2744.91
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2748.22
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR500048 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30 | 70 | 335 | 390 | 4300 | 3600 | 104 | 320 | 185 | 0 | 16000 | 2000
Run | 77.48 | 30 | 70 | 335 | 390 | 4300 | 3600 | 104 | 320 | 185 | 0 | 16000 | 2000
Comments
POOH for MWD/Gamma
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/28/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/28/2020 |  | 4 |  | 100 |  | 4 | 400
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 07/28/2020 |  | 13 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 8250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/28/2020 | 00:00 | 00:50 | 0.83 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6A | TIH to 10,580 md
07/28/2020 | 00:50 | 01:05 | 0.25 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Test MWD outside the shoe.
07/28/2020 | 01:05 | 02:05 | 1 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6A | Trip in hole to 12704.
07/28/2020 | 02:05 | 02:55 | 0.83 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 20B | Relog F/ 12,704 to 12,795
07/28/2020 | 02:55 | 03:40 | 0.75 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Pumping kill mud on the back side to place the well on vacume.
07/28/2020 | 03:40 | 05:50 | 2.17 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Trouble shoot mwd....Cannot get a survey.
07/28/2020 | 05:50 | 07:00 | 1.17 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Circulate
07/28/2020 | 07:00 | 12:30 | 5.5 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6B | POOH
07/28/2020 | 12:30 | 12:45 | 0.25 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6L | Change MWD
07/28/2020 | 12:45 | 13:00 | 0.25 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 24A | Awaiting derrickman to get ready
07/28/2020 | 13:00 | 13:10 | 0.17 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Shallow test MWD
07/28/2020 | 13:10 | 14:20 | 1.17 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6A | TIH to 3016
07/28/2020 | 14:20 | 18:15 | 3.92 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 9A | Slip and cut drill line
07/28/2020 | 18:15 | 21:21 | 3.1 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6A | TIH to 10,519
07/28/2020 | 21:21 | 21:49 | 0.47 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Fill pipe and test MWD.
07/28/2020 | 21:49 | 22:50 | 1.02 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 6A | TIH to 12,795
07/28/2020 | 22:50 | 22:55 | 0.08 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 10D | Survey @ 12,722
07/28/2020 | 22:55 | 23:10 | 0.25 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 8D | Swap from #2 pump to #1 pump. #2 sucking air.
07/28/2020 | 23:10 | 23:35 | 0.42 | 12795 | 12795 | 0 | LAT | 4: BHA 4 Lateral | 5A | Sync up MWD.
07/28/2020 | 23:35 | 24:00 | 0.42 | 12795 | 12820 | 25 | LAT | 4: BHA 4 Lateral | 2J | Slide Drill f/12805.00 t/12820.00, TF 180.00, w/WOB 30.00,Flow 390.00, Press 4300.00, Tq 16000.00, ROP 36.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_29_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/29/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19250 |  |  | Well Cost($): |  | 106850
|  |  |  | 24hr Summary: |  | POOH. Inspect BHA. Change out motor & MWD. TIH and drill lateral
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12820 |  | 12820 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 13032 |  | 13032 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  | 212 |  | 212 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  | 34 |  | 34 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  | 178 |  | 178 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  | 3.42 / 0.87 |  | 3.42 / 0.87 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 1.45 |  | 1.45 |  | SN: |  | 50597 |  | 10s Gel: | 2 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 1.97 |  | 1.97 |  | Bit # |  | 3 |  | PH / Temp(F) | 8.4 / 201.00 | Fluid Loss / Mud Type: | 25 / WBM
ROP Rot/Slide (Usft/hr): |  | 90.51 / 23.45 |  | 90.51 / 23.45 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 14.72 |  | 14.72 |  | Grade In: |  | Green
% Slide: |  | 16.04 |  | 16.04 |  | Grade Out:
% Rotary: |  | 83.96 |  | 83.96 |  | Make / Model: |  | Baker Hughes / RPS613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Ulterra RPS 613 6x16s - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.85 |  | 0.85
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 4.875 | [5 empty] | 33.33 |  | 34.18
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.43
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 48.33
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.88
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.37
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 86.15
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 117.02
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.54
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.74
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.96
Agitator |  |  |  | 5.063 | 2.5 |  |  |  |  | 27.95 |  | 2744.91
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2748.22
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR500048 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12818 | 89.9 | 335.2 | 10443.03 | 1087.05 | 216.56 | 4.37 |  | 180 | 908.43 | -4.37 |  | 0 | 96
12914 | 87.8 | 334.3 | 10444.96 | 1173.85 | 175.62 | 2.38 |  | -156.81 | 1004.37 | -2.19 |  | -0.94 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30 | 70 | 335 | 390 | 4300 | 3600 | 104 | 320 | 185 | 0 | 16000 | 2000
Run | 76.07 | 30 | 70 | 335 | 390 | 4300 | 3600 | 104 | 320 | 185 | 0 | 16000 | 2000
Comments
POOH for possible drill string obstruction.
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/29/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/29/2020 |  | 4 |  | 100 |  | 4 | 400
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 07/29/2020 |  | 6 |  | 1500 |  | 1 | 1500
5 Premium Motor Stator Reline |  |  |  |  | 07/29/2020 |  | 9 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 19250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/29/2020 | 00:00 | 00:35 | 0.58 | 12820 | 12820 | 0 | LAT | 4: BHA 4 Lateral | 24A | After slide. Drilled off. Pick up off bottom and the drill string pressured up. Killed the pumps. Bled off pressure. verified we were free. Worked drill string up and down. Brought the pump up and pressured up once more.
07/29/2020 | 00:35 | 01:17 | 0.7 | 12820 | 12820 | 0 | LAT | 4: BHA 4 Lateral | 5A | Pulled 10 stands and brought pump up and pressured up to 4100 psi immediately.
07/29/2020 | 01:17 | 07:45 | 6.47 | 12820 | 12820 | 0 | LAT | 4: BHA 4 Lateral | 6B | POOH for drill string obstruction...
07/29/2020 | 07:45 | 08:30 | 0.75 | 12820 | 12820 | 0 | LAT | 4: BHA 4 Lateral | 6P | L/D BHA
07/29/2020 | 08:30 | 09:17 | 0.78 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 6O | P/U BHA
07/29/2020 | 09:17 | 10:30 | 1.22 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 8D | Clean mud pumps
07/29/2020 | 10:30 | 10:47 | 0.28 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Shallow test MWD, No bit
07/29/2020 | 10:47 | 18:30 | 7.72 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 6A | TIH to 10,293
07/29/2020 | 18:30 | 18:45 | 0.25 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Test MWD outside the shoe.
07/29/2020 | 18:45 | 20:05 | 1.33 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 6A | TIH to 12,795
07/29/2020 | 20:05 | 20:15 | 0.17 | 12820 | 12820 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Sync up mwd and wash and ream to bottom @ 40rpms.
07/29/2020 | 20:15 | 20:58 | 0.72 | 12820 | 12891 | 71 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12820.00 t/12891.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 99.07
07/29/2020 | 20:58 | 21:03 | 0.08 | 12891 | 12891 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/29/2020 | 21:03 | 21:20 | 0.28 | 12891 | 12929 | 38 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12891.00 t/12929.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 134.12
07/29/2020 | 21:20 | 22:00 | 0.67 | 12929 | 12950 | 21 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12929.00 t/12950.00, TF 0.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 14.50, ROP 31.50
07/29/2020 | 22:00 | 22:25 | 0.42 | 12950 | 12987 | 37 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12950.00 t/12987.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 88.80
07/29/2020 | 22:25 | 22:30 | 0.08 | 12987 | 12987 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/29/2020 | 22:30 | 23:17 | 0.78 | 12987 | 13000 | 13 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12987.00 t/13000.00, TF 0.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 14.50, ROP 16.60
07/29/2020 | 23:17 | 23:40 | 0.38 | 13000 | 13016 | 16 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13000.00 t/13016.00, w/WOB 32000.00,Flow 338.00, RPM 0.00, Press 3800.00, Tq 14.50, ROP 41.74
07/29/2020 | 23:40 | 23:50 | 0.17 | 13016 | 13016 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Survey & Connection
07/29/2020 | 23:50 | 24:00 | 0.17 | 13016 | 13032 | 16 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13016.00 t/13032.00, w/WOB 32000.00,Flow 338.00, RPM 0.00, Press 3800.00, Tq 14.50, ROP 96.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_30_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/30/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 114100
|  |  |  | 24hr Summary: |  | Drilling lateral
|  |  |  | 24hr Lookahead: |  | Drilling lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13032 |  | 12820 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 14659 |  | 14659 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  | 1627 |  | 1839 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  | 86 |  | 120 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  | 1541 |  | 1719 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  | 20.35 / 1.00 |  | 23.77 / 1.87 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 3.9 |  | 5.35 |  | SN: |  | 1138553 |  | 10s Gel: | 2 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 16.45 |  | 18.42 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.4 / 201.00 | Fluid Loss / Mud Type: | 25 / WBM
ROP Rot/Slide (Usft/hr): |  | 93.68 / 22.05 |  | 93.34 / 22.43 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 38.72 |  | Grade In: |  | Green
% Slide: |  | 5.29 |  | 6.53 |  | Grade Out: |  | 02
% Rotary: |  | 94.71 |  | 93.47 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Halliburton GTD64M (Jetted 6x16s) - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.74 |  | 0.74
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | 2.563 |  |  |  |  | 33.1 |  | 33.84
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.09
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 47.99
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.54
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.03
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 85.81
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 116.68
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.2
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.4
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.62
Agitator |  |  |  | 5.188 | 2.813 |  |  |  |  | 27.99 |  | 2744.61
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2747.92
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250009 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13009 | 92.3 | 334.8 | 10444.87 | 1259.61 | 134.81 | 4.77 |  | 6.34 | 1099.3 | 4.74 |  | 0.53 | 95
13104 | 94.8 | 336.8 | 10438.99 | 1346.08 | 95.94 | 3.37 |  | 38.55 | 1194.1 | 2.63 |  | 2.11 | 95
13199 | 95.4 | 336.2 | 10430.54 | 1432.86 | 58.21 | 0.89 |  | -44.86 | 1288.73 | 0.63 |  | -0.63 | 95
13294 | 94.9 | 336.4 | 10422.02 | 1519.5 | 20.18 | 0.57 |  | 158.27 | 1383.34 | -0.53 |  | 0.21 | 95
13390 | 95.3 | 335.8 | 10413.48 | 1606.92 | -18.56 | 0.75 |  | -56.18 | 1478.96 | 0.42 |  | -0.62 | 96
13485 | 95.6 | 335.2 | 10404.46 | 1692.97 | -57.77 | 0.7 |  | -63.3 | 1573.52 | 0.32 |  | -0.63 | 95
13580 | 96.4 | 334.9 | 10394.53 | 1778.63 | -97.63 | 0.9 |  | -20.44 | 1667.98 | 0.84 |  | -0.32 | 95
13676 | 95.3 | 335.2 | 10384.75 | 1865.22 | -137.91 | 1.19 |  | 164.81 | 1763.45 | -1.15 |  | 0.31 | 96
13771 | 96.6 | 335 | 10374.9 | 1950.92 | -177.69 | 1.38 |  | -8.69 | 1857.92 | 1.37 |  | -0.21 | 95
13866 | 92.7 | 336.8 | 10367.2 | 2037.34 | -216.34 | 4.52 |  | 155.22 | 1952.58 | -4.11 |  | 1.89 | 95
13961 | 92.2 | 336.5 | 10363.14 | 2124.48 | -253.96 | 0.61 |  | -149.05 | 2047.49 | -0.53 |  | -0.32 | 95
14055 | 92.3 | 336.7 | 10359.45 | 2210.68 | -291.26 | 0.24 |  | 63.41 | 2141.42 | 0.11 |  | 0.21 | 94
14150 | 92.8 | 335.7 | 10355.22 | 2297.51 | -329.56 | 1.18 |  | -63.39 | 2236.32 | 0.53 |  | -1.05 | 95
14245 | 91.5 | 335.9 | 10351.66 | 2384.1 | -368.48 | 1.38 |  | 171.26 | 2331.25 | -1.37 |  | 0.21 | 95
14340 | 91.7 | 335.5 | 10349 | 2470.65 | -407.56 | 0.47 |  | -63.42 | 2426.21 | 0.21 |  | -0.42 | 95
14435 | 91.9 | 335 | 10346.02 | 2556.88 | -447.31 | 0.57 |  | -68.18 | 2521.14 | 0.21 |  | -0.53 | 95
14530 | 94.2 | 335.9 | 10340.96 | 2643.16 | -486.72 | 2.6 |  | 21.32 | 2615.99 | 2.42 |  | 0.95 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 76.43 | 32000 | 70 | 300 | 338 | 3800 | 3150 | 104 | 310 | 225 | 165 | 6436.86 | 2000
Run | 73.65 | 32000 | 70 | 300 | 338 | 3800 | 3150 | 104 | 310 | 225 | 165 | 4746.76 | 2000
Comments
Control drilling
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/30/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/30/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/30/2020 | 00:00 | 00:10 | 0.17 | 13032 | 13032 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | & 334.3?
07/30/2020 | 00:10 | 00:45 | 0.58 | 13032 | 13048 | 16 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13032.00 t/13048.00, TF 0.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 14.50, ROP 27.43
07/30/2020 | 00:45 | 01:09 | 0.4 | 13048 | 13082 | 34 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13048.00 t/13082.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 14.50, ROP 85.00
07/30/2020 | 01:09 | 01:14 | 0.08 | 13082 | 13082 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 01:14 | 02:14 | 1 | 13082 | 13177 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13082.00 t/13177.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 14.50, ROP 95.00
07/30/2020 | 02:14 | 02:19 | 0.08 | 13177 | 13177 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 02:19 | 03:15 | 0.93 | 13177 | 13272 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13177.00 t/13272.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 14.50, ROP 101.79
07/30/2020 | 03:15 | 03:20 | 0.08 | 13272 | 13272 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 03:20 | 03:30 | 0.17 | 13272 | 13278 | 6 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13272.00 t/13278.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 14.50, ROP 36.00
07/30/2020 | 03:30 | 03:43 | 0.22 | 13278 | 13284 | 6 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13278.00 t/13284.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 14.50, ROP 27.69
07/30/2020 | 03:43 | 04:28 | 0.75 | 13284 | 13367 | 83 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13284.00 t/13367.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 110.67
07/30/2020 | 04:28 | 04:33 | 0.08 | 13367 | 13367 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 04:33 | 05:35 | 1.03 | 13367 | 13463 | 96 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13367.00 t/13463.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 92.90
07/30/2020 | 05:35 | 05:40 | 0.08 | 13463 | 13463 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 05:40 | 07:06 | 1.43 | 13463 | 13558 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13463.00 t/13558.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 66.28
07/30/2020 | 07:06 | 07:12 | 0.1 | 13558 | 13558 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 07:12 | 08:37 | 1.42 | 13558 | 13635 | 77 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13558.00 t/13635.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 14.50, ROP 54.35
07/30/2020 | 08:37 | 09:10 | 0.55 | 13635 | 13645 | 10 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13635.00 t/13645.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 18.18
07/30/2020 | 09:10 | 10:00 | 0.83 | 13645 | 13645 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Survey & Connection
07/30/2020 | 10:00 | 10:16 | 0.27 | 13645 | 13653 | 8 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13645.00 t/13653.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 15000, ROP 30.00
07/30/2020 | 10:16 | 10:21 | 0.08 | 13653 | 13653 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 10:21 | 11:17 | 0.93 | 13653 | 13749 | 96 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13653.00 t/13749.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 15000, ROP 102.86
07/30/2020 | 11:17 | 11:22 | 0.08 | 13749 | 13749 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 11:22 | 11:44 | 0.37 | 13749 | 13790 | 41 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13749.00 t/13790.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 15000, ROP 111.82
07/30/2020 | 11:44 | 12:37 | 0.88 | 13790 | 13807 | 17 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13790.00 t/13807.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 19.25
07/30/2020 | 12:37 | 12:58 | 0.35 | 13807 | 13844 | 37 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13807.00 t/13844.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 15000, ROP 105.71
07/30/2020 | 12:58 | 13:03 | 0.08 | 13844 | 13844 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 13:03 | 13:12 | 0.15 | 13844 | 13859 | 15 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13844.00 t/13859.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 15000, ROP 100.00
07/30/2020 | 13:12 | 13:48 | 0.6 | 13859 | 13871 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13859.00 t/13871.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 20.00
07/30/2020 | 13:48 | 14:20 | 0.53 | 13871 | 13939 | 68 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13871.00 t/13939.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 3800.00, Tq 15000, ROP 127.50
07/30/2020 | 14:20 | 14:35 | 0.25 | 13939 | 13939 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 14:35 | 15:25 | 0.83 | 13939 | 14034 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13939.00 t/14034.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 114.00
07/30/2020 | 15:25 | 15:45 | 0.33 | 14034 | 14034 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 15:45 | 16:42 | 0.95 | 14034 | 14128 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14034.00 t/14128.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 98.95
07/30/2020 | 16:42 | 17:35 | 0.88 | 14128 | 14128 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 17:35 | 18:21 | 0.77 | 14128 | 14223 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14128.00 t/14223.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 123.91
07/30/2020 | 18:21 | 18:26 | 0.08 | 14223 | 14223 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 18:26 | 18:45 | 0.32 | 14223 | 14230 | 7 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14223.00 t/14230.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 22.11
07/30/2020 | 18:45 | 19:10 | 0.42 | 14230 | 14237 | 7 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14230.00 t/14237.00, TF 145.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 15000.00, ROP 16.80
07/30/2020 | 19:10 | 19:50 | 0.67 | 14237 | 14318 | 81 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14237.00 t/14318.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 121.50
07/30/2020 | 19:50 | 19:55 | 0.08 | 14318 | 14318 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 19:55 | 20:48 | 0.88 | 14318 | 14413 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14318.00 t/14413.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 107.55
07/30/2020 | 20:48 | 20:53 | 0.08 | 14413 | 14413 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 20:53 | 21:20 | 0.45 | 14413 | 14453 | 40 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14413.00 t/14453.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 88.89
07/30/2020 | 21:20 | 21:49 | 0.48 | 14453 | 14465 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14453.00 t/14465.00, TF 45.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 15000.00, ROP 24.83
07/30/2020 | 21:49 | 22:15 | 0.43 | 14465 | 14508 | 43 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14465.00 t/14508.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 99.23
07/30/2020 | 22:15 | 22:20 | 0.08 | 14508 | 14508 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 22:20 | 23:20 | 1 | 14508 | 14603 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14508.00 t/14603.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 95.00
07/30/2020 | 23:20 | 23:25 | 0.08 | 14603 | 14603 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/30/2020 | 23:25 | 23:50 | 0.42 | 14603 | 14653 | 50 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14603.00 t/14653.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 120.00
07/30/2020 | 23:50 | 24:00 | 0.17 | 14653 | 14659 | 6 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14653.00 t/14659.00, TF 180.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 15000.00, ROP 36.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_31_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/31/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 121350
|  |  |  | 24hr Summary: |  | Drill lateral
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14659 |  | 12820 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 16212 |  | 16212 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  | 1553 |  | 3392 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  | 122 |  | 242 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  | 1431 |  | 3150 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  | 20.25 / 0.32 |  | 44.02 / 2.18 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 7.18 |  | 12.53 |  | SN: |  | 1138553 |  | 10s Gel: | 2 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 13.07 |  | 31.48 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.4 / 169.00 | Fluid Loss / Mud Type: | 25 / WBM
ROP Rot/Slide (Usft/hr): |  | 109.52 / 16.98 |  | 100.05 / 19.31 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 62.72 |  | Grade In: |  | Green
% Slide: |  | 7.86 |  | 7.13 |  | Grade Out: |  | 02
% Rotary: |  | 92.14 |  | 92.87 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Halliburton GTD64M (Jetted 6x16s) - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.74 |  | 0.74
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | 2.563 |  |  |  |  | 33.1 |  | 33.84
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.09
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 47.99
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.54
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.03
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 85.81
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 116.68
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.2
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.4
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.62
Agitator |  |  |  | 5.188 | 2.813 |  |  |  |  | 27.99 |  | 2744.61
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2747.92
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250009 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14624 | 95.5 | 335.7 | 10333.02 | 2728.6 | -525.12 | 1.4 |  | -8.71 | 2709.65 | 1.38 |  | -0.21 | 94
14719 | 94.4 | 336 | 10324.82 | 2814.96 | -563.84 | 1.2 |  | 164.79 | 2804.29 | -1.16 |  | 0.32 | 95
14815 | 95.3 | 335.9 | 10316.7 | 2902.31 | -602.82 | 0.94 |  | -6.31 | 2899.94 | 0.94 |  | -0.1 | 96
14910 | 94.8 | 336.5 | 10308.34 | 2988.89 | -641.01 | 0.82 |  | 129.89 | 2994.57 | -0.53 |  | 0.63 | 95
15005 | 93.6 | 336.9 | 10301.38 | 3075.91 | -678.48 | 1.33 |  | 161.6 | 3089.31 | -1.26 |  | 0.42 | 95
15100 | 88.9 | 335.4 | 10299.31 | 3162.75 | -716.87 | 5.19 |  | -162.28 | 3184.26 | -4.95 |  | -1.58 | 95
15194 | 87.3 | 335.3 | 10302.43 | 3248.13 | -756.06 | 1.71 |  | -176.43 | 3278.19 | -1.7 |  | -0.11 | 94
15289 | 89.5 | 336.3 | 10305.08 | 3334.74 | -794.98 | 2.54 |  | 24.45 | 3373.15 | 2.32 |  | 1.05 | 95
15383 | 91.7 | 338.1 | 10304.1 | 3421.38 | -831.4 | 3.02 |  | 39.28 | 3467.12 | 2.34 |  | 1.91 | 94
15478 | 92.2 | 337.2 | 10300.86 | 3509.2 | -867.51 | 1.08 |  | -60.92 | 3562.04 | 0.53 |  | -0.95 | 95
15572 | 92.8 | 336.5 | 10296.76 | 3595.54 | -904.42 | 0.98 |  | -49.36 | 3655.94 | 0.64 |  | -0.74 | 94
15667 | 91.5 | 337.4 | 10293.2 | 3682.89 | -941.59 | 1.66 |  | 145.31 | 3750.87 | -1.37 |  | 0.95 | 95
15761 | 91 | 336.8 | 10291.15 | 3769.46 | -978.16 | 0.83 |  | -129.81 | 3844.84 | -0.53 |  | -0.64 | 94
15855 | 90.9 | 336.3 | 10289.59 | 3855.69 | -1015.56 | 0.54 |  | -101.31 | 3938.82 | -0.11 |  | -0.53 | 94
15950 | 93.2 | 335.2 | 10286.19 | 3942.24 | -1054.55 | 2.68 |  | -25.53 | 4033.75 | 2.42 |  | -1.16 | 95
16044 | 94.9 | 334.9 | 10279.55 | 4027.26 | -1094.1 | 1.84 |  | -9.97 | 4127.49 | 1.81 |  | -0.32 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 76.65 | 32000 | 70 | 300 | 338 | 3800 | 3150 | 104 | 310 | 225 | 165 | 15000 | 2000
Run | 77.04 | 32000 | 70 | 300 | 338 | 3800 | 3150 | 104 | 310 | 225 | 165 | 9433.96 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 07/31/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 07/31/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/31/2020 | 00:00 | 00:37 | 0.62 | 14659 | 14697 | 38 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14659.00 t/14697.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 61.62
07/31/2020 | 00:37 | 00:42 | 0.08 | 14697 | 14697 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 00:42 | 01:28 | 0.77 | 14697 | 14792 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14697.00 t/14792.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 123.91
07/31/2020 | 01:28 | 01:32 | 0.07 | 14792 | 14792 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 01:32 | 02:00 | 0.47 | 14792 | 14820 | 28 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14792.00 t/14820.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 60.00
07/31/2020 | 02:00 | 02:14 | 0.23 | 14820 | 14826 | 6 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14820.00 t/14826.00, TF 145.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 15000.00, ROP 25.71
07/31/2020 | 02:14 | 02:43 | 0.48 | 14826 | 14888 | 62 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14826.00 t/14888.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 128.28
07/31/2020 | 02:43 | 02:48 | 0.08 | 14888 | 14888 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 02:48 | 03:40 | 0.87 | 14888 | 14983 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14888.00 t/14983.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 109.62
07/31/2020 | 03:40 | 03:45 | 0.08 | 14983 | 14983 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 03:45 | 05:16 | 1.52 | 14983 | 14998 | 15 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14983.00 t/14998.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 15000.00, ROP 9.89
07/31/2020 | 05:16 | 06:04 | 0.8 | 14998 | 15078 | 80 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14998.00 t/15078.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 100.00
07/31/2020 | 06:04 | 06:25 | 0.35 | 15078 | 15078 | 0 | LAT | 5: BHA 5 (Lateral) | 23E | Wait on instructions
07/31/2020 | 06:25 | 06:35 | 0.17 | 15078 | 15078 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 06:35 | 08:02 | 1.45 | 15078 | 15110 | 32 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15078.00 t/15110.00, TF 180.00, w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 22.07
07/31/2020 | 08:02 | 08:30 | 0.47 | 15110 | 15173 | 63 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15110.00 t/15173.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 135.00
07/31/2020 | 08:30 | 09:05 | 0.58 | 15173 | 15173 | 0 | LAT | 5: BHA 5 (Lateral) | 23E | Wait on instructions
07/31/2020 | 09:05 | 09:53 | 0.8 | 15173 | 15267 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15173.00 t/15267.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 117.50
07/31/2020 | 09:53 | 10:00 | 0.12 | 15267 | 15267 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 10:00 | 11:30 | 1.5 | 15267 | 15294 | 27 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15267.00 t/15294.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 18.00
07/31/2020 | 11:30 | 12:06 | 0.6 | 15294 | 15362 | 68 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15294.00 t/15362.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 113.33
07/31/2020 | 12:06 | 12:20 | 0.23 | 15362 | 15362 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 12:20 | 13:05 | 0.75 | 15362 | 15374 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15362.00 t/15374.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 16.00
07/31/2020 | 13:05 | 13:45 | 0.67 | 15374 | 15456 | 82 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15374.00 t/15456.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 123.00
07/31/2020 | 13:45 | 13:55 | 0.17 | 15456 | 15456 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 13:55 | 14:35 | 0.67 | 15456 | 15557 | 101 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15456.00 t/15557.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 151.50
07/31/2020 | 14:35 | 14:45 | 0.17 | 15557 | 15557 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 14:45 | 15:18 | 0.55 | 15557 | 15645 | 88 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15557.00 t/15645.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 160.00
07/31/2020 | 15:18 | 15:30 | 0.2 | 15645 | 15645 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 15:30 | 16:14 | 0.73 | 15645 | 15657 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15645.00 t/15657.00, TF , w/WOB 32000.00,Flow 338.00, Press 3800.00, Tq 0, ROP 16.36
07/31/2020 | 16:14 | 16:52 | 0.63 | 15657 | 15740 | 83 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15657.00 t/15740.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 131.05
07/31/2020 | 16:52 | 16:57 | 0.08 | 15740 | 15740 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 16:57 | 17:40 | 0.72 | 15740 | 15740 | 0 | LAT | 5: BHA 5 (Lateral) | 8P | Rig Service
07/31/2020 | 17:40 | 18:33 | 0.88 | 15740 | 15834 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15740.00 t/15834.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 3800.00, Tq 15000.00, ROP 106.42
07/31/2020 | 18:33 | 18:38 | 0.08 | 15834 | 15834 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 18:38 | 19:05 | 0.45 | 15834 | 15890 | 56 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15834.00 t/15890.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 124.44
07/31/2020 | 19:05 | 19:47 | 0.7 | 15890 | 15902 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15890.00 t/15902.00, TF 25.00, w/WOB 32000.00,Flow 338.00, Press 4700.00, Tq 15000.00, ROP 17.14
07/31/2020 | 19:47 | 20:04 | 0.28 | 15902 | 15928 | 26 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15902.00 t/15928.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 91.76
07/31/2020 | 20:04 | 20:09 | 0.08 | 15928 | 15928 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 20:09 | 20:38 | 0.48 | 15928 | 15988 | 60 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15928.00 t/15988.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 124.14
07/31/2020 | 20:38 | 20:56 | 0.3 | 15988 | 15994 | 6 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15988.00 t/15994.00, TF , w/WOB 32000.00,Flow 338.00, Press 4700.00, Tq 15000.00, ROP 20.00
07/31/2020 | 20:56 | 21:14 | 0.3 | 15994 | 16023 | 29 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15994.00 t/16023.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 96.67
07/31/2020 | 21:14 | 21:19 | 0.08 | 16023 | 16023 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 21:19 | 22:05 | 0.77 | 16023 | 16117 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16023.00 t/16117.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 122.61
07/31/2020 | 22:05 | 22:10 | 0.08 | 16117 | 16117 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
07/31/2020 | 22:10 | 22:15 | 0.08 | 16117 | 16123 | 6 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16117.00 t/16123.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 72.00
07/31/2020 | 22:15 | 23:10 | 0.92 | 16123 | 16139 | 16 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16123.00 t/16139.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 17.45
07/31/2020 | 23:10 | 23:41 | 0.52 | 16139 | 16212 | 73 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16139.00 t/16212.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 141.29
07/31/2020 | 23:41 | 24:00 | 0.32 | 16212 | 16212 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulating: Lost 1400lbs of pump pressure.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_1_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/01/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 128600
|  |  |  | 24hr Summary: |  | Drill Lateral
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16212 |  | 12820 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 17841 |  | 17841 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  | 1629 |  | 5021 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  | 116 |  | 358 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  | 1513 |  | 4663 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  | 15.98 / 2.33 |  | 60.00 / 4.52 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 4.58 |  | 17.12 |  | SN: |  | 1138553 |  | 10s Gel: | 2 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 11.4 |  | 42.88 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.4 / 169.00 | Fluid Loss / Mud Type: | 25 / WBM
ROP Rot/Slide (Usft/hr): |  | 132.72 / 25.31 |  | 108.74 / 20.92 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 86.72 |  | Grade In: |  | Green
% Slide: |  | 7.12 |  | 7.13 |  | Grade Out: |  | 02
% Rotary: |  | 92.88 |  | 92.87 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Halliburton GTD64M (Jetted 6x16s) - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.74 |  | 0.74
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | 2.563 |  |  |  |  | 33.1 |  | 33.84
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.09
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 47.99
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.54
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.03
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 85.81
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 116.68
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.2
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.4
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.62
Agitator |  |  |  | 5.188 | 2.813 |  |  |  |  | 27.99 |  | 2744.61
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2747.92
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250009 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16139 | 94.3 | 336.3 | 10271.93 | 4113.49 | -1133.22 | 1.6 |  | 113.21 | 4222.17 | -0.63 |  | 1.47 | 95
16234 | 92 | 336.6 | 10266.71 | 4200.44 | -1171.12 | 2.44 |  | 172.57 | 4317.02 | -2.42 |  | 0.32 | 95
16329 | 89 | 337.2 | 10265.88 | 4287.81 | -1208.38 | 3.22 |  | 168.69 | 4412 | -3.16 |  | 0.63 | 95
16423 | 90.9 | 337.7 | 10265.97 | 4374.62 | -1244.43 | 2.09 |  | 14.74 | 4505.98 | 2.02 |  | 0.53 | 94
16520 | 92 | 337.3 | 10263.51 | 4464.2 | -1281.54 | 1.21 |  | -19.97 | 4602.92 | 1.13 |  | -0.41 | 97
16614 | 92.7 | 337.3 | 10259.66 | 4550.85 | -1317.78 | 0.74 |  | 0 | 4696.83 | 0.74 |  | 0 | 94
16709 | 94 | 337 | 10254.11 | 4638.24 | -1354.61 | 1.4 |  | -12.96 | 4791.66 | 1.37 |  | -0.32 | 95
16803 | 95.4 | 336.8 | 10246.4 | 4724.41 | -1391.36 | 1.5 |  | -8.1 | 4885.33 | 1.49 |  | -0.21 | 94
16899 | 93 | 337.6 | 10239.37 | 4812.67 | -1428.46 | 2.63 |  | 161.58 | 4981.06 | -2.5 |  | 0.83 | 96
16993 | 93.9 | 337.8 | 10233.72 | 4899.48 | -1464.06 | 0.98 |  | 12.5 | 5074.86 | 0.96 |  | 0.21 | 94
17087 | 95.1 | 337.9 | 10226.34 | 4986.27 | -1499.4 | 1.28 |  | 4.75 | 5168.53 | 1.28 |  | 0.11 | 94
17181 | 92.8 | 337.4 | 10219.87 | 5073 | -1535.05 | 2.5 |  | -167.75 | 5262.28 | -2.45 |  | -0.53 | 94
17276 | 93 | 339.2 | 10215.06 | 5161.15 | -1570.13 | 1.9 |  | 83.61 | 5357.09 | 0.21 |  | 1.89 | 95
17370 | 90.4 | 337.2 | 10212.27 | 5248.37 | -1605.02 | 3.49 |  | -142.41 | 5450.99 | -2.77 |  | -2.13 | 94
17464 | 90.6 | 336 | 10211.45 | 5334.64 | -1642.35 | 1.29 |  | -80.53 | 5544.98 | 0.21 |  | -1.28 | 94
17558 | 90.9 | 335.8 | 10210.22 | 5420.44 | -1680.73 | 0.38 |  | -33.69 | 5638.97 | 0.32 |  | -0.21 | 94
17653 | 91.3 | 335.6 | 10208.4 | 5507 | -1719.82 | 0.47 |  | -26.56 | 5733.95 | 0.42 |  | -0.21 | 95
17747 | 92 | 336 | 10205.69 | 5592.71 | -1758.34 | 0.86 |  | 29.73 | 5827.9 | 0.74 |  | 0.43 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 102 | 32000 | 70 | 300 | 338 | 4000 | 3300 | 104 | 330 | 225 | 165 | 15000 | 2000
Run | 83.68 | 32000 | 70 | 300 | 338 | 3870.33 | 3202.75 | 104 | 317.03 | 225 | 165 | 12048.31 | 2000
Comments
@ 16212 md, lost 1400lbs of pump pressure.
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 08/01/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 08/01/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/01/2020 | 00:00 | 01:00 | 1 | 16212 | 16212 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Lost 1400lbs of pump pressure
08/01/2020 | 01:00 | 01:05 | 0.08 | 16212 | 16212 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Connection & Survey
08/01/2020 | 01:05 | 02:04 | 0.98 | 16212 | 16238 | 26 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16212.00 t/16238.00, TF 145.00, w/WOB 32000.00,Flow 338.00, Press 4700.00, Tq 15000.00, ROP 26.44
08/01/2020 | 02:04 | 02:50 | 0.77 | 16238 | 16307 | 69 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16238.00 t/16307.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 4700.00, Tq 15000.00, ROP 90.00
08/01/2020 | 02:50 | 02:55 | 0.08 | 16307 | 16307 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 02:55 | 03:29 | 0.57 | 16307 | 16327 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16307.00 t/16327.00, TF , w/WOB 32000.00,Flow 338.00, Press 4700.00, Tq 15000.00, ROP 35.29
08/01/2020 | 03:29 | 04:13 | 0.73 | 16327 | 16402 | 75 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16327.00 t/16402.00, w/WOB 32000.00,Flow 338.00, RPM 70, Press 4700.00, Tq 15000.00, ROP 102.27
08/01/2020 | 04:13 | 05:00 | 0.78 | 16402 | 16427 | 25 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16402.00 t/16427.00, TF , w/WOB 32000.00,Flow 338.00, Press 4700.00, Tq 15000.00, ROP 31.91
08/01/2020 | 05:00 | 05:33 | 0.55 | 16427 | 16432 | 5 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16402.00 t/16432.00, TF 0.00, w/WOB 32000.00,Flow 338.00, Press 4700.00, Tq 0, ROP 54.55
08/01/2020 | 05:33 | 06:02 | 0.48 | 16432 | 16496 | 64 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16432.00 t/16496.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 132.41
08/01/2020 | 06:02 | 06:10 | 0.13 | 16496 | 16496 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 06:10 | 06:43 | 0.55 | 16496 | 16593 | 97 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16496.00 t/16593.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 176.36
08/01/2020 | 06:43 | 06:49 | 0.1 | 16593 | 16593 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 06:49 | 07:25 | 0.6 | 16593 | 16687 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16593.00 t/16687.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 156.67
08/01/2020 | 07:25 | 07:30 | 0.08 | 16687 | 16687 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 07:30 | 08:02 | 0.53 | 16687 | 16782 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16687.00 t/16782.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 178.13
08/01/2020 | 08:02 | 08:09 | 0.12 | 16782 | 16782 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 08:09 | 08:36 | 0.45 | 16782 | 16845 | 63 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16782.00 t/16845.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 140.00
08/01/2020 | 08:36 | 09:40 | 1.07 | 16845 | 16876 | 31 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16865.00 t/16876.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 10.31
08/01/2020 | 09:40 | 09:45 | 0.08 | 16876 | 16876 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 09:45 | 10:18 | 0.55 | 16876 | 16972 | 96 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16876.00 t/16972.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4700.00, Tq 15000.00, ROP 174.55
08/01/2020 | 10:18 | 10:24 | 0.1 | 16972 | 16972 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 10:24 | 11:05 | 0.68 | 16972 | 17066 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16972.00 t/17066.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 137.56
08/01/2020 | 11:05 | 11:10 | 0.08 | 17066 | 17066 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 11:10 | 11:57 | 0.78 | 17066 | 17161 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17066.00 t/17161.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 121.28
08/01/2020 | 11:57 | 12:13 | 0.27 | 17161 | 17161 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 12:13 | 13:05 | 0.87 | 17161 | 17181 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/17161.00 t/17181.00, TF 180.00, w/WOB 32000.00,Flow 338.00, Press 4000, Tq 0.00, ROP 23.08
08/01/2020 | 13:05 | 13:37 | 0.53 | 17181 | 17254 | 73 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17181.00 t/17254.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 136.88
08/01/2020 | 13:37 | 13:44 | 0.12 | 17254 | 17254 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 13:44 | 14:20 | 0.6 | 17254 | 17349 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17254.00 t/17349.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 158.33
08/01/2020 | 14:20 | 14:27 | 0.12 | 17349 | 17349 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 14:27 | 14:32 | 0.08 | 17349 | 17355 | 6 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17349.00 t/17355.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 72.00
08/01/2020 | 14:32 | 15:22 | 0.83 | 17355 | 17375 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/17355.00 t/17375.00, TF 0.00, w/WOB 32000.00,Flow 338.00, Press 4000, Tq 0, ROP 24.00
08/01/2020 | 15:22 | 15:55 | 0.55 | 17375 | 17443 | 68 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17375.00 t/17443.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 123.64
08/01/2020 | 15:55 | 16:00 | 0.08 | 17443 | 17443 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 16:00 | 16:40 | 0.67 | 17443 | 17537 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17443.00 t/17537.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000, Tq 15000.00, ROP 141.00
08/01/2020 | 16:40 | 17:18 | 0.63 | 17537 | 17537 | 0 | LAT | 5: BHA 5 (Lateral) | 8P | Rig service
08/01/2020 | 17:18 | 17:24 | 0.1 | 17537 | 17537 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 17:24 | 17:55 | 0.52 | 17537 | 17631 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17537.00 t/17631.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000.00, Tq 15000.00, ROP 181.94
08/01/2020 | 17:55 | 18:00 | 0.08 | 17631 | 17631 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 18:00 | 18:30 | 0.5 | 17631 | 17726 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17631.00 t/17726.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000.00, Tq 15000.00, ROP 190.00
08/01/2020 | 18:30 | 18:35 | 0.08 | 17726 | 17726 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 18:35 | 19:10 | 0.58 | 17726 | 17820 | 94 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17726.00 t/17820.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000.00, Tq 15000.00, ROP 161.14
08/01/2020 | 19:10 | 19:15 | 0.08 | 17820 | 17820 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
08/01/2020 | 19:15 | 19:25 | 0.17 | 17820 | 17841 | 21 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17820.00 t/17841.00, w/WOB 32000.00,Flow 338.00, RPM 70.00, Press 4000.00, Tq 15000.00, ROP 126.00
08/01/2020 | 19:25 | 20:45 | 1.33 | 17841 | 17841 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate clean up cycle.
08/01/2020 | 20:45 | 24:00 | 3.25 | 17841 | 17841 | 0 | LAT | 5: BHA 5 (Lateral) | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_2_2020_DDR
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31131 / 20DD0153Mc |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Dietz 3H
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Longitude: |  | 96° 42' 45.479" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/02/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 135850
|  |  |  | 24hr Summary: |  | Running casing
|  |  |  | 24hr Lookahead: |  | Running casing & Cement
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17841 |  | 12820 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 4 | PV: | 1
End Depth (Usft): |  | 17841 |  | 17841 |  | OD (in): |  |  |  | 300: | 3 | YP: | 2
Total Drilled (Usft): |  |  |  | 5021 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 27
Slide Drilled (Usft): |  |  |  | 358 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  |  |  | 4663 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 0.50
Drlg/Circ Hrs: |  |  |  | 60.00 / 4.52 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  |  |  | 17.12 |  | SN: |  | 1138553 |  | 10s Gel: | 2 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  |  |  | 42.88 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.4 / 169.00 | Fluid Loss / Mud Type: | 25 / WBM
ROP Rot/Slide (Usft/hr): |  |  |  | 108.74 / 20.92 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 11.75 |  | 98.47 |  | Grade In: |  | Green
% Slide: |  |  |  | 7.13 |  | Grade Out: |  | 02
% Rotary: |  |  |  | 92.87 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Jeff Wells |  | Kyle Novasod |  | David LeBlanc
James |  | Leo Douet |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
Halliburton GTD64M (Jetted 6x16s) - TFA 1.18 |  |  |  | 6.75 | 1.5 |  |  |  |  | 0.74 |  | 0.74
5" 6/7 8.8 Stg 2? FBH TS |  |  |  | 5 | 2.563 |  |  |  |  | 33.1 |  | 33.84
BTI Valve |  |  |  | 4.75 | 2.5 |  |  |  |  | 2.25 |  | 36.09
NM Pony collar |  |  |  | 5 | 2.688 |  |  |  |  | 11.9 |  | 47.99
Float sub w/Restrictor sub jetted 20/32 |  |  |  | 5 | 2.25 |  |  |  |  | 3.55 |  | 51.54
UBHO |  |  |  | 5 | 2.5 |  |  |  |  | 3.49 |  | 55.03
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.78 |  | 85.81
NM Drill collar |  |  |  | 5 | 2.688 |  |  |  |  | 30.87 |  | 116.68
DS42 Box X XT39 Pin |  |  |  | 5 | 2.688 |  |  |  |  | 3.52 |  | 120.2
27 stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2593.2 |  | 2713.4
Delta 425 Box x DS42 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.22 |  | 2716.62
Agitator |  |  |  | 5.188 | 2.813 |  |  |  |  | 27.99 |  | 2744.61
DS42 Box x Delta 425 Pin |  |  |  | 5.313 | 2.563 |  |  |  |  | 3.31 |  | 2747.92
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250009 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.3 |  | 2 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 32000 | 70 | 300 | 338 | 4000 | 3300 | 104 | 330 | 225 | 165 | 15000 | 2000
Run | 83.68 | 32000 | 70 | 300 | 338 | 3870.33 | 3202.75 | 104 | 317.03 | 225 | 165 | 12048.31 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 08/02/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 08/02/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/02/2020 | 00:00 | 09:45 | 9.75 | 17841 | 17841 | 0 | LAT | 5: BHA 5 (Lateral) | 6B | Pooh
08/02/2020 | 09:45 | 11:45 | 2 | 17841 | 17841 | 0 | LAT | 5: BHA 5 (Lateral) | 6P | Running production casing
08/02/2020 | 11:45 | 24:00 | 12.25 | 17841 | 17841 | 0 | LAT |  | 12B | Running production casing
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 398.01 (Usft)
Well: |  |  | Dietz 3H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1129020 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/09/2020 | Depth In: |  | 105 | Total Drilled: |  | 2664.00 (Usft)
Date Out: |  |  | 07/09/2020 | Depth Out: |  | 2769 | Drilling / Circ Hours: |  | 5.48 / 1.33
Survey Offset: |  |  | 74
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 49142 | 13 1/2 - Ulterra - SPL616 | 13.5 | 2.5 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800019 | 7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | 8 | 2.5 |  | 6 5/8 Reg / 6 5/8 Reg |  | 37.65 | 39.15
| 3 | SD600317 | 13 Nortrak Stabalizer | 8.125 | 2.875 |  | 6 5/8 Reg / 6 5/8 Reg |  | 6.97 | 46.12
| 4 | SD54383 | 8" Pony Collar | 7.688 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 9.55 | 55.67
| 5 | ZSB775211 | 7 3/4" UBHO | 7.75 | 2.875 |  | 6 5/8 Reg / 6 5/8 Reg |  | 3.56 | 59.23
| 6 | SD43280 | 8" Drill Collar | 7.75 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 28.55 | 87.78
| 7 | SD56210 | 8" Drill Collar | 8 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 30.02 | 117.8
| 8 | SD109674 | X/O 4 1/2 IFB x 6 5/8 RegP | 6.75 | 2.875 |  | 4 1/2 IF / 6 5/8 Reg |  | 2.22 | 120.02
| 9 | Rig 1 | 9 joints of HWDP | 5 | 3 |  | 4 1/2IF / 4 1/2 IF |  | 277.99 | 398.01
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | 13 1/2 - Ulterra - SPL616 | 1.35 | Ulterra | SPL616 | Rerun | Green | 2664
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  | PDCI / 7/8 5.9 | 5.70 / 1.50 |  | 13 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 500 | 0 |  |  | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | 13 |  | 0 |  |  | 1.5
3 |  |  | 13 Nortrak Stabalizer | 13 |  | 0 |  |  | 39.15

## BHA_2_Intermediate
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2678.24 (Usft)
Well: |  |  | Dietz 3H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1129020 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/20/2020 | Depth In: |  | 2769 | Total Drilled: |  | 7480.00 (Usft)
Date Out: |  |  | 07/22/2020 | Depth Out: |  | 10249 | Drilling / Circ Hours: |  | 30.78 / 2.90
Survey Offset: |  |  | 68 | Gamma Offset: |  | 58
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 43215 | 9 7/8 - Ulterra - SPL613 | 9.875 | 2.5 |  | 6 5/8 Reg |  | 1.3 | 1.3
| 2 | PPM800015 | 7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS | 8 | 2.5 |  | 6 5/8 Reg / 6 5/8 Reg |  | 37.32 | 38.62
| 3 | SD43935 | 8 Pony Collar | 7.938 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 7.81 | 46.43
| 4 | 775199 | 7 3/4 UBHO | 7.75 | 2.875 |  | 6 5/8 Reg / 6 5/8 Reg |  | 3.86 | 50.29
| 5 | SD51948 | 8 Drill Collar | 7.75 | 3.313 |  | 6 5/8 Reg / 6 5/8 Reg |  | 27.12 | 77.41
| 6 | SD51886 | 8 Drill Collar | 7.875 | 3.313 |  | 6 5/8 Reg / 6 5/8 Reg |  | 27.4 | 104.81
| 7 | SD118447 | X/O 4 1/2 XHB x 6 5/8 RegP | 6.75 | 2.875 |  | 4 1/2 XH / 6 5/8 Reg |  | 3.47 | 108.28
| 8 | Rig 3 | 2 Stands 6 1/2in Collars | 6.5 | 2.375 |  | 4 1/2 XH / 4 1/2 XH |  | 187.21 | 295.49
| 9 | SD107702 | X/O 4 1/2 IFB x 4 1/2 XHP | 6.5 | 2.875 |  | 4 1/2 IF / 4 1/2 XH |  | 3 | 298.49
| 10 | Rig 1 | 3 Stands of HWDP | 5 | 3 |  | 4 1/2IF / 4 1/2 IF |  | 277.99 | 576.48
| 11 | Rig 2 | 22 stands of Drillpipe | 6 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2070.98 | 2647.46
| 12 | AGHF0675-0059 | Safety Joint / Agitator/Shocksub | 7 | 2.625 |  | 4 1/2 IF / 4 1/2 IF |  | 30.78 | 2678.24
| 13 | [8 empty] | 2678.24
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8 - Ulterra - SPL613 | 1.49 | Ulterra | SPL613 | Green |  | 7480
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS |  |  | PDCI / 7/8 5.9 | 5.65 / 2.00 |  | 0 | 8.38 | 0 | 1
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 0 |  |  | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3_Curve_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2745.79 (Usft)
Well: |  |  | Dietz 3H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1129020 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/24/2020 | Depth In: |  | 10249 | Total Drilled: |  | 2164.00 (Usft)
Date Out: |  |  | 07/26/2020 | Depth Out: |  | 12413 | Drilling / Circ Hours: |  | 25.00 / 2.52
Survey Offset: |  |  | 70 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 48479 | Ulterra RPS 613 6x16s | 6.75 | 1.5 |  | 3 1/2 Reg |  | 0.85 | 0.85
| 2 | MTR475113 | 5" 6/7 8.8 Stg 2? FBH TS | 5 |  | 5.000 / 1.90 | XT39 / 3 1/2 Reg |  | 33.39 | 34.24
| 3 | 30-10063 | BTI Valve | 4.75 | 2.5 |  | XT39 / XT39 |  | 2.25 | 36.49
| 4 | SD56841 | NM Pony collar | 5 | 2.688 |  | XT39 / XT39 |  | 11.9 | 48.39
| 5 | ZSB500029 | UBHO | 5 | 2.5 |  | XT39 / XT39 |  | 3.49 | 51.88
| 6 | SD56703 | NM Drill collar | 5 | 2.688 |  | XT39 / XT39 |  | 30.78 | 82.66
| 7 | SD56284 | NM Drill collar | 5 | 2.688 |  | XT39 / XT39 |  | 30.87 | 113.53
| 8 | SD119312 | DS42 Box X XT39 Pin | 5 | 2.688 |  | DS32 / XT39 |  | 3.52 | 117.05
| 9 | Rig 1 | 27 stands of 4 1/2" DP | 4.5 | 2.5 |  | DS42 / DS42 |  | 2593.2 | 2710.25
| 10 | DR38846 | Delta 425 Box x DS42 Pin | 5.313 | 2.563 |  | Delta 425 / DS42 |  | 3.22 | 2713.47
| 11 | 0525-00035 | Agitator | 5 | 3 |  | Delta 425 / Delta 425 |  | 29.01 | 2742.48
| 12 | DR38852 | DS42 Box x Delta 425 Pin | 5.313 | 2.563 |  | DS42 / Delta 425 |  | 3.31 | 2745.79
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | Ulterra RPS 613 6x16s | 1.18 | Ulterra | RPS613 | Green | Green | 2164
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5" 6/7 8.8 Stg 2? FBH TS |  |  | PDCI / 6/7 8.8 | 4.44 / 2.00 |  | 0 | 5.38 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
12000 |  |  | 3500 | 0 |  |  | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2748.22 (Usft)
Well: |  |  | Dietz 3H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1129020 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/26/2020 | Depth In: |  | 12413 | Total Drilled: |  | 407.00 (Usft)
Date Out: |  |  | 07/29/2020 | Depth Out: |  | 12820 | Drilling / Circ Hours: |  | 5.35 / 10.37
Survey Offset: |  |  | 73 | Gamma Offset: |  | 63
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 50597 | Ulterra RPS 613 6x16s | 6.75 | 1.5 |  | 3 1/2 Reg |  | 0.85 | 0.85
| 2 | MTR500048 | 5" 6/7 8.8 Stg 2? FBH TS | 4.875 |  | 1.92 | XT39 / 3 1/2 Reg |  | 33.33 | 34.18
| 3 | 30-10063 | BTI Valve | 4.75 | 2.5 |  | XT39 / XT39 |  | 2.25 | 36.43
| 4 | SD56841 | NM Pony collar | 5 | 2.688 |  | XT39 / XT39 |  | 11.9 | 48.33
| 5 | SD119029 | Float sub w/Restrictor sub jetted 20/32 | 5 | 2.25 |  | XT39 / XT39 |  | 3.55 | 51.88
| 6 | ZSB500029 | UBHO | 5 | 2.5 |  | XT39 / XT39 |  | 3.49 | 55.37
| 7 | SD56703 | NM Drill collar | 5 | 2.688 |  | XT39 / XT39 |  | 30.78 | 86.15
| 8 | SD56284 | NM Drill collar | 5 | 2.688 |  | XT39 / XT39 |  | 30.87 | 117.02
| 9 | SD119313 | DS42 Box X XT39 Pin | 5 | 2.688 |  | DS42 / XT39 |  | 3.52 | 120.54
| 10 | Rig 1 | 27 stands of 4 1/2" DP | 4.5 | 2.5 |  | DS42 / DS42 |  | 2593.2 | 2713.74
| 11 | DR38846 | Delta 425 Box x DS42 Pin | 5.313 | 2.563 |  | Delta 425 / DS42 |  | 3.22 | 2716.96
| 12 | 0525005 | Agitator | 5.063 | 2.5 | 2.01 | Delta 425 / Delta 425 |  | 27.95 | 2744.91
| 13 | DR38852 | DS42 Box x Delta 425 Pin | 5.313 | 2.563 |  | DS42 / Delta 425 |  | 3.31 | 2748.22
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | Ulterra RPS 613 6x16s | 1.18 | Baker Hughes | RPS613 | Green |  | 407
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5" 6/7 8.8 Stg 2? FBH TS |  |  | PDCI / 6/7 8.8 | 4.30 / 2.00 |  | 0 | 5.38 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 0 |  |  | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2747.92 (Usft)
Well: |  |  | Dietz 3H | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1129020 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/29/2020 | Depth In: |  | 12820 | Total Drilled: |  | 5021.00 (Usft)
Date Out: |  |  | 08/02/2020 | Depth Out: |  | 17841 | Drilling / Circ Hours: |  | 60.00 / 4.52
Survey Offset: |  |  | 73 | Gamma Offset: |  | 63
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 1138553 | Halliburton GTD64M (Jetted 6x16s) | 6.75 | 1.5 |  | 3 1/2 Reg |  | 0.74 | 0.74
| 2 | PPM250009 | 5" 6/7 8.8 Stg 2? FBH TS | 5 | 2.563 | 5.000 / 1.92 | XT39 / 3 1/2 Reg |  | 33.1 | 33.84
| 3 | 30-10063 | BTI Valve | 4.75 | 2.5 |  | XT39 / XT39 |  | 2.25 | 36.09
| 4 | SD56841 | NM Pony collar | 5 | 2.688 |  | XT39 / XT39 |  | 11.9 | 47.99
| 5 | SD119029 | Float sub w/Restrictor sub jetted 20/32 | 5 | 2.25 |  | XT39 / XT39 |  | 3.55 | 51.54
| 6 | ZSB500029 | UBHO | 5 | 2.5 |  | XT39 / XT39 |  | 3.49 | 55.03
| 7 | SD56703 | NM Drill collar | 5 | 2.688 |  | XT39 / XT39 |  | 30.78 | 85.81
| 8 | SD56284 | NM Drill collar | 5 | 2.688 |  | XT39 / XT39 |  | 30.87 | 116.68
| 9 | SD119313 | DS42 Box X XT39 Pin | 5 | 2.688 |  | DS42 / XT39 |  | 3.52 | 120.2
| 10 | Rig 1 | 27 stands of 4 1/2" DP | 4.5 | 2.5 |  | DS42 / DS42 |  | 2593.2 | 2713.4
| 11 | DR38846 | Delta 425 Box x DS42 Pin | 5.313 | 2.563 |  | Delta 425 / DS42 |  | 3.22 | 2716.62
| 12 | AGHF0525-0004 | Agitator | 5.188 | 2.813 | 2.01 | Delta 425 / Delta 425 |  | 27.99 | 2744.61
| 13 | DR38852 | DS42 Box x Delta 425 Pin | 5.313 | 2.563 |  | DS42 / Delta 425 |  | 3.31 | 2747.92
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | Halliburton GTD64M (Jetted 6x16s) | 1.18 | Halliburton | GTD64M | Green | 02 | 5021
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5" 6/7 8.8 Stg 2? FBH TS |  |  | PDCI / 6/7 8.8 | 4.30 / 2.00 |  | 0 | 5.38 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 0 |  |  | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Well: |  | Dietz 3H
|  |  |  | Longitude: |  | 96° 42' 45.479" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 07/09/2020 11:30 |  | SN: |  | PPM800019 |  |  |  | WOB Rotate (klbs): |  | 25.00
Date Out: |  | 07/09/2020 23:00 |  | Description: |  | 7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 105.00 / 2769.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 100.00
Inc In/Out: |  | 0.45 / 13.88 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 900
Azi In/Out: |  | 125.10 / 127.68 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 1350
Total Drilled (Usft): |  | 2664 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 2100
%Slide (Ftg): |  | 11.79 |  | Bit to Bend (Usft): |  | 5.7 |  |  |  | Tq On Btm (kftlbs): |  | 12000
%Slide (Time): |  | 31.00 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 314 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi): |  | 500
Slide Hours: |  | 1.7 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 88.21 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 68.94 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL616
Rotary Drilled (Usft): |  | 2350 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 13.5
Rotary Hours: |  | 3.78 |  | Length (Usft): |  | 37.65 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 5.48 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 1.33 / 11.50 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | Rerun
Slide ROP (Usft/hr): |  | 184.71 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | Green
Rot ROP (Usft/hr): |  | 621.69 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 5.48
Avg ROP (Usft/hr): |  | 486.13 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 1.33
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
6 / 5 | 4 / 3 | 2 / 2 |  |  |  | 2 | 1 | 8.7 | 500 | WBM | 0.25 | 0.25 | 113
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
74 | [9 empty] | 6 |  | 6.00 / 2.28
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
13 1/2 - Ulterra - SPL616 1.35 |  |  |  | 49142 |  | 13.5 | 2.5 |  |  |  | 1.5 | 1.5
7 3/4" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS 0.00 |  |  |  | PPM800019 |  | 8 | 2.5 |  |  |  | 37.65 | 39.15
13 Nortrak Stabalizer 0.00 |  |  |  | SD600317 |  | 8.125 | 2.875 |  |  |  | 6.97 | 46.12
8" Pony Collar 0.00 |  |  |  | SD54383 |  | 7.688 | 3.25 |  |  |  | 9.55 | 55.67
7 3/4" UBHO 0.00 |  |  |  | ZSB775211 |  | 7.75 | 2.875 |  |  |  | 3.56 | 59.23
8" Drill Collar 0.00 |  |  |  | SD43280 |  | 7.75 | 3.25 |  |  |  | 28.55 | 87.78
8" Drill Collar 0.00 |  |  |  | SD56210 |  | 8 | 3.25 |  |  |  | 30.02 | 117.8
X/O 4 1/2 IFB x 6 5/8 RegP 0.00 |  |  |  | SD109674 |  | 6.75 | 2.875 |  |  |  | 2.22 | 120.02
9 joints of HWDP 0.00 |  |  |  | Rig 1 |  | 5 | 3 |  |  |  | 277.99 | 398.01
Additional Comments
BHA was a rerun. Motor drained @surface with no visible wear. Total drilling / circ hours for motor: 15.98 / 19.61
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Well: |  | Dietz 3H
|  |  |  | Longitude: |  | 96° 42' 45.479" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 07/20/2020 04:50 |  | SN: |  | PPM800015 |  |  |  | WOB Rotate (klbs): |  | 28.00
Date Out: |  | 07/22/2020 13:30 |  | Description: |  | 7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 2769.00 / 10249.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 79.19
Inc In/Out: |  | 13.88 / 19.92 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 740.59
Azi In/Out: |  | 127.68 / 337.93 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 3252.89
Total Drilled (Usft): |  | 7480 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 3889.26
%Slide (Ftg): |  | 7.18 |  | Bit to Bend (Usft): |  | 5.65 |  |  |  | Tq On Btm (kftlbs): |  | 16343.43
%Slide (Time): |  | 36.32 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 537 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 11.18 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.82 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 63.67 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6943 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 9.875
Rotary Hours: |  | 19.6 |  | Length (Usft): |  | 37.32 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 30.78 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 2.90 / 56.67 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | Green
Slide ROP (Usft/hr): |  | 48.03 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 354.23 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 30.78
Avg ROP (Usft/hr): |  | 243.01 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.90
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
37 / 23 | 19 / 12 | 6 / 5 |  |  |  | 14 | 9 | 9.3 | 38000 | OBM | 9.6 | 0.25 | 238
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 58 | [10 empty] | 0.00 / 3.47
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8 - Ulterra - SPL613 1.49 |  |  |  | 43215 |  | 9.875 | 2.5 |  |  |  | 1.3 | 1.3
7 3/4 - 7/8, 5.9 Stg. @ 2.0? FBH TS 0.00 |  |  |  | PPM800015 |  | 8 | 2.5 |  |  |  | 37.32 | 38.62
8 Pony Collar 0.00 |  |  |  | SD43935 |  | 7.938 | 3.25 |  |  |  | 7.81 | 46.43
7 3/4 UBHO 0.00 |  |  |  | 775199 |  | 7.75 | 2.875 |  |  |  | 3.86 | 50.29
8 Drill Collar 0.00 |  |  |  | SD51948 |  | 7.75 | 3.313 |  |  |  | 27.12 | 77.41
8 Drill Collar 0.00 |  |  |  | SD51886 |  | 7.875 | 3.313 |  |  |  | 27.4 | 104.81
X/O 4 1/2 XHB x 6 5/8 RegP 0.00 |  |  |  | SD118447 |  | 6.75 | 2.875 |  |  |  | 3.47 | 108.28
2 Stands 6 1/2in Collars 0.00 |  |  |  | Rig 3 |  | 6.5 | 2.375 |  |  |  | 187.21 | 295.49
X/O 4 1/2 IFB x 4 1/2 XHP 0.00 |  |  |  | SD107702 |  | 6.5 | 2.875 |  |  |  | 3 | 298.49
3 Stands of HWDP 0.00 |  |  |  | Rig 1 |  | 5 | 3 |  |  |  | 277.99 | 576.48
22 stands of Drillpipe 0.00 |  |  |  | Rig 2 |  | 6 | 2.75 |  |  |  | 2070.98 | 2647.46
Safety Joint / Agitator/Shocksub 0.00 |  |  |  | AGHF0675-0059 |  | 7 | 2.625 |  |  |  | 30.78 | 2678.24
-1.00 | [11 empty] | 2678.24
Additional Comments
BHA perormed as expected. Drilled vertical section as planned, and began drilling curve until seen chalk marker in gamma. POOH to set intermediate casing. Assembly had 33.75 circulating hours, was subject to 234? oil base mud. At surface, motor drained strong, bearing gap was within tollerance, no visuable signs of damage to motor at surface.
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Well: |  | Dietz 3H
|  |  |  | Longitude: |  | 96° 42' 45.479" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Hole Conditions |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Jeff Wells |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 07/24/2020 07:30 |  | SN: |  | MTR475113 |  |  |  | WOB Rotate (klbs): |  | 26.00
Date Out: |  | 07/26/2020 17:30 |  | Description: |  | 5" 6/7 8.8 Stg 2? FBH TS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10249.00 / 12413.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 30.00
Inc In/Out: |  | 19.93 / 92.93 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 380
Azi In/Out: |  | 337.93 / 335.87 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 3528.57
Total Drilled (Usft): |  | 2164 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4278.57
%Slide (Ftg): |  | 32.95 |  | Bit to Bend (Usft): |  | 4.44 |  |  |  | Tq On Btm (kftlbs): |  | 10250
%Slide (Time): |  | 61.60 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 713 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi): |  | 3500
Slide Hours: |  | 15.4 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 67.05 |  | Kickpad OD (in): |  | 5.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 38.40 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | RPS613
Rotary Drilled (Usft): |  | 1451 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 9.6 |  | Length (Usft): |  | 33.39 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 25.00 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 2.52 / 58.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | Green
Slide ROP (Usft/hr): |  | 46.3 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | Green
Rot ROP (Usft/hr): |  | 151.15 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 25.00
Avg ROP (Usft/hr): |  | 86.56 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.52
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
33 / 21 | 18 / 14 | 6 / 5 |  |  |  | 12 | 9 | 9 | 43000 | OBM | 4.9 | 0.25 | 285
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
70 | 60 | [8 empty] | 8 |  | 15.00 / 16.67
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
Ulterra RPS 613 6x16s 1.18 |  |  |  | 48479 |  | 6.75 | 1.5 |  |  |  | 0.85 | 0.85
5" 6/7 8.8 Stg 2? FBH TS 0.00 |  |  |  | MTR475113 |  | 5 |  |  |  |  | 33.39 | 34.24
BTI Valve 0.00 |  |  |  | 30-10063 |  | 4.75 | 2.5 |  |  |  | 2.25 | 36.49
NM Pony collar 0.00 |  |  |  | SD56841 |  | 5 | 2.688 |  |  |  | 11.9 | 48.39
UBHO 0.00 |  |  |  | ZSB500029 |  | 5 | 2.5 |  |  |  | 3.49 | 51.88
NM Drill collar 0.00 |  |  |  | SD56703 |  | 5 | 2.688 |  |  |  | 30.78 | 82.66
NM Drill collar 0.00 |  |  |  | SD56284 |  | 5 | 2.688 |  |  |  | 30.87 | 113.53
DS42 Box X XT39 Pin 0.00 |  |  |  | SD119312 |  | 5 | 2.688 |  |  |  | 3.52 | 117.05
27 stands of 4 1/2" DP 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 2593.2 | 2710.25
Delta 425 Box x DS42 Pin 0.00 |  |  |  | DR38846 |  | 5.313 | 2.563 |  |  |  | 3.22 | 2713.47
Agitator 0.00 |  |  |  | 0525-00035 |  | 5 | 3 |  |  |  | 29.01 | 2742.48
DS42 Box x Delta 425 Pin 0.00 |  |  |  | DR38852 |  | 5.313 | 2.563 |  |  |  | 3.31 | 2745.79
Additional Comments
POOH due to suffering complete mud losses. POOH to P/U restrictor sub. BHA performed as expected . Motor drained at surface with no visible wear or damage. Motor was subjected to OBM @ 285? F Bit was green
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Well: |  | Dietz 3H
|  |  |  | Longitude: |  | 96° 42' 45.479" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Jeff Wells |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 07/26/2020 18:30 |  | SN: |  | MTR500048 |  |  |  | WOB Rotate (klbs): |  | 30.00
Date Out: |  | 07/29/2020 08:30 |  | Description: |  | 5" 6/7 8.8 Stg 2? FBH TS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 12413.00 / 12820.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 70.00
Inc In/Out: |  | 92.93 / 89.86 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 390
Azi In/Out: |  | 335.87 / 335.18 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 3600
Total Drilled (Usft): |  | 407 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4300
%Slide (Ftg): |  | 13.02 |  | Bit to Bend (Usft): |  | 4.3 |  |  |  | Tq On Btm (kftlbs): |  | 16000
%Slide (Time): |  | 50.09 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 53 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 2.68 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 86.98 |  | Kickpad OD (in): |  | 5.375 |  |  |  | Make: |  | Baker Hughes
%Rotary (Time): |  | 49.91 |  | Body OD (in): |  | 4.875 |  |  |  | Model: |  | RPS613
Rotary Drilled (Usft): |  | 354 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 6.75
Rotary Hours: |  | 2.67 |  | Length (Usft): |  | 33.33 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 5.35 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 10.37 / 62.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | Green
Slide ROP (Usft/hr): |  | 19.78 |  | # Stalls / Pressure: |  | 1 / 0.00 |  |  |  | Grade Out:
Rot ROP (Usft/hr): |  | 132.58 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 5.35
Avg ROP (Usft/hr): |  | 76.07 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 10.37
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
4 / 3 | 2 / 1 | 1 / 1 |  |  |  | 1 | 2 | 8.4 | 400 | WBM | 0.5 | 0.25 | 201
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
73 | 63 | [8 empty] | 2 |  | 2.00 / 4.77
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
Ulterra RPS 613 6x16s 1.18 |  |  |  | 50597 |  | 6.75 | 1.5 |  |  |  | 0.85 | 0.85
5" 6/7 8.8 Stg 2? FBH TS 0.00 |  |  |  | MTR500048 |  | 4.875 |  |  |  |  | 33.33 | 34.18
BTI Valve 0.00 |  |  |  | 30-10063 |  | 4.75 | 2.5 |  |  |  | 2.25 | 36.43
NM Pony collar 0.00 |  |  |  | SD56841 |  | 5 | 2.688 |  |  |  | 11.9 | 48.33
Float sub w/Restrictor sub jetted 20/32 0.00 |  |  |  | SD119029 |  | 5 | 2.25 |  |  |  | 3.55 | 51.88
UBHO 0.00 |  |  |  | ZSB500029 |  | 5 | 2.5 |  |  |  | 3.49 | 55.37
NM Drill collar 0.00 |  |  |  | SD56703 |  | 5 | 2.688 |  |  |  | 30.78 | 86.15
NM Drill collar 0.00 |  |  |  | SD56284 |  | 5 | 2.688 |  |  |  | 30.87 | 117.02
DS42 Box X XT39 Pin 0.00 |  |  |  | SD119313 |  | 5 | 2.688 |  |  |  | 3.52 | 120.54
27 stands of 4 1/2" DP 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 2593.2 | 2713.74
Delta 425 Box x DS42 Pin 0.00 |  |  |  | DR38846 |  | 5.313 | 2.563 |  |  |  | 3.22 | 2716.96
Agitator 0.00 |  |  |  | 0525005 |  | 5.063 | 2.5 |  |  |  | 27.95 | 2744.91
DS42 Box x Delta 425 Pin 0.00 |  |  |  | DR38852 |  | 5.313 | 2.563 |  |  |  | 3.31 | 2748.22
Failure Information
Incident | YES | Hrs Before Incident |  |  | Tripped For Incident |  | NO | BHA SN |  |  | MWD SN
LIH | NO | NPT |  |  | Catastrophic Inci. |  | NO | MOTOR Inci. | NO |  | MWD Inci. | NO
Closed | NO | EDR Review |  | NO | Surface Fail |  | NO | MTBF Attrib. | NO |  | MWD Cat
Operations at Time of Incident
Troubleshooting Performed
Surface Findings
Additional Comments
After completing a slide @ 12820MD, a spike in pressure occured, (6000 PSI+) causing popoffs to blow. Attempts were made to restablish parameters to no avail. POOH, @ surface it was discovered that the motor had parted at the service break between the FBH & the lower end. Motor was subjected to 8.4 PPG water @ 174? F thru a restrictor sub. Motor was tripped twice previous due to faulty MWD components.
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1129020 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31131 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 12' 36.596" N |  |  | Well: |  | Dietz 3H
|  |  |  | Longitude: |  | 96° 42' 45.479" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Jeff Wells |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 07/29/2020 09:17 |  | SN: |  | PPM250009 |  |  |  | WOB Rotate (klbs): |  | 32000.00
Date Out: |  | 08/02/2020 11:45 |  | Description: |  | 5" 6/7 8.8 Stg 2? FBH TS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 12820.00 / 17841.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 70.00
Inc In/Out: |  | 89.85 / 92.00 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 338
Azi In/Out: |  | 335.18 / 336.00 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 3202.75
Total Drilled (Usft): |  | 5021 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 3870.33
%Slide (Ftg): |  | 7.13 |  | Bit to Bend (Usft): |  | 4.3 |  |  |  | Tq On Btm (kftlbs): |  | 12048.31
%Slide (Time): |  | 28.52 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 358 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 17.11 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.87 |  | Kickpad OD (in): |  | 5.375 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 71.48 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 4663 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 42.89 |  | Length (Usft): |  | 33.1 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 60.00 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 4.52 / 98.47 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | Green
Slide ROP (Usft/hr): |  | 20.92 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 02
Rot ROP (Usft/hr): |  | 108.72 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 60.00
Avg ROP (Usft/hr): |  | 83.68 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 4.52
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
4 / 3 | 2 / 1 | 1 / 1 |  |  |  | 1 | 2 | 8.4 | 400 | WBM | 0.5 | 0.25 | 190
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
73 | 63 | [8 empty] | 10 |  | 13.00 / 5.19
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
Halliburton GTD64M (Jetted 6x16s) 1.18 |  |  |  | 1138553 |  | 6.75 | 1.5 |  |  |  | 0.74 | 0.74
5" 6/7 8.8 Stg 2? FBH TS 0.00 |  |  |  | PPM250009 |  | 5 | 2.563 |  |  |  | 33.1 | 33.84
BTI Valve 0.00 |  |  |  | 30-10063 |  | 4.75 | 2.5 |  |  |  | 2.25 | 36.09
NM Pony collar 0.00 |  |  |  | SD56841 |  | 5 | 2.688 |  |  |  | 11.9 | 47.99
Float sub w/Restrictor sub jetted 20/32 0.00 |  |  |  | SD119029 |  | 5 | 2.25 |  |  |  | 3.55 | 51.54
UBHO 0.00 |  |  |  | ZSB500029 |  | 5 | 2.5 |  |  |  | 3.49 | 55.03
NM Drill collar 0.00 |  |  |  | SD56703 |  | 5 | 2.688 |  |  |  | 30.78 | 85.81
NM Drill collar 0.00 |  |  |  | SD56284 |  | 5 | 2.688 |  |  |  | 30.87 | 116.68
DS42 Box X XT39 Pin 0.00 |  |  |  | SD119313 |  | 5 | 2.688 |  |  |  | 3.52 | 120.2
27 stands of 4 1/2" DP 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 2593.2 | 2713.4
Delta 425 Box x DS42 Pin 0.00 |  |  |  | DR38846 |  | 5.313 | 2.563 |  |  |  | 3.22 | 2716.62
Agitator 0.00 |  |  |  | AGHF0525-0004 |  | 5.188 | 2.813 |  |  |  | 27.99 | 2744.61
DS42 Box x Delta 425 Pin 0.00 |  |  |  | DR38852 |  | 5.313 | 2.563 |  |  |  | 3.31 | 2747.92
Additional Comments
Motor was ran in WBM @ 185?F. Motor drained at surface. No wear or damage to report. Float was left inside the motor.
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_2_Intermediate_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #2 (Intermediate) |  |  |  |  | RKB: |  |  |  | 367 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7480
Site: |  |  |  |  | Dietz-Palo-Acadia - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 537
Well Name: |  |  |  |  | Dietz 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 58.00 |  |  |  |  | Grid Conv: |  |  |  | 367 |  | VS Azimuth: |  | 336.31 |  | Rotate: |  | 6943
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/20/2020 | 07:50 | 07:53 | 0.05 | 2769 | 2786 | 17 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 498; Drilling Parameters Tq: 4000; Drilling Parameters ROP: 340 | 1300 | 1150 | 150 | 116 | 140 | 120 | 110
07/20/2020 | 08:26 | 08:43 | 0.28333 | 2786 | 2865 | 79 | Rotate |  | 2797 | 13.8 | 127.4 | 2753.01 | -254.72 | 307.63 | -254.72 | 0.38 |  |  | 25 | 40 | 498 | 4000 | 278.82 | 1300 | 1150 | 150 | 116 | 140 | 120 | 110
07/20/2020 | 08:48 | 08:58 | 0.16667 | 2865 | 2959 | 94 | Rotate |  | 2891 | 13 | 128.2 | 2844.45 | -268.07 | 324.84 | -268.07 | 0.87 |  |  | 35 | 80 | 623 | 7500 | 564 | 2900 | 2300 | 600 | 116 | 140 | 120 | 110
07/20/2020 | 09:03 | 09:06 | 0.05 | 2959 | 2970 | 11 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 623; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 220 | 2900 | 2300 | 600 | 116 | 140 | 120 | 110
07/20/2020 | 09:06 | 09:15 | 0.15 | 2970 | 2988 | 18 | Slide | 0 | 2985 | 14.3 | 133.2 | 2935.79 | -282.55 | 341.62 | -282.55 | 1.87 |  |  | 12 |  | 623 |  | 120 | 2450 | 2300 | 150 | 116 | 140 | 120 | 110
07/20/2020 | 09:15 | 09:24 | 0.15 | 2988 | 3053 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 623; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 433.33 | 2900 | 2300 | 600 | 116 | 140 | 120 | 110
07/20/2020 | 09:30 | 09:37 | 0.11667 | 3053 | 3147 | 94 | Rotate |  | 3079 | 14.7 | 130.7 | 3026.8 | -298.28 | 359.12 | -298.28 | 0.79 |  |  | 35 | 80 | 623 | 7500 | 805.71 | 2900 | 2300 | 600 | 116 | 140 | 120 | 110
07/20/2020 | 09:43 | 09:47 | 0.066667 | 3147 | 3241 | 94 | Rotate |  | 3173 | 14.6 | 127.8 | 3117.75 | -313.32 | 377.52 | -313.32 | 0.79 |  |  | 35 | 80 | 750 | 13000 | 1410 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 09:52 | 09:54 | 0.033333 | 3241 | 3250 | 9 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 270 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 09:54 | 10:00 | 0.1 | 3250 | 3265 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 150 | 3250 | 3100 | 150 | 131 | 140 | 120 | 110
07/20/2020 | 10:00 | 10:07 | 0.11667 | 3265 | 3335 | 70 | Rotate |  | 3266 | 15.4 | 131 | 3207.58 | -328.6 | 396.11 | -328.6 | 1.24 |  |  | 35 | 80 | 750 | 13000 | 600 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 10:12 | 10:32 | 0.33333 | 3335 | 3428 | 93 | Rotate |  | 3360 | 15.6 | 132.1 | 3298.16 | -345.27 | 414.9 | -345.27 | 0.38 |  |  | 40 | 80 | 750 | 13000 | 279 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 10:37 | 10:39 | 0.033333 | 3428 | 3435 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 210 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 10:39 | 10:48 | 0.15 | 3435 | 3450 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 100 | 3250 | 3100 | 150 | 131 | 140 | 120 | 110
07/20/2020 | 10:48 | 11:01 | 0.21667 | 3450 | 3522 | 72 | Rotate |  | 3454 | 14.9 | 136.9 | 3388.85 | -362.56 | 432.54 | -362.56 | 1.54 |  |  | 40 | 80 | 750 | 13000 | 332.31 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 11:05 | 11:20 | 0.25 | 3522 | 3616 | 94 | Rotate |  | 3548 | 14.2 | 136.1 | 3479.84 | -379.7 | 448.79 | -379.7 | 0.77 |  |  | 40 | 80 | 750 | 13000 | 376 | 3650 | 3100 | 550 | 131 | 140 | 120 | 110
07/20/2020 | 11:25 | 11:35 | 0.16667 | 3616 | 3710 | 94 | Rotate |  | 3642 | 14.2 | 135.9 | 3570.97 | -396.28 | 464.81 | -396.28 | 0.05 |  |  | 40 | 80 | 750 | 13000 | 564 | 3650 | 3100 | 550 | 145 | 140 | 120 | 110
07/20/2020 | 11:40 | 11:41 | 0.016667 | 3710 | 3720 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 600 | 3650 | 3100 | 550 | 145 | 140 | 120 | 110
07/20/2020 | 11:41 | 11:50 | 0.15 | 3720 | 3738 | 18 | Slide | 0 | 3736 | 14.2 | 140.8 | 3662.1 | -413.5 | 480.12 | -413.5 | 1.28 |  |  | 8 |  | 750 |  | 120 | 3250 | 3100 | 150 | 145 | 140 | 120 | 110
07/20/2020 | 11:50 | 12:00 | 0.16667 | 3738 | 3804 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 396 | 3650 | 3100 | 550 | 145 | 140 | 120 | 110
07/20/2020 | 12:05 | 12:15 | 0.16667 | 3804 | 3898 | 94 | Rotate |  | 3830 | 14.2 | 142.2 | 3753.23 | -431.54 | 494.47 | -431.54 | 0.37 |  |  | 40 | 80 | 750 | 13000 | 564 | 3650 | 3100 | 550 | 145 | 140 | 120 | 110
07/20/2020 | 12:20 | 12:28 | 0.13333 | 3898 | 3993 | 95 | Rotate |  | 3925 | 14.5 | 142.3 | 3845.26 | -450.16 | 508.89 | -450.16 | 0.32 |  |  | 40 | 80 | 750 | 13000 | 712.5 | 3650 | 3100 | 550 | 154 | 140 | 120 | 110
07/20/2020 | 12:33 | 12:43 | 0.16667 | 3993 | 4086 | 93 | Rotate |  | 4018 | 15 | 141.2 | 3935.2 | -468.75 | 523.55 | -468.75 | 0.62 |  |  | 40 | 80 | 750 | 13000 | 558 | 3800 | 3100 | 700 | 154 | 140 | 120 | 110
07/20/2020 | 12:47 | 12:57 | 0.16667 | 4086 | 4180 | 94 | Rotate |  | 4112 | 14.9 | 141 | 4026.01 | -487.62 | 538.78 | -487.62 | 0.12 |  |  | 40 | 80 | 750 | 15000 | 564 | 3800 | 3100 | 700 | 158 | 155 | 135 | 120
07/20/2020 | 13:03 | 13:12 | 0.15 | 4180 | 4274 | 94 | Rotate |  | 4206 | 15.2 | 140.1 | 4116.79 | -506.47 | 554.29 | -506.47 | 0.4 |  |  | 40 | 80 | 750 | 15000 | 626.67 | 3800 | 3100 | 700 | 158 | 155 | 135 | 120
07/20/2020 | 13:17 | 13:28 | 0.18333 | 4274 | 4369 | 95 | Rotate |  | 4301 | 14.9 | 139.4 | 4208.53 | -525.3 | 570.23 | -525.3 | 0.37 |  |  | 40 | 80 | 750 | 15000 | 518.18 | 3800 | 3100 | 700 | 158 | 155 | 135 | 120
07/20/2020 | 13:32 | 13:43 | 0.18333 | 4369 | 4463 | 94 | Rotate |  | 4395 | 14.6 | 137.6 | 4299.43 | -543.22 | 586.08 | -543.22 | 0.58 |  |  | 40 | 80 | 750 | 15000 | 512.73 | 3800 | 3100 | 700 | 158 | 155 | 135 | 120
07/20/2020 | 13:48 | 13:59 | 0.18333 | 4463 | 4558 | 95 | Rotate |  | 4490 | 14.9 | 136.1 | 4391.3 | -560.87 | 602.62 | -560.87 | 0.51 |  |  | 40 | 80 | 750 | 15000 | 518.18 | 3800 | 3100 | 700 | 158 | 155 | 135 | 120
07/20/2020 | 14:05 | 14:14 | 0.15 | 4558 | 4652 | 94 | Rotate |  | 4584 | 14.5 | 135.3 | 4482.23 | -577.94 | 619.28 | -577.94 | 0.48 |  |  | 40 | 80 | 750 | 15000 | 626.67 | 3800 | 3100 | 700 | 168 | 155 | 135 | 120
07/20/2020 | 14:20 | 14:31 | 0.18333 | 4652 | 4745 | 93 | Rotate |  | 4677 | 14.1 | 136 | 4572.35 | -594.36 | 635.34 | -594.36 | 0.47 |  |  | 40 | 80 | 750 | 15000 | 507.27 | 3800 | 3100 | 700 | 168 | 155 | 135 | 120
07/20/2020 | 14:35 | 14:48 | 0.21667 | 4745 | 4840 | 95 | Rotate |  | 4772 | 13.6 | 134.7 | 4664.58 | -610.54 | 651.32 | -610.54 | 0.62 |  |  | 40 | 80 | 750 | 15000 | 438.46 | 3800 | 3100 | 700 | 168 | 155 | 135 | 120
07/20/2020 | 14:53 | 15:05 | 0.2 | 4840 | 4935 | 95 | Rotate |  | 4867 | 13.8 | 131.5 | 4756.88 | -625.91 | 667.74 | -625.91 | 0.82 |  |  | 40 | 80 | 750 | 15000 | 475 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 15:10 | 15:22 | 0.2 | 4935 | 5029 | 94 | Rotate |  | 4961 | 13.2 | 132.1 | 4848.28 | -640.53 | 684.1 | -640.53 | 0.66 |  |  | 40 | 80 | 750 | 15000 | 470 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 15:27 | 15:39 | 0.2 | 5029 | 5123 | 94 | Rotate |  | 5055 | 12.6 | 130 | 4939.91 | -654.32 | 699.92 | -654.32 | 0.81 |  |  | 40 | 80 | 750 | 15000 | 470 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 15:45 | 15:47 | 0.033333 | 5123 | 5135 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 360 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 15:47 | 15:59 | 0.2 | 5135 | 5165 | 30 | Slide | 0 | 5149 | 14.5 | 134 | 5031.29 | -669.08 | 716.24 | -669.08 | 2.25 |  |  | 15 |  | 750 |  | 150 | 3500 | 3300 | 200 | 177 | 170 | 155 | 140
07/20/2020 | 15:59 | 16:06 | 0.11667 | 5165 | 5217 | 52 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 445.71 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 16:11 | 16:23 | 0.2 | 5217 | 5311 | 94 | Rotate |  | 5243 | 15.6 | 136.9 | 5122.07 | -686.49 | 733.34 | -686.49 | 1.42 |  |  | 40 | 80 | 750 | 15000 | 470 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 16:28 | 16:40 | 0.2 | 5311 | 5404 | 93 | Rotate |  | 5336 | 15.4 | 136.9 | 5211.69 | -704.64 | 750.32 | -704.64 | 0.22 |  |  | 40 | 80 | 750 | 15000 | 465 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 16:45 | 16:55 | 0.16667 | 5404 | 5498 | 94 | Rotate |  | 5430 | 15.1 | 133.7 | 5302.38 | -722.21 | 767.7 | -722.21 | 0.95 |  |  | 40 | 80 | 750 | 15000 | 564 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 17:00 | 17:11 | 0.18333 | 5498 | 5591 | 93 | Rotate |  | 5523 | 15.4 | 133.8 | 5392.1 | -739.12 | 785.37 | -739.12 | 0.32 |  |  | 40 | 80 | 750 | 15000 | 507.27 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 17:16 | 17:18 | 0.033333 | 5591 | 5600 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 270 | 4000 | 3300 | 700 | 177 | 170 | 155 | 140
07/20/2020 | 17:18 | 17:25 | 0.11667 | 5600 | 5615 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 128.57 | 3500 | 3300 | 200 | 177 | 170 | 155 | 140
07/20/2020 | 17:25 | 17:35 | 0.16667 | 5615 | 5685 | 70 | Rotate |  | 5617 | 14.2 | 137.3 | 5482.98 | -756.24 | 802.2 | -756.24 | 1.59 |  |  | 15 | 80 | 750 | 16000 | 420 | 3500 | 3300 | 200 | 177 | 170 | 155 | 140
07/20/2020 | 17:40 | 17:52 | 0.2 | 5685 | 5780 | 95 | Rotate |  | 5712 | 14.5 | 137.6 | 5575.02 | -773.58 | 818.12 | -773.58 | 0.33 |  |  | 15 | 80 | 750 | 16000 | 475 | 4000 | 3300 | 700 | 183 | 170 | 155 | 140
07/20/2020 | 17:57 | 18:08 | 0.18333 | 5780 | 5874 | 94 | Rotate |  | 5806 | 13.6 | 136.6 | 5666.21 | -790.3 | 833.65 | -790.3 | 0.99 |  |  | 15 | 80 | 750 | 17000 | 512.73 | 4000 | 3300 | 700 | 183 | 170 | 155 | 140
07/20/2020 | 18:13 | 18:28 | 0.25 | 5874 | 5968 | 94 | Rotate |  | 5900 | 12.6 | 135.4 | 5757.76 | -805.63 | 848.44 | -805.63 | 1.1 |  |  | 15 | 80 | 750 | 17000 | 376 | 4000 | 3300 | 700 | 185 | 170 | 155 | 140
07/20/2020 | 18:33 | 18:45 | 0.2 | 5968 | 6062 | 94 | Rotate |  | 5994 | 12.3 | 134.7 | 5849.55 | -819.98 | 862.76 | -819.98 | 0.36 |  |  | 15 | 80 | 750 | 17000 | 470 | 4000 | 3300 | 700 | 185 | 170 | 155 | 140
07/20/2020 | 18:50 | 19:02 | 0.2 | 6062 | 6155 | 93 | Rotate |  | 6087 | 11.6 | 132.7 | 5940.53 | -833.28 | 876.67 | -833.28 | 0.87 |  |  | 15 | 80 | 750 | 17000 | 465 | 4000 | 3300 | 700 | 187 | 170 | 155 | 140
07/20/2020 | 19:07 | 19:10 | 0.05 | 6155 | 6165 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 200 | 4000 | 3300 | 700 | 187 | 170 | 155 | 140
07/20/2020 | 19:10 | 19:25 | 0.25 | 6165 | 6187 | 22 | Slide | 0 | 6181 | 13.7 | 136.4 | 6032.25 | -847.76 | 891.3 | -847.76 | 2.39 |  |  | 15 |  | 750 |  | 88 | 4000 | 3300 | 700 | 187 | 170 | 155 | 140
07/20/2020 | 19:25 | 19:43 | 0.3 | 6187 | 6249 | 62 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 206.67 | 4000 | 3300 | 700 | 190 | 170 | 155 | 140
07/20/2020 | 19:48 | 20:01 | 0.21667 | 6249 | 6343 | 94 | Rotate |  | 6275 | 14.5 | 138.4 | 6123.42 | -864.62 | 906.79 | -864.62 | 1 |  |  | 15 | 80 | 750 | 18000 | 433.85 | 4000 | 3300 | 700 | 190 | 170 | 155 | 140
07/20/2020 | 20:06 | 20:20 | 0.23333 | 6343 | 6436 | 93 | Rotate |  | 6368 | 13.2 | 138.6 | 6213.71 | -881.29 | 921.54 | -881.29 | 1.4 |  |  | 15 | 80 | 750 | 18000 | 398.57 | 4000 | 3300 | 700 | 193 | 170 | 155 | 140
07/20/2020 | 20:25 | 20:30 | 0.083333 | 6436 | 6450 | 14 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 168 | 4000 | 3300 | 700 | 193 | 170 | 155 | 140
07/20/2020 | 20:30 | 20:46 | 0.26667 | 6450 | 6470 | 20 | Slide | 0 | 6462 | 14.2 | 138.2 | 6305.04 | -897.94 | 936.32 | -897.94 | 1.07 |  |  | 15 |  | 750 |  | 75 | 4000 | 3300 | 700 | 193 | 170 | 155 | 140
07/20/2020 | 20:46 | 21:02 | 0.26667 | 6470 | 6530 | 60 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 225 | 4000 | 3300 | 700 | 193 | 170 | 155 | 140
07/20/2020 | 21:07 | 21:20 | 0.21667 | 6530 | 6624 | 94 | Rotate |  | 6556 | 14.5 | 138.5 | 6396.1 | -915.34 | 951.8 | -915.34 | 0.33 |  |  | 15 | 80 | 750 | 18000 | 433.85 | 4000 | 3300 | 700 | 195 | 170 | 155 | 140
07/20/2020 | 21:25 | 21:40 | 0.25 | 6624 | 6718 | 94 | Rotate |  | 6650 | 14.4 | 136.7 | 6487.13 | -932.66 | 967.62 | -932.66 | 0.49 |  |  | 15 | 80 | 750 | 18000 | 376 | 4000 | 3300 | 700 | 195 | 170 | 155 | 140
07/20/2020 | 21:45 | 21:58 | 0.21667 | 6718 | 6812 | 94 | Rotate |  | 6744 | 13.2 | 137.6 | 6578.41 | -949.1 | 982.87 | -949.1 | 1.3 |  |  | 15 | 80 | 750 | 18000 | 433.85 | 4000 | 3300 | 700 | 196 | 170 | 155 | 140
07/20/2020 | 22:03 | 22:15 | 0.2 | 6812 | 6905 | 93 | Rotate |  | 6837 | 12.7 | 136.3 | 6669.05 | -964.33 | 997.09 | -964.33 | 0.62 |  |  | 15 | 80 | 750 | 18000 | 465 | 4000 | 3300 | 700 | 196 | 170 | 155 | 140
07/20/2020 | 22:20 | 22:33 | 0.21667 | 6905 | 7000 | 95 | Rotate |  | 6932 | 12.1 | 134.4 | 6761.83 | -978.85 | 1011.42 | -978.85 | 0.76 |  |  | 15 | 80 | 750 | 18000 | 438.46 | 4000 | 3300 | 700 | 196 | 170 | 155 | 140
07/20/2020 | 22:38 | 22:43 | 0.083333 | 7000 | 7010 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 120 | 4000 | 3300 | 700 | 197 | 170 | 155 | 140
07/20/2020 | 22:43 | 23:13 | 0.5 | 7010 | 7027 | 17 | Slide | 0 | 7026 | 12.1 | 137.3 | 6853.75 | -992.98 | 1025.14 | -992.98 | 0.65 |  |  | 15 |  | 750 |  | 34 | 4000 | 3300 | 700 | 197 | 170 | 155 | 140
07/20/2020 | 23:13 | 23:25 | 0.2 | 7027 | 7094 | 67 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 335 | 4000 | 3300 | 700 | 198 | 230 | 205 | 180
07/20/2020 | 23:30 | 23:35 | 0.083333 | 7094 | 7110 | 16 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 192 | 4000 | 3300 | 700 | 198 | 230 | 205 | 180
07/20/2020 | 23:35 | 24:00 | 0.41667 | 7110 | 7129 | 19 | Slide | 0 | 7120 | 13.7 | 137.8 | 6945.37 | -1008.47 | 1039.3 | -1008.47 | 1.71 |  |  | 15 | 80 | 750 | 18000 | 45.6 | 4000 | 3300 | 700 | 198 | 230 | 205 | 180
07/21/2020 | 00:00 | 00:13 | 0.21667 | 7129 | 7188 | 59 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 272.31 | 4000 | 3300 | 700 | 198 | 170 | 155 | 140
07/21/2020 | 00:18 | 00:33 | 0.25 | 7188 | 7282 | 94 | Rotate |  | 7214 | 12.9 | 137.9 | 7036.85 | -1024.5 | 1053.82 | -1024.5 | 0.85 |  |  | 15 | 80 | 750 | 18000 | 376 | 4000 | 3300 | 700 | 198 | 170 | 155 | 140
07/21/2020 | 00:38 | 00:50 | 0.2 | 7282 | 7376 | 94 | Rotate |  | 7308 | 11.8 | 135.2 | 7128.67 | -1039.1 | 1067.62 | -1039.1 | 1.32 |  |  | 15 | 80 | 750 | 18000 | 470 | 4000 | 3300 | 700 | 200 | 170 | 155 | 140
07/21/2020 | 00:55 | 01:07 | 0.2 | 7376 | 7470 | 94 | Rotate |  | 7402 | 10.2 | 133.7 | 7220.94 | -1051.68 | 1080.41 | -1051.68 | 1.73 |  |  | 15 | 80 | 750 | 18000 | 470 | 4000 | 3300 | 700 | 200 | 170 | 155 | 140
07/21/2020 | 01:12 | 01:16 | 0.066667 | 7470 | 7477 | 7 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 105 | 4000 | 3300 | 700 | 202 | 170 | 155 | 140
07/21/2020 | 01:16 | 01:43 | 0.45 | 7477 | 7497 | 20 | Slide | 0 | 7496 | 10.6 | 137.6 | 7313.4 | -1063.81 | 1092.26 | -1063.81 | 0.86 |  |  | 15 |  | 750 |  | 44.44 | 4000 | 3300 | 700 | 202 | 170 | 155 | 140
07/21/2020 | 01:43 | 01:59 | 0.26667 | 7497 | 7564 | 67 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 251.25 | 4000 | 3300 | 700 | 202 | 170 | 155 | 140
07/21/2020 | 02:04 | 02:17 | 0.21667 | 7564 | 7657 | 93 | Rotate |  | 7589 | 8.5 | 142.7 | 7405.11 | -1075.6 | 1102.19 | -1075.6 | 2.43 |  |  | 15 | 80 | 750 | 18000 | 429.23 | 4000 | 3300 | 700 | 202 | 170 | 155 | 140
07/21/2020 | 02:20 | 02:27 | 0.11667 | 7657 | 7665 | 8 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 68.57 | 4000 | 3300 | 700 | 202 | 170 | 155 | 140
07/21/2020 | 02:27 | 02:55 | 0.46667 | 7665 | 7689 | 24 | Slide | 0 | 7682 | 9.4 | 138.5 | 7496.97 | -1086.75 | 1111.39 | -1086.75 | 1.2 |  |  | 15 |  | 750 |  | 51.43 | 4000 | 3300 | 700 | 202 | 170 | 155 | 140
07/21/2020 | 02:55 | 03:06 | 0.18333 | 7689 | 7750 | 61 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 332.73 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 03:11 | 03:48 | 0.61667 | 7750 | 7778 | 28 | Slide | 0 | 7776 | 11.3 | 141.3 | 7589.44 | -1099.69 | 1122.24 | -1099.69 | 2.09 |  |  | 15 |  | 750 |  | 45.41 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 03:48 | 04:07 | 0.31667 | 7778 | 7844 | 66 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 208.42 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 04:12 | 04:17 | 0.083333 | 7844 | 7860 | 16 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 192 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 04:17 | 04:35 | 0.3 | 7860 | 7880 | 20 | Slide | 0 | 7870 | 11.5 | 136.5 | 7681.59 | -1113.67 | 1134.45 | -1113.67 | 1.03 |  |  | 15 |  | 750 |  | 66.67 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 04:35 | 04:49 | 0.23333 | 7880 | 7938 | 58 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 248.57 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 04:54 | 05:00 | 0.1 | 7938 | 7955 | 17 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 170 | 4000 | 3300 | 700 | 203 | 170 | 155 | 140
07/21/2020 | 05:00 | 05:12 | 0.2 | 7955 | 7970 | 15 | Slide | 0 | 7964 | 12 | 136.2 | 7773.62 | -1127.52 | 1147.66 | -1127.52 | 0.54 |  |  | 15 |  | 750 |  | 75 | 4000 | 3300 | 700 | 204 | 170 | 155 | 140
07/21/2020 | 05:12 | 05:35 | 0.38333 | 7970 | 8032 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 161.74 | 4200 | 3400 | 800 | 217 | 280 | 220 | 190
07/21/2020 | 05:40 | 05:55 | 0.25 | 8032 | 8126 | 94 | Rotate |  | 8058 | 11.3 | 135.4 | 7865.68 | -1141.13 | 1160.89 | -1141.13 | 0.76 |  |  | 40 | 80 | 750 | 19000 | 376 | 4200 | 3400 | 800 | 217 | 280 | 220 | 190
07/21/2020 | 06:00 | 06:11 | 0.18333 | 8126 | 8221 | 95 | Rotate |  | 8153 | 9 | 138.3 | 7959.19 | -1153.31 | 1172.37 | -1153.31 | 2.48 |  |  | 40 | 80 | 750 | 19000 | 518.18 | 4200 | 3400 | 800 | 217 | 280 | 220 | 190
07/21/2020 | 06:15 | 06:30 | 0.25 | 8221 | 8315 | 94 | Rotate |  | 8247 | 7.2 | 136.7 | 8052.25 | -1163.09 | 1181.3 | -1163.09 | 1.93 |  |  | 40 | 80 | 750 | 19000 | 376 | 4200 | 3400 | 800 | 217 | 280 | 220 | 190
07/21/2020 | 06:35 | 06:47 | 0.2 | 8315 | 8408 | 93 | Rotate |  | 8340 | 5.4 | 136.7 | 8144.68 | -1170.52 | 1188.3 | -1170.52 | 1.94 |  |  | 40 | 80 | 750 | 19000 | 465 | 4200 | 3400 | 800 | 217 | 280 | 220 | 190
07/21/2020 | 06:52 | 07:06 | 0.23333 | 8408 | 8502 | 94 | Rotate |  | 8434 | 4 | 139.9 | 8238.36 | -1176.24 | 1193.45 | -1176.24 | 1.51 |  |  | 40 | 80 | 750 | 19000 | 402.86 | 4200 | 3400 | 800 | 217 | 280 | 220 | 190
07/21/2020 | 07:10 | 07:24 | 0.23333 | 8502 | 8597 | 95 | Rotate |  | 8529 | 2.9 | 139.2 | 8333.19 | -1180.6 | 1197.15 | -1180.6 | 1.16 |  |  | 40 | 80 | 750 | 19000 | 407.14 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 07:30 | 07:42 | 0.2 | 8597 | 8691 | 94 | Rotate |  | 8623 | 2.9 | 135.8 | 8427.07 | -1184.1 | 1200.36 | -1184.1 | 0.18 |  |  | 40 | 80 | 750 | 19000 | 470 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 07:47 | 08:00 | 0.21667 | 8691 | 8785 | 94 | Rotate |  | 8717 | 2.6 | 136.9 | 8520.96 | -1187.36 | 1203.48 | -1187.36 | 0.32 |  |  | 40 | 80 | 750 | 19000 | 433.85 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 08:05 | 08:18 | 0.21667 | 8785 | 8880 | 95 | Rotate |  | 8812 | 2 | 143.6 | 8615.88 | -1190.27 | 1205.93 | -1190.27 | 0.69 |  |  | 40 | 80 | 750 | 19000 | 438.46 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 08:23 | 08:27 | 0.066667 | 8880 | 8890 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 150 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 08:27 | 08:45 | 0.3 | 8890 | 8910 | 20 | Slide | 0 | 8906 | 2.5 | 89.3 | 8709.82 | -1191.57 | 1208.96 | -1191.57 | 2.23 |  |  | 30 |  | 750 |  | 66.67 | 3600 | 3400 | 200 | 221 | 280 | 220 | 190
07/21/2020 | 08:45 | 09:00 | 0.25 | 8910 | 8974 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 256 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 09:05 | 09:20 | 0.25 | 8974 | 9065 | 91 | Rotate |  | 8997 | 2.7 | 62.3 | 8800.73 | -1190.55 | 1212.84 | -1190.55 | 1.35 |  |  | 40 | 80 | 750 | 19000 | 364 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 09:25 | 09:38 | 0.21667 | 9065 | 9158 | 93 | Rotate |  | 9090 | 2.5 | 45.2 | 8893.64 | -1188.1 | 1216.22 | -1188.1 | 0.86 |  |  | 40 | 80 | 750 | 19000 | 429.23 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 09:43 | 09:46 | 0.05 | 9158 | 9170 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 240 | 4200 | 3400 | 800 | 221 | 280 | 220 | 190
07/21/2020 | 09:46 | 10:01 | 0.25 | 9170 | 9185 | 15 | Slide | 0 | 9184 | 1.4 | 23.5 | 8987.58 | -1185.6 | 1218.13 | -1185.6 | 1.39 |  |  | 30 |  | 750 |  | 60 | 3600 | 3400 | 200 | 224 | 280 | 220 | 190
07/21/2020 | 10:01 | 10:13 | 0.2 | 9185 | 9252 | 67 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 335 | 4200 | 3400 | 800 | 224 | 280 | 220 | 190
07/21/2020 | 10:18 | 10:40 | 0.36667 | 9252 | 9346 | 94 | Rotate |  | 9278 | 0.4 | 45.4 | 9081.57 | -1184.32 | 1218.82 | -1184.32 | 1.11 |  |  | 40 | 80 | 750 | 19000 | 256.36 | 4200 | 3400 | 800 | 224 | 280 | 220 | 190
07/21/2020 | 10:45 | 11:15 | 0.5 | 9346 | 9440 | 94 | Rotate |  | 9372 | 0.7 | 55.7 | 9175.57 | -1183.76 | 1219.53 | -1183.76 | 0.33 |  |  | 40 | 80 | 750 | 19000 | 188 | 4200 | 3400 | 800 | 224 | 280 | 220 | 190
07/21/2020 | 12:05 | 12:32 | 0.45 | 9440 | 9533 | 93 | Rotate |  | 9465 | 1.3 | 56.9 | 9268.55 | -1182.87 | 1220.88 | -1182.87 | 0.65 |  |  | 40 | 80 | 750 | 19000 | 206.67 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 12:37 | 12:41 | 0.066667 | 9533 | 9545 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 180 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 12:41 | 13:34 | 0.88333 | 9545 | 9580 | 35 | Slide | 0 | 9559 | 2.6 | 355.7 | 9362.5 | -1180.16 | 1221.62 | -1180.16 | 2.42 |  |  | 30 |  | 750 |  | 39.62 | 3900 | 3700 | 200 | 224 | 295 | 235 | 190
07/21/2020 | 14:50 | 15:09 | 0.31667 | 9580 | 9627 | 47 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 148.42 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 15:18 | 15:25 | 0.11667 | 9627 | 9650 | 23 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 197.14 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 15:25 | 15:58 | 0.55 | 9650 | 9670 | 20 | Slide | 0 | 9653 | 5.5 | 332.8 | 9456.26 | -1174.02 | 1219.4 | -1174.02 | 3.47 |  |  | 30 |  | 750 |  | 36.36 | 3900 | 3700 | 200 | 224 | 295 | 235 | 190
07/21/2020 | 15:58 | 16:16 | 0.3 | 9670 | 9721 | 51 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 170 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 16:23 | 16:30 | 0.11667 | 9721 | 9750 | 29 | Rotate |  | 9747 | 7.7 | 331.5 | 9549.63 | -1164.48 | 1214.33 | -1164.48 | 2.35 |  |  | 40 | 80 | 750 | 19000 | 248.57 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 16:30 | 16:50 | 0.33333 | 9750 | 9766 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 48 | 3900 | 3700 | 200 | 224 | 295 | 235 | 190
07/21/2020 | 16:50 | 17:05 | 0.25 | 9766 | 9815 | 49 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 196 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 17:12 | 17:17 | 0.083333 | 9815 | 9840 | 25 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 300 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 17:17 | 17:45 | 0.46667 | 9840 | 9860 | 20 | Slide | 0 | 9841 | 9.1 | 333.2 | 9642.62 | -1152.31 | 1207.98 | -1152.31 | 1.51 |  |  | 40 |  | 750 |  | 42.86 | 4400 | 3700 | 700 | 224 | 295 | 235 | 190
07/21/2020 | 17:45 | 18:02 | 0.28333 | 9860 | 9909 | 49 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 172.94 | 4400 | 3700 | 700 | 228 | 295 | 235 | 190
07/21/2020 | 18:07 | 18:13 | 0.1 | 9909 | 9930 | 21 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 210 | 4400 | 3700 | 700 | 228 | 295 | 235 | 190
07/21/2020 | 18:13 | 19:25 | 1.2 | 9930 | 9955 | 25 | Slide | 0 | 9935 | 10.4 | 341.5 | 9735.27 | -1137.63 | 1201.93 | -1137.63 | 2.03 |  |  | 40 |  | 750 |  | 20.83 | 4400 | 3700 | 700 | 234 | 295 | 235 | 190
07/21/2020 | 19:25 | 19:38 | 0.21667 | 9955 | 10003 | 48 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 221.54 | 4400 | 3700 | 700 | 234 | 295 | 235 | 190
07/21/2020 | 19:49 | 19:57 | 0.13333 | 10003 | 10017 | 14 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 105 | 4400 | 3700 | 700 | 234 | 295 | 235 | 190
07/21/2020 | 19:57 | 20:45 | 0.8 | 10017 | 10047 | 30 | Slide | 0 | 10028 | 13.5 | 338.8 | 9826.24 | -1119.54 | 1195.34 | -1119.54 | 3.39 |  |  | 40 | 80 | 750 | 19000 | 37.5 | 4400 | 3700 | 700 | 236 | 295 | 235 | 190
07/21/2020 | 20:45 | 21:00 | 0.25 | 10047 | 10096 | 49 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 196 | 4400 | 3700 | 700 | 236 | 295 | 235 | 190
07/21/2020 | 21:05 | 21:09 | 0.066667 | 10096 | 10111 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 225 | 4400 | 3700 | 700 | 238 | 295 | 235 | 190
07/21/2020 | 21:09 | 21:50 | 0.68333 | 10111 | 10141 | 30 | Slide | 0 | 10121 | 16.4 | 337.6 | 9916.09 | -1097.28 | 1186.41 | -1097.28 | 3.14 |  |  | 40 | 80 | 750 | 19000 | 43.9 | 4400 | 3700 | 700 | 238 | 295 | 235 | 190
07/21/2020 | 21:50 | 22:08 | 0.3 | 10141 | 10189 | 48 | Rotate |  | 10181 | 17.3 | 336 | 9973.51 | -1081.3 | 1179.55 | -1081.3 | 1.69 |  |  | 40 | 80 | 750 | 19000 | 160 | 4400 | 3700 | 700 | 238 | 295 | 235 | 190
07/21/2020 | 22:13 | 22:23 | 0.16667 | 10189 | 10205 | 16 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 96 | 4400 | 3700 | 700 | 238 | 295 | 235 | 190
07/21/2020 | 22:23 | 23:45 | 1.3667 | 10205 | 10235 | 30 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 21.95 | 4400 | 3700 | 700 | 238 | 295 | 235 | 190
07/21/2020 | 23:45 | 24:00 | 0.25 | 10235 | 10249 | 14 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 56 | 4400 | 3700 | 700 | 238 | 295 | 235 | 190

## BHA_3_Curve_Lateral_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 (Curve-Lateral) |  |  |  |  | RKB: |  |  |  | 367 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2164
Site: |  |  |  |  | Dietz-Palo-Acadia - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 713
Well Name: |  |  |  |  | Dietz 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 70.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 367 |  | VS Azimuth: |  | 336.31 |  | Rotate: |  | 1451
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/24/2020 | 23:10 | 23:14 | 0.066667 | 10249 | 10259 | 10 | Rotate |  | 10256 | 20.2 | 338.1 | 10044.52 | -1059.09 | 1170.19 | -1059.09 | 3.97 |  |  | 15 | 30 | 260 | 5000 | 150 | 2750 | 2500 | 250 | 231 | 240 | 200 | 180
07/25/2020 | 00:00 | 01:00 | 1 | 10259 | 10314 | 55 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 55 | 4200 | 3700 | 500 | 231 | 240 | 200 | 180
07/25/2020 | 01:00 | 01:14 | 0.23333 | 10314 | 10326 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 51.43 | 4700 | 3700 | 1000 | 231 | 240 | 200 | 180
07/25/2020 | 01:24 | 01:37 | 0.21667 | 10326 | 10341 | 15 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 69.23 | 4700 | 3700 | 1000 | 231 | 240 | 200 | 180
07/25/2020 | 01:37 | 02:24 | 0.78333 | 10341 | 10381 | 40 | Slide | 0 | 10351 | 28 | 336.6 | 10131.18 | -1023.35 | 1155.19 | -1023.35 | 8.24 |  |  | 25 |  | 400 |  | 51.06 | 4200 | 3700 | 500 | 231 | 240 | 200 | 180
07/25/2020 | 02:24 | 02:40 | 0.26667 | 10381 | 10421 | 40 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 150 | 4700 | 3700 | 1000 | 231 | 240 | 200 | 180
07/25/2020 | 02:50 | 04:35 | 1.75 | 10421 | 10517 | 96 | Slide | 0 | 10447 | 30.5 | 332.1 | 10214.94 | -981.13 | 1134.83 | -981.13 | 3.47 |  |  | 30 |  | 400 |  | 54.86 | 4700 | 3700 | 1000 | 235 | 240 | 200 | 180
07/25/2020 | 04:45 | 05:44 | 0.98333 | 10517 | 10580 | 63 | Slide | 0 | 10542 | 43.6 | 334.3 | 10290.6 | -930.08 | 1109.24 | -930.08 | 13.86 |  |  | 30 |  | 400 |  | 64.07 | 4700 | 3700 | 1000 | 237 | 240 | 200 | 180
07/25/2020 | 05:49 | 06:00 | 0.18333 | 10580 | 10612 | 32 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 174.55 | 4700 | 3700 | 1000 | 237 | 240 | 200 | 180
07/25/2020 | 06:05 | 06:24 | 0.31667 | 10612 | 10644 | 32 | Rotate |  | 10638 | 46 | 332.9 | 10358.71 | -869.51 | 1079.15 | -869.51 | 2.7 |  |  | 30 | 30 | 400 | 12000 | 101.05 | 4700 | 3700 | 1000 | 237 | 240 | 200 | 180
07/25/2020 | 06:24 | 07:24 | 1 | 10644 | 10708 | 64 | Slide | 0 | 10685 | 49.9 | 334.2 | 10390.19 | -838.26 | 1063.62 | -838.26 | 8.55 |  |  | 30 |  | 400 |  | 64 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 07:29 | 07:40 | 0.18333 | 10708 | 10711 | 3 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 16.36 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 07:40 | 08:32 | 0.86667 | 10711 | 10755 | 44 | Slide | 0 | 10732 | 57.7 | 335.1 | 10417.93 | -804.01 | 1047.4 | -804.01 | 16.67 |  |  | 30 |  | 400 |  | 50.77 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 08:37 | 09:26 | 0.81667 | 10755 | 10802 | 47 | Rotate |  | 10779 | 62.1 | 338.3 | 10441.49 | -766.67 | 1031.35 | -766.67 | 11.06 |  |  | 30 | 30 | 400 | 12000 | 57.55 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 09:32 | 10:20 | 0.8 | 10802 | 10849 | 47 | Slide | 0 | 10826 | 67.7 | 340.8 | 10461.43 | -726.8 | 1016.51 | -726.8 | 12.85 |  |  | 30 |  | 400 |  | 58.75 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 10:25 | 10:33 | 0.13333 | 10849 | 10854 | 5 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 37.5 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 10:33 | 11:17 | 0.73333 | 10854 | 10896 | 42 | Slide | 0 | 10873 | 72.6 | 338.6 | 10477.38 | -685.36 | 1001.16 | -685.36 | 11.32 |  |  | 30 |  | 400 |  | 57.27 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 11:25 | 11:29 | 0.066667 | 10896 | 10901 | 5 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 75 | 4700 | 3700 | 1000 | 244 | 240 | 200 | 180
07/25/2020 | 11:29 | 12:05 | 0.6 | 10901 | 10936 | 35 | Slide | 0 | 10921 | 78.9 | 337 | 10489.19 | -642.31 | 983.59 | -642.31 | 13.52 |  |  | 30 |  | 400 |  | 58.33 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 12:05 | 12:17 | 0.2 | 10936 | 10943 | 7 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 35 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 12:22 | 12:31 | 0.15 | 10943 | 10960 | 17 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 113.33 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 12:31 | 13:07 | 0.6 | 10960 | 10991 | 31 | Slide | 0 | 10968 | 81.5 | 335.3 | 10497.19 | -599.96 | 964.86 | -599.96 | 6.58 |  |  | 30 |  | 400 |  | 51.67 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 13:12 | 13:30 | 0.3 | 10991 | 11038 | 47 | Rotate |  | 11017 | 84.2 | 334.1 | 10503.29 | -556.01 | 944.08 | -556.01 | 6.02 |  |  | 30 | 30 | 400 | 12000 | 156.67 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 13:35 | 13:42 | 0.11667 | 11038 | 11058 | 20 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 171.43 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 13:42 | 14:07 | 0.41667 | 11058 | 11073 | 15 | Slide | 0 | 11064 | 85.1 | 332.8 | 10507.67 | -514.15 | 923.17 | -514.15 | 3.35 |  |  | 30 |  | 400 |  | 36 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 14:07 | 14:14 | 0.11667 | 11073 | 11087 | 14 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 120 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 14:14 | 14:33 | 0.31667 | 11087 | 11134 | 47 | Rotate |  | 11111 | 85.9 | 331.5 | 10511.36 | -472.72 | 901.28 | -472.72 | 3.24 |  |  | 30 | 30 | 400 | 12000 | 148.42 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 14:38 | 15:40 | 1.0333 | 11134 | 11181 | 47 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 45.48 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 15:45 | 16:20 | 0.58333 | 11181 | 11196 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 25.71 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 16:20 | 16:48 | 0.46667 | 11196 | 11276 | 80 | Rotate |  | 11206 | 92.7 | 333.5 | 10512.52 | -388.52 | 857.44 | -388.52 | 7.46 |  |  | 30 | 30 | 400 | 12000 | 171.43 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 16:54 | 17:22 | 0.46667 | 11276 | 11371 | 95 | Rotate |  | 11301 | 93.7 | 332.3 | 10507.22 | -304.08 | 814.24 | -304.08 | 1.64 |  |  | 30 | 30 | 400 | 12000 | 203.57 | 4700 | 3700 | 1000 | 251 | 240 | 200 | 180
07/25/2020 | 17:58 | 18:03 | 0.083333 | 11371 | 11380 | 9 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 108 | 4700 | 3700 | 1000 | 251 | 260 | 200 | 180
07/25/2020 | 18:03 | 19:15 | 1.2 | 11380 | 11405 | 25 | Slide | 0 | 11397 | 93.9 | 335 | 10500.85 | -218.25 | 771.72 | -218.25 | 2.81 |  |  | 30 |  | 400 |  | 20.83 | 4700 | 3700 | 1000 | 251 | 260 | 200 | 180
07/25/2020 | 19:15 | 19:31 | 0.26667 | 11405 | 11467 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 232.5 | 4700 | 3700 | 1000 | 251 | 260 | 200 | 180
07/25/2020 | 19:37 | 19:43 | 0.1 | 11467 | 11475 | 8 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 80 | 4700 | 3700 | 1000 | 253 | 260 | 200 | 180
07/25/2020 | 19:43 | 20:30 | 0.78333 | 11475 | 11495 | 20 | Slide | 0 | 11491 | 91.9 | 337.5 | 10496.1 | -132.33 | 733.92 | -132.33 | 3.4 |  |  | 30 |  | 400 |  | 25.53 | 4700 | 3700 | 1000 | 253 | 260 | 200 | 180
07/25/2020 | 20:30 | 20:47 | 0.28333 | 11495 | 11561 | 66 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 232.94 | 4700 | 3700 | 1000 | 260 | 260 | 200 | 180
07/25/2020 | 20:53 | 21:15 | 0.36667 | 11561 | 11657 | 96 | Rotate |  | 11585 | 92.5 | 337.2 | 10492.49 | -45.65 | 697.75 | -45.65 | 0.71 |  |  | 30 | 30 | 400 | 12000 | 261.82 | 4700 | 3700 | 1000 | 260 | 260 | 200 | 180
07/25/2020 | 21:22 | 22:24 | 1.0333 | 11657 | 11688 | 31 | Slide | 0 | 11680 | 91.3 | 341.2 | 10489.34 | 43.09 | 664.04 | 43.09 | 4.39 |  |  | 30 |  | 400 | 12000 | 30 | 4700 | 3700 | 1000 | 260 | 260 | 200 | 180
07/25/2020 | 22:24 | 22:48 | 0.4 | 11688 | 11750 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 155 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/25/2020 | 22:52 | 23:12 | 0.33333 | 11750 | 11844 | 94 | Rotate |  | 11774 | 91.7 | 341.4 | 10486.88 | 132.1 | 633.91 | 132.1 | 0.48 |  |  | 30 | 70 | 400 | 12000 | 282 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/25/2020 | 23:17 | 23:25 | 0.13333 | 11844 | 11850 | 6 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 45 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/25/2020 | 23:25 | 24:00 | 0.58333 | 11850 | 11878 | 28 | Slide | 0 | 11868 | 91.2 | 340 | 10484.5 | 220.79 | 602.86 | 220.79 | 1.58 |  |  | 30 |  | 400 | 12000 | 48 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/26/2020 | 00:00 | 00:45 | 0.75 | 11878 | 11938 | 60 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 80 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/26/2020 | 00:50 | 01:10 | 0.33333 | 11938 | 12034 | 96 | Rotate |  | 11964 | 90.6 | 338.5 | 10482.99 | 310.54 | 568.85 | 310.54 | 1.68 |  |  | 30 | 70 | 400 | 12000 | 288 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/26/2020 | 01:15 | 01:34 | 0.31667 | 12034 | 12129 | 95 | Rotate |  | 12059 | 90.9 | 338.2 | 10481.75 | 398.83 | 533.8 | 398.83 | 0.45 |  |  | 30 | 70 | 400 | 12000 | 300 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/26/2020 | 01:39 | 01:45 | 0.1 | 12129 | 12139 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 100 | 4700 | 3700 | 1000 | 275 | 260 | 200 | 180
07/26/2020 | 01:45 | 02:25 | 0.66667 | 12139 | 12154 | 15 | Slide | 0 | 12154 | 92.3 | 335.7 | 10479.1 | 486.21 | 496.63 | 486.21 | 3.02 |  |  | 30 | 70 | 400 | 15500 | 22.5 | 4700 | 3700 | 1000 | 275 | 240 | 200 | 180
07/26/2020 | 02:25 | 02:41 | 0.26667 | 12154 | 12224 | 70 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 262.5 | 4700 | 3700 | 1000 | 285 | 240 | 200 | 180
07/26/2020 | 02:46 | 03:10 | 0.4 | 12224 | 12319 | 95 | Rotate |  | 12249 | 93.5 | 334.2 | 10474.29 | 572.16 | 456.46 | 572.16 | 2.02 |  |  | 30 | 70 | 400 | 15500 | 237.5 | 4700 | 3700 | 1000 | 285 | 240 | 200 | 180
07/26/2020 | 03:15 | 03:20 | 0.083333 | 12319 | 12342 | 23 | Rotate |  | 12342 | 94.5 | 334.6 | 10467.8 | 655.82 | 416.37 | 655.82 | 1.16 |  |  | 30 | 70 | 400 | 15500 | 276 | 4700 | 3700 | 1000 | 285 | 240 | 200 | 180
07/26/2020 | 04:05 | 04:50 | 0.75 | 12342 | 12413 | 71 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 94.67 | 4700 | 3700 | 1000 | 285 | 240 | 200 | 180

## BHA_4_Lateral_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 Lateral |  |  |  |  | RKB: |  |  |  | 367 |  | North Reference: |  | GRID |  | Total Drilled: |  | 407
Site: |  |  |  |  | Dietz-Palo-Acadia - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 43
Well Name: |  |  |  |  | Dietz 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 73.00 / 63.00 |  |  |  |  | Grid Conv: |  |  |  | 367 |  | VS Azimuth: |  | 336.31 |  | Rotate: |  | 364
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/27/2020 | 04:05 | 04:15 | 0.16667 | 12413 | 12425 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 72 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 04:15 | 04:50 | 0.58333 | 12425 | 12436 | 11 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 18.86 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 05:20 | 06:10 | 0.83333 | 12436 | 12443 | 7 | Slide | 0 | 12437 | 92.4 | 336.3 | 10462.08 | 742.07 | 376.98 | 742.07 | 2.84 |  |  | 30 |  | 390 |  | 8.4 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 06:10 | 06:35 | 0.41667 | 12443 | 12510 | 67 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 160.8 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 06:40 | 07:18 | 0.63333 | 12510 | 12604 | 94 | Rotate |  | 12531 | 92.2 | 334.8 | 10458.31 | 827.57 | 338.1 | 827.57 | 1.61 |  |  | 30 | 70 | 390 | 16000 | 148.42 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 07:30 | 08:15 | 0.75 | 12604 | 12698 | 94 | Rotate |  | 12625 | 94 | 334.5 | 10453.23 | 912.39 | 297.92 | 912.39 | 1.94 |  |  | 30 | 70 | 390 | 16000 | 125.33 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 08:20 | 08:31 | 0.18333 | 12698 | 12715 | 17 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 92.73 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 08:31 | 09:22 | 0.85 | 12715 | 12725 | 10 | Slide | 0 | 12722 | 94.1 | 335.2 | 10446.38 | 999.97 | 256.8 | 999.97 | 0.73 |  |  | 30 |  | 390 | 16000 | 11.76 | 4300 | 3600 | 700 | 159 | 320 | 185
07/27/2020 | 09:22 | 09:53 | 0.51667 | 12725 | 12805 | 80 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 154.84 | 4300 | 3600 | 700 | 159 | 320 | 185
07/28/2020 | 23:35 | 24:00 | 0.41667 | 12805 | 12820 | 15 | Slide | 0 | 12818 | 89.9 | 335.2 | 10443.03 | 1087.05 | 216.56 | 1087.05 | 4.37 |  |  | 30 |  | 390 | 16000 | 36 | 4300 | 3600 | 700 | 174 | 320 | 185

## BHA_5_Lateral_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 (Lateral) |  |  |  |  | RKB: |  |  |  | 367 |  | North Reference: |  | GRID |  | Total Drilled: |  | 5021
Site: |  |  |  |  | Dietz-Palo-Acadia - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 394
Well Name: |  |  |  |  | Dietz 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 73.00 / 63.00 |  |  |  |  | Grid Conv: |  |  |  | 367 |  | VS Azimuth: |  | 336.31 |  | Rotate: |  | 4627
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/29/2020 | 20:15 | 20:58 | 0.71667 | 12820 | 12891 | 71 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 99.07 | 3800 | 3150 | 650 | 190 | 310 | 225 | 165
07/29/2020 | 21:03 | 21:20 | 0.28333 | 12891 | 12929 | 38 | Rotate |  | 12914 | 87.8 | 334.3 | 10444.96 | 1173.85 | 175.62 | 1173.85 | 2.38 |  |  | 32000 | 70 | 338 | 14.5 | 134.12 | 3800 | 3150 | 650 | 190 | 310 | 225 | 165
07/29/2020 | 21:20 | 22:00 | 0.66667 | 12929 | 12950 | 21 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 31.5 | 3800 | 3150 | 650 | 132 | 310 | 225 | 165
07/29/2020 | 22:00 | 22:25 | 0.41667 | 12950 | 12987 | 37 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 88.8 | 3800 | 3150 | 650 | 132 | 310 | 225 | 165
07/29/2020 | 22:30 | 23:17 | 0.78333 | 12987 | 13000 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 16.6 | 3800 | 3150 | 650 | 132 | 310 | 225 | 165
07/29/2020 | 23:17 | 23:40 | 0.38333 | 13000 | 13016 | 16 | Rotate |  | 13009 | 92.3 | 334.8 | 10444.87 | 1259.61 | 134.81 | 1259.61 | 4.77 |  |  | 32000 | 70 | 338 | 14.5 | 41.74 | 3800 | 3150 | 650 | 140 | 310 | 225 | 165
07/29/2020 | 23:40 | 24:00 | 0.33333 | 13016 | 13032 | 16 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 48 | 3800 | 3150 | 650 | 140 | 310 | 225 | 165
07/30/2020 | 00:00 | 00:45 | 0.75 | 13032 | 13048 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 21.33 | 3800 | 3150 | 650 | 134 | 310 | 225 | 165
07/30/2020 | 00:45 | 01:09 | 0.4 | 13048 | 13082 | 34 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 85 | 3800 | 3150 | 650 | 134 | 310 | 225 | 165
07/30/2020 | 01:14 | 02:14 | 1 | 13082 | 13177 | 95 | Rotate |  | 13104 | 94.8 | 336.8 | 10438.99 | 1346.08 | 95.94 | 1346.08 | 3.37 |  |  | 32000 | 70 | 338 | 14.5 | 95 | 3800 | 3150 | 650 | 143 | 310 | 225 | 165
07/30/2020 | 02:19 | 03:15 | 0.93333 | 13177 | 13272 | 95 | Rotate |  | 13199 | 95.4 | 336.2 | 10430.54 | 1432.86 | 58.21 | 1432.86 | 0.89 |  |  | 32000 | 70 | 338 | 14.5 | 101.79 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 03:20 | 03:30 | 0.16667 | 13272 | 13278 | 6 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 36 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 03:30 | 03:43 | 0.21667 | 13278 | 13284 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 14.5; Drilling Parameters ROP: 27.69 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 03:43 | 04:28 | 0.75 | 13284 | 13367 | 83 | Rotate |  | 13294 | 94.9 | 336.4 | 10422.02 | 1519.5 | 20.18 | 1519.5 | 0.57 |  |  | 32000 | 70 | 338 | 14.5 | 110.67 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 04:33 | 05:35 | 1.0333 | 13367 | 13463 | 96 | Rotate |  | 13390 | 95.3 | 335.8 | 10413.48 | 1606.92 | -18.56 | 1606.92 | 0.75 |  |  | 32000 | 70 | 338 | 14.5 | 92.9 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 05:40 | 07:06 | 1.4333 | 13463 | 13558 | 95 | Rotate |  | 13485 | 95.6 | 335.2 | 10404.46 | 1692.97 | -57.77 | 1692.97 | 0.7 |  |  | 32000 | 70 | 338 | 14.5 | 66.28 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 07:12 | 08:37 | 1.4167 | 13558 | 13635 | 77 | Rotate |  | 13580 | 96.4 | 334.9 | 10394.53 | 1778.63 | -97.63 | 1778.63 | 0.9 |  |  | 32000 | 70 | 338 | 14.5 | 54.35 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 08:37 | 09:10 | 0.55 | 13635 | 13645 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 18.18 | 3800 | 3150 | 650 | 138 | 310 | 225 | 165
07/30/2020 | 10:00 | 10:16 | 0.26667 | 13645 | 13653 | 8 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 30 | 3800 | 3150 | 650 | 142 | 310 | 225 | 165
07/30/2020 | 10:21 | 11:17 | 0.93333 | 13653 | 13749 | 96 | Rotate |  | 13676 | 95.3 | 335.2 | 10384.75 | 1865.22 | -137.91 | 1865.22 | 1.19 |  |  | 32000 | 70 | 338 | 15000 | 102.86 | 3800 | 3150 | 650 | 142 | 310 | 225 | 165
07/30/2020 | 11:22 | 11:44 | 0.36667 | 13749 | 13790 | 41 | Rotate |  | 13771 | 96.6 | 335 | 10374.9 | 1950.92 | -177.69 | 1950.92 | 1.38 |  |  | 32000 | 70 | 338 | 15000 | 111.82 | 3800 | 3150 | 650 | 142 | 310 | 225 | 165
07/30/2020 | 11:44 | 12:37 | 0.88333 | 13790 | 13807 | 17 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 19.25 | 3800 | 3150 | 650 | 145 | 310 | 225 | 165
07/30/2020 | 12:37 | 12:58 | 0.35 | 13807 | 13844 | 37 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 105.71 | 3800 | 3150 | 650 | 145 | 310 | 225 | 165
07/30/2020 | 13:03 | 13:12 | 0.15 | 13844 | 13859 | 15 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 100 | 3800 | 3150 | 650 | 148 | 310 | 225 | 165
07/30/2020 | 13:12 | 13:48 | 0.6 | 13859 | 13871 | 12 | Slide | 0 | 13866 | 92.7 | 336.8 | 10367.2 | 2037.34 | -216.34 | 2037.34 | 4.52 |  |  | 32000 |  | 338 |  | 20 | 3800 | 3150 | 650 | 148 | 310 | 225 | 165
07/30/2020 | 13:48 | 14:20 | 0.53333 | 13871 | 13939 | 68 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 127.5 | 3800 | 3150 | 650 | 148 | 310 | 225 | 165
07/30/2020 | 14:35 | 15:25 | 0.83333 | 13939 | 14034 | 95 | Rotate |  | 13961 | 92.2 | 336.5 | 10363.14 | 2124.48 | -253.96 | 2124.48 | 0.61 |  |  | 32000 | 70 | 338 | 15000 | 114 | 3800 | 3150 | 650 | 149 | 310 | 225 | 165
07/30/2020 | 15:45 | 16:42 | 0.95 | 14034 | 14128 | 94 | Rotate |  | 14055 | 92.3 | 336.7 | 10359.45 | 2210.68 | -291.26 | 2210.68 | 0.24 |  |  | 32000 | 70 | 338 | 15000 | 98.95 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 17:35 | 18:21 | 0.76667 | 14128 | 14223 | 95 | Rotate |  | 14150 | 92.8 | 335.7 | 10355.22 | 2297.51 | -329.56 | 2297.51 | 1.18 |  |  | 32000 | 70 | 338 | 15000 | 123.91 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 18:26 | 18:45 | 0.31667 | 14223 | 14230 | 7 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 22.11 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 18:45 | 19:10 | 0.41667 | 14230 | 14237 | 7 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 16.8 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 19:10 | 19:50 | 0.66667 | 14237 | 14318 | 81 | Rotate |  | 14245 | 91.5 | 335.9 | 10351.66 | 2384.1 | -368.48 | 2384.1 | 1.38 |  |  | 32000 | 70 | 338 | 15000 | 121.5 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 19:55 | 20:48 | 0.88333 | 14318 | 14413 | 95 | Rotate |  | 14340 | 91.7 | 335.5 | 10349 | 2470.65 | -407.56 | 2470.65 | 0.47 |  |  | 32000 | 70 | 338 | 15000 | 107.55 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 20:53 | 21:20 | 0.45 | 14413 | 14453 | 40 | Rotate |  | 14435 | 91.9 | 335 | 10346.02 | 2556.88 | -447.31 | 2556.88 | 0.57 |  |  | 32000 | 70 | 338 | 15000 | 88.89 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 21:20 | 21:49 | 0.48333 | 14453 | 14465 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 24.83 | 3800 | 3150 | 650 | 161 | 310 | 225 | 165
07/30/2020 | 21:49 | 22:15 | 0.43333 | 14465 | 14508 | 43 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 99.23 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/30/2020 | 22:20 | 23:20 | 1 | 14508 | 14603 | 95 | Rotate |  | 14530 | 94.2 | 335.9 | 10340.96 | 2643.16 | -486.72 | 2643.16 | 2.6 |  |  | 32000 | 70 | 338 | 15000 | 95 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/30/2020 | 23:25 | 23:50 | 0.41667 | 14603 | 14653 | 50 | Rotate |  | 14624 | 95.5 | 335.7 | 10333.02 | 2728.6 | -525.12 | 2728.6 | 1.4 |  |  | 32000 | 70 | 338 | 15000 | 120 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/30/2020 | 23:50 | 24:00 | 0.16667 | 14653 | 14659 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 36 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 00:00 | 00:37 | 0.61667 | 14659 | 14697 | 38 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 61.62 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 00:42 | 01:28 | 0.76667 | 14697 | 14792 | 95 | Rotate |  | 14719 | 94.4 | 336 | 10324.82 | 2814.96 | -563.84 | 2814.96 | 1.2 |  |  | 32000 | 70 | 338 | 15000 | 123.91 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 01:32 | 02:00 | 0.46667 | 14792 | 14820 | 28 | Rotate |  | 14815 | 95.3 | 335.9 | 10316.7 | 2902.31 | -602.82 | 2902.31 | 0.94 |  |  | 32000 | 70 | 338 | 15000 | 60 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 02:00 | 02:14 | 0.23333 | 14820 | 14826 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 25.71 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 02:14 | 02:43 | 0.48333 | 14826 | 14888 | 62 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 128.28 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 02:48 | 03:40 | 0.86667 | 14888 | 14983 | 95 | Rotate |  | 14910 | 94.8 | 336.5 | 10308.34 | 2988.89 | -641.01 | 2988.89 | 0.82 |  |  | 32000 | 70 | 338 | 15000 | 109.62 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 03:45 | 05:16 | 1.5167 | 14983 | 14998 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 9.89 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 05:16 | 06:04 | 0.8 | 14998 | 15078 | 80 | Rotate |  | 15005 | 93.6 | 336.9 | 10301.38 | 3075.91 | -678.48 | 3075.91 | 1.33 |  |  | 32000 | 70 | 338 | 15000 | 100 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 06:30 | 08:02 | 1.5333 | 15078 | 15110 | 32 | Slide | 0 | 15100 | 88.9 | 335.4 | 10299.31 | 3162.75 | -716.87 | 3162.75 | 5.19 |  |  | 32000 |  | 338 |  | 20.87 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 08:02 | 08:30 | 0.46667 | 15110 | 15173 | 63 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 135 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 09:05 | 09:53 | 0.8 | 15173 | 15267 | 94 | Rotate |  | 15194 | 87.3 | 335.3 | 10302.43 | 3248.13 | -756.06 | 3248.13 | 1.71 |  |  | 32000 | 70 | 338 | 15000 | 117.5 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 10:00 | 11:30 | 1.5 | 15267 | 15294 | 27 | Slide | 0 | 15289 | 89.5 | 336.3 | 10305.08 | 3334.74 | -794.98 | 3334.74 | 2.54 |  |  | 32000 |  | 338 |  | 18 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 11:30 | 12:06 | 0.6 | 15294 | 15362 | 68 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 113.33 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 12:20 | 13:05 | 0.75 | 15362 | 15374 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 16 | 3800 | 3150 | 650 | 165 | 310 | 225 | 165
07/31/2020 | 13:05 | 13:45 | 0.66667 | 15374 | 15456 | 82 | Rotate |  | 15383 | 91.7 | 338.1 | 10304.1 | 3421.38 | -831.4 | 3421.38 | 3.02 |  |  | 32000 | 70 | 338 | 15000 | 123 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 13:55 | 14:35 | 0.66667 | 15456 | 15557 | 101 | Rotate |  | 15478 | 92.2 | 337.2 | 10300.86 | 3509.2 | -867.51 | 3509.2 | 1.08 |  |  | 32000 | 70 | 338 | 15000 | 151.5 | 3800 | 3150 | 650 | 170 | 310 | 225 | 165
07/31/2020 | 14:45 | 15:18 | 0.55 | 15557 | 15645 | 88 | Rotate |  | 15572 | 92.8 | 336.5 | 10296.76 | 3595.54 | -904.42 | 3595.54 | 0.98 |  |  | 32000 | 70 | 338 | 15000 | 160 | 3800 | 3150 | 650 | 174 | 310 | 225 | 165
07/31/2020 | 15:30 | 16:14 | 0.73333 | 15645 | 15657 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 16.36 | 3800 | 3150 | 650 | 174 | 310 | 225 | 165
07/31/2020 | 16:14 | 16:52 | 0.63333 | 15657 | 15740 | 83 | Rotate |  | 15667 | 91.5 | 337.4 | 10293.2 | 3682.89 | -941.59 | 3682.89 | 1.66 |  |  | 32000 | 70 | 338 | 15000 | 131.05 | 3800 | 3150 | 650 | 174 | 310 | 225 | 165
07/31/2020 | 17:40 | 18:33 | 0.88333 | 15740 | 15834 | 94 | Rotate |  | 15761 | 91 | 336.8 | 10291.15 | 3769.46 | -978.16 | 3769.46 | 0.83 |  |  | 32000 | 70 | 338 | 15000 | 106.42 | 3800 | 3150 | 650 | 167 | 310 | 225 | 165
07/31/2020 | 18:38 | 19:05 | 0.45 | 15834 | 15890 | 56 | Rotate |  | 15855 | 90.9 | 336.3 | 10289.59 | 3855.69 | -1015.56 | 3855.69 | 0.54 |  |  | 32000 | 70 | 338 | 15000 | 124.44 | 4000 | 3300 | 700 | 167 | 330 | 225 | 165
07/31/2020 | 19:05 | 19:47 | 0.7 | 15890 | 15902 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 17.14 | 4000 | 3300 | 700 | 167 | 330 | 225 | 165
07/31/2020 | 19:47 | 20:04 | 0.28333 | 15902 | 15928 | 26 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 91.76 | 4000 | 3300 | 700 | 167 | 330 | 225 | 165
07/31/2020 | 20:09 | 20:38 | 0.48333 | 15928 | 15988 | 60 | Rotate |  | 15950 | 93.2 | 335.2 | 10286.19 | 3942.24 | -1054.55 | 3942.24 | 2.68 |  |  | 32000 | 70 | 338 | 15000 | 124.14 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
07/31/2020 | 20:38 | 20:56 | 0.3 | 15988 | 15994 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 20 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
07/31/2020 | 20:56 | 21:14 | 0.3 | 15994 | 16023 | 29 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 96.67 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
07/31/2020 | 21:19 | 22:05 | 0.76667 | 16023 | 16117 | 94 | Rotate |  | 16044 | 94.9 | 334.9 | 10279.55 | 4027.26 | -1094.1 | 4027.26 | 1.84 |  |  | 32000 | 70 | 338 | 15000 | 122.61 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
07/31/2020 | 22:10 | 22:15 | 0.083333 | 16117 | 16123 | 6 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 72 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
07/31/2020 | 22:15 | 23:10 | 0.91667 | 16123 | 16139 | 16 | Slide | 0 | 16139 | 94.3 | 336.3 | 10271.93 | 4113.49 | -1133.22 | 4113.49 | 1.6 |  |  | 32000 |  | 338 |  | 17.45 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
07/31/2020 | 23:10 | 23:41 | 0.51667 | 16139 | 16212 | 73 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 141.29 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
08/01/2020 | 01:05 | 02:04 | 0.98333 | 16212 | 16238 | 26 | Slide | 0 | 16234 | 92 | 336.6 | 10266.71 | 4200.44 | -1171.12 | 4200.44 | 2.44 |  |  | 32000 |  | 338 |  | 26.44 | 4000 | 3300 | 700 | 179 | 330 | 225 | 165
08/01/2020 | 02:04 | 02:50 | 0.76667 | 16238 | 16307 | 69 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 90 | 4000 | 3300 | 700 | 179 | 330 | 225 | 165
08/01/2020 | 02:55 | 03:29 | 0.56667 | 16307 | 16327 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338; Drilling Parameters ROP: 35.29 | 4000 | 3300 | 700 | 179 | 330 | 225 | 165
08/01/2020 | 03:29 | 04:13 | 0.73333 | 16327 | 16402 | 75 | Rotate |  | 16329 | 89 | 337.2 | 10265.88 | 4287.81 | -1208.38 | 4287.81 | 3.22 |  |  | 32000 | 70 | 338 | 15000 | 102.27 | 4000 | 3300 | 700 | 179 | 330 | 225 | 165
08/01/2020 | 04:13 | 05:33 | 1.3333 | 16402 | 16432 | 30 | Slide | 0 | 16423 | 90.9 | 337.7 | 10265.97 | 4374.62 | -1244.43 | 4374.62 | 2.09 |  |  | 32000 |  | 338 |  | 22.5 | 4000 | 3300 | 700 | 179 | 330 | 225 | 165
08/01/2020 | 05:33 | 06:02 | 0.48333 | 16432 | 16496 | 64 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 132.41 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
08/01/2020 | 06:10 | 06:43 | 0.55 | 16496 | 16593 | 97 | Rotate |  | 16520 | 92 | 337.3 | 10263.51 | 4464.2 | -1281.54 | 4464.2 | 1.21 |  |  | 32000 | 70 | 338 | 15000 | 176.36 | 4000 | 3300 | 700 | 170 | 330 | 225 | 165
08/01/2020 | 06:49 | 07:25 | 0.6 | 16593 | 16687 | 94 | Rotate |  | 16614 | 92.7 | 337.3 | 10259.66 | 4550.85 | -1317.78 | 4550.85 | 0.74 |  |  | 32000 | 70 | 338 | 15000 | 156.67 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 07:30 | 08:02 | 0.53333 | 16687 | 16782 | 95 | Rotate |  | 16709 | 94 | 337 | 10254.11 | 4638.24 | -1354.61 | 4638.24 | 1.4 |  |  | 32000 | 70 | 338 | 15000 | 178.13 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 08:09 | 08:36 | 0.45 | 16782 | 16845 | 63 | Rotate |  | 16803 | 95.4 | 336.8 | 10246.4 | 4724.41 | -1391.36 | 4724.41 | 1.5 |  |  | 32000 | 70 | 338 | 15000 | 140 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 08:36 | 08:36 | 0 | 16845 | 16865 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 32000; Drilling Parameters FLOW: 338 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 08:36 | 09:40 | 1.0667 | 16865 | 16876 | 11 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 10.31 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 09:45 | 10:18 | 0.55 | 16876 | 16972 | 96 | Rotate |  | 16899 | 93 | 337.6 | 10239.37 | 4812.67 | -1428.46 | 4812.67 | 2.63 |  |  | 32000 | 70 | 338 | 15000 | 174.55 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 10:24 | 11:05 | 0.68333 | 16972 | 17066 | 94 | Rotate |  | 16993 | 93.9 | 337.8 | 10233.72 | 4899.48 | -1464.06 | 4899.48 | 0.98 |  |  | 32000 | 70 | 338 | 15000 | 137.56 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 11:10 | 11:57 | 0.78333 | 17066 | 17161 | 95 | Rotate |  | 17087 | 95.1 | 337.9 | 10226.34 | 4986.27 | -1499.4 | 4986.27 | 1.28 |  |  | 32000 | 70 | 338 | 15000 | 121.28 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 12:13 | 13:05 | 0.86667 | 17161 | 17181 | 20 | Slide | 0 | 17181 | 92.8 | 337.4 | 10219.87 | 5073 | -1535.05 | 5073 | 2.5 |  |  | 32000 |  | 338 |  | 23.08 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 13:05 | 13:37 | 0.53333 | 17181 | 17254 | 73 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 136.88 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 13:44 | 14:20 | 0.6 | 17254 | 17349 | 95 | Rotate |  | 17276 | 93 | 339.2 | 10215.06 | 5161.15 | -1570.13 | 5161.15 | 1.9 |  |  | 32000 | 70 | 338 | 15000 | 158.33 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 14:27 | 14:32 | 0.083333 | 17349 | 17355 | 6 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 72 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 14:32 | 15:22 | 0.83333 | 17355 | 17375 | 20 | Slide | 0 | 17370 | 90.4 | 337.2 | 10212.27 | 5248.37 | -1605.02 | 5248.37 | 3.49 |  |  | 32000 |  | 338 |  | 24 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 15:22 | 15:55 | 0.55 | 17375 | 17443 | 68 | Rotate | Drilling Parameters WOB: 32000; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 338; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 123.64 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 16:00 | 16:40 | 0.66667 | 17443 | 17537 | 94 | Rotate |  | 17464 | 90.6 | 336 | 10211.45 | 5334.64 | -1642.35 | 5334.64 | 1.29 |  |  | 32000 | 70 | 338 | 15000 | 141 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 17:24 | 17:55 | 0.51667 | 17537 | 17631 | 94 | Rotate |  | 17558 | 90.9 | 335.8 | 10210.22 | 5420.44 | -1680.73 | 5420.44 | 0.38 |  |  | 32000 | 70 | 338 | 15000 | 181.94 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 18:00 | 18:30 | 0.5 | 17631 | 17726 | 95 | Rotate |  | 17653 | 91.3 | 335.6 | 10208.4 | 5507 | -1719.82 | 5507 | 0.47 |  |  | 32000 | 70 | 338 | 15000 | 190 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 18:35 | 19:10 | 0.58333 | 17726 | 17820 | 94 | Rotate |  | 17747 | 92 | 336 | 10205.69 | 5592.71 | -1758.34 | 5592.71 | 0.86 |  |  | 32000 | 70 | 338 | 15000 | 161.14 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165
08/01/2020 | 19:15 | 19:25 | 0.16667 | 17820 | 17841 | 21 | Rotate |  | 17841 | 92 | 336 | 10202.41 | 5678.53 | -1796.55 | 5678.53 | 0 |  |  | 32000 | 70 | 338 | 15000 | 126 | 4000 | 3300 | 700 | 154 | 330 | 225 | 165