## Summary
Magnolia Oil & Gas / Fat Tire A1H / LTX1150620 / Patterson 248
Report Date: | 12/27/2020 | Current Depth: | 17167
Start Date: | 12/09/2020 | Casing Depth: | 3098
Daily Cost: | 4800 | Distance to TD:
Well Cost: | 125200 | Average ROP: | 0
Drilling Hours: | 0 | Svy MD: | 17167
24Hr Forcast: | EOW | Svy Inc: | 95.82
Current BHA: |  | Svy Azi: | 331.72
Current BRT Hrs: | 0 | Svy TVD: | 10119.67
Bit Make / Model: |  | Svy NS: | 5552.65
POOH in last 24Hrs: | No | Svy EW: | -4261.42
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Nathan Marks | MWD Day: | Jeff Cambpell
Directional Driller Night: | Billy Mcfarland | MWD Night: | Ramon Ries
RSS Engineer 1: |  | Third Man:
RSS Engineer 2: |  | Fourth Man:
Principal Plan: |  | Max BHT Well: | 304
24Hr Summary: | Standby for Casing and Cement Ops; Skid Rig t/ B1H; EOW | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
PPM250022 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  | Dirty |  | 80.43 | 80.43
PPM250025 | 5 1/2, - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  | Clean
PPM250020 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  | Clean
PPM250001 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HT89 +.012 |  |  | Clean
MTR475035 | 5 1/2, - 7/8, 3.8 Stg. @ 2.50? Slick- HPW -.004 |  |  | Clean
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
ZSB775224 | UBHO Sub |  |  | Clean
ZSB775202 | UBHO Sub |  |  | Dirty |  | 30.68 | 30.68
ZSB500016 | UBHO Sub |  |  | Dirty |  | 80.43 | 80.43
ZSB500025 | UBHO Sub |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33515 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Fat Tire A1H
|  |  |  | County: |  | Fayette |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Total Drilled (Usft): |  | 17062 |  |  | Total Days: |  | 14
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 105 | 3105 | 3000 |  | 750 |  | 7.33 | 4 | 5.17 | 10
2 | 2 | 9.875 | 3105 | 9937 | 6832 |  | 279.43 |  | 7.14 | 24.45 | 25.52 | 46.33
3 | 3 | 6.75 | 9937 | 17167 | 7230 |  | 116.14 |  | 15.7 | 62.25 | 80.43 | 118.33
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | New |  | 0-0-NO-I-TD |  | 1.353 | 3000 | 4 | 750
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 0-1-NO-A-X-I-NO-TD |  | 1.491 | 6832 | 24.45 | 279.43
3 | Halliburton |  | GTD64M |  | 6.75 | New |  | 2-1-BT-N-X-1/16-CT-TD |  | 1.491 | 7230 | 62.25 | 116.14
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 1.5 | 5.45 | 3000 |  | 750
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 2 | 5.81 | 6832 |  | 279.43
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5 | 2.12 | 4.08 | 7230 |  | 116.14
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Nathan Marks |  | Billy Mcfarland |  | Jeff Cambpell |  | Jeff Cambpell |  | James Dyer |  | Jim |  | David Leblanc
|  |  |  | Russell Arnold |  | Ramon Ries
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.63 / 0.29 |  | 3000 |  | 742.57 |  | 0.00 / 5.50 |  | 1 |  | 4.04
INT: INTERMEDIATE |  |  | 4.00 / 1.26 |  | 6832 |  | 279.54 |  | 0.00 / 22.08 |  | 1 |  | 24.44
CRV: CURVE |  |  | 0.52 / 0.51 |  | 1041 |  | 97.11 |  |  |  | 1 |  | 10.72
INT2: INTERMEDIATE 2 |  |  | 1.01 / 0.01 |  | 10 |  | 50 |  |  |  | 1 |  | 0.2
LAT: LATERAL |  |  | 5.47 / 2.89 |  | 6179 |  | 120.4 |  |  |  | 1 |  | 51.32
Total |  |  | 13.62 |  | 17062 |  | 188.07 |  | 0.00 / 27.58 |  | 3 |  | 90.72
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA #1 (Surface) |  |  | 105.00 | 3105.00 | 874.21 | 2780.00 | 255.81 | 220.00 | 7.33 | 3000.00 | 742.57 | 4.04 | 0.86
INT: INTERMEDIATE-BHA #2 (Intermediate) |  |  | 3105.00 | 9937.00 | 462.73 | 6344.00 | 45.48 | 488.00 | 7.14 | 6832.00 | 279.54 | 24.44 | 10.73
CRV: CURVE-BHA #3 (Curve and Lateral) |  |  | 9947.00 | 10988.00 | 131.52 | 338.00 | 86.26 | 703.00 | 67.53 | 1041.00 | 97.11 | 10.72 | 8.15
INT2: INTERMEDIATE 2-BHA #3 (Curve and Lateral) |  |  | 9937.00 | 9947.00 | 50.00 | 10.00 | 0.00 | 0.00 | 0.00 | 10.00 | 50.00 | 0.20 | 0.00
LAT: LATERAL-BHA #3 (Curve and Lateral) |  |  | 10988.00 | 17167.00 | 171.45 | 5747.00 | 24.27 | 432.00 | 6.99 | 6179.00 | 120.40 | 51.32 | 17.80
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1150620 | Total Drilled(Usft) | 17062.00
Operator | Magnolia Oil & Gas | Drilling Hours | 90.70
Well Name | Fat Tire A1H | Avg ROP(Usft/hr) | 188.11
Rig | Patterson 248 | Rotary Drilled(Usft) | 15219.00
State | Texas | Rotary Hours | 53.15
County | Fayette | Rotary ROP(Usft/hr) | 286.34
Formation | Austin Chalk | Rotary % | 89.20
Start Date | 12/09/2020 | Slide Drilled(Usft) | 1843.00
End Date | 12/27/2020 | Slide Hours | 37.55
Days On Well | 14 | Slide ROP(Usft/hr) | 49.08
Start Depth (Usft) | 105.00 | Slide % | 10.80
End Depth (Usft) | 17167.00
Total Drilled (Usft) | 17062.00
# BHA's | 3
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 2.28 / 27.58
Phase Data
Phase | SUR | INT | INT2 | CRV | LAT
Start Date | 12/09/2020 | 12/17/2020 | 12/21/2020 | 12/22/2020 | 12/22/2020
End Date | 12/11/2020 | 12/20/2020 | 12/22/2020 | 12/22/2020 | 12/27/2020
Total Days | 2.63 | 4.00 | 1.01 | 0.52 | 5.47
Start Depth (Usft) | 105.00 | 3105.00 | 9937.00 | 9947.00 | 10988.00
End Depth (Usft) | 3105.00 | 9937.00 | 9947.00 | 10988.00 | 17167.00
Total Drilled(Usft) | 3000.00 | 6832.00 | 10.00 | 1041.00 | 6179.00
Drilling Hours | 4.00 | 24.45 | 0.20 | 10.72 | 51.33
Circulating Hours | 1.17 | 1.07 | 1.58 | 0.00 | 16.60
Total D&C Hours | 5.17 | 25.52 | 1.78 | 10.72 | 67.93
Avg ROP(Usft/hr) | 750.00 | 279.43 | 50.00 | 97.14 | 120.37
Rotary Drilled(Usft) | 2780.00 | 6344.00 | 10.00 | 338.00 | 5747.00
Rotary Hours | 3.15 | 13.72 | 0.20 | 2.57 | 33.52
Rotary ROP(Usft/hr) | 882.54 | 462.50 | 50.00 | 131.69 | 171.47
Rotary % | 92.67 | 92.86 | 100.00 | 32.47 | 93.01
Slide Drilled(Usft) | 220.00 | 488.00 | 0.00 | 703.00 | 432.00
Slide Hours | 0.85 | 10.73 | 0.00 | 8.15 | 17.82
Slide ROP(Usft/hr) | 258.82 | 45.47 | 0.00 | 86.26 | 24.25
Slide % | 7.33 | 7.14 | 0.00 | 67.53 | 6.99
# BHA | 1 | 1 | 1 | 1 | 1
# Motor Failures | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 5.50 | 0.00 / 22.08 | 1.25 / 0.00 | 0.00 / 0.00 | 1.03 / 0.00
Total Phase Hrs | 7.00 | 30.27 | 0.25 | 12.25 | 69.25
Phase ROP (Usft/hr) | 428.57 | 225.73 | 40.00 | 84.98 | 89.23
Avg Motor Yield (°/100ft) | 7.53 | 10.90 | 0.00 | 15.43 | 21.56
Avg Rotary DLS (°/100ft) | 0.30 | 0.42 | 0.00 | 0.00 | 0.94
Avg Rotary TF | -176.38 | -164.05 | 0.00 | 0.00 | 13.28
Avg Slide Length (Usft) | 24.44 | 24.00 | 0.00 | 63.91 | 16.62
# Slides | 9 | 20 | 0 | 11 | 26
BHA Data
BHA# | 1 | 2 | 3
Description | BHA #1 (Surface) | BHA #2 (Intermediate) | BHA #3 (Curve and Lateral)
Bit Size | 13.500 | 9.875 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491
Grade In | New | New | New
Grade Out | 0-0-NO-I-TD | 0-1-NO-A-X-I-NO-TD | 2-1-BT-N-X-1/16-CT-TD
Motor SN | PPM800004 | PPM800065 | PPM250022
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.90 | 7/8 / 5.90 | 6/7 / 8.80
WOB (klbs) | 3.00 / 14.76 / 20.00 | 12.00 / 35.94 / 42.00 | 20.00 / 45.36 / 80.00
Diff P (psi) | 45.00 / 364.80 / 700.00 | 200.00 / 749.10 / 1000.00 | 100.00 / 893.41 / 1200.00
Bend | 1.500 | 2.000 | 2.120
Date In | 12/11/2020 | 12/17/2020 | 12/21/2020
Date Out | 12/11/2020 | 12/19/2020 | 12/26/2020
Time In | 08:30 | 23:10 | 08:00
Time Out | 18:30 | 21:30 | 06:20
BRT Hrs | 10.00 | 46.33 | 118.33
Start Depth (Usft) | 105.00 | 3105.00 | 9937.00
End Depth (Usft) | 3105.00 | 9937.00 | 17167.00
Total Drilled(Usft) | 3000.00 | 6832.00 | 7230.00
Drilling Hours | 4.00 | 24.45 | 62.25
Circulating Hours | 1.17 | 1.07 | 18.18
Total D&C Hours | 5.17 | 25.52 | 80.43
Avg ROP(Usft/hr) | 750.00 | 279.43 | 116.14
Rotary Drilled(Usft) | 2780.00 | 6344.00 | 6095.00
Rotary Hours | 3.15 | 13.72 | 36.28
Rotary ROP(Usft/hr) | 882.54 | 462.50 | 167.98
Rotary % | 92.67 | 92.86 | 84.30
Slide Drilled(Usft) | 220.00 | 488.00 | 1135.00
Slide Hours | 0.85 | 10.73 | 25.97
Slide ROP(Usft/hr) | 258.82 | 45.47 | 43.71
Slide % | 7.33 | 7.14 | 15.70
Motor Failure | NO | NO | NO
MWD Failure | NO | NO | NO
Unplanned Trip | NO | NO | NO
LIH | NO | NO | NO
Avg Motor Yield (°/100ft) | 7.53 | 10.90 | 18.31
Avg Rotary DLS (°/100ft) | 0.30 | 0.42 | 0.94
Avg Rotary TF | -176.38 | -164.05 | 13.28
Avg Slide Length (Usft) | 24.44 | 24.24 | 30.68
# Slides | 9 | 21 | 37

## Personnel Report
|  | Job # | LTX1150620 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-149-33515 |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Fat Tire A1H
|  | Date: | 12/27/2020 |  | State: |  | Texas
[5 empty] | County: |  | Fayette
Fat Tire A1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Billy Mcfarland | Night DD |  | 12/09/2020 - 00:00 | 12/11/2020 - 00:00 |  | 3.00 / 0.00
Billy Mcfarland | Night DD |  | 12/17/2020 - 00:00 | 12/27/2020 - 00:00 |  | 11.00 / 0.00
Jeff Cambpell | Day MWD |  | 12/22/2020 - 00:00 | 12/27/2020 - 00:00 |  | 6.00 / 0.00
Jeff Cambpell | Night MWD |  | 12/09/2020 - 00:00 | 12/11/2020 - 00:00 |  | 3.00 / 0.00
Jeff Cambpell | Night MWD |  | 12/17/2020 - 00:00 | 12/21/2020 - 00:00 |  | 5.00 / 0.00
Nathan Marks | Day DD |  | 12/09/2020 - 00:00 | 12/11/2020 - 00:00 |  | 3.00 / 0.00
Nathan Marks | Day DD |  | 12/17/2020 - 00:00 | 12/27/2020 - 00:00 |  | 11.00 / 0.00
Ramon Ries | Night MWD |  | 12/22/2020 - 00:00 | 12/27/2020 - 00:00 |  | 6.00 / 0.00
Russell Arnold | Day MWD |  | 12/09/2020 - 00:00 | 12/11/2020 - 00:00 |  | 3.00 / 0.00
Russell Arnold | Day MWD |  | 12/17/2020 - 00:00 | 12/21/2020 - 00:00 |  | 5.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1150620 | [5 empty] | State / County: |  |  |  | Texas / Fayette
|  |  |  | Well Name: |  |  | Fat Tire A1H | [7 empty] | Day DD: |  |  |  |  | Nathan Marks | [5 empty] | API #: |  |  |  | 42-149-33515
|  |  |  | AFE #: |  |  | 20DD0325MG | [7 empty] | Night DD: |  |  |  |  | Billy Mcfarland | [5 empty] | Company Man: |  |  |  | James Dyer
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Jeff Cambpell | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Ramon Ries | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 12/09/2020 | 12/10/2020 | 12/11/2020 | 12/12/2020 | 12/13/2020 | 12/14/2020 | 12/15/2020 | 12/16/2020 | 12/17/2020 | 12/18/2020 | 12/19/2020 | 12/20/2020 | 12/21/2020 | 12/22/2020 | 12/23/2020 | 12/24/2020 | 12/25/2020 | 12/26/2020 | 12/27/2020 | 12/28/2020 | 12/29/2020 | 12/30/2020 | 12/31/2020 | 01/01/2021 | 01/02/2021 | 01/03/2021 | 01/04/2021 | 01/05/2021 | 01/06/2021 | 01/07/2021 | 01/08/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 9.875 | 9 7/8- Ulterra SPL613-Jetted 6-14s & 3-16s |  | Steel | 54300 | 0 | 16 |  |  |  | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 9.875 | 9 7/8- Ulterra SPL613-Jetted 6-14s & 3-16s |  | Steel | 54317 | 3 | 13 | [6 empty] | O | O | X | X | X | O | O | O | O | O | O | O | O
Bit |  | 6.75 | 6 3/4- Halliburton GTD64M- Jetted 6-18s |  | Steel | 13446789 | 6 | 8 | [11 empty] | O | X | X | X | X | X | X | O
Cross Over |  |  | X/O- 4 1/2 IFB x 6 5/8 RegP |  | Steel | SD115520 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.563 | X/O- 4 1/2 IFB x 6 5/8 RegP |  | Steel | SD116862 | 1 | 10 |  | O | X | O | O | O | O | O | O | O | O
Cross Over |  | 6.5 | X/O- 4 1/2 XHB x 6 5/8 RegP |  | Steel | SD108685 | 3 | 10 |  | O | O | O | O | O | O | O | X | X | X
Cross Over |  |  | X/O- 4 1/2 XHB x 6 5/8 RegP |  | Steel | SD115530 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | X/O- 4 1/2 XHB x 4 1/2 IFP |  | Steel | SD112037 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | X/O- 4 1/2 XHB x 4 1/2 IFP |  | Steel | SD112109 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | X/O- 4 1/2 IFB x 4 1/2 XHP |  | Steel | SD117249 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.625 | X/O- 4 1/2 IFB x 4 1/2 XHP |  | Steel | SD4555 | 3 | 10 |  | O | O | O | O | O | O | O | X | X | X
Cross Over |  | 5.375 | X/O- DS42B x XT39P |  | Steel | SD119105 | 6 | 9 | [10 empty] | O | O | X | X | X | X | X | X | O
Cross Over |  |  | X/O- DS42B x XT39P |  | Steel | SD119310 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
MWD / LWD |  |  | UBHO Sub |  | Steel | ZSB775224 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO Sub |  | Steel | ZSB775202 | 4 | 10 |  | O | X | O | O | O | O | O | X | X | X
MWD / LWD |  | 5.125 | UBHO Sub |  | Steel | ZSB500016 | 6 | 18 |  | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | O
MWD / LWD |  |  | UBHO Sub |  | Steel | ZSB500025 | 0 | 18 |  | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 8 | 7 3/4 -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  | Steel | PPM800049 | 0 | 4 | [7 empty] | O | O | O | O
Motor |  | 8 | 7 3/4 -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 |  | Steel | PPM800065 | 3 | 4 | [7 empty] | O | X | X | X
Motor |  | 8 | 7 3/4 -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.022 |  | Steel | PPM800011 | 0 | 4 | [7 empty] | O | O | O | O
Motor |  | 5 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  | Steel | PPM250022 | 6 | 9 | [10 empty] | O | O | X | X | X | X | X | X | O
Motor |  | 5 | 5 1/2, - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  | Steel | PPM250025 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Motor |  |  | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  | Steel | PPM250020 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Motor |  |  | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HT89 +.012 |  | Steel | PPM250001 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Motor |  |  | 5 1/2, - 7/8, 3.8 Stg. @ 2.50? Slick- HPW -.004 |  | Steel | MTR475035 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Stab |  | 8.188 | 13 - 4 Blade Nortrak Stabilizer (BFF) |  | Steel | SD603913 | 1 | 10 |  | O | X | O | O | O | O | O | O | O | O
Stab |  |  | 13 - 4 Blade Nortrak Stabilizer (BFF) |  | Steel | SD610468 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Collar |  | 7.375 | 8 - NMDC |  | Non-Mag | SD50132 | 4 | 10 |  | O | X | O | O | O | O | O | X | X | X
Collar |  |  | 8 - NMDC |  | Non-Mag | SD55520 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Collar |  | 8 | 8 - NMDC |  | Non-Mag | SD55923 | 4 | 10 |  | O | X | O | O | O | O | O | X | X | X
Collar |  |  | 8 - NMDC |  | Non-Mag | SD56274 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Collar |  |  | 8 - NMPDC |  | Steel | SD45067 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Collar |  | 8 | 8 - NMPDC |  | Steel | SD52214 | 4 | 10 |  | O | X | O | O | O | O | O | X | X | X
Collar |  | 6.5 | 2 Stands of 6 1/2 Drill Collars |  | Steel | Rig-3 | 3 | 16 |  |  |  | O | O | O | O | O | X | X | X | O | O | O | O | O | O | O | O
Collar |  | 5 | 5 NMDC |  | Non-Mag | SD55955 | 6 | 9 | [10 empty] | O | O | X | X | X | X | X | X | O
Collar |  |  | 5 NMDC |  | Non-Mag | SD56281 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Collar |  |  | 5 NMDC |  | Non-Mag | SD56700 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5.063 | 5 NMDC |  | Non-Mag | SD56701 | 6 | 9 | [10 empty] | O | O | X | X | X | X | X | X | O
Collar |  |  | 5 NMDC |  | Non-Mag | SD56783 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Collar |  |  | 5 NMDC |  | Non-Mag | SD56785 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5.063 | 5 NMPDC |  | Steel | SD56679 | 6 | 9 | [10 empty] | O | O | X | X | X | X | X | X | O
Collar |  |  | 5 NMPDC |  | Steel | SD56870 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 5 | 22 Stands of Drill Pipe |  | Steel | Rig-2 | 0 | 16 |  |  |  | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 27 Stands of Drill Pipe |  | Steel | Rig2 | 0 | 8 | [11 empty] | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax Thruster |  | Steel | A52068 | 6 | 8 | [11 empty] | O | X | X | X | X | X | X | O
Sub |  |  | Float Sub |  | Steel | SD104003 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD105364 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD104878 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD108863 | 0 | 10 |  | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD115658 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119067 | 0 | 9 | [10 empty] | O | O | O | O | O | O | O | O | O
Sub |  | 5 | BTI Valve |  | Steel | Rig1x | 6 | 8 | [11 empty] | O | X | X | X | X | X | X | O
Agitator |  | 6.75 | NOV- Safety Join / Agitator / Shock Sub |  | Steel | AGHF0675-0062 | 0 | 16 |  |  |  | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator |  | 6.75 | NOV- Safety Join / Agitator / Shock Sub |  | Steel | AGHF0675-0023 | 3 | 11 | [8 empty] | X | X | X | O | O | O | O | O | O | O | O
Agitator |  | 5.25 | DWS Agitator |  | Steel | PG525-0015 | 6 | 8 | [11 empty] | O | X | X | X | X | X | X | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Nathan Marks |  |  |  | 14 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Billy Mcfarland |  |  |  | 14 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Jeff Cambpell |  |  |  | 6 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Russell Arnold |  |  |  | 8 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jeff Cambpell |  |  |  | 8 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Ramon Ries |  |  |  | 6 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33515 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Fat Tire A1H
|  | County: |  | Fayette |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0325MG |  |  | PO #: |  | ProDirectional
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
SD50132 | 8 - NMDC | 7.375 | 28.91 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
SD55520 | 8 - NMDC |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD55923 | 8 - NMDC | 8 | 29.54 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
SD56274 | 8 - NMDC |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD45067 | 8 - NMPDC |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD52214 | 8 - NMPDC | 8 | 8.86 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
SD603913 | 13 - 4 Blade Nortrak Stabilizer (BFF) | 8.188 | 6.9 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
SD610468 | 13 - 4 Blade Nortrak Stabilizer (BFF) |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD115520 | X/O- 4 1/2 IFB x 6 5/8 RegP |  |  |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD116862 | X/O- 4 1/2 IFB x 6 5/8 RegP | 6.563 | 2.78 |  | 4 1/2 IF / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
SD108685 | X/O- 4 1/2 XHB x 6 5/8 RegP | 6.5 | 2.12 |  | 4 1/2 XH / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
SD115530 | X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD112037 | X/O- 4 1/2 XHB x 4 1/2 IFP |  |  |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 12/10/2020 |  | 12/19/2020
SD112109 | X/O- 4 1/2 XHB x 4 1/2 IFP |  |  |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 12/10/2020 |  | 12/19/2020
SD117249 | X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 12/10/2020 |  | 12/19/2020
SD4555 | X/O- 4 1/2 IFB x 4 1/2 XHP | 6.625 | 3.04 |  | 4 1/2 IF / 4 1/2 XH | Dirty |  | 12/10/2020 |  | 12/19/2020
SD104003 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD105364 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD104878 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SD108863 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
SDLC3332 | Lift Cap |  |  |  | 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
ZSB775224 | UBHO Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/19/2020
ZSB775202 | UBHO Sub | 7.75 | 3.11 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 12/10/2020 |  | 12/19/2020
ZSB500016 | UBHO Sub | 5.125 | 2.49 |  | XT 39 / XT 39 | Dirty |  | 12/10/2020
ZSB500025 | UBHO Sub |  |  |  | XT 39 / XT 39 | Clean |  | 12/10/2020
PPM800049 | 7 3/4 -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 | 8 |  |  |  | Clean |  | 12/16/2020 |  | 12/19/2020
PPM800065 | 7 3/4 -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 | 8 | 38.02 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 12/16/2020 |  | 12/19/2020
PPM800011 | 7 3/4 -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.022 | 8 |  |  |  | Clean |  | 12/16/2020 |  | 12/19/2020
AGHF0675-0062 | NOV- Safety Join / Agitator / Shock Sub | 6.75 | 30.43 |  | 4 1/2 IF / 4 1/2 IF | Clean |  | 12/12/2020
Rig-2 | 22 Stands of Drill Pipe | 5 | 2071.8 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 12/12/2020
Rig-3 | 2 Stands of 6 1/2 Drill Collars | 6.5 | 186.78 |  | 4 1/2 XH / 4 1/2 XH | Dirty |  | 12/12/2020
54300 | 9 7/8- Ulterra SPL613-Jetted 6-14s & 3-16s | 9.875 | 1.5 |  | 6 5/8 REG | Clean |  | 12/12/2020
54317 | 9 7/8- Ulterra SPL613-Jetted 6-14s & 3-16s | 9.875 | 1.5 |  | 6 5/8 REG | Dirty |  | 12/15/2020
AGHF0675-0023 | NOV- Safety Join / Agitator / Shock Sub | 6.75 | 30.97 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 12/17/2020
PPM250022 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 | 5 | 34.11 |  | XT 39 / 3 1/2 Reg | Dirty |  | 12/19/2020
PPM250025 | 5 1/2, - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 | 5 | 33.13 |  | XT 39 / 3 1/2 Reg | Clean |  | 12/19/2020
PPM250020 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  |  | XT 39 / 3 1/2 Reg | Clean |  | 12/19/2020
PPM250001 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HT89 +.012 |  |  |  | XT 39 / 3 1/2 Reg | Clean |  | 12/19/2020
MTR475035 | 5 1/2, - 7/8, 3.8 Stg. @ 2.50? Slick- HPW -.004 |  |  |  | XT 39 / 3 1/2 Reg | Clean |  | 12/19/2020
SD55955 | 5 NMDC | 5 | 30.43 |  | XT 39 / XT 39 | Dirty |  | 12/19/2020
SD56281 | 5 NMDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD56700 | 5 NMDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD56701 | 5 NMDC | 5.063 | 29.89 |  | XT 39 / XT 39 | Dirty |  | 12/19/2020
SD56783 | 5 NMDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD56785 | 5 NMDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD56679 | 5 NMPDC | 5.063 | 9.46 |  | XT 39 / XT 39 | Dirty |  | 12/19/2020
SD56870 | 5 NMPDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD115658 | Float Sub |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD119067 | Float Sub |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020
SD119105 | X/O- DS42B x XT39P | 5.375 | 3.08 |  | DS42 / XT 39 | Dirty |  | 12/19/2020
SD119310 | X/O- DS42B x XT39P |  |  |  | DS42 / XT 39 | Clean |  | 12/19/2020
GT551232 | Lift Sub- Gator Technologies |  |  |  | XT 39 | Clean |  | 12/19/2020
GT551251 | Lift Sub- Gator Technologies |  |  |  | XT 39 | Clean |  | 12/19/2020
SDLC3354 | Lift Cap |  |  |  | XT 39 | Clean |  | 12/19/2020
13446789 | 6 3/4- Halliburton GTD64M- Jetted 6-18s | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 12/20/2020
Rig1x | BTI Valve | 5 | 2.37 |  | 4 XT39 / 4 XT39 | Dirty |  | 12/20/2020
PG525-0015 | DWS Agitator | 5.25 | 23.51 |  | DS42 / DS42 | Dirty |  | 12/20/2020
A52068 | Tomax Thruster | 5 | 17.75 |  | XT39 / XT39 | Dirty |  | 12/20/2020
Rig2 | 27 Stands of Drill Pipe | 4.5 | 2556.59 |  | DS42 / DS42 | Dirty |  | 12/20/2020
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33515 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Fat Tire A1H
|  | County: |  | Fayette |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
13 1/2"- Ulterra - U616S - Jetted - 9x14s | 47245 | 12/09/2020 | 12/27/2020 | 19 |  | 1 |  | 1.17 | 4 | 10
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | PPM800004 | 12/09/2020 | 12/27/2020 | 19 |  | 1 |  | 1.17 | 4 | 10
13" - 4 Blade Nortrak Stabilizer (BFF) | SD603913 | 12/10/2020 | 12/19/2020 | 10 |  | 1 |  | 1.17 | 4 | 10
8" - NMPDC | SD52214 | 12/10/2020 | 12/19/2020 | 10 | 2 | 1 ,2 |  | 2.23 | 28.45 | 56.33
UBHO Sub | ZSB775202 | 12/10/2020 | 12/19/2020 | 10 | 2 | 1 ,2 |  | 2.23 | 28.45 | 56.33
8" - NMDC | SD50132 | 12/10/2020 | 12/19/2020 | 10 | 2 | 1 ,2 |  | 2.23 | 28.45 | 56.33
8" - NMDC | SD55923 | 12/10/2020 | 12/19/2020 | 10 | 2 | 1 ,2 |  | 2.23 | 28.45 | 56.33
X/O- 4 1/2 IFB x 6 5/8 RegP | SD116862 | 12/10/2020 | 12/19/2020 | 10 |  | 1 |  | 1.17 | 4 | 10
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s | 54317 | 12/15/2020 | 12/27/2020 | 13 | 2 | 2 |  | 1.07 | 24.45 | 46.33
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 | PPM800065 | 12/16/2020 | 12/19/2020 | 4 | 2 | 2 |  | 1.07 | 24.45 | 46.33
X/O- 4 1/2 XHB x 6 5/8 RegP | SD108685 | 12/10/2020 | 12/19/2020 | 10 | 2 | 2 |  | 1.07 | 24.45 | 46.33
2 Stands of 6 1/2" Drill Collars | Rig-3 | 12/12/2020 | 12/27/2020 | 16 | 2 | 2 |  | 1.07 | 24.45 | 46.33
X/O- 4 1/2 IFB x 4 1/2 XHP | SD4555 | 12/10/2020 | 12/19/2020 | 10 | 2 | 2 |  | 1.07 | 24.45 | 46.33
NOV- Safety Join / Agitator / Shock Sub | AGHF0675-0023 | 12/17/2020 | 12/27/2020 | 11 | 2 | 2 |  | 1.07 | 24.45 | 46.33
6 3/4"- Halliburton GTD64M- Jetted 6-18s | 13446789 | 12/20/2020 | 12/27/2020 | 8 | 5 | 3 |  | 18.18 | 62.25 | 118.33
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 | PPM250022 | 12/19/2020 | 12/27/2020 | 9 | 5 | 3 |  | 18.18 | 62.25 | 118.33
BTI Valve | Rig1x | 12/20/2020 | 12/27/2020 | 8 | 5 | 3 |  | 18.18 | 62.25 | 118.33
5" NMPDC | SD56679 | 12/19/2020 | 12/27/2020 | 9 | 5 | 3 |  | 18.18 | 62.25 | 118.33
UBHO Sub | ZSB500016 | 12/10/2020 | 12/27/2020 | 18 | 5 | 3 |  | 18.18 | 62.25 | 118.33
5" NMDC | SD55955 | 12/19/2020 | 12/27/2020 | 9 | 5 | 3 |  | 18.18 | 62.25 | 118.33
5" NMDC | SD56701 | 12/19/2020 | 12/27/2020 | 9 | 5 | 3 |  | 18.18 | 62.25 | 118.33
Tomax Thruster | A52068 | 12/20/2020 | 12/27/2020 | 8 | 5 | 3 |  | 18.18 | 62.25 | 118.33
X/O- DS42B x XT39P | SD119105 | 12/19/2020 | 12/27/2020 | 9 | 5 | 3 |  | 18.18 | 62.25 | 118.33
DWS Agitator | PG525-0015 | 12/20/2020 | 12/27/2020 | 8 | 5 | 3 |  | 18.18 | 62.25 | 118.33
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Fayette County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well
Facility |  |  | Fat Tire - Fayette County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Fat Tire A1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Fat Tire A1H
Field: |  |  | Fayette County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas South Central 4204
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 441.00 Usft
Map Northing |  |  | 816982.02 US survey foot |  |  | Map Easting |  |  | 2668460.01 US survey foot
Latitude |  |  | 30° 3' 49.16451" N |  |  | Longitude |  |  | 96° 53' 12.44787" W
Grid Convergence |  |  | 1.035
Facility: |  |  | Fat Tire - Fayette County, TX
Map Northing |  |  | 840692.37 US survey foot |  |  | Map Easting |  |  | 2700895.02 US survey foot
Latitude |  |  | 30° 7' 37.89563" N |  |  | Longitude |  |  | 96° 46' 58.28564" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.086
Well: |  |  | Fat Tire A1H
Local North |  |  | 1.69 Usft |  |  | Local East |  |  | 5.40 Usft
Map Northing |  |  | 840692.38 US survey foot |  |  | Map Easting |  |  | 2700895.02 US survey foot
Latitude |  |  | 30° 7' 37.91134" N |  |  | Longitude |  |  | 96° 46' 58.22377" W
Depth Datum |  |  | Well |  |  | Datum Elevation |  |  | 441.00 Usft
GL Elevation |  |  | 413.00 Usft
Grid Convergence |  |  | 1.086
Well bore: |  |  | Fat Tire A1H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 25/12/2020
Total Field (nT) |  |  | 46590.8 |  |  | Dip Angle (°) |  |  | 58.783
Declination (°) |  |  | 2.883
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 329.63
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Fat Tire A1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3031 |  |  | Fat Tire A1H S1 |  |  | MWD+HDGM
3031 |  |  | 9868 |  |  | Fat Tire A1H S2 |  |  | MWD+HDGM
9868 |  |  | 17167 |  |  | Fat Tire A1H S3 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -441 | 840692.38 | 2700895.02 | 30.1272 | -96.7829 | 0
138 | 0.14 | 122.41 | 138 | -0.09 | 0.14 | -0.15 | 0.1 | 0.1 | 88.7 | 122.41 | 138 | -303 | 840692.29 | 2700895.16 | 30.1272 | -96.7829 | 122.41
229 | 0.43 | 70.01 | 229 | -0.03 | 0.56 | -0.31 | 0.4 | 0.32 | -57.58 | -70.24 | 91 | -212 | 840692.35 | 2700895.58 | 30.1272 | -96.7829 | 93.41
320 | 0.48 | 80.96 | 320 | 0.14 | 1.25 | -0.51 | 0.11 | 0.05 | 12.03 | 65.65 | 91 | -121 | 840692.52 | 2700896.27 | 30.1272 | -96.7829 | 83.48
415 | 0.27 | 66.04 | 414.99 | 0.3 | 1.85 | -0.68 | 0.24 | -0.22 | -15.71 | -162.4 | 95 | -26.01 | 840692.68 | 2700896.87 | 30.1272 | -96.7829 | 80.89
510 | 0.78 | 280.11 | 509.99 | 0.5 | 1.42 | -0.29 | 1.07 | 0.54 | 153.61 | -154.5 | 95 | 68.99 | 840692.88 | 2700896.44 | 30.1272 | -96.7829 | 70.56
604 | 1.3 | 273.35 | 603.98 | 0.68 | -0.27 | 0.72 | 0.57 | 0.55 | -7.19 | -16.67 | 94 | 162.98 | 840693.06 | 2700894.75 | 30.1272 | -96.7829 | 337.9
699 | 1.67 | 285.84 | 698.94 | 1.12 | -2.68 | 2.32 | 0.52 | 0.39 | 13.15 | 47.54 | 95 | 257.94 | 840693.5 | 2700892.34 | 30.1272 | -96.7829 | 292.61
793 | 2.18 | 261.96 | 792.89 | 1.24 | -5.77 | 3.99 | 1 | 0.54 | -25.4 | -69.86 | 94 | 351.89 | 840693.62 | 2700889.25 | 30.1272 | -96.7829 | 282.13
887 | 2.42 | 256.47 | 886.82 | 0.53 | -9.47 | 5.24 | 0.35 | 0.26 | -5.84 | -45.32 | 94 | 445.82 | 840692.91 | 2700885.55 | 30.1272 | -96.7829 | 273.18
982 | 3.53 | 247.4 | 981.69 | -1.07 | -14.12 | 6.22 | 1.27 | 1.17 | -9.55 | -27.55 | 95 | 540.69 | 840691.31 | 2700880.9 | 30.1272 | -96.7829 | 265.68
1075 | 4.84 | 237.09 | 1074.44 | -4.3 | -20.06 | 6.43 | 1.62 | 1.41 | -11.09 | -35.08 | 93 | 633.44 | 840688.08 | 2700874.96 | 30.1272 | -96.7829 | 257.9
1169 | 6.46 | 235.04 | 1167.98 | -9.48 | -27.72 | 5.83 | 1.74 | 1.72 | -2.18 | -8.12 | 94 | 726.98 | 840682.9 | 2700867.3 | 30.1272 | -96.7829 | 251.11
1263 | 8.22 | 239.21 | 1261.21 | -15.95 | -37.83 | 5.36 | 1.96 | 1.87 | 4.44 | 18.92 | 94 | 820.21 | 840676.43 | 2700857.19 | 30.1272 | -96.783 | 247.13
1356 | 9.03 | 241.73 | 1353.15 | -22.81 | -49.97 | 5.58 | 0.96 | 0.87 | 2.71 | 26.26 | 93 | 912.15 | 840669.57 | 2700845.05 | 30.1271 | -96.783 | 245.46
1450 | 9.92 | 238.16 | 1445.87 | -30.58 | -63.34 | 5.64 | 1.13 | 0.95 | -3.8 | -35.21 | 94 | 1004.87 | 840661.8 | 2700831.68 | 30.1271 | -96.7831 | 244.23
1544 | 10.79 | 237.68 | 1538.34 | -39.56 | -77.66 | 5.13 | 0.93 | 0.93 | -0.51 | -5.9 | 94 | 1097.34 | 840652.82 | 2700817.36 | 30.1271 | -96.7831 | 243.01
1638 | 10.5 | 236.76 | 1630.72 | -48.96 | -92.26 | 4.41 | 0.36 | -0.31 | -0.98 | -150.08 | 94 | 1189.72 | 840643.42 | 2700802.76 | 30.1271 | -96.7832 | 242.05
1731 | 10.29 | 236.09 | 1722.19 | -58.23 | -106.24 | 3.47 | 0.26 | -0.23 | -0.72 | -150.4 | 93 | 1281.19 | 840634.15 | 2700788.78 | 30.127 | -96.7832 | 241.27
1826 | 10.17 | 238.01 | 1815.68 | -67.41 | -120.39 | 2.71 | 0.38 | -0.13 | 2.02 | 110.33 | 95 | 1374.68 | 840624.97 | 2700774.63 | 30.127 | -96.7832 | 240.75
1920 | 9.79 | 237.39 | 1908.26 | -76.11 | -134.16 | 2.16 | 0.42 | -0.4 | -0.66 | -164.52 | 94 | 1467.26 | 840616.27 | 2700760.86 | 30.127 | -96.7833 | 240.43
2013 | 10.1 | 239.67 | 1999.87 | -84.49 | -147.86 | 1.86 | 0.54 | 0.33 | 2.45 | 52.91 | 93 | 1558.87 | 840607.89 | 2700747.16 | 30.127 | -96.7833 | 240.25
2108 | 10.33 | 241.13 | 2093.36 | -92.81 | -162.51 | 2.09 | 0.36 | 0.24 | 1.54 | 49.11 | 95 | 1652.36 | 840599.57 | 2700732.51 | 30.1269 | -96.7834 | 240.27
2203 | 10.24 | 241.38 | 2186.83 | -100.97 | -177.38 | 2.57 | 0.11 | -0.09 | 0.26 | 153.74 | 95 | 1745.83 | 840591.41 | 2700717.64 | 30.1269 | -96.7834 | 240.35
2297 | 10.14 | 241.13 | 2279.35 | -108.97 | -191.96 | 3.04 | 0.12 | -0.11 | -0.27 | -156.26 | 94 | 1838.35 | 840583.41 | 2700703.06 | 30.1269 | -96.7835 | 240.42
2392 | 9.92 | 241.85 | 2372.9 | -116.87 | -206.5 | 3.57 | 0.27 | -0.23 | 0.76 | 150.67 | 95 | 1931.9 | 840575.51 | 2700688.52 | 30.1269 | -96.7835 | 240.49
2486 | 9.47 | 242.45 | 2465.56 | -124.26 | -220.5 | 4.27 | 0.49 | -0.48 | 0.64 | 167.64 | 94 | 2024.56 | 840568.12 | 2700674.52 | 30.1269 | -96.7836 | 240.6
2580 | 10.1 | 239.67 | 2558.19 | -132 | -234.47 | 4.65 | 0.84 | 0.67 | -2.96 | -38.24 | 94 | 2117.19 | 840560.38 | 2700660.55 | 30.1268 | -96.7836 | 240.62
2674 | 11.82 | 236.04 | 2650.47 | -141.54 | -249.57 | 4.06 | 1.97 | 1.83 | -3.86 | -23.65 | 94 | 2209.47 | 840550.84 | 2700645.45 | 30.1268 | -96.7837 | 240.44
2768 | 11.85 | 235.53 | 2742.47 | -152.38 | -265.51 | 2.76 | 0.12 | 0.03 | -0.54 | -74.25 | 94 | 2301.47 | 840540 | 2700629.51 | 30.1268 | -96.7837 | 240.15
2862 | 11.4 | 232.97 | 2834.55 | -163.44 | -280.88 | 1 | 0.73 | -0.48 | -2.72 | -132.35 | 94 | 2393.55 | 840528.94 | 2700614.14 | 30.1268 | -96.7838 | 239.81
2956 | 11.19 | 232.77 | 2926.72 | -174.55 | -295.56 | -1.17 | 0.23 | -0.22 | -0.21 | -169.53 | 94 | 2485.72 | 840517.83 | 2700599.46 | 30.1267 | -96.7838 | 239.43
3031 | 11.12 | 231.55 | 3000.31 | -183.45 | -307.02 | -3.06 | 0.33 | -0.09 | -1.63 | -107.12 | 75 | 2559.31 | 840508.93 | 2700588 | 30.1267 | -96.7838 | 239.14
3175 | 11.12 | 248.15 | 3141.64 | -197.26 | -330.79 | -2.95 | 2.22 | 0 | 11.53 | 98.15 | 144 | 2700.64 | 840495.12 | 2700564.23 | 30.1267 | -96.7839 | 239.19
3268 | 11.31 | 250.76 | 3232.87 | -203.6 | -347.72 | 0.14 | 0.58 | 0.2 | 2.81 | 70.76 | 93 | 2791.87 | 840488.78 | 2700547.3 | 30.1267 | -96.784 | 239.65
3362 | 11.49 | 249.85 | 3325.01 | -209.86 | -365.22 | 3.58 | 0.27 | 0.19 | -0.97 | -45.43 | 94 | 2884.01 | 840482.52 | 2700529.8 | 30.1266 | -96.784 | 240.12
3456 | 11.58 | 248.11 | 3417.11 | -216.61 | -382.76 | 6.63 | 0.38 | 0.1 | -1.85 | -76.35 | 94 | 2976.11 | 840475.77 | 2700512.26 | 30.1266 | -96.7841 | 240.49
3549 | 11.74 | 236.74 | 3508.21 | -225.28 | -399.33 | 7.53 | 2.47 | 0.17 | -12.23 | -91.6 | 93 | 3067.21 | 840467.1 | 2700495.69 | 30.1266 | -96.7841 | 240.57
3643 | 12.06 | 233.13 | 3600.19 | -236.41 | -415.19 | 5.94 | 0.86 | 0.34 | -3.84 | -68.51 | 94 | 3159.19 | 840455.97 | 2700479.83 | 30.1266 | -96.7842 | 240.34
3736 | 10.19 | 240.93 | 3691.44 | -246.24 | -430.15 | 5.02 | 2.58 | -2.01 | 8.39 | 144.96 | 93 | 3250.44 | 840446.14 | 2700464.87 | 30.1265 | -96.7842 | 240.21
3830 | 9.83 | 240.54 | 3784.01 | -254.23 | -444.41 | 5.34 | 0.39 | -0.38 | -0.41 | -169.53 | 94 | 3343.01 | 840438.15 | 2700450.61 | 30.1265 | -96.7843 | 240.23
3924 | 9.84 | 238 | 3876.63 | -262.43 | -458.2 | 5.24 | 0.46 | 0.01 | -2.7 | -89.93 | 94 | 3435.63 | 840429.95 | 2700436.82 | 30.1265 | -96.7843 | 240.2
4017 | 9.79 | 238.96 | 3968.27 | -270.72 | -471.72 | 4.92 | 0.18 | -0.05 | 1.03 | 107.46 | 93 | 3527.27 | 840421.66 | 2700423.3 | 30.1265 | -96.7844 | 240.15
4111 | 9.62 | 238.91 | 4060.92 | -278.9 | -485.29 | 4.73 | 0.18 | -0.18 | -0.05 | -177.19 | 94 | 3619.92 | 840413.48 | 2700409.73 | 30.1265 | -96.7844 | 240.11
4205 | 8.81 | 239.3 | 4153.71 | -286.63 | -498.21 | 4.59 | 0.86 | -0.86 | 0.41 | 175.78 | 94 | 3712.71 | 840405.75 | 2700396.81 | 30.1264 | -96.7845 | 240.09
4299 | 8.53 | 238.42 | 4246.63 | -293.95 | -510.34 | 4.4 | 0.33 | -0.3 | -0.94 | -155.08 | 94 | 3805.63 | 840398.43 | 2700384.68 | 30.1264 | -96.7845 | 240.06
4393 | 9.56 | 244.99 | 4339.47 | -300.9 | -523.35 | 4.98 | 1.55 | 1.1 | 6.99 | 48.36 | 94 | 3898.47 | 840391.48 | 2700371.67 | 30.1264 | -96.7845 | 240.1
4485 | 10.62 | 246.53 | 4430.04 | -307.51 | -538.05 | 6.71 | 1.19 | 1.15 | 1.67 | 15.04 | 92 | 3989.04 | 840384.87 | 2700356.97 | 30.1264 | -96.7846 | 240.25
4579 | 10.21 | 247.35 | 4522.49 | -314.17 | -553.68 | 8.87 | 0.46 | -0.44 | 0.87 | 160.53 | 94 | 4081.49 | 840378.21 | 2700341.34 | 30.1264 | -96.7846 | 240.43
4674 | 9.89 | 245.72 | 4616.04 | -320.77 | -568.89 | 10.87 | 0.45 | -0.34 | -1.72 | -139.17 | 95 | 4175.04 | 840371.61 | 2700326.13 | 30.1263 | -96.7847 | 240.58
4768 | 9.64 | 244.84 | 4708.67 | -327.43 | -583.37 | 12.44 | 0.31 | -0.27 | -0.94 | -149.6 | 94 | 4267.67 | 840364.95 | 2700311.65 | 30.1263 | -96.7847 | 240.7
4862 | 9.55 | 243.73 | 4801.36 | -334.23 | -597.49 | 13.71 | 0.22 | -0.1 | -1.18 | -116.49 | 94 | 4360.36 | 840358.15 | 2700297.53 | 30.1263 | -96.7848 | 240.78
4956 | 9.74 | 244.42 | 4894.03 | -341.11 | -611.65 | 14.94 | 0.24 | 0.2 | 0.73 | 31.66 | 94 | 4453.03 | 840351.27 | 2700283.37 | 30.1263 | -96.7848 | 240.85
5050 | 8.98 | 246.08 | 4986.78 | -347.52 | -625.53 | 16.42 | 0.86 | -0.81 | 1.77 | 161.26 | 94 | 4545.78 | 840344.86 | 2700269.49 | 30.1263 | -96.7849 | 240.95
5145 | 8.41 | 244.3 | 5080.69 | -353.54 | -638.57 | 17.82 | 0.66 | -0.6 | -1.87 | -155.61 | 95 | 4639.69 | 840338.84 | 2700256.45 | 30.1263 | -96.7849 | 241.03
5239 | 8.34 | 243.87 | 5173.68 | -359.52 | -650.88 | 18.89 | 0.1 | -0.07 | -0.46 | -138.39 | 94 | 4732.68 | 840332.86 | 2700244.14 | 30.1262 | -96.7849 | 241.09
5332 | 8.47 | 245.05 | 5265.68 | -365.38 | -663.15 | 20.03 | 0.23 | 0.14 | 1.27 | 53.58 | 93 | 4824.68 | 840327 | 2700231.87 | 30.1262 | -96.785 | 241.15
5426 | 7.87 | 243.23 | 5358.73 | -371.2 | -675.17 | 21.09 | 0.69 | -0.64 | -1.94 | -157.58 | 94 | 4917.73 | 840321.18 | 2700219.85 | 30.1262 | -96.785 | 241.2
5520 | 7.62 | 241.41 | 5451.87 | -377.08 | -686.39 | 21.69 | 0.37 | -0.27 | -1.94 | -136.45 | 94 | 5010.87 | 840315.3 | 2700208.63 | 30.1262 | -96.785 | 241.22
5614 | 7.67 | 243.78 | 5545.04 | -382.84 | -697.49 | 22.33 | 0.34 | 0.05 | 2.52 | 82.16 | 94 | 5104.04 | 840309.54 | 2700197.53 | 30.1262 | -96.7851 | 241.24
5707 | 8.57 | 235.07 | 5637.11 | -389.55 | -708.74 | 22.23 | 1.64 | 0.97 | -9.37 | -58.18 | 93 | 5196.11 | 840302.83 | 2700186.28 | 30.1262 | -96.7851 | 241.21
5801 | 10.36 | 225.04 | 5729.83 | -399.53 | -720.46 | 19.55 | 2.58 | 1.9 | -10.67 | -47.68 | 94 | 5288.83 | 840292.85 | 2700174.56 | 30.1261 | -96.7852 | 240.99
5896 | 10.2 | 223.87 | 5823.31 | -411.63 | -732.34 | 15.11 | 0.28 | -0.17 | -1.23 | -128.04 | 95 | 5382.31 | 840280.75 | 2700162.68 | 30.1261 | -96.7852 | 240.66
5990 | 8.59 | 224.12 | 5916.04 | -422.67 | -742.99 | 10.97 | 1.71 | -1.71 | 0.27 | 178.67 | 94 | 5475.04 | 840269.71 | 2700152.03 | 30.1261 | -96.7852 | 240.37
6084 | 6.91 | 226.77 | 6009.18 | -431.59 | -752 | 7.84 | 1.83 | -1.79 | 2.82 | 169.3 | 94 | 5568.18 | 840260.79 | 2700143.02 | 30.126 | -96.7853 | 240.15
6178 | 5.61 | 227.2 | 6102.62 | -438.58 | -759.49 | 5.59 | 1.38 | -1.38 | 0.46 | 178.15 | 94 | 5661.62 | 840253.8 | 2700135.53 | 30.126 | -96.7853 | 240
6272 | 3.61 | 226.68 | 6196.31 | -443.73 | -765.02 | 3.94 | 2.13 | -2.13 | -0.55 | -179.06 | 94 | 5755.31 | 840248.65 | 2700130 | 30.126 | -96.7853 | 239.89
6365 | 3.27 | 209.56 | 6289.14 | -448.05 | -768.46 | 1.95 | 1.16 | -0.37 | -18.41 | -116.73 | 93 | 5848.14 | 840244.33 | 2700126.56 | 30.126 | -96.7853 | 239.76
6460 | 1.55 | 214.4 | 6384.06 | -451.47 | -770.52 | 0.05 | 1.82 | -1.81 | 5.09 | 175.67 | 95 | 5943.06 | 840240.91 | 2700124.5 | 30.126 | -96.7853 | 239.63
6554 | 0.56 | 212.89 | 6478.04 | -452.9 | -771.49 | -0.7 | 1.05 | -1.05 | -1.61 | -179.15 | 94 | 6037.04 | 840239.48 | 2700123.53 | 30.126 | -96.7853 | 239.58
6648 | 0.47 | 212.06 | 6572.04 | -453.61 | -771.94 | -1.09 | 0.1 | -0.1 | -0.88 | -175.68 | 94 | 6131.04 | 840238.77 | 2700123.08 | 30.126 | -96.7853 | 239.56
6740 | 0.72 | 251.89 | 6664.03 | -454.11 | -772.69 | -1.14 | 0.51 | 0.27 | 43.29 | 79.81 | 92 | 6223.03 | 840238.27 | 2700122.33 | 30.126 | -96.7853 | 239.56
6835 | 0.69 | 252.44 | 6759.02 | -454.47 | -773.8 | -0.89 | 0.03 | -0.03 | 0.58 | 167.56 | 95 | 6318.02 | 840237.91 | 2700121.22 | 30.126 | -96.7853 | 239.57
6929 | 0.64 | 273.28 | 6853.02 | -454.61 | -774.87 | -0.47 | 0.26 | -0.05 | 22.17 | 111.97 | 94 | 6412.02 | 840237.77 | 2700120.15 | 30.126 | -96.7853 | 239.6
7022 | 0.75 | 273.71 | 6946.01 | -454.54 | -775.99 | 0.16 | 0.12 | 0.12 | 0.46 | 2.93 | 93 | 6505.01 | 840237.84 | 2700119.03 | 30.126 | -96.7853 | 239.64
7116 | 0.81 | 274.55 | 7040 | -454.45 | -777.27 | 0.88 | 0.06 | 0.06 | 0.89 | 11.21 | 94 | 6599 | 840237.93 | 2700117.75 | 30.126 | -96.7853 | 239.69
7210 | 0.98 | 286.9 | 7133.99 | -454.16 | -778.7 | 1.85 | 0.27 | 0.18 | 13.14 | 54.9 | 94 | 6692.99 | 840238.22 | 2700116.32 | 30.126 | -96.7853 | 239.75
7304 | 1.06 | 295.42 | 7227.98 | -453.56 | -780.26 | 3.16 | 0.18 | 0.09 | 9.06 | 66.49 | 94 | 6786.98 | 840238.82 | 2700114.76 | 30.126 | -96.7854 | 239.83
7398 | 0.49 | 34.64 | 7321.97 | -452.85 | -780.81 | 4.05 | 1.32 | -0.61 | 105.55 | 156.98 | 94 | 6880.97 | 840239.53 | 2700114.21 | 30.126 | -96.7854 | 239.89
7492 | 0.86 | 96.81 | 7415.96 | -452.61 | -779.88 | 3.8 | 0.81 | 0.39 | 66.14 | 96.64 | 94 | 6974.96 | 840239.77 | 2700115.14 | 30.126 | -96.7854 | 239.87
7585 | 0.61 | 106.78 | 7508.96 | -452.83 | -778.72 | 3.01 | 0.3 | -0.27 | 10.72 | 157.83 | 93 | 7067.96 | 840239.55 | 2700116.3 | 30.126 | -96.7853 | 239.82
7680 | 0.4 | 148.41 | 7603.95 | -453.26 | -778.06 | 2.31 | 0.43 | -0.22 | 43.82 | 139.49 | 95 | 7162.95 | 840239.12 | 2700116.96 | 30.126 | -96.7853 | 239.78
7773 | 0.37 | 196.2 | 7696.95 | -453.82 | -777.97 | 1.78 | 0.34 | -0.03 | 51.39 | 118.92 | 93 | 7255.95 | 840238.56 | 2700117.05 | 30.126 | -96.7853 | 239.74
7867 | 0.47 | 331.42 | 7790.95 | -453.78 | -778.24 | 1.96 | 0.83 | 0.11 | 143.85 | 154.8 | 94 | 7349.95 | 840238.6 | 2700116.78 | 30.126 | -96.7853 | 239.75
7961 | 0.83 | 318.86 | 7884.94 | -452.93 | -778.87 | 3.01 | 0.41 | 0.38 | -13.36 | -27.95 | 94 | 7443.94 | 840239.45 | 2700116.15 | 30.126 | -96.7853 | 239.82
8054 | 0.96 | 309.05 | 7977.93 | -451.93 | -779.92 | 4.4 | 0.22 | 0.14 | -10.55 | -54.66 | 93 | 7536.93 | 840240.45 | 2700115.1 | 30.126 | -96.7854 | 239.91
8147 | 0.77 | 0.9 | 8070.92 | -450.81 | -780.52 | 5.66 | 0.83 | -0.2 | 55.75 | 128.65 | 93 | 7629.92 | 840241.57 | 2700114.5 | 30.126 | -96.7854 | 239.99
8242 | 0.84 | 358.91 | 8165.91 | -449.48 | -780.52 | 6.82 | 0.08 | 0.07 | 2.09 | -22.77 | 95 | 7724.91 | 840242.9 | 2700114.5 | 30.126 | -96.7854 | 240.06
8336 | 1.08 | 331.97 | 8259.9 | -448.01 | -780.95 | 8.3 | 0.54 | 0.26 | -28.66 | -75.91 | 94 | 7818.9 | 840244.37 | 2700114.07 | 30.126 | -96.7854 | 240.16
8430 | 0.1 | 162.72 | 8353.9 | -447.3 | -781.34 | 9.11 | 1.25 | -1.04 | -180.05 | -179.09 | 94 | 7912.9 | 840245.08 | 2700113.68 | 30.126 | -96.7854 | 240.21
8525 | 0.42 | 153.4 | 8448.89 | -447.69 | -781.16 | 8.68 | 0.34 | 0.34 | -9.81 | -12.21 | 95 | 8007.89 | 840244.69 | 2700113.86 | 30.126 | -96.7854 | 240.18
8618 | 0.11 | 135.13 | 8541.89 | -448.06 | -780.95 | 8.25 | 0.34 | -0.33 | -19.65 | -173.76 | 93 | 8100.89 | 840244.32 | 2700114.07 | 30.126 | -96.7854 | 240.16
8712 | 0.24 | 19.63 | 8635.89 | -447.94 | -780.82 | 8.29 | 0.32 | 0.14 | -122.87 | -134.56 | 94 | 8194.89 | 840244.44 | 2700114.2 | 30.126 | -96.7854 | 240.16
8807 | 0.95 | 321.73 | 8730.89 | -447.13 | -781.24 | 9.2 | 0.89 | 0.75 | 60.95 | -71.78 | 95 | 8289.89 | 840245.25 | 2700113.78 | 30.126 | -96.7854 | 240.22
8901 | 1.15 | 4.36 | 8824.87 | -445.58 | -781.65 | 10.75 | 0.84 | 0.21 | 45.35 | 97.59 | 94 | 8383.87 | 840246.8 | 2700113.37 | 30.126 | -96.7854 | 240.31
8996 | 0.85 | 125.69 | 8919.87 | -445.04 | -781 | 10.89 | 1.84 | -0.32 | 127.72 | 155.48 | 95 | 8478.87 | 840247.34 | 2700114.02 | 30.126 | -96.7854 | 240.32
9090 | 0.58 | 160.8 | 9013.86 | -445.9 | -780.28 | 9.78 | 0.53 | -0.29 | 37.35 | 138.38 | 94 | 8572.86 | 840246.48 | 2700114.74 | 30.126 | -96.7854 | 240.25
9185 | 0.47 | 350.87 | 9108.86 | -445.97 | -780.18 | 9.67 | 1.1 | -0.12 | 178.87 | -175.49 | 95 | 8667.86 | 840246.41 | 2700114.84 | 30.126 | -96.7854 | 240.25
9279 | 1.25 | 359.08 | 9202.85 | -444.56 | -780.26 | 10.93 | 0.84 | 0.83 | 8.73 | 13.1 | 94 | 8761.85 | 840247.82 | 2700114.76 | 30.126 | -96.7854 | 240.33
9372 | 1.42 | 20.23 | 9295.82 | -442.47 | -779.88 | 12.54 | 0.56 | 0.18 | 22.74 | 81.74 | 93 | 8854.82 | 840249.91 | 2700115.14 | 30.126 | -96.7853 | 240.43
9466 | 0.94 | 105.07 | 9389.81 | -441.57 | -778.73 | 12.73 | 1.73 | -0.51 | 90.26 | 144.96 | 94 | 8948.81 | 840250.81 | 2700116.29 | 30.126 | -96.7853 | 240.44
9561 | 0.55 | 123.32 | 9484.8 | -442.03 | -777.6 | 11.77 | 0.48 | -0.41 | 19.21 | 157.59 | 95 | 9043.8 | 840250.35 | 2700117.42 | 30.126 | -96.7853 | 240.38
9654 | 0.14 | 63.27 | 9577.8 | -442.22 | -777.12 | 11.36 | 0.53 | -0.44 | -64.57 | -165.82 | 93 | 9136.8 | 840250.16 | 2700117.9 | 30.126 | -96.7853 | 240.36
9748 | 2.98 | 314.08 | 9671.76 | -440.47 | -778.78 | 13.71 | 3.22 | 3.02 | 116.16 | -111.69 | 94 | 9230.76 | 840251.91 | 2700116.24 | 30.126 | -96.7853 | 240.51
9842 | 5.54 | 320.77 | 9765.49 | -435.25 | -783.4 | 20.55 | 2.77 | 2.72 | 7.12 | 14.34 | 94 | 9324.49 | 840257.13 | 2700111.62 | 30.126 | -96.7854 | 240.94
9868 | 5.35 | 319.06 | 9791.37 | -433.37 | -784.99 | 22.98 | 0.96 | -0.73 | -6.58 | -140.35 | 26 | 9350.37 | 840259.01 | 2700110.03 | 30.126 | -96.7854 | 241.1
9966 | 12.92 | 330.93 | 9888.07 | -420.32 | -793.32 | 38.45 | 7.92 | 7.72 | 12.11 | 19.91 | 98 | 9447.07 | 840272.06 | 2700101.7 | 30.1261 | -96.7854 | 242.08
10062 | 23.83 | 331.31 | 9979.03 | -393.85 | -807.89 | 68.65 | 11.37 | 11.36 | 0.4 | 0.81 | 96 | 9538.03 | 840298.53 | 2700087.13 | 30.1262 | -96.7854 | 244.01
10157 | 30.18 | 330.45 | 10063.63 | -356.2 | -828.9 | 111.76 | 6.7 | 6.68 | -0.91 | -3.9 | 95 | 9622.63 | 840336.18 | 2700066.12 | 30.1263 | -96.7855 | 246.75
10253 | 29.23 | 324.11 | 10147.04 | -316.21 | -854.55 | 159.23 | 3.42 | -0.99 | -6.6 | -109.56 | 96 | 9706.04 | 840376.17 | 2700040.47 | 30.1264 | -96.7856 | 249.69
10348 | 40.1 | 328.32 | 10225.07 | -271.24 | -884.31 | 213.07 | 11.71 | 11.44 | 4.43 | 14.19 | 95 | 9784.07 | 840421.14 | 2700010.71 | 30.1265 | -96.7857 | 252.95
10442 | 48.88 | 329.65 | 10292.06 | -214.81 | -918.16 | 278.87 | 9.39 | 9.34 | 1.41 | 6.54 | 94 | 9851.06 | 840477.57 | 2699976.86 | 30.1267 | -96.7858 | 256.83
10537 | 53.71 | 328.89 | 10351.45 | -151.11 | -956.05 | 352.99 | 5.12 | 5.08 | -0.8 | -7.24 | 95 | 9910.45 | 840541.27 | 2699938.97 | 30.1268 | -96.7859 | 261.02
10632 | 63.85 | 330.04 | 10400.63 | -81.21 | -997.23 | 434.12 | 10.72 | 10.67 | 1.21 | 5.85 | 95 | 9959.63 | 840611.17 | 2699897.79 | 30.127 | -96.786 | 265.34
10728 | 75.49 | 329.25 | 10433.92 | -3.67 | -1042.67 | 523.98 | 12.15 | 12.13 | -0.82 | -3.79 | 96 | 9992.92 | 840688.71 | 2699852.35 | 30.1272 | -96.7862 | 269.8
10823 | 82.69 | 328.44 | 10451.89 | 76.1 | -1090.9 | 617.2 | 7.62 | 7.58 | -0.85 | -6.38 | 95 | 10010.89 | 840768.48 | 2699804.12 | 30.1275 | -96.7863 | 273.99
10917 | 80.15 | 329.74 | 10465.91 | 155.83 | -1138.65 | 710.13 | 3.03 | -2.7 | 1.38 | 153.25 | 94 | 10024.91 | 840848.21 | 2699756.37 | 30.1277 | -96.7864 | 277.79
11013 | 93.68 | 331.4 | 10471.07 | 239.13 | -1185.63 | 805.75 | 14.2 | 14.09 | 1.73 | 7.05 | 96 | 10030.07 | 840931.51 | 2699709.39 | 30.1279 | -96.7866 | 281.4
11108 | 94.58 | 331.52 | 10464.23 | 322.37 | -1230.9 | 900.46 | 0.96 | 0.95 | 0.13 | 7.57 | 95 | 10023.23 | 841014.75 | 2699664.12 | 30.1281 | -96.7867 | 284.68
11202 | 92.43 | 330.14 | 10458.48 | 404.29 | -1276.63 | 994.25 | 2.72 | -2.29 | -1.47 | -147.31 | 94 | 10017.48 | 841096.67 | 2699618.39 | 30.1284 | -96.7869 | 287.57
11296 | 91.89 | 329.65 | 10454.94 | 485.55 | -1323.74 | 1088.18 | 0.78 | -0.57 | -0.52 | -137.79 | 94 | 10013.94 | 841177.93 | 2699571.28 | 30.1286 | -96.787 | 290.14
11392 | 92 | 329.99 | 10451.68 | 568.49 | -1371.98 | 1184.13 | 0.37 | 0.11 | 0.35 | 72.06 | 96 | 10010.68 | 841260.87 | 2699523.04 | 30.1288 | -96.7872 | 292.51
11486 | 92.48 | 330.14 | 10448 | 649.89 | -1418.85 | 1278.05 | 0.53 | 0.51 | 0.16 | 17.34 | 94 | 10007 | 841342.27 | 2699476.17 | 30.1291 | -96.7873 | 294.61
11580 | 90.32 | 330.12 | 10445.71 | 731.37 | -1465.65 | 1372.02 | 2.3 | -2.3 | -0.02 | -179.47 | 94 | 10004.71 | 841423.75 | 2699429.37 | 30.1293 | -96.7874 | 296.52
11674 | 88.95 | 329.88 | 10446.31 | 812.77 | -1512.64 | 1466.01 | 1.48 | -1.46 | -0.26 | -170.06 | 94 | 10005.31 | 841505.15 | 2699382.38 | 30.1295 | -96.7876 | 298.25
11769 | 91.69 | 330.16 | 10445.78 | 895.05 | -1560.11 | 1561 | 2.9 | 2.88 | 0.29 | 5.83 | 95 | 10004.78 | 841587.43 | 2699334.91 | 30.1297 | -96.7877 | 299.84
11864 | 93.66 | 329.16 | 10441.34 | 976.95 | -1608.04 | 1655.89 | 2.33 | 2.07 | -1.05 | -26.87 | 95 | 10000.34 | 841669.33 | 2699286.98 | 30.13 | -96.7879 | 301.28
11959 | 94.05 | 328.31 | 10434.96 | 1057.97 | -1657.23 | 1750.66 | 0.98 | 0.41 | -0.89 | -65.28 | 95 | 9993.96 | 841750.35 | 2699237.79 | 30.1302 | -96.788 | 302.55
12053 | 93.47 | 327.84 | 10428.79 | 1137.58 | -1706.84 | 1844.42 | 0.79 | -0.62 | -0.5 | -141.03 | 94 | 9987.79 | 841829.96 | 2699188.18 | 30.1304 | -96.7882 | 303.68
12149 | 92.13 | 327.1 | 10424.1 | 1218.42 | -1758.4 | 1940.24 | 1.59 | -1.4 | -0.77 | -151.1 | 96 | 9983.1 | 841910.8 | 2699136.62 | 30.1306 | -96.7883 | 304.72
12245 | 94.73 | 328.84 | 10418.36 | 1299.64 | -1809.21 | 2036.01 | 3.26 | 2.71 | 1.81 | 33.7 | 96 | 9977.36 | 841992.02 | 2699085.81 | 30.1309 | -96.7885 | 305.69
12341 | 96.59 | 329.4 | 10408.89 | 1381.63 | -1858.24 | 2131.54 | 2.02 | 1.94 | 0.58 | 16.65 | 96 | 9967.89 | 842074.01 | 2699036.78 | 30.1311 | -96.7887 | 306.63
12436 | 93.64 | 331.33 | 10400.42 | 1463.86 | -1905.02 | 2226.13 | 3.71 | -3.11 | 2.03 | 146.82 | 95 | 9959.42 | 842156.24 | 2698990 | 30.1313 | -96.7888 | 307.54
12531 | 93.64 | 331.53 | 10394.39 | 1547.13 | -1950.36 | 2320.9 | 0.21 | 0 | 0.21 | 89.99 | 95 | 9953.39 | 842239.51 | 2698944.66 | 30.1315 | -96.7889 | 308.42
12627 | 94.84 | 332.2 | 10387.29 | 1631.55 | -1995.51 | 2416.56 | 1.43 | 1.25 | 0.7 | 29.09 | 96 | 9946.29 | 842323.93 | 2698899.51 | 30.1318 | -96.7891 | 309.27
12723 | 93.83 | 331.99 | 10380.04 | 1716.14 | -2040.31 | 2512.19 | 1.07 | -1.05 | -0.22 | -168.28 | 96 | 9939.04 | 842408.52 | 2698854.71 | 30.132 | -96.7892 | 310.07
12818 | 92.87 | 330.81 | 10374.48 | 1799.41 | -2085.7 | 2606.98 | 1.6 | -1.01 | -1.24 | -129.14 | 95 | 9933.48 | 842491.79 | 2698809.32 | 30.1322 | -96.7893 | 310.79
12912 | 93.5 | 331.07 | 10369.26 | 1881.45 | -2131.29 | 2700.81 | 0.72 | 0.67 | 0.28 | 22.39 | 94 | 9928.26 | 842573.83 | 2698763.73 | 30.1325 | -96.7895 | 311.44
13006 | 94.18 | 331.31 | 10362.97 | 1963.62 | -2176.49 | 2794.57 | 0.77 | 0.72 | 0.26 | 19.39 | 94 | 9921.97 | 842656 | 2698718.53 | 30.1327 | -96.7896 | 312.06
13102 | 95.29 | 331.96 | 10355.04 | 2047.81 | -2221.94 | 2890.18 | 1.34 | 1.16 | 0.68 | 30.24 | 96 | 9914.04 | 842740.19 | 2698673.08 | 30.1329 | -96.7898 | 312.66
13196 | 93.6 | 330.55 | 10347.76 | 2129.97 | -2267.01 | 2983.85 | 2.34 | -1.8 | -1.5 | -140.19 | 94 | 9906.76 | 842822.35 | 2698628.01 | 30.1332 | -96.7899 | 313.21
13291 | 93.53 | 329.24 | 10341.85 | 2212 | -2314.57 | 3078.67 | 1.38 | -0.07 | -1.38 | -93.02 | 95 | 9900.85 | 842904.38 | 2698580.45 | 30.1334 | -96.79 | 313.7
13387 | 93.93 | 328.84 | 10335.6 | 2294.14 | -2363.85 | 3174.46 | 0.59 | 0.42 | -0.42 | -44.93 | 96 | 9894.6 | 842986.52 | 2698531.17 | 30.1336 | -96.7902 | 314.14
13481 | 92.96 | 327.65 | 10329.96 | 2373.93 | -2413.23 | 3268.26 | 1.63 | -1.03 | -1.27 | -129.2 | 94 | 9888.96 | 843066.31 | 2698481.79 | 30.1338 | -96.7903 | 314.53
13577 | 95.04 | 328.33 | 10323.26 | 2455.13 | -2463.99 | 3363.98 | 2.28 | 2.17 | 0.71 | 18.04 | 96 | 9882.26 | 843147.51 | 2698431.03 | 30.1341 | -96.7905 | 314.9
13671 | 95.99 | 328.52 | 10314.23 | 2534.84 | -2512.98 | 3457.52 | 1.03 | 1.01 | 0.2 | 11.25 | 94 | 9873.23 | 843227.22 | 2698382.04 | 30.1343 | -96.7907 | 315.25
13765 | 92.84 | 329.05 | 10306.99 | 2614.98 | -2561.54 | 3551.22 | 3.4 | -3.35 | 0.56 | 170.46 | 94 | 9865.99 | 843307.36 | 2698333.48 | 30.1345 | -96.7908 | 315.59
13859 | 93.85 | 328.91 | 10301.51 | 2695.4 | -2609.9 | 3645.05 | 1.08 | 1.07 | -0.15 | -7.87 | 94 | 9860.51 | 843387.78 | 2698285.12 | 30.1347 | -96.7909 | 315.92
13954 | 94.66 | 329.49 | 10294.46 | 2776.77 | -2658.41 | 3739.79 | 1.05 | 0.85 | 0.61 | 35.51 | 95 | 9853.46 | 843469.15 | 2698236.61 | 30.135 | -96.7911 | 316.25
14048 | 92.3 | 327.35 | 10288.75 | 2856.69 | -2707.54 | 3833.58 | 3.39 | -2.51 | -2.28 | -137.78 | 94 | 9847.75 | 843549.07 | 2698187.48 | 30.1352 | -96.7912 | 316.54
14142 | 93.5 | 326.74 | 10283.99 | 2935.47 | -2758.61 | 3927.36 | 1.43 | 1.28 | -0.65 | -26.9 | 94 | 9842.99 | 843627.85 | 2698136.41 | 30.1354 | -96.7914 | 316.78
14237 | 90.2 | 326.82 | 10280.93 | 3014.89 | -2810.62 | 4022.18 | 3.47 | -3.47 | 0.08 | 178.61 | 95 | 9839.93 | 843707.27 | 2698084.4 | 30.1356 | -96.7916 | 317.01
14331 | 89.39 | 326.62 | 10281.26 | 3093.47 | -2862.2 | 4116.06 | 0.89 | -0.86 | -0.21 | -166.13 | 94 | 9840.26 | 843785.85 | 2698032.82 | 30.1358 | -96.7917 | 317.22
14425 | 93.02 | 327.76 | 10279.29 | 3172.44 | -2913.12 | 4209.94 | 4.05 | 3.86 | 1.21 | 17.42 | 94 | 9838.29 | 843864.82 | 2697981.9 | 30.1361 | -96.7919 | 317.44
14520 | 93.9 | 329.1 | 10273.55 | 3253.23 | -2962.76 | 4304.74 | 1.69 | 0.93 | 1.41 | 56.62 | 95 | 9832.55 | 843945.61 | 2697932.26 | 30.1363 | -96.792 | 317.68
14613 | 94.63 | 328.9 | 10266.64 | 3332.73 | -3010.53 | 4397.47 | 0.81 | 0.78 | -0.22 | -15.27 | 93 | 9825.64 | 844025.11 | 2697884.49 | 30.1365 | -96.7922 | 317.91
14708 | 95.83 | 328.81 | 10257.98 | 3413.7 | -3059.45 | 4492.07 | 1.27 | 1.26 | -0.09 | -4.27 | 95 | 9816.98 | 844106.08 | 2697835.57 | 30.1367 | -96.7923 | 318.13
14803 | 94.26 | 330.5 | 10249.62 | 3495.36 | -3107.26 | 4586.69 | 2.42 | -1.65 | 1.78 | 132.93 | 95 | 9808.62 | 844187.74 | 2697787.76 | 30.137 | -96.7925 | 318.36
14897 | 90.71 | 329.33 | 10245.55 | 3576.6 | -3154.33 | 4680.59 | 3.98 | -3.78 | -1.24 | -161.75 | 94 | 9804.55 | 844268.98 | 2697740.69 | 30.1372 | -96.7926 | 318.59
14993 | 90.06 | 329.27 | 10244.9 | 3659.15 | -3203.34 | 4776.58 | 0.68 | -0.68 | -0.06 | -174.73 | 96 | 9803.9 | 844351.53 | 2697691.68 | 30.1374 | -96.7928 | 318.8
15088 | 89.15 | 329.46 | 10245.56 | 3740.89 | -3251.75 | 4871.58 | 0.98 | -0.96 | 0.2 | 168.21 | 95 | 9804.56 | 844433.27 | 2697643.27 | 30.1376 | -96.7929 | 319
15183 | 90.3 | 330.62 | 10246.02 | 3823.19 | -3299.19 | 4966.57 | 1.72 | 1.21 | 1.22 | 45.25 | 95 | 9805.02 | 844515.57 | 2697595.83 | 30.1379 | -96.7931 | 319.21
15277 | 93.53 | 330.85 | 10242.87 | 3905.13 | -3345.11 | 5060.49 | 3.44 | 3.44 | 0.24 | 4.07 | 94 | 9801.87 | 844597.51 | 2697549.91 | 30.1381 | -96.7932 | 319.42
15373 | 94.05 | 331 | 10236.53 | 3988.85 | -3391.66 | 5156.26 | 0.56 | 0.54 | 0.16 | 16.05 | 96 | 9795.53 | 844681.23 | 2697503.36 | 30.1383 | -96.7933 | 319.63
15468 | 95.12 | 331.72 | 10228.93 | 4071.96 | -3437.04 | 5250.91 | 1.36 | 1.13 | 0.76 | 33.82 | 95 | 9787.93 | 844764.34 | 2697457.98 | 30.1386 | -96.7935 | 319.83
15564 | 96.57 | 331.7 | 10219.16 | 4156.05 | -3482.3 | 5346.34 | 1.51 | 1.51 | -0.02 | -0.79 | 96 | 9778.16 | 844848.43 | 2697412.72 | 30.1388 | -96.7936 | 320.04
15659 | 94.71 | 329.92 | 10209.82 | 4238.58 | -3528.41 | 5440.85 | 2.7 | -1.96 | -1.87 | -136.31 | 95 | 9768.82 | 844930.96 | 2697366.61 | 30.139 | -96.7938 | 320.22
15754 | 94.89 | 329.46 | 10201.87 | 4320.3 | -3576.18 | 5535.52 | 0.52 | 0.19 | -0.48 | -68.54 | 95 | 9760.87 | 845012.68 | 2697318.84 | 30.1393 | -96.7939 | 320.38
15849 | 92.94 | 329.02 | 10195.39 | 4401.74 | -3624.66 | 5630.29 | 2.1 | -2.05 | -0.46 | -167.3 | 95 | 9754.39 | 845094.12 | 2697270.36 | 30.1395 | -96.7941 | 320.53
15944 | 92.75 | 329.17 | 10190.67 | 4483.16 | -3673.39 | 5725.17 | 0.25 | -0.2 | 0.16 | 141.74 | 95 | 9749.67 | 845175.54 | 2697221.63 | 30.1397 | -96.7942 | 320.67
16039 | 93.21 | 329.49 | 10185.73 | 4564.76 | -3721.78 | 5820.04 | 0.59 | 0.48 | 0.34 | 34.78 | 95 | 9744.73 | 845257.14 | 2697173.24 | 30.1399 | -96.7944 | 320.81
16133 | 91.56 | 331.41 | 10181.82 | 4646.45 | -3768.1 | 5913.94 | 2.69 | -1.76 | 2.04 | 130.66 | 94 | 9740.82 | 845338.83 | 2697126.92 | 30.1402 | -96.7945 | 320.96
16227 | 91.72 | 330.76 | 10179.13 | 4728.7 | -3813.53 | 6007.87 | 0.71 | 0.17 | -0.69 | -76.16 | 94 | 9738.13 | 845421.08 | 2697081.49 | 30.1404 | -96.7946 | 321.12
16321 | 91.93 | 331.33 | 10176.14 | 4810.91 | -3859.01 | 6101.8 | 0.65 | 0.22 | 0.61 | 69.76 | 94 | 9735.14 | 845503.29 | 2697036.01 | 30.1406 | -96.7948 | 321.27
16416 | 92.13 | 331.85 | 10172.77 | 4894.41 | -3904.18 | 6196.68 | 0.59 | 0.21 | 0.55 | 68.94 | 95 | 9731.77 | 845586.79 | 2696990.84 | 30.1409 | -96.7949 | 321.42
16511 | 92.52 | 331.9 | 10168.92 | 4978.13 | -3948.93 | 6291.53 | 0.41 | 0.41 | 0.05 | 7.3 | 95 | 9727.92 | 845670.51 | 2696946.09 | 30.1411 | -96.795 | 321.58
16605 | 92.3 | 331.58 | 10164.96 | 5060.85 | -3993.4 | 6385.38 | 0.41 | -0.23 | -0.34 | -124.53 | 94 | 9723.96 | 845753.23 | 2696901.62 | 30.1413 | -96.7952 | 321.72
16700 | 93.79 | 331.69 | 10159.92 | 5144.32 | -4038.46 | 6480.19 | 1.57 | 1.57 | 0.12 | 4.21 | 95 | 9718.92 | 845836.7 | 2696856.56 | 30.1415 | -96.7953 | 321.87
16794 | 94.2 | 331.04 | 10153.37 | 5226.62 | -4083.4 | 6573.91 | 0.82 | 0.44 | -0.69 | -57.67 | 94 | 9712.37 | 845919 | 2696811.62 | 30.1418 | -96.7955 | 322
16889 | 94.94 | 331.32 | 10145.8 | 5309.59 | -4129.05 | 6668.58 | 0.83 | 0.78 | 0.29 | 20.65 | 95 | 9704.8 | 846001.97 | 2696765.97 | 30.142 | -96.7956 | 322.13
16984 | 95.01 | 331.06 | 10137.56 | 5392.52 | -4174.66 | 6763.18 | 0.28 | 0.07 | -0.27 | -74.87 | 95 | 9696.56 | 846084.9 | 2696720.36 | 30.1422 | -96.7957 | 322.25
17078 | 95.82 | 331.72 | 10128.69 | 5474.67 | -4219.47 | 6856.72 | 1.11 | 0.86 | 0.7 | 39.02 | 94 | 9687.69 | 846167.05 | 2696675.55 | 30.1425 | -96.7959 | 322.38
17167 | 95.82 | 331.72 | 10119.67 | 5552.65 | -4261.42 | 6945.2 | 0 | 0 | 0 | 0 | 89 | 9678.67 | 846245.03 | 2696633.6 | 30.1427 | -96.796 | 322.5

## 12_9_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/09/2020 |  |  | Report Time: |  | 09:00-24:00
|  |  |  | Daily Cost($): |  | 13800 |  |  | Well Cost($): |  | 13800
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 105 |  | 105 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Mob/Demob |  |  |  |  | 12/09/2020 |  | 1 |  | 6000 |  | 1 | 6000
Directional Standby |  |  |  |  | 12/09/2020 |  | 3 |  | 4400 |  | 1 | 4400
Mileage |  |  |  |  | 12/09/2020 |  | 5 |  | 2.5 |  | 1200 | 3000
Perdiem |  |  |  |  | 12/09/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 13800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/09/2020 | 09:00 | 24:00 | 15 | 105 | 105 | 0 | SUR |  | 24B | Attend spud meeting, unload tools, standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_10_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/10/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 18600
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 105 |  | 105 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 12/10/2020 |  | 3 |  | 4400 |  | 1 | 4400
Perdiem |  |  |  |  | 12/10/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/10/2020 | 00:00 | 24:00 | 24 | 105 | 105 | 0 | SUR |  | 24B | Standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_11_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/11/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 25850
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 3105 |  | 3105 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 3000 |  | 3000 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 220 |  | 220 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2780 |  | 2780 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.00 / 1.17 |  | 4.00 / 1.17 |  | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 0.85 |  | 0.85 |  | SN: |  | 47245 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 3.15 |  | 3.15 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): |  | 882.54 / 258.82 |  | 882.54 / 258.82 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 10 |  | 10 |  | Grade In: |  | New
% Slide: |  | 7.33 |  | 7.33 |  | Grade Out: |  | 0-0-NO-I-TD
% Rotary: |  | 92.67 |  | 92.67 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2"- Ulterra - U616S - Jetted - 9x14s - TFA 1.35 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  |  | 8 | 2 |  |  |  |  | 37.92 |  | 39.42
13" - 4 Blade Nortrak Stabilizer (BFF) |  |  |  | 8.188 | 2.875 |  |  |  |  | 6.9 |  | 46.32
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 55.18
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 58.29
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 87.2
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 116.74
X/O- 4 1/2 IFB x 6 5/8 RegP |  |  |  | 6.563 | 2.875 |  |  |  |  | 2.78 |  | 119.52
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 394.82
394.82
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800004 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.45 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
138 | 0.14 | 122.41 | 138 | -0.09 | 0.14 | 0.1 |  | 122.41 | -0.15 | 0.1 |  | 0 | 138
229 | 0.43 | 70.01 | 229 | -0.03 | 0.56 | 0.4 |  | -70.24 | -0.31 | 0.32 |  | 0 | 91
320 | 0.48 | 80.96 | 320 | 0.14 | 1.25 | 0.11 |  | 65.65 | -0.51 | 0.05 |  | 0 | 91
415 | 0.27 | 66.04 | 414.99 | 0.3 | 1.85 | 0.24 |  | -162.4 | -0.68 | -0.22 |  | 0 | 95
510 | 0.78 | 280.11 | 509.99 | 0.5 | 1.42 | 1.07 |  | -154.5 | -0.29 | 0.54 |  | 0 | 95
604 | 1.3 | 273.35 | 603.98 | 0.68 | -0.27 | 0.57 |  | -16.67 | 0.72 | 0.55 |  | 0 | 94
699 | 1.67 | 285.84 | 698.94 | 1.12 | -2.68 | 0.52 |  | 47.54 | 2.32 | 0.39 |  | 0 | 95
793 | 2.18 | 261.96 | 792.89 | 1.24 | -5.77 | 1 |  | -69.86 | 3.99 | 0.54 |  | -25.4 | 94
887 | 2.42 | 256.47 | 886.82 | 0.53 | -9.47 | 0.35 |  | -45.32 | 5.24 | 0.26 |  | -5.84 | 94
982 | 3.53 | 247.4 | 981.69 | -1.07 | -14.12 | 1.27 |  | -27.55 | 6.22 | 1.17 |  | -9.55 | 95
1075 | 4.84 | 237.09 | 1074.44 | -4.3 | -20.06 | 1.62 |  | -35.08 | 6.43 | 1.41 |  | -11.09 | 93
1169 | 6.46 | 235.04 | 1167.98 | -9.48 | -27.72 | 1.74 |  | -8.12 | 5.83 | 1.72 |  | -2.18 | 94
1263 | 8.22 | 239.21 | 1261.21 | -15.95 | -37.83 | 1.96 |  | 18.92 | 5.36 | 1.87 |  | 4.44 | 94
1356 | 9.03 | 241.73 | 1353.15 | -22.81 | -49.97 | 0.96 |  | 26.26 | 5.58 | 0.87 |  | 2.71 | 93
1450 | 9.92 | 238.16 | 1445.87 | -30.58 | -63.34 | 1.13 |  | -35.21 | 5.64 | 0.95 |  | -3.8 | 94
1544 | 10.79 | 237.68 | 1538.34 | -39.56 | -77.66 | 0.93 |  | -5.9 | 5.13 | 0.93 |  | -0.51 | 94
1638 | 10.5 | 236.76 | 1630.72 | -48.96 | -92.26 | 0.36 |  | -150.08 | 4.41 | -0.31 |  | -0.98 | 94
1731 | 10.29 | 236.09 | 1722.19 | -58.23 | -106.24 | 0.26 |  | -150.4 | 3.47 | -0.23 |  | -0.72 | 93
1826 | 10.17 | 238.01 | 1815.68 | -67.41 | -120.39 | 0.38 |  | 110.33 | 2.71 | -0.13 |  | 2.02 | 95
1920 | 9.79 | 237.39 | 1908.26 | -76.11 | -134.16 | 0.42 |  | -164.52 | 2.16 | -0.4 |  | -0.66 | 94
2013 | 10.1 | 239.67 | 1999.87 | -84.49 | -147.86 | 0.54 |  | 52.91 | 1.86 | 0.33 |  | 2.45 | 93
2108 | 10.33 | 241.13 | 2093.36 | -92.81 | -162.51 | 0.36 |  | 49.11 | 2.09 | 0.24 |  | 1.54 | 95
2203 | 10.24 | 241.38 | 2186.83 | -100.97 | -177.38 | 0.11 |  | 153.74 | 2.57 | -0.09 |  | 0.26 | 95
2297 | 10.14 | 241.13 | 2279.35 | -108.97 | -191.96 | 0.12 |  | -156.26 | 3.04 | -0.11 |  | -0.27 | 94
2392 | 9.92 | 241.85 | 2372.9 | -116.87 | -206.5 | 0.27 |  | 150.67 | 3.57 | -0.23 |  | 0.76 | 95
2486 | 9.47 | 242.45 | 2465.56 | -124.26 | -220.5 | 0.49 |  | 167.64 | 4.27 | -0.48 |  | 0.64 | 94
2580 | 10.1 | 239.67 | 2558.19 | -132 | -234.47 | 0.84 |  | -38.24 | 4.65 | 0.67 |  | -2.96 | 94
2674 | 11.82 | 236.04 | 2650.47 | -141.54 | -249.57 | 1.97 |  | -23.65 | 4.06 | 1.83 |  | -3.86 | 94
2768 | 11.85 | 235.53 | 2742.47 | -152.38 | -265.51 | 0.12 |  | -74.25 | 2.76 | 0.03 |  | -0.54 | 94
2862 | 11.4 | 232.97 | 2834.55 | -163.44 | -280.88 | 0.73 |  | -132.35 | 1 | -0.48 |  | -2.72 | 94
2956 | 11.19 | 232.77 | 2926.72 | -174.55 | -295.56 | 0.23 |  | -169.53 | -1.17 | -0.22 |  | -0.21 | 94
3031 | 11.12 | 231.55 | 3000.31 | -183.45 | -307.02 | 0.33 |  | -107.12 | -3.06 | -0.09 |  | -1.63 | 75
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 776.25 | 14.76 | 96.83 | 243 | 882.52 | 1870.9 | 1506.1 | 0 | 77.5 | 73.2 | 70.1 | 6251.22 | 0
Run | 776.25 | 14.76 | 96.83 | 243 | 882.52 | 1870.9 | 1506.1 | 0 | 77.5 | 73.2 | 70.1 | 6251.22 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/11/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/11/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/11/2020 | 00:00 | 06:40 | 6.67 | 105 | 105 | 0 | SUR |  | 24B | Standby
12/11/2020 | 06:40 | 08:30 | 1.83 | 105 | 105 | 0 | SUR | 1: BHA #1 (Surface) | 6O | P/U BHA #1
12/11/2020 | 08:30 | 09:00 | 0.5 | 105 | 212 | 107 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/105.00 t/212.00, w/WOB 5,Flow 480, RPM 50, Press 675, Tq 2400, ROP 214.00
12/11/2020 | 09:00 | 09:10 | 0.17 | 212 | 212 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 09:10 | 09:17 | 0.12 | 212 | 303 | 91 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/212.00 t/303.00, w/WOB 5,Flow 576, RPM 50, Press 720, Tq 2400, ROP 780.00
12/11/2020 | 09:17 | 09:25 | 0.13 | 303 | 303 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 09:25 | 09:29 | 0.07 | 303 | 394 | 91 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/303.00 t/394.00, w/WOB 7,Flow 770, RPM 70, Press 1400, Tq 6000, ROP 1365.00
12/11/2020 | 09:29 | 09:35 | 0.1 | 394 | 394 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 09:35 | 09:41 | 0.1 | 394 | 489 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/394.00 t/489.00, w/WOB 7,Flow 900, RPM 100, Press 1700, Tq 6000, ROP 950.00
12/11/2020 | 09:41 | 09:47 | 0.1 | 489 | 489 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 09:47 | 09:48 | 0.02 | 489 | 500 | 11 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/489.00 t/500.00, w/WOB 7,Flow 900, RPM 100, Press 1700, Tq 6000, ROP 660.00
12/11/2020 | 09:48 | 09:53 | 0.08 | 500 | 515 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/500.00 t/515.00, TF , w/WOB 3,Flow 900, Press 1550, Tq 0, ROP 180.00
12/11/2020 | 09:53 | 09:56 | 0.05 | 515 | 584 | 69 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/515.00 t/584.00, w/WOB 7,Flow 900, RPM 100, Press 1700, Tq 6000, ROP 1380.00
12/11/2020 | 09:56 | 10:02 | 0.1 | 584 | 584 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 10:02 | 10:09 | 0.12 | 584 | 678 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/584.00 t/678.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 805.71
12/11/2020 | 10:09 | 10:15 | 0.1 | 678 | 678 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 10:15 | 10:22 | 0.12 | 678 | 773 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/678.00 t/773.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 814.29
12/11/2020 | 10:22 | 10:37 | 0.25 | 773 | 773 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 10:37 | 10:38 | 0.02 | 773 | 785 | 12 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/773.00 t/785.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 720.00
12/11/2020 | 10:38 | 10:45 | 0.12 | 785 | 805 | 20 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/785.00 t/805.00, TF , w/WOB 3,Flow 900.00, Press 1550, Tq 0, ROP 171.43
12/11/2020 | 10:45 | 10:48 | 0.05 | 805 | 867 | 62 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/805.00 t/867.00, w/WOB 17,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 1240.00
12/11/2020 | 10:48 | 10:53 | 0.08 | 867 | 867 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 10:53 | 10:56 | 0.05 | 867 | 961 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/867.00 t/961.00, w/WOB 17,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 1880.00
12/11/2020 | 10:56 | 11:02 | 0.1 | 961 | 961 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 11:02 | 11:03 | 0.02 | 961 | 965 | 4 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/961.00 t/965.00, w/WOB 17,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 240.00
12/11/2020 | 11:03 | 11:07 | 0.07 | 965 | 985 | 20 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/965.00 t/985.00, TF , w/WOB 5,Flow 900.00, Press 1550, Tq 0, ROP 300.00
12/11/2020 | 11:07 | 11:11 | 0.07 | 985 | 1056 | 71 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/985.00 t/1056.00, w/WOB 17,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 1065.00
12/11/2020 | 11:11 | 11:16 | 0.08 | 1056 | 1056 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 11:16 | 11:17 | 0.02 | 1056 | 1065 | 9 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1056.00 t/1065.00, w/WOB 17,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 540.00
12/11/2020 | 11:17 | 11:21 | 0.07 | 1065 | 1085 | 20 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1065.00 t/1085.00, TF , w/WOB 5,Flow 900.00, Press 1550, Tq 0, ROP 300.00
12/11/2020 | 11:21 | 11:24 | 0.05 | 1085 | 1149 | 64 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1085.00 t/1149.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 6000.00, ROP 1280.00
12/11/2020 | 11:24 | 11:30 | 0.1 | 1149 | 1149 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 11:30 | 11:31 | 0.02 | 1149 | 1160 | 11 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1149.00 t/1160.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 660.00
12/11/2020 | 11:31 | 11:36 | 0.08 | 1160 | 1190 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1160.00 t/1190.00, TF , w/WOB 5,Flow 900.00, Press 1650, Tq 0, ROP 360.00
12/11/2020 | 11:36 | 11:40 | 0.07 | 1190 | 1243 | 53 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1190.00 t/1243.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 795.00
12/11/2020 | 11:40 | 11:44 | 0.07 | 1243 | 1243 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 11:44 | 11:45 | 0.02 | 1243 | 1255 | 12 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1243.00 t/1255.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 720.00
12/11/2020 | 11:45 | 11:48 | 0.05 | 1255 | 1280 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1255.00 t/1280.00, TF , w/WOB 5,Flow 900.00, Press 1650, Tq 0, ROP 500.00
12/11/2020 | 11:48 | 11:52 | 0.07 | 1280 | 1337 | 57 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1280.00 t/1337.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 855.00
12/11/2020 | 11:52 | 11:57 | 0.08 | 1337 | 1337 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 11:57 | 12:03 | 0.1 | 1337 | 1430 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1337.00 t/1430.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 930.00
12/11/2020 | 12:03 | 12:07 | 0.07 | 1430 | 1430 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 12:07 | 12:08 | 0.02 | 1430 | 1440 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1430.00 t/1440.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 600.00
12/11/2020 | 12:08 | 12:14 | 0.1 | 1440 | 1465 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1440.00 t/1465.00, TF , w/WOB 5,Flow 900.00, Press 1650, Tq 0, ROP 250.00
12/11/2020 | 12:14 | 12:17 | 0.05 | 1465 | 1524 | 59 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1465.00 t/1524.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 1180.00
12/11/2020 | 12:17 | 12:22 | 0.08 | 1524 | 1524 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 12:22 | 12:27 | 0.08 | 1524 | 1618 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1524.00 t/1618.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 1128.00
12/11/2020 | 12:27 | 12:33 | 0.1 | 1618 | 1618 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 12:33 | 12:36 | 0.05 | 1618 | 1712 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1618.00 t/1712.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 1880.00
12/11/2020 | 12:36 | 12:41 | 0.08 | 1712 | 1712 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 12:41 | 12:46 | 0.08 | 1712 | 1805 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1712.00 t/1805.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1900, Tq 6000.00, ROP 1116.00
12/11/2020 | 12:46 | 12:51 | 0.08 | 1805 | 1805 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 12:51 | 12:56 | 0.08 | 1805 | 1900 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1805.00 t/1900.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 1140.00
12/11/2020 | 12:56 | 13:00 | 0.07 | 1900 | 1900 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 13:00 | 13:06 | 0.1 | 1900 | 1994 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1900.00 t/1994.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 940.00
12/11/2020 | 13:06 | 13:11 | 0.08 | 1994 | 1994 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 13:11 | 13:12 | 0.02 | 1994 | 2005 | 11 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1994.00 t/2005.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 660.00
12/11/2020 | 13:12 | 13:19 | 0.12 | 2005 | 2030 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2005.00 t/2030.00, TF , w/WOB 12,Flow 900.00, Press 2100, Tq 0.00, ROP 214.29
12/11/2020 | 13:19 | 13:24 | 0.08 | 2030 | 2087 | 57 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2030.00 t/2087.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 684.00
12/11/2020 | 13:24 | 13:28 | 0.07 | 2087 | 2087 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 13:28 | 13:33 | 0.08 | 2087 | 2182 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2087.00 t/2182.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 1140.00
12/11/2020 | 13:33 | 13:38 | 0.08 | 2182 | 2182 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 13:38 | 13:42 | 0.07 | 2182 | 2277 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2182.00 t/2277.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 1425.00
12/11/2020 | 13:42 | 13:47 | 0.08 | 2277 | 2277 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 13:47 | 13:53 | 0.1 | 2277 | 2371 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2277.00 t/2371.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2600, Tq 8500, ROP 940.00
12/11/2020 | 13:53 | 13:58 | 0.08 | 2371 | 2371 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 13:58 | 14:03 | 0.08 | 2371 | 2466 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2371.00 t/2466.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 1140.00
12/11/2020 | 14:03 | 14:08 | 0.08 | 2466 | 2466 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 14:08 | 14:13 | 0.08 | 2466 | 2560 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2466.00 t/2560.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 1128.00
12/11/2020 | 14:13 | 14:19 | 0.1 | 2560 | 2560 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 14:19 | 14:20 | 0.02 | 2560 | 2570 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2560.00 t/2570.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 600.00
12/11/2020 | 14:20 | 14:30 | 0.17 | 2570 | 2610 | 40 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2570.00 t/2610.00, TF 0.00, w/WOB 12.00,Flow 900.00, Press 1900.00, Tq 0.00, ROP 240.00
12/11/2020 | 14:30 | 14:34 | 0.07 | 2610 | 2654 | 44 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2610.00 t/2654.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 660.00
12/11/2020 | 14:34 | 14:41 | 0.12 | 2654 | 2654 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 14:41 | 14:44 | 0.05 | 2654 | 2748 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2654.00 t/2748.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 1880.00
12/11/2020 | 14:44 | 14:50 | 0.1 | 2748 | 2748 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 14:50 | 14:55 | 0.08 | 2748 | 2842 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2748.00 t/2842.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 1128.00
12/11/2020 | 14:55 | 15:00 | 0.08 | 2842 | 2842 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 15:00 | 15:08 | 0.13 | 2842 | 2936 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2842.00 t/2936.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 705.00
12/11/2020 | 15:08 | 15:13 | 0.08 | 2936 | 2936 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 15:13 | 15:18 | 0.08 | 2936 | 3030 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2936.00 t/3030.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 1128.00
12/11/2020 | 15:18 | 15:23 | 0.08 | 3030 | 3030 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/11/2020 | 15:23 | 15:30 | 0.12 | 3030 | 3105 | 75 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/3030.00 t/3105.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 6000.00, ROP 642.86
12/11/2020 | 15:30 | 15:35 | 0.08 | 3105 | 3105 | 0 | SUR | 1: BHA #1 (Surface) | 1G | Survey @ TD of surface section
12/11/2020 | 15:35 | 16:45 | 1.17 | 3105 | 3105 | 0 | SUR | 1: BHA #1 (Surface) | 5A | Circulate
12/11/2020 | 16:45 | 18:00 | 1.25 | 3105 | 3105 | 0 | SUR | 1: BHA #1 (Surface) | 6B | POOH to run surface casing
12/11/2020 | 18:00 | 18:30 | 0.5 | 3105 | 3105 | 0 | SUR | 1: BHA #1 (Surface) | 6P | Rack back BHA in derrick
12/11/2020 | 18:30 | 24:00 | 5.5 | 3105 | 3105 | 0 | SUR |  | 26A | Standby for surface casing opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_17_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/17/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 33100
|  |  |  | 24hr Summary: |  | Standby for intermediate casing opps
|  |  |  | 24hr Lookahead: |  | Skid rig, nipple up, test, P/U BHA #, TIH
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3105 |  | 3105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 3105 |  | 3105 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 0.00 / 0.17 |  | 0.00 / 0.17 |  | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  | 54317 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 0.83 |  | 0.83 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 |  |  |  | 8 | 2 |  |  |  |  | 38.02 |  | 39.52
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.38
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.49
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.4
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.94
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 112.06
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.84
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.88
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 577.18
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.98
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.97 |  | 2679.95
2679.95
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800065 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 14.76 | 96.83 | 243 | 882.52 | 1870.9 | 1506.1 | 0 | 77.5 | 73.2 | 70.1 | 6251.22 | 0
Run | 0 | 14.76 | 96.83 | 243 | 882.52 | 1870.9 | 1506.1 | 0 | 77.5 | 73.2 | 70.1 | 6251.22 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/17/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/17/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/17/2020 | 00:00 | 22:05 | 22.08 | 3105 | 3105 | 0 | INT |  | 26B | Standby for skid, nipple up and test
12/17/2020 | 22:05 | 22:25 | 0.33 | 3105 | 3105 | 0 | INT |  | 24A | L/D Motor from previous well
12/17/2020 | 22:25 | 23:10 | 0.75 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 6O | P/U and M/U Motor and Bit; Scribe; Orient; Install MWD Tool
12/17/2020 | 23:10 | 23:50 | 0.67 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH 2x Stds 6 1/2 DC and 1x Std HWDP
12/17/2020 | 23:50 | 24:00 | 0.17 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Test MWD Tool (Good)
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_18_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/18/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 40350
|  |  |  | 24hr Summary: |  | TIH w/ BHA #2; Drill Out Shoe Track and Float Equipment; FIT; Drill Ahead in Intermediate Section as per plan
|  |  |  | 24hr Lookahead: |  | Continue Drilling Intermediate Section t/ Section TD
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3105 |  | 3105 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 9292 |  | 9292 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 6187 |  | 6187 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 43
Slide Drilled (Usft): |  | 318 |  | 318 | [5 empty] | 100: | 11 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 5869 |  | 5869 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 9.10
Drlg/Circ Hrs: |  | 15.63 / 0.83 |  | 15.63 / 1.00 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 3.83 |  | 3.83 |  | SN: |  | 54317 |  | 10s Gel: | 5 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 11.8 |  | 11.8 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): |  | 497.37 / 82.96 |  | 497.37 / 82.96 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 24.83 |  | Grade In: |  | New
% Slide: |  | 5.14 |  | 5.14 |  | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
% Rotary: |  | 94.86 |  | 94.86 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 |  |  |  | 8 | 2 |  |  |  |  | 38.02 |  | 39.52
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.38
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.49
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.4
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.94
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 112.06
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.84
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.88
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 577.18
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.98
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.97 |  | 2679.95
2679.95
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800065 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3175 | 11.12 | 248.15 | 3141.64 | -197.26 | -330.79 | 2.22 |  | 98.15 | -2.95 | 0 |  | 11.53 | 144
3268 | 11.31 | 250.76 | 3232.87 | -203.6 | -347.72 | 0.58 |  | 70.76 | 0.14 | 0.2 |  | 2.81 | 93
3362 | 11.49 | 249.85 | 3325.01 | -209.86 | -365.22 | 0.27 |  | -45.43 | 3.58 | 0.19 |  | -0.97 | 94
3456 | 11.58 | 248.11 | 3417.11 | -216.61 | -382.76 | 0.38 |  | -76.35 | 6.63 | 0.1 |  | -1.85 | 94
3549 | 11.74 | 236.74 | 3508.21 | -225.28 | -399.33 | 2.47 |  | -91.6 | 7.53 | 0.17 |  | -12.23 | 93
3643 | 12.06 | 233.13 | 3600.19 | -236.41 | -415.19 | 0.86 |  | -68.51 | 5.94 | 0.34 |  | -3.84 | 94
3736 | 10.19 | 240.93 | 3691.44 | -246.24 | -430.15 | 2.58 |  | 144.96 | 5.02 | -2.01 |  | 8.39 | 93
3830 | 9.83 | 240.54 | 3784.01 | -254.23 | -444.41 | 0.39 |  | -169.53 | 5.34 | -0.38 |  | -0.41 | 94
3924 | 9.84 | 238 | 3876.63 | -262.43 | -458.2 | 0.46 |  | -89.93 | 5.24 | 0.01 |  | -2.7 | 94
4017 | 9.79 | 238.96 | 3968.27 | -270.72 | -471.72 | 0.18 |  | 107.46 | 4.92 | -0.05 |  | 1.03 | 93
4111 | 9.62 | 238.91 | 4060.92 | -278.9 | -485.29 | 0.18 |  | -177.19 | 4.73 | -0.18 |  | -0.05 | 94
4205 | 8.81 | 239.3 | 4153.71 | -286.63 | -498.21 | 0.86 |  | 175.78 | 4.59 | -0.86 |  | 0.41 | 94
4299 | 8.53 | 238.42 | 4246.63 | -293.95 | -510.34 | 0.33 |  | -155.08 | 4.4 | -0.3 |  | -0.94 | 94
4393 | 9.56 | 244.99 | 4339.47 | -300.9 | -523.35 | 1.55 |  | 48.36 | 4.98 | 1.1 |  | 6.99 | 94
4485 | 10.62 | 246.53 | 4430.04 | -307.51 | -538.05 | 1.19 |  | 15.04 | 6.71 | 1.15 |  | 1.67 | 92
4579 | 10.21 | 247.35 | 4522.49 | -314.17 | -553.68 | 0.46 |  | 160.53 | 8.87 | -0.44 |  | 0.87 | 94
4674 | 9.89 | 245.72 | 4616.04 | -320.77 | -568.89 | 0.45 |  | -139.17 | 10.87 | -0.34 |  | -1.72 | 95
4768 | 9.64 | 244.84 | 4708.67 | -327.43 | -583.37 | 0.31 |  | -149.6 | 12.44 | -0.27 |  | -0.94 | 94
4862 | 9.55 | 243.73 | 4801.36 | -334.23 | -597.49 | 0.22 |  | -116.49 | 13.71 | -0.1 |  | -1.18 | 94
4956 | 9.74 | 244.42 | 4894.03 | -341.11 | -611.65 | 0.24 |  | 31.66 | 14.94 | 0.2 |  | 0.73 | 94
5050 | 8.98 | 246.08 | 4986.78 | -347.52 | -625.53 | 0.86 |  | 161.26 | 16.42 | -0.81 |  | 1.77 | 94
5145 | 8.41 | 244.3 | 5080.69 | -353.54 | -638.57 | 0.66 |  | -155.61 | 17.82 | -0.6 |  | -1.87 | 95
5239 | 8.34 | 243.87 | 5173.68 | -359.52 | -650.88 | 0.1 |  | -138.39 | 18.89 | -0.07 |  | -0.46 | 94
5332 | 8.47 | 245.05 | 5265.68 | -365.38 | -663.15 | 0.23 |  | 53.58 | 20.03 | 0.14 |  | 1.27 | 93
5426 | 7.87 | 243.23 | 5358.73 | -371.2 | -675.17 | 0.69 |  | -157.58 | 21.09 | -0.64 |  | -1.94 | 94
5520 | 7.62 | 241.41 | 5451.87 | -377.08 | -686.39 | 0.37 |  | -136.45 | 21.69 | -0.27 |  | -1.94 | 94
5614 | 7.67 | 243.78 | 5545.04 | -382.84 | -697.49 | 0.34 |  | 82.16 | 22.33 | 0.05 |  | 2.52 | 94
5707 | 8.57 | 235.07 | 5637.11 | -389.55 | -708.74 | 1.64 |  | -58.18 | 22.23 | 0.97 |  | -9.37 | 93
5801 | 10.36 | 225.04 | 5729.83 | -399.53 | -720.46 | 2.58 |  | -47.68 | 19.55 | 1.9 |  | -10.67 | 94
5896 | 10.2 | 223.87 | 5823.31 | -411.63 | -732.34 | 0.28 |  | -128.04 | 15.11 | -0.17 |  | -1.23 | 95
5990 | 8.59 | 224.12 | 5916.04 | -422.67 | -742.99 | 1.71 |  | 178.67 | 10.97 | -1.71 |  | 0.27 | 94
6084 | 6.91 | 226.77 | 6009.18 | -431.59 | -752 | 1.83 |  | 169.3 | 7.84 | -1.79 |  | 2.82 | 94
6178 | 5.61 | 227.2 | 6102.62 | -438.58 | -759.49 | 1.38 |  | 178.15 | 5.59 | -1.38 |  | 0.46 | 94
6272 | 3.61 | 226.68 | 6196.31 | -443.73 | -765.02 | 2.13 |  | -179.06 | 3.94 | -2.13 |  | -0.55 | 94
6365 | 3.27 | 209.56 | 6289.14 | -448.05 | -768.46 | 1.16 |  | -116.73 | 1.95 | -0.37 |  | -18.41 | 93
6460 | 1.55 | 214.4 | 6384.06 | -451.47 | -770.52 | 1.82 |  | 175.67 | 0.05 | -1.81 |  | 5.09 | 95
6554 | 0.56 | 212.89 | 6478.04 | -452.9 | -771.49 | 1.05 |  | -179.15 | -0.7 | -1.05 |  | -1.61 | 94
6648 | 0.47 | 212.06 | 6572.04 | -453.61 | -771.94 | 0.1 |  | -175.68 | -1.09 | -0.1 |  | 0 | 94
6740 | 0.72 | 251.89 | 6664.03 | -454.11 | -772.69 | 0.51 |  | 79.81 | -1.14 | 0.27 |  | 0 | 92
6835 | 0.69 | 252.44 | 6759.02 | -454.47 | -773.8 | 0.03 |  | 167.56 | -0.89 | -0.03 |  | 0 | 95
6929 | 0.64 | 273.28 | 6853.02 | -454.61 | -774.87 | 0.26 |  | 111.97 | -0.47 | -0.05 |  | 0 | 94
7022 | 0.75 | 273.71 | 6946.01 | -454.54 | -775.99 | 0.12 |  | 2.93 | 0.16 | 0.12 |  | 0 | 93
7116 | 0.81 | 274.55 | 7040 | -454.45 | -777.27 | 0.06 |  | 11.21 | 0.88 | 0.06 |  | 0 | 94
7210 | 0.98 | 286.9 | 7133.99 | -454.16 | -778.7 | 0.27 |  | 54.9 | 1.85 | 0.18 |  | 0 | 94
7304 | 1.06 | 295.42 | 7227.98 | -453.56 | -780.26 | 0.18 |  | 66.49 | 3.16 | 0.09 |  | 0 | 94
7398 | 0.49 | 34.64 | 7321.97 | -452.85 | -780.81 | 1.32 |  | 156.98 | 4.05 | -0.61 |  | 0 | 94
7492 | 0.86 | 96.81 | 7415.96 | -452.61 | -779.88 | 0.81 |  | 96.64 | 3.8 | 0.39 |  | 0 | 94
7585 | 0.61 | 106.78 | 7508.96 | -452.83 | -778.72 | 0.3 |  | 157.83 | 3.01 | -0.27 |  | 0 | 93
7680 | 0.4 | 148.41 | 7603.95 | -453.26 | -778.06 | 0.43 |  | 139.49 | 2.31 | -0.22 |  | 0 | 95
7773 | 0.37 | 196.2 | 7696.95 | -453.82 | -777.97 | 0.34 |  | 118.92 | 1.78 | -0.03 |  | 0 | 93
7867 | 0.47 | 331.42 | 7790.95 | -453.78 | -778.24 | 0.83 |  | 154.8 | 1.96 | 0.11 |  | 0 | 94
7961 | 0.83 | 318.86 | 7884.94 | -452.93 | -778.87 | 0.41 |  | -27.95 | 3.01 | 0.38 |  | 0 | 94
8054 | 0.96 | 309.05 | 7977.93 | -451.93 | -779.92 | 0.22 |  | -54.66 | 4.4 | 0.14 |  | 0 | 93
8147 | 0.77 | 0.9 | 8070.92 | -450.81 | -780.52 | 0.83 |  | 128.65 | 5.66 | -0.2 |  | 0 | 93
8242 | 0.84 | 358.91 | 8165.91 | -449.48 | -780.52 | 0.08 |  | -22.77 | 6.82 | 0.07 |  | 0 | 95
8336 | 1.08 | 331.97 | 8259.9 | -448.01 | -780.95 | 0.54 |  | -75.91 | 8.3 | 0.26 |  | 0 | 94
8430 | 0.1 | 162.72 | 8353.9 | -447.3 | -781.34 | 1.25 |  | -179.09 | 9.11 | -1.04 |  | 0 | 94
8525 | 0.42 | 153.4 | 8448.89 | -447.69 | -781.16 | 0.34 |  | -12.21 | 8.68 | 0.34 |  | 0 | 95
8618 | 0.11 | 135.13 | 8541.89 | -448.06 | -780.95 | 0.34 |  | -173.76 | 8.25 | -0.33 |  | 0 | 93
8712 | 0.24 | 19.63 | 8635.89 | -447.94 | -780.82 | 0.32 |  | -134.56 | 8.29 | 0.14 |  | 0 | 94
8807 | 0.95 | 321.73 | 8730.89 | -447.13 | -781.24 | 0.89 |  | -71.78 | 9.2 | 0.75 |  | 0 | 95
8901 | 1.15 | 4.36 | 8824.87 | -445.58 | -781.65 | 0.84 |  | 97.59 | 10.75 | 0.21 |  | 0 | 94
8996 | 0.85 | 125.69 | 8919.87 | -445.04 | -781 | 1.84 |  | 155.48 | 10.89 | -0.32 |  | 0 | 95
9090 | 0.58 | 160.8 | 9013.86 | -445.9 | -780.28 | 0.53 |  | 138.38 | 9.78 | -0.29 |  | 0 | 94
9185 | 0.47 | 350.87 | 9108.86 | -445.97 | -780.18 | 1.1 |  | -175.49 | 9.67 | -0.12 |  | 0 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 379.57 | 36.12 | 78.41 | 209 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 0
Run | 379.57 | 36.12 | 78.41 | 209 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 10000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/18/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/18/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/18/2020 | 00:00 | 01:05 | 1.08 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH t/ 2,648
12/18/2020 | 01:05 | 01:25 | 0.33 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | C/O Agitator
12/18/2020 | 01:25 | 01:40 | 0.25 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH t/ 2,857
12/18/2020 | 01:40 | 02:15 | 0.58 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 6I | BOP Drill; Flow Check @ Rotating Head Installation
12/18/2020 | 02:15 | 02:25 | 0.17 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 3C | Wash Down f/ 2,857 t/ 3,013; Tag Cement @ 3,013
12/18/2020 | 02:25 | 03:05 | 0.67 | 3105 | 3105 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Drlg Out Shoe Track & Float Equipment
12/18/2020 | 03:05 | 03:08 | 0.05 | 3105 | 3115 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3105.00 t/3115.00, w/WOB 20,Flow 420, RPM 30, Press 1500, Tq 5000, ROP 200.00
12/18/2020 | 03:08 | 03:25 | 0.28 | 3115 | 3115 | 0 | INT | 2: BHA #2 (Intermediate) | 15D | FIT t/ 382 psi
12/18/2020 | 03:25 | 03:38 | 0.22 | 3115 | 3150 | 35 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3115.00 t/3150.00, w/WOB 25,Flow 420.00, RPM 40, Press 1600, Tq 7000, ROP 161.54
12/18/2020 | 03:38 | 03:43 | 0.08 | 3150 | 3150 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 03:43 | 03:54 | 0.18 | 3150 | 3172 | 22 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3150.00 t/3172.00, TF , w/WOB 28,Flow 420.00, Press 1500.00, Tq 0, ROP 120.00
12/18/2020 | 03:54 | 04:09 | 0.25 | 3172 | 3244 | 72 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3172.00 t/3244.00, w/WOB 30,Flow 420.00, RPM 40, Press 1600, Tq 7000, ROP 288.00
12/18/2020 | 04:09 | 04:12 | 0.05 | 3244 | 3244 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 04:12 | 04:20 | 0.13 | 3244 | 3337 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3244.00 t/3337.00, w/WOB 28,Flow 800, RPM 80, Press 4100, Tq 10000, ROP 697.50
12/18/2020 | 04:20 | 04:23 | 0.05 | 3337 | 3337 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 04:23 | 04:30 | 0.12 | 3337 | 3431 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3337.00 t/3431.00, w/WOB 30,Flow 800.00, RPM 80.00, Press 4200, Tq 10000.00, ROP 805.71
12/18/2020 | 04:30 | 04:35 | 0.08 | 3431 | 3431 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 04:35 | 04:42 | 0.12 | 3431 | 3525 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3431.00 t/3525.00, w/WOB 35,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000, ROP 805.71
12/18/2020 | 04:42 | 04:46 | 0.07 | 3525 | 3525 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 04:46 | 04:48 | 0.03 | 3525 | 3527 | 2 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3525.00 t/3527.00, w/WOB 35,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000, ROP 60.00
12/18/2020 | 04:48 | 05:00 | 0.2 | 3527 | 3545 | 18 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3527.00 t/3545.00, w/WOB 20,Flow 800.00, RPM 0, Press 3800, Tq 0, ROP 90.00
12/18/2020 | 05:00 | 05:09 | 0.15 | 3545 | 3618 | 73 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3545.00 t/3618.00, w/WOB 35,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000, ROP 486.67
12/18/2020 | 05:09 | 05:12 | 0.05 | 3618 | 3618 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 05:12 | 05:18 | 0.1 | 3618 | 3712 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3618.00 t/3712.00, w/WOB 38,Flow 800.00, RPM 80.00, Press 4000, Tq 12000.00, ROP 940.00
12/18/2020 | 05:18 | 05:22 | 0.07 | 3712 | 3712 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 05:22 | 05:35 | 0.22 | 3712 | 3732 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3712.00 t/3732.00, TF , w/WOB 20,Flow 800.00, Press 4000, Tq 0, ROP 92.31
12/18/2020 | 05:35 | 05:42 | 0.12 | 3732 | 3805 | 73 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3732.00 t/3805.00, w/WOB 38,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 625.71
12/18/2020 | 05:42 | 05:47 | 0.08 | 3805 | 3805 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 05:47 | 05:52 | 0.08 | 3805 | 3899 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3805.00 t/3899.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 1128.00
12/18/2020 | 05:52 | 05:57 | 0.08 | 3899 | 3899 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 05:57 | 06:03 | 0.1 | 3899 | 3993 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3899.00 t/3993.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 940.00
12/18/2020 | 06:03 | 06:08 | 0.08 | 3993 | 3993 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 06:08 | 06:15 | 0.12 | 3993 | 4086 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3993.00 t/4086.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 797.14
12/18/2020 | 06:15 | 06:20 | 0.08 | 4086 | 4086 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 06:20 | 06:25 | 0.08 | 4086 | 4180 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4086.00 t/4180.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 1128.00
12/18/2020 | 06:25 | 06:30 | 0.08 | 4180 | 4180 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 06:30 | 06:36 | 0.1 | 4180 | 4274 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4180.00 t/4274.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 940.00
12/18/2020 | 06:36 | 06:40 | 0.07 | 4274 | 4274 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 06:40 | 06:47 | 0.12 | 4274 | 4368 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4274.00 t/4368.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 805.71
12/18/2020 | 06:47 | 06:52 | 0.08 | 4368 | 4368 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 06:52 | 06:55 | 0.05 | 4368 | 4380 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4368.00 t/4380.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 240.00
12/18/2020 | 06:55 | 07:01 | 0.1 | 4380 | 4400 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/4380.00 t/4400.00, TF 30.00, w/WOB 12.00,Flow 800.00, Press 3800.00, Tq 0.00, ROP 200.00
12/18/2020 | 07:01 | 07:08 | 0.12 | 4400 | 4462 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4400.00 t/4462.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 531.43
12/18/2020 | 07:08 | 07:13 | 0.08 | 4462 | 4462 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 07:13 | 07:20 | 0.12 | 4462 | 4554 | 92 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4462.00 t/4554.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 788.57
12/18/2020 | 07:20 | 07:25 | 0.08 | 4554 | 4554 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 07:25 | 07:31 | 0.1 | 4554 | 4648 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4554.00 t/4648.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 12000.00, ROP 940.00
12/18/2020 | 07:31 | 07:35 | 0.07 | 4648 | 4648 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 07:35 | 07:42 | 0.12 | 4648 | 4743 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4648.00 t/4743.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 814.29
12/18/2020 | 07:42 | 07:47 | 0.08 | 4743 | 4743 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 07:47 | 07:55 | 0.13 | 4743 | 4837 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4743.00 t/4837.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 705.00
12/18/2020 | 07:55 | 08:00 | 0.08 | 4837 | 4837 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 08:00 | 08:06 | 0.1 | 4837 | 4931 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4837.00 t/4931.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 940.00
12/18/2020 | 08:06 | 08:11 | 0.08 | 4931 | 4931 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 08:11 | 08:18 | 0.12 | 4931 | 5025 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4931.00 t/5025.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 805.71
12/18/2020 | 08:18 | 08:23 | 0.08 | 5025 | 5025 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 08:23 | 08:30 | 0.12 | 5025 | 5119 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5025.00 t/5119.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 805.71
12/18/2020 | 08:30 | 08:35 | 0.08 | 5119 | 5119 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 08:35 | 08:42 | 0.12 | 5119 | 5214 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5119.00 t/5214.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 814.29
12/18/2020 | 08:42 | 08:47 | 0.08 | 5214 | 5214 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 08:47 | 08:55 | 0.13 | 5214 | 5308 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5214.00 t/5308.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4200.00, Tq 14000, ROP 705.00
12/18/2020 | 08:55 | 09:05 | 0.17 | 5308 | 5308 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 09:05 | 09:11 | 0.1 | 5308 | 5401 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5308.00 t/5401.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 14000.00, ROP 930.00
12/18/2020 | 09:11 | 09:15 | 0.07 | 5401 | 5401 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 09:15 | 09:25 | 0.17 | 5401 | 5495 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5401.00 t/5495.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 14000.00, ROP 564.00
12/18/2020 | 09:25 | 09:30 | 0.08 | 5495 | 5495 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 09:30 | 09:32 | 0.03 | 5495 | 5510 | 15 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5495.00 t/5510.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 14000.00, ROP 450.00
12/18/2020 | 09:32 | 09:45 | 0.22 | 5510 | 5528 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5510.00 t/5528.00, TF -60.00, w/WOB 18.00,Flow 800.00, Press 3800.00, Tq 0.00, ROP 83.08
12/18/2020 | 09:45 | 09:56 | 0.18 | 5528 | 5589 | 61 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5528.00 t/5589.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 14000.00, ROP 332.73
12/18/2020 | 09:56 | 10:00 | 0.07 | 5589 | 5589 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 10:00 | 10:08 | 0.13 | 5589 | 5683 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5589.00 t/5683.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 705.00
12/18/2020 | 10:08 | 10:13 | 0.08 | 5683 | 5683 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 10:13 | 10:16 | 0.05 | 5683 | 5700 | 17 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5683.00 t/5700.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 340.00
12/18/2020 | 10:16 | 10:36 | 0.33 | 5700 | 5730 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5700.00 t/5730.00, TF , w/WOB 20,Flow 800.00, Press 3800, Tq 0, ROP 90.00
12/18/2020 | 10:36 | 10:45 | 0.15 | 5730 | 5776 | 46 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5730.00 t/5776.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 306.67
12/18/2020 | 10:45 | 10:50 | 0.08 | 5776 | 5776 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 10:50 | 10:59 | 0.15 | 5776 | 5870 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5776.00 t/5870.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 626.67
12/18/2020 | 10:59 | 11:04 | 0.08 | 5870 | 5870 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 11:04 | 11:15 | 0.18 | 5870 | 5965 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5870.00 t/5965.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 518.18
12/18/2020 | 11:15 | 11:20 | 0.08 | 5965 | 5965 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 11:20 | 11:23 | 0.05 | 5965 | 5975 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5965.00 t/5975.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 200.00
12/18/2020 | 11:23 | 11:34 | 0.18 | 5975 | 5995 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5975.00 t/5995.00, TF , w/WOB 20,Flow 800.00, Press 3800, Tq 0, ROP 109.09
12/18/2020 | 11:34 | 11:43 | 0.15 | 5995 | 6059 | 64 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5995.00 t/6059.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 426.67
12/18/2020 | 11:43 | 11:48 | 0.08 | 6059 | 6059 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 11:48 | 11:51 | 0.05 | 6059 | 6070 | 11 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6059.00 t/6070.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 220.00
12/18/2020 | 11:51 | 12:01 | 0.17 | 6070 | 6085 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6070.00 t/6085.00, TF , w/WOB 20,Flow 800.00, Press 3800, Tq 0, ROP 90.00
12/18/2020 | 12:01 | 12:10 | 0.15 | 6085 | 6153 | 68 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6085.00 t/6153.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000, ROP 453.33
12/18/2020 | 12:10 | 12:15 | 0.08 | 6153 | 6153 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 12:15 | 12:17 | 0.03 | 6153 | 6165 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6153.00 t/6165.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 360.00
12/18/2020 | 12:17 | 12:34 | 0.28 | 6165 | 6185 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6165.00 t/6185.00, TF 160.00, w/WOB 20.00,Flow 800.00, Press 3800.00, Tq 0.00, ROP 70.59
12/18/2020 | 12:34 | 12:45 | 0.18 | 6185 | 6247 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6185.00 t/6247.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 338.18
12/18/2020 | 12:45 | 12:50 | 0.08 | 6247 | 6247 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 12:50 | 12:53 | 0.05 | 6247 | 6260 | 13 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6247.00 t/6260.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 260.00
12/18/2020 | 12:53 | 13:09 | 0.27 | 6260 | 6280 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6260.00 t/6280.00, TF 160.00, w/WOB 20.00,Flow 800.00, Press 3800.00, Tq 0.00, ROP 75.00
12/18/2020 | 13:09 | 13:15 | 0.1 | 6280 | 6341 | 61 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6280.00 t/6341.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 610.00
12/18/2020 | 13:15 | 13:20 | 0.08 | 6341 | 6341 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 13:20 | 13:32 | 0.2 | 6341 | 6434 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6341.00 t/6434.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 465.00
12/18/2020 | 13:32 | 13:37 | 0.08 | 6434 | 6434 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 13:37 | 13:40 | 0.05 | 6434 | 6450 | 16 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6434.00 t/6450.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 320.00
12/18/2020 | 13:40 | 13:55 | 0.25 | 6450 | 6475 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6450.00 t/6475.00, TF 160.00, w/WOB 40.00,Flow 800.00, Press 4600.00, Tq 17000.00, ROP 100.00
12/18/2020 | 13:55 | 14:05 | 0.17 | 6475 | 6529 | 54 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6475.00 t/6529.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4600.00, Tq 17000.00, ROP 324.00
12/18/2020 | 14:05 | 14:10 | 0.08 | 6529 | 6529 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 14:10 | 14:20 | 0.17 | 6529 | 6623 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6529.00 t/6623.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 564.00
12/18/2020 | 14:20 | 14:25 | 0.08 | 6623 | 6623 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 14:25 | 14:38 | 0.22 | 6623 | 6717 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6623.00 t/6717.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 433.85
12/18/2020 | 14:38 | 14:44 | 0.1 | 6717 | 6717 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 14:44 | 14:53 | 0.15 | 6717 | 6809 | 92 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6717.00 t/6809.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 613.33
12/18/2020 | 14:53 | 14:58 | 0.08 | 6809 | 6809 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 14:58 | 15:09 | 0.18 | 6809 | 6904 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6809.00 t/6904.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 518.18
12/18/2020 | 15:09 | 15:15 | 0.1 | 6904 | 6904 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 15:15 | 15:26 | 0.18 | 6904 | 6998 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6904.00 t/6998.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 512.73
12/18/2020 | 15:26 | 15:30 | 0.07 | 6998 | 6998 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 15:30 | 15:41 | 0.18 | 6998 | 7091 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6998.00 t/7091.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 507.27
12/18/2020 | 15:41 | 15:45 | 0.07 | 7091 | 7091 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 15:45 | 15:55 | 0.17 | 7091 | 7158 | 67 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7091.00 t/7158.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 402.00
12/18/2020 | 15:55 | 16:00 | 0.08 | 7158 | 7158 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 16:00 | 16:09 | 0.15 | 7158 | 7279 | 121 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7158.00 t/7279.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300, Tq 18000, ROP 806.67
12/18/2020 | 16:09 | 16:15 | 0.1 | 7279 | 7279 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 16:15 | 16:24 | 0.15 | 7279 | 7373 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7279.00 t/7373.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300.00, Tq 18000.00, ROP 626.67
12/18/2020 | 16:24 | 16:30 | 0.1 | 7373 | 7373 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 16:30 | 16:33 | 0.05 | 7373 | 7385 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7373.00 t/7385.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300.00, Tq 18000.00, ROP 240.00
12/18/2020 | 16:33 | 16:49 | 0.27 | 7385 | 7405 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7385.00 t/7405.00, TF , w/WOB 20.00,Flow 800.00, Press 4650, Tq 0.00, ROP 75.00
12/18/2020 | 16:49 | 16:59 | 0.17 | 7405 | 7467 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7405.00 t/7467.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300.00, Tq 18000.00, ROP 372.00
12/18/2020 | 16:59 | 17:10 | 0.18 | 7467 | 7467 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 17:10 | 17:17 | 0.12 | 7467 | 7561 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7467.00 t/7561.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5300.00, Tq 18000.00, ROP 805.71
12/18/2020 | 17:17 | 17:23 | 0.1 | 7561 | 7561 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 17:23 | 17:30 | 0.12 | 7561 | 7654 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7561.00 t/7654.00, w/WOB 40,Flow 800.00, RPM 80, Press 5200, Tq 18000, ROP 797.14
12/18/2020 | 17:30 | 17:35 | 0.08 | 7654 | 7654 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 17:35 | 17:49 | 0.23 | 7654 | 7749 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7654.00 t/7749.00, w/WOB 40,Flow 800.00, RPM 80, Press 5200, Tq 18000, ROP 407.14
12/18/2020 | 17:49 | 17:51 | 0.03 | 7749 | 7749 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 17:51 | 18:02 | 0.18 | 7749 | 7842 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7749.00 t/7842.00, w/WOB 40,Flow 800.00, RPM 80, Press 5200, Tq 19500, ROP 507.27
12/18/2020 | 18:02 | 18:05 | 0.05 | 7842 | 7842 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 18:05 | 18:20 | 0.25 | 7842 | 7936 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7842.00 t/7936.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 19500.00, ROP 376.00
12/18/2020 | 18:20 | 18:25 | 0.08 | 7936 | 7936 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 18:25 | 18:39 | 0.23 | 7936 | 8030 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7936.00 t/8030.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 19500.00, ROP 402.86
12/18/2020 | 18:39 | 18:42 | 0.05 | 8030 | 8030 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 18:42 | 18:55 | 0.22 | 8030 | 8123 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8030.00 t/8123.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 19500.00, ROP 429.23
12/18/2020 | 18:55 | 18:59 | 0.07 | 8123 | 8123 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 18:59 | 19:02 | 0.05 | 8123 | 8126 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8123.00 t/8126.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 19500.00, ROP 60.00
12/18/2020 | 19:02 | 19:22 | 0.33 | 8126 | 8144 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8126.00 t/8144.00, TF , w/WOB 30,Flow 800.00, Press 4600, Tq 0, ROP 54.00
12/18/2020 | 19:22 | 19:38 | 0.27 | 8144 | 8216 | 72 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8144.00 t/8216.00, w/WOB 40,Flow 800.00, RPM 80, Press 5100, Tq 20000, ROP 270.00
12/18/2020 | 19:38 | 19:41 | 0.05 | 8216 | 8216 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 19:41 | 19:55 | 0.23 | 8216 | 8311 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8216.00 t/8311.00, w/WOB 40,Flow 800.00, RPM 80, Press 5100, Tq 20000, ROP 407.14
12/18/2020 | 19:55 | 19:58 | 0.05 | 8311 | 8311 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 19:58 | 20:12 | 0.23 | 8311 | 8405 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8311.00 t/8405.00, w/WOB 40,Flow 800.00, RPM 80, Press 5100, Tq 20000, ROP 402.86
12/18/2020 | 20:12 | 20:15 | 0.05 | 8405 | 8405 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 20:15 | 20:18 | 0.05 | 8405 | 8409 | 4 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8405.00 t/8409.00, w/WOB 40,Flow 800.00, RPM 80, Press 5100, Tq 20000, ROP 80.00
12/18/2020 | 20:18 | 20:40 | 0.37 | 8409 | 8431 | 22 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8409.00 t/8431.00, TF , w/WOB 18,Flow 800.00, Press 4600.00, Tq 0.00, ROP 60.00
12/18/2020 | 20:40 | 20:50 | 0.17 | 8431 | 8499 | 68 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8431.00 t/8499.00, w/WOB 42,Flow 800.00, RPM 80, Press 5000, Tq 22000, ROP 408.00
12/18/2020 | 20:50 | 20:53 | 0.05 | 8499 | 8499 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 20:53 | 21:07 | 0.23 | 8499 | 8594 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8499.00 t/8594.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200, Tq 22000.00, ROP 407.14
12/18/2020 | 21:07 | 21:10 | 0.05 | 8594 | 8594 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 21:10 | 21:24 | 0.23 | 8594 | 8687 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8594.00 t/8687.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200, Tq 22000.00, ROP 398.57
12/18/2020 | 21:24 | 21:27 | 0.05 | 8687 | 8687 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 21:27 | 21:41 | 0.23 | 8687 | 8781 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8687.00 t/8781.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200, Tq 22000.00, ROP 402.86
12/18/2020 | 21:41 | 21:44 | 0.05 | 8781 | 8781 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 21:44 | 21:57 | 0.22 | 8781 | 8876 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8781.00 t/8876.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200, Tq 22000.00, ROP 438.46
12/18/2020 | 21:57 | 22:00 | 0.05 | 8876 | 8876 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 22:00 | 22:02 | 0.03 | 8876 | 8879 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8876.00 t/8879.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200, Tq 22000.00, ROP 90.00
12/18/2020 | 22:02 | 22:22 | 0.33 | 8879 | 8901 | 22 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8879.00 t/8901.00, TF , w/WOB 18,Flow 800.00, Press 4650, Tq 0, ROP 66.00
12/18/2020 | 22:22 | 22:35 | 0.22 | 8901 | 8970 | 69 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8901.00 t/8970.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 318.46
12/18/2020 | 22:35 | 22:38 | 0.05 | 8970 | 8970 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 22:38 | 22:40 | 0.03 | 8970 | 8973 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8970.00 t/8973.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 90.00
12/18/2020 | 22:40 | 23:00 | 0.33 | 8973 | 8999 | 26 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8973.00 t/8999.00, TF , w/WOB 18,Flow 800.00, Press 4650, Tq 0, ROP 78.00
12/18/2020 | 23:00 | 23:12 | 0.2 | 8999 | 9065 | 66 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8999.00 t/9065.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 330.00
12/18/2020 | 23:12 | 23:15 | 0.05 | 9065 | 9065 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 23:15 | 23:32 | 0.28 | 9065 | 9159 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9065.00 t/9159.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 331.76
12/18/2020 | 23:32 | 23:35 | 0.05 | 9159 | 9159 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 23:35 | 23:50 | 0.25 | 9159 | 9254 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9159.00 t/9254.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 380.00
12/18/2020 | 23:50 | 23:53 | 0.05 | 9254 | 9254 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/18/2020 | 23:53 | 24:00 | 0.12 | 9254 | 9292 | 38 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9254.00 t/9292.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 325.71
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_19_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/19/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 47600
|  |  |  | 24hr Summary: |  | Drilling Intermediate Section as per plan t/ Section TD;TOH; L/D Directional BHA; Standby for Casing and Cement Ops
|  |  |  | 24hr Lookahead: |  | Standby for Casing and Cement Ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9292 |  | 3105 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 9937 |  | 9937 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 645 |  | 6832 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 43
Slide Drilled (Usft): |  | 170 |  | 488 | [5 empty] | 100: | 11 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 475 |  | 6344 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 9.10
Drlg/Circ Hrs: |  | 8.82 / 0.07 |  | 24.45 / 1.07 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 6.9 |  | 10.73 |  | SN: |  | 54317 |  | 10s Gel: | 5 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 1.92 |  | 13.72 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): |  | 247.83 / 24.64 |  | 462.50 / 45.47 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 21.5 |  | 46.33 |  | Grade In: |  | New
% Slide: |  | 26.36 |  | 7.14 |  | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
% Rotary: |  | 73.64 |  | 92.86 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 |  |  |  | 8 | 2 |  |  |  |  | 38.02 |  | 39.52
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.38
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.49
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.4
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.94
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 112.06
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.84
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.88
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 577.18
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.98
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.97 |  | 2679.95
2679.95
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800065 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9279 | 1.25 | 359.08 | 9202.85 | -444.56 | -780.26 | 0.84 |  | 13.1 | 10.93 | 0.83 |  | 0 | 94
9372 | 1.42 | 20.23 | 9295.82 | -442.47 | -779.88 | 0.56 |  | 81.74 | 12.54 | 0.18 |  | 0 | 93
9466 | 0.94 | 105.07 | 9389.81 | -441.57 | -778.73 | 1.73 |  | 144.96 | 12.73 | -0.51 |  | 0 | 94
9561 | 0.55 | 123.32 | 9484.8 | -442.03 | -777.6 | 0.48 |  | 157.59 | 11.77 | -0.41 |  | 0 | 95
9654 | 0.14 | 63.27 | 9577.8 | -442.22 | -777.12 | 0.53 |  | -165.82 | 11.36 | -0.44 |  | 0 | 93
9748 | 2.98 | 314.08 | 9671.76 | -440.47 | -778.78 | 3.22 |  | -111.69 | 13.71 | 3.02 |  | 0 | 94
9842 | 5.54 | 320.77 | 9765.49 | -435.25 | -783.4 | 2.77 |  | 14.34 | 20.55 | 2.72 |  | 7.12 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 73.16 | 36.12 | 78.41 | 209 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 0
Run | 279.43 | 36.12 | 78.41 | 209 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 10000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/19/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/19/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/19/2020 | 00:00 | 00:17 | 0.28 | 9292 | 9348 | 56 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9292.00 t/9348.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 197.65
12/19/2020 | 00:17 | 00:20 | 0.05 | 9348 | 9348 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 00:20 | 00:24 | 0.07 | 9348 | 9349 | 1 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9348.00 t/9349.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 15.00
12/19/2020 | 00:24 | 01:20 | 0.93 | 9349 | 9375 | 26 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9349.00 t/9375.00, TF , w/WOB 22,Flow 800.00, Press 4600, Tq 0, ROP 27.86
12/19/2020 | 01:20 | 01:38 | 0.3 | 9375 | 9441 | 66 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9375.00 t/9441.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 220.00
12/19/2020 | 01:38 | 01:43 | 0.08 | 9441 | 9441 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 01:43 | 02:24 | 0.68 | 9441 | 9469 | 28 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9441.00 t/9469.00, TF , w/WOB 25,Flow 800.00, Press 5200.00, Tq 0, ROP 40.98
12/19/2020 | 02:24 | 02:39 | 0.25 | 9469 | 9536 | 67 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9469.00 t/9536.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 268.00
12/19/2020 | 02:39 | 02:42 | 0.05 | 9536 | 9536 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 02:42 | 03:02 | 0.33 | 9536 | 9630 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9536.00 t/9630.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 282.00
12/19/2020 | 03:02 | 03:05 | 0.05 | 9630 | 9630 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 03:05 | 03:25 | 0.33 | 9630 | 9723 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9630.00 t/9723.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 279.00
12/19/2020 | 03:25 | 03:32 | 0.12 | 9723 | 9723 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 03:32 | 04:38 | 1.1 | 9723 | 9783 | 60 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9723.00 t/9783.00, TF , w/WOB 22,Flow 800.00, Press 4700, Tq 0, ROP 54.55
12/19/2020 | 04:38 | 04:48 | 0.17 | 9783 | 9783 | 0 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9723.00 t/9783.00, TF 320.00, w/WOB 22.00,Flow 800.00, Press 4700.00, Tq 0.00, ROP 360.00
12/19/2020 | 04:48 | 04:50 | 0.03 | 9783 | 9817 | 34 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9783.00 t/9817.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 1020.00
12/19/2020 | 04:50 | 04:55 | 0.08 | 9817 | 9817 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 04:55 | 05:14 | 0.32 | 9817 | 9881 | 64 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9817.00 t/9881.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 5200.00, Tq 22000.00, ROP 202.11
12/19/2020 | 05:14 | 07:09 | 1.92 | 9881 | 9911 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9881.00 t/9911.00, TF , w/WOB 22.00,Flow 800.00, Press 4700.00, Tq 0.00, ROP 15.65
12/19/2020 | 07:09 | 07:15 | 0.1 | 9911 | 9911 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/19/2020 | 07:15 | 09:21 | 2.1 | 9911 | 9937 | 26 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9911.00 t/9940.00, TF , w/WOB 22.00,Flow 800.00, Press 4700.00, Tq 0.00, ROP 13.81
12/19/2020 | 09:21 | 09:25 | 0.07 | 9937 | 9937 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | MWD survey @ 9868 TD of intermediate section
12/19/2020 | 09:25 | 20:30 | 11.08 | 9937 | 9937 | 0 | INT | 2: BHA #2 (Intermediate) | 6K | L/D 5 DP
12/19/2020 | 20:30 | 21:30 | 1 | 9937 | 9937 | 0 | INT | 2: BHA #2 (Intermediate) | 6P | L/D BHA
12/19/2020 | 21:30 | 24:00 | 2.5 | 9937 | 9937 | 0 | INT |  | 24B | Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_20_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/20/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 52400
|  |  |  | 24hr Summary: |  | Standby for Casing and Cement Ops
|  |  |  | 24hr Lookahead: |  | Standby for Casing and Cement Ops; P/U BHA #3; P/U DP; Drill Out Shoe Track and Float Equipment; Build Curve
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9937 |  |  |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 9937 |  | 9937 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 43
Slide Drilled (Usft): | [9 empty] | 100: | 11 | Chlorides: | 49000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 9.10
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 5 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 36.12 | 78.41 | 209 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 0
Run | 0 | 36.12 | 78.41 | 209 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 10000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5792 |  | 5500 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 12/20/2020 |  | 4 |  | 100 |  | 4 | 400
Directional Standby |  |  |  |  | 12/20/2020 |  | 3 |  | 4400 |  | 1 | 4400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/20/2020 | 00:00 | 24:00 | 24 | 9937 | 9937 | 0 | INT |  | 24B | Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_21_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/21/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17750 |  |  | Well Cost($): |  | 70150
|  |  |  | 24hr Summary: |  | Standby for Casing and Cement Ops; Handle BHA; P/U 4 1/2 DP; Drill Out Shoe Track and Float Equipment; Perform FIT
|  |  |  | 24hr Lookahead: |  | Build and Land Curve; Drill Ahead in Lateral Section
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9937 |  | 9937 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 9947 |  | 9947 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 10 |  | 10 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 43
Slide Drilled (Usft): | [9 empty] | 100: | 11 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 10 |  | 10 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 9.10
Drlg/Circ Hrs: |  | 0.20 / 1.58 |  | 0.20 / 1.58 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  | 13446789 |  | 10s Gel: | 5 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 0.2 |  | 0.2 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): |  | 50.00 / 0.00 |  | 50.00 / 0.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 16 |  | 16 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
% Rotary: |  | 100 |  | 100 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Jeff Cambpell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | 5 | 2 |  |  |  |  | 34.11 |  | 34.86
BTI Valve |  |  |  | 5 | 2.5 |  |  |  |  | 2.37 |  | 37.23
5" NMPDC |  |  |  | 5.063 | 2.563 |  |  |  |  | 9.46 |  | 46.69
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 49.18
5" NMDC |  |  |  | 5 | 2.25 |  |  |  |  | 30.43 |  | 79.61
5" NMDC |  |  |  | 5.063 | 2.5 |  |  |  |  | 29.89 |  | 109.5
Tomax Thruster |  |  |  | 5 | 2 |  |  |  |  | 17.75 |  | 127.25
X/O- DS42B x XT39P |  |  |  | 5.375 | 2.25 |  |  |  |  | 3.08 |  | 130.33
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2686.92
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.51 |  | 2710.43
2710.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9868 | 5.35 | 319.06 | 9791.37 | -433.37 | -784.99 | 0.96 |  | -140.35 | 22.98 | -0.73 |  | -6.58 | 26
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 9.68 | 36.12 | 78.41 | 612 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 0
Run | 9.68 | 36.12 | 78.41 | 612 | 784.49 | 4569.9 | 3806.12 | 248 | 211.58 | 188.21 | 167.3 | 16323.17 | 10000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/21/2020 |  | 2 |  | 6850 |  | 1 | 6850
5 Premium Motor Stator Reline |  |  |  |  | 12/21/2020 |  | 6 |  | 10500 |  | 1 | 10500
Perdiem |  |  |  |  | 12/21/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 17750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/21/2020 | 00:00 | 06:40 | 6.67 | 9937 | 9937 | 0 | INT2 |  | 24B | Standby for Casing and Cement Ops
12/21/2020 | 06:40 | 08:00 | 1.33 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 6O | Pick up BHA #3 (Curve-Lateral)
12/21/2020 | 08:00 | 08:10 | 0.17 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 5A | Surface test MWD & motor (OK)
12/21/2020 | 08:10 | 18:45 | 10.58 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 6J | P/U DP t/ 9,569
12/21/2020 | 18:45 | 20:30 | 1.75 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 9A | S/C Drill Line (11 wraps)
12/21/2020 | 20:30 | 21:45 | 1.25 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 8P | Service Rig
12/21/2020 | 21:45 | 22:20 | 0.58 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 3C | Wash Down t/ 9,803 Tag Hard Cement
12/21/2020 | 22:20 | 23:10 | 0.83 | 9937 | 9937 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 5A | Drlg Out Shoe Track and Float Equipment
12/21/2020 | 23:10 | 23:17 | 0.12 | 9937 | 9942 | 5 | INT2 | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/9937.00 t/9942.00, w/WOB 20,Flow 200, RPM 30, Press 1900, Tq 9500, ROP 42.86
12/21/2020 | 23:17 | 23:20 | 0.05 | 9942 | 9942 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/21/2020 | 23:20 | 23:25 | 0.08 | 9942 | 9947 | 5 | INT2 | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/9942.00 t/9947.00, w/WOB 20,Flow 200, RPM 30, Press 2200, Tq 9500, ROP 60.00
12/21/2020 | 23:25 | 24:00 | 0.58 | 9947 | 9947 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 15D | Perform FIT
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_22_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/22/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 80000
|  |  |  | 24hr Summary: |  | Build and Land Curve; Begin Drilling Lateral Section as per plan
|  |  |  | 24hr Lookahead: |  | Drill Lateral Section as per plan
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9947 |  | 9937 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 32 | PV: | 12
End Depth (Usft): |  | 12123 |  | 12123 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 8
Total Drilled (Usft): |  | 2176 |  | 2186 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 51
Slide Drilled (Usft): |  | 790 |  | 790 | [5 empty] | 100: | 10 | Chlorides: | 45500
Rotary Drilled (Usft): |  | 1386 |  | 1396 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 9.20
Drlg/Circ Hrs: |  | 18.92 / 0.92 |  | 19.12 / 2.50 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 10.92 |  | 10.92 |  | SN: |  | 13446789 |  | 10s Gel: | 5 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 8 |  | 8.2 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 173.25 / 72.37 |  | 170.24 / 72.37 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 40 |  | Grade In: |  | New
% Slide: |  | 36.31 |  | 36.14 |  | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
% Rotary: |  | 63.69 |  | 63.86 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Jeff Cambpell |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Ramon Ries
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | 5 | 2 |  |  |  |  | 34.11 |  | 34.86
BTI Valve |  |  |  | 5 | 2.5 |  |  |  |  | 2.37 |  | 37.23
5" NMPDC |  |  |  | 5.063 | 2.563 |  |  |  |  | 9.46 |  | 46.69
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 49.18
5" NMDC |  |  |  | 5 | 2.25 |  |  |  |  | 30.43 |  | 79.61
5" NMDC |  |  |  | 5.063 | 2.5 |  |  |  |  | 29.89 |  | 109.5
Tomax Thruster |  |  |  | 5 | 2 |  |  |  |  | 17.75 |  | 127.25
X/O- DS42B x XT39P |  |  |  | 5.375 | 2.25 |  |  |  |  | 3.08 |  | 130.33
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2686.92
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.51 |  | 2710.43
2710.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9966 | 12.92 | 330.93 | 9888.07 | -420.32 | -793.32 | 7.92 |  | 19.91 | 38.45 | 7.72 |  | 12.11 | 98
10062 | 23.83 | 331.31 | 9979.03 | -393.85 | -807.89 | 11.37 |  | 0.81 | 68.65 | 11.36 |  | 0.4 | 96
10157 | 30.18 | 330.45 | 10063.63 | -356.2 | -828.9 | 6.7 |  | -3.9 | 111.76 | 6.68 |  | -0.91 | 95
10253 | 29.23 | 324.11 | 10147.04 | -316.21 | -854.55 | 3.42 |  | -109.56 | 159.23 | -0.99 |  | -6.6 | 96
10348 | 40.1 | 328.32 | 10225.07 | -271.24 | -884.31 | 11.71 |  | 14.19 | 213.07 | 11.44 |  | 4.43 | 95
10442 | 48.88 | 329.65 | 10292.06 | -214.81 | -918.16 | 9.39 |  | 6.54 | 278.87 | 9.34 |  | 1.41 | 94
10537 | 53.71 | 328.89 | 10351.45 | -151.11 | -956.05 | 5.12 |  | -7.24 | 352.99 | 5.08 |  | -0.8 | 95
10632 | 63.85 | 330.04 | 10400.63 | -81.21 | -997.23 | 10.72 |  | 5.85 | 434.12 | 10.67 |  | 1.21 | 95
10728 | 75.49 | 329.25 | 10433.92 | -3.67 | -1042.67 | 12.15 |  | -3.79 | 523.98 | 12.13 |  | -0.82 | 96
10823 | 82.69 | 328.44 | 10451.89 | 76.1 | -1090.9 | 7.62 |  | -6.38 | 617.2 | 7.58 |  | -0.85 | 95
10917 | 80.15 | 329.74 | 10465.91 | 155.83 | -1138.65 | 3.03 |  | 153.25 | 710.13 | -2.7 |  | 1.38 | 94
11013 | 93.68 | 331.4 | 10471.07 | 239.13 | -1185.63 | 14.2 |  | 7.05 | 805.75 | 14.09 |  | 1.73 | 96
11108 | 94.58 | 331.52 | 10464.23 | 322.37 | -1230.9 | 0.96 |  | 7.57 | 900.46 | 0.95 |  | 0.13 | 95
11202 | 92.43 | 330.14 | 10458.48 | 404.29 | -1276.63 | 2.72 |  | -147.31 | 994.25 | -2.29 |  | -1.47 | 94
11296 | 91.89 | 329.65 | 10454.94 | 485.55 | -1323.74 | 0.78 |  | -137.79 | 1088.18 | -0.57 |  | -0.52 | 94
11392 | 92 | 329.99 | 10451.68 | 568.49 | -1371.98 | 0.37 |  | 72.06 | 1184.13 | 0.11 |  | 0.35 | 96
11486 | 92.48 | 330.14 | 10448 | 649.89 | -1418.85 | 0.53 |  | 17.34 | 1278.05 | 0.51 |  | 0.16 | 94
11580 | 90.32 | 330.12 | 10445.71 | 731.37 | -1465.65 | 2.3 |  | -179.47 | 1372.02 | -2.3 |  | -0.02 | 94
11674 | 88.95 | 329.88 | 10446.31 | 812.77 | -1512.64 | 1.48 |  | -170.06 | 1466.01 | -1.46 |  | -0.26 | 94
11769 | 91.69 | 330.16 | 10445.78 | 895.05 | -1560.11 | 2.9 |  | 5.83 | 1561 | 2.88 |  | 0.29 | 95
11864 | 93.66 | 329.16 | 10441.34 | 976.95 | -1608.04 | 2.33 |  | -26.87 | 1655.89 | 2.07 |  | -1.05 | 95
11959 | 94.05 | 328.31 | 10434.96 | 1057.97 | -1657.23 | 0.98 |  | -65.28 | 1750.66 | 0.41 |  | -0.89 | 95
12053 | 93.47 | 327.84 | 10428.79 | 1137.58 | -1706.84 | 0.79 |  | -141.03 | 1844.42 | -0.62 |  | -0.5 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 115.03 | 36.8 | 30 | 295 | 390 | 4380 | 3780 | 152 | 260 | 215 | 170 | 10000 | 7500
Run | 114.35 | 32 | 30 | 258 | 335.71 | 3714.29 | 3157.14 | 152 | 247.14 | 212.14 | 177.14 | 9750 | 7500
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/22/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/22/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/22/2020 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 12/22/2020 |  | 9 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/22/2020 | 00:00 | 00:20 | 0.33 | 9947 | 9947 | 0 | INT2 | 3: BHA #3 (Curve and Lateral) | 15D | FIT t/ 1,964 psi- 13ppg
12/22/2020 | 00:20 | 01:40 | 1.33 | 9947 | 10037 | 90 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/9947.00 t/10037.00, TF , w/WOB 38,Flow 350, Press 3800, Tq 0, ROP 67.50
12/22/2020 | 01:40 | 01:48 | 0.13 | 10037 | 10037 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 01:48 | 02:02 | 0.23 | 10037 | 10055 | 18 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10037.00 t/10055.00, w/WOB 28,Flow 400, RPM 30, Press 4500, Tq 10000, ROP 77.14
12/22/2020 | 02:02 | 02:50 | 0.8 | 10055 | 10133 | 78 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10055.00 t/10133.00, TF , w/WOB 42,Flow 400, Press 4400, Tq 0, ROP 97.50
12/22/2020 | 02:50 | 03:03 | 0.22 | 10133 | 10133 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 03:03 | 03:25 | 0.37 | 10133 | 10188 | 55 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10133.00 t/10188.00, w/WOB 32,Flow 400.00, RPM 30, Press 4700, Tq 10000, ROP 150.00
12/22/2020 | 03:25 | 03:52 | 0.45 | 10188 | 10228 | 40 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10188.00 t/10228.00, TF , w/WOB 44,Flow 400.00, Press 4500, Tq 0.00, ROP 88.89
12/22/2020 | 03:52 | 03:57 | 0.08 | 10228 | 10228 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 03:57 | 04:10 | 0.22 | 10228 | 10250 | 22 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10228.00 t/10250.00, w/WOB 30,Flow 400.00, RPM 30, Press 4700, Tq 10000, ROP 101.54
12/22/2020 | 04:10 | 04:56 | 0.77 | 10250 | 10324 | 74 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10250.00 t/10324.00, TF , w/WOB 46,Flow 400.00, Press 4500.00, Tq 0.00, ROP 96.52
12/22/2020 | 04:56 | 05:06 | 0.17 | 10324 | 10324 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 05:06 | 06:01 | 0.92 | 10324 | 10419 | 95 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10324.00 t/10419.00, TF 10.00, w/WOB 46.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 103.64
12/22/2020 | 06:01 | 06:08 | 0.12 | 10419 | 10419 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 06:08 | 06:27 | 0.32 | 10419 | 10455 | 36 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10419.00 t/10455.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 10000.00, ROP 113.68
12/22/2020 | 06:27 | 07:01 | 0.57 | 10455 | 10513 | 58 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10455.00 t/10513.00, TF 0.00, w/WOB 46.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 102.35
12/22/2020 | 07:01 | 07:10 | 0.15 | 10513 | 10513 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 07:10 | 07:27 | 0.28 | 10513 | 10551 | 38 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10513.00 t/10551.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 10000.00, ROP 134.12
12/22/2020 | 07:27 | 08:14 | 0.78 | 10551 | 10608 | 57 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10551.00 t/10608.00, TF 0.00, w/WOB 46.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 72.77
12/22/2020 | 08:14 | 08:24 | 0.17 | 10608 | 10608 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 08:24 | 09:33 | 1.15 | 10608 | 10703 | 95 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10608.00 t/10703.00, TF , w/WOB 46.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 82.61
12/22/2020 | 09:33 | 09:43 | 0.17 | 10703 | 10703 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 09:43 | 10:04 | 0.35 | 10703 | 10755 | 52 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10703.00 t/10755.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 10000.00, ROP 148.57
12/22/2020 | 10:04 | 10:34 | 0.5 | 10755 | 10799 | 44 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10755.00 t/10799.00, TF , w/WOB 46.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 88.00
12/22/2020 | 10:34 | 10:44 | 0.17 | 10799 | 10799 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 10:44 | 11:10 | 0.43 | 10799 | 10880 | 81 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10799.00 t/10880.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 4700.00, Tq 10000.00, ROP 186.92
12/22/2020 | 11:10 | 11:28 | 0.3 | 10880 | 10894 | 14 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10880.00 t/10894.00, TF , w/WOB 46.00,Flow 400.00, Press 4500.00, Tq 0.00, ROP 46.67
12/22/2020 | 11:28 | 11:38 | 0.17 | 10894 | 10894 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 11:38 | 12:00 | 0.37 | 10894 | 10930 | 36 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10894.00 t/10930.00, w/WOB 30,Flow 320, RPM 30, Press 3400, Tq 12000, ROP 98.18
12/22/2020 | 12:00 | 12:35 | 0.58 | 10930 | 10988 | 58 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10930.00 t/10988.00, TF , w/WOB 46.00,Flow 320, Press 3100, Tq 0.00, ROP 99.43
12/22/2020 | 12:35 | 12:45 | 0.17 | 10988 | 10988 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 12:45 | 12:50 | 0.08 | 10988 | 10998 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10988.00 t/10998.00, w/WOB 30,Flow 320, RPM 30, Press 3400, Tq 12000, ROP 120.00
12/22/2020 | 12:50 | 13:07 | 0.28 | 10998 | 11015 | 17 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10998.00 t/11015.00, TF , w/WOB 46.00,Flow 320, Press 3100, Tq 0.00, ROP 60.00
12/22/2020 | 13:07 | 13:32 | 0.42 | 11015 | 11084 | 69 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11015.00 t/11084.00, w/WOB 30,Flow 320, RPM 80, Press 3400, Tq 14000, ROP 165.60
12/22/2020 | 13:32 | 13:40 | 0.13 | 11084 | 11084 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 13:40 | 14:10 | 0.5 | 11084 | 11179 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11084.00 t/11179.00, w/WOB 40,Flow 320.00, RPM 80.00, Press 3400.00, Tq 16000, ROP 190.00
12/22/2020 | 14:10 | 14:20 | 0.17 | 11179 | 11179 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 14:20 | 14:23 | 0.05 | 11179 | 11189 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11179.00 t/11189.00, w/WOB 40,Flow 320.00, RPM 80.00, Press 3400.00, Tq 16000, ROP 200.00
12/22/2020 | 14:23 | 14:38 | 0.25 | 11189 | 11207 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11189.00 t/11207.00, TF , w/WOB 50,Flow 320.00, Press 3200, Tq 0, ROP 72.00
12/22/2020 | 14:38 | 14:59 | 0.35 | 11207 | 11273 | 66 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11207.00 t/11273.00, w/WOB 40,Flow 320.00, RPM 80.00, Press 3400.00, Tq 16000, ROP 188.57
12/22/2020 | 14:59 | 15:10 | 0.18 | 11273 | 11273 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 15:10 | 15:30 | 0.33 | 11273 | 11367 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11273.00 t/11367.00, w/WOB 40,Flow 320.00, RPM 80.00, Press 3400.00, Tq 16000, ROP 282.00
12/22/2020 | 15:30 | 15:52 | 0.37 | 11367 | 11367 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 8P | Rig Service
12/22/2020 | 15:52 | 15:59 | 0.12 | 11367 | 11367 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 15:59 | 16:21 | 0.37 | 11367 | 11463 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11367.00 t/11463.00, w/WOB 40.00,Flow 320.00, RPM 80.00, Press 3600, Tq 16000.00, ROP 261.82
12/22/2020 | 16:21 | 16:28 | 0.12 | 11463 | 11463 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 16:28 | 16:48 | 0.33 | 11463 | 11557 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11463.00 t/11557.00, w/WOB 40.00,Flow 320.00, RPM 80.00, Press 3600, Tq 16000.00, ROP 282.00
12/22/2020 | 16:48 | 16:56 | 0.13 | 11557 | 11557 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 16:56 | 16:59 | 0.05 | 11557 | 11567 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11557.00 t/11567.00, w/WOB 40.00,Flow 320.00, RPM 80.00, Press 3600, Tq 16000.00, ROP 200.00
12/22/2020 | 16:59 | 17:08 | 0.15 | 11567 | 11577 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11567.00 t/11577.00, TF , w/WOB 35,Flow 320.00, Press 3200, Tq 0, ROP 66.67
12/22/2020 | 17:08 | 17:32 | 0.4 | 11577 | 11651 | 74 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11577.00 t/11651.00, w/WOB 40.00,Flow 320.00, RPM 80.00, Press 3600, Tq 16000.00, ROP 185.00
12/22/2020 | 17:32 | 17:35 | 0.05 | 11651 | 11651 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 17:35 | 18:00 | 0.42 | 11651 | 11745 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11651.00 t/11745.00, w/WOB 40.00,Flow 320.00, RPM 80.00, Press 3600, Tq 16000.00, ROP 225.60
12/22/2020 | 18:00 | 18:05 | 0.08 | 11745 | 11745 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 18:05 | 18:10 | 0.08 | 11745 | 11750 | 5 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11745.00 t/11750.00, w/WOB 40.00,Flow 320.00, RPM 80.00, Press 3600, Tq 16000.00, ROP 60.00
12/22/2020 | 18:10 | 19:00 | 0.83 | 11750 | 11774 | 24 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11750.00 t/11774.00, TF , w/WOB 42,Flow 300, Press 2800, Tq 0, ROP 28.80
12/22/2020 | 19:00 | 19:55 | 0.92 | 11774 | 11774 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5C | Circulate; Build Volume and Pump LCM Sweeps 30 lbs/bbl
12/22/2020 | 19:55 | 20:20 | 0.42 | 11774 | 11840 | 66 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11774.00 t/11840.00, w/WOB 42.00,Flow 300.00, RPM 80, Press 3600, Tq 16000, ROP 158.40
12/22/2020 | 20:20 | 20:25 | 0.08 | 11840 | 11840 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 20:25 | 20:45 | 0.33 | 11840 | 11935 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11840.00 t/11935.00, w/WOB 42.00,Flow 300.00, RPM 80, Press 3600, Tq 16000, ROP 285.00
12/22/2020 | 20:45 | 21:00 | 0.25 | 11935 | 11935 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 21:00 | 21:25 | 0.42 | 11935 | 11947 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11935.00 t/11947.00, TF , w/WOB 55,Flow 300.00, Press 2800.00, Tq 0.00, ROP 28.80
12/22/2020 | 21:25 | 22:18 | 0.88 | 11947 | 12030 | 83 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11947.00 t/12030.00, w/WOB 42.00,Flow 300.00, RPM 80, Press 3600, Tq 16000, ROP 93.96
12/22/2020 | 22:18 | 22:25 | 0.12 | 12030 | 12030 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/22/2020 | 22:25 | 23:15 | 0.83 | 12030 | 12036 | 6 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12030.00 t/12036.00, TF , w/WOB 35,Flow 330, Press 3050, Tq 0.00, ROP 7.20
12/22/2020 | 23:15 | 23:35 | 0.33 | 12036 | 12036 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 23E | Wait on Orders from Geology; Decision was made to Rotary Drill stand
12/22/2020 | 23:35 | 24:00 | 0.42 | 12036 | 12123 | 87 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12036.00 t/12123.00, w/WOB 42.00,Flow 330, RPM 80, Press 4000, Tq 16000, ROP 208.80
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_23_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/23/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 89850
|  |  |  | 24hr Summary: |  | Drilling Lateral Section as per plan
|  |  |  | 24hr Lookahead: |  | Continue Drilling Lateral Section
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12123 |  | 9937 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 22 | PV: | 7
End Depth (Usft): |  | 14591 |  | 14591 |  | OD (in): |  | 10.75 |  | 300: | 15 | YP: | 8
Total Drilled (Usft): |  | 2468 |  | 4654 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 41
Slide Drilled (Usft): |  | 200 |  | 990 | [5 empty] | 100: | 9 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 2268 |  | 3664 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.10
Drlg/Circ Hrs: |  | 17.67 / 1.18 |  | 36.78 / 3.68 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 6.65 |  | 17.57 |  | SN: |  | 13446789 |  | 10s Gel: | 4 | Weight (ppg): | 8.6
Rotary Drilling Hrs: |  | 11.02 |  | 19.22 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 140.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 205.87 / 30.08 |  | 190.67 / 56.36 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 64 |  | Grade In: |  | New
% Slide: |  | 8.1 |  | 21.27 |  | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
% Rotary: |  | 91.9 |  | 78.73 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Jeff Cambpell |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Ramon Ries
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | 5 | 2 |  |  |  |  | 34.11 |  | 34.86
BTI Valve |  |  |  | 5 | 2.5 |  |  |  |  | 2.37 |  | 37.23
5" NMPDC |  |  |  | 5.063 | 2.563 |  |  |  |  | 9.46 |  | 46.69
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 49.18
5" NMDC |  |  |  | 5 | 2.25 |  |  |  |  | 30.43 |  | 79.61
5" NMDC |  |  |  | 5.063 | 2.5 |  |  |  |  | 29.89 |  | 109.5
Tomax Thruster |  |  |  | 5 | 2 |  |  |  |  | 17.75 |  | 127.25
X/O- DS42B x XT39P |  |  |  | 5.375 | 2.25 |  |  |  |  | 3.08 |  | 130.33
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2686.92
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.51 |  | 2710.43
2710.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12149 | 92.13 | 327.1 | 10424.1 | 1218.42 | -1758.4 | 1.59 |  | -151.1 | 1940.24 | -1.4 |  | -0.77 | 96
12245 | 94.73 | 328.84 | 10418.36 | 1299.64 | -1809.21 | 3.26 |  | 33.7 | 2036.01 | 2.71 |  | 1.81 | 96
12341 | 96.59 | 329.4 | 10408.89 | 1381.63 | -1858.24 | 2.02 |  | 16.65 | 2131.54 | 1.94 |  | 0.58 | 96
12436 | 93.64 | 331.33 | 10400.42 | 1463.86 | -1905.02 | 3.71 |  | 146.82 | 2226.13 | -3.11 |  | 2.03 | 95
12531 | 93.64 | 331.53 | 10394.39 | 1547.13 | -1950.36 | 0.21 |  | 89.99 | 2320.9 | 0 |  | 0.21 | 95
12627 | 94.84 | 332.2 | 10387.29 | 1631.55 | -1995.51 | 1.43 |  | 29.09 | 2416.56 | 1.25 |  | 0.7 | 96
12723 | 93.83 | 331.99 | 10380.04 | 1716.14 | -2040.31 | 1.07 |  | -168.28 | 2512.19 | -1.05 |  | -0.22 | 96
12818 | 92.87 | 330.81 | 10374.48 | 1799.41 | -2085.7 | 1.6 |  | -129.14 | 2606.98 | -1.01 |  | -1.24 | 95
12912 | 93.5 | 331.07 | 10369.26 | 1881.45 | -2131.29 | 0.72 |  | 22.39 | 2700.81 | 0.67 |  | 0.28 | 94
13006 | 94.18 | 331.31 | 10362.97 | 1963.62 | -2176.49 | 0.77 |  | 19.39 | 2794.57 | 0.72 |  | 0.26 | 94
13102 | 95.29 | 331.96 | 10355.04 | 2047.81 | -2221.94 | 1.34 |  | 30.24 | 2890.18 | 1.16 |  | 0.68 | 96
13196 | 93.6 | 330.55 | 10347.76 | 2129.97 | -2267.01 | 2.34 |  | -140.19 | 2983.85 | -1.8 |  | -1.5 | 94
13291 | 93.53 | 329.24 | 10341.85 | 2212 | -2314.57 | 1.38 |  | -93.02 | 3078.67 | -0.07 |  | -1.38 | 95
13387 | 93.93 | 328.84 | 10335.6 | 2294.14 | -2363.85 | 0.59 |  | -44.93 | 3174.46 | 0.42 |  | -0.42 | 96
13481 | 92.96 | 327.65 | 10329.96 | 2373.93 | -2413.23 | 1.63 |  | -129.2 | 3268.26 | -1.03 |  | -1.27 | 94
13577 | 95.04 | 328.33 | 10323.26 | 2455.13 | -2463.99 | 2.28 |  | 18.04 | 3363.98 | 2.17 |  | 0.71 | 96
13671 | 95.99 | 328.52 | 10314.23 | 2534.84 | -2512.98 | 1.03 |  | 11.25 | 3457.52 | 1.01 |  | 0.2 | 94
13765 | 92.84 | 329.05 | 10306.99 | 2614.98 | -2561.54 | 3.4 |  | 170.46 | 3551.22 | -3.35 |  | 0.56 | 94
13859 | 93.85 | 328.91 | 10301.51 | 2695.4 | -2609.9 | 1.08 |  | -7.87 | 3645.05 | 1.07 |  | -0.15 | 94
13954 | 94.66 | 329.49 | 10294.46 | 2776.77 | -2658.41 | 1.05 |  | 35.51 | 3739.79 | 0.85 |  | 0.61 | 95
14048 | 92.3 | 327.35 | 10288.75 | 2856.69 | -2707.54 | 3.39 |  | -137.78 | 3833.58 | -2.51 |  | -2.28 | 94
14142 | 93.5 | 326.74 | 10283.99 | 2935.47 | -2758.61 | 1.43 |  | -26.9 | 3927.36 | 1.28 |  | -0.65 | 94
14237 | 90.2 | 326.82 | 10280.93 | 3014.89 | -2810.62 | 3.47 |  | 178.61 | 4022.18 | -3.47 |  | 0.08 | 95
14331 | 89.39 | 326.62 | 10281.26 | 3093.47 | -2862.2 | 0.89 |  | -166.13 | 4116.06 | -0.86 |  | -0.21 | 94
14425 | 93.02 | 327.76 | 10279.29 | 3172.44 | -2913.12 | 4.05 |  | 17.42 | 4209.94 | 3.86 |  | 1.21 | 94
14520 | 93.9 | 329.1 | 10273.55 | 3253.23 | -2962.76 | 1.69 |  | 56.62 | 4304.74 | 0.93 |  | 1.41 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 139.7 | 44.2 | 80 | 304 | 330 | 3791.67 | 2800 | 152 | 300 | 220 | 160 | 16000 | 7500
Run | 126.52 | 40.95 | 68.78 | 298 | 337.67 | 3783.56 | 2941.1 | 152 | 282.88 | 218.42 | 165.48 | 14673.47 | 7500
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/23/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/23/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/23/2020 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 12/23/2020 |  | 9 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/23/2020 | 00:00 | 00:50 | 0.83 | 12123 | 12123 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 20C | Troubleshoot MWD Tool
12/23/2020 | 00:50 | 01:00 | 0.17 | 12123 | 12123 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Survey @ 12,053 SD
12/23/2020 | 01:00 | 02:10 | 1.17 | 12123 | 12123 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6F | Wiper Trip 3 Stand
12/23/2020 | 02:10 | 02:40 | 0.5 | 12123 | 12220 | 97 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12123.00 t/12220.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 194.00
12/23/2020 | 02:40 | 02:45 | 0.08 | 12220 | 12220 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 02:45 | 03:10 | 0.42 | 12220 | 12238 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12220.00 t/12238.00, TF , w/WOB 40,Flow 330.00, Press 3050, Tq 0, ROP 43.20
12/23/2020 | 03:10 | 03:38 | 0.47 | 12238 | 12316 | 78 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12238.00 t/12316.00, w/WOB 42,Flow 330.00, RPM 80, Press 4000, Tq 16000, ROP 167.14
12/23/2020 | 03:38 | 03:42 | 0.07 | 12316 | 12316 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 03:42 | 04:05 | 0.38 | 12316 | 12412 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12316.00 t/12412.00, w/WOB 42,Flow 330.00, RPM 80, Press 4000, Tq 16000, ROP 250.43
12/23/2020 | 04:05 | 04:12 | 0.12 | 12412 | 12412 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 04:12 | 04:55 | 0.72 | 12412 | 12434 | 22 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12412.00 t/12434.00, TF , w/WOB 45,Flow 330.00, Press 3200, Tq 0.00, ROP 30.70
12/23/2020 | 04:55 | 05:18 | 0.38 | 12434 | 12507 | 73 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12434.00 t/12507.00, w/WOB 42,Flow 330.00, RPM 80, Press 4000, Tq 16000, ROP 190.43
12/23/2020 | 05:18 | 05:23 | 0.08 | 12507 | 12507 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 05:23 | 05:48 | 0.42 | 12507 | 12602 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12507.00 t/12602.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 228.00
12/23/2020 | 05:48 | 05:54 | 0.1 | 12602 | 12602 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 05:54 | 06:15 | 0.35 | 12602 | 12698 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12602.00 t/12698.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 274.29
12/23/2020 | 06:15 | 06:23 | 0.13 | 12698 | 12698 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 06:23 | 06:32 | 0.15 | 12698 | 12708 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12698.00 t/12708.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 66.67
12/23/2020 | 06:32 | 07:07 | 0.58 | 12708 | 12728 | 20 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12708.00 t/12728.00, TF -140.00, w/WOB 55.00,Flow 330.00, Press 3100.00, Tq 0.00, ROP 34.29
12/23/2020 | 07:07 | 07:26 | 0.32 | 12728 | 12794 | 66 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12728.00 t/12794.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 208.42
12/23/2020 | 07:26 | 07:33 | 0.12 | 12794 | 12794 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 07:33 | 07:55 | 0.37 | 12794 | 12889 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12794.00 t/12889.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 259.09
12/23/2020 | 07:55 | 08:03 | 0.13 | 12889 | 12889 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 08:03 | 08:23 | 0.33 | 12889 | 12983 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12889.00 t/12983.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 282.00
12/23/2020 | 08:23 | 08:31 | 0.13 | 12983 | 12983 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 08:31 | 08:53 | 0.37 | 12983 | 13077 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12983.00 t/13077.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 256.36
12/23/2020 | 08:53 | 09:00 | 0.12 | 13077 | 13077 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 09:00 | 09:26 | 0.43 | 13077 | 13173 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13077.00 t/13173.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 221.54
12/23/2020 | 09:26 | 09:33 | 0.12 | 13173 | 13173 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 09:33 | 09:40 | 0.12 | 13173 | 13183 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13173.00 t/13183.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 85.71
12/23/2020 | 09:40 | 10:37 | 0.95 | 13183 | 13213 | 30 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13183.00 t/13213.00, TF -130.00, w/WOB 55.00,Flow 330.00, Press 3100.00, Tq 0.00, ROP 31.58
12/23/2020 | 10:37 | 10:52 | 0.25 | 13213 | 13267 | 54 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13213.00 t/13267.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 216.00
12/23/2020 | 10:52 | 11:53 | 1.02 | 13267 | 13267 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Circulate; Wait on orders from geologist
12/23/2020 | 11:53 | 12:02 | 0.15 | 13267 | 13267 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 12:02 | 12:07 | 0.08 | 13267 | 13277 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13267.00 t/13277.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 120.00
12/23/2020 | 12:07 | 12:24 | 0.28 | 13277 | 13292 | 15 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13277.00 t/13292.00, TF , w/WOB 55.00,Flow 330.00, Press 3100.00, Tq 0.00, ROP 52.94
12/23/2020 | 12:24 | 12:46 | 0.37 | 13292 | 13362 | 70 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13292.00 t/13362.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 190.91
12/23/2020 | 12:46 | 12:53 | 0.12 | 13362 | 13362 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 12:53 | 13:07 | 0.23 | 13362 | 13424 | 62 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13362.00 t/13424.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 265.71
12/23/2020 | 13:07 | 13:19 | 0.2 | 13424 | 13424 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 13:19 | 13:28 | 0.15 | 13424 | 13458 | 34 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13424.00 t/13458.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 226.67
12/23/2020 | 13:28 | 13:36 | 0.13 | 13458 | 13458 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 13:36 | 13:59 | 0.38 | 13458 | 13552 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13458.00 t/13552.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 245.22
12/23/2020 | 13:59 | 14:07 | 0.13 | 13552 | 13552 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 14:07 | 14:10 | 0.05 | 13552 | 13562 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13552.00 t/13562.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 200.00
12/23/2020 | 14:10 | 14:43 | 0.55 | 13562 | 13574 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13562.00 t/13574.00, TF , w/WOB 55.00,Flow 330.00, Press 3100.00, Tq 0.00, ROP 21.82
12/23/2020 | 14:43 | 15:07 | 0.4 | 13574 | 13648 | 74 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13574.00 t/13648.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 185.00
12/23/2020 | 15:07 | 15:12 | 0.08 | 13648 | 13648 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 15:12 | 15:46 | 0.57 | 13648 | 13742 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13648.00 t/13742.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 165.88
12/23/2020 | 15:46 | 16:00 | 0.23 | 13742 | 13742 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 16:00 | 16:50 | 0.83 | 13742 | 13762 | 20 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13742.00 t/13762.00, TF 180.00, w/WOB 55.00,Flow 330.00, Press 3100.00, Tq 0.00, ROP 24.00
12/23/2020 | 16:50 | 17:14 | 0.4 | 13762 | 13836 | 74 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13762.00 t/13836.00, w/WOB 42,Flow 330.00, RPM 80, Press 4000, Tq 16000, ROP 185.00
12/23/2020 | 17:14 | 17:22 | 0.13 | 13836 | 13836 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 17:22 | 17:45 | 0.38 | 13836 | 13930 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13836.00 t/13930.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 245.22
12/23/2020 | 17:45 | 17:48 | 0.05 | 13930 | 13930 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 17:48 | 18:15 | 0.45 | 13930 | 14025 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13930.00 t/14025.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 211.11
12/23/2020 | 18:15 | 18:20 | 0.08 | 14025 | 14025 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 18:20 | 18:25 | 0.08 | 14025 | 14031 | 6 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14025.00 t/14031.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 72.00
12/23/2020 | 18:25 | 19:08 | 0.72 | 14031 | 14047 | 16 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14031.00 t/14047.00, TF , w/WOB 58,Flow 330.00, Press 3000, Tq 0, ROP 22.33
12/23/2020 | 19:08 | 19:27 | 0.32 | 14047 | 14119 | 72 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14047.00 t/14119.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 227.37
12/23/2020 | 19:27 | 19:32 | 0.08 | 14119 | 14119 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 19:32 | 20:04 | 0.53 | 14119 | 14213 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14119.00 t/14213.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 176.25
12/23/2020 | 20:04 | 20:15 | 0.18 | 14213 | 14213 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 20:15 | 20:20 | 0.08 | 14213 | 14220 | 7 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14213.00 t/14220.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 84.00
12/23/2020 | 20:20 | 20:40 | 0.33 | 14220 | 14232 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14220.00 t/14232.00, TF , w/WOB 62,Flow 400, Press 3800, Tq 0, ROP 36.00
12/23/2020 | 20:40 | 21:05 | 0.42 | 14232 | 14308 | 76 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14232.00 t/14308.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 182.40
12/23/2020 | 21:05 | 21:10 | 0.08 | 14308 | 14308 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 21:10 | 21:35 | 0.42 | 14308 | 14402 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14308.00 t/14402.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 225.60
12/23/2020 | 21:35 | 21:40 | 0.08 | 14402 | 14402 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 21:40 | 22:32 | 0.87 | 14402 | 14427 | 25 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14402.00 t/14427.00, TF , w/WOB 65,Flow 375, Press 3700, Tq 0, ROP 28.85
12/23/2020 | 22:32 | 22:55 | 0.38 | 14427 | 14496 | 69 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14427.00 t/14496.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 180.00
12/23/2020 | 22:55 | 23:02 | 0.12 | 14496 | 14496 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/23/2020 | 23:02 | 23:06 | 0.07 | 14496 | 14507 | 11 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14496.00 t/14507.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 16000.00, ROP 165.00
12/23/2020 | 23:06 | 23:30 | 0.4 | 14507 | 14517 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14507.00 t/14517.00, TF , w/WOB 68,Flow 375, Press 3700, Tq 0, ROP 25.00
12/23/2020 | 23:30 | 23:55 | 0.42 | 14517 | 14591 | 74 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14517.00 t/14591.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4000.00, Tq 22000, ROP 177.60
12/23/2020 | 23:55 | 24:00 | 0.08 | 14591 | 14591 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_24_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/24/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 99700
|  |  |  | 24hr Summary: |  | Drilling Ahead in Lateral Section as per plan
|  |  |  | 24hr Lookahead: |  | Continue Drilling Lateral Section t/ Well TD
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14591 |  | 9937 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 22 | PV: | 7
End Depth (Usft): |  | 16234 |  | 16234 |  | OD (in): |  | 10.75 |  | 300: | 15 | YP: | 8
Total Drilled (Usft): |  | 1643 |  | 6297 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 41
Slide Drilled (Usft): |  | 125 |  | 1115 | [5 empty] | 100: | 9 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 1518 |  | 5182 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.10
Drlg/Circ Hrs: |  | 17.10 / 0.00 |  | 53.88 / 3.68 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 7.12 |  | 24.68 |  | SN: |  | 13446789 |  | 10s Gel: | 4 | Weight (ppg): | 8.6
Rotary Drilling Hrs: |  | 9.98 |  | 29.2 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 140.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 152.05 / 17.56 |  | 177.47 / 45.17 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 88 |  | Grade In: |  | New
% Slide: |  | 7.61 |  | 17.71 |  | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
% Rotary: |  | 92.39 |  | 82.29 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Jeff Cambpell |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Ramon Ries
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | 5 | 2 |  |  |  |  | 34.11 |  | 34.86
BTI Valve |  |  |  | 5 | 2.5 |  |  |  |  | 2.37 |  | 37.23
5" NMPDC |  |  |  | 5.063 | 2.563 |  |  |  |  | 9.46 |  | 46.69
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 49.18
5" NMDC |  |  |  | 5 | 2.25 |  |  |  |  | 30.43 |  | 79.61
5" NMDC |  |  |  | 5.063 | 2.5 |  |  |  |  | 29.89 |  | 109.5
Tomax Thruster |  |  |  | 5 | 2 |  |  |  |  | 17.75 |  | 127.25
X/O- DS42B x XT39P |  |  |  | 5.375 | 2.25 |  |  |  |  | 3.08 |  | 130.33
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2686.92
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.51 |  | 2710.43
2710.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14613 | 94.63 | 328.9 | 10266.64 | 3332.73 | -3010.53 | 0.81 |  | -15.27 | 4397.47 | 0.78 |  | -0.22 | 93
14708 | 95.83 | 328.81 | 10257.98 | 3413.7 | -3059.45 | 1.27 |  | -4.27 | 4492.07 | 1.26 |  | -0.09 | 95
14803 | 94.26 | 330.5 | 10249.62 | 3495.36 | -3107.26 | 2.42 |  | 132.93 | 4586.69 | -1.65 |  | 1.78 | 95
14897 | 90.71 | 329.33 | 10245.55 | 3576.6 | -3154.33 | 3.98 |  | -161.75 | 4680.59 | -3.78 |  | -1.24 | 94
14993 | 90.06 | 329.27 | 10244.9 | 3659.15 | -3203.34 | 0.68 |  | -174.73 | 4776.58 | -0.68 |  | -0.06 | 96
15088 | 89.15 | 329.46 | 10245.56 | 3740.89 | -3251.75 | 0.98 |  | 168.21 | 4871.58 | -0.96 |  | 0.2 | 95
15183 | 90.3 | 330.62 | 10246.01 | 3823.19 | -3299.19 | 1.72 |  | 45.25 | 4966.57 | 1.21 |  | 1.22 | 95
15277 | 93.53 | 330.85 | 10242.87 | 3905.13 | -3345.11 | 3.44 |  | 4.07 | 5060.49 | 3.44 |  | 0.24 | 94
15373 | 94.05 | 331 | 10236.53 | 3988.85 | -3391.66 | 0.56 |  | 16.05 | 5156.26 | 0.54 |  | 0.16 | 96
15468 | 95.12 | 331.72 | 10228.93 | 4071.96 | -3437.04 | 1.36 |  | 33.82 | 5250.91 | 1.13 |  | 0.76 | 95
15564 | 96.57 | 331.7 | 10219.16 | 4156.05 | -3482.3 | 1.51 |  | -0.79 | 5346.34 | 1.51 |  | -0.02 | 96
15659 | 94.71 | 329.92 | 10209.82 | 4238.58 | -3528.41 | 2.7 |  | -136.31 | 5440.85 | -1.96 |  | -1.87 | 95
15754 | 94.89 | 329.46 | 10201.87 | 4320.3 | -3576.18 | 0.52 |  | -68.54 | 5535.52 | 0.19 |  | -0.48 | 95
15849 | 92.94 | 329.02 | 10195.39 | 4401.74 | -3624.66 | 2.1 |  | -167.3 | 5630.29 | -2.05 |  | -0.46 | 95
15944 | 92.75 | 329.17 | 10190.67 | 4483.16 | -3673.39 | 0.25 |  | 141.74 | 5725.17 | -0.2 |  | 0.16 | 95
16039 | 93.21 | 329.49 | 10185.73 | 4564.76 | -3721.78 | 0.59 |  | 34.78 | 5820.04 | 0.48 |  | 0.34 | 95
16133 | 91.56 | 331.41 | 10181.82 | 4646.45 | -3768.1 | 2.69 |  | 130.66 | 5913.94 | -1.76 |  | 2.04 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 96.08 | 44.2 | 80 | 304 | 330 | 3791.67 | 2800 | 152 | 300 | 220 | 160 | 16000 | 7500
Run | 116.86 | 40.95 | 68.78 | 298 | 337.67 | 3783.56 | 2941.1 | 152 | 282.88 | 218.42 | 165.48 | 14673.47 | 7500
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/24/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/24/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/24/2020 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 12/24/2020 |  | 9 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/24/2020 | 00:00 | 00:35 | 0.58 | 14591 | 14684 | 93 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14591.00 t/14684.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 159.43
12/24/2020 | 00:35 | 00:40 | 0.08 | 14684 | 14684 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 00:40 | 01:08 | 0.47 | 14684 | 14779 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14684.00 t/14779.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 203.57
12/24/2020 | 01:08 | 01:12 | 0.07 | 14779 | 14779 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 01:12 | 01:22 | 0.17 | 14779 | 14788 | 9 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14779.00 t/14788.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 54.00
12/24/2020 | 01:22 | 02:00 | 0.63 | 14788 | 14804 | 16 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14788.00 t/14804.00, TF , w/WOB 68,Flow 375, Press 3700, Tq 0, ROP 25.26
12/24/2020 | 02:00 | 02:35 | 0.58 | 14804 | 14874 | 70 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14804.00 t/14874.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 120.00
12/24/2020 | 02:35 | 02:40 | 0.08 | 14874 | 14874 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 02:40 | 02:57 | 0.28 | 14874 | 14884 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14874.00 t/14884.00, TF , w/WOB 68,Flow 375, Press 3700, Tq 0, ROP 35.29
12/24/2020 | 02:57 | 03:25 | 0.47 | 14884 | 14968 | 84 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14884.00 t/14968.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 180.00
12/24/2020 | 03:25 | 03:30 | 0.08 | 14968 | 14968 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 03:30 | 04:00 | 0.5 | 14968 | 15064 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14968.00 t/15064.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 192.00
12/24/2020 | 04:00 | 04:05 | 0.08 | 15064 | 15064 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 04:05 | 04:30 | 0.42 | 15064 | 15148 | 84 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15064.00 t/15148.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 201.60
12/24/2020 | 04:30 | 04:35 | 0.08 | 15148 | 15159 | 11 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15064.00 t/15159.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 1140.00
12/24/2020 | 04:35 | 04:40 | 0.08 | 15159 | 15159 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 04:40 | 06:08 | 1.47 | 15159 | 15181 | 22 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15159.00 t/15181.00, TF , w/WOB 68.00,Flow 375.00, Press 3700.00, Tq 0.00, ROP 15.00
12/24/2020 | 06:08 | 06:36 | 0.47 | 15181 | 15254 | 73 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15181.00 t/15254.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 156.43
12/24/2020 | 06:36 | 07:07 | 0.52 | 15254 | 15254 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 07:07 | 08:15 | 1.13 | 15254 | 15279 | 25 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15254.00 t/15279.00, TF , w/WOB 68.00,Flow 375.00, Press 3700.00, Tq 0.00, ROP 22.06
12/24/2020 | 08:15 | 08:45 | 0.5 | 15279 | 15348 | 69 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15279.00 t/15348.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 138.00
12/24/2020 | 08:45 | 08:55 | 0.17 | 15348 | 15348 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 08:55 | 09:27 | 0.53 | 15348 | 15444 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15348.00 t/15444.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 180.00
12/24/2020 | 09:27 | 09:37 | 0.17 | 15444 | 15444 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 09:37 | 10:15 | 0.63 | 15444 | 15539 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15444.00 t/15539.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 150.00
12/24/2020 | 10:15 | 10:25 | 0.17 | 15539 | 15539 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 10:25 | 10:59 | 0.57 | 15539 | 15635 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15539.00 t/15635.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 169.41
12/24/2020 | 10:59 | 11:21 | 0.37 | 15635 | 15635 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 11:21 | 12:40 | 1.32 | 15635 | 15657 | 22 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15635.00 t/15657.00, TF -140.00, w/WOB 68.00,Flow 375.00, Press 3700.00, Tq 0.00, ROP 16.71
12/24/2020 | 12:40 | 13:13 | 0.55 | 15657 | 15730 | 73 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15657.00 t/15730.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 132.73
12/24/2020 | 13:13 | 13:29 | 0.27 | 15730 | 15730 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 13:29 | 13:58 | 0.48 | 15730 | 15825 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15730.00 t/15825.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 196.55
12/24/2020 | 13:58 | 14:12 | 0.23 | 15825 | 15825 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 14:12 | 15:39 | 1.45 | 15825 | 15843 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15825.00 t/15843.00, TF , w/WOB 70,Flow 375.00, Press 3700.00, Tq 0.00, ROP 12.41
12/24/2020 | 15:39 | 16:12 | 0.55 | 15843 | 15920 | 77 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15843.00 t/15920.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 140.00
12/24/2020 | 16:12 | 16:29 | 0.28 | 15920 | 15920 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 16:29 | 17:00 | 0.52 | 15920 | 16015 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15920.00 t/16015.00, w/WOB 42.00,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 183.87
12/24/2020 | 17:00 | 17:40 | 0.67 | 16015 | 16015 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 8P | Rig Service
12/24/2020 | 17:40 | 17:45 | 0.08 | 16015 | 16015 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 17:45 | 18:40 | 0.92 | 16015 | 16110 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16015.00 t/16110.00, w/WOB 35,Flow 330.00, RPM 80.00, Press 4100.00, Tq 22000.00, ROP 103.64
12/24/2020 | 18:40 | 18:50 | 0.17 | 16110 | 16110 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey
12/24/2020 | 18:50 | 22:00 | 3.17 | 16110 | 16110 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6F | Wiper Trip 10 Stands
12/24/2020 | 22:00 | 22:50 | 0.83 | 16110 | 16122 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/16110.00 t/16122.00, TF , w/WOB 75,Flow 380, Press 3750, Tq 0, ROP 14.40
12/24/2020 | 22:50 | 23:40 | 0.83 | 16122 | 16204 | 82 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16122.00 t/16204.00, w/WOB 35.00,Flow 380, RPM 80.00, Press 4700, Tq 22000.00, ROP 98.40
12/24/2020 | 23:40 | 23:50 | 0.17 | 16204 | 16204 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/24/2020 | 23:50 | 24:00 | 0.17 | 16204 | 16234 | 30 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16204.00 t/16234.00, w/WOB 35.00,Flow 400, RPM 80.00, Press 4950, Tq 22000.00, ROP 180.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_25_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/25/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 11600 |  |  | Well Cost($): |  | 111300
|  |  |  | 24hr Summary: |  | Drill Lateral Section t/ TD; Circulate Hole Clean; TOH
|  |  |  | 24hr Lookahead: |  | Finish TOH; L/D BHA; Standby for Casing and Cement Ops
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16234 |  | 9937 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 22 | PV: | 7
End Depth (Usft): |  | 17167 |  | 17167 |  | OD (in): |  | 10.75 |  | 300: | 15 | YP: | 8
Total Drilled (Usft): |  | 933 |  | 7230 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 41
Slide Drilled (Usft): |  | 20 |  | 1135 | [5 empty] | 100: | 9 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 913 |  | 6095 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.10
Drlg/Circ Hrs: |  | 8.37 / 14.00 |  | 62.25 / 17.68 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 1.28 |  | 25.97 |  | SN: |  | 13446789 |  | 10s Gel: | 4 | Weight (ppg): | 8.6
Rotary Drilling Hrs: |  | 7.08 |  | 36.28 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 140.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 128.89 / 15.58 |  | 167.98 / 43.71 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 112 |  | Grade In: |  | New
% Slide: |  | 2.14 |  | 15.7 |  | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
% Rotary: |  | 97.86 |  | 84.3 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Jeff Cambpell |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Ramon Ries
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | 5 | 2 |  |  |  |  | 34.11 |  | 34.86
BTI Valve |  |  |  | 5 | 2.5 |  |  |  |  | 2.37 |  | 37.23
5" NMPDC |  |  |  | 5.063 | 2.563 |  |  |  |  | 9.46 |  | 46.69
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 49.18
5" NMDC |  |  |  | 5 | 2.25 |  |  |  |  | 30.43 |  | 79.61
5" NMDC |  |  |  | 5.063 | 2.5 |  |  |  |  | 29.89 |  | 109.5
Tomax Thruster |  |  |  | 5 | 2 |  |  |  |  | 17.75 |  | 127.25
X/O- DS42B x XT39P |  |  |  | 5.375 | 2.25 |  |  |  |  | 3.08 |  | 130.33
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2686.92
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.51 |  | 2710.43
2710.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16227 | 91.72 | 330.76 | 10179.13 | 4728.7 | -3813.53 | 0.71 |  | -76.16 | 6007.87 | 0.17 |  | -0.69 | 94
16321 | 91.93 | 331.33 | 10176.14 | 4810.91 | -3859.01 | 0.65 |  | 69.76 | 6101.8 | 0.22 |  | 0.61 | 94
16416 | 92.13 | 331.85 | 10172.77 | 4894.41 | -3904.18 | 0.59 |  | 68.94 | 6196.68 | 0.21 |  | 0.55 | 95
16511 | 92.52 | 331.9 | 10168.92 | 4978.13 | -3948.93 | 0.41 |  | 7.3 | 6291.53 | 0.41 |  | 0.05 | 95
16605 | 92.3 | 331.58 | 10164.96 | 5060.85 | -3993.4 | 0.41 |  | -124.53 | 6385.38 | -0.23 |  | -0.34 | 94
16700 | 93.79 | 331.69 | 10159.92 | 5144.32 | -4038.46 | 1.57 |  | 4.21 | 6480.19 | 1.57 |  | 0.12 | 95
16794 | 94.2 | 331.04 | 10153.37 | 5226.62 | -4083.4 | 0.82 |  | -57.67 | 6573.91 | 0.44 |  | -0.69 | 94
16889 | 94.94 | 331.32 | 10145.8 | 5309.59 | -4129.05 | 0.83 |  | 20.65 | 6668.58 | 0.78 |  | 0.29 | 95
16984 | 95.01 | 331.06 | 10137.56 | 5392.52 | -4174.66 | 0.28 |  | -74.87 | 6763.18 | 0.07 |  | -0.27 | 95
17078 | 95.82 | 331.72 | 10128.69 | 5474.67 | -4219.47 | 1.11 |  | 39.02 | 6856.72 | 0.86 |  | 0.7 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 111.51 | 44.2 | 80 | 304 | 330 | 3791.67 | 2800 | 152 | 300 | 220 | 160 | 16000 | 7500
Run | 116.14 | 40.95 | 68.78 | 298 | 337.67 | 3783.56 | 2941.1 | 152 | 282.88 | 218.42 | 165.48 | 14673.47 | 7500
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/25/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/25/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/25/2020 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 12/25/2020 |  | 9 |  | 2000 |  | 1 | 2000
Hot Hole 300-347?F |  |  |  |  | 12/25/2020 |  | 8 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 11600
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/25/2020 | 00:00 | 00:23 | 0.38 | 16234 | 16298 | 64 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16234.00 t/16298.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 166.96
12/25/2020 | 00:23 | 00:29 | 0.1 | 16298 | 16298 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 00:29 | 01:05 | 0.6 | 16298 | 16392 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16298.00 t/16392.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 156.67
12/25/2020 | 01:05 | 01:10 | 0.08 | 16392 | 16392 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 01:10 | 01:43 | 0.55 | 16392 | 16487 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16392.00 t/16487.00, w/WOB 38,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 172.73
12/25/2020 | 01:43 | 01:52 | 0.15 | 16487 | 16487 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 01:52 | 02:00 | 0.13 | 16487 | 16490 | 3 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16487.00 t/16490.00, w/WOB 38,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 22.50
12/25/2020 | 02:00 | 02:20 | 0.33 | 16490 | 16498 | 8 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/16490.00 t/16498.00, TF , w/WOB 75,Flow 400.00, Press 4100, Tq 0, ROP 24.00
12/25/2020 | 02:20 | 02:50 | 0.5 | 16498 | 16582 | 84 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16498.00 t/16582.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 168.00
12/25/2020 | 02:50 | 02:55 | 0.08 | 16582 | 16582 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 02:55 | 03:32 | 0.62 | 16582 | 16676 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16582.00 t/16676.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 152.43
12/25/2020 | 03:32 | 03:38 | 0.1 | 16676 | 16676 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 03:38 | 03:48 | 0.17 | 16676 | 16678 | 2 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16676.00 t/16678.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4950.00, Tq 22000.00, ROP 12.00
12/25/2020 | 03:48 | 04:45 | 0.95 | 16678 | 16690 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/16678.00 t/16690.00, TF , w/WOB 80,Flow 400.00, Press 4000, Tq 0, ROP 12.63
12/25/2020 | 04:45 | 05:39 | 0.9 | 16690 | 16771 | 81 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16690.00 t/16771.00, w/WOB 80.00,Flow 400.00, RPM 80, Press 4950, Tq 22000, ROP 90.00
12/25/2020 | 05:39 | 05:53 | 0.23 | 16771 | 16771 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 05:53 | 06:34 | 0.68 | 16771 | 16865 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16771.00 t/16865.00, w/WOB 80.00,Flow 400.00, RPM 80, Press 4950, Tq 22000, ROP 137.56
12/25/2020 | 06:34 | 06:42 | 0.13 | 16865 | 16865 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 06:42 | 07:30 | 0.8 | 16865 | 16960 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16865.00 t/16960.00, w/WOB 80.00,Flow 400.00, RPM 80, Press 4950, Tq 22000, ROP 118.75
12/25/2020 | 07:30 | 07:40 | 0.17 | 16960 | 16960 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 07:40 | 08:25 | 0.75 | 16960 | 17055 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/16960.00 t/17055.00, w/WOB 80.00,Flow 400.00, RPM 80, Press 4950, Tq 23000, ROP 126.67
12/25/2020 | 08:25 | 08:40 | 0.25 | 17055 | 17055 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 08:40 | 09:25 | 0.75 | 17055 | 17149 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/17055.00 t/17149.00, w/WOB 80.00,Flow 400.00, RPM 80, Press 4950, Tq 23000, ROP 125.33
12/25/2020 | 09:25 | 09:45 | 0.33 | 17149 | 17149 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
12/25/2020 | 09:45 | 10:00 | 0.25 | 17149 | 17167 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/17149.00 t/17167.00, w/WOB 80.00,Flow 400.00, RPM 80, Press 4950, Tq 23000, ROP 72.00
12/25/2020 | 10:00 | 15:00 | 5 | 17167 | 17167 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Circulate Hole Clean @ TD
12/25/2020 | 15:00 | 22:30 | 7.5 | 17167 | 17167 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 3D | Backream Out of Hole t/ 9,954
12/25/2020 | 22:30 | 24:00 | 1.5 | 17167 | 17167 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5D | Circulate Out Gas; Shut in Well
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_26_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/26/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9100 |  |  | Well Cost($): |  | 120400
|  |  |  | 24hr Summary: |  | TOH; L/D BHA; Standby
|  |  |  | 24hr Lookahead: |  | Standby; EOW
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17167 |  | 9937 |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 22 | PV: | 7
End Depth (Usft): |  | 17167 |  | 17167 |  | OD (in): |  | 10.75 |  | 300: | 15 | YP: | 8
Total Drilled (Usft): |  |  |  | 7230 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 41
Slide Drilled (Usft): |  |  |  | 1135 | [5 empty] | 100: | 9 | Chlorides: | 49000
Rotary Drilled (Usft): |  |  |  | 6095 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.10
Drlg/Circ Hrs: |  | 0.00 / 0.50 |  | 62.25 / 18.18 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  |  |  | 25.97 |  | SN: |  | 13446789 |  | 10s Gel: | 4 | Weight (ppg): | 8.6
Rotary Drilling Hrs: |  |  |  | 36.28 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 140.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 167.98 / 43.71 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 6.33 |  | 118.33 |  | Grade In: |  | New
% Slide: |  |  |  | 15.7 |  | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
% Rotary: |  |  |  | 84.3 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Jeff Cambpell |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Ramon Ries
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | 5 | 2 |  |  |  |  | 34.11 |  | 34.86
BTI Valve |  |  |  | 5 | 2.5 |  |  |  |  | 2.37 |  | 37.23
5" NMPDC |  |  |  | 5.063 | 2.563 |  |  |  |  | 9.46 |  | 46.69
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 49.18
5" NMDC |  |  |  | 5 | 2.25 |  |  |  |  | 30.43 |  | 79.61
5" NMDC |  |  |  | 5.063 | 2.5 |  |  |  |  | 29.89 |  | 109.5
Tomax Thruster |  |  |  | 5 | 2 |  |  |  |  | 17.75 |  | 127.25
X/O- DS42B x XT39P |  |  |  | 5.375 | 2.25 |  |  |  |  | 3.08 |  | 130.33
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2686.92
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.51 |  | 2710.43
2710.43
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 44.2 | 80 | 304 | 330 | 3791.67 | 2800 | 152 | 300 | 220 | 160 | 16000 | 7500
Run | 116.14 | 40.95 | 68.78 | 298 | 337.67 | 3783.56 | 2941.1 | 152 | 282.88 | 218.42 | 165.48 | 14673.47 | 7500
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/26/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/26/2020 |  | 4 |  | 100 |  | 4 | 400
Post Well survey Management |  |  |  |  | 12/26/2020 |  | 10 |  | 1850 |  | 1 | 1850
Total | [11 empty] | 9100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/26/2020 | 00:00 | 00:30 | 0.5 | 17167 | 17167 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5D | Circulate and spot mud cap
12/26/2020 | 00:30 | 05:30 | 5 | 17167 | 17167 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6B | TOH
12/26/2020 | 05:30 | 06:20 | 0.83 | 17167 | 17167 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6P | L/D BHA
12/26/2020 | 06:20 | 24:00 | 17.67 | 17167 | 17167 | 0 | LAT |  | 24B | Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_27_2020_DDR
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33515 / 20DD0325MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Fat Tire A1H
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Longitude: |  | 96° 46' 58.224" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/27/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 125200
|  |  |  | 24hr Summary: |  | Standby for Casing and Cement Ops; Skid Rig t/ B1H; EOW
|  |  |  | 24hr Lookahead: |  | EOW
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17167 |  |  |  | Csg Shoe MD(Usft): |  | 3098 |  | 600: | 22 | PV: | 7
End Depth (Usft): |  | 17167 |  | 17167 |  | OD (in): |  | 10.75 |  | 300: | 15 | YP: | 8
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 41
Slide Drilled (Usft): | [9 empty] | 100: | 9 | Chlorides: | 49000
Rotary Drilled (Usft): | [9 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 5.10
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 4 | Weight (ppg): | 8.6
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 140.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Jeff Cambpell |  | David Leblanc |  |  |  | Neil Shannon
Jim |  | Billy Mcfarland |  | Ramon Ries
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 44.2 | 80 | 304 | 330 | 3791.67 | 2800 | 152 | 300 | 220 | 160 | 16000 | 7500
Run | 0 | 40.95 | 68.78 | 298 | 337.67 | 3783.56 | 2941.1 | 152 | 282.88 | 218.42 | 165.48 | 14673.47 | 7500
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 6200 |  | 6000 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 12/27/2020 |  | 3 |  | 4400 |  | 1 | 4400
Perdiem |  |  |  |  | 12/27/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/27/2020 | 00:00 | 24:00 | 24 | 17167 | 17167 | 0 | LAT |  | 24B | Standby for Casing and Cement Ops; Skid Rig t/ B1H; EOW
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 394.82 (Usft)
Well: |  |  | Fat Tire A1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150620 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/11/2020 | Depth In: |  | 105 | Total Drilled: |  | 3000.00 (Usft)
Date Out: |  |  | 12/11/2020 | Depth Out: |  | 3105 | Drilling / Circ Hours: |  | 4.00 / 1.17
Survey Offset: |  |  | 74
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47245 | 13 1/2"- Ulterra - U616S - Jetted - 9x14s | 13.5 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800004 | 8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | 8 | 2 |  | 6 5/8 REG / 6 5/8 REG |  | 37.92 | 39.42
| 3 | SD603913 | 13" - 4 Blade Nortrak Stabilizer (BFF) | 8.188 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 6.9 | 46.32
| 4 | SD52214 | 8" - NMPDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 8.86 | 55.18
| 5 | ZSB775202 | UBHO Sub | 7.75 | 2.813 |  | 6 5/8 REG / 6 5/8 REG |  | 3.11 | 58.29
| 6 | SD50132 | 8" - NMDC | 7.375 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 87.2
| 7 | SD55923 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.54 | 116.74
| 8 | SD116862 | X/O- 4 1/2 IFB x 6 5/8 RegP | 6.563 | 2.875 |  | 4 1/2 IF / 6 5/8 REG |  | 2.78 | 119.52
| 9 | Rig-1 | 9- Joints of HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 275.3 | 394.82
| 10 | [8 empty] | 394.82
Comments
Bit Info= 13 1/2" -Ulterra-U616S SN= 47245 Jets= 9x14's TFA= 1.353 Motor Info= 8", 7/8, 5.9 Stg. @ 1.5? w/ 13" NBS Bit To Bend= 5.45' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | 13 1/2"- Ulterra - U616S - Jetted - 9x14s | 1.35 | Ulterra | U616S | New | 0-0-NO-I-TD | 3000
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  | PDCI / 7/8 5.9 | 5.45 / 1.50 |  | 13 | 8.38 | 0 | 1
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 100 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | 13 |  | 0 |  |  | 1.5
3 |  |  | 13" - 4 Blade Nortrak Stabilizer (BFF) | 13 |  | 0 |  |  | 39.42

## BHA_2_Intermediate
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2679.95 (Usft)
Well: |  |  | Fat Tire A1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150620 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/17/2020 | Depth In: |  | 3105 | Total Drilled: |  | 6832.00 (Usft)
Date Out: |  |  | 12/19/2020 | Depth Out: |  | 9937 | Drilling / Circ Hours: |  | 24.45 / 1.07
Survey Offset: |  |  | 69 | Gamma Offset: |  | 59
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 54317 | 9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s | 9.875 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800065 | 7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 | 8 | 2 | 1.890 / 1.89 | 6 5/8 REG / 6 5/8 REG |  | 38.02 | 39.52
| 3 | SD52214 | 8" - NMPDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 8.86 | 48.38
| 4 | ZSB775202 | UBHO Sub | 7.75 | 2.813 |  | 6 5/8 REG / 6 5/8 REG |  | 3.11 | 51.49
| 5 | SD50132 | 8" - NMDC | 7.375 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 80.4
| 6 | SD55923 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.54 | 109.94
| 7 | SD108685 | X/O- 4 1/2 XHB x 6 5/8 RegP | 6.5 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.12 | 112.06
| 8 | Rig-3 | 2 Stands of 6 1/2" Drill Collars | 6.5 | 2.875 |  | 4 1/2 XH / 4 1/2 XH |  | 186.78 | 298.84
| 9 | SD4555 | X/O- 4 1/2 IFB x 4 1/2 XHP | 6.625 | 2.5 |  | 4 1/2 IF / 4 1/2 XH |  | 3.04 | 301.88
| 10 | Rig-1 | 9- Joints of HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 275.3 | 577.18
| 11 | Rig-2 | 22 Stands of Drill Pipe | 5 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2071.8 | 2648.98
| 12 | AGHF0675-0023 | NOV- Safety Join / Agitator / Shock Sub | 6.75 | 2.5 | 6.750 / 1.94 | 4 1/2 IF / 4 1/2 IF |  | 30.97 | 2679.95
| 13 | [8 empty] | 2679.95
Comments
Bit Info= 9 7/8" -Ulterra-SPL613 SN= 54317 Jets= 6-14's & 3-16's's TFA= 1.491 Motor Info= 8", 7/8, 5.9 Stg. @ 2.00? Slick Bit To Bend= 5.81' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s | 1.49 | Ulterra | SPL613 | New | 0-1-NO-A-X-I-NO-TD | 6832
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 |  |  | PDCI / 7/8 5.9 | 5.81 / 2.00 |  | 0 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 80 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3_Curve_and_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2710.43 (Usft)
Well: |  |  | Fat Tire A1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150620 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/21/2020 | Depth In: |  | 9937 | Total Drilled: |  | 7230.00 (Usft)
Date Out: |  |  | 12/26/2020 | Depth Out: |  | 17167 | Drilling / Circ Hours: |  | 62.25 / 18.18
Survey Offset: |  |  | 70 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13446789 | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250022 | 5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 | 5 | 2 | 5.000 / 1.93 | XT 39 / 3 1/2 Reg |  | 34.11 | 34.86
| 3 | Rig1x | BTI Valve | 5 | 2.5 |  | 4 XT39 / 4 XT39 |  | 2.37 | 37.23
| 4 | SD56679 | 5" NMPDC | 5.063 | 2.563 |  | XT 39 / XT 39 |  | 9.46 | 46.69
| 5 | ZSB500016 | UBHO Sub | 5.125 | 2.5 | 5.000 / 1.70 | XT 39 / XT 39 |  | 2.49 | 49.18
| 6 | SD55955 | 5" NMDC | 5 | 2.25 |  | XT 39 / XT 39 |  | 30.43 | 79.61
| 7 | SD56701 | 5" NMDC | 5.063 | 2.5 |  | XT 39 / XT 39 |  | 29.89 | 109.5
| 8 | A52068 | Tomax Thruster | 5 | 2 |  | XT39 / XT39 |  | 17.75 | 127.25
| 9 | SD119105 | X/O- DS42B x XT39P | 5.375 | 2.25 |  | DS42 / XT 39 |  | 3.08 | 130.33
| 10 | Rig2 | 27 Stands of Drill Pipe | 4.5 | 2 |  | DS42 / DS42 |  | 2556.59 | 2686.92
| 11 | PG525-0015 | DWS Agitator | 5.25 | 2 | 5.250 / 1.63 | DS42 / DS42 |  | 23.51 | 2710.43
| 12 | [8 empty] | 2710.43
Comments
Bit Info= 6 3/4" Security - GTD64M SN=13446789 Jets=6-18's TFA= 1.491 PN= 1138553 Motor Info= 5", 6/7, 8.8 Stg. @ 2.12? w/ True Slick Bit To Bend= 4.08' Pad OD= 5 9/16" Rev / Gal= 0.68 Flow Range= 150-400 Gpm Max Diff=2,240
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 1.49 | Halliburton | GTD64M | New | 2-1-BT-N-X-1/16-CT-TD | 7230
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  | PDCI / 6/7 8.8 | 4.08 / 2.12 |  | 0 | 5.56 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33515 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Well: |  | Fat Tire A1H
|  |  |  | Longitude: |  | 96° 46' 58.224" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/11/2020 08:30 |  | SN: |  | PPM800004 |  |  |  | WOB Rotate (klbs): |  | 14.00
Date Out: |  | 12/11/2020 18:30 |  | Description: |  | 8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 105.00 / 3105.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 96.83
Inc In/Out: |  | 0.11 / 11.01 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 882.52
Azi In/Out: |  | 122.41 / 240.07 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 1506.1
Total Drilled (Usft): |  | 3000 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1870.9
%Slide (Ftg): |  | 7.33 |  | Bit to Bend (Usft): |  | 5.45 |  |  |  | Tq On Btm (kftlbs): |  | 6251.22
%Slide (Time): |  | 21.25 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 220 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 0.85 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.67 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 78.75 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2780 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 13.5
Rotary Hours: |  | 3.15 |  | Length (Usft): |  | 37.92 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 4.00 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 1.17 / 10.00 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 258.82 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-0-NO-I-TD
Rot ROP (Usft/hr): |  | 882.54 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 4.00
Avg ROP (Usft/hr): |  | 750 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 1.17
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
|  |  |  | 0.00 | [8 empty] | 105
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
74 | [11 empty] | 0.00 / 1.97
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
13 1/2"- Ulterra - U616S - Jetted - 9x14s 1.35 |  |  |  | 47245 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS 0.00 |  |  |  | PPM800004 |  | 8 | 2 |  |  |  | 37.92 | 39.42
13" - 4 Blade Nortrak Stabilizer (BFF) 0.00 |  |  |  | SD603913 |  | 8.188 | 2.875 |  |  |  | 6.9 | 46.32
8" - NMPDC 0.00 |  |  |  | SD52214 |  | 8 | 3.25 |  |  |  | 8.86 | 55.18
UBHO Sub 0.00 |  |  |  | ZSB775202 |  | 7.75 | 2.813 |  |  |  | 3.11 | 58.29
8" - NMDC 0.00 |  |  |  | SD50132 |  | 7.375 | 3.25 |  |  |  | 28.91 | 87.2
8" - NMDC 0.00 |  |  |  | SD55923 |  | 8 | 3.25 |  |  |  | 29.54 | 116.74
X/O- 4 1/2 IFB x 6 5/8 RegP 0.00 |  |  |  | SD116862 |  | 6.563 | 2.875 |  |  |  | 2.78 | 119.52
9- Joints of HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 3 |  |  |  | 275.3 | 394.82
0.00 | [11 empty] | 394.82
Additional Comments
BHA performed as expected, drilled surface section per plan. At surface motor drained strong, bearing gap was within tollerance, no visuable signs of damage to BHA at surface. BHA was subject to 105? water base mud. Will re-run BHA on next surface.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33515 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Well: |  | Fat Tire A1H
|  |  |  | Longitude: |  | 96° 46' 58.224" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/17/2020 23:10 |  | SN: |  | PPM800065 |  |  |  | WOB Rotate (klbs): |  | 36.00
Date Out: |  | 12/19/2020 21:30 |  | Description: |  | 7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 3105.00 / 9937.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 78.41
Inc In/Out: |  | 11.01 / 10.64 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 784.49
Azi In/Out: |  | 240.09 / 329.16 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 3806.12
Total Drilled (Usft): |  | 6832 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4569.9
%Slide (Ftg): |  | 7.14 |  | Bit to Bend (Usft): |  | 5.81 |  |  |  | Tq On Btm (kftlbs): |  | 16323.17
%Slide (Time): |  | 43.89 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 10000
Slide Drilled (Usft): |  | 488 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 10.73 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.86 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 56.11 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6344 |  | Fishneck OD (in): |  | 1.89 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 13.72 |  | Length (Usft): |  | 38.02 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 24.45 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 1.07 / 46.33 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 45.48 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-NO-A-X-I-NO-TD
Rot ROP (Usft/hr): |  | 462.39 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 24.45
Avg ROP (Usft/hr): |  | 279.43 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 1.07
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 16 / 11 | 7 / 6 |  | 0.00 |  | 10 | 10 | 9.4 | 49000 | OBM | 9.1 |  | 225
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 59 | [8 empty] | 5 |  | 4.28 / 3.22
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s 1.49 |  |  |  | 54317 |  | 9.875 | 2 |  |  |  | 1.5 | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.018 0.00 |  |  |  | PPM800065 |  | 8 | 2 |  |  |  | 38.02 | 39.52
8" - NMPDC 0.00 |  |  |  | SD52214 |  | 8 | 3.25 |  |  |  | 8.86 | 48.38
UBHO Sub 0.00 |  |  |  | ZSB775202 |  | 7.75 | 2.813 |  |  |  | 3.11 | 51.49
8" - NMDC 0.00 |  |  |  | SD50132 |  | 7.375 | 3.25 |  |  |  | 28.91 | 80.4
8" - NMDC 0.00 |  |  |  | SD55923 |  | 8 | 3.25 |  |  |  | 29.54 | 109.94
X/O- 4 1/2 XHB x 6 5/8 RegP 0.00 |  |  |  | SD108685 |  | 6.5 | 2.875 |  |  |  | 2.12 | 112.06
2 Stands of 6 1/2" Drill Collars 0.00 |  |  |  | Rig-3 |  | 6.5 | 2.875 |  |  |  | 186.78 | 298.84
X/O- 4 1/2 IFB x 4 1/2 XHP 0.00 |  |  |  | SD4555 |  | 6.625 | 2.5 |  |  |  | 3.04 | 301.88
9- Joints of HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 3 |  |  |  | 275.3 | 577.18
22 Stands of Drill Pipe 0.00 |  |  |  | Rig-2 |  | 5 | 2.75 |  |  |  | 2071.8 | 2648.98
NOV- Safety Join / Agitator / Shock Sub 0.00 |  |  |  | AGHF0675-0023 |  | 6.75 | 2.5 |  |  |  | 30.97 | 2679.95
-1.00 | [11 empty] | 2679.95
Additional Comments
Motor drained well on surface and showed no visible signs of wear w/ minimal slack in bearings; Bit showed no dull characteristics and appeared to be new
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1150620 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33515 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.911" N |  |  | Well: |  | Fat Tire A1H
|  |  |  | Longitude: |  | 96° 46' 58.224" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/21/2020 08:00 |  | SN: |  | PPM250022 |  |  |  | WOB Rotate (klbs): |  | 40.00
Date Out: |  | 12/26/2020 06:20 |  | Description: |  | 5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 9937.00 / 17167.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 68.78
Inc In/Out: |  | 10.66 / 95.82 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 337.67
Azi In/Out: |  | 329.17 / 331.72 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 2941.1
Total Drilled (Usft): |  | 7230 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 3783.56
%Slide (Ftg): |  | 15.70 |  | Bit to Bend (Usft): |  | 4.08 |  |  |  | Tq On Btm (kftlbs): |  | 14673.47
%Slide (Time): |  | 41.72 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 7500
Slide Drilled (Usft): |  | 1135 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 25.97 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 84.30 |  | Kickpad OD (in): |  | 5.563 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 58.28 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 6095 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 36.28 |  | Length (Usft): |  | 34.11 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 62.25 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 18.18 / 118.33 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 43.7 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 2-1-BT-N-X-1/16-CT-TD
Rot ROP (Usft/hr): |  | 168 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 62.25
Avg ROP (Usft/hr): |  | 116.14 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 18.18
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
22 / 15 | 12 / 9 | 5 / 4 |  | 0.00 |  | 7 | 8 | 8.6 | 49000 | OBM | 5.1 |  | 304
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
70 | 57 | [10 empty] | 0.00 / 14.20
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s 1.49 |  |  |  | 13446789 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 0.00 |  |  |  | PPM250022 |  | 5 | 2 |  |  |  | 34.11 | 34.86
BTI Valve 0.00 |  |  |  | Rig1x |  | 5 | 2.5 |  |  |  | 2.37 | 37.23
5" NMPDC 0.00 |  |  |  | SD56679 |  | 5.063 | 2.563 |  |  |  | 9.46 | 46.69
UBHO Sub 0.00 |  |  |  | ZSB500016 |  | 5.125 | 2.5 |  |  |  | 2.49 | 49.18
5" NMDC 0.00 |  |  |  | SD55955 |  | 5 | 2.25 |  |  |  | 30.43 | 79.61
5" NMDC 0.00 |  |  |  | SD56701 |  | 5.063 | 2.5 |  |  |  | 29.89 | 109.5
Tomax Thruster 0.00 |  |  |  | A52068 |  | 5 | 2 |  |  |  | 17.75 | 127.25
X/O- DS42B x XT39P 0.00 |  |  |  | SD119105 |  | 5.375 | 2.25 |  |  |  | 3.08 | 130.33
27 Stands of Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 2 |  |  |  | 2556.59 | 2686.92
DWS Agitator 0.00 |  |  |  | PG525-0015 |  | 5.25 | 2 |  |  |  | 23.51 | 2710.43
-1.00 | [11 empty] | 2710.43
Additional Comments
Motor drained well on surface and showed no visible signs of wear w/ minimal slack in bearings; Bit was worn with 3 chipped cutters on inner row and 1 chipped on guage row; Bit was graded 2-1
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #1 (Surface) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3000
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 220
Well Name: |  |  |  |  | Fat Tire A1H |  |  | Survey / Gamma Offset: |  |  |  |  | 74.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 329.63 |  | Rotate: |  | 2780
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/11/2020 | 08:30 | 09:00 | 0.5 | 105 | 212 | 107 | Rotate |  | 138 | 0.14 | 122.41 | 138 | -0.09 | 0.14 | -0.09 | 0.1 |  |  | 5 | 50 | 480 | 2400 | 214 | 675 | 600 | 75 | 78 | 60 | 60 | 60
12/11/2020 | 09:10 | 09:17 | 0.11667 | 212 | 303 | 91 | Rotate |  | 229 | 0.43 | 70.01 | 229 | -0.03 | 0.56 | -0.03 | 0.4 |  |  | 5 | 50 | 576 | 2400 | 780 | 720 | 675 | 45 | 78 | 60 | 60 | 60
12/11/2020 | 09:25 | 09:29 | 0.066667 | 303 | 394 | 91 | Rotate |  | 320 | 0.48 | 80.96 | 320 | 0.14 | 1.25 | 0.14 | 0.11 |  |  | 7 | 70 | 770 | 6000 | 1365 | 1400 | 1130 | 270 | 78 | 60 | 60 | 60
12/11/2020 | 09:35 | 09:41 | 0.1 | 394 | 489 | 95 | Rotate |  | 415 | 0.27 | 66.04 | 414.99 | 0.3 | 1.85 | 0.3 | 0.24 |  |  | 7 | 100 | 900 | 6000 | 950 | 1700 | 1450 | 250 | 78 | 60 | 60 | 60
12/11/2020 | 09:47 | 09:48 | 0.016667 | 489 | 500 | 11 | Rotate | Drilling Parameters WOB: 7; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 660 | 1700 | 1450 | 250 | 78 | 60 | 60 | 60
12/11/2020 | 09:48 | 09:53 | 0.083333 | 500 | 515 | 15 | Slide | 0 | 510 | 0.78 | 280.11 | 509.99 | 0.5 | 1.42 | 0.5 | 1.07 |  |  | 3 |  | 900 |  | 180 | 1550 | 1450 | 100 | 78 | 60 | 60 | 60
12/11/2020 | 09:53 | 09:56 | 0.05 | 515 | 584 | 69 | Rotate | Drilling Parameters WOB: 7; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1380 | 1700 | 1450 | 250 | 78 | 60 | 60 | 60
12/11/2020 | 10:02 | 10:09 | 0.11667 | 584 | 678 | 94 | Rotate |  | 604 | 1.3 | 273.35 | 603.98 | 0.68 | -0.27 | 0.68 | 0.57 |  |  | 10 | 100 | 900 | 6000 | 805.71 | 1800 | 1450 | 350 | 82 | 65 | 60 | 60
12/11/2020 | 10:15 | 10:22 | 0.11667 | 678 | 773 | 95 | Rotate |  | 699 | 1.67 | 285.84 | 698.94 | 1.12 | -2.68 | 1.12 | 0.52 |  |  | 10 | 100 | 900 | 6000 | 814.29 | 1800 | 1450 | 350 | 82 | 65 | 60 | 60
12/11/2020 | 10:37 | 10:38 | 0.016667 | 773 | 785 | 12 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 720 | 1800 | 1450 | 350 | 82 | 65 | 60 | 60
12/11/2020 | 10:38 | 10:45 | 0.11667 | 785 | 805 | 20 | Slide | 0 | 793 | 2.18 | 261.96 | 792.89 | 1.24 | -5.77 | 1.24 | 1 |  |  | 3 |  | 900 |  | 171.43 | 1550 | 1450 | 100 | 82 | 65 | 60 | 60
12/11/2020 | 10:45 | 10:48 | 0.05 | 805 | 867 | 62 | Rotate | Drilling Parameters WOB: 17; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1240 | 1800 | 1450 | 350 | 86 | 65 | 60 | 60
12/11/2020 | 10:53 | 10:56 | 0.05 | 867 | 961 | 94 | Rotate |  | 887 | 2.42 | 256.47 | 886.82 | 0.53 | -9.47 | 0.53 | 0.35 |  |  | 17 | 100 | 900 | 6000 | 1880 | 1800 | 1450 | 350 | 86 | 65 | 60 | 60
12/11/2020 | 11:02 | 11:03 | 0.016667 | 961 | 965 | 4 | Rotate | Drilling Parameters WOB: 17; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 240 | 1800 | 1450 | 350 | 86 | 65 | 60 | 60
12/11/2020 | 11:03 | 11:07 | 0.066667 | 965 | 985 | 20 | Slide | 0 | 982 | 3.53 | 247.4 | 981.69 | -1.07 | -14.12 | -1.07 | 1.27 |  |  | 5 |  | 900 |  | 300 | 1550 | 1450 | 100 | 86 | 65 | 60 | 60
12/11/2020 | 11:07 | 11:11 | 0.066667 | 985 | 1056 | 71 | Rotate | Drilling Parameters WOB: 17; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1065 | 1800 | 1450 | 350 | 86 | 65 | 60 | 60
12/11/2020 | 11:16 | 11:17 | 0.016667 | 1056 | 1065 | 9 | Rotate | Drilling Parameters WOB: 17; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 540 | 1800 | 1450 | 350 | 86 | 65 | 60 | 60
12/11/2020 | 11:17 | 11:21 | 0.066667 | 1065 | 1085 | 20 | Slide | 0 | 1075 | 4.84 | 237.09 | 1074.44 | -4.3 | -20.06 | -4.3 | 1.62 |  |  | 5 |  | 900 |  | 300 | 1550 | 1450 | 100 | 86 | 65 | 60 | 60
12/11/2020 | 11:21 | 11:24 | 0.05 | 1085 | 1149 | 64 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1280 | 1800 | 1450 | 350 | 86 | 65 | 60 | 60
12/11/2020 | 11:30 | 11:31 | 0.016667 | 1149 | 1160 | 11 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 660 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 11:31 | 11:36 | 0.083333 | 1160 | 1190 | 30 | Slide | 0 | 1169 | 6.46 | 235.04 | 1167.98 | -9.48 | -27.72 | -9.48 | 1.74 |  |  | 5 |  | 900 |  | 360 | 1650 | 1500 | 150 | 86 | 85 | 80 | 75
12/11/2020 | 11:36 | 11:40 | 0.066667 | 1190 | 1243 | 53 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 795 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 11:44 | 11:45 | 0.016667 | 1243 | 1255 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 720 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 11:45 | 11:48 | 0.05 | 1255 | 1280 | 25 | Slide | 0 | 1263 | 8.22 | 239.21 | 1261.21 | -15.95 | -37.83 | -15.95 | 1.96 |  |  | 5 |  | 900 |  | 500 | 1650 | 1500 | 150 | 86 | 85 | 80 | 75
12/11/2020 | 11:48 | 11:52 | 0.066667 | 1280 | 1337 | 57 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 855 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 11:57 | 12:03 | 0.1 | 1337 | 1430 | 93 | Rotate |  | 1356 | 9.03 | 241.73 | 1353.15 | -22.81 | -49.97 | -22.81 | 0.96 |  |  | 20 | 100 | 900 | 6000 | 930 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 12:07 | 12:08 | 0.016667 | 1430 | 1440 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 600 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 12:08 | 12:14 | 0.1 | 1440 | 1465 | 25 | Slide | 0 | 1450 | 9.92 | 238.16 | 1445.87 | -30.58 | -63.34 | -30.58 | 1.13 |  |  | 5 |  | 900 |  | 250 | 1650 | 1500 | 150 | 86 | 85 | 80 | 75
12/11/2020 | 12:14 | 12:17 | 0.05 | 1465 | 1524 | 59 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1180 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 12:22 | 12:27 | 0.083333 | 1524 | 1618 | 94 | Rotate |  | 1544 | 10.79 | 237.68 | 1538.34 | -39.56 | -77.66 | -39.56 | 0.93 |  |  | 20 | 100 | 900 | 6000 | 1128 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 12:33 | 12:36 | 0.05 | 1618 | 1712 | 94 | Rotate |  | 1638 | 10.5 | 236.76 | 1630.72 | -48.96 | -92.26 | -48.96 | 0.36 |  |  | 20 | 100 | 900 | 6000 | 1880 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 12:41 | 12:46 | 0.083333 | 1712 | 1805 | 93 | Rotate |  | 1731 | 10.29 | 236.09 | 1722.19 | -58.23 | -106.24 | -58.23 | 0.26 |  |  | 20 | 100 | 900 | 6000 | 1116 | 1900 | 1500 | 400 | 86 | 85 | 80 | 75
12/11/2020 | 12:51 | 12:56 | 0.083333 | 1805 | 1900 | 95 | Rotate |  | 1826 | 10.17 | 238.01 | 1815.68 | -67.41 | -120.39 | -67.41 | 0.38 |  |  | 20 | 100 | 900 | 8500 | 1140 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:00 | 13:06 | 0.1 | 1900 | 1994 | 94 | Rotate |  | 1920 | 9.79 | 237.39 | 1908.26 | -76.11 | -134.16 | -76.11 | 0.42 |  |  | 20 | 100 | 900 | 8500 | 940 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:11 | 13:12 | 0.016667 | 1994 | 2005 | 11 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 660 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:12 | 13:19 | 0.11667 | 2005 | 2030 | 25 | Slide | 0 | 2013 | 10.1 | 239.67 | 1999.87 | -84.49 | -147.86 | -84.49 | 0.54 |  |  | 12 |  | 900 |  | 214.29 | 2100 | 1900 | 200 | 98 | 90 | 85 | 80
12/11/2020 | 13:19 | 13:24 | 0.083333 | 2030 | 2087 | 57 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 684 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:28 | 13:33 | 0.083333 | 2087 | 2182 | 95 | Rotate |  | 2108 | 10.33 | 241.13 | 2093.36 | -92.81 | -162.51 | -92.81 | 0.36 |  |  | 20 | 100 | 900 | 8500 | 1140 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:38 | 13:42 | 0.066667 | 2182 | 2277 | 95 | Rotate |  | 2203 | 10.24 | 241.38 | 2186.83 | -100.97 | -177.38 | -100.97 | 0.11 |  |  | 20 | 100 | 900 | 8500 | 1425 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:47 | 13:53 | 0.1 | 2277 | 2371 | 94 | Rotate |  | 2297 | 10.14 | 241.13 | 2279.35 | -108.97 | -191.96 | -108.97 | 0.12 |  |  | 20 | 100 | 900 | 8500 | 940 | 2600 | 1900 | 700 | 98 | 90 | 85 | 80
12/11/2020 | 13:58 | 14:03 | 0.083333 | 2371 | 2466 | 95 | Rotate |  | 2392 | 9.92 | 241.85 | 2372.9 | -116.87 | -206.5 | -116.87 | 0.27 |  |  | 20 | 100 | 900 | 6000 | 1140 | 1900 | 1500 | 400 | 98 | 85 | 80 | 75
12/11/2020 | 14:08 | 14:13 | 0.083333 | 2466 | 2560 | 94 | Rotate |  | 2486 | 9.47 | 242.45 | 2465.56 | -124.26 | -220.5 | -124.26 | 0.49 |  |  | 20 | 100 | 900 | 6000 | 1128 | 1900 | 1500 | 400 | 98 | 85 | 80 | 75
12/11/2020 | 14:19 | 14:20 | 0.016667 | 2560 | 2570 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 600 | 1900 | 1500 | 400 | 104 | 85 | 80 | 75
12/11/2020 | 14:20 | 14:30 | 0.16667 | 2570 | 2610 | 40 | Slide | 0 | 2580 | 10.1 | 239.67 | 2558.19 | -132 | -234.47 | -132 | 0.84 |  |  | 12 |  | 900 |  | 240 | 1900 | 1500 | 400 | 104 | 85 | 80 | 75
12/11/2020 | 14:30 | 14:34 | 0.066667 | 2610 | 2654 | 44 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 660 | 1900 | 1500 | 400 | 104 | 85 | 80 | 75
12/11/2020 | 14:41 | 14:44 | 0.05 | 2654 | 2748 | 94 | Rotate |  | 2674 | 11.82 | 236.04 | 2650.47 | -141.54 | -249.57 | -141.54 | 1.97 |  |  | 20 | 100 | 900 | 6000 | 1880 | 1900 | 1500 | 400 | 104 | 85 | 80 | 75
12/11/2020 | 14:50 | 14:55 | 0.083333 | 2748 | 2842 | 94 | Rotate |  | 2768 | 11.85 | 235.53 | 2742.47 | -152.38 | -265.51 | -152.38 | 0.12 |  |  | 20 | 100 | 900 | 6000 | 1128 | 1900 | 1500 | 400 | 104 | 85 | 80 | 75
12/11/2020 | 15:00 | 15:08 | 0.13333 | 2842 | 2936 | 94 | Rotate |  | 2862 | 11.4 | 232.97 | 2834.55 | -163.44 | -280.88 | -163.44 | 0.73 |  |  | 20 | 100 | 900 | 6000 | 705 | 1900 | 1500 | 400 | 105 | 85 | 80 | 75
12/11/2020 | 15:13 | 15:18 | 0.083333 | 2936 | 3030 | 94 | Rotate |  | 2956 | 11.19 | 232.77 | 2926.72 | -174.55 | -295.56 | -174.55 | 0.23 |  |  | 20 | 100 | 900 | 6000 | 1128 | 1900 | 1500 | 400 | 105 | 85 | 80 | 75
12/11/2020 | 15:23 | 15:30 | 0.11667 | 3030 | 3105 | 75 | Rotate |  | 3031 | 11.12 | 231.55 | 3000.31 | -183.45 | -307.02 | -183.45 | 0.33 |  |  | 20 | 100 | 900 | 6000 | 642.86 | 1900 | 1500 | 400 | 105 | 85 | 80 | 75

## BHA_2_Intermediate_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #2 (Intermediate) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6835
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 509
Well Name: |  |  |  |  | Fat Tire A1H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 59.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 329.63 |  | Rotate: |  | 6326
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/18/2020 | 03:05 | 03:08 | 0.05 | 3105 | 3115 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 200 | 1500 | 1300 | 200 | 97 | 135 | 130 | 125
12/18/2020 | 03:25 | 03:38 | 0.21667 | 3115 | 3150 | 35 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 161.54 | 1600 | 1300 | 300 | 97 | 135 | 130 | 125
12/18/2020 | 03:43 | 03:54 | 0.18333 | 3150 | 3172 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 420; Drilling Parameters ROP: 120 | 1500 | 1300 | 200 | 97 | 135 | 130 | 125
12/18/2020 | 03:54 | 04:09 | 0.25 | 3172 | 3244 | 72 | Rotate |  | 3175 | 11.12 | 248.15 | 3141.64 | -197.26 | -330.79 | -197.26 | 2.22 |  |  | 30 | 40 | 420 | 7000 | 288 | 1600 | 1300 | 300 | 97 | 135 | 130 | 125
12/18/2020 | 04:12 | 04:20 | 0.13333 | 3244 | 3337 | 93 | Rotate |  | 3268 | 11.31 | 250.76 | 3232.87 | -203.6 | -347.72 | -203.6 | 0.58 |  |  | 28 | 80 | 800 | 10000 | 697.5 | 4100 | 3600 | 500 | 98 | 135 | 130 | 125
12/18/2020 | 04:23 | 04:30 | 0.11667 | 3337 | 3431 | 94 | Rotate |  | 3362 | 11.49 | 249.85 | 3325.01 | -209.86 | -365.22 | -209.86 | 0.27 |  |  | 30 | 80 | 800 | 10000 | 805.71 | 4200 | 3600 | 600 | 98 | 135 | 130 | 125
12/18/2020 | 04:35 | 04:42 | 0.11667 | 3431 | 3525 | 94 | Rotate |  | 3456 | 11.58 | 248.11 | 3417.11 | -216.61 | -382.76 | -216.61 | 0.38 |  |  | 35 | 80 | 800 | 12000 | 805.71 | 4200 | 3600 | 600 | 117 | 160 | 150 | 135
12/18/2020 | 04:46 | 04:48 | 0.033333 | 3525 | 3527 | 2 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 60 | 4200 | 3600 | 600 | 117 | 160 | 150 | 135
12/18/2020 | 04:48 | 05:00 | 0.2 | 3527 | 3545 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 90 | 3800 | 3600 | 200 | 117 | 160 | 150 | 135
12/18/2020 | 05:00 | 05:09 | 0.15 | 3545 | 3618 | 73 | Rotate |  | 3549 | 11.74 | 236.74 | 3508.21 | -225.28 | -399.33 | -225.28 | 2.47 |  |  | 35 | 80 | 800 | 12000 | 486.67 | 4200 | 3600 | 600 | 117 | 160 | 150 | 135
12/18/2020 | 05:12 | 05:18 | 0.1 | 3618 | 3712 | 94 | Rotate |  | 3643 | 12.06 | 233.13 | 3600.19 | -236.41 | -415.19 | -236.41 | 0.86 |  |  | 38 | 80 | 800 | 12000 | 940 | 4000 | 3600 | 400 | 124 | 160 | 150 | 135
12/18/2020 | 05:22 | 05:35 | 0.21667 | 3712 | 3732 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 92.31 | 4000 | 3600 | 400 | 124 | 160 | 150 | 135
12/18/2020 | 05:35 | 05:42 | 0.11667 | 3732 | 3805 | 73 | Rotate |  | 3736 | 10.19 | 240.93 | 3691.44 | -246.24 | -430.15 | -246.24 | 2.58 |  |  | 38 | 80 | 800 | 12000 | 625.71 | 4200 | 3600 | 600 | 124 | 160 | 150 | 135
12/18/2020 | 05:47 | 05:52 | 0.083333 | 3805 | 3899 | 94 | Rotate |  | 3830 | 9.83 | 240.54 | 3784.01 | -254.23 | -444.41 | -254.23 | 0.39 |  |  | 40 | 80 | 800 | 12000 | 1128 | 4200 | 3600 | 600 | 124 | 170 | 150 | 135
12/18/2020 | 05:57 | 06:03 | 0.1 | 3899 | 3993 | 94 | Rotate |  | 3924 | 9.84 | 238 | 3876.63 | -262.43 | -458.2 | -262.43 | 0.46 |  |  | 40 | 80 | 800 | 12000 | 940 | 4200 | 3600 | 600 | 124 | 170 | 150 | 135
12/18/2020 | 06:08 | 06:15 | 0.11667 | 3993 | 4086 | 93 | Rotate |  | 4017 | 9.79 | 238.96 | 3968.27 | -270.72 | -471.72 | -270.72 | 0.18 |  |  | 40 | 80 | 800 | 12000 | 797.14 | 4200 | 3600 | 600 | 124 | 170 | 150 | 135
12/18/2020 | 06:20 | 06:25 | 0.083333 | 4086 | 4180 | 94 | Rotate |  | 4111 | 9.62 | 238.91 | 4060.92 | -278.9 | -485.29 | -278.9 | 0.18 |  |  | 40 | 80 | 800 | 12000 | 1128 | 4200 | 3600 | 600 | 124 | 170 | 150 | 135
12/18/2020 | 06:30 | 06:36 | 0.1 | 4180 | 4274 | 94 | Rotate |  | 4205 | 8.81 | 239.3 | 4153.71 | -286.63 | -498.21 | -286.63 | 0.86 |  |  | 40 | 80 | 800 | 12000 | 940 | 4600 | 3600 | 1000 | 124 | 170 | 150 | 135
12/18/2020 | 06:40 | 06:47 | 0.11667 | 4274 | 4368 | 94 | Rotate |  | 4299 | 8.53 | 238.42 | 4246.63 | -293.95 | -510.34 | -293.95 | 0.33 |  |  | 40 | 80 | 800 | 12000 | 805.71 | 4600 | 3600 | 1000 | 124 | 170 | 150 | 135
12/18/2020 | 06:52 | 06:55 | 0.05 | 4368 | 4380 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 240 | 4600 | 3600 | 1000 | 124 | 170 | 150 | 135
12/18/2020 | 06:55 | 07:01 | 0.1 | 4380 | 4400 | 20 | Slide | 0 | 4393 | 9.56 | 244.99 | 4339.47 | -300.9 | -523.35 | -300.9 | 1.55 |  |  | 12 |  | 800 |  | 200 | 3800 | 3600 | 200 | 124 | 170 | 150 | 135
12/18/2020 | 07:01 | 07:08 | 0.11667 | 4400 | 4462 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 531.43 | 4600 | 3600 | 1000 | 124 | 170 | 150 | 135
12/18/2020 | 07:13 | 07:20 | 0.11667 | 4462 | 4554 | 92 | Rotate |  | 4485 | 10.62 | 246.53 | 4430.04 | -307.51 | -538.05 | -307.51 | 1.19 |  |  | 40 | 80 | 800 | 12000 | 788.57 | 4600 | 3600 | 1000 | 124 | 170 | 150 | 135
12/18/2020 | 07:25 | 07:31 | 0.1 | 4554 | 4648 | 94 | Rotate |  | 4579 | 10.21 | 247.35 | 4522.49 | -314.17 | -553.68 | -314.17 | 0.46 |  |  | 40 | 80 | 800 | 12000 | 940 | 4600 | 3600 | 1000 | 124 | 170 | 150 | 135
12/18/2020 | 07:35 | 07:42 | 0.11667 | 4648 | 4743 | 95 | Rotate |  | 4674 | 9.89 | 245.72 | 4616.04 | -320.77 | -568.89 | -320.77 | 0.45 |  |  | 40 | 80 | 800 | 14000 | 814.29 | 4600 | 3600 | 1000 | 145 | 185 | 170 | 155
12/18/2020 | 07:47 | 07:55 | 0.13333 | 4743 | 4837 | 94 | Rotate |  | 4768 | 9.64 | 244.84 | 4708.67 | -327.43 | -583.37 | -327.43 | 0.31 |  |  | 40 | 80 | 800 | 14000 | 705 | 4600 | 3600 | 1000 | 145 | 185 | 170 | 155
12/18/2020 | 08:00 | 08:06 | 0.1 | 4837 | 4931 | 94 | Rotate |  | 4862 | 9.55 | 243.73 | 4801.36 | -334.23 | -597.49 | -334.23 | 0.22 |  |  | 40 | 80 | 800 | 14000 | 940 | 4600 | 3600 | 1000 | 145 | 185 | 170 | 155
12/18/2020 | 08:11 | 08:18 | 0.11667 | 4931 | 5025 | 94 | Rotate |  | 4956 | 9.74 | 244.42 | 4894.03 | -341.11 | -611.65 | -341.11 | 0.24 |  |  | 40 | 80 | 800 | 14000 | 805.71 | 4600 | 3600 | 1000 | 145 | 185 | 170 | 155
12/18/2020 | 08:23 | 08:30 | 0.11667 | 5025 | 5119 | 94 | Rotate |  | 5050 | 8.98 | 246.08 | 4986.78 | -347.52 | -625.53 | -347.52 | 0.86 |  |  | 40 | 80 | 800 | 14000 | 805.71 | 4600 | 3600 | 1000 | 154 | 185 | 170 | 155
12/18/2020 | 08:35 | 08:42 | 0.11667 | 5119 | 5214 | 95 | Rotate |  | 5145 | 8.41 | 244.3 | 5080.69 | -353.54 | -638.57 | -353.54 | 0.66 |  |  | 40 | 80 | 800 | 14000 | 814.29 | 4600 | 3600 | 1000 | 154 | 185 | 170 | 155
12/18/2020 | 08:47 | 08:55 | 0.13333 | 5214 | 5308 | 94 | Rotate |  | 5239 | 8.34 | 243.87 | 5173.68 | -359.52 | -650.88 | -359.52 | 0.1 |  |  | 40 | 80 | 800 | 14000 | 705 | 4600 | 3600 | 1000 | 154 | 185 | 170 | 155
12/18/2020 | 09:05 | 09:11 | 0.1 | 5308 | 5401 | 93 | Rotate |  | 5332 | 8.47 | 245.05 | 5265.68 | -365.38 | -663.15 | -365.38 | 0.23 |  |  | 40 | 80 | 800 | 14000 | 930 | 4600 | 3600 | 1000 | 161 | 185 | 170 | 155
12/18/2020 | 09:15 | 09:25 | 0.16667 | 5401 | 5495 | 94 | Rotate |  | 5426 | 7.87 | 243.23 | 5358.73 | -371.2 | -675.17 | -371.2 | 0.69 |  |  | 40 | 80 | 800 | 14000 | 564 | 4600 | 3600 | 1000 | 161 | 185 | 170 | 155
12/18/2020 | 09:30 | 09:32 | 0.033333 | 5495 | 5510 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 450 | 4600 | 3600 | 1000 | 161 | 185 | 170 | 155
12/18/2020 | 09:32 | 09:45 | 0.21667 | 5510 | 5528 | 18 | Slide | 0 | 5520 | 7.62 | 241.41 | 5451.87 | -377.08 | -686.39 | -377.08 | 0.37 |  |  | 18 |  | 800 |  | 83.08 | 3800 | 3600 | 200 | 161 | 185 | 170 | 155
12/18/2020 | 09:45 | 09:56 | 0.18333 | 5528 | 5589 | 61 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 332.73 | 4600 | 3600 | 1000 | 161 | 185 | 170 | 155
12/18/2020 | 10:00 | 10:08 | 0.13333 | 5589 | 5683 | 94 | Rotate |  | 5614 | 7.67 | 243.78 | 5545.04 | -382.84 | -697.49 | -382.84 | 0.34 |  |  | 40 | 80 | 800 | 17000 | 705 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 10:13 | 10:16 | 0.05 | 5683 | 5700 | 17 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 340 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 10:16 | 10:36 | 0.33333 | 5700 | 5730 | 30 | Slide | 0 | 5707 | 8.57 | 235.07 | 5637.11 | -389.55 | -708.74 | -389.55 | 1.64 |  |  | 20 |  | 800 |  | 90 | 3800 | 3600 | 200 | 161 | 195 | 175 | 160
12/18/2020 | 10:36 | 10:45 | 0.15 | 5730 | 5776 | 46 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 306.67 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 10:50 | 10:59 | 0.15 | 5776 | 5870 | 94 | Rotate |  | 5801 | 10.36 | 225.04 | 5729.83 | -399.53 | -720.46 | -399.53 | 2.58 |  |  | 40 | 80 | 800 | 17000 | 626.67 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 11:04 | 11:15 | 0.18333 | 5870 | 5965 | 95 | Rotate |  | 5896 | 10.2 | 223.87 | 5823.31 | -411.63 | -732.34 | -411.63 | 0.28 |  |  | 40 | 80 | 800 | 17000 | 518.18 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 11:20 | 11:23 | 0.05 | 5965 | 5975 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 200 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 11:23 | 11:34 | 0.18333 | 5975 | 5995 | 20 | Slide | 0 | 5990 | 8.59 | 224.12 | 5916.04 | -422.67 | -742.99 | -422.67 | 1.71 |  |  | 20 |  | 800 |  | 109.09 | 3800 | 3600 | 200 | 161 | 195 | 175 | 160
12/18/2020 | 11:34 | 11:43 | 0.15 | 5995 | 6059 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 426.67 | 4600 | 3600 | 1000 | 161 | 195 | 175 | 160
12/18/2020 | 11:48 | 11:51 | 0.05 | 6059 | 6070 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 220 | 4600 | 3600 | 1000 | 174 | 195 | 175 | 160
12/18/2020 | 11:51 | 12:01 | 0.16667 | 6070 | 6085 | 15 | Slide | 0 | 6084 | 6.91 | 226.77 | 6009.18 | -431.59 | -752 | -431.59 | 1.83 |  |  | 20 |  | 800 |  | 90 | 3800 | 3600 | 200 | 174 | 210 | 195 | 175
12/18/2020 | 12:01 | 12:10 | 0.15 | 6085 | 6153 | 68 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 453.33 | 4600 | 3600 | 1000 | 174 | 195 | 175 | 160
12/18/2020 | 12:15 | 12:17 | 0.033333 | 6153 | 6165 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 360 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 12:17 | 12:34 | 0.28333 | 6165 | 6185 | 20 | Slide | 0 | 6178 | 5.61 | 227.2 | 6102.62 | -438.58 | -759.49 | -438.58 | 1.38 |  |  | 20 |  | 800 |  | 70.59 | 3800 | 3600 | 200 | 174 | 210 | 195 | 175
12/18/2020 | 12:34 | 12:45 | 0.18333 | 6185 | 6247 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 338.18 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 12:50 | 12:53 | 0.05 | 6247 | 6260 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 260 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 12:53 | 13:09 | 0.26667 | 6260 | 6280 | 20 | Slide | 0 | 6272 | 3.61 | 226.68 | 6196.31 | -443.73 | -765.02 | -443.73 | 2.13 |  |  | 20 |  | 800 |  | 75 | 3800 | 3600 | 200 | 174 | 210 | 195 | 175
12/18/2020 | 13:09 | 13:15 | 0.1 | 6280 | 6341 | 61 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 610 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 13:20 | 13:32 | 0.2 | 6341 | 6434 | 93 | Rotate |  | 6365 | 3.27 | 209.56 | 6289.14 | -448.05 | -768.46 | -448.05 | 1.16 |  |  | 40 | 80 | 800 | 17000 | 465 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 13:37 | 13:40 | 0.05 | 6434 | 6450 | 16 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 320 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 13:40 | 13:55 | 0.25 | 6450 | 6475 | 25 | Slide | 0 | 6460 | 1.55 | 214.4 | 6384.06 | -451.47 | -770.52 | -451.47 | 1.82 |  |  | 20 |  | 800 |  | 100 | 3800 | 3600 | 200 | 174 | 210 | 195 | 175
12/18/2020 | 13:55 | 14:05 | 0.16667 | 6475 | 6529 | 54 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 324 | 4600 | 3600 | 1000 | 174 | 210 | 195 | 160
12/18/2020 | 14:10 | 14:20 | 0.16667 | 6529 | 6623 | 94 | Rotate |  | 6554 | 0.56 | 212.89 | 6478.04 | -452.9 | -771.49 | -452.9 | 1.05 |  |  | 40 | 80 | 800 | 18000 | 564 | 5300 | 4300 | 1000 | 185 | 235 | 210 | 175
12/18/2020 | 14:25 | 14:38 | 0.21667 | 6623 | 6717 | 94 | Rotate |  | 6648 | 0.47 | 212.06 | 6572.04 | -453.61 | -771.94 | -453.61 | 0.1 |  |  | 40 | 80 | 800 | 18000 | 433.85 | 5300 | 4300 | 1000 | 185 | 235 | 210 | 175
12/18/2020 | 14:44 | 14:53 | 0.15 | 6717 | 6809 | 92 | Rotate |  | 6740 | 0.72 | 251.89 | 6664.03 | -454.11 | -772.69 | -454.11 | 0.51 |  |  | 40 | 80 | 800 | 18000 | 613.33 | 5300 | 4300 | 1000 | 185 | 235 | 210 | 175
12/18/2020 | 14:58 | 15:09 | 0.18333 | 6809 | 6904 | 95 | Rotate |  | 6835 | 0.69 | 252.44 | 6759.02 | -454.47 | -773.8 | -454.47 | 0.03 |  |  | 40 | 80 | 800 | 18000 | 518.18 | 5300 | 4300 | 1000 | 185 | 235 | 210 | 175
12/18/2020 | 15:15 | 15:26 | 0.18333 | 6904 | 6998 | 94 | Rotate |  | 6929 | 0.64 | 273.28 | 6853.02 | -454.61 | -774.87 | -454.61 | 0.26 |  |  | 40 | 80 | 800 | 18000 | 512.73 | 5300 | 4300 | 1000 | 185 | 235 | 210 | 175
12/18/2020 | 15:30 | 15:41 | 0.18333 | 6998 | 7091 | 93 | Rotate |  | 7022 | 0.75 | 273.71 | 6946.01 | -454.54 | -775.99 | -454.54 | 0.12 |  |  | 40 | 80 | 800 | 18000 | 507.27 | 5300 | 4300 | 1000 | 195 | 235 | 210 | 175
12/18/2020 | 15:45 | 15:55 | 0.16667 | 7091 | 7158 | 67 | Rotate |  | 7116 | 0.81 | 274.55 | 7040 | -454.45 | -777.27 | -454.45 | 0.06 |  |  | 40 | 80 | 800 | 18000 | 402 | 5300 | 4300 | 1000 | 195 | 235 | 210 | 175
12/18/2020 | 16:00 | 16:09 | 0.15 | 7158 | 7279 | 121 | Rotate |  | 7210 | 0.98 | 286.9 | 7133.99 | -454.16 | -778.7 | -454.16 | 0.27 |  |  | 40 | 80 | 800 | 18000 | 806.67 | 5300 | 4300 | 1000 | 195 | 235 | 210 | 175
12/18/2020 | 16:15 | 16:24 | 0.15 | 7279 | 7373 | 94 | Rotate |  | 7304 | 1.06 | 295.42 | 7227.98 | -453.56 | -780.26 | -453.56 | 0.18 |  |  | 40 | 80 | 800 | 18000 | 626.67 | 5300 | 4300 | 1000 | 195 | 250 | 210 | 185
12/18/2020 | 16:30 | 16:33 | 0.05 | 7373 | 7385 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 240 | 5300 | 4300 | 1000 | 195 | 250 | 210 | 185
12/18/2020 | 16:33 | 16:49 | 0.26667 | 7385 | 7405 | 20 | Slide | 0 | 7398 | 0.49 | 34.64 | 7321.97 | -452.85 | -780.81 | -452.85 | 1.32 |  |  | 20 |  | 800 |  | 75 | 4650 | 4300 | 350 | 195 | 250 | 210 | 185
12/18/2020 | 16:49 | 16:59 | 0.16667 | 7405 | 7467 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 372 | 5300 | 4300 | 1000 | 195 | 250 | 210 | 185
12/18/2020 | 17:10 | 17:17 | 0.11667 | 7467 | 7561 | 94 | Rotate |  | 7492 | 0.86 | 96.81 | 7415.96 | -452.61 | -779.88 | -452.61 | 0.81 |  |  | 40 | 80 | 800 | 18000 | 805.71 | 5300 | 4300 | 1000 | 195 | 250 | 210 | 185
12/18/2020 | 17:23 | 17:30 | 0.11667 | 7561 | 7654 | 93 | Rotate |  | 7585 | 0.61 | 106.78 | 7508.96 | -452.83 | -778.72 | -452.83 | 0.3 |  |  | 40 | 80 | 800 | 18000 | 797.14 | 5200 | 4300 | 900 | 195 | 250 | 210 | 185
12/18/2020 | 17:35 | 17:49 | 0.23333 | 7654 | 7749 | 95 | Rotate |  | 7680 | 0.4 | 148.41 | 7603.95 | -453.26 | -778.06 | -453.26 | 0.43 |  |  | 40 | 80 | 800 | 18000 | 407.14 | 5200 | 4300 | 900 | 203 | 250 | 210 | 185
12/18/2020 | 17:51 | 18:02 | 0.18333 | 7749 | 7842 | 93 | Rotate |  | 7773 | 0.37 | 196.2 | 7696.95 | -453.82 | -777.97 | -453.82 | 0.34 |  |  | 40 | 80 | 800 | 19500 | 507.27 | 5200 | 4300 | 900 | 203 | 250 | 210 | 185
12/18/2020 | 18:05 | 18:20 | 0.25 | 7842 | 7936 | 94 | Rotate |  | 7867 | 0.47 | 331.42 | 7790.95 | -453.78 | -778.24 | -453.78 | 0.83 |  |  | 40 | 80 | 800 | 19500 | 376 | 5200 | 4300 | 900 | 203 | 250 | 210 | 185
12/18/2020 | 18:25 | 18:39 | 0.23333 | 7936 | 8030 | 94 | Rotate |  | 7961 | 0.83 | 318.86 | 7884.94 | -452.93 | -778.87 | -452.93 | 0.41 |  |  | 40 | 80 | 800 | 19500 | 402.86 | 5200 | 4300 | 900 | 203 | 250 | 210 | 185
12/18/2020 | 18:42 | 18:55 | 0.21667 | 8030 | 8123 | 93 | Rotate |  | 8054 | 0.96 | 309.05 | 7977.93 | -451.93 | -779.92 | -451.93 | 0.22 |  |  | 40 | 80 | 800 | 19500 | 429.23 | 5200 | 4300 | 900 | 203 | 250 | 210 | 185
12/18/2020 | 18:59 | 19:02 | 0.05 | 8123 | 8126 | 3 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 19500; Drilling Parameters ROP: 60 | 5200 | 4300 | 900 | 203 | 250 | 210 | 185
12/18/2020 | 19:02 | 19:22 | 0.33333 | 8126 | 8144 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 54 | 4600 | 4300 | 300 | 203 | 250 | 210 | 185
12/18/2020 | 19:22 | 19:38 | 0.26667 | 8144 | 8216 | 72 | Rotate |  | 8147 | 0.77 | 0.9 | 8070.92 | -450.81 | -780.52 | -450.81 | 0.83 |  |  | 40 | 80 | 800 | 20000 | 270 | 5100 | 4300 | 800 | 203 | 250 | 210 | 185
12/18/2020 | 19:41 | 19:55 | 0.23333 | 8216 | 8311 | 95 | Rotate |  | 8242 | 0.84 | 358.91 | 8165.91 | -449.48 | -780.52 | -449.48 | 0.08 |  |  | 40 | 80 | 800 | 20000 | 407.14 | 5100 | 4300 | 800 | 203 | 250 | 210 | 185
12/18/2020 | 19:58 | 20:12 | 0.23333 | 8311 | 8405 | 94 | Rotate |  | 8336 | 1.08 | 331.97 | 8259.9 | -448.01 | -780.95 | -448.01 | 0.54 |  |  | 40 | 80 | 800 | 20000 | 402.86 | 5100 | 4300 | 800 | 203 | 250 | 210 | 185
12/18/2020 | 20:15 | 20:18 | 0.05 | 8405 | 8409 | 4 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 80 | 5100 | 4300 | 800 | 203 | 250 | 210 | 185
12/18/2020 | 20:18 | 20:40 | 0.36667 | 8409 | 8431 | 22 | Slide | 0 | 8430 | 0.1 | 162.72 | 8353.9 | -447.3 | -781.34 | -447.3 | 1.25 |  |  | 18 |  | 800 |  | 60 | 4600 | 4300 | 300 | 210 | 270 | 235 | 210
12/18/2020 | 20:40 | 20:50 | 0.16667 | 8431 | 8499 | 68 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 408 | 5000 | 4400 | 600 | 210 | 270 | 235 | 210
12/18/2020 | 20:53 | 21:07 | 0.23333 | 8499 | 8594 | 95 | Rotate |  | 8525 | 0.42 | 153.4 | 8448.89 | -447.69 | -781.16 | -447.69 | 0.34 |  |  | 42 | 80 | 800 | 22000 | 407.14 | 5200 | 4400 | 800 | 210 | 270 | 235 | 210
12/18/2020 | 21:10 | 21:24 | 0.23333 | 8594 | 8687 | 93 | Rotate |  | 8618 | 0.11 | 135.13 | 8541.89 | -448.06 | -780.95 | -448.06 | 0.34 |  |  | 42 | 80 | 800 | 22000 | 398.57 | 5200 | 4400 | 800 | 210 | 270 | 235 | 210
12/18/2020 | 21:27 | 21:41 | 0.23333 | 8687 | 8781 | 94 | Rotate |  | 8712 | 0.24 | 19.63 | 8635.89 | -447.94 | -780.82 | -447.94 | 0.32 |  |  | 42 | 80 | 800 | 22000 | 402.86 | 5200 | 4400 | 800 | 210 | 270 | 235 | 210
12/18/2020 | 21:44 | 21:57 | 0.21667 | 8781 | 8876 | 95 | Rotate |  | 8807 | 0.95 | 321.73 | 8730.89 | -447.13 | -781.24 | -447.13 | 0.89 |  |  | 42 | 80 | 800 | 22000 | 438.46 | 5200 | 4400 | 800 | 210 | 270 | 235 | 210
12/18/2020 | 22:00 | 22:02 | 0.033333 | 8876 | 8879 | 3 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 5200 | 4400 | 800 | 210 | 270 | 235 | 210
12/18/2020 | 22:02 | 22:22 | 0.33333 | 8879 | 8901 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 66 | 4650 | 4400 | 250 | 218 | 280 | 245 | 220
12/18/2020 | 22:22 | 22:35 | 0.21667 | 8901 | 8970 | 69 | Rotate |  | 8901 | 1.15 | 4.36 | 8824.87 | -445.58 | -781.65 | -445.58 | 0.84 |  |  | 42 | 80 | 800 | 22000 | 318.46 | 5200 | 4400 | 800 | 218 | 280 | 245 | 220
12/18/2020 | 22:38 | 22:40 | 0.033333 | 8970 | 8973 | 3 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 5200 | 4400 | 800 | 218 | 280 | 245 | 220
12/18/2020 | 22:40 | 23:00 | 0.33333 | 8973 | 8999 | 26 | Slide | 0 | 8996 | 0.85 | 125.69 | 8919.87 | -445.04 | -781 | -445.04 | 1.84 |  |  | 18 |  | 800 |  | 78 | 4650 | 4400 | 250 | 218 | 280 | 245 | 220
12/18/2020 | 23:00 | 23:12 | 0.2 | 8999 | 9065 | 66 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 330 | 5200 | 4400 | 800 | 218 | 280 | 245 | 220
12/18/2020 | 23:15 | 23:32 | 0.28333 | 9065 | 9159 | 94 | Rotate |  | 9090 | 0.58 | 160.8 | 9013.86 | -445.9 | -780.28 | -445.9 | 0.53 |  |  | 42 | 80 | 800 | 22000 | 331.76 | 5200 | 4400 | 800 | 218 | 280 | 245 | 220
12/18/2020 | 23:35 | 23:50 | 0.25 | 9159 | 9254 | 95 | Rotate |  | 9185 | 0.47 | 350.87 | 9108.86 | -445.97 | -780.18 | -445.97 | 1.1 |  |  | 42 | 80 | 800 | 22000 | 380 | 5200 | 4400 | 800 | 218 | 280 | 245 | 220
12/18/2020 | 23:53 | 24:00 | 0.11667 | 9254 | 9292 | 38 | Rotate |  | 9279 | 1.25 | 359.08 | 9202.85 | -444.56 | -780.26 | -444.56 | 0.84 |  |  | 42 | 80 | 800 | 22000 | 325.71 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 00:00 | 00:17 | 0.28333 | 9292 | 9348 | 56 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 197.65 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 00:20 | 00:24 | 0.066667 | 9348 | 9349 | 1 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 15 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 00:24 | 01:20 | 0.93333 | 9349 | 9375 | 26 | Slide | 0 | 9372 | 1.42 | 20.23 | 9295.82 | -442.47 | -779.88 | -442.47 | 0.56 |  |  | 22 |  | 800 |  | 27.86 | 4600 | 4400 | 200 | 225 | 280 | 245 | 220
12/19/2020 | 01:20 | 01:38 | 0.3 | 9375 | 9441 | 66 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 220 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 01:43 | 02:24 | 0.68333 | 9441 | 9469 | 28 | Slide | 0 | 9466 | 0.94 | 105.07 | 9389.81 | -441.57 | -778.73 | -441.57 | 1.73 |  |  | 25 |  | 800 |  | 40.98 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 02:24 | 02:39 | 0.25 | 9469 | 9536 | 67 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 268 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 02:42 | 03:02 | 0.33333 | 9536 | 9630 | 94 | Rotate |  | 9561 | 0.55 | 123.32 | 9484.8 | -442.03 | -777.6 | -442.03 | 0.48 |  |  | 42 | 80 | 800 | 22000 | 282 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 03:05 | 03:25 | 0.33333 | 9630 | 9723 | 93 | Rotate |  | 9654 | 0.14 | 63.27 | 9577.8 | -442.22 | -777.12 | -442.22 | 0.53 |  |  | 42 | 80 | 800 | 22000 | 279 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 03:32 | 04:48 | 1.2667 | 9723 | 9783 | 60 | Slide | 0 | 9748 | 2.98 | 314.08 | 9671.76 | -440.47 | -778.78 | -440.47 | 3.22 |  |  | 22 |  | 800 |  | 54.55 | 4700 | 4400 | 300 | 225 | 280 | 245 | 220
12/19/2020 | 04:48 | 04:50 | 0.033333 | 9783 | 9817 | 34 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 1020 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 04:55 | 05:14 | 0.31667 | 9817 | 9881 | 64 | Rotate |  | 9842 | 5.54 | 320.77 | 9765.49 | -435.25 | -783.4 | -435.25 | 2.77 |  |  | 42 | 80 | 800 | 22000 | 202.11 | 5200 | 4400 | 800 | 225 | 280 | 245 | 220
12/19/2020 | 05:14 | 07:09 | 1.9167 | 9881 | 9911 | 30 | Slide | TTF: 10; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 15.65 | 4700 | 4400 | 300 | 225 | 280 | 245 | 220
12/19/2020 | 07:15 | 09:21 | 2.1 | 9911 | 9940 | 29 | Slide | TTF: 10; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 13.81 | 4700 | 4400 | 300 | 225 | 280 | 245 | 220

## BHA_3_Curve_and_Lateral_Slide_S
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #3 (Curve and Lateral) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7230
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1135
Well Name: |  |  |  |  | Fat Tire A1H |  |  | Survey / Gamma Offset: |  |  |  |  | 70.00 / 57.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 329.63 |  | Rotate: |  | 6095
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/21/2020 | 23:10 | 23:17 | 0.11667 | 9937 | 9942 | 5 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 200; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 42.86 | 1900 | 1600 | 300 | 231 | 215 | 205 | 195
12/21/2020 | 23:20 | 23:25 | 0.083333 | 9942 | 9947 | 5 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 200; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 60 | 2200 | 1600 | 600 | 231 | 215 | 205 | 195
12/22/2020 | 00:20 | 01:40 | 1.3333 | 9947 | 10037 | 90 | Slide | 0 | 9966 | 12.92 | 330.93 | 9888.07 | -420.32 | -793.32 | -420.32 | 7.92 |  |  | 38 |  | 350 |  | 67.5 | 3800 | 3300 | 500 | 231 | 260 | 215 | 170
12/22/2020 | 01:48 | 02:02 | 0.23333 | 10037 | 10055 | 18 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 77.14 | 4500 | 3900 | 600 | 231 | 260 | 215 | 170
12/22/2020 | 02:02 | 02:50 | 0.8 | 10055 | 10133 | 78 | Slide | 0 | 10062 | 23.83 | 331.31 | 9979.03 | -393.85 | -807.89 | -393.85 | 11.37 |  |  | 42 |  | 400 |  | 97.5 | 4400 | 3900 | 500 | 231 | 260 | 215 | 170
12/22/2020 | 03:03 | 03:25 | 0.36667 | 10133 | 10188 | 55 | Rotate |  | 10157 | 30.18 | 330.45 | 10063.63 | -356.2 | -828.9 | -356.2 | 6.7 |  |  | 32 | 30 | 400 | 10000 | 150 | 4700 | 3900 | 800 | 233 | 260 | 215 | 170
12/22/2020 | 03:25 | 03:52 | 0.45 | 10188 | 10228 | 40 | Slide | TTF: 0; Drilling Parameters WOB: 44; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 88.89 | 4500 | 3900 | 600 | 233 | 260 | 215 | 170
12/22/2020 | 03:57 | 04:10 | 0.21667 | 10228 | 10250 | 22 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 101.54 | 4700 | 3900 | 800 | 233 | 260 | 215 | 170
12/22/2020 | 04:10 | 04:56 | 0.76667 | 10250 | 10324 | 74 | Slide | 0 | 10253 | 29.23 | 324.11 | 10147.04 | -316.21 | -854.55 | -316.21 | 3.42 |  |  | 46 |  | 400 |  | 96.52 | 4500 | 3900 | 600 | 233 | 260 | 215 | 170
12/22/2020 | 05:06 | 06:01 | 0.91667 | 10324 | 10419 | 95 | Slide | 0 | 10348 | 40.1 | 328.32 | 10225.07 | -271.24 | -884.31 | -271.24 | 11.71 |  |  | 46 |  | 400 |  | 103.64 | 4500 | 3900 | 600 | 233 | 260 | 215 | 170
12/22/2020 | 06:08 | 06:27 | 0.31667 | 10419 | 10455 | 36 | Rotate |  | 10442 | 48.88 | 329.65 | 10292.06 | -214.81 | -918.16 | -214.81 | 9.39 |  |  | 30 | 30 | 400 | 10000 | 113.68 | 4700 | 3900 | 800 | 233 | 260 | 215 | 170
12/22/2020 | 06:27 | 07:01 | 0.56667 | 10455 | 10513 | 58 | Slide | TTF: 0; Drilling Parameters WOB: 46; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 102.35 | 4500 | 3900 | 600 | 240 | 260 | 215 | 170
12/22/2020 | 07:10 | 07:27 | 0.28333 | 10513 | 10551 | 38 | Rotate |  | 10537 | 53.71 | 328.89 | 10351.45 | -151.11 | -956.05 | -151.11 | 5.12 |  |  | 30 | 30 | 400 | 10000 | 134.12 | 4700 | 3900 | 800 | 240 | 260 | 215 | 170
12/22/2020 | 07:27 | 08:14 | 0.78333 | 10551 | 10608 | 57 | Slide | TTF: 0; Drilling Parameters WOB: 46; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 72.77 | 4500 | 3900 | 600 | 240 | 260 | 215 | 170
12/22/2020 | 08:24 | 09:33 | 1.15 | 10608 | 10703 | 95 | Slide | 0 | 10632 | 63.85 | 330.04 | 10400.63 | -81.21 | -997.23 | -81.21 | 10.72 |  |  | 46 |  | 400 |  | 82.61 | 4500 | 3900 | 600 | 230 | 260 | 215 | 170
12/22/2020 | 09:43 | 10:04 | 0.35 | 10703 | 10755 | 52 | Rotate |  | 10728 | 75.49 | 329.25 | 10433.92 | -3.67 | -1042.67 | -3.67 | 12.15 |  |  | 30 | 30 | 400 | 10000 | 148.57 | 4700 | 3900 | 800 | 230 | 260 | 215 | 170
12/22/2020 | 10:04 | 10:34 | 0.5 | 10755 | 10799 | 44 | Slide | TTF: 0; Drilling Parameters WOB: 46; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 88 | 4500 | 3900 | 600 | 230 | 260 | 215 | 170
12/22/2020 | 10:44 | 11:10 | 0.43333 | 10799 | 10880 | 81 | Rotate |  | 10823 | 82.69 | 328.44 | 10451.89 | 76.1 | -1090.9 | 76.1 | 7.62 |  |  | 30 | 30 | 400 | 10000 | 186.92 | 4700 | 3900 | 800 | 230 | 260 | 215 | 170
12/22/2020 | 11:10 | 11:28 | 0.3 | 10880 | 10894 | 14 | Slide | TTF: 0; Drilling Parameters WOB: 46; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 46.67 | 4500 | 3900 | 600 | 230 | 260 | 215 | 170
12/22/2020 | 11:38 | 12:00 | 0.36667 | 10894 | 10930 | 36 | Rotate |  | 10917 | 80.15 | 329.74 | 10465.91 | 155.83 | -1138.65 | 155.83 | 3.03 |  |  | 30 | 30 | 320 | 12000 | 98.18 | 3400 | 2600 | 800 | 230 | 275 | 220 | 170
12/22/2020 | 12:00 | 12:35 | 0.58333 | 10930 | 10988 | 58 | Slide | TTF: 0; Drilling Parameters WOB: 46; Drilling Parameters FLOW: 320; Drilling Parameters ROP: 99.43 | 3100 | 2600 | 500 | 230 | 275 | 220 | 170
12/22/2020 | 12:45 | 12:50 | 0.083333 | 10988 | 10998 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 320; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 120 | 3400 | 2600 | 800 | 230 | 275 | 220 | 170
12/22/2020 | 12:50 | 13:07 | 0.28333 | 10998 | 11015 | 17 | Slide | 0 | 11013 | 93.68 | 331.4 | 10471.07 | 239.13 | -1185.63 | 239.13 | 14.2 |  |  | 46 |  | 320 |  | 60 | 3100 | 2600 | 500 | 230 | 275 | 220 | 170
12/22/2020 | 13:07 | 13:32 | 0.41667 | 11015 | 11084 | 69 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 320; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 165.6 | 3400 | 2600 | 800 | 230 | 275 | 220 | 170
12/22/2020 | 13:40 | 14:10 | 0.5 | 11084 | 11179 | 95 | Rotate |  | 11108 | 94.58 | 331.52 | 10464.23 | 322.37 | -1230.9 | 322.37 | 0.96 |  |  | 40 | 80 | 320 | 16000 | 190 | 3400 | 2600 | 800 | 237 | 275 | 220 | 170
12/22/2020 | 14:20 | 14:23 | 0.05 | 11179 | 11189 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 320; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 200 | 3400 | 2600 | 800 | 237 | 275 | 220 | 170
12/22/2020 | 14:23 | 14:38 | 0.25 | 11189 | 11207 | 18 | Slide | 0 | 11202 | 92.43 | 330.14 | 10458.48 | 404.29 | -1276.63 | 404.29 | 2.72 |  |  | 50 |  | 320 |  | 72 | 3200 | 2600 | 600 | 237 | 275 | 220 | 170
12/22/2020 | 14:38 | 14:59 | 0.35 | 11207 | 11273 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 320; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 188.57 | 3400 | 2600 | 800 | 237 | 275 | 220 | 170
12/22/2020 | 15:10 | 15:30 | 0.33333 | 11273 | 11367 | 94 | Rotate |  | 11296 | 91.89 | 329.65 | 10454.94 | 485.55 | -1323.74 | 485.55 | 0.78 |  |  | 40 | 80 | 320 | 16000 | 282 | 3400 | 2600 | 800 | 237 | 275 | 220 | 170
12/22/2020 | 15:59 | 16:21 | 0.36667 | 11367 | 11463 | 96 | Rotate |  | 11392 | 92 | 329.99 | 10451.68 | 568.49 | -1371.98 | 568.49 | 0.37 |  |  | 40 | 80 | 320 | 16000 | 261.82 | 3600 | 2600 | 1000 | 237 | 275 | 220 | 170
12/22/2020 | 16:28 | 16:48 | 0.33333 | 11463 | 11557 | 94 | Rotate |  | 11486 | 92.48 | 330.14 | 10448 | 649.89 | -1418.85 | 649.89 | 0.53 |  |  | 40 | 80 | 320 | 16000 | 282 | 3600 | 2600 | 1000 | 237 | 275 | 220 | 170
12/22/2020 | 16:56 | 16:59 | 0.05 | 11557 | 11567 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 320; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 200 | 3600 | 2600 | 1000 | 237 | 275 | 220 | 170
12/22/2020 | 16:59 | 17:08 | 0.15 | 11567 | 11577 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 320; Drilling Parameters ROP: 66.67 | 3200 | 2600 | 600 | 237 | 275 | 220 | 170
12/22/2020 | 17:08 | 17:32 | 0.4 | 11577 | 11651 | 74 | Rotate |  | 11580 | 90.32 | 330.12 | 10445.71 | 731.37 | -1465.65 | 731.37 | 2.3 |  |  | 40 | 80 | 320 | 16000 | 185 | 3600 | 2600 | 1000 | 237 | 275 | 220 | 170
12/22/2020 | 17:35 | 18:00 | 0.41667 | 11651 | 11745 | 94 | Rotate |  | 11674 | 88.95 | 329.88 | 10446.31 | 812.77 | -1512.64 | 812.77 | 1.48 |  |  | 40 | 80 | 320 | 16000 | 225.6 | 3600 | 2600 | 1000 | 237 | 275 | 220 | 170
12/22/2020 | 18:05 | 18:10 | 0.083333 | 11745 | 11750 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 320; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 60 | 3600 | 2600 | 1000 | 233 | 300 | 220 | 160
12/22/2020 | 18:10 | 19:00 | 0.83333 | 11750 | 11774 | 24 | Slide | 0 | 11769 | 91.69 | 330.16 | 10445.78 | 895.05 | -1560.11 | 895.05 | 2.9 |  |  | 42 |  | 300 |  | 28.8 | 2800 | 2400 | 400 | 233 | 300 | 220 | 160
12/22/2020 | 19:55 | 20:20 | 0.41667 | 11774 | 11840 | 66 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 158.4 | 3600 | 2400 | 1200 | 235 | 300 | 220 | 160
12/22/2020 | 20:25 | 20:45 | 0.33333 | 11840 | 11935 | 95 | Rotate |  | 11864 | 93.66 | 329.16 | 10441.34 | 976.95 | -1608.04 | 976.95 | 2.33 |  |  | 42 | 80 | 300 | 16000 | 285 | 3600 | 2400 | 1200 | 235 | 300 | 220 | 160
12/22/2020 | 21:00 | 21:25 | 0.41667 | 11935 | 11947 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 55; Drilling Parameters FLOW: 300; Drilling Parameters ROP: 28.8 | 2800 | 2400 | 400 | 235 | 300 | 220 | 160
12/22/2020 | 21:25 | 22:18 | 0.88333 | 11947 | 12030 | 83 | Rotate |  | 11959 | 94.05 | 328.31 | 10434.96 | 1057.97 | -1657.23 | 1057.97 | 0.98 |  |  | 42 | 80 | 300 | 16000 | 93.96 | 3600 | 2400 | 1200 | 235 | 300 | 220 | 160
12/22/2020 | 22:25 | 23:15 | 0.83333 | 12030 | 12036 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 7.2 | 3050 | 2800 | 250 | 235 | 300 | 220 | 160
12/22/2020 | 23:35 | 24:00 | 0.41667 | 12036 | 12123 | 87 | Rotate |  | 12053 | 93.47 | 327.84 | 10428.79 | 1137.58 | -1706.84 | 1137.58 | 0.79 |  |  | 42 | 80 | 330 | 16000 | 208.8 | 4000 | 2800 | 1200 | 235 | 300 | 220 | 160
12/23/2020 | 02:10 | 02:40 | 0.5 | 12123 | 12220 | 97 | Rotate |  | 12149 | 92.13 | 327.1 | 10424.1 | 1218.42 | -1758.4 | 1218.42 | 1.59 |  |  | 42 | 80 | 330 | 16000 | 194 | 4000 | 2800 | 1200 | 242 | 300 | 220 | 160
12/23/2020 | 02:45 | 03:10 | 0.41667 | 12220 | 12238 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 43.2 | 3050 | 2800 | 250 | 248 | 300 | 220 | 160
12/23/2020 | 03:10 | 03:38 | 0.46667 | 12238 | 12316 | 78 | Rotate |  | 12245 | 94.73 | 328.84 | 10418.36 | 1299.64 | -1809.21 | 1299.64 | 3.26 |  |  | 42 | 80 | 330 | 16000 | 167.14 | 4000 | 2800 | 1200 | 255 | 300 | 220 | 160
12/23/2020 | 03:42 | 04:05 | 0.38333 | 12316 | 12412 | 96 | Rotate |  | 12341 | 96.59 | 329.4 | 10408.89 | 1381.63 | -1858.24 | 1381.63 | 2.02 |  |  | 42 | 80 | 330 | 16000 | 250.43 | 4000 | 2800 | 1200 | 255 | 300 | 220 | 160
12/23/2020 | 04:12 | 04:55 | 0.71667 | 12412 | 12434 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 30.7 | 3200 | 2800 | 400 | 255 | 300 | 220 | 160
12/23/2020 | 04:55 | 05:18 | 0.38333 | 12434 | 12507 | 73 | Rotate |  | 12436 | 93.64 | 331.33 | 10400.42 | 1463.86 | -1905.02 | 1463.86 | 3.71 |  |  | 42 | 80 | 330 | 16000 | 190.43 | 4000 | 2800 | 1200 | 257 | 300 | 220 | 160
12/23/2020 | 05:23 | 05:48 | 0.41667 | 12507 | 12602 | 95 | Rotate |  | 12531 | 93.64 | 331.53 | 10394.39 | 1547.13 | -1950.36 | 1547.13 | 0.21 |  |  | 42 | 80 | 330 | 16000 | 228 | 4000 | 2800 | 1200 | 265 | 300 | 220 | 160
12/23/2020 | 05:54 | 06:15 | 0.35 | 12602 | 12698 | 96 | Rotate |  | 12627 | 94.84 | 332.2 | 10387.29 | 1631.55 | -1995.51 | 1631.55 | 1.43 |  |  | 42 | 80 | 330 | 16000 | 274.29 | 4000 | 2800 | 1200 | 265 | 300 | 220 | 160
12/23/2020 | 06:23 | 06:32 | 0.15 | 12698 | 12708 | 10 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 66.67 | 4000 | 2800 | 1200 | 265 | 300 | 220 | 160
12/23/2020 | 06:32 | 07:07 | 0.58333 | 12708 | 12728 | 20 | Slide | 0 | 12723 | 93.83 | 331.99 | 10380.04 | 1716.14 | -2040.31 | 1716.14 | 1.07 |  |  | 55 |  | 330 |  | 34.29 | 3100 | 2800 | 300 | 265 | 300 | 220 | 160
12/23/2020 | 07:07 | 07:26 | 0.31667 | 12728 | 12794 | 66 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 208.42 | 4000 | 2800 | 1200 | 265 | 300 | 220 | 160
12/23/2020 | 07:33 | 07:55 | 0.36667 | 12794 | 12889 | 95 | Rotate |  | 12818 | 92.87 | 330.81 | 10374.48 | 1799.41 | -2085.7 | 1799.41 | 1.6 |  |  | 42 | 80 | 330 | 16000 | 259.09 | 4000 | 2800 | 1200 | 265 | 300 | 220 | 160
12/23/2020 | 08:03 | 08:23 | 0.33333 | 12889 | 12983 | 94 | Rotate |  | 12912 | 93.5 | 331.07 | 10369.26 | 1881.45 | -2131.29 | 1881.45 | 0.72 |  |  | 42 | 80 | 330 | 16000 | 282 | 4000 | 2800 | 1200 | 265 | 300 | 220 | 160
12/23/2020 | 08:31 | 08:53 | 0.36667 | 12983 | 13077 | 94 | Rotate |  | 13006 | 94.18 | 331.31 | 10362.97 | 1963.62 | -2176.49 | 1963.62 | 0.77 |  |  | 42 | 80 | 330 | 16000 | 256.36 | 4000 | 2800 | 1200 | 275 | 300 | 220 | 160
12/23/2020 | 09:00 | 09:26 | 0.43333 | 13077 | 13173 | 96 | Rotate |  | 13102 | 95.29 | 331.96 | 10355.04 | 2047.81 | -2221.94 | 2047.81 | 1.34 |  |  | 42 | 80 | 330 | 16000 | 221.54 | 4000 | 2800 | 1200 | 275 | 300 | 220 | 160
12/23/2020 | 09:33 | 09:40 | 0.11667 | 13173 | 13183 | 10 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 85.71 | 4000 | 2800 | 1200 | 275 | 300 | 220 | 160
12/23/2020 | 09:40 | 10:37 | 0.95 | 13183 | 13213 | 30 | Slide | 0 | 13196 | 93.6 | 330.55 | 10347.76 | 2129.97 | -2267.01 | 2129.97 | 2.34 |  |  | 55 |  | 330 |  | 31.58 | 3100 | 2800 | 300 | 275 | 300 | 220 | 160
12/23/2020 | 10:37 | 10:52 | 0.25 | 13213 | 13267 | 54 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 216 | 4000 | 2800 | 1200 | 275 | 300 | 220 | 160
12/23/2020 | 12:02 | 12:07 | 0.083333 | 13267 | 13277 | 10 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 120 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 12:07 | 12:24 | 0.28333 | 13277 | 13292 | 15 | Slide | 0 | 13291 | 93.53 | 329.24 | 10341.85 | 2212 | -2314.57 | 2212 | 1.38 |  |  | 55 |  | 330 |  | 52.94 | 3100 | 2800 | 300 | 280 | 300 | 220 | 160
12/23/2020 | 12:24 | 12:46 | 0.36667 | 13292 | 13362 | 70 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 190.91 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 12:53 | 13:07 | 0.23333 | 13362 | 13424 | 62 | Rotate |  | 13387 | 93.93 | 328.84 | 10335.6 | 2294.14 | -2363.85 | 2294.14 | 0.59 |  |  | 42 | 80 | 330 | 16000 | 265.71 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 13:19 | 13:28 | 0.15 | 13424 | 13458 | 34 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 226.67 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 13:36 | 13:59 | 0.38333 | 13458 | 13552 | 94 | Rotate |  | 13481 | 92.96 | 327.65 | 10329.96 | 2373.93 | -2413.23 | 2373.93 | 1.63 |  |  | 42 | 80 | 330 | 16000 | 245.22 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 14:07 | 14:10 | 0.05 | 13552 | 13562 | 10 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 200 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 14:10 | 14:43 | 0.55 | 13562 | 13574 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 55; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 21.82 | 3100 | 2800 | 300 | 280 | 300 | 220 | 160
12/23/2020 | 14:43 | 15:07 | 0.4 | 13574 | 13648 | 74 | Rotate |  | 13577 | 95.04 | 328.33 | 10323.26 | 2455.13 | -2463.99 | 2455.13 | 2.28 |  |  | 42 | 80 | 330 | 16000 | 185 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 15:12 | 15:46 | 0.56667 | 13648 | 13742 | 94 | Rotate |  | 13671 | 95.99 | 328.52 | 10314.23 | 2534.84 | -2512.98 | 2534.84 | 1.03 |  |  | 42 | 80 | 330 | 16000 | 165.88 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 16:00 | 16:50 | 0.83333 | 13742 | 13762 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 55; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 24 | 3100 | 2800 | 300 | 280 | 300 | 220 | 160
12/23/2020 | 16:50 | 17:14 | 0.4 | 13762 | 13836 | 74 | Rotate |  | 13765 | 92.84 | 329.05 | 10306.99 | 2614.98 | -2561.54 | 2614.98 | 3.4 |  |  | 42 | 80 | 330 | 16000 | 185 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 17:22 | 17:45 | 0.38333 | 13836 | 13930 | 94 | Rotate |  | 13859 | 93.85 | 328.91 | 10301.51 | 2695.4 | -2609.9 | 2695.4 | 1.08 |  |  | 42 | 80 | 330 | 16000 | 245.22 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 17:48 | 18:15 | 0.45 | 13930 | 14025 | 95 | Rotate |  | 13954 | 94.66 | 329.49 | 10294.46 | 2776.77 | -2658.41 | 2776.77 | 1.05 |  |  | 42 | 80 | 330 | 16000 | 211.11 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 18:20 | 18:25 | 0.083333 | 14025 | 14031 | 6 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 72 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 18:25 | 19:08 | 0.71667 | 14031 | 14047 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 58; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 22.33 | 3000 | 2800 | 200 | 280 | 300 | 220 | 160
12/23/2020 | 19:08 | 19:27 | 0.31667 | 14047 | 14119 | 72 | Rotate |  | 14048 | 92.3 | 327.35 | 10288.75 | 2856.69 | -2707.54 | 2856.69 | 3.39 |  |  | 42 | 80 | 330 | 16000 | 227.37 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 19:32 | 20:04 | 0.53333 | 14119 | 14213 | 94 | Rotate |  | 14142 | 93.5 | 326.74 | 10283.99 | 2935.47 | -2758.61 | 2935.47 | 1.43 |  |  | 42 | 80 | 330 | 16000 | 176.25 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 20:15 | 20:20 | 0.083333 | 14213 | 14220 | 7 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 84 | 4000 | 2800 | 1200 | 280 | 300 | 220 | 160
12/23/2020 | 20:20 | 20:40 | 0.33333 | 14220 | 14232 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 62; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 36 | 3800 | 3500 | 300 | 285 | 320 | 220 | 160
12/23/2020 | 20:40 | 21:05 | 0.41667 | 14232 | 14308 | 76 | Rotate |  | 14237 | 90.2 | 326.82 | 10280.93 | 3014.89 | -2810.62 | 3014.89 | 3.47 |  |  | 42 | 80 | 330 | 16000 | 182.4 | 4000 | 2800 | 1200 | 285 | 320 | 220 | 160
12/23/2020 | 21:10 | 21:35 | 0.41667 | 14308 | 14402 | 94 | Rotate |  | 14331 | 89.39 | 326.62 | 10281.26 | 3093.47 | -2862.2 | 3093.47 | 0.89 |  |  | 42 | 80 | 330 | 16000 | 225.6 | 4000 | 2800 | 1200 | 285 | 320 | 220 | 160
12/23/2020 | 21:40 | 22:32 | 0.86667 | 14402 | 14427 | 25 | Slide | 0 | 14425 | 93.02 | 327.76 | 10279.29 | 3172.44 | -2913.12 | 3172.44 | 4.05 |  |  | 65 |  | 375 |  | 28.85 | 3700 | 3300 | 400 | 285 | 330 | 220 | 160
12/23/2020 | 22:32 | 22:55 | 0.38333 | 14427 | 14496 | 69 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 180 | 4000 | 2800 | 1200 | 286 | 330 | 220 | 160
12/23/2020 | 23:02 | 23:06 | 0.066667 | 14496 | 14507 | 11 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 165 | 4000 | 2800 | 1200 | 286 | 330 | 220 | 160
12/23/2020 | 23:06 | 23:30 | 0.4 | 14507 | 14517 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 25 | 3700 | 3300 | 400 | 290 | 330 | 220 | 160
12/23/2020 | 23:30 | 23:55 | 0.41667 | 14517 | 14591 | 74 | Rotate |  | 14520 | 93.9 | 329.1 | 10273.55 | 3253.23 | -2962.76 | 3253.23 | 1.69 |  |  | 42 | 80 | 330 | 22000 | 177.6 | 4000 | 2800 | 1200 | 290 | 330 | 220 | 160
12/24/2020 | 00:00 | 00:35 | 0.58333 | 14591 | 14684 | 93 | Rotate |  | 14613 | 94.63 | 328.9 | 10266.64 | 3332.73 | -3010.53 | 3332.73 | 0.81 |  |  | 42 | 80 | 330 | 22000 | 159.43 | 4100 | 2900 | 1200 | 291 | 330 | 220 | 160
12/24/2020 | 00:40 | 01:08 | 0.46667 | 14684 | 14779 | 95 | Rotate |  | 14708 | 95.83 | 328.81 | 10257.98 | 3413.7 | -3059.45 | 3413.7 | 1.27 |  |  | 42 | 80 | 330 | 22000 | 203.57 | 4100 | 2900 | 1200 | 291 | 330 | 220 | 160
12/24/2020 | 01:12 | 01:22 | 0.16667 | 14779 | 14788 | 9 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 54 | 4100 | 2900 | 1200 | 291 | 330 | 220 | 160
12/24/2020 | 01:22 | 02:00 | 0.63333 | 14788 | 14804 | 16 | Slide | 0 | 14803 | 94.26 | 330.5 | 10249.62 | 3495.36 | -3107.26 | 3495.36 | 2.42 |  |  | 68 |  | 375 |  | 25.26 | 3700 | 3300 | 400 | 291 | 330 | 220 | 160
12/24/2020 | 02:00 | 02:35 | 0.58333 | 14804 | 14874 | 70 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 4100 | 2900 | 1200 | 291 | 330 | 220 | 160
12/24/2020 | 02:40 | 02:57 | 0.28333 | 14874 | 14884 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 35.29 | 3700 | 3300 | 400 | 294 | 330 | 220 | 160
12/24/2020 | 02:57 | 03:25 | 0.46667 | 14884 | 14968 | 84 | Rotate |  | 14897 | 90.71 | 329.33 | 10245.55 | 3576.6 | -3154.33 | 3576.6 | 3.98 |  |  | 42 | 80 | 330 | 22000 | 180 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 03:30 | 04:00 | 0.5 | 14968 | 15064 | 96 | Rotate |  | 14993 | 90.06 | 329.27 | 10244.9 | 3659.15 | -3203.34 | 3659.15 | 0.68 |  |  | 42 | 80 | 330 | 22000 | 192 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 04:05 | 04:35 | 0.5 | 15064 | 15159 | 95 | Rotate |  | 15088 | 89.15 | 329.46 | 10245.56 | 3740.89 | -3251.75 | 3740.89 | 0.98 |  |  | 42 | 80 | 330 | 22000 | 190 | 4100 | 2900 | 1200 | 296 | 330 | 220 | 160
12/24/2020 | 04:40 | 06:08 | 1.4667 | 15159 | 15181 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 15 | 3700 | 3300 | 400 | 294 | 330 | 220 | 160
12/24/2020 | 06:08 | 06:36 | 0.46667 | 15181 | 15254 | 73 | Rotate |  | 15183 | 90.3 | 330.62 | 10246.01 | 3823.19 | -3299.19 | 3823.19 | 1.72 |  |  | 42 | 80 | 330 | 22000 | 156.43 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 07:07 | 08:15 | 1.1333 | 15254 | 15279 | 25 | Slide | 0 | 15277 | 93.53 | 330.85 | 10242.87 | 3905.13 | -3345.11 | 3905.13 | 3.44 |  |  | 68 |  | 375 |  | 22.06 | 3700 | 3300 | 400 | 294 | 330 | 220 | 160
12/24/2020 | 08:15 | 08:45 | 0.5 | 15279 | 15348 | 69 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 138 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 08:55 | 09:27 | 0.53333 | 15348 | 15444 | 96 | Rotate |  | 15373 | 94.05 | 331 | 10236.53 | 3988.85 | -3391.66 | 3988.85 | 0.56 |  |  | 42 | 80 | 330 | 22000 | 180 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 09:37 | 10:15 | 0.63333 | 15444 | 15539 | 95 | Rotate |  | 15468 | 95.12 | 331.72 | 10228.93 | 4071.96 | -3437.04 | 4071.96 | 1.36 |  |  | 42 | 80 | 330 | 22000 | 150 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 10:25 | 10:59 | 0.56667 | 15539 | 15635 | 96 | Rotate |  | 15564 | 96.57 | 331.7 | 10219.16 | 4156.05 | -3482.3 | 4156.05 | 1.51 |  |  | 42 | 80 | 330 | 22000 | 169.41 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 11:21 | 12:40 | 1.3167 | 15635 | 15657 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 16.71 | 3700 | 3300 | 400 | 294 | 330 | 220 | 160
12/24/2020 | 12:40 | 13:13 | 0.55 | 15657 | 15730 | 73 | Rotate |  | 15659 | 94.71 | 329.92 | 10209.82 | 4238.58 | -3528.41 | 4238.58 | 2.7 |  |  | 42 | 80 | 330 | 22000 | 132.73 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 13:29 | 13:58 | 0.48333 | 15730 | 15825 | 95 | Rotate |  | 15754 | 94.89 | 329.46 | 10201.87 | 4320.3 | -3576.18 | 4320.3 | 0.52 |  |  | 42 | 80 | 330 | 22000 | 196.55 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 14:12 | 15:39 | 1.45 | 15825 | 15843 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 70; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 12.41 | 3700 | 3300 | 400 | 294 | 330 | 220 | 160
12/24/2020 | 15:39 | 16:12 | 0.55 | 15843 | 15920 | 77 | Rotate |  | 15849 | 92.94 | 329.02 | 10195.39 | 4401.74 | -3624.66 | 4401.74 | 2.1 |  |  | 42 | 80 | 330 | 22000 | 140 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 16:29 | 17:00 | 0.51667 | 15920 | 16015 | 95 | Rotate |  | 15944 | 92.75 | 329.17 | 10190.67 | 4483.16 | -3673.39 | 4483.16 | 0.25 |  |  | 42 | 80 | 330 | 22000 | 183.87 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 17:45 | 18:40 | 0.91667 | 16015 | 16110 | 95 | Rotate |  | 16039 | 93.21 | 329.49 | 10185.73 | 4564.76 | -3721.78 | 4564.76 | 0.59 |  |  | 35 | 80 | 330 | 22000 | 103.64 | 4100 | 2900 | 1200 | 294 | 330 | 220 | 160
12/24/2020 | 22:00 | 22:50 | 0.83333 | 16110 | 16122 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 380; Drilling Parameters ROP: 14.4 | 3750 | 3500 | 250 | 295 | 330 | 220 | 160
12/24/2020 | 22:50 | 23:40 | 0.83333 | 16122 | 16204 | 82 | Rotate |  | 16133 | 91.56 | 331.41 | 10181.82 | 4646.45 | -3768.1 | 4646.45 | 2.69 |  |  | 35 | 80 | 380 | 22000 | 98.4 | 4700 | 3500 | 1200 | 295 | 330 | 220 | 160
12/24/2020 | 23:50 | 24:00 | 0.16667 | 16204 | 16234 | 30 | Rotate |  | 16227 | 91.72 | 330.76 | 10179.13 | 4728.7 | -3813.53 | 4728.7 | 0.71 |  |  | 35 | 80 | 400 | 22000 | 180 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 00:00 | 00:23 | 0.38333 | 16234 | 16298 | 64 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 166.96 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 00:29 | 01:05 | 0.6 | 16298 | 16392 | 94 | Rotate |  | 16321 | 91.93 | 331.33 | 10176.14 | 4810.91 | -3859.01 | 4810.91 | 0.65 |  |  | 35 | 80 | 400 | 22000 | 156.67 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 01:10 | 01:43 | 0.55 | 16392 | 16487 | 95 | Rotate |  | 16416 | 92.13 | 331.85 | 10172.77 | 4894.41 | -3904.18 | 4894.41 | 0.59 |  |  | 38 | 80 | 400 | 22000 | 172.73 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 01:52 | 02:00 | 0.13333 | 16487 | 16490 | 3 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 22.5 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 02:00 | 02:20 | 0.33333 | 16490 | 16498 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 24 | 4100 | 3900 | 200 | 295 | 330 | 220 | 160
12/25/2020 | 02:20 | 02:50 | 0.5 | 16498 | 16582 | 84 | Rotate |  | 16511 | 92.52 | 331.9 | 10168.92 | 4978.13 | -3948.93 | 4978.13 | 0.41 |  |  | 35 | 80 | 400 | 22000 | 168 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 02:55 | 03:32 | 0.61667 | 16582 | 16676 | 94 | Rotate |  | 16605 | 92.3 | 331.58 | 10164.96 | 5060.85 | -3993.4 | 5060.85 | 0.41 |  |  | 35 | 80 | 400 | 22000 | 152.43 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 03:38 | 03:48 | 0.16667 | 16676 | 16678 | 2 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 12 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 03:48 | 04:45 | 0.95 | 16678 | 16690 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 80; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 12.63 | 4000 | 3900 | 100 | 293 | 330 | 220 | 160
12/25/2020 | 04:45 | 05:39 | 0.9 | 16690 | 16771 | 81 | Rotate |  | 16700 | 93.79 | 331.69 | 10159.92 | 5144.32 | -4038.46 | 5144.32 | 1.57 |  |  | 80 | 80 | 400 | 22000 | 90 | 4950 | 3900 | 1050 | 295 | 330 | 220 | 160
12/25/2020 | 05:53 | 06:34 | 0.68333 | 16771 | 16865 | 94 | Rotate |  | 16794 | 94.2 | 331.04 | 10153.37 | 5226.62 | -4083.4 | 5226.62 | 0.82 |  |  | 80 | 80 | 400 | 22000 | 137.56 | 4950 | 3900 | 1050 | 304 | 330 | 220 | 160
12/25/2020 | 06:42 | 07:30 | 0.8 | 16865 | 16960 | 95 | Rotate |  | 16889 | 94.94 | 331.32 | 10145.8 | 5309.59 | -4129.05 | 5309.59 | 0.83 |  |  | 80 | 80 | 400 | 22000 | 118.75 | 4950 | 3900 | 1050 | 304 | 330 | 220 | 160
12/25/2020 | 07:40 | 08:25 | 0.75 | 16960 | 17055 | 95 | Rotate |  | 16984 | 95.01 | 331.06 | 10137.56 | 5392.52 | -4174.66 | 5392.52 | 0.28 |  |  | 80 | 80 | 400 | 23000 | 126.67 | 4950 | 3900 | 1050 | 304 | 330 | 220 | 160
12/25/2020 | 08:40 | 09:25 | 0.75 | 17055 | 17149 | 94 | Rotate |  | 17078 | 95.82 | 331.72 | 10128.69 | 5474.67 | -4219.47 | 5474.67 | 1.11 |  |  | 80 | 80 | 400 | 23000 | 125.33 | 4950 | 3900 | 1050 | 304 | 330 | 220 | 160
12/25/2020 | 09:45 | 10:00 | 0.25 | 17149 | 17167 | 18 | Rotate | Drilling Parameters WOB: 80; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 72 | 4950 | 3900 | 1050 | 304 | 330 | 220 | 160