## Summary
Magnolia Oil & Gas / Fat Tire B1H ST01 / LTX1150720 / Patterson 248
Report Date: | 01/05/2021 | Current Depth: | 16840
Start Date: | 12/12/2020 | Casing Depth: | 0
Daily Cost: | 7250 | Distance to TD:
Well Cost: | 126350 | Average ROP: | 0
Drilling Hours: | 46.77 | Svy MD: | 16840
24Hr Forcast: |  | Svy Inc: | 89.6
Current BHA: | BHA #5 (Lateral) | Svy Azi: | 327.8
Current BRT Hrs: | 80 | Svy TVD: | 10261.54
Bit Make / Model: | Halliburton / GTD64M | Svy NS: | 3779
POOH in last 24Hrs: | Yes | Svy EW: | -4647.64
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | WBM | Svy Left/Right: | 0
Directional Driller Day: | Nathan Marks | MWD Day: | Russell Arnold
Directional Driller Night: | Billy McFarland | MWD Night: | Jeff Campbell
RSS Engineer 1: |  | Third Man:
RSS Engineer 2: |  | Fourth Man:
Principal Plan: |  | Max BHT Well: | 240
24Hr Summary: |  | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
PPM250020 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  | In Hole |  | 58.15 | 58.15
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
ZSB500016 | UBHO Sub |  |  | In Hole |  | 58.15 | 58.15
ZSB500025 | UBHO Sub |  |  | Dirty |  | 45.00 | 45.00
ZSB500043 | UBHO |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | County: |  | Fayette |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Total Drilled (Usft): |  | 18589 |  |  | Total Days: |  | 14
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 105 | 3080 | 2975 |  | 705.53 |  | 11.76 | 4.22 | 5.38 | 10.5
2 | 2 | 9.875 | 3080 | 10192 | 7112 |  | 275.13 |  | 10.55 | 25.85 | 40.32 | 57
3 | 3 | 6.75 | 10192 | 10209 | 17 |  | 34 |  | 41.18 | 0.5 | 6.45 | 22
4 | 4 | 6.75 | 10209 | 14949 | 4740 |  | 141.07 |  | 19.37 | 33.6 | 38.55 | 80.17
5 | 5 | 6.75 | 13095 | 16840 | 3745 |  | 80.08 |  | 10.63 | 46.77 | 58.15 | 80
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | New |  | 0-0-NO-I-TD |  | 1.353 | 2975 | 4.2167 | 705.53
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 0-1-CT-G-X-I-NO-TD |  | 1.491 | 7112 | 25.85 | 275.13
3 | Halliburton |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 17 | 0.5 | 34
4 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 4740 | 33.6 | 141.07
5 | Halliburton |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 3745 | 46.7667 | 80.08
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 1.5 | 5.45 | 2975 |  | 705.53
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 2 | 5.81 | 7112 |  | 275.13
3 | PDCI |  | 6/7 11.7 |  | 6/7 | 11.70 | 5 | 2.12 | 4.01 | 17 |  | 34
4 | PDCI |  | 6/7 11.7 |  | 6/7 | 11.70 | 5 | 2.12 | 4.01 | 4740 |  | 141.07
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5 | 2.12 | 4 | 3745 |  | 80.08
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Nathan Marks |  | Billy McFarland |  | Russell Arnold |  | Jeff Campbell |  | James Dyer |  | Jim
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 1.00 / 0.29 |  | 2975 |  | 703.31 |  |  |  | 1 |  | 4.23
INT: INTERMEDIATE |  |  | 4.00 / 1.37 |  | 7112 |  | 275.45 |  | 0.00 / 18.00 |  | 1 |  | 25.82
CRV: CURVE |  |  | 2.09 / 1.47 |  | 952 |  | 102.92 |  | 0.00 / 7.33 |  | 2 |  | 9.25
LAT: LATERAL |  |  | 2.92 / 1.89 |  | 3805 |  | 153.18 |  | 3.02 / 0.00 |  | 1 |  | 24.84
LAT2: LATERAL 2 |  |  | 2.52 / 2.05 |  | 3710 |  | 94.14 |  | 0.37 / 0.00 |  | 1 |  | 39.41
ST: SIDETRACK |  |  | 0.93 / 3.23 |  | 35 |  | 4.76 |  |  |  | 1 |  | 7.36
Total |  |  | 13.44 |  | 18589 |  | 167.6 |  | 3.39 / 25.33 |  | 5 |  | 110.91
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA #1 (Surface) |  |  | 105.00 | 3080.00 | 872.09 | 2625.00 | 286.89 | 350.00 | 11.76 | 2975.00 | 703.31 | 4.23 | 1.22
INT: INTERMEDIATE-BHA #2 (Intermediate) |  |  | 3080.00 | 10192.00 | 392.96 | 6362.00 | 77.88 | 750.00 | 10.55 | 7112.00 | 275.45 | 25.82 | 9.63
CRV: CURVE-BHA #3 (Curve and Lateral) |  |  | 10192.00 | 10209.00 | 125.00 | 10.00 | 16.67 | 7.00 | 41.18 | 17.00 | 34.00 | 0.50 | 0.42
CRV: CURVE-BHA #4 (Curve and Lateral) |  |  | 10209.00 | 11144.00 | 116.72 | 356.00 | 101.58 | 579.00 | 61.93 | 935.00 | 106.86 | 8.75 | 5.70
LAT: LATERAL-BHA #4 (Curve and Lateral) |  |  | 11144.00 | 14949.00 | 205.94 | 3466.00 | 42.32 | 339.00 | 8.91 | 3805.00 | 153.18 | 24.84 | 8.01
LAT2: LATERAL 2-BHA #5 (Lateral) |  |  | 13130.00 | 16840.00 | 158.40 | 3347.00 | 19.86 | 363.00 | 9.78 | 3710.00 | 94.14 | 39.41 | 18.28
ST: SIDETRACK-BHA #5 (Lateral) |  |  | 13095.00 | 16840.00 | 0.00 | 0.00 | 4.76 | 35.00 | 100.00 | 35.00 | 4.76 | 7.36 | 7.36
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1150720 | Total Drilled(Usft) | 18589.00
Operator | Magnolia Oil & Gas | Drilling Hours | 110.93
Well Name | Fat Tire B1H ST01 | Avg ROP(Usft/hr) | 167.57
Rig | Patterson 248 | Rotary Drilled(Usft) | 16166.00
State | Texas | Rotary Hours | 60.28
County | Fayette | Rotary ROP(Usft/hr) | 268.17
Formation | Austin Chalk | Rotary % | 86.97
Start Date | 12/12/2020 | Slide Drilled(Usft) | 2423.00
End Date | 01/05/2021 | Slide Hours | 50.65
Days On Well | 14 | Slide ROP(Usft/hr) | 47.84
Start Depth (Usft) | 105.00 | Slide % | 13.03
End Depth (Usft) | 16840.00
Total Drilled (Usft) | 18589.00
# BHA's | 5
# Motor Failures | 1
# MWD Failures | 0
NPT hrs (Rig/Dir) | 3.90 / 25.33
Phase Data
Phase | SUR | INT | CRV | LAT | ST | LAT2
Start Date | 12/12/2020 | 12/13/2020 | 12/28/2020 | 12/30/2020 | 01/02/2021 | 01/02/2021
End Date | 12/12/2020 | 12/16/2020 | 12/30/2020 | 01/01/2021 | 01/05/2021 | 01/04/2021
Total Days | 1.00 | 4.00 | 2.09 | 2.91 | 0.92 | 2.51
Start Depth (Usft) | 105.00 | 3080.00 | 10192.00 | 11144.00 | 13095.00 | 13130.00
End Depth (Usft) | 3080.00 | 10192.00 | 11144.00 | 14949.00 | 16840.00 | 16840.00
Total Drilled(Usft) | 2975.00 | 7112.00 | 952.00 | 3805.00 | 35.00 | 3710.00
Drilling Hours | 4.22 | 25.85 | 9.27 | 24.83 | 7.37 | 39.40
Circulating Hours | 1.17 | 14.47 | 8.73 | 2.17 | 1.83 | 9.55
Total D&C Hours | 5.38 | 40.32 | 18.00 | 27.00 | 9.20 | 48.95
Avg ROP(Usft/hr) | 705.53 | 275.13 | 102.73 | 153.22 | 4.75 | 94.16
Rotary Drilled(Usft) | 2625.00 | 6362.00 | 366.00 | 3466.00 | 0.00 | 3347.00
Rotary Hours | 2.98 | 16.22 | 3.13 | 16.82 | 0.00 | 21.13
Rotary ROP(Usft/hr) | 879.89 | 392.31 | 116.81 | 206.11 | 0.00 | 158.38
Rotary % | 88.24 | 89.45 | 38.45 | 91.09 | 0.00 | 90.22
Slide Drilled(Usft) | 350.00 | 750.00 | 586.00 | 339.00 | 35.00 | 363.00
Slide Hours | 1.23 | 9.63 | 6.13 | 8.02 | 7.37 | 18.27
Slide ROP(Usft/hr) | 283.78 | 77.85 | 95.54 | 42.29 | 4.75 | 19.87
Slide % | 11.76 | 10.55 | 61.55 | 8.91 | 100.00 | 9.78
# BHA | 1 | 1 | 2 | 1 | 1 | 1
# Motor Failures | 0 | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 0.00 / 18.00 | 0.00 / 7.33 | 3.02 / 0.00 | 0.00 / 0.00 | 0.88 / 0.00
Total Phase Hrs | 7.00 | 32.78 | 35.25 | 45.25 | 77.50 | 49.18
Phase ROP (Usft/hr) | 425.00 | 216.94 | 27.01 | 84.09 | 0.45 | 75.43
Avg Motor Yield (°/100ft) | 5.45 | 10.73 | 16.84 | 16.71 | 12.25 | 11.21
Avg Rotary DLS (°/100ft) | 0.72 | 0.81 | 2.85 | 1.81 | 1.79 | 1.79
Avg Rotary TF | -155.16 | -165.26 | 82.74 | -102.53 | -42.19 | -42.19
Avg Slide Length (Usft) | 29.17 | 26.79 | 53.27 | 16.14 | 14.74 | 14.78
# Slides | 12 | 28 | 11 | 21 | 19 | 18
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5
Description | BHA #1 (Surface) | BHA #2 (Intermediate) | BHA #3 (Curve and Lateral) | BHA #4 (Curve and Lateral) | BHA #5 (Lateral)
Bit Size | 13.500 | 9.875 | 6.750 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Halliburton / GTD64M | Security / GTD64M | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491 | 1.491
Grade In | New | New | New | New | New
Grade Out | 0-0-NO-I-TD | 0-1-CT-G-X-I-NO-TD
Motor SN | PPM800004 | PPM800049 | PPM250025 | PPM250025 | PPM250020
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 11.7 | PDCI / 6/7 11.7 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.90 | 7/8 / 5.90 | 6/7 / 11.70 | 6/7 / 11.70 | 6/7 / 8.80
WOB (klbs) | 2.00 / 19.10 / 30.00 | 16.00 / 34.17 / 45.00 | 10.00 / 27.50 / 45.00 | 28.00 / 42.40 / 72.00 | 10.00 / 41.10 / 80.00
Diff P (psi) | 50.00 / 535.17 / 800.00 | 200.00 / 613.71 / 900.00 | 200.00 / 300.00 / 400.00 | 250.00 / 956.08 / 1200.00 | 100.00 / 667.81 / 900.00
Bend | 1.500 | 2.000 | 2.120 | 2.120 | 2.120
Date In | 12/12/2020 | 12/13/2020 | 12/28/2020 | 12/29/2020 | 01/02/2021
Date Out | 12/12/2020 | 12/16/2020 | 12/29/2020 | 01/01/2021 | 01/05/2021
Time In | 07:00 | 21:00 | 08:40 | 07:20 | 02:30
Time Out | 17:30 | 06:00 | 06:40 | 15:30 | 10:30
BRT Hrs | 10.50 | 57.00 | 22.00 | 80.17 | 80.00
Start Depth (Usft) | 105.00 | 3080.00 | 10192.00 | 10209.00 | 13095.00
End Depth (Usft) | 3080.00 | 10192.00 | 10209.00 | 14949.00 | 16840.00
Total Drilled(Usft) | 2975.00 | 7112.00 | 17.00 | 4740.00 | 3745.00
Drilling Hours | 4.22 | 25.85 | 0.50 | 33.60 | 46.77
Circulating Hours | 1.17 | 14.47 | 5.95 | 4.95 | 11.38
Total D&C Hours | 5.38 | 40.32 | 6.45 | 38.55 | 58.15
Avg ROP(Usft/hr) | 705.53 | 275.13 | 34.00 | 141.07 | 80.08
Rotary Drilled(Usft) | 2625.00 | 6362.00 | 10.00 | 3822.00 | 3347.00
Rotary Hours | 2.98 | 16.22 | 0.08 | 19.87 | 21.13
Rotary ROP(Usft/hr) | 879.89 | 392.31 | 120.00 | 192.38 | 158.38
Rotary % | 88.24 | 89.45 | 58.82 | 80.63 | 89.37
Slide Drilled(Usft) | 350.00 | 750.00 | 7.00 | 918.00 | 398.00
Slide Hours | 1.23 | 9.63 | 0.42 | 13.73 | 25.63
Slide ROP(Usft/hr) | 283.78 | 77.85 | 16.80 | 66.84 | 15.53
Slide % | 11.76 | 10.55 | 41.18 | 19.37 | 10.63
Motor Failure | NO | NO | NO | YES | NO
MWD Failure | NO | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | YES | NO
LIH | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 5.45 | 10.73 | 0.00 | 16.50 | 11.96
Avg Rotary DLS (°/100ft) | 0.72 | 0.81 | 0.00 | 1.87 | 1.26
Avg Rotary TF | -155.16 | -165.26 | 0.00 | -104.09 | -28.28
Avg Slide Length (Usft) | 29.17 | 26.79 | 7.00 | 29.61 | 19.90
# Slides | 12 | 28 | 1 | 31 | 20

## Personnel Report
|  | Job # | LTX1150720 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-149-33514 |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Fat Tire B1H ST01
|  | Date: | 01/05/2021 |  | State: |  | Texas
[5 empty] | County: |  | Fayette
Fat Tire B1H ST01 - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Billy McFarland | Night DD |  | 12/12/2020 - 00:00 | 12/16/2020 - 00:00 |  | 5.00 / 0.00
Billy McFarland | Night DD |  | 12/28/2020 - 00:00 | 01/05/2021 - 00:00 |  | 9.00 / 0.00
Jeff Campbell | Night MWD |  | 12/12/2020 - 00:00 | 12/16/2020 - 00:00 |  | 5.00 / 0.00
Jeff Campbell | Night MWD |  | 12/28/2020 - 00:00 | 01/05/2021 - 00:00 |  | 9.00 / 0.00
Nathan Marks | Day DD |  | 12/12/2020 - 00:00 | 12/16/2020 - 00:00 |  | 5.00 / 0.00
Nathan Marks | Day DD |  | 12/28/2020 - 00:00 | 01/05/2021 - 00:00 |  | 9.00 / 0.00
Russell Arnold | Day MWD |  | 12/12/2020 - 00:00 | 12/16/2020 - 00:00 |  | 5.00 / 0.00
Russell Arnold | Day MWD |  | 12/28/2020 - 00:00 | 01/05/2021 - 00:00 |  | 9.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1150720 | [5 empty] | State / County: |  |  |  | Texas / Fayette
|  |  |  | Well Name: |  |  | Fat Tire B1H ST01 | [7 empty] | Day DD: |  |  |  |  | Nathan Marks | [5 empty] | API #: |  |  |  | 42-149-33514
|  |  |  | AFE #: |  |  | 20DD0326MG | [7 empty] | Night DD: |  |  |  |  | Billy McFarland | [5 empty] | Company Man: |  |  |  | James Dyer
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Russell Arnold | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Jeff Campbell | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 12/12/2020 | 12/13/2020 | 12/14/2020 | 12/15/2020 | 12/16/2020 | 12/17/2020 | 12/18/2020 | 12/19/2020 | 12/20/2020 | 12/21/2020 | 12/22/2020 | 12/23/2020 | 12/24/2020 | 12/25/2020 | 12/26/2020 | 12/27/2020 | 12/28/2020 | 12/29/2020 | 12/30/2020 | 12/31/2020 | 01/01/2021 | 01/02/2021 | 01/03/2021 | 01/04/2021 | 01/05/2021 | 01/06/2021 | 01/07/2021 | 01/08/2021 | 01/09/2021 | 01/10/2021 | 01/11/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | 6 3/4- Halliburton GTD64M- Jetted 6-18s |  | Steel | 13509568 | 4 | 8 | [17 empty] | X | X | X | X | O | O | O | O
Bit |  | 6.75 | 6 3/4- Halliburton GTD64M- Jetted 6-18s |  | Steel | 13522001 | 4 | 5 | [20 empty] | O | X | X | X | X
Cross Over |  | 5.375 | X/O- DS42B x XT39P |  | Steel | SD119105 | 0 | 9 | [7 empty] | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.5 | X/O- DS42B x XT39P |  | Steel | SD119310 | 9 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X
Cross Over |  | 5 | X/O- DS42B x XT39P |  | Steel | SD119318 | 0 | 10 | [15 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5 | X/O- DS42B x XT39P |  | Steel | SD119319 | 0 | 10 | [15 empty] | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.125 | UBHO Sub |  | Steel | ZSB500016 | 4 | 25 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
MWD / LWD |  | 5.188 | UBHO Sub |  | Steel | ZSB500025 | 5 | 21 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X
MWD / LWD |  | 5 | UBHO |  | Steel | ZSB500043 | 0 | 5 | [20 empty] | O | O | O | O | O
Motor |  | 5 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 |  | Steel | PPM250022 | 0 | 16 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 5 1/2, - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  | Steel | PPM250025 | 5 | 14 | [7 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X
Motor |  | 5 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  | Steel | PPM250020 | 4 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Motor |  | 5 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HT89 +.012 |  | Steel | PPM250001 | 0 | 14 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  |  | 5 1/2, - 7/8, 3.8 Stg. @ 2.50? Slick- HPW -.004 |  | Steel | MTR475035 | 0 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.002 |  | Steel | PPM250021 | 0 | 10 | [15 empty] | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.000 |  | Steel | PPM250018 | 0 | 5 | [20 empty] | O | O | O | O | O
Collar |  | 5 | 5 NMDC |  | Non-Mag | SD55955 | 0 | 9 | [7 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5 NMDC |  | Non-Mag | SD56281 | 9 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X
Collar |  |  | 5 NMDC |  | Non-Mag | SD56700 | 0 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5.063 | 5 NMDC |  | Non-Mag | SD56701 | 0 | 9 | [7 empty] | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5 NMDC |  | Non-Mag | SD56783 | 9 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X
Collar |  |  | 5 NMDC |  | Non-Mag | SD56785 | 0 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5.063 | 5 NMPDC |  | Steel | SD56679 | 0 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5 NMPDC |  | Steel | SD56870 | 9 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X
Collar |  | 5 | 5 NMDC |  | Non-Mag | SD56777 | 0 | 10 | [15 empty] | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | 5 NMDC |  | Non-Mag | SD56782 | 0 | 10 | [15 empty] | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 27 Stands of Drill Pipe |  | Steel | Rig2 | 0 | 17 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Cougar Thruster |  | Steel | DS-MT3X-500-033 | 9 | 10 | [15 empty] | O | X | X | X | X | X | X | X | X | X
Accelerator |  | 5 | Cougar Thruster |  | Steel | MT3X-500-032 | 0 | 5 | [20 empty] | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD115658 | 0 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119067 | 0 | 18 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI Valve |  | Steel | Rig1x | 9 | 17 | [8 empty] | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X
Sub |  | 5.938 | BTI Valve |  | Steel | 10063 | 0 | 5 | [20 empty] | O | O | O | O | O
Agitator |  | 5.25 | DWS Agitator |  | Steel | PG525-0015 | 0 | 17 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator |  | 5.25 | DWS Agitator |  | Steel | PG525-0020 | 9 | 10 | [15 empty] | O | X | X | X | X | X | X | X | X | X
Agitator |  | 5.25 | DWS Agitator |  | Steel | PG525-0008 | 0 | 5 | [20 empty] | O | O | O | O | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Nathan Marks |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Billy McFarland |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Russell Arnold |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jeff Campbell |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Fat Tire B1H ST01
|  | County: |  | Fayette |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0326MG |  |  | PO #: |  | ProDirectional
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
PPM250022 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.003 | 5 | 28.91 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 12/10/2020 |  | 12/27/2020
PPM250025 | 5 1/2, - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 | 5 | 33.13 |  | XT 39 / 3 1/2 Reg | Dirty / Failed |  | 12/19/2020 |  | 01/01/2021
PPM250020 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 | 5 | 30.99 |  | XT 39 / 3 1/2 Reg | In Hole |  | 12/19/2020
PPM250001 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HT89 +.012 | 5 |  |  | XT 39 / 3 1/2 Reg | Clean |  | 12/19/2020 |  | 01/01/2021
MTR475035 | 5 1/2, - 7/8, 3.8 Stg. @ 2.50? Slick- HPW -.004 |  |  |  | XT 39 / 3 1/2 Reg | Clean |  | 12/19/2020 |  | 01/05/2021
SD55955 | 5 NMDC | 5 | 30.43 |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 12/27/2020
SD56281 | 5 NMDC | 5 | 30.61 |  | XT 39 / XT 39 | In Hole |  | 12/19/2020
SD56700 | 5 NMDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
SD56701 | 5 NMDC | 5.063 | 29.89 |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 12/27/2020
SD56783 | 5 NMDC | 5 | 31.16 |  | XT 39 / XT 39 | In Hole |  | 12/19/2020
SD56785 | 5 NMDC |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
SD56679 | 5 NMPDC | 5.063 | 9.46 |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
SD56870 | 5 NMPDC | 5 | 10.12 |  | XT 39 / XT 39 | In Hole |  | 12/19/2020
SD115658 | Float Sub |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
SD119067 | Float Sub |  |  |  | XT 39 / XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
SD119105 | X/O- DS42B x XT39P | 5.375 | 3.08 |  | DS42 / XT 39 | Clean |  | 12/19/2020 |  | 12/27/2020
SD119310 | X/O- DS42B x XT39P | 5.5 | 3.31 |  | DS42 / XT 39 | In Hole |  | 12/19/2020
GT551232 | Lift Sub- Gator Technologies |  |  |  | XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
GT551251 | Lift Sub- Gator Technologies |  |  |  | XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
SDLC3354 | Lift Cap |  |  |  | XT 39 | Clean |  | 12/19/2020 |  | 01/05/2021
Rig1x | BTI Valve | 4.875 | 2.37 |  | XT39 / XT39 | In Hole |  | 12/20/2020
PG525-0015 | DWS Agitator | 5.25 | 23.51 |  | DS42 / DS42 | Clean |  | 12/20/2020
Rig2 | 27 Stands of Drill Pipe | 4.5 | 2556.59 |  | DS42 / DS42 | In Hole |  | 12/20/2020
DS-MT3X-500-033 | Cougar Thruster | 5 | 26.38 |  | XT39 / XT39 | In Hole |  | 12/27/2020
PG525-0020 | DWS Agitator | 5.25 | 23.86 |  | DS42 / DS42 | In Hole |  | 12/27/2020
ZSB500016 | UBHO Sub | 5.125 | 2.49 |  | XT 39 / XT 39 | In Hole |  | 12/10/2020
ZSB500025 | UBHO Sub | 5.188 | 3.68 |  | XT 39 / XT 39 | Dirty |  | 12/10/2020 |  | 01/01/2021
SD56777 | 5 NMDC | 5 |  |  | XT39 / XT39 | Clean |  | 12/27/2020 |  | 01/05/2021
SD56782 | 5 NMDC | 5 |  |  | XT39 / XT39 | Clean |  | 12/27/2020 |  | 01/05/2021
SD119318 | X/O- DS42B x XT39P | 5 |  |  | DS42 / XT39 | Clean |  | 12/27/2020 |  | 01/05/2021
SD119319 | X/O- DS42B x XT39P | 5 |  |  | DS42 / XT39 | Clean |  | 12/27/2020 |  | 01/05/2021
PPM250021 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.002 | 5 |  |  | XT39 / 3 1/2 Reg | Clean |  | 12/27/2020 |  | 01/05/2021
13509568 | 6 3/4- Halliburton GTD64M- Jetted 6-18s | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty / Failed |  | 12/29/2020
13522001 | 6 3/4- Halliburton GTD64M- Jetted 6-18s | 6.75 | 0.75 |  | 3 1/2 Reg | In Hole |  | 01/01/2021
MT3X-500-032 | Cougar Thruster | 5 | 26.44 |  | XT39 / XT39 | Clean |  | 01/01/2021
PG525-0008 | DWS Agitator | 5.25 | 22.77 |  | DS42 / DS42 | Clean |  | 01/01/2021
10063 | BTI Valve | 5.938 | 2.31 |  | XT39 / XT39 | Clean |  | 01/01/2021
PPM250018 | 5 1/2, - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.000 | 5 |  |  | XT39 / 3 1/2 Reg | Clean |  | 01/01/2021 |  | 01/05/2021
ZSB500043 | UBHO | 5 |  |  | XT39 / XT39 | Clean |  | 01/01/2021 |  | 01/05/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Fat Tire B1H ST01
|  | County: |  | Fayette |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
13 1/2"- Ulterra - U616S - Jetted - 9x14s | 47245 | 12/12/2020 | 01/05/2021 | 25 |  | 1 |  | 1.17 | 4.22 | 10.5
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | PPM800004 | 12/12/2020 | 01/05/2021 | 25 |  | 1 |  | 1.17 | 4.22 | 10.5
13" - 4 Blade Nortrak Stabilizer (BFF) | SD603913 | 12/12/2020 | 01/05/2021 | 25 |  | 1 |  | 1.17 | 4.22 | 10.5
8" - NMPDC | SD52214 | 12/12/2020 | 01/05/2021 | 25 | 3 | 1 ,2 |  | 15.63 | 30.07 | 67.5
UBHO Sub | ZSB775202 | 12/12/2020 | 01/05/2021 | 25 | 3 | 1 ,2 |  | 15.63 | 30.07 | 67.5
8" - NMDC | SD50132 | 12/12/2020 | 01/05/2021 | 25 | 3 | 1 ,2 |  | 15.63 | 30.07 | 67.5
8" - NMDC | SD55923 | 12/12/2020 | 01/05/2021 | 25 | 3 | 1 ,2 |  | 15.63 | 30.07 | 67.5
X/O- 4 1/2 IFB x 6 5/8 RegP | SD116862 | 12/12/2020 | 01/05/2021 | 25 |  | 1 |  | 1.17 | 4.22 | 10.5
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s | 54300 | 12/12/2020 | 01/05/2021 | 25 | 2 | 2 |  | 14.47 | 25.85 | 57
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 | PPM800049 | 12/12/2020 | 01/05/2021 | 25 | 2 | 2 |  | 14.47 | 25.85 | 57
X/O- 4 1/2 XHB x 6 5/8 RegP | SD108685 | 12/12/2020 | 01/05/2021 | 25 | 2 | 2 |  | 14.47 | 25.85 | 57
2 Stands of 6 1/2" Drill Collars | Rig-3 | 12/12/2020 | 01/05/2021 | 25 | 2 | 2 |  | 14.47 | 25.85 | 57
X/O- 4 1/2 IFB x 4 1/2 XHP | SD4555 | 12/12/2020 | 01/05/2021 | 25 | 2 | 2 |  | 14.47 | 25.85 | 57
NOV- Safety Join / Agitator / Shock Sub | AGHF0675-0062 | 12/12/2020 | 01/05/2021 | 25 | 2 | 2 |  | 14.47 | 25.85 | 57
6 3/4"- Halliburton GTD64M- Jetted 6-18s | 13522000 | 12/12/2020 | 01/05/2021 | 25 | 1 | 3 |  | 5.95 | 0.5 | 22
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 | PPM250025 | 12/19/2020 | 01/01/2021 | 14 | 4 | 3 ,4 |  | 10.9 | 34.1 | 102.17
BTI Valve | Rig1x | 12/20/2020 | 01/05/2021 | 17 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
5" NMPDC | SD56870 | 12/19/2020 | 01/05/2021 | 18 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
UBHO Sub | ZSB500025 | 12/10/2020 | 01/01/2021 | 23 | 4 | 3 ,4 |  | 10.9 | 34.1 | 102.17
5" NMDC | SD56281 | 12/19/2020 | 01/05/2021 | 18 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
5" NMDC | SD56783 | 12/19/2020 | 01/05/2021 | 18 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
Cougar Thruster | DS-MT3X-500-033 | 12/27/2020 | 01/05/2021 | 10 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
X/O- DS42B x XT39P | SD119310 | 12/19/2020 | 01/05/2021 | 18 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
DWS Agitator | PG525-0020 | 12/27/2020 | 01/05/2021 | 10 | 8 | 3 ,4 ,5 |  | 22.28 | 80.87 | 182.17
6 3/4"- Halliburton GTD64M- Jetted 6-18s | 13509568 | 12/29/2020 | 01/05/2021 | 8 | 3 | 4 |  | 4.95 | 33.6 | 80.17
6 3/4"- Halliburton GTD64M- Jetted 6-18s | 13522001 | 01/01/2021 | 01/05/2021 | 5 | 3 | 5 |  | 11.38 | 46.77 | 80
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 | PPM250020 | 12/19/2020 | 01/05/2021 | 18 | 3 | 5 |  | 11.38 | 46.77 | 80
UBHO Sub | ZSB500016 | 12/10/2020 | 01/05/2021 | 27 | 3 | 5 |  | 11.38 | 46.77 | 80
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Fayette County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well
Facility |  |  | Fat Tire - Fayette County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Fat Tire B1H ST01 |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Fat Tire B1H ST01
Field: |  |  | Fayette County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas South Central 4204
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 441.00 Usft
Map Northing |  |  | 816982.02 US survey foot |  |  | Map Easting |  |  | 2668460.01 US survey foot
Latitude |  |  | 30° 3' 49.16451" N |  |  | Longitude |  |  | 96° 53' 12.44787" W
Grid Convergence |  |  | 1.035
Facility: |  |  | Fat Tire - Fayette County, TX
Map Northing |  |  | 840692.37 US survey foot |  |  | Map Easting |  |  | 2700895.02 US survey foot
Latitude |  |  | 30° 7' 37.89563" N |  |  | Longitude |  |  | 96° 46' 58.28564" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.086
Well: |  |  | Fat Tire B1H ST01
Local North |  |  | -13.34 Usft |  |  | Local East |  |  | -7.79 Usft
Map Northing |  |  | 840677.35 US survey foot |  |  | Map Easting |  |  | 2700881.83 US survey foot
Latitude |  |  | 30° 7' 37.76506" N |  |  | Longitude |  |  | 96° 46' 58.37719" W
Depth Datum |  |  | Well |  |  | Datum Elevation |  |  | 441.00 Usft
GL Elevation |  |  | 413.00 Usft
Grid Convergence |  |  | 1.086
Well bore: |  |  | Fat Tire B1H ST01
Magnetic Model |  |  | User defined |  |  | Date |  |  | 25/12/2020
Total Field (nT) |  |  | 46590.8 |  |  | Dip Angle (°) |  |  | 58.783
Declination (°) |  |  | 2.883
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 328.33
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Fat Tire B1H ST01
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3006 |  |  | Fat Tire B1H S1 |  |  | MWD+HDGM
3006 |  |  | 10123 |  |  | Fat Tire B1H S2 |  |  | MWD+HDGM
10123 |  |  | 16840 |  |  | Fat Tire B1H S3 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -441 | 840677.35 | 2700881.83 | 30.1272 | -96.7829 | 0
138 | 0.63 | 337.95 | 138 | 0.7 | -0.28 | 0.75 | 0.46 | 0.46 | 15.98 | 337.95 | 138 | -303 | 840678.05 | 2700881.55 | 30.1272 | -96.7829 | 337.95
229 | 0.31 | 324.62 | 228.99 | 1.37 | -0.62 | 1.49 | 0.37 | -0.35 | -14.65 | -167.72 | 91 | -212.01 | 840678.72 | 2700881.21 | 30.1272 | -96.7829 | 335.78
320 | 0.45 | 239.48 | 319.99 | 1.39 | -1.07 | 1.74 | 0.58 | 0.15 | -93.56 | -121.23 | 91 | -121.01 | 840678.74 | 2700880.76 | 30.1272 | -96.7829 | 322.46
415 | 0.68 | 204.67 | 414.99 | 0.69 | -1.62 | 1.43 | 0.42 | 0.24 | -36.64 | -74.41 | 95 | -26.01 | 840678.04 | 2700880.21 | 30.1272 | -96.7829 | 292.9
510 | 0.82 | 216.67 | 509.98 | -0.37 | -2.26 | 0.87 | 0.22 | 0.15 | 12.63 | 54.39 | 95 | 68.98 | 840676.98 | 2700879.57 | 30.1272 | -96.7829 | 260.66
604 | 2.02 | 213.51 | 603.95 | -2.29 | -3.58 | -0.07 | 1.28 | 1.28 | -3.36 | -5.31 | 94 | 162.95 | 840675.06 | 2700878.25 | 30.1271 | -96.7829 | 237.36
699 | 3.05 | 217.55 | 698.86 | -5.69 | -6.04 | -1.67 | 1.1 | 1.08 | 4.25 | 11.86 | 95 | 257.86 | 840671.66 | 2700875.79 | 30.1271 | -96.7829 | 226.71
793 | 4.56 | 214.46 | 792.65 | -10.76 | -9.68 | -4.07 | 1.62 | 1.61 | -3.29 | -9.28 | 94 | 351.65 | 840666.59 | 2700872.15 | 30.1271 | -96.7829 | 221.99
887 | 5.68 | 216.2 | 886.27 | -17.59 | -14.54 | -7.34 | 1.2 | 1.19 | 1.85 | 8.76 | 94 | 445.27 | 840659.76 | 2700867.29 | 30.1271 | -96.7829 | 219.58
982 | 7.76 | 221.43 | 980.61 | -26.2 | -21.57 | -10.97 | 2.28 | 2.19 | 5.51 | 19 | 95 | 539.61 | 840651.15 | 2700860.26 | 30.1271 | -96.783 | 219.46
1075 | 10.05 | 223.01 | 1072.49 | -36.84 | -31.26 | -14.94 | 2.48 | 2.46 | 1.7 | 6.88 | 93 | 631.49 | 840640.51 | 2700850.57 | 30.1271 | -96.783 | 220.31
1169 | 12.66 | 222.8 | 1164.64 | -50.4 | -43.85 | -19.87 | 2.78 | 2.78 | -0.22 | -1.01 | 94 | 723.64 | 840626.95 | 2700837.98 | 30.127 | -96.783 | 221.03
1263 | 14.44 | 223.01 | 1256.02 | -66.53 | -58.85 | -25.72 | 1.89 | 1.89 | 0.22 | 1.69 | 94 | 815.02 | 840610.82 | 2700822.98 | 30.127 | -96.7831 | 221.5
1356 | 15 | 221.25 | 1345.96 | -84.05 | -74.69 | -32.32 | 0.77 | 0.6 | -1.89 | -39.46 | 93 | 904.96 | 840593.3 | 2700807.14 | 30.1269 | -96.7831 | 221.63
1450 | 16.38 | 218.32 | 1436.46 | -103.6 | -90.93 | -40.43 | 1.69 | 1.47 | -3.12 | -31.28 | 94 | 995.46 | 840573.75 | 2700790.9 | 30.1269 | -96.7832 | 221.27
1544 | 16.85 | 219.29 | 1526.54 | -124.54 | -107.78 | -49.41 | 0.58 | 0.5 | 1.03 | 31.01 | 94 | 1085.54 | 840552.81 | 2700774.05 | 30.1268 | -96.7832 | 220.87
1638 | 15.88 | 218.67 | 1616.73 | -145.13 | -124.44 | -58.18 | 1.05 | -1.03 | -0.66 | -170.09 | 94 | 1175.73 | 840532.22 | 2700757.39 | 30.1268 | -96.7833 | 220.61
1731 | 15.19 | 220.33 | 1706.33 | -164.35 | -140.28 | -66.23 | 0.88 | -0.74 | 1.78 | 148 | 93 | 1265.33 | 840513 | 2700741.55 | 30.1267 | -96.7834 | 220.48
1826 | 15.49 | 219.13 | 1797.95 | -183.68 | -156.34 | -74.24 | 0.46 | 0.32 | -1.26 | -47.2 | 95 | 1356.95 | 840493.67 | 2700725.49 | 30.1267 | -96.7834 | 220.4
1920 | 15.93 | 216.98 | 1888.43 | -203.72 | -172.02 | -83.07 | 0.78 | 0.47 | -2.29 | -53.96 | 94 | 1447.43 | 840473.63 | 2700709.81 | 30.1266 | -96.7835 | 220.18
2013 | 15.41 | 219.32 | 1977.98 | -223.48 | -187.53 | -91.74 | 0.88 | -0.56 | 2.52 | 130.57 | 93 | 1536.98 | 840453.87 | 2700694.3 | 30.1265 | -96.7835 | 220
2108 | 14.91 | 218.37 | 2069.67 | -242.82 | -203.11 | -100.02 | 0.59 | -0.53 | -1 | -154.04 | 95 | 1628.67 | 840434.53 | 2700678.72 | 30.1265 | -96.7836 | 219.91
2203 | 14.68 | 215.42 | 2161.52 | -262.21 | -217.67 | -108.88 | 0.83 | -0.24 | -3.11 | -108.4 | 95 | 1720.52 | 840415.14 | 2700664.16 | 30.1264 | -96.7836 | 219.7
2297 | 14.7 | 216.61 | 2252.45 | -281.49 | -231.69 | -117.93 | 0.32 | 0.02 | 1.27 | 86.78 | 94 | 1811.45 | 840395.86 | 2700650.14 | 30.1264 | -96.7836 | 219.46
2392 | 15.6 | 217.47 | 2344.15 | -301.31 | -246.65 | -126.94 | 0.98 | 0.95 | 0.91 | 14.44 | 95 | 1903.15 | 840376.04 | 2700635.18 | 30.1263 | -96.7837 | 219.3
2486 | 14.58 | 216.92 | 2434.91 | -320.8 | -261.45 | -135.76 | 1.1 | -1.09 | -0.59 | -172.27 | 94 | 1993.91 | 840356.55 | 2700620.38 | 30.1263 | -96.7837 | 219.18
2580 | 14.81 | 215.53 | 2525.83 | -340.04 | -275.53 | -144.74 | 0.45 | 0.24 | -1.48 | -57.56 | 94 | 2084.83 | 840337.31 | 2700606.3 | 30.1262 | -96.7838 | 219.02
2674 | 14.23 | 214.6 | 2616.83 | -359.32 | -289.08 | -154.04 | 0.66 | -0.62 | -0.99 | -158.55 | 94 | 2175.83 | 840318.03 | 2700592.75 | 30.1262 | -96.7838 | 218.82
2768 | 14.22 | 212.02 | 2707.95 | -378.62 | -301.76 | -163.81 | 0.67 | -0.01 | -2.74 | -92.15 | 94 | 2266.95 | 840298.73 | 2700580.07 | 30.1261 | -96.7839 | 218.55
2862 | 12.96 | 211.41 | 2799.31 | -397.41 | -313.37 | -173.7 | 1.35 | -1.34 | -0.65 | -173.81 | 94 | 2358.31 | 840279.94 | 2700568.46 | 30.1261 | -96.7839 | 218.26
2956 | 12.23 | 209.99 | 2891.05 | -415.03 | -323.84 | -183.2 | 0.84 | -0.78 | -1.51 | -157.71 | 94 | 2450.05 | 840262.32 | 2700557.99 | 30.126 | -96.7839 | 217.96
3006 | 11.87 | 209.5 | 2939.95 | -424.09 | -329.02 | -188.19 | 0.75 | -0.72 | -0.98 | -164.38 | 50 | 2498.95 | 840253.26 | 2700552.81 | 30.126 | -96.784 | 217.81
3174 | 14.6 | 212.59 | 3103.47 | -456.97 | -348.94 | -205.72 | 1.68 | 1.62 | 1.84 | 16.04 | 168 | 2662.47 | 840220.38 | 2700532.89 | 30.1259 | -96.784 | 217.37
3267 | 18.1 | 217.51 | 3192.7 | -478.32 | -364.06 | -215.95 | 4.04 | 3.76 | 5.29 | 23.97 | 93 | 2751.7 | 840199.03 | 2700517.77 | 30.1259 | -96.7841 | 217.28
3361 | 18.2 | 217.93 | 3282.03 | -501.48 | -381.97 | -226.26 | 0.18 | 0.11 | 0.45 | 52.81 | 94 | 2841.03 | 840175.87 | 2700499.86 | 30.1258 | -96.7841 | 217.3
3455 | 18.41 | 216.66 | 3371.27 | -524.96 | -399.86 | -236.85 | 0.48 | 0.22 | -1.35 | -62.84 | 94 | 2930.27 | 840152.39 | 2700481.97 | 30.1257 | -96.7842 | 217.3
3548 | 18.92 | 215.61 | 3459.38 | -549 | -417.4 | -248.1 | 0.66 | 0.55 | -1.13 | -33.88 | 93 | 3018.38 | 840128.35 | 2700464.43 | 30.1257 | -96.7843 | 217.25
3642 | 17.9 | 212.61 | 3548.57 | -573.56 | -434.06 | -260.26 | 1.48 | -1.09 | -3.19 | -138.53 | 94 | 3107.57 | 840103.79 | 2700447.77 | 30.1256 | -96.7843 | 217.12
3736 | 17.53 | 211.35 | 3638.11 | -597.82 | -449.21 | -272.95 | 0.57 | -0.39 | -1.34 | -134.58 | 94 | 3197.11 | 840079.53 | 2700432.62 | 30.1255 | -96.7844 | 216.92
3829 | 15.79 | 215.8 | 3727.21 | -620.05 | -463.9 | -284.15 | 2.32 | -1.87 | 4.78 | 145.87 | 93 | 3286.21 | 840057.3 | 2700417.93 | 30.1255 | -96.7844 | 216.8
3923 | 15 | 215.4 | 3817.84 | -640.34 | -478.43 | -293.79 | 0.85 | -0.84 | -0.43 | -172.54 | 94 | 3376.84 | 840037.01 | 2700403.4 | 30.1254 | -96.7845 | 216.77
4016 | 14.81 | 221.34 | 3907.71 | -659.07 | -493.26 | -301.95 | 1.65 | -0.2 | 6.39 | 99.95 | 93 | 3466.71 | 840018.28 | 2700388.57 | 30.1254 | -96.7845 | 216.81
4110 | 14.43 | 223.48 | 3998.67 | -676.59 | -509.25 | -308.47 | 0.7 | -0.4 | 2.28 | 126.16 | 94 | 3557.67 | 840000.76 | 2700372.58 | 30.1253 | -96.7846 | 216.97
4204 | 14.32 | 222.61 | 4089.73 | -693.65 | -525.18 | -314.62 | 0.26 | -0.12 | -0.93 | -117.41 | 94 | 3648.73 | 839983.7 | 2700356.65 | 30.1253 | -96.7846 | 217.13
4298 | 13.92 | 223.2 | 4180.89 | -710.44 | -540.79 | -320.72 | 0.45 | -0.43 | 0.63 | 160.5 | 94 | 3739.89 | 839966.91 | 2700341.04 | 30.1252 | -96.7847 | 217.28
4392 | 14.87 | 221.99 | 4271.93 | -727.65 | -556.6 | -327.06 | 1.06 | 1.01 | -1.29 | -18.16 | 94 | 3830.93 | 839949.7 | 2700325.23 | 30.1252 | -96.7847 | 217.41
4484 | 15.24 | 222.04 | 4360.78 | -745.4 | -572.59 | -333.78 | 0.4 | 0.4 | 0.05 | 2.03 | 92 | 3919.78 | 839931.95 | 2700309.24 | 30.1251 | -96.7848 | 217.53
4578 | 14.55 | 221.22 | 4451.62 | -763.46 | -588.65 | -340.72 | 0.77 | -0.73 | -0.87 | -163.41 | 94 | 4010.62 | 839913.89 | 2700293.18 | 30.1251 | -96.7848 | 217.63
4673 | 15.55 | 221.82 | 4543.36 | -781.93 | -605 | -347.85 | 1.07 | 1.05 | 0.63 | 9.15 | 95 | 4102.36 | 839895.42 | 2700276.83 | 30.125 | -96.7849 | 217.73
4768 | 16.31 | 220.66 | 4634.71 | -801.54 | -622.19 | -355.51 | 0.87 | 0.8 | -1.22 | -23.29 | 95 | 4193.71 | 839875.81 | 2700259.64 | 30.125 | -96.7849 | 217.82
4862 | 15.24 | 221.43 | 4725.17 | -820.81 | -638.96 | -363.11 | 1.16 | -1.14 | 0.82 | 169.3 | 94 | 4284.17 | 839856.54 | 2700242.87 | 30.1249 | -96.785 | 217.9
4956 | 15.04 | 221.89 | 4815.9 | -839.16 | -655.28 | -370.16 | 0.25 | -0.21 | 0.49 | 149.23 | 94 | 4374.9 | 839838.19 | 2700226.55 | 30.1249 | -96.785 | 217.99
5049 | 14.81 | 220.4 | 4905.77 | -857.19 | -671.04 | -377.23 | 0.48 | -0.25 | -1.6 | -121.65 | 93 | 4464.77 | 839820.16 | 2700210.79 | 30.1248 | -96.7851 | 218.06
5144 | 13.97 | 219.89 | 4997.79 | -875.24 | -686.26 | -384.59 | 0.89 | -0.88 | -0.54 | -171.67 | 95 | 4556.79 | 839802.11 | 2700195.57 | 30.1248 | -96.7851 | 218.1
5238 | 15.06 | 218.26 | 5088.78 | -893.53 | -701.1 | -392.37 | 1.24 | 1.16 | -1.73 | -21.34 | 94 | 4647.78 | 839783.82 | 2700180.73 | 30.1247 | -96.7852 | 218.12
5332 | 15.73 | 218.58 | 5179.41 | -913.08 | -716.61 | -400.87 | 0.72 | 0.71 | 0.34 | 7.38 | 94 | 4738.41 | 839764.27 | 2700165.22 | 30.1247 | -96.7852 | 218.13
5425 | 15.83 | 217.5 | 5268.91 | -933 | -732.19 | -409.64 | 0.33 | 0.11 | -1.16 | -71.72 | 93 | 4827.91 | 839744.35 | 2700149.64 | 30.1246 | -96.7853 | 218.12
5519 | 14.44 | 217.89 | 5359.64 | -952.42 | -747.2 | -418.29 | 1.48 | -1.48 | 0.41 | 176 | 94 | 4918.64 | 839724.93 | 2700134.63 | 30.1246 | -96.7853 | 218.12
5613 | 13.48 | 216.63 | 5450.87 | -970.46 | -760.93 | -426.44 | 1.07 | -1.02 | -1.34 | -163.04 | 94 | 5009.87 | 839706.89 | 2700120.9 | 30.1245 | -96.7854 | 218.1
5706 | 13.77 | 217.84 | 5541.25 | -987.9 | -774.19 | -434.32 | 0.44 | 0.31 | 1.3 | 45.09 | 93 | 5100.25 | 839689.45 | 2700107.64 | 30.1245 | -96.7854 | 218.08
5800 | 16.89 | 218.96 | 5631.89 | -1007.36 | -789.64 | -442.77 | 3.33 | 3.32 | 1.19 | 5.96 | 94 | 5190.89 | 839669.99 | 2700092.19 | 30.1244 | -96.7855 | 218.09
5895 | 17.56 | 220.11 | 5722.63 | -1029.05 | -807.55 | -451.83 | 0.79 | 0.71 | 1.21 | 27.49 | 95 | 5281.63 | 839648.3 | 2700074.28 | 30.1244 | -96.7855 | 218.12
5989 | 17.19 | 220.59 | 5812.34 | -1050.45 | -825.73 | -460.49 | 0.42 | -0.39 | 0.51 | 159.05 | 94 | 5371.34 | 839626.9 | 2700056.1 | 30.1243 | -96.7856 | 218.17
6083 | 15.92 | 221.13 | 5902.44 | -1070.71 | -843.25 | -468.54 | 1.36 | -1.35 | 0.57 | 173.35 | 94 | 5461.44 | 839606.64 | 2700038.58 | 30.1243 | -96.7856 | 218.22
6177 | 16.01 | 216.92 | 5992.82 | -1090.78 | -859.51 | -477.08 | 1.24 | 0.1 | -4.48 | -87.58 | 94 | 5551.82 | 839586.57 | 2700022.32 | 30.1242 | -96.7857 | 218.24
6271 | 17.07 | 215.95 | 6082.93 | -1112.31 | -875.4 | -487.07 | 1.17 | 1.13 | -1.03 | -15.07 | 94 | 5641.93 | 839565.04 | 2700006.43 | 30.1241 | -96.7857 | 218.2
6364 | 16.32 | 215.75 | 6172.01 | -1133.97 | -891.05 | -497.28 | 0.81 | -0.81 | -0.22 | -175.72 | 93 | 5731.01 | 839543.38 | 2699990.78 | 30.1241 | -96.7858 | 218.16
6459 | 15.89 | 216.62 | 6263.28 | -1155.24 | -906.6 | -507.22 | 0.52 | -0.45 | 0.92 | 151.11 | 95 | 5822.28 | 839522.11 | 2699975.23 | 30.124 | -96.7858 | 218.12
6554 | 14.73 | 214.98 | 6354.91 | -1175.57 | -921.29 | -516.81 | 1.3 | -1.22 | -1.73 | -160.32 | 95 | 5913.91 | 839501.78 | 2699960.54 | 30.124 | -96.7859 | 218.09
6647 | 14.37 | 215.12 | 6444.93 | -1194.7 | -934.7 | -526.05 | 0.39 | -0.39 | 0.15 | 174.49 | 93 | 6003.93 | 839482.65 | 2699947.13 | 30.1239 | -96.7859 | 218.04
6739 | 14.03 | 214.98 | 6534.12 | -1213.17 | -947.66 | -534.97 | 0.37 | -0.37 | -0.15 | -174.3 | 92 | 6093.12 | 839464.18 | 2699934.17 | 30.1239 | -96.786 | 217.99
6834 | 14.03 | 214.89 | 6626.28 | -1232.06 | -960.85 | -544.11 | 0.02 | 0 | -0.09 | -90.04 | 95 | 6185.28 | 839445.29 | 2699920.98 | 30.1238 | -96.786 | 217.95
6928 | 12.99 | 215.33 | 6717.68 | -1250.02 | -973.48 | -552.77 | 1.11 | -1.11 | 0.47 | 174.57 | 94 | 6276.68 | 839427.33 | 2699908.35 | 30.1238 | -96.7861 | 217.91
7021 | 12.08 | 215.55 | 6808.46 | -1266.47 | -985.18 | -560.63 | 0.98 | -0.98 | 0.24 | 177.1 | 93 | 6367.46 | 839410.88 | 2699896.65 | 30.1237 | -96.7861 | 217.88
7115 | 13.32 | 218.03 | 6900.16 | -1283 | -997.57 | -568.19 | 1.44 | 1.32 | 2.64 | 24.95 | 94 | 6459.16 | 839394.35 | 2699884.26 | 30.1237 | -96.7861 | 217.87
7209 | 14.47 | 222.35 | 6991.41 | -1300.21 | -1012.16 | -575.18 | 1.65 | 1.22 | 4.6 | 44.16 | 94 | 6550.41 | 839377.14 | 2699869.67 | 30.1236 | -96.7862 | 217.9
7303 | 13.6 | 224.03 | 7082.6 | -1316.83 | -1027.75 | -581.14 | 1.02 | -0.93 | 1.79 | 155.72 | 94 | 6641.6 | 839360.52 | 2699854.08 | 30.1236 | -96.7862 | 217.97
7397 | 14.34 | 218.56 | 7173.83 | -1333.88 | -1042.69 | -587.81 | 1.61 | 0.79 | -5.82 | -63.41 | 94 | 6732.83 | 839343.47 | 2699839.14 | 30.1235 | -96.7863 | 218.01
7491 | 14.31 | 217.63 | 7264.91 | -1352.19 | -1057.04 | -595.86 | 0.25 | -0.03 | -0.99 | -97.88 | 94 | 6823.91 | 839325.16 | 2699824.79 | 30.1235 | -96.7863 | 218.02
7585 | 14.56 | 214.46 | 7355.94 | -1371.13 | -1070.81 | -604.74 | 0.88 | 0.27 | -3.37 | -73.98 | 94 | 6914.94 | 839306.22 | 2699811.02 | 30.1234 | -96.7864 | 217.99
7679 | 13.08 | 216.48 | 7447.22 | -1389.43 | -1083.83 | -613.48 | 1.66 | -1.57 | 2.15 | 162.92 | 94 | 7006.22 | 839287.92 | 2699798 | 30.1234 | -96.7864 | 217.96
7772 | 14.04 | 213.92 | 7537.62 | -1407.25 | -1096.38 | -622.06 | 1.22 | 1.03 | -2.75 | -33.26 | 93 | 7096.62 | 839270.1 | 2699785.45 | 30.1233 | -96.7865 | 217.92
7866 | 13.94 | 213.69 | 7628.84 | -1426.13 | -1109.02 | -631.5 | 0.12 | -0.11 | -0.24 | -151.04 | 94 | 7187.84 | 839251.22 | 2699772.81 | 30.1233 | -96.7865 | 217.87
7960 | 15.53 | 216.78 | 7719.74 | -1445.63 | -1122.84 | -640.84 | 1.89 | 1.69 | 3.29 | 27.8 | 94 | 7278.74 | 839231.72 | 2699758.99 | 30.1232 | -96.7865 | 217.84
8053 | 15.71 | 219.59 | 7809.31 | -1465.31 | -1138.32 | -649.46 | 0.84 | 0.19 | 3.02 | 77.97 | 93 | 7368.31 | 839212.04 | 2699743.51 | 30.1232 | -96.7866 | 217.84
8146 | 14.69 | 219.64 | 7899.05 | -1484.09 | -1153.86 | -657.28 | 1.1 | -1.1 | 0.05 | 179.29 | 93 | 7458.05 | 839193.26 | 2699727.97 | 30.1231 | -96.7866 | 217.86
8241 | 12.76 | 220.99 | 7991.34 | -1501.29 | -1168.43 | -664.27 | 2.06 | -2.03 | 1.42 | 171.23 | 95 | 7550.34 | 839176.06 | 2699713.4 | 30.1231 | -96.7867 | 217.89
8335 | 14.34 | 222.4 | 8082.72 | -1517.72 | -1183.09 | -670.56 | 1.72 | 1.68 | 1.5 | 12.5 | 94 | 7641.72 | 839159.63 | 2699698.74 | 30.123 | -96.7867 | 217.94
8429 | 15.36 | 222.32 | 8173.58 | -1535.52 | -1199.32 | -677.19 | 1.09 | 1.09 | -0.09 | -1.19 | 94 | 7732.58 | 839141.83 | 2699682.51 | 30.123 | -96.7868 | 217.99
8524 | 13.16 | 223.61 | 8265.65 | -1552.66 | -1215.25 | -683.41 | 2.34 | -2.32 | 1.36 | 172.41 | 95 | 7824.65 | 839124.69 | 2699666.58 | 30.1229 | -96.7868 | 218.05
8617 | 14.41 | 228.66 | 8355.97 | -1567.97 | -1231.25 | -688.04 | 1.86 | 1.34 | 5.43 | 46.38 | 93 | 7914.97 | 839109.38 | 2699650.58 | 30.1229 | -96.7869 | 218.14
8711 | 15.34 | 231.02 | 8446.82 | -1583.52 | -1249.69 | -691.59 | 1.18 | 0.99 | 2.51 | 34.23 | 94 | 8005.82 | 839093.83 | 2699632.14 | 30.1229 | -96.7869 | 218.28
8806 | 15.52 | 218.58 | 8538.42 | -1601.36 | -1267.39 | -697.48 | 3.48 | 0.19 | -13.09 | -92.9 | 95 | 8097.42 | 839075.99 | 2699614.44 | 30.1228 | -96.787 | 218.36
8900 | 13.43 | 211.27 | 8629.44 | -1620.53 | -1280.9 | -706.7 | 2.95 | -2.22 | -7.78 | -142.34 | 94 | 8188.44 | 839056.82 | 2699600.93 | 30.1228 | -96.787 | 218.32
8995 | 6.58 | 193.06 | 8722.96 | -1635.28 | -1287.87 | -715.6 | 7.86 | -7.21 | -19.17 | -164 | 95 | 8281.96 | 839042.07 | 2699593.96 | 30.1227 | -96.7871 | 218.22
9089 | 4.59 | 182.53 | 8816.51 | -1644.28 | -1289.25 | -722.54 | 2.37 | -2.12 | -11.2 | -157.93 | 94 | 8375.51 | 839033.07 | 2699592.58 | 30.1227 | -96.7871 | 218.1
9184 | 2.93 | 173.19 | 8911.3 | -1650.49 | -1289.13 | -727.88 | 1.86 | -1.75 | -9.83 | -164.37 | 95 | 8470.3 | 839026.86 | 2699592.7 | 30.1227 | -96.7871 | 217.99
9278 | 1.83 | 135.39 | 9005.23 | -1653.95 | -1287.79 | -731.53 | 1.98 | -1.17 | -40.21 | -142.91 | 94 | 8564.23 | 839023.4 | 2699594.04 | 30.1227 | -96.7871 | 217.9
9371 | 2.27 | 123.2 | 9098.17 | -1656.01 | -1285.21 | -734.64 | 0.66 | 0.47 | -13.11 | -50.94 | 93 | 8657.17 | 839021.34 | 2699596.62 | 30.1227 | -96.7871 | 217.81
9465 | 2.86 | 110.72 | 9192.07 | -1657.86 | -1281.46 | -738.18 | 0.86 | 0.63 | -13.28 | -49.78 | 94 | 8751.07 | 839019.49 | 2699600.37 | 30.1227 | -96.7871 | 217.7
9560 | 3.29 | 103.07 | 9286.94 | -1659.32 | -1276.59 | -741.98 | 0.62 | 0.45 | -8.05 | -47.52 | 95 | 8845.94 | 839018.03 | 2699605.24 | 30.1227 | -96.787 | 217.57
9653 | 1.32 | 129.96 | 9379.86 | -1660.61 | -1273.17 | -744.88 | 2.36 | -2.12 | 28.91 | 164.22 | 93 | 8938.86 | 839016.74 | 2699608.66 | 30.1227 | -96.787 | 217.48
9747 | 1.49 | 268.47 | 9473.85 | -1661.34 | -1273.56 | -745.29 | 2.8 | 0.18 | 147.35 | 157.94 | 94 | 9032.85 | 839016.01 | 2699608.27 | 30.1227 | -96.787 | 217.47
9841 | 2.62 | 280.99 | 9567.78 | -1660.96 | -1276.89 | -743.22 | 1.29 | 1.2 | 13.32 | 28 | 94 | 9126.78 | 839016.39 | 2699604.94 | 30.1227 | -96.787 | 217.55
9936 | 3.32 | 292.9 | 9662.66 | -1659.48 | -1281.55 | -739.51 | 0.98 | 0.74 | 12.54 | 47.45 | 95 | 9221.66 | 839017.87 | 2699600.28 | 30.1227 | -96.7871 | 217.68
10029 | 8.33 | 322.35 | 9755.16 | -1653.09 | -1288.15 | -730.61 | 6.1 | 5.39 | 31.67 | 46.06 | 93 | 9314.16 | 839024.26 | 2699593.68 | 30.1227 | -96.7871 | 217.93
10123 | 11.12 | 328.26 | 9847.81 | -1639.99 | -1297.08 | -714.77 | 3.15 | 2.97 | 6.29 | 22.62 | 94 | 9406.81 | 839037.36 | 2699584.75 | 30.1227 | -96.7871 | 218.34
10270 | 16.37 | 319.94 | 9990.56 | -1612.05 | -1317.89 | -680.07 | 3.81 | 3.57 | -5.66 | -24.72 | 147 | 9549.56 | 839065.3 | 2699563.94 | 30.1228 | -96.7872 | 219.27
10364 | 31.15 | 325.93 | 10076.37 | -1581.6 | -1340.16 | -642.46 | 15.91 | 15.72 | 6.37 | 12.07 | 94 | 9635.37 | 839095.75 | 2699541.67 | 30.1229 | -96.7872 | 220.28
10458 | 31.62 | 328.15 | 10156.62 | -1540.53 | -1366.79 | -593.53 | 1.33 | 0.5 | 2.36 | 68.83 | 94 | 9715.62 | 839136.82 | 2699515.04 | 30.123 | -96.7873 | 221.58
10554 | 35.01 | 328.8 | 10236.83 | -1495.58 | -1394.34 | -540.81 | 3.55 | 3.53 | 0.68 | 6.28 | 96 | 9795.83 | 839181.77 | 2699487.49 | 30.1231 | -96.7874 | 222.99
10649 | 44.92 | 331.49 | 10309.55 | -1442.67 | -1424.54 | -479.91 | 10.59 | 10.43 | 2.83 | 10.94 | 95 | 9868.55 | 839234.68 | 2699457.29 | 30.1233 | -96.7875 | 224.64
10745 | 58.01 | 331.66 | 10369.23 | -1376.76 | -1460.2 | -405.1 | 13.64 | 13.64 | 0.18 | 0.64 | 96 | 9928.23 | 839300.59 | 2699421.63 | 30.1234 | -96.7876 | 226.68
10840 | 68.98 | 330.03 | 10411.57 | -1302.66 | -1501.61 | -320.3 | 11.65 | 11.55 | -1.72 | -7.95 | 95 | 9970.57 | 839374.69 | 2699380.22 | 30.1236 | -96.7877 | 229.06
10934 | 74.06 | 328.73 | 10441.35 | -1225.98 | -1547.01 | -231.19 | 5.56 | 5.4 | -1.38 | -13.85 | 94 | 10000.35 | 839451.37 | 2699334.82 | 30.1239 | -96.7879 | 231.6
11029 | 74.42 | 331.52 | 10467.16 | -1146.71 | -1592.55 | -139.82 | 2.85 | 0.38 | 2.94 | 82.74 | 95 | 10026.16 | 839530.64 | 2699289.28 | 30.1241 | -96.788 | 234.24
11124 | 92.53 | 333.12 | 10477.91 | -1063.46 | -1636.19 | -46.06 | 19.14 | 19.06 | 1.68 | 5.13 | 95 | 10036.91 | 839613.89 | 2699245.64 | 30.1243 | -96.7881 | 236.98
11218 | 97.01 | 329.75 | 10470.09 | -981.22 | -1680.95 | 47.44 | 5.96 | 4.77 | -3.59 | -36.73 | 94 | 10029.09 | 839696.13 | 2699200.88 | 30.1245 | -96.7883 | 239.73
11313 | 92.61 | 327.6 | 10462.13 | -900.38 | -1730.16 | 142.08 | 5.15 | -4.63 | -2.26 | -153.94 | 95 | 10021.13 | 839776.97 | 2699151.67 | 30.1248 | -96.7884 | 242.51
11409 | 91.56 | 326.71 | 10458.64 | -819.78 | -1782.19 | 237.99 | 1.43 | -1.09 | -0.93 | -139.72 | 96 | 10017.64 | 839857.57 | 2699099.64 | 30.125 | -96.7886 | 245.3
11503 | 90.93 | 325.9 | 10456.59 | -741.59 | -1834.32 | 331.91 | 1.09 | -0.67 | -0.86 | -127.87 | 94 | 10015.59 | 839935.76 | 2699047.51 | 30.1252 | -96.7887 | 247.99
11597 | 91.61 | 327 | 10454.51 | -663.28 | -1886.26 | 425.83 | 1.38 | 0.72 | 1.17 | 58.26 | 94 | 10013.51 | 840014.07 | 2698995.57 | 30.1254 | -96.7889 | 250.63
11691 | 91.68 | 325.77 | 10451.81 | -585.03 | -1938.28 | 519.74 | 1.31 | 0.07 | -1.31 | -86.72 | 94 | 10010.81 | 840092.32 | 2698943.55 | 30.1256 | -96.7891 | 253.2
11785 | 91.62 | 324.96 | 10449.11 | -507.72 | -1991.68 | 613.57 | 0.86 | -0.06 | -0.86 | -94.23 | 94 | 10008.11 | 840169.63 | 2698890.15 | 30.1259 | -96.7892 | 255.7
11880 | 90.42 | 326.96 | 10447.41 | -429.01 | -2044.85 | 708.47 | 2.45 | -1.26 | 2.11 | 120.95 | 95 | 10006.41 | 840248.34 | 2698836.98 | 30.1261 | -96.7894 | 258.15
11975 | 90.16 | 327.15 | 10446.93 | -349.29 | -2096.51 | 803.44 | 0.34 | -0.27 | 0.2 | 143.84 | 95 | 10005.93 | 840328.06 | 2698785.32 | 30.1263 | -96.7896 | 260.54
12070 | 89.35 | 327.68 | 10447.34 | -269.25 | -2147.67 | 898.43 | 1.02 | -0.85 | 0.56 | 146.8 | 95 | 10006.34 | 840408.1 | 2698734.16 | 30.1265 | -96.7897 | 262.85
12165 | 88.78 | 327.45 | 10448.89 | -189.08 | -2198.62 | 993.41 | 0.65 | -0.6 | -0.24 | -158.03 | 95 | 10007.89 | 840488.27 | 2698683.21 | 30.1267 | -96.7899 | 265.08
12262 | 87.69 | 327.52 | 10451.88 | -107.32 | -2250.73 | 1090.35 | 1.13 | -1.12 | 0.07 | 176.33 | 97 | 10010.88 | 840570.03 | 2698631.1 | 30.127 | -96.79 | 267.27
12357 | 88.73 | 327.64 | 10454.84 | -27.17 | -2301.64 | 1185.29 | 1.1 | 1.09 | 0.13 | 6.58 | 95 | 10013.84 | 840650.18 | 2698580.19 | 30.1272 | -96.7902 | 269.32
12452 | 91.84 | 330.14 | 10454.37 | 54.15 | -2350.71 | 1280.27 | 4.2 | 3.27 | 2.63 | 38.8 | 95 | 10013.37 | 840731.5 | 2698531.12 | 30.1274 | -96.7903 | 271.32
12547 | 96.96 | 330.3 | 10447.09 | 136.33 | -2397.74 | 1374.91 | 5.39 | 5.39 | 0.17 | 1.78 | 95 | 10006.09 | 840813.68 | 2698484.09 | 30.1277 | -96.7905 | 273.25
12643 | 95.29 | 329.8 | 10436.84 | 219.03 | -2445.39 | 1470.31 | 1.82 | -1.74 | -0.52 | -163.39 | 96 | 9995.84 | 840896.38 | 2698436.44 | 30.1279 | -96.7906 | 275.12
12739 | 92.64 | 329.49 | 10430.21 | 301.67 | -2493.79 | 1566.05 | 2.78 | -2.76 | -0.32 | -173.33 | 96 | 9989.21 | 840979.02 | 2698388.04 | 30.1281 | -96.7908 | 276.9
12834 | 93.38 | 329.87 | 10425.22 | 383.56 | -2541.68 | 1660.89 | 0.88 | 0.78 | 0.4 | 27.14 | 95 | 9984.22 | 841060.91 | 2698340.15 | 30.1283 | -96.7909 | 278.58
12929 | 90.83 | 328.94 | 10421.73 | 465.27 | -2589.99 | 1755.8 | 2.86 | -2.68 | -0.98 | -159.96 | 95 | 9980.73 | 841142.62 | 2698291.84 | 30.1286 | -96.7911 | 280.18
13023 | 90.97 | 329.29 | 10420.25 | 545.93 | -2638.24 | 1849.78 | 0.4 | 0.15 | 0.37 | 68.19 | 94 | 9979.25 | 841223.28 | 2698243.59 | 30.1288 | -96.7912 | 281.69
13118 | 90.85 | 333.47 | 10418.74 | 629.3 | -2683.73 | 1944.61 | 4.4 | -0.13 | 4.4 | 91.61 | 95 | 9977.74 | 841306.65 | 2698198.1 | 30.129 | -96.7913 | 283.2
13212 | 91.79 | 335.55 | 10416.58 | 714.12 | -2724.17 | 2038.03 | 2.43 | 1 | 2.21 | 65.65 | 94 | 9975.58 | 841391.47 | 2698157.66 | 30.1293 | -96.7915 | 284.69
13307 | 93.22 | 337.25 | 10412.42 | 801.08 | -2762.16 | 2132 | 2.34 | 1.51 | 1.79 | 49.87 | 95 | 9971.42 | 841478.43 | 2698119.67 | 30.1295 | -96.7916 | 286.17
13403 | 94.24 | 336.86 | 10406.18 | 889.3 | -2799.51 | 2226.68 | 1.14 | 1.06 | -0.41 | -20.87 | 96 | 9965.18 | 841566.65 | 2698082.32 | 30.1297 | -96.7917 | 287.62
13498 | 92.62 | 336.38 | 10400.5 | 976.34 | -2837.14 | 2320.52 | 1.78 | -1.71 | -0.51 | -163.51 | 95 | 9959.5 | 841653.69 | 2698044.69 | 30.13 | -96.7918 | 288.99
13593 | 92.64 | 334.59 | 10396.14 | 1062.68 | -2876.51 | 2414.68 | 1.88 | 0.02 | -1.88 | -89.32 | 95 | 9955.14 | 841740.03 | 2698005.32 | 30.1302 | -96.7919 | 290.28
13687 | 92.63 | 329.38 | 10391.81 | 1145.55 | -2920.6 | 2508.35 | 5.54 | -0.01 | -5.54 | -89.99 | 94 | 9950.81 | 841822.9 | 2697961.23 | 30.1305 | -96.7921 | 291.42
13782 | 92.29 | 329.59 | 10387.73 | 1227.32 | -2968.8 | 2603.25 | 0.42 | -0.36 | 0.22 | 148.32 | 95 | 9946.73 | 841904.67 | 2697913.03 | 30.1307 | -96.7922 | 292.46
13876 | 92.44 | 326.55 | 10383.85 | 1307.02 | -3018.46 | 2697.16 | 3.24 | 0.16 | -3.23 | -87.11 | 94 | 9942.85 | 841984.37 | 2697863.37 | 30.1309 | -96.7924 | 293.41
13970 | 91.82 | 325.26 | 10380.36 | 1384.8 | -3071.12 | 2791 | 1.52 | -0.66 | -1.37 | -115.66 | 94 | 9939.36 | 842062.15 | 2697810.71 | 30.1311 | -96.7925 | 294.27
14064 | 92.38 | 324.61 | 10376.92 | 1461.69 | -3125.09 | 2884.78 | 0.91 | 0.6 | -0.69 | -49.22 | 94 | 9935.92 | 842139.04 | 2697756.74 | 30.1313 | -96.7927 | 295.07
14159 | 92.43 | 327.94 | 10372.93 | 1540.62 | -3177.78 | 2979.62 | 3.5 | 0.05 | 3.51 | 89.07 | 95 | 9931.93 | 842217.97 | 2697704.05 | 30.1316 | -96.7929 | 295.86
14253 | 94.17 | 327.66 | 10367.52 | 1620.03 | -3227.78 | 3073.45 | 1.87 | 1.85 | -0.3 | -9.12 | 94 | 9926.52 | 842297.38 | 2697654.05 | 30.1318 | -96.793 | 296.65
14347 | 95.35 | 327.32 | 10359.72 | 1699.02 | -3278.13 | 3167.12 | 1.31 | 1.26 | -0.36 | -16.01 | 94 | 9918.72 | 842376.37 | 2697603.7 | 30.132 | -96.7932 | 297.4
14442 | 92.24 | 328.44 | 10353.43 | 1779.3 | -3328.52 | 3261.89 | 3.48 | -3.27 | 1.18 | 160.19 | 95 | 9912.43 | 842456.65 | 2697553.31 | 30.1322 | -96.7933 | 298.13
14536 | 93.14 | 328.56 | 10349.02 | 1859.35 | -3377.58 | 3355.79 | 0.97 | 0.96 | 0.13 | 7.58 | 94 | 9908.02 | 842536.7 | 2697504.25 | 30.1324 | -96.7935 | 298.83
14629 | 90.14 | 327.47 | 10346.36 | 1938.19 | -3426.81 | 3448.74 | 3.43 | -3.23 | -1.17 | -160.02 | 93 | 9905.36 | 842615.54 | 2697455.02 | 30.1327 | -96.7936 | 299.49
14724 | 90.91 | 327.19 | 10345.49 | 2018.16 | -3478.09 | 3543.72 | 0.86 | 0.81 | -0.29 | -19.98 | 95 | 9904.49 | 842695.51 | 2697403.74 | 30.1329 | -96.7938 | 300.12
14819 | 91.62 | 326.47 | 10343.39 | 2097.66 | -3530.06 | 3638.66 | 1.06 | 0.75 | -0.76 | -45.39 | 95 | 9902.39 | 842775.01 | 2697351.77 | 30.1331 | -96.7939 | 300.72
14913 | 93.09 | 326.12 | 10339.53 | 2175.79 | -3582.17 | 3732.52 | 1.61 | 1.56 | -0.37 | -13.37 | 94 | 9898.53 | 842853.14 | 2697299.66 | 30.1333 | -96.7941 | 301.27
15009 | 94.67 | 326.04 | 10333.03 | 2255.27 | -3635.62 | 3828.22 | 1.65 | 1.65 | -0.08 | -2.89 | 96 | 9892.03 | 842932.62 | 2697246.21 | 30.1335 | -96.7943 | 301.81
15104 | 92.54 | 327.44 | 10327.06 | 2334.54 | -3687.61 | 3922.99 | 2.68 | -2.24 | 1.47 | 146.69 | 95 | 9886.06 | 843011.89 | 2697194.22 | 30.1338 | -96.7944 | 302.34
15199 | 92.23 | 326.37 | 10323.1 | 2414.06 | -3739.44 | 4017.88 | 1.17 | -0.33 | -1.13 | -106.15 | 95 | 9882.1 | 843091.41 | 2697142.39 | 30.134 | -96.7946 | 302.84
15294 | 92.57 | 325.6 | 10319.13 | 2492.73 | -3792.54 | 4112.71 | 0.89 | 0.36 | -0.81 | -66.14 | 95 | 9878.13 | 843170.08 | 2697089.29 | 30.1342 | -96.7947 | 303.32
15389 | 91.08 | 326.84 | 10316.1 | 2571.65 | -3845.33 | 4207.6 | 2.04 | -1.57 | 1.31 | 140.22 | 95 | 9875.1 | 843249 | 2697036.5 | 30.1344 | -96.7949 | 303.77
15485 | 91.99 | 326.5 | 10313.53 | 2651.83 | -3898.06 | 4303.52 | 1.01 | 0.95 | -0.35 | -20.48 | 96 | 9872.53 | 843329.18 | 2696983.77 | 30.1346 | -96.7951 | 304.23
15580 | 93.32 | 326.04 | 10309.13 | 2730.75 | -3950.75 | 4398.35 | 1.48 | 1.4 | -0.48 | -19.05 | 95 | 9868.13 | 843408.1 | 2696931.08 | 30.1349 | -96.7952 | 304.65
15675 | 92.58 | 326.7 | 10304.24 | 2809.75 | -4003.29 | 4493.17 | 1.04 | -0.78 | 0.69 | 138.29 | 95 | 9863.24 | 843487.1 | 2696878.54 | 30.1351 | -96.7954 | 305.06
15770 | 93.53 | 325.81 | 10299.18 | 2888.63 | -4055.99 | 4587.97 | 1.37 | 1 | -0.94 | -43.07 | 95 | 9858.18 | 843565.98 | 2696825.84 | 30.1353 | -96.7956 | 305.46
15865 | 91.58 | 325.96 | 10294.94 | 2967.2 | -4109.21 | 4682.79 | 2.06 | -2.05 | 0.16 | 175.6 | 95 | 9853.94 | 843644.55 | 2696772.62 | 30.1355 | -96.7957 | 305.83
15960 | 92.66 | 325.86 | 10291.43 | 3045.82 | -4162.42 | 4777.64 | 1.14 | 1.14 | -0.11 | -5.28 | 95 | 9850.43 | 843723.17 | 2696719.41 | 30.1357 | -96.7959 | 306.19
16055 | 91.85 | 325.8 | 10287.69 | 3124.36 | -4215.74 | 4872.47 | 0.85 | -0.85 | -0.06 | -175.77 | 95 | 9846.69 | 843801.71 | 2696666.09 | 30.136 | -96.796 | 306.54
16149 | 93.25 | 325.26 | 10283.51 | 3201.78 | -4268.89 | 4966.26 | 1.6 | 1.49 | -0.57 | -21.06 | 94 | 9842.51 | 843879.13 | 2696612.94 | 30.1362 | -96.7962 | 306.87
16243 | 92.09 | 326.22 | 10279.13 | 3279.38 | -4321.74 | 5060.06 | 1.6 | -1.23 | 1.02 | 140.4 | 94 | 9838.13 | 843956.73 | 2696560.09 | 30.1364 | -96.7964 | 307.19
16338 | 93.17 | 325.99 | 10274.77 | 3358.15 | -4374.67 | 5154.89 | 1.16 | 1.14 | -0.24 | -12 | 95 | 9833.77 | 844035.5 | 2696507.16 | 30.1366 | -96.7965 | 307.51
16432 | 91.94 | 326.55 | 10270.58 | 3436.25 | -4426.81 | 5248.73 | 1.44 | -1.31 | 0.6 | 155.53 | 94 | 9829.58 | 844113.6 | 2696455.02 | 30.1368 | -96.7967 | 307.82
16527 | 93.62 | 326.39 | 10265.97 | 3515.34 | -4479.22 | 5343.57 | 1.78 | 1.77 | -0.17 | -5.43 | 95 | 9824.97 | 844192.69 | 2696402.61 | 30.137 | -96.7969 | 308.13
16621 | 91.92 | 327.3 | 10261.43 | 3593.94 | -4530.57 | 5437.42 | 2.05 | -1.81 | 0.97 | 151.84 | 94 | 9820.43 | 844271.29 | 2696351.26 | 30.1373 | -96.797 | 308.42
16716 | 89.26 | 327.84 | 10260.45 | 3674.12 | -4581.51 | 5532.4 | 2.86 | -2.8 | 0.57 | 168.52 | 95 | 9819.45 | 844351.47 | 2696300.32 | 30.1375 | -96.7972 | 308.73
16777 | 89.56 | 327.71 | 10261.08 | 3725.72 | -4614.03 | 5593.39 | 0.54 | 0.49 | -0.21 | -23.43 | 61 | 9820.08 | 844403.07 | 2696267.8 | 30.1376 | -96.7973 | 308.92
16840 | 89.6 | 327.8 | 10261.54 | 3779 | -4647.64 | 5656.39 | 0.16 | 0.06 | 0.14 | 66.04 | 63 | 9820.54 | 844456.35 | 2696234.19 | 30.1378 | -96.7974 | 309.11

## 12_12_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/12/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 13250 |  |  | Well Cost($): |  | 13250
|  |  |  | 24hr Summary: |  | Drilled Surface
|  |  |  | 24hr Lookahead: |  | Nipple up BOPs, test same, pick up BHA #2
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 3080 |  | 3080 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 2975 |  | 2975 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 350 |  | 350 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2625 |  | 2625 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.22 / 1.17 |  | 4.22 / 1.17 |  | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 1.23 |  | 1.23 |  | SN: |  | 47245 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 2.98 |  | 2.98 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): |  | 879.89 / 283.78 |  | 879.89 / 283.78 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 10.5 |  | 10.5 |  | Grade In: |  | New
% Slide: |  | 11.76 |  | 11.76 |  | Grade Out: |  | 0-0-NO-I-TD
% Rotary: |  | 88.24 |  | 88.24 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2"- Ulterra - U616S - Jetted - 9x14s - TFA 1.35 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  |  | 8 | 2 |  |  |  |  | 37.92 |  | 39.42
13" - 4 Blade Nortrak Stabilizer (BFF) |  |  |  | 8.188 | 2.875 |  |  |  |  | 6.9 |  | 46.32
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 55.18
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 58.29
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 87.2
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 116.74
X/O- 4 1/2 IFB x 6 5/8 RegP |  |  |  | 6.563 | 2.875 |  |  |  |  | 2.78 |  | 119.52
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 394.82
394.82
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800004 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.45 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
138 | 0.63 | 337.95 | 138 | 0.7 | -0.28 | 0.46 |  | 337.95 | 0.75 | 0.46 |  | 0 | 138
229 | 0.31 | 324.62 | 228.99 | 1.37 | -0.62 | 0.37 |  | -167.72 | 1.49 | -0.35 |  | 0 | 91
320 | 0.45 | 239.48 | 319.99 | 1.39 | -1.07 | 0.58 |  | -121.23 | 1.74 | 0.15 |  | 0 | 91
415 | 0.68 | 204.67 | 414.99 | 0.69 | -1.62 | 0.42 |  | -74.41 | 1.43 | 0.24 |  | 0 | 95
510 | 0.82 | 216.67 | 509.98 | -0.37 | -2.26 | 0.22 |  | 54.39 | 0.87 | 0.15 |  | 0 | 95
604 | 2.02 | 213.51 | 603.95 | -2.29 | -3.58 | 1.28 |  | -5.31 | -0.07 | 1.28 |  | 0 | 94
699 | 3.05 | 217.55 | 698.86 | -5.69 | -6.04 | 1.1 |  | 11.86 | -1.67 | 1.08 |  | 4.25 | 95
793 | 4.56 | 214.46 | 792.65 | -10.76 | -9.68 | 1.62 |  | -9.28 | -4.07 | 1.61 |  | -3.29 | 94
887 | 5.68 | 216.2 | 886.27 | -17.59 | -14.54 | 1.2 |  | 8.76 | -7.34 | 1.19 |  | 1.85 | 94
982 | 7.76 | 221.43 | 980.61 | -26.2 | -21.57 | 2.28 |  | 19 | -10.97 | 2.19 |  | 5.51 | 95
1075 | 10.05 | 223.01 | 1072.49 | -36.84 | -31.26 | 2.48 |  | 6.88 | -14.94 | 2.46 |  | 1.7 | 93
1169 | 12.66 | 222.8 | 1164.64 | -50.4 | -43.85 | 2.78 |  | -1.01 | -19.87 | 2.78 |  | -0.22 | 94
1263 | 14.44 | 223.01 | 1256.02 | -66.53 | -58.85 | 1.89 |  | 1.69 | -25.72 | 1.89 |  | 0.22 | 94
1356 | 15 | 221.25 | 1345.96 | -84.05 | -74.69 | 0.77 |  | -39.46 | -32.32 | 0.6 |  | -1.89 | 93
1450 | 16.38 | 218.32 | 1436.46 | -103.6 | -90.93 | 1.69 |  | -31.28 | -40.43 | 1.47 |  | -3.12 | 94
1544 | 16.85 | 219.29 | 1526.54 | -124.54 | -107.78 | 0.58 |  | 31.01 | -49.41 | 0.5 |  | 1.03 | 94
1638 | 15.88 | 218.67 | 1616.73 | -145.13 | -124.44 | 1.05 |  | -170.09 | -58.18 | -1.03 |  | -0.66 | 94
1731 | 15.19 | 220.33 | 1706.33 | -164.35 | -140.28 | 0.88 |  | 148 | -66.23 | -0.74 |  | 1.78 | 93
1826 | 15.49 | 219.13 | 1797.95 | -183.68 | -156.34 | 0.46 |  | -47.2 | -74.24 | 0.32 |  | -1.26 | 95
1920 | 15.93 | 216.98 | 1888.43 | -203.72 | -172.02 | 0.78 |  | -53.96 | -83.07 | 0.47 |  | -2.29 | 94
2013 | 15.41 | 219.32 | 1977.98 | -223.48 | -187.53 | 0.88 |  | 130.57 | -91.74 | -0.56 |  | 2.52 | 93
2108 | 14.91 | 218.37 | 2069.67 | -242.82 | -203.11 | 0.59 |  | -154.04 | -100.02 | -0.53 |  | -1 | 95
2203 | 14.68 | 215.42 | 2161.52 | -262.21 | -217.67 | 0.83 |  | -108.4 | -108.88 | -0.24 |  | -3.11 | 95
2297 | 14.7 | 216.61 | 2252.45 | -281.49 | -231.69 | 0.32 |  | 86.78 | -117.93 | 0.02 |  | 1.27 | 94
2392 | 15.6 | 217.47 | 2344.15 | -301.31 | -246.65 | 0.98 |  | 14.44 | -126.94 | 0.95 |  | 0.91 | 95
2486 | 14.58 | 216.92 | 2434.91 | -320.8 | -261.45 | 1.1 |  | -172.27 | -135.76 | -1.09 |  | -0.59 | 94
2580 | 14.81 | 215.53 | 2525.83 | -340.04 | -275.53 | 0.45 |  | -57.56 | -144.74 | 0.24 |  | -1.48 | 94
2674 | 14.23 | 214.6 | 2616.83 | -359.32 | -289.08 | 0.66 |  | -158.55 | -154.04 | -0.62 |  | -0.99 | 94
2768 | 14.22 | 212.02 | 2707.95 | -378.62 | -301.76 | 0.67 |  | -92.15 | -163.81 | -0.01 |  | -2.74 | 94
2862 | 12.96 | 211.41 | 2799.31 | -397.41 | -313.37 | 1.35 |  | -173.81 | -173.7 | -1.34 |  | -0.65 | 94
2956 | 12.23 | 209.99 | 2891.05 | -415.03 | -323.84 | 0.84 |  | -157.71 | -183.2 | -0.78 |  | -1.51 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 730.43 | 19.1 | 96.74 | 243 | 882.16 | 2219.66 | 1684.48 | 0 | 86.81 | 81.29 | 75.78 | 6917.39 | 0
Run | 730.43 | 19.1 | 96.74 | 243 | 882.16 | 2219.66 | 1684.48 | 0 | 86.81 | 81.29 | 75.78 | 6917.39 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Mob/Demob |  |  |  |  | 12/12/2020 |  | 1 |  | 6000 |  | 1 | 6000
Directional & MWD / Gamma Service |  |  |  |  | 12/12/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/12/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 13250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/12/2020 | 00:00 | 06:30 | 6.5 | 105 | 105 | 0 | SUR |  | 24B | Standby
12/12/2020 | 06:30 | 07:00 | 0.5 | 105 | 105 | 0 | SUR | 1: BHA #1 (Surface) | 6O | Pick up BHA #1
12/12/2020 | 07:00 | 07:02 | 0.03 | 105 | 212 | 107 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/105.00 t/212.00, w/WOB 5.00,Flow 480.00, RPM 50.00, Press 600.00, Tq 2500.00, ROP 3210.00
12/12/2020 | 07:02 | 07:05 | 0.05 | 212 | 212 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 07:05 | 07:16 | 0.18 | 212 | 303 | 91 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/212.00 t/303.00, w/WOB 5.00,Flow 675, RPM 60, Press 900, Tq 2700, ROP 496.36
12/12/2020 | 07:16 | 07:27 | 0.18 | 303 | 303 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 07:27 | 07:28 | 0.02 | 303 | 320 | 17 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/303.00 t/320.00, w/WOB 5.00,Flow 770, RPM 70, Press 1200, Tq 3200, ROP 1020.00
12/12/2020 | 07:28 | 07:36 | 0.13 | 320 | 335 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/320.00 t/335.00, TF , w/WOB 2,Flow 770, Press 1050, Tq 0, ROP 112.50
12/12/2020 | 07:36 | 07:42 | 0.1 | 335 | 394 | 59 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/335.00 t/394.00, w/WOB 7,Flow 770, RPM 70, Press 1200, Tq 3200, ROP 590.00
12/12/2020 | 07:42 | 07:47 | 0.08 | 394 | 394 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 07:47 | 07:58 | 0.18 | 394 | 489 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/394.00 t/489.00, w/WOB 7,Flow 900, RPM 100, Press 1800, Tq 4600, ROP 518.18
12/12/2020 | 07:58 | 08:03 | 0.08 | 489 | 489 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 08:03 | 08:10 | 0.12 | 489 | 584 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/489.00 t/584.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 814.29
12/12/2020 | 08:10 | 08:15 | 0.08 | 584 | 584 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 08:15 | 08:16 | 0.02 | 584 | 590 | 6 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/584.00 t/590.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 360.00
12/12/2020 | 08:16 | 08:28 | 0.2 | 590 | 610 | 20 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/590.00 t/610.00, TF 215.00, w/WOB 2.00,Flow 900.00, Press 1500.00, Tq 0.00, ROP 100.00
12/12/2020 | 08:28 | 08:33 | 0.08 | 610 | 678 | 68 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/610.00 t/678.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 816.00
12/12/2020 | 08:33 | 08:39 | 0.1 | 678 | 678 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 08:39 | 08:40 | 0.02 | 678 | 680 | 2 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/678.00 t/680.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 120.00
12/12/2020 | 08:40 | 08:45 | 0.08 | 680 | 700 | 20 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/680.00 t/700.00, TF 215.00, w/WOB 7.00,Flow 900.00, Press 1500.00, Tq 0.00, ROP 240.00
12/12/2020 | 08:45 | 08:49 | 0.07 | 700 | 773 | 73 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/700.00 t/773.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 1095.00
12/12/2020 | 08:49 | 08:55 | 0.1 | 773 | 773 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 08:55 | 08:56 | 0.02 | 773 | 780 | 7 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/773.00 t/780.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 420.00
12/12/2020 | 08:56 | 09:00 | 0.07 | 780 | 805 | 25 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/780.00 t/805.00, TF -10.00, w/WOB 7.00,Flow 900.00, Press 1500.00, Tq 0.00, ROP 375.00
12/12/2020 | 09:00 | 09:03 | 0.05 | 805 | 867 | 62 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/805.00 t/867.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1800.00, Tq 4600.00, ROP 1240.00
12/12/2020 | 09:03 | 09:08 | 0.08 | 867 | 867 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 09:08 | 09:09 | 0.02 | 867 | 875 | 8 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/867.00 t/875.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 480.00
12/12/2020 | 09:09 | 09:12 | 0.05 | 875 | 905 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/875.00 t/905.00, TF 0.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 600.00
12/12/2020 | 09:12 | 09:15 | 0.05 | 905 | 961 | 56 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/905.00 t/961.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 1120.00
12/12/2020 | 09:15 | 09:20 | 0.08 | 961 | 961 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 09:20 | 09:21 | 0.02 | 961 | 975 | 14 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/961.00 t/975.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 840.00
12/12/2020 | 09:21 | 09:26 | 0.08 | 975 | 1015 | 40 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/975.00 t/1015.00, TF 0.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 480.00
12/12/2020 | 09:26 | 09:29 | 0.05 | 1015 | 1056 | 41 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1015.00 t/1056.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 820.00
12/12/2020 | 09:29 | 09:34 | 0.08 | 1056 | 1056 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 09:34 | 09:35 | 0.02 | 1056 | 1065 | 9 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1056.00 t/1065.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 540.00
12/12/2020 | 09:35 | 09:40 | 0.08 | 1065 | 1105 | 40 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1065.00 t/1105.00, TF -20.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 480.00
12/12/2020 | 09:40 | 09:43 | 0.05 | 1105 | 1149 | 44 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1105.00 t/1149.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 880.00
12/12/2020 | 09:43 | 09:48 | 0.08 | 1149 | 1149 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 09:48 | 09:49 | 0.02 | 1149 | 1160 | 11 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1149.00 t/1160.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 660.00
12/12/2020 | 09:49 | 09:54 | 0.08 | 1160 | 1200 | 40 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1160.00 t/1200.00, TF -20.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 480.00
12/12/2020 | 09:54 | 09:56 | 0.03 | 1200 | 1243 | 43 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1200.00 t/1243.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 1290.00
12/12/2020 | 09:56 | 10:01 | 0.08 | 1243 | 1243 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 10:01 | 10:02 | 0.02 | 1243 | 1255 | 12 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1243.00 t/1255.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 720.00
12/12/2020 | 10:02 | 10:09 | 0.12 | 1255 | 1295 | 40 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1255.00 t/1295.00, TF -20.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 342.86
12/12/2020 | 10:09 | 10:11 | 0.03 | 1295 | 1337 | 42 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1295.00 t/1337.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 1260.00
12/12/2020 | 10:11 | 10:15 | 0.07 | 1337 | 1337 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 10:15 | 10:16 | 0.02 | 1337 | 1350 | 13 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1337.00 t/1350.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 780.00
12/12/2020 | 10:16 | 10:21 | 0.08 | 1350 | 1365 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1350.00 t/1365.00, TF -80.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 180.00
12/12/2020 | 10:21 | 10:24 | 0.05 | 1365 | 1430 | 65 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1365.00 t/1430.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 1300.00
12/12/2020 | 10:24 | 10:30 | 0.1 | 1430 | 1430 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 10:30 | 10:31 | 0.02 | 1430 | 1440 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1430.00 t/1440.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 4600.00, ROP 600.00
12/12/2020 | 10:31 | 10:35 | 0.07 | 1440 | 1470 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1440.00 t/1470.00, TF -20.00, w/WOB 12.00,Flow 900.00, Press 1820.00, Tq 0.00, ROP 450.00
12/12/2020 | 10:35 | 10:37 | 0.03 | 1470 | 1524 | 54 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1470.00 t/1524.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1620.00
12/12/2020 | 10:37 | 10:42 | 0.08 | 1524 | 1524 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 10:42 | 10:47 | 0.08 | 1524 | 1618 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1524.00 t/1618.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1128.00
12/12/2020 | 10:47 | 10:52 | 0.08 | 1618 | 1618 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 10:52 | 10:57 | 0.08 | 1618 | 1712 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1618.00 t/1712.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1128.00
12/12/2020 | 10:57 | 11:02 | 0.08 | 1712 | 1712 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 11:02 | 11:07 | 0.08 | 1712 | 1805 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1712.00 t/1805.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1116.00
12/12/2020 | 11:07 | 11:12 | 0.08 | 1805 | 1805 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 11:12 | 11:13 | 0.02 | 1805 | 1815 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1805.00 t/1815.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 600.00
12/12/2020 | 11:13 | 11:24 | 0.18 | 1815 | 1850 | 35 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1815.00 t/1850.00, TF , w/WOB 15,Flow 900.00, Press 2150, Tq 0.00, ROP 190.91
12/12/2020 | 11:24 | 11:26 | 0.03 | 1850 | 1900 | 50 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1850.00 t/1900.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1500.00
12/12/2020 | 11:26 | 11:31 | 0.08 | 1900 | 1900 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 11:31 | 11:37 | 0.1 | 1900 | 1994 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1900.00 t/1994.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 940.00
12/12/2020 | 11:37 | 11:42 | 0.08 | 1994 | 1994 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 11:42 | 11:46 | 0.07 | 1994 | 2087 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1994.00 t/2087.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1395.00
12/12/2020 | 11:46 | 11:51 | 0.08 | 2087 | 2087 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 11:51 | 11:57 | 0.1 | 2087 | 2182 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2087.00 t/2182.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 950.00
12/12/2020 | 11:57 | 12:02 | 0.08 | 2182 | 2182 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 12:02 | 12:10 | 0.13 | 2182 | 2277 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2182.00 t/2277.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 712.50
12/12/2020 | 12:10 | 12:20 | 0.17 | 2277 | 2277 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 12:20 | 12:21 | 0.02 | 2277 | 2285 | 8 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2277.00 t/2285.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 480.00
12/12/2020 | 12:21 | 12:36 | 0.25 | 2285 | 2325 | 40 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2285.00 t/2325.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 160.00
12/12/2020 | 12:36 | 12:40 | 0.07 | 2325 | 2371 | 46 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2325.00 t/2371.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 690.00
12/12/2020 | 12:40 | 12:45 | 0.08 | 2371 | 2371 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 12:45 | 12:49 | 0.07 | 2371 | 2466 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2371.00 t/2466.00, w/WOB 28,Flow 900.00, RPM 100, Press 2800, Tq 10000, ROP 1425.00
12/12/2020 | 12:49 | 12:55 | 0.1 | 2466 | 2466 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 12:55 | 13:00 | 0.08 | 2466 | 2560 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2466.00 t/2560.00, w/WOB 30,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 1128.00
12/12/2020 | 13:00 | 13:05 | 0.08 | 2560 | 2560 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 13:05 | 13:08 | 0.05 | 2560 | 2654 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2560.00 t/2654.00, w/WOB 30,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 1880.00
12/12/2020 | 13:08 | 13:13 | 0.08 | 2654 | 2654 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 13:13 | 13:18 | 0.08 | 2654 | 2748 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2654.00 t/2748.00, w/WOB 30,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 1128.00
12/12/2020 | 13:18 | 13:23 | 0.08 | 2748 | 2748 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 13:23 | 13:30 | 0.12 | 2748 | 2842 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2748.00 t/2842.00, w/WOB 30,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 805.71
12/12/2020 | 13:30 | 13:35 | 0.08 | 2842 | 2842 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 13:35 | 13:42 | 0.12 | 2842 | 2936 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2842.00 t/2936.00, w/WOB 30,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 805.71
12/12/2020 | 13:42 | 13:47 | 0.08 | 2936 | 2936 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 13:47 | 13:51 | 0.07 | 2936 | 3030 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2936.00 t/3030.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 1410.00
12/12/2020 | 13:51 | 13:56 | 0.08 | 3030 | 3030 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
12/12/2020 | 13:56 | 14:00 | 0.07 | 3030 | 3080 | 50 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/3030.00 t/3080.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2800.00, Tq 10000.00, ROP 750.00
12/12/2020 | 14:00 | 14:05 | 0.08 | 3080 | 3080 | 0 | SUR | 1: BHA #1 (Surface) | 10D | MWD survey @ Td of surface
12/12/2020 | 14:05 | 15:15 | 1.17 | 3080 | 3080 | 0 | SUR | 1: BHA #1 (Surface) | 5A | Circulate, prepare to POOH to run surface casing
12/12/2020 | 15:15 | 16:30 | 1.25 | 3080 | 3080 | 0 | SUR | 1: BHA #1 (Surface) | 6B | POOH
12/12/2020 | 16:30 | 17:30 | 1 | 3080 | 3080 | 0 | SUR | 1: BHA #1 (Surface) | 6P | Lay down BHA #1
12/12/2020 | 17:30 | 24:00 | 6.5 | 3080 | 3080 | 0 | SUR |  | 24B | Standby for, surface casing opps. nipple up BOPs and test same
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_13_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/13/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 20500
|  |  |  | 24hr Summary: |  | Standby; P/U BHA #2; TIH
|  |  |  | 24hr Lookahead: |  | TIH; Drill Out Float Equipment; Drill Ahead in Intermediate Section
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3080 |  | 3080 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 3080 |  | 3080 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 0.00 / 0.33 |  | 0.00 / 0.33 |  | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  | 54300 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) |  | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 3 |  | 3 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-CT-G-X-I-NO-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  |  |  | 8 | 2 |  |  |  |  | 37.67 |  | 39.17
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.03
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.14
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.05
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.59
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 111.71
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.49
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.53
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 576.83
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.63
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.43 |  | 2679.06
2679.06
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800049 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 19.1 | 96.74 | 243 | 882.16 | 2219.66 | 1684.48 | 0 | 86.81 | 81.29 | 75.78 | 6917.39 | 0
Run | 0 | 19.1 | 96.74 | 243 | 882.16 | 2219.66 | 1684.48 | 0 | 86.81 | 81.29 | 75.78 | 6917.39 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 12/13/2020 |  | 4 |  | 100 |  | 4 | 400
Directional & MWD / Gamma Service |  |  |  |  | 12/13/2020 |  | 2 |  | 6850 |  | 1 | 6850
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/13/2020 | 00:00 | 19:20 | 19.33 | 3080 | 3080 | 0 | INT |  | 24B | Standby
12/13/2020 | 19:20 | 21:00 | 1.67 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 6O | P/U Directional BHA
12/13/2020 | 21:00 | 22:05 | 1.08 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 6J | P/U and M/U 6 1/2 DC
12/13/2020 | 22:05 | 22:15 | 0.17 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Test MWD (Good)
12/13/2020 | 22:15 | 23:30 | 1.25 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH 3 Stds HWDP & 22 Stds DP
12/13/2020 | 23:30 | 23:35 | 0.08 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Check SPP before Agitator
12/13/2020 | 23:35 | 23:45 | 0.17 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | P/U Agitator
12/13/2020 | 23:45 | 23:50 | 0.08 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Check SPP after Agitator
12/13/2020 | 23:50 | 24:00 | 0.17 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_14_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/14/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 27750
|  |  |  | 24hr Summary: |  | TIH w/ BHA #2; Drill Out Float Equipment; Drill Ahead in Intermediate Section
|  |  |  | 24hr Lookahead: |  | Continue Drilling Intermediate Section t/ Section TD; TOH; Standby for Casing Ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3080 |  | 3080 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 8880 |  | 8880 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 5800 |  | 5800 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity: | 50
Slide Drilled (Usft): |  | 491 |  | 491 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 5309 |  | 5309 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 16.83 / 0.67 |  | 16.83 / 1.00 |  | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 5.02 |  | 5.02 |  | SN: |  | 54300 |  | 10s Gel: |  | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 11.82 |  | 11.82 |  | Bit # |  | 2 |  | PH / Temp(F) |  | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 449.28 / 97.87 |  | 449.28 / 97.87 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 27 |  | Grade In: |  | New
% Slide: |  | 8.47 |  | 8.47 |  | Grade Out: |  | 0-1-CT-G-X-I-NO-TD
% Rotary: |  | 91.53 |  | 91.53 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  |  |  | 8 | 2 |  |  |  |  | 37.67 |  | 39.17
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.03
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.14
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.05
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.59
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 111.71
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.49
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.53
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 576.83
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.63
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.43 |  | 2679.06
2679.06
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800049 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3174 | 14.6 | 212.59 | 3103.47 | -456.97 | -348.94 | 1.68 |  | 16.04 | -205.72 | 1.63 |  | 1.84 | 168
3267 | 18.1 | 217.51 | 3192.7 | -478.32 | -364.06 | 4.04 |  | 23.97 | -215.95 | 3.76 |  | 5.29 | 93
3361 | 18.2 | 217.93 | 3282.03 | -501.48 | -381.97 | 0.18 |  | 52.81 | -226.26 | 0.11 |  | 0.45 | 94
3455 | 18.41 | 216.66 | 3371.27 | -524.96 | -399.86 | 0.48 |  | -62.84 | -236.85 | 0.22 |  | -1.35 | 94
3548 | 18.92 | 215.61 | 3459.38 | -549 | -417.4 | 0.66 |  | -33.88 | -248.1 | 0.55 |  | -1.13 | 93
3642 | 17.9 | 212.61 | 3548.57 | -573.56 | -434.06 | 1.48 |  | -138.53 | -260.26 | -1.09 |  | -3.19 | 94
3736 | 17.53 | 211.35 | 3638.11 | -597.82 | -449.21 | 0.57 |  | -134.58 | -272.95 | -0.39 |  | -1.34 | 94
3829 | 15.79 | 215.8 | 3727.21 | -620.05 | -463.9 | 2.32 |  | 145.87 | -284.15 | -1.87 |  | 4.78 | 93
3923 | 15 | 215.4 | 3817.84 | -640.34 | -478.43 | 0.85 |  | -172.54 | -293.79 | -0.84 |  | -0.43 | 94
4016 | 14.81 | 221.34 | 3907.71 | -659.07 | -493.26 | 1.65 |  | 99.95 | -301.95 | -0.2 |  | 6.39 | 93
4110 | 14.43 | 223.48 | 3998.67 | -676.59 | -509.25 | 0.7 |  | 126.16 | -308.47 | -0.4 |  | 2.28 | 94
4204 | 14.32 | 222.61 | 4089.73 | -693.65 | -525.18 | 0.26 |  | -117.41 | -314.62 | -0.12 |  | -0.93 | 94
4298 | 13.92 | 223.2 | 4180.89 | -710.44 | -540.79 | 0.45 |  | 160.5 | -320.72 | -0.43 |  | 0.63 | 94
4392 | 14.87 | 221.99 | 4271.93 | -727.65 | -556.6 | 1.06 |  | -18.16 | -327.06 | 1.01 |  | -1.29 | 94
4484 | 15.24 | 222.04 | 4360.78 | -745.4 | -572.59 | 0.4 |  | 2.03 | -333.78 | 0.4 |  | 0.05 | 92
4578 | 14.55 | 221.22 | 4451.62 | -763.46 | -588.65 | 0.77 |  | -163.41 | -340.72 | -0.73 |  | -0.87 | 94
4673 | 15.55 | 221.82 | 4543.36 | -781.93 | -605 | 1.07 |  | 9.15 | -347.85 | 1.05 |  | 0.63 | 95
4768 | 16.31 | 220.66 | 4634.71 | -801.54 | -622.19 | 0.87 |  | -23.29 | -355.51 | 0.8 |  | -1.22 | 95
4862 | 15.24 | 221.43 | 4725.17 | -820.81 | -638.96 | 1.16 |  | 169.3 | -363.11 | -1.14 |  | 0.82 | 94
4956 | 15.04 | 221.89 | 4815.9 | -839.16 | -655.28 | 0.25 |  | 149.23 | -370.16 | -0.21 |  | 0.49 | 94
5049 | 14.81 | 220.4 | 4905.77 | -857.19 | -671.04 | 0.48 |  | -121.65 | -377.23 | -0.25 |  | -1.6 | 93
5144 | 13.97 | 219.89 | 4997.79 | -875.24 | -686.26 | 0.89 |  | -171.67 | -384.59 | -0.88 |  | -0.54 | 95
5238 | 15.06 | 218.26 | 5088.78 | -893.53 | -701.1 | 1.24 |  | -21.34 | -392.37 | 1.16 |  | -1.73 | 94
5332 | 15.73 | 218.58 | 5179.41 | -913.08 | -716.61 | 0.72 |  | 7.38 | -400.87 | 0.71 |  | 0.34 | 94
5425 | 15.83 | 217.5 | 5268.91 | -933 | -732.19 | 0.33 |  | -71.72 | -409.64 | 0.11 |  | -1.16 | 93
5519 | 14.44 | 217.89 | 5359.64 | -952.42 | -747.2 | 1.48 |  | 176 | -418.29 | -1.48 |  | 0.41 | 94
5613 | 13.48 | 216.63 | 5450.87 | -970.46 | -760.93 | 1.07 |  | -163.04 | -426.44 | -1.02 |  | -1.34 | 94
5706 | 13.77 | 217.84 | 5541.25 | -987.9 | -774.19 | 0.44 |  | 45.09 | -434.32 | 0.31 |  | 1.3 | 93
5800 | 16.89 | 218.96 | 5631.89 | -1007.36 | -789.64 | 3.33 |  | 5.96 | -442.77 | 3.32 |  | 1.19 | 94
5895 | 17.56 | 220.11 | 5722.63 | -1029.05 | -807.55 | 0.79 |  | 27.49 | -451.83 | 0.71 |  | 1.21 | 95
5989 | 17.19 | 220.59 | 5812.34 | -1050.45 | -825.73 | 0.42 |  | 159.05 | -460.49 | -0.39 |  | 0.51 | 94
6083 | 15.92 | 221.13 | 5902.44 | -1070.71 | -843.25 | 1.36 |  | 173.35 | -468.54 | -1.35 |  | 0.57 | 94
6177 | 16.01 | 216.92 | 5992.82 | -1090.78 | -859.51 | 1.24 |  | -87.58 | -477.08 | 0.1 |  | -4.48 | 94
6271 | 17.07 | 215.95 | 6082.93 | -1112.31 | -875.4 | 1.17 |  | -15.07 | -487.07 | 1.13 |  | -1.03 | 94
6364 | 16.32 | 215.75 | 6172.01 | -1133.97 | -891.05 | 0.81 |  | -175.72 | -497.28 | -0.81 |  | -0.22 | 93
6459 | 15.89 | 216.62 | 6263.28 | -1155.24 | -906.6 | 0.52 |  | 151.11 | -507.22 | -0.45 |  | 0.92 | 95
6554 | 14.73 | 214.98 | 6354.91 | -1175.57 | -921.29 | 1.3 |  | -160.32 | -516.81 | -1.22 |  | -1.73 | 95
6647 | 14.37 | 215.12 | 6444.93 | -1194.7 | -934.7 | 0.39 |  | 174.49 | -526.05 | -0.39 |  | 0.15 | 93
6739 | 14.03 | 214.98 | 6534.12 | -1213.17 | -947.66 | 0.37 |  | -174.3 | -534.97 | -0.37 |  | -0.15 | 92
6834 | 14.03 | 214.89 | 6626.28 | -1232.06 | -960.85 | 0.02 |  | -90.04 | -544.11 | 0 |  | -0.09 | 95
6928 | 12.99 | 215.33 | 6717.68 | -1250.02 | -973.48 | 1.11 |  | 174.57 | -552.77 | -1.11 |  | 0.47 | 94
7021 | 12.08 | 215.55 | 6808.46 | -1266.47 | -985.18 | 0.98 |  | 177.1 | -560.63 | -0.98 |  | 0.24 | 93
7115 | 13.32 | 218.03 | 6900.16 | -1283 | -997.57 | 1.44 |  | 24.95 | -568.19 | 1.32 |  | 2.64 | 94
7209 | 14.47 | 222.35 | 6991.41 | -1300.21 | -1012.16 | 1.65 |  | 44.16 | -575.18 | 1.22 |  | 4.6 | 94
7303 | 13.6 | 224.03 | 7082.6 | -1316.83 | -1027.75 | 1.02 |  | 155.72 | -581.14 | -0.93 |  | 1.79 | 94
7397 | 14.34 | 218.56 | 7173.83 | -1333.88 | -1042.69 | 1.61 |  | -63.41 | -587.81 | 0.79 |  | -5.82 | 94
7491 | 14.31 | 217.63 | 7264.91 | -1352.19 | -1057.04 | 0.25 |  | -97.88 | -595.86 | -0.03 |  | -0.99 | 94
7585 | 14.56 | 214.46 | 7355.94 | -1371.13 | -1070.81 | 0.88 |  | -73.98 | -604.74 | 0.27 |  | -3.37 | 94
7679 | 13.08 | 216.48 | 7447.22 | -1389.43 | -1083.83 | 1.66 |  | 162.92 | -613.48 | -1.57 |  | 2.15 | 94
7772 | 14.04 | 213.92 | 7537.62 | -1407.25 | -1096.38 | 1.22 |  | -33.26 | -622.06 | 1.03 |  | -2.75 | 93
7866 | 13.94 | 213.69 | 7628.84 | -1426.13 | -1109.02 | 0.12 |  | -151.04 | -631.5 | -0.11 |  | -0.24 | 94
7960 | 15.53 | 216.78 | 7719.74 | -1445.63 | -1122.84 | 1.89 |  | 27.8 | -640.84 | 1.69 |  | 3.29 | 94
8053 | 15.71 | 219.59 | 7809.31 | -1465.31 | -1138.32 | 0.84 |  | 77.97 | -649.46 | 0.19 |  | 3.02 | 93
8146 | 14.69 | 219.64 | 7899.05 | -1484.09 | -1153.86 | 1.1 |  | 179.29 | -657.28 | -1.1 |  | 0.05 | 93
8241 | 12.76 | 220.99 | 7991.34 | -1501.29 | -1168.43 | 2.06 |  | 171.23 | -664.27 | -2.03 |  | 1.42 | 95
8335 | 14.34 | 222.4 | 8082.72 | -1517.72 | -1183.09 | 1.72 |  | 12.5 | -670.56 | 1.68 |  | 1.5 | 94
8429 | 15.36 | 222.32 | 8173.58 | -1535.52 | -1199.32 | 1.09 |  | -1.19 | -677.19 | 1.09 |  | -0.09 | 94
8524 | 13.16 | 223.61 | 8265.65 | -1552.66 | -1215.25 | 2.34 |  | 172.41 | -683.41 | -2.32 |  | 1.36 | 95
8617 | 14.41 | 228.66 | 8355.97 | -1567.97 | -1231.25 | 1.86 |  | 46.38 | -688.04 | 1.34 |  | 5.43 | 93
8711 | 15.34 | 231.02 | 8446.82 | -1583.52 | -1249.69 | 1.18 |  | 34.23 | -691.59 | 0.99 |  | 2.51 | 94
8806 | 15.52 | 218.58 | 8538.42 | -1601.36 | -1267.39 | 3.48 |  | -92.9 | -697.48 | 0.19 |  | -13.09 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 333.01 | 29.05 | 70 | 183 | 681.58 | 3131.58 | 2726.32 | 0 | 154.21 | 142.79 | 136.32 | 10764.29 | 0
Run | 333.01 | 29.05 | 70 | 183 | 681.58 | 3131.58 | 2726.32 | 0 | 154.21 | 142.79 | 136.32 | 10764.29 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 12/14/2020 |  | 4 |  | 100 |  | 4 | 400
Directional & MWD / Gamma Service |  |  |  |  | 12/14/2020 |  | 2 |  | 6850 |  | 1 | 6850
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/14/2020 | 00:00 | 00:35 | 0.58 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH t/ 2891
12/14/2020 | 00:35 | 00:40 | 0.08 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 3C | Wash Down 1 Std
12/14/2020 | 00:40 | 01:15 | 0.58 | 3080 | 3080 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Drlg Out Shoe Track and Float Equipment
12/14/2020 | 01:15 | 01:20 | 0.08 | 3080 | 3090 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3080.00 t/3090.00, w/WOB 16,Flow 420, RPM 30, Press 1500, Tq 7500, ROP 120.00
12/14/2020 | 01:20 | 01:50 | 0.5 | 3090 | 3090 | 0 | INT | 2: BHA #2 (Intermediate) | 15D | FIT t/ 11.6 MW @ 359 psi
12/14/2020 | 01:50 | 02:00 | 0.17 | 3090 | 3149 | 59 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3090.00 t/3149.00, w/WOB 20,Flow 420.00, RPM 30.00, Press 1500.00, Tq 7500.00, ROP 354.00
12/14/2020 | 02:00 | 02:10 | 0.17 | 3149 | 3149 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 02:10 | 02:20 | 0.17 | 3149 | 3174 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3149.00 t/3174.00, TF , w/WOB 25,Flow 500, Press 1500.00, Tq 0, ROP 150.00
12/14/2020 | 02:20 | 02:35 | 0.25 | 3174 | 3243 | 69 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3174.00 t/3243.00, w/WOB 28,Flow 500, RPM 40, Press 1500.00, Tq 7500.00, ROP 276.00
12/14/2020 | 02:35 | 02:45 | 0.17 | 3243 | 3243 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 02:45 | 02:50 | 0.08 | 3243 | 3258 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3243.00 t/3258.00, TF , w/WOB 25,Flow 680, Press 2900, Tq 0, ROP 180.00
12/14/2020 | 02:50 | 02:55 | 0.08 | 3258 | 3336 | 78 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3258.00 t/3336.00, w/WOB 28,Flow 680, RPM 80, Press 3100, Tq 8200, ROP 936.00
12/14/2020 | 02:55 | 03:00 | 0.08 | 3336 | 3336 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 03:00 | 03:05 | 0.08 | 3336 | 3430 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3336.00 t/3430.00, w/WOB 35,Flow 750, RPM 80.00, Press 3700, Tq 12000, ROP 1128.00
12/14/2020 | 03:05 | 03:10 | 0.08 | 3430 | 3430 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 03:10 | 03:20 | 0.17 | 3430 | 3524 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3430.00 t/3524.00, w/WOB 35,Flow 750, RPM 80.00, Press 3700, Tq 12000, ROP 564.00
12/14/2020 | 03:20 | 03:25 | 0.08 | 3524 | 3524 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 03:25 | 03:32 | 0.12 | 3524 | 3617 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3524.00 t/3617.00, w/WOB 35,Flow 750, RPM 80.00, Press 3700, Tq 12000, ROP 797.14
12/14/2020 | 03:32 | 03:38 | 0.1 | 3617 | 3617 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 03:38 | 03:40 | 0.03 | 3617 | 3625 | 8 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3617.00 t/3625.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 240.00
12/14/2020 | 03:40 | 03:50 | 0.17 | 3625 | 3640 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3625.00 t/3640.00, TF , w/WOB 20,Flow 750.00, Press 3700.00, Tq 0, ROP 90.00
12/14/2020 | 03:50 | 03:55 | 0.08 | 3640 | 3711 | 71 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3640.00 t/3711.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 852.00
12/14/2020 | 03:55 | 04:00 | 0.08 | 3711 | 3711 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 04:00 | 04:08 | 0.13 | 3711 | 3805 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3711.00 t/3805.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 705.00
12/14/2020 | 04:08 | 04:12 | 0.07 | 3805 | 3805 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 04:12 | 04:15 | 0.05 | 3805 | 3808 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3805.00 t/3808.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 60.00
12/14/2020 | 04:15 | 04:19 | 0.07 | 3808 | 3823 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3808.00 t/3823.00, TF , w/WOB 20,Flow 750.00, Press 3400, Tq 0, ROP 225.00
12/14/2020 | 04:19 | 04:25 | 0.1 | 3823 | 3898 | 75 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3823.00 t/3898.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 750.00
12/14/2020 | 04:25 | 04:30 | 0.08 | 3898 | 3898 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 04:30 | 04:38 | 0.13 | 3898 | 3992 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3898.00 t/3992.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 705.00
12/14/2020 | 04:38 | 04:44 | 0.1 | 3992 | 3992 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 04:44 | 04:45 | 0.02 | 3992 | 3998 | 6 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3992.00 t/3998.00, w/WOB 35.00,Flow 750.00, RPM 80.00, Press 3700.00, Tq 12000.00, ROP 360.00
12/14/2020 | 04:45 | 04:50 | 0.08 | 3998 | 4010 | 12 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3998.00 t/4010.00, TF , w/WOB 20,Flow 750.00, Press 3400, Tq 0, ROP 144.00
12/14/2020 | 04:50 | 04:58 | 0.13 | 4010 | 4085 | 75 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4010.00 t/4085.00, w/WOB 35,Flow 750.00, RPM 80, Press 3700, Tq 12500, ROP 562.50
12/14/2020 | 04:58 | 05:02 | 0.07 | 4085 | 4085 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 05:02 | 05:08 | 0.1 | 4085 | 4179 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4085.00 t/4179.00, w/WOB 34,Flow 750.00, RPM 80.00, Press 3800, Tq 12500.00, ROP 940.00
12/14/2020 | 05:08 | 05:12 | 0.07 | 4179 | 4179 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 05:12 | 05:19 | 0.12 | 4179 | 4273 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4179.00 t/4273.00, w/WOB 34,Flow 750.00, RPM 80.00, Press 3800, Tq 13000, ROP 805.71
12/14/2020 | 05:19 | 05:22 | 0.05 | 4273 | 4273 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 05:22 | 05:30 | 0.13 | 4273 | 4367 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4273.00 t/4367.00, w/WOB 36,Flow 750.00, RPM 80.00, Press 3800.00, Tq 13000.00, ROP 705.00
12/14/2020 | 05:30 | 05:34 | 0.07 | 4367 | 4367 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 05:34 | 05:36 | 0.03 | 4367 | 4374 | 7 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4367.00 t/4374.00, w/WOB 36.00,Flow 750.00, RPM 80.00, Press 3800.00, Tq 13000.00, ROP 210.00
12/14/2020 | 05:36 | 05:42 | 0.1 | 4374 | 4386 | 12 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/4374.00 t/4386.00, TF , w/WOB 18,Flow 750.00, Press 3500, Tq 0, ROP 120.00
12/14/2020 | 05:42 | 05:48 | 0.1 | 4386 | 4461 | 75 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4386.00 t/4461.00, w/WOB 36.00,Flow 750.00, RPM 80.00, Press 3800.00, Tq 13000.00, ROP 750.00
12/14/2020 | 05:48 | 05:52 | 0.07 | 4461 | 4461 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 05:52 | 06:04 | 0.2 | 4461 | 4553 | 92 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4461.00 t/4553.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 460.00
12/14/2020 | 06:04 | 06:10 | 0.1 | 4553 | 4553 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 06:10 | 06:17 | 0.12 | 4553 | 4647 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4553.00 t/4647.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 805.71
12/14/2020 | 06:17 | 06:22 | 0.08 | 4647 | 4647 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 06:22 | 06:24 | 0.03 | 4647 | 4660 | 13 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4647.00 t/4660.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 390.00
12/14/2020 | 06:24 | 06:32 | 0.13 | 4660 | 4680 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/4660.00 t/4680.00, TF , w/WOB 18.00,Flow 800, Press 4200, Tq 0.00, ROP 150.00
12/14/2020 | 06:32 | 06:38 | 0.1 | 4680 | 4742 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4680.00 t/4742.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 620.00
12/14/2020 | 06:38 | 06:42 | 0.07 | 4742 | 4742 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 06:42 | 06:48 | 0.1 | 4742 | 4837 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4742.00 t/4837.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 950.00
12/14/2020 | 06:48 | 06:54 | 0.1 | 4837 | 4837 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 06:54 | 06:59 | 0.08 | 4837 | 4931 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4837.00 t/4931.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 1128.00
12/14/2020 | 06:59 | 07:05 | 0.1 | 4931 | 4931 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 07:05 | 07:11 | 0.1 | 4931 | 5025 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4931.00 t/5025.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 940.00
12/14/2020 | 07:11 | 07:15 | 0.07 | 5025 | 5025 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 07:15 | 07:23 | 0.13 | 5025 | 5118 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5025.00 t/5118.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 697.50
12/14/2020 | 07:23 | 07:28 | 0.08 | 5118 | 5118 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 07:28 | 07:36 | 0.13 | 5118 | 5213 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5118.00 t/5213.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 712.50
12/14/2020 | 07:36 | 07:40 | 0.07 | 5213 | 5213 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 07:40 | 07:42 | 0.03 | 5213 | 5225 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5213.00 t/5225.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 360.00
12/14/2020 | 07:42 | 07:51 | 0.15 | 5225 | 5245 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5225.00 t/5245.00, TF , w/WOB 18.00,Flow 800, Press 4200, Tq 0.00, ROP 133.33
12/14/2020 | 07:51 | 07:57 | 0.1 | 5245 | 5307 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5245.00 t/5307.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 13000.00, ROP 620.00
12/14/2020 | 07:57 | 08:02 | 0.08 | 5307 | 5307 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 08:02 | 08:10 | 0.13 | 5307 | 5401 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5307.00 t/5401.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 16000, ROP 705.00
12/14/2020 | 08:10 | 08:15 | 0.08 | 5401 | 5401 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 08:15 | 08:21 | 0.1 | 5401 | 5494 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5401.00 t/5494.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 16000, ROP 930.00
12/14/2020 | 08:21 | 08:26 | 0.08 | 5494 | 5494 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 08:26 | 08:34 | 0.13 | 5494 | 5588 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5494.00 t/5588.00, w/WOB 40,Flow 800, RPM 80.00, Press 4700, Tq 16000, ROP 705.00
12/14/2020 | 08:34 | 08:40 | 0.1 | 5588 | 5588 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 08:40 | 08:46 | 0.1 | 5588 | 5682 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5588.00 t/5682.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 940.00
12/14/2020 | 08:46 | 08:51 | 0.08 | 5682 | 5682 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 08:51 | 08:56 | 0.08 | 5682 | 5695 | 13 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5682.00 t/5695.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 156.00
12/14/2020 | 08:56 | 09:12 | 0.27 | 5695 | 5725 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5695.00 t/5725.00, TF 0.00, w/WOB 20.00,Flow 800.00, Press 4200.00, Tq 0.00, ROP 112.50
12/14/2020 | 09:12 | 09:21 | 0.15 | 5725 | 5775 | 50 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5725.00 t/5775.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 333.33
12/14/2020 | 09:21 | 09:26 | 0.08 | 5775 | 5775 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 09:26 | 09:28 | 0.03 | 5775 | 5785 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5775.00 t/5785.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 300.00
12/14/2020 | 09:28 | 09:47 | 0.32 | 5785 | 5810 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5785.00 t/5810.00, TF -30.00, w/WOB 20.00,Flow 800.00, Press 4200.00, Tq 0.00, ROP 78.95
12/14/2020 | 09:47 | 09:58 | 0.18 | 5810 | 5869 | 59 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5810.00 t/5869.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 321.82
12/14/2020 | 09:58 | 10:03 | 0.08 | 5869 | 5869 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 10:03 | 10:17 | 0.23 | 5869 | 5964 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5869.00 t/5964.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 407.14
12/14/2020 | 10:17 | 10:22 | 0.08 | 5964 | 5964 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 10:22 | 10:33 | 0.18 | 5964 | 6058 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5964.00 t/6058.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 512.73
12/14/2020 | 10:33 | 10:38 | 0.08 | 6058 | 6058 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 10:38 | 10:50 | 0.2 | 6058 | 6152 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6058.00 t/6152.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 470.00
12/14/2020 | 10:50 | 10:55 | 0.08 | 6152 | 6152 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 10:55 | 11:00 | 0.08 | 6152 | 6165 | 13 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6152.00 t/6165.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 156.00
12/14/2020 | 11:00 | 11:26 | 0.43 | 6165 | 6190 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6165.00 t/6190.00, TF , w/WOB 40.00,Flow 800.00, Press 4700.00, Tq 16000.00, ROP 57.69
12/14/2020 | 11:26 | 11:35 | 0.15 | 6190 | 6246 | 56 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6190.00 t/6246.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 373.33
12/14/2020 | 11:35 | 11:40 | 0.08 | 6246 | 6246 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 11:40 | 11:57 | 0.28 | 6246 | 6340 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6246.00 t/6340.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 331.76
12/14/2020 | 11:57 | 12:02 | 0.08 | 6340 | 6340 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 12:02 | 12:14 | 0.2 | 6340 | 6433 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6340.00 t/6433.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 465.00
12/14/2020 | 12:14 | 12:20 | 0.1 | 6433 | 6433 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 12:20 | 12:31 | 0.18 | 6433 | 6528 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6433.00 t/6528.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 518.18
12/14/2020 | 12:31 | 12:36 | 0.08 | 6528 | 6528 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 12:36 | 12:49 | 0.22 | 6528 | 6623 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6528.00 t/6623.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 438.46
12/14/2020 | 12:49 | 12:55 | 0.1 | 6623 | 6623 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 12:55 | 13:05 | 0.17 | 6623 | 6716 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6623.00 t/6716.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 558.00
12/14/2020 | 13:05 | 13:10 | 0.08 | 6716 | 6716 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 13:10 | 13:22 | 0.2 | 6716 | 6808 | 92 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6716.00 t/6808.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 460.00
12/14/2020 | 13:22 | 13:27 | 0.08 | 6808 | 6808 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 13:27 | 13:41 | 0.23 | 6808 | 6903 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6808.00 t/6903.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4700.00, Tq 16000.00, ROP 407.14
12/14/2020 | 13:41 | 13:46 | 0.08 | 6903 | 6903 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 13:46 | 14:08 | 0.37 | 6903 | 6997 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6903.00 t/6997.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900, Tq 18000, ROP 256.36
12/14/2020 | 14:08 | 14:13 | 0.08 | 6997 | 6997 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 14:13 | 14:24 | 0.18 | 6997 | 7090 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6997.00 t/7090.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900, Tq 18000, ROP 507.27
12/14/2020 | 14:24 | 14:30 | 0.1 | 7090 | 7090 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 14:30 | 14:33 | 0.05 | 7090 | 7100 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7090.00 t/7100.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900, Tq 18000, ROP 200.00
12/14/2020 | 14:33 | 15:00 | 0.45 | 7100 | 7140 | 40 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7100.00 t/7140.00, TF , w/WOB 20,Flow 800.00, Press 4900, Tq 0, ROP 88.89
12/14/2020 | 15:00 | 15:10 | 0.17 | 7140 | 7184 | 44 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7140.00 t/7184.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900, Tq 18000, ROP 264.00
12/14/2020 | 15:10 | 15:15 | 0.08 | 7184 | 7184 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 15:15 | 15:26 | 0.18 | 7184 | 7278 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7184.00 t/7278.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900, Tq 18000, ROP 512.73
12/14/2020 | 15:26 | 15:31 | 0.08 | 7278 | 7278 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 15:31 | 15:43 | 0.2 | 7278 | 7372 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7278.00 t/7372.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900.00, Tq 18000.00, ROP 470.00
12/14/2020 | 15:43 | 15:49 | 0.1 | 7372 | 7372 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 15:49 | 15:52 | 0.05 | 7372 | 7380 | 8 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7372.00 t/7380.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900.00, Tq 18000.00, ROP 160.00
12/14/2020 | 15:52 | 16:13 | 0.35 | 7380 | 7410 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7380.00 t/7410.00, TF , w/WOB 20,Flow 800, Press 4300, Tq 0, ROP 85.71
12/14/2020 | 16:13 | 16:26 | 0.22 | 7410 | 7466 | 56 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7410.00 t/7466.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900.00, Tq 18000.00, ROP 258.46
12/14/2020 | 16:26 | 16:30 | 0.07 | 7466 | 7466 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 16:30 | 16:43 | 0.22 | 7466 | 7560 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7466.00 t/7560.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900.00, Tq 18000.00, ROP 433.85
12/14/2020 | 16:43 | 16:48 | 0.08 | 7560 | 7560 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 16:48 | 16:50 | 0.03 | 7560 | 7565 | 5 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7560.00 t/7565.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4900.00, Tq 18000.00, ROP 150.00
12/14/2020 | 16:50 | 17:08 | 0.3 | 7565 | 7590 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7565.00 t/7590.00, TF , w/WOB 20,Flow 800.00, Press 4300, Tq 0, ROP 83.33
12/14/2020 | 17:08 | 17:20 | 0.2 | 7590 | 7654 | 64 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7590.00 t/7654.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 320.00
12/14/2020 | 17:20 | 17:28 | 0.13 | 7654 | 7654 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 17:28 | 17:35 | 0.12 | 7654 | 7748 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7654.00 t/7748.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 805.71
12/14/2020 | 17:35 | 17:42 | 0.12 | 7748 | 7748 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 17:42 | 17:44 | 0.03 | 7748 | 7753 | 5 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7748.00 t/7753.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 150.00
12/14/2020 | 17:44 | 18:03 | 0.32 | 7753 | 7788 | 35 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7753.00 t/7788.00, TF , w/WOB 28.00,Flow 800.00, Press 4500.00, Tq 0, ROP 110.53
12/14/2020 | 18:03 | 18:18 | 0.25 | 7788 | 7841 | 53 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7788.00 t/7841.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 212.00
12/14/2020 | 18:18 | 18:23 | 0.08 | 7841 | 7841 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 18:23 | 18:38 | 0.25 | 7841 | 7935 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7841.00 t/7935.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 376.00
12/14/2020 | 18:38 | 18:44 | 0.1 | 7935 | 7935 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 18:44 | 18:45 | 0.02 | 7935 | 7938 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7935.00 t/7938.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 180.00
12/14/2020 | 18:45 | 19:06 | 0.35 | 7938 | 7968 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7938.00 t/7968.00, TF , w/WOB 28.00,Flow 800.00, Press 4500.00, Tq 0, ROP 85.71
12/14/2020 | 19:06 | 19:18 | 0.2 | 7968 | 8029 | 61 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7968.00 t/8029.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4500.00, Tq 20000.00, ROP 305.00
12/14/2020 | 19:18 | 19:22 | 0.07 | 8029 | 8029 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 19:22 | 19:50 | 0.47 | 8029 | 8122 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8029.00 t/8122.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 20000.00, ROP 199.29
12/14/2020 | 19:50 | 19:55 | 0.08 | 8122 | 8122 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 19:55 | 20:10 | 0.25 | 8122 | 8215 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8122.00 t/8215.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 20000.00, ROP 372.00
12/14/2020 | 20:10 | 20:15 | 0.08 | 8215 | 8215 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 20:15 | 20:28 | 0.22 | 8215 | 8310 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8215.00 t/8310.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 20000.00, ROP 438.46
12/14/2020 | 20:28 | 20:32 | 0.07 | 8310 | 8310 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 20:32 | 20:58 | 0.43 | 8310 | 8350 | 40 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8310.00 t/8350.00, TF , w/WOB 32,Flow 800.00, Press 4400, Tq 0, ROP 92.31
12/14/2020 | 20:58 | 21:15 | 0.28 | 8350 | 8404 | 54 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8350.00 t/8404.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 20000.00, ROP 190.59
12/14/2020 | 21:15 | 21:20 | 0.08 | 8404 | 8404 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 21:20 | 21:35 | 0.25 | 8404 | 8498 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8404.00 t/8498.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000, ROP 376.00
12/14/2020 | 21:35 | 21:40 | 0.08 | 8498 | 8498 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 21:40 | 21:55 | 0.25 | 8498 | 8593 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8498.00 t/8593.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000, ROP 380.00
12/14/2020 | 21:55 | 22:00 | 0.08 | 8593 | 8593 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 22:00 | 22:20 | 0.33 | 8593 | 8638 | 45 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8593.00 t/8638.00, TF , w/WOB 32,Flow 800.00, Press 4400, Tq 0, ROP 135.00
12/14/2020 | 22:20 | 22:32 | 0.2 | 8638 | 8686 | 48 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8638.00 t/8686.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000, ROP 240.00
12/14/2020 | 22:32 | 22:37 | 0.08 | 8686 | 8686 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 22:37 | 22:53 | 0.27 | 8686 | 8780 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8686.00 t/8780.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000, ROP 352.50
12/14/2020 | 22:53 | 22:58 | 0.08 | 8780 | 8780 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 22:58 | 23:26 | 0.47 | 8780 | 8810 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8780.00 t/8810.00, TF , w/WOB 35,Flow 700, Press 4000, Tq 0, ROP 64.29
12/14/2020 | 23:26 | 23:48 | 0.37 | 8810 | 8875 | 65 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8810.00 t/8875.00, w/WOB 28.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000, ROP 177.27
12/14/2020 | 23:48 | 23:55 | 0.12 | 8875 | 8875 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/14/2020 | 23:55 | 23:57 | 0.03 | 8875 | 8878 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8875.00 t/8878.00, w/WOB 30,Flow 800.00, RPM 80.00, Press 4800, Tq 22000, ROP 90.00
12/14/2020 | 23:57 | 24:00 | 0.05 | 8878 | 8880 | 2 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8878.00 t/8880.00, TF , w/WOB 35,Flow 800.00, Press 4400, Tq 0, ROP 40.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_15_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/15/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 35000
|  |  |  | 24hr Summary: |  | Drilling Intermediate t/ Section TD; Circulate Hole Clean; TOH
|  |  |  | 24hr Lookahead: |  | Skid Rig t/ Fat Tire A 1H
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 8880 |  | 3080 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 32 | PV: | 11
End Depth (Usft): |  | 10192 |  | 10192 |  | OD (in): |  |  |  | 300: | 21 | YP: | 10
Total Drilled (Usft): |  | 1312 |  | 7112 |  | Weight (ft/lbs): |  |  |  | 200: | 17 | Viscosity: | 51
Slide Drilled (Usft): |  | 259 |  | 750 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 1053 |  | 6362 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 9.40
Drlg/Circ Hrs: |  | 9.02 / 13.47 |  | 25.85 / 14.47 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 4.62 |  | 9.63 |  | SN: |  | 54300 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 4.4 |  | 16.22 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 239.32 / 56.10 |  | 392.31 / 77.85 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 51 |  | Grade In: |  | New
% Slide: |  | 19.74 |  | 10.55 |  | Grade Out: |  | 0-1-CT-G-X-I-NO-TD
% Rotary: |  | 80.26 |  | 89.45 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  |  |  | 8 | 2 |  |  |  |  | 37.67 |  | 39.17
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.03
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.14
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.05
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.59
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 111.71
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.49
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.53
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 576.83
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.63
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.43 |  | 2679.06
2679.06
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800049 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
8900 | 13.43 | 211.27 | 8629.44 | -1620.53 | -1280.9 | 2.95 |  | -142.34 | -706.7 | -2.22 |  | -7.78 | 94
8995 | 6.58 | 193.06 | 8722.96 | -1635.28 | -1287.87 | 7.86 |  | -164 | -715.6 | -7.21 |  | -19.17 | 95
9089 | 4.59 | 182.53 | 8816.51 | -1644.28 | -1289.25 | 2.37 |  | -157.93 | -722.54 | -2.12 |  | -11.2 | 94
9184 | 2.93 | 173.19 | 8911.3 | -1650.49 | -1289.13 | 1.86 |  | -164.37 | -727.88 | -1.75 |  | -9.83 | 95
9278 | 1.83 | 135.39 | 9005.23 | -1653.95 | -1287.79 | 1.98 |  | -142.91 | -731.53 | -1.17 |  | -40.21 | 94
9371 | 2.27 | 123.2 | 9098.17 | -1656.01 | -1285.21 | 0.66 |  | -50.94 | -734.64 | 0.47 |  | -13.11 | 93
9465 | 2.86 | 110.72 | 9192.07 | -1657.86 | -1281.46 | 0.86 |  | -49.78 | -738.18 | 0.63 |  | -13.28 | 94
9560 | 3.29 | 103.07 | 9286.94 | -1659.32 | -1276.59 | 0.62 |  | -47.52 | -741.98 | 0.45 |  | -8.05 | 95
9653 | 1.32 | 129.96 | 9379.86 | -1660.61 | -1273.17 | 2.36 |  | 164.22 | -744.88 | -2.12 |  | 28.91 | 93
9747 | 1.49 | 268.47 | 9473.85 | -1661.34 | -1273.56 | 2.8 |  | 157.94 | -745.29 | 0.18 |  | 0 | 94
9841 | 2.62 | 280.99 | 9567.78 | -1660.96 | -1276.89 | 1.29 |  | 28 | -743.22 | 1.2 |  | 0 | 94
9936 | 3.32 | 292.9 | 9662.66 | -1659.48 | -1281.55 | 0.98 |  | 47.45 | -739.51 | 0.74 |  | 12.54 | 95
10029 | 8.33 | 322.35 | 9755.16 | -1653.09 | -1288.15 | 6.1 |  | 46.06 | -730.61 | 5.39 |  | 31.67 | 93
10123 | 11.12 | 328.26 | 9847.81 | -1639.99 | -1297.08 | 3.15 |  | 22.62 | -714.77 | 2.97 |  | 6.29 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 145.51 | 33.4 | 80 | 213 | 800 | 4673.33 | 4200 | 250 | 313 | 227.33 | 188.67 | 22800 | 10000
Run | 275.13 | 33.33 | 78.41 | 207 | 776.11 | 4346.9 | 3723.89 | 250 | 228.04 | 183.96 | 159.78 | 16485.23 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/15/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/15/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/15/2020 | 00:00 | 00:32 | 0.53 | 8880 | 8918 | 38 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8880.00 t/8918.00, TF , w/WOB 35,Flow 800.00, Press 4400, Tq 0, ROP 71.25
12/15/2020 | 00:32 | 00:44 | 0.2 | 8918 | 8969 | 51 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8918.00 t/8969.00, w/WOB 32.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000.00, ROP 255.00
12/15/2020 | 00:44 | 01:00 | 0.27 | 8969 | 8969 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 01:00 | 01:32 | 0.53 | 8969 | 9014 | 45 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8969.00 t/9014.00, TF , w/WOB 35,Flow 800.00, Press 4400.00, Tq 0, ROP 84.38
12/15/2020 | 01:32 | 01:42 | 0.17 | 9014 | 9064 | 50 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9014.00 t/9064.00, w/WOB 32.00,Flow 800.00, RPM 80.00, Press 4800, Tq 22000.00, ROP 300.00
12/15/2020 | 01:42 | 01:45 | 0.05 | 9064 | 9064 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 01:45 | 01:58 | 0.22 | 9064 | 9158 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9064.00 t/9158.00, w/WOB 32.00,Flow 800.00, RPM 80.00, Press 4800, Tq 23000, ROP 433.85
12/15/2020 | 01:58 | 02:02 | 0.07 | 9158 | 9158 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 02:02 | 02:05 | 0.05 | 9158 | 9167 | 9 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9158.00 t/9167.00, w/WOB 32.00,Flow 800.00, RPM 80.00, Press 4800, Tq 23000, ROP 180.00
12/15/2020 | 02:05 | 02:20 | 0.25 | 9167 | 9185 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9167.00 t/9185.00, TF , w/WOB 28,Flow 800.00, Press 4400.00, Tq 0, ROP 72.00
12/15/2020 | 02:20 | 02:33 | 0.22 | 9185 | 9253 | 68 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9185.00 t/9253.00, w/WOB 30,Flow 800.00, RPM 80.00, Press 4800, Tq 23000, ROP 313.85
12/15/2020 | 02:33 | 02:37 | 0.07 | 9253 | 9253 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 02:37 | 02:38 | 0.02 | 9253 | 9257 | 4 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9253.00 t/9257.00, w/WOB 30,Flow 800.00, RPM 80.00, Press 4800, Tq 23000, ROP 240.00
12/15/2020 | 02:38 | 02:54 | 0.27 | 9257 | 9275 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9257.00 t/9275.00, TF , w/WOB 28,Flow 800.00, Press 4400.00, Tq 0, ROP 67.50
12/15/2020 | 02:54 | 03:08 | 0.23 | 9275 | 9347 | 72 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9275.00 t/9347.00, w/WOB 30,Flow 800.00, RPM 80.00, Press 4800, Tq 23000, ROP 308.57
12/15/2020 | 03:08 | 03:12 | 0.07 | 9347 | 9347 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 03:12 | 03:28 | 0.27 | 9347 | 9440 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9347.00 t/9440.00, w/WOB 30,Flow 800.00, RPM 80.00, Press 4800, Tq 23000, ROP 348.75
12/15/2020 | 03:28 | 03:30 | 0.03 | 9440 | 9440 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 03:30 | 03:49 | 0.32 | 9440 | 9534 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9440.00 t/9534.00, w/WOB 40,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 296.84
12/15/2020 | 03:49 | 03:52 | 0.05 | 9534 | 9534 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 03:52 | 04:21 | 0.48 | 9534 | 9629 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9534.00 t/9629.00, w/WOB 42,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 196.55
12/15/2020 | 04:21 | 04:24 | 0.05 | 9629 | 9629 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 04:24 | 04:56 | 0.53 | 9629 | 9655 | 26 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9629.00 t/9655.00, TF , w/WOB 45,Flow 800.00, Press 4500, Tq 0, ROP 48.75
12/15/2020 | 04:56 | 05:17 | 0.35 | 9655 | 9722 | 67 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9655.00 t/9722.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 191.43
12/15/2020 | 05:17 | 05:20 | 0.05 | 9722 | 9722 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 05:20 | 05:21 | 0.02 | 9722 | 9726 | 4 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9722.00 t/9726.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 240.00
12/15/2020 | 05:21 | 06:04 | 0.72 | 9726 | 9742 | 16 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9726.00 t/9742.00, TF , w/WOB 45.00,Flow 800.00, Press 4500.00, Tq 0.00, ROP 22.33
12/15/2020 | 06:04 | 06:23 | 0.32 | 9742 | 9816 | 74 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9742.00 t/9816.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 233.68
12/15/2020 | 06:23 | 06:28 | 0.08 | 9816 | 9816 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 06:28 | 06:50 | 0.37 | 9816 | 9910 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9816.00 t/9910.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 256.36
12/15/2020 | 06:50 | 06:55 | 0.08 | 9910 | 9910 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 06:55 | 07:00 | 0.08 | 9910 | 9934 | 24 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9910.00 t/9934.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 288.00
12/15/2020 | 07:00 | 08:00 | 1 | 9934 | 9994 | 60 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9934.00 t/9994.00, TF , w/WOB 45.00,Flow 800.00, Press 4500.00, Tq 0.00, ROP 60.00
12/15/2020 | 08:00 | 08:06 | 0.1 | 9994 | 10005 | 11 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9994.00 t/10005.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 110.00
12/15/2020 | 08:06 | 08:10 | 0.07 | 10005 | 10005 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 08:10 | 08:30 | 0.33 | 10005 | 10060 | 55 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10005.00 t/10060.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 165.00
12/15/2020 | 08:30 | 09:17 | 0.78 | 10060 | 10098 | 38 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10060.00 t/10098.00, TF , w/WOB 45.00,Flow 800.00, Press 4500.00, Tq 0.00, ROP 48.51
12/15/2020 | 09:17 | 09:22 | 0.08 | 10098 | 10098 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 09:22 | 10:02 | 0.67 | 10098 | 10192 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10098.00 t/10192.00, w/WOB 42.00,Flow 800.00, RPM 80.00, Press 4800.00, Tq 23000.00, ROP 141.00
12/15/2020 | 10:02 | 10:07 | 0.08 | 10192 | 10192 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
12/15/2020 | 10:07 | 23:35 | 13.47 | 10192 | 10192 | 0 | INT | 2: BHA #2 (Intermediate) | 5D | Circulate Out Gas
12/15/2020 | 23:35 | 24:00 | 0.42 | 10192 | 10192 | 0 | INT | 2: BHA #2 (Intermediate) | 6B | TOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_16_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/16/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 42250
|  |  |  | 24hr Summary: |  | TOH; Rack Back BHA; Standby for Casing Ops
|  |  |  | 24hr Lookahead: |  | Skid Rig t/ Fat Tire A 1H
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10192 |  | 3080 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 32 | PV: | 11
End Depth (Usft): |  | 10192 |  | 10192 |  | OD (in): |  |  |  | 300: | 21 | YP: | 10
Total Drilled (Usft): |  |  |  | 7112 |  | Weight (ft/lbs): |  |  |  | 200: | 17 | Viscosity: | 51
Slide Drilled (Usft): |  |  |  | 750 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  |  |  | 6362 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 9.40
Drlg/Circ Hrs: |  |  |  | 25.85 / 14.47 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  |  |  | 9.63 |  | SN: |  | 54300 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  |  |  | 16.22 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 392.31 / 77.85 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 6 |  | 57 |  | Grade In: |  | New
% Slide: |  |  |  | 10.55 |  | Grade Out: |  | 0-1-CT-G-X-I-NO-TD
% Rotary: |  |  |  | 89.45 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  |  |  | 8 | 2 |  |  |  |  | 37.67 |  | 39.17
8" - NMPDC |  |  |  | 8 | 3.25 |  |  |  |  | 8.86 |  | 48.03
UBHO Sub |  |  |  | 7.75 | 2.813 |  |  |  |  | 3.11 |  | 51.14
8" - NMDC |  |  |  | 7.375 | 3.25 |  |  |  |  | 28.91 |  | 80.05
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.54 |  | 109.59
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.12 |  | 111.71
2 Stands of 6 1/2" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 186.78 |  | 298.49
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.625 | 2.5 |  |  |  |  | 3.04 |  | 301.53
9- Joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 275.3 |  | 576.83
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2071.8 |  | 2648.63
NOV- Safety Join / Agitator / Shock Sub |  |  |  | 6.75 | 2.5 |  |  |  |  | 30.43 |  | 2679.06
2679.06
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800049 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.81 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 33.4 | 80 | 213 | 800 | 4673.33 | 4200 | 250 | 313 | 227.33 | 188.67 | 22800 | 10000
Run | 275.13 | 33.33 | 78.41 | 207 | 776.11 | 4346.9 | 3723.89 | 250 | 228.04 | 183.96 | 159.78 | 16485.23 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/16/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/16/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/16/2020 | 00:00 | 05:40 | 5.67 | 10192 | 10192 | 0 | INT | 2: BHA #2 (Intermediate) | 6B | TOH @ Section TD
12/16/2020 | 05:40 | 06:00 | 0.33 | 10192 | 10192 | 0 | INT | 2: BHA #2 (Intermediate) | 6P | L/D MWD Tool; Drain Motor; Break Bit; Rack Back BHA
12/16/2020 | 06:00 | 24:00 | 18 | 10192 | 10192 | 0 | INT |  | 26A | Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_28_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/28/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17750 |  |  | Well Cost($): |  | 60000
|  |  |  | 24hr Summary: |  | Standby t/ Nipple Up and Test BOPs; P/U BHA #3; TIH; Attempt t/ Build Curve; TOH t/ Inspect BHA of Float Rubber
|  |  |  | 24hr Lookahead: |  | TOH; Inspect BHA; TIH; Build and Land Curve
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10192 |  | 10192 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 32 | PV: | 11
End Depth (Usft): |  | 10209 |  | 10209 |  | OD (in): |  |  |  | 300: | 21 | YP: | 10
Total Drilled (Usft): |  | 17 |  | 17 |  | Weight (ft/lbs): |  |  |  | 200: | 17 | Viscosity: | 51
Slide Drilled (Usft): |  | 7 |  | 7 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 10 |  | 10 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 9.40
Drlg/Circ Hrs: |  | 0.50 / 5.95 |  | 0.50 / 5.95 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 0.42 |  | 0.42 |  | SN: |  | 13522000 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 0.08 |  | 0.08 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 120.00 / 16.80 |  | 120.00 / 16.80 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 15.33 |  | 15.33 |  | Grade In: |  | New
% Slide: |  | 41.18 |  | 41.18 |  | Grade Out:
% Rotary: |  | 58.82 |  | 58.82 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | 5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 36.25
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 46.37
UBHO Sub |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.68 |  | 50.05
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 80.66
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 111.82
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 138.2
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 141.51
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2698.1
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2721.96
2721.96
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250025 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.01 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10123 | 11.12 | 328.26 | 9847.81 | -1639.99 | -1297.08 | 3.15 |  | 22.62 | -714.77 | 2.97 |  | 6.29 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 14.17 | 33.4 | 80 | 792 | 800 | 4673.33 | 4200 | 250 | 313 | 227.33 | 188.67 | 22800 | 10000
Run | 14.17 | 33.33 | 78.41 | 769 | 776.11 | 4346.9 | 3723.89 | 250 | 228.04 | 183.96 | 159.78 | 16485.23 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/28/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/28/2020 |  | 4 |  | 100 |  | 4 | 400
5 Premium Motor Stator Reline |  |  |  |  | 12/28/2020 |  | 6 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/28/2020 | 00:00 | 07:20 | 7.33 | 10192 | 10192 | 0 | CRV |  | 26B | Standby t/ Nipple Up and Test BOPs
12/28/2020 | 07:20 | 08:40 | 1.33 | 10192 | 10192 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6O | P/U BHA #3
12/28/2020 | 08:40 | 09:00 | 0.33 | 10192 | 10192 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 5A | Surface test MWD and motor (OK)
12/28/2020 | 09:00 | 14:08 | 5.13 | 10192 | 10192 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6A | Trip in hole to 9986
12/28/2020 | 14:08 | 14:50 | 0.7 | 10192 | 10192 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 5A | Drlg Out Shoe Track and Float Equipment
12/28/2020 | 14:50 | 14:55 | 0.08 | 10192 | 10202 | 10 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10192.00 t/10202.00, w/WOB 10,Flow 275, RPM 40, Press 2400, Tq 10000, ROP 120.00
12/28/2020 | 14:55 | 15:55 | 1 | 10202 | 10202 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 5A | Circulating; Expected rubber around BHA
12/28/2020 | 15:55 | 17:00 | 1.08 | 10202 | 10202 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6F | TOH 3 stands t/ attempt to knock off rubber from BHA
12/28/2020 | 17:00 | 17:40 | 0.67 | 10202 | 10202 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 15D | FIT t/ 1805 psi - 13 EMW
12/28/2020 | 17:40 | 18:05 | 0.42 | 10202 | 10209 | 7 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10202.00 t/10209.00, TF , w/WOB 45,Flow 275.00, Press 2200, Tq 0, ROP 16.80
12/28/2020 | 18:05 | 22:00 | 3.92 | 10209 | 10209 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 5A | Circulate and Prepare t/ POOH; TF not reacting to rotary turn or diff, rubber still around BHA
12/28/2020 | 22:00 | 24:00 | 2 | 10209 | 10209 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6B | TOH t/ inspect BHA of float rubber
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_29_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/29/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 69850
|  |  |  | 24hr Summary: |  | TOH t/ Inspect BHA of Rubber; TIH; Resume Building Curve
|  |  |  | 24hr Lookahead: |  | Build and Land Curve; Drill Lateral Section
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10209 |  | 10209 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 32 | PV: | 11
End Depth (Usft): |  | 11095 |  | 11095 |  | OD (in): |  |  |  | 300: | 21 | YP: | 10
Total Drilled (Usft): |  | 886 |  | 886 |  | Weight (ft/lbs): |  |  |  | 200: | 17 | Viscosity: | 51
Slide Drilled (Usft): |  | 530 |  | 530 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 356 |  | 356 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 9.40
Drlg/Circ Hrs: |  | 8.27 / 1.62 |  | 8.27 / 1.62 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 5.22 |  | 5.22 |  | SN: |  | 13522000 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 3.05 |  | 3.05 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 116.72 / 101.60 |  | 116.72 / 101.60 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 16.67 |  | 16.67 |  | Grade In: |  | New
% Slide: |  | 59.82 |  | 59.82 |  | Grade Out:
% Rotary: |  | 40.18 |  | 40.18 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | 5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 36.25
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 46.37
UBHO Sub |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.68 |  | 50.05
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 80.66
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 111.82
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 138.2
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 141.51
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2698.1
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2721.96
2721.96
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250025 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.01 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10270 | 16.37 | 319.94 | 9990.56 | -1612.05 | -1317.89 | 3.81 |  | -24.72 | -680.07 | 3.57 |  | -5.66 | 147
10364 | 31.15 | 325.93 | 10076.37 | -1581.6 | -1340.16 | 15.91 |  | 12.07 | -642.46 | 15.72 |  | 6.37 | 94
10458 | 31.62 | 328.15 | 10156.62 | -1540.53 | -1366.79 | 1.33 |  | 68.83 | -593.53 | 0.5 |  | 2.36 | 94
10554 | 35.01 | 328.8 | 10236.83 | -1495.58 | -1394.34 | 3.55 |  | 6.28 | -540.81 | 3.53 |  | 0.68 | 96
10649 | 44.92 | 331.49 | 10309.55 | -1442.67 | -1424.54 | 10.59 |  | 10.94 | -479.91 | 10.43 |  | 2.83 | 95
10745 | 58.01 | 331.66 | 10369.23 | -1376.76 | -1460.2 | 13.64 |  | 0.64 | -405.1 | 13.64 |  | 0.18 | 96
10840 | 68.98 | 330.03 | 10411.57 | -1302.66 | -1501.61 | 11.65 |  | -7.95 | -320.3 | 11.55 |  | -1.72 | 95
10934 | 74.06 | 328.73 | 10441.35 | -1225.98 | -1547.01 | 5.56 |  | -13.85 | -231.19 | 5.4 |  | -1.38 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 33.4 | 80 | 792 | 800 | 4673.33 | 4200 | 250 | 313 | 227.33 | 188.67 | 22800 | 10000
Run | 34 | 33.33 | 78.41 | 769 | 776.11 | 4346.9 | 3723.89 | 250 | 228.04 | 183.96 | 159.78 | 16485.23 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 12/29/2020 |  | 8 |  | 2000 |  | 1 | 2000
Directional & MWD / Gamma Service |  |  |  |  | 12/29/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/29/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/29/2020 |  | 7 |  | 600 |  | 1 | 600
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/29/2020 | 00:00 | 06:15 | 6.25 | 10209 | 10209 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6B | TOH t/ Inspect BHA of Rubber
12/29/2020 | 06:15 | 06:40 | 0.42 | 10209 | 10209 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6P | Pull MWD, break bit
12/29/2020 | 06:40 | 07:20 | 0.67 | 10209 | 10209 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 6O | Make up new bit, install MWD
12/29/2020 | 07:20 | 07:30 | 0.17 | 10209 | 10209 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 5A | Surface test MWD and motor
12/29/2020 | 07:30 | 12:23 | 4.88 | 10209 | 10209 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 6A | TIH
12/29/2020 | 12:23 | 13:50 | 1.45 | 10209 | 10209 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 5A | Circulate bottoms up
12/29/2020 | 13:50 | 14:13 | 0.38 | 10209 | 10240 | 31 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10209.00 t/10240.00, TF , w/WOB 35,Flow 350, Press 4100, Tq 0, ROP 80.87
12/29/2020 | 14:13 | 14:23 | 0.17 | 10240 | 10240 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 24A | Connection
12/29/2020 | 14:23 | 15:28 | 1.08 | 10240 | 10336 | 96 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10240.00 t/10336.00, TF , w/WOB 40,Flow 350, Press 4100, Tq 0, ROP 88.62
12/29/2020 | 15:28 | 15:38 | 0.17 | 10336 | 10336 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 15:38 | 16:20 | 0.7 | 10336 | 10401 | 65 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10336.00 t/10401.00, TF , w/WOB 40,Flow 400, Press 4650, Tq 0, ROP 92.86
12/29/2020 | 16:20 | 16:32 | 0.2 | 10401 | 10430 | 29 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/10401.00 t/10430.00, w/WOB 30,Flow 400, RPM 50, Press 4950, Tq 12500, ROP 145.00
12/29/2020 | 16:32 | 16:42 | 0.17 | 10430 | 10430 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 16:42 | 17:11 | 0.48 | 10430 | 10488 | 58 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/10430.00 t/10488.00, w/WOB 30.00,Flow 400.00, RPM 50.00, Press 4950.00, Tq 12500.00, ROP 120.00
12/29/2020 | 17:11 | 17:38 | 0.45 | 10488 | 10524 | 36 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10488.00 t/10524.00, TF , w/WOB 50,Flow 400, Press 4650, Tq 0, ROP 80.00
12/29/2020 | 17:38 | 17:44 | 0.1 | 10524 | 10524 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 17:44 | 18:00 | 0.27 | 10524 | 10549 | 25 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/10524.00 t/10549.00, w/WOB 30,Flow 40, RPM 50, Press 4950, Tq 12500, ROP 93.75
12/29/2020 | 18:00 | 18:36 | 0.6 | 10549 | 10620 | 71 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10549.00 t/10620.00, TF , w/WOB 55,Flow 400, Press 4800, Tq 0.00, ROP 118.33
12/29/2020 | 18:36 | 18:50 | 0.23 | 10620 | 10620 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 18:50 | 19:40 | 0.83 | 10620 | 10705 | 85 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10620.00 t/10705.00, TF , w/WOB 60,Flow 400, Press 4800, Tq 0.00, ROP 102.00
12/29/2020 | 19:40 | 19:48 | 0.13 | 10705 | 10715 | 10 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/10705.00 t/10715.00, w/WOB 30,Flow 400, RPM 50, Press 5000, Tq 14000, ROP 75.00
12/29/2020 | 19:48 | 19:58 | 0.17 | 10715 | 10715 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 19:58 | 20:42 | 0.73 | 10715 | 10811 | 96 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10715.00 t/10811.00, TF , w/WOB 65,Flow 330, Press 3500, Tq 0.00, ROP 130.91
12/29/2020 | 20:42 | 20:55 | 0.22 | 10811 | 10811 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 20:55 | 21:22 | 0.45 | 10811 | 10856 | 45 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/10811.00 t/10856.00, w/WOB 30,Flow 330, RPM 50, Press 3600, Tq 14500, ROP 100.00
12/29/2020 | 21:22 | 21:48 | 0.43 | 10856 | 10906 | 50 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/10856.00 t/10906.00, TF , w/WOB 68,Flow 330, Press 3500, Tq 0.00, ROP 115.38
12/29/2020 | 21:48 | 22:20 | 0.53 | 10906 | 10906 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 22:20 | 23:03 | 0.72 | 10906 | 11000 | 94 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/10906.00 t/11000.00, w/WOB 32,Flow 330, RPM 50, Press 3750, Tq 14500, ROP 131.16
12/29/2020 | 23:03 | 23:12 | 0.15 | 11000 | 11000 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/29/2020 | 23:12 | 24:00 | 0.8 | 11000 | 11095 | 95 | CRV | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11000.00 t/11095.00, w/WOB 68,Flow 330, RPM 0.00, Press 3500, Tq 0.00, ROP 118.75
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_30_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/30/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 79700
|  |  |  | 24hr Summary: |  | Build and Land Curve; Begin Drilling Lateral Section as per plan
|  |  |  | 24hr Lookahead: |  | Drill Lateral Section
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11095 |  | 10209 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 32 | PV: | 11
End Depth (Usft): |  | 12808 |  | 12808 |  | OD (in): |  |  |  | 300: | 21 | YP: | 10
Total Drilled (Usft): |  | 1713 |  | 2599 |  | Weight (ft/lbs): |  |  |  | 200: | 17 | Viscosity: | 51
Slide Drilled (Usft): |  | 253 |  | 783 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 1460 |  | 1816 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 9.40
Drlg/Circ Hrs: |  | 12.83 / 3.17 |  | 21.10 / 4.78 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 4.7 |  | 9.92 |  | SN: |  | 13509568 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 8.13 |  | 11.18 |  | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 138.00 | Fluid Loss / Mud Type: | 9 / WBM
ROP Rot/Slide (Usft/hr): |  | 179.51 / 53.83 |  | 162.38 / 78.96 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 40.67 |  | Grade In: |  | New
% Slide: |  | 14.77 |  | 30.13 |  | Grade Out:
% Rotary: |  | 85.23 |  | 69.87 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | 5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 36.25
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 46.37
UBHO Sub |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.68 |  | 50.05
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 80.66
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 111.82
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 138.2
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 141.51
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2698.1
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2721.96
2721.96
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250025 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.01 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11029 | 74.42 | 331.52 | 10467.16 | -1146.71 | -1592.55 | 2.85 |  | 82.74 | -139.82 | 0.38 |  | 2.94 | 95
11124 | 92.53 | 333.12 | 10477.91 | -1063.46 | -1636.19 | 19.14 |  | 5.13 | -46.06 | 19.06 |  | 1.68 | 95
11218 | 97.01 | 329.75 | 10470.09 | -981.22 | -1680.95 | 5.96 |  | -36.73 | 47.44 | 4.77 |  | -3.59 | 94
11313 | 92.61 | 327.6 | 10462.13 | -900.38 | -1730.16 | 5.15 |  | -153.94 | 142.08 | -4.63 |  | -2.26 | 95
11409 | 91.56 | 326.71 | 10458.64 | -819.78 | -1782.19 | 1.43 |  | -139.72 | 237.99 | -1.09 |  | -0.93 | 96
11503 | 90.93 | 325.9 | 10456.59 | -741.59 | -1834.32 | 1.09 |  | -127.87 | 331.91 | -0.67 |  | -0.86 | 94
11597 | 91.61 | 327 | 10454.51 | -663.28 | -1886.26 | 1.38 |  | 58.26 | 425.83 | 0.72 |  | 1.17 | 94
11691 | 91.68 | 325.77 | 10451.81 | -585.03 | -1938.28 | 1.31 |  | -86.72 | 519.74 | 0.07 |  | -1.31 | 94
11785 | 91.62 | 324.96 | 10449.11 | -507.72 | -1991.68 | 0.86 |  | -94.23 | 613.57 | -0.06 |  | -0.86 | 94
11880 | 90.42 | 326.96 | 10447.41 | -429.01 | -2044.85 | 2.45 |  | 120.95 | 708.47 | -1.26 |  | 2.11 | 95
11975 | 90.16 | 327.15 | 10446.93 | -349.29 | -2096.51 | 0.34 |  | 143.84 | 803.44 | -0.27 |  | 0.2 | 95
12070 | 89.35 | 327.68 | 10447.34 | -269.25 | -2147.67 | 1.02 |  | 146.8 | 898.43 | -0.85 |  | 0.56 | 95
12165 | 88.78 | 327.45 | 10448.89 | -189.08 | -2198.62 | 0.65 |  | -158.03 | 993.41 | -0.6 |  | -0.24 | 95
12262 | 87.69 | 327.52 | 10451.88 | -107.32 | -2250.73 | 1.13 |  | 176.33 | 1090.35 | -1.12 |  | 0.07 | 97
12357 | 88.73 | 327.64 | 10454.84 | -27.17 | -2301.64 | 1.1 |  | 6.58 | 1185.29 | 1.09 |  | 0.13 | 95
12452 | 91.84 | 330.14 | 10454.37 | 54.15 | -2350.71 | 4.2 |  | 38.8 | 1280.27 | 3.27 |  | 2.63 | 95
12547 | 96.96 | 330.3 | 10447.09 | 136.33 | -2397.74 | 5.39 |  | 1.78 | 1374.91 | 5.39 |  | 0.17 | 95
12643 | 95.29 | 329.8 | 10436.84 | 219.03 | -2445.39 | 1.82 |  | -163.39 | 1470.31 | -1.74 |  | -0.52 | 96
12739 | 92.64 | 329.49 | 10430.21 | 301.67 | -2493.79 | 2.78 |  | -173.33 | 1566.05 | -2.76 |  | -0.32 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 133.48 | 33.4 | 80 | 792 | 800 | 4673.33 | 4200 | 250 | 313 | 227.33 | 188.67 | 22800 | 10000
Run | 123.18 | 33.33 | 78.41 | 769 | 776.11 | 4346.9 | 3723.89 | 250 | 228.04 | 183.96 | 159.78 | 16485.23 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 12/30/2020 |  | 8 |  | 2000 |  | 1 | 2000
Directional & MWD / Gamma Service |  |  |  |  | 12/30/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/30/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/30/2020 |  | 7 |  | 600 |  | 1 | 600
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/30/2020 | 00:00 | 00:25 | 0.42 | 11095 | 11095 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection; Run Numbers
12/30/2020 | 00:25 | 00:50 | 0.42 | 11095 | 11134 | 39 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/11095.00 t/11134.00, TF 0.00, w/WOB 68.00,Flow 330.00, Press 3500.00, Tq 0.00, ROP 93.60
12/30/2020 | 00:50 | 02:00 | 1.17 | 11134 | 11134 | 0 | CRV | 4: BHA #4 (Curve and Lateral) | 5F | Spot Mud Cap; Displace w/ Water
12/30/2020 | 02:00 | 02:05 | 0.08 | 11134 | 11144 | 10 | CRV | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/11134.00 t/11144.00, TF , w/WOB 68,Flow 330, Press 3500, Tq 0.00, ROP 120.00
12/30/2020 | 02:05 | 02:35 | 0.5 | 11144 | 11190 | 46 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11144.00 t/11190.00, w/WOB 35,Flow 330, RPM 50, Press 3700, Tq 14500, ROP 92.00
12/30/2020 | 02:35 | 02:40 | 0.08 | 11190 | 11190 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 02:40 | 03:50 | 1.17 | 11190 | 11190 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 8C | Recalibrate Omron system
12/30/2020 | 03:50 | 04:35 | 0.75 | 11190 | 11190 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 04:35 | 05:10 | 0.58 | 11190 | 11218 | 28 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/11190.00 t/11218.00, TF -120.00, w/WOB 68.00,Flow 330.00, Press 3500.00, Tq 0.00, ROP 48.00
12/30/2020 | 05:10 | 05:45 | 0.58 | 11218 | 11284 | 66 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11218.00 t/11284.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 14500.00, ROP 113.14
12/30/2020 | 05:45 | 06:05 | 0.33 | 11284 | 11284 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 06:05 | 06:33 | 0.47 | 11284 | 11309 | 25 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/11284.00 t/11309.00, TF 180.00, w/WOB 65.00,Flow 330.00, Press 3700.00, Tq 0.00, ROP 53.57
12/30/2020 | 06:33 | 07:04 | 0.52 | 11309 | 11379 | 70 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11309.00 t/11379.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 135.48
12/30/2020 | 07:04 | 07:20 | 0.27 | 11379 | 11379 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 07:20 | 07:24 | 0.07 | 11379 | 11389 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11379.00 t/11389.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 150.00
12/30/2020 | 07:24 | 07:39 | 0.25 | 11389 | 11399 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/11389.00 t/11399.00, TF , w/WOB 65.00,Flow 330.00, Press 3700.00, Tq 0.00, ROP 40.00
12/30/2020 | 07:39 | 08:07 | 0.47 | 11399 | 11475 | 76 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11399.00 t/11475.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 162.86
12/30/2020 | 08:07 | 08:21 | 0.23 | 11475 | 11475 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 08:21 | 08:44 | 0.38 | 11475 | 11569 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11475.00 t/11569.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 245.22
12/30/2020 | 08:44 | 09:00 | 0.27 | 11569 | 11569 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 09:00 | 09:22 | 0.37 | 11569 | 11663 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11569.00 t/11663.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 256.36
12/30/2020 | 09:22 | 09:34 | 0.2 | 11663 | 11663 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 09:34 | 10:01 | 0.45 | 11663 | 11757 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11663.00 t/11757.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 208.89
12/30/2020 | 10:01 | 10:15 | 0.23 | 11757 | 11757 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 10:15 | 10:37 | 0.37 | 11757 | 11851 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11757.00 t/11851.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 256.36
12/30/2020 | 10:37 | 10:50 | 0.22 | 11851 | 11851 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 10:50 | 10:53 | 0.05 | 11851 | 11861 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11851.00 t/11861.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 200.00
12/30/2020 | 10:53 | 11:17 | 0.4 | 11861 | 11881 | 20 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/11861.00 t/11881.00, TF , w/WOB 65.00,Flow 330.00, Press 3700.00, Tq 0.00, ROP 50.00
12/30/2020 | 11:17 | 11:42 | 0.42 | 11881 | 11946 | 65 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11881.00 t/11946.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000, ROP 156.00
12/30/2020 | 11:42 | 11:55 | 0.22 | 11946 | 11946 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 11:55 | 12:18 | 0.38 | 11946 | 12041 | 95 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/11946.00 t/12041.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000.00, ROP 247.83
12/30/2020 | 12:18 | 13:10 | 0.87 | 12041 | 12041 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 5A | Relog gamm from 11851 to 11946
12/30/2020 | 13:10 | 14:00 | 0.83 | 12041 | 12041 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 5A | Circulate, wait on orders from geologist
12/30/2020 | 14:00 | 14:10 | 0.17 | 12041 | 12041 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 14:10 | 14:15 | 0.08 | 12041 | 12051 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12041.00 t/12051.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000.00, ROP 120.00
12/30/2020 | 14:15 | 14:33 | 0.3 | 12051 | 12059 | 8 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12051.00 t/12059.00, TF , w/WOB 65.00,Flow 330.00, Press 3700.00, Tq 0.00, ROP 26.67
12/30/2020 | 14:33 | 14:59 | 0.43 | 12059 | 12136 | 77 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12059.00 t/12136.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000.00, ROP 177.69
12/30/2020 | 14:59 | 15:48 | 0.82 | 12136 | 12136 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 24A | Pump kill mud down back side
12/30/2020 | 15:48 | 15:58 | 0.17 | 12136 | 12136 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 15:58 | 16:02 | 0.07 | 12136 | 12153 | 17 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12136.00 t/12153.00, w/WOB 35.00,Flow 330.00, RPM 50.00, Press 3700.00, Tq 15000.00, ROP 255.00
12/30/2020 | 16:02 | 16:20 | 0.3 | 12153 | 12153 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 5D | Pump Kill Mud Down Backside
12/30/2020 | 16:20 | 16:49 | 0.48 | 12153 | 12231 | 78 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12153.00 t/12231.00, w/WOB 35.00,Flow 395, RPM 80, Press 4400, Tq 17000, ROP 161.38
12/30/2020 | 16:49 | 16:59 | 0.17 | 12231 | 12231 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 16:59 | 17:26 | 0.45 | 12231 | 12328 | 97 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12231.00 t/12328.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 4400.00, Tq 17000.00, ROP 215.56
12/30/2020 | 17:26 | 17:32 | 0.1 | 12328 | 12328 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 17:32 | 17:48 | 0.27 | 12328 | 12338 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12328.00 t/12338.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 4400.00, Tq 17000.00, ROP 37.50
12/30/2020 | 17:48 | 18:14 | 0.43 | 12338 | 12358 | 20 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12338.00 t/12358.00, TF , w/WOB 60,Flow 395.00, Press 4400.00, Tq 0, ROP 46.15
12/30/2020 | 18:14 | 18:36 | 0.37 | 12358 | 12423 | 65 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12358.00 t/12423.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5000, Tq 17000.00, ROP 177.27
12/30/2020 | 18:36 | 18:48 | 0.2 | 12423 | 12423 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 18:48 | 19:00 | 0.2 | 12423 | 12434 | 11 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12423.00 t/12434.00, TF , w/WOB 60,Flow 395.00, Press 4400.00, Tq 0, ROP 55.00
12/30/2020 | 19:00 | 20:25 | 1.42 | 12434 | 12434 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 23E | WOO from Geology; Gamma @ 120
12/30/2020 | 20:25 | 20:55 | 0.5 | 12434 | 12463 | 29 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12434.00 t/12463.00, TF 0.00, w/WOB 60.00,Flow 395.00, Press 4400.00, Tq 0.00, ROP 58.00
12/30/2020 | 20:55 | 21:12 | 0.28 | 12463 | 12518 | 55 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12463.00 t/12518.00, w/WOB 35,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 194.12
12/30/2020 | 21:12 | 21:23 | 0.18 | 12518 | 12518 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 21:23 | 21:40 | 0.28 | 12518 | 12530 | 12 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12518.00 t/12530.00, TF , w/WOB 60.00,Flow 395.00, Press 4400, Tq 0, ROP 42.35
12/30/2020 | 21:40 | 22:05 | 0.42 | 12530 | 12613 | 83 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12530.00 t/12613.00, w/WOB 35,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 199.20
12/30/2020 | 22:05 | 22:15 | 0.17 | 12613 | 12613 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 22:15 | 22:40 | 0.42 | 12613 | 12638 | 25 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12613.00 t/12638.00, TF , w/WOB 60.00,Flow 395.00, Press 4500, Tq 0, ROP 60.00
12/30/2020 | 22:40 | 23:00 | 0.33 | 12638 | 12709 | 71 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12638.00 t/12709.00, w/WOB 35,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 213.00
12/30/2020 | 23:00 | 23:08 | 0.13 | 12709 | 12709 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 23:08 | 23:30 | 0.37 | 12709 | 12725 | 16 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12709.00 t/12725.00, TF , w/WOB 60.00,Flow 395.00, Press 4500, Tq 0, ROP 43.64
12/30/2020 | 23:30 | 23:52 | 0.37 | 12725 | 12805 | 80 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12725.00 t/12805.00, w/WOB 35,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 218.18
12/30/2020 | 23:52 | 23:58 | 0.1 | 12805 | 12805 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/30/2020 | 23:58 | 24:00 | 0.03 | 12805 | 12808 | 3 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12805.00 t/12808.00, w/WOB 35,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 90.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 12_31_2020_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 12/31/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 89550
|  |  |  | 24hr Summary: |  | Drilling Ahead in Lateral Section as per plan
|  |  |  | 24hr Lookahead: |  | Continue Drilling Lateral Section
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12808 |  | 10209 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 14949 |  | 14949 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 2141 |  | 4740 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  | 135 |  | 918 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  | 2006 |  | 3822 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  | 12.50 / 0.17 |  | 33.60 / 4.95 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 3.82 |  | 13.73 |  | SN: |  | 13509568 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 8.68 |  | 19.87 |  | Bit # |  | 4 |  | PH / Temp(F) | 8.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 231.02 / 35.37 |  | 192.38 / 66.84 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 64.67 |  | Grade In: |  | New
% Slide: |  | 6.31 |  | 19.37 |  | Grade Out:
% Rotary: |  | 93.69 |  | 80.63 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | 5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 36.25
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 46.37
UBHO Sub |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.68 |  | 50.05
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 80.66
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 111.82
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 138.2
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 141.51
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2698.1
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2721.96
2721.96
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250025 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.01 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12834 | 93.38 | 329.87 | 10425.22 | 383.56 | -2541.68 | 0.88 |  | 27.14 | 1660.89 | 0.78 |  | 0.4 | 95
12929 | 90.83 | 328.94 | 10421.73 | 465.27 | -2589.99 | 2.86 |  | -159.96 | 1755.8 | -2.68 |  | -0.98 | 95
13023 | 90.97 | 329.29 | 10420.25 | 545.93 | -2638.24 | 0.4 |  | 68.19 | 1849.78 | 0.15 |  | 0.37 | 94
13118 | 90.85 | 333.47 | 10418.74 | 629.3 | -2683.73 | 4.4 |  | 91.61 | 1944.61 | -0.13 |  | 4.4 | 95
13212 | 91.79 | 335.55 | 10416.58 | 714.12 | -2724.17 | 2.43 |  | 65.65 | 2038.03 | 1 |  | 2.21 | 94
13307 | 93.22 | 337.25 | 10412.42 | 801.08 | -2762.16 | 2.34 |  | 49.87 | 2132 | 1.51 |  | 1.79 | 95
13403 | 94.24 | 336.86 | 10406.18 | 889.3 | -2799.51 | 1.14 |  | -20.87 | 2226.68 | 1.06 |  | -0.41 | 96
13498 | 92.62 | 336.38 | 10400.5 | 976.34 | -2837.14 | 1.78 |  | -163.51 | 2320.52 | -1.71 |  | -0.51 | 95
13593 | 92.64 | 334.59 | 10396.14 | 1062.68 | -2876.51 | 1.88 |  | -89.32 | 2414.68 | 0.02 |  | -1.88 | 95
13687 | 92.63 | 329.38 | 10391.81 | 1145.55 | -2920.6 | 5.54 |  | -89.99 | 2508.35 | -0.01 |  | -5.54 | 94
13782 | 92.29 | 329.59 | 10387.73 | 1227.32 | -2968.8 | 0.42 |  | 148.32 | 2603.25 | -0.36 |  | 0.22 | 95
13876 | 92.44 | 326.55 | 10383.85 | 1307.02 | -3018.46 | 3.24 |  | -87.11 | 2697.16 | 0.16 |  | -3.23 | 94
13970 | 91.82 | 325.26 | 10380.36 | 1384.8 | -3071.12 | 1.52 |  | -115.66 | 2791 | -0.66 |  | -1.37 | 94
14064 | 92.38 | 324.61 | 10376.92 | 1461.69 | -3125.09 | 0.91 |  | -49.22 | 2884.78 | 0.6 |  | -0.69 | 94
14159 | 92.43 | 327.94 | 10372.93 | 1540.62 | -3177.78 | 3.5 |  | 89.07 | 2979.62 | 0.05 |  | 3.51 | 95
14253 | 94.17 | 327.66 | 10367.52 | 1620.03 | -3227.78 | 1.87 |  | -9.12 | 3073.45 | 1.85 |  | -0.3 | 94
14347 | 95.35 | 327.32 | 10359.72 | 1699.02 | -3278.13 | 1.31 |  | -16.01 | 3167.12 | 1.26 |  | -0.36 | 94
14442 | 92.24 | 328.44 | 10353.43 | 1779.3 | -3328.52 | 3.48 |  | 160.19 | 3261.89 | -3.27 |  | 1.18 | 95
14536 | 93.14 | 328.56 | 10349.02 | 1859.35 | -3377.58 | 0.97 |  | 7.58 | 3355.79 | 0.96 |  | 0.13 | 94
14629 | 90.14 | 327.47 | 10346.36 | 1938.19 | -3426.81 | 3.43 |  | -160.02 | 3448.74 | -3.23 |  | -1.17 | 93
14724 | 90.91 | 327.19 | 10345.49 | 2018.16 | -3478.09 | 0.86 |  | -19.98 | 3543.72 | 0.81 |  | -0.29 | 95
14819 | 91.62 | 326.47 | 10343.39 | 2097.66 | -3530.06 | 1.06 |  | -45.39 | 3638.66 | 0.75 |  | -0.76 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 171.28 | 39.6 | 80 | 432 | 395 | 5258.14 | 4320.93 | 250 | 340.47 | 205 | 145.12 | 18636.36 | 10000
Run | 141.07 | 42.42 | 70 | 401 | 372.21 | 4647.37 | 3686.95 | 250 | 326.95 | 209.79 | 162.47 | 17023.81 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 12/31/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 12/31/2020 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 12/31/2020 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 12/31/2020 |  | 8 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
12/31/2020 | 00:00 | 00:20 | 0.33 | 12808 | 12900 | 92 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12808.00 t/12900.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 276.00
12/31/2020 | 00:20 | 00:25 | 0.08 | 12900 | 12900 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 00:25 | 00:30 | 0.08 | 12900 | 12914 | 14 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12900.00 t/12914.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5000.00, Tq 17000.00, ROP 168.00
12/31/2020 | 00:30 | 00:52 | 0.37 | 12914 | 12930 | 16 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/12914.00 t/12930.00, TF 180.00, w/WOB 66.00,Flow 395.00, Press 4600.00, Tq 0.00, ROP 43.64
12/31/2020 | 00:52 | 01:11 | 0.32 | 12930 | 12995 | 65 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12930.00 t/12995.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5400.00, Tq 17000.00, ROP 205.26
12/31/2020 | 01:11 | 01:18 | 0.12 | 12995 | 12995 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 01:18 | 01:44 | 0.43 | 12995 | 13089 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/12995.00 t/13089.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 216.92
12/31/2020 | 01:44 | 01:50 | 0.1 | 13089 | 13089 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 01:50 | 01:55 | 0.08 | 13089 | 13095 | 6 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13089.00 t/13095.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 72.00
12/31/2020 | 01:55 | 02:20 | 0.42 | 13095 | 13109 | 14 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/13095.00 t/13109.00, TF , w/WOB 68,Flow 395.00, Press 4600, Tq 0, ROP 33.60
12/31/2020 | 02:20 | 02:42 | 0.37 | 13109 | 13184 | 75 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13109.00 t/13184.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 204.55
12/31/2020 | 02:42 | 02:48 | 0.1 | 13184 | 13184 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 02:48 | 03:11 | 0.38 | 13184 | 13278 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13184.00 t/13278.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 245.22
12/31/2020 | 03:11 | 03:16 | 0.08 | 13278 | 13278 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 03:16 | 03:24 | 0.13 | 13278 | 13284 | 6 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13278.00 t/13284.00, w/WOB 35.00,Flow 395.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 45.00
12/31/2020 | 03:24 | 03:48 | 0.4 | 13284 | 13300 | 16 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/13284.00 t/13300.00, TF , w/WOB 72,Flow 395.00, Press 4600, Tq 0, ROP 40.00
12/31/2020 | 03:48 | 04:10 | 0.37 | 13300 | 13374 | 74 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13300.00 t/13374.00, w/WOB 35,Flow 395.00, RPM 80, Press 5400, Tq 18000, ROP 201.82
12/31/2020 | 04:10 | 04:18 | 0.13 | 13374 | 13374 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 04:18 | 04:48 | 0.5 | 13374 | 13389 | 15 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/13374.00 t/13389.00, TF , w/WOB 72.00,Flow 395.00, Press 4600.00, Tq 0.00, ROP 30.00
12/31/2020 | 04:48 | 05:07 | 0.32 | 13389 | 13469 | 80 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13389.00 t/13469.00, w/WOB 32,Flow 395.00, RPM 80, Press 5500, Tq 18000, ROP 252.63
12/31/2020 | 05:07 | 05:15 | 0.13 | 13469 | 13469 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 05:15 | 05:37 | 0.37 | 13469 | 13564 | 95 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13469.00 t/13564.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 259.09
12/31/2020 | 05:37 | 05:47 | 0.17 | 13564 | 13564 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 05:47 | 06:05 | 0.3 | 13564 | 13659 | 95 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13564.00 t/13659.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 316.67
12/31/2020 | 06:05 | 06:15 | 0.17 | 13659 | 13659 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 06:15 | 06:32 | 0.28 | 13659 | 13754 | 95 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13659.00 t/13754.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 335.29
12/31/2020 | 06:32 | 06:42 | 0.17 | 13754 | 13754 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 06:42 | 07:00 | 0.3 | 13754 | 13848 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13754.00 t/13848.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 313.33
12/31/2020 | 07:00 | 07:10 | 0.17 | 13848 | 13848 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 07:10 | 07:26 | 0.27 | 13848 | 13942 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13848.00 t/13942.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 352.50
12/31/2020 | 07:26 | 07:36 | 0.17 | 13942 | 13942 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 07:36 | 07:38 | 0.03 | 13942 | 13950 | 8 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13942.00 t/13950.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 240.00
12/31/2020 | 07:38 | 08:48 | 1.17 | 13950 | 13950 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 8A | Troubleshoot top drive
12/31/2020 | 08:48 | 09:09 | 0.35 | 13950 | 14036 | 86 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/13950.00 t/14036.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 245.71
12/31/2020 | 09:09 | 09:19 | 0.17 | 14036 | 14036 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 09:19 | 09:23 | 0.07 | 14036 | 14046 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14036.00 t/14046.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 150.00
12/31/2020 | 09:23 | 09:43 | 0.33 | 14046 | 14058 | 12 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/14046.00 t/14058.00, TF , w/WOB 65,Flow 395.00, Press 1650, Tq 0, ROP 36.00
12/31/2020 | 09:43 | 10:05 | 0.37 | 14058 | 14130 | 72 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14058.00 t/14130.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 196.36
12/31/2020 | 10:05 | 10:15 | 0.17 | 14130 | 14130 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 10:15 | 10:34 | 0.32 | 14130 | 14225 | 95 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14130.00 t/14225.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 300.00
12/31/2020 | 10:34 | 10:44 | 0.17 | 14225 | 14225 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 10:44 | 10:47 | 0.05 | 14225 | 14235 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14225.00 t/14235.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 200.00
12/31/2020 | 10:47 | 11:08 | 0.35 | 14235 | 14247 | 12 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/14235.00 t/14247.00, TF , w/WOB 65.00,Flow 395.00, Press 1650.00, Tq 0.00, ROP 34.29
12/31/2020 | 11:08 | 11:29 | 0.35 | 14247 | 14319 | 72 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14247.00 t/14319.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 205.71
12/31/2020 | 11:29 | 12:10 | 0.68 | 14319 | 14319 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 8O | Replace plug
12/31/2020 | 12:10 | 12:20 | 0.17 | 14319 | 14319 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 12:20 | 12:25 | 0.08 | 14319 | 14329 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14319.00 t/14329.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 120.00
12/31/2020 | 12:25 | 12:36 | 0.18 | 14329 | 14339 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/14329.00 t/14339.00, TF , w/WOB 65.00,Flow 395.00, Press 1650.00, Tq 0.00, ROP 54.55
12/31/2020 | 12:36 | 12:59 | 0.38 | 14339 | 14414 | 75 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14339.00 t/14414.00, w/WOB 32.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 18000.00, ROP 195.65
12/31/2020 | 12:59 | 13:30 | 0.52 | 14414 | 14414 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 24A | Get pipe screen unstuck from gooseneck on top drive
12/31/2020 | 13:30 | 13:40 | 0.17 | 14414 | 14414 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 5D | Survey & Connection
12/31/2020 | 13:40 | 13:43 | 0.05 | 14414 | 14424 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14414.00 t/14424.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 200.00
12/31/2020 | 13:43 | 14:00 | 0.28 | 14424 | 14436 | 12 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/14424.00 t/14436.00, TF 180.00, w/WOB 65.00,Flow 395.00, Press 1650.00, Tq 0.00, ROP 42.35
12/31/2020 | 14:00 | 14:25 | 0.42 | 14436 | 14508 | 72 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14436.00 t/14508.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 172.80
12/31/2020 | 14:25 | 14:35 | 0.17 | 14508 | 14508 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 14:35 | 14:57 | 0.37 | 14508 | 14602 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14508.00 t/14602.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 256.36
12/31/2020 | 14:57 | 15:07 | 0.17 | 14602 | 14602 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 15:07 | 15:24 | 0.28 | 14602 | 14696 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14602.00 t/14696.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 331.76
12/31/2020 | 15:24 | 15:34 | 0.17 | 14696 | 14696 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 15:34 | 15:52 | 0.3 | 14696 | 14790 | 94 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14696.00 t/14790.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 313.33
12/31/2020 | 15:52 | 16:00 | 0.13 | 14790 | 14790 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 16:00 | 16:03 | 0.05 | 14790 | 14800 | 10 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14790.00 t/14800.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 200.00
12/31/2020 | 16:03 | 16:29 | 0.43 | 14800 | 14813 | 13 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/14800.00 t/14813.00, TF -140.00, w/WOB 65.00,Flow 395.00, Press 1650.00, Tq 0.00, ROP 30.00
12/31/2020 | 16:29 | 16:54 | 0.42 | 14813 | 14885 | 72 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14813.00 t/14885.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 172.80
12/31/2020 | 16:54 | 17:04 | 0.17 | 14885 | 14885 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 10D | Survey & Connection
12/31/2020 | 17:04 | 17:14 | 0.17 | 14885 | 14927 | 42 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14885.00 t/14927.00, w/WOB 28.00,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 252.00
12/31/2020 | 17:14 | 17:47 | 0.55 | 14927 | 14942 | 15 | LAT | 4: BHA #4 (Curve and Lateral) | 2J | Slide Drill f/14927.00 t/14942.00, TF , w/WOB 65.00,Flow 395.00, Press 1650.00, Tq 0.00, ROP 27.27
12/31/2020 | 17:47 | 17:50 | 0.05 | 14942 | 14944 | 2 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14942.00 t/14944.00, w/WOB 28,Flow 395.00, RPM 80, Press 5500, Tq 20000, ROP 40.00
12/31/2020 | 17:50 | 21:08 | 3.3 | 14944 | 14944 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 6F | TOH 10 Stds
12/31/2020 | 21:08 | 21:15 | 0.12 | 14944 | 14946 | 2 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14944.00 t/14946.00, w/WOB 38,Flow 395.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 17.14
12/31/2020 | 21:15 | 23:12 | 1.95 | 14946 | 14946 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 3B | Attempt t/ work back to btm after top drive stall
12/31/2020 | 23:12 | 23:20 | 0.13 | 14946 | 14949 | 3 | LAT | 4: BHA #4 (Curve and Lateral) | 2K | Rotary Drill f/14946.00 t/14949.00, w/WOB 45,Flow 350, RPM 80.00, Press 4800, Tq 23000, ROP 22.50
12/31/2020 | 23:20 | 24:00 | 0.67 | 14949 | 14949 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 3B | Top Drive stall; P/U and attempt to run to bottom
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_1_2021_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 01/01/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 89550
|  |  |  | 24hr Summary: |  | Attempt t/ Drill; TOH t/ Inspect BHA; Left Bit and Power Section in Hole; P/U BHA #5; TIH
|  |  |  | 24hr Lookahead: |  | TIH; Sidetrack; Begin Drilling Ahead in Lateral Section as per plan ST01 P1
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14949 |  | 10209 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 14949 |  | 14949 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  |  |  | 4740 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  |  |  | 918 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  |  |  | 3822 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  |  |  | 33.60 / 4.95 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  |  |  | 13.73 |  | SN: |  | 13509568 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  |  |  | 19.87 |  | Bit # |  | 4 |  | PH / Temp(F) | 8.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  |  |  | 192.38 / 66.84 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 15.5 |  | 80.17 |  | Grade In: |  | New
% Slide: |  |  |  | 19.37 |  | Grade Out:
% Rotary: |  |  |  | 80.63 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | 5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 36.25
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 46.37
UBHO Sub |  |  |  | 5.188 | 2.5 |  |  |  |  | 3.68 |  | 50.05
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 80.66
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 111.82
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 138.2
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 141.51
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2698.1
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2721.96
2721.96
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250025 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.01 |  | 2.12 |  | 0.89 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 39.6 | 80 | 432 | 395 | 5258.14 | 4320.93 | 250 | 340.47 | 205 | 145.12 | 18636.36 | 10000
Run | 141.07 | 42.42 | 70 | 401 | 372.21 | 4647.37 | 3686.95 | 250 | 326.95 | 209.79 | 162.47 | 17023.81 | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/01/2021 | 00:00 | 02:35 | 2.58 | 14949 | 14949 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 3B | Attempt t/ Drill; Unable to drill off w/ 35k WOB, 400psi diff, 22k torque, and 80 RPM
01/01/2021 | 02:35 | 14:00 | 11.42 | 14949 | 14949 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 6B | TOH t/ Inspect BHA
01/01/2021 | 14:00 | 15:30 | 1.5 | 14949 | 14949 | 0 | LAT | 4: BHA #4 (Curve and Lateral) | 6P | Lay down BHA #4
01/01/2021 | 15:30 | 24:00 | 8.5 | 14949 | 14949 | 0 | LAT |  | 24B | P/U BHA #5
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_2_2021_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 01/02/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 99400
|  |  |  | 24hr Summary: |  | TIH; Trough f/ 13,075 t/ 13,095; Begin Time Drilling; Drill Lateral Section
|  |  |  | 24hr Lookahead: |  | Drilling Ahead in Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13095 |  | 13095 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 14137 |  | 14137 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 1042 |  | 1042 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  | 178 |  | 178 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  | 864 |  | 864 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  | 17.32 / 1.83 |  | 17.32 / 1.83 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 10.95 |  | 10.95 |  | SN: |  | 13522001 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 6.37 |  | 6.37 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 135.71 / 16.26 |  | 135.71 / 16.26 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 21.5 |  | 21.5 |  | Grade In: |  | New
% Slide: |  | 17.08 |  | 17.08 |  | Grade Out:
% Rotary: |  | 82.92 |  | 82.92 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  |  | 5 | 2 |  |  |  |  | 30.99 |  | 31.74
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 34.11
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 44.23
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 46.72
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 77.33
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 108.49
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 134.87
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 138.18
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2694.77
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2718.63
2718.63
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250020 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13118 | 90.85 | 333.47 | 10418.74 | 629.3 | -2683.73 | 4.4 |  | 91.61 | 1944.61 | -0.13 |  | 4.4 | 95
13212 | 91.79 | 335.55 | 10416.58 | 714.12 | -2724.17 | 2.43 |  | 65.65 | 2038.03 | 1 |  | 2.21 | 94
13307 | 93.22 | 337.25 | 10412.42 | 801.08 | -2762.16 | 2.34 |  | 49.87 | 2132 | 1.51 |  | 1.79 | 95
13403 | 94.24 | 336.86 | 10406.18 | 889.3 | -2799.51 | 1.14 |  | -20.87 | 2226.68 | 1.06 |  | -0.41 | 96
13498 | 92.62 | 336.38 | 10400.5 | 976.34 | -2837.14 | 1.78 |  | -163.51 | 2320.52 | -1.71 |  | -0.51 | 95
13593 | 92.64 | 334.59 | 10396.14 | 1062.68 | -2876.51 | 1.88 |  | -89.32 | 2414.68 | 0.02 |  | -1.88 | 95
13687 | 92.63 | 329.38 | 10391.81 | 1145.55 | -2920.6 | 5.54 |  | -89.99 | 2508.35 | -0.01 |  | -5.54 | 94
13782 | 92.29 | 329.59 | 10387.73 | 1227.32 | -2968.8 | 0.42 |  | 148.32 | 2603.25 | -0.36 |  | 0.22 | 95
13876 | 92.44 | 326.55 | 10383.85 | 1307.02 | -3018.46 | 3.24 |  | -87.11 | 2697.16 | 0.16 |  | -3.23 | 94
13970 | 91.82 | 325.26 | 10380.36 | 1384.8 | -3071.12 | 1.52 |  | -115.66 | 2791 | -0.66 |  | -1.37 | 94
14064 | 92.38 | 324.61 | 10376.92 | 1461.69 | -3125.09 | 0.91 |  | -49.22 | 2884.78 | 0.6 |  | -0.69 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 60.17 | 39.6 | 80 | 349 | 395 | 5258.14 | 4320.93 | 250 | 340.47 | 205 | 145.12 | 18636.36 | 10000
Run | 60.17 | 42.42 | 70 | 323 | 372.21 | 4647.37 | 3686.95 | 250 | 326.95 | 209.79 | 162.47 | 17023.81 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 01/02/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 01/02/2021 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 01/02/2021 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 01/02/2021 |  | 8 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/02/2021 | 00:00 | 02:30 | 2.5 | 13095 | 13095 | 0 | ST | 5: BHA #5 (Lateral) | 6O | TIH t/ 13,084
01/02/2021 | 02:30 | 02:34 | 0.07 | 13095 | 13095 | 0 | ST | 5: BHA #5 (Lateral) | 3C | Ream f/ 13,084 t/ 13,175 to assure fish isnt in way
01/02/2021 | 02:34 | 04:20 | 1.77 | 13095 | 13095 | 0 | ST | 5: BHA #5 (Lateral) | 5A | Trough f/ 13,075 t/ 13,095
01/02/2021 | 04:20 | 09:04 | 4.73 | 13095 | 13100 | 5 | ST | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13095.00 t/13100.00, TF , w/WOB 10,Flow 400, Press 4800, Tq 0, ROP 1.06
01/02/2021 | 09:04 | 11:42 | 2.63 | 13100 | 13130 | 30 | ST | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13100.00 t/13130.00, TF , w/WOB 40,Flow 400, Press 4800, Tq 0, ROP 11.39
01/02/2021 | 11:42 | 12:48 | 1.1 | 13130 | 13181 | 51 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13130.00 t/13181.00, w/WOB 20,Flow 400.00, RPM 30, Press 5400, Tq 17000, ROP 46.36
01/02/2021 | 12:48 | 12:58 | 0.17 | 13181 | 13181 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 12:58 | 13:42 | 0.73 | 13181 | 13275 | 94 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13181.00 t/13275.00, w/WOB 30,Flow 400.00, RPM 80, Press 5600, Tq 18500, ROP 128.18
01/02/2021 | 13:42 | 13:52 | 0.17 | 13275 | 13275 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 13:52 | 13:57 | 0.08 | 13275 | 13285 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13275.00 t/13285.00, w/WOB 30,Flow 400.00, RPM 80, Press 5600, Tq 18500, ROP 120.00
01/02/2021 | 13:57 | 14:36 | 0.65 | 13285 | 13330 | 45 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13285.00 t/13330.00, TF , w/WOB 60,Flow 400.00, Press 5000, Tq 0.00, ROP 69.23
01/02/2021 | 14:36 | 14:55 | 0.32 | 13330 | 13370 | 40 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13330.00 t/13370.00, w/WOB 32,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 126.32
01/02/2021 | 14:55 | 15:05 | 0.17 | 13370 | 13370 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 15:05 | 15:32 | 0.45 | 13370 | 13466 | 96 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13370.00 t/13466.00, w/WOB 32,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 213.33
01/02/2021 | 15:32 | 15:42 | 0.17 | 13466 | 13466 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 15:42 | 15:47 | 0.08 | 13466 | 13476 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13466.00 t/13476.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5600.00, Tq 19000.00, ROP 120.00
01/02/2021 | 15:47 | 16:38 | 0.85 | 13476 | 13494 | 18 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13476.00 t/13494.00, TF -150.00, w/WOB 60.00,Flow 400.00, Press 5000.00, Tq 0.00, ROP 21.18
01/02/2021 | 16:38 | 17:06 | 0.47 | 13494 | 13561 | 67 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13494.00 t/13561.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 143.57
01/02/2021 | 17:06 | 17:16 | 0.17 | 13561 | 13561 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 17:16 | 17:20 | 0.07 | 13561 | 13571 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13561.00 t/13571.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 150.00
01/02/2021 | 17:20 | 17:55 | 0.58 | 13571 | 13591 | 20 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13571.00 t/13591.00, TF , w/WOB 65,Flow 400.00, Press 5000.00, Tq 0.00, ROP 34.29
01/02/2021 | 17:55 | 18:25 | 0.5 | 13591 | 13656 | 65 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13591.00 t/13656.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 130.00
01/02/2021 | 18:25 | 18:32 | 0.12 | 13656 | 13656 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 18:32 | 19:30 | 0.97 | 13656 | 13696 | 40 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13656.00 t/13696.00, TF , w/WOB 70,Flow 400.00, Press 5000.00, Tq 0.00, ROP 41.38
01/02/2021 | 19:30 | 19:52 | 0.37 | 13696 | 13750 | 54 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13696.00 t/13750.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 147.27
01/02/2021 | 19:52 | 19:58 | 0.1 | 13750 | 13750 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 19:58 | 20:32 | 0.57 | 13750 | 13845 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13750.00 t/13845.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 167.65
01/02/2021 | 20:32 | 20:38 | 0.1 | 13845 | 13845 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 20:38 | 20:43 | 0.08 | 13845 | 13855 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13845.00 t/13855.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 120.00
01/02/2021 | 20:43 | 21:15 | 0.53 | 13855 | 13875 | 20 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/13855.00 t/13875.00, TF , w/WOB 70,Flow 400.00, Press 5000.00, Tq 0.00, ROP 37.50
01/02/2021 | 21:15 | 21:40 | 0.42 | 13875 | 13939 | 64 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13875.00 t/13939.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 153.60
01/02/2021 | 21:40 | 21:44 | 0.07 | 13939 | 13939 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 21:44 | 22:10 | 0.43 | 13939 | 14033 | 94 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/13939.00 t/14033.00, w/WOB 35,Flow 400.00, RPM 80, Press 5600, Tq 19000, ROP 216.92
01/02/2021 | 22:10 | 23:10 | 1 | 14033 | 14033 | 0 | LAT2 | 5: BHA #5 (Lateral) | 23E | WOO f/ Engineer
01/02/2021 | 23:10 | 23:15 | 0.08 | 14033 | 14033 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 23:15 | 23:45 | 0.5 | 14033 | 14127 | 94 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14033.00 t/14127.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 5600.00, Tq 19000.00, ROP 188.00
01/02/2021 | 23:45 | 23:48 | 0.05 | 14127 | 14127 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/02/2021 | 23:48 | 24:00 | 0.2 | 14127 | 14137 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14127.00 t/14137.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 5600.00, Tq 19000.00, ROP 50.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_3_2021_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 01/03/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 109250
|  |  |  | 24hr Summary: |  | Drilling Ahead in Lateral Section
|  |  |  | 24hr Lookahead: |  | Continue Drilling Lateral Section
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14137 |  | 13095 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 16118 |  | 16118 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 1981 |  | 3023 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  | 140 |  | 318 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  | 1841 |  | 2705 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  | 17.48 / 0.00 |  | 34.80 / 1.83 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 6.95 |  | 17.9 |  | SN: |  | 13522001 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 10.53 |  | 16.9 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 174.78 / 20.14 |  | 160.06 / 17.77 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 45.5 |  | Grade In: |  | New
% Slide: |  | 7.07 |  | 10.52 |  | Grade Out:
% Rotary: |  | 92.93 |  | 89.48 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  |  | 5 | 2 |  |  |  |  | 30.99 |  | 31.74
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 34.11
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 44.23
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 46.72
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 77.33
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 108.49
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 134.87
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 138.18
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2694.77
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2718.63
2718.63
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250020 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14159 | 92.43 | 327.94 | 10372.93 | 1540.62 | -3177.78 | 3.5 |  | 89.07 | 2979.62 | 0.05 |  | 3.51 | 95
14253 | 94.17 | 327.66 | 10367.52 | 1620.03 | -3227.78 | 1.87 |  | -9.12 | 3073.45 | 1.85 |  | -0.3 | 94
14347 | 95.35 | 327.32 | 10359.72 | 1699.02 | -3278.13 | 1.31 |  | -16.01 | 3167.12 | 1.26 |  | -0.36 | 94
14442 | 92.24 | 328.44 | 10353.43 | 1779.3 | -3328.52 | 3.48 |  | 160.19 | 3261.89 | -3.27 |  | 1.18 | 95
14536 | 93.14 | 328.56 | 10349.02 | 1859.35 | -3377.58 | 0.97 |  | 7.58 | 3355.79 | 0.96 |  | 0.13 | 94
14629 | 90.14 | 327.47 | 10346.36 | 1938.19 | -3426.81 | 3.43 |  | -160.02 | 3448.74 | -3.23 |  | -1.17 | 93
14724 | 90.91 | 327.19 | 10345.49 | 2018.16 | -3478.09 | 0.86 |  | -19.98 | 3543.72 | 0.81 |  | -0.29 | 95
14819 | 91.62 | 326.47 | 10343.39 | 2097.66 | -3530.06 | 1.06 |  | -45.39 | 3638.66 | 0.75 |  | -0.76 | 95
14913 | 93.09 | 326.12 | 10339.53 | 2175.79 | -3582.17 | 1.61 |  | -13.37 | 3732.52 | 1.56 |  | -0.37 | 94
15009 | 94.67 | 326.04 | 10333.03 | 2255.27 | -3635.62 | 1.65 |  | -2.89 | 3828.22 | 1.65 |  | -0.08 | 96
15104 | 92.54 | 327.44 | 10327.06 | 2334.54 | -3687.61 | 2.68 |  | 146.69 | 3922.99 | -2.24 |  | 1.47 | 95
15199 | 92.23 | 326.37 | 10323.1 | 2414.06 | -3739.44 | 1.17 |  | -106.15 | 4017.88 | -0.33 |  | -1.13 | 95
15294 | 92.57 | 325.6 | 10319.13 | 2492.73 | -3792.54 | 0.89 |  | -66.14 | 4112.71 | 0.36 |  | -0.81 | 95
15389 | 91.08 | 326.84 | 10316.1 | 2571.65 | -3845.33 | 2.04 |  | 140.22 | 4207.6 | -1.57 |  | 1.31 | 95
15485 | 91.99 | 326.5 | 10313.53 | 2651.83 | -3898.06 | 1.01 |  | -20.48 | 4303.52 | 0.95 |  | -0.35 | 96
15580 | 93.32 | 326.04 | 10309.13 | 2730.75 | -3950.75 | 1.48 |  | -19.05 | 4398.35 | 1.4 |  | -0.48 | 95
15675 | 92.58 | 326.7 | 10304.24 | 2809.75 | -4003.29 | 1.04 |  | 138.29 | 4493.17 | -0.78 |  | 0.69 | 95
15770 | 93.53 | 325.81 | 10299.18 | 2888.63 | -4055.99 | 1.37 |  | -43.07 | 4587.97 | 1 |  | -0.94 | 95
15865 | 91.58 | 325.96 | 10294.94 | 2967.2 | -4109.21 | 2.06 |  | 175.6 | 4682.79 | -2.05 |  | 0.16 | 95
15960 | 92.66 | 325.86 | 10291.43 | 3045.82 | -4162.42 | 1.14 |  | -5.28 | 4777.64 | 1.14 |  | -0.11 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 113.31 | 39.6 | 80 | 349 | 395 | 5258.14 | 4320.93 | 250 | 340.47 | 205 | 145.12 | 18636.36 | 10000
Run | 86.87 | 42.42 | 70 | 323 | 372.21 | 4647.37 | 3686.95 | 250 | 326.95 | 209.79 | 162.47 | 17023.81 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 01/03/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 01/03/2021 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 01/03/2021 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 01/03/2021 |  | 8 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/03/2021 | 00:00 | 00:46 | 0.77 | 14137 | 14159 | 22 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/14137.00 t/14159.00, TF , w/WOB 70,Flow 400.00, Press 4950, Tq 0, ROP 28.70
01/03/2021 | 00:46 | 01:07 | 0.35 | 14159 | 14222 | 63 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14159.00 t/14222.00, w/WOB 32,Flow 400.00, RPM 80, Press 5600, Tq 20000, ROP 180.00
01/03/2021 | 01:07 | 01:12 | 0.08 | 14222 | 14222 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 01:12 | 01:50 | 0.63 | 14222 | 14315 | 93 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14222.00 t/14315.00, w/WOB 32,Flow 400.00, RPM 80, Press 5600, Tq 20000, ROP 146.84
01/03/2021 | 01:50 | 01:57 | 0.12 | 14315 | 14315 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 01:57 | 02:27 | 0.5 | 14315 | 14410 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14315.00 t/14410.00, w/WOB 32,Flow 400.00, RPM 80, Press 5600, Tq 20000, ROP 190.00
01/03/2021 | 02:27 | 02:35 | 0.13 | 14410 | 14410 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 02:35 | 02:38 | 0.05 | 14410 | 14415 | 5 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14410.00 t/14415.00, w/WOB 32,Flow 400.00, RPM 80, Press 5700, Tq 20000, ROP 100.00
01/03/2021 | 02:38 | 03:36 | 0.97 | 14415 | 14440 | 25 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/14415.00 t/14440.00, TF , w/WOB 75,Flow 400.00, Press 5000, Tq 0.00, ROP 25.86
01/03/2021 | 03:36 | 03:58 | 0.37 | 14440 | 14440 | 0 | LAT2 | 5: BHA #5 (Lateral) | 8L | Replace 2 Valve on Rig Floor
01/03/2021 | 03:58 | 04:16 | 0.3 | 14440 | 14505 | 65 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14440.00 t/14505.00, w/WOB 30,Flow 400.00, RPM 80, Press 5700, Tq 20000, ROP 216.67
01/03/2021 | 04:16 | 04:24 | 0.13 | 14505 | 14505 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 04:24 | 04:30 | 0.1 | 14505 | 14528 | 23 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14505.00 t/14528.00, w/WOB 30,Flow 400.00, RPM 80, Press 5700, Tq 20000, ROP 230.00
01/03/2021 | 04:30 | 04:55 | 0.42 | 14528 | 14599 | 71 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14505.00 t/14599.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 225.60
01/03/2021 | 04:55 | 05:04 | 0.15 | 14599 | 14599 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 05:04 | 05:35 | 0.52 | 14599 | 14611 | 12 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/14599.00 t/14611.00, TF 180.00, w/WOB 75.00,Flow 400.00, Press 5000.00, Tq 0.00, ROP 23.23
01/03/2021 | 05:35 | 06:06 | 0.52 | 14611 | 14692 | 81 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14611.00 t/14692.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 156.77
01/03/2021 | 06:06 | 06:16 | 0.17 | 14692 | 14692 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 06:16 | 06:42 | 0.43 | 14692 | 14787 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14692.00 t/14787.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 219.23
01/03/2021 | 06:42 | 06:52 | 0.17 | 14787 | 14787 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 06:52 | 07:25 | 0.55 | 14787 | 14882 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14787.00 t/14882.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 172.73
01/03/2021 | 07:25 | 07:35 | 0.17 | 14882 | 14882 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 07:35 | 08:16 | 0.68 | 14882 | 14976 | 94 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14882.00 t/14976.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 137.56
01/03/2021 | 08:16 | 08:26 | 0.17 | 14976 | 14976 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 08:26 | 09:07 | 0.68 | 14976 | 15072 | 96 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/14976.00 t/15072.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 140.49
01/03/2021 | 09:07 | 09:17 | 0.17 | 15072 | 15072 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 09:17 | 10:27 | 1.17 | 15072 | 15097 | 25 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/15072.00 t/15097.00, TF 150.00, w/WOB 75.00,Flow 400.00, Press 5000.00, Tq 0.00, ROP 21.43
01/03/2021 | 10:27 | 10:58 | 0.52 | 15097 | 15167 | 70 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15097.00 t/15167.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 135.48
01/03/2021 | 10:58 | 11:08 | 0.17 | 15167 | 15167 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 11:08 | 11:32 | 0.4 | 15167 | 15262 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15167.00 t/15262.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 237.50
01/03/2021 | 11:32 | 11:42 | 0.17 | 15262 | 15262 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 11:42 | 12:11 | 0.48 | 15262 | 15357 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15262.00 t/15357.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 196.55
01/03/2021 | 12:11 | 12:21 | 0.17 | 15357 | 15357 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 12:21 | 12:25 | 0.07 | 15357 | 15367 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15357.00 t/15367.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 150.00
01/03/2021 | 12:25 | 13:10 | 0.75 | 15367 | 15382 | 15 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/15367.00 t/15382.00, TF , w/WOB 70,Flow 390, Press 5100, Tq 0, ROP 20.00
01/03/2021 | 13:10 | 13:36 | 0.43 | 15382 | 15452 | 70 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15382.00 t/15452.00, w/WOB 30.00,Flow 390, RPM 80.00, Press 5700, Tq 20000.00, ROP 161.54
01/03/2021 | 13:36 | 13:46 | 0.17 | 15452 | 15452 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 13:46 | 14:10 | 0.4 | 15452 | 15548 | 96 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15452.00 t/15548.00, w/WOB 30.00,Flow 390, RPM 80.00, Press 5700, Tq 20000.00, ROP 240.00
01/03/2021 | 14:10 | 14:20 | 0.17 | 15548 | 15548 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 14:20 | 14:50 | 0.5 | 15548 | 15643 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15548.00 t/15643.00, w/WOB 30.00,Flow 390, RPM 80.00, Press 5700, Tq 20000.00, ROP 190.00
01/03/2021 | 14:50 | 15:00 | 0.17 | 15643 | 15643 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 15:00 | 15:05 | 0.08 | 15643 | 15653 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15643.00 t/15653.00, w/WOB 30.00,Flow 390, RPM 80.00, Press 5700, Tq 20000.00, ROP 120.00
01/03/2021 | 15:05 | 15:56 | 0.85 | 15653 | 15665 | 12 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/15653.00 t/15665.00, TF , w/WOB 70,Flow 390, Press 5100, Tq 0, ROP 14.12
01/03/2021 | 15:56 | 16:24 | 0.47 | 15665 | 15738 | 73 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15665.00 t/15738.00, w/WOB 30.00,Flow 390, RPM 80.00, Press 5700, Tq 20000.00, ROP 156.43
01/03/2021 | 16:24 | 16:55 | 0.52 | 15738 | 15738 | 0 | LAT2 | 5: BHA #5 (Lateral) | 8P | Rig Service
01/03/2021 | 16:55 | 17:05 | 0.17 | 15738 | 15738 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 17:05 | 17:29 | 0.4 | 15738 | 15833 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15738.00 t/15833.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 237.50
01/03/2021 | 17:29 | 17:39 | 0.17 | 15833 | 15833 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 17:39 | 17:40 | 0.02 | 15833 | 15842 | 9 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15833.00 t/15842.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 540.00
01/03/2021 | 17:40 | 18:32 | 0.87 | 15842 | 15852 | 10 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/15842.00 t/15852.00, TF , w/WOB 75,Flow 390.00, Press 5100, Tq 0, ROP 11.54
01/03/2021 | 18:32 | 18:35 | 0.05 | 15852 | 15857 | 5 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15852.00 t/15857.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 100.00
01/03/2021 | 18:35 | 21:15 | 2.67 | 15857 | 15857 | 0 | LAT2 | 5: BHA #5 (Lateral) | 6F | Wiper Trip (10 Stands)
01/03/2021 | 21:15 | 21:34 | 0.32 | 15857 | 15864 | 7 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/15857.00 t/15864.00, TF , w/WOB 75,Flow 390.00, Press 5100, Tq 0, ROP 22.11
01/03/2021 | 21:34 | 21:58 | 0.4 | 15864 | 15928 | 64 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15864.00 t/15928.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 160.00
01/03/2021 | 21:58 | 22:02 | 0.07 | 15928 | 15928 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 22:02 | 22:35 | 0.55 | 15928 | 16023 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/15928.00 t/16023.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 172.73
01/03/2021 | 22:35 | 22:40 | 0.08 | 16023 | 16023 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/03/2021 | 22:40 | 22:45 | 0.08 | 16023 | 16028 | 5 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16023.00 t/16028.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 60.00
01/03/2021 | 22:45 | 23:30 | 0.75 | 16028 | 16040 | 12 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/16028.00 t/16040.00, TF , w/WOB 80,Flow 390.00, Press 5100, Tq 0, ROP 16.00
01/03/2021 | 23:30 | 23:58 | 0.47 | 16040 | 16118 | 78 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16040.00 t/16118.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 167.14
01/03/2021 | 23:58 | 24:00 | 0.03 | 16118 | 16118 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_4_2021_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 01/04/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 119100
|  |  |  | 24hr Summary: |  | Drill Ahead in Lateral Section t/ TD; Circulate Hole Clean; TOH
|  |  |  | 24hr Lookahead: |  | TOH; L/D BHA; Load Clean up Truck; EOW
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16118 |  | 13095 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 16840 |  | 16840 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 722 |  | 3745 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  | 80 |  | 398 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  | 642 |  | 3347 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  | 11.97 / 9.55 |  | 46.77 / 11.38 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 7.73 |  | 25.63 |  | SN: |  | 13522001 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 4.23 |  | 21.13 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 151.65 / 10.34 |  | 158.38 / 15.53 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 69.5 |  | Grade In: |  | New
% Slide: |  | 11.08 |  | 10.63 |  | Grade Out:
% Rotary: |  | 88.92 |  | 89.37 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  |  | 5 | 2 |  |  |  |  | 30.99 |  | 31.74
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 34.11
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 44.23
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 46.72
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 77.33
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 108.49
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 134.87
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 138.18
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2694.77
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2718.63
2718.63
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250020 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16055 | 91.85 | 325.8 | 10287.69 | 3124.36 | -4215.74 | 0.85 |  | -175.77 | 4872.47 | -0.85 |  | -0.06 | 95
16149 | 93.25 | 325.26 | 10283.51 | 3201.78 | -4268.89 | 1.6 |  | -21.06 | 4966.26 | 1.49 |  | -0.57 | 94
16243 | 92.09 | 326.22 | 10279.13 | 3279.38 | -4321.74 | 1.6 |  | 140.4 | 5060.06 | -1.23 |  | 1.02 | 94
16338 | 93.17 | 325.99 | 10274.77 | 3358.15 | -4374.67 | 1.16 |  | -12 | 5154.89 | 1.14 |  | -0.24 | 95
16432 | 91.94 | 326.55 | 10270.58 | 3436.25 | -4426.81 | 1.44 |  | 155.53 | 5248.73 | -1.31 |  | 0.6 | 94
16527 | 93.62 | 326.39 | 10265.97 | 3515.34 | -4479.22 | 1.78 |  | -5.43 | 5343.57 | 1.77 |  | -0.17 | 95
16621 | 91.92 | 327.3 | 10261.43 | 3593.94 | -4530.57 | 2.05 |  | 151.84 | 5437.42 | -1.81 |  | 0.97 | 94
16716 | 89.26 | 327.84 | 10260.45 | 3674.12 | -4581.51 | 2.86 |  | 168.52 | 5532.4 | -2.8 |  | 0.57 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 60.33 | 39.6 | 80 | 349 | 395 | 5258.14 | 4320.93 | 250 | 340.47 | 205 | 145.12 | 18636.36 | 10000
Run | 80.08 | 42.42 | 70 | 323 | 372.21 | 4647.37 | 3686.95 | 250 | 326.95 | 209.79 | 162.47 | 17023.81 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 01/04/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 01/04/2021 |  | 4 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 01/04/2021 |  | 7 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 01/04/2021 |  | 8 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/04/2021 | 00:00 | 00:36 | 0.6 | 16118 | 16212 | 94 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16118.00 t/16212.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5700.00, Tq 20000.00, ROP 156.67
01/04/2021 | 00:36 | 00:42 | 0.1 | 16212 | 16212 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 00:42 | 00:48 | 0.1 | 16212 | 16217 | 5 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16212.00 t/16217.00, w/WOB 30.00,Flow 390.00, RPM 80.00, Press 5800, Tq 21000, ROP 50.00
01/04/2021 | 00:48 | 01:38 | 0.83 | 16217 | 16232 | 15 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/16217.00 t/16232.00, TF , w/WOB 75,Flow 390.00, Press 5300, Tq 0, ROP 18.00
01/04/2021 | 01:38 | 02:06 | 0.47 | 16232 | 16306 | 74 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16232.00 t/16306.00, w/WOB 32,Flow 390.00, RPM 80.00, Press 5800, Tq 21000, ROP 158.57
01/04/2021 | 02:06 | 02:14 | 0.13 | 16306 | 16306 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 02:14 | 02:43 | 0.48 | 16306 | 16401 | 95 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16306.00 t/16401.00, w/WOB 32,Flow 390.00, RPM 80.00, Press 5800, Tq 21000, ROP 196.55
01/04/2021 | 02:43 | 02:50 | 0.12 | 16401 | 16401 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 02:50 | 02:56 | 0.1 | 16401 | 16406 | 5 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16401.00 t/16406.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 50.00
01/04/2021 | 02:56 | 03:40 | 0.73 | 16406 | 16418 | 12 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/16406.00 t/16418.00, TF , w/WOB 75,Flow 390.00, Press 5300, Tq 0, ROP 16.36
01/04/2021 | 03:40 | 04:08 | 0.47 | 16418 | 16495 | 77 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16418.00 t/16495.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 165.00
01/04/2021 | 04:08 | 04:14 | 0.1 | 16495 | 16495 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 04:14 | 04:30 | 0.27 | 16495 | 16545 | 50 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16495.00 t/16545.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 187.50
01/04/2021 | 04:30 | 04:42 | 0.2 | 16545 | 16590 | 45 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16495.00 t/16590.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 475.00
01/04/2021 | 04:42 | 04:50 | 0.13 | 16590 | 16590 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 04:50 | 09:00 | 4.17 | 16590 | 16623 | 33 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/16590.00 t/16623.00, TF , w/WOB 75.00,Flow 390.00, Press 5300.00, Tq 0.00, ROP 7.92
01/04/2021 | 09:00 | 09:35 | 0.58 | 16623 | 16684 | 61 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16623.00 t/16684.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 104.57
01/04/2021 | 09:35 | 09:45 | 0.17 | 16684 | 16684 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 09:45 | 11:45 | 2 | 16684 | 16704 | 20 | LAT2 | 5: BHA #5 (Lateral) | 2J | Slide Drill f/16684.00 t/16704.00, TF , w/WOB 75.00,Flow 390.00, Press 5300.00, Tq 0.00, ROP 10.00
01/04/2021 | 11:45 | 12:20 | 0.58 | 16704 | 16779 | 75 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16704.00 t/16779.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 128.57
01/04/2021 | 12:20 | 12:30 | 0.17 | 16779 | 16779 | 0 | LAT2 | 5: BHA #5 (Lateral) | 10D | Survey & Connection
01/04/2021 | 12:30 | 12:53 | 0.38 | 16779 | 16840 | 61 | LAT2 | 5: BHA #5 (Lateral) | 2K | Rotary Drill f/16779.00 t/16840.00, w/WOB 32.00,Flow 390.00, RPM 80.00, Press 5800.00, Tq 21000.00, ROP 159.13
01/04/2021 | 12:53 | 12:57 | 0.07 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) | 1G | MWD survey @ TD
01/04/2021 | 12:57 | 15:00 | 2.05 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) | 5A | Circulate
01/04/2021 | 15:00 | 19:50 | 4.83 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) | 3D | Backream from 16840 to 13185
01/04/2021 | 19:50 | 20:20 | 0.5 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) |  | Orient toolface @ 110R to pull through sidetrack. Pulled through sidetrack succefully 13185 to 13060
01/04/2021 | 20:20 | 23:00 | 2.67 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) | 3D | Backream from 13060 to 10704
01/04/2021 | 23:00 | 23:30 | 0.5 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) | 6B | Pull out of hole from 10704 to10038
01/04/2021 | 23:30 | 24:00 | 0.5 | 16840 | 16840 | 0 | LAT2 | 5: BHA #5 (Lateral) | 6B | Pull out of hole, laying down drill pipe
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_5_2021_DDR
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33514 / 20DD0326MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Longitude: |  | 96° 46' 58.377" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 01/05/2021 |  |  | Report Time: |  | 00:00-10:30
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 126350
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16840 |  | 13095 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 16840 |  | 16840 |  | OD (in): |  |  |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  |  |  | 3745 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  |  |  | 398 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  |  |  | 3347 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  |  |  | 46.77 / 11.38 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  |  |  | 25.63 |  | SN: |  | 13522001 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  |  |  | 21.13 |  | Bit # |  | 5 |  | PH / Temp(F) | 8.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  |  |  | 158.38 / 15.53 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 10.5 |  | 80 |  | Grade In: |  | New
% Slide: |  |  |  | 10.63 |  | Grade Out:
% Rotary: |  |  |  | 89.37 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold
Jim |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  |  | 5 | 2 |  |  |  |  | 30.99 |  | 31.74
BTI Valve |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.37 |  | 34.11
5" NMPDC |  |  |  | 5 | 2.75 |  |  |  |  | 10.12 |  | 44.23
UBHO Sub |  |  |  | 5.125 | 2.5 |  |  |  |  | 2.49 |  | 46.72
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.61 |  | 77.33
5" NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.16 |  | 108.49
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 26.38 |  | 134.87
X/O- DS42B x XT39P |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.31 |  | 138.18
27 Stands of Drill Pipe |  |  |  | 4.5 | 2 |  |  |  |  | 2556.59 |  | 2694.77
DWS Agitator |  |  |  | 5.25 | 2 |  |  |  |  | 23.86 |  | 2718.63
2718.63
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250020 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 39.6 | 80 | 349 | 395 | 5258.14 | 4320.93 | 250 | 340.47 | 205 | 145.12 | 18636.36 | 10000
Run | 80.08 | 42.42 | 70 | 323 | 372.21 | 4647.37 | 3686.95 | 250 | 326.95 | 209.79 | 162.47 | 17023.81 | 10000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Service |  |  |  |  | 01/05/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 01/05/2021 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/05/2021 | 00:00 | 09:50 | 9.83 | 16840 | 16840 | 0 | ST | 5: BHA #5 (Lateral) | 6B | Pull out of hol laying down drill pipe to lay down tools
01/05/2021 | 09:50 | 10:30 | 0.67 | 16840 | 16840 | 0 | ST | 5: BHA #5 (Lateral) | 6P | Lay down BHA #4. End of job
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 394.82 (Usft)
Well: |  |  | Fat Tire B1H ST01 | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150720 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/12/2020 | Depth In: |  | 105 | Total Drilled: |  | 2975.00 (Usft)
Date Out: |  |  | 12/12/2020 | Depth Out: |  | 3080 | Drilling / Circ Hours: |  | 4.22 / 1.17
Survey Offset: |  |  | 74
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47245 | 13 1/2"- Ulterra - U616S - Jetted - 9x14s | 13.5 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800004 | 8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | 8 | 2 |  | 6 5/8 REG / 6 5/8 REG |  | 37.92 | 39.42
| 3 | SD603913 | 13" - 4 Blade Nortrak Stabilizer (BFF) | 8.188 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 6.9 | 46.32
| 4 | SD52214 | 8" - NMPDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 8.86 | 55.18
| 5 | ZSB775202 | UBHO Sub | 7.75 | 2.813 |  | 6 5/8 REG / 6 5/8 REG |  | 3.11 | 58.29
| 6 | SD50132 | 8" - NMDC | 7.375 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 87.2
| 7 | SD55923 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.54 | 116.74
| 8 | SD116862 | X/O- 4 1/2 IFB x 6 5/8 RegP | 6.563 | 2.875 |  | 4 1/2 IF / 6 5/8 REG |  | 2.78 | 119.52
| 9 | Rig-1 | 9- Joints of HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 275.3 | 394.82
| 10 | [8 empty] | 394.82
Comments
Bit Info= 13 1/2" -Ulterra-U616S SN= 47245 Jets= 9x14's TFA= 1.353 Motor Info= 8", 7/8, 5.9 Stg. @ 1.5? w/ 13" NBS Bit To Bend= 5.45' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | 13 1/2"- Ulterra - U616S - Jetted - 9x14s | 1.35 | Ulterra | U616S | New | 0-0-NO-I-TD | 2975
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  | PDCI / 7/8 5.9 | 5.45 / 1.50 |  | 13 | 8.38 | 0 | 1
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 100 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS | 13 |  | 0 |  |  | 1.5
3 |  |  | 13" - 4 Blade Nortrak Stabilizer (BFF) | 13 |  | 0 |  |  | 39.42

## BHA_2_Intermediate
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2679.06 (Usft)
Well: |  |  | Fat Tire B1H ST01 | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150720 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/13/2020 | Depth In: |  | 3080 | Total Drilled: |  | 7112.00 (Usft)
Date Out: |  |  | 12/16/2020 | Depth Out: |  | 10192 | Drilling / Circ Hours: |  | 25.85 / 14.47
Survey Offset: |  |  | 69 | Gamma Offset: |  | 59
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 54300 | 9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s | 9.875 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800049 | 7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 | 8 | 2 | 1.89 | 6 5/8 REG / 6 5/8 REG |  | 37.67 | 39.17
| 3 | SD52214 | 8" - NMPDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 8.86 | 48.03
| 4 | ZSB775202 | UBHO Sub | 7.75 | 2.813 |  | 6 5/8 REG / 6 5/8 REG |  | 3.11 | 51.14
| 5 | SD50132 | 8" - NMDC | 7.375 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 80.05
| 6 | SD55923 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.54 | 109.59
| 7 | SD108685 | X/O- 4 1/2 XHB x 6 5/8 RegP | 6.5 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.12 | 111.71
| 8 | Rig-3 | 2 Stands of 6 1/2" Drill Collars | 6.5 | 2.875 |  | 4 1/2 XH / 4 1/2 XH |  | 186.78 | 298.49
| 9 | SD4555 | X/O- 4 1/2 IFB x 4 1/2 XHP | 6.625 | 2.5 |  | 4 1/2 IF / 4 1/2 XH |  | 3.04 | 301.53
| 10 | Rig-1 | 9- Joints of HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 275.3 | 576.83
| 11 | Rig-2 | 22 Stands of Drill Pipe | 5 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2071.8 | 2648.63
| 12 | AGHF0675-0062 | NOV- Safety Join / Agitator / Shock Sub | 6.75 | 2.5 |  | 4 1/2 IF / 4 1/2 IF |  | 30.43 | 2679.06
| 13 | [8 empty] | 2679.06
Comments
Bit Info= 9 7/8" -Ulterra-SPL613 SN= 54300 Jets= 6-14's & 3-16's's TFA= 1.491 Motor Info= 8", 7/8, 5.9 Stg. @ 2.00? Slick Bit To Bend= 5.81' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s | 1.49 | Ulterra | SPL613 | New | 0-1-CT-G-X-I-NO-TD | 7112
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  |  | PDCI / 7/8 5.9 | 5.81 / 2.00 |  | 0 | 8.38 | 0 | 1
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 80 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3_Curve_and_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2721.96 (Usft)
Well: |  |  | Fat Tire B1H ST01 | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150720 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/28/2020 | Depth In: |  | 10192 | Total Drilled: |  | 17.00 (Usft)
Date Out: |  |  | 12/29/2020 | Depth Out: |  | 10209 | Drilling / Circ Hours: |  | 0.50 / 5.95
Survey Offset: |  |  | 72 | Gamma Offset: |  | 58
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13522000 | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250025 | 5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 | 5 | 2 | 5.000 / 1.93 | XT 39 / 3 1/2 Reg |  | 33.13 | 33.88
| 3 | Rig1x | BTI Valve | 4.875 | 2.5 |  | XT39 / XT39 |  | 2.37 | 36.25
| 4 | SD56870 | 5" NMPDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 10.12 | 46.37
| 5 | ZSB500025 | UBHO Sub | 5.188 | 2.5 | 5.000 / 1.70 | XT 39 / XT 39 |  | 3.68 | 50.05
| 6 | SD56281 | 5" NMDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 30.61 | 80.66
| 7 | SD56783 | 5" NMDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 31.16 | 111.82
| 8 | DS-MT3X-500-033 | Cougar Thruster | 5 | 2 |  | XT39 / XT39 |  | 26.38 | 138.2
| 9 | SD119310 | X/O- DS42B x XT39P | 5.5 | 2.75 |  | DS42 / XT 39 |  | 3.31 | 141.51
| 10 | Rig2 | 27 Stands of Drill Pipe | 4.5 | 2 |  | DS42 / DS42 |  | 2556.59 | 2698.1
| 11 | PG525-0020 | DWS Agitator | 5.25 | 2 | 5.250 / 1.63 | DS42 / DS42 |  | 23.86 | 2721.96
| 12 | [8 empty] | 2721.96
Comments
Bit Info= 6 3/4" Security - GTD64M SN=13522000 Jets=6-18's TFA= 1.491 PN= 1138553 Motor Info= 5", 6/7, 11.7 Stg. @ 2.12? w/ True Slick Bit To Bend= 4.01' Pad OD= 5 9/16" Rev / Gal= 0.89 Flow Range= 150-350 Gpm Max Diff=2,905
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 1.49 | Halliburton | GTD64M | New |  | 17
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  | PDCI / 6/7 11.7 | 4.01 / 2.12 |  | 0 | 5.56 | 0 | 2905
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
7623 |  |  | 0 | 80 |  | 150-350 | 0.89 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4_Curve_and_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2721.96 (Usft)
Well: |  |  | Fat Tire B1H ST01 | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150720 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 12/29/2020 | Depth In: |  | 10209 | Total Drilled: |  | 4740.00 (Usft)
Date Out: |  |  | 01/01/2021 | Depth Out: |  | 14949 | Drilling / Circ Hours: |  | 33.60 / 4.95
Survey Offset: |  |  | 66 | Gamma Offset: |  | 58
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13509568 | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250025 | 5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 | 5 | 2 | 5.000 / 1.93 | XT 39 / 3 1/2 Reg |  | 33.13 | 33.88
| 3 | Rig1x | BTI Valve | 4.875 | 2.5 |  | XT39 / XT39 |  | 2.37 | 36.25
| 4 | SD56870 | 5" NMPDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 10.12 | 46.37
| 5 | ZSB500025 | UBHO Sub | 5.188 | 2.5 | 5.000 / 1.70 | XT 39 / XT 39 |  | 3.68 | 50.05
| 6 | SD56281 | 5" NMDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 30.61 | 80.66
| 7 | SD56783 | 5" NMDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 31.16 | 111.82
| 8 | DS-MT3X-500-033 | Cougar Thruster | 5 | 2 |  | XT39 / XT39 |  | 26.38 | 138.2
| 9 | SD119310 | X/O- DS42B x XT39P | 5.5 | 2.75 |  | DS42 / XT 39 |  | 3.31 | 141.51
| 10 | Rig2 | 27 Stands of Drill Pipe | 4.5 | 2 |  | DS42 / DS42 |  | 2556.59 | 2698.1
| 11 | PG525-0020 | DWS Agitator | 5.25 | 2 | 5.250 / 1.63 | DS42 / DS42 |  | 23.86 | 2721.96
| 12 | [8 empty] | 2721.96
Comments
Bit Info= 6 3/4" Security - GTD64M SN=13509568 Jets=6-18's TFA= 1.491 PN= 1138553 Motor Info= 5", 6/7, 11.7 Stg. @ 2.12? w/ True Slick Bit To Bend= 4.01' Pad OD= 5 9/16" Rev / Gal= 0.89 Flow Range= 150-350 Gpm Max Diff=2,905
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 1.49 | Security | GTD64M | New |  | 4740
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  | PDCI / 6/7 11.7 | 4.01 / 2.12 |  | 0 | 5.56 | 0 | 2905
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
7623 |  |  | 0 | 80 |  | 150-350 | 0.89 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2718.63 (Usft)
Well: |  |  | Fat Tire B1H ST01 | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1150720 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 01/02/2021 | Depth In: |  | 13095 | Total Drilled: |  | 3745.00 (Usft)
Date Out: |  |  | 01/05/2021 | Depth Out: |  | 16840 | Drilling / Circ Hours: |  | 46.77 / 11.38
Survey Offset: |  |  | 64 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13522001 | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250020 | 5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 | 5 | 2 | 5.000 / 1.87 | XT 39 / 3 1/2 Reg |  | 30.99 | 31.74
| 3 | Rig1x | BTI Valve | 4.875 | 2.5 |  | XT39 / XT39 |  | 2.37 | 34.11
| 4 | SD56870 | 5" NMPDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 10.12 | 44.23
| 5 | ZSB500016 | UBHO Sub | 5.125 | 2.5 | 5.000 / 1.70 | XT 39 / XT 39 |  | 2.49 | 46.72
| 6 | SD56281 | 5" NMDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 30.61 | 77.33
| 7 | SD56783 | 5" NMDC | 5 | 2.75 |  | XT 39 / XT 39 |  | 31.16 | 108.49
| 8 | DS-MT3X-500-033 | Cougar Thruster | 5 | 2 |  | XT39 / XT39 |  | 26.38 | 134.87
| 9 | SD119310 | X/O- DS42B x XT39P | 5.5 | 2.75 |  | DS42 / XT 39 |  | 3.31 | 138.18
| 10 | Rig2 | 27 Stands of Drill Pipe | 4.5 | 2 |  | DS42 / DS42 |  | 2556.59 | 2694.77
| 11 | PG525-0020 | DWS Agitator | 5.25 | 2 | 5.250 / 1.63 | DS42 / DS42 |  | 23.86 | 2718.63
| 12 | [8 empty] | 2718.63
Comments
Bit Info= 6 3/4" Security - GTD64M SN=13522001 Jets=6-18's TFA= 1.491 PN= 1138553 Motor Info= 5", 6/7, 8.8 Stg. @ 2.12? w/ True Slick Bit To Bend= 4.00' Pad OD= 5 1/2" Rev / Gal= 0.68 Flow Range= 150-400 Gpm Max Diff=2,240
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4"- Halliburton GTD64M- Jetted 6-18s | 1.49 | Halliburton | GTD64M | New |  | 3745
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  | PDCI / 6/7 8.8 | 4.00 / 2.12 |  | 0 | 5.5 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Longitude: |  | 96° 46' 58.377" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/12/2020 07:00 |  | SN: |  | PPM800004 |  |  |  | WOB Rotate (klbs): |  | 19.00
Date Out: |  | 12/12/2020 17:30 |  | Description: |  | 8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 105.00 / 3080.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 96.74
Inc In/Out: |  | 0.48 / 13.07 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 882.16
Azi In/Out: |  | 337.95 / 211.02 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 1684.48
Total Drilled (Usft): |  | 2975 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 2219.66
%Slide (Ftg): |  | 11.76 |  | Bit to Bend (Usft): |  | 5.45 |  |  |  | Tq On Btm (kftlbs): |  | 6917.39
%Slide (Time): |  | 29.17 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 350 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 1.23 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 88.24 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 70.91 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2625 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 13.5
Rotary Hours: |  | 2.99 |  | Length (Usft): |  | 37.92 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 4.22 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 1.17 / 10.50 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 284.55 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-0-NO-I-TD
Rot ROP (Usft/hr): |  | 877.93 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 4.22
Avg ROP (Usft/hr): |  | 704.98 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 1.17
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
|  |  |  | 0.00 | [8 empty] | 105
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
74 | [9 empty] | 2 |  | 6.00 / 2.78
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
13 1/2"- Ulterra - U616S - Jetted - 9x14s 1.35 |  |  |  | 47245 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
8" - 7/8, 5.9 Stg. @ 1.50? w/ 13" NBS 0.00 |  |  |  | PPM800004 |  | 8 | 2 |  |  |  | 37.92 | 39.42
13" - 4 Blade Nortrak Stabilizer (BFF) 0.00 |  |  |  | SD603913 |  | 8.188 | 2.875 |  |  |  | 6.9 | 46.32
8" - NMPDC 0.00 |  |  |  | SD52214 |  | 8 | 3.25 |  |  |  | 8.86 | 55.18
UBHO Sub 0.00 |  |  |  | ZSB775202 |  | 7.75 | 2.813 |  |  |  | 3.11 | 58.29
8" - NMDC 0.00 |  |  |  | SD50132 |  | 7.375 | 3.25 |  |  |  | 28.91 | 87.2
8" - NMDC 0.00 |  |  |  | SD55923 |  | 8 | 3.25 |  |  |  | 29.54 | 116.74
X/O- 4 1/2 IFB x 6 5/8 RegP 0.00 |  |  |  | SD116862 |  | 6.563 | 2.875 |  |  |  | 2.78 | 119.52
9- Joints of HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 3 |  |  |  | 275.3 | 394.82
0.00 | [11 empty] | 394.82
Additional Comments
BHA performed as expected, drilled surface section per plan, this was second surface drilled with assembly. At surface, motor drained strong with minimal slack in bearing assembly, no visuable signs of damage to motor at surface. Bit was green.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Longitude: |  | 96° 46' 58.377" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/13/2020 21:00 |  | SN: |  | PPM800049 |  |  |  | WOB Rotate (klbs): |  | 33.00
Date Out: |  | 12/16/2020 06:00 |  | Description: |  | 7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 3080.00 / 10192.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 78.41
Inc In/Out: |  | 13.07 / 13.55 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 776.11
Azi In/Out: |  | 211.02 / 323.57 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 3723.89
Total Drilled (Usft): |  | 7112 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4346.9
%Slide (Ftg): |  | 10.55 |  | Bit to Bend (Usft): |  | 5.81 |  |  |  | Tq On Btm (kftlbs): |  | 16485.23
%Slide (Time): |  | 37.25 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 10000
Slide Drilled (Usft): |  | 750 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 9.63 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 89.45 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 62.75 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6362 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 9.875
Rotary Hours: |  | 16.22 |  | Length (Usft): |  | 37.67 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 25.85 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 14.47 / 57.00 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 77.88 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-CT-G-X-I-NO-TD
Rot ROP (Usft/hr): |  | 392.23 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 25.85
Avg ROP (Usft/hr): |  | 275.13 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 14.47
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
32 / 21 | 17 / 13 | 6 / 5 |  | 0.00 |  | 11 | 10 | 9.3 | 55000 | OBM | 9.4 |  | 227
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 59 | [10 empty] | 0.00 / 7.86
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8"- Ulterra SPL613-Jetted 6-14s & 3-16s 1.49 |  |  |  | 54300 |  | 9.875 | 2 |  |  |  | 1.5 | 1.5
7 3/4" -7/8, 5.9 Stg. @ 2.00? Slick, HPW -.008 0.00 |  |  |  | PPM800049 |  | 8 | 2 |  |  |  | 37.67 | 39.17
8" - NMPDC 0.00 |  |  |  | SD52214 |  | 8 | 3.25 |  |  |  | 8.86 | 48.03
UBHO Sub 0.00 |  |  |  | ZSB775202 |  | 7.75 | 2.813 |  |  |  | 3.11 | 51.14
8" - NMDC 0.00 |  |  |  | SD50132 |  | 7.375 | 3.25 |  |  |  | 28.91 | 80.05
8" - NMDC 0.00 |  |  |  | SD55923 |  | 8 | 3.25 |  |  |  | 29.54 | 109.59
X/O- 4 1/2 XHB x 6 5/8 RegP 0.00 |  |  |  | SD108685 |  | 6.5 | 2.875 |  |  |  | 2.12 | 111.71
2 Stands of 6 1/2" Drill Collars 0.00 |  |  |  | Rig-3 |  | 6.5 | 2.875 |  |  |  | 186.78 | 298.49
X/O- 4 1/2 IFB x 4 1/2 XHP 0.00 |  |  |  | SD4555 |  | 6.625 | 2.5 |  |  |  | 3.04 | 301.53
9- Joints of HWDP 0.00 |  |  |  | Rig-1 |  | 5 | 3 |  |  |  | 275.3 | 576.83
22 Stands of Drill Pipe 0.00 |  |  |  | Rig-2 |  | 5 | 2.75 |  |  |  | 2071.8 | 2648.63
NOV- Safety Join / Agitator / Shock Sub 0.00 |  |  |  | AGHF0675-0062 |  | 6.75 | 2.5 |  |  |  | 30.43 | 2679.06
-1.00 | [11 empty] | 2679.06
Additional Comments
Motor Drained as expected on surface and showed no visible signs of wear w/ no slack in bearings; Bit was green w/ 1 chipped cutter on guage row
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Longitude: |  | 96° 46' 58.377" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Inspect BHA |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/28/2020 08:40 |  | SN: |  | PPM250025 |  |  |  | WOB Rotate (klbs): |  | 33.00
Date Out: |  | 12/29/2020 06:40 |  | Description: |  | 5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10192.00 / 10209.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 78.41
Inc In/Out: |  | 13.55 / 14.16 |  | Model: |  | 6/7 11.7 |  |  |  | Flow Rate (gpm): |  | 776.11
Azi In/Out: |  | 323.56 / 322.66 |  | Lobes / Stages: |  | 6/7 / 11.70 |  |  |  | Off Btm Press (psi): |  | 3723.89
Total Drilled (Usft): |  | 17 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4346.9
%Slide (Ftg): |  | 41.18 |  | Bit to Bend (Usft): |  | 4.01 |  |  |  | Tq On Btm (kftlbs): |  | 16485.23
%Slide (Time): |  | 84.00 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 10000
Slide Drilled (Usft): |  | 7 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 0.42 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 58.82 |  | Kickpad OD (in): |  | 5.563 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 16.00 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 10 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0.08 |  | Length (Usft): |  | 33.13 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 0.50 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 5.95 / 22.00 |  | Rev per Gal: |  | 0.89 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 16.67 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 125 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 0.50
Avg ROP (Usft/hr): |  | 34 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 5.95
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
32 / 21 | 17 / 13 | 6 / 5 |  | 0.00 |  | 11 | 10 | 9.3 | 55000 | OBM | 9.4 |  | 230
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
72 | 58 | [10 empty] | 0.00 / 15.91
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s 1.49 |  |  |  | 13522000 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 0.00 |  |  |  | PPM250025 |  | 5 | 2 |  |  |  | 33.13 | 33.88
BTI Valve 0.00 |  |  |  | Rig1x |  | 4.875 | 2.5 |  |  |  | 2.37 | 36.25
5" NMPDC 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 10.12 | 46.37
UBHO Sub 0.00 |  |  |  | ZSB500025 |  | 5.188 | 2.5 |  |  |  | 3.68 | 50.05
5" NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.61 | 80.66
5" NMDC 0.00 |  |  |  | SD56783 |  | 5 | 2.75 |  |  |  | 31.16 | 111.82
Cougar Thruster 0.00 |  |  |  | DS-MT3X-500-033 |  | 5 | 2 |  |  |  | 26.38 | 138.2
X/O- DS42B x XT39P 0.00 |  |  |  | SD119310 |  | 5.5 | 2.75 |  |  |  | 3.31 | 141.51
27 Stands of Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 2 |  |  |  | 2556.59 | 2698.1
DWS Agitator 0.00 |  |  |  | PG525-0020 |  | 5.25 | 2 |  |  |  | 23.86 | 2721.96
-1.00 | [11 empty] | 2721.96
Additional Comments
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Longitude: |  | 96° 46' 58.377" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 12/29/2020 07:20 |  | SN: |  | PPM250025 |  |  |  | WOB Rotate (klbs): |  | 42.00
Date Out: |  | 01/01/2021 15:30 |  | Description: |  | 5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10209.00 / 14949.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 70.00
Inc In/Out: |  | 14.16 / 93.68 |  | Model: |  | 6/7 11.7 |  |  |  | Flow Rate (gpm): |  | 372.21
Azi In/Out: |  | 322.65 / 326.09 |  | Lobes / Stages: |  | 6/7 / 11.70 |  |  |  | Off Btm Press (psi): |  | 3686.95
Total Drilled (Usft): |  | 4740 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4647.37
%Slide (Ftg): |  | 19.37 |  | Bit to Bend (Usft): |  | 4.01 |  |  |  | Tq On Btm (kftlbs): |  | 17023.81
%Slide (Time): |  | 40.86 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 10000
Slide Drilled (Usft): |  | 918 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 13.73 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 80.63 |  | Kickpad OD (in): |  | 5.563 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 59.14 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 3822 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 19.87 |  | Length (Usft): |  | 33.13 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 33.60 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 4.95 / 80.17 |  | Rev per Gal: |  | 0.89 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 66.86 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 192.35 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 33.60
Avg ROP (Usft/hr): |  | 141.07 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 4.95
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  | 0.00 |  | 1 | 1 | 8.4 | 300 | WBM | 0.4 |  | 240
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
66 | 58 | [10 empty] | 0.00 / 19.14
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s 1.49 |  |  |  | 13509568 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
5 1/2", - 6/7, 11.7 Stg. @ 2.12? Slick- HS88 +.014 0.00 |  |  |  | PPM250025 |  | 5 | 2 |  |  |  | 33.13 | 33.88
BTI Valve 0.00 |  |  |  | Rig1x |  | 4.875 | 2.5 |  |  |  | 2.37 | 36.25
5" NMPDC 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 10.12 | 46.37
UBHO Sub 0.00 |  |  |  | ZSB500025 |  | 5.188 | 2.5 |  |  |  | 3.68 | 50.05
5" NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.61 | 80.66
5" NMDC 0.00 |  |  |  | SD56783 |  | 5 | 2.75 |  |  |  | 31.16 | 111.82
Cougar Thruster 0.00 |  |  |  | DS-MT3X-500-033 |  | 5 | 2 |  |  |  | 26.38 | 138.2
X/O- DS42B x XT39P 0.00 |  |  |  | SD119310 |  | 5.5 | 2.75 |  |  |  | 3.31 | 141.51
27 Stands of Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 2 |  |  |  | 2556.59 | 2698.1
DWS Agitator 0.00 |  |  |  | PG525-0020 |  | 5.25 | 2 |  |  |  | 23.86 | 2721.96
-1.00 | [11 empty] | 2721.96
Additional Comments
Put in slide from 14927 to 14942 @ 27 hr.Attempted to get back to bottom with several diff pressure spikes. At 14,944 MD, torque began to increase to 24k (stalling out top drive); Decision was made to perform wiper trip (10 stands); while reaming back to bottom @ 14,925 MD, drill string began to take weight and torque was at 24k while diff psi was 2000; P/U above 14,925 and psi and torque stabilized to normal; attempt to return to bottom and at same spot torque began to climb along with diff; Eased way to bottom and attempted to drill; Was unable to drill; Decision was made by operator to TOH to inspect and change out BHA. At surface, motor was missing lower end from stator tube break down.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1150720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33514 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 7' 37.765" N |  |  | Well: |  | Fat Tire B1H ST01
|  |  |  | Longitude: |  | 96° 46' 58.377" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 01/02/2021 02:30 |  | SN: |  | PPM250020 |  |  |  | WOB Rotate (klbs): |  | 42.00
Date Out: |  | 01/05/2021 10:30 |  | Description: |  | 5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 13095.00 / 16840.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 70.00
Inc In/Out: |  | 90.88 / 89.60 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 372.21
Azi In/Out: |  | 332.46 / 327.80 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 3686.95
Total Drilled (Usft): |  | 3745 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4647.37
%Slide (Ftg): |  | 10.63 |  | Bit to Bend (Usft): |  | 4 |  |  |  | Tq On Btm (kftlbs): |  | 17023.81
%Slide (Time): |  | 54.80 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 10000
Slide Drilled (Usft): |  | 398 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 25.63 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 89.37 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 45.20 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 3347 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 21.14 |  | Length (Usft): |  | 30.99 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 46.77 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 11.38 / 80.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 15.53 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 158.33 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 46.77
Avg ROP (Usft/hr): |  | 80.07 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 11.38
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  | 0.00 |  | 1 | 1 | 8.4 | 300 | WBM | 0.4 |  | 214
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
64 | 56 | [10 empty] | 0.00 / 5.54
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4"- Halliburton GTD64M- Jetted 6-18s 1.49 |  |  |  | 13522001 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
5 1/2", - 6/7, 8.8 Stg. @ 2.12? Slick- HS88 +.013 0.00 |  |  |  | PPM250020 |  | 5 | 2 |  |  |  | 30.99 | 31.74
BTI Valve 0.00 |  |  |  | Rig1x |  | 4.875 | 2.5 |  |  |  | 2.37 | 34.11
5" NMPDC 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 10.12 | 44.23
UBHO Sub 0.00 |  |  |  | ZSB500016 |  | 5.125 | 2.5 |  |  |  | 2.49 | 46.72
5" NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.61 | 77.33
5" NMDC 0.00 |  |  |  | SD56783 |  | 5 | 2.75 |  |  |  | 31.16 | 108.49
Cougar Thruster 0.00 |  |  |  | DS-MT3X-500-033 |  | 5 | 2 |  |  |  | 26.38 | 134.87
X/O- DS42B x XT39P 0.00 |  |  |  | SD119310 |  | 5.5 | 2.75 |  |  |  | 3.31 | 138.18
27 Stands of Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 2 |  |  |  | 2556.59 | 2694.77
DWS Agitator 0.00 |  |  |  | PG525-0020 |  | 5.25 | 2 |  |  |  | 23.86 | 2718.63
-1.00 | [11 empty] | 2718.63
Additional Comments
BHA performed as expected. Sidetracked well and drilled lateral until TD. BHA was subject to 204 water base. Drilled lateral with no returns. Controlled drilled due to no returns. Drilling torque while drilling was 17-20k. At surface motor drained, bearing gap was within tollerance, no visuable signs of damage to motor at surface.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #1 (Surface) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2975
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 350
Well Name: |  |  |  |  | Fat Tire B1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 74.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 328.33 |  | Rotate: |  | 2625
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/12/2020 | 07:00 | 07:02 | 0.033333 | 105 | 212 | 107 | Rotate |  | 138 | 0.63 | 337.95 | 138 | 0.7 | -0.28 | 0.7 | 0.46 |  |  | 5 | 50 | 480 | 2500 | 3209.99 | 600 | 550 | 50 | 70 | 60 | 60 | 60
12/12/2020 | 07:05 | 07:16 | 0.18333 | 212 | 303 | 91 | Rotate |  | 229 | 0.31 | 324.62 | 228.99 | 1.37 | -0.62 | 1.37 | 0.37 |  |  | 5 | 60 | 675 | 2700 | 496.36 | 900 | 750 | 150 | 70 | 60 | 60 | 60
12/12/2020 | 07:27 | 07:28 | 0.016667 | 303 | 320 | 17 | Rotate |  | 320 | 0.45 | 239.48 | 319.99 | 1.39 | -1.07 | 1.39 | 0.58 |  |  | 5 | 70 | 770 | 3200 | 1020 | 1200 | 1000 | 200 | 70 | 60 | 60 | 60
12/12/2020 | 07:28 | 07:36 | 0.13333 | 320 | 335 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 2; Drilling Parameters FLOW: 770; Drilling Parameters ROP: 112.5 | 1050 | 1000 | 50 | 70 | 60 | 60 | 60
12/12/2020 | 07:36 | 07:42 | 0.1 | 335 | 394 | 59 | Rotate | Drilling Parameters WOB: 7; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 770; Drilling Parameters Tq: 3200; Drilling Parameters ROP: 590 | 1200 | 1000 | 200 | 70 | 60 | 60 | 60
12/12/2020 | 07:47 | 07:58 | 0.18333 | 394 | 489 | 95 | Rotate |  | 415 | 0.68 | 204.67 | 414.99 | 0.69 | -1.62 | 0.69 | 0.42 |  |  | 7 | 100 | 900 | 4600 | 518.18 | 1800 | 1400 | 400 | 70 | 70 | 70 | 70
12/12/2020 | 08:03 | 08:10 | 0.11667 | 489 | 584 | 95 | Rotate |  | 510 | 0.82 | 216.67 | 509.98 | -0.37 | -2.26 | -0.37 | 0.22 |  |  | 12 | 100 | 900 | 4600 | 814.29 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 08:15 | 08:16 | 0.016667 | 584 | 590 | 6 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 360 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 08:16 | 08:28 | 0.2 | 590 | 610 | 20 | Slide | 0 | 604 | 2.02 | 213.51 | 603.95 | -2.29 | -3.58 | -2.29 | 1.28 |  |  | 2 |  | 900 |  | 100 | 1500 | 1400 | 100 | 91 | 70 | 70 | 70
12/12/2020 | 08:28 | 08:33 | 0.083333 | 610 | 678 | 68 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 816 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 08:39 | 08:40 | 0.016667 | 678 | 680 | 2 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 120 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 08:40 | 08:45 | 0.083333 | 680 | 700 | 20 | Slide | 0 | 699 | 3.05 | 217.55 | 698.86 | -5.69 | -6.04 | -5.69 | 1.1 |  |  | 7 |  | 900 |  | 240 | 1500 | 1400 | 100 | 91 | 70 | 70 | 70
12/12/2020 | 08:45 | 08:49 | 0.066667 | 700 | 773 | 73 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 1095 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 08:55 | 08:56 | 0.016667 | 773 | 780 | 7 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 420 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 08:56 | 09:00 | 0.066667 | 780 | 805 | 25 | Slide | 0 | 793 | 4.56 | 214.46 | 792.65 | -10.76 | -9.68 | -10.76 | 1.62 |  |  | 7 |  | 900 |  | 375 | 1500 | 1400 | 100 | 91 | 70 | 70 | 70
12/12/2020 | 09:00 | 09:03 | 0.05 | 805 | 867 | 62 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 1240 | 1800 | 1400 | 400 | 91 | 70 | 70 | 70
12/12/2020 | 09:08 | 09:09 | 0.016667 | 867 | 875 | 8 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 480 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:09 | 09:12 | 0.05 | 875 | 905 | 30 | Slide | 0 | 887 | 5.68 | 216.2 | 886.27 | -17.59 | -14.54 | -17.59 | 1.2 |  |  | 12 |  | 900 |  | 600 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 09:12 | 09:15 | 0.05 | 905 | 961 | 56 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 1120 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:20 | 09:21 | 0.016667 | 961 | 975 | 14 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 840 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:21 | 09:26 | 0.083333 | 975 | 1015 | 40 | Slide | 0 | 982 | 7.76 | 221.43 | 980.61 | -26.2 | -21.57 | -26.2 | 2.28 |  |  | 12 |  | 900 |  | 480 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 09:26 | 09:29 | 0.05 | 1015 | 1056 | 41 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 820 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:34 | 09:35 | 0.016667 | 1056 | 1065 | 9 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 540 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:35 | 09:40 | 0.083333 | 1065 | 1105 | 40 | Slide | 0 | 1075 | 10.05 | 223.01 | 1072.49 | -36.84 | -31.26 | -36.84 | 2.48 |  |  | 12 |  | 900 |  | 480 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 09:40 | 09:43 | 0.05 | 1105 | 1149 | 44 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 880 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:48 | 09:49 | 0.016667 | 1149 | 1160 | 11 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 660 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 09:49 | 09:54 | 0.083333 | 1160 | 1200 | 40 | Slide | 0 | 1169 | 12.66 | 222.8 | 1164.64 | -50.4 | -43.85 | -50.4 | 2.78 |  |  | 12 |  | 900 |  | 480 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 09:54 | 09:56 | 0.033333 | 1200 | 1243 | 43 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 1290 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 10:01 | 10:02 | 0.016667 | 1243 | 1255 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 720 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 10:02 | 10:09 | 0.11667 | 1255 | 1295 | 40 | Slide | 0 | 1263 | 14.44 | 223.01 | 1256.02 | -66.53 | -58.85 | -66.53 | 1.89 |  |  | 12 |  | 900 |  | 342.86 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 10:09 | 10:11 | 0.033333 | 1295 | 1337 | 42 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 1260 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 10:15 | 10:16 | 0.016667 | 1337 | 1350 | 13 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 780 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 10:16 | 10:21 | 0.083333 | 1350 | 1365 | 15 | Slide | 0 | 1356 | 15 | 221.25 | 1345.96 | -84.05 | -74.69 | -84.05 | 0.77 |  |  | 12 |  | 900 |  | 180 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 10:21 | 10:24 | 0.05 | 1365 | 1430 | 65 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 1300 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 10:30 | 10:31 | 0.016667 | 1430 | 1440 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 4600; Drilling Parameters ROP: 600 | 2400 | 1700 | 700 | 91 | 85 | 80 | 75
12/12/2020 | 10:31 | 10:35 | 0.066667 | 1440 | 1470 | 30 | Slide | 0 | 1450 | 16.38 | 218.32 | 1436.46 | -103.6 | -90.93 | -103.6 | 1.69 |  |  | 12 |  | 900 |  | 450 | 1820 | 1700 | 120 | 91 | 85 | 80 | 75
12/12/2020 | 10:35 | 10:37 | 0.033333 | 1470 | 1524 | 54 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 1620 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 10:42 | 10:47 | 0.083333 | 1524 | 1618 | 94 | Rotate |  | 1544 | 16.85 | 219.29 | 1526.54 | -124.54 | -107.78 | -124.54 | 0.58 |  |  | 28 | 100 | 900 | 10000 | 1128 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 10:52 | 10:57 | 0.083333 | 1618 | 1712 | 94 | Rotate |  | 1638 | 15.88 | 218.67 | 1616.73 | -145.13 | -124.44 | -145.13 | 1.05 |  |  | 28 | 100 | 900 | 10000 | 1128 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 11:02 | 11:07 | 0.083333 | 1712 | 1805 | 93 | Rotate |  | 1731 | 15.19 | 220.33 | 1706.33 | -164.35 | -140.28 | -164.35 | 0.88 |  |  | 28 | 100 | 900 | 10000 | 1116 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 11:12 | 11:13 | 0.016667 | 1805 | 1815 | 10 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 600 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 11:13 | 11:24 | 0.18333 | 1815 | 1850 | 35 | Slide | 0 | 1826 | 15.49 | 219.13 | 1797.95 | -183.68 | -156.34 | -183.68 | 0.46 |  |  | 15 |  | 900 |  | 190.91 | 2150 | 2000 | 150 | 98 | 95 | 85 | 75
12/12/2020 | 11:24 | 11:26 | 0.033333 | 1850 | 1900 | 50 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 1500 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 11:31 | 11:37 | 0.1 | 1900 | 1994 | 94 | Rotate |  | 1920 | 15.93 | 216.98 | 1888.43 | -203.72 | -172.02 | -203.72 | 0.78 |  |  | 28 | 100 | 900 | 10000 | 940 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 11:42 | 11:46 | 0.066667 | 1994 | 2087 | 93 | Rotate |  | 2013 | 15.41 | 219.32 | 1977.98 | -223.48 | -187.53 | -223.48 | 0.88 |  |  | 28 | 100 | 900 | 10000 | 1395 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 11:51 | 11:57 | 0.1 | 2087 | 2182 | 95 | Rotate |  | 2108 | 14.91 | 218.37 | 2069.67 | -242.82 | -203.11 | -242.82 | 0.59 |  |  | 28 | 100 | 900 | 10000 | 950 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 12:02 | 12:10 | 0.13333 | 2182 | 2277 | 95 | Rotate |  | 2203 | 14.68 | 215.42 | 2161.52 | -262.21 | -217.67 | -262.21 | 0.83 |  |  | 28 | 100 | 900 | 10000 | 712.5 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 12:20 | 12:21 | 0.016667 | 2277 | 2285 | 8 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 480 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 12:21 | 12:36 | 0.25 | 2285 | 2325 | 40 | Rotate |  | 2297 | 14.7 | 216.61 | 2252.45 | -281.49 | -231.69 | -281.49 | 0.32 |  |  | 28 | 100 | 900 | 10000 | 160 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 12:36 | 12:40 | 0.066667 | 2325 | 2371 | 46 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 690 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 12:45 | 12:49 | 0.066667 | 2371 | 2466 | 95 | Rotate |  | 2392 | 15.6 | 217.47 | 2344.15 | -301.31 | -246.65 | -301.31 | 0.98 |  |  | 28 | 100 | 900 | 10000 | 1425 | 2800 | 2000 | 800 | 98 | 95 | 85 | 75
12/12/2020 | 12:55 | 13:00 | 0.083333 | 2466 | 2560 | 94 | Rotate |  | 2486 | 14.58 | 216.92 | 2434.91 | -320.8 | -261.45 | -320.8 | 1.1 |  |  | 30 | 100 | 900 | 10000 | 1128 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100
12/12/2020 | 13:05 | 13:08 | 0.05 | 2560 | 2654 | 94 | Rotate |  | 2580 | 14.81 | 215.53 | 2525.83 | -340.04 | -275.53 | -340.04 | 0.45 |  |  | 30 | 100 | 900 | 10000 | 1880 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100
12/12/2020 | 13:13 | 13:18 | 0.083333 | 2654 | 2748 | 94 | Rotate |  | 2674 | 14.23 | 214.6 | 2616.83 | -359.32 | -289.08 | -359.32 | 0.66 |  |  | 30 | 100 | 900 | 10000 | 1128 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100
12/12/2020 | 13:23 | 13:30 | 0.11667 | 2748 | 2842 | 94 | Rotate |  | 2768 | 14.22 | 212.02 | 2707.95 | -378.62 | -301.76 | -378.62 | 0.67 |  |  | 30 | 100 | 900 | 10000 | 805.71 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100
12/12/2020 | 13:35 | 13:42 | 0.11667 | 2842 | 2936 | 94 | Rotate |  | 2862 | 12.96 | 211.41 | 2799.31 | -397.41 | -313.37 | -397.41 | 1.35 |  |  | 30 | 100 | 900 | 10000 | 805.71 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100
12/12/2020 | 13:47 | 13:51 | 0.066667 | 2936 | 3030 | 94 | Rotate |  | 2956 | 12.23 | 209.99 | 2891.05 | -415.03 | -323.84 | -415.03 | 0.84 |  |  | 30 | 100 | 900 | 10000 | 1410 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100
12/12/2020 | 13:56 | 14:00 | 0.066667 | 3030 | 3080 | 50 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 750 | 2800 | 2000 | 800 | 105 | 120 | 110 | 100

## BHA_2_Intermediate_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #2 (Intermediate) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7112
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 750
Well Name: |  |  |  |  | Fat Tire B1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 59.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 328.33 |  | Rotate: |  | 6362
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/14/2020 | 01:15 | 01:20 | 0.083333 | 3080 | 3090 | 10 | Rotate | Drilling Parameters WOB: 16; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 120 | 1500 | 1200 | 300 | 96 | 140 | 132 | 130
12/14/2020 | 01:50 | 02:00 | 0.16667 | 3090 | 3149 | 59 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 354 | 1500 | 1200 | 300 | 96 | 140 | 132 | 130
12/14/2020 | 02:10 | 02:20 | 0.16667 | 3149 | 3174 | 25 | Slide | 0 | 3174 | 14.6 | 212.59 | 3103.47 | -456.97 | -348.94 | -456.97 | 1.68 |  |  | 25 |  | 500 |  | 150 | 1500 | 1200 | 300 | 96 | 140 | 132 | 130
12/14/2020 | 02:20 | 02:35 | 0.25 | 3174 | 3243 | 69 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 500; Drilling Parameters Tq: 7500; Drilling Parameters ROP: 276 | 1500 | 1200 | 300 | 96 | 140 | 132 | 130
12/14/2020 | 02:45 | 02:50 | 0.083333 | 3243 | 3258 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 180 | 2900 | 2700 | 200 | 102 | 152 | 140 | 135
12/14/2020 | 02:50 | 02:55 | 0.083333 | 3258 | 3336 | 78 | Rotate |  | 3267 | 18.1 | 217.51 | 3192.7 | -478.32 | -364.06 | -478.32 | 4.04 |  |  | 28 | 80 | 680 | 8200 | 936 | 3100 | 2700 | 400 | 102 | 152 | 140 | 135
12/14/2020 | 03:00 | 03:05 | 0.083333 | 3336 | 3430 | 94 | Rotate |  | 3361 | 18.2 | 217.93 | 3282.03 | -501.48 | -381.97 | -501.48 | 0.18 |  |  | 35 | 80 | 750 | 12000 | 1128 | 3700 | 3200 | 500 | 105 | 152 | 140 | 135
12/14/2020 | 03:10 | 03:20 | 0.16667 | 3430 | 3524 | 94 | Rotate |  | 3455 | 18.41 | 216.66 | 3371.27 | -524.96 | -399.86 | -524.96 | 0.48 |  |  | 35 | 80 | 750 | 12000 | 564 | 3700 | 3200 | 500 | 105 | 152 | 140 | 135
12/14/2020 | 03:25 | 03:32 | 0.11667 | 3524 | 3617 | 93 | Rotate |  | 3548 | 18.92 | 215.61 | 3459.38 | -549 | -417.4 | -549 | 0.66 |  |  | 35 | 80 | 750 | 12000 | 797.14 | 3700 | 3200 | 500 | 105 | 152 | 140 | 135
12/14/2020 | 03:38 | 03:40 | 0.033333 | 3617 | 3625 | 8 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 240 | 3700 | 3200 | 500 | 105 | 152 | 140 | 135
12/14/2020 | 03:40 | 03:50 | 0.16667 | 3625 | 3640 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 90 | 3700 | 3200 | 500 | 116 | 162 | 150 | 140
12/14/2020 | 03:50 | 03:55 | 0.083333 | 3640 | 3711 | 71 | Rotate |  | 3642 | 17.9 | 212.61 | 3548.57 | -573.56 | -434.06 | -573.56 | 1.48 |  |  | 35 | 80 | 750 | 12000 | 852 | 3700 | 3200 | 500 | 116 | 162 | 150 | 140
12/14/2020 | 04:00 | 04:08 | 0.13333 | 3711 | 3805 | 94 | Rotate |  | 3736 | 17.53 | 211.35 | 3638.11 | -597.82 | -449.21 | -597.82 | 0.57 |  |  | 35 | 80 | 750 | 12000 | 705 | 3700 | 3200 | 500 | 116 | 162 | 150 | 140
12/14/2020 | 04:12 | 04:15 | 0.05 | 3805 | 3808 | 3 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 60 | 3700 | 3200 | 500 | 116 | 162 | 150 | 140
12/14/2020 | 04:15 | 04:19 | 0.066667 | 3808 | 3823 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 225 | 3400 | 3200 | 200 | 116 | 162 | 150 | 140
12/14/2020 | 04:19 | 04:25 | 0.1 | 3823 | 3898 | 75 | Rotate |  | 3829 | 15.79 | 215.8 | 3727.21 | -620.05 | -463.9 | -620.05 | 2.32 |  |  | 35 | 80 | 750 | 12000 | 750 | 3700 | 3200 | 500 | 116 | 162 | 150 | 140
12/14/2020 | 04:30 | 04:38 | 0.13333 | 3898 | 3992 | 94 | Rotate |  | 3923 | 15 | 215.4 | 3817.84 | -640.34 | -478.43 | -640.34 | 0.85 |  |  | 35 | 80 | 750 | 12000 | 705 | 3700 | 3200 | 500 | 122 | 162 | 150 | 140
12/14/2020 | 04:44 | 04:45 | 0.016667 | 3992 | 3998 | 6 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 360 | 3700 | 3200 | 500 | 125 | 162 | 150 | 140
12/14/2020 | 04:45 | 04:50 | 0.083333 | 3998 | 4010 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 144 | 3400 | 3200 | 200 | 125 | 162 | 145 | 140
12/14/2020 | 04:50 | 04:58 | 0.13333 | 4010 | 4085 | 75 | Rotate |  | 4016 | 14.81 | 221.34 | 3907.71 | -659.07 | -493.26 | -659.07 | 1.65 |  |  | 35 | 80 | 750 | 12500 | 562.5 | 3700 | 3200 | 500 | 127 | 162 | 145 | 140
12/14/2020 | 05:02 | 05:08 | 0.1 | 4085 | 4179 | 94 | Rotate |  | 4110 | 14.43 | 223.48 | 3998.67 | -676.59 | -509.25 | -676.59 | 0.7 |  |  | 34 | 80 | 750 | 12500 | 940 | 3800 | 3200 | 600 | 127 | 162 | 145 | 140
12/14/2020 | 05:12 | 05:19 | 0.11667 | 4179 | 4273 | 94 | Rotate |  | 4204 | 14.32 | 222.61 | 4089.73 | -693.65 | -525.18 | -693.65 | 0.26 |  |  | 34 | 80 | 750 | 13000 | 805.71 | 3800 | 3200 | 600 | 132 | 162 | 145 | 140
12/14/2020 | 05:22 | 05:30 | 0.13333 | 4273 | 4367 | 94 | Rotate |  | 4298 | 13.92 | 223.2 | 4180.89 | -710.44 | -540.79 | -710.44 | 0.45 |  |  | 36 | 80 | 750 | 13000 | 705 | 3800 | 3300 | 500 | 135 | 162 | 145 | 140
12/14/2020 | 05:34 | 05:36 | 0.033333 | 4367 | 4374 | 7 | Rotate | Drilling Parameters WOB: 36; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 750; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 210 | 3800 | 3300 | 500 | 135 | 162 | 145 | 140
12/14/2020 | 05:36 | 05:42 | 0.1 | 4374 | 4386 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 750; Drilling Parameters ROP: 120 | 3500 | 3300 | 200 | 137 | 162 | 145 | 140
12/14/2020 | 05:42 | 05:48 | 0.1 | 4386 | 4461 | 75 | Rotate |  | 4392 | 14.87 | 221.99 | 4271.93 | -727.65 | -556.6 | -727.65 | 1.06 |  |  | 36 | 80 | 750 | 13000 | 750 | 3800 | 3300 | 500 | 137 | 162 | 145 | 140
12/14/2020 | 05:52 | 06:04 | 0.2 | 4461 | 4553 | 92 | Rotate |  | 4484 | 15.24 | 222.04 | 4360.78 | -745.4 | -572.59 | -745.4 | 0.4 |  |  | 40 | 80 | 800 | 13000 | 460 | 4700 | 3800 | 900 | 150 | 162 | 145 | 140
12/14/2020 | 06:10 | 06:17 | 0.11667 | 4553 | 4647 | 94 | Rotate |  | 4578 | 14.55 | 221.22 | 4451.62 | -763.46 | -588.65 | -763.46 | 0.77 |  |  | 40 | 80 | 800 | 13000 | 805.71 | 4700 | 3800 | 900 | 150 | 162 | 145 | 140
12/14/2020 | 06:22 | 06:24 | 0.033333 | 4647 | 4660 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 390 | 4700 | 3800 | 900 | 150 | 162 | 145 | 140
12/14/2020 | 06:24 | 06:32 | 0.13333 | 4660 | 4680 | 20 | Slide | 0 | 4673 | 15.55 | 221.82 | 4543.36 | -781.93 | -605 | -781.93 | 1.07 |  |  | 18 |  | 800 |  | 150 | 4200 | 3800 | 400 | 150 | 162 | 145 | 140
12/14/2020 | 06:32 | 06:38 | 0.1 | 4680 | 4742 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 620 | 4700 | 3800 | 900 | 150 | 162 | 145 | 140
12/14/2020 | 06:42 | 06:48 | 0.1 | 4742 | 4837 | 95 | Rotate |  | 4768 | 16.31 | 220.66 | 4634.71 | -801.54 | -622.19 | -801.54 | 0.87 |  |  | 40 | 80 | 800 | 13000 | 950 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 06:54 | 06:59 | 0.083333 | 4837 | 4931 | 94 | Rotate |  | 4862 | 15.24 | 221.43 | 4725.17 | -820.81 | -638.96 | -820.81 | 1.16 |  |  | 40 | 80 | 800 | 13000 | 1128 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 07:05 | 07:11 | 0.1 | 4931 | 5025 | 94 | Rotate |  | 4956 | 15.04 | 221.89 | 4815.9 | -839.16 | -655.28 | -839.16 | 0.25 |  |  | 40 | 80 | 800 | 13000 | 940 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 07:15 | 07:23 | 0.13333 | 5025 | 5118 | 93 | Rotate |  | 5049 | 14.81 | 220.4 | 4905.77 | -857.19 | -671.04 | -857.19 | 0.48 |  |  | 40 | 80 | 800 | 13000 | 697.5 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 07:28 | 07:36 | 0.13333 | 5118 | 5213 | 95 | Rotate |  | 5144 | 13.97 | 219.89 | 4997.79 | -875.24 | -686.26 | -875.24 | 0.89 |  |  | 40 | 80 | 800 | 13000 | 712.5 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 07:40 | 07:42 | 0.033333 | 5213 | 5225 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 360 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 07:42 | 07:51 | 0.15 | 5225 | 5245 | 20 | Slide | 0 | 5238 | 15.06 | 218.26 | 5088.78 | -893.53 | -701.1 | -893.53 | 1.24 |  |  | 18 |  | 800 |  | 133.33 | 4200 | 3800 | 400 | 150 | 185 | 155 | 145
12/14/2020 | 07:51 | 07:57 | 0.1 | 5245 | 5307 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 620 | 4700 | 3800 | 900 | 150 | 185 | 155 | 145
12/14/2020 | 08:02 | 08:10 | 0.13333 | 5307 | 5401 | 94 | Rotate |  | 5332 | 15.73 | 218.58 | 5179.41 | -913.08 | -716.61 | -913.08 | 0.72 |  |  | 40 | 80 | 800 | 16000 | 705 | 4700 | 3800 | 900 | 156 | 185 | 155 | 145
12/14/2020 | 08:15 | 08:21 | 0.1 | 5401 | 5494 | 93 | Rotate |  | 5425 | 15.83 | 217.5 | 5268.91 | -933 | -732.19 | -933 | 0.33 |  |  | 40 | 80 | 800 | 16000 | 930 | 4700 | 3800 | 900 | 156 | 185 | 155 | 145
12/14/2020 | 08:26 | 08:34 | 0.13333 | 5494 | 5588 | 94 | Rotate |  | 5519 | 14.44 | 217.89 | 5359.64 | -952.42 | -747.2 | -952.42 | 1.48 |  |  | 40 | 80 | 800 | 16000 | 705 | 4700 | 3800 | 900 | 156 | 185 | 155 | 145
12/14/2020 | 08:40 | 08:46 | 0.1 | 5588 | 5682 | 94 | Rotate |  | 5613 | 13.48 | 216.63 | 5450.87 | -970.46 | -760.93 | -970.46 | 1.07 |  |  | 40 | 80 | 800 | 16000 | 940 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 08:51 | 08:56 | 0.083333 | 5682 | 5695 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 156 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 08:56 | 09:12 | 0.26667 | 5695 | 5725 | 30 | Slide | 0 | 5706 | 13.77 | 217.84 | 5541.25 | -987.9 | -774.19 | -987.9 | 0.44 |  |  | 20 |  | 800 |  | 112.5 | 4200 | 3800 | 400 | 165 | 220 | 180 | 150
12/14/2020 | 09:12 | 09:21 | 0.15 | 5725 | 5775 | 50 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 333.33 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 09:26 | 09:28 | 0.033333 | 5775 | 5785 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 300 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 09:28 | 09:47 | 0.31667 | 5785 | 5810 | 25 | Slide | 0 | 5800 | 16.89 | 218.96 | 5631.89 | -1007.36 | -789.64 | -1007.36 | 3.33 |  |  | 20 |  | 800 |  | 78.95 | 4200 | 3800 | 400 | 165 | 220 | 180 | 150
12/14/2020 | 09:47 | 09:58 | 0.18333 | 5810 | 5869 | 59 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 321.82 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 10:03 | 10:17 | 0.23333 | 5869 | 5964 | 95 | Rotate |  | 5895 | 17.56 | 220.11 | 5722.63 | -1029.05 | -807.55 | -1029.05 | 0.79 |  |  | 40 | 80 | 800 | 16000 | 407.14 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 10:22 | 10:33 | 0.18333 | 5964 | 6058 | 94 | Rotate |  | 5989 | 17.19 | 220.59 | 5812.34 | -1050.45 | -825.73 | -1050.45 | 0.42 |  |  | 40 | 80 | 800 | 16000 | 512.73 | 4700 | 3800 | 900 | 165 | 220 | 180 | 150
12/14/2020 | 10:38 | 10:50 | 0.2 | 6058 | 6152 | 94 | Rotate |  | 6083 | 15.92 | 221.13 | 5902.44 | -1070.71 | -843.25 | -1070.71 | 1.36 |  |  | 40 | 80 | 800 | 16000 | 470 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 10:55 | 11:00 | 0.083333 | 6152 | 6165 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 156 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 11:00 | 11:26 | 0.43333 | 6165 | 6190 | 25 | Slide | 0 | 6177 | 16.01 | 216.92 | 5992.82 | -1090.78 | -859.51 | -1090.78 | 1.24 |  |  | 40 | 80 | 800 | 16000 | 57.69 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 11:26 | 11:35 | 0.15 | 6190 | 6246 | 56 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 373.33 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 11:40 | 11:57 | 0.28333 | 6246 | 6340 | 94 | Rotate |  | 6271 | 17.07 | 215.95 | 6082.93 | -1112.31 | -875.4 | -1112.31 | 1.17 |  |  | 40 | 80 | 800 | 16000 | 331.76 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 12:02 | 12:14 | 0.2 | 6340 | 6433 | 93 | Rotate |  | 6364 | 16.32 | 215.75 | 6172.01 | -1133.97 | -891.05 | -1133.97 | 0.81 |  |  | 40 | 80 | 800 | 16000 | 465 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 12:20 | 12:31 | 0.18333 | 6433 | 6528 | 95 | Rotate |  | 6459 | 15.89 | 216.62 | 6263.28 | -1155.24 | -906.6 | -1155.24 | 0.52 |  |  | 40 | 80 | 800 | 16000 | 518.18 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 12:36 | 12:49 | 0.21667 | 6528 | 6623 | 95 | Rotate |  | 6554 | 14.73 | 214.98 | 6354.91 | -1175.57 | -921.29 | -1175.57 | 1.3 |  |  | 40 | 80 | 800 | 16000 | 438.46 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 12:55 | 13:05 | 0.16667 | 6623 | 6716 | 93 | Rotate |  | 6647 | 14.37 | 215.12 | 6444.93 | -1194.7 | -934.7 | -1194.7 | 0.39 |  |  | 40 | 80 | 800 | 16000 | 558 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 13:10 | 13:22 | 0.2 | 6716 | 6808 | 92 | Rotate |  | 6739 | 14.03 | 214.98 | 6534.12 | -1213.17 | -947.66 | -1213.17 | 0.37 |  |  | 40 | 80 | 800 | 16000 | 460 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 13:27 | 13:41 | 0.23333 | 6808 | 6903 | 95 | Rotate |  | 6834 | 14.03 | 214.89 | 6626.28 | -1232.06 | -960.85 | -1232.06 | 0.02 |  |  | 40 | 80 | 800 | 16000 | 407.14 | 4700 | 3800 | 900 | 172 | 220 | 180 | 150
12/14/2020 | 13:46 | 14:08 | 0.36667 | 6903 | 6997 | 94 | Rotate |  | 6928 | 12.99 | 215.33 | 6717.68 | -1250.02 | -973.48 | -1250.02 | 1.11 |  |  | 40 | 80 | 800 | 18000 | 256.36 | 4900 | 4000 | 900 | 190 | 250 | 205 | 170
12/14/2020 | 14:13 | 14:24 | 0.18333 | 6997 | 7090 | 93 | Rotate |  | 7021 | 12.08 | 215.55 | 6808.46 | -1266.47 | -985.18 | -1266.47 | 0.98 |  |  | 40 | 80 | 800 | 18000 | 507.27 | 4900 | 4000 | 900 | 190 | 250 | 205 | 170
12/14/2020 | 14:30 | 14:33 | 0.05 | 7090 | 7100 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 200 | 4900 | 4000 | 900 | 190 | 250 | 205 | 170
12/14/2020 | 14:33 | 15:00 | 0.45 | 7100 | 7140 | 40 | Slide | 0 | 7115 | 13.32 | 218.03 | 6900.16 | -1283 | -997.57 | -1283 | 1.44 |  |  | 20 |  | 800 |  | 88.89 | 4900 | 4000 | 900 | 190 | 250 | 205 | 170
12/14/2020 | 15:00 | 15:10 | 0.16667 | 7140 | 7184 | 44 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 264 | 4900 | 4000 | 900 | 190 | 250 | 205 | 170
12/14/2020 | 15:15 | 15:26 | 0.18333 | 7184 | 7278 | 94 | Rotate |  | 7209 | 14.47 | 222.35 | 6991.41 | -1300.21 | -1012.16 | -1300.21 | 1.65 |  |  | 40 | 80 | 800 | 18000 | 512.73 | 4900 | 4000 | 900 | 190 | 250 | 205 | 170
12/14/2020 | 15:31 | 15:43 | 0.2 | 7278 | 7372 | 94 | Rotate |  | 7303 | 13.6 | 224.03 | 7082.6 | -1316.83 | -1027.75 | -1316.83 | 1.02 |  |  | 40 | 80 | 800 | 18000 | 470 | 4900 | 4000 | 900 | 194 | 265 | 210 | 175
12/14/2020 | 15:49 | 15:52 | 0.05 | 7372 | 7380 | 8 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 160 | 4900 | 4000 | 900 | 194 | 265 | 210 | 175
12/14/2020 | 15:52 | 16:13 | 0.35 | 7380 | 7410 | 30 | Slide | 0 | 7397 | 14.34 | 218.56 | 7173.83 | -1333.88 | -1042.69 | -1333.88 | 1.61 |  |  | 20 |  | 800 |  | 85.71 | 4300 | 4000 | 300 | 194 | 265 | 210 | 175
12/14/2020 | 16:13 | 16:26 | 0.21667 | 7410 | 7466 | 56 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 258.46 | 4900 | 4000 | 900 | 194 | 265 | 210 | 175
12/14/2020 | 16:30 | 16:43 | 0.21667 | 7466 | 7560 | 94 | Rotate |  | 7491 | 14.31 | 217.63 | 7264.91 | -1352.19 | -1057.04 | -1352.19 | 0.25 |  |  | 40 | 80 | 800 | 18000 | 433.85 | 4900 | 4000 | 900 | 194 | 265 | 210 | 175
12/14/2020 | 16:48 | 16:50 | 0.033333 | 7560 | 7565 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 150 | 4900 | 4000 | 900 | 194 | 265 | 210 | 175
12/14/2020 | 16:50 | 17:08 | 0.3 | 7565 | 7590 | 25 | Slide | 0 | 7585 | 14.56 | 214.46 | 7355.94 | -1371.13 | -1070.81 | -1371.13 | 0.88 |  |  | 20 |  | 800 |  | 83.33 | 4300 | 4000 | 300 | 194 | 265 | 210 | 175
12/14/2020 | 17:08 | 17:20 | 0.2 | 7590 | 7654 | 64 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 320 | 4500 | 4000 | 500 | 194 | 265 | 210 | 175
12/14/2020 | 17:28 | 17:35 | 0.11667 | 7654 | 7748 | 94 | Rotate |  | 7679 | 13.08 | 216.48 | 7447.22 | -1389.43 | -1083.83 | -1389.43 | 1.66 |  |  | 28 | 80 | 800 | 20000 | 805.71 | 4500 | 4000 | 500 | 198 | 265 | 210 | 175
12/14/2020 | 17:42 | 17:44 | 0.033333 | 7748 | 7753 | 5 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 150 | 4500 | 4000 | 500 | 198 | 265 | 210 | 175
12/14/2020 | 17:44 | 18:03 | 0.31667 | 7753 | 7788 | 35 | Slide | 0 | 7772 | 14.04 | 213.92 | 7537.62 | -1407.25 | -1096.38 | -1407.25 | 1.22 |  |  | 28 |  | 800 |  | 110.53 | 4500 | 4000 | 500 | 198 | 265 | 210 | 175
12/14/2020 | 18:03 | 18:18 | 0.25 | 7788 | 7841 | 53 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 212 | 4500 | 4000 | 500 | 198 | 265 | 210 | 175
12/14/2020 | 18:23 | 18:38 | 0.25 | 7841 | 7935 | 94 | Rotate |  | 7866 | 13.94 | 213.69 | 7628.84 | -1426.13 | -1109.02 | -1426.13 | 0.12 |  |  | 28 | 80 | 800 | 20000 | 376 | 4500 | 4000 | 500 | 200 | 265 | 210 | 175
12/14/2020 | 18:44 | 18:45 | 0.016667 | 7935 | 7938 | 3 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 180 | 4500 | 4000 | 500 | 200 | 265 | 210 | 175
12/14/2020 | 18:45 | 19:06 | 0.35 | 7938 | 7968 | 30 | Slide | 0 | 7960 | 15.53 | 216.78 | 7719.74 | -1445.63 | -1122.84 | -1445.63 | 1.89 |  |  | 28 |  | 800 |  | 85.71 | 4500 | 4000 | 500 | 200 | 265 | 210 | 175
12/14/2020 | 19:06 | 19:18 | 0.2 | 7968 | 8029 | 61 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 305 | 4500 | 4000 | 500 | 200 | 265 | 210 | 175
12/14/2020 | 19:22 | 19:50 | 0.46667 | 8029 | 8122 | 93 | Rotate |  | 8053 | 15.71 | 219.59 | 7809.31 | -1465.31 | -1138.32 | -1465.31 | 0.84 |  |  | 28 | 80 | 800 | 20000 | 199.29 | 4800 | 4200 | 600 | 200 | 265 | 210 | 175
12/14/2020 | 19:55 | 20:10 | 0.25 | 8122 | 8215 | 93 | Rotate |  | 8146 | 14.69 | 219.64 | 7899.05 | -1484.09 | -1153.86 | -1484.09 | 1.1 |  |  | 28 | 80 | 800 | 20000 | 372 | 4800 | 4200 | 600 | 200 | 265 | 210 | 175
12/14/2020 | 20:15 | 20:28 | 0.21667 | 8215 | 8310 | 95 | Rotate |  | 8241 | 12.76 | 220.99 | 7991.34 | -1501.29 | -1168.43 | -1501.29 | 2.06 |  |  | 28 | 80 | 800 | 20000 | 438.46 | 4800 | 4200 | 600 | 200 | 265 | 210 | 175
12/14/2020 | 20:32 | 20:58 | 0.43333 | 8310 | 8350 | 40 | Slide | 0 | 8335 | 14.34 | 222.4 | 8082.72 | -1517.72 | -1183.09 | -1517.72 | 1.72 |  |  | 32 |  | 800 |  | 92.31 | 4400 | 4200 | 200 | 204 | 265 | 210 | 175
12/14/2020 | 20:58 | 21:15 | 0.28333 | 8350 | 8404 | 54 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 190.59 | 4800 | 4200 | 600 | 204 | 265 | 210 | 175
12/14/2020 | 21:20 | 21:35 | 0.25 | 8404 | 8498 | 94 | Rotate |  | 8429 | 15.36 | 222.32 | 8173.58 | -1535.52 | -1199.32 | -1535.52 | 1.09 |  |  | 28 | 80 | 800 | 22000 | 376 | 4800 | 4200 | 600 | 204 | 300 | 220 | 185
12/14/2020 | 21:40 | 21:55 | 0.25 | 8498 | 8593 | 95 | Rotate |  | 8524 | 13.16 | 223.61 | 8265.65 | -1552.66 | -1215.25 | -1552.66 | 2.34 |  |  | 28 | 80 | 800 | 22000 | 380 | 4800 | 4200 | 600 | 204 | 300 | 220 | 185
12/14/2020 | 22:00 | 22:20 | 0.33333 | 8593 | 8638 | 45 | Slide | 0 | 8617 | 14.41 | 228.66 | 8355.97 | -1567.97 | -1231.25 | -1567.97 | 1.86 |  |  | 32 |  | 800 |  | 135 | 4400 | 4200 | 200 | 204 | 300 | 220 | 185
12/14/2020 | 22:20 | 22:32 | 0.2 | 8638 | 8686 | 48 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 240 | 4800 | 4200 | 600 | 204 | 300 | 220 | 185
12/14/2020 | 22:37 | 22:53 | 0.26667 | 8686 | 8780 | 94 | Rotate |  | 8711 | 15.34 | 231.02 | 8446.82 | -1583.52 | -1249.69 | -1583.52 | 1.18 |  |  | 28 | 80 | 800 | 22000 | 352.5 | 4800 | 4200 | 600 | 204 | 300 | 220 | 185
12/14/2020 | 22:58 | 23:26 | 0.46667 | 8780 | 8810 | 30 | Slide | 0 | 8806 | 15.52 | 218.58 | 8538.42 | -1601.36 | -1267.39 | -1601.36 | 3.48 |  |  | 35 |  | 700 |  | 64.29 | 4000 | 3800 | 200 | 205 | 300 | 220 | 185
12/14/2020 | 23:26 | 23:48 | 0.36667 | 8810 | 8875 | 65 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 177.27 | 4800 | 4200 | 600 | 205 | 300 | 220 | 185
12/14/2020 | 23:55 | 23:57 | 0.033333 | 8875 | 8878 | 3 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 4800 | 4200 | 600 | 205 | 300 | 220 | 185
12/14/2020 | 23:57 | 24:00 | 0.05 | 8878 | 8880 | 2 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 40 | 4400 | 4200 | 200 | 205 | 300 | 220 | 185
12/15/2020 | 00:00 | 00:32 | 0.53333 | 8880 | 8918 | 38 | Slide | 0 | 8900 | 13.43 | 211.27 | 8629.44 | -1620.53 | -1280.9 | -1620.53 | 2.95 |  |  | 35 |  | 800 |  | 71.25 | 4400 | 4200 | 200 | 205 | 300 | 220 | 185
12/15/2020 | 00:32 | 00:44 | 0.2 | 8918 | 8969 | 51 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 255 | 4800 | 4200 | 600 | 205 | 300 | 220 | 185
12/15/2020 | 01:00 | 01:32 | 0.53333 | 8969 | 9014 | 45 | Slide | 0 | 8995 | 6.58 | 193.06 | 8722.96 | -1635.28 | -1287.87 | -1635.28 | 7.86 |  |  | 35 |  | 800 |  | 84.38 | 4400 | 4200 | 200 | 207 | 300 | 220 | 185
12/15/2020 | 01:32 | 01:42 | 0.16667 | 9014 | 9064 | 50 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 300 | 4800 | 4200 | 600 | 207 | 300 | 220 | 185
12/15/2020 | 01:45 | 01:58 | 0.21667 | 9064 | 9158 | 94 | Rotate |  | 9089 | 4.59 | 182.53 | 8816.51 | -1644.28 | -1289.25 | -1644.28 | 2.37 |  |  | 32 | 80 | 800 | 23000 | 433.85 | 4800 | 4200 | 600 | 217 | 315 | 230 | 190
12/15/2020 | 02:02 | 02:05 | 0.05 | 9158 | 9167 | 9 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 180 | 4800 | 4200 | 600 | 217 | 315 | 230 | 190
12/15/2020 | 02:05 | 02:20 | 0.25 | 9167 | 9185 | 18 | Slide | 0 | 9184 | 2.93 | 173.19 | 8911.3 | -1650.49 | -1289.13 | -1650.49 | 1.86 |  |  | 28 |  | 800 |  | 72 | 4400 | 4200 | 200 | 217 | 315 | 230 | 190
12/15/2020 | 02:20 | 02:33 | 0.21667 | 9185 | 9253 | 68 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 313.85 | 4800 | 4200 | 600 | 217 | 315 | 230 | 190
12/15/2020 | 02:37 | 02:38 | 0.016667 | 9253 | 9257 | 4 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 240 | 4800 | 4200 | 600 | 217 | 315 | 230 | 190
12/15/2020 | 02:38 | 02:54 | 0.26667 | 9257 | 9275 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 67.5 | 4400 | 4200 | 200 | 222 | 315 | 230 | 190
12/15/2020 | 02:54 | 03:08 | 0.23333 | 9275 | 9347 | 72 | Rotate |  | 9278 | 1.83 | 135.39 | 9005.23 | -1653.95 | -1287.79 | -1653.95 | 1.98 |  |  | 30 | 80 | 800 | 23000 | 308.57 | 4800 | 4200 | 600 | 222 | 315 | 230 | 190
12/15/2020 | 03:12 | 03:28 | 0.26667 | 9347 | 9440 | 93 | Rotate |  | 9371 | 2.27 | 123.2 | 9098.17 | -1656.01 | -1285.21 | -1656.01 | 0.66 |  |  | 30 | 80 | 800 | 23000 | 348.75 | 4800 | 4200 | 600 | 222 | 315 | 230 | 190
12/15/2020 | 03:30 | 03:49 | 0.31667 | 9440 | 9534 | 94 | Rotate |  | 9465 | 2.86 | 110.72 | 9192.07 | -1657.86 | -1281.46 | -1657.86 | 0.86 |  |  | 40 | 80 | 800 | 23000 | 296.84 | 4800 | 4200 | 600 | 225 | 325 | 230 | 190
12/15/2020 | 03:52 | 04:21 | 0.48333 | 9534 | 9629 | 95 | Rotate |  | 9560 | 3.29 | 103.07 | 9286.94 | -1659.32 | -1276.59 | -1659.32 | 0.62 |  |  | 42 | 80 | 800 | 23000 | 196.55 | 4800 | 4200 | 600 | 227 | 325 | 230 | 190
12/15/2020 | 04:24 | 04:56 | 0.53333 | 9629 | 9655 | 26 | Slide | 0 | 9653 | 1.32 | 129.96 | 9379.86 | -1660.61 | -1273.17 | -1660.61 | 2.36 |  |  | 45 |  | 800 |  | 48.75 | 4500 | 4200 | 300 | 222 | 325 | 230 | 190
12/15/2020 | 04:56 | 05:17 | 0.35 | 9655 | 9722 | 67 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 191.43 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 05:20 | 05:21 | 0.016667 | 9722 | 9726 | 4 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 240 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 05:21 | 06:04 | 0.71667 | 9726 | 9742 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 22.33 | 4500 | 4200 | 300 | 227 | 350 | 250 | 200
12/15/2020 | 06:04 | 06:23 | 0.31667 | 9742 | 9816 | 74 | Rotate |  | 9747 | 1.49 | 268.47 | 9473.85 | -1661.34 | -1273.56 | -1661.34 | 2.8 |  |  | 42 | 80 | 800 | 23000 | 233.68 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 06:28 | 06:50 | 0.36667 | 9816 | 9910 | 94 | Rotate |  | 9841 | 2.62 | 280.99 | 9567.78 | -1660.96 | -1276.89 | -1660.96 | 1.29 |  |  | 42 | 80 | 800 | 23000 | 256.36 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 06:55 | 07:00 | 0.083333 | 9910 | 9934 | 24 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 288 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 07:00 | 08:00 | 1 | 9934 | 9994 | 60 | Slide | 330 | 9936 | 3.32 | 292.9 | 9662.66 | -1659.48 | -1281.55 | -1659.48 | 0.98 |  |  | 45 |  | 800 |  | 60 | 4500 | 4200 | 300 | 227 | 350 | 250 | 200
12/15/2020 | 08:00 | 08:06 | 0.1 | 9994 | 10005 | 11 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 110 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 08:10 | 08:30 | 0.33333 | 10005 | 10060 | 55 | Rotate |  | 10029 | 8.33 | 322.35 | 9755.16 | -1653.09 | -1288.15 | -1653.09 | 6.1 |  |  | 42 | 80 | 800 | 23000 | 165 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200
12/15/2020 | 08:30 | 09:17 | 0.78333 | 10060 | 10098 | 38 | Slide | TTF: 20; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 48.51 | 4500 | 4200 | 300 | 227 | 350 | 250 | 200
12/15/2020 | 09:22 | 10:02 | 0.66667 | 10098 | 10192 | 94 | Rotate |  | 10123 | 11.12 | 328.26 | 9847.81 | -1639.99 | -1297.08 | -1639.99 | 3.15 |  |  | 42 | 80 | 800 | 23000 | 141 | 4800 | 4200 | 600 | 227 | 350 | 250 | 200

## BHA_3_Curve_and_Lateral_Slide_S
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #3 (Curve and Lateral) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 17
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 7
Well Name: |  |  |  |  | Fat Tire B1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 72.00 / 58.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 328.33 |  | Rotate: |  | 10
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/28/2020 | 14:50 | 14:55 | 0.083333 | 10192 | 10202 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 275; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 2400 | 2000 | 400 | 230 | 225 | 200 | 180
12/28/2020 | 17:40 | 18:05 | 0.41667 | 10202 | 10209 | 7 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 275; Drilling Parameters ROP: 16.8 | 2200 | 2000 | 200 | 230 | 225 | 200 | 180

## BHA_4_Curve_and_Lateral_Slide_S
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #4 (Curve and Lateral) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 4740
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 918
Well Name: |  |  |  |  | Fat Tire B1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 66.00 / 58.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 328.33 |  | Rotate: |  | 3822
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
12/29/2020 | 13:50 | 14:13 | 0.38333 | 10209 | 10240 | 31 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 80.87 | 4100 | 3530 | 570 | 238 | 270 | 210 | 180
12/29/2020 | 14:23 | 15:28 | 1.0833 | 10240 | 10336 | 96 | Slide | 0 | 10270 | 16.37 | 319.94 | 9990.56 | -1612.05 | -1317.89 | -1612.05 | 3.81 |  |  | 40 |  | 350 |  | 88.62 | 4100 | 3530 | 570 | 238 | 270 | 210 | 180
12/29/2020 | 15:38 | 16:20 | 0.7 | 10336 | 10401 | 65 | Slide | 0 | 10364 | 31.15 | 325.93 | 10076.37 | -1581.6 | -1340.16 | -1581.6 | 15.91 |  |  | 40 |  | 400 |  | 92.86 | 4650 | 4000 | 650 | 240 | 270 | 210 | 180
12/29/2020 | 16:20 | 16:32 | 0.2 | 10401 | 10430 | 29 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 145 | 4950 | 4000 | 950 | 240 | 270 | 210 | 180
12/29/2020 | 16:42 | 17:11 | 0.48333 | 10430 | 10488 | 58 | Rotate |  | 10458 | 31.62 | 328.15 | 10156.62 | -1540.53 | -1366.79 | -1540.53 | 1.33 |  |  | 30 | 50 | 400 | 12500 | 120 | 4950 | 4000 | 950 | 240 | 270 | 210 | 180
12/29/2020 | 17:11 | 17:38 | 0.45 | 10488 | 10524 | 36 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 80 | 4650 | 4000 | 650 | 240 | 270 | 210 | 180
12/29/2020 | 17:44 | 18:00 | 0.26667 | 10524 | 10549 | 25 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 40; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 93.75 | 4950 | 4000 | 950 | 240 | 270 | 210 | 180
12/29/2020 | 18:00 | 18:36 | 0.6 | 10549 | 10620 | 71 | Slide | 0 | 10554 | 35.01 | 328.8 | 10236.83 | -1495.58 | -1394.34 | -1495.58 | 3.55 |  |  | 55 |  | 400 |  | 118.33 | 4800 | 4000 | 800 | 240 | 270 | 210 | 180
12/29/2020 | 18:50 | 19:40 | 0.83333 | 10620 | 10705 | 85 | Slide | 0 | 10649 | 44.92 | 331.49 | 10309.55 | -1442.67 | -1424.54 | -1442.67 | 10.59 |  |  | 60 |  | 400 |  | 102 | 4800 | 4000 | 800 | 240 | 270 | 210 | 180
12/29/2020 | 19:40 | 19:48 | 0.13333 | 10705 | 10715 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 75 | 5000 | 4000 | 1000 | 230 | 270 | 210 | 180
12/29/2020 | 19:58 | 20:42 | 0.73333 | 10715 | 10811 | 96 | Slide | 0 | 10745 | 58.01 | 331.66 | 10369.23 | -1376.76 | -1460.2 | -1376.76 | 13.64 |  |  | 65 |  | 330 |  | 130.91 | 3500 | 2600 | 900 | 200 | 290 | 220 | 185
12/29/2020 | 20:55 | 21:22 | 0.45 | 10811 | 10856 | 45 | Rotate |  | 10840 | 68.98 | 330.03 | 10411.57 | -1302.66 | -1501.61 | -1302.66 | 11.65 |  |  | 30 | 50 | 330 | 14500 | 100 | 3600 | 2600 | 1000 | 200 | 290 | 220 | 185
12/29/2020 | 21:22 | 21:48 | 0.43333 | 10856 | 10906 | 50 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 115.38 | 3500 | 2600 | 900 | 200 | 290 | 220 | 185
12/29/2020 | 22:20 | 23:03 | 0.71667 | 10906 | 11000 | 94 | Rotate |  | 10934 | 74.06 | 328.73 | 10441.35 | -1225.98 | -1547.01 | -1225.98 | 5.56 |  |  | 32 | 50 | 330 | 14500 | 131.16 | 3750 | 2600 | 1150 | 200 | 310 | 220 | 185
12/29/2020 | 23:12 | 24:00 | 0.8 | 11000 | 11095 | 95 | Rotate |  | 11029 | 74.42 | 331.52 | 10467.16 | -1146.71 | -1592.55 | -1146.71 | 2.85 |  |  | 68 |  | 330 |  | 118.75 | 3500 | 2600 | 900 | 200 | 330 | 220 | 185
12/30/2020 | 00:25 | 00:50 | 0.41667 | 11095 | 11134 | 39 | Slide | 0 | 11124 | 92.53 | 333.12 | 10477.91 | -1063.46 | -1636.19 | -1063.46 | 19.14 |  |  | 68 |  | 330 |  | 93.6 | 3500 | 2600 | 900 | 200 | 330 | 220 | 185
12/30/2020 | 02:00 | 02:05 | 0.083333 | 11134 | 11144 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 120 | 3500 | 2600 | 900 | 200 | 330 | 220 | 185
12/30/2020 | 02:05 | 02:35 | 0.5 | 11144 | 11190 | 46 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14500; Drilling Parameters ROP: 92 | 3700 | 2600 | 1100 | 200 | 330 | 220 | 185
12/30/2020 | 04:35 | 05:10 | 0.58333 | 11190 | 11218 | 28 | Slide | 0 | 11218 | 97.01 | 329.75 | 10470.09 | -981.22 | -1680.95 | -981.22 | 5.96 |  |  | 68 |  | 330 |  | 48 | 3500 | 2600 | 900 | 200 | 330 | 220 | 185
12/30/2020 | 05:10 | 05:45 | 0.58333 | 11218 | 11284 | 66 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14500; Drilling Parameters ROP: 113.14 | 3700 | 2600 | 1100 | 200 | 330 | 220 | 185
12/30/2020 | 06:05 | 06:33 | 0.46667 | 11284 | 11309 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 53.57 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 06:33 | 07:04 | 0.51667 | 11309 | 11379 | 70 | Rotate |  | 11313 | 92.61 | 327.6 | 10462.13 | -900.38 | -1730.16 | -900.38 | 5.15 |  |  | 35 | 50 | 330 | 15000 | 135.48 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 07:20 | 07:24 | 0.066667 | 11379 | 11389 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 150 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 07:24 | 07:39 | 0.25 | 11389 | 11399 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 40 | 3700 | 2600 | 1100 | 128 | 330 | 220 | 185
12/30/2020 | 07:39 | 08:07 | 0.46667 | 11399 | 11475 | 76 | Rotate |  | 11409 | 91.56 | 326.71 | 10458.64 | -819.78 | -1782.19 | -819.78 | 1.43 |  |  | 35 | 50 | 330 | 15000 | 162.86 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 08:21 | 08:44 | 0.38333 | 11475 | 11569 | 94 | Rotate |  | 11503 | 90.93 | 325.9 | 10456.59 | -741.59 | -1834.32 | -741.59 | 1.09 |  |  | 35 | 50 | 330 | 15000 | 245.22 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 09:00 | 09:22 | 0.36667 | 11569 | 11663 | 94 | Rotate |  | 11597 | 91.61 | 327 | 10454.51 | -663.28 | -1886.26 | -663.28 | 1.38 |  |  | 35 | 50 | 330 | 15000 | 256.36 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 09:34 | 10:01 | 0.45 | 11663 | 11757 | 94 | Rotate |  | 11691 | 91.68 | 325.77 | 10451.81 | -585.03 | -1938.28 | -585.03 | 1.31 |  |  | 35 | 50 | 330 | 15000 | 208.89 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 10:15 | 10:37 | 0.36667 | 11757 | 11851 | 94 | Rotate |  | 11785 | 91.62 | 324.96 | 10449.11 | -507.72 | -1991.68 | -507.72 | 0.86 |  |  | 35 | 50 | 330 | 15000 | 256.36 | 3700 | 2600 | 1100 | 125 | 330 | 220 | 185
12/30/2020 | 10:50 | 10:53 | 0.05 | 11851 | 11861 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 200 | 3700 | 2600 | 1100 | 136 | 330 | 220 | 185
12/30/2020 | 10:53 | 11:17 | 0.4 | 11861 | 11881 | 20 | Slide | 0 | 11880 | 90.42 | 326.96 | 10447.41 | -429.01 | -2044.85 | -429.01 | 2.45 |  |  | 65 |  | 330 |  | 50 | 3700 | 2600 | 1100 | 136 | 330 | 220 | 185
12/30/2020 | 11:17 | 11:42 | 0.41667 | 11881 | 11946 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 156 | 3700 | 2600 | 1100 | 136 | 330 | 220 | 185
12/30/2020 | 11:55 | 12:18 | 0.38333 | 11946 | 12041 | 95 | Rotate |  | 11975 | 90.16 | 327.15 | 10446.93 | -349.29 | -2096.51 | -349.29 | 0.34 |  |  | 35 | 50 | 330 | 15000 | 247.83 | 3700 | 2600 | 1100 | 136 | 330 | 220 | 185
12/30/2020 | 14:10 | 14:15 | 0.083333 | 12041 | 12051 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 120 | 3700 | 2600 | 1100 | 136 | 330 | 220 | 185
12/30/2020 | 14:15 | 14:33 | 0.3 | 12051 | 12059 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 26.67 | 3700 | 2600 | 1100 | 136 | 330 | 220 | 185
12/30/2020 | 14:33 | 14:59 | 0.43333 | 12059 | 12136 | 77 | Rotate |  | 12070 | 89.35 | 327.68 | 10447.34 | -269.25 | -2147.67 | -269.25 | 1.02 |  |  | 35 | 50 | 330 | 15000 | 177.69 | 3700 | 2600 | 1100 | 167 | 330 | 220 | 185
12/30/2020 | 15:58 | 16:02 | 0.066667 | 12136 | 12153 | 17 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 255 | 3700 | 2600 | 1100 | 167 | 330 | 220 | 185
12/30/2020 | 16:20 | 16:49 | 0.48333 | 12153 | 12231 | 78 | Rotate |  | 12165 | 88.78 | 327.45 | 10448.89 | -189.08 | -2198.62 | -189.08 | 0.65 |  |  | 35 | 80 | 395 | 17000 | 161.38 | 4400 | 3200 | 1200 | 167 | 330 | 205 | 160
12/30/2020 | 16:59 | 17:26 | 0.45 | 12231 | 12328 | 97 | Rotate |  | 12262 | 87.69 | 327.52 | 10451.88 | -107.32 | -2250.73 | -107.32 | 1.13 |  |  | 35 | 80 | 395 | 17000 | 215.56 | 4400 | 3200 | 1200 | 167 | 330 | 205 | 160
12/30/2020 | 17:32 | 17:48 | 0.26667 | 12328 | 12338 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 37.5 | 4400 | 3200 | 1200 | 167 | 330 | 205 | 160
12/30/2020 | 17:48 | 18:14 | 0.43333 | 12338 | 12358 | 20 | Slide | 0 | 12357 | 88.73 | 327.64 | 10454.84 | -27.17 | -2301.64 | -27.17 | 1.1 |  |  | 60 |  | 395 |  | 46.15 | 4400 | 3800 | 600 | 160 | 330 | 205 | 160
12/30/2020 | 18:14 | 18:36 | 0.36667 | 12358 | 12423 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 177.27 | 5000 | 3800 | 1200 | 160 | 330 | 205 | 160
12/30/2020 | 18:48 | 19:00 | 0.2 | 12423 | 12434 | 11 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 55 | 4400 | 3800 | 600 | 150 | 330 | 205 | 160
12/30/2020 | 20:25 | 20:55 | 0.5 | 12434 | 12463 | 29 | Slide | 0 | 12452 | 91.84 | 330.14 | 10454.37 | 54.15 | -2350.71 | 54.15 | 4.2 |  |  | 60 |  | 395 |  | 58 | 4400 | 3800 | 600 | 150 | 330 | 205 | 160
12/30/2020 | 20:55 | 21:12 | 0.28333 | 12463 | 12518 | 55 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 194.12 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/30/2020 | 21:23 | 21:40 | 0.28333 | 12518 | 12530 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 42.35 | 4400 | 3800 | 600 | 150 | 330 | 205 | 160
12/30/2020 | 21:40 | 22:05 | 0.41667 | 12530 | 12613 | 83 | Rotate |  | 12547 | 96.96 | 330.3 | 10447.09 | 136.33 | -2397.74 | 136.33 | 5.39 |  |  | 35 | 80 | 395 | 17000 | 199.2 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/30/2020 | 22:15 | 22:40 | 0.41667 | 12613 | 12638 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 60 | 4500 | 3800 | 700 | 150 | 330 | 205 | 160
12/30/2020 | 22:40 | 23:00 | 0.33333 | 12638 | 12709 | 71 | Rotate |  | 12643 | 95.29 | 329.8 | 10436.84 | 219.03 | -2445.39 | 219.03 | 1.82 |  |  | 35 | 80 | 395 | 17000 | 213 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/30/2020 | 23:08 | 23:30 | 0.36667 | 12709 | 12725 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 43.64 | 4500 | 3800 | 700 | 150 | 330 | 205 | 160
12/30/2020 | 23:30 | 23:52 | 0.36667 | 12725 | 12805 | 80 | Rotate |  | 12739 | 92.64 | 329.49 | 10430.21 | 301.67 | -2493.79 | 301.67 | 2.78 |  |  | 35 | 80 | 395 | 17000 | 218.18 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/30/2020 | 23:58 | 24:00 | 0.033333 | 12805 | 12808 | 3 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 90 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/31/2020 | 00:00 | 00:20 | 0.33333 | 12808 | 12900 | 92 | Rotate |  | 12834 | 93.38 | 329.87 | 10425.22 | 383.56 | -2541.68 | 383.56 | 0.88 |  |  | 35 | 80 | 395 | 17000 | 276 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/31/2020 | 00:25 | 00:30 | 0.083333 | 12900 | 12914 | 14 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 168 | 5000 | 3800 | 1200 | 150 | 330 | 205 | 160
12/31/2020 | 00:30 | 00:52 | 0.36667 | 12914 | 12930 | 16 | Slide | 0 | 12929 | 90.83 | 328.94 | 10421.73 | 465.27 | -2589.99 | 465.27 | 2.86 |  |  | 66 |  | 395 |  | 43.64 | 4600 | 4200 | 400 | 150 | 330 | 205 | 160
12/31/2020 | 00:52 | 01:11 | 0.31667 | 12930 | 12995 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 205.26 | 5400 | 4200 | 1200 | 160 | 330 | 205 | 160
12/31/2020 | 01:18 | 01:44 | 0.43333 | 12995 | 13089 | 94 | Rotate |  | 13023 | 90.97 | 329.29 | 10420.25 | 545.93 | -2638.24 | 545.93 | 0.4 |  |  | 35 | 80 | 395 | 18000 | 216.92 | 5400 | 4200 | 1200 | 160 | 330 | 205 | 160
12/31/2020 | 01:50 | 01:55 | 0.083333 | 13089 | 13095 | 6 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 72 | 5400 | 4200 | 1200 | 160 | 330 | 205 | 160
12/31/2020 | 01:55 | 02:20 | 0.41667 | 13095 | 13109 | 14 | Slide | TTF: 0; Drilling Parameters WOB: 68; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 33.6 | 4600 | 4200 | 400 | 155 | 330 | 205 | 160
12/31/2020 | 02:20 | 02:42 | 0.36667 | 13109 | 13184 | 75 | Rotate |  | 13118 | 90.85 | 333.47 | 10418.74 | 629.3 | -2683.73 | 629.3 | 4.4 |  |  | 35 | 80 | 395 | 18000 | 204.55 | 5400 | 4200 | 1200 | 155 | 330 | 205 | 160
12/31/2020 | 02:48 | 03:11 | 0.38333 | 13184 | 13278 | 94 | Rotate |  | 13212 | 91.79 | 335.55 | 10416.58 | 714.12 | -2724.17 | 714.12 | 2.43 |  |  | 35 | 80 | 395 | 18000 | 245.22 | 5400 | 4200 | 1200 | 160 | 330 | 205 | 160
12/31/2020 | 03:16 | 03:24 | 0.13333 | 13278 | 13284 | 6 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 45 | 5400 | 4200 | 1200 | 160 | 330 | 205 | 160
12/31/2020 | 03:24 | 03:48 | 0.4 | 13284 | 13300 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 72; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 40 | 4600 | 4200 | 400 | 150 | 330 | 205 | 160
12/31/2020 | 03:48 | 04:10 | 0.36667 | 13300 | 13374 | 74 | Rotate |  | 13307 | 93.22 | 337.25 | 10412.42 | 801.08 | -2762.16 | 801.08 | 2.34 |  |  | 35 | 80 | 395 | 18000 | 201.82 | 5400 | 4200 | 1200 | 150 | 330 | 205 | 140
12/31/2020 | 04:18 | 04:48 | 0.5 | 13374 | 13389 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 72; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 30 | 4600 | 4200 | 400 | 150 | 330 | 205 | 140
12/31/2020 | 04:48 | 05:07 | 0.31667 | 13389 | 13469 | 80 | Rotate |  | 13403 | 94.24 | 336.86 | 10406.18 | 889.3 | -2799.51 | 889.3 | 1.14 |  |  | 32 | 80 | 395 | 18000 | 252.63 | 5500 | 4400 | 1100 | 150 | 345 | 205 | 140
12/31/2020 | 05:15 | 05:37 | 0.36667 | 13469 | 13564 | 95 | Rotate |  | 13498 | 92.62 | 336.38 | 10400.5 | 976.34 | -2837.14 | 976.34 | 1.78 |  |  | 32 | 80 | 395 | 18000 | 259.09 | 5500 | 4400 | 1100 | 157 | 345 | 205 | 140
12/31/2020 | 05:47 | 06:05 | 0.3 | 13564 | 13659 | 95 | Rotate |  | 13593 | 92.64 | 334.59 | 10396.14 | 1062.68 | -2876.51 | 1062.68 | 1.88 |  |  | 32 | 80 | 395 | 18000 | 316.67 | 5500 | 4400 | 1100 | 157 | 345 | 205 | 140
12/31/2020 | 06:15 | 06:32 | 0.28333 | 13659 | 13754 | 95 | Rotate |  | 13687 | 92.63 | 329.38 | 10391.81 | 1145.55 | -2920.6 | 1145.55 | 5.54 |  |  | 32 | 80 | 395 | 18000 | 335.29 | 5500 | 4400 | 1100 | 157 | 345 | 205 | 140
12/31/2020 | 06:42 | 07:00 | 0.3 | 13754 | 13848 | 94 | Rotate |  | 13782 | 92.29 | 329.59 | 10387.73 | 1227.32 | -2968.8 | 1227.32 | 0.42 |  |  | 32 | 80 | 395 | 18000 | 313.33 | 5500 | 4400 | 1100 | 157 | 345 | 205 | 140
12/31/2020 | 07:10 | 07:26 | 0.26667 | 13848 | 13942 | 94 | Rotate |  | 13876 | 92.44 | 326.55 | 10383.85 | 1307.02 | -3018.46 | 1307.02 | 3.24 |  |  | 32 | 80 | 395 | 18000 | 352.5 | 5500 | 4400 | 1100 | 157 | 345 | 205 | 140
12/31/2020 | 07:36 | 07:38 | 0.033333 | 13942 | 13950 | 8 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 240 | 5500 | 4400 | 1100 | 157 | 345 | 205 | 140
12/31/2020 | 08:48 | 09:09 | 0.35 | 13950 | 14036 | 86 | Rotate |  | 13970 | 91.82 | 325.26 | 10380.36 | 1384.8 | -3071.12 | 1384.8 | 1.52 |  |  | 32 | 80 | 395 | 18000 | 245.71 | 5500 | 4400 | 1100 | 162 | 345 | 205 | 140
12/31/2020 | 09:19 | 09:23 | 0.066667 | 14036 | 14046 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 150 | 5500 | 4400 | 1100 | 162 | 345 | 205 | 140
12/31/2020 | 09:23 | 09:43 | 0.33333 | 14046 | 14058 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 36 | 4650 | 4400 | 250 | 167 | 345 | 205 | 140
12/31/2020 | 09:43 | 10:05 | 0.36667 | 14058 | 14130 | 72 | Rotate |  | 14064 | 92.38 | 324.61 | 10376.92 | 1461.69 | -3125.09 | 1461.69 | 0.91 |  |  | 32 | 80 | 395 | 18000 | 196.36 | 5500 | 4400 | 1100 | 167 | 345 | 205 | 140
12/31/2020 | 10:15 | 10:34 | 0.31667 | 14130 | 14225 | 95 | Rotate |  | 14159 | 92.43 | 327.94 | 10372.93 | 1540.62 | -3177.78 | 1540.62 | 3.5 |  |  | 32 | 80 | 395 | 18000 | 300 | 5500 | 4400 | 1100 | 167 | 345 | 205 | 140
12/31/2020 | 10:44 | 10:47 | 0.05 | 14225 | 14235 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 200 | 5500 | 4400 | 1100 | 167 | 345 | 205 | 140
12/31/2020 | 10:47 | 11:08 | 0.35 | 14235 | 14247 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 34.29 | 4650 | 4400 | 250 | 167 | 345 | 205 | 140
12/31/2020 | 11:08 | 11:29 | 0.35 | 14247 | 14319 | 72 | Rotate |  | 14253 | 94.17 | 327.66 | 10367.52 | 1620.03 | -3227.78 | 1620.03 | 1.87 |  |  | 28 | 80 | 395 | 20000 | 205.71 | 5500 | 4400 | 1100 | 167 | 345 | 205 | 140
12/31/2020 | 12:20 | 12:25 | 0.083333 | 14319 | 14329 | 10 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 5500 | 4400 | 1100 | 167 | 345 | 205 | 140
12/31/2020 | 12:25 | 12:36 | 0.18333 | 14329 | 14339 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 54.55 | 4650 | 4400 | 250 | 167 | 345 | 205 | 140
12/31/2020 | 12:36 | 12:59 | 0.38333 | 14339 | 14414 | 75 | Rotate |  | 14347 | 95.35 | 327.32 | 10359.72 | 1699.02 | -3278.13 | 1699.02 | 1.31 |  |  | 28 | 80 | 395 | 20000 | 195.65 | 5500 | 4400 | 1100 | 175 | 345 | 205 | 140
12/31/2020 | 13:40 | 13:43 | 0.05 | 14414 | 14424 | 10 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 200 | 5500 | 4400 | 1100 | 175 | 345 | 205 | 140
12/31/2020 | 13:43 | 14:00 | 0.28333 | 14424 | 14436 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 42.35 | 4650 | 4400 | 250 | 199 | 345 | 205 | 140
12/31/2020 | 14:00 | 14:25 | 0.41667 | 14436 | 14508 | 72 | Rotate |  | 14442 | 92.24 | 328.44 | 10353.43 | 1779.3 | -3328.52 | 1779.3 | 3.48 |  |  | 28 | 80 | 395 | 20000 | 172.8 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 14:35 | 14:57 | 0.36667 | 14508 | 14602 | 94 | Rotate |  | 14536 | 93.14 | 328.56 | 10349.02 | 1859.35 | -3377.58 | 1859.35 | 0.97 |  |  | 28 | 80 | 395 | 20000 | 256.36 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 15:07 | 15:24 | 0.28333 | 14602 | 14696 | 94 | Rotate |  | 14629 | 90.14 | 327.47 | 10346.36 | 1938.19 | -3426.81 | 1938.19 | 3.43 |  |  | 28 | 80 | 395 | 20000 | 331.76 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 15:34 | 15:52 | 0.3 | 14696 | 14790 | 94 | Rotate |  | 14724 | 90.91 | 327.19 | 10345.49 | 2018.16 | -3478.09 | 2018.16 | 0.86 |  |  | 28 | 80 | 395 | 20000 | 313.33 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 16:00 | 16:03 | 0.05 | 14790 | 14800 | 10 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 200 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 16:03 | 16:29 | 0.43333 | 14800 | 14813 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 30 | 4650 | 4400 | 250 | 199 | 345 | 205 | 140
12/31/2020 | 16:29 | 16:54 | 0.41667 | 14813 | 14885 | 72 | Rotate |  | 14819 | 91.62 | 326.47 | 10343.39 | 2097.66 | -3530.06 | 2097.66 | 1.06 |  |  | 28 | 80 | 395 | 20000 | 172.8 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 17:04 | 17:14 | 0.16667 | 14885 | 14927 | 42 | Rotate |  | 14913 | 93.09 | 326.12 | 10339.53 | 2175.79 | -3582.17 | 2175.79 | 1.61 |  |  | 28 | 80 | 395 | 20000 | 252 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 17:14 | 17:47 | 0.55 | 14927 | 14942 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 395; Drilling Parameters ROP: 27.27 | 4650 | 4400 | 250 | 199 | 345 | 205 | 140
12/31/2020 | 17:47 | 17:50 | 0.05 | 14942 | 14944 | 2 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 40 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 21:08 | 21:15 | 0.11667 | 14944 | 14946 | 2 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 17.14 | 5500 | 4400 | 1100 | 199 | 345 | 205 | 140
12/31/2020 | 23:12 | 23:20 | 0.13333 | 14946 | 14949 | 3 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 22.5 | 4800 | 4400 | 400 | 199 | 345 | 205 | 140

## BHA_5_Lateral_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #5 (Lateral) |  |  |  |  | RKB: |  |  |  | 441 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3745
Site: |  |  |  |  | Fat Tire - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 398
Well Name: |  |  |  |  | Fat Tire B1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 64.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 441 |  | VS Azimuth: |  | 328.33 |  | Rotate: |  | 3347
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
01/02/2021 | 04:20 | 09:04 | 4.7333 | 13095 | 13100 | 5 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 1.06 | 4800 | 4700 | 100 | 125 | 320 | 210 | 150
01/02/2021 | 09:04 | 11:42 | 2.6333 | 13100 | 13130 | 30 | Slide | 0 | 13118 | 90.85 | 333.47 | 10418.74 | 629.3 | -2683.73 | 629.3 | 4.4 |  |  | 40 |  | 400 |  | 11.39 | 4800 | 4700 | 100 | 125 | 320 | 210 | 150
01/02/2021 | 11:42 | 12:48 | 1.1 | 13130 | 13181 | 51 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 46.36 | 5400 | 4700 | 700 | 145 | 335 | 210 | 150
01/02/2021 | 12:58 | 13:42 | 0.73333 | 13181 | 13275 | 94 | Rotate |  | 13212 | 91.79 | 335.55 | 10416.58 | 714.12 | -2724.17 | 714.12 | 2.43 |  |  | 30 | 80 | 400 | 18500 | 128.18 | 5600 | 4700 | 900 | 145 | 335 | 210 | 150
01/02/2021 | 13:52 | 13:57 | 0.083333 | 13275 | 13285 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 120 | 5600 | 4700 | 900 | 145 | 335 | 210 | 150
01/02/2021 | 13:57 | 14:36 | 0.65 | 13285 | 13330 | 45 | Slide | 0 | 13307 | 93.22 | 337.25 | 10412.42 | 801.08 | -2762.16 | 801.08 | 2.34 |  |  | 60 |  | 400 |  | 69.23 | 5000 | 4700 | 300 | 145 | 335 | 210 | 150
01/02/2021 | 14:36 | 14:55 | 0.31667 | 13330 | 13370 | 40 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 126.32 | 5600 | 4700 | 900 | 145 | 335 | 210 | 150
01/02/2021 | 15:05 | 15:32 | 0.45 | 13370 | 13466 | 96 | Rotate |  | 13403 | 94.24 | 336.86 | 10406.18 | 889.3 | -2799.51 | 889.3 | 1.14 |  |  | 32 | 80 | 400 | 19000 | 213.33 | 5600 | 4700 | 900 | 145 | 335 | 210 | 150
01/02/2021 | 15:42 | 15:47 | 0.083333 | 13466 | 13476 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 120 | 5600 | 4700 | 900 | 136 | 335 | 210 | 150
01/02/2021 | 15:47 | 16:38 | 0.85 | 13476 | 13494 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 21.18 | 5000 | 4700 | 300 | 136 | 335 | 210 | 150
01/02/2021 | 16:38 | 17:06 | 0.46667 | 13494 | 13561 | 67 | Rotate |  | 13498 | 92.62 | 336.38 | 10400.5 | 976.34 | -2837.14 | 976.34 | 1.78 |  |  | 35 | 80 | 400 | 19000 | 143.57 | 5600 | 4700 | 900 | 136 | 335 | 210 | 150
01/02/2021 | 17:16 | 17:20 | 0.066667 | 13561 | 13571 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 150 | 5600 | 4700 | 900 | 136 | 335 | 210 | 150
01/02/2021 | 17:20 | 17:55 | 0.58333 | 13571 | 13591 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 34.29 | 5000 | 4700 | 300 | 138 | 335 | 210 | 150
01/02/2021 | 17:55 | 18:25 | 0.5 | 13591 | 13656 | 65 | Rotate |  | 13593 | 92.64 | 334.59 | 10396.14 | 1062.68 | -2876.51 | 1062.68 | 1.88 |  |  | 35 | 80 | 400 | 19000 | 130 | 5600 | 4700 | 900 | 138 | 335 | 210 | 150
01/02/2021 | 18:32 | 19:30 | 0.96667 | 13656 | 13696 | 40 | Slide | 0 | 13687 | 92.63 | 329.38 | 10391.81 | 1145.55 | -2920.6 | 1145.55 | 5.54 |  |  | 70 |  | 400 |  | 41.38 | 5000 | 4700 | 300 | 140 | 335 | 210 | 150
01/02/2021 | 19:30 | 19:52 | 0.36667 | 13696 | 13750 | 54 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 147.27 | 5600 | 4700 | 900 | 140 | 335 | 210 | 150
01/02/2021 | 19:58 | 20:32 | 0.56667 | 13750 | 13845 | 95 | Rotate |  | 13782 | 92.29 | 329.59 | 10387.73 | 1227.32 | -2968.8 | 1227.32 | 0.42 |  |  | 35 | 80 | 400 | 19000 | 167.65 | 5600 | 4700 | 900 | 140 | 335 | 210 | 150
01/02/2021 | 20:38 | 20:43 | 0.083333 | 13845 | 13855 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 120 | 5600 | 4700 | 900 | 150 | 335 | 210 | 150
01/02/2021 | 20:43 | 21:15 | 0.53333 | 13855 | 13875 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 70; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 37.5 | 5000 | 4700 | 300 | 150 | 335 | 210 | 150
01/02/2021 | 21:15 | 21:40 | 0.41667 | 13875 | 13939 | 64 | Rotate |  | 13876 | 92.44 | 326.55 | 10383.85 | 1307.02 | -3018.46 | 1307.02 | 3.24 |  |  | 35 | 80 | 400 | 19000 | 153.6 | 5600 | 4700 | 900 | 150 | 335 | 210 | 150
01/02/2021 | 21:44 | 22:10 | 0.43333 | 13939 | 14033 | 94 | Rotate |  | 13970 | 91.82 | 325.26 | 10380.36 | 1384.8 | -3071.12 | 1384.8 | 1.52 |  |  | 35 | 80 | 400 | 19000 | 216.92 | 5600 | 4700 | 900 | 155 | 335 | 210 | 150
01/02/2021 | 23:15 | 23:45 | 0.5 | 14033 | 14127 | 94 | Rotate |  | 14064 | 92.38 | 324.61 | 10376.92 | 1461.69 | -3125.09 | 1461.69 | 0.91 |  |  | 35 | 80 | 400 | 19000 | 188 | 5600 | 4700 | 900 | 155 | 335 | 210 | 150
01/02/2021 | 23:48 | 24:00 | 0.2 | 14127 | 14137 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 50 | 5600 | 4700 | 900 | 155 | 335 | 210 | 150
01/03/2021 | 00:00 | 00:46 | 0.76667 | 14137 | 14159 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 70; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 28.7 | 4950 | 4700 | 250 | 155 | 335 | 210 | 150
01/03/2021 | 00:46 | 01:07 | 0.35 | 14159 | 14222 | 63 | Rotate |  | 14159 | 92.43 | 327.94 | 10372.93 | 1540.62 | -3177.78 | 1540.62 | 3.5 |  |  | 32 | 80 | 400 | 20000 | 180 | 5600 | 4700 | 900 | 155 | 355 | 210 | 150
01/03/2021 | 01:12 | 01:50 | 0.63333 | 14222 | 14315 | 93 | Rotate |  | 14253 | 94.17 | 327.66 | 10367.52 | 1620.03 | -3227.78 | 1620.03 | 1.87 |  |  | 32 | 80 | 400 | 20000 | 146.84 | 5600 | 4700 | 900 | 155 | 355 | 210 | 150
01/03/2021 | 01:57 | 02:27 | 0.5 | 14315 | 14410 | 95 | Rotate |  | 14347 | 95.35 | 327.32 | 10359.72 | 1699.02 | -3278.13 | 1699.02 | 1.31 |  |  | 32 | 80 | 400 | 20000 | 190 | 5600 | 4700 | 900 | 155 | 355 | 210 | 150
01/03/2021 | 02:35 | 02:38 | 0.05 | 14410 | 14415 | 5 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 100 | 5700 | 4800 | 900 | 165 | 355 | 210 | 150
01/03/2021 | 02:38 | 03:36 | 0.96667 | 14415 | 14440 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 25.86 | 5000 | 4800 | 200 | 170 | 355 | 210 | 150
01/03/2021 | 03:58 | 04:16 | 0.3 | 14440 | 14505 | 65 | Rotate |  | 14442 | 92.24 | 328.44 | 10353.43 | 1779.3 | -3328.52 | 1779.3 | 3.48 |  |  | 30 | 80 | 400 | 20000 | 216.67 | 5700 | 4800 | 900 | 170 | 355 | 210 | 150
01/03/2021 | 04:24 | 04:55 | 0.51667 | 14505 | 14599 | 94 | Rotate |  | 14536 | 93.14 | 328.56 | 10349.02 | 1859.35 | -3377.58 | 1859.35 | 0.97 |  |  | 30 | 80 | 400 | 20000 | 181.94 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 05:04 | 05:35 | 0.51667 | 14599 | 14611 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 23.23 | 5000 | 4800 | 200 | 175 | 355 | 210 | 150
01/03/2021 | 05:35 | 06:06 | 0.51667 | 14611 | 14692 | 81 | Rotate |  | 14629 | 90.14 | 327.47 | 10346.36 | 1938.19 | -3426.81 | 1938.19 | 3.43 |  |  | 30 | 80 | 400 | 20000 | 156.77 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 06:16 | 06:42 | 0.43333 | 14692 | 14787 | 95 | Rotate |  | 14724 | 90.91 | 327.19 | 10345.49 | 2018.16 | -3478.09 | 2018.16 | 0.86 |  |  | 30 | 80 | 400 | 20000 | 219.23 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 06:52 | 07:25 | 0.55 | 14787 | 14882 | 95 | Rotate |  | 14819 | 91.62 | 326.47 | 10343.39 | 2097.66 | -3530.06 | 2097.66 | 1.06 |  |  | 30 | 80 | 400 | 20000 | 172.73 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 07:35 | 08:16 | 0.68333 | 14882 | 14976 | 94 | Rotate |  | 14913 | 93.09 | 326.12 | 10339.53 | 2175.79 | -3582.17 | 2175.79 | 1.61 |  |  | 30 | 80 | 400 | 20000 | 137.56 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 08:26 | 09:07 | 0.68333 | 14976 | 15072 | 96 | Rotate |  | 15009 | 94.67 | 326.04 | 10333.03 | 2255.27 | -3635.62 | 2255.27 | 1.65 |  |  | 30 | 80 | 400 | 20000 | 140.49 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 09:17 | 10:27 | 1.1667 | 15072 | 15097 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 21.43 | 5000 | 4800 | 200 | 175 | 355 | 210 | 150
01/03/2021 | 10:27 | 10:58 | 0.51667 | 15097 | 15167 | 70 | Rotate |  | 15104 | 92.54 | 327.44 | 10327.06 | 2334.54 | -3687.61 | 2334.54 | 2.68 |  |  | 30 | 80 | 400 | 20000 | 135.48 | 5700 | 4800 | 900 | 175 | 355 | 210 | 150
01/03/2021 | 11:08 | 11:32 | 0.4 | 15167 | 15262 | 95 | Rotate |  | 15199 | 92.23 | 326.37 | 10323.1 | 2414.06 | -3739.44 | 2414.06 | 1.17 |  |  | 30 | 80 | 400 | 20000 | 237.5 | 5700 | 4800 | 900 | 185 | 355 | 210 | 150
01/03/2021 | 11:42 | 12:11 | 0.48333 | 15262 | 15357 | 95 | Rotate |  | 15294 | 92.57 | 325.6 | 10319.13 | 2492.73 | -3792.54 | 2492.73 | 0.89 |  |  | 30 | 80 | 400 | 20000 | 196.55 | 5700 | 4800 | 900 | 185 | 355 | 210 | 150
01/03/2021 | 12:21 | 12:25 | 0.066667 | 15357 | 15367 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 150 | 5700 | 4800 | 900 | 185 | 355 | 210 | 150
01/03/2021 | 12:25 | 13:10 | 0.75 | 15367 | 15382 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 70; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 20 | 5100 | 4900 | 200 | 185 | 355 | 210 | 150
01/03/2021 | 13:10 | 13:36 | 0.43333 | 15382 | 15452 | 70 | Rotate |  | 15389 | 91.08 | 326.84 | 10316.1 | 2571.65 | -3845.33 | 2571.65 | 2.04 |  |  | 30 | 80 | 390 | 20000 | 161.54 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 13:46 | 14:10 | 0.4 | 15452 | 15548 | 96 | Rotate |  | 15485 | 91.99 | 326.5 | 10313.53 | 2651.83 | -3898.06 | 2651.83 | 1.01 |  |  | 30 | 80 | 390 | 20000 | 240 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 14:20 | 14:50 | 0.5 | 15548 | 15643 | 95 | Rotate |  | 15580 | 93.32 | 326.04 | 10309.13 | 2730.75 | -3950.75 | 2730.75 | 1.48 |  |  | 30 | 80 | 390 | 20000 | 190 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 15:00 | 15:05 | 0.083333 | 15643 | 15653 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 15:05 | 15:56 | 0.85 | 15653 | 15665 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 70; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 14.12 | 5100 | 4900 | 200 | 185 | 355 | 210 | 150
01/03/2021 | 15:56 | 16:24 | 0.46667 | 15665 | 15738 | 73 | Rotate |  | 15675 | 92.58 | 326.7 | 10304.24 | 2809.75 | -4003.29 | 2809.75 | 1.04 |  |  | 30 | 80 | 390 | 20000 | 156.43 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 17:05 | 17:29 | 0.4 | 15738 | 15833 | 95 | Rotate |  | 15770 | 93.53 | 325.81 | 10299.18 | 2888.63 | -4055.99 | 2888.63 | 1.37 |  |  | 30 | 80 | 390 | 20000 | 237.5 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 17:39 | 17:40 | 0.016667 | 15833 | 15842 | 9 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 540 | 5700 | 4900 | 800 | 185 | 355 | 210 | 150
01/03/2021 | 17:40 | 18:32 | 0.86667 | 15842 | 15852 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 11.54 | 5100 | 4900 | 200 | 190 | 355 | 210 | 150
01/03/2021 | 18:32 | 18:35 | 0.05 | 15852 | 15857 | 5 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 100 | 5700 | 4900 | 800 | 190 | 355 | 210 | 150
01/03/2021 | 21:15 | 21:34 | 0.31667 | 15857 | 15864 | 7 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 22.11 | 5100 | 4900 | 200 | 195 | 355 | 210 | 150
01/03/2021 | 21:34 | 21:58 | 0.4 | 15864 | 15928 | 64 | Rotate |  | 15865 | 91.58 | 325.96 | 10294.94 | 2967.2 | -4109.21 | 2967.2 | 2.06 |  |  | 30 | 80 | 390 | 20000 | 160 | 5700 | 4900 | 800 | 195 | 355 | 210 | 150
01/03/2021 | 22:02 | 22:35 | 0.55 | 15928 | 16023 | 95 | Rotate |  | 15960 | 92.66 | 325.86 | 10291.43 | 3045.82 | -4162.42 | 3045.82 | 1.14 |  |  | 30 | 80 | 390 | 20000 | 172.73 | 5700 | 4900 | 800 | 195 | 355 | 210 | 150
01/03/2021 | 22:40 | 22:45 | 0.083333 | 16023 | 16028 | 5 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 60 | 5700 | 4900 | 800 | 198 | 355 | 210 | 150
01/03/2021 | 22:45 | 23:30 | 0.75 | 16028 | 16040 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 80; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 16 | 5100 | 4900 | 200 | 203 | 355 | 210 | 150
01/03/2021 | 23:30 | 23:58 | 0.46667 | 16040 | 16118 | 78 | Rotate |  | 16055 | 91.85 | 325.8 | 10287.69 | 3124.36 | -4215.74 | 3124.36 | 0.85 |  |  | 30 | 80 | 390 | 20000 | 167.14 | 5700 | 4900 | 800 | 203 | 355 | 210 | 150
01/04/2021 | 00:00 | 00:36 | 0.6 | 16118 | 16212 | 94 | Rotate |  | 16149 | 93.25 | 325.26 | 10283.51 | 3201.78 | -4268.89 | 3201.78 | 1.6 |  |  | 30 | 80 | 390 | 20000 | 156.67 | 5700 | 4900 | 800 | 203 | 355 | 210 | 150
01/04/2021 | 00:42 | 00:48 | 0.1 | 16212 | 16217 | 5 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 50 | 5800 | 5100 | 700 | 205 | 355 | 210 | 150
01/04/2021 | 00:48 | 01:38 | 0.83333 | 16217 | 16232 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 18 | 5300 | 5100 | 200 | 205 | 355 | 210 | 150
01/04/2021 | 01:38 | 02:06 | 0.46667 | 16232 | 16306 | 74 | Rotate |  | 16243 | 92.09 | 326.22 | 10279.13 | 3279.38 | -4321.74 | 3279.38 | 1.6 |  |  | 32 | 80 | 390 | 21000 | 158.57 | 5800 | 5100 | 700 | 205 | 355 | 210 | 150
01/04/2021 | 02:14 | 02:43 | 0.48333 | 16306 | 16401 | 95 | Rotate |  | 16338 | 93.17 | 325.99 | 10274.77 | 3358.15 | -4374.67 | 3358.15 | 1.16 |  |  | 32 | 80 | 390 | 21000 | 196.55 | 5800 | 5100 | 700 | 208 | 355 | 210 | 150
01/04/2021 | 02:50 | 02:56 | 0.1 | 16401 | 16406 | 5 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 50 | 5800 | 5100 | 700 | 208 | 355 | 210 | 150
01/04/2021 | 02:56 | 03:40 | 0.73333 | 16406 | 16418 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 16.36 | 5300 | 5100 | 200 | 208 | 355 | 210 | 150
01/04/2021 | 03:40 | 04:08 | 0.46667 | 16418 | 16495 | 77 | Rotate |  | 16432 | 91.94 | 326.55 | 10270.58 | 3436.25 | -4426.81 | 3436.25 | 1.44 |  |  | 32 | 80 | 390 | 21000 | 165 | 5800 | 5100 | 700 | 214 | 355 | 210 | 150
01/04/2021 | 04:14 | 04:42 | 0.46667 | 16495 | 16590 | 95 | Rotate |  | 16527 | 93.62 | 326.39 | 10265.97 | 3515.34 | -4479.22 | 3515.34 | 1.78 |  |  | 32 | 80 | 390 | 21000 | 203.57 | 5800 | 5100 | 700 | 214 | 355 | 210 | 150
01/04/2021 | 04:50 | 09:00 | 4.1667 | 16590 | 16623 | 33 | Slide | 150 | 16621 | 91.92 | 327.3 | 10261.43 | 3593.94 | -4530.57 | 3593.94 | 2.05 |  |  | 75 |  | 390 |  | 7.92 | 5300 | 5100 | 200 | 214 | 355 | 210 | 150
01/04/2021 | 09:00 | 09:35 | 0.58333 | 16623 | 16684 | 61 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 104.57 | 5800 | 5100 | 700 | 214 | 355 | 210 | 150
01/04/2021 | 09:45 | 11:45 | 2 | 16684 | 16704 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 75; Drilling Parameters FLOW: 390; Drilling Parameters ROP: 10 | 5300 | 5100 | 200 | 214 | 355 | 210 | 150
01/04/2021 | 11:45 | 12:20 | 0.58333 | 16704 | 16779 | 75 | Rotate |  | 16716 | 89.26 | 327.84 | 10260.45 | 3674.12 | -4581.51 | 3674.12 | 2.86 |  |  | 32 | 80 | 390 | 21000 | 128.57 | 5800 | 5100 | 700 | 214 | 355 | 210 | 150
01/04/2021 | 12:30 | 12:53 | 0.38333 | 16779 | 16840 | 61 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 390; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 159.13 | 5800 | 5100 | 700 | 214 | 355 | 210 | 150