## Summary
Magnolia Oil & Gas / Grand Canyon 1H / LTX1124720 / Patterson 248
Report Date: | 06/30/2020 | Current Depth: | 17886
Start Date: | 04/28/2020 | Casing Depth: | 0
Daily Cost: | 9000 | Distance to TD:
Well Cost: | 148500 | Average ROP: | 0
Drilling Hours: | 81.08 | Svy MD: | 17886
24Hr Forcast: |  | Svy Inc: | 92.4
Current BHA: | BHA 5 (Lateral) | Svy Azi: | 332.4
Current BRT Hrs: | 125.25 | Svy TVD: | 10233.16
Bit Make / Model: | Halliburton / GTD64C | Svy NS: | 7911.38
POOH in last 24Hrs: | Yes | Svy EW: | -2533.26
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Dean Day | MWD Day: | Patrick Broussard
Directional Driller Night: | Kody Grisham | MWD Night: | John Brandon
RSS Engineer 1: |  | Third Man:
RSS Engineer 2: |  | Fourth Man:
Principal Plan: |  | Max BHT Well: | 315
24Hr Summary: |  | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MTR475076 | 7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick |  |  | Dirty |  | 8.08 | 8.08
MTR500011 | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  | Dirty |  | 15.17 | 15.17
MTR500048 | 6/7, 8.8 Stg. @ 2.12? w/ True Slick |  |  | Clean
MTR475062 | 6/7, 8.8 Stg. @ 2.12? w/ True Slick |  |  | Clean
PPM250004 | 6/7, 8.8 Stg. @ 2.0? w/ True Slick |  |  | Dirty |  | 96.50 | 96.50
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
500029 | UBHO |  |  | Dirty |  | 119.75 | 119.75
ZSB500031 | UBHO |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Total Drilled (Usft): |  | 17781 |  |  | Total Days: |  | 15
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 0 | 13.5 | 105 | 3005 | 2900 |  | 451.95 |  | 7.03 | 6.42 | 7.56 | 13.5
2 | 2 | 9.875 | 3005 | 10335 | 7330 |  | 186.2 |  | 9.66 | 39.37 | 42.88 | 63.42
3 | 3 | 6.75 | 10335 | 10862 | 527 |  | 44.54 |  | 78.37 | 11.83 | 15.16 | 30.75
4 | 4 | 6.75 | 10862 | 10954 | 92 |  | 16 |  | 100 | 5.75 | 8.09 | 22
5 | 5 | 6.75 | 10954 | 17886 | 6932 |  | 85.49 |  | 12.29 | 81.08 | 96.48 | 125.25
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
0 | Baker Hughes |  | SPL616 |  | 13.5 | Green / RR |  |  |  | 1.353 | 2900 | 6.4167 | 451.95
2 | Ulterra |  | SPL613 |  | 9.875 | Green |  |  |  | 1.353 | 7330 | 39.3667 | 186.2
3 | Ulterra |  | U611S |  | 6.75 | 0-0 |  | 1-1 |  | 1.178 | 527 | 11.8333 | 44.54
4 | Baker Hughes |  | U611S |  | 6.75 | 0-0 |  | 0-1 |  | 1.144 | 92 | 5.75 | 16
5 | Halliburton |  | GTD64C |  | 6.75 | 0-0 |  | 1-1 |  | 1.178 | 6932 | 81.0833 | 85.49
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 1.5 | 6.37 | 2900 |  | 451.95
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 2.12 | 5.87 | 7330 |  | 186.2
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5 | 2 | 3.94 | 527 |  | 44.54
4 | PDCI |  | 7/8 3.8 |  | 7/8 | 3.80 | 5 | 2.5 | 4 | 92 |  | 16
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5 | 2 | 3.85 | 6932 |  | 85.49
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Dean Day |  | Jeff Wells |  | Patrick Broussard |  | Blake Goodrum |  | James Dyer |  | Bobby Guin |  | David Lablanc
Jonathan Moore |  | Kody Grisham |  | Russell Arnold |  | John Brandon
Nathan Marks
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.37 |  | 2900 |  | 453.83 |  |  |  | 1 |  | 6.39
INT: INTERMEDIATE |  |  | 3.99 / 2.07 |  | 7330 |  | 186.18 |  | 1.27 / 11.33 |  | 1 |  | 39.37
CRV: CURVE |  |  | 3.26 / 1.59 |  | 619 |  | 35.21 |  | 1.08 / 22.50 |  | 2 |  | 17.58
LAT: LATERAL |  |  | 5.35 / 3.60 |  | 6932 |  | 85.51 |  | 4.50 / 0.00 |  | 1 |  | 81.07
Total |  |  | 14.61 |  | 17781 |  | 123.13 |  | 6.85 / 33.83 |  | 5 |  | 144.41
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA #1 (Surface) |  |  | 105.00 | 3005.00 | 646.52 | 2696.00 | 91.89 | 204.00 | 7.03 | 2900.00 | 453.83 | 6.39 | 2.22
INT: INTERMEDIATE-BHA #2 (Intermediate) |  |  | 3005.00 | 10335.00 | 397.72 | 6622.00 | 31.16 | 708.00 | 9.66 | 7330.00 | 186.18 | 39.37 | 22.72
CRV: CURVE-BHA 3 (Curve / Lateral) |  |  | 10335.00 | 10862.00 | 68.26 | 114.00 | 40.65 | 413.00 | 78.37 | 527.00 | 44.55 | 11.83 | 10.16
CRV: CURVE-BHA 4 (Bailout) |  |  | 10862.00 | 10954.00 | 0.00 | 0.00 | 16.00 | 92.00 | 100.00 | 92.00 | 16.00 | 5.75 | 5.75
LAT: LATERAL-BHA 5 (Lateral) |  |  | 10954.00 | 17886.00 | 146.90 | 6080.00 | 21.47 | 852.00 | 12.29 | 6932.00 | 85.51 | 81.07 | 39.68
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1124720 | Total Drilled(Usft) | 17781.00
Operator | Magnolia Oil & Gas | Drilling Hours | 144.45
Well Name | Grand Canyon 1H | Avg ROP(Usft/hr) | 123.09
Rig | Patterson 248 | Rotary Drilled(Usft) | 15512.00
State | Texas | Rotary Hours | 63.92
County | Washington | Rotary ROP(Usft/hr) | 242.69
Formation | Austin Chalk | Rotary % | 87.24
Start Date | 04/28/2020 | Slide Drilled(Usft) | 2269.00
End Date | 06/30/2020 | Slide Hours | 80.53
Days On Well | 15 | Slide ROP(Usft/hr) | 28.17
Start Depth (Usft) | 105.00 | Slide % | 12.76
End Depth (Usft) | 17886.00
Total Drilled (Usft) | 17781.00
# BHA's | 5
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 9.70 / 33.83
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 04/28/2020 | 04/30/2020 | 06/22/2020 | 06/25/2020
End Date | 04/29/2020 | 05/03/2020 | 06/25/2020 | 06/30/2020
Total Days | 2.00 | 4.00 | 3.26 | 5.35
Start Depth (Usft) | 105.00 | 3005.00 | 10335.00 | 10954.00
End Depth (Usft) | 3005.00 | 10335.00 | 10954.00 | 17886.00
Total Drilled(Usft) | 2900.00 | 7330.00 | 619.00 | 6932.00
Drilling Hours | 6.42 | 39.37 | 17.58 | 81.08
Circulating Hours | 1.17 | 3.52 | 5.67 | 15.42
Total D&C Hours | 7.58 | 42.88 | 23.25 | 96.50
Avg ROP(Usft/hr) | 451.95 | 186.20 | 35.20 | 85.49
Rotary Drilled(Usft) | 2696.00 | 6622.00 | 114.00 | 6080.00
Rotary Hours | 4.18 | 16.65 | 1.67 | 41.42
Rotary ROP(Usft/hr) | 644.46 | 397.72 | 68.40 | 146.80
Rotary % | 92.97 | 90.34 | 18.42 | 87.71
Slide Drilled(Usft) | 204.00 | 708.00 | 505.00 | 852.00
Slide Hours | 2.23 | 22.72 | 15.92 | 39.67
Slide ROP(Usft/hr) | 91.34 | 31.17 | 31.73 | 21.48
Slide % | 7.03 | 9.66 | 81.58 | 12.29
# BHA | 1 | 1 | 2 | 1
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.35 / 0.00 | 1.27 / 11.33 | 1.58 / 22.50 | 6.50 / 0.00
Total Phase Hrs | 8.92 | 49.75 | 38.25 | 86.42
Phase ROP (Usft/hr) | 325.23 | 147.34 | 16.18 | 80.22
Avg Motor Yield (°/100ft) | 6.81 | 14.35 | 15.17 | 20.30
Avg Rotary DLS (°/100ft) | 0.24 | 0.64 | 0.00 | 1.59
Avg Rotary TF | -122.67 | -131.07 | 0.00 | -54.76
Avg Slide Length (Usft) | 17.00 | 24.41 | 40.45 | 19.18
# Slides | 12 | 29 | 11 | 40
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5
Description | BHA #1 (Surface) | BHA #2 (Intermediate) | BHA 3 (Curve / Lateral) | BHA 4 (Bailout) | BHA 5 (Lateral)
Bit Size | 13.500 | 9.875 | 6.750 | 6.750 | 6.750
Bit Make/Model | Baker Hughes / SPL616 | Ulterra / SPL613 | Ulterra / U611S | Baker Hughes / U611S | Halliburton / GTD64C
Bit TFA | 1.353 | 1.353 | 1.178 | 1.144 | 1.178
Grade In | Green / RR | Green | 0-0 | 0-0 | 0-0
Grade Out |  |  | 1-1 | 0-1 | 1-1
Motor SN | PPM800032 | PPM800001 | MTR500011 | MTR475076 | PPM250004
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 7/8 3.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.90 | 7/8 / 5.90 | 6/7 / 8.80 | 7/8 / 3.80 | 6/7 / 8.80
WOB (klbs) | 8.00 / 9.58 / 10.00 | 10.00 / 31.36 / 180.00 | 14.00 / 23.93 / 35.00 | 15.00 / 22.50 / 25.00 | 15.00 / 29.57 / 40.00
Diff P (psi) | 25.00 / 325.96 / 550.00 | 300.00 / 518.25 / 650.00 | 100.00 / 100.00 / 100.00 | 150.00 / 150.00 / 150.00 | 150.00 / 797.87 / 1000.00
Bend | 1.500 | 2.120 | 2.000 | 2.500 | 2.000
Date In | 04/28/2020 | 04/30/2020 | 06/22/2020 | 06/24/2020 | 06/25/2020
Date Out | 04/29/2020 | 05/03/2020 | 06/24/2020 | 06/25/2020 | 06/30/2020
Time In | 18:00 | 21:15 | 24:00 | 07:15 | 07:00
Time Out | 07:30 | 12:40 | 06:45 | 05:15 | 12:15
BRT Hrs | 13.50 | 63.42 | 30.75 | 22.00 | 125.25
Start Depth (Usft) | 105.00 | 3005.00 | 10335.00 | 10862.00 | 10954.00
End Depth (Usft) | 3005.00 | 10335.00 | 10862.00 | 10954.00 | 17886.00
Total Drilled(Usft) | 2900.00 | 7330.00 | 527.00 | 92.00 | 6932.00
Drilling Hours | 6.42 | 39.37 | 11.83 | 5.75 | 81.08
Circulating Hours | 1.17 | 3.52 | 3.33 | 2.33 | 15.42
Total D&C Hours | 7.58 | 42.88 | 15.17 | 8.08 | 96.50
Avg ROP(Usft/hr) | 451.95 | 186.20 | 44.54 | 16.00 | 85.49
Rotary Drilled(Usft) | 2696.00 | 6622.00 | 114.00 | 0.00 | 6080.00
Rotary Hours | 4.18 | 16.65 | 1.67 | 0.00 | 41.42
Rotary ROP(Usft/hr) | 644.46 | 397.72 | 68.40 | 0.00 | 146.80
Rotary % | 92.97 | 90.34 | 21.63 | 0.00 | 87.71
Slide Drilled(Usft) | 204.00 | 708.00 | 413.00 | 92.00 | 852.00
Slide Hours | 2.23 | 22.72 | 10.17 | 5.75 | 39.67
Slide ROP(Usft/hr) | 91.34 | 31.17 | 40.62 | 16.00 | 21.48
Slide % | 7.03 | 9.66 | 78.37 | 100.00 | 12.29
Motor Failure | NO | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | YES | NO
LIH | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 6.81 | 14.35 | 13.41 | 68.09 | 20.30
Avg Rotary DLS (°/100ft) | 0.24 | 0.64 | 0.00 | 0.00 | 1.59
Avg Rotary TF | -122.67 | -131.07 | 0.00 | 0.00 | -54.76
Avg Slide Length (Usft) | 17.00 | 24.41 | 51.62 | 23.50 | 19.18
# Slides | 12 | 29 | 8 | 4 | 40

## Personnel Report
|  | Job # | LTX1124720 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31136 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Grand Canyon 1H
|  | Date: | 06/30/2020 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Grand Canyon 1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Blake Goodrum | Night MWD |  | 04/28/2020 - 00:00 | 05/03/2020 - 24:00 |  | 6.00 / 120.00
Blake Goodrum | Night MWD |  | 06/22/2020 - 00:00 | 06/23/2020 - 24:00 |  | 2.00 / 48.00
Dean Day | Day DD |  | 06/26/2020 - 00:00 | 06/30/2020 - 24:00 |  | 5.00 / 120.00
Dean Day | Day DD |  | 06/25/2020 - 18:00 | 06/25/2020 - 24:00 |  | 1.00 / 6.00
Jeff Wells | Night DD |  | 04/28/2020 - 00:00 | 05/03/2020 - 24:00 |  | 6.00 / 120.00
Jeff Wells | Night DD |  | 06/22/2020 - 00:00 | 06/23/2020 - 24:00 |  | 2.00 / 48.00
John Brandon | Night MWD |  | 06/24/2020 - 00:00 | 06/30/2020 - 24:00 |  | 7.00 / 168.00
Jonathan Moore | Day DD |  | 06/24/2020 - 00:00 | 06/25/2020 - 18:00 |  | 2.00 / 42.00
Kody Grisham | Night DD |  | 06/24/2020 - 00:00 | 06/30/2020 - 24:00 |  | 7.00 / 168.00
Nathan Marks | Day DD |  | 04/28/2020 - 00:00 | 05/03/2020 - 24:00 |  | 6.00 / 120.00
Nathan Marks | Day DD |  | 06/22/2020 - 00:00 | 06/23/2020 - 24:00 |  | 2.00 / 48.00
Patrick Broussard | Day MWD |  | 06/24/2020 - 00:00 | 06/30/2020 - 24:00 |  | 7.00 / 168.00
Russell Arnold | Day MWD |  | 04/28/2020 - 00:00 | 05/03/2020 - 24:00 |  | 6.00 / 120.00
Russell Arnold | Day MWD |  | 06/22/2020 - 00:00 | 06/23/2020 - 24:00 |  | 2.00 / 48.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1124720 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Grand Canyon 1H | [7 empty] | Day DD: |  |  |  |  | Dean Day | [5 empty] | API #: |  |  |  | 42-477-31136
|  |  |  | AFE #: |  |  | 20DD0219MG | [7 empty] | Night DD: |  |  |  |  | Kody Grisham | [5 empty] | Company Man: |  |  |  | James Dyer
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Patrick Broussard | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | John Brandon | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 04/28/2020 | 04/29/2020 | 04/30/2020 | 05/01/2020 | 05/02/2020 | 05/03/2020 | 05/04/2020 | 05/05/2020 | 05/06/2020 | 05/07/2020 | 05/08/2020 | 05/09/2020 | 05/10/2020 | 05/11/2020 | 05/12/2020 | 05/13/2020 | 05/14/2020 | 05/15/2020 | 05/16/2020 | 05/17/2020 | 05/18/2020 | 05/19/2020 | 05/20/2020 | 05/21/2020 | 05/22/2020 | 05/23/2020 | 05/24/2020 | 05/25/2020 | 05/26/2020 | 05/27/2020 | 05/28/2020 | 05/29/2020 | 05/30/2020 | 05/31/2020 | 06/01/2020 | 06/02/2020 | 06/03/2020 | 06/04/2020 | 06/05/2020 | 06/06/2020 | 06/07/2020 | 06/08/2020 | 06/09/2020 | 06/10/2020 | 06/11/2020 | 06/12/2020 | 06/13/2020 | 06/14/2020 | 06/15/2020 | 06/16/2020 | 06/17/2020 | 06/18/2020 | 06/19/2020 | 06/20/2020 | 06/21/2020 | 06/22/2020 | 06/23/2020 | 06/24/2020 | 06/25/2020 | 06/26/2020 | 06/27/2020 | 06/28/2020 | 06/29/2020 | 06/30/2020 | 07/01/2020
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | 6 3/4" - Ulterra - U611S |  | Steel | 39992 | 3 | 10 | [54 empty] | O | X | X | X | O | O | O | O | O | O
Bit |  | 6.75 | 6 3/4" - Ulterra - U611S |  | Steel | 40962 | 2 | 8 | [56 empty] | O | X | X | O | O | O | O | O
Bit |  | 6.75 | 6 3/4" - Halliburton GTD64C |  | Steel | 13430004 | 6 | 6 | [58 empty] | X | X | X | X | X | X
Cross Over |  |  | X/O- XT-39P x DS42B |  | Steel | GT55331421 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.25 | XO- Delta 425B x DS42P |  | Steel | DR38846 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Cross Over |  | 5.25 | XO- DS42B x Delta 425P |  | Steel | DR38852 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500029 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
MWD / LWD |  |  | UBHO |  | Steel | ZSB500031 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick |  | Steel | MTR475076 | 2 | 10 | [54 empty] | O | O | O | X | X | O | O | O | O | O
Motor |  | 5 | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  | Steel | MTR500011 | 3 | 10 | [54 empty] | O | X | X | X | O | O | O | O | O | O
Motor |  | 5 | 6/7, 8.8 Stg. @ 2.12? w/ True Slick |  | Steel | MTR500048 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Motor |  | 4.938 | 6/7, 8.8 Stg. @ 2.12? w/ True Slick |  | Steel | MTR475062 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Motor |  |  | 6/7, 8.8 Stg. @ 2.0? w/ True Slick |  | Steel | PPM250004 | 6 | 10 | [54 empty] | O | O | O | O | X | X | X | X | X | X
Collar |  | 4.938 | NMDC |  | Non-Mag | SD55819 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Collar |  | 5 | NMPC |  | Steel | 50-10-479 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Collar |  | 5 | NMDC |  | Non-Mag | SD56283 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Collar |  | 4.938 | NMDC |  | Non-Mag | SD56287 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Collar |  |  | NMDC |  | Non-Mag | SD56703 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Collar |  |  | NMPC |  | Steel | GT50-10-585 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 27 Stands- 4 1/2" Drill Pipe |  | Steel | Rig 5 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  | 5 | Float Sub |  | Steel | SD115376 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD115393 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119074 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.75 | BTI Valve |  | Steel | 306844 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Sub |  | 5.25 | X/O- XT-39P x DS-42B |  | Steel | GT52331286 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Sub |  |  | 5" Float Sub |  | Steel | SDI119029 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119067 | 0 | 10 | [54 empty] | O | O | O | O | O | O | O | O | O | O
Agitator |  | 5.188 | NOV Shock Sub / Agitator / Safety Joint |  | Steel | 525-OD-007 | 9 | 10 | [54 empty] | O | X | X | X | X | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Dean Day |  |  |  | 6 | [59 empty] | 1 | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Jonathan Moore |  |  |  | 2 | [58 empty] | 1 | 1
Day DD |  |  | Nathan Marks |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1
Night DD |  |  | Jeff Wells |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1
Night DD |  |  | Kody Grisham |  |  |  | 7 | [58 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Patrick Broussard |  |  |  | 7 | [58 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Russell Arnold |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1
Night MWD |  |  | Blake Goodrum |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1
Night MWD |  |  | John Brandon |  |  |  | 7 | [58 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Grand Canyon 1H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0219MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
DIR10 | Innova PC |  |  |  |  | Clean |  | 06/21/2020
MTR475076 | 7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick | 5 | 26.14 |  | XT-39 / 3 1/2 Reg | Dirty |  | 06/21/2020
SD55819 | NMDC | 4.938 | 30.87 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
50-10-479 | NMPC | 5 | 9.87 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
SD115376 | Float Sub | 5 | 2.61 |  | XT-39 / XT-39 | Clean |  | 06/21/2020
SD115393 | Lift Sub |  |  |  | XT-39 | Clean |  | 06/21/2020
SD119074 | Lift Sub |  |  |  | XT-39 | Clean |  | 06/21/2020
LC1115 | Lift Cap |  |  |  | XT-39 | Clean |  | 06/21/2020
306844 | BTI Valve | 4.75 | 2.28 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
MTR500011 | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick | 5 | 33.1 |  | XT-39 / 3 1/2 Reg | Dirty |  | 06/21/2020
GT52331286 | X/O- XT-39P x DS-42B | 5.25 | 3.09 |  | DS-42 / XT-39 | Dirty |  | 06/21/2020
Rig 5 | 27 Stands- 4 1/2" Drill Pipe | 4.5 | 2608.57 |  | DS-42 / DS-42 | Dirty |  | 06/21/2020
SDI119029 | 5" Float Sub |  |  |  | XT-39 / XT-39 | Clean |  | 06/21/2020
MTR500048 | 6/7, 8.8 Stg. @ 2.12? w/ True Slick | 5 | 33.4 |  | XT-39 / 3 1/2 Reg | Clean |  | 06/21/2020
MTR475062 | 6/7, 8.8 Stg. @ 2.12? w/ True Slick | 4.938 | 33.32 |  | XT-39 / 3 1/2 Reg | Clean |  | 06/21/2020
525-OD-007 | NOV Shock Sub / Agitator / Safety Joint | 5.188 | 29.16 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
39992 | 6 3/4" - Ulterra - U611S | 6.75 | 0.6 |  | 3 1/2 Reg | Dirty |  | 06/21/2020
500029 | UBHO | 5.25 | 3.44 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
PPM250004 | 6/7, 8.8 Stg. @ 2.0? w/ True Slick |  |  |  | XT-39 / 3 1/2 Reg | Dirty |  | 06/21/2020
ZSB500031 | UBHO |  |  |  | XT-39 / XT-39 | Clean |  | 06/21/2020
SD56283 | NMDC | 5 | 31.34 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
SD56287 | NMDC | 4.938 | 31 |  | XT-39 / XT-39 | Dirty |  | 06/21/2020
SD56703 | NMDC |  |  |  | XT-39 / XT-39 | Clean |  | 06/21/2020
GT50-10-585 | NMPC |  |  |  | XT-39 / XT-39 | Clean |  | 06/21/2020
SD119067 | Float Sub |  |  |  | XT-39 / XT-39 | Clean |  | 06/21/2020
GT55331421 | X/O- XT-39P x DS42B |  |  |  | DS-42 / XT-39 | Clean |  | 06/21/2020
WIN41 | Winserve Computer |  |  |  |  | Clean |  | 06/21/2020
DR38846 | XO- Delta 425B x DS42P | 5.25 | 3.23 |  | Delta 425 / DS-42 | Dirty |  | 06/21/2020
DR38852 | XO- DS42B x Delta 425P | 5.25 | 3.31 |  | DS-42 / Delta 425 | Dirty |  | 06/21/2020
40962 | 6 3/4" - Ulterra - U611S | 6.75 | 0.6 |  | 3 1/2 Reg | Dirty |  | 06/23/2020
13430004 | 6 3/4" - Halliburton GTD64C | 6.75 | 0.6 |  | 3 1/2 Reg | Dirty |  | 06/25/2020
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Grand Canyon 1H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
13 1/2 - Ulterra - SPL616 | 49754 | 04/28/2020 | 06/30/2020 | 64 | 1 | 1 |  | 1.17 | 6.42 | 13.5
7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS | PPM800032 | 04/28/2020 | 06/30/2020 | 64 | 1 | 1 |  | 1.17 | 6.42 | 13.5
13 Stabilizer | 603255 | 04/28/2020 | 06/30/2020 | 64 | 1 | 1 |  | 1.17 | 6.42 | 13.5
Pony Collar | 46071 | 04/28/2020 | 06/30/2020 | 64 | 3 | 1 ,2 |  | 4.68 | 45.78 | 76.92
8 UBHO | ZSB775186 | 04/28/2020 | 06/30/2020 | 64 | 3 | 1 ,2 |  | 4.68 | 45.78 | 76.92
Drill Collar | 51269 | 04/28/2020 | 06/30/2020 | 64 | 3 | 1 ,2 |  | 4.68 | 45.78 | 76.92
Drill Collar | 56067 | 04/28/2020 | 06/30/2020 | 64 | 3 | 1 ,2 |  | 4.68 | 45.78 | 76.92
X/O 4 1/2 IFB x 6 5/8 RegP | 113667 | 04/28/2020 | 06/30/2020 | 64 | 1 | 1 |  | 1.17 | 6.42 | 13.5
9 7/8 - Ulterra - SPL613 | 47857 | 04/28/2020 | 06/30/2020 | 64 | 3 | 2 |  | 3.52 | 39.37 | 63.42
7 3/4- 7/8 5.9 Stg 2.12? True Slick | PPM800001 | 04/28/2020 | 06/30/2020 | 64 | 3 | 2 |  | 3.52 | 39.37 | 63.42
X/O 4 1/2 XHB x 6 5/8 RegP | 117717 | 04/28/2020 | 06/30/2020 | 64 | 3 | 2 |  | 3.52 | 39.37 | 63.42
2 Stands 6 1/2 DCs | Rig-2 | 04/28/2020 | 06/30/2020 | 64 | 3 | 2 |  | 3.52 | 39.37 | 63.42
X/O 4 1/2 IFB x 4 1/2 XHP | 110280 | 04/28/2020 | 06/30/2020 | 64 | 3 | 2 |  | 3.52 | 39.37 | 63.42
6 3/4 - Ulterra - U611S | 39992 | 06/21/2020 | 06/30/2020 | 10 | 1 | 3 |  | 3.33 | 11.83 | 30.75
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick | MTR500011 | 06/21/2020 | 06/30/2020 | 10 | 1 | 3 |  | 3.33 | 11.83 | 30.75
BTI Valve | 306844 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
NMPC | 50-10-479 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
UBHO | 500029 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
NMDC | SD56287 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
NMDC | SD56283 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
NMDC | SD55819 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
X/O- XT-39P x DS-42B | GT52331286 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
XO- Delta 425B x DS42P | DR38846 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
NOV Shock Sub / Agitator / Safety Joint | 525-OD-007 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
XO- DS42B x Delta 425P | DR38852 | 06/21/2020 | 06/30/2020 | 10 | 7 | 3 ,4 ,5 |  | 21.08 | 98.67 | 178
6 3/4" - Ulterra - U611S | 40962 | 06/23/2020 | 06/30/2020 | 8 | 1 | 4 |  | 2.33 | 5.75 | 22
7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick | MTR475076 | 06/21/2020 | 06/30/2020 | 10 | 1 | 4 |  | 2.33 | 5.75 | 22
6 3/4" - Halliburton GTD64C | 13430004 | 06/25/2020 | 06/30/2020 | 6 | 5 | 5 |  | 15.42 | 81.08 | 125.25
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick | PPM250004 | 06/21/2020 | 06/30/2020 | 10 | 5 | 5 |  | 15.42 | 81.08 | 125.25
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well
Facility |  |  | Grand Canyon-Levi Goodrich - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Grand Canyon 1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Grand Canyon 1H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 332.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Grand Canyon-Levi Goodrich - Washington County, TX
Map Northing |  |  | 223720.57 US survey foot |  |  | Map Easting |  |  | 3155518.18 US survey foot
Latitude |  |  | 30° 13' 46.34716" N |  |  | Longitude |  |  | 96° 40' 26.06754" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.885
Well: |  |  | Grand Canyon 1H
Local North |  |  | 0.01 Usft |  |  | Local East |  |  | -0.00 Usft
Map Northing |  |  | 223720.58 US survey foot |  |  | Map Easting |  |  | 3155518.18 US survey foot
Latitude |  |  | 30° 13' 46.347" N |  |  | Longitude |  |  | 96° 40' 26.068" W
Depth Datum |  |  | Well |  |  | Datum Elevation |  |  | 332.00 Usft
GL Elevation |  |  | 304.00 Usft
Grid Convergence |  |  | 1.885
Well bore: |  |  | Grand Canyon 1H
Magnetic Model |  |  | User Defined |  |  | Date |  |  | 30/03/2020
Total Field (nT) |  |  | 46758.6 |  |  | Dip Angle (°) |  |  | 58.9
Declination (°) |  |  | 3.1
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 335.04
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Grand Canyon 1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2929 |  |  | Grand Canyon 1H S1 |  |  | MWD+HDGM
2929 |  |  | 10265 |  |  | Grand Canyon 1H S2 |  |  | MWD+HDGM
10335 |  |  | 17886 |  |  | Grand Canyon 1H S3 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -332 | 223720.58 | 3155518.18 | 30.2295 | -96.6739 | 0
138 | 0.5 | 325 | 138 | 0.49 | -0.35 | 0.59 | 0.36 | 0.36 | 25.36 | 325 | 138 | -194 | 223721.07 | 3155517.83 | 30.2295 | -96.6739 | 325
231 | 0.6 | 307.6 | 230.99 | 1.12 | -0.96 | 1.42 | 0.21 | 0.11 | -18.71 | -67.98 | 93 | -101.01 | 223721.7 | 3155517.22 | 30.2295 | -96.6739 | 319.35
322 | 0.5 | 315.4 | 321.99 | 1.7 | -1.62 | 2.22 | 0.14 | -0.11 | 8.57 | 147.03 | 91 | -10.01 | 223722.28 | 3155516.56 | 30.2295 | -96.6739 | 316.31
416 | 0.4 | 313.9 | 415.99 | 2.22 | -2.14 | 2.91 | 0.11 | -0.11 | -1.6 | -174.03 | 94 | 83.99 | 223722.8 | 3155516.04 | 30.2295 | -96.6739 | 315.93
511 | 0.4 | 319.5 | 510.98 | 2.7 | -2.6 | 3.54 | 0.04 | 0 | 5.89 | 92.8 | 95 | 178.98 | 223723.28 | 3155515.58 | 30.2295 | -96.6739 | 316.07
605 | 0.6 | 284.8 | 604.98 | 3.07 | -3.29 | 4.17 | 0.38 | 0.21 | -36.91 | -74.72 | 94 | 272.98 | 223723.65 | 3155514.89 | 30.2295 | -96.6739 | 313.07
699 | 0.4 | 287.6 | 698.98 | 3.3 | -4.08 | 4.71 | 0.21 | -0.21 | 2.98 | 174.43 | 94 | 366.98 | 223723.88 | 3155514.1 | 30.2295 | -96.6739 | 308.97
792 | 0.4 | 258.2 | 791.98 | 3.33 | -4.7 | 5 | 0.22 | 0 | -31.61 | -104.7 | 93 | 459.97 | 223723.91 | 3155513.48 | 30.2295 | -96.6739 | 305.29
887 | 0.4 | 6.5 | 886.97 | 3.59 | -4.99 | 5.36 | 0.68 | 0 | 114 | 144.15 | 95 | 554.97 | 223724.17 | 3155513.19 | 30.2296 | -96.6739 | 305.74
981 | 0.8 | 26.9 | 980.97 | 4.5 | -4.66 | 6.05 | 0.48 | 0.43 | 21.7 | 38.56 | 94 | 648.97 | 223725.08 | 3155513.52 | 30.2296 | -96.6739 | 314.04
1076 | 0.6 | 33.2 | 1075.96 | 5.51 | -4.08 | 6.72 | 0.23 | -0.21 | 6.63 | 162.08 | 95 | 743.96 | 223726.09 | 3155514.1 | 30.2296 | -96.6739 | 323.45
1170 | 1 | 35.2 | 1169.95 | 6.59 | -3.34 | 7.39 | 0.43 | 0.43 | 2.13 | 4.99 | 94 | 837.95 | 223727.17 | 3155514.84 | 30.2296 | -96.6739 | 333.12
1264 | 1.4 | 35.9 | 1263.93 | 8.19 | -2.2 | 8.35 | 0.43 | 0.43 | 0.74 | 2.45 | 94 | 931.93 | 223728.77 | 3155515.98 | 30.2296 | -96.6739 | 345
1359 | 1.6 | 41.3 | 1358.9 | 10.13 | -0.64 | 9.45 | 0.26 | 0.21 | 5.68 | 37.97 | 95 | 1026.9 | 223730.71 | 3155517.54 | 30.2296 | -96.6739 | 356.39
1453 | 2 | 41.2 | 1452.85 | 12.35 | 1.31 | 10.64 | 0.43 | 0.43 | -0.11 | -0.5 | 94 | 1120.85 | 223732.93 | 3155519.49 | 30.2296 | -96.6739 | 6.04
1547 | 2.4 | 34.2 | 1546.78 | 15.21 | 3.49 | 12.32 | 0.51 | 0.43 | -7.45 | -37.42 | 94 | 1214.78 | 223735.79 | 3155521.67 | 30.2296 | -96.6739 | 12.93
1641 | 2.5 | 30.6 | 1640.7 | 18.6 | 5.64 | 14.48 | 0.2 | 0.11 | -3.83 | -58.79 | 94 | 1308.7 | 223739.18 | 3155523.82 | 30.2296 | -96.6739 | 16.87
1736 | 2.5 | 33.3 | 1735.61 | 22.12 | 7.84 | 16.75 | 0.12 | 0 | 2.84 | 91.35 | 95 | 1403.61 | 223742.7 | 3155526.02 | 30.2296 | -96.6739 | 19.51
1830 | 2.4 | 24.3 | 1829.52 | 25.63 | 9.77 | 19.11 | 0.42 | -0.11 | -9.57 | -109.04 | 94 | 1497.52 | 223746.21 | 3155527.95 | 30.2296 | -96.6739 | 20.87
1924 | 2.8 | 23.6 | 1923.42 | 29.52 | 11.5 | 21.91 | 0.43 | 0.43 | -0.74 | -4.89 | 94 | 1591.42 | 223750.1 | 3155529.68 | 30.2296 | -96.6739 | 21.28
2018 | 2.6 | 24.2 | 2017.32 | 33.57 | 13.29 | 24.83 | 0.21 | -0.21 | 0.64 | 172.26 | 94 | 1685.32 | 223754.15 | 3155531.47 | 30.2296 | -96.6739 | 21.6
2111 | 2.9 | 26.4 | 2110.21 | 37.6 | 15.2 | 27.68 | 0.34 | 0.32 | 2.37 | 20.48 | 93 | 1778.21 | 223758.18 | 3155533.38 | 30.2296 | -96.6739 | 22.01
2206 | 3.7 | 31.9 | 2205.05 | 42.36 | 17.89 | 30.85 | 0.9 | 0.84 | 5.79 | 24.35 | 95 | 1873.05 | 223762.94 | 3155536.07 | 30.2297 | -96.6738 | 22.9
2299 | 4.4 | 33.6 | 2297.82 | 47.88 | 21.45 | 34.35 | 0.76 | 0.75 | 1.83 | 10.58 | 93 | 1965.82 | 223768.46 | 3155539.63 | 30.2297 | -96.6738 | 24.14
2393 | 5.5 | 38.6 | 2391.47 | 54.4 | 26.26 | 38.24 | 1.26 | 1.17 | 5.32 | 23.92 | 94 | 2059.47 | 223774.98 | 3155544.44 | 30.2297 | -96.6738 | 25.77
2487 | 6.7 | 39.3 | 2484.94 | 62.17 | 32.54 | 42.63 | 1.28 | 1.28 | 0.74 | 3.9 | 94 | 2152.94 | 223782.75 | 3155550.72 | 30.2297 | -96.6738 | 27.63
2581 | 7.9 | 39.5 | 2578.17 | 71.39 | 40.12 | 47.79 | 1.28 | 1.28 | 0.21 | 1.31 | 94 | 2246.17 | 223791.97 | 3155558.3 | 30.2297 | -96.6738 | 29.34
2675 | 8.7 | 36.8 | 2671.19 | 82.07 | 48.49 | 53.94 | 0.95 | 0.85 | -2.87 | -27.32 | 94 | 2339.19 | 223802.65 | 3155566.67 | 30.2298 | -96.6737 | 30.58
2769 | 10.3 | 36.4 | 2763.9 | 94.53 | 57.74 | 61.34 | 1.7 | 1.7 | -0.43 | -2.56 | 94 | 2431.89 | 223815.11 | 3155575.92 | 30.2298 | -96.6737 | 31.42
2929 | 11.3 | 36.1 | 2921.06 | 118.71 | 75.46 | 75.78 | 0.63 | 0.62 | -0.19 | -3.36 | 160 | 2589.06 | 223839.29 | 3155593.64 | 30.2299 | -96.6737 | 32.44
3050 | 10.9 | 35.4 | 3039.8 | 137.61 | 89.08 | 87.17 | 0.35 | -0.33 | -0.58 | -161.72 | 121 | 2707.79 | 223858.19 | 3155607.26 | 30.2299 | -96.6736 | 32.91
3144 | 10.6 | 33.2 | 3132.15 | 152.09 | 98.96 | 96.13 | 0.54 | -0.32 | -2.34 | -127.25 | 94 | 2800.15 | 223872.67 | 3155617.14 | 30.2299 | -96.6736 | 33.05
3239 | 12.3 | 31.8 | 3225.25 | 168 | 109.08 | 106.29 | 1.81 | 1.79 | -1.47 | -9.97 | 95 | 2893.25 | 223888.58 | 3155627.26 | 30.23 | -96.6735 | 32.99
3333 | 12.8 | 31.5 | 3317.01 | 185.39 | 119.79 | 117.53 | 0.54 | 0.53 | -0.32 | -7.57 | 94 | 2985 | 223905.97 | 3155637.97 | 30.23 | -96.6735 | 32.87
3427 | 13.1 | 30.9 | 3408.62 | 203.41 | 130.7 | 129.26 | 0.35 | 0.32 | -0.64 | -24.43 | 94 | 3076.61 | 223923.99 | 3155648.88 | 30.2301 | -96.6735 | 32.72
3521 | 13.2 | 29.4 | 3500.15 | 221.9 | 141.44 | 141.49 | 0.38 | 0.11 | -1.6 | -74.4 | 94 | 3168.15 | 223942.48 | 3155659.62 | 30.2301 | -96.6734 | 32.51
3615 | 13.1 | 28.2 | 3591.69 | 240.64 | 151.75 | 154.13 | 0.31 | -0.11 | -1.28 | -110.7 | 94 | 3259.68 | 223961.22 | 3155669.93 | 30.2302 | -96.6734 | 32.23
3708 | 12.8 | 27.4 | 3682.32 | 259.08 | 161.47 | 166.74 | 0.38 | -0.32 | -0.86 | -149.53 | 93 | 3350.32 | 223979.66 | 3155679.65 | 30.2302 | -96.6734 | 31.93
3801 | 12.8 | 26.4 | 3773.01 | 277.45 | 170.79 | 179.47 | 0.24 | 0 | -1.08 | -90.49 | 93 | 3441.01 | 223998.03 | 3155688.97 | 30.2303 | -96.6733 | 31.61
3895 | 12.6 | 26.2 | 3864.71 | 295.98 | 179.94 | 192.4 | 0.22 | -0.21 | -0.21 | -167.7 | 94 | 3532.71 | 224016.56 | 3155698.12 | 30.2303 | -96.6733 | 31.3
3989 | 12.7 | 25.4 | 3956.43 | 314.51 | 188.9 | 205.42 | 0.21 | 0.11 | -0.85 | -60.67 | 94 | 3624.43 | 224035.09 | 3155707.08 | 30.2304 | -96.6733 | 30.99
4083 | 12.6 | 24.4 | 4048.15 | 333.18 | 197.57 | 218.69 | 0.26 | -0.11 | -1.06 | -115.03 | 94 | 3716.15 | 224053.76 | 3155715.75 | 30.2304 | -96.6732 | 30.67
4178 | 12.7 | 30.1 | 4140.84 | 351.65 | 207.09 | 231.42 | 1.32 | 0.11 | 6 | 88.2 | 95 | 3808.84 | 224072.23 | 3155725.27 | 30.2305 | -96.6732 | 30.49
4271 | 12.7 | 33.4 | 4231.57 | 369.03 | 217.84 | 242.64 | 0.78 | 0 | 3.55 | 91.61 | 93 | 3899.57 | 224089.61 | 3155736.02 | 30.2305 | -96.6732 | 30.55
4365 | 12.4 | 32.3 | 4323.32 | 386.19 | 228.92 | 253.52 | 0.41 | -0.32 | -1.17 | -141.99 | 94 | 3991.32 | 224106.77 | 3155747.1 | 30.2306 | -96.6731 | 30.66
4458 | 12.4 | 30.1 | 4414.16 | 403.27 | 239.27 | 264.64 | 0.51 | 0 | -2.37 | -91.07 | 93 | 4082.15 | 224123.85 | 3155757.45 | 30.2306 | -96.6731 | 30.68
4553 | 12.2 | 28.7 | 4506.97 | 420.9 | 249.2 | 276.43 | 0.38 | -0.21 | -1.47 | -124.53 | 95 | 4174.97 | 224141.48 | 3155767.38 | 30.2307 | -96.6731 | 30.63
4646 | 12.3 | 27.4 | 4597.86 | 438.31 | 258.48 | 288.3 | 0.32 | 0.11 | -1.4 | -70.71 | 93 | 4265.86 | 224158.89 | 3155776.66 | 30.2307 | -96.673 | 30.53
4739 | 12.4 | 27.6 | 4688.71 | 455.95 | 267.67 | 300.42 | 0.12 | 0.11 | 0.22 | 23.26 | 93 | 4356.7 | 224176.53 | 3155785.85 | 30.2308 | -96.673 | 30.41
4834 | 12 | 26.1 | 4781.56 | 473.86 | 276.74 | 312.83 | 0.54 | -0.42 | -1.58 | -142.34 | 95 | 4449.56 | 224194.44 | 3155794.92 | 30.2308 | -96.673 | 30.29
4928 | 11.6 | 25.7 | 4873.57 | 491.15 | 285.13 | 324.96 | 0.43 | -0.43 | -0.43 | -168.64 | 94 | 4541.57 | 224211.73 | 3155803.31 | 30.2309 | -96.673 | 30.14
5022 | 11.3 | 23.5 | 4965.7 | 508.11 | 292.9 | 337.06 | 0.56 | -0.32 | -2.34 | -125.56 | 94 | 4633.7 | 224228.69 | 3155811.08 | 30.2309 | -96.6729 | 29.96
5117 | 11.9 | 29.8 | 5058.77 | 525.15 | 301.48 | 348.88 | 1.47 | 0.63 | 6.63 | 67.76 | 95 | 4726.76 | 224245.73 | 3155819.66 | 30.231 | -96.6729 | 29.86
5211 | 11.3 | 27.1 | 5150.85 | 541.76 | 310.5 | 360.14 | 0.86 | -0.64 | -2.87 | -139.18 | 94 | 4818.84 | 224262.34 | 3155828.68 | 30.231 | -96.6729 | 29.82
5305 | 12.1 | 29.7 | 5242.89 | 558.52 | 319.57 | 371.5 | 1.02 | 0.85 | 2.77 | 34.66 | 94 | 4910.89 | 224279.1 | 3155837.75 | 30.231 | -96.6728 | 29.78
5398 | 11.7 | 30 | 5333.89 | 575.15 | 329.12 | 382.55 | 0.44 | -0.43 | 0.32 | 171.36 | 93 | 5001.89 | 224295.73 | 3155847.3 | 30.2311 | -96.6728 | 29.78
5492 | 11.6 | 29.3 | 5425.96 | 591.64 | 338.51 | 393.54 | 0.18 | -0.11 | -0.74 | -125.62 | 94 | 5093.96 | 224312.22 | 3155856.69 | 30.2311 | -96.6728 | 29.78
5586 | 11.7 | 27.8 | 5518.02 | 608.32 | 347.58 | 404.83 | 0.34 | 0.11 | -1.6 | -72.47 | 94 | 5186.02 | 224328.9 | 3155865.76 | 30.2312 | -96.6727 | 29.74
5682 | 11.6 | 33.9 | 5612.05 | 624.94 | 357.5 | 415.71 | 1.29 | -0.1 | 6.35 | 97.62 | 96 | 5280.05 | 224345.52 | 3155875.68 | 30.2312 | -96.6727 | 29.77
5776 | 11.9 | 37.1 | 5704.08 | 640.51 | 368.62 | 425.14 | 0.76 | 0.32 | 3.4 | 66.85 | 94 | 5372.08 | 224361.09 | 3155886.8 | 30.2313 | -96.6727 | 29.92
5870 | 11.3 | 33.5 | 5796.16 | 655.92 | 379.55 | 434.5 | 1 | -0.64 | -3.83 | -131.41 | 94 | 5464.16 | 224376.5 | 3155897.73 | 30.2313 | -96.6726 | 30.06
5964 | 10.9 | 32.3 | 5888.4 | 671.12 | 389.38 | 444.12 | 0.49 | -0.43 | -1.28 | -150.58 | 94 | 5556.4 | 224391.7 | 3155907.56 | 30.2313 | -96.6726 | 30.12
6058 | 11.8 | 33.5 | 5980.56 | 686.64 | 399.43 | 453.96 | 0.99 | 0.96 | 1.28 | 15.29 | 94 | 5648.56 | 224407.22 | 3155917.61 | 30.2314 | -96.6726 | 30.19
6152 | 11.5 | 30.3 | 6072.63 | 702.75 | 409.47 | 464.32 | 0.76 | -0.32 | -3.4 | -116.47 | 94 | 5740.62 | 224423.33 | 3155927.65 | 30.2314 | -96.6725 | 30.23
6245 | 10.6 | 27.7 | 6163.9 | 718.33 | 418.12 | 474.8 | 1.11 | -0.97 | -2.8 | -152.3 | 93 | 5831.9 | 224438.91 | 3155936.3 | 30.2315 | -96.6725 | 30.2
6339 | 10.4 | 31.6 | 6256.33 | 733.21 | 426.58 | 484.72 | 0.79 | -0.21 | 4.15 | 107.63 | 94 | 5924.33 | 224453.79 | 3155944.76 | 30.2315 | -96.6725 | 30.19
6434 | 13.2 | 34.3 | 6349.31 | 749.47 | 437.19 | 494.99 | 3 | 2.95 | 2.84 | 12.48 | 95 | 6017.31 | 224470.05 | 3155955.37 | 30.2316 | -96.6724 | 30.26
6527 | 14.9 | 33.5 | 6439.53 | 768.22 | 449.78 | 506.67 | 1.84 | 1.83 | -0.86 | -6.91 | 93 | 6107.53 | 224488.8 | 3155967.96 | 30.2316 | -96.6724 | 30.35
6621 | 14.2 | 31.8 | 6530.51 | 788.1 | 462.52 | 519.31 | 0.87 | -0.74 | -1.81 | -149.43 | 94 | 6198.51 | 224508.67 | 3155980.7 | 30.2317 | -96.6724 | 30.41
6716 | 13.7 | 31.1 | 6622.71 | 807.63 | 474.47 | 531.98 | 0.56 | -0.53 | -0.74 | -161.69 | 95 | 6290.71 | 224528.21 | 3155992.65 | 30.2317 | -96.6723 | 30.43
6809 | 13.5 | 30.4 | 6713.1 | 826.42 | 485.66 | 544.3 | 0.28 | -0.22 | -0.75 | -140.89 | 93 | 6381.1 | 224547 | 3156003.84 | 30.2318 | -96.6723 | 30.44
6904 | 12.8 | 27.8 | 6805.61 | 845.3 | 496.17 | 556.97 | 0.96 | -0.74 | -2.74 | -141.06 | 95 | 6473.61 | 224565.88 | 3156014.35 | 30.2318 | -96.6722 | 30.41
6998 | 12 | 25.6 | 6897.42 | 863.32 | 505.25 | 569.48 | 0.99 | -0.85 | -2.34 | -150.51 | 94 | 6565.42 | 224583.9 | 3156023.43 | 30.2319 | -96.6722 | 30.34
7092 | 11.2 | 22.4 | 6989.5 | 880.57 | 512.95 | 581.87 | 1.09 | -0.85 | -3.4 | -142.75 | 94 | 6657.5 | 224601.15 | 3156031.13 | 30.2319 | -96.6722 | 30.22
7185 | 13.1 | 20.8 | 7080.41 | 898.78 | 520.14 | 595.34 | 2.07 | 2.04 | -1.72 | -10.83 | 93 | 6748.41 | 224619.36 | 3156038.32 | 30.232 | -96.6722 | 30.06
7280 | 12.8 | 18.6 | 7173 | 918.82 | 527.32 | 610.48 | 0.61 | -0.32 | -2.32 | -122.39 | 95 | 6840.99 | 224639.4 | 3156045.5 | 30.232 | -96.6721 | 29.85
7374 | 12 | 26.8 | 7264.81 | 937.41 | 535.05 | 624.08 | 2.06 | -0.85 | 8.72 | 118.4 | 94 | 6932.81 | 224657.99 | 3156053.23 | 30.2321 | -96.6721 | 29.72
7468 | 10.8 | 23 | 7356.95 | 954.24 | 542.89 | 636.02 | 1.51 | -1.28 | -4.04 | -149.81 | 94 | 7024.95 | 224674.82 | 3156061.07 | 30.2321 | -96.6721 | 29.64
7562 | 10.4 | 17.5 | 7449.35 | 970.44 | 548.89 | 648.18 | 1.16 | -0.43 | -5.85 | -114.26 | 94 | 7117.35 | 224691.02 | 3156067.07 | 30.2322 | -96.6721 | 29.49
7656 | 10.7 | 18.6 | 7541.76 | 986.8 | 554.22 | 660.76 | 0.38 | 0.32 | 1.17 | 34.42 | 94 | 7209.76 | 224707.38 | 3156072.4 | 30.2322 | -96.6721 | 29.32
7750 | 9.9 | 31.4 | 7634.26 | 1001.97 | 561.22 | 671.56 | 2.57 | -0.85 | 13.62 | 115.49 | 94 | 7302.26 | 224722.55 | 3156079.4 | 30.2322 | -96.672 | 29.25
7844 | 8.4 | 27.8 | 7727.06 | 1014.94 | 568.63 | 680.2 | 1.71 | -1.6 | -3.83 | -160.88 | 94 | 7395.06 | 224735.52 | 3156086.81 | 30.2323 | -96.672 | 29.26
7938 | 7.1 | 20 | 7820.2 | 1026.48 | 573.82 | 688.46 | 1.78 | -1.38 | -8.3 | -144.84 | 94 | 7488.2 | 224747.06 | 3156092 | 30.2323 | -96.672 | 29.21
8032 | 7.9 | 33.3 | 7913.41 | 1037.34 | 579.35 | 695.97 | 2.03 | 0.85 | 14.15 | 71.95 | 94 | 7581.41 | 224757.92 | 3156097.53 | 30.2323 | -96.672 | 29.18
8125 | 7.2 | 35.2 | 8005.6 | 1047.44 | 586.22 | 702.23 | 0.8 | -0.75 | 2.04 | 161.31 | 93 | 7673.6 | 224768.02 | 3156104.4 | 30.2324 | -96.6719 | 29.23
8216 | 6 | 30.8 | 8096 | 1056.19 | 591.94 | 707.75 | 1.43 | -1.32 | -4.84 | -159.32 | 91 | 7763.99 | 224776.77 | 3156110.12 | 30.2324 | -96.6719 | 29.27
8310 | 6.7 | 46.5 | 8189.43 | 1064.18 | 598.44 | 712.26 | 1.98 | 0.74 | 16.7 | 75.97 | 94 | 7857.42 | 224784.76 | 3156116.62 | 30.2324 | -96.6719 | 29.35
8403 | 5.7 | 45.9 | 8281.88 | 1071.13 | 605.69 | 715.5 | 1.08 | -1.08 | -0.65 | -176.59 | 93 | 7949.88 | 224791.71 | 3156123.87 | 30.2324 | -96.6719 | 29.49
8498 | 4.9 | 42.6 | 8376.47 | 1077.4 | 611.82 | 718.59 | 0.9 | -0.84 | -3.47 | -160.78 | 95 | 8044.47 | 224797.98 | 3156130 | 30.2324 | -96.6719 | 29.59
8592 | 4.8 | 40.2 | 8470.14 | 1083.36 | 617.08 | 721.78 | 0.24 | -0.11 | -2.55 | -117.43 | 94 | 8138.14 | 224803.94 | 3156135.26 | 30.2325 | -96.6718 | 29.67
8687 | 5.1 | 38 | 8564.78 | 1089.72 | 622.25 | 725.37 | 0.37 | 0.32 | -2.32 | -33.42 | 95 | 8232.78 | 224810.3 | 3156140.43 | 30.2325 | -96.6718 | 29.73
8781 | 4.6 | 36.8 | 8658.45 | 1096.03 | 627.08 | 729.05 | 0.54 | -0.53 | -1.28 | -169.13 | 94 | 8326.44 | 224816.61 | 3156145.26 | 30.2325 | -96.6718 | 29.78
8875 | 5 | 22.6 | 8752.12 | 1102.83 | 630.91 | 733.6 | 1.33 | 0.43 | -15.11 | -78.56 | 94 | 8420.12 | 224823.41 | 3156149.09 | 30.2325 | -96.6718 | 29.77
8969 | 4.6 | 34.1 | 8845.79 | 1109.74 | 634.6 | 738.3 | 1.11 | -0.43 | 12.23 | 118.23 | 94 | 8513.79 | 224830.32 | 3156152.78 | 30.2325 | -96.6718 | 29.76
9064 | 4.2 | 38.6 | 8940.51 | 1115.61 | 638.9 | 741.81 | 0.56 | -0.42 | 4.74 | 141.43 | 95 | 8608.51 | 224836.19 | 3156157.08 | 30.2325 | -96.6718 | 29.8
9158 | 2.9 | 44.2 | 9034.33 | 1120 | 642.71 | 744.19 | 1.43 | -1.38 | 5.96 | 167.85 | 94 | 8702.33 | 224840.58 | 3156160.89 | 30.2326 | -96.6718 | 29.85
9252 | 2.6 | 52.5 | 9128.22 | 1123.01 | 646.06 | 745.49 | 0.53 | -0.32 | 8.83 | 131.09 | 94 | 8796.22 | 224843.59 | 3156164.24 | 30.2326 | -96.6717 | 29.91
9346 | 1.5 | 46.9 | 9222.16 | 1125.14 | 648.65 | 746.34 | 1.19 | -1.17 | -5.96 | -172.47 | 94 | 8890.16 | 224845.72 | 3156166.83 | 30.2326 | -96.6717 | 29.96
9439 | 0.3 | 331.7 | 9315.15 | 1126.19 | 649.42 | 746.96 | 1.56 | -1.29 | 80.86 | -168.48 | 93 | 8983.15 | 224846.77 | 3156167.6 | 30.2326 | -96.6717 | 29.97
9533 | 2.2 | 320.6 | 9409.12 | 1127.8 | 648.16 | 748.96 | 2.03 | 2.02 | -11.81 | -12.84 | 94 | 9077.12 | 224848.38 | 3156166.34 | 30.2326 | -96.6717 | 29.89
9627 | 4.3 | 327.8 | 9502.97 | 1132.18 | 645.13 | 754.2 | 2.27 | 2.23 | 7.66 | 14.61 | 94 | 9170.97 | 224852.76 | 3156163.31 | 30.2326 | -96.6717 | 29.68
9672 | 5.6 | 329.9 | 9547.8 | 1135.51 | 643.13 | 758.06 | 2.92 | 2.89 | 4.67 | 8.98 | 45 | 9215.8 | 224856.09 | 3156161.31 | 30.2326 | -96.6718 | 29.53
9721 | 5.3 | 330.1 | 9596.58 | 1139.54 | 640.81 | 762.7 | 0.61 | -0.61 | 0.41 | 176.48 | 49 | 9264.57 | 224860.12 | 3156158.99 | 30.2326 | -96.6718 | 29.35
9816 | 7.9 | 330.5 | 9690.94 | 1149.02 | 635.4 | 773.58 | 2.74 | 2.74 | 0.42 | 1.21 | 95 | 9358.94 | 224869.6 | 3156153.58 | 30.2326 | -96.6718 | 28.94
9861 | 8.2 | 332 | 9735.49 | 1154.55 | 632.37 | 779.86 | 0.81 | 0.67 | 3.33 | 35.74 | 45 | 9403.49 | 224875.13 | 3156150.55 | 30.2327 | -96.6718 | 28.71
9910 | 9.3 | 332 | 9783.92 | 1161.13 | 628.87 | 787.31 | 2.24 | 2.24 | 0 | 0 | 49 | 9451.92 | 224881.71 | 3156147.05 | 30.2327 | -96.6718 | 28.44
10004 | 11.7 | 332.4 | 9876.34 | 1176.28 | 620.89 | 804.42 | 2.55 | 2.55 | 0.43 | 1.94 | 94 | 9544.34 | 224896.86 | 3156139.07 | 30.2327 | -96.6718 | 27.83
10049 | 14.5 | 331.1 | 9920.17 | 1185.26 | 616.05 | 814.6 | 6.26 | 6.22 | -2.89 | -6.64 | 45 | 9588.17 | 224905.84 | 3156134.23 | 30.2327 | -96.6718 | 27.46
10098 | 15.6 | 330.7 | 9967.49 | 1196.38 | 609.87 | 827.29 | 2.25 | 2.24 | -0.82 | -5.59 | 49 | 9635.48 | 224916.96 | 3156128.05 | 30.2328 | -96.6719 | 27.01
10193 | 18.6 | 338.8 | 10058.29 | 1221.65 | 598.13 | 855.15 | 4.03 | 3.16 | 8.53 | 42.37 | 95 | 9726.29 | 224942.23 | 3156116.31 | 30.2328 | -96.6719 | 26.09
10240 | 18.2 | 339.7 | 10102.89 | 1235.53 | 592.87 | 869.95 | 1.04 | -0.85 | 1.91 | 145.04 | 47 | 9770.89 | 224956.11 | 3156111.05 | 30.2329 | -96.6719 | 25.63
10265 | 17.8 | 339.5 | 10126.66 | 1242.77 | 590.18 | 877.65 | 1.62 | -1.6 | -0.8 | -171.31 | 25 | 9794.66 | 224963.35 | 3156108.36 | 30.2329 | -96.6719 | 25.4
10413 | 23.3 | 330.5 | 10265.23 | 1289.48 | 567.82 | 929.43 | 4.28 | 3.72 | -6.08 | -34.15 | 148 | 9933.22 | 225010.06 | 3156086 | 30.233 | -96.672 | 23.77
10508 | 32.7 | 330.6 | 10349.01 | 1328.27 | 545.92 | 973.84 | 9.89 | 9.89 | 0.11 | 0.33 | 95 | 10017.01 | 225048.85 | 3156064.1 | 30.2331 | -96.672 | 22.34
10602 | 40 | 336.1 | 10424.69 | 1378.1 | 521.18 | 1029.46 | 8.5 | 7.77 | 5.85 | 26.31 | 94 | 10092.69 | 225098.68 | 3156039.36 | 30.2333 | -96.6721 | 20.72
10697 | 51.8 | 341.5 | 10490.71 | 1441.66 | 496.87 | 1097.34 | 13.07 | 12.42 | 5.68 | 20.12 | 95 | 10158.71 | 225162.24 | 3156015.05 | 30.2335 | -96.6722 | 19.02
10791 | 61 | 339.9 | 10542.68 | 1515.45 | 470.97 | 1175.17 | 9.89 | 9.79 | -1.7 | -8.7 | 94 | 10210.67 | 225236.03 | 3155989.15 | 30.2337 | -96.6723 | 17.26
10885 | 77.5 | 335.4 | 10575.88 | 1596.37 | 437.49 | 1262.66 | 18.11 | 17.55 | -4.79 | -15.17 | 94 | 10243.88 | 225316.95 | 3155955.67 | 30.2339 | -96.6724 | 15.33
10980 | 93 | 332.5 | 10583.72 | 1681.15 | 396.02 | 1357.02 | 16.6 | 16.32 | -3.05 | -10.72 | 95 | 10251.72 | 225401.73 | 3155914.2 | 30.2341 | -96.6725 | 13.26
11075 | 94.2 | 331.2 | 10577.76 | 1764.74 | 351.29 | 1451.68 | 1.86 | 1.26 | -1.37 | -47.2 | 95 | 10245.76 | 225485.32 | 3155869.47 | 30.2344 | -96.6726 | 11.26
11171 | 91 | 333.8 | 10573.4 | 1849.79 | 307.02 | 1547.47 | 4.29 | -3.33 | 2.71 | 140.87 | 96 | 10241.4 | 225570.37 | 3155825.2 | 30.2346 | -96.6727 | 9.42
11266 | 89.9 | 333.2 | 10572.66 | 1934.81 | 264.64 | 1642.43 | 1.32 | -1.16 | -0.63 | -151.39 | 95 | 10240.66 | 225655.39 | 3155782.82 | 30.2348 | -96.6729 | 7.79
11361 | 87.9 | 332.7 | 10574.48 | 2019.39 | 221.44 | 1737.34 | 2.17 | -2.11 | -0.53 | -165.97 | 95 | 10242.48 | 225739.97 | 3155739.62 | 30.2351 | -96.673 | 6.26
11455 | 89.1 | 333.8 | 10576.94 | 2103.3 | 179.15 | 1831.26 | 1.73 | 1.28 | 1.17 | 42.52 | 94 | 10244.94 | 225823.88 | 3155697.33 | 30.2353 | -96.6731 | 4.87
11550 | 90.5 | 334.1 | 10577.27 | 2188.65 | 137.43 | 1926.24 | 1.51 | 1.47 | 0.32 | 12.1 | 95 | 10245.27 | 225909.23 | 3155655.61 | 30.2355 | -96.6732 | 3.59
11645 | 91.2 | 334.3 | 10575.86 | 2274.17 | 96.09 | 2021.22 | 0.77 | 0.74 | 0.21 | 15.94 | 95 | 10243.86 | 225994.75 | 3155614.27 | 30.2358 | -96.6734 | 2.42
11740 | 95.5 | 336.8 | 10570.31 | 2360.47 | 56.85 | 2116.02 | 5.23 | 4.53 | 2.63 | 30.07 | 95 | 10238.31 | 226081.05 | 3155575.03 | 30.236 | -96.6735 | 1.38
11835 | 97.6 | 336 | 10559.48 | 2446.95 | 19.07 | 2210.37 | 2.36 | 2.21 | -0.84 | -20.69 | 95 | 10227.47 | 226167.53 | 3155537.25 | 30.2363 | -96.6736 | 0.45
11932 | 98.5 | 334.8 | 10545.89 | 2534.28 | -20.91 | 2306.41 | 1.54 | 0.93 | -1.24 | -52.77 | 97 | 10213.89 | 226254.86 | 3155497.27 | 30.2365 | -96.6737 | 359.53
12027 | 96.6 | 334.6 | 10533.41 | 2619.42 | -61.16 | 2400.58 | 2.01 | -2 | -0.21 | -174.03 | 95 | 10201.41 | 226340 | 3155457.02 | 30.2367 | -96.6738 | 358.66
12122 | 95.2 | 333.9 | 10523.65 | 2704.53 | -102.21 | 2495.06 | 1.65 | -1.47 | -0.74 | -153.52 | 95 | 10191.64 | 226425.11 | 3155415.97 | 30.237 | -96.6739 | 357.84
12216 | 92.4 | 329.7 | 10517.41 | 2787.16 | -146.53 | 2588.68 | 5.36 | -2.98 | -4.47 | -123.59 | 94 | 10185.41 | 226507.74 | 3155371.65 | 30.2372 | -96.6741 | 356.99
12311 | 90.5 | 329.3 | 10515.01 | 2868.98 | -194.72 | 2683.2 | 2.04 | -2 | -0.42 | -168.11 | 95 | 10183.01 | 226589.56 | 3155323.46 | 30.2374 | -96.6742 | 356.12
12405 | 90.9 | 330.7 | 10513.86 | 2950.38 | -241.72 | 2776.82 | 1.55 | 0.43 | 1.49 | 74.05 | 94 | 10181.86 | 226670.96 | 3155276.46 | 30.2377 | -96.6744 | 355.32
12499 | 91.1 | 333 | 10512.22 | 3033.24 | -286.06 | 2870.66 | 2.46 | 0.21 | 2.45 | 85.01 | 94 | 10180.22 | 226753.82 | 3155232.12 | 30.2379 | -96.6745 | 354.61
12595 | 92.4 | 334.9 | 10509.29 | 3119.44 | -328.19 | 2966.59 | 2.4 | 1.35 | 1.98 | 55.58 | 96 | 10177.29 | 226840.02 | 3155189.99 | 30.2381 | -96.6746 | 353.99
12689 | 93.1 | 336.3 | 10504.78 | 3204.95 | -366.98 | 3060.47 | 1.66 | 0.74 | 1.49 | 63.38 | 94 | 10172.78 | 226925.53 | 3155151.2 | 30.2384 | -96.6747 | 353.47
12784 | 93.2 | 336.2 | 10499.56 | 3291.77 | -405.18 | 3155.31 | 0.15 | 0.11 | -0.11 | -44.95 | 95 | 10167.56 | 227012.35 | 3155113 | 30.2386 | -96.6748 | 352.98
12879 | 93.1 | 334.9 | 10494.34 | 3378.12 | -444.44 | 3250.16 | 1.37 | -0.11 | -1.37 | -94.37 | 95 | 10162.34 | 227098.7 | 3155073.74 | 30.2389 | -96.675 | 352.5
12973 | 93.8 | 336.1 | 10488.68 | 3463.5 | -483.35 | 3343.98 | 1.48 | 0.74 | 1.28 | 59.66 | 94 | 10156.68 | 227184.08 | 3155034.83 | 30.2391 | -96.6751 | 352.06
13067 | 95.3 | 335.7 | 10481.22 | 3549.03 | -521.61 | 3437.67 | 1.65 | 1.6 | -0.43 | -14.87 | 94 | 10149.22 | 227269.61 | 3154996.57 | 30.2393 | -96.6752 | 351.64
13162 | 95.3 | 337.7 | 10472.45 | 3635.91 | -559.03 | 3532.22 | 2.1 | 0 | 2.11 | 89.91 | 95 | 10140.45 | 227356.49 | 3154959.15 | 30.2396 | -96.6753 | 351.26
13256 | 92.7 | 339.9 | 10465.89 | 3723.32 | -592.93 | 3625.78 | 3.62 | -2.77 | 2.34 | 139.75 | 94 | 10133.89 | 227443.9 | 3154925.25 | 30.2398 | -96.6754 | 350.95
13352 | 91.2 | 339.8 | 10462.62 | 3813.39 | -625.98 | 3721.38 | 1.57 | -1.56 | -0.1 | -176.19 | 96 | 10130.62 | 227533.97 | 3154892.2 | 30.2401 | -96.6755 | 350.68
13446 | 90.8 | 339.4 | 10460.98 | 3901.48 | -658.74 | 3815.07 | 0.6 | -0.43 | -0.43 | -135 | 94 | 10128.98 | 227622.06 | 3154859.44 | 30.2403 | -96.6756 | 350.42
13541 | 90.6 | 339.5 | 10459.82 | 3990.43 | -692.09 | 3909.78 | 0.24 | -0.21 | 0.11 | 153.44 | 95 | 10127.82 | 227711.01 | 3154826.09 | 30.2406 | -96.6757 | 350.16
13635 | 92.1 | 339.2 | 10457.61 | 4078.36 | -725.23 | 4003.49 | 1.63 | 1.6 | -0.32 | -11.3 | 94 | 10125.61 | 227798.94 | 3154792.95 | 30.2408 | -96.6758 | 349.92
13730 | 94.3 | 339.1 | 10452.31 | 4167 | -758.98 | 4098.09 | 2.32 | 2.32 | -0.11 | -2.6 | 95 | 10120.3 | 227887.58 | 3154759.2 | 30.2411 | -96.6759 | 349.68
13826 | 96 | 337.4 | 10443.69 | 4255.8 | -794.41 | 4193.55 | 2.5 | 1.77 | -1.77 | -44.81 | 96 | 10111.69 | 227976.38 | 3154723.77 | 30.2413 | -96.676 | 349.43
13922 | 97.8 | 337 | 10432.16 | 4343.65 | -831.34 | 4288.78 | 1.92 | 1.88 | -0.42 | -12.42 | 96 | 10100.15 | 228064.23 | 3154686.84 | 30.2416 | -96.6761 | 349.17
14018 | 97.4 | 335.7 | 10419.46 | 4430.81 | -869.51 | 4383.91 | 1.41 | -0.42 | -1.35 | -107.16 | 96 | 10087.46 | 228151.39 | 3154648.67 | 30.2418 | -96.6762 | 348.9
14112 | 93.3 | 333.7 | 10410.69 | 4515.4 | -909.5 | 4477.47 | 4.85 | -4.36 | -2.13 | -153.99 | 94 | 10078.69 | 228235.98 | 3154608.68 | 30.242 | -96.6763 | 348.61
14208 | 90.5 | 332.7 | 10407.51 | 4601.03 | -952.76 | 4573.36 | 3.1 | -2.92 | -1.04 | -160.34 | 96 | 10075.51 | 228321.61 | 3154565.42 | 30.2423 | -96.6764 | 348.3
14302 | 89.9 | 332.7 | 10407.18 | 4684.56 | -995.87 | 4667.28 | 0.64 | -0.64 | 0 | 180 | 94 | 10075.18 | 228405.14 | 3154522.31 | 30.2425 | -96.6766 | 348
14397 | 89.4 | 332.3 | 10407.76 | 4768.83 | -1039.73 | 4762.18 | 0.67 | -0.53 | -0.42 | -141.34 | 95 | 10075.76 | 228489.41 | 3154478.45 | 30.2427 | -96.6767 | 347.7
14491 | 90.5 | 333.3 | 10407.85 | 4852.43 | -1082.7 | 4856.11 | 1.58 | 1.17 | 1.06 | 42.28 | 94 | 10075.84 | 228573.01 | 3154435.48 | 30.243 | -96.6768 | 347.42
14585 | 91.6 | 334.1 | 10406.12 | 4936.68 | -1124.34 | 4950.07 | 1.45 | 1.17 | 0.85 | 36.02 | 94 | 10074.12 | 228657.26 | 3154393.84 | 30.2432 | -96.677 | 347.17
14681 | 92.7 | 335.4 | 10402.52 | 5023.45 | -1165.26 | 5045.99 | 1.77 | 1.15 | 1.35 | 49.72 | 96 | 10070.52 | 228744.03 | 3154352.92 | 30.2435 | -96.6771 | 346.94
14775 | 94.2 | 336.2 | 10396.87 | 5109.03 | -1203.72 | 5139.81 | 1.81 | 1.6 | 0.85 | 28.01 | 94 | 10064.86 | 228829.61 | 3154314.46 | 30.2437 | -96.6772 | 346.74
14871 | 94.3 | 334.9 | 10389.75 | 5196.18 | -1243.35 | 5235.54 | 1.35 | 0.1 | -1.35 | -85.54 | 96 | 10057.75 | 228916.76 | 3154274.83 | 30.2439 | -96.6773 | 346.54
14965 | 92.6 | 334.3 | 10384.09 | 5280.93 | -1283.59 | 5329.36 | 1.92 | -1.81 | -0.64 | -160.57 | 94 | 10052.09 | 229001.51 | 3154234.59 | 30.2442 | -96.6774 | 346.34
15060 | 92.7 | 334.5 | 10379.7 | 5366.51 | -1324.6 | 5424.26 | 0.24 | 0.11 | 0.21 | 63.41 | 95 | 10047.7 | 229087.09 | 3154193.58 | 30.2444 | -96.6775 | 346.14
15155 | 93.9 | 334.5 | 10374.23 | 5452.12 | -1365.43 | 5519.09 | 1.26 | 1.26 | 0 | 0 | 95 | 10042.23 | 229172.7 | 3154152.75 | 30.2446 | -96.6777 | 345.94
15250 | 92.9 | 334.1 | 10368.6 | 5537.57 | -1406.55 | 5613.92 | 1.13 | -1.05 | -0.42 | -158.22 | 95 | 10036.6 | 229258.15 | 3154111.63 | 30.2449 | -96.6778 | 345.75
15344 | 92.8 | 334.2 | 10363.93 | 5622.06 | -1447.49 | 5707.79 | 0.15 | -0.11 | 0.11 | 135.03 | 94 | 10031.92 | 229342.64 | 3154070.69 | 30.2451 | -96.6779 | 345.56
15439 | 93.6 | 334.6 | 10358.62 | 5707.6 | -1488.47 | 5802.63 | 0.94 | 0.84 | 0.42 | 26.52 | 95 | 10026.62 | 229428.18 | 3154029.71 | 30.2454 | -96.678 | 345.38
15534 | 94.2 | 332.8 | 10352.16 | 5792.56 | -1530.46 | 5897.38 | 1.99 | 0.63 | -1.89 | -71.47 | 95 | 10020.16 | 229513.14 | 3153987.72 | 30.2456 | -96.6781 | 345.2
15628 | 92.2 | 333.2 | 10346.91 | 5876.18 | -1573.07 | 5991.17 | 2.17 | -2.13 | 0.43 | 168.7 | 94 | 10014.91 | 229596.76 | 3153945.11 | 30.2458 | -96.6783 | 345.01
15722 | 92.4 | 333.5 | 10343.14 | 5960.13 | -1615.2 | 6085.06 | 0.38 | 0.21 | 0.32 | 56.28 | 94 | 10011.14 | 229680.71 | 3153902.98 | 30.2461 | -96.6784 | 344.84
15817 | 93 | 332 | 10338.67 | 6044.49 | -1658.65 | 6179.87 | 1.7 | 0.63 | -1.58 | -68.14 | 95 | 10006.66 | 229765.07 | 3153859.53 | 30.2463 | -96.6785 | 344.66
15912 | 94.2 | 331.3 | 10332.7 | 6127.93 | -1703.67 | 6274.52 | 1.46 | 1.26 | -0.74 | -30.19 | 95 | 10000.7 | 229848.51 | 3153814.51 | 30.2465 | -96.6787 | 344.46
16006 | 93.1 | 331.9 | 10326.72 | 6210.44 | -1748.28 | 6368.15 | 1.33 | -1.17 | 0.64 | 151.42 | 94 | 9994.72 | 229931.02 | 3153769.9 | 30.2468 | -96.6788 | 344.28
16100 | 90.6 | 332.7 | 10323.68 | 6293.62 | -1791.95 | 6461.99 | 2.79 | -2.66 | 0.85 | 162.25 | 94 | 9991.68 | 230014.2 | 3153726.23 | 30.247 | -96.6789 | 344.11
16195 | 90.2 | 333.4 | 10323.02 | 6378.3 | -1835.01 | 6556.93 | 0.85 | -0.42 | 0.74 | 119.74 | 95 | 9991.02 | 230098.88 | 3153683.17 | 30.2472 | -96.6791 | 343.95
16291 | 92.2 | 334.7 | 10321.01 | 6464.6 | -1877 | 6652.89 | 2.48 | 2.08 | 1.35 | 33.01 | 96 | 9989.01 | 230185.18 | 3153641.18 | 30.2475 | -96.6792 | 343.81
16385 | 92.8 | 341.4 | 10316.9 | 6551.65 | -1912.09 | 6746.61 | 7.15 | 0.64 | 7.13 | 84.74 | 94 | 9984.9 | 230272.23 | 3153606.09 | 30.2477 | -96.6793 | 343.73
16480 | 95 | 345.8 | 10310.44 | 6642.54 | -1938.84 | 6840.31 | 5.17 | 2.32 | 4.63 | 63.24 | 95 | 9978.44 | 230363.12 | 3153579.34 | 30.248 | -96.6794 | 343.73
16574 | 96.1 | 341.7 | 10301.34 | 6732.34 | -1965.01 | 6932.77 | 4.5 | 1.17 | -4.36 | -74.72 | 94 | 9969.34 | 230452.92 | 3153553.17 | 30.2482 | -96.6794 | 343.73
16669 | 95.1 | 336.9 | 10292.07 | 6820.76 | -1998.43 | 7027.02 | 5.14 | -1.05 | -5.05 | -101.58 | 95 | 9960.07 | 230541.34 | 3153519.75 | 30.2485 | -96.6795 | 343.67
16764 | 93.9 | 335 | 10284.61 | 6907.24 | -2037.02 | 7121.71 | 2.36 | -1.26 | -2 | -122.28 | 95 | 9952.61 | 230627.82 | 3153481.16 | 30.2487 | -96.6796 | 343.57
16860 | 91.3 | 332 | 10280.26 | 6993.04 | -2079.81 | 7217.56 | 4.13 | -2.71 | -3.12 | -130.87 | 96 | 9948.26 | 230713.62 | 3153438.37 | 30.2489 | -96.6798 | 343.44
16954 | 92 | 331.8 | 10277.55 | 7075.93 | -2124.06 | 7311.38 | 0.77 | 0.74 | -0.21 | -15.94 | 94 | 9945.55 | 230796.51 | 3153394.12 | 30.2492 | -96.6799 | 343.29
17049 | 91.6 | 331.7 | 10274.57 | 7159.57 | -2169.01 | 7406.18 | 0.43 | -0.42 | -0.11 | -165.97 | 95 | 9942.57 | 230880.15 | 3153349.17 | 30.2494 | -96.68 | 343.15
17145 | 91.8 | 334.5 | 10271.72 | 7245.14 | -2212.42 | 7502.07 | 2.92 | 0.21 | 2.92 | 85.87 | 96 | 9939.72 | 230965.72 | 3153305.76 | 30.2497 | -96.6802 | 343.02
17239 | 93.7 | 337.1 | 10267.21 | 7330.77 | -2250.9 | 7595.94 | 3.42 | 2.02 | 2.77 | 53.75 | 94 | 9935.21 | 231051.35 | 3153267.28 | 30.2499 | -96.6803 | 342.93
17333 | 95.1 | 337.3 | 10260 | 7417.17 | -2287.22 | 7689.59 | 1.5 | 1.49 | 0.21 | 8.1 | 94 | 9928 | 231137.75 | 3153230.96 | 30.2501 | -96.6804 | 342.86
17427 | 94.5 | 335.3 | 10252.13 | 7502.93 | -2324.87 | 7783.24 | 2.21 | -0.64 | -2.13 | -106.67 | 94 | 9920.13 | 231223.51 | 3153193.31 | 30.2504 | -96.6805 | 342.78
17522 | 92.2 | 333.4 | 10246.58 | 7588.41 | -2365.92 | 7878.06 | 3.14 | -2.42 | -2 | -140.43 | 95 | 9914.58 | 231308.99 | 3153152.26 | 30.2506 | -96.6806 | 342.68
17618 | 91.7 | 332.6 | 10243.31 | 7673.9 | -2409.48 | 7973.94 | 0.98 | -0.52 | -0.83 | -122.01 | 96 | 9911.31 | 231394.48 | 3153108.7 | 30.2508 | -96.6807 | 342.57
17712 | 92.1 | 332.5 | 10240.2 | 7757.27 | -2452.78 | 8067.8 | 0.44 | 0.43 | -0.11 | -14.03 | 94 | 9908.2 | 231477.85 | 3153065.4 | 30.2511 | -96.6809 | 342.45
17806 | 92.4 | 332.4 | 10236.51 | 7840.55 | -2496.23 | 8161.63 | 0.34 | 0.32 | -0.11 | -18.42 | 94 | 9904.51 | 231561.13 | 3153021.95 | 30.2513 | -96.681 | 342.34
17886 | 92.4 | 332.4 | 10233.16 | 7911.38 | -2533.26 | 8241.48 | 0 | 0 | 0 | 0 | 80 | 9901.16 | 231631.96 | 3152984.92 | 30.2515 | -96.6811 | 342.24

## 4_28_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 04/28/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 13250 |  |  | Well Cost($): |  | 13250
|  |  |  | 24hr Summary: |  | P/U BHA, Drill surface
|  |  |  | 24hr Lookahead: |  | TD surface, POOH, Run casing
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 2403 |  | 2403 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 2298 |  | 2298 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 98 |  | 98 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2200 |  | 2200 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 3.85 / 0.00 |  | 3.85 / 0.00 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: |  | 0.9 |  | 0.9 |  | SN: |  | 49754 |  | 10s Gel: |  | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 2.95 |  | 2.95 |  | Bit # |  |  |  | PH / Temp(F) | 0.0 / 100.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 745.76 / 108.89 |  | 745.76 / 108.89 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 6 |  | 6 |  | Grade In: |  | Green / RR
% Slide: |  | 4.26 |  | 4.26 |  | Grade Out:
% Rotary: |  | 95.74 |  | 95.74 |  | Make / Model: |  | Baker Hughes / SPL616
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2 - Ulterra - SPL616 - TFA 1.35 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS |  |  |  | 8 | 2 |  |  |  |  | 38.4 |  | 39.9
13 Stabilizer |  |  |  | 8.188 | 2.875 |  |  |  |  | 7.29 |  | 47.19
Pony Collar |  |  |  | 8.063 | 3.25 |  |  |  |  | 10.39 |  | 57.58
8 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 2.72 |  | 60.3
Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 29.09 |  | 89.39
Drill Collar |  |  |  | 8.125 | 3.25 |  |  |  |  | 29.92 |  | 119.31
X/O 4 1/2 IFB x 6 5/8 RegP |  |  |  | 6.75 | 3.25 |  |  |  |  | 2.61 |  | 121.92
3 Stands HWDP |  |  |  | 6.5 | 3 |  |  |  |  | 276.68 |  | 398.6
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800032 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.37 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
138 | 0.5 | 325 | 138 | 0.49 | -0.35 | 0.36 |  | 325 | 0.59 | 0.36 |  | 0 | 138
231 | 0.6 | 307.6 | 230.99 | 1.12 | -0.96 | 0.21 |  | -67.98 | 1.42 | 0.11 |  | 0 | 93
322 | 0.5 | 315.4 | 321.99 | 1.7 | -1.62 | 0.14 |  | 147.03 | 2.22 | -0.11 |  | 0 | 91
416 | 0.4 | 313.9 | 415.99 | 2.22 | -2.14 | 0.11 |  | -174.03 | 2.91 | -0.11 |  | 0 | 94
511 | 0.4 | 319.5 | 510.98 | 2.7 | -2.6 | 0.04 |  | 92.8 | 3.54 | 0 |  | 0 | 95
605 | 0.6 | 284.8 | 604.98 | 3.07 | -3.29 | 0.38 |  | -74.72 | 4.17 | 0.21 |  | 0 | 94
699 | 0.4 | 287.6 | 698.98 | 3.3 | -4.08 | 0.21 |  | 174.43 | 4.71 | -0.21 |  | 0 | 94
792 | 0.4 | 258.2 | 791.98 | 3.33 | -4.7 | 0.22 |  | -104.7 | 5 | 0 |  | 0 | 93
887 | 0.4 | 6.5 | 886.97 | 3.59 | -4.99 | 0.68 |  | 144.15 | 5.36 | 0 |  | 0 | 95
981 | 0.8 | 26.9 | 980.97 | 4.5 | -4.66 | 0.48 |  | 38.56 | 6.05 | 0.43 |  | 0 | 94
1076 | 0.6 | 33.2 | 1075.96 | 5.51 | -4.08 | 0.23 |  | 162.08 | 6.72 | -0.21 |  | 0 | 95
1170 | 1 | 35.2 | 1169.95 | 6.59 | -3.34 | 0.43 |  | 4.99 | 7.39 | 0.43 |  | 0 | 94
1264 | 1.4 | 35.9 | 1263.93 | 8.19 | -2.2 | 0.43 |  | 2.45 | 8.35 | 0.43 |  | 0 | 94
1359 | 1.6 | 41.3 | 1358.9 | 10.13 | -0.64 | 0.26 |  | 37.97 | 9.45 | 0.21 |  | 0 | 95
1453 | 2 | 41.2 | 1452.85 | 12.35 | 1.31 | 0.43 |  | -0.5 | 10.64 | 0.43 |  | -0.11 | 94
1547 | 2.4 | 34.2 | 1546.78 | 15.21 | 3.49 | 0.51 |  | -37.42 | 12.32 | 0.43 |  | -7.45 | 94
1641 | 2.5 | 30.6 | 1640.7 | 18.6 | 5.64 | 0.2 |  | -58.79 | 14.48 | 0.11 |  | -3.83 | 94
1736 | 2.5 | 33.3 | 1735.61 | 22.12 | 7.84 | 0.12 |  | 91.35 | 16.75 | 0 |  | 2.84 | 95
1830 | 2.4 | 24.3 | 1829.52 | 25.63 | 9.77 | 0.42 |  | -109.04 | 19.11 | -0.11 |  | -9.57 | 94
1924 | 2.8 | 23.6 | 1923.42 | 29.52 | 11.5 | 0.43 |  | -4.89 | 21.91 | 0.43 |  | -0.74 | 94
2018 | 2.6 | 24.2 | 2017.32 | 33.57 | 13.29 | 0.21 |  | 172.26 | 24.83 | -0.21 |  | 0.64 | 94
2111 | 2.9 | 26.4 | 2110.21 | 37.6 | 15.2 | 0.34 |  | 20.48 | 27.68 | 0.32 |  | 2.37 | 93
2206 | 3.7 | 31.9 | 2205.05 | 42.36 | 17.89 | 0.9 |  | 24.35 | 30.85 | 0.84 |  | 5.79 | 95
2299 | 4.4 | 33.6 | 2297.82 | 47.88 | 21.45 | 0.76 |  | 10.58 | 34.35 | 0.75 |  | 1.83 | 93
2393 | 5.5 | 38.6 | 2391.47 | 54.4 | 26.26 | 1.26 |  | 23.92 | 38.24 | 1.17 |  | 5.32 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 625.78 | 9.39 | 91.33 | 223 | 795.75 | 1814.44 | 1535.28 | 204 | 73.89 | 73.89 | 73.89 | 5830 | 1200
Run | 625.78 | 9.39 | 91.33 | 223 | 795.75 | 1814.44 | 1535.28 | 204 | 73.89 | 73.89 | 73.89 | 5830 | 1200
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Mob/DeMob |  |  |  |  | 04/28/2020 |  | 1 |  | 6000 |  | 1 | 6000
Directional & MWD / Gamma Services |  |  |  |  | 04/28/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 04/28/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 13250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
04/28/2020 | 00:00 | 17:30 | 17.5 | 105 | 105 | 0 | SUR |  | 24B | Standby
04/28/2020 | 17:30 | 18:00 | 0.5 | 105 | 105 | 0 | SUR | 1: BHA #1 (Surface) | 6O | Pick up BHA #1
04/28/2020 | 18:00 | 18:02 | 0.03 | 105 | 214 | 109 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/108.00 t/214.00, w/WOB 8,Flow 498, RPM 40, Press 520, Tq 2800, ROP 3180.00
04/28/2020 | 18:02 | 18:04 | 0.03 | 214 | 214 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 18:04 | 18:14 | 0.17 | 214 | 307 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/214.00 t/307.00, w/WOB 8.00,Flow 581, RPM 60, Press 675, Tq 2800.00, ROP 558.00
04/28/2020 | 18:14 | 18:20 | 0.1 | 307 | 307 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 18:20 | 18:34 | 0.23 | 307 | 398 | 91 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/307.00 t/398.00, w/WOB 8.00,Flow 498.00, RPM 40.00, Press 675, Tq 2800.00, ROP 390.00
04/28/2020 | 18:34 | 18:55 | 0.35 | 398 | 398 | 0 | SUR | 1: BHA #1 (Surface) | 8P | Rig service
04/28/2020 | 18:55 | 19:00 | 0.08 | 398 | 398 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 19:00 | 19:09 | 0.15 | 398 | 492 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/398.00 t/492.00, w/WOB 8.00,Flow 680.00, RPM 80.00, Press 1650.00, Tq 3500.00, ROP 626.67
04/28/2020 | 19:09 | 19:14 | 0.08 | 492 | 492 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 19:14 | 19:18 | 0.07 | 492 | 587 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/492.00 t/587.00, w/WOB 8.00,Flow 819.00, RPM 80.00, Press 1650.00, Tq 3500.00, ROP 1425.00
04/28/2020 | 19:18 | 19:23 | 0.08 | 587 | 587 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 19:23 | 19:27 | 0.07 | 587 | 681 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/587.00 t/681.00, w/WOB 8.00,Flow 819.00, RPM 80.00, Press 1650.00, Tq 3500.00, ROP 1410.00
04/28/2020 | 19:27 | 19:31 | 0.07 | 681 | 681 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 19:31 | 19:37 | 0.1 | 681 | 775 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/681.00 t/775.00, w/WOB 8.00,Flow 819.00, RPM 80.00, Press 1650.00, Tq 3500.00, ROP 940.00
04/28/2020 | 19:37 | 19:41 | 0.07 | 775 | 775 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 19:41 | 19:47 | 0.1 | 775 | 868 | 93 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/775.00 t/868.00, w/WOB 8.00,Flow 819.00, RPM 80.00, Press 1650.00, Tq 3500.00, ROP 930.00
04/28/2020 | 19:47 | 19:52 | 0.08 | 868 | 868 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 19:52 | 19:56 | 0.07 | 868 | 878 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/868.00 t/878.00, w/WOB 8.00,Flow 819.00, RPM 80.00, Press 1650.00, Tq 3500.00, ROP 150.00
04/28/2020 | 19:56 | 20:01 | 0.08 | 878 | 890 | 12 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/878.00 t/890.00, TF 40.00, w/WOB 8.00,Flow 819.00, Press 1650.00, Tq 3500.00, ROP 144.00
04/28/2020 | 20:01 | 20:06 | 0.08 | 890 | 963 | 73 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/890.00 t/963.00, w/WOB 8.00,Flow 819.00, RPM 100, Press 1650.00, Tq 3500.00, ROP 876.00
04/28/2020 | 20:06 | 20:11 | 0.08 | 963 | 963 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 20:11 | 20:17 | 0.1 | 963 | 1057 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/963.00 t/1057.00, w/WOB 8.00,Flow 819.00, RPM 100, Press 1650.00, Tq 3500.00, ROP 940.00
04/28/2020 | 20:17 | 20:22 | 0.08 | 1057 | 1057 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 20:22 | 20:26 | 0.07 | 1057 | 1152 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1057.00 t/1152.00, w/WOB 10,Flow 819.00, RPM 100.00, Press 1650.00, Tq 3500.00, ROP 1425.00
04/28/2020 | 20:26 | 20:30 | 0.07 | 1152 | 1152 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 20:30 | 20:34 | 0.07 | 1152 | 1167 | 15 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1152.00 t/1167.00, w/WOB 10,Flow 819.00, RPM 100.00, Press 1650.00, Tq 3500.00, ROP 225.00
04/28/2020 | 20:34 | 20:40 | 0.1 | 1167 | 1178 | 11 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1167.00 t/1178.00, TF , w/WOB 10,Flow 819.00, Press 1650.00, Tq 3500.00, ROP 110.00
04/28/2020 | 20:40 | 20:45 | 0.08 | 1178 | 1246 | 68 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1178.00 t/1246.00, w/WOB 10,Flow 819.00, RPM 100.00, Press 1650.00, Tq 3500.00, ROP 816.00
04/28/2020 | 20:45 | 20:49 | 0.07 | 1246 | 1246 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 20:49 | 20:54 | 0.08 | 1246 | 1340 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1246.00 t/1340.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100, Tq 5500, ROP 1128.00
04/28/2020 | 20:54 | 21:00 | 0.1 | 1340 | 1340 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 21:00 | 21:04 | 0.07 | 1340 | 1435 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1340.00 t/1435.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100, Tq 5500, ROP 1425.00
04/28/2020 | 21:04 | 21:09 | 0.08 | 1435 | 1435 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 21:09 | 21:11 | 0.03 | 1435 | 1445 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1435.00 t/1445.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100, Tq 5500, ROP 300.00
04/28/2020 | 21:11 | 21:18 | 0.12 | 1445 | 1460 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/1445.00 t/1460.00, TF , w/WOB 10.00,Flow 819.00, Press 2100, Tq 5500, ROP 128.57
04/28/2020 | 21:18 | 21:23 | 0.08 | 1460 | 1529 | 69 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1460.00 t/1529.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100, Tq 5500, ROP 828.00
04/28/2020 | 21:23 | 21:25 | 0.03 | 1529 | 1529 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 21:25 | 21:31 | 0.1 | 1529 | 1623 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1529.00 t/1623.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100, Tq 5500, ROP 940.00
04/28/2020 | 21:31 | 21:34 | 0.05 | 1623 | 1623 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 21:34 | 21:43 | 0.15 | 1623 | 1717 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1623.00 t/1717.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100, Tq 5500, ROP 626.67
04/28/2020 | 21:43 | 21:48 | 0.08 | 1717 | 1717 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 21:48 | 21:53 | 0.08 | 1717 | 1812 | 95 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1717.00 t/1812.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 8000.00, ROP 1140.00
04/28/2020 | 21:53 | 21:57 | 0.07 | 1812 | 1812 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 21:57 | 22:02 | 0.08 | 1812 | 1906 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1812.00 t/1906.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 8000.00, ROP 1128.00
04/28/2020 | 22:02 | 22:06 | 0.07 | 1906 | 1906 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 22:06 | 22:12 | 0.1 | 1906 | 2000 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/1906.00 t/2000.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 8000.00, ROP 940.00
04/28/2020 | 22:12 | 22:19 | 0.12 | 2000 | 2000 | 0 | SUR | 1: BHA #1 (Surface) | 24A | Glean gumbo
04/28/2020 | 22:19 | 22:24 | 0.08 | 2000 | 2000 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 22:24 | 22:43 | 0.32 | 2000 | 2094 | 94 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2000.00 t/2094.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 8000.00, ROP 296.84
04/28/2020 | 22:43 | 22:45 | 0.03 | 2094 | 2094 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 22:45 | 22:48 | 0.05 | 2094 | 2104 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2094.00 t/2104.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 8000.00, ROP 200.00
04/28/2020 | 22:48 | 22:55 | 0.12 | 2104 | 2114 | 10 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2104.00 t/2114.00, TF , w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 8000.00, ROP 85.71
04/28/2020 | 22:55 | 23:02 | 0.12 | 2114 | 2187 | 73 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2114.00 t/2187.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 8000.00, ROP 625.71
04/28/2020 | 23:02 | 23:05 | 0.05 | 2187 | 2187 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 23:05 | 23:07 | 0.03 | 2187 | 2197 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2187.00 t/2197.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000, ROP 300.00
04/28/2020 | 23:07 | 23:18 | 0.18 | 2197 | 2212 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2197.00 t/2212.00, TF , w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 10000, ROP 81.82
04/28/2020 | 23:18 | 23:21 | 0.05 | 2212 | 2282 | 70 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2212.00 t/2282.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000, ROP 1400.00
04/28/2020 | 23:21 | 23:25 | 0.07 | 2282 | 2282 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 23:25 | 23:28 | 0.05 | 2282 | 2292 | 10 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2282.00 t/2292.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000, ROP 200.00
04/28/2020 | 23:28 | 23:36 | 0.13 | 2292 | 2307 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2292.00 t/2307.00, TF , w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 10000, ROP 112.50
04/28/2020 | 23:36 | 23:44 | 0.13 | 2307 | 2375 | 68 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2307.00 t/2375.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000, ROP 510.00
04/28/2020 | 23:44 | 23:48 | 0.07 | 2375 | 2375 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/28/2020 | 23:48 | 23:50 | 0.03 | 2375 | 2383 | 8 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2375.00 t/2383.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000.00, ROP 240.00
04/28/2020 | 23:50 | 24:00 | 0.17 | 2383 | 2403 | 20 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2383.00 t/2403.00, TF , w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 10000.00, ROP 120.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 4_29_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 04/29/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 20500
|  |  |  | 24hr Summary: |  | Drill surface, POOH, L/D directional, Run casing
|  |  |  | 24hr Lookahead: |  | L/D directional tools, Run casing, cemnt same
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2403 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV: | 2
End Depth (Usft): |  | 3005 |  | 3005 |  | OD (in): |  |  |  | 300: | 3 | YP: | 1
Total Drilled (Usft): |  | 602 |  | 2900 |  | Weight (ft/lbs): |  |  |  | 200: | 2 | Viscosity: | 34
Slide Drilled (Usft): |  | 106 |  | 204 | [5 empty] | 100: | 1 | Chlorides: | 400
Rotary Drilled (Usft): |  | 496 |  | 2696 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.25 / 6.40
Drlg/Circ Hrs: |  | 2.57 / 1.17 |  | 6.42 / 1.17 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 1.33 |  | 2.23 |  | SN: |  | 49754 |  | 10s Gel: | 1 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 1.23 |  | 4.18 |  | Bit # |  |  |  | PH / Temp(F) | 0.1 / 100.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 402.16 / 79.50 |  | 644.46 / 91.34 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 7.5 |  | 13.5 |  | Grade In: |  | Green / RR
% Slide: |  | 17.61 |  | 7.03 |  | Grade Out:
% Rotary: |  | 82.39 |  | 92.97 |  | Make / Model: |  | Baker Hughes / SPL616
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2 - Ulterra - SPL616 - TFA 1.35 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS |  |  |  | 8 | 2 |  |  |  |  | 38.4 |  | 39.9
13 Stabilizer |  |  |  | 8.188 | 2.875 |  |  |  |  | 7.29 |  | 47.19
Pony Collar |  |  |  | 8.063 | 3.25 |  |  |  |  | 10.39 |  | 57.58
8 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 2.72 |  | 60.3
Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 29.09 |  | 89.39
Drill Collar |  |  |  | 8.125 | 3.25 |  |  |  |  | 29.92 |  | 119.31
X/O 4 1/2 IFB x 6 5/8 RegP |  |  |  | 6.75 | 3.25 |  |  |  |  | 2.61 |  | 121.92
3 Stands HWDP |  |  |  | 6.5 | 3 |  |  |  |  | 276.68 |  | 398.6
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800032 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.37 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2487 | 6.7 | 39.3 | 2484.94 | 62.17 | 32.54 | 1.28 |  | 3.9 | 42.63 | 1.28 |  | 0.74 | 94
2581 | 7.9 | 39.5 | 2578.17 | 71.39 | 40.12 | 1.28 |  | 1.31 | 47.79 | 1.28 |  | 0.21 | 94
2675 | 8.7 | 36.8 | 2671.19 | 82.07 | 48.49 | 0.95 |  | -27.32 | 53.94 | 0.85 |  | -2.87 | 94
2769 | 10.3 | 36.4 | 2763.9 | 94.53 | 57.74 | 1.7 |  | -2.56 | 61.34 | 1.7 |  | -0.43 | 94
2929 | 11.3 | 36.1 | 2921.06 | 118.71 | 75.46 | 0.63 |  | -3.36 | 75.78 | 0.62 |  | -0.19 | 160
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 236.08 | 10 | 100 | 223 | 739.93 | 1960.71 | 1532.14 | 204 | 102.5 | 100 | 95 | 10000 | 1200
Run | 453.83 | 9.58 | 93.5 | 223 | 781.62 | 1864.81 | 1538.85 | 204 | 82.02 | 81.35 | 80 | 6872.5 | 1200
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 04/29/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 04/29/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
04/29/2020 | 00:00 | 00:10 | 0.17 | 2403 | 2469 | 66 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2403.00 t/2469.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000.00, ROP 396.00
04/29/2020 | 00:10 | 00:12 | 0.03 | 2469 | 2469 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 00:12 | 00:16 | 0.07 | 2469 | 2480 | 11 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2469.00 t/2480.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000.00, ROP 165.00
04/29/2020 | 00:16 | 00:30 | 0.23 | 2480 | 2503 | 23 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2480.00 t/2503.00, TF , w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 10000.00, ROP 98.57
04/29/2020 | 00:30 | 00:38 | 0.13 | 2503 | 2563 | 60 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2503.00 t/2563.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000.00, ROP 450.00
04/29/2020 | 00:38 | 00:42 | 0.07 | 2563 | 2563 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 00:42 | 00:45 | 0.05 | 2563 | 2568 | 5 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2563.00 t/2568.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000.00, ROP 100.00
04/29/2020 | 00:45 | 00:54 | 0.15 | 2568 | 2578 | 10 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2568.00 t/2578.00, TF , w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 10000.00, ROP 66.67
04/29/2020 | 00:54 | 01:02 | 0.13 | 2578 | 2657 | 79 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2578.00 t/2657.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2100.00, Tq 10000.00, ROP 592.50
04/29/2020 | 01:02 | 01:06 | 0.07 | 2657 | 2657 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 01:06 | 01:23 | 0.28 | 2657 | 2685 | 28 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2657.00 t/2685.00, TF 0.00, w/WOB 10.00,Flow 819.00, Press 2100.00, Tq 10000.00, ROP 98.82
04/29/2020 | 01:23 | 01:28 | 0.08 | 2685 | 2751 | 66 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2685.00 t/2751.00, w/WOB 10.00,Flow 819.00, RPM 100.00, Press 2450, Tq 10000.00, ROP 792.00
04/29/2020 | 01:28 | 01:32 | 0.07 | 2751 | 2751 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 01:32 | 01:52 | 0.33 | 2751 | 2781 | 30 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2751.00 t/2781.00, TF , w/WOB 10.00,Flow 819.00, Press 2450, Tq 10000.00, ROP 90.00
04/29/2020 | 01:52 | 01:58 | 0.1 | 2781 | 2845 | 64 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2781.00 t/2845.00, w/WOB 10.00,Flow 819.00, RPM 100, Press 2450, Tq 10000.00, ROP 640.00
04/29/2020 | 01:58 | 02:02 | 0.07 | 2845 | 2845 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 02:02 | 02:22 | 0.33 | 2845 | 2860 | 15 | SUR | 1: BHA #1 (Surface) | 2J | Slide Drill f/2845.00 t/2860.00, TF , w/WOB 10.00,Flow 450, Press 1100, Tq 10000.00, ROP 45.00
04/29/2020 | 02:22 | 02:37 | 0.25 | 2860 | 2939 | 79 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2860.00 t/2939.00, w/WOB 10.00,Flow 450, RPM 100, Press 1100, Tq 10000.00, ROP 316.00
04/29/2020 | 02:37 | 02:40 | 0.05 | 2939 | 2939 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 02:40 | 02:55 | 0.25 | 2939 | 3005 | 66 | SUR | 1: BHA #1 (Surface) | 2K | Rotary Drill f/2939.00 t/3005.00, w/WOB 10.00,Flow 450.00, RPM 100.00, Press 1100.00, Tq 10000.00, ROP 264.00
04/29/2020 | 02:55 | 03:00 | 0.08 | 3005 | 3005 | 0 | SUR | 1: BHA #1 (Surface) | 10D | Survey & Connection
04/29/2020 | 03:00 | 04:10 | 1.17 | 3005 | 3005 | 0 | SUR | 1: BHA #1 (Surface) | 5A | Circulate
04/29/2020 | 04:10 | 06:50 | 2.67 | 3005 | 3005 | 0 | SUR | 1: BHA #1 (Surface) | 6B | Pull out of hole to lay down BHA #1 and run surface casing
04/29/2020 | 06:50 | 07:30 | 0.67 | 3005 | 3005 | 0 | SUR | 1: BHA #1 (Surface) | 6P | Lay down BHA #1
04/29/2020 | 07:30 | 24:00 | 16.5 | 3005 | 3005 | 0 | SUR |  | 24B | Standby for surface casing opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 4_30_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 04/30/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 27750
|  |  |  | 24hr Summary: |  | Nipple up BOPS, P/U BHA
|  |  |  | 24hr Lookahead: |  | TIH, Drill out cement, FIT, drill ahead
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3005 |  | 3005 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 26 | PV: | 10
End Depth (Usft): |  | 3005 |  | 3005 |  | OD (in): |  |  |  | 300: | 16 | YP: | 6
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 9 | Chlorides: | 51000
Rotary Drilled (Usft): | [9 empty] | 6: | 4 | % Sand/Solids: | 0.25 / 11.00
Drlg/Circ Hrs: |  | 0.00 / 0.17 |  | 0.00 / 0.17 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 47857 |  | 10s Gel: | 3 | Weight (ppg): | 9.5
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) | 1.5 / 105.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.353
BRT Hrs: |  | 2.75 |  | 2.75 |  | Grade In: |  | Green
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.35 |  |  |  | 9.875 | 2 |  |  |  |  | 1.35 |  | 1.35
7 3/4- 7/8 5.9 Stg 2.12? True Slick |  |  |  | 8 | 2 |  |  |  |  | 37.48 |  | 38.83
Pony Collar |  |  |  | 8.063 | 3.25 |  |  |  |  | 10.39 |  | 49.22
8 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 2.72 |  | 51.94
Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 29.09 |  | 81.03
Drill Collar |  |  |  | 8.125 | 3.25 |  |  |  |  | 29.92 |  | 110.95
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.813 | 2.938 |  |  |  |  | 3.7 |  | 114.65
2 Stands 6 1/2 DCs |  |  |  | 6.563 | 2.438 |  |  |  |  | 186.61 |  | 301.26
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.29 |  | 303.55
3 Stands HWDP |  |  |  | 6.5 | 3 |  |  |  |  | 276.68 |  | 580.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.87 |  | 2.12 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 10 | 100 | 223 | 739.93 | 1960.71 | 1532.14 | 204 | 102.5 | 100 | 95 | 10000 | 1200
Run | 0 | 9.58 | 93.5 | 223 | 781.62 | 1864.81 | 1538.85 | 204 | 82.02 | 81.35 | 80 | 6872.5 | 1200
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 04/30/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 04/30/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
04/30/2020 | 00:00 | 20:00 | 20 | 3005 | 3005 | 0 | INT |  | 24B | Attended standby for Nipple up
04/30/2020 | 20:00 | 21:15 | 1.25 | 3005 | 3005 | 0 | INT | 2: BHA #2 (Intermediate) | 6O | P/U BHA
04/30/2020 | 21:15 | 21:25 | 0.17 | 3005 | 3005 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Shallow test MWD
04/30/2020 | 21:25 | 24:00 | 2.58 | 3005 | 3005 | 0 | INT | 2: BHA #2 (Intermediate) | 6L | P/U Drill collars
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_1_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 05/01/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 35000
|  |  |  | 24hr Summary: |  | Drill intermediate
|  |  |  | 24hr Lookahead: |  | Drill ahead in intermediate
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3005 |  | 3005 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 36 | PV: | 14
End Depth (Usft): |  | 7732 |  | 7732 |  | OD (in): |  |  |  | 300: | 24 | YP: | 10
Total Drilled (Usft): |  | 4727 |  | 4727 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 52
Slide Drilled (Usft): |  | 231 |  | 231 | [5 empty] | 100: | 13 | Chlorides: | 56000
Rotary Drilled (Usft): |  | 4496 |  | 4496 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.25 / 11.00
Drlg/Circ Hrs: |  | 15.52 / 1.02 |  | 15.52 / 1.18 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water:
Slide Drilling Hrs: |  | 5.95 |  | 5.95 |  | SN: |  | 47857 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 9.57 |  | 9.57 |  | Bit # |  | 2 |  | PH / Temp(F) | 1.5 / 190.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 469.97 / 38.82 |  | 469.97 / 38.82 |  | OD (in) / TFA: |  | 9.875 / 1.353
BRT Hrs: |  | 24 |  | 26.75 |  | Grade In: |  | Green
% Slide: |  | 4.89 |  | 4.89 |  | Grade Out:
% Rotary: |  | 95.11 |  | 95.11 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.35 |  |  |  | 9.875 | 2 |  |  |  |  | 1.35 |  | 1.35
7 3/4- 7/8 5.9 Stg 2.12? True Slick |  |  |  | 8 | 2 |  |  |  |  | 37.48 |  | 38.83
Pony Collar |  |  |  | 8.063 | 3.25 |  |  |  |  | 10.39 |  | 49.22
8 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 2.72 |  | 51.94
Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 29.09 |  | 81.03
Drill Collar |  |  |  | 8.125 | 3.25 |  |  |  |  | 29.92 |  | 110.95
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.813 | 2.938 |  |  |  |  | 3.7 |  | 114.65
2 Stands 6 1/2 DCs |  |  |  | 6.563 | 2.438 |  |  |  |  | 186.61 |  | 301.26
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.29 |  | 303.55
3 Stands HWDP |  |  |  | 6.5 | 3 |  |  |  |  | 276.68 |  | 580.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.87 |  | 2.12 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3050 | 10.9 | 35.4 | 3039.8 | 137.61 | 89.08 | 0.35 |  | -161.72 | 87.17 | -0.33 |  | -0.58 | 121
3144 | 10.6 | 33.2 | 3132.15 | 152.09 | 98.96 | 0.54 |  | -127.25 | 96.13 | -0.32 |  | -2.34 | 94
3239 | 12.3 | 31.8 | 3225.25 | 168 | 109.08 | 1.81 |  | -9.97 | 106.29 | 1.79 |  | -1.47 | 95
3333 | 12.8 | 31.5 | 3317.01 | 185.39 | 119.79 | 0.54 |  | -7.57 | 117.53 | 0.53 |  | -0.32 | 94
3427 | 13.1 | 30.9 | 3408.62 | 203.41 | 130.7 | 0.35 |  | -24.43 | 129.26 | 0.32 |  | -0.64 | 94
3521 | 13.2 | 29.4 | 3500.15 | 221.9 | 141.44 | 0.38 |  | -74.4 | 141.49 | 0.11 |  | -1.6 | 94
3615 | 13.1 | 28.2 | 3591.69 | 240.64 | 151.75 | 0.31 |  | -110.7 | 154.13 | -0.11 |  | -1.28 | 94
3708 | 12.8 | 27.4 | 3682.32 | 259.08 | 161.47 | 0.38 |  | -149.53 | 166.74 | -0.32 |  | -0.86 | 93
3801 | 12.8 | 26.4 | 3773.01 | 277.45 | 170.79 | 0.24 |  | -90.49 | 179.47 | 0 |  | -1.08 | 93
3895 | 12.6 | 26.2 | 3864.71 | 295.98 | 179.94 | 0.22 |  | -167.7 | 192.4 | -0.21 |  | -0.21 | 94
3989 | 12.7 | 25.4 | 3956.43 | 314.51 | 188.9 | 0.21 |  | -60.67 | 205.42 | 0.11 |  | -0.85 | 94
4083 | 12.6 | 24.4 | 4048.15 | 333.18 | 197.57 | 0.26 |  | -115.03 | 218.69 | -0.11 |  | -1.06 | 94
4178 | 12.7 | 30.1 | 4140.84 | 351.65 | 207.09 | 1.32 |  | 88.2 | 231.42 | 0.11 |  | 6 | 95
4271 | 12.7 | 33.4 | 4231.57 | 369.03 | 217.84 | 0.78 |  | 91.61 | 242.64 | 0 |  | 3.55 | 93
4365 | 12.4 | 32.3 | 4323.32 | 386.19 | 228.92 | 0.41 |  | -141.99 | 253.52 | -0.32 |  | -1.17 | 94
4458 | 12.4 | 30.1 | 4414.16 | 403.27 | 239.27 | 0.51 |  | -91.07 | 264.64 | 0 |  | -2.37 | 93
4553 | 12.2 | 28.7 | 4506.97 | 420.9 | 249.2 | 0.38 |  | -124.53 | 276.43 | -0.21 |  | -1.47 | 95
4646 | 12.3 | 27.4 | 4597.86 | 438.31 | 258.48 | 0.32 |  | -70.71 | 288.3 | 0.11 |  | -1.4 | 93
4739 | 12.4 | 27.6 | 4688.71 | 455.95 | 267.67 | 0.12 |  | 23.26 | 300.42 | 0.11 |  | 0.22 | 93
4834 | 12 | 26.1 | 4781.56 | 473.86 | 276.74 | 0.54 |  | -142.34 | 312.83 | -0.42 |  | -1.58 | 95
4928 | 11.6 | 25.7 | 4873.57 | 491.15 | 285.13 | 0.43 |  | -168.64 | 324.96 | -0.43 |  | -0.43 | 94
5022 | 11.3 | 23.5 | 4965.7 | 508.11 | 292.9 | 0.56 |  | -125.56 | 337.06 | -0.32 |  | -2.34 | 94
5117 | 11.9 | 29.8 | 5058.77 | 525.15 | 301.48 | 1.47 |  | 67.76 | 348.88 | 0.63 |  | 6.63 | 95
5211 | 11.3 | 27.1 | 5150.85 | 541.76 | 310.5 | 0.86 |  | -139.18 | 360.14 | -0.64 |  | -2.87 | 94
5305 | 12.1 | 29.7 | 5242.89 | 558.52 | 319.57 | 1.02 |  | 34.66 | 371.5 | 0.85 |  | 2.77 | 94
5398 | 11.7 | 30 | 5333.89 | 575.15 | 329.12 | 0.44 |  | 171.36 | 382.55 | -0.43 |  | 0.32 | 93
5492 | 11.6 | 29.3 | 5425.96 | 591.64 | 338.51 | 0.18 |  | -125.62 | 393.54 | -0.11 |  | -0.74 | 94
5586 | 11.7 | 27.8 | 5518.02 | 608.32 | 347.58 | 0.34 |  | -72.47 | 404.83 | 0.11 |  | -1.6 | 94
5682 | 11.6 | 33.9 | 5612.05 | 624.94 | 357.5 | 1.29 |  | 97.62 | 415.71 | -0.1 |  | 6.35 | 96
5776 | 11.9 | 37.1 | 5704.08 | 640.51 | 368.62 | 0.76 |  | 66.85 | 425.14 | 0.32 |  | 3.4 | 94
5870 | 11.3 | 33.5 | 5796.16 | 655.92 | 379.55 | 1 |  | -131.41 | 434.5 | -0.64 |  | -3.83 | 94
5964 | 10.9 | 32.3 | 5888.4 | 671.12 | 389.38 | 0.49 |  | -150.58 | 444.12 | -0.43 |  | -1.28 | 94
6058 | 11.8 | 33.5 | 5980.56 | 686.64 | 399.43 | 0.99 |  | 15.29 | 453.96 | 0.96 |  | 1.28 | 94
6152 | 11.5 | 30.3 | 6072.63 | 702.75 | 409.47 | 0.76 |  | -116.47 | 464.32 | -0.32 |  | -3.4 | 94
6245 | 10.6 | 27.7 | 6163.9 | 718.33 | 418.12 | 1.11 |  | -152.3 | 474.8 | -0.97 |  | -2.8 | 93
6339 | 10.4 | 31.6 | 6256.33 | 733.21 | 426.58 | 0.79 |  | 107.63 | 484.72 | -0.21 |  | 4.15 | 94
6434 | 13.2 | 34.3 | 6349.31 | 749.47 | 437.19 | 3 |  | 12.48 | 494.99 | 2.95 |  | 2.84 | 95
6527 | 14.9 | 33.5 | 6439.53 | 768.22 | 449.78 | 1.84 |  | -6.91 | 506.67 | 1.83 |  | -0.86 | 93
6621 | 14.2 | 31.8 | 6530.51 | 788.09 | 462.52 | 0.87 |  | -149.43 | 519.31 | -0.74 |  | -1.81 | 94
6716 | 13.7 | 31.1 | 6622.71 | 807.63 | 474.47 | 0.56 |  | -161.69 | 531.98 | -0.53 |  | -0.74 | 95
6809 | 13.5 | 30.4 | 6713.1 | 826.42 | 485.66 | 0.28 |  | -140.89 | 544.3 | -0.22 |  | -0.75 | 93
6904 | 12.8 | 27.8 | 6805.61 | 845.3 | 496.17 | 0.96 |  | -141.06 | 556.97 | -0.74 |  | -2.74 | 95
6998 | 12 | 25.6 | 6897.42 | 863.32 | 505.25 | 0.99 |  | -150.51 | 569.48 | -0.85 |  | -2.34 | 94
7092 | 11.2 | 22.4 | 6989.5 | 880.57 | 512.95 | 1.09 |  | -142.75 | 581.87 | -0.85 |  | -3.4 | 94
7185 | 13.1 | 20.8 | 7080.41 | 898.78 | 520.14 | 2.07 |  | -10.83 | 595.34 | 2.04 |  | -1.72 | 93
7280 | 12.8 | 18.6 | 7173 | 918.82 | 527.32 | 0.61 |  | -122.39 | 610.48 | -0.32 |  | -2.32 | 95
7374 | 12 | 26.8 | 7264.81 | 937.41 | 535.05 | 2.06 |  | 118.4 | 624.08 | -0.85 |  | 8.72 | 94
7468 | 10.8 | 23 | 7356.95 | 954.24 | 542.89 | 1.51 |  | -149.81 | 636.02 | -1.28 |  | -4.04 | 94
7562 | 10.4 | 17.5 | 7449.35 | 970.44 | 548.89 | 1.16 |  | -114.26 | 648.18 | -0.43 |  | -5.85 | 94
7656 | 10.7 | 18.6 | 7541.76 | 986.8 | 554.22 | 0.38 |  | 34.42 | 660.76 | 0.32 |  | 1.17 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 296.36 | 30.76 | 78.52 | 200 | 733.24 | 3329.05 | 2808.78 | 204 | 164.53 | 155.41 | 147.09 | 11114.75 | 3000
Run | 296.36 | 30.76 | 78.52 | 200 | 733.24 | 3329.05 | 2808.78 | 204 | 164.53 | 155.41 | 147.09 | 11114.75 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 05/01/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 05/01/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/01/2020 | 00:00 | 01:40 | 1.67 | 3005 | 3005 | 0 | INT | 2: BHA #2 (Intermediate) | 6A | TIH
05/01/2020 | 01:40 | 02:25 | 0.75 | 3005 | 3005 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | Install rotating head
05/01/2020 | 02:25 | 02:50 | 0.42 | 3005 | 3005 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Drill out
05/01/2020 | 02:50 | 02:55 | 0.08 | 3005 | 3015 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3005.00 t/3015.00, w/WOB 10,Flow 420, RPM 50, Press 750, Tq 6, ROP 120.00
05/01/2020 | 02:55 | 03:16 | 0.35 | 3015 | 3015 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate
05/01/2020 | 03:16 | 03:30 | 0.23 | 3015 | 3015 | 0 | INT | 2: BHA #2 (Intermediate) | 15D | FIT
05/01/2020 | 03:30 | 03:45 | 0.25 | 3015 | 3015 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate thru gasbuster
05/01/2020 | 03:45 | 04:00 | 0.25 | 3015 | 3120 | 105 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3015.00 t/3120.00, w/WOB 10.00,Flow 500.00, RPM 60.00, Press 1000.00, Tq 6000.00, ROP 420.00
05/01/2020 | 04:00 | 04:05 | 0.08 | 3120 | 3120 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 04:05 | 04:11 | 0.1 | 3120 | 3214 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3120.00 t/3214.00, w/WOB 10.00,Flow 730.00, RPM 70.00, Press 3000.00, Tq 9000.00, ROP 940.00
05/01/2020 | 04:11 | 04:15 | 0.07 | 3214 | 3214 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 04:15 | 04:23 | 0.13 | 3214 | 3226 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3214.00 t/3226.00, w/WOB 18.00,Flow 730.00, RPM 75.00, Press 3000.00, Tq 9000.00, ROP 90.00
05/01/2020 | 04:23 | 04:30 | 0.12 | 3226 | 3234 | 8 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/3226.00 t/3234.00, TF -10.00, w/WOB 18.00,Flow 730.00, Press 3000.00, Tq 9000.00, ROP 68.57
05/01/2020 | 04:30 | 04:38 | 0.13 | 3234 | 3309 | 75 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3234.00 t/3309.00, w/WOB 18.00,Flow 730.00, RPM 75.00, Press 3000.00, Tq 9000.00, ROP 562.50
05/01/2020 | 04:38 | 04:43 | 0.08 | 3309 | 3309 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 04:43 | 04:51 | 0.13 | 3309 | 3403 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3309.00 t/3403.00, w/WOB 25,Flow 730.00, RPM 75.00, Press 3000.00, Tq 9000.00, ROP 705.00
05/01/2020 | 04:51 | 04:55 | 0.07 | 3403 | 3403 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 04:55 | 05:03 | 0.13 | 3403 | 3497 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3403.00 t/3497.00, w/WOB 25.00,Flow 730.00, RPM 75.00, Press 3000.00, Tq 9000.00, ROP 705.00
05/01/2020 | 05:03 | 05:08 | 0.08 | 3497 | 3497 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 05:08 | 05:18 | 0.17 | 3497 | 3591 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3497.00 t/3591.00, w/WOB 25.00,Flow 730.00, RPM 75.00, Press 3000.00, Tq 9000.00, ROP 564.00
05/01/2020 | 05:18 | 05:23 | 0.08 | 3591 | 3591 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 05:23 | 05:30 | 0.12 | 3591 | 3685 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3591.00 t/3685.00, w/WOB 25.00,Flow 730.00, RPM 75.00, Press 3000.00, Tq 9000.00, ROP 805.71
05/01/2020 | 05:30 | 05:35 | 0.08 | 3685 | 3685 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 05:35 | 05:46 | 0.18 | 3685 | 3778 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3685.00 t/3778.00, w/WOB 30,Flow 730.00, RPM 80, Press 3200, Tq 9000.00, ROP 507.27
05/01/2020 | 05:46 | 05:51 | 0.08 | 3778 | 3778 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 05:51 | 06:02 | 0.18 | 3778 | 3871 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3778.00 t/3871.00, w/WOB 30,Flow 730.00, RPM 80, Press 3200, Tq 9000.00, ROP 507.27
05/01/2020 | 06:02 | 06:07 | 0.08 | 3871 | 3871 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 06:07 | 06:15 | 0.13 | 3871 | 3965 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3871.00 t/3965.00, w/WOB 30,Flow 730.00, RPM 80, Press 3200, Tq 9000.00, ROP 705.00
05/01/2020 | 06:15 | 06:20 | 0.08 | 3965 | 3965 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 06:20 | 06:28 | 0.13 | 3965 | 4059 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/3965.00 t/4059.00, w/WOB 30,Flow 730.00, RPM 80, Press 3200, Tq 9000.00, ROP 705.00
05/01/2020 | 06:28 | 06:47 | 0.32 | 4059 | 4059 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | Troubleshoot Draworks
05/01/2020 | 06:47 | 06:52 | 0.08 | 4059 | 4059 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 06:52 | 07:02 | 0.17 | 4059 | 4153 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4059.00 t/4153.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 564.00
05/01/2020 | 07:02 | 07:08 | 0.1 | 4153 | 4153 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 07:08 | 07:10 | 0.03 | 4153 | 4175 | 22 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4153.00 t/4175.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 660.00
05/01/2020 | 07:10 | 07:20 | 0.17 | 4175 | 4187 | 12 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/4175.00 t/4187.00, TF , w/WOB 18,Flow 730.00, Press 3200.00, Tq 0, ROP 72.00
05/01/2020 | 07:20 | 07:43 | 0.38 | 4187 | 4248 | 61 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4187.00 t/4248.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 159.13
05/01/2020 | 07:43 | 07:47 | 0.07 | 4248 | 4248 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 07:47 | 07:58 | 0.18 | 4248 | 4435 | 187 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4341.00 t/4435.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 512.73
05/01/2020 | 07:58 | 08:03 | 0.08 | 4435 | 4435 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 08:03 | 08:09 | 0.1 | 4435 | 4528 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4435.00 t/4528.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 930.00
05/01/2020 | 08:09 | 08:14 | 0.08 | 4528 | 4528 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 08:14 | 08:21 | 0.12 | 4528 | 4623 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4528.00 t/4623.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 814.29
05/01/2020 | 08:21 | 08:26 | 0.08 | 4623 | 4623 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 08:26 | 08:35 | 0.15 | 4623 | 4716 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4623.00 t/4716.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 620.00
05/01/2020 | 08:35 | 08:40 | 0.08 | 4716 | 4716 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 08:40 | 08:48 | 0.13 | 4716 | 4809 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4716.00 t/4809.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 697.50
05/01/2020 | 08:48 | 08:53 | 0.08 | 4809 | 4809 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 08:53 | 09:02 | 0.15 | 4809 | 4904 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4809.00 t/4904.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 633.33
05/01/2020 | 09:02 | 09:07 | 0.08 | 4904 | 4904 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 09:07 | 09:14 | 0.12 | 4904 | 4998 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4904.00 t/4998.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 805.71
05/01/2020 | 09:14 | 09:20 | 0.1 | 4998 | 4998 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 09:20 | 09:23 | 0.05 | 4998 | 5035 | 37 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/4998.00 t/5035.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 740.00
05/01/2020 | 09:23 | 09:36 | 0.22 | 5035 | 5050 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5035.00 t/5050.00, TF , w/WOB 180,Flow 0, Press 3200.00, Tq 9000.00, ROP 69.23
05/01/2020 | 09:36 | 09:42 | 0.1 | 5050 | 5092 | 42 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5050.00 t/5092.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 420.00
05/01/2020 | 09:42 | 09:47 | 0.08 | 5092 | 5092 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 09:47 | 09:56 | 0.15 | 5092 | 5187 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5092.00 t/5187.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 633.33
05/01/2020 | 09:56 | 10:00 | 0.07 | 5187 | 5187 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 10:00 | 10:10 | 0.17 | 5187 | 5281 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5187.00 t/5281.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 564.00
05/01/2020 | 10:10 | 10:15 | 0.08 | 5281 | 5281 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 10:15 | 10:18 | 0.05 | 5281 | 5290 | 9 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5281.00 t/5290.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 180.00
05/01/2020 | 10:18 | 10:28 | 0.17 | 5290 | 5305 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5290.00 t/5305.00, TF , w/WOB 30.00,Flow 730.00, Press 3200.00, Tq 9000.00, ROP 90.00
05/01/2020 | 10:28 | 10:38 | 0.17 | 5305 | 5375 | 70 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5305.00 t/5375.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 420.00
05/01/2020 | 10:38 | 10:43 | 0.08 | 5375 | 5375 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 10:43 | 10:52 | 0.15 | 5375 | 5468 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5375.00 t/5468.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 9000.00, ROP 620.00
05/01/2020 | 10:52 | 10:57 | 0.08 | 5468 | 5468 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 10:57 | 11:04 | 0.12 | 5468 | 5562 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5468.00 t/5562.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 805.71
05/01/2020 | 11:04 | 11:10 | 0.1 | 5562 | 5562 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 11:10 | 11:17 | 0.12 | 5562 | 5656 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5562.00 t/5656.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 805.71
05/01/2020 | 11:17 | 11:22 | 0.08 | 5656 | 5656 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 11:22 | 11:25 | 0.05 | 5656 | 5670 | 14 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5656.00 t/5670.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 280.00
05/01/2020 | 11:25 | 11:37 | 0.2 | 5670 | 5690 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/5670.00 t/5690.00, TF , w/WOB 18,Flow 730.00, Press 3200.00, Tq 0, ROP 100.00
05/01/2020 | 11:37 | 11:47 | 0.17 | 5690 | 5752 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5690.00 t/5752.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 372.00
05/01/2020 | 11:47 | 11:52 | 0.08 | 5752 | 5752 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 11:52 | 12:00 | 0.13 | 5752 | 5846 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5752.00 t/5846.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 705.00
05/01/2020 | 12:00 | 12:05 | 0.08 | 5846 | 5846 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 12:05 | 12:15 | 0.17 | 5846 | 5940 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5846.00 t/5940.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 564.00
05/01/2020 | 12:15 | 12:20 | 0.08 | 5940 | 5940 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 12:20 | 12:31 | 0.18 | 5940 | 6034 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/5940.00 t/6034.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000, ROP 512.73
05/01/2020 | 12:31 | 12:37 | 0.1 | 6034 | 6034 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 12:37 | 12:40 | 0.05 | 6034 | 6045 | 11 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6034.00 t/6045.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000.00, ROP 220.00
05/01/2020 | 12:40 | 12:58 | 0.3 | 6045 | 6065 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6045.00 t/6065.00, TF 0.00, w/WOB 20.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 66.67
05/01/2020 | 12:58 | 13:09 | 0.18 | 6065 | 6128 | 63 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6065.00 t/6128.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000.00, ROP 343.64
05/01/2020 | 13:09 | 13:15 | 0.1 | 6128 | 6128 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 13:15 | 13:25 | 0.17 | 6128 | 6222 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6128.00 t/6222.00, w/WOB 30.00,Flow 730.00, RPM 80.00, Press 3200.00, Tq 12000.00, ROP 564.00
05/01/2020 | 13:25 | 13:30 | 0.08 | 6222 | 6222 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 13:30 | 13:46 | 0.27 | 6222 | 6315 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6222.00 t/6315.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3600.00, Tq 12000.00, ROP 348.75
05/01/2020 | 13:46 | 13:50 | 0.07 | 6315 | 6315 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 13:50 | 13:55 | 0.08 | 6315 | 6325 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6315.00 t/6325.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800, Tq 12000.00, ROP 120.00
05/01/2020 | 13:55 | 14:26 | 0.52 | 6325 | 6350 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6325.00 t/6350.00, TF , w/WOB 20.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 48.39
05/01/2020 | 14:26 | 14:35 | 0.15 | 6350 | 6409 | 59 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6350.00 t/6409.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800, Tq 12000.00, ROP 393.33
05/01/2020 | 14:35 | 14:40 | 0.08 | 6409 | 6409 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 14:40 | 14:45 | 0.08 | 6409 | 6415 | 6 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6409.00 t/6415.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800, Tq 12000.00, ROP 72.00
05/01/2020 | 14:45 | 15:15 | 0.5 | 6415 | 6445 | 30 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/6415.00 t/6445.00, TF , w/WOB 20.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 60.00
05/01/2020 | 15:15 | 15:21 | 0.1 | 6445 | 6504 | 59 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6445.00 t/6504.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800, Tq 12000.00, ROP 590.00
05/01/2020 | 15:21 | 15:26 | 0.08 | 6504 | 6504 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 15:26 | 15:41 | 0.25 | 6504 | 6597 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6504.00 t/6597.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000, ROP 372.00
05/01/2020 | 15:41 | 15:46 | 0.08 | 6597 | 6597 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 15:46 | 15:57 | 0.18 | 6597 | 6691 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6597.00 t/6691.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000, ROP 512.73
05/01/2020 | 15:57 | 16:02 | 0.08 | 6691 | 6691 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 16:02 | 16:11 | 0.15 | 6691 | 6753 | 62 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6691.00 t/6753.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000, ROP 413.33
05/01/2020 | 16:11 | 16:23 | 0.2 | 6753 | 6753 | 0 | INT | 2: BHA #2 (Intermediate) | 24A | Repair liner washer on #1 mud pump
05/01/2020 | 16:23 | 16:28 | 0.08 | 6753 | 6786 | 33 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6753.00 t/6786.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000, ROP 396.00
05/01/2020 | 16:28 | 16:33 | 0.08 | 6786 | 6786 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 16:33 | 16:53 | 0.33 | 6786 | 6879 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6786.00 t/6879.00, w/WOB 30.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 279.00
05/01/2020 | 16:53 | 16:58 | 0.08 | 6879 | 6879 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 16:58 | 17:11 | 0.22 | 6879 | 6974 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6879.00 t/6974.00, w/WOB 34,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 438.46
05/01/2020 | 17:11 | 17:16 | 0.08 | 6974 | 6974 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 17:16 | 17:28 | 0.2 | 6974 | 7068 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/6974.00 t/7068.00, w/WOB 34,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 470.00
05/01/2020 | 17:28 | 17:33 | 0.08 | 7068 | 7068 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 17:33 | 17:45 | 0.2 | 7068 | 7162 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7068.00 t/7162.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 470.00
05/01/2020 | 17:45 | 17:55 | 0.17 | 7162 | 7162 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 17:55 | 18:17 | 0.37 | 7162 | 7182 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7162.00 t/7182.00, TF 20.00, w/WOB 20.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 54.55
05/01/2020 | 18:17 | 18:33 | 0.27 | 7182 | 7255 | 73 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7182.00 t/7255.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 273.75
05/01/2020 | 18:33 | 18:38 | 0.08 | 7255 | 7255 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 18:38 | 18:54 | 0.27 | 7255 | 7350 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7255.00 t/7350.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 356.25
05/01/2020 | 18:54 | 19:03 | 0.15 | 7350 | 7350 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 19:03 | 19:25 | 0.37 | 7350 | 7370 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7350.00 t/7370.00, TF , w/WOB 20.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 54.55
05/01/2020 | 19:25 | 19:40 | 0.25 | 7370 | 7444 | 74 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7370.00 t/7444.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 296.00
05/01/2020 | 19:40 | 19:45 | 0.08 | 7444 | 7444 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 19:45 | 19:58 | 0.22 | 7444 | 7538 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7444.00 t/7538.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 433.85
05/01/2020 | 19:58 | 20:03 | 0.08 | 7538 | 7538 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 20:03 | 20:09 | 0.1 | 7538 | 7548 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7538.00 t/7548.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 100.00
05/01/2020 | 20:09 | 21:20 | 1.18 | 7548 | 7568 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7548.00 t/7568.00, TF 90.00, w/WOB 34.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 16.90
05/01/2020 | 21:20 | 21:39 | 0.32 | 7568 | 7632 | 64 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7568.00 t/7632.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 202.11
05/01/2020 | 21:39 | 21:48 | 0.15 | 7632 | 7632 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 21:48 | 23:20 | 1.53 | 7632 | 7652 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7632.00 t/7652.00, TF 70.00, w/WOB 34.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 13.04
05/01/2020 | 23:20 | 23:36 | 0.27 | 7652 | 7726 | 74 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7652.00 t/7726.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 277.50
05/01/2020 | 23:36 | 23:41 | 0.08 | 7726 | 7726 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/01/2020 | 23:41 | 24:00 | 0.32 | 7726 | 7732 | 6 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7726.00 t/7732.00, TF , w/WOB 34.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 18.95
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_2_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 05/02/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 42250
|  |  |  | 24hr Summary: |  | Drill Intermediate
|  |  |  | 24hr Lookahead: |  | TD Intermediate
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 7732 |  | 3005 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 36 | PV: | 14
End Depth (Usft): |  | 10276 |  | 10276 |  | OD (in): |  |  |  | 300: | 24 | YP: | 10
Total Drilled (Usft): |  | 2544 |  | 7271 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 52
Slide Drilled (Usft): |  | 418 |  | 649 | [5 empty] | 100: | 13 | Chlorides: | 56000
Rotary Drilled (Usft): |  | 2126 |  | 6622 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.25 / 11.00
Drlg/Circ Hrs: |  | 19.35 / 1.00 |  | 34.87 / 2.18 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water:
Slide Drilling Hrs: |  | 12.27 |  | 18.22 |  | SN: |  | 47857 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 7.08 |  | 16.65 |  | Bit # |  | 2 |  | PH / Temp(F) | 1.5 / 190.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 300.14 / 34.08 |  | 397.72 / 35.63 |  | OD (in) / TFA: |  | 9.875 / 1.353
BRT Hrs: |  | 24 |  | 50.75 |  | Grade In: |  | Green
% Slide: |  | 16.43 |  | 8.93 |  | Grade Out:
% Rotary: |  | 83.57 |  | 91.07 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.35 |  |  |  | 9.875 | 2 |  |  |  |  | 1.35 |  | 1.35
7 3/4- 7/8 5.9 Stg 2.12? True Slick |  |  |  | 8 | 2 |  |  |  |  | 37.48 |  | 38.83
Pony Collar |  |  |  | 8.063 | 3.25 |  |  |  |  | 10.39 |  | 49.22
8 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 2.72 |  | 51.94
Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 29.09 |  | 81.03
Drill Collar |  |  |  | 8.125 | 3.25 |  |  |  |  | 29.92 |  | 110.95
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.813 | 2.938 |  |  |  |  | 3.7 |  | 114.65
2 Stands 6 1/2 DCs |  |  |  | 6.563 | 2.438 |  |  |  |  | 186.61 |  | 301.26
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.29 |  | 303.55
3 Stands HWDP |  |  |  | 6.5 | 3 |  |  |  |  | 276.68 |  | 580.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.87 |  | 2.12 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
7750 | 9.9 | 31.4 | 7634.26 | 1001.97 | 561.22 | 2.57 |  | 115.49 | 671.56 | -0.85 |  | 13.62 | 94
7844 | 8.4 | 27.8 | 7727.06 | 1014.94 | 568.63 | 1.71 |  | -160.88 | 680.2 | -1.6 |  | -3.83 | 94
7938 | 7.1 | 20 | 7820.2 | 1026.48 | 573.82 | 1.78 |  | -144.84 | 688.46 | -1.38 |  | -8.3 | 94
8032 | 7.9 | 33.3 | 7913.41 | 1037.34 | 579.35 | 2.03 |  | 71.95 | 695.97 | 0.85 |  | 14.15 | 94
8125 | 7.2 | 35.2 | 8005.6 | 1047.44 | 586.22 | 0.8 |  | 161.31 | 702.23 | -0.75 |  | 2.04 | 93
8216 | 6 | 30.8 | 8096 | 1056.19 | 591.94 | 1.43 |  | -159.32 | 707.75 | -1.32 |  | -4.84 | 91
8310 | 6.7 | 46.5 | 8189.43 | 1064.18 | 598.44 | 1.98 |  | 75.97 | 712.26 | 0.74 |  | 16.7 | 94
8403 | 5.7 | 45.9 | 8281.88 | 1071.13 | 605.69 | 1.08 |  | -176.59 | 715.5 | -1.08 |  | -0.65 | 93
8498 | 4.9 | 42.6 | 8376.47 | 1077.4 | 611.82 | 0.9 |  | -160.78 | 718.59 | -0.84 |  | -3.47 | 95
8592 | 4.8 | 40.2 | 8470.14 | 1083.36 | 617.08 | 0.24 |  | -117.43 | 721.78 | -0.11 |  | -2.55 | 94
8687 | 5.1 | 38 | 8564.78 | 1089.72 | 622.25 | 0.37 |  | -33.42 | 725.37 | 0.32 |  | -2.32 | 95
8781 | 4.6 | 36.8 | 8658.45 | 1096.03 | 627.08 | 0.54 |  | -169.13 | 729.05 | -0.53 |  | -1.28 | 94
8875 | 5 | 22.6 | 8752.12 | 1102.83 | 630.91 | 1.33 |  | -78.56 | 733.6 | 0.43 |  | -15.11 | 94
8969 | 4.6 | 34.1 | 8845.79 | 1109.74 | 634.6 | 1.11 |  | 118.23 | 738.3 | -0.43 |  | 12.23 | 94
9064 | 4.2 | 38.6 | 8940.51 | 1115.61 | 638.9 | 0.56 |  | 141.43 | 741.81 | -0.42 |  | 4.74 | 95
9158 | 2.9 | 44.2 | 9034.33 | 1120 | 642.71 | 1.43 |  | 167.85 | 744.19 | -1.38 |  | 5.96 | 94
9252 | 2.6 | 52.5 | 9128.22 | 1123.01 | 646.06 | 0.53 |  | 131.09 | 745.49 | -0.32 |  | 8.83 | 94
9346 | 1.5 | 46.9 | 9222.16 | 1125.14 | 648.65 | 1.19 |  | -172.47 | 746.34 | -1.17 |  | -5.96 | 94
9439 | 0.3 | 331.7 | 9315.15 | 1126.19 | 649.42 | 1.56 |  | -168.48 | 746.96 | -1.29 |  | -80.86 | 93
9533 | 2.2 | 320.6 | 9409.12 | 1127.8 | 648.16 | 2.03 |  | -12.84 | 748.96 | 2.02 |  | 0 | 94
9627 | 4.3 | 327.8 | 9502.97 | 1132.18 | 645.13 | 2.27 |  | 14.61 | 754.2 | 2.23 |  | 7.66 | 94
9672 | 5.6 | 329.9 | 9547.8 | 1135.51 | 643.13 | 2.92 |  | 8.98 | 758.06 | 2.89 |  | 4.67 | 45
9721 | 5.3 | 330.1 | 9596.58 | 1139.54 | 640.81 | 0.61 |  | 176.48 | 762.7 | -0.61 |  | 0.41 | 49
9816 | 7.9 | 330.5 | 9690.94 | 1149.02 | 635.4 | 2.74 |  | 1.21 | 773.58 | 2.74 |  | 0.42 | 95
9861 | 8.2 | 332 | 9735.49 | 1154.55 | 632.37 | 0.81 |  | 35.74 | 779.86 | 0.67 |  | 3.33 | 45
9910 | 9.3 | 332 | 9783.92 | 1161.13 | 628.87 | 2.24 |  | 0 | 787.31 | 2.24 |  | 0 | 49
10004 | 11.7 | 332.4 | 9876.34 | 1176.28 | 620.89 | 2.55 |  | 1.94 | 804.42 | 2.55 |  | 0.43 | 94
10049 | 14.5 | 331.1 | 9920.17 | 1185.26 | 616.05 | 6.26 |  | -6.64 | 814.6 | 6.22 |  | -2.89 | 45
10098 | 15.6 | 330.7 | 9967.49 | 1196.38 | 609.87 | 2.25 |  | -5.59 | 827.29 | 2.24 |  | -0.82 | 49
10193 | 18.6 | 338.8 | 10058.29 | 1221.65 | 598.13 | 4.03 |  | 42.37 | 855.15 | 3.16 |  | 8.53 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 131.54 | 32.12 | 80 | 205 | 756 | 3796.15 | 3300 | 204 | 235 | 215 | 195 | 15789.47 | 3000
Run | 208.52 | 31.32 | 79.09 | 202 | 742.63 | 3521.83 | 3011.51 | 204 | 194.33 | 180.6 | 167.3 | 12909.09 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 05/02/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 05/02/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/02/2020 | 00:00 | 00:17 | 0.28 | 7732 | 7751 | 19 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/7732.00 t/7751.00, TF 90.00, w/WOB 34.00,Flow 756.00, Press 3600.00, Tq 0.00, ROP 67.06
05/02/2020 | 00:17 | 00:29 | 0.2 | 7751 | 7820 | 69 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7751.00 t/7820.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 345.00
05/02/2020 | 00:29 | 00:34 | 0.08 | 7820 | 7820 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 00:34 | 00:45 | 0.18 | 7820 | 7914 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7820.00 t/7914.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 512.73
05/02/2020 | 00:45 | 00:50 | 0.08 | 7914 | 7914 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 00:50 | 01:01 | 0.18 | 7914 | 8008 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/7914.00 t/8008.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 512.73
05/02/2020 | 01:01 | 01:06 | 0.08 | 8008 | 8008 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 01:06 | 01:12 | 0.1 | 8008 | 8013 | 5 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8008.00 t/8013.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 50.00
05/02/2020 | 01:12 | 01:45 | 0.55 | 8013 | 8042 | 29 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8013.00 t/8042.00, TF 90.00, w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 52.73
05/02/2020 | 01:45 | 02:00 | 0.25 | 8042 | 8102 | 60 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8042.00 t/8102.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 240.00
05/02/2020 | 02:00 | 02:05 | 0.08 | 8102 | 8102 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 02:05 | 02:20 | 0.25 | 8102 | 8195 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8102.00 t/8195.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 372.00
05/02/2020 | 02:20 | 02:25 | 0.08 | 8195 | 8195 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 02:25 | 02:32 | 0.12 | 8195 | 8286 | 91 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8195.00 t/8286.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 780.00
05/02/2020 | 02:32 | 02:37 | 0.08 | 8286 | 8286 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 02:37 | 02:43 | 0.1 | 8286 | 8289 | 3 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8286.00 t/8289.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 30.00
05/02/2020 | 02:43 | 03:06 | 0.38 | 8289 | 8315 | 26 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8289.00 t/8315.00, TF 90.00, w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 67.83
05/02/2020 | 03:06 | 03:19 | 0.22 | 8315 | 8380 | 65 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8315.00 t/8380.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 300.00
05/02/2020 | 03:19 | 03:24 | 0.08 | 8380 | 8380 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 03:24 | 03:36 | 0.2 | 8380 | 8473 | 93 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8380.00 t/8473.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 465.00
05/02/2020 | 03:36 | 03:41 | 0.08 | 8473 | 8473 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 03:41 | 03:51 | 0.17 | 8473 | 8568 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8473.00 t/8568.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 570.00
05/02/2020 | 03:51 | 03:56 | 0.08 | 8568 | 8568 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 03:56 | 04:05 | 0.15 | 8568 | 8662 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8568.00 t/8662.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 626.67
05/02/2020 | 04:05 | 04:07 | 0.03 | 8662 | 8662 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 04:07 | 04:23 | 0.27 | 8662 | 8757 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8662.00 t/8757.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 356.25
05/02/2020 | 04:23 | 04:27 | 0.07 | 8757 | 8757 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 04:27 | 04:38 | 0.18 | 8757 | 8851 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8757.00 t/8851.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 512.73
05/02/2020 | 04:38 | 04:43 | 0.08 | 8851 | 8851 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 04:43 | 04:53 | 0.17 | 8851 | 8945 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8851.00 t/8945.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 564.00
05/02/2020 | 04:53 | 04:55 | 0.03 | 8945 | 8945 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 04:55 | 05:00 | 0.08 | 8945 | 8953 | 8 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8945.00 t/8953.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 96.00
05/02/2020 | 05:00 | 05:18 | 0.3 | 8953 | 8968 | 15 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/8953.00 t/8968.00, TF , w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0, ROP 50.00
05/02/2020 | 05:18 | 05:29 | 0.18 | 8968 | 9039 | 71 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/8968.00 t/9039.00, w/WOB 34.00,Flow 756.00, RPM 0.00, Press 3800.00, Tq 0.00, ROP 387.27
05/02/2020 | 05:29 | 05:35 | 0.1 | 9039 | 9039 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Slow pump rates
05/02/2020 | 05:35 | 05:40 | 0.08 | 9039 | 9039 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 05:40 | 05:51 | 0.18 | 9039 | 9134 | 95 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9039.00 t/9134.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 518.18
05/02/2020 | 05:51 | 05:56 | 0.08 | 9134 | 9134 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 05:56 | 06:00 | 0.07 | 9134 | 9150 | 16 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9134.00 t/9150.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 240.00
05/02/2020 | 06:00 | 06:19 | 0.32 | 9150 | 9170 | 20 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9150.00 t/9170.00, TF , w/WOB 20,Flow 756.00, Press 3800.00, Tq 0.00, ROP 63.16
05/02/2020 | 06:19 | 06:30 | 0.18 | 9170 | 9228 | 58 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9170.00 t/9228.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 316.36
05/02/2020 | 06:30 | 06:35 | 0.08 | 9228 | 9228 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 06:35 | 06:48 | 0.22 | 9228 | 9322 | 94 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9228.00 t/9322.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 433.85
05/02/2020 | 06:48 | 06:53 | 0.08 | 9322 | 9322 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 06:53 | 07:00 | 0.12 | 9322 | 9335 | 13 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9322.00 t/9335.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 111.43
05/02/2020 | 07:00 | 07:11 | 0.18 | 9335 | 9353 | 18 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9335.00 t/9353.00, TF , w/WOB 20,Flow 756.00, Press 3800.00, Tq 0.00, ROP 98.18
05/02/2020 | 07:11 | 07:21 | 0.17 | 9353 | 9417 | 64 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9353.00 t/9417.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 384.00
05/02/2020 | 07:21 | 08:37 | 1.27 | 9417 | 9417 | 0 | INT | 2: BHA #2 (Intermediate) | 8O | Replace vibrator hose
05/02/2020 | 08:37 | 08:44 | 0.12 | 9417 | 9417 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 08:44 | 09:08 | 0.4 | 9417 | 9509 | 92 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9417.00 t/9509.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 230.00
05/02/2020 | 09:08 | 09:14 | 0.1 | 9509 | 9509 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 09:14 | 10:05 | 0.85 | 9509 | 9540 | 31 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9509.00 t/9540.00, TF , w/WOB 20,Flow 756.00, Press 3800.00, Tq 0, ROP 36.47
05/02/2020 | 10:05 | 10:40 | 0.58 | 9540 | 9540 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate with #2 pump while repair liner washer on #1
05/02/2020 | 10:40 | 10:51 | 0.18 | 9540 | 9603 | 63 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9540.00 t/9603.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 343.64
05/02/2020 | 10:51 | 10:56 | 0.08 | 9603 | 9603 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 10:56 | 11:03 | 0.12 | 9603 | 9615 | 12 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9603.00 t/9615.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 102.86
05/02/2020 | 11:03 | 11:42 | 0.65 | 9615 | 9640 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9615.00 t/9640.00, TF , w/WOB 20.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 38.46
05/02/2020 | 11:42 | 11:57 | 0.25 | 9640 | 9697 | 57 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9640.00 t/9697.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 228.00
05/02/2020 | 11:57 | 12:04 | 0.12 | 9697 | 9697 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 12:04 | 12:13 | 0.15 | 9697 | 9742 | 45 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9697.00 t/9742.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 300.00
05/02/2020 | 12:13 | 12:18 | 0.08 | 9742 | 9742 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | MWD Survey @ 9672
05/02/2020 | 12:18 | 12:30 | 0.2 | 9742 | 9791 | 49 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9742.00 t/9791.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 245.00
05/02/2020 | 12:30 | 12:35 | 0.08 | 9791 | 9791 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 12:35 | 13:02 | 0.45 | 9791 | 9826 | 35 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9791.00 t/9826.00, TF , w/WOB 20.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 77.78
05/02/2020 | 13:02 | 13:19 | 0.28 | 9826 | 9886 | 60 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9826.00 t/9886.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 211.76
05/02/2020 | 13:19 | 13:25 | 0.1 | 9886 | 9886 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 13:25 | 13:36 | 0.18 | 9886 | 9896 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9886.00 t/9896.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 54.55
05/02/2020 | 13:36 | 14:05 | 0.48 | 9896 | 9921 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9896.00 t/9921.00, TF , w/WOB 20.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 51.72
05/02/2020 | 14:05 | 14:12 | 0.12 | 9921 | 9931 | 10 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9921.00 t/9931.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 85.71
05/02/2020 | 14:12 | 14:17 | 0.08 | 9931 | 9931 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 14:17 | 14:21 | 0.07 | 9931 | 9940 | 9 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9931.00 t/9940.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 135.00
05/02/2020 | 14:21 | 15:05 | 0.73 | 9940 | 9965 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9940.00 t/9965.00, TF , w/WOB 20.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 34.09
05/02/2020 | 15:05 | 15:11 | 0.1 | 9965 | 9980 | 15 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/9965.00 t/9980.00, w/WOB 34.00,Flow 756.00, RPM 80.00, Press 3800.00, Tq 16000.00, ROP 150.00
05/02/2020 | 15:11 | 15:25 | 0.23 | 9980 | 9980 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate with #2 pump while repair liner washer on #1
05/02/2020 | 15:25 | 15:30 | 0.08 | 9980 | 9980 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 15:30 | 19:51 | 4.35 | 9980 | 10074 | 94 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/9980.00 t/10074.00, TF 0.00, w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 21.61
05/02/2020 | 19:51 | 19:55 | 0.07 | 10074 | 10074 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 19:55 | 20:21 | 0.43 | 10074 | 10119 | 45 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10074.00 t/10119.00, w/WOB 34.00,Flow 756.00, RPM 80, Press 3800.00, Tq 16000, ROP 103.85
05/02/2020 | 20:21 | 20:26 | 0.08 | 10119 | 10119 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 20:26 | 22:14 | 1.8 | 10119 | 10150 | 31 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10119.00 t/10150.00, TF , w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 17.22
05/02/2020 | 22:14 | 22:21 | 0.12 | 10150 | 10168 | 18 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10150.00 t/10168.00, w/WOB 34.00,Flow 756.00, RPM 80, Press 3800.00, Tq 16000, ROP 154.29
05/02/2020 | 22:21 | 22:26 | 0.08 | 10168 | 10168 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 22:26 | 23:22 | 0.93 | 10168 | 10193 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10168.00 t/10193.00, TF , w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 26.79
05/02/2020 | 23:22 | 23:45 | 0.38 | 10193 | 10263 | 70 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10193.00 t/10263.00, w/WOB 34.00,Flow 756.00, RPM 80, Press 3800.00, Tq 16000, ROP 182.61
05/02/2020 | 23:45 | 23:50 | 0.08 | 10263 | 10263 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/02/2020 | 23:50 | 24:00 | 0.17 | 10263 | 10276 | 13 | INT | 2: BHA #2 (Intermediate) | 2K | Rotary Drill f/10263.00 t/10276.00, w/WOB 34.00,Flow 756.00, RPM 80, Press 3800.00, Tq 16000, ROP 78.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_3_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 05/03/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 42250
|  |  |  | 24hr Summary: |  | TD Intermediate
|  |  |  | 24hr Lookahead: |  | Circulate, POOH, run casing
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10276 |  | 3005 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 36 | PV: | 14
End Depth (Usft): |  | 10335 |  | 10335 |  | OD (in): |  |  |  | 300: | 24 | YP: | 10
Total Drilled (Usft): |  | 59 |  | 7330 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 52
Slide Drilled (Usft): |  | 59 |  | 708 | [5 empty] | 100: | 13 | Chlorides: | 56000
Rotary Drilled (Usft): |  |  |  | 6622 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.25 / 11.00
Drlg/Circ Hrs: |  | 4.50 / 1.33 |  | 39.37 / 3.52 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water:
Slide Drilling Hrs: |  | 4.5 |  | 22.72 |  | SN: |  | 47857 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  |  |  | 16.65 |  | Bit # |  | 2 |  | PH / Temp(F) | 1.5 / 190.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 13.11 |  | 397.72 / 31.17 |  | OD (in) / TFA: |  | 9.875 / 1.353
BRT Hrs: |  | 12.67 |  | 63.42 |  | Grade In: |  | Green
% Slide: |  | 100 |  | 9.66 |  | Grade Out:
% Rotary: |  |  |  | 90.34 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 - Ulterra - SPL613 - TFA 1.35 |  |  |  | 9.875 | 2 |  |  |  |  | 1.35 |  | 1.35
7 3/4- 7/8 5.9 Stg 2.12? True Slick |  |  |  | 8 | 2 |  |  |  |  | 37.48 |  | 38.83
Pony Collar |  |  |  | 8.063 | 3.25 |  |  |  |  | 10.39 |  | 49.22
8 UBHO |  |  |  | 7.75 | 2.875 |  |  |  |  | 2.72 |  | 51.94
Drill Collar |  |  |  | 7.875 | 3.25 |  |  |  |  | 29.09 |  | 81.03
Drill Collar |  |  |  | 8.125 | 3.25 |  |  |  |  | 29.92 |  | 110.95
X/O 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.813 | 2.938 |  |  |  |  | 3.7 |  | 114.65
2 Stands 6 1/2 DCs |  |  |  | 6.563 | 2.438 |  |  |  |  | 186.61 |  | 301.26
X/O 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.29 |  | 303.55
3 Stands HWDP |  |  |  | 6.5 | 3 |  |  |  |  | 276.68 |  | 580.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.87 |  | 2.12 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10240 | 18.2 | 339.7 | 10102.89 | 1235.53 | 592.87 | 1.04 |  | 145.04 | 869.95 | -0.85 |  | 1.91 | 47
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 13.11 | 32.12 | 80 | 205 | 756 | 3796.15 | 3300 | 204 | 235 | 215 | 195 | 15789.47 | 3000
Run | 186.18 | 31.32 | 79.09 | 202 | 742.63 | 3521.83 | 3011.51 | 204 | 194.33 | 180.6 | 167.3 | 12909.09 | 3000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/03/2020 | 00:00 | 03:00 | 3 | 10276 | 10310 | 34 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10276.00 t/10310.00, TF 0.00, w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 0.00, ROP 11.33
05/03/2020 | 03:00 | 03:05 | 0.08 | 10310 | 10310 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/03/2020 | 03:05 | 04:35 | 1.5 | 10310 | 10335 | 25 | INT | 2: BHA #2 (Intermediate) | 2J | Slide Drill f/10310.00 t/10335.00, TF 0.00, w/WOB 34.00,Flow 756.00, Press 3800.00, Tq 16000.00, ROP 16.67
05/03/2020 | 04:35 | 04:40 | 0.08 | 10335 | 10335 | 0 | INT | 2: BHA #2 (Intermediate) | 10D | Survey & Connection
05/03/2020 | 04:40 | 06:00 | 1.33 | 10335 | 10335 | 0 | INT | 2: BHA #2 (Intermediate) | 5A | Circulate sweeps out
05/03/2020 | 06:00 | 11:40 | 5.67 | 10335 | 10335 | 0 | INT | 2: BHA #2 (Intermediate) | 6B | POOH to run intermediate casing
05/03/2020 | 11:40 | 12:40 | 1 | 10335 | 10335 | 0 | INT | 2: BHA #2 (Intermediate) | 6P | Lay down motor, pick up new motor and rack back BHA in derrick
05/03/2020 | 12:40 | 24:00 | 11.33 | 10335 | 10335 | 0 | INT |  | 26A | Standby for casing opps.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_22_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/22/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17750 |  |  | Well Cost($): |  | 60000
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10335 |  | 10335 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 36 | PV: | 14
End Depth (Usft): |  | 10335 |  | 10335 |  | OD (in): |  |  |  | 300: | 24 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 52
Slide Drilled (Usft): | [9 empty] | 100: | 13 | Chlorides: | 56000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.25 / 11.00
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 6 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 39992 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 1.5 / 190.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: | [5 empty] | Grade In: |  | 0-0
% Slide: | [5 empty] | Grade Out: |  | 1-1
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / U611S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4 - Ulterra - U611S - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.14 |  | 33.74
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 36.02
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.89
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.33
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.33
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.67
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.54
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.63
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.2
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.43
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.59
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.9
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR500011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.94 |  | 2 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 32.12 | 80 | 594 | 756 | 3796.15 | 3300 | 204 | 235 | 215 | 195 | 15789.47 | 3000
Run | 0 | 31.32 | 79.09 | 584 | 742.63 | 3521.83 | 3011.51 | 204 | 194.33 | 180.6 | 167.3 | 12909.09 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/22/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/22/2020 |  | 4 |  | 100 |  | 4 | 400
5 Premium Motor Stator Reline |  |  |  |  | 06/22/2020 |  | 7 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/22/2020 | 00:00 | 22:30 | 22.5 | 10335 | 10335 | 0 | CRV |  | 26B | Standby
06/22/2020 | 22:30 | 24:00 | 1.5 | 10335 | 10335 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6O | P/U BHA 3
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_23_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/23/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 67250
|  |  |  | 24hr Summary: |  | TIH / Drill Cement / Build Curve / Circulate
|  |  |  | 24hr Lookahead: |  | POOH / Swap BHA / TIH / Build Curve to Landing Point / POOH / Swap BHA
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10335 |  | 10335 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 28 | PV: | 10
End Depth (Usft): |  | 10862 |  | 10862 |  | OD (in): |  |  |  | 300: | 18 | YP: | 8
Total Drilled (Usft): |  | 527 |  | 527 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): |  | 413 |  | 413 | [5 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 114 |  | 114 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 11.83 / 3.33 |  | 11.83 / 3.33 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 10.17 |  | 10.17 |  | SN: |  | 39992 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 1.67 |  | 1.67 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 243.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 68.40 / 40.62 |  | 68.40 / 40.62 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 24 |  | Grade In: |  | 0-0
% Slide: |  | 78.37 |  | 78.37 |  | Grade Out: |  | 1-1
% Rotary: |  | 21.63 |  | 21.63 |  | Make / Model: |  | Ulterra / U611S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Nathan Marks |  | Russell Arnold |  | David Lablanc
Bobby Guin |  | Jeff Wells |  | Blake Goodrum
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4 - Ulterra - U611S - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.14 |  | 33.74
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 36.02
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.89
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.33
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.33
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.67
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.54
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.63
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.2
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.43
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.59
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.9
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR500011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.94 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10413 | 23.3 | 330.5 | 10265.23 | 1289.48 | 567.82 | 4.28 |  | -34.15 | 929.43 | 3.72 |  | -6.08 | 148
10508 | 32.7 | 330.6 | 10349.01 | 1328.27 | 545.92 | 9.89 |  | 0.33 | 973.84 | 9.89 |  | 0.11 | 95
10602 | 40 | 336.1 | 10424.69 | 1378.1 | 521.18 | 8.5 |  | 26.31 | 1029.46 | 7.77 |  | 5.85 | 94
10697 | 51.8 | 341.5 | 10490.71 | 1441.66 | 496.87 | 13.07 |  | 20.12 | 1097.34 | 12.42 |  | 5.68 | 95
10791 | 61 | 339.9 | 10542.68 | 1515.45 | 470.97 | 9.89 |  | -8.7 | 1175.17 | 9.79 |  | -1.7 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 44.55 | 23.93 | 30 | 275 | 359.64 | 2932.14 | 3389.29 | 204 | 250 | 220 | 190 | 9083.33 | 3000
Run | 44.55 | 23.93 | 30 | 275 | 359.64 | 2932.14 | 3389.29 | 204 | 250 | 220 | 190 | 9083.33 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/23/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/23/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/23/2020 | 00:00 | 00:20 | 0.33 | 10335 | 10335 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 5A | Test MWD
06/23/2020 | 00:20 | 06:25 | 6.08 | 10335 | 10335 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6A | TIH
06/23/2020 | 06:25 | 06:55 | 0.5 | 10335 | 10335 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 8P | Install Rot. Head
06/23/2020 | 06:55 | 08:05 | 1.17 | 10335 | 10335 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 5A | Drill Cement and Float F/10192
06/23/2020 | 08:05 | 08:15 | 0.17 | 10335 | 10345 | 10 | CRV | 3: BHA 3 (Curve / Lateral) | 2K | Rotary Drill f/10335.00 t/10345.00, w/WOB 14,Flow 245, RPM 30, Press 1950, Tq 9000, ROP 60.00
06/23/2020 | 08:15 | 09:05 | 0.83 | 10345 | 10345 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 5A | Circulate Bottoms Up
06/23/2020 | 09:05 | 09:30 | 0.42 | 10345 | 10345 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 15D | F.I.T.
06/23/2020 | 09:30 | 13:00 | 3.5 | 10345 | 10388 | 43 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10345.00 t/10388.00, TF , w/WOB 35,Flow 350, Press 2600, Tq 9000.00, ROP 12.29
06/23/2020 | 13:00 | 13:15 | 0.25 | 10388 | 10388 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 10D | Survey & Connection
06/23/2020 | 13:15 | 13:40 | 0.42 | 10388 | 10418 | 30 | CRV | 3: BHA 3 (Curve / Lateral) | 2K | Rotary Drill f/10388.00 t/10418.00, w/WOB 25,Flow 350, RPM 30.00, Press 2600, Tq 9000.00, ROP 72.00
06/23/2020 | 13:40 | 14:45 | 1.08 | 10418 | 10482 | 64 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10418.00 t/10482.00, TF , w/WOB 30,Flow 400, Press 3300, Tq 9000.00, ROP 59.08
06/23/2020 | 14:45 | 15:00 | 0.25 | 10482 | 10482 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 10D | Survey & Connection
06/23/2020 | 15:00 | 15:15 | 0.25 | 10482 | 10506 | 24 | CRV | 3: BHA 3 (Curve / Lateral) | 2K | Rotary Drill f/10482.00 t/10506.00, w/WOB 25,Flow 400, RPM 30.00, Press 3300, Tq 9500, ROP 96.00
06/23/2020 | 15:15 | 15:40 | 0.42 | 10506 | 10513 | 7 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10506.00 t/10513.00, TF , w/WOB 14.00,Flow 245.00, Press 1950.00, Tq 9000.00, ROP 16.80
06/23/2020 | 15:40 | 15:55 | 0.25 | 10513 | 10513 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 24A | Drop Agitator Dart
06/23/2020 | 15:55 | 16:00 | 0.08 | 10513 | 10513 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 24A | Check Shot @ 10444 Inc. 27.6 Azi. 329.5
06/23/2020 | 16:00 | 17:10 | 1.17 | 10513 | 10567 | 54 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10513.00 t/10567.00, TF , w/WOB 14.00,Flow 245.00, Press 1950.00, Tq 9000.00, ROP 46.29
06/23/2020 | 17:10 | 17:20 | 0.17 | 10567 | 10577 | 10 | CRV | 3: BHA 3 (Curve / Lateral) | 2K | Rotary Drill f/10567.00 t/10577.00, w/WOB 14.00,Flow 245.00, RPM 30.00, Press 1950.00, Tq 9000.00, ROP 60.00
06/23/2020 | 17:20 | 17:40 | 0.33 | 10577 | 10597 | 20 | CRV | 3: BHA 3 (Curve / Lateral) | 2K | Rotary Drill f/10577.00 t/10597.00, w/WOB 14.00,Flow 245.00, RPM 30.00, Press 1950.00, Tq 9000.00, ROP 60.00
06/23/2020 | 17:40 | 18:45 | 1.08 | 10597 | 10671 | 74 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10597.00 t/10671.00, TF , w/WOB 30,Flow 380, Press 3300.00, Tq 2000, ROP 68.31
06/23/2020 | 18:45 | 19:05 | 0.33 | 10671 | 10671 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 10D | Survey & Connection
06/23/2020 | 19:05 | 19:55 | 0.83 | 10671 | 10720 | 49 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10671.00 t/10720.00, TF , w/WOB 30,Flow 380, Press 3300.00, Tq 2000, ROP 58.80
06/23/2020 | 19:55 | 20:05 | 0.17 | 10720 | 10720 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 1G | Check Shot @ 10651 Inc. 47.4 Azm. 339.6
06/23/2020 | 20:05 | 20:25 | 0.33 | 10720 | 10740 | 20 | CRV | 3: BHA 3 (Curve / Lateral) | 2K | Rotary Drill f/10720.00 t/10740.00, w/WOB 30,Flow 380, RPM 30, Press 3300.00, Tq 9000, ROP 60.00
06/23/2020 | 20:25 | 21:00 | 0.58 | 10740 | 10766 | 26 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10740.00 t/10766.00, TF , w/WOB 30,Flow 380, Press 3300.00, Tq 9000, ROP 44.57
06/23/2020 | 21:00 | 21:10 | 0.17 | 10766 | 10766 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 10D | Survey & Connection
06/23/2020 | 21:10 | 22:40 | 1.5 | 10766 | 10862 | 96 | CRV | 3: BHA 3 (Curve / Lateral) | 2J | Slide Drill f/10766.00 t/10860.00, TF , w/WOB 30,Flow 380, Press 3300.00, Tq 9000, ROP 62.67
06/23/2020 | 22:40 | 22:45 | 0.08 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 10D | Survey
06/23/2020 | 22:45 | 23:45 | 1 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 5A | Circulate
06/23/2020 | 23:45 | 24:00 | 0.25 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6I | Flow Check
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_24_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/24/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17750 |  |  | Well Cost($): |  | 85000
|  |  |  | 24hr Summary: |  | POOH / Swap BHA / TIH / Land Curve / POOH
|  |  |  | 24hr Lookahead: |  | POOH / Swap BHA / TIH / Begin Drilling Lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10862 |  | 10862 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 10954 |  | 10954 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 92 |  | 92 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 46
Slide Drilled (Usft): |  | 92 |  | 92 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 5.75 / 2.33 |  | 5.75 / 2.33 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 5.75 |  | 5.75 |  | SN: |  | 39992 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 226.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 16.00 |  | 0.00 / 16.00 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 16.5 |  | 16.75 |  | Grade In: |  | 0-0
% Slide: |  | 100 |  | 100 |  | Grade Out: |  | 1-1
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / U611S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Jonathan Moore |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4 - Ulterra - U611S - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.14 |  | 33.74
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 36.02
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.89
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.33
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.33
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.67
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.54
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.63
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.2
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.43
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.59
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.9
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR500011 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.94 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10885 | 77.5 | 335.4 | 10575.88 | 1596.37 | 437.49 | 18.11 |  | -15.17 | 1262.66 | 17.55 |  | -4.79 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 22.5 | 0 | 129 | 247 | 2100 | 1950 | 204 | 250 | 230 | 190 | 0 | 3000
Run | 40.54 | 22.5 | 0 | 129 | 247 | 2100 | 1950 | 204 | 250 | 230 | 190 | 0 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/24/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/24/2020 |  | 4 |  | 100 |  | 4 | 400
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 06/24/2020 |  | 5 |  | 1500 |  | 1 | 1500
4 3/4 Motor Reline |  |  |  |  | 06/24/2020 |  | 8 |  | 8000 |  | 1 | 8000
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 06/24/2020 |  | 14 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 17750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/24/2020 | 00:00 | 00:15 | 0.25 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6I | Flow Check
06/24/2020 | 00:15 | 00:50 | 0.58 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6B | POOH
06/24/2020 | 00:50 | 01:15 | 0.42 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6I | Flow Check
06/24/2020 | 01:15 | 01:50 | 0.58 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6B | POOH
06/24/2020 | 01:50 | 02:15 | 0.42 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6I | Pull Rotating Head / Flow Check
06/24/2020 | 02:15 | 06:00 | 3.75 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6B | POOH
06/24/2020 | 06:00 | 06:45 | 0.75 | 10862 | 10862 | 0 | CRV | 3: BHA 3 (Curve / Lateral) | 6P | L/D BHA 3
06/24/2020 | 06:45 | 07:15 | 0.5 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 6O | P/U BHA 4
06/24/2020 | 07:15 | 07:40 | 0.42 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 20C | Test MWD, Bad Test
06/24/2020 | 07:40 | 08:45 | 1.08 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 24A | Replace MWD Tool
06/24/2020 | 08:45 | 08:55 | 0.17 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 5A | Test MWD, Good Test
06/24/2020 | 08:55 | 09:20 | 0.42 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 24A | Make Bit and Top NMDCs
06/24/2020 | 09:20 | 15:05 | 5.75 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 6A | Trip In Hole
06/24/2020 | 15:05 | 15:30 | 0.42 | 10862 | 10862 | 0 | CRV | 4: BHA 4 (Bailout) | 5A | Break Circ. Sync MWD
06/24/2020 | 15:30 | 19:00 | 3.5 | 10862 | 10922 | 60 | CRV | 4: BHA 4 (Bailout) | 2J | Slide Drill f/10860.00 t/10922.00, TF , w/WOB 25,Flow 247, Press 2100, Tq 0, ROP 17.71
06/24/2020 | 19:00 | 19:15 | 0.25 | 10922 | 10922 | 0 | CRV | 4: BHA 4 (Bailout) | 5A | Check Shot @ 10860 72.7 inc. 336.5 azi.
06/24/2020 | 19:15 | 20:15 | 1 | 10922 | 10935 | 13 | CRV | 4: BHA 4 (Bailout) | 2J | Slide Drill f/10922.00 t/10935.00, TF , w/WOB 25,Flow 247, Press 2100, Tq 0, ROP 13.00
06/24/2020 | 20:15 | 20:50 | 0.58 | 10935 | 10935 | 0 | CRV | 4: BHA 4 (Bailout) | 5A | Check Shot @ 10875 75.3 inc. 335.9 azi. - Conference Call
06/24/2020 | 20:50 | 21:40 | 0.83 | 10935 | 10947 | 12 | CRV | 4: BHA 4 (Bailout) | 2J | Slide Drill f/10935.00 t/10947.00, TF , w/WOB 25,Flow 247, Press 2100, Tq 0, ROP 14.40
06/24/2020 | 21:40 | 21:55 | 0.25 | 10947 | 10947 | 0 | CRV |  | 10D | Survey & Connection
06/24/2020 | 21:55 | 22:20 | 0.42 | 10947 | 10954 | 7 | CRV | 4: BHA 4 (Bailout) | 2J | Slide Drill f/10947.00 t/10954.00, TF , w/WOB 15,Flow 247.00, Press 2100.00, Tq 2000, ROP 16.80
06/24/2020 | 22:20 | 23:15 | 0.92 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 5A | Circulate
06/24/2020 | 23:15 | 23:30 | 0.25 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 6I | Flow Check / Pump Slug
06/24/2020 | 23:30 | 24:00 | 0.5 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_25_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/25/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 20250 |  |  | Well Cost($): |  | 105250
|  |  |  | 24hr Summary: |  | POOH / Swap BHA / TIH / Begin Drilling Lateral
|  |  |  | 24hr Lookahead: |  | Continue Drilling Lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10954 |  | 10954 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 11442 |  | 11442 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 488 |  | 488 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 46
Slide Drilled (Usft): |  | 27 |  | 27 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): |  | 461 |  | 461 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 4.75 / 0.00 |  | 4.75 / 0.00 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 1.17 |  | 1.17 |  | SN: |  | 40962 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 3.58 |  | 3.58 |  | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 226.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 128.65 / 23.14 |  | 128.65 / 23.14 |  | OD (in) / TFA: |  | 6.750 / 1.144
BRT Hrs: |  | 17 |  | 17 |  | Grade In: |  | 0-0
% Slide: |  | 5.53 |  | 5.53 |  | Grade Out: |  | 0-1
% Rotary: |  | 94.47 |  | 94.47 |  | Make / Model: |  | Baker Hughes / U611S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Jonathan Moore |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" - Ulterra - U611S - TFA 1.14 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 26.14 |  | 26.74
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 29.02
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 38.89
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 42.33
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 73.33
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 104.67
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 135.54
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 138.63
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2747.2
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2750.43
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2779.59
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2782.9
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475076 |  | PDCI |  | 7/8 3.8 |  | 7/8 | 4 |  | 2.5 |  | 0.52 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10980 | 93 | 332.5 | 10583.72 | 1681.15 | 396.02 | 16.6 |  | -10.72 | 1357.02 | 16.32 |  | -3.05 | 95
11075 | 94.2 | 331.2 | 10577.76 | 1764.74 | 351.29 | 1.86 |  | -47.2 | 1451.68 | 1.26 |  | -1.37 | 95
11171 | 91 | 333.8 | 10573.4 | 1849.79 | 307.02 | 4.29 |  | 140.87 | 1547.47 | -3.33 |  | 2.71 | 96
11266 | 89.9 | 333.2 | 10572.66 | 1934.81 | 264.64 | 1.32 |  | -151.39 | 1642.43 | -1.16 |  | -0.63 | 95
11361 | 87.9 | 332.7 | 10574.48 | 2019.39 | 221.44 | 2.17 |  | -165.97 | 1737.34 | -2.11 |  | -0.53 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 23.33 | 58.57 | 331 | 400 | 4233.33 | 3800 | 204 | 250 | 220 | 190 | 10000 | 3000
Run | 16 | 23.33 | 58.57 | 331 | 400 | 4233.33 | 3800 | 204 | 250 | 220 | 190 | 10000 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/25/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/25/2020 |  | 4 |  | 100 |  | 4 | 400
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 06/25/2020 |  | 5 |  | 1500 |  | 1 | 1500
5 Premium Motor Stator Reline |  |  |  |  | 06/25/2020 |  | 7 |  | 10500 |  | 1 | 10500
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 06/25/2020 |  | 14 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 20250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/25/2020 | 00:00 | 00:15 | 0.25 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 6I | Flow Check
06/25/2020 | 00:15 | 00:30 | 0.25 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 24A | Pull R/T Head
06/25/2020 | 00:30 | 04:30 | 4 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 6B | POOH
06/25/2020 | 04:30 | 05:15 | 0.75 | 10954 | 10954 | 0 | CRV | 4: BHA 4 (Bailout) | 6P | L/D BHA 4
06/25/2020 | 05:15 | 06:20 | 1.08 | 10954 | 10954 | 0 | CRV |  | 8K | Repair ST-80
06/25/2020 | 06:20 | 07:00 | 0.67 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 6O | P/U BHA 5
06/25/2020 | 07:00 | 08:40 | 1.67 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 8O | Repair Rig Floor
06/25/2020 | 08:40 | 09:10 | 0.5 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 24A | Pick Up and Test MWD
06/25/2020 | 09:10 | 09:30 | 0.33 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 24A | Make Up Bit and Top NMDCs
06/25/2020 | 09:30 | 12:30 | 3 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 6A | Trip in hole
06/25/2020 | 12:30 | 14:50 | 2.33 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 8O | Repair Damaged Floor Plate
06/25/2020 | 14:50 | 18:35 | 3.75 | 10954 | 10954 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/25/2020 | 18:35 | 19:40 | 1.08 | 10954 | 11049 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/10954.00 t/11049.00, w/WOB 15.00,Flow 400.00, RPM 30.00, Press 4150.00, Tq 10000.00, ROP 87.69
06/25/2020 | 19:40 | 19:50 | 0.17 | 11049 | 11049 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/25/2020 | 19:50 | 20:25 | 0.58 | 11049 | 11098 | 49 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11049.00 t/11098.00, w/WOB 15.00,Flow 400.00, RPM 30.00, Press 4150.00, Tq 10000.00, ROP 84.00
06/25/2020 | 20:25 | 20:35 | 0.17 | 11098 | 11098 | 0 | LAT | 5: BHA 5 (Lateral) | 1G | Checkshot 93.8 / 331.5
06/25/2020 | 20:35 | 21:35 | 1 | 11098 | 11123 | 25 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/11098.00 t/11123.00, TF 140.00, w/WOB 15.00,Flow 400.00, Press 3950.00, Tq 3000.00, ROP 25.00
06/25/2020 | 21:35 | 21:55 | 0.33 | 11123 | 11144 | 21 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11123.00 t/11144.00, w/WOB 15.00,Flow 400.00, RPM 30.00, Press 4150.00, Tq 10000.00, ROP 63.00
06/25/2020 | 21:55 | 22:00 | 0.08 | 11144 | 11144 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/25/2020 | 22:00 | 22:35 | 0.58 | 11144 | 11240 | 96 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11144.00 t/11240.00, w/WOB 25,Flow 400.00, RPM 80.00, Press 4350.00, Tq 10000.00, ROP 164.57
06/25/2020 | 22:35 | 22:40 | 0.08 | 11240 | 11240 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/25/2020 | 22:40 | 23:05 | 0.42 | 11240 | 11335 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11240.00 t/11335.00, w/WOB 30,Flow 400.00, RPM 80.00, Press 4350.00, Tq 10000.00, ROP 228.00
06/25/2020 | 23:05 | 23:10 | 0.08 | 11335 | 11335 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/25/2020 | 23:10 | 23:40 | 0.5 | 11335 | 11430 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11335.00 t/11430.00, w/WOB 30,Flow 400.00, RPM 80.00, Press 4500, Tq 10000.00, ROP 190.00
06/25/2020 | 23:40 | 23:45 | 0.08 | 11430 | 11430 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/25/2020 | 23:45 | 23:50 | 0.08 | 11430 | 11440 | 10 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11430.00 t/11440.00, w/WOB 30,Flow 400.00, RPM 80.00, Press 4500, Tq 10000.00, ROP 120.00
06/25/2020 | 23:50 | 24:00 | 0.17 | 11440 | 11442 | 2 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/11440.00 t/11442.00, TF 20.00, w/WOB 35,Flow 400.00, Press 4000, Tq 10000.00, ROP 12.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_26_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/26/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 112500
|  |  |  | 24hr Summary: |  | Drill Ahead in Lateral Section
|  |  |  | 24hr Lookahead: |  | Drill Ahead in Lateral Section
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11442 |  | 10954 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 13920 |  | 13920 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 2478 |  | 2966 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 46
Slide Drilled (Usft): |  | 401 |  | 428 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): |  | 2077 |  | 2538 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 21.75 / 0.00 |  | 26.50 / 0.00 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 9.67 |  | 10.83 |  | SN: |  | 13430004 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 12.08 |  | 15.67 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 226.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 171.89 / 41.48 |  | 162.00 / 39.51 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 25.25 |  | 41 |  | Grade In: |  | 0-0
% Slide: |  | 16.18 |  | 14.43 |  | Grade Out: |  | 1-1
% Rotary: |  | 83.82 |  | 85.57 |  | Make / Model: |  | Halliburton / GTD64C
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Dean Day |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" - Halliburton GTD64C - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.1 |  | 33.7
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 35.98
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.85
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.29
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.63
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.5
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.59
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.16
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.39
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.55
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.86
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.85 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11455 | 89.1 | 333.8 | 10576.94 | 2103.3 | 179.15 | 1.73 |  | 42.52 | 1831.26 | 1.28 |  | 1.17 | 94
11550 | 90.5 | 334.1 | 10577.27 | 2188.65 | 137.43 | 1.51 |  | 12.1 | 1926.24 | 1.47 |  | 0.32 | 95
11645 | 91.2 | 334.3 | 10575.86 | 2274.17 | 96.09 | 0.77 |  | 15.94 | 2021.22 | 0.74 |  | 0.21 | 95
11740 | 95.5 | 336.8 | 10570.31 | 2360.47 | 56.85 | 5.23 |  | 30.07 | 2116.02 | 4.53 |  | 2.63 | 95
11835 | 97.6 | 336 | 10559.48 | 2446.95 | 19.07 | 2.36 |  | -20.69 | 2210.37 | 2.21 |  | -0.84 | 95
11932 | 98.5 | 334.8 | 10545.89 | 2534.28 | -20.91 | 1.54 |  | -52.77 | 2306.41 | 0.93 |  | -1.24 | 97
12027 | 96.6 | 334.6 | 10533.41 | 2619.42 | -61.16 | 2.01 |  | -174.03 | 2400.58 | -2 |  | -0.21 | 95
12122 | 95.2 | 333.9 | 10523.65 | 2704.53 | -102.21 | 1.65 |  | -153.52 | 2495.06 | -1.47 |  | -0.74 | 95
12216 | 92.4 | 329.7 | 10517.41 | 2787.16 | -146.53 | 5.36 |  | -123.59 | 2588.68 | -2.98 |  | -4.47 | 94
12311 | 90.5 | 329.3 | 10515.01 | 2868.98 | -194.72 | 2.04 |  | -168.11 | 2683.2 | -2 |  | -0.42 | 95
12405 | 90.9 | 330.7 | 10513.86 | 2950.38 | -241.72 | 1.55 |  | 74.05 | 2776.82 | 0.43 |  | 1.49 | 94
12499 | 91.1 | 333 | 10512.22 | 3033.24 | -286.06 | 2.46 |  | 85.01 | 2870.66 | 0.21 |  | 2.45 | 94
12595 | 92.4 | 334.9 | 10509.29 | 3119.44 | -328.19 | 2.4 |  | 55.58 | 2966.59 | 1.35 |  | 1.98 | 96
12689 | 93.1 | 336.3 | 10504.78 | 3204.95 | -366.98 | 1.66 |  | 63.38 | 3060.47 | 0.74 |  | 1.49 | 94
12784 | 93.2 | 336.2 | 10499.56 | 3291.77 | -405.18 | 0.15 |  | -44.95 | 3155.31 | 0.11 |  | -0.11 | 95
12879 | 93.1 | 334.9 | 10494.34 | 3378.12 | -444.44 | 1.37 |  | -94.37 | 3250.16 | -0.11 |  | -1.37 | 95
12973 | 93.8 | 336.1 | 10488.68 | 3463.5 | -483.35 | 1.48 |  | 59.66 | 3343.98 | 0.74 |  | 1.28 | 94
13067 | 95.3 | 335.7 | 10481.22 | 3549.03 | -521.61 | 1.65 |  | -14.87 | 3437.67 | 1.6 |  | -0.43 | 94
13162 | 95.3 | 337.7 | 10472.45 | 3635.91 | -559.03 | 2.1 |  | 89.91 | 3532.22 | 0 |  | 2.11 | 95
13256 | 92.7 | 339.9 | 10465.89 | 3723.32 | -592.93 | 3.62 |  | 139.75 | 3625.78 | -2.77 |  | 2.34 | 94
13352 | 91.2 | 339.8 | 10462.62 | 3813.39 | -625.98 | 1.57 |  | -176.19 | 3721.38 | -1.56 |  | -0.1 | 96
13446 | 90.8 | 339.4 | 10460.98 | 3901.48 | -658.74 | 0.6 |  | -135 | 3815.07 | -0.43 |  | -0.43 | 94
13541 | 90.6 | 339.5 | 10459.82 | 3990.43 | -692.09 | 0.24 |  | 153.44 | 3909.78 | -0.21 |  | 0.11 | 95
13635 | 92.1 | 339.2 | 10457.61 | 4078.36 | -725.23 | 1.63 |  | -11.3 | 4003.49 | 1.6 |  | -0.32 | 94
13730 | 94.3 | 339.1 | 10452.31 | 4167 | -758.98 | 2.32 |  | -2.6 | 4098.09 | 2.32 |  | -0.11 | 95
13826 | 96 | 337.4 | 10443.69 | 4255.8 | -794.41 | 2.5 |  | -44.81 | 4193.55 | 1.77 |  | -1.77 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 114.04 | 30.56 | 79.52 | 352 | 400 | 4538.89 | 3800 | 204 | 262.64 | 213.19 | 197.78 | 13000 | 3000
Run | 112.05 | 29.11 | 74.29 | 346 | 400 | 4477.78 | 3800 | 204 | 260.11 | 214.56 | 196.22 | 12250 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/26/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/26/2020 |  | 4 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/26/2020 | 00:00 | 00:45 | 0.75 | 11442 | 11475 | 33 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/11442.00 t/11475.00, TF 20.00, w/WOB 35,Flow 400.00, Press 4000, Tq 10000.00, ROP 44.00
06/26/2020 | 00:45 | 01:00 | 0.25 | 11475 | 11524 | 49 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11475.00 t/11524.00, w/WOB 30,Flow 400.00, RPM 70, Press 4500, Tq 13000, ROP 196.00
06/26/2020 | 01:00 | 01:05 | 0.08 | 11524 | 11524 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 01:05 | 01:25 | 0.33 | 11524 | 11524 | 0 | LAT | 5: BHA 5 (Lateral) | 1G | Recycle for Survey
06/26/2020 | 01:25 | 01:50 | 0.42 | 11524 | 11619 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11524.00 t/11619.00, w/WOB 30,Flow 400.00, RPM 80.00, Press 4500, Tq 10000.00, ROP 228.00
06/26/2020 | 01:50 | 02:00 | 0.17 | 11619 | 11619 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 02:00 | 02:05 | 0.08 | 11619 | 11632 | 13 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11619.00 t/11632.00, w/WOB 30,Flow 400.00, RPM 80.00, Press 4500, Tq 10000.00, ROP 156.00
06/26/2020 | 02:05 | 02:55 | 0.83 | 11632 | 11672 | 40 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/11632.00 t/11672.00, TF , w/WOB 35,Flow 400.00, Press 4000, Tq 10000.00, ROP 48.00
06/26/2020 | 02:55 | 03:05 | 0.17 | 11672 | 11714 | 42 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11672.00 t/11714.00, w/WOB 30,Flow 400.00, RPM 80.00, Press 4500, Tq 10000.00, ROP 252.00
06/26/2020 | 03:05 | 03:10 | 0.08 | 11714 | 11714 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 03:10 | 03:35 | 0.42 | 11714 | 11809 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11714.00 t/11809.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 228.00
06/26/2020 | 03:35 | 03:40 | 0.08 | 11809 | 11809 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 03:40 | 04:00 | 0.33 | 11809 | 11904 | 95 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11809.00 t/11904.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 285.00
06/26/2020 | 04:00 | 04:10 | 0.17 | 11904 | 11904 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 04:10 | 04:15 | 0.08 | 11904 | 11920 | 16 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11904.00 t/11920.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 192.00
06/26/2020 | 04:15 | 04:55 | 0.67 | 11920 | 11940 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/11920.00 t/11940.00, TF , w/WOB 40,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 30.00
06/26/2020 | 04:55 | 05:15 | 0.33 | 11940 | 12001 | 61 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/11940.00 t/12001.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 183.00
06/26/2020 | 05:15 | 05:25 | 0.17 | 12001 | 12001 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 05:25 | 05:30 | 0.08 | 12001 | 12020 | 19 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12001.00 t/12020.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 228.00
06/26/2020 | 05:30 | 06:00 | 0.5 | 12020 | 12045 | 25 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12020.00 t/12045.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 50.00
06/26/2020 | 06:00 | 07:00 | 1 | 12045 | 12120 | 75 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12045.00 t/12120.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 75.00
06/26/2020 | 07:00 | 07:30 | 0.5 | 12120 | 12135 | 15 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12120.00 t/12135.00, TF 180.00 , w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 30.00
06/26/2020 | 07:30 | 08:00 | 0.5 | 12135 | 12211 | 76 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12135.00 t/12211.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 152.00
06/26/2020 | 08:00 | 08:20 | 0.33 | 12211 | 12231 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12211.00 t/12231.00, TF 180.00 , w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 60.00
06/26/2020 | 08:20 | 09:25 | 1.08 | 12231 | 12395 | 164 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12231.00 t/12395.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 151.38
06/26/2020 | 09:25 | 10:25 | 1 | 12395 | 12425 | 30 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12395.00 t/12425.00, TF 90.00 , w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 30.00
06/26/2020 | 10:25 | 11:30 | 1.08 | 12425 | 12580 | 155 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12425.00 t/12580.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 143.08
06/26/2020 | 11:30 | 12:00 | 0.5 | 12580 | 12605 | 25 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12580.00 t/12605.00, TF , w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 50.00
06/26/2020 | 12:00 | 14:00 | 2 | 12605 | 12960 | 355 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12605.00 t/12960.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 177.50
06/26/2020 | 14:00 | 14:30 | 0.5 | 12960 | 12960 | 0 | LAT | 5: BHA 5 (Lateral) | 8O | O-ring bad on Vibrator Hose. Repair Same.
06/26/2020 | 14:30 | 14:50 | 0.33 | 12960 | 12980 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/12960.00 t/12980.00, TF 80.00, w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 60.00
06/26/2020 | 14:50 | 15:00 | 0.17 | 12980 | 13042 | 62 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/12980.00 t/13042.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 372.00
06/26/2020 | 15:00 | 15:40 | 0.67 | 13042 | 13042 | 0 | LAT | 5: BHA 5 (Lateral) | 8P | Rig Service.
06/26/2020 | 15:40 | 16:15 | 0.58 | 13042 | 13150 | 108 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13042.00 t/13150.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 185.14
06/26/2020 | 16:15 | 17:00 | 0.75 | 13150 | 13175 | 25 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13150.00 t/13175.00, TF 120 , w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 33.33
06/26/2020 | 17:00 | 17:35 | 0.58 | 13175 | 13242 | 67 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13175.00 t/13242.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4500.00, Tq 13000.00, ROP 114.86
06/26/2020 | 17:35 | 18:20 | 0.75 | 13242 | 13260 | 18 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13242.00 t/13260.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4500.00, Tq 13000.00, ROP 24.00
06/26/2020 | 18:20 | 19:30 | 1.17 | 13260 | 13535 | 275 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13260.00 t/13535.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 235.71
06/26/2020 | 19:30 | 20:10 | 0.67 | 13535 | 13620 | 85 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13535.00 t/13535.00, TF -40.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 0.00
06/26/2020 | 19:30 | 20:10 | 0.67 | 13535 | 13535 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 20:10 | 20:45 | 0.58 | 13620 | 13620 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/26/2020 | 20:10 | 20:45 | 0.58 | 13620 | 13620 | 0 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13535.00 t/13620.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 145.71
06/26/2020 | 20:45 | 21:45 | 1 | 13620 | 13645 | 25 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13620.00 t/13645.00, TF -40.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 25.00
06/26/2020 | 21:45 | 22:10 | 0.42 | 13645 | 13726 | 81 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13645.00 t/13726.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 194.40
06/26/2020 | 22:10 | 23:00 | 0.83 | 13726 | 13745 | 19 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13726.00 t/13745.00, TF -60.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 22.80
06/26/2020 | 23:00 | 23:45 | 0.75 | 13745 | 13919 | 174 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13745.00 t/13919.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 232.00
06/26/2020 | 23:45 | 24:00 | 0.25 | 13919 | 13920 | 1 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13919.00 t/13920.00, TF -140.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 4.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_27_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/27/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9000 |  |  | Well Cost($): |  | 121500
|  |  |  | 24hr Summary: |  | Drill ahead in lateral section
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral section
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13920 |  | 10954 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 15995 |  | 15995 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 2075 |  | 5041 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 46
Slide Drilled (Usft): |  | 189 |  | 617 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): |  | 1886 |  | 4424 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 23.08 / 0.08 |  | 49.58 / 0.08 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 10.58 |  | 21.42 |  | SN: |  | 13430004 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 12.5 |  | 28.17 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 226.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 150.88 / 17.86 |  | 157.07 / 28.81 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 65 |  | Grade In: |  | 0-0
% Slide: |  | 9.11 |  | 12.24 |  | Grade Out: |  | 1-1
% Rotary: |  | 90.89 |  | 87.76 |  | Make / Model: |  | Halliburton / GTD64C
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Dean Day |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" - Halliburton GTD64C - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.1 |  | 33.7
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 35.98
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.85
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.29
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.63
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.5
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.59
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.16
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.39
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.55
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.86
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.85 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13922 | 97.8 | 337 | 10432.16 | 4343.65 | -831.34 | 1.92 |  | -12.42 | 4288.78 | 1.88 |  | -0.42 | 96
14018 | 97.4 | 335.7 | 10419.46 | 4430.81 | -869.51 | 1.41 |  | -107.16 | 4383.91 | -0.42 |  | -1.35 | 96
14112 | 93.3 | 333.7 | 10410.69 | 4515.4 | -909.5 | 4.85 |  | -153.99 | 4477.47 | -4.36 |  | -2.13 | 94
14208 | 90.5 | 332.7 | 10407.51 | 4601.03 | -952.76 | 3.1 |  | -160.34 | 4573.36 | -2.92 |  | -1.04 | 96
14302 | 89.9 | 332.7 | 10407.18 | 4684.56 | -995.87 | 0.64 |  | 180 | 4667.28 | -0.64 |  | 0 | 94
14397 | 89.4 | 332.3 | 10407.76 | 4768.83 | -1039.73 | 0.67 |  | -141.34 | 4762.18 | -0.53 |  | -0.42 | 95
14491 | 90.5 | 333.3 | 10407.85 | 4852.43 | -1082.7 | 1.58 |  | 42.28 | 4856.11 | 1.17 |  | 1.06 | 94
14585 | 91.6 | 334.1 | 10406.12 | 4936.68 | -1124.34 | 1.45 |  | 36.02 | 4950.07 | 1.17 |  | 0.85 | 94
14681 | 92.7 | 335.4 | 10402.52 | 5023.45 | -1165.26 | 1.77 |  | 49.72 | 5045.99 | 1.15 |  | 1.35 | 96
14775 | 94.2 | 336.2 | 10396.87 | 5109.03 | -1203.72 | 1.81 |  | 28.01 | 5139.81 | 1.6 |  | 0.85 | 94
14871 | 94.3 | 334.9 | 10389.75 | 5196.18 | -1243.35 | 1.35 |  | -85.54 | 5235.54 | 0.1 |  | -1.35 | 96
14965 | 92.6 | 334.3 | 10384.09 | 5280.93 | -1283.59 | 1.92 |  | -160.57 | 5329.36 | -1.81 |  | -0.64 | 94
15060 | 92.7 | 334.5 | 10379.7 | 5366.51 | -1324.6 | 0.24 |  | 63.41 | 5424.26 | 0.11 |  | 0.21 | 95
15155 | 93.9 | 334.5 | 10374.23 | 5452.12 | -1365.43 | 1.26 |  | 0 | 5519.09 | 1.26 |  | 0 | 95
15250 | 92.9 | 334.1 | 10368.6 | 5537.57 | -1406.55 | 1.13 |  | -158.22 | 5613.92 | -1.05 |  | -0.42 | 95
15344 | 92.8 | 334.2 | 10363.93 | 5622.06 | -1447.49 | 0.15 |  | 135.03 | 5707.79 | -0.11 |  | 0.11 | 94
15439 | 93.6 | 334.6 | 10358.62 | 5707.6 | -1488.47 | 0.94 |  | 26.52 | 5802.63 | 0.84 |  | 0.42 | 95
15534 | 94.2 | 332.8 | 10352.16 | 5792.56 | -1530.46 | 1.99 |  | -71.47 | 5897.38 | 0.63 |  | -1.89 | 95
15628 | 92.2 | 333.2 | 10346.91 | 5876.18 | -1573.07 | 2.17 |  | 168.7 | 5991.17 | -2.13 |  | 0.43 | 94
15722 | 92.4 | 333.5 | 10343.14 | 5960.13 | -1615.2 | 0.38 |  | 56.28 | 6085.06 | 0.21 |  | 0.32 | 94
15817 | 93 | 332 | 10338.67 | 6044.49 | -1658.65 | 1.7 |  | -68.14 | 6179.87 | 0.63 |  | -1.58 | 95
15912 | 94.2 | 331.3 | 10332.7 | 6127.93 | -1703.67 | 1.46 |  | -30.19 | 6274.52 | 1.26 |  | -0.74 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 89.83 | 30 | 80 | 352 | 400 | 4808.7 | 3834.78 | 204 | 263 | 213 | 198 | 15333.33 | 3000
Run | 101.69 | 29.41 | 76 | 348 | 400 | 4589.71 | 3811.76 | 204 | 261.09 | 214.03 | 196.82 | 13175 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/27/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/27/2020 |  | 4 |  | 100 |  | 4 | 400
300-347?F |  |  |  |  | 06/27/2020 |  | 13 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 9000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/27/2020 | 00:00 | 01:30 | 1.5 | 13920 | 13949 | 29 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/13920.00 t/13949.00, TF -140.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 19.33
06/27/2020 | 01:30 | 02:00 | 0.5 | 13949 | 14038 | 89 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/13949.00 t/14038.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 178.00
06/27/2020 | 02:00 | 02:05 | 0.08 | 14038 | 14038 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/27/2020 | 02:05 | 03:20 | 1.25 | 14038 | 14068 | 30 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14038.00 t/14068.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 24.00
06/27/2020 | 03:20 | 03:50 | 0.5 | 14068 | 14146 | 78 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14068.00 t/14146.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 156.00
06/27/2020 | 03:50 | 03:55 | 0.08 | 14146 | 14146 | 0 | LAT | 5: BHA 5 (Lateral) | 10D | Survey & Connection
06/27/2020 | 03:55 | 05:05 | 1.17 | 14146 | 14166 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14146.00 t/14166.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 17.14
06/27/2020 | 05:05 | 05:40 | 0.58 | 14166 | 14235 | 69 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14166.00 t/14235.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 118.29
06/27/2020 | 05:40 | 05:45 | 0.08 | 14235 | 14235 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Checkshot @ 14235 90.7 / 332.8
06/27/2020 | 05:45 | 07:30 | 1.75 | 14235 | 14478 | 243 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14235.00 t/14478.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 138.86
06/27/2020 | 07:30 | 08:30 | 1 | 14478 | 14500 | 22 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14478.00 t/14500.00, TF 20 , w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 22.00
06/27/2020 | 08:30 | 10:00 | 1.5 | 14500 | 14665 | 165 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14500.00 t/14665.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 110.00
06/27/2020 | 10:00 | 11:00 | 1 | 14665 | 14685 | 20 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14665.00 t/14685.00, TF 30 , w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 20.00
06/27/2020 | 11:00 | 12:20 | 1.33 | 14685 | 14856 | 171 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14685.00 t/14856.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 128.25
06/27/2020 | 12:20 | 13:00 | 0.67 | 14856 | 14868 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14856.00 t/14868.00, TF 180 , w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 18.00
06/27/2020 | 13:00 | 13:40 | 0.67 | 14868 | 14950 | 82 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14868.00 t/14950.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 123.00
06/27/2020 | 13:40 | 14:20 | 0.67 | 14950 | 14962 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/14950.00 t/14962.00, TF 180, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 18.00
06/27/2020 | 14:20 | 16:00 | 1.67 | 14962 | 15236 | 274 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/14962.00 t/15236.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 164.40
06/27/2020 | 16:00 | 16:40 | 0.67 | 15236 | 15248 | 12 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15236.00 t/15248.00, TF 180, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 13000.00, ROP 18.00
06/27/2020 | 16:40 | 17:00 | 0.33 | 15248 | 15319 | 71 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15248.00 t/15319.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 13000.00, ROP 213.00
06/27/2020 | 17:00 | 17:40 | 0.67 | 15319 | 15319 | 0 | LAT | 5: BHA 5 (Lateral) | 8P | Rig Service
06/27/2020 | 17:40 | 18:50 | 1.17 | 15319 | 15527 | 208 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15319.00 t/15527.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 17000.00, ROP 178.29
06/27/2020 | 18:50 | 19:30 | 0.67 | 15527 | 15535 | 8 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15527.00 t/15535.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4800.00, Tq 17000.00, ROP 12.00
06/27/2020 | 19:30 | 20:00 | 0.5 | 15535 | 15615 | 80 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15535.00 t/15615.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 160.00
06/27/2020 | 20:00 | 21:15 | 1.25 | 15615 | 15631 | 16 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15615.00 t/15631.00, TF 160.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 12.80
06/27/2020 | 21:15 | 23:15 | 2 | 15631 | 15987 | 356 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/15631.00 t/15987.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 178.00
06/27/2020 | 23:15 | 24:00 | 0.75 | 15987 | 15995 | 8 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15987.00 t/15995.00, TF 150.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 10.67
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_28_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/28/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9000 |  |  | Well Cost($): |  | 130500
|  |  |  | 24hr Summary: |  | Drill ahead in lateral section
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral section
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15995 |  | 10954 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 17138 |  | 17138 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 1143 |  | 6184 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 46
Slide Drilled (Usft): |  | 201 |  | 818 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): |  | 942 |  | 5366 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 22.75 / 0.58 |  | 72.33 / 0.67 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 15 |  | 36.42 |  | SN: |  | 13430004 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 7.75 |  | 35.92 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 226.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 121.55 / 13.40 |  | 149.40 / 22.46 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 89 |  | Grade In: |  | 0-0
% Slide: |  | 17.59 |  | 13.23 |  | Grade Out: |  | 1-1
% Rotary: |  | 82.41 |  | 86.77 |  | Make / Model: |  | Halliburton / GTD64C
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Dean Day |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" - Halliburton GTD64C - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.1 |  | 33.7
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 35.98
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.85
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.29
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.63
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.5
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.59
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.16
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.39
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.55
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.86
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.85 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16006 | 93.1 | 331.9 | 10326.72 | 6210.44 | -1748.28 | 1.33 |  | 151.42 | 6368.15 | -1.17 |  | 0.64 | 94
16100 | 90.6 | 332.7 | 10323.68 | 6293.62 | -1791.95 | 2.79 |  | 162.25 | 6461.99 | -2.66 |  | 0.85 | 94
16195 | 90.2 | 333.4 | 10323.02 | 6378.3 | -1835.01 | 0.85 |  | 119.74 | 6556.93 | -0.42 |  | 0.74 | 95
16291 | 92.2 | 334.7 | 10321.01 | 6464.6 | -1877 | 2.48 |  | 33.01 | 6652.89 | 2.08 |  | 1.35 | 96
16385 | 92.8 | 341.4 | 10316.9 | 6551.65 | -1912.09 | 7.15 |  | 84.74 | 6746.61 | 0.64 |  | 7.13 | 94
16480 | 95 | 345.8 | 10310.44 | 6642.54 | -1938.84 | 5.17 |  | 63.24 | 6840.31 | 2.32 |  | 4.63 | 95
16574 | 96.1 | 341.7 | 10301.34 | 6732.34 | -1965.01 | 4.5 |  | -74.72 | 6932.77 | 1.17 |  | -4.36 | 94
16669 | 95.1 | 336.9 | 10292.07 | 6820.76 | -1998.43 | 5.14 |  | -101.58 | 7027.02 | -1.05 |  | -5.05 | 95
16764 | 93.9 | 335 | 10284.61 | 6907.24 | -2037.02 | 2.36 |  | -122.28 | 7121.71 | -1.26 |  | -2 | 95
16860 | 91.3 | 332 | 10280.26 | 6993.04 | -2079.81 | 4.13 |  | -130.87 | 7217.56 | -2.71 |  | -3.12 | 96
16954 | 92 | 331.8 | 10277.55 | 7075.93 | -2124.06 | 0.77 |  | -15.94 | 7311.38 | 0.74 |  | -0.21 | 94
17049 | 91.6 | 331.7 | 10274.57 | 7159.57 | -2169.01 | 0.43 |  | -165.97 | 7406.18 | -0.42 |  | -0.11 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 50.24 | 30 | 80 | 352 | 400 | 4850 | 4000 | 204 | 278.58 | 211.74 | 188.32 | 17000 | 3000
Run | 85.51 | 29.54 | 76.8 | 349 | 400 | 4646.55 | 3852.87 | 204 | 264.91 | 213.53 | 194.97 | 14020 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/28/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/28/2020 |  | 4 |  | 100 |  | 4 | 400
300-347?F |  |  |  |  | 06/28/2020 |  | 13 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 9000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/28/2020 | 00:00 | 01:05 | 1.08 | 15995 | 16011 | 16 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/15995.00 t/16011.00, TF 150.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 14.77
06/28/2020 | 01:05 | 01:35 | 0.5 | 16011 | 16080 | 69 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16011.00 t/16080.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 138.00
06/28/2020 | 01:35 | 03:20 | 1.75 | 16080 | 16110 | 30 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16080.00 t/16110.00, TF 130.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 17.14
06/28/2020 | 03:20 | 04:30 | 1.17 | 16110 | 16275 | 165 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16110.00 t/16275.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 141.43
06/28/2020 | 04:30 | 06:25 | 1.92 | 16275 | 16302 | 27 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16275.00 t/16302.00, TF 20.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 14.09
06/28/2020 | 06:25 | 07:40 | 1.25 | 16302 | 16460 | 158 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16302.00 t/16460.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 126.40
06/28/2020 | 07:40 | 10:00 | 2.33 | 16460 | 16490 | 30 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16460.00 t/16490.00, TF -70, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 12.86
06/28/2020 | 10:00 | 10:45 | 0.75 | 16490 | 16562 | 72 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16490.00 t/16562.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 96.00
06/28/2020 | 10:45 | 13:25 | 2.67 | 16562 | 16595 | 33 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16562.00 t/16595.00, TF -100, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 12.38
06/28/2020 | 13:25 | 14:15 | 0.83 | 16595 | 16657 | 62 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16595.00 t/16657.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 74.40
06/28/2020 | 14:15 | 16:00 | 1.75 | 16657 | 16684 | 27 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16657.00 t/16684.00, TF , w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 15.43
06/28/2020 | 16:00 | 16:30 | 0.5 | 16684 | 16738 | 54 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16684.00 t/16738.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 108.00
06/28/2020 | 16:30 | 17:10 | 0.67 | 16738 | 16738 | 0 | LAT | 5: BHA 5 (Lateral) | 8P | Rig Service.
06/28/2020 | 17:10 | 17:15 | 0.08 | 16738 | 16745 | 7 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16738.00 t/16745.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 84.00
06/28/2020 | 17:15 | 17:50 | 0.58 | 16745 | 16745 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate / Pump Repair
06/28/2020 | 17:50 | 18:00 | 0.17 | 16745 | 16751 | 6 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16745.00 t/16751.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 36.00
06/28/2020 | 18:00 | 19:30 | 1.5 | 16751 | 16766 | 15 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16751.00 t/16766.00, TF -170.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 10.00
06/28/2020 | 19:30 | 20:05 | 0.58 | 16766 | 16836 | 70 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16766.00 t/16836.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 120.00
06/28/2020 | 20:05 | 21:05 | 1 | 16836 | 16846 | 10 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/16836.00 t/16846.00, TF 180.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 10.00
06/28/2020 | 21:05 | 23:00 | 1.92 | 16846 | 17125 | 279 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/16846.00 t/17125.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 17000.00, ROP 145.57
06/28/2020 | 23:00 | 24:00 | 1 | 17125 | 17138 | 13 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/17125.00 t/17138.00, TF 80.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 17000.00, ROP 13.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_29_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/29/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9000 |  |  | Well Cost($): |  | 139500
|  |  |  | 24hr Summary: |  | Drill Lateral to TD 17886
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17138 |  | 10954 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 17886 |  | 17886 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 748 |  | 6932 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 46
Slide Drilled (Usft): |  | 34 |  | 852 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): |  | 714 |  | 6080 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 8.75 / 13.42 |  | 81.08 / 14.08 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  | 3.25 |  | 39.67 |  | SN: |  | 13430004 |  | 10s Gel: | 5 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 5.5 |  | 41.42 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 226.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 129.82 / 10.46 |  | 146.80 / 21.48 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 24 |  | 113 |  | Grade In: |  | 0-0
% Slide: |  | 4.55 |  | 12.29 |  | Grade Out: |  | 1-1
% Rotary: |  | 95.45 |  | 87.71 |  | Make / Model: |  | Halliburton / GTD64C
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Dean Day |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" - Halliburton GTD64C - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.1 |  | 33.7
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 35.98
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.85
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.29
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.63
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.5
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.59
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.16
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.39
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.55
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.86
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.85 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17145 | 91.8 | 334.5 | 10271.72 | 7245.14 | -2212.42 | 2.92 |  | 85.87 | 7502.07 | 0.21 |  | 2.92 | 96
17239 | 93.7 | 337.1 | 10267.21 | 7330.77 | -2250.9 | 3.42 |  | 53.75 | 7595.94 | 2.02 |  | 2.77 | 94
17333 | 95.1 | 337.3 | 10260 | 7417.17 | -2287.22 | 1.5 |  | 8.1 | 7689.59 | 1.49 |  | 0.21 | 94
17427 | 94.5 | 335.3 | 10252.13 | 7502.93 | -2324.87 | 2.21 |  | -106.67 | 7783.24 | -0.64 |  | -2.13 | 94
17522 | 92.2 | 333.4 | 10246.58 | 7588.41 | -2365.92 | 3.14 |  | -140.43 | 7878.06 | -2.42 |  | -2 | 95
17618 | 91.7 | 332.6 | 10243.31 | 7673.9 | -2409.48 | 0.98 |  | -122.01 | 7973.94 | -0.52 |  | -0.83 | 96
17712 | 92.1 | 332.5 | 10240.2 | 7757.27 | -2452.78 | 0.44 |  | -14.03 | 8067.8 | 0.43 |  | -0.11 | 94
17806 | 92.4 | 332.4 | 10236.51 | 7840.55 | -2496.23 | 0.34 |  | -18.42 | 8161.63 | 0.32 |  | -0.11 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 85.49 | 30 | 80 | 352 | 400 | 4850 | 4000 | 204 | 300 | 210 | 175 | 18000 | 3000
Run | 85.51 | 29.57 | 77.04 | 349 | 400 | 4661.7 | 3863.83 | 204 | 267.52 | 213.27 | 193.48 | 14407.41 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/29/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/29/2020 |  | 4 |  | 100 |  | 4 | 400
300-347?F |  |  |  |  | 06/29/2020 |  | 13 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 9000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/29/2020 | 00:00 | 01:00 | 1 | 17138 | 17147 | 9 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/17138.00 t/17147.00, TF 80.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 18000.00, ROP 9.00
06/29/2020 | 01:00 | 01:20 | 0.33 | 17147 | 17214 | 67 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17147.00 t/17214.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 18000.00, ROP 201.00
06/29/2020 | 01:20 | 01:35 | 0.25 | 17214 | 17214 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate while work on pump.
06/29/2020 | 01:35 | 03:00 | 1.42 | 17214 | 17410 | 196 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17214.00 t/17410.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 18000.00, ROP 138.35
06/29/2020 | 03:00 | 04:20 | 1.33 | 17410 | 17425 | 15 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/17410.00 t/17425.00, TF -140.00, w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 18000.00, ROP 11.25
06/29/2020 | 04:20 | 05:00 | 0.67 | 17425 | 17505 | 80 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17425.00 t/17505.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 18000.00, ROP 120.00
06/29/2020 | 05:00 | 05:55 | 0.92 | 17505 | 17515 | 10 | LAT | 5: BHA 5 (Lateral) | 2J | Slide Drill f/17505.00 t/17515.00, TF , w/WOB 30.00,Flow 400.00, Press 4850.00, Tq 18000.00, ROP 10.91
06/29/2020 | 05:55 | 09:00 | 3.08 | 17515 | 17886 | 371 | LAT | 5: BHA 5 (Lateral) | 2K | Rotary Drill f/17515.00 t/17886.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 4850.00, Tq 18000.00, ROP 120.32
06/29/2020 | 09:00 | 11:00 | 2 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate Sweep.
06/29/2020 | 11:00 | 12:00 | 1 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 3D | Back Ream out 10 stds F/17886 - T/16948
06/29/2020 | 12:00 | 13:30 | 1.5 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 3C | Wash & Ream to bottom F/16948 - T/17886
06/29/2020 | 13:30 | 16:30 | 3 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate Clean Up Cycles.
06/29/2020 | 16:30 | 20:30 | 4 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 3D | Back Ream F/17886 - T/15473
06/29/2020 | 20:30 | 22:10 | 1.67 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate.
06/29/2020 | 22:10 | 24:00 | 1.83 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_30_2020_DDR
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31136 / 20DD0219MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Longitude: |  | 96° 40' 26.068" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 06/30/2020 |  |  | Report Time: |  | 00:00-13:30
|  |  |  | Daily Cost($): |  | 9000 |  |  | Well Cost($): |  | 148500
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17886 |  | 10954 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 35 | PV: | 12
End Depth (Usft): |  | 17886 |  | 17886 |  | OD (in): |  |  |  | 300: | 23 | YP: | 11
Total Drilled (Usft): |  |  |  | 6932 |  | Weight (ft/lbs): |  |  |  | 200: | 18 | Viscosity: | 42
Slide Drilled (Usft): |  |  |  | 852 | [5 empty] | 100: | 13 | Chlorides: | 46500
Rotary Drilled (Usft): |  |  |  | 6080 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 5.60
Drlg/Circ Hrs: |  | 0.00 / 1.33 |  | 81.08 / 15.42 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water:
Slide Drilling Hrs: |  |  |  | 39.67 |  | SN: |  | 13430004 |  | 10s Gel: | 6 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  |  |  | 41.42 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 307.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 146.80 / 21.48 |  | OD (in) / TFA: |  | 6.750 / 1.178
BRT Hrs: |  | 12.25 |  | 125.25 |  | Grade In: |  | 0-0
% Slide: |  |  |  | 12.29 |  | Grade Out: |  | 1-1
% Rotary: |  |  |  | 87.71 |  | Make / Model: |  | Halliburton / GTD64C
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
James Dyer |  | Dean Day |  | Patrick Broussard |  | David Lablanc
Bobby Guin |  | Kody Grisham |  | John Brandon
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" - Halliburton GTD64C - TFA 1.18 |  |  |  | 6.75 | 2 |  |  |  |  | 0.6 |  | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | 5 | 2 |  |  |  |  | 33.1 |  | 33.7
BTI Valve |  |  |  | 4.75 | 2.563 |  |  |  |  | 2.28 |  | 35.98
NMPC |  |  |  | 5 | 2.688 |  |  |  |  | 9.87 |  | 45.85
UBHO |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.44 |  | 49.29
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 31 |  | 80.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 31.34 |  | 111.63
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.87 |  | 142.5
X/O- XT-39P x DS-42B |  |  |  | 5.25 | 2.688 |  |  |  |  | 3.09 |  | 145.59
27 Stands- 4 1/2" Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2608.57 |  | 2754.16
XO- Delta 425B x DS42P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.23 |  | 2757.39
NOV Shock Sub / Agitator / Safety Joint |  |  |  | 5.188 | 2.75 |  |  |  |  | 29.16 |  | 2786.55
XO- DS42B x Delta 425P |  |  |  | 5.25 | 2.563 |  |  |  |  | 3.31 |  | 2789.86
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.85 |  | 2 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30 | 80 | 352 | 400 | 4850 | 4000 | 204 | 300 | 210 | 175 | 18000 | 3000
Run | 85.51 | 29.57 | 77.04 | 349 | 400 | 4661.7 | 3863.83 | 204 | 267.52 | 213.27 | 193.48 | 14407.41 | 3000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 06/30/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 06/30/2020 |  | 4 |  | 100 |  | 4 | 400
300-347?F |  |  |  |  | 06/30/2020 |  | 13 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 9000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/30/2020 | 00:00 | 01:20 | 1.33 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 6B | POOH
06/30/2020 | 01:20 | 02:40 | 1.33 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 5A | Circulate
06/30/2020 | 02:40 | 03:50 | 1.17 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 6B | POOH
06/30/2020 | 03:50 | 04:00 | 0.17 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 6I | Flow Check
06/30/2020 | 04:00 | 11:00 | 7 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 6B | POOH L/D DP
06/30/2020 | 11:00 | 12:15 | 1.25 | 17886 | 17886 | 0 | LAT | 5: BHA 5 (Lateral) | 6P | L/D BHA 5
06/30/2020 | 12:15 | 13:30 | 1.25 | 17886 | 17886 | 0 | LAT |  | 24B | Load Truck for EOW.
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 398.60 (Usft)
Well: |  |  | Grand Canyon 1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | -0.28 / -0.24 (klbs)
Job #: |  |  | LTX1124720 | Bit #: |  |  | Wt. Below Jars (Air/Mud): |  | -0.28 / -0.24 (klbs)
Date In: |  |  | 04/28/2020 | Depth In: |  | 105 | Total Drilled: |  | 2900.00 (Usft)
Date Out: |  |  | 04/29/2020 | Depth Out: |  | 3005 | Drilling / Circ Hours: |  | 6.42 / 1.17
Survey Offset: |  |  | 0
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 49754 | 13 1/2 - Ulterra - SPL616 | 13.5 | 2 |  | 6 5/8 Reg |  | 1.5 | 1.5
| 2 | PPM800032 | 7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS | 8 | 2 | 1.43 | 6 5/8 Reg / 6 5/8 Reg |  | 38.4 | 39.9
| 3 | 603255 | 13 Stabilizer | 8.188 | 2.875 |  | 6 5/8 Reg / 6 5/8 Reg |  | 7.29 | 47.19
| 4 | 46071 | Pony Collar | 8.063 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 10.39 | 57.58
| 5 | ZSB775186 | 8 UBHO | 7.75 | 2.875 |  | 6 5/8 Reg / 6 5/8 Reg |  | 2.72 | 60.3
| 6 | 51269 | Drill Collar | 7.875 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 29.09 | 89.39
| 7 | 56067 | Drill Collar | 8.125 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 29.92 | 119.31
| 8 | 113667 | X/O 4 1/2 IFB x 6 5/8 RegP | 6.75 | 3.25 |  | 4 1/2 IF / 6 5/8 Reg |  | 2.61 | 121.92
| 9 | Rig-1 | 3 Stands HWDP | 6.5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 276.68 | 398.6
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | 13 1/2 - Ulterra - SPL616 | 1.35 | Baker Hughes | SPL616 | Green / RR |  | 2900
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS |  |  | PDCI / 7/8 5.9 | 6.37 / 1.50 |  | 13 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 0 |  |  | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS | 13 |  | 0 |  |  | 1.5

## BHA_2_Intermediate
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 580.23 (Usft)
Well: |  |  | Grand Canyon 1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | -0.28 / -0.24 (klbs)
Job #: |  |  | LTX1124720 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | -0.28 / -0.24 (klbs)
Date In: |  |  | 04/30/2020 | Depth In: |  | 3005 | Total Drilled: |  | 7330.00 (Usft)
Date Out: |  |  | 05/03/2020 | Depth Out: |  | 10335 | Drilling / Circ Hours: |  | 39.37 / 3.52
Survey Offset: |  |  | 70 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47857 | 9 7/8 - Ulterra - SPL613 | 9.875 | 2 |  | 6 5/8 Reg |  | 1.35 | 1.35
| 2 | PPM800001 | 7 3/4- 7/8 5.9 Stg 2.12? True Slick | 8 | 2 | 1.98 | 6 5/8 / 6 5/8 Reg |  | 37.48 | 38.83
| 3 | 46071 | Pony Collar | 8.063 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 10.39 | 49.22
| 4 | ZSB775186 | 8 UBHO | 7.75 | 2.875 |  | 6 5/8 Reg / 6 5/8 Reg |  | 2.72 | 51.94
| 5 | 51269 | Drill Collar | 7.875 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 29.09 | 81.03
| 6 | 56067 | Drill Collar | 8.125 | 3.25 |  | 6 5/8 Reg / 6 5/8 Reg |  | 29.92 | 110.95
| 7 | 117717 | X/O 4 1/2 XHB x 6 5/8 RegP | 6.813 | 2.938 |  | 4 1/2 XH / 6 5/8 Reg |  | 3.7 | 114.65
| 8 | Rig-2 | 2 Stands 6 1/2 DCs | 6.563 | 2.438 |  | 4 1/2 XH / 4 1/2 XH |  | 186.61 | 301.26
| 9 | 110280 | X/O 4 1/2 IFB x 4 1/2 XHP | 6.5 | 2.875 |  | 4 1/2 IF / 4 1/2 XH |  | 2.29 | 303.55
| 10 | Rig-1 | 3 Stands HWDP | 6.5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 276.68 | 580.23
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8 - Ulterra - SPL613 | 1.35 | Ulterra | SPL613 | Green |  | 7330
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4- 7/8 5.9 Stg 2.12? True Slick |  |  | PDCI / 7/8 5.9 | 5.87 / 2.12 |  | 0 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 0 |  |  | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3_Curve__Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2789.90 (Usft)
Well: |  |  | Grand Canyon 1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124720 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/22/2020 | Depth In: |  | 10335 | Total Drilled: |  | 527.00 (Usft)
Date Out: |  |  | 06/24/2020 | Depth Out: |  | 10862 | Drilling / Circ Hours: |  | 11.83 / 3.33
Survey Offset: |  |  | 67 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 39992 | 6 3/4 - Ulterra - U611S | 6.75 | 2 |  | 3 1/2 Reg |  | 0.6 | 0.6
| 2 | MTR500011 | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick | 5 | 2 | 4.875 / 1.98 | XT-39 / 3 1/2 Reg |  | 33.14 | 33.74
| 3 | 306844 | BTI Valve | 4.75 | 2.563 |  | XT-39 / XT-39 |  | 2.28 | 36.02
| 4 | 50-10-479 | NMPC | 5 | 2.688 |  | XT-39 / XT-39 |  | 9.87 | 45.89
| 5 | 500029 | UBHO | 5.25 | 2.563 |  | XT-39 / XT-39 |  | 3.44 | 49.33
| 6 | SD56287 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 31 | 80.33
| 7 | SD56283 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 31.34 | 111.67
| 8 | SD55819 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.87 | 142.54
| 9 | GT52331286 | X/O- XT-39P x DS-42B | 5.25 | 2.688 |  | DS-42 / XT-39 |  | 3.09 | 145.63
| 10 | Rig 5 | 27 Stands- 4 1/2" Drill Pipe | 4.5 | 2.5 |  | DS-42 / DS-42 |  | 2608.57 | 2754.2
| 11 | DR38846 | XO- Delta 425B x DS42P | 5.25 | 2.563 |  | Delta 425 / DS-42 |  | 3.23 | 2757.43
| 12 | 525-OD-007 | NOV Shock Sub / Agitator / Safety Joint | 5.188 | 2.75 |  | XT-39 / XT-39 |  | 29.16 | 2786.59
| 13 | DR38852 | XO- DS42B x Delta 425P | 5.25 | 2.563 |  | DS-42 / Delta 425 |  | 3.31 | 2789.9
Comments
Bit Info= 6 3/4 Security - U611S SN=39992 Jets=6-16 s TFA= 1.178 PN= U02278 Motor Info= 5 Inch, 6/7, 8.8 Stg. @ 2.00? w/ True Slick Bit To Bend= 4.05 Pad OD= 5 1/2 Rev / Gal= 0.68 Flow Range= 150-400 Gpm Max Diff=2,240
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4 - Ulterra - U611S | 1.18 | Ulterra | U611S | 0-0 | 1-1 | 527
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  | PDCI / 6/7 8.8 | 3.94 / 2.00 |  | 0 | 5.25 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 0 |  |  | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4_Bailout
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2782.90 (Usft)
Well: |  |  | Grand Canyon 1H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124720 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/24/2020 | Depth In: |  | 10862 | Total Drilled: |  | 92.00 (Usft)
Date Out: |  |  | 06/25/2020 | Depth Out: |  | 10954 | Drilling / Circ Hours: |  | 5.75 / 2.33
Survey Offset: |  |  | 62 | Gamma Offset: |  | 50
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 40962 | 6 3/4" - Ulterra - U611S | 6.75 | 2 |  | 3 1/2 Reg |  | 0.6 | 0.6
| 2 | MTR475076 | 7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick | 5 | 2 | 5.000 / 1.98 | XT-39 / 3 1/2 Reg |  | 26.14 | 26.74
| 3 | 306844 | BTI Valve | 4.75 | 2.563 |  | XT-39 / XT-39 |  | 2.28 | 29.02
| 4 | 50-10-479 | NMPC | 5 | 2.688 |  | XT-39 / XT-39 |  | 9.87 | 38.89
| 5 | 500029 | UBHO | 5.25 | 2.563 |  | XT-39 / XT-39 |  | 3.44 | 42.33
| 6 | SD56287 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 31 | 73.33
| 7 | SD56283 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 31.34 | 104.67
| 8 | SD55819 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.87 | 135.54
| 9 | GT52331286 | X/O- XT-39P x DS-42B | 5.25 | 2.688 |  | DS-42 / XT-39 |  | 3.09 | 138.63
| 10 | Rig 5 | 27 Stands- 4 1/2" Drill Pipe | 4.5 | 2.5 |  | DS-42 / DS-42 |  | 2608.57 | 2747.2
| 11 | DR38846 | XO- Delta 425B x DS42P | 5.25 | 2.563 |  | Delta 425 / DS-42 |  | 3.23 | 2750.43
| 12 | 525-OD-007 | NOV Shock Sub / Agitator / Safety Joint | 5.188 | 2.75 |  | XT-39 / XT-39 |  | 29.16 | 2779.59
| 13 | DR38852 | XO- DS42B x Delta 425P | 5.25 | 2.563 |  | DS-42 / Delta 425 |  | 3.31 | 2782.9
Comments
Bit Info= 6 3/4 Ultera - U611S SN=40962 Jets=4-16 s 1-18 1-12 TFA= 1.178 PN= U02278 Motor Info= 5 Inch, 7/8, 3.8 Stg. @ 2.50? w/ True Slick Bit To Bend= 4.00 Pad OD= 5 1/4 Rev / Gal= 0.521 Flow Range= 150-250 Gpm Max Diff=860
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4" - Ulterra - U611S | 1.14 | Baker Hughes | U611S | 0-0 | 0-1 | 92
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick |  |  | PDCI / 7/8 3.8 | 4.00 / 2.50 |  | 0 | 5.25 | 0 | 860
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
4450 |  |  | 0 | 0 |  |  | 0.521 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2789.86 (Usft)
Well: |  |  | Grand Canyon 1H | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1124720 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/25/2020 | Depth In: |  | 10954 | Total Drilled: |  | 6932.00 (Usft)
Date Out: |  |  | 06/30/2020 | Depth Out: |  | 17886 | Drilling / Circ Hours: |  | 81.08 / 15.42
Survey Offset: |  |  | 69 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13430004 | 6 3/4" - Halliburton GTD64C | 6.75 | 2 |  | 3 1/2 Reg |  | 0.6 | 0.6
| 2 | PPM250004 | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick | 5 | 2 | 5.000 / 1.94 | XT-39 / 3 1/2 Reg |  | 33.1 | 33.7
| 3 | 306844 | BTI Valve | 4.75 | 2.563 |  | XT-39 / XT-39 |  | 2.28 | 35.98
| 4 | 50-10-479 | NMPC | 5 | 2.688 |  | XT-39 / XT-39 |  | 9.87 | 45.85
| 5 | 500029 | UBHO | 5.25 | 2.563 |  | XT-39 / XT-39 |  | 3.44 | 49.29
| 6 | SD56287 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 31 | 80.29
| 7 | SD56283 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 31.34 | 111.63
| 8 | SD55819 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.87 | 142.5
| 9 | GT52331286 | X/O- XT-39P x DS-42B | 5.25 | 2.688 |  | DS-42 / XT-39 |  | 3.09 | 145.59
| 10 | Rig 5 | 27 Stands- 4 1/2" Drill Pipe | 4.5 | 2.5 |  | DS-42 / DS-42 |  | 2608.57 | 2754.16
| 11 | DR38846 | XO- Delta 425B x DS42P | 5.25 | 2.563 |  | Delta 425 / DS-42 |  | 3.23 | 2757.39
| 12 | 525-OD-007 | NOV Shock Sub / Agitator / Safety Joint | 5.188 | 2.75 |  | XT-39 / XT-39 |  | 29.16 | 2786.55
| 13 | DR38852 | XO- DS42B x Delta 425P | 5.25 | 2.563 |  | DS-42 / Delta 425 |  | 3.31 | 2789.86
Comments
Bit Info= 6 3/4 Halliburton - GTD64C SN=13430004 Jets=6-16s TFA= 1.178 Motor Info= 5 Inch, 6/7, 8.8 Stg. @ 2.00? w/ True Slick Bit To Bend= 3.85 Pad OD= 5 9/16 Rev / Gal= 0.68 Flow Range= 150-400 Gpm Max Diff=2,240
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4" - Halliburton GTD64C | 1.18 | Halliburton | GTD64C | 0-0 | 1-1 | 6932
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  | PDCI / 6/7 8.8 | 3.85 / 2.00 |  | 0 | 5.56 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 0 |  |  | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Longitude: |  | 96° 40' 26.068" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 04/28/2020 18:00 |  | SN: |  | PPM800032 |  |  |  | WOB Rotate (klbs): |  | 9.00
Date Out: |  | 04/29/2020 07:30 |  | Description: |  | 7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 105.00 / 3005.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 93.50
Inc In/Out: |  | 0.38 / 11.05 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 781.62
Azi In/Out: |  | 325.00 / 35.67 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 1538.85
Total Drilled (Usft): |  | 2900 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1864.81
%Slide (Ftg): |  | 7.03 |  | Bit to Bend (Usft): |  | 6.37 |  |  |  | Tq On Btm (kftlbs): |  | 6872.5
%Slide (Time): |  | 34.60 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs): |  | 1200
Slide Drilled (Usft): |  | 204 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 2.22 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.97 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Baker Hughes
%Rotary (Time): |  | 65.45 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL616
Rotary Drilled (Usft): |  | 2696 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 13.5
Rotary Hours: |  | 4.2 |  | Length (Usft): |  | 38.4 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 6.42 |  | Integral Float: |  | YES |  |  |  | Bit #
Circ/BRT Hrs: |  | 1.17 / 13.50 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | Green / RR
Slide ROP (Usft/hr): |  | 91.89 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 641.9 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 6.42
Avg ROP (Usft/hr): |  | 451.71 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 1.17
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
5 / 3 | 2 / 1 | 1 / 1 |  |  |  | 2 | 1 | 9.2 | 400 | WBM | 6.4 | 0.25 | 110
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
0.00 / 1.70
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
13 1/2 - Ulterra - SPL616 1.35 |  |  |  | 49754 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
7 3/4- 7/8 5.9 Stg 1.5? w/ 13 NBS 0.00 |  |  |  | PPM800032 |  | 8 | 2 |  |  |  | 38.4 | 39.9
13 Stabilizer 0.00 |  |  |  | 603255 |  | 8.188 | 2.875 |  |  |  | 7.29 | 47.19
Pony Collar 0.00 |  |  |  | 46071 |  | 8.063 | 3.25 |  |  |  | 10.39 | 57.58
8 UBHO 0.00 |  |  |  | ZSB775186 |  | 7.75 | 2.875 |  |  |  | 2.72 | 60.3
Drill Collar 0.00 |  |  |  | 51269 |  | 7.875 | 3.25 |  |  |  | 29.09 | 89.39
Drill Collar 0.00 |  |  |  | 56067 |  | 8.125 | 3.25 |  |  |  | 29.92 | 119.31
X/O 4 1/2 IFB x 6 5/8 RegP 0.00 |  |  |  | 113667 |  | 6.75 | 3.25 |  |  |  | 2.61 | 121.92
3 Stands HWDP -1.00 |  |  |  | Rig-1 |  | 6.5 | 3 |  |  |  | 276.68 | 398.6
Additional Comments
BHA performed as expected, drilled surface section per plan #1. At surface, motor drained strong with minimual slack in bearing assembly. No sisuable signs of damage to BHA at surface. Bit grade was green. Drilled three surface sections with BHA. Was subject to 100? water base spud mud.
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Longitude: |  | 96° 40' 26.068" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 04/30/2020 21:15 |  | SN: |  | PPM800001 |  |  |  | WOB Rotate (klbs): |  | 31.00
Date Out: |  | 05/03/2020 12:40 |  | Description: |  | 7 3/4- 7/8 5.9 Stg 2.12? True Slick |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 3005.00 / 10335.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 79.09
Inc In/Out: |  | 11.05 / 20.34 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 742.63
Azi In/Out: |  | 35.67 / 334.67 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 3011.51
Total Drilled (Usft): |  | 7330 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 3521.83
%Slide (Ftg): |  | 9.66 |  | Bit to Bend (Usft): |  | 5.87 |  |  |  | Tq On Btm (kftlbs): |  | 12909.09
%Slide (Time): |  | 57.71 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 3000
Slide Drilled (Usft): |  | 708 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 22.72 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 90.34 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 42.29 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6622 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 9.875
Rotary Hours: |  | 16.65 |  | Length (Usft): |  | 37.48 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 39.37 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 3.52 / 63.42 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | Green
Slide ROP (Usft/hr): |  | 31.16 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 397.72 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 39.37
Avg ROP (Usft/hr): |  | 186.18 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.52
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
36 / 24 | 18 / 13 | 7 / 6 |  |  |  | 14 | 10 | 9.6 | 56000 | OBM | 11 | 0.25 | 219
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
70 | 60 | [10 empty] | 0.00 / 6.26
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8 - Ulterra - SPL613 1.35 |  |  |  | 47857 |  | 9.875 | 2 |  |  |  | 1.35 | 1.35
7 3/4- 7/8 5.9 Stg 2.12? True Slick 0.00 |  |  |  | PPM800001 |  | 8 | 2 |  |  |  | 37.48 | 38.83
Pony Collar 0.00 |  |  |  | 46071 |  | 8.063 | 3.25 |  |  |  | 10.39 | 49.22
8 UBHO 0.00 |  |  |  | ZSB775186 |  | 7.75 | 2.875 |  |  |  | 2.72 | 51.94
Drill Collar 0.00 |  |  |  | 51269 |  | 7.875 | 3.25 |  |  |  | 29.09 | 81.03
Drill Collar 0.00 |  |  |  | 56067 |  | 8.125 | 3.25 |  |  |  | 29.92 | 110.95
X/O 4 1/2 XHB x 6 5/8 RegP 0.00 |  |  |  | 117717 |  | 6.813 | 2.938 |  |  |  | 3.7 | 114.65
2 Stands 6 1/2 DCs 0.00 |  |  |  | Rig-2 |  | 6.563 | 2.438 |  |  |  | 186.61 | 301.26
X/O 4 1/2 IFB x 4 1/2 XHP 0.00 |  |  |  | 110280 |  | 6.5 | 2.875 |  |  |  | 2.29 | 303.55
3 Stands HWDP -1.00 |  |  |  | Rig-1 |  | 6.5 | 3 |  |  |  | 276.68 | 580.23
Additional Comments
BHA performed as expected. Held 12? tangent until 7900, then dropped back vertical, built 20? once we seen chalk marker, pulled out of hole to run intermediate casing. At surface, bearing gap was with in tollerance, drained strong with minimual side to side play in bit box. No visuable signs of damage to motor at surface. Bit graded 1/1. Max temp. 226.0?
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Longitude: |  | 96° 40' 26.068" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Build Rates |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Jonathan Moore |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 06/22/2020 24:00 |  | SN: |  | MTR500011 |  |  |  | WOB Rotate (klbs): |  | 22.00
Date Out: |  | 06/24/2020 06:45 |  | Description: |  | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10335.00 / 10862.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 20.35 / 73.44 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 247
Azi In/Out: |  | 334.66 / 336.42 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 1950
Total Drilled (Usft): |  | 527 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 2100
%Slide (Ftg): |  | 78.37 |  | Bit to Bend (Usft): |  | 3.94 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 85.86 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 3000
Slide Drilled (Usft): |  | 413 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 10.16 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 21.63 |  | Kickpad OD (in): |  | 5.25 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 14.11 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | U611S
Rotary Drilled (Usft): |  | 114 |  | Fishneck OD (in): |  | 4.875 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 1.67 |  | Length (Usft): |  | 33.14 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 11.83 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 3.33 / 30.75 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | 0-0
Slide ROP (Usft/hr): |  | 40.65 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1
Rot ROP (Usft/hr): |  | 68.26 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 11.83
Avg ROP (Usft/hr): |  | 44.55 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.33
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 15 / 11 | 6 / 5 |  |  |  | 10 | 10 | 8.9 | 48000 | OBM | 5.7 |  | 243
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
67 | 57 | [10 empty] | 0.00 / 18.11
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4 - Ulterra - U611S 1.18 |  |  |  | 39992 |  | 6.75 | 2 |  |  |  | 0.6 | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick 0.00 |  |  |  | MTR500011 |  | 5 | 2 |  |  |  | 33.14 | 33.74
BTI Valve 0.00 |  |  |  | 306844 |  | 4.75 | 2.563 |  |  |  | 2.28 | 36.02
NMPC 0.00 |  |  |  | 50-10-479 |  | 5 | 2.688 |  |  |  | 9.87 | 45.89
UBHO 0.00 |  |  |  | 500029 |  | 5.25 | 2.563 |  |  |  | 3.44 | 49.33
NMDC 0.00 |  |  |  | SD56287 |  | 4.938 | 2.75 |  |  |  | 31 | 80.33
NMDC 0.00 |  |  |  | SD56283 |  | 5 | 2.75 |  |  |  | 31.34 | 111.67
NMDC 0.00 |  |  |  | SD55819 |  | 4.938 | 2.75 |  |  |  | 30.87 | 142.54
X/O- XT-39P x DS-42B 0.00 |  |  |  | GT52331286 |  | 5.25 | 2.688 |  |  |  | 3.09 | 145.63
27 Stands- 4 1/2" Drill Pipe 0.00 |  |  |  | Rig 5 |  | 4.5 | 2.5 |  |  |  | 2608.57 | 2754.2
XO- Delta 425B x DS42P 0.00 |  |  |  | DR38846 |  | 5.25 | 2.563 |  |  |  | 3.23 | 2757.43
NOV Shock Sub / Agitator / Safety Joint 0.00 |  |  |  | 525-OD-007 |  | 5.188 | 2.75 |  |  |  | 29.16 | 2786.59
XO- DS42B x Delta 425P 0.00 |  |  |  | DR38852 |  | 5.25 | 2.563 |  |  |  | 3.31 | 2789.9
Additional Comments
Motor self drained some above rotary and drained remainder of fluidl in rotary. No visible wash or wear with minimal slack. Bit was green graded 1-1 with one missing jet.
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Longitude: |  | 96° 40' 26.068" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Lay Out BR / ST BHA |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Jonathan Moore |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 06/24/2020 07:15 |  | SN: |  | MTR475076 |  |  |  | WOB Rotate (klbs): |  | 23.00
Date Out: |  | 06/25/2020 05:15 |  | Description: |  | 7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10862.00 / 10954.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 58.57
Inc In/Out: |  | 73.47 / 88.74 |  | Model: |  | 7/8 3.8 |  |  |  | Flow Rate (gpm): |  | 400
Azi In/Out: |  | 336.41 / 333.29 |  | Lobes / Stages: |  | 7/8 / 3.80 |  |  |  | Off Btm Press (psi): |  | 3800
Total Drilled (Usft): |  | 92 |  | Bend Angle: |  | 2.5 |  |  |  | On Btm Press (psi): |  | 4233.33
%Slide (Ftg): |  | 100.00 |  | Bit to Bend (Usft): |  | 4 |  |  |  | Tq On Btm (kftlbs): |  | 10000
%Slide (Time): |  | 100.00 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 3000
Slide Drilled (Usft): |  | 92 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 5.75 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 0.00 |  | Kickpad OD (in): |  | 5.25 |  |  |  | Make: |  | Baker Hughes
%Rotary (Time): |  | 0.00 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | U611S
Rotary Drilled (Usft): |  | 0 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0 |  | Length (Usft): |  | 26.14 |  |  |  | TFA: |  | 1.14
Total Drlg Hrs: |  | 5.75 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 2.33 / 22.00 |  | Rev per Gal: |  | 0.521 |  |  |  | Grade In: |  | 0-0
Slide ROP (Usft/hr): |  | 16 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1
Rot ROP (Usft/hr): |  | 0 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 5.75
Avg ROP (Usft/hr): |  | 16 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.33
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 15 / 11 | 6 / 5 |  |  |  | 10 | 10 | 8.9 | 48000 | OBM | 5.7 |  | 262
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
62 | 50 | [10 empty] | 0.00 / 18.11
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4" - Ulterra - U611S 1.14 |  |  |  | 40962 |  | 6.75 | 2 |  |  |  | 0.6 | 0.6
7/8 Lobe 3.8 Stage @ 2.5? w/ True Slick 0.00 |  |  |  | MTR475076 |  | 5 | 2 |  |  |  | 26.14 | 26.74
BTI Valve 0.00 |  |  |  | 306844 |  | 4.75 | 2.563 |  |  |  | 2.28 | 29.02
NMPC 0.00 |  |  |  | 50-10-479 |  | 5 | 2.688 |  |  |  | 9.87 | 38.89
UBHO 0.00 |  |  |  | 500029 |  | 5.25 | 2.563 |  |  |  | 3.44 | 42.33
NMDC 0.00 |  |  |  | SD56287 |  | 4.938 | 2.75 |  |  |  | 31 | 73.33
NMDC 0.00 |  |  |  | SD56283 |  | 5 | 2.75 |  |  |  | 31.34 | 104.67
NMDC 0.00 |  |  |  | SD55819 |  | 4.938 | 2.75 |  |  |  | 30.87 | 135.54
X/O- XT-39P x DS-42B 0.00 |  |  |  | GT52331286 |  | 5.25 | 2.688 |  |  |  | 3.09 | 138.63
27 Stands- 4 1/2" Drill Pipe 0.00 |  |  |  | Rig 5 |  | 4.5 | 2.5 |  |  |  | 2608.57 | 2747.2
XO- Delta 425B x DS42P 0.00 |  |  |  | DR38846 |  | 5.25 | 2.563 |  |  |  | 3.23 | 2750.43
NOV Shock Sub / Agitator / Safety Joint 0.00 |  |  |  | 525-OD-007 |  | 5.188 | 2.75 |  |  |  | 29.16 | 2779.59
XO- DS42B x Delta 425P 0.00 |  |  |  | DR38852 |  | 5.25 | 2.563 |  |  |  | 3.31 | 2782.9
Additional Comments
Motor performed well with no issues on bailout run. Motor self drained some above rotary and drained remainder of fluid in rotary with minimal slack. No visible signs of wash or wear. Bit graded 0-1 with one chipped cutter on shoulder.
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1124720 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31136 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 46.347" N |  |  | Well: |  | Grand Canyon 1H
|  |  |  | Longitude: |  | 96° 40' 26.068" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Dean Day |  |  | Company Man: |  | James Dyer
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 06/25/2020 07:00 |  | SN: |  | PPM250004 |  |  |  | WOB Rotate (klbs): |  | 29.00
Date Out: |  | 06/30/2020 12:15 |  | Description: |  | 6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10954.00 / 17886.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 77.04
Inc In/Out: |  | 88.77 / 92.40 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 400
Azi In/Out: |  | 333.28 / 332.40 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 3863.83
Total Drilled (Usft): |  | 6932 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4661.7
%Slide (Ftg): |  | 12.29 |  | Bit to Bend (Usft): |  | 3.85 |  |  |  | Tq On Btm (kftlbs): |  | 14407.41
%Slide (Time): |  | 48.94 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 3000
Slide Drilled (Usft): |  | 852 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 39.68 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 87.71 |  | Kickpad OD (in): |  | 5.563 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 51.06 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64C
Rotary Drilled (Usft): |  | 6080 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 41.4 |  | Length (Usft): |  | 33.1 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 81.08 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 15.42 / 125.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | 0-0
Slide ROP (Usft/hr): |  | 21.47 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1
Rot ROP (Usft/hr): |  | 146.86 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 81.08
Avg ROP (Usft/hr): |  | 85.5 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 15.42
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
35 / 23 | 18 / 13 | 7 / 6 |  |  |  | 12 | 11 | 8.9 | 46500 | OBM | 5.6 |  | 315
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 57 | [10 empty] | 0.00 / 16.60
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4" - Halliburton GTD64C 1.18 |  |  |  | 13430004 |  | 6.75 | 2 |  |  |  | 0.6 | 0.6
6/7 Lobe 8.8 Stage @ 2.00? w/ True Slick 0.00 |  |  |  | PPM250004 |  | 5 | 2 |  |  |  | 33.1 | 33.7
BTI Valve 0.00 |  |  |  | 306844 |  | 4.75 | 2.563 |  |  |  | 2.28 | 35.98
NMPC 0.00 |  |  |  | 50-10-479 |  | 5 | 2.688 |  |  |  | 9.87 | 45.85
UBHO 0.00 |  |  |  | 500029 |  | 5.25 | 2.563 |  |  |  | 3.44 | 49.29
NMDC 0.00 |  |  |  | SD56287 |  | 4.938 | 2.75 |  |  |  | 31 | 80.29
NMDC 0.00 |  |  |  | SD56283 |  | 5 | 2.75 |  |  |  | 31.34 | 111.63
NMDC 0.00 |  |  |  | SD55819 |  | 4.938 | 2.75 |  |  |  | 30.87 | 142.5
X/O- XT-39P x DS-42B 0.00 |  |  |  | GT52331286 |  | 5.25 | 2.688 |  |  |  | 3.09 | 145.59
27 Stands- 4 1/2" Drill Pipe 0.00 |  |  |  | Rig 5 |  | 4.5 | 2.5 |  |  |  | 2608.57 | 2754.16
XO- Delta 425B x DS42P 0.00 |  |  |  | DR38846 |  | 5.25 | 2.563 |  |  |  | 3.23 | 2757.39
NOV Shock Sub / Agitator / Safety Joint 0.00 |  |  |  | 525-OD-007 |  | 5.188 | 2.75 |  |  |  | 29.16 | 2786.55
XO- DS42B x Delta 425P 0.00 |  |  |  | DR38852 |  | 5.25 | 2.563 |  |  |  | 3.31 | 2789.86
Additional Comments
Max BHT 315? F - This assembly did not track well at all throughout the lateral, requiring a significant amount of sliding. Fortunately, slides yielded great for the most part with MY averaging 15?/100. Sliding did slow considerably towards the latter part of the well, but still maintained around 15 fph average sliding. Rotating ROP slowed down as well, as we were restricted by torqued (18K). Overall, a good run. Motor self drained above rotary completely. Half inch of slack. Bit graded 1-1 with one missing cutter on nose.
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #1 (Surface) |  |  |  |  | RKB: |  |  |  | 332 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2897
Site: |  |  |  |  | Grand Canyon-Levi Goodrich - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 204
Well Name: |  |  |  |  | Grand Canyon 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 0.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 332 |  | VS Azimuth: |  | 335.04 |  | Rotate: |  | 2693
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
04/28/2020 | 18:00 | 18:02 | 0.033333 | 108 | 214 | 106 | Rotate |  | 138 | 0.5 | 325 | 138 | 0.49 | -0.35 | 0.49 | 0.36 |  |  | 8 | 40 | 498 | 2800 | 3179.99 | 520 | 430 | 90 | 70 | 60 | 60 | 60
04/28/2020 | 18:04 | 18:14 | 0.16667 | 214 | 307 | 93 | Rotate |  | 231 | 0.6 | 307.6 | 230.99 | 1.12 | -0.96 | 1.12 | 0.21 |  |  | 8 | 60 | 581 | 2800 | 558 | 675 | 650 | 25 | 70 | 60 | 60 | 60
04/28/2020 | 18:20 | 18:34 | 0.23333 | 307 | 398 | 91 | Rotate |  | 322 | 0.5 | 315.4 | 321.99 | 1.7 | -1.62 | 1.7 | 0.14 |  |  | 8 | 60 | 680 | 2800 | 390 | 675 | 650 | 25 | 70 | 60 | 60 | 60
04/28/2020 | 19:00 | 19:09 | 0.15 | 398 | 492 | 94 | Rotate |  | 416 | 0.4 | 313.9 | 415.99 | 2.22 | -2.14 | 2.22 | 0.11 |  |  | 8 | 80 | 680 | 3500 | 626.67 | 1650 | 1580 | 70 | 75 | 60 | 60 | 60
04/28/2020 | 19:14 | 19:18 | 0.066667 | 492 | 587 | 95 | Rotate |  | 511 | 0.4 | 319.5 | 510.98 | 2.7 | -2.6 | 2.7 | 0.04 |  |  | 8 | 80 | 819 | 3500 | 1425 | 1650 | 1580 | 70 | 75 | 60 | 60 | 60
04/28/2020 | 19:23 | 19:27 | 0.066667 | 587 | 681 | 94 | Rotate |  | 605 | 0.6 | 284.8 | 604.98 | 3.07 | -3.29 | 3.07 | 0.38 |  |  | 8 | 80 | 819 | 3500 | 1410 | 1650 | 1580 | 70 | 75 | 60 | 60 | 60
04/28/2020 | 19:31 | 19:37 | 0.1 | 681 | 775 | 94 | Rotate |  | 699 | 0.4 | 287.6 | 698.98 | 3.3 | -4.08 | 3.3 | 0.21 |  |  | 8 | 80 | 819 | 3500 | 940 | 1650 | 1580 | 70 | 85 | 60 | 60 | 60
04/28/2020 | 19:41 | 19:47 | 0.1 | 775 | 868 | 93 | Rotate |  | 792 | 0.4 | 258.2 | 791.98 | 3.33 | -4.7 | 3.33 | 0.22 |  |  | 8 | 80 | 819 | 3500 | 930 | 1650 | 1580 | 70 | 85 | 60 | 60 | 60
04/28/2020 | 19:52 | 19:56 | 0.066667 | 868 | 878 | 10 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 150 | 1650 | 1580 | 70 | 95 | 60 | 60 | 60
04/28/2020 | 19:56 | 20:01 | 0.083333 | 878 | 890 | 12 | Slide | 0 | 887 | 0.4 | 6.5 | 886.97 | 3.59 | -4.99 | 3.59 | 0.68 |  |  | 8 |  | 819 | 3500 | 144 | 1650 | 1580 | 70 | 95 | 60 | 60 | 60
04/28/2020 | 20:01 | 20:06 | 0.083333 | 890 | 963 | 73 | Rotate | Drilling Parameters WOB: 8; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 876 | 1650 | 1580 | 70 | 95 | 60 | 60 | 60
04/28/2020 | 20:11 | 20:17 | 0.1 | 963 | 1057 | 94 | Rotate |  | 981 | 0.8 | 26.9 | 980.97 | 4.5 | -4.66 | 4.5 | 0.48 |  |  | 10 | 100 | 819 | 3500 | 940 | 1650 | 1580 | 70 | 95 | 60 | 60 | 60
04/28/2020 | 20:22 | 20:26 | 0.066667 | 1057 | 1152 | 95 | Rotate |  | 1076 | 0.6 | 33.2 | 1075.96 | 5.51 | -4.08 | 5.51 | 0.23 |  |  | 10 | 100 | 819 | 3500 | 1425 | 1650 | 1580 | 70 | 99 | 60 | 60 | 60
04/28/2020 | 20:30 | 20:34 | 0.066667 | 1152 | 1167 | 15 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 225 | 1650 | 1580 | 70 | 99 | 60 | 60 | 60
04/28/2020 | 20:34 | 20:40 | 0.1 | 1167 | 1178 | 11 | Slide | 0 | 1170 | 1 | 35.2 | 1169.95 | 6.59 | -3.34 | 6.59 | 0.43 |  |  | 10 |  | 819 | 3500 | 110 | 1650 | 1580 | 70 | 99 | 60 | 60 | 60
04/28/2020 | 20:40 | 20:45 | 0.083333 | 1178 | 1246 | 68 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 816 | 1650 | 1580 | 70 | 99 | 60 | 60 | 60
04/28/2020 | 20:49 | 20:54 | 0.083333 | 1246 | 1340 | 94 | Rotate |  | 1264 | 1.4 | 35.9 | 1263.93 | 8.19 | -2.2 | 8.19 | 0.43 |  |  | 10 | 100 | 819 | 5500 | 1128 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:00 | 21:04 | 0.066667 | 1340 | 1435 | 95 | Rotate |  | 1359 | 1.6 | 41.3 | 1358.9 | 10.13 | -0.64 | 10.13 | 0.26 |  |  | 10 | 100 | 819 | 5500 | 1425 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:09 | 21:11 | 0.033333 | 1435 | 1445 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 5500; Drilling Parameters ROP: 300 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:11 | 21:18 | 0.11667 | 1445 | 1460 | 15 | Slide | 0 | 1453 | 2 | 41.2 | 1452.85 | 12.35 | 1.31 | 12.35 | 0.43 |  |  | 10 |  | 819 | 5500 | 128.57 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:18 | 21:23 | 0.083333 | 1460 | 1529 | 69 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 5500; Drilling Parameters ROP: 828 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:25 | 21:31 | 0.1 | 1529 | 1623 | 94 | Rotate |  | 1547 | 2.4 | 34.2 | 1546.78 | 15.21 | 3.49 | 15.21 | 0.51 |  |  | 10 | 100 | 819 | 8000 | 940 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:34 | 21:43 | 0.15 | 1623 | 1717 | 94 | Rotate |  | 1641 | 2.5 | 30.6 | 1640.7 | 18.6 | 5.64 | 18.6 | 0.2 |  |  | 10 | 100 | 819 | 8000 | 626.67 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:48 | 21:53 | 0.083333 | 1717 | 1812 | 95 | Rotate |  | 1736 | 2.5 | 33.3 | 1735.61 | 22.12 | 7.84 | 22.12 | 0.12 |  |  | 10 | 100 | 819 | 8000 | 1140 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 21:57 | 22:02 | 0.083333 | 1812 | 1906 | 94 | Rotate |  | 1830 | 2.4 | 24.3 | 1829.52 | 25.63 | 9.77 | 25.63 | 0.42 |  |  | 10 | 100 | 819 | 8000 | 1128 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 22:06 | 22:12 | 0.1 | 1906 | 2000 | 94 | Rotate |  | 1924 | 2.8 | 23.6 | 1923.42 | 29.52 | 11.5 | 29.52 | 0.43 |  |  | 10 | 100 | 819 | 8000 | 940 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 22:24 | 22:43 | 0.31667 | 2000 | 2094 | 94 | Rotate |  | 2018 | 2.6 | 24.2 | 2017.32 | 33.57 | 13.29 | 33.57 | 0.21 |  |  | 10 | 100 | 819 | 8000 | 296.84 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 22:45 | 22:48 | 0.05 | 2094 | 2104 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 200 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 22:48 | 22:55 | 0.11667 | 2104 | 2114 | 10 | Slide | 0 | 2111 | 2.9 | 26.4 | 2110.21 | 37.6 | 15.2 | 37.6 | 0.34 |  |  | 10 |  | 819 | 8000 | 85.71 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 22:55 | 23:02 | 0.11667 | 2114 | 2187 | 73 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 625.71 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 23:05 | 23:07 | 0.033333 | 2187 | 2197 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 300 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 23:07 | 23:18 | 0.18333 | 2197 | 2212 | 15 | Slide | 0 | 2206 | 3.7 | 31.9 | 2205.05 | 42.36 | 17.89 | 42.36 | 0.9 |  |  | 10 |  | 819 | 10000 | 81.82 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 23:18 | 23:21 | 0.05 | 2212 | 2282 | 70 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 1400 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 23:25 | 23:28 | 0.05 | 2282 | 2292 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 200 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 23:28 | 23:36 | 0.13333 | 2292 | 2307 | 15 | Slide | 0 | 2299 | 4.4 | 33.6 | 2297.82 | 47.88 | 21.45 | 47.88 | 0.76 |  |  | 10 |  | 819 | 10000 | 112.5 | 2100 | 1650 | 450 | 100 | 85 | 85 | 85
04/28/2020 | 23:36 | 23:44 | 0.13333 | 2307 | 2375 | 68 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 510 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/28/2020 | 23:48 | 23:50 | 0.033333 | 2375 | 2383 | 8 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 240 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/28/2020 | 23:50 | 24:00 | 0.16667 | 2383 | 2403 | 20 | Slide | 0 | 2393 | 5.5 | 38.6 | 2391.47 | 54.4 | 26.26 | 54.4 | 1.26 |  |  | 10 |  | 819 | 10000 | 120 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:00 | 00:10 | 0.16667 | 2403 | 2469 | 66 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 396 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:12 | 00:16 | 0.066667 | 2469 | 2480 | 11 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 165 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:16 | 00:30 | 0.23333 | 2480 | 2503 | 23 | Slide | 0 | 2487 | 6.7 | 39.3 | 2484.94 | 62.17 | 32.54 | 62.17 | 1.28 |  |  | 10 |  | 819 | 10000 | 98.57 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:30 | 00:38 | 0.13333 | 2503 | 2563 | 60 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 450 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:42 | 00:45 | 0.05 | 2563 | 2568 | 5 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 100 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:45 | 00:54 | 0.15 | 2568 | 2578 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 66.67 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 00:54 | 01:02 | 0.13333 | 2578 | 2657 | 79 | Rotate |  | 2581 | 7.9 | 39.5 | 2578.17 | 71.39 | 40.12 | 71.39 | 1.28 |  |  | 10 | 100 | 819 | 10000 | 592.5 | 2100 | 1650 | 450 | 101 | 85 | 85 | 85
04/29/2020 | 01:06 | 01:23 | 0.28333 | 2657 | 2685 | 28 | Slide | 0 | 2675 | 8.7 | 36.8 | 2671.19 | 82.07 | 48.49 | 82.07 | 0.95 |  |  | 10 |  | 819 | 10000 | 98.82 | 2100 | 1650 | 450 | 101 | 120 | 115 | 105
04/29/2020 | 01:23 | 01:28 | 0.083333 | 2685 | 2751 | 66 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 792 | 2450 | 1900 | 550 | 107 | 120 | 115 | 105
04/29/2020 | 01:32 | 01:52 | 0.33333 | 2751 | 2781 | 30 | Slide | 0 | 2769 | 10.3 | 36.4 | 2763.9 | 94.53 | 57.74 | 94.53 | 1.7 |  |  | 10 |  | 819 | 10000 | 90 | 2450 | 1900 | 550 | 107 | 120 | 115 | 105
04/29/2020 | 01:52 | 01:58 | 0.1 | 2781 | 2845 | 64 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 819; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 640 | 2450 | 1900 | 550 | 107 | 120 | 115 | 105
04/29/2020 | 02:02 | 02:22 | 0.33333 | 2845 | 2860 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 450; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 45 | 1100 | 850 | 250 | 107 | 120 | 115 | 105
04/29/2020 | 02:22 | 02:37 | 0.25 | 2860 | 2939 | 79 | Rotate |  | 2929 | 11.3 | 36.1 | 2921.06 | 118.71 | 75.46 | 118.71 | 0.63 |  |  | 10 | 100 | 450 | 10000 | 316 | 1100 | 850 | 250 | 110 | 120 | 115 | 105
04/29/2020 | 02:40 | 02:55 | 0.25 | 2939 | 3005 | 66 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 450; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 264 | 1100 | 850 | 250 | 110 | 120 | 115 | 105

## BHA_2_Intermediate_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #2 (Intermediate) |  |  |  |  | RKB: |  |  |  | 332 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7330
Site: |  |  |  |  | Grand Canyon-Levi Goodrich - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 708
Well Name: |  |  |  |  | Grand Canyon 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 70.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 332 |  | VS Azimuth: |  | 335.04 |  | Rotate: |  | 6622
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/01/2020 | 02:50 | 02:55 | 0.083333 | 3005 | 3015 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 120 | 750 | 750 | 0 | 105 | 130 | 125 | 120
05/01/2020 | 03:45 | 04:00 | 0.25 | 3015 | 3120 | 105 | Rotate |  | 3050 | 10.9 | 35.4 | 3039.8 | 137.61 | 89.08 | 137.61 | 0.35 |  |  | 10 | 60 | 500 | 6000 | 420 | 1000 | 1000 | 0 | 105 | 130 | 125 | 120
05/01/2020 | 04:05 | 04:11 | 0.1 | 3120 | 3214 | 94 | Rotate |  | 3144 | 10.6 | 33.2 | 3132.15 | 152.09 | 98.96 | 152.09 | 0.54 |  |  | 10 | 70 | 730 | 9000 | 940 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 04:15 | 04:23 | 0.13333 | 3214 | 3226 | 12 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 75; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 90 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 04:23 | 04:30 | 0.11667 | 3226 | 3234 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 68.57 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 04:30 | 04:38 | 0.13333 | 3234 | 3309 | 75 | Rotate |  | 3239 | 12.3 | 31.8 | 3225.25 | 168 | 109.08 | 168 | 1.81 |  |  | 18 | 75 | 730 | 9000 | 562.5 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 04:43 | 04:51 | 0.13333 | 3309 | 3403 | 94 | Rotate |  | 3333 | 12.8 | 31.5 | 3317.01 | 185.39 | 119.79 | 185.39 | 0.54 |  |  | 25 | 75 | 730 | 9000 | 705 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 04:55 | 05:03 | 0.13333 | 3403 | 3497 | 94 | Rotate |  | 3427 | 13.1 | 30.9 | 3408.62 | 203.41 | 130.7 | 203.41 | 0.35 |  |  | 25 | 75 | 730 | 9000 | 705 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 05:08 | 05:18 | 0.16667 | 3497 | 3591 | 94 | Rotate |  | 3521 | 13.2 | 29.4 | 3500.15 | 221.9 | 141.44 | 221.9 | 0.38 |  |  | 25 | 75 | 730 | 9000 | 564 | 3000 | 2550 | 450 | 105 | 130 | 125 | 120
05/01/2020 | 05:23 | 05:30 | 0.11667 | 3591 | 3685 | 94 | Rotate |  | 3615 | 13.1 | 28.2 | 3591.69 | 240.64 | 151.75 | 240.64 | 0.31 |  |  | 25 | 75 | 730 | 9000 | 805.71 | 3000 | 2550 | 450 | 109 | 130 | 125 | 120
05/01/2020 | 05:35 | 05:46 | 0.18333 | 3685 | 3778 | 93 | Rotate |  | 3708 | 12.8 | 27.4 | 3682.32 | 259.08 | 161.47 | 259.08 | 0.38 |  |  | 30 | 80 | 730 | 9000 | 507.27 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 05:51 | 06:02 | 0.18333 | 3778 | 3871 | 93 | Rotate |  | 3801 | 12.8 | 26.4 | 3773.01 | 277.45 | 170.79 | 277.45 | 0.24 |  |  | 30 | 80 | 730 | 9000 | 507.27 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 06:07 | 06:15 | 0.13333 | 3871 | 3965 | 94 | Rotate |  | 3895 | 12.6 | 26.2 | 3864.71 | 295.98 | 179.94 | 295.98 | 0.22 |  |  | 30 | 80 | 730 | 9000 | 705 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 06:20 | 06:28 | 0.13333 | 3965 | 4059 | 94 | Rotate |  | 3989 | 12.7 | 25.4 | 3956.43 | 314.51 | 188.9 | 314.51 | 0.21 |  |  | 30 | 80 | 730 | 9000 | 705 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 06:52 | 07:02 | 0.16667 | 4059 | 4153 | 94 | Rotate |  | 4083 | 12.6 | 24.4 | 4048.15 | 333.18 | 197.57 | 333.18 | 0.26 |  |  | 30 | 80 | 730 | 9000 | 564 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 07:08 | 07:10 | 0.033333 | 4153 | 4175 | 22 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 660 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 07:10 | 07:20 | 0.16667 | 4175 | 4187 | 12 | Slide | 0 | 4178 | 12.7 | 30.1 | 4140.84 | 351.65 | 207.09 | 351.65 | 1.32 |  |  | 18 |  | 730 |  | 72 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 07:20 | 07:27 | 0.11667 | 4187 | 4248 | 61 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 522.86 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 07:32 | 07:43 | 0.18333 | 4248 | 4341 | 93 | Rotate |  | 4271 | 12.7 | 33.4 | 4231.57 | 369.03 | 217.84 | 369.03 | 0.78 |  |  | 30 | 80 | 730 | 9000 | 507.27 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 07:47 | 07:58 | 0.18333 | 4341 | 4435 | 94 | Rotate |  | 4365 | 12.4 | 32.3 | 4323.32 | 386.19 | 228.92 | 386.19 | 0.41 |  |  | 30 | 80 | 730 | 9000 | 512.73 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 08:03 | 08:09 | 0.1 | 4435 | 4528 | 93 | Rotate |  | 4458 | 12.4 | 30.1 | 4414.16 | 403.27 | 239.27 | 403.27 | 0.51 |  |  | 30 | 80 | 730 | 9000 | 930 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 08:14 | 08:21 | 0.11667 | 4528 | 4623 | 95 | Rotate |  | 4553 | 12.2 | 28.7 | 4506.97 | 420.9 | 249.2 | 420.9 | 0.38 |  |  | 30 | 80 | 730 | 9000 | 814.29 | 3200 | 2550 | 650 | 109 | 140 | 135 | 130
05/01/2020 | 08:26 | 08:35 | 0.15 | 4623 | 4716 | 93 | Rotate |  | 4646 | 12.3 | 27.4 | 4597.86 | 438.31 | 258.48 | 438.31 | 0.32 |  |  | 30 | 80 | 730 | 9000 | 620 | 3200 | 2550 | 650 | 158 | 140 | 135 | 130
05/01/2020 | 08:40 | 08:48 | 0.13333 | 4716 | 4809 | 93 | Rotate |  | 4739 | 12.4 | 27.6 | 4688.71 | 455.95 | 267.67 | 455.95 | 0.12 |  |  | 30 | 80 | 730 | 9000 | 697.5 | 3200 | 2550 | 650 | 158 | 140 | 135 | 130
05/01/2020 | 08:53 | 09:02 | 0.15 | 4809 | 4904 | 95 | Rotate |  | 4834 | 12 | 26.1 | 4781.56 | 473.86 | 276.74 | 473.86 | 0.54 |  |  | 30 | 80 | 730 | 9000 | 633.33 | 3200 | 2550 | 650 | 158 | 140 | 135 | 130
05/01/2020 | 09:07 | 09:14 | 0.11667 | 4904 | 4998 | 94 | Rotate |  | 4928 | 11.6 | 25.7 | 4873.57 | 491.15 | 285.13 | 491.15 | 0.43 |  |  | 30 | 80 | 730 | 9000 | 805.71 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 09:20 | 09:23 | 0.05 | 4998 | 5035 | 37 | Rotate |  | 5022 | 11.3 | 23.5 | 4965.7 | 508.11 | 292.9 | 508.11 | 0.56 |  |  | 30 | 80 | 730 | 9000 | 740 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 09:23 | 09:36 | 0.21667 | 5035 | 5050 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 180; Drilling Parameters FLOW: 730; Drilling Parameters ROP: 69.23 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 09:36 | 09:42 | 0.1 | 5050 | 5092 | 42 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 420 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 09:47 | 09:56 | 0.15 | 5092 | 5187 | 95 | Rotate |  | 5117 | 11.9 | 29.8 | 5058.77 | 525.15 | 301.48 | 525.15 | 1.47 |  |  | 30 | 80 | 730 | 9000 | 633.33 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 10:00 | 10:10 | 0.16667 | 5187 | 5281 | 94 | Rotate |  | 5211 | 11.3 | 27.1 | 5150.85 | 541.76 | 310.5 | 541.76 | 0.86 |  |  | 30 | 80 | 730 | 9000 | 564 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 10:15 | 10:18 | 0.05 | 5281 | 5290 | 9 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 180 | 3200 | 2550 | 650 | 158 | 165 | 155 | 145
05/01/2020 | 10:18 | 10:28 | 0.16667 | 5290 | 5305 | 15 | Slide | 0 | 5305 | 12.1 | 29.7 | 5242.89 | 558.52 | 319.57 | 558.52 | 1.02 |  |  | 30 | 80 | 730 | 9000 | 90 | 3200 | 2550 | 650 | 160 | 165 | 155 | 145
05/01/2020 | 10:28 | 10:38 | 0.16667 | 5305 | 5375 | 70 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 420 | 3200 | 2550 | 650 | 160 | 165 | 155 | 145
05/01/2020 | 10:43 | 10:52 | 0.15 | 5375 | 5468 | 93 | Rotate |  | 5398 | 11.7 | 30 | 5333.89 | 575.15 | 329.12 | 575.15 | 0.44 |  |  | 30 | 80 | 730 | 9000 | 620 | 3200 | 2550 | 650 | 160 | 165 | 155 | 145
05/01/2020 | 10:57 | 11:04 | 0.11667 | 5468 | 5562 | 94 | Rotate |  | 5492 | 11.6 | 29.3 | 5425.96 | 591.64 | 338.51 | 591.64 | 0.18 |  |  | 30 | 80 | 730 | 12000 | 805.71 | 3200 | 2550 | 650 | 160 | 165 | 155 | 145
05/01/2020 | 11:10 | 11:17 | 0.11667 | 5562 | 5656 | 94 | Rotate |  | 5586 | 11.7 | 27.8 | 5518.02 | 608.32 | 347.58 | 608.32 | 0.34 |  |  | 30 | 80 | 730 | 12000 | 805.71 | 3200 | 2550 | 650 | 160 | 165 | 155 | 145
05/01/2020 | 11:22 | 11:25 | 0.05 | 5656 | 5670 | 14 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 280 | 3200 | 2550 | 650 | 160 | 165 | 155 | 145
05/01/2020 | 11:25 | 11:37 | 0.2 | 5670 | 5690 | 20 | Slide | 0 | 5682 | 11.6 | 33.9 | 5612.05 | 624.94 | 357.5 | 624.94 | 1.29 |  |  | 18 |  | 730 |  | 100 | 3200 | 2550 | 650 | 164 | 165 | 155 | 145
05/01/2020 | 11:37 | 11:47 | 0.16667 | 5690 | 5752 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 372 | 3200 | 2550 | 650 | 164 | 165 | 155 | 145
05/01/2020 | 11:52 | 12:00 | 0.13333 | 5752 | 5846 | 94 | Rotate |  | 5776 | 11.9 | 37.1 | 5704.08 | 640.51 | 368.62 | 640.51 | 0.76 |  |  | 30 | 80 | 730 | 12000 | 705 | 3200 | 2550 | 650 | 164 | 165 | 155 | 145
05/01/2020 | 12:05 | 12:15 | 0.16667 | 5846 | 5940 | 94 | Rotate |  | 5870 | 11.3 | 33.5 | 5796.16 | 655.92 | 379.55 | 655.92 | 1 |  |  | 30 | 80 | 730 | 12000 | 564 | 3200 | 2550 | 650 | 164 | 165 | 155 | 145
05/01/2020 | 12:20 | 12:31 | 0.18333 | 5940 | 6034 | 94 | Rotate |  | 5964 | 10.9 | 32.3 | 5888.4 | 671.12 | 389.38 | 671.12 | 0.49 |  |  | 30 | 80 | 730 | 12000 | 512.73 | 3200 | 2550 | 650 | 164 | 165 | 155 | 145
05/01/2020 | 12:37 | 12:40 | 0.05 | 6034 | 6045 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 730; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 220 | 3200 | 2550 | 650 | 170 | 165 | 155 | 145
05/01/2020 | 12:40 | 12:58 | 0.3 | 6045 | 6065 | 20 | Slide | 0 | 6058 | 11.8 | 33.5 | 5980.56 | 686.64 | 399.43 | 686.64 | 0.99 |  |  | 20 |  | 756 |  | 66.67 | 3600 | 3300 | 300 | 170 | 180 | 170 | 160
05/01/2020 | 12:58 | 13:09 | 0.18333 | 6065 | 6128 | 63 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 343.64 | 3600 | 3300 | 300 | 170 | 180 | 170 | 160
05/01/2020 | 13:15 | 13:25 | 0.16667 | 6128 | 6222 | 94 | Rotate |  | 6152 | 11.5 | 30.3 | 6072.63 | 702.75 | 409.47 | 702.75 | 0.76 |  |  | 34 | 80 | 756 | 12000 | 564 | 3600 | 3300 | 300 | 170 | 180 | 170 | 160
05/01/2020 | 13:30 | 13:46 | 0.26667 | 6222 | 6315 | 93 | Rotate |  | 6245 | 10.6 | 27.7 | 6163.9 | 718.33 | 418.12 | 718.33 | 1.11 |  |  | 30 | 80 | 756 | 12000 | 348.75 | 3600 | 3300 | 300 | 170 | 180 | 170 | 160
05/01/2020 | 13:50 | 13:55 | 0.083333 | 6315 | 6325 | 10 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 120 | 3800 | 3300 | 500 | 170 | 180 | 170 | 160
05/01/2020 | 13:55 | 14:26 | 0.51667 | 6325 | 6350 | 25 | Slide | 0 | 6339 | 10.4 | 31.6 | 6256.33 | 733.21 | 426.58 | 733.21 | 0.79 |  |  | 20 |  | 756 |  | 48.39 | 3600 | 3300 | 300 | 170 | 180 | 170 | 160
05/01/2020 | 14:26 | 14:35 | 0.15 | 6350 | 6409 | 59 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 393.33 | 3800 | 3300 | 500 | 170 | 180 | 170 | 160
05/01/2020 | 14:40 | 14:45 | 0.083333 | 6409 | 6415 | 6 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 72 | 3800 | 3300 | 500 | 170 | 180 | 170 | 160
05/01/2020 | 14:45 | 15:15 | 0.5 | 6415 | 6445 | 30 | Slide | 0 | 6434 | 13.2 | 34.3 | 6349.31 | 749.47 | 437.19 | 749.47 | 3 |  |  | 20 |  | 756 |  | 60 | 3600 | 3300 | 300 | 170 | 180 | 170 | 160
05/01/2020 | 15:15 | 15:21 | 0.1 | 6445 | 6504 | 59 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 590 | 3800 | 3300 | 500 | 170 | 180 | 170 | 160
05/01/2020 | 15:26 | 15:41 | 0.25 | 6504 | 6597 | 93 | Rotate |  | 6527 | 14.9 | 33.5 | 6439.53 | 768.22 | 449.78 | 768.22 | 1.84 |  |  | 34 | 80 | 756 | 15000 | 372 | 3800 | 3300 | 500 | 183 | 180 | 170 | 160
05/01/2020 | 15:46 | 15:57 | 0.18333 | 6597 | 6691 | 94 | Rotate |  | 6621 | 14.2 | 31.8 | 6530.51 | 788.09 | 462.52 | 788.09 | 0.87 |  |  | 34 | 80 | 756 | 15000 | 512.73 | 3800 | 3300 | 500 | 183 | 180 | 170 | 160
05/01/2020 | 16:02 | 16:11 | 0.15 | 6691 | 6753 | 62 | Rotate |  | 6716 | 13.7 | 31.1 | 6622.71 | 807.63 | 474.47 | 807.63 | 0.56 |  |  | 34 | 80 | 756 | 15000 | 413.33 | 3800 | 3300 | 500 | 183 | 180 | 170 | 160
05/01/2020 | 16:23 | 16:28 | 0.083333 | 6753 | 6786 | 33 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 396 | 3800 | 3300 | 500 | 183 | 200 | 185 | 175
05/01/2020 | 16:33 | 16:53 | 0.33333 | 6786 | 6879 | 93 | Rotate |  | 6809 | 13.5 | 30.4 | 6713.1 | 826.42 | 485.66 | 826.42 | 0.28 |  |  | 34 | 80 | 756 | 15000 | 279 | 3800 | 3300 | 500 | 183 | 200 | 185 | 175
05/01/2020 | 16:58 | 17:11 | 0.21667 | 6879 | 6974 | 95 | Rotate |  | 6904 | 12.8 | 27.8 | 6805.61 | 845.3 | 496.17 | 845.3 | 0.96 |  |  | 34 | 80 | 756 | 15000 | 438.46 | 3800 | 3300 | 500 | 183 | 200 | 185 | 175
05/01/2020 | 17:16 | 17:28 | 0.2 | 6974 | 7068 | 94 | Rotate |  | 6998 | 12 | 25.6 | 6897.42 | 863.32 | 505.25 | 863.32 | 0.99 |  |  | 34 | 80 | 756 | 15000 | 470 | 3800 | 3300 | 500 | 183 | 200 | 185 | 175
05/01/2020 | 17:33 | 17:45 | 0.2 | 7068 | 7162 | 94 | Rotate |  | 7092 | 11.2 | 22.4 | 6989.5 | 880.57 | 512.95 | 880.57 | 1.09 |  |  | 34 | 80 | 756 | 15000 | 470 | 3800 | 3300 | 500 | 190 | 200 | 185 | 175
05/01/2020 | 17:55 | 18:17 | 0.36667 | 7162 | 7182 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 54.55 | 3600 | 3300 | 300 | 190 | 180 | 170 | 160
05/01/2020 | 18:17 | 18:33 | 0.26667 | 7182 | 7255 | 73 | Rotate |  | 7185 | 13.1 | 20.8 | 7080.41 | 898.78 | 520.14 | 898.78 | 2.07 |  |  | 34 | 80 | 756 | 15000 | 273.75 | 3800 | 3300 | 500 | 190 | 200 | 185 | 175
05/01/2020 | 18:38 | 18:54 | 0.26667 | 7255 | 7350 | 95 | Rotate |  | 7280 | 12.8 | 18.6 | 7173 | 918.82 | 527.32 | 918.82 | 0.61 |  |  | 34 | 80 | 756 | 15000 | 356.25 | 3800 | 3300 | 500 | 190 | 200 | 185 | 175
05/01/2020 | 19:03 | 19:25 | 0.36667 | 7350 | 7370 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 54.55 | 3600 | 3300 | 300 | 190 | 180 | 170 | 160
05/01/2020 | 19:25 | 19:40 | 0.25 | 7370 | 7444 | 74 | Rotate |  | 7374 | 12 | 26.8 | 7264.81 | 937.41 | 535.05 | 937.41 | 2.06 |  |  | 34 | 80 | 756 | 15000 | 296 | 3800 | 3300 | 500 | 190 | 200 | 185 | 175
05/01/2020 | 19:45 | 19:58 | 0.21667 | 7444 | 7538 | 94 | Rotate |  | 7468 | 10.8 | 23 | 7356.95 | 954.24 | 542.89 | 954.24 | 1.51 |  |  | 34 | 80 | 756 | 15000 | 433.85 | 3800 | 3300 | 500 | 190 | 200 | 185 | 175
05/01/2020 | 20:03 | 20:09 | 0.1 | 7538 | 7548 | 10 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 100 | 3800 | 3300 | 500 | 190 | 200 | 185 | 175
05/01/2020 | 20:09 | 21:20 | 1.1833 | 7548 | 7568 | 20 | Slide | 0 | 7562 | 10.4 | 17.5 | 7449.35 | 970.44 | 548.89 | 970.44 | 1.16 |  |  | 34 |  | 756 |  | 16.9 | 3600 | 3300 | 300 | 194 | 180 | 170 | 160
05/01/2020 | 21:20 | 21:39 | 0.31667 | 7568 | 7632 | 64 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 202.11 | 3800 | 3300 | 500 | 194 | 200 | 185 | 175
05/01/2020 | 21:48 | 23:20 | 1.5333 | 7632 | 7652 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 34; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 13.04 | 3600 | 3300 | 300 | 194 | 180 | 170 | 160
05/01/2020 | 23:20 | 23:36 | 0.26667 | 7652 | 7726 | 74 | Rotate |  | 7656 | 10.7 | 18.6 | 7541.76 | 986.8 | 554.22 | 986.8 | 0.38 |  |  | 34 | 80 | 756 | 15000 | 277.5 | 3800 | 3300 | 500 | 194 | 235 | 215 | 195
05/01/2020 | 23:41 | 24:00 | 0.31667 | 7726 | 7732 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 34; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 18.95 | 3600 | 3300 | 300 | 194 | 235 | 215 | 195
05/02/2020 | 00:00 | 00:17 | 0.28333 | 7732 | 7751 | 19 | Slide | 0 | 7750 | 9.9 | 31.4 | 7634.26 | 1001.97 | 561.22 | 1001.97 | 2.57 |  |  | 34 |  | 756 |  | 67.06 | 3600 | 3300 | 300 | 194 | 235 | 215 | 195
05/02/2020 | 00:17 | 00:29 | 0.2 | 7751 | 7820 | 69 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 345 | 3800 | 3300 | 500 | 194 | 235 | 215 | 195
05/02/2020 | 00:34 | 00:45 | 0.18333 | 7820 | 7914 | 94 | Rotate |  | 7844 | 8.4 | 27.8 | 7727.06 | 1014.94 | 568.63 | 1014.94 | 1.71 |  |  | 34 | 80 | 756 | 15000 | 512.73 | 3800 | 3300 | 500 | 196 | 235 | 215 | 195
05/02/2020 | 00:50 | 01:01 | 0.18333 | 7914 | 8008 | 94 | Rotate |  | 7938 | 7.1 | 20 | 7820.2 | 1026.48 | 573.82 | 1026.48 | 1.78 |  |  | 34 | 80 | 756 | 15000 | 512.73 | 3800 | 3300 | 500 | 196 | 235 | 215 | 195
05/02/2020 | 01:06 | 01:12 | 0.1 | 8008 | 8013 | 5 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 50 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 01:12 | 01:45 | 0.55 | 8013 | 8042 | 29 | Slide | 0 | 8032 | 7.9 | 33.3 | 7913.41 | 1037.34 | 579.35 | 1037.34 | 2.03 |  |  | 34 |  | 756 |  | 52.73 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 01:45 | 02:00 | 0.25 | 8042 | 8102 | 60 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 240 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 02:05 | 02:20 | 0.25 | 8102 | 8195 | 93 | Rotate |  | 8125 | 7.2 | 35.2 | 8005.6 | 1047.44 | 586.22 | 1047.44 | 0.8 |  |  | 34 | 80 | 756 | 15000 | 372 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 02:25 | 02:32 | 0.11667 | 8195 | 8286 | 91 | Rotate |  | 8216 | 6 | 30.8 | 8096 | 1056.19 | 591.94 | 1056.19 | 1.43 |  |  | 34 | 80 | 756 | 15000 | 780 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 02:37 | 02:43 | 0.1 | 8286 | 8289 | 3 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 30 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 02:43 | 03:06 | 0.38333 | 8289 | 8315 | 26 | Slide | 0 | 8310 | 6.7 | 46.5 | 8189.43 | 1064.18 | 598.44 | 1064.18 | 1.98 |  |  | 34 |  | 756 |  | 67.83 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 03:06 | 03:19 | 0.21667 | 8315 | 8380 | 65 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 300 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 03:24 | 03:36 | 0.2 | 8380 | 8473 | 93 | Rotate |  | 8403 | 5.7 | 45.9 | 8281.88 | 1071.13 | 605.69 | 1071.13 | 1.08 |  |  | 34 | 80 | 756 | 16000 | 465 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 03:41 | 03:51 | 0.16667 | 8473 | 8568 | 95 | Rotate |  | 8498 | 4.9 | 42.6 | 8376.47 | 1077.4 | 611.82 | 1077.4 | 0.9 |  |  | 34 | 80 | 756 | 16000 | 570 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 03:56 | 04:05 | 0.15 | 8568 | 8662 | 94 | Rotate |  | 8592 | 4.8 | 40.2 | 8470.14 | 1083.36 | 617.08 | 1083.36 | 0.24 |  |  | 34 | 80 | 756 | 16000 | 626.67 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 04:07 | 04:23 | 0.26667 | 8662 | 8757 | 95 | Rotate |  | 8687 | 5.1 | 38 | 8564.78 | 1089.72 | 622.25 | 1089.72 | 0.37 |  |  | 34 | 80 | 756 | 16000 | 356.25 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 04:27 | 04:38 | 0.18333 | 8757 | 8851 | 94 | Rotate |  | 8781 | 4.6 | 36.8 | 8658.45 | 1096.03 | 627.08 | 1096.03 | 0.54 |  |  | 34 | 80 | 756 | 16000 | 512.73 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 04:43 | 04:53 | 0.16667 | 8851 | 8945 | 94 | Rotate |  | 8875 | 5 | 22.6 | 8752.12 | 1102.83 | 630.91 | 1102.83 | 1.33 |  |  | 34 | 80 | 756 | 16000 | 564 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 04:55 | 05:00 | 0.083333 | 8945 | 8953 | 8 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 96 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 05:00 | 05:18 | 0.3 | 8953 | 8968 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 34; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 50 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 05:18 | 05:29 | 0.18333 | 8968 | 9039 | 71 | Rotate |  | 8969 | 4.6 | 34.1 | 8845.79 | 1109.74 | 634.6 | 1109.74 | 1.11 |  |  | 34 | 80 | 756 | 16000 | 387.27 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 05:40 | 05:51 | 0.18333 | 9039 | 9134 | 95 | Rotate |  | 9064 | 4.2 | 38.6 | 8940.51 | 1115.61 | 638.9 | 1115.61 | 0.56 |  |  | 34 | 80 | 756 | 16000 | 518.18 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 05:56 | 06:00 | 0.066667 | 9134 | 9150 | 16 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 240 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 06:00 | 06:19 | 0.31667 | 9150 | 9170 | 20 | Slide | 0 | 9158 | 2.9 | 44.2 | 9034.33 | 1120 | 642.71 | 1120 | 1.43 |  |  | 20 |  | 756 |  | 63.16 | 3800 | 3300 | 500 | 202 | 235 | 215 | 195
05/02/2020 | 06:19 | 06:30 | 0.18333 | 9170 | 9228 | 58 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 316.36 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 06:35 | 06:48 | 0.21667 | 9228 | 9322 | 94 | Rotate |  | 9252 | 2.6 | 52.5 | 9128.22 | 1123.01 | 646.06 | 1123.01 | 0.53 |  |  | 34 | 80 | 756 | 16000 | 433.85 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 06:53 | 07:00 | 0.11667 | 9322 | 9335 | 13 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 111.43 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 07:00 | 07:11 | 0.18333 | 9335 | 9353 | 18 | Slide | 0 | 9346 | 1.5 | 46.9 | 9222.16 | 1125.14 | 648.65 | 1125.14 | 1.19 |  |  | 20 |  | 756 |  | 98.18 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 07:11 | 07:21 | 0.16667 | 9353 | 9417 | 64 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 384 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 08:44 | 09:08 | 0.4 | 9417 | 9509 | 92 | Rotate |  | 9439 | 0.3 | 331.7 | 9315.15 | 1126.19 | 649.42 | 1126.19 | 1.56 |  |  | 34 | 80 | 756 | 16000 | 230 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 09:14 | 10:05 | 0.85 | 9509 | 9540 | 31 | Slide | 0 | 9533 | 2.2 | 320.6 | 9409.12 | 1127.8 | 648.16 | 1127.8 | 2.03 |  |  | 20 |  | 756 |  | 36.47 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 10:40 | 10:51 | 0.18333 | 9540 | 9603 | 63 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 343.64 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 10:56 | 11:03 | 0.11667 | 9603 | 9615 | 12 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 102.86 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 11:03 | 11:42 | 0.65 | 9615 | 9640 | 25 | Slide | 0 | 9627 | 4.3 | 327.8 | 9502.97 | 1132.18 | 645.13 | 1132.18 | 2.27 |  |  | 20 |  | 756 |  | 38.46 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 11:42 | 11:57 | 0.25 | 9640 | 9697 | 57 | Rotate |  | 9672 | 5.6 | 329.9 | 9547.8 | 1135.51 | 643.13 | 1135.51 | 2.92 |  |  | 34 | 80 | 756 | 16000 | 228 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 12:04 | 12:13 | 0.15 | 9697 | 9742 | 45 | Rotate |  | 9721 | 5.3 | 330.1 | 9596.58 | 1139.54 | 640.81 | 1139.54 | 0.61 |  |  | 34 | 80 | 756 | 16000 | 300 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 12:18 | 12:30 | 0.2 | 9742 | 9791 | 49 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 245 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 12:35 | 13:02 | 0.45 | 9791 | 9826 | 35 | Slide | 0 | 9816 | 7.9 | 330.5 | 9690.94 | 1149.02 | 635.4 | 1149.02 | 2.74 |  |  | 20 |  | 756 |  | 77.78 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 13:02 | 13:19 | 0.28333 | 9826 | 9886 | 60 | Rotate |  | 9861 | 8.2 | 332 | 9735.49 | 1154.55 | 632.37 | 1154.55 | 0.81 |  |  | 34 | 80 | 756 | 16000 | 211.76 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 13:25 | 13:36 | 0.18333 | 9886 | 9896 | 10 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 54.55 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 13:36 | 14:05 | 0.48333 | 9896 | 9921 | 25 | Slide | 0 | 9910 | 9.3 | 332 | 9783.92 | 1161.13 | 628.87 | 1161.13 | 2.24 |  |  | 20 |  | 756 |  | 51.72 | 3800 | 3300 | 500 |  | 235 | 215 | 195
05/02/2020 | 14:05 | 14:12 | 0.11667 | 9921 | 9931 | 10 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 85.71 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 14:17 | 14:21 | 0.066667 | 9931 | 9940 | 9 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 135 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 14:21 | 15:05 | 0.73333 | 9940 | 9965 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 34.09 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 15:05 | 15:11 | 0.1 | 9965 | 9980 | 15 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 150 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 15:30 | 19:51 | 4.35 | 9980 | 10074 | 94 | Slide | 0 | 10004 | 11.7 | 332.4 | 9876.34 | 1176.28 | 620.89 | 1176.28 | 2.55 |  |  | 34 |  | 756 |  | 21.61 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 19:55 | 20:21 | 0.43333 | 10074 | 10119 | 45 | Rotate |  | 10098 | 15.6 | 330.7 | 9967.49 | 1196.38 | 609.87 | 1196.38 | 2.25 |  |  | 34 | 80 | 756 | 16000 | 103.85 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 20:26 | 22:14 | 1.8 | 10119 | 10150 | 31 | Slide | TTF: 0; Drilling Parameters WOB: 34; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 17.22 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 22:14 | 22:21 | 0.11667 | 10150 | 10168 | 18 | Rotate | Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 154.29 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 22:26 | 23:22 | 0.93333 | 10168 | 10193 | 25 | Slide | 0 | 10193 | 18.6 | 338.8 | 10058.29 | 1221.65 | 598.13 | 1221.65 | 4.03 |  |  | 34 |  | 756 |  | 26.79 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 23:22 | 23:45 | 0.38333 | 10193 | 10263 | 70 | Rotate |  | 10240 | 18.2 | 339.7 | 10102.89 | 1235.53 | 592.87 | 1235.53 | 1.04 |  |  | 34 | 80 | 756 | 16000 | 182.61 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/02/2020 | 23:50 | 24:00 | 0.16667 | 10263 | 10276 | 13 | Rotate |  | 10265 | 17.8 | 339.5 | 10126.66 | 1242.77 | 590.18 | 1242.77 | 1.62 |  |  | 34 | 80 | 756 | 16000 | 78 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/03/2020 | 00:00 | 03:00 | 3 | 10276 | 10310 | 34 | Slide | TTF: 0; Drilling Parameters WOB: 34; Drilling Parameters FLOW: 756; Drilling Parameters ROP: 11.33 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195
05/03/2020 | 03:05 | 04:35 | 1.5 | 10310 | 10335 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 34; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 756; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 16.67 | 3800 | 3300 | 500 | 219 | 235 | 215 | 195

## BHA_3_Curve__Lateral_Slide_Shee
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 (Curve / Lateral) |  |  |  |  | RKB: |  |  |  | 332 |  | North Reference: |  | GRID |  | Total Drilled: |  | 527
Site: |  |  |  |  | Grand Canyon-Levi Goodrich - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 413
Well Name: |  |  |  |  | Grand Canyon 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 67.00 / 57.00 |  |  |  |  | Grid Conv: |  |  |  | 332 |  | VS Azimuth: |  | 335.04 |  | Rotate: |  | 114
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/23/2020 | 08:05 | 08:15 | 0.16667 | 10335 | 10345 | 10 | Rotate | Drilling Parameters WOB: 14; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 245; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 60 | 1950 | 1850 | 100 | 239 | 250 | 220 | 190
06/23/2020 | 09:30 | 13:00 | 3.5 | 10345 | 10388 | 43 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 12.29 | 2600 | 3100 | -500 | 239 | 250 | 220 | 190
06/23/2020 | 13:15 | 13:40 | 0.41667 | 10388 | 10418 | 30 | Rotate |  | 10413 | 23.3 | 330.5 | 10265.23 | 1289.48 | 567.82 | 1289.48 | 4.28 |  |  | 25 | 30 | 350 | 9000 | 72 | 2600 | 3100 | -500 | 239 | 250 | 220 | 190
06/23/2020 | 13:40 | 14:45 | 1.0833 | 10418 | 10482 | 64 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 59.08 | 2500 | 2700 | -200 | 239 | 250 | 220 | 190
06/23/2020 | 15:00 | 15:15 | 0.25 | 10482 | 10506 | 24 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 96 | 2500 | 3800 | -1300 | 239 | 250 | 220 | 190
06/23/2020 | 15:15 | 15:40 | 0.41667 | 10506 | 10513 | 7 | Slide | 0 | 10508 | 32.7 | 330.6 | 10349.01 | 1328.27 | 545.92 | 1328.27 | 9.89 |  |  | 14 |  | 350 | 2000 | 16.8 | 2500 | 2700 | -200 | 239 | 250 | 220 | 190
06/23/2020 | 16:00 | 17:10 | 1.1667 | 10513 | 10567 | 54 | Slide | TTF: 0; Drilling Parameters WOB: 14; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 46.29 | 3300 | 3800 | -500 | 239 | 250 | 220 | 190
06/23/2020 | 17:10 | 17:20 | 0.16667 | 10567 | 10577 | 10 | Rotate | Drilling Parameters WOB: 14; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 60 | 3300 | 3800 | -500 | 239 | 250 | 220 | 190
06/23/2020 | 17:20 | 17:40 | 0.33333 | 10577 | 10597 | 20 | Rotate | Drilling Parameters WOB: 14; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 60 | 3300 | 3800 | -500 | 239 | 250 | 220 | 190
06/23/2020 | 17:40 | 18:45 | 1.0833 | 10597 | 10671 | 74 | Slide | 0 | 10602 | 40 | 336.1 | 10424.69 | 1378.1 | 521.18 | 1378.1 | 8.5 |  |  | 30 |  | 380 | 2000 | 68.31 | 3300 | 3800 | -500 | 243 | 250 | 220 | 190
06/23/2020 | 19:05 | 19:55 | 0.83333 | 10671 | 10720 | 49 | Slide | 0 | 10697 | 51.8 | 341.5 | 10490.71 | 1441.66 | 496.87 | 1441.66 | 13.07 |  |  | 30 |  | 380 | 2000 | 58.8 | 3300 | 3800 | -500 | 243 | 250 | 220 | 190
06/23/2020 | 20:05 | 20:25 | 0.33333 | 10720 | 10740 | 20 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 60 | 3300 | 3800 | -500 | 243 | 250 | 220 | 190
06/23/2020 | 20:25 | 21:00 | 0.58333 | 10740 | 10766 | 26 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 44.57 | 3300 | 3700 | -400 | 243 | 250 | 220 | 190
06/23/2020 | 21:10 | 22:40 | 1.5 | 10766 | 10862 | 96 | Slide | 0 | 10791 | 61 | 339.9 | 10542.68 | 1515.45 | 470.97 | 1515.45 | 9.89 |  |  | 30 |  | 380 | 9000 | 64 | 3300 | 3700 | -400 | 243 | 250 | 220 | 190

## BHA_4_Bailout_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 (Bailout) |  |  |  |  | RKB: |  |  |  | 332 |  | North Reference: |  | GRID |  | Total Drilled: |  | 94
Site: |  |  |  |  | Grand Canyon-Levi Goodrich - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 94
Well Name: |  |  |  |  | Grand Canyon 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 62.00 / 50.00 |  |  |  |  | Grid Conv: |  |  |  | 332 |  | VS Azimuth: |  | 335.04 |  | Rotate: |  | 0
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/24/2020 | 15:30 | 19:00 | 3.5 | 10860 | 10922 | 62 | Slide | 0 | 10885 | 77.5 | 335.4 | 10575.88 | 1596.37 | 437.49 | 1596.37 | 18.11 |  |  | 25 |  | 247 | 2000 | 17.71 | 2100 | 1950 | 150 | 262 | 250 | 230 | 190
06/24/2020 | 19:15 | 20:15 | 1 | 10922 | 10935 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 247; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 13 | 2100 | 1950 | 150 | 262 | 250 | 230 | 190
06/24/2020 | 20:50 | 21:40 | 0.83333 | 10935 | 10947 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 247; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 14.4 | 2100 | 1950 | 150 | 226 | 250 | 230 | 190
06/24/2020 | 21:55 | 22:20 | 0.41667 | 10947 | 10954 | 7 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 247; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 16.8 | 2100 | 1950 | 150 | 226 | 250 | 230 | 190

## BHA_5_Lateral_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 (Lateral) |  |  |  |  | RKB: |  |  |  | 332 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6932
Site: |  |  |  |  | Grand Canyon-Levi Goodrich - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 767
Well Name: |  |  |  |  | Grand Canyon 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 57.00 |  |  |  |  | Grid Conv: |  |  |  | 332 |  | VS Azimuth: |  | 335.04 |  | Rotate: |  | 6165
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/25/2020 | 18:35 | 19:40 | 1.0833 | 10954 | 11049 | 95 | Rotate |  | 10980 | 93 | 332.5 | 10583.72 | 1681.15 | 396.02 | 1681.15 | 16.6 |  |  | 15 | 30 | 400 | 10000 | 87.69 | 4150 | 3800 | 350 | 250 | 250 | 220 | 190
06/25/2020 | 19:50 | 20:25 | 0.58333 | 11049 | 11098 | 49 | Rotate |  | 11075 | 94.2 | 331.2 | 10577.76 | 1764.74 | 351.29 | 1764.74 | 1.86 |  |  | 15 | 30 | 400 | 10000 | 84 | 4150 | 3800 | 350 | 250 | 250 | 220 | 190
06/25/2020 | 20:35 | 21:35 | 1 | 11098 | 11123 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 3000; Drilling Parameters ROP: 25 | 3950 | 3800 | 150 | 250 | 250 | 220 | 190
06/25/2020 | 21:35 | 21:55 | 0.33333 | 11123 | 11144 | 21 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 63 | 4150 | 3800 | 350 | 255 | 250 | 220 | 190
06/25/2020 | 22:00 | 22:35 | 0.58333 | 11144 | 11240 | 96 | Rotate |  | 11171 | 91 | 333.8 | 10573.4 | 1849.79 | 307.02 | 1849.79 | 4.29 |  |  | 25 | 80 | 400 | 10000 | 164.57 | 4350 | 3800 | 550 | 255 | 250 | 220 | 190
06/25/2020 | 22:40 | 23:05 | 0.41667 | 11240 | 11335 | 95 | Rotate |  | 11266 | 89.9 | 333.2 | 10572.66 | 1934.81 | 264.64 | 1934.81 | 1.32 |  |  | 30 | 80 | 400 | 10000 | 228 | 4350 | 3800 | 550 | 255 | 250 | 220 | 190
06/25/2020 | 23:10 | 23:40 | 0.5 | 11335 | 11430 | 95 | Rotate |  | 11361 | 87.9 | 332.7 | 10574.48 | 2019.39 | 221.44 | 2019.39 | 2.17 |  |  | 30 | 80 | 400 | 10000 | 190 | 4500 | 3800 | 700 | 260 | 250 | 220 | 190
06/25/2020 | 23:45 | 23:50 | 0.083333 | 11430 | 11440 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 4500 | 3800 | 700 | 260 | 250 | 220 | 190
06/25/2020 | 23:50 | 24:00 | 0.16667 | 11440 | 11442 | 2 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 12 | 4000 | 3800 | 200 | 260 | 250 | 220 | 190
06/26/2020 | 00:00 | 00:45 | 0.75 | 11442 | 11475 | 33 | Slide | 0 | 11455 | 89.1 | 333.8 | 10576.94 | 2103.3 | 179.15 | 2103.3 | 1.73 |  |  | 35 | 80 | 400 | 10000 | 44 | 4000 | 3800 | 200 | 260 | 250 | 220 | 190
06/26/2020 | 00:45 | 01:00 | 0.25 | 11475 | 11524 | 49 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 196 | 4500 | 3800 | 700 | 264 | 263 | 213 | 198
06/26/2020 | 01:25 | 01:50 | 0.41667 | 11524 | 11619 | 95 | Rotate |  | 11550 | 90.5 | 334.1 | 10577.27 | 2188.65 | 137.43 | 2188.65 | 1.51 |  |  | 30 | 80 | 400 | 13000 | 228 | 4500 | 3800 | 700 | 264 | 263 | 213 | 198
06/26/2020 | 02:00 | 02:05 | 0.083333 | 11619 | 11632 | 13 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 156 | 4500 | 3800 | 700 | 264 | 263 | 213 | 198
06/26/2020 | 02:05 | 02:55 | 0.83333 | 11632 | 11672 | 40 | Slide | 0 | 11645 | 91.2 | 334.3 | 10575.86 | 2274.17 | 96.09 | 2274.17 | 0.77 |  |  | 35 | 80 | 400 | 13000 | 48 | 4000 | 3800 | 200 | 264 | 263 | 213 | 198
06/26/2020 | 02:55 | 03:05 | 0.16667 | 11672 | 11714 | 42 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 252 | 4500 | 3800 | 700 | 264 | 263 | 213 | 198
06/26/2020 | 03:10 | 03:35 | 0.41667 | 11714 | 11809 | 95 | Rotate |  | 11740 | 95.5 | 336.8 | 10570.31 | 2360.47 | 56.85 | 2360.47 | 5.23 |  |  | 30 | 80 | 400 | 13000 | 228 | 4500 | 3800 | 700 | 265 | 263 | 213 | 198
06/26/2020 | 03:40 | 04:00 | 0.33333 | 11809 | 11904 | 95 | Rotate |  | 11835 | 97.6 | 336 | 10559.48 | 2446.95 | 19.07 | 2446.95 | 2.36 |  |  | 30 | 80 | 400 | 13000 | 285 | 4500 | 3800 | 700 | 265 | 263 | 213 | 198
06/26/2020 | 04:10 | 04:15 | 0.083333 | 11904 | 11920 | 16 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 192 | 4500 | 3800 | 700 | 265 | 263 | 213 | 198
06/26/2020 | 04:15 | 04:55 | 0.66667 | 11920 | 11940 | 20 | Slide | 0 | 11932 | 98.5 | 334.8 | 10545.89 | 2534.28 | -20.91 | 2534.28 | 1.54 |  |  | 40 | 80 | 400 | 13000 | 30 | 4500 | 3800 | 700 | 265 | 263 | 213 | 198
06/26/2020 | 04:55 | 05:15 | 0.33333 | 11940 | 12001 | 61 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 183 | 4500 | 3800 | 700 | 270 | 263 | 213 | 198
06/26/2020 | 05:25 | 05:30 | 0.083333 | 12001 | 12020 | 19 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 228 | 4500 | 3800 | 700 | 270 | 263 | 213 | 198
06/26/2020 | 05:30 | 06:00 | 0.5 | 12020 | 12045 | 25 | Slide | 0 | 12027 | 96.6 | 334.6 | 10533.41 | 2619.42 | -61.16 | 2619.42 | 2.01 |  |  | 30 | 80 | 400 | 13000 | 50 | 4500 | 3800 | 700 | 270 | 263 | 213 | 198
06/26/2020 | 06:00 | 07:00 | 1 | 12045 | 12120 | 75 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 75 | 4500 | 3800 | 700 | 270 | 263 | 213 | 198
06/26/2020 | 07:00 | 07:30 | 0.5 | 12120 | 12135 | 15 | Slide | 0 | 12122 | 95.2 | 333.9 | 10523.65 | 2704.53 | -102.21 | 2704.53 | 1.65 |  |  | 30 | 80 | 400 | 13000 | 30 | 4500 | 3800 | 700 | 276.8 | 263 | 213 | 198
06/26/2020 | 07:30 | 08:00 | 0.5 | 12135 | 12211 | 76 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 152 | 4500 | 3800 | 700 | 276.8 | 263 | 213 | 198
06/26/2020 | 08:00 | 08:20 | 0.33333 | 12211 | 12231 | 20 | Slide | 0 | 12216 | 92.4 | 329.7 | 10517.41 | 2787.16 | -146.53 | 2787.16 | 5.36 |  |  | 30 | 80 | 400 | 13000 | 60 | 4500 | 3800 | 700 | 276.8 | 263 | 213 | 198
06/26/2020 | 08:20 | 09:25 | 1.0833 | 12231 | 12395 | 164 | Rotate |  | 12311 | 90.5 | 329.3 | 10515.01 | 2868.98 | -194.72 | 2868.98 | 2.04 |  |  | 30 | 80 | 400 | 13000 | 151.38 | 4500 | 3800 | 700 | 275 | 263 | 213 | 198
06/26/2020 | 09:25 | 10:25 | 1 | 12395 | 12425 | 30 | Slide | 0 | 12405 | 90.9 | 330.7 | 10513.86 | 2950.38 | -241.72 | 2950.38 | 1.55 |  |  | 30 | 80 | 400 | 13000 | 30 | 4500 | 3800 | 700 | 273 | 263 | 213 | 198
06/26/2020 | 10:25 | 11:30 | 1.0833 | 12425 | 12580 | 155 | Rotate |  | 12499 | 91.1 | 333 | 10512.22 | 3033.24 | -286.06 | 3033.24 | 2.46 |  |  | 30 | 80 | 400 | 13000 | 143.08 | 4500 | 3800 | 700 | 276.8 | 263 | 213 | 198
06/26/2020 | 11:30 | 12:00 | 0.5 | 12580 | 12605 | 25 | Slide | 0 | 12595 | 92.4 | 334.9 | 10509.29 | 3119.44 | -328.19 | 3119.44 | 2.4 |  |  | 30 | 80 | 400 | 13000 | 50 | 4500 | 3800 | 700 | 276.8 | 263 | 213 | 198
06/26/2020 | 12:00 | 14:00 | 2 | 12605 | 12960 | 355 | Rotate |  | 12689 | 93.1 | 336.3 | 10504.78 | 3204.95 | -366.98 | 3204.95 | 1.66 |  |  | 30 | 80 | 400 | 13000 | 177.5 | 4500 | 3800 | 700 | 285.5 | 263 | 213 | 198
06/26/2020 | 14:30 | 14:50 | 0.33333 | 12960 | 12980 | 20 | Slide | 0 | 12973 | 93.8 | 336.1 | 10488.68 | 3463.5 | -483.35 | 3463.5 | 1.48 |  |  | 30 | 80 | 400 | 13000 | 60 | 4500 | 3800 | 700 | 285.5 | 263 | 213 | 198
06/26/2020 | 14:50 | 15:00 | 0.16667 | 12980 | 13042 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 372 | 4500 | 3800 | 700 | 285.5 | 263 | 213 | 198
06/26/2020 | 15:40 | 16:15 | 0.58333 | 13042 | 13150 | 108 | Rotate |  | 13067 | 95.3 | 335.7 | 10481.22 | 3549.03 | -521.61 | 3549.03 | 1.65 |  |  | 30 | 80 | 400 | 13000 | 185.14 | 4500 | 3800 | 700 | 285.5 | 263 | 213 | 198
06/26/2020 | 16:15 | 17:00 | 0.75 | 13150 | 13175 | 25 | Slide | 0 | 13162 | 95.3 | 337.7 | 10472.45 | 3635.91 | -559.03 | 3635.91 | 2.1 |  |  | 30 | 80 | 400 | 13000 | 33.33 | 4500 | 3800 | 700 | 282.2 | 263 | 213 | 198
06/26/2020 | 17:00 | 17:35 | 0.58333 | 13175 | 13242 | 67 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 114.86 | 4500 | 3800 | 700 | 285.5 | 263 | 213 | 198
06/26/2020 | 17:35 | 18:20 | 0.75 | 13242 | 13260 | 18 | Slide | 0 | 13256 | 92.7 | 339.9 | 10465.89 | 3723.32 | -592.93 | 3723.32 | 3.62 |  |  | 30 | 80 | 400 | 13000 | 24 | 4500 | 3800 | 700 | 289 | 263 | 213 | 198
06/26/2020 | 18:20 | 19:30 | 1.1667 | 13260 | 13535 | 275 | Rotate |  | 13352 | 91.2 | 339.8 | 10462.62 | 3813.39 | -625.98 | 3813.39 | 1.57 |  |  | 30 | 80 | 400 | 13000 | 235.71 | 4800 | 3800 | 1000 | 289 | 263 | 213 | 198
06/26/2020 | 19:30 | 20:10 | 0.66667 | 13535 | 13535 |  | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000 | 4800 | 3800 | 1000 | 289 | 263 | 213 | 198
06/26/2020 | 20:10 | 20:45 | 0.58333 | 13535 | 13620 | 85 | Rotate |  | 13541 | 90.6 | 339.5 | 10459.82 | 3990.43 | -692.09 | 3990.43 | 0.24 |  |  | 30 | 80 | 400 | 13000 | 145.71 | 4800 | 3800 | 1000 | 289 | 263 | 213 | 198
06/26/2020 | 20:45 | 21:45 | 1 | 13620 | 13645 | 25 | Slide | 0 | 13635 | 92.1 | 339.2 | 10457.61 | 4078.36 | -725.23 | 4078.36 | 1.63 |  |  | 30 | 80 | 400 | 13000 | 25 | 4800 | 3800 | 1000 | 292 | 263 | 213 | 198
06/26/2020 | 21:45 | 22:10 | 0.41667 | 13645 | 13726 | 81 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 194.4 | 4800 | 3800 | 1000 | 292 | 263 | 213 | 198
06/26/2020 | 22:10 | 23:00 | 0.83333 | 13726 | 13745 | 19 | Slide | 0 | 13730 | 94.3 | 339.1 | 10452.31 | 4167 | -758.98 | 4167 | 2.32 |  |  | 30 | 80 | 400 | 13000 | 22.8 | 4800 | 3800 | 1000 | 292 | 263 | 213 | 198
06/26/2020 | 23:00 | 23:45 | 0.75 | 13745 | 13919 | 174 | Rotate |  | 13826 | 96 | 337.4 | 10443.69 | 4255.8 | -794.41 | 4255.8 | 2.5 |  |  | 30 | 80 | 400 | 13000 | 232 | 4800 | 3800 | 1000 | 295 | 263 | 213 | 198
06/26/2020 | 23:45 | 24:00 | 0.25 | 13919 | 13920 | 1 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 4 | 4800 | 3800 | 1000 | 295 | 263 | 213 | 198
06/27/2020 | 00:00 | 01:30 | 1.5 | 13920 | 13949 | 29 | Slide | 0 | 13922 | 97.8 | 337 | 10432.16 | 4343.65 | -831.34 | 4343.65 | 1.92 |  |  | 30 | 80 | 400 | 13000 | 19.33 | 4800 | 3800 | 1000 | 292 | 263 | 213 | 198
06/27/2020 | 01:30 | 02:00 | 0.5 | 13949 | 14038 | 89 | Rotate |  | 14018 | 97.4 | 335.7 | 10419.46 | 4430.81 | -869.51 | 4430.81 | 1.41 |  |  | 30 | 80 | 400 | 13000 | 178 | 4800 | 3800 | 1000 | 292 | 263 | 213 | 198
06/27/2020 | 02:05 | 03:20 | 1.25 | 14038 | 14068 | 30 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 24 | 4800 | 3800 | 1000 | 289 | 263 | 213 | 198
06/27/2020 | 03:20 | 03:50 | 0.5 | 14068 | 14146 | 78 | Rotate |  | 14112 | 93.3 | 333.7 | 10410.69 | 4515.4 | -909.5 | 4515.4 | 4.85 |  |  | 30 | 80 | 400 | 13000 | 156 | 4800 | 3800 | 1000 | 290 | 263 | 213 | 198
06/27/2020 | 03:55 | 05:05 | 1.1667 | 14146 | 14166 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 17.14 | 4800 | 3800 | 1000 | 290 | 263 | 213 | 198
06/27/2020 | 05:05 | 05:40 | 0.58333 | 14166 | 14235 | 69 | Rotate |  | 14208 | 90.5 | 332.7 | 10407.51 | 4601.03 | -952.76 | 4601.03 | 3.1 |  |  | 30 | 80 | 400 | 13000 | 118.29 | 4800 | 3800 | 1000 | 290 | 263 | 213 | 198
06/27/2020 | 05:45 | 07:30 | 1.75 | 14235 | 14478 | 243 | Rotate |  | 14302 | 89.9 | 332.7 | 10407.18 | 4684.56 | -995.87 | 4684.56 | 0.64 |  |  | 30 | 80 | 400 | 13000 | 138.86 | 4800 | 3800 | 1000 | 295 | 263 | 213 | 198
06/27/2020 | 07:30 | 08:30 | 1 | 14478 | 14500 | 22 | Slide | 0 | 14491 | 90.5 | 333.3 | 10407.85 | 4852.43 | -1082.7 | 4852.43 | 1.58 |  |  | 30 |  | 400 | 17000 | 22 | 4800 | 3800 | 1000 | 300 | 263 | 213 | 198
06/27/2020 | 08:30 | 10:00 | 1.5 | 14500 | 14665 | 165 | Rotate |  | 14585 | 91.6 | 334.1 | 10406.12 | 4936.68 | -1124.34 | 4936.68 | 1.45 |  |  | 30 | 80 | 400 | 17000 | 110 | 4800 | 3800 | 1000 | 300 | 263 | 213 | 198
06/27/2020 | 10:00 | 11:00 | 1 | 14665 | 14685 | 20 | Slide | 0 | 14681 | 92.7 | 335.4 | 10402.52 | 5023.45 | -1165.26 | 5023.45 | 1.77 |  |  | 30 |  | 400 | 17000 | 20 | 4800 | 3800 | 1000 | 298 | 263 | 213 | 198
06/27/2020 | 11:00 | 12:20 | 1.3333 | 14685 | 14856 | 171 | Rotate |  | 14775 | 94.2 | 336.2 | 10396.87 | 5109.03 | -1203.72 | 5109.03 | 1.81 |  |  | 30 | 80 | 400 | 17000 | 128.25 | 4800 | 3800 | 1000 | 300 | 263 | 213 | 198
06/27/2020 | 12:20 | 13:00 | 0.66667 | 14856 | 14868 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 18 | 4800 | 3800 | 1000 | 298 | 263 | 213 | 198
06/27/2020 | 13:00 | 13:40 | 0.66667 | 14868 | 14950 | 82 | Rotate |  | 14871 | 94.3 | 334.9 | 10389.75 | 5196.18 | -1243.35 | 5196.18 | 1.35 |  |  | 30 | 80 | 400 | 17000 | 123 | 4800 | 3800 | 1000 | 300 | 263 | 213 | 198
06/27/2020 | 13:40 | 14:20 | 0.66667 | 14950 | 14962 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 18 | 4800 | 3800 | 1000 | 298 | 263 | 213 | 198
06/27/2020 | 14:20 | 16:00 | 1.6667 | 14962 | 15236 | 274 | Rotate |  | 14965 | 92.6 | 334.3 | 10384.09 | 5280.93 | -1283.59 | 5280.93 | 1.92 |  |  | 30 | 80 | 400 | 17000 | 164.4 | 4800 | 3800 | 1000 | 300 | 263 | 213 | 198
06/27/2020 | 16:00 | 16:40 | 0.66667 | 15236 | 15248 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 18 | 4800 | 3800 | 1000 | 298 | 263 | 213 | 198
06/27/2020 | 16:40 | 17:00 | 0.33333 | 15248 | 15319 | 71 | Rotate |  | 15250 | 92.9 | 334.1 | 10368.6 | 5537.57 | -1406.55 | 5537.57 | 1.13 |  |  | 30 | 80 | 400 | 17000 | 213 | 4800 | 3800 | 1000 | 300 | 263 | 213 | 198
06/27/2020 | 17:40 | 18:50 | 1.1667 | 15319 | 15527 | 208 | Rotate |  | 15344 | 92.8 | 334.2 | 10363.93 | 5622.06 | -1447.49 | 5622.06 | 0.15 |  |  | 30 | 80 | 400 | 17000 | 178.29 | 4800 | 3800 | 1000 | 305 | 263 | 213 | 198
06/27/2020 | 18:50 | 19:30 | 0.66667 | 15527 | 15535 | 8 | Slide | 0 | 15534 | 94.2 | 332.8 | 10352.16 | 5792.56 | -1530.46 | 5792.56 | 1.99 |  |  | 30 | 80 | 400 | 17000 | 12 | 4800 | 3800 | 1000 | 305 | 263 | 213 | 198
06/27/2020 | 19:30 | 20:00 | 0.5 | 15535 | 15615 | 80 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 160 | 4850 | 4000 | 850 | 305 | 263 | 213 | 198
06/27/2020 | 20:00 | 21:15 | 1.25 | 15615 | 15631 | 16 | Slide | 0 | 15628 | 92.2 | 333.2 | 10346.91 | 5876.18 | -1573.07 | 5876.18 | 2.17 |  |  | 30 | 80 | 400 | 17000 | 12.8 | 4850 | 4000 | 850 | 302 | 263 | 213 | 198
06/27/2020 | 21:15 | 23:15 | 2 | 15631 | 15987 | 356 | Rotate |  | 15722 | 92.4 | 333.5 | 10343.14 | 5960.13 | -1615.2 | 5960.13 | 0.38 |  |  | 30 | 80 | 400 | 17000 | 178 | 4850 | 4000 | 850 | 305 | 263 | 213 | 198
06/27/2020 | 23:15 | 24:00 | 0.75 | 15987 | 15995 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 10.67 | 4850 | 4000 | 850 | 302 | 263 | 213 | 198
06/28/2020 | 00:00 | 01:05 | 1.0833 | 15995 | 16011 | 16 | Slide | 0 | 16006 | 93.1 | 331.9 | 10326.72 | 6210.44 | -1748.28 | 6210.44 | 1.33 |  |  | 30 | 80 | 400 | 17000 | 14.77 | 4850 | 4000 | 850 | 302 | 263 | 213 | 198
06/28/2020 | 01:05 | 01:35 | 0.5 | 16011 | 16080 | 69 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 138 | 4850 | 4000 | 850 | 304 | 263 | 213 | 198
06/28/2020 | 01:35 | 03:20 | 1.75 | 16080 | 16110 | 30 | Slide | 0 | 16100 | 90.6 | 332.7 | 10323.68 | 6293.62 | -1791.95 | 6293.62 | 2.79 |  |  | 30 | 80 | 400 | 17000 | 17.14 | 4850 | 4000 | 850 |  | 263 | 213 | 198
06/28/2020 | 03:20 | 04:30 | 1.1667 | 16110 | 16275 | 165 | Rotate |  | 16195 | 90.2 | 333.4 | 10323.02 | 6378.3 | -1835.01 | 6378.3 | 0.85 |  |  | 30 | 80 | 400 | 17000 | 141.43 | 4850 | 4000 | 850 |  | 263 | 213 | 198
06/28/2020 | 04:30 | 06:25 | 1.9167 | 16275 | 16302 | 27 | Slide | 0 | 16291 | 92.2 | 334.7 | 10321.01 | 6464.6 | -1877 | 6464.6 | 2.48 |  |  | 30 | 80 | 400 | 17000 | 14.09 | 4850 | 4000 | 850 |  | 263 | 213 | 198
06/28/2020 | 06:25 | 07:40 | 1.25 | 16302 | 16460 | 158 | Rotate |  | 16385 | 92.8 | 341.4 | 10316.9 | 6551.65 | -1912.09 | 6551.65 | 7.15 |  |  | 30 | 80 | 400 | 17000 | 126.4 | 4850 | 4000 | 850 | 304 | 263 | 213 | 198
06/28/2020 | 07:40 | 10:00 | 2.3333 | 16460 | 16490 | 30 | Slide | 0 | 16480 | 95 | 345.8 | 10310.44 | 6642.54 | -1938.84 | 6642.54 | 5.17 |  |  | 30 | 80 | 400 | 17000 | 12.86 | 4850 | 4000 | 850 | 302 | 263 | 213 | 198
06/28/2020 | 10:00 | 10:45 | 0.75 | 16490 | 16562 | 72 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 96 | 4850 | 4000 | 850 | 300 | 263 | 213 | 198
06/28/2020 | 10:45 | 13:25 | 2.6667 | 16562 | 16595 | 33 | Slide | 0 | 16574 | 96.1 | 341.7 | 10301.34 | 6732.34 | -1965.01 | 6732.34 | 4.5 |  |  | 30 | 80 | 400 | 17000 | 12.38 | 4850 | 4000 | 850 | 300 | 263 | 213 | 198
06/28/2020 | 13:25 | 14:15 | 0.83333 | 16595 | 16657 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 74.4 | 4850 | 4000 | 850 | 302 | 263 | 213 | 198
06/28/2020 | 14:15 | 16:00 | 1.75 | 16657 | 16684 | 27 | Slide | 0 | 16669 | 95.1 | 336.9 | 10292.07 | 6820.76 | -1998.43 | 6820.76 | 5.14 |  |  | 30 | 80 | 400 | 17000 | 15.43 | 4850 | 4000 | 850 | 298 | 263 | 213 | 198
06/28/2020 | 16:00 | 16:30 | 0.5 | 16684 | 16738 | 54 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 108 | 4850 | 4000 | 850 | 302 | 300 | 210 | 175
06/28/2020 | 17:10 | 17:15 | 0.083333 | 16738 | 16745 | 7 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 84 | 4850 | 4000 | 850 | 302 | 300 | 210 | 175
06/28/2020 | 17:50 | 18:00 | 0.16667 | 16745 | 16751 | 6 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 36 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/28/2020 | 18:00 | 19:30 | 1.5 | 16751 | 16766 | 15 | Slide | 0 | 16764 | 93.9 | 335 | 10284.61 | 6907.24 | -2037.02 | 6907.24 | 2.36 |  |  | 30 | 80 | 400 | 18000 | 10 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/28/2020 | 19:30 | 20:05 | 0.58333 | 16766 | 16836 | 70 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 120 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/28/2020 | 20:05 | 21:05 | 1 | 16836 | 16846 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 10 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/28/2020 | 21:05 | 23:00 | 1.9167 | 16846 | 17125 | 279 | Rotate |  | 16860 | 91.3 | 332 | 10280.26 | 6993.04 | -2079.81 | 6993.04 | 4.13 |  |  | 30 | 80 | 400 | 18000 | 145.57 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/28/2020 | 23:00 | 24:00 | 1 | 17125 | 17138 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 13 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 00:00 | 01:00 | 1 | 17138 | 17147 | 9 | Slide | 0 | 17145 | 91.8 | 334.5 | 10271.72 | 7245.14 | -2212.42 | 7245.14 | 2.92 |  |  | 30 | 80 | 400 | 18000 | 9 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 01:00 | 01:20 | 0.33333 | 17147 | 17214 | 67 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 201 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 01:35 | 03:00 | 1.4167 | 17214 | 17410 | 196 | Rotate |  | 17239 | 93.7 | 337.1 | 10267.21 | 7330.77 | -2250.9 | 7330.77 | 3.42 |  |  | 30 | 80 | 400 | 18000 | 138.35 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 03:00 | 04:20 | 1.3333 | 17410 | 17425 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 11.25 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 04:20 | 05:00 | 0.66667 | 17425 | 17505 | 80 | Rotate |  | 17427 | 94.5 | 335.3 | 10252.13 | 7502.93 | -2324.87 | 7502.93 | 2.21 |  |  | 30 | 80 | 400 | 18000 | 120 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 05:00 | 05:55 | 0.91667 | 17505 | 17515 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 10.91 | 4850 | 4000 | 850 | 306 | 300 | 210 | 175
06/29/2020 | 05:55 | 09:00 | 3.0833 | 17515 | 17886 | 371 | Rotate |  | 17522 | 92.2 | 333.4 | 10246.58 | 7588.41 | -2365.92 | 7588.41 | 3.14 |  |  | 30 | 80 | 400 | 18000 | 120.32 | 4850 | 4000 | 850 | 315 | 300 | 210 | 175