## Summary
Magnolia Oil & Gas / Mill H08 / LTX1105822 / Patterson 248
Report Date: | 03/25/2022 | Current Depth: | 19429.04
Start Date: | 02/01/2022 | Casing Depth: | 2818
Daily Cost: | 10000 | Distance to TD:
Well Cost: | 154230 | Average ROP: | 200.11
Drilling Hours: | 11.62 | Svy MD: | 19327
24Hr Forcast: | End of Job | Svy Inc: | 85.32
Current BHA: | BHA 4 | Svy Azi: | 133.88
Current BRT Hrs: | 52 | Svy TVD: | 11103.85
Bit Make / Model: | Halliburton / GTD64M | Svy NS: | -6132.47
POOH in last 24Hrs: | Yes | Svy EW: | 6855.89
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | Water | Svy Left/Right: | 0
Directional Driller Day: | Jesse Taylor | MWD Day: | Danny Veronie
Directional Driller Night: | Marshall Adams | MWD Night: | A Mejia B Kitzman
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 293
24Hr Summary: | Drill Lateral to TD - POOH | Max BHT 24Hrs: | 161.6
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
775234 | UBHO Sub | PDCI |  | Dirty |  | 42.38 | 42.38
775240 | UBHO Sub | PDCI |  | Clean
500056 | UBHO Sub | PDCI |  | Clean
500070 | UBHO Sub | PDCI |  | Clean
500057 | UBHO Sub | PDCI |  | Clean
500065 | UBHO Sub | PDCI |  | Dirty |  | 103.73 | 103.73
500068 | UBHO Sub | PDCI | On rig floor | Clean
500065 | UBHO Sub |  |  | Dirty |  | 103.73 | 103.73

## Well Summary
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Mill H08
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Total Drilled (Usft): |  | 19321.04 |  |  | Total Days: |  | 14
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 2828 | 2720 |  | 655.42 |  | 7.61 | 4.15 | 3.47 | 10.17
2 | 2 | 9.875 | 2828 | 10230 | 7402 |  | 275 |  | 9.2 | 26.92 | 7.85 | 50
3 | 3 | 6.75 | 10230 | 17890 | 7660 |  | 133.37 |  | 16.57 | 57.43 | 25.8 | 142
4 | 4 | 6.75 | 17890 | 19429.04 | 1539.04 |  | 132.49 |  | 7.8 | 11.62 | 8.88 | 52
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | 0-0-NO-A-X-I-NO-TD |  | 0-0-NO-A-X-I-NO-TD |  | 1.353 | 2720 | 4.15 | 655.42
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 1-1-WT-A-X-I-NO-TD |  | 1.491 | 7402 | 26.9167 | 275
3 | Halliburton |  | GTD64M |  | 6.75 | New |  | 1-1-CT-S-X-I-NO-DMF |  | 1.491 | 7660 | 57.4333 | 133.37
4 | Halliburton |  | GTD64M |  | 6.75 | New |  | 3-3-CT-N-X-I-LT-TD |  | 1.491 | 1539.04 | 11.6167 | 132.49
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.82 | 2720 |  | 655.42
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 6.04 | 7402 |  | 275
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.25 | 2.12 | 4.11 | 7660 |  | 133.37
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5 | 2.12 | 4.1 | 1539.04 |  | 132.49
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | Marshall Adams |  | Danny Veronie |  | A Mejia B Kitzman |  | Brandon Parks |  | Chris Mayeux |  | Peter Langille
Josh Ray | [5 empty] | Rick Montijo |  | Kevin Burt |  | Jim Harrison
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 0.75 / 0.32 |  | 2720 |  | 655.42 |  |  |  | 1 |  | 4.15
INT: INTERMEDIATE |  |  | 2.15 / 1.06 |  | 6907 |  | 353.48 |  | 0.72 / 0.00 |  | 1 |  | 19.54
CRV: CURVE |  |  | 1.85 / 0.39 |  | 495 |  | 67.16 |  | 1.29 / 0.00 |  | 1 |  | 7.37
CRV2: CURVE 2 |  |  | 1.40 / 0.40 |  | 900 |  | 114.07 |  |  |  | 1 |  | 7.89
LAT: LATERAL |  |  | 7.61 / 6.62 |  | 8299.04 |  | 135.69 |  | 23.59 / 0.00 |  | 2 |  | 61.16
Total |  |  | 13.75 |  | 19321.04 |  | 193 |  | 25.60 / 0.00 |  | 4 |  | 100.11
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 2828.00 | 741.30 | 2513.00 | 272.37 | 207.00 | 7.61 | 2720.00 | 655.42 | 4.15 | 0.76
INT: INTERMEDIATE-BHA 2 |  |  | 2828.00 | 9735.00 | 437.95 | 6543.00 | 79.13 | 364.00 | 5.27 | 6907.00 | 353.48 | 19.54 | 4.60
CRV: CURVE-BHA 2 |  |  | 9735.00 | 10230.00 | 136.92 | 178.00 | 52.22 | 317.00 | 64.04 | 495.00 | 67.16 | 7.37 | 6.07
CRV2: CURVE 2-BHA 3 |  |  | 10230.00 | 11130.00 | 147.24 | 240.00 | 105.43 | 660.00 | 73.33 | 900.00 | 114.07 | 7.89 | 6.26
LAT: LATERAL-BHA 3 |  |  | 11130.00 | 17890.00 | 182.25 | 6151.00 | 38.57 | 609.00 | 9.01 | 6760.00 | 136.46 | 49.54 | 15.79
LAT: LATERAL-BHA 4 |  |  | 17890.00 | 19429.04 | 158.73 | 1419.04 | 44.78 | 120.00 | 7.80 | 1539.04 | 132.45 | 11.62 | 2.68
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1105822 | Total Drilled(Usft) | 19321.04
Operator | Magnolia Oil & Gas | Drilling Hours | 100.12
Well Name | Mill H08 | Avg ROP(Usft/hr) | 192.99
Rig | Patterson 248 | Rotary Drilled(Usft) | 17044.04
State | Texas | Rotary Hours | 63.93
County | Washington | Rotary ROP(Usft/hr) | 266.59
Formation | Austin Chalk | Rotary % | 88.21
Start Date | 02/01/2022 | Slide Drilled(Usft) | 2277.00
End Date | 03/25/2022 | Slide Hours | 36.18
Days On Well | 14 | Slide ROP(Usft/hr) | 62.93
Start Depth (Usft) | 108.00 | Slide % | 11.79
End Depth (Usft) | 19429.04
Total Drilled (Usft) | 19321.04
# BHA's | 4
# Motor Failures | 1
# MWD Failures | 0
NPT hrs (Rig/Dir) | 26.88 / 0.00
Phase Data
Phase | SUR | INT | CRV | CRV2 | LAT
Start Date | 02/01/2022 | 02/02/2022 | 02/04/2022 | 03/17/2022 | 03/18/2022
End Date | 02/01/2022 | 02/04/2022 | 02/05/2022 | 03/18/2022 | 03/25/2022
Total Days | 0.75 | 2.15 | 1.85 | 1.40 | 7.60
Start Depth (Usft) | 108.00 | 2828.00 | 9735.00 | 10230.00 | 11130.00
End Depth (Usft) | 2828.00 | 9735.00 | 10230.00 | 11130.00 | 19429.04
Total Drilled(Usft) | 2720.00 | 6907.00 | 495.00 | 900.00 | 8299.04
Drilling Hours | 4.15 | 19.55 | 7.37 | 7.90 | 61.15
Circulating Hours | 3.47 | 5.90 | 1.95 | 3.37 | 31.32
Total D&C Hours | 7.62 | 25.45 | 9.32 | 11.27 | 92.47
Avg ROP(Usft/hr) | 655.42 | 353.30 | 67.19 | 113.92 | 135.72
Rotary Drilled(Usft) | 2513.00 | 6543.00 | 178.00 | 240.00 | 7570.04
Rotary Hours | 3.40 | 14.95 | 1.30 | 1.63 | 42.65
Rotary ROP(Usft/hr) | 739.12 | 437.66 | 136.92 | 146.94 | 177.49
Rotary % | 92.39 | 94.73 | 35.96 | 26.67 | 91.22
Slide Drilled(Usft) | 207.00 | 364.00 | 317.00 | 660.00 | 729.00
Slide Hours | 0.75 | 4.60 | 6.07 | 6.27 | 18.50
Slide ROP(Usft/hr) | 276.00 | 79.13 | 52.25 | 105.32 | 39.41
Slide % | 7.61 | 5.27 | 64.04 | 73.33 | 8.78
# BHA | 1 | 1 | 1 | 1 | 2
# Motor Failures | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 0.72 / 0.00 | 1.28 / 0.00 | 0.00 / 0.00 | 24.88 / 0.00
Total Phase Hrs | 7.73 | 25.55 | 9.30 | 9.50 | 159.00
Phase ROP (Usft/hr) | 351.72 | 270.33 | 53.23 | 94.74 | 52.20
Avg Motor Yield (°/100ft) | 7.72 | 8.83 | 9.11 | 11.63 | 22.32
Avg Rotary DLS (°/100ft) | 0.50 | 0.39 | 0.00 | 0.00 | 1.00
Avg Rotary TF | 83.61 | -12.57 | 0.00 | 0.00 | -54.17
Avg Slide Length (Usft) | 17.25 | 15.83 | 45.29 | 66.00 | 16.20
# Slides | 12 | 23 | 7 | 10 | 45
BHA Data
BHA# | 1 | 2 | 3 | 4
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4
Bit Size | 13.500 | 9.875 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Halliburton / GTD64M | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491
Grade In | 0-0-NO-A-X-I-NO-TD | New | New | New
Grade Out | 0-0-NO-A-X-I-NO-TD | 1-1-WT-A-X-I-NO-TD | 1-1-CT-S-X-I-NO-DMF | 3-3-CT-N-X-I-LT-TD
Motor SN | PPM800035 | MTR775009 | PPM250003 | PPM250005
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 5.00 / 16.50 / 25.00 | 2.00 / 28.27 / 42.00 | 10.00 / 29.40 / 50.00 | 25.00 / 25.00 / 25.00
Diff P (psi) | 100.00 / 302.78 / 500.00 | 31.22 / 427.67 / 800.00 | 3.91 / 540.10 / 1961.13 | 2.14 / 1122.11 / 2748.50
Bend | 1.500 | 2.000 | 2.120 | 2.120
Date In | 02/01/2022 | 02/02/2022 | 03/17/2022 | 03/23/2022
Date Out | 02/01/2022 | 02/04/2022 | 03/23/2022 | 03/25/2022
Time In | 11:20 | 20:00 | 14:45 | 19:30
Time Out | 21:30 | 22:00 | 12:45 | 23:30
BRT Hrs | 10.17 | 50.00 | 142.00 | 52.00
Start Depth (Usft) | 108.00 | 2828.00 | 10230.00 | 17890.00
End Depth (Usft) | 2828.00 | 10230.00 | 17890.00 | 19429.04
Total Drilled(Usft) | 2720.00 | 7402.00 | 7660.00 | 1539.04
Drilling Hours | 4.15 | 26.92 | 57.43 | 11.62
Circulating Hours | 3.47 | 7.85 | 25.80 | 8.88
Total D&C Hours | 7.62 | 34.77 | 83.23 | 20.50
Avg ROP(Usft/hr) | 655.42 | 275.00 | 133.37 | 132.49
Rotary Drilled(Usft) | 2513.00 | 6721.00 | 6391.00 | 1419.04
Rotary Hours | 3.40 | 16.25 | 35.35 | 8.93
Rotary ROP(Usft/hr) | 739.12 | 413.60 | 180.79 | 158.85
Rotary % | 92.39 | 90.80 | 83.43 | 92.20
Slide Drilled(Usft) | 207.00 | 681.00 | 1269.00 | 120.00
Slide Hours | 0.75 | 10.67 | 22.08 | 2.68
Slide ROP(Usft/hr) | 276.00 | 63.84 | 57.46 | 44.72
Slide % | 7.61 | 9.20 | 16.57 | 7.80
Motor Failure | NO | NO | YES | NO
MWD Failure | NO | NO | NO | NO
Unplanned Trip | NO | NO | NO | NO
LIH | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 7.72 | 8.88 | 21.33 | 17.40
Avg Rotary DLS (°/100ft) | 0.50 | 0.39 | 1.09 | 0.66
Avg Rotary TF | 83.61 | -12.57 | -36.27 | -130.21
Avg Slide Length (Usft) | 17.25 | 22.70 | 26.44 | 17.14
# Slides | 12 | 30 | 48 | 7

## Personnel Report
|  | Job # | LTX1105822 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31194 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Mill H08
|  | Date: | 03/25/2022 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Mill H08 - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
A Mejia B Kitzman | Night MWD |  | 03/20/2022 - 00:00 | 03/25/2022 - 00:00 |  | 6.00 / 0.00
Danny Veronie | Day MWD |  | 02/01/2022 - 00:00 | 02/05/2022 - 00:00 |  | 5.00 / 0.00
Danny Veronie | Day MWD |  | 03/17/2022 - 00:00 | 03/25/2022 - 00:00 |  | 9.00 / 0.00
Jesse Taylor | Day DD |  | 03/19/2022 - 00:00 | 03/25/2022 - 00:00 |  | 7.00 / 0.00
Josh Ray | Day DD |  | 02/01/2022 - 00:00 | 02/05/2022 - 00:00 |  | 5.00 / 0.00
Josh Ray | Day DD |  | 03/17/2022 - 00:00 | 03/18/2022 - 00:00 |  | 2.00 / 0.00
Marshall Adams | Night DD |  | 02/01/2022 - 00:00 | 02/05/2022 - 00:00 |  | 5.00 / 0.00
Marshall Adams | Night DD |  | 03/17/2022 - 00:00 | 03/25/2022 - 00:00 |  | 9.00 / 0.00
NA | Trainee 1 |  | 02/01/2022 - 00:00 | 02/05/2022 - 24:00 |  | 5.00 / 120.00
NA | Trainee 1 |  | 03/17/2022 - 00:00 | 03/25/2022 - 24:00 |  | 9.00 / 216.00
NA | Trainee 2 |  | 02/01/2022 - 00:00 | 02/05/2022 - 24:00 |  | 5.00 / 120.00
NA | Trainee 2 |  | 03/17/2022 - 00:00 | 03/25/2022 - 24:00 |  | 9.00 / 216.00
NA | Rss Eng. 1 |  | 02/01/2022 - 00:00 | 02/05/2022 - 24:00 |  | 5.00 / 120.00
NA | Rss Eng. 1 |  | 03/17/2022 - 00:00 | 03/25/2022 - 24:00 |  | 9.00 / 216.00
NA | Rss Eng. 2 |  | 02/01/2022 - 00:00 | 02/05/2022 - 24:00 |  | 5.00 / 120.00
NA | Rss Eng. 2 |  | 03/17/2022 - 00:00 | 03/25/2022 - 24:00 |  | 9.00 / 216.00
NA | Third Man |  | 02/01/2022 - 00:00 | 02/05/2022 - 24:00 |  | 5.00 / 120.00
NA | Third Man |  | 03/17/2022 - 00:00 | 03/25/2022 - 24:00 |  | 9.00 / 216.00
NA | Fourth Man |  | 02/01/2022 - 00:00 | 02/05/2022 - 24:00 |  | 5.00 / 120.00
NA | Fourth Man |  | 03/17/2022 - 00:00 | 03/25/2022 - 24:00 |  | 9.00 / 216.00
Rick Montijo | Night MWD |  | 02/01/2022 - 00:00 | 02/05/2022 - 00:00 |  | 5.00 / 0.00
Rick Montijo | Night MWD |  | 03/17/2022 - 00:00 | 03/19/2022 - 00:00 |  | 3.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1105822 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Mill H08 | [7 empty] | Day DD: |  |  |  |  | Jesse Taylor | [5 empty] | API #: |  |  |  | 42-477-31194
|  |  |  | AFE #: |  |  | 21DD0262MG | [7 empty] | Night DD: |  |  |  |  | Marshall Adams | [5 empty] | Company Man: |  |  |  | Kevin Burt
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | A Mejia B Kitzman | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 02/01/2022 | 02/02/2022 | 02/03/2022 | 02/04/2022 | 02/05/2022 | 02/06/2022 | 02/07/2022 | 02/08/2022 | 02/09/2022 | 02/10/2022 | 02/11/2022 | 02/12/2022 | 02/13/2022 | 02/14/2022 | 02/15/2022 | 02/16/2022 | 02/17/2022 | 02/18/2022 | 02/19/2022 | 02/20/2022 | 02/21/2022 | 02/22/2022 | 02/23/2022 | 02/24/2022 | 02/25/2022 | 02/26/2022 | 02/27/2022 | 02/28/2022 | 03/01/2022 | 03/02/2022 | 03/03/2022 | 03/04/2022 | 03/05/2022 | 03/06/2022 | 03/07/2022 | 03/08/2022 | 03/09/2022 | 03/10/2022 | 03/11/2022 | 03/12/2022 | 03/13/2022 | 03/14/2022 | 03/15/2022 | 03/16/2022 | 03/17/2022 | 03/18/2022 | 03/19/2022 | 03/20/2022 | 03/21/2022 | 03/22/2022 | 03/23/2022 | 03/24/2022 | 03/25/2022 | 03/26/2022
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit | Ulterra | 13.5 | U616S |  | Steel | 47245 | 1 | 4 | X | O | O | O
Bit | Ulterra | 9.875 | SPL613 |  | Steel | 59253 | 3 | 4 | O | X | X | X
Bit | Halliburton | 6.75 | GTD64M |  | Steel | 13711499 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Bit | Halliburton | 6.75 | GTD64M |  | Steel | 13618579 | 3 | 8 | [45 empty] | O | O | O | O | O | X | X | X
Cross Over | Gator | 7.688 | Crossover Sub |  | Steel | GT7746831 | 1 | 4 | X | O | O | O
Cross Over | Gator | 7.812 | Crossover Sub |  | Steel | GT8046231 | 0 | 4 | O | O | O | O
Cross Over | Gator | 7.938 | Crossover Sub |  | Steel | GT8046294 | 3 | 4 | O | X | X | X
Cross Over | Gator | 7.875 | Crossover Sub |  | Steel | GT8046642 | 0 | 4 | O | O | O | O
Cross Over | Gator | 6.75 | Crossover Sub |  | Steel | GT6744398 | 0 | 4 | O | O | O | O
Cross Over | Gator | 6.75 | Crossover Sub |  | Steel | GT6744705 | 0 | 4 | O | O | O | O
Cross Over | Gator | 6.688 | Crossover Sub |  | Steel | GT6744684 | 3 | 4 | O | X | X | X
Cross Over | Gator | 6.688 | Crossover Sub |  | Steel | GT6744908 | 0 | 4 | O | O | O | O
Cross Over | Gator | 5.312 | Crossover |  | Steel | GT52331433 | 9 | 10 | [43 empty] | O | X | X | X | X | X | X | X | X | X
Cross Over | Gator | 5.188 | Crossover |  | Steel | GT52331431 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over | Gator | 5.312 | Crossover |  | Steel | GT52331100 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | GT52331432 | 0 | 7 | [46 empty] | O | O | O | O | O | O | O
MWD / LWD | PDCI | 7.75 | UBHO Sub |  | Steel | 775234 | 4 | 4 | X | X | X | X
MWD / LWD | PDCI | 7.75 | UBHO Sub |  | Steel | 775240 | 0 | 4 | O | O | O | O
MWD / LWD | PDCI | 5 | UBHO Sub |  | Steel | 500056 | 0 | 4 | O | O | O | O
MWD / LWD | PDCI | 5 | UBHO Sub |  | Steel | 500070 | 0 | 4 | O | O | O | O
MWD / LWD | PDCI | 5.25 | UBHO Sub |  | Steel | 500057 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
MWD / LWD | PDCI | 5.25 | UBHO Sub |  | Steel | 500065 | 9 | 10 | [43 empty] | O | X | X | X | X | X | X | X | X | X
MWD / LWD | PDCI | 5.188 | UBHO Sub |  | Steel | 500068 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5 | UBHO Sub |  | Steel | 500065 | 9 | 7 | [44 empty] | X | X | X | X | X | X | X | X | X
Motor | PDCI | 8 | 7/8 5.9 2.0 TS HPW +.002 |  | Steel | PPM800005 | 0 | 4 | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.0 TS HPW -.012 |  | Steel | MTR775009 | 3 | 4 | O | X | X | X
Motor | PDCI | 8 | 7/8 5.9 2.0 TS HPW -.013 |  | Steel | MTR775026 | 0 | 4 | O | O | O | O
Motor | PDCI | 5 | 5.5 6/7 8.8 2.12 TS HS88 +.024 |  | Steel | PPM250030 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Motor | PDCI | 5 | 5.5 6/7 8.8 2.12 TS HS88 -.004 |  | Steel | PPM250005 | 3 | 10 | [43 empty] | O | O | O | O | O | O | O | X | X | X
Motor | PDCI | 5.25 | 5.5 6/7 8.8 2.12 TS HS88 +.002 |  | Steel | PPM250003 | 7 | 10 | [43 empty] | O | X | X | X | X | X | X | X | O | O
Motor | PDCI | 5.25 | 5.5 6/7 8.8 2.12 TS HS88 0.000 |  | Steel | PPM250032 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Motor | PDCI | 4.938 | 5 7/8 4.5 2.50 TS HPW -.004 |  | Steel | MTR475107 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Motor | PDCI | 5 | 5.5 6/7 8.8 2.12 TS HS88 +.015 |  | Steel | PPM250004 | 0 | 7 | [46 empty] | O | O | O | O | O | O | O
Collar | Gator | 7.938 | Drill Collar (NO HARDBANDING) |  | Steel | GT80-30-378 | 4 | 4 | X | X | X | X
Collar | Gator | 8 | Drill Collar (NO HARDBANDING) |  | Steel | GT80-30-171 | 4 | 4 | X | X | X | X
Collar | Gator | 8 | Drill Collar (NO HARDBANDING) |  | Steel | GT80-30-593 | 0 | 4 | O | O | O | O
Collar | Gator | 8 | Drill Collar (NO HARDBANDING) |  | Steel | GT80-30-627 | 0 | 4 | O | O | O | O
Collar | Gator | 8 | Pony Collar (NO HARDBANDING) |  | Steel | GT80-10-369 | 0 | 4 | O | O | O | O
Collar | Gator | 8 | Pony Collar (NO HARDBANDING) |  | Steel | GT80-10-648 | 4 | 4 | X | X | X | X
Collar | RIG | 6.5 | 6 Jts 6 1/2in DC |  | Steel | 6DC | 3 | 4 | O | X | X | X
Collar | Gator | 5.188 | Non Mag Drill Collar |  | Non-Mag | GT51-30-697 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Collar | Gator | 5.188 | Non Mag Drill Collar |  | Non-Mag | GT51-30-698 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Collar | Gator | 5.25 | Non Mag Drill Collar |  | Non-Mag | GT52-30-458 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Collar | Gator | 5.25 | Non Mag Drill Collar |  | Non-Mag | GT52-30-606 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Collar | Gator | 5 | Non Mag Drill Collar |  | Non-Mag | GT50-30-722 | 9 | 10 | [43 empty] | O | X | X | X | X | X | X | X | X | X
Collar | Gator | 5 | Non Mag Drill Collar |  | Non-Mag | GT50-30-707 | 9 | 10 | [43 empty] | O | X | X | X | X | X | X | X | X | X
Collar | Gator | 5 | Non Mag Pony Collar |  | Non-Mag | GT50-10-465 | 9 | 10 | [43 empty] | O | X | X | X | X | X | X | X | X | X
Collar | Gator | 5 | Non Mag Pony Collar |  | Non-Mag | GT50-10-585 | 7 | 10 | [43 empty] | O | X | X | X | X | X | X | X | O | O
Collar | Gator | 5 | Non Mag Pony Collar |  | Non-Mag | GT50-10-654 | 0 | 4 | [43 empty] | O | O | O | O
Collar | Gator | 5 | Non Mag Pony Collar |  | Non-Mag | GT50-10-477 | 0 | 4 | [43 empty] | O | O | O | O
Collar |  | 5 | Non Mag Pony Collar |  | Non-Mag | GT50-10-637 | 0 | 7 | [46 empty] | O | O | O | O | O | O | O
Collar |  | 5 | Non Mag Pony Collar |  | Non-Mag | GT50-10-479 | 0 | 7 | [46 empty] | O | O | O | O | O | O | O
Collar |  | 5 | Non Mag Drill Collar |  | Non-Mag | GT51-30-695 | 0 | 7 | [46 empty] | O | O | O | O | O | O | O
Collar |  | 5 | Non Mag Drill Collar |  | Non-Mag | GT51-30-696 | 0 | 7 | [46 empty] | O | O | O | O | O | O | O
Drill Pipe |  | 5 | 11 Jts 5 HWDP |  | Steel | Rig1 | 0 | 4 | O | O | O | O
Drill Pipe | RIG | 5 | 22 Stds 5in DP |  | Steel | Rig2 | 0 | 4 | O | O | O | O
Drill Pipe |  | 4.5 | 28 Stands DP |  | Steel | Rig28 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub | Gator | 8 | Float Sub |  | Steel | GT8066003F | 0 | 4 | O | O | O | O
Sub | Gator | 8 | Float Sub |  | Steel | GT8066004F | 0 | 4 | O | O | O | O
Sub | Gator | 8 | Lift Sub |  | Steel | GT80300 | 0 | 4 | O | O | O | O
Sub | Gator | 8 | Lift Sub |  | Steel | GT80656 | 0 | 4 | O | O | O | O
Sub | Gator |  | Lift Cap |  | Steel | GT222 | 0 | 4 | O | O | O | O
Sub | Gator | 5 | Float Sub |  | Steel | GT50331297FF | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub | Gator |  | Float Sub |  | Steel | GT52331248FF | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub | Gator | 5.5 | Lift Sub |  | Steel | GT551251 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub | Gator | 5.5 | Lift Sub |  | Steel | GT551232 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub | Gator |  | Lift Cap |  | Steel | GT225 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub | Tomax | 5 | ToMax |  | Steel | A52180 | 9 | 10 | [43 empty] | O | X | X | X | X | X | X | X | X | X
Sub | Tomax | 5 | ToMax |  | Steel | A52105 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI |  | Steel | BTI01 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI |  | Steel | BTI03 | 3 | 10 | [43 empty] | O | O | O | O | O | O | O | X | X | X
Sub | Tomax | 5 | ToMax |  | Steel | A52130 | 0 | 8 | [45 empty] | O | O | O | O | O | O | O | O
Agitator | DWS | 6.75 | Agitator |  | Steel | PG675-0050 | 3 | 4 | O | X | X | X
Agitator | DWS | 6.75 | Agitator |  | Steel | PG675-0029 | 0 | 4 | O | O | O | O
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0037 | 3 | 10 | [43 empty] | O | O | O | O | O | O | O | X | X | X
Agitator |  | 5.25 | Agitator |  | Steel | PG525-0056 | 7 | 10 | [43 empty] | O | X | X | X | X | X | X | X | O | O
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0079 | 0 | 10 | [43 empty] | O | O | O | O | O | O | O | O | O | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 7 | [47 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Josh Ray |  |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | [39 empty] | 1 | 1
Night DD |  |  | Marshall Adams |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | A Mejia B Kitzman |  |  |  | 6 | [48 empty] | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Rick Montijo |  |  |  | 8 |  | 1 | 1 | 1 | 1 | 1 | [39 empty] | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Mill H08
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0262MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
PPM800005 | 7/8 5.9 2.0 TS HPW +.002 | 8 | 37.37 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 02/01/2022 |  | 02/04/2022
MTR775009 | 7/8 5.9 2.0 TS HPW -.012 | 8 | 37.54 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / Pro Power | 02/01/2022 |  | 02/04/2022
MTR775026 | 7/8 5.9 2.0 TS HPW -.013 | 8 | 37.65 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 02/01/2022 |  | 02/04/2022
GT80-30-378 | Drill Collar (NO HARDBANDING) | 7.938 | 29.59 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Gator / NMDC | 02/01/2022 |  | 02/04/2022
GT80-30-171 | Drill Collar (NO HARDBANDING) | 8 | 29.64 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Gator / NMDC | 02/01/2022 |  | 02/04/2022
GT80-30-593 | Drill Collar (NO HARDBANDING) | 8 | 30.33 |  | 6 5/8 REG / 6 5/8 REG | Clean | Gator / NMDC | 02/01/2022 |  | 02/04/2022
GT80-30-627 | Drill Collar (NO HARDBANDING) | 8 | 31.07 |  | 6 5/8 REG / 6 5/8 REG | Clean | Gator / NMDC | 02/01/2022 |  | 02/04/2022
GT80-10-369 | Pony Collar (NO HARDBANDING) | 8 | 9.14 |  | 6 5/8 REG / 6 5/8 REG | Clean | Gator / NMPC | 02/01/2022 |  | 02/04/2022
GT80-10-648 | Pony Collar (NO HARDBANDING) | 8 | 9.99 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Gator / NMPC | 02/01/2022 |  | 02/04/2022
GT7746831 | Crossover Sub | 7.688 | 3.17 |  | 4 1/2 IF / 6 5/8 REG | Dirty | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT8046231 | Crossover Sub | 7.812 | 3.19 |  | 4 1/2 IF / 6 5/8 REG | Clean | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT8046294 | Crossover Sub | 7.938 | 3.18 |  | 4 1/2 XH / 6 5/8 REG | Dirty | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT8046642 | Crossover Sub | 7.875 | 3.32 |  | 4 1/2 XH / 6 5/8 REG | Clean | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT6744398 | Crossover Sub | 6.75 | 3.65 |  | 4 1/2 XH / 4 1/2 IF | Clean | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT6744705 | Crossover Sub | 6.75 | 3.22 |  | 4 1/2 XH / 4 1/2 IF | Clean | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT6744684 | Crossover Sub | 6.688 | 3.2 |  | 4 1/2 IF / 4 1/2 XH | Dirty | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
GT6744908 | Crossover Sub | 6.688 | 3.49 |  | 4 1/2 IF / 4 1/2 XH | Clean | Gator / XO Sub | 02/01/2022 |  | 02/04/2022
775234 | UBHO Sub | 7.75 | 3.96 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / UBHO Sub | 02/01/2022 |  | 02/04/2022
775240 | UBHO Sub | 7.75 | 4 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / UBHO Sub | 02/01/2022 |  | 02/04/2022
500056 | UBHO Sub | 5 |  |  | XT39 / XT39 | Clean | PDCI / UBHO Sub | 02/01/2022 |  | 02/04/2022
500070 | UBHO Sub | 5 |  |  | XT39 / XT39 | Clean | PDCI / UBHO Sub | 02/01/2022 |  | 02/04/2022
GT8066003F | Float Sub | 8 |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Gator / Float Sub | 02/01/2022 |  | 02/04/2022
GT8066004F | Float Sub | 8 |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Gator / Float Sub | 02/01/2022 |  | 02/04/2022
GT80300 | Lift Sub | 8 | 3.3 |  | 6 5/8 REG | Clean | Gator / 5 OD Neck | 02/01/2022 |  | 02/04/2022
GT80656 | Lift Sub | 8 | 2.86 |  | 6 5/8 REG | Clean | Gator / 5 OD Neck | 02/01/2022 |  | 02/04/2022
GT222 | Lift Cap |  |  |  | 6 5/8 REG | Clean | Gator | 02/01/2022 |  | 02/04/2022
47245 | U616S | 13.5 | 1.5 |  | 6 5/8 REG | Dirty | Ulterra / U616S | 02/01/2022 |  | 02/04/2022
Rig1 | 11 Jts 5 HWDP | 5 | 334.01 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 02/01/2022 |  | 02/04/2022
PG675-0050 | Agitator | 6.75 | 22.46 |  | 4 1/2 IF / 4 1/2 IF | Dirty | DWS / Power Glide | 02/01/2022 |  | 02/04/2022
PG675-0029 | Agitator | 6.75 | 22.14 |  | 4 1/2 IF / 4 1/2 IF | Clean | DWS / Power Glide | 02/01/2022 |  | 02/04/2022
59253 | SPL613 | 9.875 | 1.5 |  | 6 5/8 REG | Dirty | Ulterra / SPL613 | 02/01/2022 |  | 02/04/2022
6DC | 6 Jts 6 1/2in DC | 6.5 | 186.19 |  | 4 1/2 XH / 4 1/2 XH | Dirty | RIG | 02/01/2022 |  | 02/04/2022
Rig2 | 22 Stds 5in DP | 5 | 2065.88 |  | 4 1/2 IF / 4 1/2 IF | Dirty | RIG | 02/01/2022 |  | 02/04/2022
PPM250030 | 5.5 6/7 8.8 2.12 TS HS88 +.024 | 5 | 33.09 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 03/16/2022 |  | 03/25/2022
PPM250005 | 5.5 6/7 8.8 2.12 TS HS88 -.004 | 5 | 33.16 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 03/16/2022 |  | 03/25/2022
PPM250003 | 5.5 6/7 8.8 2.12 TS HS88 +.002 | 5.25 | 33.26 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 03/16/2022 |  | 03/25/2022
PPM250032 | 5.5 6/7 8.8 2.12 TS HS88 0.000 | 5.25 | 33.26 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 03/16/2022
MTR475107 | 5 7/8 4.5 2.50 TS HPW -.004 | 4.938 | 29.8 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 03/16/2022 |  | 03/25/2022
GT51-30-697 | Non Mag Drill Collar | 5.188 | 31.17 |  | XT39 / XT39 | Clean | Gator / NMDC | 03/16/2022 |  | 03/25/2022
GT51-30-698 | Non Mag Drill Collar | 5.188 | 31.1 |  | XT39 / XT39 | Clean | Gator / NMDC | 03/16/2022 |  | 03/25/2022
GT52-30-458 | Non Mag Drill Collar | 5.25 | 30.42 |  | XT39 / XT39 | Clean | Gator / NMDC | 03/16/2022
GT52-30-606 | Non Mag Drill Collar | 5.25 | 31.02 |  | XT39 / XT39 | Clean | Gator / NMDC | 03/16/2022
GT50-30-722 | Non Mag Drill Collar | 5 | 31.42 |  | XT39 / XT39 | Dirty | Gator / NMDC | 03/16/2022 |  | 03/25/2022
GT50-30-707 | Non Mag Drill Collar | 5 | 31.38 |  | XT39 / XT39 | Dirty | Gator / NMDC | 03/16/2022 |  | 03/25/2022
GT50-10-465 | Non Mag Pony Collar | 5 | 9.46 |  | XT39 / XT39 | Dirty | Gator / NMPC | 03/16/2022 |  | 03/25/2022
GT50-10-585 | Non Mag Pony Collar | 5 | 9.34 |  | XT39 / XT39 | Dirty | Gator / NMPC | 03/16/2022 |  | 03/25/2022
GT50-10-654 | Non Mag Pony Collar | 5 | 9.29 |  | XT39 / XT39 | Clean | Gator / NMPC | 03/16/2022 |  | 03/19/2022
GT50-10-477 | Non Mag Pony Collar | 5 | 9.59 |  | XT39 / XT39 | Clean | Gator / NMPC | 03/16/2022 |  | 03/19/2022
500057 | UBHO Sub | 5.25 | 3.94 |  | XT39 / XT39 | Clean | PDCI / UBHO Sub | 03/16/2022 |  | 03/25/2022
500065 | UBHO Sub | 5.25 | 4 |  | XT39 / XT39 | Dirty | PDCI / UBHO Sub | 03/16/2022 |  | 03/25/2022
500068 | UBHO Sub | 5.188 | 4 |  | XT39 / XT39 | Clean | PDCI / UBHO Sub | 03/16/2022
GT50331297FF | Float Sub | 5 | 3.64 |  | XT39 / XT39 | Clean | Gator / Float Sub | 03/16/2022 |  | 03/25/2022
GT52331248FF | Float Sub |  |  |  | XT39 / XT39 | Clean | Gator / Float Sub | 03/16/2022 |  | 03/25/2022
GT52331433 | Crossover | 5.312 | 3.63 |  | CET43 / XT39 | Dirty | Gator / XO Sub | 03/16/2022 |  | 03/25/2022
GT52331431 | Crossover | 5.188 | 3.38 |  | CET43 / XT39 | Clean | Gator / XO Sub | 03/16/2022
GT52331100 | Crossover | 5.312 | 2.61 |  | CET43 / XT39 | Clean | Gator / XO Sub | 03/16/2022 |  | 03/25/2022
GT551251 | Lift Sub | 5.5 | 3.23 |  | XT39 | Clean | Gator / Lift Sub | 03/16/2022 |  | 03/25/2022
GT551232 | Lift Sub | 5.5 | 3.2 |  | XT39 | Clean | Gator / Lift Sub | 03/16/2022 |  | 03/25/2022
GT225 | Lift Cap |  |  |  | XT39 | Clean | Gator | 03/16/2022 |  | 03/25/2022
A52180 | ToMax | 5 | 17.57 |  | XT39 / XT39 | Dirty | Tomax | 03/16/2022
A52105 | ToMax | 5 | 17.86 |  | XT39 / XT39 | Clean | Tomax | 03/16/2022
PG525-0037 | Agitator | 5.312 | 21.17 |  | CET43 / CET43 | Dirty | DWS / Power glide | 03/16/2022
PG525-0056 | Agitator | 5.25 | 21.26 |  | CET43 / CET43 | Dirty |  | 03/16/2022
PG525-0079 | Agitator | 5.312 | 21.2 |  | CET43 / CET43 | Clean | DWS / Power glide | 03/16/2022
Rig28 | 28 Stands DP | 4.5 | 2639.81 |  | CET43 / CET43 | Dirty |  | 03/16/2022
13711499 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Clean | Halliburton / GTD64M | 03/16/2022
BTI01 | BTI | 4.875 | 1.65 |  | XT39 / XT39 | Clean |  | 03/16/2022
BTI03 | BTI | 4.875 | 2.11 |  | XT39 / XT39 | Dirty |  | 03/16/2022
13618579 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Dirty | Halliburton | 03/18/2022
A52130 | ToMax | 5 | 21.97 |  | XT39 / XT39 | Clean | Tomax | 03/18/2022
PPM250004 | 5.5 6/7 8.8 2.12 TS HS88 +.015 | 5 | 33.1 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 03/19/2022 |  | 03/25/2022
GT50-10-637 | Non Mag Pony Collar | 5 | 8.6 |  | XT39 / XT39 | Clean |  | 03/19/2022 |  | 03/25/2022
GT50-10-479 | Non Mag Pony Collar | 5 | 9.86 |  | XT39 / XT39 | Clean |  | 03/19/2022 |  | 03/25/2022
GT51-30-695 | Non Mag Drill Collar | 5 |  |  | XT39 / XT39 | Clean |  | 03/19/2022 |  | 03/25/2022
GT51-30-696 | Non Mag Drill Collar | 5 |  |  | XT39 / XT39 | Clean |  | 03/19/2022 |  | 03/25/2022
GT52331432 | Crossover |  |  |  | CET43 / XT39 | Clean |  | 03/19/2022 |  | 03/25/2022
500065 | UBHO Sub | 5 |  |  | XT39 / XT39 | Dirty |  | 03/19/2022 |  | 03/25/2022
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Mill H08
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 47245 | 02/01/2022 | 02/04/2022 | 4 |  | 1 |  | 3.47 | 4.15 | 10.17
7/8 5.9 1.50 Stab HPW -.013 NBS 13 | PPM800035 | 02/01/2022 | 03/25/2022 | 53 |  | 1 |  | 3.47 | 4.15 | 10.17
Nortrak Stabilizer (BFF) | GT801175 | 02/01/2022 | 03/25/2022 | 53 |  | 1 |  | 3.47 | 4.15 | 10.17
Pony Collar (NO HARDBANDING) | GT80-10-648 | 02/01/2022 | 02/04/2022 | 4 | 3 | 1 ,2 |  | 11.32 | 31.07 | 60.17
UBHO Sub | 775234 | 02/01/2022 | 02/04/2022 | 4 | 3 | 1 ,2 |  | 11.32 | 31.07 | 60.17
Drill Collar (NO HARDBANDING) | GT80-30-171 | 02/01/2022 | 02/04/2022 | 4 | 3 | 1 ,2 |  | 11.32 | 31.07 | 60.17
Drill Collar (NO HARDBANDING) | GT80-30-378 | 02/01/2022 | 02/04/2022 | 4 | 3 | 1 ,2 |  | 11.32 | 31.07 | 60.17
Crossover Sub | GT7746831 | 02/01/2022 | 02/04/2022 | 4 |  | 1 |  | 3.47 | 4.15 | 10.17
SPL613 | 59253 | 02/01/2022 | 02/04/2022 | 4 | 2 | 2 |  | 7.85 | 26.92 | 50
7/8 5.9 2.0 TS HPW -.012 | MTR775009 | 02/01/2022 | 02/04/2022 | 4 | 2 | 2 |  | 7.85 | 26.92 | 50
Crossover Sub | GT8046294 | 02/01/2022 | 02/04/2022 | 4 | 2 | 2 |  | 7.85 | 26.92 | 50
6 Jts 6 1/2in DC | 6DC | 02/01/2022 | 02/04/2022 | 4 | 2 | 2 |  | 7.85 | 26.92 | 50
Crossover Sub | GT6744684 | 02/01/2022 | 02/04/2022 | 4 | 2 | 2 |  | 7.85 | 26.92 | 50
Agitator | PG675-0050 | 02/01/2022 | 02/04/2022 | 4 | 2 | 2 |  | 7.85 | 26.92 | 50
GTD64M | 13685101 | 02/01/2022 | 03/25/2022 | 53 | 6 | 3 |  | 25.8 | 57.43 | 142
5.5 6/7 8.8 2.12 TS HS88 +.002 | PPM250003 | 03/16/2022 | 03/25/2022 | 10 | 6 | 3 |  | 25.8 | 57.43 | 142
BTI | BTI02 | 02/01/2022 | 03/25/2022 | 53 | 6 | 3 |  | 25.8 | 57.43 | 142
Non Mag Pony Collar | GT50-10-465 | 03/16/2022 | 03/25/2022 | 10 | 8 | 3 ,4 |  | 34.68 | 69.05 | 194
UBHO Sub | 500065 | 03/19/2022 | 03/25/2022 | 7 | 8 | 3 ,4 |  | 34.68 | 69.05 | 194
Non Mag Drill Collar | GT50-30-707 | 03/16/2022 | 03/25/2022 | 10 | 8 | 3 ,4 |  | 34.68 | 69.05 | 194
Non Mag Pony Collar | GT50-10-585 | 03/16/2022 | 03/25/2022 | 10 | 6 | 3 |  | 25.8 | 57.43 | 142
Non Mag Drill Collar | GT50-30-722 | 03/16/2022 | 03/25/2022 | 10 | 8 | 3 ,4 |  | 34.68 | 69.05 | 194
ToMax | A52180 | 03/16/2022 | 03/25/2022 | 10 | 8 | 3 ,4 |  | 34.68 | 69.05 | 194
Crossover | GT52331433 | 03/16/2022 | 03/25/2022 | 10 | 8 | 3 ,4 |  | 34.68 | 69.05 | 194
Agitator | PG525-0056 | 03/16/2022 | 03/25/2022 | 10 | 6 | 3 |  | 25.8 | 57.43 | 142
GTD64M | 13618579 | 03/18/2022 | 03/25/2022 | 8 | 2 | 4 |  | 8.88 | 11.62 | 52
5.5 6/7 8.8 2.12 TS HS88 -.004 | PPM250005 | 03/16/2022 | 03/25/2022 | 10 | 2 | 4 |  | 8.88 | 11.62 | 52
BTI | BTI03 | 03/16/2022 | 03/25/2022 | 10 | 2 | 4 |  | 8.88 | 11.62 | 52
Agitator | PG525-0037 | 03/16/2022 | 03/25/2022 | 10 | 2 | 4 |  | 8.88 | 11.62 | 52
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well-GL: 342 + KB: 28 (Pat248)
Facility |  |  | Klondike - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Mill H08 |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Mill H08
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 370.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Klondike - Washington County, TX
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.863
Well: |  |  | Mill H08
Local North |  |  | 42.01 Usft |  |  | Local East |  |  | 36.12 Usft
Map Northing |  |  | 208481.42 US survey foot |  |  | Map Easting |  |  | 3142406.29 US survey foot
Latitude |  |  | 30° 11' 19.82152" N |  |  | Longitude |  |  | 96° 43' 1.09492" W
Depth Datum |  |  | Well-GL: 342 + KB: 28 (Pat248) |  |  | Datum Elevation |  |  | 370.00 Usft
GL Elevation |  |  | 342.00 Usft
Grid Convergence |  |  | 1.863
Well bore: |  |  | Mill H08
Magnetic Model |  |  | User defined |  |  | Date |  |  | 21/02/2022
Total Field (nT) |  |  | 46537.7 |  |  | Dip Angle (°) |  |  | 58.783
Declination (°) |  |  | 2.85
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 134.53
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Mill H08
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2729 |  |  | Mill H08 s1 |  |  | MWD+HDGM
2729 |  |  | 10165 |  |  | Mill H08 s2 |  |  | MWD+HDGM
10165 |  |  | 17822 |  |  | Mill H08 s3 |  |  | MWD+HRGM
17822 |  |  | 19327 |  |  | Mill H08 s4 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -370 | 208481.42 | 3142406.29 | 30.1888 | -96.717 | 0
199 | 0.46 | 81.51 | 199 | 0.12 | 0.79 | 0.48 | 0.23 | 0.23 | 40.96 | 81.51 | 199 | -171 | 208481.54 | 3142407.08 | 30.1888 | -96.717 | 81.51
291 | 0.77 | 109.25 | 290.99 | -0.03 | 1.74 | 1.26 | 0.46 | 0.34 | 30.15 | 58.28 | 92 | -79.01 | 208481.39 | 3142408.03 | 30.1888 | -96.717 | 91.03
382 | 0.29 | 132.43 | 381.99 | -0.39 | 2.49 | 2.04 | 0.57 | -0.53 | 25.47 | 167.22 | 91 | 11.99 | 208481.03 | 3142408.78 | 30.1888 | -96.717 | 98.88
476 | 0.7 | 80.86 | 475.99 | -0.46 | 3.23 | 2.62 | 0.6 | 0.44 | -54.86 | -75.18 | 94 | 105.99 | 208480.96 | 3142409.52 | 30.1888 | -96.717 | 98.07
570 | 1.05 | 77.25 | 569.97 | -0.18 | 4.64 | 3.43 | 0.38 | 0.37 | -3.84 | -10.76 | 94 | 199.97 | 208481.24 | 3142410.93 | 30.1888 | -96.717 | 92.18
664 | 1.86 | 55.73 | 663.94 | 0.87 | 6.74 | 4.19 | 1.03 | 0.86 | -22.89 | -45.08 | 94 | 293.94 | 208482.29 | 3142413.03 | 30.1888 | -96.7169 | 82.62
758 | 1.96 | 70.25 | 757.89 | 2.27 | 9.51 | 5.18 | 0.52 | 0.11 | 15.45 | 85.64 | 94 | 387.89 | 208483.69 | 3142415.8 | 30.1888 | -96.7169 | 76.55
851 | 2.2 | 66.2 | 850.83 | 3.53 | 12.64 | 6.53 | 0.3 | 0.26 | -4.35 | -33.52 | 93 | 480.83 | 208484.95 | 3142418.93 | 30.1888 | -96.7169 | 74.38
945 | 3.15 | 59.21 | 944.73 | 5.58 | 16.51 | 7.85 | 1.07 | 1.01 | -7.44 | -22.47 | 94 | 574.73 | 208487 | 3142422.8 | 30.1889 | -96.7169 | 71.32
1039 | 4.02 | 58.68 | 1038.54 | 8.62 | 21.54 | 9.31 | 0.93 | 0.93 | -0.56 | -2.45 | 94 | 668.54 | 208490.04 | 3142427.83 | 30.1889 | -96.7169 | 68.2
1132 | 4.91 | 63.18 | 1131.26 | 12.11 | 27.88 | 11.38 | 1.03 | 0.96 | 4.84 | 23.74 | 93 | 761.26 | 208493.53 | 3142434.17 | 30.1889 | -96.7169 | 66.52
1227 | 4.48 | 66.74 | 1225.94 | 15.41 | 34.92 | 14.09 | 0.55 | -0.45 | 3.75 | 147.64 | 95 | 855.94 | 208496.83 | 3142441.21 | 30.1889 | -96.7169 | 66.19
1320 | 5.18 | 66.39 | 1318.61 | 18.52 | 42.1 | 17.02 | 0.75 | 0.75 | -0.38 | -2.59 | 93 | 948.61 | 208499.94 | 3142448.39 | 30.1889 | -96.7168 | 66.25
1414 | 6.48 | 68.4 | 1412.12 | 22.18 | 50.92 | 20.75 | 1.4 | 1.38 | 2.14 | 9.93 | 94 | 1042.12 | 208503.6 | 3142457.21 | 30.1889 | -96.7168 | 66.47
1508 | 7.04 | 69.82 | 1505.47 | 26.12 | 61.26 | 25.36 | 0.62 | 0.6 | 1.51 | 17.33 | 94 | 1135.47 | 208507.54 | 3142467.55 | 30.1889 | -96.7168 | 66.91
1602 | 7.44 | 68.98 | 1598.72 | 30.29 | 72.35 | 30.34 | 0.44 | 0.43 | -0.89 | -15.24 | 94 | 1228.72 | 208511.71 | 3142478.64 | 30.1889 | -96.7167 | 67.29
1696 | 8.21 | 73.34 | 1691.84 | 34.39 | 84.46 | 36.09 | 1.03 | 0.82 | 4.64 | 39.8 | 94 | 1321.84 | 208515.81 | 3142490.75 | 30.1889 | -96.7167 | 67.84
1789 | 8.92 | 78.57 | 1783.81 | 37.73 | 97.89 | 43.33 | 1.13 | 0.76 | 5.62 | 50.26 | 93 | 1413.81 | 208519.15 | 3142504.18 | 30.1889 | -96.7167 | 68.92
1883 | 9.81 | 80.41 | 1876.55 | 40.5 | 112.93 | 52.1 | 1 | 0.95 | 1.96 | 19.5 | 94 | 1506.55 | 208521.92 | 3142519.22 | 30.1889 | -96.7166 | 70.27
1977 | 9.49 | 77.26 | 1969.22 | 43.55 | 128.38 | 60.98 | 0.66 | -0.34 | -3.35 | -122.76 | 94 | 1599.22 | 208524.97 | 3142534.67 | 30.1889 | -96.7166 | 71.26
2071 | 10.1 | 76.52 | 2061.85 | 47.18 | 143.96 | 69.54 | 0.66 | 0.65 | -0.79 | -12.03 | 94 | 1691.85 | 208528.6 | 3142550.25 | 30.189 | -96.7165 | 71.85
2164 | 10.61 | 73.48 | 2153.34 | 51.51 | 160.09 | 78 | 0.8 | 0.55 | -3.27 | -48.48 | 93 | 1783.34 | 208532.93 | 3142566.38 | 30.189 | -96.7165 | 72.16
2259 | 10.52 | 70.1 | 2246.73 | 56.95 | 176.63 | 85.98 | 0.66 | -0.09 | -3.56 | -99.92 | 95 | 1876.73 | 208538.37 | 3142582.92 | 30.189 | -96.7164 | 72.13
2354 | 10.87 | 70.46 | 2340.08 | 62.9 | 193.23 | 93.64 | 0.38 | 0.37 | 0.38 | 10.98 | 95 | 1970.08 | 208544.32 | 3142599.52 | 30.189 | -96.7164 | 71.97
2448 | 11.29 | 71.19 | 2432.33 | 68.83 | 210.29 | 101.64 | 0.47 | 0.45 | 0.78 | 18.83 | 94 | 2062.33 | 208550.25 | 3142616.58 | 30.189 | -96.7163 | 71.88
2542 | 11.48 | 69.56 | 2524.48 | 75.06 | 227.77 | 109.73 | 0.4 | 0.2 | -1.73 | -60.24 | 94 | 2154.48 | 208556.48 | 3142634.06 | 30.189 | -96.7162 | 71.76
2635 | 10.72 | 69.8 | 2615.74 | 81.28 | 244.56 | 117.34 | 0.82 | -0.82 | 0.26 | 176.64 | 93 | 2245.74 | 208562.7 | 3142650.85 | 30.189 | -96.7162 | 71.61
2729 | 10.55 | 72.71 | 2708.12 | 86.86 | 260.98 | 125.13 | 0.6 | -0.18 | 3.1 | 108.99 | 94 | 2338.12 | 208568.28 | 3142667.27 | 30.1891 | -96.7161 | 71.59
2849 | 10.3 | 70.26 | 2826.14 | 93.75 | 281.57 | 134.98 | 0.42 | -0.21 | -2.04 | -120.62 | 120 | 2456.14 | 208575.17 | 3142687.86 | 30.1891 | -96.7161 | 71.58
2943 | 10.76 | 68.88 | 2918.56 | 99.75 | 297.66 | 142.25 | 0.56 | 0.49 | -1.47 | -29.41 | 94 | 2548.56 | 208581.17 | 3142703.95 | 30.1891 | -96.716 | 71.47
3037 | 9.13 | 70.78 | 3011.14 | 105.37 | 312.89 | 149.16 | 1.77 | -1.73 | 2.02 | 169.55 | 94 | 2641.14 | 208586.79 | 3142719.18 | 30.1891 | -96.716 | 71.39
3131 | 9.1 | 69.17 | 3103.96 | 110.46 | 326.88 | 155.56 | 0.27 | -0.03 | -1.71 | -97.5 | 94 | 2733.96 | 208591.88 | 3142733.17 | 30.1891 | -96.7159 | 71.33
3225 | 9.05 | 67.6 | 3196.78 | 115.92 | 340.66 | 161.56 | 0.27 | -0.05 | -1.67 | -102.19 | 94 | 2826.78 | 208597.34 | 3142746.95 | 30.1891 | -96.7159 | 71.21
3319 | 10.24 | 72.17 | 3289.45 | 121.3 | 355.45 | 168.33 | 1.5 | 1.27 | 4.86 | 35.03 | 94 | 2919.45 | 208602.72 | 3142761.74 | 30.1891 | -96.7158 | 71.16
3414 | 9.7 | 79.66 | 3383.02 | 125.32 | 371.36 | 176.85 | 1.48 | -0.57 | 7.88 | 116.27 | 95 | 3013.02 | 208606.74 | 3142777.65 | 30.1892 | -96.7158 | 71.35
3507 | 8.07 | 82.92 | 3474.9 | 127.53 | 385.55 | 185.42 | 1.83 | -1.75 | 3.51 | 164.44 | 93 | 3104.9 | 208608.95 | 3142791.84 | 30.1892 | -96.7157 | 71.7
3602 | 8.12 | 84.59 | 3568.96 | 128.99 | 398.85 | 193.88 | 0.25 | 0.05 | 1.76 | 78.82 | 95 | 3198.96 | 208610.41 | 3142805.14 | 30.1892 | -96.7157 | 72.08
3696 | 6.89 | 85.64 | 3662.15 | 130.04 | 411.08 | 201.86 | 1.32 | -1.31 | 1.12 | 174.16 | 94 | 3292.15 | 208611.46 | 3142817.37 | 30.1892 | -96.7157 | 72.45
3790 | 6.87 | 85.9 | 3755.47 | 130.87 | 422.31 | 209.28 | 0.04 | -0.02 | 0.28 | 122.84 | 94 | 3385.47 | 208612.29 | 3142828.6 | 30.1892 | -96.7156 | 72.78
3884 | 6.02 | 89.23 | 3848.88 | 131.34 | 432.85 | 216.46 | 0.99 | -0.9 | 3.54 | 157.91 | 94 | 3478.88 | 208612.76 | 3142839.14 | 30.1892 | -96.7156 | 73.12
3978 | 5.28 | 74.48 | 3942.42 | 132.56 | 441.94 | 222.09 | 1.73 | -0.79 | -15.69 | -124.21 | 94 | 3572.42 | 208613.98 | 3142848.23 | 30.1892 | -96.7156 | 73.3
4072 | 3.64 | 71.62 | 4036.14 | 134.66 | 448.94 | 225.61 | 1.76 | -1.74 | -3.04 | -173.7 | 94 | 3666.14 | 208616.08 | 3142855.23 | 30.1892 | -96.7155 | 73.3
4165 | 3.31 | 67.02 | 4128.97 | 136.64 | 454.22 | 227.98 | 0.46 | -0.35 | -4.95 | -142.09 | 93 | 3758.97 | 208618.06 | 3142860.51 | 30.1892 | -96.7155 | 73.26
4258 | 2.66 | 85.08 | 4221.84 | 137.88 | 458.84 | 230.41 | 1.22 | -0.7 | 19.42 | 133.45 | 93 | 3851.84 | 208619.3 | 3142865.13 | 30.1892 | -96.7155 | 73.28
4353 | 2.88 | 110.48 | 4316.73 | 137.23 | 463.27 | 234.02 | 1.3 | 0.23 | 26.74 | 92.69 | 95 | 3946.73 | 208618.65 | 3142869.56 | 30.1892 | -96.7155 | 73.5
4446 | 2.67 | 109.69 | 4409.62 | 135.68 | 467.5 | 238.12 | 0.23 | -0.23 | -0.85 | -170.07 | 93 | 4039.62 | 208617.1 | 3142873.79 | 30.1892 | -96.7155 | 73.82
4540 | 1.64 | 142.98 | 4503.56 | 133.87 | 470.37 | 241.44 | 1.68 | -1.1 | 35.41 | 145.28 | 94 | 4133.56 | 208615.29 | 3142876.66 | 30.1892 | -96.7155 | 74.11
4634 | 1.01 | 173.24 | 4597.54 | 131.97 | 471.28 | 243.41 | 0.98 | -0.67 | 32.19 | 146.45 | 94 | 4227.54 | 208613.39 | 3142877.57 | 30.1892 | -96.7155 | 74.36
4728 | 0.79 | 149.92 | 4691.52 | 130.59 | 471.7 | 244.69 | 0.45 | -0.23 | -24.81 | -132.3 | 94 | 4321.52 | 208612.01 | 3142877.99 | 30.1892 | -96.7155 | 74.53
4821 | 0.73 | 172.11 | 4784.52 | 129.45 | 472.1 | 245.77 | 0.32 | -0.06 | 23.86 | 112.48 | 93 | 4414.52 | 208610.87 | 3142878.39 | 30.1892 | -96.7155 | 74.67
4915 | 0.54 | 158.64 | 4878.51 | 128.44 | 472.35 | 246.65 | 0.26 | -0.2 | -14.33 | -148.45 | 94 | 4508.51 | 208609.86 | 3142878.64 | 30.1892 | -96.7155 | 74.79
5009 | 0.16 | 179.76 | 4972.51 | 127.9 | 472.51 | 247.15 | 0.42 | -0.4 | 22.47 | 171.61 | 94 | 4602.51 | 208609.32 | 3142878.8 | 30.1891 | -96.7155 | 74.85
5104 | 0.42 | 283.87 | 5067.51 | 127.85 | 472.17 | 246.94 | 0.51 | 0.27 | 109.59 | 122.79 | 95 | 4697.51 | 208609.27 | 3142878.46 | 30.1891 | -96.7155 | 74.85
5197 | 0.7 | 307.59 | 5160.5 | 128.28 | 471.39 | 246.09 | 0.38 | 0.3 | 25.51 | 51.89 | 93 | 4790.5 | 208609.7 | 3142877.68 | 30.1892 | -96.7155 | 74.78
5291 | 0.74 | 303.53 | 5254.5 | 128.96 | 470.43 | 244.92 | 0.07 | 0.04 | -4.32 | -53.94 | 94 | 4884.5 | 208610.38 | 3142876.72 | 30.1892 | -96.7155 | 74.67
5384 | 0.65 | 316.87 | 5347.49 | 129.68 | 469.57 | 243.8 | 0.2 | -0.1 | 14.34 | 125.64 | 93 | 4977.49 | 208611.1 | 3142875.86 | 30.1892 | -96.7155 | 74.56
5477 | 0.67 | 328.26 | 5440.48 | 130.53 | 468.92 | 242.75 | 0.14 | 0.02 | 12.25 | 87.06 | 93 | 5070.48 | 208611.95 | 3142875.21 | 30.1892 | -96.7155 | 74.44
5571 | 0.83 | 329.76 | 5534.48 | 131.58 | 468.29 | 241.56 | 0.17 | 0.17 | 1.6 | 7.75 | 94 | 5164.48 | 208613 | 3142874.58 | 30.1892 | -96.7155 | 74.31
5665 | 0.85 | 345.47 | 5628.47 | 132.85 | 467.77 | 240.3 | 0.25 | 0.02 | 16.71 | 92.92 | 94 | 5258.47 | 208614.27 | 3142874.06 | 30.1892 | -96.7155 | 74.15
5758 | 0.94 | 334.84 | 5721.45 | 134.2 | 467.27 | 238.99 | 0.2 | 0.1 | -11.43 | -66.92 | 93 | 5351.45 | 208615.62 | 3142873.56 | 30.1892 | -96.7155 | 73.98
5851 | 1.17 | 317.36 | 5814.44 | 135.59 | 466.3 | 237.33 | 0.42 | 0.25 | -18.8 | -63.4 | 93 | 5444.44 | 208617.01 | 3142872.59 | 30.1892 | -96.7155 | 73.79
5945 | 1.5 | 316.78 | 5908.41 | 137.2 | 464.81 | 235.14 | 0.35 | 0.35 | -0.62 | -2.63 | 94 | 5538.41 | 208618.62 | 3142871.1 | 30.1892 | -96.7155 | 73.56
6038 | 1.62 | 320.04 | 6001.38 | 139.09 | 463.13 | 232.62 | 0.16 | 0.13 | 3.51 | 38.12 | 93 | 5631.38 | 208620.51 | 3142869.42 | 30.1892 | -96.7155 | 73.28
6132 | 2.17 | 327.76 | 6095.33 | 141.61 | 461.33 | 229.56 | 0.64 | 0.59 | 8.21 | 28.79 | 94 | 5725.33 | 208623.03 | 3142867.62 | 30.1892 | -96.7155 | 72.94
6226 | 2.06 | 318.87 | 6189.26 | 144.39 | 459.27 | 226.15 | 0.37 | -0.12 | -9.46 | -112.94 | 94 | 5819.26 | 208625.81 | 3142865.56 | 30.1892 | -96.7155 | 72.55
6320 | 0.91 | 308.58 | 6283.23 | 146.13 | 457.58 | 223.72 | 1.25 | -1.22 | -10.95 | -172.05 | 94 | 5913.23 | 208627.55 | 3142863.87 | 30.1892 | -96.7155 | 72.29
6414 | 1.03 | 305.46 | 6377.22 | 147.09 | 456.3 | 222.14 | 0.14 | 0.13 | -3.32 | -25.32 | 94 | 6007.22 | 208628.51 | 3142862.59 | 30.1892 | -96.7155 | 72.13
6508 | 1.28 | 311.57 | 6471.2 | 148.27 | 454.83 | 220.26 | 0.3 | 0.27 | 6.5 | 29.3 | 94 | 6101.2 | 208629.69 | 3142861.12 | 30.1892 | -96.7155 | 71.94
6601 | 1.56 | 327.43 | 6564.17 | 150.03 | 453.37 | 217.99 | 0.52 | 0.3 | 17.05 | 62.63 | 93 | 6194.17 | 208631.45 | 3142859.66 | 30.1892 | -96.7155 | 71.69
6695 | 1.82 | 327.41 | 6658.13 | 152.37 | 451.88 | 215.29 | 0.28 | 0.28 | -0.02 | -0.14 | 94 | 6288.13 | 208633.79 | 3142858.17 | 30.1892 | -96.7155 | 71.37
6789 | 2.13 | 321.33 | 6752.07 | 154.99 | 449.98 | 212.1 | 0.4 | 0.33 | -6.47 | -37.12 | 94 | 6382.07 | 208636.41 | 3142856.27 | 30.1892 | -96.7155 | 70.99
6883 | 1.5 | 334.19 | 6846.02 | 157.46 | 448.36 | 209.2 | 0.79 | -0.67 | 13.68 | 153.43 | 94 | 6476.02 | 208638.88 | 3142854.65 | 30.1892 | -96.7155 | 70.65
6977 | 0.91 | 31.81 | 6940.01 | 159.2 | 448.21 | 207.88 | 1.35 | -0.63 | 61.3 | 142.8 | 94 | 6570.01 | 208640.62 | 3142854.5 | 30.1892 | -96.7155 | 70.45
7071 | 0.9 | 34.78 | 7034 | 160.44 | 449.03 | 207.59 | 0.05 | -0.01 | 3.16 | 103.52 | 94 | 6664 | 208641.86 | 3142855.32 | 30.1892 | -96.7155 | 70.34
7165 | 0.94 | 18.84 | 7127.98 | 161.78 | 449.7 | 207.13 | 0.27 | 0.04 | -16.96 | -89.14 | 94 | 6757.98 | 208643.2 | 3142855.99 | 30.1892 | -96.7155 | 70.21
7259 | 1.05 | 8.11 | 7221.97 | 163.36 | 450.07 | 206.29 | 0.23 | 0.12 | -11.41 | -64.88 | 94 | 6851.97 | 208644.78 | 3142856.36 | 30.1892 | -96.7155 | 70.05
7352 | 1.1 | 18.66 | 7314.95 | 165.05 | 450.48 | 205.39 | 0.22 | 0.05 | 11.34 | 81.14 | 93 | 6944.95 | 208646.47 | 3142856.77 | 30.1893 | -96.7155 | 69.88
7446 | 1.14 | 4.5 | 7408.93 | 166.84 | 450.84 | 204.4 | 0.3 | 0.04 | -15.06 | -88.9 | 94 | 7038.93 | 208648.26 | 3142857.13 | 30.1893 | -96.7155 | 69.69
7540 | 1.3 | 347.03 | 7502.91 | 168.81 | 450.67 | 202.89 | 0.43 | 0.17 | 18.59 | -75.62 | 94 | 7132.91 | 208650.23 | 3142856.96 | 30.1893 | -96.7155 | 69.47
7634 | 1.4 | 307.87 | 7596.89 | 170.55 | 449.53 | 200.85 | 0.97 | 0.11 | -41.66 | -103.63 | 94 | 7226.89 | 208651.97 | 3142855.82 | 30.1893 | -96.7155 | 69.22
7728 | 1.8 | 310.24 | 7690.85 | 172.21 | 447.49 | 198.24 | 0.43 | 0.43 | 2.52 | 10.58 | 94 | 7320.85 | 208653.63 | 3142853.78 | 30.1893 | -96.7155 | 68.95
7822 | 1.19 | 276.79 | 7784.82 | 173.28 | 445.4 | 196 | 1.11 | -0.65 | -35.59 | -140.9 | 94 | 7414.82 | 208654.7 | 3142851.69 | 30.1893 | -96.7155 | 68.74
7916 | 1.46 | 262.58 | 7878.8 | 173.24 | 443.24 | 194.49 | 0.45 | 0.29 | -15.12 | -57.84 | 94 | 7508.8 | 208654.66 | 3142849.53 | 30.1893 | -96.7156 | 68.65
8010 | 0.19 | 216.43 | 7972.79 | 172.96 | 441.96 | 193.77 | 1.42 | -1.35 | -49.1 | -174.11 | 94 | 7602.79 | 208654.38 | 3142848.25 | 30.1893 | -96.7156 | 68.63
8104 | 0.51 | 109.66 | 8066.78 | 172.69 | 442.26 | 194.17 | 0.63 | 0.34 | -113.59 | -124.62 | 94 | 7696.78 | 208654.11 | 3142848.55 | 30.1893 | -96.7156 | 68.67
8197 | 0.24 | 303.68 | 8159.78 | 172.66 | 442.49 | 194.36 | 0.8 | -0.29 | 178.47 | -175.52 | 93 | 7789.78 | 208654.08 | 3142848.78 | 30.1893 | -96.7156 | 68.68
8292 | 0.6 | 307.97 | 8254.78 | 173.08 | 441.93 | 193.67 | 0.38 | 0.38 | 4.52 | 7.14 | 95 | 7884.78 | 208654.5 | 3142848.22 | 30.1893 | -96.7156 | 68.61
8385 | 1.04 | 297.42 | 8347.77 | 173.77 | 440.8 | 192.38 | 0.5 | 0.47 | -11.34 | -24.26 | 93 | 7977.77 | 208655.19 | 3142847.09 | 30.1893 | -96.7156 | 68.49
8479 | 0.97 | 284.72 | 8441.76 | 174.36 | 439.27 | 190.87 | 0.25 | -0.07 | -13.51 | -113.73 | 94 | 8071.76 | 208655.78 | 3142845.56 | 30.1893 | -96.7156 | 68.35
8573 | 0.99 | 69.26 | 8535.75 | 174.85 | 439.26 | 190.52 | 1.99 | 0.02 | 153.77 | 162.08 | 94 | 8165.75 | 208656.27 | 3142845.55 | 30.1893 | -96.7156 | 68.29
8666 | 0.87 | 89.4 | 8628.74 | 175.14 | 440.72 | 191.36 | 0.37 | -0.13 | 21.66 | 120.04 | 93 | 8258.74 | 208656.56 | 3142847.01 | 30.1893 | -96.7156 | 68.33
8760 | 0.24 | 90.42 | 8722.73 | 175.15 | 441.63 | 192 | 0.67 | -0.67 | 1.09 | 179.61 | 94 | 8352.73 | 208656.57 | 3142847.92 | 30.1893 | -96.7156 | 68.37
8854 | 0.05 | 221.29 | 8816.73 | 175.12 | 441.8 | 192.14 | 0.29 | -0.2 | 139.22 | 172.11 | 94 | 8446.73 | 208656.54 | 3142848.09 | 30.1893 | -96.7156 | 68.38
8947 | 0.89 | 246.93 | 8909.73 | 174.8 | 441.11 | 191.87 | 0.91 | 0.9 | 27.57 | 27.11 | 93 | 8539.73 | 208656.22 | 3142847.4 | 30.1893 | -96.7156 | 68.38
9042 | 1.45 | 227.26 | 9004.71 | 173.7 | 439.55 | 191.53 | 0.72 | 0.59 | -20.71 | -45.75 | 95 | 8634.71 | 208655.12 | 3142845.84 | 30.1893 | -96.7156 | 68.44
9136 | 2.14 | 245.82 | 9098.66 | 172.17 | 437.07 | 190.84 | 0.95 | 0.73 | 19.74 | 49.64 | 94 | 8728.66 | 208653.59 | 3142843.36 | 30.1893 | -96.7156 | 68.5
9231 | 1.82 | 258.34 | 9193.61 | 171.14 | 433.98 | 189.36 | 0.56 | -0.34 | 13.18 | 132.64 | 95 | 8823.61 | 208652.56 | 3142840.27 | 30.1893 | -96.7156 | 68.48
9325 | 0.19 | 334.89 | 9287.59 | 170.98 | 432.45 | 188.38 | 1.9 | -1.73 | 81.44 | 174.06 | 94 | 8917.59 | 208652.4 | 3142838.74 | 30.1893 | -96.7156 | 68.43
9419 | 0.6 | 73.92 | 9381.59 | 171.26 | 432.85 | 188.47 | 0.7 | 0.44 | 105.35 | 115.62 | 94 | 9011.59 | 208652.68 | 3142839.14 | 30.1893 | -96.7156 | 68.41
9512 | 1.11 | 81.6 | 9474.58 | 171.52 | 434.21 | 189.26 | 0.56 | 0.55 | 8.26 | 16.52 | 93 | 9104.58 | 208652.94 | 3142840.5 | 30.1893 | -96.7156 | 68.44
9606 | 1.1 | 72.94 | 9568.56 | 171.92 | 435.98 | 190.23 | 0.18 | -0.01 | -9.21 | -97.75 | 94 | 9198.56 | 208653.34 | 3142842.27 | 30.1893 | -96.7156 | 68.48
9700 | 0.73 | 43.34 | 9662.55 | 172.62 | 437.25 | 190.65 | 0.63 | -0.39 | -31.49 | -142.22 | 94 | 9292.55 | 208654.04 | 3142843.54 | 30.1893 | -96.7156 | 68.46
9794 | 4.42 | 173.02 | 9756.46 | 169.46 | 438.1 | 193.48 | 5.23 | 3.93 | 137.96 | 136.23 | 94 | 9386.46 | 208650.88 | 3142844.39 | 30.1893 | -96.7156 | 68.85
9889 | 11.76 | 158.21 | 9850.46 | 156.82 | 442.15 | 205.22 | 7.97 | 7.73 | -15.59 | -23.29 | 95 | 9480.46 | 208638.24 | 3142848.44 | 30.1892 | -96.7156 | 70.47
9982 | 18.28 | 149.74 | 9940.25 | 135.4 | 453.03 | 228 | 7.38 | 7.01 | -9.11 | -22.74 | 93 | 9570.25 | 208616.82 | 3142859.32 | 30.1892 | -96.7155 | 73.36
10076 | 22.46 | 141.78 | 10028.37 | 108.54 | 471.58 | 260.06 | 5.33 | 4.45 | -8.47 | -37.32 | 94 | 9658.37 | 208589.96 | 3142877.87 | 30.1891 | -96.7155 | 77.04
10165 | 21.85 | 137.34 | 10110.8 | 83 | 493.32 | 293.47 | 2 | -0.69 | -4.99 | -112.06 | 89 | 9740.8 | 208564.42 | 3142899.61 | 30.189 | -96.7154 | 80.45
10283 | 23.35 | 138.54 | 10219.74 | 49.33 | 523.68 | 338.73 | 1.33 | 1.27 | 1.02 | 17.64 | 118 | 9849.74 | 208530.75 | 3142929.97 | 30.1889 | -96.7153 | 84.62
10378 | 31.47 | 143.69 | 10304.01 | 15.17 | 550.88 | 382.07 | 8.9 | 8.55 | 5.42 | 18.59 | 95 | 9934.01 | 208496.59 | 3142957.17 | 30.1888 | -96.7152 | 88.42
10472 | 40.82 | 141.51 | 10379.84 | -28.75 | 584.61 | 436.92 | 10.04 | 9.95 | -2.32 | -8.72 | 94 | 10009.84 | 208452.67 | 3142990.9 | 30.1887 | -96.7151 | 92.82
10567 | 49.62 | 129.05 | 10446.82 | -76.03 | 632.22 | 504.02 | 13.1 | 9.26 | -13.12 | -49.7 | 95 | 10076.82 | 208405.39 | 3143038.51 | 30.1886 | -96.715 | 96.86
10662 | 58.49 | 123.09 | 10502.57 | -121.05 | 694.41 | 579.93 | 10.62 | 9.34 | -6.27 | -30.35 | 95 | 10132.57 | 208360.37 | 3143100.7 | 30.1884 | -96.7148 | 99.89
10752 | 61.38 | 132.95 | 10547.73 | -169.01 | 755.59 | 657.17 | 10.01 | 3.21 | 10.96 | 73.81 | 90 | 10177.73 | 208312.41 | 3143161.88 | 30.1883 | -96.7146 | 102.61
10848 | 65.65 | 135.19 | 10590.54 | -228.78 | 817.29 | 743.07 | 4.91 | 4.45 | 2.33 | 25.66 | 96 | 10220.54 | 208252.64 | 3143223.58 | 30.1881 | -96.7144 | 105.64
10942 | 69.85 | 136.49 | 10626.13 | -291.19 | 877.87 | 830.03 | 4.65 | 4.47 | 1.38 | 16.24 | 94 | 10256.13 | 208190.23 | 3143284.16 | 30.188 | -96.7142 | 108.35
11035 | 76.61 | 136.94 | 10652.94 | -355.97 | 938.88 | 918.95 | 7.28 | 7.27 | 0.48 | 3.71 | 93 | 10282.94 | 208125.45 | 3143345.17 | 30.1878 | -96.714 | 110.76
11130 | 85.89 | 136.75 | 10667.38 | -424.4 | 1003.04 | 1012.67 | 9.77 | 9.77 | -0.2 | -1.18 | 95 | 10297.38 | 208057.02 | 3143409.33 | 30.1876 | -96.7138 | 112.93
11224 | 87.21 | 136.09 | 10673.04 | -492.36 | 1067.72 | 1106.44 | 1.57 | 1.4 | -0.7 | -26.54 | 94 | 10303.04 | 207989.06 | 3143474.01 | 30.1874 | -96.7136 | 114.76
11319 | 85.78 | 134.58 | 10678.84 | -559.8 | 1134.37 | 1201.25 | 2.19 | -1.51 | -1.59 | -133.54 | 95 | 10308.84 | 207921.62 | 3143540.66 | 30.1872 | -96.7134 | 116.27
11413 | 86.93 | 135.2 | 10684.82 | -626.01 | 1200.83 | 1295.06 | 1.39 | 1.22 | 0.66 | 28.3 | 94 | 10314.82 | 207855.41 | 3143607.12 | 30.187 | -96.7132 | 117.53
11507 | 84.27 | 134.19 | 10692.03 | -691.92 | 1267.44 | 1388.77 | 3.03 | -2.83 | -1.07 | -159.3 | 94 | 10322.03 | 207789.5 | 3143673.73 | 30.1868 | -96.713 | 118.63
11602 | 83.96 | 134 | 10701.77 | -757.68 | 1335.31 | 1483.27 | 0.38 | -0.33 | -0.2 | -148.64 | 95 | 10331.77 | 207723.74 | 3143741.6 | 30.1866 | -96.7128 | 119.57
11696 | 84.05 | 133.98 | 10711.59 | -822.61 | 1402.57 | 1576.75 | 0.1 | 0.1 | -0.02 | -12.46 | 94 | 10341.59 | 207658.81 | 3143808.86 | 30.1865 | -96.7126 | 120.39
11790 | 86.34 | 133.69 | 10719.46 | -887.47 | 1470.14 | 1670.41 | 2.46 | 2.44 | -0.31 | -7.2 | 94 | 10349.46 | 207593.95 | 3143876.43 | 30.1863 | -96.7124 | 121.12
11885 | 87.97 | 133.01 | 10724.18 | -952.6 | 1539.13 | 1765.26 | 1.86 | 1.72 | -0.72 | -22.64 | 95 | 10354.18 | 207528.82 | 3143945.42 | 30.1861 | -96.7122 | 121.75
11981 | 88.55 | 132.3 | 10727.09 | -1017.62 | 1609.7 | 1861.17 | 0.95 | 0.6 | -0.74 | -50.75 | 96 | 10357.09 | 207463.8 | 3144015.99 | 30.1859 | -96.712 | 122.3
12075 | 89.75 | 131.88 | 10728.49 | -1080.62 | 1679.45 | 1955.07 | 1.35 | 1.28 | -0.45 | -19.29 | 94 | 10358.49 | 207400.8 | 3144085.74 | 30.1857 | -96.7118 | 122.76
12171 | 86.4 | 131.26 | 10731.71 | -1144.28 | 1751.22 | 2050.87 | 3.55 | -3.49 | -0.65 | -169.53 | 96 | 10361.71 | 207337.14 | 3144157.51 | 30.1855 | -96.7115 | 123.16
12262 | 86.82 | 131.02 | 10737.09 | -1204.04 | 1819.63 | 2141.56 | 0.53 | 0.46 | -0.26 | -29.71 | 91 | 10367.09 | 207277.38 | 3144225.92 | 30.1854 | -96.7113 | 123.49
12354 | 86.97 | 134.33 | 10742.08 | -1266.3 | 1887.16 | 2233.36 | 3.6 | 0.16 | 3.6 | 87.49 | 92 | 10372.08 | 207215.12 | 3144293.45 | 30.1852 | -96.7111 | 123.86
12450 | 87.11 | 139.17 | 10747.04 | -1336.11 | 1952.83 | 2329.13 | 5.04 | 0.15 | 5.04 | 88.47 | 96 | 10377.04 | 207145.31 | 3144359.12 | 30.185 | -96.7109 | 124.38
12544 | 87.03 | 143.96 | 10751.85 | -1409.62 | 2011.17 | 2422.27 | 5.09 | -0.09 | 5.1 | 91.08 | 94 | 10381.85 | 207071.8 | 3144417.46 | 30.1848 | -96.7108 | 125.03
12639 | 85.28 | 144.76 | 10758.22 | -1486.65 | 2066.4 | 2515.66 | 2.02 | -1.84 | 0.84 | 155.51 | 95 | 10388.22 | 206994.77 | 3144472.69 | 30.1846 | -96.7106 | 125.73
12733 | 85.44 | 139.28 | 10765.83 | -1560.47 | 2124.03 | 2608.52 | 5.81 | 0.17 | -5.83 | -88.55 | 94 | 10395.83 | 206920.95 | 3144530.32 | 30.1844 | -96.7104 | 126.3
12827 | 87.91 | 134 | 10771.28 | -1628.67 | 2188.44 | 2702.26 | 6.19 | 2.63 | -5.62 | -65.06 | 94 | 10401.28 | 206852.75 | 3144594.73 | 30.1842 | -96.7102 | 126.66
12922 | 85.77 | 131.57 | 10776.52 | -1693.09 | 2258.04 | 2797.06 | 3.41 | -2.25 | -2.56 | -131.47 | 95 | 10406.52 | 206788.33 | 3144664.33 | 30.184 | -96.71 | 126.86
13017 | 86.2 | 131.05 | 10783.17 | -1755.65 | 2329.23 | 2891.67 | 0.71 | 0.45 | -0.55 | -50.36 | 95 | 10413.17 | 206725.77 | 3144735.52 | 30.1838 | -96.7098 | 127.01
13112 | 86.97 | 130.77 | 10788.83 | -1817.75 | 2400.89 | 2986.32 | 0.86 | 0.81 | -0.29 | -19.96 | 95 | 10418.83 | 206663.67 | 3144807.18 | 30.1836 | -96.7096 | 127.13
13206 | 86.08 | 130.8 | 10794.53 | -1879.04 | 2471.94 | 3079.94 | 0.95 | -0.95 | 0.03 | 178.07 | 94 | 10424.53 | 206602.38 | 3144878.23 | 30.1835 | -96.7093 | 127.24
13301 | 85.93 | 130.74 | 10801.15 | -1940.93 | 2543.71 | 3174.51 | 0.17 | -0.16 | -0.06 | -158.25 | 95 | 10431.15 | 206540.49 | 3144950 | 30.1833 | -96.7091 | 127.34
13393 | 86.37 | 131.42 | 10807.32 | -2001.25 | 2612.9 | 3266.13 | 0.88 | 0.48 | 0.74 | 57.06 | 92 | 10437.32 | 206480.17 | 3145019.19 | 30.1831 | -96.7089 | 127.45
13487 | 86.62 | 130.94 | 10813.07 | -2063.02 | 2683.52 | 3359.8 | 0.57 | 0.27 | -0.51 | -62.46 | 94 | 10443.07 | 206418.4 | 3145089.81 | 30.1829 | -96.7087 | 127.55
13581 | 86.22 | 132.84 | 10818.94 | -2125.66 | 2753.35 | 3453.51 | 2.06 | -0.43 | 2.02 | 101.97 | 94 | 10448.94 | 206355.76 | 3145159.64 | 30.1828 | -96.7085 | 127.67
13675 | 85.33 | 132.71 | 10825.87 | -2189.32 | 2822.16 | 3547.21 | 0.96 | -0.95 | -0.14 | -171.72 | 94 | 10455.87 | 206292.1 | 3145228.45 | 30.1826 | -96.7083 | 127.8
13769 | 87.51 | 134.01 | 10831.73 | -2253.73 | 2890.37 | 3641 | 2.7 | 2.32 | 1.38 | 30.8 | 94 | 10461.73 | 206227.69 | 3145296.66 | 30.1824 | -96.7081 | 127.94
13863 | 86.92 | 133.18 | 10836.3 | -2318.47 | 2958.36 | 3734.87 | 1.08 | -0.63 | -0.88 | -125.46 | 94 | 10466.3 | 206162.95 | 3145364.65 | 30.1822 | -96.7079 | 128.09
13957 | 87.84 | 132.92 | 10840.6 | -2382.57 | 3026.98 | 3828.74 | 1.02 | 0.98 | -0.28 | -15.77 | 94 | 10470.6 | 206098.85 | 3145433.27 | 30.182 | -96.7076 | 128.21
14051 | 88 | 132.81 | 10844.01 | -2446.48 | 3095.83 | 3922.64 | 0.21 | 0.17 | -0.12 | -34.49 | 94 | 10474.01 | 206034.94 | 3145502.12 | 30.1818 | -96.7074 | 128.32
14146 | 89.16 | 132.63 | 10846.36 | -2510.9 | 3165.61 | 4017.56 | 1.24 | 1.22 | -0.19 | -8.82 | 95 | 10476.36 | 205970.52 | 3145571.9 | 30.1817 | -96.7072 | 128.42
14241 | 87.75 | 132.31 | 10848.93 | -2575.02 | 3235.65 | 4112.46 | 1.52 | -1.48 | -0.34 | -167.22 | 95 | 10478.93 | 205906.4 | 3145641.94 | 30.1815 | -96.707 | 128.51
14333 | 86.79 | 138.3 | 10853.31 | -2640.32 | 3300.26 | 4204.31 | 6.59 | -1.04 | 6.51 | 99.25 | 92 | 10483.31 | 205841.1 | 3145706.55 | 30.1813 | -96.7068 | 128.66
14427 | 85.59 | 137.79 | 10859.56 | -2710.07 | 3362.96 | 4297.92 | 1.39 | -1.28 | -0.54 | -157.04 | 94 | 10489.56 | 205771.35 | 3145769.25 | 30.1811 | -96.7066 | 128.86
14521 | 84.05 | 136.44 | 10868.04 | -2778.66 | 3426.66 | 4391.44 | 2.17 | -1.64 | -1.44 | -138.94 | 94 | 10498.04 | 205702.76 | 3145832.95 | 30.1809 | -96.7064 | 129.04
14615 | 83.22 | 135.55 | 10878.47 | -2845.85 | 3491.56 | 4484.83 | 1.29 | -0.88 | -0.95 | -133.23 | 94 | 10508.47 | 205635.57 | 3145897.85 | 30.1807 | -96.7062 | 129.18
14709 | 85.14 | 135.94 | 10888 | -2912.83 | 3556.82 | 4578.31 | 2.08 | 2.04 | 0.41 | 11.44 | 94 | 10518 | 205568.59 | 3145963.11 | 30.1805 | -96.706 | 129.32
14804 | 86.85 | 135.69 | 10894.63 | -2980.78 | 3622.87 | 4673.06 | 1.82 | 1.8 | -0.26 | -8.31 | 95 | 10524.63 | 205500.64 | 3146029.16 | 30.1803 | -96.7058 | 129.45
14897 | 88.55 | 134.11 | 10898.36 | -3046.37 | 3688.69 | 4765.97 | 2.49 | 1.83 | -1.7 | -42.92 | 93 | 10528.36 | 205435.05 | 3146094.98 | 30.1801 | -96.7056 | 129.55
14992 | 88.16 | 133.16 | 10901.09 | -3111.9 | 3757.42 | 4860.92 | 1.08 | -0.41 | -1 | -112.34 | 95 | 10531.09 | 205369.52 | 3146163.71 | 30.18 | -96.7054 | 129.63
15087 | 89.76 | 133.19 | 10902.82 | -3176.89 | 3826.68 | 4955.88 | 1.68 | 1.68 | 0.03 | 1.07 | 95 | 10532.82 | 205304.53 | 3146232.97 | 30.1798 | -96.7052 | 129.7
15182 | 87.96 | 132.63 | 10904.71 | -3241.55 | 3896.25 | 5050.81 | 1.98 | -1.89 | -0.59 | -162.73 | 95 | 10534.71 | 205239.87 | 3146302.54 | 30.1796 | -96.705 | 129.76
15277 | 87.96 | 132.86 | 10908.09 | -3305.99 | 3965.97 | 5145.71 | 0.24 | 0 | 0.24 | 90 | 95 | 10538.09 | 205175.43 | 3146372.26 | 30.1794 | -96.7048 | 129.81
15371 | 87.97 | 131.71 | 10911.43 | -3369.2 | 4035.46 | 5239.57 | 1.22 | 0.01 | -1.22 | -89.52 | 94 | 10541.43 | 205112.22 | 3146441.75 | 30.1792 | -96.7046 | 129.86
15466 | 89.08 | 131.9 | 10913.87 | -3432.5 | 4106.25 | 5334.43 | 1.19 | 1.17 | 0.2 | 9.71 | 95 | 10543.87 | 205048.92 | 3146512.54 | 30.179 | -96.7043 | 129.89
15561 | 88.13 | 132.84 | 10916.18 | -3496.5 | 4176.42 | 5429.34 | 1.41 | -1 | 0.99 | 135.32 | 95 | 10546.18 | 204984.92 | 3146582.71 | 30.1789 | -96.7041 | 129.94
15655 | 87.5 | 131.84 | 10919.77 | -3559.77 | 4245.85 | 5523.2 | 1.26 | -0.67 | -1.06 | -122.25 | 94 | 10549.77 | 204921.65 | 3146652.14 | 30.1787 | -96.7039 | 129.98
15749 | 87.25 | 132.15 | 10924.07 | -3622.59 | 4315.64 | 5617.01 | 0.42 | -0.27 | 0.33 | 128.92 | 94 | 10554.07 | 204858.83 | 3146721.93 | 30.1785 | -96.7037 | 130.01
15843 | 87.27 | 134.07 | 10928.57 | -3686.76 | 4384.18 | 5710.87 | 2.04 | 0.02 | 2.04 | 89.45 | 94 | 10558.57 | 204794.66 | 3146790.47 | 30.1783 | -96.7035 | 130.06
15938 | 87.01 | 135.09 | 10933.31 | -3753.35 | 4451.76 | 5805.75 | 1.11 | -0.27 | 1.07 | 104.34 | 95 | 10563.31 | 204728.07 | 3146858.05 | 30.1781 | -96.7033 | 130.13
16032 | 87 | 135.02 | 10938.22 | -3819.8 | 4518.07 | 5899.61 | 0.08 | -0.01 | -0.07 | -98.14 | 94 | 10568.22 | 204661.62 | 3146924.36 | 30.1779 | -96.7031 | 130.21
16127 | 87.22 | 135.53 | 10943.01 | -3887.21 | 4584.84 | 5994.49 | 0.58 | 0.23 | 0.54 | 66.65 | 95 | 10573.01 | 204594.21 | 3146991.13 | 30.1777 | -96.7029 | 130.29
16220 | 87.29 | 137.21 | 10947.46 | -3954.44 | 4648.93 | 6087.33 | 1.81 | 0.08 | 1.81 | 87.65 | 93 | 10577.46 | 204526.98 | 3147055.22 | 30.1776 | -96.7027 | 130.38
16315 | 86.93 | 136.87 | 10952.25 | -4023.88 | 4713.59 | 6182.12 | 0.52 | -0.38 | -0.36 | -136.68 | 95 | 10582.25 | 204457.54 | 3147119.88 | 30.1774 | -96.7025 | 130.49
16409 | 87.32 | 136.44 | 10956.97 | -4092.15 | 4778.03 | 6275.93 | 0.62 | 0.41 | -0.46 | -47.77 | 94 | 10586.97 | 204389.27 | 3147184.32 | 30.1772 | -96.7023 | 130.58
16502 | 87.26 | 139.86 | 10961.37 | -4161.34 | 4840 | 6368.63 | 3.67 | -0.06 | 3.68 | 91.09 | 93 | 10591.37 | 204320.08 | 3147246.29 | 30.177 | -96.7021 | 130.69
16597 | 87.15 | 136.62 | 10966 | -4232.11 | 4903.19 | 6463.3 | 3.41 | -0.12 | -3.41 | -92.03 | 95 | 10596 | 204249.31 | 3147309.48 | 30.1768 | -96.7019 | 130.8
16692 | 86 | 133.43 | 10971.68 | -4299.18 | 4970.2 | 6558.12 | 3.56 | -1.21 | -3.36 | -109.95 | 95 | 10601.68 | 204182.24 | 3147376.49 | 30.1766 | -96.7017 | 130.86
16786 | 86.26 | 132.8 | 10978.02 | -4363.28 | 5038.66 | 6651.87 | 0.72 | 0.28 | -0.67 | -67.55 | 94 | 10608.02 | 204118.14 | 3147444.95 | 30.1764 | -96.7015 | 130.89
16881 | 88.55 | 132.11 | 10982.32 | -4427.34 | 5108.68 | 6746.71 | 2.52 | 2.41 | -0.73 | -16.77 | 95 | 10612.32 | 204054.08 | 3147514.97 | 30.1762 | -96.7013 | 130.91
16974 | 84.8 | 132.24 | 10987.71 | -4489.66 | 5177.47 | 6839.46 | 4.03 | -4.03 | 0.14 | 178.02 | 93 | 10617.71 | 203991.76 | 3147583.76 | 30.176 | -96.7011 | 130.93
17068 | 84.3 | 133.64 | 10996.64 | -4553.4 | 5245.97 | 6932.99 | 1.58 | -0.53 | 1.49 | 109.8 | 94 | 10626.64 | 203928.02 | 3147652.26 | 30.1759 | -96.7008 | 130.96
17163 | 85.55 | 134.14 | 11005.05 | -4619.01 | 5314.17 | 7027.61 | 1.42 | 1.32 | 0.53 | 21.75 | 95 | 10635.05 | 203862.41 | 3147720.46 | 30.1757 | -96.7006 | 131
17256 | 85.93 | 133.66 | 11011.95 | -4683.31 | 5380.99 | 7120.35 | 0.66 | 0.41 | -0.52 | -51.57 | 93 | 10641.95 | 203798.11 | 3147787.28 | 30.1755 | -96.7004 | 131.03
17350 | 89.02 | 134.22 | 11016.1 | -4748.47 | 5448.61 | 7214.24 | 3.34 | 3.29 | 0.6 | 10.28 | 94 | 10646.1 | 203732.95 | 3147854.9 | 30.1753 | -96.7002 | 131.07
17444 | 87.67 | 133.69 | 11018.81 | -4813.69 | 5516.24 | 7308.19 | 1.54 | -1.44 | -0.56 | -158.58 | 94 | 10648.81 | 203667.73 | 3147922.53 | 30.1751 | -96.7 | 131.11
17539 | 87.64 | 134.59 | 11022.7 | -4879.79 | 5584.36 | 7403.11 | 0.95 | -0.03 | 0.95 | 91.93 | 95 | 10652.7 | 203601.63 | 3147990.65 | 30.1749 | -96.6998 | 131.15
17633 | 91.04 | 135.14 | 11023.78 | -4946.09 | 5650.97 | 7497.09 | 3.66 | 3.62 | 0.59 | 9.19 | 94 | 10653.78 | 203535.33 | 3148057.26 | 30.1747 | -96.6996 | 131.19
17728 | 91.43 | 133.91 | 11021.73 | -5012.69 | 5718.69 | 7592.06 | 1.36 | 0.41 | -1.29 | -72.39 | 95 | 10651.73 | 203468.73 | 3148124.98 | 30.1746 | -96.6994 | 131.24
17822 | 89.66 | 134.12 | 11020.84 | -5078 | 5786.28 | 7686.05 | 1.9 | -1.88 | 0.22 | 173.23 | 94 | 10650.84 | 203403.42 | 3148192.57 | 30.1744 | -96.6992 | 131.27
17910 | 85.77 | 134.76 | 11024.35 | -5139.55 | 5849.05 | 7773.97 | 4.48 | -4.42 | 0.73 | 170.68 | 88 | 10654.35 | 203341.87 | 3148255.34 | 30.1742 | -96.699 | 131.31
18005 | 84.91 | 134.69 | 11032.06 | -5206.18 | 5916.32 | 7868.65 | 0.91 | -0.91 | -0.07 | -175.36 | 95 | 10662.06 | 203275.24 | 3148322.61 | 30.174 | -96.6988 | 131.35
18098 | 84.56 | 134.82 | 11040.6 | -5271.38 | 5982.08 | 7961.26 | 0.4 | -0.38 | 0.14 | 159.71 | 93 | 10670.6 | 203210.04 | 3148388.37 | 30.1738 | -96.6986 | 131.39
18193 | 85.53 | 134.82 | 11048.8 | -5338.09 | 6049.22 | 8055.9 | 1.02 | 1.02 | 0 | 0 | 95 | 10678.8 | 203143.33 | 3148455.51 | 30.1736 | -96.6984 | 131.43
18288 | 85.18 | 134.24 | 11056.5 | -5404.5 | 6116.72 | 8150.59 | 0.71 | -0.37 | -0.61 | -121.22 | 95 | 10686.5 | 203076.92 | 3148523.01 | 30.1734 | -96.6982 | 131.46
18382 | 88.05 | 134.59 | 11062.05 | -5470.16 | 6183.74 | 8244.41 | 3.08 | 3.05 | 0.37 | 6.95 | 94 | 10692.05 | 203011.26 | 3148590.03 | 30.1733 | -96.698 | 131.5
18477 | 88.98 | 134.63 | 11064.51 | -5536.85 | 6251.34 | 8339.38 | 0.98 | 0.98 | 0.04 | 2.46 | 95 | 10694.51 | 202944.57 | 3148657.63 | 30.1731 | -96.6978 | 131.53
18571 | 89.33 | 134.29 | 11065.89 | -5602.69 | 6318.43 | 8433.37 | 0.52 | 0.37 | -0.36 | -44.17 | 94 | 10695.89 | 202878.73 | 3148724.72 | 30.1729 | -96.6976 | 131.56
18666 | 89.58 | 134.17 | 11066.8 | -5668.95 | 6386.5 | 8528.36 | 0.29 | 0.26 | -0.13 | -25.64 | 95 | 10696.8 | 202812.47 | 3148792.79 | 30.1727 | -96.6974 | 131.59
18760 | 87.58 | 135.29 | 11069.13 | -5735.08 | 6453.25 | 8622.33 | 2.44 | -2.13 | 1.19 | 150.77 | 94 | 10699.13 | 202746.34 | 3148859.54 | 30.1725 | -96.6971 | 131.63
18856 | 88.28 | 135.68 | 11072.6 | -5803.49 | 6520.51 | 8718.25 | 0.83 | 0.73 | 0.41 | 29.12 | 96 | 10702.6 | 202677.93 | 3148926.8 | 30.1723 | -96.6969 | 131.67
18951 | 88.24 | 135.42 | 11075.48 | -5871.27 | 6587.01 | 8813.19 | 0.28 | -0.04 | -0.27 | -98.75 | 95 | 10705.48 | 202610.15 | 3148993.3 | 30.1721 | -96.6967 | 131.71
19045 | 86.07 | 134.41 | 11080.15 | -5937.56 | 6653.49 | 8907.07 | 2.55 | -2.31 | -1.07 | -155.09 | 94 | 10710.15 | 202543.86 | 3149059.78 | 30.1719 | -96.6965 | 131.75
19137 | 85.5 | 133.71 | 11086.91 | -6001.36 | 6719.42 | 8998.81 | 0.98 | -0.62 | -0.76 | -129.26 | 92 | 10716.91 | 202480.06 | 3149125.71 | 30.1717 | -96.6963 | 131.77
19232 | 84.36 | 133.91 | 11095.3 | -6066.87 | 6787.71 | 9093.43 | 1.22 | -1.2 | 0.21 | 170.1 | 95 | 10725.3 | 202414.55 | 3149194 | 30.1716 | -96.6961 | 131.79
19327 | 85.32 | 133.88 | 11103.85 | -6132.47 | 6855.89 | 9188.04 | 1.01 | 1.01 | -0.03 | -1.78 | 95 | 10733.85 | 202348.95 | 3149262.18 | 30.1714 | -96.6959 | 131.81

## 2_1_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 02/01/2022 |  |  | Report Time: |  | 06:00-24:00
|  |  |  | Daily Cost($): |  | 16380 |  |  | Well Cost($): |  | 16380
|  |  |  | 24hr Summary: |  | Standby, M/U BHA 1 Drill surface
|  |  |  | 24hr Lookahead: |  | Standby for Casing Ops and Nipple Up
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 2828 |  | 2828 |  | OD (in): |  | 20 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 2720 |  | 2720 |  | Weight (ft/lbs): |  | 40 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): |  | 207 |  | 207 | [5 empty] | 100: | 1 | Chlorides:
Rotary Drilled (Usft): |  | 2513 |  | 2513 | [5 empty] | 6: | 1 | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.15 / 3.47 |  | 4.15 / 3.47 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0/100
Slide Drilling Hrs: |  | 0.75 |  | 0.75 |  | SN: |  | 47245 |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: |  | 3.4 |  | 3.4 |  | Bit # |  | 1 |  | PH / Temp(F) | 0.0 / 100.00 | Fluid Loss / Mud Type: | 100 / FW
ROP Rot/Slide (Usft/hr): |  | 739.12 / 276.00 |  | 739.12 / 276.00 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 10.17 |  | 10.17 |  | Grade In: |  | 0-0-NO-A-X-I-NO-TD
% Slide: |  | 7.61 |  | 7.61 |  | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
% Rotary: |  | 92.39 |  | 92.39 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 1.50 Stab HPW -.013 NBS 13 |  |  |  | 8 | 2 |  |  |  |  | 37.47 |  | 38.97
Nortrak Stabilizer (BFF) |  |  |  | 13 | 2.875 |  |  |  |  | 7.87 |  | 46.84
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 9.99 |  | 56.83
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.96 |  | 60.79
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 29.64 |  | 90.43
Drill Collar (NO HARDBANDING) |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.59 |  | 120.02
Crossover Sub |  |  |  | 7.688 | 3.25 |  |  |  |  | 3.17 |  | 123.19
11 Jts 5" HWDP |  |  |  | 5 | 3 |  |  |  |  | 334.01 |  | 457.2
457.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800035 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.82 |  | 1.5 |  | 0.15 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
199 | 0.46 | 81.51 | 199 | 0.12 | 0.79 | 0.23 |  | 81.51 | 0.48 | 0.23 |  | 0 | 199
291 | 0.77 | 109.25 | 290.99 | -0.03 | 1.74 | 0.46 |  | 58.28 | 1.26 | 0.34 |  | 0 | 92
382 | 0.29 | 132.43 | 381.99 | -0.39 | 2.49 | 0.57 |  | 167.22 | 2.04 | -0.53 |  | 0 | 91
476 | 0.7 | 80.86 | 475.99 | -0.46 | 3.23 | 0.6 |  | -75.18 | 2.62 | 0.44 |  | 0 | 94
570 | 1.05 | 77.25 | 569.97 | -0.18 | 4.64 | 0.38 |  | -10.76 | 3.43 | 0.37 |  | 0 | 94
664 | 1.86 | 55.73 | 663.94 | 0.87 | 6.74 | 1.03 |  | -45.08 | 4.19 | 0.86 |  | 0 | 94
758 | 1.96 | 70.25 | 757.89 | 2.27 | 9.51 | 0.52 |  | 85.64 | 5.18 | 0.11 |  | 15.45 | 94
851 | 2.2 | 66.2 | 850.83 | 3.53 | 12.64 | 0.3 |  | -33.52 | 6.53 | 0.26 |  | -4.35 | 93
945 | 3.15 | 59.21 | 944.73 | 5.58 | 16.51 | 1.07 |  | -22.47 | 7.85 | 1.01 |  | -7.44 | 94
1039 | 4.02 | 58.68 | 1038.54 | 8.62 | 21.54 | 0.93 |  | -2.45 | 9.31 | 0.93 |  | -0.56 | 94
1132 | 4.91 | 63.18 | 1131.26 | 12.11 | 27.88 | 1.03 |  | 23.74 | 11.38 | 0.96 |  | 4.84 | 93
1227 | 4.48 | 66.74 | 1225.94 | 15.41 | 34.92 | 0.55 |  | 147.64 | 14.09 | -0.45 |  | 3.75 | 95
1320 | 5.18 | 66.39 | 1318.61 | 18.52 | 42.1 | 0.75 |  | -2.59 | 17.02 | 0.75 |  | -0.38 | 93
1414 | 6.48 | 68.4 | 1412.12 | 22.18 | 50.92 | 1.4 |  | 9.93 | 20.75 | 1.38 |  | 2.14 | 94
1508 | 7.04 | 69.82 | 1505.47 | 26.12 | 61.26 | 0.62 |  | 17.33 | 25.36 | 0.6 |  | 1.51 | 94
1602 | 7.44 | 68.98 | 1598.72 | 30.29 | 72.35 | 0.44 |  | -15.24 | 30.34 | 0.43 |  | -0.89 | 94
1696 | 8.21 | 73.34 | 1691.84 | 34.39 | 84.46 | 1.03 |  | 39.8 | 36.09 | 0.82 |  | 4.64 | 94
1789 | 8.92 | 78.57 | 1783.81 | 37.73 | 97.89 | 1.13 |  | 50.26 | 43.33 | 0.76 |  | 5.62 | 93
1883 | 9.81 | 80.41 | 1876.55 | 40.5 | 112.93 | 1 |  | 19.5 | 52.1 | 0.95 |  | 1.96 | 94
1977 | 9.49 | 77.26 | 1969.22 | 43.55 | 128.38 | 0.66 |  | -122.76 | 60.98 | -0.34 |  | -3.35 | 94
2071 | 10.1 | 76.52 | 2061.85 | 47.18 | 143.96 | 0.66 |  | -12.03 | 69.54 | 0.65 |  | -0.79 | 94
2164 | 10.61 | 73.48 | 2153.34 | 51.51 | 160.09 | 0.8 |  | -48.48 | 78 | 0.55 |  | -3.27 | 93
2259 | 10.52 | 70.1 | 2246.73 | 56.95 | 176.63 | 0.66 |  | -99.92 | 85.98 | -0.09 |  | -3.56 | 95
2354 | 10.87 | 70.46 | 2340.08 | 62.9 | 193.23 | 0.38 |  | 10.98 | 93.64 | 0.37 |  | 0.38 | 95
2448 | 11.29 | 71.19 | 2432.33 | 68.83 | 210.29 | 0.47 |  | 18.83 | 101.64 | 0.45 |  | 0.78 | 94
2542 | 11.48 | 69.56 | 2524.48 | 75.06 | 227.77 | 0.4 |  | -60.24 | 109.73 | 0.2 |  | -1.73 | 94
2635 | 10.72 | 69.8 | 2615.74 | 81.28 | 244.56 | 0.82 |  | 176.64 | 117.34 | -0.82 |  | 0.26 | 93
2729 | 10.55 | 72.71 | 2708.12 | 86.86 | 260.98 | 0.6 |  | 108.99 | 125.13 | -0.18 |  | 3.1 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 655.42 | 16.5 | 94.76 | 230 | 872.22 | 1889.81 | 1587.04 | 281 | 95.61 | 91.35 | 89.11 | 8.66 | 4
Run | 655.42 | 16.5 | 94.76 | 230 | 872.22 | 1889.81 | 1587.04 | 281 | 95.61 | 91.35 | 89.11 | 8.66 | 4
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Job Start-Up Incidentals |  |  |  |  | 02/01/2022 |  | 1 |  | 6000 |  | 1 | 6000
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 02/01/2022 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 02/01/2022 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 02/01/2022 |  | 7 |  | 100 |  | 4 | 400
Personnel Mileage |  |  |  |  | 02/01/2022 |  | 8 |  | 2 |  | 800 | 1600
Stabilizer Rental 13 Used |  |  |  |  | 02/01/2022 | GT801175 | 17 |  | 1150 |  | 1 | 1150
Stabilizer Rental 13 Not Used |  |  |  |  | 02/01/2022 | GT801171 | 18 |  | 230 |  | 1 | 230
Total | [11 empty] | 16380
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
02/01/2022 | 06:00 | 11:00 | 5 | 108 | 108 | 0 | SUR |  | 24B | Standby to MU BHA 1
02/01/2022 | 11:00 | 11:20 | 0.33 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | M/U BHA 1 out of derrick
02/01/2022 | 11:20 | 11:35 | 0.25 | 108 | 183 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/183.00, w/WOB 5,Flow 400, RPM 40, Press 450, Tq 2, ROP 300.00, Diff 100.00, Temp 75.00
02/01/2022 | 11:35 | 11:41 | 0.1 | 183 | 183 | 0 | SUR | 1: BHA 1 | 5A | Connection
02/01/2022 | 11:41 | 11:52 | 0.18 | 183 | 274 | 91 | SUR | 1: BHA 1 | 2K | Rotary Drill f/183.00 t/274.00, w/WOB 5.00,Flow 500, RPM 50, Press 550, Tq 4, ROP 496.36, Diff 100.00, Temp 75.00
02/01/2022 | 11:52 | 11:57 | 0.08 | 274 | 274 | 0 | SUR | 1: BHA 1 | 5A | Attempt survey, tool not pulsing
02/01/2022 | 11:57 | 12:17 | 0.33 | 274 | 274 | 0 | SUR | 1: BHA 1 | 6B | POOH t/ MWD
02/01/2022 | 12:17 | 12:40 | 0.38 | 274 | 274 | 0 | SUR | 1: BHA 1 | 20C | Pull MWD, Tap test tool - good, seat tool, M/U NMDC
02/01/2022 | 12:40 | 12:45 | 0.08 | 274 | 274 | 0 | SUR | 1: BHA 1 | 5A | Shallow Test MWD, tool pulsing
02/01/2022 | 12:45 | 12:50 | 0.08 | 274 | 274 | 0 | SUR | 1: BHA 1 | 6A | TIH
02/01/2022 | 12:50 | 12:55 | 0.08 | 274 | 274 | 0 | SUR | 1: BHA 1 | 5A | Survey
02/01/2022 | 12:55 | 13:05 | 0.17 | 274 | 366 | 92 | SUR | 1: BHA 1 | 2K | Rotary Drill f/274.00 t/366.00, w/WOB 5.00,Flow 600.00, RPM 60.00, Press 750.00, Tq 5.00, ROP 552.00, Diff 150.00, Temp 80.00
02/01/2022 | 13:05 | 13:11 | 0.1 | 366 | 366 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 13:11 | 13:19 | 0.13 | 366 | 457 | 91 | SUR | 1: BHA 1 | 2K | Rotary Drill f/366.00 t/457.00, w/WOB 8.00,Flow 700.00, RPM 70.00, Press 1000.00, Tq 7.00, ROP 682.50, Diff 200.00, Temp 80.00
02/01/2022 | 13:19 | 13:23 | 0.07 | 457 | 457 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 13:23 | 13:30 | 0.12 | 457 | 551 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/457.00 t/551.00, w/WOB 15.00,Flow 800.00, RPM 80.00, Press 1300.00, Tq 7.00, ROP 805.71, Diff 200.00, Temp 82.40
02/01/2022 | 13:30 | 13:35 | 0.08 | 551 | 551 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 13:35 | 13:38 | 0.05 | 551 | 566 | 15 | SUR | 1: BHA 1 | 2K | Rotary Drill f/551.00 t/566.00, w/WOB 15.00,Flow 900, RPM 90, Press 1750, Tq 6, ROP 300.00, Diff 250.00, Temp 82.40
02/01/2022 | 13:38 | 13:41 | 0.05 | 566 | 581 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/566.00 t/581.00, TF M, w/WOB 5,Flow 900, Press 1600, Tq 0, ROP 300.00, Diff 100.00, Temp 82.40
02/01/2022 | 13:41 | 13:45 | 0.07 | 581 | 645 | 64 | SUR | 1: BHA 1 | 2K | Rotary Drill f/581.00 t/645.00, w/WOB 15.00,Flow 900, RPM 90, Press 1750, Tq 6, ROP 960.00, Diff 250.00, Temp 82.40
02/01/2022 | 13:45 | 13:51 | 0.1 | 645 | 645 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 13:51 | 13:56 | 0.08 | 645 | 739 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/645.00 t/739.00, w/WOB 18,Flow 900.00, RPM 100, Press 1900, Tq 8.8, ROP 1128.00, Diff 400.00, Temp 82.40
02/01/2022 | 13:56 | 14:02 | 0.1 | 739 | 739 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 14:02 | 14:07 | 0.08 | 739 | 833 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/739.00 t/833.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 8.80, ROP 1128.00, Diff 400.00, Temp 82.40
02/01/2022 | 14:07 | 14:13 | 0.1 | 833 | 833 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 14:13 | 14:15 | 0.03 | 833 | 848 | 15 | SUR | 1: BHA 1 | 2K | Rotary Drill f/833.00 t/848.00, w/WOB 15,Flow 900.00, RPM 100.00, Press 1900.00, Tq 8.80, ROP 450.00, Diff 400.00, Temp 82.40
02/01/2022 | 14:15 | 14:18 | 0.05 | 848 | 868 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/848.00 t/868.00, TF M, w/WOB 5,Flow 900.00, Press 1700, Tq 0, ROP 400.00, Diff 200.00, Temp 82.40
02/01/2022 | 14:18 | 14:21 | 0.05 | 868 | 926 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/868.00 t/926.00, w/WOB 25,Flow 900.00, RPM 100.00, Press 1900.00, Tq 8.80, ROP 1160.00, Diff 400.00, Temp 82.40
02/01/2022 | 14:21 | 14:26 | 0.08 | 926 | 926 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 14:26 | 14:31 | 0.08 | 926 | 1020 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/926.00 t/1020.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 8.80, ROP 1128.00, Diff 400.00, Temp 82.40
02/01/2022 | 14:31 | 14:36 | 0.08 | 1020 | 1020 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 14:36 | 14:38 | 0.03 | 1020 | 1035 | 15 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1020.00 t/1035.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 8.80, ROP 450.00, Diff 300.00, Temp 82.40
02/01/2022 | 14:38 | 14:42 | 0.07 | 1035 | 1055 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1035.00 t/1055.00, TF 30.00G, w/WOB 5.00,Flow 900.00, Press 1700.00, Tq 0.00, ROP 300.00, Diff 100.00, Temp 82.40
02/01/2022 | 14:42 | 14:45 | 0.05 | 1055 | 1114 | 59 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1055.00 t/1114.00, w/WOB 22.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 8.80, ROP 1180.00, Diff 300.00, Temp 82.40
02/01/2022 | 14:45 | 14:50 | 0.08 | 1114 | 1114 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 14:50 | 14:56 | 0.1 | 1114 | 1207 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1114.00 t/1207.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 7.20, ROP 930.00, Diff 300.00, Temp 82.40
02/01/2022 | 14:56 | 15:02 | 0.1 | 1207 | 1207 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 15:02 | 15:09 | 0.12 | 1207 | 1302 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1207.00 t/1302.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 7.20, ROP 814.29, Diff 400.00, Temp 87.80
02/01/2022 | 15:09 | 15:14 | 0.08 | 1302 | 1302 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 15:14 | 15:16 | 0.03 | 1302 | 1313 | 11 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1302.00 t/1313.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 7.20, ROP 330.00, Diff 400.00, Temp 87.80
02/01/2022 | 15:16 | 15:19 | 0.05 | 1313 | 1333 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1313.00 t/1333.00, TF 30.00G, w/WOB 8.00,Flow 900.00, Press 1700.00, Tq 0.00, ROP 400.00, Diff 100.00, Temp 87.80
02/01/2022 | 15:19 | 15:23 | 0.07 | 1333 | 1395 | 62 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1333.00 t/1395.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8.20, ROP 930.00, Diff 400.00, Temp 87.80
02/01/2022 | 15:23 | 15:29 | 0.1 | 1395 | 1395 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 15:29 | 15:32 | 0.05 | 1395 | 1415 | 20 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1395.00 t/1415.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8.20, ROP 400.00, Diff 400.00, Temp 87.80
02/01/2022 | 15:32 | 15:35 | 0.05 | 1415 | 1430 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1415.00 t/1430.00, TF 60.00G, w/WOB 8.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 300.00, Diff 150.00, Temp 87.80
02/01/2022 | 15:35 | 15:40 | 0.08 | 1430 | 1489 | 59 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1430.00 t/1489.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8.20, ROP 708.00, Diff 300.00, Temp 87.80
02/01/2022 | 15:40 | 15:46 | 0.1 | 1489 | 1489 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 15:46 | 15:52 | 0.1 | 1489 | 1583 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1489.00 t/1583.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 9.30, ROP 940.00, Diff 300.00, Temp 87.80
02/01/2022 | 15:52 | 15:57 | 0.08 | 1583 | 1583 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 15:57 | 15:59 | 0.03 | 1583 | 1595 | 12 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1583.00 t/1595.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 9.30, ROP 360.00, Diff 300.00, Temp 87.80
02/01/2022 | 15:59 | 16:03 | 0.07 | 1595 | 1615 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1595.00 t/1615.00, TF 60.00G, w/WOB 8.00,Flow 900.00, Press 1800.00, Tq 0.00, ROP 300.00, Diff 100.00, Temp 87.80
02/01/2022 | 16:03 | 16:07 | 0.07 | 1615 | 1677 | 62 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1615.00 t/1677.00, w/WOB 22.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 9.30, ROP 930.00, Diff 300.00, Temp 93.20
02/01/2022 | 16:07 | 16:13 | 0.1 | 1677 | 1677 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 16:13 | 16:15 | 0.03 | 1677 | 1695 | 18 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1677.00 t/1695.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 9.30, ROP 540.00, Diff 300.00, Temp 93.20
02/01/2022 | 16:15 | 16:18 | 0.05 | 1695 | 1710 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1695.00 t/1710.00, TF 60.00G, w/WOB 10.00,Flow 900.00, Press 1850.00, Tq 0.00, ROP 300.00, Diff 150.00, Temp 93.20
02/01/2022 | 16:18 | 16:21 | 0.05 | 1710 | 1771 | 61 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1710.00 t/1771.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 10.10, ROP 1220.00, Diff 400.00, Temp 93.20
02/01/2022 | 16:21 | 16:28 | 0.12 | 1771 | 1771 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 16:28 | 16:30 | 0.03 | 1771 | 1789 | 18 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1771.00 t/1789.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 10.10, ROP 540.00, Diff 200.00, Temp 93.20
02/01/2022 | 16:30 | 16:34 | 0.07 | 1789 | 1809 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1789.00 t/1809.00, TF 30.00G, w/WOB 12.00,Flow 900.00, Press 1900.00, Tq 0.00, ROP 300.00, Diff 200.00, Temp 93.20
02/01/2022 | 16:34 | 16:38 | 0.07 | 1809 | 1864 | 55 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1809.00 t/1864.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 10.10, ROP 825.00, Diff 400.00, Temp 93.20
02/01/2022 | 16:38 | 16:44 | 0.1 | 1864 | 1864 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 16:44 | 16:51 | 0.12 | 1864 | 1958 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1864.00 t/1958.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 805.71, Diff 400.00, Temp 93.20
02/01/2022 | 16:51 | 16:57 | 0.1 | 1958 | 1958 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 16:57 | 17:00 | 0.05 | 1958 | 1977 | 19 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1958.00 t/1977.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 380.00, Diff 400.00, Temp 93.20
02/01/2022 | 17:00 | 17:05 | 0.08 | 1977 | 1992 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1977.00 t/1992.00, TF 0.00G, w/WOB 12.00,Flow 900.00, Press 2000.00, Tq 0.00, ROP 180.00, Diff 200.00, Temp 93.20
02/01/2022 | 17:05 | 17:10 | 0.08 | 1992 | 2052 | 60 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1992.00 t/2052.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2300.00, Tq 10.10, ROP 720.00, Diff 500.00, Temp 93.20
02/01/2022 | 17:10 | 17:16 | 0.1 | 2052 | 2052 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 17:16 | 17:19 | 0.05 | 2052 | 2072 | 20 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2052.00 t/2072.00, w/WOB 15,Flow 900.00, RPM 100.00, Press 2100, Tq 10.10, ROP 400.00, Diff 300.00, Temp 96.80
02/01/2022 | 17:19 | 17:23 | 0.07 | 2072 | 2087 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2072.00 t/2087.00, TF G, w/WOB 12,Flow 900.00, Press 2000, Tq 0, ROP 225.00, Diff 200.00, Temp 96.80
02/01/2022 | 17:23 | 17:27 | 0.07 | 2087 | 2146 | 59 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2087.00 t/2146.00, w/WOB 22,Flow 900.00, RPM 100.00, Press 2200, Tq 10.10, ROP 885.00, Diff 400.00, Temp 96.80
02/01/2022 | 17:27 | 17:32 | 0.08 | 2146 | 2146 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 17:32 | 17:38 | 0.1 | 2146 | 2239 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2146.00 t/2239.00, w/WOB 22.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 930.00, Diff 400.00, Temp 96.80
02/01/2022 | 17:38 | 17:43 | 0.08 | 2239 | 2239 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 17:43 | 17:49 | 0.1 | 2239 | 2334 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2239.00 t/2334.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 950.00, Diff 400.00, Temp 96.80
02/01/2022 | 17:49 | 17:54 | 0.08 | 2334 | 2334 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 17:54 | 17:58 | 0.07 | 2334 | 2354 | 20 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2334.00 t/2354.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 300.00, Diff 400.00, Temp 96.80
02/01/2022 | 17:58 | 18:02 | 0.07 | 2354 | 2371 | 17 | SUR | 1: BHA 1 | 2J | Slide Drill f/2354.00 t/2371.00, TF 60.00G, w/WOB 15.00,Flow 900.00, Press 2000.00, Tq 0.00, ROP 255.00, Diff 200.00, Temp 96.80
02/01/2022 | 18:02 | 18:06 | 0.07 | 2371 | 2429 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2371.00 t/2429.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 870.00, Diff 400.00, Temp 96.80
02/01/2022 | 18:06 | 18:12 | 0.1 | 2429 | 2429 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 18:12 | 18:18 | 0.1 | 2429 | 2523 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2429.00 t/2523.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 940.00, Diff 400.00, Temp 96.80
02/01/2022 | 18:18 | 18:22 | 0.07 | 2523 | 2523 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 18:22 | 18:29 | 0.12 | 2523 | 2617 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2523.00 t/2617.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 805.71, Diff 400.00, Temp 96.80
02/01/2022 | 18:29 | 18:33 | 0.07 | 2617 | 2617 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 18:33 | 18:35 | 0.03 | 2617 | 2627 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2617.00 t/2627.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 300.00, Diff 400.00, Temp 96.80
02/01/2022 | 18:35 | 18:40 | 0.08 | 2627 | 2642 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2627.00 t/2642.00, TF 120.00G, w/WOB 25.00,Flow 900.00, Press 2200.00, Tq 10.10, ROP 180.00, Diff 400.00, Temp 96.80
02/01/2022 | 18:40 | 18:44 | 0.07 | 2642 | 2710 | 68 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2642.00 t/2710.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 1020.00, Diff 400.00, Temp 102.20
02/01/2022 | 18:44 | 18:48 | 0.07 | 2710 | 2710 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 18:48 | 18:56 | 0.13 | 2710 | 2804 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2710.00 t/2804.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 705.00, Diff 400.00, Temp 102.20
02/01/2022 | 18:56 | 19:02 | 0.1 | 2804 | 2804 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
02/01/2022 | 19:02 | 19:04 | 0.03 | 2804 | 2828 | 24 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2804.00 t/2828.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 10.10, ROP 720.00, Diff 400.00, Temp 102.20
02/01/2022 | 19:04 | 19:45 | 0.68 | 2828 | 2828 | 0 | SUR | 1: BHA 1 | 5A | Circulate
02/01/2022 | 19:45 | 20:45 | 1 | 2828 | 2828 | 0 | SUR | 1: BHA 1 | 6B | POOH
02/01/2022 | 20:45 | 21:30 | 0.75 | 2828 | 2828 | 0 | SUR | 1: BHA 1 | 6P | Lay Down BHA 1
02/01/2022 | 21:30 | 24:00 | 2.5 | 2828 | 2828 | 0 | SUR |  | 24B | Standby for Casing Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 2_2_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 02/02/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17900 |  |  | Well Cost($): |  | 34280
|  |  |  | 24hr Summary: |  | Standby for Casing and Cement Ops
|  |  |  | 24hr Lookahead: |  | Standby - Nipple Up - P/U BHA 2
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2828 |  | 2828 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 2828 |  | 2828 |  | OD (in): |  | 10.75 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45.5 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): | [9 empty] | 100: | 1 | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids:
Drlg/Circ Hrs: |  | 0.00 / 0.22 |  | 0.00 / 0.22 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0/100
Slide Drilling Hrs: | [5 empty] | SN: |  | 59253 |  | 10s Gel: | 1 | Weight (ppg): | 8.3
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 100.00 | Fluid Loss / Mud Type: | 100 / FW
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 4 |  | 4 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-WT-A-X-I-NO-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 TS HPW -.012 |  |  |  | 8 | 2 |  |  |  |  | 37.54 |  | 39.04
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 9.99 |  | 49.03
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.96 |  | 52.99
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 29.64 |  | 82.63
Drill Collar (NO HARDBANDING) |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.59 |  | 112.22
Crossover Sub |  |  |  | 7.938 | 3 |  |  |  |  | 3.18 |  | 115.4
6 Jts 6 1/2in DC |  |  |  | 6.5 | 3 |  |  |  |  | 186.19 |  | 301.59
Crossover Sub |  |  |  | 6.688 | 2.812 |  |  |  |  | 3.2 |  | 304.79
11 Jts 5 HWDP |  |  |  | 5 | 3 |  |  |  |  | 334.01 |  | 638.8
22 Stds 5in DP |  |  |  | 5 | 3 |  |  |  |  | 2065.88 |  | 2704.68
Agitator |  |  |  | 6.75 | 2.5 |  |  |  |  | 22.46 |  | 2727.14
2727.14
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR775009 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.15 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 02/02/2022 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 02/02/2022 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 02/02/2022 |  | 7 |  | 100 |  | 4 | 400
8 Motor Reline |  |  |  |  | 02/02/2022 | MTR775009 | 15 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17900
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
02/02/2022 | 00:00 | 18:20 | 18.33 | 2828 | 2828 | 0 | INT |  | 24B | Standby for Casing Ops
02/02/2022 | 18:20 | 20:00 | 1.67 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 6O | Pick Up BHA #2 & Surface Test
02/02/2022 | 20:00 | 22:00 | 2 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 6J | Pick Up 6 Jts 6.5 DCs
02/02/2022 | 22:00 | 23:47 | 1.78 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 6A | TIH
02/02/2022 | 23:47 | 24:00 | 0.22 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 5A | Drill Shoe Float Assembly & Shoe Track
Well Seeker PRO 2.0.8.0 - Pro Directional

## 2_3_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 02/03/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7400 |  |  | Well Cost($): |  | 41680
|  |  |  | 24hr Summary: |  | TIH - Perform FIT - Drill Ahead in Intermediate
|  |  |  | 24hr Lookahead: |  | Drill ahead in intermediate
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2828 |  | 2828 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 10
End Depth (Usft): |  | 9201 |  | 9201 |  | OD (in): |  | 10.75 |  | 300: | 17 | YP: | 7
Total Drilled (Usft): |  | 6373 |  | 6373 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 12 | Viscosity: | 44
Slide Drilled (Usft): |  | 327 |  | 327 | [5 empty] | 100: | 8 | Chlorides:
Rotary Drilled (Usft): |  | 6046 |  | 6046 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.10 / 6.90
Drlg/Circ Hrs: |  | 17.10 / 5.28 |  | 17.10 / 5.50 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 3.85 |  | 3.85 |  | SN: |  | 59253 |  | 10s Gel: | 4 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 13.25 |  | 13.25 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 72.00 | Fluid Loss / Mud Type: | 100 / OBM
ROP Rot/Slide (Usft/hr): |  | 456.30 / 84.94 |  | 456.30 / 84.94 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 28 |  | Grade In: |  | New
% Slide: |  | 5.13 |  | 5.13 |  | Grade Out: |  | 1-1-WT-A-X-I-NO-TD
% Rotary: |  | 94.87 |  | 94.87 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 TS HPW -.012 |  |  |  | 8 | 2 |  |  |  |  | 37.54 |  | 39.04
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 9.99 |  | 49.03
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.96 |  | 52.99
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 29.64 |  | 82.63
Drill Collar (NO HARDBANDING) |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.59 |  | 112.22
Crossover Sub |  |  |  | 7.938 | 3 |  |  |  |  | 3.18 |  | 115.4
6 Jts 6 1/2in DC |  |  |  | 6.5 | 3 |  |  |  |  | 186.19 |  | 301.59
Crossover Sub |  |  |  | 6.688 | 2.812 |  |  |  |  | 3.2 |  | 304.79
11 Jts 5 HWDP |  |  |  | 5 | 3 |  |  |  |  | 334.01 |  | 638.8
22 Stds 5in DP |  |  |  | 5 | 3 |  |  |  |  | 2065.88 |  | 2704.68
Agitator |  |  |  | 6.75 | 2.5 |  |  |  |  | 22.46 |  | 2727.14
2727.14
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR775009 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.15 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2849 | 10.3 | 70.26 | 2826.14 | 93.75 | 281.57 | 0.42 |  | -120.62 | 134.98 | -0.21 |  | -2.04 | 120
2943 | 10.76 | 68.88 | 2918.56 | 99.75 | 297.66 | 0.56 |  | -29.41 | 142.25 | 0.49 |  | -1.47 | 94
3037 | 9.13 | 70.78 | 3011.14 | 105.37 | 312.89 | 1.77 |  | 169.55 | 149.16 | -1.73 |  | 2.02 | 94
3131 | 9.1 | 69.17 | 3103.96 | 110.46 | 326.88 | 0.27 |  | -97.5 | 155.56 | -0.03 |  | -1.71 | 94
3225 | 9.05 | 67.6 | 3196.78 | 115.92 | 340.66 | 0.27 |  | -102.19 | 161.56 | -0.05 |  | -1.67 | 94
3319 | 10.24 | 72.17 | 3289.45 | 121.3 | 355.45 | 1.5 |  | 35.03 | 168.33 | 1.27 |  | 4.86 | 94
3414 | 9.7 | 79.66 | 3383.02 | 125.32 | 371.36 | 1.48 |  | 116.27 | 176.85 | -0.57 |  | 7.88 | 95
3507 | 8.07 | 82.92 | 3474.9 | 127.53 | 385.55 | 1.83 |  | 164.44 | 185.42 | -1.75 |  | 3.51 | 93
3602 | 8.12 | 84.59 | 3568.96 | 128.99 | 398.85 | 0.25 |  | 78.82 | 193.88 | 0.05 |  | 1.76 | 95
3696 | 6.89 | 85.64 | 3662.15 | 130.04 | 411.08 | 1.32 |  | 174.16 | 201.86 | -1.31 |  | 1.12 | 94
3790 | 6.87 | 85.9 | 3755.47 | 130.87 | 422.31 | 0.04 |  | 122.84 | 209.28 | -0.02 |  | 0.28 | 94
3884 | 6.02 | 89.23 | 3848.88 | 131.34 | 432.85 | 0.99 |  | 157.91 | 216.46 | -0.9 |  | 3.54 | 94
3978 | 5.28 | 74.48 | 3942.42 | 132.56 | 441.94 | 1.73 |  | -124.21 | 222.09 | -0.79 |  | -15.69 | 94
4072 | 3.64 | 71.62 | 4036.14 | 134.66 | 448.94 | 1.76 |  | -173.7 | 225.61 | -1.74 |  | -3.04 | 94
4165 | 3.31 | 67.02 | 4128.97 | 136.64 | 454.22 | 0.46 |  | -142.09 | 227.98 | -0.35 |  | -4.95 | 93
4258 | 2.66 | 85.08 | 4221.84 | 137.88 | 458.84 | 1.22 |  | 133.45 | 230.41 | -0.7 |  | 19.42 | 93
4353 | 2.88 | 110.48 | 4316.73 | 137.23 | 463.27 | 1.3 |  | 92.69 | 234.02 | 0.23 |  | 26.74 | 95
4446 | 2.67 | 109.69 | 4409.62 | 135.68 | 467.5 | 0.23 |  | -170.07 | 238.12 | -0.23 |  | -0.85 | 93
4540 | 1.64 | 142.98 | 4503.56 | 133.87 | 470.37 | 1.68 |  | 145.28 | 241.44 | -1.1 |  | 35.41 | 94
4634 | 1.01 | 173.24 | 4597.54 | 131.97 | 471.28 | 0.98 |  | 146.45 | 243.41 | -0.67 |  | 32.19 | 94
4728 | 0.79 | 149.92 | 4691.52 | 130.59 | 471.7 | 0.45 |  | -132.3 | 244.69 | -0.23 |  | 0 | 94
4821 | 0.73 | 172.11 | 4784.52 | 129.45 | 472.1 | 0.32 |  | 112.48 | 245.77 | -0.06 |  | 0 | 93
4915 | 0.54 | 158.64 | 4878.51 | 128.44 | 472.35 | 0.26 |  | -148.45 | 246.65 | -0.2 |  | 0 | 94
5009 | 0.16 | 179.76 | 4972.51 | 127.9 | 472.51 | 0.42 |  | 171.61 | 247.15 | -0.4 |  | 0 | 94
5104 | 0.42 | 283.87 | 5067.51 | 127.85 | 472.17 | 0.51 |  | 122.79 | 246.94 | 0.27 |  | 0 | 95
5197 | 0.7 | 307.59 | 5160.5 | 128.28 | 471.39 | 0.38 |  | 51.89 | 246.09 | 0.3 |  | 0 | 93
5291 | 0.74 | 303.53 | 5254.5 | 128.96 | 470.43 | 0.07 |  | -53.94 | 244.92 | 0.04 |  | 0 | 94
5384 | 0.65 | 316.87 | 5347.49 | 129.68 | 469.57 | 0.2 |  | 125.64 | 243.8 | -0.1 |  | 0 | 93
5477 | 0.67 | 328.26 | 5440.48 | 130.53 | 468.92 | 0.14 |  | 87.06 | 242.75 | 0.02 |  | 0 | 93
5571 | 0.83 | 329.76 | 5534.48 | 131.58 | 468.29 | 0.17 |  | 7.75 | 241.56 | 0.17 |  | 0 | 94
5665 | 0.85 | 345.47 | 5628.47 | 132.85 | 467.77 | 0.25 |  | 92.92 | 240.3 | 0.02 |  | 0 | 94
5758 | 0.94 | 334.84 | 5721.45 | 134.2 | 467.27 | 0.2 |  | -66.92 | 238.99 | 0.1 |  | 0 | 93
5851 | 1.17 | 317.36 | 5814.44 | 135.59 | 466.3 | 0.42 |  | -63.4 | 237.33 | 0.25 |  | 0 | 93
5945 | 1.5 | 316.78 | 5908.41 | 137.2 | 464.81 | 0.35 |  | -2.63 | 235.14 | 0.35 |  | 0 | 94
6038 | 1.62 | 320.04 | 6001.38 | 139.09 | 463.13 | 0.16 |  | 38.12 | 232.62 | 0.13 |  | 3.51 | 93
6132 | 2.17 | 327.76 | 6095.33 | 141.61 | 461.33 | 0.64 |  | 28.79 | 229.56 | 0.59 |  | 8.21 | 94
6226 | 2.06 | 318.87 | 6189.26 | 144.39 | 459.27 | 0.37 |  | -112.94 | 226.15 | -0.12 |  | -9.46 | 94
6320 | 0.91 | 308.58 | 6283.23 | 146.13 | 457.58 | 1.25 |  | -172.05 | 223.72 | -1.22 |  | -10.95 | 94
6414 | 1.03 | 305.46 | 6377.22 | 147.09 | 456.3 | 0.14 |  | -25.32 | 222.14 | 0.13 |  | 0 | 94
6508 | 1.28 | 311.57 | 6471.2 | 148.27 | 454.83 | 0.3 |  | 29.3 | 220.26 | 0.27 |  | 0 | 94
6601 | 1.56 | 327.43 | 6564.17 | 150.03 | 453.37 | 0.52 |  | 62.63 | 217.99 | 0.3 |  | 0 | 93
6695 | 1.82 | 327.41 | 6658.13 | 152.37 | 451.88 | 0.28 |  | -0.14 | 215.29 | 0.28 |  | -0.02 | 94
6789 | 2.13 | 321.33 | 6752.07 | 154.99 | 449.98 | 0.4 |  | -37.12 | 212.1 | 0.33 |  | -6.47 | 94
6883 | 1.5 | 334.19 | 6846.02 | 157.46 | 448.36 | 0.79 |  | 153.43 | 209.2 | -0.67 |  | 13.68 | 94
6977 | 0.91 | 31.81 | 6940.01 | 159.2 | 448.21 | 1.35 |  | 142.8 | 207.88 | -0.63 |  | 61.3 | 94
7071 | 0.9 | 34.78 | 7034 | 160.44 | 449.03 | 0.05 |  | 103.52 | 207.59 | -0.01 |  | 0 | 94
7165 | 0.94 | 18.84 | 7127.98 | 161.78 | 449.7 | 0.27 |  | -89.14 | 207.13 | 0.04 |  | 0 | 94
7259 | 1.05 | 8.11 | 7221.97 | 163.36 | 450.07 | 0.23 |  | -64.88 | 206.29 | 0.12 |  | 0 | 94
7352 | 1.1 | 18.66 | 7314.95 | 165.05 | 450.48 | 0.22 |  | 81.14 | 205.39 | 0.05 |  | 0 | 93
7446 | 1.14 | 4.5 | 7408.93 | 166.84 | 450.84 | 0.3 |  | -88.9 | 204.4 | 0.04 |  | 0 | 94
7540 | 1.3 | 347.03 | 7502.91 | 168.81 | 450.67 | 0.43 |  | -75.62 | 202.89 | 0.17 |  | 0 | 94
7634 | 1.4 | 307.87 | 7596.89 | 170.55 | 449.53 | 0.97 |  | -103.63 | 200.85 | 0.11 |  | 0 | 94
7728 | 1.8 | 310.24 | 7690.85 | 172.21 | 447.49 | 0.43 |  | 10.58 | 198.24 | 0.43 |  | 0 | 94
7822 | 1.19 | 276.79 | 7784.82 | 173.28 | 445.4 | 1.11 |  | -140.9 | 196 | -0.65 |  | -35.59 | 94
7916 | 1.46 | 262.58 | 7878.8 | 173.24 | 443.24 | 0.45 |  | -57.84 | 194.49 | 0.29 |  | 0 | 94
8010 | 0.19 | 216.43 | 7972.79 | 172.96 | 441.96 | 1.42 |  | -174.11 | 193.77 | -1.35 |  | 0 | 94
8104 | 0.51 | 109.66 | 8066.78 | 172.69 | 442.26 | 0.63 |  | -124.62 | 194.17 | 0.34 |  | 0 | 94
8197 | 0.24 | 303.68 | 8159.78 | 172.66 | 442.49 | 0.8 |  | -175.52 | 194.36 | -0.29 |  | 0 | 93
8292 | 0.6 | 307.97 | 8254.78 | 173.08 | 441.93 | 0.38 |  | 7.14 | 193.67 | 0.38 |  | 0 | 95
8385 | 1.04 | 297.42 | 8347.77 | 173.77 | 440.8 | 0.5 |  | -24.26 | 192.38 | 0.47 |  | 0 | 93
8479 | 0.97 | 284.72 | 8441.76 | 174.36 | 439.27 | 0.25 |  | -113.73 | 190.87 | -0.07 |  | 0 | 94
8573 | 0.99 | 69.26 | 8535.75 | 174.85 | 439.26 | 1.99 |  | 162.08 | 190.52 | 0.02 |  | 0 | 94
8666 | 0.87 | 89.4 | 8628.74 | 175.14 | 440.72 | 0.37 |  | 120.04 | 191.36 | -0.13 |  | 0 | 93
8760 | 0.24 | 90.42 | 8722.73 | 175.15 | 441.63 | 0.67 |  | 179.61 | 192 | -0.67 |  | 0 | 94
8854 | 0.05 | 221.29 | 8816.73 | 175.12 | 441.8 | 0.29 |  | 172.11 | 192.14 | -0.2 |  | 0 | 94
8947 | 0.89 | 246.93 | 8909.73 | 174.8 | 441.11 | 0.91 |  | 27.11 | 191.87 | 0.9 |  | 0 | 93
9042 | 1.45 | 227.26 | 9004.71 | 173.7 | 439.55 | 0.72 |  | -45.75 | 191.53 | 0.59 |  | 0 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 372.69 | 27.7 | 78.85 | 215 | 877.14 | 4884.43 | 4461.31 | 0 | 186.01 | 173.38 | 160.94 | 11.76 | 0
Run | 372.69 | 27.7 | 78.85 | 215 | 877.14 | 4884.43 | 4461.31 | 0 | 186.01 | 173.38 | 160.94 | 11.76 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 02/03/2022 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 02/03/2022 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 02/03/2022 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 7400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
02/03/2022 | 00:00 | 00:23 | 0.38 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 5A | Drill Float Assembly & Shoe Track
02/03/2022 | 00:23 | 01:37 | 1.23 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 24A | Pull Trip Nipple / Install Rotating Head
02/03/2022 | 01:37 | 02:01 | 0.4 | 2828 | 2828 | 0 | INT | 2: BHA 2 | 5A | Drill Float Assembly & Shoe Track
02/03/2022 | 02:01 | 02:05 | 0.07 | 2828 | 2838 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/2828.00 t/2838.00, w/WOB 11,Flow 477, RPM 30, Press 1695, Tq 2.6, ROP 150.00, Diff 86.00, Temp 109.40
02/03/2022 | 02:05 | 02:19 | 0.23 | 2838 | 2838 | 0 | INT | 2: BHA 2 | 5A | Circulate - Establish Consistent Mud Weight In/Out Prior to performing FIT
02/03/2022 | 02:19 | 02:42 | 0.38 | 2838 | 2838 | 0 | INT | 2: BHA 2 | 15D | Perform FIT
02/03/2022 | 02:42 | 03:06 | 0.4 | 2838 | 2914 | 76 | INT | 2: BHA 2 | 2K | Rotary Drill f/2838.00 t/2914.00, w/WOB 12.00,Flow 548.00, RPM 35.00, Press 1925.00, Tq 2.40, ROP 190.00, Diff 75.00, Temp 109.40
02/03/2022 | 03:06 | 03:10 | 0.07 | 2914 | 2914 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 03:10 | 03:31 | 0.35 | 2914 | 3008 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/2914.00 t/3008.00, w/WOB 7.93,Flow 720.00, RPM 65, Press 3113, Tq 3.59, ROP 268.57, Diff 288.00, Temp 109.40
02/03/2022 | 03:31 | 03:36 | 0.08 | 3008 | 3008 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 03:36 | 03:39 | 0.05 | 3008 | 3018 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3008.00 t/3018.00, w/WOB 7.93,Flow 807, RPM 75, Press 3850, Tq 4.6, ROP 200.00, Diff 230.00, Temp 122.00
02/03/2022 | 03:39 | 03:44 | 0.08 | 3018 | 3030 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3018.00 t/3030.00, TF G, w/WOB 11,Flow 807, Press 3850, Tq 4.6, ROP 144.00, Diff 230.00, Temp 122.00
02/03/2022 | 03:44 | 03:58 | 0.23 | 3030 | 3102 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/3030.00 t/3102.00, w/WOB 7.93,Flow 807, RPM 75, Press 3850, Tq 4.6, ROP 308.57, Diff 230.00, Temp 122.00
02/03/2022 | 03:58 | 04:03 | 0.08 | 3102 | 3102 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 04:03 | 04:22 | 0.32 | 3102 | 3196 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3102.00 t/3196.00, w/WOB 7.93,Flow 853.00, RPM 80.00, Press 3850.00, Tq 4.60, ROP 296.84, Diff 200.00, Temp 122.00
02/03/2022 | 04:22 | 04:27 | 0.08 | 3196 | 3196 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 04:27 | 04:39 | 0.2 | 3196 | 3290 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3196.00 t/3290.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 470.00, Diff 250.00, Temp 122.00
02/03/2022 | 04:39 | 04:42 | 0.05 | 3290 | 3290 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 04:42 | 04:45 | 0.05 | 3290 | 3300 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3290.00 t/3300.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 200.00, Diff 250.00, Temp 122.00
02/03/2022 | 04:45 | 04:51 | 0.1 | 3300 | 3315 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3300.00 t/3315.00, TF 60.00G, w/WOB 7.93,Flow 891.00, Press 4320.00, Tq 5.20, ROP 150.00, Diff 250.00, Temp 122.00
02/03/2022 | 04:51 | 05:00 | 0.15 | 3315 | 3384 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/3315.00 t/3384.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 460.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:00 | 05:03 | 0.05 | 3384 | 3384 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 05:03 | 05:06 | 0.05 | 3384 | 3394 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3384.00 t/3394.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 200.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:06 | 05:12 | 0.1 | 3394 | 3409 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3394.00 t/3409.00, TF 120.00G, w/WOB 7.93,Flow 891.00, Press 4320.00, Tq 5.20, ROP 150.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:12 | 05:20 | 0.13 | 3409 | 3479 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/3409.00 t/3479.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 525.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:20 | 05:24 | 0.07 | 3479 | 3479 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 05:24 | 05:27 | 0.05 | 3479 | 3489 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3479.00 t/3489.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 200.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:27 | 05:31 | 0.07 | 3489 | 3501 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3489.00 t/3501.00, TF 150.00G, w/WOB 7.93,Flow 891.00, Press 4320.00, Tq 5.20, ROP 180.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:31 | 05:37 | 0.1 | 3501 | 3572 | 71 | INT | 2: BHA 2 | 2K | Rotary Drill f/3501.00 t/3572.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 710.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:37 | 05:41 | 0.07 | 3572 | 3572 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 05:41 | 05:49 | 0.13 | 3572 | 3667 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/3572.00 t/3667.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 712.50, Diff 250.00, Temp 122.00
02/03/2022 | 05:49 | 05:53 | 0.07 | 3667 | 3667 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 05:53 | 05:55 | 0.03 | 3667 | 3677 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3667.00 t/3677.00, w/WOB 7.93,Flow 891.00, RPM 80.00, Press 4320.00, Tq 5.20, ROP 300.00, Diff 250.00, Temp 122.00
02/03/2022 | 05:55 | 06:00 | 0.08 | 3677 | 3689 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3677.00 t/3689.00, TF 180.00G, w/WOB 7.93,Flow 891.00, Press 4320.00, Tq 5.20, ROP 144.00, Diff 250.00, Temp 122.00
02/03/2022 | 06:00 | 06:07 | 0.12 | 3689 | 3761 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/3689.00 t/3761.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 617.14, Diff 400.00, Temp 160.00
02/03/2022 | 06:07 | 06:09 | 0.03 | 3761 | 3761 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 06:09 | 06:17 | 0.13 | 3761 | 3855 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3761.00 t/3855.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 705.00, Diff 400.00, Temp 160.00
02/03/2022 | 06:17 | 06:20 | 0.05 | 3855 | 3855 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 06:20 | 06:22 | 0.03 | 3855 | 3867 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/3855.00 t/3867.00, w/WOB 20.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 360.00, Diff 400.00, Temp 160.00
02/03/2022 | 06:22 | 06:27 | 0.08 | 3867 | 3879 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3867.00 t/3879.00, TF 180.00G, w/WOB 5.00,Flow 891.00, Press 4500.00, Tq 0.00, ROP 144.00, Diff 200.00, Temp 160.00
02/03/2022 | 06:27 | 06:32 | 0.08 | 3879 | 3949 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/3879.00 t/3949.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 840.00, Diff 400.00, Temp 160.00
02/03/2022 | 06:32 | 06:35 | 0.05 | 3949 | 3949 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 06:35 | 06:38 | 0.05 | 3949 | 3961 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/3949.00 t/3961.00, w/WOB 20.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 240.00, Diff 400.00, Temp 160.00
02/03/2022 | 06:38 | 06:42 | 0.07 | 3961 | 3973 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3961.00 t/3973.00, TF 180.00G, w/WOB 8.00,Flow 891.00, Press 4500.00, Tq 0.00, ROP 180.00, Diff 200.00, Temp 160.00
02/03/2022 | 06:42 | 06:48 | 0.1 | 3973 | 4043 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/3973.00 t/4043.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 700.00, Diff 400.00, Temp 160.00
02/03/2022 | 06:48 | 06:50 | 0.03 | 4043 | 4043 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 06:50 | 06:53 | 0.05 | 4043 | 4055 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/4043.00 t/4055.00, w/WOB 20.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 240.00, Diff 400.00, Temp 160.00
02/03/2022 | 06:53 | 06:57 | 0.07 | 4055 | 4067 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/4055.00 t/4067.00, TF 180.00G, w/WOB 8.00,Flow 891.00, Press 4500.00, Tq 0.00, ROP 180.00, Diff 200.00, Temp 160.00
02/03/2022 | 06:57 | 07:02 | 0.08 | 4067 | 4137 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/4067.00 t/4137.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 840.00, Diff 400.00, Temp 160.00
02/03/2022 | 07:02 | 07:04 | 0.03 | 4137 | 4137 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 07:04 | 07:10 | 0.1 | 4137 | 4230 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4137.00 t/4230.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 930.00, Diff 400.00, Temp 160.00
02/03/2022 | 07:10 | 07:14 | 0.07 | 4230 | 4230 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 07:14 | 07:17 | 0.05 | 4230 | 4242 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/4230.00 t/4242.00, w/WOB 15.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 240.00, Diff 400.00, Temp 160.00
02/03/2022 | 07:17 | 07:22 | 0.08 | 4242 | 4257 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4242.00 t/4257.00, TF 150.00G, w/WOB 10.00,Flow 891.00, Press 4400.00, Tq 0.00, ROP 180.00, Diff 100.00, Temp 160.00
02/03/2022 | 07:22 | 07:27 | 0.08 | 4257 | 4323 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/4257.00 t/4323.00, w/WOB 38.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 792.00, Diff 400.00, Temp 160.00
02/03/2022 | 07:27 | 07:29 | 0.03 | 4323 | 4323 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 07:29 | 07:32 | 0.05 | 4323 | 4335 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/4323.00 t/4335.00, w/WOB 15.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 240.00, Diff 400.00, Temp 160.00
02/03/2022 | 07:32 | 07:38 | 0.1 | 4335 | 4350 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4335.00 t/4350.00, TF 230.00M, w/WOB 12.00,Flow 891.00, Press 4500.00, Tq 0.00, ROP 150.00, Diff 200.00, Temp 160.00
02/03/2022 | 07:38 | 07:43 | 0.08 | 4350 | 4418 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/4350.00 t/4418.00, w/WOB 40.00,Flow 891.00, RPM 80.00, Press 4700.00, Tq 9.80, ROP 816.00, Diff 400.00, Temp 160.00
02/03/2022 | 07:43 | 07:46 | 0.05 | 4418 | 4418 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 07:46 | 07:53 | 0.12 | 4418 | 4511 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4418.00 t/4511.00, w/WOB 4.00,Flow 891.00, RPM 80.13, Press 4700.00, Tq 5.25, ROP 797.14, Diff 288.68, Temp 160.00
02/03/2022 | 07:53 | 07:56 | 0.05 | 4511 | 4511 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 07:56 | 07:59 | 0.05 | 4511 | 4525 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/4511.00 t/4525.00, w/WOB 25.00,Flow 891.00, RPM 80.13, Press 4700.00, Tq 5.25, ROP 280.00, Diff 288.68, Temp 160.00
02/03/2022 | 07:59 | 08:04 | 0.08 | 4525 | 4540 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4525.00 t/4540.00, TF 255.73M, w/WOB 2.00,Flow 891.00, Press 4700.00, Tq 0, ROP 180.00, Diff 180.57, Temp 160.00
02/03/2022 | 08:04 | 08:10 | 0.1 | 4540 | 4605 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/4540.00 t/4605.00, w/WOB 38.00,Flow 889.29, RPM 79.41, Press 4518.11, Tq 5.92, ROP 650.00, Diff 289.49, Temp 160.00
02/03/2022 | 08:10 | 08:12 | 0.03 | 4605 | 4605 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 08:12 | 08:21 | 0.15 | 4605 | 4699 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4605.00 t/4699.00, w/WOB 38.00,Flow 892.90, RPM 79.95, Press 4456.23, Tq 2.81, ROP 626.67, Diff 227.61, Temp 152.60
02/03/2022 | 08:21 | 08:25 | 0.07 | 4699 | 4699 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 08:25 | 08:34 | 0.15 | 4699 | 4793 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4699.00 t/4793.00, w/WOB 38,Flow 892.66, RPM 80.14, Press 4836, Tq 3.89, ROP 626.67, Diff 607.38, Temp 152.60
02/03/2022 | 08:34 | 08:37 | 0.05 | 4793 | 4793 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 08:37 | 08:45 | 0.13 | 4793 | 4886 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4793.00 t/4886.00, w/WOB 27.61,Flow 890.63, RPM 80.15, Press 4867.99, Tq 9.34, ROP 697.50, Diff 560.33, Temp 159.80
02/03/2022 | 08:45 | 08:48 | 0.05 | 4886 | 4886 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 08:48 | 08:58 | 0.17 | 4886 | 4980 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4886.00 t/4980.00, w/WOB 25.11,Flow 890.91, RPM 80.16, Press 4782.77, Tq 7.86, ROP 564.00, Diff 277.85, Temp 161.60
02/03/2022 | 08:58 | 09:01 | 0.05 | 4980 | 4980 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 09:01 | 09:10 | 0.15 | 4980 | 5074 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4980.00 t/5074.00, w/WOB 25.93,Flow 890.87, RPM 80.20, Press 4817.63, Tq 8.57, ROP 626.67, Diff 312.71, Temp 163.40
02/03/2022 | 09:10 | 09:13 | 0.05 | 5074 | 5074 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 09:13 | 09:22 | 0.15 | 5074 | 5169 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5074.00 t/5169.00, w/WOB 37.57,Flow 890.65, RPM 80.02, Press 4817.63, Tq 4.57, ROP 633.33, Diff 312.71, Temp 165.20
02/03/2022 | 09:22 | 09:26 | 0.07 | 5169 | 5169 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 09:26 | 09:36 | 0.17 | 5169 | 5262 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5169.00 t/5262.00, w/WOB 32.20,Flow 891.40, RPM 80.22, Press 4782.77, Tq 5.53, ROP 558.00, Diff 475.11, Temp 167.00
02/03/2022 | 09:36 | 09:39 | 0.05 | 5262 | 5262 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 09:39 | 09:48 | 0.15 | 5262 | 5356 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5262.00 t/5356.00, w/WOB 33.21,Flow 891.31, RPM 80.22, Press 4814.21, Tq 9.93, ROP 626.67, Diff 485.61, Temp 168.80
02/03/2022 | 09:48 | 09:58 | 0.17 | 5356 | 5356 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 09:58 | 10:10 | 0.2 | 5356 | 5449 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5356.00 t/5449.00, w/WOB 33.68,Flow 891.29, RPM 80.17, Press 4886.94, Tq 7.04, ROP 465.00, Diff 542.72, Temp 172.40
02/03/2022 | 10:10 | 10:14 | 0.07 | 5449 | 5449 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 10:14 | 10:24 | 0.17 | 5449 | 5542 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5449.00 t/5542.00, w/WOB 33.01,Flow 891.29, RPM 80.22, Press 4922.69, Tq 8.35, ROP 558.00, Diff 375.57, Temp 174.20
02/03/2022 | 10:24 | 10:27 | 0.05 | 5542 | 5542 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 10:27 | 10:38 | 0.18 | 5542 | 5636 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5542.00 t/5636.00, w/WOB 35.54,Flow 891.29, RPM 80.25, Press 5110.86, Tq 9.77, ROP 512.73, Diff 594.83, Temp 176.00
02/03/2022 | 10:38 | 10:41 | 0.05 | 5636 | 5636 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 10:41 | 10:50 | 0.15 | 5636 | 5730 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5636.00 t/5730.00, w/WOB 36.50,Flow 891.29, RPM 80.26, Press 5210.86, Tq 8.17, ROP 626.67, Diff 694.83, Temp 177.80
02/03/2022 | 10:50 | 10:54 | 0.07 | 5730 | 5730 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 10:54 | 11:03 | 0.15 | 5730 | 5823 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5730.00 t/5823.00, w/WOB 33.65,Flow 891.29, RPM 80.29, Press 5203.45, Tq 9.44, ROP 620.00, Diff 687.42, Temp 177.80
02/03/2022 | 11:03 | 11:07 | 0.07 | 5823 | 5823 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 11:07 | 11:17 | 0.17 | 5823 | 5916 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5823.00 t/5916.00, w/WOB 34.77,Flow 891.29, RPM 80.25, Press 5106.28, Tq 10.06, ROP 558.00, Diff 534.25, Temp 179.60
02/03/2022 | 11:17 | 11:21 | 0.07 | 5916 | 5916 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 11:21 | 11:31 | 0.17 | 5916 | 6010 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5916.00 t/6010.00, w/WOB 35.64,Flow 891.29, RPM 80.25, Press 5242.24, Tq 11.87, ROP 564.00, Diff 670.21, Temp 181.40
02/03/2022 | 11:31 | 11:33 | 0.03 | 6010 | 6010 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 11:33 | 11:44 | 0.18 | 6010 | 6103 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6010.00 t/6103.00, w/WOB 28.46,Flow 890.76, RPM 80.32, Press 5178.55, Tq 10.43, ROP 507.27, Diff 521.98, Temp 183.20
02/03/2022 | 11:44 | 11:47 | 0.05 | 6103 | 6103 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 11:47 | 11:57 | 0.17 | 6103 | 6197 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6103.00 t/6197.00, w/WOB 31.82,Flow 890.14, RPM 80.28, Press 5175.20, Tq 10.72, ROP 564.00, Diff 428.84, Temp 185.00
02/03/2022 | 11:57 | 12:00 | 0.05 | 6197 | 6197 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 12:00 | 12:03 | 0.05 | 6197 | 6209 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6197.00 t/6209.00, w/WOB 31.82,Flow 890.78, RPM 80.26, Press 4802.66, Tq 9.05, ROP 240.00, Diff 31.22, Temp 179.60
02/03/2022 | 12:03 | 12:15 | 0.2 | 6209 | 6224 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6209.00 t/6224.00, TF 199.06M, w/WOB 31.82,Flow 891.08, Press 4781.38, Tq 0.00, ROP 75.00, Diff 39.49, Temp 179.60
02/03/2022 | 12:15 | 12:23 | 0.13 | 6224 | 6291 | 67 | INT | 2: BHA 2 | 2K | Rotary Drill f/6224.00 t/6291.00, w/WOB 31.82,Flow 890.43, RPM 80.24, Press 5011.84, Tq 10.13, ROP 502.50, Diff 410.97, Temp 179.60
02/03/2022 | 12:23 | 12:26 | 0.05 | 6291 | 6291 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 12:26 | 12:29 | 0.05 | 6291 | 6305 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/6291.00 t/6305.00, w/WOB 31.82,Flow 891.14, RPM 80.29, Press 4803.32, Tq 8.95, ROP 280.00, Diff 44.47, Temp 176.00
02/03/2022 | 12:29 | 12:38 | 0.15 | 6305 | 6320 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6305.00 t/6320.00, TF 105.62M, w/WOB 31.82,Flow 890.61, Press 4803.32, Tq 0.00, ROP 100.00, Diff 56.88, Temp 176.00
02/03/2022 | 12:38 | 12:47 | 0.15 | 6320 | 6385 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/6320.00 t/6385.00, w/WOB 31.82,Flow 890.35, RPM 80.37, Press 5092.67, Tq 11.49, ROP 433.33, Diff 491.80, Temp 176.00
02/03/2022 | 12:47 | 12:50 | 0.05 | 6385 | 6385 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 12:50 | 13:01 | 0.18 | 6385 | 6479 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6385.00 t/6479.00, w/WOB 40.00,Flow 890.98, RPM 80.10, Press 4644.08, Tq 9.08, ROP 512.73, Diff 43.21, Temp 176.00
02/03/2022 | 13:01 | 13:04 | 0.05 | 6479 | 6479 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 13:04 | 13:15 | 0.18 | 6479 | 6573 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6479.00 t/6573.00, w/WOB 40.00,Flow 890.08, RPM 80.33, Press 5314.60, Tq 14.20, ROP 512.73, Diff 713.73, Temp 186.80
02/03/2022 | 13:15 | 13:18 | 0.05 | 6573 | 6573 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 13:18 | 13:28 | 0.17 | 6573 | 6666 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6573.00 t/6666.00, w/WOB 40.00,Flow 890.22, RPM 80.24, Press 5136.77, Tq 14.20, ROP 558.00, Diff 436.77, Temp 188.60
02/03/2022 | 13:28 | 13:31 | 0.05 | 6666 | 6666 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 13:31 | 13:43 | 0.2 | 6666 | 6760 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6666.00 t/6760.00, w/WOB 40.00,Flow 889.95, RPM 80.34, Press 5137.75, Tq 11.36, ROP 470.00, Diff 437.75, Temp 194.00
02/03/2022 | 13:43 | 13:45 | 0.03 | 6760 | 6760 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 13:45 | 13:57 | 0.2 | 6760 | 6854 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6760.00 t/6854.00, w/WOB 40.00,Flow 889.95, RPM 80.34, Press 5100.00, Tq 15.00, ROP 470.00, Diff 400.00, Temp 194.00
02/03/2022 | 13:57 | 14:00 | 0.05 | 6854 | 6854 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 14:00 | 14:03 | 0.05 | 6854 | 6866 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6854.00 t/6866.00, w/WOB 25.00,Flow 889.95, RPM 80.34, Press 5100.00, Tq 15.00, ROP 240.00, Diff 400.00, Temp 194.00
02/03/2022 | 14:03 | 14:19 | 0.27 | 6866 | 6884 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/6866.00 t/6884.00, TF 140.00M, w/WOB 15.00,Flow 889.95, Press 4900.00, Tq 0.00, ROP 67.50, Diff 200.00, Temp 194.00
02/03/2022 | 14:19 | 14:27 | 0.13 | 6884 | 6948 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/6884.00 t/6948.00, w/WOB 40.00,Flow 889.95, RPM 80.34, Press 5300.00, Tq 15.00, ROP 480.00, Diff 600.00, Temp 194.00
02/03/2022 | 14:27 | 14:30 | 0.05 | 6948 | 6948 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 14:30 | 14:33 | 0.05 | 6948 | 6960 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6948.00 t/6960.00, w/WOB 25.00,Flow 889.95, RPM 80.34, Press 5300.00, Tq 15.00, ROP 240.00, Diff 600.00, Temp 194.00
02/03/2022 | 14:33 | 14:42 | 0.15 | 6960 | 6975 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6960.00 t/6975.00, TF 150.00M, w/WOB 15.00,Flow 889.95, Press 5100.00, Tq 0.00, ROP 100.00, Diff 400.00, Temp 194.00
02/03/2022 | 14:42 | 14:51 | 0.15 | 6975 | 7042 | 67 | INT | 2: BHA 2 | 2K | Rotary Drill f/6975.00 t/7042.00, w/WOB 40.00,Flow 889.95, RPM 80.34, Press 5300.00, Tq 15.00, ROP 446.67, Diff 600.00, Temp 194.00
02/03/2022 | 14:51 | 14:54 | 0.05 | 7042 | 7042 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 14:54 | 15:05 | 0.18 | 7042 | 7136 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7042.00 t/7136.00, w/WOB 42.00,Flow 890.00, RPM 80.34, Press 5450.00, Tq 18.90, ROP 512.73, Diff 650.00, Temp 194.00
02/03/2022 | 15:05 | 15:07 | 0.03 | 7136 | 7136 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 15:07 | 15:20 | 0.22 | 7136 | 7230 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7136.00 t/7230.00, w/WOB 42.00,Flow 890.00, RPM 80.34, Press 5450.00, Tq 18.90, ROP 433.85, Diff 650.00, Temp 194.00
02/03/2022 | 15:20 | 15:23 | 0.05 | 7230 | 7230 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 15:23 | 15:34 | 0.18 | 7230 | 7324 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7230.00 t/7324.00, w/WOB 42.00,Flow 890.00, RPM 80.34, Press 5450.00, Tq 18.90, ROP 512.73, Diff 650.00, Temp 198.00
02/03/2022 | 15:34 | 15:37 | 0.05 | 7324 | 7324 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 15:37 | 15:49 | 0.2 | 7324 | 7417 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7324.00 t/7417.00, w/WOB 38.00,Flow 890.00, RPM 80.34, Press 5550.00, Tq 18.40, ROP 465.00, Diff 750.00, Temp 201.00
02/03/2022 | 15:49 | 15:52 | 0.05 | 7417 | 7417 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 15:52 | 16:05 | 0.22 | 7417 | 7511 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7417.00 t/7511.00, w/WOB 38.00,Flow 890.00, RPM 80.34, Press 5600, Tq 19.2, ROP 433.85, Diff 800.00, Temp 203.00
02/03/2022 | 16:05 | 16:09 | 0.07 | 7511 | 7511 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 16:09 | 16:22 | 0.22 | 7511 | 7605 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7511.00 t/7605.00, w/WOB 38.00,Flow 890.00, RPM 80.34, Press 5550, Tq 18, ROP 433.85, Diff 650.00, Temp 207.00
02/03/2022 | 16:22 | 16:25 | 0.05 | 7605 | 7605 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 16:25 | 16:28 | 0.05 | 7605 | 7617 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/7605.00 t/7617.00, w/WOB 20,Flow 890.00, RPM 80.34, Press 5550, Tq 18, ROP 240.00, Diff 650.00, Temp 207.00
02/03/2022 | 16:28 | 16:41 | 0.22 | 7617 | 7637 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7617.00 t/7637.00, TF M, w/WOB 15,Flow 890.00, Press 5200, Tq 0, ROP 92.31, Diff 300.00, Temp 207.00
02/03/2022 | 16:41 | 16:50 | 0.15 | 7637 | 7699 | 62 | INT | 2: BHA 2 | 2K | Rotary Drill f/7637.00 t/7699.00, w/WOB 38.00,Flow 890.00, RPM 80.34, Press 5550, Tq 18, ROP 413.33, Diff 650.00, Temp 207.00
02/03/2022 | 16:50 | 17:19 | 0.48 | 7699 | 7699 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 17:19 | 17:32 | 0.22 | 7699 | 7793 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7699.00 t/7793.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5550.00, Tq 20.00, ROP 433.85, Diff 650.00, Temp 207.00
02/03/2022 | 17:32 | 17:35 | 0.05 | 7793 | 7793 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 17:35 | 17:38 | 0.05 | 7793 | 7808 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/7793.00 t/7808.00, w/WOB 20.00,Flow 890.00, RPM 80.34, Press 5550.00, Tq 20.00, ROP 300.00, Diff 650.00, Temp 207.00
02/03/2022 | 17:38 | 17:53 | 0.25 | 7808 | 7828 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7808.00 t/7828.00, TF 180.00M, w/WOB 15.00,Flow 890.00, Press 5100.00, Tq 0.00, ROP 80.00, Diff 200.00, Temp 207.00
02/03/2022 | 17:53 | 18:03 | 0.17 | 7828 | 7887 | 59 | INT | 2: BHA 2 | 2K | Rotary Drill f/7828.00 t/7887.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5550.00, Tq 20.00, ROP 354.00, Diff 650.00, Temp 207.00
02/03/2022 | 18:03 | 18:07 | 0.07 | 7887 | 7887 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 18:07 | 18:21 | 0.23 | 7887 | 7981 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7887.00 t/7981.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5550.00, Tq 20.00, ROP 402.86, Diff 650.00, Temp 207.00
02/03/2022 | 18:21 | 18:25 | 0.07 | 7981 | 7981 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 18:25 | 18:28 | 0.05 | 7981 | 7991 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7981.00 t/7991.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5550.00, Tq 20.00, ROP 200.00, Diff 650.00, Temp 207.00
02/03/2022 | 18:28 | 18:52 | 0.4 | 7991 | 8016 | 25 | INT | 2: BHA 2 | 2J | Slide Drill f/7991.00 t/8016.00, TF 120.00M, w/WOB 40.00,Flow 890.00, Press 5550.00, Tq 20.00, ROP 62.50, Diff 650.00, Temp 207.00
02/03/2022 | 18:52 | 19:04 | 0.2 | 8016 | 8075 | 59 | INT | 2: BHA 2 | 2K | Rotary Drill f/8016.00 t/8075.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 295.00, Diff 508.00, Temp 207.00
02/03/2022 | 19:04 | 19:07 | 0.05 | 8075 | 8075 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 19:07 | 19:23 | 0.27 | 8075 | 8169 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8075.00 t/8169.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 352.50, Diff 508.00, Temp 207.00
02/03/2022 | 19:23 | 19:27 | 0.07 | 8169 | 8169 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 19:27 | 19:41 | 0.23 | 8169 | 8262 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8169.00 t/8262.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 398.57, Diff 508.00, Temp 207.00
02/03/2022 | 19:41 | 19:45 | 0.07 | 8262 | 8262 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 19:45 | 19:59 | 0.23 | 8262 | 8357 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8262.00 t/8357.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 407.14, Diff 508.00, Temp 207.00
02/03/2022 | 19:59 | 20:02 | 0.05 | 8357 | 8357 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 20:02 | 20:08 | 0.1 | 8357 | 8390 | 33 | INT | 2: BHA 2 | 2K | Rotary Drill f/8357.00 t/8390.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 330.00, Diff 508.00, Temp 207.00
02/03/2022 | 20:08 | 20:25 | 0.28 | 8390 | 8400 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/8390.00 t/8400.00, TF 225.00M, w/WOB 40.00,Flow 890.00, Press 5458.00, Tq 20.00, ROP 35.29, Diff 508.00, Temp 207.00
02/03/2022 | 20:25 | 20:34 | 0.15 | 8400 | 8450 | 50 | INT | 2: BHA 2 | 2K | Rotary Drill f/8400.00 t/8450.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 333.33, Diff 508.00, Temp 207.00
02/03/2022 | 20:34 | 20:38 | 0.07 | 8450 | 8450 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 20:38 | 20:39 | 0.02 | 8450 | 8455 | 5 | INT | 2: BHA 2 | 2K | Rotary Drill f/8450.00 t/8455.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 300.00, Diff 508.00, Temp 207.00
02/03/2022 | 20:39 | 21:07 | 0.47 | 8455 | 8472 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/8455.00 t/8472.00, TF 100.00M, w/WOB 40.00,Flow 890.00, Press 5458.00, Tq 20.00, ROP 36.43, Diff 508.00, Temp 207.00
02/03/2022 | 21:07 | 21:23 | 0.27 | 8472 | 8544 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/8472.00 t/8544.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 270.00, Diff 508.00, Temp 207.00
02/03/2022 | 21:23 | 21:26 | 0.05 | 8544 | 8544 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 21:26 | 21:28 | 0.03 | 8544 | 8550 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/8544.00 t/8550.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 180.00, Diff 508.00, Temp 207.00
02/03/2022 | 21:28 | 22:01 | 0.55 | 8550 | 8575 | 25 | INT | 2: BHA 2 | 2J | Slide Drill f/8550.00 t/8575.00, TF 100.00M, w/WOB 40.00,Flow 890.00, Press 5458.00, Tq 20.00, ROP 45.45, Diff 508.00, Temp 207.00
02/03/2022 | 22:01 | 22:13 | 0.2 | 8575 | 8638 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/8575.00 t/8638.00, w/WOB 40.00,Flow 890.00, RPM 80.34, Press 5458.00, Tq 20.00, ROP 315.00, Diff 508.00, Temp 207.00
02/03/2022 | 22:13 | 22:18 | 0.08 | 8638 | 8638 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 22:18 | 22:33 | 0.25 | 8638 | 8731 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8638.00 t/8731.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5503.00, Tq 15.10, ROP 372.00, Diff 753.00, Temp 213.80
02/03/2022 | 22:33 | 22:37 | 0.07 | 8731 | 8731 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 22:37 | 22:50 | 0.22 | 8731 | 8825 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8731.00 t/8825.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5503.00, Tq 15.10, ROP 433.85, Diff 753.00, Temp 213.80
02/03/2022 | 22:50 | 22:55 | 0.08 | 8825 | 8825 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 22:55 | 23:08 | 0.22 | 8825 | 8919 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8825.00 t/8919.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5503.00, Tq 15.10, ROP 433.85, Diff 753.00, Temp 213.80
02/03/2022 | 23:08 | 23:11 | 0.05 | 8919 | 8919 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 23:11 | 23:25 | 0.23 | 8919 | 9012 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8919.00 t/9012.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5503.00, Tq 15.10, ROP 398.57, Diff 753.00, Temp 213.80
02/03/2022 | 23:25 | 23:29 | 0.07 | 9012 | 9012 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 23:29 | 23:42 | 0.22 | 9012 | 9107 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/9012.00 t/9107.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 438.46, Diff 622.00, Temp 213.80
02/03/2022 | 23:42 | 23:46 | 0.07 | 9107 | 9107 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/03/2022 | 23:46 | 24:00 | 0.23 | 9107 | 9201 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9107.00 t/9201.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 402.86, Diff 622.00, Temp 213.80
Well Seeker PRO 2.0.8.0 - Pro Directional

## 2_4_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 02/04/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7400 |  |  | Well Cost($): |  | 49080
|  |  |  | 24hr Summary: |  | Drill intermaediate - Kick Of Curve @ 9735
|  |  |  | 24hr Lookahead: |  | Build Curve - POOH for Casing Ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9201 |  | 2828 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 10
End Depth (Usft): |  | 10230 |  | 10230 |  | OD (in): |  | 10.75 |  | 300: | 17 | YP: | 7
Total Drilled (Usft): |  | 1029 |  | 7402 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 12 | Viscosity: | 44
Slide Drilled (Usft): |  | 354 |  | 681 | [5 empty] | 100: | 8 | Chlorides:
Rotary Drilled (Usft): |  | 675 |  | 6721 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.10 / 6.90
Drlg/Circ Hrs: |  | 9.82 / 2.35 |  | 26.92 / 7.85 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 6.82 |  | 10.67 |  | SN: |  | 59253 |  | 10s Gel: | 4 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 3 |  | 16.25 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 72.00 | Fluid Loss / Mud Type: | 100 / OBM
ROP Rot/Slide (Usft/hr): |  | 225.00 / 51.93 |  | 413.60 / 63.84 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 22 |  | 50 |  | Grade In: |  | New
% Slide: |  | 34.4 |  | 9.2 |  | Grade Out: |  | 1-1-WT-A-X-I-NO-TD
% Rotary: |  | 65.6 |  | 90.8 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.5 |  | 1.5
7/8 5.9 2.0 TS HPW -.012 |  |  |  | 8 | 2 |  |  |  |  | 37.54 |  | 39.04
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 9.99 |  | 49.03
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.96 |  | 52.99
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.25 |  |  |  |  | 29.64 |  | 82.63
Drill Collar (NO HARDBANDING) |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.59 |  | 112.22
Crossover Sub |  |  |  | 7.938 | 3 |  |  |  |  | 3.18 |  | 115.4
6 Jts 6 1/2in DC |  |  |  | 6.5 | 3 |  |  |  |  | 186.19 |  | 301.59
Crossover Sub |  |  |  | 6.688 | 2.812 |  |  |  |  | 3.2 |  | 304.79
11 Jts 5 HWDP |  |  |  | 5 | 3 |  |  |  |  | 334.01 |  | 638.8
22 Stds 5in DP |  |  |  | 5 | 3 |  |  |  |  | 2065.88 |  | 2704.68
Agitator |  |  |  | 6.75 | 2.5 |  |  |  |  | 22.46 |  | 2727.14
2727.14
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR775009 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.15 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9136 | 2.14 | 245.82 | 9098.66 | 172.17 | 437.07 | 0.95 |  | 49.64 | 190.84 | 0.73 |  | 0 | 94
9231 | 1.82 | 258.34 | 9193.61 | 171.14 | 433.98 | 0.56 |  | 132.64 | 189.36 | -0.34 |  | 13.18 | 95
9325 | 0.19 | 334.89 | 9287.59 | 170.98 | 432.45 | 1.9 |  | 174.06 | 188.38 | -1.73 |  | 81.44 | 94
9419 | 0.6 | 73.92 | 9381.59 | 171.26 | 432.85 | 0.7 |  | 115.62 | 188.47 | 0.44 |  | 0 | 94
9512 | 1.11 | 81.6 | 9474.58 | 171.52 | 434.21 | 0.56 |  | 16.52 | 189.26 | 0.55 |  | 0 | 93
9606 | 1.1 | 72.94 | 9568.56 | 171.92 | 435.98 | 0.18 |  | -97.75 | 190.23 | -0.01 |  | 0 | 94
9700 | 0.73 | 43.34 | 9662.55 | 172.62 | 437.25 | 0.63 |  | -142.22 | 190.65 | -0.39 |  | 0 | 94
9794 | 4.42 | 173.02 | 9756.46 | 169.46 | 438.1 | 5.23 |  | 136.23 | 193.48 | 3.93 |  | 0 | 94
9889 | 11.76 | 158.21 | 9850.46 | 156.82 | 442.15 | 7.97 |  | -23.29 | 205.22 | 7.73 |  | -15.59 | 95
9982 | 18.28 | 149.74 | 9940.25 | 135.4 | 453.03 | 7.38 |  | -22.74 | 228 | 7.01 |  | -9.11 | 93
10076 | 22.46 | 141.78 | 10028.37 | 108.54 | 471.58 | 5.33 |  | -37.32 | 260.06 | 4.45 |  | -8.47 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 104.82 | 31.14 | 67.44 | 190 | 792.09 | 4980.05 | 4529.41 | 0 | 254.55 | 238.41 | 215.27 | 15.69 | 0
Run | 275 | 28.27 | 77.41 | 211 | 863.07 | 4900.25 | 4472.58 | 0 | 197.35 | 184.14 | 169.92 | 12.25 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 02/04/2022 |  | 2 |  | 7400 |  | 1 | 7400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 02/04/2022 |  | 3 |  | -400 |  | 1 | -400
Perdiem Per Hand |  |  |  |  | 02/04/2022 |  | 7 |  | 100 |  | 4 | 400
Total | [11 empty] | 7400
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
02/04/2022 | 00:00 | 00:03 | 0.05 | 9201 | 9201 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 00:03 | 00:05 | 0.03 | 9201 | 9206 | 5 | INT | 2: BHA 2 | 2K | Rotary Drill f/9201.00 t/9206.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 150.00, Diff 622.00, Temp 213.80
02/04/2022 | 00:05 | 00:28 | 0.38 | 9206 | 9223 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/9206.00 t/9223.00, TF 90.00M, w/WOB 40.00,Flow 844.00, Press 5602.00, Tq 17.30, ROP 44.35, Diff 622.00, Temp 213.80
02/04/2022 | 00:28 | 00:40 | 0.2 | 9223 | 9296 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/9223.00 t/9296.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 365.00, Diff 622.00, Temp 213.80
02/04/2022 | 00:40 | 00:44 | 0.07 | 9296 | 9296 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 00:44 | 00:45 | 0.02 | 9296 | 9300 | 4 | INT | 2: BHA 2 | 2K | Rotary Drill f/9296.00 t/9300.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 240.00, Diff 622.00, Temp 213.80
02/04/2022 | 00:45 | 01:07 | 0.37 | 9300 | 9320 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9300.00 t/9320.00, TF 100.00M, w/WOB 40.00,Flow 844.00, Press 5602.00, Tq 17.30, ROP 54.55, Diff 622.00, Temp 213.80
02/04/2022 | 01:07 | 01:19 | 0.2 | 9320 | 9390 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/9320.00 t/9390.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 350.00, Diff 622.00, Temp 213.80
02/04/2022 | 01:19 | 01:23 | 0.07 | 9390 | 9390 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 01:23 | 01:41 | 0.3 | 9390 | 9484 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9390.00 t/9484.00, w/WOB 40.00,Flow 844.00, RPM 80.34, Press 5602.00, Tq 17.30, ROP 313.33, Diff 622.00, Temp 213.80
02/04/2022 | 01:41 | 01:46 | 0.08 | 9484 | 9484 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 01:46 | 02:07 | 0.35 | 9484 | 9577 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9484.00 t/9577.00, w/WOB 40.00,Flow 828.00, RPM 80.00, Press 5429.00, Tq 13.70, ROP 265.71, Diff 589.00, Temp 226.40
02/04/2022 | 02:07 | 02:10 | 0.05 | 9577 | 9577 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 02:10 | 02:12 | 0.03 | 9577 | 9583 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/9577.00 t/9583.00, w/WOB 40.00,Flow 828.00, RPM 80.00, Press 5429.00, Tq 13.70, ROP 180.00, Diff 589.00, Temp 226.40
02/04/2022 | 02:12 | 02:55 | 0.72 | 9583 | 9583 | 0 | INT | 2: BHA 2 | 8D | Repair Standpipe Gasket
02/04/2022 | 02:55 | 03:14 | 0.32 | 9583 | 9671 | 88 | INT | 2: BHA 2 | 2K | Rotary Drill f/9583.00 t/9671.00, w/WOB 40.00,Flow 708.00, RPM 80.00, Press 4272.00, Tq 17.30, ROP 277.89, Diff 522.00, Temp 226.40
02/04/2022 | 03:14 | 03:19 | 0.08 | 9671 | 9671 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 03:19 | 03:34 | 0.25 | 9671 | 9735 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/9671.00 t/9735.00, w/WOB 40.00,Flow 708.00, RPM 80.00, Press 4272.00, Tq 17.30, ROP 256.00, Diff 522.00, Temp 226.40
02/04/2022 | 03:34 | 04:00 | 0.43 | 9735 | 9765 | 30 | CRV | 2: BHA 2 | 2J | Slide Drill f/9735.00 t/9765.00, TF M, w/WOB 40.00,Flow 708.00, Press 3985, Tq 17.30, ROP 69.23, Diff 232.00, Temp 224.60
02/04/2022 | 04:00 | 04:22 | 0.37 | 9765 | 9765 | 0 | CRV | 2: BHA 2 | 8D | Repair Standpipe Gasket
02/04/2022 | 04:22 | 04:25 | 0.05 | 9765 | 9765 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 04:25 | 04:37 | 0.2 | 9765 | 9777 | 12 | CRV | 2: BHA 2 | 2J | Slide Drill f/9765.00 t/9777.00, TF M, w/WOB 23,Flow 813, Press 5210, Tq 17.30, ROP 60.00, Diff 483.00, Temp 224.60
02/04/2022 | 04:37 | 05:32 | 0.92 | 9777 | 9777 | 0 | CRV | 2: BHA 2 | 8D | Repair Standpipe Gasket
02/04/2022 | 05:32 | 06:15 | 0.72 | 9777 | 9827 | 50 | CRV | 2: BHA 2 | 2J | Slide Drill f/9777.00 t/9827.00, TF 140.00M, w/WOB 15.00,Flow 813.00, Press 4900.00, Tq 0.00, ROP 69.77, Diff 173.00, Temp 224.60
02/04/2022 | 06:15 | 07:27 | 1.2 | 9827 | 9859 | 32 | CRV | 2: BHA 2 | 2J | Slide Drill f/9827.00 t/9859.00, TF 140.00M, w/WOB 12.00,Flow 704, Press 3750.00, Tq 0.00, ROP 26.67, Diff 150.00, Temp 224.60
02/04/2022 | 07:27 | 07:36 | 0.15 | 9859 | 9859 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 07:36 | 09:44 | 2.13 | 9859 | 9954 | 95 | CRV | 2: BHA 2 | 2J | Slide Drill f/9859.00 t/9954.00, TF G, w/WOB 15,Flow 704, Press 3800, Tq 0.00, ROP 44.53, Diff 200.00, Temp 224.60
02/04/2022 | 09:44 | 09:54 | 0.17 | 9954 | 9954 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 09:54 | 10:05 | 0.18 | 9954 | 9969 | 15 | CRV | 2: BHA 2 | 2K | Rotary Drill f/9954.00 t/9969.00, w/WOB 15.00,Flow 704.00, RPM 50.00, Press 4000.00, Tq 13.50, ROP 81.82, Diff 400.00, Temp 224.60
02/04/2022 | 10:05 | 11:03 | 0.97 | 9969 | 10047 | 78 | CRV | 2: BHA 2 | 2J | Slide Drill f/9969.00 t/10047.00, TF -45.00G, w/WOB 22.00,Flow 800.00, Press 5000.00, Tq 0.00, ROP 80.69, Diff 300.00, Temp 216.00
02/04/2022 | 11:03 | 11:13 | 0.17 | 10047 | 10047 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 11:13 | 11:40 | 0.45 | 10047 | 10141 | 94 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10047.00 t/10141.00, w/WOB 30.00,Flow 800.00, RPM 35.00, Press 5150.00, Tq 14.00, ROP 208.89, Diff 450.00, Temp 221.00
02/04/2022 | 11:40 | 11:47 | 0.12 | 10141 | 10141 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
02/04/2022 | 11:47 | 11:51 | 0.07 | 10141 | 10151 | 10 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10141.00 t/10151.00, w/WOB 30.00,Flow 800.00, RPM 35.00, Press 5150.00, Tq 14.00, ROP 150.00, Diff 450.00, Temp 221.00
02/04/2022 | 11:51 | 12:16 | 0.42 | 10151 | 10171 | 20 | CRV | 2: BHA 2 | 2J | Slide Drill f/10151.00 t/10171.00, TF -60.00G, w/WOB 25.00,Flow 800.00, Press 4900.00, Tq 0.00, ROP 48.00, Diff 200.00, Temp 223.00
02/04/2022 | 12:16 | 12:52 | 0.6 | 10171 | 10230 | 59 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10171.00 t/10230.00, w/WOB 35,Flow 800.00, RPM 35, Press 5100, Tq 14, ROP 98.33, Diff 300.00, Temp 223.00
02/04/2022 | 12:52 | 12:55 | 0.05 | 10230 | 10230 | 0 | CRV | 2: BHA 2 | 5A | Survey
02/04/2022 | 12:55 | 14:10 | 1.25 | 10230 | 10230 | 0 | CRV | 2: BHA 2 | 5A | Circulate @ Int TD
02/04/2022 | 14:10 | 20:40 | 6.5 | 10230 | 10230 | 0 | CRV | 2: BHA 2 | 6B | POOH t/ run casing
02/04/2022 | 20:40 | 22:00 | 1.33 | 10230 | 10230 | 0 | CRV | 2: BHA 2 | 6P | Lay Down Motor & Pull MWD Tool
02/04/2022 | 22:00 | 24:00 | 2 | 10230 | 10230 | 0 | CRV |  | 24B | Stanby for Casing ops and rig skid
Well Seeker PRO 2.0.8.0 - Pro Directional

## 2_5_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 02/05/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4350 |  |  | Well Cost($): |  | 53430
|  |  |  | 24hr Summary: |  | Build Curve - POOH for Casing Ops
|  |  |  | 24hr Lookahead: |  | Standby for Casing Ops
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10230 |  |  |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 10
End Depth (Usft): |  | 10230 |  | 10230 |  | OD (in): |  | 10.75 |  | 300: | 17 | YP: | 7
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45.5 |  | 200: | 12 | Viscosity: | 44
Slide Drilled (Usft): | [9 empty] | 100: | 8 | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: | 4 | % Sand/Solids: | 0.10 / 6.90
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 69/31
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 4 | Weight (ppg): | 8.9
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 72.00 | Fluid Loss / Mud Type: | 100 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma (Standby) |  |  |  |  | 02/05/2022 |  | 4 |  | 4350 |  | 1 | 4350
Perdiem Per Hand |  |  |  |  | 02/05/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 02/05/2022 |  | 3 |  | -400 |  | 1 | -400
Total | [11 empty] | 4350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
02/05/2022 | 00:00 | 24:00 | 24 | 10230 | 10230 | 0 | CRV |  | 24B | Standby for Casing Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_17_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/17/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19000 |  |  | Well Cost($): |  | 72430
|  |  |  | 24hr Summary: |  | P/U BHA and TIH, Drill out shoe
|  |  |  | 24hr Lookahead: |  | Build and Land Curve
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10230 |  | 10230 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 10
End Depth (Usft): |  | 10230 |  | 10230 |  | OD (in): |  | 10.75 |  | 300: | 17 | YP: | 7
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45.5 |  | 200: | 12 | Viscosity: | 44
Slide Drilled (Usft): | [9 empty] | 100: | 8 | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: | 4 | % Sand/Solids: | 0.10 / 6.90
Drlg/Circ Hrs: |  | 0.00 / 1.77 |  | 0.00 / 1.77 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 69/31
Slide Drilling Hrs: | [5 empty] | SN: |  | 13685101 |  | 10s Gel: | 4 | Weight (ppg): | 8.9
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 72.00 | Fluid Loss / Mud Type: | 100 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 9.25 |  | 9.25 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/17/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/17/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/17/2022 |  | 3 |  | -400 |  | 1 | -400
5.5 Premium Motor Stator Reline |  |  |  |  | 03/17/2022 | PPM250003 | 12 |  | 9000 |  | 1 | 9000
Real Time Survey Management |  |  |  |  | 03/17/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/17/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 19000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/17/2022 | 00:00 | 13:00 | 13 | 10230 | 10230 | 0 | CRV2 |  | 24B | Walk Rig and Test
03/17/2022 | 13:00 | 14:45 | 1.75 | 10230 | 10230 | 0 | CRV2 | 3: BHA 3 | 6O | P/U BHA and Test MWD
03/17/2022 | 14:45 | 19:45 | 5 | 10230 | 10230 | 0 | CRV2 | 3: BHA 3 | 6A | TIH
03/17/2022 | 19:45 | 21:52 | 2.12 | 10230 | 10230 | 0 | CRV2 | 3: BHA 3 | 9A | Slip And Cut
03/17/2022 | 21:52 | 23:38 | 1.77 | 10230 | 10230 | 0 | CRV2 | 3: BHA 3 | 5A | Drill Cement and Shoe
03/17/2022 | 23:38 | 24:00 | 0.37 | 10230 | 10230 | 0 | CRV2 | 3: BHA 3 | 15D | FIT
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_18_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/18/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 82430
|  |  |  | 24hr Summary: |  | Drill Lateral - POOH Looking For Wash Out
|  |  |  | 24hr Lookahead: |  | POOH Looking For Wash Out
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10230 |  | 10230 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 10
End Depth (Usft): |  | 12611.38 |  | 12611.38 |  | OD (in): |  | 10.75 |  | 300: | 17 | YP: | 7
Total Drilled (Usft): |  | 2381 |  | 2381 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 12 | Viscosity: | 35
Slide Drilled (Usft): |  | 779 |  | 779 | [5 empty] | 100: | 8 | Chlorides: | 50000
Rotary Drilled (Usft): |  | 1602 |  | 1602 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.10 / 10.00
Drlg/Circ Hrs: |  | 17.33 / 4.18 |  | 17.33 / 5.95 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77/23
Slide Drilling Hrs: |  | 9.65 |  | 9.65 |  | SN: |  | 13685101 |  | 10s Gel: | 4 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  | 7.68 |  | 7.68 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 73.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 208.55 / 80.73 |  | 208.55 / 80.73 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 33.25 |  | Grade In: |  | New
% Slide: |  | 32.71 |  | 32.71 |  | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: |  | 67.29 |  | 67.29 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10165 | 21.85 | 137.34 | 10110.8 | 83 | 493.32 | 2 |  | -112.06 | 293.47 | -0.69 |  | -4.99 | 89
10283 | 23.35 | 138.54 | 10219.74 | 49.33 | 523.68 | 1.33 |  | 17.64 | 338.73 | 1.27 |  | 1.02 | 118
10378 | 31.47 | 143.69 | 10304.01 | 15.17 | 550.88 | 8.9 |  | 18.59 | 382.07 | 8.55 |  | 5.42 | 95
10472 | 40.82 | 141.51 | 10379.84 | -28.75 | 584.61 | 10.04 |  | -8.72 | 436.92 | 9.95 |  | -2.32 | 94
10567 | 49.62 | 129.05 | 10446.82 | -76.03 | 632.22 | 13.1 |  | -49.7 | 504.02 | 9.26 |  | -13.12 | 95
10662 | 58.49 | 123.09 | 10502.57 | -121.05 | 694.41 | 10.62 |  | -30.35 | 579.93 | 9.34 |  | -6.27 | 95
10752 | 61.38 | 132.95 | 10547.73 | -169.01 | 755.59 | 10.01 |  | 73.81 | 657.17 | 3.21 |  | 10.96 | 90
10848 | 65.65 | 135.19 | 10590.54 | -228.78 | 817.29 | 4.91 |  | 25.66 | 743.07 | 4.45 |  | 2.33 | 96
10942 | 69.85 | 136.49 | 10626.13 | -291.19 | 877.87 | 4.65 |  | 16.24 | 830.03 | 4.47 |  | 1.38 | 94
11035 | 76.61 | 136.94 | 10652.94 | -355.97 | 938.88 | 7.28 |  | 3.71 | 918.95 | 7.27 |  | 0.48 | 93
11130 | 85.89 | 136.75 | 10667.38 | -424.4 | 1003.04 | 9.77 |  | -1.18 | 1012.67 | 9.77 |  | -0.2 | 95
11224 | 87.21 | 136.09 | 10673.04 | -492.36 | 1067.72 | 1.57 |  | -26.54 | 1106.44 | 1.4 |  | -0.7 | 94
11319 | 85.78 | 134.58 | 10678.84 | -559.8 | 1134.37 | 2.19 |  | -133.54 | 1201.25 | -1.51 |  | -1.59 | 95
11413 | 86.93 | 135.2 | 10684.82 | -626.01 | 1200.83 | 1.39 |  | 28.3 | 1295.06 | 1.22 |  | 0.66 | 94
11507 | 84.27 | 134.19 | 10692.03 | -691.92 | 1267.44 | 3.03 |  | -159.3 | 1388.77 | -2.83 |  | -1.07 | 94
11602 | 83.96 | 134 | 10701.77 | -757.68 | 1335.31 | 0.38 |  | -148.64 | 1483.27 | -0.33 |  | -0.2 | 95
11696 | 84.05 | 133.98 | 10711.59 | -822.61 | 1402.57 | 0.1 |  | -12.46 | 1576.75 | 0.1 |  | -0.02 | 94
11790 | 86.34 | 133.69 | 10719.46 | -887.47 | 1470.14 | 2.46 |  | -7.2 | 1670.41 | 2.44 |  | -0.31 | 94
11885 | 87.97 | 133.01 | 10724.18 | -952.6 | 1539.13 | 1.86 |  | -22.64 | 1765.26 | 1.72 |  | -0.72 | 95
11981 | 88.55 | 132.3 | 10727.09 | -1017.62 | 1609.7 | 0.95 |  | -50.75 | 1861.17 | 0.6 |  | -0.74 | 96
12075 | 89.75 | 131.88 | 10728.49 | -1080.62 | 1679.45 | 1.35 |  | -19.29 | 1955.07 | 1.28 |  | -0.45 | 94
12171 | 86.4 | 131.26 | 10731.71 | -1144.28 | 1751.22 | 3.55 |  | -169.53 | 2050.87 | -3.49 |  | -0.65 | 96
12262 | 86.82 | 131.02 | 10737.09 | -1204.04 | 1819.63 | 0.53 |  | -29.71 | 2141.56 | 0.46 |  | -0.26 | 91
12354 | 86.97 | 134.33 | 10742.08 | -1266.3 | 1887.16 | 3.6 |  | 87.49 | 2233.36 | 0.16 |  | 3.6 | 92
12450 | 87.11 | 139.17 | 10747.04 | -1336.11 | 1952.83 | 5.04 |  | 88.47 | 2329.13 | 0.15 |  | 5.04 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 137.39 | 20 | 56.1 | 327 | 398.06 | 3810.19 | 3368.56 | 0 | 240 | 200.41 | 170 | 12.48 | 0
Run | 125.2 | 20 | 56.1 | 327 | 398.06 | 3810.19 | 3368.56 | 0 | 240 | 200.41 | 170 | 12.48 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/18/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/18/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/18/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/18/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/18/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/18/2022 | 00:00 | 01:08 | 1.13 | 10230 | 10351 | 121 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10230.00 t/10351.00, TF 0.00G, w/WOB 20.00,Flow 350.00, Press 3250.00, Tq 0.00, ROP 106.76, Diff 400.00, Temp 219.00
03/18/2022 | 01:08 | 01:20 | 0.2 | 10351 | 10351 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 01:20 | 02:10 | 0.83 | 10351 | 10446 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10351.00 t/10446.00, TF 330.00G, w/WOB 20.00,Flow 400.00, Press 3900.00, Tq 0.00, ROP 114.00, Diff 600.00, Temp 215.00
03/18/2022 | 02:10 | 02:19 | 0.15 | 10446 | 10446 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 02:19 | 03:15 | 0.93 | 10446 | 10540 | 94 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10446.00 t/10540.00, TF 315.00G, w/WOB 20.00,Flow 400.00, Press 3850.00, Tq 0.00, ROP 100.71, Diff 550.00, Temp 217.00
03/18/2022 | 03:15 | 03:24 | 0.15 | 10540 | 10540 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 03:24 | 04:15 | 0.85 | 10540 | 10635 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10540.00 t/10635.00, TF G, w/WOB 20.00,Flow 400.00, Press 3850.00, Tq 0.00, ROP 111.76, Diff 550.00, Temp 219.00
03/18/2022 | 04:15 | 04:27 | 0.2 | 10635 | 10635 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 04:27 | 04:42 | 0.25 | 10635 | 10665 | 30 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/10635.00 t/10665.00, w/WOB 10,Flow 400.00, RPM 30, Press 3850.00, Tq 6.8, ROP 120.00, Diff 550.00, Temp 219.00
03/18/2022 | 04:42 | 05:16 | 0.57 | 10665 | 10730 | 65 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10665.00 t/10730.00, TF 30.00G, w/WOB 25.00,Flow 400.00, Press 3850.00, Tq 6.80, ROP 114.71, Diff 550.00, Temp 219.00
03/18/2022 | 05:16 | 05:27 | 0.18 | 10730 | 10730 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 05:27 | 05:46 | 0.32 | 10730 | 10780 | 50 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/10730.00 t/10780.00, w/WOB 10.00,Flow 400.00, RPM 30.00, Press 3850.00, Tq 6.80, ROP 157.89, Diff 550.00, Temp 219.00
03/18/2022 | 05:46 | 06:12 | 0.43 | 10780 | 10820 | 40 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10780.00 t/10820.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 3850.00, Tq 6.80, ROP 92.31, Diff 550.00, Temp 219.00
03/18/2022 | 06:12 | 06:25 | 0.22 | 10820 | 10820 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 06:25 | 06:46 | 0.35 | 10820 | 10880 | 60 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/10820.00 t/10880.00, w/WOB 10.00,Flow 400.00, RPM 30.00, Press 3850.00, Tq 6.80, ROP 171.43, Diff 550.00, Temp 219.00
03/18/2022 | 06:46 | 07:07 | 0.35 | 10880 | 10916 | 36 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10880.00 t/10916.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 3850.00, Tq 6.80, ROP 102.86, Diff 550.00, Temp 219.00
03/18/2022 | 07:07 | 07:17 | 0.17 | 10916 | 10916 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 07:17 | 07:40 | 0.38 | 10916 | 10966 | 50 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/10916.00 t/10966.00, w/WOB 10.00,Flow 400.00, RPM 30.00, Press 3850.00, Tq 6.80, ROP 130.43, Diff 550.00, Temp 221.00
03/18/2022 | 07:40 | 08:04 | 0.4 | 10966 | 11010 | 44 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10966.00 t/11010.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 3850.00, Tq 6.80, ROP 110.00, Diff 550.00, Temp 224.00
03/18/2022 | 08:04 | 08:14 | 0.17 | 11010 | 11010 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 08:14 | 08:34 | 0.33 | 11010 | 11060 | 50 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11010.00 t/11060.00, w/WOB 15.00,Flow 400.00, RPM 30.00, Press 3850.00, Tq 6.80, ROP 150.00, Diff 550.00, Temp 224.00
03/18/2022 | 08:34 | 08:59 | 0.42 | 11060 | 11103 | 43 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11060.00 t/11103.00, TF 330.00G, w/WOB 25.00,Flow 400.00, Press 3850.00, Tq 6.80, ROP 103.20, Diff 550.00, Temp 231.00
03/18/2022 | 08:59 | 09:09 | 0.17 | 11103 | 11103 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 09:09 | 09:30 | 0.35 | 11103 | 11130 | 27 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11103.00 t/11130.00, TF 330.00G, w/WOB 25.00,Flow 417.51, Press 4012.18, Tq 13.77, ROP 77.14, Diff 712.18, Temp 231.00
03/18/2022 | 09:30 | 09:55 | 0.42 | 11130 | 11198 | 68 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11130.00 t/11198.00, w/WOB 25.00,Flow 398.25, RPM 66.11, Press 4068.84, Tq 13.77, ROP 163.20, Diff 944.86, Temp 237.20
03/18/2022 | 09:55 | 10:00 | 0.08 | 11198 | 11198 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 10:00 | 10:28 | 0.47 | 11198 | 11292 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11198.00 t/11292.00, w/WOB 25.00,Flow 398.25, RPM 66.11, Press 4068.84, Tq 13.77, ROP 201.43, Diff 944.86, Temp 237.20
03/18/2022 | 10:28 | 10:33 | 0.08 | 11292 | 11292 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 10:33 | 10:43 | 0.17 | 11292 | 11304 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11292.00 t/11304.00, w/WOB 25.00,Flow 398.06, RPM 49.95, Press 3445.73, Tq 13.77, ROP 72.00, Diff 8.85, Temp 239.00
03/18/2022 | 10:43 | 10:57 | 0.23 | 11304 | 11325 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/11304.00 t/11325.00, TF -153.98G, w/WOB ,Flow 398.21, Press 3617.28, Tq 13.77, ROP 90.00, Diff 136.39, Temp 239.00
03/18/2022 | 10:57 | 11:10 | 0.22 | 11325 | 11387 | 62 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11325.00 t/11387.00, w/WOB ,Flow 398.17, RPM 65.49, Press 4087.76, Tq 13.77, ROP 286.15, Diff 341.79, Temp 239.00
03/18/2022 | 11:10 | 11:16 | 0.1 | 11387 | 11387 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 11:16 | 11:37 | 0.35 | 11387 | 11482 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11387.00 t/11482.00, w/WOB ,Flow 398.19, RPM 65.69, Press 4148.93, Tq 13.77, ROP 271.43, Diff 970.64, Temp 242.60
03/18/2022 | 11:37 | 11:43 | 0.1 | 11482 | 11482 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 11:43 | 11:49 | 0.1 | 11482 | 11487 | 5 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11482.00 t/11487.00, w/WOB ,Flow 398.13, RPM 49.95, Press 3461.07, Tq 13.77, ROP 50.00, Diff 3.91, Temp 244.40
03/18/2022 | 11:49 | 12:02 | 0.22 | 11487 | 11508 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/11487.00 t/11508.00, TF -170.59G, w/WOB ,Flow 398.27, Press 3698.82, Tq 13.77, ROP 96.92, Diff 140.69
03/18/2022 | 12:02 | 12:15 | 0.22 | 11508 | 11574 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11508.00 t/11574.00, w/WOB ,Flow 398.20, RPM 66.48, Press 4181.44, Tq 13.77, ROP 304.62, Diff 479.15, Temp 246.20
03/18/2022 | 12:15 | 12:22 | 0.12 | 11574 | 11574 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 12:22 | 12:42 | 0.33 | 11574 | 11669 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11574.00 t/11669.00, w/WOB ,Flow 398.20, RPM 66.53, Press 4095.74, Tq 13.77, ROP 285.00, Diff 634.38, Temp 253.40
03/18/2022 | 12:42 | 12:49 | 0.12 | 11669 | 11669 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 12:49 | 13:10 | 0.35 | 11669 | 11764 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11669.00 t/11764.00, w/WOB ,Flow 398.18, RPM 65.72, Press 4073.86, Tq 13.77, ROP 271.43, Diff 876.14, Temp 258.80
03/18/2022 | 13:10 | 13:16 | 0.1 | 11764 | 11764 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 13:16 | 13:26 | 0.17 | 11764 | 11775 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11764.00 t/11775.00, w/WOB ,Flow 398.36, RPM 49.78, Press 3511.17, Tq 13.77, ROP 66.00, Diff 39.97, Temp 258.80
03/18/2022 | 13:26 | 13:37 | 0.18 | 11775 | 11791 | 16 | LAT | 3: BHA 3 | 2J | Slide Drill f/11775.00 t/11791.00, TF -39.60G, w/WOB ,Flow 398.27, Press 3805.14, Tq 13.77, ROP 87.27, Diff 225.59, Temp 258.80
03/18/2022 | 13:37 | 13:53 | 0.27 | 11791 | 11859 | 68 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11791.00 t/11859.00, w/WOB ,Flow 398.16, RPM 66.31, Press 4210.43, Tq 13.77, ROP 255.00, Diff 200.80, Temp 258.80
03/18/2022 | 13:53 | 14:00 | 0.12 | 11859 | 11859 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 14:00 | 14:20 | 0.33 | 11859 | 11955 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11859.00 t/11955.00, w/WOB ,Flow 398.17, RPM 67.31, Press 4270.82, Tq 13.77, ROP 288.00, Diff 207.05, Temp 262.40
03/18/2022 | 14:20 | 14:26 | 0.1 | 11955 | 11955 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 14:26 | 14:48 | 0.37 | 11955 | 12051 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11955.00 t/12051.00, w/WOB ,Flow 398.19, RPM 66.99, Press 4180.05, Tq 13.77, ROP 261.82, Diff 500.67, Temp 264.20
03/18/2022 | 14:48 | 14:56 | 0.13 | 12051 | 12051 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 14:56 | 15:17 | 0.35 | 12051 | 12144 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12051.00 t/12144.00, w/WOB ,Flow 398.15, RPM 67.42, Press 4242.25, Tq 13.77, ROP 265.71, Diff 633.18, Temp 267.80
03/18/2022 | 15:17 | 15:23 | 0.1 | 12144 | 12144 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 15:23 | 15:32 | 0.15 | 12144 | 12151 | 7 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12144.00 t/12151.00, w/WOB ,Flow 397.85, RPM 49.96, Press 3626.64, Tq 13.77, ROP 46.67, Diff 65.60, Temp 266.00
03/18/2022 | 15:32 | 15:46 | 0.23 | 12151 | 12173 | 22 | LAT | 3: BHA 3 | 2J | Slide Drill f/12151.00 t/12173.00, TF 159.83G, w/WOB ,Flow 398.41, Press 3702.02, Tq 13.77, ROP 94.29, Diff 72.18, Temp 266.00
03/18/2022 | 15:46 | 15:59 | 0.22 | 12173 | 12238 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12173.00 t/12238.00, w/WOB ,Flow 398.15, RPM 66.27, Press 4149.10, Tq 13.77, ROP 300.00, Diff 309.50, Temp 266.00
03/18/2022 | 15:59 | 16:04 | 0.08 | 12238 | 12238 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 16:04 | 16:24 | 0.33 | 12238 | 12334 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12238.00 t/12334.00, w/WOB ,Flow 398.19, RPM 66.33, Press 4154.87, Tq 13.77, ROP 288.00, Diff 125.51, Temp 269.60
03/18/2022 | 16:24 | 16:31 | 0.12 | 12334 | 12334 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 16:31 | 16:41 | 0.17 | 12334 | 12343 | 9 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12334.00 t/12343.00, w/WOB ,Flow 398.18, RPM 55.18, Press 3598.13, Tq 13.77, ROP 54.00, Diff 15.49, Temp 269.60
03/18/2022 | 16:41 | 16:56 | 0.25 | 12343 | 12366 | 23 | LAT | 3: BHA 3 | 2J | Slide Drill f/12343.00 t/12366.00, TF 132.90G, w/WOB ,Flow 398.06, Press 3748.43, Tq 13.77, ROP 92.00, Diff 91.77, Temp 269.60
03/18/2022 | 16:56 | 17:07 | 0.18 | 12366 | 12426 | 60 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12366.00 t/12426.00, w/WOB ,Flow 398.15, RPM 66.33, Press 4188.39, Tq 13.77, ROP 327.27, Diff 737.73, Temp 267.80
03/18/2022 | 17:07 | 17:40 | 0.55 | 12426 | 12426 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
03/18/2022 | 17:40 | 17:44 | 0.07 | 12426 | 12426 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 17:44 | 18:03 | 0.32 | 12426 | 12522 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12426.00 t/12522.00, w/WOB ,Flow 398.16, RPM 64.26, Press 4106.72, Tq 13.77, ROP 303.16, Diff 934.41, Temp 267.80
03/18/2022 | 18:03 | 18:08 | 0.08 | 12522 | 12522 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/18/2022 | 18:08 | 18:18 | 0.17 | 12522 | 12528 | 6 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12522.00 t/12528.00, w/WOB ,Flow 398.15, RPM 49.92, Press 3050.63, Tq 13.77, ROP 36.00, Diff -108.19, Temp 267.80
03/18/2022 | 18:18 | 20:34 | 2.27 | 12528 | 12544 | 16 | LAT | 3: BHA 3 | 2J | Slide Drill f/12528.00 t/12544.00, TF -147.30G, w/WOB ,Flow 398.00, Press 2421.71, Tq 13.77, ROP 7.06, Diff 662.22, Temp 266.00
03/18/2022 | 20:34 | 20:59 | 0.42 | 12544 | 12611.38 | 67.38 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12544.00 t/12611.38, w/WOB ,Flow 398.19, RPM 66.62, Press 2561.05, Tq 13.77, ROP 161.71, Diff 482.83, Temp 267.80
03/18/2022 | 20:59 | 21:24 | 0.42 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 5A | Circulate
03/18/2022 | 21:24 | 23:20 | 1.93 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 6B | POOH Wet Looking for Wash in DP
03/18/2022 | 23:20 | 24:00 | 0.67 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 5A | Circulate Surface to Surface - Pump Kill Mud Due to Casing PSI Communicating in DP - Bleed Off Casing PSI to Open IBOP
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_19_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/19/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 92430
|  |  |  | 24hr Summary: |  | POOH LookingforWah Out - Found Wash - TIH - Drill Lateral
|  |  |  | 24hr Lookahead: |  | Standby for Rig Repair after Fire on Shakers
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12611.38 |  | 10230 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 9
End Depth (Usft): |  | 13743 |  | 13743 |  | OD (in): |  | 10.75 |  | 300: | 18 | YP: | 9
Total Drilled (Usft): |  | 1132 |  | 3513 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 14 | Viscosity: | 46
Slide Drilled (Usft): |  | 132 |  | 911 | [5 empty] | 100: | 10 | Chlorides: | 59000
Rotary Drilled (Usft): |  | 1000 |  | 2602 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 8.10
Drlg/Circ Hrs: |  | 7.35 / 6.40 |  | 24.68 / 12.35 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73:27
Slide Drilling Hrs: |  | 2.27 |  | 11.92 |  | SN: |  | 13685101 |  | 10s Gel: | 5 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 5.08 |  | 12.77 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 126.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 196.65 / 58.24 |  | 203.81 / 76.45 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 57.25 |  | Grade In: |  | New
% Slide: |  | 11.66 |  | 25.93 |  | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: |  | 88.34 |  | 74.07 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Jim Harrison |  | Marshall Adams |  | Rick Montijo | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12544 | 87.03 | 143.96 | 10751.85 | -1409.62 | 2011.17 | 5.09 |  | 91.08 | 2422.27 | -0.09 |  | 5.1 | 94
12639 | 85.28 | 144.76 | 10758.22 | -1486.65 | 2066.4 | 2.02 |  | 155.51 | 2515.66 | -1.84 |  | 0.84 | 95
12733 | 85.44 | 139.28 | 10765.83 | -1560.47 | 2124.03 | 5.81 |  | -88.55 | 2608.52 | 0.17 |  | -5.83 | 94
12827 | 87.91 | 134 | 10771.28 | -1628.67 | 2188.44 | 6.19 |  | -65.06 | 2702.26 | 2.63 |  | -5.62 | 94
12922 | 85.77 | 131.57 | 10776.52 | -1693.09 | 2258.04 | 3.41 |  | -131.47 | 2797.06 | -2.25 |  | -2.56 | 95
13017 | 86.2 | 131.05 | 10783.17 | -1755.65 | 2329.23 | 0.71 |  | -50.36 | 2891.67 | 0.45 |  | -0.55 | 95
13112 | 86.97 | 130.77 | 10788.83 | -1817.75 | 2400.89 | 0.86 |  | -19.96 | 2986.32 | 0.81 |  | -0.29 | 95
13206 | 86.08 | 130.8 | 10794.53 | -1879.04 | 2471.94 | 0.95 |  | 178.07 | 3079.94 | -0.95 |  | 0.03 | 94
13301 | 85.93 | 130.74 | 10801.15 | -1940.93 | 2543.71 | 0.17 |  | -158.25 | 3174.51 | -0.16 |  | -0.06 | 95
13393 | 86.37 | 131.42 | 10807.32 | -2001.25 | 2612.9 | 0.88 |  | 57.06 | 3266.13 | 0.48 |  | 0.74 | 92
13487 | 86.62 | 130.94 | 10813.07 | -2063.02 | 2683.52 | 0.57 |  | -62.46 | 3359.8 | 0.27 |  | -0.51 | 94
13581 | 86.22 | 132.84 | 10818.94 | -2125.66 | 2753.35 | 2.06 |  | 101.97 | 3453.51 | -0.43 |  | 2.02 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 153.96 | 29.82 | 63.85 | 334 | 397.28 | 4279.56 | 3712.48 | 0 | 252.14 | 198.49 | 162.5 | 12.94 | 0
Run | 142.32 | 25.63 | 59.4 | 330 | 397.75 | 3995.29 | 3504.19 | 0 | 246.2 | 199.65 | 166.76 | 12.67 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/19/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/19/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/19/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/19/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/19/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/19/2022 | 00:00 | 04:00 | 4 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 5A | Circulate Surface to Surface - Pump Kill Mud Due to Casing PSI Communicating in DP - Bleed Off Casing PSI to Open IBOP
03/19/2022 | 04:00 | 11:00 | 7 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 6B | POOH looking for Wash
03/19/2022 | 11:00 | 13:30 | 2.5 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 6A | TIH
03/19/2022 | 13:30 | 14:47 | 1.28 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 5A | Circulate out gas
03/19/2022 | 14:47 | 14:52 | 0.08 | 12611.38 | 12611.38 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 14:52 | 14:56 | 0.07 | 12611.38 | 12615 | 3.62 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12611.38 t/12615.00, w/WOB 20.00,Flow 398.19, RPM 70.00, Press 4200.00, Tq 11.00, ROP 54.30, Diff 700.00, Temp 274.00
03/19/2022 | 14:56 | 15:18 | 0.37 | 12615 | 12640 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/12615.00 t/12640.00, TF -150.00G, w/WOB 40.00,Flow 398.19, Press 4200.00, Tq 11.00, ROP 68.18, Diff 700.00, Temp 271.00
03/19/2022 | 15:18 | 15:31 | 0.22 | 12640 | 12670 | 30 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12640.00 t/12670.00, w/WOB 25,Flow 398.19, RPM 70.00, Press 4200.00, Tq 11.00, ROP 138.46, Diff 700.00, Temp 271.00
03/19/2022 | 15:31 | 15:45 | 0.23 | 12670 | 12685 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12670.00 t/12685.00, TF G, w/WOB 40.00,Flow 398.19, Press 4200.00, Tq 11.00, ROP 64.29, Diff 700.00, Temp 271.00
03/19/2022 | 15:45 | 15:55 | 0.17 | 12685 | 12707 | 22 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12685.00 t/12707.00, w/WOB 25,Flow 398.19, RPM 70.00, Press 4200.00, Tq 11.00, ROP 132.00, Diff 700.00, Temp 271.00
03/19/2022 | 15:55 | 16:00 | 0.08 | 12707 | 12707 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 16:00 | 16:06 | 0.1 | 12707 | 12718 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12707.00 t/12718.00, w/WOB 25,Flow 398.19, RPM 70.00, Press 4200.00, Tq 11.00, ROP 110.00, Diff 700.00, Temp 271.00
03/19/2022 | 16:06 | 16:22 | 0.27 | 12718 | 12733 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12718.00 t/12733.00, TF G, w/WOB 40.00,Flow 398.19, Press 4200.00, Tq 11.00, ROP 56.25, Diff 700.00, Temp 271.00
03/19/2022 | 16:22 | 16:34 | 0.2 | 12733 | 12763 | 30 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12733.00 t/12763.00, w/WOB 25,Flow 398.19, RPM 70.00, Press 4200.00, Tq 11.00, ROP 150.00, Diff 700.00, Temp 271.00
03/19/2022 | 16:34 | 16:51 | 0.28 | 12763 | 12778 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12763.00 t/12778.00, TF G, w/WOB 40.00,Flow 398.19, Press 4200.00, Tq 11.00, ROP 52.94, Diff 700.00, Temp 271.00
03/19/2022 | 16:51 | 16:59 | 0.13 | 12778 | 12800 | 22 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12778.00 t/12800.00, w/WOB 25,Flow 398.19, RPM 70.00, Press 4200.00, Tq 11.00, ROP 165.00, Diff 700.00, Temp 271.00
03/19/2022 | 16:59 | 17:05 | 0.1 | 12800 | 12800 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 17:05 | 17:16 | 0.18 | 12800 | 12812 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12800.00 t/12812.00, w/WOB ,Flow 396.70, RPM 49.96, Press 3735.96, Tq 13.77, ROP 65.45, Diff 29.77, Temp 271.40
03/19/2022 | 17:16 | 17:33 | 0.28 | 12812 | 12831 | 19 | LAT | 3: BHA 3 | 2J | Slide Drill f/12812.00 t/12831.00, TF -91.05G, w/WOB ,Flow 396.81, Press 4036.97, Tq 13.77, ROP 67.06, Diff 210.49, Temp 271.40
03/19/2022 | 17:33 | 17:48 | 0.25 | 12831 | 12895 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12831.00 t/12894.80, w/WOB ,Flow 396.79, RPM 66.47, Press 4480.62, Tq 13.77, ROP 255.20, Temp 273.20
03/19/2022 | 17:48 | 17:55 | 0.12 | 12895 | 12895 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 17:55 | 18:06 | 0.18 | 12895 | 12902 | 7 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12895.00 t/12902.00, w/WOB 25,Flow 396.75, RPM 49.92, Press 3820.84, Tq 13.77, ROP 38.18, Diff -35.16, Temp 275.00
03/19/2022 | 18:06 | 18:29 | 0.38 | 12902 | 12923 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/12902.00 t/12923.00, TF -168.75G, w/WOB 50,Flow 396.64, Press 4155.16, Tq 13.77, ROP 54.78, Diff 336.36, Temp 275.00
03/19/2022 | 18:29 | 18:45 | 0.27 | 12923 | 12990 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12923.00 t/12990.00, w/WOB 25,Flow 396.75, RPM 66.04, Press 4393.36, Tq 13.77, ROP 251.25, Diff -23.00, Temp 275.00
03/19/2022 | 18:45 | 18:52 | 0.12 | 12990 | 12990 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 18:52 | 19:14 | 0.37 | 12990 | 13083 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12990.00 t/13083.00, w/WOB 25,Flow 396.77, RPM 65.76, Press 4513.74, Tq 13.77, ROP 253.64, Diff 860.05, Temp 278.60
03/19/2022 | 19:14 | 19:19 | 0.08 | 13083 | 13083 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 19:19 | 19:42 | 0.38 | 13083 | 13179 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13083.00 t/13179.00, w/WOB 25,Flow 396.75, RPM 65.62, Press 4618.87, Tq 13.77, ROP 250.43, Diff 664.55, Temp 282.20
03/19/2022 | 19:42 | 19:46 | 0.07 | 13179 | 13179 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 19:46 | 19:59 | 0.22 | 13179 | 13192 | 13 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13179.00 t/13192.00, w/WOB 25,Flow 396.84, RPM 49.92, Press 4098.05, Tq 13.77, ROP 60.00, Diff 114.94, Temp 282.20
03/19/2022 | 19:59 | 20:12 | 0.22 | 13192 | 13203 | 11 | LAT | 3: BHA 3 | 2J | Slide Drill f/13192.00 t/13203.00, TF 150.20G, w/WOB 40,Flow 396.97, Press 4253.20, Tq 13.77, ROP 50.77, Diff 353.39, Temp 282.20
03/19/2022 | 20:12 | 20:27 | 0.25 | 13203 | 13272 | 69 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13203.00 t/13272.00, w/WOB 25,Flow 396.79, RPM 66.49, Press 4559.78, Tq 13.77, ROP 276.00, Diff 1163.62, Temp 280.40
03/19/2022 | 20:27 | 20:32 | 0.08 | 13272 | 13272 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 20:32 | 20:54 | 0.37 | 13272 | 13368 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13272.00 t/13368.00, w/WOB 25,Flow 396.76, RPM 64.57, Press 4600.35, Tq 13.77, ROP 261.82, Diff 938.27, Temp 284.00
03/19/2022 | 20:54 | 20:59 | 0.08 | 13368 | 13368 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 20:59 | 21:26 | 0.45 | 13368 | 13461 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13368.00 t/13461.00, w/WOB 25,Flow 396.74, RPM 66.10, Press 4634.29, Tq 13.77, ROP 206.67, Diff 830.48, Temp 278.60
03/19/2022 | 21:26 | 22:11 | 0.75 | 13461 | 13461 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
03/19/2022 | 22:11 | 22:15 | 0.07 | 13461 | 13461 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 22:15 | 22:39 | 0.4 | 13461 | 13555 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13461.00 t/13467.06, w/WOB ,Flow 396.69, RPM 49.90, Press 4035.45, Tq 13.77, ROP 121.20, Temp 275.00
03/19/2022 | 22:39 | 22:43 | 0.07 | 13555 | 13555 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 22:43 | 22:56 | 0.22 | 13555 | 13567 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13555.00 t/13567.00, w/WOB 25,Flow 396.79, RPM 49.91, Press 4042.44, Tq 13.77, ROP 55.38, Diff 63.85, Temp 280.40
03/19/2022 | 22:56 | 23:10 | 0.23 | 13567 | 13578 | 11 | LAT | 3: BHA 3 | 2J | Slide Drill f/13567.00 t/13578.00, TF 120.04G, w/WOB 40,Flow 396.84, Press 4270.89, Tq 13.77, ROP 47.14, Diff 330.07, Temp 280.40
03/19/2022 | 23:10 | 23:27 | 0.28 | 13578 | 13648 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13578.00 t/13648.00, w/WOB 25,Flow 396.76, RPM 64.78, Press 4530.98, Tq 13.77, ROP 247.06, Diff 1026.30, Temp 278.60
03/19/2022 | 23:27 | 23:32 | 0.08 | 13648 | 13648 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/19/2022 | 23:32 | 23:55 | 0.38 | 13648 | 13743 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13648.00 t/13743.00, w/WOB 25,Flow 396.77, RPM 65.96, Press 4566.39, Tq 13.77, ROP 247.83, Diff 628.33, Temp 280.40
03/19/2022 | 23:55 | 24:00 | 0.08 | 13743 | 13743 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_20_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/20/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 102430
|  |  |  | 24hr Summary: |  | Drill Lateral - POOH to Shoe after Fire on Shale Shakers
|  |  |  | 24hr Lookahead: |  | Standby for Repair to Shale Shakers after Fire
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13743 |  | 10230 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 27 | PV: | 9
End Depth (Usft): |  | 14968 |  | 14968 |  | OD (in): |  | 10.75 |  | 300: | 18 | YP: | 9
Total Drilled (Usft): |  | 1225 |  | 4738 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 14 | Viscosity: | 46
Slide Drilled (Usft): |  | 90 |  | 1001 | [5 empty] | 100: | 10 | Chlorides: | 59000
Rotary Drilled (Usft): |  | 1135 |  | 3737 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 8.10
Drlg/Circ Hrs: |  | 8.03 / 2.92 |  | 32.72 / 15.27 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73:27
Slide Drilling Hrs: |  | 2.43 |  | 14.35 |  | SN: |  | 13685101 |  | 10s Gel: | 5 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 5.6 |  | 18.37 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 126.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 202.68 / 36.99 |  | 203.47 / 69.76 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 81.25 |  | Grade In: |  | New
% Slide: |  | 7.35 |  | 21.13 |  | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: |  | 92.65 |  | 78.87 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | A Mejia B Kitzman | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13675 | 85.33 | 132.71 | 10825.87 | -2189.32 | 2822.16 | 0.96 |  | -171.72 | 3547.21 | -0.95 |  | -0.14 | 94
13769 | 87.51 | 134.01 | 10831.73 | -2253.73 | 2890.37 | 2.7 |  | 30.8 | 3641 | 2.32 |  | 1.38 | 94
13863 | 86.92 | 133.18 | 10836.3 | -2318.47 | 2958.36 | 1.08 |  | -125.46 | 3734.87 | -0.63 |  | -0.88 | 94
13957 | 87.84 | 132.92 | 10840.6 | -2382.57 | 3026.98 | 1.02 |  | -15.77 | 3828.74 | 0.98 |  | -0.28 | 94
14051 | 88 | 132.81 | 10844.01 | -2446.48 | 3095.83 | 0.21 |  | -34.49 | 3922.64 | 0.17 |  | -0.12 | 94
14146 | 89.16 | 132.63 | 10846.36 | -2510.9 | 3165.61 | 1.24 |  | -8.82 | 4017.56 | 1.22 |  | -0.19 | 95
14241 | 87.75 | 132.31 | 10848.93 | -2575.02 | 3235.65 | 1.52 |  | -167.22 | 4112.46 | -1.48 |  | -0.34 | 95
14333 | 86.79 | 138.3 | 10853.31 | -2640.32 | 3300.26 | 6.59 |  | 99.25 | 4204.31 | -1.04 |  | 6.51 | 92
14427 | 85.59 | 137.79 | 10859.56 | -2710.07 | 3362.96 | 1.39 |  | -157.04 | 4297.92 | -1.28 |  | -0.54 | 94
14521 | 84.05 | 136.44 | 10868.04 | -2778.66 | 3426.66 | 2.17 |  | -138.94 | 4391.44 | -1.64 |  | -1.44 | 94
14615 | 83.22 | 135.55 | 10878.47 | -2845.85 | 3491.56 | 1.29 |  | -133.23 | 4484.83 | -0.88 |  | -0.95 | 94
14709 | 85.14 | 135.94 | 10888 | -2912.83 | 3556.82 | 2.08 |  | 11.44 | 4578.31 | 2.04 |  | 0.41 | 94
14804 | 86.85 | 135.69 | 10894.63 | -2980.78 | 3622.87 | 1.82 |  | -8.31 | 4673.06 | 1.8 |  | -0.26 | 95
14897 | 88.55 | 134.11 | 10898.36 | -3046.37 | 3688.69 | 2.49 |  | -42.92 | 4765.97 | 1.83 |  | -1.7 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 152.49 | 25 | 49.96 | 320 | 396.75 | 4023.08 | 3026.71 | 0 | 255 | 199.55 | 160 | 13.77 | 0
Run | 137.69 | 25.62 | 59.2 | 330 | 397.74 | 3995.68 | 3497.56 | 0 | 246.32 | 199.65 | 166.67 | 12.7 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/20/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/20/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/20/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/20/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/20/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/20/2022 | 00:00 | 00:12 | 0.2 | 13743 | 13755 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13743.00 t/13755.00, w/WOB 25,Flow 396.75, RPM 49.96, Press 4023.08, Tq 13.77, ROP 60.00, Diff 996.37, Temp 280.40
03/20/2022 | 00:12 | 01:20 | 1.13 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 24A | Fire On Shale Shakers - Shut In Well - Regroup and Consult w/ Patterson and DE about Plan Forward
03/20/2022 | 01:20 | 05:00 | 3.67 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 6B | POOH to Shoe
03/20/2022 | 05:00 | 11:10 | 6.17 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 8M | Repair Shakers
03/20/2022 | 11:10 | 13:15 | 2.08 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 6A | TIH
03/20/2022 | 13:15 | 14:45 | 1.5 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 5A | Circulate
03/20/2022 | 14:45 | 14:46 | 0.02 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 14:46 | 14:56 | 0.17 | 13755 | 13755 | 0 | LAT | 3: BHA 3 | 2J | Slide Drill f/13743.00 t/13755.00, TF G, w/WOB 30,Flow 396.75, Press 4450, Tq 13.77, ROP 72.00, Diff 850.00, Temp 280.40
03/20/2022 | 14:56 | 15:18 | 0.37 | 13755 | 13835 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13755.00 t/13835.00, w/WOB 30,Flow 396.75, RPM 68.80, Press 4492.39, Tq 13.77, ROP 218.18, Diff 1175.05, Temp 280.40
03/20/2022 | 15:18 | 15:24 | 0.1 | 13835 | 13835 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 15:24 | 15:50 | 0.43 | 13835 | 13930 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13835.00 t/13930.00, w/WOB 30,Flow 396.78, RPM 66.80, Press 4516.19, Tq 13.77, ROP 219.23, Diff 155.45, Temp 282.20
03/20/2022 | 15:50 | 15:56 | 0.1 | 13930 | 13930 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 15:56 | 16:20 | 0.4 | 13930 | 14024 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13930.00 t/14024.00, w/WOB 30,Flow 396.78, RPM 67.05, Press 4596.00, Tq 13.77, ROP 235.00, Diff 404.01, Temp 284.00
03/20/2022 | 16:20 | 16:26 | 0.1 | 14024 | 14024 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 16:26 | 16:52 | 0.43 | 14024 | 14119 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14024.00 t/14119.00, w/WOB 30,Flow 396.76, RPM 66.49, Press 4532.63, Tq 13.77, ROP 219.23, Diff 138.41, Temp 285.80
03/20/2022 | 16:52 | 16:57 | 0.08 | 14119 | 14119 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 16:57 | 17:22 | 0.42 | 14119 | 14215 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14119.00 t/14215.00, w/WOB 30,Flow 396.76, RPM 66.76, Press 4511.84, Tq 13.77, ROP 230.40, Diff 124.11, Temp 287.60
03/20/2022 | 17:22 | 17:28 | 0.1 | 14215 | 14215 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 17:28 | 17:38 | 0.17 | 14215 | 14226 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14215.00 t/14226.00, w/WOB 30,Flow 396.68, RPM 49.98, Press 3878.05, Tq 13.77, ROP 66.00, Diff 4.60, Temp 287.60
03/20/2022 | 17:38 | 17:57 | 0.32 | 14226 | 14245 | 19 | LAT | 3: BHA 3 | 2J | Slide Drill f/14226.00 t/14245.00, TF 166.41G, w/WOB 30,Flow 396.71, Press 4150.82, Tq 13.77, ROP 60.00, Diff 275.76, Temp 287.60
03/20/2022 | 17:57 | 18:10 | 0.22 | 14245 | 14310 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14245.00 t/14310.00, w/WOB 30,Flow 396.75, RPM 64.98, Press 4465.89, Tq 13.77, ROP 300.00, Diff 1157.44, Temp 285.80
03/20/2022 | 18:10 | 18:14 | 0.07 | 14310 | 14310 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 18:14 | 18:26 | 0.2 | 14310 | 14320 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14310.00 t/14320.00, w/WOB 30,Flow 396.75, RPM 49.98, Press 3942.98, Tq 13.77, ROP 50.00, Diff 65.55, Temp 285.80
03/20/2022 | 18:26 | 18:41 | 0.25 | 14320 | 14334 | 14 | LAT | 3: BHA 3 | 2J | Slide Drill f/14320.00 t/14334.00, TF 143.75G, w/WOB 30,Flow 396.89, Press 4183.93, Tq 13.77, ROP 56.00, Diff 237.82, Temp 285.80
03/20/2022 | 18:41 | 18:55 | 0.23 | 14334 | 14403 | 69 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14334.00 t/14403.00, w/WOB 30,Flow 396.77, RPM 64.24, Press 4540.88, Tq 13.77, ROP 295.71, Diff 619.65, Temp 285.80
03/20/2022 | 18:55 | 19:00 | 0.08 | 14403 | 14403 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 19:00 | 19:23 | 0.38 | 14403 | 14416 | 13 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14403.00 t/14416.00, w/WOB 30,Flow 396.78, RPM 49.99, Press 4040.09, Tq 13.77, ROP 33.91, Diff 46.57, Temp 287.60
03/20/2022 | 19:23 | 19:49 | 0.43 | 14416 | 14425 | 9 | LAT | 3: BHA 3 | 2J | Slide Drill f/14416.00 t/14425.00, TF -111.37G, w/WOB 30,Flow 396.82, Press 4268.69, Tq 13.77, ROP 20.77, Diff 371.74, Temp 287.60
03/20/2022 | 19:49 | 20:04 | 0.25 | 14425 | 14495 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14425.00 t/14495.00, w/WOB 30,Flow 396.79, RPM 66.30, Press 4562.83, Tq 13.77, ROP 280.00, Diff 604.00, Temp 285.80
03/20/2022 | 20:04 | 20:08 | 0.07 | 14495 | 14495 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 20:08 | 20:12 | 0.07 | 14495 | 14505 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14495.00 t/14505.00, w/WOB 30,Flow 396.77, RPM 62.78, Press 4540.15, Tq 13.77, ROP 150.00, Diff 598.26, Temp 287.60
03/20/2022 | 20:12 | 20:33 | 0.35 | 14505 | 14517 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/14505.00 t/14517.00, TF 0.0G, w/WOB 30,Flow 396.77, Press 4540, Tq 13.77, ROP 34.29, Diff 599.00, Temp 287.60
03/20/2022 | 20:33 | 20:58 | 0.42 | 14517 | 14517 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 20:58 | 21:21 | 0.38 | 14517 | 14683 | 166 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14517.00 t/14683.00, w/WOB 30,Flow 396.77, RPM 65.79, Press 4581.50, Tq 13.77, ROP 433.04, Diff 605.50, Temp 289.40
03/20/2022 | 21:21 | 21:25 | 0.07 | 14683 | 14683 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 21:25 | 21:36 | 0.18 | 14683 | 14693 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14683.00 t/14693.00, w/WOB 30,Flow 396.74, RPM 49.93, Press 3940.33, Tq 13.77, ROP 54.55, Diff -35.99, Temp 289.40
03/20/2022 | 21:36 | 22:05 | 0.48 | 14693 | 14714 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/14693.00 t/14714.00, TF 0.41G, w/WOB 30,Flow 396.69, Press 4226.64, Tq 13.77, ROP 43.45, Diff 292.14, Temp 289.40
03/20/2022 | 22:05 | 22:19 | 0.23 | 14714 | 14777 | 63 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14714.00 t/14777.00, w/WOB 30,Flow 396.74, RPM 66.30, Press 4562.57, Tq 13.77, ROP 270.00, Diff -58.50, Temp 287.60
03/20/2022 | 22:19 | 22:22 | 0.05 | 14777 | 14777 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 22:22 | 22:34 | 0.2 | 14777 | 14787 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14777.00 t/14787.00, w/WOB 30,Flow 396.78, RPM 49.93, Press 3902.14, Tq 13.77, ROP 50.00, Diff -12.01, Temp 289.40
03/20/2022 | 22:34 | 22:45 | 0.18 | 14787 | 14795 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/14787.00 t/14795.00, TF -6.49G, w/WOB 30,Flow 396.73, Press 4270.49, Tq 13.77, ROP 43.64, Diff 336.86, Temp 289.40
03/20/2022 | 22:45 | 23:04 | 0.32 | 14795 | 14870 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14795.00 t/14870.00, w/WOB 30,Flow 396.77, RPM 65.57, Press 4624.10, Tq 13.77, ROP 236.84, Diff 1092.48, Temp 289.40
03/20/2022 | 23:04 | 23:08 | 0.07 | 14870 | 14870 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 23:08 | 23:19 | 0.18 | 14870 | 14882 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14870.00 t/14882.00, w/WOB 30,Flow 396.79, RPM 49.93, Press 3975.37, Tq 13.77, ROP 65.45, Diff -30.67, Temp 289.40
03/20/2022 | 23:19 | 23:34 | 0.25 | 14882 | 14889 | 7 | LAT | 3: BHA 3 | 2J | Slide Drill f/14882.00 t/14889.00, TF -68.07G, w/WOB 30,Flow 396.05, Press 4325.95, Tq 13.77, ROP 28.00, Diff 300.55, Temp 289.40
03/20/2022 | 23:34 | 23:35 | 0.02 | 14889 | 14889 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 23:35 | 23:54 | 0.32 | 14889 | 14965 | 76 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14889.00 t/14965.00, w/WOB 30,Flow 396.76, RPM 66.10, Press 4612.07, Tq 13.77, ROP 240.00, Diff 961.33, Temp 289.40
03/20/2022 | 23:54 | 23:59 | 0.08 | 14965 | 14965 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/20/2022 | 23:59 | 24:00 | 0.02 | 14965 | 14968 | 3 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14965.00 t/14968.00, w/WOB 30,Flow 396.72, RPM 49.87, Press 4325.95, Tq 13.77, ROP 180.00, Diff 575.07, Temp 289.40
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_21_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/21/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 112430
|  |  |  | 24hr Summary: |  | Drill Lateral
|  |  |  | 24hr Lookahead: |  | Drill Lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14968 |  | 10230 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 17044 |  | 17044 |  | OD (in): |  | 10.75 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 2076 |  | 6814 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): |  | 160 |  | 1161 | [5 empty] | 100: | 1 | Chlorides: | 600
Rotary Drilled (Usft): |  | 1916 |  | 5653 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.10 / 0.40
Drlg/Circ Hrs: |  | 15.70 / 7.15 |  | 48.42 / 22.42 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 3.95 |  | 18.3 |  | SN: |  | 13685101 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 11.75 |  | 30.12 |  | Bit # |  | 3 |  | PH / Temp(F) | 7.0 / 67.00 | Mud Type: | Water
ROP Rot/Slide (Usft/hr): |  | 163.06 / 40.51 |  | 187.70 / 63.44 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 105.25 |  | Grade In: |  | New
% Slide: |  | 7.71 |  | 17.04 |  | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: |  | 92.29 |  | 82.96 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | A Mejia B Kitzman | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14992 | 88.16 | 133.16 | 10901.09 | -3111.9 | 3757.42 | 1.08 |  | -112.34 | 4860.92 | -0.41 |  | -1 | 95
15087 | 89.76 | 133.19 | 10902.82 | -3176.89 | 3826.68 | 1.68 |  | 1.07 | 4955.88 | 1.68 |  | 0.03 | 95
15182 | 87.96 | 132.63 | 10904.71 | -3241.55 | 3896.25 | 1.98 |  | -162.73 | 5050.81 | -1.89 |  | -0.59 | 95
15277 | 87.96 | 132.86 | 10908.09 | -3305.99 | 3965.97 | 0.24 |  | 90 | 5145.71 | 0 |  | 0.24 | 95
15371 | 87.97 | 131.71 | 10911.43 | -3369.2 | 4035.46 | 1.22 |  | -89.52 | 5239.57 | 0.01 |  | -1.22 | 94
15466 | 89.08 | 131.9 | 10913.87 | -3432.5 | 4106.25 | 1.19 |  | 9.71 | 5334.43 | 1.17 |  | 0.2 | 95
15561 | 88.13 | 132.84 | 10916.18 | -3496.5 | 4176.42 | 1.41 |  | 135.32 | 5429.34 | -1 |  | 0.99 | 95
15655 | 87.5 | 131.84 | 10919.77 | -3559.77 | 4245.85 | 1.26 |  | -122.25 | 5523.2 | -0.67 |  | -1.06 | 94
15749 | 87.25 | 132.15 | 10924.07 | -3622.59 | 4315.64 | 0.42 |  | 128.92 | 5617.01 | -0.27 |  | 0.33 | 94
15843 | 87.27 | 134.07 | 10928.57 | -3686.76 | 4384.18 | 2.04 |  | 89.45 | 5710.87 | 0.02 |  | 2.04 | 94
15938 | 87.01 | 135.09 | 10933.31 | -3753.35 | 4451.76 | 1.11 |  | 104.34 | 5805.75 | -0.27 |  | 1.07 | 95
16032 | 87 | 135.02 | 10938.22 | -3819.8 | 4518.07 | 0.08 |  | -98.14 | 5899.61 | -0.01 |  | -0.07 | 94
16127 | 87.22 | 135.53 | 10943.01 | -3887.21 | 4584.84 | 0.58 |  | 66.65 | 5994.49 | 0.23 |  | 0.54 | 95
16220 | 87.29 | 137.21 | 10947.46 | -3954.44 | 4648.93 | 1.81 |  | 87.65 | 6087.33 | 0.08 |  | 1.81 | 93
16315 | 86.93 | 136.87 | 10952.25 | -4023.88 | 4713.59 | 0.52 |  | -136.68 | 6182.12 | -0.38 |  | -0.36 | 95
16409 | 87.32 | 136.44 | 10956.97 | -4092.15 | 4778.03 | 0.62 |  | -47.77 | 6275.93 | 0.41 |  | -0.46 | 94
16502 | 87.26 | 139.86 | 10961.37 | -4161.34 | 4840 | 3.67 |  | 91.09 | 6368.63 | -0.06 |  | 3.68 | 93
16597 | 87.15 | 136.62 | 10966 | -4232.11 | 4903.19 | 3.41 |  | -92.03 | 6463.3 | -0.12 |  | -3.41 | 95
16692 | 86 | 133.43 | 10971.68 | -4299.18 | 4970.2 | 3.56 |  | -109.95 | 6558.12 | -1.21 |  | -3.36 | 95
16786 | 86.26 | 132.8 | 10978.02 | -4363.28 | 5038.66 | 0.72 |  | -67.55 | 6651.87 | 0.28 |  | -0.67 | 94
16881 | 88.55 | 132.11 | 10982.32 | -4427.34 | 5108.68 | 2.52 |  | -16.77 | 6746.71 | 2.41 |  | -0.73 | 95
16974 | 84.8 | 132.24 | 10987.71 | -4489.66 | 5177.47 | 4.03 |  | 178.02 | 6839.46 | -4.03 |  | 0.14 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 132.23 | 25 | 49.96 | 320 | 396.75 | 4023.08 | 3026.71 | 0 | 255 | 199.55 | 160 | 13.77 | 0
Run | 140.74 | 25.62 | 59.2 | 330 | 397.74 | 3995.68 | 3497.56 | 0 | 246.32 | 199.65 | 166.67 | 12.7 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/21/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/21/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/21/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/21/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/21/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/21/2022 | 00:00 | 00:25 | 0.42 | 14968 | 15060 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14968.00 t/15060.00, w/WOB 30.00,Flow 396.78, RPM 66.17, Press 4628.18, Tq 13.77, ROP 220.80, Diff 49.49, Temp 291.20
03/21/2022 | 00:25 | 00:29 | 0.07 | 15060 | 15060 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 00:29 | 00:54 | 0.42 | 15060 | 15154 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15060.00 t/15154.00, w/WOB 30.00,Flow 396.77, RPM 66.72, Press 4653.32, Tq 13.77, ROP 225.60, Diff 1222.27, Temp 293.00
03/21/2022 | 00:54 | 00:59 | 0.08 | 15154 | 15154 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 00:59 | 01:13 | 0.23 | 15154 | 15165 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15154.00 t/15165.00, w/WOB 30.00,Flow 396.81, RPM 49.94, Press 4135.89, Tq 13.77, ROP 47.14, Diff 45.94, Temp 293.00
03/21/2022 | 01:13 | 01:40 | 0.45 | 15165 | 15186 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/15165.00 t/15186.00, TF 166.39G, w/WOB 30.00,Flow 396.69, Press 4464.59, Tq 13.77, ROP 46.67, Diff 392.61, Temp 289.40
03/21/2022 | 01:40 | 01:41 | 0.02 | 15186 | 15186 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 01:41 | 01:49 | 0.13 | 15186 | 15217 | 31 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15186.00 t/15217.29, w/WOB 30.00,Flow 396.76, RPM 63.70, Press 4621.49, Tq 13.77, ROP 234.67, Diff 1490.81, Temp 289.40
03/21/2022 | 01:49 | 05:33 | 3.73 | 15217 | 15217 | 0 | LAT | 3: BHA 3 | 5A | Lost Returns - Transfer Kill Mud to Tanks - Pumping Fresh Water - Swap to Mud Cap
03/21/2022 | 05:33 | 05:41 | 0.13 | 15217 | 15249 | 32 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15186.00 t/15249.00, w/WOB 30.00,Flow 401.32, RPM 62.41, Press 3589.64, Tq 13.77, ROP 472.50, Diff -3.10, Temp 251.60
03/21/2022 | 05:41 | 05:46 | 0.08 | 15249 | 15249 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 05:46 | 06:09 | 0.38 | 15249 | 15344 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15249.00 t/15344.00, w/WOB ,Flow 401.28, RPM 66.75, Press 3824.64, Tq 13.77, ROP 247.83, Diff 564.02, Temp 213.80
03/21/2022 | 06:09 | 06:16 | 0.12 | 15344 | 15344 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 06:16 | 06:57 | 0.68 | 15344 | 15439 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15344.00 t/15439.00, w/WOB ,Flow 401.29, RPM 67.58, Press 4191.25, Tq 13.77, ROP 139.02, Diff 376.97, Temp 163.40
03/21/2022 | 06:57 | 07:07 | 0.17 | 15439 | 15439 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 07:07 | 07:48 | 0.68 | 15439 | 15535 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15439.00 t/15535.00, w/WOB ,Flow 448.71, RPM 66.54, Press 4607.46, Tq 13.77, ROP 140.49, Diff 600.01, Temp 145.40
03/21/2022 | 07:48 | 07:56 | 0.13 | 15535 | 15535 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 07:56 | 08:05 | 0.15 | 15535 | 15546 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15535.00 t/15546.00, w/WOB ,Flow 401.31, RPM 49.95, Press 4167.96, Tq 13.77, ROP 73.33, Diff -21.54, Temp 140.00
03/21/2022 | 08:05 | 08:25 | 0.33 | 15546 | 15565 | 19 | LAT | 3: BHA 3 | 2J | Slide Drill f/15546.00 t/15565.00, TF 145.92G, w/WOB ,Flow 401.19, Press 4790.43, Tq 13.77, ROP 57.00, Diff 330.85, Temp 140.00
03/21/2022 | 08:25 | 08:47 | 0.37 | 15565 | 15631 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15565.00 t/15631.00, w/WOB ,Flow 401.28, RPM 65.35, Press 4925.06, Tq 13.77, ROP 180.00, Temp 131.00
03/21/2022 | 08:47 | 08:54 | 0.12 | 15631 | 15631 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 08:54 | 09:29 | 0.58 | 15631 | 15723 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15631.00 t/15723.00, w/WOB ,Flow 401.32, RPM 67.20, Press 5099.39, Tq 13.77, ROP 157.71, Diff 893.49, Temp 140.00
03/21/2022 | 09:29 | 09:35 | 0.1 | 15723 | 15723 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 09:35 | 09:44 | 0.15 | 15723 | 15734 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15723.00 t/15734.00, w/WOB ,Flow 401.32, RPM 49.99, Press 4601.79, Tq 13.77, ROP 73.33, Diff -14.07, Temp 141.80
03/21/2022 | 09:44 | 10:04 | 0.33 | 15734 | 15752 | 18 | LAT | 3: BHA 3 | 2J | Slide Drill f/15734.00 t/15752.00, TF 112.38G, w/WOB ,Flow 401.34, Press 5019.81, Tq 13.77, ROP 54.00, Diff 336.99, Temp 141.80
03/21/2022 | 10:04 | 10:23 | 0.32 | 15752 | 15817 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15752.00 t/15817.00, w/WOB ,Flow 401.33, RPM 65.79, Press 5036.55, Tq 13.77, ROP 205.26, Diff 1609.03, Temp 129.20
03/21/2022 | 10:23 | 10:30 | 0.12 | 15817 | 15817 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 10:30 | 11:13 | 0.72 | 15817 | 15910 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15817.00 t/15910.00, w/WOB ,Flow 401.33, RPM 67.60, Press 5051.15, Tq 13.77, ROP 129.77, Diff 1961.13, Temp 143.60
03/21/2022 | 11:13 | 11:49 | 0.6 | 15910 | 15910 | 0 | LAT | 3: BHA 3 | 5A | Pump Kill Mud
03/21/2022 | 11:49 | 12:01 | 0.2 | 15910 | 15941 | 31 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15910.00 t/15916.65, w/WOB ,Flow 401.43, RPM 49.95, Press 5106.38, Tq 13.77, ROP 99.75, Temp 143.60
03/21/2022 | 12:01 | 12:41 | 0.67 | 15941 | 15941 | 0 | LAT | 3: BHA 3 | 8O | L/D 2 Washed Joints
03/21/2022 | 12:41 | 13:00 | 0.32 | 15941 | 16004 | 63 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15941.00 t/16004.00, w/WOB ,Flow 401.30, RPM 66.55, Press 5558.33, Tq 13.77, ROP 198.95, Diff 519.63, Temp 158.00
03/21/2022 | 13:00 | 13:06 | 0.1 | 16004 | 16004 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 13:06 | 13:20 | 0.23 | 16004 | 16044 | 40 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16004.00 t/16044.00, w/WOB ,Flow 401.33, RPM 63.28, Press 5440.47, Tq 13.77, ROP 171.43, Diff 570.35, Temp 154.40
03/21/2022 | 13:20 | 13:49 | 0.48 | 16044 | 16044 | 0 | LAT | 3: BHA 3 | 8O | L/D Bent Joint
03/21/2022 | 13:49 | 14:06 | 0.28 | 16044 | 16100 | 56 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16044.00 t/16100.00, w/WOB ,Flow 401.32, RPM 66.49, Press 5579.20, Tq 13.77, ROP 197.65, Diff 272.40, Temp 156.20
03/21/2022 | 14:06 | 14:13 | 0.12 | 16100 | 16100 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 14:13 | 14:55 | 0.7 | 16100 | 16195 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16100.00 t/16195.00, w/WOB ,Flow 401.32, RPM 67.44, Press 5748.91, Tq 13.77, ROP 135.71, Diff 932.71, Temp 161.60
03/21/2022 | 14:55 | 15:08 | 0.22 | 16195 | 16195 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 15:08 | 15:35 | 0.45 | 16195 | 16290 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16195.00 t/16290.00, w/WOB ,Flow 401.32, RPM 66.70, Press 5927.63, Tq 13.77, ROP 211.11, Diff 285.69, Temp 161.60
03/21/2022 | 15:35 | 15:42 | 0.12 | 16290 | 16290 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 15:42 | 15:52 | 0.17 | 16290 | 16296 | 6 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16290.00 t/16296.00, w/WOB 30.00,Flow 401.31, RPM 49.98, Press 5280.82, Tq 13.77, ROP 36.00, Diff 86.52, Temp 159.80
03/21/2022 | 15:52 | 16:27 | 0.58 | 16296 | 16317 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/16296.00 t/16317.00, TF -120.62G, w/WOB 50,Flow 401.14, Press 5840.93, Tq 13.77, ROP 36.00, Diff 377.63, Temp 159.80
03/21/2022 | 16:27 | 16:47 | 0.33 | 16317 | 16384 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16317.00 t/16384.00, w/WOB 30,Flow 401.32, RPM 65.18, Press 6031.36, Tq 13.77, ROP 201.00, Diff 1201.11, Temp 150.80
03/21/2022 | 16:47 | 17:31 | 0.73 | 16384 | 16384 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 17:31 | 17:39 | 0.13 | 16384 | 16406 | 22 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16384.00 t/16406.00, w/WOB 30,Flow 401.19, RPM 55.79, Press 5509.31, Tq 13.77, ROP 165.00, Diff 693.11, Temp 150.80
03/21/2022 | 17:39 | 17:40 | 0.02 | 16406 | 16406 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 17:40 | 18:02 | 0.37 | 16406 | 16473 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16406.00 t/16473.00, w/WOB 30,Flow 401.30, RPM 68.95, Press 5251.69, Tq 13.77, ROP 182.73, Diff 1379.62, Temp 152.60
03/21/2022 | 18:02 | 18:07 | 0.08 | 16473 | 16473 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 18:07 | 18:19 | 0.2 | 16473 | 16487 | 14 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16473.00 t/16487.00, w/WOB 30,Flow 401.33, RPM 49.97, Press 4420.81, Tq 13.77, ROP 70.00, Diff -64.16, Temp 156.20
03/21/2022 | 18:19 | 18:39 | 0.33 | 16487 | 16501 | 14 | LAT | 3: BHA 3 | 2J | Slide Drill f/16487.00 t/16501.00, TF -146.55G, w/WOB 40,Flow 401.35, Press 4719.06, Tq 13.77, ROP 42.00, Diff 486.58, Temp 156.20
03/21/2022 | 18:39 | 18:58 | 0.32 | 16501 | 16570 | 69 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16501.00 t/16570.00, w/WOB 30,Flow 401.34, RPM 67.62, Press 5196.73, Tq 13.77, ROP 217.89, Diff -151.56, Temp 147.20
03/21/2022 | 18:58 | 19:02 | 0.07 | 16570 | 16570 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 19:02 | 19:14 | 0.2 | 16570 | 16580 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16570.00 t/16580.00, w/WOB 30,Flow 401.37, RPM 49.99, Press 4628.40, Tq 13.77, ROP 50.00, Diff 56.98, Temp 147.20
03/21/2022 | 19:14 | 19:50 | 0.6 | 16580 | 16605 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/16580.00 t/16605.00, TF -118.81G, w/WOB 40,Flow 401.53, Press 5018.54, Tq 13.77, ROP 41.67, Diff 459.69, Temp 147.20
03/21/2022 | 19:50 | 20:07 | 0.28 | 16605 | 16664 | 59 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16605.00 t/16664.00, w/WOB 30,Flow 401.37, RPM 58.73, Press 5270.91, Tq 13.77, ROP 208.24, Diff 561.13, Temp 141.80
03/21/2022 | 20:07 | 20:11 | 0.07 | 16664 | 16664 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 20:11 | 20:21 | 0.17 | 16664 | 16675 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16664.00 t/16675.00, w/WOB 30,Flow 401.34, RPM 49.97, Press 4419.58, Tq 13.77, ROP 66.00, Diff -14.42, Temp 141.80
03/21/2022 | 20:21 | 20:57 | 0.6 | 16675 | 16697 | 22 | LAT | 3: BHA 3 | 2J | Slide Drill f/16675.00 t/16697.00, TF -148.42G, w/WOB 40,Flow 401.20, Press 5138.49, Tq 13.77, ROP 36.67, Diff 512.13, Temp 141.80
03/21/2022 | 20:57 | 21:17 | 0.33 | 16697 | 16759 | 62 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16697.00 t/16759.00, w/WOB 30,Flow 401.32, RPM 66.93, Press 5325.72, Tq 13.77, ROP 186.00, Diff 1060.99, Temp 140.00
03/21/2022 | 21:17 | 21:22 | 0.08 | 16759 | 16759 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 21:22 | 21:51 | 0.48 | 16759 | 16854 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16759.00 t/16854.00, w/WOB 30,Flow 401.35, RPM 66.07, Press 5198.44, Tq 13.77, ROP 196.55, Diff 554.06, Temp 150.80
03/21/2022 | 21:51 | 21:55 | 0.07 | 16854 | 16854 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 21:55 | 22:22 | 0.45 | 16854 | 16948 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16854.00 t/16948.00, w/WOB 30,Flow 401.33, RPM 66.68, Press 5118.30, Tq 13.77, ROP 208.89, Diff 323.35, Temp 156.20
03/21/2022 | 22:22 | 22:26 | 0.07 | 16948 | 16948 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 22:26 | 22:43 | 0.28 | 16948 | 16960 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16948.00 t/16960.00, w/WOB 30,Flow 401.32, RPM 49.93, Press 4428.13, Tq 13.77, ROP 42.35, Diff 344.52, Temp 156.20
03/21/2022 | 22:43 | 23:26 | 0.72 | 16960 | 16980 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/16960.00 t/16980.00, TF 159.42G, w/WOB 40,Flow 401.31, Press 5253.45, Tq 13.77, ROP 27.91, Diff 409.75
03/21/2022 | 23:26 | 23:53 | 0.45 | 16980 | 17042 | 62 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16980.00 t/17042.00, w/WOB 30,Flow 401.34, RPM 67.69, Press 5345.14, Tq 13.77, ROP 137.78, Diff 733.60, Temp 154.40
03/21/2022 | 23:53 | 23:58 | 0.08 | 17042 | 17042 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/21/2022 | 23:58 | 24:00 | 0.03 | 17042 | 17044 | 2 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17042.00 t/17044.00, w/WOB 30,Flow 401.28, RPM 49.94, Press 5013.18, Tq 13.77, ROP 60.00, Diff 929.33, Temp 154.40
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_22_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/22/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 122430
|  |  |  | 24hr Summary: |  | Drill Lateral
|  |  |  | 24hr Lookahead: |  | POOH for BHA - Change BHA - TIH - Drill Lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17044 |  | 10230 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 17890 |  | 17890 |  | OD (in): |  | 10.75 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 846 |  | 7660 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): |  | 108 |  | 1269 | [5 empty] | 100: | 1 | Chlorides: | 600
Rotary Drilled (Usft): |  | 738 |  | 6391 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.10 / 0.40
Drlg/Circ Hrs: |  | 9.02 / 3.38 |  | 57.43 / 25.80 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 3.78 |  | 22.08 |  | SN: |  | 13685101 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 5.23 |  | 35.35 |  | Bit # |  | 3 |  | PH / Temp(F) | 7.0 / 67.00 | Mud Type: | Water
ROP Rot/Slide (Usft/hr): |  | 141.02 / 28.55 |  | 180.79 / 57.46 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 129.25 |  | Grade In: |  | New
% Slide: |  | 12.77 |  | 16.57 |  | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: |  | 87.23 |  | 83.43 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | A Mejia B Kitzman | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17068 | 84.3 | 133.64 | 10996.64 | -4553.4 | 5245.97 | 1.58 |  | 109.8 | 6932.99 | -0.53 |  | 1.49 | 94
17163 | 85.55 | 134.14 | 11005.05 | -4619.01 | 5314.17 | 1.42 |  | 21.75 | 7027.61 | 1.32 |  | 0.53 | 95
17256 | 85.93 | 133.66 | 11011.95 | -4683.31 | 5380.99 | 0.66 |  | -51.57 | 7120.35 | 0.41 |  | -0.52 | 93
17350 | 89.02 | 134.22 | 11016.1 | -4748.47 | 5448.61 | 3.34 |  | 10.28 | 7214.24 | 3.29 |  | 0.6 | 94
17444 | 87.67 | 133.69 | 11018.81 | -4813.69 | 5516.24 | 1.54 |  | -158.58 | 7308.19 | -1.44 |  | -0.56 | 94
17539 | 87.64 | 134.59 | 11022.7 | -4879.79 | 5584.36 | 0.95 |  | 91.93 | 7403.11 | -0.03 |  | 0.95 | 95
17633 | 91.04 | 135.14 | 11023.78 | -4946.09 | 5650.97 | 3.66 |  | 9.19 | 7497.09 | 3.62 |  | 0.59 | 94
17728 | 91.43 | 133.91 | 11021.73 | -5012.69 | 5718.69 | 1.36 |  | -72.39 | 7592.06 | 0.41 |  | -1.29 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 93.82 | 35 | 58.04 | 331 | 400.98 | 4978.63 | 4529.69 | 0 | 270 | 180.53 | 150 | 13.77 | 0
Run | 133.37 | 29.4 | 59.87 | 331 | 399.12 | 4446.25 | 3967.54 | 0 | 259.07 | 192.31 | 157.29 | 13.33 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/22/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/22/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/22/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/22/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/22/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/22/2022 | 00:00 | 00:10 | 0.17 | 17044 | 17052 | 8 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17044.00 t/17052.00, w/WOB 30,Flow 401.36, RPM 49.92, Press 4842.22, Tq 13.77, ROP 48.00, Diff 34.46, Temp 159.80
03/22/2022 | 00:10 | 00:25 | 0.25 | 17052 | 17059 | 7 | LAT | 3: BHA 3 | 2J | Slide Drill f/17052.00 t/17059.00, TF 64.95G, w/WOB 40,Flow 401.29, Press 5284.95, Tq 13.77, ROP 28.00, Diff 426.07
03/22/2022 | 00:25 | 00:49 | 0.4 | 17059 | 17136 | 77 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17059.00 t/17136.00, w/WOB 30,Flow 401.29, RPM 67.25, Press 5600.59, Tq 13.77, ROP 192.50, Diff 926.41, Temp 168.80
03/22/2022 | 00:49 | 00:53 | 0.07 | 17136 | 17136 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 00:53 | 01:03 | 0.17 | 17136 | 17146 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17136.00 t/17146.00, w/WOB 30,Flow 401.45, RPM 49.94, Press 4812.73, Tq 13.77, ROP 60.00, Diff -74.11, Temp 168.80
03/22/2022 | 01:03 | 01:42 | 0.65 | 17146 | 17163 | 17 | LAT | 3: BHA 3 | 2J | Slide Drill f/17146.00 t/17163.00, TF 5.44G, w/WOB 40,Flow 401.52, Press 5539.03, Tq 13.77, ROP 26.15, Diff 616.90
03/22/2022 | 01:42 | 02:06 | 0.4 | 17163 | 17230 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17163.00 t/17230.00, w/WOB 30,Flow 401.35, RPM 67.49, Press 4883.28, Tq 13.77, ROP 167.50, Diff 1143.49, Temp 163.40
03/22/2022 | 02:06 | 02:11 | 0.08 | 17230 | 17230 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 02:11 | 02:44 | 0.55 | 17230 | 17324 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17230.00 t/17324.00, w/WOB 30,Flow 401.26, RPM 49.85, Press 4232.48, Tq 13.77, ROP 170.91, Diff 934.04, Temp 165.20
03/22/2022 | 02:44 | 02:49 | 0.08 | 17324 | 17324 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 02:49 | 03:03 | 0.23 | 17324 | 17334 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17324.00 t/17334.00, w/WOB 30,Flow 401.26, RPM 49.94, Press 4447.01, Tq 13.77, ROP 42.86, Diff 40.62, Temp 165.20
03/22/2022 | 03:03 | 03:24 | 0.35 | 17334 | 17350 | 16 | LAT | 3: BHA 3 | 2J | Slide Drill f/17334.00 t/17350.00, TF 12.24G, w/WOB 40,Flow 401.15, Press 5080.89, Tq 13.77, ROP 45.71, Diff 434.33, Temp 165.20
03/22/2022 | 03:24 | 03:45 | 0.35 | 17350 | 17418 | 68 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17350.00 t/17418.00, w/WOB 30,Flow 401.30, RPM 65.93, Press 5287.23, Tq 13.77, ROP 194.29, Diff 440.13, Temp 154.40
03/22/2022 | 03:45 | 03:50 | 0.08 | 17418 | 17418 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 03:50 | 04:21 | 0.52 | 17418 | 17512 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17418.00 t/17428.40, w/WOB ,Flow 401.38, RPM 49.92, Press 5140.79, Tq 13.77, ROP 156.00, Temp 152.60
03/22/2022 | 04:21 | 04:25 | 0.07 | 17512 | 17512 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 04:25 | 04:38 | 0.22 | 17512 | 17524 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17512.00 t/17524.00, w/WOB 30.00,Flow 401.33, RPM 49.91, Press 4539.27, Tq 13.77, ROP 55.38, Diff 15.20, Temp 154.40
03/22/2022 | 04:38 | 04:58 | 0.33 | 17524 | 17534 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/17524.00 t/17534.00, TF 38.94G, w/WOB 40.00,Flow 401.38, Press 5227.81, Tq 13.77, ROP 30.00, Diff 473.08, Temp 154.40
03/22/2022 | 04:58 | 05:19 | 0.35 | 17534 | 17607 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17534.00 t/17607.00, w/WOB 30.00,Flow 401.26, RPM 66.91, Press 5410.15, Tq 13.77, ROP 208.57, Diff 1191.30, Temp 145.40
03/22/2022 | 05:19 | 05:23 | 0.07 | 17607 | 17607 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 05:23 | 05:33 | 0.17 | 17607 | 17620 | 13 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17607.00 t/17620.00, w/WOB 30.00,Flow 401.32, RPM 54.47, Press 4405.82, Tq 13.77, ROP 78.00, Diff -97.42, Temp 145.40
03/22/2022 | 05:33 | 05:48 | 0.25 | 17620 | 17630 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/17620.00 t/17630.00, TF 5.09G, w/WOB 50.00,Flow 401.32, Press 4929.06, Tq 13.77, ROP 40.00, Diff 410.41, Temp 154.40
03/22/2022 | 05:48 | 06:11 | 0.38 | 17630 | 17702 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17630.00 t/17702.00, w/WOB 30,Flow 401.32, RPM 66.34, Press 5252.54, Tq 13.77, ROP 187.83, Diff 303.83, Temp 152.60
03/22/2022 | 06:11 | 06:19 | 0.13 | 17702 | 17702 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 06:19 | 06:29 | 0.17 | 17702 | 17713 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17702.00 t/17713.00, w/WOB 30,Flow 401.41, RPM 49.91, Press 4472.90, Tq 13.77, ROP 66.00, Diff -105.11, Temp 156.20
03/22/2022 | 06:29 | 07:14 | 0.75 | 17713 | 17731 | 18 | LAT | 3: BHA 3 | 2J | Slide Drill f/17713.00 t/17731.00, TF 80.63G, w/WOB 50,Flow 401.17, Press 5167.24, Tq 13.77, ROP 24.00, Diff 484.53, Temp 156.20
03/22/2022 | 07:14 | 07:44 | 0.5 | 17731 | 17798 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17731.00 t/17798.00, w/WOB 30,Flow 401.37, RPM 67.21, Press 5333.03, Tq 13.77, ROP 134.00, Diff 1098.96, Temp 145.40
03/22/2022 | 07:44 | 07:54 | 0.17 | 17798 | 17798 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 07:54 | 08:04 | 0.17 | 17798 | 17807 | 9 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17798.00 t/17807.00, w/WOB 30,Flow 401.41, RPM 49.89, Press 4451.76, Tq 13.77, ROP 54.00, Diff -159.25, Temp 147.20
03/22/2022 | 08:04 | 08:28 | 0.4 | 17807 | 17818 | 11 | LAT | 3: BHA 3 | 2J | Slide Drill f/17807.00 t/17818.00, TF 145.60G, w/WOB 50,Flow 401.31, Press 4315.50, Tq 0.00, ROP 27.50, Diff 41.49, Temp 256.00
03/22/2022 | 08:28 | 19:44 | 11.27 | 17818 | 17818 | 0 | LAT | 3: BHA 3 | 8A | Repair IBOP
03/22/2022 | 19:44 | 20:32 | 0.8 | 17818 | 17837 | 19 | LAT | 3: BHA 3 | 2J | Slide Drill f/17818.00 t/17837.00, TF 166.73G, w/WOB 50,Flow 398.29, Press 5390.00, Tq 13.77, ROP 23.75, Diff 396.30, Temp 256.00
03/22/2022 | 20:32 | 21:02 | 0.5 | 17837 | 17890 | 53 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17837.00 t/17889.90, w/WOB 30,Flow 396.03, RPM 54.12, Press 5278.63, Tq 13.77, ROP 105.80, Diff 1283.02, Temp 177.80
03/22/2022 | 21:02 | 21:05 | 0.05 | 17890 | 17890 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
03/22/2022 | 21:05 | 21:50 | 0.75 | 17890 | 17890 | 0 | LAT | 3: BHA 3 | 5A | Circulate - Consult w/ Drilling Engineer
03/22/2022 | 21:50 | 23:40 | 1.83 | 17890 | 17890 | 0 | LAT | 3: BHA 3 | 3D | Backreaming Out of Hole to 16,850
03/22/2022 | 23:40 | 24:00 | 0.33 | 17890 | 17890 | 0 | LAT | 3: BHA 3 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_23_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/23/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 11800 |  |  | Well Cost($): |  | 134230
|  |  |  | 24hr Summary: |  | POOH - Repair IBOP - Change BHA - TIH
|  |  |  | 24hr Lookahead: |  | TIH - Drill Lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17890 |  | 17890 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 17890 |  | 17890 |  | OD (in): |  | 10.75 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45.5 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): | [9 empty] | 100: | 1 | Chlorides: | 600
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids: | 0.10 / 0.40
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 13685101 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 7.0 / 67.00 | Mud Type: | Water
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 4.5 |  | 4.5 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | A Mejia B Kitzman | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | 5.25 | 2 |  |  |  |  | 33.26 |  | 34.26
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 1.65 |  | 35.91
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.37
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.37
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 80.75
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.34 |  | 90.09
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 121.51
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 139.08
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 142.71
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2782.53
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 21.26 |  | 2803.79
2803.79
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.11 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 133.37 | 29.4 | 59.87 | 331 | 399.12 | 4446.25 | 3967.54 | 0 | 259.07 | 192.31 | 157.29 | 13.33 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/23/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/23/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/23/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/23/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/23/2022 |  | 23 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 03/23/2022 | PPM250005 | 9 |  | 1000 |  | 1 | 1000
MWD Inspection Fee Per Run(First 3 included in Mob/DeMob) |  |  |  |  | 03/23/2022 |  | 24 |  | 800 |  | 1 | 800
Total | [11 empty] | 11800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/23/2022 | 00:00 | 12:00 | 12 | 17890 | 17890 | 0 | LAT | 3: BHA 3 | 6B | POOH
03/23/2022 | 12:00 | 12:45 | 0.75 | 17890 | 17890 | 0 | LAT | 3: BHA 3 | 6P | Lay Down BHA 3
03/23/2022 | 12:45 | 17:45 | 5 | 17890 | 17890 | 0 | LAT |  | 8A | Work on IBOP
03/23/2022 | 17:45 | 19:30 | 1.75 | 17890 | 17890 | 0 | LAT | 4: BHA 4 | 6O | Pick Up BHA 4
03/23/2022 | 19:30 | 24:00 | 4.5 | 17890 | 17890 | 0 | LAT | 4: BHA 4 | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_24_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/24/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 144230
|  |  |  | 24hr Summary: |  | POOH - Reapir IBOP - Change BHA - TIH
|  |  |  | 24hr Lookahead: |  | TIH - Drill Lateral to TD
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17890 |  | 17890 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 19359 |  | 19359 |  | OD (in): |  | 10.75 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 1469 |  | 1469 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): |  | 120 |  | 120 | [5 empty] | 100: | 1 | Chlorides: | 600
Rotary Drilled (Usft): |  | 1349 |  | 1349 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.10 / 0.40
Drlg/Circ Hrs: |  | 11.27 / 7.73 |  | 11.27 / 7.73 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  | 2.68 |  | 2.68 |  | SN: |  | 13618579 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 8.58 |  | 8.58 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 67.00 | Fluid Loss / Mud Type: | 6 / Water
ROP Rot/Slide (Usft/hr): |  | 157.17 / 44.72 |  | 157.17 / 44.72 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 28.5 |  | Grade In: |  | New
% Slide: |  | 8.17 |  | 8.17 |  | Grade Out: |  | 3-3-CT-N-X-I-LT-TD
% Rotary: |  | 91.83 |  | 91.83 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | A Mejia B Kitzman | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 -.004 |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 34.16
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 2.11 |  | 36.27
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.73
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.73
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 81.11
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 112.53
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 130.1
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 133.73
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2773.55
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.17 |  | 2794.72
2794.72
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250005 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17910 | 85.77 | 134.76 | 11024.35 | -5139.55 | 5849.05 | 4.48 |  | 170.68 | 7773.97 | -4.42 |  | 0.73 | 88
18005 | 84.91 | 134.69 | 11032.06 | -5206.18 | 5916.32 | 0.91 |  | -175.36 | 7868.65 | -0.91 |  | -0.07 | 95
18098 | 84.56 | 134.82 | 11040.6 | -5271.38 | 5982.08 | 0.4 |  | 159.71 | 7961.26 | -0.38 |  | 0.14 | 93
18193 | 85.53 | 134.82 | 11048.8 | -5338.09 | 6049.22 | 1.02 |  | 0 | 8055.9 | 1.02 |  | 0 | 95
18288 | 85.18 | 134.24 | 11056.5 | -5404.5 | 6116.72 | 0.71 |  | -121.22 | 8150.59 | -0.37 |  | -0.61 | 95
18382 | 88.05 | 134.59 | 11062.05 | -5470.16 | 6183.74 | 3.08 |  | 6.95 | 8244.41 | 3.05 |  | 0.37 | 94
18477 | 88.98 | 134.63 | 11064.51 | -5536.85 | 6251.34 | 0.98 |  | 2.46 | 8339.38 | 0.98 |  | 0.04 | 95
18571 | 89.33 | 134.29 | 11065.89 | -5602.69 | 6318.43 | 0.52 |  | -44.17 | 8433.37 | 0.37 |  | -0.36 | 94
18666 | 89.58 | 134.17 | 11066.8 | -5668.95 | 6386.5 | 0.29 |  | -25.64 | 8528.36 | 0.26 |  | -0.13 | 95
18760 | 87.58 | 135.29 | 11069.13 | -5735.08 | 6453.25 | 2.44 |  | 150.77 | 8622.33 | -2.13 |  | 1.19 | 94
18856 | 88.28 | 135.68 | 11072.6 | -5803.49 | 6520.51 | 0.83 |  | 29.12 | 8718.25 | 0.73 |  | 0.41 | 96
18951 | 88.24 | 135.42 | 11075.48 | -5871.27 | 6587.01 | 0.28 |  | -98.75 | 8813.19 | -0.04 |  | -0.27 | 95
19045 | 86.07 | 134.41 | 11080.15 | -5937.56 | 6653.49 | 2.55 |  | -155.09 | 8907.07 | -2.31 |  | -1.07 | 94
19137 | 85.5 | 133.71 | 11086.91 | -6001.36 | 6719.42 | 0.98 |  | -129.26 | 8998.81 | -0.62 |  | -0.76 | 92
19232 | 84.36 | 133.91 | 11095.3 | -6066.87 | 6787.71 | 1.22 |  | 170.1 | 9093.43 | -1.2 |  | 0.21 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 130.38 | 25 | 62.69 | 321 | 379.55 | 5420.35 | 4536.31 | 281 | 220 | 229.52 | 130 | 13.77 | 4
Run | 130.38 | 25 | 62.69 | 321 | 380.26 | 5419.65 | 4559.19 | 281 | 220 | 227.29 | 130 | 13.77 | 4
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/24/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/24/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/24/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/24/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/24/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/24/2022 | 00:00 | 05:00 | 5 | 17890 | 17890 | 0 | LAT | 4: BHA 4 | 6A | TIH
03/24/2022 | 05:00 | 10:00 | 5 | 17890 | 17890 | 0 | LAT | 4: BHA 4 | 3C | Wash & Ream F/ 14,962
03/24/2022 | 10:00 | 10:10 | 0.17 | 17890 | 17890 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 10:10 | 10:31 | 0.35 | 17890 | 17910 | 20 | LAT | 4: BHA 4 | 2J | Rotary Drill f/17910.00 t/17973.00, w/WOB 25.00,Flow 401.39, RPM 64.35, Press 5576.53, Tq 13.77, ROP 945.00, Diff 1844.55, Temp 165.20
03/24/2022 | 10:31 | 10:50 | 0.32 | 17910 | 17910 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 10:50 | 10:54 | 0.07 | 17910 | 17973 | 63 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17973.00 t/18068.00, w/WOB 25.00,Flow 429.58, RPM 65.95, Press 5607.29, Tq 13.77, ROP 196.55, Diff 2289.12, Temp 165.20
03/24/2022 | 10:54 | 11:02 | 0.13 | 17973 | 17973 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 11:02 | 11:31 | 0.48 | 17973 | 18068 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18068.00 t/18163.00, w/WOB 25.00,Flow 401.33, RPM 67.97, Press 5967.18, Tq 13.77, ROP 154.05, Diff 2189.33, Temp 158.00
03/24/2022 | 11:31 | 12:20 | 0.82 | 18068 | 18068 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 12:20 | 12:57 | 0.62 | 18068 | 18163 | 95 | LAT | 4: BHA 4 | 2K | Survey & Connection
03/24/2022 | 12:57 | 13:04 | 0.12 | 18163 | 18163 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 13:04 | 13:17 | 0.22 | 18163 | 18178 | 15 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18163.00 t/18178.00, w/WOB 25.00,Flow 375.81, RPM 59.23, Press 5039.45, Tq 13.77, ROP 69.23, Diff -25.32, Temp 156.20
03/24/2022 | 13:17 | 13:43 | 0.43 | 18178 | 18196 | 18 | LAT | 4: BHA 4 | 2J | Slide Drill f/18178.00 t/18196.00, TF 4.81G, w/WOB 25.00,Flow 375.77, Press 5073.49, Tq 13.77, ROP 41.54, Diff 551.56, Temp 156.20
03/24/2022 | 13:43 | 14:01 | 0.3 | 18196 | 18258 | 62 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18196.00 t/18258.00, w/WOB 25.00,Flow 375.82, RPM 67.27, Press 5480.17, Tq 13.77, ROP 206.67, Diff 706.24, Temp 140.00
03/24/2022 | 14:01 | 14:07 | 0.1 | 18258 | 18258 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 14:07 | 14:37 | 0.5 | 18258 | 18305 | 47 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18258.00 t/18305.00, w/WOB 25.00,Flow 375.76, RPM 65.39, Press 4592.03, Tq 13.77, ROP 94.00, Diff -217.60, Temp 154.40
03/24/2022 | 14:37 | 14:58 | 0.35 | 18305 | 18322 | 17 | LAT | 4: BHA 4 | 2J | Slide Drill f/18305.00 t/18322.00, TF -31.73G, w/WOB 25.00,Flow 375.84, Press 5508.25, Tq 13.77, ROP 48.57, Diff 376.22, Temp 154.40
03/24/2022 | 14:58 | 15:08 | 0.17 | 18322 | 18353 | 31 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18322.00 t/18353.00, w/WOB 25.00,Flow 375.80, RPM 62.75, Press 5837.73, Tq 13.77, ROP 186.00, Diff 1483.67, Temp 136.40
03/24/2022 | 15:08 | 15:15 | 0.12 | 18353 | 18353 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 15:15 | 15:28 | 0.22 | 18353 | 18372 | 19 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18353.00 t/18372.00, w/WOB 25.00,Flow 375.78, RPM 49.89, Press 5001.92, Tq 13.77, ROP 87.69, Diff 2.14, Temp 145.40
03/24/2022 | 15:28 | 15:51 | 0.38 | 18372 | 18387 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/18372.00 t/18387.00, TF -3.35G, w/WOB 25.00,Flow 375.53, Press 5056.36, Tq 13.77, ROP 39.13, Diff 97.01, Temp 145.40
03/24/2022 | 15:51 | 16:48 | 0.95 | 18387 | 18448 | 61 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18387.00 t/18448.00, w/WOB 25.00,Flow 375.81, RPM 67.02, Press 5870.98, Tq 13.77, ROP 64.21, Diff 2277.05, Temp 145.40
03/24/2022 | 16:48 | 16:54 | 0.1 | 18448 | 18448 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 16:54 | 17:26 | 0.53 | 18448 | 18544.14 | 96.14 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18448.00 t/18544.14, w/WOB 25.00,Flow 375.80, RPM 67.38, Press 5185.67, Tq 13.77, ROP 180.26, Diff 1787.69, Temp 145.40
03/24/2022 | 17:26 | 17:37 | 0.18 | 18544.14 | 18544.14 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 17:37 | 18:14 | 0.62 | 18544.14 | 18636 | 91.86 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18544.14 t/18636.00, w/WOB 25.00,Flow 375.80, RPM 67.38, Press 5185.67, Tq 13.77, ROP 148.96, Diff 1787.69, Temp 145.40
03/24/2022 | 18:14 | 18:20 | 0.1 | 18636 | 18636 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 18:20 | 18:44 | 0.4 | 18636 | 18735 | 99 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18636.00 t/18735.00, w/WOB 25.00,Flow 375.82, RPM 66.18, Press 5780.86, Tq 13.77, ROP 247.50, Diff 1068.55, Temp 163.40
03/24/2022 | 18:44 | 18:49 | 0.08 | 18735 | 18735 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 18:49 | 19:00 | 0.18 | 18735 | 18745 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18735.00 t/18745.00, w/WOB 25.00,Flow 375.81, RPM 49.92, Press 4904.45, Tq 13.77, ROP 54.55, Diff 154.99, Temp 163.40
03/24/2022 | 19:00 | 19:24 | 0.4 | 18745 | 18762 | 17 | LAT | 4: BHA 4 | 2J | Slide Drill f/18745.00 t/18762.00, TF 141.33G, w/WOB 25.00,Flow 375.84, Press 5456.12, Tq 13.77, ROP 42.50, Diff 290.64, Temp 163.40
03/24/2022 | 19:24 | 19:47 | 0.38 | 18762 | 18830 | 68 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18762.00 t/18830.00, w/WOB 25.00,Flow 375.83, RPM 65.43, Press 5487.04, Tq 13.77, ROP 177.39, Diff 1460.68, Temp 150.80
03/24/2022 | 19:47 | 19:51 | 0.07 | 18830 | 18830 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 19:51 | 20:26 | 0.58 | 18830 | 18920 | 90 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18830.00 t/18920.00, w/WOB 25.00,Flow 375.80, RPM 68.10, Press 5812.00, Tq 13.77, ROP 154.29, Diff -88.67, Temp 159.80
03/24/2022 | 20:26 | 20:30 | 0.07 | 18920 | 18920 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 20:30 | 20:55 | 0.42 | 18920 | 19014 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18920.00 t/19014.00, w/WOB 25.00,Flow 375.82, RPM 65.95, Press 5791.17, Tq 13.77, ROP 225.60, Diff 492.61, Temp 165.20
03/24/2022 | 20:55 | 21:00 | 0.08 | 19014 | 19014 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 21:00 | 21:13 | 0.22 | 19014 | 19026 | 12 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19014.00 t/19026.00, w/WOB 25.00,Flow 375.88, RPM 49.91, Press 4606.41, Tq 13.77, ROP 55.38, Diff -7.61, Temp 165.20
03/24/2022 | 21:13 | 21:32 | 0.32 | 19026 | 19039 | 13 | LAT | 4: BHA 4 | 2J | Slide Drill f/19026.00 t/19039.00, TF -172.41G, w/WOB 25.00,Flow 375.73, Press 5302.72, Tq 13.77, ROP 41.05, Diff 498.87, Temp 165.20
03/24/2022 | 21:32 | 21:56 | 0.4 | 19039 | 19110 | 71 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19039.00 t/19110.00, w/WOB 25.00,Flow 375.83, RPM 67.66, Press 5881.26, Tq 13.77, ROP 177.50, Diff 1491.48, Temp 150.80
03/24/2022 | 21:56 | 22:00 | 0.07 | 19110 | 19110 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 22:00 | 22:29 | 0.48 | 19110 | 19202 | 92 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19110.00 t/19202.00, w/WOB 25.00,Flow 375.83, RPM 65.74, Press 5949.41, Tq 13.77, ROP 190.34, Diff 267.43, Temp 163.40
03/24/2022 | 22:29 | 22:33 | 0.07 | 19202 | 19202 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 22:33 | 23:02 | 0.48 | 19202 | 19296 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19202.00 t/19296.00, w/WOB 25.00,Flow 375.83, RPM 65.58, Press 5830.03, Tq 13.77, ROP 194.48, Diff 2713.58, Temp 167.00
03/24/2022 | 23:02 | 23:11 | 0.15 | 19296 | 19296 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/24/2022 | 23:11 | 23:23 | 0.2 | 19296 | 19307 | 11 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19296.00 t/19307.00, w/WOB 25.00,Flow 375.85, RPM 49.89, Press 5124.66, Tq 13.77, ROP 55.00, Diff -74.77, Temp 167.00
03/24/2022 | 23:23 | 23:50 | 0.45 | 19307 | 19327 | 20 | LAT | 4: BHA 4 | 2J | Slide Drill f/19307.00 t/19327.00, TF 3.73G, w/WOB 25.00,Flow 375.89, Press 5387.61, Tq 13.77, ROP 44.44, Diff 624.77, Temp 167.00
03/24/2022 | 23:50 | 24:00 | 0.17 | 19327 | 19359 | 32 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19327.00 t/19359.00, w/WOB 25.00,Flow 375.82, RPM 60.28, Press 5473.27, Tq 13.77, ROP 192.00, Diff 711.27, Temp 152.60
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_25_2022_DDR
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31194 / 21DD0262MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Mill H08
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Longitude: |  | 96° 43' 1.095" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/25/2022 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10000 |  |  | Well Cost($): |  | 154230
|  |  |  | 24hr Summary: |  | Drill Lateral to TD - POOH
|  |  |  | 24hr Lookahead: |  | End of Job
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 19359 |  | 17890 |  | Csg Shoe MD(Usft): |  | 2818 |  | 600: | 3 | PV: | 1
End Depth (Usft): |  | 19429.04 |  | 19429.04 |  | OD (in): |  | 10.75 |  | 300: | 2 | YP: | 1
Total Drilled (Usft): |  | 70 |  | 1539 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 1 | Viscosity: | 28
Slide Drilled (Usft): |  |  |  | 120 | [5 empty] | 100: | 1 | Chlorides: | 600
Rotary Drilled (Usft): |  | 70 |  | 1419 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.10 / 0.40
Drlg/Circ Hrs: |  | 0.35 / 1.15 |  | 11.62 / 8.88 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water:
Slide Drilling Hrs: |  |  |  | 2.68 |  | SN: |  | 13618579 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 0.35 |  | 8.93 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.0 / 67.00 | Mud Type: | Water
ROP Rot/Slide (Usft/hr): |  | 200.11 / 0.00 |  | 158.85 / 44.72 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 23.5 |  | 52 |  | Grade In: |  | New
% Slide: |  |  |  | 7.8 |  | Grade Out: |  | 3-3-CT-N-X-I-LT-TD
% Rotary: |  | 100 |  | 92.2 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | NA |  | NA
Chris Mayeux |  | Marshall Adams |  | A Mejia B Kitzman | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 1 |  | 1
5.5 6/7 8.8 2.12 TS HS88 -.004 |  |  |  | 5 | 2 |  |  |  |  | 33.16 |  | 34.16
BTI |  |  |  | 4.875 | 2.25 |  |  |  |  | 2.11 |  | 36.27
Non Mag Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.46 |  | 45.73
UBHO Sub |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 49.73
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.38 |  | 81.11
Non Mag Drill Collar |  |  |  | 5 | 2.688 |  |  |  |  | 31.42 |  | 112.53
ToMax |  |  |  | 5 | 2.75 |  |  |  |  | 17.57 |  | 130.1
Crossover |  |  |  | 5.312 | 2.688 |  |  |  |  | 3.63 |  | 133.73
28 Stands DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2639.82 |  | 2773.55
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 21.17 |  | 2794.72
2794.72
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250005 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
19327 | 85.32 | 133.88 | 11103.85 | -6132.47 | 6855.89 | 1.01 |  | -1.78 | 9188.04 | 1.01 |  | -0.03 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 200.11 | 25 | 62.69 | 321 | 379.55 | 5420.35 | 4536.31 | 0 | 220 | 229.52 | 130 | 13.77 | 0
Run | 128.98 | 25 | 62.69 | 321 | 380.26 | 5419.65 | 4559.19 | 0 | 220 | 227.29 | 130 | 13.77 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5500 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD with Gamma Services (Operating) |  |  |  |  | 03/25/2022 |  | 2 |  | 7400 |  | 1 | 7400
Perdiem Per Hand |  |  |  |  | 03/25/2022 |  | 7 |  | 100 |  | 4 | 400
Multi-Rig Discount Off of Operating Day Rate |  |  |  |  | 03/25/2022 |  | 3 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 03/25/2022 |  | 19 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/25/2022 |  | 23 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 10000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/25/2022 | 00:00 | 00:09 | 0.15 | 19359 | 19390 | 31 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19359.00 t/19390.00, w/WOB 25.00,Flow 375.81, RPM 63.54, Press 5577.87, Tq 13.77, ROP 206.67, Diff 2748.50, Temp 152.60
03/25/2022 | 00:09 | 00:18 | 0.15 | 19390 | 19390 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
03/25/2022 | 00:18 | 00:30 | 0.2 | 19390 | 19429.04 | 39.04 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19390.00 t/19429.04, w/WOB 25.00,Flow 375.82, RPM 62.54, Press 5495.48, Tq 13.77, ROP 195.20, Diff 1059.33, Temp 161.60
03/25/2022 | 00:30 | 01:30 | 1 | 19429.04 | 19429.04 | 0 | LAT | 4: BHA 4 | 5A | Circulate
03/25/2022 | 01:30 | 02:10 | 0.67 | 19429.04 | 19429.04 | 0 | LAT | 4: BHA 4 | 6B | POOH T/ 18,467
03/25/2022 | 02:10 | 22:30 | 20.33 | 19429.04 | 19429.04 | 0 | LAT | 4: BHA 4 | 6K | POOH laying down DP
03/25/2022 | 22:30 | 23:30 | 1 | 19429.04 | 19429.04 | 0 | LAT | 4: BHA 4 | 6P | Lay Down BHA
03/25/2022 | 23:30 | 24:00 | 0.5 | 19429.04 | 19429.04 | 0 | LAT |  | 1I | Rig Down and Backhaul Tools for EOW
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 457.20 (Usft)
Well: |  |  | Mill H08 | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1105822 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 02/01/2022 | Depth In: |  | 108 | Total Drilled: |  | 2720.00 (Usft)
Date Out: |  |  | 02/01/2022 | Depth Out: |  | 2828 | Drilling / Circ Hours: |  | 4.15 / 3.47
Survey Offset: |  |  | 75
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47245 | U616S | 13.5 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800035 | 7/8 5.9 1.50 Stab HPW -.013 NBS 13 | 8 | 2 | 8.000 / 1.94 | 6 5/8 REG / 6 5/8 REG |  | 37.47 | 38.97
| 3 | GT801175 | Nortrak Stabilizer (BFF) | 13 | 2.875 | 3.120 / 8.00 | 6 5/8 REG / 6 5/8 REG |  | 7.87 | 46.84
| 4 | GT80-10-648 | Pony Collar (NO HARDBANDING) | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 9.99 | 56.83
| 5 | 775234 | UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.96 | 60.79
| 6 | GT80-30-171 | Drill Collar (NO HARDBANDING) | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.64 | 90.43
| 7 | GT80-30-378 | Drill Collar (NO HARDBANDING) | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.59 | 120.02
| 8 | GT7746831 | Crossover Sub | 7.688 | 3.25 | 6.750 / 1.52 | 4 1/2 IF / 6 5/8 REG |  | 3.17 | 123.19
| 9 | Rig1 | 11 Jts 5" HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 334.01 | 457.2
| 10 | [8 empty] | 457.2
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | U616S | 0-0-NO-A-X-I-NO-TD | 0-0-NO-A-X-I-NO-TD | 2720
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.50 Stab HPW -.013 NBS 13 |  |  | PDCI / 7/8 5.9 | 5.82 / 1.50 |  | 13 | 8.31 | 200 | 1390
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
21870 |  |  | 900 | 100 |  | 400-900 | 0.155 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPW |  | -0.013
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO Sub
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7/8 5.9 1.50 Stab HPW -.013 NBS 13 | 13 |  | 5.25 |  |  | 3.75
3 |  |  | Nortrak Stabilizer (BFF) | 13 |  | 6 |  |  | 42.67

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2727.14 (Usft)
Well: |  |  | Mill H08 | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1105822 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 02/02/2022 | Depth In: |  | 2828 | Total Drilled: |  | 7402.00 (Usft)
Date Out: |  |  | 02/04/2022 | Depth Out: |  | 10230 | Drilling / Circ Hours: |  | 26.92 / 7.85
Survey Offset: |  |  | 65 | Gamma Offset: |  | 61
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 59253 | SPL613 | 9.875 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | MTR775009 | 7/8 5.9 2.0 TS HPW -.012 | 8 | 2 | 8.000 / 1.88 | 6 5/8 REG / 6 5/8 REG |  | 37.54 | 39.04
| 3 | GT80-10-648 | Pony Collar (NO HARDBANDING) | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 9.99 | 49.03
| 4 | 775234 | UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.96 | 52.99
| 5 | GT80-30-171 | Drill Collar (NO HARDBANDING) | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.64 | 82.63
| 6 | GT80-30-378 | Drill Collar (NO HARDBANDING) | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.59 | 112.22
| 7 | GT8046294 | Crossover Sub | 7.938 | 3 | 6.500 / 1.43 | 4 1/2 XH / 6 5/8 REG |  | 3.18 | 115.4
| 8 | 6DC | 6 Jts 6 1/2in DC | 6.5 | 3 |  | 4 1/2 XH / 4 1/2 XH |  | 186.19 | 301.59
| 9 | GT6744684 | Crossover Sub | 6.688 | 2.812 |  | 4 1/2 IF / 4 1/2 XH |  | 3.2 | 304.79
| 10 | Rig1 | 11 Jts 5 HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 334.01 | 638.8
| 11 | Rig2 | 22 Stds 5in DP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 2065.88 | 2704.68
| 12 | PG675-0050 | Agitator | 6.75 | 2.5 | 6.750 / 1.80 | 4 1/2 IF / 4 1/2 IF |  | 22.46 | 2727.14
| 13 | [8 empty] | 2727.14
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 1-1-WT-A-X-I-NO-TD | 7402
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.0 TS HPW -.012 |  |  | PDCI / 7/8 5.9 | 6.04 / 2.00 |  | 0 | 8.35 | 318 | 1390
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
21870 |  |  | 900 | 80 |  | 400-900 | 0.155 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPW |  | -0.012
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO Sub
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2803.79 (Usft)
Well: |  |  | Mill H08 | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1105822 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 03/17/2022 | Depth In: |  | 10230 | Total Drilled: |  | 7660.00 (Usft)
Date Out: |  |  | 03/23/2022 | Depth Out: |  | 17890 | Drilling / Circ Hours: |  | 57.43 / 25.80
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13685101 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 1 | 1
| 2 | PPM250003 | 5.5 6/7 8.8 2.12 TS HS88 +.002 | 5.25 | 2 | 5.250 / 2.08 | XT39 / 3 1/2 Reg |  | 33.26 | 34.26
| 3 | BTI02 | BTI | 4.875 | 2.25 |  | XT39 / XT39 |  | 1.65 | 35.91
| 4 | GT50-10-465 | Non Mag Pony Collar | 5 | 2.75 |  | XT39 / XT39 |  | 9.46 | 45.37
| 5 | 500065 | UBHO Sub | 5.25 | 2.5 |  | XT39 / XT39 |  | 4 | 49.37
| 6 | GT50-30-707 | Non Mag Drill Collar | 5 | 2.688 | 5.000 / 1.28 | XT39 / XT39 |  | 31.38 | 80.75
| 7 | GT50-10-585 | Non Mag Pony Collar | 5 | 2.75 |  | XT39 / XT39 |  | 9.34 | 90.09
| 8 | GT50-30-722 | Non Mag Drill Collar | 5 | 2.688 | 5.000 / 1.18 | XT39 / XT39 |  | 31.42 | 121.51
| 9 | A52180 | ToMax | 5 | 2.75 | 5.000 / 2.89 | XT39 / XT39 |  | 17.57 | 139.08
| 10 | GT52331433 | Crossover | 5.312 | 2.688 |  | CET43 / XT39 |  | 3.63 | 142.71
| 11 | Rig28 | 28 Stands DP | 4.5 | 2.5 |  | CET43 / CET43 |  | 2639.82 | 2782.53
| 12 | PG525-0056 | Agitator | 5.25 | 2.5 | 5.250 / 1.80 | CET43 / CET43 |  | 21.26 | 2803.79
| 13 | [8 empty] | 2803.79
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 1-1-CT-S-X-I-NO-DMF | 7660
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  | PDCI / 6/7 8.8 | 4.11 / 2.12 |  | 0 | 5.5 | 250 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 900 | 70 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.002
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO Sub
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2794.72 (Usft)
Well: |  |  | Mill H08 | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1105822 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 03/23/2022 | Depth In: |  | 17890 | Total Drilled: |  | 1539.04 (Usft)
Date Out: |  |  | 03/25/2022 | Depth Out: |  | 19429.04 | Drilling / Circ Hours: |  | 11.62 / 8.88
Survey Offset: |  |  | 64 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618579 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 1 | 1
| 2 | PPM250005 | 5.5 6/7 8.8 2.12 TS HS88 -.004 | 5 | 2 | 5.250 / 1.97 | XT39 / 3 1/2 Reg |  | 33.16 | 34.16
| 3 | BTI03 | BTI | 4.875 | 2.25 |  | XT39 / XT39 |  | 2.11 | 36.27
| 4 | GT50-10-465 | Non Mag Pony Collar | 5 | 2.75 |  | XT39 / XT39 |  | 9.46 | 45.73
| 5 | 500065 | UBHO Sub | 5.25 | 2.5 |  | XT39 / XT39 |  | 4 | 49.73
| 6 | GT50-30-707 | Non Mag Drill Collar | 5 | 2.688 | 5.000 / 1.28 | XT39 / XT39 |  | 31.38 | 81.11
| 7 | GT50-30-722 | Non Mag Drill Collar | 5 | 2.688 | 5.000 / 1.18 | XT39 / XT39 |  | 31.42 | 112.53
| 8 | A52180 | ToMax | 5 | 2.75 | 5.000 / 2.89 | XT39 / XT39 |  | 17.57 | 130.1
| 9 | GT52331433 | Crossover | 5.312 | 2.688 |  | CET43 / XT39 |  | 3.63 | 133.73
| 10 | Rig28 | 28 Stands DP | 4.5 | 2.5 |  | CET43 / CET43 |  | 2639.82 | 2773.55
| 11 | PG525-0037 | Agitator | 5.312 | 2.5 | 5.250 / 1.80 | CET43 / CET43 |  | 21.17 | 2794.72
| 12 | [8 empty] | 2794.72
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 3-3-CT-N-X-I-LT-TD | 1539.04
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5.5 6/7 8.8 2.12 TS HS88 -.004 |  |  | PDCI / 6/7 8.8 | 4.10 / 2.12 |  | 0 | 5.5 | 250 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 900 | 70 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | -0.004
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO Sub
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Well: |  | Mill H08
|  |  |  | Longitude: |  | 96° 43' 1.095" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 75.00/89.54/102.20
Date In: |  | 02/01/2022 11:20 |  | SN: |  | PPM800035 |  |  |  | WOB Rotate (klbs): |  | 18.00
Date Out: |  | 02/01/2022 21:30 |  | Description: |  | 7/8 5.9 1.50 Stab HPW -.013 NBS 13 |  |  |  | WOB Slide (klbs): |  | 10.42
Depth In/Out(Usft): |  | 108.00 / 2828.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 94.76
Inc In/Out: |  | 0.25 / 10.34 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 872.22
Azi In/Out: |  | 81.51 / 70.70 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1587.04
Total Drilled (Usft): |  | 2720 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1889.81
%Slide (Ftg): |  | 7.61 |  | Bit to Bend (Usft): |  | 5.82 |  |  |  | Tq On Btm (kftlbs): |  | 8.66
%Slide (Time): |  | 18.07 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs): |  | 4
Slide Drilled (Usft): |  | 207 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 900
Slide Hours: |  | 0.75 |  | Stab to Bit (Usft): |  | 2.25 |  |  |  | Bit Data
%Rotary (Ftg): |  | 92.39 |  | Kickpad OD (in): |  | 8.312 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 81.93 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2513 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 3.4 |  | Length (Usft): |  | 37.47 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 4.15 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 3.47 / 10.17 |  | Rev per Gal: |  | 0.155 |  |  |  | Grade In: |  | 0-0-NO-A-X-I-NO-TD
Slide ROP (Usft/hr): |  | 276 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
Rot ROP (Usft/hr): |  | 739.12 |  | Stator Vendor/Type/Fit: |  | Abaco / HPW / -0.013 |  |  |  | Drill Hrs: |  | 4.15
Avg ROP (Usft/hr): |  | 655.42 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.47
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  |  |  | 1 | 1 | 8.3 |  | FW
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
75 | [11 empty] | 0.00 / 1.40
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 47245 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
7/8 5.9 1.50 Stab HPW -.013 NBS 13 0.00 |  |  |  | PPM800035 |  | 8 | 2 |  |  |  | 37.47 | 38.97
Nortrak Stabilizer (BFF) 0.00 |  |  |  | GT801175 |  | 13 | 2.875 |  |  |  | 7.87 | 46.84
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | GT80-10-648 |  | 8 | 3.25 |  |  |  | 9.99 | 56.83
UBHO Sub 0.00 |  |  |  | 775234 |  | 7.75 | 2.875 |  |  |  | 3.96 | 60.79
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT80-30-171 |  | 8 | 3.25 |  |  |  | 29.64 | 90.43
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT80-30-378 |  | 7.938 | 3.25 |  |  |  | 29.59 | 120.02
Crossover Sub 0.00 |  |  |  | GT7746831 |  | 7.688 | 3.25 |  |  |  | 3.17 | 123.19
11 Jts 5" HWDP 0.00 |  |  |  | Rig1 |  | 5 | 3 |  |  |  | 334.01 | 457.2
-1.00 | [11 empty] | 457.2
Additional Comments
Reason POOH ? TD Surface How did motor drain ? Motor drained as it should. While spinning bit box with rotary table, no abnormal sounds were heard or movement observed. Visual wear ? Slight wear observed to stabilizer on bottom side of motor. Run Description ? BHA drilled good. Minimum amount of sliding compared to some surface wells in the past. Averaging 15 ? 20? slides. Assembly maintained well in rotation, no drop seen. Max temp on run - 104 Degrees How Many Stalls and what pressure was seen on stalls ? 0 stalls Motor Yields ? 8/100 Max Drilling Diff - 800 psi Average Drilling Diff - 500 psi Condition of bit on surface - 0-0-NO-A-X-I-NO-TD
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Well: |  | Mill H08
|  |  |  | Longitude: |  | 96° 43' 1.095" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 109.40/181.12/226.40
Date In: |  | 02/02/2022 20:00 |  | SN: |  | MTR775009 |  |  |  | WOB Rotate (klbs): |  | 31.00
Date Out: |  | 02/04/2022 22:00 |  | Description: |  | 7/8 5.9 2.0 TS HPW -.012 |  |  |  | WOB Slide (klbs): |  | 18.42
Depth In/Out(Usft): |  | 2828.00 / 10230.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 77.41
Inc In/Out: |  | 10.34 / 22.67 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 863.07
Azi In/Out: |  | 70.70 / 138.02 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 4472.58
Total Drilled (Usft): |  | 7402 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4900.25
%Slide (Ftg): |  | 9.20 |  | Bit to Bend (Usft): |  | 6.04 |  |  |  | Tq On Btm (kftlbs): |  | 12.25
%Slide (Time): |  | 39.64 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 681 |  | Bearing Gap (in): |  | 0.08 |  |  |  | Avg Diff Press (psi): |  | 900
Slide Hours: |  | 10.67 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 90.80 |  | Kickpad OD (in): |  | 8.35 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 60.37 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6721 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 16.25 |  | Length (Usft): |  | 37.54 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 26.92 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 7.85 / 50.00 |  | Rev per Gal: |  | 0.155 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 63.82 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-WT-A-X-I-NO-TD
Rot ROP (Usft/hr): |  | 413.6 |  | Stator Vendor/Type/Fit: |  | Abaco / HPW / -0.012 |  |  |  | Drill Hrs: |  | 26.92
Avg ROP (Usft/hr): |  | 274.96 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 7.85
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
27 / 17 | 12 / 8 | 4 / 3 |  | 69.00 |  | 10 | 7 | 8.9 |  | OBM | 6.9 | 0.1
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
65 | 61 | [10 empty] | 0.00 / 7.97
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 59253 |  | 9.875 | 2 |  |  |  | 1.5 | 1.5
7/8 5.9 2.0 TS HPW -.012 0.00 |  |  |  | MTR775009 |  | 8 | 2 |  |  |  | 37.54 | 39.04
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | GT80-10-648 |  | 8 | 3.25 |  |  |  | 9.99 | 49.03
UBHO Sub 0.00 |  |  |  | 775234 |  | 7.75 | 2.875 |  |  |  | 3.96 | 52.99
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT80-30-171 |  | 8 | 3.25 |  |  |  | 29.64 | 82.63
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | GT80-30-378 |  | 7.938 | 3.25 |  |  |  | 29.59 | 112.22
Crossover Sub 0.00 |  |  |  | GT8046294 |  | 7.938 | 3 |  |  |  | 3.18 | 115.4
6 Jts 6 1/2in DC 0.00 |  |  |  | 6DC |  | 6.5 | 3 |  |  |  | 186.19 | 301.59
Crossover Sub 0.00 |  |  |  | GT6744684 |  | 6.688 | 2.812 |  |  |  | 3.2 | 304.79
11 Jts 5 HWDP 0.00 |  |  |  | Rig1 |  | 5 | 3 |  |  |  | 334.01 | 638.8
22 Stds 5in DP 0.00 |  |  |  | Rig2 |  | 5 | 3 |  |  |  | 2065.88 | 2704.68
Agitator 0.00 |  |  |  | PG675-0050 |  | 6.75 | 2.5 |  |  |  | 22.46 | 2727.14
0.00 | [11 empty] | 2727.14
Additional Comments
Reason POOH ? TD Intermediate How did motor drain ? Motor drained as it should. While spinning bit box with rotary table, no abnormal sounds were heard or movement observed. About ?? squat seen in bearing play Visual wear ? No abnormal wear seen on motor. Run Description ? BHA drilled good. Had small maintenance slide in the intermediate due to a short tangent. Once we got into the pecan gap, motor didn?t yield great and became ratty sliding. In the intermediate curve, motor yielded 8?s and only had a few ratty spots while sliding. Max temp on run - 226 Degrees How Many Stalls and what pressure was seen on stalls ? 0 stalls Motor Yields ? 8/100 Max Drilling Diff - 1000 psi Average Drilling Diff - 700 psi Condition of bit on surface - 1-1-WT-A-X-I-NO-TD
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Well: |  | Mill H08
|  |  |  | Longitude: |  | 96° 43' 1.095" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 129.20/226.26/293.00
Date In: |  | 03/17/2022 14:45 |  | SN: |  | PPM250003 |  |  |  | WOB Rotate (klbs): |  | 27.00
Date Out: |  | 03/23/2022 12:45 |  | Description: |  | 5.5 6/7 8.8 2.12 TS HS88 +.002 |  |  |  | WOB Slide (klbs): |  | 34.38
Depth In/Out(Usft): |  | 10230.00 / 17890.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 70.00 / 59.87
Inc In/Out: |  | 22.68 / 86.66 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 399.12
Azi In/Out: |  | 138.02 / 134.61 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3967.54
Total Drilled (Usft): |  | 7660 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4446.25
%Slide (Ftg): |  | 16.57 |  | Bit to Bend (Usft): |  | 4.11 |  |  |  | Tq On Btm (kftlbs): |  | 13.33
%Slide (Time): |  | 38.44 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1269 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 900
Slide Hours: |  | 22.08 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 83.43 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 61.55 |  | Body OD (in): |  | 5.25 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 6391 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 35.35 |  | Length (Usft): |  | 33.26 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 57.43 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 25.80 / 142.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 57.47 |  | # Stalls / Pressure: |  | 5 / 1300.00 |  |  |  | Grade Out: |  | 1-1-CT-S-X-I-NO-DMF
Rot ROP (Usft/hr): |  | 180.79 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.002 |  |  |  | Drill Hrs: |  | 57.43
Avg ROP (Usft/hr): |  | 133.38 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 25.80
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  |  |  | 1 | 1 | 8.4 | 600 | Water | 0.4 | 0.1
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [8 empty] | 8 |  | 13.00 / 13.10
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13685101 |  | 6.75 | 2 |  |  |  | 1 | 1
5.5 6/7 8.8 2.12 TS HS88 +.002 0.00 |  |  |  | PPM250003 |  | 5.25 | 2 |  |  |  | 33.26 | 34.26
BTI 0.00 |  |  |  | BTI02 |  | 4.875 | 2.25 |  |  |  | 1.65 | 35.91
Non Mag Pony Collar 0.00 |  |  |  | GT50-10-465 |  | 5 | 2.75 |  |  |  | 9.46 | 45.37
UBHO Sub 0.00 |  |  |  | 500065 |  | 5.25 | 2.5 |  |  |  | 4 | 49.37
Non Mag Drill Collar 0.00 |  |  |  | GT50-30-707 |  | 5 | 2.688 |  |  |  | 31.38 | 80.75
Non Mag Pony Collar 0.00 |  |  |  | GT50-10-585 |  | 5 | 2.75 |  |  |  | 9.34 | 90.09
Non Mag Drill Collar 0.00 |  |  |  | GT50-30-722 |  | 5 | 2.688 |  |  |  | 31.42 | 121.51
ToMax 0.00 |  |  |  | A52180 |  | 5 | 2.75 |  |  |  | 17.57 | 139.08
Crossover 0.00 |  |  |  | GT52331433 |  | 5.312 | 2.688 |  |  |  | 3.63 | 142.71
28 Stands DP 0.00 |  |  |  | Rig28 |  | 4.5 | 2.5 |  |  |  | 2639.82 | 2782.53
Agitator 0.00 |  |  |  | PG525-0056 |  | 5.25 | 2.5 |  |  |  | 21.26 | 2803.79
-1.00 | [11 empty] | 2803.79
Additional Comments
Reason POOH ? Motor Incident How did motor drain ? Motor was dry on surface, no abnormal noises were heard. Visual wear ? No visual damage. 1/8? squat and 1? play in rotation by hand Run Description ? Built curve and drilled into lateral. Motor yielded 9-15 throughout curve and held consistent TF. Drilled well throughout lateral with build trend during rotation, some sporadic azimuth trends associated with formation seen. Had to POOH from 12,612? to 8500? due to wash out in drill pipe before tripping back to bottom and drilling ahead to 13,755? and POOH to shoe after fire on shale shakers. Tripped back to bottom and drilled ahead in lateral to 17,817? where repairs to IBOP were required. Pipe was rotated during rig repair for 10 hours without circulation. Drilled down to 17,878? after repairs, where the motor began micro stalling 4-5 times in a row. Decision was made by Co Man and DE to POOH Max temp on run ? 293? How Many Stalls and what pressure was seen on stalls ? 5 stalls up to 1300 psi Motor Yields ?15?/100 Max Drilling Diff - 1000 psi Average Drilling Diff - 800 Condition of bit on surface - 1-1-CT-S-X-I-NO-DMF
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1105822 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31194 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 11' 19.822" N |  |  | Well: |  | Mill H08
|  |  |  | Longitude: |  | 96° 43' 1.095" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 136.00/159.00/246.00
Date In: |  | 03/23/2022 19:30 |  | SN: |  | PPM250005 |  |  |  | WOB Rotate (klbs): |  | 25.00
Date Out: |  | 03/25/2022 23:30 |  | Description: |  | 5.5 6/7 8.8 2.12 TS HS88 -.004 |  |  |  | WOB Slide (klbs): |  | 25.00
Depth In/Out(Usft): |  | 17890.00 / 19429.04 |  | Make: |  | PDCI |  |  |  | RPM: |  | 70.00 / 63.00
Inc In/Out: |  | 86.65 / 85.32 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 380.26
Azi In/Out: |  | 134.61 / 133.88 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4559.19
Total Drilled (Usft): |  | 1539.04 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5419.65
%Slide (Ftg): |  | 7.80 |  | Bit to Bend (Usft): |  | 4.1 |  |  |  | Tq On Btm (kftlbs): |  | 13.77
%Slide (Time): |  | 23.07 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 120 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi): |  | 900
Slide Hours: |  | 2.68 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.20 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 76.96 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 1419.04 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 8.94 |  | Length (Usft): |  | 33.16 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 11.62 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 8.88 / 52.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 44.78 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 3-3-CT-N-X-I-LT-TD
Rot ROP (Usft/hr): |  | 158.73 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / -0.004 |  |  |  | Drill Hrs: |  | 11.62
Avg ROP (Usft/hr): |  | 132.45 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 8.88
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
3 / 2 | 1 / 1 | 1 / 1 |  |  |  | 1 | 1 | 8.4 | 600 | Water | 0.4 | 0.1
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
64 | 55 | [10 empty] | 0.00 / 4.48
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618579 |  | 6.75 | 2 |  |  |  | 1 | 1
5.5 6/7 8.8 2.12 TS HS88 -.004 0.00 |  |  |  | PPM250005 |  | 5 | 2 |  |  |  | 33.16 | 34.16
BTI 0.00 |  |  |  | BTI03 |  | 4.875 | 2.25 |  |  |  | 2.11 | 36.27
Non Mag Pony Collar 0.00 |  |  |  | GT50-10-465 |  | 5 | 2.75 |  |  |  | 9.46 | 45.73
UBHO Sub 0.00 |  |  |  | 500065 |  | 5.25 | 2.5 |  |  |  | 4 | 49.73
Non Mag Drill Collar 0.00 |  |  |  | GT50-30-707 |  | 5 | 2.688 |  |  |  | 31.38 | 81.11
Non Mag Drill Collar 0.00 |  |  |  | GT50-30-722 |  | 5 | 2.688 |  |  |  | 31.42 | 112.53
ToMax 0.00 |  |  |  | A52180 |  | 5 | 2.75 |  |  |  | 17.57 | 130.1
Crossover 0.00 |  |  |  | GT52331433 |  | 5.312 | 2.688 |  |  |  | 3.63 | 133.73
28 Stands DP 0.00 |  |  |  | Rig28 |  | 4.5 | 2.5 |  |  |  | 2639.82 | 2773.55
Agitator 0.00 |  |  |  | PG525-0037 |  | 5.312 | 2.5 |  |  |  | 21.17 | 2794.72
-1.00 | [11 empty] | 2794.72
Additional Comments
Reason POOH ? TD How did motor drain ? Motor was dry on surface, no abnormal noises were heard. Visual wear ? No visual damage. Run Description ? Motor drilled well from 17,890? to TD at 19,429?. Slid well with much less torque required after tripping. Held consistent toolface. Averaged 800 diff while drilling with 150-250 ROP during rotation. Max temp on run ? 246? How Many Stalls and what pressure was seen on stalls ?0 Motor Yields ?15?/100 Max Drilling Diff - 1000 psi Average Drilling Diff - 800 Condition of bit on surface - 3-3-CT-N-X-I-LT-TD
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 370 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2720
Site: |  |  |  |  | Klondike - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 207
Well Name: |  |  |  |  | Mill H08 |  |  | Survey / Gamma Offset: |  |  |  |  | 75.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 370 |  | VS Azimuth: |  | 134.53 |  | Rotate: |  | 2513
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
02/01/2022 | 11:20 | 11:35 | 0.25 | 108 | 183 | 75 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 2; Drilling Parameters ROP: 300 | 450 | 350 | 100 | 75 | 55 | 55 | 55
02/01/2022 | 11:41 | 11:52 | 0.18333 | 183 | 274 | 91 | Rotate |  | 199 | 0.46 | 81.51 | 199 | 0.12 | 0.79 | 0.12 | 0.23 |  |  | 5 | 50 | 500 | 4 | 496.36 | 550 | 450 | 100 | 75 | 55 | 55 | 55
02/01/2022 | 12:55 | 13:05 | 0.16667 | 274 | 366 | 92 | Rotate |  | 291 | 0.77 | 109.25 | 290.99 | -0.03 | 1.74 | -0.03 | 0.46 |  |  | 5 | 60 | 600 | 5 | 552 | 750 | 600 | 150 | 80 | 70 | 70 | 70
02/01/2022 | 13:11 | 13:19 | 0.13333 | 366 | 457 | 91 | Rotate |  | 382 | 0.29 | 132.43 | 381.99 | -0.39 | 2.49 | -0.39 | 0.57 |  |  | 8 | 70 | 700 | 7 | 682.5 | 1000 | 800 | 200 | 80 | 70 | 70 | 70
02/01/2022 | 13:23 | 13:30 | 0.11667 | 457 | 551 | 94 | Rotate |  | 476 | 0.7 | 80.86 | 475.99 | -0.46 | 3.23 | -0.46 | 0.6 |  |  | 15 | 80 | 800 | 7 | 805.71 | 1300 | 1100 | 200 | 82.4 | 75 | 75 | 75
02/01/2022 | 13:35 | 13:38 | 0.05 | 551 | 566 | 15 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 90; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6; Drilling Parameters ROP: 300 | 1750 | 1500 | 250 | 82.4 | 75 | 75 | 75
02/01/2022 | 13:38 | 13:41 | 0.05 | 566 | 581 | 15 | Slide | 0 | 570 | 1.05 | 77.25 | 569.97 | -0.18 | 4.64 | -0.18 | 0.38 |  |  | 5 |  | 900 |  | 300 | 1600 | 1500 | 100 | 82.4 | 75 | 75 | 75
02/01/2022 | 13:41 | 13:45 | 0.066667 | 581 | 645 | 64 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 90; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6; Drilling Parameters ROP: 960 | 1750 | 1500 | 250 | 82.4 | 75 | 75 | 75
02/01/2022 | 13:51 | 13:56 | 0.083333 | 645 | 739 | 94 | Rotate |  | 664 | 1.86 | 55.73 | 663.94 | 0.87 | 6.74 | 0.87 | 1.03 |  |  | 18 | 100 | 900 | 8.8 | 1128 | 1900 | 1500 | 400 | 82.4 | 80 | 80 | 80
02/01/2022 | 14:02 | 14:07 | 0.083333 | 739 | 833 | 94 | Rotate |  | 758 | 1.96 | 70.25 | 757.89 | 2.27 | 9.51 | 2.27 | 0.52 |  |  | 20 | 100 | 900 | 8.8 | 1128 | 1900 | 1500 | 400 | 82.4 | 80 | 80 | 80
02/01/2022 | 14:13 | 14:15 | 0.033333 | 833 | 848 | 15 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8.8; Drilling Parameters ROP: 450 | 1900 | 1500 | 400 | 82.4 | 82 | 80 | 78
02/01/2022 | 14:15 | 14:18 | 0.05 | 848 | 868 | 20 | Slide | 0 | 851 | 2.2 | 66.2 | 850.83 | 3.53 | 12.64 | 3.53 | 0.3 |  |  | 5 |  | 900 |  | 400 | 1700 | 1500 | 200 | 82.4 | 82 | 80 | 78
02/01/2022 | 14:18 | 14:21 | 0.05 | 868 | 926 | 58 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8.8; Drilling Parameters ROP: 1160 | 1900 | 1500 | 400 | 82.4 | 82 | 80 | 78
02/01/2022 | 14:26 | 14:31 | 0.083333 | 926 | 1020 | 94 | Rotate |  | 945 | 3.15 | 59.21 | 944.73 | 5.58 | 16.51 | 5.58 | 1.07 |  |  | 25 | 100 | 900 | 8.8 | 1128 | 1900 | 1500 | 400 | 82.4 | 82 | 80 | 78
02/01/2022 | 14:36 | 14:38 | 0.033333 | 1020 | 1035 | 15 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8.8; Drilling Parameters ROP: 450 | 1900 | 1600 | 300 | 82.4 | 90 | 88 | 86
02/01/2022 | 14:38 | 14:42 | 0.066667 | 1035 | 1055 | 20 | Slide | 0 | 1039 | 4.02 | 58.68 | 1038.54 | 8.62 | 21.54 | 8.62 | 0.93 |  |  | 5 |  | 900 |  | 300 | 1700 | 1600 | 100 | 82.4 | 90 | 88 | 86
02/01/2022 | 14:42 | 14:45 | 0.05 | 1055 | 1114 | 59 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8.8; Drilling Parameters ROP: 1180 | 1900 | 1600 | 300 | 82.4 | 90 | 88 | 86
02/01/2022 | 14:50 | 14:56 | 0.1 | 1114 | 1207 | 93 | Rotate |  | 1132 | 4.91 | 63.18 | 1131.26 | 12.11 | 27.88 | 12.11 | 1.03 |  |  | 15 | 100 | 900 | 7.2 | 930 | 1900 | 1600 | 300 | 82.4 | 90 | 88 | 86
02/01/2022 | 15:02 | 15:09 | 0.11667 | 1207 | 1302 | 95 | Rotate |  | 1227 | 4.48 | 66.74 | 1225.94 | 15.41 | 34.92 | 15.41 | 0.55 |  |  | 15 | 100 | 900 | 7.2 | 814.29 | 2000 | 1600 | 400 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:14 | 15:16 | 0.033333 | 1302 | 1313 | 11 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 7.2; Drilling Parameters ROP: 330 | 2000 | 1600 | 400 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:16 | 15:19 | 0.05 | 1313 | 1333 | 20 | Slide | 0 | 1320 | 5.18 | 66.39 | 1318.61 | 18.52 | 42.1 | 18.52 | 0.75 |  |  | 8 |  | 900 |  | 400 | 1700 | 1600 | 100 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:19 | 15:23 | 0.066667 | 1333 | 1395 | 62 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8.2; Drilling Parameters ROP: 930 | 2000 | 1600 | 400 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:29 | 15:32 | 0.05 | 1395 | 1415 | 20 | Rotate |  | 1414 | 6.48 | 68.4 | 1412.12 | 22.18 | 50.92 | 22.18 | 1.4 |  |  | 10 | 100 | 900 | 8.2 | 400 | 2000 | 1600 | 400 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:32 | 15:35 | 0.05 | 1415 | 1430 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 300 | 1750 | 1600 | 150 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:35 | 15:40 | 0.083333 | 1430 | 1489 | 59 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8.2; Drilling Parameters ROP: 708 | 2000 | 1700 | 300 | 87.8 | 90 | 88 | 86
02/01/2022 | 15:46 | 15:52 | 0.1 | 1489 | 1583 | 94 | Rotate |  | 1508 | 7.04 | 69.82 | 1505.47 | 26.12 | 61.26 | 26.12 | 0.62 |  |  | 20 | 100 | 900 | 9.3 | 940 | 2000 | 1700 | 300 | 87.8 | 95 | 90 | 88
02/01/2022 | 15:57 | 15:59 | 0.033333 | 1583 | 1595 | 12 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 9.3; Drilling Parameters ROP: 360 | 2000 | 1700 | 300 | 87.8 | 95 | 90 | 88
02/01/2022 | 15:59 | 16:03 | 0.066667 | 1595 | 1615 | 20 | Slide | 0 | 1602 | 7.44 | 68.98 | 1598.72 | 30.29 | 72.35 | 30.29 | 0.44 |  |  | 8 |  | 900 |  | 300 | 1800 | 1700 | 100 | 87.8 | 105 | 100 | 98
02/01/2022 | 16:03 | 16:07 | 0.066667 | 1615 | 1677 | 62 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 9.3; Drilling Parameters ROP: 930 | 2000 | 1700 | 300 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:13 | 16:15 | 0.033333 | 1677 | 1695 | 18 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 9.3; Drilling Parameters ROP: 540 | 2000 | 1700 | 300 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:15 | 16:18 | 0.05 | 1695 | 1710 | 15 | Slide | 0 | 1696 | 8.21 | 73.34 | 1691.84 | 34.39 | 84.46 | 34.39 | 1.03 |  |  | 10 |  | 900 |  | 300 | 1850 | 1700 | 150 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:18 | 16:21 | 0.05 | 1710 | 1771 | 61 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 1220 | 2100 | 1700 | 400 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:28 | 16:30 | 0.033333 | 1771 | 1789 | 18 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 540 | 1900 | 1700 | 200 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:30 | 16:34 | 0.066667 | 1789 | 1809 | 20 | Slide | 0 | 1789 | 8.92 | 78.57 | 1783.81 | 37.73 | 97.89 | 37.73 | 1.13 |  |  | 12 |  | 900 |  | 300 | 1900 | 1700 | 200 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:34 | 16:38 | 0.066667 | 1809 | 1864 | 55 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 825 | 2100 | 1700 | 400 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:44 | 16:51 | 0.11667 | 1864 | 1958 | 94 | Rotate |  | 1883 | 9.81 | 80.41 | 1876.55 | 40.5 | 112.93 | 40.5 | 1 |  |  | 25 | 100 | 900 | 10.1 | 805.71 | 2200 | 1800 | 400 | 93.2 | 105 | 100 | 98
02/01/2022 | 16:57 | 17:00 | 0.05 | 1958 | 1977 | 19 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 380 | 2200 | 1800 | 400 | 93.2 | 105 | 100 | 98
02/01/2022 | 17:00 | 17:05 | 0.083333 | 1977 | 1992 | 15 | Slide | 0 | 1977 | 9.49 | 77.26 | 1969.22 | 43.55 | 128.38 | 43.55 | 0.66 |  |  | 12 |  | 900 |  | 180 | 2000 | 1800 | 200 | 93.2 | 105 | 100 | 98
02/01/2022 | 17:05 | 17:10 | 0.083333 | 1992 | 2052 | 60 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 720 | 2300 | 1800 | 500 | 93.2 | 105 | 100 | 98
02/01/2022 | 17:16 | 17:19 | 0.05 | 2052 | 2072 | 20 | Rotate |  | 2071 | 10.1 | 76.52 | 2061.85 | 47.18 | 143.96 | 47.18 | 0.66 |  |  | 15 | 100 | 900 | 10.1 | 400 | 2100 | 1800 | 300 | 96.8 | 105 | 100 | 98
02/01/2022 | 17:19 | 17:23 | 0.066667 | 2072 | 2087 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 225 | 2000 | 1800 | 200 | 96.8 | 105 | 100 | 98
02/01/2022 | 17:23 | 17:27 | 0.066667 | 2087 | 2146 | 59 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 885 | 2200 | 1800 | 400 | 96.8 | 105 | 100 | 98
02/01/2022 | 17:32 | 17:38 | 0.1 | 2146 | 2239 | 93 | Rotate |  | 2164 | 10.61 | 73.48 | 2153.34 | 51.51 | 160.09 | 51.51 | 0.8 |  |  | 22 | 100 | 900 | 10.1 | 930 | 2200 | 1800 | 400 | 96.8 | 105 | 100 | 98
02/01/2022 | 17:43 | 17:49 | 0.1 | 2239 | 2334 | 95 | Rotate |  | 2259 | 10.52 | 70.1 | 2246.73 | 56.95 | 176.63 | 56.95 | 0.66 |  |  | 25 | 100 | 900 | 10.1 | 950 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 17:54 | 17:58 | 0.066667 | 2334 | 2354 | 20 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 300 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 17:58 | 18:02 | 0.066667 | 2354 | 2371 | 17 | Slide | 0 | 2354 | 10.87 | 70.46 | 2340.08 | 62.9 | 193.23 | 62.9 | 0.38 |  |  | 15 |  | 900 |  | 255 | 2000 | 1800 | 200 | 96.8 | 115 | 105 | 100
02/01/2022 | 18:02 | 18:06 | 0.066667 | 2371 | 2429 | 58 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 870 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 18:12 | 18:18 | 0.1 | 2429 | 2523 | 94 | Rotate |  | 2448 | 11.29 | 71.19 | 2432.33 | 68.83 | 210.29 | 68.83 | 0.47 |  |  | 25 | 100 | 900 | 10.1 | 940 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 18:22 | 18:29 | 0.11667 | 2523 | 2617 | 94 | Rotate |  | 2542 | 11.48 | 69.56 | 2524.48 | 75.06 | 227.77 | 75.06 | 0.4 |  |  | 25 | 100 | 900 | 10.1 | 805.71 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 18:33 | 18:35 | 0.033333 | 2617 | 2627 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 300 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 18:35 | 18:40 | 0.083333 | 2627 | 2642 | 15 | Slide | 0 | 2635 | 10.72 | 69.8 | 2615.74 | 81.28 | 244.56 | 81.28 | 0.82 |  |  | 25 | 100 | 900 | 10.1 | 180 | 2200 | 1800 | 400 | 96.8 | 115 | 105 | 100
02/01/2022 | 18:40 | 18:44 | 0.066667 | 2642 | 2710 | 68 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 1020 | 2200 | 1800 | 400 | 102.2 | 115 | 105 | 100
02/01/2022 | 18:48 | 18:56 | 0.13333 | 2710 | 2804 | 94 | Rotate |  | 2729 | 10.55 | 72.71 | 2708.12 | 86.86 | 260.98 | 86.86 | 0.6 |  |  | 25 | 100 | 900 | 10.1 | 705 | 2200 | 1800 | 400 | 102.2 | 115 | 105 | 100
02/01/2022 | 19:02 | 19:04 | 0.033333 | 2804 | 2828 | 24 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10.1; Drilling Parameters ROP: 720 | 2200 | 1800 | 400 | 102.2 | 115 | 105 | 100

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 370 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7402
Site: |  |  |  |  | Klondike - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 681
Well Name: |  |  |  |  | Mill H08 |  |  | Survey / Gamma Offset: |  |  |  |  | 65.00 / 61.00 |  |  |  |  | Grid Conv: |  |  |  | 370 |  | VS Azimuth: |  | 134.53 |  | Rotate: |  | 6721
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
02/03/2022 | 02:01 | 02:05 | 0.066667 | 2828 | 2838 | 10 | Rotate | Drilling Parameters WOB: 11; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 477; Drilling Parameters Tq: 2.6; Drilling Parameters ROP: 150 | 1695 | 1609 | 86 | 109.4 | 102 | 102 | 102
02/03/2022 | 02:42 | 03:06 | 0.4 | 2838 | 2914 | 76 | Rotate |  | 2849 | 10.3 | 70.26 | 2826.14 | 93.75 | 281.57 | 93.75 | 0.42 |  |  | 12 | 35 | 548 | 2.4 | 190 | 1925 | 1850 | 75 | 109.4 | 102 | 102 | 102
02/03/2022 | 03:10 | 03:31 | 0.35 | 2914 | 3008 | 94 | Rotate |  | 2943 | 10.76 | 68.88 | 2918.56 | 99.75 | 297.66 | 99.75 | 0.56 |  |  | 7.93 | 65 | 720 | 3.59 | 268.57 | 3113 | 2825 | 288 | 109.4 | 102 | 102 | 102
02/03/2022 | 03:36 | 03:39 | 0.05 | 3008 | 3018 | 10 | Rotate | Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 75; Drilling Parameters FLOW: 807; Drilling Parameters Tq: 4.6; Drilling Parameters ROP: 200 | 3850 | 3620 | 230 | 122 | 105 | 105 | 105
02/03/2022 | 03:39 | 03:44 | 0.083333 | 3018 | 3030 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 11; Drilling Parameters FLOW: 807; Drilling Parameters Tq: 4.6; Drilling Parameters ROP: 144 | 3850 | 3620 | 230 | 122 | 105 | 105 | 105
02/03/2022 | 03:44 | 03:58 | 0.23333 | 3030 | 3102 | 72 | Rotate |  | 3037 | 9.13 | 70.78 | 3011.14 | 105.37 | 312.89 | 105.37 | 1.77 |  |  | 7.93 | 75 | 807 | 4.6 | 308.57 | 3850 | 3620 | 230 | 122 | 105 | 105 | 105
02/03/2022 | 04:03 | 04:22 | 0.31667 | 3102 | 3196 | 94 | Rotate |  | 3131 | 9.1 | 69.17 | 3103.96 | 110.46 | 326.88 | 110.46 | 0.27 |  |  | 7.93 | 80 | 853 | 4.6 | 296.84 | 3850 | 3650 | 200 | 122 | 105 | 105 | 105
02/03/2022 | 04:27 | 04:39 | 0.2 | 3196 | 3290 | 94 | Rotate |  | 3225 | 9.05 | 67.6 | 3196.78 | 115.92 | 340.66 | 115.92 | 0.27 |  |  | 7.93 | 80 | 891 | 5.2 | 470 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 04:42 | 04:45 | 0.05 | 3290 | 3300 | 10 | Rotate | Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 200 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 04:45 | 04:51 | 0.1 | 3300 | 3315 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 150 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 04:51 | 05:00 | 0.15 | 3315 | 3384 | 69 | Rotate |  | 3319 | 10.24 | 72.17 | 3289.45 | 121.3 | 355.45 | 121.3 | 1.5 |  |  | 7.93 | 80 | 891 | 5.2 | 460 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:03 | 05:06 | 0.05 | 3384 | 3394 | 10 | Rotate | Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 200 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:06 | 05:12 | 0.1 | 3394 | 3409 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 150 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:12 | 05:20 | 0.13333 | 3409 | 3479 | 70 | Rotate |  | 3414 | 9.7 | 79.66 | 3383.02 | 125.32 | 371.36 | 125.32 | 1.48 |  |  | 7.93 | 80 | 891 | 5.2 | 525 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:24 | 05:27 | 0.05 | 3479 | 3489 | 10 | Rotate | Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 200 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:27 | 05:31 | 0.066667 | 3489 | 3501 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 180 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:31 | 05:37 | 0.1 | 3501 | 3572 | 71 | Rotate |  | 3507 | 8.07 | 82.92 | 3474.9 | 127.53 | 385.55 | 127.53 | 1.83 |  |  | 7.93 | 80 | 891 | 5.2 | 710 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:41 | 05:49 | 0.13333 | 3572 | 3667 | 95 | Rotate |  | 3602 | 8.12 | 84.59 | 3568.96 | 128.99 | 398.85 | 128.99 | 0.25 |  |  | 7.93 | 80 | 891 | 5.2 | 712.5 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:53 | 05:55 | 0.033333 | 3667 | 3677 | 10 | Rotate | Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 300 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 05:55 | 06:00 | 0.083333 | 3677 | 3689 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 7.93; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.2; Drilling Parameters ROP: 144 | 4320 | 4070 | 250 | 122 | 107 | 107 | 107
02/03/2022 | 06:00 | 06:07 | 0.11667 | 3689 | 3761 | 72 | Rotate |  | 3696 | 6.89 | 85.64 | 3662.15 | 130.04 | 411.08 | 130.04 | 1.32 |  |  | 40 | 80 | 891 | 9.8 | 617.14 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:09 | 06:17 | 0.13333 | 3761 | 3855 | 94 | Rotate |  | 3790 | 6.87 | 85.9 | 3755.47 | 130.87 | 422.31 | 130.87 | 0.04 |  |  | 40 | 80 | 891 | 9.8 | 705 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:20 | 06:22 | 0.033333 | 3855 | 3867 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 9.8; Drilling Parameters ROP: 360 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:22 | 06:27 | 0.083333 | 3867 | 3879 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 891; Drilling Parameters ROP: 144 | 4500 | 4300 | 200 | 160 | 155 | 148 | 140
02/03/2022 | 06:27 | 06:32 | 0.083333 | 3879 | 3949 | 70 | Rotate |  | 3884 | 6.02 | 89.23 | 3848.88 | 131.34 | 432.85 | 131.34 | 0.99 |  |  | 40 | 80 | 891 | 9.8 | 840 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:35 | 06:38 | 0.05 | 3949 | 3961 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 9.8; Drilling Parameters ROP: 240 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:38 | 06:42 | 0.066667 | 3961 | 3973 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 891; Drilling Parameters ROP: 180 | 4500 | 4300 | 200 | 160 | 155 | 148 | 140
02/03/2022 | 06:42 | 06:48 | 0.1 | 3973 | 4043 | 70 | Rotate |  | 3978 | 5.28 | 74.48 | 3942.42 | 132.56 | 441.94 | 132.56 | 1.73 |  |  | 40 | 80 | 891 | 9.8 | 700 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:50 | 06:53 | 0.05 | 4043 | 4055 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 9.8; Drilling Parameters ROP: 240 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 06:53 | 06:57 | 0.066667 | 4055 | 4067 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 891; Drilling Parameters ROP: 180 | 4500 | 4300 | 200 | 160 | 155 | 148 | 140
02/03/2022 | 06:57 | 07:02 | 0.083333 | 4067 | 4137 | 70 | Rotate |  | 4072 | 3.64 | 71.62 | 4036.14 | 134.66 | 448.94 | 134.66 | 1.76 |  |  | 40 | 80 | 891 | 9.8 | 840 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 07:04 | 07:10 | 0.1 | 4137 | 4230 | 93 | Rotate |  | 4165 | 3.31 | 67.02 | 4128.97 | 136.64 | 454.22 | 136.64 | 0.46 |  |  | 40 | 80 | 891 | 9.8 | 930 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 07:14 | 07:17 | 0.05 | 4230 | 4242 | 12 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 9.8; Drilling Parameters ROP: 240 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 07:17 | 07:22 | 0.083333 | 4242 | 4257 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 891; Drilling Parameters ROP: 180 | 4400 | 4300 | 100 | 160 | 155 | 148 | 140
02/03/2022 | 07:22 | 07:27 | 0.083333 | 4257 | 4323 | 66 | Rotate |  | 4258 | 2.66 | 85.08 | 4221.84 | 137.88 | 458.84 | 137.88 | 1.22 |  |  | 38 | 80 | 891 | 9.8 | 792 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 07:29 | 07:32 | 0.05 | 4323 | 4335 | 12 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 9.8; Drilling Parameters ROP: 240 | 4700 | 4300 | 400 | 160 | 155 | 148 | 140
02/03/2022 | 07:32 | 07:38 | 0.1 | 4335 | 4350 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 891; Drilling Parameters ROP: 150 | 4500 | 4300 | 200 | 160 | 155 | 148 | 140
02/03/2022 | 07:38 | 07:43 | 0.083333 | 4350 | 4418 | 68 | Rotate |  | 4353 | 2.88 | 110.48 | 4316.73 | 137.23 | 463.27 | 137.23 | 1.3 |  |  | 40 | 80 | 891 | 9.8 | 816 | 4700 | 4300 | 400 | 160 | 155 | 157.23 | 140
02/03/2022 | 07:46 | 07:53 | 0.11667 | 4418 | 4511 | 93 | Rotate |  | 4446 | 2.67 | 109.69 | 4409.62 | 135.68 | 467.5 | 135.68 | 0.23 |  |  | 4 | 80.13 | 891 | 5.25 | 797.14 | 4700 | 4411.32 | 288.68 | 160 | 175 | 164.78 | 145
02/03/2022 | 07:56 | 07:59 | 0.05 | 4511 | 4525 | 14 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80.13; Drilling Parameters FLOW: 891; Drilling Parameters Tq: 5.25; Drilling Parameters ROP: 280 | 4700 | 4411.32 | 288.68 | 160 | 175 | 164.78 | 145
02/03/2022 | 07:59 | 08:04 | 0.083333 | 4525 | 4540 | 15 | Slide | TTF: 255.73; Drilling Parameters WOB: 2; Drilling Parameters FLOW: 891; Drilling Parameters ROP: 180 | 4700 | 4519.43 | 180.57 | 160 | 175 | 164.26 | 145
02/03/2022 | 08:04 | 08:10 | 0.1 | 4540 | 4605 | 65 | Rotate |  | 4540 | 1.64 | 142.98 | 4503.56 | 133.87 | 470.37 | 133.87 | 1.68 |  |  | 38 | 79.41 | 889.29 | 5.92 | 650 | 4518.11 | 4228.62 | 289.49 | 160 | 175 | 163.37 | 145
02/03/2022 | 08:12 | 08:21 | 0.15 | 4605 | 4699 | 94 | Rotate |  | 4634 | 1.01 | 173.24 | 4597.54 | 131.97 | 471.28 | 131.97 | 0.98 |  |  | 38 | 79.95 | 892.9 | 2.81 | 626.67 | 4456.23 | 4228.62 | 227.61 | 152.6 | 175 | 165.38 | 145
02/03/2022 | 08:25 | 08:34 | 0.15 | 4699 | 4793 | 94 | Rotate |  | 4728 | 0.79 | 149.92 | 4691.52 | 130.59 | 471.7 | 130.59 | 0.45 |  |  | 38 | 80.14 | 892.66 | 3.89 | 626.67 | 4836 | 4228.62 | 607.38 | 152.6 | 175 | 165.38 | 145
02/03/2022 | 08:37 | 08:45 | 0.13333 | 4793 | 4886 | 93 | Rotate |  | 4821 | 0.73 | 172.11 | 4784.52 | 129.45 | 472.1 | 129.45 | 0.32 |  |  | 27.61 | 80.15 | 890.63 | 9.34 | 697.5 | 4867.99 | 4307.66 | 560.33 | 159.8 | 175 | 165.38 | 145
02/03/2022 | 08:48 | 08:58 | 0.16667 | 4886 | 4980 | 94 | Rotate |  | 4915 | 0.54 | 158.64 | 4878.51 | 128.44 | 472.35 | 128.44 | 0.26 |  |  | 25.11 | 80.16 | 890.91 | 7.86 | 564 | 4782.77 | 4504.92 | 277.85 | 161.6 | 180 | 165.38 | 145
02/03/2022 | 09:01 | 09:10 | 0.15 | 4980 | 5074 | 94 | Rotate |  | 5009 | 0.16 | 179.76 | 4972.51 | 127.9 | 472.51 | 127.9 | 0.42 |  |  | 25.93 | 80.2 | 890.87 | 8.57 | 626.67 | 4817.63 | 4504.92 | 312.71 | 163.4 | 180 | 165.38 | 145
02/03/2022 | 09:13 | 09:22 | 0.15 | 5074 | 5169 | 95 | Rotate |  | 5104 | 0.42 | 283.87 | 5067.51 | 127.85 | 472.17 | 127.85 | 0.51 |  |  | 37.57 | 80.02 | 890.65 | 4.57 | 633.33 | 4817.63 | 4504.92 | 312.71 | 165.2 | 180 | 152.58 | 145
02/03/2022 | 09:26 | 09:36 | 0.16667 | 5169 | 5262 | 93 | Rotate |  | 5197 | 0.7 | 307.59 | 5160.5 | 128.28 | 471.39 | 128.28 | 0.38 |  |  | 32.2 | 80.22 | 891.4 | 5.53 | 558 | 4782.77 | 4307.66 | 475.11 | 167 | 180 | 152.58 | 145
02/03/2022 | 09:39 | 09:48 | 0.15 | 5262 | 5356 | 94 | Rotate |  | 5291 | 0.74 | 303.53 | 5254.5 | 128.96 | 470.43 | 128.96 | 0.07 |  |  | 33.21 | 80.22 | 891.31 | 9.93 | 626.67 | 4814.21 | 4328.6 | 485.61 | 168.8 | 200 | 173.57 | 160
02/03/2022 | 09:58 | 10:10 | 0.2 | 5356 | 5449 | 93 | Rotate |  | 5384 | 0.65 | 316.87 | 5347.49 | 129.68 | 469.57 | 129.68 | 0.2 |  |  | 33.68 | 80.17 | 891.29 | 7.04 | 465 | 4886.94 | 4344.22 | 542.72 | 172.4 | 200 | 173.67 | 160
02/03/2022 | 10:14 | 10:24 | 0.16667 | 5449 | 5542 | 93 | Rotate |  | 5477 | 0.67 | 328.26 | 5440.48 | 130.53 | 468.92 | 130.53 | 0.14 |  |  | 33.01 | 80.22 | 891.29 | 8.35 | 558 | 4922.69 | 4547.12 | 375.57 | 174.2 | 200 | 177.86 | 160
02/03/2022 | 10:27 | 10:38 | 0.18333 | 5542 | 5636 | 94 | Rotate |  | 5571 | 0.83 | 329.76 | 5534.48 | 131.58 | 468.29 | 131.58 | 0.17 |  |  | 35.54 | 80.25 | 891.29 | 9.77 | 512.73 | 5110.86 | 4516.03 | 594.83 | 176 | 205 | 177.86 | 165
02/03/2022 | 10:41 | 10:50 | 0.15 | 5636 | 5730 | 94 | Rotate |  | 5665 | 0.85 | 345.47 | 5628.47 | 132.85 | 467.77 | 132.85 | 0.25 |  |  | 36.5 | 80.26 | 891.29 | 8.17 | 626.67 | 5210.86 | 4516.03 | 694.83 | 177.8 | 210 | 177.86 | 165
02/03/2022 | 10:54 | 11:03 | 0.15 | 5730 | 5823 | 93 | Rotate |  | 5758 | 0.94 | 334.84 | 5721.45 | 134.2 | 467.27 | 134.2 | 0.2 |  |  | 33.65 | 80.29 | 891.29 | 9.44 | 620 | 5203.45 | 4516.03 | 687.42 | 177.8 | 210 | 177.86 | 165
02/03/2022 | 11:07 | 11:17 | 0.16667 | 5823 | 5916 | 93 | Rotate |  | 5851 | 1.17 | 317.36 | 5814.44 | 135.59 | 466.3 | 135.59 | 0.42 |  |  | 34.77 | 80.25 | 891.29 | 10.06 | 558 | 5106.28 | 4572.03 | 534.25 | 179.6 | 210 | 177.86 | 165
02/03/2022 | 11:21 | 11:31 | 0.16667 | 5916 | 6010 | 94 | Rotate |  | 5945 | 1.5 | 316.78 | 5908.41 | 137.2 | 464.81 | 137.2 | 0.35 |  |  | 35.64 | 80.25 | 891.29 | 11.87 | 564 | 5242.24 | 4572.03 | 670.21 | 181.4 | 210 | 180 | 165
02/03/2022 | 11:33 | 11:44 | 0.18333 | 6010 | 6103 | 93 | Rotate |  | 6038 | 1.62 | 320.04 | 6001.38 | 139.09 | 463.13 | 139.09 | 0.16 |  |  | 28.46 | 80.32 | 890.76 | 10.43 | 507.27 | 5178.55 | 4656.57 | 521.98 | 183.2 | 210 | 185.1 | 170
02/03/2022 | 11:47 | 11:57 | 0.16667 | 6103 | 6197 | 94 | Rotate |  | 6132 | 2.17 | 327.76 | 6095.33 | 141.61 | 461.33 | 141.61 | 0.64 |  |  | 31.82 | 80.28 | 890.14 | 10.72 | 564 | 5175.2 | 4746.36 | 428.84 | 185 | 210 | 188.71 | 170
02/03/2022 | 12:00 | 12:03 | 0.05 | 6197 | 6209 | 12 | Rotate | Drilling Parameters WOB: 31.82; Drilling Parameters RPM: 80.26; Drilling Parameters FLOW: 890.78; Drilling Parameters Tq: 9.05; Drilling Parameters ROP: 240 | 4802.66 | 4771.44 | 31.22 | 179.6 | 215 | 190.96 | 175
02/03/2022 | 12:03 | 12:15 | 0.2 | 6209 | 6224 | 15 | Slide | TTF: 199.06; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 891.08; Drilling Parameters ROP: 75 | 4781.38 | 4741.89 | 39.49 | 179.6 | 215 | 190.98 | 175
02/03/2022 | 12:15 | 12:23 | 0.13333 | 6224 | 6291 | 67 | Rotate |  | 6226 | 2.06 | 318.87 | 6189.26 | 144.39 | 459.27 | 144.39 | 0.37 |  |  | 31.82 | 80.24 | 890.43 | 10.13 | 502.5 | 5011.84 | 4600.87 | 410.97 | 179.6 | 215 | 191.78 | 180
02/03/2022 | 12:26 | 12:29 | 0.05 | 6291 | 6305 | 14 | Rotate | Drilling Parameters WOB: 31.82; Drilling Parameters RPM: 80.29; Drilling Parameters FLOW: 891.14; Drilling Parameters Tq: 8.95; Drilling Parameters ROP: 280 | 4803.32 | 4600.87 | 202.45 | 176 | 215 | 202.36 | 180
02/03/2022 | 12:29 | 12:38 | 0.15 | 6305 | 6320 | 15 | Slide | TTF: 105.62; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 890.61; Drilling Parameters ROP: 100 | 4803.32 | 4600.87 | 202.45 | 176 | 215 | 198.16 | 180
02/03/2022 | 12:38 | 12:47 | 0.15 | 6320 | 6385 | 65 | Rotate |  | 6320 | 0.91 | 308.58 | 6283.23 | 146.13 | 457.58 | 146.13 | 1.25 |  |  | 31.82 | 80.37 | 890.35 | 11.49 | 433.33 | 5092.67 | 4600.87 | 491.8 | 176 | 215 | 198.16 | 180
02/03/2022 | 12:50 | 13:01 | 0.18333 | 6385 | 6479 | 94 | Rotate |  | 6414 | 1.03 | 305.46 | 6377.22 | 147.09 | 456.3 | 147.09 | 0.14 |  |  | 40 | 80.1 | 890.98 | 9.08 | 512.73 | 4644.08 | 4600.87 | 43.21 | 176 | 220 | 194.43 | 180
02/03/2022 | 13:04 | 13:15 | 0.18333 | 6479 | 6573 | 94 | Rotate |  | 6508 | 1.28 | 311.57 | 6471.2 | 148.27 | 454.83 | 148.27 | 0.3 |  |  | 40 | 80.33 | 890.08 | 14.2 | 512.73 | 5314.6 | 4600.87 | 713.73 | 186.8 | 220 | 200 | 185
02/03/2022 | 13:18 | 13:28 | 0.16667 | 6573 | 6666 | 93 | Rotate |  | 6601 | 1.56 | 327.43 | 6564.17 | 150.03 | 453.37 | 150.03 | 0.52 |  |  | 40 | 80.24 | 890.22 | 14.2 | 558 | 5136.77 | 4700 | 436.77 | 188.6 | 220 | 200 | 185
02/03/2022 | 13:31 | 13:43 | 0.2 | 6666 | 6760 | 94 | Rotate |  | 6695 | 1.82 | 327.41 | 6658.13 | 152.37 | 451.88 | 152.37 | 0.28 |  |  | 40 | 80.34 | 889.95 | 11.36 | 470 | 5137.75 | 4700 | 437.75 | 194 | 220 | 203 | 190
02/03/2022 | 13:45 | 13:57 | 0.2 | 6760 | 6854 | 94 | Rotate |  | 6789 | 2.13 | 321.33 | 6752.07 | 154.99 | 449.98 | 154.99 | 0.4 |  |  | 40 | 80.34 | 889.95 | 15 | 470 | 5100 | 4700 | 400 | 194 | 220 | 203 | 192
02/03/2022 | 14:00 | 14:03 | 0.05 | 6854 | 6866 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 889.95; Drilling Parameters Tq: 15; Drilling Parameters ROP: 240 | 5100 | 4700 | 400 | 194 | 220 | 203 | 192
02/03/2022 | 14:03 | 14:19 | 0.26667 | 6866 | 6884 | 18 | Slide | 0 | 6883 | 1.5 | 334.19 | 6846.02 | 157.46 | 448.36 | 157.46 | 0.79 |  |  | 15 |  | 889.95 |  | 67.5 | 4900 | 4700 | 200 | 194 | 220 | 203 | 192
02/03/2022 | 14:19 | 14:27 | 0.13333 | 6884 | 6948 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 889.95; Drilling Parameters Tq: 15; Drilling Parameters ROP: 480 | 5300 | 4700 | 600 | 194 | 220 | 203 | 192
02/03/2022 | 14:30 | 14:33 | 0.05 | 6948 | 6960 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 889.95; Drilling Parameters Tq: 15; Drilling Parameters ROP: 240 | 5300 | 4700 | 600 | 194 | 220 | 203 | 192
02/03/2022 | 14:33 | 14:42 | 0.15 | 6960 | 6975 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 889.95; Drilling Parameters ROP: 100 | 5100 | 4700 | 400 | 194 | 220 | 203 | 192
02/03/2022 | 14:42 | 14:51 | 0.15 | 6975 | 7042 | 67 | Rotate |  | 6977 | 0.91 | 31.81 | 6940.01 | 159.2 | 448.21 | 159.2 | 1.35 |  |  | 40 | 80.34 | 889.95 | 15 | 446.67 | 5300 | 4700 | 600 | 194 | 220 | 203 | 192
02/03/2022 | 14:54 | 15:05 | 0.18333 | 7042 | 7136 | 94 | Rotate |  | 7071 | 0.9 | 34.78 | 7034 | 160.44 | 449.03 | 160.44 | 0.05 |  |  | 42 | 80.34 | 890 | 18.9 | 512.73 | 5450 | 4800 | 650 | 194 | 220 | 203 | 192
02/03/2022 | 15:07 | 15:20 | 0.21667 | 7136 | 7230 | 94 | Rotate |  | 7165 | 0.94 | 18.84 | 7127.98 | 161.78 | 449.7 | 161.78 | 0.27 |  |  | 42 | 80.34 | 890 | 18.9 | 433.85 | 5450 | 4800 | 650 | 198 | 220 | 203 | 192
02/03/2022 | 15:23 | 15:34 | 0.18333 | 7230 | 7324 | 94 | Rotate |  | 7259 | 1.05 | 8.11 | 7221.97 | 163.36 | 450.07 | 163.36 | 0.23 |  |  | 42 | 80.34 | 890 | 18.9 | 512.73 | 5450 | 4800 | 650 | 198 | 220 | 203 | 192
02/03/2022 | 15:37 | 15:49 | 0.2 | 7324 | 7417 | 93 | Rotate |  | 7352 | 1.1 | 18.66 | 7314.95 | 165.05 | 450.48 | 165.05 | 0.22 |  |  | 38 | 80.34 | 890 | 18.4 | 465 | 5550 | 4800 | 750 | 201 | 220 | 203 | 192
02/03/2022 | 15:52 | 16:05 | 0.21667 | 7417 | 7511 | 94 | Rotate |  | 7446 | 1.14 | 4.5 | 7408.93 | 166.84 | 450.84 | 166.84 | 0.3 |  |  | 38 | 80.34 | 890 | 19.2 | 433.85 | 5600 | 4800 | 800 | 203 | 220 | 203 | 192
02/03/2022 | 16:09 | 16:22 | 0.21667 | 7511 | 7605 | 94 | Rotate |  | 7540 | 1.3 | 347.03 | 7502.91 | 168.81 | 450.67 | 168.81 | 0.43 |  |  | 38 | 80.34 | 890 | 18 | 433.85 | 5550 | 4900 | 650 | 207 | 225 | 210 | 195
02/03/2022 | 16:25 | 16:28 | 0.05 | 7605 | 7617 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 18; Drilling Parameters ROP: 240 | 5550 | 4900 | 650 | 207 | 225 | 210 | 195
02/03/2022 | 16:28 | 16:41 | 0.21667 | 7617 | 7637 | 20 | Slide | 0 | 7634 | 1.4 | 307.87 | 7596.89 | 170.55 | 449.53 | 170.55 | 0.97 |  |  | 15 |  | 890 |  | 92.31 | 5200 | 4900 | 300 | 207 | 225 | 210 | 195
02/03/2022 | 16:41 | 16:50 | 0.15 | 7637 | 7699 | 62 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 18; Drilling Parameters ROP: 413.33 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 17:19 | 17:32 | 0.21667 | 7699 | 7793 | 94 | Rotate |  | 7728 | 1.8 | 310.24 | 7690.85 | 172.21 | 447.49 | 172.21 | 0.43 |  |  | 40 | 80.34 | 890 | 20 | 433.85 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 17:35 | 17:38 | 0.05 | 7793 | 7808 | 15 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 300 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 17:38 | 17:53 | 0.25 | 7808 | 7828 | 20 | Slide | 0 | 7822 | 1.19 | 276.79 | 7784.82 | 173.28 | 445.4 | 173.28 | 1.11 |  |  | 15 |  | 890 |  | 80 | 5100 | 4900 | 200 | 207 | 235 | 220 | 200
02/03/2022 | 17:53 | 18:03 | 0.16667 | 7828 | 7887 | 59 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 393.33 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 18:07 | 18:21 | 0.23333 | 7887 | 7981 | 94 | Rotate |  | 7916 | 1.46 | 262.58 | 7878.8 | 173.24 | 443.24 | 173.24 | 0.45 |  |  | 40 | 80.34 | 890 | 20 | 402.86 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 18:25 | 18:28 | 0.05 | 7981 | 7991 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 200 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 18:28 | 18:52 | 0.4 | 7991 | 8016 | 25 | Slide | 0 | 8010 | 0.19 | 216.43 | 7972.79 | 172.96 | 441.96 | 172.96 | 1.42 |  |  | 40 |  | 890 | 20 | 62.5 | 5550 | 4900 | 650 | 207 | 230 | 215 | 195
02/03/2022 | 18:52 | 19:04 | 0.2 | 8016 | 8075 | 59 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 295 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 19:07 | 19:23 | 0.26667 | 8075 | 8169 | 94 | Rotate |  | 8104 | 0.51 | 109.66 | 8066.78 | 172.69 | 442.26 | 172.69 | 0.63 |  |  | 40 | 80.34 | 890 | 20 | 352.5 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 19:27 | 19:41 | 0.23333 | 8169 | 8262 | 93 | Rotate |  | 8197 | 0.24 | 303.68 | 8159.78 | 172.66 | 442.49 | 172.66 | 0.8 |  |  | 40 | 80.34 | 890 | 20 | 398.57 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 19:45 | 19:59 | 0.23333 | 8262 | 8357 | 95 | Rotate |  | 8292 | 0.6 | 307.97 | 8254.78 | 173.08 | 441.93 | 173.08 | 0.38 |  |  | 40 | 80.34 | 890 | 20 | 407.14 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 20:02 | 20:08 | 0.1 | 8357 | 8390 | 33 | Rotate |  | 8385 | 1.04 | 297.42 | 8347.77 | 173.77 | 440.8 | 173.77 | 0.5 |  |  | 40 | 80.34 | 890 | 20 | 330 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 20:08 | 20:25 | 0.28333 | 8390 | 8400 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 35.29 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 20:25 | 20:34 | 0.15 | 8400 | 8450 | 50 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 333.33 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 20:38 | 20:39 | 0.016667 | 8450 | 8455 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 300 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 20:39 | 21:07 | 0.46667 | 8455 | 8472 | 17 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 36.43 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 21:07 | 21:23 | 0.26667 | 8472 | 8544 | 72 | Rotate |  | 8479 | 0.97 | 284.72 | 8441.76 | 174.36 | 439.27 | 174.36 | 0.25 |  |  | 40 | 80.34 | 890 | 20 | 270 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 21:26 | 21:28 | 0.033333 | 8544 | 8550 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 180 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 21:28 | 22:01 | 0.55 | 8550 | 8575 | 25 | Slide | 0 | 8573 | 0.99 | 69.26 | 8535.75 | 174.85 | 439.26 | 174.85 | 1.99 |  |  | 40 |  | 890 | 20 | 45.45 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 22:01 | 22:13 | 0.2 | 8575 | 8638 | 63 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 890; Drilling Parameters Tq: 20; Drilling Parameters ROP: 315 | 5458 | 4950 | 508 | 207 | 230 | 215 | 195
02/03/2022 | 22:18 | 22:33 | 0.25 | 8638 | 8731 | 93 | Rotate |  | 8666 | 0.87 | 89.4 | 8628.74 | 175.14 | 440.72 | 175.14 | 0.37 |  |  | 40 | 80.34 | 844 | 15.1 | 372 | 5503 | 4750 | 753 | 213.8 | 235 | 220 | 198
02/03/2022 | 22:37 | 22:50 | 0.21667 | 8731 | 8825 | 94 | Rotate |  | 8760 | 0.24 | 90.42 | 8722.73 | 175.15 | 441.63 | 175.15 | 0.67 |  |  | 40 | 80.34 | 844 | 15.1 | 433.85 | 5503 | 4750 | 753 | 213.8 | 235 | 220 | 198
02/03/2022 | 22:55 | 23:08 | 0.21667 | 8825 | 8919 | 94 | Rotate |  | 8854 | 0.05 | 221.29 | 8816.73 | 175.12 | 441.8 | 175.12 | 0.29 |  |  | 40 | 80.34 | 844 | 15.1 | 433.85 | 5503 | 4750 | 753 | 213.8 | 235 | 220 | 198
02/03/2022 | 23:11 | 23:25 | 0.23333 | 8919 | 9012 | 93 | Rotate |  | 8947 | 0.89 | 246.93 | 8909.73 | 174.8 | 441.11 | 174.8 | 0.91 |  |  | 40 | 80.34 | 844 | 15.1 | 398.57 | 5503 | 4750 | 753 | 213.8 | 235 | 220 | 198
02/03/2022 | 23:29 | 23:42 | 0.21667 | 9012 | 9107 | 95 | Rotate |  | 9042 | 1.45 | 227.26 | 9004.71 | 173.7 | 439.55 | 173.7 | 0.72 |  |  | 40 | 80.34 | 844 | 17.3 | 438.46 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/03/2022 | 23:46 | 24:00 | 0.23333 | 9107 | 9201 | 94 | Rotate |  | 9136 | 2.14 | 245.82 | 9098.66 | 172.17 | 437.07 | 172.17 | 0.95 |  |  | 40 | 80.34 | 844 | 17.3 | 402.86 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 00:03 | 00:05 | 0.033333 | 9201 | 9206 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 844; Drilling Parameters Tq: 17.3; Drilling Parameters ROP: 150 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 00:05 | 00:28 | 0.38333 | 9206 | 9223 | 17 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 844; Drilling Parameters Tq: 17.3; Drilling Parameters ROP: 44.35 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 00:28 | 00:40 | 0.2 | 9223 | 9296 | 73 | Rotate |  | 9231 | 1.82 | 258.34 | 9193.61 | 171.14 | 433.98 | 171.14 | 0.56 |  |  | 40 | 80.34 | 844 | 17.3 | 365 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 00:44 | 00:45 | 0.016667 | 9296 | 9300 | 4 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80.34; Drilling Parameters FLOW: 844; Drilling Parameters Tq: 17.3; Drilling Parameters ROP: 240 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 00:45 | 01:07 | 0.36667 | 9300 | 9320 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 844; Drilling Parameters Tq: 17.3; Drilling Parameters ROP: 54.55 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 01:07 | 01:19 | 0.2 | 9320 | 9390 | 70 | Rotate |  | 9325 | 0.19 | 334.89 | 9287.59 | 170.98 | 432.45 | 170.98 | 1.9 |  |  | 40 | 80.34 | 844 | 17.3 | 350 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 01:23 | 01:41 | 0.3 | 9390 | 9484 | 94 | Rotate |  | 9419 | 0.6 | 73.92 | 9381.59 | 171.26 | 432.85 | 171.26 | 0.7 |  |  | 40 | 80.34 | 844 | 17.3 | 313.33 | 5602 | 4980 | 622 | 213.8 | 235 | 220 | 198
02/04/2022 | 01:46 | 02:07 | 0.35 | 9484 | 9577 | 93 | Rotate |  | 9512 | 1.11 | 81.6 | 9474.58 | 171.52 | 434.21 | 171.52 | 0.56 |  |  | 40 | 80 | 828 | 13.7 | 398.57 | 5429 | 4840 | 589 | 226.4 | 240 | 225 | 205
02/04/2022 | 02:10 | 02:12 | 0.033333 | 9577 | 9583 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 828; Drilling Parameters Tq: 13.7; Drilling Parameters ROP: 180 | 5429 | 4840 | 589 | 226.4 | 240 | 225 | 205
02/04/2022 | 02:55 | 03:14 | 0.31667 | 9583 | 9671 | 88 | Rotate |  | 9606 | 1.1 | 72.94 | 9568.56 | 171.92 | 435.98 | 171.92 | 0.18 |  |  | 40 | 80 | 708 | 17.3 | 211.2 | 4272 | 3750 | 522 | 226.4 | 240 | 225 | 205
02/04/2022 | 03:19 | 03:34 | 0.25 | 9671 | 9735 | 64 | Rotate |  | 9700 | 0.73 | 43.34 | 9662.55 | 172.62 | 437.25 | 172.62 | 0.63 |  |  | 40 | 80 | 708 | 17.3 | 256 | 4272 | 3750 | 522 | 226.4 | 240 | 225 | 205
02/04/2022 | 03:34 | 04:00 | 0.43333 | 9735 | 9765 | 30 | Slide | TTF: 0; Drilling Parameters WOB: 23; Drilling Parameters FLOW: 708; Drilling Parameters Tq: 17.3; Drilling Parameters ROP: 69.23 | 3985 | 3753 | 232 | 224.6 | 260 | 255 | 230
02/04/2022 | 04:25 | 04:37 | 0.2 | 9765 | 9777 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 23; Drilling Parameters FLOW: 813; Drilling Parameters Tq: 17.3; Drilling Parameters ROP: 60 | 5210 | 4727 | 483 | 224.6 | 260 | 255 | 230
02/04/2022 | 05:32 | 06:15 | 0.71667 | 9777 | 9827 | 50 | Slide | 0 | 9794 | 4.42 | 173.02 | 9756.46 | 169.46 | 438.1 | 169.46 | 5.23 |  |  | 15 |  | 813 |  | 69.77 | 4900 | 4727 | 173 | 224.6 | 275 | 255 | 230
02/04/2022 | 06:15 | 07:27 | 1.2 | 9827 | 9859 | 32 | Slide | TTF: 0; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 704; Drilling Parameters ROP: 26.67 | 3750 | 3600 | 150 | 224.6 | 275 | 255 | 230
02/04/2022 | 07:36 | 09:44 | 2.1333 | 9859 | 9954 | 95 | Slide | 0 | 9889 | 11.76 | 158.21 | 9850.46 | 156.82 | 442.15 | 156.82 | 7.97 |  |  | 15 |  | 704 |  | 44.53 | 3800 | 3600 | 200 | 224.6 | 275 | 255 | 230
02/04/2022 | 09:54 | 10:05 | 0.18333 | 9954 | 9969 | 15 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 704; Drilling Parameters Tq: 13.5; Drilling Parameters ROP: 81.82 | 4000 | 3600 | 400 | 224.6 | 275 | 255 | 230
02/04/2022 | 10:05 | 11:03 | 0.96667 | 9969 | 10047 | 78 | Slide | 0 | 9982 | 18.28 | 149.74 | 9940.25 | 135.4 | 453.03 | 135.4 | 7.38 |  |  | 22 |  | 800 |  | 80.69 | 5000 | 4700 | 300 | 216 | 275 | 255 | 230
02/04/2022 | 11:13 | 11:40 | 0.45 | 10047 | 10141 | 94 | Rotate |  | 10076 | 22.46 | 141.78 | 10028.37 | 108.54 | 471.58 | 108.54 | 5.33 |  |  | 30 | 35 | 800 | 14 | 208.89 | 5150 | 4700 | 450 | 221 | 275 | 255 | 230
02/04/2022 | 11:47 | 11:51 | 0.066667 | 10141 | 10151 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 14; Drilling Parameters ROP: 150 | 5150 | 4700 | 450 | 221 | 275 | 255 | 230
02/04/2022 | 11:51 | 12:16 | 0.41667 | 10151 | 10171 | 20 | Slide | 0 | 10165 | 21.85 | 137.34 | 10110.8 | 83 | 493.32 | 83 | 2 |  |  | 25 |  | 800 |  | 48 | 4900 | 4700 | 200 | 223 | 275 | 255 | 230
02/04/2022 | 12:16 | 12:52 | 0.6 | 10171 | 10230 | 59 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 14; Drilling Parameters ROP: 98.33 | 5100 | 4800 | 300 | 223 | 275 | 255 | 230

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 370 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7659.9
Site: |  |  |  |  | Klondike - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1269
Well Name: |  |  |  |  | Mill H08 |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 370 |  | VS Azimuth: |  | 134.53 |  | Rotate: |  | 6390.9
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
03/18/2022 | 00:00 | 01:08 | 1.1333 | 10230 | 10351 | 121 | Slide | 0 | 10283 | 23.35 | 138.54 | 10219.74 | 49.33 | 523.68 | 49.33 | 1.33 |  |  | 20 |  | 350 |  | 106.76 | 3250 | 2850 | 400 | 219 | 240 | 200 | 170
03/18/2022 | 01:20 | 02:10 | 0.83333 | 10351 | 10446 | 95 | Slide | 0 | 10378 | 31.47 | 143.69 | 10304.01 | 15.17 | 550.88 | 15.17 | 8.9 |  |  | 20 |  | 400 |  | 114 | 3900 | 3300 | 600 | 215 | 240 | 200 | 170
03/18/2022 | 02:19 | 03:15 | 0.93333 | 10446 | 10540 | 94 | Slide | 0 | 10472 | 40.82 | 141.51 | 10379.84 | -28.75 | 584.61 | -28.75 | 10.04 |  |  | 20 |  | 400 |  | 100.71 | 3850 | 3300 | 550 | 217 | 240 | 200 | 170
03/18/2022 | 03:24 | 04:15 | 0.85 | 10540 | 10635 | 95 | Slide | 0 | 10567 | 49.62 | 129.05 | 10446.82 | -76.03 | 632.22 | -76.03 | 13.1 |  |  | 20 |  | 400 |  | 111.76 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 04:27 | 04:42 | 0.25 | 10635 | 10665 | 30 | Rotate |  | 10662 | 58.49 | 123.09 | 10502.57 | -121.05 | 694.41 | -121.05 | 10.62 |  |  | 10 | 30 | 400 | 6.8 | 120 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 04:42 | 05:16 | 0.56667 | 10665 | 10730 | 65 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6.8; Drilling Parameters ROP: 114.71 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 05:27 | 05:46 | 0.31667 | 10730 | 10780 | 50 | Rotate |  | 10752 | 61.38 | 132.95 | 10547.73 | -169.01 | 755.59 | -169.01 | 10.01 |  |  | 10 | 30 | 400 | 6.8 | 157.89 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 05:46 | 06:12 | 0.43333 | 10780 | 10820 | 40 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6.8; Drilling Parameters ROP: 92.31 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 06:25 | 06:46 | 0.35 | 10820 | 10880 | 60 | Rotate |  | 10848 | 65.65 | 135.19 | 10590.54 | -228.78 | 817.29 | -228.78 | 4.91 |  |  | 10 | 30 | 400 | 6.8 | 171.43 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 06:46 | 07:07 | 0.35 | 10880 | 10916 | 36 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6.8; Drilling Parameters ROP: 102.86 | 3850 | 3300 | 550 | 219 | 240 | 200 | 170
03/18/2022 | 07:17 | 07:40 | 0.38333 | 10916 | 10966 | 50 | Rotate |  | 10942 | 69.85 | 136.49 | 10626.13 | -291.19 | 877.87 | -291.19 | 4.65 |  |  | 10 | 30 | 400 | 6.8 | 130.43 | 3850 | 3300 | 550 | 221 | 240 | 200 | 170
03/18/2022 | 07:40 | 08:04 | 0.4 | 10966 | 11010 | 44 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6.8; Drilling Parameters ROP: 110 | 3850 | 3300 | 550 | 224 | 240 | 200 | 170
03/18/2022 | 08:14 | 08:34 | 0.33333 | 11010 | 11060 | 50 | Rotate |  | 11035 | 76.61 | 136.94 | 10652.94 | -355.97 | 938.88 | -355.97 | 7.28 |  |  | 15 | 30 | 400 | 6.8 | 150 | 3850 | 3300 | 550 | 224 | 240 | 200 | 170
03/18/2022 | 08:34 | 08:59 | 0.41667 | 11060 | 11103 | 43 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6.8; Drilling Parameters ROP: 103.2 | 3850 | 3300 | 550 | 231 | 240 | 200 | 170
03/18/2022 | 09:09 | 09:30 | 0.35 | 11103 | 11130 | 27 | Slide | 0 | 11130 | 85.89 | 136.75 | 10667.38 | -424.4 | 1003.04 | -424.4 | 9.77 |  |  | 25 | 74.37 | 417.51 | 13.77 | 240.6 | 4012.18 | 3300 | 712.18 | 231 | 240 | 200 | 170
03/18/2022 | 09:30 | 09:55 | 0.41667 | 11130 | 11198 | 68 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.11; Drilling Parameters FLOW: 398.25; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 163.2 | 4068.84 | 3123.98 | 944.86 | 237.2 | 240 | 200.26 | 170
03/18/2022 | 10:00 | 10:28 | 0.46667 | 11198 | 11292 | 94 | Rotate |  | 11224 | 87.21 | 136.09 | 10673.04 | -492.36 | 1067.72 | -492.36 | 1.57 |  |  | 25 | 66.11 | 398.25 | 13.77 | 201.43 | 4068.84 | 3123.98 | 944.86 | 237.2 | 240 | 200.26 | 170
03/18/2022 | 10:33 | 10:43 | 0.16667 | 11292 | 11304 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.95; Drilling Parameters FLOW: 398.06; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 84.48 | 3445.73 | 3436.88 | 8.85 | 239 | 240 | 200 | 170
03/18/2022 | 10:43 | 10:57 | 0.23333 | 11304 | 11325 | 21 | Slide | -153.98 | 11319 | 85.78 | 134.58 | 10678.84 | -559.8 | 1134.37 | -559.8 | 2.19 |  |  | 25 | 49.91 | 398.21 | 13.77 | 90 | 3617.28 | 3480.89 | 136.39 | 239 | 240 | 200 | 170
03/18/2022 | 10:57 | 11:10 | 0.21667 | 11325 | 11387 | 62 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 65.49; Drilling Parameters FLOW: 398.17; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 286.15 | 4087.76 | 3745.97 | 341.79 | 239 | 240 | 200.25 | 170
03/18/2022 | 11:16 | 11:37 | 0.35 | 11387 | 11482 | 95 | Rotate |  | 11413 | 86.93 | 135.2 | 10684.82 | -626.01 | 1200.83 | -626.01 | 1.39 |  |  | 25 | 65.69 | 398.19 | 13.77 | 271.43 | 4148.93 | 3178.29 | 970.64 | 242.6 | 240 | 200.19 | 170
03/18/2022 | 11:43 | 11:49 | 0.1 | 11482 | 11487 | 5 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.95; Drilling Parameters FLOW: 398.13; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 50 | 3461.07 | 3457.16 | 3.91 | 244.4 | 240 | 201.12 | 170
03/18/2022 | 11:49 | 12:02 | 0.21667 | 11487 | 11508 | 21 | Slide | -170.59 | 11507 | 84.27 | 134.19 | 10692.03 | -691.92 | 1267.44 | -691.92 | 3.03 |  |  | 25 | 49.98 | 398.27 | 13.77 | 96.92 | 3698.82 | 3558.13 | 140.69 | 244.4 | 240 | 201.12 | 170
03/18/2022 | 12:02 | 12:15 | 0.21667 | 11508 | 11574 | 66 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.48; Drilling Parameters FLOW: 398.2; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 304.62 | 4181.44 | 3702.29 | 479.15 | 246.2 | 240 | 200.48 | 170
03/18/2022 | 12:22 | 12:42 | 0.33333 | 11574 | 11669 | 95 | Rotate |  | 11602 | 83.96 | 134 | 10701.77 | -757.68 | 1335.31 | -757.68 | 0.38 |  |  | 25 | 66.53 | 398.2 | 13.77 | 285 | 4095.74 | 3461.36 | 634.38 | 253.4 | 240 | 202.65 | 170
03/18/2022 | 12:49 | 13:10 | 0.35 | 11669 | 11764 | 95 | Rotate |  | 11696 | 84.05 | 133.98 | 10711.59 | -822.61 | 1402.57 | -822.61 | 0.1 |  |  | 25 | 65.72 | 398.18 | 13.77 | 271.43 | 4073.86 | 3197.72 | 876.14 | 258.8 | 240 | 201.99 | 170
03/18/2022 | 13:16 | 13:26 | 0.16667 | 11764 | 11775 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.78; Drilling Parameters FLOW: 398.36; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 66 | 3511.17 | 3471.2 | 39.97 | 258.8 | 240 | 201.99 | 170
03/18/2022 | 13:26 | 13:37 | 0.18333 | 11775 | 11791 | 16 | Slide | -39.6 | 11790 | 86.34 | 133.69 | 10719.46 | -887.47 | 1470.14 | -887.47 | 2.46 |  |  | 25 | 49.94 | 398.27 | 13.77 | 87.27 | 3805.14 | 3579.55 | 225.59 | 258.8 | 240 | 201.99 | 170
03/18/2022 | 13:37 | 13:53 | 0.26667 | 11791 | 11859 | 68 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.31; Drilling Parameters FLOW: 398.16; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 255 | 4210.43 | 4009.63 | 200.8 | 258.8 | 240 | 198.45 | 170
03/18/2022 | 14:00 | 14:20 | 0.33333 | 11859 | 11955 | 96 | Rotate |  | 11885 | 87.97 | 133.01 | 10724.18 | -952.6 | 1539.13 | -952.6 | 1.86 |  |  | 25 | 67.31 | 398.17 | 13.77 | 288 | 4270.82 | 4063.77 | 207.05 | 262.4 | 240 | 194.58 | 170
03/18/2022 | 14:26 | 14:48 | 0.36667 | 11955 | 12051 | 96 | Rotate |  | 11981 | 88.55 | 132.3 | 10727.09 | -1017.62 | 1609.7 | -1017.62 | 0.95 |  |  | 25 | 66.99 | 398.19 | 13.77 | 261.82 | 4180.05 | 3679.38 | 500.67 | 264.2 | 240 | 199.07 | 170
03/18/2022 | 14:56 | 15:17 | 0.35 | 12051 | 12144 | 93 | Rotate |  | 12075 | 89.75 | 131.88 | 10728.49 | -1080.62 | 1679.45 | -1080.62 | 1.35 |  |  | 25 | 67.42 | 398.15 | 13.77 | 265.71 | 4242.25 | 3609.07 | 633.18 | 267.8 | 240 | 199.54 | 170
03/18/2022 | 15:23 | 15:32 | 0.15 | 12144 | 12151 | 7 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.96; Drilling Parameters FLOW: 397.85; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 46.67 | 3626.64 | 3561.04 | 65.6 | 266 | 240 | 199.8 | 170
03/18/2022 | 15:32 | 15:46 | 0.23333 | 12151 | 12173 | 22 | Slide | 159.83 | 12171 | 86.4 | 131.26 | 10731.71 | -1144.28 | 1751.22 | -1144.28 | 3.55 |  |  | 25 | 50.01 | 398.41 | 13.77 | 94.29 | 3702.02 | 3629.84 | 72.18 | 266 | 250 | 199.8 | 170
03/18/2022 | 15:46 | 15:59 | 0.21667 | 12173 | 12238 | 65 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.27; Drilling Parameters FLOW: 398.15; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 300 | 4149.1 | 3839.6 | 309.5 | 266 | 250 | 200.31 | 170
03/18/2022 | 16:04 | 16:24 | 0.33333 | 12238 | 12334 | 96 | Rotate |  | 12262 | 86.82 | 131.02 | 10737.09 | -1204.04 | 1819.63 | -1204.04 | 0.53 |  |  | 25 | 66.33 | 398.19 | 13.77 | 288 | 4154.87 | 4029.36 | 125.51 | 269.6 | 250 | 199.89 | 170
03/18/2022 | 16:31 | 16:41 | 0.16667 | 12334 | 12343 | 9 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 55.18; Drilling Parameters FLOW: 398.18; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 54 | 3598.13 | 3582.64 | 15.49 | 269.6 | 250 | 199.89 | 170
03/18/2022 | 16:41 | 16:56 | 0.25 | 12343 | 12366 | 23 | Slide | 132.9 | 12354 | 86.97 | 134.33 | 10742.08 | -1266.3 | 1887.16 | -1266.3 | 3.6 |  |  | 25 | 49.92 | 398.06 | 13.77 | 92 | 3748.43 | 3656.66 | 91.77 | 269.6 | 250 | 199.89 | 170
03/18/2022 | 16:56 | 17:07 | 0.18333 | 12366 | 12426 | 60 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.33; Drilling Parameters FLOW: 398.15; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 327.27 | 4188.39 | 3450.66 | 737.73 | 267.8 | 250 | 199.89 | 170
03/18/2022 | 17:44 | 18:03 | 0.31667 | 12426 | 12522 | 96 | Rotate |  | 12450 | 87.11 | 139.17 | 10747.04 | -1336.11 | 1952.83 | -1336.11 | 5.04 |  |  | 25 | 64.26 | 398.16 | 13.77 | 303.16 | 4106.72 | 3172.31 | 934.41 | 267.8 | 250 | 203.81 | 165
03/18/2022 | 18:08 | 18:18 | 0.16667 | 12522 | 12528 | 6 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.92; Drilling Parameters FLOW: 398.15; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 36 | 3050.63 | 3158.82 | -108.19 | 267.8 | 250 | 208.2 | 165
03/18/2022 | 18:18 | 20:34 | 2.2667 | 12528 | 12544 | 16 | Slide | -147.3 | 12544 | 87.03 | 143.96 | 10751.85 | -1409.62 | 2011.17 | -1409.62 | 5.09 |  |  | 25 | 49.89 | 398 | 13.77 | 7.06 | 2421.71 | 1759.49 | 662.22 | 266 | 250 | 200.46 | 165
03/18/2022 | 20:34 | 20:59 | 0.41667 | 12544 | 12611.38 | 67.38 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.62; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 161.71 | 2561.05 | 2078.22 | 482.83 | 267.8 | 250 | 201.62 | 165
03/19/2022 | 14:52 | 14:56 | 0.066667 | 12611.38 | 12615 | 3.62 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 54.3 | 4200 | 3500 | 700 | 274 | 250 | 201.62 | 165
03/19/2022 | 14:56 | 15:18 | 0.36667 | 12615 | 12640 | 25 | Slide | 0 | 12639 | 85.28 | 144.76 | 10758.22 | -1486.65 | 2066.4 | -1486.65 | 2.02 |  |  | 40 | 70 | 398.19 | 11 | 68.18 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 15:18 | 15:31 | 0.21667 | 12640 | 12670 | 30 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 138.46 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 15:31 | 15:45 | 0.23333 | 12670 | 12685 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 64.29 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 15:45 | 15:55 | 0.16667 | 12685 | 12707 | 22 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 132 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 16:00 | 16:06 | 0.1 | 12707 | 12718 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 110 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 16:06 | 16:22 | 0.26667 | 12718 | 12733 | 15 | Slide | 0 | 12733 | 85.44 | 139.28 | 10765.83 | -1560.47 | 2124.03 | -1560.47 | 5.81 |  |  | 40 | 70 | 398.19 | 11 | 56.25 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 16:22 | 16:34 | 0.2 | 12733 | 12763 | 30 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 150 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 16:34 | 16:51 | 0.28333 | 12763 | 12778 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 52.94 | 4200 | 3500 | 700 | 271 | 250 | 201.62 | 165
03/19/2022 | 16:51 | 16:59 | 0.13333 | 12778 | 12800 | 22 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 398.19; Drilling Parameters Tq: 11; Drilling Parameters ROP: 165 | 4200 | 3500 | 700 | 271 | 250 | 194.28 | 165
03/19/2022 | 17:05 | 17:16 | 0.18333 | 12800 | 12812 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.96; Drilling Parameters FLOW: 396.7; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 65.45 | 3735.96 | 3706.19 | 29.77 | 271.4 | 250 | 197.88 | 165
03/19/2022 | 17:16 | 17:33 | 0.28333 | 12812 | 12831 | 19 | Slide | -91.05 | 12827 | 87.91 | 134 | 10771.28 | -1628.67 | 2188.44 | -1628.67 | 6.19 |  |  | 50 | 49.98 | 396.81 | 13.77 | 67.06 | 4036.97 | 3826.48 | 210.49 | 271.4 | 250 | 198.06 | 165
03/19/2022 | 17:33 | 17:48 | 0.25 | 12831 | 12895 | 64 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 65.95; Drilling Parameters FLOW: 396.78; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 256 | 4482.56 | 4206.49 | 276.07 | 275 | 250 | 195.17 | 165
03/19/2022 | 17:55 | 18:06 | 0.18333 | 12895 | 12902 | 7 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.92; Drilling Parameters FLOW: 396.75; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 38.18 | 3820.84 | 3856 | -35.16 | 275 | 250 | 195.17 | 165
03/19/2022 | 18:06 | 18:29 | 0.38333 | 12902 | 12923 | 21 | Slide | -168.75 | 12922 | 85.77 | 131.57 | 10776.52 | -1693.09 | 2258.04 | -1693.09 | 3.41 |  |  | 50 | 49.95 | 396.64 | 13.77 | 54.78 | 4155.16 | 3818.8 | 336.36 | 275 | 250 | 195.17 | 160
03/19/2022 | 18:29 | 18:45 | 0.26667 | 12923 | 12990 | 67 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 66.04; Drilling Parameters FLOW: 396.75; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 251.25 | 4393.36 | 4416.36 | -23 | 275 | 250 | 199.27 | 160
03/19/2022 | 18:52 | 19:14 | 0.36667 | 12990 | 13083 | 93 | Rotate |  | 13017 | 86.2 | 131.05 | 10783.17 | -1755.65 | 2329.23 | -1755.65 | 0.71 |  |  | 25 | 65.76 | 396.77 | 13.77 | 253.64 | 4513.74 | 3653.69 | 860.05 | 278.6 | 255 | 195.08 | 160
03/19/2022 | 19:19 | 19:42 | 0.38333 | 13083 | 13179 | 96 | Rotate |  | 13112 | 86.97 | 130.77 | 10788.83 | -1817.75 | 2400.89 | -1817.75 | 0.86 |  |  | 25 | 65.62 | 396.75 | 13.77 | 250.43 | 4618.87 | 3954.32 | 664.55 | 282.2 | 255 | 197.9 | 160
03/19/2022 | 19:46 | 19:59 | 0.21667 | 13179 | 13192 | 13 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.92; Drilling Parameters FLOW: 396.84; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 60 | 4098.05 | 3983.11 | 114.94 | 282.2 | 255 | 200.81 | 160
03/19/2022 | 19:59 | 20:12 | 0.21667 | 13192 | 13203 | 11 | Slide | TTF: 150.2; Drilling Parameters WOB: 40; Drilling Parameters RPM: 49.95; Drilling Parameters FLOW: 396.97; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 50.77 | 4253.2 | 3899.81 | 353.39 | 282.2 | 255 | 194.68 | 160
03/19/2022 | 20:12 | 20:27 | 0.25 | 13203 | 13272 | 69 | Rotate |  | 13206 | 86.08 | 130.8 | 10794.53 | -1879.04 | 2471.94 | -1879.04 | 0.95 |  |  | 25 | 66.49 | 396.79 | 13.77 | 276 | 4559.78 | 3396.16 | 1163.62 | 280.4 | 255 | 200.49 | 160
03/19/2022 | 20:32 | 20:54 | 0.36667 | 13272 | 13368 | 96 | Rotate |  | 13301 | 85.93 | 130.74 | 10801.15 | -1940.93 | 2543.71 | -1940.93 | 0.17 |  |  | 25 | 64.57 | 396.76 | 13.77 | 261.82 | 4600.35 | 3662.08 | 938.27 | 284 | 255 | 197.38 | 160
03/19/2022 | 20:59 | 21:26 | 0.45 | 13368 | 13461 | 93 | Rotate |  | 13393 | 86.37 | 131.42 | 10807.32 | -2001.25 | 2612.9 | -2001.25 | 0.88 |  |  | 25 | 66.1 | 396.74 | 13.77 | 206.67 | 4634.29 | 3803.81 | 830.48 | 278.6 | 255 | 192.73 | 160
03/19/2022 | 22:15 | 22:39 | 0.4 | 13461 | 13555 | 94 | Rotate |  | 13487 | 86.62 | 130.94 | 10813.07 | -2063.02 | 2683.52 | -2063.02 | 0.57 |  |  | 25 | 66.03 | 396.78 | 13.77 | 235 | 4513.82 | 3403.95 | 1109.87 | 278.6 | 255 | 192.2 | 160
03/19/2022 | 22:43 | 22:56 | 0.21667 | 13555 | 13567 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.91; Drilling Parameters FLOW: 396.79; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 55.38 | 4042.44 | 3978.59 | 63.85 | 280.4 | 255 | 205.97 | 160
03/19/2022 | 22:56 | 23:10 | 0.23333 | 13567 | 13578 | 11 | Slide | TTF: 120.04; Drilling Parameters WOB: 40; Drilling Parameters RPM: 49.96; Drilling Parameters FLOW: 396.84; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 47.14 | 4270.89 | 3940.82 | 330.07 | 280.4 | 255 | 205.97 | 160
03/19/2022 | 23:10 | 23:27 | 0.28333 | 13578 | 13648 | 70 | Rotate |  | 13581 | 86.22 | 132.84 | 10818.94 | -2125.66 | 2753.35 | -2125.66 | 2.06 |  |  | 25 | 64.78 | 396.76 | 13.77 | 247.06 | 4530.98 | 3504.68 | 1026.3 | 278.6 | 255 | 192.07 | 160
03/19/2022 | 23:32 | 23:55 | 0.38333 | 13648 | 13743 | 95 | Rotate |  | 13675 | 85.33 | 132.71 | 10825.87 | -2189.32 | 2822.16 | -2189.32 | 0.96 |  |  | 25 | 65.96 | 396.77 | 13.77 | 247.83 | 4566.39 | 3938.06 | 628.33 | 280.4 | 255 | 192.89 | 160
03/20/2022 | 00:00 | 00:12 | 0.2 | 13743 | 13755 | 12 | Rotate | Drilling Parameters ROP: 60
03/20/2022 | 14:46 | 14:56 | 0.16667 | 13755 | 13755 |  | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.96; Drilling Parameters FLOW: 396.75; Drilling Parameters Tq: 13.77 | 4450 | 3600 | 850 | 280.4 | 255 | 199.55 | 160
03/20/2022 | 14:56 | 15:18 | 0.36667 | 13755 | 13835 | 80 | Rotate |  | 13769 | 87.51 | 134.01 | 10831.73 | -2253.73 | 2890.37 | -2253.73 | 2.7 |  |  | 30 | 68.8 | 396.75 | 13.77 | 218.18 | 4492.39 | 3317.34 | 1175.05 | 280.4 | 255 | 194.61 | 160
03/20/2022 | 15:24 | 15:50 | 0.43333 | 13835 | 13930 | 95 | Rotate |  | 13863 | 86.92 | 133.18 | 10836.3 | -2318.47 | 2958.36 | -2318.47 | 1.08 |  |  | 30 | 66.8 | 396.78 | 13.77 | 219.23 | 4516.19 | 4360.74 | 155.45 | 282.2 | 265 | 194 | 150
03/20/2022 | 15:56 | 16:20 | 0.4 | 13930 | 14024 | 94 | Rotate |  | 13957 | 87.84 | 132.92 | 10840.6 | -2382.57 | 3026.98 | -2382.57 | 1.02 |  |  | 30 | 67.05 | 396.78 | 13.77 | 235 | 4596 | 4191.99 | 404.01 | 284 | 265 | 193.55 | 150
03/20/2022 | 16:26 | 16:52 | 0.43333 | 14024 | 14119 | 95 | Rotate |  | 14051 | 88 | 132.81 | 10844.01 | -2446.48 | 3095.83 | -2446.48 | 0.21 |  |  | 30 | 66.49 | 396.76 | 13.77 | 219.23 | 4532.63 | 4394.22 | 138.41 | 285.8 | 265 | 193.5 | 150
03/20/2022 | 16:57 | 17:22 | 0.41667 | 14119 | 14215 | 96 | Rotate |  | 14146 | 89.16 | 132.63 | 10846.36 | -2510.9 | 3165.61 | -2510.9 | 1.24 |  |  | 30 | 66.76 | 396.76 | 13.77 | 230.4 | 4511.84 | 4387.73 | 124.11 | 287.6 | 265 | 193.73 | 150
03/20/2022 | 17:28 | 17:38 | 0.16667 | 14215 | 14226 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.98; Drilling Parameters FLOW: 396.68; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 66 | 3878.05 | 3873.45 | 4.6 | 287.6 | 265 | 193.98 | 150
03/20/2022 | 17:38 | 17:57 | 0.31667 | 14226 | 14245 | 19 | Slide | 166.41 | 14241 | 87.75 | 132.31 | 10848.93 | -2575.02 | 3235.65 | -2575.02 | 1.52 |  |  | 30 | 50.04 | 396.71 | 13.77 | 60 | 4150.82 | 3875.06 | 275.76 | 287.6 | 265 | 193.98 | 150
03/20/2022 | 17:57 | 18:10 | 0.21667 | 14245 | 14310 | 65 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 64.98; Drilling Parameters FLOW: 396.75; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 300 | 4465.89 | 3308.45 | 1157.44 | 285.8 | 265 | 195.98 | 150
03/20/2022 | 18:14 | 18:26 | 0.2 | 14310 | 14320 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.98; Drilling Parameters FLOW: 396.75; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 50 | 3942.98 | 3877.43 | 65.55 | 285.8 | 265 | 201.99 | 150
03/20/2022 | 18:26 | 18:41 | 0.25 | 14320 | 14334 | 14 | Slide | 143.75 | 14333 | 86.79 | 138.3 | 10853.31 | -2640.32 | 3300.26 | -2640.32 | 6.59 |  |  | 30 | 49.97 | 396.89 | 13.77 | 56 | 4183.93 | 3946.11 | 237.82 | 285.8 | 265 | 201.99 | 150
03/20/2022 | 18:41 | 18:55 | 0.23333 | 14334 | 14403 | 69 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 64.24; Drilling Parameters FLOW: 396.77; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 295.71 | 4540.88 | 3921.23 | 619.65 | 285.8 | 265 | 201.99 | 150
03/20/2022 | 19:00 | 19:23 | 0.38333 | 14403 | 14416 | 13 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.99; Drilling Parameters FLOW: 396.78; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 33.91 | 4040.09 | 3993.52 | 46.57 | 287.6 | 265 | 207.85 | 150
03/20/2022 | 19:23 | 19:49 | 0.43333 | 14416 | 14425 | 9 | Slide | TTF: -111.37; Drilling Parameters WOB: 30; Drilling Parameters RPM: 50.01; Drilling Parameters FLOW: 396.82; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 20.77 | 4268.69 | 3896.95 | 371.74 | 287.6 | 265 | 207.85 | 150
03/20/2022 | 19:49 | 20:04 | 0.25 | 14425 | 14495 | 70 | Rotate |  | 14427 | 85.59 | 137.79 | 10859.56 | -2710.07 | 3362.96 | -2710.07 | 1.39 |  |  | 30 | 66.3 | 396.79 | 13.77 | 280 | 4562.83 | 3958.83 | 604 | 285.8 | 265 | 207.85 | 150
03/20/2022 | 20:08 | 20:12 | 0.066667 | 14495 | 14505 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 62.78; Drilling Parameters FLOW: 396.77; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 150 | 4540.15 | 3941.89 | 598.26 | 287.6 | 265 | 193.7 | 150
03/20/2022 | 20:12 | 20:33 | 0.35 | 14505 | 14517 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 50.01; Drilling Parameters FLOW: 396.77; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 34.29 | 4540 | 3941 | 599 | 287.6 | 265 | 207.85 | 150
03/20/2022 | 20:33 | 20:54 | 0.35 | 14517 | 14517 |  | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 50.01; Drilling Parameters FLOW: 396.77; Drilling Parameters Tq: 13.77 | 4540 | 3941 | 599 | 287.6 | 265 | 207.85 | 150
03/20/2022 | 20:58 | 21:21 | 0.38333 | 14517 | 14683 | 166 | Rotate |  | 14521 | 84.05 | 136.44 | 10868.04 | -2778.66 | 3426.66 | -2778.66 | 2.17 |  |  | 30 | 65.79 | 396.77 | 13.77 | 433.04 | 4581.5 | 3976 | 605.5 | 289.4 | 265 | 186.51 | 150
03/20/2022 | 21:25 | 21:36 | 0.18333 | 14683 | 14693 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.93; Drilling Parameters FLOW: 396.74; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 54.55 | 3940.33 | 3976.32 | -35.99 | 289.4 | 265 | 202.92 | 150
03/20/2022 | 21:36 | 22:05 | 0.48333 | 14693 | 14714 | 21 | Slide | 0.41 | 14709 | 85.14 | 135.94 | 10888 | -2912.83 | 3556.82 | -2912.83 | 2.08 |  |  | 30 | 49.94 | 396.69 | 13.77 | 43.45 | 4226.64 | 3934.5 | 292.14 | 289.4 | 265 | 202.92 | 150
03/20/2022 | 22:05 | 22:19 | 0.23333 | 14714 | 14777 | 63 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 66.3; Drilling Parameters FLOW: 396.74; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 270 | 4562.57 | 4621.07 | -58.5 | 287.6 | 270 | 202.92 | 150
03/20/2022 | 22:22 | 22:34 | 0.2 | 14777 | 14787 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.93; Drilling Parameters FLOW: 396.78; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 50 | 3902.14 | 3914.15 | -12.01 | 289.4 | 270 | 196.07 | 150
03/20/2022 | 22:34 | 22:45 | 0.18333 | 14787 | 14795 | 8 | Slide | TTF: -6.49; Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.97; Drilling Parameters FLOW: 396.73; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 43.64 | 4270.49 | 3933.63 | 336.86 | 289.4 | 270 | 189.44 | 150
03/20/2022 | 22:45 | 23:04 | 0.31667 | 14795 | 14870 | 75 | Rotate |  | 14804 | 86.85 | 135.69 | 10894.63 | -2980.78 | 3622.87 | -2980.78 | 1.82 |  |  | 30 | 65.57 | 396.77 | 13.77 | 236.84 | 4624.1 | 3531.62 | 1092.48 | 289.4 | 270 | 189.44 | 150
03/20/2022 | 23:08 | 23:19 | 0.18333 | 14870 | 14882 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.93; Drilling Parameters FLOW: 396.79; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 65.45 | 3975.37 | 4006.04 | -30.67 | 289.4 | 270 | 203.22 | 150
03/20/2022 | 23:19 | 23:34 | 0.25 | 14882 | 14889 | 7 | Slide | TTF: -68.07; Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.99; Drilling Parameters FLOW: 396.05; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 28 | 4325.95 | 4025.4 | 300.55 | 289.4 | 270 | 194.99 | 150
03/20/2022 | 23:35 | 23:54 | 0.31667 | 14889 | 14965 | 76 | Rotate |  | 14897 | 88.55 | 134.11 | 10898.36 | -3046.37 | 3688.69 | -3046.37 | 2.49 |  |  | 30 | 66.1 | 396.76 | 13.77 | 240 | 4612.07 | 3650.74 | 961.33 | 289.4 | 270 | 194.99 | 150
03/20/2022 | 23:59 | 24:00 | 0.016667 | 14965 | 14968 | 3 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.87; Drilling Parameters FLOW: 396.72; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 180 | 4325.95 | 3750.88 | 575.07 | 289.4 | 270 | 203.22 | 150
03/21/2022 | 00:00 | 00:25 | 0.41667 | 14968 | 15060 | 92 | Rotate |  | 14992 | 88.16 | 133.16 | 10901.09 | -3111.9 | 3757.42 | -3111.9 | 1.08 |  |  | 30 | 66.17 | 396.78 | 13.77 | 220.8 | 4628.18 | 4578.69 | 49.49 | 291.2 | 270 | 194.99 | 150
03/21/2022 | 00:29 | 00:54 | 0.41667 | 15060 | 15154 | 94 | Rotate |  | 15087 | 89.76 | 133.19 | 10902.82 | -3176.89 | 3826.68 | -3176.89 | 1.68 |  |  | 30 | 66.72 | 396.77 | 13.77 | 225.6 | 4653.32 | 3431.05 | 1222.27 | 293 | 270 | 209.39 | 150
03/21/2022 | 00:59 | 01:13 | 0.23333 | 15154 | 15165 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.94; Drilling Parameters FLOW: 396.81; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 47.14 | 4135.89 | 4089.95 | 45.94 | 293 | 270 | 209.39 | 150
03/21/2022 | 01:13 | 01:40 | 0.45 | 15165 | 15186 | 21 | Slide | 166.39 | 15182 | 87.96 | 132.63 | 10904.71 | -3241.55 | 3896.25 | -3241.55 | 1.98 |  |  | 30 | 49.96 | 396.69 | 13.77 | 46.67 | 4464.59 | 4071.98 | 392.61 | 289.4 | 270 | 209.39 | 150
03/21/2022 | 01:41 | 01:49 | 0.13333 | 15186 | 15217 | 31 | Rotate | Drilling Parameters ROP: 232.5
03/21/2022 | 05:33 | 05:41 | 0.13333 | 15217 | 15249 | 32 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 62.41; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 240 | 3589.64 | 3592.74 | -3.1 | 251.6 | 270 | 191.79 | 150
03/21/2022 | 05:46 | 06:09 | 0.38333 | 15249 | 15344 | 95 | Rotate |  | 15277 | 87.96 | 132.86 | 10908.09 | -3305.99 | 3965.97 | -3305.99 | 0.24 |  |  | 30 | 66.75 | 401.28 | 13.77 | 247.83 | 3824.64 | 3260.62 | 564.02 | 213.8 | 270 | 191.61 | 150
03/21/2022 | 06:16 | 06:57 | 0.68333 | 15344 | 15439 | 95 | Rotate |  | 15371 | 87.97 | 131.71 | 10911.43 | -3369.2 | 4035.46 | -3369.2 | 1.22 |  |  | 30 | 67.58 | 401.29 | 13.77 | 139.02 | 4191.25 | 3814.28 | 376.97 | 163.4 | 270 | 183.74 | 150
03/21/2022 | 07:07 | 07:48 | 0.68333 | 15439 | 15535 | 96 | Rotate |  | 15466 | 89.08 | 131.9 | 10913.87 | -3432.5 | 4106.25 | -3432.5 | 1.19 |  |  | 30 | 66.54 | 448.71 | 13.77 | 140.49 | 4607.46 | 4007.45 | 600.01 | 145.4 | 270 | 182.38 | 150
03/21/2022 | 07:56 | 08:05 | 0.15 | 15535 | 15546 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.95; Drilling Parameters FLOW: 401.31; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 73.33 | 4167.96 | 4189.5 | -21.54 | 140 | 270 | 182.38 | 150
03/21/2022 | 08:05 | 08:25 | 0.33333 | 15546 | 15565 | 19 | Slide | 145.92 | 15561 | 88.13 | 132.84 | 10916.18 | -3496.5 | 4176.42 | -3496.5 | 1.41 |  |  | 45 | 50 | 401.19 | 13.77 | 57 | 4790.43 | 4459.58 | 330.85 | 140 | 270 | 182.38 | 150
03/21/2022 | 08:25 | 08:47 | 0.36667 | 15565 | 15631 | 66 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 65.35; Drilling Parameters FLOW: 401.28; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 180 | 4925.06 | 4459.58 | 465.48 | 131 | 270 | 178.73 | 150
03/21/2022 | 08:54 | 09:29 | 0.58333 | 15631 | 15723 | 92 | Rotate |  | 15655 | 87.5 | 131.84 | 10919.77 | -3559.77 | 4245.85 | -3559.77 | 1.26 |  |  | 30 | 67.2 | 401.32 | 13.77 | 157.71 | 5099.39 | 4205.9 | 893.49 | 140 | 270 | 176.33 | 150
03/21/2022 | 09:35 | 09:44 | 0.15 | 15723 | 15734 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.99; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 73.33 | 4601.79 | 4615.86 | -14.07 | 141.8 | 270 | 176.36 | 150
03/21/2022 | 09:44 | 10:04 | 0.33333 | 15734 | 15752 | 18 | Slide | 112.38 | 15749 | 87.25 | 132.15 | 10924.07 | -3622.59 | 4315.64 | -3622.59 | 0.42 |  |  | 45 | 50.19 | 401.34 | 13.77 | 54 | 5019.81 | 4682.82 | 336.99 | 141.8 | 270 | 176.36 | 150
03/21/2022 | 10:04 | 10:23 | 0.31667 | 15752 | 15817 | 65 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 65.79; Drilling Parameters FLOW: 401.33; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 205.26 | 5036.55 | 3427.52 | 1609.03 | 129.2 | 270 | 174.06 | 150
03/21/2022 | 10:30 | 11:13 | 0.71667 | 15817 | 15910 | 93 | Rotate |  | 15843 | 87.27 | 134.07 | 10928.57 | -3686.76 | 4384.18 | -3686.76 | 2.04 |  |  | 30 | 67.6 | 401.33 | 13.77 | 129.77 | 5051.15 | 3090.02 | 1961.13 | 143.6 | 270 | 172.22 | 150
03/21/2022 | 11:49 | 12:01 | 0.2 | 15910 | 15941 | 31 | Rotate |  | 15938 | 87.01 | 135.09 | 10933.31 | -3753.35 | 4451.76 | -3753.35 | 1.11 |  |  | 30 | 60.81 | 401.32 | 13.77 | 155 | 5373.51 | 4933.55 | 439.96 | 145.4 | 270 | 176.72 | 150
03/21/2022 | 12:41 | 13:00 | 0.31667 | 15941 | 16004 | 63 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 66.55; Drilling Parameters FLOW: 401.3; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 198.95 | 5558.33 | 5038.7 | 519.63 | 158 | 270 | 171.18 | 150
03/21/2022 | 13:06 | 13:20 | 0.23333 | 16004 | 16044 | 40 | Rotate |  | 16032 | 87 | 135.02 | 10938.22 | -3819.8 | 4518.07 | -3819.8 | 0.08 |  |  | 30 | 63.28 | 401.33 | 13.77 | 171.43 | 5440.47 | 4870.12 | 570.35 | 154.4 | 270 | 173.42 | 150
03/21/2022 | 13:49 | 14:06 | 0.28333 | 16044 | 16100 | 56 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 66.49; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 197.65 | 5579.2 | 5306.8 | 272.4 | 156.2 | 270 | 171.53 | 150
03/21/2022 | 14:13 | 14:55 | 0.7 | 16100 | 16195 | 95 | Rotate |  | 16127 | 87.22 | 135.53 | 10943.01 | -3887.21 | 4584.84 | -3887.21 | 0.58 |  |  | 30 | 67.44 | 401.32 | 13.77 | 135.71 | 5748.91 | 4816.2 | 932.71 | 161.6 | 270 | 169.71 | 150
03/21/2022 | 15:08 | 15:35 | 0.45 | 16195 | 16290 | 95 | Rotate |  | 16220 | 87.29 | 137.21 | 10947.46 | -3954.44 | 4648.93 | -3954.44 | 1.81 |  |  | 30 | 66.7 | 401.32 | 13.77 | 211.11 | 5927.63 | 5641.94 | 285.69 | 161.6 | 270 | 168.13 | 150
03/21/2022 | 15:42 | 15:52 | 0.16667 | 16290 | 16296 | 6 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.98; Drilling Parameters FLOW: 401.31; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 36 | 5280.82 | 5194.3 | 86.52 | 159.8 | 270 | 168.13 | 150
03/21/2022 | 15:52 | 16:27 | 0.58333 | 16296 | 16317 | 21 | Slide | -120.62 | 16315 | 86.93 | 136.87 | 10952.25 | -4023.88 | 4713.59 | -4023.88 | 0.52 |  |  | 50 | 50.07 | 401.14 | 13.77 | 36 | 5840.93 | 5463.3 | 377.63 | 159.8 | 270 | 168.13 | 150
03/21/2022 | 16:27 | 16:47 | 0.33333 | 16317 | 16384 | 67 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 65.18; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 201 | 6031.36 | 4830.25 | 1201.11 | 150.8 | 270 | 168.13 | 150
03/21/2022 | 17:31 | 17:39 | 0.13333 | 16384 | 16406 | 22 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 55.79; Drilling Parameters FLOW: 401.19; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 165 | 5509.31 | 4816.2 | 693.11 | 150.8 | 270 | 168.13 | 150
03/21/2022 | 17:40 | 18:02 | 0.36667 | 16406 | 16473 | 67 | Rotate |  | 16409 | 87.32 | 136.44 | 10956.97 | -4092.15 | 4778.03 | -4092.15 | 0.62 |  |  | 30 | 68.95 | 401.3 | 13.77 | 182.73 | 5251.69 | 3872.07 | 1379.62 | 152.6 | 270 | 168.13 | 150
03/21/2022 | 18:07 | 18:19 | 0.2 | 16473 | 16487 | 14 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.97; Drilling Parameters FLOW: 401.33; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 70 | 4420.81 | 4484.97 | -64.16 | 156.2 | 270 | 188.67 | 150
03/21/2022 | 18:19 | 18:39 | 0.33333 | 16487 | 16501 | 14 | Slide | TTF: -146.55; Drilling Parameters WOB: 40; Drilling Parameters RPM: 49.99; Drilling Parameters FLOW: 401.35; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 42 | 4719.06 | 4232.48 | 486.58 | 156.2 | 270 | 188.67 | 150
03/21/2022 | 18:39 | 18:58 | 0.31667 | 16501 | 16570 | 69 | Rotate |  | 16502 | 87.26 | 139.86 | 10961.37 | -4161.34 | 4840 | -4161.34 | 3.67 |  |  | 30 | 67.62 | 401.34 | 13.77 | 217.89 | 5196.73 | 5348.29 | -151.56 | 147.2 | 270 | 188.67 | 150
03/21/2022 | 19:02 | 19:14 | 0.2 | 16570 | 16580 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.99; Drilling Parameters FLOW: 401.37; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 50 | 4628.4 | 4571.42 | 56.98 | 147.2 | 270 | 186.44 | 150
03/21/2022 | 19:14 | 19:50 | 0.6 | 16580 | 16605 | 25 | Slide | -118.81 | 16597 | 87.15 | 136.62 | 10966 | -4232.11 | 4903.19 | -4232.11 | 3.41 |  |  | 40 | 49.99 | 401.53 | 13.77 | 41.67 | 5018.54 | 4558.85 | 459.69 | 147.2 | 270 | 186.44 | 150
03/21/2022 | 19:50 | 20:07 | 0.28333 | 16605 | 16664 | 59 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 58.73; Drilling Parameters FLOW: 401.37; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 208.24 | 5270.91 | 4709.78 | 561.13 | 141.8 | 270 | 186.44 | 150
03/21/2022 | 20:11 | 20:21 | 0.16667 | 16664 | 16675 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.97; Drilling Parameters FLOW: 401.34; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 66 | 4419.58 | 4434 | -14.42 | 141.8 | 270 | 191.39 | 150
03/21/2022 | 20:21 | 20:57 | 0.6 | 16675 | 16697 | 22 | Slide | -148.42 | 16692 | 86 | 133.43 | 10971.68 | -4299.18 | 4970.2 | -4299.18 | 3.56 |  |  | 40 | 49.95 | 401.2 | 13.77 | 36.67 | 5138.49 | 4626.36 | 512.13 | 141.8 | 270 | 191.39 | 150
03/21/2022 | 20:57 | 21:17 | 0.33333 | 16697 | 16759 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 66.93; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 186 | 5325.72 | 4264.73 | 1060.99 | 140 | 270 | 191.39 | 150
03/21/2022 | 21:22 | 21:51 | 0.48333 | 16759 | 16854 | 95 | Rotate |  | 16786 | 86.26 | 132.8 | 10978.02 | -4363.28 | 5038.66 | -4363.28 | 0.72 |  |  | 30 | 66.07 | 401.35 | 13.77 | 196.55 | 5198.44 | 4644.38 | 554.06 | 150.8 | 270 | 186.44 | 150
03/21/2022 | 21:55 | 22:22 | 0.45 | 16854 | 16948 | 94 | Rotate |  | 16881 | 88.55 | 132.11 | 10982.32 | -4427.34 | 5108.68 | -4427.34 | 2.52 |  |  | 30 | 66.68 | 401.33 | 13.77 | 208.89 | 5118.3 | 4794.95 | 323.35 | 156.2 | 270 | 186.44 | 150
03/21/2022 | 22:26 | 22:43 | 0.28333 | 16948 | 16960 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.93; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 42.35 | 4428.13 | 4083.61 | 344.52 | 156.2 | 270 | 178.19 | 150
03/21/2022 | 22:43 | 23:26 | 0.71667 | 16960 | 16980 | 20 | Slide | 159.42 | 16974 | 84.8 | 132.24 | 10987.71 | -4489.66 | 5177.47 | -4489.66 | 4.03 |  |  | 40 | 50.11 | 401.31 | 13.77 | 27.91 | 5253.45 | 4843.7 | 409.75 | 156.2 | 270 | 209.14 | 150
03/21/2022 | 23:26 | 23:53 | 0.45 | 16980 | 17042 | 62 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 67.69; Drilling Parameters FLOW: 401.34; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 137.78 | 5345.14 | 4611.54 | 733.6 | 154.4 | 270 | 167.26 | 150
03/21/2022 | 23:58 | 24:00 | 0.033333 | 17042 | 17044 | 2 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.94; Drilling Parameters FLOW: 401.28; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 60 | 5013.18 | 4083.85 | 929.33 | 154.4 | 270 | 167.26 | 150
03/22/2022 | 00:00 | 00:10 | 0.16667 | 17044 | 17052 | 8 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.92; Drilling Parameters FLOW: 401.36; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 48 | 4842.22 | 4807.76 | 34.46 | 159.8 | 270 | 169.47 | 150
03/22/2022 | 00:10 | 00:25 | 0.25 | 17052 | 17059 | 7 | Slide | TTF: 64.95; Drilling Parameters WOB: 40; Drilling Parameters RPM: 49.93; Drilling Parameters FLOW: 401.29; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 28 | 5284.95 | 4858.88 | 426.07 | 159.8 | 270 | 169.47 | 150
03/22/2022 | 00:25 | 00:49 | 0.4 | 17059 | 17136 | 77 | Rotate |  | 17068 | 84.3 | 133.64 | 10996.64 | -4553.4 | 5245.97 | -4553.4 | 1.58 |  |  | 30 | 67.25 | 401.29 | 13.77 | 192.5 | 5600.59 | 4674.18 | 926.41 | 168.8 | 270 | 169.47 | 150
03/22/2022 | 00:53 | 01:03 | 0.16667 | 17136 | 17146 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.94; Drilling Parameters FLOW: 401.45; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 60 | 4812.73 | 4886.84 | -74.11 | 168.8 | 270 | 190.67 | 150
03/22/2022 | 01:03 | 01:42 | 0.65 | 17146 | 17163 | 17 | Slide | TTF: 5.44; Drilling Parameters WOB: 40; Drilling Parameters RPM: 50.02; Drilling Parameters FLOW: 401.52; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 26.15 | 5539.03 | 4922.13 | 616.9 | 168.8 | 270 | 190.67 | 150
03/22/2022 | 01:42 | 02:06 | 0.4 | 17163 | 17230 | 67 | Rotate |  | 17163 | 85.55 | 134.14 | 11005.05 | -4619.01 | 5314.17 | -4619.01 | 1.42 |  |  | 30 | 67.49 | 401.35 | 13.77 | 167.5 | 4883.28 | 3739.79 | 1143.49 | 163.4 | 270 | 178.16 | 150
03/22/2022 | 02:11 | 02:44 | 0.55 | 17230 | 17324 | 94 | Rotate |  | 17256 | 85.93 | 133.66 | 11011.95 | -4683.31 | 5380.99 | -4683.31 | 0.66 |  |  | 30 | 49.85 | 401.26 | 13.77 | 170.91 | 4232.48 | 3298.44 | 934.04 | 165.2 | 270 | 180.59 | 150
03/22/2022 | 02:49 | 03:03 | 0.23333 | 17324 | 17334 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.94; Drilling Parameters FLOW: 401.26; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 42.86 | 4447.01 | 4406.39 | 40.62 | 165.2 | 270 | 187.5 | 150
03/22/2022 | 03:03 | 03:24 | 0.35 | 17334 | 17350 | 16 | Slide | TTF: 12.24; Drilling Parameters WOB: 40; Drilling Parameters RPM: 49.94; Drilling Parameters FLOW: 401.15; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 45.71 | 5080.89 | 4646.56 | 434.33 | 165.2 | 270 | 187.5 | 150
03/22/2022 | 03:24 | 03:45 | 0.35 | 17350 | 17418 | 68 | Rotate |  | 17350 | 89.02 | 134.22 | 11016.1 | -4748.47 | 5448.61 | -4748.47 | 3.34 |  |  | 30 | 65.93 | 401.3 | 13.77 | 194.29 | 5287.23 | 4847.1 | 440.13 | 154.4 | 270 | 187.5 | 150
03/22/2022 | 03:50 | 04:21 | 0.51667 | 17418 | 17512 | 94 | Rotate |  | 17444 | 87.67 | 133.69 | 11018.81 | -4813.69 | 5516.24 | -4813.69 | 1.54 |  |  | 30 | 69.52 | 401.34 | 13.77 | 181.94 | 5303.05 | 4787.21 | 515.84 | 154.4 | 270 | 187.5 | 150
03/22/2022 | 04:25 | 04:38 | 0.21667 | 17512 | 17524 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.91; Drilling Parameters FLOW: 401.33; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 55.38 | 4539.27 | 4524.07 | 15.2 | 154.4 | 270 | 192.97 | 150
03/22/2022 | 04:38 | 04:58 | 0.33333 | 17524 | 17534 | 10 | Slide | TTF: 38.94; Drilling Parameters WOB: 40; Drilling Parameters RPM: 49.97; Drilling Parameters FLOW: 401.38; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 30 | 5227.81 | 4754.73 | 473.08 | 154.4 | 270 | 192.97 | 150
03/22/2022 | 04:58 | 05:19 | 0.35 | 17534 | 17607 | 73 | Rotate |  | 17539 | 87.64 | 134.59 | 11022.7 | -4879.79 | 5584.36 | -4879.79 | 0.95 |  |  | 30 | 66.91 | 401.26 | 13.77 | 208.57 | 5410.15 | 4218.85 | 1191.3 | 145.4 | 270 | 192.97 | 150
03/22/2022 | 05:23 | 05:33 | 0.16667 | 17607 | 17620 | 13 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 54.47; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 78 | 4405.82 | 4503.24 | -97.42 | 145.4 | 270 | 192.97 | 150
03/22/2022 | 05:33 | 05:48 | 0.25 | 17620 | 17630 | 10 | Slide | TTF: 5.09; Drilling Parameters WOB: 50; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 401.32; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 40 | 4929.06 | 4518.65 | 410.41 | 154.4 | 270 | 192.97 | 150
03/22/2022 | 05:48 | 06:11 | 0.38333 | 17630 | 17702 | 72 | Rotate |  | 17633 | 91.04 | 135.14 | 11023.78 | -4946.09 | 5650.97 | -4946.09 | 3.66 |  |  | 30 | 66.34 | 401.32 | 13.77 | 187.83 | 5252.54 | 4948.71 | 303.83 | 152.6 | 270 | 167.37 | 150
03/22/2022 | 06:19 | 06:29 | 0.16667 | 17702 | 17713 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.91; Drilling Parameters FLOW: 401.41; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 66 | 4472.9 | 4578.01 | -105.11 | 156.2 | 270 | 167.37 | 150
03/22/2022 | 06:29 | 07:14 | 0.75 | 17713 | 17731 | 18 | Slide | 80.63 | 17728 | 91.43 | 133.91 | 11021.73 | -5012.69 | 5718.69 | -5012.69 | 1.36 |  |  | 50 | 49.9 | 401.17 | 13.77 | 24 | 5167.24 | 4682.71 | 484.53 | 156.2 | 270 | 167.37 | 150
03/22/2022 | 07:14 | 07:44 | 0.5 | 17731 | 17798 | 67 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 67.21; Drilling Parameters FLOW: 401.37; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 134 | 5333.03 | 4234.07 | 1098.96 | 145.4 | 270 | 167.56 | 150
03/22/2022 | 07:54 | 08:04 | 0.16667 | 17798 | 17807 | 9 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 49.89; Drilling Parameters FLOW: 401.41; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 54 | 4451.76 | 4611.01 | -159.25 | 147.2 | 270 | 167.56 | 150
03/22/2022 | 08:04 | 08:28 | 0.4 | 17807 | 17818 | 11 | Slide | TTF: 145.6; Drilling Parameters WOB: 50; Drilling Parameters RPM: 49.98; Drilling Parameters FLOW: 401.31; Drilling Parameters ROP: 27.5 | 4315.5 | 4274.01 | 41.49 | 256 | 270 | 177.07 | 150
03/22/2022 | 19:44 | 20:32 | 0.8 | 17818 | 17837 | 19 | Slide | 166.73 | 17822 | 89.66 | 134.12 | 11020.84 | -5078 | 5786.28 | -5078 | 1.9 |  |  | 50 | 49.98 | 398.29 | 13.77 | 23.75 | 5390 | 4993.7 | 396.3 | 256 | 270 | 177.07 | 150
03/22/2022 | 20:32 | 21:02 | 0.5 | 17837 | 17889.9 | 52.9 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 54.12; Drilling Parameters FLOW: 396.03; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 105.8 | 5278.63 | 3995.61 | 1283.02 | 177.8 | 270 | 178.09 | 150

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 370 |  | North Reference: |  | GRID |  | Total Drilled: |  | 1539.04
Site: |  |  |  |  | Klondike - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 120
Well Name: |  |  |  |  | Mill H08 |  |  | Survey / Gamma Offset: |  |  |  |  | 64.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 370 |  | VS Azimuth: |  | 134.53 |  | Rotate: |  | 1419.04
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
03/24/2021 | 10:10 | 10:31 | 0.35 | 17890 | 17910 | 20 | Slide | 0 | 17910 | 85.77 | 134.76 | 11024.35 | -5139.55 | 5849.05 | -5139.55 | 4.48 |  |  | 25 |  | 400 |  | 57.14 | 5400 | 5200 | 200 | 246 | 220 | 165 | 130
03/24/2022 | 10:50 | 10:54 | 0.066667 | 17910 | 17973 | 63 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 64.35; Drilling Parameters FLOW: 401.39; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 945 | 5576.53 | 3731.98 | 1844.55 | 165.2 | 220 | 166.73 | 130
03/24/2022 | 11:02 | 11:31 | 0.48333 | 17973 | 18068 | 95 | Rotate |  | 18005 | 84.91 | 134.69 | 11032.06 | -5206.18 | 5916.32 | -5206.18 | 0.91 |  |  | 25 | 65.95 | 429.58 | 13.77 | 196.55 | 5607.29 | 3318.17 | 2289.12 | 165.2 | 220 | 164.92 | 130
03/24/2022 | 12:20 | 12:57 | 0.61667 | 18068 | 18163 | 95 | Rotate |  | 18098 | 84.56 | 134.82 | 11040.6 | -5271.38 | 5982.08 | -5271.38 | 0.4 |  |  | 25 | 67.97 | 401.33 | 13.77 | 154.05 | 5967.18 | 3777.85 | 2189.33 | 158 | 220 | 164.35 | 130
03/24/2022 | 13:04 | 13:17 | 0.21667 | 18163 | 18178 | 15 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 59.23; Drilling Parameters FLOW: 375.81; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 69.23 | 5039.45 | 5064.77 | -25.32 | 156.2 | 220 | 164.74 | 130
03/24/2022 | 13:17 | 13:43 | 0.43333 | 18178 | 18196 | 18 | Slide | 4.81 | 18193 | 85.53 | 134.82 | 11048.8 | -5338.09 | 6049.22 | -5338.09 | 1.02 |  |  | 25 | 50.01 | 375.77 | 13.77 | 41.54 | 5073.49 | 4521.93 | 551.56 | 156.2 | 220 | 164.74 | 130
03/24/2022 | 13:43 | 14:01 | 0.3 | 18196 | 18258 | 62 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 67.27; Drilling Parameters FLOW: 375.82; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 206.67 | 5480.17 | 4773.93 | 706.24 | 140 | 220 | 166.03 | 130
03/24/2022 | 14:07 | 14:37 | 0.5 | 18258 | 18305 | 47 | Rotate |  | 18288 | 85.18 | 134.24 | 11056.5 | -5404.5 | 6116.72 | -5404.5 | 0.71 |  |  | 25 | 65.39 | 375.76 | 13.77 | 94 | 4592.03 | 4809.63 | -217.6 | 154.4 | 220 | 166.38 | 130
03/24/2022 | 14:37 | 14:58 | 0.35 | 18305 | 18322 | 17 | Slide | TTF: -31.73; Drilling Parameters WOB: 25; Drilling Parameters RPM: 50.01; Drilling Parameters FLOW: 375.84; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 48.57 | 5508.25 | 5132.03 | 376.22 | 154.4 | 220 | 166.38 | 130
03/24/2022 | 14:58 | 15:08 | 0.16667 | 18322 | 18353 | 31 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 62.75; Drilling Parameters FLOW: 375.8; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 186 | 5837.73 | 4354.06 | 1483.67 | 136.4 | 220 | 166.04 | 130
03/24/2022 | 15:15 | 15:28 | 0.21667 | 18353 | 18372 | 19 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.89; Drilling Parameters FLOW: 375.78; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 87.69 | 5001.92 | 4999.78 | 2.14 | 145.4 | 220 | 167.87 | 130
03/24/2022 | 15:28 | 15:51 | 0.38333 | 18372 | 18387 | 15 | Slide | -3.35 | 18382 | 88.05 | 134.59 | 11062.05 | -5470.16 | 6183.74 | -5470.16 | 3.08 |  |  | 25 | 49.91 | 375.53 | 13.77 | 39.13 | 5056.36 | 4959.35 | 97.01 | 145.4 | 220 | 167.56 | 130
03/24/2022 | 15:51 | 16:48 | 0.95 | 18387 | 18448 | 61 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 67.02; Drilling Parameters FLOW: 375.81; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 64.21 | 5870.98 | 3593.93 | 2277.05 | 145.4 | 220 | 166.43 | 130
03/24/2022 | 16:54 | 17:26 | 0.53333 | 18448 | 18544.14 | 96.14 | Rotate |  | 18477 | 88.98 | 134.63 | 11064.51 | -5536.85 | 6251.34 | -5536.85 | 0.98 |  |  | 25 | 67.38 | 375.8 | 13.77 | 180.26 | 5185.67 | 3397.98 | 1787.69 | 145.4 | 220 | 166.46 | 130
03/24/2022 | 17:37 | 18:14 | 0.61667 | 18544.14 | 18636 | 91.86 | Rotate |  | 18571 | 89.33 | 134.29 | 11065.89 | -5602.69 | 6318.43 | -5602.69 | 0.52 |  |  | 25 | 67.38 | 375.8 | 13.77 | 148.96 | 5185.67 | 3397.98 | 1787.69 | 145.4 | 220 | 166.46 | 130
03/24/2022 | 18:20 | 18:44 | 0.4 | 18636 | 18735 | 99 | Rotate |  | 18666 | 89.58 | 134.17 | 11066.8 | -5668.95 | 6386.5 | -5668.95 | 0.29 |  |  | 25 | 66.18 | 375.82 | 13.77 | 247.5 | 5780.86 | 4712.31 | 1068.55 | 163.4 | 220 | 166.46 | 130
03/24/2022 | 18:49 | 19:00 | 0.18333 | 18735 | 18745 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.92; Drilling Parameters FLOW: 375.81; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 54.55 | 4904.45 | 4749.46 | 154.99 | 163.4 | 220 | 178.74 | 130
03/24/2022 | 19:00 | 19:24 | 0.4 | 18745 | 18762 | 17 | Slide | 141.33 | 18760 | 87.58 | 135.29 | 11069.13 | -5735.08 | 6453.25 | -5735.08 | 2.44 |  |  | 25 | 49.93 | 375.84 | 13.77 | 42.5 | 5456.12 | 5165.48 | 290.64 | 163.4 | 220 | 178.74 | 130
03/24/2022 | 19:24 | 19:47 | 0.38333 | 18762 | 18830 | 68 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 65.43; Drilling Parameters FLOW: 375.83; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 177.39 | 5487.04 | 4026.36 | 1460.68 | 150.8 | 220 | 178.74 | 130
03/24/2022 | 19:51 | 20:26 | 0.58333 | 18830 | 18920 | 90 | Rotate |  | 18856 | 88.28 | 135.68 | 11072.6 | -5803.49 | 6520.51 | -5803.49 | 0.83 |  |  | 25 | 68.1 | 375.8 | 13.77 | 154.29 | 5812 | 5900.67 | -88.67 | 159.8 | 220 | 168.57 | 130
03/24/2022 | 20:30 | 20:55 | 0.41667 | 18920 | 19014 | 94 | Rotate |  | 18951 | 88.24 | 135.42 | 11075.48 | -5871.27 | 6587.01 | -5871.27 | 0.28 |  |  | 25 | 65.95 | 375.82 | 13.77 | 225.6 | 5791.17 | 5298.56 | 492.61 | 165.2 | 220 | 1778.74 | 130
03/24/2022 | 21:00 | 21:13 | 0.21667 | 19014 | 19026 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.91; Drilling Parameters FLOW: 375.88; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 55.38 | 4606.41 | 4614.02 | -7.61 | 165.2 | 220 | 182.44 | 130
03/24/2022 | 21:13 | 21:32 | 0.31667 | 19026 | 19039 | 13 | Slide | TTF: -172.41; Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.94; Drilling Parameters FLOW: 375.73; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 41.05 | 5302.72 | 4803.85 | 498.87 | 165.2 | 220 | 177.95 | 130
03/24/2022 | 21:32 | 21:56 | 0.4 | 19039 | 19110 | 71 | Rotate |  | 19045 | 86.07 | 134.41 | 11080.15 | -5937.56 | 6653.49 | -5937.56 | 2.55 |  |  | 25 | 67.66 | 375.83 | 13.77 | 177.5 | 5881.26 | 4389.78 | 1491.48 | 150.8 | 220 | 176.02 | 130
03/24/2022 | 22:00 | 22:29 | 0.48333 | 19110 | 19202 | 92 | Rotate |  | 19137 | 85.5 | 133.71 | 11086.91 | -6001.36 | 6719.42 | -6001.36 | 0.98 |  |  | 25 | 65.74 | 375.83 | 13.77 | 190.34 | 5949.41 | 5681.98 | 267.43 | 163.4 | 220 | 176.02 | 130
03/24/2022 | 22:33 | 23:02 | 0.48333 | 19202 | 19296 | 94 | Rotate |  | 19232 | 84.36 | 133.91 | 11095.3 | -6066.87 | 6787.71 | -6066.87 | 1.22 |  |  | 25 | 65.58 | 375.83 | 13.77 | 194.48 | 5830.03 | 3116.45 | 2713.58 | 167 | 220 | 180.2 | 130
03/24/2022 | 23:11 | 23:23 | 0.2 | 19296 | 19307 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.89; Drilling Parameters FLOW: 375.85; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 55 | 5124.66 | 5199.43 | -74.77 | 167 | 220 | 186.24 | 130
03/24/2022 | 23:23 | 23:50 | 0.45 | 19307 | 19327 | 20 | Slide | TTF: 3.73; Drilling Parameters WOB: 25; Drilling Parameters RPM: 49.82; Drilling Parameters FLOW: 375.89; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 44.44 | 5387.61 | 4762.84 | 624.77 | 167 | 220 | 186.24 | 130
03/24/2022 | 23:50 | 24:00 | 0.16667 | 19327 | 19359 | 32 | Rotate |  | 19327 | 85.32 | 133.88 | 11103.85 | -6132.47 | 6855.89 | -6132.47 | 1.01 |  |  | 25 | 60.28 | 375.82 | 13.77 | 192 | 5473.27 | 4762 | 711.27 | 152.6 | 220 | 186.24 | 130
03/25/2022 | 00:00 | 00:09 | 0.15 | 19359 | 19390 | 31 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 63.54; Drilling Parameters FLOW: 375.81; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 206.67 | 5577.87 | 2829.37 | 2748.5 | 152.6 | 220 | 186.24 | 130
03/25/2022 | 00:18 | 00:30 | 0.2 | 19390 | 19429.04 | 39.04 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 62.54; Drilling Parameters FLOW: 375.82; Drilling Parameters Tq: 13.77; Drilling Parameters ROP: 195.2 | 5495.48 | 4436.15 | 1059.33 | 161.6 | 220 | 170.31 | 130