## Summary
Magnolia Oil & Gas / Ozark 1H / LTX1126621 / Patterson 248
Report Date: | 07/06/2021 | Current Depth: | 20437
Start Date: | 06/18/2021 | Casing Depth: | 12238
Daily Cost: | 8850 | Distance to TD:
Well Cost: | 337560 | Average ROP: | 0
Drilling Hours: | 14.58 | Svy MD: | 20437
24Hr Forcast: | Released from location, PIYAH!! | Svy Inc: | 87.64
Current BHA: | BHA 6 | Svy Azi: | 143.88
Current BRT Hrs: | 56.67 | Svy TVD: | 13098.24
Bit Make / Model: | Security / GTD64M | Svy NS: | -6156.22
POOH in last 24Hrs: | Yes | Svy EW: | 4801.87
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Josh Ray | MWD Day: | Danny Veronie
Directional Driller Night: | Xavier Cantu | MWD Night: | Jason Smetters
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 351
24Hr Summary: | POOH. LDDP, LD tools, PIYAH!! | Max BHT 24Hrs: | 0
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
14954251 | 5/6 9.5 1.80 Slick x 5 3/8" stab | Baker |  | In Hole |  | 25.42 | 25.42
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
ZSB775203 | UBHO |  |  | Clean
ZSB775192 | UBHO |  |  | Dirty |  | 61.95 | 61.95
ZSB500025 | UBHO | PDCI |  | Clean
ZSB500049 | UBHO | PDCI |  | In Hole |  | 123.33 | 123.33

## Well Summary
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Ozark 1H
|  |  |  | County: |  | Fayette |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Total Drilled (Usft): |  | 20329 |  |  | Total Days: |  | 19
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 3845 | 3737 |  | 363.4 |  | 4.12 | 10.28 | 2.33 | 22.5
2 | 2 | 9.875 | 3845 | 12250 | 8405 |  | 191.02 |  | 6.9 | 44 | 5.33 | 90
3 | 3 | 6.75 | 12250 | 16230 | 3980 |  | 103.15 |  | 20.9 | 38.58 | 12.75 | 84.42
4 | 4 | 6.75 | 16230 | 18363 | 2133 |  | 127.98 |  | 3.52 | 16.67 | 14.08 | 59.08
5 | 5 | 6.75 | 18363 | 18971 | 608 |  | 99.95 |  | 3.62 | 6.08 | 9.75 | 42 | YES
6 | 6 | 6.75 | 18971 | 20437 | 1466 |  | 100.53 |  | 2.05 | 14.58 | 10.83 | 56.67
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | SPL616 |  | 13.5 |  |  |  |  | 1.353 | 3737 | 10.2833 | 363.4
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 0-1-WT-G-X-I-CT-TD |  | 1.491 | 8405 | 44 | 191.02
3 | Security |  | GTD64M |  | 6.75 | New |  | 0-1-WT-A-X-I-NO-BHA |  | 1.491 | 3980 | 38.5833 | 103.15
4 | Security |  | GTD64M |  | 6.75 | New |  | 0-1-WT-G-X-I-PN-PP |  | 1.491 | 2133 | 16.6667 | 127.98
5 | Security |  | GTD64M |  | 6.75 | New |  | 0-1-WT-G-X-I-PN-BHA |  | 1.491 | 608 | 6.0833 | 99.95
6 | Security |  | GTD64M |  | 6.75 | New |  | 0-1-LT-S-X-I-NO-TD |  | 1.491 | 1466 | 14.5833 | 100.53
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.78 | 3737 |  | 363.4
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 6.04 | 8405 |  | 191.02
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.05 | 3980 |  | 103.15
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 3.96 | 2133 |  | 127.98
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4 | 608 |  | 99.95
6 | Baker Hughes |  | 5/6 9.5 |  | 5/6 | 9.5 | 5 | 1.8 | 4.32 | 1466 |  | 100.53
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | Xavier Cantu |  | Danny Veronie |  | Jason Smetters |  | Brandon Parks |  | James Dyer |  | Peter Langille
Jesse Taylor Josh Ray | [5 empty] | Jason Smitters |  | Kevin Burk |  | Kevin
Josh Ray
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.94 / 0.52 |  | 3737 |  | 363.52 |  | 5.17 / 0.00 |  | 1 |  | 10.28
INT: INTERMEDIATE |  |  | 2.30 / 1.89 |  | 8068 |  | 267.24 |  | 5.83 / 0.00 |  | 1 |  | 30.19
CRV: CURVE |  |  | 2.76 / 0.61 |  | 337 |  | 24.38 |  |  |  | 1 |  | 13.82
CRV2: CURVE 2 |  |  | 1.92 / 0.53 |  | 694 |  | 67.71 |  |  |  | 1 |  | 10.25
LAT: LATERAL |  |  | 8.82 / 7.86 |  | 7493 |  | 114.12 |  |  |  | 4 |  | 65.66
Total |  |  | 18.73 |  | 20329 |  | 156.14 |  | 11.00 / 0.00 |  | 6 |  | 130.2
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 3845.00 | 402.58 | 3583.00 | 111.59 | 154.00 | 4.12 | 3737.00 | 363.52 | 10.28 | 1.38
INT: INTERMEDIATE-BHA 2 |  |  | 3845.00 | 11913.00 | 313.97 | 7821.00 | 46.78 | 247.00 | 3.06 | 8068.00 | 267.24 | 30.19 | 5.28
CRV: CURVE-BHA 2 |  |  | 11913.00 | 12250.00 | 50.00 | 4.00 | 24.24 | 333.00 | 98.81 | 337.00 | 24.38 | 13.82 | 13.74
CRV2: CURVE 2-BHA 3 |  |  | 12250.00 | 12944.00 | 67.38 | 95.00 | 67.76 | 599.00 | 86.31 | 694.00 | 67.71 | 10.25 | 8.84
LAT: LATERAL-BHA 3 |  |  | 12944.00 | 16230.00 | 141.41 | 3053.00 | 34.47 | 233.00 | 7.09 | 3286.00 | 115.91 | 28.35 | 6.76
LAT: LATERAL-BHA 4 |  |  | 16230.00 | 18363.00 | 155.32 | 2058.00 | 21.99 | 75.00 | 3.52 | 2133.00 | 128.03 | 16.66 | 3.41
LAT: LATERAL-BHA 5 |  |  | 18363.00 | 18971.00 | 115.58 | 586.00 | 22.00 | 22.00 | 3.62 | 608.00 | 100.16 | 6.07 | 1.00
LAT: LATERAL-BHA 6 |  |  | 18971.00 | 20437.00 | 109.04 | 1436.00 | 21.28 | 30.00 | 2.05 | 1466.00 | 100.55 | 14.58 | 1.41
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1126621 | Total Drilled(Usft) | 20329.00
Operator | Magnolia Oil & Gas | Drilling Hours | 130.20
Well Name | Ozark 1H | Avg ROP(Usft/hr) | 156.14
Rig | Patterson 248 | Rotary Drilled(Usft) | 18636.00
State | Texas | Rotary Hours | 88.37
County | Fayette | Rotary ROP(Usft/hr) | 210.89
Formation | Austin Chalk | Rotary % | 91.67
Start Date | 06/18/2021 | Slide Drilled(Usft) | 1693.00
End Date | 07/06/2021 | Slide Hours | 41.83
Days On Well | 19 | Slide ROP(Usft/hr) | 40.47
Start Depth (Usft) | 108.00 | Slide % | 8.33
End Depth (Usft) | 20437.00
Total Drilled (Usft) | 20329.00
# BHA's | 6
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 16.25 / 0.00
Phase Data
Phase | SUR | INT | CRV | CRV2 | LAT
Start Date | 06/18/2021 | 06/20/2021 | 06/23/2021 | 06/26/2021 | 06/27/2021
End Date | 06/20/2021 | 06/23/2021 | 06/25/2021 | 06/27/2021 | 07/06/2021
Total Days | 2.94 | 2.31 | 2.76 | 1.92 | 8.83
Start Depth (Usft) | 108.00 | 3845.00 | 11913.00 | 12250.00 | 12944.00
End Depth (Usft) | 3845.00 | 11913.00 | 12250.00 | 12944.00 | 20437.00
Total Drilled(Usft) | 3737.00 | 8068.00 | 337.00 | 694.00 | 7493.00
Drilling Hours | 10.28 | 30.17 | 13.83 | 10.25 | 65.67
Circulating Hours | 2.33 | 3.58 | 1.75 | 4.08 | 43.33
Total D&C Hours | 12.62 | 33.75 | 15.58 | 14.33 | 109.00
Avg ROP(Usft/hr) | 363.40 | 267.45 | 24.36 | 67.71 | 114.11
Rotary Drilled(Usft) | 3583.00 | 7821.00 | 4.00 | 95.00 | 7133.00
Rotary Hours | 8.90 | 24.88 | 0.08 | 1.42 | 53.08
Rotary ROP(Usft/hr) | 402.58 | 314.31 | 48.00 | 67.06 | 134.37
Rotary % | 95.88 | 96.94 | 1.19 | 13.69 | 95.20
Slide Drilled(Usft) | 154.00 | 247.00 | 333.00 | 599.00 | 360.00
Slide Hours | 1.38 | 5.28 | 13.75 | 8.83 | 12.58
Slide ROP(Usft/hr) | 111.33 | 46.75 | 24.22 | 67.81 | 28.61
Slide % | 4.12 | 3.06 | 98.81 | 86.31 | 4.80
# BHA | 1 | 1 | 1 | 1 | 4
# Motor Failures | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 5.67 / 0.00 | 7.08 / 0.00 | 0.00 / 0.00 | 1.00 / 0.00 | 2.50 / 0.00
Total Phase Hrs | 12.57 | 45.25 | 14.75 | 12.83 | 188.67
Phase ROP (Usft/hr) | 297.37 | 178.30 | 22.85 | 54.08 | 39.72
Avg Motor Yield (°/100ft) | 7.38 | 8.71 | 4.55 | 11.68 | 15.53
Avg Rotary DLS (°/100ft) | 0.22 | 0.34 | 0.00 | 0.00 | 0.82
Avg Rotary TF | 157.37 | -22.42 | 0.00 | 0.00 | 40.43
Avg Slide Length (Usft) | 12.83 | 13.00 | 55.50 | 66.56 | 13.85
# Slides | 12 | 19 | 6 | 9 | 26
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5 | 6
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4 | BHA 5 | BHA 6
Bit Size | 13.500 | 9.875 | 6.750 | 6.750 | 6.750 | 6.750
Bit Make/Model | Ulterra / SPL616 | Ulterra / SPL613 | Security / GTD64M | Security / GTD64M | Security / GTD64M | Security / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491 | 1.491 | 1.491
Grade In |  | New | New | New | New | New
Grade Out |  | 0-1-WT-G-X-I-CT-TD | 0-1-WT-A-X-I-NO-BHA | 0-1-WT-G-X-I-PN-PP | 0-1-WT-G-X-I-PN-BHA | 0-1-LT-S-X-I-NO-TD
Motor SN | PPM800053 | PPM800059 | PPM250010 | PPM250022 | PPM250005 | 14954251
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | Baker Hughes / 5/6 9.5
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8 | 5/6 / 9.5
WOB (klbs) | 25.00 / 29.23 / 35.00 | 10.00 / 26.09 / 35.00 | 14.00 / 27.25 / 40.00 | 20.00 / 23.03 / 25.00 | 15.00 / 21.91 / 28.00 | 6.00 / 18.18 / 25.00
Diff P (psi) | 200.00 / 437.67 / 680.00 | 300.00 / 618.30 / 950.00 | 200.00 / 831.17 / 1300.00 | 300.00 / 884.21 / 1000.00 | 250.00 / 627.27 / 750.00 | 200.00 / 588.64 / 700.00
Bend | 1.500 | 2.000 | 2.120 | 2.120 | 2.120 | 1.800
Date In | 06/18/2021 | 06/20/2021 | 06/26/2021 | 06/30/2021 | 07/02/2021 | 07/04/2021
Date Out | 06/19/2021 | 06/24/2021 | 06/29/2021 | 07/02/2021 | 07/04/2021 | 07/06/2021
Time In | 21:30 | 24:00 | 11:35 | 02:00 | 14:00 | 09:20
Time Out | 20:00 | 18:00 | 24:00 | 13:05 | 08:00 | 18:00
BRT Hrs | 22.50 | 90.00 | 84.42 | 59.08 | 42.00 | 56.67
Start Depth (Usft) | 108.00 | 3845.00 | 12250.00 | 16230.00 | 18363.00 | 18971.00
End Depth (Usft) | 3845.00 | 12250.00 | 16230.00 | 18363.00 | 18971.00 | 20437.00
Total Drilled(Usft) | 3737.00 | 8405.00 | 3980.00 | 2133.00 | 608.00 | 1466.00
Drilling Hours | 10.28 | 44.00 | 38.58 | 16.67 | 6.08 | 14.58
Circulating Hours | 2.33 | 5.33 | 12.75 | 14.08 | 9.75 | 10.83
Total D&C Hours | 12.62 | 49.33 | 51.33 | 30.75 | 15.83 | 25.42
Avg ROP(Usft/hr) | 363.40 | 191.02 | 103.15 | 127.98 | 99.95 | 100.53
Rotary Drilled(Usft) | 3583.00 | 7825.00 | 3148.00 | 2058.00 | 586.00 | 1436.00
Rotary Hours | 8.90 | 24.97 | 23.00 | 13.25 | 5.08 | 13.17
Rotary ROP(Usft/hr) | 402.58 | 313.42 | 136.87 | 155.32 | 115.28 | 109.06
Rotary % | 95.88 | 93.10 | 79.10 | 96.48 | 96.38 | 97.95
Slide Drilled(Usft) | 154.00 | 580.00 | 832.00 | 75.00 | 22.00 | 30.00
Slide Hours | 1.38 | 19.03 | 15.58 | 3.42 | 1.00 | 1.42
Slide ROP(Usft/hr) | 111.33 | 30.47 | 53.39 | 21.95 | 22.00 | 21.18
Slide % | 4.12 | 6.90 | 20.90 | 3.52 | 3.62 | 2.05
Motor Failure | NO | NO | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | YES | YES | NO
LIH | NO | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 7.38 | 8.19 | 13.91 | 17.09 | 17.99 | 12.02
Avg Rotary DLS (°/100ft) | 0.22 | 0.34 | 0.61 | 0.69 | 0.59 | 0.75
Avg Rotary TF | 157.37 | -22.42 | 46.18 | 38.24 | 36.09 | 45.69
Avg Slide Length (Usft) | 12.83 | 23.20 | 34.67 | 10.71 | 11.00 | 15.00
# Slides | 12 | 25 | 24 | 7 | 2 | 2

## Personnel Report
|  | Job # | LTX1126621 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-149-33522 |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Ozark 1H
|  | Date: | 07/06/2021 |  | State: |  | Texas
[5 empty] | County: |  | Fayette
Ozark 1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Danny Veronie | Day MWD |  | 06/18/2021 - 00:00 | 07/06/2021 - 00:00 |  | 19.00 / 0.00
Jason Smetters | Night MWD |  | 06/23/2021 - 00:00 | 07/06/2021 - 00:00 |  | 14.00 / 0.00
Jason Smitters | Night MWD |  | 06/18/2021 - 00:00 | 06/22/2021 - 00:00 |  | 5.00 / 0.00
Jesse Taylor | Day DD |  | 06/18/2021 - 00:00 | 06/22/2021 - 00:00 |  | 5.00 / 0.00
Jesse Taylor Josh Ray | Day DD |  | 06/23/2021 - 00:00 | 06/23/2021 - 00:00 |  | 1.00 / 0.00
Josh Ray | Day DD |  | 06/24/2021 - 00:00 | 07/06/2021 - 00:00 |  | 13.00 / 0.00
NA | Trainee 1 |  | 06/26/2021 - 00:00 | 07/06/2021 - 00:00 |  | 11.00 / 0.00
NA | Trainee 2 |  | 06/26/2021 - 00:00 | 07/06/2021 - 00:00 |  | 11.00 / 0.00
NA | Rss Eng. 1 |  | 06/26/2021 - 00:00 | 07/06/2021 - 00:00 |  | 11.00 / 0.00
NA | Rss Eng. 2 |  | 06/26/2021 - 00:00 | 07/06/2021 - 00:00 |  | 11.00 / 0.00
NA | Third Man |  | 06/26/2021 - 00:00 | 07/06/2021 - 00:00 |  | 11.00 / 0.00
NA | Fourth Man |  | 06/26/2021 - 00:00 | 07/06/2021 - 00:00 |  | 11.00 / 0.00
Xavier Cantu | Night DD |  | 06/18/2021 - 00:00 | 07/06/2021 - 00:00 |  | 19.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1126621 | [5 empty] | State / County: |  |  |  | Texas / Fayette
|  |  |  | Well Name: |  |  | Ozark 1H | [7 empty] | Day DD: |  |  |  |  | Josh Ray | [5 empty] | API #: |  |  |  | 42-149-33522
|  |  |  | AFE #: |  |  | 21DD0111MG | [7 empty] | Night DD: |  |  |  |  | Xavier Cantu | [5 empty] | Company Man: |  |  |  | Brandon Parks
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Jason Smetters | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 06/18/2021 | 06/19/2021 | 06/20/2021 | 06/21/2021 | 06/22/2021 | 06/23/2021 | 06/24/2021 | 06/25/2021 | 06/26/2021 | 06/27/2021 | 06/28/2021 | 06/29/2021 | 06/30/2021 | 07/01/2021 | 07/02/2021 | 07/03/2021 | 07/04/2021 | 07/05/2021 | 07/06/2021 | 07/07/2021 | 07/08/2021 | 07/09/2021 | 07/10/2021 | 07/11/2021 | 07/12/2021 | 07/13/2021 | 07/14/2021 | 07/15/2021 | 07/16/2021 | 07/17/2021 | 07/18/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | GTD64M |  | Steel | 13509567 | 3 | 6 | [13 empty] | O | X | X | X | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13601236 | 4 | 12 | [7 empty] | O | X | X | X | X | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13594950 | 3 | 8 | [11 empty] | O | X | X | X | O | O | O | O
Cross Over |  | 8.25 | Crossover Sub |  | Steel | SD104164 | 2 | 7 | X | X | O | O | O | O | O
Cross Over |  |  | Crossover Sub |  | Steel | SD118777 | 0 | 7 | O | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD115530 | 5 | 7 | O | O | X | X | X | X | X
Cross Over |  |  | Crossover Sub |  | Steel | SD118021 | 0 | 7 | O | O | O | O | O | O | O
Cross Over |  | 6.125 | Crossover Sub |  | Steel | SD115076 | 5 | 7 | O | O | X | X | X | X | X
Cross Over |  |  | Crossover Sub |  | Steel | SD115656 | 0 | 7 | O | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD110296 | 0 | 7 | O | O | O | O | O | O | O
Cross Over |  |  | Crossover Sub |  | Steel | SD112774 | 0 | 7 | O | O | O | O | O | O | O
Cross Over | Gator Tech | 5.188 | Crossover Sub |  | Steel | GT52331429 | 11 | 13 | [6 empty] | O | O | X | X | X | X | X | X | X | X | X | X | X
Cross Over | Gator Tech |  | Crossover Sub |  | Steel | GT52331431 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD119321 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD119435 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over | Stabil Drill | 4.875 | Crossover Sub |  | Steel | SD107608 | 0 | 3 | [16 empty] | O | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD107750 | 0 | 3 | [16 empty] | O | O | O
MWD / LWD |  |  | UBHO |  | Steel | ZSB775203 | 0 | 7 | O | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO |  | Steel | ZSB775192 | 7 | 7 | X | X | X | X | X | X | X
MWD / LWD | PDCI |  | UBHO |  | Steel | ZSB500025 | 0 | 19 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD | PDCI | 5.125 | UBHO |  | Steel | ZSB500049 | 11 | 19 | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X | X
Motor |  | 8 | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 |  | Steel | PPM800053 | 2 | 2 | X | X
Motor |  |  | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.014 |  | Steel | PPM800032 | 0 | 2 | O | O
Motor |  | 8 | 7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  | Steel | PPM800059 | 5 | 6 |  | O | X | X | X | X | X
Motor |  |  | 7/8 Lobe 5.9 Slick 2.0F HPO -.020 |  | Steel | PPM800033 | 0 | 6 |  | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 Slick HS88 0.000 |  | Steel | PPM250003 | 0 | 6 | [6 empty] | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 Slick HS88 0.003 |  | Steel | PPM250010 | 4 | 7 | [6 empty] | O | O | X | X | X | X | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 Slick HS88 0.015 |  | Steel | PPM250015 | 0 | 6 | [6 empty] | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 Slick HPT 0.023 |  | Steel | PPM250022 | 3 | 5 | [11 empty] | O | X | X | X | O
Motor | PDCI |  | 6/7 8.8 2.12 Slick HPT 0.026 |  | Steel | PPM250010 | 4 | 4 | [8 empty] | X | X | X | X |  |  |  | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 Slick HS88 0.026 |  | Steel | PPM250006 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor | Baker | 5 | 5/6 9.5 1.80 Slick x 5 3/8" stab |  | Steel | 14954251 | 3 | 3 | [16 empty] | X | X | X
Motor | Baker |  | 5/6 9.5 1.80 Slick x 5 3/8" stab |  | Steel | 14962896 | 0 | 3 | [16 empty] | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 Slick HPT 0.028 |  | Steel | PPM250005 | 3 | 5 | [13 empty] | O | X | X | X | O
Motor | PDCI | 5.5 | 7/8 3.8 2.50 Slick HS88 -0.005 |  | Steel | MTR500030 | 0 | 6 | [6 empty] | O | O | O | O | O | O
Stab |  |  | Nortrak Stabilizer (BFF) 13" |  | Steel | SD603912 | 0 | 2 | O | O
Stab |  | 8.125 | Nortrak Stabilizer (BFF) 13" |  | Steel | SD610222 | 2 | 2 | X | X
Collar |  | 8 | Drill Collar (NO HARDBANDING) |  | Steel | SD47865 | 7 | 7 | X | X | X | X | X | X | X
Collar |  |  | Drill Collar (NO HARDBANDING) |  | Steel | SD55076 | 0 | 7 | O | O | O | O | O | O | O
Collar |  | 8 | Drill Collar (NO HARDBANDING) |  | Steel | SD55256 | 7 | 7 | X | X | X | X | X | X | X
Collar |  |  | Drill Collar (NO HARDBANDING) |  | Steel | SD55924 | 0 | 7 | O | O | O | O | O | O | O
Collar |  | 8 | Pony Collar (NO HARDBANDING) |  | Steel | SD40153 | 7 | 7 | X | X | X | X | X | X | X
Collar |  |  | Pony Collar (NO HARDBANDING) |  | Steel | SD46071 | 0 | 7 | O | O | O | O | O | O | O
Collar | Stabil Drill | 4.875 | Drill Collar (NO HARDBANDING) |  | Steel | SD55911 | 11 | 13 | [6 empty] | O | O | X | X | X | X | X | X | X | X | X | X | X
Collar | Stabil Drill |  | Drill Collar (NO HARDBANDING) |  | Steel | SD55955 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Stabil Drill |  | Drill Collar (NO HARDBANDING) |  | Steel | SD56238 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Stabil Drill | 4.875 | Drill Collar (NO HARDBANDING) |  | Steel | SD56632 | 11 | 13 | [6 empty] | O | O | X | X | X | X | X | X | X | X | X | X | X
Collar | Stabil Drill |  | Drill Collar (NO HARDBANDING) |  | Steel | SD56700 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Stabil Drill |  | Drill Collar (NO HARDBANDING) |  | Steel | SD56709 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Stabil Drill | 5 | Pony Collar (NO HARDBANDING) |  | Steel | SD56679 | 11 | 13 | [6 empty] | O | O | X | X | X | X | X | X | X | X | X | X | X
Collar | Stabil Drill |  | Pony Collar (NO HARDBANDING) |  | Steel | SD56919 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Gator Tech | 5 | Pony Collar (NO HARDBANDING) |  | Steel | GT50-10-585 | 11 | 13 | [6 empty] | O | O | X | X | X | X | X | X | X | X | X | X | X
Collar | Gator Tech |  | Pony Collar (NO HARDBANDING) |  | Steel | GT50-10-479 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 2 Stands 4.5 Drill Pipe |  | Steel | Rig1 | 0 | 12 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 26 Stands 4.5 Drill Pipe |  | Steel | Rig2 | 0 | 12 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 33 Stands 4.5 Drill Pipe |  | Steel | Rig3 | 0 | 12 | [7 empty] | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD112914 | 0 | 7 | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD1155542 | 0 | 7 | O | O | O | O | O | O | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD115374 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD119565 | 0 | 13 | [6 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD114757 | 0 | 19 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0050 | 3 | 8 | [11 empty] | O | X | X | X | O | O | O | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 5 |  | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Jesse Taylor Josh Ray |  |  |  | 1 | [6 empty] | 1
Day DD |  |  | Josh Ray |  |  |  | 13 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Xavier Cantu |  |  |  | 19 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 19 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smetters |  |  |  | 14 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smitters |  |  |  | 5 |  | 1 | 1 | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 11 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 11 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Ozark 1H
|  | County: |  | Fayette |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0111MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
PPM800053 | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 | 8 | 37.48 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/19/2021
PPM800032 | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.014 |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/19/2021
PPM800059 | 7/8 Lobe 5.9 Slick 2.0F HPO -.017 | 8 | 37.46 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/19/2021 |  | 06/24/2021
PPM800033 | 7/8 Lobe 5.9 Slick 2.0F HPO -.020 |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/19/2021 |  | 06/24/2021
ZSB775203 | UBHO |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
ZSB775192 | UBHO | 7.75 | 3.72 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/24/2021
ZSB500025 | UBHO |  |  |  | XT 39 / XT 39 | Clean | PDCI / UBHO | 06/16/2021 |  | 07/06/2021
ZSB500049 | UBHO | 5.125 | 3.99 |  | XT 39 / XT 39 | In Hole | PDCI / UBHO | 06/16/2021
SD47865 | Drill Collar (NO HARDBANDING) | 8 | 28.77 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/24/2021
SD55076 | Drill Collar (NO HARDBANDING) |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD55256 | Drill Collar (NO HARDBANDING) | 8 | 28.41 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/24/2021
SD55924 | Drill Collar (NO HARDBANDING) |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD40153 | Pony Collar (NO HARDBANDING) | 8 | 7.93 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/24/2021
SD46071 | Pony Collar (NO HARDBANDING) |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD603912 | Nortrak Stabilizer (BFF) 13" |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/19/2021
SD610222 | Nortrak Stabilizer (BFF) 13" | 8.125 | 7.63 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/19/2021
SD104164 | Crossover Sub | 8.25 | 2.56 |  | 4 1/2 IF / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/24/2021
SD118777 | Crossover Sub |  |  |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD115530 | Crossover Sub | 6.5 | 2.7 |  | 4 1/2 XH / 6 5/8 REG | Dirty |  | 06/16/2021 |  | 06/24/2021
SD118021 | Crossover Sub |  |  |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD115076 | Crossover Sub | 6.125 | 2.36 |  | 4 1/2 IF / 4 1/2 XH | Dirty |  | 06/16/2021 |  | 06/24/2021
SD115656 | Crossover Sub |  |  |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 06/16/2021 |  | 06/24/2021
SD110296 | Crossover Sub | 6.5 | 2.4 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 06/16/2021 |  | 06/24/2021
SD112774 | Crossover Sub |  |  |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 06/16/2021 |  | 06/24/2021
SD112914 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD1155542 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD113285 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD118607 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
SD | Lift Cap |  |  |  | 6 5/8 REG | Clean |  | 06/16/2021 |  | 06/24/2021
PG525-0050 | Agitator | 5.312 | 23.65 |  | CET43 / CET43 | Dirty | DWS / Power glide | 06/29/2021
13509567 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 07/01/2021
13601236 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 06/25/2021
13594950 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 06/29/2021
PPM250003 | 6/7 8.8 2.12 Slick HS88 0.000 | 5.5 |  |  | XT39 / 3 1/2 REG | Clean | PDCI / Pro Power | 06/24/2021 |  | 06/29/2021
PPM250010 | 6/7 8.8 2.12 Slick HS88 0.003 | 5.5 | 33.13 |  | XT39 / 3 1/2 REG | Dirty | PDCI / Pro Power | 06/24/2021 |  | 06/30/2021
PPM250015 | 6/7 8.8 2.12 Slick HS88 0.015 | 5.5 |  |  | XT39 / 3 1/2 REG | Clean | PDCI / Pro Power | 06/24/2021 |  | 06/29/2021
PPM250022 | 6/7 8.8 2.12 Slick HPT 0.023 | 5.5 | 32.99 |  | XT39 / 3 1/2 REG | Dirty | PDCI / Pro Power | 06/29/2021 |  | 07/03/2021
PPM250010 | 6/7 8.8 2.12 Slick HPT 0.026 |  |  |  | XT39 / 3 1/2 REG | Dirty | PDCI / Pro Power | 07/03/2021 |  | 07/06/2021
PPM250006 | 6/7 8.8 2.12 Slick HS88 0.026 | 5.5 | 33.12 |  | XT39 / 3 1/2 REG | Clean | PDCI / Pro Power | 06/24/2021 |  | 07/06/2021
14954251 | 5/6 9.5 1.80 Slick x 5 3/8" stab | 5 | 31.22 |  | 3 1/2 IF / 3 1/2 REG | In Hole | Baker / NaviDrill | 07/04/2021
14962896 | 5/6 9.5 1.80 Slick x 5 3/8" stab |  |  |  | 3 1/2 IF / 3 1/2 REG | Clean | Baker / NaviDrill | 07/04/2021 |  | 07/06/2021
PPM250005 | 6/7 8.8 2.12 Slick HPT 0.028 | 5.5 | 33.15 |  | XT39 / 3 1/2 REG | Dirty | PDCI / Pro Power | 07/01/2021 |  | 07/05/2021
MTR500030 | 7/8 3.8 2.50 Slick HS88 -0.005 | 5.5 |  |  | XT39 / 3 1/2 REG | Clean | PDCI / Pro Power | 06/24/2021 |  | 06/29/2021
SD55911 | Drill Collar (NO HARDBANDING) | 4.875 | 30.05 |  | XT39 / XT39 | In Hole | Stabil Drill | 06/24/2021
SD55955 | Drill Collar (NO HARDBANDING) |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD56238 | Drill Collar (NO HARDBANDING) |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD56632 | Drill Collar (NO HARDBANDING) | 4.875 | 30.57 |  | XT39 / XT39 | In Hole | Stabil Drill | 06/24/2021
SD56700 | Drill Collar (NO HARDBANDING) |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD56709 | Drill Collar (NO HARDBANDING) |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD56679 | Pony Collar (NO HARDBANDING) | 5 | 9.27 |  | XT39 / XT39 | In Hole | Stabil Drill | 06/24/2021
SD56919 | Pony Collar (NO HARDBANDING) |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
GT50-10-585 | Pony Collar (NO HARDBANDING) | 5 | 9.54 |  | XT39 / XT39 | In Hole | Gator Tech | 06/24/2021
GT50-10-479 | Pony Collar (NO HARDBANDING) |  |  |  | XT39 / XT39 | Clean | Gator Tech | 06/24/2021 |  | 07/06/2021
GT52331429 | Crossover Sub | 5.188 | 3.38 |  | CET43 / XT39 | In Hole | Gator Tech | 06/24/2021
GT52331431 | Crossover Sub |  |  |  | CET43 / XT39 | Clean | Gator Tech | 06/24/2021 |  | 07/06/2021
SD119321 | Crossover Sub |  |  |  | DS42 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD119435 | Crossover Sub |  |  |  | DS42 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD115374 | Float Sub |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD119565 | Float Sub |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD114757 | Float Sub |  |  |  | XT39 / XT39 | Clean | Stabil Drill | 06/16/2021 |  | 07/06/2021
SD119271 | Lift Sub (4 1/2" Shank) | 6.25 | 3 |  | XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
SD119274 | Lift Sub (4 1/2" Shank) | 6.25 | 3.11 |  | XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
LC3364 | Lift Cap |  |  |  | XT39 | Clean | Stabil Drill | 06/24/2021 |  | 07/06/2021
Rig1 | 2 Stands 4.5 Drill Pipe | 4.5 | 189.66 |  | CET43 / CET43 | In Hole |  | 06/25/2021
Rig2 | 26 Stands 4.5 Drill Pipe | 4.5 | 2458.99 |  | CET43 / CET43 | In Hole |  | 06/25/2021
Rig3 | 33 Stands 4.5 Drill Pipe | 4.5 | 3108.44 |  | CET43 / CET43 | In Hole |  | 06/25/2021
SD107608 | Crossover Sub | 4.875 | 2.36 |  | XT39 / 3 1/2 IF | Clean | Stabil Drill | 07/04/2021 |  | 07/06/2021
SD107750 | Crossover Sub |  |  |  | XT39 / 3 1/2 IF | Clean | Stabil Drill | 07/04/2021 |  | 07/06/2021
0 | Dir 33 Well seeker kit |  |  |  |  | In Hole |  | 07/06/2021
0 | Dir 40 HP 200 printer |  |  |  |  | In Hole |  | 07/06/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Ozark 1H
|  | County: |  | Fayette |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 43518 | 06/18/2021 | 07/06/2021 | 19 | 1 | 1 |  | 2.33 | 10.28 | 22.5
7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 | PPM800053 | 06/16/2021 | 06/19/2021 | 4 | 1 | 1 |  | 2.33 | 10.28 | 22.5
Nortrak Stabilizer (BFF) 13" | SD610222 | 06/16/2021 | 06/19/2021 | 4 | 1 | 1 |  | 2.33 | 10.28 | 22.5
Pony Collar (NO HARDBANDING) | SD40153 | 06/16/2021 | 06/24/2021 | 9 | 5 | 1 ,2 |  | 7.67 | 54.28 | 112.5
UBHO | ZSB775192 | 06/16/2021 | 06/24/2021 | 9 | 5 | 1 ,2 |  | 7.67 | 54.28 | 112.5
Drill Collar (NO HARDBANDING) | SD47865 | 06/16/2021 | 06/24/2021 | 9 | 5 | 1 ,2 |  | 7.67 | 54.28 | 112.5
Drill Collar (NO HARDBANDING) | SD55256 | 06/16/2021 | 06/24/2021 | 9 | 5 | 1 ,2 |  | 7.67 | 54.28 | 112.5
Crossover Sub | SD104164 | 06/16/2021 | 06/24/2021 | 9 | 1 | 1 |  | 2.33 | 10.28 | 22.5
SPL613 | 54861 | 06/18/2021 | 07/06/2021 | 19 | 4 | 2 |  | 5.33 | 44 | 90
7/8 Lobe 5.9 Slick 2.0F HPO -.017 | PPM800059 | 06/19/2021 | 06/24/2021 | 6 | 4 | 2 |  | 5.33 | 44 | 90
Crossover Sub | SD115530 | 06/16/2021 | 06/24/2021 | 9 | 4 | 2 |  | 5.33 | 44 | 90
2 Stds 6.5 in DC | SD104164 | 06/18/2021 | 07/06/2021 | 19 | 4 | 2 |  | 5.33 | 44 | 90
Crossover Sub | SD115076 | 06/16/2021 | 06/24/2021 | 9 | 4 | 2 |  | 5.33 | 44 | 90
Agitator | PG675 | 06/18/2021 | 07/06/2021 | 19 | 4 | 2 |  | 5.33 | 44 | 90
GTD64M | 13601236 | 06/25/2021 | 07/06/2021 | 12 | 4 | 3 |  | 12.75 | 38.58 | 84.42
6/7 8.8 2.12 Slick HS88 0.003 | PPM250010 | 07/03/2021 | 07/06/2021 | 4 | 4 | 3 |  | 12.75 | 38.58 | 84.42
BTI | RIG | 06/18/2021 | 07/06/2021 | 19 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Pony Collar (NO HARDBANDING) | GT50-10-585 | 06/24/2021 | 07/06/2021 | 13 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
UBHO | ZSB500049 | 06/16/2021 | 07/06/2021 | 21 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
Pulser | 6232 | 06/16/2021 | 07/06/2021 | 20 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Battery - Plug In Hrs 0.00 | 1338 | 06/16/2021 | 07/06/2021 | 20 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Battery - Plug In Hrs 0.00 | 1180 | 06/16/2021 | 07/06/2021 | 20 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Gamma | 3122/ AZ4000 | 06/16/2021 | 07/06/2021 | 20 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Directional Module | 7462 / 9009 | 06/16/2021 | 07/06/2021 | 20 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Drill Collar (NO HARDBANDING) | SD55911 | 06/24/2021 | 07/06/2021 | 13 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
Pony Collar (NO HARDBANDING) | SD56679 | 06/24/2021 | 07/06/2021 | 13 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
Drill Collar (NO HARDBANDING) | SD56632 | 06/24/2021 | 07/06/2021 | 13 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
Tomax | A52107 | 06/18/2021 | 07/06/2021 | 19 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
Crossover Sub | GT52331429 | 06/24/2021 | 07/06/2021 | 13 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
6 13/16 Drill-N-Ream | 520 | 06/18/2021 | 07/06/2021 | 19 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
Agitator | PG525-0051 | 06/18/2021 | 07/06/2021 | 19 | 4 | 3 |  | 12.75 | 38.58 | 84.42
Agitator | PG525-0049 | 06/18/2021 | 07/06/2021 | 19 | 10 | 3 ,4 ,5 ,6 |  | 47.42 | 75.92 | 242.17
GTD64M | 13594950 | 06/29/2021 | 07/06/2021 | 8 | 2 | 4 |  | 14.08 | 16.67 | 59.08
BTI | 306842 | 06/18/2021 | 07/06/2021 | 19 | 7 | 4 ,5 ,6 |  | 34.67 | 37.33 | 157.75
6/7 8.8 2.12 Slick HPT 0.023 | PPM250022 | 06/29/2021 | 07/03/2021 | 5 | 2 | 4 |  | 14.08 | 16.67 | 59.08
Agitator | PG525-0050 | 06/29/2021 | 07/06/2021 | 8 | 2 | 4 |  | 14.08 | 16.67 | 59.08
GTD64M | 13509567 | 07/01/2021 | 07/06/2021 | 6 | 2 | 5 |  | 9.75 | 6.08 | 42
6/7 8.8 2.12 Slick HPT 0.028 | PPM250005 | 07/01/2021 | 07/05/2021 | 5 | 2 | 5 |  | 9.75 | 6.08 | 42
Helix | 45 | 06/16/2021 | 07/06/2021 | 20 | 2 | 5 |  | 9.75 | 6.08 | 42
Pulser | 6114 | 06/16/2021 | 07/06/2021 | 20 | 2 | 5 |  | 9.75 | 6.08 | 42
Battery - Plug In Hrs 0.00 | 1386 | 06/16/2021 | 07/06/2021 | 20 | 2 | 5 |  | 9.75 | 6.08 | 42
Battery - Plug In Hrs 0.00 | 1056 | 06/16/2021 | 07/06/2021 | 20 | 2 | 5 |  | 9.75 | 6.08 | 42
Gamma | 2576 | 06/16/2021 | 07/06/2021 | 20 | 2 | 5 |  | 9.75 | 6.08 | 42
Directional Module | 9003 | 06/16/2021 | 07/06/2021 | 20 | 2 | 5 |  | 9.75 | 6.08 | 42
Agitator | PG525-0056 | 06/18/2021 | 07/06/2021 | 19 | 4 | 5 ,6 |  | 20.58 | 20.67 | 98.67
GTD64M | 13564680 | 06/18/2021 | 07/06/2021 | 19 | 2 | 6 |  | 10.83 | 14.58 | 56.67
5/6 9.5 1.80 adj 5 3/8 stab | 14954251 | 07/04/2021 | 07/06/2021 | 3 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Crossover Sub | 107608 | 06/18/2021 | 07/06/2021 | 19 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Helix | 290 | 06/16/2021 | 07/06/2021 | 20 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Pulser | 6163 | 06/16/2021 | 07/06/2021 | 20 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Battery - Plug In Hrs 0.00 | 1249 | 06/16/2021 | 07/06/2021 | 20 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Battery - Plug In Hrs 0.00 | 1411 | 06/16/2021 | 07/06/2021 | 20 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Gamma | 3032/4002 | 06/16/2021 | 07/06/2021 | 20 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Directional Module | 9009/7477 | 06/16/2021 | 07/06/2021 | 20 | 2 | 6 |  | 10.83 | 14.58 | 56.67
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Fayette County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well-GL: 378 + KB: 28 (Pat248)
Facility |  |  | Ozark - Fayette County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Ozark 1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Ozark 1H
Field: |  |  | Fayette County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas South Central 4204
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 406.00 Usft
Map Northing |  |  | 816982.02 US survey foot |  |  | Map Easting |  |  | 2668460.01 US survey foot
Latitude |  |  | 30° 3' 49.16451" N |  |  | Longitude |  |  | 96° 53' 12.44787" W
Grid Convergence |  |  | 1.035
Facility: |  |  | Ozark - Fayette County, TX
Map Northing |  |  | 789362.49 US survey foot |  |  | Map Easting |  |  | 2727473.71 US survey foot
Latitude |  |  | 29° 59' 4.77528" N |  |  | Longitude |  |  | 96° 42' 7.17138" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.126
Well: |  |  | Ozark 1H
Local North |  |  | 0.01 Usft |  |  | Local East |  |  | 0.00 Usft
Map Northing |  |  | 789362.50 US survey foot |  |  | Map Easting |  |  | 2727473.71 US survey foot
Latitude |  |  | 29° 59' 4.775" N |  |  | Longitude |  |  | 96° 42' 7.171" W
Depth Datum |  |  | Well-GL: 378 + KB: 28 (Pat248) |  |  | Datum Elevation |  |  | 406.00 Usft
GL Elevation |  |  | 378.00 Usft
Grid Convergence |  |  | 1.126
Well bore: |  |  | Ozark 1H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 20/06/2021
Total Field (nT) |  |  | 46512.7 |  |  | Dip Angle (°) |  |  | 58.7
Declination (°) |  |  | 3.017
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 141.87
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Ozark 1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3779 |  |  | Ozark No. 1H S1 |  |  | MWD+HDGM
3779 |  |  | 12183 |  |  | Ozark No. 1H S2 |  |  | MWD+HDGM
12183 |  |  | 16093 |  |  | Ozark No. 1H S3 |  |  | MWD+HDGM
16093 |  |  | 18265 |  |  | Ozark No. 1H S4 |  |  | MWD+HDGM
18265 |  |  | 18832 |  |  | Ozark No. 1H S5 |  |  | MWD+HDGM
18832 |  |  | 20437 |  |  | Ozark No. 1H S6 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -406 | 789362.5 | 2727473.71 | 29.9847 | -96.702 | 0
143 | 0.36 | 30.81 | 143 | 0.39 | 0.23 | -0.16 | 0.25 | 0.25 | 21.55 | 30.81 | 143 | -263 | 789362.89 | 2727473.94 | 29.9847 | -96.702 | 30.81
234 | 0.42 | 22.16 | 234 | 0.94 | 0.5 | -0.43 | 0.09 | 0.07 | -9.51 | -48.84 | 91 | -172 | 789363.44 | 2727474.21 | 29.9847 | -96.702 | 28.11
326 | 0.51 | 19.26 | 325.99 | 1.64 | 0.76 | -0.82 | 0.1 | 0.1 | -3.15 | -16.11 | 92 | -80.01 | 789364.14 | 2727474.47 | 29.9847 | -96.702 | 25.01
421 | 0.47 | 24.42 | 420.99 | 2.39 | 1.07 | -1.22 | 0.06 | -0.04 | 5.43 | 134.75 | 95 | 14.99 | 789364.89 | 2727474.78 | 29.9847 | -96.702 | 23.99
515 | 0.55 | 19.81 | 514.99 | 3.17 | 1.38 | -1.64 | 0.1 | 0.09 | -4.9 | -29.47 | 94 | 108.99 | 789365.67 | 2727475.09 | 29.9847 | -96.702 | 23.5
609 | 0.4 | 23.04 | 608.98 | 3.89 | 1.66 | -2.04 | 0.16 | -0.16 | 3.44 | 171.49 | 94 | 202.98 | 789366.39 | 2727475.37 | 29.9847 | -96.702 | 23.07
704 | 0.34 | 81.83 | 703.98 | 4.24 | 2.07 | -2.06 | 0.39 | -0.06 | 61.88 | 127.58 | 95 | 297.98 | 789366.74 | 2727475.78 | 29.9847 | -96.702 | 25.99
798 | 0.52 | 138.26 | 797.98 | 3.96 | 2.63 | -1.49 | 0.46 | 0.19 | 60.03 | 96.9 | 94 | 391.98 | 789366.46 | 2727476.34 | 29.9847 | -96.702 | 33.56
892 | 0.78 | 155.99 | 891.97 | 3.06 | 3.17 | -0.45 | 0.35 | 0.28 | 18.86 | 46.81 | 94 | 485.97 | 789365.56 | 2727476.88 | 29.9847 | -96.702 | 46.04
986 | 1.17 | 159.22 | 985.96 | 1.58 | 3.77 | 1.09 | 0.42 | 0.41 | 3.44 | 9.64 | 94 | 579.96 | 789364.08 | 2727477.48 | 29.9847 | -96.702 | 67.31
1079 | 1.22 | 164.31 | 1078.94 | -0.26 | 4.38 | 2.91 | 0.13 | 0.05 | 5.47 | 67.34 | 93 | 672.94 | 789362.24 | 2727478.09 | 29.9847 | -96.702 | 93.45
1173 | 1.15 | 164.93 | 1172.92 | -2.14 | 4.89 | 4.7 | 0.08 | -0.07 | 0.66 | 169.93 | 94 | 766.92 | 789360.36 | 2727478.6 | 29.9847 | -96.702 | 113.6
1266 | 0.84 | 165.9 | 1265.91 | -3.7 | 5.3 | 6.18 | 0.33 | -0.33 | 1.04 | 177.37 | 93 | 859.91 | 789358.8 | 2727479.01 | 29.9846 | -96.702 | 124.91
1360 | 0.66 | 162.8 | 1359.9 | -4.89 | 5.63 | 7.32 | 0.2 | -0.19 | -3.3 | -168.84 | 94 | 953.9 | 789357.61 | 2727479.34 | 29.9846 | -96.702 | 130.95
1454 | 0.39 | 179.35 | 1453.89 | -5.72 | 5.79 | 8.08 | 0.33 | -0.29 | 17.61 | 158.78 | 94 | 1047.89 | 789356.78 | 2727479.5 | 29.9846 | -96.702 | 134.65
1548 | 0.14 | 166.63 | 1547.89 | -6.15 | 5.82 | 8.44 | 0.27 | -0.27 | -13.53 | -173.06 | 94 | 1141.89 | 789356.35 | 2727479.53 | 29.9846 | -96.702 | 136.58
1642 | 0.04 | 343.05 | 1641.89 | -6.23 | 5.84 | 8.51 | 0.19 | -0.11 | 187.68 | 179.2 | 94 | 1235.89 | 789356.27 | 2727479.55 | 29.9846 | -96.702 | 136.87
1736 | 0.03 | 321.69 | 1735.89 | -6.18 | 5.82 | 8.46 | 0.02 | -0.01 | -22.72 | -137.82 | 94 | 1329.89 | 789356.32 | 2727479.53 | 29.9846 | -96.702 | 136.76
1829 | 0.12 | 199.85 | 1828.89 | -6.26 | 5.77 | 8.48 | 0.15 | 0.1 | -131.01 | -132.47 | 93 | 1422.89 | 789356.24 | 2727479.48 | 29.9846 | -96.702 | 137.33
1923 | 0.08 | 271.91 | 1922.89 | -6.35 | 5.67 | 8.49 | 0.13 | -0.04 | 76.66 | 141.4 | 94 | 1516.89 | 789356.15 | 2727479.38 | 29.9846 | -96.702 | 138.23
2017 | 0.83 | 327.04 | 2016.89 | -5.77 | 5.23 | 7.77 | 0.84 | 0.8 | 58.65 | 59.91 | 94 | 1610.89 | 789356.73 | 2727478.94 | 29.9846 | -96.702 | 137.81
2110 | 1.82 | 332.89 | 2109.86 | -3.89 | 4.19 | 5.65 | 1.07 | 1.06 | 6.29 | 10.71 | 93 | 1703.86 | 789358.61 | 2727477.9 | 29.9846 | -96.702 | 132.88
2203 | 2.89 | 334.42 | 2202.78 | -0.46 | 2.51 | 1.91 | 1.15 | 1.15 | 1.65 | 4.13 | 93 | 1796.78 | 789362.04 | 2727476.22 | 29.9847 | -96.702 | 100.49
2298 | 3.92 | 329.96 | 2297.61 | 4.51 | -0.15 | -3.64 | 1.12 | 1.08 | -4.69 | -16.66 | 95 | 1891.61 | 789367.01 | 2727473.56 | 29.9847 | -96.702 | 358.07
2392 | 4.74 | 326.3 | 2391.34 | 10.52 | -3.92 | -10.69 | 0.92 | 0.87 | -3.89 | -20.45 | 94 | 1985.34 | 789373.02 | 2727469.79 | 29.9847 | -96.702 | 339.59
2486 | 5.67 | 321.12 | 2484.96 | 17.37 | -8.98 | -19.21 | 1.11 | 0.99 | -5.51 | -29.4 | 94 | 2078.96 | 789379.87 | 2727464.73 | 29.9847 | -96.702 | 332.64
2579 | 6.05 | 319.05 | 2577.47 | 24.64 | -15.08 | -28.7 | 0.47 | 0.41 | -2.23 | -30.11 | 93 | 2171.47 | 789387.14 | 2727458.63 | 29.9847 | -96.702 | 328.54
2674 | 5.87 | 318.34 | 2671.96 | 32.05 | -21.59 | -38.55 | 0.2 | -0.19 | -0.75 | -158.08 | 95 | 2265.96 | 789394.55 | 2727452.12 | 29.9847 | -96.7021 | 326.04
2767 | 5.88 | 319.22 | 2764.47 | 39.21 | -27.86 | -48.05 | 0.1 | 0.01 | 0.95 | 84.1 | 93 | 2358.47 | 789401.71 | 2727445.85 | 29.9848 | -96.7021 | 324.6
2861 | 5.87 | 317.91 | 2857.97 | 46.43 | -34.23 | -57.66 | 0.14 | -0.01 | -1.39 | -94.92 | 94 | 2451.97 | 789408.93 | 2727439.48 | 29.9848 | -96.7021 | 323.6
2955 | 5.43 | 321.26 | 2951.52 | 53.46 | -40.24 | -66.9 | 0.58 | -0.47 | 3.56 | 144.8 | 94 | 2545.52 | 789415.96 | 2727433.47 | 29.9848 | -96.7021 | 323.04
3049 | 4.44 | 326.48 | 3045.17 | 59.97 | -45.03 | -74.97 | 1.16 | -1.05 | 5.55 | 158.19 | 94 | 2639.17 | 789422.47 | 2727428.68 | 29.9848 | -96.7021 | 323.1
3143 | 3.56 | 330.79 | 3138.94 | 65.55 | -48.46 | -81.48 | 0.99 | -0.94 | 4.59 | 163.28 | 94 | 2732.94 | 789428.05 | 2727425.25 | 29.9848 | -96.7021 | 323.52
3238 | 2.58 | 336.95 | 3233.8 | 70.09 | -50.74 | -86.46 | 1.09 | -1.03 | 6.48 | 164.45 | 95 | 2827.8 | 789432.59 | 2727422.97 | 29.9849 | -96.7021 | 324.1
3332 | 1.8 | 348.65 | 3327.73 | 73.48 | -51.86 | -89.82 | 0.95 | -0.83 | 12.45 | 155.94 | 94 | 2921.73 | 789435.98 | 2727421.85 | 29.9849 | -96.7022 | 324.79
3426 | 1.06 | 13.92 | 3421.7 | 75.77 | -51.94 | -91.67 | 1.02 | -0.79 | 26.88 | 151.73 | 94 | 3015.7 | 789438.27 | 2727421.77 | 29.9849 | -96.7022 | 325.57
3520 | 0.9 | 30.37 | 3515.69 | 77.26 | -51.36 | -92.48 | 0.34 | -0.17 | 17.5 | 127.68 | 94 | 3109.69 | 789439.76 | 2727422.35 | 29.9849 | -96.7021 | 326.39
3614 | 0.75 | 34.81 | 3609.68 | 78.4 | -50.63 | -92.93 | 0.17 | -0.16 | 4.72 | 159.13 | 94 | 3203.68 | 789440.9 | 2727423.08 | 29.9849 | -96.7021 | 327.14
3708 | 0.81 | 32.52 | 3703.67 | 79.46 | -49.92 | -93.33 | 0.07 | 0.06 | -2.44 | -28.6 | 94 | 3297.67 | 789441.96 | 2727423.79 | 29.9849 | -96.7021 | 327.86
3779 | 0.66 | 13.43 | 3774.67 | 80.28 | -49.56 | -93.75 | 0.4 | -0.21 | -26.89 | -130.8 | 71 | 3368.67 | 789442.78 | 2727424.15 | 29.9849 | -96.7021 | 328.31
3916 | 1.08 | 359.28 | 3911.65 | 82.34 | -49.39 | -95.27 | 0.34 | 0.31 | 10.33 | -34.28 | 137 | 3505.65 | 789444.84 | 2727424.32 | 29.9849 | -96.7021 | 329.04
4010 | 1.41 | 350.28 | 4005.63 | 84.37 | -49.6 | -96.99 | 0.41 | 0.35 | -9.57 | -35.2 | 94 | 3599.63 | 789446.87 | 2727424.11 | 29.9849 | -96.7021 | 329.55
4105 | 1.5 | 342.64 | 4100.6 | 86.71 | -50.17 | -99.18 | 0.22 | 0.09 | -8.04 | -68.96 | 95 | 3694.6 | 789449.21 | 2727423.54 | 29.9849 | -96.7021 | 329.95
4199 | 0.29 | 334.04 | 4194.58 | 88.1 | -50.64 | -100.56 | 1.29 | -1.29 | -9.15 | -177.95 | 94 | 3788.58 | 789450.6 | 2727423.07 | 29.9849 | -96.7021 | 330.11
4292 | 0.24 | 4.12 | 4287.58 | 88.5 | -50.73 | -100.94 | 0.16 | -0.05 | 32.34 | 124.39 | 93 | 3881.58 | 789451 | 2727422.98 | 29.9849 | -96.7021 | 330.18
4387 | 0.65 | 1.68 | 4382.58 | 89.24 | -50.7 | -101.5 | 0.43 | 0.43 | -2.57 | -3.87 | 95 | 3976.58 | 789451.74 | 2727423.01 | 29.9849 | -96.7021 | 330.4
4480 | 1.15 | 349.02 | 4475.57 | 90.68 | -50.86 | -102.73 | 0.58 | 0.54 | 13.61 | -28.1 | 93 | 4069.57 | 789453.18 | 2727422.85 | 29.9849 | -96.7021 | 330.71
4574 | 1.12 | 339.77 | 4569.55 | 92.47 | -51.36 | -104.45 | 0.2 | -0.03 | -9.84 | -103.9 | 94 | 4163.55 | 789454.97 | 2727422.35 | 29.9849 | -96.7021 | 330.95
4668 | 0.38 | 331.91 | 4663.54 | 93.61 | -51.82 | -105.63 | 0.79 | -0.79 | -8.36 | -176 | 94 | 4257.54 | 789456.11 | 2727421.89 | 29.9849 | -96.7022 | 331.03
4762 | 0.65 | 328.26 | 4757.54 | 94.34 | -52.25 | -106.47 | 0.29 | 0.29 | -3.88 | -8.76 | 94 | 4351.54 | 789456.84 | 2727421.46 | 29.9849 | -96.7022 | 331.02
4856 | 1.67 | 279.22 | 4851.52 | 95.01 | -53.88 | -108 | 1.42 | 1.09 | -52.17 | -70.57 | 94 | 4445.52 | 789457.51 | 2727419.83 | 29.9849 | -96.7022 | 330.44
4951 | 1.9 | 279.38 | 4946.47 | 95.49 | -56.8 | -110.18 | 0.24 | 0.24 | 0.17 | 1.32 | 95 | 4540.47 | 789457.99 | 2727416.91 | 29.9849 | -96.7022 | 329.25
5045 | 1.93 | 281.17 | 5040.42 | 96.05 | -59.89 | -112.53 | 0.07 | 0.03 | 1.9 | 64.26 | 94 | 4634.42 | 789458.55 | 2727413.82 | 29.9849 | -96.7022 | 328.05
5139 | 1.26 | 271.53 | 5134.38 | 96.38 | -62.48 | -114.39 | 0.77 | -0.71 | -10.26 | -162.95 | 94 | 4728.38 | 789458.88 | 2727411.23 | 29.9849 | -96.7022 | 327.05
5234 | 1.1 | 266.35 | 5229.36 | 96.35 | -64.43 | -115.57 | 0.2 | -0.17 | -5.45 | -148.88 | 95 | 4823.36 | 789458.85 | 2727409.28 | 29.9849 | -96.7022 | 326.23
5327 | 1.03 | 276.83 | 5322.35 | 96.39 | -66.15 | -116.67 | 0.22 | -0.08 | 11.27 | 114.95 | 93 | 4916.35 | 789458.89 | 2727407.56 | 29.9849 | -96.7022 | 325.54
5421 | 1.08 | 282.99 | 5416.33 | 96.69 | -67.85 | -117.96 | 0.13 | 0.05 | 6.55 | 69.31 | 94 | 5010.33 | 789459.19 | 2727405.86 | 29.9849 | -96.7022 | 324.94
5516 | 1.13 | 279.46 | 5511.31 | 97.05 | -69.65 | -119.35 | 0.09 | 0.05 | -3.72 | -55.48 | 95 | 5105.31 | 789459.55 | 2727404.06 | 29.9849 | -96.7022 | 324.33
5610 | 0.67 | 232.22 | 5605.3 | 96.86 | -71 | -120.03 | 0.89 | -0.49 | -50.26 | -143.92 | 94 | 5199.3 | 789459.36 | 2727402.71 | 29.9849 | -96.7022 | 323.76
5703 | 0.63 | 227.77 | 5698.3 | 96.19 | -71.81 | -120 | 0.07 | -0.04 | -4.78 | -130.6 | 93 | 5292.3 | 789458.69 | 2727401.9 | 29.9849 | -96.7022 | 323.26
5794 | 0.55 | 258.07 | 5789.29 | 95.76 | -72.61 | -120.16 | 0.35 | -0.09 | 33.3 | 119.21 | 91 | 5383.29 | 789458.26 | 2727401.1 | 29.9849 | -96.7022 | 322.83
5887 | 0.61 | 277.7 | 5882.29 | 95.74 | -73.53 | -120.71 | 0.22 | 0.06 | 21.11 | 83.17 | 93 | 5476.29 | 789458.24 | 2727400.18 | 29.9849 | -96.7022 | 322.47
5980 | 0.43 | 200.62 | 5975.29 | 95.47 | -74.15 | -120.88 | 0.71 | -0.19 | -82.88 | -140.8 | 93 | 5569.29 | 789457.97 | 2727399.56 | 29.9849 | -96.7022 | 322.17
6074 | 0.36 | 197.49 | 6069.28 | 94.86 | -74.36 | -120.53 | 0.08 | -0.07 | -3.33 | -164.43 | 94 | 5663.28 | 789457.36 | 2727399.35 | 29.9849 | -96.7022 | 321.91
6168 | 0.33 | 210.52 | 6163.28 | 94.35 | -74.59 | -120.27 | 0.09 | -0.03 | 13.86 | 117.36 | 94 | 5757.28 | 789456.85 | 2727399.12 | 29.9849 | -96.7022 | 321.67
6262 | 0.36 | 209.87 | 6257.28 | 93.86 | -74.87 | -120.06 | 0.03 | 0.03 | -0.69 | -7.76 | 94 | 5851.28 | 789456.36 | 2727398.84 | 29.9849 | -96.7022 | 321.42
6356 | 0.55 | 25.53 | 6351.28 | 94.01 | -74.82 | -120.15 | 0.97 | 0.2 | 186.87 | 177.38 | 94 | 5945.28 | 789456.51 | 2727398.89 | 29.9849 | -96.7022 | 321.48
6450 | 0.53 | 37.47 | 6445.27 | 94.76 | -74.36 | -120.46 | 0.12 | -0.02 | 12.7 | 106.01 | 94 | 6039.27 | 789457.26 | 2727399.35 | 29.9849 | -96.7022 | 321.88
6544 | 0.27 | 24.37 | 6539.27 | 95.31 | -74.01 | -120.67 | 0.29 | -0.28 | -13.94 | -167.09 | 94 | 6133.27 | 789457.81 | 2727399.7 | 29.9849 | -96.7022 | 322.17
6638 | 0.33 | 358.11 | 6633.27 | 95.78 | -73.93 | -120.99 | 0.16 | 0.06 | 27.94 | -79.92 | 94 | 6227.27 | 789458.28 | 2727399.78 | 29.9849 | -96.7022 | 322.34
6733 | 0.33 | 355.51 | 6728.27 | 96.33 | -73.96 | -121.44 | 0.02 | 0 | -2.74 | -91.3 | 95 | 6322.27 | 789458.83 | 2727399.75 | 29.9849 | -96.7022 | 322.48
6827 | 0.86 | 113.2 | 6822.27 | 96.32 | -73.33 | -121.04 | 1.12 | 0.56 | 125.2 | 133.77 | 94 | 6416.27 | 789458.82 | 2727400.38 | 29.9849 | -96.7022 | 322.72
6921 | 1.12 | 122.32 | 6916.25 | 95.55 | -71.9 | -119.56 | 0.32 | 0.28 | 9.7 | 35.83 | 94 | 6510.25 | 789458.05 | 2727401.81 | 29.9849 | -96.7022 | 323.04
7016 | 1.02 | 119.65 | 7011.23 | 94.64 | -70.38 | -117.9 | 0.12 | -0.11 | -2.81 | -154.83 | 95 | 6605.23 | 789457.14 | 2727403.33 | 29.9849 | -96.7022 | 323.36
7110 | 0.68 | 105.13 | 7105.22 | 94.08 | -69.12 | -116.68 | 0.43 | -0.36 | -15.45 | -154.76 | 94 | 6699.22 | 789456.58 | 2727404.59 | 29.9849 | -96.7022 | 323.69
7204 | 0.48 | 81.25 | 7199.22 | 93.99 | -68.19 | -116.04 | 0.33 | -0.21 | -25.4 | -141.13 | 94 | 6793.22 | 789456.49 | 2727405.52 | 29.9849 | -96.7022 | 324.04
7298 | 0.47 | 39.4 | 7293.22 | 94.35 | -67.56 | -115.93 | 0.36 | -0.01 | -44.52 | -112.5 | 94 | 6887.22 | 789456.85 | 2727406.15 | 29.9849 | -96.7022 | 324.4
7391 | 0.51 | 15.21 | 7386.21 | 95.04 | -67.21 | -116.26 | 0.22 | 0.04 | -26.01 | -91.31 | 93 | 6980.21 | 789457.54 | 2727406.5 | 29.9849 | -96.7022 | 324.73
7485 | 0.1 | 200.5 | 7480.21 | 95.37 | -67.13 | -116.47 | 0.65 | -0.44 | 185.86 | -179.13 | 94 | 7074.21 | 789457.87 | 2727406.58 | 29.9849 | -96.7022 | 324.86
7578 | 0.22 | 205.9 | 7573.21 | 95.13 | -67.23 | -116.34 | 0.13 | 0.13 | 5.81 | 9.87 | 93 | 7167.21 | 789457.63 | 2727406.48 | 29.9849 | -96.7022 | 324.75
7672 | 0.43 | 285.87 | 7667.21 | 95.07 | -67.65 | -116.55 | 0.48 | 0.22 | 85.07 | 108.92 | 94 | 7261.21 | 789457.57 | 2727406.06 | 29.9849 | -96.7022 | 324.56
7765 | 0.84 | 285.93 | 7760.21 | 95.35 | -68.64 | -117.39 | 0.44 | 0.44 | 0.06 | 0.12 | 93 | 7354.21 | 789457.85 | 2727405.07 | 29.9849 | -96.7022 | 324.25
7859 | 0.64 | 352.31 | 7854.2 | 96.06 | -69.37 | -118.4 | 0.88 | -0.21 | 70.62 | 134.86 | 94 | 7448.2 | 789458.56 | 2727404.34 | 29.9849 | -96.7022 | 324.16
7953 | 0.27 | 253.73 | 7948.2 | 96.52 | -69.66 | -118.93 | 0.78 | -0.39 | -104.87 | -158.57 | 94 | 7542.2 | 789459.02 | 2727404.05 | 29.9849 | -96.7022 | 324.18
8046 | 0.8 | 248.35 | 8041.19 | 96.22 | -70.47 | -119.2 | 0.57 | 0.57 | -5.78 | -8.11 | 93 | 7635.19 | 789458.72 | 2727403.24 | 29.9849 | -96.7022 | 323.78
8140 | 0.57 | 143.35 | 8135.19 | 95.6 | -70.8 | -118.92 | 1.17 | -0.24 | -111.7 | -149.84 | 94 | 7729.19 | 789458.1 | 2727402.91 | 29.9849 | -96.7022 | 323.48
8234 | 0.9 | 124.35 | 8229.18 | 94.81 | -69.91 | -117.74 | 0.43 | 0.35 | -20.21 | -46.2 | 94 | 7823.18 | 789457.31 | 2727403.8 | 29.9849 | -96.7022 | 323.59
8328 | 0.66 | 123.77 | 8323.17 | 94.09 | -68.85 | -116.53 | 0.26 | -0.26 | -0.62 | -178.41 | 94 | 7917.17 | 789456.59 | 2727404.86 | 29.9849 | -96.7022 | 323.8
8422 | 0.59 | 126.94 | 8417.17 | 93.5 | -68.02 | -115.54 | 0.08 | -0.07 | 3.37 | 155.29 | 94 | 8011.17 | 789456 | 2727405.69 | 29.9849 | -96.7022 | 323.97
8516 | 0.61 | 94.17 | 8511.16 | 93.17 | -67.13 | -114.74 | 0.36 | 0.02 | -34.86 | -103.14 | 94 | 8105.16 | 789455.67 | 2727406.58 | 29.9849 | -96.7022 | 324.23
8610 | 0.56 | 85.61 | 8605.16 | 93.17 | -66.17 | -114.15 | 0.11 | -0.05 | -9.11 | -124.01 | 94 | 8199.16 | 789455.67 | 2727407.54 | 29.9849 | -96.7022 | 324.62
8704 | 0.57 | 56.41 | 8699.15 | 93.46 | -65.33 | -113.85 | 0.3 | 0.01 | -31.06 | -102.65 | 94 | 8293.15 | 789455.96 | 2727408.38 | 29.9849 | -96.7022 | 325.05
8798 | 0.62 | 17.7 | 8793.15 | 94.21 | -64.78 | -114.1 | 0.42 | 0.05 | -41.18 | -102.53 | 94 | 8387.15 | 789456.71 | 2727408.93 | 29.9849 | -96.7022 | 325.49
8892 | 0.65 | 355.67 | 8887.14 | 95.22 | -64.67 | -114.83 | 0.26 | 0.03 | 23.44 | -94.09 | 94 | 8481.14 | 789457.72 | 2727409.04 | 29.9849 | -96.7022 | 325.82
8986 | 0.85 | 346.54 | 8981.13 | 96.43 | -64.87 | -115.91 | 0.25 | 0.21 | -9.71 | -35.48 | 94 | 8575.13 | 789458.93 | 2727408.84 | 29.9849 | -96.7022 | 326.07
9080 | 1.07 | 341.32 | 9075.12 | 97.94 | -65.31 | -117.37 | 0.25 | 0.23 | -5.55 | -24.3 | 94 | 8669.12 | 789460.44 | 2727408.4 | 29.9849 | -96.7022 | 326.3
9174 | 1.33 | 335.34 | 9169.1 | 99.76 | -66.05 | -119.26 | 0.31 | 0.28 | -6.36 | -28.73 | 94 | 8763.1 | 789462.26 | 2727407.66 | 29.9849 | -96.7022 | 326.49
9268 | 1.66 | 329.64 | 9263.07 | 101.93 | -67.19 | -121.67 | 0.38 | 0.35 | -6.06 | -27.13 | 94 | 8857.07 | 789464.43 | 2727406.52 | 29.9849 | -96.7022 | 326.61
9361 | 2.01 | 325.88 | 9356.02 | 104.44 | -68.79 | -124.63 | 0.4 | 0.38 | -4.04 | -20.87 | 93 | 8950.02 | 789466.94 | 2727404.92 | 29.985 | -96.7022 | 326.63
9455 | 1.61 | 300.71 | 9449.97 | 106.48 | -70.85 | -127.51 | 0.94 | -0.43 | -26.78 | -128.92 | 94 | 9043.97 | 789468.98 | 2727402.86 | 29.985 | -96.7022 | 326.36
9549 | 0.68 | 301.23 | 9543.95 | 107.45 | -72.46 | -129.26 | 0.99 | -0.99 | 0.55 | 179.62 | 94 | 9137.95 | 789469.95 | 2727401.25 | 29.985 | -96.7022 | 326
9643 | 0.79 | 8.2 | 9637.95 | 108.38 | -72.85 | -130.23 | 0.87 | 0.12 | 71.24 | 117.03 | 94 | 9231.95 | 789470.88 | 2727400.86 | 29.985 | -96.7022 | 326.09
9738 | 1.29 | 6.27 | 9732.93 | 110.09 | -72.64 | -131.45 | 0.53 | 0.53 | -2.03 | -4.97 | 95 | 9326.93 | 789472.59 | 2727401.07 | 29.985 | -96.7022 | 326.58
9831 | 1.49 | 353.25 | 9825.9 | 112.33 | -72.66 | -133.23 | 0.4 | 0.22 | 14 | -64.28 | 93 | 9419.9 | 789474.83 | 2727401.05 | 29.985 | -96.7022 | 327.1
9925 | 1.84 | 344.04 | 9919.87 | 114.99 | -73.22 | -135.67 | 0.47 | 0.37 | -9.8 | -42.06 | 94 | 9513.87 | 789477.49 | 2727400.49 | 29.985 | -96.7022 | 327.51
10018 | 1.11 | 340.64 | 10012.83 | 117.28 | -73.93 | -137.9 | 0.79 | -0.78 | -3.66 | -174.86 | 93 | 9606.83 | 789479.78 | 2727399.78 | 29.985 | -96.7022 | 327.77
10112 | 0.95 | 327.46 | 10106.82 | 118.8 | -74.65 | -139.54 | 0.3 | -0.17 | -14.02 | -130.5 | 94 | 9700.82 | 789481.3 | 2727399.06 | 29.985 | -96.7022 | 327.85
10205 | 1.32 | 326.51 | 10199.8 | 120.34 | -75.66 | -141.37 | 0.4 | 0.4 | -1.02 | -3.39 | 93 | 9793.8 | 789482.84 | 2727398.05 | 29.985 | -96.7022 | 327.84
10300 | 0.38 | 315.03 | 10294.79 | 121.47 | -76.48 | -142.78 | 1 | -0.99 | -12.08 | -175.44 | 95 | 9888.79 | 789483.97 | 2727397.23 | 29.985 | -96.7022 | 327.8
10394 | 0.28 | 340.05 | 10388.79 | 121.91 | -76.78 | -143.31 | 0.18 | -0.11 | 26.62 | 136.84 | 94 | 9982.79 | 789484.41 | 2727396.93 | 29.985 | -96.7022 | 327.8
10488 | 1.15 | 356.28 | 10482.78 | 123.07 | -76.92 | -144.3 | 0.94 | 0.93 | 17.27 | 21.3 | 94 | 10076.78 | 789485.57 | 2727396.79 | 29.985 | -96.7022 | 327.99
10582 | 0.57 | 50.24 | 10576.77 | 124.31 | -76.62 | -145.09 | 1 | -0.62 | 57.4 | 150.5 | 94 | 10170.77 | 789486.81 | 2727397.09 | 29.985 | -96.7022 | 328.35
10675 | 0.82 | 134.06 | 10669.76 | 124.14 | -75.79 | -144.45 | 1.02 | 0.27 | 90.13 | 120.58 | 93 | 10263.76 | 789486.64 | 2727397.92 | 29.985 | -96.7022 | 328.6
10770 | 0.62 | 162.14 | 10764.76 | 123.18 | -75.14 | -143.29 | 0.42 | -0.21 | 29.56 | 133.09 | 95 | 10358.76 | 789485.68 | 2727398.57 | 29.985 | -96.7022 | 328.62
10863 | 0.71 | 210.73 | 10857.75 | 122.2 | -75.28 | -142.61 | 0.59 | 0.1 | 52.25 | 105.77 | 93 | 10451.75 | 789484.7 | 2727398.43 | 29.985 | -96.7022 | 328.36
10957 | 1.41 | 232.76 | 10951.74 | 121 | -76.5 | -142.42 | 0.85 | 0.74 | 23.44 | 41.53 | 94 | 10545.74 | 789483.5 | 2727397.21 | 29.985 | -96.7022 | 327.7
11052 | 1.9 | 245.75 | 11046.7 | 119.65 | -78.87 | -142.82 | 0.65 | 0.52 | 13.67 | 44.05 | 95 | 10640.7 | 789482.15 | 2727394.84 | 29.985 | -96.7022 | 326.61
11145 | 2.22 | 258.66 | 11139.64 | 118.66 | -82.04 | -144 | 0.6 | 0.34 | 13.88 | 61.98 | 93 | 10733.64 | 789481.16 | 2727391.67 | 29.985 | -96.7022 | 325.34
11239 | 1.24 | 229.24 | 11233.59 | 117.64 | -84.6 | -144.77 | 1.37 | -1.04 | -31.3 | -151.88 | 94 | 10827.59 | 789480.14 | 2727389.11 | 29.985 | -96.7023 | 324.28
11334 | 1.43 | 216.8 | 11328.57 | 116.02 | -86.09 | -144.42 | 0.36 | 0.2 | -13.09 | -63.07 | 95 | 10922.57 | 789478.52 | 2727387.62 | 29.985 | -96.7023 | 323.43
11427 | 2.01 | 227.04 | 11421.53 | 113.98 | -87.97 | -143.98 | 0.7 | 0.62 | 11.01 | 33.1 | 93 | 11015.53 | 789476.48 | 2727385.74 | 29.985 | -96.7023 | 322.34
11522 | 2.13 | 233.72 | 11516.46 | 111.8 | -90.62 | -143.89 | 0.28 | 0.13 | 7.03 | 66.92 | 95 | 11110.46 | 789474.3 | 2727383.09 | 29.985 | -96.7023 | 320.97
11616 | 1.49 | 252.88 | 11610.42 | 110.41 | -93.19 | -144.39 | 0.93 | -0.68 | 20.38 | 145.91 | 94 | 11204.42 | 789472.91 | 2727380.52 | 29.985 | -96.7023 | 319.83
11709 | 1.65 | 267.6 | 11703.38 | 109.99 | -95.69 | -145.6 | 0.46 | 0.17 | 15.83 | 75.83 | 93 | 11297.38 | 789472.49 | 2727378.02 | 29.985 | -96.7023 | 318.98
11802 | 1.04 | 265.94 | 11796.36 | 109.88 | -97.87 | -146.86 | 0.66 | -0.66 | -1.78 | -177.17 | 93 | 11390.36 | 789472.38 | 2727375.84 | 29.985 | -96.7023 | 318.31
11896 | 0.96 | 281.31 | 11890.34 | 109.97 | -99.49 | -147.93 | 0.3 | -0.09 | 16.35 | 114.2 | 94 | 11484.34 | 789472.47 | 2727374.22 | 29.985 | -96.7023 | 317.87
11989 | 2.07 | 268.94 | 11983.31 | 110.09 | -101.93 | -149.54 | 1.24 | 1.19 | -13.3 | -22.66 | 93 | 11577.31 | 789472.59 | 2727371.78 | 29.985 | -96.7023 | 317.2
12083 | 2.84 | 156.97 | 12077.26 | 107.92 | -102.72 | -148.31 | 4.35 | 0.82 | -119.12 | -139.92 | 94 | 11671.26 | 789470.42 | 2727370.99 | 29.985 | -96.7023 | 316.41
12183 | 10.33 | 134.78 | 12176.54 | 99.31 | -95.37 | -137.01 | 7.77 | 7.49 | -22.19 | -30.05 | 100 | 11770.54 | 789461.81 | 2727378.34 | 29.9849 | -96.7023 | 316.16
12308 | 18.38 | 139.86 | 12297.54 | 76.31 | -74.68 | -106.14 | 6.51 | 6.44 | 4.06 | 11.37 | 125 | 11891.54 | 789438.81 | 2727399.03 | 29.9849 | -96.7022 | 315.62
12403 | 26.28 | 146.12 | 12385.36 | 47.35 | -53.26 | -70.13 | 8.67 | 8.32 | 6.59 | 19.69 | 95 | 11979.36 | 789409.85 | 2727420.45 | 29.9848 | -96.7022 | 311.64
12498 | 34.6 | 146.72 | 12467.2 | 7.27 | -26.69 | -22.2 | 8.76 | 8.76 | 0.63 | 2.35 | 95 | 12061.2 | 789369.77 | 2727447.02 | 29.9847 | -96.7021 | 285.24
12592 | 42.06 | 144.87 | 12540.88 | -40.86 | 6.12 | 35.92 | 8.03 | 7.94 | -1.97 | -9.48 | 94 | 12134.88 | 789321.64 | 2727479.83 | 29.9845 | -96.702 | 171.48
12688 | 51.93 | 141.23 | 12606.29 | -96.77 | 48.4 | 106 | 10.65 | 10.28 | -3.79 | -16.36 | 96 | 12200.29 | 789265.73 | 2727522.11 | 29.9844 | -96.7018 | 153.43
12783 | 57.88 | 141.86 | 12660.89 | -157.62 | 96.7 | 183.69 | 6.29 | 6.26 | 0.66 | 5.13 | 95 | 12254.89 | 789204.88 | 2727570.41 | 29.9842 | -96.7017 | 148.47
12876 | 68.15 | 142.31 | 12703.03 | -222.92 | 147.55 | 266.46 | 11.05 | 11.04 | 0.48 | 2.34 | 93 | 12297.03 | 789139.58 | 2727621.26 | 29.984 | -96.7015 | 146.5
12970 | 76.14 | 140.65 | 12731.83 | -292.85 | 203.25 | 355.85 | 8.66 | 8.5 | -1.77 | -11.45 | 94 | 12325.83 | 789069.65 | 2727676.96 | 29.9838 | -96.7014 | 145.24
13064 | 74.31 | 140.23 | 12755.8 | -362.92 | 261.13 | 446.71 | 1.99 | -1.95 | -0.45 | -167.54 | 94 | 12349.8 | 788999.58 | 2727734.84 | 29.9836 | -96.7012 | 144.26
13159 | 79.6 | 141.21 | 12777.24 | -434.54 | 319.69 | 539.21 | 5.66 | 5.57 | 1.03 | 10.34 | 95 | 12371.24 | 788927.96 | 2727793.4 | 29.9834 | -96.701 | 143.66
13254 | 84.21 | 141.36 | 12790.61 | -507.9 | 378.5 | 633.23 | 4.86 | 4.85 | 0.16 | 1.86 | 95 | 12384.61 | 788854.6 | 2727852.21 | 29.9832 | -96.7008 | 143.31
13349 | 88.87 | 140.83 | 12796.34 | -581.68 | 438.04 | 728.02 | 4.94 | 4.91 | -0.56 | -6.49 | 95 | 12390.34 | 788780.82 | 2727911.75 | 29.983 | -96.7006 | 143.02
13443 | 88.06 | 140.8 | 12798.86 | -654.51 | 497.41 | 821.97 | 0.86 | -0.86 | -0.03 | -177.88 | 94 | 12392.86 | 788707.99 | 2727971.12 | 29.9828 | -96.7005 | 142.77
13537 | 88.35 | 140.78 | 12801.81 | -727.31 | 556.81 | 915.91 | 0.31 | 0.31 | -0.02 | -3.94 | 94 | 12395.81 | 788635.19 | 2728030.52 | 29.9826 | -96.7003 | 142.56
13630 | 87.11 | 140.67 | 12805.49 | -799.24 | 615.63 | 1008.81 | 1.34 | -1.33 | -0.12 | -174.94 | 93 | 12399.49 | 788563.26 | 2728089.34 | 29.9824 | -96.7001 | 142.39
13725 | 86.34 | 140.91 | 12810.92 | -872.73 | 675.59 | 1103.64 | 0.85 | -0.81 | 0.25 | 162.72 | 95 | 12404.92 | 788489.77 | 2728149.3 | 29.9822 | -96.6999 | 142.26
13820 | 86.72 | 140.95 | 12816.67 | -946.35 | 735.35 | 1198.45 | 0.4 | 0.4 | 0.04 | 6 | 95 | 12410.67 | 788416.15 | 2728209.06 | 29.982 | -96.6997 | 142.15
13915 | 87.18 | 141.04 | 12821.72 | -1020.07 | 795.06 | 1293.31 | 0.49 | 0.48 | 0.09 | 11.06 | 95 | 12415.72 | 788342.43 | 2728268.77 | 29.9818 | -96.6995 | 142.07
14009 | 87.25 | 140.95 | 12826.29 | -1093.03 | 854.15 | 1387.19 | 0.12 | 0.07 | -0.1 | -52.09 | 94 | 12420.29 | 788269.47 | 2728327.86 | 29.9816 | -96.6994 | 141.99
14103 | 86.56 | 141.02 | 12831.36 | -1165.96 | 913.24 | 1481.04 | 0.74 | -0.73 | 0.07 | 174.22 | 94 | 12425.36 | 788196.54 | 2728386.95 | 29.9814 | -96.6992 | 141.93
14197 | 88.68 | 141.94 | 12835.27 | -1239.44 | 971.73 | 1574.95 | 2.46 | 2.26 | 0.98 | 23.46 | 94 | 12429.27 | 788123.06 | 2728445.44 | 29.9812 | -96.699 | 141.9
14292 | 89.53 | 142.09 | 12836.75 | -1314.3 | 1030.19 | 1669.94 | 0.91 | 0.89 | 0.16 | 10.01 | 95 | 12430.75 | 788048.2 | 2728503.9 | 29.981 | -96.6988 | 141.91
14388 | 88.47 | 141.18 | 12838.43 | -1389.56 | 1089.76 | 1765.92 | 1.46 | -1.1 | -0.95 | -139.37 | 96 | 12432.43 | 787972.94 | 2728563.47 | 29.9808 | -96.6986 | 141.89
14482 | 88.9 | 141.15 | 12840.58 | -1462.76 | 1148.69 | 1859.89 | 0.46 | 0.46 | -0.03 | -3.99 | 94 | 12434.58 | 787899.74 | 2728622.4 | 29.9806 | -96.6985 | 141.86
14577 | 87.81 | 140.87 | 12843.31 | -1536.57 | 1208.44 | 1954.83 | 1.18 | -1.15 | -0.29 | -165.6 | 95 | 12437.31 | 787825.93 | 2728682.15 | 29.9804 | -96.6983 | 141.82
14672 | 88.14 | 140.99 | 12846.67 | -1610.28 | 1268.28 | 2049.76 | 0.37 | 0.35 | 0.13 | 19.97 | 95 | 12440.67 | 787752.22 | 2728741.99 | 29.9802 | -96.6981 | 141.78
14768 | 86.63 | 141.74 | 12851.05 | -1685.19 | 1328.15 | 2145.65 | 1.76 | -1.57 | 0.78 | 153.63 | 96 | 12445.05 | 787677.31 | 2728801.86 | 29.98 | -96.6979 | 141.76
14862 | 86.24 | 141.86 | 12856.89 | -1758.92 | 1386.17 | 2239.47 | 0.43 | -0.41 | 0.13 | 162.93 | 94 | 12450.89 | 787603.58 | 2728859.88 | 29.9797 | -96.6977 | 141.76
14956 | 86.25 | 142.01 | 12863.05 | -1832.77 | 1444 | 2333.27 | 0.16 | 0.01 | 0.16 | 86.18 | 94 | 12457.05 | 787529.73 | 2728917.71 | 29.9795 | -96.6975 | 141.77
15050 | 86 | 142.16 | 12869.4 | -1906.75 | 1501.63 | 2427.06 | 0.31 | -0.27 | 0.16 | 149.1 | 94 | 12463.4 | 787455.75 | 2728975.34 | 29.9793 | -96.6974 | 141.78
15145 | 87.64 | 142.83 | 12874.67 | -1982 | 1559.38 | 2521.9 | 1.86 | 1.73 | 0.71 | 22.21 | 95 | 12468.67 | 787380.5 | 2729033.09 | 29.9791 | -96.6972 | 141.81
15240 | 88.09 | 143.23 | 12878.21 | -2057.85 | 1616.47 | 2616.81 | 0.63 | 0.47 | 0.42 | 41.62 | 95 | 12472.21 | 787304.65 | 2729090.18 | 29.9789 | -96.697 | 141.85
15334 | 88.71 | 143.28 | 12880.83 | -2133.14 | 1672.69 | 2710.75 | 0.66 | 0.66 | 0.05 | 4.61 | 94 | 12474.83 | 787229.36 | 2729146.4 | 29.9787 | -96.6968 | 141.9
15430 | 86.31 | 141.79 | 12885.01 | -2209.26 | 1731.02 | 2806.64 | 2.94 | -2.5 | -1.55 | -148.22 | 96 | 12479.01 | 787153.24 | 2729204.73 | 29.9785 | -96.6967 | 141.92
15524 | 86.21 | 142.02 | 12891.14 | -2283.08 | 1788.89 | 2900.44 | 0.27 | -0.11 | 0.24 | 113.55 | 94 | 12485.14 | 787079.42 | 2729262.6 | 29.9783 | -96.6965 | 141.92
15619 | 87.41 | 143.2 | 12896.42 | -2358.44 | 1846.49 | 2995.28 | 1.77 | 1.26 | 1.24 | 44.51 | 95 | 12490.42 | 787004.06 | 2729320.2 | 29.9781 | -96.6963 | 141.94
15714 | 87.25 | 143.29 | 12900.85 | -2434.47 | 1903.27 | 3090.15 | 0.19 | -0.17 | 0.09 | 150.67 | 95 | 12494.85 | 786928.03 | 2729376.98 | 29.9779 | -96.6961 | 141.98
15809 | 88.47 | 141.61 | 12904.4 | -2509.73 | 1961.13 | 3185.08 | 2.18 | 1.28 | -1.77 | -54.03 | 95 | 12498.4 | 786852.77 | 2729434.84 | 29.9777 | -96.696 | 142
15903 | 89.44 | 141.89 | 12906.11 | -2583.54 | 2019.31 | 3279.06 | 1.07 | 1.03 | 0.3 | 16.1 | 94 | 12500.11 | 786778.96 | 2729493.02 | 29.9774 | -96.6958 | 141.99
15998 | 90.53 | 142.06 | 12906.14 | -2658.37 | 2077.83 | 3374.06 | 1.16 | 1.15 | 0.18 | 8.86 | 95 | 12500.14 | 786704.13 | 2729551.54 | 29.9772 | -96.6956 | 141.99
16093 | 89.58 | 140.74 | 12906.04 | -2732.61 | 2137.1 | 3469.05 | 1.71 | -1 | -1.39 | -125.74 | 95 | 12500.04 | 786629.89 | 2729610.81 | 29.977 | -96.6954 | 141.97
16187 | 89.2 | 141.16 | 12907.05 | -2805.61 | 2196.31 | 3563.03 | 0.6 | -0.4 | 0.45 | 132.14 | 94 | 12501.05 | 786556.89 | 2729670.02 | 29.9768 | -96.6952 | 141.95
16282 | 88.17 | 141.87 | 12909.23 | -2879.95 | 2255.42 | 3658 | 1.32 | -1.08 | 0.75 | 145.44 | 95 | 12503.23 | 786482.55 | 2729729.13 | 29.9766 | -96.695 | 141.93
16376 | 87.7 | 141.26 | 12912.61 | -2953.53 | 2313.81 | 3751.94 | 0.82 | -0.5 | -0.65 | -127.64 | 94 | 12506.61 | 786408.97 | 2729787.52 | 29.9764 | -96.6949 | 141.92
16471 | 87.75 | 141.09 | 12916.38 | -3027.49 | 2373.32 | 3846.86 | 0.19 | 0.05 | -0.18 | -73.6 | 95 | 12510.38 | 786335.01 | 2729847.03 | 29.9762 | -96.6947 | 141.91
16564 | 87.32 | 141.22 | 12920.38 | -3099.85 | 2431.6 | 3939.77 | 0.48 | -0.46 | 0.14 | 163.2 | 93 | 12514.38 | 786262.65 | 2729905.31 | 29.976 | -96.6945 | 141.89
16659 | 86.88 | 142.83 | 12925.19 | -3174.64 | 2489.98 | 4034.64 | 1.75 | -0.46 | 1.69 | 105.34 | 95 | 12519.19 | 786187.86 | 2729963.69 | 29.9758 | -96.6943 | 141.89
16753 | 86.04 | 141.69 | 12930.99 | -3248.83 | 2547.4 | 4128.46 | 1.5 | -0.89 | -1.21 | -126.47 | 94 | 12524.99 | 786113.67 | 2730021.11 | 29.9756 | -96.6941 | 141.9
16848 | 87.69 | 141.82 | 12936.19 | -3323.33 | 2606.12 | 4223.31 | 1.74 | 1.74 | 0.14 | 4.5 | 95 | 12530.19 | 786039.17 | 2730079.83 | 29.9754 | -96.694 | 141.9
16942 | 88.4 | 142.25 | 12939.4 | -3397.39 | 2663.91 | 4317.26 | 0.88 | 0.76 | 0.46 | 31.19 | 94 | 12533.4 | 785965.11 | 2730137.62 | 29.9752 | -96.6938 | 141.9
17037 | 87.03 | 141.52 | 12943.18 | -3472.07 | 2722.5 | 4412.18 | 1.63 | -1.44 | -0.77 | -151.98 | 95 | 12537.18 | 785890.43 | 2730196.21 | 29.975 | -96.6936 | 141.9
17131 | 87.11 | 141.32 | 12947.99 | -3545.46 | 2781.04 | 4506.05 | 0.23 | 0.09 | -0.21 | -68.18 | 94 | 12541.99 | 785817.04 | 2730254.75 | 29.9748 | -96.6934 | 141.89
17224 | 86.36 | 141.59 | 12953.29 | -3618.08 | 2838.9 | 4598.9 | 0.86 | -0.81 | 0.29 | 160.24 | 93 | 12547.29 | 785744.42 | 2730312.61 | 29.9746 | -96.6933 | 141.88
17319 | 86.19 | 141.42 | 12959.46 | -3692.28 | 2897.91 | 4693.69 | 0.25 | -0.18 | -0.18 | -135.07 | 95 | 12553.46 | 785670.22 | 2730371.62 | 29.9744 | -96.6931 | 141.87
17414 | 85.99 | 141.83 | 12965.94 | -3766.58 | 2956.75 | 4788.47 | 0.48 | -0.21 | 0.43 | 116.07 | 95 | 12559.94 | 785595.92 | 2730430.46 | 29.9741 | -96.6929 | 141.87
17509 | 86.05 | 142.18 | 12972.53 | -3841.26 | 3015.09 | 4883.24 | 0.37 | 0.06 | 0.37 | 80.26 | 95 | 12566.53 | 785521.24 | 2730488.8 | 29.9739 | -96.6927 | 141.87
17602 | 86.19 | 142.17 | 12978.82 | -3914.55 | 3071.99 | 4976.03 | 0.15 | 0.15 | -0.01 | -4.08 | 93 | 12572.82 | 785447.95 | 2730545.7 | 29.9737 | -96.6925 | 141.88
17697 | 86.23 | 142.62 | 12985.1 | -3989.65 | 3129.83 | 5070.82 | 0.47 | 0.04 | 0.47 | 84.92 | 95 | 12579.1 | 785372.85 | 2730603.54 | 29.9735 | -96.6924 | 141.89
17792 | 86.25 | 143 | 12991.33 | -4065.17 | 3187.13 | 5165.6 | 0.4 | 0.02 | 0.4 | 86.99 | 95 | 12585.33 | 785297.33 | 2730660.84 | 29.9733 | -96.6922 | 141.9
17887 | 86.79 | 143.42 | 12997.1 | -4141.11 | 3243.92 | 5260.4 | 0.72 | 0.57 | 0.44 | 37.84 | 95 | 12591.1 | 785221.39 | 2730717.63 | 29.9731 | -96.692 | 141.93
17981 | 88.02 | 143.54 | 13001.35 | -4216.57 | 3299.8 | 5354.26 | 1.31 | 1.31 | 0.13 | 5.57 | 94 | 12595.35 | 785145.93 | 2730773.51 | 29.9729 | -96.6918 | 141.95
18076 | 87.54 | 142.21 | 13005.03 | -4292.26 | 3357.1 | 5449.17 | 1.49 | -0.51 | -1.4 | -109.88 | 95 | 12599.03 | 785070.24 | 2730830.81 | 29.9727 | -96.6917 | 141.97
18170 | 87.93 | 141.53 | 13008.75 | -4366.14 | 3415.09 | 5543.1 | 0.83 | 0.41 | -0.72 | -60.16 | 94 | 12602.75 | 784996.36 | 2730888.8 | 29.9725 | -96.6915 | 141.97
18265 | 87.21 | 143.3 | 13012.78 | -4441.35 | 3472.98 | 5638.01 | 2.01 | -0.76 | 1.86 | 112.19 | 95 | 12606.78 | 784921.15 | 2730946.69 | 29.9723 | -96.6913 | 141.98
18361 | 86.01 | 142.36 | 13018.45 | -4517.72 | 3530.88 | 5733.82 | 1.59 | -1.25 | -0.98 | -142 | 96 | 12612.45 | 784844.78 | 2731004.59 | 29.972 | -96.6911 | 141.99
18455 | 86.09 | 142.07 | 13024.93 | -4591.83 | 3588.33 | 5827.6 | 0.32 | 0.09 | -0.31 | -74.55 | 94 | 12618.93 | 784770.67 | 2731062.04 | 29.9718 | -96.6909 | 141.99
18551 | 86.44 | 142.27 | 13031.18 | -4667.49 | 3647.09 | 5923.39 | 0.42 | 0.36 | 0.21 | 29.7 | 96 | 12625.18 | 784695.01 | 2731120.8 | 29.9716 | -96.6908 | 142
18644 | 86.28 | 142.72 | 13037.09 | -4741.12 | 3703.59 | 6016.2 | 0.51 | -0.17 | 0.48 | 109.62 | 93 | 12631.09 | 784621.38 | 2731177.3 | 29.9714 | -96.6906 | 142
18737 | 86.3 | 141.03 | 13043.11 | -4814.12 | 3760.89 | 6109 | 1.81 | 0.02 | -1.82 | -89.38 | 93 | 12637.11 | 784548.38 | 2731234.6 | 29.9712 | -96.6904 | 142
18832 | 88.48 | 140.8 | 13047.43 | -4887.78 | 3820.72 | 6203.88 | 2.31 | 2.29 | -0.24 | -6.02 | 95 | 12641.43 | 784474.72 | 2731294.43 | 29.971 | -96.6902 | 141.99
18926 | 89.25 | 141.49 | 13049.29 | -4960.97 | 3879.68 | 6297.85 | 1.1 | 0.82 | 0.73 | 41.87 | 94 | 12643.29 | 784401.53 | 2731353.39 | 29.9708 | -96.69 | 141.97
19021 | 90.19 | 141.03 | 13049.76 | -5035.07 | 3939.12 | 6392.85 | 1.1 | 0.99 | -0.48 | -26.08 | 95 | 12643.76 | 784327.43 | 2731412.83 | 29.9706 | -96.6899 | 141.96
19114 | 89.27 | 140.9 | 13050.2 | -5107.3 | 3997.69 | 6485.83 | 1 | -0.99 | -0.14 | -171.96 | 93 | 12644.2 | 784255.2 | 2731471.4 | 29.9704 | -96.6897 | 141.95
19208 | 89.45 | 140.47 | 13051.25 | -5180.02 | 4057.25 | 6579.81 | 0.5 | 0.19 | -0.46 | -67.29 | 94 | 12645.25 | 784182.48 | 2731530.96 | 29.9702 | -96.6895 | 141.93
19301 | 87.61 | 139.94 | 13053.63 | -5251.45 | 4116.75 | 6672.73 | 2.06 | -1.98 | -0.57 | -163.94 | 93 | 12647.63 | 784111.05 | 2731590.46 | 29.97 | -96.6893 | 141.91
19394 | 87.18 | 141.01 | 13057.86 | -5323.11 | 4175.87 | 6765.61 | 1.24 | -0.46 | 1.15 | 111.94 | 93 | 12651.86 | 784039.39 | 2731649.58 | 29.9698 | -96.6891 | 141.89
19488 | 87.63 | 141.5 | 13062.11 | -5396.35 | 4234.64 | 6859.5 | 0.71 | 0.48 | 0.52 | 47.42 | 94 | 12656.11 | 783966.15 | 2731708.35 | 29.9696 | -96.689 | 141.88
19583 | 87.9 | 142.24 | 13065.82 | -5471.02 | 4293.26 | 6954.43 | 0.83 | 0.28 | 0.78 | 69.96 | 95 | 12659.82 | 783891.48 | 2731766.97 | 29.9694 | -96.6888 | 141.88
19677 | 88.21 | 142.54 | 13069.01 | -5545.44 | 4350.59 | 7048.37 | 0.46 | 0.33 | 0.32 | 44.05 | 94 | 12663.01 | 783817.06 | 2731824.3 | 29.9692 | -96.6886 | 141.88
19773 | 88.42 | 143.23 | 13071.83 | -5621.96 | 4408.49 | 7144.32 | 0.75 | 0.22 | 0.72 | 73.08 | 96 | 12665.83 | 783740.54 | 2731882.2 | 29.969 | -96.6884 | 141.9
19868 | 86.89 | 142.85 | 13075.72 | -5697.81 | 4465.56 | 7239.21 | 1.66 | -1.61 | -0.4 | -166.07 | 95 | 12669.72 | 783664.69 | 2731939.27 | 29.9688 | -96.6882 | 141.91
19963 | 87.69 | 143.74 | 13080.21 | -5773.88 | 4522.28 | 7334.08 | 1.26 | 0.84 | 0.94 | 48.04 | 95 | 12674.21 | 783588.62 | 2731995.99 | 29.9685 | -96.6881 | 141.93
20057 | 87.85 | 143.78 | 13083.87 | -5849.64 | 4577.81 | 7427.95 | 0.18 | 0.17 | 0.04 | 14.03 | 94 | 12677.87 | 783512.86 | 2732051.52 | 29.9683 | -96.6879 | 141.95
20152 | 87.94 | 144.04 | 13087.36 | -5926.36 | 4633.73 | 7522.83 | 0.29 | 0.09 | 0.27 | 70.9 | 95 | 12681.36 | 783436.14 | 2732107.44 | 29.9681 | -96.6877 | 141.98
20246 | 87.88 | 143.83 | 13090.79 | -6002.29 | 4689.03 | 7616.71 | 0.23 | -0.06 | -0.22 | -105.96 | 94 | 12684.79 | 783360.21 | 2732162.74 | 29.9679 | -96.6876 | 142
20340 | 87.84 | 143.53 | 13094.3 | -6077.98 | 4744.67 | 7710.59 | 0.32 | -0.04 | -0.32 | -97.61 | 94 | 12688.3 | 783284.52 | 2732218.38 | 29.9677 | -96.6874 | 142.02
20368 | 87.64 | 143.88 | 13095.4 | -6100.53 | 4761.23 | 7738.56 | 1.44 | -0.71 | 1.25 | 119.77 | 28 | 12689.4 | 783261.97 | 2732234.94 | 29.9676 | -96.6873 | 142.03
20437 | 87.64 | 143.88 | 13098.24 | -6156.22 | 4801.87 | 7807.46 | 0 | 0 | 0 | 0 | 69 | 12692.24 | 783206.28 | 2732275.58 | 29.9675 | -96.6872 | 142.05

## 6_18_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/18/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18730 |  |  | Well Cost($): |  | 18730
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: |  | PV:
End Depth (Usft): |  | 108 |  | 108 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 43518 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 2.5 |  | 2.5 |  | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL616
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Xavier Cantu |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 |  |  |  | 8 | [5 empty] | 37.48 |  | 38.98
Nortrak Stabilizer (BFF) 13" |  |  |  | 8.125 | 2.875 |  |  |  |  | 7.63 |  | 46.61
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 54.54
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 58.26
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 87.03
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 115.44
Crossover Sub |  |  |  | 8.25 | 2.875 |  |  |  |  | 2.56 |  | 118
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 392.54
392.54
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800053 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.78 |  | 1.5 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/18/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/18/2021 |  | 5 |  | 100 |  | 4 | 400
8 Motor Reline |  |  |  |  | 06/18/2021 |  | 6 |  | 10500 |  | 1 | 10500
Multi Rig Discount |  |  |  |  | 06/18/2021 |  | 20 |  | -400 |  | 1 | -400
13 Stab Rental (Used) |  |  |  |  | 06/18/2021 |  | 7 |  | 1150 |  | 1 | 1150
13 Stab Rental (Not Used) |  |  |  |  | 06/18/2021 |  | 8 |  | 230 |  | 1 | 230
Total | [11 empty] | 18730
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/18/2021 | 00:00 | 19:30 | 19.5 | 108 | 108 | 0 | SUR |  | 24B | STBY
06/18/2021 | 19:30 | 21:30 | 2 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | Pick up BHA 1
06/18/2021 | 21:30 | 24:00 | 2.5 | 108 | 108 | 0 | SUR | 1: BHA 1 | 8O | Fix standpipe gasket
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_19_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 8230 |  |  | Well Cost($): |  | 26960
|  |  |  | 24hr Summary: |  | P/U BHA, Work on Rig, Spud in
|  |  |  | 24hr Lookahead: |  | Drill ahead and nudge 6*
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 1 | PV:
End Depth (Usft): |  | 3845 |  | 3845 |  | OD (in): |  |  |  | 300: | 1 | YP: | 1
Total Drilled (Usft): |  | 3737 |  | 3737 |  | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): |  | 154 |  | 154 | [5 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): |  | 3583 |  | 3583 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: |  | 10.28 / 2.33 |  | 10.28 / 2.33 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | .4/99.6
Slide Drilling Hrs: |  | 1.38 |  | 1.38 |  | SN: |  | 43518 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: |  | 8.9 |  | 8.9 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 402.58 / 111.33 |  | 402.58 / 111.33 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 20 |  | 22.5 |  | Grade In:
% Slide: |  | 4.12 |  | 4.12 |  | Grade Out:
% Rotary: |  | 95.88 |  | 95.88 |  | Make / Model: |  | Ulterra / SPL616
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Xavier Cantu |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 |  |  |  | 8 | [5 empty] | 37.48 |  | 38.98
Nortrak Stabilizer (BFF) 13" |  |  |  | 8.125 | 2.875 |  |  |  |  | 7.63 |  | 46.61
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 54.54
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 58.26
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 87.03
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 115.44
Crossover Sub |  |  |  | 8.25 | 2.875 |  |  |  |  | 2.56 |  | 118
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 392.54
392.54
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800053 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.78 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
143 | 0.36 | 30.81 | 143 | 0.39 | 0.23 | 0.25 |  | 30.81 | -0.16 | 0.25 |  | 0 | 143
234 | 0.42 | 22.16 | 234 | 0.94 | 0.5 | 0.09 |  | -48.84 | -0.43 | 0.07 |  | 0 | 91
326 | 0.51 | 19.26 | 325.99 | 1.64 | 0.76 | 0.1 |  | -16.11 | -0.82 | 0.1 |  | 0 | 92
421 | 0.47 | 24.42 | 420.99 | 2.39 | 1.07 | 0.06 |  | 134.75 | -1.22 | -0.04 |  | 0 | 95
515 | 0.55 | 19.81 | 514.99 | 3.17 | 1.38 | 0.1 |  | -29.47 | -1.64 | 0.09 |  | 0 | 94
609 | 0.4 | 23.04 | 608.98 | 3.89 | 1.66 | 0.16 |  | 171.49 | -2.04 | -0.16 |  | 0 | 94
704 | 0.34 | 81.83 | 703.98 | 4.24 | 2.07 | 0.39 |  | 127.58 | -2.06 | -0.06 |  | 0 | 95
798 | 0.52 | 138.26 | 797.98 | 3.96 | 2.63 | 0.46 |  | 96.9 | -1.49 | 0.19 |  | 0 | 94
892 | 0.78 | 155.99 | 891.97 | 3.06 | 3.17 | 0.35 |  | 46.81 | -0.45 | 0.28 |  | 0 | 94
986 | 1.17 | 159.22 | 985.96 | 1.58 | 3.77 | 0.42 |  | 9.64 | 1.09 | 0.41 |  | 0 | 94
1079 | 1.22 | 164.31 | 1078.94 | -0.26 | 4.38 | 0.13 |  | 67.34 | 2.91 | 0.05 |  | 0 | 93
1173 | 1.15 | 164.93 | 1172.92 | -2.14 | 4.89 | 0.08 |  | 169.93 | 4.7 | -0.07 |  | 0 | 94
1266 | 0.84 | 165.9 | 1265.91 | -3.7 | 5.3 | 0.33 |  | 177.37 | 6.18 | -0.33 |  | 0 | 93
1360 | 0.66 | 162.8 | 1359.9 | -4.89 | 5.63 | 0.2 |  | -168.84 | 7.32 | -0.19 |  | 0 | 94
1454 | 0.39 | 179.35 | 1453.89 | -5.72 | 5.79 | 0.33 |  | 158.78 | 8.08 | -0.29 |  | 0 | 94
1548 | 0.14 | 166.63 | 1547.89 | -6.15 | 5.82 | 0.27 |  | -173.06 | 8.44 | -0.27 |  | 0 | 94
1642 | 0.04 | 343.05 | 1641.89 | -6.23 | 5.84 | 0.19 |  | 179.2 | 8.51 | -0.11 |  | 0 | 94
1736 | 0.03 | 321.69 | 1735.89 | -6.18 | 5.82 | 0.02 |  | -137.82 | 8.46 | -0.01 |  | 0 | 94
1829 | 0.12 | 199.85 | 1828.89 | -6.26 | 5.77 | 0.15 |  | -132.47 | 8.48 | 0.1 |  | 0 | 93
1923 | 0.08 | 271.91 | 1922.89 | -6.35 | 5.67 | 0.13 |  | 141.4 | 8.49 | -0.04 |  | 0 | 94
2017 | 0.83 | 327.04 | 2016.89 | -5.77 | 5.23 | 0.84 |  | 59.91 | 7.77 | 0.8 |  | 0 | 94
2110 | 1.82 | 332.89 | 2109.86 | -3.89 | 4.19 | 1.07 |  | 10.71 | 5.65 | 1.06 |  | 0 | 93
2203 | 2.89 | 334.42 | 2202.78 | -0.46 | 2.51 | 1.15 |  | 4.13 | 1.91 | 1.15 |  | 1.65 | 93
2298 | 3.92 | 329.96 | 2297.61 | 4.51 | -0.15 | 1.12 |  | -16.66 | -3.64 | 1.08 |  | -4.69 | 95
2392 | 4.74 | 326.3 | 2391.34 | 10.52 | -3.92 | 0.92 |  | -20.45 | -10.69 | 0.87 |  | -3.89 | 94
2486 | 5.67 | 321.12 | 2484.96 | 17.37 | -8.98 | 1.11 |  | -29.4 | -19.21 | 0.99 |  | -5.51 | 94
2579 | 6.05 | 319.05 | 2577.47 | 24.64 | -15.08 | 0.47 |  | -30.11 | -28.7 | 0.41 |  | -2.23 | 93
2674 | 5.87 | 318.34 | 2671.96 | 32.05 | -21.59 | 0.2 |  | -158.08 | -38.55 | -0.19 |  | -0.75 | 95
2767 | 5.88 | 319.22 | 2764.47 | 39.21 | -27.86 | 0.1 |  | 84.1 | -48.05 | 0.01 |  | 0.95 | 93
2861 | 5.87 | 317.91 | 2857.97 | 46.43 | -34.23 | 0.14 |  | -94.92 | -57.66 | -0.01 |  | -1.39 | 94
2955 | 5.43 | 321.26 | 2951.52 | 53.46 | -40.24 | 0.58 |  | 144.8 | -66.9 | -0.47 |  | 3.56 | 94
3049 | 4.44 | 326.48 | 3045.17 | 59.97 | -45.03 | 1.16 |  | 158.19 | -74.97 | -1.05 |  | 5.55 | 94
3143 | 3.56 | 330.79 | 3138.94 | 65.55 | -48.46 | 0.99 |  | 163.28 | -81.48 | -0.94 |  | 4.59 | 94
3238 | 2.58 | 336.95 | 3233.8 | 70.09 | -50.74 | 1.09 |  | 164.45 | -86.46 | -1.03 |  | 6.48 | 95
3332 | 1.8 | 348.65 | 3327.73 | 73.48 | -51.86 | 0.95 |  | 155.94 | -89.82 | -0.83 |  | 12.45 | 94
3426 | 1.06 | 13.92 | 3421.7 | 75.77 | -51.94 | 1.02 |  | 151.73 | -91.67 | -0.79 |  | 26.88 | 94
3520 | 0.9 | 30.37 | 3515.69 | 77.26 | -51.36 | 0.34 |  | 127.68 | -92.48 | -0.17 |  | 0 | 94
3614 | 0.75 | 34.81 | 3609.68 | 78.4 | -50.63 | 0.17 |  | 159.13 | -92.93 | -0.16 |  | 0 | 94
3708 | 0.81 | 32.52 | 3703.67 | 79.46 | -49.92 | 0.07 |  | -28.6 | -93.33 | 0.06 |  | 0 | 94
3779 | 0.66 | 13.43 | 3774.67 | 80.28 | -49.56 | 0.4 |  | -130.8 | -93.75 | -0.21 |  | 0 | 71
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 363.4 | 29.23 | 97.9 | 242 | 868.37 | 1874.88 | 1437.21 | 0 | 111.86 | 98.02 | 88.6 | 8580.65 | 0
Run | 363.4 | 29.23 | 97.9 | 242 | 868.37 | 1874.88 | 1437.21 | 0 | 111.86 | 98.02 | 88.6 | 8580.65 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/19/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/19/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/19/2021 |  | 20 |  | -400 |  | 1 | -400
13 Stab Rental (Used) |  |  |  |  | 06/19/2021 |  | 7 |  | 1150 |  | 1 | 1150
13 Stab Rental (Not Used) |  |  |  |  | 06/19/2021 |  | 8 |  | 230 |  | 1 | 230
Total | [11 empty] | 8230
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/19/2021 | 00:00 | 01:30 | 1.5 | 108 | 108 | 0 | SUR | 1: BHA 1 | 8O | Rerplace standpipe gasket
06/19/2021 | 01:30 | 02:40 | 1.17 | 108 | 108 | 0 | SUR | 1: BHA 1 | 8A | Troubleshoot tope drive
06/19/2021 | 02:40 | 03:40 | 1 | 108 | 300 | 192 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/300.00, w/WOB 25.00,Flow 560.00, RPM 60.00, Press 850.00, Tq 4000.00, ROP 192.00, Diff 200.00, Temp 70.00
06/19/2021 | 03:40 | 04:00 | 0.33 | 300 | 392 | 92 | SUR | 1: BHA 1 | 2K | Rotary Drill f/300.00 t/392.00, w/WOB 25.00,Flow 700.00, RPM 75.00, Press 950.00, Tq 4000.00, ROP 276.00, Diff 200.00, Temp 80.00
06/19/2021 | 04:00 | 05:43 | 1.72 | 392 | 1126 | 734 | SUR | 1: BHA 1 | 2K | Rotary Drill f/392.00 t/1126.00, w/WOB 25.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 427.57, Diff 250.00, Temp 90.00
06/19/2021 | 05:43 | 05:55 | 0.2 | 1126 | 1332 | 206 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1126.00 t/1332.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 1030.00, Diff 250.00, Temp 93.00
06/19/2021 | 05:55 | 06:00 | 0.08 | 1332 | 1332 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 06:00 | 06:07 | 0.12 | 1332 | 1426 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1332.00 t/1426.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 805.71, Diff 250.00, Temp 93.00
06/19/2021 | 06:07 | 06:17 | 0.17 | 1426 | 1426 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 06:17 | 06:27 | 0.17 | 1426 | 1520 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1426.00 t/1520.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 564.00, Diff 250.00, Temp 93.00
06/19/2021 | 06:27 | 06:33 | 0.1 | 1520 | 1520 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 06:33 | 06:45 | 0.2 | 1520 | 1614 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1520.00 t/1614.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 470.00, Diff 250.00, Temp 95.00
06/19/2021 | 06:45 | 06:49 | 0.07 | 1614 | 1614 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 06:49 | 06:57 | 0.13 | 1614 | 1708 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1614.00 t/1708.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 705.00, Diff 250.00, Temp 95.00
06/19/2021 | 06:57 | 07:01 | 0.07 | 1708 | 1708 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 07:01 | 07:10 | 0.15 | 1708 | 1802 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1708.00 t/1802.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 626.67, Diff 250.00, Temp 95.00
06/19/2021 | 07:10 | 07:16 | 0.1 | 1802 | 1802 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 07:16 | 07:22 | 0.1 | 1802 | 1895 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1802.00 t/1895.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 930.00, Diff 250.00, Temp 95.00
06/19/2021 | 07:22 | 07:26 | 0.07 | 1895 | 1895 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 07:26 | 07:40 | 0.23 | 1895 | 1989 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1895.00 t/1989.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 402.86, Diff 250.00, Temp 95.00
06/19/2021 | 07:40 | 07:46 | 0.1 | 1989 | 1989 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 07:46 | 07:57 | 0.18 | 1989 | 2004 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1989.00 t/2004.00, TF 330.00M, w/WOB 27.00,Flow 880.00, Press 1700.00, Tq 8000.00, ROP 81.82, Diff 250.00, Temp 95.00
06/19/2021 | 07:57 | 08:12 | 0.25 | 2004 | 2083 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2004.00 t/2083.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 316.00, Diff 250.00, Temp 95.00
06/19/2021 | 08:12 | 08:17 | 0.08 | 2083 | 2083 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 08:17 | 08:25 | 0.13 | 2083 | 2098 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2083.00 t/2098.00, TF 330.00M, w/WOB 27.00,Flow 880.00, Press 1700.00, Tq 8000.00, ROP 112.50, Diff 250.00, Temp 95.00
06/19/2021 | 08:25 | 08:35 | 0.17 | 2098 | 2176 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2098.00 t/2176.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 468.00, Diff 250.00, Temp 95.00
06/19/2021 | 08:35 | 08:39 | 0.07 | 2176 | 2176 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 08:39 | 08:46 | 0.12 | 2176 | 2191 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2176.00 t/2191.00, TF 330.00M, w/WOB 27.00,Flow 880.00, Press 1700.00, Tq 8000.00, ROP 128.57, Diff 250.00, Temp 99.00
06/19/2021 | 08:46 | 08:56 | 0.17 | 2191 | 2269 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2191.00 t/2269.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 468.00, Diff 250.00, Temp 99.00
06/19/2021 | 08:56 | 09:00 | 0.07 | 2269 | 2269 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 09:00 | 09:08 | 0.13 | 2269 | 2281 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/2269.00 t/2281.00, TF 330.00M, w/WOB 27.00,Flow 880.00, Press 1700.00, Tq 8000.00, ROP 90.00, Diff 250.00, Temp 99.00
06/19/2021 | 09:08 | 09:19 | 0.18 | 2281 | 2364 | 83 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2281.00 t/2364.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 452.73, Diff 250.00, Temp 99.00
06/19/2021 | 09:19 | 09:24 | 0.08 | 2364 | 2364 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 09:24 | 09:31 | 0.12 | 2364 | 2376 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/2364.00 t/2376.00, TF 0.00G, w/WOB 27.00,Flow 880.00, Press 1700.00, Tq 8000.00, ROP 102.86, Diff 250.00, Temp 99.00
06/19/2021 | 09:31 | 09:42 | 0.18 | 2376 | 2458 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2376.00 t/2458.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 447.27, Diff 250.00, Temp 99.00
06/19/2021 | 09:42 | 09:46 | 0.07 | 2458 | 2458 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 09:46 | 09:52 | 0.1 | 2458 | 2470 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/2458.00 t/2470.00, TF 0.00G, w/WOB 27.00,Flow 880.00, Press 1700.00, Tq 8000.00, ROP 120.00, Diff 250.00, Temp 99.00
06/19/2021 | 09:52 | 10:00 | 0.13 | 2470 | 2552 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2470.00 t/2552.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 615.00, Diff 250.00, Temp 99.00
06/19/2021 | 10:00 | 10:05 | 0.08 | 2552 | 2552 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 10:05 | 10:16 | 0.18 | 2552 | 2645 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2552.00 t/2645.00, w/WOB 27.00,Flow 880.00, RPM 100.00, Press 1700.00, Tq 8000.00, ROP 507.27, Diff 250.00, Temp 99.00
06/19/2021 | 10:16 | 10:20 | 0.07 | 2645 | 2645 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 10:20 | 10:31 | 0.18 | 2645 | 2740 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2645.00 t/2740.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 518.18, Diff 680.00, Temp 107.00
06/19/2021 | 10:31 | 10:35 | 0.07 | 2740 | 2740 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 10:35 | 10:48 | 0.22 | 2740 | 2833 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2740.00 t/2833.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 429.23, Diff 680.00, Temp 107.00
06/19/2021 | 10:48 | 10:53 | 0.08 | 2833 | 2833 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 10:53 | 11:06 | 0.22 | 2833 | 2927 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2833.00 t/2927.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 433.85, Diff 680.00, Temp 107.00
06/19/2021 | 11:06 | 11:11 | 0.08 | 2927 | 2927 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 11:11 | 11:15 | 0.07 | 2927 | 2937 | 10 | SUR | 1: BHA 1 | 2J | Slide Drill f/2927.00 t/2937.00, TF 180.00G, w/WOB 30.00,Flow 880.00, Press 2180.00, Tq 10000.00, ROP 150.00, Diff 680.00, Temp 107.00
06/19/2021 | 11:15 | 11:27 | 0.2 | 2937 | 3021 | 84 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2937.00 t/3021.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 420.00, Diff 680.00, Temp 107.00
06/19/2021 | 11:27 | 11:32 | 0.08 | 3021 | 3021 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 11:32 | 11:38 | 0.1 | 3021 | 3033 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/3021.00 t/3033.00, TF 180.00G, w/WOB 30.00,Flow 880.00, Press 2180.00, Tq 10000.00, ROP 120.00, Diff 680.00, Temp 107.00
06/19/2021 | 11:38 | 11:52 | 0.23 | 3033 | 3115 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3033.00 t/3115.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 351.43, Diff 680.00, Temp 113.00
06/19/2021 | 11:52 | 11:58 | 0.1 | 3115 | 3115 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 11:58 | 12:04 | 0.1 | 3115 | 3127 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/3115.00 t/3127.00, TF 180.00G, w/WOB 25.00,Flow 880.00, Press 2180.00, Tq 10000.00, ROP 120.00, Diff 680.00, Temp 113.00
06/19/2021 | 12:04 | 12:18 | 0.23 | 3127 | 3209 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3127.00 t/3209.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 351.43, Diff 680.00, Temp 113.00
06/19/2021 | 12:18 | 12:24 | 0.1 | 3209 | 3209 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 12:24 | 12:30 | 0.1 | 3209 | 3221 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/3209.00 t/3221.00, TF 180.00G, w/WOB 25.00,Flow 880.00, Press 2180.00, Tq 10000.00, ROP 120.00, Diff 680.00, Temp 113.00
06/19/2021 | 12:30 | 12:43 | 0.22 | 3221 | 3304 | 83 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3221.00 t/3304.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 383.08, Diff 680.00, Temp 113.00
06/19/2021 | 12:43 | 12:49 | 0.1 | 3304 | 3304 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 12:49 | 12:55 | 0.1 | 3304 | 3316 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/3304.00 t/3316.00, TF 150.00M, w/WOB 25.00,Flow 880.00, Press 2180.00, Tq 10000.00, ROP 120.00, Diff 680.00, Temp 113.00
06/19/2021 | 12:55 | 13:09 | 0.23 | 3316 | 3398 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3316.00 t/3398.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 351.43, Diff 680.00, Temp 113.00
06/19/2021 | 13:09 | 13:15 | 0.1 | 3398 | 3398 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 13:15 | 13:23 | 0.13 | 3398 | 3413 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/3398.00 t/3413.00, TF 150.00M, w/WOB 25.00,Flow 880.00, Press 2180.00, Tq 10000.00, ROP 112.50, Diff 680.00, Temp 113.00
06/19/2021 | 13:23 | 13:36 | 0.22 | 3413 | 3413 | 0 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3413.00 t/3492.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 364.62, Diff 680.00, Temp 113.00
06/19/2021 | 13:36 | 13:41 | 0.08 | 3413 | 3413 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 13:41 | 13:59 | 0.3 | 3413 | 3586 | 173 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3492.00 t/3586.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 313.33, Diff 680.00, Temp 113.00
06/19/2021 | 13:59 | 14:04 | 0.08 | 3586 | 3586 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 14:04 | 14:31 | 0.45 | 3586 | 3680 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3586.00 t/3680.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 208.89, Diff 680.00, Temp 113.00
06/19/2021 | 14:31 | 14:35 | 0.07 | 3680 | 3680 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 14:35 | 14:54 | 0.32 | 3680 | 3774 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3680.00 t/3774.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 296.84, Diff 680.00, Temp 113.00
06/19/2021 | 14:54 | 14:58 | 0.07 | 3774 | 3774 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
06/19/2021 | 14:58 | 15:14 | 0.27 | 3774 | 3845 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3774.00 t/3845.00, w/WOB 35.00,Flow 880.00, RPM 100.00, Press 2180.00, Tq 10000.00, ROP 266.25, Diff 680.00, Temp 117.00
06/19/2021 | 15:14 | 15:17 | 0.05 | 3845 | 3845 | 0 | SUR | 1: BHA 1 | 5A | Circulate
06/19/2021 | 15:17 | 18:00 | 2.72 | 3845 | 3845 | 0 | SUR | 1: BHA 1 | 6B | POOH
06/19/2021 | 18:00 | 20:00 | 2 | 3845 | 3845 | 0 | SUR | 1: BHA 1 | 6P | L/D motor, stab, & UBHO sub. Pick up drill pipe & rack back tools in derrick
06/19/2021 | 20:00 | 20:30 | 0.5 | 3845 | 3845 | 0 | SUR |  | 8P | Rig service
06/19/2021 | 20:30 | 21:00 | 0.5 | 3845 | 3845 | 0 | SUR |  | 24A | Remove conductor & install casing guide. Remove elevators & mouse hole
06/19/2021 | 21:00 | 24:00 | 3 | 3845 | 3845 | 0 | SUR |  | 12A | Rig up and run casing
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_20_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 44310
|  |  |  | 24hr Summary: |  | TD surface,POOH,LD BHA,Run casing
|  |  |  | 24hr Lookahead: |  | P/U BHA#2/ TIH/ Drill ahead
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3845 |  | 3845 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 1 | PV:
End Depth (Usft): |  | 3845 |  | 3845 |  | OD (in): |  |  |  | 300: | 1 | YP: | 1
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 1 | Viscosity: | 26
Slide Drilled (Usft): | [9 empty] | 100: | 1 | Chlorides: | 300
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids: | 0.00 / 0.40
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 1 | Oil/Water: | .4/99.6
Slide Drilling Hrs: | [5 empty] | SN: |  | 54861 |  | 10s Gel: | 1 | Weight (ppg): | 8.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) | 7.0 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: | [5 empty] | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-WT-G-X-I-CT-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Xavier Cantu |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  |  | 8 | [5 empty] | 37.46 |  | 38.96
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 46.89
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 50.61
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 79.38
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 107.79
Crossover Sub |  |  |  | 6.5 | 3 |  |  |  |  | 2.7 |  | 110.49
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 185.82 |  | 296.31
Crossover Sub |  |  |  | 6.125 | 2.75 |  |  |  |  | 2.36 |  | 298.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 573.21
22 Stds 5 in DP |  |  |  | 5 | 4.276 |  |  |  |  | 2066.2 |  | 2639.41
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.7 |  | 2664.11
2664.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800059 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 29.23 | 97.9 | 242 | 868.37 | 1874.88 | 1437.21 | 0 | 111.86 | 98.02 | 88.6 | 8580.65 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/20/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/20/2021 |  | 5 |  | 100 |  | 4 | 400
8 Motor Reline |  |  |  |  | 06/20/2021 |  | 6 |  | 10500 |  | 1 | 10500
Multi Rig Discount |  |  |  |  | 06/20/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/20/2021 | 00:00 | 05:00 | 5 | 3845 | 3845 | 0 | SUR |  | 12B | Run casimng
06/20/2021 | 05:00 | 06:00 | 1 | 3845 | 3845 | 0 | SUR |  | 1G | Clean pits
06/20/2021 | 06:00 | 10:00 | 4 | 3845 | 3845 | 0 | SUR |  | 12E | Cement
06/20/2021 | 10:00 | 11:30 | 1.5 | 3845 | 3845 | 0 | SUR |  | 24A | Prep well head
06/20/2021 | 11:30 | 15:30 | 4 | 3845 | 3845 | 0 | SUR |  | 14A | Nipplke up BOPs
06/20/2021 | 15:30 | 18:30 | 3 | 3845 | 3845 | 0 | SUR |  | 15A | Test BOPs
06/20/2021 | 18:30 | 19:00 | 0.5 | 3845 | 3845 | 0 | SUR |  | 24A | Install trip nipple & weasr bushing
06/20/2021 | 19:00 | 22:30 | 3.5 | 3845 | 3845 | 0 | SUR |  | 24A | Make up flow line & catch can
06/20/2021 | 22:30 | 24:00 | 1.5 | 3845 | 3845 | 0 | INT | 2: BHA 2 | 6O | Pick up BHA #2
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_21_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/21/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 51160
|  |  |  | 24hr Summary: |  | TIH, Drill shoe, dril ahead in intermediate
|  |  |  | 24hr Lookahead: |  | Drilling ahead
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3845 |  | 3845 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 24 | PV: | 9
End Depth (Usft): |  | 7850 |  | 7850 |  | OD (in): |  |  |  | 300: | 15 | YP: | 6
Total Drilled (Usft): |  | 4005 |  | 4005 |  | Weight (ft/lbs): |  |  |  | 200: | 11 | Viscosity: | 45
Slide Drilled (Usft): |  | 112 |  | 112 | [5 empty] | 100: | 7 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 3893 |  | 3893 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 11.17 / 3.58 |  | 11.17 / 3.58 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | .4/99.6
Slide Drilling Hrs: |  | 1.37 |  | 1.37 |  | SN: |  | 54861 |  | 10s Gel: | 4 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  | 9.8 |  | 9.8 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.0 / 124.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 397.24 / 81.95 |  | 397.24 / 81.95 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 24 |  | Grade In: |  | New
% Slide: |  | 2.8 |  | 2.8 |  | Grade Out: |  | 0-1-WT-G-X-I-CT-TD
% Rotary: |  | 97.2 |  | 97.2 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Xavier Cantu |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  |  | 8 | [5 empty] | 37.46 |  | 38.96
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 46.89
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 50.61
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 79.38
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 107.79
Crossover Sub |  |  |  | 6.5 | 3 |  |  |  |  | 2.7 |  | 110.49
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 185.82 |  | 296.31
Crossover Sub |  |  |  | 6.125 | 2.75 |  |  |  |  | 2.36 |  | 298.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 573.21
22 Stds 5 in DP |  |  |  | 5 | 4.276 |  |  |  |  | 2066.2 |  | 2639.41
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.7 |  | 2664.11
2664.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800059 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3916 | 1.08 | 359.28 | 3911.65 | 82.34 | -49.39 | 0.34 |  | -34.28 | -95.27 | 0.31 |  | 0 | 137
4010 | 1.41 | 350.28 | 4005.63 | 84.37 | -49.6 | 0.41 |  | -35.2 | -96.99 | 0.35 |  | 0 | 94
4105 | 1.5 | 342.64 | 4100.6 | 86.71 | -50.17 | 0.22 |  | -68.96 | -99.18 | 0.09 |  | 0 | 95
4199 | 0.29 | 334.04 | 4194.58 | 88.1 | -50.64 | 1.29 |  | -177.95 | -100.56 | -1.29 |  | -9.15 | 94
4292 | 0.24 | 4.12 | 4287.58 | 88.5 | -50.73 | 0.16 |  | 124.39 | -100.94 | -0.05 |  | 0 | 93
4387 | 0.65 | 1.68 | 4382.58 | 89.24 | -50.7 | 0.43 |  | -3.87 | -101.5 | 0.43 |  | 0 | 95
4480 | 1.15 | 349.02 | 4475.57 | 90.68 | -50.86 | 0.58 |  | -28.1 | -102.73 | 0.54 |  | 0 | 93
4574 | 1.12 | 339.77 | 4569.55 | 92.47 | -51.36 | 0.2 |  | -103.9 | -104.45 | -0.03 |  | 0 | 94
4668 | 0.38 | 331.91 | 4663.54 | 93.61 | -51.82 | 0.79 |  | -176 | -105.63 | -0.79 |  | 0 | 94
4762 | 0.65 | 328.26 | 4757.54 | 94.34 | -52.25 | 0.29 |  | -8.76 | -106.47 | 0.29 |  | 0 | 94
4856 | 1.67 | 279.22 | 4851.52 | 95.01 | -53.88 | 1.42 |  | -70.57 | -108 | 1.09 |  | 0 | 94
4951 | 1.9 | 279.38 | 4946.47 | 95.49 | -56.8 | 0.24 |  | 1.32 | -110.18 | 0.24 |  | 0.17 | 95
5045 | 1.93 | 281.17 | 5040.42 | 96.05 | -59.89 | 0.07 |  | 64.26 | -112.53 | 0.03 |  | 1.9 | 94
5139 | 1.26 | 271.53 | 5134.38 | 96.38 | -62.48 | 0.77 |  | -162.95 | -114.39 | -0.71 |  | -10.26 | 94
5234 | 1.1 | 266.35 | 5229.36 | 96.35 | -64.43 | 0.2 |  | -148.88 | -115.57 | -0.17 |  | 0 | 95
5327 | 1.03 | 276.83 | 5322.35 | 96.39 | -66.15 | 0.22 |  | 114.95 | -116.67 | -0.08 |  | 0 | 93
5421 | 1.08 | 282.99 | 5416.33 | 96.69 | -67.85 | 0.13 |  | 69.31 | -117.96 | 0.05 |  | 0 | 94
5516 | 1.13 | 279.46 | 5511.31 | 97.05 | -69.65 | 0.09 |  | -55.48 | -119.35 | 0.05 |  | 0 | 95
5610 | 0.67 | 232.22 | 5605.3 | 96.86 | -71 | 0.89 |  | -143.92 | -120.03 | -0.49 |  | 0 | 94
5703 | 0.63 | 227.77 | 5698.3 | 96.19 | -71.81 | 0.07 |  | -130.6 | -120 | -0.04 |  | 0 | 93
5794 | 0.55 | 258.07 | 5789.29 | 95.76 | -72.61 | 0.35 |  | 119.21 | -120.16 | -0.09 |  | 0 | 91
5887 | 0.61 | 277.7 | 5882.29 | 95.74 | -73.53 | 0.22 |  | 83.17 | -120.71 | 0.06 |  | 0 | 93
5980 | 0.43 | 200.62 | 5975.29 | 95.47 | -74.15 | 0.71 |  | -140.8 | -120.88 | -0.19 |  | 0 | 93
6074 | 0.36 | 197.49 | 6069.28 | 94.86 | -74.36 | 0.08 |  | -164.43 | -120.53 | -0.07 |  | 0 | 94
6168 | 0.33 | 210.52 | 6163.28 | 94.35 | -74.59 | 0.09 |  | 117.36 | -120.27 | -0.03 |  | 0 | 94
6262 | 0.36 | 209.87 | 6257.28 | 93.86 | -74.87 | 0.03 |  | -7.76 | -120.06 | 0.03 |  | 0 | 94
6356 | 0.55 | 25.53 | 6351.28 | 94.01 | -74.82 | 0.97 |  | 177.38 | -120.15 | 0.2 |  | 0 | 94
6450 | 0.53 | 37.47 | 6445.27 | 94.76 | -74.36 | 0.12 |  | 106.01 | -120.46 | -0.02 |  | 0 | 94
6544 | 0.27 | 24.37 | 6539.27 | 95.31 | -74.01 | 0.29 |  | -167.09 | -120.67 | -0.28 |  | 0 | 94
6638 | 0.33 | 358.11 | 6633.27 | 95.78 | -73.93 | 0.16 |  | -79.92 | -120.99 | 0.06 |  | 0 | 94
6733 | 0.33 | 355.51 | 6728.27 | 96.33 | -73.96 | 0.02 |  | -91.3 | -121.44 | 0 |  | 0 | 95
6827 | 0.86 | 113.2 | 6822.27 | 96.32 | -73.33 | 1.12 |  | 133.77 | -121.04 | 0.56 |  | 0 | 94
6921 | 1.12 | 122.32 | 6916.25 | 95.55 | -71.9 | 0.32 |  | 35.83 | -119.56 | 0.28 |  | 0 | 94
7016 | 1.02 | 119.65 | 7011.23 | 94.64 | -70.38 | 0.12 |  | -154.83 | -117.9 | -0.11 |  | 0 | 95
7110 | 0.68 | 105.13 | 7105.22 | 94.08 | -69.12 | 0.43 |  | -154.76 | -116.68 | -0.36 |  | 0 | 94
7204 | 0.48 | 81.25 | 7199.22 | 93.99 | -68.19 | 0.33 |  | -141.13 | -116.04 | -0.21 |  | 0 | 94
7298 | 0.47 | 39.4 | 7293.22 | 94.35 | -67.56 | 0.36 |  | -112.5 | -115.93 | -0.01 |  | 0 | 94
7391 | 0.51 | 15.21 | 7386.21 | 95.04 | -67.21 | 0.22 |  | -91.31 | -116.26 | 0.04 |  | 0 | 93
7485 | 0.1 | 200.5 | 7480.21 | 95.37 | -67.13 | 0.65 |  | -179.13 | -116.47 | -0.44 |  | 0 | 94
7578 | 0.22 | 205.9 | 7573.21 | 95.13 | -67.23 | 0.13 |  | 9.87 | -116.34 | 0.13 |  | 0 | 93
7672 | 0.43 | 285.87 | 7667.21 | 95.07 | -67.65 | 0.48 |  | 108.92 | -116.55 | 0.22 |  | 0 | 94
7765 | 0.84 | 285.93 | 7760.21 | 95.35 | -68.64 | 0.44 |  | 0.12 | -117.39 | 0.44 |  | 0 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 358.66 | 26.64 | 79.3 | 221 | 854.72 | 3975.47 | 3321.7 | 0 | 184.34 | 164.34 | 150.75 | 11023.26 | 0
Run | 358.66 | 26.64 | 79.3 | 221 | 854.72 | 3975.47 | 3321.7 | 0 | 184.34 | 164.34 | 150.75 | 11023.26 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/21/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/21/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/21/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/21/2021 | 00:00 | 00:45 | 0.75 | 3845 | 3845 | 0 | INT | 2: BHA 2 | 6L | Pick up BHA #2
06/21/2021 | 00:45 | 02:00 | 1.25 | 3845 | 3845 | 0 | INT | 2: BHA 2 | 8P | Rig service
06/21/2021 | 02:00 | 05:00 | 3 | 3845 | 3845 | 0 | INT | 2: BHA 2 | 6A | TIH
06/21/2021 | 05:00 | 08:35 | 3.58 | 3845 | 3845 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
06/21/2021 | 08:35 | 09:20 | 0.75 | 3845 | 3979 | 134 | INT | 2: BHA 2 | 2K | Rotary Drill f/3845.00 t/3979.00, w/WOB 10.00,Flow 400.00, RPM 50.00, Press 1450.00, Tq 8000.00, ROP 178.67, Diff 400.00, Temp 121.00
06/21/2021 | 09:20 | 09:25 | 0.08 | 3979 | 3979 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 09:25 | 09:40 | 0.25 | 3979 | 4073 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3979.00 t/4073.00, w/WOB 25.00,Flow 650.00, RPM 80.00, Press 3000.00, Tq 10000.00, ROP 376.00, Diff 650.00, Temp 127.00
06/21/2021 | 09:40 | 09:45 | 0.08 | 4073 | 4073 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 09:45 | 10:00 | 0.25 | 4073 | 4168 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4073.00 t/4168.00, w/WOB 25.00,Flow 650.00, RPM 80.00, Press 3000.00, Tq 10000.00, ROP 380.00, Diff 650.00, Temp 127.00
06/21/2021 | 10:00 | 10:10 | 0.17 | 4168 | 4168 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 10:10 | 10:15 | 0.08 | 4168 | 4178 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4168.00 t/4178.00, TF 150.00M, w/WOB 10.00,Flow 900.00, Press 3900.00, Tq 10000.00, ROP 120.00, Diff 500.00, Temp 133.00
06/21/2021 | 10:15 | 10:25 | 0.17 | 4178 | 4262 | 84 | INT | 2: BHA 2 | 2K | Rotary Drill f/4178.00 t/4262.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 504.00, Diff 500.00, Temp 136.00
06/21/2021 | 10:25 | 10:30 | 0.08 | 4262 | 4262 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 10:30 | 10:40 | 0.17 | 4262 | 4355 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4262.00 t/4355.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 558.00, Diff 500.00, Temp 136.00
06/21/2021 | 10:40 | 10:45 | 0.08 | 4355 | 4355 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 10:45 | 10:55 | 0.17 | 4355 | 4450 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4355.00 t/4450.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 570.00, Diff 500.00, Temp 136.00
06/21/2021 | 10:55 | 11:00 | 0.08 | 4450 | 4450 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 11:00 | 11:10 | 0.17 | 4450 | 4543 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4450.00 t/4543.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 558.00, Diff 500.00, Temp 136.00
06/21/2021 | 11:10 | 11:15 | 0.08 | 4543 | 4543 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 11:15 | 11:20 | 0.08 | 4543 | 4569 | 26 | INT | 2: BHA 2 | 2K | Rotary Drill f/4543.00 t/4569.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 312.00, Diff 500.00, Temp 136.00
06/21/2021 | 11:20 | 11:25 | 0.08 | 4569 | 4579 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4569.00 t/4579.00, TF 180.00M, w/WOB 10.00,Flow 900.00, Press 3900.00, Tq 10000.00, ROP 120.00, Diff 500.00, Temp 136.00
06/21/2021 | 11:25 | 11:35 | 0.17 | 4579 | 4637 | 58 | INT | 2: BHA 2 | 2K | Rotary Drill f/4579.00 t/4637.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 348.00, Diff 500.00, Temp 136.00
06/21/2021 | 11:35 | 11:40 | 0.08 | 4637 | 4637 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 11:40 | 11:50 | 0.17 | 4637 | 4731 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4637.00 t/4731.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 3900.00, Tq 10000.00, ROP 564.00, Diff 500.00, Temp 145.00
06/21/2021 | 11:50 | 11:55 | 0.08 | 4731 | 4731 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 11:55 | 12:10 | 0.25 | 4731 | 4825 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4731.00 t/4825.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 3200.00, Tq 10000.00, ROP 376.00, Diff 500.00, Temp 145.00
06/21/2021 | 12:10 | 12:15 | 0.08 | 4825 | 4825 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 12:15 | 12:20 | 0.08 | 4825 | 4835 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4825.00 t/4835.00, TF 180.00M, w/WOB 15.00,Flow 700.00, Press 3200.00, Tq 10000.00, ROP 120.00, Diff 500.00, Temp 145.00
06/21/2021 | 12:20 | 12:35 | 0.25 | 4835 | 4919 | 84 | INT | 2: BHA 2 | 2K | Rotary Drill f/4835.00 t/4919.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 3200.00, Tq 10000.00, ROP 336.00, Diff 500.00, Temp 145.00
06/21/2021 | 12:35 | 12:40 | 0.08 | 4919 | 4919 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 12:40 | 12:55 | 0.25 | 4919 | 5014 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4919.00 t/5014.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 3200.00, Tq 12000.00, ROP 380.00, Diff 500.00, Temp 154.00
06/21/2021 | 12:55 | 13:00 | 0.08 | 5014 | 5014 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 13:00 | 13:10 | 0.17 | 5014 | 5108 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5014.00 t/5108.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 3200.00, Tq 12000.00, ROP 564.00, Diff 500.00, Temp 154.00
06/21/2021 | 13:10 | 13:15 | 0.08 | 5108 | 5108 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 13:15 | 13:22 | 0.12 | 5108 | 5118 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5108.00 t/5118.00, TF 120.00M, w/WOB 15.00,Flow 700.00, Press 3200.00, Tq 12000.00, ROP 85.71, Diff 500.00, Temp 154.00
06/21/2021 | 13:22 | 13:40 | 0.3 | 5118 | 5202 | 84 | INT | 2: BHA 2 | 2K | Rotary Drill f/5118.00 t/5202.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 3200.00, Tq 12000.00, ROP 280.00, Diff 500.00, Temp 154.00
06/21/2021 | 13:40 | 13:45 | 0.08 | 5202 | 5202 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 13:45 | 13:55 | 0.17 | 5202 | 5299 | 97 | INT | 2: BHA 2 | 2K | Rotary Drill f/5202.00 t/5299.00, w/WOB 25.00,Flow 900, RPM 80.00, Press 4100.00, Tq 12000.00, ROP 582.00, Diff 900.00, Temp 154.00
06/21/2021 | 13:55 | 14:00 | 0.08 | 5299 | 5299 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 14:00 | 14:10 | 0.17 | 5299 | 5390 | 91 | INT | 2: BHA 2 | 2K | Rotary Drill f/5299.00 t/5390.00, w/WOB 25.00,Flow 900, RPM 80.00, Press 4100.00, Tq 12000.00, ROP 546.00, Diff 900.00, Temp 154.00
06/21/2021 | 14:10 | 14:15 | 0.08 | 5390 | 5390 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 14:15 | 14:30 | 0.25 | 5390 | 5484 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5390.00 t/5484.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4100.00, Tq 12000.00, ROP 376.00, Diff 900.00, Temp 154.00
06/21/2021 | 14:30 | 14:35 | 0.08 | 5484 | 5484 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 14:35 | 14:45 | 0.17 | 5484 | 5579 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5484.00 t/5579.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4100.00, Tq 12000.00, ROP 570.00, Diff 900.00, Temp 154.00
06/21/2021 | 14:45 | 14:50 | 0.08 | 5579 | 5579 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 14:50 | 14:58 | 0.13 | 5579 | 5589 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5579.00 t/5589.00, TF 120.00M, w/WOB 25.00,Flow 900, Press 4100.00, Tq 12000.00, ROP 75.00, Diff 900.00, Temp 154.00
06/21/2021 | 14:58 | 15:10 | 0.2 | 5589 | 5673 | 84 | INT | 2: BHA 2 | 2K | Rotary Drill f/5589.00 t/5673.00, w/WOB 35.00,Flow 900, RPM 80.00, Press 4100.00, Tq 10000.00, ROP 420.00, Diff 900.00, Temp 167.00
06/21/2021 | 15:10 | 15:50 | 0.67 | 5673 | 5673 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 15:50 | 16:05 | 0.25 | 5673 | 5766 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5673.00 t/5766.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4100.00, Tq 10000.00, ROP 372.00, Diff 900.00, Temp 171.00
06/21/2021 | 16:05 | 16:10 | 0.08 | 5766 | 5766 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 16:10 | 16:25 | 0.25 | 5766 | 5857 | 91 | INT | 2: BHA 2 | 2K | Rotary Drill f/5766.00 t/5857.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4150.00, Tq 10000.00, ROP 364.00, Diff 950.00, Temp 171.00
06/21/2021 | 16:25 | 16:30 | 0.08 | 5857 | 5857 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 16:30 | 16:50 | 0.33 | 5857 | 5950 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5857.00 t/5950.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4150.00, Tq 10000.00, ROP 279.00, Diff 950.00, Temp 172.00
06/21/2021 | 16:50 | 16:55 | 0.08 | 5950 | 5950 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 16:55 | 17:02 | 0.12 | 5950 | 5960 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5950.00 t/5960.00, TF 90.00M, w/WOB 20.00,Flow 900, Press 4150.00, Tq 10000.00, ROP 85.71, Diff 950.00, Temp 174.00
06/21/2021 | 17:02 | 17:20 | 0.3 | 5960 | 6043 | 83 | INT | 2: BHA 2 | 2K | Rotary Drill f/5960.00 t/6043.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4150.00, Tq 10000.00, ROP 276.67, Diff 950.00, Temp 172.00
06/21/2021 | 17:20 | 17:25 | 0.08 | 6043 | 6043 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 17:25 | 17:40 | 0.25 | 6043 | 6137 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6043.00 t/6137.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4150.00, Tq 10000.00, ROP 376.00, Diff 950.00, Temp 172.00
06/21/2021 | 17:40 | 17:45 | 0.08 | 6137 | 6137 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 17:45 | 17:55 | 0.17 | 6137 | 6231 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6137.00 t/6231.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4150.00, Tq 10000.00, ROP 564.00, Diff 950.00, Temp 172.00
06/21/2021 | 17:55 | 18:00 | 0.08 | 6231 | 6231 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 18:00 | 18:10 | 0.17 | 6231 | 6325 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6231.00 t/6325.00, w/WOB 30.00,Flow 900, RPM 80.00, Press 4150.00, Tq 10000.00, ROP 564.00, Diff 950.00, Temp 172.00
06/21/2021 | 18:10 | 18:15 | 0.08 | 6325 | 6325 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 18:15 | 18:25 | 0.17 | 6325 | 6345 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/6325.00 t/6345.00, TF 90.00M, w/WOB 30.00,Flow 900.00, Press 4400.00, Tq 10000.00, ROP 120.00, Diff 600.00, Temp 183.00
06/21/2021 | 18:25 | 18:35 | 0.17 | 6345 | 6419 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/6345.00 t/6419.00, w/WOB 32.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 444.00, Diff 600.00, Temp 183.00
06/21/2021 | 18:35 | 18:40 | 0.08 | 6419 | 6419 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 18:40 | 18:50 | 0.17 | 6419 | 6513 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6419.00 t/6513.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 564.00, Diff 600.00, Temp 183.00
06/21/2021 | 18:50 | 18:55 | 0.08 | 6513 | 6513 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 18:55 | 19:05 | 0.17 | 6513 | 6607 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6513.00 t/6607.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 564.00, Diff 600.00, Temp 183.00
06/21/2021 | 19:05 | 19:10 | 0.08 | 6607 | 6607 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 19:10 | 19:25 | 0.25 | 6607 | 6701 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6607.00 t/6701.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 376.00, Diff 600.00, Temp 183.00
06/21/2021 | 19:25 | 19:30 | 0.08 | 6701 | 6701 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 19:30 | 19:55 | 0.42 | 6701 | 6806 | 105 | INT | 2: BHA 2 | 2K | Rotary Drill f/6701.00 t/6806.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 252.00, Diff 600.00, Temp 183.00
06/21/2021 | 19:55 | 20:00 | 0.08 | 6806 | 6806 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 20:00 | 20:15 | 0.25 | 6806 | 6816 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/6806.00 t/6816.00, TF 160M, w/WOB 30.00,Flow 900.00, Press 4400.00, Tq 12000.00, ROP 40.00, Diff 600.00, Temp 183.00
06/21/2021 | 20:15 | 20:25 | 0.17 | 6816 | 6890 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/6816.00 t/6890.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 444.00, Diff 600.00, Temp 183.00
06/21/2021 | 20:25 | 20:30 | 0.08 | 6890 | 6890 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 20:30 | 20:40 | 0.17 | 6890 | 6984 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6890.00 t/6984.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 564.00, Diff 600.00, Temp 183.00
06/21/2021 | 20:40 | 20:45 | 0.08 | 6984 | 6984 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 20:45 | 21:00 | 0.25 | 6984 | 7079 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6984.00 t/7079.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 380.00, Diff 600.00, Temp 183.00
06/21/2021 | 21:00 | 21:05 | 0.08 | 7079 | 7079 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 21:05 | 21:15 | 0.17 | 7079 | 7173 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7079.00 t/7173.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 564.00, Diff 600.00, Temp 183.00
06/21/2021 | 21:15 | 21:20 | 0.08 | 7173 | 7173 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 21:20 | 21:30 | 0.17 | 7173 | 7268 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/7173.00 t/7268.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 570.00, Diff 600.00, Temp 183.00
06/21/2021 | 21:30 | 21:40 | 0.17 | 7268 | 7268 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 21:40 | 21:50 | 0.17 | 7268 | 7361 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7268.00 t/7361.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 558.00, Diff 600.00, Temp 183.00
06/21/2021 | 21:50 | 21:55 | 0.08 | 7361 | 7361 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 21:55 | 22:10 | 0.25 | 7361 | 7464 | 103 | INT | 2: BHA 2 | 2K | Rotary Drill f/7361.00 t/7464.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 412.00, Diff 600.00, Temp 183.00
06/21/2021 | 22:10 | 22:15 | 0.08 | 7464 | 7464 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 22:15 | 22:25 | 0.17 | 7464 | 7474 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/7464.00 t/7474.00, TF 150M, w/WOB 30.00,Flow 900.00, Press 4400.00, Tq 12000.00, ROP 60.00, Diff 600.00, Temp 189.00
06/21/2021 | 22:25 | 22:35 | 0.17 | 7474 | 7548 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/7474.00 t/7548.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 444.00, Diff 600.00, Temp 189.00
06/21/2021 | 22:35 | 22:40 | 0.08 | 7548 | 7548 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 22:40 | 23:00 | 0.33 | 7548 | 7641 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7548.00 t/7641.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 279.00, Diff 600.00, Temp 189.00
06/21/2021 | 23:00 | 23:05 | 0.08 | 7641 | 7641 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 23:05 | 23:20 | 0.25 | 7641 | 7735 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7641.00 t/7735.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 376.00, Diff 600.00, Temp 189.00
06/21/2021 | 23:20 | 23:25 | 0.08 | 7735 | 7735 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 23:25 | 23:45 | 0.33 | 7735 | 7838 | 103 | INT | 2: BHA 2 | 2K | Rotary Drill f/7735.00 t/7838.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 309.00, Diff 600.00, Temp 189.00
06/21/2021 | 23:45 | 23:50 | 0.08 | 7838 | 7838 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/21/2021 | 23:50 | 24:00 | 0.17 | 7838 | 7850 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7838.00 t/7850.00, TF M, w/WOB 30.00,Flow 900.00, Press 4400.00, Tq 12000.00, ROP 72.00, Diff 600.00, Temp 189.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_22_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/22/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 58010
|  |  |  | 24hr Summary: |  | Drilled ahead im intermediate section
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 7850 |  | 3845 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 24 | PV: | 9
End Depth (Usft): |  | 11115 |  | 11115 |  | OD (in): |  |  |  | 300: | 15 | YP: | 6
Total Drilled (Usft): |  | 3265 |  | 7270 |  | Weight (ft/lbs): |  |  |  | 200: | 11 | Viscosity: | 45
Slide Drilled (Usft): |  | 82 |  | 194 | [5 empty] | 100: | 7 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 3183 |  | 7076 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 13.75 / 0.00 |  | 24.92 / 3.58 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | .4/99.6
Slide Drilling Hrs: |  | 2.08 |  | 3.45 |  | SN: |  | 54861 |  | 10s Gel: | 4 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  | 11.67 |  | 21.47 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.0 / 124.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 272.83 / 39.36 |  | 329.63 / 56.23 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 48 |  | Grade In: |  | New
% Slide: |  | 2.51 |  | 2.67 |  | Grade Out: |  | 0-1-WT-G-X-I-CT-TD
% Rotary: |  | 97.49 |  | 97.33 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Xavier Cantu |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  |  | 8 | [5 empty] | 37.46 |  | 38.96
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 46.89
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 50.61
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 79.38
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 107.79
Crossover Sub |  |  |  | 6.5 | 3 |  |  |  |  | 2.7 |  | 110.49
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 185.82 |  | 296.31
Crossover Sub |  |  |  | 6.125 | 2.75 |  |  |  |  | 2.36 |  | 298.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 573.21
22 Stds 5 in DP |  |  |  | 5 | 4.276 |  |  |  |  | 2066.2 |  | 2639.41
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.7 |  | 2664.11
2664.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800059 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
7859 | 0.64 | 352.31 | 7854.2 | 96.06 | -69.37 | 0.88 |  | 134.86 | -118.4 | -0.21 |  | 0 | 94
7953 | 0.27 | 253.73 | 7948.2 | 96.52 | -69.66 | 0.78 |  | -158.57 | -118.93 | -0.39 |  | 0 | 94
8046 | 0.8 | 248.35 | 8041.19 | 96.22 | -70.47 | 0.57 |  | -8.11 | -119.2 | 0.57 |  | 0 | 93
8140 | 0.57 | 143.35 | 8135.19 | 95.6 | -70.8 | 1.17 |  | -149.84 | -118.92 | -0.24 |  | 0 | 94
8234 | 0.9 | 124.35 | 8229.18 | 94.81 | -69.91 | 0.43 |  | -46.2 | -117.74 | 0.35 |  | 0 | 94
8328 | 0.66 | 123.77 | 8323.17 | 94.09 | -68.85 | 0.26 |  | -178.41 | -116.53 | -0.26 |  | 0 | 94
8422 | 0.59 | 126.94 | 8417.17 | 93.5 | -68.02 | 0.08 |  | 155.29 | -115.54 | -0.07 |  | 0 | 94
8516 | 0.61 | 94.17 | 8511.16 | 93.17 | -67.13 | 0.36 |  | -103.14 | -114.74 | 0.02 |  | 0 | 94
8610 | 0.56 | 85.61 | 8605.16 | 93.17 | -66.17 | 0.11 |  | -124.01 | -114.15 | -0.05 |  | 0 | 94
8704 | 0.57 | 56.41 | 8699.15 | 93.46 | -65.33 | 0.3 |  | -102.65 | -113.85 | 0.01 |  | 0 | 94
8798 | 0.62 | 17.7 | 8793.15 | 94.21 | -64.78 | 0.42 |  | -102.53 | -114.1 | 0.05 |  | 0 | 94
8892 | 0.65 | 355.67 | 8887.14 | 95.22 | -64.67 | 0.26 |  | -94.09 | -114.83 | 0.03 |  | 0 | 94
8986 | 0.85 | 346.54 | 8981.13 | 96.43 | -64.87 | 0.25 |  | -35.48 | -115.91 | 0.21 |  | 0 | 94
9080 | 1.07 | 341.32 | 9075.12 | 97.94 | -65.31 | 0.25 |  | -24.3 | -117.37 | 0.23 |  | 0 | 94
9174 | 1.33 | 335.34 | 9169.1 | 99.76 | -66.05 | 0.31 |  | -28.73 | -119.26 | 0.28 |  | 0 | 94
9268 | 1.66 | 329.64 | 9263.07 | 101.93 | -67.19 | 0.38 |  | -27.13 | -121.67 | 0.35 |  | 0 | 94
9361 | 2.01 | 325.88 | 9356.02 | 104.44 | -68.79 | 0.4 |  | -20.87 | -124.63 | 0.38 |  | -4.04 | 93
9455 | 1.61 | 300.71 | 9449.97 | 106.48 | -70.85 | 0.94 |  | -128.92 | -127.51 | -0.43 |  | -26.78 | 94
9549 | 0.68 | 301.23 | 9543.95 | 107.45 | -72.46 | 0.99 |  | 179.62 | -129.26 | -0.99 |  | 0.55 | 94
9643 | 0.79 | 8.2 | 9637.95 | 108.38 | -72.85 | 0.87 |  | 117.03 | -130.23 | 0.12 |  | 0 | 94
9738 | 1.29 | 6.27 | 9732.93 | 110.09 | -72.64 | 0.53 |  | -4.97 | -131.45 | 0.53 |  | 0 | 95
9831 | 1.49 | 353.25 | 9825.9 | 112.33 | -72.66 | 0.4 |  | -64.28 | -133.23 | 0.22 |  | 0 | 93
9925 | 1.84 | 344.04 | 9919.87 | 114.99 | -73.22 | 0.47 |  | -42.06 | -135.67 | 0.37 |  | 0 | 94
10018 | 1.11 | 340.64 | 10012.83 | 117.28 | -73.93 | 0.79 |  | -174.86 | -137.9 | -0.78 |  | -3.66 | 93
10112 | 0.95 | 327.46 | 10106.82 | 118.8 | -74.65 | 0.3 |  | -130.5 | -139.54 | -0.17 |  | 0 | 94
10205 | 1.32 | 326.51 | 10199.8 | 120.34 | -75.66 | 0.4 |  | -3.39 | -141.37 | 0.4 |  | 0 | 93
10300 | 0.38 | 315.03 | 10294.79 | 121.47 | -76.48 | 1 |  | -175.44 | -142.78 | -0.99 |  | 0 | 95
10394 | 0.28 | 340.05 | 10388.79 | 121.91 | -76.78 | 0.18 |  | 136.84 | -143.31 | -0.11 |  | 0 | 94
10488 | 1.15 | 356.28 | 10482.78 | 123.07 | -76.92 | 0.94 |  | 21.3 | -144.3 | 0.93 |  | 0 | 94
10582 | 0.57 | 50.24 | 10576.77 | 124.31 | -76.62 | 1 |  | 150.5 | -145.09 | -0.62 |  | 0 | 94
10675 | 0.82 | 134.06 | 10669.76 | 124.14 | -75.79 | 1.02 |  | 120.58 | -144.45 | 0.27 |  | 0 | 93
10770 | 0.62 | 162.14 | 10764.76 | 123.18 | -75.14 | 0.42 |  | 133.09 | -143.29 | -0.21 |  | 0 | 95
10863 | 0.71 | 210.73 | 10857.75 | 122.2 | -75.28 | 0.59 |  | 105.77 | -142.61 | 0.1 |  | 0 | 93
10957 | 1.41 | 232.76 | 10951.74 | 121 | -76.5 | 0.85 |  | 41.53 | -142.42 | 0.74 |  | 0 | 94
11052 | 1.9 | 245.75 | 11046.7 | 119.65 | -78.87 | 0.65 |  | 44.05 | -142.82 | 0.52 |  | 0 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 230.55 | 25.85 | 80 | 216 | 820.98 | 5009.76 | 4414.63 | 0 | 257.07 | 235.49 | 209.02 | 14171.43 | 0
Run | 287.96 | 26.3 | 79.62 | 219 | 840 | 4426.6 | 3798.4 | 0 | 216.06 | 195.37 | 176.17 | 12435.9 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/22/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/22/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/22/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/22/2021 | 00:00 | 00:20 | 0.33 | 7850 | 7940 | 90 | INT | 2: BHA 2 | 2K | Rotary Drill f/7850.00 t/7940.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 270.00, Diff 600.00, Temp 189.00
06/22/2021 | 00:20 | 01:30 | 1.17 | 7940 | 7940 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 01:30 | 01:50 | 0.33 | 7940 | 7952 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7940.00 t/7952.00, TF 150M, w/WOB 30.00,Flow 900.00, Press 4400.00, Tq 12000.00, ROP 36.00, Diff 600.00, Temp 189.00
06/22/2021 | 01:50 | 02:05 | 0.25 | 7952 | 8016 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/7952.00 t/8016.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 256.00, Diff 600.00, Temp 189.00
06/22/2021 | 02:05 | 02:10 | 0.08 | 8016 | 8016 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 02:10 | 02:30 | 0.33 | 8016 | 8120 | 104 | INT | 2: BHA 2 | 2K | Rotary Drill f/8016.00 t/8120.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4400.00, Tq 12000.00, ROP 312.00, Diff 600.00, Temp 189.00
06/22/2021 | 02:30 | 02:35 | 0.08 | 8120 | 8120 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 02:35 | 02:55 | 0.33 | 8120 | 8135 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8120.00 t/8135.00, TF 120M, w/WOB 30.00,Flow 900.00, Press 4800, Tq 14000, ROP 45.00, Diff 600.00, Temp 192.00
06/22/2021 | 02:55 | 03:10 | 0.25 | 8135 | 8203 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/8135.00 t/8203.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800, Tq 14000, ROP 272.00, Diff 600.00, Temp 192.00
06/22/2021 | 03:10 | 03:15 | 0.08 | 8203 | 8203 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 03:15 | 03:40 | 0.42 | 8203 | 8297 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8203.00 t/8297.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800, Tq 14000, ROP 225.60, Diff 600.00, Temp 192.00
06/22/2021 | 03:40 | 04:10 | 0.5 | 8297 | 8297 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 04:10 | 04:30 | 0.33 | 8297 | 8391 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8297.00 t/8391.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800, Tq 14000, ROP 282.00, Diff 600.00, Temp 192.00
06/22/2021 | 04:30 | 04:35 | 0.08 | 8391 | 8391 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 04:35 | 04:55 | 0.33 | 8391 | 8485 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8391.00 t/8485.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800, Tq 14000, ROP 282.00, Diff 600.00, Temp 192.00
06/22/2021 | 04:55 | 05:00 | 0.08 | 8485 | 8485 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 05:00 | 05:20 | 0.33 | 8485 | 8579 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8485.00 t/8579.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800, Tq 14000, ROP 282.00, Diff 600.00, Temp 192.00
06/22/2021 | 05:20 | 05:25 | 0.08 | 8579 | 8579 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 05:25 | 05:45 | 0.33 | 8579 | 8673 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8579.00 t/8673.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 14000.00, ROP 282.00, Diff 600.00, Temp 192.00
06/22/2021 | 05:45 | 05:50 | 0.08 | 8673 | 8673 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 05:50 | 06:20 | 0.5 | 8673 | 8767 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8673.00 t/8767.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 14000.00, ROP 188.00, Diff 600.00, Temp 198.00
06/22/2021 | 06:20 | 06:25 | 0.08 | 8767 | 8767 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 06:25 | 06:45 | 0.33 | 8767 | 8861 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8767.00 t/8861.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 14000.00, ROP 282.00, Diff 600.00, Temp 198.00
06/22/2021 | 06:45 | 08:45 | 2 | 8861 | 8861 | 0 | INT | 2: BHA 2 | 8A | Work on TD
06/22/2021 | 08:45 | 09:15 | 0.5 | 8861 | 8955 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8861.00 t/8955.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 14000.00, ROP 188.00, Diff 600.00, Temp 198.00
06/22/2021 | 09:15 | 09:20 | 0.08 | 8955 | 8955 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 09:20 | 09:35 | 0.25 | 8955 | 9009 | 54 | INT | 2: BHA 2 | 2K | Rotary Drill f/8955.00 t/9009.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 216.00, Diff 500.00, Temp 198.00
06/22/2021 | 09:35 | 13:25 | 3.83 | 9009 | 9009 | 0 | INT | 2: BHA 2 | 8D | Work on MP
06/22/2021 | 13:25 | 13:40 | 0.25 | 9009 | 9049 | 40 | INT | 2: BHA 2 | 2K | Rotary Drill f/9009.00 t/9049.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 160.00, Diff 500.00, Temp 185.00
06/22/2021 | 13:40 | 13:45 | 0.08 | 9049 | 9049 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 13:45 | 14:10 | 0.42 | 9049 | 9143 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9049.00 t/9143.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 225.60, Diff 500.00, Temp 185.00
06/22/2021 | 14:10 | 14:15 | 0.08 | 9143 | 9143 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 14:15 | 14:35 | 0.33 | 9143 | 9237 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9143.00 t/9237.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 282.00, Diff 500.00, Temp 192.00
06/22/2021 | 14:35 | 14:40 | 0.08 | 9237 | 9237 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 14:40 | 15:00 | 0.33 | 9237 | 9331 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9237.00 t/9331.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 282.00, Diff 500.00, Temp 198.00
06/22/2021 | 15:00 | 15:05 | 0.08 | 9331 | 9331 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 15:05 | 15:25 | 0.33 | 9331 | 9424 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9331.00 t/9424.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 279.00, Diff 500.00, Temp 198.00
06/22/2021 | 15:25 | 15:30 | 0.08 | 9424 | 9424 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 15:30 | 15:40 | 0.17 | 9424 | 9434 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/9424.00 t/9434.00, TF 150.00M, w/WOB 20.00,Flow 700.00, Press 4100.00, Tq 14000.00, ROP 60.00, Diff 500.00, Temp 198.00
06/22/2021 | 15:40 | 16:00 | 0.33 | 9434 | 9518 | 84 | INT | 2: BHA 2 | 2K | Rotary Drill f/9434.00 t/9518.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 252.00, Diff 500.00, Temp 205.00
06/22/2021 | 16:00 | 16:05 | 0.08 | 9518 | 9518 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 16:05 | 16:25 | 0.33 | 9518 | 9612 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9518.00 t/9612.00, w/WOB 25.00,Flow 700.00, RPM 80.00, Press 4100.00, Tq 14000.00, ROP 282.00, Diff 500.00, Temp 205.00
06/22/2021 | 16:25 | 16:40 | 0.25 | 9612 | 9612 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 16:40 | 17:00 | 0.33 | 9612 | 9706 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9612.00 t/9706.00, w/WOB 25.00,Flow 820, RPM 80.00, Press 5600, Tq 14000.00, ROP 282.00, Diff 600.00, Temp 205.00
06/22/2021 | 17:00 | 17:05 | 0.08 | 9706 | 9706 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 17:05 | 17:25 | 0.33 | 9706 | 9801 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/9706.00 t/9801.00, w/WOB 25.00,Flow 820, RPM 80.00, Press 5600, Tq 14000.00, ROP 285.00, Diff 600.00, Temp 210.00
06/22/2021 | 17:25 | 17:30 | 0.08 | 9801 | 9801 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 17:30 | 18:20 | 0.83 | 9801 | 10000 | 199 | INT | 2: BHA 2 | 2K | Rotary Drill f/9801.00 t/10000.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 238.80, Diff 600.00, Temp 210.00
06/22/2021 | 18:20 | 18:25 | 0.08 | 10000 | 10000 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 18:25 | 18:45 | 0.33 | 10000 | 10015 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/10000.00 t/10015.00, TF 150M, w/WOB 25.00,Flow 820.00, Press 5600.00, Tq 14000.00, ROP 45.00, Diff 600.00, Temp 210.00
06/22/2021 | 18:45 | 19:05 | 0.33 | 10015 | 10081 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/10015.00 t/10081.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 198.00, Diff 600.00, Temp 210.00
06/22/2021 | 19:05 | 19:10 | 0.08 | 10081 | 10081 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 19:10 | 19:30 | 0.33 | 10081 | 10175 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10081.00 t/10175.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 282.00, Diff 600.00, Temp 210.00
06/22/2021 | 19:30 | 19:35 | 0.08 | 10175 | 10175 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 19:35 | 20:00 | 0.42 | 10175 | 10283 | 108 | INT | 2: BHA 2 | 2K | Rotary Drill f/10175.00 t/10283.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 259.20, Diff 600.00, Temp 210.00
06/22/2021 | 20:00 | 20:05 | 0.08 | 10283 | 10283 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 20:05 | 20:35 | 0.5 | 10283 | 10298 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/10283.00 t/10298.00, TF 150M, w/WOB 25.00,Flow 820.00, Press 5600.00, Tq 14000.00, ROP 30.00, Diff 600.00, Temp 210.00
06/22/2021 | 20:35 | 20:50 | 0.25 | 10298 | 10363 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/10298.00 t/10363.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 260.00, Diff 600.00, Temp 210.00
06/22/2021 | 20:50 | 20:55 | 0.08 | 10363 | 10363 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 20:55 | 21:10 | 0.25 | 10363 | 10457 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10363.00 t/10457.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 376.00, Diff 600.00, Temp 210.00
06/22/2021 | 21:10 | 21:15 | 0.08 | 10457 | 10457 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 21:15 | 21:40 | 0.42 | 10457 | 10570 | 113 | INT | 2: BHA 2 | 2K | Rotary Drill f/10457.00 t/10570.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 271.20, Diff 600.00, Temp 210.00
06/22/2021 | 21:40 | 21:45 | 0.08 | 10570 | 10570 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 21:45 | 22:10 | 0.42 | 10570 | 10585 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/10570.00 t/10585.00, TF 160M, w/WOB 25.00,Flow 820.00, Press 5600.00, Tq 14000.00, ROP 36.00, Diff 600.00, Temp 210.00
06/22/2021 | 22:10 | 22:20 | 0.17 | 10585 | 10645 | 60 | INT | 2: BHA 2 | 2K | Rotary Drill f/10585.00 t/10645.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5600.00, Tq 14000.00, ROP 360.00, Diff 600.00, Temp 210.00
06/22/2021 | 22:20 | 22:25 | 0.08 | 10645 | 10645 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 22:25 | 22:40 | 0.25 | 10645 | 10738 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/10645.00 t/10738.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900, Tq 16000, ROP 372.00, Diff 700.00, Temp 241.00
06/22/2021 | 22:40 | 22:45 | 0.08 | 10738 | 10738 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 22:45 | 23:00 | 0.25 | 10738 | 10833 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/10738.00 t/10833.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900, Tq 16000, ROP 380.00, Diff 700.00, Temp 241.00
06/22/2021 | 23:00 | 23:05 | 0.08 | 10833 | 10833 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 23:05 | 23:20 | 0.25 | 10833 | 10926 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/10833.00 t/10926.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900, Tq 16000, ROP 372.00, Diff 700.00, Temp 241.00
06/22/2021 | 23:20 | 23:25 | 0.08 | 10926 | 10926 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 23:25 | 23:40 | 0.25 | 10926 | 11020 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10926.00 t/11020.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900, Tq 16000, ROP 376.00, Diff 700.00, Temp 241.00
06/22/2021 | 23:40 | 23:45 | 0.08 | 11020 | 11020 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/22/2021 | 23:45 | 23:55 | 0.17 | 11020 | 11115 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/11020.00 t/11020.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900, Tq 16000, ROP 0.00, Diff 700.00, Temp 241.00
06/22/2021 | 23:55 | 24:00 | 0.08 | 11115 | 11115 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_23_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/23/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 64860
|  |  |  | 24hr Summary: |  | Drilled ahead in intermediate section
|  |  |  | 24hr Lookahead: |  | Begin building curve
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11115 |  | 3845 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 24 | PV: | 9
End Depth (Usft): |  | 12250 |  | 12250 |  | OD (in): |  |  |  | 300: | 15 | YP: | 6
Total Drilled (Usft): |  | 1135 |  | 8405 |  | Weight (ft/lbs): |  |  |  | 200: | 11 | Viscosity: | 45
Slide Drilled (Usft): |  | 386 |  | 580 | [5 empty] | 100: | 7 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 749 |  | 7825 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  | 19.08 / 1.75 |  | 44.00 / 5.33 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | .4/99.6
Slide Drilling Hrs: |  | 15.58 |  | 19.03 |  | SN: |  | 54861 |  | 10s Gel: | 4 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  | 3.5 |  | 24.97 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.0 / 124.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 214.00 / 24.77 |  | 313.42 / 30.47 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 72 |  | Grade In: |  | New
% Slide: |  | 34.01 |  | 6.9 |  | Grade Out: |  | 0-1-WT-G-X-I-CT-TD
% Rotary: |  | 65.99 |  | 93.1 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Jesse Taylor Josh Ray |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Trey
Kevin |  | Xavier Cantu |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  |  | 8 | [5 empty] | 37.46 |  | 38.96
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 46.89
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 50.61
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 79.38
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 107.79
Crossover Sub |  |  |  | 6.5 | 3 |  |  |  |  | 2.7 |  | 110.49
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 185.82 |  | 296.31
Crossover Sub |  |  |  | 6.125 | 2.75 |  |  |  |  | 2.36 |  | 298.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 573.21
22 Stds 5 in DP |  |  |  | 5 | 4.276 |  |  |  |  | 2066.2 |  | 2639.41
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.7 |  | 2664.11
2664.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800059 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11145 | 2.22 | 258.66 | 11139.64 | 118.66 | -82.04 | 0.6 |  | 61.98 | -144 | 0.34 |  | 13.88 | 93
11239 | 1.24 | 229.24 | 11233.59 | 117.64 | -84.6 | 1.37 |  | -151.88 | -144.77 | -1.04 |  | -31.3 | 94
11334 | 1.43 | 216.8 | 11328.57 | 116.02 | -86.09 | 0.36 |  | -63.07 | -144.42 | 0.2 |  | 0 | 95
11427 | 2.01 | 227.04 | 11421.53 | 113.98 | -87.97 | 0.7 |  | 33.1 | -143.98 | 0.62 |  | 0 | 93
11522 | 2.13 | 233.72 | 11516.46 | 111.8 | -90.62 | 0.28 |  | 66.92 | -143.89 | 0.13 |  | 7.03 | 95
11616 | 1.49 | 252.88 | 11610.42 | 110.41 | -93.19 | 0.93 |  | 145.91 | -144.39 | -0.68 |  | 20.38 | 94
11709 | 1.65 | 267.6 | 11703.38 | 109.99 | -95.69 | 0.46 |  | 75.83 | -145.6 | 0.17 |  | 0 | 93
11802 | 1.04 | 265.94 | 11796.36 | 109.88 | -97.87 | 0.66 |  | -177.17 | -146.86 | -0.66 |  | -1.78 | 93
11896 | 0.96 | 281.31 | 11890.34 | 109.97 | -99.49 | 0.3 |  | 114.2 | -147.93 | -0.09 |  | 0 | 94
11989 | 2.07 | 268.94 | 11983.31 | 110.09 | -101.93 | 1.24 |  | -22.66 | -149.54 | 1.19 |  | 0 | 93
12083 | 2.84 | 156.97 | 12077.26 | 107.92 | -102.72 | 4.35 |  | -139.92 | -148.31 | 0.82 |  | -119.12 | 94
12183 | 10.33 | 134.78 | 12176.54 | 99.31 | -95.37 | 7.77 |  | -30.05 | -137.01 | 7.49 |  | -22.19 | 100
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 59.48 | 25 | 80 | 216 | 820 | 5766.67 | 5200 | 0 | 303.61 | 284.72 | 261.67 | 14000 | 0
Run | 191.02 | 26.09 | 79.65 | 219 | 836.79 | 4641.96 | 4023.66 | 0 | 230.13 | 209.73 | 189.91 | 12581.4 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/23/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/23/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/23/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/23/2021 | 00:00 | 00:15 | 0.25 | 11115 | 11220 | 105 | INT | 2: BHA 2 | 2K | Rotary Drill f/11115.00 t/11220.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 420.00, Diff 700.00, Temp 241.00
06/23/2021 | 00:15 | 00:20 | 0.08 | 11220 | 11220 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 00:20 | 00:50 | 0.5 | 11220 | 11238 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/11220.00 t/11238.00, TF 120M, w/WOB 25.00,Flow 820.00, Press 5900.00, Tq 14000.00, ROP 36.00, Diff 700.00, Temp 248.00
06/23/2021 | 00:50 | 01:05 | 0.25 | 11238 | 11302 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/11238.00 t/11302.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 256.00, Diff 700.00, Temp 248.00
06/23/2021 | 01:05 | 01:10 | 0.08 | 11302 | 11302 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 01:10 | 01:25 | 0.25 | 11302 | 11397 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/11302.00 t/11397.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 380.00, Diff 700.00, Temp 248.00
06/23/2021 | 01:25 | 01:30 | 0.08 | 11397 | 11397 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 01:30 | 02:00 | 0.5 | 11397 | 11490 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/11397.00 t/11490.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 186.00, Diff 700.00, Temp 248.00
06/23/2021 | 02:00 | 02:05 | 0.08 | 11490 | 11490 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 02:05 | 02:35 | 0.5 | 11490 | 11598 | 108 | INT | 2: BHA 2 | 2K | Rotary Drill f/11490.00 t/11598.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 216.00, Diff 700.00, Temp 241.00
06/23/2021 | 02:35 | 02:40 | 0.08 | 11598 | 11598 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 02:40 | 03:25 | 0.75 | 11598 | 11616 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/11598.00 t/11616.00, TF M, w/WOB 25.00,Flow 820.00, Press 5900.00, Tq 14000.00, ROP 24.00, Diff 700.00, Temp 241.00
06/23/2021 | 03:25 | 03:50 | 0.42 | 11616 | 11679 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/11616.00 t/11679.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 151.20, Diff 700.00, Temp 241.00
06/23/2021 | 03:50 | 03:55 | 0.08 | 11679 | 11679 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 03:55 | 04:20 | 0.42 | 11679 | 11785 | 106 | INT | 2: BHA 2 | 2K | Rotary Drill f/11679.00 t/11785.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 254.40, Diff 700.00, Temp 241.00
06/23/2021 | 04:20 | 04:25 | 0.08 | 11785 | 11785 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 04:25 | 05:00 | 0.58 | 11785 | 11802 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/11785.00 t/11802.00, TF M, w/WOB 25.00,Flow 820.00, Press 5900.00, Tq 14000.00, ROP 29.14, Diff 700.00, Temp 241.00
06/23/2021 | 05:00 | 05:50 | 0.83 | 11802 | 11913 | 111 | INT | 2: BHA 2 | 2K | Rotary Drill f/11802.00 t/11913.00, w/WOB 25.00,Flow 820.00, RPM 80.00, Press 5900.00, Tq 14000.00, ROP 133.20, Diff 700.00, Temp 241.00
06/23/2021 | 05:50 | 07:15 | 1.42 | 11913 | 11959 | 46 | CRV | 2: BHA 2 | 2J | Slide Drill f/11913.00 t/11959.00, TF 140.00M, w/WOB 25.00,Flow 820.00, Press 5900.00, Tq 0.00, ROP 32.47, Diff 700.00, Temp 250.00
06/23/2021 | 07:15 | 07:20 | 0.08 | 11959 | 11959 | 0 | CRV | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 07:20 | 10:40 | 3.33 | 11959 | 12052 | 93 | CRV | 2: BHA 2 | 2J | Slide Drill f/11959.00 t/12052.00, TF 130.00M, w/WOB 25.00,Flow 820.00, Press 5500.00, Tq 0.00, ROP 27.90, Diff 300.00, Temp 250.00
06/23/2021 | 10:40 | 10:45 | 0.08 | 12052 | 12052 | 0 | CRV | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 10:45 | 14:35 | 3.83 | 12052 | 12146 | 94 | CRV | 2: BHA 2 | 2J | Slide Drill f/12052.00 t/12146.00, TF 130.00M, w/WOB 25.00,Flow 820.00, Press 5500.00, Tq 0.00, ROP 24.52, Diff 300.00, Temp 250.00
06/23/2021 | 14:35 | 14:40 | 0.08 | 12146 | 12146 | 0 | CRV | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 14:40 | 17:45 | 3.08 | 12146 | 12210 | 64 | CRV | 2: BHA 2 | 2J | Slide Drill f/12146.00 t/12210.00, TF 140.00M, w/WOB 25.00,Flow 820.00, Press 5500.00, Tq 0.00, ROP 20.76, Diff 300.00, Temp 250.00
06/23/2021 | 17:45 | 17:50 | 0.08 | 12210 | 12210 | 0 | CRV | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 17:50 | 19:20 | 1.5 | 12210 | 12240 | 30 | CRV | 2: BHA 2 | 2J | Slide Drill f/12210.00 t/12240.00, TF 20G, w/WOB 25.00,Flow 820.00, Press 5500.00, Tq 0.00, ROP 20.00, Diff 300.00, Temp 250.00
06/23/2021 | 19:20 | 19:25 | 0.08 | 12240 | 12240 | 0 | CRV | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 19:25 | 20:00 | 0.58 | 12240 | 12246 | 6 | CRV | 2: BHA 2 | 2J | Slide Drill f/12240.00 t/12246.00, TF 20G, w/WOB 25.00,Flow 820.00, Press 5500.00, Tq 0.00, ROP 10.29, Diff 300.00, Temp 250.00
06/23/2021 | 20:00 | 20:30 | 0.5 | 12246 | 12246 | 0 | CRV | 2: BHA 2 | 10D | Survey & Connection
06/23/2021 | 20:30 | 20:35 | 0.08 | 12246 | 12250 | 4 | CRV | 2: BHA 2 | 2K | Rotary Drill f/12246.00 t/12250.00, w/WOB 25.00,Flow 820.00, RPM 0.00, Press 5500.00, Tq 0.00, ROP 48.00, Diff 300.00, Temp 250.00
06/23/2021 | 20:35 | 22:20 | 1.75 | 12250 | 12250 | 0 | CRV | 2: BHA 2 | 5A | Circ to lay down pipe and run casing
06/23/2021 | 22:20 | 24:00 | 1.67 | 12250 | 12250 | 0 | CRV | 2: BHA 2 | 6B | Lay down drill pipe
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_24_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/24/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 71710
|  |  |  | 24hr Summary: |  | Started curve & got into chaulk, LD drill pipe, Lay down tools, run casing
|  |  |  | 24hr Lookahead: |  | Standby for casing ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12250 |  | 3845 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 24 | PV: | 9
End Depth (Usft): |  | 12250 |  | 12250 |  | OD (in): |  |  |  | 300: | 15 | YP: | 6
Total Drilled (Usft): |  |  |  | 8405 |  | Weight (ft/lbs): |  |  |  | 200: | 11 | Viscosity: | 45
Slide Drilled (Usft): |  |  |  | 580 | [5 empty] | 100: | 7 | Chlorides: | 58000
Rotary Drilled (Usft): |  |  |  | 7825 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: |  |  |  | 44.00 / 5.33 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | .4/99.6
Slide Drilling Hrs: |  |  |  | 19.03 |  | SN: |  | 54861 |  | 10s Gel: | 4 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  |  |  | 24.97 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.0 / 124.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 313.42 / 30.47 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 18 |  | 90 |  | Grade In: |  | New
% Slide: |  |  |  | 6.9 |  | Grade Out: |  | 0-1-WT-G-X-I-CT-TD
% Rotary: |  |  |  | 93.1 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Trey
Kevin |  | Xavier Cantu |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  |  | 8 | [5 empty] | 37.46 |  | 38.96
Pony Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 7.93 |  | 46.89
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 3.72 |  | 50.61
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.77 |  | 79.38
Drill Collar (NO HARDBANDING) |  |  |  | 8 | 3.375 |  |  |  |  | 28.41 |  | 107.79
Crossover Sub |  |  |  | 6.5 | 3 |  |  |  |  | 2.7 |  | 110.49
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 185.82 |  | 296.31
Crossover Sub |  |  |  | 6.125 | 2.75 |  |  |  |  | 2.36 |  | 298.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  |  |  | 274.54 |  | 573.21
22 Stds 5 in DP |  |  |  | 5 | 4.276 |  |  |  |  | 2066.2 |  | 2639.41
Agitator |  |  |  | 6.75 | 3.75 |  |  |  |  | 24.7 |  | 2664.11
2664.11
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800059 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 191.02 | 26.09 | 79.65 | 219 | 836.79 | 4641.96 | 4023.66 | 0 | 230.13 | 209.73 | 189.91 | 12581.4 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/24/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/24/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/24/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/24/2021 | 00:00 | 16:45 | 16.75 | 12250 | 12250 | 0 | CRV | 2: BHA 2 | 6K | Lay down drill pipe
06/24/2021 | 16:45 | 18:00 | 1.25 | 12250 | 12250 | 0 | CRV | 2: BHA 2 | 6P | L/D BHA #2
06/24/2021 | 18:00 | 24:00 | 6 | 12250 | 12250 | 0 | CRV |  | 24B | Standby for Casing ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_25_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/25/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4200 |  |  | Well Cost($): |  | 75910
|  |  |  | 24hr Summary: |  | Finish Running casing, Cement
|  |  |  | 24hr Lookahead: |  | Finish running casing & cement
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12250 |  |  |  | Csg Shoe MD(Usft): |  | 4160 |  | 600: | 24 | PV: | 9
End Depth (Usft): |  | 12250 |  | 12250 |  | OD (in): |  | 10.75 |  | 300: | 15 | YP: | 6
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45.5 |  | 200: | 11 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 7 | Chlorides: | 58000
Rotary Drilled (Usft): | [9 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 5.70
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 3 | Oil/Water: | .4/99.6
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 4 | Weight (ppg): | 8.8
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 7.0 / 124.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burk |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Trey
Kevin |  | Xavier Cantu |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 06/25/2021 |  | 5 |  | 100 |  | 4 | 400
STBY |  |  |  |  | 06/25/2021 |  | 2 |  | 3800 |  | 1 | 3800
Total | [11 empty] | 4200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/25/2021 | 00:00 | 12:00 | 12 | 12250 | 12250 | 0 | CRV |  | 24B | Stand by for casing ops
06/25/2021 | 12:00 | 18:00 | 6 | 12250 | 12250 | 0 | CRV |  | 24B | Stand by for cementing ops
06/25/2021 | 18:00 | 20:00 | 2 | 12250 | 12250 | 0 | CRV |  | 24B | Prep rig floor
06/25/2021 | 20:00 | 24:00 | 4 | 12250 | 12250 | 0 | CRV |  | 24B | Change pipe rams
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_26_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/26/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17850 |  |  | Well Cost($): |  | 93760
|  |  |  | 24hr Summary: |  | P/U BHA #3, P/U Drill pipe
|  |  |  | 24hr Lookahead: |  | P/U Drill pipe, Drill out, Fit Test, Drill curve
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12250 |  | 12250 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 42 | PV: | 16
End Depth (Usft): |  | 12250 |  | 12250 |  | OD (in): |  | 7.625 |  | 300: | 26 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 29.7 |  | 200: | 19 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 62000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 14.00
Drlg/Circ Hrs: |  | 0.00 / 0.17 |  | 0.00 / 0.17 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: | [5 empty] | SN: |  | 13601236 |  | 10s Gel: | 6 | Weight (ppg): | 11
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 7.0 / 110.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 12.42 |  | 12.42 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-WT-A-X-I-NO-BHA
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.003 |  |  |  | 5.5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.03 |  | 35.91
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.18
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.17
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.22
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.76
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.33
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.35
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.73
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.39
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.84
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.83
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.77 |  | 2821.6
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5930.04
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.98
5951.98
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.05 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/26/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/26/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/26/2021 |  | 20 |  | -400 |  | 1 | -400
5.5 Premium Motor Reline |  |  |  |  | 06/26/2021 |  | 9 |  | 9000 |  | 1 | 9000
Pro Azimuthal Gamma Ray |  |  |  |  | 06/26/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 17850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/26/2021 | 00:00 | 10:10 | 10.17 | 12250 | 12250 | 0 | CRV2 |  | 24B | Test BOPs
06/26/2021 | 10:10 | 11:35 | 1.42 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 6O | P/U BHA #3
06/26/2021 | 11:35 | 11:45 | 0.17 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 5A | Test Motor and MWD
06/26/2021 | 11:45 | 12:35 | 0.83 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 6L | Continue P/U BHA #3
06/26/2021 | 12:35 | 24:00 | 11.42 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 6J | Pick up Drill Pipe
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_27_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/27/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 103210
|  |  |  | 24hr Summary: |  | Pick up drill pipe
|  |  |  | 24hr Lookahead: |  | Cut drill line, continue curve
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12250 |  | 12250 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 42 | PV: | 16
End Depth (Usft): |  | 13010 |  | 13010 |  | OD (in): |  | 7.625 |  | 300: | 26 | YP: | 10
Total Drilled (Usft): |  | 760 |  | 760 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 19 | Viscosity: | 45
Slide Drilled (Usft): |  | 599 |  | 599 | [5 empty] | 100: | 12 | Chlorides: | 62000
Rotary Drilled (Usft): |  | 161 |  | 161 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 14.00
Drlg/Circ Hrs: |  | 11.25 / 4.83 |  | 11.25 / 5.00 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 70/30
Slide Drilling Hrs: |  | 8.83 |  | 8.83 |  | SN: |  | 13601236 |  | 10s Gel: | 6 | Weight (ppg): | 11
Rotary Drilling Hrs: |  | 2.42 |  | 2.42 |  | Bit # |  | 3 |  | PH / Temp(F) | 7.0 / 110.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 66.62 / 67.81 |  | 66.62 / 67.81 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 36.42 |  | Grade In: |  | New
% Slide: |  | 78.82 |  | 78.82 |  | Grade Out: |  | 0-1-WT-A-X-I-NO-BHA
% Rotary: |  | 21.18 |  | 21.18 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.003 |  |  |  | 5.5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.03 |  | 35.91
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.18
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.17
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.22
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.76
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.33
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.35
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.73
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.39
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.84
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.83
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.77 |  | 2821.6
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5930.04
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.98
5951.98
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.05 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12183 | 10.33 | 134.78 | 12176.54 | 99.31 | -95.37 | 7.77 |  | -30.05 | -137.01 | 7.49 |  | -22.19 | 100
12308 | 18.38 | 139.86 | 12297.54 | 76.31 | -74.68 | 6.51 |  | 11.37 | -106.14 | 6.44 |  | 4.06 | 125
12403 | 26.28 | 146.12 | 12385.36 | 47.35 | -53.26 | 8.67 |  | 19.69 | -70.13 | 8.32 |  | 6.59 | 95
12498 | 34.6 | 146.72 | 12467.2 | 7.27 | -26.69 | 8.76 |  | 2.35 | -22.2 | 8.76 |  | 0.63 | 95
12592 | 42.06 | 144.87 | 12540.88 | -40.86 | 6.12 | 8.03 |  | -9.48 | 35.92 | 7.94 |  | -1.97 | 94
12688 | 51.93 | 141.23 | 12606.29 | -96.77 | 48.4 | 10.65 |  | -16.36 | 106 | 10.28 |  | -3.79 | 96
12783 | 57.88 | 141.86 | 12660.89 | -157.62 | 96.7 | 6.29 |  | 5.13 | 183.69 | 6.26 |  | 0.66 | 95
12876 | 68.15 | 142.31 | 12703.03 | -222.92 | 147.55 | 11.05 |  | 2.34 | 266.46 | 11.04 |  | 0.48 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 67.56 | 21.29 | 30 | 294 | 388.24 | 5652.94 | 5105.88 | 150 | 250 | 226.47 | 206.47 | 9000 | 0
Run | 67.56 | 21.29 | 30 | 294 | 388.24 | 5652.94 | 5105.88 | 150 | 250 | 226.47 | 206.47 | 9000 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/27/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/27/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/27/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/27/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 06/27/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/27/2021 | 00:00 | 04:30 | 4.5 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 6J | Pick up Drill Pipe
06/27/2021 | 04:30 | 05:00 | 0.5 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 5A | Tag cement and break circulation
06/27/2021 | 05:00 | 06:30 | 1.5 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 9A | Slip and cut
06/27/2021 | 06:30 | 07:30 | 1 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 8P | Service Rig
06/27/2021 | 07:30 | 08:00 | 0.5 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 24A | Install rotating head
06/27/2021 | 08:00 | 09:15 | 1.25 | 12250 | 12250 | 0 | CRV2 | 3: BHA 3 | 5A | Drill cement, float and shoe 12124 - 12238
06/27/2021 | 09:15 | 09:25 | 0.17 | 12250 | 12260 | 10 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/12250.00 t/12260.00, w/WOB 20,Flow 200, RPM 30, Press 2200, Tq 8000, ROP 60.00, Diff 200.00, Temp 257.00
06/27/2021 | 09:25 | 10:10 | 0.75 | 12260 | 12260 | 0 | CRV2 | 3: BHA 3 | 5A | Circulate for FIT
06/27/2021 | 10:10 | 10:35 | 0.42 | 12260 | 12260 | 0 | CRV2 | 3: BHA 3 | 15D | Perform FIT
06/27/2021 | 10:35 | 11:30 | 0.92 | 12260 | 12281 | 21 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12260.00 t/12281.00, TF 20.00G, w/WOB 14.00,Flow 400.00, Press 5600.00, Tq 0.00, ROP 22.91, Diff 300.00, Temp 257.00
06/27/2021 | 11:30 | 11:40 | 0.17 | 12281 | 12281 | 0 | CRV2 | 3: BHA 3 | 5A | Connection
06/27/2021 | 11:40 | 12:50 | 1.17 | 12281 | 12376 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12281.00 t/12376.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 6000.00, Tq 0.00, ROP 81.43, Diff 700.00, Temp 257.00
06/27/2021 | 12:50 | 13:05 | 0.25 | 12376 | 12376 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 13:05 | 14:25 | 1.33 | 12376 | 12425 | 49 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12376.00 t/12425.00, TF 20.00G, w/WOB 22.00,Flow 400.00, Press 5500.00, Tq 0.00, ROP 36.75, Diff 200.00, Temp 265.00
06/27/2021 | 14:25 | 14:30 | 0.08 | 12425 | 12425 | 0 | CRV2 | 3: BHA 3 | 5A | Check shot
06/27/2021 | 14:30 | 14:50 | 0.33 | 12425 | 12445 | 20 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/12425.00 t/12445.00, w/WOB 20.00,Flow 400.00, RPM 30.00, Press 6000.00, Tq 10000.00, ROP 60.00, Diff 700.00, Temp 270.00
06/27/2021 | 14:50 | 15:20 | 0.5 | 12445 | 12471 | 26 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12445.00 t/12471.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 52.00, Diff 600.00, Temp 272.00
06/27/2021 | 15:20 | 15:30 | 0.17 | 12471 | 12471 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 15:30 | 16:45 | 1.25 | 12471 | 12566 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12471.00 t/12566.00, TF -20.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 76.00, Diff 600.00, Temp 272.00
06/27/2021 | 16:45 | 16:55 | 0.17 | 12566 | 12566 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 16:55 | 17:15 | 0.33 | 12566 | 12586 | 20 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/12566.00 t/12586.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 60.00, Diff 600.00, Temp 272.00
06/27/2021 | 17:15 | 18:05 | 0.83 | 12586 | 12660 | 74 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12586.00 t/12660.00, TF -10G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 88.80, Diff 600.00, Temp 272.00
06/27/2021 | 18:05 | 18:10 | 0.08 | 12660 | 12660 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 18:10 | 18:30 | 0.33 | 12660 | 12680 | 20 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/12660.00 t/12680.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 60.00, Diff 600.00, Temp 272.00
06/27/2021 | 18:30 | 19:40 | 1.17 | 12680 | 12756 | 76 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12680.00 t/12756.00, TF -10G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 65.14, Diff 600.00, Temp 272.00
06/27/2021 | 19:40 | 20:05 | 0.42 | 12756 | 12756 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 20:05 | 21:00 | 0.92 | 12756 | 12851 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12756.00 t/12851.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 103.64, Diff 600.00, Temp 277.00
06/27/2021 | 21:00 | 21:05 | 0.08 | 12851 | 12851 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 21:05 | 21:20 | 0.25 | 12851 | 12876 | 25 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/12851.00 t/12876.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 100.00, Diff 600.00, Temp 277.00
06/27/2021 | 21:20 | 22:05 | 0.75 | 12876 | 12944 | 68 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12876.00 t/12944.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 90.67, Diff 600.00, Temp 277.00
06/27/2021 | 22:05 | 22:10 | 0.08 | 12944 | 12944 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 22:10 | 22:40 | 0.5 | 12944 | 12994 | 50 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12944.00 t/12994.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 100.00, Diff 600.00, Temp 277.00
06/27/2021 | 22:40 | 23:30 | 0.83 | 12994 | 12994 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/27/2021 | 23:30 | 24:00 | 0.5 | 12994 | 13010 | 16 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12994.00 t/13010.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 32.00, Diff 600.00, Temp 277.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_28_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 112660
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Drill ahead
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13010 |  | 12250 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 44 | PV: | 17
End Depth (Usft): |  | 15558 |  | 15558 |  | OD (in): |  | 7.625 |  | 300: | 27 | YP: | 10
Total Drilled (Usft): |  | 2548 |  | 3308 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 20 | Viscosity: | 48
Slide Drilled (Usft): |  | 195 |  | 794 | [5 empty] | 100: | 14 | Chlorides: | 59800
Rotary Drilled (Usft): |  | 2353 |  | 2514 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 16.00
Drlg/Circ Hrs: |  | 20.58 / 3.00 |  | 31.83 / 8.00 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 72/28
Slide Drilling Hrs: |  | 5.17 |  | 14 |  | SN: |  | 13601236 |  | 10s Gel: | 7 | Weight (ppg): | 11.3
Rotary Drilling Hrs: |  | 15.42 |  | 17.83 |  | Bit # |  | 3 |  | PH / Temp(F) | 7.0 / 288.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 152.63 / 37.74 |  | 140.97 / 56.71 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 60.42 |  | Grade In: |  | New
% Slide: |  | 7.65 |  | 24 |  | Grade Out: |  | 0-1-WT-A-X-I-NO-BHA
% Rotary: |  | 92.35 |  | 76 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.003 |  |  |  | 5.5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.03 |  | 35.91
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.18
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.17
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.22
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.76
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.33
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.35
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.73
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.39
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.84
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.83
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.77 |  | 2821.6
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5930.04
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.98
5951.98
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.05 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12970 | 76.14 | 140.65 | 12731.83 | -292.85 | 203.25 | 8.66 |  | -11.45 | 355.85 | 8.5 |  | -1.77 | 94
13064 | 74.31 | 140.23 | 12755.8 | -362.92 | 261.13 | 1.99 |  | -167.54 | 446.71 | -1.95 |  | -0.45 | 94
13159 | 79.6 | 141.21 | 12777.24 | -434.54 | 319.69 | 5.66 |  | 10.34 | 539.21 | 5.57 |  | 1.03 | 95
13254 | 84.21 | 141.36 | 12790.61 | -507.9 | 378.5 | 4.86 |  | 1.86 | 633.23 | 4.85 |  | 0.16 | 95
13349 | 88.87 | 140.83 | 12796.34 | -581.68 | 438.04 | 4.94 |  | -6.49 | 728.02 | 4.91 |  | -0.56 | 95
13443 | 88.06 | 140.8 | 12798.86 | -654.51 | 497.41 | 0.86 |  | -177.88 | 821.97 | -0.86 |  | -0.03 | 94
13537 | 88.35 | 140.78 | 12801.81 | -727.31 | 556.81 | 0.31 |  | -3.94 | 915.91 | 0.31 |  | -0.02 | 94
13630 | 87.11 | 140.67 | 12805.49 | -799.24 | 615.63 | 1.34 |  | -174.94 | 1008.81 | -1.33 |  | -0.12 | 93
13725 | 86.34 | 140.91 | 12810.92 | -872.73 | 675.59 | 0.85 |  | 162.72 | 1103.64 | -0.81 |  | 0.25 | 95
13820 | 86.72 | 140.95 | 12816.67 | -946.35 | 735.35 | 0.4 |  | 6 | 1198.45 | 0.4 |  | 0.04 | 95
13915 | 87.18 | 141.04 | 12821.72 | -1020.07 | 795.06 | 0.49 |  | 11.06 | 1293.31 | 0.48 |  | 0.09 | 95
14009 | 87.25 | 140.95 | 12826.29 | -1093.03 | 854.15 | 0.12 |  | -52.09 | 1387.19 | 0.07 |  | -0.1 | 94
14103 | 86.56 | 141.02 | 12831.36 | -1165.96 | 913.24 | 0.74 |  | 174.22 | 1481.04 | -0.73 |  | 0.07 | 94
14197 | 88.68 | 141.94 | 12835.27 | -1239.44 | 971.73 | 2.46 |  | 23.46 | 1574.95 | 2.26 |  | 0.98 | 94
14292 | 89.53 | 142.09 | 12836.75 | -1314.3 | 1030.19 | 0.91 |  | 10.01 | 1669.94 | 0.89 |  | 0.16 | 95
14388 | 88.47 | 141.18 | 12838.43 | -1389.56 | 1089.76 | 1.46 |  | -139.37 | 1765.92 | -1.1 |  | -0.95 | 96
14482 | 88.9 | 141.15 | 12840.58 | -1462.76 | 1148.69 | 0.46 |  | -3.99 | 1859.89 | 0.46 |  | -0.03 | 94
14577 | 87.81 | 140.87 | 12843.31 | -1536.57 | 1208.44 | 1.18 |  | -165.6 | 1954.83 | -1.15 |  | -0.29 | 95
14672 | 88.14 | 140.99 | 12846.67 | -1610.28 | 1268.28 | 0.37 |  | 19.97 | 2049.76 | 0.35 |  | 0.13 | 95
14768 | 86.63 | 141.74 | 12851.05 | -1685.19 | 1328.15 | 1.76 |  | 153.63 | 2145.65 | -1.57 |  | 0.78 | 96
14862 | 86.24 | 141.86 | 12856.89 | -1758.92 | 1386.17 | 0.43 |  | 162.93 | 2239.47 | -0.41 |  | 0.13 | 94
14956 | 86.25 | 142.01 | 12863.05 | -1832.77 | 1444 | 0.16 |  | 86.18 | 2333.27 | 0.01 |  | 0.16 | 94
15050 | 86 | 142.16 | 12869.4 | -1906.75 | 1501.63 | 0.31 |  | 149.1 | 2427.06 | -0.27 |  | 0.16 | 94
15145 | 87.64 | 142.83 | 12874.67 | -1982 | 1559.38 | 1.86 |  | 22.21 | 2521.9 | 1.73 |  | 0.71 | 95
15240 | 88.09 | 143.23 | 12878.21 | -2057.85 | 1616.47 | 0.63 |  | 41.62 | 2616.81 | 0.47 |  | 0.42 | 95
15334 | 88.71 | 143.28 | 12880.83 | -2133.14 | 1672.69 | 0.66 |  | 4.61 | 2710.75 | 0.66 |  | 0.05 | 94
15430 | 86.31 | 141.79 | 12885.01 | -2209.26 | 1731.02 | 2.94 |  | -148.22 | 2806.64 | -2.5 |  | -1.55 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 123.79 | 27.73 | 80 | 340 | 382 | 6222.22 | 5384.44 | 140 | 256.62 | 226.33 | 205.07 | 11379.31 | 6000
Run | 103.92 | 25.97 | 76.77 | 338 | 383.71 | 6066.13 | 5308.06 | 150 | 254.81 | 226.37 | 205.45 | 11225.81 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Multi Rig Discount |  |  |  |  | 06/28/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/28/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 06/28/2021 |  | 10 |  | 600 |  | 1 | 600
Dir & MWD /Gamma |  |  |  |  | 06/28/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/28/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/28/2021 | 00:00 | 00:20 | 0.33 | 13010 | 13038 | 28 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13010.00 t/13038.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 84.00, Diff 600.00, Temp 277.00
06/28/2021 | 00:20 | 00:25 | 0.08 | 13038 | 13038 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 00:25 | 01:20 | 0.92 | 13038 | 13112 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13038.00 t/13112.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 80.73, Diff 600.00, Temp 277.00
06/28/2021 | 01:20 | 01:55 | 0.58 | 13112 | 13132 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/13112.00 t/13132.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 34.29, Diff 600.00, Temp 277.00
06/28/2021 | 01:55 | 02:00 | 0.08 | 13132 | 13132 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 02:00 | 02:40 | 0.67 | 13132 | 13162 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/13132.00 t/13162.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 45.00, Diff 600.00, Temp 277.00
06/28/2021 | 02:40 | 03:20 | 0.67 | 13162 | 13227 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13162.00 t/13227.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 97.50, Diff 600.00, Temp 277.00
06/28/2021 | 03:20 | 03:25 | 0.08 | 13227 | 13227 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 03:25 | 04:20 | 0.92 | 13227 | 13277 | 50 | LAT | 3: BHA 3 | 2J | Slide Drill f/13227.00 t/13277.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 5900.00, Tq 0.00, ROP 54.55, Diff 600.00, Temp 277.00
06/28/2021 | 04:20 | 04:50 | 0.5 | 13277 | 13377 | 100 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13277.00 t/13377.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 200.00, Diff 600.00, Temp 277.00
06/28/2021 | 04:50 | 05:00 | 0.17 | 13377 | 13377 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 05:00 | 05:40 | 0.67 | 13377 | 13417 | 40 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13377.00 t/13417.00, w/WOB 22.00,Flow 400.00, RPM 0.00, Press 5900.00, Tq 0.00, ROP 60.00, Diff 600.00, Temp 277.00
06/28/2021 | 05:40 | 05:45 | 0.08 | 13417 | 13417 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 05:45 | 05:55 | 0.17 | 13417 | 13427 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13417.00 t/13427.00, w/WOB 25,Flow 400.00, RPM 80, Press 6200, Tq 12000, ROP 60.00, Diff 800.00, Temp 288.00
06/28/2021 | 05:55 | 06:10 | 0.25 | 13427 | 13437 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/13427.00 t/13437.00, TF 180G, w/WOB 20,Flow 400.00, Press 5700, Tq 0, ROP 40.00, Diff 300.00, Temp 288.00
06/28/2021 | 06:10 | 06:35 | 0.42 | 13437 | 13511 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13437.00 t/13511.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 6200.00, Tq 12000.00, ROP 177.60, Diff 800.00, Temp 288.00
06/28/2021 | 06:35 | 06:40 | 0.08 | 13511 | 13511 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 06:40 | 07:10 | 0.5 | 13511 | 13605 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13511.00 t/13605.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 12000.00, ROP 188.00, Diff 800.00, Temp 290.00
06/28/2021 | 07:10 | 07:15 | 0.08 | 13605 | 13605 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 07:15 | 07:20 | 0.08 | 13605 | 13615 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13605.00 t/13615.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 12000.00, ROP 120.00, Diff 800.00, Temp 295.00
06/28/2021 | 07:20 | 07:40 | 0.33 | 13615 | 13627 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/13615.00 t/13627.00, TF 180.00G, w/WOB 20.00,Flow 370.00, Press 5600.00, Tq 0.00, ROP 36.00, Diff 400.00, Temp 295.00
06/28/2021 | 07:40 | 07:50 | 0.17 | 13627 | 13646 | 19 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13627.00 t/13646.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 12000.00, ROP 114.00, Diff 800.00, Temp 295.00
06/28/2021 | 07:50 | 08:10 | 0.33 | 13646 | 13646 | 0 | LAT | 3: BHA 3 | 5D | Circulate out gas
06/28/2021 | 08:10 | 08:30 | 0.33 | 13646 | 13698 | 52 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13646.00 t/13698.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 10000.00, ROP 156.00, Diff 800.00, Temp 293.00
06/28/2021 | 08:30 | 08:35 | 0.08 | 13698 | 13698 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 08:35 | 09:10 | 0.58 | 13698 | 13793 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13698.00 t/13793.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6100.00, Tq 10000.00, ROP 162.86, Diff 800.00, Temp 293.00
06/28/2021 | 09:10 | 09:15 | 0.08 | 13793 | 13793 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 09:15 | 09:50 | 0.58 | 13793 | 13888 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13793.00 t/13888.00, w/WOB 25.00,Flow 370.00, RPM 80.00, Press 6100.00, Tq 10000.00, ROP 162.86, Diff 800.00, Temp 297.00
06/28/2021 | 09:50 | 09:55 | 0.08 | 13888 | 13888 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 09:55 | 10:45 | 0.83 | 13888 | 13983 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13888.00 t/13983.00, w/WOB 25.00,Flow 370.00, RPM 80.00, Press 6100.00, Tq 10000.00, ROP 114.00, Diff 800.00, Temp 298.00
06/28/2021 | 10:45 | 10:50 | 0.08 | 13983 | 13983 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 10:50 | 11:35 | 0.75 | 13983 | 14077 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13983.00 t/14077.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6100.00, Tq 10000.00, ROP 125.33, Diff 800.00, Temp 300.00
06/28/2021 | 11:35 | 11:40 | 0.08 | 14077 | 14077 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 11:40 | 12:25 | 0.75 | 14077 | 14171 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14077.00 t/14171.00, w/WOB 25.00,Flow 340.00, RPM 80.00, Press 5800.00, Tq 11000.00, ROP 125.33, Diff 800.00, Temp 300.00
06/28/2021 | 12:25 | 12:50 | 0.42 | 14171 | 14171 | 0 | LAT | 3: BHA 3 | 6K | L/D bad joint of DP
06/28/2021 | 12:50 | 12:55 | 0.08 | 14171 | 14171 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 12:55 | 13:00 | 0.08 | 14171 | 14181 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14171.00 t/14181.00, w/WOB 25.00,Flow 380.00, RPM 80.00, Press 6200.00, Tq 11000.00, ROP 120.00, Diff 800.00, Temp 306.00
06/28/2021 | 13:00 | 13:20 | 0.33 | 14181 | 14191 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/14181.00 t/14191.00, TF 20.00G, w/WOB 20.00,Flow 380.00, Press 5700.00, Tq 0.00, ROP 30.00, Diff 300.00, Temp 306.00
06/28/2021 | 13:20 | 13:50 | 0.5 | 14191 | 14265 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14191.00 t/14265.00, w/WOB 25.00,Flow 380.00, RPM 80.00, Press 6200.00, Tq 11000.00, ROP 148.00, Diff 800.00, Temp 306.00
06/28/2021 | 13:50 | 13:55 | 0.08 | 14265 | 14265 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 13:55 | 14:25 | 0.5 | 14265 | 14360 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14265.00 t/14360.00, w/WOB 30.00,Flow 380.00, RPM 80.00, Press 6200.00, Tq 11000.00, ROP 190.00, Diff 800.00, Temp 309.00
06/28/2021 | 14:25 | 14:30 | 0.08 | 14360 | 14360 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 14:30 | 14:35 | 0.08 | 14360 | 14370 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14360.00 t/14370.00, w/WOB 30.00,Flow 380.00, RPM 80.00, Press 6400.00, Tq 11000.00, ROP 120.00, Diff 1000.00, Temp 309.00
06/28/2021 | 14:35 | 15:00 | 0.42 | 14370 | 14384 | 14 | LAT | 3: BHA 3 | 2J | Slide Drill f/14370.00 t/14384.00, TF 180.00G, w/WOB 22.00,Flow 380.00, Press 5800.00, Tq 0.00, ROP 33.60, Diff 300.00, Temp 309.00
06/28/2021 | 15:00 | 15:25 | 0.42 | 14384 | 14456 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14384.00 t/14456.00, w/WOB 30.00,Flow 380.00, RPM 80.00, Press 6700.00, Tq 11000.00, ROP 172.80, Diff 1200.00, Temp 309.00
06/28/2021 | 15:25 | 15:30 | 0.08 | 14456 | 14456 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 15:30 | 16:00 | 0.5 | 14456 | 14555 | 99 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14456.00 t/14555.00, w/WOB 35.00,Flow 380.00, RPM 80.00, Press 6700.00, Tq 11000.00, ROP 198.00, Diff 1200.00, Temp 309.00
06/28/2021 | 16:00 | 16:05 | 0.08 | 14555 | 14555 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 16:05 | 16:10 | 0.08 | 14555 | 14565 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14555.00 t/14565.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6700.00, Tq 11000.00, ROP 120.00, Diff 1200.00, Temp 309.00
06/28/2021 | 16:10 | 16:30 | 0.33 | 14565 | 14577 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/14565.00 t/14577.00, TF 180.00G, w/WOB 25.00,Flow 380.00, Press 5900.00, Tq 0.00, ROP 36.00, Diff 400.00, Temp 310.00
06/28/2021 | 16:30 | 16:50 | 0.33 | 14577 | 14645 | 68 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14577.00 t/14645.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 204.00, Diff 1100.00, Temp 311.00
06/28/2021 | 16:50 | 16:55 | 0.08 | 14645 | 14645 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 16:55 | 17:20 | 0.42 | 14645 | 14740 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14645.00 t/14740.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 228.00, Diff 1100.00, Temp 311.00
06/28/2021 | 17:20 | 17:25 | 0.08 | 14740 | 14740 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 17:25 | 17:30 | 0.08 | 14740 | 14750 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14740.00 t/14750.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 120.00, Diff 1100.00, Temp 311.00
06/28/2021 | 17:30 | 18:00 | 0.5 | 14750 | 14765 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/14750.00 t/14765.00, TF 180G, w/WOB 32.00,Flow 380.00, Press 6600.00, Tq 12000.00, ROP 30.00, Diff 1100.00, Temp 311.00
06/28/2021 | 18:00 | 18:55 | 0.92 | 14765 | 14930 | 165 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14765.00 t/14930.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 180.00, Diff 1100.00, Temp 311.00
06/28/2021 | 18:55 | 19:05 | 0.17 | 14930 | 14930 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 19:05 | 19:30 | 0.42 | 14930 | 15024 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14930.00 t/15024.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 225.60, Diff 1100.00, Temp 311.00
06/28/2021 | 19:30 | 19:35 | 0.08 | 15024 | 15024 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 19:35 | 20:10 | 0.58 | 15024 | 15130 | 106 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15024.00 t/15130.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 181.71, Diff 1100.00, Temp 311.00
06/28/2021 | 20:10 | 20:20 | 0.17 | 15130 | 15130 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 20:20 | 20:45 | 0.42 | 15130 | 15142 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/15130.00 t/15142.00, TF 0G, w/WOB 32.00,Flow 380.00, Press 6600.00, Tq 12000.00, ROP 28.80, Diff 1100.00, Temp 311.00
06/28/2021 | 20:45 | 21:10 | 0.42 | 15142 | 15213 | 71 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15142.00 t/15213.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 170.40, Diff 1100.00, Temp 311.00
06/28/2021 | 21:10 | 21:20 | 0.17 | 15213 | 15213 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 21:20 | 21:45 | 0.42 | 15213 | 15308 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15213.00 t/15308.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 228.00, Diff 1100.00, Temp 311.00
06/28/2021 | 21:45 | 22:00 | 0.25 | 15308 | 15308 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 22:00 | 22:40 | 0.67 | 15308 | 15414 | 106 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15308.00 t/15414.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 159.00, Diff 1100.00, Temp 311.00
06/28/2021 | 22:40 | 22:45 | 0.08 | 15414 | 15414 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 22:45 | 23:10 | 0.42 | 15414 | 15424 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/15414.00 t/15424.00, TF -140G, w/WOB 32.00,Flow 380.00, Press 6600.00, Tq 12000.00, ROP 24.00, Diff 1100.00, Temp 311.00
06/28/2021 | 23:10 | 23:35 | 0.42 | 15424 | 15498 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15424.00 t/15498.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 177.60, Diff 1100.00, Temp 311.00
06/28/2021 | 23:35 | 23:40 | 0.08 | 15498 | 15498 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/28/2021 | 23:40 | 24:00 | 0.33 | 15498 | 15558 | 60 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15498.00 t/15558.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 180.00, Diff 1100.00, Temp 311.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_29_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/29/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 22700 |  |  | Well Cost($): |  | 135360
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15558 |  | 12250 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 42 | PV: | 16
End Depth (Usft): |  | 16230 |  | 16230 |  | OD (in): |  | 7.625 |  | 300: | 26 | YP: | 10
Total Drilled (Usft): |  | 672 |  | 3980 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 19 | Viscosity: | 48
Slide Drilled (Usft): |  | 38 |  | 832 | [5 empty] | 100: | 13 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 634 |  | 3148 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.80
Drlg/Circ Hrs: |  | 6.75 / 4.75 |  | 38.58 / 12.75 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 1.58 |  | 15.58 |  | SN: |  | 13601236 |  | 10s Gel: | 6 | Weight (ppg): | 11.7
Rotary Drilling Hrs: |  | 5.17 |  | 23 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 327.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 122.71 / 24.00 |  | 136.87 / 53.39 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 84.42 |  | Grade In: |  | New
% Slide: |  | 5.65 |  | 20.9 |  | Grade Out: |  | 0-1-WT-A-X-I-NO-BHA
% Rotary: |  | 94.35 |  | 79.1 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.003 |  |  |  | 5.5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.03 |  | 35.91
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.18
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.17
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.22
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.76
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.33
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.35
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.73
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.39
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.84
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.83
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.77 |  | 2821.6
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5930.04
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.98
5951.98
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.05 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15524 | 86.21 | 142.02 | 12891.14 | -2283.08 | 1788.89 | 0.27 |  | 113.55 | 2900.44 | -0.11 |  | 0.24 | 94
15619 | 87.41 | 143.2 | 12896.42 | -2358.44 | 1846.49 | 1.77 |  | 44.51 | 2995.28 | 1.26 |  | 1.24 | 95
15714 | 87.25 | 143.29 | 12900.85 | -2434.47 | 1903.27 | 0.19 |  | 150.67 | 3090.15 | -0.17 |  | 0.09 | 95
15809 | 88.47 | 141.61 | 12904.4 | -2509.73 | 1961.13 | 2.18 |  | -54.03 | 3185.08 | 1.28 |  | -1.77 | 95
15903 | 89.44 | 141.89 | 12906.11 | -2583.54 | 2019.31 | 1.07 |  | 16.1 | 3279.06 | 1.03 |  | 0.3 | 94
15998 | 90.53 | 142.06 | 12906.14 | -2658.37 | 2077.83 | 1.16 |  | 8.86 | 3374.06 | 1.15 |  | 0.18 | 95
16093 | 89.58 | 140.74 | 12906.04 | -2732.61 | 2137.1 | 1.71 |  | -125.74 | 3469.05 | -1 |  | -1.39 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 99.56 | 32.53 | 80 | 334 | 373.33 | 6366.67 | 5233.33 | 140 | 266.8 | 223.67 | 198.8 | 14727.27 | 8000
Run | 103.15 | 27.25 | 77.62 | 337 | 381.69 | 6124.68 | 5293.51 | 150 | 257.14 | 225.84 | 204.16 | 12142.86 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12805 TVD at 0 VS with 88.3 INC 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/29/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/29/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/29/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/29/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 06/29/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 06/29/2021 |  | 18 |  | 1250 |  | 1 | 1250
Pro Azimuthal Gamma Ray Core charge >330F |  |  |  |  | 06/29/2021 |  | 19 |  | 12000 |  | 1 | 12000
Total | [11 empty] | 22700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/29/2021 | 00:00 | 00:15 | 0.25 | 15558 | 15607 | 49 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15558.00 t/15607.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 136.00, Diff 1100.00, Temp 311.00
06/29/2021 | 00:15 | 00:50 | 0.58 | 15607 | 15607 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 00:50 | 01:10 | 0.33 | 15607 | 15615 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/15607.00 t/15615.00, TF 0.00G, w/WOB 32.00,Flow 380.00, Press 6600.00, Tq 12000.00, ROP 24.00, Diff 1100.00, Temp 311.00
06/29/2021 | 01:10 | 01:35 | 0.42 | 15615 | 15687 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15615.00 t/15687.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 172.80, Diff 1100.00
06/29/2021 | 01:35 | 01:40 | 0.08 | 15687 | 15687 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 01:40 | 02:15 | 0.58 | 15687 | 15782 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15687.00 t/15782.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 162.86, Diff 1100.00
06/29/2021 | 02:15 | 02:20 | 0.08 | 15782 | 15782 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 02:20 | 02:35 | 0.25 | 15782 | 15795 | 13 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15782.00 t/15795.00, w/WOB 32.00,Flow 380.00, RPM 80.00, Press 6600.00, Tq 12000.00, ROP 52.00, Diff 1100.00
06/29/2021 | 02:35 | 03:00 | 0.42 | 15795 | 15805 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/15795.00 t/15805.00, TF -45G, w/WOB 32.00,Flow 380.00, Press 6600.00, Tq 12000.00, ROP 24.00, Diff 1100.00
06/29/2021 | 03:00 | 03:35 | 0.58 | 15805 | 15877 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15805.00 t/15877.00, w/WOB 32.00,Flow 370.00, RPM 80.00, Press 6300.00, Tq 13000.00, ROP 123.43, Diff 1200.00, Temp 329.00
06/29/2021 | 03:35 | 03:40 | 0.08 | 15877 | 15877 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 03:40 | 04:20 | 0.67 | 15877 | 15971 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15877.00 t/15971.00, w/WOB 32.00,Flow 370.00, RPM 80.00, Press 6300.00, Tq 13000.00, ROP 141.00, Diff 1200.00, Temp 329.00
06/29/2021 | 04:20 | 04:25 | 0.08 | 15971 | 15971 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 04:25 | 05:05 | 0.67 | 15971 | 16066 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15971.00 t/16066.00, w/WOB 32.00,Flow 370.00, RPM 80.00, Press 6300.00, Tq 13000.00, ROP 162.86, Diff 1200.00, Temp 329.00
06/29/2021 | 05:05 | 05:10 | 0.08 | 16066 | 16066 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 05:10 | 05:20 | 0.17 | 16066 | 16078 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16066.00 t/16078.00, w/WOB 32.00,Flow 370.00, RPM 80.00, Press 6300.00, Tq 13000.00, ROP 72.00, Diff 1200.00, Temp 329.00
06/29/2021 | 05:20 | 05:45 | 0.42 | 16078 | 16088 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/16078.00 t/16088.00, TF -150.00G, w/WOB 32.00,Flow 370.00, Press 6300.00, Tq 0.00, ROP 24.00, Diff 1200.00, Temp 330.00
06/29/2021 | 05:45 | 06:25 | 0.67 | 16088 | 16161 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16088.00 t/16161.00, w/WOB 38.00,Flow 370.00, RPM 80.00, Press 6400.00, Tq 20000.00, ROP 109.50, Diff 1300.00, Temp 331.00
06/29/2021 | 06:25 | 06:30 | 0.08 | 16161 | 16161 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
06/29/2021 | 06:30 | 06:35 | 0.08 | 16161 | 16171 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16161.00 t/16171.00, w/WOB 38.00,Flow 370.00, RPM 80.00, Press 6400.00, Tq 20000.00, ROP 120.00, Diff 1300.00, Temp 331.00
06/29/2021 | 06:35 | 07:00 | 0.42 | 16171 | 16181 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/16171.00 t/16181.00, TF 180.00G, w/WOB 20.00,Flow 370.00, Press 5500.00, Tq 0.00, ROP 24.00, Diff 400.00, Temp 325.00
06/29/2021 | 07:00 | 07:50 | 0.83 | 16181 | 16230 | 49 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16181.00 t/16230.00, w/WOB 40.00,Flow 370.00, RPM 80.00, Press 6400.00, Tq 22000.00, ROP 58.80, Diff 1300.00, Temp 331.00
06/29/2021 | 07:50 | 09:15 | 1.42 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 5A | Circulate to POOH f/ Slow ROP
06/29/2021 | 09:15 | 10:30 | 1.25 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 6B | POOH t/ change bit and motor t/15189
06/29/2021 | 10:30 | 11:00 | 0.5 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
06/29/2021 | 11:00 | 12:30 | 1.5 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 6B | POOH t/12338
06/29/2021 | 12:30 | 13:15 | 0.75 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 5A | Circulate B/U
06/29/2021 | 13:15 | 13:30 | 0.25 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 6B | POOH t/11855
06/29/2021 | 13:30 | 15:00 | 1.5 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 5D | Monitor casing pressure and pump mud cap
06/29/2021 | 15:00 | 23:30 | 8.5 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 6B | POOH t/surface
06/29/2021 | 23:30 | 24:00 | 0.5 | 16230 | 16230 | 0 | LAT | 3: BHA 3 | 6P | Rack back NMDC, Tomax, and x-o in derrick with single drill pipe and pup joint
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_30_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/30/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 20700 |  |  | Well Cost($): |  | 156060
24hr Summary:
|  |  |  | 24hr Lookahead: |  | TIH and continue drilling
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16230 |  | 16230 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 42 | PV: | 16
End Depth (Usft): |  | 16821 |  | 16821 |  | OD (in): |  | 7.625 |  | 300: | 26 | YP: | 10
Total Drilled (Usft): |  | 591 |  | 591 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 19 | Viscosity: | 48
Slide Drilled (Usft): |  | 18 |  | 18 | [5 empty] | 100: | 13 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 573 |  | 573 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.80
Drlg/Circ Hrs: |  | 4.08 / 5.67 |  | 4.08 / 5.67 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 0.67 |  | 0.67 |  | SN: |  | 13594950 |  | 10s Gel: | 6 | Weight (ppg): | 11.7
Rotary Drilling Hrs: |  | 3.42 |  | 3.42 |  | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 327.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 167.71 / 27.00 |  | 167.71 / 27.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 22 |  | 22 |  | Grade In: |  | New
% Slide: |  | 3.05 |  | 3.05 |  | Grade Out: |  | 0-1-WT-G-X-I-PN-PP
% Rotary: |  | 96.95 |  | 96.95 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 2.9
6/7 8.8 2.12 Slick HPT 0.023 |  |  |  | 5.5 | 2 |  |  |  |  | 32.99 |  | 35.89
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.16
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.15
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.2
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.74
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.31
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.33
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.71
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.37
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.82
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.81
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 23.65 |  | 2821.46
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5929.9
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.84
5951.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.96 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16282 | 88.17 | 141.87 | 12909.23 | -2879.95 | 2255.42 | 1.32 |  | 145.44 | 3658 | -1.08 |  | 0.75 | 95
16376 | 87.7 | 141.26 | 12912.61 | -2953.53 | 2313.81 | 0.82 |  | -127.64 | 3751.94 | -0.5 |  | -0.65 | 94
16471 | 87.75 | 141.09 | 12916.38 | -3027.49 | 2373.32 | 0.19 |  | -73.6 | 3846.86 | 0.05 |  | -0.18 | 95
16564 | 87.32 | 141.22 | 12920.38 | -3099.85 | 2431.6 | 0.48 |  | 163.2 | 3939.77 | -0.46 |  | 0.14 | 93
16659 | 86.88 | 142.83 | 12925.19 | -3174.64 | 2489.98 | 1.75 |  | 105.34 | 4034.64 | -0.46 |  | 1.69 | 95
16753 | 86.04 | 141.69 | 12930.99 | -3248.83 | 2547.4 | 1.5 |  | -126.47 | 4128.46 | -0.89 |  | -1.21 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 144.73 | 25 | 80 | 325 | 360 | 6400 | 5400 | 140 | 260 | 220 | 190 | 14000 | 8000
Run | 144.73 | 25 | 80 | 325 | 360 | 6400 | 5400 | 150 | 260 | 220 | 190 | 14000 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12805 TVD at 0 VS with 88.3 INC 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/30/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/30/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 06/30/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/30/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 06/30/2021 |  | 10 |  | 600 |  | 1 | 600
5.5 Premium Motor Reline |  |  |  |  | 06/30/2021 |  | 9 |  | 9000 |  | 1 | 9000
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 06/30/2021 |  | 15 |  | 1000 |  | 1 | 1000
MWD hot hole charge |  |  |  |  | 06/30/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 20700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/30/2021 | 00:00 | 02:00 | 2 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 6O | Lay down BHA 3 and pick up BHA 4
06/30/2021 | 02:00 | 07:00 | 5 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 6A | TIH t/ 5951
06/30/2021 | 07:00 | 08:00 | 1 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 9A | Slip and cut
06/30/2021 | 08:00 | 09:00 | 1 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 8P | Rig Service
06/30/2021 | 09:00 | 10:45 | 1.75 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 6A | Tih t/ 9827
06/30/2021 | 10:45 | 12:45 | 2 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 5A | Circulate out mud cap
06/30/2021 | 12:45 | 14:00 | 1.25 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 6A | TIH t/ 12400
06/30/2021 | 14:00 | 16:00 | 2 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 5A | Circulate out mud cap
06/30/2021 | 16:00 | 16:15 | 0.25 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 5A | Test MWD and orient motor HS
06/30/2021 | 16:15 | 18:30 | 2.25 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 6A | TIH t/ 16160
06/30/2021 | 18:30 | 19:05 | 0.58 | 16230 | 16230 | 0 | LAT | 4: BHA 4 | 3C | Wash to bottom
06/30/2021 | 19:05 | 19:15 | 0.17 | 16230 | 16255 | 25 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16230.00 t/16255.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 150.00, Diff 1000.00, Temp 327.00
06/30/2021 | 19:15 | 19:20 | 0.08 | 16255 | 16255 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
06/30/2021 | 19:20 | 19:40 | 0.33 | 16255 | 16274 | 19 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16255.00 t/16274.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 57.00, Diff 1000.00, Temp 327.00
06/30/2021 | 19:40 | 20:00 | 0.33 | 16274 | 16284 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/16274.00 t/16284.00, TF 180.00G, w/WOB 25.00,Flow 360.00, Press 6400.00, Tq 14000.00, ROP 30.00, Diff 1000.00, Temp 327.00
06/30/2021 | 20:00 | 20:25 | 0.42 | 16284 | 16350 | 66 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16284.00 t/16350.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 158.40, Diff 1000.00, Temp 327.00
06/30/2021 | 20:25 | 20:35 | 0.17 | 16350 | 16350 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
06/30/2021 | 20:35 | 21:00 | 0.42 | 16350 | 16444 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16350.00 t/16444.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 225.60, Diff 1000.00, Temp 331.00
06/30/2021 | 21:00 | 21:10 | 0.17 | 16444 | 16444 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
06/30/2021 | 21:10 | 21:40 | 0.5 | 16444 | 16539 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16444.00 t/16539.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 190.00, Diff 1000.00, Temp 331.00
06/30/2021 | 21:40 | 21:45 | 0.08 | 16539 | 16539 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
06/30/2021 | 21:45 | 22:15 | 0.5 | 16539 | 16632 | 93 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16539.00 t/16632.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 186.00, Diff 1000.00, Temp 331.00
06/30/2021 | 22:15 | 22:25 | 0.17 | 16632 | 16632 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
06/30/2021 | 22:25 | 22:55 | 0.5 | 16632 | 16727 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16632.00 t/16727.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 190.00, Diff 1000.00, Temp 331.00
06/30/2021 | 22:55 | 23:00 | 0.08 | 16727 | 16727 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
06/30/2021 | 23:00 | 23:10 | 0.17 | 16727 | 16739 | 12 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16727.00 t/16739.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 72.00, Diff 1000.00
06/30/2021 | 23:10 | 23:30 | 0.33 | 16739 | 16747 | 8 | LAT | 4: BHA 4 | 2J | Slide Drill f/16739.00 t/16747.00, TF -90.00G, w/WOB 25.00,Flow 360.00, Press 6400.00, Tq 14000.00, ROP 24.00, Diff 1000.00
06/30/2021 | 23:30 | 23:55 | 0.42 | 16747 | 16821 | 74 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16747.00 t/16821.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 177.60, Diff 1000.00
06/30/2021 | 23:55 | 24:00 | 0.08 | 16821 | 16821 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_1_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 07/01/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 22700 |  |  | Well Cost($): |  | 178760
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16821 |  | 16230 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 56 | PV: | 23
End Depth (Usft): |  | 18363 |  | 18363 |  | OD (in): |  | 7.625 |  | 300: | 33 | YP: | 10
Total Drilled (Usft): |  | 1542 |  | 2133 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 25 | Viscosity: | 48
Slide Drilled (Usft): |  | 57 |  | 75 | [5 empty] | 100: | 16 | Chlorides: | 53800
Rotary Drilled (Usft): |  | 1485 |  | 2058 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.80
Drlg/Circ Hrs: |  | 12.58 / 4.42 |  | 16.67 / 10.08 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 2.75 |  | 3.42 |  | SN: |  | 13594950 |  | 10s Gel: | 6 | Weight (ppg): | 11.8
Rotary Drilling Hrs: |  | 9.83 |  | 13.25 |  | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 331.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 151.02 / 20.73 |  | 155.32 / 21.95 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 46 |  | Grade In: |  | New
% Slide: |  | 3.7 |  | 3.52 |  | Grade Out: |  | 0-1-WT-G-X-I-PN-PP
% Rotary: |  | 96.3 |  | 96.48 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 2.9
6/7 8.8 2.12 Slick HPT 0.023 |  |  |  | 5.5 | 2 |  |  |  |  | 32.99 |  | 35.89
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.16
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.15
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.2
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.74
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.31
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.33
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.71
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.37
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.82
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.81
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 23.65 |  | 2821.46
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5929.9
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.84
5951.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.96 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16848 | 87.69 | 141.82 | 12936.19 | -3323.33 | 2606.12 | 1.74 |  | 4.5 | 4223.31 | 1.74 |  | 0.14 | 95
16942 | 88.4 | 142.25 | 12939.4 | -3397.39 | 2663.91 | 0.88 |  | 31.19 | 4317.26 | 0.76 |  | 0.46 | 94
17037 | 87.03 | 141.52 | 12943.18 | -3472.07 | 2722.5 | 1.63 |  | -151.98 | 4412.18 | -1.44 |  | -0.77 | 95
17131 | 87.11 | 141.32 | 12947.99 | -3545.46 | 2781.04 | 0.23 |  | -68.18 | 4506.05 | 0.09 |  | -0.21 | 94
17224 | 86.36 | 141.59 | 12953.29 | -3618.08 | 2838.9 | 0.86 |  | 160.24 | 4598.9 | -0.81 |  | 0.29 | 93
17319 | 86.19 | 141.42 | 12959.46 | -3692.28 | 2897.91 | 0.25 |  | -135.07 | 4693.69 | -0.18 |  | -0.18 | 95
17414 | 85.99 | 141.83 | 12965.94 | -3766.58 | 2956.75 | 0.48 |  | 116.07 | 4788.47 | -0.21 |  | 0.43 | 95
17509 | 86.05 | 142.18 | 12972.53 | -3841.26 | 3015.09 | 0.37 |  | 80.26 | 4883.24 | 0.06 |  | 0.37 | 95
17602 | 86.19 | 142.17 | 12978.82 | -3914.55 | 3071.99 | 0.15 |  | -4.08 | 4976.03 | 0.15 |  | -0.01 | 93
17697 | 86.23 | 142.62 | 12985.1 | -3989.65 | 3129.83 | 0.47 |  | 84.92 | 5070.82 | 0.04 |  | 0.47 | 95
17792 | 86.25 | 143 | 12991.33 | -4065.17 | 3187.13 | 0.4 |  | 86.99 | 5165.6 | 0.02 |  | 0.4 | 95
17887 | 86.79 | 143.42 | 12997.1 | -4141.11 | 3243.92 | 0.72 |  | 37.84 | 5260.4 | 0.57 |  | 0.44 | 95
17981 | 88.02 | 143.54 | 13001.35 | -4216.57 | 3299.8 | 1.31 |  | 5.57 | 5354.26 | 1.31 |  | 0.13 | 94
18076 | 87.54 | 142.21 | 13005.03 | -4292.26 | 3357.1 | 1.49 |  | -109.88 | 5449.17 | -0.51 |  | -1.4 | 95
18170 | 87.93 | 141.53 | 13008.75 | -4366.14 | 3415.09 | 0.83 |  | -60.16 | 5543.1 | 0.41 |  | -0.72 | 94
18265 | 87.21 | 143.3 | 13012.78 | -4441.35 | 3472.98 | 2.01 |  | 112.19 | 5638.01 | -0.76 |  | 1.86 | 95
18361 | 86.01 | 142.36 | 13018.45 | -4517.72 | 3530.88 | 1.59 |  | -142 | 5733.82 | -1.25 |  | -0.98 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 122.54 | 22.22 | 80 | 325 | 360 | 6237.04 | 5400 | 140 | 287.78 | 217.22 | 184.44 | 14000 | 8000
Run | 127.98 | 23.03 | 80 | 325 | 360 | 6284.21 | 5400 | 150 | 279.74 | 218.03 | 186.05 | 14000 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/01/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/01/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/01/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 07/01/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 07/01/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 07/01/2021 |  | 18 |  | 1250 |  | 1 | 1250
Pro Azimuthal Gamma Ray Core charge >330F |  |  |  |  | 07/01/2021 |  | 19 |  | 12000 |  | 1 | 12000
Total | [11 empty] | 22700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/01/2021 | 00:00 | 00:35 | 0.58 | 16821 | 16916 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16821.00 t/16916.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 162.86, Diff 1000.00, Temp 331.00
07/01/2021 | 00:35 | 00:45 | 0.17 | 16916 | 16916 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 00:45 | 01:15 | 0.5 | 16916 | 17010 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/16916.00 t/17010.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 188.00, Diff 1000.00, Temp 331.00
07/01/2021 | 01:15 | 01:25 | 0.17 | 17010 | 17010 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 01:25 | 01:30 | 0.08 | 17010 | 17025 | 15 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17010.00 t/17025.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 180.00, Diff 1000.00, Temp 331.00
07/01/2021 | 01:30 | 01:55 | 0.42 | 17025 | 17037 | 12 | LAT | 4: BHA 4 | 2J | Slide Drill f/17025.00 t/17037.00, TF -150.00G, w/WOB 25.00,Flow 360.00, Press 6400.00, Tq 14000.00, ROP 28.80, Diff 1000.00, Temp 331.00
07/01/2021 | 01:55 | 02:20 | 0.42 | 17037 | 17105 | 68 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17037.00 t/17105.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 163.20, Diff 1000.00, Temp 331.00
07/01/2021 | 02:20 | 02:30 | 0.17 | 17105 | 17105 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 02:30 | 03:00 | 0.5 | 17105 | 17199 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17105.00 t/17199.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 188.00, Diff 1000.00, Temp 331.00
07/01/2021 | 03:00 | 03:10 | 0.17 | 17199 | 17199 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 03:10 | 03:15 | 0.08 | 17199 | 17210 | 11 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17199.00 t/17210.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 132.00, Diff 1000.00, Temp 331.00
07/01/2021 | 03:15 | 03:40 | 0.42 | 17210 | 17220 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/17210.00 t/17220.00, TF -160.00G, w/WOB 25.00,Flow 360.00, Press 6400.00, Tq 14000.00, ROP 24.00, Diff 1000.00, Temp 331.00
07/01/2021 | 03:40 | 04:10 | 0.5 | 17220 | 17292 | 72 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17220.00 t/17292.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 144.00, Diff 1000.00, Temp 331.00
07/01/2021 | 04:10 | 04:20 | 0.17 | 17292 | 17292 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 04:20 | 04:50 | 0.5 | 17292 | 17387 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17292.00 t/17387.00, w/WOB 25.00,Flow 360.00, RPM 80.00, Press 6400.00, Tq 14000.00, ROP 190.00, Diff 1000.00, Temp 334.00
07/01/2021 | 04:50 | 05:00 | 0.17 | 17387 | 17387 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 05:00 | 05:30 | 0.5 | 17387 | 17482 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17387.00 t/17482.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 190.00, Diff 800.00, Temp 336.00
07/01/2021 | 05:30 | 05:40 | 0.17 | 17482 | 17482 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 05:40 | 06:10 | 0.5 | 17482 | 17577 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17482.00 t/17577.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 190.00, Diff 800.00, Temp 336.00
07/01/2021 | 06:10 | 06:15 | 0.08 | 17577 | 17577 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 06:15 | 07:00 | 0.75 | 17577 | 17670 | 93 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17577.00 t/17670.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 124.00, Diff 800.00, Temp 336.00
07/01/2021 | 07:00 | 07:05 | 0.08 | 17670 | 17670 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 07:05 | 07:45 | 0.67 | 17670 | 17765 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17670.00 t/17765.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 142.50, Diff 800.00, Temp 338.00
07/01/2021 | 07:45 | 07:50 | 0.08 | 17765 | 17765 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 07:50 | 08:25 | 0.58 | 17765 | 17860 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17765.00 t/17860.00, w/WOB 21,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 162.86, Diff 800.00, Temp 338.00
07/01/2021 | 08:25 | 08:30 | 0.08 | 17860 | 17860 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 08:30 | 09:10 | 0.67 | 17860 | 17955 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17860.00 t/17955.00, w/WOB 21.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 142.50, Diff 800.00, Temp 340.00
07/01/2021 | 09:10 | 09:15 | 0.08 | 17955 | 17955 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 09:15 | 09:50 | 0.58 | 17955 | 18049 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17955.00 t/18049.00, w/WOB 21.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 161.14, Diff 800.00, Temp 338.00
07/01/2021 | 09:50 | 09:55 | 0.08 | 18049 | 18049 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 09:55 | 10:00 | 0.08 | 18049 | 18059 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18049.00 t/18059.00, w/WOB 21.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 120.00, Diff 800.00, Temp 338.00
07/01/2021 | 10:00 | 10:45 | 0.75 | 18059 | 18073 | 14 | LAT | 4: BHA 4 | 2J | Slide Drill f/18059.00 t/18073.00, TF -120.00G, w/WOB 25.00,Flow 360.00, Press 5700.00, Tq 0.00, ROP 18.67, Diff 300.00, Temp 331.00
07/01/2021 | 10:45 | 11:20 | 0.58 | 18073 | 18144 | 71 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18073.00 t/18144.00, w/WOB 21.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 121.71, Diff 800.00, Temp 333.00
07/01/2021 | 11:20 | 11:25 | 0.08 | 18144 | 18144 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 11:25 | 12:10 | 0.75 | 18144 | 18238 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18144.00 t/18238.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 125.33, Diff 800.00, Temp 334.00
07/01/2021 | 12:10 | 12:15 | 0.08 | 18238 | 18238 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 12:15 | 12:20 | 0.08 | 18238 | 18247 | 9 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18238.00 t/18247.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 108.00, Diff 800.00, Temp 334.00
07/01/2021 | 12:20 | 12:55 | 0.58 | 18247 | 18256 | 9 | LAT | 4: BHA 4 | 2J | Slide Drill f/18247.00 t/18256.00, TF 180.00G, w/WOB 20.00,Flow 360.00, Press 5700.00, Tq 0.00, ROP 15.43, Diff 300.00, Temp 331.00
07/01/2021 | 12:55 | 13:35 | 0.67 | 18256 | 18333 | 77 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18256.00 t/18333.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 115.50, Diff 800.00, Temp 332.00
07/01/2021 | 13:35 | 13:40 | 0.08 | 18333 | 18333 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
07/01/2021 | 13:40 | 13:45 | 0.08 | 18333 | 18343 | 10 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18333.00 t/18343.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 120.00, Diff 800.00, Temp 332.00
07/01/2021 | 13:45 | 14:20 | 0.58 | 18343 | 18355 | 12 | LAT | 4: BHA 4 | 2J | Slide Drill f/18343.00 t/18355.00, TF -110G, w/WOB 20.00,Flow 360.00, Press 6200.00, Tq 14000.00, ROP 20.57, Diff 800.00, Temp 332.00
07/01/2021 | 14:20 | 14:30 | 0.17 | 18355 | 18363 | 8 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18355.00 t/18363.00, w/WOB 20.00,Flow 360.00, RPM 80.00, Press 6200.00, Tq 14000.00, ROP 48.00, Diff 800.00, Temp 332.00
07/01/2021 | 14:30 | 17:00 | 2.5 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 5A | Circ to POOH f/ 800 psi increase in pump pressure while drilling
07/01/2021 | 17:00 | 24:00 | 7 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6B | POOH t/13364
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_2_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 17 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 07/02/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19650 |  |  | Well Cost($): |  | 198410
|  |  |  | 24hr Summary: |  | POOH, Change BHA, TIH
|  |  |  | 24hr Lookahead: |  | POOH & swap BHA
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18363 |  | 18363 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 56 | PV: | 23
End Depth (Usft): |  | 18363 |  | 18363 |  | OD (in): |  | 7.625 |  | 300: | 33 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 29.7 |  | 200: | 25 | Viscosity: | 48
Slide Drilled (Usft): | [9 empty] | 100: | 16 | Chlorides: | 53800
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.80
Drlg/Circ Hrs: |  | 0.00 / 1.33 |  | 0.00 / 1.33 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: | [5 empty] | SN: |  | 13594950 |  | 10s Gel: | 6 | Weight (ppg): | 11.8
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 331.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 10 |  | 10 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-WT-G-X-I-PN-PP
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 2.9
6/7 8.8 2.12 Slick HPT 0.023 |  |  |  | 5.5 | 2 |  |  |  |  | 32.99 |  | 35.89
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.16
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.15
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.2
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.74
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.31
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.33
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.71
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.37
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.82
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.81
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 23.65 |  | 2821.46
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5929.9
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5951.84
5951.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.96 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 127.98 | 23.03 | 80 | 325 | 360 | 6284.21 | 5400 | 150 | 279.74 | 218.03 | 186.05 | 14000 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/02/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/02/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/02/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 07/02/2021 |  | 14 |  | 2000 |  | 1 | 2000
5.5 Premium Motor Reline |  |  |  |  | 07/02/2021 |  | 9 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 07/02/2021 |  | 11 |  | 800 |  | 1 | 800
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 07/02/2021 |  | 15 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 19650
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/02/2021 | 00:00 | 01:30 | 1.5 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 5A | Circ
07/02/2021 | 01:30 | 02:30 | 1 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6B | POOH t/12318
07/02/2021 | 02:30 | 04:30 | 2 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 5A | Circ bottoms up
07/02/2021 | 04:30 | 05:00 | 0.5 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 5A | Spot mud cap
07/02/2021 | 05:00 | 07:00 | 2 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6B | POOH t/8347
07/02/2021 | 07:00 | 07:30 | 0.5 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6I | Flow check and pump slug
07/02/2021 | 07:30 | 08:30 | 1 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6B | POOH t/6362
07/02/2021 | 08:30 | 09:00 | 0.5 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 24A | Remove rotating head
07/02/2021 | 09:00 | 12:25 | 3.42 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6B | POOH
07/02/2021 | 12:25 | 13:05 | 0.67 | 18363 | 18363 | 0 | LAT | 4: BHA 4 | 6P | L/D BHA #4
07/02/2021 | 13:05 | 13:20 | 0.25 | 18363 | 18363 | 0 | LAT |  | 7B | Clean rig floor
07/02/2021 | 13:20 | 14:00 | 0.67 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6O | P/U BHA #5
07/02/2021 | 14:00 | 14:10 | 0.17 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 5A | Test MWD and motor
07/02/2021 | 14:10 | 15:15 | 1.08 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 2822
07/02/2021 | 15:15 | 15:30 | 0.25 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6L | P/U Agitator
07/02/2021 | 15:30 | 16:30 | 1 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 4988
07/02/2021 | 16:30 | 17:30 | 1 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 8P | Rig Service
07/02/2021 | 17:30 | 20:00 | 2.5 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 8200
07/02/2021 | 20:00 | 21:20 | 1.33 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 9A | Cut drill line
07/02/2021 | 21:20 | 22:20 | 1 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 10550
07/02/2021 | 22:20 | 23:30 | 1.17 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 5A | Circ bottoms up
07/02/2021 | 23:30 | 24:00 | 0.5 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 11000
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_3_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 18 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 07/03/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 22700 |  |  | Well Cost($): |  | 221110
24hr Summary:
|  |  |  | 24hr Lookahead: |  | TIH & continue drilling lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18363 |  | 18363 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 56 | PV: | 23
End Depth (Usft): |  | 18971 |  | 18971 |  | OD (in): |  | 7.625 |  | 300: | 33 | YP: | 10
Total Drilled (Usft): |  | 608 |  | 608 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 24 | Viscosity: | 51
Slide Drilled (Usft): |  | 22 |  | 22 | [5 empty] | 100: | 15 | Chlorides: | 53400
Rotary Drilled (Usft): |  | 586 |  | 586 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.30
Drlg/Circ Hrs: |  | 6.08 / 8.42 |  | 6.08 / 9.75 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 1 |  | 1 |  | SN: |  | 13509567 |  | 10s Gel: | 6 | Weight (ppg): | 11.7
Rotary Drilling Hrs: |  | 5.08 |  | 5.08 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 331.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 115.28 / 22.00 |  | 115.28 / 22.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 34 |  | Grade In: |  | New
% Slide: |  | 3.62 |  | 3.62 |  | Grade Out: |  | 0-1-WT-G-X-I-PN-BHA
% Rotary: |  | 96.38 |  | 96.38 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 2.9
6/7 8.8 2.12 Slick HPT 0.028 |  |  |  | 5.5 | 2 |  |  |  |  | 33.15 |  | 36.05
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.32
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.31
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.36
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.9
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.47
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.49
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.87
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.53
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.98
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.97
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 24.56 |  | 2822.53
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5930.97
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5952.91
5952.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250005 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18361 | 86.01 | 142.36 | 13018.45 | -4517.72 | 3530.88 | 1.59 |  | -142 | 5733.82 | -1.25 |  | -0.98 | 96
18455 | 86.09 | 142.07 | 13024.93 | -4591.83 | 3588.33 | 0.32 |  | -74.55 | 5827.6 | 0.09 |  | -0.31 | 94
18551 | 86.44 | 142.27 | 13031.18 | -4667.49 | 3647.09 | 0.42 |  | 29.7 | 5923.39 | 0.36 |  | 0.21 | 96
18644 | 86.28 | 142.72 | 13037.09 | -4741.12 | 3703.59 | 0.51 |  | 109.62 | 6016.2 | -0.17 |  | 0.48 | 93
18737 | 86.3 | 141.03 | 13043.11 | -4814.12 | 3760.89 | 1.81 |  | -89.38 | 6109 | 0.02 |  | -1.82 | 93
18832 | 88.48 | 140.8 | 13047.43 | -4887.78 | 3820.72 | 2.31 |  | -6.02 | 6203.88 | 2.29 |  | -0.24 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 99.95 | 21.91 | 77.78 | 316 | 350.45 | 6036.36 | 5409.09 | 0 | 310 | 220 | 160 | 12222.22 | 0
Run | 99.95 | 21.91 | 77.78 | 316 | 350.45 | 6036.36 | 5409.09 | 150 | 310 | 220 | 160 | 12222.22 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/03/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/03/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/03/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 07/03/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 07/03/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray Core charge >330F |  |  |  |  | 07/03/2021 |  | 19 |  | 12000 |  | 1 | 12000
MWD hot hole charge |  |  |  |  | 07/03/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 22700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/03/2021 | 00:00 | 00:45 | 0.75 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 12478
07/03/2021 | 00:45 | 02:30 | 1.75 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 5A | Circ bottoms up
07/03/2021 | 02:30 | 04:40 | 2.17 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 16000
07/03/2021 | 04:40 | 04:50 | 0.17 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 5A | Fill pipe & break circulation
07/03/2021 | 04:50 | 05:30 | 0.67 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 3C | W/R f/ 15989 t/ 16367
07/03/2021 | 05:30 | 06:25 | 0.92 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 6A | TIH t/ 18334
07/03/2021 | 06:25 | 06:35 | 0.17 | 18363 | 18363 | 0 | LAT | 5: BHA 5 | 3C | W/R f/ 18334 t/ 18363
07/03/2021 | 06:35 | 07:00 | 0.42 | 18363 | 18429 | 66 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18363.00 t/18429.00, w/WOB 28.00,Flow 355, RPM 80.00, Press 6300.00, Tq 13800.00, ROP 158.40, Diff 600.00, Temp 330.00
07/03/2021 | 07:00 | 07:05 | 0.08 | 18429 | 18429 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/03/2021 | 07:05 | 07:40 | 0.58 | 18429 | 18523 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18429.00 t/18523.00, w/WOB 25.00,Flow 350, RPM 80.00, Press 6100.00, Tq 13200.00, ROP 161.14, Diff 700.00, Temp 331.00
07/03/2021 | 07:40 | 07:45 | 0.08 | 18523 | 18523 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/03/2021 | 07:45 | 08:35 | 0.83 | 18523 | 18619 | 96 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18523.00 t/18619.00, w/WOB 20.00,Flow 350, RPM 80.00, Press 6000.00, Tq 12500.00, ROP 115.20, Diff 700.00, Temp 336.00
07/03/2021 | 08:35 | 08:40 | 0.08 | 18619 | 18619 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/03/2021 | 08:40 | 09:25 | 0.75 | 18619 | 18712 | 93 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18619.00 t/18712.00, w/WOB 21.00,Flow 350.00, RPM 80.00, Press 6100.00, Tq 11300.00, ROP 124.00, Diff 750.00, Temp 338.00
07/03/2021 | 09:25 | 09:30 | 0.08 | 18712 | 18712 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/03/2021 | 09:30 | 09:35 | 0.08 | 18712 | 18722 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18712.00 t/18722.00, w/WOB 15.00,Flow 350.00, RPM 80.00, Press 6100.00, Tq 11000.00, ROP 120.00, Diff 750.00, Temp 338.00
07/03/2021 | 09:35 | 10:10 | 0.58 | 18722 | 18734 | 12 | LAT | 5: BHA 5 | 2J | Slide Drill f/18722.00 t/18734.00, TF -70.00G, w/WOB 25.00,Flow 350.00, Press 5700.00, Tq 0.00, ROP 20.57, Diff 350.00, Temp 336.00
07/03/2021 | 10:10 | 10:45 | 0.58 | 18734 | 18805 | 71 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18734.00 t/18805.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 6100.00, Tq 11500.00, ROP 121.71, Diff 750.00, Temp 340.00
07/03/2021 | 10:45 | 10:50 | 0.08 | 18805 | 18805 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/03/2021 | 10:50 | 10:55 | 0.08 | 18805 | 18812 | 7 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18805.00 t/18812.00, w/WOB 18,Flow 350.00, RPM 70, Press 6100.00, Tq 11500.00, ROP 84.00, Diff 650.00, Temp 340.00
07/03/2021 | 10:55 | 11:20 | 0.42 | 18812 | 18822 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/18812.00 t/18822.00, TF 0G, w/WOB 25,Flow 350.00, Press 5700, Tq 0, ROP 24.00, Diff 250.00, Temp 338.00
07/03/2021 | 11:20 | 12:00 | 0.67 | 18822 | 18900 | 78 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18822.00 t/18900.00, w/WOB 22,Flow 350, RPM 70, Press 6100.00, Tq 12600, ROP 117.00, Diff 700.00, Temp 342.00
07/03/2021 | 12:00 | 12:05 | 0.08 | 18900 | 18900 | 0 | LAT | 5: BHA 5 | 5A | Survey & Connection
07/03/2021 | 12:05 | 13:10 | 1.08 | 18900 | 18971 | 71 | LAT | 5: BHA 5 | 2K | Rotary Drill f/18900.00 t/18971.00, w/WOB 22.00,Flow 350.00, RPM 80, Press 6100.00, Tq 12600.00, ROP 65.54, Diff 700.00, Temp 342.00
07/03/2021 | 13:10 | 15:50 | 2.67 | 18971 | 18971 | 0 | LAT | 5: BHA 5 | 5A | Circulate t/ POOH f/ motor. Observed what appeared to be stator rubber coming over shakers. ROP fell off to 0 along with differential pressure while drilling
07/03/2021 | 15:50 | 19:30 | 3.67 | 18971 | 18971 | 0 | LAT | 5: BHA 5 | 6B | POOH t/ change motor
07/03/2021 | 19:30 | 22:00 | 2.5 | 18971 | 18971 | 0 | LAT | 5: BHA 5 | 5A | Circ bottoms up & spot mud cap
07/03/2021 | 22:00 | 24:00 | 2 | 18971 | 18971 | 0 | LAT | 5: BHA 5 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_4_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 19 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 07/04/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 20900 |  |  | Well Cost($): |  | 242010
|  |  |  | 24hr Summary: |  | Trip pipe and change BHA
|  |  |  | 24hr Lookahead: |  | Change out BHA & TIH
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18971 |  | 18971 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 57 | PV: | 23
End Depth (Usft): |  | 18971 |  | 18971 |  | OD (in): |  | 7.625 |  | 300: | 34 | YP: | 11
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 29.7 |  | 200: | 24 | Viscosity: | 51
Slide Drilled (Usft): | [9 empty] | 100: | 16 | Chlorides: | 52000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.30
Drlg/Circ Hrs: |  | 0.00 / 3.92 |  | 0.00 / 3.92 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: | [5 empty] | SN: |  | 13509567 |  | 10s Gel: | 6 | Weight (ppg): | 11.7
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 336.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 14.67 |  | 14.67 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 0-1-WT-G-X-I-PN-BHA
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 2.9
6/7 8.8 2.12 Slick HPT 0.028 |  |  |  | 5.5 | 2 |  |  |  |  | 33.15 |  | 36.05
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.32
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.31
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.36
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 88.9
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.47
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.49
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 140.87
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.53
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 338.98
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2797.97
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 24.56 |  | 2822.53
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5930.97
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5952.91
5952.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250005 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 21.91 | 77.78 | 341 | 350.45 | 6036.36 | 5409.09 | 0 | 310 | 220 | 160 | 12222.22 | 0
Run | 99.95 | 21.91 | 77.78 | 341 | 350.45 | 6036.36 | 5409.09 | 150 | 310 | 220 | 160 | 12222.22 | 6000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/04/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/04/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/04/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 07/04/2021 |  | 14 |  | 2000 |  | 1 | 2000
MWD hot hole charge |  |  |  |  | 07/04/2021 |  | 18 |  | 1250 |  | 1 | 1250
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 07/04/2021 |  | 15 |  | 1000 |  | 1 | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 07/04/2021 |  | 12 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 07/04/2021 |  | 11 |  | 800 |  | 1 | 800
Total | [11 empty] | 20900
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/04/2021 | 00:00 | 07:30 | 7.5 | 18971 | 18971 | 0 | LAT | 5: BHA 5 | 6B | POOH
07/04/2021 | 07:30 | 08:00 | 0.5 | 18971 | 18971 | 0 | LAT | 5: BHA 5 | 6P | L/D BHA #5
07/04/2021 | 08:00 | 08:30 | 0.5 | 18971 | 18971 | 0 | LAT |  | 7B | Clean rig floor
07/04/2021 | 08:30 | 09:20 | 0.83 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 6O | M/U BHA #6
07/04/2021 | 09:20 | 09:35 | 0.25 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 5A | Test MWD and motor
07/04/2021 | 09:35 | 17:00 | 7.42 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 6A | TIH t/10677
07/04/2021 | 17:00 | 19:15 | 2.25 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 5A | Circ
07/04/2021 | 19:15 | 20:05 | 0.83 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 6A | TIH t/12605
07/04/2021 | 20:05 | 21:30 | 1.42 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 5A | Circ
07/04/2021 | 21:30 | 24:00 | 2.5 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 6A | TIH t/17768
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_5_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 20 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 07/05/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 86700 |  |  | Well Cost($): |  | 328710
|  |  |  | 24hr Summary: |  | Drill ahead to TD, Cric, POOH
|  |  |  | 24hr Lookahead: |  | LDDP, L/D tools
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18971 |  | 18971 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 57 | PV: | 23
End Depth (Usft): |  | 20437 |  | 20437 |  | OD (in): |  | 7.625 |  | 300: | 34 | YP: | 11
Total Drilled (Usft): |  | 1466 |  | 1466 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 24 | Viscosity: | 51
Slide Drilled (Usft): |  | 30 |  | 30 | [5 empty] | 100: | 16 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 1436 |  | 1436 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.30
Drlg/Circ Hrs: |  | 14.58 / 6.92 |  | 14.58 / 10.83 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 1.42 |  | 1.42 |  | SN: |  | 13564680 |  | 10s Gel: | 6 | Weight (ppg): | 11.7
Rotary Drilling Hrs: |  | 13.17 |  | 13.17 |  | Bit # |  | 6 |  | PH / Temp(F) | 0.0 / 336.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 109.06 / 21.18 |  | 109.06 / 21.18 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 38.67 |  | Grade In: |  | New
% Slide: |  | 2.05 |  | 2.05 |  | Grade Out: |  | 0-1-LT-S-X-I-NO-TD
% Rotary: |  | 97.95 |  | 97.95 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5/6 9.5 1.80 adj 5 3/8 stab |  |  |  | 5 | 2 |  |  |  |  | 31.22 |  | 31.97
Crossover Sub |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.36 |  | 34.33
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 36.48
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.75
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.74
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.79
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 89.33
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.9
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.92
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 141.3
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.96
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 339.41
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2798.4
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 24.56 |  | 2822.96
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5931.4
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5953.34
5953.34
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
14954251 |  | Baker Hughes |  | 5/6 9.5 |  | 5/6 | 4.32 |  | 1.8 |  | 0.75 |  | ADJ
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18926 | 89.25 | 141.49 | 13049.29 | -4960.97 | 3879.68 | 1.1 |  | 41.87 | 6297.85 | 0.82 |  | 0.73 | 94
19021 | 90.19 | 141.03 | 13049.76 | -5035.07 | 3939.12 | 1.1 |  | -26.08 | 6392.85 | 0.99 |  | -0.48 | 95
19114 | 89.27 | 140.9 | 13050.2 | -5107.3 | 3997.69 | 1 |  | -171.96 | 6485.83 | -0.99 |  | -0.14 | 93
19208 | 89.45 | 140.47 | 13051.25 | -5180.02 | 4057.25 | 0.5 |  | -67.29 | 6579.81 | 0.19 |  | -0.46 | 94
19301 | 87.61 | 139.94 | 13053.63 | -5251.45 | 4116.75 | 2.06 |  | -163.94 | 6672.73 | -1.98 |  | -0.57 | 93
19394 | 87.18 | 141.01 | 13057.86 | -5323.11 | 4175.87 | 1.24 |  | 111.94 | 6765.61 | -0.46 |  | 1.15 | 93
19488 | 87.63 | 141.5 | 13062.11 | -5396.35 | 4234.64 | 0.71 |  | 47.42 | 6859.5 | 0.48 |  | 0.52 | 94
19583 | 87.9 | 142.24 | 13065.82 | -5471.02 | 4293.26 | 0.83 |  | 69.96 | 6954.43 | 0.28 |  | 0.78 | 95
19677 | 88.21 | 142.54 | 13069.01 | -5545.44 | 4350.59 | 0.46 |  | 44.05 | 7048.37 | 0.33 |  | 0.32 | 94
19773 | 88.42 | 143.23 | 13071.83 | -5621.96 | 4408.49 | 0.75 |  | 73.08 | 7144.32 | 0.22 |  | 0.72 | 96
19868 | 86.89 | 142.85 | 13075.72 | -5697.81 | 4465.56 | 1.66 |  | -166.07 | 7239.21 | -1.61 |  | -0.4 | 95
19963 | 87.69 | 143.74 | 13080.21 | -5773.88 | 4522.28 | 1.26 |  | 48.04 | 7334.08 | 0.84 |  | 0.94 | 95
20057 | 87.85 | 143.78 | 13083.87 | -5849.64 | 4577.81 | 0.18 |  | 14.03 | 7427.95 | 0.17 |  | 0.04 | 94
20152 | 87.94 | 144.04 | 13087.36 | -5926.36 | 4633.73 | 0.29 |  | 70.9 | 7522.83 | 0.09 |  | 0.27 | 95
20246 | 87.88 | 143.83 | 13090.79 | -6002.29 | 4689.03 | 0.23 |  | -105.96 | 7616.71 | -0.06 |  | -0.22 | 94
20340 | 87.84 | 143.53 | 13094.3 | -6077.98 | 4744.67 | 0.32 |  | -97.61 | 7710.59 | -0.04 |  | -0.32 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 100.53 | 18.18 | 70.5 | 313 | 323.18 | 5277.27 | 4688.64 | 130 | 297.27 | 226.36 | 165 | 12220 | 8000
Run | 100.53 | 18.18 | 70.5 | 313 | 323.18 | 5277.27 | 4688.64 | 130 | 297.27 | 226.36 | 165 | 12220 | 8000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 07/05/2021 |  | 14 |  | 2000 |  | 1 | 2000
MWD hot hole charge |  |  |  |  | 07/05/2021 |  | 18 |  | 1250 |  | 1 | 1250
Pro Azimuthal Gamma Ray Core charge >330F |  |  |  |  | 07/05/2021 |  | 19 |  | 12000 |  | 1 | 12000
Real Time Survey Management |  |  |  |  | 07/05/2021 |  | 10 |  | 600 |  | 1 | 600
MWD Core Charge >347 |  |  |  |  | 07/05/2021 |  | 25 |  | 64000 |  | 1 | 64000
Dir & MWD /Gamma |  |  |  |  | 07/05/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/05/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/05/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 86700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/05/2021 | 00:00 | 00:30 | 0.5 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 6A | TIH t/ 18713
07/05/2021 | 00:30 | 01:30 | 1 | 18971 | 18971 | 0 | LAT | 6: BHA 6 | 3C | Wash to bottom
07/05/2021 | 01:30 | 01:55 | 0.42 | 18971 | 18995 | 24 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18971.00 t/18995.00, w/WOB 6.00,Flow 340.00, RPM 80.00, Press 5200.00, Tq 11000.00, ROP 57.60, Diff 250.00, Temp 340.00
07/05/2021 | 01:55 | 02:05 | 0.17 | 18995 | 18995 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 02:05 | 03:15 | 1.17 | 18995 | 19090 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/18995.00 t/19090.00, w/WOB 6.00,Flow 300.00, RPM 70.00, Press 4850.00, Tq 11000.00, ROP 81.43, Diff 500.00, Temp 342.00
07/05/2021 | 03:15 | 03:20 | 0.08 | 19090 | 19090 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 03:20 | 03:35 | 0.25 | 19090 | 19102 | 12 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19090.00 t/19102.00, w/WOB 6.00,Flow 300.00, RPM 70.00, Press 4850.00, Tq 11000.00, ROP 48.00, Diff 500.00, Temp 342.00
07/05/2021 | 03:35 | 04:25 | 0.83 | 19102 | 19117 | 15 | LAT | 6: BHA 6 | 2J | Slide Drill f/19102.00 t/19117.00, TF -160.00G, w/WOB 6.00,Flow 350.00, Press 5600.00, Tq 11000.00, ROP 18.00, Diff 200.00, Temp 342.00
07/05/2021 | 04:25 | 05:25 | 1 | 19117 | 19183 | 66 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19117.00 t/19183.00, w/WOB 15,Flow 300.00, RPM 70.00, Press 4850.00, Tq 11000.00, ROP 66.00, Diff 500.00, Temp 343.00
07/05/2021 | 05:25 | 05:30 | 0.08 | 19183 | 19183 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 05:30 | 06:45 | 1.25 | 19183 | 19277 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19183.00 t/19277.00, w/WOB 15,Flow 300.00, RPM 70.00, Press 4850.00, Tq 11000.00, ROP 75.20, Diff 500.00, Temp 345.00
07/05/2021 | 06:45 | 06:50 | 0.08 | 19277 | 19277 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 06:50 | 06:55 | 0.08 | 19277 | 19285 | 8 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19277.00 t/19285.00, w/WOB 15.00,Flow 300.00, RPM 70.00, Press 4850.00, Tq 11000.00, ROP 96.00, Diff 500.00, Temp 345.00
07/05/2021 | 06:55 | 07:30 | 0.58 | 19285 | 19300 | 15 | LAT | 6: BHA 6 | 2J | Slide Drill f/19285.00 t/19300.00, TF 180.00G, w/WOB 20.00,Flow 330.00, Press 5100.00, Tq 0.00, ROP 25.71, Diff 350.00, Temp 343.00
07/05/2021 | 07:30 | 08:05 | 0.58 | 19300 | 19370 | 70 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19300.00 t/19370.00, w/WOB 23.00,Flow 330.00, RPM 70.00, Press 5450.00, Tq 13500.00, ROP 120.00, Diff 700.00, Temp 345.00
07/05/2021 | 08:05 | 08:10 | 0.08 | 19370 | 19370 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 08:10 | 09:00 | 0.83 | 19370 | 19463 | 93 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19370.00 t/19463.00, w/WOB 25.00,Flow 330.00, RPM 70.00, Press 5450.00, Tq 12500.00, ROP 111.60, Diff 700.00, Temp 349.00
07/05/2021 | 09:00 | 09:05 | 0.08 | 19463 | 19463 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 09:05 | 09:50 | 0.75 | 19463 | 19463 | 0 | LAT | 6: BHA 6 | 5A | Circulate to reduce bottom hole temp. dropped from 349 down to 342
07/05/2021 | 09:50 | 10:45 | 0.92 | 19463 | 19557 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19463.00 t/19557.00, w/WOB 23,Flow 300, RPM 70.00, Press 4500, Tq 12500.00, ROP 102.55, Diff 600.00, Temp 347.00
07/05/2021 | 10:45 | 10:50 | 0.08 | 19557 | 19557 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 10:50 | 11:50 | 1 | 19557 | 19652 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19557.00 t/19652.00, w/WOB 22.00,Flow 330.00, RPM 70.00, Press 5450, Tq 12500.00, ROP 95.00, Diff 650.00, Temp 347.00
07/05/2021 | 11:50 | 11:55 | 0.08 | 19652 | 19652 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 11:55 | 12:40 | 0.75 | 19652 | 19746 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19652.00 t/19746.00, w/WOB 24.00,Flow 330.00, RPM 70.00, Press 5450, Tq 12500.00, ROP 125.33, Diff 700.00, Temp 349.00
07/05/2021 | 12:40 | 12:45 | 0.08 | 19746 | 19746 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 12:45 | 13:00 | 0.25 | 19746 | 19776 | 30 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19746.00 t/19776.00, w/WOB 23.00,Flow 330.00, RPM 70.00, Press 5450.00, Tq 12500.00, ROP 120.00, Diff 700.00, Temp 349.00
07/05/2021 | 13:00 | 13:35 | 0.58 | 19776 | 19776 | 0 | LAT | 6: BHA 6 | 5A | Circulate to reduce bottom hole temp. dropped from 349 down to 343
07/05/2021 | 13:35 | 14:00 | 0.42 | 19776 | 19842 | 66 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19776.00 t/19842.00, w/WOB 24.00,Flow 330.00, RPM 70.00, Press 5450.00, Tq 12500.00, ROP 158.40, Diff 700.00, Temp 347.00
07/05/2021 | 14:00 | 14:05 | 0.08 | 19842 | 19842 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 14:05 | 14:55 | 0.83 | 19842 | 19937 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19842.00 t/19937.00, w/WOB 20.00,Flow 330.00, RPM 70.00, Press 5450.00, Tq 12500.00, ROP 114.00, Diff 700.00, Temp 349.00
07/05/2021 | 14:55 | 15:00 | 0.08 | 19937 | 19937 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 15:00 | 15:40 | 0.67 | 19937 | 20032 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/19937.00 t/20032.00, w/WOB 25.00,Flow 330.00, RPM 70.00, Press 5450.00, Tq 12500.00, ROP 142.50, Diff 700.00, Temp 349.00
07/05/2021 | 15:40 | 15:45 | 0.08 | 20032 | 20032 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 15:45 | 16:20 | 0.58 | 20032 | 20126 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/20032.00 t/20126.00, w/WOB 22,Flow 330.00, RPM 70.00, Press 5450.00, Tq 12500.00, ROP 161.14, Diff 700.00, Temp 350.00
07/05/2021 | 16:20 | 16:25 | 0.08 | 20126 | 20126 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 16:25 | 17:00 | 0.58 | 20126 | 20221 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/20126.00 t/20221.00, w/WOB 20,Flow 330.00, RPM 70.00, Press 5600, Tq 13100, ROP 162.86, Diff 700.00, Temp 351.00
07/05/2021 | 17:00 | 17:05 | 0.08 | 20221 | 20221 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 17:05 | 17:45 | 0.67 | 20221 | 20315 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/20221.00 t/20315.00, w/WOB 20.00,Flow 330.00, RPM 70.00, Press 5600.00, Tq 13100.00, ROP 141.00, Diff 700.00, Temp 351.00
07/05/2021 | 17:45 | 17:50 | 0.08 | 20315 | 20315 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 17:50 | 18:30 | 0.67 | 20315 | 20409 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/20315.00 t/20409.00, w/WOB 20.00,Flow 330.00, RPM 70.00, Press 5600.00, Tq 13100.00, ROP 141.00, Diff 700.00, Temp 351.00
07/05/2021 | 18:30 | 18:35 | 0.08 | 20409 | 20409 | 0 | LAT | 6: BHA 6 | 5A | Survey & Connection
07/05/2021 | 18:35 | 18:50 | 0.25 | 20409 | 20437 | 28 | LAT | 6: BHA 6 | 2K | Rotary Drill f/20409.00 t/20437.00, w/WOB 20.00,Flow 330.00, RPM 70.00, Press 5600.00, Tq 13100.00, ROP 112.00, Diff 700.00, Temp 351.00
07/05/2021 | 18:50 | 18:55 | 0.08 | 20437 | 20437 | 0 | LAT | 6: BHA 6 | 5A | Survey @ TD
07/05/2021 | 18:55 | 22:00 | 3.08 | 20437 | 20437 | 0 | LAT | 6: BHA 6 | 5A | Circulate @ TD
07/05/2021 | 22:00 | 24:00 | 2 | 20437 | 20437 | 0 | LAT | 6: BHA 6 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_6_2021_DDR
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33522 / 21DD0111MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 21 |  |  | Well: |  | Ozark 1H
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Longitude: |  | 96° 42' 7.171" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 07/06/2021 |  |  | Report Time: |  | 00:00-18:00
|  |  |  | Daily Cost($): |  | 8850 |  |  | Well Cost($): |  | 337560
|  |  |  | 24hr Summary: |  | POOH. LDDP, LD tools, PIYAH!!
|  |  |  | 24hr Lookahead: |  | Released from location, PIYAH!!
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 20437 |  | 18971 |  | Csg Shoe MD(Usft): |  | 12238 |  | 600: | 57 | PV: | 23
End Depth (Usft): |  | 20437 |  | 20437 |  | OD (in): |  | 7.625 |  | 300: | 34 | YP: | 11
Total Drilled (Usft): |  |  |  | 1466 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 24 | Viscosity: | 51
Slide Drilled (Usft): |  |  |  | 30 | [5 empty] | 100: | 16 | Chlorides: | 52000
Rotary Drilled (Usft): |  |  |  | 1436 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 17.30
Drlg/Circ Hrs: |  |  |  | 14.58 / 10.83 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 74/26
Slide Drilling Hrs: |  |  |  | 1.42 |  | SN: |  | 13564680 |  | 10s Gel: | 6 | Weight (ppg): | 11.7
Rotary Drilling Hrs: |  |  |  | 13.17 |  | Bit # |  | 6 |  | PH / Temp(F) | 0.0 / 336.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 109.06 / 21.18 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 18 |  | 56.67 |  | Grade In: |  | New
% Slide: |  |  |  | 2.05 |  | Grade Out: |  | 0-1-LT-S-X-I-NO-TD
% Rotary: |  |  |  | 97.95 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | ChrisMark |  | BillTrey |  | Bobby Lewis
James Dyer |  | Xavier Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
5/6 9.5 1.80 adj 5 3/8 stab |  |  |  | 5 | 2 |  |  |  |  | 31.22 |  | 31.97
Crossover Sub |  |  |  | 4.875 | 2.5 |  |  |  |  | 2.36 |  | 34.33
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.15 |  | 36.48
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.27 |  | 45.75
UBHO |  |  |  | 5.125 | 2.5 |  |  |  |  | 3.99 |  | 49.74
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.05 |  | 79.79
Pony Collar (NO HARDBANDING) |  |  |  | 5 | 2.75 |  |  |  |  | 9.54 |  | 89.33
Drill Collar (NO HARDBANDING) |  |  |  | 4.875 | 2.688 |  |  |  |  | 30.57 |  | 119.9
Tomax |  |  |  | 4.875 | 2.5 |  |  |  |  | 18.02 |  | 137.92
Crossover Sub |  |  |  | 5.188 | 2.688 |  |  |  |  | 3.38 |  | 141.3
2 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 189.66 |  | 330.96
6 13/16 Drill-N-Ream |  |  |  | 5.25 | 2.5 |  |  |  |  | 8.45 |  | 339.41
26 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 2458.99 |  | 2798.4
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 24.56 |  | 2822.96
33 Stands 4.5 Drill Pipe |  |  |  | 4.5 | 3.5 |  |  |  |  | 3108.44 |  | 5931.4
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 21.94 |  | 5953.34
5953.34
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
14954251 |  | Baker Hughes |  | 5/6 9.5 |  | 5/6 | 4.32 |  | 1.8 |  | 0.75 |  | ADJ
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 313 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 8000
Run | 100.53 | 18.18 | 70.5 | 313 | 323.18 | 5277.27 | 4688.64 | 130 | 297.27 | 226.36 | 165 | 12220 | 8000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7200 |  | 0.0630 / 2.6460
Comments
12855 TVD at 0 VS with 88.3 INC 5A/10B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/06/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/06/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/06/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 07/06/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 8850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/06/2021 | 00:00 | 08:00 | 8 | 20437 | 20437 | 0 | LAT | 6: BHA 6 | 6B | POOH t/ 8400
07/06/2021 | 08:00 | 16:00 | 8 | 20437 | 20437 | 0 | LAT | 6: BHA 6 | 6K | LDDP
07/06/2021 | 16:00 | 18:00 | 2 | 20437 | 20437 | 0 | LAT | 6: BHA 6 | 6P | L/D BHA #6
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 392.54 (Usft)
Well: |  |  | Ozark 1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1126621 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/18/2021 | Depth In: |  | 108 | Total Drilled: |  | 3737.00 (Usft)
Date Out: |  |  | 06/19/2021 | Depth Out: |  | 3845 | Drilling / Circ Hours: |  | 10.28 / 2.33
Survey Offset: |  |  | 0
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 43518 | U616S | 13.5 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800053 | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 | 8 |  | 8.000 / 1.88 | 6 5/8 REG / 6 5/8 REG |  | 37.48 | 38.98
| 3 | SD610222 | Nortrak Stabilizer (BFF) 13" | 8.125 | 2.875 | 8.125 / 2.88 | 6 5/8 REG / 6 5/8 REG |  | 7.63 | 46.61
| 4 | SD40153 | Pony Collar (NO HARDBANDING) | 8 | 3.375 |  | 6 5/8 REG / 6 5/8 REG |  | 7.93 | 54.54
| 5 | ZSB775192 | UBHO | 7.75 | 3 |  | 6 5/8 REG / 6 5/8 REG |  | 3.72 | 58.26
| 6 | SD47865 | Drill Collar (NO HARDBANDING) | 8 | 3.375 |  | 6 5/8 REG / 6 5/8 REG |  | 28.77 | 87.03
| 7 | SD55256 | Drill Collar (NO HARDBANDING) | 8 | 3.375 |  | 6 5/8 REG / 6 5/8 REG |  | 28.41 | 115.44
| 8 | SD104164 | Crossover Sub | 8.25 | 2.875 | 6.875 / 1.44 | 4 1/2 IF / 6 5/8 REG |  | 2.56 | 118
| 9 | Rig | HWDP 9 Jts | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 274.54 | 392.54
| 10 | [8 empty] | 392.54
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | SPL616 |  |  | 3737
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 |  |  | PDCI / 7/8 5.9 | 5.78 / 1.50 |  | 13 | 8.5 | 175 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22000 |  |  | 800 | 100 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PVFluid | HPO |  | 0.012
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 | 13 |  | 0 |  |  | 3.67
3 |  |  | Nortrak Stabilizer (BFF) 13" | 13 |  | 0 |  |  | 41.37

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2664.11 (Usft)
Well: |  |  | Ozark 1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1126621 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/20/2021 | Depth In: |  | 3845 | Total Drilled: |  | 8405.00 (Usft)
Date Out: |  |  | 06/24/2021 | Depth Out: |  | 12250 | Drilling / Circ Hours: |  | 44.00 / 5.33
Survey Offset: |  |  | 63 | Gamma Offset: |  | 53
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 54861 | SPL613 | 9.875 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800059 | 7/8 Lobe 5.9 Slick 2.0F HPO -.017 | 8 |  | 8.125 / 2.88 | 6 5/8 REG / 6 5/8 REG |  | 37.46 | 38.96
| 3 | SD40153 | Pony Collar (NO HARDBANDING) | 8 | 3.375 |  | 6 5/8 REG / 6 5/8 REG |  | 7.93 | 46.89
| 4 | ZSB775192 | UBHO | 7.75 | 3 |  | 6 5/8 REG / 6 5/8 REG |  | 3.72 | 50.61
| 5 | SD47865 | Drill Collar (NO HARDBANDING) | 8 | 3.375 |  | 6 5/8 REG / 6 5/8 REG |  | 28.77 | 79.38
| 6 | SD55256 | Drill Collar (NO HARDBANDING) | 8 | 3.375 |  | 6 5/8 REG / 6 5/8 REG |  | 28.41 | 107.79
| 7 | SD115530 | Crossover Sub | 6.5 | 3 | 6.500 / 2.03 | 4 1/2 XH / 6 5/8 REG |  | 2.7 | 110.49
| 8 | SD104164 | 2 Stds 6.5 in DC | 6.5 | 2.75 | 6.375 / 3.50 | 4 1/2 XH / 4 1/2 XH |  | 185.82 | 296.31
| 9 | SD115076 | Crossover Sub | 6.125 | 2.75 | 6.125 | 4 1/2 IF / 4 1/2 XH |  | 2.36 | 298.67
| 10 | Rig | HWDP 9 Jts | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 274.54 | 573.21
| 11 |  | 22 Stds 5 in DP | 5 | 4.276 |  | 4 1/2 IF |  | 2066.2 | 2639.41
| 12 | PG675 | Agitator | 6.75 | 3.75 | 6.750 | 4 1/2 IF / 4 1/2 IF |  | 24.7 | 2664.11
| 13 | [8 empty] | 2664.11
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 0-1-WT-G-X-I-CT-TD | 8405
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  | PDCI / 7/8 5.9 | 6.04 / 2.00 |  | 8 | 8.25 | 250 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 100 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.017
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5951.98 (Usft)
Well: |  |  | Ozark 1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1126621 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/26/2021 | Depth In: |  | 12250 | Total Drilled: |  | 3980.00 (Usft)
Date Out: |  |  | 06/29/2021 | Depth Out: |  | 16230 | Drilling / Circ Hours: |  | 38.58 / 12.75
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13601236 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250010 | 6/7 8.8 2.12 Slick HS88 0.003 | 5.5 | 2 | 4.875 / 1.98 | XT39 / 3 1/2 REG |  | 33.13 | 33.88
| 3 | RIG | BTI | 4.812 | 2.5 |  | XT39 / XT39 |  | 2.03 | 35.91
| 4 | GT50-10-585 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.27 | 45.18
| 5 | ZSB500049 | UBHO | 5.125 | 2.5 |  | XT 39 / XT 39 |  | 3.99 | 49.17
| 6 | SD55911 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.05 | 79.22
| 7 | SD56679 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.54 | 88.76
| 8 | SD56632 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.57 | 119.33
| 9 | A52107 | Tomax | 4.875 | 2.5 | 4.875 | 4 XT39 / 4 XT39 |  | 18.02 | 137.35
| 10 | GT52331429 | Crossover Sub | 5.188 | 2.688 |  | CET43 / XT39 |  | 3.38 | 140.73
| 11 | Rig1 | 2 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 189.66 | 330.39
| 12 | 520 | 6 13/16 Drill-N-Ream | 5.25 | 2.5 |  | CET-43 / CET-43 |  | 8.45 | 338.84
| 13 | Rig2 | 26 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 2458.99 | 2797.83
| 14 | PG525-0051 | Agitator | 5.25 | 2.75 | 5.250 / 1.79 | CET-43 / CET-43 |  | 23.77 | 2821.6
| 15 | Rig3 | 33 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 3108.44 | 5930.04
| 16 | PG525-0049 | Agitator | 5.25 | 2.75 | 5.250 / 2.32 | CET-43 / CET-43 |  | 21.94 | 5951.98
| 17 | [8 empty] | 5951.98
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 0-1-WT-A-X-I-NO-BHA | 3980
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 Slick HS88 0.003 |  |  | PDCI / 6/7 8.8 | 4.05 / 2.12 |  | 0 | 5.5 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1100 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV | HS88 |  | 0.003
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.165 | PDCI | UBHO | 2.68
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6232 |  |  |  | 7462 / 9009 |  | 1338 | 1180
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
3122/ AZ4000 |  |  |  | 0.6 |  |  |  |  | Yes
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5951.84 (Usft)
Well: |  |  | Ozark 1H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1126621 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/30/2021 | Depth In: |  | 16230 | Total Drilled: |  | 2133.00 (Usft)
Date Out: |  |  | 07/02/2021 | Depth Out: |  | 18363 | Drilling / Circ Hours: |  | 16.67 / 14.08
Survey Offset: |  |  | 0
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13594950 | GTD64M | 6.75 | 2 |  | XT39 |  | 0.75 | 0.75
| 2 | 306842 | BTI | 4.812 | 2.5 |  | XT39 / XT39 |  | 2.15 | 2.9
| 3 | PPM250022 | 6/7 8.8 2.12 Slick HPT 0.023 | 5.5 | 2 | 4.875 / 1.98 | XT39 / 3 1/2 REG |  | 32.99 | 35.89
| 4 | GT50-10-585 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.27 | 45.16
| 5 | ZSB500049 | UBHO | 5.125 | 2.5 |  | XT 39 / XT 39 |  | 3.99 | 49.15
| 6 | SD55911 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.05 | 79.2
| 7 | SD56679 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.54 | 88.74
| 8 | SD56632 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.57 | 119.31
| 9 | A52107 | Tomax | 4.875 | 2.5 | 4.875 | 4 XT39 / 4 XT39 |  | 18.02 | 137.33
| 10 | GT52331429 | Crossover Sub | 5.188 | 2.688 |  | CET43 / XT39 |  | 3.38 | 140.71
| 11 | Rig1 | 2 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 189.66 | 330.37
| 12 | 520 | 6 13/16 Drill-N-Ream | 5.25 | 2.5 |  | CET-43 / CET-43 |  | 8.45 | 338.82
| 13 | Rig2 | 26 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 2458.99 | 2797.81
| 14 | PG525-0050 | Agitator | 5.312 | 2.75 | 5.312 / 1.80 | CET43 / CET43 |  | 23.65 | 2821.46
| 15 | Rig3 | 33 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 3108.44 | 5929.9
| 16 | PG525-0049 | Agitator | 5.25 | 2.75 | 5.250 / 2.32 | CET43 / CET43 |  | 21.94 | 5951.84
| 17 | [8 empty] | 5951.84
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 0-1-WT-G-X-I-PN-PP | 2133
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 Slick HPT 0.023 |  |  | PDCI / 6/7 8.8 | 3.96 / 2.12 |  | 0 | 5.5 | 200 | 900
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 800 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPT |  | 0.023
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
[7 empty] | PDCI | UBHO
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5952.91 (Usft)
Well: |  |  | Ozark 1H | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1126621 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/02/2021 | Depth In: |  | 18363 | Total Drilled: |  | 608.00 (Usft)
Date Out: |  |  | 07/04/2021 | Depth Out: |  | 18971 | Drilling / Circ Hours: |  | 6.08 / 9.75
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13509567 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | 306842 | BTI | 4.812 | 2.5 |  | XT39 / XT39 |  | 2.15 | 2.9
| 3 | PPM250005 | 6/7 8.8 2.12 Slick HPT 0.028 | 5.5 | 2 | 4.875 / 1.96 | XT39 / 3 1/2 REG |  | 33.15 | 36.05
| 4 | GT50-10-585 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.27 | 45.32
| 5 | ZSB500049 | UBHO | 5.125 | 2.5 |  | XT 39 / XT 39 |  | 3.99 | 49.31
| 6 | SD55911 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.05 | 79.36
| 7 | SD56679 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.54 | 88.9
| 8 | SD56632 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.57 | 119.47
| 9 | A52107 | Tomax | 4.875 | 2.5 | 4.875 | 4 XT39 / 4 XT39 |  | 18.02 | 137.49
| 10 | GT52331429 | Crossover Sub | 5.188 | 2.688 |  | CET43 / XT39 |  | 3.38 | 140.87
| 11 | Rig1 | 2 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 189.66 | 330.53
| 12 | 520 | 6 13/16 Drill-N-Ream | 5.25 | 2.5 |  | CET-43 / CET-43 |  | 8.45 | 338.98
| 13 | Rig2 | 26 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 2458.99 | 2797.97
| 14 | PG525-0056 | Agitator | 5.312 | 2.75 | 5.250 / 1.83 | CET43 / CET43 |  | 24.56 | 2822.53
| 15 | Rig3 | 33 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 3108.44 | 5930.97
| 16 | PG525-0049 | Agitator | 5.25 | 2.75 | 5.250 / 2.32 | CET43 / CET43 |  | 21.94 | 5952.91
| 17 | [8 empty] | 5952.91
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 0-1-WT-G-X-I-PN-BHA | 608
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 Slick HPT 0.028 |  |  | PDCI / 6/7 8.8 | 4.00 / 2.12 |  | 0 | 5.44 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 650 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPT |  | 0.028
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.165 | PDCI | UBHO | 2.5
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6114 |  |  |  | 9003 |  | 1386 | 1056 |  | 45
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
2576 |  |  |  | 0.6
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_6
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5953.34 (Usft)
Well: |  |  | Ozark 1H | BHA #: |  | 6 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1126621 | Bit #: |  | 6 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/04/2021 | Depth In: |  | 18971 | Total Drilled: |  | 1466.00 (Usft)
Date Out: |  |  | 07/06/2021 | Depth Out: |  | 20437 | Drilling / Circ Hours: |  | 14.58 / 10.83
Survey Offset: |  |  | 69 | Gamma Offset: |  | 56
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13564680 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | 14954251 | 5/6 9.5 1.80 adj 5 3/8 stab | 5 | 2 | 5.000 / 1.66 | 3 1/2 IF / 3 1/2 REG |  | 31.22 | 31.97
| 3 | 107608 | Crossover Sub | 4.875 | 2.5 |  | XT39 / 3 1/2 IF |  | 2.36 | 34.33
| 4 | 306842 | BTI | 4.812 | 2.5 |  | XT39 / XT39 |  | 2.15 | 36.48
| 5 | GT50-10-585 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.27 | 45.75
| 6 | ZSB500049 | UBHO | 5.125 | 2.5 |  | XT 39 / XT 39 |  | 3.99 | 49.74
| 7 | SD55911 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.05 | 79.79
| 8 | SD56679 | Pony Collar (NO HARDBANDING) | 5 | 2.75 |  | XT39 / XT39 |  | 9.54 | 89.33
| 9 | SD56632 | Drill Collar (NO HARDBANDING) | 4.875 | 2.688 |  | XT39 / XT39 |  | 30.57 | 119.9
| 10 | A52107 | Tomax | 4.875 | 2.5 | 4.875 | 4 XT39 / 4 XT39 |  | 18.02 | 137.92
| 11 | GT52331429 | Crossover Sub | 5.188 | 2.688 |  | CET43 / XT39 |  | 3.38 | 141.3
| 12 | Rig1 | 2 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 189.66 | 330.96
| 13 | 520 | 6 13/16 Drill-N-Ream | 5.25 | 2.5 |  | CET-43 / CET-43 |  | 8.45 | 339.41
| 14 | Rig2 | 26 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 2458.99 | 2798.4
| 15 | PG525-0056 | Agitator | 5.312 | 2.75 | 5.250 / 1.83 | CET43 / CET43 |  | 24.56 | 2822.96
| 16 | Rig3 | 33 Stands 4.5 Drill Pipe | 4.5 | 3.5 |  | CET43 / CET43 |  | 3108.44 | 5931.4
| 17 | PG525-0049 | Agitator | 5.25 | 2.75 | 5.250 / 2.32 | CET43 / CET43 |  | 21.94 | 5953.34
| 18 | [8 empty] | 5953.34
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 0-1-LT-S-X-I-NO-TD | 1466
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
5/6 9.5 1.80 adj 5 3/8 stab |  |  | Baker Hughes / 5/6 9.5 | 4.32 / 1.80 |  | 5.38 | 5 | 300 | 2610
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
5050 |  |  | 750 | 80 |  | 106-360 | 0.75 | ADJ | Diamond
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.165 | PDCI | UBHO | 2.5
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6163 |  |  |  | 9009/7477 |  | 1249 | 1411 |  | 290
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
3032/4002 |  |  |  | 0.6
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Well: |  | Ozark 1H
|  |  |  | Longitude: |  | 96° 42' 7.171" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burk
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 70.00/101.86/117.00
Date In: |  | 06/18/2021 21:30 |  | SN: |  | PPM800053 |  |  |  | WOB Rotate (klbs): |  | 29.00
Date Out: |  | 06/19/2021 20:00 |  | Description: |  | 7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 |  |  |  | WOB Slide (klbs): |  | 26.83
Depth In/Out(Usft): |  | 108.00 / 3845.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 97.90
Inc In/Out: |  | 0.27 / 0.86 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 868.37
Azi In/Out: |  | 30.81 / 4.90 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1437.21
Total Drilled (Usft): |  | 3737 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1874.88
%Slide (Ftg): |  | 4.12 |  | Bit to Bend (Usft): |  | 5.78 |  |  |  | Tq On Btm (kftlbs): |  | 8580.65
%Slide (Time): |  | 13.42 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 154 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 1.38 |  | Stab to Bit (Usft): |  | 2.17 |  |  |  | Bit Data
%Rotary (Ftg): |  | 95.88 |  | Kickpad OD (in): |  | 8.5 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 86.55 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL616
Rotary Drilled (Usft): |  | 3583 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 8.9 |  | Length (Usft): |  | 37.48 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 10.28 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 2.33 / 22.50 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In:
Slide ROP (Usft/hr): |  | 111.59 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 402.58 |  | Stator Vendor/Type/Fit: |  | PVFluid / HPO / 0.012 |  |  |  | Drill Hrs: |  | 10.28
Avg ROP (Usft/hr): |  | 363.52 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.33
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
117
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
[10 empty] | 1 |  | 1.19 / 1.16
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 43518 |  | 13.5 |  |  |  |  | 1.5 | 1.5
7/8 Lobe 5.9 Stage 13" NBS 1.5F HPO -.012 0.00 |  |  |  | PPM800053 |  | 8 |  |  |  |  | 37.48 | 38.98
Nortrak Stabilizer (BFF) 13" 0.00 |  |  |  | SD610222 |  | 8.125 | 2.875 |  |  |  | 7.63 | 46.61
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | SD40153 |  | 8 | 3.375 |  |  |  | 7.93 | 54.54
UBHO 0.00 |  |  |  | ZSB775192 |  | 7.75 | 3 |  |  |  | 3.72 | 58.26
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD47865 |  | 8 | 3.375 |  |  |  | 28.77 | 87.03
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD55256 |  | 8 | 3.375 |  |  |  | 28.41 | 115.44
Crossover Sub 0.00 |  |  |  | SD104164 |  | 8.25 | 2.875 |  |  |  | 2.56 | 118
HWDP 9 Jts 0.00 |  |  |  | Rig |  | 5 | 3 |  |  |  | 274.54 | 392.54
-1.00 | [11 empty] | 392.54
Additional Comments
Did motor drain - Yes Visual Wear ? No visual damage to be seen. Start Temp & Max Temp - 90-117 Bit Grade Number of Stalls ? No Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No Misc. Comments ? Drilled to plan build. Motor yeilded 6-9*/100 and held 6 degrees for approx 330 to drop. Dropped back to verticle and held tp casing point.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Well: |  | Ozark 1H
|  |  |  | Longitude: |  | 96° 42' 7.171" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burk
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 121.00/192.36/250.00
Date In: |  | 06/20/2021 24:00 |  | SN: |  | PPM800059 |  |  |  | WOB Rotate (klbs): |  | 26.00
Date Out: |  | 06/24/2021 18:00 |  | Description: |  | 7/8 Lobe 5.9 Slick 2.0F HPO -.017 |  |  |  | WOB Slide (klbs): |  | 23.80
Depth In/Out(Usft): |  | 3845.00 / 12250.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 79.65
Inc In/Out: |  | 0.86 / 14.63 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 836.79
Azi In/Out: |  | 4.88 / 138.18 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 4023.66
Total Drilled (Usft): |  | 8405 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4641.96
%Slide (Ftg): |  | 6.90 |  | Bit to Bend (Usft): |  | 6.04 |  |  |  | Tq On Btm (kftlbs): |  | 12581.4
%Slide (Time): |  | 43.25 |  | Sleeve Stab OD (in): |  | 8 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 580 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 19.03 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 93.10 |  | Kickpad OD (in): |  | 8.25 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 56.75 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 7825 |  | Fishneck OD (in): |  | 8.125 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 24.97 |  | Length (Usft): |  | 37.46 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 44.00 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 5.33 / 90.00 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 30.48 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-WT-G-X-I-CT-TD
Rot ROP (Usft/hr): |  | 313.38 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.017 |  |  |  | Drill Hrs: |  | 44.00
Avg ROP (Usft/hr): |  | 191.02 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 5.33
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
1 / 1 | 1 / 1 | 1 / 1 |  | .4/99.6 |  |  | 1 | 8.4 | 300 | WBM | 0.4 |  | 250
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
63 | 53 | [8 empty] | 8 |  | 8.00 / 7.77
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 54861 |  | 9.875 |  |  |  |  | 1.5 | 1.5
7/8 Lobe 5.9 Slick 2.0F HPO -.017 0.00 |  |  |  | PPM800059 |  | 8 |  |  |  |  | 37.46 | 38.96
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | SD40153 |  | 8 | 3.375 |  |  |  | 7.93 | 46.89
UBHO 0.00 |  |  |  | ZSB775192 |  | 7.75 | 3 |  |  |  | 3.72 | 50.61
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD47865 |  | 8 | 3.375 |  |  |  | 28.77 | 79.38
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD55256 |  | 8 | 3.375 |  |  |  | 28.41 | 107.79
Crossover Sub 0.00 |  |  |  | SD115530 |  | 6.5 | 3 |  |  |  | 2.7 | 110.49
2 Stds 6.5 in DC 0.00 |  |  |  | SD104164 |  | 6.5 | 2.75 |  |  |  | 185.82 | 296.31
Crossover Sub 0.00 |  |  |  | SD115076 |  | 6.125 | 2.75 |  |  |  | 2.36 | 298.67
HWDP 9 Jts 0.00 |  |  |  | Rig |  | 5 | 3 |  |  |  | 274.54 | 573.21
22 Stds 5 in DP 0.00 | [5 empty] | 5 | 4.276 |  |  |  | 2066.2 | 2639.41
Agitator 0.00 |  |  |  | PG675 |  | 6.75 | 3.75 |  |  |  | 24.7 | 2664.11
-1.00 | [11 empty] | 2664.11
Additional Comments
Reason POOH: Intermediate casing point How did motor drain: Motor partially drained by itself when above the table. Once spun with the rotary remaining fluid drained strong out of bit. Visual Wear: No abnormal wear or sounds were observed. Axial play in bearing was approximately .25 inches and minimal play in thrust bearings Run description: Assembly stayed vertical with few maintenance slides. A little rough, difficult to control tool faces when starting the curve. Once we established some angle it was considerably better control Max Temp: 255 Stalls: 0 Motor Yield: 8/100 Max Drilling Diff: 800 Average Drilling Diff: 600 Condition of bit: Bit graded 0-1-WT-G-X-I-CT-TD
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Well: |  | Ozark 1H
|  |  |  | Longitude: |  | 96° 42' 7.171" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 257.00/298.60/331.00
Date In: |  | 06/26/2021 11:35 |  | SN: |  | PPM250010 |  |  |  | WOB Rotate (klbs): |  | 27.00
Date Out: |  | 06/29/2021 24:00 |  | Description: |  | 6/7 8.8 2.12 Slick HS88 0.003 |  |  |  | WOB Slide (klbs): |  | 23.96
Depth In/Out(Usft): |  | 12250.00 / 16230.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 77.62
Inc In/Out: |  | 14.64 / 88.73 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 381.69
Azi In/Out: |  | 138.19 / 141.48 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 5293.51
Total Drilled (Usft): |  | 3980 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 6124.68
%Slide (Ftg): |  | 20.90 |  | Bit to Bend (Usft): |  | 4.05 |  |  |  | Tq On Btm (kftlbs): |  | 12142.86
%Slide (Time): |  | 40.38 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 832 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi): |  | 1100
Slide Hours: |  | 15.58 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 79.10 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 59.61 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 3148 |  | Fishneck OD (in): |  | 4.875 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 23 |  | Length (Usft): |  | 33.13 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 38.58 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 12.75 / 84.42 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 53.4 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-WT-A-X-I-NO-BHA
Rot ROP (Usft/hr): |  | 136.87 |  | Stator Vendor/Type/Fit: |  | PV / HS88 / 0.003 |  |  |  | Drill Hrs: |  | 38.58
Avg ROP (Usft/hr): |  | 103.16 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 12.75
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
42 / 26 | 19 / 12 | 6 / 5 |  | 70/30 |  | 16 | 10 | 11 | 62000 | OBM | 14 |  | 331
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [8 empty] | 8 |  | 8.00 / 11.05
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13601236 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 Slick HS88 0.003 0.00 |  |  |  | PPM250010 |  | 5.5 | 2 |  |  |  | 33.13 | 33.88
BTI 0.00 |  |  |  | RIG |  | 4.812 | 2.5 |  |  |  | 2.03 | 35.91
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | GT50-10-585 |  | 5 | 2.75 |  |  |  | 9.27 | 45.18
UBHO 0.00 |  |  |  | ZSB500049 |  | 5.125 | 2.5 |  |  |  | 3.99 | 49.17
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD55911 |  | 4.875 | 2.688 |  |  |  | 30.05 | 79.22
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | SD56679 |  | 5 | 2.75 |  |  |  | 9.54 | 88.76
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD56632 |  | 4.875 | 2.688 |  |  |  | 30.57 | 119.33
Tomax 0.00 |  |  |  | A52107 |  | 4.875 | 2.5 |  |  |  | 18.02 | 137.35
Crossover Sub 0.00 |  |  |  | GT52331429 |  | 5.188 | 2.688 |  |  |  | 3.38 | 140.73
2 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig1 |  | 4.5 | 3.5 |  |  |  | 189.66 | 330.39
6 13/16 Drill-N-Ream 0.00 |  |  |  | 520 |  | 5.25 | 2.5 |  |  |  | 8.45 | 338.84
26 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 3.5 |  |  |  | 2458.99 | 2797.83
Agitator 0.00 |  |  |  | PG525-0051 |  | 5.25 | 2.75 |  |  |  | 23.77 | 2821.6
33 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig3 |  | 4.5 | 3.5 |  |  |  | 3108.44 | 5930.04
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.75 |  |  |  | 21.94 | 5951.98
0.00 | [11 empty] | 5951.98
Additional Comments
Reason POOH: ROP began to fall off and torque increased. How did motor drain: Motor seemed to have drained by itself therefor couldn?t tell if it would have drained or not. Visual Wear: Didn?t hear anything moving internally. Bit wasn?t hurt. Axial play in bearing was approximately .25 inches and minimal play in thrust bearings Run description: Assembly drilled shoe track, curve, and 2953? of lateral. Assembly yielded 13?s to 15?s and performed well. Maintenance slides were put in to stay in customer?s window. Max Temp: 331 Stalls: 0 Motor Yield: 14?/100? Max Drilling Diff: 1300 Average Drilling Diff: 1100 Condition of bit: Bit graded 0-1-WT-A-X-I-NO-PR
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Well: |  | Ozark 1H
|  |  |  | Longitude: |  | 96° 42' 7.171" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 327.00/332.34/340.00
Date In: |  | 06/30/2021 02:00 |  | SN: |  | PPM250022 |  |  |  | WOB Rotate (klbs): |  | 23.00
Date Out: |  | 07/02/2021 13:05 |  | Description: |  | 6/7 8.8 2.12 Slick HPT 0.023 |  |  |  | WOB Slide (klbs): |  | 23.57
Depth In/Out(Usft): |  | 16230.00 / 18363.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 88.73 / 86.01 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 360
Azi In/Out: |  | 141.48 / 142.35 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 5400
Total Drilled (Usft): |  | 2133 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 6284.21
%Slide (Ftg): |  | 3.52 |  | Bit to Bend (Usft): |  | 3.96 |  |  |  | Tq On Btm (kftlbs): |  | 14000
%Slide (Time): |  | 20.52 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 75 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 3.42 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 96.48 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 79.50 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2058 |  | Fishneck OD (in): |  | 4.875 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 13.25 |  | Length (Usft): |  | 32.99 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 16.67 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 14.08 / 59.08 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 21.93 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-WT-G-X-I-PN-PP
Rot ROP (Usft/hr): |  | 155.32 |  | Stator Vendor/Type/Fit: |  | Abaco / HPT / 0.023 |  |  |  | Drill Hrs: |  | 16.67
Avg ROP (Usft/hr): |  | 127.95 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 14.08
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
42 / 26 | 19 / 13 | 7 / 6 |  | 74/26 |  | 16 | 10 | 11.7 | 54000 | OBM | 17.8 |  | 340
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
[10 empty] | 14 |  | 14.00 / 2.01
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13594950 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
BTI 0.00 |  |  |  | 306842 |  | 4.812 | 2.5 |  |  |  | 2.15 | 2.9
6/7 8.8 2.12 Slick HPT 0.023 0.00 |  |  |  | PPM250022 |  | 5.5 | 2 |  |  |  | 32.99 | 35.89
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | GT50-10-585 |  | 5 | 2.75 |  |  |  | 9.27 | 45.16
UBHO 0.00 |  |  |  | ZSB500049 |  | 5.125 | 2.5 |  |  |  | 3.99 | 49.15
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD55911 |  | 4.875 | 2.688 |  |  |  | 30.05 | 79.2
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | SD56679 |  | 5 | 2.75 |  |  |  | 9.54 | 88.74
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD56632 |  | 4.875 | 2.688 |  |  |  | 30.57 | 119.31
Tomax 0.00 |  |  |  | A52107 |  | 4.875 | 2.5 |  |  |  | 18.02 | 137.33
Crossover Sub 0.00 |  |  |  | GT52331429 |  | 5.188 | 2.688 |  |  |  | 3.38 | 140.71
2 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig1 |  | 4.5 | 3.5 |  |  |  | 189.66 | 330.37
6 13/16 Drill-N-Ream 0.00 |  |  |  | 520 |  | 5.25 | 2.5 |  |  |  | 8.45 | 338.82
26 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 3.5 |  |  |  | 2458.99 | 2797.81
Agitator 0.00 |  |  |  | PG525-0050 |  | 5.312 | 2.75 |  |  |  | 23.65 | 2821.46
33 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig3 |  | 4.5 | 3.5 |  |  |  | 3108.44 | 5929.9
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.75 |  |  |  | 21.94 | 5951.84
0.00 | [11 empty] | 5951.84
Additional Comments
Reason POOH: Went back to rotating after a slide and made approximately six feet. Pump pressure increased approximately 1000 psi and top drive torque increased from 12000 ft/lbs to 15800 ft/lbs. One pump was killed while picking up off bottom. The top drive never stalled and 1700 psi was the max diff on the motor during this event. gpms were reduced to 310 and 5400 psi while circulating to POOH for pressure increase. At drilling gpm of 360 off bottom pressure was 5400 psi. While circulating to POOH what appeared to be stator rubber came across the shakers. How did motor drain: Only a couple gallons of mud was observed coming out of the bit once above the rotary. When trying to drain the motor with the table, motor was really tight and a popping sound was heard when it did break free and started to spin. No other noises were heard nor did any fluid come out of the bit while spinning the bit box. I put chain tongs on the bit box and couldn?t turn it. Visual Wear: No visual wear was observed. Axial play in bearing was tight with little movement and very minimal, if any, play in thrust bearings Run description: Assembly drilled 2133 of lateral. Assembly yielded 13?s to 15?s and performed well in rotation. Maintenance slides were put in to stay in customer?s window. Max Temp: 340 for a couple updates. Stalls: 0 Motor Yield: 14?/100? Max Drilling Diff: 900 Average Drilling Diff: 800 Condition of bit: Bit graded 0-1-WT-G-X-I-PN-PP. One nozzle was plugged with what appeared to be stator rubber.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Well: |  | Ozark 1H
|  |  |  | Longitude: |  | 96° 42' 7.171" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 330.00/337.36/342.00
Date In: |  | 07/02/2021 14:00 |  | SN: |  | PPM250005 |  |  |  | WOB Rotate (klbs): |  | 21.00
Date Out: |  | 07/04/2021 08:00 |  | Description: |  | 6/7 8.8 2.12 Slick HPT 0.028 |  |  |  | WOB Slide (klbs): |  | 25.00
Depth In/Out(Usft): |  | 18363.00 / 18971.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 77.78
Inc In/Out: |  | 86.01 / 89.69 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 350.45
Azi In/Out: |  | 142.35 / 141.27 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 5409.09
Total Drilled (Usft): |  | 608 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 6036.36
%Slide (Ftg): |  | 3.62 |  | Bit to Bend (Usft): |  | 4 |  |  |  | Tq On Btm (kftlbs): |  | 12222.22
%Slide (Time): |  | 16.44 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 22 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 650
Slide Hours: |  | 1 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 96.38 |  | Kickpad OD (in): |  | 5.438 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 83.51 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 586 |  | Fishneck OD (in): |  | 4.875 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 5.08 |  | Length (Usft): |  | 33.15 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 6.08 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 9.75 / 42.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 22 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-WT-G-X-I-PN-BHA
Rot ROP (Usft/hr): |  | 115.35 |  | Stator Vendor/Type/Fit: |  | Abaco / HPT / 0.028 |  |  |  | Drill Hrs: |  | 6.08
Avg ROP (Usft/hr): |  | 100 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 9.75
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
56 / 33 | 25 / 16 | 7 / 6 |  | 74/26 |  | 23 | 10 | 11.8 | 53800 | OBM | 17.8 |  | 342
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [8 empty] | 14 |  | 14.00 / 2.31
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13509567 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
BTI 0.00 |  |  |  | 306842 |  | 4.812 | 2.5 |  |  |  | 2.15 | 2.9
6/7 8.8 2.12 Slick HPT 0.028 0.00 |  |  |  | PPM250005 |  | 5.5 | 2 |  |  |  | 33.15 | 36.05
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | GT50-10-585 |  | 5 | 2.75 |  |  |  | 9.27 | 45.32
UBHO 0.00 |  |  |  | ZSB500049 |  | 5.125 | 2.5 |  |  |  | 3.99 | 49.31
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD55911 |  | 4.875 | 2.688 |  |  |  | 30.05 | 79.36
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | SD56679 |  | 5 | 2.75 |  |  |  | 9.54 | 88.9
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD56632 |  | 4.875 | 2.688 |  |  |  | 30.57 | 119.47
Tomax 0.00 |  |  |  | A52107 |  | 4.875 | 2.5 |  |  |  | 18.02 | 137.49
Crossover Sub 0.00 |  |  |  | GT52331429 |  | 5.188 | 2.688 |  |  |  | 3.38 | 140.87
2 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig1 |  | 4.5 | 3.5 |  |  |  | 189.66 | 330.53
6 13/16 Drill-N-Ream 0.00 |  |  |  | 520 |  | 5.25 | 2.5 |  |  |  | 8.45 | 338.98
26 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 3.5 |  |  |  | 2458.99 | 2797.97
Agitator 0.00 |  |  |  | PG525-0056 |  | 5.312 | 2.75 |  |  |  | 24.56 | 2822.53
33 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig3 |  | 4.5 | 3.5 |  |  |  | 3108.44 | 5930.97
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.75 |  |  |  | 21.94 | 5952.91
0.00 | [11 empty] | 5952.91
Failure Information
Incident | YES | Hrs Before Incident |  |  | Tripped For Incident |  | NO | BHA SN |  |  | MWD SN
LIH | NO | NPT |  |  | Catastrophic Inci. |  | NO | MOTOR Inci. | NO |  | MWD Inci. | NO
Closed | NO | EDR Review |  | NO | Surface Fail |  | NO | MTBF Attrib. | NO |  | MWD Cat
Operations at Time of Incident
Troubleshooting Performed
Surface Findings
Additional Comments
Reason POOH: While rotating ahead @ 18913 , pump pressure spiked 300 psi and picked up off bottom. Double checked zeros and went back to drilling. Another pressure spike was encountered @ 18958. String was picked up off bottom and zeros verified. Prior to the second spike the ROP was 135/hr. After the spike ROP gradually fell off to zero. Around this time, the bottoms up strokes were figured and the bottoms up from the first spike was coming over the shakers. Pea size chunks of what appeared to be stator rubber was coming over the shakers. How did motor drain: No mud was observed coming out of the bit once above the rotary. No mud was observed coming out of the motor while spinning the bit box with the rotary. Visual Wear: No visual wear was observed. Axial play in bearing was tight with little movement and approximately 1/8 inch play in thrust bearings Run description: Assembly drilled 608 of lateral. Assembly yielded 13?s to 15?s and performed well in rotation. Maintenance slides were put in to stay in customer?s window. Max Temp: 342 for two live updates from MWD Stalls: 0 Motor Yield: 14?/100? Max Drilling Diff: 650 Average Drilling Diff: 600 Condition of bit: Bit graded 0-1-WT-G-X-I-PN-MI. One nozzle was plugged with what appeared to be stator rubber.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 6
|  |  |  | Job # |  | LTX1126621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33522 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 59' 4.775" N |  |  | Well: |  | Ozark 1H
|  |  |  | Longitude: |  | 96° 42' 7.171" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 6
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 340.00/346.68/351.00
Date In: |  | 07/04/2021 09:20 |  | SN: |  | 14954251 |  |  |  | WOB Rotate (klbs): |  | 18.00
Date Out: |  | 07/06/2021 18:00 |  | Description: |  | 5/6 9.5 1.80 adj 5 3/8 stab |  |  |  | WOB Slide (klbs): |  | 13.00
Depth In/Out(Usft): |  | 18971.00 / 20437.00 |  | Make: |  | Baker Hughes |  |  |  | RPM: |  | 80.00 / 70.50
Inc In/Out: |  | 89.70 / 87.64 |  | Model: |  | 5/6 9.5 |  |  |  | Flow Rate (gpm): |  | 323.18
Azi In/Out: |  | 141.27 / 143.88 |  | Lobes / Stages: |  | 5/6 / 9.5 |  |  |  | Off Btm Press (psi): |  | 4688.64
Total Drilled (Usft): |  | 1466 |  | Bend Angle: |  | 1.8 |  |  |  | On Btm Press (psi): |  | 5277.27
%Slide (Ftg): |  | 2.05 |  | Bit to Bend (Usft): |  | 4.32 |  |  |  | Tq On Btm (kftlbs): |  | 12220
%Slide (Time): |  | 9.74 |  | Sleeve Stab OD (in): |  | 5.375 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 30 |  | Bearing Gap (in): |  | 0.05 |  |  |  | Avg Diff Press (psi): |  | 750
Slide Hours: |  | 1.42 |  | Stab to Bit (Usft): |  | 3 |  |  |  | Bit Data
%Rotary (Ftg): |  | 97.95 |  | Kickpad OD (in): |  | 5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 90.24 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 1436 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 13.16 |  | Length (Usft): |  | 31.22 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 14.58 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 6
Circ/BRT Hrs: |  | 10.83 / 56.67 |  | Rev per Gal: |  | 0.75 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 21.13 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-LT-S-X-I-NO-TD
Rot ROP (Usft/hr): |  | 109.12 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 14.58
Avg ROP (Usft/hr): |  | 100.55 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 10.83
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
57 / 34 | 24 / 16 | 7 / 6 |  | 74/26 |  | 23 | 11 | 11.7 | 52000 | OBM | 17.3 |  | 351
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 56 | [8 empty] | 10 |  | 12.00 / 2.06
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13564680 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
5/6 9.5 1.80 adj 5 3/8 stab 0.00 |  |  |  | 14954251 |  | 5 | 2 |  |  |  | 31.22 | 31.97
Crossover Sub 0.00 |  |  |  | 107608 |  | 4.875 | 2.5 |  |  |  | 2.36 | 34.33
BTI 0.00 |  |  |  | 306842 |  | 4.812 | 2.5 |  |  |  | 2.15 | 36.48
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | GT50-10-585 |  | 5 | 2.75 |  |  |  | 9.27 | 45.75
UBHO 0.00 |  |  |  | ZSB500049 |  | 5.125 | 2.5 |  |  |  | 3.99 | 49.74
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD55911 |  | 4.875 | 2.688 |  |  |  | 30.05 | 79.79
Pony Collar (NO HARDBANDING) 0.00 |  |  |  | SD56679 |  | 5 | 2.75 |  |  |  | 9.54 | 89.33
Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD56632 |  | 4.875 | 2.688 |  |  |  | 30.57 | 119.9
Tomax 0.00 |  |  |  | A52107 |  | 4.875 | 2.5 |  |  |  | 18.02 | 137.92
Crossover Sub 0.00 |  |  |  | GT52331429 |  | 5.188 | 2.688 |  |  |  | 3.38 | 141.3
2 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig1 |  | 4.5 | 3.5 |  |  |  | 189.66 | 330.96
6 13/16 Drill-N-Ream 0.00 |  |  |  | 520 |  | 5.25 | 2.5 |  |  |  | 8.45 | 339.41
26 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig2 |  | 4.5 | 3.5 |  |  |  | 2458.99 | 2798.4
Agitator 0.00 |  |  |  | PG525-0056 |  | 5.312 | 2.75 |  |  |  | 24.56 | 2822.96
33 Stands 4.5 Drill Pipe 0.00 |  |  |  | Rig3 |  | 4.5 | 3.5 |  |  |  | 3108.44 | 5931.4
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.25 | 2.75 |  |  |  | 21.94 | 5953.34
0.00 | [11 empty] | 5953.34
Additional Comments
Reason POOH: TD well How did motor drain: Motor was full of fluid and drained as expected with rotary Visual Wear: No visual wear was observed. Axial play in bearing was tight with little movement and approximately 1/16 inch play in thrust bearings Run description: Assembly drilled 1466 of lateral. Assembly yielded 10?s to 12?s and performed well in rotation. Two maintenance slides were put in to stay in customer?s window. Max Temp: 351 Stalls: 0 Motor Yield: 12?/100? Max Drilling Diff: 800 Average Drilling Diff: 750 Condition of bit: Bit graded 0-1-LT-S-X-I-NO-TD. One cutter was missing on the shoulder
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 406 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3737
Site: |  |  |  |  | Ozark - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 154
Well Name: |  |  |  |  | Ozark 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 0.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 406 |  | VS Azimuth: |  | 141.87 |  | Rotate: |  | 3583
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/19/2021 | 02:40 | 03:40 | 1 | 108 | 300 | 192 | Rotate |  | 143 | 0.36 | 30.81 | 143 | 0.39 | 0.23 | 0.39 | 0.25 |  |  | 25 | 60 | 560 | 4000 | 192 | 850 | 650 | 200 | 70 | 75 | 70 | 65
06/19/2021 | 03:40 | 04:00 | 0.33333 | 300 | 392 | 92 | Rotate |  | 326 | 0.51 | 19.26 | 325.99 | 1.64 | 0.76 | 1.64 | 0.1 |  |  | 25 | 75 | 700 | 4000 | 276 | 950 | 750 | 200 | 80 | 80 | 75 | 70
06/19/2021 | 04:00 | 05:30 | 1.5 | 392 | 1126 | 734 | Rotate |  | 421 | 0.47 | 24.42 | 420.99 | 2.39 | 1.07 | 2.39 | 0.06 |  |  | 25 | 100 | 880 | 8000 | 489.33 | 1700 | 1450 | 250 | 90 | 95 | 90 | 85
06/19/2021 | 05:35 | 05:55 | 0.33333 | 1126 | 1332 | 206 | Rotate |  | 1173 | 1.15 | 164.93 | 1172.92 | -2.14 | 4.89 | -2.14 | 0.08 |  |  | 27 | 100 | 880 | 8000 | 618 | 1700 | 1450 | 250 | 93 | 95 | 90 | 85
06/19/2021 | 06:00 | 06:07 | 0.11667 | 1332 | 1426 | 94 | Rotate |  | 1360 | 0.66 | 162.8 | 1359.9 | -4.89 | 5.63 | -4.89 | 0.2 |  |  | 27 | 100 | 880 | 8000 | 805.71 | 1700 | 1450 | 250 | 93 | 95 | 90 | 85
06/19/2021 | 06:17 | 06:27 | 0.16667 | 1426 | 1520 | 94 | Rotate |  | 1454 | 0.39 | 179.35 | 1453.89 | -5.72 | 5.79 | -5.72 | 0.33 |  |  | 27 | 100 | 880 | 8000 | 564 | 1700 | 1450 | 250 | 93 | 95 | 90 | 85
06/19/2021 | 06:33 | 06:45 | 0.2 | 1520 | 1614 | 94 | Rotate |  | 1548 | 0.14 | 166.63 | 1547.89 | -6.15 | 5.82 | -6.15 | 0.27 |  |  | 27 | 100 | 880 | 8000 | 470 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 06:49 | 06:57 | 0.13333 | 1614 | 1708 | 94 | Rotate |  | 1642 | 0.04 | 343.05 | 1641.89 | -6.23 | 5.84 | -6.23 | 0.19 |  |  | 27 | 100 | 880 | 8000 | 705 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 07:01 | 07:10 | 0.15 | 1708 | 1802 | 94 | Rotate |  | 1736 | 0.03 | 321.69 | 1735.89 | -6.18 | 5.82 | -6.18 | 0.02 |  |  | 27 | 100 | 880 | 8000 | 626.67 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 07:16 | 07:22 | 0.1 | 1802 | 1895 | 93 | Rotate |  | 1829 | 0.12 | 199.85 | 1828.89 | -6.26 | 5.77 | -6.26 | 0.15 |  |  | 27 | 100 | 880 | 8000 | 930 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 07:26 | 07:40 | 0.23333 | 1895 | 1989 | 94 | Rotate |  | 1923 | 0.08 | 271.91 | 1922.89 | -6.35 | 5.67 | -6.35 | 0.13 |  |  | 27 | 100 | 880 | 8000 | 402.86 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 07:46 | 07:57 | 0.18333 | 1989 | 2004 | 15 | Slide | TTF: 330; Drilling Parameters WOB: 27; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 81.82 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 07:57 | 08:12 | 0.25 | 2004 | 2083 | 79 | Rotate |  | 2017 | 0.83 | 327.04 | 2016.89 | -5.77 | 5.23 | -5.77 | 0.84 |  |  | 27 | 100 | 880 | 8000 | 316 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 08:17 | 08:25 | 0.13333 | 2083 | 2098 | 15 | Slide | TTF: 330; Drilling Parameters WOB: 27; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 112.5 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 08:25 | 08:35 | 0.16667 | 2098 | 2176 | 78 | Rotate |  | 2110 | 1.82 | 332.89 | 2109.86 | -3.89 | 4.19 | -3.89 | 1.07 |  |  | 27 | 100 | 880 | 8000 | 468 | 1700 | 1450 | 250 | 95 | 95 | 90 | 85
06/19/2021 | 08:39 | 08:46 | 0.11667 | 2176 | 2191 | 15 | Slide | TTF: 330; Drilling Parameters WOB: 27; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 128.57 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 08:46 | 08:56 | 0.16667 | 2191 | 2269 | 78 | Rotate |  | 2203 | 2.89 | 334.42 | 2202.78 | -0.46 | 2.51 | -0.46 | 1.15 |  |  | 27 | 100 | 880 | 8000 | 468 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 09:00 | 09:08 | 0.13333 | 2269 | 2281 | 12 | Slide | TTF: 330; Drilling Parameters WOB: 27; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 90 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 09:08 | 09:19 | 0.18333 | 2281 | 2364 | 83 | Rotate |  | 2298 | 3.92 | 329.96 | 2297.61 | 4.51 | -0.15 | 4.51 | 1.12 |  |  | 27 | 100 | 880 | 8000 | 452.73 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 09:24 | 09:31 | 0.11667 | 2364 | 2376 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 27; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 102.86 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 09:31 | 09:42 | 0.18333 | 2376 | 2458 | 82 | Rotate |  | 2392 | 4.74 | 326.3 | 2391.34 | 10.52 | -3.92 | 10.52 | 0.92 |  |  | 27 | 100 | 880 | 8000 | 447.27 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 09:46 | 09:52 | 0.1 | 2458 | 2470 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 27; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 120 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 09:52 | 10:00 | 0.13333 | 2470 | 2552 | 82 | Rotate |  | 2486 | 5.67 | 321.12 | 2484.96 | 17.37 | -8.98 | 17.37 | 1.11 |  |  | 27 | 100 | 880 | 8000 | 615 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 10:05 | 10:16 | 0.18333 | 2552 | 2645 | 93 | Rotate |  | 2579 | 6.05 | 319.05 | 2577.47 | 24.64 | -15.08 | 24.64 | 0.47 |  |  | 27 | 100 | 880 | 8000 | 507.27 | 1700 | 1450 | 250 | 99 | 95 | 90 | 85
06/19/2021 | 10:20 | 10:31 | 0.18333 | 2645 | 2740 | 95 | Rotate |  | 2674 | 5.87 | 318.34 | 2671.96 | 32.05 | -21.59 | 32.05 | 0.2 |  |  | 35 | 100 | 880 | 10000 | 518.18 | 2180 | 1500 | 680 | 107 | 135 | 110 | 95
06/19/2021 | 10:35 | 10:48 | 0.21667 | 2740 | 2833 | 93 | Rotate |  | 2767 | 5.88 | 319.22 | 2764.47 | 39.21 | -27.86 | 39.21 | 0.1 |  |  | 35 | 100 | 880 | 10000 | 429.23 | 2180 | 1500 | 680 | 107 | 135 | 110 | 95
06/19/2021 | 10:53 | 11:06 | 0.21667 | 2833 | 2927 | 94 | Rotate |  | 2861 | 5.87 | 317.91 | 2857.97 | 46.43 | -34.23 | 46.43 | 0.14 |  |  | 35 | 100 | 880 | 10000 | 433.85 | 2180 | 1500 | 680 | 107 | 135 | 110 | 95
06/19/2021 | 11:11 | 11:15 | 0.066667 | 2927 | 2937 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 150 | 2180 | 1500 | 680 | 107 | 135 | 110 | 95
06/19/2021 | 11:15 | 11:27 | 0.2 | 2937 | 3021 | 84 | Rotate |  | 2955 | 5.43 | 321.26 | 2951.52 | 53.46 | -40.24 | 53.46 | 0.58 |  |  | 35 | 100 | 880 | 10000 | 420 | 2180 | 1500 | 680 | 107 | 135 | 110 | 95
06/19/2021 | 11:32 | 11:38 | 0.1 | 3021 | 3033 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 2180 | 1500 | 680 | 107 | 135 | 110 | 95
06/19/2021 | 11:38 | 11:52 | 0.23333 | 3033 | 3115 | 82 | Rotate |  | 3049 | 4.44 | 326.48 | 3045.17 | 59.97 | -45.03 | 59.97 | 1.16 |  |  | 35 | 100 | 880 | 10000 | 351.43 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 11:58 | 12:04 | 0.1 | 3115 | 3127 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 12:04 | 12:18 | 0.23333 | 3127 | 3209 | 82 | Rotate |  | 3143 | 3.56 | 330.79 | 3138.94 | 65.55 | -48.46 | 65.55 | 0.99 |  |  | 35 | 100 | 880 | 10000 | 351.43 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 12:24 | 12:30 | 0.1 | 3209 | 3221 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 12:30 | 12:43 | 0.21667 | 3221 | 3304 | 83 | Rotate |  | 3238 | 2.58 | 336.95 | 3233.8 | 70.09 | -50.74 | 70.09 | 1.09 |  |  | 35 | 100 | 880 | 10000 | 383.08 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 12:49 | 12:55 | 0.1 | 3304 | 3316 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 12:55 | 13:09 | 0.23333 | 3316 | 3398 | 82 | Rotate |  | 3332 | 1.8 | 348.65 | 3327.73 | 73.48 | -51.86 | 73.48 | 0.95 |  |  | 35 | 100 | 880 | 10000 | 351.43 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 13:15 | 13:23 | 0.13333 | 3398 | 3413 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 25; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 880; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 112.5 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 13:23 | 13:36 | 0.21667 | 3413 | 3492 | 79 | Rotate |  | 3426 | 1.06 | 13.92 | 3421.7 | 75.77 | -51.94 | 75.77 | 1.02 |  |  | 35 | 100 | 880 | 10000 | 364.62 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 13:41 | 13:59 | 0.3 | 3492 | 3586 | 94 | Rotate |  | 3520 | 0.9 | 30.37 | 3515.69 | 77.26 | -51.36 | 77.26 | 0.34 |  |  | 35 | 100 | 880 | 10000 | 313.33 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 14:04 | 14:31 | 0.45 | 3586 | 3680 | 94 | Rotate |  | 3614 | 0.75 | 34.81 | 3609.68 | 78.4 | -50.63 | 78.4 | 0.17 |  |  | 35 | 100 | 880 | 10000 | 208.89 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 14:35 | 14:54 | 0.31667 | 3680 | 3774 | 94 | Rotate |  | 3708 | 0.81 | 32.52 | 3703.67 | 79.46 | -49.92 | 79.46 | 0.07 |  |  | 35 | 100 | 880 | 10000 | 296.84 | 2180 | 1500 | 680 | 113 | 135 | 110 | 95
06/19/2021 | 14:58 | 15:14 | 0.26667 | 3774 | 3845 | 71 | Rotate |  | 3779 | 0.66 | 13.43 | 3774.67 | 80.28 | -49.56 | 80.28 | 0.4 |  |  | 35 | 100 | 880 | 10000 | 266.25 | 2180 | 1500 | 680 | 117 | 135 | 110 | 95

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 406 |  | North Reference: |  | GRID |  | Total Drilled: |  | 8405
Site: |  |  |  |  | Ozark - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 580
Well Name: |  |  |  |  | Ozark 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 63.00 / 53.00 |  |  |  |  | Grid Conv: |  |  |  | 406 |  | VS Azimuth: |  | 141.87 |  | Rotate: |  | 7825
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/21/2021 | 08:35 | 09:20 | 0.75 | 3845 | 3979 | 134 | Rotate |  | 3916 | 1.08 | 359.28 | 3911.65 | 82.34 | -49.39 | 82.34 | 0.34 |  |  | 10 | 50 | 400 | 8000 | 178.67 | 1450 | 1050 | 400 | 121 | 170 | 150 | 140
06/21/2021 | 09:25 | 09:40 | 0.25 | 3979 | 4073 | 94 | Rotate |  | 4010 | 1.41 | 350.28 | 4005.63 | 84.37 | -49.6 | 84.37 | 0.41 |  |  | 25 | 80 | 650 | 10000 | 376 | 3000 | 2350 | 650 | 127 | 170 | 150 | 140
06/21/2021 | 09:45 | 10:00 | 0.25 | 4073 | 4168 | 95 | Rotate |  | 4105 | 1.5 | 342.64 | 4100.6 | 86.71 | -50.17 | 86.71 | 0.22 |  |  | 25 | 80 | 650 | 10000 | 380 | 3000 | 2350 | 650 | 127 | 170 | 150 | 140
06/21/2021 | 10:10 | 10:15 | 0.083333 | 4168 | 4178 | 10 | Slide | TTF: 150; Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 3900 | 3400 | 500 | 133 | 170 | 150 | 140
06/21/2021 | 10:15 | 10:25 | 0.16667 | 4178 | 4262 | 84 | Rotate |  | 4199 | 0.29 | 334.04 | 4194.58 | 88.1 | -50.64 | 88.1 | 1.29 |  |  | 25 | 80 | 900 | 10000 | 504 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 10:30 | 10:40 | 0.16667 | 4262 | 4355 | 93 | Rotate |  | 4292 | 0.24 | 4.12 | 4287.58 | 88.5 | -50.73 | 88.5 | 0.16 |  |  | 25 | 80 | 900 | 10000 | 558 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 10:45 | 10:55 | 0.16667 | 4355 | 4450 | 95 | Rotate |  | 4387 | 0.65 | 1.68 | 4382.58 | 89.24 | -50.7 | 89.24 | 0.43 |  |  | 25 | 80 | 900 | 10000 | 570 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 11:00 | 11:10 | 0.16667 | 4450 | 4543 | 93 | Rotate |  | 4480 | 1.15 | 349.02 | 4475.57 | 90.68 | -50.86 | 90.68 | 0.58 |  |  | 25 | 80 | 900 | 10000 | 558 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 11:15 | 11:20 | 0.083333 | 4543 | 4569 | 26 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 312 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 11:20 | 11:25 | 0.083333 | 4569 | 4579 | 10 | Slide | 180 | 4574 | 1.12 | 339.77 | 4569.55 | 92.47 | -51.36 | 92.47 | 0.2 |  |  | 10 | 80 | 900 | 10000 | 120 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 11:25 | 11:35 | 0.16667 | 4579 | 4637 | 58 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 348 | 3900 | 3400 | 500 | 136 | 170 | 150 | 140
06/21/2021 | 11:40 | 11:50 | 0.16667 | 4637 | 4731 | 94 | Rotate |  | 4668 | 0.38 | 331.91 | 4663.54 | 93.61 | -51.82 | 93.61 | 0.79 |  |  | 25 | 80 | 900 | 10000 | 564 | 3900 | 3400 | 500 | 145 | 170 | 150 | 140
06/21/2021 | 11:55 | 12:10 | 0.25 | 4731 | 4825 | 94 | Rotate |  | 4762 | 0.65 | 328.26 | 4757.54 | 94.34 | -52.25 | 94.34 | 0.29 |  |  | 25 | 80 | 700 | 10000 | 376 | 3200 | 2700 | 500 | 145 | 170 | 150 | 140
06/21/2021 | 12:15 | 12:20 | 0.083333 | 4825 | 4835 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 3200 | 2700 | 500 | 145 | 170 | 150 | 140
06/21/2021 | 12:20 | 12:35 | 0.25 | 4835 | 4919 | 84 | Rotate |  | 4856 | 1.67 | 279.22 | 4851.52 | 95.01 | -53.88 | 95.01 | 1.42 |  |  | 25 | 80 | 700 | 10000 | 336 | 3200 | 2700 | 500 | 145 | 170 | 150 | 140
06/21/2021 | 12:40 | 12:55 | 0.25 | 4919 | 5014 | 95 | Rotate |  | 4951 | 1.9 | 279.38 | 4946.47 | 95.49 | -56.8 | 95.49 | 0.24 |  |  | 25 | 80 | 700 | 12000 | 380 | 3200 | 2700 | 500 | 154 | 190 | 170 | 155
06/21/2021 | 13:00 | 13:10 | 0.16667 | 5014 | 5108 | 94 | Rotate |  | 5045 | 1.93 | 281.17 | 5040.42 | 96.05 | -59.89 | 96.05 | 0.07 |  |  | 25 | 80 | 700 | 12000 | 564 | 3200 | 2700 | 500 | 154 | 190 | 170 | 155
06/21/2021 | 13:15 | 13:22 | 0.11667 | 5108 | 5118 | 10 | Slide | TTF: 120; Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 85.71 | 3200 | 2700 | 500 | 154 | 190 | 170 | 155
06/21/2021 | 13:22 | 13:40 | 0.3 | 5118 | 5202 | 84 | Rotate |  | 5139 | 1.26 | 271.53 | 5134.38 | 96.38 | -62.48 | 96.38 | 0.77 |  |  | 25 | 80 | 700 | 12000 | 280 | 3200 | 2700 | 500 | 154 | 190 | 170 | 155
06/21/2021 | 13:45 | 13:55 | 0.16667 | 5202 | 5299 | 97 | Rotate |  | 5234 | 1.1 | 266.35 | 5229.36 | 96.35 | -64.43 | 96.35 | 0.2 |  |  | 25 | 80 | 900 | 12000 | 582 | 4100 | 3200 | 900 | 154 | 190 | 170 | 155
06/21/2021 | 14:00 | 14:10 | 0.16667 | 5299 | 5390 | 91 | Rotate |  | 5327 | 1.03 | 276.83 | 5322.35 | 96.39 | -66.15 | 96.39 | 0.22 |  |  | 25 | 80 | 900 | 12000 | 546 | 4100 | 3200 | 900 | 154 | 190 | 170 | 155
06/21/2021 | 14:15 | 14:30 | 0.25 | 5390 | 5484 | 94 | Rotate |  | 5421 | 1.08 | 282.99 | 5416.33 | 96.69 | -67.85 | 96.69 | 0.13 |  |  | 30 | 80 | 900 | 12000 | 376 | 4100 | 3200 | 900 | 154 | 190 | 170 | 155
06/21/2021 | 14:35 | 14:45 | 0.16667 | 5484 | 5579 | 95 | Rotate |  | 5516 | 1.13 | 279.46 | 5511.31 | 97.05 | -69.65 | 97.05 | 0.09 |  |  | 30 | 80 | 900 | 12000 | 570 | 4100 | 3200 | 900 | 154 | 190 | 170 | 155
06/21/2021 | 14:50 | 14:58 | 0.13333 | 5579 | 5589 | 10 | Slide | TTF: 120; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 75 | 4100 | 3200 | 900 | 154 | 190 | 170 | 155
06/21/2021 | 14:58 | 15:10 | 0.2 | 5589 | 5673 | 84 | Rotate |  | 5610 | 0.67 | 232.22 | 5605.3 | 96.86 | -71 | 96.86 | 0.89 |  |  | 35 | 80 | 900 | 10000 | 420 | 4100 | 3200 | 900 | 167 | 190 | 170 | 155
06/21/2021 | 15:50 | 16:05 | 0.25 | 5673 | 5766 | 93 | Rotate |  | 5703 | 0.63 | 227.77 | 5698.3 | 96.19 | -71.81 | 96.19 | 0.07 |  |  | 30 | 80 | 900 | 10000 | 372 | 4100 | 3200 | 900 | 171 | 190 | 170 | 155
06/21/2021 | 16:10 | 16:25 | 0.25 | 5766 | 5857 | 91 | Rotate |  | 5794 | 0.55 | 258.07 | 5789.29 | 95.76 | -72.61 | 95.76 | 0.35 |  |  | 30 | 80 | 900 | 10000 | 364 | 4150 | 3200 | 950 | 171 | 190 | 170 | 155
06/21/2021 | 16:30 | 16:50 | 0.33333 | 5857 | 5950 | 93 | Rotate |  | 5887 | 0.61 | 277.7 | 5882.29 | 95.74 | -73.53 | 95.74 | 0.22 |  |  | 30 | 80 | 900 | 10000 | 279 | 4150 | 3200 | 950 | 172 | 190 | 170 | 155
06/21/2021 | 16:55 | 17:02 | 0.11667 | 5950 | 5960 | 10 | Slide | TTF: 90; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 85.71 | 4150 | 3200 | 950 | 174 | 190 | 170 | 155
06/21/2021 | 17:02 | 17:20 | 0.3 | 5960 | 6043 | 83 | Rotate |  | 5980 | 0.43 | 200.62 | 5975.29 | 95.47 | -74.15 | 95.47 | 0.71 |  |  | 30 | 80 | 900 | 10000 | 276.67 | 4150 | 3200 | 950 | 172 | 190 | 170 | 155
06/21/2021 | 17:25 | 17:40 | 0.25 | 6043 | 6137 | 94 | Rotate |  | 6074 | 0.36 | 197.49 | 6069.28 | 94.86 | -74.36 | 94.86 | 0.08 |  |  | 30 | 80 | 900 | 10000 | 376 | 4150 | 3200 | 950 | 172 | 190 | 170 | 155
06/21/2021 | 17:45 | 17:55 | 0.16667 | 6137 | 6231 | 94 | Rotate |  | 6168 | 0.33 | 210.52 | 6163.28 | 94.35 | -74.59 | 94.35 | 0.09 |  |  | 30 | 80 | 900 | 10000 | 564 | 4150 | 3200 | 950 | 172 | 190 | 170 | 155
06/21/2021 | 18:00 | 18:10 | 0.16667 | 6231 | 6325 | 94 | Rotate |  | 6262 | 0.36 | 209.87 | 6257.28 | 93.86 | -74.87 | 93.86 | 0.03 |  |  | 30 | 80 | 900 | 10000 | 564 | 4150 | 3200 | 950 | 172 | 190 | 170 | 155
06/21/2021 | 18:15 | 18:25 | 0.16667 | 6325 | 6345 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 18:25 | 18:35 | 0.16667 | 6345 | 6419 | 74 | Rotate |  | 6356 | 0.55 | 25.53 | 6351.28 | 94.01 | -74.82 | 94.01 | 0.97 |  |  | 32 | 80 | 900 | 12000 | 444 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 18:40 | 18:50 | 0.16667 | 6419 | 6513 | 94 | Rotate |  | 6450 | 0.53 | 37.47 | 6445.27 | 94.76 | -74.36 | 94.76 | 0.12 |  |  | 30 | 80 | 900 | 12000 | 564 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 18:55 | 19:05 | 0.16667 | 6513 | 6607 | 94 | Rotate |  | 6544 | 0.27 | 24.37 | 6539.27 | 95.31 | -74.01 | 95.31 | 0.29 |  |  | 30 | 80 | 900 | 12000 | 564 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 19:10 | 19:25 | 0.25 | 6607 | 6701 | 94 | Rotate |  | 6638 | 0.33 | 358.11 | 6633.27 | 95.78 | -73.93 | 95.78 | 0.16 |  |  | 30 | 80 | 900 | 12000 | 376 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 19:30 | 19:55 | 0.41667 | 6701 | 6806 | 105 | Rotate |  | 6733 | 0.33 | 355.51 | 6728.27 | 96.33 | -73.96 | 96.33 | 0.02 |  |  | 30 | 80 | 900 | 12000 | 252 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 20:00 | 20:15 | 0.25 | 6806 | 6816 | 10 | Slide | TTF: 160; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 40 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 20:15 | 20:25 | 0.16667 | 6816 | 6890 | 74 | Rotate |  | 6827 | 0.86 | 113.2 | 6822.27 | 96.32 | -73.33 | 96.32 | 1.12 |  |  | 30 | 80 | 900 | 12000 | 444 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 20:30 | 20:40 | 0.16667 | 6890 | 6984 | 94 | Rotate |  | 6921 | 1.12 | 122.32 | 6916.25 | 95.55 | -71.9 | 95.55 | 0.32 |  |  | 30 | 80 | 900 | 12000 | 564 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 20:45 | 21:00 | 0.25 | 6984 | 7079 | 95 | Rotate |  | 7016 | 1.02 | 119.65 | 7011.23 | 94.64 | -70.38 | 94.64 | 0.12 |  |  | 30 | 80 | 900 | 12000 | 380 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 21:05 | 21:15 | 0.16667 | 7079 | 7173 | 94 | Rotate |  | 7110 | 0.68 | 105.13 | 7105.22 | 94.08 | -69.12 | 94.08 | 0.43 |  |  | 30 | 80 | 900 | 12000 | 564 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 21:20 | 21:30 | 0.16667 | 7173 | 7268 | 95 | Rotate |  | 7204 | 0.48 | 81.25 | 7199.22 | 93.99 | -68.19 | 93.99 | 0.33 |  |  | 30 | 80 | 900 | 12000 | 570 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 21:40 | 21:50 | 0.16667 | 7268 | 7361 | 93 | Rotate |  | 7298 | 0.47 | 39.4 | 7293.22 | 94.35 | -67.56 | 94.35 | 0.36 |  |  | 30 | 80 | 900 | 12000 | 558 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 21:55 | 22:10 | 0.25 | 7361 | 7464 | 103 | Rotate |  | 7391 | 0.51 | 15.21 | 7386.21 | 95.04 | -67.21 | 95.04 | 0.22 |  |  | 30 | 80 | 900 | 12000 | 412 | 4400 | 3800 | 600 | 183 | 190 | 170 | 155
06/21/2021 | 22:15 | 22:25 | 0.16667 | 7464 | 7474 | 10 | Slide | TTF: 150; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 60 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/21/2021 | 22:25 | 22:35 | 0.16667 | 7474 | 7548 | 74 | Rotate |  | 7485 | 0.1 | 200.5 | 7480.21 | 95.37 | -67.13 | 95.37 | 0.65 |  |  | 30 | 80 | 900 | 12000 | 444 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/21/2021 | 22:40 | 23:00 | 0.33333 | 7548 | 7641 | 93 | Rotate |  | 7578 | 0.22 | 205.9 | 7573.21 | 95.13 | -67.23 | 95.13 | 0.13 |  |  | 30 | 80 | 900 | 12000 | 279 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/21/2021 | 23:05 | 23:20 | 0.25 | 7641 | 7735 | 94 | Rotate |  | 7672 | 0.43 | 285.87 | 7667.21 | 95.07 | -67.65 | 95.07 | 0.48 |  |  | 30 | 80 | 900 | 12000 | 376 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/21/2021 | 23:25 | 23:45 | 0.33333 | 7735 | 7838 | 103 | Rotate |  | 7765 | 0.84 | 285.93 | 7760.21 | 95.35 | -68.64 | 95.35 | 0.44 |  |  | 30 | 80 | 900 | 12000 | 309 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/21/2021 | 23:50 | 24:00 | 0.16667 | 7838 | 7850 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 72 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/22/2021 | 00:00 | 00:20 | 0.33333 | 7850 | 7940 | 90 | Rotate |  | 7859 | 0.64 | 352.31 | 7854.2 | 96.06 | -69.37 | 96.06 | 0.88 |  |  | 30 | 80 | 900 | 12000 | 270 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/22/2021 | 01:30 | 01:50 | 0.33333 | 7940 | 7952 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 36 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/22/2021 | 01:50 | 02:05 | 0.25 | 7952 | 8016 | 64 | Rotate |  | 7953 | 0.27 | 253.73 | 7948.2 | 96.52 | -69.66 | 96.52 | 0.78 |  |  | 30 | 80 | 900 | 12000 | 256 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/22/2021 | 02:10 | 02:30 | 0.33333 | 8016 | 8120 | 104 | Rotate |  | 8046 | 0.8 | 248.35 | 8041.19 | 96.22 | -70.47 | 96.22 | 0.57 |  |  | 30 | 80 | 900 | 12000 | 312 | 4400 | 3800 | 600 | 189 | 190 | 170 | 155
06/22/2021 | 02:35 | 02:55 | 0.33333 | 8120 | 8135 | 15 | Slide | TTF: 120; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 45 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 02:55 | 03:10 | 0.25 | 8135 | 8203 | 68 | Rotate |  | 8140 | 0.57 | 143.35 | 8135.19 | 95.6 | -70.8 | 95.6 | 1.17 |  |  | 30 | 80 | 900 | 14000 | 272 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 03:15 | 03:40 | 0.41667 | 8203 | 8297 | 94 | Rotate |  | 8234 | 0.9 | 124.35 | 8229.18 | 94.81 | -69.91 | 94.81 | 0.43 |  |  | 30 | 80 | 900 | 14000 | 225.6 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 04:10 | 04:30 | 0.33333 | 8297 | 8391 | 94 | Rotate |  | 8328 | 0.66 | 123.77 | 8323.17 | 94.09 | -68.85 | 94.09 | 0.26 |  |  | 30 | 80 | 900 | 14000 | 282 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 04:35 | 04:55 | 0.33333 | 8391 | 8485 | 94 | Rotate |  | 8422 | 0.59 | 126.94 | 8417.17 | 93.5 | -68.02 | 93.5 | 0.08 |  |  | 30 | 80 | 900 | 14000 | 282 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 05:00 | 05:20 | 0.33333 | 8485 | 8579 | 94 | Rotate |  | 8516 | 0.61 | 94.17 | 8511.16 | 93.17 | -67.13 | 93.17 | 0.36 |  |  | 30 | 80 | 900 | 14000 | 282 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 05:25 | 05:45 | 0.33333 | 8579 | 8673 | 94 | Rotate |  | 8610 | 0.56 | 85.61 | 8605.16 | 93.17 | -66.17 | 93.17 | 0.11 |  |  | 25 | 80 | 900 | 14000 | 282 | 4800 | 4200 | 600 | 192 | 255 | 230 | 200
06/22/2021 | 05:50 | 06:20 | 0.5 | 8673 | 8767 | 94 | Rotate |  | 8704 | 0.57 | 56.41 | 8699.15 | 93.46 | -65.33 | 93.46 | 0.3 |  |  | 25 | 80 | 900 | 14000 | 188 | 4800 | 4200 | 600 | 198 | 255 | 230 | 200
06/22/2021 | 06:25 | 06:45 | 0.33333 | 8767 | 8861 | 94 | Rotate |  | 8798 | 0.62 | 17.7 | 8793.15 | 94.21 | -64.78 | 94.21 | 0.42 |  |  | 25 | 80 | 900 | 14000 | 282 | 4800 | 4200 | 600 | 198 | 255 | 230 | 200
06/22/2021 | 08:45 | 09:15 | 0.5 | 8861 | 8955 | 94 | Rotate |  | 8892 | 0.65 | 355.67 | 8887.14 | 95.22 | -64.67 | 95.22 | 0.26 |  |  | 25 | 80 | 900 | 14000 | 188 | 4800 | 4200 | 600 | 198 | 255 | 230 | 200
06/22/2021 | 09:20 | 09:35 | 0.25 | 8955 | 9009 | 54 | Rotate |  | 8986 | 0.85 | 346.54 | 8981.13 | 96.43 | -64.87 | 96.43 | 0.25 |  |  | 25 | 80 | 700 | 14000 | 216 | 4100 | 3600 | 500 | 198 | 255 | 230 | 200
06/22/2021 | 13:25 | 13:40 | 0.25 | 9009 | 9049 | 40 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 160 | 4100 | 3600 | 500 | 185 | 255 | 230 | 200
06/22/2021 | 13:45 | 14:10 | 0.41667 | 9049 | 9143 | 94 | Rotate |  | 9080 | 1.07 | 341.32 | 9075.12 | 97.94 | -65.31 | 97.94 | 0.25 |  |  | 20 | 80 | 700 | 14000 | 225.6 | 4100 | 3600 | 500 | 185 | 255 | 230 | 200
06/22/2021 | 14:15 | 14:35 | 0.33333 | 9143 | 9237 | 94 | Rotate |  | 9174 | 1.33 | 335.34 | 9169.1 | 99.76 | -66.05 | 99.76 | 0.31 |  |  | 20 | 80 | 700 | 14000 | 282 | 4100 | 3600 | 500 | 192 | 255 | 230 | 200
06/22/2021 | 14:40 | 15:00 | 0.33333 | 9237 | 9331 | 94 | Rotate |  | 9268 | 1.66 | 329.64 | 9263.07 | 101.93 | -67.19 | 101.93 | 0.38 |  |  | 25 | 80 | 700 | 14000 | 282 | 4100 | 3600 | 500 | 198 | 255 | 230 | 200
06/22/2021 | 15:05 | 15:25 | 0.33333 | 9331 | 9424 | 93 | Rotate |  | 9361 | 2.01 | 325.88 | 9356.02 | 104.44 | -68.79 | 104.44 | 0.4 |  |  | 25 | 80 | 700 | 14000 | 279 | 4100 | 3600 | 500 | 198 | 255 | 230 | 200
06/22/2021 | 15:30 | 15:40 | 0.16667 | 9424 | 9434 | 10 | Slide | TTF: 150; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 700; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 60 | 4100 | 3600 | 500 | 198 | 255 | 230 | 200
06/22/2021 | 15:40 | 16:00 | 0.33333 | 9434 | 9518 | 84 | Rotate |  | 9455 | 1.61 | 300.71 | 9449.97 | 106.48 | -70.85 | 106.48 | 0.94 |  |  | 25 | 80 | 700 | 14000 | 252 | 4100 | 3600 | 500 | 205 | 255 | 230 | 200
06/22/2021 | 16:05 | 16:25 | 0.33333 | 9518 | 9612 | 94 | Rotate |  | 9549 | 0.68 | 301.23 | 9543.95 | 107.45 | -72.46 | 107.45 | 0.99 |  |  | 25 | 80 | 700 | 14000 | 282 | 4100 | 3600 | 500 | 205 | 255 | 230 | 200
06/22/2021 | 16:40 | 17:00 | 0.33333 | 9612 | 9706 | 94 | Rotate |  | 9643 | 0.79 | 8.2 | 9637.95 | 108.38 | -72.85 | 108.38 | 0.87 |  |  | 25 | 80 | 820 | 14000 | 282 | 5600 | 5000 | 600 | 205 | 255 | 230 | 200
06/22/2021 | 17:05 | 17:25 | 0.33333 | 9706 | 9801 | 95 | Rotate |  | 9738 | 1.29 | 6.27 | 9732.93 | 110.09 | -72.64 | 110.09 | 0.53 |  |  | 25 | 80 | 820 | 14000 | 285 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 17:30 | 18:20 | 0.83333 | 9801 | 10000 | 199 | Rotate |  | 9831 | 1.49 | 353.25 | 9825.9 | 112.33 | -72.66 | 112.33 | 0.4 |  |  | 25 | 80 | 820 | 14000 | 238.8 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 18:25 | 18:45 | 0.33333 | 10000 | 10015 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 45 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 18:45 | 19:05 | 0.33333 | 10015 | 10081 | 66 | Rotate |  | 10018 | 1.11 | 340.64 | 10012.83 | 117.28 | -73.93 | 117.28 | 0.79 |  |  | 25 | 80 | 820 | 14000 | 198 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 19:10 | 19:30 | 0.33333 | 10081 | 10175 | 94 | Rotate |  | 10112 | 0.95 | 327.46 | 10106.82 | 118.8 | -74.65 | 118.8 | 0.3 |  |  | 25 | 80 | 820 | 14000 | 282 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 19:35 | 20:00 | 0.41667 | 10175 | 10283 | 108 | Rotate |  | 10205 | 1.32 | 326.51 | 10199.8 | 120.34 | -75.66 | 120.34 | 0.4 |  |  | 25 | 80 | 820 | 14000 | 259.2 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 20:05 | 20:35 | 0.5 | 10283 | 10298 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 30 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 20:35 | 20:50 | 0.25 | 10298 | 10363 | 65 | Rotate |  | 10300 | 0.38 | 315.03 | 10294.79 | 121.47 | -76.48 | 121.47 | 1 |  |  | 25 | 80 | 820 | 14000 | 260 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 20:55 | 21:10 | 0.25 | 10363 | 10457 | 94 | Rotate |  | 10394 | 0.28 | 340.05 | 10388.79 | 121.91 | -76.78 | 121.91 | 0.18 |  |  | 25 | 80 | 820 | 14000 | 376 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 21:15 | 21:40 | 0.41667 | 10457 | 10570 | 113 | Rotate |  | 10488 | 1.15 | 356.28 | 10482.78 | 123.07 | -76.92 | 123.07 | 0.94 |  |  | 25 | 80 | 820 | 14000 | 271.2 | 5600 | 5000 | 600 | 210 | 265 | 245 | 220
06/22/2021 | 21:45 | 22:10 | 0.41667 | 10570 | 10585 | 15 | Slide | 160 | 10582 | 0.57 | 50.24 | 10576.77 | 124.31 | -76.62 | 124.31 | 1 |  |  | 25 | 80 | 820 | 16000 | 36 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/22/2021 | 22:10 | 22:20 | 0.16667 | 10585 | 10645 | 60 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 360 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/22/2021 | 22:25 | 22:40 | 0.25 | 10645 | 10738 | 93 | Rotate |  | 10675 | 0.82 | 134.06 | 10669.76 | 124.14 | -75.79 | 124.14 | 1.02 |  |  | 25 | 80 | 820 | 16000 | 372 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/22/2021 | 22:45 | 23:00 | 0.25 | 10738 | 10833 | 95 | Rotate |  | 10770 | 0.62 | 162.14 | 10764.76 | 123.18 | -75.14 | 123.18 | 0.42 |  |  | 25 | 80 | 820 | 16000 | 380 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/22/2021 | 23:05 | 23:20 | 0.25 | 10833 | 10926 | 93 | Rotate |  | 10863 | 0.71 | 210.73 | 10857.75 | 122.2 | -75.28 | 122.2 | 0.59 |  |  | 25 | 80 | 820 | 16000 | 372 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/22/2021 | 23:25 | 23:40 | 0.25 | 10926 | 11020 | 94 | Rotate |  | 10957 | 1.41 | 232.76 | 10951.74 | 121 | -76.5 | 121 | 0.85 |  |  | 25 | 80 | 820 | 16000 | 376 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/22/2021 | 23:45 | 23:55 | 0.16667 | 11020 | 11115 | 95 | Rotate |  | 11052 | 1.9 | 245.75 | 11046.7 | 119.65 | -78.87 | 119.65 | 0.65 |  |  | 25 | 80 | 820 | 16000 | 570 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 00:00 | 00:15 | 0.25 | 11115 | 11220 | 105 | Rotate |  | 11145 | 2.22 | 258.66 | 11139.64 | 118.66 | -82.04 | 118.66 | 0.6 |  |  | 25 | 80 | 820 | 14000 | 420 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 00:20 | 00:50 | 0.5 | 11220 | 11238 | 18 | Slide | TTF: 120; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 36 | 5900 | 5200 | 700 | 248 | 290 | 275 | 250
06/23/2021 | 00:50 | 01:05 | 0.25 | 11238 | 11302 | 64 | Rotate |  | 11239 | 1.24 | 229.24 | 11233.59 | 117.64 | -84.6 | 117.64 | 1.37 |  |  | 25 | 80 | 820 | 14000 | 256 | 5900 | 5200 | 700 | 248 | 290 | 275 | 250
06/23/2021 | 01:10 | 01:25 | 0.25 | 11302 | 11397 | 95 | Rotate |  | 11334 | 1.43 | 216.8 | 11328.57 | 116.02 | -86.09 | 116.02 | 0.36 |  |  | 25 | 80 | 820 | 14000 | 380 | 5900 | 5200 | 700 | 248 | 290 | 275 | 250
06/23/2021 | 01:30 | 02:00 | 0.5 | 11397 | 11490 | 93 | Rotate |  | 11427 | 2.01 | 227.04 | 11421.53 | 113.98 | -87.97 | 113.98 | 0.7 |  |  | 25 | 80 | 820 | 14000 | 186 | 5900 | 5200 | 700 | 248 | 290 | 275 | 250
06/23/2021 | 02:05 | 02:35 | 0.5 | 11490 | 11598 | 108 | Rotate |  | 11522 | 2.13 | 233.72 | 11516.46 | 111.8 | -90.62 | 111.8 | 0.28 |  |  | 25 | 80 | 820 | 14000 | 216 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 02:40 | 03:25 | 0.75 | 11598 | 11616 | 18 | Slide | TTF: 55; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 24 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 03:25 | 03:50 | 0.41667 | 11616 | 11679 | 63 | Rotate |  | 11616 | 1.49 | 252.88 | 11610.42 | 110.41 | -93.19 | 110.41 | 0.93 |  |  | 25 | 80 | 820 | 14000 | 151.2 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 03:55 | 04:20 | 0.41667 | 11679 | 11785 | 106 | Rotate |  | 11709 | 1.65 | 267.6 | 11703.38 | 109.99 | -95.69 | 109.99 | 0.46 |  |  | 25 | 80 | 820 | 14000 | 254.4 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 04:25 | 05:00 | 0.58333 | 11785 | 11802 | 17 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 29.14 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 05:00 | 05:50 | 0.83333 | 11802 | 11913 | 111 | Rotate |  | 11802 | 1.04 | 265.94 | 11796.36 | 109.88 | -97.87 | 109.88 | 0.66 |  |  | 25 | 80 | 820 | 14000 | 133.2 | 5900 | 5200 | 700 | 241 | 290 | 275 | 250
06/23/2021 | 05:50 | 07:15 | 1.4167 | 11913 | 11959 | 46 | Slide | TTF: 140; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 820; Drilling Parameters ROP: 32.47 | 5900 | 5200 | 700 | 250 | 325 | 300 | 280
06/23/2021 | 07:20 | 10:40 | 3.3333 | 11959 | 12052 | 93 | Slide | 130 | 11989 | 2.07 | 268.94 | 11983.31 | 110.09 | -101.93 | 110.09 | 1.24 |  |  | 25 |  | 820 |  | 27.9 | 5500 | 5200 | 300 | 250 | 325 | 300 | 280
06/23/2021 | 10:45 | 14:35 | 3.8333 | 12052 | 12146 | 94 | Slide | 130 | 12083 | 2.84 | 156.97 | 12077.26 | 107.92 | -102.72 | 107.92 | 4.35 |  |  | 25 |  | 820 |  | 24.52 | 5500 | 5200 | 300 | 250 | 325 | 300 | 280
06/23/2021 | 14:40 | 17:45 | 3.0833 | 12146 | 12210 | 64 | Slide | 140 | 12183 | 10.33 | 134.78 | 12176.54 | 99.31 | -95.37 | 99.31 | 7.77 |  |  | 25 |  | 820 |  | 20.76 | 5500 | 5200 | 300 | 250 | 325 | 300 | 280
06/23/2021 | 17:50 | 19:20 | 1.5 | 12210 | 12240 | 30 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 820; Drilling Parameters ROP: 20 | 5500 | 5200 | 300 | 250 | 325 | 300 | 280
06/23/2021 | 19:25 | 20:00 | 0.58333 | 12240 | 12246 | 6 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 820; Drilling Parameters ROP: 10.29 | 5500 | 5200 | 300 | 250 | 325 | 300 | 280
06/23/2021 | 20:30 | 20:35 | 0.083333 | 12246 | 12250 | 4 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters FLOW: 820; Drilling Parameters ROP: 48 | 5500 | 5200 | 300 | 250 | 325 | 300 | 280

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 406 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3980
Site: |  |  |  |  | Ozark - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 832
Well Name: |  |  |  |  | Ozark 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 406 |  | VS Azimuth: |  | 141.87 |  | Rotate: |  | 3148
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/27/2021 | 09:15 | 09:25 | 0.16667 | 12250 | 12260 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 200; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 60 | 2200 | 2000 | 200 | 257 | 250 | 225 | 205
06/27/2021 | 10:35 | 11:30 | 0.91667 | 12260 | 12281 | 21 | Slide | TTF: 20; Drilling Parameters WOB: 14; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 22.91 | 5600 | 5300 | 300 | 257 | 250 | 225 | 205
06/27/2021 | 11:40 | 12:50 | 1.1667 | 12281 | 12376 | 95 | Slide | 0 | 12308 | 18.38 | 139.86 | 12297.54 | 76.31 | -74.68 | 76.31 | 6.51 |  |  | 22 |  | 400 |  | 81.43 | 6000 | 5300 | 700 | 257 | 250 | 225 | 205
06/27/2021 | 13:05 | 14:25 | 1.3333 | 12376 | 12425 | 49 | Slide | 20 | 12403 | 26.28 | 146.12 | 12385.36 | 47.35 | -53.26 | 47.35 | 8.67 |  |  | 22 |  | 400 |  | 36.75 | 5500 | 5300 | 200 | 265 | 250 | 225 | 205
06/27/2021 | 14:30 | 14:50 | 0.33333 | 12425 | 12445 | 20 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 60 | 6000 | 5300 | 700 | 270 | 250 | 225 | 205
06/27/2021 | 14:50 | 15:20 | 0.5 | 12445 | 12471 | 26 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 52 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 15:30 | 16:45 | 1.25 | 12471 | 12566 | 95 | Slide | -20 | 12498 | 34.6 | 146.72 | 12467.2 | 7.27 | -26.69 | 7.27 | 8.76 |  |  | 22 |  | 400 |  | 76 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 16:55 | 17:15 | 0.33333 | 12566 | 12586 | 20 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 17:15 | 18:05 | 0.83333 | 12586 | 12660 | 74 | Slide | -10 | 12592 | 42.06 | 144.87 | 12540.88 | -40.86 | 6.12 | -40.86 | 8.03 |  |  | 22 |  | 400 |  | 88.8 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 18:10 | 18:30 | 0.33333 | 12660 | 12680 | 20 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 18:30 | 19:40 | 1.1667 | 12680 | 12756 | 76 | Slide | -10 | 12688 | 51.93 | 141.23 | 12606.29 | -96.77 | 48.4 | -96.77 | 10.65 |  |  | 22 |  | 400 |  | 65.14 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 19:45 | 20:05 | 0.33333 | 12756 | 12756 |  | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400 | 5900 | 5300 | 600 | 272 | 250 | 225 | 205
06/27/2021 | 20:05 | 21:00 | 0.91667 | 12756 | 12851 | 95 | Slide | 0 | 12783 | 57.88 | 141.86 | 12660.89 | -157.62 | 96.7 | -157.62 | 6.29 |  |  | 22 |  | 400 |  | 103.64 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/27/2021 | 21:05 | 21:20 | 0.25 | 12851 | 12876 | 25 | Rotate |  | 12876 | 68.15 | 142.31 | 12703.03 | -222.92 | 147.55 | -222.92 | 11.05 |  |  | 22 |  | 400 |  | 100 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/27/2021 | 21:20 | 22:05 | 0.75 | 12876 | 12944 | 68 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 90.67 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/27/2021 | 22:10 | 22:40 | 0.5 | 12944 | 12994 | 50 | Rotate |  | 12970 | 76.14 | 140.65 | 12731.83 | -292.85 | 203.25 | -292.85 | 8.66 |  |  | 22 |  | 400 |  | 100 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/27/2021 | 23:30 | 24:00 | 0.5 | 12994 | 13010 | 16 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 32 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 00:00 | 00:20 | 0.33333 | 13010 | 13038 | 28 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 84 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 00:25 | 01:20 | 0.91667 | 13038 | 13112 | 74 | Rotate |  | 13064 | 74.31 | 140.23 | 12755.8 | -362.92 | 261.13 | -362.92 | 1.99 |  |  | 22 |  | 400 |  | 80.73 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 01:20 | 01:55 | 0.58333 | 13112 | 13132 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 34.29 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 02:00 | 02:40 | 0.66667 | 13132 | 13162 | 30 | Slide | 0 | 13159 | 79.6 | 141.21 | 12777.24 | -434.54 | 319.69 | -434.54 | 5.66 |  |  | 22 |  | 400 |  | 45 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 02:40 | 03:20 | 0.66667 | 13162 | 13227 | 65 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 97.5 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 03:25 | 04:20 | 0.91667 | 13227 | 13277 | 50 | Slide | 0 | 13254 | 84.21 | 141.36 | 12790.61 | -507.9 | 378.5 | -507.9 | 4.86 |  |  | 22 |  | 400 |  | 54.55 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 04:20 | 04:50 | 0.5 | 13277 | 13377 | 100 | Rotate |  | 13349 | 88.87 | 140.83 | 12796.34 | -581.68 | 438.04 | -581.68 | 4.94 |  |  | 22 |  | 400 |  | 200 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 05:00 | 05:40 | 0.66667 | 13377 | 13417 | 40 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 68.57 | 5900 | 5300 | 600 | 277 | 250 | 230 | 210
06/28/2021 | 05:45 | 05:55 | 0.16667 | 13417 | 13427 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 60 | 6200 | 5400 | 800 | 288 | 250 | 230 | 210
06/28/2021 | 05:55 | 06:10 | 0.25 | 13427 | 13437 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 40 | 5700 | 5400 | 300 | 288 | 250 | 230 | 210
06/28/2021 | 06:10 | 06:35 | 0.41667 | 13437 | 13511 | 74 | Rotate |  | 13443 | 88.06 | 140.8 | 12798.86 | -654.51 | 497.41 | -654.51 | 0.86 |  |  | 30 | 80 | 400 | 12000 | 177.6 | 6200 | 5400 | 800 | 288 | 250 | 230 | 210
06/28/2021 | 06:40 | 07:10 | 0.5 | 13511 | 13605 | 94 | Rotate |  | 13537 | 88.35 | 140.78 | 12801.81 | -727.31 | 556.81 | -727.31 | 0.31 |  |  | 30 | 80 | 370 | 12000 | 188 | 6000 | 5200 | 800 | 295 | 250 | 230 | 210
06/28/2021 | 07:15 | 07:20 | 0.083333 | 13605 | 13615 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 120 | 6000 | 5200 | 800 | 295 | 255 | 225 | 205
06/28/2021 | 07:20 | 07:40 | 0.33333 | 13615 | 13627 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 36 | 5600 | 5200 | 400 | 295 | 255 | 225 | 205
06/28/2021 | 07:40 | 07:50 | 0.16667 | 13627 | 13646 | 19 | Rotate |  | 13630 | 87.11 | 140.67 | 12805.49 | -799.24 | 615.63 | -799.24 | 1.34 |  |  | 30 | 80 | 370 | 12000 | 114 | 6000 | 5200 | 800 | 295 | 255 | 225 | 205
06/28/2021 | 08:10 | 08:30 | 0.33333 | 13646 | 13698 | 52 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 156 | 6000 | 5200 | 800 | 293 | 255 | 225 | 205
06/28/2021 | 08:35 | 09:10 | 0.58333 | 13698 | 13793 | 95 | Rotate |  | 13725 | 86.34 | 140.91 | 12810.92 | -872.73 | 675.59 | -872.73 | 0.85 |  |  | 30 | 80 | 370 | 10000 | 162.86 | 6100 | 5300 | 800 | 293 | 255 | 225 | 205
06/28/2021 | 09:15 | 09:50 | 0.58333 | 13793 | 13888 | 95 | Rotate |  | 13820 | 86.72 | 140.95 | 12816.67 | -946.35 | 735.35 | -946.35 | 0.4 |  |  | 25 | 80 | 370 | 10000 | 162.86 | 6100 | 5300 | 800 | 297 | 255 | 225 | 205
06/28/2021 | 09:55 | 10:45 | 0.83333 | 13888 | 13983 | 95 | Rotate |  | 13915 | 87.18 | 141.04 | 12821.72 | -1020.07 | 795.06 | -1020.07 | 0.49 |  |  | 25 | 80 | 370 | 10000 | 114 | 6100 | 5300 | 800 | 298 | 255 | 225 | 205
06/28/2021 | 10:50 | 11:35 | 0.75 | 13983 | 14077 | 94 | Rotate |  | 14009 | 87.25 | 140.95 | 12826.29 | -1093.03 | 854.15 | -1093.03 | 0.12 |  |  | 30 | 80 | 370 | 10000 | 125.33 | 6100 | 5300 | 800 | 300 | 255 | 225 | 205
06/28/2021 | 11:40 | 12:25 | 0.75 | 14077 | 14171 | 94 | Rotate |  | 14103 | 86.56 | 141.02 | 12831.36 | -1165.96 | 913.24 | -1165.96 | 0.74 |  |  | 25 | 80 | 340 | 11000 | 125.33 | 5800 | 5000 | 800 | 300 | 255 | 225 | 205
06/28/2021 | 12:55 | 13:00 | 0.083333 | 14171 | 14181 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 120 | 6200 | 5400 | 800 | 306 | 255 | 225 | 205
06/28/2021 | 13:00 | 13:20 | 0.33333 | 14181 | 14191 | 10 | Slide | TTF: 20; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 380; Drilling Parameters ROP: 30 | 5700 | 5400 | 300 | 306 | 255 | 225 | 205
06/28/2021 | 13:20 | 13:50 | 0.5 | 14191 | 14265 | 74 | Rotate |  | 14197 | 88.68 | 141.94 | 12835.27 | -1239.44 | 971.73 | -1239.44 | 2.46 |  |  | 25 | 80 | 380 | 11000 | 148 | 6200 | 5400 | 800 | 306 | 255 | 225 | 205
06/28/2021 | 13:55 | 14:25 | 0.5 | 14265 | 14360 | 95 | Rotate |  | 14292 | 89.53 | 142.09 | 12836.75 | -1314.3 | 1030.19 | -1314.3 | 0.91 |  |  | 30 | 80 | 380 | 11000 | 190 | 6200 | 5400 | 800 | 309 | 255 | 225 | 205
06/28/2021 | 14:30 | 14:35 | 0.083333 | 14360 | 14370 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 120 | 6400 | 5400 | 1000 | 309 | 255 | 225 | 205
06/28/2021 | 14:35 | 15:00 | 0.41667 | 14370 | 14384 | 14 | Slide | TTF: 180; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 380; Drilling Parameters ROP: 33.6 | 5800 | 5500 | 300 | 309 | 262 | 225 | 202
06/28/2021 | 15:00 | 15:25 | 0.41667 | 14384 | 14456 | 72 | Rotate |  | 14388 | 88.47 | 141.18 | 12838.43 | -1389.56 | 1089.76 | -1389.56 | 1.46 |  |  | 30 | 80 | 380 | 11000 | 172.8 | 6700 | 5500 | 1200 | 309 | 262 | 225 | 202
06/28/2021 | 15:30 | 16:00 | 0.5 | 14456 | 14555 | 99 | Rotate |  | 14482 | 88.9 | 141.15 | 12840.58 | -1462.76 | 1148.69 | -1462.76 | 0.46 |  |  | 35 | 80 | 380 | 11000 | 198 | 6700 | 5500 | 1200 | 309 | 262 | 225 | 202
06/28/2021 | 16:05 | 16:10 | 0.083333 | 14555 | 14565 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 120 | 6700 | 5500 | 1200 | 309 | 262 | 225 | 202
06/28/2021 | 16:10 | 16:30 | 0.33333 | 14565 | 14577 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 380; Drilling Parameters ROP: 36 | 5900 | 5500 | 400 | 310 | 262 | 225 | 202
06/28/2021 | 16:30 | 16:50 | 0.33333 | 14577 | 14645 | 68 | Rotate |  | 14577 | 87.81 | 140.87 | 12843.31 | -1536.57 | 1208.44 | -1536.57 | 1.18 |  |  | 32 | 80 | 380 | 12000 | 204 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 16:55 | 17:20 | 0.41667 | 14645 | 14740 | 95 | Rotate |  | 14672 | 88.14 | 140.99 | 12846.67 | -1610.28 | 1268.28 | -1610.28 | 0.37 |  |  | 32 | 80 | 380 | 12000 | 228 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 17:25 | 17:30 | 0.083333 | 14740 | 14750 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 120 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 17:30 | 18:00 | 0.5 | 14750 | 14765 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 30 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 18:00 | 18:55 | 0.91667 | 14765 | 14930 | 165 | Rotate |  | 14768 | 86.63 | 141.74 | 12851.05 | -1685.19 | 1328.15 | -1685.19 | 1.76 |  |  | 32 | 80 | 380 | 12000 | 180 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 19:05 | 19:30 | 0.41667 | 14930 | 15024 | 94 | Rotate |  | 14956 | 86.25 | 142.01 | 12863.05 | -1832.77 | 1444 | -1832.77 | 0.16 |  |  | 32 | 80 | 380 | 12000 | 225.6 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 19:35 | 20:10 | 0.58333 | 15024 | 15130 | 106 | Rotate |  | 15050 | 86 | 142.16 | 12869.4 | -1906.75 | 1501.63 | -1906.75 | 0.31 |  |  | 32 | 80 | 380 | 12000 | 181.71 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 20:20 | 20:45 | 0.41667 | 15130 | 15142 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 28.8 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 20:45 | 21:10 | 0.41667 | 15142 | 15213 | 71 | Rotate |  | 15145 | 87.64 | 142.83 | 12874.67 | -1982 | 1559.38 | -1982 | 1.86 |  |  | 32 | 80 | 380 | 12000 | 170.4 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 21:20 | 21:45 | 0.41667 | 15213 | 15308 | 95 | Rotate |  | 15240 | 88.09 | 143.23 | 12878.21 | -2057.85 | 1616.47 | -2057.85 | 0.63 |  |  | 32 | 80 | 380 | 12000 | 228 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 22:00 | 22:40 | 0.66667 | 15308 | 15414 | 106 | Rotate |  | 15334 | 88.71 | 143.28 | 12880.83 | -2133.14 | 1672.69 | -2133.14 | 0.66 |  |  | 32 | 80 | 380 | 12000 | 159 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 22:45 | 23:10 | 0.41667 | 15414 | 15424 | 10 | Slide | TTF: -140; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 24 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 23:10 | 23:35 | 0.41667 | 15424 | 15498 | 74 | Rotate |  | 15430 | 86.31 | 141.79 | 12885.01 | -2209.26 | 1731.02 | -2209.26 | 2.94 |  |  | 32 | 80 | 380 | 12000 | 177.6 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/28/2021 | 23:40 | 24:00 | 0.33333 | 15498 | 15558 | 60 | Rotate |  | 15524 | 86.21 | 142.02 | 12891.14 | -2283.08 | 1788.89 | -2283.08 | 0.27 |  |  | 32 | 80 | 380 | 12000 | 180 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/29/2021 | 00:00 | 00:15 | 0.25 | 15558 | 15607 | 49 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 196 | 6600 | 5500 | 1100 | 311 | 262 | 225 | 202
06/29/2021 | 00:50 | 01:10 | 0.33333 | 15607 | 15615 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 24 | 6600 | 5500 | 1100 | 329 | 262 | 225 | 202
06/29/2021 | 01:10 | 01:35 | 0.41667 | 15615 | 15687 | 72 | Rotate |  | 15619 | 87.41 | 143.2 | 12896.42 | -2358.44 | 1846.49 | -2358.44 | 1.77 |  |  | 32 | 80 | 380 | 12000 | 172.8 | 6600 | 5500 | 1100 | 329 | 262 | 225 | 202
06/29/2021 | 01:40 | 02:15 | 0.58333 | 15687 | 15782 | 95 | Rotate |  | 15714 | 87.25 | 143.29 | 12900.85 | -2434.47 | 1903.27 | -2434.47 | 0.19 |  |  | 32 | 80 | 380 | 12000 | 162.86 | 6600 | 5500 | 1100 | 329 | 262 | 225 | 202
06/29/2021 | 02:20 | 02:35 | 0.25 | 15782 | 15795 | 13 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 380; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 52 | 6600 | 5500 | 1100 | 329 | 262 | 225 | 202
06/29/2021 | 02:35 | 03:00 | 0.41667 | 15795 | 15805 | 10 | Slide | TTF: -45; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 24 | 6300 | 5100 | 1200 | 329 | 262 | 225 | 202
06/29/2021 | 03:00 | 03:35 | 0.58333 | 15805 | 15877 | 72 | Rotate |  | 15809 | 88.47 | 141.61 | 12904.4 | -2509.73 | 1961.13 | -2509.73 | 2.18 |  |  | 32 | 80 | 370 | 13000 | 123.43 | 6300 | 5100 | 1200 | 329 | 262 | 225 | 202
06/29/2021 | 03:40 | 04:20 | 0.66667 | 15877 | 15971 | 94 | Rotate |  | 15903 | 89.44 | 141.89 | 12906.11 | -2583.54 | 2019.31 | -2583.54 | 1.07 |  |  | 32 | 80 | 370 | 13000 | 141 | 6300 | 5100 | 1200 | 329 | 262 | 225 | 202
06/29/2021 | 04:25 | 05:05 | 0.66667 | 15971 | 16066 | 95 | Rotate |  | 15998 | 90.53 | 142.06 | 12906.14 | -2658.37 | 2077.83 | -2658.37 | 1.16 |  |  | 32 | 80 | 370 | 13000 | 142.5 | 6300 | 5100 | 1200 | 329 | 262 | 225 | 202
06/29/2021 | 05:10 | 05:20 | 0.16667 | 16066 | 16078 | 12 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 72 | 6300 | 5100 | 1200 | 329 | 262 | 225 | 202
06/29/2021 | 05:20 | 05:45 | 0.41667 | 16078 | 16088 | 10 | Slide | TTF: -150; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 24 | 6300 | 5100 | 1200 | 330 | 262 | 225 | 202
06/29/2021 | 05:45 | 06:25 | 0.66667 | 16088 | 16161 | 73 | Rotate |  | 16093 | 89.58 | 140.74 | 12906.04 | -2732.61 | 2137.1 | -2732.61 | 1.71 |  |  | 38 | 80 | 370 | 20000 | 109.5 | 6400 | 5100 | 1300 | 331 | 280 | 220 | 190
06/29/2021 | 06:30 | 06:35 | 0.083333 | 16161 | 16171 | 10 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 6400 | 5100 | 1300 | 331 | 280 | 220 | 190
06/29/2021 | 06:35 | 07:00 | 0.41667 | 16171 | 16181 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 24 | 5500 | 5100 | 400 | 325 | 280 | 220 | 190
06/29/2021 | 07:00 | 07:50 | 0.83333 | 16181 | 16230 | 49 | Rotate |  | 16187 | 89.2 | 141.16 | 12907.05 | -2805.61 | 2196.31 | -2805.61 | 0.6 |  |  | 40 | 80 | 370 | 22000 | 58.8 | 6400 | 5100 | 1300 | 331 | 280 | 220 | 190

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 406 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2133
Site: |  |  |  |  | Ozark - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 75
Well Name: |  |  |  |  | Ozark 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 0.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 406 |  | VS Azimuth: |  | 141.87 |  | Rotate: |  | 2058
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/30/2021 | 19:05 | 19:15 | 0.16667 | 16230 | 16255 | 25 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 150 | 6400 | 5400 | 1000 | 327 | 260 | 220 | 190
06/30/2021 | 19:20 | 19:40 | 0.33333 | 16255 | 16274 | 19 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 57 | 6400 | 5400 | 1000 | 327 | 260 | 220 | 190
06/30/2021 | 19:40 | 20:00 | 0.33333 | 16274 | 16284 | 10 | Slide | 180 | 16282 | 88.17 | 141.87 | 12909.23 | -2879.95 | 2255.42 | -2879.95 | 1.32 |  |  | 25 | 80 | 360 | 14000 | 30 | 6400 | 5400 | 1000 | 327 | 260 | 220 | 190
06/30/2021 | 20:00 | 20:25 | 0.41667 | 16284 | 16350 | 66 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 158.4 | 6400 | 5400 | 1000 | 327 | 260 | 220 | 190
06/30/2021 | 20:35 | 21:00 | 0.41667 | 16350 | 16444 | 94 | Rotate |  | 16376 | 87.7 | 141.26 | 12912.61 | -2953.53 | 2313.81 | -2953.53 | 0.82 |  |  | 25 | 80 | 360 | 14000 | 225.6 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
06/30/2021 | 21:10 | 21:40 | 0.5 | 16444 | 16539 | 95 | Rotate |  | 16471 | 87.75 | 141.09 | 12916.38 | -3027.49 | 2373.32 | -3027.49 | 0.19 |  |  | 25 | 80 | 360 | 14000 | 190 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
06/30/2021 | 21:45 | 22:15 | 0.5 | 16539 | 16632 | 93 | Rotate |  | 16564 | 87.32 | 141.22 | 12920.38 | -3099.85 | 2431.6 | -3099.85 | 0.48 |  |  | 25 | 80 | 360 | 14000 | 186 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
06/30/2021 | 22:25 | 22:55 | 0.5 | 16632 | 16727 | 95 | Rotate |  | 16659 | 86.88 | 142.83 | 12925.19 | -3174.64 | 2489.98 | -3174.64 | 1.75 |  |  | 25 | 80 | 360 | 14000 | 190 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
06/30/2021 | 23:00 | 23:10 | 0.16667 | 16727 | 16739 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 72 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
06/30/2021 | 23:10 | 23:30 | 0.33333 | 16739 | 16747 | 8 | Slide | TTF: -90; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 24 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
06/30/2021 | 23:30 | 23:55 | 0.41667 | 16747 | 16821 | 74 | Rotate |  | 16753 | 86.04 | 141.69 | 12930.99 | -3248.83 | 2547.4 | -3248.83 | 1.5 |  |  | 25 | 80 | 360 | 14000 | 177.6 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 00:00 | 00:35 | 0.58333 | 16821 | 16916 | 95 | Rotate |  | 16848 | 87.69 | 141.82 | 12936.19 | -3323.33 | 2606.12 | -3323.33 | 1.74 |  |  | 25 | 80 | 360 | 14000 | 162.86 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 00:45 | 01:15 | 0.5 | 16916 | 17010 | 94 | Rotate |  | 16942 | 88.4 | 142.25 | 12939.4 | -3397.39 | 2663.91 | -3397.39 | 0.88 |  |  | 25 | 80 | 360 | 14000 | 188 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 01:25 | 01:30 | 0.083333 | 17010 | 17025 | 15 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 180 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 01:30 | 01:55 | 0.41667 | 17025 | 17037 | 12 | Slide | TTF: -150; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 28.8 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 01:55 | 02:20 | 0.41667 | 17037 | 17105 | 68 | Rotate |  | 17037 | 87.03 | 141.52 | 12943.18 | -3472.07 | 2722.5 | -3472.07 | 1.63 |  |  | 25 | 80 | 360 | 14000 | 163.2 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 02:30 | 03:00 | 0.5 | 17105 | 17199 | 94 | Rotate |  | 17131 | 87.11 | 141.32 | 12947.99 | -3545.46 | 2781.04 | -3545.46 | 0.23 |  |  | 25 | 80 | 360 | 14000 | 188 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 03:10 | 03:15 | 0.083333 | 17199 | 17210 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 132 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 03:15 | 03:40 | 0.41667 | 17210 | 17220 | 10 | Slide | TTF: -160; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 24 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 03:40 | 04:10 | 0.5 | 17220 | 17292 | 72 | Rotate |  | 17224 | 86.36 | 141.59 | 12953.29 | -3618.08 | 2838.9 | -3618.08 | 0.86 |  |  | 25 | 80 | 360 | 14000 | 144 | 6400 | 5400 | 1000 | 331 | 260 | 220 | 190
07/01/2021 | 04:20 | 04:50 | 0.5 | 17292 | 17387 | 95 | Rotate |  | 17319 | 86.19 | 141.42 | 12959.46 | -3692.28 | 2897.91 | -3692.28 | 0.25 |  |  | 25 | 80 | 360 | 14000 | 190 | 6400 | 5400 | 1000 | 334 | 260 | 220 | 190
07/01/2021 | 05:00 | 05:30 | 0.5 | 17387 | 17482 | 95 | Rotate |  | 17414 | 85.99 | 141.83 | 12965.94 | -3766.58 | 2956.75 | -3766.58 | 0.48 |  |  | 20 | 80 | 360 | 14000 | 190 | 6200 | 5400 | 800 | 336 | 260 | 220 | 190
07/01/2021 | 05:40 | 06:10 | 0.5 | 17482 | 17577 | 95 | Rotate |  | 17509 | 86.05 | 142.18 | 12972.53 | -3841.26 | 3015.09 | -3841.26 | 0.37 |  |  | 20 | 80 | 360 | 14000 | 190 | 6200 | 5400 | 800 | 336 | 260 | 220 | 190
07/01/2021 | 06:15 | 07:00 | 0.75 | 17577 | 17670 | 93 | Rotate |  | 17602 | 86.19 | 142.17 | 12978.82 | -3914.55 | 3071.99 | -3914.55 | 0.15 |  |  | 20 | 80 | 360 | 14000 | 124 | 6200 | 5400 | 800 | 336 | 310 | 215 | 180
07/01/2021 | 07:05 | 07:45 | 0.66667 | 17670 | 17765 | 95 | Rotate |  | 17697 | 86.23 | 142.62 | 12985.1 | -3989.65 | 3129.83 | -3989.65 | 0.47 |  |  | 20 | 80 | 360 | 14000 | 142.5 | 6200 | 5400 | 800 | 338 | 310 | 215 | 180
07/01/2021 | 07:50 | 08:25 | 0.58333 | 17765 | 17860 | 95 | Rotate |  | 17792 | 86.25 | 143 | 12991.33 | -4065.17 | 3187.13 | -4065.17 | 0.4 |  |  | 21 | 80 | 360 | 14000 | 162.86 | 6200 | 5400 | 800 | 338 | 310 | 215 | 180
07/01/2021 | 08:30 | 09:10 | 0.66667 | 17860 | 17955 | 95 | Rotate |  | 17887 | 86.79 | 143.42 | 12997.1 | -4141.11 | 3243.92 | -4141.11 | 0.72 |  |  | 21 | 80 | 360 | 14000 | 142.5 | 6200 | 5400 | 800 | 340 | 310 | 215 | 180
07/01/2021 | 09:15 | 09:50 | 0.58333 | 17955 | 18049 | 94 | Rotate |  | 17981 | 88.02 | 143.54 | 13001.35 | -4216.57 | 3299.8 | -4216.57 | 1.31 |  |  | 21 | 80 | 360 | 14000 | 161.14 | 6200 | 5400 | 800 | 338 | 310 | 215 | 180
07/01/2021 | 09:55 | 10:00 | 0.083333 | 18049 | 18059 | 10 | Rotate | Drilling Parameters WOB: 21; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 120 | 6200 | 5400 | 800 | 338 | 310 | 215 | 180
07/01/2021 | 10:00 | 10:45 | 0.75 | 18059 | 18073 | 14 | Slide | TTF: -120; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 360; Drilling Parameters ROP: 18.67 | 5700 | 5400 | 300 | 331 | 310 | 215 | 180
07/01/2021 | 10:45 | 11:20 | 0.58333 | 18073 | 18144 | 71 | Rotate |  | 18076 | 87.54 | 142.21 | 13005.03 | -4292.26 | 3357.1 | -4292.26 | 1.49 |  |  | 21 | 80 | 360 | 14000 | 121.71 | 6200 | 5400 | 800 | 333 | 310 | 215 | 180
07/01/2021 | 11:25 | 12:10 | 0.75 | 18144 | 18238 | 94 | Rotate |  | 18170 | 87.93 | 141.53 | 13008.75 | -4366.14 | 3415.09 | -4366.14 | 0.83 |  |  | 20 | 80 | 360 | 14000 | 125.33 | 6200 | 5400 | 800 | 334 | 310 | 215 | 180
07/01/2021 | 12:15 | 12:20 | 0.083333 | 18238 | 18247 | 9 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 108 | 6200 | 5400 | 800 | 334 | 310 | 215 | 180
07/01/2021 | 12:20 | 12:55 | 0.58333 | 18247 | 18256 | 9 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 360; Drilling Parameters ROP: 15.43 | 5700 | 5400 | 300 | 331 | 310 | 215 | 180
07/01/2021 | 12:55 | 13:35 | 0.66667 | 18256 | 18333 | 77 | Rotate |  | 18265 | 87.21 | 143.3 | 13012.78 | -4441.35 | 3472.98 | -4441.35 | 2.01 |  |  | 20 | 80 | 360 | 14000 | 115.5 | 6200 | 5400 | 800 | 332 | 310 | 215 | 180
07/01/2021 | 13:40 | 13:45 | 0.083333 | 18333 | 18343 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 120 | 6200 | 5400 | 800 | 332 | 310 | 215 | 180
07/01/2021 | 13:45 | 14:20 | 0.58333 | 18343 | 18355 | 12 | Slide | TTF: -110; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 360; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 20.57 | 6200 | 5400 | 800 | 332 | 310 | 215 | 180
07/01/2021 | 14:20 | 14:30 | 0.16667 | 18355 | 18363 | 8 | Rotate |  | 18361 | 86.01 | 142.36 | 13018.45 | -4517.72 | 3530.88 | -4517.72 | 1.59 |  |  | 20 | 80 | 360 | 14000 | 48 | 6200 | 5400 | 800 | 332 | 310 | 215 | 180

## BHA_5_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 |  |  |  |  | RKB: |  |  |  | 406 |  | North Reference: |  | GRID |  | Total Drilled: |  | 608
Site: |  |  |  |  | Ozark - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 22
Well Name: |  |  |  |  | Ozark 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 406 |  | VS Azimuth: |  | 141.87 |  | Rotate: |  | 586
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/03/2021 | 06:35 | 07:00 | 0.41667 | 18363 | 18429 | 66 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 355; Drilling Parameters Tq: 13800; Drilling Parameters ROP: 158.4 | 6300 | 5700 | 600 | 330 | 310 | 220 | 160
07/03/2021 | 07:05 | 07:40 | 0.58333 | 18429 | 18523 | 94 | Rotate |  | 18455 | 86.09 | 142.07 | 13024.93 | -4591.83 | 3588.33 | -4591.83 | 0.32 |  |  | 25 | 80 | 350 | 13200 | 161.14 | 6100 | 5400 | 700 | 331 | 310 | 220 | 160
07/03/2021 | 07:45 | 08:35 | 0.83333 | 18523 | 18619 | 96 | Rotate |  | 18551 | 86.44 | 142.27 | 13031.18 | -4667.49 | 3647.09 | -4667.49 | 0.42 |  |  | 20 | 80 | 350 | 12500 | 115.2 | 6000 | 5300 | 700 | 336 | 310 | 220 | 160
07/03/2021 | 08:40 | 09:25 | 0.75 | 18619 | 18712 | 93 | Rotate |  | 18644 | 86.28 | 142.72 | 13037.09 | -4741.12 | 3703.59 | -4741.12 | 0.51 |  |  | 21 | 80 | 350 | 11300 | 124 | 6100 | 5350 | 750 | 338 | 310 | 220 | 160
07/03/2021 | 09:30 | 09:35 | 0.083333 | 18712 | 18722 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 120 | 6100 | 5350 | 750 | 338 | 310 | 220 | 160
07/03/2021 | 09:35 | 10:10 | 0.58333 | 18722 | 18734 | 12 | Slide | TTF: -70; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 20.57 | 5700 | 5350 | 350 | 336 | 310 | 220 | 160
07/03/2021 | 10:10 | 10:45 | 0.58333 | 18734 | 18805 | 71 | Rotate |  | 18737 | 86.3 | 141.03 | 13043.11 | -4814.12 | 3760.89 | -4814.12 | 1.81 |  |  | 20 | 80 | 350 | 11500 | 121.71 | 6100 | 5350 | 750 | 340 | 310 | 220 | 160
07/03/2021 | 10:50 | 10:55 | 0.083333 | 18805 | 18812 | 7 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 11500; Drilling Parameters ROP: 84 | 6100 | 5450 | 650 | 340 | 310 | 220 | 160
07/03/2021 | 10:55 | 11:20 | 0.41667 | 18812 | 18822 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 24 | 5700 | 5450 | 250 | 338 | 310 | 220 | 160
07/03/2021 | 11:20 | 12:00 | 0.66667 | 18822 | 18900 | 78 | Rotate |  | 18832 | 88.48 | 140.8 | 13047.43 | -4887.78 | 3820.72 | -4887.78 | 2.31 |  |  | 22 | 70 | 350 | 12600 | 117 | 6100 | 5400 | 700 | 342 | 310 | 220 | 160
07/03/2021 | 12:05 | 13:10 | 1.0833 | 18900 | 18971 | 71 | Rotate |  | 18926 | 89.25 | 141.49 | 13049.29 | -4960.97 | 3879.68 | -4960.97 | 1.1 |  |  | 22 | 80 | 350 | 12600 | 65.54 | 6100 | 5400 | 700 | 342 | 310 | 220 | 160

## BHA_6_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 6 |  |  |  |  | RKB: |  |  |  | 406 |  | North Reference: |  | GRID |  | Total Drilled: |  | 1466
Site: |  |  |  |  | Ozark - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 30
Well Name: |  |  |  |  | Ozark 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 56.00 |  |  |  |  | Grid Conv: |  |  |  | 406 |  | VS Azimuth: |  | 141.87 |  | Rotate: |  | 1436
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/05/2021 | 01:30 | 01:55 | 0.41667 | 18971 | 18995 | 24 | Rotate | Drilling Parameters WOB: 6; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 340; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 57.6 | 5200 | 4950 | 250 | 340 | 250 | 230 | 205
07/05/2021 | 02:05 | 03:15 | 1.1667 | 18995 | 19090 | 95 | Rotate |  | 19021 | 90.19 | 141.03 | 13049.76 | -5035.07 | 3939.12 | -5035.07 | 1.1 |  |  | 6 | 70 | 300 | 11000 | 81.43 | 4850 | 4350 | 500 | 342 | 250 | 230 | 205
07/05/2021 | 03:20 | 03:35 | 0.25 | 19090 | 19102 | 12 | Rotate | Drilling Parameters WOB: 6; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 48 | 4850 | 4350 | 500 | 342 | 250 | 230 | 205
07/05/2021 | 03:35 | 04:25 | 0.83333 | 19102 | 19117 | 15 | Slide | -160 | 19114 | 89.27 | 140.9 | 13050.2 | -5107.3 | 3997.69 | -5107.3 | 1 |  |  | 6 |  | 350 |  | 18 | 5600 | 5400 | 200 | 342 | 250 | 230 | 205
07/05/2021 | 04:25 | 05:25 | 1 | 19117 | 19183 | 66 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 66 | 4850 | 4350 | 500 | 343 | 250 | 230 | 205
07/05/2021 | 05:30 | 06:45 | 1.25 | 19183 | 19277 | 94 | Rotate |  | 19208 | 89.45 | 140.47 | 13051.25 | -5180.02 | 4057.25 | -5180.02 | 0.5 |  |  | 15 | 70 | 300 | 11000 | 75.2 | 4850 | 4350 | 500 | 345 | 250 | 230 | 205
07/05/2021 | 06:50 | 06:55 | 0.083333 | 19277 | 19285 | 8 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 300; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 96 | 4850 | 4350 | 500 | 345 | 315 | 225 | 150
07/05/2021 | 06:55 | 07:30 | 0.58333 | 19285 | 19300 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 25.71 | 5100 | 4750 | 350 | 343 | 315 | 225 | 150
07/05/2021 | 07:30 | 08:05 | 0.58333 | 19300 | 19370 | 70 | Rotate |  | 19301 | 87.61 | 139.94 | 13053.63 | -5251.45 | 4116.75 | -5251.45 | 2.06 |  |  | 23 | 70 | 330 | 13500 | 120 | 5450 | 4750 | 700 | 345 | 315 | 225 | 150
07/05/2021 | 08:10 | 09:00 | 0.83333 | 19370 | 19463 | 93 | Rotate |  | 19394 | 87.18 | 141.01 | 13057.86 | -5323.11 | 4175.87 | -5323.11 | 1.24 |  |  | 25 | 70 | 330 | 12500 | 111.6 | 5450 | 4750 | 700 | 349 | 315 | 225 | 150
07/05/2021 | 09:50 | 10:45 | 0.91667 | 19463 | 19557 | 94 | Rotate |  | 19488 | 87.63 | 141.5 | 13062.11 | -5396.35 | 4234.64 | -5396.35 | 0.71 |  |  | 23 | 70 | 300 | 12500 | 102.55 | 4500 | 3900 | 600 | 347 | 315 | 225 | 150
07/05/2021 | 10:50 | 11:50 | 1 | 19557 | 19652 | 95 | Rotate |  | 19583 | 87.9 | 142.24 | 13065.82 | -5471.02 | 4293.26 | -5471.02 | 0.83 |  |  | 22 | 70 | 330 | 12500 | 95 | 5450 | 4800 | 650 | 347 | 315 | 225 | 150
07/05/2021 | 11:55 | 12:40 | 0.75 | 19652 | 19746 | 94 | Rotate |  | 19677 | 88.21 | 142.54 | 13069.01 | -5545.44 | 4350.59 | -5545.44 | 0.46 |  |  | 24 | 70 | 330 | 12500 | 125.33 | 5450 | 4750 | 700 | 349 | 315 | 225 | 150
07/05/2021 | 12:45 | 13:00 | 0.25 | 19746 | 19776 | 30 | Rotate |  | 19773 | 88.42 | 143.23 | 13071.83 | -5621.96 | 4408.49 | -5621.96 | 0.75 |  |  | 23 | 70 | 330 | 12500 | 120 | 5450 | 4750 | 700 | 349 | 315 | 225 | 150
07/05/2021 | 13:35 | 14:00 | 0.41667 | 19776 | 19842 | 66 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 158.4 | 5450 | 4750 | 700 | 347 | 315 | 225 | 150
07/05/2021 | 14:05 | 14:55 | 0.83333 | 19842 | 19937 | 95 | Rotate |  | 19868 | 86.89 | 142.85 | 13075.72 | -5697.81 | 4465.56 | -5697.81 | 1.66 |  |  | 20 | 70 | 330 | 12500 | 114 | 5450 | 4750 | 700 | 349 | 315 | 225 | 150
07/05/2021 | 15:00 | 15:40 | 0.66667 | 19937 | 20032 | 95 | Rotate |  | 19963 | 87.69 | 143.74 | 13080.21 | -5773.88 | 4522.28 | -5773.88 | 1.26 |  |  | 25 | 70 | 330 | 12500 | 142.5 | 5450 | 4750 | 700 | 349 | 315 | 225 | 150
07/05/2021 | 15:45 | 16:20 | 0.58333 | 20032 | 20126 | 94 | Rotate |  | 20057 | 87.85 | 143.78 | 13083.87 | -5849.64 | 4577.81 | -5849.64 | 0.18 |  |  | 22 | 70 | 330 | 12500 | 161.14 | 5450 | 4750 | 700 | 350 | 315 | 225 | 150
07/05/2021 | 16:25 | 17:00 | 0.58333 | 20126 | 20221 | 95 | Rotate |  | 20152 | 87.94 | 144.04 | 13087.36 | -5926.36 | 4633.73 | -5926.36 | 0.29 |  |  | 20 | 70 | 330 | 13100 | 162.86 | 5600 | 4900 | 700 | 351 | 315 | 225 | 150
07/05/2021 | 17:05 | 17:45 | 0.66667 | 20221 | 20315 | 94 | Rotate |  | 20246 | 87.88 | 143.83 | 13090.79 | -6002.29 | 4689.03 | -6002.29 | 0.23 |  |  | 20 | 70 | 330 | 13100 | 141 | 5600 | 4900 | 700 | 351 | 315 | 225 | 150
07/05/2021 | 17:50 | 18:30 | 0.66667 | 20315 | 20409 | 94 | Rotate |  | 20340 | 87.84 | 143.53 | 13094.3 | -6077.98 | 4744.67 | -6077.98 | 0.32 |  |  | 20 | 70 | 330 | 13100 | 141 | 5600 | 4900 | 700 | 351 | 315 | 225 | 150
07/05/2021 | 18:35 | 18:50 | 0.25 | 20409 | 20437 | 28 | Rotate |  | 20437 | 87.64 | 143.88 | 13098.24 | -6156.22 | 4801.87 | -6156.22 | 0 |  |  | 20 | 70 | 330 | 13100 | 112 | 5600 | 4900 | 700 | 351 | 315 | 225 | 150