## Summary
Magnolia Oil & Gas / Rainier 1H ST01 / LTX1123821 / Patterson 248
Report Date: | 06/09/2021 | Current Depth: | 20659
Start Date: | 05/12/2021 | Casing Depth: | 11974
Daily Cost: | 11100 | Distance to TD:
Well Cost: | 339430 | Average ROP: | 0
Drilling Hours: | 20.42 | Svy MD: | 20591
24Hr Forcast: |  | Svy Inc: | 86.67
Current BHA: | BHA 8 | Svy Azi: | 131.26
Current BRT Hrs: | 92 | Svy TVD: | 12697.07
Bit Make / Model: | Halliburton / GTD64M | Svy NS: | -4055.99
POOH in last 24Hrs: | Yes | Svy EW: | 7189.5
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Jesse Taylor | MWD Day: | Danny Veronie
Directional Driller Night: | Josh Ray | MWD Night: | Jason Smetters
RSS Engineer 1: |  | Third Man:
RSS Engineer 2: |  | Fourth Man:
Principal Plan: |  | Max BHT Well: | 347
24Hr Summary: |  | Max BHT 24Hrs: | 0
Comments
Plan 9 STO 1, Window 10A/5B
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
PPM250019 | 6/7 11.7 2.0 Slick HS88 .013 | PDCI |  | Clean
PPM250022 | 6/7 8.8 @ 2.12? FIX Slick HPT +.020 | PDCI |  | In Hole |  | 30.08 | 30.08
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
775151 | UBHO |  |  | Dirty |  | 107.45 | 107.45
500033 | UBHO |  |  | Clean
500048 | UBHO |  |  | Dirty |  | 199.35 | 199.35
ZSBX500033 | UBHO |  |  | In Hole |  | 30.08 | 30.08
500047 | UBHO | PDCI |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | County: |  | Fayette |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Total Drilled (Usft): |  | 21100 |  |  | Total Days: |  | 28
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 3033 | 2925 |  | 575.41 |  | 12.07 | 5.08 | 5 | 12.25
2 | 2 | 9.875 | 3033 | 11985 | 8953 |  | 114.17 |  | 14.46 | 78.42 | 18.95 | 120.83
3 | 3 | 6.75 | 11985 | 12540 | 555 |  | 55.97 |  | 98.2 | 9.92 | 17.95 | 55
4 | 3 | 6.75 | 11992 | 12305 | 313 |  | 9.49 |  | 100 | 32.97 | 9.2 | 51
5 | 5 | 6.75 | 12305 | 12725 | 420 |  | 52.94 |  | 88.33 | 7.93 | 8.3 | 32.5
6 | 5 | 6.75 | 12725 | 15494 | 2769 |  | 96.59 |  | 12.5 | 28.67 | 12.17 | 62.08
7 | 6 | 6.75 | 15494 | 18577 | 3083 |  | 60.06 |  | 9.41 | 51.33 | 20.92 | 106.67 | YES
8 | 7 | 6.75 | 18577 | 20659 | 2082 |  | 101.98 |  | 6.24 | 20.42 | 9.67 | 92
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 |  |  |  |  | 1.353 | 2925 | 5.0833 | 575.41
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 1-1-CT-N-X-I-PN-TD |  | 1.491 | 8953 | 78.4167 | 114.17
3 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 555 | 9.9167 | 55.97
3 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 313 | 32.9667 | 9.49
5 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 420 | 7.9333 | 52.94
5 | Security |  | GTD64M |  | 6.75 |  |  |  |  | 1.491 | 2769 | 28.6667 | 96.59
6 | Halliburton |  | GTD64M |  | 6.75 | New |  | 4-6-BT-A-X-I-WT-HP |  | 1.491 | 3083 | 51.3333 | 60.06
7 | Halliburton |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 2082 | 20.4167 | 101.98
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 7.938 | 1.5 | 0 | 2925 |  | 575.41
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 5.98 | 8953 |  | 114.17
3 | PDCI |  | 6/7 11.7 |  | 6/7 | 11.7 | 5 | 2 | 4.05 | 555 |  | 55.97
4 | PDCI |  | 7/8 3.8 |  | 7/8 | 3.8 | 5 | 2.5 | 4.11 | 313 |  | 9.49
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.25 | 4.01 | 420 |  | 52.94
6 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.04 | 2769 |  | 96.59
7 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.1 | 3083 |  | 60.06
8 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.09 | 2082 |  | 101.98
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | Douglas Ferguson |  | Danny Veronie |  | Jason Smetters |  | Jessie Collison |  | Jim Harrison |  | Peter Langille
Nathan Marks |  | Josh Ray |  |  |  | Stephen Simmons
Nathan Marks Jesse Taylor |  | Paul Oates
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 1.99 / 0.34 |  | 2925 |  | 588.53 |  |  |  | 1 |  | 4.97
INT: INTERMEDIATE |  |  | 5.01 / 3.99 |  | 8894 |  | 118.92 |  | 4.00 / 0.00 |  | 1 |  | 74.79
CRV: CURVE |  |  | 1.98 / 0.18 |  | 59 |  | 16.86 |  |  |  | 1 |  | 3.5
CRV2: CURVE 2 |  |  | 3.00 / 0.58 |  | 555 |  | 56.06 |  | 0.17 / 0.00 |  | 1 |  | 9.9
ST: SIDETRACK |  |  | 3.56 / 2.96 |  | 733 |  | 17.93 |  |  |  | 2 |  | 40.89
LAT: LATERAL |  |  | 12.42 / 11.34 |  | 7934 |  | 79.12 |  | 3.67 / 0.00 |  | 3 |  | 100.28
Total |  |  | 27.96 |  | 21100 |  | 90.04 |  | 7.84 / 0.00 |  | 8 |  | 234.33
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 3033.00 | 712.47 | 2572.00 | 259.56 | 353.00 | 12.07 | 2925.00 | 588.53 | 4.97 | 1.36
INT: INTERMEDIATE-BHA 2 |  |  | 3032.00 | 11926.00 | 267.02 | 7658.00 | 26.81 | 1236.00 | 13.90 | 8894.00 | 118.92 | 74.79 | 46.11
CRV: CURVE-BHA 2 |  |  | 11926.00 | 11985.00 | 0.00 | 0.00 | 16.86 | 59.00 | 100.00 | 59.00 | 16.86 | 3.50 | 3.50
CRV2: CURVE 2-BHA 3 |  |  | 11985.00 | 12540.00 | 55.56 | 10.00 | 56.07 | 545.00 | 98.20 | 555.00 | 56.06 | 9.90 | 9.72
ST: SIDETRACK-BHA 4 |  |  | 11992.00 | 12305.00 | 0.00 | 0.00 | 9.50 | 313.00 | 100.00 | 313.00 | 9.50 | 32.96 | 32.96
ST: SIDETRACK-BHA 5 |  |  | 12305.00 | 12725.00 | 44.55 | 49.00 | 54.32 | 371.00 | 88.33 | 420.00 | 52.96 | 7.93 | 6.83
LAT: LATERAL-BHA 6 |  |  | 12725.00 | 15494.00 | 140.14 | 2423.00 | 30.51 | 346.00 | 12.50 | 2769.00 | 96.72 | 28.63 | 11.34
LAT: LATERAL-BHA 7 |  |  | 15494.00 | 18577.00 | 89.03 | 2793.00 | 14.58 | 290.00 | 9.41 | 3083.00 | 60.14 | 51.26 | 19.89
LAT: LATERAL-BHA 8 |  |  | 18577.00 | 20659.00 | 144.06 | 1952.00 | 19.01 | 130.00 | 6.24 | 2082.00 | 102.11 | 20.39 | 6.84
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1123821 | Total Drilled(Usft) | 21100.00
Operator | Magnolia Oil & Gas | Drilling Hours | 234.73
Well Name | Rainier 1H ST01 | Avg ROP(Usft/hr) | 89.89
Rig | Patterson 248 | Rotary Drilled(Usft) | 17457.00
State | Texas | Rotary Hours | 96.03
County | Fayette | Rotary ROP(Usft/hr) | 181.78
Formation | Austin Chalk | Rotary % | 82.73
Start Date | 05/12/2021 | Slide Drilled(Usft) | 3643.00
End Date | 06/09/2021 | Slide Hours | 138.70
Days On Well | 28 | Slide ROP(Usft/hr) | 26.27
Start Depth (Usft) | 108.00 | Slide % | 17.27
End Depth (Usft) | 20659.00
Total Drilled (Usft) | 21100.00
# BHA's | 8
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 13.63 / 0.00
Phase Data
Phase | SUR | INT | CRV | CRV2 | ST | LAT
Start Date | 05/12/2021 | 05/14/2021 | 05/19/2021 | 05/21/2021 | 05/24/2021 | 05/27/2021
End Date | 05/13/2021 | 05/19/2021 | 05/20/2021 | 05/23/2021 | 05/27/2021 | 06/09/2021
Total Days | 2.00 | 5.02 | 1.98 | 3.00 | 3.56 | 12.44
Start Depth (Usft) | 108.00 | 3033.00 | 11926.00 | 11985.00 | 11992.00 | 12725.00
End Depth (Usft) | 3033.00 | 11926.00 | 11985.00 | 12540.00 | 12725.00 | 20659.00
Total Drilled(Usft) | 2925.00 | 8894.00 | 59.00 | 555.00 | 733.00 | 7934.00
Drilling Hours | 5.08 | 74.92 | 3.50 | 9.92 | 40.90 | 100.42
Circulating Hours | 5.50 | 16.53 | 2.42 | 17.95 | 17.50 | 42.75
Total D&C Hours | 10.58 | 91.45 | 5.92 | 27.87 | 58.40 | 143.17
Avg ROP(Usft/hr) | 575.41 | 118.72 | 16.86 | 55.97 | 17.92 | 79.01
Rotary Drilled(Usft) | 2572.00 | 7658.00 | 0.00 | 10.00 | 49.00 | 7168.00
Rotary Hours | 3.67 | 28.75 | 0.00 | 0.18 | 1.10 | 62.33
Rotary ROP(Usft/hr) | 701.45 | 266.37 | 0.00 | 54.55 | 44.55 | 114.99
Rotary % | 87.93 | 86.10 | 0.00 | 1.80 | 6.68 | 90.35
Slide Drilled(Usft) | 353.00 | 1236.00 | 59.00 | 545.00 | 684.00 | 766.00
Slide Hours | 1.42 | 46.17 | 3.50 | 9.73 | 39.80 | 38.08
Slide ROP(Usft/hr) | 249.18 | 26.77 | 16.86 | 55.99 | 17.19 | 20.11
Slide % | 12.07 | 13.90 | 100.00 | 98.20 | 93.32 | 9.65
# BHA | 1 | 1 | 1 | 1 | 2 | 3
# Motor Failures | 0 | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 6.47 / 0.00 | 0.00 / 0.00 | 0.17 / 0.00 | 0.00 / 0.00 | 7.00 / 0.00
Total Phase Hrs | 8.25 | 95.83 | 4.33 | 13.93 | 71.00 | 272.25
Phase ROP (Usft/hr) | 354.55 | 92.81 | 13.62 | 39.83 | 10.32 | 29.14
Avg Motor Yield (°/100ft) | 9.38 | 9.97 | 0.00 | 10.13 | 14.61 | 16.21
Avg Rotary DLS (°/100ft) | 0.29 | 0.81 | 0.00 | 1.56 | 0.00 | 1.08
Avg Rotary TF | -177.27 | -134.45 | 0.00 | 39.37 | 0.00 | 136.35
Avg Slide Length (Usft) | 20.76 | 19.31 | 19.67 | 49.55 | 47.85 | 15.96
# Slides | 17 | 64 | 3 | 11 | 13 | 48
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4 | BHA 5 | BHA 6 | BHA 7 | BHA 8
Bit Size | 13.500 | 9.875 | 6.750 | 6.750 | 6.750 | 6.750 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Security / GTD64M | Security / GTD64M | Security / GTD64M | Security / GTD64M | Halliburton / GTD64M | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491 | 1.491 | 1.491 | 1.491 | 1.491
Grade In |  | New | New | New | New |  | New | New
Grade Out | BHA 2: 1-1-CT-N-X-I-PN-TD; BHA 7: 4-6-BT-A-X-I-WT-HP
Motor SN | SD610174 | PPM800055 | PPM250014 | MTR475015 | PPM250018 | PPM250024 | PPM250010 | PPM250022
Motor Make/Model |  | PDCI / 7/8 5.9 | PDCI / 6/7 11.7 | PDCI / 7/8 3.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages |  | 7/8 / 5.9 | 6/7 / 11.7 | 7/8 / 3.8 | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 10.00 / 10.00 / 10.00 | 25.00 / 35.92 / 45.00 | 18.00 / 18.00 / 18.00 | 10000.00 / 10000.00 / 10000.00 | 30.00 / 30.00 / 30.00 | 22.00 / 29.41 / 40.00 | 23.00 / 29.62 / 45.00 | 20.00 / 25.07 / 30.00
Diff P (psi) | 300.00 / 491.49 / 500.00 | 200.00 / 527.78 / 800.00 | 300.00 / 666.67 / 700.00 | 100.00 / 100.00 / 100.00 | 550.00 / 550.00 / 550.00 | 300.00 / 781.07 / 1000.00 | 200.00 / 583.95 / 1000.00 | 300.00 / 700.00 / 1100.00
Bend | 0.000 | 2.000 | 2.000 | 2.500 | 2.250 | 2.120 | 2.120 | 2.120
Date In | 05/12/2021 | 05/14/2021 | 05/21/2021 | 05/24/2021 | 05/26/2021 | 05/27/2021 | 05/30/2021 | 06/06/2021
Date Out | 05/13/2021 | 05/19/2021 | 05/23/2021 | 05/26/2021 | 05/27/2021 | 05/30/2021 | 06/03/2021 | 06/09/2021
Time In | 16:30 | 18:00 | 01:00 | 01:00 | 05:00 | 14:30 | 05:20 | 04:00
Time Out | 04:45 | 18:50 | 08:00 | 04:00 | 13:30 | 04:35 | 16:00 | 24:00
BRT Hrs | 12.25 | 120.83 | 55.00 | 51.00 | 32.50 | 62.08 | 106.67 | 92.00
Start Depth (Usft) | 108.00 | 3033.00 | 11985.00 | 11992.00 | 12305.00 | 12725.00 | 15494.00 | 18577.00
End Depth (Usft) | 3033.00 | 11985.00 | 12540.00 | 12305.00 | 12725.00 | 15494.00 | 18577.00 | 20659.00
Total Drilled(Usft) | 2925.00 | 8953.00 | 555.00 | 313.00 | 420.00 | 2769.00 | 3083.00 | 2082.00
Drilling Hours | 5.08 | 78.42 | 9.92 | 32.97 | 7.93 | 28.67 | 51.33 | 20.42
Circulating Hours | 5.00 | 18.95 | 17.95 | 9.20 | 8.30 | 12.17 | 20.92 | 9.67
Total D&C Hours | 10.08 | 97.37 | 27.87 | 42.17 | 16.23 | 40.83 | 72.25 | 30.08
Avg ROP(Usft/hr) | 575.41 | 114.17 | 55.97 | 9.49 | 52.94 | 96.59 | 60.06 | 101.98
Rotary Drilled(Usft) | 2572.00 | 7658.00 | 10.00 | 0.00 | 49.00 | 2423.00 | 2793.00 | 1952.00
Rotary Hours | 3.67 | 28.75 | 0.18 | 0.00 | 1.10 | 17.33 | 31.42 | 13.58
Rotary ROP(Usft/hr) | 701.45 | 266.37 | 54.55 | 0.00 | 44.55 | 139.79 | 88.90 | 143.71
Rotary % | 87.93 | 85.54 | 1.80 | 0.00 | 11.67 | 87.50 | 90.59 | 93.76
Slide Drilled(Usft) | 353.00 | 1295.00 | 545.00 | 313.00 | 371.00 | 346.00 | 290.00 | 130.00
Slide Hours | 1.42 | 49.67 | 9.73 | 32.97 | 6.83 | 11.33 | 19.92 | 6.83
Slide ROP(Usft/hr) | 249.18 | 26.07 | 55.99 | 9.49 | 54.29 | 30.53 | 14.56 | 19.02
Slide % | 12.07 | 14.46 | 98.20 | 100.00 | 88.33 | 12.50 | 9.41 | 6.24
Motor Failure | bar: BHA 1 to BHA 8
MWD Failure | bar: BHA 1 to BHA 8
Unplanned Trip | NO | NO | YES | YES | NO | YES | YES | NO
LIH | bar: BHA 1 to BHA 8
Avg Motor Yield (°/100ft) | 9.38 | 9.97 | 10.13 | 8.64 | 16.24 | 14.89 | 17.79 | 15.01
Avg Rotary DLS (°/100ft) | 0.29 | 0.81 | 1.56 | 1.56 | 0.00 | 1.02 | 1.31 | 0.94
Avg Rotary TF | -177.27 | -135.37 | 39.37 | 39.37 | 0.00 | 80.35 | 109.21 | -100.95
Avg Slide Length (Usft) | 20.76 | 19.33 | 49.55 | 26.25 | 53.00 | 20.35 | 13.18 | 14.44
# Slides | 17 | 67 | 11 | 12 | 7 | 17 | 22 | 9

## Personnel Report
|  | Job # | LTX1123821 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-149-33519 |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Rainier 1H ST01
|  | Date: | 06/09/2021 |  | State: |  | Texas
[5 empty] | County: |  | Fayette
Rainier 1H ST01 - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Danny Veronie | Day MWD |  | 05/12/2021 - 00:00 | 06/03/2021 - 00:00 |  | 23.00 / 0.00
Danny Veronie | Day MWD |  | 06/05/2021 - 00:00 | 06/09/2021 - 00:00 |  | 5.00 / 0.00
Douglas Ferguson | Night DD |  | 05/21/2021 - 00:00 | 05/27/2021 - 00:00 |  | 7.00 / 0.00
Jason Smetters | Night MWD |  | 05/12/2021 - 00:00 | 05/28/2021 - 00:00 |  | 17.00 / 0.00
Jason Smetters | Night MWD |  | 06/01/2021 - 00:00 | 06/03/2021 - 00:00 |  | 3.00 / 0.00
Jason Smetters | Night MWD |  | 06/05/2021 - 00:00 | 06/09/2021 - 00:00 |  | 5.00 / 0.00
Jesse Taylor | Day DD |  | 05/12/2021 - 00:00 | 05/14/2021 - 00:00 |  | 3.00 / 0.00
Jesse Taylor | Day DD |  | 05/28/2021 - 00:00 | 06/03/2021 - 00:00 |  | 7.00 / 0.00
Jesse Taylor | Day DD |  | 06/05/2021 - 00:00 | 06/09/2021 - 00:00 |  | 5.00 / 0.00
Josh Ray | Night DD |  | 05/28/2021 - 00:00 | 06/03/2021 - 00:00 |  | 7.00 / 0.00
Josh Ray | Night DD |  | 06/05/2021 - 00:00 | 06/09/2021 - 00:00 |  | 5.00 / 0.00
Nathan Marks | Day DD |  | 05/16/2021 - 00:00 | 05/27/2021 - 00:00 |  | 12.00 / 0.00
Nathan Marks Jesse Taylor | Day DD |  | 05/15/2021 - 00:00 | 05/15/2021 - 00:00 |  | 1.00 / 0.00
Paul Oates | Night DD |  | 05/12/2021 - 00:00 | 05/20/2021 - 00:00 |  | 9.00 / 0.00
Stephen Simmons | Night MWD |  | 05/29/2021 - 00:00 | 05/31/2021 - 00:00 |  | 3.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1123821 | [5 empty] | State / County: |  |  |  | Texas / Fayette
|  |  |  | Well Name: |  |  | Rainier 1H ST01 | [7 empty] | Day DD: |  |  |  |  | Jesse Taylor | [5 empty] | API #: |  |  |  | 42-149-33519
|  |  |  | AFE #: |  |  | 21DD0100MG | [7 empty] | Night DD: |  |  |  |  | Josh Ray | [5 empty] | Company Man: |  |  |  | Jessie Collison
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Jason Smetters | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 05/12/2021 | 05/13/2021 | 05/14/2021 | 05/15/2021 | 05/16/2021 | 05/17/2021 | 05/18/2021 | 05/19/2021 | 05/20/2021 | 05/21/2021 | 05/22/2021 | 05/23/2021 | 05/24/2021 | 05/25/2021 | 05/26/2021 | 05/27/2021 | 05/28/2021 | 05/29/2021 | 05/30/2021 | 05/31/2021 | 06/01/2021 | 06/02/2021 | 06/03/2021 | 06/04/2021 | 06/05/2021 | 06/06/2021 | 06/07/2021 | 06/08/2021 | 06/09/2021 | 06/10/2021 | 06/11/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | GTD64M |  | Steel | 13590860 | 3 | 21 | [8 empty] | O | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13090615 | 3 | 18 | [11 empty] | O | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M 6.75 Jets 6X18's |  | Steel | 1138553 | 5 | 15 | [14 empty] | X | X | X | X | X | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13558789 | 5 | 12 | [17 empty] | O | X | X | X | X | X | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13594950 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Cross Over |  | 6.625 | Crossover Sub |  | Steel | SD113433 | 0 | 9 | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.438 | Crossover Sub |  | Steel | SD3539 | 6 | 9 | O | O | X | X | X | X | X | X | O
Cross Over |  | 6.75 | Crossover Sub |  | Steel | SD114897 | 2 | 9 | X | X | O | O | O | O | O | O | O
Cross Over |  | 6.75 | Crossover Sub |  | Steel | SD117746 | 0 | 9 | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD114463 | 0 | 9 | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD116860 | 6 | 9 | O | O | X | X | X | X | X | X | O
Cross Over |  |  | Crossover Sub |  | Steel | SD110972 | 0 | 9 | O | O | O | O | O | O | O | O | O
Cross Over |  | 6.438 | Crossover Sub |  | Steel | SD116198 | 0 | 9 | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.312 | Crossover Sub |  | Steel | PS17183DTI | 0 | 29 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.312 | Crossover Sub |  | Steel | PS17184DT | 0 | 29 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.125 | Crossover |  | Steel | SD119105 | 14 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Cross Over |  | 4.938 | Crossover |  | Steel | SD119321 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  |  | Crossover |  | Steel | GT52331432 | 0 | 14 | [15 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.312 | Crossover |  | Steel | GT52331433 | 4 | 14 | [15 empty] | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Cross Over |  | 5.375 | Crossover |  | Steel | CE1161 | 0 | 7 | [22 empty] | O | O | O | O | O | O | O
Cross Over |  | 5.375 | Crossover |  | Steel | CE2210 | 0 | 7 | [22 empty] | O | O | O | O | O | O | O
Cross Over |  | 5.375 | Crossover |  | Steel | CE1112 | 0 | 7 | [22 empty] | O | O | O | O | O | O | O
Cross Over |  | 5.375 | Crossover |  | Steel | CE1113 | 0 | 7 | [22 empty] | O | O | O | O | O | O | O
RSS |  |  | PDORBIT 825 |  | Steel | 97063 | 0 | 1 | [7 empty] | O
MWD / LWD |  | 7.75 | UBHO |  | Steel | 775151 | 8 | 9 | X | X | X | X | X | X | X | X | O
MWD / LWD |  | 7.375 | UBHO |  | Steel | 500033 | 0 | 9 | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500048 | 14 | 23 | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X
MWD / LWD |  | 5.25 | UBHO |  | Steel | ZSBX500033 | 4 | 29 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
MWD / LWD | PDCI | 5.25 | UBHO |  | Steel | 500047 | 0 | 7 | [22 empty] | O | O | O | O | O | O | O
Motor |  | 7.938 | 7.75" 7/8 5.9 1.5F 13" NBS -.023 |  | Steel | PPM800069 | 0 | 2 | O | O
Motor |  | 7.938 | 7.75" 7/8 5.9 1.5F 13" NBS -.022 |  | Steel | PPM800075 | 2 | 2 | X | X
Motor |  | 8 | 7.75" 7/8 5.9 2.0F Slick -.016 |  | Steel | PPM800055 | 6 | 8 |  | O | X | X | X | X | X | X | O
Motor |  | 8 | 7.75" 7/8 5.9 2.0F Slick -.022 |  | Steel | PPM800033 | 0 | 8 |  | O | O | O | O | O | O | O | O
Motor |  |  | 7/8 5.9 0 Slick HPO -0.22 |  | Steel | PPM800001 | 0 | 1 | [7 empty] | O
Motor |  |  | 7/8 5.9 0 Slick HPO -0.22 |  | Steel | PPM800065 | 0 | 1 | [7 empty] | O
Motor |  | 5 | 6/7 11.7 2.0 Slick HS88 -.005 |  | Steel | PPM250001 | 0 | 5 | [8 empty] | O | O | O | O | O
Motor |  | 5 | 6/7 11.7 2.0 Slick HS88 .015 |  | Steel | PPM250014 | 3 | 5 | [8 empty] | O | X | X | X | O
Motor |  | 5 | 6/7 11.7 2.0 Slick HS88 .009 |  | Steel | PPM250016 | 0 | 1 | [8 empty] | O
Motor |  | 5 | 6/7 11.7 2.0 Slick HS88 .013 |  | Steel | PPM250019 | 0 | 1 | [8 empty] | O
Motor |  | 5 | 6/7 11.7 2.0 Slick HS88 .017 |  | Steel | PPM250021 | 0 | 1 | [8 empty] | O
Motor | PDCI | 5 | 6/7 11.7 2.0 Slick HS88 .013 |  | Steel | PPM250019 | 0 | 19 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 7/8 3.8 2.5 Slick HS88 -.001 |  | Steel | MTR475015 | 3 | 21 | [8 empty] | O | O | O | O | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 @ 2.12? FIX Slick HS88 +.009 |  | Steel | PPM250024 | 4 | 10 | [12 empty] | O | O | O | X | X | X | X | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  | Steel | PPM250022 | 4 | 8 | [21 empty] | O | O | O | O | X | X | X | X
Motor | PDCI | 5.5 | 6/7 8.8 @ 2.12? FIX Slick HS88 +.021 |  | Steel | PPM250010 | 5 | 10 | [17 empty] | O | X | X | X | X | X | O | O | O | O
Motor |  | 5.5 | 6/7 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 |  | Steel | PPM250018 | 2 | 5 | [13 empty] | O | X | X | O | O
Stab |  | 8 | Nortrak Stabilizer (BFF) |  | Steel | SD610174 | 0 | 2 | O | O
Stab |  | 8 | Nortrak Stabilizer (BFF) |  | Steel | SD610175 | 0 | 2 | O | O
Stab |  |  | Stabalizer |  | Steel | 25237 | 0 | 1 | [7 empty] | O
Stab |  |  | Stabalizer |  | Steel | 604427 | 0 | 1 | [7 empty] | O
Stab |  |  | Stabalizer |  | Steel | 28223 | 0 | 1 | [7 empty] | O
Stab |  |  | Stabalizer |  | Steel | 600512 | 0 | 1 | [7 empty] | O
Collar |  | 7.75 | NMDC |  | Non-Mag | SD55287 | 0 | 9 | O | O | O | O | O | O | O | O | O
Collar |  | 7.75 | NMDC |  | Non-Mag | SD55517 | 0 | 9 | O | O | O | O | O | O | O | O | O
Collar |  | 8 | NMDC |  | Non-Mag | SD55726 | 8 | 9 | X | X | X | X | X | X | X | X | O
Collar |  | 7.938 | NMDC |  | Non-Mag | SD56047 | 8 | 9 | X | X | X | X | X | X | X | X | O
Collar |  | 7.875 | NMPC |  | Steel | SD54641 | 0 | 9 | O | O | O | O | O | O | O | O | O
Collar |  | 8.062 | NMPC |  | Steel | SD54328 | 8 | 9 | X | X | X | X | X | X | X | X | O
Collar |  | 4.938 | NMDC |  | Non-Mag | SD55848 | 14 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Collar |  | 4.938 | NMDC |  | Non-Mag | SD56238 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NMDC |  | Non-Mag | SD56281 | 14 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Collar |  | 5 | NMDC |  | Non-Mag | SD56699 | 4 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Collar |  | 5 | NMDC |  | Non-Mag | SD56709 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NMDC |  | Non-Mag | SD56777 | 4 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Collar |  | 5.062 | Pony Collar |  | Steel | SD56837 | 14 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Collar |  | 5 | Pony Collar |  | Steel | SD56870 | 14 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Collar | Gator Tech | 5 | Pony Collar |  | Steel | GT50-10-479 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Collar | Gator Tech | 5 | Pony Collar |  | Steel | GT50-10-637 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Collar | StabilDrill | 5 | Pony Collar |  | Steel | SD56679 | 0 | 7 | [22 empty] | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 2 Stds 4.5 Drill Pipe |  | Steel | Rig | 0 | 29 | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 26 Stds 4.5 in Drill Pipe |  | Steel | Rig | 0 | 28 |  | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 33 Stds 4.5 in Drill Pipe |  | Steel | Rig | 0 | 28 |  | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 2 Std Drill Pipe |  | Steel | Rig 1 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 26 Std Drill Pipe |  | Steel | Rig 2 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 33 Std Drill Pipe |  | Steel | Rig 3 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 28 Std Drill Pipe |  | Steel | Rig 4 | 0 | 19 | [10 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 4.938 | Tomax |  | Steel | A52074 | 14 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Accelerator |  | 5 | Tomax |  | Steel | A52102 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Sub |  | 7.938 | Float Sub |  | Steel | SD108610 | 0 | 9 | O | O | O | O | O | O | O | O | O
Sub |  | 8 | Float Sub |  | Steel | SD117182 | 0 | 9 | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD118474 | 0 | 9 | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119151 | 0 | 9 | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Cap |  | Steel | LC3378 | 0 | 9 | O | O | O | O | O | O | O | O | O
Sub |  |  | Filter Sub |  | Steel | 118006 | 0 | 1 | [7 empty] | O
Sub |  |  | Filter Sub |  | Steel | 119156 | 0 | 1 | [7 empty] | O
Sub |  |  | Double Pin |  | Steel | 108131 | 0 | 1 | [7 empty] | O
Sub |  |  | Double Pin |  | Steel | 108240 | 0 | 1 | [7 empty] | O
Sub |  |  | Float Sub |  | Steel | SD114757 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119565 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119274 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  |  | Lift Sub |  | Steel | SD119682 | 0 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.812 | BTI |  | Steel | 306839 | 10 | 21 | [8 empty] | O | X | X | X | X | X | X | X | X | X | X | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.812 | BTI |  | Steel | 306842 | 9 | 21 | [8 empty] | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | O | O | X | X | X | X
Sub |  | 5.188 | Reamer |  | Steel | DTI-DNR-98 | 11 | 21 | [8 empty] | O | X | X | X | O | O | O | X | X | X | X | X | X | X | X | O | O | O | O | O | O
Agitator |  | 6.812 | Agitator |  | Steel | P6675-0022 | 6 | 28 |  | O | X | X | X | X | X | X | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0037 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0049 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Agitator |  | 5.312 | Agitator |  | Steel | PG525-0046 | 4 | 14 | [15 empty] | X | X | X | X | O | O | O | O | O | O | O | O | O | O
Agitator |  | 5.25 | Agitator |  | Steel | PG5250027 | 5 | 14 | [14 empty] | X | X | X | X | X | O | O | O | O | O | O | O | O | O | O
Reamer | DTI | 5.375 | 6 13/16 Reamer |  | Steel | DTI-DNR-533 | 4 | 7 | [22 empty] | O | O | O | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 15 |  | 1 | 1 | 1 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Nathan Marks |  |  |  | 12 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Nathan Marks Jesse Taylor |  |  |  | 1 |  |  |  |  | 1
Night DD |  |  | Douglas Ferguson |  |  |  | 7 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Josh Ray |  |  |  | 12 | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Paul Oates |  |  |  | 9 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 28 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smetters |  |  |  | 25 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Stephen Simmons |  |  |  | 3 | [18 empty] | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Rainier 1H ST01
|  | County: |  | Fayette |  |  | State: |  | Texas
|  | AFE #: |  | 21DD0100MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
PPM800069 | 7.75" 7/8 5.9 1.5F 13" NBS -.023 | 7.938 | 37.54 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/13/2021
PPM800075 | 7.75" 7/8 5.9 1.5F 13" NBS -.022 | 7.938 | 37.52 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/13/2021
SD55287 | NMDC | 7.75 | 29.2 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD55517 | NMDC | 7.75 | 30.06 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD55726 | NMDC | 8 | 29.13 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/20/2021
SD56047 | NMDC | 7.938 | 29.2 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/20/2021
SD54641 | NMPC | 7.875 | 11.28 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD54328 | NMPC | 8.062 | 10.1 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/20/2021
SD610174 | Nortrak Stabilizer (BFF) | 8 | 6.74 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/13/2021
SD610175 | Nortrak Stabilizer (BFF) | 8 | 7.85 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/13/2021
SD113433 | Crossover Sub | 6.625 | 2.06 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 05/11/2021 |  | 05/20/2021
SD3539 | Crossover Sub | 6.438 | 2.89 |  | 4 1/2 IF / 4 1/2 XH | Dirty |  | 05/11/2021 |  | 05/20/2021
SD114897 | Crossover Sub | 6.75 | 3.6 |  | 4 1/2 IF / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/20/2021
SD117746 | Crossover Sub | 6.75 | 2.9 |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD114463 | Crossover Sub | 6.5 | 3.05 |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD116860 | Crossover Sub | 6.5 | 2.35 |  | 4 1/2 XH / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/20/2021
SD110972 | Crossover Sub |  |  |  |  | Clean |  | 05/11/2021 |  | 05/20/2021
SD116198 | Crossover Sub | 6.438 | 3.62 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 05/11/2021 |  | 05/20/2021
SD108610 | Float Sub | 7.938 | 1.76 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD117182 | Float Sub | 8 | 2.74 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD118474 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
SD119151 | Lift Sub |  |  |  | 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
LC3378 | Lift Cap |  |  |  | 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
775151 | UBHO | 7.75 | 2.55 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 05/11/2021 |  | 05/20/2021
500033 | UBHO | 7.375 | 3.87 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/11/2021 |  | 05/20/2021
500048 | UBHO | 5.25 | 3.07 |  | XT39 / XT39 | Dirty |  | 05/11/2021 |  | 06/03/2021
ZSBX500033 | UBHO | 5.25 | 3.63 |  | XT39 / XT39 | In Hole |  | 05/11/2021
500047 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Clean | PDCI / UBHO | 06/03/2021
PS17183DTI | Crossover Sub | 5.312 | 3.2 |  | DS42 / 4 1/2 IF | Clean |  | 05/11/2021
PS17184DT | Crossover Sub | 5.312 | 3.53 |  | DS42 / 4 1/2 IF | Clean |  | 05/11/2021
Rig | 2 Stds 4.5 Drill Pipe | 4.5 | 189.58 |  | CET-43 / CET-43 | In Hole |  | 05/11/2021
Rig | 26 Stds 4.5 in Drill Pipe | 4.5 | 2460.5 |  | CET-43 / CET-43 | In Hole |  | 05/13/2021
Rig | 33 Stds 4.5 in Drill Pipe | 4.5 | 3118.79 |  | CET-43 / CET-43 | In Hole |  | 05/13/2021
P6675-0022 | Agitator | 6.812 | 24.62 |  | 4 1/2 IF / 4 1/2 IF | Dirty |  | 05/13/2021
PPM800055 | 7.75" 7/8 5.9 2.0F Slick -.016 | 8 | 37.58 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 05/13/2021 |  | 05/20/2021
PPM800033 | 7.75" 7/8 5.9 2.0F Slick -.022 | 8 |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 05/13/2021 |  | 05/20/2021
PPM800001 | 7/8 5.9 0 Slick HPO -0.22 |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
PPM800065 | 7/8 5.9 0 Slick HPO -0.22 |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
25237 | Stabalizer |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
604427 | Stabalizer |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
28223 | Stabalizer |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
600512 | Stabalizer |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
118006 | Filter Sub |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
119156 | Filter Sub |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
V248 | Filter Screen |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
V339 | Filter Screen |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
108131 | Double Pin |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
108240 | Double Pin |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
97063 | PDORBIT 825 |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
FRK978-7-EXT | PDFRK 9 7/8 |  |  |  |  | Clean |  | 05/19/2021 |  | 05/19/2021
SD55848 | NMDC | 4.938 | 30.78 |  | XT-39 / XT-39 | Dirty |  | 05/20/2021
SD56238 | NMDC | 4.938 | 30.76 |  | XT-39 / XT-39 | Clean |  | 05/20/2021
SD56281 | NMDC | 5 | 30.19 |  | XT-39 / XT-39 | Dirty |  | 05/20/2021
SD56699 | NMDC | 5 | 30.72 |  | XT-39 / XT-39 | In Hole |  | 05/20/2021
SD56709 | NMDC | 5 | 29.98 |  | XT-39 / XT-39 | Clean |  | 05/20/2021
SD56777 | NMDC | 5 | 30.86 |  | XT-39 / XT-39 | In Hole |  | 05/20/2021
SD56837 | Pony Collar | 5.062 | 9.44 |  | XT-39 / XT-39 | Dirty |  | 05/20/2021
SD56870 | Pony Collar | 5 | 9.99 |  | XT-39 / XT-39 | Dirty |  | 05/20/2021
GT50-10-479 | Pony Collar | 5 | 9.86 |  | XT-39 / XT-39 | In Hole | Gator Tech | 06/03/2021
GT50-10-637 | Pony Collar | 5 | 9.29 |  | XT-39 / XT-39 | In Hole | Gator Tech | 06/03/2021
SD56679 | Pony Collar | 5 | 9.27 |  | XT-39 / XT-39 | Clean | StabilDrill | 06/03/2021
SD114757 | Float Sub |  |  |  | XT-39 / XT-39 | Clean |  | 05/20/2021
SD119565 | Float Sub |  |  |  | XT-39 / XT-39 | Clean |  | 05/20/2021
SD119105 | Crossover | 5.125 | 3.07 |  | DS42 / XT-39 | Dirty |  | 05/20/2021
SD119321 | Crossover | 4.938 | 2.45 |  | DS42 / XT-39 | Clean |  | 05/20/2021
SD119274 | Lift Sub |  |  |  | XT-39 | Clean |  | 05/20/2021
SD119682 | Lift Sub |  |  |  | XT-39 | Clean |  | 05/20/2021
SDLC1115 | Lift Cap |  |  |  | XT-39 | Clean |  | 05/20/2021
306839 | BTI | 4.812 | 2.1 |  | XT-39 / XT-39 | Dirty |  | 05/20/2021
306842 | BTI | 4.812 | 2.1 |  | XT-39 / XT-39 | In Hole |  | 05/20/2021
A52074 | Tomax | 4.938 | 17.57 |  | XT-39 / XT-39 | Dirty |  | 05/20/2021
A52102 | Tomax | 5 | 17.65 |  | XT-39 / XT-39 | In Hole |  | 06/03/2021
PG525-0037 | Agitator | 5.312 | 22.42 |  | CET-43 / CET-43 | In Hole | DWS / Power Glide | 06/03/2021
PG525-0049 | Agitator | 5.312 | 21.95 |  | CET-43 / CE-43 | In Hole | DWS / Power Glide | 06/03/2021
DTI-DNR-98 | Reamer | 5.188 | 8.16 |  | DS42 / DS42 | Dirty |  | 05/20/2021
DTI-DNR-533 | 6 13/16 Reamer | 5.375 | 8.41 |  | CET-43 / CET-43 | In Hole | DTI / DNR | 06/03/2021
13590860 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 05/20/2021
PPM250001 | 6/7 11.7 2.0 Slick HS88 -.005 | 5 | 33.08 |  | XT-39 / 3 1/2 Reg | Clean |  | 05/20/2021 |  | 05/24/2021
PPM250014 | 6/7 11.7 2.0 Slick HS88 .015 | 5 | 33.06 |  | XT-39 / 3 1/2 Reg | Dirty |  | 05/20/2021 |  | 05/24/2021
PPM250016 | 6/7 11.7 2.0 Slick HS88 .009 | 5 | 33.17 |  | XT-39 / 3 1/2 Reg | Clean |  | 05/20/2021 |  | 05/20/2021
PPM250019 | 6/7 11.7 2.0 Slick HS88 .013 | 5 | 33.17 |  | XT-39 / 3 1/2 Reg | Clean |  | 05/20/2021 |  | 05/20/2021
PPM250021 | 6/7 11.7 2.0 Slick HS88 .017 | 5 | 33.11 |  | XT-39 / 3 1/2 Reg | Clean |  | 05/20/2021 |  | 05/20/2021
PPM250019 | 6/7 11.7 2.0 Slick HS88 .013 | 5 |  |  | XT-39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 05/22/2021
MTR475015 | 7/8 3.8 2.5 Slick HS88 -.001 | 5 | 26.22 |  | XT-39 / 3 1/2 Reg | Dirty |  | 05/20/2021
Rig 1 | 2 Std Drill Pipe | 4.5 | 188.32 |  | DS42 / DS42 | Dirty |  | 05/20/2021
Rig 2 | 26 Std Drill Pipe | 4.5 | 2453 |  | DS42 / DS42 | Dirty |  | 05/20/2021
Rig 3 | 33 Std Drill Pipe | 4.5 | 3138.03 |  | DS42 / DS42 | Dirty |  | 05/20/2021
Rig 4 | 28 Std Drill Pipe | 4.5 | 2651.32 |  | DS42 / DS42 | Dirty |  | 05/22/2021
13090615 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 05/23/2021
PPM250024 | 6/7 8.8 @ 2.12? FIX Slick HS88 +.009 | 5.5 | 33.14 |  | 4 XT39 / 3 1/2Reg | Dirty | PDCI / Pro Power | 05/24/2021 |  | 06/02/2021
PPM250022 | 6/7 8.8 @ 2.12? FIX Slick HPT +.020 | 5.5 | 32.95 |  | 4 XT39 / 3 1/2Reg | In Hole | PDCI / Pro Power | 06/02/2021
PPM250010 | 6/7 8.8 @ 2.12? FIX Slick HS88 +.021 | 5.5 | 33.08 |  | 4 XT39 / 3 1/2Reg | Dirty | PDCI / Pro Power | 05/29/2021 |  | 06/07/2021
PPM250018 | 6/7 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 | 5.5 | 33.13 |  | 4 XT39 / 3 1/2Reg | Dirty |  | 05/25/2021 |  | 05/29/2021
1138553 | GTD64M 6.75 Jets 6X18's | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 05/26/2021
PG525-0046 | Agitator | 5.312 | 23.48 |  | DS42 / DS42 | Dirty |  | 05/27/2021
PG5250027 | Agitator | 5.25 | 23.5 |  | DS42 / DS42 | Dirty |  | 05/27/2021
GT52331432 | Crossover |  |  |  | CET-43 / XT-39 | Clean |  | 05/27/2021
GT52331433 | Crossover | 5.312 | 3.64 |  | CET-43 / XT-39 | In Hole |  | 05/27/2021
CE1161 | Crossover | 5.375 | 3.66 |  | DS42 / CET-43 | Clean |  | 06/03/2021
CE2210 | Crossover | 5.375 | 3.47 |  | DS42 / CET-43 | Clean |  | 06/03/2021
CE1112 | Crossover | 5.375 | 3.5 |  | CET-43 / DS42 | Clean |  | 06/03/2021
CE1113 | Crossover | 5.375 | 3.49 |  | CET-43 / DS42 | Clean |  | 06/03/2021
13558789 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 05/29/2021
13594950 | GTD64M | 6.75 | 0.75 |  | 3 1/2 Reg | In Hole |  | 06/03/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Rainier 1H ST01
|  | County: |  | Fayette |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 47245 | 05/12/2021 | 06/09/2021 | 29 | 1 | 1 |  | 5 | 5.08 | 12.25
7.75" 7/8 5.9 1.5F 13" NBS -.022 | PPM800075 | 05/11/2021 | 05/13/2021 | 3 | 1 | 1 |  | 5 | 5.08 | 12.25
Nortrak Stabilizer 13" | SD610174 | 05/12/2021 | 06/09/2021 | 29 | 1 | 1 |  | 5 | 5.08 | 12.25
NMPC | SD54328 | 05/11/2021 | 05/20/2021 | 10 | 6 | 1 ,2 |  | 23.95 | 83.5 | 133.08
UBHO | 775151 | 05/11/2021 | 05/20/2021 | 10 | 6 | 1 ,2 |  | 23.95 | 83.5 | 133.08
NMDC | SD55726 | 05/11/2021 | 05/20/2021 | 10 | 6 | 1 ,2 |  | 23.95 | 83.5 | 133.08
NMDC | SD56047 | 05/11/2021 | 05/20/2021 | 10 | 6 | 1 ,2 |  | 23.95 | 83.5 | 133.08
Crossover Sub | SD114897 | 05/11/2021 | 05/20/2021 | 10 | 1 | 1 |  | 5 | 5.08 | 12.25
SPL613 | 54682 | 05/12/2021 | 06/09/2021 | 29 | 5 | 2 |  | 18.95 | 78.42 | 120.83
8 7/8 5.9 2.0F Slick -.016 | PPM800055 | 05/13/2021 | 05/20/2021 | 8 | 5 | 2 |  | 18.95 | 78.42 | 120.83
Crossover Sub | SD116860 | 05/11/2021 | 05/20/2021 | 10 | 5 | 2 |  | 18.95 | 78.42 | 120.83
2 Stds 6.5 in DC | Rig | 05/12/2021 | 06/09/2021 | 29 | 5 | 2 |  | 18.95 | 78.42 | 120.83
Crossover Sub | SD3539 | 05/11/2021 | 05/20/2021 | 10 | 5 | 2 |  | 18.95 | 78.42 | 120.83
Agitator | P6675-0022 | 05/13/2021 | 06/09/2021 | 28 | 5 | 2 |  | 18.95 | 78.42 | 120.83
GTD64M | 13590860 | 05/20/2021 | 06/09/2021 | 21 | 2 | 3 |  | 17.95 | 9.92 | 55
6/7 11.7 2.0 Slick HS88 .015 | PPM250014 | 05/20/2021 | 05/24/2021 | 5 | 2 | 3 |  | 17.95 | 9.92 | 55
BTI | 306839 | 05/20/2021 | 06/09/2021 | 21 | 8 | 3 ,4 ,5 ,6 |  | 47.62 | 79.48 | 200.58
Pony Collar | SD56837 | 05/20/2021 | 06/09/2021 | 21 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
UBHO | 500048 | 05/11/2021 | 06/03/2021 | 24 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
NMDC | SD56281 | 05/20/2021 | 06/09/2021 | 21 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
Pony Collar | SD56870 | 05/20/2021 | 06/09/2021 | 21 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
NMDC | SD55848 | 05/20/2021 | 06/09/2021 | 21 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
Tomax | A52074 | 05/20/2021 | 06/09/2021 | 21 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
Crossover | SD119105 | 05/20/2021 | 06/09/2021 | 21 | 13 | 3 ,4 ,5 ,6 ,7 |  | 68.53 | 130.82 | 307.25
Reamer | DTI-DNR-98 | 05/20/2021 | 06/09/2021 | 21 | 9 | 3 ,6 ,7 |  | 51.03 | 89.92 | 223.75
Agitator | PG525-0021 | 05/12/2021 | 06/09/2021 | 29 | 4 | 3 ,4 |  | 27.15 | 42.88 | 106
Agitator | PG525-0006 | 05/12/2021 | 06/09/2021 | 29 | 7 | 3 ,7 |  | 38.87 | 61.25 | 161.67
GTD64M | 13090615 | 05/23/2021 | 06/09/2021 | 18 | 2 | 4 |  | 9.2 | 32.97 | 51
7/8 3.8 2.5 Slick HS88 -.001 | MTR475015 | 05/20/2021 | 06/09/2021 | 21 | 2 | 4 |  | 9.2 | 32.97 | 51
GTD64M 6.75 Jets 6X18's | 1138553 | 05/26/2021 | 06/09/2021 | 15 | 4 | 5 ,6 |  | 20.47 | 36.6 | 94.58
6/7 Lobe 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 | PPM250018 | 05/25/2021 | 05/29/2021 | 5 | 1 | 5 |  | 8.3 | 7.93 | 32.5
Agitator | PG5250027 | 05/27/2021 | 06/09/2021 | 14 | 4 | 5 ,6 |  | 20.47 | 36.6 | 94.58
6/7 8.8 @ 2.12? FIX Slick HS88 +.009 | PPM250024 | 05/24/2021 | 06/02/2021 | 10 | 3 | 6 |  | 12.17 | 28.67 | 62.08
Agitator | PG525-0046 | 05/27/2021 | 06/09/2021 | 14 | 3 | 6 |  | 12.17 | 28.67 | 62.08
GTD64M | 13558789 | 05/29/2021 | 06/09/2021 | 12 | 4 | 7 |  | 20.92 | 51.33 | 106.67
6/7 8.8 2.12 Slick HS88 0.021 | PPM250010 | 05/29/2021 | 06/07/2021 | 10 | 4 | 7 |  | 20.92 | 51.33 | 106.67
BTI | 306842 | 05/20/2021 | 06/09/2021 | 21 | 8 | 7 ,8 |  | 30.58 | 71.75 | 198.67
Pulser | 6250 | 05/11/2021 | 06/03/2021 | 23 | 4 | 7 |  | 20.92 | 51.33 | 106.67
Battery - Plug In Hrs 0.00 | 1262 | 05/11/2021 | 06/03/2021 | 23 | 4 | 7 |  | 20.92 | 51.33 | 106.67
Battery - Plug In Hrs 0.00 | 1343 | 05/11/2021 | 06/03/2021 | 23 | 4 | 7 |  | 20.92 | 51.33 | 106.67
Gamma | 3030 | 05/11/2021 | 06/03/2021 | 23 | 4 | 7 |  | 20.92 | 51.33 | 106.67
Directional Module | 7460 | 05/11/2021 | 06/03/2021 | 23 | 4 | 7 |  | 20.92 | 51.33 | 106.67
Agitator | PG525-0015 | 05/12/2021 | 06/09/2021 | 29 | 4 | 7 |  | 20.92 | 51.33 | 106.67
GTD64M | 13594950 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
6/7 8.8 @ 2.12? FIX Slick HPT +.020 | PPM250022 | 06/02/2021 | 06/09/2021 | 8 | 4 | 8 |  | 9.67 | 20.42 | 92
Pony Collar | GT50-10-479 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
UBHO | ZSBX500033 | 05/11/2021 | 06/09/2021 | 30 | 4 | 8 |  | 9.67 | 20.42 | 92
NMDC | SD56699 | 05/20/2021 | 06/09/2021 | 21 | 4 | 8 |  | 9.67 | 20.42 | 92
Pony Collar | GT50-10-637 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
NMDC | SD56777 | 05/20/2021 | 06/09/2021 | 21 | 4 | 8 |  | 9.67 | 20.42 | 92
Tomax | A52102 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
Crossover | GT52331433 | 05/27/2021 | 06/09/2021 | 14 | 4 | 8 |  | 9.67 | 20.42 | 92
6 13/16 Reamer | DTI-DNR-533 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
Agitator | PG525-0037 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
Agitator | PG525-0049 | 06/03/2021 | 06/09/2021 | 7 | 4 | 8 |  | 9.67 | 20.42 | 92
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Fayette County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well-GL: 243 + KB: 28 (Pat248)
Facility |  |  | Rainier - Fayette County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Rainier 1H ST01 |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Rainier 1H ST01
Field: |  |  | Fayette County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas South Central 4204
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 271.00 Usft
Map Northing |  |  | 816982.02 US survey foot |  |  | Map Easting |  |  | 2668460.01 US survey foot
Latitude |  |  | 30° 3' 49.16451" N |  |  | Longitude |  |  | 96° 53' 12.44787" W
Grid Convergence |  |  | 1.035
Facility: |  |  | Rainier - Fayette County, TX
Map Northing |  |  | 751048.80 US survey foot |  |  | Map Easting |  |  | 2699495.95 US survey foot
Latitude |  |  | 29° 52' 50.88026" N |  |  | Longitude |  |  | 96° 47' 33.47983" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.081
Well: |  |  | Rainier 1H ST01
Local North |  |  | 0.01 Usft |  |  | Local East |  |  | 0.00 Usft
Map Northing |  |  | 751048.81 US survey foot |  |  | Map Easting |  |  | 2699495.95 US survey foot
Latitude |  |  | 29° 52' 50.880" N |  |  | Longitude |  |  | 96° 47' 33.480" W
Depth Datum |  |  | Well-GL: 243 + KB: 28 (Pat248) |  |  | Datum Elevation |  |  | 271.00 Usft
GL Elevation |  |  | 243.00 Usft
Grid Convergence |  |  | 1.081
Well bore: |  |  | Rainier 1H ST01
Magnetic Model |  |  | User defined |  |  | Date |  |  | 23/04/2021
Total Field (nT) |  |  | 46485.7 |  |  | Dip Angle (°) |  |  | 58.583
Declination (°) |  |  | 3
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 133.1
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Rainier 1H ST01
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2956 |  |  | Rainer 1H Surveys 1 |  |  | MWD+HDGM
2956 |  |  | 11915 |  |  | Rainier 1H Surveys 2 |  |  | MWD+HDGM
11915 |  |  | 12626 |  |  | Rainier 1H Surveys 3 |  |  | MWD+HDGM
12626 |  |  | 15412 |  |  | Rainier 1H Surveys 4 |  |  | MWD+HDGM
15412 |  |  | 18446 |  |  | Rainier 1H Surveys 5 |  |  | MWD+HDGM
18446 |  |  | 20591 |  |  | Rainier 1H Surveys 6 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -271 | 751048.81 | 2699495.95 | 29.8808 | -96.7926 | 0
143 | 0.2 | 227.43 | 143 | -0.17 | -0.18 | -0.02 | 0.14 | 0.14 | 92.71 | 227.43 | 143 | -128 | 751048.64 | 2699495.77 | 29.8808 | -96.7926 | 227.43
235 | 0.39 | 273.36 | 235 | -0.26 | -0.61 | -0.27 | 0.31 | 0.21 | 49.92 | 75.73 | 92 | -36 | 751048.55 | 2699495.34 | 29.8808 | -96.7926 | 247.14
328 | 0.48 | 275.81 | 328 | -0.2 | -1.32 | -0.83 | 0.1 | 0.1 | 2.63 | 12.9 | 93 | 57 | 751048.61 | 2699494.63 | 29.8808 | -96.7926 | 261.32
418 | 0.45 | 282.42 | 417.99 | -0.09 | -2.04 | -1.43 | 0.07 | -0.03 | 7.34 | 122.49 | 90 | 146.99 | 751048.72 | 2699493.91 | 29.8808 | -96.7926 | 267.56
513 | 0.63 | 3.54 | 512.99 | 0.51 | -2.37 | -2.08 | 0.75 | 0.19 | 85.39 | 119.54 | 95 | 241.99 | 751049.32 | 2699493.58 | 29.8808 | -96.7926 | 282.25
606 | 1.68 | 43.79 | 605.97 | 2.01 | -1.4 | -2.39 | 1.36 | 1.13 | 43.28 | 59 | 93 | 334.97 | 751050.82 | 2699494.55 | 29.8808 | -96.7926 | 325.22
700 | 3.38 | 40.99 | 699.88 | 5.1 | 1.38 | -2.48 | 1.81 | 1.81 | -2.98 | -5.56 | 94 | 428.88 | 751053.91 | 2699497.33 | 29.8808 | -96.7926 | 15.11
795 | 5.02 | 40.89 | 794.62 | 10.35 | 5.93 | -2.74 | 1.73 | 1.73 | -0.11 | -0.31 | 95 | 523.62 | 751059.16 | 2699501.88 | 29.8808 | -96.7926 | 29.82
889 | 6.73 | 50.86 | 888.12 | 16.94 | 12.9 | -2.16 | 2.11 | 1.82 | 10.61 | 35.85 | 94 | 617.12 | 751065.75 | 2699508.85 | 29.8808 | -96.7926 | 37.29
982 | 7.7 | 50.33 | 980.39 | 24.36 | 21.92 | -0.64 | 1.05 | 1.04 | -0.57 | -4.19 | 93 | 709.39 | 751073.17 | 2699517.87 | 29.8809 | -96.7926 | 41.99
1077 | 8.65 | 47.68 | 1074.42 | 33.23 | 32.1 | 0.74 | 1.08 | 1 | -2.79 | -22.95 | 95 | 803.42 | 751082.04 | 2699528.05 | 29.8809 | -96.7925 | 44.01
1171 | 9.37 | 42.54 | 1167.26 | 43.63 | 42.5 | 1.23 | 1.15 | 0.77 | -5.47 | -50.75 | 94 | 896.26 | 751092.44 | 2699538.45 | 29.8809 | -96.7925 | 44.25
1265 | 9.89 | 30.96 | 1259.94 | 56.19 | 51.83 | -0.55 | 2.13 | 0.55 | -12.32 | -80.73 | 94 | 988.94 | 751105 | 2699547.78 | 29.881 | -96.7925 | 42.69
1359 | 9.57 | 27.18 | 1352.59 | 70.06 | 59.55 | -4.39 | 0.76 | -0.34 | -4.02 | -118.46 | 94 | 1081.59 | 751118.87 | 2699555.5 | 29.881 | -96.7924 | 40.36
1452 | 9.19 | 25.88 | 1444.35 | 83.62 | 66.33 | -8.71 | 0.47 | -0.41 | -1.4 | -151.5 | 93 | 1173.35 | 751132.43 | 2699562.28 | 29.881 | -96.7924 | 38.42
1546 | 8.92 | 32.21 | 1537.18 | 96.54 | 73.49 | -12.31 | 1.1 | -0.29 | 6.73 | 108.28 | 94 | 1266.18 | 751145.35 | 2699569.44 | 29.8811 | -96.7924 | 37.28
1641 | 9.05 | 32.84 | 1631.01 | 109.05 | 81.46 | -15.03 | 0.17 | 0.14 | 0.66 | 37.43 | 95 | 1360.01 | 751157.86 | 2699577.41 | 29.8811 | -96.7924 | 36.76
1736 | 10.79 | 36.53 | 1724.59 | 122.47 | 90.81 | -17.38 | 1.95 | 1.83 | 3.88 | 21.89 | 95 | 1453.59 | 751171.28 | 2699586.76 | 29.8811 | -96.7923 | 36.56
1829 | 12.03 | 36.81 | 1815.75 | 137.23 | 101.8 | -19.43 | 1.33 | 1.33 | 0.3 | 2.7 | 93 | 1544.75 | 751186.04 | 2699597.75 | 29.8812 | -96.7923 | 36.57
1923 | 14.21 | 38.66 | 1907.29 | 154.08 | 114.88 | -21.4 | 2.36 | 2.32 | 1.97 | 11.81 | 94 | 1636.29 | 751202.89 | 2699610.83 | 29.8812 | -96.7923 | 36.71
2017 | 15.1 | 38.84 | 1998.23 | 172.63 | 129.76 | -23.2 | 0.95 | 0.95 | 0.19 | 3.02 | 94 | 1727.23 | 751221.44 | 2699625.71 | 29.8813 | -96.7922 | 36.93
2111 | 14.94 | 38.85 | 2089.02 | 191.6 | 145.04 | -25.01 | 0.17 | -0.17 | 0.01 | 179.08 | 94 | 1818.02 | 751240.41 | 2699640.99 | 29.8813 | -96.7922 | 37.13
2205 | 14.56 | 39.02 | 2179.92 | 210.22 | 160.08 | -26.75 | 0.41 | -0.4 | 0.18 | 173.58 | 94 | 1908.92 | 751259.03 | 2699656.03 | 29.8814 | -96.7921 | 37.29
2299 | 14.11 | 39.45 | 2271 | 228.25 | 174.8 | -28.32 | 0.49 | -0.48 | 0.46 | 166.9 | 94 | 2000 | 751277.06 | 2699670.75 | 29.8814 | -96.7921 | 37.45
2393 | 13.88 | 39.8 | 2362.21 | 245.76 | 189.3 | -29.7 | 0.26 | -0.24 | 0.37 | 159.97 | 94 | 2091.21 | 751294.57 | 2699685.25 | 29.8815 | -96.792 | 37.61
2487 | 12.78 | 38.74 | 2453.67 | 262.53 | 203.02 | -31.14 | 1.2 | -1.17 | -1.13 | -167.99 | 94 | 2182.67 | 751311.34 | 2699698.97 | 29.8815 | -96.792 | 37.72
2581 | 13.38 | 36.99 | 2545.23 | 279.32 | 216.07 | -33.09 | 0.76 | 0.64 | -1.86 | -34.28 | 94 | 2274.23 | 751328.13 | 2699712.02 | 29.8816 | -96.7919 | 37.72
2675 | 13.39 | 36.82 | 2636.68 | 296.73 | 229.14 | -35.43 | 0.04 | 0.01 | -0.18 | -75.83 | 94 | 2365.68 | 751345.54 | 2699725.09 | 29.8816 | -96.7919 | 37.68
2769 | 10.41 | 24.56 | 2728.67 | 313.17 | 239.2 | -39.33 | 4.14 | -3.17 | -13.04 | -145.58 | 94 | 2457.67 | 751361.98 | 2699735.15 | 29.8816 | -96.7919 | 37.37
2863 | 9.18 | 18.87 | 2821.3 | 327.99 | 245.15 | -45.1 | 1.66 | -1.31 | -6.05 | -144.58 | 94 | 2550.3 | 751376.8 | 2699741.1 | 29.8817 | -96.7918 | 36.78
2956 | 8.52 | 16.96 | 2913.19 | 341.6 | 249.56 | -51.18 | 0.78 | -0.71 | -2.05 | -156.94 | 93 | 2642.19 | 751390.41 | 2699745.51 | 29.8817 | -96.7918 | 36.15
3071 | 7.79 | 14.09 | 3027.02 | 357.31 | 253.94 | -58.72 | 0.73 | -0.63 | -2.5 | -152.27 | 115 | 2756.02 | 751406.12 | 2699749.89 | 29.8818 | -96.7918 | 35.4
3165 | 8.24 | 24.62 | 3120.11 | 369.61 | 258.3 | -63.94 | 1.63 | 0.48 | 11.2 | 78.22 | 94 | 2849.11 | 751418.42 | 2699754.25 | 29.8818 | -96.7918 | 34.95
3259 | 7.61 | 39.37 | 3213.22 | 380.55 | 265.06 | -66.48 | 2.26 | -0.67 | 15.69 | 114.43 | 94 | 2942.22 | 751429.36 | 2699761.01 | 29.8818 | -96.7918 | 34.86
3353 | 7.96 | 33.87 | 3306.36 | 390.76 | 272.63 | -67.93 | 0.88 | 0.37 | -5.85 | -67.58 | 94 | 3035.36 | 751439.57 | 2699768.58 | 29.8819 | -96.7917 | 34.9
3447 | 10.04 | 35.62 | 3399.2 | 402.83 | 281.03 | -70.04 | 2.23 | 2.21 | 1.86 | 8.36 | 94 | 3128.2 | 751451.64 | 2699776.98 | 29.8819 | -96.7917 | 34.9
3541 | 11.79 | 32.59 | 3491.49 | 417.58 | 290.98 | -72.86 | 1.96 | 1.86 | -3.22 | -19.64 | 94 | 3220.49 | 751466.39 | 2699786.93 | 29.8819 | -96.7917 | 34.87
3635 | 11.38 | 30.76 | 3583.58 | 433.64 | 300.89 | -76.59 | 0.59 | -0.44 | -1.95 | -139.02 | 94 | 3312.58 | 751482.45 | 2699796.84 | 29.882 | -96.7917 | 34.76
3729 | 10.14 | 31.12 | 3675.92 | 448.7 | 309.91 | -80.29 | 1.32 | -1.32 | 0.38 | 177.07 | 94 | 3404.92 | 751497.51 | 2699805.86 | 29.882 | -96.7916 | 34.63
3822 | 12.6 | 28.37 | 3767.09 | 464.63 | 318.97 | -84.57 | 2.71 | 2.65 | -2.96 | -13.78 | 93 | 3496.09 | 751513.44 | 2699814.92 | 29.8821 | -96.7916 | 34.47
3916 | 13.05 | 26.79 | 3858.75 | 483.13 | 328.62 | -90.16 | 0.61 | 0.48 | -1.68 | -38.7 | 94 | 3587.75 | 751531.94 | 2699824.57 | 29.8821 | -96.7916 | 34.22
4010 | 12.82 | 29.42 | 3950.36 | 501.68 | 338.53 | -95.61 | 0.67 | -0.24 | 2.8 | 112.62 | 94 | 3679.36 | 751550.49 | 2699834.48 | 29.8822 | -96.7915 | 34.01
4105 | 13.85 | 30.42 | 4042.8 | 520.67 | 349.46 | -100.6 | 1.11 | 1.08 | 1.05 | 13.11 | 95 | 3771.8 | 751569.48 | 2699845.41 | 29.8822 | -96.7915 | 33.87
4198 | 13.92 | 39.57 | 4133.09 | 538.89 | 362.23 | -103.73 | 2.36 | 0.08 | 9.84 | 92.62 | 93 | 3862.09 | 751587.7 | 2699858.18 | 29.8823 | -96.7915 | 33.91
4292 | 12.99 | 38.37 | 4224.51 | 555.89 | 375.99 | -105.3 | 1.03 | -0.99 | -1.28 | -163.87 | 94 | 3953.51 | 751604.7 | 2699871.94 | 29.8823 | -96.7914 | 34.07
4386 | 12.34 | 36.44 | 4316.22 | 572.26 | 388.51 | -107.33 | 0.83 | -0.69 | -2.05 | -147.87 | 94 | 4045.22 | 751621.07 | 2699884.46 | 29.8824 | -96.7914 | 34.17
4479 | 11.59 | 35.02 | 4407.2 | 587.9 | 399.78 | -109.8 | 0.87 | -0.81 | -1.53 | -159.26 | 93 | 4136.2 | 751636.71 | 2699895.73 | 29.8824 | -96.7913 | 34.22
4573 | 10.97 | 34.23 | 4499.39 | 603.03 | 410.23 | -112.5 | 0.68 | -0.66 | -0.84 | -166.39 | 94 | 4228.39 | 751651.84 | 2699906.18 | 29.8824 | -96.7913 | 34.23
4666 | 12.13 | 33.76 | 4590.5 | 618.47 | 420.63 | -115.45 | 1.25 | 1.25 | -0.51 | -4.87 | 93 | 4319.5 | 751667.28 | 2699916.58 | 29.8825 | -96.7913 | 34.22
4760 | 12.91 | 38.25 | 4682.27 | 634.93 | 432.62 | -117.95 | 1.33 | 0.83 | 4.78 | 53.5 | 94 | 4411.27 | 751683.74 | 2699928.57 | 29.8825 | -96.7912 | 34.27
4854 | 12.85 | 37.78 | 4773.9 | 651.44 | 445.53 | -119.8 | 0.13 | -0.06 | -0.5 | -120.03 | 94 | 4502.9 | 751700.25 | 2699941.48 | 29.8826 | -96.7912 | 34.37
4948 | 12.74 | 37.67 | 4865.57 | 667.9 | 458.27 | -121.75 | 0.12 | -0.12 | -0.12 | -167.57 | 94 | 4594.57 | 751716.71 | 2699954.22 | 29.8826 | -96.7911 | 34.46
5043 | 12.77 | 36.32 | 4958.23 | 684.65 | 470.89 | -123.98 | 0.32 | 0.03 | -1.42 | -84.91 | 95 | 4687.23 | 751733.46 | 2699966.84 | 29.8827 | -96.7911 | 34.52
5137 | 12.73 | 35.99 | 5049.91 | 701.4 | 483.12 | -126.49 | 0.09 | -0.04 | -0.35 | -118.94 | 94 | 4778.91 | 751750.21 | 2699979.07 | 29.8827 | -96.7911 | 34.56
5231 | 12.75 | 35.48 | 5141.59 | 718.23 | 495.23 | -129.15 | 0.12 | 0.02 | -0.54 | -80.17 | 94 | 4870.59 | 751767.04 | 2699991.18 | 29.8827 | -96.791 | 34.59
5325 | 12.74 | 34.33 | 5233.28 | 735.24 | 507.1 | -132.1 | 0.27 | -0.01 | -1.22 | -92.82 | 94 | 4962.28 | 751784.05 | 2700003.05 | 29.8828 | -96.791 | 34.59
5419 | 12.39 | 33.2 | 5325.03 | 752.23 | 518.46 | -135.42 | 0.45 | -0.37 | -1.2 | -145.47 | 94 | 5054.03 | 751801.04 | 2700014.41 | 29.8828 | -96.791 | 34.58
5513 | 12.29 | 32.08 | 5416.85 | 769.15 | 529.3 | -139.07 | 0.28 | -0.11 | -1.19 | -113.22 | 94 | 5145.85 | 751817.96 | 2700025.25 | 29.8829 | -96.7909 | 34.53
5607 | 12.27 | 31.05 | 5508.7 | 786.18 | 539.76 | -143.06 | 0.23 | -0.02 | -1.1 | -95.72 | 94 | 5237.7 | 751834.99 | 2700035.71 | 29.8829 | -96.7909 | 34.47
5701 | 11.06 | 28.02 | 5600.76 | 802.7 | 549.15 | -147.49 | 1.44 | -1.29 | -3.22 | -154.62 | 94 | 5329.76 | 751851.51 | 2700045.1 | 29.883 | -96.7909 | 34.38
5795 | 10.09 | 21.93 | 5693.17 | 818.3 | 556.46 | -152.81 | 1.57 | -1.03 | -6.48 | -133.92 | 94 | 5422.17 | 751867.11 | 2700052.41 | 29.883 | -96.7908 | 34.22
5889 | 10.05 | 17.95 | 5785.72 | 833.74 | 562.07 | -159.27 | 0.74 | -0.04 | -4.23 | -95.25 | 94 | 5514.72 | 751882.55 | 2700058.02 | 29.8831 | -96.7908 | 33.99
5983 | 10.81 | 23.34 | 5878.17 | 849.64 | 568.09 | -165.74 | 1.31 | 0.81 | 5.73 | 54.76 | 94 | 5607.17 | 751898.45 | 2700064.04 | 29.8831 | -96.7908 | 33.77
6078 | 10.13 | 27.06 | 5971.59 | 865.26 | 575.42 | -171.06 | 1.01 | -0.72 | 3.92 | 136.99 | 95 | 5700.59 | 751914.07 | 2700071.37 | 29.8831 | -96.7908 | 33.62
6171 | 10.35 | 31.62 | 6063.11 | 879.66 | 583.52 | -174.98 | 0.9 | 0.24 | 4.9 | 77.07 | 93 | 5792.11 | 751928.47 | 2700079.47 | 29.8832 | -96.7907 | 33.56
6266 | 11.68 | 39.78 | 6156.36 | 894.31 | 594.15 | -177.24 | 2.15 | 1.4 | 8.59 | 53.59 | 95 | 5885.36 | 751943.12 | 2700090.1 | 29.8832 | -96.7907 | 33.6
6360 | 12.03 | 42.07 | 6248.36 | 908.9 | 606.8 | -177.96 | 0.62 | 0.37 | 2.44 | 54.48 | 94 | 5977.36 | 751957.71 | 2700102.75 | 29.8833 | -96.7907 | 33.73
6454 | 11.41 | 41.93 | 6340.4 | 923.09 | 619.58 | -178.33 | 0.66 | -0.66 | -0.15 | -177.44 | 94 | 6069.4 | 751971.9 | 2700115.53 | 29.8833 | -96.7906 | 33.87
6547 | 11.27 | 42.1 | 6431.58 | 936.67 | 631.81 | -178.68 | 0.15 | -0.15 | 0.18 | 166.65 | 93 | 6160.58 | 751985.48 | 2700127.76 | 29.8833 | -96.7906 | 34
6642 | 11.02 | 42.73 | 6524.79 | 950.23 | 644.2 | -178.9 | 0.29 | -0.26 | 0.66 | 154.34 | 95 | 6253.79 | 751999.04 | 2700140.15 | 29.8834 | -96.7905 | 34.13
6735 | 10.61 | 41.93 | 6616.14 | 963.13 | 655.95 | -179.13 | 0.47 | -0.44 | -0.86 | -160.28 | 93 | 6345.14 | 752011.94 | 2700151.9 | 29.8834 | -96.7905 | 34.26
6830 | 11.56 | 45.17 | 6709.36 | 976.35 | 668.55 | -178.96 | 1.2 | 1 | 3.41 | 34.85 | 95 | 6438.36 | 752025.16 | 2700164.5 | 29.8834 | -96.7905 | 34.4
6924 | 11.78 | 42.49 | 6801.42 | 990.06 | 681.71 | -178.73 | 0.62 | 0.23 | -2.85 | -69.23 | 94 | 6530.42 | 752038.87 | 2700177.66 | 29.8835 | -96.7904 | 34.55
7015 | 12.42 | 39.34 | 6890.4 | 1004.48 | 694.19 | -179.47 | 1.01 | 0.7 | -3.46 | -47.44 | 91 | 6619.4 | 752053.29 | 2700190.14 | 29.8835 | -96.7904 | 34.65
7110 | 12.93 | 40.07 | 6983.09 | 1020.52 | 707.5 | -180.7 | 0.56 | 0.54 | 0.77 | 17.79 | 95 | 6712.09 | 752069.33 | 2700203.45 | 29.8836 | -96.7903 | 34.73
7203 | 12.87 | 38.89 | 7073.74 | 1036.54 | 720.71 | -182.01 | 0.29 | -0.06 | -1.27 | -103.41 | 93 | 6802.74 | 752085.35 | 2700216.66 | 29.8836 | -96.7903 | 34.81
7297 | 11.77 | 36.31 | 7165.57 | 1052.42 | 732.96 | -183.91 | 1.31 | -1.17 | -2.74 | -154.67 | 94 | 6894.57 | 752101.23 | 2700228.91 | 29.8837 | -96.7903 | 34.86
7391 | 11.06 | 40.53 | 7257.71 | 1066.99 | 744.49 | -185.45 | 1.17 | -0.76 | 4.49 | 132.42 | 94 | 6986.71 | 752115.8 | 2700240.44 | 29.8837 | -96.7902 | 34.91
7484 | 11.24 | 43.21 | 7348.96 | 1080.38 | 756.49 | -185.83 | 0.59 | 0.19 | 2.88 | 72.16 | 93 | 7077.96 | 752129.19 | 2700252.44 | 29.8837 | -96.7902 | 35
7579 | 11.02 | 37.82 | 7442.18 | 1094.3 | 768.4 | -186.65 | 1.12 | -0.23 | -5.67 | -104.57 | 95 | 7171.18 | 752143.11 | 2700264.35 | 29.8838 | -96.7901 | 35.08
7673 | 11.54 | 35.63 | 7534.36 | 1109.04 | 779.39 | -188.7 | 0.72 | 0.55 | -2.33 | -40.56 | 94 | 7263.36 | 752157.85 | 2700275.34 | 29.8838 | -96.7901 | 35.1
7767 | 11.75 | 43.89 | 7626.43 | 1123.58 | 791.5 | -189.79 | 1.79 | 0.22 | 8.79 | 86.88 | 94 | 7355.43 | 752172.39 | 2700287.45 | 29.8838 | -96.7901 | 35.16
7861 | 12.15 | 47.73 | 7718.4 | 1137.13 | 805.46 | -188.86 | 0.95 | 0.43 | 4.09 | 65.18 | 94 | 7447.4 | 752185.94 | 2700301.41 | 29.8839 | -96.79 | 35.31
7955 | 10.72 | 45.72 | 7810.53 | 1149.89 | 819.04 | -187.66 | 1.58 | -1.52 | -2.14 | -165.41 | 94 | 7539.53 | 752198.7 | 2700314.99 | 29.8839 | -96.79 | 35.46
8049 | 10.86 | 41.63 | 7902.87 | 1162.61 | 831.18 | -187.49 | 0.83 | 0.15 | -4.35 | -81.65 | 94 | 7631.87 | 752211.42 | 2700327.13 | 29.884 | -96.7899 | 35.56
8143 | 11.73 | 35.46 | 7995.05 | 1177.02 | 842.61 | -188.99 | 1.58 | 0.93 | -6.56 | -57.3 | 94 | 7724.05 | 752225.83 | 2700338.56 | 29.884 | -96.7899 | 35.6
8236 | 11.71 | 28.79 | 8086.11 | 1192.99 | 852.64 | -192.58 | 1.46 | -0.02 | -7.17 | -94.11 | 93 | 7815.11 | 752241.8 | 2700348.59 | 29.884 | -96.7899 | 35.55
8330 | 12.34 | 23.84 | 8178.05 | 1210.54 | 861.29 | -198.25 | 1.29 | 0.67 | -5.27 | -61.02 | 94 | 7907.05 | 752259.35 | 2700357.24 | 29.8841 | -96.7898 | 35.43
8424 | 11.14 | 20.97 | 8270.09 | 1228.2 | 868.6 | -204.98 | 1.42 | -1.28 | -3.05 | -155.45 | 94 | 7999.09 | 752277.01 | 2700364.55 | 29.8841 | -96.7898 | 35.27
8519 | 10.17 | 17.73 | 8363.45 | 1244.76 | 874.44 | -212.03 | 1.2 | -1.02 | -3.41 | -149.89 | 95 | 8092.45 | 752293.57 | 2700370.39 | 29.8842 | -96.7898 | 35.09
8613 | 10.06 | 22.98 | 8455.99 | 1260.23 | 880.17 | -218.41 | 0.99 | -0.12 | 5.59 | 99.38 | 94 | 8184.99 | 752309.04 | 2700376.12 | 29.8842 | -96.7898 | 34.93
8708 | 11.06 | 26.58 | 8549.38 | 1276.02 | 887.49 | -223.86 | 1.26 | 1.05 | 3.79 | 35.19 | 95 | 8278.38 | 752324.83 | 2700383.44 | 29.8843 | -96.7898 | 34.82
8801 | 12.49 | 32.28 | 8640.42 | 1292.5 | 896.85 | -228.28 | 1.98 | 1.54 | 6.13 | 41.94 | 93 | 8369.42 | 752341.31 | 2700392.8 | 29.8843 | -96.7897 | 34.76
8894 | 12.75 | 32.93 | 8731.18 | 1309.61 | 907.8 | -231.98 | 0.32 | 0.28 | 0.7 | 28.96 | 93 | 8460.18 | 752358.42 | 2700403.75 | 29.8844 | -96.7897 | 34.73
8988 | 11.49 | 29.99 | 8823.08 | 1326.43 | 918.12 | -235.94 | 1.49 | -1.34 | -3.13 | -155.33 | 94 | 8552.08 | 752375.24 | 2700414.07 | 29.8844 | -96.7897 | 34.69
9082 | 10.39 | 28.01 | 8915.37 | 1342.02 | 926.78 | -240.27 | 1.24 | -1.17 | -2.11 | -162.11 | 94 | 8644.37 | 752390.83 | 2700422.73 | 29.8844 | -96.7896 | 34.63
9177 | 12.57 | 37.74 | 9008.47 | 1357.76 | 937.13 | -243.46 | 3.06 | 2.29 | 10.24 | 46.45 | 95 | 8737.47 | 752406.57 | 2700433.08 | 29.8845 | -96.7896 | 34.61
9270 | 12.03 | 38.02 | 9099.34 | 1373.4 | 949.3 | -245.27 | 0.58 | -0.58 | 0.3 | 173.83 | 93 | 8828.34 | 752422.21 | 2700445.25 | 29.8845 | -96.7896 | 34.65
9364 | 10.88 | 36.76 | 9191.46 | 1388.23 | 960.64 | -247.11 | 1.25 | -1.22 | -1.34 | -168.34 | 94 | 8920.46 | 752437.04 | 2700456.59 | 29.8846 | -96.7895 | 34.68
9458 | 11.34 | 38.46 | 9283.7 | 1402.57 | 971.7 | -248.84 | 0.6 | 0.49 | 1.81 | 36.29 | 94 | 9012.7 | 752451.38 | 2700467.65 | 29.8846 | -96.7895 | 34.71
9552 | 10.65 | 36.73 | 9375.98 | 1416.77 | 982.64 | -250.55 | 0.81 | -0.73 | -1.84 | -155.29 | 94 | 9104.98 | 752465.58 | 2700478.59 | 29.8846 | -96.7894 | 34.74
9647 | 10.17 | 37.57 | 9469.41 | 1430.45 | 993 | -252.34 | 0.53 | -0.51 | 0.88 | 162.87 | 95 | 9198.41 | 752479.26 | 2700488.95 | 29.8847 | -96.7894 | 34.77
9740 | 10.82 | 47.12 | 9560.86 | 1442.9 | 1004.41 | -252.51 | 1.99 | 0.7 | 10.27 | 74.25 | 93 | 9289.86 | 752491.71 | 2700500.36 | 29.8847 | -96.7894 | 34.84
9834 | 11.17 | 52.87 | 9653.14 | 1454.4 | 1018.13 | -250.35 | 1.22 | 0.37 | 6.12 | 75.14 | 94 | 9382.14 | 752503.21 | 2700514.08 | 29.8847 | -96.7893 | 34.99
9927 | 9.59 | 49.09 | 9744.62 | 1464.91 | 1031.17 | -248.01 | 1.85 | -1.7 | -4.06 | -158.53 | 93 | 9473.62 | 752513.72 | 2700527.12 | 29.8848 | -96.7893 | 35.14
10021 | 8.61 | 46.51 | 9837.43 | 1474.88 | 1042.19 | -246.78 | 1.13 | -1.04 | -2.74 | -158.66 | 94 | 9566.43 | 752523.69 | 2700538.14 | 29.8848 | -96.7893 | 35.25
10114 | 7.27 | 41.65 | 9929.54 | 1484.07 | 1051.15 | -246.51 | 1.61 | -1.44 | -5.23 | -155.78 | 93 | 9658.54 | 752532.88 | 2700547.1 | 29.8848 | -96.7892 | 35.31
10208 | 6.17 | 37.16 | 10022.89 | 1492.54 | 1058.16 | -247.19 | 1.3 | -1.17 | -4.78 | -156.69 | 94 | 9751.89 | 752541.35 | 2700554.11 | 29.8848 | -96.7892 | 35.34
10302 | 6.28 | 44.74 | 10116.34 | 1500.22 | 1064.83 | -247.56 | 0.88 | 0.12 | 8.06 | 86.16 | 94 | 9845.34 | 752549.03 | 2700560.78 | 29.8849 | -96.7892 | 35.37
10396 | 5.27 | 48.29 | 10209.86 | 1506.74 | 1071.67 | -247.02 | 1.14 | -1.07 | 3.78 | 162.28 | 94 | 9938.86 | 752555.55 | 2700567.62 | 29.8849 | -96.7892 | 35.42
10490 | 4.97 | 46.63 | 10303.49 | 1512.41 | 1077.85 | -246.38 | 0.36 | -0.32 | -1.77 | -154.54 | 94 | 10032.49 | 752561.22 | 2700573.8 | 29.8849 | -96.7891 | 35.48
10583 | 3.95 | 39.05 | 10396.21 | 1517.67 | 1082.8 | -246.36 | 1.26 | -1.1 | -8.15 | -153.72 | 93 | 10125.21 | 752566.48 | 2700578.75 | 29.8849 | -96.7891 | 35.51
10678 | 4.3 | 32.07 | 10490.96 | 1523.22 | 1086.75 | -247.27 | 0.64 | 0.37 | -7.35 | -58.63 | 95 | 10219.96 | 752572.03 | 2700582.7 | 29.8849 | -96.7891 | 35.51
10772 | 4.4 | 41.58 | 10584.69 | 1528.91 | 1091.02 | -248.04 | 0.77 | 0.11 | 10.12 | 86.87 | 94 | 10313.69 | 752577.72 | 2700586.97 | 29.8849 | -96.7891 | 35.51
10866 | 4.38 | 34.6 | 10678.42 | 1534.56 | 1095.45 | -248.67 | 0.57 | -0.02 | -7.43 | -95.62 | 94 | 10407.42 | 752583.37 | 2700591.4 | 29.885 | -96.7891 | 35.52
10960 | 3.93 | 17.45 | 10772.17 | 1540.59 | 1098.45 | -250.6 | 1.4 | -0.48 | -18.24 | -118.32 | 94 | 10501.17 | 752589.4 | 2700594.4 | 29.885 | -96.7891 | 35.49
11053 | 3.81 | 358.97 | 10864.96 | 1546.72 | 1099.35 | -254.13 | 1.34 | -0.13 | 19.87 | -104.67 | 93 | 10593.96 | 752595.53 | 2700595.3 | 29.885 | -96.7891 | 35.4
11147 | 3.88 | 347.34 | 10958.75 | 1552.94 | 1098.6 | -258.93 | 0.83 | 0.07 | -12.37 | -90.69 | 94 | 10687.75 | 752601.75 | 2700594.55 | 29.885 | -96.7891 | 35.28
11240 | 3.95 | 339.68 | 11051.54 | 1559.02 | 1096.8 | -264.4 | 0.57 | 0.08 | -8.24 | -86.21 | 93 | 10780.54 | 752607.83 | 2700592.75 | 29.885 | -96.7891 | 35.13
11334 | 3.01 | 339.3 | 11145.36 | 1564.36 | 1094.8 | -269.51 | 1 | -1 | -0.4 | -178.78 | 94 | 10874.36 | 752613.17 | 2700590.75 | 29.885 | -96.7891 | 34.99
11427 | 2.62 | 339.22 | 11238.25 | 1568.63 | 1093.18 | -273.61 | 0.42 | -0.42 | -0.09 | -179.46 | 93 | 10967.25 | 752617.44 | 2700589.13 | 29.8851 | -96.7891 | 34.87
11521 | 2.19 | 31.58 | 11332.18 | 1572.17 | 1093.36 | -275.89 | 2.29 | -0.46 | 55.7 | 126.47 | 94 | 11061.18 | 752620.98 | 2700589.31 | 29.8851 | -96.7891 | 34.82
11614 | 1.7 | 54.45 | 11425.13 | 1574.49 | 1095.41 | -275.98 | 0.98 | -0.53 | 24.59 | 133.35 | 93 | 11154.13 | 752623.3 | 2700591.36 | 29.8851 | -96.7891 | 34.83
11708 | 3.76 | 99.54 | 11519.02 | 1574.79 | 1099.59 | -273.13 | 3.01 | 2.19 | 47.97 | 70.25 | 94 | 11248.02 | 752623.6 | 2700595.54 | 29.8851 | -96.7891 | 34.92
11802 | 6.23 | 124.67 | 11612.67 | 1571.38 | 1106.83 | -265.52 | 3.45 | 2.63 | 26.73 | 54.52 | 94 | 11341.67 | 752620.19 | 2700602.78 | 29.8851 | -96.789 | 35.16
11896 | 5.42 | 127.01 | 11706.18 | 1565.8 | 1114.57 | -256.06 | 0.9 | -0.86 | 2.49 | 164.82 | 94 | 11435.18 | 752614.61 | 2700610.52 | 29.885 | -96.789 | 35.44
11915 | 5.19 | 128.29 | 11725.1 | 1564.73 | 1115.96 | -254.31 | 1.36 | -1.21 | 6.74 | 153.41 | 19 | 11454.1 | 752613.54 | 2700611.91 | 29.885 | -96.789 | 35.5
11990 | 6.14 | 135.25 | 11799.74 | 1559.78 | 1121.44 | -246.92 | 1.56 | 1.27 | 9.28 | 39.37 | 75 | 11528.74 | 752608.59 | 2700617.39 | 29.885 | -96.789 | 35.72
12085 | 15.62 | 145.67 | 11892.93 | 1545.58 | 1132.26 | -229.32 | 10.15 | 9.98 | 10.97 | 16.9 | 95 | 11621.93 | 752594.39 | 2700628.21 | 29.885 | -96.789 | 36.23
12181 | 23.96 | 139.68 | 11983.19 | 1519.99 | 1152.2 | -197.28 | 8.93 | 8.69 | -6.24 | -16.52 | 96 | 11712.19 | 752568.8 | 2700648.15 | 29.8849 | -96.7889 | 37.16
12244 | 24.85 | 149.89 | 12040.59 | 1498.78 | 1167.12 | -171.89 | 6.84 | 1.41 | 16.21 | 82.77 | 63 | 11769.59 | 752547.59 | 2700663.07 | 29.8849 | -96.7889 | 37.91
12339 | 32.89 | 150.78 | 12123.71 | 1458.93 | 1189.76 | -128.13 | 8.48 | 8.46 | 0.94 | 3.45 | 95 | 11852.71 | 752507.74 | 2700685.71 | 29.8848 | -96.7888 | 39.2
12436 | 42.09 | 141.13 | 12200.66 | 1410.49 | 1223.12 | -70.67 | 11.23 | 9.48 | -9.95 | -36.49 | 97 | 11929.66 | 752459.3 | 2700719.07 | 29.8846 | -96.7887 | 40.93
12532 | 55.51 | 135.63 | 12263.78 | 1356.89 | 1271.22 | 1.07 | 14.62 | 13.98 | -5.73 | -19.01 | 96 | 11992.78 | 752405.7 | 2700767.17 | 29.8845 | -96.7885 | 43.13
12626 | 69.86 | 133.11 | 12306.8 | 1298.73 | 1330.84 | 84.34 | 15.45 | 15.27 | -2.68 | -9.48 | 94 | 12035.8 | 752347.54 | 2700826.79 | 29.8843 | -96.7884 | 45.7
12754 | 76.84 | 129.35 | 12343.47 | 1218.03 | 1423.04 | 206.81 | 6.14 | 5.45 | -2.94 | -27.86 | 128 | 12072.47 | 752266.84 | 2700918.99 | 29.8841 | -96.7881 | 49.44
12849 | 80 | 126.6 | 12362.54 | 1160.79 | 1496.4 | 299.48 | 4.37 | 3.33 | -2.89 | -40.73 | 95 | 12091.54 | 752209.6 | 2700992.35 | 29.8839 | -96.7878 | 52.2
12943 | 86.52 | 123.29 | 12373.57 | 1107.37 | 1572.88 | 391.82 | 7.77 | 6.94 | -3.52 | -26.97 | 94 | 12102.57 | 752156.18 | 2701068.83 | 29.8838 | -96.7876 | 54.85
13039 | 88.01 | 121.1 | 12378.15 | 1056.28 | 1654.02 | 485.97 | 2.76 | 1.55 | -2.28 | -55.8 | 96 | 12107.15 | 752105.09 | 2701149.97 | 29.8836 | -96.7874 | 57.44
13134 | 87.13 | 124.02 | 12382.18 | 1005.21 | 1734 | 579.27 | 3.21 | -0.93 | 3.07 | 106.84 | 95 | 12111.18 | 752054.02 | 2701229.95 | 29.8835 | -96.7871 | 59.9
13230 | 87 | 127.66 | 12387.1 | 949.08 | 1811.71 | 674.36 | 3.79 | -0.14 | 3.79 | 92.14 | 96 | 12116.1 | 751997.89 | 2701307.66 | 29.8833 | -96.7869 | 62.35
13325 | 87.22 | 130.95 | 12391.89 | 888.99 | 1885.12 | 769.02 | 3.47 | 0.23 | 3.46 | 86.25 | 95 | 12120.89 | 751937.8 | 2701381.07 | 29.8831 | -96.7866 | 64.75
13420 | 86.38 | 130.88 | 12397.19 | 826.87 | 1956.79 | 863.8 | 0.89 | -0.88 | -0.07 | -175.25 | 95 | 12126.19 | 751875.68 | 2701452.74 | 29.883 | -96.7864 | 67.09
13514 | 85.25 | 131.43 | 12404.05 | 765.17 | 2027.38 | 957.5 | 1.34 | -1.2 | 0.59 | 154.13 | 94 | 12133.05 | 751813.98 | 2701523.33 | 29.8828 | -96.7862 | 69.32
13609 | 86.44 | 133.03 | 12410.93 | 701.49 | 2097.53 | 1052.23 | 2.1 | 1.25 | 1.68 | 53.35 | 95 | 12139.93 | 751750.3 | 2701593.48 | 29.8826 | -96.786 | 71.51
13706 | 90.4 | 133.8 | 12413.61 | 634.86 | 2167.95 | 1149.17 | 4.16 | 4.08 | 0.79 | 11.01 | 97 | 12142.61 | 751683.67 | 2701663.9 | 29.8824 | -96.7858 | 73.68
13800 | 90.26 | 134.06 | 12413.07 | 569.65 | 2235.65 | 1243.16 | 0.31 | -0.15 | 0.28 | 118.3 | 94 | 12142.07 | 751618.46 | 2701731.6 | 29.8822 | -96.7855 | 75.71
13894 | 88.68 | 133.99 | 12413.94 | 504.33 | 2303.23 | 1337.14 | 1.68 | -1.68 | -0.07 | -177.46 | 94 | 12142.94 | 751553.14 | 2701799.18 | 29.8821 | -96.7853 | 77.65
13989 | 85.74 | 134.64 | 12418.56 | 438.05 | 2371.12 | 1432 | 3.17 | -3.09 | 0.68 | 167.56 | 95 | 12147.56 | 751486.86 | 2701867.07 | 29.8819 | -96.7851 | 79.53
14083 | 84.65 | 134.92 | 12426.43 | 372.07 | 2437.61 | 1525.62 | 1.2 | -1.16 | 0.3 | 165.65 | 94 | 12155.43 | 751420.88 | 2701933.56 | 29.8817 | -96.7849 | 81.32
14178 | 85.24 | 134.8 | 12434.8 | 305.32 | 2504.68 | 1620.21 | 0.63 | 0.62 | -0.13 | -11.46 | 95 | 12163.8 | 751354.13 | 2702000.63 | 29.8815 | -96.7847 | 83.05
14272 | 85.73 | 133.44 | 12442.2 | 240.08 | 2571.95 | 1713.9 | 1.53 | 0.52 | -1.45 | -70.18 | 94 | 12171.2 | 751288.89 | 2702067.9 | 29.8813 | -96.7845 | 84.67
14367 | 87.06 | 133.46 | 12448.18 | 174.88 | 2640.78 | 1808.71 | 1.4 | 1.4 | 0.02 | 0.86 | 95 | 12177.18 | 751223.69 | 2702136.73 | 29.8811 | -96.7843 | 86.21
14461 | 88.35 | 134.71 | 12451.94 | 109.54 | 2708.25 | 1902.61 | 1.91 | 1.37 | 1.33 | 44.1 | 94 | 12180.94 | 751158.35 | 2702204.2 | 29.881 | -96.7841 | 87.68
14557 | 89.12 | 135.54 | 12454.06 | 41.53 | 2775.96 | 1998.53 | 1.18 | 0.8 | 0.86 | 47.15 | 96 | 12183.06 | 751090.34 | 2702271.91 | 29.8808 | -96.7839 | 89.14
14652 | 88.14 | 132.32 | 12456.33 | -24.36 | 2844.35 | 2093.48 | 3.54 | -1.03 | -3.39 | -106.97 | 95 | 12185.33 | 751024.45 | 2702340.3 | 29.8806 | -96.7837 | 90.49
14748 | 87.6 | 131.36 | 12459.9 | -88.35 | 2915.82 | 2189.39 | 1.15 | -0.56 | -1 | -119.39 | 96 | 12188.9 | 750960.46 | 2702411.77 | 29.8804 | -96.7834 | 91.74
14843 | 87.37 | 130.9 | 12464.07 | -150.78 | 2987.31 | 2284.24 | 0.54 | -0.24 | -0.48 | -116.6 | 95 | 12193.07 | 750898.03 | 2702483.26 | 29.8802 | -96.7832 | 92.89
14937 | 87.67 | 131.3 | 12468.14 | -212.51 | 3058.08 | 2378.09 | 0.53 | 0.32 | 0.43 | 53.11 | 94 | 12197.14 | 750836.3 | 2702554.03 | 29.8801 | -96.783 | 93.98
15032 | 88.19 | 131.07 | 12471.57 | -275.03 | 3129.52 | 2472.98 | 0.6 | 0.55 | -0.24 | -23.85 | 95 | 12200.57 | 750773.78 | 2702625.47 | 29.8799 | -96.7828 | 95.02
15127 | 88.63 | 131.12 | 12474.2 | -337.45 | 3201.09 | 2567.88 | 0.47 | 0.46 | 0.05 | 6.48 | 95 | 12203.2 | 750711.36 | 2702697.04 | 29.8797 | -96.7826 | 96.02
15222 | 87.72 | 132.21 | 12477.23 | -400.57 | 3272.02 | 2662.8 | 1.49 | -0.96 | 1.15 | 129.89 | 95 | 12206.23 | 750648.24 | 2702767.97 | 29.8795 | -96.7823 | 96.98
15316 | 87.96 | 133.49 | 12480.77 | -464.45 | 3340.89 | 2756.73 | 1.38 | 0.26 | 1.36 | 79.4 | 94 | 12209.77 | 750584.36 | 2702836.84 | 29.8793 | -96.7821 | 97.91
15412 | 87.52 | 134.51 | 12484.56 | -531.08 | 3409.89 | 2852.65 | 1.16 | -0.46 | 1.06 | 113.37 | 96 | 12213.56 | 750517.73 | 2702905.84 | 29.8792 | -96.7819 | 98.85
15505 | 88.85 | 135.05 | 12487.5 | -596.56 | 3475.87 | 2945.56 | 1.54 | 1.43 | 0.58 | 22.1 | 93 | 12216.5 | 750452.25 | 2702971.82 | 29.879 | -96.7817 | 99.74
15600 | 87.8 | 132.98 | 12490.28 | -662.53 | 3544.15 | 3040.5 | 2.44 | -1.11 | -2.18 | -116.93 | 95 | 12219.28 | 750386.28 | 2703040.1 | 29.8788 | -96.7815 | 100.59
15695 | 88.07 | 134.33 | 12493.7 | -728.07 | 3612.84 | 3135.43 | 1.45 | 0.28 | 1.42 | 78.71 | 95 | 12222.7 | 750320.74 | 2703108.79 | 29.8786 | -96.7813 | 101.39
15791 | 86.73 | 133.62 | 12498.06 | -794.66 | 3681.85 | 3231.32 | 1.58 | -1.4 | -0.74 | -152.12 | 96 | 12227.06 | 750254.15 | 2703177.8 | 29.8784 | -96.7811 | 102.18
15885 | 85.88 | 133.81 | 12504.12 | -859.48 | 3749.65 | 3325.12 | 0.93 | -0.9 | 0.2 | 167.43 | 94 | 12233.12 | 750189.33 | 2703245.6 | 29.8782 | -96.7809 | 102.91
15981 | 84.63 | 134.09 | 12512.06 | -925.88 | 3818.53 | 3420.77 | 1.33 | -1.3 | 0.29 | 167.43 | 96 | 12241.06 | 750122.93 | 2703314.48 | 29.8781 | -96.7806 | 103.63
16076 | 84.72 | 133.02 | 12520.88 | -991.05 | 3887.08 | 3515.36 | 1.13 | 0.09 | -1.13 | -85.22 | 95 | 12249.88 | 750057.76 | 2703383.03 | 29.8779 | -96.7804 | 104.3
16170 | 86.44 | 132.04 | 12528.12 | -1054.4 | 3956.14 | 3609.07 | 2.1 | 1.83 | -1.04 | -29.64 | 94 | 12257.12 | 749994.41 | 2703452.09 | 29.8777 | -96.7802 | 104.92
16265 | 92.79 | 131.93 | 12528.76 | -1117.92 | 4026.72 | 3704 | 6.69 | 6.68 | -0.12 | -0.99 | 95 | 12257.76 | 749930.89 | 2703522.67 | 29.8775 | -96.78 | 105.52
16359 | 90.57 | 130.69 | 12526 | -1179.94 | 4097.29 | 3797.91 | 2.7 | -2.36 | -1.32 | -150.8 | 94 | 12255 | 749868.87 | 2703593.24 | 29.8773 | -96.7798 | 106.07
16453 | 90.41 | 130.99 | 12525.2 | -1241.41 | 4168.4 | 3891.83 | 0.36 | -0.17 | 0.32 | 118.07 | 94 | 12254.2 | 749807.4 | 2703664.35 | 29.8772 | -96.7796 | 106.58
16549 | 91.04 | 131.14 | 12523.98 | -1304.47 | 4240.78 | 3987.76 | 0.67 | 0.66 | 0.16 | 13.39 | 96 | 12252.98 | 749744.34 | 2703736.73 | 29.877 | -96.7793 | 107.1
16646 | 92.26 | 131.13 | 12521.19 | -1368.25 | 4313.8 | 4084.66 | 1.26 | 1.26 | -0.01 | -0.47 | 97 | 12250.19 | 749680.56 | 2703809.75 | 29.8768 | -96.7791 | 107.6
16740 | 89.81 | 131.15 | 12519.49 | -1430.08 | 4384.58 | 4178.59 | 2.61 | -2.61 | 0.02 | 179.53 | 94 | 12248.49 | 749618.73 | 2703880.53 | 29.8766 | -96.7789 | 108.06
16835 | 88.61 | 131.19 | 12520.8 | -1492.61 | 4456.08 | 4273.52 | 1.26 | -1.26 | 0.04 | 178.09 | 95 | 12249.8 | 749556.2 | 2703952.03 | 29.8765 | -96.7787 | 108.52
16930 | 87.37 | 131.55 | 12524.13 | -1555.35 | 4527.33 | 4368.42 | 1.36 | -1.31 | 0.38 | 163.83 | 95 | 12253.13 | 749493.46 | 2704023.28 | 29.8763 | -96.7784 | 108.96
17025 | 88.69 | 132.78 | 12527.4 | -1619.08 | 4597.7 | 4463.34 | 1.9 | 1.39 | 1.29 | 42.98 | 95 | 12256.4 | 749429.73 | 2704093.65 | 29.8761 | -96.7782 | 109.4
17119 | 89.65 | 133.47 | 12528.76 | -1683.33 | 4666.3 | 4557.33 | 1.26 | 1.02 | 0.73 | 35.71 | 94 | 12257.76 | 749365.48 | 2704162.25 | 29.8759 | -96.778 | 109.84
17213 | 90.9 | 134.33 | 12528.31 | -1748.51 | 4734.03 | 4651.32 | 1.61 | 1.33 | 0.91 | 34.53 | 94 | 12257.31 | 749300.3 | 2704229.98 | 29.8757 | -96.7778 | 110.27
17308 | 90.79 | 135.3 | 12526.91 | -1815.46 | 4801.41 | 4746.27 | 1.03 | -0.12 | 1.02 | 96.46 | 95 | 12255.91 | 749233.35 | 2704297.36 | 29.8756 | -96.7776 | 110.71
17403 | 92.79 | 134.26 | 12523.94 | -1882.34 | 4868.81 | 4841.17 | 2.37 | 2.11 | -1.09 | -27.45 | 95 | 12252.94 | 749166.47 | 2704364.76 | 29.8754 | -96.7774 | 111.14
17499 | 94.61 | 133.69 | 12517.75 | -1948.86 | 4937.74 | 4936.96 | 1.99 | 1.9 | -0.59 | -17.34 | 96 | 12246.75 | 749099.95 | 2704433.69 | 29.8752 | -96.7772 | 111.54
17593 | 92.17 | 133.53 | 12512.19 | -2013.57 | 5005.68 | 5030.78 | 2.6 | -2.6 | -0.17 | -176.25 | 94 | 12241.19 | 749035.24 | 2704501.63 | 29.875 | -96.777 | 111.91
17688 | 88.68 | 132.84 | 12511.48 | -2078.58 | 5074.94 | 5125.76 | 3.74 | -3.67 | -0.73 | -168.81 | 95 | 12240.48 | 748970.23 | 2704570.89 | 29.8748 | -96.7767 | 112.27
17782 | 86.34 | 133.15 | 12515.57 | -2142.61 | 5143.62 | 5219.67 | 2.51 | -2.49 | 0.33 | 172.47 | 94 | 12244.57 | 748906.2 | 2704639.57 | 29.8746 | -96.7765 | 112.61
17877 | 85.72 | 133.38 | 12522.15 | -2207.57 | 5212.63 | 5314.44 | 0.7 | -0.65 | 0.24 | 159.7 | 95 | 12251.15 | 748841.24 | 2704708.58 | 29.8745 | -96.7763 | 112.95
17973 | 87.19 | 134.18 | 12528.08 | -2273.86 | 5281.81 | 5410.25 | 1.74 | 1.53 | 0.83 | 28.54 | 96 | 12257.08 | 748774.95 | 2704777.76 | 29.8743 | -96.7761 | 113.29
18067 | 90.64 | 133.11 | 12529.86 | -2338.71 | 5349.81 | 5504.21 | 3.84 | 3.67 | -1.14 | -17.24 | 94 | 12258.86 | 748710.1 | 2704845.76 | 29.8741 | -96.7759 | 113.61
18163 | 89.03 | 133.27 | 12530.14 | -2404.42 | 5419.8 | 5600.2 | 1.69 | -1.68 | 0.17 | 174.32 | 96 | 12259.14 | 748644.39 | 2704915.75 | 29.8739 | -96.7757 | 113.92
18257 | 87.36 | 133.94 | 12533.1 | -2469.21 | 5487.83 | 5694.15 | 1.91 | -1.78 | 0.71 | 158.16 | 94 | 12262.1 | 748579.6 | 2704983.78 | 29.8737 | -96.7755 | 114.23
18352 | 86.04 | 133.98 | 12538.57 | -2535.04 | 5556.09 | 5788.98 | 1.39 | -1.39 | 0.04 | 178.27 | 95 | 12267.57 | 748513.77 | 2705052.04 | 29.8735 | -96.7753 | 114.53
18446 | 87.49 | 133.59 | 12543.87 | -2599.98 | 5623.85 | 5882.82 | 1.6 | 1.54 | -0.41 | -15.04 | 94 | 12272.87 | 748448.83 | 2705119.8 | 29.8734 | -96.775 | 114.81
18527 | 89.37 | 132.76 | 12546.09 | -2655.38 | 5682.89 | 5963.79 | 2.54 | 2.32 | -1.02 | -23.83 | 81 | 12275.09 | 748393.43 | 2705178.84 | 29.8732 | -96.7749 | 115.04
18621 | 89.8 | 133.12 | 12546.77 | -2719.42 | 5751.71 | 6057.78 | 0.6 | 0.46 | 0.38 | 39.94 | 94 | 12275.77 | 748329.39 | 2705247.66 | 29.873 | -96.7747 | 115.3
18715 | 90.38 | 132.96 | 12546.62 | -2783.57 | 5820.41 | 6151.78 | 0.64 | 0.62 | -0.17 | -15.42 | 94 | 12275.62 | 748265.24 | 2705316.36 | 29.8728 | -96.7744 | 115.56
18810 | 86.1 | 131.55 | 12549.54 | -2847.41 | 5890.67 | 6246.7 | 4.74 | -4.51 | -1.48 | -161.79 | 95 | 12278.54 | 748201.4 | 2705386.62 | 29.8727 | -96.7742 | 115.8
18905 | 87.21 | 131.75 | 12555.08 | -2910.43 | 5961.53 | 6341.51 | 1.19 | 1.17 | 0.21 | 10.2 | 95 | 12284.08 | 748138.38 | 2705457.48 | 29.8725 | -96.774 | 116.02
18998 | 83.66 | 130.46 | 12562.48 | -2971.37 | 6031.37 | 6434.14 | 4.06 | -3.82 | -1.39 | -160.14 | 93 | 12291.48 | 748077.44 | 2705527.32 | 29.8723 | -96.7738 | 116.23
19092 | 83.5 | 130.59 | 12573 | -3032.07 | 6102.38 | 6527.46 | 0.22 | -0.17 | 0.14 | 141.09 | 94 | 12302 | 748016.74 | 2705598.33 | 29.8721 | -96.7736 | 116.42
19187 | 86.49 | 132.3 | 12581.28 | -3094.7 | 6173.3 | 6622.04 | 3.62 | 3.15 | 1.8 | 29.75 | 95 | 12310.28 | 747954.11 | 2705669.25 | 29.872 | -96.7733 | 116.62
19283 | 87.3 | 132.87 | 12586.48 | -3159.57 | 6243.88 | 6717.9 | 1.03 | 0.84 | 0.59 | 35.11 | 96 | 12315.48 | 747889.24 | 2705739.83 | 29.8718 | -96.7731 | 116.84
19377 | 85.53 | 133.9 | 12592.36 | -3224 | 6312.06 | 6811.71 | 2.18 | -1.88 | 1.1 | 149.88 | 94 | 12321.36 | 747824.81 | 2705808.01 | 29.8716 | -96.7729 | 117.06
19470 | 85.11 | 134.22 | 12599.95 | -3288.46 | 6378.67 | 6904.38 | 0.57 | -0.45 | 0.34 | 142.8 | 93 | 12328.95 | 747760.35 | 2705874.62 | 29.8714 | -96.7727 | 117.27
19565 | 83.74 | 133.83 | 12609.18 | -3354.17 | 6446.65 | 6998.92 | 1.5 | -1.44 | -0.41 | -164.2 | 95 | 12338.18 | 747694.64 | 2705942.6 | 29.8712 | -96.7725 | 117.49
19658 | 83.2 | 133.37 | 12619.75 | -3417.89 | 6513.56 | 7091.31 | 0.76 | -0.58 | -0.49 | -139.78 | 93 | 12348.75 | 747630.92 | 2706009.51 | 29.8711 | -96.7723 | 117.69
19753 | 82.85 | 132.58 | 12631.29 | -3482.17 | 6582.55 | 7185.61 | 0.9 | -0.37 | -0.83 | -114.1 | 95 | 12360.29 | 747566.64 | 2706078.5 | 29.8709 | -96.7721 | 117.88
19848 | 84.72 | 134.06 | 12641.58 | -3546.96 | 6651.26 | 7280.04 | 2.5 | 1.97 | 1.56 | 38.28 | 95 | 12370.58 | 747501.85 | 2706147.21 | 29.8707 | -96.7719 | 118.07
19942 | 85.65 | 133.97 | 12649.47 | -3612.04 | 6718.62 | 7373.7 | 0.99 | 0.99 | -0.1 | -5.51 | 94 | 12378.47 | 747436.77 | 2706214.57 | 29.8705 | -96.7717 | 118.26
20036 | 85.82 | 133.78 | 12656.46 | -3677.01 | 6786.19 | 7467.43 | 0.27 | 0.18 | -0.2 | -48.11 | 94 | 12385.46 | 747371.8 | 2706282.14 | 29.8703 | -96.7714 | 118.45
20129 | 85.09 | 133.06 | 12663.83 | -3740.73 | 6853.53 | 7560.13 | 1.1 | -0.78 | -0.77 | -135.51 | 93 | 12392.83 | 747308.08 | 2706349.48 | 29.8702 | -96.7712 | 118.63
20224 | 84.57 | 132.87 | 12672.39 | -3805.22 | 6922.76 | 7654.74 | 0.58 | -0.55 | -0.2 | -160.01 | 95 | 12401.39 | 747243.59 | 2706418.71 | 29.87 | -96.771 | 118.8
20318 | 86.03 | 134.6 | 12680.09 | -3869.98 | 6990.45 | 7748.42 | 2.4 | 1.55 | 1.84 | 49.82 | 94 | 12409.09 | 747178.83 | 2706486.4 | 29.8698 | -96.7708 | 118.97
20412 | 86.29 | 133.16 | 12686.38 | -3934.99 | 7058.05 | 7842.19 | 1.55 | 0.28 | -1.53 | -79.79 | 94 | 12415.38 | 747113.82 | 2706554 | 29.8696 | -96.7706 | 119.14
20507 | 86.69 | 132.99 | 12692.2 | -3999.75 | 7127.31 | 7937.02 | 0.46 | 0.42 | -0.18 | -22.99 | 95 | 12421.2 | 747049.06 | 2706623.26 | 29.8694 | -96.7704 | 119.3
20591 | 86.67 | 131.26 | 12697.07 | -4055.99 | 7189.5 | 8020.86 | 2.06 | -0.02 | -2.06 | -90.71 | 84 | 12426.07 | 746992.82 | 2706685.45 | 29.8693 | -96.7702 | 119.43

## 5_12_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/12/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19130 |  |  | Well Cost($): |  | 19130
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: |  | PV:
End Depth (Usft): |  | 2697 |  | 2697 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 2589 |  | 2589 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 318 |  | 318 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2271 |  | 2271 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.17 / 3.33 |  | 4.17 / 3.33 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: |  | 1.25 |  | 1.25 |  | SN: |  | 47245 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 2.92 |  | 2.92 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): |  | 778.63 / 254.40 |  | 778.63 / 254.40 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 7.5 |  | 7.5 |  | Grade In:
% Slide: |  | 12.28 |  | 12.28 |  | Grade Out:
% Rotary: |  | 87.72 |  | 87.72 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7.75" 7/8 5.9 1.5F 13" NBS -.022 |  |  |  | 7.938 | [5 empty] | 37.52 |  | 39.02
Nortrak Stabilizer 13" |  |  |  | 8 | 3.25 |  |  |  |  | 6.74 |  | 45.76
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 55.86
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 58.41
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 87.54
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 116.74
Crossover Sub |  |  |  | 6.75 | 2.812 |  |  |  |  | 3.6 |  | 120.34
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 397.46
397.46
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800075 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 0 |  | 1.5 |  | 0 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
143 | 0.2 | 227.43 | 143 | -0.17 | -0.18 | 0.14 |  | 227.43 | -0.02 | 0.14 |  | 0 | 143
235 | 0.39 | 273.36 | 235 | -0.26 | -0.61 | 0.31 |  | 75.73 | -0.27 | 0.21 |  | 0 | 92
328 | 0.48 | 275.81 | 328 | -0.2 | -1.32 | 0.1 |  | 12.9 | -0.83 | 0.1 |  | 0 | 93
418 | 0.45 | 282.42 | 417.99 | -0.09 | -2.04 | 0.07 |  | 122.49 | -1.43 | -0.03 |  | 0 | 90
513 | 0.63 | 3.54 | 512.99 | 0.51 | -2.37 | 0.75 |  | 119.54 | -2.08 | 0.19 |  | 0 | 95
606 | 1.68 | 43.79 | 605.97 | 2.01 | -1.4 | 1.36 |  | 59 | -2.39 | 1.13 |  | 0 | 93
700 | 3.38 | 40.99 | 699.88 | 5.1 | 1.38 | 1.81 |  | -5.56 | -2.48 | 1.81 |  | -2.98 | 94
795 | 5.02 | 40.89 | 794.62 | 10.35 | 5.93 | 1.73 |  | -0.31 | -2.74 | 1.73 |  | -0.11 | 95
889 | 6.73 | 50.86 | 888.12 | 16.94 | 12.9 | 2.11 |  | 35.85 | -2.16 | 1.82 |  | 10.61 | 94
982 | 7.7 | 50.33 | 980.39 | 24.36 | 21.92 | 1.05 |  | -4.19 | -0.64 | 1.04 |  | -0.57 | 93
1077 | 8.65 | 47.68 | 1074.42 | 33.23 | 32.1 | 1.08 |  | -22.95 | 0.74 | 1 |  | -2.79 | 95
1171 | 9.37 | 42.54 | 1167.26 | 43.63 | 42.5 | 1.15 |  | -50.75 | 1.23 | 0.77 |  | -5.47 | 94
1265 | 9.89 | 30.96 | 1259.94 | 56.19 | 51.83 | 2.13 |  | -80.73 | -0.55 | 0.55 |  | -12.32 | 94
1359 | 9.57 | 27.18 | 1352.59 | 70.06 | 59.55 | 0.76 |  | -118.46 | -4.39 | -0.34 |  | -4.02 | 94
1452 | 9.19 | 25.88 | 1444.35 | 83.62 | 66.33 | 0.47 |  | -151.5 | -8.71 | -0.41 |  | -1.4 | 93
1546 | 8.92 | 32.21 | 1537.18 | 96.54 | 73.49 | 1.1 |  | 108.28 | -12.31 | -0.29 |  | 6.73 | 94
1641 | 9.05 | 32.84 | 1631.01 | 109.05 | 81.46 | 0.17 |  | 37.43 | -15.03 | 0.14 |  | 0.66 | 95
1736 | 10.79 | 36.53 | 1724.59 | 122.47 | 90.81 | 1.95 |  | 21.89 | -17.38 | 1.83 |  | 3.88 | 95
1829 | 12.03 | 36.81 | 1815.75 | 137.23 | 101.8 | 1.33 |  | 2.7 | -19.43 | 1.33 |  | 0.3 | 93
1923 | 14.21 | 38.66 | 1907.29 | 154.08 | 114.88 | 2.36 |  | 11.81 | -21.4 | 2.32 |  | 1.97 | 94
2017 | 15.1 | 38.84 | 1998.23 | 172.63 | 129.76 | 0.95 |  | 3.02 | -23.2 | 0.95 |  | 0.19 | 94
2111 | 14.94 | 38.85 | 2089.02 | 191.6 | 145.04 | 0.17 |  | 179.08 | -25.01 | -0.17 |  | 0.01 | 94
2205 | 14.56 | 39.02 | 2179.92 | 210.22 | 160.08 | 0.41 |  | 173.58 | -26.75 | -0.4 |  | 0.18 | 94
2299 | 14.11 | 39.45 | 2271 | 228.25 | 174.8 | 0.49 |  | 166.9 | -28.32 | -0.48 |  | 0.46 | 94
2393 | 13.88 | 39.8 | 2362.21 | 245.76 | 189.3 | 0.26 |  | 159.97 | -29.7 | -0.24 |  | 0.37 | 94
2487 | 12.78 | 38.74 | 2453.67 | 262.53 | 203.02 | 1.2 |  | -167.99 | -31.14 | -1.17 |  | -1.13 | 94
2581 | 13.38 | 36.99 | 2545.23 | 279.32 | 216.07 | 0.76 |  | -34.28 | -33.09 | 0.64 |  | -1.86 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 621.36 | 10 | 60 | 60 | 854.66 | 1553.66 | 1084.15 | 0 | 85 | 80 | 75 | 2000 | 0
Run | 621.36 | 10 | 60 | 60 | 854.66 | 1553.66 | 1084.15 | 0 | 85 | 80 | 75 | 2000 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/12/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/12/2021 |  | 5 |  | 100 |  | 4 | 400
8 Motor Reline |  |  |  |  | 05/12/2021 |  | 6 |  | 10500 |  | 1 | 10500
13 Stab Rental (Used) |  |  |  |  | 05/12/2021 |  | 7 |  | 1150 |  | 1 | 1150
13 Stab Rental (Not Used) |  |  |  |  | 05/12/2021 |  | 8 |  | 230 |  | 1 | 230
Total | [11 empty] | 19130
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/12/2021 | 00:00 | 14:00 | 14 | 108 | 108 | 0 | SUR |  | 24B | Wait On Rig
05/12/2021 | 14:00 | 16:30 | 2.5 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | P/U BHA #1, Scribe / Test
05/12/2021 | 16:30 | 17:45 | 1.25 | 108 | 108 | 0 | SUR | 1: BHA 1 | 5A | Drill Shoe Track
05/12/2021 | 17:45 | 18:00 | 0.25 | 108 | 215 | 107 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/215.00, w/WOB 10.00,Flow 487.00, RPM 60.00, Press 300.00, Tq 2000.00, ROP 428.00, Diff -350.00
05/12/2021 | 18:00 | 18:05 | 0.08 | 215 | 215 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 18:05 | 18:15 | 0.17 | 215 | 307 | 92 | SUR | 1: BHA 1 | 2K | Rotary Drill f/215.00 t/307.00, w/WOB 10.00,Flow 747.00, RPM 60.00, Press 1300.00, Tq 2000.00, ROP 552.00, Diff 300.00
05/12/2021 | 18:15 | 18:20 | 0.08 | 307 | 307 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 18:20 | 18:35 | 0.25 | 307 | 400 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/307.00 t/400.00, w/WOB 10.00,Flow 747.00, RPM 60.00, Press 1300.00, Tq 2000.00, ROP 372.00, Diff 300.00
05/12/2021 | 18:35 | 18:40 | 0.08 | 400 | 400 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 18:40 | 18:50 | 0.17 | 400 | 493 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/400.00 t/493.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 558.00, Diff 500.00
05/12/2021 | 18:50 | 18:55 | 0.08 | 493 | 493 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 18:55 | 19:00 | 0.08 | 493 | 518 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/493.00 t/518.00, TF 35.00M, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 300.00, Diff 500.00
05/12/2021 | 19:00 | 19:10 | 0.17 | 518 | 583 | 65 | SUR | 1: BHA 1 | 2K | Rotary Drill f/518.00 t/583.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 390.00, Diff 500.00
05/12/2021 | 19:10 | 19:15 | 0.08 | 583 | 583 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 19:15 | 19:20 | 0.08 | 583 | 608 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/583.00 t/608.00, TF 35.00M, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 300.00, Diff 500.00
05/12/2021 | 19:20 | 19:25 | 0.08 | 608 | 686 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/608.00 t/686.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 936.00, Diff 500.00
05/12/2021 | 19:25 | 19:30 | 0.08 | 686 | 686 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 19:30 | 19:35 | 0.08 | 686 | 711 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/686.00 t/711.00, TF 35M, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 300.00, Diff 500.00
05/12/2021 | 19:35 | 19:40 | 0.08 | 711 | 780 | 69 | SUR | 1: BHA 1 | 2K | Rotary Drill f/711.00 t/780.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 828.00, Diff 500.00
05/12/2021 | 19:40 | 19:45 | 0.08 | 780 | 780 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 19:45 | 19:50 | 0.08 | 780 | 800 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/780.00 t/800.00, TF 0G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 19:50 | 19:55 | 0.08 | 800 | 875 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/800.00 t/875.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 900.00, Diff 500.00
05/12/2021 | 19:55 | 20:00 | 0.08 | 875 | 875 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 20:00 | 20:05 | 0.08 | 875 | 895 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/875.00 t/895.00, TF -10G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 20:05 | 20:10 | 0.08 | 895 | 972 | 77 | SUR | 1: BHA 1 | 2K | Rotary Drill f/895.00 t/972.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 924.00, Diff 500.00
05/12/2021 | 20:10 | 20:15 | 0.08 | 972 | 972 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 20:15 | 20:20 | 0.08 | 972 | 992 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/972.00 t/992.00, TF -45G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 20:20 | 20:25 | 0.08 | 992 | 1068 | 76 | SUR | 1: BHA 1 | 2K | Rotary Drill f/992.00 t/1068.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 912.00, Diff 500.00
05/12/2021 | 20:25 | 20:30 | 0.08 | 1068 | 1068 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 20:30 | 20:35 | 0.08 | 1068 | 1088 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1068.00 t/1088.00, TF -90G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 20:35 | 20:40 | 0.08 | 1088 | 1158 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1088.00 t/1158.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 840.00, Diff 500.00
05/12/2021 | 20:40 | 20:45 | 0.08 | 1158 | 1158 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 20:45 | 20:50 | 0.08 | 1158 | 1178 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1158.00 t/1178.00, TF -90G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 20:50 | 20:55 | 0.08 | 1178 | 1256 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1178.00 t/1256.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 936.00, Diff 500.00
05/12/2021 | 20:55 | 21:00 | 0.08 | 1256 | 1256 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 21:00 | 21:05 | 0.08 | 1256 | 1276 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1256.00 t/1276.00, TF -90G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 21:05 | 21:10 | 0.08 | 1276 | 1433 | 157 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1276.00 t/1433.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1884.00, Diff 500.00
05/12/2021 | 21:10 | 21:15 | 0.08 | 1433 | 1433 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 21:15 | 21:20 | 0.08 | 1433 | 1527 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1433.00 t/1527.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1128.00, Diff 500.00
05/12/2021 | 21:20 | 21:25 | 0.08 | 1527 | 1527 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 21:25 | 21:30 | 0.08 | 1527 | 1550 | 23 | SUR | 1: BHA 1 | 2J | Slide Drill f/1527.00 t/1550.00, TF 60G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 276.00, Diff 500.00
05/12/2021 | 21:30 | 21:35 | 0.08 | 1550 | 1634 | 84 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1550.00 t/1634.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1008.00, Diff 500.00
05/12/2021 | 21:35 | 21:40 | 0.08 | 1634 | 1634 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 21:40 | 21:45 | 0.08 | 1634 | 1654 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1634.00 t/1654.00, TF 0G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 21:45 | 21:50 | 0.08 | 1654 | 1725 | 71 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1654.00 t/1725.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 852.00, Diff 500.00
05/12/2021 | 21:50 | 21:55 | 0.08 | 1725 | 1725 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 21:55 | 22:00 | 0.08 | 1725 | 1745 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1725.00 t/1745.00, TF 0G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 22:00 | 22:05 | 0.08 | 1745 | 1852 | 107 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1745.00 t/1852.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1284.00, Diff 500.00
05/12/2021 | 22:05 | 22:10 | 0.08 | 1852 | 1852 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 22:10 | 22:15 | 0.08 | 1852 | 1872 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1852.00 t/1872.00, TF 0G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 22:15 | 22:20 | 0.08 | 1872 | 1915 | 43 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1872.00 t/1915.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 516.00, Diff 500.00
05/12/2021 | 22:20 | 22:25 | 0.08 | 1915 | 1915 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 22:25 | 22:30 | 0.08 | 1915 | 1935 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1915.00 t/1935.00, TF 0G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 22:30 | 22:35 | 0.08 | 1935 | 1997 | 62 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1935.00 t/1997.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 744.00, Diff 500.00
05/12/2021 | 22:35 | 22:40 | 0.08 | 1997 | 1997 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 22:40 | 22:45 | 0.08 | 1997 | 2091 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1997.00 t/2091.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1128.00, Diff 500.00
05/12/2021 | 22:45 | 22:50 | 0.08 | 2091 | 2091 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 22:50 | 22:55 | 0.08 | 2091 | 2185 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2091.00 t/2185.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1128.00, Diff 500.00
05/12/2021 | 22:55 | 23:00 | 0.08 | 2185 | 2185 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 23:00 | 23:05 | 0.08 | 2185 | 2279 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2185.00 t/2279.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1128.00, Diff 500.00
05/12/2021 | 23:05 | 23:10 | 0.08 | 2279 | 2279 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 23:10 | 23:15 | 0.08 | 2279 | 2373 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2279.00 t/2373.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1128.00, Diff 500.00
05/12/2021 | 23:15 | 23:20 | 0.08 | 2373 | 2373 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 23:20 | 23:25 | 0.08 | 2373 | 2480 | 107 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2373.00 t/2480.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1284.00, Diff 500.00
05/12/2021 | 23:25 | 23:30 | 0.08 | 2480 | 2480 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 23:30 | 23:35 | 0.08 | 2480 | 2500 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2480.00 t/2500.00, TF -135G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/12/2021 | 23:35 | 23:40 | 0.08 | 2500 | 2561 | 61 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2500.00 t/2561.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 732.00, Diff 500.00
05/12/2021 | 23:40 | 23:45 | 0.08 | 2561 | 2561 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/12/2021 | 23:45 | 24:00 | 0.25 | 2561 | 2697 | 136 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2561.00 t/2697.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 544.00, Diff 500.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_13_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/13/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 26380
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2697 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: |  | PV:
End Depth (Usft): |  | 3033 |  | 3033 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 336 |  | 2925 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 35 |  | 353 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 301 |  | 2572 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 0.92 / 1.67 |  | 5.08 / 5.00 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: |  | 0.17 |  | 1.42 |  | SN: |  | 47245 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 0.75 |  | 3.67 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): |  | 401.33 / 210.00 |  | 701.45 / 249.18 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 4.75 |  | 12.25 |  | Grade In:
% Slide: |  | 10.42 |  | 12.07 |  | Grade Out:
% Rotary: |  | 89.58 |  | 87.93 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7.75" 7/8 5.9 1.5F 13" NBS -.022 |  |  |  | 7.938 | [5 empty] | 37.52 |  | 39.02
Nortrak Stabilizer 13" |  |  |  | 8 | 3.25 |  |  |  |  | 6.74 |  | 45.76
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 55.86
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 58.41
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 87.54
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 116.74
Crossover Sub |  |  |  | 6.75 | 2.812 |  |  |  |  | 3.6 |  | 120.34
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 397.46
397.46
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800075 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 0 |  | 1.5 |  | 0 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2675 | 13.39 | 36.82 | 2636.68 | 296.73 | 229.14 | 0.04 |  | -75.83 | -35.43 | 0.01 |  | -0.18 | 94
2769 | 10.41 | 24.56 | 2728.67 | 313.17 | 239.2 | 4.14 |  | -145.58 | -39.33 | -3.17 |  | -13.04 | 94
2863 | 9.18 | 18.87 | 2821.3 | 327.99 | 245.15 | 1.66 |  | -144.58 | -45.1 | -1.31 |  | -6.05 | 94
2956 | 8.52 | 16.96 | 2913.19 | 341.6 | 249.56 | 0.78 |  | -156.94 | -51.18 | -0.71 |  | -2.05 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 366.55 | 10 | 60 | 60 | 870 | 1600 | 1100 | 0 | 85 | 80 | 75 | 2000 | 0
Run | 575.41 | 10 | 60 | 60 | 856.9 | 1560.42 | 1086.46 | 0 | 85 | 80 | 75 | 2000 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/13/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/13/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/13/2021 | 00:00 | 00:05 | 0.08 | 2697 | 2717 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2697.00 t/2717.00, TF 180G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 240.00, Diff 500.00
05/13/2021 | 00:05 | 00:20 | 0.25 | 2717 | 2758 | 41 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2717.00 t/2758.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 164.00, Diff 500.00
05/13/2021 | 00:20 | 00:25 | 0.08 | 2758 | 2758 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/13/2021 | 00:25 | 00:30 | 0.08 | 2758 | 2773 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2758.00 t/2773.00, TF -150G, w/WOB 10.00,Flow 870.00, Press 1600.00, Tq 2000.00, ROP 180.00, Diff 500.00
05/13/2021 | 00:30 | 00:40 | 0.17 | 2773 | 2843 | 70 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2773.00 t/2843.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 420.00, Diff 500.00
05/13/2021 | 00:40 | 00:45 | 0.08 | 2843 | 2843 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/13/2021 | 00:45 | 00:50 | 0.08 | 2843 | 2900 | 57 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2843.00 t/2900.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 684.00, Diff 500.00
05/13/2021 | 00:50 | 01:40 | 0.83 | 2900 | 2900 | 0 | SUR | 1: BHA 1 | 5A | Circulate
05/13/2021 | 01:40 | 01:50 | 0.17 | 2900 | 2935 | 35 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2900.00 t/2935.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 210.00, Diff 500.00
05/13/2021 | 01:50 | 01:55 | 0.08 | 2935 | 2935 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/13/2021 | 01:55 | 02:00 | 0.08 | 2935 | 3033 | 98 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2935.00 t/3033.00, w/WOB 10.00,Flow 870.00, RPM 60.00, Press 1600.00, Tq 2000.00, ROP 1176.00, Diff 500.00
05/13/2021 | 02:00 | 02:05 | 0.08 | 3033 | 3033 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
05/13/2021 | 02:05 | 02:35 | 0.5 | 3033 | 3033 | 0 | SUR | 1: BHA 1 | 5A | Circulate
05/13/2021 | 02:35 | 04:00 | 1.42 | 3033 | 3033 | 0 | SUR | 1: BHA 1 | 6B | POOH w/BHA #1
05/13/2021 | 04:00 | 04:45 | 0.75 | 3033 | 3033 | 0 | SUR | 1: BHA 1 | 6P | L/D BHA #1
05/13/2021 | 04:45 | 05:20 | 0.58 | 3033 | 3033 | 0 | SUR |  | 6O | P/U BHA #1
05/13/2021 | 05:20 | 07:00 | 1.67 | 3033 | 3033 | 0 | SUR |  | 6A | TIH
05/13/2021 | 07:00 | 07:30 | 0.5 | 3033 | 3033 | 0 | SUR |  | 5A | Circulate
05/13/2021 | 07:30 | 09:00 | 1.5 | 3033 | 3033 | 0 | SUR |  | 6B | POOH
05/13/2021 | 09:00 | 10:00 | 1 | 3033 | 3033 | 0 | SUR |  | 6B | L/D BHA
05/13/2021 | 10:00 | 24:00 | 14 | 3033 | 3033 | 0 | SUR |  | 24B | Run Casing / Cement / Nipple Up
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_14_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/14/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17750 |  |  | Well Cost($): |  | 44130
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3033 |  | 3033 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: |  | PV:
End Depth (Usft): |  | 3033 |  | 3033 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 0.00 / 1.67 |  | 0.00 / 1.67 |  | Bit Details |  |  |  | 3: |  | Oil/Water:
Slide Drilling Hrs: | [5 empty] | SN: |  | 54682 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 6 |  | 6 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
8 7/8 5.9 2.0F Slick -.016 |  |  |  | 8 | [5 empty] | 37.58 |  | 39.08
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 49.18
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 51.73
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 80.86
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 110.06
Crossover Sub |  |  |  | 6.5 | 2.375 |  |  |  |  | 2.35 |  | 112.41
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 186.82 |  | 299.23
Crossover Sub |  |  |  | 6.438 | 2.375 |  |  |  |  | 2.89 |  | 302.12
3 Stds 5 in HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 579.24
22 Stds 5 in DP |  |  |  | 5 | 2.563 |  |  |  |  | 2067.72 |  | 2646.96
Agitator |  |  |  | 6.812 | [5 empty] | 24.62 |  | 2671.58
2671.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800055 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.98 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 10 | 60 | 204 | 870 | 1600 | 1100 | 0 | 85 | 80 | 75 | 2000 | 0
Run | 0 | 10 | 60 | 202 | 856.9 | 1560.42 | 1086.46 | 0 | 85 | 80 | 75 | 2000 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/14/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/14/2021 |  | 5 |  | 100 |  | 4 | 400
8 Motor Reline |  |  |  |  | 05/14/2021 |  | 6 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17750
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/14/2021 | 00:00 | 16:00 | 16 | 3033 | 3033 | 0 | INT |  | 24B | Nipple Up And Test
05/14/2021 | 16:00 | 18:00 | 2 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 6O | P/U BHA #2 / Scribe / Test MWD
05/14/2021 | 18:00 | 19:00 | 1 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 6J | P/U 6 jts DCs
05/14/2021 | 19:00 | 20:00 | 1 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 6A | TIH to 2646
05/14/2021 | 20:00 | 20:30 | 0.5 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 24A | Fill Pipe / Test Agitator
05/14/2021 | 20:30 | 21:00 | 0.5 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 24A | Install Rot Head
05/14/2021 | 21:00 | 21:30 | 0.5 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 5A | Fill Gasbuster / BOP Drill
05/14/2021 | 21:30 | 22:30 | 1 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 8P | Rig Service
05/14/2021 | 22:30 | 23:40 | 1.17 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 5A | Drill Shoe Track
05/14/2021 | 23:40 | 24:00 | 0.33 | 3033 | 3033 | 0 | INT | 2: BHA 2 | 15D | FIT Test
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_15_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/15/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 51380
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3032 |  | 3033 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 19 | PV: | 6
End Depth (Usft): |  | 7576 |  | 7576 |  | OD (in): |  |  |  | 300: | 13 | YP: | 7
Total Drilled (Usft): |  | 4544 |  | 4544 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): |  | 347 |  | 347 | [5 empty] | 100: | 8 | Chlorides: | 45000
Rotary Drilled (Usft): |  | 4197 |  | 4197 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 6.20
Drlg/Circ Hrs: |  | 16.92 / 4.12 |  | 16.92 / 5.78 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77:23
Slide Drilling Hrs: |  | 7.95 |  | 7.95 |  | SN: |  | 54682 |  | 10s Gel: | 3 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 8.97 |  | 8.97 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 82.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 468.07 / 43.65 |  | 468.07 / 43.65 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 30 |  | Grade In: |  | New
% Slide: |  | 7.64 |  | 7.64 |  | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
% Rotary: |  | 92.36 |  | 92.36 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
8 7/8 5.9 2.0F Slick -.016 |  |  |  | 8 | [5 empty] | 37.58 |  | 39.08
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 49.18
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 51.73
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 80.86
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 110.06
Crossover Sub |  |  |  | 6.5 | 2.375 |  |  |  |  | 2.35 |  | 112.41
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 186.82 |  | 299.23
Crossover Sub |  |  |  | 6.438 | 2.375 |  |  |  |  | 2.89 |  | 302.12
3 Stds 5 in HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 579.24
22 Stds 5 in DP |  |  |  | 5 | 2.563 |  |  |  |  | 2067.72 |  | 2646.96
Agitator |  |  |  | 6.812 | [5 empty] | 24.62 |  | 2671.58
2671.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800055 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.98 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3071 | 7.79 | 14.09 | 3027.02 | 357.31 | 253.94 | 0.73 |  | -152.27 | -58.72 | -0.63 |  | -2.5 | 115
3165 | 8.24 | 24.62 | 3120.11 | 369.61 | 258.3 | 1.63 |  | 78.22 | -63.94 | 0.48 |  | 11.2 | 94
3259 | 7.61 | 39.37 | 3213.22 | 380.55 | 265.06 | 2.26 |  | 114.43 | -66.48 | -0.67 |  | 15.69 | 94
3353 | 7.96 | 33.87 | 3306.36 | 390.76 | 272.63 | 0.88 |  | -67.58 | -67.93 | 0.37 |  | -5.85 | 94
3447 | 10.04 | 35.62 | 3399.2 | 402.83 | 281.03 | 2.23 |  | 8.36 | -70.04 | 2.21 |  | 1.86 | 94
3541 | 11.79 | 32.59 | 3491.49 | 417.58 | 290.98 | 1.96 |  | -19.64 | -72.86 | 1.86 |  | -3.22 | 94
3635 | 11.38 | 30.76 | 3583.58 | 433.64 | 300.89 | 0.59 |  | -139.02 | -76.59 | -0.44 |  | -1.95 | 94
3729 | 10.14 | 31.12 | 3675.92 | 448.7 | 309.91 | 1.32 |  | 177.07 | -80.29 | -1.32 |  | 0.38 | 94
3822 | 12.6 | 28.37 | 3767.09 | 464.63 | 318.97 | 2.71 |  | -13.78 | -84.57 | 2.65 |  | -2.96 | 93
3916 | 13.05 | 26.79 | 3858.75 | 483.13 | 328.62 | 0.61 |  | -38.7 | -90.16 | 0.48 |  | -1.68 | 94
4010 | 12.82 | 29.42 | 3950.36 | 501.68 | 338.53 | 0.67 |  | 112.62 | -95.61 | -0.24 |  | 2.8 | 94
4105 | 13.85 | 30.42 | 4042.8 | 520.67 | 349.46 | 1.11 |  | 13.11 | -100.6 | 1.08 |  | 1.05 | 95
4198 | 13.92 | 39.57 | 4133.09 | 538.89 | 362.23 | 2.36 |  | 92.62 | -103.73 | 0.08 |  | 9.84 | 93
4292 | 12.99 | 38.37 | 4224.51 | 555.89 | 375.99 | 1.03 |  | -163.87 | -105.3 | -0.99 |  | -1.28 | 94
4386 | 12.34 | 36.44 | 4316.22 | 572.26 | 388.51 | 0.83 |  | -147.87 | -107.33 | -0.69 |  | -2.05 | 94
4479 | 11.59 | 35.02 | 4407.2 | 587.9 | 399.78 | 0.87 |  | -159.26 | -109.8 | -0.81 |  | -1.53 | 93
4573 | 10.97 | 34.23 | 4499.39 | 603.03 | 410.23 | 0.68 |  | -166.39 | -112.5 | -0.66 |  | -0.84 | 94
4666 | 12.13 | 33.76 | 4590.5 | 618.47 | 420.63 | 1.25 |  | -4.87 | -115.45 | 1.25 |  | -0.51 | 93
4760 | 12.91 | 38.25 | 4682.27 | 634.93 | 432.62 | 1.33 |  | 53.5 | -117.95 | 0.83 |  | 4.78 | 94
4854 | 12.85 | 37.78 | 4773.9 | 651.44 | 445.53 | 0.13 |  | -120.03 | -119.8 | -0.06 |  | -0.5 | 94
4948 | 12.74 | 37.67 | 4865.57 | 667.9 | 458.27 | 0.12 |  | -167.57 | -121.75 | -0.12 |  | -0.12 | 94
5043 | 12.77 | 36.32 | 4958.23 | 684.65 | 470.89 | 0.32 |  | -84.91 | -123.98 | 0.03 |  | -1.42 | 95
5137 | 12.73 | 35.99 | 5049.91 | 701.4 | 483.12 | 0.09 |  | -118.94 | -126.49 | -0.04 |  | -0.35 | 94
5231 | 12.75 | 35.48 | 5141.59 | 718.23 | 495.23 | 0.12 |  | -80.17 | -129.15 | 0.02 |  | -0.54 | 94
5325 | 12.74 | 34.33 | 5233.28 | 735.24 | 507.1 | 0.27 |  | -92.82 | -132.1 | -0.01 |  | -1.22 | 94
5419 | 12.39 | 33.2 | 5325.03 | 752.23 | 518.46 | 0.45 |  | -145.47 | -135.42 | -0.37 |  | -1.2 | 94
5513 | 12.29 | 32.08 | 5416.85 | 769.15 | 529.3 | 0.28 |  | -113.22 | -139.07 | -0.11 |  | -1.19 | 94
5607 | 12.27 | 31.05 | 5508.7 | 786.18 | 539.76 | 0.23 |  | -95.72 | -143.06 | -0.02 |  | -1.1 | 94
5701 | 11.06 | 28.02 | 5600.76 | 802.7 | 549.15 | 1.44 |  | -154.62 | -147.49 | -1.29 |  | -3.22 | 94
5795 | 10.09 | 21.93 | 5693.17 | 818.3 | 556.46 | 1.57 |  | -133.92 | -152.81 | -1.03 |  | -6.48 | 94
5889 | 10.05 | 17.95 | 5785.72 | 833.74 | 562.07 | 0.74 |  | -95.25 | -159.27 | -0.04 |  | -4.23 | 94
5983 | 10.81 | 23.34 | 5878.17 | 849.64 | 568.09 | 1.31 |  | 54.76 | -165.74 | 0.81 |  | 5.73 | 94
6078 | 10.13 | 27.06 | 5971.59 | 865.26 | 575.42 | 1.01 |  | 136.99 | -171.06 | -0.72 |  | 3.92 | 95
6171 | 10.35 | 31.62 | 6063.11 | 879.66 | 583.52 | 0.9 |  | 77.07 | -174.98 | 0.24 |  | 4.9 | 93
6266 | 11.68 | 39.78 | 6156.36 | 894.31 | 594.15 | 2.15 |  | 53.59 | -177.24 | 1.4 |  | 8.59 | 95
6360 | 12.03 | 42.07 | 6248.36 | 908.9 | 606.8 | 0.62 |  | 54.48 | -177.96 | 0.37 |  | 2.44 | 94
6454 | 11.41 | 41.93 | 6340.4 | 923.09 | 619.58 | 0.66 |  | -177.44 | -178.33 | -0.66 |  | -0.15 | 94
6547 | 11.27 | 42.1 | 6431.58 | 936.67 | 631.81 | 0.15 |  | 166.65 | -178.68 | -0.15 |  | 0.18 | 93
6642 | 11.02 | 42.73 | 6524.79 | 950.23 | 644.2 | 0.29 |  | 154.34 | -178.9 | -0.26 |  | 0.66 | 95
6735 | 10.61 | 41.93 | 6616.14 | 963.13 | 655.95 | 0.47 |  | -160.28 | -179.13 | -0.44 |  | -0.86 | 93
6830 | 11.56 | 45.17 | 6709.36 | 976.35 | 668.55 | 1.2 |  | 34.85 | -178.96 | 1 |  | 3.41 | 95
6924 | 11.78 | 42.49 | 6801.42 | 990.06 | 681.71 | 0.62 |  | -69.23 | -178.73 | 0.23 |  | -2.85 | 94
7015 | 12.42 | 39.34 | 6890.4 | 1004.48 | 694.19 | 1.01 |  | -47.44 | -179.47 | 0.7 |  | -3.46 | 91
7110 | 12.93 | 40.07 | 6983.09 | 1020.52 | 707.5 | 0.56 |  | 17.79 | -180.7 | 0.54 |  | 0.77 | 95
7203 | 12.87 | 38.89 | 7073.74 | 1036.54 | 720.71 | 0.29 |  | -103.41 | -182.01 | -0.06 |  | -1.27 | 93
7297 | 11.77 | 36.31 | 7165.57 | 1052.42 | 732.96 | 1.31 |  | -154.67 | -183.91 | -1.17 |  | -2.74 | 94
7391 | 11.06 | 40.53 | 7257.71 | 1066.99 | 744.49 | 1.17 |  | 132.42 | -185.45 | -0.76 |  | 4.49 | 94
7484 | 11.24 | 43.21 | 7348.96 | 1080.38 | 756.49 | 0.59 |  | 72.16 | -185.83 | 0.19 |  | 2.88 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 270.48 | 33.29 | 79.42 | 222 | 858.16 | 3289.14 | 2772.04 | 0 | 181.64 | 162.76 | 146.05 | 11423.08 | 0
Run | 252.91 | 33.29 | 79.42 | 222 | 858.16 | 3289.14 | 2772.04 | 0 | 181.64 | 162.76 | 146.05 | 11423.08 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/15/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/15/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/15/2021 | 00:00 | 00:30 | 0.5 | 3032 | 3032 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 00:30 | 00:50 | 0.33 | 3032 | 3152 | 120 | INT | 2: BHA 2 | 2K | Rotary Drill f/3033.00 t/3152.00, w/WOB 25.00,Flow 500.00, RPM 50.00, Press 1775.00, Tq 6000.00, ROP 357.00, Diff 400.00
05/15/2021 | 00:50 | 00:55 | 0.08 | 3152 | 3152 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 00:55 | 01:00 | 0.08 | 3152 | 3167 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3152.00 t/3167.00, TF 60.00G, w/WOB 25.00,Flow 500.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00
05/15/2021 | 01:00 | 01:05 | 0.08 | 3167 | 3249 | 82 | INT | 2: BHA 2 | 2K | Rotary Drill f/3167.00 t/3249.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 984.00, Diff 400.00
05/15/2021 | 01:05 | 01:10 | 0.08 | 3249 | 3249 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 01:10 | 01:15 | 0.08 | 3249 | 3264 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3249.00 t/3264.00, TF 60.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00
05/15/2021 | 01:15 | 01:20 | 0.08 | 3264 | 3345 | 81 | INT | 2: BHA 2 | 2K | Rotary Drill f/3264.00 t/3345.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 972.00, Diff 400.00
05/15/2021 | 01:20 | 01:25 | 0.08 | 3345 | 3345 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 01:25 | 01:30 | 0.08 | 3345 | 3357 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3345.00 t/3357.00, TF 0.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 144.00, Diff 400.00
05/15/2021 | 01:30 | 01:35 | 0.08 | 3357 | 3442 | 85 | INT | 2: BHA 2 | 2K | Rotary Drill f/3357.00 t/3442.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1020.00, Diff 400.00
05/15/2021 | 01:35 | 01:40 | 0.08 | 3442 | 3442 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 01:40 | 01:45 | 0.08 | 3442 | 3457 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3442.00 t/3457.00, TF 0.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00, Temp 129.00
05/15/2021 | 01:45 | 01:50 | 0.08 | 3457 | 3517 | 60 | INT | 2: BHA 2 | 2K | Rotary Drill f/3457.00 t/3517.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 720.00, Diff 400.00, Temp 129.00
05/15/2021 | 01:50 | 01:55 | 0.08 | 3517 | 3517 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 01:55 | 02:00 | 0.08 | 3517 | 3611 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3517.00 t/3611.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:00 | 02:05 | 0.08 | 3611 | 3611 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 02:05 | 02:10 | 0.08 | 3611 | 3728 | 117 | INT | 2: BHA 2 | 2K | Rotary Drill f/3611.00 t/3728.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1404.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:10 | 02:15 | 0.08 | 3728 | 3728 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 02:15 | 02:20 | 0.08 | 3728 | 3743 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3728.00 t/3743.00, TF 15.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:20 | 02:25 | 0.08 | 3743 | 3799 | 56 | INT | 2: BHA 2 | 2K | Rotary Drill f/3743.00 t/3799.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 672.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:25 | 02:30 | 0.08 | 3799 | 3799 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 02:30 | 02:35 | 0.08 | 3799 | 3918 | 119 | INT | 2: BHA 2 | 2K | Rotary Drill f/3799.00 t/3918.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1428.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:35 | 02:40 | 0.08 | 3918 | 3918 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 02:40 | 02:45 | 0.08 | 3918 | 3933 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3918.00 t/3933.00, TF 30.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:45 | 02:50 | 0.08 | 3933 | 3986 | 53 | INT | 2: BHA 2 | 2K | Rotary Drill f/3933.00 t/3986.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 636.00, Diff 400.00, Temp 129.00
05/15/2021 | 02:50 | 02:55 | 0.08 | 3986 | 3986 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 02:55 | 03:00 | 0.08 | 3986 | 4100 | 114 | INT | 2: BHA 2 | 2K | Rotary Drill f/3986.00 t/4100.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1368.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:00 | 03:05 | 0.08 | 4100 | 4100 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 03:05 | 03:10 | 0.08 | 4100 | 4115 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4100.00 t/4115.00, TF 60.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:10 | 03:15 | 0.08 | 4115 | 4175 | 60 | INT | 2: BHA 2 | 2K | Rotary Drill f/4115.00 t/4175.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 720.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:15 | 03:20 | 0.08 | 4175 | 4175 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 03:20 | 03:25 | 0.08 | 4175 | 4268 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4175.00 t/4268.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1116.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:25 | 03:30 | 0.08 | 4268 | 4268 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 03:30 | 03:35 | 0.08 | 4268 | 4362 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4268.00 t/4362.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:35 | 03:40 | 0.08 | 4362 | 4362 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 03:40 | 03:45 | 0.08 | 4362 | 4456 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4362.00 t/4456.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:45 | 03:50 | 0.08 | 4456 | 4456 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 03:50 | 03:55 | 0.08 | 4456 | 4549 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4456.00 t/4549.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1116.00, Diff 400.00, Temp 129.00
05/15/2021 | 03:55 | 04:00 | 0.08 | 4549 | 4549 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 04:00 | 04:05 | 0.08 | 4549 | 4655 | 106 | INT | 2: BHA 2 | 2K | Rotary Drill f/4549.00 t/4655.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1272.00, Diff 400.00, Temp 129.00
05/15/2021 | 04:05 | 04:10 | 0.08 | 4655 | 4655 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 04:10 | 04:15 | 0.08 | 4655 | 4670 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4655.00 t/4670.00, TF 15.00G, w/WOB 30.00,Flow 885.00, Press 1775.00, Tq 6000.00, ROP 180.00, Diff 400.00, Temp 129.00
05/15/2021 | 04:15 | 04:20 | 0.08 | 4670 | 4736 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/4670.00 t/4736.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 792.00, Diff 400.00, Temp 129.00
05/15/2021 | 04:20 | 04:25 | 0.08 | 4736 | 4736 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 04:25 | 04:35 | 0.17 | 4736 | 4830 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4736.00 t/4830.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 564.00, Diff 400.00, Temp 129.00
05/15/2021 | 04:35 | 04:40 | 0.08 | 4830 | 4830 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 04:40 | 04:45 | 0.08 | 4830 | 4924 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4830.00 t/4924.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 04:45 | 04:50 | 0.08 | 4924 | 4924 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 04:50 | 04:55 | 0.08 | 4924 | 5018 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4924.00 t/5018.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 04:55 | 05:00 | 0.08 | 5018 | 5018 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 05:00 | 05:10 | 0.17 | 5018 | 5113 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5018.00 t/5113.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 570.00, Diff 400.00, Temp 129.00
05/15/2021 | 05:10 | 05:15 | 0.08 | 5113 | 5113 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 05:15 | 05:20 | 0.08 | 5113 | 5207 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5113.00 t/5207.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 05:20 | 05:25 | 0.08 | 5207 | 5207 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 05:25 | 05:30 | 0.08 | 5207 | 5301 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5207.00 t/5301.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 1128.00, Diff 400.00, Temp 129.00
05/15/2021 | 05:30 | 05:40 | 0.17 | 5301 | 5395 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5301.00 t/5395.00, w/WOB 30.00,Flow 885.00, RPM 80.00, Press 1775.00, Tq 6000.00, ROP 564.00, Diff 400.00, Temp 129.00
05/15/2021 | 05:40 | 05:45 | 0.08 | 5395 | 5395 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 05:45 | 05:55 | 0.17 | 5395 | 5489 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5395.00 t/5489.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 564.00, Diff 800.00, Temp 178.00
05/15/2021 | 05:55 | 06:00 | 0.08 | 5489 | 5489 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 06:00 | 06:10 | 0.17 | 5489 | 5583 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5489.00 t/5583.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 564.00, Diff 800.00, Temp 178.00
05/15/2021 | 06:10 | 06:15 | 0.08 | 5583 | 5583 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 06:15 | 06:25 | 0.17 | 5583 | 5677 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5583.00 t/5677.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 564.00, Diff 800.00, Temp 178.00
05/15/2021 | 06:25 | 06:30 | 0.08 | 5677 | 5677 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 06:30 | 06:35 | 0.08 | 5677 | 5771 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5677.00 t/5771.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 1128.00, Diff 800.00, Temp 178.00
05/15/2021 | 06:35 | 06:40 | 0.08 | 5771 | 5771 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 06:40 | 06:41 | 0.02 | 5771 | 5780 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/5771.00 t/5780.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 540.00, Diff 800.00, Temp 178.00
05/15/2021 | 06:41 | 06:48 | 0.12 | 5780 | 5795 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5780.00 t/5795.00, TF 60.00G, w/WOB 45.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 128.57, Diff 800.00, Temp 178.00
05/15/2021 | 06:48 | 07:00 | 0.2 | 5795 | 5865 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/5795.00 t/5865.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 350.00, Diff 800.00, Temp 178.00
05/15/2021 | 07:00 | 07:05 | 0.08 | 5865 | 5865 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 07:05 | 07:20 | 0.25 | 5865 | 5880 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5865.00 t/5880.00, TF 45.00G, w/WOB 45.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 60.00, Diff 800.00, Temp 178.00
05/15/2021 | 07:20 | 07:40 | 0.33 | 5880 | 5959 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5880.00 t/5959.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 237.00, Diff 800.00, Temp 178.00
05/15/2021 | 07:40 | 07:45 | 0.08 | 5959 | 5959 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 07:45 | 08:05 | 0.33 | 5959 | 5974 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5959.00 t/5974.00, TF 45.00G, w/WOB 45.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 45.00, Diff 800.00, Temp 178.00
05/15/2021 | 08:05 | 08:20 | 0.25 | 5974 | 6053 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5974.00 t/6053.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 316.00, Diff 800.00, Temp 178.00
05/15/2021 | 08:20 | 08:25 | 0.08 | 6053 | 6053 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 08:25 | 08:45 | 0.33 | 6053 | 6068 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6053.00 t/6068.00, TF 45.00G, w/WOB 30.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 45.00, Diff 800.00, Temp 178.00
05/15/2021 | 08:45 | 09:00 | 0.25 | 6068 | 6148 | 80 | INT | 2: BHA 2 | 2K | Rotary Drill f/6068.00 t/6148.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 320.00, Diff 800.00, Temp 178.00
05/15/2021 | 09:00 | 09:05 | 0.08 | 6148 | 6148 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 09:05 | 09:20 | 0.25 | 6148 | 6163 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6148.00 t/6163.00, TF 45.00G, w/WOB 30.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 60.00, Diff 800.00, Temp 178.00
05/15/2021 | 09:20 | 09:35 | 0.25 | 6163 | 6241 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/6163.00 t/6241.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 312.00, Diff 800.00, Temp 178.00
05/15/2021 | 09:35 | 09:40 | 0.08 | 6241 | 6241 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 09:40 | 09:55 | 0.25 | 6241 | 6256 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6241.00 t/6256.00, TF 45.00G, w/WOB 30.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 60.00, Diff 800.00, Temp 178.00
05/15/2021 | 09:55 | 10:10 | 0.25 | 6256 | 6336 | 80 | INT | 2: BHA 2 | 2K | Rotary Drill f/6256.00 t/6336.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 320.00, Diff 800.00, Temp 194.00
05/15/2021 | 10:10 | 10:15 | 0.08 | 6336 | 6336 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 10:15 | 10:25 | 0.17 | 6336 | 6430 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6336.00 t/6430.00, w/WOB 35.00,Flow 885.00, RPM 80.00, Press 4900.00, Tq 15500.00, ROP 564.00, Diff 800.00, Temp 194.00
05/15/2021 | 10:25 | 10:30 | 0.08 | 6430 | 6430 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 10:30 | 10:50 | 0.33 | 6430 | 6445 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6430.00 t/6445.00, TF 0.00G, w/WOB 35.00,Flow 885.00, Press 4900.00, Tq 15500.00, ROP 45.00, Diff 800.00, Temp 194.00
05/15/2021 | 10:50 | 11:20 | 0.5 | 6445 | 6524 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/6445.00 t/6524.00, w/WOB 35.00,Flow 670.00, RPM 80.00, Press 3100.00, Tq 15500.00, ROP 158.00, Diff 500.00, Temp 194.00
05/15/2021 | 11:20 | 11:25 | 0.08 | 6524 | 6524 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 11:25 | 11:27 | 0.03 | 6524 | 6530 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/6524.00 t/6530.00, w/WOB 35.00,Flow 670.00, RPM 80.00, Press 3100.00, Tq 15500.00, ROP 180.00, Diff 500.00, Temp 194.00
05/15/2021 | 11:27 | 12:08 | 0.68 | 6530 | 6545 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6530.00 t/6545.00, TF 0G, w/WOB 35.00,Flow 670.00, Press 3100.00, Tq 15500.00, ROP 21.95, Diff 500.00, Temp 194.00
05/15/2021 | 12:08 | 12:25 | 0.28 | 6545 | 6617 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/6545.00 t/6617.00, w/WOB 35.00,Flow 670.00, RPM 80.00, Press 3100.00, Tq 15500.00, ROP 254.12, Diff 500.00, Temp 194.00
05/15/2021 | 12:25 | 12:30 | 0.08 | 6617 | 6617 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 12:30 | 12:35 | 0.08 | 6617 | 6625 | 8 | INT | 2: BHA 2 | 2K | Rotary Drill f/6617.00 t/6625.00, w/WOB 35.00,Flow 670.00, RPM 80.00, Press 3100.00, Tq 15500.00, ROP 96.00, Diff 500.00, Temp 194.00
05/15/2021 | 12:35 | 13:13 | 0.63 | 6625 | 6640 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6625.00 t/6640.00, TF 0G, w/WOB 35.00,Flow 900, Press 4500, Tq 0, ROP 23.68, Diff 300.00, Temp 194.00
05/15/2021 | 13:13 | 13:24 | 0.18 | 6640 | 6712 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/6640.00 t/6712.00, w/WOB 40,Flow 900, RPM 80.00, Press 4850, Tq 18500, ROP 392.73, Diff 650.00, Temp 194.00
05/15/2021 | 13:24 | 13:30 | 0.1 | 6712 | 6712 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 13:30 | 13:35 | 0.08 | 6712 | 6730 | 18 | INT | 2: BHA 2 | 2K | Rotary Drill f/6712.00 t/6730.00, w/WOB 40,Flow 900, RPM 80.00, Press 4850, Tq 18500, ROP 216.00, Diff 650.00, Temp 194.00
05/15/2021 | 13:35 | 14:30 | 0.92 | 6730 | 6745 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6730.00 t/6745.00, TF 0G, w/WOB 35.00,Flow 900, Press 4500, Tq 0, ROP 16.36, Diff 300.00, Temp 194.00
05/15/2021 | 14:30 | 14:44 | 0.23 | 6745 | 6805 | 60 | INT | 2: BHA 2 | 2K | Rotary Drill f/6745.00 t/6805.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 18500.00, ROP 257.14, Diff 650.00, Temp 194.00
05/15/2021 | 14:44 | 14:50 | 0.1 | 6805 | 6805 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 14:50 | 14:55 | 0.08 | 6805 | 6815 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/6805.00 t/6815.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 18500.00, ROP 120.00, Diff 650.00, Temp 194.00
05/15/2021 | 14:55 | 15:51 | 0.93 | 6815 | 6835 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/6815.00 t/6835.00, TF 0G, w/WOB 35.00,Flow 900.00, Press 4500.00, Tq 0.00, ROP 21.43, Diff 300.00, Temp 194.00
05/15/2021 | 15:51 | 16:05 | 0.23 | 6835 | 6900 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/6835.00 t/6900.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 18500.00, ROP 278.57, Diff 650.00, Temp 194.00
05/15/2021 | 16:05 | 16:53 | 0.8 | 6900 | 6900 | 0 | INT | 2: BHA 2 | 8P | Rig Service
05/15/2021 | 16:53 | 17:03 | 0.17 | 6900 | 6910 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/6900.00 t/6910.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 18500.00, ROP 60.00, Diff 650.00, Temp 194.00
05/15/2021 | 17:03 | 17:58 | 0.92 | 6910 | 6925 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6910.00 t/6925.00, TF -30.00G, w/WOB 35.00,Flow 660.00, Press 2900.00, Tq 0.00, ROP 16.36, Diff 200.00, Temp 194.00
05/15/2021 | 17:58 | 18:10 | 0.2 | 6925 | 6994 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/6925.00 t/6994.00, w/WOB 35.00,Flow 660.00, RPM 0.00, Press 2900.00, Tq 0.00, ROP 345.00, Diff 200.00, Temp 194.00
05/15/2021 | 18:10 | 18:30 | 0.33 | 6994 | 6994 | 0 | INT | 2: BHA 2 | 8P | Rig Service
05/15/2021 | 18:30 | 19:10 | 0.67 | 6994 | 6994 | 0 | INT | 2: BHA 2 | 8O | Circ. / Work Pipe / Weld Stand Pipe Clamp
05/15/2021 | 19:10 | 19:25 | 0.25 | 6994 | 7006 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6994.00 t/7006.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 48.00, Diff 400.00, Temp 194.00
05/15/2021 | 19:25 | 19:45 | 0.33 | 7006 | 7021 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7006.00 t/7021.00, TF 0G, w/WOB 35.00,Flow 900, Press 4300, Tq 17000, ROP 45.00, Diff 400.00, Temp 194.00
05/15/2021 | 19:45 | 20:45 | 1 | 7021 | 7273 | 252 | INT | 2: BHA 2 | 2K | Rotary Drill f/7021.00 t/7273.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 252.00, Diff 400.00, Temp 194.00
05/15/2021 | 20:45 | 20:50 | 0.08 | 7273 | 7273 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 20:50 | 22:00 | 1.17 | 7273 | 7273 | 0 | INT | 2: BHA 2 | 8D | Work On Pumps
05/15/2021 | 22:00 | 22:10 | 0.17 | 7273 | 7386 | 113 | INT | 2: BHA 2 | 2K | Rotary Drill f/7273.00 t/7386.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 678.00, Diff 400.00, Temp 194.00
05/15/2021 | 22:10 | 22:15 | 0.08 | 7386 | 7386 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 22:15 | 22:45 | 0.5 | 7386 | 7406 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7386.00 t/7406.00, TF 60G, w/WOB 35.00,Flow 900, Press 4300, Tq 17000, ROP 40.00, Diff 400.00, Temp 194.00
05/15/2021 | 22:45 | 23:00 | 0.25 | 7406 | 7461 | 55 | INT | 2: BHA 2 | 2K | Rotary Drill f/7406.00 t/7461.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 220.00, Diff 400.00, Temp 194.00
05/15/2021 | 23:00 | 23:05 | 0.08 | 7461 | 7461 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 23:05 | 23:25 | 0.33 | 7461 | 7566 | 105 | INT | 2: BHA 2 | 2K | Rotary Drill f/7461.00 t/7566.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 315.00, Diff 400.00, Temp 194.00
05/15/2021 | 23:25 | 23:30 | 0.08 | 7566 | 7566 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/15/2021 | 23:30 | 24:00 | 0.5 | 7566 | 7576 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/7566.00 t/7576.00, TF 0G, w/WOB 35.00,Flow 900, Press 4300, Tq 17000, ROP 20.00, Diff 400.00, Temp 194.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_16_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/16/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 58630
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 7576 |  | 3033 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 19 | PV: | 6
End Depth (Usft): |  | 9424 |  | 9424 |  | OD (in): |  |  |  | 300: | 13 | YP: | 7
Total Drilled (Usft): |  | 1848 |  | 6392 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): |  | 341 |  | 688 | [5 empty] | 100: | 8 | Chlorides: | 45000
Rotary Drilled (Usft): |  | 1507 |  | 5704 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 6.20
Drlg/Circ Hrs: |  | 20.18 / 2.23 |  | 37.10 / 8.02 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77:23
Slide Drilling Hrs: |  | 12.83 |  | 20.78 |  | SN: |  | 54682 |  | 10s Gel: | 3 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 7.35 |  | 16.32 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 82.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 205.03 / 26.57 |  | 349.58 / 33.10 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 54 |  | Grade In: |  | New
% Slide: |  | 18.45 |  | 10.76 |  | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
% Rotary: |  | 81.55 |  | 89.24 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
8 7/8 5.9 2.0F Slick -.016 |  |  |  | 8 | [5 empty] | 37.58 |  | 39.08
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 49.18
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 51.73
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 80.86
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 110.06
Crossover Sub |  |  |  | 6.5 | 2.375 |  |  |  |  | 2.35 |  | 112.41
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 186.82 |  | 299.23
Crossover Sub |  |  |  | 6.438 | 2.375 |  |  |  |  | 2.89 |  | 302.12
3 Stds 5 in HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 579.24
22 Stds 5 in DP |  |  |  | 5 | 2.563 |  |  |  |  | 2067.72 |  | 2646.96
Agitator |  |  |  | 6.812 | [5 empty] | 24.62 |  | 2671.58
2671.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800055 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.98 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
7579 | 11.02 | 37.82 | 7442.18 | 1094.3 | 768.4 | 1.12 |  | -104.57 | -186.65 | -0.23 |  | -5.67 | 95
7673 | 11.54 | 35.63 | 7534.36 | 1109.04 | 779.39 | 0.72 |  | -40.56 | -188.7 | 0.55 |  | -2.33 | 94
7767 | 11.75 | 43.89 | 7626.43 | 1123.58 | 791.5 | 1.79 |  | 86.88 | -189.79 | 0.22 |  | 8.79 | 94
7861 | 12.15 | 47.73 | 7718.4 | 1137.13 | 805.46 | 0.95 |  | 65.18 | -188.86 | 0.43 |  | 4.09 | 94
7955 | 10.72 | 45.72 | 7810.53 | 1149.89 | 819.04 | 1.58 |  | -165.41 | -187.66 | -1.52 |  | -2.14 | 94
8049 | 10.86 | 41.63 | 7902.87 | 1162.61 | 831.18 | 0.83 |  | -81.65 | -187.49 | 0.15 |  | -4.35 | 94
8143 | 11.73 | 35.46 | 7995.05 | 1177.02 | 842.61 | 1.58 |  | -57.3 | -188.99 | 0.93 |  | -6.56 | 94
8236 | 11.71 | 28.79 | 8086.11 | 1192.99 | 852.64 | 1.46 |  | -94.11 | -192.58 | -0.02 |  | -7.17 | 93
8330 | 12.34 | 23.84 | 8178.05 | 1210.54 | 861.29 | 1.29 |  | -61.02 | -198.25 | 0.67 |  | -5.27 | 94
8424 | 11.14 | 20.97 | 8270.09 | 1228.2 | 868.6 | 1.42 |  | -155.45 | -204.98 | -1.28 |  | -3.05 | 94
8519 | 10.17 | 17.73 | 8363.45 | 1244.76 | 874.44 | 1.2 |  | -149.89 | -212.03 | -1.02 |  | -3.41 | 95
8613 | 10.06 | 22.98 | 8455.99 | 1260.23 | 880.17 | 0.99 |  | 99.38 | -218.41 | -0.12 |  | 5.59 | 94
8708 | 11.06 | 26.58 | 8549.38 | 1276.02 | 887.49 | 1.26 |  | 35.19 | -223.86 | 1.05 |  | 3.79 | 95
8801 | 12.49 | 32.28 | 8640.42 | 1292.5 | 896.85 | 1.98 |  | 41.94 | -228.28 | 1.54 |  | 6.13 | 93
8894 | 12.75 | 32.93 | 8731.18 | 1309.61 | 907.8 | 0.32 |  | 28.96 | -231.98 | 0.28 |  | 0.7 | 93
8988 | 11.49 | 29.99 | 8823.08 | 1326.43 | 918.12 | 1.49 |  | -155.33 | -235.94 | -1.34 |  | -3.13 | 94
9082 | 10.39 | 28.01 | 8915.37 | 1342.02 | 926.78 | 1.24 |  | -162.11 | -240.27 | -1.17 |  | -2.11 | 94
9177 | 12.57 | 37.74 | 9008.47 | 1357.76 | 937.13 | 3.06 |  | 46.45 | -243.46 | 2.29 |  | 10.24 | 95
9270 | 12.03 | 38.02 | 9099.34 | 1373.4 | 949.3 | 0.58 |  | 173.83 | -245.27 | -0.58 |  | 0.3 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 91.62 | 38.44 | 80 | 219 | 836.44 | 4186.67 | 3702.22 | 0 | 260 | 210 | 180 | 20965.52 | 0
Run | 167.1 | 35.21 | 79.63 | 221 | 850.08 | 3622.93 | 3117.98 | 0 | 210.79 | 180.33 | 158.68 | 14839.51 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/16/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/16/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/16/2021 | 00:00 | 00:25 | 0.42 | 7576 | 7584 | 8 | INT | 2: BHA 2 | 2J | Slide Drill f/7576.00 t/7584.00, TF 0G, w/WOB 35.00,Flow 900, Press 4300, Tq 17000, ROP 19.20, Diff 400.00, Temp 194.00
05/16/2021 | 00:25 | 00:45 | 0.33 | 7584 | 7649 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/7584.00 t/7649.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 195.00, Diff 400.00, Temp 194.00
05/16/2021 | 00:45 | 00:50 | 0.08 | 7649 | 7649 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 00:50 | 02:25 | 1.58 | 7649 | 7649 | 0 | INT | 2: BHA 2 | 8A | Change Saver Sub
05/16/2021 | 02:25 | 02:30 | 0.08 | 7649 | 7659 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7649.00 t/7659.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 120.00, Diff 400.00, Temp 194.00
05/16/2021 | 02:30 | 03:30 | 1 | 7659 | 7679 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7659.00 t/7679.00, TF 0G, w/WOB 35.00,Flow 900, Press 4300, Tq 17000, ROP 20.00, Diff 400.00, Temp 194.00
05/16/2021 | 03:30 | 03:50 | 0.33 | 7679 | 7753 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/7679.00 t/7753.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 222.00, Diff 400.00, Temp 194.00
05/16/2021 | 03:50 | 03:55 | 0.08 | 7753 | 7753 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 03:55 | 04:10 | 0.25 | 7753 | 7773 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7753.00 t/7773.00, TF 0G, w/WOB 35.00,Flow 900, Press 4300, Tq 17000, ROP 80.00, Diff 400.00, Temp 194.00
05/16/2021 | 04:10 | 04:20 | 0.17 | 7773 | 7873 | 100 | INT | 2: BHA 2 | 2K | Rotary Drill f/7773.00 t/7873.00, w/WOB 35.00,Flow 900, RPM 80, Press 4300, Tq 17000, ROP 600.00, Diff 400.00, Temp 194.00
05/16/2021 | 04:20 | 04:25 | 0.08 | 7873 | 7873 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 04:25 | 04:45 | 0.33 | 7873 | 7939 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/7873.00 t/7939.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 4300.00, Tq 17000.00, ROP 198.00, Diff 400.00, Temp 194.00
05/16/2021 | 04:45 | 04:50 | 0.08 | 7939 | 7939 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 04:50 | 05:10 | 0.33 | 7939 | 7959 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7939.00 t/7959.00, TF -45G, w/WOB 35.00,Flow 900.00, Press 4300.00, Tq 17000.00, ROP 60.00, Diff 400.00, Temp 194.00
05/16/2021 | 05:10 | 05:40 | 0.5 | 7959 | 8044 | 85 | INT | 2: BHA 2 | 2K | Rotary Drill f/7959.00 t/8044.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 4300.00, Tq 17000.00, ROP 170.00, Diff 400.00, Temp 194.00
05/16/2021 | 05:40 | 05:45 | 0.08 | 8044 | 8044 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 05:45 | 06:36 | 0.85 | 8044 | 8064 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8044.00 t/8064.00, TF -45G, w/WOB 35.00,Flow 900.00, Press 4300.00, Tq 0, ROP 23.53, Diff 400.00, Temp 194.00
05/16/2021 | 06:36 | 06:52 | 0.27 | 8064 | 8119 | 55 | INT | 2: BHA 2 | 2K | Rotary Drill f/8064.00 t/8119.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 4300.00, Tq 22000, ROP 206.25, Diff 400.00, Temp 194.00
05/16/2021 | 06:52 | 06:57 | 0.08 | 8119 | 8119 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 06:57 | 07:00 | 0.05 | 8119 | 8130 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/8119.00 t/8130.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 4300.00, Tq 22000, ROP 220.00, Diff 400.00, Temp 194.00
05/16/2021 | 07:00 | 07:57 | 0.95 | 8130 | 8147 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/8130.00 t/8147.00, TF -30G, w/WOB 35.00,Flow 900.00, Press 4300.00, Tq 0, ROP 17.89, Diff 400.00, Temp 194.00
05/16/2021 | 07:57 | 08:15 | 0.3 | 8147 | 8213 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/8147.00 t/8213.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 4300.00, Tq 22000, ROP 220.00, Diff 400.00, Temp 194.00
05/16/2021 | 08:15 | 08:25 | 0.17 | 8213 | 8213 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 08:25 | 08:30 | 0.08 | 8213 | 8225 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/8213.00 t/8225.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 4300.00, Tq 22000, ROP 144.00, Diff 400.00, Temp 194.00
05/16/2021 | 08:30 | 09:35 | 1.08 | 8225 | 8245 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8225.00 t/8245.00, TF 0G, w/WOB 35.00,Flow 900.00, Press 4300.00, Tq 0, ROP 18.46, Diff 400.00, Temp 219.00
05/16/2021 | 09:35 | 09:50 | 0.25 | 8245 | 8275 | 30 | INT | 2: BHA 2 | 2K | Rotary Drill f/8245.00 t/8275.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 4300.00, Tq 22000, ROP 120.00, Diff 400.00, Temp 219.00
05/16/2021 | 09:50 | 10:20 | 0.5 | 8275 | 8285 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/8275.00 t/8285.00, TF 0G, w/WOB 35.00,Flow 900.00, Press 4300.00, Tq 0, ROP 20.00, Diff 400.00, Temp 219.00
05/16/2021 | 10:20 | 10:31 | 0.18 | 8285 | 8306 | 21 | INT | 2: BHA 2 | 2K | Rotary Drill f/8285.00 t/8306.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 4300.00, Tq 22000, ROP 114.55, Diff 400.00, Temp 219.00
05/16/2021 | 10:31 | 10:41 | 0.17 | 8306 | 8306 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 10:41 | 10:54 | 0.22 | 8306 | 8400 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8306.00 t/8400.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850, Tq 22000.00, ROP 433.85, Diff 500.00, Temp 219.00
05/16/2021 | 10:54 | 11:00 | 0.1 | 8400 | 8400 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 11:00 | 11:18 | 0.3 | 8400 | 8494 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8400.00 t/8494.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850, Tq 22000.00, ROP 313.33, Diff 500.00, Temp 219.00
05/16/2021 | 11:18 | 11:28 | 0.17 | 8494 | 8494 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 11:28 | 11:46 | 0.3 | 8494 | 8589 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8494.00 t/8589.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850, Tq 22000.00, ROP 316.67, Diff 500.00, Temp 219.00
05/16/2021 | 11:46 | 11:56 | 0.17 | 8589 | 8589 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 11:56 | 12:00 | 0.07 | 8589 | 8595 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/8589.00 t/8595.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850, Tq 22000.00, ROP 90.00, Diff 500.00, Temp 219.00
05/16/2021 | 12:00 | 12:29 | 0.48 | 8595 | 8622 | 27 | INT | 2: BHA 2 | 2J | Slide Drill f/8595.00 t/8622.00, TF 40G, w/WOB 40.00,Flow 900.00, Press 4850, Tq 0, ROP 55.86, Diff 500.00, Temp 228.00
05/16/2021 | 12:29 | 12:48 | 0.32 | 8622 | 8683 | 61 | INT | 2: BHA 2 | 2K | Rotary Drill f/8622.00 t/8683.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850, Tq 22000.00, ROP 192.63, Diff 500.00, Temp 228.00
05/16/2021 | 12:48 | 12:58 | 0.17 | 8683 | 8683 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 12:58 | 13:01 | 0.05 | 8683 | 8695 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/8683.00 t/8695.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850, Tq 22000.00, ROP 240.00, Diff 500.00, Temp 228.00
05/16/2021 | 13:01 | 13:35 | 0.57 | 8695 | 8725 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/8695.00 t/8725.00, TF 40G, w/WOB 40.00,Flow 900.00, Press 4850, Tq 0, ROP 52.94, Diff 500.00, Temp 228.00
05/16/2021 | 13:35 | 13:51 | 0.27 | 8725 | 8778 | 53 | INT | 2: BHA 2 | 2K | Rotary Drill f/8725.00 t/8778.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 22000.00, ROP 198.75, Diff 500.00, Temp 228.00
05/16/2021 | 13:51 | 14:00 | 0.15 | 8778 | 8778 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 14:00 | 14:05 | 0.08 | 8778 | 8790 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/8778.00 t/8790.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 22000.00, ROP 144.00, Diff 500.00, Temp 228.00
05/16/2021 | 14:05 | 14:25 | 0.33 | 8790 | 8816 | 26 | INT | 2: BHA 2 | 2J | Slide Drill f/8790.00 t/8816.00, TF 40G, w/WOB 40.00,Flow 900.00, Press 4850.00, Tq 0.00, ROP 78.00, Diff 500.00, Temp 228.00
05/16/2021 | 14:25 | 14:41 | 0.27 | 8816 | 8871 | 55 | INT | 2: BHA 2 | 2K | Rotary Drill f/8816.00 t/8871.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 4850.00, Tq 22000.00, ROP 206.25, Diff 500.00, Temp 228.00
05/16/2021 | 14:41 | 14:50 | 0.15 | 8871 | 8871 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 14:50 | 15:16 | 0.43 | 8871 | 8964 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8871.00 t/8964.00, w/WOB 40.00,Flow 680, RPM 80.00, Press 3400, Tq 22000.00, ROP 214.62, Diff 600.00, Temp 228.00
05/16/2021 | 15:16 | 15:26 | 0.17 | 8964 | 8964 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 15:26 | 15:48 | 0.37 | 8964 | 9058 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8964.00 t/9058.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 256.36, Diff 600.00, Temp 228.00
05/16/2021 | 15:48 | 15:58 | 0.17 | 9058 | 9058 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 15:58 | 16:02 | 0.07 | 9058 | 9065 | 7 | INT | 2: BHA 2 | 2K | Rotary Drill f/9058.00 t/9065.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 105.00, Diff 600.00, Temp 228.00
05/16/2021 | 16:02 | 17:12 | 1.17 | 9065 | 9082 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/9065.00 t/9082.00, TF 60G, w/WOB 40.00,Flow 900, Press 4900, Tq 22000.00, ROP 14.57, Diff 200.00, Temp 228.00
05/16/2021 | 17:12 | 17:26 | 0.23 | 9082 | 9122 | 40 | INT | 2: BHA 2 | 2K | Rotary Drill f/9082.00 t/9122.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 171.43, Diff 600.00, Temp 228.00
05/16/2021 | 17:26 | 18:55 | 1.48 | 9122 | 9152 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/9122.00 t/9152.00, TF 60.00G, w/WOB 40.00,Flow 680.00, Press 3400.00, Tq 22000.00, ROP 20.22, Diff 600.00, Temp 228.00
05/16/2021 | 18:55 | 19:00 | 0.08 | 9152 | 9152 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 19:00 | 19:15 | 0.25 | 9152 | 9170 | 18 | INT | 2: BHA 2 | 2K | Rotary Drill f/9152.00 t/9170.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 72.00, Diff 600.00, Temp 228.00
05/16/2021 | 19:15 | 20:35 | 1.33 | 9170 | 9194 | 24 | INT | 2: BHA 2 | 2J | Slide Drill f/9170.00 t/9194.00, TF 60G, w/WOB 40.00,Flow 680.00, Press 3400.00, Tq 22000.00, ROP 18.00, Diff 600.00, Temp 228.00
05/16/2021 | 20:35 | 21:15 | 0.67 | 9194 | 9247 | 53 | INT | 2: BHA 2 | 2K | Rotary Drill f/9194.00 t/9247.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 79.50, Diff 600.00, Temp 228.00
05/16/2021 | 21:15 | 21:15 | 0 | 9247 | 9247 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 21:15 | 21:35 | 0.33 | 9247 | 9352 | 105 | INT | 2: BHA 2 | 2K | Rotary Drill f/9247.00 t/9352.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 315.00, Diff 600.00, Temp 228.00
05/16/2021 | 21:35 | 21:40 | 0.08 | 9352 | 9352 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/16/2021 | 21:40 | 23:10 | 1.5 | 9352 | 9377 | 25 | INT | 2: BHA 2 | 2J | Slide Drill f/9352.00 t/9377.00, TF 50G, w/WOB 40.00,Flow 680.00, Press 3400.00, Tq 22000.00, ROP 16.67, Diff 600.00, Temp 228.00
05/16/2021 | 23:10 | 23:25 | 0.25 | 9377 | 9397 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/9377.00 t/9397.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 80.00, Diff 600.00, Temp 228.00
05/16/2021 | 23:25 | 24:00 | 0.58 | 9397 | 9424 | 27 | INT | 2: BHA 2 | 2J | Slide Drill f/9397.00 t/9424.00, TF 45G, w/WOB 40.00,Flow 680.00, Press 3400.00, Tq 22000.00, ROP 46.29, Diff 600.00, Temp 228.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_17_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/17/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17000 |  |  | Well Cost($): |  | 75630
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9424 |  | 3033 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 19 | PV: | 6
End Depth (Usft): |  | 11217 |  | 11217 |  | OD (in): |  |  |  | 300: | 13 | YP: | 7
Total Drilled (Usft): |  | 1793 |  | 8185 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): |  | 264 |  | 952 | [5 empty] | 100: | 8 | Chlorides: | 45000
Rotary Drilled (Usft): |  | 1529 |  | 7233 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 6.20
Drlg/Circ Hrs: |  | 18.20 / 5.47 |  | 55.30 / 13.48 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77:23
Slide Drilling Hrs: |  | 10.33 |  | 31.12 |  | SN: |  | 54682 |  | 10s Gel: | 3 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 7.87 |  | 24.18 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 82.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 194.36 / 25.55 |  | 299.09 / 30.59 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 78 |  | Grade In: |  | New
% Slide: |  | 14.72 |  | 11.63 |  | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
% Rotary: |  | 85.28 |  | 88.37 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
8 7/8 5.9 2.0F Slick -.016 |  |  |  | 8 | [5 empty] | 37.58 |  | 39.08
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 49.18
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 51.73
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 80.86
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 110.06
Crossover Sub |  |  |  | 6.5 | 2.375 |  |  |  |  | 2.35 |  | 112.41
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 186.82 |  | 299.23
Crossover Sub |  |  |  | 6.438 | 2.375 |  |  |  |  | 2.89 |  | 302.12
3 Stds 5 in HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 579.24
22 Stds 5 in DP |  |  |  | 5 | 2.563 |  |  |  |  | 2067.72 |  | 2646.96
Agitator |  |  |  | 6.812 | [5 empty] | 24.62 |  | 2671.58
2671.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800055 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.98 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9364 | 10.88 | 36.76 | 9191.46 | 1388.23 | 960.64 | 1.25 |  | -168.34 | -247.11 | -1.22 |  | -1.34 | 94
9458 | 11.34 | 38.46 | 9283.7 | 1402.57 | 971.7 | 0.6 |  | 36.29 | -248.84 | 0.49 |  | 1.81 | 94
9552 | 10.65 | 36.73 | 9375.98 | 1416.77 | 982.64 | 0.81 |  | -155.29 | -250.55 | -0.73 |  | -1.84 | 94
9647 | 10.17 | 37.57 | 9469.41 | 1430.45 | 993 | 0.53 |  | 162.87 | -252.34 | -0.51 |  | 0.88 | 95
9740 | 10.82 | 47.12 | 9560.86 | 1442.9 | 1004.41 | 1.99 |  | 74.25 | -252.51 | 0.7 |  | 10.27 | 93
9834 | 11.17 | 52.87 | 9653.14 | 1454.4 | 1018.13 | 1.22 |  | 75.14 | -250.35 | 0.37 |  | 6.12 | 94
9927 | 9.59 | 49.09 | 9744.62 | 1464.91 | 1031.17 | 1.85 |  | -158.53 | -248.01 | -1.7 |  | -4.06 | 93
10021 | 8.61 | 46.51 | 9837.43 | 1474.88 | 1042.19 | 1.13 |  | -158.66 | -246.78 | -1.04 |  | -2.74 | 94
10114 | 7.27 | 41.65 | 9929.54 | 1484.07 | 1051.15 | 1.61 |  | -155.78 | -246.51 | -1.44 |  | -5.23 | 93
10208 | 6.17 | 37.16 | 10022.89 | 1492.54 | 1058.16 | 1.3 |  | -156.69 | -247.19 | -1.17 |  | -4.78 | 94
10302 | 6.28 | 44.74 | 10116.34 | 1500.22 | 1064.83 | 0.88 |  | 86.16 | -247.56 | 0.12 |  | 8.06 | 94
10396 | 5.27 | 48.29 | 10209.86 | 1506.74 | 1071.67 | 1.14 |  | 162.28 | -247.02 | -1.07 |  | 3.78 | 94
10490 | 4.97 | 46.63 | 10303.49 | 1512.41 | 1077.85 | 0.36 |  | -154.54 | -246.38 | -0.32 |  | -1.77 | 94
10583 | 3.95 | 39.05 | 10396.21 | 1517.67 | 1082.8 | 1.26 |  | -153.72 | -246.36 | -1.1 |  | -8.15 | 93
10678 | 4.3 | 32.07 | 10490.96 | 1523.22 | 1086.75 | 0.64 |  | -58.63 | -247.27 | 0.37 |  | -7.35 | 95
10772 | 4.4 | 41.58 | 10584.69 | 1528.91 | 1091.02 | 0.77 |  | 86.87 | -248.04 | 0.11 |  | 10.12 | 94
10866 | 4.38 | 34.6 | 10678.42 | 1534.56 | 1095.45 | 0.57 |  | -95.62 | -248.67 | -0.02 |  | -7.43 | 94
10960 | 3.93 | 17.45 | 10772.17 | 1540.59 | 1098.45 | 1.4 |  | -118.32 | -250.6 | -0.48 |  | -18.24 | 94
11053 | 3.81 | 358.97 | 10864.96 | 1546.72 | 1099.35 | 1.34 |  | -104.67 | -254.13 | -0.13 |  | -19.87 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 98.52 | 38.98 | 80 | 217 | 823.48 | 5004.35 | 4454.35 | 0 | 310.22 | 240.98 | 192.39 | 22000 | 0
Run | 144.95 | 36.25 | 79.74 | 221 | 851.98 | 4088.47 | 3574.1 | 0 | 239.64 | 197.04 | 167.96 | 16912.28 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/17/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/17/2021 |  | 5 |  | 100 |  | 4 | 400
Extreme Orbitt RSS - Standby |  |  |  |  | 05/17/2021 |  | 17 |  | 9750 |  | 1 | 9750
Total | [11 empty] | 17000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/17/2021 | 00:00 | 00:15 | 0.25 | 9424 | 9444 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/9424.00 t/9444.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 80.00, Diff 600.00, Temp 228.00
05/17/2021 | 00:15 | 00:20 | 0.08 | 9444 | 9444 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 00:20 | 01:15 | 0.92 | 9444 | 9460 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/9444.00 t/9460.00, TF 60G, w/WOB 40.00,Flow 680.00, Press 3400.00, Tq 22000.00, ROP 17.45, Diff 600.00, Temp 228.00
05/17/2021 | 01:15 | 01:35 | 0.33 | 9460 | 9528 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/9460.00 t/9528.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 204.00, Diff 600.00, Temp 228.00
05/17/2021 | 01:35 | 01:40 | 0.08 | 9528 | 9528 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 01:40 | 02:00 | 0.33 | 9528 | 9528 | 0 | INT | 2: BHA 2 | 8P | Rig Service
05/17/2021 | 02:00 | 02:10 | 0.17 | 9528 | 9543 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/9528.00 t/9543.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 90.00, Diff 600.00, Temp 228.00
05/17/2021 | 02:10 | 03:20 | 1.17 | 9543 | 9573 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/9543.00 t/9573.00, TF 60.00G, w/WOB 40.00,Flow 680.00, Press 3400.00, Tq 22000.00, ROP 25.71, Diff 600.00, Temp 228.00
05/17/2021 | 03:20 | 03:35 | 0.25 | 9573 | 9622 | 49 | INT | 2: BHA 2 | 2K | Rotary Drill f/9573.00 t/9622.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 196.00, Diff 600.00, Temp 228.00
05/17/2021 | 03:35 | 05:30 | 1.92 | 9622 | 9622 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 05:30 | 05:35 | 0.08 | 9622 | 9637 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/9622.00 t/9637.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3400.00, Tq 22000.00, ROP 180.00, Diff 600.00, Temp 228.00
05/17/2021 | 05:35 | 06:06 | 0.52 | 9637 | 9652 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/9637.00 t/9652.00, TF 60G, w/WOB 40.00,Flow 900.00, Press 5300.00, Tq 0.00, ROP 29.03, Diff 400.00, Temp 228.00
05/17/2021 | 06:06 | 06:26 | 0.33 | 9652 | 9717 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/9652.00 t/9717.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 195.00, Diff 700.00, Temp 228.00
05/17/2021 | 06:26 | 06:36 | 0.17 | 9717 | 9717 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 06:36 | 06:41 | 0.08 | 9717 | 9725 | 8 | INT | 2: BHA 2 | 2K | Rotary Drill f/9717.00 t/9725.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 96.00, Diff 700.00, Temp 228.00
05/17/2021 | 06:41 | 07:17 | 0.6 | 9725 | 9765 | 40 | INT | 2: BHA 2 | 2J | Slide Drill f/9725.00 t/9765.00, TF 60G, w/WOB 40.00,Flow 900.00, Press 5300.00, Tq 0.00, ROP 66.67, Diff 400.00, Temp 228.00
05/17/2021 | 07:17 | 07:30 | 0.22 | 9765 | 9810 | 45 | INT | 2: BHA 2 | 2K | Rotary Drill f/9765.00 t/9810.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 207.69, Diff 700.00, Temp 228.00
05/17/2021 | 07:30 | 07:40 | 0.17 | 9810 | 9810 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 07:40 | 07:58 | 0.3 | 9810 | 9904 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9810.00 t/9904.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 313.33, Diff 700.00, Temp 228.00
05/17/2021 | 07:58 | 08:05 | 0.12 | 9904 | 9904 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 08:05 | 08:35 | 0.5 | 9904 | 9997 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9904.00 t/9997.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 186.00, Diff 700.00, Temp 248.00
05/17/2021 | 08:35 | 08:45 | 0.17 | 9997 | 9997 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 08:45 | 09:00 | 0.25 | 9997 | 10091 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9997.00 t/10091.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 376.00, Diff 700.00, Temp 248.00
05/17/2021 | 09:00 | 09:10 | 0.17 | 10091 | 10091 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 09:10 | 09:22 | 0.2 | 10091 | 10184 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/10091.00 t/10184.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 465.00, Diff 700.00, Temp 248.00
05/17/2021 | 09:22 | 09:32 | 0.17 | 10184 | 10184 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 09:32 | 09:37 | 0.08 | 10184 | 10195 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/10184.00 t/10195.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 132.00, Diff 700.00, Temp 248.00
05/17/2021 | 09:37 | 10:16 | 0.65 | 10195 | 10209 | 14 | INT | 2: BHA 2 | 2J | Slide Drill f/10195.00 t/10209.00, TF 60G, w/WOB 27,Flow 900.00, Press 5600, Tq 0, ROP 21.54, Diff 200.00, Temp 248.00
05/17/2021 | 10:16 | 10:27 | 0.18 | 10209 | 10225 | 16 | INT | 2: BHA 2 | 2K | Rotary Drill f/10209.00 t/10225.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5800, Tq 22000.00, ROP 87.27, Diff 400.00, Temp 248.00
05/17/2021 | 10:27 | 10:59 | 0.53 | 10225 | 10236 | 11 | INT | 2: BHA 2 | 2J | Slide Drill f/10225.00 t/10236.00, TF 60G, w/WOB 27,Flow 900.00, Press 5600, Tq 0, ROP 20.63, Diff 200.00, Temp 248.00
05/17/2021 | 10:59 | 11:12 | 0.22 | 10236 | 10278 | 42 | INT | 2: BHA 2 | 2K | Rotary Drill f/10236.00 t/10278.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 193.85, Diff 700.00, Temp 248.00
05/17/2021 | 11:12 | 11:22 | 0.17 | 10278 | 10278 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 11:22 | 11:27 | 0.08 | 10278 | 10285 | 7 | INT | 2: BHA 2 | 2K | Rotary Drill f/10278.00 t/10285.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 84.00, Diff 700.00, Temp 248.00
05/17/2021 | 11:27 | 11:48 | 0.35 | 10285 | 10307 | 22 | INT | 2: BHA 2 | 2J | Slide Drill f/10285.00 t/10307.00, TF 60G, w/WOB 27,Flow 900.00, Press 5600, Tq 0, ROP 62.86, Diff 200.00, Temp 248.00
05/17/2021 | 11:48 | 12:05 | 0.28 | 10307 | 10372 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/10307.00 t/10372.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 229.41, Diff 700.00, Temp 248.00
05/17/2021 | 12:05 | 12:15 | 0.17 | 10372 | 10372 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 12:15 | 12:22 | 0.12 | 10372 | 10408 | 36 | INT | 2: BHA 2 | 2K | Rotary Drill f/10372.00 t/10408.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 22000.00, ROP 308.57, Diff 700.00, Temp 248.00
05/17/2021 | 12:22 | 12:43 | 0.35 | 10408 | 10466 | 58 | INT | 2: BHA 2 | 2K | Rotary Drill f/10408.00 t/10466.00, w/WOB 40.00,Flow 680, RPM 80.00, Press 3850, Tq 22000.00, ROP 165.71, Diff 600.00, Temp 248.00
05/17/2021 | 12:43 | 12:53 | 0.17 | 10466 | 10466 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 12:53 | 13:02 | 0.15 | 10466 | 10524 | 58 | INT | 2: BHA 2 | 2K | Rotary Drill f/10466.00 t/10524.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3850.00, Tq 22000.00, ROP 386.67, Diff 600.00, Temp 248.00
05/17/2021 | 13:02 | 13:13 | 0.18 | 10524 | 10560 | 36 | INT | 2: BHA 2 | 2K | Rotary Drill f/10524.00 t/10560.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 22000.00, ROP 196.36, Diff 400.00, Temp 248.00
05/17/2021 | 13:13 | 13:23 | 0.17 | 10560 | 10560 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 13:23 | 13:28 | 0.08 | 10560 | 10570 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/10560.00 t/10570.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 22000.00, ROP 120.00, Diff 400.00, Temp 248.00
05/17/2021 | 13:28 | 14:08 | 0.67 | 10570 | 10585 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/10570.00 t/10585.00, TF 30G, w/WOB 32,Flow 900.00, Press 5600.00, Tq 0.00, ROP 22.50, Diff 200.00, Temp 248.00
05/17/2021 | 14:08 | 14:26 | 0.3 | 10585 | 10653 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/10585.00 t/10653.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 22000.00, ROP 226.67, Diff 400.00, Temp 248.00
05/17/2021 | 14:26 | 14:36 | 0.17 | 10653 | 10653 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 14:36 | 14:40 | 0.07 | 10653 | 10660 | 7 | INT | 2: BHA 2 | 2K | Rotary Drill f/10653.00 t/10660.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 22000.00, ROP 105.00, Diff 400.00, Temp 248.00
05/17/2021 | 14:40 | 15:43 | 1.05 | 10660 | 10678 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/10660.00 t/10678.00, TF 20G, w/WOB 40.00,Flow 680, Press 3650, Tq 0, ROP 17.14, Diff 300.00, Temp 248.00
05/17/2021 | 15:43 | 15:55 | 0.2 | 10678 | 10710 | 32 | INT | 2: BHA 2 | 2K | Rotary Drill f/10678.00 t/10710.00, w/WOB 40.00,Flow 680, RPM 80, Press 3950, Tq 22000, ROP 160.00, Diff 600.00, Temp 248.00
05/17/2021 | 15:55 | 16:44 | 0.82 | 10710 | 10728 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/10710.00 t/10728.00, TF 20G, w/WOB 40.00,Flow 680, Press 3650, Tq 0, ROP 22.04, Diff 300.00, Temp 248.00
05/17/2021 | 16:44 | 16:56 | 0.2 | 10728 | 10748 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/10728.00 t/10748.00, w/WOB 40.00,Flow 680, RPM 80, Press 3950, Tq 22000, ROP 100.00, Diff 600.00, Temp 248.00
05/17/2021 | 16:56 | 17:02 | 0.1 | 10748 | 10748 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 17:02 | 17:06 | 0.07 | 10748 | 10755 | 7 | INT | 2: BHA 2 | 2K | Rotary Drill f/10748.00 t/10755.00, w/WOB 40.00,Flow 680, RPM 80, Press 3950, Tq 22000, ROP 105.00, Diff 600.00, Temp 248.00
05/17/2021 | 17:06 | 18:20 | 1.23 | 10755 | 10783 | 28 | INT | 2: BHA 2 | 2J | Slide Drill f/10755.00 t/10783.00, TF 60G, w/WOB 40.00,Flow 680.00, Press 3950.00, Tq 22000.00, ROP 22.70, Diff 600.00, Temp 248.00
05/17/2021 | 18:20 | 18:30 | 0.17 | 10783 | 10803 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/10783.00 t/10803.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 120.00, Diff 600.00, Temp 248.00
05/17/2021 | 18:30 | 19:30 | 1 | 10803 | 10820 | 17 | INT | 2: BHA 2 | 2J | Slide Drill f/10803.00 t/10820.00, TF 60G, w/WOB 40.00,Flow 680.00, Press 3950.00, Tq 22000.00, ROP 17.00, Diff 600.00, Temp 248.00
05/17/2021 | 19:30 | 19:45 | 0.25 | 10820 | 10842 | 22 | INT | 2: BHA 2 | 2K | Rotary Drill f/10820.00 t/10842.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 88.00, Diff 600.00, Temp 248.00
05/17/2021 | 19:45 | 19:50 | 0.08 | 10842 | 10842 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 19:50 | 20:15 | 0.42 | 10842 | 10842 | 0 | INT | 2: BHA 2 | 5A | Circulate / Work Pipe
05/17/2021 | 20:15 | 20:45 | 0.5 | 10842 | 10936 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10842.00 t/10936.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 188.00, Diff 600.00, Temp 248.00
05/17/2021 | 20:45 | 20:50 | 0.08 | 10936 | 10936 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 20:50 | 21:15 | 0.42 | 10936 | 10936 | 0 | INT | 2: BHA 2 | 5A | Circulate / Work Pipe
05/17/2021 | 21:15 | 21:35 | 0.33 | 10936 | 11030 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10936.00 t/11030.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 282.00, Diff 600.00, Temp 248.00
05/17/2021 | 21:35 | 21:40 | 0.08 | 11030 | 11030 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 21:40 | 22:20 | 0.67 | 11030 | 11135 | 105 | INT | 2: BHA 2 | 2K | Rotary Drill f/11030.00 t/11135.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 157.50, Diff 600.00, Temp 248.00
05/17/2021 | 22:20 | 22:25 | 0.08 | 11135 | 11135 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/17/2021 | 22:25 | 23:15 | 0.83 | 11135 | 11155 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/11135.00 t/11155.00, TF 120G, w/WOB 40.00,Flow 680.00, Press 3950.00, Tq 22000.00, ROP 24.00, Diff 600.00, Temp 248.00
05/17/2021 | 23:15 | 23:40 | 0.42 | 11155 | 11217 | 62 | INT | 2: BHA 2 | 2K | Rotary Drill f/11155.00 t/11217.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 148.80, Diff 600.00, Temp 248.00
05/17/2021 | 23:40 | 24:00 | 0.33 | 11217 | 11217 | 0 | INT | 2: BHA 2 | 5A | Circulate / Work Pipe
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_18_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/18/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17000 |  |  | Well Cost($): |  | 92630
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11217 |  | 3033 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 19 | PV: | 6
End Depth (Usft): |  | 11893 |  | 11893 |  | OD (in): |  |  |  | 300: | 13 | YP: | 7
Total Drilled (Usft): |  | 676 |  | 8861 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): |  | 284 |  | 1236 | [5 empty] | 100: | 8 | Chlorides: | 45000
Rotary Drilled (Usft): |  | 392 |  | 7625 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 6.20
Drlg/Circ Hrs: |  | 19.28 / 2.88 |  | 74.58 / 16.37 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77:23
Slide Drilling Hrs: |  | 15.05 |  | 46.17 |  | SN: |  | 54682 |  | 10s Gel: | 3 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 4.23 |  | 28.42 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 82.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 92.60 / 18.87 |  | 268.33 / 26.77 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 102 |  | Grade In: |  | New
% Slide: |  | 42.01 |  | 13.95 |  | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
% Rotary: |  | 57.99 |  | 86.05 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
8 7/8 5.9 2.0F Slick -.016 |  |  |  | 8 | [5 empty] | 37.58 |  | 39.08
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 49.18
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 51.73
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 80.86
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 110.06
Crossover Sub |  |  |  | 6.5 | 2.375 |  |  |  |  | 2.35 |  | 112.41
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 186.82 |  | 299.23
Crossover Sub |  |  |  | 6.438 | 2.375 |  |  |  |  | 2.89 |  | 302.12
3 Stds 5 in HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 579.24
22 Stds 5 in DP |  |  |  | 5 | 2.563 |  |  |  |  | 2067.72 |  | 2646.96
Agitator |  |  |  | 6.812 | [5 empty] | 24.62 |  | 2671.58
2671.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800055 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.98 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11147 | 3.88 | 347.34 | 10958.75 | 1552.94 | 1098.6 | 0.83 |  | -90.69 | -258.93 | 0.07 |  | -12.37 | 94
11240 | 3.95 | 339.68 | 11051.54 | 1559.02 | 1096.8 | 0.57 |  | -86.21 | -264.4 | 0.08 |  | -8.24 | 93
11334 | 3.01 | 339.3 | 11145.36 | 1564.36 | 1094.8 | 1 |  | -178.78 | -269.51 | -1 |  | -0.4 | 94
11427 | 2.62 | 339.22 | 11238.25 | 1568.63 | 1093.18 | 0.42 |  | -179.46 | -273.61 | -0.42 |  | -0.09 | 93
11521 | 2.19 | 31.58 | 11332.18 | 1572.17 | 1093.36 | 2.29 |  | 126.47 | -275.89 | -0.46 |  | 55.7 | 94
11614 | 1.7 | 54.45 | 11425.13 | 1574.49 | 1095.41 | 0.98 |  | 133.35 | -275.98 | -0.53 |  | 24.59 | 93
11708 | 3.76 | 99.54 | 11519.02 | 1574.79 | 1099.59 | 3.01 |  | 70.25 | -273.13 | 2.19 |  | 47.97 | 94
11802 | 6.23 | 124.67 | 11612.67 | 1571.38 | 1106.83 | 3.45 |  | 54.52 | -265.52 | 2.63 |  | 26.73 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 35.06 | 36.25 | 80 | 193 | 680 | 3950 | 3350 | 0 | 315 | 285 | 210 | 22000 | 0
Run | 118.81 | 36.25 | 79.76 | 218 | 833.58 | 4073.66 | 3550.13 | 0 | 247.7 | 206.44 | 172.46 | 17396.83 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/18/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/18/2021 |  | 5 |  | 100 |  | 4 | 400
Extreme Orbitt RSS - Standby |  |  |  |  | 05/18/2021 |  | 17 |  | 9750 |  | 1 | 9750
Total | [11 empty] | 17000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/18/2021 | 00:00 | 00:15 | 0.25 | 11217 | 11217 | 0 | INT | 2: BHA 2 | 5A | Wash / Ream
05/18/2021 | 00:15 | 00:25 | 0.17 | 11217 | 11228 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/11217.00 t/11228.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 66.00, Diff 600.00
05/18/2021 | 00:25 | 01:15 | 0.83 | 11228 | 11244 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/11228.00 t/11244.00, TF 150G, w/WOB 40.00,Flow 680.00, Press 3950.00, Tq 22000.00, ROP 19.20, Diff 600.00
05/18/2021 | 01:15 | 01:25 | 0.17 | 11244 | 11264 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/11244.00 t/11264.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 120.00, Diff 600.00
05/18/2021 | 01:25 | 02:00 | 0.58 | 11264 | 11290 | 26 | INT | 2: BHA 2 | 2J | Slide Drill f/11264.00 t/11290.00, TF 150G, w/WOB 40.00,Flow 680.00, Press 3950.00, Tq 22000.00, ROP 44.57, Diff 600.00
05/18/2021 | 02:00 | 02:20 | 0.33 | 11290 | 11310 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/11290.00 t/11310.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 60.00, Diff 600.00
05/18/2021 | 02:20 | 02:25 | 0.08 | 11310 | 11310 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 02:25 | 02:35 | 0.17 | 11310 | 11327 | 17 | INT | 2: BHA 2 | 2K | Rotary Drill f/11310.00 t/11327.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 102.00, Diff 600.00
05/18/2021 | 02:35 | 04:45 | 2.17 | 11327 | 11365 | 38 | INT | 2: BHA 2 | 2J | Slide Drill f/11327.00 t/11365.00, TF 150.00G, w/WOB 40.00,Flow 680.00, Press 3950.00, Tq 22000.00, ROP 17.54, Diff 600.00
05/18/2021 | 04:45 | 05:20 | 0.58 | 11365 | 11404 | 39 | INT | 2: BHA 2 | 2K | Rotary Drill f/11365.00 t/11404.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 66.86, Diff 600.00
05/18/2021 | 05:20 | 05:25 | 0.08 | 11404 | 11404 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
05/18/2021 | 05:25 | 05:35 | 0.17 | 11404 | 11404 | 0 | INT | 2: BHA 2 | 5A | Circulate, work pipe
05/18/2021 | 05:35 | 05:45 | 0.17 | 11404 | 11419 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/11404.00 t/11419.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 90.00, Diff 600.00
05/18/2021 | 05:45 | 06:50 | 1.08 | 11419 | 11430 | 11 | INT | 2: BHA 2 | 2J | Slide Drill f/11419.00 t/11430.00, TF 130M, w/WOB 25,Flow 680.00, Press 3950.00, Tq 0, ROP 10.15, Diff 600.00, Temp 246.00
05/18/2021 | 06:50 | 07:15 | 0.42 | 11430 | 11468 | 38 | INT | 2: BHA 2 | 2K | Rotary Drill f/11430.00 t/11468.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 91.20, Diff 600.00, Temp 246.00
05/18/2021 | 07:15 | 09:10 | 1.92 | 11468 | 11488 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/11468.00 t/11488.00, TF 130.00M, w/WOB 25.00,Flow 680.00, Press 3950.00, Tq 0.00, ROP 10.43, Diff 600.00, Temp 246.00
05/18/2021 | 09:10 | 09:23 | 0.22 | 11488 | 11497 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/11488.00 t/11497.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 41.54, Diff 600.00, Temp 246.00
05/18/2021 | 09:23 | 09:33 | 0.17 | 11497 | 11497 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 09:33 | 09:43 | 0.17 | 11497 | 11510 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/11497.00 t/11510.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 78.00, Diff 600.00, Temp 246.00
05/18/2021 | 09:43 | 11:09 | 1.43 | 11510 | 11540 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/11510.00 t/11540.00, TF 130.00M, w/WOB 25.00,Flow 680.00, Press 3950.00, Tq 0.00, ROP 20.93, Diff 600.00, Temp 246.00
05/18/2021 | 11:09 | 11:50 | 0.68 | 11540 | 11540 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 11:50 | 12:18 | 0.47 | 11540 | 11591 | 51 | INT | 2: BHA 2 | 2K | Rotary Drill f/11540.00 t/11591.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 109.29, Diff 600.00, Temp 246.00
05/18/2021 | 12:18 | 12:28 | 0.17 | 11591 | 11591 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 12:28 | 12:48 | 0.33 | 11591 | 11660 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/11591.00 t/11660.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 207.00, Diff 600.00, Temp 246.00
05/18/2021 | 12:48 | 12:53 | 0.08 | 11660 | 11660 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 12:53 | 13:35 | 0.7 | 11660 | 11684 | 24 | INT | 2: BHA 2 | 2J | Slide Drill f/11660.00 t/11684.00, TF 150.00M, w/WOB 25.00,Flow 680.00, Press 3950.00, Tq 0.00, ROP 34.29, Diff 600.00, Temp 246.00
05/18/2021 | 13:35 | 14:42 | 1.12 | 11684 | 11684 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 14:42 | 14:47 | 0.08 | 11684 | 11700 | 16 | INT | 2: BHA 2 | 2K | Rotary Drill f/11684.00 t/11700.00, w/WOB 40.00,Flow 680.00, RPM 80.00, Press 3950.00, Tq 22000.00, ROP 192.00, Diff 600.00, Temp 246.00
05/18/2021 | 14:47 | 17:16 | 2.48 | 11700 | 11773 | 73 | INT | 2: BHA 2 | 2J | Slide Drill f/11700.00 t/11773.00, TF 140.00M, w/WOB 25.00,Flow 680.00, Press 3950.00, Tq 0.00, ROP 29.40, Diff 600.00, Temp 246.00
05/18/2021 | 17:16 | 17:21 | 0.08 | 11773 | 11778 | 5 | INT | 2: BHA 2 | 2K | Rotary Drill f/11773.00 t/11778.00, w/WOB 0.00,Flow 0.00, RPM 0.00, Press 0.00, Tq 0.00, ROP 60.00
05/18/2021 | 17:21 | 17:26 | 0.08 | 11778 | 11778 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 17:26 | 19:20 | 1.9 | 11778 | 11802 | 24 | INT | 2: BHA 2 | 2J | Slide Drill f/11778.00 t/11802.00, TF 20G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 12.63
05/18/2021 | 19:20 | 20:30 | 1.17 | 11802 | 11802 | 0 | INT | 2: BHA 2 | 23K | Wait Om Weather
05/18/2021 | 20:30 | 21:10 | 0.67 | 11802 | 11808 | 6 | INT | 2: BHA 2 | 2J | Slide Drill f/11802.00 t/11808.00, TF 20G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 9.00
05/18/2021 | 21:10 | 21:45 | 0.58 | 11808 | 11808 | 0 | INT | 2: BHA 2 | 8D | Work OnPumps
05/18/2021 | 21:45 | 22:32 | 0.78 | 11808 | 11815 | 7 | INT | 2: BHA 2 | 2J | Slide Drill f/11808.00 t/11815.00, TF 20G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 8.94
05/18/2021 | 22:32 | 23:15 | 0.72 | 11815 | 11872 | 57 | INT | 2: BHA 2 | 2K | Rotary Drill f/11815.00 t/11872.00, w/WOB 0.00,Flow 0.00, RPM 0.00, Press 0.00, Tq 0.00, ROP 79.53
05/18/2021 | 23:15 | 23:20 | 0.08 | 11872 | 11872 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
05/18/2021 | 23:20 | 23:50 | 0.5 | 11872 | 11881 | 9 | INT | 2: BHA 2 | 2J | Slide Drill f/11872.00 t/11881.00, TF 20G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 18.00
05/18/2021 | 23:50 | 24:00 | 0.17 | 11881 | 11893 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/11881.00 t/11893.00, w/WOB 0.00,Flow 0.00, RPM 0.00, Press 0.00, Tq 0.00, ROP 72.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_19_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 99880
|  |  |  | 24hr Summary: |  | Drilled intermediate
|  |  |  | 24hr Lookahead: |  | POOH, lay down tools, Standby for intermediate casing opps
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11893 |  | 3033 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 19 | PV: | 6
End Depth (Usft): |  | 11985 |  | 11985 |  | OD (in): |  |  |  | 300: | 13 | YP: | 7
Total Drilled (Usft): |  | 92 |  | 8953 |  | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): |  | 59 |  | 1295 | [5 empty] | 100: | 8 | Chlorides: | 45000
Rotary Drilled (Usft): |  | 33 |  | 7658 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 6.20
Drlg/Circ Hrs: |  | 3.83 / 2.58 |  | 78.42 / 18.95 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77:23
Slide Drilling Hrs: |  | 3.5 |  | 49.67 |  | SN: |  | 54682 |  | 10s Gel: | 3 | Weight (ppg): | 8.9
Rotary Drilling Hrs: |  | 0.33 |  | 28.75 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 82.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 99.00 / 16.86 |  | 266.37 / 26.07 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 18.83 |  | 120.83 |  | Grade In: |  | New
% Slide: |  | 64.13 |  | 14.46 |  | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
% Rotary: |  | 35.87 |  | 85.54 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | [5 empty] | 1.5 |  | 1.5
8 7/8 5.9 2.0F Slick -.016 |  |  |  | 8 | [5 empty] | 37.58 |  | 39.08
NMPC |  |  |  | 8.062 | 3.25 |  |  |  |  | 10.1 |  | 49.18
UBHO |  |  |  | 7.75 | 3 |  |  |  |  | 2.55 |  | 51.73
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.13 |  | 80.86
NMDC |  |  |  | 7.938 | 3.25 |  |  |  |  | 29.2 |  | 110.06
Crossover Sub |  |  |  | 6.5 | 2.375 |  |  |  |  | 2.35 |  | 112.41
2 Stds 6.5 in DC |  |  |  | 6.5 | 2.75 |  |  |  |  | 186.82 |  | 299.23
Crossover Sub |  |  |  | 6.438 | 2.375 |  |  |  |  | 2.89 |  | 302.12
3 Stds 5 in HWDP |  |  |  | 5 | 3 |  |  |  |  | 277.12 |  | 579.24
22 Stds 5 in DP |  |  |  | 5 | 2.563 |  |  |  |  | 2067.72 |  | 2646.96
Agitator |  |  |  | 6.812 | [5 empty] | 24.62 |  | 2671.58
2671.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800055 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.98 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11896 | 5.42 | 127.01 | 11706.18 | 1565.8 | 1114.57 | 0.9 |  | 164.82 | -256.06 | -0.86 |  | 2.49 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 24 | 0 | 0 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 114.17 | 36.25 | 79.76 | 218 | 833.58 | 4073.66 | 3550.13 | 0 | 247.7 | 206.44 | 172.46 | 17396.83 | 0
Comments
Plan 2
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/19/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/19/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/19/2021 | 00:00 | 00:20 | 0.33 | 11893 | 11926 | 33 | INT | 2: BHA 2 | 2K | Rotary Drill f/11893.00 t/11926.00, w/WOB 0.00,Flow 0.00, RPM 0.00, Press 0.00, Tq 0.00, ROP 99.00
05/19/2021 | 00:20 | 00:25 | 0.08 | 11926 | 11926 | 0 | INT | 2: BHA 2 | 5A | Check Shot
05/19/2021 | 00:25 | 00:30 | 0.08 | 11926 | 11926 | 0 | INT | 2: BHA 2 | 5A | Work On Pumps
05/19/2021 | 00:30 | 02:30 | 2 | 11926 | 11966 | 40 | CRV | 2: BHA 2 | 2J | Slide Drill f/11926.00 t/11966.00, TF 0G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 20.00
05/19/2021 | 02:30 | 02:35 | 0.08 | 11966 | 11966 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
05/19/2021 | 02:35 | 04:00 | 1.42 | 11966 | 11982 | 16 | CRV | 2: BHA 2 | 2J | Slide Drill f/11966.00 t/11982.00, TF 0G, w/WOB 0.00,Flow 0.00, Press 0.00, Tq 0.00, ROP 11.29
05/19/2021 | 04:00 | 04:45 | 0.75 | 11982 | 11982 | 0 | CRV | 2: BHA 2 | 24A | Change out rotating head
05/19/2021 | 04:45 | 04:50 | 0.08 | 11982 | 11985 | 3 | CRV | 2: BHA 2 | 2J | Slide Drill f/11982.00 t/11985.00, TF 0.00G, w/WOB 25.00,Flow 680.00, Press 3950.00, Tq 0.00, ROP 36.00, Diff 600.00, Temp 246.00
05/19/2021 | 04:50 | 07:10 | 2.33 | 11985 | 11985 | 0 | CRV | 2: BHA 2 | 5A | Prepare to POOH to lay down tools for intermediate casing opps.
05/19/2021 | 07:10 | 17:50 | 10.67 | 11985 | 11985 | 0 | CRV | 2: BHA 2 | 6B | POOH laying down 5 drill pipe
05/19/2021 | 17:50 | 18:50 | 1 | 11985 | 11985 | 0 | CRV | 2: BHA 2 | 6P | Lay down BHA #2
05/19/2021 | 18:50 | 24:00 | 5.17 | 11985 | 11985 | 0 | CRV |  | 24B | Standby for intermediate casing opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_20_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4200 |  |  | Well Cost($): |  | 104080
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11985 |  |  |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 19 | PV: | 6
End Depth (Usft): |  | 11985 |  | 11985 |  | OD (in): |  |  |  | 300: | 13 | YP: | 7
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 12 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 8 | Chlorides: | 45000
Rotary Drilled (Usft): | [9 empty] | 6: | 4 | % Sand/Solids: | 0.00 / 6.20
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 77:23
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 3 | Weight (ppg): | 8.9
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 82.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Paul Oates |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 36.25 | 79.76 | 218 | 833.58 | 4073.66 | 3550.13 | 0 | 247.7 | 206.44 | 172.46 | 17396.83 | 0
Comments
Plan 2
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
STBY |  |  |  |  | 05/20/2021 |  | 2 |  | 3800 |  | 1 | 3800
Perdiem |  |  |  |  | 05/20/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 4200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/20/2021 | 00:00 | 24:00 | 24 | 11985 | 11985 | 0 | CRV |  | 24B | Casing Opps.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_21_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/21/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 16850 |  |  | Well Cost($): |  | 120930
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11985 |  | 11985 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 42 | PV: | 16
End Depth (Usft): |  | 12293 |  | 12293 |  | OD (in): |  |  |  | 300: | 26 | YP: | 10
Total Drilled (Usft): |  | 308 |  | 308 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 50
Slide Drilled (Usft): |  | 298 |  | 298 | [5 empty] | 100: | 16 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 10 |  | 10 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 11.00
Drlg/Circ Hrs: |  | 5.55 / 3.98 |  | 5.55 / 3.98 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 74:26
Slide Drilling Hrs: |  | 5.37 |  | 5.37 |  | SN: |  | 13590860 |  | 10s Gel: | 12 | Weight (ppg): | 9.8
Rotary Drilling Hrs: |  | 0.18 |  | 0.18 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.2 / 82.00 | Fluid Loss / Mud Type: | 8 / OBM
ROP Rot/Slide (Usft/hr): |  | 54.55 / 55.53 |  | 54.55 / 55.53 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 23 |  | 23 |  | Grade In: |  | New
% Slide: |  | 96.75 |  | 96.75 |  | Grade Out:
% Rotary: |  | 3.25 |  | 3.25 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 11.7 2.0 Slick HS88 .015 |  |  |  | 5 | 2 |  |  |  |  | 33.06 |  | 33.81
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.91
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.35
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.42
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.61
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.6
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.38
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.95
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.02
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.34
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.5
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2452.32 |  | 2788.82
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.72 |  | 2812.54
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3116.63 |  | 5929.17
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 21.93 |  | 5951.1
5951.1
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250014 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.05 |  | 2 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11990 | 6.14 | 135.25 | 11799.74 | 1559.78 | 1121.44 | 1.56 |  | 39.37 | -246.92 | 1.27 |  | 9.28 | 75
12085 | 15.62 | 145.67 | 11892.93 | 1545.57 | 1132.26 | 10.15 |  | 16.9 | -229.32 | 9.98 |  | 10.97 | 95
12181 | 23.96 | 139.68 | 11983.19 | 1519.99 | 1152.2 | 8.93 |  | -16.52 | -197.28 | 8.69 |  | -6.24 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 55.5 | 18 | 30 | 204 | 195 | 4933.33 | 4300 | 0 | 310 | 250 | 190 | 19000 | 0
Run | 55.5 | 18 | 30 | 204 | 195 | 4933.33 | 4300 | 0 | 310 | 250 | 190 | 19000 | 0
Comments
Plan 6
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/21/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/21/2021 |  | 5 |  | 100 |  | 4 | 400
5.5 Premium Motor Reline |  |  |  |  | 05/21/2021 | PPM250014 | 9 |  | 9000 |  | 1 | 9000
Real Time Survey Management |  |  |  |  | 05/21/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 16850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/21/2021 | 00:00 | 01:00 | 1 | 11985 | 11985 | 0 | CRV2 | 3: BHA 3 | 6O | P/U BHA
05/21/2021 | 01:00 | 12:15 | 11.25 | 11985 | 11985 | 0 | CRV2 | 3: BHA 3 | 6J | P/U 4.5 DP to 11680
05/21/2021 | 12:15 | 13:25 | 1.17 | 11985 | 11985 | 0 | CRV2 | 3: BHA 3 | 24A | Slip and cut drill line
05/21/2021 | 13:25 | 13:50 | 0.42 | 11985 | 11985 | 0 | CRV2 | 3: BHA 3 | 6J | P/U 4.5 DP to 11866
05/21/2021 | 13:50 | 15:55 | 2.08 | 11985 | 11985 | 0 | CRV2 | 3: BHA 3 | 5A | Circulate
05/21/2021 | 15:55 | 16:12 | 0.28 | 11985 | 11985 | 0 | CRV2 | 3: BHA 3 | 5A | Drill out float and shoe track
05/21/2021 | 16:12 | 16:23 | 0.18 | 11985 | 11995 | 10 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11985.00 t/11995.00, w/WOB 18,Flow 195, RPM 30, Press 2600, Tq 19000, ROP 54.55, Diff 300.00
05/21/2021 | 16:23 | 16:49 | 0.43 | 11995 | 11995 | 0 | CRV2 | 3: BHA 3 | 5A | Circulate Clean Up
05/21/2021 | 16:49 | 17:27 | 0.63 | 11995 | 11995 | 0 | CRV2 | 3: BHA 3 | 15D | FIT
05/21/2021 | 17:27 | 19:39 | 2.2 | 11995 | 12057 | 62 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11995.00 t/12057.00, TF 0.00G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 28.18, Diff 700.00, Temp 284.00
05/21/2021 | 19:39 | 19:47 | 0.13 | 12057 | 12057 | 0 | CRV2 | 3: BHA 3 | 5A | 2J: Slide Drilling @11990
05/21/2021 | 19:47 | 20:35 | 0.8 | 12057 | 12102 | 45 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12057.00 t/12102.00, TF -20G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 56.25, Diff 700.00, Temp 284.00
05/21/2021 | 20:35 | 20:50 | 0.25 | 12102 | 12102 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection @ 12053
05/21/2021 | 20:50 | 21:37 | 0.78 | 12102 | 12152 | 50 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12102.00 t/12152.00, TF -45G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 63.83, Diff 700.00, Temp 284.00
05/21/2021 | 21:37 | 22:05 | 0.47 | 12152 | 12152 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection @12085
05/21/2021 | 22:05 | 23:05 | 1 | 12152 | 12248 | 96 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12152.00 t/12248.00, TF -45G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 96.00, Diff 700.00, Temp 284.00
05/21/2021 | 23:05 | 23:25 | 0.33 | 12248 | 12248 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection @12181
05/21/2021 | 23:25 | 24:00 | 0.58 | 12248 | 12293 | 45 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12248.00 t/12293.00, TF -30G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 77.14, Diff 700.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_22_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/22/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7850 |  |  | Well Cost($): |  | 128780
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12293 |  | 11985 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 12540 |  | 12540 |  | OD (in): |  |  |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 247 |  | 555 |  | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 53
Slide Drilled (Usft): |  | 247 |  | 545 | [5 empty] | 100: | 17 | Chlorides: | 57000
Rotary Drilled (Usft): |  |  |  | 10 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 14.80
Drlg/Circ Hrs: |  | 4.37 / 13.97 |  | 9.92 / 17.95 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 4.37 |  | 9.73 |  | SN: |  | 13590860 |  | 10s Gel: |  | Weight (ppg): | 11
Rotary Drilling Hrs: |  |  |  | 0.18 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.2 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 56.56 |  | 54.55 / 55.99 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 47 |  | Grade In: |  | New
% Slide: |  | 100 |  | 98.2 |  | Grade Out:
% Rotary: |  |  |  | 1.8 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 11.7 2.0 Slick HS88 .015 |  |  |  | 5 | 2 |  |  |  |  | 33.06 |  | 33.81
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.91
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.35
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.42
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.61
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.6
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.38
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.95
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.02
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.34
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.5
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2452.32 |  | 2788.82
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.72 |  | 2812.54
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3116.63 |  | 5929.17
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 21.93 |  | 5951.1
5951.1
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250014 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.05 |  | 2 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12244 | 24.85 | 149.89 | 12040.59 | 1498.78 | 1167.12 | 6.84 |  | 82.77 | -171.89 | 1.41 |  | 16.21 | 63
12339 | 32.89 | 150.78 | 12123.71 | 1458.93 | 1189.76 | 8.48 |  | 3.45 | -128.13 | 8.46 |  | 0.94 | 95
12436 | 42.09 | 141.13 | 12200.66 | 1410.49 | 1223.12 | 11.23 |  | -36.49 | -70.67 | 9.48 |  | -9.95 | 97
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 56.56 | 18 | 0 | 174 | 195 | 5400 | 4700 | 0 | 310 | 250 | 190 | 0 | 0
Run | 55.97 | 18 | 30 | 204 | 195 | 5145.45 | 4481.82 | 0 | 310 | 250 | 190 | 19000 | 0
Comments
Plan 6
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/22/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/22/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 05/22/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 7850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/22/2021 | 00:00 | 00:55 | 0.92 | 12293 | 12342 | 49 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12293.00 t/12342.00, TF -30.00G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 53.45, Diff 700.00, Temp 284.00
05/22/2021 | 00:55 | 01:06 | 0.18 | 12342 | 12342 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
05/22/2021 | 01:06 | 01:15 | 0.15 | 12342 | 12350 | 8 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12342.00 t/12350.00, TF -30.00G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 53.33, Diff 700.00, Temp 284.00
05/22/2021 | 01:15 | 01:25 | 0.17 | 12350 | 12350 | 0 | CRV2 | 3: BHA 3 | 8D | Working on Mud Pump
05/22/2021 | 01:25 | 02:45 | 1.33 | 12350 | 12437 | 87 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12350.00 t/12437.00, TF -30.00G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 65.25, Diff 700.00, Temp 284.00
05/22/2021 | 02:45 | 03:00 | 0.25 | 12437 | 12437 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection @12370
05/22/2021 | 03:00 | 04:05 | 1.08 | 12437 | 12523 | 86 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12437.00 t/12523.00, TF 0.00G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 79.38, Diff 700.00, Temp 284.00
05/22/2021 | 04:05 | 05:05 | 1 | 12523 | 12523 | 0 | CRV2 | 3: BHA 3 | 5D | Circulate Out Gas
05/22/2021 | 05:05 | 05:25 | 0.33 | 12523 | 12533 | 10 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12523.00 t/12533.00, TF 0.00G, w/WOB 18.00,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 30.00, Diff 700.00, Temp 284.00
05/22/2021 | 05:25 | 05:35 | 0.17 | 12533 | 12533 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
05/22/2021 | 05:35 | 06:08 | 0.55 | 12533 | 12540 | 7 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/12533.00 t/12540.00, TF 0G, w/WOB 18,Flow 195.00, Press 5400.00, Tq 19000.00, ROP 12.73, Diff 700.00, Temp 284.00
05/22/2021 | 06:08 | 13:00 | 6.87 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 5D | Circulate, weight up mud to 11.0 ppg.
05/22/2021 | 13:00 | 13:30 | 0.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6B | POOH F/12540 T/ 12057
05/22/2021 | 13:30 | 14:30 | 1 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 5A | Circulate Bottoms Up
05/22/2021 | 14:30 | 15:00 | 0.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6B | POOH F/12057 T/11700
05/22/2021 | 15:00 | 17:00 | 2 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 5A | Spot WT Pill
05/22/2021 | 17:00 | 18:00 | 1 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6B | POOH F/11700 T/8600
05/22/2021 | 18:00 | 19:30 | 1.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 24A | Monitor Well After Pumping Slug
05/22/2021 | 19:30 | 20:00 | 0.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6B | POOH F/8600 T/7160
05/22/2021 | 20:00 | 20:30 | 0.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 24A | Monitor Well Due To Not Taking Proper Fill
05/22/2021 | 20:30 | 21:30 | 1 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6A | TIH F/7160 T/8600
05/22/2021 | 21:30 | 24:00 | 2.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 5A | Circulating Weighting Up 13.0 ppg / Spot Mud Cap Pump Slug
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_23_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/23/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17250 |  |  | Well Cost($): |  | 146030
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12540 |  | 11985 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 12540 |  | 12540 |  | OD (in): |  |  |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  |  |  | 555 |  | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 53
Slide Drilled (Usft): |  |  |  | 545 | [5 empty] | 100: | 17 | Chlorides: | 57000
Rotary Drilled (Usft): |  |  |  | 10 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 14.80
Drlg/Circ Hrs: |  |  |  | 9.92 / 17.95 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 70:30
Slide Drilling Hrs: |  |  |  | 9.73 |  | SN: |  | 13590860 |  | 10s Gel: |  | Weight (ppg): | 11
Rotary Drilling Hrs: |  |  |  | 0.18 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.2 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 54.55 / 55.99 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 8 |  | 55 |  | Grade In: |  | New
% Slide: |  |  |  | 98.2 |  | Grade Out:
% Rotary: |  |  |  | 1.8 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 11.7 2.0 Slick HS88 .015 |  |  |  | 5 | 2 |  |  |  |  | 33.06 |  | 33.81
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.91
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.35
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.42
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.61
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.6
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.38
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.95
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.02
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.34
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.5
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2452.32 |  | 2788.82
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.72 |  | 2812.54
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3116.63 |  | 5929.17
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 21.93 |  | 5951.1
5951.1
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250014 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 4.05 |  | 2 |  | 0.89 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 10000 | 0 | 214 | 240 | 2800 | 2700 | 0 | 205 | 205 | 205 | 0 | 0
Run | 55.97 | 10000 | 0 | 214 | 240 | 2800 | 2700 | 0 | 205 | 205 | 205 | 0 | 0
Comments
Plan 6
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/23/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/23/2021 |  | 5 |  | 100 |  | 4 | 400
5.5 Premium Motor Stator Reline |  |  |  |  | 05/23/2021 | PPM250014 | 12 |  | 9000 |  | 1 | 9000
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 05/23/2021 |  | 15 |  | 1000 |  | 1 | 1000
Total | [11 empty] | 17250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/23/2021 | 00:00 | 06:30 | 6.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6B | POOH F/8600 T/BHA
05/23/2021 | 06:30 | 08:00 | 1.5 | 12540 | 12540 | 0 | CRV2 | 3: BHA 3 | 6P | Lay down BHA
05/23/2021 | 08:00 | 24:00 | 16 | 12540 | 12540 | 0 | CRV2 |  | 24A | Rig Service, wait on orders
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_24_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 14 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/24/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 153280
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11992 |  | 11992 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 12229 |  | 12229 |  | OD (in): |  |  |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 237 |  | 237 |  | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 53
Slide Drilled (Usft): |  | 237 |  | 237 | [5 empty] | 100: | 17 | Chlorides: | 57000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 14.80
Drlg/Circ Hrs: |  | 15.63 / 6.43 |  | 15.63 / 6.43 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 15.63 |  | 15.63 |  | SN: |  | 13090615 |  | 10s Gel: |  | Weight (ppg): | 11
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 2.2 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 15.16 |  | 0.00 / 15.16 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 23 |  | 23 |  | Grade In: |  | New
% Slide: |  | 100 |  | 100 |  | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
7/8 3.8 2.5 Slick HS88 -.001 |  |  |  | 5 | 2 |  |  |  |  | 26.22 |  | 26.97
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 29.07
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 38.51
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 41.58
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 71.77
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 81.76
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 112.54
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 130.11
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 133.18
28 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2651.32 |  | 2784.5
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.72 |  | 2808.22
2808.22
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475015 |  | PDCI |  | 7/8 3.8 |  | 7/8 | 4.11 |  | 2.5 |  | 0.52 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11990 | 6.14 | 135.25 | 11799.74 | 1559.78 | 1121.44 | 1.56 |  | 39.37 | -246.92 | 1.27 |  | 9.28 | 75
12085 | 15.62 | 145.67 | 11892.93 | 1545.57 | 1132.26 | 10.15 |  | 16.9 | -229.32 | 9.98 |  | 10.97 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 22.12 | 10000 | 0 | 125 | 240 | 2775 | 2675 | 0 | 205 | 205 | 205 | 0 | 0
Run | 22.12 | 10000 | 0 | 125 | 240 | 2780 | 2680 | 0 | 205 | 205 | 205 | 0 | 0
Comments
Plan 7 STO 1
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/24/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/24/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/24/2021 | 00:00 | 01:00 | 1 | 11992 | 11992 | 0 | ST | 4: BHA 4 | 6O | Slide Drill f/11992.00 t/12001.00, TF -50G, w/WOB 10000.00,Flow 240.00, Press 2800.00, Tq 0.00, ROP 1.52, Diff 100.00, Temp 242.00
05/24/2021 | 01:00 | 05:55 | 4.92 | 11992 | 12001 | 9 | ST | 4: BHA 4 | 2J
05/24/2021 | 05:55 | 06:40 | 0.75 | 12001 | 12001 | 0 | ST | 4: BHA 4 | 5A | Work trough
05/24/2021 | 06:40 | 10:20 | 3.67 | 12001 | 12006 | 5 | ST | 4: BHA 4 | 2J | Slide Drill f/12001.00 t/12006.00, TF -50G, w/WOB 10000.00,Flow 240.00, Press 2800.00, Tq 0.00, ROP 1.36, Diff 100.00, Temp 242.00
05/24/2021 | 10:20 | 11:27 | 1.12 | 12006 | 12020 | 14 | ST | 4: BHA 4 | 2J | Slide Drill f/12006.00 t/12020.00, TF -50G, w/WOB 10000.00,Flow 240.00, Press 2800.00, Tq 0.00, ROP 12.54, Diff 100.00, Temp 242.00
05/24/2021 | 11:27 | 12:40 | 1.22 | 12020 | 12020 | 0 | ST | 4: BHA 4 | 5A | Confirmed we were in original hole / wait on orders
05/24/2021 | 12:40 | 13:36 | 0.93 | 12020 | 12020 | 0 | ST | 4: BHA 4 | 6A | Trip in hole 12195
05/24/2021 | 13:36 | 18:04 | 4.47 | 12020 | 12020 | 0 | ST | 4: BHA 4 | 5A | Trough F/12195 T/12224
05/24/2021 | 18:04 | 24:00 | 5.93 | 12020 | 12229 | 209 | ST | 4: BHA 4 | 2J | Slide Drill f/1225.00 t/12229.00, TF 135.00G, w/WOB 10000.00,Flow 240.00, Press 2700, Tq 0.00, ROP 35.22, Diff 100.00, Temp 242.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_25_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 15 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/25/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 160530
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12229 |  | 11992 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 12305 |  | 12305 |  | OD (in): |  |  |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 76 |  | 313 |  | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 53
Slide Drilled (Usft): |  | 76 |  | 313 | [5 empty] | 100: | 17 | Chlorides: | 57000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 14.80
Drlg/Circ Hrs: |  | 17.33 / 2.77 |  | 32.97 / 9.20 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 17.33 |  | 32.97 |  | SN: |  | 13090615 |  | 10s Gel: |  | Weight (ppg): | 11
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 2.2 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 4.38 |  | 0.00 / 9.49 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 47 |  | Grade In: |  | New
% Slide: |  | 100 |  | 100 |  | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
7/8 3.8 2.5 Slick HS88 -.001 |  |  |  | 5 | 2 |  |  |  |  | 26.22 |  | 26.97
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 29.07
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 38.51
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 41.58
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 71.77
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 81.76
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 112.54
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 130.11
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 133.18
28 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2651.32 |  | 2784.5
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.72 |  | 2808.22
2808.22
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475015 |  | PDCI |  | 7/8 3.8 |  | 7/8 | 4.11 |  | 2.5 |  | 0.52 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12181 | 23.96 | 139.68 | 11983.19 | 1519.99 | 1152.2 | 8.93 |  | -16.52 | -197.28 | 8.69 |  | -6.24 | 96
12244 | 24.85 | 149.89 | 12040.59 | 1498.78 | 1167.12 | 6.84 |  | 82.77 | -171.89 | 1.41 |  | 16.21 | 63
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 4.38 | 10000 | 0 | 125 | 240 | 2700 | 2600 | 0 | 205 | 205 | 205 | 0 | 0
Run | 9.49 | 10000 | 0 | 125 | 240 | 2733.33 | 2633.33 | 0 | 205 | 205 | 205 | 0 | 0
Comments
Plan 7 STO 1
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/25/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/25/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/25/2021 | 00:00 | 08:50 | 8.83 | 12229 | 12235 | 6 | ST | 4: BHA 4 | 2J | Slide Drill f/12229.00 t/12235.00, TF 135.00G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 0.68, Diff 100.00, Temp 242.00 / Side Track
05/25/2021 | 08:50 | 10:28 | 1.63 | 12235 | 12240 | 5 | ST | 4: BHA 4 | 2J | Slide Drill f/12235.00 t/12240.00, TF 135G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 3.06, Diff 100.00, Temp 248.00
05/25/2021 | 10:28 | 11:15 | 0.78 | 12240 | 12245 | 5 | ST | 4: BHA 4 | 2J | Slide Drill f/12240.00 t/12245.00, TF 135G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 6.38, Diff 100.00, Temp 248.00
05/25/2021 | 11:15 | 12:21 | 1.1 | 12245 | 12255 | 10 | ST | 4: BHA 4 | 2J | Slide Drill f/12245.00 t/12255.00, TF 60G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 9.09, Diff 100.00, Temp 248.00
05/25/2021 | 12:21 | 13:07 | 0.77 | 12255 | 12273 | 18 | ST | 4: BHA 4 | 2J | Slide Drill f/12255.00 t/12273.00, TF 20G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 23.48, Diff 100.00, Temp 248.00
05/25/2021 | 13:07 | 13:17 | 0.17 | 12273 | 12273 | 0 | ST | 4: BHA 4 | 5A | Survey & Connection
05/25/2021 | 13:17 | 15:40 | 2.38 | 12273 | 12293 | 20 | ST | 4: BHA 4 | 2J | Slide Drill f/12273.00 t/12293.00, TF 0G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 8.39, Diff 100.00, Temp 248.00
05/25/2021 | 15:40 | 16:16 | 0.6 | 12293 | 12293 | 0 | ST | 4: BHA 4 | 5A | Waiting on Orders
05/25/2021 | 16:16 | 18:06 | 1.83 | 12293 | 12305 | 12 | ST | 4: BHA 4 | 2J | Slide Drill f/12293.00 t/12305.00, TF 0G, w/WOB 10000.00,Flow 240.00, Press 2700.00, Tq 0.00, ROP 6.55, Diff 100.00, Temp 248.00
05/25/2021 | 18:06 | 18:18 | 0.2 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 10D | Survey @ 12244
05/25/2021 | 18:18 | 19:00 | 0.7 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 6B | POOH F/12305 T/11974
05/25/2021 | 19:00 | 21:00 | 2 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 5A | Circulate Bottoms Up / Spot Mud Cap
05/25/2021 | 21:00 | 22:30 | 1.5 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 6B | POOH F/11974 T/10305
05/25/2021 | 22:30 | 23:00 | 0.5 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 24A | Take Flow Check
05/25/2021 | 23:00 | 24:00 | 1 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 6B | POOH F/10305 T/7920
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_26_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/26/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18650 |  |  | Well Cost($): |  | 179180
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12305 |  | 12305 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 12725 |  | 12725 |  | OD (in): |  |  |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 420 |  | 420 |  | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 53
Slide Drilled (Usft): |  | 371 |  | 371 | [5 empty] | 100: | 17 | Chlorides: | 57000
Rotary Drilled (Usft): |  | 49 |  | 49 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 14.80
Drlg/Circ Hrs: |  | 7.93 / 3.25 |  | 7.93 / 3.25 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 70:30
Slide Drilling Hrs: |  | 6.83 |  | 6.83 |  | SN: |  | 13090615 |  | 10s Gel: |  | Weight (ppg): | 11
Rotary Drilling Hrs: |  | 1.1 |  | 1.1 |  | Bit # |  | 3 |  | PH / Temp(F) | 2.2 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 44.55 / 54.29 |  | 44.55 / 54.29 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 19 |  | 19 |  | Grade In: |  | New
% Slide: |  | 88.33 |  | 88.33 |  | Grade Out:
% Rotary: |  | 11.67 |  | 11.67 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
7/8 3.8 2.5 Slick HS88 -.001 |  |  |  | 5 | 2 |  |  |  |  | 26.22 |  | 26.97
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 29.07
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 38.51
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 41.58
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 71.77
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 81.76
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 112.54
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 130.11
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 133.18
28 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2651.32 |  | 2784.5
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.72 |  | 2808.22
2808.22
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR475015 |  | PDCI |  | 7/8 3.8 |  | 7/8 | 4.11 |  | 2.5 |  | 0.52 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12339 | 32.89 | 150.78 | 12123.71 | 1458.93 | 1189.76 | 8.48 |  | 3.45 | -128.13 | 8.46 |  | 0.94 | 95
12436 | 42.09 | 141.13 | 12200.66 | 1410.49 | 1223.12 | 11.23 |  | -36.49 | -70.67 | 9.48 |  | -9.95 | 97
12532 | 55.51 | 135.63 | 12263.78 | 1356.89 | 1271.22 | 14.62 |  | -19.01 | 1.07 | 13.98 |  | -5.73 | 96
12626 | 69.86 | 133.11 | 12306.8 | 1298.73 | 1330.84 | 15.45 |  | -9.48 | 84.34 | 15.27 |  | -2.68 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 10000 | 0 | 163 | 240 | 2700 | 2600 | 0 | 205 | 205 | 205 | 0 | 0
Run | 9.49 | 10000 | 0 | 163 | 240 | 2733.33 | 2633.33 | 0 | 205 | 205 | 205 | 0 | 0
Comments
Plan 7 STO 1
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/26/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/26/2021 |  | 5 |  | 100 |  | 4 | 400
5.5 Premium Motor Stator Reline |  |  |  |  | 05/26/2021 | PPM250014 | 12 |  | 9000 |  | 1 | 9000
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 05/26/2021 |  | 15 |  | 1000 |  | 1 | 1000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 05/26/2021 |  | 11 |  | 800 |  | 1 | 800
Real Time Survey Management |  |  |  |  | 05/26/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 18650
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/26/2021 | 00:00 | 01:30 | 1.5 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 6B | POOH F/7920 T/2963
05/26/2021 | 01:30 | 02:00 | 0.5 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 24A | Remove Rotating Head And Install Trip Nipple
05/26/2021 | 02:00 | 03:00 | 1 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 6B | POOH F/2963 T/Surface
05/26/2021 | 03:00 | 04:00 | 1 | 12305 | 12305 | 0 | ST | 4: BHA 4 | 6P | L/D BHA #4
05/26/2021 | 04:00 | 05:00 | 1 | 12305 | 12305 | 0 | ST | 5: BHA 5 | 6O | P/U BHA #5
05/26/2021 | 05:00 | 12:16 | 7.27 | 12305 | 12305 | 0 | ST | 5: BHA 5 | 6A | TIH to 12018
05/26/2021 | 12:16 | 14:10 | 1.9 | 12305 | 12305 | 0 | ST | 5: BHA 5 | 5A | Circulate out mud cap
05/26/2021 | 14:10 | 14:30 | 0.33 | 12305 | 12305 | 0 | ST | 5: BHA 5 | 5A | Wash from 12018 to 12190
05/26/2021 | 14:30 | 14:56 | 0.43 | 12305 | 12305 | 0 | ST | 5: BHA 5 | 5A | Orient tool face @ 140R prepare to trip through side track
05/26/2021 | 14:56 | 15:20 | 0.4 | 12305 | 12305 | 0 | ST | 5: BHA 5 | 6A | TIH to 12305
05/26/2021 | 15:20 | 15:51 | 0.52 | 12305 | 12311 | 6 | ST | 5: BHA 5 | 2J | Slide Drill f/12305.00 t/12311.00, TF -40G, w/WOB 30,Flow 345, Press 5000, Tq 0, ROP 11.61, Diff 550.00
05/26/2021 | 15:51 | 16:00 | 0.15 | 12311 | 12311 | 0 | ST | 5: BHA 5 | 24A | Connection
05/26/2021 | 16:00 | 17:23 | 1.38 | 12311 | 12375 | 64 | ST | 5: BHA 5 | 2J | Slide Drill f/12311.00 t/12375.00, TF -30G, w/WOB 30,Flow 345, Press 5000, Tq 0, ROP 46.27, Diff 550.00
05/26/2021 | 17:23 | 17:33 | 0.17 | 12375 | 12375 | 0 | ST | 5: BHA 5 | 5A | Check Shot @ 12308
05/26/2021 | 17:33 | 18:12 | 0.65 | 12375 | 12406 | 31 | ST | 5: BHA 5 | 2J | Slide Drill f/12375.00 t/12406.00, TF 0G, w/WOB 30.00,Flow 345.00, Press 5000.00, Tq 0.00, ROP 47.69, Diff 550.00, Temp 258.00
05/26/2021 | 18:12 | 18:22 | 0.17 | 12406 | 12406 | 0 | ST | 5: BHA 5 | 5A | Survey & Connection
05/26/2021 | 18:22 | 20:05 | 1.72 | 12406 | 12503 | 97 | ST | 5: BHA 5 | 2J | Slide Drill f/12406.00 t/12503.00, TF -30G, w/WOB 30.00,Flow 345.00, Press 5000.00, Tq 0.00, ROP 56.50, Diff 550.00, Temp 258.00
05/26/2021 | 20:05 | 20:10 | 0.08 | 12503 | 12503 | 0 | ST | 5: BHA 5 | 5A | Survey & Connection
05/26/2021 | 20:10 | 21:30 | 1.33 | 12503 | 12599 | 96 | ST | 5: BHA 5 | 2J | Slide Drill f/12503.00 t/12599.00, TF -30G, w/WOB 30.00,Flow 345.00, Press 5000.00, Tq 0.00, ROP 72.00, Diff 550.00, Temp 258.00
05/26/2021 | 21:30 | 21:40 | 0.17 | 12599 | 12599 | 0 | ST | 5: BHA 5 | 5A | Survey & Connection
05/26/2021 | 21:40 | 22:10 | 0.5 | 12599 | 12631 | 32 | ST | 5: BHA 5 | 2J | Slide Drill f/12599.00 t/12631.00, TF -30G, w/WOB 30.00,Flow 345.00, Press 5000.00, Tq 0.00, ROP 64.00, Diff 550.00, Temp 258.00
05/26/2021 | 22:10 | 22:20 | 0.17 | 12631 | 12648 | 17 | ST | 5: BHA 5 | 2K | Rotary Drill f/12631.00 t/12648.00, w/WOB 30.00,Flow 345.00, RPM 0.00, Press 5000.00, Tq 0.00, ROP 102.00, Diff 550.00, Temp 258.00
05/26/2021 | 22:20 | 23:04 | 0.73 | 12648 | 12693 | 45 | ST | 5: BHA 5 | 2J | Slide Drill f/12648.00 t/12693.00, TF -30G, w/WOB 30.00,Flow 345.00, Press 5000.00, Tq 0.00, ROP 61.36, Diff 550.00, Temp 258.00
05/26/2021 | 23:04 | 24:00 | 0.93 | 12693 | 12725 | 32 | ST | 5: BHA 5 | 2K | Rotary Drill f/12693.00 t/12725.00, w/WOB 30.00,Flow 345.00, RPM 0.00, Press 5000.00, Tq 0.00, ROP 34.29, Diff 550.00, Temp 258.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_27_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 17 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/27/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18050 |  |  | Well Cost($): |  | 197230
|  |  |  | 24hr Summary: |  | Build curve with 2.25? motor, POOH f/ Lateral assembly, TIH
|  |  |  | 24hr Lookahead: |  | TIH
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12725 |  | 12725 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 49 | PV: | 19
End Depth (Usft): |  | 12725 |  | 12725 |  | OD (in): |  |  |  | 300: | 30 | YP: | 11
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 47
Slide Drilled (Usft): | [9 empty] | 100: | 15 | Chlorides: | 54000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 18.80
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: | [5 empty] | SN: |  | 1138553 |  | 10s Gel: | 6 | Weight (ppg): | 11.9
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 261.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 9.5 |  | 9.5 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Nathan Marks |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Douglas Ferguson |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M 6.75 Jets 6X18's - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 Lobe 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 |  |  |  | 5.5 | 2 |  |  |  |  | 33.13 |  | 33.88
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.98
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.42
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.49
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.68
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.67
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.45
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 137.02
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.09
28 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2651.32 |  | 2791.41
Agitator |  |  |  | 5.25 | 2.25 |  |  |  |  | 23.5 |  | 2814.91
2814.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250018 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.01 |  | 2.25 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 10000 | 0 | 163 | 240 | 2700 | 2600 | 0 | 205 | 205 | 205 | 0 | 0
Run | 52.94 | 10000 | 0 | 163 | 240 | 2733.33 | 2633.33 | 0 | 205 | 205 | 205 | 0 | 0
Comments
Plan 9 STO 1
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/27/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/27/2021 |  | 5 |  | 100 |  | 4 | 400
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 05/27/2021 | PPM250024 | 15 |  | 1000 |  | 1 | 1000
5.5 Premium Motor Reline |  |  |  |  | 05/27/2021 |  | 9 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 05/27/2021 |  | 11 |  | 800 |  | 1 | 800
Total | [11 empty] | 18050
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/27/2021 | 00:00 | 00:40 | 0.67 | 12725 | 12725 | 0 | ST | 5: BHA 5 | 5A | Circulate to prepare to POOH to pick up 2.12 motor
05/27/2021 | 00:40 | 01:37 | 0.95 | 12725 | 12725 | 0 | ST | 5: BHA 5 | 6B | Pooh to 10272.
05/27/2021 | 01:37 | 01:50 | 0.22 | 12725 | 12725 | 0 | ST | 5: BHA 5 | 5A | Orient toolface @ 140R.
05/27/2021 | 01:50 | 06:00 | 4.17 | 12725 | 12725 | 0 | ST | 5: BHA 5 | 5A | Circulate, spot mud cap
05/27/2021 | 06:00 | 12:30 | 6.5 | 12725 | 12725 | 0 | ST | 5: BHA 5 | 6B | POOH
05/27/2021 | 12:30 | 13:30 | 1 | 12725 | 12725 | 0 | ST | 5: BHA 5 | 6P | L/D BHA
05/27/2021 | 13:30 | 14:30 | 1 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 6O | P/U BHA
05/27/2021 | 14:30 | 19:30 | 5 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 6A | TIH t/5924
05/27/2021 | 19:30 | 20:30 | 1 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 8P | Rig Service
05/27/2021 | 20:30 | 21:45 | 1.25 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 9A | Slip and cut
05/27/2021 | 21:45 | 24:00 | 2.25 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 6A | TIH t/11974
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_28_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 18 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9100 |  |  | Well Cost($): |  | 206330
|  |  |  | 24hr Summary: |  | Displace Mud cap, W/R to bottom, land curve, drill ahead in lateral
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12725 |  | 12725 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 49 | PV: | 19
End Depth (Usft): |  | 14214 |  | 14214 |  | OD (in): |  |  |  | 300: | 30 | YP: | 11
Total Drilled (Usft): |  | 1489 |  | 1489 |  | Weight (ft/lbs): |  |  |  | 200: | 22 | Viscosity: | 47
Slide Drilled (Usft): |  | 284 |  | 284 | [5 empty] | 100: | 15 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 1205 |  | 1205 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.00 / 18.80
Drlg/Circ Hrs: |  | 17.17 / 3.92 |  | 17.17 / 3.92 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 8.42 |  | 8.42 |  | SN: |  | 1138553 |  | 10s Gel: | 6 | Weight (ppg): | 11.9
Rotary Drilling Hrs: |  | 8.75 |  | 8.75 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 261.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 137.71 / 33.74 |  | 137.71 / 33.74 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 33.5 |  | Grade In:
% Slide: |  | 19.07 |  | 19.07 |  | Grade Out:
% Rotary: |  | 80.93 |  | 80.93 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M 6.75 Jets 6X18's - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HS88 +.009 |  |  |  | 5.5 | 2 |  |  |  |  | 33.14 |  | 33.89
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.99
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.43
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.5
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.69
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.68
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.46
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 137.03
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.1
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.42
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.58
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.58
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 23.5 |  | 2813.08
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.11
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 23.48 |  | 5974.59
5974.59
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.04 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
12754 | 76.84 | 129.35 | 12343.47 | 1218.03 | 1423.04 | 6.14 |  | -27.86 | 206.81 | 5.45 |  | -2.94 | 128
12849 | 80 | 126.6 | 12362.54 | 1160.79 | 1496.4 | 4.37 |  | -40.73 | 299.48 | 3.33 |  | -2.89 | 95
12943 | 86.52 | 123.29 | 12373.57 | 1107.37 | 1572.88 | 7.77 |  | -26.97 | 391.82 | 6.94 |  | -3.52 | 94
13039 | 88.01 | 121.1 | 12378.15 | 1056.28 | 1654.02 | 2.76 |  | -55.8 | 485.97 | 1.55 |  | -2.28 | 96
13134 | 87.13 | 124.02 | 12382.18 | 1005.21 | 1734 | 3.21 |  | 106.84 | 579.27 | -0.93 |  | 3.07 | 95
13230 | 87 | 127.66 | 12387.1 | 949.08 | 1811.71 | 3.79 |  | 92.14 | 674.36 | -0.14 |  | 3.79 | 96
13325 | 87.22 | 130.95 | 12391.89 | 888.99 | 1885.12 | 3.47 |  | 86.25 | 769.02 | 0.23 |  | 3.46 | 95
13420 | 86.38 | 130.88 | 12397.19 | 826.87 | 1956.79 | 0.89 |  | -175.25 | 863.8 | -0.88 |  | -0.07 | 95
13514 | 85.25 | 131.43 | 12404.05 | 765.17 | 2027.38 | 1.34 |  | 154.13 | 957.5 | -1.2 |  | 0.59 | 94
13609 | 86.44 | 133.03 | 12410.93 | 701.49 | 2097.53 | 2.1 |  | 53.35 | 1052.23 | 1.25 |  | 1.68 | 95
13706 | 90.4 | 133.8 | 12413.61 | 634.86 | 2167.95 | 4.16 |  | 11.01 | 1149.17 | 4.08 |  | 0.79 | 97
13800 | 90.26 | 134.06 | 12413.07 | 569.65 | 2235.65 | 0.31 |  | 118.3 | 1243.16 | -0.15 |  | 0.28 | 94
13894 | 88.68 | 133.99 | 12413.94 | 504.33 | 2303.23 | 1.68 |  | -177.46 | 1337.14 | -1.68 |  | -0.07 | 94
13989 | 85.74 | 134.64 | 12418.56 | 438.05 | 2371.12 | 3.17 |  | 167.56 | 1432 | -3.09 |  | 0.68 | 95
14083 | 84.65 | 134.92 | 12426.43 | 372.07 | 2437.61 | 1.2 |  | 165.65 | 1525.62 | -1.16 |  | 0.3 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 86.74 | 29.91 | 62 | 318 | 376.56 | 5953.12 | 5195.62 | 0 | 310 | 211.72 | 153.44 | 17700 | 0
Run | 86.74 | 29.91 | 62 | 318 | 376.56 | 5953.12 | 5195.62 | 0 | 310 | 211.72 | 153.44 | 17700 | 0
Comments
Plan 9 STO 1
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/28/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/28/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 05/28/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 05/28/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 9100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/28/2021 | 00:00 | 01:40 | 1.67 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 5A | Displace Mud Cap
05/28/2021 | 01:40 | 02:00 | 0.33 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 6A | TIH t/ 12225
05/28/2021 | 02:00 | 02:40 | 0.67 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 5A | Orient into sidetrack and confirm by survey
05/28/2021 | 02:40 | 02:55 | 0.25 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 6A | TIH t/ 12575
05/28/2021 | 02:55 | 04:30 | 1.58 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 3C | W/R f/ 12575 t/ 12700
05/28/2021 | 04:30 | 04:35 | 0.08 | 12725 | 12725 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 04:35 | 06:30 | 1.92 | 12725 | 12765 | 40 | LAT | 6: BHA 6 | 2J | Slide Drill f/12725.00 t/12765.00, TF -70.00G, w/WOB 30.00,Flow 350.00, Press 5100.00, Tq 0.00, ROP 20.87, Diff 400.00
05/28/2021 | 06:30 | 07:15 | 0.75 | 12765 | 12822 | 57 | LAT | 6: BHA 6 | 2K | Rotary Drill f/12765.00 t/12822.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 6700.00, Tq 17000.00, ROP 76.00, Diff 780.00, Temp 285.00
05/28/2021 | 07:15 | 07:20 | 0.08 | 12822 | 12822 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 07:20 | 08:45 | 1.42 | 12822 | 12872 | 50 | LAT | 6: BHA 6 | 2J | Slide Drill f/12822.00 t/12872.00, TF -30.00G, w/WOB 25.00,Flow 400.00, Press 6700.00, Tq 0, ROP 35.29, Diff 780.00, Temp 285.00
05/28/2021 | 08:45 | 09:15 | 0.5 | 12872 | 12912 | 40 | LAT | 6: BHA 6 | 2K | Rotary Drill f/12872.00 t/12912.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 6700.00, Tq 17000.00, ROP 80.00, Diff 780.00, Temp 285.00
05/28/2021 | 09:15 | 09:20 | 0.08 | 12912 | 12912 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 09:20 | 10:20 | 1 | 12912 | 12962 | 50 | LAT | 6: BHA 6 | 2J | Slide Drill f/12912.00 t/12962.00, TF 0.00G, w/WOB 35.00,Flow 400.00, Press 6700.00, Tq 0, ROP 50.00, Diff 780.00, Temp 285.00
05/28/2021 | 10:20 | 10:50 | 0.5 | 12962 | 13011 | 49 | LAT | 6: BHA 6 | 2K | Rotary Drill f/12962.00 t/13011.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 6700.00, Tq 17000.00, ROP 98.00, Diff 780.00, Temp 285.00
05/28/2021 | 10:50 | 10:55 | 0.08 | 13011 | 13011 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 10:55 | 11:40 | 0.75 | 13011 | 13107 | 96 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13011.00 t/13107.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 6700.00, Tq 17000.00, ROP 128.00, Diff 780.00, Temp 293.00
05/28/2021 | 11:40 | 11:45 | 0.08 | 13107 | 13107 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 11:45 | 12:15 | 0.5 | 13107 | 13127 | 20 | LAT | 6: BHA 6 | 2J | Slide Drill f/13107.00 t/13127.00, TF 90.00G, w/WOB 30.00,Flow 400.00, Press 6700.00, Tq 0, ROP 40.00, Diff 780.00, Temp 293.00
05/28/2021 | 12:15 | 12:45 | 0.5 | 13127 | 13202 | 75 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13127.00 t/13202.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 6700.00, Tq 17000.00, ROP 150.00, Diff 780.00, Temp 293.00
05/28/2021 | 12:45 | 12:50 | 0.08 | 13202 | 13202 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 12:50 | 13:20 | 0.5 | 13202 | 13222 | 20 | LAT | 6: BHA 6 | 2J | Slide Drill f/13202.00 t/13222.00, TF 90.00G, w/WOB 30.00,Flow 400.00, Press 6700.00, Tq 0, ROP 40.00, Diff 780.00, Temp 293.00
05/28/2021 | 13:20 | 13:55 | 0.58 | 13222 | 13298 | 76 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13222.00 t/13298.00, w/WOB 30.00,Flow 400.00, RPM 30.00, Press 6700.00, Tq 17000.00, ROP 130.29, Diff 780.00, Temp 293.00
05/28/2021 | 13:55 | 14:00 | 0.08 | 13298 | 13298 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 14:00 | 14:20 | 0.33 | 13298 | 13318 | 20 | LAT | 6: BHA 6 | 2J | Slide Drill f/13298.00 t/13318.00, TF 90.00G, w/WOB 30.00,Flow 400.00, Press 6700.00, Tq 0, ROP 60.00, Diff 780.00, Temp 293.00
05/28/2021 | 14:20 | 14:45 | 0.42 | 13318 | 13393 | 75 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13318.00 t/13393.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 6700.00, Tq 16000.00, ROP 180.00, Diff 780.00, Temp 300.00
05/28/2021 | 14:45 | 14:50 | 0.08 | 13393 | 13393 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 14:50 | 15:30 | 0.67 | 13393 | 13488 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13393.00 t/13488.00, w/WOB 30.00,Flow 400.00, RPM 80.00, Press 6700.00, Tq 16000.00, ROP 142.50, Diff 780.00, Temp 300.00
05/28/2021 | 15:30 | 15:35 | 0.08 | 13488 | 13488 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 15:35 | 16:10 | 0.58 | 13488 | 13582 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13488.00 t/13582.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5900.00, Tq 16000, ROP 161.14, Diff 900.00, Temp 303.00
05/28/2021 | 16:10 | 16:15 | 0.08 | 13582 | 13582 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 16:15 | 16:50 | 0.58 | 13582 | 13602 | 20 | LAT | 6: BHA 6 | 2J | Slide Drill f/13582.00 t/13602.00, TF 30.00G, w/WOB 35.00,Flow 375.00, Press 5900.00, Tq 0, ROP 34.29, Diff 900.00, Temp 303.00
05/28/2021 | 16:50 | 17:20 | 0.5 | 13602 | 13677 | 75 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13602.00 t/13677.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5900.00, Tq 16000.00, ROP 150.00, Diff 900.00, Temp 307.00
05/28/2021 | 17:20 | 17:25 | 0.08 | 13677 | 13677 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 17:25 | 17:50 | 0.42 | 13677 | 13690 | 13 | LAT | 6: BHA 6 | 2J | Slide Drill f/13677.00 t/13690.00, TF 0G, w/WOB 35,Flow 375.00, Press 5400, Tq 0, ROP 31.20, Diff 400.00, Temp 307.00
05/28/2021 | 17:50 | 18:20 | 0.5 | 13690 | 13774 | 84 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13690.00 t/13774.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5900.00, Tq 16000.00, ROP 168.00, Diff 900.00, Temp 307.00
05/28/2021 | 18:20 | 18:25 | 0.08 | 13774 | 13774 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 18:25 | 18:30 | 0.08 | 13774 | 13781 | 7 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13774.00 t/13781.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5900.00, Tq 16000.00, ROP 84.00, Diff 900.00, Temp 307.00
05/28/2021 | 18:30 | 18:50 | 0.33 | 13781 | 13793 | 12 | LAT | 6: BHA 6 | 2J | Slide Drill f/13781.00 t/13793.00, TF 180G, w/WOB 30.00,Flow 375, Press 5400, Tq 0, ROP 36.00, Diff 400.00, Temp 307.00
05/28/2021 | 18:50 | 19:15 | 0.42 | 13793 | 13868 | 75 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13793.00 t/13868.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5400.00, Tq 18000.00, ROP 180.00, Diff 400.00, Temp 300.00
05/28/2021 | 19:15 | 19:20 | 0.08 | 13868 | 13868 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 19:20 | 19:25 | 0.08 | 13868 | 13875 | 7 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13868.00 t/13875.00, w/WOB 28.00,Flow 350.00, RPM 70.00, Press 5400.00, Tq 18000.00, ROP 84.00, Diff 900.00, Temp 300.00
05/28/2021 | 19:25 | 19:55 | 0.5 | 13875 | 13890 | 15 | LAT | 6: BHA 6 | 2J | Slide Drill f/13875.00 t/13890.00, TF 180.00G, w/WOB 32.00,Flow 350.00, Press 5000.00, Tq 0.00, ROP 30.00, Diff 500.00, Temp 300.00
05/28/2021 | 19:55 | 20:20 | 0.42 | 13890 | 13962 | 72 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13890.00 t/13962.00, w/WOB 30.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 20000.00, ROP 172.80, Diff 900.00, Temp 300.00
05/28/2021 | 20:20 | 20:25 | 0.08 | 13962 | 13962 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 20:25 | 20:30 | 0.08 | 13962 | 13968 | 6 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13962.00 t/13968.00, w/WOB 30.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 20000.00, ROP 72.00, Diff 900.00, Temp 300.00
05/28/2021 | 20:30 | 21:30 | 1 | 13968 | 13968 | 0 | LAT | 6: BHA 6 | 23K | Wait on severe weather to pass
05/28/2021 | 21:30 | 21:55 | 0.42 | 13968 | 13980 | 12 | LAT | 6: BHA 6 | 2J | Slide Drill f/13968.00 t/13980.00, TF 180.00G, w/WOB 35.00,Flow 350.00, Press 5000.00, Tq 0.00, ROP 28.80, Diff 500.00, Temp 300.00
05/28/2021 | 21:55 | 22:25 | 0.5 | 13980 | 14057 | 77 | LAT | 6: BHA 6 | 2K | Rotary Drill f/13980.00 t/14057.00, w/WOB 30.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 20000.00, ROP 154.00, Diff 900.00, Temp 300.00
05/28/2021 | 22:25 | 22:30 | 0.08 | 14057 | 14057 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 22:30 | 23:00 | 0.5 | 14057 | 14151 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14057.00 t/14151.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 20000.00, ROP 188.00, Diff 1000.00, Temp 295.00
05/28/2021 | 23:00 | 23:05 | 0.08 | 14151 | 14151 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/28/2021 | 23:05 | 23:10 | 0.08 | 14151 | 14158 | 7 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14151.00 t/14158.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 20000.00, ROP 84.00, Diff 1000.00, Temp 290.00
05/28/2021 | 23:10 | 23:40 | 0.5 | 14158 | 14170 | 12 | LAT | 6: BHA 6 | 2J | Slide Drill f/14158.00 t/14170.00, TF -30.00G, w/WOB 30.00,Flow 350.00, Press 4800.00, Tq 0.00, ROP 24.00, Diff 400.00, Temp 290.00
05/28/2021 | 23:40 | 24:00 | 0.33 | 14170 | 14214 | 44 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14170.00 t/14214.00, w/WOB 22.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 20000.00, ROP 132.00, Diff 1000.00, Temp 290.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_29_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 19 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/29/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9100 |  |  | Well Cost($): |  | 215430
|  |  |  | 24hr Summary: |  | Drill ahed in lateral, POOH f/ bit and motor
|  |  |  | 24hr Lookahead: |  | POOH change BHA , TIH
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14214 |  | 12725 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 35 | PV: | 13
End Depth (Usft): |  | 15494 |  | 15494 |  | OD (in): |  |  |  | 300: | 22 | YP: | 9
Total Drilled (Usft): |  | 1280 |  | 2769 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 41
Slide Drilled (Usft): |  | 62 |  | 346 | [5 empty] | 100: | 10 | Chlorides: | 51000
Rotary Drilled (Usft): |  | 1218 |  | 2423 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.90
Drlg/Circ Hrs: |  | 11.50 / 8.25 |  | 28.67 / 12.17 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 76/24
Slide Drilling Hrs: |  | 2.92 |  | 11.33 |  | SN: |  | 1138553 |  | 10s Gel: | 6 | Weight (ppg): | 10.8
Rotary Drilling Hrs: |  | 8.58 |  | 17.33 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 286.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 141.90 / 21.26 |  | 139.79 / 30.53 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 57.5 |  | Grade In:
% Slide: |  | 4.84 |  | 12.5 |  | Grade Out:
% Rotary: |  | 95.16 |  | 87.5 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Stephen Simmons
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M 6.75 Jets 6X18's - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HS88 +.009 |  |  |  | 5.5 | 2 |  |  |  |  | 33.14 |  | 33.89
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.99
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.43
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.5
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.69
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.68
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.46
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 137.03
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.1
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.42
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.58
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.58
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 23.5 |  | 2813.08
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.11
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 23.48 |  | 5974.59
5974.59
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.04 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14178 | 85.24 | 134.8 | 12434.8 | 305.32 | 2504.68 | 0.63 |  | -11.46 | 1620.21 | 0.62 |  | -0.13 | 95
14272 | 85.73 | 133.44 | 12442.2 | 240.08 | 2571.95 | 1.53 |  | -70.18 | 1713.9 | 0.52 |  | -1.45 | 94
14367 | 87.06 | 133.46 | 12448.18 | 174.88 | 2640.78 | 1.4 |  | 0.86 | 1808.71 | 1.4 |  | 0.02 | 95
14461 | 88.35 | 134.71 | 12451.94 | 109.54 | 2708.25 | 1.91 |  | 44.1 | 1902.61 | 1.37 |  | 1.33 | 94
14557 | 89.12 | 135.54 | 12454.06 | 41.53 | 2775.96 | 1.18 |  | 47.15 | 1998.53 | 0.8 |  | 0.86 | 96
14652 | 88.14 | 132.32 | 12456.33 | -24.36 | 2844.35 | 3.54 |  | -106.97 | 2093.48 | -1.03 |  | -3.39 | 95
14748 | 87.6 | 131.36 | 12459.9 | -88.35 | 2915.82 | 1.15 |  | -119.39 | 2189.39 | -0.56 |  | -1 | 96
14843 | 87.37 | 130.9 | 12464.07 | -150.78 | 2987.31 | 0.54 |  | -116.6 | 2284.24 | -0.24 |  | -0.48 | 95
14937 | 87.67 | 131.3 | 12468.14 | -212.51 | 3058.08 | 0.53 |  | 53.11 | 2378.09 | 0.32 |  | 0.43 | 94
15032 | 88.19 | 131.07 | 12471.57 | -275.03 | 3129.52 | 0.6 |  | -23.85 | 2472.98 | 0.55 |  | -0.24 | 95
15127 | 88.63 | 131.12 | 12474.2 | -337.45 | 3201.09 | 0.47 |  | 6.48 | 2567.88 | 0.46 |  | 0.05 | 95
15222 | 87.72 | 132.21 | 12477.23 | -400.57 | 3272.02 | 1.49 |  | 129.89 | 2662.8 | -0.96 |  | 1.15 | 95
15316 | 87.96 | 133.49 | 12480.77 | -464.45 | 3340.89 | 1.38 |  | 79.4 | 2756.73 | 0.26 |  | 1.36 | 94
15412 | 87.52 | 134.51 | 12484.56 | -531.08 | 3409.89 | 1.16 |  | 113.37 | 2852.65 | -0.46 |  | 1.06 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 111.3 | 28.75 | 77.37 | 315 | 350 | 5212.5 | 4400 | 0 | 324.17 | 215 | 160 | 20342.11 | 0
Run | 96.59 | 29.41 | 69.49 | 318 | 365.18 | 5635.71 | 4854.64 | 0 | 316.07 | 213.12 | 156.25 | 18987.18 | 0
Comments
Plan 9 STO 1, Window 15A/0B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 05/29/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 05/29/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 05/29/2021 |  | 18 |  | 1250 |  | 1 | 1250
Dir & MWD /Gamma |  |  |  |  | 05/29/2021 |  | 4 |  | 6850 |  | 1 | 6850
Total | [11 empty] | 9100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/29/2021 | 00:00 | 00:10 | 0.17 | 14214 | 14246 | 32 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14214.00 t/14246.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 21000.00, ROP 192.00, Diff 1000.00, Temp 290.00
05/29/2021 | 00:10 | 00:15 | 0.08 | 14246 | 14246 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 00:15 | 00:20 | 0.08 | 14246 | 14256 | 10 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14246.00 t/14256.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 21000.00, ROP 120.00, Diff 1000.00, Temp 290.00
05/29/2021 | 00:20 | 00:50 | 0.5 | 14256 | 14266 | 10 | LAT | 6: BHA 6 | 2J | Slide Drill f/14256.00 t/14266.00, TF -45.00G, w/WOB 32.00,Flow 350.00, Press 4800.00, Tq 0.00, ROP 20.00, Diff 400.00, Temp 290.00
05/29/2021 | 00:50 | 01:20 | 0.5 | 14266 | 14340 | 74 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14266.00 t/14340.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5400.00, Tq 21000.00, ROP 148.00, Diff 1000.00, Temp 290.00
05/29/2021 | 01:20 | 01:55 | 0.58 | 14340 | 14340 | 0 | LAT | 6: BHA 6 | 8P | Rig Service
05/29/2021 | 01:55 | 02:00 | 0.08 | 14340 | 14340 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 02:00 | 02:05 | 0.08 | 14340 | 14348 | 8 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14340.00 t/14348.00, w/WOB 25.00,Flow 350.00, RPM 70.00, Press 5400.00, Tq 21000.00, ROP 96.00, Diff 1000.00, Temp 285.00
05/29/2021 | 02:05 | 02:30 | 0.42 | 14348 | 14360 | 12 | LAT | 6: BHA 6 | 2J | Slide Drill f/14348.00 t/14360.00, TF -30.00G, w/WOB 30.00,Flow 350.00, Press 4700.00, Tq 0.00, ROP 28.80, Diff 300.00, Temp 285.00
05/29/2021 | 02:30 | 03:00 | 0.5 | 14360 | 14435 | 75 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14360.00 t/14435.00, w/WOB 30.00,Flow 350.00, RPM 70.00, Press 5300.00, Tq 21000.00, ROP 150.00, Diff 900.00, Temp 280.00
05/29/2021 | 03:00 | 03:05 | 0.08 | 14435 | 14435 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 03:05 | 03:35 | 0.5 | 14435 | 14529 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14435.00 t/14529.00, w/WOB 28.00,Flow 350.00, RPM 70.00, Press 5300.00, Tq 21000.00, ROP 188.00, Diff 900.00, Temp 280.00
05/29/2021 | 03:35 | 03:40 | 0.08 | 14529 | 14529 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 03:40 | 04:15 | 0.58 | 14529 | 14625 | 96 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14529.00 t/14625.00, w/WOB 28.00,Flow 350.00, RPM 70.00, Press 5300.00, Tq 21000.00, ROP 164.57, Diff 900.00, Temp 280.00
05/29/2021 | 04:15 | 04:20 | 0.08 | 14625 | 14625 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 04:20 | 04:25 | 0.08 | 14625 | 14636 | 11 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14625.00 t/14636.00, w/WOB 28.00,Flow 350.00, RPM 70.00, Press 5300.00, Tq 21000.00, ROP 132.00, Diff 900.00, Temp 280.00
05/29/2021 | 04:25 | 04:55 | 0.5 | 14636 | 14651 | 15 | LAT | 6: BHA 6 | 2J | Slide Drill f/14636.00 t/14651.00, TF -90.00G, w/WOB 32.00,Flow 350.00, Press 4700.00, Tq 0.00, ROP 30.00, Diff 300.00, Temp 280.00
05/29/2021 | 04:55 | 05:25 | 0.5 | 14651 | 14720 | 69 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14651.00 t/14720.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 20000.00, ROP 138.00, Diff 900.00, Temp 286.00
05/29/2021 | 05:25 | 05:30 | 0.08 | 14720 | 14720 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 05:30 | 06:05 | 0.58 | 14720 | 14816 | 96 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14720.00 t/14816.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 20000.00, ROP 164.57, Diff 900.00, Temp 286.00
05/29/2021 | 06:05 | 06:10 | 0.08 | 14816 | 14816 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 06:10 | 06:45 | 0.58 | 14816 | 14911 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14816.00 t/14911.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 20000.00, ROP 162.86, Diff 900.00, Temp 286.00
05/29/2021 | 06:45 | 06:50 | 0.08 | 14911 | 14911 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 06:50 | 07:25 | 0.58 | 14911 | 15005 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/14911.00 t/15005.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 20000.00, ROP 161.14, Diff 900.00, Temp 286.00
05/29/2021 | 07:25 | 07:30 | 0.08 | 15005 | 15005 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 07:30 | 08:05 | 0.58 | 15005 | 15100 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15005.00 t/15100.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 18500.00, ROP 162.86, Diff 900.00, Temp 305.00
05/29/2021 | 08:05 | 08:10 | 0.08 | 15100 | 15100 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 08:10 | 08:45 | 0.58 | 15100 | 15195 | 95 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15100.00 t/15195.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 18500.00, ROP 162.86, Diff 900.00, Temp 305.00
05/29/2021 | 08:45 | 08:50 | 0.08 | 15195 | 15195 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 08:50 | 09:50 | 1 | 15195 | 15210 | 15 | LAT | 6: BHA 6 | 2J | Slide Drill f/15195.00 t/15210.00, TF 150G, w/WOB 40,Flow 350.00, Press 5300.00, Tq 18500.00, ROP 15.00, Diff 900.00, Temp 305.00
05/29/2021 | 09:50 | 10:25 | 0.58 | 15210 | 15290 | 80 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15210.00 t/15290.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 18500.00, ROP 137.14, Diff 900.00, Temp 305.00
05/29/2021 | 10:25 | 10:30 | 0.08 | 15290 | 15290 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 10:30 | 11:10 | 0.67 | 15290 | 15384 | 94 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15290.00 t/15384.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 18500.00, ROP 141.00, Diff 900.00, Temp 309.00
05/29/2021 | 11:10 | 11:15 | 0.08 | 15384 | 15384 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 11:15 | 11:20 | 0.08 | 15384 | 15394 | 10 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15384.00 t/15394.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5300.00, Tq 18500.00, ROP 120.00, Diff 900.00, Temp 309.00
05/29/2021 | 11:20 | 11:50 | 0.5 | 15394 | 15404 | 10 | LAT | 6: BHA 6 | 2J | Slide Drill f/15394.00 t/15404.00, TF 180G, w/WOB 40,Flow 350.00, Press 5300.00, Tq 18500.00, ROP 20.00, Diff 900.00, Temp 309.00
05/29/2021 | 11:50 | 12:50 | 1 | 15404 | 15480 | 76 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15404.00 t/15480.00, w/WOB 35,Flow 350.00, RPM 80.00, Press 4900, Tq 23000, ROP 76.00, Diff 500.00, Temp 316.00
05/29/2021 | 12:50 | 12:55 | 0.08 | 15480 | 15480 | 0 | LAT | 6: BHA 6 | 10D | Survey & Connection
05/29/2021 | 12:55 | 13:15 | 0.33 | 15480 | 15494 | 14 | LAT | 6: BHA 6 | 2K | Rotary Drill f/15480.00 t/15494.00, w/WOB 35,Flow 350.00, RPM 80.00, Press 4900, Tq 23000, ROP 42.00, Diff 500.00, Temp 316.00
05/29/2021 | 13:15 | 14:30 | 1.25 | 15494 | 15494 | 0 | LAT | 6: BHA 6 | 5A | Circulate to POOH t/ change bit and motor due to slow ROP
05/29/2021 | 14:30 | 20:30 | 6 | 15494 | 15494 | 0 | LAT | 6: BHA 6 | 3D | Back ream out t/ shoe.
05/29/2021 | 20:30 | 21:30 | 1 | 15494 | 15494 | 0 | LAT | 6: BHA 6 | 5A | Circulate B/U and pump slug
05/29/2021 | 21:30 | 24:00 | 2.5 | 15494 | 15494 | 0 | LAT | 6: BHA 6 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_30_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 20 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/30/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19900 |  |  | Well Cost($): |  | 235330
|  |  |  | 24hr Summary: |  | POOH t/ change BHA, TIH, Drill ahed
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15494 |  | 15494 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 29 | PV: | 10
End Depth (Usft): |  | 16035 |  | 16035 |  | OD (in): |  | 7.625 |  | 300: | 19 | YP: | 9
Total Drilled (Usft): |  | 541 |  | 541 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 14 | Viscosity: | 42
Slide Drilled (Usft): |  | 27 |  | 27 | [5 empty] | 100: | 9 | Chlorides: | 53000
Rotary Drilled (Usft): |  | 514 |  | 514 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 12.90
Drlg/Circ Hrs: |  | 4.17 / 2.33 |  | 4.17 / 2.33 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 1.17 |  | 1.17 |  | SN: |  | 1138553 |  | 10s Gel: | 5 | Weight (ppg): | 10.4
Rotary Drilling Hrs: |  | 3 |  | 3 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 304.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 171.33 / 23.14 |  | 171.33 / 23.14 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 18.67 |  | 18.67 |  | Grade In:
% Slide: |  | 4.99 |  | 4.99 |  | Grade Out:
% Rotary: |  | 95.01 |  | 95.01 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Stephen Simmons
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M 6.75 Jets 6X18's - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HS88 +.009 |  |  |  | 5.5 | 2 |  |  |  |  | 33.14 |  | 33.89
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.99
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.43
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.5
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.69
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.68
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.46
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 137.03
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.1
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.42
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.58
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.58
Agitator |  |  |  | 5.25 | 2.5 |  |  |  |  | 23.5 |  | 2813.08
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.11
Agitator |  |  |  | 5.312 | 2.5 |  |  |  |  | 23.48 |  | 5974.59
5974.59
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.04 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15505 | 88.85 | 135.05 | 12487.5 | -596.56 | 3475.87 | 1.54 |  | 22.1 | 2945.56 | 1.43 |  | 0.58 | 93
15600 | 87.8 | 132.98 | 12490.28 | -662.53 | 3544.15 | 2.44 |  | -116.93 | 3040.5 | -1.11 |  | -2.18 | 95
15695 | 88.07 | 134.33 | 12493.7 | -728.07 | 3612.84 | 1.45 |  | 78.71 | 3135.43 | 0.28 |  | 1.42 | 95
15791 | 86.73 | 133.62 | 12498.06 | -794.66 | 3681.85 | 1.58 |  | -152.12 | 3231.32 | -1.4 |  | -0.74 | 96
15885 | 85.88 | 133.81 | 12504.12 | -859.48 | 3749.65 | 0.93 |  | 167.43 | 3325.12 | -0.9 |  | 0.2 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 26.78 | 80 | 318 | 350 | 5333.33 | 4500 | 134 | 325 | 260 | 200 | 21000 | 12000
Run | 96.59 | 26.78 | 80 | 318 | 350 | 5333.33 | 4500 | 134 | 325 | 260 | 200 | 21000 | 12000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 15A/0B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 05/30/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 05/30/2021 |  | 5 |  | 100 |  | 4 | 400
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 05/30/2021 |  | 15 |  | 1000 |  | 1 | 1000
5.5 Premium Motor Reline |  |  |  |  | 05/30/2021 |  | 9 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 05/30/2021 |  | 11 |  | 800 |  | 1 | 800
Real Time Survey Management |  |  |  |  | 05/30/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 05/30/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 19900
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/30/2021 | 00:00 | 03:50 | 3.83 | 15494 | 15494 | 0 | LAT | 6: BHA 6 | 6B | POOH
05/30/2021 | 03:50 | 04:35 | 0.75 | 15494 | 15494 | 0 | LAT | 6: BHA 6 | 6P | L/D BHA #6
05/30/2021 | 04:35 | 05:20 | 0.75 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 6O | M/U BHA #7
05/30/2021 | 05:20 | 05:35 | 0.25 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 5A | Test motor and MWD
05/30/2021 | 05:35 | 06:00 | 0.42 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 6L | M/U Bit
05/30/2021 | 06:00 | 14:50 | 8.83 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 6A | TIH
05/30/2021 | 14:50 | 16:00 | 1.17 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 8P | Rig Service
05/30/2021 | 16:00 | 17:00 | 1 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 5A | Orient through ST
05/30/2021 | 17:00 | 18:20 | 1.33 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 6A | TIH t/ 15000
05/30/2021 | 18:20 | 19:10 | 0.83 | 15494 | 15494 | 0 | LAT | 7: BHA 7 | 3C | W/R to bottom
05/30/2021 | 19:10 | 19:40 | 0.5 | 15494 | 15572 | 78 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15494.00 t/15572.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 156.00, Diff 1000.00, Temp 304.00
05/30/2021 | 19:40 | 19:55 | 0.25 | 15572 | 15572 | 0 | LAT | 7: BHA 7 | 5A | Circulate
05/30/2021 | 19:55 | 20:00 | 0.08 | 15572 | 15572 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/30/2021 | 20:00 | 20:05 | 0.08 | 15572 | 15579 | 7 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15572.00 t/15579.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 84.00, Diff 1000.00, Temp 304.00
05/30/2021 | 20:05 | 20:40 | 0.58 | 15579 | 15594 | 15 | LAT | 7: BHA 7 | 2J | Slide Drill f/15579.00 t/15594.00, TF -130.00G, w/WOB 30.00,Flow 350.00, Press 4800.00, Tq 0.00, ROP 25.71, Diff 300.00, Temp 304.00
05/30/2021 | 20:40 | 21:10 | 0.5 | 15594 | 15667 | 73 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15594.00 t/15667.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 146.00, Diff 1000.00, Temp 304.00
05/30/2021 | 21:10 | 21:15 | 0.08 | 15667 | 15667 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/30/2021 | 21:15 | 21:45 | 0.5 | 15667 | 15762 | 95 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15667.00 t/15762.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 190.00, Diff 1000.00, Temp 307.00
05/30/2021 | 21:45 | 21:50 | 0.08 | 15762 | 15762 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/30/2021 | 21:50 | 22:25 | 0.58 | 15762 | 15774 | 12 | LAT | 7: BHA 7 | 2J | Slide Drill f/15762.00 t/15774.00, TF -150.00G, w/WOB 35.00,Flow 350.00, Press 4700.00, Tq 0.00, ROP 20.57, Diff 200.00, Temp 307.00
05/30/2021 | 22:25 | 22:55 | 0.5 | 15774 | 15858 | 84 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15774.00 t/15858.00, w/WOB 28.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 168.00, Diff 1000.00, Temp 307.00
05/30/2021 | 22:55 | 23:00 | 0.08 | 15858 | 15858 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/30/2021 | 23:00 | 23:25 | 0.42 | 15858 | 15952 | 94 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15858.00 t/15952.00, w/WOB 30.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 225.60, Diff 1000.00, Temp 310.00
05/30/2021 | 23:25 | 23:30 | 0.08 | 15952 | 15952 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/30/2021 | 23:30 | 24:00 | 0.5 | 15952 | 16035 | 83 | LAT | 7: BHA 7 | 2K | Rotary Drill f/15952.00 t/16035.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 166.00, Diff 1000.00, Temp 310.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 5_31_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 21 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 05/31/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9100 |  |  | Well Cost($): |  | 244430
|  |  |  | 24hr Summary: |  | Drill ahead in lateral
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16035 |  | 15494 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 17510 |  | 17510 |  | OD (in): |  | 7.625 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 1475 |  | 2016 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 13 | Viscosity: | 44
Slide Drilled (Usft): |  | 164 |  | 191 | [5 empty] | 100: | 9 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 1311 |  | 1825 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 11.80
Drlg/Circ Hrs: |  | 21.00 / 0.00 |  | 25.17 / 2.33 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 9.92 |  | 11.08 |  | SN: |  | 13558789 |  | 10s Gel: | 5 | Weight (ppg): | 10
Rotary Drilling Hrs: |  | 11.08 |  | 14.08 |  | Bit # |  | 6 |  | PH / Temp(F) | 0.0 / 338.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 118.29 / 16.54 |  | 129.59 / 17.23 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 42.67 |  | Grade In: |  | New
% Slide: |  | 11.12 |  | 9.47 |  | Grade Out: |  | 4-6-BT-A-X-I-WT-HP
% Rotary: |  | 88.88 |  | 90.53 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Stephen Simmons
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.021 |  |  |  | 5.5 | 2 |  |  |  |  | 33.08 |  | 33.83
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.93
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.37
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.44
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.63
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.62
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.4
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.97
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.04
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.36
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.52
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.52
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.7 |  | 2813.22
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.25
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 20.82 |  | 5972.07
5972.07
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15981 | 84.63 | 134.09 | 12512.06 | -925.88 | 3818.53 | 1.33 |  | 167.43 | 3420.77 | -1.3 |  | 0.29 | 96
16076 | 84.72 | 133.02 | 12520.88 | -991.05 | 3887.08 | 1.13 |  | -85.22 | 3515.36 | 0.09 |  | -1.13 | 95
16170 | 86.44 | 132.04 | 12528.12 | -1054.4 | 3956.14 | 2.1 |  | -29.64 | 3609.07 | 1.83 |  | -1.04 | 94
16265 | 92.79 | 131.93 | 12528.76 | -1117.92 | 4026.72 | 6.69 |  | -0.99 | 3704 | 6.68 |  | -0.12 | 95
16359 | 90.57 | 130.69 | 12526 | -1179.94 | 4097.29 | 2.7 |  | -150.8 | 3797.91 | -2.36 |  | -1.32 | 94
16453 | 90.41 | 130.99 | 12525.2 | -1241.41 | 4168.4 | 0.36 |  | 118.07 | 3891.83 | -0.17 |  | 0.32 | 94
16549 | 91.04 | 131.14 | 12523.98 | -1304.47 | 4240.78 | 0.67 |  | 13.39 | 3987.76 | 0.66 |  | 0.16 | 96
16646 | 92.26 | 131.13 | 12521.19 | -1368.25 | 4313.8 | 1.26 |  | -0.47 | 4084.66 | 1.26 |  | -0.01 | 97
16740 | 89.81 | 131.15 | 12519.49 | -1430.08 | 4384.58 | 2.61 |  | 179.53 | 4178.59 | -2.61 |  | 0.02 | 94
16835 | 88.61 | 131.19 | 12520.8 | -1492.61 | 4456.08 | 1.26 |  | 178.09 | 4273.52 | -1.26 |  | 0.04 | 95
16930 | 87.37 | 131.55 | 12524.13 | -1555.35 | 4527.33 | 1.36 |  | 163.83 | 4368.42 | -1.31 |  | 0.38 | 95
17025 | 88.69 | 132.78 | 12527.4 | -1619.08 | 4597.7 | 1.9 |  | 42.98 | 4463.34 | 1.39 |  | 1.29 | 95
17119 | 89.65 | 133.47 | 12528.76 | -1683.33 | 4666.3 | 1.26 |  | 35.71 | 4557.33 | 1.02 |  | 0.73 | 94
17213 | 90.9 | 134.33 | 12528.31 | -1748.51 | 4734.03 | 1.61 |  | 34.53 | 4651.32 | 1.33 |  | 0.91 | 94
17308 | 90.79 | 135.3 | 12526.91 | -1815.46 | 4801.41 | 1.03 |  | 96.46 | 4746.27 | -0.12 |  | 1.02 | 95
17403 | 92.79 | 134.26 | 12523.94 | -1882.34 | 4868.81 | 2.37 |  | -27.45 | 4841.17 | 2.11 |  | -1.09 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 66.57 | 29.73 | 78.15 | 326 | 364.86 | 5345.95 | 4716.22 | 134 | 331.08 | 260 | 195.14 | 21333.33 | 12000
Run | 76.27 | 29.15 | 78.53 | 325 | 361.96 | 5343.48 | 4673.91 | 134 | 329.89 | 260 | 196.09 | 21264.71 | 12000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/0B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 05/31/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 05/31/2021 |  | 10 |  | 600 |  | 1 | 600
Dir & MWD /Gamma |  |  |  |  | 05/31/2021 |  | 4 |  | 6850 |  | 1 | 6850
MWD hot hole charge |  |  |  |  | 05/31/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 9100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
05/31/2021 | 00:00 | 00:05 | 0.08 | 16035 | 16048 | 13 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16035.00 t/16048.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 156.00, Diff 1000.00, Temp 310.00
05/31/2021 | 00:05 | 00:10 | 0.08 | 16048 | 16048 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 00:10 | 00:15 | 0.08 | 16048 | 16053 | 5 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16048.00 t/16053.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 60.00, Diff 1000.00, Temp 310.00
05/31/2021 | 00:15 | 01:15 | 1 | 16053 | 16073 | 20 | LAT | 7: BHA 7 | 2J | Slide Drill f/16053.00 t/16073.00, TF -45.00G, w/WOB 32.00,Flow 370.00, Press 5000.00, Tq 0.00, ROP 20.00, Diff 200.00, Temp 313.00
05/31/2021 | 01:15 | 01:45 | 0.5 | 16073 | 16143 | 70 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16073.00 t/16143.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 140.00, Diff 1000.00, Temp 313.00
05/31/2021 | 01:45 | 01:50 | 0.08 | 16143 | 16143 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 01:50 | 01:55 | 0.08 | 16143 | 16150 | 7 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16143.00 t/16150.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 84.00, Diff 1000.00, Temp 313.00
05/31/2021 | 01:55 | 03:15 | 1.33 | 16150 | 16180 | 30 | LAT | 7: BHA 7 | 2J | Slide Drill f/16150.00 t/16180.00, TF 0.00G, w/WOB 32.00,Flow 370.00, Press 5000.00, Tq 0.00, ROP 22.50, Diff 200.00, Temp 313.00
05/31/2021 | 03:15 | 03:25 | 0.17 | 16180 | 16207 | 27 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16180.00 t/16207.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 162.00, Diff 1000.00, Temp 313.00
05/31/2021 | 03:25 | 03:35 | 0.17 | 16207 | 16207 | 0 | LAT | 7: BHA 7 | 10D | Check shot
05/31/2021 | 03:35 | 04:10 | 0.58 | 16207 | 16222 | 15 | LAT | 7: BHA 7 | 2J | Slide Drill f/16207.00 t/16222.00, TF 0.00G, w/WOB 32.00,Flow 370.00, Press 5000.00, Tq 0.00, ROP 25.71, Diff 200.00, Temp 313.00
05/31/2021 | 04:10 | 04:15 | 0.08 | 16222 | 16237 | 15 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16222.00 t/16237.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 180.00, Diff 1000.00, Temp 313.00
05/31/2021 | 04:15 | 04:20 | 0.08 | 16237 | 16237 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 04:20 | 04:25 | 0.08 | 16237 | 16243 | 6 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16237.00 t/16243.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5500.00, Tq 21000.00, ROP 72.00, Diff 1000.00, Temp 313.00
05/31/2021 | 04:25 | 05:15 | 0.83 | 16243 | 16255 | 12 | LAT | 7: BHA 7 | 2J | Slide Drill f/16243.00 t/16255.00, TF 0.00G, w/WOB 32.00,Flow 370.00, Press 5000.00, Tq 0.00, ROP 14.40, Diff 200.00, Temp 313.00
05/31/2021 | 05:15 | 06:00 | 0.75 | 16255 | 16332 | 77 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16255.00 t/16332.00, w/WOB 32.00,Flow 370.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 102.67, Diff 200.00, Temp 313.00
05/31/2021 | 06:00 | 06:05 | 0.08 | 16332 | 16332 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 06:05 | 06:10 | 0.08 | 16332 | 16338 | 6 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16332.00 t/16338.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 72.00, Diff 600.00, Temp 318.00
05/31/2021 | 06:10 | 06:55 | 0.75 | 16338 | 16353 | 15 | LAT | 7: BHA 7 | 2J | Slide Drill f/16338.00 t/16353.00, TF 180.00G, w/WOB 35.00,Flow 350.00, Press 5000.00, Tq 21000.00, ROP 20.00, Diff 600.00, Temp 318.00
05/31/2021 | 06:55 | 07:35 | 0.67 | 16353 | 16426 | 73 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16353.00 t/16426.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 109.50, Diff 600.00, Temp 318.00
05/31/2021 | 07:35 | 07:40 | 0.08 | 16426 | 16426 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 07:40 | 08:20 | 0.67 | 16426 | 16520 | 94 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16426.00 t/16520.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 141.00, Diff 600.00, Temp 318.00
05/31/2021 | 08:20 | 08:25 | 0.08 | 16520 | 16520 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 08:25 | 09:05 | 0.67 | 16520 | 16616 | 96 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16520.00 t/16616.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 144.00, Diff 600.00, Temp 318.00
05/31/2021 | 09:05 | 09:10 | 0.08 | 16616 | 16616 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 09:10 | 09:50 | 0.67 | 16616 | 16713 | 97 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16616.00 t/16713.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 145.50, Diff 600.00, Temp 318.00
05/31/2021 | 09:50 | 09:55 | 0.08 | 16713 | 16713 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 09:55 | 10:00 | 0.08 | 16713 | 16723 | 10 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16713.00 t/16723.00, w/WOB 27.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 21000.00, ROP 120.00, Diff 600.00, Temp 318.00
05/31/2021 | 10:00 | 10:50 | 0.83 | 16723 | 16738 | 15 | LAT | 7: BHA 7 | 2J | Slide Drill f/16723.00 t/16738.00, TF 180.00G, w/WOB 40.00,Flow 375.00, Press 5100.00, Tq 21000.00, ROP 18.00, Diff 200.00, Temp 318.00
05/31/2021 | 10:50 | 11:35 | 0.75 | 16738 | 16807 | 69 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16738.00 t/16807.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 21000.00, ROP 92.00, Diff 800.00, Temp 318.00
05/31/2021 | 11:35 | 12:25 | 0.83 | 16807 | 16807 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 12:25 | 13:00 | 0.58 | 16807 | 16902 | 95 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16807.00 t/16902.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 21000.00, ROP 162.86, Diff 800.00, Temp 318.00
05/31/2021 | 13:00 | 13:05 | 0.08 | 16902 | 16902 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 13:05 | 13:55 | 0.83 | 16902 | 16997 | 95 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16902.00 t/16997.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 21000.00, ROP 114.00, Diff 800.00, Temp 334.00
05/31/2021 | 13:55 | 14:45 | 0.83 | 16997 | 16997 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 14:45 | 14:50 | 0.08 | 16997 | 17005 | 8 | LAT | 7: BHA 7 | 2K | Rotary Drill f/16997.00 t/17005.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 21000.00, ROP 96.00, Diff 800.00, Temp 329.00
05/31/2021 | 14:50 | 16:00 | 1.17 | 17005 | 17025 | 20 | LAT | 7: BHA 7 | 2J | Slide Drill f/17005.00 t/17025.00, TF 0.00G, w/WOB 45.00,Flow 375.00, Press 5300.00, Tq 21000.00, ROP 17.14, Diff 400.00, Temp 329.00
05/31/2021 | 16:00 | 16:40 | 0.67 | 17025 | 17092 | 67 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17025.00 t/17092.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 22000.00, ROP 100.50, Diff 800.00, Temp 330.00
05/31/2021 | 16:40 | 16:45 | 0.08 | 17092 | 17092 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 16:45 | 16:50 | 0.08 | 17092 | 17102 | 10 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17092.00 t/17102.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 22000.00, ROP 120.00, Diff 800.00, Temp 331.00
05/31/2021 | 16:50 | 17:40 | 0.83 | 17102 | 17112 | 10 | LAT | 7: BHA 7 | 2J | Slide Drill f/17102.00 t/17112.00, TF 0.00G, w/WOB 45.00,Flow 375.00, Press 5100.00, Tq 0.00, ROP 12.00, Diff 200.00, Temp 331.00
05/31/2021 | 17:40 | 18:15 | 0.58 | 17112 | 17186 | 74 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17112.00 t/17186.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 22000.00, ROP 126.86, Diff 800.00, Temp 334.00
05/31/2021 | 18:15 | 18:20 | 0.08 | 17186 | 17186 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 18:20 | 18:25 | 0.08 | 17186 | 17196 | 10 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17186.00 t/17196.00, w/WOB 30.00,Flow 375.00, RPM 80.00, Press 5700.00, Tq 22000.00, ROP 120.00, Diff 800.00, Temp 334.00
05/31/2021 | 18:25 | 19:30 | 1.08 | 17196 | 17211 | 15 | LAT | 7: BHA 7 | 2J | Slide Drill f/17196.00 t/17211.00, TF 0.00G, w/WOB 40.00,Flow 375.00, Press 5100.00, Tq 0.00, ROP 13.85, Diff 200.00, Temp 334.00
05/31/2021 | 19:30 | 20:10 | 0.67 | 17211 | 17280 | 69 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17211.00 t/17280.00, w/WOB 27.00,Flow 375.00, RPM 70.00, Press 5600.00, Tq 22000.00, ROP 103.50, Diff 700.00, Temp 338.00
05/31/2021 | 20:10 | 20:15 | 0.08 | 17280 | 17280 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 20:15 | 21:00 | 0.75 | 17280 | 17375 | 95 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17280.00 t/17375.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5700.00, Tq 22000.00, ROP 126.67, Diff 800.00, Temp 338.00
05/31/2021 | 21:00 | 21:05 | 0.08 | 17375 | 17375 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 21:05 | 21:10 | 0.08 | 17375 | 17385 | 10 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17375.00 t/17385.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 5700.00, Tq 22000.00, ROP 120.00, Diff 800.00, Temp 334.00
05/31/2021 | 21:10 | 22:40 | 1.5 | 17385 | 17397 | 12 | LAT | 7: BHA 7 | 2J | Slide Drill f/17385.00 t/17397.00, TF -45.00G, w/WOB 30.00,Flow 375.00, Press 5100.00, Tq 0.00, ROP 8.00, Diff 200.00, Temp 334.00
05/31/2021 | 22:40 | 23:30 | 0.83 | 17397 | 17470 | 73 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17397.00 t/17470.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 5500.00, Tq 22000.00, ROP 87.60, Diff 600.00, Temp 335.00
05/31/2021 | 23:30 | 23:35 | 0.08 | 17470 | 17470 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
05/31/2021 | 23:35 | 24:00 | 0.42 | 17470 | 17510 | 40 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17470.00 t/17510.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 5500.00, Tq 22000.00, ROP 96.00, Diff 600.00, Temp 335.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_1_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 22 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/01/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9100 |  |  | Well Cost($): |  | 253530
|  |  |  | 24hr Summary: |  | Drill ahead in lateral
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17510 |  | 15494 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 29 | PV: | 9
End Depth (Usft): |  | 18333 |  | 18333 |  | OD (in): |  | 7.625 |  | 300: | 20 | YP: | 1
Total Drilled (Usft): |  | 823 |  | 2839 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 44
Slide Drilled (Usft): |  | 83 |  | 274 | [5 empty] | 100: | 11 | Chlorides: | 56000
Rotary Drilled (Usft): |  | 740 |  | 2565 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 13.80
Drlg/Circ Hrs: |  | 18.08 / 3.17 |  | 43.25 / 5.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 7.33 |  | 18.42 |  | SN: |  | 13558789 |  | 10s Gel: | 5 | Weight (ppg): | 10.7
Rotary Drilling Hrs: |  | 10.75 |  | 24.83 |  | Bit # |  | 6 |  | PH / Temp(F) | 0.0 / 347.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 68.84 / 11.32 |  | 103.29 / 14.88 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 66.67 |  | Grade In: |  | New
% Slide: |  | 10.09 |  | 9.65 |  | Grade Out: |  | 4-6-BT-A-X-I-WT-HP
% Rotary: |  | 89.91 |  | 90.35 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.021 |  |  |  | 5.5 | 2 |  |  |  |  | 33.08 |  | 33.83
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.93
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.37
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.44
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.63
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.62
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.4
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.97
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.04
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.36
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.52
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.52
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.7 |  | 2813.22
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.25
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 20.82 |  | 5972.07
5972.07
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17499 | 94.61 | 133.69 | 12517.75 | -1948.86 | 4937.74 | 1.99 |  | -17.34 | 4936.96 | 1.9 |  | -0.59 | 96
17593 | 92.17 | 133.53 | 12512.19 | -2013.57 | 5005.68 | 2.6 |  | -176.25 | 5030.78 | -2.6 |  | -0.17 | 94
17688 | 88.68 | 132.84 | 12511.48 | -2078.58 | 5074.94 | 3.74 |  | -168.81 | 5125.76 | -3.67 |  | -0.73 | 95
17782 | 86.34 | 133.15 | 12515.57 | -2142.61 | 5143.62 | 2.51 |  | 172.47 | 5219.67 | -2.49 |  | 0.33 | 94
17877 | 85.72 | 133.38 | 12522.15 | -2207.57 | 5212.63 | 0.7 |  | 159.7 | 5314.44 | -0.65 |  | 0.24 | 95
17973 | 87.19 | 134.18 | 12528.08 | -2273.86 | 5281.81 | 1.74 |  | 28.54 | 5410.25 | 1.53 |  | 0.83 | 96
18067 | 90.64 | 133.11 | 12529.86 | -2338.71 | 5349.81 | 3.84 |  | -17.24 | 5504.21 | 3.67 |  | -1.14 | 94
18163 | 89.03 | 133.27 | 12530.14 | -2404.42 | 5419.8 | 1.69 |  | 174.32 | 5600.2 | -1.68 |  | 0.17 | 96
18257 | 87.36 | 133.94 | 12533.1 | -2469.21 | 5487.83 | 1.91 |  | 158.16 | 5694.15 | -1.78 |  | 0.71 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 45.51 | 31.78 | 69.47 | 323 | 373.15 | 5525.93 | 5044.44 | 134 | 350 | 260 | 180 | 22684.21 | 12000
Run | 65.64 | 30.12 | 75.28 | 324 | 366.1 | 5410.96 | 4810.96 | 134 | 337.33 | 260 | 190.14 | 21773.58 | 12000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/0B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
MWD hot hole charge |  |  |  |  | 06/01/2021 |  | 18 |  | 1250 |  | 1 | 1250
Dir & MWD /Gamma |  |  |  |  | 06/01/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/01/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 06/01/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 9100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/01/2021 | 00:00 | 00:05 | 0.08 | 17510 | 17514 | 4 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17510.00 t/17514.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 5500.00, Tq 22000.00, ROP 48.00, Diff 600.00, Temp 335.00
06/01/2021 | 00:05 | 00:10 | 0.08 | 17514 | 17514 | 0 | LAT | 7: BHA 7 | 10D | Check shot 93.57 133.63
06/01/2021 | 00:10 | 01:45 | 1.58 | 17514 | 17529 | 15 | LAT | 7: BHA 7 | 2J | Slide Drill f/17514.00 t/17529.00, TF 180.00G, w/WOB 30.00,Flow 375.00, Press 5100.00, Tq 0.00, ROP 9.47, Diff 200.00, Temp 330.00
06/01/2021 | 01:45 | 02:15 | 0.5 | 17529 | 17566 | 37 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17529.00 t/17566.00, w/WOB 28.00,Flow 375.00, RPM 60.00, Press 5500.00, Tq 22000.00, ROP 444.00, Diff 600.00, Temp 334.00
06/01/2021 | 02:15 | 02:20 | 0.08 | 17566 | 17566 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 02:20 | 02:40 | 0.33 | 17566 | 17597 | 31 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17566.00 t/17597.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5500.00, Tq 22000.00, ROP 93.00, Diff 600.00, Temp 334.00
06/01/2021 | 02:40 | 02:45 | 0.08 | 17597 | 17597 | 0 | LAT | 7: BHA 7 | 10D | Check shot 92.02 133.60
06/01/2021 | 02:45 | 03:20 | 0.58 | 17597 | 17660 | 63 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17597.00 t/17660.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5500.00, Tq 22000.00, ROP 108.00, Diff 600.00, Temp 333.00
06/01/2021 | 03:20 | 03:25 | 0.08 | 17660 | 17660 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 03:25 | 03:30 | 0.08 | 17660 | 17667 | 7 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17660.00 t/17667.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5500.00, Tq 22000.00, ROP 84.00, Diff 600.00, Temp 334.00
06/01/2021 | 03:30 | 03:50 | 0.33 | 17667 | 17667 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 03:50 | 05:50 | 2 | 17667 | 17685 | 18 | LAT | 7: BHA 7 | 2J | Slide Drill f/17667.00 t/17685.00, TF 180.00G, w/WOB 35.00,Flow 375.00, Press 5100.00, Tq 0.00, ROP 9.00, Diff 200.00, Temp 331.00
06/01/2021 | 05:50 | 06:50 | 1 | 17685 | 17755 | 70 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17685.00 t/17755.00, w/WOB 35.00,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 70.00, Diff 200.00, Temp 338.00
06/01/2021 | 06:50 | 07:25 | 0.58 | 17755 | 17755 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 07:25 | 08:30 | 1.08 | 17755 | 17831 | 76 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17755.00 t/17831.00, w/WOB 35.00,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 70.15, Diff 200.00, Temp 342.00
06/01/2021 | 08:30 | 09:30 | 1 | 17831 | 17831 | 0 | LAT | 7: BHA 7 | 5D | Cir out Gas
06/01/2021 | 09:30 | 09:50 | 0.33 | 17831 | 17838 | 7 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17831.00 t/17838.00, w/WOB 35.00,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 21.00, Diff 200.00, Temp 338.00
06/01/2021 | 09:50 | 10:30 | 0.67 | 17838 | 17838 | 0 | LAT | 7: BHA 7 | 5D | Cir out Gas
06/01/2021 | 10:30 | 10:50 | 0.33 | 17838 | 17849 | 11 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17838.00 t/17849.00, w/WOB 35.00,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 33.00, Diff 200.00, Temp 338.00
06/01/2021 | 10:50 | 10:55 | 0.08 | 17849 | 17849 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 10:55 | 11:10 | 0.25 | 17849 | 17862 | 13 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17849.00 t/17862.00, w/WOB 35.00,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 52.00, Diff 200.00, Temp 340.00
06/01/2021 | 11:10 | 11:40 | 0.5 | 17862 | 17867 | 5 | LAT | 7: BHA 7 | 2J | Slide Drill f/17930.00 t/17942.00, TF 0G, w/WOB 45,Flow 375.00, Press 5100.00, Tq 0.00, ROP 16.00, Diff 200.00, Temp 333.00
06/01/2021 | 11:40 | 12:15 | 0.58 | 17867 | 17867 | 0 | LAT | 7: BHA 7 | 5D | Cir out Gas
06/01/2021 | 12:15 | 13:45 | 1.5 | 17867 | 17930 | 63 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17867.00 t/17930.00, w/WOB 35.00,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 42.00, Diff 200.00, Temp 333.00
06/01/2021 | 13:45 | 14:00 | 0.25 | 17930 | 17930 | 0 | LAT | 7: BHA 7 | 3D | Reaming for slide
06/01/2021 | 14:00 | 14:45 | 0.75 | 17930 | 17942 | 12 | LAT | 7: BHA 7 | 2J | Slide Drill f/17930.00 t/17942.00, TF 0G, w/WOB 45,Flow 375.00, Press 5100.00, Tq 0.00, ROP 16.00, Diff 200.00, Temp 333.00
06/01/2021 | 14:45 | 14:50 | 0.08 | 17942 | 17942 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 14:50 | 15:40 | 0.83 | 17942 | 18021 | 79 | LAT | 7: BHA 7 | 2K | Rotary Drill f/17942.00 t/18021.00, w/WOB 35,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 94.80, Diff 200.00, Temp 333.00
06/01/2021 | 15:40 | 15:50 | 0.17 | 18021 | 18021 | 0 | LAT | 7: BHA 7 | 3D | Reaming for slide
06/01/2021 | 15:50 | 16:35 | 0.75 | 18021 | 18031 | 10 | LAT | 7: BHA 7 | 2J | Slide Drill f/18021.00 t/18031.00, TF 0G, w/WOB 45.00,Flow 375.00, Press 5100.00, Tq 0.00, ROP 13.33, Diff 200.00, Temp 333.00
06/01/2021 | 16:35 | 16:45 | 0.17 | 18031 | 18040 | 9 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18031.00 t/18040.00, w/WOB 35,Flow 375.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 54.00, Diff 200.00, Temp 334.00
06/01/2021 | 16:45 | 17:00 | 0.25 | 18040 | 18040 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 17:00 | 17:55 | 0.92 | 18040 | 18116 | 76 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18040.00 t/18116.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5700.00, Tq 23000.00, ROP 82.91, Diff 600.00, Temp 336.00
06/01/2021 | 17:55 | 18:05 | 0.17 | 18116 | 18116 | 0 | LAT | 7: BHA 7 | 3D | Ream for slide
06/01/2021 | 18:05 | 18:10 | 0.08 | 18116 | 18116 | 0 | LAT | 7: BHA 7 | 10D | Check shot @ 18049 90.23 133.13
06/01/2021 | 18:10 | 18:35 | 0.42 | 18116 | 18122 | 6 | LAT | 7: BHA 7 | 2J | Slide Drill f/18116.00 t/18122.00, TF 180.00G, w/WOB 25.00,Flow 375.00, Press 5300.00, Tq 0.00, ROP 14.40, Diff 200.00, Temp 336.00
06/01/2021 | 18:35 | 18:45 | 0.17 | 18122 | 18122 | 0 | LAT | 7: BHA 7 | 10C | RFD froze up, recycle pumps and wait for tool face
06/01/2021 | 18:45 | 19:30 | 0.75 | 18122 | 18131 | 9 | LAT | 7: BHA 7 | 2J | Slide Drill f/18122.00 t/18131.00, TF 180.00G, w/WOB 25.00,Flow 375.00, Press 5300.00, Tq 0.00, ROP 12.00, Diff 200.00, Temp 336.00
06/01/2021 | 19:30 | 19:35 | 0.08 | 18131 | 18134 | 3 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18131.00 t/18134.00, w/WOB 30.00,Flow 375.00, RPM 70.00, Press 5700.00, Tq 23000.00, ROP 36.00, Diff 600.00, Temp 336.00
06/01/2021 | 19:35 | 19:50 | 0.25 | 18134 | 18134 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 19:50 | 21:10 | 1.33 | 18134 | 18230 | 96 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18134.00 t/18230.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 5700.00, Tq 24000.00, ROP 72.00, Diff 600.00, Temp 345.00
06/01/2021 | 21:10 | 21:15 | 0.08 | 18230 | 18230 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 21:15 | 21:20 | 0.08 | 18230 | 18240 | 10 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18230.00 t/18240.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 6100, Tq 25000, ROP 120.00, Diff 600.00, Temp 345.00
06/01/2021 | 21:20 | 21:30 | 0.17 | 18240 | 18240 | 0 | LAT | 7: BHA 7 | 3D | Ream for slide
06/01/2021 | 21:30 | 22:05 | 0.58 | 18240 | 18248 | 8 | LAT | 7: BHA 7 | 2J | Slide Drill f/18240.00 t/18248.00, TF 180G, w/WOB 25.00,Flow 375.00, Press 5700, Tq 0, ROP 13.71, Diff 200.00, Temp 341.00
06/01/2021 | 22:05 | 23:10 | 1.08 | 18248 | 18324 | 76 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18248.00 t/18324.00, w/WOB 25.00,Flow 375.00, RPM 70.00, Press 6100.00, Tq 25000.00, ROP 70.15, Diff 600.00, Temp 344.00
06/01/2021 | 23:10 | 23:45 | 0.58 | 18324 | 18324 | 0 | LAT | 7: BHA 7 | 8P | Rig Service
06/01/2021 | 23:45 | 23:50 | 0.08 | 18324 | 18324 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/01/2021 | 23:50 | 24:00 | 0.17 | 18324 | 18333 | 9 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18324.00 t/18333.00, w/WOB 25.00,Flow 325.00, RPM 70.00, Press 5200.00, Tq 25000.00, ROP 54.00, Diff 600.00, Temp 347.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_2_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 23 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/02/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9100 |  |  | Well Cost($): |  | 262630
|  |  |  | 24hr Summary: |  | Drill ahead in lateral, POOH f/ pressure loss, LDDP
|  |  |  | 24hr Lookahead: |  | LDDP, L/D tools, Set packer
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18333 |  | 15494 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 18577 |  | 18577 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  | 244 |  | 3083 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 44
Slide Drilled (Usft): |  | 16 |  | 290 | [5 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 228 |  | 2793 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.30
Drlg/Circ Hrs: |  | 8.08 / 15.42 |  | 51.33 / 20.92 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 1.5 |  | 19.92 |  | SN: |  | 13558789 |  | 10s Gel: | 5 | Weight (ppg): | 11
Rotary Drilling Hrs: |  | 6.58 |  | 31.42 |  | Bit # |  | 6 |  | PH / Temp(F) | 0.0 / 338.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 34.63 / 10.67 |  | 88.90 / 14.56 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 90.67 |  | Grade In: |  | New
% Slide: |  | 6.56 |  | 9.41 |  | Grade Out: |  | 4-6-BT-A-X-I-WT-HP
% Rotary: |  | 93.44 |  | 90.59 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.021 |  |  |  | 5.5 | 2 |  |  |  |  | 33.08 |  | 33.83
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.93
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.37
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.44
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.63
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.62
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.4
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.97
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.04
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.36
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.52
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.52
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.7 |  | 2813.22
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.25
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 20.82 |  | 5972.07
5972.07
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18352 | 86.04 | 133.98 | 12538.57 | -2535.04 | 5556.09 | 1.39 |  | 178.27 | 5788.98 | -1.39 |  | 0.04 | 95
18446 | 87.49 | 133.59 | 12543.87 | -2599.98 | 5623.85 | 1.6 |  | -15.04 | 5882.82 | 1.54 |  | -0.41 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 30.19 | 25 | 70 | 308 | 350 | 5512.5 | 5075 | 134 | 350 | 260 | 180 | 25000 | 12000
Run | 60.06 | 29.62 | 74.91 | 323 | 364.51 | 5420.99 | 4837.04 | 134 | 338.58 | 260 | 189.14 | 22000 | 12000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/02/2021 |  | 4 |  | 6850 |  | 1 | 6850
Real Time Survey Management |  |  |  |  | 06/02/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 06/02/2021 |  | 18 |  | 1250 |  | 1 | 1250
Perdiem |  |  |  |  | 06/02/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 9100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/02/2021 | 00:00 | 00:10 | 0.17 | 18333 | 18341 | 8 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18333.00 t/18341.00, w/WOB 25.00,Flow 325.00, RPM 70.00, Press 5200.00, Tq 25000.00, ROP 48.00, Diff 600.00, Temp 347.00
06/02/2021 | 00:10 | 00:15 | 0.08 | 18341 | 18341 | 0 | LAT | 7: BHA 7 | 3D | Ream for slide
06/02/2021 | 00:15 | 00:55 | 0.67 | 18341 | 18348 | 7 | LAT | 7: BHA 7 | 2J | Slide Drill f/18341.00 t/18348.00, TF 180.00G, w/WOB 25.00,Flow 375.00, Press 5700.00, Tq 0.00, ROP 10.50, Diff 200.00, Temp 342.00
06/02/2021 | 00:55 | 02:00 | 1.08 | 18348 | 18387 | 39 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18348.00 t/18387.00, w/WOB 25.00,Flow 325.00, RPM 70.00, Press 5200.00, Tq 25000.00, ROP 36.00, Diff 600.00, Temp 344.00
06/02/2021 | 02:00 | 03:00 | 1 | 18387 | 18387 | 0 | LAT | 7: BHA 7 | 5D | Circulate out gas
06/02/2021 | 03:00 | 03:30 | 0.5 | 18387 | 18419 | 32 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18387.00 t/18419.00, w/WOB 25.00,Flow 325.00, RPM 70.00, Press 5300.00, Tq 25000.00, ROP 64.00, Diff 600.00, Temp 342.00
06/02/2021 | 03:30 | 03:35 | 0.08 | 18419 | 18419 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/02/2021 | 03:35 | 04:05 | 0.5 | 18419 | 18442 | 23 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18419.00 t/18442.00, w/WOB 25.00,Flow 325.00, RPM 70.00, Press 5300.00, Tq 25000.00, ROP 46.00, Diff 600.00, Temp 342.00
06/02/2021 | 04:05 | 04:15 | 0.17 | 18442 | 18442 | 0 | LAT | 7: BHA 7 | 10D | Check shot @ 18375 85.47 133.74
06/02/2021 | 04:15 | 05:05 | 0.83 | 18442 | 18451 | 9 | LAT | 7: BHA 7 | 2J | Slide Drill f/18442.00 t/18451.00, TF -20.00G, w/WOB 25.00,Flow 375.00, Press 5800.00, Tq 0.00, ROP 10.80, Diff 300.00, Temp 338.00
06/02/2021 | 05:05 | 07:30 | 2.42 | 18451 | 18513 | 62 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18451.00 t/18513.00, w/WOB 25.00,Flow 375.00, RPM 0.00, Press 5800.00, Tq 0.00, ROP 25.66, Diff 300.00, Temp 338.00
06/02/2021 | 07:30 | 07:35 | 0.08 | 18513 | 18513 | 0 | LAT | 7: BHA 7 | 10D | Survey & Connection
06/02/2021 | 07:35 | 09:30 | 1.92 | 18513 | 18577 | 64 | LAT | 7: BHA 7 | 2K | Rotary Drill f/18513.00 t/18577.00, w/WOB 25.00,Flow 375.00, RPM 0.00, Press 5800.00, Tq 0.00, ROP 33.39, Diff 300.00, Temp 338.00
06/02/2021 | 09:30 | 10:30 | 1 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 5A | Circulate to POOH f/ Pressure loss and loss of torque
06/02/2021 | 10:30 | 19:30 | 9 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 3D | Back ream out t/13000
06/02/2021 | 19:30 | 20:30 | 1 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 5A | Circulate
06/02/2021 | 20:30 | 21:30 | 1 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 3D | Back ream out t/11974
06/02/2021 | 21:30 | 23:50 | 2.33 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 5A | Circulate b/u and spot mud cap
06/02/2021 | 23:50 | 24:00 | 0.17 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_3_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 24 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/03/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 269880
|  |  |  | 24hr Summary: |  | POOH, LDDP, Set packer, LDDP
|  |  |  | 24hr Lookahead: |  | Standby on location
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18577 |  | 15494 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 18577 |  | 18577 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  |  |  | 3083 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 44
Slide Drilled (Usft): |  |  |  | 290 | [5 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): |  |  |  | 2793 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.30
Drlg/Circ Hrs: |  |  |  | 51.33 / 20.92 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  |  |  | 19.92 |  | SN: |  | 13558789 |  | 10s Gel: | 5 | Weight (ppg): | 11
Rotary Drilling Hrs: |  |  |  | 31.42 |  | Bit # |  | 6 |  | PH / Temp(F) | 0.0 / 338.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 88.90 / 14.56 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 16 |  | 106.67 |  | Grade In: |  | New
% Slide: |  |  |  | 9.41 |  | Grade Out: |  | 4-6-BT-A-X-I-WT-HP
% Rotary: |  |  |  | 90.59 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 2.12 Slick HS88 0.021 |  |  |  | 5.5 | 2 |  |  |  |  | 33.08 |  | 33.83
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.93
Pony Collar |  |  |  | 5.062 | 2.75 |  |  |  |  | 9.44 |  | 45.37
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.07 |  | 48.44
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.19 |  | 78.63
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.99 |  | 88.62
NMDC |  |  |  | 4.938 | 2.75 |  |  |  |  | 30.78 |  | 119.4
Tomax |  |  |  | 4.938 | 2.25 |  |  |  |  | 17.57 |  | 136.97
Crossover |  |  |  | 5.125 | 2.25 |  |  |  |  | 3.07 |  | 140.04
2 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 188.32 |  | 328.36
Reamer |  |  |  | 5.188 | 2.5 |  |  |  |  | 8.16 |  | 336.52
26 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2453 |  | 2789.52
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 23.7 |  | 2813.22
33 Std Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 3138.03 |  | 5951.25
Agitator |  |  |  | 5.25 | 2.75 |  |  |  |  | 20.82 |  | 5972.07
5972.07
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250010 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 25 | 70 | 308 | 350 | 5512.5 | 5075 | 134 | 350 | 260 | 180 | 25000 | 12000
Run | 60.06 | 29.62 | 74.91 | 323 | 364.51 | 5420.99 | 4837.04 | 134 | 338.58 | 260 | 189.14 | 22000 | 12000
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/03/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/03/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/03/2021 | 00:00 | 01:35 | 1.58 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 6B | POOH
06/03/2021 | 01:35 | 02:00 | 0.42 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 6I | Flow check
06/03/2021 | 02:00 | 15:00 | 13 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 6K | LD DS42 Drill pipe
06/03/2021 | 15:00 | 16:00 | 1 | 18577 | 18577 | 0 | LAT | 7: BHA 7 | 6P | Rack Back BHA
06/03/2021 | 16:00 | 24:00 | 8 | 18577 | 18577 | 0 | LAT |  | 24B | Standby on location
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_5_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 26 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/05/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4200 |  |  | Well Cost($): |  | 274080
|  |  |  | 24hr Summary: |  | Standby on location
|  |  |  | 24hr Lookahead: |  | Standby on location
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18577 |  |  |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 18577 |  | 18577 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 44
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.30
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 5 | Weight (ppg): | 11
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 338.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
STBY |  |  |  |  | 06/05/2021 |  | 2 |  | 3800 |  | 1 | 3800
Perdiem |  |  |  |  | 06/05/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 4200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/05/2021 | 00:00 | 04:00 | 4 | 18577 | 18577 | 0 | LAT |  | 24B | Standby on location
06/05/2021 | 04:00 | 05:15 | 1.25 | 18577 | 18577 | 0 | LAT |  | 24B | LD BHA #7 out of derrick
06/05/2021 | 05:15 | 09:30 | 4.25 | 18577 | 18577 | 0 | LAT |  | 24B | L/D DP
06/05/2021 | 09:30 | 11:30 | 2 | 18577 | 18577 | 0 | LAT |  | 6L | Rack Back BHA
06/05/2021 | 11:30 | 14:30 | 3 | 18577 | 18577 | 0 | LAT |  | 9A | Slip and Cut / Rig Service
06/05/2021 | 14:30 | 24:00 | 9.5 | 18577 | 18577 | 0 | LAT |  | 24B | Standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_6_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 27 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/06/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 20050 |  |  | Well Cost($): |  | 294130
|  |  |  | 24hr Summary: |  | Standby, M/U BHA #8, TIH
|  |  |  | 24hr Lookahead: |  | TIH, Drill ahead
Drilling Summary |  | 24Hr (BHA 8) |  | Run (BHA 8) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18577 |  | 18577 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 18577 |  | 18577 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 44
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.30
Drlg/Circ Hrs: |  | 0.00 / 0.50 |  | 0.00 / 0.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: | [5 empty] | SN: |  | 13594950 |  | 10s Gel: | 5 | Weight (ppg): | 11
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 7 |  | PH / Temp(F) | 0.0 / 338.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 20 |  | 20 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  |  |  | 5.5 | 2 |  |  |  |  | 32.95 |  | 33.7
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.8
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.86 |  | 45.66
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.63 |  | 49.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.72 |  | 80.01
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.29 |  | 89.3
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.86 |  | 120.16
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 17.65 |  | 137.81
Crossover |  |  |  | 5.312 | 2.75 |  |  |  |  | 3.64 |  | 141.45
2 Stds 4.5 Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 189.58 |  | 331.03
6 13/16 Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.41 |  | 339.44
26 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 2460.5 |  | 2799.94
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 22.42 |  | 2822.36
33 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3118.79 |  | 5941.15
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 21.95 |  | 5963.1
32 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3018.22 |  | 8981.32
11 Stds 4.5 HWDP |  |  |  | 4.5 | 3 |  |  |  |  | 1005.65 |  | 9986.97
9986.97
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.09 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 06/06/2021 |  | 11 |  | 800 |  | 1 | 800
Dir & MWD /Gamma |  |  |  |  | 06/06/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/06/2021 |  | 5 |  | 100 |  | 4 | 400
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 06/06/2021 |  | 15 |  | 1000 |  | 1 | 1000
5.5 Premium Motor Stator Reline |  |  |  |  | 06/06/2021 |  | 12 |  | 9000 |  | 1 | 9000
Pro Azimuthal Gamma Ray |  |  |  |  | 06/06/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 20050
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/06/2021 | 00:00 | 03:30 | 3.5 | 18577 | 18577 | 0 | LAT |  | 24B | Standby
06/06/2021 | 03:30 | 04:00 | 0.5 | 18577 | 18577 | 0 | LAT | 8: BHA 8 | 6O | M/U BHA #8 out of derrick
06/06/2021 | 04:00 | 19:45 | 15.75 | 18577 | 18577 | 0 | LAT | 8: BHA 8 | 6A | Trip in hole picking up singles
06/06/2021 | 19:45 | 20:15 | 0.5 | 18577 | 18577 | 0 | LAT | 8: BHA 8 | 5A | Orient into sidetrack and confirm
06/06/2021 | 20:15 | 24:00 | 3.75 | 18577 | 18577 | 0 | LAT | 8: BHA 8 | 6A | Trip in hole picking up singles
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_7_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 28 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/07/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 23100 |  |  | Well Cost($): |  | 317230
|  |  |  | 24hr Summary: |  | TIH picking up singles, Drill ahead in lateral
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 8) |  | Run (BHA 8) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18577 |  | 18577 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 19351 |  | 19351 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  | 774 |  | 774 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 17 | Viscosity: | 43
Slide Drilled (Usft): |  | 88 |  | 88 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 686 |  | 686 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.80
Drlg/Circ Hrs: |  | 9.67 / 3.00 |  | 9.67 / 3.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 72/28
Slide Drilling Hrs: |  | 4.67 |  | 4.67 |  | SN: |  | 13594950 |  | 10s Gel: | 5 | Weight (ppg): | 11.4
Rotary Drilling Hrs: |  | 5 |  | 5 |  | Bit # |  | 7 |  | PH / Temp(F) | 0.0 / 334.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 137.20 / 18.86 |  | 137.20 / 18.86 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 44 |  | Grade In: |  | New
% Slide: |  | 11.37 |  | 11.37 |  | Grade Out:
% Rotary: |  | 88.63 |  | 88.63 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  |  |  | 5.5 | 2 |  |  |  |  | 32.95 |  | 33.7
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.8
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.86 |  | 45.66
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.63 |  | 49.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.72 |  | 80.01
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.29 |  | 89.3
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.86 |  | 120.16
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 17.65 |  | 137.81
Crossover |  |  |  | 5.312 | 2.75 |  |  |  |  | 3.64 |  | 141.45
2 Stds 4.5 Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 189.58 |  | 331.03
6 13/16 Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.41 |  | 339.44
26 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 2460.5 |  | 2799.94
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 22.42 |  | 2822.36
33 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3118.79 |  | 5941.15
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 21.95 |  | 5963.1
32 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3018.22 |  | 8981.32
11 Stds 4.5 HWDP |  |  |  | 4.5 | 3 |  |  |  |  | 1005.65 |  | 9986.97
9986.97
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.09 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
18527 | 89.37 | 132.76 | 12546.09 | -2655.38 | 5682.89 | 2.54 |  | -23.83 | 5963.79 | 2.32 |  | -1.02 | 81
18621 | 89.8 | 133.12 | 12546.77 | -2719.42 | 5751.71 | 0.6 |  | 39.94 | 6057.78 | 0.46 |  | 0.38 | 94
18715 | 90.38 | 132.96 | 12546.62 | -2783.57 | 5820.41 | 0.64 |  | -15.42 | 6151.78 | 0.62 |  | -0.17 | 94
18810 | 86.1 | 131.55 | 12549.54 | -2847.41 | 5890.67 | 4.74 |  | -161.79 | 6246.7 | -4.51 |  | -1.48 | 95
18905 | 87.21 | 131.75 | 12555.08 | -2910.43 | 5961.53 | 1.19 |  | 10.2 | 6341.51 | 1.17 |  | 0.21 | 95
18998 | 83.66 | 130.46 | 12562.48 | -2971.37 | 6031.37 | 4.06 |  | -160.14 | 6434.14 | -3.82 |  | -1.39 | 93
19092 | 83.5 | 130.59 | 12573 | -3032.07 | 6102.38 | 0.22 |  | 141.09 | 6527.46 | -0.17 |  | 0.14 | 94
19187 | 86.49 | 132.3 | 12581.28 | -3094.7 | 6173.3 | 3.62 |  | 29.75 | 6622.04 | 3.15 |  | 1.8 | 95
19283 | 87.3 | 132.87 | 12586.48 | -3159.57 | 6243.88 | 1.03 |  | 35.11 | 6717.9 | 0.84 |  | 0.59 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 80.07 | 25.35 | 80 | 318 | 350 | 6575 | 5800 | 0 | 330 | 230 | 150 | 20000 | 0
Run | 80.07 | 25.35 | 80 | 318 | 350 | 6575 | 5800 | 0 | 330 | 230 | 150 | 20000 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 06/07/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/07/2021 |  | 5 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/07/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 06/07/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray Core charge >330F |  |  |  |  | 06/07/2021 |  | 19 |  | 12000 |  | 1 | 12000
MWD hot hole charge |  |  |  |  | 06/07/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 23100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/07/2021 | 00:00 | 04:45 | 4.75 | 18577 | 18577 | 0 | LAT | 8: BHA 8 | 6A | Trip in hole picking up singles
06/07/2021 | 04:45 | 07:20 | 2.58 | 18577 | 18577 | 0 | LAT | 8: BHA 8 | 3C | Reaming to Bottom
06/07/2021 | 07:20 | 07:40 | 0.33 | 18577 | 18582 | 5 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18577.00 t/18582.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 15.00, Diff 800.00, Temp 325.00
06/07/2021 | 07:40 | 08:05 | 0.42 | 18582 | 18596 | 14 | LAT | 8: BHA 8 | 2J | Slide Drill f/18582.00 t/18596.00, TF 180.00G, w/WOB 30.00,Flow 350.00, Press 6600.00, Tq 20000.00, ROP 33.60, Diff 800.00, Temp 325.00
06/07/2021 | 08:05 | 08:20 | 0.25 | 18596 | 18596 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 08:20 | 08:50 | 0.5 | 18596 | 18689 | 93 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18596.00 t/18689.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 186.00, Diff 800.00, Temp 325.00
06/07/2021 | 08:50 | 09:10 | 0.33 | 18689 | 18689 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 09:10 | 09:15 | 0.08 | 18689 | 18694 | 5 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18689.00 t/18694.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 60.00, Diff 800.00, Temp 325.00
06/07/2021 | 09:15 | 10:20 | 1.08 | 18694 | 18707 | 13 | LAT | 8: BHA 8 | 2J | Slide Drill f/18694.00 t/18707.00, TF 180.00G, w/WOB 30.00,Flow 350.00, Press 6600.00, Tq 20000.00, ROP 12.00, Diff 800.00, Temp 325.00
06/07/2021 | 10:20 | 10:45 | 0.42 | 18707 | 18707 | 0 | LAT | 8: BHA 8 | 5A | Screw back into Pipe
06/07/2021 | 10:45 | 11:05 | 0.33 | 18707 | 18761 | 54 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18707.00 t/18761.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 162.00, Diff 800.00, Temp 325.00
06/07/2021 | 11:05 | 11:45 | 0.67 | 18761 | 18770 | 9 | LAT | 8: BHA 8 | 2J | Slide Drill f/18761.00 t/18770.00, TF 180.00G, w/WOB 30.00,Flow 350.00, Press 6600.00, Tq 20000.00, ROP 13.50, Diff 800.00, Temp 325.00
06/07/2021 | 11:45 | 12:00 | 0.25 | 18770 | 18783 | 13 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18770.00 t/18783.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 52.00, Diff 800.00, Temp 325.00
06/07/2021 | 12:00 | 12:15 | 0.25 | 18783 | 18783 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 12:15 | 12:20 | 0.08 | 18783 | 18788 | 5 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18783.00 t/18788.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 60.00, Diff 800.00, Temp 325.00
06/07/2021 | 12:20 | 13:00 | 0.67 | 18788 | 18808 | 20 | LAT | 8: BHA 8 | 2J | Slide Drill f/18788.00 t/18808.00, TF 180.00G, w/WOB 20.00,Flow 350.00, Press 6600.00, Tq 20000.00, ROP 30.00, Diff 800.00, Temp 325.00
06/07/2021 | 13:00 | 13:40 | 0.67 | 18808 | 18878 | 70 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18808.00 t/18878.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 105.00, Diff 800.00, Temp 325.00
06/07/2021 | 13:40 | 14:15 | 0.58 | 18878 | 18878 | 0 | LAT | 8: BHA 8 | 23E | Wait on Geo
06/07/2021 | 14:15 | 14:50 | 0.58 | 18878 | 18941 | 63 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18878.00 t/18941.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 108.00, Diff 800.00, Temp 329.00
06/07/2021 | 14:50 | 15:50 | 1 | 18941 | 18961 | 20 | LAT | 8: BHA 8 | 2J | Slide Drill f/18941.00 t/18961.00, TF 180G, w/WOB 25.00,Flow 350.00, Press 6600.00, Tq 20000.00, ROP 20.00, Diff 800.00, Temp 325.00
06/07/2021 | 15:50 | 16:05 | 0.25 | 18961 | 18973 | 12 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18961.00 t/18973.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 72.00, Diff 800.00, Temp 325.00
06/07/2021 | 16:05 | 17:40 | 1.58 | 18973 | 18973 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 17:40 | 18:05 | 0.42 | 18973 | 19066 | 93 | LAT | 8: BHA 8 | 2K | Rotary Drill f/18973.00 t/19066.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 223.20, Diff 800.00, Temp 331.00
06/07/2021 | 18:05 | 18:15 | 0.17 | 19066 | 19066 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 18:15 | 18:40 | 0.42 | 19066 | 19131 | 65 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19066.00 t/19131.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 156.00, Diff 800.00, Temp 336.00
06/07/2021 | 18:40 | 18:45 | 0.08 | 19131 | 19131 | 0 | LAT | 8: BHA 8 | 10D | Check shot @ 19063, 83.17, 131.29
06/07/2021 | 18:45 | 19:35 | 0.83 | 19131 | 19143 | 12 | LAT | 8: BHA 8 | 2J | Slide Drill f/19131.00 t/19143.00, TF 20.00G, w/WOB 20.00,Flow 350.00, Press 6100.00, Tq 0.00, ROP 14.40, Diff 300.00, Temp 332.00
06/07/2021 | 19:35 | 19:45 | 0.17 | 19143 | 19160 | 17 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19143.00 t/19160.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 102.00, Diff 800.00, Temp 331.00
06/07/2021 | 19:45 | 19:50 | 0.08 | 19160 | 19160 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 19:50 | 20:20 | 0.5 | 19160 | 19255 | 95 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19160.00 t/19255.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 190.00, Diff 800.00, Temp 334.00
06/07/2021 | 20:20 | 20:25 | 0.08 | 19255 | 19255 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/07/2021 | 20:25 | 20:50 | 0.42 | 19255 | 19351 | 96 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19255.00 t/19351.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 230.40, Diff 800.00, Temp 334.00
06/07/2021 | 20:50 | 24:00 | 3.17 | 19351 | 19351 | 0 | LAT | 8: BHA 8 | 8A | Change adjustment bolts on top drive carriage.
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_8_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 29 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/08/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 11100 |  |  | Well Cost($): |  | 328330
|  |  |  | 24hr Summary: |  | Drill ahead in lateral
|  |  |  | 24hr Lookahead: |  | Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 8) |  | Run (BHA 8) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 19351 |  | 18577 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 20659 |  | 20659 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  | 1308 |  | 2082 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 17 | Viscosity: | 43
Slide Drilled (Usft): |  | 42 |  | 130 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  | 1266 |  | 1952 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.80
Drlg/Circ Hrs: |  | 10.75 / 6.17 |  | 20.42 / 9.67 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 72/28
Slide Drilling Hrs: |  | 2.17 |  | 6.83 |  | SN: |  | 13594950 |  | 10s Gel: | 5 | Weight (ppg): | 11.4
Rotary Drilling Hrs: |  | 8.58 |  | 13.58 |  | Bit # |  | 7 |  | PH / Temp(F) | 0.0 / 334.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 147.50 / 19.38 |  | 143.71 / 19.02 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 68 |  | Grade In: |  | New
% Slide: |  | 3.21 |  | 6.24 |  | Grade Out:
% Rotary: |  | 96.79 |  | 93.76 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  |  |  | 5.5 | 2 |  |  |  |  | 32.95 |  | 33.7
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.8
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.86 |  | 45.66
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.63 |  | 49.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.72 |  | 80.01
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.29 |  | 89.3
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.86 |  | 120.16
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 17.65 |  | 137.81
Crossover |  |  |  | 5.312 | 2.75 |  |  |  |  | 3.64 |  | 141.45
2 Stds 4.5 Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 189.58 |  | 331.03
6 13/16 Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.41 |  | 339.44
26 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 2460.5 |  | 2799.94
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 22.42 |  | 2822.36
33 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3118.79 |  | 5941.15
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 21.95 |  | 5963.1
32 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3018.22 |  | 8981.32
11 Stds 4.5 HWDP |  |  |  | 4.5 | 3 |  |  |  |  | 1005.65 |  | 9986.97
9986.97
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.09 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
19377 | 85.53 | 133.9 | 12592.36 | -3224 | 6312.06 | 2.18 |  | 149.88 | 6811.71 | -1.88 |  | 1.1 | 94
19470 | 85.11 | 134.22 | 12599.95 | -3288.46 | 6378.67 | 0.57 |  | 142.8 | 6904.38 | -0.45 |  | 0.34 | 93
19565 | 83.74 | 133.83 | 12609.18 | -3354.17 | 6446.65 | 1.5 |  | -164.2 | 6998.92 | -1.44 |  | -0.41 | 95
19658 | 83.2 | 133.37 | 12619.75 | -3417.89 | 6513.56 | 0.76 |  | -139.78 | 7091.31 | -0.58 |  | -0.49 | 93
19753 | 82.85 | 132.58 | 12631.29 | -3482.17 | 6582.55 | 0.9 |  | -114.1 | 7185.61 | -0.37 |  | -0.83 | 95
19848 | 84.72 | 134.06 | 12641.58 | -3546.96 | 6651.26 | 2.5 |  | 38.28 | 7280.04 | 1.97 |  | 1.56 | 95
19942 | 85.65 | 133.97 | 12649.47 | -3612.04 | 6718.62 | 0.99 |  | -5.51 | 7373.7 | 0.99 |  | -0.1 | 94
20036 | 85.82 | 133.78 | 12656.46 | -3677.01 | 6786.19 | 0.27 |  | -48.11 | 7467.43 | 0.18 |  | -0.2 | 94
20129 | 85.09 | 133.06 | 12663.83 | -3740.73 | 6853.53 | 1.1 |  | -135.51 | 7560.13 | -0.78 |  | -0.77 | 93
20224 | 84.57 | 132.87 | 12672.39 | -3805.22 | 6922.76 | 0.58 |  | -160.01 | 7654.74 | -0.55 |  | -0.2 | 95
20318 | 86.03 | 134.6 | 12680.09 | -3869.98 | 6990.45 | 2.4 |  | 49.82 | 7748.42 | 1.55 |  | 1.84 | 94
20412 | 86.29 | 133.16 | 12686.38 | -3934.99 | 7058.05 | 1.55 |  | -79.79 | 7842.19 | 0.28 |  | -1.53 | 94
20507 | 86.69 | 132.99 | 12692.2 | -3999.75 | 7127.31 | 0.46 |  | -22.99 | 7937.02 | 0.42 |  | -0.18 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 110 | 24.71 | 80 | 318 | 350 | 6342.86 | 5500 | 0 | 330 | 230 | 0 | 20666.67 | 0
Run | 89.58 | 25.19 | 80 | 318 | 350 | 6514.81 | 5688.89 | 0 | 330 | 230 | 150 | 20200 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 06/08/2021 |  | 5 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/08/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 06/08/2021 |  | 10 |  | 600 |  | 1 | 600
Dir & MWD /Gamma |  |  |  |  | 06/08/2021 |  | 4 |  | 6850 |  | 1 | 6850
MWD hot hole charge |  |  |  |  | 06/08/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 11100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/08/2021 | 00:00 | 00:30 | 0.5 | 19351 | 19351 | 0 | LAT | 8: BHA 8 | 8A | Change adjustment bolts on top drive carriage.
06/08/2021 | 00:30 | 00:40 | 0.17 | 19351 | 19351 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 00:40 | 00:45 | 0.08 | 19351 | 19361 | 10 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19351.00 t/19361.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 120.00, Diff 800.00, Temp 324.00
06/08/2021 | 00:45 | 01:25 | 0.67 | 19361 | 19376 | 15 | LAT | 8: BHA 8 | 2J | Slide Drill f/19361.00 t/19376.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 6200.00, Tq 0.00, ROP 22.50, Diff 400.00, Temp 324.00
06/08/2021 | 01:25 | 01:45 | 0.33 | 19376 | 19445 | 69 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19376.00 t/19445.00, w/WOB 26.00,Flow 350.00, RPM 80.00, Press 6600.00, Tq 20000.00, ROP 207.00, Diff 800.00, Temp 324.00
06/08/2021 | 01:45 | 01:50 | 0.08 | 19445 | 19445 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 01:50 | 02:25 | 0.58 | 19445 | 19538 | 93 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19445.00 t/19538.00, w/WOB 24,Flow 350.00, RPM 80.00, Press 6400, Tq 21000, ROP 159.43, Diff 900.00, Temp 332.00
06/08/2021 | 02:25 | 02:30 | 0.08 | 19538 | 19538 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 02:30 | 03:10 | 0.67 | 19538 | 19633 | 95 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19538.00 t/19633.00, w/WOB 24,Flow 350.00, RPM 80.00, Press 6400, Tq 21000, ROP 142.50, Diff 900.00, Temp 334.00
06/08/2021 | 03:10 | 03:15 | 0.08 | 19633 | 19633 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 03:15 | 03:50 | 0.58 | 19633 | 19726 | 93 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19633.00 t/19726.00, w/WOB 24,Flow 350.00, RPM 80.00, Press 6400, Tq 21000, ROP 159.43, Diff 900.00, Temp 336.00
06/08/2021 | 03:50 | 03:55 | 0.08 | 19726 | 19726 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 03:55 | 04:35 | 0.67 | 19726 | 19821 | 95 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19726.00 t/19821.00, w/WOB 24,Flow 350.00, RPM 80.00, Press 6400, Tq 21000, ROP 142.50, Diff 900.00, Temp 336.00
06/08/2021 | 04:35 | 04:40 | 0.08 | 19821 | 19821 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 04:40 | 04:45 | 0.08 | 19821 | 19831 | 10 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19821.00 t/19831.00, w/WOB 24.00,Flow 350.00, RPM 80.00, Press 6400.00, Tq 21000.00, ROP 120.00, Diff 900.00, Temp 330.00
06/08/2021 | 04:45 | 05:35 | 0.83 | 19831 | 19846 | 15 | LAT | 8: BHA 8 | 2J | Slide Drill f/19831.00 t/19846.00, TF 20G, w/WOB 22,Flow 350.00, Press 5900, Tq 0, ROP 18.00, Diff 400.00, Temp 330.00
06/08/2021 | 05:35 | 06:05 | 0.5 | 19846 | 19916 | 70 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19846.00 t/19916.00, w/WOB 22.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 140.00, Diff 400.00, Temp 336.00
06/08/2021 | 06:05 | 06:10 | 0.08 | 19916 | 19916 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 06:10 | 07:00 | 0.83 | 19916 | 20010 | 94 | LAT | 8: BHA 8 | 2K | Rotary Drill f/19916.00 t/20010.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 112.80, Diff 400.00, Temp 336.00
06/08/2021 | 07:00 | 07:05 | 0.08 | 20010 | 20010 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 07:05 | 07:40 | 0.58 | 20010 | 20104 | 94 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20010.00 t/20104.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 161.14, Diff 400.00, Temp 336.00
06/08/2021 | 07:40 | 07:50 | 0.17 | 20104 | 20104 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 07:50 | 08:35 | 0.75 | 20104 | 20197 | 93 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20104.00 t/20197.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 124.00, Diff 400.00, Temp 336.00
06/08/2021 | 08:35 | 08:45 | 0.17 | 20197 | 20197 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 08:45 | 09:20 | 0.58 | 20197 | 20292 | 95 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20197.00 t/20292.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 162.86, Diff 400.00, Temp 340.00
06/08/2021 | 09:20 | 09:30 | 0.17 | 20292 | 20292 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 09:30 | 09:35 | 0.08 | 20292 | 20303 | 11 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20292.00 t/20303.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 132.00, Diff 400.00, Temp 340.00
06/08/2021 | 09:35 | 10:15 | 0.67 | 20303 | 20315 | 12 | LAT | 8: BHA 8 | 2J | Slide Drill f/20303.00 t/20315.00, TF 0.00G, w/WOB 30.00,Flow 350.00, Press 5900.00, Tq 0.00, ROP 18.00, Diff 400.00, Temp 336.00
06/08/2021 | 10:15 | 10:45 | 0.5 | 20315 | 20386 | 71 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20315.00 t/20386.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 142.00, Diff 400.00, Temp 330.00
06/08/2021 | 10:45 | 10:55 | 0.17 | 20386 | 20386 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 10:55 | 11:30 | 0.58 | 20386 | 20480 | 94 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20386.00 t/20480.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 161.14, Diff 400.00, Temp 330.00
06/08/2021 | 11:30 | 11:35 | 0.08 | 20480 | 20480 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 11:35 | 12:10 | 0.58 | 20480 | 20575 | 95 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20480.00 t/20575.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 162.86, Diff 400.00, Temp 330.00
06/08/2021 | 12:10 | 12:15 | 0.08 | 20575 | 20575 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 12:15 | 12:50 | 0.58 | 20575 | 20659 | 84 | LAT | 8: BHA 8 | 2K | Rotary Drill f/20575.00 t/20659.00, w/WOB 25.00,Flow 350.00, RPM 0.00, Press 5900.00, Tq 21000.00, ROP 144.00, Diff 400.00, Temp 330.00
06/08/2021 | 12:50 | 12:50 | 0 | 20659 | 20659 | 0 | LAT | 8: BHA 8 | 10D | Survey & Connection
06/08/2021 | 12:50 | 19:00 | 6.17 | 20659 | 20659 | 0 | LAT | 8: BHA 8 | 5A | Circulate
06/08/2021 | 19:00 | 24:00 | 5 | 20659 | 20659 | 0 | LAT | 8: BHA 8 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 6_9_2021_DDR
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-149-33519 / 21DD0100MG |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 30 |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Longitude: |  | 96° 47' 33.480" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Fayette / Texas
|  |  |  | Date: |  | 06/09/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 11100 |  |  | Well Cost($): |  | 339430
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 8) |  | Run (BHA 8) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 20659 |  | 18577 |  | Csg Shoe MD(Usft): |  | 11974 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 20659 |  | 20659 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  |  |  | 2082 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 17 | Viscosity: | 43
Slide Drilled (Usft): |  |  |  | 130 | [5 empty] | 100: | 13 | Chlorides: | 55000
Rotary Drilled (Usft): |  |  |  | 1952 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 15.80
Drlg/Circ Hrs: |  |  |  | 20.42 / 9.67 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 72/28
Slide Drilling Hrs: |  |  |  | 6.83 |  | SN: |  | 13594950 |  | 10s Gel: | 5 | Weight (ppg): | 11.4
Rotary Drilling Hrs: |  |  |  | 13.58 |  | Bit # |  | 7 |  | PH / Temp(F) | 0.0 / 334.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 143.71 / 19.02 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 92 |  | Grade In: |  | New
% Slide: |  |  |  | 6.24 |  | Grade Out:
% Rotary: |  |  |  | 93.76 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jessie Collison |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | Bill Paul
Jim Harrison |  | Josh Ray |  | Jason Smetters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  |  |  | 5.5 | 2 |  |  |  |  | 32.95 |  | 33.7
BTI |  |  |  | 4.812 | 2.5 |  |  |  |  | 2.1 |  | 35.8
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.86 |  | 45.66
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.63 |  | 49.29
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.72 |  | 80.01
Pony Collar |  |  |  | 5 | 2.75 |  |  |  |  | 9.29 |  | 89.3
NMDC |  |  |  | 5 | 2.75 |  |  |  |  | 30.86 |  | 120.16
Tomax |  |  |  | 5 | 2.25 |  |  |  |  | 17.65 |  | 137.81
Crossover |  |  |  | 5.312 | 2.75 |  |  |  |  | 3.64 |  | 141.45
2 Stds 4.5 Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 189.58 |  | 331.03
6 13/16 Reamer |  |  |  | 5.375 | 2.562 |  |  |  |  | 8.41 |  | 339.44
26 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 2460.5 |  | 2799.94
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 22.42 |  | 2822.36
33 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3118.79 |  | 5941.15
Agitator |  |  |  | 5.312 | 2.75 |  |  |  |  | 21.95 |  | 5963.1
32 Stds 4.5 in Drill Pipe |  |  |  | 4.5 | 3 |  |  |  |  | 3018.22 |  | 8981.32
11 Stds 4.5 HWDP |  |  |  | 4.5 | 3 |  |  |  |  | 1005.65 |  | 9986.97
9986.97
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250022 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.09 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 24.71 | 80 | 318 | 350 | 6342.86 | 5500 | 0 | 330 | 230 | 0 | 20666.67 | 0
Run | 101.98 | 25.19 | 80 | 318 | 350 | 6514.81 | 5688.89 | 0 | 330 | 230 | 150 | 20200 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
2 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
3 | Triplex |  |  | 95 | 12 | 4.75 | 7500 |  | 7000 |  | 0.0630 / 2.6460
Comments
Plan 9 STO 1, Window 10A/5B
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
MWD hot hole charge |  |  |  |  | 06/09/2021 |  | 18 |  | 1250 |  | 1 | 1250
Real Time Survey Management |  |  |  |  | 06/09/2021 |  | 10 |  | 600 |  | 1 | 600
Dir & MWD /Gamma |  |  |  |  | 06/09/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 06/09/2021 |  | 5 |  | 100 |  | 4 | 400
Pro Azimuthal Gamma Ray |  |  |  |  | 06/09/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 11100
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
06/09/2021 | 00:00 | 22:30 | 22.5 | 20659 | 20659 | 0 | LAT | 8: BHA 8 | 6B | POOH
06/09/2021 | 22:30 | 24:00 | 1.5 | 20659 | 20659 | 0 | LAT | 8: BHA 8 | 6P | L/D BHA
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 397.46 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/12/2021 | Depth In: |  | 108 | Total Drilled: |  | 2925.00 (Usft)
Date Out: |  |  | 05/13/2021 | Depth Out: |  | 3033 | Drilling / Circ Hours: |  | 5.08 / 5.00
Survey Offset: |  |  | 72
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47245 | U616S | 13.5 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800075 | 7.75" 7/8 5.9 1.5F 13" NBS -.022 | 7.938 |  | 8.000 / 3.17 | 6 5/8 REG / 6 5/8 REG |  | 37.52 | 39.02
| 3 | SD610174 | Nortrak Stabilizer 13" | 8 | 3.25 | 8.000 / 3.17 | 6 5/8 REG / 6 5/8 REG |  | 6.74 | 45.76
| 4 | SD54328 | NMPC | 8.062 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 10.1 | 55.86
| 5 | 775151 | UBHO | 7.75 | 3 |  | 6 5/8 REG / 6 5/8 REG |  | 2.55 | 58.41
| 6 | SD55726 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.13 | 87.54
| 7 | SD56047 | NMDC | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.2 | 116.74
| 8 | SD114897 | Crossover Sub | 6.75 | 2.812 | 6.760 / 1.75 | 4 1/2 IF / 6 5/8 REG |  | 3.6 | 120.34
| 9 |  | 9 Jts HWDP | 5 | 3 |  |  |  | 277.12 | 397.46
| 10 | [8 empty] | 397.46
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | U616S |  |  | 2925
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7.75" 7/8 5.9 1.5F 13" NBS -.022 |  |  | PDCI / 7/8 5.9 | 0.00 / 1.50 |  | 13 | 0 | 0 | 0
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
0 |  |  | 0 | 100 |  |  | 0 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2671.58 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/14/2021 | Depth In: |  | 3033 | Total Drilled: |  | 8953.00 (Usft)
Date Out: |  |  | 05/19/2021 | Depth Out: |  | 11985 | Drilling / Circ Hours: |  | 78.42 / 18.95
Survey Offset: |  |  | 70 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 54682 | SPL613 | 9.875 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800055 | 8 7/8 5.9 2.0F Slick -.016 | 8 |  | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 37.58 | 39.08
| 3 | SD54328 | NMPC | 8.062 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 10.1 | 49.18
| 4 | 775151 | UBHO | 7.75 | 3 |  | 6 5/8 REG / 6 5/8 REG |  | 2.55 | 51.73
| 5 | SD55726 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.13 | 80.86
| 6 | SD56047 | NMDC | 7.938 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.2 | 110.06
| 7 | SD116860 | Crossover Sub | 6.5 | 2.375 | 6.760 / 1.75 | 4 1/2 XH / 6 5/8 REG |  | 2.35 | 112.41
| 8 | Rig | 2 Stds 6.5 in DC | 6.5 | 2.75 |  | 4 1/2 XH / 4 1/2 XH |  | 186.82 | 299.23
| 9 | SD3539 | Crossover Sub | 6.438 | 2.375 |  | 4 1/2 IF / 4 1/2 XH |  | 2.89 | 302.12
| 10 | Rig | 3 Stds 5 in HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 277.12 | 579.24
| 11 | Rig | 22 Stds 5 in DP | 5 | 2.563 |  | 4 1/2 IF / 4 1/2 IF |  | 2067.72 | 2646.96
| 12 | P6675-0022 | Agitator | 6.812 |  |  | 4 1/2 IF / 4 1/2 IF |  | 24.62 | 2671.58
| 13 | [8 empty] | 2671.58
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 1-1-CT-N-X-I-PN-TD | 8953
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
8 7/8 5.9 2.0F Slick -.016 |  |  | PDCI / 7/8 5.9 | 5.98 / 2.00 |  | 0 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 80 |  | 400-900 | 0.166 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HPW |  | 0.016
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5951.10 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/21/2021 | Depth In: |  | 11985 | Total Drilled: |  | 555.00 (Usft)
Date Out: |  |  | 05/23/2021 | Depth Out: |  | 12540 | Drilling / Circ Hours: |  | 9.92 / 17.95
Survey Offset: |  |  | 67 | Gamma Offset: |  | 54
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13590860 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250014 | 6/7 11.7 2.0 Slick HS88 .015 | 5 | 2 | 4.938 / 1.73 | XT-39 / 3 1/2 Reg |  | 33.06 | 33.81
| 3 | 306839 | BTI | 4.812 | 2.5 |  | XT-39 / XT-39 |  | 2.1 | 35.91
| 4 | SD56837 | Pony Collar | 5.062 | 2.75 |  | XT-39 / XT-39 |  | 9.44 | 45.35
| 5 | 500048 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 3.07 | 48.42
| 6 | SD56281 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.19 | 78.61
| 7 | SD56870 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.99 | 88.6
| 8 | SD55848 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.78 | 119.38
| 9 | A52074 | Tomax | 4.938 | 2.25 |  | XT-39 / XT-39 |  | 17.57 | 136.95
| 10 | SD119105 | Crossover | 5.125 | 2.25 |  | DS42 / XT-39 |  | 3.07 | 140.02
| 11 | Rig 1 | 2 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 188.32 | 328.34
| 12 | DTI-DNR-98 | Reamer | 5.188 | 2.5 |  | DS42 / DS42 |  | 8.16 | 336.5
| 13 | Rig 2 | 26 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2452.32 | 2788.82
| 14 | PG525-0021 | Agitator | 5.25 | 2.25 |  | DS42 / DS42 |  | 23.72 | 2812.54
| 15 | Rig 3 | 33 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 3116.63 | 5929.17
| 16 | PG525-0006 | Agitator | 5.25 | 2.25 |  | DS42 / DS42 |  | 21.93 | 5951.1
| 17 | [8 empty] | 5951.1
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New |  | 555
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 11.7 2.0 Slick HS88 .015 |  |  | PDCI / 6/7 11.7 | 4.05 / 2.00 |  | 0 | 4.5 | 0 | 2905
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
7623 |  |  | 0 | 80 |  | 150-350 | 0.89 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Plus) |  | 0.015
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2808.22 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/24/2021 | Depth In: |  | 11992 | Total Drilled: |  | 313.00 (Usft)
Date Out: |  |  | 05/26/2021 | Depth Out: |  | 12305 | Drilling / Circ Hours: |  | 32.97 / 9.20
Survey Offset: |  |  | 61 | Gamma Offset: |  | 48
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13090615 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | MTR475015 | 7/8 3.8 2.5 Slick HS88 -.001 | 5 | 2 | 4.938 / 1.74 | XT-39 / 3 1/2 Reg |  | 26.22 | 26.97
| 3 | 306839 | BTI | 4.812 | 2.5 |  | XT-39 / XT-39 |  | 2.1 | 29.07
| 4 | SD56837 | Pony Collar | 5.062 | 2.75 |  | XT-39 / XT-39 |  | 9.44 | 38.51
| 5 | 500048 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 3.07 | 41.58
| 6 | SD56281 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.19 | 71.77
| 7 | SD56870 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.99 | 81.76
| 8 | SD55848 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.78 | 112.54
| 9 | A52074 | Tomax | 4.938 | 2.25 |  | XT-39 / XT-39 |  | 17.57 | 130.11
| 10 | SD119105 | Crossover | 5.125 | 2.25 |  | DS42 / XT-39 |  | 3.07 | 133.18
| 11 | Rig 4 | 28 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2651.32 | 2784.5
| 12 | PG525-0021 | Agitator | 5.25 | 2.25 |  | DS42 / DS42 |  | 23.72 | 2808.22
| 13 | [8 empty] | 2808.22
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New |  | 313
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 3.8 2.5 Slick HS88 -.001 |  |  | PDCI / 7/8 3.8 | 4.11 / 2.50 |  | 0 | 5.25 | 0 | 860
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
4 |  |  | 0 | 0 |  | 150-250 | 0.521 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Minus) |  | -0.001
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2814.91 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/26/2021 | Depth In: |  | 12305 | Total Drilled: |  | 420.00 (Usft)
Date Out: |  |  | 05/27/2021 | Depth Out: |  | 12725 | Drilling / Circ Hours: |  | 7.93 / 8.30
Survey Offset: |  |  | 67 | Gamma Offset: |  | 54
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 1138553 | GTD64M 6.75 Jets 6X18's | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250018 | 6/7 Lobe 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 | 5.5 | 2 | 5.000 / 1.72 | 4 XT39 / 3 1/2Reg |  | 33.13 | 33.88
| 3 | 306839 | BTI | 4.812 | 2.5 |  | XT-39 / XT-39 |  | 2.1 | 35.98
| 4 | SD56837 | Pony Collar | 5.062 | 2.75 |  | XT-39 / XT-39 |  | 9.44 | 45.42
| 5 | 500048 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 3.07 | 48.49
| 6 | SD56281 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.19 | 78.68
| 7 | SD56870 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.99 | 88.67
| 8 | SD55848 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.78 | 119.45
| 9 | A52074 | Tomax | 4.938 | 2.25 |  | XT-39 / XT-39 |  | 17.57 | 137.02
| 10 | SD119105 | Crossover | 5.125 | 2.25 |  | DS42 / XT-39 |  | 3.07 | 140.09
| 11 | Rig 4 | 28 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2651.32 | 2791.41
| 12 | PG5250027 | Agitator | 5.25 | 2.25 |  | DS42 / DS42 |  | 23.5 | 2814.91
| 13 | [8 empty] | 2814.91
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M 6.75 Jets 6X18's | 1.49 | Security | GTD64M | New |  | 420
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 Lobe 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 |  |  | PDCI / 6/7 8.8 | 4.01 / 2.25 |  | 0 | 5.56 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 0 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.009
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_6
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5974.59 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 6 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/27/2021 | Depth In: |  | 12725 | Total Drilled: |  | 2769.00 (Usft)
Date Out: |  |  | 05/30/2021 | Depth Out: |  | 15494 | Drilling / Circ Hours: |  | 28.67 / 12.17
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 1138553 | GTD64M 6.75 Jets 6X18's | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250024 | 6/7 8.8 @ 2.12? FIX Slick HS88 +.009 | 5.5 | 2 | 1.73 | 4 XT39 / 3 1/2Reg |  | 33.14 | 33.89
| 3 | 306839 | BTI | 4.812 | 2.5 |  | XT-39 / XT-39 |  | 2.1 | 35.99
| 4 | SD56837 | Pony Collar | 5.062 | 2.75 |  | XT-39 / XT-39 |  | 9.44 | 45.43
| 5 | 500048 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 3.07 | 48.5
| 6 | SD56281 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.19 | 78.69
| 7 | SD56870 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.99 | 88.68
| 8 | SD55848 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.78 | 119.46
| 9 | A52074 | Tomax | 4.938 | 2.25 |  | XT-39 / XT-39 |  | 17.57 | 137.03
| 10 | SD119105 | Crossover | 5.125 | 2.25 |  | DS42 / XT-39 |  | 3.07 | 140.1
| 11 | Rig 1 | 2 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 188.32 | 328.42
| 12 | DTI-DNR-98 | Reamer | 5.188 | 2.5 |  | DS42 / DS42 |  | 8.16 | 336.58
| 13 | Rig 2 | 26 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2453 | 2789.58
| 14 | PG5250027 | Agitator | 5.25 | 2.5 |  | DS42 / DS42 |  | 23.5 | 2813.08
| 15 | Rig 3 | 33 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 3138.03 | 5951.11
| 16 | PG525-0046 | Agitator | 5.312 | 2.5 |  | DS42 / DS42 |  | 23.48 | 5974.59
| 17 | [8 empty] | 5974.59
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M 6.75 Jets 6X18's | 1.49 | Security | GTD64M |  |  | 2769
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 @ 2.12? FIX Slick HS88 +.009 |  |  | PDCI / 6/7 8.8 | 4.04 / 2.12 |  | 0 | 5.62 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Plus) |  | 0.009
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_7
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5972.07 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 7 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 6 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 05/30/2021 | Depth In: |  | 15494 | Total Drilled: |  | 3083.00 (Usft)
Date Out: |  |  | 06/03/2021 | Depth Out: |  | 18577 | Drilling / Circ Hours: |  | 51.33 / 20.92
Survey Offset: |  |  | 67 | Gamma Offset: |  | 54
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13558789 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250010 | 6/7 8.8 2.12 Slick HS88 0.021 | 5.5 | 2 | 5.000 / 1.95 | 4 XT39 / 3 1/2Reg |  | 33.08 | 33.83
| 3 | 306842 | BTI | 4.812 | 2.5 |  | XT-39 / XT-39 |  | 2.1 | 35.93
| 4 | SD56837 | Pony Collar | 5.062 | 2.75 |  | XT-39 / XT-39 |  | 9.44 | 45.37
| 5 | 500048 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 3.07 | 48.44
| 6 | SD56281 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.19 | 78.63
| 7 | SD56870 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.99 | 88.62
| 8 | SD55848 | NMDC | 4.938 | 2.75 |  | XT-39 / XT-39 |  | 30.78 | 119.4
| 9 | A52074 | Tomax | 4.938 | 2.25 |  | XT-39 / XT-39 |  | 17.57 | 136.97
| 10 | SD119105 | Crossover | 5.125 | 2.25 |  | DS42 / XT-39 |  | 3.07 | 140.04
| 11 | Rig 1 | 2 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 188.32 | 328.36
| 12 | DTI-DNR-98 | Reamer | 5.188 | 2.5 |  | DS42 / DS42 |  | 8.16 | 336.52
| 13 | Rig 2 | 26 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2453 | 2789.52
| 14 | PG525-0006 | Agitator | 5.25 | 2.75 | 5.250 / 1.63 | DS42 / DS42 |  | 23.7 | 2813.22
| 15 | Rig 3 | 33 Std Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 3138.03 | 5951.25
| 16 | PG525-0015 | Agitator | 5.25 | 2.75 | 5.250 / 1.47 | DS42 / DS42 |  | 20.82 | 5972.07
| 17 | [8 empty] | 5972.07
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 4-6-BT-A-X-I-WT-HP | 3083
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 Slick HS88 0.021 |  |  | PDCI / 6/7 8.8 | 4.10 / 2.12 |  | 0 | 5.5 | 150 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1100 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 |  | 0.021
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positve Pulse |  |  | 1.28 |  |  | 1.165 | PDCI |  | 2.75
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6250 |  |  |  | 7460 |  | 1262 | 1343
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
3030 |  |  |  | 0.5 |  |  |  |  | Yes
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_8
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 9986.97 (Usft)
Well: |  |  | Rainier 1H ST01 | BHA #: |  | 8 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1123821 | Bit #: |  | 7 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 06/06/2021 | Depth In: |  | 18577 | Total Drilled: |  | 2082.00 (Usft)
Date Out: |  |  | 06/09/2021 | Depth Out: |  | 20659 | Drilling / Circ Hours: |  | 20.42 / 9.67
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13594950 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250022 | 6/7 8.8 @ 2.12? FIX Slick HPT +.020 | 5.5 | 2 | 5.000 / 1.97 | 4 XT39 / 3 1/2Reg |  | 32.95 | 33.7
| 3 | 306842 | BTI | 4.812 | 2.5 |  | XT-39 / XT-39 |  | 2.1 | 35.8
| 4 | GT50-10-479 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.86 | 45.66
| 5 | ZSBX500033 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 3.63 | 49.29
| 6 | SD56699 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.72 | 80.01
| 7 | GT50-10-637 | Pony Collar | 5 | 2.75 |  | XT-39 / XT-39 |  | 9.29 | 89.3
| 8 | SD56777 | NMDC | 5 | 2.75 |  | XT-39 / XT-39 |  | 30.86 | 120.16
| 9 | A52102 | Tomax | 5 | 2.25 | 5.000 / 2.05 | XT-39 / XT-39 |  | 17.65 | 137.81
| 10 | GT52331433 | Crossover | 5.312 | 2.75 |  | CET-43 / XT-39 |  | 3.64 | 141.45
| 11 | Rig | 2 Stds 4.5 Drill Pipe | 4.5 | 3 |  | CET-43 / CET-43 |  | 189.58 | 331.03
| 12 | DTI-DNR-533 | 6 13/16 Reamer | 5.375 | 2.562 | 5.375 / 1.16 | CET-43 / CET-43 |  | 8.41 | 339.44
| 13 | Rig | 26 Stds 4.5 in Drill Pipe | 4.5 | 3 |  | CET-43 / CET-43 |  | 2460.5 | 2799.94
| 14 | PG525-0037 | Agitator | 5.312 | 2.75 | 5.312 / 1.75 | CET-43 / CET-43 |  | 22.42 | 2822.36
| 15 | Rig | 33 Stds 4.5 in Drill Pipe | 4.5 | 3 |  | CET-43 / CET-43 |  | 3118.79 | 5941.15
| 16 | PG525-0049 | Agitator | 5.312 | 2.75 | 5.312 / 1.83 | CET-43 / CET-43 |  | 21.95 | 5963.1
| 17 | Rig | 32 Stds 4.5 in Drill Pipe | 4.5 | 3 |  | CET 43 / CET 43 |  | 3018.22 | 8981.32
| 18 | Rig | 11 Stds 4.5 HWDP | 4.5 | 3 |  | CET 43 / CET 43 |  | 1005.65 | 9986.97
| 19 | [8 empty] | 9986.97
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New |  | 2082
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  |  | PDCI / 6/7 8.8 | 4.09 / 2.12 |  | 0 | 5.56 | 150 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1000 | 80 |  | 150-400 | 0.68 | FBH | Mud lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPT |  | 0.02
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 1000.25/0.00/0.00
Date In: |  | 05/12/2021 16:30 |  | SN: |  | PPM800075 |  |  |  | WOB Rotate (klbs): |  | 10.00
Date Out: |  | 05/13/2021 04:45 |  | Description: |  | 7.75" 7/8 5.9 1.5F 13" NBS -.022 |  |  |  | WOB Slide (klbs): |  | 10.00
Depth In/Out(Usft): |  | 108.00 / 3033.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 60.00
Inc In/Out: |  | 0.15 / 8.03 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 856.9
Azi In/Out: |  | 227.43 / 15.10 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1086.46
Total Drilled (Usft): |  | 2925 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1560.42
%Slide (Ftg): |  | 12.07 |  | Bit to Bend (Usft): | [5 empty] | Tq On Btm (kftlbs): |  | 2000
%Slide (Time): |  | 27.93 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 353 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 1.42 |  | Stab to Bit (Usft): |  | 2.08 |  |  |  | Bit Data
%Rotary (Ftg): |  | 87.93 |  | Kickpad OD (in): | [5 empty] | Make: |  | Ulterra
%Rotary (Time): |  | 72.00 |  | Body OD (in): |  | 7.938 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2572 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 3.66 |  | Length (Usft): |  | 37.52 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 5.08 |  | Integral Float: |  | NO |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 5.00 / 12.25 |  | Rev per Gal: | [5 empty] | Grade In:
Slide ROP (Usft/hr): |  | 248.59 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 702.73 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 5.08
Avg ROP (Usft/hr): |  | 575.79 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 5.00
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
72 | [9 empty] | 1 |  | 0.00 / 4.14
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 47245 |  | 13.5 |  |  |  |  | 1.5 | 1.5
7.75" 7/8 5.9 1.5F 13" NBS -.022 0.00 |  |  |  | PPM800075 |  | 7.938 |  |  |  |  | 37.52 | 39.02
Nortrak Stabilizer 13" 0.00 |  |  |  | SD610174 |  | 8 | 3.25 |  |  |  | 6.74 | 45.76
NMPC 0.00 |  |  |  | SD54328 |  | 8.062 | 3.25 |  |  |  | 10.1 | 55.86
UBHO 0.00 |  |  |  | 775151 |  | 7.75 | 3 |  |  |  | 2.55 | 58.41
NMDC 0.00 |  |  |  | SD55726 |  | 8 | 3.25 |  |  |  | 29.13 | 87.54
NMDC 0.00 |  |  |  | SD56047 |  | 7.938 | 3.25 |  |  |  | 29.2 | 116.74
Crossover Sub 0.00 |  |  |  | SD114897 |  | 6.75 | 2.812 |  |  |  | 3.6 | 120.34
9 Jts HWDP 0.00 | [5 empty] | 5 | 3 |  |  |  | 277.12 | 397.46
0.00 | [11 empty] | 397.46
Additional Comments
Plan was to build and hold 12 deg. MYs was 4-7/100.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 129.00/206.84/248.00
Date In: |  | 05/14/2021 18:00 |  | SN: |  | PPM800055 |  |  |  | WOB Rotate (klbs): |  | 35.00
Date Out: |  | 05/19/2021 18:50 |  | Description: |  | 8 7/8 5.9 2.0F Slick -.016 |  |  |  | WOB Slide (klbs): |  | 33.85
Depth In/Out(Usft): |  | 3033.00 / 11985.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 79.77
Inc In/Out: |  | 8.03 / 6.07 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 825.05
Azi In/Out: |  | 15.09 / 134.85 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 3539.02
Total Drilled (Usft): |  | 8953 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4066.79
%Slide (Ftg): |  | 14.46 |  | Bit to Bend (Usft): |  | 5.98 |  |  |  | Tq On Btm (kftlbs): |  | 17538.46
%Slide (Time): |  | 63.34 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1295 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 49.67 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 85.54 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 36.66 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 7658 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 28.75 |  | Length (Usft): |  | 37.58 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 78.42 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 18.95 / 120.83 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 26.07 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-CT-N-X-I-PN-TD
Rot ROP (Usft/hr): |  | 266.37 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HPW / 0.016 |  |  |  | Drill Hrs: |  | 78.42
Avg ROP (Usft/hr): |  | 114.17 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 18.95
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
248
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
70 | 60 | [10 empty] | 0.00 / 3.45
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 54682 |  | 9.875 |  |  |  |  | 1.5 | 1.5
8 7/8 5.9 2.0F Slick -.016 0.00 |  |  |  | PPM800055 |  | 8 |  |  |  |  | 37.58 | 39.08
NMPC 0.00 |  |  |  | SD54328 |  | 8.062 | 3.25 |  |  |  | 10.1 | 49.18
UBHO 0.00 |  |  |  | 775151 |  | 7.75 | 3 |  |  |  | 2.55 | 51.73
NMDC 0.00 |  |  |  | SD55726 |  | 8 | 3.25 |  |  |  | 29.13 | 80.86
NMDC 0.00 |  |  |  | SD56047 |  | 7.938 | 3.25 |  |  |  | 29.2 | 110.06
Crossover Sub 0.00 |  |  |  | SD116860 |  | 6.5 | 2.375 |  |  |  | 2.35 | 112.41
2 Stds 6.5 in DC 0.00 |  |  |  | Rig |  | 6.5 | 2.75 |  |  |  | 186.82 | 299.23
Crossover Sub 0.00 |  |  |  | SD3539 |  | 6.438 | 2.375 |  |  |  | 2.89 | 302.12
3 Stds 5 in HWDP 0.00 |  |  |  | Rig |  | 5 | 3 |  |  |  | 277.12 | 579.24
22 Stds 5 in DP 0.00 |  |  |  | Rig |  | 5 | 2.563 |  |  |  | 2067.72 | 2646.96
Agitator 0.00 |  |  |  | P6675-0022 |  | 6.812 |  |  |  |  | 24.62 | 2671.58
-1.00 | [11 empty] | 2671.58
Additional Comments
Did motor drain - Yes Visual Wear - Bearing gap was within tollerance, motor drained strong, no visuable signs of damage to motor at surface Build/Drop Tendency and Magnitude - Hold 12? nudge to 9976. Drop back to vertical and began building curve @ 11700 Start Temp & Max Temp - 98 - 255 Bit Grade 1-1-CT-N-X-I-PN-TD Number of Stalls ?Several mini stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No Misc. Comments ?BHA was used to drill out intermediate section per plan. Sliding was a challenge due to hangin up in upper part of hole. Once slipped off, weight would transfer causing differntial spikes and loss of tool face. This section took quiet a bit longer to drill cmpared to our previous runs in the area. While rotating, torque was higher than usual in the area slip sticking from 14-23. Off bottom torque at times would reach 21k. Over pull over 100k.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Build Rates |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 284.00/284.00/284.00
Date In: |  | 05/21/2021 01:00 |  | SN: |  | PPM250014 |  |  |  | WOB Rotate (klbs): |  | 18.00
Date Out: |  | 05/23/2021 08:00 |  | Description: |  | 6/7 11.7 2.0 Slick HS88 .015 |  |  |  | WOB Slide (klbs): |  | 18.00
Depth In/Out(Usft): |  | 11985.00 / 12540.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 30.00
Inc In/Out: |  | 6.08 / 56.71 |  | Model: |  | 6/7 11.7 |  |  |  | Flow Rate (gpm): |  | 195
Azi In/Out: |  | 134.86 / 135.39 |  | Lobes / Stages: |  | 6/7 / 11.7 |  |  |  | Off Btm Press (psi): |  | 4500
Total Drilled (Usft): |  | 555 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 5166.67
%Slide (Ftg): |  | 98.20 |  | Bit to Bend (Usft): |  | 4.05 |  |  |  | Tq On Btm (kftlbs): |  | 19000
%Slide (Time): |  | 98.12 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 545 |  | Bearing Gap (in): |  | 1.25 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 9.73 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 1.80 |  | Kickpad OD (in): |  | 4.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 1.92 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 10 |  | Fishneck OD (in): |  | 4.938 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0.19 |  | Length (Usft): |  | 33.06 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 9.92 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 17.95 / 55.00 |  | Rev per Gal: |  | 0.89 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 56.01 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 52.63 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Plus) / 0.015 |  |  |  | Drill Hrs: |  | 9.92
Avg ROP (Usft/hr): |  | 55.95 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 17.95
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
42 / 26 | 19 / 16 | 6 / 5 |  | 74:26 |  | 16 | 10 | 9.8 | 52000 | OBM | 11 |  | 284
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
67 | 54 | [10 empty] | 0.00 / 14.62
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13590860 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 11.7 2.0 Slick HS88 .015 0.00 |  |  |  | PPM250014 |  | 5 | 2 |  |  |  | 33.06 | 33.81
BTI 0.00 |  |  |  | 306839 |  | 4.812 | 2.5 |  |  |  | 2.1 | 35.91
Pony Collar 0.00 |  |  |  | SD56837 |  | 5.062 | 2.75 |  |  |  | 9.44 | 45.35
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.5 |  |  |  | 3.07 | 48.42
NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.19 | 78.61
Pony Collar 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 9.99 | 88.6
NMDC 0.00 |  |  |  | SD55848 |  | 4.938 | 2.75 |  |  |  | 30.78 | 119.38
Tomax 0.00 |  |  |  | A52074 |  | 4.938 | 2.25 |  |  |  | 17.57 | 136.95
Crossover 0.00 |  |  |  | SD119105 |  | 5.125 | 2.25 |  |  |  | 3.07 | 140.02
2 Std Drill Pipe 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 188.32 | 328.34
Reamer 0.00 |  |  |  | DTI-DNR-98 |  | 5.188 | 2.5 |  |  |  | 8.16 | 336.5
26 Std Drill Pipe 0.00 |  |  |  | Rig 2 |  | 4.5 | 2.5 |  |  |  | 2452.32 | 2788.82
Agitator 0.00 |  |  |  | PG525-0021 |  | 5.25 | 2.25 |  |  |  | 23.72 | 2812.54
33 Std Drill Pipe 0.00 |  |  |  | Rig 3 |  | 4.5 | 2.5 |  |  |  | 3116.63 | 5929.17
Agitator 0.00 |  |  |  | PG525-0006 |  | 5.25 | 2.25 |  |  |  | 21.93 | 5951.1
-1.00 | [11 empty] | 5951.1
Additional Comments
Did motor drain - N/A Visual Wear - Backed out at stator tube. Build/Drop Tendency and Magnitude ?BHA was intended to build curve on 8s and continue onto lateral Start Temp & Max Temp - 244 - 282 Bit Grade- N/A Number of Stalls ? 1 Stalls Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No Misc. Comments ? This Bha was used to begin the curve on 8?s. Sliding was not difficult and build rates were 8 ? 9?s and started falling off with about 40? of angle in the hole and started Dropping with no rotation in the hole. We started getting 4 ? 5?s. Shortly after we started having well control issues. It was decided to pull out and pick up a bail out motor. Once we reached surface, noticed that all that was ledt of motor was stator tube and top sub. Decision was made to sidetrack around motor with 2.5? motor.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Lay Out BR / ST BHA |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 242.00/245.00/248.00
Date In: |  | 05/24/2021 01:00 |  | SN: |  | MTR475015 |  |  |  | WOB Rotate (klbs): |  | 10000.00
Date Out: |  | 05/26/2021 04:00 |  | Description: |  | 7/8 3.8 2.5 Slick HS88 -.001 |  |  |  | WOB Slide (klbs): |  | 10000.00
Depth In/Out(Usft): |  | 11992.00 / 12305.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 6.34 / 30.00 |  | Model: |  | 7/8 3.8 |  |  |  | Flow Rate (gpm): |  | 240
Azi In/Out: |  | 135.81 / 150.51 |  | Lobes / Stages: |  | 7/8 / 3.8 |  |  |  | Off Btm Press (psi): |  | 2633.33
Total Drilled (Usft): |  | 313 |  | Bend Angle: |  | 2.5 |  |  |  | On Btm Press (psi): |  | 2733.33
%Slide (Ftg): |  | 100.00 |  | Bit to Bend (Usft): |  | 4.11 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 100.01 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 313 |  | Bearing Gap (in): |  | 1.25 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 32.97 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 0.00 |  | Kickpad OD (in): |  | 5.25 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 0.00 |  | Body OD (in): |  | 5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 0 |  | Fishneck OD (in): |  | 4.938 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0 |  | Length (Usft): |  | 26.22 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 32.97 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 9.20 / 51.00 |  | Rev per Gal: |  | 0.521 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 9.49 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 0 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Minus) / -0.001 |  |  |  | Drill Hrs: |  | 32.97
Avg ROP (Usft/hr): |  | 9.49 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 9.20
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
50 / 30 | 22 / 17 | 7 / 6 |  | 70:30 |  | 20 | 10 | 11 | 57000 | OBM | 14.8 |  | 248
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
61 | 48 | [10 empty] | 0.00 / 10.15
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13090615 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
7/8 3.8 2.5 Slick HS88 -.001 0.00 |  |  |  | MTR475015 |  | 5 | 2 |  |  |  | 26.22 | 26.97
BTI 0.00 |  |  |  | 306839 |  | 4.812 | 2.5 |  |  |  | 2.1 | 29.07
Pony Collar 0.00 |  |  |  | SD56837 |  | 5.062 | 2.75 |  |  |  | 9.44 | 38.51
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.5 |  |  |  | 3.07 | 41.58
NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.19 | 71.77
Pony Collar 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 9.99 | 81.76
NMDC 0.00 |  |  |  | SD55848 |  | 4.938 | 2.75 |  |  |  | 30.78 | 112.54
Tomax 0.00 |  |  |  | A52074 |  | 4.938 | 2.25 |  |  |  | 17.57 | 130.11
Crossover 0.00 |  |  |  | SD119105 |  | 5.125 | 2.25 |  |  |  | 3.07 | 133.18
28 Std Drill Pipe 0.00 |  |  |  | Rig 4 |  | 4.5 | 2.5 |  |  |  | 2651.32 | 2784.5
Agitator 0.00 |  |  |  | PG525-0021 |  | 5.25 | 2.25 |  |  |  | 23.72 | 2808.22
-1.00 | [11 empty] | 2808.22
Additional Comments
Did motor drain - Yes Visual Wear ? No visual damage to be seen. Build/Drop Tendency and Magnitude ? This motor was Picked up for side track and was pulled due to big motor yields. Trying to keep dog legs down Start Temp & Max Temp - 242 - 248 Bit Grade 1-1-BT-G-x16 Number of Stalls ? No Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No Misc. Comments ? Once out of the hole the motor had about 1/8 of squat with minimal Bearing leakage drained well with no visible damage to be seen.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 258.00/258.00/258.00
Date In: |  | 05/26/2021 05:00 |  | SN: |  | PPM250018 |  |  |  | WOB Rotate (klbs): |  | 30.00
Date Out: |  | 05/27/2021 13:30 |  | Description: |  | 6/7 Lobe 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 |  |  |  | WOB Slide (klbs): |  | 30.00
Depth In/Out(Usft): |  | 12305.00 / 12725.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 30.02 / 75.25 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 345
Azi In/Out: |  | 150.51 / 130.18 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4450
Total Drilled (Usft): |  | 420 |  | Bend Angle: |  | 2.25 |  |  |  | On Btm Press (psi): |  | 5000
%Slide (Ftg): |  | 88.33 |  | Bit to Bend (Usft): |  | 4.01 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 86.09 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 371 |  | Bearing Gap (in): |  | 1.25 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 6.83 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 11.67 |  | Kickpad OD (in): |  | 5.562 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 13.87 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 49 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 1.1 |  | Length (Usft): |  | 33.13 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 7.93 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 8.30 / 32.50 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 54.32 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 44.55 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.009 |  |  |  | Drill Hrs: |  | 7.93
Avg ROP (Usft/hr): |  | 52.96 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 8.30
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
50 / 30 | 22 / 17 | 7 / 6 |  | 70:30 |  | 20 | 10 | 11 | 57000 | OBM | 14.8 |  | 258
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
67 | 54 | [8 empty] | 12 |  | 13.50 / 15.45
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 6.75 Jets 6X18's 1.49 |  |  |  | 1138553 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 Lobe 8.8 Stage @ 2.25? Fix Slick (BFF) (FBH) HS88 + .009 0.00 |  |  |  | PPM250018 |  | 5.5 | 2 |  |  |  | 33.13 | 33.88
BTI 0.00 |  |  |  | 306839 |  | 4.812 | 2.5 |  |  |  | 2.1 | 35.98
Pony Collar 0.00 |  |  |  | SD56837 |  | 5.062 | 2.75 |  |  |  | 9.44 | 45.42
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.5 |  |  |  | 3.07 | 48.49
NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.19 | 78.68
Pony Collar 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 9.99 | 88.67
NMDC 0.00 |  |  |  | SD55848 |  | 4.938 | 2.75 |  |  |  | 30.78 | 119.45
Tomax 0.00 |  |  |  | A52074 |  | 4.938 | 2.25 |  |  |  | 17.57 | 137.02
Crossover 0.00 |  |  |  | SD119105 |  | 5.125 | 2.25 |  |  |  | 3.07 | 140.09
28 Std Drill Pipe 0.00 |  |  |  | Rig 4 |  | 4.5 | 2.5 |  |  |  | 2651.32 | 2791.41
Agitator 0.00 |  |  |  | PG5250027 |  | 5.25 | 2.25 |  |  |  | 23.5 | 2814.91
-1.00 | [11 empty] | 2814.91
Additional Comments
Did motor drain - Yes Visual Wear ? No visual damage to be seen. Motor was used for after Side Track to build curve until 6s were need to land. Start Temp & Max Temp - 258 Bit Grade 1-1-BT-G-x16 Number of Stalls ? No Reaming - No Back Reaming - No Jarring - No Mud Sample Collected - No Misc. Comments ? Once out of the hole the motor had about 1/8 of squat with minimal Bearing leakage drained well with no visible damage to be seen.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 6
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | DBR Bit / Damaged Bit |  |  | BHA # |  | 6
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 280.00/295.31/316.00
Date In: |  | 05/27/2021 14:30 |  | SN: |  | PPM250024 |  |  |  | WOB Rotate (klbs): |  | 29.00
Date Out: |  | 05/30/2021 04:35 |  | Description: |  | 6/7 8.8 @ 2.12? FIX Slick HS88 +.009 |  |  |  | WOB Slide (klbs): |  | 32.41
Depth In/Out(Usft): |  | 12725.00 / 15494.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 69.49
Inc In/Out: |  | 75.26 / 88.69 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 365.18
Azi In/Out: |  | 130.18 / 134.99 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4854.64
Total Drilled (Usft): |  | 2769 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5635.71
%Slide (Ftg): |  | 12.50 |  | Bit to Bend (Usft): |  | 4.04 |  |  |  | Tq On Btm (kftlbs): |  | 18987.18
%Slide (Time): |  | 39.52 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 346 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 11.33 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 87.50 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 60.49 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2423 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 6.75
Rotary Hours: |  | 17.34 |  | Length (Usft): |  | 33.14 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 28.67 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 12.17 / 62.08 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In:
Slide ROP (Usft/hr): |  | 30.54 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 139.73 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Plus) / 0.009 |  |  |  | Drill Hrs: |  | 28.67
Avg ROP (Usft/hr): |  | 96.58 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 12.17
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
49 / 30 | 22 / 15 | 7 / 5 |  | 75/25 |  | 19 | 11 | 11.9 | 54000 | OBM | 18.8 |  | 316
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [8 empty] | 6 |  | 8.00 / 7.77
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 6.75 Jets 6X18's 1.49 |  |  |  | 1138553 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 @ 2.12? FIX Slick HS88 +.009 0.00 |  |  |  | PPM250024 |  | 5.5 | 2 |  |  |  | 33.14 | 33.89
BTI 0.00 |  |  |  | 306839 |  | 4.812 | 2.5 |  |  |  | 2.1 | 35.99
Pony Collar 0.00 |  |  |  | SD56837 |  | 5.062 | 2.75 |  |  |  | 9.44 | 45.43
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.5 |  |  |  | 3.07 | 48.5
NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.19 | 78.69
Pony Collar 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 9.99 | 88.68
NMDC 0.00 |  |  |  | SD55848 |  | 4.938 | 2.75 |  |  |  | 30.78 | 119.46
Tomax 0.00 |  |  |  | A52074 |  | 4.938 | 2.25 |  |  |  | 17.57 | 137.03
Crossover 0.00 |  |  |  | SD119105 |  | 5.125 | 2.25 |  |  |  | 3.07 | 140.1
2 Std Drill Pipe 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 188.32 | 328.42
Reamer 0.00 |  |  |  | DTI-DNR-98 |  | 5.188 | 2.5 |  |  |  | 8.16 | 336.58
26 Std Drill Pipe 0.00 |  |  |  | Rig 2 |  | 4.5 | 2.5 |  |  |  | 2453 | 2789.58
Agitator 0.00 |  |  |  | PG5250027 |  | 5.25 | 2.5 |  |  |  | 23.5 | 2813.08
33 Std Drill Pipe 0.00 |  |  |  | Rig 3 |  | 4.5 | 2.5 |  |  |  | 3138.03 | 5951.11
Agitator 0.00 |  |  |  | PG525-0046 |  | 5.312 | 2.5 |  |  |  | 23.48 | 5974.59
-1.00 | [11 empty] | 5974.59
Additional Comments
Did motor drain - Yes Visual Wear ? No visual damage to be seen on motor. Bit was ringed out with chipped/broken cutters. Start Temp & Max Temp - 258 Bit Grade 2-5- Number of Stalls ? No Reaming - No Back Reaming - Yes Jarring - No Mud Sample Collected - No Misc. Comments ? While drilling ROP dropped from 200/hr to 40-60hr. Was only able to get 400 diff and stick slip was 13k-23k. Drilled approx 80 once ROP had dropped.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 7
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 7
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 304.00/327.40/347.00
Date In: |  | 05/30/2021 05:20 |  | SN: |  | PPM250010 |  |  |  | WOB Rotate (klbs): |  | 29.00
Date Out: |  | 06/03/2021 16:00 |  | Description: |  | 6/7 8.8 2.12 Slick HS88 0.021 |  |  |  | WOB Slide (klbs): |  | 34.23
Depth In/Out(Usft): |  | 15494.00 / 18577.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 74.91
Inc In/Out: |  | 88.69 / 89.60 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 364.51
Azi In/Out: |  | 134.99 / 132.95 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4837.04
Total Drilled (Usft): |  | 3083 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5420.99
%Slide (Ftg): |  | 9.41 |  | Bit to Bend (Usft): |  | 4.1 |  |  |  | Tq On Btm (kftlbs): |  | 22000
%Slide (Time): |  | 38.81 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 290 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi): |  | 1100
Slide Hours: |  | 19.92 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 90.59 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 61.19 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2793 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 31.41 |  | Length (Usft): |  | 33.08 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 51.33 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 6
Circ/BRT Hrs: |  | 20.92 / 106.67 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 14.56 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 4-6-BT-A-X-I-WT-HP
Rot ROP (Usft/hr): |  | 88.92 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 / 0.021 |  |  |  | Drill Hrs: |  | 51.33
Avg ROP (Usft/hr): |  | 60.06 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 20.92
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
29 / 19 | 14 / 9 | 5 / 4 |  | 74/26 |  | 10 | 9 | 10.4 | 53000 | OBM | 12.9 |  | 347
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
67 | 54 | [10 empty] | 6.00 / 6.69
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13558789 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 2.12 Slick HS88 0.021 0.00 |  |  |  | PPM250010 |  | 5.5 | 2 |  |  |  | 33.08 | 33.83
BTI 0.00 |  |  |  | 306842 |  | 4.812 | 2.5 |  |  |  | 2.1 | 35.93
Pony Collar 0.00 |  |  |  | SD56837 |  | 5.062 | 2.75 |  |  |  | 9.44 | 45.37
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.5 |  |  |  | 3.07 | 48.44
NMDC 0.00 |  |  |  | SD56281 |  | 5 | 2.75 |  |  |  | 30.19 | 78.63
Pony Collar 0.00 |  |  |  | SD56870 |  | 5 | 2.75 |  |  |  | 9.99 | 88.62
NMDC 0.00 |  |  |  | SD55848 |  | 4.938 | 2.75 |  |  |  | 30.78 | 119.4
Tomax 0.00 |  |  |  | A52074 |  | 4.938 | 2.25 |  |  |  | 17.57 | 136.97
Crossover 0.00 |  |  |  | SD119105 |  | 5.125 | 2.25 |  |  |  | 3.07 | 140.04
2 Std Drill Pipe 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 188.32 | 328.36
Reamer 0.00 |  |  |  | DTI-DNR-98 |  | 5.188 | 2.5 |  |  |  | 8.16 | 336.52
26 Std Drill Pipe 0.00 |  |  |  | Rig 2 |  | 4.5 | 2.5 |  |  |  | 2453 | 2789.52
Agitator 0.00 |  |  |  | PG525-0006 |  | 5.25 | 2.75 |  |  |  | 23.7 | 2813.22
33 Std Drill Pipe 0.00 |  |  |  | Rig 3 |  | 4.5 | 2.5 |  |  |  | 3138.03 | 5951.25
Agitator 0.00 |  |  |  | PG525-0015 |  | 5.25 | 2.75 |  |  |  | 20.82 | 5972.07
-1.00 | [11 empty] | 5972.07
Failure Information
Incident | YES | Hrs Before Incident |  |  | Tripped For Incident |  | NO | BHA SN |  |  | MWD SN
LIH | NO | NPT |  |  | Catastrophic Inci. |  | NO | MOTOR Inci. | NO |  | MWD Inci. | NO
Closed | NO | EDR Review |  | NO | Surface Fail |  | NO | MTBF Attrib. | NO |  | MWD Cat
Operations at Time of Incident
Troubleshooting Performed
Surface Findings
Additional Comments
Did motor drain - No Visual Wear - No Motor had 1/4 of squat and was able to turn bit by hand. Start Temp & Max Temp - 333-347 Bit Grade 4-6-BT-A-X-I-WT Number of Stalls ? Reaming - Yes Back Reaming - Yes Jarring - No Mud Sample Collected - No Misc. Comments ? While drilling. Differntal and torque started spiking. Diff 200-900 Tor 0-25k. Lost 500 psi of SPP and Drilling stopped. Picked up off bottom to check pressure lose and noticed rot torque had dropped 4k off bottom. While drilling top drive was maxing out on torque (25k) and causing top drive stalls. Drilled through choke with 200-1300 psi on the backside. Client had us reaming before slide.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 8
|  |  |  | Job # |  | LTX1123821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-149-33519 |  |  | Field: |  | Fayette County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 29° 52' 50.880" N |  |  | Well: |  | Rainier 1H ST01
|  |  |  | Longitude: |  | 96° 47' 33.480" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Fayette
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 8
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Jessie Collison
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 324.00/330.20/340.00
Date In: |  | 06/06/2021 04:00 |  | SN: |  | PPM250022 |  |  |  | WOB Rotate (klbs): |  | 25.00
Date Out: |  | 06/09/2021 24:00 |  | Description: |  | 6/7 8.8 @ 2.12? FIX Slick HPT +.020 |  |  |  | WOB Slide (klbs): |  | 25.78
Depth In/Out(Usft): |  | 18577.00 / 20659.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 89.60 / 86.67 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 350
Azi In/Out: |  | 132.95 / 131.26 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 5627.5
Total Drilled (Usft): |  | 2082 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 6327.5
%Slide (Ftg): |  | 6.24 |  | Bit to Bend (Usft): |  | 4.09 |  |  |  | Tq On Btm (kftlbs): |  | 20483.87
%Slide (Time): |  | 33.45 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 130 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 6.83 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 93.76 |  | Kickpad OD (in): |  | 5.562 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 66.56 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 1952 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 13.59 |  | Length (Usft): |  | 32.95 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 20.42 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 7
Circ/BRT Hrs: |  | 9.67 / 92.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 19.03 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 143.64 |  | Stator Vendor/Type/Fit: |  | Abaco / HPT / 0.020 |  |  |  | Drill Hrs: |  | 20.42
Avg ROP (Usft/hr): |  | 101.96 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 9.67
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
34 / 22 | 16 / 12 | 6 / 5 |  | 75/25 |  | 12 | 10 | 11 | 54000 | OBM | 15.3 |  | 340
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [10 empty] | 0.00 / 4.74
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13594950 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 8.8 @ 2.12? FIX Slick HPT +.020 0.00 |  |  |  | PPM250022 |  | 5.5 | 2 |  |  |  | 32.95 | 33.7
BTI 0.00 |  |  |  | 306842 |  | 4.812 | 2.5 |  |  |  | 2.1 | 35.8
Pony Collar 0.00 |  |  |  | GT50-10-479 |  | 5 | 2.75 |  |  |  | 9.86 | 45.66
UBHO 0.00 |  |  |  | ZSBX500033 |  | 5.25 | 2.5 |  |  |  | 3.63 | 49.29
NMDC 0.00 |  |  |  | SD56699 |  | 5 | 2.75 |  |  |  | 30.72 | 80.01
Pony Collar 0.00 |  |  |  | GT50-10-637 |  | 5 | 2.75 |  |  |  | 9.29 | 89.3
NMDC 0.00 |  |  |  | SD56777 |  | 5 | 2.75 |  |  |  | 30.86 | 120.16
Tomax 0.00 |  |  |  | A52102 |  | 5 | 2.25 |  |  |  | 17.65 | 137.81
Crossover 0.00 |  |  |  | GT52331433 |  | 5.312 | 2.75 |  |  |  | 3.64 | 141.45
2 Stds 4.5 Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3 |  |  |  | 189.58 | 331.03
6 13/16 Reamer 0.00 |  |  |  | DTI-DNR-533 |  | 5.375 | 2.562 |  |  |  | 8.41 | 339.44
26 Stds 4.5 in Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3 |  |  |  | 2460.5 | 2799.94
Agitator 0.00 |  |  |  | PG525-0037 |  | 5.312 | 2.75 |  |  |  | 22.42 | 2822.36
33 Stds 4.5 in Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3 |  |  |  | 3118.79 | 5941.15
Agitator 0.00 |  |  |  | PG525-0049 |  | 5.312 | 2.75 |  |  |  | 21.95 | 5963.1
32 Stds 4.5 in Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3 |  |  |  | 3018.22 | 8981.32
11 Stds 4.5 HWDP 0.00 |  |  |  | Rig |  | 4.5 | 3 |  |  |  | 1005.65 | 9986.97
-1.00 | [11 empty] | 9986.97
Additional Comments
Did motor drain -Yes Visual Wear - No Start Temp & Max Temp - 320-340 Bit Grade 1-1 Number of Stalls ? 0 Reaming - Yes Back Reaming - Yes Jarring - No Mud Sample Collected - No Misc. Comments ? Motor and bit looked green.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2925
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 353
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 72.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 2572
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/12/2021 | 17:45 | 18:00 | 0.25 | 108 | 215 | 107 | Rotate |  | 143 | 0.2 | 227.43 | 143 | -0.17 | -0.18 | -0.17 | 0.14 |  |  | 10 | 60 | 487 | 2000 | 428 | 300 | 650 | -350 |  | 85 | 80 | 75
05/12/2021 | 18:05 | 18:15 | 0.16667 | 215 | 307 | 92 | Rotate |  | 235 | 0.39 | 273.36 | 235 | -0.26 | -0.61 | -0.26 | 0.31 |  |  | 10 | 60 | 747 | 2000 | 552 | 1300 | 1000 | 300 |  | 85 | 80 | 75
05/12/2021 | 18:20 | 18:35 | 0.25 | 307 | 400 | 93 | Rotate |  | 328 | 0.48 | 275.81 | 328 | -0.2 | -1.32 | -0.2 | 0.1 |  |  | 10 | 60 | 747 | 2000 | 372 | 1300 | 1000 | 300 |  | 85 | 80 | 75
05/12/2021 | 18:40 | 18:50 | 0.16667 | 400 | 493 | 93 | Rotate |  | 418 | 0.45 | 282.42 | 417.99 | -0.09 | -2.04 | -0.09 | 0.07 |  |  | 10 | 60 | 870 | 2000 | 558 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 18:55 | 19:00 | 0.083333 | 493 | 518 | 25 | Slide | 35 | 513 | 0.63 | 3.54 | 512.99 | 0.51 | -2.37 | 0.51 | 0.75 |  |  | 10 | 60 | 870 | 2000 | 300 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:00 | 19:10 | 0.16667 | 518 | 583 | 65 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 390 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:15 | 19:20 | 0.083333 | 583 | 608 | 25 | Slide | 35 | 606 | 1.68 | 43.79 | 605.97 | 2.01 | -1.4 | 2.01 | 1.36 |  |  | 10 | 60 | 870 | 2000 | 300 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:20 | 19:25 | 0.083333 | 608 | 686 | 78 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 936 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:30 | 19:35 | 0.083333 | 686 | 711 | 25 | Slide | 35 | 700 | 3.38 | 40.99 | 699.88 | 5.1 | 1.38 | 5.1 | 1.81 |  |  | 10 | 60 | 870 | 2000 | 300 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:35 | 19:40 | 0.083333 | 711 | 780 | 69 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 828 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:45 | 19:50 | 0.083333 | 780 | 800 | 20 | Slide | 0 | 795 | 5.02 | 40.89 | 794.62 | 10.35 | 5.93 | 10.35 | 1.73 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 19:50 | 19:55 | 0.083333 | 800 | 875 | 75 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 900 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:00 | 20:05 | 0.083333 | 875 | 895 | 20 | Slide | -10 | 889 | 6.73 | 50.86 | 888.12 | 16.94 | 12.9 | 16.94 | 2.11 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:05 | 20:10 | 0.083333 | 895 | 972 | 77 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 924 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:15 | 20:20 | 0.083333 | 972 | 992 | 20 | Slide | -45 | 982 | 7.7 | 50.33 | 980.39 | 24.36 | 21.92 | 24.36 | 1.05 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:20 | 20:25 | 0.083333 | 992 | 1068 | 76 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 912 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:30 | 20:35 | 0.083333 | 1068 | 1088 | 20 | Slide | -90 | 1077 | 8.65 | 47.68 | 1074.42 | 33.23 | 32.1 | 33.23 | 1.08 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:35 | 20:40 | 0.083333 | 1088 | 1158 | 70 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 840 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:45 | 20:50 | 0.083333 | 1158 | 1178 | 20 | Slide | -90 | 1171 | 9.37 | 42.54 | 1167.26 | 43.63 | 42.5 | 43.63 | 1.15 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 20:50 | 20:55 | 0.083333 | 1178 | 1256 | 78 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 936 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:00 | 21:05 | 0.083333 | 1256 | 1276 | 20 | Slide | -90 | 1265 | 9.89 | 30.96 | 1259.94 | 56.19 | 51.83 | 56.19 | 2.13 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:05 | 21:10 | 0.083333 | 1276 | 1433 | 157 | Rotate |  | 1359 | 9.57 | 27.18 | 1352.59 | 70.06 | 59.55 | 70.06 | 0.76 |  |  | 10 | 60 | 870 | 2000 | 1884 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:15 | 21:20 | 0.083333 | 1433 | 1527 | 94 | Rotate |  | 1452 | 9.19 | 25.88 | 1444.35 | 83.62 | 66.33 | 83.62 | 0.47 |  |  | 10 | 60 | 870 | 2000 | 1128 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:25 | 21:30 | 0.083333 | 1527 | 1550 | 23 | Slide | 60 | 1546 | 8.92 | 32.21 | 1537.18 | 96.54 | 73.49 | 96.54 | 1.1 |  |  | 10 | 60 | 870 | 2000 | 276 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:30 | 21:35 | 0.083333 | 1550 | 1634 | 84 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 1008 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:40 | 21:45 | 0.083333 | 1634 | 1654 | 20 | Slide | 0 | 1641 | 9.05 | 32.84 | 1631.01 | 109.05 | 81.46 | 109.05 | 0.17 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:45 | 21:50 | 0.083333 | 1654 | 1725 | 71 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 852 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 21:55 | 22:00 | 0.083333 | 1725 | 1745 | 20 | Slide | 0 | 1736 | 10.79 | 36.53 | 1724.59 | 122.47 | 90.81 | 122.47 | 1.95 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:00 | 22:05 | 0.083333 | 1745 | 1852 | 107 | Rotate |  | 1829 | 12.03 | 36.81 | 1815.75 | 137.23 | 101.8 | 137.23 | 1.33 |  |  | 10 | 60 | 870 | 2000 | 1284 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:10 | 22:15 | 0.083333 | 1852 | 1872 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:15 | 22:20 | 0.083333 | 1872 | 1915 | 43 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 516 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:25 | 22:30 | 0.083333 | 1915 | 1935 | 20 | Slide | 0 | 1923 | 14.21 | 38.66 | 1907.29 | 154.08 | 114.88 | 154.08 | 2.36 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:30 | 22:35 | 0.083333 | 1935 | 1997 | 62 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 744 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:40 | 22:45 | 0.083333 | 1997 | 2091 | 94 | Rotate |  | 2017 | 15.1 | 38.84 | 1998.23 | 172.63 | 129.76 | 172.63 | 0.95 |  |  | 10 | 60 | 870 | 2000 | 1128 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 22:50 | 22:55 | 0.083333 | 2091 | 2185 | 94 | Rotate |  | 2111 | 14.94 | 38.85 | 2089.02 | 191.6 | 145.04 | 191.6 | 0.17 |  |  | 10 | 60 | 870 | 2000 | 1128 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 23:00 | 23:05 | 0.083333 | 2185 | 2279 | 94 | Rotate |  | 2205 | 14.56 | 39.02 | 2179.92 | 210.22 | 160.08 | 210.22 | 0.41 |  |  | 10 | 60 | 870 | 2000 | 1128 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 23:10 | 23:15 | 0.083333 | 2279 | 2373 | 94 | Rotate |  | 2299 | 14.11 | 39.45 | 2271 | 228.25 | 174.8 | 228.25 | 0.49 |  |  | 10 | 60 | 870 | 2000 | 1128 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 23:20 | 23:25 | 0.083333 | 2373 | 2480 | 107 | Rotate |  | 2393 | 13.88 | 39.8 | 2362.21 | 245.76 | 189.3 | 245.76 | 0.26 |  |  | 10 | 60 | 870 | 2000 | 1284 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 23:30 | 23:35 | 0.083333 | 2480 | 2500 | 20 | Slide | -135 | 2487 | 12.78 | 38.74 | 2453.67 | 262.53 | 203.02 | 262.53 | 1.2 |  |  | 10 | 60 | 870 | 2000 | 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 23:35 | 23:40 | 0.083333 | 2500 | 2561 | 61 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 732 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/12/2021 | 23:45 | 24:00 | 0.25 | 2561 | 2697 | 136 | Rotate |  | 2581 | 13.38 | 36.99 | 2545.23 | 279.32 | 216.07 | 279.32 | 0.76 |  |  | 10 | 60 | 870 | 2000 | 544 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 00:00 | 00:05 | 0.083333 | 2697 | 2717 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 240 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 00:05 | 00:20 | 0.25 | 2717 | 2758 | 41 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 164 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 00:25 | 00:30 | 0.083333 | 2758 | 2773 | 15 | Slide | -150 | 2769 | 10.41 | 24.56 | 2728.67 | 313.17 | 239.2 | 313.17 | 4.14 |  |  | 10 | 60 | 870 | 2000 | 180 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 00:30 | 00:40 | 0.16667 | 2773 | 2843 | 70 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 420 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 00:45 | 00:50 | 0.083333 | 2843 | 2900 | 57 | Rotate |  | 2863 | 9.18 | 18.87 | 2821.3 | 327.99 | 245.15 | 327.99 | 1.66 |  |  | 10 | 60 | 870 | 2000 | 684 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 01:40 | 01:50 | 0.16667 | 2900 | 2935 | 35 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 2000; Drilling Parameters ROP: 210 | 1600 | 1100 | 500 |  | 85 | 80 | 75
05/13/2021 | 01:55 | 02:00 | 0.083333 | 2935 | 3033 | 98 | Rotate |  | 2956 | 8.52 | 16.96 | 2913.19 | 341.6 | 249.56 | 341.6 | 0.78 |  |  | 10 | 60 | 870 | 2000 | 1176 | 1600 | 1100 | 500 |  | 85 | 80 | 75

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 8953
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1295
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 70.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 7658
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/15/2021 | 00:30 | 00:50 | 0.33333 | 3032 | 3152 | 120 | Rotate |  | 3071 | 7.79 | 14.09 | 3027.02 | 357.31 | 253.94 | 357.31 | 0.73 |  |  | 25 | 50 | 500 | 6000 | 360 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 00:55 | 01:00 | 0.083333 | 3152 | 3167 | 15 | Slide | 60 | 3165 | 8.24 | 24.62 | 3120.11 | 369.61 | 258.3 | 369.61 | 1.63 |  |  | 25 | 50 | 500 | 6000 | 180 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 01:00 | 01:05 | 0.083333 | 3167 | 3249 | 82 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 984 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 01:10 | 01:15 | 0.083333 | 3249 | 3264 | 15 | Slide | 60 | 3259 | 7.61 | 39.37 | 3213.22 | 380.55 | 265.06 | 380.55 | 2.26 |  |  | 30 | 80 | 885 | 6000 | 180 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 01:15 | 01:20 | 0.083333 | 3264 | 3345 | 81 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 972 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 01:25 | 01:30 | 0.083333 | 3345 | 3357 | 12 | Slide | 0 | 3353 | 7.96 | 33.87 | 3306.36 | 390.76 | 272.63 | 390.76 | 0.88 |  |  | 30 | 80 | 885 | 6000 | 144 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 01:30 | 01:35 | 0.083333 | 3357 | 3442 | 85 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 1020 | 1775 | 1375 | 400 |  | 135 | 130 | 125
05/15/2021 | 01:40 | 01:45 | 0.083333 | 3442 | 3457 | 15 | Slide | 0 | 3447 | 10.04 | 35.62 | 3399.2 | 402.83 | 281.03 | 402.83 | 2.23 |  |  | 30 | 80 | 885 | 6000 | 180 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 01:45 | 01:50 | 0.083333 | 3457 | 3517 | 60 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 720 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 01:55 | 02:00 | 0.083333 | 3517 | 3611 | 94 | Rotate |  | 3541 | 11.79 | 32.59 | 3491.49 | 417.58 | 290.98 | 417.58 | 1.96 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:05 | 02:10 | 0.083333 | 3611 | 3728 | 117 | Rotate |  | 3635 | 11.38 | 30.76 | 3583.58 | 433.64 | 300.89 | 433.64 | 0.59 |  |  | 30 | 80 | 885 | 6000 | 1404 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:15 | 02:20 | 0.083333 | 3728 | 3743 | 15 | Slide | 15 | 3729 | 10.14 | 31.12 | 3675.92 | 448.7 | 309.91 | 448.7 | 1.32 |  |  | 30 | 80 | 885 | 6000 | 180 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:20 | 02:25 | 0.083333 | 3743 | 3799 | 56 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 672 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:30 | 02:35 | 0.083333 | 3799 | 3918 | 119 | Rotate |  | 3822 | 12.6 | 28.37 | 3767.09 | 464.63 | 318.97 | 464.63 | 2.71 |  |  | 30 | 80 | 885 | 6000 | 1428 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:40 | 02:45 | 0.083333 | 3918 | 3933 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 180 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:45 | 02:50 | 0.083333 | 3933 | 3986 | 53 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 636 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 02:55 | 03:00 | 0.083333 | 3986 | 4100 | 114 | Rotate |  | 4010 | 12.82 | 29.42 | 3950.36 | 501.68 | 338.53 | 501.68 | 0.67 |  |  | 30 | 80 | 885 | 6000 | 1368 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 03:05 | 03:10 | 0.083333 | 4100 | 4115 | 15 | Slide | 60 | 4105 | 13.85 | 30.42 | 4042.8 | 520.67 | 349.46 | 520.67 | 1.11 |  |  | 30 | 80 | 885 | 6000 | 180 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 03:10 | 03:15 | 0.083333 | 4115 | 4175 | 60 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 720 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 03:20 | 03:25 | 0.083333 | 4175 | 4268 | 93 | Rotate |  | 4198 | 13.92 | 39.57 | 4133.09 | 538.89 | 362.23 | 538.89 | 2.36 |  |  | 30 | 80 | 885 | 6000 | 1116 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 03:30 | 03:35 | 0.083333 | 4268 | 4362 | 94 | Rotate |  | 4292 | 12.99 | 38.37 | 4224.51 | 555.89 | 375.99 | 555.89 | 1.03 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 03:40 | 03:45 | 0.083333 | 4362 | 4456 | 94 | Rotate |  | 4386 | 12.34 | 36.44 | 4316.22 | 572.26 | 388.51 | 572.26 | 0.83 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 03:50 | 03:55 | 0.083333 | 4456 | 4549 | 93 | Rotate |  | 4479 | 11.59 | 35.02 | 4407.2 | 587.9 | 399.78 | 587.9 | 0.87 |  |  | 30 | 80 | 885 | 6000 | 1116 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 04:00 | 04:05 | 0.083333 | 4549 | 4655 | 106 | Rotate |  | 4573 | 10.97 | 34.23 | 4499.39 | 603.03 | 410.23 | 603.03 | 0.68 |  |  | 30 | 80 | 885 | 6000 | 1272 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 04:10 | 04:15 | 0.083333 | 4655 | 4670 | 15 | Slide | 15 | 4666 | 12.13 | 33.76 | 4590.5 | 618.47 | 420.63 | 618.47 | 1.25 |  |  | 30 | 80 | 885 | 6000 | 180 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 04:15 | 04:20 | 0.083333 | 4670 | 4736 | 66 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 792 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 04:25 | 04:35 | 0.16667 | 4736 | 4830 | 94 | Rotate |  | 4760 | 12.91 | 38.25 | 4682.27 | 634.93 | 432.62 | 634.93 | 1.33 |  |  | 30 | 80 | 885 | 6000 | 564 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 04:40 | 04:45 | 0.083333 | 4830 | 4924 | 94 | Rotate |  | 4854 | 12.85 | 37.78 | 4773.9 | 651.44 | 445.53 | 651.44 | 0.13 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 04:50 | 04:55 | 0.083333 | 4924 | 5018 | 94 | Rotate |  | 4948 | 12.74 | 37.67 | 4865.57 | 667.9 | 458.27 | 667.9 | 0.12 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 05:00 | 05:10 | 0.16667 | 5018 | 5113 | 95 | Rotate |  | 5043 | 12.77 | 36.32 | 4958.23 | 684.65 | 470.89 | 684.65 | 0.32 |  |  | 30 | 80 | 885 | 6000 | 570 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 05:15 | 05:20 | 0.083333 | 5113 | 5207 | 94 | Rotate |  | 5137 | 12.73 | 35.99 | 5049.91 | 701.4 | 483.12 | 701.4 | 0.09 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 05:25 | 05:30 | 0.083333 | 5207 | 5301 | 94 | Rotate |  | 5231 | 12.75 | 35.48 | 5141.59 | 718.23 | 495.23 | 718.23 | 0.12 |  |  | 30 | 80 | 885 | 6000 | 1128 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 05:30 | 05:40 | 0.16667 | 5301 | 5395 | 94 | Rotate |  | 5325 | 12.74 | 34.33 | 5233.28 | 735.24 | 507.1 | 735.24 | 0.27 |  |  | 30 | 80 | 885 | 6000 | 564 | 1775 | 1375 | 400 | 129 | 135 | 130 | 125
05/15/2021 | 05:45 | 05:55 | 0.16667 | 5395 | 5489 | 94 | Rotate |  | 5419 | 12.39 | 33.2 | 5325.03 | 752.23 | 518.46 | 752.23 | 0.45 |  |  | 35 | 80 | 885 | 15500 | 564 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 06:00 | 06:10 | 0.16667 | 5489 | 5583 | 94 | Rotate |  | 5513 | 12.29 | 32.08 | 5416.85 | 769.15 | 529.3 | 769.15 | 0.28 |  |  | 35 | 80 | 885 | 15500 | 564 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 06:15 | 06:25 | 0.16667 | 5583 | 5677 | 94 | Rotate |  | 5607 | 12.27 | 31.05 | 5508.7 | 786.18 | 539.76 | 786.18 | 0.23 |  |  | 35 | 80 | 885 | 15500 | 564 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 06:30 | 06:35 | 0.083333 | 5677 | 5771 | 94 | Rotate |  | 5701 | 11.06 | 28.02 | 5600.76 | 802.7 | 549.15 | 802.7 | 1.44 |  |  | 35 | 80 | 885 | 15500 | 1128 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 06:40 | 06:41 | 0.016667 | 5771 | 5780 | 9 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 540 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 06:41 | 06:48 | 0.11667 | 5780 | 5795 | 15 | Slide | 60 | 5795 | 10.09 | 21.93 | 5693.17 | 818.3 | 556.46 | 818.3 | 1.57 |  |  | 45 | 80 | 885 | 15500 | 128.57 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 06:48 | 07:00 | 0.2 | 5795 | 5865 | 70 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 350 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 07:05 | 07:20 | 0.25 | 5865 | 5880 | 15 | Slide | TTF: 45; Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 60 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 07:20 | 07:40 | 0.33333 | 5880 | 5959 | 79 | Rotate |  | 5889 | 10.05 | 17.95 | 5785.72 | 833.74 | 562.07 | 833.74 | 0.74 |  |  | 35 | 80 | 885 | 15500 | 237 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 07:45 | 08:05 | 0.33333 | 5959 | 5974 | 15 | Slide | TTF: 45; Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 45 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 08:05 | 08:20 | 0.25 | 5974 | 6053 | 79 | Rotate |  | 5983 | 10.81 | 23.34 | 5878.17 | 849.64 | 568.09 | 849.64 | 1.31 |  |  | 35 | 80 | 885 | 15500 | 316 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 08:25 | 08:45 | 0.33333 | 6053 | 6068 | 15 | Slide | TTF: 45; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 45 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 08:45 | 09:00 | 0.25 | 6068 | 6148 | 80 | Rotate |  | 6078 | 10.13 | 27.06 | 5971.59 | 865.26 | 575.42 | 865.26 | 1.01 |  |  | 35 | 80 | 885 | 15500 | 320 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 09:05 | 09:20 | 0.25 | 6148 | 6163 | 15 | Slide | TTF: 45; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 60 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 09:20 | 09:35 | 0.25 | 6163 | 6241 | 78 | Rotate |  | 6171 | 10.35 | 31.62 | 6063.11 | 879.66 | 583.52 | 879.66 | 0.9 |  |  | 35 | 80 | 885 | 15500 | 312 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 09:40 | 09:55 | 0.25 | 6241 | 6256 | 15 | Slide | TTF: 45; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 60 | 4900 | 4100 | 800 | 178 | 195 | 175 | 155
05/15/2021 | 09:55 | 10:10 | 0.25 | 6256 | 6336 | 80 | Rotate |  | 6266 | 11.68 | 39.78 | 6156.36 | 894.31 | 594.15 | 894.31 | 2.15 |  |  | 35 | 80 | 885 | 15500 | 320 | 4900 | 4100 | 800 | 194 | 195 | 175 | 155
05/15/2021 | 10:15 | 10:25 | 0.16667 | 6336 | 6430 | 94 | Rotate |  | 6360 | 12.03 | 42.07 | 6248.36 | 908.9 | 606.8 | 908.9 | 0.62 |  |  | 35 | 80 | 885 | 15500 | 564 | 4900 | 4100 | 800 | 194 | 195 | 175 | 155
05/15/2021 | 10:30 | 10:50 | 0.33333 | 6430 | 6445 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 885; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 45 | 4900 | 4100 | 800 | 194 | 195 | 175 | 155
05/15/2021 | 10:50 | 11:20 | 0.5 | 6445 | 6524 | 79 | Rotate |  | 6454 | 11.41 | 41.93 | 6340.4 | 923.09 | 619.58 | 923.09 | 0.66 |  |  | 35 | 80 | 670 | 15500 | 158 | 3100 | 2600 | 500 | 194 | 195 | 175 | 155
05/15/2021 | 11:25 | 11:27 | 0.033333 | 6524 | 6530 | 6 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 670; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 180 | 3100 | 2600 | 500 | 194 | 195 | 175 | 155
05/15/2021 | 11:27 | 12:08 | 0.68333 | 6530 | 6545 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 670; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 21.95 | 3100 | 2600 | 500 | 194 | 195 | 175 | 155
05/15/2021 | 12:08 | 12:25 | 0.28333 | 6545 | 6617 | 72 | Rotate |  | 6547 | 11.27 | 42.1 | 6431.58 | 936.67 | 631.81 | 936.67 | 0.15 |  |  | 35 | 80 | 670 | 15500 | 254.12 | 3100 | 2600 | 500 | 194 | 195 | 175 | 155
05/15/2021 | 12:30 | 12:35 | 0.083333 | 6617 | 6625 | 8 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 670; Drilling Parameters Tq: 15500; Drilling Parameters ROP: 96 | 3100 | 2600 | 500 | 194 | 195 | 175 | 155
05/15/2021 | 12:35 | 13:13 | 0.63333 | 6625 | 6640 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 23.68 | 4500 | 4200 | 300 | 194 | 250 | 200 | 165
05/15/2021 | 13:13 | 13:24 | 0.18333 | 6640 | 6712 | 72 | Rotate |  | 6642 | 11.02 | 42.73 | 6524.79 | 950.23 | 644.2 | 950.23 | 0.29 |  |  | 40 | 80 | 900 | 18500 | 392.73 | 4850 | 4200 | 650 | 194 | 250 | 200 | 165
05/15/2021 | 13:30 | 13:35 | 0.083333 | 6712 | 6730 | 18 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 216 | 4850 | 4200 | 650 | 194 | 250 | 200 | 165
05/15/2021 | 13:35 | 14:30 | 0.91667 | 6730 | 6745 | 15 | Slide | 0 | 6735 | 10.61 | 41.93 | 6616.14 | 963.13 | 655.95 | 963.13 | 0.47 |  |  | 35 |  | 900 |  | 16.36 | 4500 | 4200 | 300 | 194 | 250 | 200 | 165
05/15/2021 | 14:30 | 14:44 | 0.23333 | 6745 | 6805 | 60 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 257.14 | 4850 | 4200 | 650 | 194 | 250 | 200 | 165
05/15/2021 | 14:50 | 14:55 | 0.083333 | 6805 | 6815 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 120 | 4850 | 4200 | 650 | 194 | 250 | 200 | 165
05/15/2021 | 14:55 | 15:51 | 0.93333 | 6815 | 6835 | 20 | Slide | 0 | 6830 | 11.56 | 45.17 | 6709.36 | 976.35 | 668.55 | 976.35 | 1.2 |  |  | 35 |  | 900 |  | 21.43 | 4500 | 4200 | 300 | 194 | 250 | 200 | 165
05/15/2021 | 15:51 | 16:05 | 0.23333 | 6835 | 6900 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 278.57 | 4850 | 4200 | 650 | 194 | 250 | 200 | 165
05/15/2021 | 16:53 | 17:03 | 0.16667 | 6900 | 6910 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 60 | 4850 | 4200 | 650 | 194 | 250 | 200 | 165
05/15/2021 | 17:03 | 17:58 | 0.91667 | 6910 | 6925 | 15 | Slide | -30 | 6924 | 11.78 | 42.49 | 6801.42 | 990.06 | 681.71 | 990.06 | 0.62 |  |  | 35 |  | 660 |  | 16.36 | 2900 | 2700 | 200 | 194 | 250 | 200 | 165
05/15/2021 | 17:58 | 18:10 | 0.2 | 6925 | 6994 | 69 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters FLOW: 660; Drilling Parameters ROP: 345 | 2900 | 2700 | 200 | 194 | 250 | 200 | 165
05/15/2021 | 19:10 | 19:25 | 0.25 | 6994 | 7006 | 12 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 48 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 19:25 | 19:45 | 0.33333 | 7006 | 7021 | 15 | Slide | 0 | 7015 | 12.42 | 39.34 | 6890.4 | 1004.48 | 694.19 | 1004.48 | 1.01 |  |  | 35 | 80 | 900 | 17000 | 45 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 19:45 | 20:45 | 1 | 7021 | 7273 | 252 | Rotate |  | 7110 | 12.93 | 40.07 | 6983.09 | 1020.52 | 707.5 | 1020.52 | 0.56 |  |  | 35 | 80 | 900 | 17000 | 252 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 22:00 | 22:10 | 0.16667 | 7273 | 7386 | 113 | Rotate |  | 7297 | 11.77 | 36.31 | 7165.57 | 1052.42 | 732.96 | 1052.42 | 1.31 |  |  | 35 | 80 | 900 | 17000 | 678 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 22:15 | 22:45 | 0.5 | 7386 | 7406 | 20 | Slide | 60 | 7391 | 11.06 | 40.53 | 7257.71 | 1066.99 | 744.49 | 1066.99 | 1.17 |  |  | 35 | 80 | 900 | 17000 | 40 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 22:45 | 23:00 | 0.25 | 7406 | 7461 | 55 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 220 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 23:05 | 23:25 | 0.33333 | 7461 | 7566 | 105 | Rotate |  | 7484 | 11.24 | 43.21 | 7348.96 | 1080.38 | 756.49 | 1080.38 | 0.59 |  |  | 35 | 80 | 900 | 17000 | 315 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/15/2021 | 23:30 | 24:00 | 0.5 | 7566 | 7576 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 20 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 00:00 | 00:25 | 0.41667 | 7576 | 7584 | 8 | Slide | 0 | 7579 | 11.02 | 37.82 | 7442.18 | 1094.3 | 768.4 | 1094.3 | 1.12 |  |  | 35 | 80 | 900 | 17000 | 19.2 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 00:25 | 00:45 | 0.33333 | 7584 | 7649 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 195 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 02:25 | 02:30 | 0.083333 | 7649 | 7659 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 120 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 02:30 | 03:30 | 1 | 7659 | 7679 | 20 | Slide | 0 | 7673 | 11.54 | 35.63 | 7534.36 | 1109.04 | 779.39 | 1109.04 | 0.72 |  |  | 35 | 80 | 900 | 17000 | 20 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 03:30 | 03:50 | 0.33333 | 7679 | 7753 | 74 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 222 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 03:55 | 04:10 | 0.25 | 7753 | 7773 | 20 | Slide | 0 | 7767 | 11.75 | 43.89 | 7626.43 | 1123.58 | 791.5 | 1123.58 | 1.79 |  |  | 35 | 80 | 900 | 17000 | 80 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 04:10 | 04:20 | 0.16667 | 7773 | 7873 | 100 | Rotate |  | 7861 | 12.15 | 47.73 | 7718.4 | 1137.13 | 805.46 | 1137.13 | 0.95 |  |  | 35 | 80 | 900 | 17000 | 600 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 04:25 | 04:45 | 0.33333 | 7873 | 7939 | 66 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 198 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 04:50 | 05:10 | 0.33333 | 7939 | 7959 | 20 | Slide | -45 | 7955 | 10.72 | 45.72 | 7810.53 | 1149.89 | 819.04 | 1149.89 | 1.58 |  |  | 35 | 80 | 900 | 17000 | 60 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 05:10 | 05:40 | 0.5 | 7959 | 8044 | 85 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 170 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 05:45 | 06:36 | 0.85 | 8044 | 8064 | 20 | Slide | -45 | 8049 | 10.86 | 41.63 | 7902.87 | 1162.61 | 831.18 | 1162.61 | 0.83 |  |  | 35 |  | 900 |  | 23.53 | 4300 | 3900 | 400 | 194 | 270 | 210 | 180
05/16/2021 | 06:36 | 06:52 | 0.26667 | 8064 | 8119 | 55 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 206.25 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 06:57 | 07:00 | 0.05 | 8119 | 8130 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 220 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 07:00 | 07:57 | 0.95 | 8130 | 8147 | 17 | Slide | -30 | 8143 | 11.73 | 35.46 | 7995.05 | 1177.02 | 842.61 | 1177.02 | 1.58 |  |  | 35 |  | 900 |  | 17.89 | 4300 | 3900 | 400 | 194 | 270 | 210 | 180
05/16/2021 | 07:57 | 08:15 | 0.3 | 8147 | 8213 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 220 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 08:25 | 08:30 | 0.083333 | 8213 | 8225 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 144 | 4300 | 3900 | 400 | 194 | 240 | 210 | 180
05/16/2021 | 08:30 | 09:35 | 1.0833 | 8225 | 8245 | 20 | Slide | 0 | 8236 | 11.71 | 28.79 | 8086.11 | 1192.99 | 852.64 | 1192.99 | 1.46 |  |  | 35 |  | 900 |  | 18.46 | 4300 | 3900 | 400 | 219 | 270 | 210 | 180
05/16/2021 | 09:35 | 09:50 | 0.25 | 8245 | 8275 | 30 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 4300 | 3900 | 400 | 219 | 240 | 210 | 180
05/16/2021 | 09:50 | 10:20 | 0.5 | 8275 | 8285 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 20 | 4300 | 3900 | 400 | 219 | 270 | 210 | 180
05/16/2021 | 10:20 | 10:31 | 0.18333 | 8285 | 8306 | 21 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 114.55 | 4300 | 3900 | 400 | 219 | 270 | 210 | 180
05/16/2021 | 10:41 | 10:54 | 0.21667 | 8306 | 8400 | 94 | Rotate |  | 8330 | 12.34 | 23.84 | 8178.05 | 1210.54 | 861.29 | 1210.54 | 1.29 |  |  | 40 | 80 | 900 | 22000 | 433.85 | 4850 | 4350 | 500 | 219 | 270 | 210 | 180
05/16/2021 | 11:00 | 11:18 | 0.3 | 8400 | 8494 | 94 | Rotate |  | 8424 | 11.14 | 20.97 | 8270.09 | 1228.2 | 868.6 | 1228.2 | 1.42 |  |  | 40 | 80 | 900 | 22000 | 313.33 | 4850 | 4350 | 500 | 219 | 270 | 210 | 180
05/16/2021 | 11:28 | 11:46 | 0.3 | 8494 | 8589 | 95 | Rotate |  | 8519 | 10.17 | 17.73 | 8363.45 | 1244.76 | 874.44 | 1244.76 | 1.2 |  |  | 40 | 80 | 900 | 22000 | 316.67 | 4850 | 4350 | 500 | 219 | 270 | 210 | 180
05/16/2021 | 11:56 | 12:00 | 0.066667 | 8589 | 8595 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 4850 | 4350 | 500 | 219 | 270 | 210 | 180
05/16/2021 | 12:00 | 12:29 | 0.48333 | 8595 | 8622 | 27 | Slide | 40 | 8613 | 10.06 | 22.98 | 8455.99 | 1260.23 | 880.17 | 1260.23 | 0.99 |  |  | 40 |  | 900 |  | 55.86 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 12:29 | 12:48 | 0.31667 | 8622 | 8683 | 61 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 192.63 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 12:58 | 13:01 | 0.05 | 8683 | 8695 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 240 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 13:01 | 13:35 | 0.56667 | 8695 | 8725 | 30 | Slide | 40 | 8708 | 11.06 | 26.58 | 8549.38 | 1276.02 | 887.49 | 1276.02 | 1.26 |  |  | 40 |  | 900 |  | 52.94 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 13:35 | 13:51 | 0.26667 | 8725 | 8778 | 53 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 198.75 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 14:00 | 14:05 | 0.083333 | 8778 | 8790 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 144 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 14:05 | 14:25 | 0.33333 | 8790 | 8816 | 26 | Slide | 40 | 8801 | 12.49 | 32.28 | 8640.42 | 1292.5 | 896.85 | 1292.5 | 1.98 |  |  | 40 |  | 900 |  | 78 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 14:25 | 14:41 | 0.26667 | 8816 | 8871 | 55 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 206.25 | 4850 | 4350 | 500 | 228 | 270 | 210 | 180
05/16/2021 | 14:50 | 15:16 | 0.43333 | 8871 | 8964 | 93 | Rotate |  | 8894 | 12.75 | 32.93 | 8731.18 | 1309.61 | 907.8 | 1309.61 | 0.32 |  |  | 40 | 80 | 680 | 22000 | 214.62 | 3400 | 2800 | 600 | 228 | 270 | 210 | 180
05/16/2021 | 15:26 | 15:48 | 0.36667 | 8964 | 9058 | 94 | Rotate |  | 8988 | 11.49 | 29.99 | 8823.08 | 1326.43 | 918.12 | 1326.43 | 1.49 |  |  | 40 | 80 | 680 | 22000 | 256.36 | 3400 | 2800 | 600 | 228 | 270 | 210 | 180
05/16/2021 | 15:58 | 16:02 | 0.066667 | 9058 | 9065 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 105 | 3400 | 2800 | 600 | 228 | 270 | 210 | 180
05/16/2021 | 16:02 | 17:12 | 1.1667 | 9065 | 9082 | 17 | Slide | TTF: 60; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 14.57 | 3400 | 2800 | 600 | 228 | 270 | 210 | 180
05/16/2021 | 17:12 | 17:26 | 0.23333 | 9082 | 9122 | 40 | Rotate |  | 9082 | 10.39 | 28.01 | 8915.37 | 1342.02 | 926.78 | 1342.02 | 1.24 |  |  | 40 | 80 | 680 | 22000 | 171.43 | 3400 | 2800 | 600 | 228 | 270 | 210 | 180
05/16/2021 | 17:26 | 18:55 | 1.4833 | 9122 | 9152 | 30 | Slide | TTF: 60; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 20.22 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/16/2021 | 19:00 | 19:15 | 0.25 | 9152 | 9170 | 18 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 72 | 3400 | 2800 | 600 | 228 | 270 | 210 | 180
05/16/2021 | 19:15 | 20:35 | 1.3333 | 9170 | 9194 | 24 | Slide | 60 | 9177 | 12.57 | 37.74 | 9008.47 | 1357.76 | 937.13 | 1357.76 | 3.06 |  |  | 40 |  | 900 |  | 18 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/16/2021 | 20:35 | 21:15 | 0.66667 | 9194 | 9247 | 53 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 79.5 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/16/2021 | 21:15 | 21:35 | 0.33333 | 9247 | 9352 | 105 | Rotate |  | 9270 | 12.03 | 38.02 | 9099.34 | 1373.4 | 949.3 | 1373.4 | 0.58 |  |  | 40 | 80 | 900 | 22000 | 315 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/16/2021 | 21:40 | 23:10 | 1.5 | 9352 | 9377 | 25 | Slide | 50 | 9364 | 10.88 | 36.76 | 9191.46 | 1388.23 | 960.64 | 1388.23 | 1.25 |  |  | 40 |  | 900 |  | 16.67 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/16/2021 | 23:10 | 23:25 | 0.25 | 9377 | 9397 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 80 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/16/2021 | 23:25 | 24:00 | 0.58333 | 9397 | 9424 | 27 | Slide | TTF: 45; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 46.29 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/17/2021 | 00:00 | 00:15 | 0.25 | 9424 | 9444 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 80 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 00:20 | 01:15 | 0.91667 | 9444 | 9460 | 16 | Slide | 60 | 9458 | 11.34 | 38.46 | 9283.7 | 1402.57 | 971.7 | 1402.57 | 0.6 |  |  | 40 |  | 900 |  | 17.45 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/17/2021 | 01:15 | 01:35 | 0.33333 | 9460 | 9528 | 68 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 204 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 02:00 | 02:10 | 0.16667 | 9528 | 9543 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 02:10 | 03:20 | 1.1667 | 9543 | 9573 | 30 | Slide | 60 | 9552 | 10.65 | 36.73 | 9375.98 | 1416.77 | 982.64 | 1416.77 | 0.81 |  |  | 40 |  | 900 |  | 25.71 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/17/2021 | 03:20 | 03:35 | 0.25 | 9573 | 9622 | 49 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 196 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 05:30 | 05:35 | 0.083333 | 9622 | 9637 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 180 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 05:35 | 06:06 | 0.51667 | 9637 | 9652 | 15 | Slide | 60 | 9647 | 10.17 | 37.57 | 9469.41 | 1430.45 | 993 | 1430.45 | 0.53 |  |  | 40 |  | 900 |  | 29.03 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/17/2021 | 06:06 | 06:26 | 0.33333 | 9652 | 9717 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 195 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 06:36 | 06:41 | 0.083333 | 9717 | 9725 | 8 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 96 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 06:41 | 07:17 | 0.6 | 9725 | 9765 | 40 | Slide | 60 | 9740 | 10.82 | 47.12 | 9560.86 | 1442.9 | 1004.41 | 1442.9 | 1.99 |  |  | 40 |  | 900 |  | 66.67 | 5300 | 4900 | 400 | 228 | 305 | 210 | 180
05/17/2021 | 07:17 | 07:30 | 0.21667 | 9765 | 9810 | 45 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 207.69 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 07:40 | 07:58 | 0.3 | 9810 | 9904 | 94 | Rotate |  | 9834 | 11.17 | 52.87 | 9653.14 | 1454.4 | 1018.13 | 1454.4 | 1.22 |  |  | 40 | 80 | 900 | 22000 | 313.33 | 5600 | 4900 | 700 | 228 | 305 | 210 | 180
05/17/2021 | 08:05 | 08:35 | 0.5 | 9904 | 9997 | 93 | Rotate |  | 9927 | 9.59 | 49.09 | 9744.62 | 1464.91 | 1031.17 | 1464.91 | 1.85 |  |  | 40 | 80 | 900 | 22000 | 186 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 08:45 | 09:00 | 0.25 | 9997 | 10091 | 94 | Rotate |  | 10021 | 8.61 | 46.51 | 9837.43 | 1474.88 | 1042.19 | 1474.88 | 1.13 |  |  | 40 | 80 | 900 | 22000 | 376 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 09:10 | 09:22 | 0.2 | 10091 | 10184 | 93 | Rotate |  | 10114 | 7.27 | 41.65 | 9929.54 | 1484.07 | 1051.15 | 1484.07 | 1.61 |  |  | 40 | 80 | 900 | 22000 | 465 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 09:32 | 09:37 | 0.083333 | 10184 | 10195 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 132 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 09:37 | 10:16 | 0.65 | 10195 | 10209 | 14 | Slide | 60 | 10208 | 6.17 | 37.16 | 10022.89 | 1492.54 | 1058.16 | 1492.54 | 1.3 |  |  | 27 |  | 900 |  | 21.54 | 5600 | 5400 | 200 | 248 | 325 | 285 | 210
05/17/2021 | 10:16 | 10:27 | 0.18333 | 10209 | 10225 | 16 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 87.27 | 5800 | 5400 | 400 | 248 | 325 | 285 | 210
05/17/2021 | 10:27 | 10:59 | 0.53333 | 10225 | 10236 | 11 | Slide | TTF: 60; Drilling Parameters WOB: 27; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 20.63 | 5600 | 5400 | 200 | 248 | 325 | 285 | 210
05/17/2021 | 10:59 | 11:12 | 0.21667 | 10236 | 10278 | 42 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 193.85 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 11:22 | 11:27 | 0.083333 | 10278 | 10285 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 84 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 11:27 | 11:48 | 0.35 | 10285 | 10307 | 22 | Slide | 60 | 10302 | 6.28 | 44.74 | 10116.34 | 1500.22 | 1064.83 | 1500.22 | 0.88 |  |  | 27 |  | 900 |  | 62.86 | 5600 | 5400 | 200 | 248 | 325 | 285 | 210
05/17/2021 | 11:48 | 12:05 | 0.28333 | 10307 | 10372 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 229.41 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 12:15 | 12:22 | 0.11667 | 10372 | 10408 | 36 | Rotate |  | 10396 | 5.27 | 48.29 | 10209.86 | 1506.74 | 1071.67 | 1506.74 | 1.14 |  |  | 40 | 80 | 900 | 22000 | 308.57 | 5600 | 4900 | 700 | 248 | 305 | 210 | 180
05/17/2021 | 12:22 | 12:43 | 0.35 | 10408 | 10466 | 58 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 165.71 | 3850 | 3250 | 600 | 248 | 305 | 210 | 180
05/17/2021 | 12:53 | 13:02 | 0.15 | 10466 | 10524 | 58 | Rotate |  | 10490 | 4.97 | 46.63 | 10303.49 | 1512.41 | 1077.85 | 1512.41 | 0.36 |  |  | 40 | 80 | 680 | 22000 | 386.67 | 3850 | 3250 | 600 | 248 | 305 | 210 | 180
05/17/2021 | 13:02 | 13:13 | 0.18333 | 10524 | 10560 | 36 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 196.36 | 5800 | 5400 | 400 | 248 | 305 | 210 | 180
05/17/2021 | 13:23 | 13:28 | 0.083333 | 10560 | 10570 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 5800 | 5400 | 400 | 248 | 305 | 210 | 180
05/17/2021 | 13:28 | 14:08 | 0.66667 | 10570 | 10585 | 15 | Slide | 30 | 10583 | 3.95 | 39.05 | 10396.21 | 1517.67 | 1082.8 | 1517.67 | 1.26 |  |  | 32 |  | 900 |  | 22.5 | 5600 | 5400 | 200 | 248 | 325 | 285 | 210
05/17/2021 | 14:08 | 14:26 | 0.3 | 10585 | 10653 | 68 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 226.67 | 5800 | 5400 | 400 | 248 | 305 | 210 | 180
05/17/2021 | 14:36 | 14:40 | 0.066667 | 10653 | 10660 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 105 | 5800 | 5400 | 400 | 248 | 305 | 210 | 180
05/17/2021 | 14:40 | 15:43 | 1.05 | 10660 | 10678 | 18 | Slide | 20 | 10678 | 4.3 | 32.07 | 10490.96 | 1523.22 | 1086.75 | 1523.22 | 0.64 |  |  | 40 |  | 680 |  | 17.14 | 3650 | 3350 | 300 | 248 | 315 | 285 | 210
05/17/2021 | 15:43 | 15:55 | 0.2 | 10678 | 10710 | 32 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 160 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 15:55 | 16:44 | 0.81667 | 10710 | 10728 | 18 | Slide | TTF: 20; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 22.04 | 3650 | 3350 | 300 | 248 | 315 | 285 | 210
05/17/2021 | 16:44 | 16:56 | 0.2 | 10728 | 10748 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 100 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 17:02 | 17:06 | 0.066667 | 10748 | 10755 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 105 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 17:06 | 18:20 | 1.2333 | 10755 | 10783 | 28 | Slide | 60 | 10772 | 4.4 | 41.58 | 10584.69 | 1528.91 | 1091.02 | 1528.91 | 0.77 |  |  | 40 | 80 | 680 | 22000 | 22.7 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 18:20 | 18:30 | 0.16667 | 10783 | 10803 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 18:30 | 19:30 | 1 | 10803 | 10820 | 17 | Slide | TTF: 60; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 17 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 19:30 | 19:45 | 0.25 | 10820 | 10842 | 22 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 88 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 20:15 | 20:45 | 0.5 | 10842 | 10936 | 94 | Rotate |  | 10866 | 4.38 | 34.6 | 10678.42 | 1534.56 | 1095.45 | 1534.56 | 0.57 |  |  | 40 | 80 | 680 | 22000 | 188 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 21:15 | 21:35 | 0.33333 | 10936 | 11030 | 94 | Rotate |  | 10960 | 3.93 | 17.45 | 10772.17 | 1540.59 | 1098.45 | 1540.59 | 1.4 |  |  | 40 | 80 | 680 | 22000 | 282 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 21:35 | 22:20 | 0.75 | 11030 | 11135 | 105 | Rotate |  | 11053 | 3.81 | 358.97 | 10864.96 | 1546.72 | 1099.35 | 1546.72 | 1.34 |  |  | 40 | 80 | 680 | 22000 | 140 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 22:25 | 23:15 | 0.83333 | 11135 | 11155 | 20 | Slide | 120 | 11147 | 3.88 | 347.34 | 10958.75 | 1552.94 | 1098.6 | 1552.94 | 0.83 |  |  | 40 | 80 | 680 | 22000 | 24 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/17/2021 | 23:15 | 23:40 | 0.41667 | 11155 | 11217 | 62 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 148.8 | 3950 | 3350 | 600 | 248 | 315 | 285 | 210
05/18/2021 | 00:15 | 00:25 | 0.16667 | 11217 | 11228 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 66 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 00:25 | 01:15 | 0.83333 | 11228 | 11244 | 16 | Slide | 150 | 11240 | 3.95 | 339.68 | 11051.54 | 1559.02 | 1096.8 | 1559.02 | 0.57 |  |  | 40 | 80 | 680 | 22000 | 19.2 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 01:15 | 01:25 | 0.16667 | 11244 | 11264 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 01:25 | 02:00 | 0.58333 | 11264 | 11290 | 26 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 44.57 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 02:00 | 02:20 | 0.33333 | 11290 | 11310 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 60 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 02:25 | 02:35 | 0.16667 | 11310 | 11327 | 17 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 102 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 02:35 | 04:45 | 2.1667 | 11327 | 11365 | 38 | Slide | 150 | 11334 | 3.01 | 339.3 | 11145.36 | 1564.36 | 1094.8 | 1564.36 | 1 |  |  | 40 | 80 | 680 | 22000 | 17.54 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 04:45 | 05:20 | 0.58333 | 11365 | 11404 | 39 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 66.86 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 05:35 | 05:45 | 0.16667 | 11404 | 11419 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 90 | 3950 | 3350 | 600 |  | 315 | 285 | 210
05/18/2021 | 05:45 | 06:50 | 1.0833 | 11419 | 11430 | 11 | Slide | 130 | 11427 | 2.62 | 339.22 | 11238.25 | 1568.63 | 1093.18 | 1568.63 | 0.42 |  |  | 25 |  | 680 |  | 10.15 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 06:50 | 07:15 | 0.41667 | 11430 | 11468 | 38 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 91.2 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 07:15 | 09:10 | 1.9167 | 11468 | 11488 | 20 | Slide | TTF: 130; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 10.43 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 09:10 | 09:23 | 0.21667 | 11488 | 11497 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 41.54 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 09:33 | 09:43 | 0.16667 | 11497 | 11510 | 13 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 78 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 09:43 | 11:09 | 1.4333 | 11510 | 11540 | 30 | Slide | 130 | 11521 | 2.19 | 31.58 | 11332.18 | 1572.17 | 1093.36 | 1572.17 | 2.29 |  |  | 25 |  | 680 |  | 20.93 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 11:50 | 12:18 | 0.46667 | 11540 | 11591 | 51 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 109.29 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 12:28 | 12:48 | 0.33333 | 11591 | 11660 | 69 | Rotate |  | 11614 | 1.7 | 54.45 | 11425.13 | 1574.49 | 1095.41 | 1574.49 | 0.98 |  |  | 40 | 80 | 680 | 22000 | 207 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 12:53 | 13:35 | 0.7 | 11660 | 11684 | 24 | Slide | TTF: 150; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 34.29 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 14:42 | 14:47 | 0.083333 | 11684 | 11700 | 16 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 192 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 14:47 | 17:16 | 2.4833 | 11700 | 11773 | 73 | Slide | 140 | 11708 | 3.76 | 99.54 | 11519.02 | 1574.79 | 1099.59 | 1574.79 | 3.01 |  |  | 25 |  | 680 |  | 29.4 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 17:16 | 17:21 | 0.083333 | 11773 | 11778 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 60 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 17:26 | 19:20 | 1.9 | 11778 | 11802 | 24 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 12.63 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 20:30 | 21:10 | 0.66667 | 11802 | 11808 | 6 | Slide | 20 | 11802 | 6.23 | 124.67 | 11612.67 | 1571.38 | 1106.83 | 1571.38 | 3.45 |  |  | 25 |  | 680 |  | 9 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 21:45 | 22:32 | 0.78333 | 11808 | 11815 | 7 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 8.94 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 22:32 | 23:15 | 0.71667 | 11815 | 11872 | 57 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 79.53 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 23:20 | 23:50 | 0.5 | 11872 | 11881 | 9 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 18 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/18/2021 | 23:50 | 24:00 | 0.16667 | 11881 | 11893 | 12 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 680; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 72 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/19/2021 | 00:00 | 00:20 | 0.33333 | 11893 | 11926 | 33 | Rotate |  | 11896 | 5.42 | 127.01 | 11706.18 | 1565.8 | 1114.57 | 1565.8 | 0.9 |  |  | 40 | 80 | 680 | 22000 | 99 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/19/2021 | 00:30 | 02:30 | 2 | 11926 | 11966 | 40 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 20 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/19/2021 | 02:35 | 04:00 | 1.4167 | 11966 | 11982 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 11.29 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210
05/19/2021 | 04:45 | 04:50 | 0.083333 | 11982 | 11985 | 3 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 680; Drilling Parameters ROP: 36 | 3950 | 3350 | 600 | 246 | 315 | 285 | 210

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 555
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 545
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 67.00 / 54.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 10
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/21/2021 | 16:12 | 16:23 | 0.18333 | 11985 | 11995 | 10 | Rotate |  | 11990 | 6.14 | 135.25 | 11799.74 | 1559.78 | 1121.44 | 1559.78 | 1.56 |  |  | 18 | 30 | 195 | 19000 | 54.55 | 2600 | 2300 | 300 |  | 310 | 250 | 190
05/21/2021 | 17:27 | 19:39 | 2.2 | 11995 | 12057 | 62 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 195; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 28.18 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/21/2021 | 19:47 | 20:35 | 0.8 | 12057 | 12102 | 45 | Slide | -20 | 12085 | 15.62 | 145.67 | 11892.93 | 1545.57 | 1132.26 | 1545.57 | 10.15 |  |  | 18 | 30 | 195 | 19000 | 56.25 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/21/2021 | 20:50 | 21:37 | 0.78333 | 12102 | 12152 | 50 | Slide | TTF: -45; Drilling Parameters WOB: 18; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 195; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 63.83 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/21/2021 | 22:05 | 23:05 | 1 | 12152 | 12248 | 96 | Slide | -45 | 12181 | 23.96 | 139.68 | 11983.19 | 1519.99 | 1152.2 | 1519.99 | 8.93 |  |  | 18 | 30 | 195 | 19000 | 96 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/21/2021 | 23:25 | 24:00 | 0.58333 | 12248 | 12293 | 45 | Slide | TTF: -30; Drilling Parameters WOB: 18; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 195; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 77.14 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/22/2021 | 00:00 | 00:55 | 0.91667 | 12293 | 12342 | 49 | Slide | -30 | 12339 | 32.89 | 150.78 | 12123.71 | 1458.93 | 1189.76 | 1458.93 | 8.48 |  |  | 18 | 30 | 195 | 19000 | 53.45 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/22/2021 | 01:06 | 01:15 | 0.15 | 12342 | 12350 | 8 | Slide | TTF: -30; Drilling Parameters WOB: 18; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 195; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 53.33 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/22/2021 | 01:25 | 02:45 | 1.3333 | 12350 | 12437 | 87 | Slide | -30 | 12436 | 42.09 | 141.13 | 12200.66 | 1410.49 | 1223.12 | 1410.49 | 11.23 |  |  | 18 | 30 | 195 | 19000 | 65.25 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/22/2021 | 03:00 | 04:05 | 1.0833 | 12437 | 12523 | 86 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 195; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 79.38 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/22/2021 | 05:05 | 05:25 | 0.33333 | 12523 | 12533 | 10 | Slide | 0 | 12532 | 55.51 | 135.63 | 12263.78 | 1356.89 | 1271.22 | 1356.89 | 14.62 |  |  | 18 | 30 | 195 | 19000 | 30 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190
05/22/2021 | 05:35 | 06:08 | 0.55 | 12533 | 12540 | 7 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 195; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 12.73 | 5400 | 4700 | 700 | 284 | 310 | 250 | 190

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 315
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 315
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 61.00 / 48.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 0
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/23/2021 | 22:35 | 24:00 | 1.4167 | 11990 | 11992 | 2 | Slide | -50 | 11990 | 6.14 | 135.25 | 11799.74 | 1559.78 | 1121.44 | 1559.78 | 1.56 |  |  | 10000 |  | 240 |  | 1.41 | 2800 | 2700 | 100 | 242 | 205 | 205 | 205
05/24/2021 | 00:00 | 05:55 | 5.9167 | 11992 | 12001 | 9 | Slide | TTF: -50; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 1.52 | 2800 | 2700 | 100 | 242 | 205 | 205 | 205
05/24/2021 | 06:40 | 10:20 | 3.6667 | 12001 | 12006 | 5 | Slide | TTF: -50; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 1.36 | 2800 | 2700 | 100 | 242 | 205 | 205 | 205
05/24/2021 | 10:20 | 11:27 | 1.1167 | 12006 | 12020 | 14 | Slide | TTF: -50; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 12.54 | 2800 | 2700 | 100 | 242 | 205 | 205 | 205
05/24/2021 | 18:04 | 24:00 | 5.9333 | 12020 | 12229 | 209 | Slide | 135 | 12085 | 15.62 | 145.67 | 11892.93 | 1545.57 | 1132.26 | 1545.57 | 10.15 |  |  | 10000 |  | 240 |  | 35.22 | 2700 | 2600 | 100 | 242 | 205 | 205 | 205
05/25/2021 | 00:00 | 08:50 | 8.8333 | 12229 | 12235 | 6 | Slide | TTF: 135; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 0.68 | 2700 | 2600 | 100 | 242 | 205 | 205 | 205
05/25/2021 | 08:50 | 10:28 | 1.6333 | 12235 | 12240 | 5 | Slide | TTF: 135; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 3.06 | 2700 | 2600 | 100 | 248 | 205 | 205 | 205
05/25/2021 | 10:28 | 11:15 | 0.78333 | 12240 | 12245 | 5 | Slide | 135 | 12244 | 24.85 | 149.89 | 12040.59 | 1498.78 | 1167.12 | 1498.78 | 6.84 |  |  | 10000 |  | 240 |  | 6.38 | 2700 | 2600 | 100 | 248 | 205 | 205 | 205
05/25/2021 | 11:15 | 12:21 | 1.1 | 12245 | 12255 | 10 | Slide | TTF: 60; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 9.09 | 2700 | 2600 | 100 | 248 | 205 | 205 | 205
05/25/2021 | 12:21 | 13:07 | 0.76667 | 12255 | 12273 | 18 | Slide | TTF: 20; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 23.48 | 2700 | 2600 | 100 | 248 | 205 | 205 | 205
05/25/2021 | 13:17 | 15:40 | 2.3833 | 12273 | 12293 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 8.39 | 2700 | 2600 | 100 | 248 | 205 | 205 | 205
05/25/2021 | 16:16 | 18:06 | 1.8333 | 12293 | 12305 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 10000; Drilling Parameters FLOW: 240; Drilling Parameters ROP: 6.55 | 2700 | 2600 | 100 | 248 | 205 | 205 | 205

## BHA_5_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 420
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 371
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 67.00 / 54.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 49
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/26/2021 | 15:20 | 15:51 | 0.51667 | 12305 | 12311 | 6 | Slide | TTF: -40; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 345; Drilling Parameters ROP: 11.61 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 16:00 | 17:23 | 1.3833 | 12311 | 12375 | 64 | Slide | -30 | 12339 | 32.89 | 150.78 | 12123.71 | 1458.93 | 1189.76 | 1458.93 | 8.48 |  |  | 30 |  | 345 |  | 46.27 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 17:33 | 18:12 | 0.65 | 12375 | 12406 | 31 | Slide | TTF: -30; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 345; Drilling Parameters ROP: 47.69 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 18:22 | 20:05 | 1.7167 | 12406 | 12503 | 97 | Slide | -30 | 12436 | 42.09 | 141.13 | 12200.66 | 1410.49 | 1223.12 | 1410.49 | 11.23 |  |  | 30 |  | 345 |  | 56.5 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 20:10 | 21:30 | 1.3333 | 12503 | 12599 | 96 | Slide | -30 | 12532 | 55.51 | 135.63 | 12263.78 | 1356.89 | 1271.22 | 1356.89 | 14.62 |  |  | 30 |  | 345 |  | 72 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 21:40 | 22:10 | 0.5 | 12599 | 12631 | 32 | Slide | -30 | 12626 | 69.86 | 133.11 | 12306.8 | 1298.73 | 1330.84 | 1298.73 | 15.45 |  |  | 30 |  | 345 |  | 64 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 22:10 | 22:20 | 0.16667 | 12631 | 12648 | 17 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters FLOW: 345; Drilling Parameters ROP: 102 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 22:20 | 23:04 | 0.73333 | 12648 | 12693 | 45 | Slide | TTF: -30; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 345; Drilling Parameters ROP: 61.36 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175
05/26/2021 | 23:04 | 24:00 | 0.93333 | 12693 | 12725 | 32 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters FLOW: 345; Drilling Parameters ROP: 34.29 | 5000 | 4450 | 550 | 258 | 320 | 220 | 175

## BHA_6_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 6 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2769
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 346
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 2423
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/28/2021 | 04:35 | 06:30 | 1.9167 | 12725 | 12765 | 40 | Slide | -70 | 12754 | 76.84 | 129.35 | 12343.47 | 1218.03 | 1423.04 | 1218.03 | 6.14 |  |  | 30 |  | 350 |  | 20.87 | 5100 | 4700 | 400 |  | 310 | 210 | 150
05/28/2021 | 06:30 | 07:15 | 0.75 | 12765 | 12822 | 57 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 76 | 6700 | 5920 | 780 | 285 | 310 | 210 | 150
05/28/2021 | 07:20 | 08:45 | 1.4167 | 12822 | 12872 | 50 | Slide | -30 | 12849 | 80 | 126.6 | 12362.54 | 1160.79 | 1496.4 | 1160.79 | 4.37 |  |  | 25 |  | 400 |  | 35.29 | 6700 | 5920 | 780 | 285 | 310 | 210 | 150
05/28/2021 | 08:45 | 09:15 | 0.5 | 12872 | 12912 | 40 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 80 | 6700 | 5920 | 780 | 285 | 310 | 210 | 150
05/28/2021 | 09:20 | 10:20 | 1 | 12912 | 12962 | 50 | Slide | 0 | 12943 | 86.52 | 123.29 | 12373.57 | 1107.37 | 1572.88 | 1107.37 | 7.77 |  |  | 35 |  | 400 |  | 50 | 6700 | 5920 | 780 | 285 | 310 | 210 | 150
05/28/2021 | 10:20 | 10:50 | 0.5 | 12962 | 13011 | 49 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 98 | 6700 | 5920 | 780 | 285 | 310 | 210 | 150
05/28/2021 | 10:55 | 11:40 | 0.75 | 13011 | 13107 | 96 | Rotate |  | 13039 | 88.01 | 121.1 | 12378.15 | 1056.28 | 1654.02 | 1056.28 | 2.76 |  |  | 30 | 30 | 400 | 17000 | 128 | 6700 | 5920 | 780 | 293 | 310 | 210 | 150
05/28/2021 | 11:45 | 12:15 | 0.5 | 13107 | 13127 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 40 | 6700 | 5920 | 780 | 293 | 310 | 210 | 150
05/28/2021 | 12:15 | 12:45 | 0.5 | 13127 | 13202 | 75 | Rotate |  | 13134 | 87.13 | 124.02 | 12382.18 | 1005.21 | 1734 | 1005.21 | 3.21 |  |  | 30 | 30 | 400 | 17000 | 150 | 6700 | 5920 | 780 | 293 | 310 | 210 | 150
05/28/2021 | 12:50 | 13:20 | 0.5 | 13202 | 13222 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 40 | 6700 | 5920 | 780 | 293 | 310 | 210 | 150
05/28/2021 | 13:20 | 13:55 | 0.58333 | 13222 | 13298 | 76 | Rotate |  | 13230 | 87 | 127.66 | 12387.1 | 949.08 | 1811.71 | 949.08 | 3.79 |  |  | 30 | 30 | 400 | 17000 | 130.29 | 6700 | 5920 | 780 | 293 | 310 | 210 | 150
05/28/2021 | 14:00 | 14:20 | 0.33333 | 13298 | 13318 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 6700 | 5920 | 780 | 293 | 310 | 210 | 150
05/28/2021 | 14:20 | 14:45 | 0.41667 | 13318 | 13393 | 75 | Rotate |  | 13325 | 87.22 | 130.95 | 12391.89 | 888.99 | 1885.12 | 888.99 | 3.47 |  |  | 30 | 80 | 400 | 16000 | 180 | 6700 | 5920 | 780 | 300 | 310 | 210 | 150
05/28/2021 | 14:50 | 15:30 | 0.66667 | 13393 | 13488 | 95 | Rotate |  | 13420 | 86.38 | 130.88 | 12397.19 | 826.87 | 1956.79 | 826.87 | 0.89 |  |  | 30 | 80 | 400 | 16000 | 142.5 | 6700 | 5920 | 780 | 300 | 310 | 210 | 150
05/28/2021 | 15:35 | 16:10 | 0.58333 | 13488 | 13582 | 94 | Rotate |  | 13514 | 85.25 | 131.43 | 12404.05 | 765.17 | 2027.38 | 765.17 | 1.34 |  |  | 30 | 70 | 375 | 16000 | 161.14 | 5900 | 5000 | 900 | 303 | 310 | 210 | 150
05/28/2021 | 16:15 | 16:50 | 0.58333 | 13582 | 13602 | 20 | Slide | TTF: 30; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 34.29 | 5900 | 5000 | 900 | 303 | 310 | 210 | 150
05/28/2021 | 16:50 | 17:20 | 0.5 | 13602 | 13677 | 75 | Rotate |  | 13609 | 86.44 | 133.03 | 12410.93 | 701.49 | 2097.53 | 701.49 | 2.1 |  |  | 30 | 70 | 375 | 16000 | 150 | 5900 | 5000 | 900 | 307 | 310 | 210 | 150
05/28/2021 | 17:25 | 17:50 | 0.41667 | 13677 | 13690 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 31.2 | 5400 | 5000 | 400 | 307 | 310 | 210 | 150
05/28/2021 | 17:50 | 18:20 | 0.5 | 13690 | 13774 | 84 | Rotate |  | 13706 | 90.4 | 133.8 | 12413.61 | 634.86 | 2167.95 | 634.86 | 4.16 |  |  | 30 | 70 | 375 | 16000 | 168 | 5900 | 5000 | 900 | 307 | 310 | 210 | 150
05/28/2021 | 18:25 | 18:30 | 0.083333 | 13774 | 13781 | 7 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 84 | 5900 | 5000 | 900 | 307 | 310 | 210 | 150
05/28/2021 | 18:30 | 18:50 | 0.33333 | 13781 | 13793 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 36 | 5400 | 5000 | 400 | 307 | 310 | 210 | 150
05/28/2021 | 18:50 | 19:15 | 0.41667 | 13793 | 13868 | 75 | Rotate |  | 13800 | 90.26 | 134.06 | 12413.07 | 569.65 | 2235.65 | 569.65 | 0.31 |  |  | 30 | 70 | 375 | 18000 | 180 | 5400 | 5000 | 400 | 300 | 310 | 215 | 160
05/28/2021 | 19:20 | 19:25 | 0.083333 | 13868 | 13875 | 7 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 84 | 5400 | 4500 | 900 | 300 | 310 | 215 | 160
05/28/2021 | 19:25 | 19:55 | 0.5 | 13875 | 13890 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 30 | 5000 | 4500 | 500 | 300 | 310 | 215 | 160
05/28/2021 | 19:55 | 20:20 | 0.41667 | 13890 | 13962 | 72 | Rotate |  | 13894 | 88.68 | 133.99 | 12413.94 | 504.33 | 2303.23 | 504.33 | 1.68 |  |  | 30 | 80 | 350 | 20000 | 172.8 | 5400 | 4500 | 900 | 300 | 310 | 215 | 160
05/28/2021 | 20:25 | 20:30 | 0.083333 | 13962 | 13968 | 6 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 72 | 5400 | 4500 | 900 | 300 | 310 | 215 | 160
05/28/2021 | 21:30 | 21:55 | 0.41667 | 13968 | 13980 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 28.8 | 5000 | 4500 | 500 | 300 | 310 | 215 | 160
05/28/2021 | 21:55 | 22:25 | 0.5 | 13980 | 14057 | 77 | Rotate |  | 13989 | 85.74 | 134.64 | 12418.56 | 438.05 | 2371.12 | 438.05 | 3.17 |  |  | 30 | 80 | 350 | 20000 | 154 | 5400 | 4500 | 900 | 300 | 310 | 215 | 160
05/28/2021 | 22:30 | 23:00 | 0.5 | 14057 | 14151 | 94 | Rotate |  | 14083 | 84.65 | 134.92 | 12426.43 | 372.07 | 2437.61 | 372.07 | 1.2 |  |  | 25 | 80 | 350 | 20000 | 188 | 5400 | 4400 | 1000 | 295 | 310 | 215 | 160
05/28/2021 | 23:05 | 23:10 | 0.083333 | 14151 | 14158 | 7 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 84 | 5400 | 4400 | 1000 | 290 | 310 | 215 | 160
05/28/2021 | 23:10 | 23:40 | 0.5 | 14158 | 14170 | 12 | Slide | TTF: -30; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 24 | 4800 | 4400 | 400 | 290 | 310 | 215 | 160
05/28/2021 | 23:40 | 24:00 | 0.33333 | 14170 | 14214 | 44 | Rotate |  | 14178 | 85.24 | 134.8 | 12434.8 | 305.32 | 2504.68 | 305.32 | 0.63 |  |  | 22 | 80 | 350 | 20000 | 132 | 5400 | 4400 | 1000 | 290 | 310 | 215 | 160
05/29/2021 | 00:00 | 00:10 | 0.16667 | 14214 | 14246 | 32 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 192 | 5400 | 4400 | 1000 | 290 | 310 | 215 | 160
05/29/2021 | 00:15 | 00:20 | 0.083333 | 14246 | 14256 | 10 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 120 | 5400 | 4400 | 1000 | 290 | 310 | 215 | 160
05/29/2021 | 00:20 | 00:50 | 0.5 | 14256 | 14266 | 10 | Slide | TTF: -45; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 20 | 4800 | 4400 | 400 | 290 | 310 | 215 | 160
05/29/2021 | 00:50 | 01:20 | 0.5 | 14266 | 14340 | 74 | Rotate |  | 14272 | 85.73 | 133.44 | 12442.2 | 240.08 | 2571.95 | 240.08 | 1.53 |  |  | 24 | 80 | 350 | 21000 | 148 | 5400 | 4400 | 1000 | 290 | 310 | 215 | 160
05/29/2021 | 02:00 | 02:05 | 0.083333 | 14340 | 14348 | 8 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 96 | 5400 | 4400 | 1000 | 285 | 310 | 215 | 160
05/29/2021 | 02:05 | 02:30 | 0.41667 | 14348 | 14360 | 12 | Slide | TTF: -30; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 28.8 | 4700 | 4400 | 300 | 285 | 310 | 215 | 160
05/29/2021 | 02:30 | 03:00 | 0.5 | 14360 | 14435 | 75 | Rotate |  | 14367 | 87.06 | 133.46 | 12448.18 | 174.88 | 2640.78 | 174.88 | 1.4 |  |  | 30 | 70 | 350 | 21000 | 150 | 5300 | 4400 | 900 | 280 | 310 | 215 | 160
05/29/2021 | 03:05 | 03:35 | 0.5 | 14435 | 14529 | 94 | Rotate |  | 14461 | 88.35 | 134.71 | 12451.94 | 109.54 | 2708.25 | 109.54 | 1.91 |  |  | 28 | 70 | 350 | 21000 | 188 | 5300 | 4400 | 900 | 280 | 330 | 215 | 160
05/29/2021 | 03:40 | 04:15 | 0.58333 | 14529 | 14625 | 96 | Rotate |  | 14557 | 89.12 | 135.54 | 12454.06 | 41.53 | 2775.96 | 41.53 | 1.18 |  |  | 28 | 70 | 350 | 21000 | 164.57 | 5300 | 4400 | 900 | 280 | 330 | 215 | 160
05/29/2021 | 04:20 | 04:25 | 0.083333 | 14625 | 14636 | 11 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 132 | 5300 | 4400 | 900 | 280 | 330 | 215 | 160
05/29/2021 | 04:25 | 04:55 | 0.5 | 14636 | 14651 | 15 | Slide | TTF: -90; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 30 | 4700 | 4400 | 300 | 280 | 330 | 215 | 160
05/29/2021 | 04:55 | 05:25 | 0.5 | 14651 | 14720 | 69 | Rotate |  | 14652 | 88.14 | 132.32 | 12456.33 | -24.36 | 2844.35 | -24.36 | 3.54 |  |  | 25 | 80 | 350 | 20000 | 138 | 5300 | 4400 | 900 | 286 | 330 | 215 | 160
05/29/2021 | 05:30 | 06:05 | 0.58333 | 14720 | 14816 | 96 | Rotate |  | 14748 | 87.6 | 131.36 | 12459.9 | -88.35 | 2915.82 | -88.35 | 1.15 |  |  | 25 | 80 | 350 | 20000 | 164.57 | 5300 | 4400 | 900 | 286 | 330 | 215 | 160
05/29/2021 | 06:10 | 06:45 | 0.58333 | 14816 | 14911 | 95 | Rotate |  | 14843 | 87.37 | 130.9 | 12464.07 | -150.78 | 2987.31 | -150.78 | 0.54 |  |  | 25 | 80 | 350 | 20000 | 162.86 | 5300 | 4400 | 900 | 286 | 330 | 215 | 160
05/29/2021 | 06:50 | 07:25 | 0.58333 | 14911 | 15005 | 94 | Rotate |  | 14937 | 87.67 | 131.3 | 12468.14 | -212.51 | 3058.08 | -212.51 | 0.53 |  |  | 25 | 80 | 350 | 20000 | 161.14 | 5300 | 4400 | 900 | 286 | 330 | 215 | 160
05/29/2021 | 07:30 | 08:05 | 0.58333 | 15005 | 15100 | 95 | Rotate |  | 15032 | 88.19 | 131.07 | 12471.57 | -275.03 | 3129.52 | -275.03 | 0.6 |  |  | 27 | 80 | 350 | 18500 | 162.86 | 5300 | 4400 | 900 | 305 | 330 | 215 | 160
05/29/2021 | 08:10 | 08:45 | 0.58333 | 15100 | 15195 | 95 | Rotate |  | 15127 | 88.63 | 131.12 | 12474.2 | -337.45 | 3201.09 | -337.45 | 0.47 |  |  | 27 | 80 | 350 | 18500 | 162.86 | 5300 | 4400 | 900 | 305 | 330 | 215 | 160
05/29/2021 | 08:50 | 09:50 | 1 | 15195 | 15210 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 15 | 5300 | 4400 | 900 | 305 | 330 | 215 | 160
05/29/2021 | 09:50 | 10:25 | 0.58333 | 15210 | 15290 | 80 | Rotate |  | 15222 | 87.72 | 132.21 | 12477.23 | -400.57 | 3272.02 | -400.57 | 1.49 |  |  | 27 | 80 | 350 | 18500 | 137.14 | 5300 | 4400 | 900 | 305 | 330 | 215 | 160
05/29/2021 | 10:30 | 11:10 | 0.66667 | 15290 | 15384 | 94 | Rotate |  | 15316 | 87.96 | 133.49 | 12480.77 | -464.45 | 3340.89 | -464.45 | 1.38 |  |  | 27 | 80 | 350 | 18500 | 141 | 5300 | 4400 | 900 | 309 | 330 | 215 | 160
05/29/2021 | 11:15 | 11:20 | 0.083333 | 15384 | 15394 | 10 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 120 | 5300 | 4400 | 900 | 309 | 330 | 215 | 160
05/29/2021 | 11:20 | 11:50 | 0.5 | 15394 | 15404 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 18500; Drilling Parameters ROP: 20 | 5300 | 4400 | 900 | 309 | 330 | 215 | 160
05/29/2021 | 11:50 | 12:50 | 1 | 15404 | 15480 | 76 | Rotate |  | 15412 | 87.52 | 134.51 | 12484.56 | -531.08 | 3409.89 | -531.08 | 1.16 |  |  | 35 | 80 | 350 | 23000 | 76 | 4900 | 4400 | 500 | 316 | 330 | 215 | 160
05/29/2021 | 12:55 | 13:15 | 0.33333 | 15480 | 15494 | 14 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 42 | 4900 | 4400 | 500 | 316 | 330 | 215 | 160

## BHA_7_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 7 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3083
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 290
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 67.00 / 54.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 2793
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
05/30/2021 | 19:10 | 19:40 | 0.5 | 15494 | 15572 | 78 | Rotate |  | 15505 | 88.85 | 135.05 | 12487.5 | -596.56 | 3475.87 | -596.56 | 1.54 |  |  | 23 | 80 | 350 | 21000 | 156 | 5500 | 4500 | 1000 | 304 | 325 | 260 | 200
05/30/2021 | 20:00 | 20:05 | 0.083333 | 15572 | 15579 | 7 | Rotate | Drilling Parameters WOB: 23; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 84 | 5500 | 4500 | 1000 | 304 | 325 | 260 | 200
05/30/2021 | 20:05 | 20:40 | 0.58333 | 15579 | 15594 | 15 | Slide | TTF: -130; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 25.71 | 4800 | 4500 | 300 | 304 | 325 | 260 | 200
05/30/2021 | 20:40 | 21:10 | 0.5 | 15594 | 15667 | 73 | Rotate |  | 15600 | 87.8 | 132.98 | 12490.28 | -662.53 | 3544.15 | -662.53 | 2.44 |  |  | 23 | 80 | 350 | 21000 | 146 | 5500 | 4500 | 1000 | 304 | 325 | 260 | 200
05/30/2021 | 21:15 | 21:45 | 0.5 | 15667 | 15762 | 95 | Rotate |  | 15695 | 88.07 | 134.33 | 12493.7 | -728.07 | 3612.84 | -728.07 | 1.45 |  |  | 25 | 80 | 350 | 21000 | 190 | 5500 | 4500 | 1000 | 307 | 325 | 260 | 200
05/30/2021 | 21:50 | 22:25 | 0.58333 | 15762 | 15774 | 12 | Slide | TTF: -150; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 20.57 | 4700 | 4500 | 200 | 307 | 325 | 260 | 200
05/30/2021 | 22:25 | 22:55 | 0.5 | 15774 | 15858 | 84 | Rotate |  | 15791 | 86.73 | 133.62 | 12498.06 | -794.66 | 3681.85 | -794.66 | 1.58 |  |  | 28 | 80 | 350 | 21000 | 168 | 5500 | 4500 | 1000 | 307 | 325 | 260 | 200
05/30/2021 | 23:00 | 23:25 | 0.41667 | 15858 | 15952 | 94 | Rotate |  | 15885 | 85.88 | 133.81 | 12504.12 | -859.48 | 3749.65 | -859.48 | 0.93 |  |  | 30 | 80 | 350 | 21000 | 225.6 | 5500 | 4500 | 1000 | 310 | 325 | 260 | 200
05/30/2021 | 23:30 | 24:00 | 0.5 | 15952 | 16035 | 83 | Rotate |  | 15981 | 84.63 | 134.09 | 12512.06 | -925.88 | 3818.53 | -925.88 | 1.33 |  |  | 24 | 80 | 350 | 21000 | 166 | 5500 | 4500 | 1000 | 310 | 325 | 260 | 200
05/31/2021 | 00:00 | 00:05 | 0.083333 | 16035 | 16048 | 13 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 156 | 5500 | 4500 | 1000 | 310 | 325 | 260 | 200
05/31/2021 | 00:10 | 00:15 | 0.083333 | 16048 | 16053 | 5 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 60 | 5500 | 4500 | 1000 | 310 | 325 | 260 | 200
05/31/2021 | 00:15 | 01:15 | 1 | 16053 | 16073 | 20 | Slide | TTF: -45; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 20 | 5000 | 4800 | 200 | 313 | 325 | 260 | 200
05/31/2021 | 01:15 | 01:45 | 0.5 | 16073 | 16143 | 70 | Rotate |  | 16076 | 84.72 | 133.02 | 12520.88 | -991.05 | 3887.08 | -991.05 | 1.13 |  |  | 25 | 80 | 350 | 21000 | 140 | 5500 | 4500 | 1000 | 313 | 325 | 260 | 200
05/31/2021 | 01:50 | 01:55 | 0.083333 | 16143 | 16150 | 7 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 84 | 5500 | 4500 | 1000 | 313 | 325 | 260 | 200
05/31/2021 | 01:55 | 03:15 | 1.3333 | 16150 | 16180 | 30 | Slide | 0 | 16170 | 86.44 | 132.04 | 12528.12 | -1054.4 | 3956.14 | -1054.4 | 2.1 |  |  | 32 |  | 370 |  | 22.5 | 5000 | 4800 | 200 | 313 | 325 | 260 | 200
05/31/2021 | 03:15 | 03:25 | 0.16667 | 16180 | 16207 | 27 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 162 | 5500 | 4500 | 1000 | 313 | 325 | 260 | 200
05/31/2021 | 03:35 | 04:10 | 0.58333 | 16207 | 16222 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 25.71 | 5000 | 4800 | 200 | 313 | 325 | 260 | 200
05/31/2021 | 04:10 | 04:15 | 0.083333 | 16222 | 16237 | 15 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 180 | 5500 | 4500 | 1000 | 313 | 325 | 260 | 200
05/31/2021 | 04:20 | 04:25 | 0.083333 | 16237 | 16243 | 6 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 72 | 5500 | 4500 | 1000 | 313 | 325 | 260 | 200
05/31/2021 | 04:25 | 05:15 | 0.83333 | 16243 | 16255 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 370; Drilling Parameters ROP: 14.4 | 5000 | 4800 | 200 | 313 | 325 | 260 | 200
05/31/2021 | 05:15 | 06:00 | 0.75 | 16255 | 16332 | 77 | Rotate |  | 16265 | 92.79 | 131.93 | 12528.76 | -1117.92 | 4026.72 | -1117.92 | 6.69 |  |  | 32 | 80 | 370 | 21000 | 102.67 | 5000 | 4800 | 200 | 313 | 325 | 260 | 200
05/31/2021 | 06:05 | 06:10 | 0.083333 | 16332 | 16338 | 6 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 72 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 06:10 | 06:55 | 0.75 | 16338 | 16353 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 20 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 06:55 | 07:35 | 0.66667 | 16353 | 16426 | 73 | Rotate |  | 16359 | 90.57 | 130.69 | 12526 | -1179.94 | 4097.29 | -1179.94 | 2.7 |  |  | 27 | 80 | 350 | 21000 | 109.5 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 07:40 | 08:20 | 0.66667 | 16426 | 16520 | 94 | Rotate |  | 16453 | 90.41 | 130.99 | 12525.2 | -1241.41 | 4168.4 | -1241.41 | 0.36 |  |  | 27 | 80 | 350 | 21000 | 141 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 08:25 | 09:05 | 0.66667 | 16520 | 16616 | 96 | Rotate |  | 16549 | 91.04 | 131.14 | 12523.98 | -1304.47 | 4240.78 | -1304.47 | 0.67 |  |  | 27 | 80 | 350 | 21000 | 144 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 09:10 | 09:50 | 0.66667 | 16616 | 16713 | 97 | Rotate |  | 16646 | 92.26 | 131.13 | 12521.19 | -1368.25 | 4313.8 | -1368.25 | 1.26 |  |  | 27 | 80 | 350 | 21000 | 145.5 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 09:55 | 10:00 | 0.083333 | 16713 | 16723 | 10 | Rotate | Drilling Parameters WOB: 27; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 120 | 5000 | 4400 | 600 | 318 | 325 | 260 | 200
05/31/2021 | 10:00 | 10:50 | 0.83333 | 16723 | 16738 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 18 | 5100 | 4900 | 200 | 318 | 325 | 260 | 200
05/31/2021 | 10:50 | 11:35 | 0.75 | 16738 | 16807 | 69 | Rotate |  | 16740 | 89.81 | 131.15 | 12519.49 | -1430.08 | 4384.58 | -1430.08 | 2.61 |  |  | 30 | 80 | 375 | 21000 | 92 | 5700 | 4900 | 800 | 318 | 325 | 260 | 200
05/31/2021 | 12:25 | 13:00 | 0.58333 | 16807 | 16902 | 95 | Rotate |  | 16835 | 88.61 | 131.19 | 12520.8 | -1492.61 | 4456.08 | -1492.61 | 1.26 |  |  | 30 | 80 | 375 | 21000 | 162.86 | 5700 | 4900 | 800 | 318 | 325 | 260 | 200
05/31/2021 | 13:05 | 13:55 | 0.83333 | 16902 | 16997 | 95 | Rotate |  | 16930 | 87.37 | 131.55 | 12524.13 | -1555.35 | 4527.33 | -1555.35 | 1.36 |  |  | 30 | 80 | 375 | 21000 | 114 | 5700 | 4900 | 800 | 334 | 325 | 260 | 200
05/31/2021 | 14:45 | 14:50 | 0.083333 | 16997 | 17005 | 8 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 96 | 5700 | 4900 | 800 | 329 | 325 | 260 | 200
05/31/2021 | 14:50 | 16:00 | 1.1667 | 17005 | 17025 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 17.14 | 5300 | 4900 | 400 | 329 | 325 | 260 | 200
05/31/2021 | 16:00 | 16:40 | 0.66667 | 17025 | 17092 | 67 | Rotate |  | 17025 | 88.69 | 132.78 | 12527.4 | -1619.08 | 4597.7 | -1619.08 | 1.9 |  |  | 30 | 80 | 375 | 22000 | 100.5 | 5700 | 4900 | 800 | 330 | 325 | 260 | 200
05/31/2021 | 16:45 | 16:50 | 0.083333 | 17092 | 17102 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 5700 | 4900 | 800 | 331 | 325 | 260 | 200
05/31/2021 | 16:50 | 17:40 | 0.83333 | 17102 | 17112 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 12 | 5100 | 4900 | 200 | 331 | 325 | 260 | 200
05/31/2021 | 17:40 | 18:15 | 0.58333 | 17112 | 17186 | 74 | Rotate |  | 17119 | 89.65 | 133.47 | 12528.76 | -1683.33 | 4666.3 | -1683.33 | 1.26 |  |  | 30 | 80 | 375 | 22000 | 126.86 | 5700 | 4900 | 800 | 334 | 350 | 260 | 180
05/31/2021 | 18:20 | 18:25 | 0.083333 | 17186 | 17196 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 5700 | 4900 | 800 | 334 | 350 | 260 | 180
05/31/2021 | 18:25 | 19:30 | 1.0833 | 17196 | 17211 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 13.85 | 5100 | 4900 | 200 | 334 | 350 | 260 | 180
05/31/2021 | 19:30 | 20:10 | 0.66667 | 17211 | 17280 | 69 | Rotate |  | 17213 | 90.9 | 134.33 | 12528.31 | -1748.51 | 4734.03 | -1748.51 | 1.61 |  |  | 27 | 70 | 375 | 22000 | 103.5 | 5600 | 4900 | 700 | 338 | 350 | 260 | 180
05/31/2021 | 20:15 | 21:00 | 0.75 | 17280 | 17375 | 95 | Rotate |  | 17308 | 90.79 | 135.3 | 12526.91 | -1815.46 | 4801.41 | -1815.46 | 1.03 |  |  | 30 | 70 | 375 | 22000 | 126.67 | 5700 | 4900 | 800 | 338 | 350 | 260 | 180
05/31/2021 | 21:05 | 21:10 | 0.083333 | 17375 | 17385 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 120 | 5700 | 4900 | 800 | 334 | 350 | 260 | 180
05/31/2021 | 21:10 | 22:40 | 1.5 | 17385 | 17397 | 12 | Slide | TTF: -45; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 8 | 5100 | 4900 | 200 | 334 | 350 | 260 | 180
05/31/2021 | 22:40 | 23:30 | 0.83333 | 17397 | 17470 | 73 | Rotate |  | 17403 | 92.79 | 134.26 | 12523.94 | -1882.34 | 4868.81 | -1882.34 | 2.37 |  |  | 25 | 70 | 375 | 22000 | 87.6 | 5500 | 4900 | 600 | 335 | 350 | 260 | 180
05/31/2021 | 23:35 | 24:00 | 0.41667 | 17470 | 17510 | 40 | Rotate |  | 17499 | 94.61 | 133.69 | 12517.75 | -1948.86 | 4937.74 | -1948.86 | 1.99 |  |  | 25 | 70 | 375 | 22000 | 96 | 5500 | 4900 | 600 | 335 | 350 | 260 | 180
06/01/2021 | 00:00 | 00:05 | 0.083333 | 17510 | 17514 | 4 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 48 | 5500 | 4900 | 600 | 335 | 350 | 260 | 180
06/01/2021 | 00:10 | 01:45 | 1.5833 | 17514 | 17529 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 9.47 | 5100 | 4900 | 200 | 330 | 350 | 260 | 180
06/01/2021 | 01:45 | 02:15 | 0.5 | 17529 | 17566 | 37 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 74 | 5500 | 4900 | 600 | 334 | 350 | 260 | 180
06/01/2021 | 02:20 | 02:40 | 0.33333 | 17566 | 17597 | 31 | Rotate |  | 17593 | 92.17 | 133.53 | 12512.19 | -2013.57 | 5005.68 | -2013.57 | 2.6 |  |  | 30 | 70 | 375 | 22000 | 93 | 5500 | 4900 | 600 | 334 | 350 | 260 | 180
06/01/2021 | 02:45 | 03:20 | 0.58333 | 17597 | 17660 | 63 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 108 | 5500 | 4900 | 600 | 333 | 350 | 260 | 180
06/01/2021 | 03:25 | 03:30 | 0.083333 | 17660 | 17667 | 7 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 84 | 5500 | 4900 | 600 | 334 | 350 | 260 | 180
06/01/2021 | 03:50 | 05:50 | 2 | 17667 | 17685 | 18 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 9 | 5100 | 4900 | 200 | 331 | 350 | 260 | 180
06/01/2021 | 05:50 | 06:50 | 1 | 17685 | 17755 | 70 | Rotate |  | 17688 | 88.68 | 132.84 | 12511.48 | -2078.58 | 5074.94 | -2078.58 | 3.74 |  |  | 35 | 70 | 375 | 22000 | 70 | 5500 | 4900 | 600 | 338 | 350 | 260 | 180
06/01/2021 | 07:25 | 08:30 | 1.0833 | 17755 | 17831 | 76 | Rotate |  | 17782 | 86.34 | 133.15 | 12515.57 | -2142.61 | 5143.62 | -2142.61 | 2.51 |  |  | 35 | 70 | 375 | 22000 | 70.15 | 5700 | 5100 | 600 | 342 | 350 | 260 | 180
06/01/2021 | 09:30 | 09:50 | 0.33333 | 17831 | 17838 | 7 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 21 | 5700 | 5100 | 600 | 338 | 350 | 260 | 180
06/01/2021 | 10:30 | 10:50 | 0.33333 | 17838 | 17849 | 11 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 33 | 5700 | 5100 | 600 | 338 | 350 | 260 | 180
06/01/2021 | 10:55 | 11:10 | 0.25 | 17849 | 17862 | 13 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 52 | 5700 | 5100 | 600 | 340 | 350 | 260 | 180
06/01/2021 | 11:10 | 11:40 | 0.5 | 17862 | 17867 | 5 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 10 | 5100 | 4900 | 200 | 338 | 350 | 260 | 180
06/01/2021 | 12:15 | 13:45 | 1.5 | 17867 | 17930 | 63 | Rotate |  | 17877 | 85.72 | 133.38 | 12522.15 | -2207.57 | 5212.63 | -2207.57 | 0.7 |  |  | 35 | 70 | 375 | 22000 | 42 | 5700 | 5100 | 600 | 333 | 350 | 260 | 180
06/01/2021 | 14:00 | 14:45 | 0.75 | 17930 | 17942 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 16 | 5100 | 4900 | 200 | 333 | 350 | 260 | 180
06/01/2021 | 14:50 | 15:40 | 0.83333 | 17942 | 18021 | 79 | Rotate |  | 17973 | 87.19 | 134.18 | 12528.08 | -2273.86 | 5281.81 | -2273.86 | 1.74 |  |  | 35 | 70 | 375 | 22000 | 94.8 | 5700 | 5100 | 600 | 333 | 350 | 260 | 180
06/01/2021 | 15:50 | 16:35 | 0.75 | 18021 | 18031 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 13.33 | 5100 | 4900 | 200 | 333 | 350 | 260 | 180
06/01/2021 | 16:35 | 16:45 | 0.16667 | 18031 | 18040 | 9 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 22000; Drilling Parameters ROP: 54 | 5700 | 5100 | 600 | 334 | 350 | 260 | 180
06/01/2021 | 17:00 | 17:55 | 0.91667 | 18040 | 18116 | 76 | Rotate |  | 18067 | 90.64 | 133.11 | 12529.86 | -2338.71 | 5349.81 | -2338.71 | 3.84 |  |  | 30 | 70 | 375 | 23000 | 82.91 | 5700 | 5100 | 600 | 336 | 350 | 260 | 180
06/01/2021 | 18:10 | 18:35 | 0.41667 | 18116 | 18122 | 6 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 14.4 | 5300 | 5100 | 200 | 336 | 350 | 260 | 180
06/01/2021 | 18:45 | 19:30 | 0.75 | 18122 | 18131 | 9 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 12 | 5300 | 5100 | 200 | 336 | 350 | 260 | 180
06/01/2021 | 19:30 | 19:35 | 0.083333 | 18131 | 18134 | 3 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 23000; Drilling Parameters ROP: 36 | 5700 | 5100 | 600 | 340 | 350 | 260 | 180
06/01/2021 | 19:50 | 21:10 | 1.3333 | 18134 | 18230 | 96 | Rotate |  | 18163 | 89.03 | 133.27 | 12530.14 | -2404.42 | 5419.8 | -2404.42 | 1.69 |  |  | 25 | 70 | 375 | 24000 | 72 | 5700 | 5100 | 600 | 345 | 350 | 260 | 180
06/01/2021 | 21:15 | 21:20 | 0.083333 | 18230 | 18240 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 375; Drilling Parameters Tq: 25000; Drilling Parameters ROP: 120 | 6100 | 5500 | 600 | 345 | 350 | 260 | 180
06/01/2021 | 21:30 | 22:05 | 0.58333 | 18240 | 18248 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 13.71 | 5700 | 5500 | 200 | 341 | 350 | 260 | 180
06/01/2021 | 22:05 | 23:10 | 1.0833 | 18248 | 18324 | 76 | Rotate |  | 18257 | 87.36 | 133.94 | 12533.1 | -2469.21 | 5487.83 | -2469.21 | 1.91 |  |  | 25 | 70 | 375 | 25000 | 70.15 | 6100 | 5500 | 600 | 344 | 350 | 260 | 180
06/01/2021 | 23:50 | 24:00 | 0.16667 | 18324 | 18333 | 9 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 325; Drilling Parameters Tq: 25000; Drilling Parameters ROP: 54 | 5200 | 4600 | 600 | 347 | 350 | 260 | 180
06/02/2021 | 00:00 | 00:10 | 0.16667 | 18333 | 18341 | 8 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 325; Drilling Parameters Tq: 25000; Drilling Parameters ROP: 48 | 5200 | 4600 | 600 | 347 | 350 | 260 | 180
06/02/2021 | 00:15 | 00:55 | 0.66667 | 18341 | 18348 | 7 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 10.5 | 5700 | 5500 | 200 | 342 | 350 | 260 | 180
06/02/2021 | 00:55 | 02:00 | 1.0833 | 18348 | 18387 | 39 | Rotate |  | 18352 | 86.04 | 133.98 | 12538.57 | -2535.04 | 5556.09 | -2535.04 | 1.39 |  |  | 25 | 70 | 325 | 25000 | 36 | 5200 | 4600 | 600 | 344 | 350 | 260 | 180
06/02/2021 | 03:00 | 03:30 | 0.5 | 18387 | 18419 | 32 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 325; Drilling Parameters Tq: 25000; Drilling Parameters ROP: 64 | 5300 | 4700 | 600 | 342 | 350 | 260 | 180
06/02/2021 | 03:35 | 04:05 | 0.5 | 18419 | 18442 | 23 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 325; Drilling Parameters Tq: 25000; Drilling Parameters ROP: 46 | 5300 | 4700 | 600 | 342 | 350 | 260 | 180
06/02/2021 | 04:15 | 05:05 | 0.83333 | 18442 | 18451 | 9 | Slide | -20 | 18446 | 87.49 | 133.59 | 12543.87 | -2599.98 | 5623.85 | -2599.98 | 1.6 |  |  | 25 |  | 375 |  | 10.8 | 5800 | 5500 | 300 | 338 | 350 | 260 | 180
06/02/2021 | 05:05 | 07:30 | 2.4167 | 18451 | 18513 | 62 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters FLOW: 375; Drilling Parameters ROP: 25.66 | 5800 | 5500 | 300 | 338 | 350 | 260 | 180
06/02/2021 | 07:35 | 09:30 | 1.9167 | 18513 | 18577 | 64 | Rotate |  | 18527 | 89.37 | 132.76 | 12546.09 | -2655.38 | 5682.89 | -2655.38 | 2.54 |  |  | 25 |  | 375 |  | 21.91 | 5800 | 5500 | 300 | 338 | 350 | 260 | 180

## BHA_8_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 8 |  |  |  |  | RKB: |  |  |  | 271 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2082
Site: |  |  |  |  | Rainier - Fayette County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 130
Well Name: |  |  |  |  | Rainier 1H ST01 |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 271 |  | VS Azimuth: |  | 133.1 |  | Rotate: |  | 1952
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
06/07/2021 | 07:20 | 07:40 | 0.33333 | 18577 | 18582 | 5 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 15 | 6600 | 5800 | 800 | 325 | 330 | 230 | 150
06/07/2021 | 07:40 | 08:05 | 0.41667 | 18582 | 18596 | 14 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 33.6 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 08:20 | 08:50 | 0.5 | 18596 | 18689 | 93 | Rotate |  | 18621 | 89.8 | 133.12 | 12546.77 | -2719.42 | 5751.71 | -2719.42 | 0.6 |  |  | 25 | 80 | 350 | 20000 | 186 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 09:10 | 09:15 | 0.083333 | 18689 | 18694 | 5 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 60 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 09:15 | 10:20 | 1.0833 | 18694 | 18707 | 13 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 12 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 10:45 | 11:05 | 0.33333 | 18707 | 18761 | 54 | Rotate |  | 18715 | 90.38 | 132.96 | 12546.62 | -2783.57 | 5820.41 | -2783.57 | 0.64 |  |  | 25 | 80 | 350 | 20000 | 162 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 11:05 | 11:45 | 0.66667 | 18761 | 18770 | 9 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 13.5 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 11:45 | 12:00 | 0.25 | 18770 | 18783 | 13 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 52 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 12:15 | 12:20 | 0.083333 | 18783 | 18788 | 5 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 60 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 12:20 | 13:00 | 0.66667 | 18788 | 18808 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 30 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 13:00 | 13:40 | 0.66667 | 18808 | 18878 | 70 | Rotate |  | 18810 | 86.1 | 131.55 | 12549.54 | -2847.41 | 5890.67 | -2847.41 | 4.74 |  |  | 25 | 80 | 350 | 20000 | 105 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 14:15 | 14:50 | 0.58333 | 18878 | 18941 | 63 | Rotate |  | 18905 | 87.21 | 131.75 | 12555.08 | -2910.43 | 5961.53 | -2910.43 | 1.19 |  |  | 25 | 80 | 350 | 20000 | 108 | 6600 | 5800 | 800 | 329 | 330 | 230
06/07/2021 | 14:50 | 15:50 | 1 | 18941 | 18961 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 20 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 15:50 | 16:05 | 0.25 | 18961 | 18973 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 48 | 6600 | 5800 | 800 | 325 | 330 | 230
06/07/2021 | 17:40 | 18:05 | 0.41667 | 18973 | 19066 | 93 | Rotate |  | 18998 | 83.66 | 130.46 | 12562.48 | -2971.37 | 6031.37 | -2971.37 | 4.06 |  |  | 25 | 80 | 350 | 20000 | 223.2 | 6600 | 5800 | 800 | 331 | 330 | 230
06/07/2021 | 18:15 | 18:40 | 0.41667 | 19066 | 19131 | 65 | Rotate |  | 19092 | 83.5 | 130.59 | 12573 | -3032.07 | 6102.38 | -3032.07 | 0.22 |  |  | 25 | 80 | 350 | 20000 | 156 | 6600 | 5800 | 800 | 336 | 330 | 230
06/07/2021 | 18:45 | 19:35 | 0.83333 | 19131 | 19143 | 12 | Slide | TTF: 20; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 14.4 | 6100 | 5800 | 300 | 332 | 330 | 230
06/07/2021 | 19:35 | 19:45 | 0.16667 | 19143 | 19160 | 17 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 102 | 6600 | 5500 | 1100 | 331 | 330 | 230
06/07/2021 | 19:50 | 20:20 | 0.5 | 19160 | 19255 | 95 | Rotate |  | 19187 | 86.49 | 132.3 | 12581.28 | -3094.7 | 6173.3 | -3094.7 | 3.62 |  |  | 26 | 80 | 350 | 20000 | 190 | 6600 | 5500 | 1100 | 334 | 330 | 230
06/07/2021 | 20:25 | 20:50 | 0.41667 | 19255 | 19351 | 96 | Rotate |  | 19283 | 87.3 | 132.87 | 12586.48 | -3159.57 | 6243.88 | -3159.57 | 1.03 |  |  | 26 | 80 | 350 | 20000 | 230.4 | 6600 | 5500 | 1100 | 334 | 330 | 230
06/08/2021 | 00:40 | 00:45 | 0.083333 | 19351 | 19361 | 10 | Rotate | Drilling Parameters WOB: 26; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 6600 | 5500 | 1100 | 324 | 330 | 230
06/08/2021 | 00:45 | 01:25 | 0.66667 | 19361 | 19376 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 22.5 | 5800 | 5500 | 300 | 324 | 330 | 230
06/08/2021 | 01:25 | 01:45 | 0.33333 | 19376 | 19445 | 69 | Rotate |  | 19377 | 85.53 | 133.9 | 12592.36 | -3224 | 6312.06 | -3224 | 2.18 |  |  | 26 | 80 | 350 | 20000 | 207 | 6400 | 5500 | 900 | 330 | 330 | 230
06/08/2021 | 01:50 | 02:25 | 0.58333 | 19445 | 19538 | 93 | Rotate |  | 19470 | 85.11 | 134.22 | 12599.95 | -3288.46 | 6378.67 | -3288.46 | 0.57 |  |  | 24 | 80 | 350 | 21000 | 159.43 | 6400 | 5500 | 900 | 332 | 330 | 230
06/08/2021 | 02:30 | 03:10 | 0.66667 | 19538 | 19633 | 95 | Rotate |  | 19565 | 83.74 | 133.83 | 12609.18 | -3354.17 | 6446.65 | -3354.17 | 1.5 |  |  | 24 | 80 | 350 | 21000 | 142.5 | 6400 | 5500 | 900 | 334 | 330 | 230
06/08/2021 | 03:15 | 03:50 | 0.58333 | 19633 | 19726 | 93 | Rotate |  | 19658 | 83.2 | 133.37 | 12619.75 | -3417.89 | 6513.56 | -3417.89 | 0.76 |  |  | 24 | 80 | 350 | 21000 | 159.43 | 6400 | 5500 | 900 | 336 | 330 | 230
06/08/2021 | 03:55 | 04:35 | 0.66667 | 19726 | 19821 | 95 | Rotate |  | 19753 | 82.85 | 132.58 | 12631.29 | -3482.17 | 6582.55 | -3482.17 | 0.9 |  |  | 24 | 80 | 350 | 21000 | 142.5 | 6400 | 5500 | 900 | 336 | 330 | 230
06/08/2021 | 04:40 | 04:45 | 0.083333 | 19821 | 19831 | 10 | Rotate | Drilling Parameters WOB: 24; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 120 | 6400 | 5500 | 900 | 330 | 330 | 230
06/08/2021 | 04:45 | 05:35 | 0.83333 | 19831 | 19846 | 15 | Slide | TTF: 20; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 18 | 5900 | 5500 | 400 | 330 | 330 | 230
06/08/2021 | 05:35 | 06:05 | 0.5 | 19846 | 19916 | 70 | Rotate |  | 19848 | 84.72 | 134.06 | 12641.58 | -3546.96 | 6651.26 | -3546.96 | 2.5 |  |  | 22 |  | 350 | 21000 | 140 | 5900 | 5500 | 400 | 336 | 330 | 230
06/08/2021 | 06:10 | 07:00 | 0.83333 | 19916 | 20010 | 94 | Rotate |  | 19942 | 85.65 | 133.97 | 12649.47 | -3612.04 | 6718.62 | -3612.04 | 0.99 |  |  | 25 |  | 350 | 21000 | 112.8 | 5900 | 5500 | 400 | 336 | 330 | 230
06/08/2021 | 07:05 | 07:40 | 0.58333 | 20010 | 20104 | 94 | Rotate |  | 20036 | 85.82 | 133.78 | 12656.46 | -3677.01 | 6786.19 | -3677.01 | 0.27 |  |  | 25 |  | 350 | 21000 | 161.14 | 5900 | 5500 | 400 | 336 | 330 | 230
06/08/2021 | 07:50 | 08:35 | 0.75 | 20104 | 20197 | 93 | Rotate |  | 20129 | 85.09 | 133.06 | 12663.83 | -3740.73 | 6853.53 | -3740.73 | 1.1 |  |  | 25 |  | 350 | 21000 | 124 | 5900 | 5500 | 400 | 336 | 330 | 230
06/08/2021 | 08:45 | 09:20 | 0.58333 | 20197 | 20292 | 95 | Rotate |  | 20224 | 84.57 | 132.87 | 12672.39 | -3805.22 | 6922.76 | -3805.22 | 0.58 |  |  | 25 |  | 350 | 21000 | 162.86 | 5900 | 5500 | 400 | 340 | 330 | 230
06/08/2021 | 09:30 | 09:35 | 0.083333 | 20292 | 20303 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 132 | 5900 | 5500 | 400 | 340 | 330 | 230
06/08/2021 | 09:35 | 10:15 | 0.66667 | 20303 | 20315 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 18 | 5900 | 5500 | 400 | 336 | 330 | 230
06/08/2021 | 10:15 | 10:45 | 0.5 | 20315 | 20386 | 71 | Rotate |  | 20318 | 86.03 | 134.6 | 12680.09 | -3869.98 | 6990.45 | -3869.98 | 2.4 |  |  | 25 |  | 350 | 21000 | 142 | 5900 | 5500 | 400 | 330 | 330 | 230
06/08/2021 | 10:55 | 11:30 | 0.58333 | 20386 | 20480 | 94 | Rotate |  | 20412 | 86.29 | 133.16 | 12686.38 | -3934.99 | 7058.05 | -3934.99 | 1.55 |  |  | 25 |  | 350 | 21000 | 161.14 | 5900 | 5500 | 400 | 330 | 330 | 230
06/08/2021 | 11:35 | 12:10 | 0.58333 | 20480 | 20575 | 95 | Rotate |  | 20507 | 86.69 | 132.99 | 12692.2 | -3999.75 | 7127.31 | -3999.75 | 0.46 |  |  | 25 |  | 350 | 21000 | 162.86 | 5900 | 5500 | 400 | 330 | 330 | 230
06/08/2021 | 12:15 | 12:50 | 0.58333 | 20575 | 20659 | 84 | Rotate |  | 20591 | 86.67 | 131.26 | 12697.07 | -4055.99 | 7189.5 | -4055.99 | 2.06 |  |  | 25 |  | 350 | 21000 | 144 | 5900 | 5500 | 400 | 330 | 330 | 230