## Summary
Magnolia Oil & Gas / Redwood A1H / LTX1125521 / Patterson 248
Report Date: | 09/14/2021 | Current Depth: | 18028
Start Date: | 07/15/2021 | Casing Depth: | 11053
Daily Cost: | 9450 | Distance to TD:
Well Cost: | 120830 | Average ROP: | 0
Drilling Hours: | 63.57 | Svy MD: | 18112
24Hr Forcast: |  | Svy Inc: | 94.07
Current BHA: | BHA 3 | Svy Azi: | 340.67
Current BRT Hrs: | 98.25 | Svy TVD: | 10784.68
Bit Make / Model: | Security / 1187517 | Svy NS: | 4858.85
POOH in last 24Hrs: | Yes | Svy EW: | -3761.32
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Josh Ray | MWD Day: | Jason Smetters
Directional Driller Night: | Jesse Taylor | MWD Night: | Chris Inman
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 303.8
24Hr Summary: |  | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MTR500028 | 7/8 3.8 2.50 TS HS88 -.004 | PDCI | Bailout | Clean
PPM250004 | 6/7 8.8 2.12 TS HS88 -0.001 | PDCI | 225 - 250 | Clean
PPM250017 | 6/7 8.8 2.12 TS HS88 +.024 | PDCI | 280 - 320 | Clean
PPM250019 | 6/7 8.8 2.12 TS HS88 +.008 | PDCI | 225-250 | Dirty |  | 78.30 | 78.30
BPB5550-0003 | 5/6 9.5 1.83 TS EW | Bico | Even-Wall | Clean
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
775182 | UBHO Sub |  |  | Dirty |  | 58.43 | 58.43
775225 | UBHO Sub |  |  | Clean
775219 | UBHO Sub |  |  | Clean
500031 | UBHO Sub |  |  | Clean
500046 | UBHO Sub |  |  | Clean
500048 | UBHO | PDCI |  | Dirty |  | 78.30 | 78.30
500037 | UBHO | PDCI |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31161 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Redwood A1H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Total Drilled (Usft): |  | 18004 |  |  | Total Days: |  | 12
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 3514 | 3406 |  | 487.73 |  | 9.42 | 6.98 | 3.68 | 12.83
2 | 2 | 9.875 | 3514 | 11063 | 7549 |  | 154.11 |  | 14.7 | 48.98 | 9.45 | 73
3 | 3 | 6.75 | 11063 | 18028 | 7049 |  | 110.89 |  | 16.39 | 63.57 | 14.73 | 98.25
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 |  |  | 0-0-NO-A-X-I-NO-TD |  | 1.353 | 3406 | 6.9833 | 487.73
2 | Ulterra |  | SPL613 |  | 9.875 | New |  |  |  | 1.491 | 7549 | 48.9833 | 154.11
3 | Security |  | 1187517 |  | 6.75 | New |  | 1-2-CT-S-X-I-NO-TD |  | 1.491 | 7049 | 63.5667 | 110.89
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.8 | 3406 |  | 487.73
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 5.9 | 7549 |  | 154.11
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.03 | 7049 |  | 110.89
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
J. Taylor J. Ray |  | Jesse Taylor |  | Danny Veronie |  | Chris Inman |  | Brandon Parks |  | James Dyer |  | Peter Langille
Jesse Taylor |  | Josh Ray |  | Jason Smetters |  | Jason Smitters |  | Kevin Burt |  | Kevin
Josh Ray |  | Xavier Cantu
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.40 |  | 3406 |  | 490.78 |  |  |  | 1 |  | 6.94
INT: INTERMEDIATE |  |  | 2.84 / 1.55 |  | 6727 |  | 222.09 |  |  |  | 1 |  | 30.29
CRV: CURVE |  |  | 2.17 / 0.80 |  | 822 |  | 44.03 |  |  |  | 1 |  | 18.67
CRV2: CURVE 2 |  |  | 1.11 / 0.47 |  | 657 |  | 80.51 |  |  |  | 1 |  | 8.16
LAT: LATERAL |  |  | 3.88 / 2.68 |  | 6392 |  | 115.36 |  |  |  | 1 |  | 55.41
Total |  |  | 12 |  | 18004 |  | 150.7 |  |  |  | 3 |  | 119.47
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 3514.00 | 615.77 | 3085.00 | 166.32 | 321.00 | 9.42 | 3406.00 | 490.78 | 6.94 | 1.93
INT: INTERMEDIATE-BHA 2 |  |  | 3514.00 | 10241.00 | 392.88 | 6231.00 | 34.37 | 496.00 | 7.37 | 6727.00 | 222.09 | 30.29 | 14.43
CRV: CURVE-BHA 2 |  |  | 10241.00 | 11063.00 | 77.32 | 208.00 | 38.42 | 614.00 | 74.70 | 822.00 | 44.03 | 18.67 | 15.98
CRV2: CURVE 2-BHA 3 |  |  | 11063.00 | 11720.00 | 80.84 | 135.00 | 80.43 | 522.00 | 79.45 | 657.00 | 80.51 | 8.16 | 6.49
LAT: LATERAL-BHA 3 |  |  | 11720.00 | 18112.00 | 143.94 | 5759.00 | 41.10 | 633.00 | 9.90 | 6392.00 | 115.36 | 55.41 | 15.40
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1125521 | Total Drilled(Usft) | 18004.00
Operator | Magnolia Oil & Gas | Drilling Hours | 119.53
Well Name | Redwood A1H | Avg ROP(Usft/hr) | 150.62
Rig | Patterson 248 | Rotary Drilled(Usft) | 15418.00
State | Texas | Rotary Hours | 65.28
County | Washington | Rotary ROP(Usft/hr) | 236.17
Formation | Austin Chalk | Rotary % | 85.64
Start Date | 07/15/2021 | Slide Drilled(Usft) | 2586.00
End Date | 09/14/2021 | Slide Hours | 54.25
Days On Well | 12 | Slide ROP(Usft/hr) | 47.67
Start Depth (Usft) | 108.00 | Slide % | 14.36
End Depth (Usft) | 18112.00
Total Drilled (Usft) | 18004.00
# BHA's | 3
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 1.70 / 0.00
Phase Data
Phase | SUR | INT | CRV | CRV2 | LAT
Start Date | 07/15/2021 | 07/28/2021 | 07/30/2021 | 09/10/2021 | 09/11/2021
End Date | 07/16/2021 | 07/30/2021 | 08/01/2021 | 09/11/2021 | 09/14/2021
Total Days | 2.00 | 2.83 | 2.17 | 1.11 | 3.89
Start Depth (Usft) | 108.00 | 3514.00 | 10241.00 | 11063.00 | 11720.00
End Depth (Usft) | 3514.00 | 10241.00 | 11063.00 | 11720.00 | 18028.00
Total Drilled(Usft) | 3406.00 | 6727.00 | 822.00 | 657.00 | 6392.00
Drilling Hours | 6.98 | 30.32 | 18.67 | 8.17 | 55.40
Circulating Hours | 3.68 | 7.43 | 2.02 | 4.58 | 10.15
Total D&C Hours | 10.67 | 37.75 | 20.68 | 12.75 | 65.55
Avg ROP(Usft/hr) | 487.73 | 221.89 | 44.04 | 80.45 | 115.38
Rotary Drilled(Usft) | 3085.00 | 6231.00 | 208.00 | 135.00 | 5759.00
Rotary Hours | 5.03 | 15.90 | 2.68 | 1.67 | 40.00
Rotary ROP(Usft/hr) | 612.91 | 391.89 | 77.52 | 81.00 | 143.97
Rotary % | 90.58 | 92.63 | 25.30 | 20.55 | 90.10
Slide Drilled(Usft) | 321.00 | 496.00 | 614.00 | 522.00 | 633.00
Slide Hours | 1.95 | 14.42 | 15.98 | 6.50 | 15.40
Slide ROP(Usft/hr) | 164.62 | 34.40 | 38.42 | 80.31 | 41.10
Slide % | 9.42 | 7.37 | 74.70 | 79.45 | 9.90
# BHA | 1 | 1 | 1 | 1 | 1
# Motor Failures | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 0.00 / 0.00 | 0.00 / 0.00 | 0.00 / 0.00 | 1.70 / 0.00
Total Phase Hrs | 9.58 | 37.17 | 19.23 | 11.25 | 64.25
Phase ROP (Usft/hr) | 355.41 | 181.00 | 42.74 | 58.40 | 99.49
Avg Motor Yield (°/100ft) | 4.00 | 5.83 | 6.65 | 12.67 | 14.40
Avg Rotary DLS (°/100ft) | 0.25 | 0.78 | 0.00 | 0.00 | 2.39
Avg Rotary TF | 171.38 | -167.34 | 0.00 | 0.00 | 6.83
Avg Slide Length (Usft) | 18.88 | 15.03 | 68.22 | 52.20 | 17.11
# Slides | 17 | 33 | 9 | 10 | 37
BHA Data
BHA# | 1 | 2 | 3
Description | BHA 1 | BHA 2 | BHA 3
Bit Size | 13.500 | 9.875 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Security / 1187517
Bit TFA | 1.353 | 1.491 | 1.491
Grade In |  | New | New
Grade Out | 0-0-NO-A-X-I-NO-TD |  | 1-2-CT-S-X-I-NO-TD
Motor SN | PPM800067 | PPM800001 | PPM250019
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 8.8
WOB (klbs) | 3.00 / 17.51 / 35.00 | 15.00 / 30.47 / 40.00 | 7.83 / 26.18 / 40.00
Diff P (psi) | 100.00 / 355.09 / 600.00 | 200.00 / 727.91 / 800.00 | 51.87 / 605.73 / 1484.01
Bend | 1.500 | 2.000 | 2.120
Date In | 07/15/2021 | 07/28/2021 | 09/10/2021
Date Out | 07/16/2021 | 08/01/2021 | 09/14/2021
Time In | 15:40 | 24:00 | 06:15
Time Out | 04:30 | 01:00 | 08:30
BRT Hrs | 12.83 | 73.00 | 98.25
Start Depth (Usft) | 108.00 | 3514.00 | 11063.00
End Depth (Usft) | 3514.00 | 11063.00 | 18028.00
Total Drilled(Usft) | 3406.00 | 7549.00 | 7049.00
Drilling Hours | 6.98 | 48.98 | 63.57
Circulating Hours | 3.68 | 9.45 | 14.73
Total D&C Hours | 10.67 | 58.43 | 78.30
Avg ROP(Usft/hr) | 487.73 | 154.11 | 110.89
Rotary Drilled(Usft) | 3085.00 | 6439.00 | 5894.00
Rotary Hours | 5.03 | 18.58 | 41.67
Rotary ROP(Usft/hr) | 612.91 | 346.49 | 141.46
Rotary % | 90.58 | 85.30 | 83.61
Slide Drilled(Usft) | 321.00 | 1110.00 | 1155.00
Slide Hours | 1.95 | 30.40 | 21.90
Slide ROP(Usft/hr) | 164.62 | 36.51 | 52.74
Slide % | 9.42 | 14.70 | 16.39
Motor Failure | NO | NO | NO
MWD Failure | NO | NO | NO
Unplanned Trip | NO | NO | NO
LIH | NO | NO | NO
Avg Motor Yield (°/100ft) | 4.00 | 6.01 | 14.07
Avg Rotary DLS (°/100ft) | 0.25 | 0.78 | 2.16
Avg Rotary TF | 171.38 | -167.34 | 4.93
Avg Slide Length (Usft) | 18.88 | 26.43 | 24.57
# Slides | 17 | 42 | 47

## Personnel Report
|  | Job # | LTX1125521 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31161 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Redwood A1H
|  | Date: | 09/14/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Redwood A1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Chris Inman | Night MWD |  | 07/31/2021 - 00:00 | 08/01/2021 - 00:00 |  | 2.00 / 0.00
Chris Inman | Night MWD |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
Danny Veronie | Day MWD |  | 07/15/2021 - 00:00 | 07/16/2021 - 00:00 |  | 2.00 / 0.00
Danny Veronie | Day MWD |  | 07/28/2021 - 00:00 | 07/30/2021 - 00:00 |  | 3.00 / 0.00
J. Taylor J. Ray | Day DD |  | 07/31/2021 - 00:00 | 07/31/2021 - 00:00 |  | 1.00 / 0.00
Jason Smetters | Day MWD |  | 07/31/2021 - 00:00 | 08/01/2021 - 00:00 |  | 2.00 / 0.00
Jason Smetters | Day MWD |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
Jason Smitters | Night MWD |  | 07/15/2021 - 00:00 | 07/16/2021 - 00:00 |  | 2.00 / 0.00
Jason Smitters | Night MWD |  | 07/28/2021 - 00:00 | 07/30/2021 - 00:00 |  | 3.00 / 0.00
Jesse Taylor | Day DD |  | 07/15/2021 - 00:00 | 07/16/2021 - 00:00 |  | 2.00 / 0.00
Jesse Taylor | Day DD |  | 07/28/2021 - 00:00 | 07/30/2021 - 00:00 |  | 3.00 / 0.00
Jesse Taylor | Night DD |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
Josh Ray | Day DD |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
Josh Ray | Day DD |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
Josh Ray | Night DD |  | 07/15/2021 - 00:00 | 07/16/2021 - 00:00 |  | 2.00 / 0.00
Josh Ray | Night DD |  | 07/28/2021 - 00:00 | 07/30/2021 - 00:00 |  | 3.00 / 0.00
NA | Trainee 1 |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
NA | Trainee 1 |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
NA | Trainee 2 |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
NA | Trainee 2 |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
NA | Rss Eng. 1 |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
NA | Rss Eng. 1 |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
NA | Rss Eng. 2 |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
NA | Rss Eng. 2 |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
NA | Third Man |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
NA | Third Man |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
NA | Fourth Man |  | 08/01/2021 - 00:00 | 08/01/2021 - 00:00 |  | 1.00 / 0.00
NA | Fourth Man |  | 09/10/2021 - 00:00 | 09/14/2021 - 00:00 |  | 5.00 / 0.00
Xavier Cantu | Night DD |  | 07/31/2021 - 00:00 | 08/01/2021 - 00:00 |  | 2.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1125521 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Redwood A1H | [7 empty] | Day DD: |  |  |  |  | Josh Ray | [5 empty] | API #: |  |  |  | 42-477-31161
|  |  |  | AFE #: |  |  | 20dd0221mg | [7 empty] | Night DD: |  |  |  |  | Jesse Taylor | [5 empty] | Company Man: |  |  |  | Kevin Burt
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Jason Smetters | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Chris Inman | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 07/15/2021 | 07/16/2021 | 07/17/2021 | 07/18/2021 | 07/19/2021 | 07/20/2021 | 07/21/2021 | 07/22/2021 | 07/23/2021 | 07/24/2021 | 07/25/2021 | 07/26/2021 | 07/27/2021 | 07/28/2021 | 07/29/2021 | 07/30/2021 | 07/31/2021 | 08/01/2021 | 08/02/2021 | 08/03/2021 | 08/04/2021 | 08/05/2021 | 08/06/2021 | 08/07/2021 | 08/08/2021 | 08/09/2021 | 08/10/2021 | 08/11/2021 | 08/12/2021 | 08/13/2021 | 08/14/2021 | 08/15/2021 | 08/16/2021 | 08/17/2021 | 08/18/2021 | 08/19/2021 | 08/20/2021 | 08/21/2021 | 08/22/2021 | 08/23/2021 | 08/24/2021 | 08/25/2021 | 08/26/2021 | 08/27/2021 | 08/28/2021 | 08/29/2021 | 08/30/2021 | 08/31/2021 | 09/01/2021 | 09/02/2021 | 09/03/2021 | 09/04/2021 | 09/05/2021 | 09/06/2021 | 09/07/2021 | 09/08/2021 | 09/09/2021 | 09/10/2021 | 09/11/2021 | 09/12/2021 | 09/13/2021 | 09/14/2021 | 09/15/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 9.875 | SPL613 |  | Steel | 56410 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Bit | Security | 6.75 | GTD64M |  | Steel | 13618580 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Cross Over |  | 6.75 | Crossover Sub |  | Steel | SD115348 | 0 | 1 | [17 empty] | O
Cross Over |  | 6.625 | Crossover Sub |  | Steel | SD4555 | 0 | 1 | [17 empty] | O
Cross Over |  | 6.75 | Crossover Sub |  | Steel | SD117248 | 2 | 6 | X | X | [10 empty] | O | O | O | O | O | O
Cross Over |  |  | Crossover Sub |  | Steel | SD117749 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Cross Over |  | 7.875 | Crossover Sub |  | Steel | SD118418 | 5 | 6 | [12 empty] | O | X | X | X | X | X
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD107702 | 5 | 6 | [12 empty] | O | X | X | X | X | X
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD110296 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Cross Over |  | 6.5 | Crossover Sub |  | Steel | SD110972 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Cross Over |  | 6.75 | Crossover Sub |  | Steel | SD118447 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Cross Over |  | 6.625 | Crossover Sub |  | Steel | SD105593 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Cross Over | Gator Tech | 5.188 | Crossover |  | Steel | GT52331432 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Cross Over | Gator Tech | 5.375 | Crossover |  | Steel | GT52331100 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Cross Over | Gator Tech | 5.25 | Crossover |  | Steel | GT52331431 | 5 | 6 | [56 empty] | O | X | X | X | X | X
MWD / LWD |  | 7.75 | UBHO Sub |  | Steel | 775182 | 5 | 6 | [12 empty] | O | X | X | X | X | X
MWD / LWD |  | 7.75 | UBHO Sub |  | Steel | 775225 | 0 | 6 | [12 empty] | O | O | O | O | O | O
MWD / LWD |  | 7.75 | UBHO Sub |  | Steel | 775219 | 0 | 1 | [17 empty] | O
MWD / LWD |  |  | UBHO Sub |  | Steel | 500031 | 0 | 6 | [12 empty] | O | O | O | O | O | O
MWD / LWD |  |  | UBHO Sub |  | Steel | 500046 | 0 | 6 | [12 empty] | O | O | O | O | O | O
MWD / LWD | PDCI | 5.25 | UBHO |  | Steel | 500048 | 5 | 6 | [56 empty] | O | X | X | X | X | X
MWD / LWD | PDCI | 5.25 | UBHO |  | Steel | 500037 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPW .006 |  | Steel | PPM800011 | 0 | 1 | [17 empty] | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPW .003 |  | Steel | PPM800034 | 0 | 1 | [17 empty] | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPO -.003 |  | Steel | PPM800077 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPO -.013 |  | Steel | PPM800001 | 5 | 6 | [12 empty] | O | X | X | X | X | X
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPO -.014 |  | Steel | PPM800058 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Motor | PDCI | 5 | 7/8 3.8 2.50 TS HS88 -.004 |  | Steel | MTR500028 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 -0.001 |  | Steel | PPM250004 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 +.024 |  | Steel | PPM250017 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 +.008 |  | Steel | PPM250019 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Motor | Bico | 5.25 | 5/6 9.5 1.83 TS EW |  | Steel | BPB5550-0003 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Collar |  | 8 | NMDC |  | Non-Mag | SD55920 | 2 | 6 | X | X | [10 empty] | O | O | O | O | O | O
Collar |  | 8 | NMDC |  | Non-Mag | SD50132 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Collar |  | 8 | NMDC |  | Non-Mag | SD56047 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Collar |  | 8 | NMDC |  | Non-Mag | SD56223 | 5 | 6 | [12 empty] | O | X | X | X | X | X
Collar |  | 8 | NMDC |  | Non-Mag | SD55704 | 5 | 6 | [12 empty] | O | X | X | X | X | X
Collar |  | 8 | NMDC |  | Non-Mag | SD46074 | 0 | 1 | [17 empty] | O
Collar |  | 7.812 | NMDC |  | Non-Mag | SD53215 | 0 | 1 | [17 empty] | O
Collar |  | 7.938 | NMPC |  | Steel | SD4326 | 0 | 1 | [17 empty] | O
Collar |  | 8 | NMPC |  | Steel | SD54514 | 5 | 6 | [12 empty] | O | X | X | X | X | X
Collar |  | 8 | NMPC |  | Steel | SD54585 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-586 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Collar | Gator Tech | 5.125 | NMDC (NO HARDBANDING) |  | Non-Mag | GT51-30-616 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Collar | Gator Tech | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-481 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-587 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-589 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMPC |  | Steel | GT50-10-652 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Collar | Gator Tech | 4.938 | NMPC |  | Steel | GT50-10-637 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMPC |  | Steel | GT50-10-479 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMPC |  | Steel | GT50-10-585 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Sub |  |  | Float Sub |  | Steel | SD105081 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Sub |  |  | Float Sub |  | Steel | SD119499 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Sub |  | 6.625 | Lift Sub |  | Steel | SD100672 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Sub |  | 6.625 | Lift Sub |  | Steel | SD103938 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Sub |  |  | Lift Cap |  | Steel | LC3377 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Sub | Gator Tech | 5 | Filter Sub |  | Steel | GT50331343 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Sub | Gator Tech | 5 | Filter Sub |  | Steel | GT50331288 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Sub | Gator Tech | 5 | Float Sub |  | Steel | GT50331370FF | 0 | 6 | [56 empty] | O | O | O | O | O | O
Sub | Gator Tech | 5 | Float Sub |  | Steel | GT50331372FF | 0 | 6 | [56 empty] | O | O | O | O | O | O
Sub | Gator Tech | 5.5 | Lift Sub |  | Steel | GT551232 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Sub | Gator Tech | 5.5 | Lift Sub |  | Steel | GT551251 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Sub |  | 4.875 | BTI Valve |  | Steel | BTI1 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Sub |  | 5.25 | Tomax |  | Steel | A52123 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Agitator | DWS | 6.75 | Agitator |  | Steel | PG675-0027 | 0 | 6 | [12 empty] | O | O | O | O | O | O
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0055 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Agitator |  | 5.312 | Agitator (Ball Drop) |  | Steel | PG525-0049 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Agitator |  | 5.312 | Agitator (Ball Drop) |  | Steel | PG525-0033 | 0 | 6 | [56 empty] | O | O | O | O | O | O
Reamer | DTI | 5.375 | Drill-N-Ream |  | Steel | 532 | 5 | 6 | [56 empty] | O | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | J. Taylor J. Ray |  |  |  | 1 | [17 empty] | 1
Day DD |  |  | Jesse Taylor |  |  |  | 5 |  | 1 | 1 | [11 empty] | 1 | 1 | 1
Day DD |  |  | Josh Ray |  |  |  | 6 | [18 empty] | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Jesse Taylor |  |  |  | 5 | [58 empty] | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Josh Ray |  |  |  | 5 |  | 1 | 1 | [11 empty] | 1 | 1 | 1
Night DD |  |  | Xavier Cantu |  |  |  | 2 | [17 empty] | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 5 |  | 1 | 1 | [11 empty] | 1 | 1 | 1
Day MWD |  |  | Jason Smetters |  |  |  | 7 | [17 empty] | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Chris Inman |  |  |  | 7 | [17 empty] | 1 | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smitters |  |  |  | 5 |  | 1 | 1 | [11 empty] | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 6 | [18 empty] | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 6 | [18 empty] | 1 | [39 empty] | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31161 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Redwood A1H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20dd0221mg |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
SD55920 | NMDC | 8 | 28.99 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
SD50132 | NMDC | 8 | 28.66 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD56047 | NMDC | 8 | 29.12 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD56223 | NMDC | 8 | 29.84 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
SD55704 | NMDC | 8 | 29.58 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
SD46074 | NMDC | 8 | 28.75 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 08/01/2021 |  | 08/01/2021
SD53215 | NMDC | 7.812 | 27.55 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 08/01/2021 |  | 08/01/2021
SD4326 | NMPC | 7.938 | 9.5 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 08/01/2021 |  | 08/01/2021
SD54514 | NMPC | 8 | 9.01 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
SD54585 | NMPC | 8 | 9.21 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD115348 | Crossover Sub | 6.75 | 2.25 |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 08/01/2021 |  | 08/01/2021
SD4555 | Crossover Sub | 6.625 | 3 |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 08/01/2021 |  | 08/01/2021
SD117248 | Crossover Sub | 6.75 | 2.13 |  | 4 1/2 IF / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
SD117749 | Crossover Sub |  |  |  | 4 1/2 IF / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD118418 | Crossover Sub | 7.875 | 3.06 |  | 4 1/2 XH / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
SD107702 | Crossover Sub | 6.5 | 2.67 |  | 4 1/2 IF / 4 1/2 XH | Dirty |  | 07/27/2021 |  | 08/01/2021
SD110296 | Crossover Sub | 6.5 | 2.4 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 07/27/2021 |  | 08/01/2021
SD110972 | Crossover Sub | 6.5 | 2.71 |  | 4 1/2 XH / 4 1/2 IF | Clean |  | 07/27/2021 |  | 08/01/2021
SD118447 | Crossover Sub | 6.75 | 2.55 |  | 4 1/2 XH / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD105593 | Crossover Sub | 6.625 | 2.56 |  | 4 1/2 IF / 4 1/2 XH | Clean |  | 07/27/2021 |  | 08/01/2021
SD105081 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD119499 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD100672 | Lift Sub | 6.625 | 3.04 |  | 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
SD103938 | Lift Sub | 6.625 | 2.71 |  | 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
LC3377 | Lift Cap |  |  |  | 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
775182 | UBHO Sub | 7.75 | 3.73 |  | 6 5/8 REG / 6 5/8 REG | Dirty |  | 07/27/2021 |  | 08/01/2021
775225 | UBHO Sub | 7.75 | 3.97 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
775219 | UBHO Sub | 7.75 | 3.78 |  | 6 5/8 REG / 6 5/8 REG | Clean |  | 08/01/2021 |  | 08/01/2021
500031 | UBHO Sub |  |  |  | XT39 / XT39 | Clean |  | 07/27/2021 |  | 08/01/2021
500046 | UBHO Sub |  |  |  | XT39 / XT39 | Clean |  | 07/27/2021 |  | 08/01/2021
PPM800011 | 7/8 5.9 2.00 Slick HPW .006 | 8 | 37.3 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 08/01/2021 |  | 08/01/2021
PPM800034 | 7/8 5.9 2.00 Slick HPW .003 | 8 | 37.72 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 08/01/2021 |  | 08/01/2021
PPM800077 | 7/8 5.9 2.00 Slick HPO -.003 | 8 | 37.6 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 07/27/2021 |  | 08/01/2021
PPM800001 | 7/8 5.9 2.00 Slick HPO -.013 | 8 | 38.05 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / Pro Power | 07/27/2021 |  | 08/01/2021
PPM800058 | 7/8 5.9 2.00 Slick HPO -.014 | 8 | 37.56 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 07/27/2021 |  | 08/01/2021
PG675-0027 | Agitator | 6.75 | 24.65 |  | 4 1/2 IF / 4 1/2 IF | Clean | DWS / Power Glide | 07/27/2021 |  | 08/01/2021
56410 | SPL613 | 9.875 | 1.5 |  | 6 5/8 REG | Clean |  | 07/27/2021 |  | 08/01/2021
MTR500028 | 7/8 3.8 2.50 TS HS88 -.004 | 5 | 26.11 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 09/09/2021
PPM250004 | 6/7 8.8 2.12 TS HS88 -0.001 | 5.5 | 33.11 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 09/09/2021
PPM250017 | 6/7 8.8 2.12 TS HS88 +.024 | 5.5 | 33.08 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 09/09/2021
PPM250019 | 6/7 8.8 2.12 TS HS88 +.008 | 5.5 | 33.11 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 09/09/2021
BPB5550-0003 | 5/6 9.5 1.83 TS EW | 5.25 | 32 |  | XT39 / 3 1/2 Reg | Clean | Bico / SS170(EW) | 09/09/2021
GT50-30-586 | NMDC (NO HARDBANDING) | 5 | 30.72 |  | XT39 / XT39 | Dirty | Gator Tech | 09/09/2021
GT51-30-616 | NMDC (NO HARDBANDING) | 5.125 | 29.28 |  | XT39 / XT39 | Dirty | Gator Tech | 09/09/2021
GT50-30-481 | NMDC (NO HARDBANDING) | 5 | 29.93 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50-30-587 | NMDC (NO HARDBANDING) | 5 | 30.8 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50-30-589 | NMDC (NO HARDBANDING) | 5 | 30.81 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50-10-652 | NMPC | 5 | 9.6 |  | XT39 / XT39 | Dirty | Gator Tech | 09/09/2021
GT50-10-637 | NMPC | 4.938 | 9.17 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50-10-479 | NMPC | 5 | 9.87 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50-10-585 | NMPC | 5 | 9.45 |  | XT39 / XT39 | Dirty | Gator Tech | 09/09/2021
500048 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Dirty | PDCI | 09/09/2021
500037 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Clean | PDCI | 09/09/2021
GT52331432 | Crossover | 5.188 | 3.64 |  | CET43 / XT39 | Clean | Gator Tech | 09/09/2021
GT52331100 | Crossover | 5.375 | 2.6 |  | CET43 / XT39 | Clean | Gator Tech | 09/09/2021
GT52331431 | Crossover | 5.25 | 3.37 |  | CET43 / XT39 | Dirty | Gator Tech | 09/09/2021
GT50331343 | Filter Sub | 5 | 5.55 |  | XT39 / XT39 | Dirty | Gator Tech | 09/09/2021
GT50331288 | Filter Sub | 5 | 5.1 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50331370FF | Float Sub | 5 | 3.08 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT50331372FF | Float Sub | 5 | 3.1 |  | XT39 / XT39 | Clean | Gator Tech | 09/09/2021
GT551232 | Lift Sub | 5.5 | 3.3 |  | XT39 | Clean | Gator Tech | 09/09/2021
GT551251 | Lift Sub | 5.5 | 3.35 |  | XT39 | Clean | Gator Tech | 09/09/2021
GT180 | Lift Cap |  |  |  | XT39 | Clean | Gator Tech | 09/09/2021
532 | Drill-N-Ream | 5.375 | 8.45 |  | CET43 / CET43 | Dirty | DTI / DNR | 09/09/2021
BTI1 | BTI Valve | 4.875 | 1.65 |  | XT39 / XT39 | Dirty |  | 09/09/2021
13618580 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Dirty | Security / 1187517 | 09/09/2021
PG525-0055 | Agitator | 5.312 | 21.41 |  | CET43 / CET43 | Dirty | DWS / Power Glide | 09/09/2021
PG525-0049 | Agitator (Ball Drop) | 5.312 | 21.39 |  | CET43 / CET43 | Clean |  | 09/09/2021
A52123 | Tomax | 5.25 | 17.92 |  | XT39 / XT39 | Dirty |  | 09/09/2021
PG525-0033 | Agitator (Ball Drop) | 5.312 | 21.42 |  | CET43 / CET43 | Clean |  | 09/09/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31161 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Redwood A1H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 47424 | 07/15/2021 | 09/14/2021 | 62 | 1 | 1 |  | 3.68 | 6.98 | 12.83
13 Stab | SD603251 | 07/15/2021 | 09/14/2021 | 62 | 1 | 1 |  | 3.68 | 6.98 | 12.83
7/8 5.9 1.50 Stab HPO -.015 NBS 13 | PPM800067 | 07/15/2021 | 09/14/2021 | 62 | 1 | 1 |  | 3.68 | 6.98 | 12.83
NMPC | SD55524 | 07/15/2021 | 09/14/2021 | 62 | 1 | 1 |  | 3.68 | 6.98 | 12.83
UBHO Sub UBHO Sub | 775213 | 07/15/2021 | 09/14/2021 | 62 | 1 | 1 |  | 3.68 | 6.98 | 12.83
NMDC | SD56120 | 07/15/2021 | 09/14/2021 | 62 | 1 | 1 |  | 3.68 | 6.98 | 12.83
NMDC | SD55920 | 07/27/2021 | 08/01/2021 | 6 | 1 | 1 |  | 3.68 | 6.98 | 12.83
Crossover Sub | SD117248 | 07/27/2021 | 08/01/2021 | 6 | 1 | 1 |  | 3.68 | 6.98 | 12.83
SPL613 | 55308 | 07/15/2021 | 09/14/2021 | 62 | 3 | 2 |  | 9.45 | 48.98 | 73
7/8 5.9 2.00 Slick HPO -.013 | PPM800001 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
NMPC | SD54514 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
UBHO Sub | 775182 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
NMDC | SD56223 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
NMDC | SD55704 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
Crossover Sub | SD118418 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
Crossover Sub | SD107702 | 07/27/2021 | 08/01/2021 | 6 | 3 | 2 |  | 9.45 | 48.98 | 73
Agitator | PG675-0011 | 07/15/2021 | 09/14/2021 | 62 | 3 | 2 |  | 9.45 | 48.98 | 73
GTD64M | 13618580 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
6/7 8.8 2.12 TS HS88 +.008 | PPM250019 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
BTI Valve | BTI1 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
NMPC | GT50-10-652 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
UBHO | 500048 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
NMDC (NO HARDBANDING) | GT51-30-616 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
NMPC | GT50-10-585 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
NMDC (NO HARDBANDING) | GT50-30-586 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
Tomax | A52123 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
Filter Sub | GT50331343 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
Crossover | GT52331431 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
Drill-N-Ream | 532 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
Agitator | PG525-0055 | 09/09/2021 | 09/14/2021 | 6 | 4 | 3 |  | 14.73 | 63.57 | 98.25
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well-GL: 359 + KB: 28 (Pat248)
Facility |  |  | Rommel-Redwood - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Redwood A1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Redwood A1H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 387.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Rommel-Redwood - Washington County, TX
Map Northing |  |  | 224504.93 US survey foot |  |  | Map Easting |  |  | 3168972.23 US survey foot
Latitude |  |  | 30° 13' 49.70133" N |  |  | Longitude |  |  | 96° 37' 52.49452" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.907
Well: |  |  | Redwood A1H
Local North |  |  | 0.46 Usft |  |  | Local East |  |  | 6.34 Usft
Map Northing |  |  | 224504.94 US survey foot |  |  | Map Easting |  |  | 3168972.23 US survey foot
Latitude |  |  | 30° 13' 49.70376" N |  |  | Longitude |  |  | 96° 37' 52.42214" W
Depth Datum |  |  | Well-GL: 359 + KB: 28 (Pat248) |  |  | Datum Elevation |  |  | 387.00 Usft
GL Elevation |  |  | 359.00 Usft
Grid Convergence |  |  | 1.907
Well bore: |  |  | Redwood A1H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 04/07/2021
Total Field (nT) |  |  | 46654.9 |  |  | Dip Angle (°) |  |  | 58.867
Declination (°) |  |  | 2.983
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 321.52
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Redwood A1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3443 |  |  | Redwood A1H S1 |  |  | MWD+HDGM
3443 |  |  | 10999 |  |  | Redwood A1H S2 |  |  | MWD+HDGM
10999 |  |  | 18112 |  |  | Redwood A1H S3 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -387 | 224504.94 | 3168972.23 | 30.2305 | -96.6312 | 0
198 | 0.66 | 225.19 | 198 | -0.8 | -0.81 | -0.13 | 0.33 | 0.33 | 68.09 | 225.19 | 198 | -189 | 224504.14 | 3168971.42 | 30.2305 | -96.6313 | 225.19
290 | 0.67 | 227.06 | 289.99 | -1.54 | -1.58 | -0.23 | 0.03 | 0.01 | 2.03 | 66.2 | 92 | -97.01 | 224503.4 | 3168970.65 | 30.2305 | -96.6313 | 225.65
414 | 0.64 | 233.25 | 413.98 | -2.45 | -2.66 | -0.26 | 0.06 | -0.02 | 4.99 | 116.05 | 124 | 26.98 | 224502.49 | 3168969.57 | 30.2305 | -96.6313 | 227.38
508 | 0.45 | 227.27 | 507.98 | -3.02 | -3.36 | -0.27 | 0.21 | -0.2 | -6.36 | -166.31 | 94 | 120.98 | 224501.92 | 3168968.87 | 30.2305 | -96.6313 | 228.05
602 | 0.75 | 211.25 | 601.97 | -3.79 | -3.95 | -0.51 | 0.36 | 0.32 | -17.04 | -37.38 | 94 | 214.97 | 224501.15 | 3168968.28 | 30.2305 | -96.6313 | 226.14
696 | 1.09 | 196.84 | 695.96 | -5.17 | -4.52 | -1.24 | 0.43 | 0.36 | -15.33 | -41.58 | 94 | 308.96 | 224499.77 | 3168967.71 | 30.2305 | -96.6313 | 221.17
790 | 1.22 | 192.81 | 789.94 | -7.01 | -5.01 | -2.37 | 0.16 | 0.14 | -4.29 | -34.03 | 94 | 402.94 | 224497.93 | 3168967.22 | 30.2305 | -96.6313 | 215.54
884 | 1.01 | 198.94 | 883.92 | -8.77 | -5.5 | -3.44 | 0.26 | -0.22 | 6.52 | 153.44 | 94 | 496.92 | 224496.17 | 3168966.73 | 30.2304 | -96.6313 | 212.09
978 | 1.14 | 200.51 | 977.91 | -10.42 | -6.09 | -4.37 | 0.14 | 0.14 | 1.67 | 13.55 | 94 | 590.91 | 224494.52 | 3168966.14 | 30.2304 | -96.6313 | 210.3
1072 | 1 | 214.5 | 1071.89 | -11.98 | -6.89 | -5.09 | 0.31 | -0.15 | 14.88 | 125.06 | 94 | 684.89 | 224492.96 | 3168965.34 | 30.2304 | -96.6313 | 209.89
1166 | 0.92 | 206.13 | 1165.88 | -13.33 | -7.68 | -5.66 | 0.17 | -0.09 | -8.9 | -123.84 | 94 | 778.88 | 224491.61 | 3168964.55 | 30.2304 | -96.6313 | 209.95
1260 | 1.07 | 215.66 | 1259.86 | -14.72 | -8.53 | -6.22 | 0.24 | 0.16 | 10.14 | 52.64 | 94 | 872.86 | 224490.22 | 3168963.7 | 30.2304 | -96.6313 | 210.08
1354 | 1.17 | 218.45 | 1353.84 | -16.19 | -9.63 | -6.68 | 0.12 | 0.11 | 2.97 | 30.01 | 94 | 966.84 | 224488.75 | 3168962.6 | 30.2304 | -96.6313 | 210.76
1448 | 0.96 | 223.27 | 1447.83 | -17.51 | -10.77 | -7.01 | 0.24 | -0.22 | 5.13 | 159.29 | 94 | 1060.83 | 224487.43 | 3168961.46 | 30.2304 | -96.6313 | 211.6
1543 | 1.07 | 199.39 | 1542.81 | -18.93 | -11.61 | -7.59 | 0.46 | 0.12 | -25.14 | -87.56 | 95 | 1155.81 | 224486.01 | 3168960.62 | 30.2304 | -96.6313 | 211.53
1636 | 1.33 | 168.66 | 1635.79 | -20.8 | -11.69 | -9.01 | 0.73 | 0.28 | -33.04 | -83.84 | 93 | 1248.79 | 224484.14 | 3168960.54 | 30.2304 | -96.6313 | 209.33
1730 | 2.3 | 153.45 | 1729.75 | -23.56 | -10.63 | -11.83 | 1.14 | 1.03 | -16.18 | -34.15 | 94 | 1342.75 | 224481.38 | 3168961.6 | 30.2304 | -96.6313 | 204.28
1823 | 3.54 | 143.58 | 1822.62 | -27.54 | -8.09 | -16.53 | 1.43 | 1.33 | -10.61 | -27.05 | 93 | 1435.62 | 224477.4 | 3168964.14 | 30.2304 | -96.6313 | 196.37
1917 | 4.38 | 139.96 | 1916.4 | -32.62 | -4.06 | -23.01 | 0.93 | 0.89 | -3.85 | -18.38 | 94 | 1529.4 | 224472.32 | 3168968.17 | 30.2304 | -96.6313 | 187.09
2012 | 4.84 | 138.27 | 2011.09 | -38.39 | 0.94 | -30.64 | 0.5 | 0.48 | -1.78 | -17.29 | 95 | 1624.09 | 224466.55 | 3168973.17 | 30.2304 | -96.6312 | 178.59
2106 | 5.4 | 136.46 | 2104.72 | -44.56 | 6.63 | -39.01 | 0.62 | 0.6 | -1.93 | -16.99 | 94 | 1717.72 | 224460.38 | 3168978.86 | 30.2304 | -96.6312 | 171.54
2201 | 6.48 | 138.8 | 2199.21 | -51.83 | 13.24 | -48.81 | 1.16 | 1.14 | 2.46 | 13.8 | 95 | 1812.21 | 224453.11 | 3168985.47 | 30.2303 | -96.6312 | 165.67
2294 | 7.09 | 141.51 | 2291.55 | -60.27 | 20.27 | -59.8 | 0.74 | 0.66 | 2.91 | 29.04 | 93 | 1904.55 | 224444.67 | 3168992.5 | 30.2303 | -96.6312 | 161.41
2388 | 7.92 | 139.89 | 2384.75 | -69.77 | 28.05 | -72.07 | 0.91 | 0.88 | -1.72 | -15.11 | 94 | 1997.75 | 224435.17 | 3169000.28 | 30.2303 | -96.6312 | 158.1
2482 | 9.07 | 136.17 | 2477.72 | -80.07 | 37.36 | -85.92 | 1.36 | 1.22 | -3.96 | -27.39 | 94 | 2090.72 | 224424.87 | 3169009.59 | 30.2302 | -96.6311 | 154.99
2575 | 10.07 | 137.56 | 2569.42 | -91.35 | 47.92 | -101.33 | 1.1 | 1.08 | 1.49 | 13.7 | 93 | 2182.42 | 224413.59 | 3169020.15 | 30.2302 | -96.6311 | 152.32
2669 | 10.18 | 136.84 | 2661.96 | -103.48 | 59.15 | -117.81 | 0.18 | 0.12 | -0.77 | -49.36 | 94 | 2274.96 | 224401.46 | 3169031.38 | 30.2302 | -96.6311 | 150.25
2764 | 9.75 | 136.7 | 2755.52 | -115.46 | 70.41 | -134.19 | 0.45 | -0.45 | -0.15 | -176.84 | 95 | 2368.52 | 224389.48 | 3169042.64 | 30.2301 | -96.631 | 148.62
2858 | 10.18 | 137.06 | 2848.1 | -127.33 | 81.52 | -150.4 | 0.46 | 0.46 | 0.38 | 8.42 | 94 | 2461.1 | 224377.61 | 3169053.75 | 30.2301 | -96.631 | 147.37
2953 | 10.19 | 138.25 | 2941.61 | -139.75 | 92.84 | -167.16 | 0.22 | 0.01 | 1.25 | 87.86 | 95 | 2554.61 | 224365.19 | 3169065.07 | 30.2301 | -96.631 | 146.4
3046 | 9.84 | 135.63 | 3033.19 | -151.56 | 103.87 | -183.28 | 0.62 | -0.38 | -2.82 | -128.82 | 93 | 2646.19 | 224353.38 | 3169076.1 | 30.23 | -96.6309 | 145.58
3140 | 9.44 | 133.49 | 3125.86 | -162.61 | 115.08 | -198.91 | 0.57 | -0.43 | -2.28 | -139.19 | 94 | 2738.86 | 224342.33 | 3169087.31 | 30.23 | -96.6309 | 144.71
3234 | 9.01 | 135.32 | 3218.65 | -173.15 | 125.85 | -213.86 | 0.55 | -0.46 | 1.95 | 146.6 | 94 | 2831.65 | 224331.79 | 3169098.08 | 30.23 | -96.6309 | 143.99
3327 | 8.87 | 138.61 | 3310.52 | -183.71 | 135.71 | -228.26 | 0.57 | -0.15 | 3.54 | 106.93 | 93 | 2923.52 | 224321.23 | 3169107.94 | 30.23 | -96.6308 | 143.55
3443 | 8.56 | 138.7 | 3425.18 | -196.9 | 147.32 | -245.81 | 0.27 | -0.27 | 0.08 | 177.53 | 116 | 3038.18 | 224308.04 | 3169119.55 | 30.2299 | -96.6308 | 143.2
3541 | 8 | 136.03 | 3522.16 | -207.29 | 156.87 | -259.88 | 0.69 | -0.57 | -2.72 | -146.84 | 98 | 3135.16 | 224297.65 | 3169129.1 | 30.2299 | -96.6308 | 142.88
3636 | 8.3 | 134.01 | 3616.2 | -216.81 | 166.39 | -273.26 | 0.44 | 0.32 | -2.13 | -44.67 | 95 | 3229.2 | 224288.13 | 3169138.62 | 30.2299 | -96.6307 | 142.5
3729 | 8.71 | 138.68 | 3708.18 | -226.76 | 175.87 | -286.95 | 0.86 | 0.44 | 5.02 | 61.63 | 93 | 3321.18 | 224278.18 | 3169148.1 | 30.2298 | -96.6307 | 142.2
3823 | 9.74 | 147.9 | 3800.96 | -238.85 | 184.8 | -301.96 | 1.91 | 1.1 | 9.81 | 59.74 | 94 | 3413.96 | 224266.09 | 3169157.03 | 30.2298 | -96.6307 | 142.27
3917 | 9.95 | 153.73 | 3893.58 | -252.86 | 192.62 | -317.8 | 1.08 | 0.22 | 6.2 | 80.99 | 94 | 3506.58 | 224252.08 | 3169164.85 | 30.2298 | -96.6307 | 142.7
4011 | 11.21 | 152.8 | 3985.98 | -268.27 | 200.39 | -334.7 | 1.35 | 1.34 | -0.99 | -8.18 | 94 | 3598.98 | 224236.67 | 3169172.62 | 30.2297 | -96.6306 | 143.24
4105 | 11.75 | 152.19 | 4078.1 | -284.87 | 209.03 | -353.07 | 0.59 | 0.57 | -0.65 | -12.97 | 94 | 3691.1 | 224220.07 | 3169181.26 | 30.2297 | -96.6306 | 143.73
4199 | 11.25 | 152.1 | 4170.21 | -301.44 | 217.78 | -371.49 | 0.53 | -0.53 | -0.1 | -177.99 | 94 | 3783.21 | 224203.5 | 3169190.01 | 30.2296 | -96.6306 | 144.15
4292 | 10.94 | 149.61 | 4261.48 | -317.07 | 226.49 | -389.14 | 0.61 | -0.33 | -2.68 | -124.12 | 93 | 3874.48 | 224187.87 | 3169198.72 | 30.2296 | -96.6306 | 144.46
4386 | 10.72 | 148.37 | 4353.8 | -332.2 | 235.59 | -406.65 | 0.34 | -0.23 | -1.32 | -133.97 | 94 | 3966.8 | 224172.74 | 3169207.82 | 30.2295 | -96.6305 | 144.66
4479 | 11.85 | 148.04 | 4445 | -347.67 | 245.18 | -424.73 | 1.22 | 1.22 | -0.35 | -3.43 | 93 | 4058 | 224157.27 | 3169217.41 | 30.2295 | -96.6305 | 144.81
4574 | 12.2 | 147.64 | 4537.92 | -364.42 | 255.72 | -444.4 | 0.38 | 0.37 | -0.42 | -13.59 | 95 | 4150.92 | 224140.52 | 3169227.95 | 30.2294 | -96.6305 | 144.94
4669 | 12.23 | 145.75 | 4630.77 | -381.22 | 266.75 | -464.41 | 0.42 | 0.03 | -1.99 | -86.63 | 95 | 4243.77 | 224123.72 | 3169238.98 | 30.2294 | -96.6304 | 145.02
4763 | 11.92 | 143.2 | 4722.69 | -397.22 | 278.17 | -484.05 | 0.66 | -0.33 | -2.71 | -121.41 | 94 | 4335.69 | 224107.72 | 3169250.4 | 30.2294 | -96.6304 | 145
4856 | 11.12 | 144.2 | 4813.81 | -412.19 | 289.17 | -502.61 | 0.89 | -0.86 | 1.08 | 166.47 | 93 | 4426.81 | 224092.75 | 3169261.4 | 30.2293 | -96.6304 | 144.95
4951 | 10.82 | 142.76 | 4907.08 | -426.72 | 299.93 | -520.67 | 0.43 | -0.32 | -1.52 | -138.3 | 95 | 4520.08 | 224078.22 | 3169272.16 | 30.2293 | -96.6303 | 144.9
5045 | 10.49 | 142.08 | 4999.46 | -440.49 | 310.53 | -538.05 | 0.38 | -0.35 | -0.72 | -159.48 | 94 | 4612.46 | 224064.45 | 3169282.76 | 30.2292 | -96.6303 | 144.82
5138 | 9.89 | 140.62 | 5090.99 | -453.34 | 320.8 | -554.5 | 0.7 | -0.65 | -1.57 | -157.43 | 93 | 4703.99 | 224051.6 | 3169293.03 | 30.2292 | -96.6303 | 144.72
5232 | 9.58 | 137.6 | 5183.64 | -465.36 | 331.19 | -570.38 | 0.64 | -0.33 | -3.21 | -122.74 | 94 | 4796.64 | 224039.58 | 3169303.42 | 30.2292 | -96.6302 | 144.56
5326 | 9.94 | 139.75 | 5276.28 | -477.33 | 341.71 | -586.29 | 0.54 | 0.38 | 2.29 | 46.42 | 94 | 4889.28 | 224027.61 | 3169313.94 | 30.2291 | -96.6302 | 144.4
5420 | 10.35 | 143.5 | 5368.81 | -490.31 | 351.97 | -602.84 | 0.83 | 0.44 | 3.99 | 60.03 | 94 | 4981.81 | 224014.63 | 3169324.2 | 30.2291 | -96.6302 | 144.33
5514 | 9.86 | 142.9 | 5461.35 | -503.52 | 361.85 | -619.32 | 0.53 | -0.52 | -0.64 | -168.17 | 94 | 5074.35 | 224001.42 | 3169334.08 | 30.2291 | -96.6302 | 144.3
5607 | 10.21 | 142 | 5552.93 | -516.36 | 371.73 | -635.53 | 0.41 | 0.38 | -0.97 | -24.58 | 93 | 5165.93 | 223988.58 | 3169343.96 | 30.229 | -96.6301 | 144.25
5700 | 10.45 | 140.65 | 5644.42 | -529.38 | 382.15 | -652.2 | 0.37 | 0.26 | -1.45 | -45.91 | 93 | 5257.42 | 223975.56 | 3169354.38 | 30.229 | -96.6301 | 144.18
5794 | 9.18 | 140.68 | 5737.04 | -541.77 | 392.31 | -668.22 | 1.35 | -1.35 | 0.03 | 179.78 | 94 | 5350.04 | 223963.17 | 3169364.54 | 30.2289 | -96.6301 | 144.09
5888 | 8.05 | 137.83 | 5829.98 | -552.45 | 401.48 | -682.29 | 1.28 | -1.2 | -3.03 | -160.71 | 94 | 5442.98 | 223952.49 | 3169373.71 | 30.2289 | -96.63 | 143.99
5982 | 8.54 | 136.98 | 5923 | -562.43 | 410.66 | -695.82 | 0.54 | 0.52 | -0.9 | -14.47 | 94 | 5536 | 223942.51 | 3169382.89 | 30.2289 | -96.63 | 143.87
6076 | 9.84 | 137.24 | 6015.79 | -573.43 | 420.87 | -710.78 | 1.38 | 1.38 | 0.28 | 1.96 | 94 | 5628.79 | 223931.51 | 3169393.1 | 30.2289 | -96.63 | 143.72
6169 | 9.94 | 140.35 | 6107.41 | -585.45 | 431.39 | -726.73 | 0.58 | 0.11 | 3.34 | 80.93 | 93 | 5720.41 | 223919.49 | 3169403.62 | 30.2288 | -96.6299 | 143.62
6263 | 8.91 | 138.58 | 6200.14 | -597.15 | 441.38 | -742.11 | 1.14 | -1.1 | -1.88 | -165.15 | 94 | 5813.14 | 223907.79 | 3169413.61 | 30.2288 | -96.6299 | 143.53
6357 | 8.5 | 134.86 | 6293.05 | -607.51 | 451.12 | -756.28 | 0.74 | -0.44 | -3.96 | -127.89 | 94 | 5906.05 | 223897.43 | 3169423.35 | 30.2288 | -96.6299 | 143.4
6452 | 8.28 | 137.71 | 6387.04 | -617.53 | 460.7 | -770.08 | 0.5 | -0.23 | 3 | 119.29 | 95 | 6000.04 | 223887.41 | 3169432.93 | 30.2287 | -96.6299 | 143.28
6546 | 8.32 | 135.25 | 6480.05 | -627.36 | 470.05 | -783.6 | 0.38 | 0.04 | -2.62 | -84.79 | 94 | 6093.05 | 223877.58 | 3169442.28 | 30.2287 | -96.6298 | 143.16
6640 | 7.96 | 136.43 | 6573.11 | -636.91 | 479.32 | -796.84 | 0.42 | -0.38 | 1.26 | 155.69 | 94 | 6186.11 | 223868.03 | 3169451.55 | 30.2287 | -96.6298 | 143.04
6734 | 8.41 | 141.21 | 6666.15 | -646.98 | 488.11 | -810.2 | 0.87 | 0.48 | 5.09 | 58.91 | 94 | 6279.15 | 223857.96 | 3169460.34 | 30.2286 | -96.6298 | 142.97
6828 | 9.14 | 150.58 | 6759.05 | -658.84 | 496.09 | -824.45 | 1.7 | 0.78 | 9.97 | 67.63 | 94 | 6372.05 | 223846.1 | 3169468.32 | 30.2286 | -96.6297 | 143.02
6922 | 10.81 | 149.87 | 6851.63 | -672.97 | 504.18 | -840.54 | 1.78 | 1.78 | -0.76 | -4.56 | 94 | 6464.63 | 223831.97 | 3169476.41 | 30.2286 | -96.6297 | 143.16
7016 | 10.62 | 148.93 | 6943.99 | -688.02 | 513.07 | -857.85 | 0.27 | -0.2 | -1 | -137.85 | 94 | 6556.99 | 223816.92 | 3169485.3 | 30.2285 | -96.6297 | 143.29
7110 | 10.54 | 146.43 | 7036.39 | -702.6 | 522.3 | -875.01 | 0.5 | -0.09 | -2.66 | -101.11 | 94 | 6649.39 | 223802.34 | 3169494.53 | 30.2285 | -96.6297 | 143.37
7204 | 10.11 | 144.91 | 7128.87 | -716.51 | 531.8 | -891.81 | 0.54 | -0.46 | -1.62 | -148.39 | 94 | 6741.87 | 223788.43 | 3169504.03 | 30.2285 | -96.6296 | 143.42
7297 | 9.73 | 144.79 | 7220.48 | -729.61 | 541.02 | -907.8 | 0.41 | -0.41 | -0.13 | -176.95 | 93 | 6833.48 | 223775.33 | 3169513.25 | 30.2284 | -96.6296 | 143.44
7391 | 9.56 | 142.3 | 7313.15 | -742.28 | 550.37 | -923.54 | 0.48 | -0.18 | -2.65 | -113.39 | 94 | 6926.15 | 223762.66 | 3169522.6 | 30.2284 | -96.6296 | 143.44
7486 | 9.32 | 139.8 | 7406.87 | -754.4 | 560.16 | -939.12 | 0.5 | -0.25 | -2.63 | -121.57 | 95 | 7019.87 | 223750.54 | 3169532.39 | 30.2283 | -96.6296 | 143.41
7581 | 8.45 | 138.52 | 7500.73 | -765.5 | 569.75 | -953.78 | 0.94 | -0.92 | -1.35 | -167.83 | 95 | 7113.73 | 223739.44 | 3169541.98 | 30.2283 | -96.6295 | 143.34
7675 | 9.38 | 141.1 | 7593.59 | -776.64 | 579.14 | -968.33 | 1.08 | 0.99 | 2.74 | 24.54 | 94 | 7206.59 | 223728.3 | 3169551.37 | 30.2283 | -96.6295 | 143.29
7768 | 8.56 | 141.52 | 7685.45 | -787.95 | 588.2 | -982.83 | 0.88 | -0.88 | 0.45 | 175.64 | 93 | 7298.45 | 223716.99 | 3169560.43 | 30.2283 | -96.6295 | 143.26
7861 | 8.1 | 140.75 | 7777.47 | -798.45 | 596.65 | -996.31 | 0.51 | -0.49 | -0.83 | -166.75 | 93 | 7390.47 | 223706.49 | 3169568.88 | 30.2282 | -96.6294 | 143.23
7955 | 8.71 | 136.04 | 7870.46 | -808.7 | 605.78 | -1010.01 | 0.98 | 0.65 | -5.01 | -50.8 | 94 | 7483.46 | 223696.24 | 3169578.01 | 30.2282 | -96.6294 | 143.16
8049 | 7.67 | 139.11 | 7963.5 | -818.56 | 614.83 | -1023.37 | 1.2 | -1.11 | 3.27 | 158.71 | 94 | 7576.5 | 223686.38 | 3169587.06 | 30.2282 | -96.6294 | 143.09
8144 | 8.05 | 142.22 | 8057.61 | -828.61 | 623.06 | -1036.35 | 0.6 | 0.4 | 3.27 | 49.77 | 95 | 7670.61 | 223676.33 | 3169595.29 | 30.2281 | -96.6294 | 143.06
8237 | 6.69 | 141.6 | 8149.84 | -838.01 | 630.41 | -1048.28 | 1.46 | -1.46 | -0.67 | -176.96 | 93 | 7762.84 | 223666.93 | 3169602.64 | 30.2281 | -96.6293 | 143.05
8331 | 6.14 | 141.12 | 8243.25 | -846.21 | 636.97 | -1058.78 | 0.59 | -0.59 | -0.51 | -174.67 | 94 | 7856.25 | 223658.73 | 3169609.2 | 30.2281 | -96.6293 | 143.03
8426 | 7.14 | 142.84 | 8337.61 | -854.87 | 643.72 | -1069.77 | 1.07 | 1.05 | 1.81 | 12.1 | 95 | 7950.61 | 223650.07 | 3169615.95 | 30.2281 | -96.6293 | 143.02
8520 | 6.83 | 140.84 | 8430.91 | -863.86 | 650.78 | -1081.19 | 0.42 | -0.33 | -2.13 | -142.87 | 94 | 8043.91 | 223641.08 | 3169623.01 | 30.228 | -96.6293 | 143.01
8614 | 5.41 | 141.48 | 8524.38 | -871.66 | 657.07 | -1091.22 | 1.51 | -1.51 | 0.68 | 177.57 | 94 | 8137.38 | 223633.28 | 3169629.3 | 30.228 | -96.6293 | 142.99
8709 | 3.83 | 143.04 | 8619.06 | -877.7 | 661.77 | -1098.87 | 1.67 | -1.66 | 1.64 | 176.23 | 95 | 8232.06 | 223627.24 | 3169634 | 30.228 | -96.6292 | 142.98
8802 | 2.95 | 148.19 | 8711.9 | -882.22 | 664.9 | -1104.35 | 1 | -0.95 | 5.54 | 163.47 | 93 | 8324.9 | 223622.72 | 3169637.13 | 30.228 | -96.6292 | 143
8897 | 3.59 | 159.43 | 8806.75 | -887.08 | 667.23 | -1109.61 | 0.95 | 0.67 | 11.83 | 50.75 | 95 | 8419.75 | 223617.86 | 3169639.46 | 30.228 | -96.6292 | 143.05
8990 | 2.17 | 164.15 | 8899.63 | -891.5 | 668.73 | -1114 | 1.55 | -1.53 | 5.08 | 172.87 | 93 | 8512.63 | 223613.44 | 3169640.96 | 30.228 | -96.6292 | 143.13
9084 | 1.25 | 173.22 | 8993.58 | -894.23 | 669.34 | -1116.52 | 1.02 | -0.98 | 9.65 | 168.11 | 94 | 8606.58 | 223610.71 | 3169641.57 | 30.228 | -96.6292 | 143.18
9178 | 0.94 | 211.03 | 9087.57 | -895.91 | 669.07 | -1117.66 | 0.82 | -0.33 | 40.22 | 131.36 | 94 | 8700.57 | 223609.03 | 3169641.3 | 30.2279 | -96.6292 | 143.25
9272 | 0.98 | 212.51 | 9181.55 | -897.25 | 668.24 | -1118.19 | 0.05 | 0.04 | 1.57 | 32.54 | 94 | 8794.55 | 223607.69 | 3169640.47 | 30.2279 | -96.6292 | 143.32
9365 | 1.21 | 241.29 | 9274.54 | -898.39 | 666.95 | -1118.28 | 0.63 | 0.25 | 30.95 | 82.13 | 93 | 8887.54 | 223606.55 | 3169639.18 | 30.2279 | -96.6292 | 143.41
9459 | 2.49 | 272.95 | 9368.49 | -898.76 | 664.04 | -1116.76 | 1.69 | 1.36 | 33.68 | 55.16 | 94 | 8981.49 | 223606.18 | 3169636.27 | 30.2279 | -96.6292 | 143.54
9553 | 3.69 | 279.06 | 9462.35 | -898.18 | 659.01 | -1113.18 | 1.32 | 1.28 | 6.5 | 18.41 | 94 | 9075.35 | 223606.76 | 3169631.24 | 30.2279 | -96.6293 | 143.73
9647 | 4.96 | 290.49 | 9556.08 | -896.28 | 652.22 | -1107.47 | 1.63 | 1.35 | 12.16 | 39.95 | 94 | 9169.08 | 223608.66 | 3169624.45 | 30.2279 | -96.6293 | 143.96
9740 | 4.58 | 297.07 | 9648.76 | -893.18 | 645.14 | -1100.64 | 0.72 | -0.41 | 7.08 | 128.03 | 93 | 9261.76 | 223611.76 | 3169617.37 | 30.228 | -96.6293 | 144.16
9834 | 3.9 | 293.57 | 9742.5 | -890.2 | 638.87 | -1094.4 | 0.77 | -0.72 | -3.72 | -160.91 | 94 | 9355.5 | 223614.74 | 3169611.1 | 30.228 | -96.6293 | 144.33
9928 | 3.09 | 294.81 | 9836.33 | -887.86 | 633.64 | -1089.31 | 0.87 | -0.86 | 1.32 | 175.29 | 94 | 9449.33 | 223617.08 | 3169605.87 | 30.228 | -96.6293 | 144.49
10021 | 2.34 | 297.94 | 9929.22 | -885.91 | 629.69 | -1085.34 | 0.82 | -0.81 | 3.37 | 170.38 | 93 | 9542.22 | 223619.03 | 3169601.92 | 30.228 | -96.6293 | 144.6
10115 | 2 | 303.57 | 10023.16 | -884.11 | 626.63 | -1082.02 | 0.43 | -0.36 | 5.99 | 150.7 | 94 | 9636.16 | 223620.83 | 3169598.86 | 30.228 | -96.6294 | 144.67
10209 | 2.13 | 306.82 | 10117.1 | -882.15 | 623.86 | -1078.77 | 0.19 | 0.14 | 3.46 | 43.65 | 94 | 9730.1 | 223622.79 | 3169596.09 | 30.228 | -96.6294 | 144.73
10302 | 5.75 | 315.91 | 10209.86 | -877.77 | 619.24 | -1072.46 | 3.94 | 3.89 | 9.77 | 14.35 | 93 | 9822.86 | 223627.17 | 3169591.47 | 30.228 | -96.6294 | 144.8
10397 | 11.68 | 327.33 | 10303.73 | -866.25 | 610.73 | -1058.14 | 6.47 | 6.24 | 12.02 | 21.98 | 95 | 9916.73 | 223638.69 | 3169582.96 | 30.228 | -96.6294 | 144.82
10491 | 12.96 | 332.93 | 10395.56 | -848.85 | 600.79 | -1038.34 | 1.86 | 1.36 | 5.96 | 45.79 | 94 | 10008.56 | 223656.09 | 3169573.02 | 30.2281 | -96.6294 | 144.71
10585 | 14.53 | 332.42 | 10486.87 | -829.01 | 590.54 | -1016.43 | 1.68 | 1.67 | -0.54 | -4.66 | 94 | 10099.87 | 223675.93 | 3169562.77 | 30.2281 | -96.6295 | 144.54
10679 | 20.95 | 334.63 | 10576.35 | -803.35 | 577.86 | -988.45 | 6.87 | 6.83 | 2.35 | 7.05 | 94 | 10189.35 | 223701.59 | 3169550.09 | 30.2282 | -96.6295 | 144.27
10773 | 25.26 | 337.89 | 10662.8 | -769.56 | 563.11 | -952.82 | 4.78 | 4.59 | 3.47 | 18.04 | 94 | 10275.8 | 223735.38 | 3169535.34 | 30.2283 | -96.6295 | 143.81
10866 | 30.1 | 339.29 | 10745.13 | -729.34 | 547.38 | -911.55 | 5.25 | 5.2 | 1.51 | 8.28 | 93 | 10358.13 | 223775.6 | 3169519.61 | 30.2284 | -96.6296 | 143.11
10960 | 36.06 | 333.87 | 10823.88 | -682.4 | 526.84 | -862.02 | 7.07 | 6.34 | -5.77 | -28.7 | 94 | 10436.88 | 223822.54 | 3169499.07 | 30.2285 | -96.6297 | 142.33
10999 | 38.78 | 331.38 | 10854.85 | -661.37 | 515.93 | -838.77 | 7.98 | 6.97 | -6.38 | -30.08 | 39 | 10467.85 | 223843.57 | 3169488.16 | 30.2286 | -96.6297 | 142.04
11096 | 43.19 | 327.65 | 10928.07 | -606.63 | 483.6 | -775.8 | 5.2 | 4.55 | -3.85 | -30.44 | 97 | 10541.07 | 223898.31 | 3169455.83 | 30.2288 | -96.6298 | 141.44
11159 | 46.84 | 327.36 | 10972.59 | -569.05 | 459.66 | -731.49 | 5.8 | 5.79 | -0.46 | -3.32 | 63 | 10585.59 | 223935.89 | 3169431.89 | 30.2289 | -96.6299 | 141.07
11254 | 57.45 | 329.48 | 11030.81 | -505.2 | 420.52 | -657.15 | 11.31 | 11.17 | 2.23 | 9.63 | 95 | 10643.81 | 223999.74 | 3169392.75 | 30.229 | -96.63 | 140.23
11348 | 67.25 | 329.88 | 11074.38 | -433.4 | 378.55 | -574.83 | 10.43 | 10.43 | 0.43 | 2.17 | 94 | 10687.38 | 224071.54 | 3169350.78 | 30.2292 | -96.6301 | 138.86
11443 | 72.5 | 323.69 | 11107.09 | -358.89 | 329.67 | -486.08 | 8.24 | 5.53 | -6.52 | -49.01 | 95 | 10720.09 | 224146.05 | 3169301.9 | 30.2295 | -96.6302 | 137.43
11537 | 78.42 | 315.73 | 11130.71 | -289.64 | 270.84 | -395.27 | 10.33 | 6.3 | -8.47 | -53.52 | 94 | 10743.71 | 224215.3 | 3169243.07 | 30.2297 | -96.6304 | 136.92
11632 | 86.7 | 316.44 | 11143 | -221.83 | 205.57 | -301.57 | 8.75 | 8.72 | 0.75 | 4.91 | 95 | 10756 | 224283.11 | 3169177.8 | 30.2298 | -96.6306 | 137.18
11727 | 92.45 | 318.39 | 11143.71 | -151.92 | 141.32 | -206.86 | 6.39 | 6.05 | 2.05 | 18.75 | 95 | 10756.71 | 224353.02 | 3169113.55 | 30.23 | -96.6308 | 137.07
11821 | 93.56 | 318.15 | 11138.78 | -81.87 | 78.83 | -113.14 | 1.21 | 1.18 | -0.26 | -12.18 | 94 | 10751.78 | 224423.07 | 3169051.06 | 30.2302 | -96.631 | 136.08
11916 | 95.02 | 317.94 | 11131.67 | -11.42 | 15.5 | -18.59 | 1.55 | 1.54 | -0.22 | -8.15 | 95 | 10744.67 | 224493.52 | 3168987.73 | 30.2304 | -96.6312 | 126.38
12011 | 92.97 | 316.24 | 11125.05 | 57.98 | -49.02 | 75.89 | 2.8 | -2.16 | -1.79 | -140.34 | 95 | 10738.05 | 224562.92 | 3168923.21 | 30.2306 | -96.6314 | 319.79
12106 | 93 | 316.63 | 11120.11 | 126.73 | -114.4 | 170.39 | 0.41 | 0.03 | 0.41 | 85.59 | 95 | 10733.11 | 224631.67 | 3168857.83 | 30.2308 | -96.6316 | 317.93
12200 | 92.08 | 317.5 | 11115.94 | 195.48 | -178.36 | 264.01 | 1.35 | -0.98 | 0.93 | 136.61 | 94 | 10728.94 | 224700.42 | 3168793.87 | 30.231 | -96.6318 | 317.62
12295 | 91.82 | 318.59 | 11112.71 | 266.09 | -241.84 | 358.78 | 1.18 | -0.27 | 1.15 | 103.4 | 95 | 10725.71 | 224771.03 | 3168730.39 | 30.2312 | -96.632 | 317.73
12390 | 90.56 | 320.87 | 11110.73 | 338.55 | -303.23 | 453.71 | 2.74 | -1.33 | 2.4 | 118.9 | 95 | 10723.73 | 224843.49 | 3168669 | 30.2314 | -96.6322 | 318.15
12482 | 89.79 | 321.52 | 11110.45 | 410.24 | -360.88 | 545.7 | 1.1 | -0.84 | 0.71 | 139.83 | 92 | 10723.45 | 224915.18 | 3168611.35 | 30.2316 | -96.6323 | 318.66
12576 | 89.93 | 321.75 | 11110.68 | 483.94 | -419.22 | 639.7 | 0.29 | 0.15 | 0.24 | 58.67 | 94 | 10723.68 | 224988.88 | 3168553.01 | 30.2318 | -96.6325 | 319.1
12671 | 91.65 | 322.96 | 11109.37 | 559.15 | -477.24 | 734.68 | 2.21 | 1.81 | 1.27 | 35.12 | 95 | 10722.37 | 225064.09 | 3168494.99 | 30.2321 | -96.6327 | 319.52
12763 | 92.09 | 322.96 | 11106.37 | 632.55 | -532.63 | 826.6 | 0.48 | 0.48 | 0 | 0 | 92 | 10719.37 | 225137.49 | 3168439.6 | 30.2323 | -96.6329 | 319.9
12858 | 94.26 | 322.64 | 11101.11 | 708.1 | -589.97 | 921.42 | 2.31 | 2.28 | -0.34 | -8.37 | 95 | 10714.11 | 225213.04 | 3168382.26 | 30.2325 | -96.633 | 320.2
12952 | 94.84 | 321.8 | 11093.65 | 782.16 | -647.38 | 1015.12 | 1.08 | 0.62 | -0.89 | -55.26 | 94 | 10706.65 | 225287.1 | 3168324.85 | 30.2327 | -96.6332 | 320.39
13047 | 96.03 | 322.05 | 11084.65 | 856.61 | -705.7 | 1109.69 | 1.28 | 1.25 | 0.26 | 11.8 | 95 | 10697.65 | 225361.55 | 3168266.53 | 30.2329 | -96.6334 | 320.52
13141 | 95.43 | 321.83 | 11075.27 | 930.25 | -763.36 | 1203.22 | 0.68 | -0.64 | -0.23 | -159.95 | 94 | 10688.27 | 225435.19 | 3168208.87 | 30.2331 | -96.6336 | 320.63
13236 | 93.8 | 321.49 | 11067.63 | 1004.52 | -822.09 | 1297.9 | 1.75 | -1.72 | -0.36 | -168.24 | 95 | 10680.63 | 225509.46 | 3168150.14 | 30.2333 | -96.6337 | 320.7
13331 | 94.17 | 320.83 | 11061.02 | 1078.33 | -881.53 | 1392.67 | 0.79 | 0.39 | -0.69 | -60.64 | 95 | 10674.02 | 225583.27 | 3168090.7 | 30.2335 | -96.6339 | 320.73
13426 | 93.42 | 323.2 | 11054.74 | 1153.04 | -939.86 | 1487.45 | 2.61 | -0.79 | 2.49 | 107.52 | 95 | 10667.74 | 225657.98 | 3168032.37 | 30.2337 | -96.6341 | 320.82
13520 | 93.84 | 332.18 | 11048.77 | 1232.24 | -989.96 | 1580.62 | 9.54 | 0.45 | 9.55 | 87.04 | 94 | 10661.77 | 225737.18 | 3167982.27 | 30.234 | -96.6343 | 321.22
13615 | 93.48 | 338.2 | 11042.7 | 1318.26 | -1029.72 | 1672.7 | 6.34 | -0.38 | 6.34 | 93.23 | 95 | 10655.7 | 225823.2 | 3167942.51 | 30.2342 | -96.6344 | 322.01
13710 | 93.76 | 329.5 | 11036.69 | 1403.28 | -1071.46 | 1765.23 | 9.14 | 0.29 | -9.16 | -87.88 | 95 | 10649.69 | 225908.22 | 3167900.77 | 30.2344 | -96.6345 | 322.64
13804 | 93.57 | 323.01 | 11030.68 | 1481.25 | -1123.54 | 1858.67 | 6.89 | -0.2 | -6.9 | -91.47 | 94 | 10643.68 | 225986.19 | 3167848.69 | 30.2346 | -96.6346 | 322.82
13898 | 91.49 | 322.99 | 11026.53 | 1556.24 | -1180.06 | 1952.54 | 2.21 | -2.21 | -0.02 | -179.45 | 94 | 10639.53 | 226061.18 | 3167792.17 | 30.2349 | -96.6348 | 322.83
13992 | 91.36 | 320.56 | 11024.19 | 1630.06 | -1238.2 | 2046.51 | 2.59 | -0.14 | -2.59 | -93.03 | 94 | 10637.19 | 226135 | 3167734.03 | 30.2351 | -96.635 | 322.78
14085 | 90.57 | 319.96 | 11022.62 | 1701.56 | -1297.64 | 2139.47 | 1.07 | -0.85 | -0.65 | -142.78 | 93 | 10635.62 | 226206.5 | 3167674.59 | 30.2353 | -96.6352 | 322.67
14180 | 91.84 | 319.1 | 11020.63 | 1773.81 | -1359.29 | 2234.39 | 1.61 | 1.34 | -0.91 | -34.09 | 95 | 10633.63 | 226278.75 | 3167612.94 | 30.2355 | -96.6354 | 322.54
14274 | 91.01 | 318.01 | 11018.29 | 1844.25 | -1421.49 | 2328.23 | 1.46 | -0.88 | -1.16 | -127.28 | 94 | 10631.29 | 226349.19 | 3167550.74 | 30.2357 | -96.6356 | 322.38
14369 | 94 | 320.3 | 11014.14 | 1916.03 | -1483.55 | 2423.04 | 3.96 | 3.15 | 2.41 | 37.38 | 95 | 10627.14 | 226420.97 | 3167488.68 | 30.2359 | -96.6357 | 322.25
14464 | 93.81 | 320.09 | 11007.67 | 1988.84 | -1544.22 | 2517.8 | 0.3 | -0.2 | -0.22 | -132.2 | 95 | 10620.67 | 226493.78 | 3167428.01 | 30.2361 | -96.6359 | 322.17
14559 | 94.55 | 321.74 | 11000.74 | 2062.38 | -1603.96 | 2612.54 | 1.9 | 0.78 | 1.74 | 65.73 | 95 | 10613.74 | 226567.32 | 3167368.27 | 30.2363 | -96.6361 | 322.13
14653 | 94.99 | 321.49 | 10992.92 | 2135.81 | -1662.12 | 2706.21 | 0.54 | 0.47 | -0.27 | -29.51 | 94 | 10605.92 | 226640.75 | 3167310.11 | 30.2365 | -96.6363 | 322.11
14748 | 95.69 | 321.07 | 10984.08 | 2209.61 | -1721.29 | 2800.8 | 0.86 | 0.74 | -0.44 | -30.83 | 95 | 10597.08 | 226714.55 | 3167250.94 | 30.2367 | -96.6365 | 322.08
14841 | 94.64 | 319.42 | 10975.71 | 2280.81 | -1780.52 | 2893.39 | 2.1 | -1.13 | -1.77 | -122.5 | 93 | 10588.71 | 226785.75 | 3167191.71 | 30.2369 | -96.6366 | 322.02
14934 | 95.77 | 319.93 | 10967.27 | 2351.42 | -1840.45 | 2985.96 | 1.33 | 1.22 | 0.55 | 24.18 | 93 | 10580.27 | 226856.36 | 3167131.78 | 30.2371 | -96.6368 | 321.95
15029 | 95.25 | 319.59 | 10958.15 | 2423.6 | -1901.54 | 3080.47 | 0.65 | -0.55 | -0.36 | -146.93 | 95 | 10571.15 | 226928.54 | 3167070.69 | 30.2373 | -96.637 | 321.88
15124 | 92.49 | 319.08 | 10951.74 | 2495.49 | -1963.3 | 3175.18 | 2.95 | -2.91 | -0.54 | -169.54 | 95 | 10564.74 | 227000.43 | 3167008.93 | 30.2375 | -96.6372 | 321.81
15219 | 91.89 | 318.54 | 10948.11 | 2566.93 | -2025.81 | 3270 | 0.85 | -0.63 | -0.57 | -138.02 | 95 | 10561.11 | 227071.87 | 3166946.42 | 30.2377 | -96.6374 | 321.72
15314 | 93.21 | 320.46 | 10943.88 | 2639.09 | -2087.45 | 3364.84 | 2.45 | 1.39 | 2.02 | 55.43 | 95 | 10556.88 | 227144.03 | 3166884.78 | 30.2379 | -96.6376 | 321.66
15409 | 93.95 | 320.79 | 10937.95 | 2712.38 | -2147.6 | 3459.64 | 0.85 | 0.78 | 0.35 | 23.98 | 95 | 10550.95 | 227217.32 | 3166824.63 | 30.2381 | -96.6378 | 321.63
15504 | 95.5 | 321.08 | 10930.13 | 2785.89 | -2207.26 | 3554.31 | 1.66 | 1.63 | 0.31 | 10.55 | 95 | 10543.13 | 227290.83 | 3166764.97 | 30.2383 | -96.6379 | 321.61
15598 | 95.34 | 320.06 | 10921.25 | 2858.17 | -2266.69 | 3647.88 | 1.09 | -0.17 | -1.09 | -98.91 | 94 | 10534.25 | 227363.11 | 3166705.54 | 30.2385 | -96.6381 | 321.58
15692 | 96.01 | 320.21 | 10911.95 | 2929.97 | -2326.65 | 3741.39 | 0.73 | 0.71 | 0.16 | 12.55 | 94 | 10524.95 | 227434.91 | 3166645.58 | 30.2387 | -96.6383 | 321.55
15787 | 93.7 | 320.09 | 10903.91 | 3002.63 | -2387.3 | 3836.02 | 2.43 | -2.43 | -0.13 | -177.03 | 95 | 10516.91 | 227507.57 | 3166584.93 | 30.2389 | -96.6385 | 321.51
15880 | 93.84 | 320.49 | 10897.8 | 3074.02 | -2446.59 | 3928.79 | 0.45 | 0.15 | 0.43 | 70.66 | 93 | 10510.8 | 227578.96 | 3166525.64 | 30.2391 | -96.6387 | 321.48
15975 | 92.87 | 321.23 | 10892.24 | 3147.58 | -2506.45 | 4023.62 | 1.28 | -1.02 | 0.78 | 142.69 | 95 | 10505.24 | 227652.52 | 3166465.78 | 30.2394 | -96.6389 | 321.47
16069 | 92.98 | 321.23 | 10887.44 | 3220.77 | -2565.24 | 4117.5 | 0.12 | 0.12 | 0 | 0 | 94 | 10500.44 | 227725.71 | 3166406.99 | 30.2396 | -96.639 | 321.46
16164 | 93.59 | 323.2 | 10882 | 3295.72 | -2623.35 | 4212.33 | 2.17 | 0.64 | 2.07 | 72.71 | 95 | 10495 | 227800.66 | 3166348.88 | 30.2398 | -96.6392 | 321.48
16258 | 91.81 | 321.15 | 10877.57 | 3369.88 | -2680.92 | 4306.21 | 2.89 | -1.89 | -2.18 | -130.95 | 94 | 10490.57 | 227874.82 | 3166291.31 | 30.24 | -96.6394 | 321.5
16354 | 92.16 | 320.65 | 10874.24 | 3444.34 | -2741.43 | 4402.15 | 0.64 | 0.36 | -0.52 | -54.98 | 96 | 10487.24 | 227949.28 | 3166230.8 | 30.2402 | -96.6396 | 321.48
16446 | 93.25 | 321.13 | 10869.9 | 3515.64 | -2799.4 | 4494.04 | 1.29 | 1.18 | 0.52 | 23.73 | 92 | 10482.9 | 228020.58 | 3166172.83 | 30.2404 | -96.6397 | 321.47
16540 | 93.67 | 320.69 | 10864.23 | 3588.47 | -2858.56 | 4587.86 | 0.65 | 0.45 | -0.47 | -46.27 | 94 | 10477.23 | 228093.41 | 3166113.67 | 30.2406 | -96.6399 | 321.46
16633 | 93.01 | 319.58 | 10858.81 | 3659.73 | -2918.07 | 4680.67 | 1.39 | -0.71 | -1.19 | -120.75 | 93 | 10471.81 | 228164.67 | 3166054.16 | 30.2408 | -96.6401 | 321.43
16728 | 93.25 | 318.89 | 10853.62 | 3731.57 | -2980.01 | 4775.46 | 0.77 | 0.25 | -0.73 | -70.78 | 95 | 10466.62 | 228236.51 | 3165992.22 | 30.241 | -96.6403 | 321.39
16823 | 91.43 | 318.29 | 10849.74 | 3802.76 | -3042.79 | 4870.25 | 2.02 | -1.92 | -0.63 | -161.76 | 95 | 10462.74 | 228307.7 | 3165929.44 | 30.2412 | -96.6405 | 321.33
16917 | 92.16 | 318.25 | 10846.8 | 3872.87 | -3105.33 | 4964.05 | 0.78 | 0.78 | -0.04 | -3.13 | 94 | 10459.8 | 228377.81 | 3165866.9 | 30.2414 | -96.6407 | 321.28
17012 | 94.63 | 318.46 | 10841.17 | 3943.74 | -3168.34 | 5058.73 | 2.61 | 2.6 | 0.22 | 4.85 | 95 | 10454.17 | 228448.68 | 3165803.89 | 30.2416 | -96.6409 | 321.22
17106 | 93.06 | 317.91 | 10834.87 | 4013.63 | -3230.87 | 5152.36 | 1.77 | -1.67 | -0.59 | -160.71 | 94 | 10447.87 | 228518.57 | 3165741.36 | 30.2418 | -96.6411 | 321.17
17201 | 91.97 | 322.29 | 10830.7 | 4086.43 | -3291.73 | 5247.21 | 4.75 | -1.15 | 4.61 | 103.88 | 95 | 10443.7 | 228591.37 | 3165680.5 | 30.242 | -96.6412 | 321.15
17296 | 92 | 329.38 | 10827.41 | 4164.93 | -3345.02 | 5341.83 | 7.46 | 0.03 | 7.46 | 89.63 | 95 | 10440.41 | 228669.87 | 3165627.21 | 30.2422 | -96.6414 | 321.23
17391 | 90.69 | 326.01 | 10825.17 | 4245.19 | -3395.77 | 5436.23 | 3.8 | -1.38 | -3.55 | -111.2 | 95 | 10438.17 | 228750.13 | 3165576.46 | 30.2424 | -96.6415 | 321.34
17486 | 92 | 323.72 | 10822.94 | 4322.86 | -3450.42 | 5531.04 | 2.78 | 1.38 | -2.41 | -60.2 | 95 | 10435.94 | 228827.8 | 3165521.81 | 30.2427 | -96.6417 | 321.4
17580 | 93.61 | 323.11 | 10818.34 | 4398.24 | -3506.38 | 5624.87 | 1.83 | 1.71 | -0.65 | -20.71 | 94 | 10431.34 | 228903.18 | 3165465.85 | 30.2429 | -96.6419 | 321.44
17674 | 93.73 | 322.86 | 10812.33 | 4473.15 | -3562.85 | 5718.65 | 0.29 | 0.13 | -0.27 | -64.31 | 94 | 10425.33 | 228978.09 | 3165409.38 | 30.2431 | -96.6421 | 321.46
17770 | 93.19 | 324.78 | 10806.53 | 4550.49 | -3619.41 | 5814.39 | 2.07 | -0.56 | 2 | 105.68 | 96 | 10419.53 | 229055.43 | 3165352.82 | 30.2433 | -96.6422 | 321.5
17864 | 93.03 | 329.15 | 10801.43 | 4629.16 | -3670.57 | 5907.8 | 4.65 | -0.17 | 4.65 | 91.98 | 94 | 10414.43 | 229134.1 | 3165301.66 | 30.2435 | -96.6424 | 321.59
17960 | 94.07 | 340.67 | 10795.47 | 4715.78 | -3711.14 | 6000.86 | 12.03 | 1.08 | 12 | 84.49 | 96 | 10408.47 | 229220.72 | 3165261.09 | 30.2438 | -96.6425 | 321.8
18112 | 94.07 | 340.67 | 10784.68 | 4858.85 | -3761.32 | 6144.08 | 0 | 0 | 0 | 0 | 152 | 10397.68 | 229363.79 | 3165210.91 | 30.2442 | -96.6426 | 322.26

## 7_15_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/15/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 15630 |  |  | Well Cost($): |  | 15630
|  |  |  | 24hr Summary: |  | M/U BHA #1, Drill Surface
|  |  |  | 24hr Lookahead: |  | Drill Surface, Casing ops, Skid Rig
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 7 | PV: | 2
End Depth (Usft): |  | 3174 |  | 3174 |  | OD (in): |  |  |  | 300: | 5 | YP: | 3
Total Drilled (Usft): |  | 3066 |  | 3066 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): |  | 261 |  | 261 | [5 empty] | 100: | 2 | Chlorides: | 400
Rotary Drilled (Usft): |  | 2805 |  | 2805 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.40 / 5.70
Drlg/Circ Hrs: |  | 5.98 / 2.35 |  | 5.98 / 2.35 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 5.7/94.3
Slide Drilling Hrs: |  | 1.52 |  | 1.52 |  | SN: |  | 47424 |  | 10s Gel: | 1 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 4.47 |  | 4.47 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.5 / 120.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 627.99 / 172.09 |  | 627.99 / 172.09 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 8.33 |  | 8.33 |  | Grade In:
% Slide: |  | 8.51 |  | 8.51 |  | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
% Rotary: |  | 91.49 |  | 91.49 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
13 Stab |  |  |  | 8.125 | 3 |  |  |  |  | 6.34 |  | 7.84
7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  |  | 8 | [5 empty] | 37.27 |  | 45.11
NMPC |  |  |  | 8 | 3.25 |  |  |  |  | 8.58 |  | 53.69
UBHO Sub UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.66 |  | 57.35
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.83 |  | 86.18
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.99 |  | 115.17
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.13 |  | 117.3
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 274.62 |  | 391.92
391.92
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800067 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.8 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
198 | 0.66 | 225.19 | 198 | -0.8 | -0.81 | 0.33 |  | 225.19 | -0.13 | 0.33 |  | 0 | 198
290 | 0.67 | 227.06 | 289.99 | -1.54 | -1.58 | 0.03 |  | 66.2 | -0.23 | 0.01 |  | 0 | 92
414 | 0.64 | 233.25 | 413.98 | -2.45 | -2.66 | 0.06 |  | 116.05 | -0.26 | -0.02 |  | 0 | 124
508 | 0.45 | 227.27 | 507.98 | -3.02 | -3.36 | 0.21 |  | -166.31 | -0.27 | -0.2 |  | 0 | 94
602 | 0.75 | 211.25 | 601.97 | -3.79 | -3.95 | 0.36 |  | -37.38 | -0.51 | 0.32 |  | 0 | 94
696 | 1.09 | 196.84 | 695.96 | -5.17 | -4.52 | 0.43 |  | -41.58 | -1.24 | 0.36 |  | 0 | 94
790 | 1.22 | 192.81 | 789.94 | -7.01 | -5.01 | 0.16 |  | -34.03 | -2.37 | 0.14 |  | 0 | 94
884 | 1.01 | 198.94 | 883.92 | -8.77 | -5.5 | 0.26 |  | 153.44 | -3.44 | -0.22 |  | 0 | 94
978 | 1.14 | 200.51 | 977.91 | -10.42 | -6.09 | 0.14 |  | 13.55 | -4.37 | 0.14 |  | 0 | 94
1072 | 1 | 214.5 | 1071.89 | -11.98 | -6.89 | 0.31 |  | 125.06 | -5.09 | -0.15 |  | 0 | 94
1166 | 0.92 | 206.13 | 1165.88 | -13.33 | -7.68 | 0.17 |  | -123.84 | -5.66 | -0.09 |  | 0 | 94
1260 | 1.07 | 215.66 | 1259.86 | -14.72 | -8.53 | 0.24 |  | 52.64 | -6.22 | 0.16 |  | 0 | 94
1354 | 1.17 | 218.45 | 1353.84 | -16.19 | -9.63 | 0.12 |  | 30.01 | -6.68 | 0.11 |  | 0 | 94
1448 | 0.96 | 223.27 | 1447.83 | -17.51 | -10.77 | 0.24 |  | 159.29 | -7.01 | -0.22 |  | 0 | 94
1543 | 1.07 | 199.39 | 1542.81 | -18.93 | -11.61 | 0.46 |  | -87.56 | -7.59 | 0.12 |  | 0 | 95
1636 | 1.33 | 168.66 | 1635.79 | -20.8 | -11.69 | 0.73 |  | -83.84 | -9.01 | 0.28 |  | 0 | 93
1730 | 2.3 | 153.45 | 1729.75 | -23.56 | -10.63 | 1.14 |  | -34.15 | -11.83 | 1.03 |  | 0 | 94
1823 | 3.54 | 143.58 | 1822.62 | -27.54 | -8.09 | 1.43 |  | -27.05 | -16.53 | 1.33 |  | -10.61 | 93
1917 | 4.38 | 139.96 | 1916.4 | -32.62 | -4.06 | 0.93 |  | -18.38 | -23.01 | 0.89 |  | -3.85 | 94
2012 | 4.84 | 138.27 | 2011.09 | -38.39 | 0.94 | 0.5 |  | -17.29 | -30.64 | 0.48 |  | -1.78 | 95
2106 | 5.4 | 136.46 | 2104.72 | -44.56 | 6.63 | 0.62 |  | -16.99 | -39.01 | 0.6 |  | -1.93 | 94
2201 | 6.48 | 138.8 | 2199.21 | -51.83 | 13.24 | 1.16 |  | 13.8 | -48.81 | 1.14 |  | 2.46 | 95
2294 | 7.09 | 141.51 | 2291.55 | -60.27 | 20.27 | 0.74 |  | 29.04 | -59.8 | 0.66 |  | 2.91 | 93
2388 | 7.92 | 139.89 | 2384.75 | -69.77 | 28.05 | 0.91 |  | -15.11 | -72.07 | 0.88 |  | -1.72 | 94
2482 | 9.07 | 136.17 | 2477.72 | -80.07 | 37.36 | 1.36 |  | -27.39 | -85.92 | 1.22 |  | -3.96 | 94
2575 | 10.07 | 137.56 | 2569.42 | -91.35 | 47.92 | 1.1 |  | 13.7 | -101.33 | 1.08 |  | 1.49 | 93
2669 | 10.18 | 136.84 | 2661.96 | -103.48 | 59.15 | 0.18 |  | -49.36 | -117.81 | 0.12 |  | -0.77 | 94
2764 | 9.75 | 136.7 | 2755.52 | -115.46 | 70.41 | 0.45 |  | -176.84 | -134.19 | -0.45 |  | -0.15 | 95
2858 | 10.18 | 137.06 | 2848.1 | -127.33 | 81.52 | 0.46 |  | 8.42 | -150.4 | 0.46 |  | 0.38 | 94
2953 | 10.19 | 138.25 | 2941.61 | -139.75 | 92.84 | 0.22 |  | 87.86 | -167.16 | 0.01 |  | 1.25 | 95
3046 | 9.84 | 135.63 | 3033.19 | -151.56 | 103.87 | 0.62 |  | -128.82 | -183.28 | -0.38 |  | -2.82 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 512.42 | 16.39 | 97.97 | 243 | 876.09 | 1995.65 | 1649.57 | 0 | 96.41 | 91.41 | 86.41 | 8304.38 | 0
Run | 512.42 | 16.39 | 97.97 | 243 | 876.09 | 1995.65 | 1649.57 | 0 | 96.41 | 91.41 | 86.41 | 8304.38 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Mob/DeMob |  |  |  |  | 07/15/2021 |  | 1 |  | 6000 |  | 1 | 6000
Dir & MWD /Gamma |  |  |  |  | 07/15/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/15/2021 |  | 5 |  | 100 |  | 4 | 400
13 Stab Rental (Used) |  |  |  |  | 07/15/2021 |  | 7 |  | 1150 |  | 1 | 1150
13 Stab Rental (Not Used) |  |  |  |  | 07/15/2021 |  | 8 |  | 230 |  | 1 | 230
Mileage |  |  |  |  | 07/15/2021 |  | 16 |  | 2 |  | 700 | 1400
Multi Rig Discount |  |  |  |  | 07/15/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 15630
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/15/2021 | 00:00 | 14:30 | 14.5 | 108 | 108 | 0 | SUR |  | 24B | STBY
07/15/2021 | 14:30 | 15:40 | 1.17 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | P/U BHA #1
07/15/2021 | 15:40 | 16:05 | 0.42 | 108 | 269 | 161 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/269.00, w/WOB 3.00,Flow 600.00, RPM 65.00, Press 600.00, Tq 1500.00, ROP 386.40, Diff 220.00, Temp 92.00
07/15/2021 | 16:05 | 16:10 | 0.08 | 269 | 269 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 16:10 | 16:20 | 0.17 | 269 | 361 | 92 | SUR | 1: BHA 1 | 2K | Rotary Drill f/269.00 t/361.00, w/WOB 5.00,Flow 700.00, RPM 85.00, Press 800.00, Tq 2500.00, ROP 552.00, Diff 150.00, Temp 95.00
07/15/2021 | 16:20 | 16:25 | 0.08 | 361 | 361 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 16:25 | 16:45 | 0.33 | 361 | 485 | 124 | SUR | 1: BHA 1 | 2K | Rotary Drill f/361.00 t/485.00, w/WOB 5.00,Flow 700.00, RPM 85.00, Press 800.00, Tq 2500.00, ROP 372.00, Diff 150.00, Temp 95.00
07/15/2021 | 16:45 | 16:50 | 0.08 | 485 | 485 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 16:50 | 16:57 | 0.12 | 485 | 579 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/485.00 t/579.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1100.00, Tq 2500.00, ROP 805.71, Diff 200.00, Temp 95.00
07/15/2021 | 16:57 | 17:01 | 0.07 | 579 | 579 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 17:01 | 17:11 | 0.17 | 579 | 673 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/579.00 t/673.00, w/WOB 5.00,Flow 700.00, RPM 100.00, Press 1100.00, Tq 2500.00, ROP 564.00, Diff 200.00, Temp 95.00
07/15/2021 | 17:11 | 17:15 | 0.07 | 673 | 673 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 17:15 | 17:22 | 0.12 | 673 | 767 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/673.00 t/767.00, w/WOB 7.00,Flow 900.00, RPM 100.00, Press 1700.00, Tq 3000.00, ROP 805.71, Diff 400.00, Temp 97.00
07/15/2021 | 17:22 | 17:26 | 0.07 | 767 | 767 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 17:26 | 17:32 | 0.1 | 767 | 861 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/767.00 t/861.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 6059.00, ROP 940.00, Diff 400.00, Temp 99.00
07/15/2021 | 17:32 | 17:36 | 0.07 | 861 | 861 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 17:36 | 17:42 | 0.1 | 861 | 955 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/861.00 t/955.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 6059.00, ROP 940.00, Diff 400.00, Temp 99.00
07/15/2021 | 17:42 | 17:46 | 0.07 | 955 | 955 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 17:46 | 17:51 | 0.08 | 955 | 1049 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/955.00 t/1049.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 6059.00, ROP 1128.00, Diff 400.00, Temp 99.00
07/15/2021 | 17:51 | 17:54 | 0.05 | 1049 | 1049 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 17:54 | 18:00 | 0.1 | 1049 | 1143 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1049.00 t/1143.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 6227.00, ROP 940.00, Diff 400.00, Temp 99.00
07/15/2021 | 18:00 | 18:04 | 0.07 | 1143 | 1143 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 18:04 | 18:10 | 0.1 | 1143 | 1237 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1143.00 t/1237.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 7591.00, ROP 940.00, Diff 400.00, Temp 99.00
07/15/2021 | 18:10 | 18:15 | 0.08 | 1237 | 1237 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 18:15 | 18:23 | 0.13 | 1237 | 1331 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1237.00 t/1331.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8153.00, ROP 705.00, Diff 400.00, Temp 99.00
07/15/2021 | 18:23 | 18:27 | 0.07 | 1331 | 1331 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 18:27 | 18:33 | 0.1 | 1331 | 1425 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1331.00 t/1425.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8400, ROP 940.00, Diff 400.00, Temp 99.00
07/15/2021 | 18:33 | 18:37 | 0.07 | 1425 | 1425 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 18:37 | 18:43 | 0.1 | 1425 | 1519 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1425.00 t/1519.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8400, ROP 940.00, Diff 400.00, Temp 99.00
07/15/2021 | 18:43 | 18:47 | 0.07 | 1519 | 1519 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 18:47 | 18:52 | 0.08 | 1519 | 1534 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1519.00 t/1534.00, TF 135.00M, w/WOB 5.00,Flow 900.00, Press 1800.00, Tq 0.00, ROP 180.00, Diff 200.00, Temp 99.00
07/15/2021 | 18:52 | 18:57 | 0.08 | 1534 | 1614 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1534.00 t/1614.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8400.00, ROP 960.00, Diff 400.00, Temp 99.00
07/15/2021 | 18:57 | 19:01 | 0.07 | 1614 | 1614 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 19:01 | 19:06 | 0.08 | 1614 | 1634 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1614.00 t/1634.00, TF 135.00M, w/WOB 5.00,Flow 900.00, Press 1800.00, Tq 0.00, ROP 240.00, Diff 200.00, Temp 99.00
07/15/2021 | 19:06 | 19:14 | 0.13 | 1634 | 1707 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1634.00 t/1707.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8400.00, ROP 547.50, Diff 400.00, Temp 99.00
07/15/2021 | 19:14 | 19:18 | 0.07 | 1707 | 1707 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 19:18 | 19:23 | 0.08 | 1707 | 1727 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1707.00 t/1727.00, TF 135.00M, w/WOB 5.00,Flow 900.00, Press 1800.00, Tq 0.00, ROP 240.00, Diff 200.00, Temp 99.00
07/15/2021 | 19:23 | 19:31 | 0.13 | 1727 | 1801 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1727.00 t/1801.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 8935.00, ROP 555.00, Diff 400.00, Temp 105.00
07/15/2021 | 19:31 | 19:36 | 0.08 | 1801 | 1801 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 19:36 | 19:41 | 0.08 | 1801 | 1819 | 18 | SUR | 1: BHA 1 | 2J | Slide Drill f/1801.00 t/1819.00, TF 110.00M, w/WOB 5.00,Flow 900.00, Press 1800.00, Tq 0.00, ROP 216.00, Diff 200.00, Temp 105.00
07/15/2021 | 19:41 | 19:48 | 0.12 | 1819 | 1894 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1819.00 t/1894.00, w/WOB 24.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 10692.00, ROP 642.86, Diff 300.00, Temp 105.00
07/15/2021 | 19:48 | 19:53 | 0.08 | 1894 | 1894 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 19:53 | 19:58 | 0.08 | 1894 | 1909 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1894.00 t/1909.00, TF -20.00G, w/WOB 6.00,Flow 900.00, Press 1900.00, Tq 0.00, ROP 180.00, Diff 200.00, Temp 105.00
07/15/2021 | 19:58 | 20:06 | 0.13 | 1909 | 1988 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1909.00 t/1988.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 10692.00, ROP 592.50, Diff 400.00, Temp 105.00
07/15/2021 | 20:06 | 20:10 | 0.07 | 1988 | 1988 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 20:10 | 20:14 | 0.07 | 1988 | 2003 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1988.00 t/2003.00, TF -20.00G, w/WOB 7.00,Flow 900.00, Press 1900.00, Tq 0.00, ROP 225.00, Diff 200.00, Temp 105.00
07/15/2021 | 20:14 | 20:22 | 0.13 | 2003 | 2083 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2003.00 t/2083.00, w/WOB 28.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 10692.00, ROP 600.00, Diff 400.00, Temp 105.00
07/15/2021 | 20:22 | 20:26 | 0.07 | 2083 | 2083 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 20:26 | 20:36 | 0.17 | 2083 | 2103 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2083.00 t/2103.00, TF 0.00G, w/WOB 5.00,Flow 900.00, Press 2000.00, Tq 0.00, ROP 120.00, Diff 300.00, Temp 105.00
07/15/2021 | 20:36 | 20:46 | 0.17 | 2103 | 2177 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2103.00 t/2177.00, w/WOB 28.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 10692.00, ROP 444.00, Diff 400.00, Temp 105.00
07/15/2021 | 20:46 | 20:51 | 0.08 | 2177 | 2177 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 20:51 | 21:00 | 0.15 | 2177 | 2197 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2177.00 t/2197.00, TF 10.00G, w/WOB 5.00,Flow 900.00, Press 2100.00, Tq 0.00, ROP 133.33, Diff 200.00, Temp 105.00
07/15/2021 | 21:00 | 21:08 | 0.13 | 2197 | 2272 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2197.00 t/2272.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 10692.00, ROP 562.50, Diff 600.00, Temp 111.00
07/15/2021 | 21:08 | 21:13 | 0.08 | 2272 | 2272 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 21:13 | 21:18 | 0.08 | 2272 | 2292 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2272.00 t/2292.00, TF 0.00G, w/WOB 5.00,Flow 900.00, Press 2100.00, Tq 0.00, ROP 240.00, Diff 200.00, Temp 111.00
07/15/2021 | 21:18 | 21:26 | 0.13 | 2292 | 2365 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2292.00 t/2365.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 10692.00, ROP 547.50, Diff 600.00, Temp 111.00
07/15/2021 | 21:26 | 21:34 | 0.13 | 2365 | 2365 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection Recycle 1 time missed sync
07/15/2021 | 21:34 | 21:42 | 0.13 | 2365 | 2385 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2365.00 t/2385.00, TF -20.00G, w/WOB 5.00,Flow 900.00, Press 2100.00, Tq 0.00, ROP 150.00, Diff 200.00, Temp 111.00
07/15/2021 | 21:42 | 21:52 | 0.17 | 2385 | 2459 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2385.00 t/2459.00, w/WOB 32.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 12467.00, ROP 444.00, Diff 600.00, Temp 111.00
07/15/2021 | 21:52 | 21:57 | 0.08 | 2459 | 2459 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 21:57 | 22:05 | 0.13 | 2459 | 2479 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2459.00 t/2479.00, TF -10.00G, w/WOB 5.00,Flow 900.00, Press 2100.00, Tq 0.00, ROP 150.00, Diff 200.00, Temp 111.00
07/15/2021 | 22:05 | 22:12 | 0.12 | 2479 | 2553 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2479.00 t/2553.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 12500.00, ROP 634.29, Diff 600.00, Temp 111.00
07/15/2021 | 22:12 | 22:16 | 0.07 | 2553 | 2553 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 22:16 | 22:23 | 0.12 | 2553 | 2571 | 18 | SUR | 1: BHA 1 | 2J | Slide Drill f/2553.00 t/2571.00, TF 0.00G, w/WOB 5.00,Flow 900.00, Press 2100.00, Tq 0.00, ROP 154.29, Diff 100.00, Temp 114.00
07/15/2021 | 22:23 | 22:30 | 0.12 | 2571 | 2646 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2571.00 t/2646.00, w/WOB 32.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 11611.00, ROP 642.86, Diff 500.00, Temp 114.00
07/15/2021 | 22:30 | 22:35 | 0.08 | 2646 | 2646 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 22:35 | 22:44 | 0.15 | 2646 | 2740 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2646.00 t/2740.00, w/WOB 33,Flow 900.00, RPM 100.00, Press 2500.00, Tq 12505, ROP 626.67, Diff 500.00, Temp 114.00
07/15/2021 | 22:44 | 22:49 | 0.08 | 2740 | 2740 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 22:49 | 22:57 | 0.13 | 2740 | 2835 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2740.00 t/2835.00, w/WOB 34.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 10848.00, ROP 712.50, Diff 500.00, Temp 114.00
07/15/2021 | 22:57 | 23:02 | 0.08 | 2835 | 2835 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 23:02 | 23:08 | 0.1 | 2835 | 2855 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2835.00 t/2855.00, TF 20.00G, w/WOB 8.00,Flow 900.00, Press 2200.00, Tq 0.00, ROP 200.00, Diff 200.00, Temp 114.00
07/15/2021 | 23:08 | 23:16 | 0.13 | 2855 | 2929 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2855.00 t/2929.00, w/WOB 34.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 10848.00, ROP 555.00, Diff 500.00, Temp 116.00
07/15/2021 | 23:16 | 23:20 | 0.07 | 2929 | 2929 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 23:20 | 23:28 | 0.13 | 2929 | 3024 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2929.00 t/3024.00, w/WOB 33.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 12222.00, ROP 712.50, Diff 500.00, Temp 116.00
07/15/2021 | 23:28 | 23:33 | 0.08 | 3024 | 3024 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 23:33 | 23:41 | 0.13 | 3024 | 3117 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3024.00 t/3117.00, w/WOB 32,Flow 900.00, RPM 100.00, Press 2500.00, Tq 11840, ROP 697.50, Diff 500.00, Temp 116.00
07/15/2021 | 23:41 | 23:46 | 0.08 | 3117 | 3117 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 23:46 | 23:55 | 0.15 | 3117 | 3137 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3117.00 t/3137.00, TF 30.00G, w/WOB 12.00,Flow 900.00, Press 2200.00, Tq 0.00, ROP 133.33, Diff 200.00, Temp 116.00
07/15/2021 | 23:55 | 24:00 | 0.08 | 3137 | 3174 | 37 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3137.00 t/3174.00, w/WOB 33.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 9564.00, ROP 444.00, Diff 500.00, Temp 116.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_16_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/16/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 22480
|  |  |  | 24hr Summary: |  | Drill Surface t/ TD, POOH, Stand by for casing ops
|  |  |  | 24hr Lookahead: |  | Casing ops, Skid Rig to Redwood C1H
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3174 |  | 108 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 7 | PV: | 2
End Depth (Usft): |  | 3514 |  | 3514 |  | OD (in): |  |  |  | 300: | 5 | YP: | 3
Total Drilled (Usft): |  | 340 |  | 3406 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): |  | 60 |  | 321 | [5 empty] | 100: | 2 | Chlorides: | 400
Rotary Drilled (Usft): |  | 280 |  | 3085 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.40 / 5.70
Drlg/Circ Hrs: |  | 1.00 / 1.33 |  | 6.98 / 3.68 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 5.7/94.3
Slide Drilling Hrs: |  | 0.43 |  | 1.95 |  | SN: |  | 47424 |  | 10s Gel: | 1 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 0.57 |  | 5.03 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.5 / 120.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 494.12 / 138.46 |  | 612.91 / 164.62 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 4.5 |  | 12.83 |  | Grade In:
% Slide: |  | 17.65 |  | 9.42 |  | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
% Rotary: |  | 82.35 |  | 90.58 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
13 Stab |  |  |  | 8.125 | 3 |  |  |  |  | 6.34 |  | 7.84
7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  |  | 8 | [5 empty] | 37.27 |  | 45.11
NMPC |  |  |  | 8 | 3.25 |  |  |  |  | 8.58 |  | 53.69
UBHO Sub UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.66 |  | 57.35
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.83 |  | 86.18
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.99 |  | 115.17
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.13 |  | 117.3
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 274.62 |  | 391.92
391.92
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800067 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.8 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3140 | 9.44 | 133.49 | 3125.86 | -162.61 | 115.08 | 0.57 |  | -139.19 | -198.91 | -0.43 |  | -2.28 | 94
3234 | 9.01 | 135.32 | 3218.65 | -173.15 | 125.85 | 0.55 |  | 146.6 | -213.86 | -0.46 |  | 1.95 | 94
3327 | 8.87 | 138.61 | 3310.52 | -183.71 | 135.71 | 0.57 |  | 106.93 | -228.26 | -0.15 |  | 3.54 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 340 | 24.86 | 100 | 249 | 900 | 2414.29 | 2000 | 0 | 120 | 115 | 110 | 13138.75 | 0
Run | 487.73 | 17.51 | 98.19 | 244 | 879.25 | 2050.94 | 1695.85 | 0 | 99.53 | 94.53 | 89.53 | 8841.53 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Multi Rig Discount |  |  |  |  | 07/16/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 07/16/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/16/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/16/2021 | 00:00 | 00:03 | 0.05 | 3174 | 3211 | 37 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3174.00 t/3211.00, w/WOB 33.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 9564.00, ROP 740.00, Diff 500.00, Temp 116.00
07/16/2021 | 00:03 | 00:08 | 0.08 | 3211 | 3211 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/16/2021 | 00:08 | 00:17 | 0.15 | 3211 | 3231 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3211.00 t/3231.00, TF 20.00G, w/WOB 10.00,Flow 900.00, Press 2200.00, Tq 0.00, ROP 133.33, Diff 200.00, Temp 120.00
07/16/2021 | 00:17 | 00:26 | 0.15 | 3231 | 3305 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3231.00 t/3305.00, w/WOB 33.00,Flow 900.00, RPM 100.00, Press 2500.00, Tq 11741.00, ROP 493.33, Diff 500.00, Temp 120.00
07/16/2021 | 00:26 | 00:31 | 0.08 | 3305 | 3305 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/16/2021 | 00:31 | 00:40 | 0.15 | 3305 | 3325 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3305.00 t/3325.00, TF 30.00G, w/WOB 14.00,Flow 900.00, Press 2300.00, Tq 0.00, ROP 133.33, Diff 300.00, Temp 120.00
07/16/2021 | 00:40 | 00:48 | 0.13 | 3325 | 3398 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3325.00 t/3398.00, w/WOB 35.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 15625.00, ROP 547.50, Diff 600.00, Temp 120.00
07/16/2021 | 00:48 | 00:53 | 0.08 | 3398 | 3398 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/16/2021 | 00:53 | 01:01 | 0.13 | 3398 | 3418 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3398.00 t/3418.00, TF 0G, w/WOB 14,Flow 900.00, Press 2200, Tq 0, ROP 150.00, Diff 200.00, Temp 120.00
07/16/2021 | 01:01 | 01:15 | 0.23 | 3418 | 3514 | 96 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3418.00 t/3514.00, w/WOB 35.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 15625.00, ROP 411.43, Diff 600.00, Temp 120.00
07/16/2021 | 01:15 | 01:20 | 0.08 | 3514 | 3514 | 0 | SUR | 1: BHA 1 | 5A | Survey on bottom
07/16/2021 | 01:20 | 02:20 | 1 | 3514 | 3514 | 0 | SUR | 1: BHA 1 | 5A | Circulate @ TD for surface
07/16/2021 | 02:20 | 04:00 | 1.67 | 3514 | 3514 | 0 | SUR | 1: BHA 1 | 6B | POOH t/ run surface casing
07/16/2021 | 04:00 | 04:30 | 0.5 | 3514 | 3514 | 0 | SUR | 1: BHA 1 | 6P | Rack BHA in derrick. L/D MWD tool
07/16/2021 | 04:30 | 24:00 | 19.5 | 3514 | 3514 | 0 | SUR |  | 24B | Standby for casing ops and rig skid
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_28_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 39830
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Skid rig, nipple up, test, pick up BHA 2
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3514 |  | 3514 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 3514 |  | 3514 |  | OD (in): |  |  |  | 300: | 25 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): | [9 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: | [5 empty] | SN: |  | 55308 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: | [5 empty] | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.013 |  |  |  | 8 | 2 |  |  | 100 |  | 38.05 |  | 39.55
NMPC |  |  |  | 8 | 3.125 |  |  | 150 |  | 9.01 |  | 48.56
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.73 |  | 52.29
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.84 |  | 82.13
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.58 |  | 111.71
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 3.06 |  | 114.77
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 302
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 304.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 579.52
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2641.22
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.61 |  | 2665.83
2665.83
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
8 Motor Reline |  |  |  |  | 07/28/2021 |  | 6 |  | 10500 |  | 1 | 10500
Dir & MWD /Gamma |  |  |  |  | 07/28/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/28/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/28/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/28/2021 | 00:00 | 23:15 | 23.25 | 3514 | 3514 | 0 | INT |  | 24B | Stand by
07/28/2021 | 23:15 | 24:00 | 0.75 | 3514 | 3514 | 0 | INT | 2: BHA 2 | 6O | Pick u BHA #2
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_29_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/29/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 46680
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Drill ahead in tangent section
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3514 |  | 3514 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 7268 |  | 7268 |  | OD (in): |  |  |  | 300: | 25 | YP: | 9
Total Drilled (Usft): |  | 3754 |  | 3754 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 272 |  | 272 | [5 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): |  | 3482 |  | 3482 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: |  | 13.88 / 3.87 |  | 13.88 / 3.87 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 6.45 |  | 6.45 |  | SN: |  | 55308 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  | 7.43 |  | 7.43 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 468.43 / 42.17 |  | 468.43 / 42.17 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 24 |  | Grade In: |  | New
% Slide: |  | 7.25 |  | 7.25 |  | Grade Out:
% Rotary: |  | 92.75 |  | 92.75 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.013 |  |  |  | 8 | 2 |  |  | 100 |  | 38.05 |  | 39.55
NMPC |  |  |  | 8 | 3.125 |  |  | 150 |  | 9.01 |  | 48.56
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.73 |  | 52.29
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.84 |  | 82.13
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.58 |  | 111.71
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 3.06 |  | 114.77
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 302
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 304.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 579.52
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2641.22
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.61 |  | 2665.83
2665.83
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3541 | 8 | 136.03 | 3522.16 | -207.29 | 156.87 | 0.69 |  | -146.84 | -259.88 | -0.57 |  | -2.72 | 98
3636 | 8.3 | 134.01 | 3616.2 | -216.81 | 166.39 | 0.44 |  | -44.67 | -273.26 | 0.32 |  | -2.13 | 95
3729 | 8.71 | 138.68 | 3708.18 | -226.76 | 175.87 | 0.86 |  | 61.63 | -286.95 | 0.44 |  | 5.02 | 93
3823 | 9.74 | 147.9 | 3800.96 | -238.85 | 184.8 | 1.91 |  | 59.74 | -301.96 | 1.1 |  | 9.81 | 94
3917 | 9.95 | 153.73 | 3893.58 | -252.86 | 192.62 | 1.08 |  | 80.99 | -317.8 | 0.22 |  | 6.2 | 94
4011 | 11.21 | 152.8 | 3985.98 | -268.27 | 200.39 | 1.35 |  | -8.18 | -334.7 | 1.34 |  | -0.99 | 94
4105 | 11.75 | 152.19 | 4078.1 | -284.87 | 209.03 | 0.59 |  | -12.97 | -353.07 | 0.57 |  | -0.65 | 94
4199 | 11.25 | 152.1 | 4170.21 | -301.44 | 217.78 | 0.53 |  | -177.99 | -371.49 | -0.53 |  | -0.1 | 94
4292 | 10.94 | 149.61 | 4261.48 | -317.07 | 226.49 | 0.61 |  | -124.12 | -389.14 | -0.33 |  | -2.68 | 93
4386 | 10.72 | 148.37 | 4353.8 | -332.2 | 235.59 | 0.34 |  | -133.97 | -406.65 | -0.23 |  | -1.32 | 94
4479 | 11.85 | 148.04 | 4445 | -347.67 | 245.18 | 1.22 |  | -3.43 | -424.73 | 1.22 |  | -0.35 | 93
4574 | 12.2 | 147.64 | 4537.92 | -364.42 | 255.72 | 0.38 |  | -13.59 | -444.4 | 0.37 |  | -0.42 | 95
4669 | 12.23 | 145.75 | 4630.77 | -381.22 | 266.75 | 0.42 |  | -86.63 | -464.41 | 0.03 |  | -1.99 | 95
4763 | 11.92 | 143.2 | 4722.69 | -397.22 | 278.17 | 0.66 |  | -121.41 | -484.05 | -0.33 |  | -2.71 | 94
4856 | 11.12 | 144.2 | 4813.81 | -412.19 | 289.17 | 0.89 |  | 166.47 | -502.61 | -0.86 |  | 1.08 | 93
4951 | 10.82 | 142.76 | 4907.08 | -426.72 | 299.93 | 0.43 |  | -138.3 | -520.67 | -0.32 |  | -1.52 | 95
5045 | 10.49 | 142.08 | 4999.46 | -440.49 | 310.53 | 0.38 |  | -159.48 | -538.05 | -0.35 |  | -0.72 | 94
5138 | 9.89 | 140.62 | 5090.99 | -453.34 | 320.8 | 0.7 |  | -157.43 | -554.5 | -0.65 |  | -1.57 | 93
5232 | 9.58 | 137.6 | 5183.64 | -465.36 | 331.19 | 0.64 |  | -122.74 | -570.38 | -0.33 |  | -3.21 | 94
5326 | 9.94 | 139.75 | 5276.28 | -477.33 | 341.71 | 0.54 |  | 46.42 | -586.29 | 0.38 |  | 2.29 | 94
5420 | 10.35 | 143.5 | 5368.81 | -490.31 | 351.97 | 0.83 |  | 60.03 | -602.84 | 0.44 |  | 3.99 | 94
5514 | 9.86 | 142.9 | 5461.35 | -503.52 | 361.85 | 0.53 |  | -168.17 | -619.32 | -0.52 |  | -0.64 | 94
5607 | 10.21 | 142 | 5552.93 | -516.36 | 371.73 | 0.41 |  | -24.58 | -635.53 | 0.38 |  | -0.97 | 93
5700 | 10.45 | 140.65 | 5644.42 | -529.38 | 382.15 | 0.37 |  | -45.91 | -652.2 | 0.26 |  | -1.45 | 93
5794 | 9.18 | 140.68 | 5737.04 | -541.77 | 392.31 | 1.35 |  | 179.78 | -668.22 | -1.35 |  | 0.03 | 94
5888 | 8.05 | 137.83 | 5829.98 | -552.45 | 401.48 | 1.28 |  | -160.71 | -682.29 | -1.2 |  | -3.03 | 94
5982 | 8.54 | 136.98 | 5923 | -562.43 | 410.66 | 0.54 |  | -14.47 | -695.82 | 0.52 |  | -0.9 | 94
6076 | 9.84 | 137.24 | 6015.79 | -573.43 | 420.87 | 1.38 |  | 1.96 | -710.78 | 1.38 |  | 0.28 | 94
6169 | 9.94 | 140.35 | 6107.41 | -585.45 | 431.39 | 0.58 |  | 80.93 | -726.73 | 0.11 |  | 3.34 | 93
6263 | 8.91 | 138.58 | 6200.14 | -597.15 | 441.38 | 1.14 |  | -165.15 | -742.11 | -1.1 |  | -1.88 | 94
6357 | 8.5 | 134.86 | 6293.05 | -607.51 | 451.12 | 0.74 |  | -127.89 | -756.28 | -0.44 |  | -3.96 | 94
6452 | 8.28 | 137.71 | 6387.04 | -617.53 | 460.7 | 0.5 |  | 119.29 | -770.08 | -0.23 |  | 3 | 95
6546 | 8.32 | 135.25 | 6480.05 | -627.36 | 470.05 | 0.38 |  | -84.79 | -783.6 | 0.04 |  | -2.62 | 94
6640 | 7.96 | 136.43 | 6573.11 | -636.91 | 479.32 | 0.42 |  | 155.69 | -796.84 | -0.38 |  | 1.26 | 94
6734 | 8.41 | 141.21 | 6666.15 | -646.98 | 488.11 | 0.87 |  | 58.91 | -810.2 | 0.48 |  | 5.09 | 94
6828 | 9.14 | 150.58 | 6759.05 | -658.84 | 496.09 | 1.7 |  | 67.63 | -824.45 | 0.78 |  | 9.97 | 94
6922 | 10.81 | 149.87 | 6851.63 | -672.97 | 504.18 | 1.78 |  | -4.56 | -840.54 | 1.78 |  | -0.76 | 94
7016 | 10.62 | 148.93 | 6943.99 | -688.02 | 513.07 | 0.27 |  | -137.85 | -857.85 | -0.2 |  | -1 | 94
7110 | 10.54 | 146.43 | 7036.39 | -702.6 | 522.3 | 0.5 |  | -101.11 | -875.01 | -0.09 |  | -2.66 | 94
7204 | 10.11 | 144.91 | 7128.87 | -716.51 | 531.8 | 0.54 |  | -148.39 | -891.81 | -0.46 |  | -1.62 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 270.4 | 29.11 | 78.37 | 220 | 852.74 | 4438.71 | 3741.94 | 0 | 161.13 | 150.89 | 140.73 | 8837.21 | 0
Run | 270.4 | 29.11 | 78.37 | 220 | 852.74 | 4438.71 | 3741.94 | 0 | 161.13 | 150.89 | 140.73 | 8837.21 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/29/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/29/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/29/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/29/2021 | 00:00 | 00:30 | 0.5 | 3514 | 3514 | 0 | INT | 2: BHA 2 | 6L | Pick up BHA #2
07/29/2021 | 00:30 | 05:40 | 5.17 | 3514 | 3514 | 0 | INT | 2: BHA 2 | 6A | TIH t/3321
07/29/2021 | 05:40 | 06:15 | 0.58 | 3514 | 3514 | 0 | INT | 2: BHA 2 | 5A | Drill cement
07/29/2021 | 06:15 | 06:50 | 0.58 | 3514 | 3514 | 0 | INT | 2: BHA 2 | 15D | FIT
07/29/2021 | 06:50 | 07:08 | 0.3 | 3514 | 3606 | 92 | INT | 2: BHA 2 | 2K | Rotary Drill f/3514.00 t/3606.00, w/WOB 25.00,Flow 520.00, RPM 30.00, Press 1900.00, Tq 7000.00, ROP 306.67, Diff 400.00, Temp 124.00
07/29/2021 | 07:08 | 07:16 | 0.13 | 3606 | 3616 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/3606.00 t/3616.00, TF 30.00G, w/WOB 20.00,Flow 650.00, Press 2400.00, Tq 7000.00, ROP 75.00, Diff 500.00, Temp 124.00
07/29/2021 | 07:16 | 07:26 | 0.17 | 3616 | 3700 | 84 | INT | 2: BHA 2 | 2K | Rotary Drill f/3616.00 t/3700.00, w/WOB 25.00,Flow 650.00, RPM 60.00, Press 2400.00, Tq 7000.00, ROP 504.00, Diff 500.00, Temp 124.00
07/29/2021 | 07:26 | 07:30 | 0.07 | 3700 | 3700 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 07:30 | 07:40 | 0.17 | 3700 | 3710 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/3700.00 t/3710.00, TF 30.00G, w/WOB 20.00,Flow 850.00, Press 4000.00, Tq 7000.00, ROP 60.00, Diff 400.00, Temp 124.00
07/29/2021 | 07:40 | 07:48 | 0.13 | 3710 | 3793 | 83 | INT | 2: BHA 2 | 2K | Rotary Drill f/3710.00 t/3793.00, w/WOB 25.00,Flow 850.00, RPM 80.00, Press 4000.00, Tq 7000.00, ROP 622.50, Diff 400.00, Temp 124.00
07/29/2021 | 07:48 | 07:52 | 0.07 | 3793 | 3793 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 07:52 | 08:00 | 0.13 | 3793 | 3808 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3793.00 t/3808.00, TF 30.00G, w/WOB 20.00,Flow 850.00, Press 4000.00, Tq 7000.00, ROP 112.50, Diff 400.00, Temp 124.00
07/29/2021 | 08:00 | 08:07 | 0.12 | 3808 | 3887 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/3808.00 t/3887.00, w/WOB 25.00,Flow 850.00, RPM 80.00, Press 4000.00, Tq 7000.00, ROP 677.14, Diff 400.00, Temp 124.00
07/29/2021 | 08:07 | 08:11 | 0.07 | 3887 | 3887 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 08:11 | 08:21 | 0.17 | 3887 | 3902 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3887.00 t/3902.00, TF 0.00G, w/WOB 20.00,Flow 850.00, Press 4000.00, Tq 7000.00, ROP 90.00, Diff 400.00, Temp 124.00
07/29/2021 | 08:21 | 08:30 | 0.15 | 3902 | 3981 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/3902.00 t/3981.00, w/WOB 20.00,Flow 850.00, RPM 80.00, Press 4000.00, Tq 7000.00, ROP 526.67, Diff 400.00, Temp 124.00
07/29/2021 | 08:30 | 08:34 | 0.07 | 3981 | 3981 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 08:34 | 08:47 | 0.22 | 3981 | 3996 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3981.00 t/3996.00, TF 0.00G, w/WOB 20.00,Flow 850.00, Press 4000.00, Tq 7000.00, ROP 69.23, Diff 400.00, Temp 124.00
07/29/2021 | 08:47 | 08:56 | 0.15 | 3996 | 4075 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/3996.00 t/4075.00, w/WOB 30.00,Flow 850.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 526.67, Diff 600.00, Temp 130.00
07/29/2021 | 08:56 | 09:00 | 0.07 | 4075 | 4075 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 09:00 | 09:06 | 0.1 | 4075 | 4169 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4075.00 t/4169.00, w/WOB 30.00,Flow 850.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 940.00, Diff 600.00, Temp 130.00
07/29/2021 | 09:06 | 09:10 | 0.07 | 4169 | 4169 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 09:10 | 09:17 | 0.12 | 4169 | 4263 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4169.00 t/4263.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 805.71, Diff 600.00, Temp 153.00
07/29/2021 | 09:17 | 09:21 | 0.07 | 4263 | 4263 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 09:21 | 09:29 | 0.13 | 4263 | 4356 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4263.00 t/4356.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 697.50, Diff 600.00, Temp 153.00
07/29/2021 | 09:29 | 09:33 | 0.07 | 4356 | 4356 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 09:33 | 09:42 | 0.15 | 4356 | 4450 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4356.00 t/4450.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 626.67, Diff 600.00, Temp 153.00
07/29/2021 | 09:42 | 09:46 | 0.07 | 4450 | 4450 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 09:46 | 09:53 | 0.12 | 4450 | 4465 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4450.00 t/4465.00, TF 0.00G, w/WOB 20.00,Flow 875.00, Press 4400.00, Tq 9000.00, ROP 128.57, Diff 600.00, Temp 153.00
07/29/2021 | 09:53 | 10:02 | 0.15 | 4465 | 4543 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/4465.00 t/4543.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 520.00, Diff 600.00, Temp 160.00
07/29/2021 | 10:02 | 10:06 | 0.07 | 4543 | 4543 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 10:06 | 10:15 | 0.15 | 4543 | 4638 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4543.00 t/4638.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4600.00, Tq 9000.00, ROP 633.33, Diff 600.00, Temp 160.00
07/29/2021 | 10:15 | 10:19 | 0.07 | 4638 | 4638 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 10:19 | 10:28 | 0.15 | 4638 | 4733 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4638.00 t/4733.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4600.00, Tq 9000.00, ROP 633.33, Diff 600.00, Temp 160.00
07/29/2021 | 10:28 | 10:32 | 0.07 | 4733 | 4733 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 10:32 | 10:39 | 0.12 | 4733 | 4827 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4733.00 t/4827.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4600.00, Tq 9000.00, ROP 805.71, Diff 600.00, Temp 160.00
07/29/2021 | 10:39 | 10:43 | 0.07 | 4827 | 4827 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 10:43 | 10:51 | 0.13 | 4827 | 4920 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4827.00 t/4920.00, w/WOB 35.00,Flow 875.00, RPM 80.00, Press 4600.00, Tq 9000.00, ROP 697.50, Diff 600.00, Temp 169.00
07/29/2021 | 10:51 | 10:55 | 0.07 | 4920 | 4920 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 10:55 | 11:04 | 0.15 | 4920 | 5015 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4920.00 t/5015.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 633.33, Diff 800.00, Temp 172.00
07/29/2021 | 11:04 | 11:08 | 0.07 | 5015 | 5015 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 11:08 | 11:17 | 0.15 | 5015 | 5109 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5015.00 t/5109.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 626.67, Diff 800.00, Temp 174.00
07/29/2021 | 11:17 | 11:21 | 0.07 | 5109 | 5109 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 11:21 | 11:32 | 0.18 | 5109 | 5202 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5109.00 t/5202.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 3300.00, Tq 11000.00, ROP 507.27, Diff 600.00, Temp 174.00
07/29/2021 | 11:32 | 11:36 | 0.07 | 5202 | 5202 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 11:36 | 11:47 | 0.18 | 5202 | 5296 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5202.00 t/5296.00, w/WOB 35.00,Flow 700.00, RPM 80.00, Press 3300.00, Tq 10000.00, ROP 512.73, Diff 600.00, Temp 174.00
07/29/2021 | 11:47 | 11:51 | 0.07 | 5296 | 5296 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 11:51 | 12:01 | 0.17 | 5296 | 5311 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5296.00 t/5311.00, TF 30.00G, w/WOB 20.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 90.00, Diff 800.00, Temp 174.00
07/29/2021 | 12:01 | 12:11 | 0.17 | 5311 | 5390 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5311.00 t/5390.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 474.00, Diff 800.00, Temp 174.00
07/29/2021 | 12:11 | 12:15 | 0.07 | 5390 | 5390 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 12:15 | 12:25 | 0.17 | 5390 | 5405 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5390.00 t/5405.00, TF 30.00G, w/WOB 20.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 90.00, Diff 800.00, Temp 174.00
07/29/2021 | 12:25 | 12:34 | 0.15 | 5405 | 5484 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5405.00 t/5484.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 526.67, Diff 800.00, Temp 174.00
07/29/2021 | 12:34 | 12:38 | 0.07 | 5484 | 5484 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 12:38 | 12:47 | 0.15 | 5484 | 5578 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5484.00 t/5578.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 626.67, Diff 800.00, Temp 174.00
07/29/2021 | 12:47 | 12:51 | 0.07 | 5578 | 5578 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 12:51 | 12:59 | 0.13 | 5578 | 5671 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5578.00 t/5671.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 697.50, Diff 800.00, Temp 174.00
07/29/2021 | 12:59 | 13:03 | 0.07 | 5671 | 5671 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 13:03 | 13:12 | 0.15 | 5671 | 5764 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5671.00 t/5764.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 620.00, Diff 800.00, Temp 174.00
07/29/2021 | 13:12 | 13:16 | 0.07 | 5764 | 5764 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 13:16 | 13:24 | 0.13 | 5764 | 5858 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5764.00 t/5858.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 705.00, Diff 800.00, Temp 174.00
07/29/2021 | 13:24 | 13:28 | 0.07 | 5858 | 5858 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 13:28 | 13:36 | 0.13 | 5858 | 5952 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5858.00 t/5952.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 705.00, Diff 800.00, Temp 174.00
07/29/2021 | 13:36 | 13:40 | 0.07 | 5952 | 5952 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 13:40 | 13:50 | 0.17 | 5952 | 5967 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5952.00 t/5967.00, TF 30.00G, w/WOB 20.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 90.00, Diff 800.00, Temp 174.00
07/29/2021 | 13:50 | 13:58 | 0.13 | 5967 | 6046 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5967.00 t/6046.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 592.50, Diff 800.00, Temp 174.00
07/29/2021 | 13:58 | 14:02 | 0.07 | 6046 | 6046 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 14:02 | 14:12 | 0.17 | 6046 | 6061 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6046.00 t/6061.00, TF 30.00G, w/WOB 20.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 90.00, Diff 800.00, Temp 174.00
07/29/2021 | 14:12 | 14:22 | 0.17 | 6061 | 6140 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/6061.00 t/6140.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 474.00, Diff 800.00, Temp 174.00
07/29/2021 | 14:22 | 14:26 | 0.07 | 6140 | 6140 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 14:26 | 14:47 | 0.35 | 6140 | 6155 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6140.00 t/6155.00, TF 30.00G, w/WOB 20.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 42.86, Diff 800.00, Temp 174.00
07/29/2021 | 14:47 | 14:57 | 0.17 | 6155 | 6233 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/6155.00 t/6233.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 468.00, Diff 800.00, Temp 174.00
07/29/2021 | 14:57 | 15:01 | 0.07 | 6233 | 6233 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 15:01 | 15:21 | 0.33 | 6233 | 6248 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6233.00 t/6248.00, TF 30.00G, w/WOB 20.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 45.00, Diff 800.00, Temp 174.00
07/29/2021 | 15:21 | 15:29 | 0.13 | 6248 | 6327 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/6248.00 t/6327.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 592.50, Diff 800.00, Temp 174.00
07/29/2021 | 15:29 | 15:43 | 0.23 | 6327 | 6327 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 15:43 | 16:10 | 0.45 | 6327 | 6342 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6327.00 t/6342.00, TF 30.00G, w/WOB 25.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 33.33, Diff 800.00, Temp 174.00
07/29/2021 | 16:10 | 16:18 | 0.13 | 6342 | 6421 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/6342.00 t/6421.00, w/WOB 40.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 592.50, Diff 800.00, Temp 174.00
07/29/2021 | 16:18 | 16:22 | 0.07 | 6421 | 6421 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 16:22 | 16:55 | 0.55 | 6421 | 6436 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6421.00 t/6436.00, TF 30.00G, w/WOB 25.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 27.27, Diff 800.00, Temp 202.00
07/29/2021 | 16:55 | 17:08 | 0.22 | 6436 | 6516 | 80 | INT | 2: BHA 2 | 2K | Rotary Drill f/6436.00 t/6516.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 369.23, Diff 800.00, Temp 202.00
07/29/2021 | 17:08 | 17:40 | 0.53 | 6516 | 6516 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 17:40 | 17:50 | 0.17 | 6516 | 6535 | 19 | INT | 2: BHA 2 | 2K | Rotary Drill f/6516.00 t/6535.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 114.00, Diff 800.00, Temp 202.00
07/29/2021 | 17:50 | 18:30 | 0.67 | 6535 | 6547 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/6535.00 t/6547.00, TF 20.00G, w/WOB 25.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 18.00, Diff 800.00, Temp 202.00
07/29/2021 | 18:30 | 18:50 | 0.33 | 6547 | 6610 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/6547.00 t/6610.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 189.00, Diff 800.00, Temp 202.00
07/29/2021 | 18:50 | 18:55 | 0.08 | 6610 | 6610 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 18:55 | 19:00 | 0.08 | 6610 | 6625 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/6610.00 t/6625.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 180.00, Diff 800.00, Temp 202.00
07/29/2021 | 19:00 | 19:45 | 0.75 | 6625 | 6640 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6625.00 t/6640.00, TF 20.00G, w/WOB 25.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 20.00, Diff 800.00, Temp 202.00
07/29/2021 | 19:45 | 19:55 | 0.17 | 6640 | 6715 | 75 | INT | 2: BHA 2 | 2K | Rotary Drill f/6640.00 t/6715.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 450.00, Diff 800.00, Temp 202.00
07/29/2021 | 19:55 | 20:00 | 0.08 | 6715 | 6715 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 20:00 | 20:45 | 0.75 | 6715 | 6735 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/6715.00 t/6735.00, TF 20.00G, w/WOB 25.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 26.67, Diff 800.00, Temp 202.00
07/29/2021 | 20:45 | 21:05 | 0.33 | 6735 | 6798 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/6735.00 t/6798.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 189.00, Diff 800.00, Temp 202.00
07/29/2021 | 21:05 | 21:10 | 0.08 | 6798 | 6798 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 21:10 | 21:15 | 0.08 | 6798 | 6810 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6798.00 t/6810.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 144.00, Diff 800.00, Temp 202.00
07/29/2021 | 21:15 | 21:50 | 0.58 | 6810 | 6828 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/6810.00 t/6828.00, TF 0.00G, w/WOB 25.00,Flow 875.00, Press 4800.00, Tq 9000.00, ROP 30.86, Diff 800.00, Temp 202.00
07/29/2021 | 21:50 | 22:20 | 0.5 | 6828 | 6905 | 77 | INT | 2: BHA 2 | 2K | Rotary Drill f/6828.00 t/6905.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4800.00, Tq 9000.00, ROP 154.00, Diff 800.00, Temp 202.00
07/29/2021 | 22:20 | 22:25 | 0.08 | 6905 | 6905 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 22:25 | 22:50 | 0.42 | 6905 | 6912 | 7 | INT | 2: BHA 2 | 2J | Slide Drill f/6905.00 t/6912.00, TF -30.00G, w/WOB 25.00,Flow 875.00, Press 4300.00, Tq 9000.00, ROP 16.80, Diff 800.00, Temp 210.00
07/29/2021 | 22:50 | 23:05 | 0.25 | 6912 | 6986 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/6912.00 t/6986.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 296.00, Diff 800.00, Temp 210.00
07/29/2021 | 23:05 | 23:10 | 0.08 | 6986 | 6986 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 23:10 | 23:25 | 0.25 | 6986 | 7080 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6986.00 t/7080.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 376.00, Diff 800.00, Temp 210.00
07/29/2021 | 23:25 | 23:30 | 0.08 | 7080 | 7080 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 23:30 | 23:40 | 0.17 | 7080 | 7174 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7080.00 t/7174.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 564.00, Diff 800.00, Temp 210.00
07/29/2021 | 23:40 | 23:45 | 0.08 | 7174 | 7174 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/29/2021 | 23:45 | 24:00 | 0.25 | 7174 | 7268 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7174.00 t/7268.00, w/WOB 25.00,Flow 875.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 376.00, Diff 800.00, Temp 210.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_30_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/30/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 53530
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Drill ahead in vertical section
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 7268 |  | 3514 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 10308 |  | 10308 |  | OD (in): |  |  |  | 300: | 25 | YP: | 9
Total Drilled (Usft): |  | 3040 |  | 6794 |  | Weight (ft/lbs): |  |  |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 291 |  | 563 | [5 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): |  | 2749 |  | 6231 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: |  | 20.35 / 3.65 |  | 34.23 / 7.52 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 11.88 |  | 18.33 |  | SN: |  | 55308 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  | 8.47 |  | 15.9 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 324.69 / 24.49 |  | 391.89 / 30.71 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 48 |  | Grade In: |  | New
% Slide: |  | 9.57 |  | 8.29 |  | Grade Out:
% Rotary: |  | 90.43 |  | 91.71 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.013 |  |  |  | 8 | 2 |  |  | 100 |  | 38.05 |  | 39.55
NMPC |  |  |  | 8 | 3.125 |  |  | 150 |  | 9.01 |  | 48.56
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.73 |  | 52.29
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.84 |  | 82.13
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.58 |  | 111.71
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 3.06 |  | 114.77
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 302
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 304.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 579.52
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2641.22
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.61 |  | 2665.83
2665.83
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
7297 | 9.73 | 144.79 | 7220.48 | -729.61 | 541.02 | 0.41 |  | -176.95 | -907.8 | -0.41 |  | -0.13 | 93
7391 | 9.56 | 142.3 | 7313.15 | -742.28 | 550.37 | 0.48 |  | -113.39 | -923.54 | -0.18 |  | -2.65 | 94
7486 | 9.32 | 139.8 | 7406.87 | -754.4 | 560.16 | 0.5 |  | -121.57 | -939.12 | -0.25 |  | -2.63 | 95
7581 | 8.45 | 138.52 | 7500.73 | -765.5 | 569.75 | 0.94 |  | -167.83 | -953.78 | -0.92 |  | -1.35 | 95
7675 | 9.38 | 141.1 | 7593.59 | -776.64 | 579.14 | 1.08 |  | 24.54 | -968.33 | 0.99 |  | 2.74 | 94
7768 | 8.56 | 141.52 | 7685.45 | -787.95 | 588.2 | 0.88 |  | 175.64 | -982.83 | -0.88 |  | 0.45 | 93
7861 | 8.1 | 140.75 | 7777.47 | -798.45 | 596.65 | 0.51 |  | -166.75 | -996.31 | -0.49 |  | -0.83 | 93
7955 | 8.71 | 136.04 | 7870.46 | -808.7 | 605.78 | 0.98 |  | -50.8 | -1010.01 | 0.65 |  | -5.01 | 94
8049 | 7.67 | 139.11 | 7963.5 | -818.56 | 614.83 | 1.2 |  | 158.71 | -1023.37 | -1.11 |  | 3.27 | 94
8144 | 8.05 | 142.22 | 8057.61 | -828.61 | 623.06 | 0.6 |  | 49.77 | -1036.35 | 0.4 |  | 3.27 | 95
8237 | 6.69 | 141.6 | 8149.84 | -838.01 | 630.41 | 1.46 |  | -176.96 | -1048.28 | -1.46 |  | -0.67 | 93
8331 | 6.14 | 141.12 | 8243.25 | -846.21 | 636.97 | 0.59 |  | -174.67 | -1058.78 | -0.59 |  | -0.51 | 94
8426 | 7.14 | 142.84 | 8337.61 | -854.87 | 643.72 | 1.07 |  | 12.1 | -1069.77 | 1.05 |  | 1.81 | 95
8520 | 6.83 | 140.84 | 8430.91 | -863.86 | 650.78 | 0.42 |  | -142.87 | -1081.19 | -0.33 |  | -2.13 | 94
8614 | 5.41 | 141.48 | 8524.38 | -871.66 | 657.07 | 1.51 |  | 177.57 | -1091.22 | -1.51 |  | 0.68 | 94
8709 | 3.83 | 143.04 | 8619.06 | -877.7 | 661.77 | 1.67 |  | 176.23 | -1098.87 | -1.66 |  | 1.64 | 95
8802 | 2.95 | 148.19 | 8711.9 | -882.22 | 664.9 | 1 |  | 163.47 | -1104.35 | -0.95 |  | 5.54 | 93
8897 | 3.59 | 159.43 | 8806.75 | -887.08 | 667.23 | 0.95 |  | 50.75 | -1109.61 | 0.67 |  | 11.83 | 95
8990 | 2.17 | 164.15 | 8899.63 | -891.5 | 668.73 | 1.55 |  | 172.87 | -1114 | -1.53 |  | 5.08 | 93
9084 | 1.25 | 173.22 | 8993.58 | -894.23 | 669.34 | 1.02 |  | 168.11 | -1116.52 | -0.98 |  | 9.65 | 94
9178 | 0.94 | 211.03 | 9087.57 | -895.91 | 669.07 | 0.82 |  | 131.36 | -1117.66 | -0.33 |  | 0 | 94
9272 | 0.98 | 212.51 | 9181.55 | -897.25 | 668.24 | 0.05 |  | 32.54 | -1118.19 | 0.04 |  | 0 | 94
9365 | 1.21 | 241.29 | 9274.54 | -898.39 | 666.95 | 0.63 |  | 82.13 | -1118.28 | 0.25 |  | 0 | 93
9459 | 2.49 | 272.95 | 9368.49 | -898.76 | 664.04 | 1.69 |  | 55.16 | -1116.76 | 1.36 |  | 0 | 94
9553 | 3.69 | 279.06 | 9462.35 | -898.18 | 659.01 | 1.32 |  | 18.41 | -1113.18 | 1.28 |  | 6.5 | 94
9647 | 4.96 | 290.49 | 9556.08 | -896.28 | 652.22 | 1.63 |  | 39.95 | -1107.47 | 1.35 |  | 12.16 | 94
9740 | 4.58 | 297.07 | 9648.76 | -893.18 | 645.14 | 0.72 |  | 128.03 | -1100.64 | -0.41 |  | 7.08 | 93
9834 | 3.9 | 293.57 | 9742.5 | -890.2 | 638.87 | 0.77 |  | -160.91 | -1094.4 | -0.72 |  | -3.72 | 94
9928 | 3.09 | 294.81 | 9836.33 | -887.86 | 633.64 | 0.87 |  | 175.29 | -1089.31 | -0.86 |  | 1.32 | 94
10021 | 2.34 | 297.94 | 9929.22 | -885.91 | 629.69 | 0.82 |  | 170.38 | -1085.34 | -0.81 |  | 3.37 | 93
10115 | 2 | 303.57 | 10023.16 | -884.11 | 626.63 | 0.43 |  | 150.7 | -1082.02 | -0.36 |  | 5.99 | 94
10209 | 2.13 | 306.82 | 10117.1 | -882.15 | 623.86 | 0.19 |  | 43.65 | -1078.77 | 0.14 |  | 3.46 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 149.39 | 32.59 | 80 | 217 | 825 | 4792.59 | 3992.59 | 0 | 243.7 | 218.43 | 198.43 | 15157.89 | 0
Run | 198.46 | 30.73 | 79.14 | 218 | 837.67 | 4603.45 | 3858.62 | 0 | 201.98 | 184.57 | 169.48 | 11802.47 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/30/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/30/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/30/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/30/2021 | 00:00 | 00:05 | 0.08 | 7268 | 7268 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 00:05 | 00:20 | 0.25 | 7268 | 7361 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7268.00 t/7361.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 372.00, Diff 800.00, Temp 210.00
07/30/2021 | 00:20 | 00:25 | 0.08 | 7361 | 7361 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 00:25 | 00:30 | 0.08 | 7361 | 7372 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/7361.00 t/7372.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 132.00, Diff 800.00, Temp 210.00
07/30/2021 | 00:30 | 00:45 | 0.25 | 7372 | 7382 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/7372.00 t/7382.00, TF -20G, w/WOB 25.00,Flow 825.00, Press 4300.00, Tq 9000.00, ROP 40.00, Diff 800.00, Temp 210.00
07/30/2021 | 00:45 | 01:00 | 0.25 | 7382 | 7455 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/7382.00 t/7455.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 292.00, Diff 800.00, Temp 210.00
07/30/2021 | 01:00 | 01:05 | 0.08 | 7455 | 7455 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 01:05 | 01:10 | 0.08 | 7455 | 7465 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7455.00 t/7465.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 120.00, Diff 800.00, Temp 210.00
07/30/2021 | 01:10 | 01:45 | 0.58 | 7465 | 7477 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7465.00 t/7477.00, TF 0G, w/WOB 25.00,Flow 825.00, Press 4300.00, Tq 9000.00, ROP 20.57, Diff 800.00, Temp 210.00
07/30/2021 | 01:45 | 02:00 | 0.25 | 7477 | 7550 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/7477.00 t/7550.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 292.00, Diff 800.00, Temp 210.00
07/30/2021 | 02:00 | 02:05 | 0.08 | 7550 | 7550 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 02:05 | 02:10 | 0.08 | 7550 | 7565 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/7550.00 t/7565.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 180.00, Diff 800.00, Temp 210.00
07/30/2021 | 02:10 | 02:50 | 0.67 | 7565 | 7577 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7565.00 t/7577.00, TF 0G, w/WOB 25.00,Flow 825.00, Press 4300.00, Tq 9000.00, ROP 18.00, Diff 800.00, Temp 210.00
07/30/2021 | 02:50 | 03:05 | 0.25 | 7577 | 7645 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/7577.00 t/7645.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 272.00, Diff 800.00, Temp 210.00
07/30/2021 | 03:05 | 03:10 | 0.08 | 7645 | 7645 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 03:10 | 03:15 | 0.08 | 7645 | 7655 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7645.00 t/7655.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 120.00, Diff 800.00, Temp 210.00
07/30/2021 | 03:15 | 03:50 | 0.58 | 7655 | 7675 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7655.00 t/7675.00, TF 0G, w/WOB 25.00,Flow 825.00, Press 4300.00, Tq 9000.00, ROP 34.29, Diff 800.00, Temp 210.00
07/30/2021 | 03:50 | 04:00 | 0.17 | 7675 | 7739 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/7675.00 t/7739.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 384.00, Diff 800.00, Temp 210.00
07/30/2021 | 04:00 | 04:05 | 0.08 | 7739 | 7739 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 04:05 | 04:20 | 0.25 | 7739 | 7832 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7739.00 t/7832.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 372.00, Diff 800.00, Temp 210.00
07/30/2021 | 04:20 | 04:25 | 0.08 | 7832 | 7832 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 04:25 | 04:30 | 0.08 | 7832 | 7845 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/7832.00 t/7845.00, w/WOB 25.00,Flow 825.00, RPM 80.00, Press 4300.00, Tq 9000.00, ROP 156.00, Diff 800.00, Temp 210.00
07/30/2021 | 04:30 | 05:00 | 0.5 | 7845 | 7855 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/7845.00 t/7855.00, TF 0G, w/WOB 25.00,Flow 825.00, Press 4300.00, Tq 9000.00, ROP 20.00, Diff 800.00, Temp 210.00
07/30/2021 | 05:00 | 05:25 | 0.42 | 7855 | 7925 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/7855.00 t/7925.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 9000.00, ROP 168.00, Diff 800.00, Temp 221.00
07/30/2021 | 05:25 | 05:30 | 0.08 | 7925 | 7925 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 05:30 | 05:35 | 0.08 | 7925 | 7935 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/7925.00 t/7935.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 120.00, Diff 800.00, Temp 221.00
07/30/2021 | 05:35 | 06:34 | 0.98 | 7935 | 7955 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/7935.00 t/7955.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 20.34, Diff 800.00, Temp 221.00
07/30/2021 | 06:34 | 06:44 | 0.17 | 7955 | 8019 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/7955.00 t/8019.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 384.00, Diff 800.00, Temp 221.00
07/30/2021 | 06:44 | 06:48 | 0.07 | 8019 | 8019 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 06:48 | 07:35 | 0.78 | 8019 | 8034 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8019.00 t/8034.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 19.15, Diff 800.00, Temp 221.00
07/30/2021 | 07:35 | 07:48 | 0.22 | 8034 | 8113 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/8034.00 t/8113.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 364.62, Diff 800.00, Temp 221.00
07/30/2021 | 07:48 | 07:52 | 0.07 | 8113 | 8113 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 07:52 | 08:11 | 0.32 | 8113 | 8133 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8113.00 t/8133.00, TF 0.00G, w/WOB 40.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 63.16, Diff 800.00, Temp 221.00
07/30/2021 | 08:11 | 08:25 | 0.23 | 8133 | 8208 | 75 | INT | 2: BHA 2 | 2K | Rotary Drill f/8133.00 t/8208.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 321.43, Diff 800.00, Temp 221.00
07/30/2021 | 08:25 | 09:44 | 1.32 | 8208 | 8208 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 09:44 | 10:07 | 0.38 | 8208 | 8228 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8208.00 t/8228.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 52.17, Diff 800.00, Temp 221.00
07/30/2021 | 10:07 | 10:19 | 0.2 | 8228 | 8301 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/8228.00 t/8301.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 365.00, Diff 800.00, Temp 221.00
07/30/2021 | 10:19 | 10:23 | 0.07 | 8301 | 8301 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 10:23 | 10:58 | 0.58 | 8301 | 8316 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8301.00 t/8316.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 25.71, Diff 800.00, Temp 221.00
07/30/2021 | 10:58 | 11:10 | 0.2 | 8316 | 8395 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/8316.00 t/8395.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 395.00, Diff 800.00, Temp 221.00
07/30/2021 | 11:10 | 11:14 | 0.07 | 8395 | 8395 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 11:14 | 11:42 | 0.47 | 8395 | 8415 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8395.00 t/8415.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 42.86, Diff 800.00, Temp 221.00
07/30/2021 | 11:42 | 11:56 | 0.23 | 8415 | 8490 | 75 | INT | 2: BHA 2 | 2K | Rotary Drill f/8415.00 t/8490.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 321.43, Diff 800.00, Temp 221.00
07/30/2021 | 11:56 | 12:00 | 0.07 | 8490 | 8490 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 12:00 | 12:25 | 0.42 | 8490 | 8505 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8490.00 t/8505.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 36.00, Diff 800.00, Temp 221.00
07/30/2021 | 12:25 | 12:38 | 0.22 | 8505 | 8584 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/8505.00 t/8584.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 364.62, Diff 800.00, Temp 221.00
07/30/2021 | 12:38 | 12:42 | 0.07 | 8584 | 8584 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 12:42 | 12:56 | 0.23 | 8584 | 8678 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8584.00 t/8678.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 402.86, Diff 800.00, Temp 221.00
07/30/2021 | 12:56 | 13:00 | 0.07 | 8678 | 8678 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 13:00 | 13:11 | 0.18 | 8678 | 8773 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8678.00 t/8773.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 518.18, Diff 800.00, Temp 221.00
07/30/2021 | 13:11 | 13:15 | 0.07 | 8773 | 8773 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 13:15 | 13:28 | 0.22 | 8773 | 8866 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8773.00 t/8866.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 429.23, Diff 800.00, Temp 221.00
07/30/2021 | 13:28 | 13:32 | 0.07 | 8866 | 8866 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 13:32 | 13:43 | 0.18 | 8866 | 8961 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8866.00 t/8961.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 518.18, Diff 800.00, Temp 221.00
07/30/2021 | 13:43 | 13:47 | 0.07 | 8961 | 8961 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 13:47 | 13:57 | 0.17 | 8961 | 9034 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/8961.00 t/9034.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 438.00, Diff 800.00, Temp 221.00
07/30/2021 | 13:57 | 14:54 | 0.95 | 9034 | 9054 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9034.00 t/9054.00, TF 320.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 21.05, Diff 800.00, Temp 221.00
07/30/2021 | 14:54 | 14:58 | 0.07 | 9054 | 9054 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 14:58 | 15:11 | 0.22 | 9054 | 9148 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9054.00 t/9148.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 433.85, Diff 800.00, Temp 221.00
07/30/2021 | 15:11 | 15:15 | 0.07 | 9148 | 9148 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 15:15 | 15:26 | 0.18 | 9148 | 9242 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9148.00 t/9242.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 512.73, Diff 800.00, Temp 221.00
07/30/2021 | 15:26 | 15:30 | 0.07 | 9242 | 9242 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 15:30 | 16:00 | 0.5 | 9242 | 9257 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/9242.00 t/9257.00, TF 130.00M, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 30.00, Diff 800.00, Temp 221.00
07/30/2021 | 16:00 | 16:17 | 0.28 | 9257 | 9336 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/9257.00 t/9336.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 278.82, Diff 800.00, Temp 221.00
07/30/2021 | 16:17 | 16:21 | 0.07 | 9336 | 9336 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 16:21 | 16:32 | 0.18 | 9336 | 9429 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9336.00 t/9429.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 507.27, Diff 800.00, Temp 221.00
07/30/2021 | 16:32 | 16:36 | 0.07 | 9429 | 9429 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 16:36 | 16:48 | 0.2 | 9429 | 9523 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9429.00 t/9523.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 470.00, Diff 800.00, Temp 221.00
07/30/2021 | 16:48 | 16:52 | 0.07 | 9523 | 9523 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 16:52 | 17:03 | 0.18 | 9523 | 9617 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9523.00 t/9617.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 512.73, Diff 800.00, Temp 221.00
07/30/2021 | 17:03 | 17:07 | 0.07 | 9617 | 9617 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 17:07 | 17:28 | 0.35 | 9617 | 9711 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9617.00 t/9711.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 268.57, Diff 800.00, Temp 221.00
07/30/2021 | 17:28 | 17:32 | 0.07 | 9711 | 9711 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 17:32 | 17:46 | 0.23 | 9711 | 9804 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9711.00 t/9804.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 398.57, Diff 800.00, Temp 221.00
07/30/2021 | 17:46 | 17:50 | 0.07 | 9804 | 9804 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 17:50 | 18:03 | 0.22 | 9804 | 9898 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9804.00 t/9898.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 433.85, Diff 800.00, Temp 221.00
07/30/2021 | 18:03 | 18:07 | 0.07 | 9898 | 9898 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 18:07 | 18:30 | 0.38 | 9898 | 9992 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9898.00 t/9992.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 245.22, Diff 800.00, Temp 221.00
07/30/2021 | 18:30 | 18:35 | 0.08 | 9992 | 9992 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 18:35 | 19:00 | 0.42 | 9992 | 10085 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9992.00 t/10085.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 223.20, Diff 800.00, Temp 221.00
07/30/2021 | 19:00 | 19:05 | 0.08 | 10085 | 10085 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 19:05 | 19:40 | 0.58 | 10085 | 10179 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10085.00 t/10179.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 161.14, Diff 800.00, Temp 221.00
07/30/2021 | 19:40 | 19:45 | 0.08 | 10179 | 10179 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 19:45 | 20:00 | 0.25 | 10179 | 10241 | 62 | INT | 2: BHA 2 | 2K | Rotary Drill f/10179.00 t/10241.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 248.00, Diff 800.00, Temp 221.00
07/30/2021 | 20:00 | 22:00 | 2 | 10241 | 10273 | 32 | CRV | 2: BHA 2 | 2J | Slide Drill f/10241.00 t/10273.00, TF 325M, w/WOB 40.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 16.00, Diff 800.00, Temp 221.00
07/30/2021 | 22:00 | 22:05 | 0.08 | 10273 | 10273 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/30/2021 | 22:05 | 24:00 | 1.92 | 10273 | 10308 | 35 | CRV | 2: BHA 2 | 2J | Slide Drill f/10273.00 t/10308.00, TF 325M, w/WOB 40.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 18.26, Diff 800.00, Temp 221.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_31_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/31/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 60380
|  |  |  | 24hr Summary: |  | Drill to casing point, POOH, LD BHA
|  |  |  | 24hr Lookahead: |  | Run Casing, Skid Rig to Rommel 3H
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10308 |  | 3514 |  | Csg Shoe MD(Usft): |  | 3504 |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 11063 |  | 11063 |  | OD (in): |  | 10.75 |  | 300: | 25 | YP: | 9
Total Drilled (Usft): |  | 755 |  | 7549 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 547 |  | 1110 | [5 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): |  | 208 |  | 6439 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: |  | 14.75 / 1.93 |  | 48.98 / 9.45 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 12.07 |  | 30.4 |  | SN: |  | 55308 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  | 2.68 |  | 18.58 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 77.52 / 45.33 |  | 346.49 / 36.51 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 72 |  | Grade In: |  | New
% Slide: |  | 72.45 |  | 14.7 |  | Grade Out:
% Rotary: |  | 27.55 |  | 85.3 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | J. Taylor J. Ray |  | Jason Smetters |  | Peter Langille |  |  |  | BillTrey
James Dyer |  | Xavier Cantu |  | Chris Inman
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.013 |  |  |  | 8 | 2 |  |  | 100 |  | 38.05 |  | 39.55
NMPC |  |  |  | 8 | 3.125 |  |  | 150 |  | 9.01 |  | 48.56
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.73 |  | 52.29
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.84 |  | 82.13
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.58 |  | 111.71
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 3.06 |  | 114.77
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 302
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 304.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 579.52
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2641.22
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.61 |  | 2665.83
2665.83
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10302 | 5.75 | 315.91 | 10209.86 | -877.77 | 619.24 | 3.94 |  | 14.35 | -1072.46 | 3.89 |  | 9.77 | 93
10397 | 11.68 | 327.33 | 10303.73 | -866.25 | 610.73 | 6.47 |  | 21.98 | -1058.14 | 6.24 |  | 12.02 | 95
10491 | 12.96 | 332.93 | 10395.56 | -848.85 | 600.79 | 1.86 |  | 45.79 | -1038.34 | 1.36 |  | 5.96 | 94
10585 | 14.53 | 332.42 | 10486.87 | -829.01 | 590.54 | 1.68 |  | -4.66 | -1016.43 | 1.67 |  | -0.54 | 94
10679 | 20.95 | 334.63 | 10576.35 | -803.35 | 577.86 | 6.87 |  | 7.05 | -988.45 | 6.83 |  | 2.35 | 94
10773 | 25.26 | 337.89 | 10662.8 | -769.56 | 563.11 | 4.78 |  | 18.04 | -952.82 | 4.59 |  | 3.47 | 94
10866 | 30.1 | 339.29 | 10745.13 | -729.34 | 547.38 | 5.25 |  | 8.28 | -911.55 | 5.2 |  | 1.51 | 93
10960 | 36.06 | 333.87 | 10823.88 | -682.4 | 526.84 | 7.07 |  | -28.7 | -862.02 | 6.34 |  | -5.77 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 51.19 | 40 | 80 | 217 | 825 | 5000 | 4200 | 0 | 250 | 220 | 200 | 18000 | 0
Run | 154.11 | 31.04 | 79.16 | 218 | 837.25 | 4616.67 | 3870 | 0 | 203.58 | 185.75 | 170.5 | 11951.81 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/31/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/31/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/31/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/31/2021 | 00:00 | 01:35 | 1.58 | 10308 | 10366 | 58 | CRV | 2: BHA 2 | 2J | Slide Drill f/10308.00 t/10366.00, TF 325.00M, w/WOB 40.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 36.63, Diff 800.00, Temp 221.00
07/31/2021 | 01:35 | 01:40 | 0.08 | 10366 | 10366 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 01:40 | 02:55 | 1.25 | 10366 | 10386 | 20 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10366.00 t/10386.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 16.00, Diff 800.00, Temp 240.00
07/31/2021 | 02:55 | 04:15 | 1.33 | 10386 | 10457 | 71 | CRV | 2: BHA 2 | 2J | Slide Drill f/10386.00 t/10457.00, TF 0.00G, w/WOB 40.00,Flow 825.00, Press 5000.00, Tq 18000.00, ROP 53.25, Diff 800.00, Temp 240.00
07/31/2021 | 04:15 | 04:20 | 0.08 | 10457 | 10457 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 04:20 | 05:00 | 0.67 | 10457 | 10555 | 98 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10457.00 t/10555.00, w/WOB 40.00,Flow 825.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 147.00, Diff 800.00, Temp 240.00
07/31/2021 | 05:00 | 05:05 | 0.08 | 10555 | 10555 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 05:05 | 08:58 | 3.88 | 10555 | 10743 | 188 | CRV | 2: BHA 2 | 2J | Slide Drill f/10555.00 t/10743.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 5000.00, Tq 0.00, ROP 48.41, Diff 800.00, Temp 240.00
07/31/2021 | 08:58 | 09:02 | 0.07 | 10743 | 10743 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 09:02 | 09:17 | 0.25 | 10743 | 10781 | 38 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10743.00 t/10781.00, w/WOB 20.00,Flow 825.00, RPM 20.00, Press 5000.00, Tq 12000.00, ROP 152.00, Diff 800.00, Temp 240.00
07/31/2021 | 09:17 | 10:40 | 1.38 | 10781 | 10837 | 56 | CRV | 2: BHA 2 | 2J | Slide Drill f/10781.00 t/10837.00, TF 0.00G, w/WOB 20.00,Flow 825.00, Press 4600.00, Tq 0.00, ROP 40.48, Diff 400.00, Temp 240.00
07/31/2021 | 10:40 | 10:44 | 0.07 | 10837 | 10837 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 10:44 | 10:53 | 0.15 | 10837 | 10857 | 20 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10837.00 t/10857.00, w/WOB 25.00,Flow 825.00, RPM 20.00, Press 5100.00, Tq 16000.00, ROP 133.33, Diff 500.00, Temp 252.00
07/31/2021 | 10:53 | 12:12 | 1.32 | 10857 | 10930 | 73 | CRV | 2: BHA 2 | 2J | Slide Drill f/10857.00 t/10930.00, TF -30.00G, w/WOB 15.00,Flow 825.00, Press 4900.00, Tq 0.00, ROP 55.44, Diff 300.00, Temp 252.00
07/31/2021 | 12:12 | 12:15 | 0.05 | 10930 | 10930 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 12:15 | 12:22 | 0.12 | 10930 | 10942 | 12 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10930.00 t/10942.00, w/WOB 30.00,Flow 825.00, RPM 20.00, Press 5100.00, Tq 16000.00, ROP 102.86, Diff 500.00, Temp 252.00
07/31/2021 | 12:22 | 14:14 | 1.87 | 10942 | 11024 | 82 | CRV | 2: BHA 2 | 2J | Slide Drill f/10942.00 t/11024.00, TF -50.00G, w/WOB 15.00,Flow 825.00, Press 4900.00, Tq 0.00, ROP 43.93, Diff 300.00, Temp 252.00
07/31/2021 | 14:14 | 14:17 | 0.05 | 11024 | 11024 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/31/2021 | 14:17 | 14:32 | 0.25 | 11024 | 11044 | 20 | CRV | 2: BHA 2 | 2K | Rotary Drill f/11024.00 t/11044.00, w/WOB 35.00,Flow 825.00, RPM 20.00, Press 5100.00, Tq 16000.00, ROP 80.00, Diff 500.00, Temp 252.00
07/31/2021 | 14:32 | 15:14 | 0.7 | 11044 | 11063 | 19 | CRV | 2: BHA 2 | 2J | Slide Drill f/11044.00 t/11063.00, TF -30.00G, w/WOB 25.00,Flow 825.00, Press 4800.00, Tq 0.00, ROP 27.14, Diff 200.00, Temp 252.00
07/31/2021 | 15:14 | 15:17 | 0.05 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 5A | Survey
07/31/2021 | 15:17 | 16:36 | 1.32 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 5A | Circulate t/ POOH and run casing
07/31/2021 | 16:36 | 16:55 | 0.32 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 6I | Flow check
07/31/2021 | 16:55 | 17:00 | 0.08 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 5A | Pump slug
07/31/2021 | 17:00 | 23:30 | 6.5 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 6B | POOH
07/31/2021 | 23:30 | 24:00 | 0.5 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 6L | Lay down BHA
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_1_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/01/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4200 |  |  | Well Cost($): |  | 64580
|  |  |  | 24hr Summary: |  | Casing & cement operations
|  |  |  | 24hr Lookahead: |  | Casing & cement operations
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11063 |  | 3514 |  | Csg Shoe MD(Usft): |  | 3504 |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 11063 |  | 11063 |  | OD (in): |  | 10.75 |  | 300: | 25 | YP: | 9
Total Drilled (Usft): |  |  |  | 7549 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  |  |  | 1110 | [5 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): |  |  |  | 6439 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: |  |  |  | 48.98 / 9.45 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  |  |  | 30.4 |  | SN: |  | 55308 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  |  |  | 18.58 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 346.49 / 36.51 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 1 |  | 73 |  | Grade In: |  | New
% Slide: |  |  |  | 14.7 |  | Grade Out:
% Rotary: |  |  |  | 85.3 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  | Mike Chris |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Xavier Cantu |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.013 |  |  |  | 8 | 2 |  |  | 100 |  | 38.05 |  | 39.55
NMPC |  |  |  | 8 | 3.125 |  |  | 150 |  | 9.01 |  | 48.56
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.73 |  | 52.29
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.84 |  | 82.13
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 29.58 |  | 111.71
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 3.06 |  | 114.77
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 302
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 304.67
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 579.52
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2641.22
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.61 |  | 2665.83
2665.83
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 40 | 80 | 217 | 825 | 5000 | 4200 | 0 | 250 | 220 | 200 | 18000 | 0
Run | 154.11 | 31.04 | 79.16 | 218 | 837.25 | 4616.67 | 3870 | 0 | 203.58 | 185.75 | 170.5 | 11951.81 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 08/01/2021 |  | 5 |  | 100 |  | 4 | 400
STBY |  |  |  |  | 08/01/2021 |  | 2 |  | 3800 |  | 1 | 3800
Total | [11 empty] | 4200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/01/2021 | 00:00 | 01:00 | 1 | 11063 | 11063 | 0 | CRV | 2: BHA 2 | 6P | Finish laying down BHA #2
08/01/2021 | 01:00 | 24:00 | 23 | 11063 | 11063 | 0 | CRV |  | 24B | Stand by casing operations
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_10_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/10/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18450 |  |  | Well Cost($): |  | 83030
|  |  |  | 24hr Summary: |  | Standby
|  |  |  | 24hr Lookahead: |  | P/U BHA #3, TIH, Drill curve/lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11063 |  | 11063 |  | Csg Shoe MD(Usft): |  | 11053 |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 11511 |  | 11511 |  | OD (in): |  | 10.75 |  | 300: | 25 | YP: | 9
Total Drilled (Usft): |  | 448 |  | 448 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 394 |  | 394 | [5 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): |  | 54 |  | 54 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: |  | 5.83 / 4.17 |  | 5.83 / 4.17 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 5.17 |  | 5.17 |  | SN: |  | 13618580 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  | 0.67 |  | 0.67 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 81.00 / 76.26 |  | 81.00 / 76.26 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 17.75 |  | 17.75 |  | Grade In: |  | New
% Slide: |  | 87.95 |  | 87.95 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 12.05 |  | 12.05 |  | Make / Model: |  | Security / 1187517
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  | Mike Chris |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Jesse Taylor |  | Chris Inman | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 +.008 |  |  |  | 5.5 | 2 |  |  | 45.3 |  | 33.11 |  | 34.11
BTI Valve |  |  |  | 4.875 | 2 |  |  | 45.45 |  | 1.65 |  | 35.76
NMPC |  |  |  | 5 | 2.688 |  |  | 52.08 |  | 9.6 |  | 45.36
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 4 |  | 49.36
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 51.23 |  | 29.28 |  | 78.64
NMPC |  |  |  | 5 | 2.688 |  |  | 52.91 |  | 9.45 |  | 88.09
NMDC (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.83 |  | 30.72 |  | 118.81
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.92 |  | 136.73
Filter Sub |  |  |  | 4.75 | 2.875 |  |  | 50 |  | 5.55 |  | 142.28
Crossover |  |  |  | 5.25 | 2.688 |  |  | 44.51 |  | 3.37 |  | 145.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 333.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 341.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2796.16
Agitator |  |  |  | 5.312 | 2.688 |  |  | 56.05 |  | 21.41 |  | 2817.57
2817.57
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250019 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10999 | 38.78 | 331.38 | 10854.85 | -661.37 | 515.93 | 7.98 |  | -30.08 | -838.77 | 6.97 |  | -6.38 | 39
11096 | 43.19 | 327.65 | 10928.07 | -606.63 | 483.6 | 5.2 |  | -30.44 | -775.8 | 4.55 |  | -3.85 | 97
11159 | 46.84 | 327.36 | 10972.59 | -569.05 | 459.66 | 5.8 |  | -3.32 | -731.49 | 5.79 |  | -0.46 | 63
11254 | 57.45 | 329.48 | 11030.81 | -505.2 | 420.52 | 11.31 |  | 9.63 | -657.15 | 11.17 |  | 2.23 | 95
11348 | 67.25 | 329.88 | 11074.38 | -433.4 | 378.55 | 10.43 |  | 2.17 | -574.83 | 10.43 |  | 0.43 | 94
11443 | 72.5 | 323.69 | 11107.09 | -358.89 | 329.67 | 8.24 |  | -49.01 | -486.08 | 5.53 |  | -6.52 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 76.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 76.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 09/10/2021 |  | 14 |  | 2000 |  | 1 | 2000
Multi Rig Discount |  |  |  |  | 09/10/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/10/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 09/10/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 09/10/2021 |  | 10 |  | 600 |  | 1 | 600
5.5 Premium Motor Reline |  |  |  |  | 09/10/2021 |  | 9 |  | 9000 |  | 1 | 9000
Total | [11 empty] | 18450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/10/2021 | 00:00 | 04:15 | 4.25 | 11063 | 11063 | 0 | CRV2 |  | 24B | Standby on location
09/10/2021 | 04:15 | 06:15 | 2 | 11063 | 11063 | 0 | CRV2 | 3: BHA 3 | 6O | M/U BHA #3
09/10/2021 | 06:15 | 06:30 | 0.25 | 11063 | 11063 | 0 | CRV2 | 3: BHA 3 | 5A | Test MWD and motor
09/10/2021 | 06:30 | 13:45 | 7.25 | 11063 | 11063 | 0 | CRV2 | 3: BHA 3 | 6A | TIH t/ 10875 tag cement
09/10/2021 | 13:45 | 15:30 | 1.75 | 11063 | 11063 | 0 | CRV2 | 3: BHA 3 | 5A | Drill shoe track
09/10/2021 | 15:30 | 15:40 | 0.17 | 11063 | 11073 | 10 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11063.00 t/11073.00, w/WOB 10.00,Flow 350.00, RPM 30, Press 4400.00, Tq 6, ROP 60.00, Diff 600.00, Temp 228.00
09/10/2021 | 15:40 | 16:30 | 0.83 | 11073 | 11073 | 0 | CRV2 | 3: BHA 3 | 5A | Circulate B/U
09/10/2021 | 16:30 | 17:00 | 0.5 | 11073 | 11073 | 0 | CRV2 | 3: BHA 3 | 15D | FIT
09/10/2021 | 17:00 | 18:05 | 1.08 | 11073 | 11118 | 45 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11073.00 t/11118.00, TF -30G, w/WOB 10.00,Flow 350.00, Press 4400.00, Tq 0.00, ROP 41.54, Diff 600.00, Temp 228.00
09/10/2021 | 18:05 | 18:15 | 0.17 | 11118 | 11132 | 14 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11118.00 t/11132.00, w/WOB 15.00,Flow 350.00, RPM 30, Press 4400.00, Tq 5500, ROP 84.00, Diff 600.00, Temp 228.00
09/10/2021 | 18:15 | 18:35 | 0.33 | 11132 | 11132 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/10/2021 | 18:35 | 19:10 | 0.58 | 11132 | 11164 | 32 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11132.00 t/11164.00, TF -30.00G, w/WOB 25.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 54.86, Diff 500.00, Temp 228.00
09/10/2021 | 19:10 | 19:15 | 0.08 | 11164 | 11164 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/10/2021 | 19:15 | 20:00 | 0.75 | 11164 | 11227 | 63 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11164.00 t/11227.00, TF -30.00G, w/WOB 25.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 84.00, Diff 500.00, Temp 228.00
09/10/2021 | 20:00 | 20:15 | 0.25 | 11227 | 11227 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/10/2021 | 20:15 | 21:15 | 1 | 11227 | 11322 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11227.00 t/11322.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 95.00, Diff 500.00, Temp 228.00
09/10/2021 | 21:15 | 21:25 | 0.17 | 11322 | 11322 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/10/2021 | 21:25 | 21:50 | 0.42 | 11322 | 11352 | 30 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11322.00 t/11352.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 72.00, Diff 500.00, Temp 239.00
09/10/2021 | 21:50 | 22:10 | 0.33 | 11352 | 11382 | 30 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11352.00 t/11382.00, w/WOB 25.00,Flow 400.00, RPM 30.00, Press 5100.00, Tq 5500, ROP 90.00, Diff 500.00, Temp 239.00
09/10/2021 | 22:10 | 22:30 | 0.33 | 11382 | 11416 | 34 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11382.00 t/11416.00, TF -30.00G, w/WOB 30.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 102.00, Diff 500.00, Temp 239.00
09/10/2021 | 22:30 | 22:40 | 0.17 | 11416 | 11416 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/10/2021 | 22:40 | 23:40 | 1 | 11416 | 11511 | 95 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11416.00 t/11511.00, TF -45.00G, w/WOB 35.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 95.00, Diff 500.00, Temp 239.00
09/10/2021 | 23:40 | 24:00 | 0.33 | 11511 | 11511 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_11_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/11/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 92480
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11511 |  | 11063 |  | Csg Shoe MD(Usft): |  | 11053 |  | 600: | 41 | PV: | 16
End Depth (Usft): |  | 14178 |  | 14178 |  | OD (in): |  | 10.75 |  | 300: | 25 | YP: | 9
Total Drilled (Usft): |  | 2667 |  | 3115 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 19 | Viscosity: | 46
Slide Drilled (Usft): |  | 470 |  | 864 | [5 empty] | 100: | 13 | Chlorides: | 70000
Rotary Drilled (Usft): |  | 2197 |  | 2251 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.10 / 10.10
Drlg/Circ Hrs: |  | 20.63 / 3.37 |  | 26.47 / 7.53 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 6.73 |  | 11.9 |  | SN: |  | 13618580 |  | 10s Gel: | 6 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  | 13.9 |  | 14.57 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 117.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 158.06 / 69.80 |  | 154.53 / 72.61 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 41.75 |  | Grade In: |  | New
% Slide: |  | 17.62 |  | 27.74 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 82.38 |  | 72.26 |  | Make / Model: |  | Security / 1187517
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  | Mike Chris |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Jesse Taylor |  | Chris Inman | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 +.008 |  |  |  | 5.5 | 2 |  |  | 45.3 |  | 33.11 |  | 34.11
BTI Valve |  |  |  | 4.875 | 2 |  |  | 45.45 |  | 1.65 |  | 35.76
NMPC |  |  |  | 5 | 2.688 |  |  | 52.08 |  | 9.6 |  | 45.36
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 4 |  | 49.36
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 51.23 |  | 29.28 |  | 78.64
NMPC |  |  |  | 5 | 2.688 |  |  | 52.91 |  | 9.45 |  | 88.09
NMDC (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.83 |  | 30.72 |  | 118.81
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.92 |  | 136.73
Filter Sub |  |  |  | 4.75 | 2.875 |  |  | 50 |  | 5.55 |  | 142.28
Crossover |  |  |  | 5.25 | 2.688 |  |  | 44.51 |  | 3.37 |  | 145.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 333.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 341.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2796.16
Agitator |  |  |  | 5.312 | 2.688 |  |  | 56.05 |  | 21.41 |  | 2817.57
2817.57
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250019 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11537 | 78.42 | 315.73 | 11130.71 | -289.64 | 270.84 | 10.33 |  | -53.52 | -395.27 | 6.3 |  | -8.47 | 94
11632 | 86.7 | 316.44 | 11143 | -221.83 | 205.57 | 8.75 |  | 4.91 | -301.57 | 8.72 |  | 0.75 | 95
11727 | 92.45 | 318.39 | 11143.71 | -151.92 | 141.32 | 6.39 |  | 18.75 | -206.86 | 6.05 |  | 2.05 | 95
11821 | 93.56 | 318.15 | 11138.78 | -81.87 | 78.83 | 1.21 |  | -12.18 | -113.14 | 1.18 |  | -0.26 | 94
11916 | 95.02 | 317.94 | 11131.67 | -11.42 | 15.5 | 1.55 |  | -8.15 | -18.59 | 1.54 |  | -0.22 | 95
12011 | 92.97 | 316.24 | 11125.05 | 57.98 | -49.02 | 2.8 |  | -140.34 | 75.89 | -2.16 |  | -1.79 | 95
12106 | 93 | 316.63 | 11120.11 | 126.73 | -114.4 | 0.41 |  | 85.59 | 170.39 | 0.03 |  | 0.41 | 95
12200 | 92.08 | 317.5 | 11115.94 | 195.48 | -178.36 | 1.35 |  | 136.61 | 264.01 | -0.98 |  | 0.93 | 94
12295 | 91.82 | 318.59 | 11112.71 | 266.09 | -241.84 | 1.18 |  | 103.4 | 358.78 | -0.27 |  | 1.15 | 95
12390 | 90.56 | 320.87 | 11110.73 | 338.55 | -303.23 | 2.74 |  | 118.9 | 453.71 | -1.33 |  | 2.4 | 95
12482 | 89.79 | 321.52 | 11110.45 | 410.24 | -360.88 | 1.1 |  | 139.83 | 545.7 | -0.84 |  | 0.71 | 92
12576 | 89.93 | 321.75 | 11110.68 | 483.94 | -419.22 | 0.29 |  | 58.67 | 639.7 | 0.15 |  | 0.24 | 94
12671 | 91.65 | 322.96 | 11109.37 | 559.15 | -477.24 | 2.21 |  | 35.12 | 734.68 | 1.81 |  | 1.27 | 95
12763 | 92.09 | 322.96 | 11106.37 | 632.55 | -532.63 | 0.48 |  | 0 | 826.6 | 0.48 |  | 0 | 92
12858 | 94.26 | 322.64 | 11101.11 | 708.1 | -589.97 | 2.31 |  | -8.37 | 921.42 | 2.28 |  | -0.34 | 95
12952 | 94.84 | 321.8 | 11093.65 | 782.16 | -647.38 | 1.08 |  | -55.26 | 1015.12 | 0.62 |  | -0.89 | 94
13047 | 96.03 | 322.05 | 11084.65 | 856.61 | -705.7 | 1.28 |  | 11.8 | 1109.69 | 1.25 |  | 0.26 | 95
13141 | 95.43 | 321.83 | 11075.27 | 930.25 | -763.36 | 0.68 |  | -159.95 | 1203.22 | -0.64 |  | -0.23 | 94
13236 | 93.8 | 321.49 | 11067.63 | 1004.52 | -822.09 | 1.75 |  | -168.24 | 1297.9 | -1.72 |  | -0.36 | 95
13331 | 94.17 | 320.83 | 11061.02 | 1078.33 | -881.53 | 0.79 |  | -60.64 | 1392.67 | 0.39 |  | -0.69 | 95
13426 | 93.42 | 323.2 | 11054.74 | 1153.04 | -939.86 | 2.61 |  | 107.52 | 1487.45 | -0.79 |  | 2.49 | 95
13520 | 93.84 | 332.18 | 11048.77 | 1232.24 | -989.96 | 9.54 |  | 87.04 | 1580.62 | 0.45 |  | 9.55 | 94
13615 | 93.48 | 338.2 | 11042.7 | 1318.26 | -1029.72 | 6.34 |  | 93.23 | 1672.7 | -0.38 |  | 6.34 | 95
13710 | 93.76 | 329.5 | 11036.69 | 1403.28 | -1071.46 | 9.14 |  | -87.88 | 1765.23 | 0.29 |  | -9.16 | 95
13804 | 93.57 | 323.01 | 11030.68 | 1481.25 | -1123.54 | 6.89 |  | -91.47 | 1858.67 | -0.2 |  | -6.9 | 94
13898 | 91.49 | 322.99 | 11026.53 | 1556.24 | -1180.06 | 2.21 |  | -179.45 | 1952.54 | -2.21 |  | -0.02 | 94
13992 | 91.36 | 320.56 | 11024.19 | 1630.06 | -1238.2 | 2.59 |  | -93.03 | 2046.51 | -0.14 |  | -2.59 | 94
14085 | 90.57 | 319.96 | 11022.62 | 1701.56 | -1297.64 | 1.07 |  | -142.78 | 2139.47 | -0.85 |  | -0.65 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 129.26 | 24.97 | 64.66 | 338 | 401.35 | 5317.81 | 4664.4 | 0 | 230.82 | 205.02 | 176.84 | 7.45 | 0
Run | 117.7 | 24.55 | 61.77 | 333 | 398.58 | 5245.3 | 4612.81 | 0 | 228.98 | 204.17 | 177.37 | 7.3 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Pro Azimuthal Gamma Ray |  |  |  |  | 09/11/2021 |  | 14 |  | 2000 |  | 1 | 2000
Multi Rig Discount |  |  |  |  | 09/11/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/11/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 09/11/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 09/11/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/11/2021 | 00:00 | 00:20 | 0.33 | 11511 | 11532 | 21 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11511.00 t/11532.00, w/WOB 25.00,Flow 400.00, RPM 30.00, Press 5100.00, Tq 5500.00, ROP 63.00
09/11/2021 | 00:20 | 00:55 | 0.58 | 11532 | 11605 | 73 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11532.00 t/11605.00, TF 0.00, w/WOB 35.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 125.14
09/11/2021 | 00:55 | 01:10 | 0.25 | 11605 | 11605 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 01:10 | 01:50 | 0.67 | 11605 | 11665 | 60 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11605.00 t/11665.00, w/WOB 25.00,Flow 400.00, RPM 30.00, Press 5100.00, Tq 6000.00, ROP 90.00
09/11/2021 | 01:50 | 02:10 | 0.33 | 11665 | 11700 | 35 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11665.00 t/11700.00, TF 0.00, w/WOB 35.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 105.00
09/11/2021 | 02:10 | 02:20 | 0.17 | 11700 | 11700 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 02:20 | 02:45 | 0.42 | 11700 | 11720 | 20 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11700.00 t/11720.00, TF 0.00, w/WOB 35.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 48.00
09/11/2021 | 02:45 | 03:25 | 0.67 | 11720 | 11795 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11720.00 t/11795.00, w/WOB 25.00,Flow 400.00, RPM 30.00, Press 5100.00, Tq 6000.00, ROP 112.50
09/11/2021 | 03:25 | 03:30 | 0.08 | 11795 | 11795 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 03:30 | 04:10 | 0.67 | 11795 | 11889 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11795.00 t/11889.00, w/WOB 25.00,Flow 400.00, RPM 0.00, Press 5100.00, Tq 0.00, ROP 141.00
09/11/2021 | 04:10 | 04:15 | 0.08 | 11889 | 11889 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 04:15 | 04:30 | 0.25 | 11889 | 11909 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/11889.00 t/11909.00, TF -150.00, w/WOB 35.00,Flow 400.00, Press 5100.00, Tq 0.00, ROP 80.00
09/11/2021 | 04:30 | 04:57 | 0.45 | 11909 | 11984 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11909.00 t/11984.00, w/WOB 20,Flow 400.00, RPM 70, Press 5100.00, Tq 7, ROP 166.67
09/11/2021 | 04:57 | 05:02 | 0.08 | 11984 | 11984 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 05:02 | 05:10 | 0.13 | 11984 | 11994 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11984.00 t/11994.00, w/WOB 20,Flow 400.00, RPM 70, Press 5100.00, Tq 7, ROP 75.00
09/11/2021 | 05:10 | 05:30 | 0.33 | 11994 | 12014 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/11994.00 t/12014.00, TF 180, w/WOB 25,Flow 400.00, Press 5100.00, Tq 7, ROP 60.00
09/11/2021 | 05:30 | 05:55 | 0.42 | 12014 | 12079 | 65 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12014.00 t/12079.00, w/WOB 20,Flow 400.00, RPM 70, Press 5100.00, Tq 7, ROP 156.00
09/11/2021 | 05:55 | 06:01 | 0.1 | 12079 | 12079 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 06:01 | 06:08 | 0.12 | 12079 | 12089 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12079.00 t/12089.00, w/WOB 20,Flow 400.00, RPM 70, Press 5100.00, Tq 7, ROP 85.71
09/11/2021 | 06:08 | 06:20 | 0.2 | 12089 | 12101 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/12089.00 t/12101.00, TF 120, w/WOB 20,Flow 400.00, Press 5000, Tq 0, ROP 60.00
09/11/2021 | 06:20 | 06:49 | 0.48 | 12101 | 12174 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12101.00 t/12174.00, w/WOB 20,Flow 400.00, RPM 70, Press 5100.00, Tq 7, ROP 151.03
09/11/2021 | 06:49 | 06:54 | 0.08 | 12174 | 12174 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 06:54 | 07:05 | 0.18 | 12174 | 12181 | 7 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12174.00 t/12181.00, w/WOB 22.67,Flow 401.94, RPM 70, Press 4918.71, Tq 6.21, ROP 38.18
09/11/2021 | 07:05 | 07:20 | 0.25 | 12181 | 12201 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/12181.00 t/12201.00, TF 120.35, w/WOB 16.14,Flow 401.83, Press 5110.22, Tq 0, ROP 80.00
09/11/2021 | 07:20 | 07:39 | 0.32 | 12201 | 12268 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12201.00 t/12268.00, w/WOB 31.22,Flow 402.01, RPM 70, Press 5700, Tq 10.14, ROP 211.58
09/11/2021 | 07:39 | 07:43 | 0.07 | 12268 | 12268 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 07:43 | 07:50 | 0.12 | 12268 | 12279 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12268.00 t/12279.00, w/WOB 32,Flow 402.09, RPM 70, Press 5700, Tq 8.13, ROP 94.29
09/11/2021 | 07:50 | 08:10 | 0.33 | 12279 | 12306 | 27 | LAT | 3: BHA 3 | 2J | Slide Drill f/12279.00 t/12306.00, TF 103.16, w/WOB 14.57,Flow 402.06, Press 5097.56, Tq 0, ROP 81.00
09/11/2021 | 08:10 | 08:28 | 0.3 | 12306 | 12361 | 55 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12306.00 t/12361.00, w/WOB 30,Flow 401.45, RPM 70, Press 5700, Tq 7.47, ROP 183.33
09/11/2021 | 08:28 | 08:32 | 0.07 | 12361 | 12361 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 08:32 | 08:43 | 0.18 | 12361 | 12373 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12361.00 t/12373.00, w/WOB 25,Flow 402.13, RPM 70, Press 5700, Tq 5.93, ROP 65.45
09/11/2021 | 08:43 | 09:02 | 0.32 | 12373 | 12398 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/12373.00 t/12398.00, TF 85.06, w/WOB 20.96,Flow 401.94, Press 5115.16, Tq 0, ROP 78.95
09/11/2021 | 09:02 | 09:16 | 0.23 | 12398 | 12456 | 58 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12398.00 t/12456.00, w/WOB 36.14,Flow 401.99, RPM 70, Press 5564.77, Tq 9.07, ROP 248.57
09/11/2021 | 09:16 | 09:21 | 0.08 | 12456 | 12456 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 09:21 | 09:46 | 0.42 | 12456 | 12552 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12456.00 t/12552.00, w/WOB 32,Flow 402.02, RPM 70, Press 5700, Tq 10, ROP 230.40
09/11/2021 | 09:46 | 09:54 | 0.13 | 12552 | 12552 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 09:54 | 10:05 | 0.18 | 12552 | 12561 | 9 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12552.00 t/12561.00, w/WOB 12.90,Flow 402.09, RPM 70, Press 5700, Tq 6.21, ROP 49.09
09/11/2021 | 10:05 | 10:18 | 0.22 | 12561 | 12573 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/12561.00 t/12573.00, TF 17.81, w/WOB 16.26,Flow 402.03, Press 4971.99, Tq 0, ROP 55.38
09/11/2021 | 10:18 | 10:32 | 0.23 | 12573 | 12644 | 71 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12573.00 t/12644.00, w/WOB 32.42,Flow 401.94, RPM 67.46, Press 5700, Tq 8.89, ROP 304.29
09/11/2021 | 10:32 | 10:37 | 0.08 | 12644 | 12644 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 10:37 | 10:48 | 0.18 | 12644 | 12655 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12644.00 t/12655.00, w/WOB 21.13,Flow 402.01, RPM 70.10, Press 5700, Tq 6.01, ROP 60.00
09/11/2021 | 10:48 | 11:01 | 0.22 | 12655 | 12667 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/12655.00 t/12667.00, TF 24.12, w/WOB 15.73,Flow 402.06, Press 5108.67, Tq 0, ROP 55.38
09/11/2021 | 11:01 | 11:16 | 0.25 | 12667 | 12739 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12667.00 t/12739.00, w/WOB 30.97,Flow 401.94, RPM 66.74, Press 5700, Tq 8.68, ROP 288.00
09/11/2021 | 11:16 | 11:20 | 0.07 | 12739 | 12739 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 11:20 | 11:42 | 0.37 | 12739 | 12831 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12739.00 t/12831.00, w/WOB 36.84,Flow 401.85, RPM 70.05, Press 5642.51, Tq 7.99, ROP 251.67
09/11/2021 | 11:42 | 11:46 | 0.07 | 12831 | 12831 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 11:46 | 11:57 | 0.18 | 12831 | 12843 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12831.00 t/12843.00, w/WOB 24.84,Flow 402.05, RPM 70.07, Press 4946.76, Tq 6.65, ROP 76.85
09/11/2021 | 11:57 | 12:11 | 0.23 | 12843 | 12855 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/12843.00 t/12855.00, TF -23.91, w/WOB 15.71,Flow 401.71, Press 5127.82, Tq 6.11, ROP 51.43
09/11/2021 | 12:11 | 12:26 | 0.25 | 12855 | 12926 | 71 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12855.00 t/12926.00, w/WOB 30.86,Flow 401.76, RPM 67.70, Press 5637.89, Tq 9.00, ROP 284.96
09/11/2021 | 12:26 | 12:31 | 0.08 | 12926 | 12926 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 12:31 | 12:53 | 0.37 | 12926 | 13020 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12926.00 t/13020.00, w/WOB 34.35,Flow 401.91, RPM 70.07, Press 5664.35, Tq 8.70, ROP 256.36
09/11/2021 | 12:53 | 12:58 | 0.08 | 13020 | 13020 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 12:58 | 13:21 | 0.38 | 13020 | 13115 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13020.00 t/13115.00, w/WOB 25.97,Flow 402.10, RPM 70.05, Press 5664.35, Tq 7.25, ROP 247.83
09/11/2021 | 13:21 | 13:26 | 0.08 | 13115 | 13115 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 13:26 | 13:33 | 0.12 | 13115 | 13125 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13115.00 t/13125.00, w/WOB 25.97,Flow 401.76, RPM 50, Press 5664.35, Tq 7.25, ROP 85.71
09/11/2021 | 13:33 | 13:52 | 0.32 | 13125 | 13143 | 18 | LAT | 3: BHA 3 | 2J | Slide Drill f/13125.00 t/13143.00, TF 180, w/WOB 17.26,Flow 401.85, Press 5180.44, Tq 0, ROP 56.84
09/11/2021 | 13:52 | 14:09 | 0.28 | 13143 | 13209 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13143.00 t/13209.00, w/WOB 29.53,Flow 401.87, RPM 66.86, Press 5601.99, Tq 9.08, ROP 232.94
09/11/2021 | 14:09 | 14:15 | 0.1 | 13209 | 13209 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 14:15 | 14:22 | 0.12 | 13209 | 13219 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13209.00 t/13219.00, w/WOB 29.53,Flow 402.09, RPM 66.86, Press 5601.99, Tq 7.37, ROP 85.71
09/11/2021 | 14:22 | 14:43 | 0.35 | 13219 | 13234 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/13219.00 t/13234.00, TF 180, w/WOB 19.87,Flow 402.09, Press 5213.03, Tq 0, ROP 42.86
09/11/2021 | 14:43 | 15:00 | 0.28 | 13234 | 13304 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13234.00 t/13304.00, w/WOB 30.55,Flow 401.96, RPM 67.12, Press 5590.79, Tq 9.54, ROP 247.06
09/11/2021 | 15:00 | 15:04 | 0.07 | 13304 | 13304 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 15:04 | 15:25 | 0.35 | 13304 | 13399 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13304.00 t/13399.00, w/WOB 28.59,Flow 401.95, RPM 70.13, Press 5573.75, Tq 7.80, ROP 271.43
09/11/2021 | 15:25 | 15:30 | 0.08 | 13399 | 13399 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 15:30 | 15:50 | 0.33 | 13399 | 13493 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13399.00 t/13493.00, w/WOB 27.58,Flow 401.95, RPM 70.13, Press 5584.99, Tq 7.60, ROP 282.00
09/11/2021 | 15:50 | 15:58 | 0.13 | 13493 | 13493 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 15:58 | 16:16 | 0.3 | 13493 | 13588 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13493.00 t/13588.00, w/WOB 31.18,Flow 401.93, RPM 70.11, Press 5619.42, Tq 7.53, ROP 316.67
09/11/2021 | 16:16 | 16:23 | 0.12 | 13588 | 13588 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 16:23 | 16:34 | 0.18 | 13588 | 13598 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13588.00 t/13598.00, w/WOB 19.43,Flow 401.85, RPM 70.10, Press 4895.61, Tq 5.69, ROP 54.55
09/11/2021 | 16:34 | 16:54 | 0.33 | 13598 | 13622 | 24 | LAT | 3: BHA 3 | 2J | Slide Drill f/13598.00 t/13622.00, TF -83.66, w/WOB 10.25,Flow 401.96, Press 4947.58, Tq 4.71, ROP 72.00
09/11/2021 | 16:54 | 17:04 | 0.17 | 13622 | 13632 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13622.00 t/13632.00, w/WOB 10.29,Flow 402.05, RPM 50.13, Press 4828.15, Tq 5.28, ROP 60.00
09/11/2021 | 17:04 | 17:20 | 0.27 | 13632 | 13653 | 21 | LAT | 3: BHA 3 | 2J | Slide Drill f/13632.00 t/13653.00, TF -110.00G, w/WOB 15.00,Flow 402.05, Press 5300.00, Tq 5.28, ROP 78.75, Diff 474.93, Temp 275.00
09/11/2021 | 17:20 | 17:28 | 0.13 | 13653 | 13663 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13653.00 t/13663.00, w/WOB 10.29,Flow 402.05, RPM 50.13, Press 5300.00, Tq 5.28, ROP 75.00, Diff 474.93, Temp 275.00
09/11/2021 | 17:28 | 17:45 | 0.28 | 13663 | 13683 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/13663.00 t/13683.00, TF -110.00G, w/WOB 15.00,Flow 402.05, Press 5300.00, Tq 5.28, ROP 70.59, Diff 474.93, Temp 275.00
09/11/2021 | 17:45 | 17:52 | 0.12 | 13683 | 13683 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 17:52 | 18:50 | 0.97 | 13683 | 13778 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13683.00 t/13778.00, w/WOB 20.00,Flow 402.05, RPM 50.13, Press 5300.00, Tq 5.28, ROP 98.28, Diff 474.93, Temp 275.00
09/11/2021 | 18:50 | 19:35 | 0.75 | 13778 | 13778 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 19:35 | 19:50 | 0.25 | 13778 | 13793 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/13778.00 t/13793.00, TF -150.00G, w/WOB 20.00,Flow 402.05, Press 5300.00, Tq 5.28, ROP 60.00, Diff 474.93, Temp 275.00
09/11/2021 | 19:50 | 20:35 | 0.75 | 13793 | 13872 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13793.00 t/13872.00, w/WOB 10.29,Flow 402.05, RPM 50.13, Press 5300.00, Tq 5.28, ROP 105.33, Diff 474.93, Temp 275.00
09/11/2021 | 20:35 | 20:40 | 0.08 | 13872 | 13872 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 20:40 | 21:35 | 0.92 | 13872 | 13916 | 44 | LAT | 3: BHA 3 | 2J | Slide Drill f/13872.00 t/13916.00, TF -140.00G, w/WOB 30.00,Flow 402.05, Press 5300.00, Tq 5.28, ROP 48.00, Diff 474.93, Temp 271.00
09/11/2021 | 21:35 | 22:05 | 0.5 | 13916 | 13966 | 50 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13916.00 t/13966.00, w/WOB 25.00,Flow 402.05, RPM 50.13, Press 5300.00, Tq 5.28, ROP 100.00, Diff 474.93, Temp 271.00
09/11/2021 | 22:05 | 22:10 | 0.08 | 13966 | 13966 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 22:10 | 22:50 | 0.67 | 13966 | 14060 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13966.00 t/14060.00, w/WOB 25.00,Flow 402.05, RPM 70.00, Press 5300.00, Tq 5.28, ROP 141.00, Diff 474.93, Temp 271.00
09/11/2021 | 22:50 | 22:55 | 0.08 | 14060 | 14060 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 22:55 | 23:35 | 0.67 | 14060 | 14153 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14060.00 t/14153.00, w/WOB 25.00,Flow 402.05, RPM 70.00, Press 5300.00, Tq 8.00, ROP 139.50, Diff 474.93, Temp 275.00
09/11/2021 | 23:35 | 23:40 | 0.08 | 14153 | 14153 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/11/2021 | 23:40 | 24:00 | 0.33 | 14153 | 14178 | 25 | LAT | 3: BHA 3 | 2J | Slide Drill f/14153.00 t/14178.00, TF -30.00G, w/WOB 35.00,Flow 402.05, Press 5300.00, Tq 8.00, ROP 75.00, Diff 474.93, Temp 275.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_12_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/12/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 101930
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14178 |  | 11063 |  | Csg Shoe MD(Usft): |  | 11053 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 16615 |  | 16615 |  | OD (in): |  | 10.75 |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 2437 |  | 5552 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 22 | Viscosity: | 64
Slide Drilled (Usft): |  | 176 |  | 1040 | [5 empty] | 100: | 16 | Chlorides: | 57000
Rotary Drilled (Usft): |  | 2261 |  | 4512 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.10 / 12.60
Drlg/Circ Hrs: |  | 19.90 / 2.93 |  | 46.37 / 10.47 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 5.52 |  | 17.42 |  | SN: |  | 13618580 |  | 10s Gel: | 8 | Weight (ppg): | 10.3
Rotary Drilling Hrs: |  | 14.38 |  | 28.95 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 127.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 157.20 / 31.90 |  | 155.85 / 59.71 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 65.75 |  | Grade In: |  | New
% Slide: |  | 7.22 |  | 18.73 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 92.78 |  | 81.27 |  | Make / Model: |  | Security / 1187517
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  | Mike Chris |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Jesse Taylor |  | Chris Inman | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 +.008 |  |  |  | 5.5 | 2 |  |  | 45.3 |  | 33.11 |  | 34.11
BTI Valve |  |  |  | 4.875 | 2 |  |  | 45.45 |  | 1.65 |  | 35.76
NMPC |  |  |  | 5 | 2.688 |  |  | 52.08 |  | 9.6 |  | 45.36
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 4 |  | 49.36
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 51.23 |  | 29.28 |  | 78.64
NMPC |  |  |  | 5 | 2.688 |  |  | 52.91 |  | 9.45 |  | 88.09
NMDC (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.83 |  | 30.72 |  | 118.81
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.92 |  | 136.73
Filter Sub |  |  |  | 4.75 | 2.875 |  |  | 50 |  | 5.55 |  | 142.28
Crossover |  |  |  | 5.25 | 2.688 |  |  | 44.51 |  | 3.37 |  | 145.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 333.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 341.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2796.16
Agitator |  |  |  | 5.312 | 2.688 |  |  | 56.05 |  | 21.41 |  | 2817.57
2817.57
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250019 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14180 | 91.84 | 319.1 | 11020.63 | 1773.81 | -1359.29 | 1.61 |  | -34.09 | 2234.39 | 1.34 |  | -0.91 | 95
14274 | 91.01 | 318.01 | 11018.29 | 1844.25 | -1421.49 | 1.46 |  | -127.28 | 2328.23 | -0.88 |  | -1.16 | 94
14369 | 94 | 320.3 | 11014.14 | 1916.03 | -1483.55 | 3.96 |  | 37.38 | 2423.04 | 3.15 |  | 2.41 | 95
14464 | 93.81 | 320.09 | 11007.67 | 1988.84 | -1544.22 | 0.3 |  | -132.2 | 2517.8 | -0.2 |  | -0.22 | 95
14559 | 94.55 | 321.74 | 11000.74 | 2062.38 | -1603.96 | 1.9 |  | 65.73 | 2612.54 | 0.78 |  | 1.74 | 95
14653 | 94.99 | 321.49 | 10992.92 | 2135.81 | -1662.12 | 0.54 |  | -29.51 | 2706.21 | 0.47 |  | -0.27 | 94
14748 | 95.69 | 321.07 | 10984.08 | 2209.61 | -1721.29 | 0.86 |  | -30.83 | 2800.8 | 0.74 |  | -0.44 | 95
14841 | 94.64 | 319.42 | 10975.71 | 2280.81 | -1780.52 | 2.1 |  | -122.5 | 2893.39 | -1.13 |  | -1.77 | 93
14934 | 95.77 | 319.93 | 10967.27 | 2351.42 | -1840.45 | 1.33 |  | 24.18 | 2985.96 | 1.22 |  | 0.55 | 93
15029 | 95.25 | 319.59 | 10958.15 | 2423.6 | -1901.54 | 0.65 |  | -146.93 | 3080.47 | -0.55 |  | -0.36 | 95
15124 | 92.49 | 319.08 | 10951.74 | 2495.49 | -1963.3 | 2.95 |  | -169.54 | 3175.18 | -2.91 |  | -0.54 | 95
15219 | 91.89 | 318.54 | 10948.11 | 2566.93 | -2025.81 | 0.85 |  | -138.02 | 3270 | -0.63 |  | -0.57 | 95
15314 | 93.21 | 320.46 | 10943.88 | 2639.09 | -2087.45 | 2.45 |  | 55.43 | 3364.84 | 1.39 |  | 2.02 | 95
15409 | 93.95 | 320.79 | 10937.95 | 2712.38 | -2147.6 | 0.85 |  | 23.98 | 3459.64 | 0.78 |  | 0.35 | 95
15504 | 95.5 | 321.08 | 10930.13 | 2785.89 | -2207.26 | 1.66 |  | 10.55 | 3554.31 | 1.63 |  | 0.31 | 95
15598 | 95.34 | 320.06 | 10921.25 | 2858.17 | -2266.69 | 1.09 |  | -98.91 | 3647.88 | -0.17 |  | -1.09 | 94
15692 | 96.01 | 320.21 | 10911.95 | 2929.97 | -2326.65 | 0.73 |  | 12.55 | 3741.39 | 0.71 |  | 0.16 | 94
15787 | 93.7 | 320.09 | 10903.91 | 3002.63 | -2387.3 | 2.43 |  | -177.03 | 3836.02 | -2.43 |  | -0.13 | 95
15880 | 93.84 | 320.49 | 10897.8 | 3074.02 | -2446.59 | 0.45 |  | 70.66 | 3928.79 | 0.15 |  | 0.43 | 93
15975 | 92.87 | 321.23 | 10892.24 | 3147.58 | -2506.45 | 1.28 |  | 142.69 | 4023.62 | -1.02 |  | 0.78 | 95
16069 | 92.98 | 321.23 | 10887.44 | 3220.77 | -2565.24 | 0.12 |  | 0 | 4117.5 | 0.12 |  | 0 | 94
16164 | 93.59 | 323.2 | 10882 | 3295.72 | -2623.35 | 2.17 |  | 72.71 | 4212.33 | 0.64 |  | 2.07 | 95
16258 | 91.81 | 321.15 | 10877.57 | 3369.88 | -2680.92 | 2.89 |  | -130.95 | 4306.21 | -1.89 |  | -2.18 | 94
16354 | 92.16 | 320.65 | 10874.24 | 3444.34 | -2741.43 | 0.64 |  | -54.98 | 4402.15 | 0.36 |  | -0.52 | 96
16446 | 93.25 | 321.13 | 10869.9 | 3515.64 | -2799.4 | 1.29 |  | 23.73 | 4494.04 | 1.18 |  | 0.52 | 92
16540 | 93.67 | 320.69 | 10864.23 | 3588.47 | -2858.56 | 0.65 |  | -46.27 | 4587.86 | 0.45 |  | -0.47 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 122.52 | 27.61 | 75.95 | 345 | 396.33 | 5359.61 | 4774.41 | 0 | 246.86 | 200.39 | 161.43 | 9.8 | 0
Run | 119.77 | 25.2 | 66.75 | 338 | 398.19 | 5300.84 | 4741.37 | 0 | 236.1 | 202.56 | 171.29 | 8.12 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 09/12/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 09/12/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 09/12/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/12/2021 |  | 14 |  | 2000 |  | 1 | 2000
Multi Rig Discount |  |  |  |  | 09/12/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/12/2021 | 00:00 | 00:35 | 0.58 | 14178 | 14248 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14178.00 t/14248.00, w/WOB 35.00,Flow 402.05, RPM 70.00, Press 5300.00, Tq 8.00, ROP 120.00, Diff 474.93, Temp 275.00
09/12/2021 | 00:35 | 00:40 | 0.08 | 14248 | 14248 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 00:40 | 01:15 | 0.58 | 14248 | 14342 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14248.00 t/14342.00, w/WOB 35.00,Flow 402.05, RPM 70.00, Press 5300.00, Tq 8.00, ROP 161.14, Diff 474.93, Temp 279.00
09/12/2021 | 01:15 | 01:20 | 0.08 | 14342 | 14342 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 01:20 | 01:45 | 0.42 | 14342 | 14362 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/14342.00 t/14362.00, TF 30.00G, w/WOB 35.00,Flow 402.05, Press 5300.00, Tq 8.00, ROP 48.00, Diff 474.93, Temp 279.00
09/12/2021 | 01:45 | 02:10 | 0.42 | 14362 | 14437 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14362.00 t/14437.00, w/WOB 35.00,Flow 402.05, RPM 70.00, Press 5300.00, Tq 8.00, ROP 180.00, Diff 474.93, Temp 279.00
09/12/2021 | 02:10 | 02:15 | 0.08 | 14437 | 14437 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 02:15 | 02:45 | 0.5 | 14437 | 14532 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14437.00 t/14532.00, w/WOB 35.00,Flow 402.05, RPM 70.00, Press 5300.00, Tq 8.00, ROP 190.00, Diff 474.93, Temp 279.00
09/12/2021 | 02:45 | 02:50 | 0.08 | 14532 | 14532 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 02:50 | 03:00 | 0.17 | 14532 | 14540 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/14532.00 t/14540.00, TF 0.00G, w/WOB 40.00,Flow 402.05, Press 5300.00, Tq 8.00, ROP 48.00, Diff 474.93, Temp 279.00
09/12/2021 | 03:00 | 03:35 | 0.58 | 14540 | 14627 | 87 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14540.00 t/14627.00, w/WOB 35.00,Flow 402.05, RPM 80.00, Press 5300.00, Tq 8.00, ROP 149.14, Diff 474.93, Temp 279.00
09/12/2021 | 03:35 | 03:40 | 0.08 | 14627 | 14627 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 03:40 | 04:10 | 0.5 | 14627 | 14721 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14627.00 t/14721.00, w/WOB 35.00,Flow 402.05, RPM 80.00, Press 5300.00, Tq 8.00, ROP 188.00, Diff 474.93, Temp 279.00
09/12/2021 | 04:10 | 04:15 | 0.08 | 14721 | 14721 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 04:15 | 04:50 | 0.58 | 14721 | 14816 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14721.00 t/14816.00, w/WOB 35.00,Flow 402.05, RPM 80.00, Press 5300.00, Tq 8.00, ROP 162.86, Diff 474.93, Temp 279.00
09/12/2021 | 04:50 | 04:55 | 0.08 | 14816 | 14816 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 04:55 | 05:20 | 0.42 | 14816 | 14833 | 17 | LAT | 3: BHA 3 | 2J | Slide Drill f/14816.00 t/14833.00, TF -150G, w/WOB 35.00,Flow 402.05, Press 5300.00, Tq 0, ROP 40.80, Diff 474.93, Temp 279.00
09/12/2021 | 05:20 | 05:47 | 0.45 | 14833 | 14909 | 76 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14833.00 t/14909.00, w/WOB 20.83,Flow 393.13, RPM 76.74, Press 5587, Tq 8.44, ROP 168.89, Diff 708.54, Temp 278.60
09/12/2021 | 05:47 | 06:57 | 1.17 | 14909 | 14909 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
09/12/2021 | 06:57 | 07:03 | 0.1 | 14909 | 14909 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 07:03 | 07:34 | 0.52 | 14909 | 15002 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14909.00 t/15002.00, w/WOB 34.69,Flow 393.27, RPM 80.09, Press 5526.36, Tq 9.33, ROP 180.00, Diff 647.90, Temp 285.80
09/12/2021 | 07:34 | 07:39 | 0.08 | 15002 | 15002 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 07:39 | 07:53 | 0.23 | 15002 | 15013 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15002.00 t/15013.00, w/WOB 35.78,Flow 393.18, RPM 80.09, Press 5526.36, Tq 8.07, ROP 47.14, Diff 647.90, Temp 285.80
09/12/2021 | 07:53 | 08:25 | 0.53 | 15013 | 15033 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15013.00 t/15033.00, TF 177.09G, w/WOB 17.15,Flow 393.13, Press 4998.07, Tq 0, ROP 37.50, Diff 267.12, Temp 282.20
09/12/2021 | 08:25 | 08:41 | 0.27 | 15033 | 15097 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15033.00 t/15097.00, w/WOB 31.05,Flow 392.86, RPM 80, Press 5503.57, Tq 11.51, ROP 240.00, Diff 1484.01, Temp 284.00
09/12/2021 | 08:41 | 08:46 | 0.08 | 15097 | 15097 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 08:46 | 08:54 | 0.13 | 15097 | 15107 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15097.00 t/15107.00, w/WOB 27.61,Flow 393.29, RPM 80.10, Press 5503.57, Tq 9.51, ROP 75.00, Diff 782.77, Temp 285.80
09/12/2021 | 08:54 | 09:12 | 0.3 | 15107 | 15117 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/15107.00 t/15117.00, TF 162.59G, w/WOB 18.57,Flow 393.21, Press 5084.49, Tq 0, ROP 33.33, Diff 274.58, Temp 284.00
09/12/2021 | 09:12 | 09:38 | 0.43 | 15117 | 15192 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15117.00 t/15192.00, w/WOB 28.33,Flow 393.21, RPM 75.81, Press 5535.95, Tq 10.80, ROP 173.08, Diff 726.04, Temp 285.80
09/12/2021 | 09:38 | 09:47 | 0.15 | 15192 | 15192 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 09:47 | 10:18 | 0.52 | 15192 | 15287 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15192.00 t/15287.00, w/WOB 33.65,Flow 393.48, RPM 80.08, Press 5560.60, Tq 10.47, ROP 183.87, Diff 750.69, Temp 289.40
09/12/2021 | 10:18 | 10:28 | 0.17 | 15287 | 15287 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 10:28 | 10:35 | 0.12 | 15287 | 15297 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15287.00 t/15297.00, w/WOB 17.52,Flow 393.69, RPM 80.09, Press 5560.60, Tq 9.88, ROP 85.71, Diff 721.84, Temp 289.40
09/12/2021 | 10:35 | 11:05 | 0.5 | 15297 | 15312 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/15297.00 t/15312.00, TF 60.36G, w/WOB 14.16,Flow 393.58, Press 4940.62, Tq 0, ROP 30.00, Diff 176.34, Temp 285.80
09/12/2021 | 11:05 | 11:33 | 0.47 | 15312 | 15382 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15312.00 t/15382.00, w/WOB 30.65,Flow 393.46, RPM 75.53, Press 5511.11, Tq 11.47, ROP 150.00, Diff 746.83, Temp 287.60
09/12/2021 | 11:33 | 11:43 | 0.17 | 15382 | 15382 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 11:43 | 12:15 | 0.53 | 15382 | 15477 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15382.00 t/15477.00, w/WOB 29.77,Flow 393.86, RPM 80.11, Press 5587.37, Tq 11.27, ROP 178.13, Diff 823.09, Temp 291.20
09/12/2021 | 12:15 | 12:23 | 0.13 | 15477 | 15477 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 12:23 | 12:55 | 0.53 | 15477 | 15572 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15477.00 t/15572.00, w/WOB 29.34,Flow 394.66, RPM 80.09, Press 5584.14, Tq 10.83, ROP 178.13, Diff 819.86, Temp 293.00
09/12/2021 | 12:55 | 13:02 | 0.12 | 15572 | 15572 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 13:02 | 13:10 | 0.13 | 15572 | 15582 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15572.00 t/15582.00, w/WOB 15.64,Flow 394.93, RPM 80.12, Press 4846.78, Tq 8.50, ROP 75.00, Diff 19.78, Temp 293.00
09/12/2021 | 13:10 | 13:16 | 0.1 | 15582 | 15582 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 13:16 | 14:14 | 0.97 | 15582 | 15602 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15582.00 t/15602.00, TF -143.38G, w/WOB 18.39,Flow 394.32, Press 5002.01, Tq 0, ROP 20.69, Diff 248.63, Temp 285.80
09/12/2021 | 14:14 | 14:31 | 0.28 | 15602 | 15666 | 64 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15602.00 t/15666.00, w/WOB 32.38,Flow 394.62, RPM 75.11, Press 5602.30, Tq 13.09, ROP 225.88, Diff 1561.10, Temp 287.60
09/12/2021 | 14:31 | 14:42 | 0.18 | 15666 | 15666 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 14:42 | 15:12 | 0.5 | 15666 | 15760 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15666.00 t/15760.00, w/WOB 31.05,Flow 394.72, RPM 80, Press 5598.77, Tq 11.94, ROP 188.00, Diff 845.39, Temp 293.00
09/12/2021 | 15:12 | 15:19 | 0.12 | 15760 | 15760 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 15:19 | 15:27 | 0.13 | 15760 | 15770 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15760.00 t/15770.00, w/WOB 26.05,Flow 394.94, RPM 50.09, Press 5598.77, Tq 10.55, ROP 75.00, Diff 791.04, Temp 293.00
09/12/2021 | 15:27 | 16:12 | 0.75 | 15770 | 15788 | 18 | LAT | 3: BHA 3 | 2J | Slide Drill f/15770.00 t/15788.00, TF 168.57G, w/WOB 7.83,Flow 394.73, Press 4939.60, Tq 0, ROP 24.00, Diff 238.26, Temp 287.60
09/12/2021 | 16:12 | 16:15 | 0.05 | 15788 | 15788 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 16:15 | 16:33 | 0.3 | 15788 | 15855 | 67 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15788.00 t/15855.00, w/WOB 26.21,Flow 394.64, RPM 80.00, Press 5521.87, Tq 12.07, ROP 223.33, Diff 820.53, Temp 289.40
09/12/2021 | 16:33 | 16:41 | 0.13 | 15855 | 15855 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 16:41 | 17:09 | 0.47 | 15855 | 15948 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15855.00 t/15948.00, w/WOB 27.47,Flow 394.97, RPM 77.39, Press 5610.27, Tq 11.98, ROP 199.29, Diff 908.93, Temp 294.80
09/12/2021 | 17:09 | 17:15 | 0.1 | 15948 | 15948 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 17:15 | 17:29 | 0.23 | 15948 | 15960 | 12 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15948.00 t/15960.00, w/WOB 21.10,Flow 395.15, RPM 58.04, Press 4830.80, Tq 10.07, ROP 51.43, Diff -11.86, Temp 294.80
09/12/2021 | 17:29 | 17:42 | 0.22 | 15960 | 15966 | 6 | LAT | 3: BHA 3 | 2J | Slide Drill f/15960.00 t/15966.00, TF 171.45G, w/WOB 16.29,Flow 394.91, Press 5049.83, Tq 0, ROP 27.69, Diff 244.28, Temp 293.00
09/12/2021 | 17:42 | 18:10 | 0.47 | 15966 | 16043 | 77 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15966.00 t/16043.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5238.11, Tq 12.00, ROP 165.00, Diff 432.56, Temp 293.00
09/12/2021 | 18:10 | 18:15 | 0.08 | 16043 | 16043 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 18:15 | 18:50 | 0.58 | 16043 | 16137 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16043.00 t/16137.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 161.14, Diff 894.45, Temp 293.00
09/12/2021 | 18:50 | 18:55 | 0.08 | 16137 | 16137 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 18:55 | 19:25 | 0.5 | 16137 | 16232 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16137.00 t/16232.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 190.00, Diff 894.45, Temp 293.00
09/12/2021 | 19:25 | 19:30 | 0.08 | 16232 | 16232 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 19:30 | 19:55 | 0.42 | 16232 | 16252 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/16232.00 t/16252.00, TF -140.00G, w/WOB 40.00,Flow 394.97, Press 5700.00, Tq 12.00, ROP 48.00, Diff 894.45, Temp 297.00
09/12/2021 | 19:55 | 20:40 | 0.75 | 16252 | 16326 | 74 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16252.00 t/16326.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 98.67, Diff 894.45, Temp 297.00
09/12/2021 | 20:40 | 20:45 | 0.08 | 16326 | 16326 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 20:45 | 21:30 | 0.75 | 16326 | 16422 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16326.00 t/16422.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 128.00, Diff 894.45, Temp 297.00
09/12/2021 | 21:30 | 21:35 | 0.08 | 16422 | 16422 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 21:35 | 22:20 | 0.75 | 16422 | 16514 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16422.00 t/16514.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 122.67, Diff 894.45, Temp 297.00
09/12/2021 | 22:20 | 22:25 | 0.08 | 16514 | 16514 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 22:25 | 22:55 | 0.5 | 16514 | 16529 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/16514.00 t/16529.00, TF -150.00G, w/WOB 40.00,Flow 394.97, Press 5700.00, Tq 12.00, ROP 30.00, Diff 894.45, Temp 297.00
09/12/2021 | 22:55 | 23:30 | 0.58 | 16529 | 16608 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16529.00 t/16608.00, w/WOB 25.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 135.43, Diff 894.45, Temp 297.00
09/12/2021 | 23:30 | 23:40 | 0.17 | 16608 | 16608 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/12/2021 | 23:40 | 24:00 | 0.33 | 16608 | 16615 | 7 | LAT | 3: BHA 3 | 2J | Slide Drill f/16608.00 t/16615.00, TF -150.00G, w/WOB 40.00,Flow 394.97, Press 5700.00, Tq 12.00, ROP 21.00, Diff 894.45, Temp 297.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_13_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/13/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 111380
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16615 |  | 11063 |  | Csg Shoe MD(Usft): |  | 11053 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 18112 |  | 18112 |  | OD (in): |  | 10.75 |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 1497 |  | 7049 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 22 | Viscosity: | 64
Slide Drilled (Usft): |  | 115 |  | 1155 | [5 empty] | 100: | 16 | Chlorides: | 57000
Rotary Drilled (Usft): |  | 1382 |  | 5894 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.10 / 12.60
Drlg/Circ Hrs: |  | 17.20 / 4.27 |  | 63.57 / 14.73 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 4.48 |  | 21.9 |  | SN: |  | 13618580 |  | 10s Gel: | 8 | Weight (ppg): | 10.3
Rotary Drilling Hrs: |  | 12.72 |  | 41.67 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 127.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 108.68 / 25.65 |  | 141.46 / 52.74 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 89.75 |  | Grade In: |  | New
% Slide: |  | 7.68 |  | 16.39 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  | 92.32 |  | 83.61 |  | Make / Model: |  | Security / 1187517
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  | Mike Chris |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Jesse Taylor |  | Chris Inman | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 +.008 |  |  |  | 5.5 | 2 |  |  | 45.3 |  | 33.11 |  | 34.11
BTI Valve |  |  |  | 4.875 | 2 |  |  | 45.45 |  | 1.65 |  | 35.76
NMPC |  |  |  | 5 | 2.688 |  |  | 52.08 |  | 9.6 |  | 45.36
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 4 |  | 49.36
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 51.23 |  | 29.28 |  | 78.64
NMPC |  |  |  | 5 | 2.688 |  |  | 52.91 |  | 9.45 |  | 88.09
NMDC (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.83 |  | 30.72 |  | 118.81
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.92 |  | 136.73
Filter Sub |  |  |  | 4.75 | 2.875 |  |  | 50 |  | 5.55 |  | 142.28
Crossover |  |  |  | 5.25 | 2.688 |  |  | 44.51 |  | 3.37 |  | 145.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 333.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 341.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2796.16
Agitator |  |  |  | 5.312 | 2.688 |  |  | 56.05 |  | 21.41 |  | 2817.57
2817.57
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250019 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
16633 | 93.01 | 319.58 | 10858.81 | 3659.73 | -2918.07 | 1.39 |  | -120.75 | 4680.67 | -0.71 |  | -1.19 | 93
16728 | 93.25 | 318.89 | 10853.62 | 3731.57 | -2980.01 | 0.77 |  | -70.78 | 4775.46 | 0.25 |  | -0.73 | 95
16823 | 91.43 | 318.29 | 10849.74 | 3802.76 | -3042.79 | 2.02 |  | -161.76 | 4870.25 | -1.92 |  | -0.63 | 95
16917 | 92.16 | 318.25 | 10846.8 | 3872.87 | -3105.33 | 0.78 |  | -3.13 | 4964.05 | 0.78 |  | -0.04 | 94
17012 | 94.63 | 318.46 | 10841.17 | 3943.74 | -3168.34 | 2.61 |  | 4.85 | 5058.73 | 2.6 |  | 0.22 | 95
17106 | 93.06 | 317.91 | 10834.87 | 4013.63 | -3230.87 | 1.77 |  | -160.71 | 5152.36 | -1.67 |  | -0.59 | 94
17201 | 91.97 | 322.29 | 10830.7 | 4086.43 | -3291.73 | 4.75 |  | 103.88 | 5247.21 | -1.15 |  | 4.61 | 95
17296 | 92 | 329.38 | 10827.41 | 4164.93 | -3345.02 | 7.46 |  | 89.63 | 5341.83 | 0.03 |  | 7.46 | 95
17391 | 90.69 | 326.01 | 10825.17 | 4245.19 | -3395.77 | 3.8 |  | -111.2 | 5436.23 | -1.38 |  | -3.55 | 95
17486 | 92 | 323.72 | 10822.94 | 4322.86 | -3450.42 | 2.78 |  | -60.2 | 5531.04 | 1.38 |  | -2.41 | 95
17580 | 93.61 | 323.11 | 10818.34 | 4398.24 | -3506.38 | 1.83 |  | -20.71 | 5624.87 | 1.71 |  | -0.65 | 94
17674 | 93.73 | 322.86 | 10812.33 | 4473.15 | -3562.85 | 0.29 |  | -64.31 | 5718.65 | 0.13 |  | -0.27 | 94
17770 | 93.19 | 324.78 | 10806.53 | 4550.49 | -3619.41 | 2.07 |  | 105.68 | 5814.39 | -0.56 |  | 2 | 96
17864 | 93.03 | 329.15 | 10801.43 | 4629.16 | -3670.57 | 4.65 |  | 91.98 | 5907.8 | -0.17 |  | 4.65 | 94
17960 | 94.07 | 340.67 | 10795.47 | 4715.78 | -3711.14 | 12.03 |  | 84.49 | 6000.86 | 1.08 |  | 12 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 82.15 | 28.36 | 80 | 349 | 395.76 | 5658.22 | 4990.04 | 0 | 275.71 | 194.71 | 144.29 | 11.59 | 0
Run | 109.57 | 26.16 | 70.73 | 341 | 397.51 | 5396.6 | 4794.93 | 0 | 244.79 | 200.7 | 164.61 | 9.14 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 09/13/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 09/13/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 09/13/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/13/2021 |  | 14 |  | 2000 |  | 1 | 2000
Multi Rig Discount |  |  |  |  | 09/13/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/13/2021 | 00:00 | 00:20 | 0.33 | 16615 | 16623 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/16615.00 t/16623.00, TF -150.00, w/WOB 40.00,Flow 394.97, Press 5700.00, Tq 12.00, ROP 24.00
09/13/2021 | 00:20 | 00:55 | 0.58 | 16623 | 16701 | 78 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16623.00 t/16701.00, w/WOB 30.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 133.71
09/13/2021 | 00:55 | 01:00 | 0.08 | 16701 | 16701 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 01:00 | 01:45 | 0.75 | 16701 | 16796 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16701.00 t/16796.00, w/WOB 30.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 126.67
09/13/2021 | 01:45 | 01:50 | 0.08 | 16796 | 16796 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 01:50 | 02:25 | 0.58 | 16796 | 16811 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/16796.00 t/16811.00, TF 150.00, w/WOB 40.00,Flow 394.97, Press 5700.00, Tq 12.00, ROP 25.71
09/13/2021 | 02:25 | 03:05 | 0.67 | 16811 | 16891 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16811.00 t/16891.00, w/WOB 30.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 120.00
09/13/2021 | 03:05 | 03:10 | 0.08 | 16891 | 16891 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 03:10 | 03:50 | 0.67 | 16891 | 16985 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16891.00 t/16985.00, w/WOB 30.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 141.00
09/13/2021 | 03:50 | 03:55 | 0.08 | 16985 | 16985 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 03:55 | 04:45 | 0.83 | 16985 | 17080 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16985.00 t/17080.00, w/WOB 30.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 114.00
09/13/2021 | 04:45 | 05:10 | 0.42 | 17080 | 17092 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/17080.00 t/17092.00, TF 150.00, w/WOB 40.00,Flow 394.97, Press 5700.00, Tq 12.00, ROP 28.80
09/13/2021 | 05:10 | 05:53 | 0.72 | 17092 | 17174 | 82 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17092.00 t/17174.00, w/WOB 40.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 114.42
09/13/2021 | 05:53 | 06:00 | 0.12 | 17174 | 17174 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 06:00 | 06:07 | 0.12 | 17174 | 17184 | 10 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17174.00 t/17184.00, w/WOB 30.00,Flow 394.97, RPM 80.00, Press 5700.00, Tq 12.00, ROP 85.71
09/13/2021 | 06:07 | 06:30 | 0.38 | 17184 | 17199 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/17184.00 t/17199.00, TF 180.00, w/WOB 20.00,Flow 394.97, Press 5100.00, Tq 0.00, ROP 39.13
09/13/2021 | 06:30 | 07:01 | 0.52 | 17199 | 17269 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17199.00 t/17269.00, w/WOB 28.97,Flow 395.54, RPM 80.00, Press 5790.87, Tq 12.72, ROP 135.48
09/13/2021 | 07:01 | 07:08 | 0.12 | 17269 | 17269 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 07:08 | 07:27 | 0.32 | 17269 | 17304 | 35 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17269.00 t/17304.00, w/WOB 20.22,Flow 396.23, RPM 80.00, Press 5790.87, Tq 10.09, ROP 110.53
09/13/2021 | 07:27 | 08:24 | 0.95 | 17304 | 17334 | 30 | LAT | 3: BHA 3 | 2J | Slide Drill f/17304.00 t/17334.00, TF -90.00, w/WOB 18.30,Flow 395.73, Press 5480.03, Tq 0.00, ROP 31.58
09/13/2021 | 08:24 | 08:40 | 0.27 | 17334 | 17364 | 30 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17334.00 t/17364.00, w/WOB 20.69,Flow 395.84, RPM 80.00, Press 5651.22, Tq 10.51, ROP 112.50
09/13/2021 | 08:40 | 08:47 | 0.12 | 17364 | 17364 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 08:47 | 09:12 | 0.42 | 17364 | 17403 | 39 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17364.00 t/17403.00, w/WOB 25.00,Flow 396.04, RPM 80.00, Press 5651.22, Tq 9.77, ROP 93.60
09/13/2021 | 09:12 | 09:53 | 0.68 | 17403 | 17418 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/17403.00 t/17418.00, TF -45.00, w/WOB 19.76,Flow 395.96, Press 5530.09, Tq 0.00, ROP 21.95
09/13/2021 | 09:53 | 10:21 | 0.47 | 17418 | 17459 | 41 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17418.00 t/17459.00, w/WOB 19.40,Flow 395.78, RPM 80.00, Press 5685.11, Tq 10.99, ROP 87.86
09/13/2021 | 10:21 | 10:26 | 0.08 | 17459 | 17459 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 10:26 | 11:21 | 0.92 | 17459 | 17554 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17459.00 t/17554.00, w/WOB 36.77,Flow 396.12, RPM 80.00, Press 5702.91, Tq 11.36, ROP 103.64
09/13/2021 | 11:21 | 11:53 | 0.53 | 17554 | 17554 | 0 | LAT | 3: BHA 3 | 8P | Rig Service
09/13/2021 | 11:53 | 11:58 | 0.08 | 17554 | 17554 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 11:58 | 12:10 | 0.2 | 17554 | 17570 | 16 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17554.00 t/17570.00, w/WOB 26.23,Flow 396.24, RPM 80.00, Press 5789.11, Tq 13.10, ROP 80.00
09/13/2021 | 12:10 | 12:48 | 0.63 | 17570 | 17582 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/17570.00 t/17582.00, TF -90.00, w/WOB 26.23,Flow 396.24, Press 5400.00, Tq 0.00, ROP 18.95
09/13/2021 | 12:48 | 13:30 | 0.7 | 17582 | 17648 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17582.00 t/17648.00, w/WOB 30.00,Flow 396.24, RPM 80.00, Press 5789.11, Tq 13.10, ROP 94.29
09/13/2021 | 13:30 | 13:35 | 0.08 | 17648 | 17648 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 13:35 | 13:45 | 0.17 | 17648 | 17659 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17648.00 t/17659.00, w/WOB 30,Flow 396.70, RPM 80, Press 5731.85, Tq 13.51, ROP 66.00
09/13/2021 | 13:45 | 14:15 | 0.5 | 17659 | 17667 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/17659.00 t/17667.00, TF -150, w/WOB 24.04,Flow 396.70, Press 5300, Tq 0, ROP 16.00
09/13/2021 | 14:15 | 14:57 | 0.7 | 17667 | 17742 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17667.00 t/17742.00, w/WOB 25.53,Flow 396.68, RPM 80, Press 5779.41, Tq 12.54, ROP 107.14
09/13/2021 | 14:57 | 15:02 | 0.08 | 17742 | 17742 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 15:02 | 15:52 | 0.83 | 17742 | 17838 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17742.00 t/17838.00, w/WOB 25.34,Flow 396.67, RPM 80, Press 5776.03, Tq 10.77, ROP 115.20
09/13/2021 | 15:52 | 16:01 | 0.15 | 17838 | 17838 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 16:01 | 16:53 | 0.87 | 17838 | 17932 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17838.00 t/17932.00, w/WOB 28.94,Flow 397.00, RPM 80, Press 5778.09, Tq 10.43, ROP 108.46, Diff 636.85, Temp 302.00
09/13/2021 | 16:53 | 16:59 | 0.1 | 17932 | 17932 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/13/2021 | 16:59 | 17:57 | 0.97 | 17932 | 18028 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17932.00 t/18028.00, w/WOB 28.58,Flow 396.81, RPM 80, Press 5704.18, Tq 8.92, ROP 99.31, Diff 562.94, Temp 303.80
09/13/2021 | 17:57 | 19:00 | 1.05 | 18028 | 18112 | 84 | LAT | 3: BHA 3 | 2K | Rotary Drill f/18028.00 t/18112.00, w/WOB 28.58,Flow 396.81, RPM 80.00, Press 5704.18, Tq 8.92, ROP 80.00, Diff 562.94, Temp 303.80
09/13/2021 | 19:00 | 22:00 | 3 | 18112 | 18112 | 0 | LAT | 3: BHA 3 | 5A | Circulate
09/13/2021 | 22:00 | 24:00 | 2 | 18112 | 18112 | 0 | LAT | 3: BHA 3 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_14_2021_DDR
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31161 / 20dd0221mg |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Redwood A1H
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Longitude: |  | 96° 37' 52.422" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/14/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 120830
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 18028 |  | 11063 |  | Csg Shoe MD(Usft): |  | 11053 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 18028 |  | 18028 |  | OD (in): |  | 10.75 |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  |  |  | 7049 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 22 | Viscosity: | 64
Slide Drilled (Usft): |  |  |  | 1155 | [5 empty] | 100: | 16 | Chlorides: | 57000
Rotary Drilled (Usft): |  |  |  | 5894 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.10 / 12.60
Drlg/Circ Hrs: |  |  |  | 63.57 / 14.73 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 75/25
Slide Drilling Hrs: |  |  |  | 21.9 |  | SN: |  | 13618580 |  | 10s Gel: | 8 | Weight (ppg): | 10.3
Rotary Drilling Hrs: |  |  |  | 41.67 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 127.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 141.46 / 52.74 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 8.5 |  | 98.25 |  | Grade In: |  | New
% Slide: |  |  |  | 16.39 |  | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
% Rotary: |  |  |  | 83.61 |  | Make / Model: |  | Security / 1187517
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  | Mike Chris |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Jesse Taylor |  | Chris Inman | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 +.008 |  |  |  | 5.5 | 2 |  |  | 45.3 |  | 33.11 |  | 34.11
BTI Valve |  |  |  | 4.875 | 2 |  |  | 45.45 |  | 1.65 |  | 35.76
NMPC |  |  |  | 5 | 2.688 |  |  | 52.08 |  | 9.6 |  | 45.36
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 4 |  | 49.36
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 51.23 |  | 29.28 |  | 78.64
NMPC |  |  |  | 5 | 2.688 |  |  | 52.91 |  | 9.45 |  | 88.09
NMDC (NO HARDBANDING) |  |  |  | 5 | 2.688 |  |  | 48.83 |  | 30.72 |  | 118.81
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.92 |  | 136.73
Filter Sub |  |  |  | 4.75 | 2.875 |  |  | 50 |  | 5.55 |  | 142.28
Crossover |  |  |  | 5.25 | 2.688 |  |  | 44.51 |  | 3.37 |  | 145.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 333.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 341.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2796.16
Agitator |  |  |  | 5.312 | 2.688 |  |  | 56.05 |  | 21.41 |  | 2817.57
2817.57
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250019 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 28.36 | 80 | 349 | 395.76 | 5658.22 | 4990.04 | 0 | 275.71 | 194.71 | 144.29 | 11.59 | 0
Run | 110.89 | 26.16 | 70.73 | 341 | 397.51 | 5396.6 | 4794.93 | 0 | 244.79 | 200.7 | 164.61 | 9.14 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Real Time Survey Management |  |  |  |  | 09/14/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/14/2021 |  | 14 |  | 2000 |  | 1 | 2000
Multi Rig Discount |  |  |  |  | 09/14/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/14/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 09/14/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/14/2021 | 00:00 | 07:00 | 7 | 18028 | 18028 | 0 | LAT | 3: BHA 3 | 6B | POOH
09/14/2021 | 07:00 | 08:30 | 1.5 | 18028 | 18028 | 0 | LAT | 3: BHA 3 | 6P | L/D BHA
09/14/2021 | 08:30 | 24:00 | 15.5 | 18028 | 18028 | 0 | LAT |  | 24B | Casing Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 391.92 (Usft)
Well: |  |  | Redwood A1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1125521 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/15/2021 | Depth In: |  | 108 | Total Drilled: |  | 3406.00 (Usft)
Date Out: |  |  | 07/16/2021 | Depth Out: |  | 3514 | Drilling / Circ Hours: |  | 6.98 / 3.68
Survey Offset: |  |  | 71
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47424 | U616S | 13.5 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | SD603251 | 13 Stab | 8.125 | 3 | 8.125 / 2.57 | 6 5/8 REG / 6 5/8 REG |  | 6.34 | 7.84
| 3 | PPM800067 | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 | 8 |  | 8.000 / 1.71 | 6 5/8 REG / 6 5/8 REG |  | 37.27 | 45.11
| 4 | SD55524 | NMPC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 8.58 | 53.69
| 5 | 775213 | UBHO Sub UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.66 | 57.35
| 6 | SD56120 | NMDC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 28.83 | 86.18
| 7 | SD55920 | NMDC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 28.99 | 115.17
| 8 | SD117248 | Crossover Sub | 6.75 | 2.875 | 6.750 / 1.44 | 4 1/2 IF / 6 5/8 REG |  | 2.13 | 117.3
| 9 |  | 9 Jts HWDP | 5 | 3 |  |  |  | 274.62 | 391.92
| 10 | [8 empty] | 391.92
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | U616S |  | 0-0-NO-A-X-I-NO-TD | 3406
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  | PDCI / 7/8 5.9 | 5.80 / 1.50 |  | 13 | 8.25 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 100 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.015
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 13 Stab | 13 |  | 0 |  |  | 3.21
3 |  |  | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 | 13 |  | 0 |  |  | 10.15

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2665.83 (Usft)
Well: |  |  | Redwood A1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 44.98 / 39.21 (klbs)
Job #: |  |  | LTX1125521 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 44.98 / 39.21 (klbs)
Date In: |  |  | 07/28/2021 | Depth In: |  | 3514 | Total Drilled: |  | 7549.00 (Usft)
Date Out: |  |  | 08/01/2021 | Depth Out: |  | 11063 | Drilling / Circ Hours: |  | 48.98 / 9.45
Survey Offset: |  |  | 64 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 55308 | SPL613 | 9.875 | 2 |  | 6 5/8 REG | 125.00 / 0.19 / 0.19 | 1.5 | 1.5
| 2 | PPM800001 | 7/8 5.9 2.00 Slick HPO -.013 | 8 | 2 | 8.000 / 1.80 | 6 5/8 REG / 6 5/8 REG | 100.00 / 3.80 / 3.99 | 38.05 | 39.55
| 3 | SD54514 | NMPC | 8 | 3.125 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 1.35 / 5.34 | 9.01 | 48.56
| 4 | 775182 | UBHO Sub | 7.75 | 3 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 0.56 / 5.90 | 3.73 | 52.29
| 5 | SD56223 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 4.48 / 10.38 | 29.84 | 82.13
| 6 | SD55704 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 4.44 / 14.82 | 29.58 | 111.71
| 7 | SD118418 | Crossover Sub | 7.875 | 2.875 | 6.750 / 1.48 | 4 1/2 XH / 6 5/8 REG | 100.00 / 0.31 / 15.12 | 3.06 | 114.77
| 8 |  | 6.5 DC 6 Jts | 6.5 | 2.375 |  | 4 1/2 XH / 4 1/2 XH | 95.00 / 17.79 / 32.91 | 187.23 | 302
| 9 | SD107702 | Crossover Sub | 6.5 | 2.875 |  | 4 1/2 IF / 4 1/2 XH | 95.00 / 0.25 / 33.16 | 2.67 | 304.67
| 10 |  | HWDP 9 Jts | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF | 43.00 / 11.82 / 44.98 | 274.85 | 579.52
| 11 |  | DP 22 Stds | 5 | 3.5 |  | 4 1/2 IF / 4 1/2 IF | 19.60 / 40.41 / 85.39 | 2061.7 | 2641.22
| 12 | PG675-0011 | Agitator | 6.75 | 3.75 | 6.750 / 1.84 | 4 1/2 IF / 4 1/2 IF | 80.00 / 1.97 / 87.36 | 24.61 | 2665.83
| 13 | [8 empty] | 2665.83
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New |  | 7549
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.00 Slick HPO -.013 |  |  | PDCI / 7/8 5.9 | 5.90 / 2.00 |  | 0 | 8.38 | 250 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 80 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.013
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2817.57 (Usft)
Well: |  |  | Redwood A1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 10.60 / 8.90 (klbs)
Job #: |  |  | LTX1125521 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 10.60 / 8.90 (klbs)
Date In: |  |  | 09/10/2021 | Depth In: |  | 11063 | Total Drilled: |  | 7049.00 (Usft)
Date Out: |  |  | 09/14/2021 | Depth Out: |  | 18028 | Drilling / Circ Hours: |  | 63.57 / 14.73
Survey Offset: |  |  | 68 | Gamma Offset: |  | 55
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618580 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250019 | 6/7 8.8 2.12 TS HS88 +.008 | 5.5 | 2 | 5.000 / 1.97 | XT39 / 3 1/2 Reg | 45.30 / 1.50 / 1.55 | 33.11 | 34.11
| 3 | BTI1 | BTI Valve | 4.875 | 2 |  | XT39 / XT39 | 45.45 / 0.08 / 1.63 | 1.65 | 35.76
| 4 | GT50-10-652 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 52.08 / 0.50 / 2.13 | 9.6 | 45.36
| 5 | 500048 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 12.50 / 0.05 / 2.18 | 4 | 49.36
| 6 | GT51-30-616 | NMDC (NO HARDBANDING) | 5.125 | 2.688 |  | XT39 / XT39 | 51.23 / 1.50 / 3.68 | 29.28 | 78.64
| 7 | GT50-10-585 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 52.91 / 0.50 / 4.18 | 9.45 | 88.09
| 8 | GT50-30-586 | NMDC (NO HARDBANDING) | 5 | 2.688 |  | XT39 / XT39 | 48.83 / 1.50 / 5.68 | 30.72 | 118.81
| 9 | A52123 | Tomax | 5.25 | 2.5 |  | XT39 / XT39 | 54.67 / 0.98 / 6.65 | 17.92 | 136.73
| 10 | GT50331343 | Filter Sub | 4.75 | 2.875 |  | XT39 / XT39 | 50.00 / 0.28 / 6.93 | 5.55 | 142.28
| 11 | GT52331431 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 | 44.51 / 0.15 / 7.08 | 3.37 | 145.65
| 12 | Rig | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.12 / 10.20 | 187.82 | 333.47
| 13 | 532 | Drill-N-Ream | 5.375 | 2.625 |  | CET43 / CET43 | 47.34 / 0.40 / 10.60 | 8.45 | 341.92
| 14 | Rig 26 | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 17.84 / 43.78 / 54.38 | 2454.24 | 2796.16
| 15 | PG525-0055 | Agitator | 5.312 | 2.688 |  | CET43 / CET43 | 56.05 / 1.20 / 55.58 | 21.41 | 2817.57
| 16 | [8 empty] | 2817.57
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | 1187517 | New | 1-2-CT-S-X-I-NO-TD | 7049
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 TS HS88 +.008 |  |  | PDCI / 6/7 8.8 | 4.03 / 2.12 |  | 0 | 5.62 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1200 | 80 |  | 200-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluid | HS88 |  | 0.008
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
PDCI
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31161 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Well: |  | Redwood A1H
|  |  |  | Longitude: |  | 96° 37' 52.422" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 92.00/106.96/120.00
Date In: |  | 07/15/2021 15:40 |  | SN: |  | PPM800067 |  |  |  | WOB Rotate (klbs): |  | 17.00
Date Out: |  | 07/16/2021 04:30 |  | Description: |  | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  |  | WOB Slide (klbs): |  | 7.12
Depth In/Out(Usft): |  | 108.00 / 3514.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 98.19
Inc In/Out: |  | 0.36 / 8.15 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 879.25
Azi In/Out: |  | 225.19 / 136.80 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1695.85
Total Drilled (Usft): |  | 3406 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 2050.94
%Slide (Ftg): |  | 9.42 |  | Bit to Bend (Usft): |  | 5.8 |  |  |  | Tq On Btm (kftlbs): |  | 8841.53
%Slide (Time): |  | 27.92 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 321 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 1.95 |  | Stab to Bit (Usft): |  | 2.31 |  |  |  | Bit Data
%Rotary (Ftg): |  | 90.58 |  | Kickpad OD (in): |  | 8.25 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 72.03 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 3085 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 5.03 |  | Length (Usft): |  | 37.27 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 6.98 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 3.68 / 12.83 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In:
Slide ROP (Usft/hr): |  | 164.62 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
Rot ROP (Usft/hr): |  | 613.32 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.015 |  |  |  | Drill Hrs: |  | 6.98
Avg ROP (Usft/hr): |  | 487.97 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.68
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
7 / 5 | 3 / 2 | 1 / 1 |  | 5.7/94.3 |  | 2 | 3 | 9.1 | 400 | WBM | 5.7 | 0.4 | 120
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
71 | [9 empty] | 5 |  | 6.00 / 1.43
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 47424 |  | 13.5 |  |  |  |  | 1.5 | 1.5
13 Stab 0.00 |  |  |  | SD603251 |  | 8.125 | 3 |  |  |  | 6.34 | 7.84
7/8 5.9 1.50 Stab HPO -.015 NBS 13 0.00 |  |  |  | PPM800067 |  | 8 |  |  |  |  | 37.27 | 45.11
NMPC 0.00 |  |  |  | SD55524 |  | 8 | 3.25 |  |  |  | 8.58 | 53.69
UBHO Sub UBHO Sub 0.00 |  |  |  | 775213 |  | 7.75 | 2.875 |  |  |  | 3.66 | 57.35
NMDC 0.00 |  |  |  | SD56120 |  | 8 | 3.25 |  |  |  | 28.83 | 86.18
NMDC 0.00 |  |  |  | SD55920 |  | 8 | 3.25 |  |  |  | 28.99 | 115.17
Crossover Sub 0.00 |  |  |  | SD117248 |  | 6.75 | 2.875 |  |  |  | 2.13 | 117.3
9 Jts HWDP 0.00 | [5 empty] | 5 | 3 |  |  |  | 274.62 | 391.92
-1.00 | [11 empty] | 391.92
Additional Comments
Reason POOH: TD Surface hole. POOH f/ Casing ops How did motor drain: Motor drained strong and was full of fluid Visual Wear: No visual wear was observed. Axial play in bearing was tight with little movement and approximately 1/16 inch play in thrust bearings Run description: Assembly drilled well and slides were yielding 6?s at best. In rotation it wanted to walk to the left off of a hole direction of 142. It dropped .4/100. Max Temp: 124 Stalls: 0 Motor Yield: 6?/100? Max Drilling Diff: 800 Average Drilling Diff: 500 Condition of bit: Bit graded 0-0 -NO-A-X-I-NO-TD. Bit and motor will be reran on next surface well
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31161 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Well: |  | Redwood A1H
|  |  |  | Longitude: |  | 96° 37' 52.422" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 124.00/197.89/252.00
Date In: |  | 07/28/2021 24:00 |  | SN: |  | PPM800001 |  |  |  | WOB Rotate (klbs): |  | 30.00
Date Out: |  | 08/01/2021 01:00 |  | Description: |  | 7/8 5.9 2.00 Slick HPO -.013 |  |  |  | WOB Slide (klbs): |  | 23.69
Depth In/Out(Usft): |  | 3514.00 / 11063.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 76.44
Inc In/Out: |  | 8.15 / 41.67 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 836.4
Azi In/Out: |  | 136.80 / 328.85 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 3911.63
Total Drilled (Usft): |  | 7549 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4639.53
%Slide (Ftg): |  | 14.70 |  | Bit to Bend (Usft): |  | 5.9 |  |  |  | Tq On Btm (kftlbs): |  | 12091.95
%Slide (Time): |  | 62.06 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1110 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 30.4 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 85.30 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 37.93 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6439 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 18.58 |  | Length (Usft): |  | 38.05 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 48.98 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 9.45 / 73.00 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 36.51 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 346.56 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.013 |  |  |  | Drill Hrs: |  | 48.98
Avg ROP (Usft/hr): |  | 154.12 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 9.45
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
41 / 25 | 19 / 13 | 6 / 5 |  | 69/31 |  | 16 | 9 | 9.7 | 70000 | OBM | 10.1 | 0.1 | 252
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
64 | 60 | [10 empty] | 0.00 / 7.98
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 55308 |  | 9.875 | 2 |  |  | 125 | 1.5 | 1.5
7/8 5.9 2.00 Slick HPO -.013 0.00 |  |  |  | PPM800001 |  | 8 | 2 |  |  | 100 | 38.05 | 39.55
NMPC 0.00 |  |  |  | SD54514 |  | 8 | 3.125 |  |  | 150 | 9.01 | 48.56
UBHO Sub 0.00 |  |  |  | 775182 |  | 7.75 | 3 |  |  | 150 | 3.73 | 52.29
NMDC 0.00 |  |  |  | SD56223 |  | 8 | 3.25 |  |  | 150 | 29.84 | 82.13
NMDC 0.00 |  |  |  | SD55704 |  | 8 | 3.25 |  |  | 150 | 29.58 | 111.71
Crossover Sub 0.00 |  |  |  | SD118418 |  | 7.875 | 2.875 |  |  | 100 | 3.06 | 114.77
6.5 DC 6 Jts 0.00 | [5 empty] | 6.5 | 2.375 |  |  | 95 | 187.23 | 302
Crossover Sub 0.00 |  |  |  | SD107702 |  | 6.5 | 2.875 |  |  | 95 | 2.67 | 304.67
HWDP 9 Jts 0.00 | [5 empty] | 5 | 3 |  |  | 43 | 274.85 | 579.52
DP 22 Stds 0.00 | [5 empty] | 5 | 3.5 |  |  | 19.6 | 2061.7 | 2641.22
Agitator 0.00 |  |  |  | PG675-0011 |  | 6.75 | 3.75 |  |  | 80 | 24.61 | 2665.83
0.00 | [11 empty] | 2665.83
Additional Comments
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1125521 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31161 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.704" N |  |  | Well: |  | Redwood A1H
|  |  |  | Longitude: |  | 96° 37' 52.422" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 228.00/273.82/303.80
Date In: |  | 09/10/2021 06:15 |  | SN: |  | PPM250019 |  |  |  | WOB Rotate (klbs): |  | 26.00
Date Out: |  | 09/14/2021 08:30 |  | Description: |  | 6/7 8.8 2.12 TS HS88 +.008 |  |  |  | WOB Slide (klbs): |  | 24.95
Depth In/Out(Usft): |  | 11063.00 / 18028.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 70.83
Inc In/Out: |  | 41.68 / 94.07 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 397.5
Azi In/Out: |  | 328.84 / 340.67 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4797.35
Total Drilled (Usft): |  | 7049 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5398.76
%Slide (Ftg): |  | 16.39 |  | Bit to Bend (Usft): |  | 4.03 |  |  |  | Tq On Btm (kftlbs): |  | 9.14
%Slide (Time): |  | 34.45 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 1155 |  | Bearing Gap (in): |  | 0.11 |  |  |  | Avg Diff Press (psi): |  | 1200
Slide Hours: |  | 21.9 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 83.61 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 65.55 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | 1187517
Rotary Drilled (Usft): |  | 5894 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 41.67 |  | Length (Usft): |  | 33.11 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 63.57 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 14.73 / 98.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 52.74 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-2-CT-S-X-I-NO-TD
Rot ROP (Usft/hr): |  | 141.44 |  | Stator Vendor/Type/Fit: |  | PV Fluid / HS88 / 0.008 |  |  |  | Drill Hrs: |  | 63.57
Avg ROP (Usft/hr): |  | 110.89 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 14.73
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
41 / 25 | 19 / 13 | 6 / 5 |  | 69/31 |  | 16 | 9 | 9.7 | 70000 | OBM | 10.1 | 0.1 | 303.8
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 55 | [8 empty] | 10 |  | 0.00 / 12.03
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618580 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 8.8 2.12 TS HS88 +.008 0.00 |  |  |  | PPM250019 |  | 5.5 | 2 |  |  | 45.3 | 33.11 | 34.11
BTI Valve 0.00 |  |  |  | BTI1 |  | 4.875 | 2 |  |  | 45.45 | 1.65 | 35.76
NMPC 0.00 |  |  |  | GT50-10-652 |  | 5 | 2.688 |  |  | 52.08 | 9.6 | 45.36
UBHO 0.00 |  |  |  | 500048 |  | 5.25 | 2.5 |  |  | 12.5 | 4 | 49.36
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT51-30-616 |  | 5.125 | 2.688 |  |  | 51.23 | 29.28 | 78.64
NMPC 0.00 |  |  |  | GT50-10-585 |  | 5 | 2.688 |  |  | 52.91 | 9.45 | 88.09
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT50-30-586 |  | 5 | 2.688 |  |  | 48.83 | 30.72 | 118.81
Tomax 0.00 |  |  |  | A52123 |  | 5.25 | 2.5 |  |  | 54.67 | 17.92 | 136.73
Filter Sub 0.00 |  |  |  | GT50331343 |  | 4.75 | 2.875 |  |  | 50 | 5.55 | 142.28
Crossover 0.00 |  |  |  | GT52331431 |  | 5.25 | 2.688 |  |  | 44.51 | 3.37 | 145.65
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3.8 |  |  | 16.6 | 187.82 | 333.47
Drill-N-Ream 0.00 |  |  |  | 532 |  | 5.375 | 2.625 |  |  | 47.34 | 8.45 | 341.92
26 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig 26 |  | 4.5 | 3.8 |  |  | 17.84 | 2454.24 | 2796.16
Agitator 0.00 |  |  |  | PG525-0055 |  | 5.312 | 2.688 |  |  | 56.05 | 21.41 | 2817.57
0.00 | [11 empty] | 2817.57
Additional Comments
Motor drained with minimum slack. Kick pad had crack and chipping. Motor was used to build the curve and drillout to TD. It would build hard anything over 95* and hold angle arouns 91*. We had two hard right turns during rotation (18-20 degress)
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3406
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 321
Well Name: |  |  |  |  | Redwood A1H |  |  | Survey / Gamma Offset: |  |  |  |  | 71.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 321.52 |  | Rotate: |  | 3085
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/15/2021 | 15:40 | 16:05 | 0.41667 | 108 | 269 | 161 | Rotate |  | 198 | 0.66 | 225.19 | 198 | -0.8 | -0.81 | -0.8 | 0.33 |  |  | 3 | 65 | 600 | 1500 | 386.4 | 600 | 380 | 220 | 92 | 70 | 65 | 60
07/15/2021 | 16:10 | 16:20 | 0.16667 | 269 | 361 | 92 | Rotate |  | 290 | 0.67 | 227.06 | 289.99 | -1.54 | -1.58 | -1.54 | 0.03 |  |  | 5 | 85 | 700 | 2500 | 552 | 800 | 650 | 150 | 95 | 70 | 65 | 60
07/15/2021 | 16:25 | 16:45 | 0.33333 | 361 | 485 | 124 | Rotate |  | 414 | 0.64 | 233.25 | 413.98 | -2.45 | -2.66 | -2.45 | 0.06 |  |  | 5 | 85 | 700 | 2500 | 372 | 800 | 650 | 150 | 95 | 70 | 65 | 60
07/15/2021 | 16:50 | 16:57 | 0.11667 | 485 | 579 | 94 | Rotate |  | 508 | 0.45 | 227.27 | 507.98 | -3.02 | -3.36 | -3.02 | 0.21 |  |  | 5 | 100 | 700 | 2500 | 805.71 | 1100 | 900 | 200 | 95 | 75 | 70 | 65
07/15/2021 | 17:01 | 17:11 | 0.16667 | 579 | 673 | 94 | Rotate |  | 602 | 0.75 | 211.25 | 601.97 | -3.79 | -3.95 | -3.79 | 0.36 |  |  | 5 | 100 | 700 | 2500 | 564 | 1100 | 900 | 200 | 95 | 75 | 70 | 65
07/15/2021 | 17:15 | 17:22 | 0.11667 | 673 | 767 | 94 | Rotate |  | 696 | 1.09 | 196.84 | 695.96 | -5.17 | -4.52 | -5.17 | 0.43 |  |  | 7 | 100 | 900 | 3000 | 805.71 | 1700 | 1300 | 400 | 97 | 75 | 70 | 65
07/15/2021 | 17:26 | 17:32 | 0.1 | 767 | 861 | 94 | Rotate |  | 790 | 1.22 | 192.81 | 789.94 | -7.01 | -5.01 | -7.01 | 0.16 |  |  | 10 | 100 | 900 | 6059 | 940 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 17:36 | 17:42 | 0.1 | 861 | 955 | 94 | Rotate |  | 884 | 1.01 | 198.94 | 883.92 | -8.77 | -5.5 | -8.77 | 0.26 |  |  | 10 | 100 | 900 | 6059 | 940 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 17:46 | 17:51 | 0.083333 | 955 | 1049 | 94 | Rotate |  | 978 | 1.14 | 200.51 | 977.91 | -10.42 | -6.09 | -10.42 | 0.14 |  |  | 10 | 100 | 900 | 6059 | 1128 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 17:54 | 18:00 | 0.1 | 1049 | 1143 | 94 | Rotate |  | 1072 | 1 | 214.5 | 1071.89 | -11.98 | -6.89 | -11.98 | 0.31 |  |  | 15 | 100 | 900 | 6227 | 940 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 18:04 | 18:10 | 0.1 | 1143 | 1237 | 94 | Rotate |  | 1166 | 0.92 | 206.13 | 1165.88 | -13.33 | -7.68 | -13.33 | 0.17 |  |  | 20 | 100 | 900 | 7591 | 940 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 18:15 | 18:23 | 0.13333 | 1237 | 1331 | 94 | Rotate |  | 1260 | 1.07 | 215.66 | 1259.86 | -14.72 | -8.53 | -14.72 | 0.24 |  |  | 18 | 100 | 900 | 8153 | 705 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 18:27 | 18:33 | 0.1 | 1331 | 1425 | 94 | Rotate |  | 1354 | 1.17 | 218.45 | 1353.84 | -16.19 | -9.63 | -16.19 | 0.12 |  |  | 20 | 100 | 900 | 8400 | 940 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 18:37 | 18:43 | 0.1 | 1425 | 1519 | 94 | Rotate |  | 1448 | 0.96 | 223.27 | 1447.83 | -17.51 | -10.77 | -17.51 | 0.24 |  |  | 20 | 100 | 900 | 8400 | 940 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 18:47 | 18:52 | 0.083333 | 1519 | 1534 | 15 | Slide | TTF: 135; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 1800 | 1600 | 200 | 99 | 95 | 90 | 85
07/15/2021 | 18:52 | 18:57 | 0.083333 | 1534 | 1614 | 80 | Rotate |  | 1543 | 1.07 | 199.39 | 1542.81 | -18.93 | -11.61 | -18.93 | 0.46 |  |  | 20 | 100 | 900 | 8400 | 960 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 19:01 | 19:06 | 0.083333 | 1614 | 1634 | 20 | Slide | TTF: 135; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 1800 | 1600 | 200 | 99 | 95 | 90 | 85
07/15/2021 | 19:06 | 19:14 | 0.13333 | 1634 | 1707 | 73 | Rotate |  | 1636 | 1.33 | 168.66 | 1635.79 | -20.8 | -11.69 | -20.8 | 0.73 |  |  | 20 | 100 | 900 | 8400 | 547.5 | 2000 | 1600 | 400 | 99 | 95 | 90 | 85
07/15/2021 | 19:18 | 19:23 | 0.083333 | 1707 | 1727 | 20 | Slide | TTF: 135; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 1800 | 1600 | 200 | 99 | 95 | 90 | 85
07/15/2021 | 19:23 | 19:31 | 0.13333 | 1727 | 1801 | 74 | Rotate |  | 1730 | 2.3 | 153.45 | 1729.75 | -23.56 | -10.63 | -23.56 | 1.14 |  |  | 20 | 100 | 900 | 8935 | 555 | 2000 | 1600 | 400 | 105 | 95 | 90 | 85
07/15/2021 | 19:36 | 19:41 | 0.083333 | 1801 | 1819 | 18 | Slide | TTF: 110; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 216 | 1800 | 1600 | 200 | 105 | 95 | 90 | 85
07/15/2021 | 19:41 | 19:48 | 0.11667 | 1819 | 1894 | 75 | Rotate |  | 1823 | 3.54 | 143.58 | 1822.62 | -27.54 | -8.09 | -27.54 | 1.43 |  |  | 24 | 100 | 900 | 10692 | 642.86 | 2000 | 1700 | 300 | 105 | 95 | 90 | 85
07/15/2021 | 19:53 | 19:58 | 0.083333 | 1894 | 1909 | 15 | Slide | TTF: -20; Drilling Parameters WOB: 6; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 1900 | 1700 | 200 | 105 | 95 | 90 | 85
07/15/2021 | 19:58 | 20:06 | 0.13333 | 1909 | 1988 | 79 | Rotate |  | 1917 | 4.38 | 139.96 | 1916.4 | -32.62 | -4.06 | -32.62 | 0.93 |  |  | 25 | 100 | 900 | 10692 | 592.5 | 2100 | 1700 | 400 | 105 | 95 | 90 | 85
07/15/2021 | 20:10 | 20:14 | 0.066667 | 1988 | 2003 | 15 | Slide | TTF: -20; Drilling Parameters WOB: 7; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 225 | 1900 | 1700 | 200 | 105 | 95 | 90 | 85
07/15/2021 | 20:14 | 20:22 | 0.13333 | 2003 | 2083 | 80 | Rotate |  | 2012 | 4.84 | 138.27 | 2011.09 | -38.39 | 0.94 | -38.39 | 0.5 |  |  | 28 | 100 | 900 | 10692 | 600 | 2100 | 1700 | 400 | 105 | 95 | 90 | 85
07/15/2021 | 20:26 | 20:36 | 0.16667 | 2083 | 2103 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 120 | 2000 | 1700 | 300 | 105 | 95 | 90 | 85
07/15/2021 | 20:36 | 20:46 | 0.16667 | 2103 | 2177 | 74 | Rotate |  | 2106 | 5.4 | 136.46 | 2104.72 | -44.56 | 6.63 | -44.56 | 0.62 |  |  | 28 | 100 | 900 | 10692 | 444 | 2100 | 1700 | 400 | 105 | 95 | 90 | 85
07/15/2021 | 20:51 | 21:00 | 0.15 | 2177 | 2197 | 20 | Slide | TTF: 10; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2100 | 1900 | 200 | 105 | 95 | 90 | 85
07/15/2021 | 21:00 | 21:08 | 0.13333 | 2197 | 2272 | 75 | Rotate |  | 2201 | 6.48 | 138.8 | 2199.21 | -51.83 | 13.24 | -51.83 | 1.16 |  |  | 30 | 100 | 900 | 10692 | 562.5 | 2500 | 1900 | 600 | 111 | 95 | 90 | 85
07/15/2021 | 21:13 | 21:18 | 0.083333 | 2272 | 2292 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 2100 | 1900 | 200 | 111 | 95 | 90 | 85
07/15/2021 | 21:18 | 21:26 | 0.13333 | 2292 | 2365 | 73 | Rotate |  | 2294 | 7.09 | 141.51 | 2291.55 | -60.27 | 20.27 | -60.27 | 0.74 |  |  | 30 | 100 | 900 | 10692 | 547.5 | 2500 | 1900 | 600 | 111 | 95 | 90 | 85
07/15/2021 | 21:34 | 21:42 | 0.13333 | 2365 | 2385 | 20 | Slide | TTF: -20; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2100 | 1900 | 200 | 111 | 95 | 90 | 85
07/15/2021 | 21:42 | 21:52 | 0.16667 | 2385 | 2459 | 74 | Rotate |  | 2388 | 7.92 | 139.89 | 2384.75 | -69.77 | 28.05 | -69.77 | 0.91 |  |  | 32 | 100 | 900 | 12467 | 444 | 2500 | 1900 | 600 | 111 | 95 | 90 | 85
07/15/2021 | 21:57 | 22:05 | 0.13333 | 2459 | 2479 | 20 | Slide | TTF: -10; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2100 | 1900 | 200 | 111 | 95 | 90 | 85
07/15/2021 | 22:05 | 22:12 | 0.11667 | 2479 | 2553 | 74 | Rotate |  | 2482 | 9.07 | 136.17 | 2477.72 | -80.07 | 37.36 | -80.07 | 1.36 |  |  | 30 | 100 | 900 | 12500 | 634.29 | 2500 | 1900 | 600 | 111 | 95 | 90 | 85
07/15/2021 | 22:16 | 22:23 | 0.11667 | 2553 | 2571 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 154.29 | 2100 | 2000 | 100 | 114 | 95 | 90 | 85
07/15/2021 | 22:23 | 22:30 | 0.11667 | 2571 | 2646 | 75 | Rotate |  | 2575 | 10.07 | 137.56 | 2569.42 | -91.35 | 47.92 | -91.35 | 1.1 |  |  | 32 | 100 | 900 | 11611 | 642.86 | 2500 | 2000 | 500 | 114 | 95 | 90 | 85
07/15/2021 | 22:35 | 22:44 | 0.15 | 2646 | 2740 | 94 | Rotate |  | 2669 | 10.18 | 136.84 | 2661.96 | -103.48 | 59.15 | -103.48 | 0.18 |  |  | 33 | 100 | 900 | 12505 | 626.67 | 2500 | 2000 | 500 | 114 | 120 | 115 | 110
07/15/2021 | 22:49 | 22:57 | 0.13333 | 2740 | 2835 | 95 | Rotate |  | 2764 | 9.75 | 136.7 | 2755.52 | -115.46 | 70.41 | -115.46 | 0.45 |  |  | 34 | 100 | 900 | 10848 | 712.5 | 2500 | 2000 | 500 | 114 | 120 | 115 | 110
07/15/2021 | 23:02 | 23:08 | 0.1 | 2835 | 2855 | 20 | Slide | TTF: 20; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 200 | 2200 | 2000 | 200 | 114 | 120 | 115 | 110
07/15/2021 | 23:08 | 23:16 | 0.13333 | 2855 | 2929 | 74 | Rotate |  | 2858 | 10.18 | 137.06 | 2848.1 | -127.33 | 81.52 | -127.33 | 0.46 |  |  | 34 | 100 | 900 | 10848 | 555 | 2500 | 2000 | 500 | 116 | 120 | 115 | 110
07/15/2021 | 23:20 | 23:28 | 0.13333 | 2929 | 3024 | 95 | Rotate |  | 2953 | 10.19 | 138.25 | 2941.61 | -139.75 | 92.84 | -139.75 | 0.22 |  |  | 33 | 100 | 900 | 12222 | 712.5 | 2500 | 2000 | 500 | 116 | 120 | 115 | 110
07/15/2021 | 23:33 | 23:41 | 0.13333 | 3024 | 3117 | 93 | Rotate |  | 3046 | 9.84 | 135.63 | 3033.19 | -151.56 | 103.87 | -151.56 | 0.62 |  |  | 32 | 100 | 900 | 11840 | 697.5 | 2500 | 2000 | 500 | 116 | 120 | 115 | 110
07/15/2021 | 23:46 | 23:55 | 0.15 | 3117 | 3137 | 20 | Slide | TTF: 30; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2200 | 2000 | 200 | 116 | 120 | 115 | 110
07/15/2021 | 23:55 | 24:00 | 0.083333 | 3137 | 3174 | 37 | Rotate |  | 3140 | 9.44 | 133.49 | 3125.86 | -162.61 | 115.08 | -162.61 | 0.57 |  |  | 33 | 100 | 900 | 9564 | 444 | 2500 | 2000 | 500 | 116 | 120 | 115 | 110
07/16/2021 | 00:00 | 00:03 | 0.05 | 3174 | 3211 | 37 | Rotate | Drilling Parameters WOB: 33; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 9564; Drilling Parameters ROP: 740 | 2500 | 2000 | 500 | 116 | 120 | 115 | 110
07/16/2021 | 00:08 | 00:17 | 0.15 | 3211 | 3231 | 20 | Slide | TTF: 20; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2200 | 2000 | 200 | 120 | 120 | 115 | 110
07/16/2021 | 00:17 | 00:26 | 0.15 | 3231 | 3305 | 74 | Rotate |  | 3234 | 9.01 | 135.32 | 3218.65 | -173.15 | 125.85 | -173.15 | 0.55 |  |  | 33 | 100 | 900 | 11741 | 493.33 | 2500 | 2000 | 500 | 120 | 120 | 115 | 110
07/16/2021 | 00:31 | 00:40 | 0.15 | 3305 | 3325 | 20 | Slide | TTF: 30; Drilling Parameters WOB: 14; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2300 | 2000 | 300 | 120 | 120 | 115 | 110
07/16/2021 | 00:40 | 00:48 | 0.13333 | 3325 | 3398 | 73 | Rotate |  | 3327 | 8.87 | 138.61 | 3310.52 | -183.71 | 135.71 | -183.71 | 0.57 |  |  | 35 | 100 | 900 | 15625 | 547.5 | 2600 | 2000 | 600 | 120 | 120 | 115 | 110
07/16/2021 | 00:53 | 01:01 | 0.13333 | 3398 | 3418 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 14; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2200 | 2000 | 200 | 120 | 120 | 115 | 110
07/16/2021 | 01:01 | 01:15 | 0.23333 | 3418 | 3514 | 96 | Rotate |  | 3443 | 8.56 | 138.7 | 3425.18 | -196.9 | 147.32 | -196.9 | 0.27 |  |  | 35 | 100 | 900 | 15625 | 411.43 | 2600 | 2000 | 600 | 120 | 120 | 115 | 110

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7549
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1110
Well Name: |  |  |  |  | Redwood A1H |  |  | Survey / Gamma Offset: |  |  |  |  | 64.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 321.52 |  | Rotate: |  | 6439
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/29/2021 | 06:50 | 07:08 | 0.3 | 3514 | 3606 | 92 | Rotate |  | 3541 | 8 | 136.03 | 3522.16 | -207.29 | 156.87 | -207.29 | 0.69 |  |  | 25 | 30 | 520 | 7000 | 306.67 | 1900 | 1500 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 07:08 | 07:16 | 0.13333 | 3606 | 3616 | 10 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 650; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 75 | 2400 | 1900 | 500 | 124 | 155 | 145 | 135
07/29/2021 | 07:16 | 07:26 | 0.16667 | 3616 | 3700 | 84 | Rotate |  | 3636 | 8.3 | 134.01 | 3616.2 | -216.81 | 166.39 | -216.81 | 0.44 |  |  | 25 | 60 | 650 | 7000 | 504 | 2400 | 1900 | 500 | 124 | 155 | 145 | 135
07/29/2021 | 07:30 | 07:40 | 0.16667 | 3700 | 3710 | 10 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 850; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 60 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 07:40 | 07:48 | 0.13333 | 3710 | 3793 | 83 | Rotate |  | 3729 | 8.71 | 138.68 | 3708.18 | -226.76 | 175.87 | -226.76 | 0.86 |  |  | 25 | 80 | 850 | 7000 | 622.5 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 07:52 | 08:00 | 0.13333 | 3793 | 3808 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 850; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 112.5 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 08:00 | 08:07 | 0.11667 | 3808 | 3887 | 79 | Rotate |  | 3823 | 9.74 | 147.9 | 3800.96 | -238.85 | 184.8 | -238.85 | 1.91 |  |  | 25 | 80 | 850 | 7000 | 677.14 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 08:11 | 08:21 | 0.16667 | 3887 | 3902 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 850; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 90 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 08:21 | 08:30 | 0.15 | 3902 | 3981 | 79 | Rotate |  | 3917 | 9.95 | 153.73 | 3893.58 | -252.86 | 192.62 | -252.86 | 1.08 |  |  | 20 | 80 | 850 | 7000 | 526.67 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 08:34 | 08:47 | 0.21667 | 3981 | 3996 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 850; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 69.23 | 4000 | 3600 | 400 | 124 | 155 | 145 | 135
07/29/2021 | 08:47 | 08:56 | 0.15 | 3996 | 4075 | 79 | Rotate |  | 4011 | 11.21 | 152.8 | 3985.98 | -268.27 | 200.39 | -268.27 | 1.35 |  |  | 30 | 80 | 850 | 9000 | 526.67 | 4400 | 3800 | 600 | 130 | 160 | 150 | 140
07/29/2021 | 09:00 | 09:06 | 0.1 | 4075 | 4169 | 94 | Rotate |  | 4105 | 11.75 | 152.19 | 4078.1 | -284.87 | 209.03 | -284.87 | 0.59 |  |  | 30 | 80 | 850 | 9000 | 940 | 4400 | 3800 | 600 | 130 | 160 | 150 | 140
07/29/2021 | 09:10 | 09:17 | 0.11667 | 4169 | 4263 | 94 | Rotate |  | 4199 | 11.25 | 152.1 | 4170.21 | -301.44 | 217.78 | -301.44 | 0.53 |  |  | 35 | 80 | 875 | 9000 | 805.71 | 4400 | 3800 | 600 | 153 | 160 | 150 | 140
07/29/2021 | 09:21 | 09:29 | 0.13333 | 4263 | 4356 | 93 | Rotate |  | 4292 | 10.94 | 149.61 | 4261.48 | -317.07 | 226.49 | -317.07 | 0.61 |  |  | 35 | 80 | 875 | 9000 | 697.5 | 4400 | 3800 | 600 | 153 | 160 | 150 | 140
07/29/2021 | 09:33 | 09:42 | 0.15 | 4356 | 4450 | 94 | Rotate |  | 4386 | 10.72 | 148.37 | 4353.8 | -332.2 | 235.59 | -332.2 | 0.34 |  |  | 35 | 80 | 875 | 9000 | 626.67 | 4400 | 3800 | 600 | 153 | 160 | 150 | 140
07/29/2021 | 09:46 | 09:53 | 0.11667 | 4450 | 4465 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 128.57 | 4400 | 3800 | 600 | 153 | 160 | 150 | 140
07/29/2021 | 09:53 | 10:02 | 0.15 | 4465 | 4543 | 78 | Rotate |  | 4479 | 11.85 | 148.04 | 4445 | -347.67 | 245.18 | -347.67 | 1.22 |  |  | 35 | 80 | 875 | 9000 | 520 | 4400 | 3800 | 600 | 160 | 160 | 150 | 140
07/29/2021 | 10:06 | 10:15 | 0.15 | 4543 | 4638 | 95 | Rotate |  | 4574 | 12.2 | 147.64 | 4537.92 | -364.42 | 255.72 | -364.42 | 0.38 |  |  | 35 | 80 | 875 | 9000 | 633.33 | 4600 | 4000 | 600 | 160 | 160 | 150 | 140
07/29/2021 | 10:19 | 10:28 | 0.15 | 4638 | 4733 | 95 | Rotate |  | 4669 | 12.23 | 145.75 | 4630.77 | -381.22 | 266.75 | -381.22 | 0.42 |  |  | 35 | 80 | 875 | 9000 | 633.33 | 4600 | 4000 | 600 | 160 | 160 | 150 | 140
07/29/2021 | 10:32 | 10:39 | 0.11667 | 4733 | 4827 | 94 | Rotate |  | 4763 | 11.92 | 143.2 | 4722.69 | -397.22 | 278.17 | -397.22 | 0.66 |  |  | 35 | 80 | 875 | 9000 | 805.71 | 4600 | 4000 | 600 | 160 | 160 | 150 | 140
07/29/2021 | 10:43 | 10:51 | 0.13333 | 4827 | 4920 | 93 | Rotate |  | 4856 | 11.12 | 144.2 | 4813.81 | -412.19 | 289.17 | -412.19 | 0.89 |  |  | 35 | 80 | 875 | 9000 | 697.5 | 4600 | 4000 | 600 | 169 | 160 | 150 | 140
07/29/2021 | 10:55 | 11:04 | 0.15 | 4920 | 5015 | 95 | Rotate |  | 4951 | 10.82 | 142.76 | 4907.08 | -426.72 | 299.93 | -426.72 | 0.43 |  |  | 40 | 80 | 875 | 9000 | 633.33 | 4800 | 4000 | 800 | 172 | 160 | 150 | 140
07/29/2021 | 11:08 | 11:17 | 0.15 | 5015 | 5109 | 94 | Rotate |  | 5045 | 10.49 | 142.08 | 4999.46 | -440.49 | 310.53 | -440.49 | 0.38 |  |  | 40 | 80 | 875 | 9000 | 626.67 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 11:21 | 11:32 | 0.18333 | 5109 | 5202 | 93 | Rotate |  | 5138 | 9.89 | 140.62 | 5090.99 | -453.34 | 320.8 | -453.34 | 0.7 |  |  | 35 | 80 | 700 | 11000 | 507.27 | 3300 | 2700 | 600 | 174 | 185 | 170 | 160
07/29/2021 | 11:36 | 11:47 | 0.18333 | 5202 | 5296 | 94 | Rotate |  | 5232 | 9.58 | 137.6 | 5183.64 | -465.36 | 331.19 | -465.36 | 0.64 |  |  | 35 | 80 | 700 | 10000 | 512.73 | 3300 | 2700 | 600 | 174 | 185 | 170 | 160
07/29/2021 | 11:51 | 12:01 | 0.16667 | 5296 | 5311 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 90 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 12:01 | 12:11 | 0.16667 | 5311 | 5390 | 79 | Rotate |  | 5326 | 9.94 | 139.75 | 5276.28 | -477.33 | 341.71 | -477.33 | 0.54 |  |  | 40 | 80 | 875 | 9000 | 474 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 12:15 | 12:25 | 0.16667 | 5390 | 5405 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 90 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 12:25 | 12:34 | 0.15 | 5405 | 5484 | 79 | Rotate |  | 5420 | 10.35 | 143.5 | 5368.81 | -490.31 | 351.97 | -490.31 | 0.83 |  |  | 40 | 80 | 875 | 9000 | 526.67 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 12:38 | 12:47 | 0.15 | 5484 | 5578 | 94 | Rotate |  | 5514 | 9.86 | 142.9 | 5461.35 | -503.52 | 361.85 | -503.52 | 0.53 |  |  | 40 | 80 | 875 | 9000 | 626.67 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 12:51 | 12:59 | 0.13333 | 5578 | 5671 | 93 | Rotate |  | 5607 | 10.21 | 142 | 5552.93 | -516.36 | 371.73 | -516.36 | 0.41 |  |  | 40 | 80 | 875 | 9000 | 697.5 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 13:03 | 13:12 | 0.15 | 5671 | 5764 | 93 | Rotate |  | 5700 | 10.45 | 140.65 | 5644.42 | -529.38 | 382.15 | -529.38 | 0.37 |  |  | 40 | 80 | 875 | 9000 | 620 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 13:16 | 13:24 | 0.13333 | 5764 | 5858 | 94 | Rotate |  | 5794 | 9.18 | 140.68 | 5737.04 | -541.77 | 392.31 | -541.77 | 1.35 |  |  | 40 | 80 | 875 | 9000 | 705 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 13:28 | 13:36 | 0.13333 | 5858 | 5952 | 94 | Rotate |  | 5888 | 8.05 | 137.83 | 5829.98 | -552.45 | 401.48 | -552.45 | 1.28 |  |  | 40 | 80 | 875 | 9000 | 705 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 13:40 | 13:50 | 0.16667 | 5952 | 5967 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 90 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 13:50 | 13:58 | 0.13333 | 5967 | 6046 | 79 | Rotate |  | 5982 | 8.54 | 136.98 | 5923 | -562.43 | 410.66 | -562.43 | 0.54 |  |  | 40 | 80 | 875 | 9000 | 592.5 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 14:02 | 14:12 | 0.16667 | 6046 | 6061 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 90 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 14:12 | 14:22 | 0.16667 | 6061 | 6140 | 79 | Rotate |  | 6076 | 9.84 | 137.24 | 6015.79 | -573.43 | 420.87 | -573.43 | 1.38 |  |  | 40 | 80 | 875 | 9000 | 474 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 14:26 | 14:47 | 0.35 | 6140 | 6155 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 42.86 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 14:47 | 14:57 | 0.16667 | 6155 | 6233 | 78 | Rotate |  | 6169 | 9.94 | 140.35 | 6107.41 | -585.45 | 431.39 | -585.45 | 0.58 |  |  | 40 | 80 | 875 | 9000 | 468 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 15:01 | 15:21 | 0.33333 | 6233 | 6248 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 45 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 15:21 | 15:29 | 0.13333 | 6248 | 6327 | 79 | Rotate |  | 6263 | 8.91 | 138.58 | 6200.14 | -597.15 | 441.38 | -597.15 | 1.14 |  |  | 40 | 80 | 875 | 9000 | 592.5 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 15:43 | 16:10 | 0.45 | 6327 | 6342 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 33.33 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 16:10 | 16:18 | 0.13333 | 6342 | 6421 | 79 | Rotate |  | 6357 | 8.5 | 134.86 | 6293.05 | -607.51 | 451.12 | -607.51 | 0.74 |  |  | 40 | 80 | 875 | 9000 | 592.5 | 4800 | 4000 | 800 | 174 | 160 | 150 | 140
07/29/2021 | 16:22 | 16:55 | 0.55 | 6421 | 6436 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 27.27 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 16:55 | 17:08 | 0.21667 | 6436 | 6516 | 80 | Rotate |  | 6452 | 8.28 | 137.71 | 6387.04 | -617.53 | 460.7 | -617.53 | 0.5 |  |  | 25 | 80 | 875 | 9000 | 369.23 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 17:40 | 17:50 | 0.16667 | 6516 | 6535 | 19 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 114 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 17:50 | 18:30 | 0.66667 | 6535 | 6547 | 12 | Slide | 20 | 6546 | 8.32 | 135.25 | 6480.05 | -627.36 | 470.05 | -627.36 | 0.38 |  |  | 25 | 80 | 875 | 9000 | 18 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 18:30 | 18:50 | 0.33333 | 6547 | 6610 | 63 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 189 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 18:55 | 19:00 | 0.083333 | 6610 | 6625 | 15 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 180 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 19:00 | 19:45 | 0.75 | 6625 | 6640 | 15 | Slide | TTF: 20; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 20 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 19:45 | 19:55 | 0.16667 | 6640 | 6715 | 75 | Rotate |  | 6640 | 7.96 | 136.43 | 6573.11 | -636.91 | 479.32 | -636.91 | 0.42 |  |  | 25 | 80 | 875 | 9000 | 450 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 20:00 | 20:45 | 0.75 | 6715 | 6735 | 20 | Slide | 20 | 6734 | 8.41 | 141.21 | 6666.15 | -646.98 | 488.11 | -646.98 | 0.87 |  |  | 25 | 80 | 875 | 9000 | 26.67 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 20:45 | 21:05 | 0.33333 | 6735 | 6798 | 63 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 189 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 21:10 | 21:15 | 0.083333 | 6798 | 6810 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 144 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 21:15 | 21:50 | 0.58333 | 6810 | 6828 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 875; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 30.86 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 21:50 | 22:20 | 0.5 | 6828 | 6905 | 77 | Rotate |  | 6828 | 9.14 | 150.58 | 6759.05 | -658.84 | 496.09 | -658.84 | 1.7 |  |  | 25 | 80 | 875 | 9000 | 154 | 4800 | 4000 | 800 | 202 | 160 | 150 | 140
07/29/2021 | 22:25 | 22:50 | 0.41667 | 6905 | 6912 | 7 | Slide | TTF: -30; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 16.8 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/29/2021 | 22:50 | 23:05 | 0.25 | 6912 | 6986 | 74 | Rotate |  | 6922 | 10.81 | 149.87 | 6851.63 | -672.97 | 504.18 | -672.97 | 1.78 |  |  | 25 | 80 | 825 | 9000 | 296 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/29/2021 | 23:10 | 23:25 | 0.25 | 6986 | 7080 | 94 | Rotate |  | 7016 | 10.62 | 148.93 | 6943.99 | -688.02 | 513.07 | -688.02 | 0.27 |  |  | 25 | 80 | 825 | 9000 | 376 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/29/2021 | 23:30 | 23:40 | 0.16667 | 7080 | 7174 | 94 | Rotate |  | 7110 | 10.54 | 146.43 | 7036.39 | -702.6 | 522.3 | -702.6 | 0.5 |  |  | 25 | 80 | 825 | 9000 | 564 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/29/2021 | 23:45 | 24:00 | 0.25 | 7174 | 7268 | 94 | Rotate |  | 7204 | 10.11 | 144.91 | 7128.87 | -716.51 | 531.8 | -716.51 | 0.54 |  |  | 25 | 80 | 825 | 9000 | 376 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 00:05 | 00:20 | 0.25 | 7268 | 7361 | 93 | Rotate |  | 7297 | 9.73 | 144.79 | 7220.48 | -729.61 | 541.02 | -729.61 | 0.41 |  |  | 25 | 80 | 825 | 9000 | 372 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 00:25 | 00:30 | 0.083333 | 7361 | 7372 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 132 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 00:30 | 00:45 | 0.25 | 7372 | 7382 | 10 | Slide | TTF: -20; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 40 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 00:45 | 01:00 | 0.25 | 7382 | 7455 | 73 | Rotate |  | 7391 | 9.56 | 142.3 | 7313.15 | -742.28 | 550.37 | -742.28 | 0.48 |  |  | 25 | 80 | 825 | 9000 | 292 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 01:05 | 01:10 | 0.083333 | 7455 | 7465 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 120 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 01:10 | 01:45 | 0.58333 | 7465 | 7477 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 20.57 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 01:45 | 02:00 | 0.25 | 7477 | 7550 | 73 | Rotate |  | 7486 | 9.32 | 139.8 | 7406.87 | -754.4 | 560.16 | -754.4 | 0.5 |  |  | 25 | 80 | 825 | 9000 | 292 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 02:05 | 02:10 | 0.083333 | 7550 | 7565 | 15 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 180 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 02:10 | 02:50 | 0.66667 | 7565 | 7577 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 18 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 02:50 | 03:05 | 0.25 | 7577 | 7645 | 68 | Rotate |  | 7581 | 8.45 | 138.52 | 7500.73 | -765.5 | 569.75 | -765.5 | 0.94 |  |  | 25 | 80 | 825 | 9000 | 272 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 03:10 | 03:15 | 0.083333 | 7645 | 7655 | 10 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 120 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 03:15 | 03:50 | 0.58333 | 7655 | 7675 | 20 | Slide | 0 | 7675 | 9.38 | 141.1 | 7593.59 | -776.64 | 579.14 | -776.64 | 1.08 |  |  | 25 | 80 | 825 | 9000 | 34.29 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 03:50 | 04:00 | 0.16667 | 7675 | 7739 | 64 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 384 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 04:05 | 04:20 | 0.25 | 7739 | 7832 | 93 | Rotate |  | 7768 | 8.56 | 141.52 | 7685.45 | -787.95 | 588.2 | -787.95 | 0.88 |  |  | 25 | 80 | 825 | 9000 | 372 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 04:25 | 04:30 | 0.083333 | 7832 | 7845 | 13 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 156 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 04:30 | 05:00 | 0.5 | 7845 | 7855 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 20 | 4300 | 3500 | 800 | 210 | 230 | 215 | 195
07/30/2021 | 05:00 | 05:25 | 0.41667 | 7855 | 7925 | 70 | Rotate |  | 7861 | 8.1 | 140.75 | 7777.47 | -798.45 | 596.65 | -798.45 | 0.51 |  |  | 40 | 80 | 825 | 9000 | 168 | 5000 | 4200 | 800 | 221 | 230 | 215 | 195
07/30/2021 | 05:30 | 05:35 | 0.083333 | 7925 | 7935 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 120 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 05:35 | 06:34 | 0.98333 | 7935 | 7955 | 20 | Slide | 0 | 7955 | 8.71 | 136.04 | 7870.46 | -808.7 | 605.78 | -808.7 | 0.98 |  |  | 20 | 80 | 825 | 18000 | 20.34 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 06:34 | 06:44 | 0.16667 | 7955 | 8019 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 384 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 06:48 | 07:35 | 0.78333 | 8019 | 8034 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 19.15 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 07:35 | 07:48 | 0.21667 | 8034 | 8113 | 79 | Rotate |  | 8049 | 7.67 | 139.11 | 7963.5 | -818.56 | 614.83 | -818.56 | 1.2 |  |  | 40 | 80 | 825 | 18000 | 364.62 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 07:52 | 08:11 | 0.31667 | 8113 | 8133 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 63.16 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 08:11 | 08:25 | 0.23333 | 8133 | 8208 | 75 | Rotate |  | 8144 | 8.05 | 142.22 | 8057.61 | -828.61 | 623.06 | -828.61 | 0.6 |  |  | 40 | 80 | 825 | 18000 | 321.43 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 09:44 | 10:07 | 0.38333 | 8208 | 8228 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 52.17 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 10:07 | 10:19 | 0.2 | 8228 | 8301 | 73 | Rotate |  | 8237 | 6.69 | 141.6 | 8149.84 | -838.01 | 630.41 | -838.01 | 1.46 |  |  | 40 | 80 | 825 | 18000 | 365 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 10:23 | 10:58 | 0.58333 | 8301 | 8316 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 25.71 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 10:58 | 11:10 | 0.2 | 8316 | 8395 | 79 | Rotate |  | 8331 | 6.14 | 141.12 | 8243.25 | -846.21 | 636.97 | -846.21 | 0.59 |  |  | 40 | 80 | 825 | 18000 | 395 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 11:14 | 11:42 | 0.46667 | 8395 | 8415 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 42.86 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 11:42 | 11:56 | 0.23333 | 8415 | 8490 | 75 | Rotate |  | 8426 | 7.14 | 142.84 | 8337.61 | -854.87 | 643.72 | -854.87 | 1.07 |  |  | 40 | 80 | 825 | 18000 | 321.43 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 12:00 | 12:25 | 0.41667 | 8490 | 8505 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 36 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 12:25 | 12:38 | 0.21667 | 8505 | 8584 | 79 | Rotate |  | 8520 | 6.83 | 140.84 | 8430.91 | -863.86 | 650.78 | -863.86 | 0.42 |  |  | 40 | 80 | 825 | 18000 | 364.62 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 12:42 | 12:56 | 0.23333 | 8584 | 8678 | 94 | Rotate |  | 8614 | 5.41 | 141.48 | 8524.38 | -871.66 | 657.07 | -871.66 | 1.51 |  |  | 40 | 80 | 825 | 18000 | 402.86 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 13:00 | 13:11 | 0.18333 | 8678 | 8773 | 95 | Rotate |  | 8709 | 3.83 | 143.04 | 8619.06 | -877.7 | 661.77 | -877.7 | 1.67 |  |  | 40 | 80 | 825 | 18000 | 518.18 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 13:15 | 13:28 | 0.21667 | 8773 | 8866 | 93 | Rotate |  | 8802 | 2.95 | 148.19 | 8711.9 | -882.22 | 664.9 | -882.22 | 1 |  |  | 40 | 80 | 825 | 18000 | 429.23 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 13:32 | 13:43 | 0.18333 | 8866 | 8961 | 95 | Rotate |  | 8897 | 3.59 | 159.43 | 8806.75 | -887.08 | 667.23 | -887.08 | 0.95 |  |  | 40 | 80 | 825 | 18000 | 518.18 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 13:47 | 13:57 | 0.16667 | 8961 | 9034 | 73 | Rotate |  | 8990 | 2.17 | 164.15 | 8899.63 | -891.5 | 668.73 | -891.5 | 1.55 |  |  | 40 | 80 | 825 | 18000 | 438 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 13:57 | 14:54 | 0.95 | 9034 | 9054 | 20 | Slide | TTF: 320; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 21.05 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 14:58 | 15:11 | 0.21667 | 9054 | 9148 | 94 | Rotate |  | 9084 | 1.25 | 173.22 | 8993.58 | -894.23 | 669.34 | -894.23 | 1.02 |  |  | 40 | 80 | 825 | 18000 | 433.85 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 15:15 | 15:26 | 0.18333 | 9148 | 9242 | 94 | Rotate |  | 9178 | 0.94 | 211.03 | 9087.57 | -895.91 | 669.07 | -895.91 | 0.82 |  |  | 40 | 80 | 825 | 18000 | 512.73 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 15:30 | 16:00 | 0.5 | 9242 | 9257 | 15 | Slide | TTF: 130; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 30 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 16:00 | 16:17 | 0.28333 | 9257 | 9336 | 79 | Rotate |  | 9272 | 0.98 | 212.51 | 9181.55 | -897.25 | 668.24 | -897.25 | 0.05 |  |  | 40 | 80 | 825 | 18000 | 278.82 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 16:21 | 16:32 | 0.18333 | 9336 | 9429 | 93 | Rotate |  | 9365 | 1.21 | 241.29 | 9274.54 | -898.39 | 666.95 | -898.39 | 0.63 |  |  | 40 | 80 | 825 | 18000 | 507.27 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 16:36 | 16:48 | 0.2 | 9429 | 9523 | 94 | Rotate |  | 9459 | 2.49 | 272.95 | 9368.49 | -898.76 | 664.04 | -898.76 | 1.69 |  |  | 40 | 80 | 825 | 18000 | 470 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 16:52 | 17:03 | 0.18333 | 9523 | 9617 | 94 | Rotate |  | 9553 | 3.69 | 279.06 | 9462.35 | -898.18 | 659.01 | -898.18 | 1.32 |  |  | 40 | 80 | 825 | 18000 | 512.73 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 17:07 | 17:28 | 0.35 | 9617 | 9711 | 94 | Rotate |  | 9647 | 4.96 | 290.49 | 9556.08 | -896.28 | 652.22 | -896.28 | 1.63 |  |  | 40 | 80 | 825 | 18000 | 268.57 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 17:32 | 17:46 | 0.23333 | 9711 | 9804 | 93 | Rotate |  | 9740 | 4.58 | 297.07 | 9648.76 | -893.18 | 645.14 | -893.18 | 0.72 |  |  | 40 | 80 | 825 | 18000 | 398.57 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 17:50 | 18:03 | 0.21667 | 9804 | 9898 | 94 | Rotate |  | 9834 | 3.9 | 293.57 | 9742.5 | -890.2 | 638.87 | -890.2 | 0.77 |  |  | 40 | 80 | 825 | 18000 | 433.85 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 18:07 | 18:30 | 0.38333 | 9898 | 9992 | 94 | Rotate |  | 9928 | 3.09 | 294.81 | 9836.33 | -887.86 | 633.64 | -887.86 | 0.87 |  |  | 40 | 80 | 825 | 18000 | 245.22 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 18:35 | 19:00 | 0.41667 | 9992 | 10085 | 93 | Rotate |  | 10021 | 2.34 | 297.94 | 9929.22 | -885.91 | 629.69 | -885.91 | 0.82 |  |  | 40 | 80 | 825 | 18000 | 223.2 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 19:05 | 19:40 | 0.58333 | 10085 | 10179 | 94 | Rotate |  | 10115 | 2 | 303.57 | 10023.16 | -884.11 | 626.63 | -884.11 | 0.43 |  |  | 40 | 80 | 825 | 18000 | 161.14 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 19:45 | 20:00 | 0.25 | 10179 | 10241 | 62 | Rotate |  | 10209 | 2.13 | 306.82 | 10117.1 | -882.15 | 623.86 | -882.15 | 0.19 |  |  | 40 | 80 | 825 | 18000 | 248 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 20:00 | 22:00 | 2 | 10241 | 10273 | 32 | Slide | TTF: 325; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 16 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/30/2021 | 22:05 | 24:00 | 1.9167 | 10273 | 10308 | 35 | Slide | 325 | 10302 | 5.75 | 315.91 | 10209.86 | -877.77 | 619.24 | -877.77 | 3.94 |  |  | 40 | 80 | 825 | 18000 | 18.26 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/31/2021 | 00:00 | 01:35 | 1.5833 | 10308 | 10366 | 58 | Slide | TTF: 325; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 36.63 | 5000 | 4200 | 800 | 221 | 250 | 220 | 200
07/31/2021 | 01:40 | 02:55 | 1.25 | 10366 | 10386 | 20 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 16 | 5000 | 4200 | 800 | 240 | 250 | 220 | 200
07/31/2021 | 02:55 | 04:15 | 1.3333 | 10386 | 10457 | 71 | Slide | 0 | 10397 | 11.68 | 327.33 | 10303.73 | -866.25 | 610.73 | -866.25 | 6.47 |  |  | 40 | 80 | 825 | 18000 | 53.25 | 5000 | 4200 | 800 | 240 | 250 | 220 | 200
07/31/2021 | 04:20 | 05:00 | 0.66667 | 10457 | 10555 | 98 | Rotate |  | 10491 | 12.96 | 332.93 | 10395.56 | -848.85 | 600.79 | -848.85 | 1.86 |  |  | 40 | 80 | 825 | 18000 | 147 | 5000 | 4200 | 800 | 240 | 250 | 220 | 200
07/31/2021 | 05:05 | 08:58 | 3.8833 | 10555 | 10743 | 188 | Slide | 0 | 10585 | 14.53 | 332.42 | 10486.87 | -829.01 | 590.54 | -829.01 | 1.68 |  |  | 20 |  | 825 |  | 48.41 | 5000 | 4200 | 800 | 240 | 250 | 220 | 200
07/31/2021 | 09:02 | 09:17 | 0.25 | 10743 | 10781 | 38 | Rotate |  | 10773 | 25.26 | 337.89 | 10662.8 | -769.56 | 563.11 | -769.56 | 4.78 |  |  | 20 | 20 | 825 | 12000 | 152 | 5000 | 4200 | 800 | 240 | 250 | 220 | 200
07/31/2021 | 09:17 | 10:40 | 1.3833 | 10781 | 10837 | 56 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 825; Drilling Parameters ROP: 40.48 | 4600 | 4200 | 400 | 240 | 250 | 220 | 200
07/31/2021 | 10:44 | 10:53 | 0.15 | 10837 | 10857 | 20 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 20; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 133.33 | 5100 | 4600 | 500 | 252 | 300 | 280 | 265
07/31/2021 | 10:53 | 12:12 | 1.3167 | 10857 | 10930 | 73 | Slide | -30 | 10866 | 30.1 | 339.29 | 10745.13 | -729.34 | 547.38 | -729.34 | 5.25 |  |  | 15 |  | 825 |  | 55.44 | 4900 | 4600 | 300 | 252 | 300 | 280 | 265
07/31/2021 | 12:15 | 12:22 | 0.11667 | 10930 | 10942 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 20; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 102.86 | 5100 | 4600 | 500 | 252 | 300 | 280 | 265
07/31/2021 | 12:22 | 14:14 | 1.8667 | 10942 | 11024 | 82 | Slide | -50 | 10960 | 36.06 | 333.87 | 10823.88 | -682.4 | 526.84 | -682.4 | 7.07 |  |  | 15 |  | 825 |  | 43.93 | 4900 | 4600 | 300 | 252 | 300 | 280 | 265
07/31/2021 | 14:17 | 14:32 | 0.25 | 11024 | 11044 | 20 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 20; Drilling Parameters FLOW: 825; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 80 | 5100 | 4600 | 500 | 252 | 300 | 280 | 265
07/31/2021 | 14:32 | 15:14 | 0.7 | 11044 | 11063 | 19 | Slide | TTF: -30; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 825; Drilling Parameters ROP: 27.14 | 4800 | 4600 | 200 | 252 | 300 | 280 | 265

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7049
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 1155
Well Name: |  |  |  |  | Redwood A1H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 55.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 321.52 |  | Rotate: |  | 5894
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
09/10/2021 | 15:30 | 15:40 | 0.16667 | 11063 | 11073 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 6; Drilling Parameters ROP: 60 | 4400 | 3800 | 600 | 228 | 220 | 200 | 180
09/10/2021 | 17:00 | 18:05 | 1.0833 | 11073 | 11118 | 45 | Slide | -30 | 11096 | 43.19 | 327.65 | 10928.07 | -606.63 | 483.6 | -606.63 | 5.2 |  |  | 10 |  | 350 |  | 41.54 | 4400 | 3800 | 600 | 228 | 220 | 200 | 180
09/10/2021 | 18:05 | 18:15 | 0.16667 | 11118 | 11132 | 14 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 84 | 4400 | 3800 | 600 | 228 | 220 | 200 | 180
09/10/2021 | 18:35 | 19:10 | 0.58333 | 11132 | 11164 | 32 | Slide | -30 | 11159 | 46.84 | 327.36 | 10972.59 | -569.05 | 459.66 | -569.05 | 5.8 |  |  | 25 |  | 400 |  | 54.86 | 5100 | 4600 | 500 | 228 | 220 | 200 | 180
09/10/2021 | 19:15 | 20:00 | 0.75 | 11164 | 11227 | 63 | Slide | TTF: -30; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 84 | 5100 | 4600 | 500 | 228 | 220 | 200 | 180
09/10/2021 | 20:15 | 21:15 | 1 | 11227 | 11322 | 95 | Slide | 0 | 11254 | 57.45 | 329.48 | 11030.81 | -505.2 | 420.52 | -505.2 | 11.31 |  |  | 25 |  | 400 |  | 95 | 5100 | 4600 | 500 | 228 | 220 | 200 | 180
09/10/2021 | 21:25 | 21:50 | 0.41667 | 11322 | 11352 | 30 | Slide | 0 | 11348 | 67.25 | 329.88 | 11074.38 | -433.4 | 378.55 | -433.4 | 10.43 |  |  | 25 |  | 400 |  | 72 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/10/2021 | 21:50 | 22:10 | 0.33333 | 11352 | 11382 | 30 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 90 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/10/2021 | 22:10 | 22:30 | 0.33333 | 11382 | 11416 | 34 | Slide | TTF: -30; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 102 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/10/2021 | 22:40 | 23:40 | 1 | 11416 | 11511 | 95 | Slide | -45 | 11443 | 72.5 | 323.69 | 11107.09 | -358.89 | 329.67 | -358.89 | 8.24 |  |  | 35 |  | 400 |  | 95 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 00:00 | 00:20 | 0.33333 | 11511 | 11532 | 21 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 63 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 00:20 | 00:55 | 0.58333 | 11532 | 11605 | 73 | Slide | 0 | 11537 | 78.42 | 315.73 | 11130.71 | -289.64 | 270.84 | -289.64 | 10.33 |  |  | 35 |  | 400 |  | 125.14 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 01:10 | 01:50 | 0.66667 | 11605 | 11665 | 60 | Rotate |  | 11632 | 86.7 | 316.44 | 11143 | -221.83 | 205.57 | -221.83 | 8.75 |  |  | 25 | 30 | 400 | 6 | 90 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 01:50 | 02:10 | 0.33333 | 11665 | 11700 | 35 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 105 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 02:20 | 02:45 | 0.41667 | 11700 | 11720 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 48 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 02:45 | 03:25 | 0.66667 | 11720 | 11795 | 75 | Rotate |  | 11727 | 92.45 | 318.39 | 11143.71 | -151.92 | 141.32 | -151.92 | 6.39 |  |  | 25 | 30 | 400 | 6 | 112.5 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 03:30 | 04:10 | 0.66667 | 11795 | 11889 | 94 | Rotate |  | 11821 | 93.56 | 318.15 | 11138.78 | -81.87 | 78.83 | -81.87 | 1.21 |  |  | 25 |  | 400 |  | 141 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 04:15 | 04:30 | 0.25 | 11889 | 11909 | 20 | Slide | TTF: -150; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 80 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 04:30 | 04:57 | 0.45 | 11909 | 11984 | 75 | Rotate |  | 11916 | 95.02 | 317.94 | 11131.67 | -11.42 | 15.5 | -11.42 | 1.55 |  |  | 20 | 70 | 400 | 7 | 166.67 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 05:02 | 05:10 | 0.13333 | 11984 | 11994 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 7; Drilling Parameters ROP: 75 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 05:10 | 05:30 | 0.33333 | 11994 | 12014 | 20 | Slide | 180 | 12011 | 92.97 | 316.24 | 11125.05 | 57.98 | -49.02 | 57.98 | 2.8 |  |  | 25 | 70 | 400 | 7 | 60 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 05:30 | 05:55 | 0.41667 | 12014 | 12079 | 65 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 7; Drilling Parameters ROP: 156 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 06:01 | 06:08 | 0.11667 | 12079 | 12089 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 7; Drilling Parameters ROP: 85.71 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 06:08 | 06:20 | 0.2 | 12089 | 12101 | 12 | Slide | TTF: 120; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 5000 | 4600 | 400 | 239 | 220 | 200 | 180
09/11/2021 | 06:20 | 06:49 | 0.48333 | 12101 | 12174 | 73 | Rotate |  | 12106 | 93 | 316.63 | 11120.11 | 126.73 | -114.4 | 126.73 | 0.41 |  |  | 20 | 70 | 400 | 7 | 151.03 | 5100 | 4600 | 500 | 239 | 220 | 200 | 180
09/11/2021 | 06:54 | 07:05 | 0.18333 | 12174 | 12181 | 7 | Rotate | Drilling Parameters WOB: 22.67; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 401.94; Drilling Parameters Tq: 6.21; Drilling Parameters ROP: 38.18 | 4918.71 | 4864.69 | 54.02 | 251.6 | 220 | 208.12 | 180
09/11/2021 | 07:05 | 07:20 | 0.25 | 12181 | 12201 | 20 | Slide | 120.35 | 12200 | 92.08 | 317.5 | 11115.94 | 195.48 | -178.36 | 195.48 | 1.35 |  |  | 16.14 |  | 401.83 |  | 80 | 5110.22 | 4868.64 | 241.58 | 249.8 | 220 | 207.87 | 180
09/11/2021 | 07:20 | 07:39 | 0.31667 | 12201 | 12268 | 67 | Rotate | Drilling Parameters WOB: 31.22; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.01; Drilling Parameters Tq: 10.14; Drilling Parameters ROP: 211.58 | 5700 | 4800 | 900 | 249.8 | 230 | 209.04 | 180
09/11/2021 | 07:43 | 07:50 | 0.11667 | 12268 | 12279 | 11 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.09; Drilling Parameters Tq: 8.13; Drilling Parameters ROP: 94.29 | 5700 | 4851.58 | 848.42 | 251.6 | 230 | 211.08 | 180
09/11/2021 | 07:50 | 08:10 | 0.33333 | 12279 | 12306 | 27 | Slide | 103.16 | 12295 | 91.82 | 318.59 | 11112.71 | 266.09 | -241.84 | 266.09 | 1.18 |  |  | 14.57 |  | 402.06 |  | 81 | 5097.56 | 4894.9 | 202.66 | 249.8 | 230 | 205.8 | 180
09/11/2021 | 08:10 | 08:28 | 0.3 | 12306 | 12361 | 55 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 401.45; Drilling Parameters Tq: 7.47; Drilling Parameters ROP: 183.33 | 5700 | 4919.46 | 780.54 | 251.6 | 230 | 209.19 | 180
09/11/2021 | 08:32 | 08:43 | 0.18333 | 12361 | 12373 | 12 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.13; Drilling Parameters Tq: 5.93; Drilling Parameters ROP: 65.45 | 5700 | 4877.62 | 822.38 | 253.4 | 230 | 209.19 | 180
09/11/2021 | 08:43 | 09:02 | 0.31667 | 12373 | 12398 | 25 | Slide | 85.06 | 12390 | 90.56 | 320.87 | 11110.73 | 338.55 | -303.23 | 338.55 | 2.74 |  |  | 20.96 |  | 401.94 |  | 78.95 | 5115.16 | 4883.24 | 231.92 | 251.6 | 230 | 209.19 | 180
09/11/2021 | 09:02 | 09:16 | 0.23333 | 12398 | 12456 | 58 | Rotate | Drilling Parameters WOB: 36.14; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 401.99; Drilling Parameters Tq: 9.07; Drilling Parameters ROP: 248.57 | 5564.77 | 4900 | 664.77 | 251.6 | 230 | 206.44 | 180
09/11/2021 | 09:21 | 09:46 | 0.41667 | 12456 | 12552 | 96 | Rotate |  | 12482 | 89.79 | 321.52 | 11110.45 | 410.24 | -360.88 | 410.24 | 1.1 |  |  | 32 | 70 | 402.02 | 10 | 230.4 | 5700 | 4900 | 800 | 257 | 230 | 204.94 | 175
09/11/2021 | 09:54 | 10:05 | 0.18333 | 12552 | 12561 | 9 | Rotate | Drilling Parameters WOB: 12.9; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.09; Drilling Parameters Tq: 6.21; Drilling Parameters ROP: 49.09 | 5700 | 4887.47 | 812.53 | 257 | 230 | 205.34 | 175
09/11/2021 | 10:05 | 10:18 | 0.21667 | 12561 | 12573 | 12 | Slide | TTF: 17.81; Drilling Parameters WOB: 16.26; Drilling Parameters FLOW: 402.03; Drilling Parameters ROP: 55.38 | 4971.99 | 4826.34 | 145.65 | 257 | 230 | 205.34 | 175
09/11/2021 | 10:18 | 10:32 | 0.23333 | 12573 | 12644 | 71 | Rotate |  | 12576 | 89.93 | 321.75 | 11110.68 | 483.94 | -419.22 | 483.94 | 0.29 |  |  | 32.42 | 67.46 | 401.94 | 8.89 | 304.29 | 5700 | 4900 | 800 | 258.8 | 230 | 208.66 | 175
09/11/2021 | 10:37 | 10:48 | 0.18333 | 12644 | 12655 | 11 | Rotate | Drilling Parameters WOB: 21.13; Drilling Parameters RPM: 70.1; Drilling Parameters FLOW: 402.01; Drilling Parameters Tq: 6.01; Drilling Parameters ROP: 60 | 5700 | 4857.74 | 842.26 | 260.6 | 240 | 208.66 | 175
09/11/2021 | 10:48 | 11:01 | 0.21667 | 12655 | 12667 | 12 | Slide | TTF: 24.12; Drilling Parameters WOB: 15.73; Drilling Parameters FLOW: 402.06; Drilling Parameters ROP: 55.38 | 5108.67 | 4940.16 | 168.51 | 260.6 | 240 | 208.27 | 175
09/11/2021 | 11:01 | 11:16 | 0.25 | 12667 | 12739 | 72 | Rotate |  | 12671 | 91.65 | 322.96 | 11109.37 | 559.15 | -477.24 | 559.15 | 2.21 |  |  | 30.97 | 66.74 | 401.94 | 8.68 | 288 | 5700 | 4900 | 800 | 260.6 | 240 | 212.28 | 175
09/11/2021 | 11:20 | 11:42 | 0.36667 | 12739 | 12831 | 92 | Rotate |  | 12763 | 92.09 | 322.96 | 11106.37 | 632.55 | -532.63 | 632.55 | 0.48 |  |  | 36.84 | 70.05 | 401.85 | 7.99 | 250.91 | 5642.51 | 4795.24 | 847.27 | 264.2 | 240 | 212.28 | 175
09/11/2021 | 11:46 | 11:57 | 0.18333 | 12831 | 12843 | 12 | Rotate | Drilling Parameters WOB: 24.84; Drilling Parameters RPM: 70.07; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 6.65; Drilling Parameters ROP: 65.45 | 4946.76 | 4894.89 | 51.87 | 264.2 | 240 | 211.94 | 175
09/11/2021 | 11:57 | 12:11 | 0.23333 | 12843 | 12855 | 12 | Slide | TTF: -23.91; Drilling Parameters WOB: 15.71; Drilling Parameters RPM: 50.08; Drilling Parameters FLOW: 401.71; Drilling Parameters Tq: 6.11; Drilling Parameters ROP: 51.43 | 5127.82 | 4870.54 | 257.28 | 262.4 | 240 | 204.66 | 175
09/11/2021 | 12:11 | 12:26 | 0.25 | 12855 | 12926 | 71 | Rotate |  | 12858 | 94.26 | 322.64 | 11101.11 | 708.1 | -589.97 | 708.1 | 2.31 |  |  | 30.86 | 67.7 | 401.76 | 9 | 284 | 5637.89 | 4870.54 | 767.35 | 262.4 | 240 | 207.7 | 175
09/11/2021 | 12:31 | 12:53 | 0.36667 | 12926 | 13020 | 94 | Rotate |  | 12952 | 94.84 | 321.8 | 11093.65 | 782.16 | -647.38 | 782.16 | 1.08 |  |  | 34.35 | 70.07 | 401.91 | 8.7 | 256.36 | 5664.35 | 4870.54 | 793.81 | 267.8 | 240 | 208.04 | 175
09/11/2021 | 12:58 | 13:21 | 0.38333 | 13020 | 13115 | 95 | Rotate |  | 13047 | 96.03 | 322.05 | 11084.65 | 856.61 | -705.7 | 856.61 | 1.28 |  |  | 25.97 | 70.05 | 402.1 | 7.25 | 247.83 | 5664.35 | 4870.54 | 793.81 | 271.4 | 240 | 205.89 | 175
09/11/2021 | 13:26 | 13:33 | 0.11667 | 13115 | 13125 | 10 | Rotate | Drilling Parameters WOB: 25.97; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 401.76; Drilling Parameters Tq: 7.25; Drilling Parameters ROP: 85.71 | 5664.35 | 4917.19 | 747.16 | 267.8 | 240 | 204.81 | 175
09/11/2021 | 13:33 | 13:52 | 0.31667 | 13125 | 13143 | 18 | Slide | 180 | 13141 | 95.43 | 321.83 | 11075.27 | 930.25 | -763.36 | 930.25 | 0.68 |  |  | 17.26 |  | 401.85 |  | 56.84 | 5180.44 | 4917.19 | 263.25 | 267.8 | 240 | 204.81 | 175
09/11/2021 | 13:52 | 14:09 | 0.28333 | 13143 | 13209 | 66 | Rotate | Drilling Parameters WOB: 29.53; Drilling Parameters RPM: 66.86; Drilling Parameters FLOW: 401.87; Drilling Parameters Tq: 9.08; Drilling Parameters ROP: 232.94 | 5601.99 | 4917.19 | 684.8 | 267.8 | 240 | 206.55 | 175
09/11/2021 | 14:15 | 14:22 | 0.11667 | 13209 | 13219 | 10 | Rotate | Drilling Parameters WOB: 29.53; Drilling Parameters RPM: 66.86; Drilling Parameters FLOW: 402.09; Drilling Parameters Tq: 7.37; Drilling Parameters ROP: 85.71 | 5601.99 | 4856.67 | 745.32 | 267.8 | 240 | 206.27 | 175
09/11/2021 | 14:22 | 14:43 | 0.35 | 13219 | 13234 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 19.87; Drilling Parameters FLOW: 402.09; Drilling Parameters ROP: 42.86 | 5213.03 | 4856.67 | 356.36 | 267.8 | 240 | 206.27 | 175
09/11/2021 | 14:43 | 15:00 | 0.28333 | 13234 | 13304 | 70 | Rotate |  | 13236 | 93.8 | 321.49 | 11067.63 | 1004.52 | -822.09 | 1004.52 | 1.75 |  |  | 30.55 | 67.12 | 401.96 | 9.54 | 247.06 | 5590.79 | 4115.85 | 1474.94 | 269.6 | 240 | 207 | 175
09/11/2021 | 15:04 | 15:25 | 0.35 | 13304 | 13399 | 95 | Rotate |  | 13331 | 94.17 | 320.83 | 11061.02 | 1078.33 | -881.53 | 1078.33 | 0.79 |  |  | 28.59 | 70.13 | 401.95 | 7.8 | 271.43 | 5573.75 | 4898.37 | 675.38 | 273.2 | 240 | 206.8 | 170
09/11/2021 | 15:30 | 15:50 | 0.33333 | 13399 | 13493 | 94 | Rotate |  | 13426 | 93.42 | 323.2 | 11054.74 | 1153.04 | -939.86 | 1153.04 | 2.61 |  |  | 27.58 | 70.13 | 401.95 | 7.6 | 282 | 5584.99 | 4898.37 | 686.62 | 275 | 240 | 203.7 | 170
09/11/2021 | 15:58 | 16:16 | 0.3 | 13493 | 13588 | 95 | Rotate |  | 13520 | 93.84 | 332.18 | 11048.77 | 1232.24 | -989.96 | 1232.24 | 9.54 |  |  | 31.18 | 70.11 | 401.93 | 7.53 | 316.67 | 5619.42 | 4898.37 | 721.05 | 276.8 | 240 | 206.84 | 170
09/11/2021 | 16:23 | 16:34 | 0.18333 | 13588 | 13598 | 10 | Rotate | Drilling Parameters WOB: 19.43; Drilling Parameters RPM: 70.1; Drilling Parameters FLOW: 401.85; Drilling Parameters Tq: 5.69; Drilling Parameters ROP: 54.55 | 5300 | 4898.37 | 401.63 | 276.8 | 240 | 211.45 | 170
09/11/2021 | 16:34 | 16:54 | 0.33333 | 13598 | 13622 | 24 | Slide | -83.66 | 13615 | 93.48 | 338.2 | 11042.7 | 1318.26 | -1029.72 | 1318.26 | 6.34 |  |  | 10.25 | 50.13 | 401.96 | 4.71 | 72 | 5300 | 4853.64 | 446.36 | 275 | 240 | 200.77 | 170
09/11/2021 | 16:54 | 17:04 | 0.16667 | 13622 | 13632 | 10 | Rotate | Drilling Parameters WOB: 10.29; Drilling Parameters RPM: 50.13; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 5.28; Drilling Parameters ROP: 60 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 17:04 | 17:20 | 0.26667 | 13632 | 13653 | 21 | Slide | TTF: -110; Drilling Parameters WOB: 15; Drilling Parameters RPM: 50.13; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 5.28; Drilling Parameters ROP: 78.75 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 17:20 | 17:28 | 0.13333 | 13653 | 13663 | 10 | Rotate | Drilling Parameters WOB: 10.29; Drilling Parameters RPM: 50.13; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 5.28; Drilling Parameters ROP: 75 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 17:28 | 17:45 | 0.28333 | 13663 | 13683 | 20 | Slide | TTF: -110; Drilling Parameters WOB: 15; Drilling Parameters RPM: 50.13; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 5.28; Drilling Parameters ROP: 70.59 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 17:52 | 18:50 | 0.96667 | 13683 | 13778 | 95 | Rotate |  | 13710 | 93.76 | 329.5 | 11036.69 | 1403.28 | -1071.46 | 1403.28 | 9.14 |  |  | 20 | 50.13 | 402.05 | 5.28 | 98.28 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 19:35 | 19:50 | 0.25 | 13778 | 13793 | 15 | Slide | TTF: -150; Drilling Parameters WOB: 20; Drilling Parameters RPM: 50.13; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 5.28; Drilling Parameters ROP: 60 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 19:50 | 20:35 | 0.75 | 13793 | 13872 | 79 | Rotate |  | 13804 | 93.57 | 323.01 | 11030.68 | 1481.25 | -1123.54 | 1481.25 | 6.89 |  |  | 10.29 | 50.13 | 402.05 | 5.28 | 105.33 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 20:40 | 21:35 | 0.91667 | 13872 | 13916 | 44 | Slide | -140 | 13898 | 91.49 | 322.99 | 11026.53 | 1556.24 | -1180.06 | 1556.24 | 2.21 |  |  | 30 | 50.13 | 402.05 | 5.28 | 48 | 5300 | 4825.07 | 474.93 | 271 | 240 | 200.87 | 170
09/11/2021 | 21:35 | 22:05 | 0.5 | 13916 | 13966 | 50 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 50.13; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 5.28; Drilling Parameters ROP: 100 | 5300 | 4825.07 | 474.93 | 271 | 240 | 200.87 | 170
09/11/2021 | 22:10 | 22:50 | 0.66667 | 13966 | 14060 | 94 | Rotate |  | 13992 | 91.36 | 320.56 | 11024.19 | 1630.06 | -1238.2 | 1630.06 | 2.59 |  |  | 25 | 70 | 402.05 | 5.28 | 141 | 5300 | 4825.07 | 474.93 | 271 | 240 | 200.87 | 170
09/11/2021 | 22:55 | 23:35 | 0.66667 | 14060 | 14153 | 93 | Rotate |  | 14085 | 90.57 | 319.96 | 11022.62 | 1701.56 | -1297.64 | 1701.56 | 1.07 |  |  | 25 | 70 | 402.05 | 8 | 139.5 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/11/2021 | 23:40 | 24:00 | 0.33333 | 14153 | 14178 | 25 | Slide | TTF: -30; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 8; Drilling Parameters ROP: 75 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/12/2021 | 00:00 | 00:35 | 0.58333 | 14178 | 14248 | 70 | Rotate |  | 14180 | 91.84 | 319.1 | 11020.63 | 1773.81 | -1359.29 | 1773.81 | 1.61 |  |  | 35 | 70 | 402.05 | 8 | 120 | 5300 | 4825.07 | 474.93 | 275 | 240 | 200.87 | 170
09/12/2021 | 00:40 | 01:15 | 0.58333 | 14248 | 14342 | 94 | Rotate |  | 14274 | 91.01 | 318.01 | 11018.29 | 1844.25 | -1421.49 | 1844.25 | 1.46 |  |  | 35 | 70 | 402.05 | 8 | 161.14 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 01:20 | 01:45 | 0.41667 | 14342 | 14362 | 20 | Slide | TTF: 30; Drilling Parameters WOB: 35; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 8; Drilling Parameters ROP: 48 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 01:45 | 02:10 | 0.41667 | 14362 | 14437 | 75 | Rotate |  | 14369 | 94 | 320.3 | 11014.14 | 1916.03 | -1483.55 | 1916.03 | 3.96 |  |  | 35 | 70 | 402.05 | 8 | 180 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 02:15 | 02:45 | 0.5 | 14437 | 14532 | 95 | Rotate |  | 14464 | 93.81 | 320.09 | 11007.67 | 1988.84 | -1544.22 | 1988.84 | 0.3 |  |  | 35 | 70 | 402.05 | 8 | 190 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 02:50 | 03:00 | 0.16667 | 14532 | 14540 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 402.05; Drilling Parameters Tq: 8; Drilling Parameters ROP: 48 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 03:00 | 03:35 | 0.58333 | 14540 | 14627 | 87 | Rotate |  | 14559 | 94.55 | 321.74 | 11000.74 | 2062.38 | -1603.96 | 2062.38 | 1.9 |  |  | 35 | 80 | 402.05 | 8 | 149.14 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 03:40 | 04:10 | 0.5 | 14627 | 14721 | 94 | Rotate |  | 14653 | 94.99 | 321.49 | 10992.92 | 2135.81 | -1662.12 | 2135.81 | 0.54 |  |  | 35 | 80 | 402.05 | 8 | 188 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 04:15 | 04:50 | 0.58333 | 14721 | 14816 | 95 | Rotate |  | 14748 | 95.69 | 321.07 | 10984.08 | 2209.61 | -1721.29 | 2209.61 | 0.86 |  |  | 35 | 80 | 402.05 | 8 | 162.86 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 04:55 | 05:20 | 0.41667 | 14816 | 14833 | 17 | Slide | TTF: -150; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 402.05; Drilling Parameters ROP: 40.8 | 5300 | 4825.07 | 474.93 | 279 | 240 | 200.87 | 170
09/12/2021 | 05:20 | 05:47 | 0.45 | 14833 | 14909 | 76 | Rotate |  | 14841 | 94.64 | 319.42 | 10975.71 | 2280.81 | -1780.52 | 2280.81 | 2.1 |  |  | 20.83 | 76.74 | 393.13 | 8.44 | 168.89 | 5587 | 4878.46 | 708.54 | 278.6 | 240 | 201.7 | 170
09/12/2021 | 07:03 | 07:34 | 0.51667 | 14909 | 15002 | 93 | Rotate |  | 14934 | 95.77 | 319.93 | 10967.27 | 2351.42 | -1840.45 | 2351.42 | 1.33 |  |  | 34.69 | 80.09 | 393.27 | 9.33 | 180 | 5526.36 | 4878.46 | 647.9 | 285.8 | 250 | 201.55 | 165
09/12/2021 | 07:39 | 07:53 | 0.23333 | 15002 | 15013 | 11 | Rotate | Drilling Parameters WOB: 35.78; Drilling Parameters RPM: 80.09; Drilling Parameters FLOW: 393.18; Drilling Parameters Tq: 8.07; Drilling Parameters ROP: 47.14 | 5526.36 | 4878.46 | 647.9 | 285.8 | 250 | 201.55 | 165
09/12/2021 | 07:53 | 08:25 | 0.53333 | 15013 | 15033 | 20 | Slide | 177.09 | 15029 | 95.25 | 319.59 | 10958.15 | 2423.6 | -1901.54 | 2423.6 | 0.65 |  |  | 17.15 |  | 393.13 |  | 37.5 | 4998.07 | 4730.95 | 267.12 | 282.2 | 250 | 196.22 | 165
09/12/2021 | 08:25 | 08:41 | 0.26667 | 15033 | 15097 | 64 | Rotate | Drilling Parameters WOB: 31.05; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 392.86; Drilling Parameters Tq: 11.51; Drilling Parameters ROP: 240 | 5503.57 | 4019.56 | 1484.01 | 284 | 250 | 201.95 | 165
09/12/2021 | 08:46 | 08:54 | 0.13333 | 15097 | 15107 | 10 | Rotate | Drilling Parameters WOB: 27.61; Drilling Parameters RPM: 80.1; Drilling Parameters FLOW: 393.29; Drilling Parameters Tq: 9.51; Drilling Parameters ROP: 75 | 5503.57 | 4720.8 | 782.77 | 285.8 | 250 | 201.95 | 165
09/12/2021 | 08:54 | 09:12 | 0.3 | 15107 | 15117 | 10 | Slide | TTF: 162.59; Drilling Parameters WOB: 18.57; Drilling Parameters FLOW: 393.21; Drilling Parameters ROP: 33.33 | 5084.49 | 4809.91 | 274.58 | 284 | 250 | 197.37 | 165
09/12/2021 | 09:12 | 09:38 | 0.43333 | 15117 | 15192 | 75 | Rotate |  | 15124 | 92.49 | 319.08 | 10951.74 | 2495.49 | -1963.3 | 2495.49 | 2.95 |  |  | 28.33 | 75.81 | 393.21 | 10.8 | 173.08 | 5535.95 | 4809.91 | 726.04 | 285.8 | 250 | 207.58 | 165
09/12/2021 | 09:47 | 10:18 | 0.51667 | 15192 | 15287 | 95 | Rotate |  | 15219 | 91.89 | 318.54 | 10948.11 | 2566.93 | -2025.81 | 2566.93 | 0.85 |  |  | 33.65 | 80.08 | 393.48 | 10.47 | 183.87 | 5560.6 | 4809.91 | 750.69 | 289.4 | 250 | 197.51 | 165
09/12/2021 | 10:28 | 10:35 | 0.11667 | 15287 | 15297 | 10 | Rotate | Drilling Parameters WOB: 17.52; Drilling Parameters RPM: 80.09; Drilling Parameters FLOW: 393.69; Drilling Parameters Tq: 9.88; Drilling Parameters ROP: 85.71 | 5560.6 | 4838.76 | 721.84 | 289.4 | 250 | 197.51 | 165
09/12/2021 | 10:35 | 11:05 | 0.5 | 15297 | 15312 | 15 | Slide | TTF: 60.36; Drilling Parameters WOB: 14.16; Drilling Parameters FLOW: 393.58; Drilling Parameters ROP: 30 | 4940.62 | 4764.28 | 176.34 | 285.8 | 250 | 200.91 | 165
09/12/2021 | 11:05 | 11:33 | 0.46667 | 15312 | 15382 | 70 | Rotate |  | 15314 | 93.21 | 320.46 | 10943.88 | 2639.09 | -2087.45 | 2639.09 | 2.45 |  |  | 30.65 | 75.53 | 393.46 | 11.47 | 150 | 5511.11 | 4764.28 | 746.83 | 287.6 | 250 | 201.48 | 165
09/12/2021 | 11:43 | 12:15 | 0.53333 | 15382 | 15477 | 95 | Rotate |  | 15409 | 93.95 | 320.79 | 10937.95 | 2712.38 | -2147.6 | 2712.38 | 0.85 |  |  | 29.77 | 80.11 | 393.86 | 11.27 | 178.13 | 5587.37 | 4764.28 | 823.09 | 291.2 | 250 | 200.34 | 165
09/12/2021 | 12:23 | 12:55 | 0.53333 | 15477 | 15572 | 95 | Rotate |  | 15504 | 95.5 | 321.08 | 10930.13 | 2785.89 | -2207.26 | 2785.89 | 1.66 |  |  | 29.34 | 80.09 | 394.66 | 10.83 | 178.13 | 5584.14 | 4764.28 | 819.86 | 293 | 250 | 200.19 | 150
09/12/2021 | 13:02 | 13:10 | 0.13333 | 15572 | 15582 | 10 | Rotate | Drilling Parameters WOB: 15.64; Drilling Parameters RPM: 80.12; Drilling Parameters FLOW: 394.93; Drilling Parameters Tq: 8.5; Drilling Parameters ROP: 75 | 5584.14 | 4827 | 757.14 | 293 | 250 | 200.19 | 150
09/12/2021 | 13:16 | 14:14 | 0.96667 | 15582 | 15602 | 20 | Slide | -143.38 | 15598 | 95.34 | 320.06 | 10921.25 | 2858.17 | -2266.69 | 2858.17 | 1.09 |  |  | 18.39 |  | 394.32 |  | 20.69 | 5002.01 | 4753.38 | 248.63 | 285.8 | 250 | 199.77 | 150
09/12/2021 | 14:14 | 14:31 | 0.28333 | 15602 | 15666 | 64 | Rotate | Drilling Parameters WOB: 32.38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.62; Drilling Parameters Tq: 13.09; Drilling Parameters ROP: 225.88 | 5602.3 | 4753.38 | 848.92 | 287.6 | 250 | 198.97 | 150
09/12/2021 | 14:42 | 15:12 | 0.5 | 15666 | 15760 | 94 | Rotate |  | 15692 | 96.01 | 320.21 | 10911.95 | 2929.97 | -2326.65 | 2929.97 | 0.73 |  |  | 31.05 | 80 | 394.72 | 11.94 | 188 | 5598.77 | 4753.38 | 845.39 | 293 | 250 | 201.22 | 150
09/12/2021 | 15:19 | 15:27 | 0.13333 | 15760 | 15770 | 10 | Rotate | Drilling Parameters WOB: 26.05; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.94; Drilling Parameters Tq: 10.55; Drilling Parameters ROP: 75 | 5598.77 | 4807.73 | 791.04 | 293 | 250 | 201.22 | 150
09/12/2021 | 15:27 | 16:12 | 0.75 | 15770 | 15788 | 18 | Slide | 168.57 | 15787 | 93.7 | 320.09 | 10903.91 | 3002.63 | -2387.3 | 3002.63 | 2.43 |  |  | 7.83 |  | 394.73 |  | 24 | 4939.6 | 4701.34 | 238.26 | 287.6 | 250 | 198.54 | 150
09/12/2021 | 16:15 | 16:33 | 0.3 | 15788 | 15855 | 67 | Rotate | Drilling Parameters WOB: 26.21; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.64; Drilling Parameters Tq: 12.07; Drilling Parameters ROP: 223.33 | 5521.87 | 4701.34 | 820.53 | 289.4 | 250 | 201.99 | 150
09/12/2021 | 16:41 | 17:09 | 0.46667 | 15855 | 15948 | 93 | Rotate |  | 15880 | 93.84 | 320.49 | 10897.8 | 3074.02 | -2446.59 | 3074.02 | 0.45 |  |  | 27.47 | 77.39 | 394.97 | 11.98 | 199.29 | 5610.27 | 4701.34 | 908.93 | 294.8 | 250 | 200.56 | 150
09/12/2021 | 17:15 | 17:29 | 0.23333 | 15948 | 15960 | 12 | Rotate | Drilling Parameters WOB: 21.1; Drilling Parameters RPM: 58.04; Drilling Parameters FLOW: 395.15; Drilling Parameters Tq: 10.07; Drilling Parameters ROP: 51.43 | 4830.8 | 4842.66 | -11.86 | 294.8 | 250 | 199.34 | 150
09/12/2021 | 17:29 | 17:42 | 0.21667 | 15960 | 15966 | 6 | Slide | TTF: 171.45; Drilling Parameters WOB: 16.29; Drilling Parameters FLOW: 394.91; Drilling Parameters ROP: 27.69 | 5049.83 | 4805.55 | 244.28 | 293 | 250 | 197.65 | 150
09/12/2021 | 17:42 | 18:10 | 0.46667 | 15966 | 16043 | 77 | Rotate |  | 15975 | 92.87 | 321.23 | 10892.24 | 3147.58 | -2506.45 | 3147.58 | 1.28 |  |  | 25 | 80 | 394.97 | 12 | 165 | 5238.11 | 4805.55 | 432.56 | 293 | 250 | 197.65 | 150
09/12/2021 | 18:15 | 18:50 | 0.58333 | 16043 | 16137 | 94 | Rotate |  | 16069 | 92.98 | 321.23 | 10887.44 | 3220.77 | -2565.24 | 3220.77 | 0.12 |  |  | 25 | 80 | 394.97 | 12 | 161.14 | 5700 | 4805.55 | 894.45 | 293 | 250 | 197.65 | 150
09/12/2021 | 18:55 | 19:25 | 0.5 | 16137 | 16232 | 95 | Rotate |  | 16164 | 93.59 | 323.2 | 10882 | 3295.72 | -2623.35 | 3295.72 | 2.17 |  |  | 25 | 80 | 394.97 | 12 | 190 | 5700 | 4805.55 | 894.45 | 293 | 250 | 197.65 | 150
09/12/2021 | 19:30 | 19:55 | 0.41667 | 16232 | 16252 | 20 | Slide | TTF: -140; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 48 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/12/2021 | 19:55 | 20:40 | 0.75 | 16252 | 16326 | 74 | Rotate |  | 16258 | 91.81 | 321.15 | 10877.57 | 3369.88 | -2680.92 | 3369.88 | 2.89 |  |  | 25 | 80 | 394.97 | 12 | 98.67 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/12/2021 | 20:45 | 21:30 | 0.75 | 16326 | 16422 | 96 | Rotate |  | 16354 | 92.16 | 320.65 | 10874.24 | 3444.34 | -2741.43 | 3444.34 | 0.64 |  |  | 25 | 80 | 394.97 | 12 | 128 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/12/2021 | 21:35 | 22:20 | 0.75 | 16422 | 16514 | 92 | Rotate |  | 16446 | 93.25 | 321.13 | 10869.9 | 3515.64 | -2799.4 | 3515.64 | 1.29 |  |  | 25 | 80 | 394.97 | 12 | 122.67 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/12/2021 | 22:25 | 22:55 | 0.5 | 16514 | 16529 | 15 | Slide | TTF: -150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 30 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/12/2021 | 22:55 | 23:30 | 0.58333 | 16529 | 16608 | 79 | Rotate |  | 16540 | 93.67 | 320.69 | 10864.23 | 3588.47 | -2858.56 | 3588.47 | 0.65 |  |  | 25 | 80 | 394.97 | 12 | 135.43 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/12/2021 | 23:40 | 24:00 | 0.33333 | 16608 | 16615 | 7 | Slide | TTF: -150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 21 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/13/2021 | 00:00 | 00:20 | 0.33333 | 16615 | 16623 | 8 | Slide | TTF: -150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 24 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/13/2021 | 00:20 | 00:55 | 0.58333 | 16623 | 16701 | 78 | Rotate |  | 16633 | 93.01 | 319.58 | 10858.81 | 3659.73 | -2918.07 | 3659.73 | 1.39 |  |  | 30 | 80 | 394.97 | 12 | 133.71 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/13/2021 | 01:00 | 01:45 | 0.75 | 16701 | 16796 | 95 | Rotate |  | 16728 | 93.25 | 318.89 | 10853.62 | 3731.57 | -2980.01 | 3731.57 | 0.77 |  |  | 30 | 80 | 394.97 | 12 | 126.67 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/13/2021 | 01:50 | 02:25 | 0.58333 | 16796 | 16811 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 25.71 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/13/2021 | 02:25 | 03:05 | 0.66667 | 16811 | 16891 | 80 | Rotate |  | 16823 | 91.43 | 318.29 | 10849.74 | 3802.76 | -3042.79 | 3802.76 | 2.02 |  |  | 30 | 80 | 394.97 | 12 | 120 | 5700 | 4805.55 | 894.45 | 297 | 250 | 197.65 | 150
09/13/2021 | 03:10 | 03:50 | 0.66667 | 16891 | 16985 | 94 | Rotate |  | 16917 | 92.16 | 318.25 | 10846.8 | 3872.87 | -3105.33 | 3872.87 | 0.78 |  |  | 30 | 80 | 394.97 | 12 | 141 | 5700 | 4805.55 | 894.45 | 300 | 250 | 197.65 | 150
09/13/2021 | 03:55 | 04:45 | 0.83333 | 16985 | 17080 | 95 | Rotate |  | 17012 | 94.63 | 318.46 | 10841.17 | 3943.74 | -3168.34 | 3943.74 | 2.61 |  |  | 30 | 80 | 394.97 | 12 | 114 | 5700 | 4805.55 | 894.45 | 300 | 250 | 197.65 | 150
09/13/2021 | 04:45 | 05:10 | 0.41667 | 17080 | 17092 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 28.8 | 5700 | 4805.55 | 894.45 | 300 | 250 | 197.65 | 150
09/13/2021 | 05:10 | 05:53 | 0.71667 | 17092 | 17174 | 82 | Rotate |  | 17106 | 93.06 | 317.91 | 10834.87 | 4013.63 | -3230.87 | 4013.63 | 1.77 |  |  | 40 | 80 | 394.97 | 12 | 114.42 | 5700 | 4805.55 | 894.45 | 300 | 250 | 197.65 | 150
09/13/2021 | 06:00 | 06:07 | 0.11667 | 17174 | 17184 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 394.97; Drilling Parameters Tq: 12; Drilling Parameters ROP: 85.71 | 5700 | 4805.55 | 894.45 | 300 | 250 | 197.65 | 150
09/13/2021 | 06:07 | 06:30 | 0.38333 | 17184 | 17199 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 394.97; Drilling Parameters ROP: 39.13 | 5100 | 4805.55 | 294.45 | 298 | 290 | 197.65 | 150
09/13/2021 | 06:30 | 07:01 | 0.51667 | 17199 | 17269 | 70 | Rotate |  | 17201 | 91.97 | 322.29 | 10830.7 | 4086.43 | -3291.73 | 4086.43 | 4.75 |  |  | 28.97 | 80 | 395.54 | 12.72 | 135.48 | 5790.87 | 4805.55 | 985.32 | 298.4 | 290 | 189.86 | 150
09/13/2021 | 07:08 | 07:27 | 0.31667 | 17269 | 17304 | 35 | Rotate |  | 17296 | 92 | 329.38 | 10827.41 | 4164.93 | -3345.02 | 4164.93 | 7.46 |  |  | 20.22 | 80 | 396.23 | 10.09 | 110.53 | 5790.87 | 5069.77 | 721.1 | 300.2 | 290 | 191.09 | 140
09/13/2021 | 07:27 | 08:24 | 0.95 | 17304 | 17334 | 30 | Slide | TTF: -90; Drilling Parameters WOB: 18.3; Drilling Parameters FLOW: 395.73; Drilling Parameters ROP: 31.58 | 5480.03 | 5075.34 | 404.69 | 294.8 | 290 | 192.31 | 140
09/13/2021 | 08:24 | 08:40 | 0.26667 | 17334 | 17364 | 30 | Rotate | Drilling Parameters WOB: 20.69; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395.84; Drilling Parameters Tq: 10.51; Drilling Parameters ROP: 112.5 | 5651.22 | 5075.34 | 575.88 | 294.8 | 290 | 192.31 | 140
09/13/2021 | 08:47 | 09:12 | 0.41667 | 17364 | 17403 | 39 | Rotate |  | 17391 | 90.69 | 326.01 | 10825.17 | 4245.19 | -3395.77 | 4245.19 | 3.8 |  |  | 25 | 80 | 396.04 | 9.77 | 93.6 | 5651.22 | 5121 | 530.22 | 296.6 | 290 | 192 | 140
09/13/2021 | 09:12 | 09:53 | 0.68333 | 17403 | 17418 | 15 | Slide | TTF: -45; Drilling Parameters WOB: 19.76; Drilling Parameters FLOW: 395.96; Drilling Parameters ROP: 21.95 | 5530.09 | 5144.27 | 385.82 | 293 | 290 | 192 | 140
09/13/2021 | 09:53 | 10:21 | 0.46667 | 17418 | 17459 | 41 | Rotate | Drilling Parameters WOB: 19.4; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 395.78; Drilling Parameters Tq: 10.99; Drilling Parameters ROP: 87.86 | 5685.11 | 5144.27 | 540.84 | 296.6 | 290 | 201.62 | 140
09/13/2021 | 10:26 | 11:21 | 0.91667 | 17459 | 17554 | 95 | Rotate |  | 17486 | 92 | 323.72 | 10822.94 | 4322.86 | -3450.42 | 4322.86 | 2.78 |  |  | 36.77 | 80 | 396.12 | 11.36 | 103.64 | 5702.91 | 5144.27 | 558.64 | 294.8 | 290 | 196.77 | 140
09/13/2021 | 11:58 | 12:10 | 0.2 | 17554 | 17570 | 16 | Rotate | Drilling Parameters WOB: 26.23; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 396.24; Drilling Parameters Tq: 13.1; Drilling Parameters ROP: 80 | 5789.11 | 5144.27 | 644.84 | 298.4 | 290 | 191.44 | 140
09/13/2021 | 12:10 | 12:48 | 0.63333 | 17570 | 17582 | 12 | Slide | -90 | 17580 | 93.61 | 323.11 | 10818.34 | 4398.24 | -3506.38 | 4398.24 | 1.83 |  |  | 26.23 |  | 396.24 |  | 18.95 | 5400 | 5144.27 | 255.73 | 298.4 | 290 | 191.44 | 140
09/13/2021 | 12:48 | 13:30 | 0.7 | 17582 | 17648 | 66 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 396.24; Drilling Parameters Tq: 13.1; Drilling Parameters ROP: 94.29 | 5789.11 | 5144.27 | 644.84 | 298.4 | 290 | 191.44 | 140
09/13/2021 | 13:35 | 13:45 | 0.16667 | 17648 | 17659 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 396.7; Drilling Parameters Tq: 13.51; Drilling Parameters ROP: 66 | 5731.85 | 5141.24 | 590.61 | 294.8 | 290 | 192.76 | 140
09/13/2021 | 13:45 | 14:15 | 0.5 | 17659 | 17667 | 8 | Slide | TTF: -150; Drilling Parameters WOB: 24.04; Drilling Parameters FLOW: 396.7; Drilling Parameters ROP: 16 | 5300 | 5141.24 | 158.76 | 294.8 | 290 | 192.76 | 140
09/13/2021 | 14:15 | 14:57 | 0.7 | 17667 | 17742 | 75 | Rotate |  | 17674 | 93.73 | 322.86 | 10812.33 | 4473.15 | -3562.85 | 4473.15 | 0.29 |  |  | 25.53 | 80 | 396.68 | 12.54 | 107.14 | 5779.41 | 5141.24 | 638.17 | 298.4 | 290 | 187.56 | 140
09/13/2021 | 15:02 | 15:52 | 0.83333 | 17742 | 17838 | 96 | Rotate |  | 17770 | 93.19 | 324.78 | 10806.53 | 4550.49 | -3619.41 | 4550.49 | 2.07 |  |  | 25.34 | 80 | 396.67 | 10.77 | 115.2 | 5776.03 | 5141.24 | 634.79 | 300.2 | 290 | 191.69 | 140
09/13/2021 | 16:01 | 16:53 | 0.86667 | 17838 | 17932 | 94 | Rotate |  | 17864 | 93.03 | 329.15 | 10801.43 | 4629.16 | -3670.57 | 4629.16 | 4.65 |  |  | 28.94 | 80 | 397 | 10.43 | 108.46 | 5778.09 | 5141.24 | 636.85 | 302 | 290 | 194.72 | 140
09/13/2021 | 16:59 | 17:57 | 0.96667 | 17932 | 18028 | 96 | Rotate |  | 17960 | 94.07 | 340.67 | 10795.47 | 4715.78 | -3711.14 | 4715.78 | 12.03 |  |  | 28.58 | 80 | 396.81 | 8.92 | 96.91 | 5704.18 | 5141.24 | 562.94 | 303.8 | 290 | 195.9 | 140
09/13/2021 | 17:57 | 19:00 | 1.05 | 18028 | 18112 | 84 | Rotate |  | 18112 | 94.07 | 340.67 | 10784.68 | 4858.85 | -3761.32 | 4858.85 | 0 |  |  | 28.58 | 80 | 396.81 | 8.92 | 80 | 5704.18 | 5141.24 | 562.94 | 303.8 | 290 | 195.9 | 140