## Summary
Magnolia Oil & Gas / Redwood B1H / LTX1125621 / Patterson 248
Report Date: | 09/29/2021 | Current Depth: | 19389
Start Date: | 07/17/2021 | Casing Depth: | 3482
Daily Cost: | 9450 | Distance to TD:
Well Cost: | 126080 | Average ROP: | 0
Drilling Hours: | 22.7 | Svy MD: | 19389
24Hr Forcast: |  | Svy Inc: | 90.95
Current BHA: | BHA 4 | Svy Azi: | 140.73
Current BRT Hrs: | 56 | Svy TVD: | 11680.26
Bit Make / Model: | Halliburton / GTD64M | Svy NS: | -7409.22
POOH in last 24Hrs: | Yes | Svy EW: | 3093.58
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Jesse Taylor | MWD Day: | Danny Veronie
Directional Driller Night: | Marshall Adams | MWD Night: | Jason Smetters
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 329
24Hr Summary: | POOH - Rig Down End of Job | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
500048 | UBHO |  |  | Clean
500046 | UBHO |  |  | Dirty |  | 84.73 | 84.73

## Well Summary
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Redwood B1H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Total Drilled (Usft): |  | 19281 |  |  | Total Days: |  | 12
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 3492 | 3384 |  | 511.44 |  | 10.73 | 6.62 | 3.72 | 13.67
2 | 2 | 9.875 | 3492 | 10936 | 7444 |  | 175.08 |  | 13.11 | 42.52 | 9.05 | 76.17
3 | 4 | 6.75 | 10936 | 17133 | 6197 |  | 141.92 |  | 12.26 | 43.67 | 12.32 | 75.33
4 | 4 | 6.75 | 17133 | 19389 | 2256 |  | 99.38 |  | 10.77 | 22.7 | 6.05 | 56
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | 0-0- |  | 0-0-NO-A-X-I-NO-TD |  | 1.353 | 3384 | 6.6167 | 511.44
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 1-1-BT-N-X-I-CT-TD |  | 1.491 | 7444 | 42.5167 | 175.08
4 | Halliburton |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 6197 | 43.6667 | 141.92
4 | Halliburton |  | GTD64M |  | 6.75 | New |  | 0-1-WT-A-N-I-NO-TD |  | 1.491 | 2256 | 22.7 | 99.38
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 5.8 | 3384 |  | 511.44
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 5.82 | 7444 |  | 175.08
3 | PDCI |  | 6/7 11.7 |  | 6/7 | 11.7 | 5.5 | 2.12 | 3.97 | 6197 |  | 141.92
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 3.56 | 2256 |  | 99.38
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | J. Ray X. Cantu |  | Danny Veronie |  | Jason Smetters |  | Brandon Parks |  | James Dyer |  | Peter Langille
|  | Josh Ray |  |  |  | Jason Smitters |  | Kevin Burt |  | Kevin
|  | Marshall Adams | [7 empty] | Kevin Cooper
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.39 |  | 3384 |  | 509.64 |  |  |  | 1 |  | 6.64
INT: INTERMEDIATE |  |  | 2.02 / 1.18 |  | 6788 |  | 310.38 |  |  |  | 1 |  | 21.87
CRV: CURVE |  |  | 1.99 / 0.94 |  | 656 |  | 31.71 |  |  |  | 1 |  | 20.69
CRV2: CURVE 2 |  |  | 0.90 / 0.31 |  | 629 |  | 102.78 |  |  |  | 1 |  | 6.12
LAT: LATERAL |  |  | 5.11 / 4.07 |  | 7824 |  | 129.82 |  |  |  | 2 |  | 60.27
Total |  |  | 12.01 |  | 19281 |  | 166.81 |  |  |  | 4 |  | 115.59
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 3492.00 | 614.02 | 3021.00 | 211.05 | 363.00 | 10.73 | 3384.00 | 509.64 | 6.64 | 1.72
INT: INTERMEDIATE-BHA 2 |  |  | 3492.00 | 10280.00 | 349.19 | 6453.00 | 98.82 | 335.00 | 4.94 | 6788.00 | 310.38 | 21.87 | 3.39
CRV: CURVE-BHA 2 |  |  | 10280.00 | 10936.00 | 100.00 | 15.00 | 31.21 | 641.00 | 97.71 | 656.00 | 31.71 | 20.69 | 20.54
CRV2: CURVE 2-BHA 3 |  |  | 10936.00 | 11565.00 | 133.90 | 237.00 | 90.11 | 392.00 | 62.32 | 629.00 | 102.78 | 6.12 | 4.35
LAT: LATERAL-BHA 4 |  |  | 17133.00 | 19389.00 | 138.73 | 2013.00 | 29.60 | 243.00 | 10.77 | 2256.00 | 99.30 | 22.72 | 8.21
LAT: LATERAL-BHA 3 |  |  | 11565.00 | 17133.00 | 168.50 | 5200.00 | 55.01 | 368.00 | 6.61 | 5568.00 | 148.28 | 37.55 | 6.69
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1125621 | Total Drilled(Usft) | 19281.00
Operator | Magnolia Oil & Gas | Drilling Hours | 115.50
Well Name | Redwood B1H | Avg ROP(Usft/hr) | 166.94
Rig | Patterson 248 | Rotary Drilled(Usft) | 16939.00
State | Texas | Rotary Hours | 70.68
County | Washington | Rotary ROP(Usft/hr) | 239.65
Formation | Austin Chalk | Rotary % | 87.85
Start Date | 07/17/2021 | Slide Drilled(Usft) | 2342.00
End Date | 09/29/2021 | Slide Hours | 44.82
Days On Well | 12 | Slide ROP(Usft/hr) | 52.26
Start Depth (Usft) | 108.00 | Slide % | 12.15
End Depth (Usft) | 19389.00
Total Drilled (Usft) | 19281.00
# BHA's | 4
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 2.00 / 0.00
Phase Data
Phase | SUR | INT | CRV | CRV2 | LAT
Start Date | 07/17/2021 | 07/19/2021 | 07/21/2021 | 09/24/2021 | 09/24/2021
End Date | 07/18/2021 | 07/21/2021 | 07/22/2021 | 09/24/2021 | 09/29/2021
Total Days | 2.00 | 2.02 | 1.98 | 0.90 | 5.10
Start Depth (Usft) | 108.00 | 3492.00 | 10280.00 | 10936.00 | 11565.00
End Depth (Usft) | 3492.00 | 10280.00 | 10936.00 | 11565.00 | 19389.00
Total Drilled(Usft) | 3384.00 | 6788.00 | 656.00 | 629.00 | 7824.00
Drilling Hours | 6.62 | 21.83 | 20.68 | 6.12 | 60.25
Circulating Hours | 3.72 | 5.62 | 3.43 | 3.43 | 14.93
Total D&C Hours | 10.33 | 27.45 | 24.12 | 9.55 | 75.18
Avg ROP(Usft/hr) | 511.44 | 310.90 | 31.72 | 102.83 | 129.86
Rotary Drilled(Usft) | 3021.00 | 6453.00 | 15.00 | 237.00 | 7213.00
Rotary Hours | 4.92 | 18.47 | 0.15 | 1.77 | 45.38
Rotary ROP(Usft/hr) | 614.44 | 349.44 | 100.00 | 134.15 | 158.93
Rotary % | 89.27 | 95.06 | 2.29 | 37.68 | 92.19
Slide Drilled(Usft) | 363.00 | 335.00 | 641.00 | 392.00 | 611.00
Slide Hours | 1.70 | 3.37 | 20.53 | 4.35 | 14.87
Slide ROP(Usft/hr) | 213.53 | 99.50 | 31.22 | 90.11 | 41.10
Slide % | 10.73 | 4.94 | 97.71 | 62.32 | 7.81
# BHA | 1 | 1 | 1 | 1 | 2
# Motor Failures | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 1.00 / 0.00 | 1.00 / 0.00 | 0.00 / 0.00 | 0.00 / 0.00
Total Phase Hrs | 9.35 | 28.30 | 22.45 | 7.38 | 97.65
Phase ROP (Usft/hr) | 361.93 | 239.86 | 29.22 | 85.19 | 80.12
Avg Motor Yield (°/100ft) | 4.87 | 9.20 | 6.01 | 17.28 | 22.71
Avg Rotary DLS (°/100ft) | 0.30 | 0.30 | 0.00 | 0.00 | 0.89
Avg Rotary TF | 22.54 | -76.64 | 0.00 | 0.00 | -31.13
Avg Slide Length (Usft) | 16.50 | 13.40 | 71.22 | 54.57 | 15.67
# Slides | 22 | 25 | 9 | 7 | 39
BHA Data
BHA# | 1 | 2 | 3 | 4
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4
Bit Size | 13.500 | 9.875 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Halliburton / GTD64M | Halliburton / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491
Grade In | 0-0- | New | New | New
Grade Out | 0-0-NO-A-X-I-NO-TD | 1-1-BT-N-X-I-CT-TD |  | 0-1-WT-A-N-I-NO-TD
Motor SN | PPM800017 | PPM800011 | PPM250003 | PPM250015
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 11.7 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 11.7 | 6/7 / 8.8
WOB (klbs) | 3.00 / 16.68 / 35.20 | 2.00 / 24.16 / 38.00 | 20.00 / 25.64 / 50.00 | 30.00 / 33.09 / 55.00
Diff P (psi) | 66.00 / 356.62 / 815.00 | 114.00 / 493.61 / 800.00 | 800.00 / 940.19 / 1050.00 | 800.00 / 895.74 / 900.00
Bend | 1.500 | 2.000 | 2.120 | 2.120
Date In | 07/17/2021 | 07/19/2021 | 09/24/2021 | 09/27/2021
Date Out | 07/18/2021 | 07/22/2021 | 09/27/2021 | 09/29/2021
Time In | 16:00 | 13:50 | 04:40 | 09:30
Time Out | 05:40 | 18:00 | 08:00 | 17:30
BRT Hrs | 13.67 | 76.17 | 75.33 | 56.00
Start Depth (Usft) | 108.00 | 3492.00 | 10936.00 | 17133.00
End Depth (Usft) | 3492.00 | 10936.00 | 17133.00 | 19389.00
Total Drilled(Usft) | 3384.00 | 7444.00 | 6197.00 | 2256.00
Drilling Hours | 6.62 | 42.52 | 43.67 | 22.70
Circulating Hours | 3.72 | 9.05 | 12.32 | 6.05
Total D&C Hours | 10.33 | 51.57 | 55.98 | 28.75
Avg ROP(Usft/hr) | 511.44 | 175.08 | 141.92 | 99.38
Rotary Drilled(Usft) | 3021.00 | 6468.00 | 5437.00 | 2013.00
Rotary Hours | 4.92 | 18.62 | 32.65 | 14.50
Rotary ROP(Usft/hr) | 614.44 | 347.43 | 166.52 | 138.83
Rotary % | 89.27 | 86.89 | 87.74 | 89.23
Slide Drilled(Usft) | 363.00 | 976.00 | 760.00 | 243.00
Slide Hours | 1.70 | 23.90 | 11.02 | 8.20
Slide ROP(Usft/hr) | 213.53 | 40.84 | 68.99 | 29.63
Slide % | 10.73 | 13.11 | 12.26 | 10.77
Motor Failure | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO
Unplanned Trip | NO | NO | YES | NO
LIH | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 4.87 | 8.52 | 16.62 | 34.59
Avg Rotary DLS (°/100ft) | 0.30 | 0.30 | 0.74 | 1.30
Avg Rotary TF | 22.54 | -76.64 | -26.90 | -99.45
Avg Slide Length (Usft) | 16.50 | 28.71 | 22.73 | 18.69
# Slides | 22 | 34 | 33 | 13

## Personnel Report
|  | Job # | LTX1125621 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31163 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Redwood B1H
|  | Date: | 09/29/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Redwood B1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Danny Veronie | Day MWD |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
Danny Veronie | Day MWD |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
J. Ray X. Cantu | Night DD |  | 07/22/2021 - 00:00 | 07/22/2021 - 00:00 |  | 1.00 / 0.00
Jason Smetters | Night MWD |  | 07/22/2021 - 00:00 | 07/22/2021 - 00:00 |  | 1.00 / 0.00
Jason Smetters | Night MWD |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
Jason Smitters | Night MWD |  | 07/17/2021 - 00:00 | 07/21/2021 - 00:00 |  | 5.00 / 0.00
Jesse Taylor | Day DD |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
Jesse Taylor | Day DD |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
Josh Ray | Night DD |  | 07/17/2021 - 00:00 | 07/21/2021 - 00:00 |  | 5.00 / 0.00
Marshall Adams | Night DD |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
NA | Trainee 1 |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
NA | Trainee 1 |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
NA | Trainee 2 |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
NA | Trainee 2 |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
NA | Rss Eng. 1 |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
NA | Rss Eng. 1 |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
NA | Rss Eng. 2 |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
NA | Rss Eng. 2 |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
NA | Third Man |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
NA | Third Man |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
NA | Fourth Man |  | 07/17/2021 - 00:00 | 07/22/2021 - 00:00 |  | 6.00 / 0.00
NA | Fourth Man |  | 09/24/2021 - 00:00 | 09/29/2021 - 00:00 |  | 6.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1125621 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Redwood B1H | [7 empty] | Day DD: |  |  |  |  | Jesse Taylor | [5 empty] | API #: |  |  |  | 42-477-31163
|  |  |  | AFE #: |  |  | 20DD0220MG | [7 empty] | Night DD: |  |  |  |  | Marshall Adams | [5 empty] | Company Man: |  |  |  | Brandon Parks
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Jason Smetters | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 07/17/2021 | 07/18/2021 | 07/19/2021 | 07/20/2021 | 07/21/2021 | 07/22/2021 | 07/23/2021 | 07/24/2021 | 07/25/2021 | 07/26/2021 | 07/27/2021 | 07/28/2021 | 07/29/2021 | 07/30/2021 | 07/31/2021 | 08/01/2021 | 08/02/2021 | 08/03/2021 | 08/04/2021 | 08/05/2021 | 08/06/2021 | 08/07/2021 | 08/08/2021 | 08/09/2021 | 08/10/2021 | 08/11/2021 | 08/12/2021 | 08/13/2021 | 08/14/2021 | 08/15/2021 | 08/16/2021 | 08/17/2021 | 08/18/2021 | 08/19/2021 | 08/20/2021 | 08/21/2021 | 08/22/2021 | 08/23/2021 | 08/24/2021 | 08/25/2021 | 08/26/2021 | 08/27/2021 | 08/28/2021 | 08/29/2021 | 08/30/2021 | 08/31/2021 | 09/01/2021 | 09/02/2021 | 09/03/2021 | 09/04/2021 | 09/05/2021 | 09/06/2021 | 09/07/2021 | 09/08/2021 | 09/09/2021 | 09/10/2021 | 09/11/2021 | 09/12/2021 | 09/13/2021 | 09/14/2021 | 09/15/2021 | 09/16/2021 | 09/17/2021 | 09/18/2021 | 09/19/2021 | 09/20/2021 | 09/21/2021 | 09/22/2021 | 09/23/2021 | 09/24/2021 | 09/25/2021 | 09/26/2021 | 09/27/2021 | 09/28/2021 | 09/29/2021 | 09/30/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Cross Over |  | 5.188 | Crossover |  | Steel | GT52331432 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Cross Over |  | 5.375 | Crossover |  | Steel | GT52331430 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Cross Over |  | 5.375 | Crossover |  | Steel | GT52331100 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Cross Over |  | 5.25 | Crossover |  | Steel | GT52331431 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500048 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500046 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Motor |  | 5 | 7/8 3.8 2.50 TS HS88 -.004 |  | Steel | MTR500028 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 8.8 2.12 TS HS88 |  | Steel | PPM25007 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 8.8 2.12 TS HS88 -0.001 |  | Steel | PPM250004 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 8.8 2.12 TS HS88 +.022 |  | Steel | PPM250015 | 3 | 8 | [67 empty] | O | O | O | O | O | X | X | X
Motor |  | 5.25 | 5/6 9.5 1.83 TS EW |  | Steel | BPB5550-0003 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Collar |  | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-606 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Collar |  | 5.125 | NMDC (NO HARDBANDING) |  | Non-Mag | GT51-30-616 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Collar |  | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-481 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Collar |  | 5.25 | NMDC |  | Non-Mag | GT5230458 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Collar |  | 5.25 | NMDC |  | Non-Mag | GT5130618 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Collar |  | 5 | NMPC |  | Steel | GT5010533 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Collar |  | 5 | NMPC |  | Steel | GT5110622 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Collar |  | 5 | NMPC |  | Steel | GT5010585 | 0 | 1 | [74 empty] | O
Collar |  | 5 | NMPC |  | Steel | GT5010652 | 0 | 1 | [74 empty] | O
Sub |  | 5 | Float Sub |  | Steel | GT50331370FF | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Sub |  | 5 | Float Sub |  | Steel | GT50331372FF | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Sub |  | 5.5 | Lift Sub |  | Steel | GT551232 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Sub |  | 5.5 | Lift Sub |  | Steel | GT551251 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Sub |  | 5 | Filter Sub |  | Steel | GT5033743 | 6 | 8 | [67 empty] | O | O | X | X | X | X | X | X
Sub |  | 5 | Filter Sub |  | Steel | GT50331343 | 0 | 8 | [67 empty] | O | O | O | O | O | O | O | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 12 |  | 1 | 1 | 1 | 1 | 1 | 1 | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | J. Ray X. Cantu |  |  |  | 1 | [6 empty] | 1
Night DD |  |  | Josh Ray |  |  |  | 5 |  | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Marshall Adams |  |  |  | 6 | [70 empty] | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 12 |  | 1 | 1 | 1 | 1 | 1 | 1 | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smetters |  |  |  | 7 | [6 empty] | 1 | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smitters |  |  |  | 5 |  | 1 | 1 | 1 | 1 | 1
Third Man |  |  | NA |  |  |  | 12 |  | 1 | 1 | 1 | 1 | 1 | 1 | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 12 |  | 1 | 1 | 1 | 1 | 1 | 1 | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Redwood B1H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0220MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
MTR500028 | 7/8 3.8 2.50 TS HS88 -.004 | 5 | 26.11 |  | XT39 / 3 1/2 Reg | Clean |  | 09/22/2021 |  | 09/29/2021
PPM25007 | 6/7 8.8 2.12 TS HS88 | 5.5 | 33.11 |  | XT39 / 3 1/2 Reg | Clean |  | 09/22/2021 |  | 09/29/2021
PPM250004 | 6/7 8.8 2.12 TS HS88 -0.001 | 5.5 | 33.11 |  | XT39 / 3 1/2 Reg | Clean |  | 09/22/2021 |  | 09/29/2021
PPM250015 | 6/7 8.8 2.12 TS HS88 +.022 | 5.5 | 33.15 |  | XT39 / 3 1/2 Reg | Dirty |  | 09/22/2021 |  | 09/29/2021
BPB5550-0003 | 5/6 9.5 1.83 TS EW | 5.25 | 32 |  | XT39 / 3 1/2 Reg | Clean |  | 09/22/2021 |  | 09/29/2021
GT50-30-606 | NMDC (NO HARDBANDING) | 5 | 30.72 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT51-30-616 | NMDC (NO HARDBANDING) | 5.125 | 29.28 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT50-30-481 | NMDC (NO HARDBANDING) | 5 | 29.93 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
500048 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT52331432 | Crossover | 5.188 | 3.64 |  | CET43 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT52331430 | Crossover | 5.375 |  |  | CET43 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT52331100 | Crossover | 5.375 | 2.6 |  | CET43 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT52331431 | Crossover | 5.25 | 3.37 |  | CET43 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT50331370FF | Float Sub | 5 | 3.08 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT50331372FF | Float Sub | 5 | 3.1 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT551232 | Lift Sub | 5.5 | 3.3 |  | XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT551251 | Lift Sub | 5.5 | 3.35 |  | XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT180 | Lift Cap |  |  |  | XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT126 | Lift Cap |  |  |  | XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
500046 | UBHO | 5.25 | 3.83 |  | XT39 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT5230458 | NMDC | 5.25 | 30.54 |  | XT39 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT5130618 | NMDC | 5.25 | 31.23 |  | XT39 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT5010533 | NMPC | 5 | 9.88 |  | XT39 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT5110622 | NMPC | 5 | 7.49 |  | XT39 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT5033743 | Filter Sub | 5 | 4.95 |  | XT39 / XT39 | Dirty |  | 09/22/2021 |  | 09/29/2021
GT50331343 | Filter Sub | 5 | 4.95 |  | XT39 / XT39 | Clean |  | 09/22/2021 |  | 09/29/2021
GT5010585 | NMPC | 5 |  |  |  | Clean |  | 09/29/2021 |  | 09/29/2021
GT5010652 | NMPC | 5 |  |  |  | Clean |  | 09/29/2021 |  | 09/29/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Redwood B1H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 47424 | 07/17/2021 | 09/29/2021 | 75 | 1 | 1 |  | 3.72 | 6.62 | 13.67
7/8 5.9 1.50 Stab HPO -.011 NBS 13 | PPM800017 | 07/17/2021 | 09/29/2021 | 75 | 1 | 1 |  | 3.72 | 6.62 | 13.67
13 Stab | SD603251 | 07/17/2021 | 09/29/2021 | 75 | 1 | 1 |  | 3.72 | 6.62 | 13.67
NMPC | SD55524 | 07/17/2021 | 09/29/2021 | 75 | 4 | 1 ,2 |  | 12.77 | 49.13 | 89.83
UBHO Sub UBHO Sub | 775213 | 07/17/2021 | 09/29/2021 | 75 | 1 | 1 |  | 3.72 | 6.62 | 13.67
NMDC | SD56120 | 07/17/2021 | 09/29/2021 | 75 | 4 | 1 ,2 |  | 12.77 | 49.13 | 89.83
NMDC | SD55920 | 07/17/2021 | 09/29/2021 | 75 | 4 | 1 ,2 |  | 12.77 | 49.13 | 89.83
Crossover Sub | SD117248 | 07/17/2021 | 09/29/2021 | 75 | 1 | 1 |  | 3.72 | 6.62 | 13.67
SPL613 | 55156 | 07/17/2021 | 09/29/2021 | 75 | 3 | 2 |  | 9.05 | 42.52 | 76.17
7/8 5.9 2.00 Slick HPO -.006 | PPM800011 | 07/17/2021 | 09/29/2021 | 75 | 3 | 2 |  | 9.05 | 42.52 | 76.17
UBHO Sub | 775213 | 07/17/2021 | 09/29/2021 | 75 | 3 | 2 |  | 9.05 | 42.52 | 76.17
Crossover Sub | SD103353 | 07/17/2021 | 09/29/2021 | 75 | 3 | 2 |  | 9.05 | 42.52 | 76.17
Crossover Sub | SD103463 | 07/17/2021 | 09/29/2021 | 75 | 3 | 2 |  | 9.05 | 42.52 | 76.17
Agitator | PG675-0022 | 07/17/2021 | 09/29/2021 | 75 | 3 | 2 |  | 9.05 | 42.52 | 76.17
GTD64M | 13635755 | 07/17/2021 | 09/29/2021 | 75 | 3 | 3 |  | 12.32 | 43.67 | 75.33
6/7 11.7 2.12 TS HS88 +.011 | PPM250003 | 07/17/2021 | 09/29/2021 | 75 | 3 | 3 |  | 12.32 | 43.67 | 75.33
BTI | BTI3 | 07/17/2021 | 09/29/2021 | 75 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
NMPC | GT5110622 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
UBHO | 500046 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
NMDC | GT5130618 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
NMPC | GT5010533 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
NMDC | GT5230458 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
Filter Sub | GT5033743 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
Tomax | A52130 | 07/17/2021 | 09/29/2021 | 75 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
Crossover | GT52331100 | 09/22/2021 | 09/29/2021 | 8 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
Drill-N-Ream | 531 | 07/17/2021 | 09/29/2021 | 75 | 5 | 3 ,4 |  | 18.37 | 66.37 | 131.33
Agitator | PG525-0057 | 07/17/2021 | 09/29/2021 | 75 | 3 | 3 |  | 12.32 | 43.67 | 75.33
GTD64M | 13601237 | 07/17/2021 | 09/29/2021 | 75 | 2 | 4 |  | 6.05 | 22.7 | 56
6/7 8.8 2.12 TS HS88 +.022 | PPM250015 | 09/22/2021 | 09/29/2021 | 8 | 2 | 4 |  | 6.05 | 22.7 | 56
Agitator | ST5250050 | 07/17/2021 | 09/29/2021 | 75 | 2 | 4 |  | 6.05 | 22.7 | 56
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well-GL: 359 + KB: 28 (Pat248)
Facility |  |  | Rommel-Redwood - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Redwood B1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Redwood B1H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 387.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Rommel-Redwood - Washington County, TX
Map Northing |  |  | 224504.93 US survey foot |  |  | Map Easting |  |  | 3168972.23 US survey foot
Latitude |  |  | 30° 13' 49.70133" N |  |  | Longitude |  |  | 96° 37' 52.49452" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.907
Well: |  |  | Redwood B1H
Local North |  |  | -26.14 Usft |  |  | Local East |  |  | -23.53 Usft
Map Northing |  |  | 224478.34 US survey foot |  |  | Map Easting |  |  | 3168942.36 US survey foot
Latitude |  |  | 30° 13' 49.45044" N |  |  | Longitude |  |  | 96° 37' 52.77253" W
Depth Datum |  |  | Well-GL: 359 + KB: 28 (Pat248) |  |  | Datum Elevation |  |  | 387.00 Usft
GL Elevation |  |  | 359.00 Usft
Grid Convergence |  |  | 1.907
Well bore: |  |  | Redwood B1H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 04/07/2021
Total Field (nT) |  |  | 46654.5 |  |  | Dip Angle (°) |  |  | 58.867
Declination (°) |  |  | 2.983
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 152.22
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Redwood B1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3420 |  |  | Redwood B1H S1 |  |  | MWD+HDGM
3420 |  |  | 10873 |  |  | Redwood B1H S2 |  |  | MWD+HDGM
10873 |  |  | 17014 |  |  | Redwood B1H S3 |  |  | MWD+HDGM
17014 |  |  | 19389 |  |  | Redwood B1H S4 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -387 | 224478.34 | 3168942.36 | 30.2304 | -96.6313 | 0
198 | 0.04 | 359.23 | 198 | 0.07 | 0 | -0.06 | 0.02 | 0.02 | 0.39 | 359.23 | 198 | -189 | 224478.41 | 3168942.36 | 30.2304 | -96.6313 | 359.23
289 | 0.04 | 292.44 | 289 | 0.11 | -0.03 | -0.11 | 0.05 | 0 | -73.4 | -123.39 | 91 | -98 | 224478.45 | 3168942.33 | 30.2304 | -96.6313 | 344.79
382 | 0.26 | 240.76 | 382 | 0.02 | -0.24 | -0.13 | 0.26 | 0.24 | -55.57 | -59.28 | 93 | -5 | 224478.36 | 3168942.12 | 30.2304 | -96.6313 | 275.21
507 | 0.35 | 252.71 | 507 | -0.23 | -0.86 | -0.2 | 0.09 | 0.07 | 9.56 | 41.33 | 125 | 120 | 224478.11 | 3168941.5 | 30.2304 | -96.6313 | 254.99
601 | 0.26 | 244.98 | 601 | -0.41 | -1.32 | -0.26 | 0.11 | -0.1 | -8.22 | -159.26 | 94 | 214 | 224477.93 | 3168941.04 | 30.2304 | -96.6313 | 252.99
695 | 0.26 | 250.43 | 695 | -0.57 | -1.72 | -0.3 | 0.03 | 0 | 5.8 | 92.72 | 94 | 308 | 224477.77 | 3168940.64 | 30.2304 | -96.6314 | 251.74
789 | 0.35 | 261.06 | 788.99 | -0.68 | -2.2 | -0.42 | 0.11 | 0.1 | 11.31 | 37.55 | 94 | 401.99 | 224477.66 | 3168940.16 | 30.2304 | -96.6314 | 252.78
883 | 0.35 | 299.73 | 882.99 | -0.59 | -2.74 | -0.76 | 0.25 | 0 | 41.14 | 109.33 | 94 | 495.99 | 224477.75 | 3168939.62 | 30.2304 | -96.6314 | 257.93
977 | 1.01 | 279.34 | 976.99 | -0.31 | -3.8 | -1.5 | 0.74 | 0.7 | -21.69 | -30.53 | 94 | 589.99 | 224478.03 | 3168938.56 | 30.2304 | -96.6314 | 265.36
1071 | 1.93 | 270.38 | 1070.95 | -0.16 | -6.2 | -2.75 | 1.01 | 0.98 | -9.53 | -18.53 | 94 | 683.95 | 224478.18 | 3168936.16 | 30.2304 | -96.6314 | 268.49
1166 | 3.12 | 278.99 | 1165.86 | 0.25 | -10.36 | -5.05 | 1.31 | 1.25 | 9.06 | 22.01 | 95 | 778.86 | 224478.59 | 3168932 | 30.2304 | -96.6314 | 271.39
1259 | 3.34 | 283.47 | 1258.71 | 1.28 | -15.49 | -8.35 | 0.36 | 0.24 | 4.82 | 51.18 | 93 | 871.71 | 224479.62 | 3168926.87 | 30.2304 | -96.6314 | 274.72
1353 | 3.74 | 285.05 | 1352.53 | 2.71 | -21.11 | -12.24 | 0.44 | 0.43 | 1.68 | 14.5 | 94 | 965.53 | 224481.05 | 3168921.25 | 30.2304 | -96.6314 | 277.32
1447 | 4.48 | 286.64 | 1446.29 | 4.56 | -27.59 | -16.89 | 0.8 | 0.79 | 1.69 | 9.55 | 94 | 1059.29 | 224482.9 | 3168914.77 | 30.2304 | -96.6314 | 279.38
1542 | 5.76 | 281.36 | 1540.91 | 6.56 | -35.82 | -22.5 | 1.43 | 1.35 | -5.56 | -22.85 | 95 | 1153.91 | 224484.9 | 3168906.54 | 30.2304 | -96.6315 | 280.38
1635 | 6.42 | 274.42 | 1633.39 | 7.88 | -45.58 | -28.22 | 1.06 | 0.71 | -7.46 | -51.61 | 93 | 1246.39 | 224486.22 | 3168896.78 | 30.2304 | -96.6315 | 279.81
1729 | 7.08 | 270.38 | 1726.73 | 8.32 | -56.61 | -33.75 | 0.86 | 0.7 | -4.3 | -37.75 | 94 | 1339.73 | 224486.66 | 3168885.75 | 30.2304 | -96.6315 | 278.36
1822 | 7.69 | 269.76 | 1818.96 | 8.34 | -68.57 | -39.33 | 0.66 | 0.66 | -0.67 | -7.75 | 93 | 1431.96 | 224486.68 | 3168873.79 | 30.2304 | -96.6316 | 276.93
1916 | 8.83 | 267.74 | 1911.99 | 8.03 | -82.07 | -45.35 | 1.25 | 1.21 | -2.15 | -15.28 | 94 | 1524.99 | 224486.37 | 3168860.29 | 30.2304 | -96.6316 | 275.59
2011 | 9.62 | 270.03 | 2005.76 | 7.74 | -97.29 | -52.19 | 0.92 | 0.83 | 2.41 | 26.06 | 95 | 1618.76 | 224486.08 | 3168845.07 | 30.2304 | -96.6317 | 274.55
2106 | 9.98 | 268.62 | 2099.37 | 7.55 | -113.46 | -59.56 | 0.46 | 0.38 | -1.48 | -34.39 | 95 | 1712.37 | 224485.89 | 3168828.9 | 30.2304 | -96.6317 | 273.81
2200 | 10.63 | 267.56 | 2191.85 | 6.98 | -130.26 | -66.89 | 0.72 | 0.69 | -1.13 | -16.79 | 94 | 1804.85 | 224485.32 | 3168812.1 | 30.2304 | -96.6318 | 273.07
2293 | 11.47 | 270.11 | 2283.13 | 6.63 | -148.08 | -74.89 | 1.04 | 0.9 | 2.74 | 31.45 | 93 | 1896.13 | 224484.97 | 3168794.28 | 30.2304 | -96.6318 | 272.57
2387 | 12.57 | 271.52 | 2375.07 | 6.92 | -167.65 | -84.27 | 1.21 | 1.17 | 1.5 | 15.64 | 94 | 1988.07 | 224485.26 | 3168774.71 | 30.2304 | -96.6319 | 272.37
2481 | 13.67 | 271.96 | 2466.61 | 7.58 | -188.98 | -94.78 | 1.18 | 1.17 | 0.47 | 5.4 | 94 | 2079.61 | 224485.92 | 3168753.38 | 30.2304 | -96.6319 | 272.3
2575 | 13.89 | 268.27 | 2557.91 | 7.61 | -211.36 | -105.25 | 0.96 | 0.23 | -3.93 | -77.74 | 94 | 2170.91 | 224485.95 | 3168731 | 30.2304 | -96.632 | 272.06
2669 | 13.93 | 265.98 | 2649.15 | 6.48 | -233.92 | -114.76 | 0.59 | 0.04 | -2.44 | -86.96 | 94 | 2262.15 | 224484.82 | 3168708.44 | 30.2304 | -96.6321 | 271.59
2763 | 13.4 | 265.37 | 2740.49 | 4.81 | -256.07 | -123.6 | 0.58 | -0.56 | -0.65 | -165.08 | 94 | 2353.49 | 224483.15 | 3168686.29 | 30.2304 | -96.6322 | 271.08
2857 | 13.45 | 265.19 | 2831.92 | 3.01 | -277.82 | -132.15 | 0.07 | 0.05 | -0.19 | -39.98 | 94 | 2444.92 | 224481.35 | 3168664.54 | 30.2304 | -96.6322 | 270.62
2952 | 13.97 | 269.06 | 2924.22 | 1.9 | -300.29 | -141.64 | 1.11 | 0.55 | 4.07 | 62.34 | 95 | 2537.22 | 224480.24 | 3168642.07 | 30.2304 | -96.6323 | 270.36
3045 | 14.46 | 271.7 | 3014.37 | 2.06 | -323.12 | -152.42 | 0.87 | 0.53 | 2.84 | 54.2 | 93 | 2627.37 | 224480.4 | 3168619.24 | 30.2304 | -96.6324 | 270.36
3139 | 14.11 | 269.85 | 3105.46 | 2.38 | -346.31 | -163.51 | 0.61 | -0.37 | -1.97 | -128.37 | 94 | 2718.46 | 224480.72 | 3168596.05 | 30.2304 | -96.6324 | 270.39
3233 | 13.84 | 269.76 | 3196.68 | 2.3 | -369.01 | -174.02 | 0.29 | -0.29 | -0.1 | -175.44 | 94 | 2809.68 | 224480.64 | 3168573.35 | 30.2304 | -96.6325 | 270.36
3326 | 13.67 | 269.15 | 3287.02 | 2.09 | -391.12 | -184.14 | 0.24 | -0.18 | -0.66 | -139.83 | 93 | 2900.02 | 224480.43 | 3168551.24 | 30.2304 | -96.6326 | 270.31
3420 | 14.28 | 270.03 | 3378.23 | 1.93 | -413.82 | -194.58 | 0.69 | 0.65 | 0.94 | 19.64 | 94 | 2991.23 | 224480.27 | 3168528.54 | 30.2304 | -96.6327 | 270.27
3542 | 14.5 | 269.17 | 3496.41 | 1.72 | -444.14 | -208.52 | 0.25 | 0.18 | -0.7 | -44.59 | 122 | 3109.41 | 224480.06 | 3168498.22 | 30.2304 | -96.6328 | 270.22
3636 | 14.52 | 270.47 | 3587.41 | 1.64 | -467.69 | -219.43 | 0.35 | 0.02 | 1.38 | 87.12 | 94 | 3200.41 | 224479.98 | 3168474.67 | 30.2305 | -96.6328 | 270.2
3730 | 14.61 | 269.44 | 3678.39 | 1.62 | -491.33 | -230.44 | 0.29 | 0.1 | -1.1 | -71.34 | 94 | 3291.39 | 224479.96 | 3168451.03 | 30.2305 | -96.6329 | 270.19
3824 | 14.55 | 269.65 | 3769.36 | 1.44 | -514.99 | -241.3 | 0.09 | -0.06 | 0.22 | 138.72 | 94 | 3382.36 | 224479.78 | 3168427.37 | 30.2305 | -96.633 | 270.16
3919 | 14.73 | 268.83 | 3861.28 | 1.12 | -539 | -252.2 | 0.29 | 0.19 | -0.86 | -49.42 | 95 | 3474.28 | 224479.46 | 3168403.36 | 30.2305 | -96.6331 | 270.12
4012 | 14.85 | 268.82 | 3951.19 | 0.63 | -562.73 | -262.84 | 0.13 | 0.13 | -0.01 | -1.22 | 93 | 3564.19 | 224478.97 | 3168379.63 | 30.2305 | -96.6331 | 270.06
4105 | 14.79 | 268.59 | 4041.1 | 0.09 | -586.52 | -273.44 | 0.09 | -0.06 | -0.25 | -135.68 | 93 | 3654.1 | 224478.43 | 3168355.84 | 30.2305 | -96.6332 | 270.01
4197 | 14.56 | 268.97 | 4130.1 | -0.4 | -609.82 | -283.87 | 0.27 | -0.25 | 0.41 | 157.47 | 92 | 3743.1 | 224477.94 | 3168332.54 | 30.2305 | -96.6333 | 269.96
4290 | 14.43 | 268.77 | 4220.14 | -0.86 | -633.09 | -294.31 | 0.15 | -0.14 | -0.22 | -159.04 | 93 | 3833.14 | 224477.48 | 3168309.27 | 30.2305 | -96.6333 | 269.92
4384 | 13.74 | 269.81 | 4311.31 | -1.15 | -655.96 | -304.71 | 0.78 | -0.73 | 1.11 | 160.36 | 94 | 3924.31 | 224477.19 | 3168286.4 | 30.2305 | -96.6334 | 269.9
4477 | 13.89 | 269.9 | 4401.62 | -1.21 | -678.17 | -315.01 | 0.16 | 0.16 | 0.1 | 8.2 | 93 | 4014.62 | 224477.13 | 3168264.19 | 30.2305 | -96.6335 | 269.9
4571 | 12.99 | 269.51 | 4493.05 | -1.32 | -700.02 | -325.1 | 0.96 | -0.96 | -0.41 | -174.44 | 94 | 4106.05 | 224477.02 | 3168242.34 | 30.2305 | -96.6336 | 269.89
4664 | 12.77 | 264.24 | 4583.71 | -2.44 | -720.7 | -333.74 | 1.28 | -0.24 | -5.67 | -103.17 | 93 | 4196.71 | 224475.9 | 3168221.66 | 30.2305 | -96.6336 | 269.81
4759 | 13.2 | 262.3 | 4676.28 | -4.95 | -741.89 | -341.4 | 0.64 | 0.45 | -2.04 | -46.34 | 95 | 4289.28 | 224473.39 | 3168200.47 | 30.2305 | -96.6337 | 269.62
4853 | 12.02 | 262.45 | 4768.01 | -7.67 | -762.23 | -348.47 | 1.26 | -1.26 | 0.16 | 178.48 | 94 | 4381.01 | 224470.67 | 3168180.13 | 30.2305 | -96.6338 | 269.42
4947 | 11.14 | 257.78 | 4860.1 | -10.88 | -780.81 | -354.29 | 1.37 | -0.94 | -4.97 | -135.46 | 94 | 4473.1 | 224467.46 | 3168161.55 | 30.2304 | -96.6338 | 269.2
5041 | 10.23 | 255.57 | 4952.47 | -14.88 | -797.77 | -358.66 | 1.06 | -0.97 | -2.35 | -156.84 | 94 | 4565.47 | 224463.46 | 3168144.59 | 30.2304 | -96.6339 | 268.93
5134 | 9.77 | 252.98 | 5044.06 | -19.25 | -813.31 | -362.04 | 0.69 | -0.49 | -2.78 | -136.92 | 93 | 4657.06 | 224459.09 | 3168129.05 | 30.2304 | -96.6339 | 268.64
5229 | 8.1 | 255.26 | 5137.9 | -23.31 | -827.49 | -365.05 | 1.8 | -1.76 | 2.4 | 169.15 | 95 | 4750.9 | 224455.03 | 3168114.87 | 30.2304 | -96.634 | 268.39
5322 | 6.71 | 257.59 | 5230.12 | -26.15 | -839.14 | -367.97 | 1.53 | -1.49 | 2.51 | 168.96 | 93 | 4843.12 | 224452.19 | 3168103.22 | 30.2304 | -96.634 | 268.22
5416 | 4.88 | 256.17 | 5323.64 | -28.28 | -848.38 | -370.39 | 1.95 | -1.95 | -1.51 | -176.23 | 94 | 4936.64 | 224450.06 | 3168093.98 | 30.2304 | -96.634 | 268.09
5510 | 3.7 | 274.01 | 5417.38 | -29.03 | -855.29 | -372.95 | 1.88 | -1.26 | 18.98 | 140.15 | 94 | 5030.38 | 224449.31 | 3168087.07 | 30.2304 | -96.6341 | 268.06
5604 | 2.06 | 298.6 | 5511.26 | -28 | -859.8 | -375.96 | 2.15 | -1.74 | 26.16 | 154.86 | 94 | 5124.26 | 224450.34 | 3168082.56 | 30.2304 | -96.6341 | 268.13
5699 | 1.96 | 325.57 | 5606.2 | -25.85 | -862.22 | -378.99 | 0.99 | -0.11 | 28.39 | 109.4 | 95 | 5219.2 | 224452.49 | 3168080.14 | 30.2304 | -96.6341 | 268.28
5792 | 2 | 352.82 | 5699.15 | -22.92 | -863.32 | -382.09 | 1 | 0.04 | 29.3 | 101.23 | 93 | 5312.15 | 224455.42 | 3168079.04 | 30.2304 | -96.6341 | 268.48
5886 | 2.42 | 347.57 | 5793.08 | -19.36 | -863.95 | -385.54 | 0.5 | 0.45 | -5.59 | -28.37 | 94 | 5406.08 | 224458.98 | 3168078.41 | 30.2304 | -96.6341 | 268.72
5980 | 0.95 | 309.7 | 5887.04 | -16.92 | -864.98 | -388.18 | 1.88 | -1.56 | -40.29 | -160.75 | 94 | 5500.04 | 224461.42 | 3168077.38 | 30.2304 | -96.6341 | 268.88
6074 | 1.17 | 285.97 | 5981.02 | -16.16 | -866.5 | -389.56 | 0.52 | 0.23 | -25.24 | -75.58 | 94 | 5594.02 | 224462.18 | 3168075.86 | 30.2304 | -96.6341 | 268.93
6168 | 1.46 | 302.88 | 6075 | -15.25 | -868.43 | -391.27 | 0.51 | 0.31 | 17.99 | 61.88 | 94 | 5688 | 224463.09 | 3168073.93 | 30.2304 | -96.6341 | 268.99
6262 | 1.61 | 303.64 | 6168.96 | -13.87 | -870.54 | -393.47 | 0.16 | 0.16 | 0.81 | 8.11 | 94 | 5781.96 | 224464.47 | 3168071.82 | 30.2304 | -96.6341 | 269.09
6355 | 1.73 | 307.7 | 6261.92 | -12.28 | -872.74 | -395.89 | 0.18 | 0.13 | 4.37 | 46.64 | 93 | 5874.92 | 224466.06 | 3168069.62 | 30.2304 | -96.6341 | 269.19
6449 | 0.92 | 279.91 | 6355.9 | -11.29 | -874.6 | -397.65 | 1.08 | -0.86 | -29.56 | -154.91 | 94 | 5968.9 | 224467.05 | 3168067.76 | 30.2305 | -96.6341 | 269.26
6543 | 0.85 | 219.9 | 6449.89 | -11.69 | -875.79 | -397.84 | 0.94 | -0.07 | -63.84 | -123.92 | 94 | 6062.89 | 224466.65 | 3168066.57 | 30.2305 | -96.6341 | 269.24
6637 | 0.72 | 167.1 | 6543.88 | -12.8 | -876.11 | -397.01 | 0.75 | -0.14 | -56.17 | -125.87 | 94 | 6156.88 | 224465.54 | 3168066.25 | 30.2304 | -96.6341 | 269.16
6732 | 0.47 | 206.33 | 6638.88 | -13.73 | -876.15 | -396.2 | 0.49 | -0.26 | 41.29 | 140.13 | 95 | 6251.88 | 224464.61 | 3168066.21 | 30.2304 | -96.6341 | 269.1
6826 | 0.51 | 217.69 | 6732.87 | -14.41 | -876.57 | -395.8 | 0.11 | 0.04 | 12.09 | 73.37 | 94 | 6345.87 | 224463.93 | 3168065.79 | 30.2304 | -96.6341 | 269.06
6919 | 0.59 | 125.8 | 6825.87 | -15.02 | -876.44 | -395.2 | 0.85 | 0.09 | -98.81 | -131.92 | 93 | 6438.87 | 224463.32 | 3168065.92 | 30.2304 | -96.6341 | 269.02
7014 | 1.03 | 111.51 | 6920.86 | -15.62 | -875.25 | -394.12 | 0.51 | 0.46 | -15.04 | -31.92 | 95 | 6533.86 | 224462.72 | 3168067.11 | 30.2304 | -96.6341 | 268.98
7108 | 0.82 | 104.26 | 7014.85 | -16.09 | -873.81 | -393.03 | 0.26 | -0.22 | -7.71 | -154.46 | 94 | 6627.85 | 224462.25 | 3168068.55 | 30.2304 | -96.6341 | 268.95
7201 | 0.7 | 82.9 | 7107.84 | -16.19 | -872.6 | -392.38 | 0.33 | -0.13 | -22.97 | -123.39 | 93 | 6720.84 | 224462.15 | 3168069.76 | 30.2304 | -96.6341 | 268.94
7295 | 0.76 | 61.92 | 7201.83 | -15.82 | -871.48 | -392.18 | 0.29 | 0.06 | -22.32 | -87.97 | 94 | 6814.83 | 224462.52 | 3168070.88 | 30.2304 | -96.6341 | 268.96
7389 | 0.82 | 59.15 | 7295.83 | -15.18 | -870.35 | -392.22 | 0.08 | 0.06 | -2.95 | -33.87 | 94 | 6908.83 | 224463.16 | 3168072.01 | 30.2304 | -96.6341 | 269
7483 | 0.69 | 44.51 | 7389.82 | -14.43 | -869.38 | -392.43 | 0.25 | -0.14 | -15.57 | -131.15 | 94 | 7002.82 | 224463.91 | 3168072.98 | 30.2304 | -96.6341 | 269.05
7577 | 0.76 | 40.21 | 7483.81 | -13.55 | -868.58 | -392.83 | 0.09 | 0.07 | -4.57 | -40.02 | 94 | 7096.81 | 224464.79 | 3168073.78 | 30.2304 | -96.6341 | 269.11
7670 | 0.95 | 9.95 | 7576.8 | -12.32 | -868.05 | -393.67 | 0.52 | 0.2 | -32.54 | -82.79 | 93 | 7189.8 | 224466.02 | 3168074.31 | 30.2304 | -96.6341 | 269.19
7764 | 1.16 | 340.87 | 7670.78 | -10.66 | -868.23 | -395.23 | 0.6 | 0.22 | 30.94 | -83.54 | 94 | 7283.78 | 224467.68 | 3168074.13 | 30.2305 | -96.6341 | 269.3
7857 | 0.58 | 339.92 | 7763.77 | -9.33 | -868.7 | -396.63 | 0.62 | -0.62 | -1.02 | -179.05 | 93 | 7376.77 | 224469.01 | 3168073.66 | 30.2305 | -96.6341 | 269.38
7951 | 0.92 | 322.02 | 7857.77 | -8.28 | -869.32 | -397.84 | 0.44 | 0.36 | -19.04 | -43.74 | 94 | 7470.77 | 224470.06 | 3168073.04 | 30.2305 | -96.6341 | 269.45
8045 | 1.6 | 330.4 | 7951.74 | -6.55 | -870.44 | -399.9 | 0.75 | 0.72 | 8.91 | 19.38 | 94 | 7564.74 | 224471.79 | 3168071.92 | 30.2305 | -96.6341 | 269.57
8139 | 1.67 | 344.01 | 8045.7 | -4.09 | -871.46 | -402.55 | 0.42 | 0.07 | 14.48 | 86.63 | 94 | 7658.7 | 224474.25 | 3168070.9 | 30.2305 | -96.6341 | 269.73
8232 | 1.47 | 51.42 | 8138.68 | -2.04 | -870.9 | -404.1 | 1.88 | -0.22 | 72.48 | 129.15 | 93 | 7751.68 | 224476.3 | 3168071.46 | 30.2305 | -96.6341 | 269.87
8326 | 1.48 | 60.76 | 8232.65 | -0.7 | -868.9 | -404.36 | 0.26 | 0.01 | 9.94 | 92.29 | 94 | 7845.65 | 224477.64 | 3168073.46 | 30.2305 | -96.6341 | 269.95
8420 | 1.39 | 53.58 | 8326.62 | 0.57 | -866.92 | -404.56 | 0.21 | -0.1 | -7.64 | -120.15 | 94 | 7939.62 | 224478.91 | 3168075.44 | 30.2305 | -96.6341 | 270.04
8515 | 1.43 | 61.1 | 8421.59 | 1.83 | -864.96 | -404.76 | 0.2 | 0.04 | 7.92 | 81.58 | 95 | 8034.59 | 224480.17 | 3168077.4 | 30.2305 | -96.6341 | 270.12
8609 | 1.07 | 50.44 | 8515.56 | 2.95 | -863.26 | -404.96 | 0.45 | -0.38 | -11.34 | -152.39 | 94 | 8128.56 | 224481.29 | 3168079.1 | 30.2305 | -96.6341 | 270.2
8703 | 1.06 | 40.28 | 8609.55 | 4.18 | -862.02 | -405.46 | 0.2 | -0.01 | -10.81 | -98.1 | 94 | 8222.55 | 224482.52 | 3168080.34 | 30.2305 | -96.6341 | 270.28
8797 | 1.13 | 16.53 | 8703.53 | 5.73 | -861.19 | -406.45 | 0.48 | 0.07 | -25.27 | -93.23 | 94 | 8316.53 | 224484.07 | 3168081.17 | 30.2305 | -96.6341 | 270.38
8891 | 1.08 | 15.41 | 8797.51 | 7.47 | -860.69 | -407.76 | 0.06 | -0.05 | -1.19 | -157.2 | 94 | 8410.51 | 224485.81 | 3168081.67 | 30.2305 | -96.6341 | 270.5
8986 | 0.86 | 3.85 | 8892.5 | 9.05 | -860.41 | -409.02 | 0.31 | -0.23 | -12.17 | -144.03 | 95 | 8505.5 | 224487.39 | 3168081.95 | 30.2305 | -96.6341 | 270.6
9079 | 0.83 | 1.52 | 8985.49 | 10.41 | -860.34 | -410.2 | 0.05 | -0.03 | -2.51 | -132.28 | 93 | 8598.49 | 224488.75 | 3168082.02 | 30.2305 | -96.6341 | 270.69
9173 | 1.15 | 4.62 | 9079.48 | 12.04 | -860.25 | -411.59 | 0.35 | 0.34 | 3.3 | 11.05 | 94 | 8692.48 | 224490.38 | 3168082.11 | 30.2305 | -96.6341 | 270.8
9267 | 0.99 | 355.47 | 9173.46 | 13.79 | -860.24 | -413.13 | 0.25 | -0.17 | 9.73 | -137.63 | 94 | 8786.46 | 224492.13 | 3168082.12 | 30.2305 | -96.6341 | 270.92
9360 | 1.29 | 328.24 | 9266.44 | 15.48 | -860.85 | -414.92 | 0.66 | 0.32 | -29.28 | -75.1 | 93 | 8879.44 | 224493.82 | 3168081.51 | 30.2305 | -96.6341 | 271.03
9454 | 1.42 | 321.16 | 9360.42 | 17.28 | -862.14 | -417.11 | 0.23 | 0.14 | -7.53 | -55.75 | 94 | 8973.42 | 224495.62 | 3168080.22 | 30.2305 | -96.6341 | 271.15
9549 | 0.75 | 313.13 | 9455.4 | 18.63 | -863.33 | -418.86 | 0.72 | -0.71 | -8.45 | -171.21 | 95 | 9068.4 | 224496.97 | 3168079.03 | 30.2305 | -96.6341 | 271.24
9644 | 0.95 | 325.24 | 9550.39 | 19.7 | -864.23 | -420.23 | 0.28 | 0.21 | 12.75 | 48.09 | 95 | 9163.39 | 224498.04 | 3168078.13 | 30.2305 | -96.6341 | 271.31
9738 | 0.52 | 4 | 9644.38 | 20.76 | -864.65 | -421.36 | 0.67 | -0.46 | 41.23 | 149.13 | 94 | 9257.38 | 224499.1 | 3168077.71 | 30.2305 | -96.6341 | 271.38
9831 | 0.38 | 345.1 | 9737.38 | 21.48 | -864.7 | -422.02 | 0.22 | -0.15 | 20.32 | -142.51 | 93 | 9350.38 | 224499.82 | 3168077.66 | 30.2305 | -96.6341 | 271.42
9924 | 0.51 | 336.31 | 9830.38 | 22.16 | -864.94 | -422.74 | 0.16 | 0.14 | -9.45 | -32.15 | 93 | 9443.38 | 224500.5 | 3168077.42 | 30.2305 | -96.6341 | 271.47
10019 | 0.96 | 304.32 | 9925.37 | 22.99 | -865.77 | -423.86 | 0.62 | 0.47 | -33.67 | -59.11 | 95 | 9538.37 | 224501.33 | 3168076.59 | 30.2305 | -96.6341 | 271.52
10112 | 1.04 | 257.64 | 10018.35 | 23.25 | -867.24 | -424.77 | 0.86 | 0.09 | -50.19 | -108.04 | 93 | 9631.35 | 224501.59 | 3168075.12 | 30.2305 | -96.6341 | 271.54
10207 | 1.16 | 264.5 | 10113.34 | 22.98 | -869.04 | -425.37 | 0.19 | 0.13 | 7.22 | 51.12 | 95 | 9726.34 | 224501.32 | 3168073.32 | 30.2305 | -96.6341 | 271.51
10300 | 1.75 | 188.09 | 10206.31 | 21.48 | -870.17 | -424.57 | 2 | 0.63 | -82.16 | -113.75 | 93 | 9819.31 | 224499.82 | 3168072.19 | 30.2305 | -96.6341 | 271.41
10394 | 8.87 | 176.55 | 10299.85 | 12.81 | -869.94 | -416.8 | 7.62 | 7.57 | -12.28 | -14.32 | 94 | 9912.85 | 224491.15 | 3168072.42 | 30.2305 | -96.6341 | 270.84
10489 | 13.68 | 180.07 | 10392.99 | -5.74 | -869.51 | -400.18 | 5.11 | 5.06 | 3.71 | 9.88 | 95 | 10005.99 | 224472.6 | 3168072.85 | 30.2305 | -96.6341 | 269.62
10583 | 16.65 | 200.72 | 10483.77 | -29.48 | -874.29 | -381.41 | 6.51 | 3.16 | 21.97 | 71.44 | 94 | 10096.77 | 224448.86 | 3168068.07 | 30.2304 | -96.6341 | 268.07
10677 | 20.55 | 198.52 | 10572.85 | -57.73 | -884.3 | -361.08 | 4.21 | 4.15 | -2.34 | -11.25 | 94 | 10185.85 | 224420.61 | 3168058.06 | 30.2303 | -96.6342 | 266.27
10772 | 21.39 | 193.16 | 10661.56 | -90.41 | -893.54 | -336.47 | 2.2 | 0.88 | -5.64 | -68.87 | 95 | 10274.56 | 224387.93 | 3168048.82 | 30.2302 | -96.6342 | 264.22
10873 | 27.54 | 191.21 | 10753.45 | -131.29 | -902.29 | -304.38 | 6.14 | 6.09 | -1.93 | -8.37 | 101 | 10366.45 | 224347.05 | 3168040.07 | 30.2301 | -96.6342 | 261.72
10971 | 34.37 | 187.7 | 10837.45 | -180.99 | -910.41 | -264.19 | 7.21 | 6.97 | -3.58 | -16.33 | 98 | 10450.45 | 224297.35 | 3168031.95 | 30.23 | -96.6342 | 258.76
11065 | 46.48 | 171.82 | 10909.07 | -241.4 | -909.1 | -210.14 | 16.83 | 12.88 | -16.89 | -46.7 | 94 | 10522.07 | 224236.94 | 3168033.26 | 30.2298 | -96.6342 | 255.13
11160 | 52.12 | 158.41 | 10971.15 | -310.59 | -890.34 | -140.18 | 12.22 | 5.94 | -14.12 | -65.49 | 95 | 10584.15 | 224167.75 | 3168052.02 | 30.2296 | -96.6342 | 250.77
11255 | 58.27 | 149.11 | 11025.43 | -380.29 | -855.72 | -62.37 | 10.31 | 6.47 | -9.79 | -53.89 | 95 | 10638.43 | 224098.05 | 3168086.64 | 30.2294 | -96.6341 | 246.04
11350 | 59.92 | 149.47 | 11074.22 | -450.37 | -814.1 | 19.03 | 1.77 | 1.74 | 0.38 | 10.7 | 95 | 10687.22 | 224027.97 | 3168128.26 | 30.2292 | -96.634 | 241.05
11444 | 63.22 | 147.37 | 11118.97 | -520.77 | -770.8 | 101.49 | 4.02 | 3.51 | -2.23 | -29.74 | 94 | 10731.97 | 223957.57 | 3168171.56 | 30.229 | -96.6338 | 235.96
11539 | 70.52 | 142.47 | 11156.29 | -592.12 | -720.56 | 188.04 | 9.03 | 7.68 | -5.16 | -32.68 | 95 | 10769.29 | 223886.22 | 3168221.8 | 30.2288 | -96.6337 | 230.59
11633 | 78.73 | 142.05 | 11181.19 | -663.73 | -665.13 | 277.23 | 8.74 | 8.73 | -0.45 | -2.88 | 94 | 10794.19 | 223814.61 | 3168277.23 | 30.2286 | -96.6335 | 225.06
11728 | 80.94 | 142.94 | 11197.95 | -737.91 | -608.2 | 369.39 | 2.5 | 2.33 | 0.94 | 21.7 | 95 | 10810.95 | 223740.43 | 3168334.16 | 30.2284 | -96.6333 | 219.5
11823 | 84.85 | 143.15 | 11209.7 | -813.23 | -551.54 | 462.44 | 4.12 | 4.12 | 0.22 | 3.06 | 95 | 10822.7 | 223665.11 | 3168390.82 | 30.2282 | -96.6332 | 214.15
11917 | 86.62 | 144.18 | 11216.69 | -888.74 | -496 | 555.13 | 2.18 | 1.88 | 1.1 | 30.17 | 94 | 10829.69 | 223589.6 | 3168446.36 | 30.228 | -96.633 | 209.17
12012 | 84.62 | 144.11 | 11223.95 | -965.51 | -440.52 | 648.91 | 2.11 | -2.11 | -0.07 | -178 | 95 | 10836.95 | 223512.83 | 3168501.84 | 30.2278 | -96.6328 | 204.53
12107 | 84.6 | 144.15 | 11232.87 | -1042.15 | -385.1 | 742.55 | 0.05 | -0.02 | 0.04 | 116.67 | 95 | 10845.87 | 223436.19 | 3168557.26 | 30.2276 | -96.6327 | 200.28
12202 | 84.4 | 144.41 | 11241.98 | -1118.92 | -329.89 | 836.2 | 0.34 | -0.21 | 0.27 | 127.71 | 95 | 10854.98 | 223359.42 | 3168612.47 | 30.2274 | -96.6325 | 196.43
12297 | 84.13 | 144.29 | 11251.47 | -1195.73 | -274.8 | 929.84 | 0.31 | -0.28 | -0.13 | -156.15 | 95 | 10864.47 | 223282.61 | 3168667.56 | 30.2271 | -96.6323 | 192.94
12391 | 85.55 | 146.42 | 11259.92 | -1272.75 | -221.59 | 1022.78 | 2.72 | 1.51 | 2.27 | 56.3 | 94 | 10872.92 | 223205.59 | 3168720.77 | 30.2269 | -96.6322 | 189.88
12483 | 86.35 | 147.74 | 11266.42 | -1349.78 | -171.71 | 1114.18 | 1.67 | 0.87 | 1.43 | 58.77 | 92 | 10879.42 | 223128.56 | 3168770.65 | 30.2267 | -96.632 | 187.25
12578 | 86.32 | 148.26 | 11272.49 | -1430.18 | -121.48 | 1208.72 | 0.55 | -0.03 | 0.55 | 93.33 | 95 | 10885.49 | 223048.16 | 3168820.88 | 30.2265 | -96.6319 | 184.85
12672 | 86.32 | 147.71 | 11278.53 | -1509.72 | -71.74 | 1302.27 | 0.58 | 0 | -0.59 | -90.02 | 94 | 10891.53 | 222968.62 | 3168870.62 | 30.2263 | -96.6317 | 182.72
12764 | 86.45 | 149.32 | 11284.33 | -1588.01 | -23.79 | 1393.9 | 1.75 | 0.14 | 1.75 | 85.43 | 92 | 10897.33 | 222890.33 | 3168918.57 | 30.226 | -96.6316 | 180.86
12859 | 86.52 | 149.46 | 11290.15 | -1669.62 | 24.49 | 1488.6 | 0.16 | 0.07 | 0.15 | 63.4 | 95 | 10903.15 | 222808.72 | 3168966.85 | 30.2258 | -96.6314 | 179.16
12953 | 84.54 | 151.22 | 11297.48 | -1751.05 | 70.86 | 1582.26 | 2.81 | -2.11 | 1.87 | 138.52 | 94 | 10910.48 | 222727.29 | 3169013.22 | 30.2256 | -96.6313 | 177.68
13048 | 84.44 | 151.64 | 11306.6 | -1834.1 | 116.08 | 1676.81 | 0.45 | -0.11 | 0.44 | 103.47 | 95 | 10919.6 | 222644.24 | 3169058.44 | 30.2254 | -96.6312 | 176.38
13142 | 84.45 | 151.58 | 11315.7 | -1916.4 | 160.57 | 1770.36 | 0.06 | 0.01 | -0.06 | -80.5 | 94 | 10928.7 | 222561.94 | 3169102.93 | 30.2251 | -96.631 | 175.21
13237 | 85.17 | 152.63 | 11324.29 | -2000.02 | 204.83 | 1864.97 | 1.34 | 0.76 | 1.11 | 55.5 | 95 | 10937.29 | 222478.32 | 3169147.19 | 30.2249 | -96.6309 | 174.15
13332 | 85.83 | 153 | 11331.75 | -2084.26 | 248.1 | 1959.67 | 0.8 | 0.69 | 0.39 | 29.21 | 95 | 10944.75 | 222394.08 | 3169190.46 | 30.2247 | -96.6308 | 173.21
13427 | 85.54 | 153.08 | 11338.9 | -2168.7 | 291.05 | 2054.39 | 0.32 | -0.31 | 0.08 | 164.62 | 95 | 10951.9 | 222309.64 | 3169233.41 | 30.2244 | -96.6307 | 172.36
13521 | 89.34 | 152.46 | 11343.09 | -2252.18 | 334.01 | 2148.28 | 4.1 | 4.04 | -0.66 | -9.27 | 94 | 10956.09 | 222226.16 | 3169276.37 | 30.2242 | -96.6305 | 171.56
13616 | 89.02 | 151.01 | 11344.45 | -2335.84 | 378.99 | 2243.26 | 1.56 | -0.34 | -1.53 | -102.46 | 95 | 10957.45 | 222142.5 | 3169321.35 | 30.2239 | -96.6304 | 170.78
13711 | 87.67 | 150.23 | 11347.2 | -2418.59 | 425.57 | 2338.18 | 1.64 | -1.42 | -0.82 | -150 | 95 | 10960.2 | 222059.75 | 3169367.93 | 30.2237 | -96.6303 | 170.02
13805 | 88.48 | 150.2 | 11350.35 | -2500.12 | 472.24 | 2432.07 | 0.86 | 0.86 | -0.03 | -2.12 | 94 | 10963.35 | 221978.22 | 3169414.6 | 30.2235 | -96.6301 | 169.3
13899 | 86.87 | 151.22 | 11354.17 | -2582.04 | 518.19 | 2525.96 | 2.03 | -1.71 | 1.09 | 147.68 | 94 | 10967.17 | 221896.3 | 3169460.55 | 30.2233 | -96.63 | 168.65
13993 | 87.48 | 151 | 11358.8 | -2664.24 | 563.55 | 2619.82 | 0.69 | 0.65 | -0.23 | -19.82 | 94 | 10971.8 | 221814.1 | 3169505.91 | 30.223 | -96.6298 | 168.06
14086 | 86.27 | 151.36 | 11363.87 | -2745.59 | 608.31 | 2712.67 | 1.36 | -1.3 | 0.39 | 163.46 | 93 | 10976.87 | 221732.75 | 3169550.67 | 30.2228 | -96.6297 | 167.51
14181 | 86.38 | 150.68 | 11369.96 | -2828.53 | 654.25 | 2807.45 | 0.72 | 0.12 | -0.72 | -80.81 | 95 | 10982.96 | 221649.81 | 3169596.61 | 30.2226 | -96.6296 | 166.98
14275 | 86.11 | 149.93 | 11376.12 | -2910.01 | 700.71 | 2901.2 | 0.85 | -0.29 | -0.8 | -109.86 | 94 | 10989.12 | 221568.33 | 3169643.07 | 30.2223 | -96.6294 | 166.46
14370 | 86.32 | 148.83 | 11382.39 | -2991.58 | 748.99 | 2995.87 | 1.18 | 0.22 | -1.16 | -79.21 | 95 | 10995.39 | 221486.76 | 3169691.35 | 30.2221 | -96.6293 | 165.94
14466 | 86.47 | 152 | 11388.42 | -3074.89 | 796.29 | 3091.62 | 3.3 | 0.16 | 3.3 | 87.39 | 96 | 11001.42 | 221403.45 | 3169738.65 | 30.2219 | -96.6291 | 165.48
14560 | 86.66 | 151.69 | 11394.06 | -3157.62 | 840.56 | 3185.45 | 0.39 | 0.2 | -0.33 | -58.46 | 94 | 11007.06 | 221320.72 | 3169782.92 | 30.2216 | -96.629 | 165.09
14654 | 86.35 | 151.16 | 11399.79 | -3240.01 | 885.44 | 3279.27 | 0.65 | -0.33 | -0.56 | -120.39 | 94 | 11012.79 | 221238.33 | 3169827.8 | 30.2214 | -96.6289 | 164.72
14749 | 86.91 | 150.37 | 11405.37 | -3322.77 | 931.76 | 3374.07 | 1.02 | 0.59 | -0.83 | -54.65 | 95 | 11018.37 | 221155.57 | 3169874.12 | 30.2212 | -96.6287 | 164.34
14842 | 86.42 | 149.01 | 11410.78 | -3402.92 | 978.61 | 3466.82 | 1.55 | -0.53 | -1.46 | -109.88 | 93 | 11023.78 | 221075.42 | 3169920.97 | 30.221 | -96.6286 | 163.96
14936 | 86.86 | 150.53 | 11416.29 | -3483.99 | 1025.86 | 3560.57 | 1.68 | 0.47 | 1.62 | 73.87 | 94 | 11029.29 | 220994.35 | 3169968.22 | 30.2207 | -96.6285 | 163.59
15031 | 85.39 | 154.29 | 11422.71 | -3567.98 | 1069.75 | 3655.33 | 4.24 | -1.55 | 3.96 | 111.52 | 95 | 11035.71 | 220910.36 | 3170012.11 | 30.2205 | -96.6283 | 163.31
15125 | 85.42 | 154.63 | 11430.24 | -3652.52 | 1110.14 | 3748.96 | 0.36 | 0.03 | 0.36 | 84.96 | 94 | 11043.24 | 220825.82 | 3170052.5 | 30.2203 | -96.6282 | 163.09
15220 | 87.47 | 154.37 | 11436.14 | -3738.1 | 1150.96 | 3843.7 | 2.18 | 2.16 | -0.27 | -7.22 | 95 | 11049.14 | 220740.24 | 3170093.32 | 30.22 | -96.6281 | 162.89
15315 | 87.37 | 154.46 | 11440.41 | -3823.69 | 1191.95 | 3938.53 | 0.14 | -0.11 | 0.09 | 138.04 | 95 | 11053.41 | 220654.65 | 3170134.31 | 30.2198 | -96.628 | 162.69
15410 | 84.62 | 152.31 | 11447.05 | -3908.41 | 1234.39 | 4033.26 | 3.67 | -2.89 | -2.26 | -142.12 | 95 | 11060.05 | 220569.93 | 3170176.75 | 30.2195 | -96.6279 | 162.47
15505 | 84.63 | 152.35 | 11455.95 | -3992.17 | 1278.31 | 4127.85 | 0.04 | 0.01 | 0.04 | 75.91 | 95 | 11068.95 | 220486.17 | 3170220.67 | 30.2193 | -96.6277 | 162.24
15599 | 85.28 | 151.78 | 11464.21 | -4074.9 | 1322.18 | 4221.48 | 0.92 | 0.69 | -0.61 | -41.16 | 94 | 11077.21 | 220403.44 | 3170264.54 | 30.2191 | -96.6276 | 162.02
15693 | 86.07 | 151.72 | 11471.3 | -4157.47 | 1366.54 | 4315.21 | 0.84 | 0.84 | -0.06 | -4.33 | 94 | 11084.3 | 220320.87 | 3170308.9 | 30.2189 | -96.6275 | 161.8
15788 | 87.6 | 151.72 | 11476.55 | -4241 | 1411.48 | 4410.06 | 1.61 | 1.61 | 0 | 0 | 95 | 11089.55 | 220237.34 | 3170353.84 | 30.2186 | -96.6273 | 161.59
15881 | 86.43 | 151.3 | 11481.39 | -4322.62 | 1455.78 | 4502.92 | 1.34 | -1.26 | -0.45 | -160.29 | 93 | 11094.39 | 220155.72 | 3170398.14 | 30.2184 | -96.6272 | 161.39
15976 | 86.51 | 151.15 | 11487.24 | -4405.73 | 1501.43 | 4597.73 | 0.18 | 0.08 | -0.16 | -61.89 | 95 | 11100.24 | 220072.61 | 3170443.79 | 30.2182 | -96.6271 | 161.18
16070 | 84.24 | 150.69 | 11494.82 | -4487.61 | 1546.96 | 4691.39 | 2.46 | -2.41 | -0.49 | -168.6 | 94 | 11107.82 | 219990.73 | 3170489.32 | 30.2179 | -96.6269 | 160.98
16165 | 84.66 | 153.88 | 11504.01 | -4571.31 | 1590.93 | 4785.93 | 3.37 | 0.44 | 3.36 | 82.62 | 95 | 11117.01 | 219907.03 | 3170533.29 | 30.2177 | -96.6268 | 160.81
16260 | 84.63 | 154.41 | 11512.87 | -4656.42 | 1632.18 | 4880.46 | 0.56 | -0.03 | 0.56 | 93.28 | 95 | 11125.87 | 219821.92 | 3170574.54 | 30.2175 | -96.6267 | 160.68
16355 | 86.67 | 155.9 | 11520.08 | -4742.38 | 1671.97 | 4975.06 | 2.66 | 2.15 | 1.57 | 36.12 | 95 | 11133.08 | 219735.96 | 3170614.33 | 30.2172 | -96.6266 | 160.58
16448 | 88.64 | 155.92 | 11523.88 | -4827.2 | 1709.9 | 5067.78 | 2.12 | 2.12 | 0.02 | 0.58 | 93 | 11136.88 | 219651.14 | 3170652.26 | 30.217 | -96.6264 | 160.49
16542 | 86.17 | 154.58 | 11528.14 | -4912.47 | 1749.21 | 5161.55 | 2.99 | -2.63 | -1.43 | -151.57 | 94 | 11141.14 | 219565.87 | 3170691.57 | 30.2167 | -96.6263 | 160.4
16635 | 86.65 | 154.39 | 11533.96 | -4996.24 | 1789.19 | 5254.29 | 0.55 | 0.52 | -0.2 | -21.56 | 93 | 11146.96 | 219482.1 | 3170731.55 | 30.2165 | -96.6262 | 160.3
16729 | 87.35 | 154.12 | 11538.88 | -5080.79 | 1829.96 | 5348.1 | 0.8 | 0.74 | -0.29 | -21.07 | 94 | 11151.88 | 219397.55 | 3170772.32 | 30.2163 | -96.6261 | 160.19
16824 | 88.15 | 153.99 | 11542.61 | -5166.15 | 1871.49 | 5442.98 | 0.85 | 0.84 | -0.14 | -9.23 | 95 | 11155.61 | 219312.19 | 3170813.85 | 30.216 | -96.626 | 160.09
16919 | 86.59 | 152.77 | 11546.97 | -5250.98 | 1914.01 | 5537.86 | 2.08 | -1.64 | -1.28 | -142.03 | 95 | 11159.97 | 219227.36 | 3170856.37 | 30.2158 | -96.6258 | 159.97
17014 | 87.42 | 152.17 | 11551.94 | -5335.11 | 1957.86 | 5632.72 | 1.08 | 0.87 | -0.63 | -35.84 | 95 | 11164.94 | 219143.23 | 3170900.22 | 30.2156 | -96.6257 | 159.85
17107 | 86.63 | 152.05 | 11556.76 | -5417.2 | 2001.31 | 5725.6 | 0.86 | -0.85 | -0.13 | -171.38 | 93 | 11169.76 | 219061.14 | 3170943.67 | 30.2153 | -96.6256 | 159.72
17203 | 87.35 | 152.4 | 11561.8 | -5502.02 | 2045.98 | 5821.46 | 0.83 | 0.75 | 0.36 | 25.9 | 96 | 11174.8 | 218976.32 | 3170988.34 | 30.2151 | -96.6255 | 159.6
17298 | 86.99 | 152.06 | 11566.49 | -5585.98 | 2090.19 | 5916.35 | 0.52 | -0.38 | -0.36 | -136.68 | 95 | 11179.49 | 218892.36 | 3171032.55 | 30.2149 | -96.6253 | 159.48
17392 | 86.73 | 151.45 | 11571.64 | -5668.66 | 2134.61 | 6010.2 | 0.7 | -0.28 | -0.65 | -113.13 | 94 | 11184.64 | 218809.68 | 3171076.97 | 30.2146 | -96.6252 | 159.37
17487 | 86.91 | 150.9 | 11576.91 | -5751.76 | 2180.34 | 6105.04 | 0.61 | 0.19 | -0.58 | -71.87 | 95 | 11189.91 | 218726.58 | 3171122.7 | 30.2144 | -96.6251 | 159.24
17582 | 85.04 | 152.93 | 11583.58 | -5835.36 | 2224.95 | 6199.8 | 2.9 | -1.97 | 2.14 | 132.79 | 95 | 11196.58 | 218642.98 | 3171167.31 | 30.2142 | -96.6249 | 159.13
17676 | 83.87 | 152.5 | 11592.66 | -5918.51 | 2267.84 | 6293.35 | 1.33 | -1.24 | -0.46 | -159.93 | 94 | 11205.66 | 218559.83 | 3171210.2 | 30.2139 | -96.6248 | 159.03
17771 | 84.76 | 154.33 | 11602.07 | -6003.04 | 2310.14 | 6387.86 | 2.13 | 0.94 | 1.93 | 64.05 | 95 | 11215.07 | 218475.3 | 3171252.5 | 30.2137 | -96.6247 | 158.95
17866 | 86.96 | 155.09 | 11608.93 | -6088.7 | 2350.62 | 6482.51 | 2.45 | 2.32 | 0.8 | 19.04 | 95 | 11221.93 | 218389.64 | 3171292.98 | 30.2135 | -96.6245 | 158.89
17961 | 86.49 | 154.59 | 11614.36 | -6174.55 | 2390.94 | 6577.26 | 0.72 | -0.49 | -0.53 | -133.29 | 95 | 11227.36 | 218303.79 | 3171333.3 | 30.2132 | -96.6244 | 158.83
18055 | 86.54 | 154.81 | 11620.07 | -6259.38 | 2431.04 | 6671 | 0.24 | 0.05 | 0.23 | 77.18 | 94 | 11233.07 | 218218.96 | 3171373.4 | 30.213 | -96.6243 | 158.77
18151 | 86.73 | 155.59 | 11625.71 | -6346.37 | 2471.23 | 6766.7 | 0.83 | 0.2 | 0.81 | 76.31 | 96 | 11238.71 | 218131.97 | 3171413.59 | 30.2127 | -96.6242 | 158.72
18246 | 86.42 | 153.74 | 11631.39 | -6432.08 | 2511.81 | 6861.44 | 1.97 | -0.33 | -1.95 | -99.58 | 95 | 11244.39 | 218046.26 | 3171454.17 | 30.2125 | -96.6241 | 158.67
18340 | 86.75 | 155.13 | 11636.98 | -6516.72 | 2552.3 | 6955.2 | 1.52 | 0.35 | 1.48 | 76.66 | 94 | 11249.98 | 217961.62 | 3171494.66 | 30.2123 | -96.624 | 158.61
18435 | 86.91 | 150.49 | 11642.24 | -6601.07 | 2595.63 | 7050.02 | 4.88 | 0.17 | -4.88 | -88.15 | 95 | 11255.24 | 217877.27 | 3171537.99 | 30.212 | -96.6238 | 158.53
18529 | 87.06 | 146.36 | 11647.19 | -6681.03 | 2644.77 | 7143.67 | 4.39 | 0.16 | -4.39 | -88.03 | 94 | 11260.19 | 217797.31 | 3171587.13 | 30.2118 | -96.6237 | 158.4
18622 | 86.64 | 144.35 | 11652.3 | -6757.42 | 2697.56 | 7235.86 | 2.2 | -0.45 | -2.16 | -101.87 | 93 | 11265.3 | 217720.92 | 3171639.92 | 30.2116 | -96.6235 | 158.24
18718 | 85.54 | 146.87 | 11658.85 | -6836.45 | 2751.65 | 7330.99 | 2.86 | -1.15 | 2.62 | 113.71 | 96 | 11271.85 | 217641.89 | 3171694.01 | 30.2114 | -96.6234 | 158.08
18810 | 85.84 | 151.34 | 11665.76 | -6915.15 | 2798.75 | 7422.57 | 4.86 | 0.33 | 4.86 | 86.32 | 92 | 11278.76 | 217563.19 | 3171741.11 | 30.2111 | -96.6232 | 157.97
18904 | 86.26 | 155.74 | 11672.24 | -6999.08 | 2840.52 | 7516.3 | 4.69 | 0.45 | 4.68 | 84.69 | 94 | 11285.24 | 217479.26 | 3171782.88 | 30.2109 | -96.6231 | 157.91
18998 | 87.74 | 157.79 | 11677.16 | -7085.33 | 2877.55 | 7609.86 | 2.69 | 1.57 | 2.18 | 54.19 | 94 | 11290.16 | 217393.01 | 3171819.91 | 30.2107 | -96.623 | 157.9
19093 | 89.38 | 150.69 | 11679.55 | -7170.81 | 2918.8 | 7704.71 | 7.67 | 1.73 | -7.47 | -77.1 | 95 | 11292.55 | 217307.53 | 3171861.16 | 30.2104 | -96.6229 | 157.85
19188 | 88.94 | 143.77 | 11680.95 | -7250.63 | 2970.18 | 7799.28 | 7.3 | -0.46 | -7.28 | -93.68 | 95 | 11293.95 | 217227.71 | 3171912.54 | 30.2102 | -96.6227 | 157.72
19283 | 90.12 | 142.71 | 11681.73 | -7326.73 | 3027.03 | 7893.11 | 1.67 | 1.24 | -1.12 | -41.94 | 95 | 11294.73 | 217151.61 | 3171969.39 | 30.21 | -96.6225 | 157.55
19323 | 90.95 | 140.73 | 11681.35 | -7358.13 | 3051.81 | 7932.44 | 5.37 | 2.08 | -4.95 | -67.25 | 40 | 11294.35 | 217120.21 | 3171994.17 | 30.2099 | -96.6225 | 157.47
19389 | 90.95 | 140.73 | 11680.26 | -7409.22 | 3093.58 | 7997.11 | 0 | 0 | 0 | 0 | 66 | 11293.26 | 217069.12 | 3172035.94 | 30.2098 | -96.6223 | 157.34

## 7_17_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/17/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 15630 |  |  | Well Cost($): |  | 15630
|  |  |  | 24hr Summary: |  | M/U BHA #1, Drill surface
|  |  |  | 24hr Lookahead: |  | Drill Surface, Run casing, N/U BOPE
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 7 | PV: | 2
End Depth (Usft): |  | 2975 |  | 2975 |  | OD (in): |  | 20 |  | 300: | 5 | YP: | 3
Total Drilled (Usft): |  | 2867 |  | 2867 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): |  | 315 |  | 315 | [5 empty] | 100: | 2 | Chlorides: | 400
Rotary Drilled (Usft): |  | 2552 |  | 2552 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.40 / 5.60
Drlg/Circ Hrs: |  | 5.58 / 2.42 |  | 5.58 / 2.42 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0/100
Slide Drilling Hrs: |  | 1.4 |  | 1.4 |  | SN: |  | 47424 |  | 10s Gel: | 1 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 4.18 |  | 4.18 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.4 / 120.00 | Fluid Loss / Mud Type: | 10 / WBM
ROP Rot/Slide (Usft/hr): |  | 610.04 / 225.00 |  | 610.04 / 225.00 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 8 |  | 8 |  | Grade In: |  | 0-0-
% Slide: |  | 10.99 |  | 10.99 |  | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
% Rotary: |  | 89.01 |  | 89.01 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | BillTrey |  | NA
Kevin |  | Josh Ray |  | Jason Smitters | [7 empty] | NA
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7/8 5.9 1.50 Stab HPO -.011 NBS 13 |  |  |  | 8 | [5 empty] | 37.43 |  | 38.93
13 Stab |  |  |  | 8.125 | 3 |  |  |  |  | 6.34 |  | 45.27
NMPC |  |  |  | 8 | 3.25 |  |  |  |  | 8.58 |  | 53.85
UBHO Sub UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.66 |  | 57.51
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.83 |  | 86.34
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.99 |  | 115.33
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.13 |  | 117.46
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 274.62 |  | 392.08
392.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800017 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.8 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
198 | 0.04 | 359.23 | 198 | 0.07 | 0 | 0.02 |  | 359.23 | -0.06 | 0.02 |  | 0 | 198
289 | 0.04 | 292.44 | 289 | 0.11 | -0.03 | 0.05 |  | -123.39 | -0.11 | 0 |  | 0 | 91
382 | 0.26 | 240.76 | 382 | 0.02 | -0.24 | 0.26 |  | -59.28 | -0.13 | 0.24 |  | 0 | 93
507 | 0.35 | 252.71 | 507 | -0.23 | -0.86 | 0.09 |  | 41.33 | -0.2 | 0.07 |  | 0 | 125
601 | 0.26 | 244.98 | 601 | -0.41 | -1.32 | 0.11 |  | -159.26 | -0.26 | -0.1 |  | 0 | 94
695 | 0.26 | 250.43 | 695 | -0.57 | -1.72 | 0.03 |  | 92.72 | -0.3 | 0 |  | 0 | 94
789 | 0.35 | 261.06 | 788.99 | -0.68 | -2.2 | 0.11 |  | 37.55 | -0.42 | 0.1 |  | 0 | 94
883 | 0.35 | 299.73 | 882.99 | -0.59 | -2.74 | 0.25 |  | 109.33 | -0.76 | 0 |  | 0 | 94
977 | 1.01 | 279.34 | 976.99 | -0.31 | -3.8 | 0.74 |  | -30.53 | -1.5 | 0.7 |  | 0 | 94
1071 | 1.93 | 270.38 | 1070.95 | -0.16 | -6.2 | 1.01 |  | -18.53 | -2.75 | 0.98 |  | 0 | 94
1166 | 3.12 | 278.99 | 1165.86 | 0.25 | -10.36 | 1.31 |  | 22.01 | -5.05 | 1.25 |  | 9.06 | 95
1259 | 3.34 | 283.47 | 1258.71 | 1.28 | -15.49 | 0.36 |  | 51.18 | -8.35 | 0.24 |  | 4.82 | 93
1353 | 3.74 | 285.05 | 1352.53 | 2.71 | -21.11 | 0.44 |  | 14.5 | -12.24 | 0.43 |  | 1.68 | 94
1447 | 4.48 | 286.64 | 1446.29 | 4.56 | -27.59 | 0.8 |  | 9.55 | -16.89 | 0.79 |  | 1.69 | 94
1542 | 5.76 | 281.36 | 1540.91 | 6.56 | -35.82 | 1.43 |  | -22.85 | -22.5 | 1.35 |  | -5.56 | 95
1635 | 6.42 | 274.42 | 1633.39 | 7.88 | -45.58 | 1.06 |  | -51.61 | -28.22 | 0.71 |  | -7.46 | 93
1729 | 7.08 | 270.38 | 1726.73 | 8.32 | -56.61 | 0.86 |  | -37.75 | -33.75 | 0.7 |  | -4.3 | 94
1822 | 7.69 | 269.76 | 1818.96 | 8.34 | -68.57 | 0.66 |  | -7.75 | -39.33 | 0.66 |  | -0.67 | 93
1916 | 8.83 | 267.74 | 1911.99 | 8.03 | -82.07 | 1.25 |  | -15.28 | -45.35 | 1.21 |  | -2.15 | 94
2011 | 9.62 | 270.03 | 2005.76 | 7.74 | -97.29 | 0.92 |  | 26.06 | -52.19 | 0.83 |  | 2.41 | 95
2106 | 9.98 | 268.62 | 2099.37 | 7.55 | -113.46 | 0.46 |  | -34.39 | -59.56 | 0.38 |  | -1.48 | 95
2200 | 10.63 | 267.56 | 2191.85 | 6.98 | -130.26 | 0.72 |  | -16.79 | -66.89 | 0.69 |  | -1.13 | 94
2293 | 11.47 | 270.11 | 2283.13 | 6.63 | -148.08 | 1.04 |  | 31.45 | -74.89 | 0.9 |  | 2.74 | 93
2387 | 12.57 | 271.52 | 2375.07 | 6.92 | -167.65 | 1.21 |  | 15.64 | -84.27 | 1.17 |  | 1.5 | 94
2481 | 13.67 | 271.96 | 2466.61 | 7.58 | -188.98 | 1.18 |  | 5.4 | -94.78 | 1.17 |  | 0.47 | 94
2575 | 13.89 | 268.27 | 2557.91 | 7.61 | -211.36 | 0.96 |  | -77.74 | -105.25 | 0.23 |  | -3.93 | 94
2669 | 13.93 | 265.98 | 2649.15 | 6.48 | -233.92 | 0.59 |  | -86.96 | -114.76 | 0.04 |  | -2.44 | 94
2763 | 13.4 | 265.37 | 2740.49 | 4.81 | -256.07 | 0.58 |  | -165.08 | -123.6 | -0.56 |  | -0.65 | 94
2857 | 13.45 | 265.19 | 2831.92 | 3.01 | -277.82 | 0.07 |  | -39.98 | -132.15 | 0.05 |  | -0.19 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 513.49 | 14.99 | 97 | 241 | 868.88 | 1914.47 | 1581.29 | 182 | 92.24 | 87.24 | 83.65 | 8091 | 3
Run | 513.49 | 14.99 | 97 | 241 | 868.88 | 1914.47 | 1581.29 | 182 | 92.24 | 87.24 | 83.65 | 8091 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/17/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/17/2021 |  | 5 |  | 100 |  | 4 | 400
13 Stab Rental (Used) |  |  |  |  | 07/17/2021 |  | 7 |  | 1150 |  | 1 | 1150
13 Stab Rental (Not Used) |  |  |  |  | 07/17/2021 |  | 8 |  | 230 |  | 1 | 230
Mileage |  |  |  |  | 07/17/2021 |  | 16 |  | 2 |  | 700 | 1400
Multi Rig Discount |  |  |  |  | 07/17/2021 |  | 20 |  | -400 |  | 1 | -400
Mob/DeMob |  |  |  |  | 07/17/2021 |  | 1 |  | 6000 |  | 1 | 6000
Total | [11 empty] | 15630
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/17/2021 | 00:00 | 14:30 | 14.5 | 108 | 108 | 0 | SUR |  | 24B | STBY
07/17/2021 | 14:30 | 16:00 | 1.5 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | P/U BHA
07/17/2021 | 16:00 | 16:35 | 0.58 | 108 | 270 | 162 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/270.00, w/WOB 3.00,Flow 600.00, RPM 60.00, Press 650.00, Tq 1500.00, ROP 277.71
07/17/2021 | 16:35 | 16:40 | 0.08 | 270 | 270 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 16:40 | 16:48 | 0.13 | 270 | 361 | 91 | SUR | 1: BHA 1 | 2K | Rotary Drill f/270.00 t/361.00, w/WOB 5.00,Flow 700.00, RPM 70.00, Press 900.00, Tq 1500.00, ROP 682.50
07/17/2021 | 16:48 | 16:53 | 0.08 | 361 | 361 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 16:53 | 17:01 | 0.13 | 361 | 454 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/361.00 t/454.00, w/WOB 5.00,Flow 800.00, RPM 80.00, Press 1200.00, Tq 2500.00, ROP 697.50
07/17/2021 | 17:01 | 17:05 | 0.07 | 454 | 454 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 17:05 | 17:23 | 0.3 | 454 | 579 | 125 | SUR | 1: BHA 1 | 2K | Rotary Drill f/454.00 t/579.00, w/WOB 5.00,Flow 900.00, RPM 100.00, Press 1500.00, Tq 2500.00, ROP 416.67
07/17/2021 | 17:23 | 17:27 | 0.07 | 579 | 579 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 17:27 | 17:35 | 0.13 | 579 | 673 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/579.00 t/673.00, w/WOB 8.00,Flow 900.00, RPM 100.00, Press 1500.00, Tq 2500.00, ROP 705.00
07/17/2021 | 17:35 | 17:39 | 0.07 | 673 | 673 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 17:39 | 17:45 | 0.1 | 673 | 767 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/673.00 t/767.00, w/WOB 5.00,Flow 900.00, RPM 100.00, Press 1500.00, Tq 2500.00, ROP 940.00
07/17/2021 | 17:45 | 17:50 | 0.08 | 767 | 767 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 17:50 | 17:54 | 0.07 | 767 | 861 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/767.00 t/861.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 10229.00, ROP 1410.00
07/17/2021 | 17:54 | 17:59 | 0.08 | 861 | 861 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 17:59 | 18:05 | 0.1 | 861 | 955 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/861.00 t/955.00, w/WOB 15.20,Flow 900.00, RPM 100.00, Press 1800.00, Tq 5746.00, ROP 940.00
07/17/2021 | 18:05 | 18:10 | 0.08 | 955 | 955 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 18:10 | 18:13 | 0.05 | 955 | 970 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/955.00 t/970.00, TF 270.00, w/WOB 5.00,Flow 900.00, Press 1700.00, Tq 0.00, ROP 300.00
07/17/2021 | 18:13 | 18:19 | 0.1 | 970 | 1049 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/970.00 t/1049.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 1900.00, Tq 7230.00, ROP 790.00
07/17/2021 | 18:19 | 18:24 | 0.08 | 1049 | 1049 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 18:24 | 18:27 | 0.05 | 1049 | 1064 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1049.00 t/1064.00, TF 260.00, w/WOB 5.00,Flow 900.00, Press 1700.00, Tq 0.00, ROP 300.00
07/17/2021 | 18:27 | 18:33 | 0.1 | 1064 | 1143 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1064.00 t/1143.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 9736.00, ROP 790.00
07/17/2021 | 18:33 | 18:38 | 0.08 | 1143 | 1143 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 18:38 | 18:41 | 0.05 | 1143 | 1157 | 14 | SUR | 1: BHA 1 | 2J | Slide Drill f/1143.00 t/1157.00, TF 260.00, w/WOB 5.00,Flow 900.00, Press 1700.00, Tq 0.00, ROP 280.00
07/17/2021 | 18:41 | 18:47 | 0.1 | 1157 | 1238 | 81 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1157.00 t/1238.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 2041.00, Tq 6515.00, ROP 810.00
07/17/2021 | 18:47 | 18:51 | 0.07 | 1238 | 1238 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 18:51 | 18:57 | 0.1 | 1238 | 1331 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1238.00 t/1331.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 2064.00, Tq 6233.00, ROP 930.00
07/17/2021 | 18:57 | 19:02 | 0.08 | 1331 | 1331 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 19:02 | 19:05 | 0.05 | 1331 | 1343 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/1331.00 t/1343.00, TF -20.00, w/WOB 10.00,Flow 900.00, Press 1733.00, Tq 0.00, ROP 240.00
07/17/2021 | 19:05 | 19:11 | 0.1 | 1343 | 1425 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1343.00 t/1425.00, w/WOB 21.40,Flow 900.00, RPM 100.00, Press 2104.00, Tq 9004.00, ROP 820.00
07/17/2021 | 19:11 | 19:16 | 0.08 | 1425 | 1425 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 19:16 | 19:19 | 0.05 | 1425 | 1440 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1425.00 t/1440.00, TF -40.00, w/WOB 5.00,Flow 900.00, Press 1600.00, Tq 0.00, ROP 300.00
07/17/2021 | 19:19 | 19:25 | 0.1 | 1440 | 1519 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1440.00 t/1519.00, w/WOB 22.00,Flow 900.00, RPM 100.00, Press 2098.00, Tq 8435.00, ROP 790.00
07/17/2021 | 19:25 | 19:30 | 0.08 | 1519 | 1519 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 19:30 | 19:34 | 0.07 | 1519 | 1539 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1519.00 t/1539.00, TF -60.00, w/WOB 10.00,Flow 900.00, Press 1788.00, Tq 0.00, ROP 300.00
07/17/2021 | 19:34 | 19:40 | 0.1 | 1539 | 1614 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1539.00 t/1614.00, w/WOB 23.90,Flow 900.00, RPM 100.00, Press 2104.00, Tq 8097.00, ROP 750.00
07/17/2021 | 19:40 | 19:45 | 0.08 | 1614 | 1614 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 19:45 | 19:49 | 0.07 | 1614 | 1629 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1614.00 t/1629.00, TF -60.00, w/WOB 4.00,Flow 900.00, Press 1798.00, Tq 0.00, ROP 225.00
07/17/2021 | 19:49 | 19:55 | 0.1 | 1629 | 1707 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1629.00 t/1707.00, w/WOB 27.40,Flow 900.00, RPM 100.00, Press 2186.00, Tq 9448.00, ROP 780.00
07/17/2021 | 19:55 | 20:00 | 0.08 | 1707 | 1707 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 20:00 | 20:04 | 0.07 | 1707 | 1719 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/1707.00 t/1719.00, TF -30.00, w/WOB 8.00,Flow 715.00, Press 1220.00, Tq 0.00, ROP 180.00
07/17/2021 | 20:04 | 20:16 | 0.2 | 1719 | 1801 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1719.00 t/1801.00, w/WOB 13.20,Flow 715.00, RPM 100.00, Press 1419.00, Tq 5008.00, ROP 410.00
07/17/2021 | 20:16 | 20:21 | 0.08 | 1801 | 1801 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 20:21 | 20:25 | 0.07 | 1801 | 1816 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1801.00 t/1816.00, TF -20.00, w/WOB 11.00,Flow 715.00, Press 1290.00, Tq 0.00, ROP 225.00
07/17/2021 | 20:25 | 20:37 | 0.2 | 1816 | 1894 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1816.00 t/1894.00, w/WOB 13.90,Flow 715.00, RPM 100.00, Press 1517.00, Tq 4327.00, ROP 390.00
07/17/2021 | 20:37 | 20:43 | 0.1 | 1894 | 1894 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 20:43 | 20:49 | 0.1 | 1894 | 1914 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1894.00 t/1914.00, TF -20.00, w/WOB 5.20,Flow 715.00, Press 1341.00, Tq 0.00, ROP 200.00
07/17/2021 | 20:49 | 20:59 | 0.17 | 1914 | 1988 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1914.00 t/1988.00, w/WOB 13.90,Flow 900.00, RPM 100.00, Press 2319.00, Tq 8753.00, ROP 444.00
07/17/2021 | 20:59 | 21:05 | 0.1 | 1988 | 1988 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 21:05 | 21:09 | 0.07 | 1988 | 2003 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1988.00 t/2003.00, TF 0.00, w/WOB 7.40,Flow 900.00, Press 1921.00, Tq 0.00, ROP 225.00
07/17/2021 | 21:09 | 21:16 | 0.12 | 2003 | 2083 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2003.00 t/2083.00, w/WOB 30.60,Flow 900.00, RPM 100.00, Press 2340.00, Tq 11079.00, ROP 685.71
07/17/2021 | 21:16 | 21:21 | 0.08 | 2083 | 2083 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 21:21 | 21:25 | 0.07 | 2083 | 2098 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2083.00 t/2098.00, TF -20.00, w/WOB 14.60,Flow 900.00, Press 2049.00, Tq 0.00, ROP 225.00
07/17/2021 | 21:25 | 21:33 | 0.13 | 2098 | 2178 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2098.00 t/2178.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2355.00, Tq 9129.00, ROP 600.00
07/17/2021 | 21:33 | 21:38 | 0.08 | 2178 | 2178 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 21:38 | 21:44 | 0.1 | 2178 | 2198 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2178.00 t/2198.00, TF -10.00, w/WOB 12.10,Flow 900.00, Press 2091.00, Tq 0.00, ROP 200.00
07/17/2021 | 21:44 | 21:53 | 0.15 | 2198 | 2272 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2198.00 t/2272.00, w/WOB 29.30,Flow 900.00, RPM 100.00, Press 2381.00, Tq 9416.00, ROP 493.33
07/17/2021 | 21:53 | 21:58 | 0.08 | 2272 | 2272 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 21:58 | 22:04 | 0.1 | 2272 | 2292 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2272.00 t/2292.00, TF 0.00, w/WOB 11.60,Flow 900.00, Press 2059.00, Tq 0.00, ROP 200.00
07/17/2021 | 22:04 | 22:11 | 0.12 | 2292 | 2365 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2292.00 t/2365.00, w/WOB 17.50,Flow 900.00, RPM 100.00, Press 2232.00, Tq 7784.00, ROP 625.71
07/17/2021 | 22:11 | 22:16 | 0.08 | 2365 | 2365 | 0 | SUR | 1: BHA 1 | 5A | Circulate out gumbo
07/17/2021 | 22:16 | 22:21 | 0.08 | 2365 | 2365 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 22:21 | 22:28 | 0.12 | 2365 | 2385 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2365.00 t/2385.00, TF -20.00, w/WOB 12.50,Flow 900.00, Press 2087.00, Tq 0.00, ROP 171.43
07/17/2021 | 22:28 | 22:33 | 0.08 | 2385 | 2459 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2385.00 t/2459.00, w/WOB 32.30,Flow 900.00, RPM 100.00, Press 2469.00, Tq 15011.00, ROP 888.00
07/17/2021 | 22:33 | 22:37 | 0.07 | 2459 | 2459 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 22:37 | 22:42 | 0.08 | 2459 | 2479 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2459.00 t/2479.00, TF -20.00, w/WOB 6.80,Flow 900.00, Press 1995.00, Tq 0.00, ROP 240.00
07/17/2021 | 22:42 | 22:47 | 0.08 | 2479 | 2553 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2479.00 t/2553.00, w/WOB 23.00,Flow 900.00, RPM 100.00, Press 2276.00, Tq 17763.00, ROP 888.00
07/17/2021 | 22:47 | 22:52 | 0.08 | 2553 | 2553 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 22:52 | 22:56 | 0.07 | 2553 | 2565 | 12 | SUR | 1: BHA 1 | 2J | Slide Drill f/2553.00 t/2565.00, TF -60.00, w/WOB 5.00,Flow 900.00, Press 1950.00, Tq 0.00, ROP 180.00
07/17/2021 | 22:56 | 23:03 | 0.12 | 2565 | 2647 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2565.00 t/2647.00, w/WOB 23.60,Flow 900.00, RPM 100.00, Press 2327.00, Tq 8879.00, ROP 702.86
07/17/2021 | 23:03 | 23:08 | 0.08 | 2647 | 2647 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 23:08 | 23:15 | 0.12 | 2647 | 2741 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2647.00 t/2741.00, w/WOB 34.50,Flow 900.00, RPM 100.00, Press 2409.00, Tq 13768.00, ROP 805.71
07/17/2021 | 23:15 | 23:19 | 0.07 | 2741 | 2741 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 23:19 | 23:26 | 0.12 | 2741 | 2835 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2741.00 t/2835.00, w/WOB 31.80,Flow 900.00, RPM 100.00, Press 2579.00, Tq 11961.00, ROP 805.71
07/17/2021 | 23:26 | 23:30 | 0.07 | 2835 | 2835 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 23:30 | 23:35 | 0.08 | 2835 | 2855 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2835.00 t/2855.00, TF 20.00, w/WOB 11.10,Flow 900.00, Press 2179.00, Tq 0.00, ROP 240.00
07/17/2021 | 23:35 | 23:45 | 0.17 | 2855 | 2929 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2855.00 t/2929.00, w/WOB 33.70,Flow 900.00, RPM 100.00, Press 2660.00, Tq 13080.00, ROP 444.00
07/17/2021 | 23:45 | 23:50 | 0.08 | 2929 | 2929 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/17/2021 | 23:50 | 23:56 | 0.1 | 2929 | 2949 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2929.00 t/2949.00, TF 30.00, w/WOB 12.80,Flow 900.00, Press 2288.00, Tq 0.00, ROP 200.00
07/17/2021 | 23:56 | 24:00 | 0.07 | 2949 | 2975 | 26 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2949.00 t/2975.00, w/WOB 18.40,Flow 900.00, RPM 100.00, Press 2490.00, Tq 13099.00, ROP 390.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_18_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/18/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 22480
|  |  |  | 24hr Summary: |  | Drill Surface, Circ, POOH, L/D BHA #1, Run casing, N/U BOPE
|  |  |  | 24hr Lookahead: |  | N/U BOPE, Test, Drill Int.
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2975 |  | 108 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 7 | PV: | 2
End Depth (Usft): |  | 3492 |  | 3492 |  | OD (in): |  | 10.75 |  | 300: | 5 | YP: | 3
Total Drilled (Usft): |  | 517 |  | 3384 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): |  | 48 |  | 363 | [5 empty] | 100: | 2 | Chlorides: | 400
Rotary Drilled (Usft): |  | 469 |  | 3021 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.40 / 5.60
Drlg/Circ Hrs: |  | 1.03 / 1.30 |  | 6.62 / 3.72 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0/100
Slide Drilling Hrs: |  | 0.3 |  | 1.7 |  | SN: |  | 47424 |  | 10s Gel: | 1 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 0.73 |  | 4.92 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.4 / 120.00 | Fluid Loss / Mud Type: | 10 / WBM
ROP Rot/Slide (Usft/hr): |  | 639.55 / 160.00 |  | 614.44 / 213.53 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 5.67 |  | 13.67 |  | Grade In: |  | 0-0-
% Slide: |  | 9.28 |  | 10.73 |  | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
% Rotary: |  | 90.72 |  | 89.27 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
Kevin Cooper |  | Josh Ray |  | Jason Smitters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7/8 5.9 1.50 Stab HPO -.011 NBS 13 |  |  |  | 8 | [5 empty] | 37.43 |  | 38.93
13 Stab |  |  |  | 8.125 | 3 |  |  |  |  | 6.34 |  | 45.27
NMPC |  |  |  | 8 | 3.25 |  |  |  |  | 8.58 |  | 53.85
UBHO Sub UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.66 |  | 57.51
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.83 |  | 86.34
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.99 |  | 115.33
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.13 |  | 117.46
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 274.62 |  | 392.08
392.08
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800017 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.8 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2952 | 13.97 | 269.06 | 2924.22 | 1.9 | -300.29 | 1.11 |  | 62.34 | -141.64 | 0.55 |  | 4.07 | 95
3045 | 14.46 | 271.7 | 3014.37 | 2.06 | -323.12 | 0.87 |  | 54.2 | -152.42 | 0.53 |  | 2.84 | 93
3139 | 14.11 | 269.85 | 3105.46 | 2.38 | -346.31 | 0.61 |  | -128.37 | -163.51 | -0.37 |  | -1.97 | 94
3233 | 13.84 | 269.76 | 3196.68 | 2.3 | -369.01 | 0.29 |  | -175.44 | -174.02 | -0.29 |  | -0.1 | 94
3326 | 13.67 | 269.15 | 3287.02 | 2.09 | -391.12 | 0.24 |  | -139.83 | -184.14 | -0.18 |  | -0.66 | 93
3420 | 14.28 | 270.03 | 3378.23 | 1.93 | -413.82 | 0.69 |  | 19.64 | -194.58 | 0.65 |  | 0.94 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 500.32 | 25.87 | 100 | 249 | 900 | 2606.89 | 2122.67 | 182 | 115 | 110 | 105 | 14327.83 | 3
Run | 511.44 | 16.68 | 97.5 | 243 | 873.71 | 2021.91 | 1665.29 | 182 | 95.78 | 90.78 | 86.97 | 9130.47 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/18/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/18/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/18/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/18/2021 | 00:00 | 00:05 | 0.08 | 2975 | 3024 | 49 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2975.00 t/3024.00, w/WOB 18.60,Flow 900.00, RPM 100.00, Press 2490.00, Tq 13099.00, ROP 588.00
07/18/2021 | 00:05 | 00:08 | 0.05 | 3024 | 3024 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/18/2021 | 00:08 | 00:15 | 0.12 | 3024 | 3117 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3024.00 t/3117.00, w/WOB 33.70,Flow 900.00, RPM 100.00, Press 2721.00, Tq 14531.00, ROP 797.14
07/18/2021 | 00:15 | 00:18 | 0.05 | 3117 | 3117 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/18/2021 | 00:18 | 00:25 | 0.12 | 3117 | 3211 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3117.00 t/3211.00, w/WOB 29.20,Flow 900.00, RPM 100.00, Press 2804.00, Tq 15487.00, ROP 805.71
07/18/2021 | 00:25 | 00:28 | 0.05 | 3211 | 3211 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/18/2021 | 00:28 | 00:33 | 0.08 | 3211 | 3226 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/3211.00 t/3226.00, TF 0.00, w/WOB 20.00,Flow 900.00, Press 2402.00, Tq 0.00, ROP 180.00
07/18/2021 | 00:33 | 00:42 | 0.15 | 3226 | 3305 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3226.00 t/3305.00, w/WOB 35.20,Flow 900.00, RPM 100.00, Press 2639.00, Tq 13744.00, ROP 526.67
07/18/2021 | 00:42 | 00:47 | 0.08 | 3305 | 3305 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/18/2021 | 00:47 | 00:54 | 0.12 | 3305 | 3323 | 18 | SUR | 1: BHA 1 | 2J | Slide Drill f/3305.00 t/3323.00, TF 0.00, w/WOB 19.20,Flow 900.00, Press 2330.00, Tq 0.00, ROP 154.29
07/18/2021 | 00:54 | 01:02 | 0.13 | 3323 | 3398 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3323.00 t/3398.00, w/WOB 30.70,Flow 900.00, RPM 100.00, Press 2874.00, Tq 16495.00, ROP 562.50
07/18/2021 | 01:02 | 01:07 | 0.08 | 3398 | 3398 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/18/2021 | 01:07 | 01:13 | 0.1 | 3398 | 3413 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/3398.00 t/3413.00, TF 0.00, w/WOB 17.30,Flow 900.00, Press 2422.00, Tq 0.00, ROP 150.00
07/18/2021 | 01:13 | 01:21 | 0.13 | 3413 | 3492 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3413.00 t/3492.00, w/WOB 28.90,Flow 900.00, RPM 100.00, Press 2780.00, Tq 12611.00, ROP 592.50
07/18/2021 | 01:21 | 01:25 | 0.07 | 3492 | 3492 | 0 | SUR | 1: BHA 1 | 5A | Survey @ TD
07/18/2021 | 01:25 | 02:20 | 0.92 | 3492 | 3492 | 0 | SUR | 1: BHA 1 | 5A | Circulate t/ POOH f/ casing ops
07/18/2021 | 02:20 | 03:45 | 1.42 | 3492 | 3492 | 0 | SUR | 1: BHA 1 | 6B | POOH
07/18/2021 | 03:45 | 05:40 | 1.92 | 3492 | 3492 | 0 | SUR | 1: BHA 1 | 6P | L/D MWD, Rack back monels in derrick. Drain motor, break bit. L/D UBHO and NMPC. L/D stabilizer and motor.
07/18/2021 | 05:40 | 24:00 | 18.33 | 3492 | 3492 | 0 | SUR |  | 24B | Stand by for casing ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_19_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 39830
|  |  |  | 24hr Summary: |  | N/U BOPE, Test, Drill Int.
|  |  |  | 24hr Lookahead: |  | Drill Int.
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3492 |  | 3492 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 23 | PV: | 9
End Depth (Usft): |  | 4582 |  | 4582 |  | OD (in): |  | 10.75 |  | 300: | 14 | YP: | 5
Total Drilled (Usft): |  | 1090 |  | 1090 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 11 | Viscosity: | 43
Slide Drilled (Usft): |  | 20 |  | 20 | [5 empty] | 100: | 7 | Chlorides: | 70000
Rotary Drilled (Usft): |  | 1070 |  | 1070 | [5 empty] | 6: | 2 | % Sand/Solids: | 0.40 / 4.20
Drlg/Circ Hrs: |  | 2.58 / 1.33 |  | 2.58 / 1.33 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 68/32
Slide Drilling Hrs: |  | 0.12 |  | 0.12 |  | SN: |  | 55156 |  | 10s Gel: | 3 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  | 2.47 |  | 2.47 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.4 / 145.00 | Fluid Loss / Mud Type: | 12 / OBM
ROP Rot/Slide (Usft/hr): |  | 433.78 / 171.43 |  | 433.78 / 171.43 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 10.17 |  | 10.17 |  | Grade In: |  | New
% Slide: |  | 1.83 |  | 1.83 |  | Grade Out: |  | 1-1-BT-N-X-I-CT-TD
% Rotary: |  | 98.17 |  | 98.17 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
Kevin Cooper |  | Josh Ray |  | Jason Smitters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.006 |  |  |  | 8 | 2 |  |  | 100 |  | 37.34 |  | 38.84
NMPC |  |  |  | 8 | 3.25 |  |  | 150 |  | 8.58 |  | 47.42
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.66 |  | 51.08
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.83 |  | 79.91
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.99 |  | 108.9
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 2.36 |  | 111.26
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 185.81 |  | 297.07
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 95 |  | 2.46 |  | 299.53
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.62 |  | 574.15
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2067.4 |  | 2641.55
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.65 |  | 2666.2
2666.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800011 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.82 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3542 | 14.5 | 269.17 | 3496.41 | 1.72 | -444.14 | 0.25 |  | -44.59 | -208.52 | 0.18 |  | -0.7 | 122
3636 | 14.52 | 270.47 | 3587.41 | 1.64 | -467.69 | 0.35 |  | 87.12 | -219.43 | 0.02 |  | 1.38 | 94
3730 | 14.61 | 269.44 | 3678.39 | 1.62 | -491.33 | 0.29 |  | -71.34 | -230.44 | 0.1 |  | -1.1 | 94
3824 | 14.55 | 269.65 | 3769.36 | 1.44 | -514.99 | 0.09 |  | 138.72 | -241.3 | -0.06 |  | 0.22 | 94
3919 | 14.73 | 268.83 | 3861.28 | 1.12 | -539 | 0.29 |  | -49.42 | -252.2 | 0.19 |  | -0.86 | 95
4012 | 14.85 | 268.82 | 3951.19 | 0.63 | -562.73 | 0.13 |  | -1.22 | -262.84 | 0.13 |  | -0.01 | 93
4105 | 14.79 | 268.59 | 4041.1 | 0.09 | -586.52 | 0.09 |  | -135.68 | -273.44 | -0.06 |  | -0.25 | 93
4197 | 14.56 | 268.97 | 4130.1 | -0.4 | -609.82 | 0.27 |  | 157.47 | -283.87 | -0.25 |  | 0.41 | 92
4290 | 14.43 | 268.77 | 4220.14 | -0.86 | -633.09 | 0.15 |  | -159.04 | -294.31 | -0.14 |  | -0.22 | 93
4384 | 13.74 | 269.81 | 4311.31 | -1.15 | -655.96 | 0.78 |  | 160.36 | -304.71 | -0.73 |  | 1.11 | 94
4477 | 13.89 | 269.9 | 4401.62 | -1.21 | -678.17 | 0.16 |  | 8.2 | -315.01 | 0.16 |  | 0.1 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 421.94 | 23.78 | 74.62 | 192 | 708.27 | 3188.47 | 2828.87 | 255 | 151.33 | 148.33 | 144.67 | 8212.15 | 3
Run | 421.94 | 23.78 | 74.62 | 192 | 708.27 | 3188.47 | 2828.87 | 255 | 151.33 | 148.33 | 144.67 | 8212.15 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 07/19/2021 |  | 5 |  | 100 |  | 4 | 400
Dir & MWD /Gamma |  |  |  |  | 07/19/2021 |  | 4 |  | 6850 |  | 1 | 6850
8 Motor Reline |  |  |  |  | 07/19/2021 | PPM800011 | 6 |  | 10500 |  | 1 | 10500
Multi Rig Discount |  |  |  |  | 07/19/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/19/2021 | 00:00 | 12:30 | 12.5 | 3492 | 3492 | 0 | INT |  | 24B | Standby f/ N/U BOPE and test
07/19/2021 | 12:30 | 13:50 | 1.33 | 3492 | 3492 | 0 | INT | 2: BHA 2 | 6O | P/U BHA #2
07/19/2021 | 13:50 | 16:00 | 2.17 | 3492 | 3492 | 0 | INT | 2: BHA 2 | 6A | TIH t/2293
07/19/2021 | 16:00 | 17:00 | 1 | 3492 | 3492 | 0 | INT | 2: BHA 2 | 8P | Rig Service
07/19/2021 | 17:00 | 18:00 | 1 | 3492 | 3492 | 0 | INT | 2: BHA 2 | 24A | P/U Agitator and test same
07/19/2021 | 18:00 | 19:35 | 1.58 | 3492 | 3492 | 0 | INT | 2: BHA 2 | 6A | TIH t/3400
07/19/2021 | 19:35 | 20:05 | 0.5 | 3492 | 3492 | 0 | INT | 2: BHA 2 | 5A | Drill out float collar, shoe track and shoe 3400 -3482
07/19/2021 | 20:05 | 20:10 | 0.08 | 3492 | 3502 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3492.00 t/3502.00, w/WOB 15.00,Flow 420.00, RPM 30.00, Press 1252.00, Tq 4000.00, ROP 120.00
07/19/2021 | 20:10 | 20:20 | 0.17 | 3502 | 3502 | 0 | INT | 2: BHA 2 | 5A | Circulate f/ FIT
07/19/2021 | 20:20 | 20:50 | 0.5 | 3502 | 3502 | 0 | INT | 2: BHA 2 | 15D | FIT
07/19/2021 | 20:50 | 21:10 | 0.33 | 3502 | 3605 | 103 | INT | 2: BHA 2 | 2K | Rotary Drill f/3502.00 t/3605.00, w/WOB 20.00,Flow 600.00, RPM 60.00, Press 2244.00, Tq 4000.00, ROP 309.00
07/19/2021 | 21:10 | 21:15 | 0.08 | 3605 | 3605 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 21:15 | 21:25 | 0.17 | 3605 | 3699 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3605.00 t/3699.00, w/WOB 21.00,Flow 600.00, RPM 80.00, Press 2451.00, Tq 8059.00, ROP 564.00
07/19/2021 | 21:25 | 21:30 | 0.08 | 3699 | 3699 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 21:30 | 21:40 | 0.17 | 3699 | 3793 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3699.00 t/3793.00, w/WOB 29.10,Flow 718.00, RPM 80.00, Press 3221.00, Tq 8772.00, ROP 564.00
07/19/2021 | 21:40 | 21:44 | 0.07 | 3793 | 3793 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 21:44 | 21:55 | 0.18 | 3793 | 3887 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3793.00 t/3887.00, w/WOB 24.20,Flow 718.00, RPM 80.00, Press 3151.00, Tq 7096.00, ROP 512.73
07/19/2021 | 21:55 | 21:58 | 0.05 | 3887 | 3887 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 21:58 | 22:08 | 0.17 | 3887 | 3982 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/3887.00 t/3982.00, w/WOB 29.30,Flow 766.00, RPM 80.00, Press 3520.00, Tq 6184.00, ROP 570.00
07/19/2021 | 22:08 | 22:11 | 0.05 | 3982 | 3982 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 22:11 | 22:21 | 0.17 | 3982 | 4075 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3982.00 t/4075.00, w/WOB 30.10,Flow 766.00, RPM 80.00, Press 3617.00, Tq 9654.00, ROP 558.00
07/19/2021 | 22:21 | 22:24 | 0.05 | 4075 | 4075 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 22:24 | 22:33 | 0.15 | 4075 | 4168 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4075.00 t/4168.00, w/WOB 28.70,Flow 815.00, RPM 80.00, Press 4066.00, Tq 11286.00, ROP 620.00
07/19/2021 | 22:33 | 22:36 | 0.05 | 4168 | 4168 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 22:36 | 22:47 | 0.18 | 4168 | 4260 | 92 | INT | 2: BHA 2 | 2K | Rotary Drill f/4168.00 t/4260.00, w/WOB 29.40,Flow 718.00, RPM 80.00, Press 3315.00, Tq 8241.00, ROP 501.82
07/19/2021 | 22:47 | 22:49 | 0.03 | 4260 | 4260 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 22:49 | 22:59 | 0.17 | 4260 | 4353 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4260.00 t/4353.00, w/WOB 25.40,Flow 718.00, RPM 80.00, Press 3353.00, Tq 8172.00, ROP 558.00
07/19/2021 | 22:59 | 23:03 | 0.07 | 4353 | 4353 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 23:03 | 23:06 | 0.05 | 4353 | 4361 | 8 | INT | 2: BHA 2 | 2J | Slide Drill f/4353.00 t/4361.00, TF 180.00, w/WOB 12.00,Flow 815.00, Press 3806.00, Tq 0.00, ROP 160.00
07/19/2021 | 23:06 | 23:16 | 0.17 | 4361 | 4447 | 86 | INT | 2: BHA 2 | 2K | Rotary Drill f/4361.00 t/4447.00, w/WOB 27.20,Flow 815.00, RPM 80.00, Press 3900.00, Tq 9548.00, ROP 516.00
07/19/2021 | 23:16 | 23:20 | 0.07 | 4447 | 4447 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 23:20 | 23:41 | 0.35 | 4447 | 4540 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4447.00 t/4540.00, w/WOB 28.50,Flow 670.00, RPM 80.00, Press 3027.00, Tq 10198.00, ROP 265.71
07/19/2021 | 23:41 | 23:45 | 0.07 | 4540 | 4540 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/19/2021 | 23:45 | 23:49 | 0.07 | 4540 | 4552 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/4540.00 t/4552.00, TF 180.00, w/WOB 10.00,Flow 670.00, Press 2792.00, Tq 0.00, ROP 180.00
07/19/2021 | 23:49 | 24:00 | 0.18 | 4552 | 4582 | 30 | INT | 2: BHA 2 | 2K | Rotary Drill f/4552.00 t/4582.00, w/WOB 26.80,Flow 815.00, RPM 80.00, Press 4112.00, Tq 11548.00, ROP 163.64
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_20_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 46680
|  |  |  | 24hr Summary: |  | Drill Int.
|  |  |  | 24hr Lookahead: |  | Drill Int.
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 4582 |  | 3492 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 30 | PV: | 11
End Depth (Usft): |  | 10210 |  | 10210 |  | OD (in): |  | 10.75 |  | 300: | 19 | YP: | 8
Total Drilled (Usft): |  | 5628 |  | 6718 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 14 | Viscosity: | 45
Slide Drilled (Usft): |  | 315 |  | 335 | [5 empty] | 100: | 9 | Chlorides: | 78000
Rotary Drilled (Usft): |  | 5313 |  | 6383 | [5 empty] | 6: | 4 | % Sand/Solids: | 0.40 / 3.80
Drlg/Circ Hrs: |  | 18.92 / 4.23 |  | 21.50 / 5.57 |  | Bit Details |  |  |  | 3: | 3 | Oil/Water: | 65/35
Slide Drilling Hrs: |  | 3.25 |  | 3.37 |  | SN: |  | 55156 |  | 10s Gel: | 3 | Weight (ppg): | 8.8
Rotary Drilling Hrs: |  | 15.67 |  | 18.13 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.4 / 176.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 339.13 / 96.92 |  | 352.00 / 99.50 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 34.17 |  | Grade In: |  | New
% Slide: |  | 5.6 |  | 4.99 |  | Grade Out: |  | 1-1-BT-N-X-I-CT-TD
% Rotary: |  | 94.4 |  | 95.01 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
Kevin Cooper |  | Josh Ray |  | Jason Smitters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.006 |  |  |  | 8 | 2 |  |  | 100 |  | 37.34 |  | 38.84
NMPC |  |  |  | 8 | 3.25 |  |  | 150 |  | 8.58 |  | 47.42
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.66 |  | 51.08
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.83 |  | 79.91
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.99 |  | 108.9
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 2.36 |  | 111.26
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 185.81 |  | 297.07
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 95 |  | 2.46 |  | 299.53
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.62 |  | 574.15
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2067.4 |  | 2641.55
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.65 |  | 2666.2
2666.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800011 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.82 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
4571 | 12.99 | 269.51 | 4493.05 | -1.32 | -700.02 | 0.96 |  | -174.44 | -325.1 | -0.96 |  | -0.41 | 94
4664 | 12.77 | 264.24 | 4583.71 | -2.44 | -720.7 | 1.28 |  | -103.17 | -333.74 | -0.24 |  | -5.67 | 93
4759 | 13.2 | 262.3 | 4676.28 | -4.95 | -741.89 | 0.64 |  | -46.34 | -341.4 | 0.45 |  | -2.04 | 95
4853 | 12.02 | 262.45 | 4768.01 | -7.67 | -762.23 | 1.26 |  | 178.48 | -348.47 | -1.26 |  | 0.16 | 94
4947 | 11.14 | 257.78 | 4860.1 | -10.88 | -780.81 | 1.37 |  | -135.46 | -354.29 | -0.94 |  | -4.97 | 94
5041 | 10.23 | 255.57 | 4952.47 | -14.88 | -797.77 | 1.06 |  | -156.84 | -358.66 | -0.97 |  | -2.35 | 94
5134 | 9.77 | 252.98 | 5044.06 | -19.25 | -813.31 | 0.69 |  | -136.92 | -362.04 | -0.49 |  | -2.78 | 93
5229 | 8.1 | 255.26 | 5137.9 | -23.31 | -827.49 | 1.8 |  | 169.15 | -365.05 | -1.76 |  | 2.4 | 95
5322 | 6.71 | 257.59 | 5230.12 | -26.15 | -839.14 | 1.53 |  | 168.96 | -367.97 | -1.49 |  | 2.51 | 93
5416 | 4.88 | 256.17 | 5323.64 | -28.28 | -848.38 | 1.95 |  | -176.23 | -370.39 | -1.95 |  | -1.51 | 94
5510 | 3.7 | 274.01 | 5417.38 | -29.03 | -855.29 | 1.88 |  | 140.15 | -372.95 | -1.26 |  | 18.98 | 94
5604 | 2.06 | 298.6 | 5511.26 | -28 | -859.8 | 2.15 |  | 154.86 | -375.96 | -1.74 |  | 26.16 | 94
5699 | 1.96 | 325.57 | 5606.2 | -25.85 | -862.22 | 0.99 |  | 109.4 | -378.99 | -0.11 |  | 28.39 | 95
5792 | 2 | 352.82 | 5699.15 | -22.92 | -863.32 | 1 |  | 101.23 | -382.09 | 0.04 |  | 29.3 | 93
5886 | 2.42 | 347.57 | 5793.08 | -19.36 | -863.95 | 0.5 |  | -28.37 | -385.54 | 0.45 |  | -5.59 | 94
5980 | 0.95 | 309.7 | 5887.04 | -16.92 | -864.98 | 1.88 |  | -160.75 | -388.18 | -1.56 |  | -40.29 | 94
6074 | 1.17 | 285.97 | 5981.02 | -16.16 | -866.5 | 0.52 |  | -75.58 | -389.56 | 0.23 |  | 0 | 94
6168 | 1.46 | 302.88 | 6075 | -15.25 | -868.43 | 0.51 |  | 61.88 | -391.27 | 0.31 |  | 0 | 94
6262 | 1.61 | 303.64 | 6168.96 | -13.87 | -870.54 | 0.16 |  | 8.11 | -393.47 | 0.16 |  | 0 | 94
6355 | 1.73 | 307.7 | 6261.92 | -12.28 | -872.74 | 0.18 |  | 46.64 | -395.89 | 0.13 |  | 4.37 | 93
6449 | 0.92 | 279.91 | 6355.9 | -11.29 | -874.6 | 1.08 |  | -154.91 | -397.65 | -0.86 |  | -29.56 | 94
6543 | 0.85 | 219.9 | 6449.89 | -11.69 | -875.79 | 0.94 |  | -123.92 | -397.84 | -0.07 |  | 0 | 94
6637 | 0.72 | 167.1 | 6543.88 | -12.8 | -876.11 | 0.75 |  | -125.87 | -397.01 | -0.14 |  | 0 | 94
6732 | 0.47 | 206.33 | 6638.88 | -13.73 | -876.15 | 0.49 |  | 140.13 | -396.2 | -0.26 |  | 0 | 95
6826 | 0.51 | 217.69 | 6732.87 | -14.41 | -876.57 | 0.11 |  | 73.37 | -395.8 | 0.04 |  | 0 | 94
6919 | 0.59 | 125.8 | 6825.87 | -15.02 | -876.44 | 0.85 |  | -131.92 | -395.2 | 0.09 |  | 0 | 93
7014 | 1.03 | 111.51 | 6920.86 | -15.62 | -875.25 | 0.51 |  | -31.92 | -394.12 | 0.46 |  | 0 | 95
7108 | 0.82 | 104.26 | 7014.85 | -16.09 | -873.81 | 0.26 |  | -154.46 | -393.03 | -0.22 |  | 0 | 94
7201 | 0.7 | 82.9 | 7107.84 | -16.19 | -872.6 | 0.33 |  | -123.39 | -392.38 | -0.13 |  | 0 | 93
7295 | 0.76 | 61.92 | 7201.83 | -15.82 | -871.48 | 0.29 |  | -87.97 | -392.18 | 0.06 |  | 0 | 94
7389 | 0.82 | 59.15 | 7295.83 | -15.18 | -870.35 | 0.08 |  | -33.87 | -392.22 | 0.06 |  | 0 | 94
7483 | 0.69 | 44.51 | 7389.82 | -14.43 | -869.38 | 0.25 |  | -131.15 | -392.43 | -0.14 |  | 0 | 94
7577 | 0.76 | 40.21 | 7483.81 | -13.55 | -868.58 | 0.09 |  | -40.02 | -392.83 | 0.07 |  | 0 | 94
7670 | 0.95 | 9.95 | 7576.8 | -12.32 | -868.05 | 0.52 |  | -82.79 | -393.67 | 0.2 |  | 0 | 93
7764 | 1.16 | 340.87 | 7670.78 | -10.66 | -868.23 | 0.6 |  | -83.54 | -395.23 | 0.22 |  | 0 | 94
7857 | 0.58 | 339.92 | 7763.77 | -9.33 | -868.7 | 0.62 |  | -179.05 | -396.63 | -0.62 |  | 0 | 93
7951 | 0.92 | 322.02 | 7857.77 | -8.28 | -869.32 | 0.44 |  | -43.74 | -397.84 | 0.36 |  | 0 | 94
8045 | 1.6 | 330.4 | 7951.74 | -6.55 | -870.44 | 0.75 |  | 19.38 | -399.9 | 0.72 |  | 0 | 94
8139 | 1.67 | 344.01 | 8045.7 | -4.09 | -871.46 | 0.42 |  | 86.63 | -402.55 | 0.07 |  | 14.48 | 94
8232 | 1.47 | 51.42 | 8138.68 | -2.04 | -870.9 | 1.88 |  | 129.15 | -404.1 | -0.22 |  | 72.48 | 93
8326 | 1.48 | 60.76 | 8232.65 | -0.7 | -868.9 | 0.26 |  | 92.29 | -404.36 | 0.01 |  | 0 | 94
8420 | 1.39 | 53.58 | 8326.62 | 0.57 | -866.92 | 0.21 |  | -120.15 | -404.56 | -0.1 |  | 0 | 94
8515 | 1.43 | 61.1 | 8421.59 | 1.83 | -864.96 | 0.2 |  | 81.58 | -404.76 | 0.04 |  | 0 | 95
8609 | 1.07 | 50.44 | 8515.56 | 2.95 | -863.26 | 0.45 |  | -152.39 | -404.96 | -0.38 |  | 0 | 94
8703 | 1.06 | 40.28 | 8609.55 | 4.18 | -862.02 | 0.2 |  | -98.1 | -405.46 | -0.01 |  | 0 | 94
8797 | 1.13 | 16.53 | 8703.53 | 5.73 | -861.19 | 0.48 |  | -93.23 | -406.45 | 0.07 |  | 0 | 94
8891 | 1.08 | 15.41 | 8797.51 | 7.47 | -860.69 | 0.06 |  | -157.2 | -407.76 | -0.05 |  | 0 | 94
8986 | 0.86 | 3.85 | 8892.5 | 9.05 | -860.41 | 0.31 |  | -144.03 | -409.02 | -0.23 |  | 0 | 95
9079 | 0.83 | 1.52 | 8985.49 | 10.41 | -860.34 | 0.05 |  | -132.28 | -410.2 | -0.03 |  | 0 | 93
9173 | 1.15 | 4.62 | 9079.48 | 12.04 | -860.25 | 0.35 |  | 11.05 | -411.59 | 0.34 |  | 0 | 94
9267 | 0.99 | 355.47 | 9173.46 | 13.79 | -860.24 | 0.25 |  | -137.63 | -413.13 | -0.17 |  | 0 | 94
9360 | 1.29 | 328.24 | 9266.44 | 15.48 | -860.85 | 0.66 |  | -75.1 | -414.92 | 0.32 |  | 0 | 93
9454 | 1.42 | 321.16 | 9360.42 | 17.28 | -862.14 | 0.23 |  | -55.75 | -417.11 | 0.14 |  | 0 | 94
9549 | 0.75 | 313.13 | 9455.4 | 18.63 | -863.33 | 0.72 |  | -171.21 | -418.86 | -0.71 |  | 0 | 95
9644 | 0.95 | 325.24 | 9550.39 | 19.7 | -864.23 | 0.28 |  | 48.09 | -420.23 | 0.21 |  | 0 | 95
9738 | 0.52 | 4 | 9644.38 | 20.76 | -864.65 | 0.67 |  | 149.13 | -421.36 | -0.46 |  | 0 | 94
9831 | 0.38 | 345.1 | 9737.38 | 21.48 | -864.7 | 0.22 |  | -142.51 | -422.02 | -0.15 |  | 0 | 93
9924 | 0.51 | 336.31 | 9830.38 | 22.16 | -864.94 | 0.16 |  | -32.15 | -422.74 | 0.14 |  | 0 | 93
10019 | 0.96 | 304.32 | 9925.37 | 22.99 | -865.77 | 0.62 |  | -59.11 | -423.86 | 0.47 |  | 0 | 95
10112 | 1.04 | 257.64 | 10018.35 | 23.25 | -867.24 | 0.86 |  | -108.04 | -424.77 | 0.09 |  | 0 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 297.52 | 24.97 | 80 | 224 | 865.98 | 4798.18 | 4263.59 | 255 | 212.42 | 193.82 | 177.85 | 14677.44 | 3
Run | 312.47 | 24.8 | 79.16 | 219 | 844.07 | 4574.61 | 4064.32 | 255 | 203.94 | 187.5 | 173.24 | 13664.81 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/20/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/20/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/20/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/20/2021 | 00:00 | 00:05 | 0.08 | 4582 | 4634 | 52 | INT | 2: BHA 2 | 2K | Rotary Drill f/4582.00 t/4634.00, w/WOB 26.80,Flow 815.00, RPM 80.00, Press 4112.00, Tq 11548.00, ROP 624.00
07/20/2021 | 00:05 | 00:08 | 0.05 | 4634 | 4634 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 00:08 | 00:11 | 0.05 | 4634 | 4644 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4634.00 t/4644.00, TF 180.00, w/WOB 8.00,Flow 815.00, Press 3787.00, Tq 0.00, ROP 200.00
07/20/2021 | 00:11 | 00:21 | 0.17 | 4644 | 4727 | 83 | INT | 2: BHA 2 | 2K | Rotary Drill f/4644.00 t/4727.00, w/WOB 25.40,Flow 815.00, RPM 80.00, Press 4003.00, Tq 12205.00, ROP 498.00
07/20/2021 | 00:21 | 00:24 | 0.05 | 4727 | 4727 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 00:24 | 00:28 | 0.07 | 4727 | 4739 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/4727.00 t/4739.00, TF 150.00, w/WOB 10.00,Flow 815.00, Press 3864.00, Tq 0.00, ROP 180.00
07/20/2021 | 00:28 | 00:39 | 0.18 | 4739 | 4822 | 83 | INT | 2: BHA 2 | 2K | Rotary Drill f/4739.00 t/4822.00, w/WOB 25.20,Flow 815.00, RPM 80.00, Press 4049.00, Tq 11029.00, ROP 452.73
07/20/2021 | 00:39 | 00:43 | 0.07 | 4822 | 4822 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 00:43 | 00:50 | 0.12 | 4822 | 4834 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/4822.00 t/4834.00, TF 150.00, w/WOB 10.00,Flow 861.00, Press 4115.00, Tq 0.00, ROP 102.86
07/20/2021 | 00:50 | 00:59 | 0.15 | 4834 | 4916 | 82 | INT | 2: BHA 2 | 2K | Rotary Drill f/4834.00 t/4916.00, w/WOB 28.90,Flow 861.00, RPM 80.00, Press 4433.00, Tq 13324.00, ROP 546.67
07/20/2021 | 00:59 | 01:02 | 0.05 | 4916 | 4916 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 01:02 | 01:07 | 0.08 | 4916 | 4928 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/4916.00 t/4928.00, TF 150.00, w/WOB 12.00,Flow 861.00, Press 4221.00, Tq 0.00, ROP 144.00
07/20/2021 | 01:07 | 01:18 | 0.18 | 4928 | 5010 | 82 | INT | 2: BHA 2 | 2K | Rotary Drill f/4928.00 t/5010.00, w/WOB 26.80,Flow 861.00, RPM 80.00, Press 4120.00, Tq 11067.00, ROP 447.27
07/20/2021 | 01:18 | 01:23 | 0.08 | 5010 | 5010 | 0 | INT | 2: BHA 2 | 24A | Replace pin in pop-off
07/20/2021 | 01:23 | 01:27 | 0.07 | 5010 | 5010 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 01:27 | 01:33 | 0.1 | 5010 | 5024 | 14 | INT | 2: BHA 2 | 2J | Slide Drill f/5010.00 t/5024.00, TF 140.00, w/WOB 8.00,Flow 815.00, Press 3923.00, Tq 0.00, ROP 140.00
07/20/2021 | 01:33 | 01:43 | 0.17 | 5024 | 5104 | 80 | INT | 2: BHA 2 | 2K | Rotary Drill f/5024.00 t/5104.00, w/WOB 27.90,Flow 815.00, RPM 80.00, Press 4152.00, Tq 12324.00, ROP 480.00
07/20/2021 | 01:43 | 01:46 | 0.05 | 5104 | 5104 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 01:46 | 01:57 | 0.18 | 5104 | 5119 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5104.00 t/5119.00, TF 140.00, w/WOB 2.00,Flow 900.00, Press 4501.00, Tq 0.00, ROP 81.82
07/20/2021 | 01:57 | 02:04 | 0.12 | 5119 | 5197 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/5119.00 t/5197.00, w/WOB 33.20,Flow 900.00, RPM 80.00, Press 4866.00, Tq 12424.00, ROP 668.57
07/20/2021 | 02:04 | 02:08 | 0.07 | 5197 | 5197 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 02:08 | 02:16 | 0.13 | 5197 | 5215 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/5197.00 t/5215.00, TF 130.00, w/WOB 12.30,Flow 765.00, Press 3537.00, Tq 0.00, ROP 135.00
07/20/2021 | 02:16 | 02:29 | 0.22 | 5215 | 5292 | 77 | INT | 2: BHA 2 | 2K | Rotary Drill f/5215.00 t/5292.00, w/WOB 30.10,Flow 900.00, RPM 80.00, Press 4677.00, Tq 13227.00, ROP 355.38
07/20/2021 | 02:29 | 02:33 | 0.07 | 5292 | 5292 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 02:33 | 02:40 | 0.12 | 5292 | 5310 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/5292.00 t/5310.00, TF 130.00, w/WOB 14.00,Flow 900.00, Press 4672.00, Tq 0.00, ROP 154.29
07/20/2021 | 02:40 | 02:50 | 0.17 | 5310 | 5385 | 75 | INT | 2: BHA 2 | 2K | Rotary Drill f/5310.00 t/5385.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 4828.00, Tq 12461.00, ROP 450.00
07/20/2021 | 02:50 | 02:54 | 0.07 | 5385 | 5385 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 02:54 | 03:00 | 0.1 | 5385 | 5403 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/5385.00 t/5403.00, TF 130.00, w/WOB 2.00,Flow 900.00, Press 4545.00, Tq 0.00, ROP 180.00
07/20/2021 | 03:00 | 03:11 | 0.18 | 5403 | 5479 | 76 | INT | 2: BHA 2 | 2K | Rotary Drill f/5403.00 t/5479.00, w/WOB 34.30,Flow 900.00, RPM 80.00, Press 4804.00, Tq 15137.00, ROP 414.55
07/20/2021 | 03:11 | 03:14 | 0.05 | 5479 | 5479 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 03:14 | 03:20 | 0.1 | 5479 | 5497 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/5479.00 t/5497.00, TF 120.00, w/WOB 16.00,Flow 900.00, Press 4551.00, Tq 0.00, ROP 180.00
07/20/2021 | 03:20 | 03:30 | 0.17 | 5497 | 5573 | 76 | INT | 2: BHA 2 | 2K | Rotary Drill f/5497.00 t/5573.00, w/WOB 28.30,Flow 900.00, RPM 80.00, Press 4757.00, Tq 12155.00, ROP 456.00
07/20/2021 | 03:30 | 03:33 | 0.05 | 5573 | 5573 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 03:33 | 03:40 | 0.12 | 5573 | 5591 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/5573.00 t/5591.00, TF 130.00, w/WOB 16.00,Flow 900.00, Press 4687.00, Tq 0.00, ROP 154.29
07/20/2021 | 03:40 | 03:50 | 0.17 | 5591 | 5667 | 76 | INT | 2: BHA 2 | 2K | Rotary Drill f/5591.00 t/5667.00, w/WOB 25.70,Flow 900.00, RPM 80.00, Press 4871.00, Tq 15025.00, ROP 456.00
07/20/2021 | 03:50 | 03:53 | 0.05 | 5667 | 5667 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 03:53 | 03:59 | 0.1 | 5667 | 5682 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5667.00 t/5682.00, TF 30.00, w/WOB 12.00,Flow 900.00, Press 4703.00, Tq 0.00, ROP 150.00
07/20/2021 | 03:59 | 04:09 | 0.17 | 5682 | 5762 | 80 | INT | 2: BHA 2 | 2K | Rotary Drill f/5682.00 t/5762.00, w/WOB 29.20,Flow 900.00, RPM 80.00, Press 4931.00, Tq 14700.00, ROP 480.00
07/20/2021 | 04:09 | 04:12 | 0.05 | 5762 | 5762 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 04:12 | 04:19 | 0.12 | 5762 | 5777 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5762.00 t/5777.00, TF 90.00, w/WOB 12.00,Flow 900.00, Press 4727.00, Tq 0.00, ROP 128.57
07/20/2021 | 04:19 | 04:34 | 0.25 | 5777 | 5855 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/5777.00 t/5855.00, w/WOB 33.10,Flow 900.00, RPM 80.00, Press 4953.00, Tq 11692.00, ROP 312.00
07/20/2021 | 04:34 | 04:38 | 0.07 | 5855 | 5855 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 04:38 | 04:46 | 0.13 | 5855 | 5870 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/5855.00 t/5870.00, TF 150.00, w/WOB 12.00,Flow 900.00, Press 4672.00, Tq 0.00, ROP 112.50
07/20/2021 | 04:46 | 04:56 | 0.17 | 5870 | 5949 | 79 | INT | 2: BHA 2 | 2K | Rotary Drill f/5870.00 t/5949.00, w/WOB 30.30,Flow 900.00, RPM 80.00, Press 4981.00, Tq 15442.00, ROP 474.00
07/20/2021 | 04:56 | 05:00 | 0.07 | 5949 | 5949 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 05:00 | 05:07 | 0.12 | 5949 | 5967 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/5949.00 t/5967.00, TF 150.00, w/WOB 12.00,Flow 900.00, Press 4520.00, Tq 0.00, ROP 154.29
07/20/2021 | 05:07 | 05:18 | 0.18 | 5967 | 6043 | 76 | INT | 2: BHA 2 | 2K | Rotary Drill f/5967.00 t/6043.00, w/WOB 31.40,Flow 900.00, RPM 80.00, Press 4874.00, Tq 14337.00, ROP 414.55
07/20/2021 | 05:18 | 05:22 | 0.07 | 6043 | 6043 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 05:22 | 05:34 | 0.2 | 6043 | 6137 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6043.00 t/6137.00, w/WOB 30.90,Flow 900.00, RPM 80.00, Press 5050.00, Tq 11217.00, ROP 470.00
07/20/2021 | 05:34 | 05:37 | 0.05 | 6137 | 6137 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 05:37 | 05:50 | 0.22 | 6137 | 6232 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6137.00 t/6232.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 11217.00, ROP 438.46
07/20/2021 | 05:50 | 05:53 | 0.05 | 6232 | 6232 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 05:53 | 06:05 | 0.2 | 6232 | 6325 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6232.00 t/6325.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 465.00
07/20/2021 | 06:05 | 06:08 | 0.05 | 6325 | 6325 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 06:08 | 06:20 | 0.2 | 6325 | 6418 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6325.00 t/6418.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 465.00
07/20/2021 | 06:20 | 06:23 | 0.05 | 6418 | 6418 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 06:23 | 06:26 | 0.05 | 6418 | 6441 | 23 | INT | 2: BHA 2 | 2K | Rotary Drill f/6418.00 t/6441.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 460.00
07/20/2021 | 06:26 | 06:36 | 0.17 | 6441 | 6451 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/6441.00 t/6451.00, TF 120.00, w/WOB 18.00,Flow 900.00, Press 5050.00, Tq 12000.00, ROP 60.00
07/20/2021 | 06:36 | 06:45 | 0.15 | 6451 | 6512 | 61 | INT | 2: BHA 2 | 2K | Rotary Drill f/6451.00 t/6512.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 406.67
07/20/2021 | 06:45 | 06:48 | 0.05 | 6512 | 6512 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 06:48 | 06:53 | 0.08 | 6512 | 6535 | 23 | INT | 2: BHA 2 | 2K | Rotary Drill f/6512.00 t/6535.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 276.00
07/20/2021 | 06:53 | 07:03 | 0.17 | 6535 | 6545 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/6535.00 t/6545.00, TF 90.00, w/WOB 28.00,Flow 900.00, Press 5050.00, Tq 12000.00, ROP 60.00
07/20/2021 | 07:03 | 07:15 | 0.2 | 6545 | 6606 | 61 | INT | 2: BHA 2 | 2K | Rotary Drill f/6545.00 t/6606.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 305.00
07/20/2021 | 07:15 | 07:18 | 0.05 | 6606 | 6606 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 07:18 | 07:30 | 0.2 | 6606 | 6700 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6606.00 t/6700.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 470.00
07/20/2021 | 07:30 | 07:43 | 0.22 | 6700 | 6700 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 07:43 | 07:57 | 0.23 | 6700 | 6795 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6700.00 t/6795.00, w/WOB 28.00,Flow 900.00, RPM 80.00, Press 5050.00, Tq 12000.00, ROP 407.14
07/20/2021 | 07:57 | 08:00 | 0.05 | 6795 | 6795 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 08:00 | 08:09 | 0.15 | 6795 | 6864 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/6795.00 t/6864.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 460.00
07/20/2021 | 08:09 | 08:20 | 0.18 | 6864 | 6864 | 0 | INT | 2: BHA 2 | 24A | Replace pin in pop-off
07/20/2021 | 08:20 | 08:24 | 0.07 | 6864 | 6889 | 25 | INT | 2: BHA 2 | 2K | Rotary Drill f/6864.00 t/6889.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 375.00
07/20/2021 | 08:24 | 08:28 | 0.07 | 6889 | 6889 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 08:28 | 08:32 | 0.07 | 6889 | 6906 | 17 | INT | 2: BHA 2 | 2K | Rotary Drill f/6889.00 t/6906.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 255.00
07/20/2021 | 08:32 | 08:40 | 0.13 | 6906 | 6919 | 13 | INT | 2: BHA 2 | 2J | Slide Drill f/6906.00 t/6919.00, TF 90.00, w/WOB 15.00,Flow 900.00, Press 5300.00, Tq 13000.00, ROP 97.50
07/20/2021 | 08:40 | 08:54 | 0.23 | 6919 | 6982 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/6919.00 t/6982.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 270.00
07/20/2021 | 08:54 | 08:58 | 0.07 | 6982 | 6982 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 08:58 | 09:10 | 0.2 | 6982 | 7077 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6982.00 t/7077.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 475.00
07/20/2021 | 09:10 | 09:17 | 0.12 | 7077 | 7077 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 09:17 | 09:40 | 0.38 | 7077 | 7171 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7077.00 t/7171.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 245.22
07/20/2021 | 09:40 | 09:44 | 0.07 | 7171 | 7171 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 09:44 | 09:55 | 0.18 | 7171 | 7264 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7171.00 t/7264.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 507.27
07/20/2021 | 09:55 | 09:59 | 0.07 | 7264 | 7264 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 09:59 | 10:15 | 0.27 | 7264 | 7358 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7264.00 t/7358.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 5300.00, Tq 13000.00, ROP 352.50
07/20/2021 | 10:15 | 10:19 | 0.07 | 7358 | 7358 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 10:19 | 10:38 | 0.32 | 7358 | 7452 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7358.00 t/7452.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 296.84
07/20/2021 | 10:38 | 10:42 | 0.07 | 7452 | 7452 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 10:42 | 11:01 | 0.32 | 7452 | 7546 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7452.00 t/7546.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 296.84
07/20/2021 | 11:01 | 11:06 | 0.08 | 7546 | 7546 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 11:06 | 11:16 | 0.17 | 7546 | 7640 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7546.00 t/7640.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 564.00
07/20/2021 | 11:16 | 11:20 | 0.07 | 7640 | 7640 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 11:20 | 11:42 | 0.37 | 7640 | 7733 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7640.00 t/7733.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 253.64
07/20/2021 | 11:42 | 11:46 | 0.07 | 7733 | 7733 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 11:46 | 12:00 | 0.23 | 7733 | 7827 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7733.00 t/7827.00, w/WOB 20.00,Flow 700.00, RPM 80.00, Press 3800.00, Tq 15000.00, ROP 402.86
07/20/2021 | 12:00 | 12:08 | 0.13 | 7827 | 7827 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 12:08 | 12:12 | 0.07 | 7827 | 7844 | 17 | INT | 2: BHA 2 | 2K | Rotary Drill f/7827.00 t/7844.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 15000.00, ROP 255.00
07/20/2021 | 12:12 | 12:22 | 0.17 | 7844 | 7854 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/7844.00 t/7854.00, TF 90.00, w/WOB 15.00,Flow 900.00, Press 4800.00, Tq 15000.00, ROP 60.00
07/20/2021 | 12:22 | 12:34 | 0.2 | 7854 | 7920 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/7854.00 t/7920.00, w/WOB 25.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 15000.00, ROP 330.00
07/20/2021 | 12:34 | 12:38 | 0.07 | 7920 | 7920 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 12:38 | 13:01 | 0.38 | 7920 | 8014 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7920.00 t/8014.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 245.22
07/20/2021 | 13:01 | 13:05 | 0.07 | 8014 | 8014 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 13:05 | 13:16 | 0.18 | 8014 | 8108 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8014.00 t/8108.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 512.73
07/20/2021 | 13:16 | 13:20 | 0.07 | 8108 | 8108 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 13:20 | 13:23 | 0.05 | 8108 | 8132 | 24 | INT | 2: BHA 2 | 2K | Rotary Drill f/8108.00 t/8132.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 480.00
07/20/2021 | 13:23 | 13:33 | 0.17 | 8132 | 8142 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/8132.00 t/8142.00, TF 180.00, w/WOB 20.00,Flow 900.00, Press 4800.00, Tq 16500.00, ROP 60.00
07/20/2021 | 13:33 | 13:45 | 0.2 | 8142 | 8202 | 60 | INT | 2: BHA 2 | 2K | Rotary Drill f/8142.00 t/8202.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 300.00
07/20/2021 | 13:45 | 13:49 | 0.07 | 8202 | 8202 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 13:49 | 13:52 | 0.05 | 8202 | 8213 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/8202.00 t/8213.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 220.00
07/20/2021 | 13:52 | 14:02 | 0.17 | 8213 | 8228 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/8213.00 t/8228.00, TF 90.00, w/WOB 20.00,Flow 900.00, Press 4800.00, Tq 16500.00, ROP 90.00
07/20/2021 | 14:02 | 14:14 | 0.2 | 8228 | 8295 | 67 | INT | 2: BHA 2 | 2K | Rotary Drill f/8228.00 t/8295.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 335.00
07/20/2021 | 14:14 | 14:17 | 0.05 | 8295 | 8295 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 14:17 | 14:30 | 0.22 | 8295 | 8389 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8295.00 t/8389.00, w/WOB 30.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 433.85
07/20/2021 | 14:30 | 14:34 | 0.07 | 8389 | 8389 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 14:34 | 14:51 | 0.28 | 8389 | 8483 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8389.00 t/8483.00, w/WOB 33.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 331.76
07/20/2021 | 14:51 | 14:55 | 0.07 | 8483 | 8483 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 14:55 | 15:09 | 0.23 | 8483 | 8578 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8483.00 t/8578.00, w/WOB 33.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 16500.00, ROP 407.14
07/20/2021 | 15:09 | 15:13 | 0.07 | 8578 | 8578 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 15:13 | 15:48 | 0.58 | 8578 | 8672 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8578.00 t/8672.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5700.00, Tq 19000.00, ROP 161.14
07/20/2021 | 15:48 | 15:52 | 0.07 | 8672 | 8672 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 15:52 | 16:06 | 0.23 | 8672 | 8766 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8672.00 t/8766.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5700.00, Tq 19000.00, ROP 402.86
07/20/2021 | 16:06 | 16:10 | 0.07 | 8766 | 8766 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 16:10 | 16:34 | 0.4 | 8766 | 8860 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8766.00 t/8860.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5700.00, Tq 19000.00, ROP 235.00
07/20/2021 | 16:34 | 16:38 | 0.07 | 8860 | 8860 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 16:38 | 17:17 | 0.65 | 8860 | 8954 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8860.00 t/8954.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5700.00, Tq 19000.00, ROP 144.62
07/20/2021 | 17:17 | 17:52 | 0.58 | 8954 | 8954 | 0 | INT | 2: BHA 2 | 24A | Inspect and clean inline screen
07/20/2021 | 17:52 | 17:56 | 0.07 | 8954 | 8954 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 17:56 | 18:14 | 0.3 | 8954 | 9049 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8954.00 t/9049.00, w/WOB 29.20,Flow 880.00, RPM 80.00, Press 5437.00, Tq 17063.00, ROP 316.67
07/20/2021 | 18:14 | 18:18 | 0.07 | 9049 | 9049 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 18:18 | 18:33 | 0.25 | 9049 | 9142 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9049.00 t/9142.00, w/WOB 25.40,Flow 880.00, RPM 80.00, Press 5449.00, Tq 17438.00, ROP 372.00
07/20/2021 | 18:33 | 18:37 | 0.07 | 9142 | 9142 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 18:37 | 18:50 | 0.22 | 9142 | 9236 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9142.00 t/9236.00, w/WOB 25.40,Flow 880.00, RPM 80.00, Press 5500.00, Tq 17338.00, ROP 433.85
07/20/2021 | 18:50 | 18:53 | 0.05 | 9236 | 9236 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 18:53 | 19:09 | 0.27 | 9236 | 9330 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9236.00 t/9330.00, w/WOB 27.80,Flow 880.00, RPM 80.00, Press 5348.00, Tq 16682.00, ROP 352.50
07/20/2021 | 19:09 | 19:12 | 0.05 | 9330 | 9330 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 19:12 | 19:28 | 0.27 | 9330 | 9423 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9330.00 t/9423.00, w/WOB 27.20,Flow 880.00, RPM 80.00, Press 5324.00, Tq 16006.00, ROP 348.75
07/20/2021 | 19:28 | 19:38 | 0.17 | 9423 | 9423 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 19:38 | 19:56 | 0.3 | 9423 | 9517 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9423.00 t/9517.00, w/WOB 28.20,Flow 880.00, RPM 80.00, Press 5342.00, Tq 16669.00, ROP 313.33
07/20/2021 | 19:56 | 19:59 | 0.05 | 9517 | 9517 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 19:59 | 20:14 | 0.25 | 9517 | 9612 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/9517.00 t/9612.00, w/WOB 35.00,Flow 860.00, RPM 80.00, Press 5393.00, Tq 17301.00, ROP 380.00
07/20/2021 | 20:14 | 20:18 | 0.07 | 9612 | 9612 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 20:18 | 20:34 | 0.27 | 9612 | 9707 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/9612.00 t/9707.00, w/WOB 35.00,Flow 860.00, RPM 80.00, Press 5393.00, Tq 17301.00, ROP 356.25
07/20/2021 | 20:34 | 20:37 | 0.05 | 9707 | 9707 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 20:37 | 20:41 | 0.07 | 9707 | 9723 | 16 | INT | 2: BHA 2 | 2K | Rotary Drill f/9707.00 t/9723.00, w/WOB 35.00,Flow 860.00, RPM 80.00, Press 5393.00, Tq 17301.00, ROP 240.00
07/20/2021 | 20:41 | 20:55 | 0.23 | 9723 | 9731 | 8 | INT | 2: BHA 2 | 2J | Slide Drill f/9723.00 t/9731.00, TF 150.00, w/WOB 20.00,Flow 860.00, Press 4897.00, Tq 0.00, ROP 34.29
07/20/2021 | 20:55 | 21:10 | 0.25 | 9731 | 9731 | 0 | INT | 2: BHA 2 | 5A | Reduce flow for shakers blinding off
07/20/2021 | 21:10 | 21:25 | 0.25 | 9731 | 9801 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/9731.00 t/9801.00, w/WOB 30.00,Flow 691.00, RPM 80.00, Press 3769.00, Tq 16038.00, ROP 280.00
07/20/2021 | 21:25 | 21:28 | 0.05 | 9801 | 9801 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 21:28 | 21:47 | 0.32 | 9801 | 9894 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9801.00 t/9894.00, w/WOB 34.00,Flow 860.00, RPM 80.00, Press 5394.00, Tq 16926.00, ROP 293.68
07/20/2021 | 21:47 | 21:50 | 0.05 | 9894 | 9894 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 21:50 | 22:19 | 0.48 | 9894 | 9987 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9894.00 t/9987.00, w/WOB 35.00,Flow 860.00, RPM 80.00, Press 5198.00, Tq 15844.00, ROP 192.41
07/20/2021 | 22:19 | 22:22 | 0.05 | 9987 | 9987 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 22:22 | 22:46 | 0.4 | 9987 | 10082 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/9987.00 t/10082.00, w/WOB 35.00,Flow 860.00, RPM 80.00, Press 5198.00, Tq 15844.00, ROP 237.50
07/20/2021 | 22:46 | 22:50 | 0.07 | 10082 | 10082 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 22:50 | 22:55 | 0.08 | 10082 | 10094 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/10082.00 t/10094.00, w/WOB 35.00,Flow 691.00, RPM 80.00, Press 3836.00, Tq 16875.00, ROP 144.00
07/20/2021 | 22:55 | 23:20 | 0.42 | 10094 | 10105 | 11 | INT | 2: BHA 2 | 2J | Slide Drill f/10094.00 t/10105.00, TF 150.00, w/WOB 15.00,Flow 691.00, Press 3523.00, Tq 0.00, ROP 26.40
07/20/2021 | 23:20 | 23:49 | 0.48 | 10105 | 10175 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/10105.00 t/10175.00, w/WOB 25.00,Flow 765.00, RPM 80.00, Press 4957.00, Tq 16382.00, ROP 144.83
07/20/2021 | 23:49 | 23:52 | 0.05 | 10175 | 10175 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/20/2021 | 23:52 | 24:00 | 0.13 | 10175 | 10210 | 35 | INT | 2: BHA 2 | 2K | Rotary Drill f/10175.00 t/10210.00, w/WOB 25.00,Flow 784.00, RPM 80.00, Press 5144.00, Tq 16382.00, ROP 262.50
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_21_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/21/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 53530
|  |  |  | 24hr Summary: |  | Drill Int. circulate to POOH f/ casing ops
|  |  |  | 24hr Lookahead: |  | Circulate, POOH, Casing ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10210 |  | 3492 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 30 | PV: | 11
End Depth (Usft): |  | 10936 |  | 10936 |  | OD (in): |  | 10.75 |  | 300: | 19 | YP: | 8
Total Drilled (Usft): |  | 726 |  | 7444 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 14 | Viscosity: | 45
Slide Drilled (Usft): |  | 641 |  | 976 | [5 empty] | 100: | 10 | Chlorides: | 79000
Rotary Drilled (Usft): |  | 85 |  | 6468 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 7.80
Drlg/Circ Hrs: |  | 21.02 / 1.98 |  | 42.52 / 7.55 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 65/35
Slide Drilling Hrs: |  | 20.53 |  | 23.9 |  | SN: |  | 55156 |  | 10s Gel: | 5 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 0.48 |  | 18.62 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.4 / 230.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 175.86 / 31.22 |  | 347.43 / 40.84 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 58.17 |  | Grade In: |  | New
% Slide: |  | 88.29 |  | 13.11 |  | Grade Out: |  | 1-1-BT-N-X-I-CT-TD
% Rotary: |  | 11.71 |  | 86.89 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
Kevin Cooper |  | Josh Ray |  | Jason Smitters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.006 |  |  |  | 8 | 2 |  |  | 100 |  | 37.34 |  | 38.84
NMPC |  |  |  | 8 | 3.25 |  |  | 150 |  | 8.58 |  | 47.42
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.66 |  | 51.08
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.83 |  | 79.91
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.99 |  | 108.9
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 2.36 |  | 111.26
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 185.81 |  | 297.07
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 95 |  | 2.46 |  | 299.53
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.62 |  | 574.15
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2067.4 |  | 2641.55
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.65 |  | 2666.2
2666.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800011 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.82 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10207 | 1.16 | 264.5 | 10113.34 | 22.98 | -869.04 | 0.19 |  | 51.12 | -425.37 | 0.13 |  | 0 | 95
10300 | 1.75 | 188.09 | 10206.31 | 21.48 | -870.17 | 2 |  | -113.75 | -424.57 | 0.63 |  | 0 | 93
10394 | 8.87 | 176.55 | 10299.85 | 12.81 | -869.94 | 7.62 |  | -14.32 | -416.8 | 7.57 |  | -12.28 | 94
10489 | 13.68 | 180.07 | 10392.99 | -5.74 | -869.51 | 5.11 |  | 9.88 | -400.18 | 5.06 |  | 3.71 | 95
10583 | 16.65 | 200.72 | 10483.77 | -29.48 | -874.29 | 6.51 |  | 71.44 | -381.41 | 3.16 |  | 21.97 | 94
10677 | 20.55 | 198.52 | 10572.85 | -57.73 | -884.3 | 4.21 |  | -11.25 | -361.08 | 4.15 |  | -2.34 | 94
10772 | 21.39 | 193.16 | 10661.56 | -90.41 | -893.54 | 2.2 |  | -68.87 | -336.47 | 0.88 |  | -5.64 | 95
10873 | 27.54 | 191.21 | 10753.45 | -131.29 | -902.29 | 6.14 |  | -8.37 | -304.38 | 6.09 |  | -1.93 | 101
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 34.54 | 18.33 | 80 | 202 | 732.67 | 4441.08 | 4097.58 | 255 | 306.67 | 259.17 | 242.5 | 17000 | 3
Run | 175.08 | 24.16 | 79.18 | 217 | 832.93 | 4561.26 | 4067.65 | 255 | 214.21 | 194.67 | 180.17 | 13743.28 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/21/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/21/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/21/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/21/2021 | 00:00 | 00:15 | 0.25 | 10210 | 10270 | 60 | INT | 2: BHA 2 | 2K | Rotary Drill f/10210.00 t/10270.00, w/WOB 25.00,Flow 784.00, RPM 80.00, Press 5411.00, Tq 17000.00, ROP 240.00
07/21/2021 | 00:15 | 00:18 | 0.05 | 10270 | 10270 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
07/21/2021 | 00:18 | 00:23 | 0.08 | 10270 | 10280 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/10270.00 t/10280.00, w/WOB 35.00,Flow 784.00, RPM 80.00, Press 5411.00, Tq 17000.00, ROP 120.00
07/21/2021 | 00:23 | 02:55 | 2.53 | 10280 | 10363 | 83 | CRV | 2: BHA 2 | 2J | Slide Drill f/10280.00 t/10363.00, TF 150.00, w/WOB 12.00,Flow 784.00, Press 4804.00, Tq 0.00, ROP 32.76
07/21/2021 | 02:55 | 02:58 | 0.05 | 10363 | 10363 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/21/2021 | 02:58 | 04:20 | 1.37 | 10363 | 10410 | 47 | CRV | 2: BHA 2 | 2J | Slide Drill f/10363.00 t/10410.00, TF 150.00, w/WOB 14.00,Flow 717.00, Press 4149.00, Tq 0.00, ROP 34.39
07/21/2021 | 04:20 | 04:24 | 0.07 | 10410 | 10410 | 0 | CRV | 2: BHA 2 | 5A | Check shot
07/21/2021 | 04:24 | 05:28 | 1.07 | 10410 | 10457 | 47 | CRV | 2: BHA 2 | 2J | Slide Drill f/10410.00 t/10457.00, TF -40.00, w/WOB 18.00,Flow 717.00, Press 4180.00, Tq 0.00, ROP 44.06
07/21/2021 | 05:28 | 05:31 | 0.05 | 10457 | 10457 | 0 | CRV | 2: BHA 2 | 5A | BOP Drill
07/21/2021 | 05:31 | 05:36 | 0.08 | 10457 | 10457 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/21/2021 | 05:36 | 05:45 | 0.15 | 10457 | 10472 | 15 | CRV | 2: BHA 2 | 2K | Rotary Drill f/10457.00 t/10472.00, w/WOB 18.00,Flow 717.00, RPM 0.00, Press 4180.00, Tq 0.00, ROP 100.00
07/21/2021 | 05:45 | 07:36 | 1.85 | 10472 | 10552 | 80 | CRV | 2: BHA 2 | 2J | Slide Drill f/10472.00 t/10552.00, TF 0.00, w/WOB 18.00,Flow 717.00, Press 4180.00, Tq 0.00, ROP 43.24
07/21/2021 | 07:36 | 07:43 | 0.12 | 10552 | 10552 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/21/2021 | 07:43 | 10:23 | 2.67 | 10552 | 10646 | 94 | CRV | 2: BHA 2 | 2J | Slide Drill f/10552.00 t/10646.00, TF -60.00, w/WOB 18.00,Flow 717.00, Press 4180.00, Tq 0.00, ROP 35.25
07/21/2021 | 10:23 | 10:30 | 0.12 | 10646 | 10646 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/21/2021 | 10:30 | 13:42 | 3.2 | 10646 | 10740 | 94 | CRV | 2: BHA 2 | 2J | Slide Drill f/10646.00 t/10740.00, TF -60.00, w/WOB 18.00,Flow 717.00, Press 4180.00, Tq 0.00, ROP 29.38
07/21/2021 | 13:42 | 13:49 | 0.12 | 10740 | 10740 | 0 | CRV | 2: BHA 2 | 5A | Survey & Connection
07/21/2021 | 13:49 | 16:52 | 3.05 | 10740 | 10835 | 95 | CRV | 2: BHA 2 | 2J | Slide Drill f/10740.00 t/10835.00, TF -40.00, w/WOB 20.00,Flow 800.00, Press 5200.00, Tq 0.00, ROP 31.15
07/21/2021 | 16:52 | 17:52 | 1 | 10835 | 10835 | 0 | CRV | 2: BHA 2 | 8P | Rig Service
07/21/2021 | 17:52 | 22:00 | 4.13 | 10835 | 10929 | 94 | CRV | 2: BHA 2 | 2J | Slide Drill f/10835.00 t/10929.00, TF -30.00, w/WOB 12.00,Flow 669.00, Press 3709.00, Tq 0.00, ROP 22.74
07/21/2021 | 22:00 | 22:10 | 0.17 | 10929 | 10929 | 0 | CRV | 2: BHA 2 | 5A | Connection
07/21/2021 | 22:10 | 22:50 | 0.67 | 10929 | 10936 | 7 | CRV | 2: BHA 2 | 2J | Slide Drill f/10929.00 t/10936.00, TF -30.00, w/WOB 12.00,Flow 669.00, Press 3709.00, Tq 0.00, ROP 10.50
07/21/2021 | 22:50 | 24:00 | 1.17 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 5A | Circulate @ Int TD
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_22_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/22/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 60380
|  |  |  | 24hr Summary: |  | Circulate, POOH, Work Tight Hole, POOH
|  |  |  | 24hr Lookahead: |  | POOH f/ casing ops, Run Casing
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10936 |  | 3492 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 10936 |  | 10936 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  |  |  | 7444 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 15 | Viscosity: | 42
Slide Drilled (Usft): |  |  |  | 976 | [5 empty] | 100: | 10 | Chlorides: | 80000
Rotary Drilled (Usft): |  |  |  | 6468 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.40 / 9.70
Drlg/Circ Hrs: |  | 0.00 / 1.50 |  | 42.52 / 9.05 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 66/34
Slide Drilling Hrs: |  |  |  | 23.9 |  | SN: |  | 55156 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  |  |  | 18.62 |  | Bit # |  | 2 |  | PH / Temp(F) | 7.4 / 242.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 347.43 / 40.84 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 18 |  | 76.17 |  | Grade In: |  | New
% Slide: |  |  |  | 13.11 |  | Grade Out: |  | 1-1-BT-N-X-I-CT-TD
% Rotary: |  |  |  | 86.89 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | J. Ray X. Cantu |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.006 |  |  |  | 8 | 2 |  |  | 100 |  | 37.34 |  | 38.84
NMPC |  |  |  | 8 | 3.25 |  |  | 150 |  | 8.58 |  | 47.42
UBHO Sub |  |  |  | 7.75 | 2.875 |  |  | 150 |  | 3.66 |  | 51.08
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.83 |  | 79.91
NMDC |  |  |  | 8 | 3.25 |  |  | 150 |  | 28.99 |  | 108.9
Crossover Sub |  |  |  | 7.875 | 2.875 |  |  | 100 |  | 2.36 |  | 111.26
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 185.81 |  | 297.07
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 95 |  | 2.46 |  | 299.53
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.62 |  | 574.15
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2067.4 |  | 2641.55
Agitator |  |  |  | 6.75 | 3.75 |  |  | 80 |  | 24.65 |  | 2666.2
2666.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800011 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.82 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 18.33 | 80 | 202 | 732.67 | 4441.08 | 4097.58 | 255 | 306.67 | 259.17 | 242.5 | 17000 | 3
Run | 175.08 | 24.16 | 79.18 | 217 | 832.93 | 4561.26 | 4067.65 | 255 | 214.21 | 194.67 | 180.17 | 13743.28 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/22/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/22/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 07/22/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/22/2021 | 00:00 | 00:30 | 0.5 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 5A | Circulate t/ POOH f/ Casing ops
07/22/2021 | 00:30 | 01:00 | 0.5 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 6B | POOH t/ 10489
07/22/2021 | 01:00 | 01:30 | 0.5 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 6I | Flow check and pump slug
07/22/2021 | 01:30 | 02:45 | 1.25 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 6B | POOH t/ 6942
07/22/2021 | 02:45 | 03:45 | 1 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 3B | Work tight hole
07/22/2021 | 03:45 | 04:45 | 1 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 3D | Attempt to back ream, lost 80k string weight and 1700 PSI
07/22/2021 | 04:45 | 17:00 | 12.25 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 6B | POOH
07/22/2021 | 17:00 | 18:00 | 1 | 10936 | 10936 | 0 | CRV | 2: BHA 2 | 6P | Lay down BHA
07/22/2021 | 18:00 | 24:00 | 6 | 10936 | 10936 | 0 | CRV |  | 24B | Stand by to run casing
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_24_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/24/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 69830
|  |  |  | 24hr Summary: |  | P/U BHA
|  |  |  | 24hr Lookahead: |  | Land curve & drill lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10936 |  | 10936 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 31 | PV: | 11
End Depth (Usft): |  | 11802 |  | 11802 |  | OD (in): |  | 10.75 |  | 300: | 20 | YP: | 9
Total Drilled (Usft): |  | 866 |  | 866 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 15 | Viscosity: | 42
Slide Drilled (Usft): |  | 437 |  | 437 | [5 empty] | 100: | 10 | Chlorides: | 80000
Rotary Drilled (Usft): |  | 429 |  | 429 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.40 / 9.70
Drlg/Circ Hrs: |  | 7.93 / 4.07 |  | 7.93 / 4.07 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 66/34
Slide Drilling Hrs: |  | 4.93 |  | 4.93 |  | SN: |  | 13635755 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 3 |  | 3 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.4 / 242.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 143.00 / 88.58 |  | 143.00 / 88.58 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 19.33 |  | 19.33 |  | Grade In: |  | New
% Slide: |  | 50.46 |  | 50.46 |  | Grade Out:
% Rotary: |  | 49.54 |  | 49.54 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 TS HS88 +.011 |  |  |  | 5.5 | 2 |  |  | 45.34 |  | 33.27 |  | 34.27
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.91
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 7.49 |  | 43.4
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 3.83 |  | 47.23
NMDC |  |  |  | 5.25 | 2.75 |  |  | 48.69 |  | 31.23 |  | 78.46
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.88 |  | 88.34
NMDC |  |  |  | 5.25 | 2.625 |  |  | 48.7 |  | 30.54 |  | 118.88
Filter Sub |  |  |  | 5 | 2.25 |  |  | 68.63 |  | 4.95 |  | 123.83
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.94 |  | 141.77
Crossover |  |  |  | 5.375 | 2.688 |  |  | 57.69 |  | 2.6 |  | 144.37
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 332.19
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 340.82
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2795.06
Agitator |  |  |  | 5.25 | 2.688 |  |  | 55.38 |  | 21.67 |  | 2816.73
2816.73
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 3.97 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10873 | 27.54 | 191.21 | 10753.45 | -131.29 | -902.29 | 6.14 |  | -8.37 | -304.38 | 6.09 |  | -1.93 | 101
10971 | 34.37 | 187.7 | 10837.45 | -180.99 | -910.41 | 7.21 |  | -16.33 | -264.19 | 6.97 |  | -3.58 | 98
11065 | 46.48 | 171.82 | 10909.07 | -241.4 | -909.1 | 16.83 |  | -46.7 | -210.14 | 12.88 |  | -16.89 | 94
11160 | 52.12 | 158.41 | 10971.15 | -310.59 | -890.34 | 12.22 |  | -65.49 | -140.18 | 5.94 |  | -14.12 | 95
11255 | 58.27 | 149.11 | 11025.43 | -380.29 | -855.72 | 10.31 |  | -53.89 | -62.37 | 6.47 |  | -9.79 | 95
11350 | 59.92 | 149.47 | 11074.22 | -450.37 | -814.1 | 1.77 |  | 10.7 | 19.03 | 1.74 |  | 0.38 | 95
11444 | 63.22 | 147.37 | 11118.97 | -520.77 | -770.8 | 4.02 |  | -29.74 | 101.49 | 3.51 |  | -2.23 | 94
11539 | 70.52 | 142.47 | 11156.29 | -592.12 | -720.56 | 9.03 |  | -32.68 | 188.04 | 7.68 |  | -5.16 | 95
11633 | 78.73 | 142.05 | 11181.19 | -663.73 | -665.13 | 8.74 |  | -2.88 | 277.23 | 8.73 |  | -0.45 | 94
11728 | 80.94 | 142.94 | 11197.95 | -737.91 | -608.2 | 2.5 |  | 21.7 | 369.39 | 2.33 |  | 0.94 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 109.16 | 18.33 | 80 | 732 | 732.67 | 4441.08 | 4097.58 | 140 | 306.67 | 259.17 | 242.5 | 17000 | 3
Run | 109.16 | 24.16 | 79.18 | 820 | 832.93 | 4561.26 | 4067.65 | 140 | 214.21 | 194.67 | 180.17 | 13743.28 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 09/24/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 09/24/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/24/2021 |  | 4 |  | 6850 |  | 1 | 6850
Real Time Survey Management |  |  |  |  | 09/24/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/24/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/24/2021 | 00:00 | 02:40 | 2.67 | 10936 | 10936 | 0 | CRV2 |  | 24B | Standby for BOP Test
09/24/2021 | 02:40 | 04:40 | 2 | 10936 | 10936 | 0 | CRV2 | 3: BHA 3 | 6O | Pick Up BHA #3
09/24/2021 | 04:40 | 12:00 | 7.33 | 10936 | 10936 | 0 | CRV2 | 3: BHA 3 | 6A | TIH
09/24/2021 | 12:00 | 14:10 | 2.17 | 10936 | 10936 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 14:10 | 15:18 | 1.13 | 10936 | 11037 | 101 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/10946.00 t/11037.00, TF -60.00G, w/WOB 26.00,Flow 300.00, Press 3600.00, Tq 0.00, ROP 80.29, Diff 1000.00, Temp 224.00
09/24/2021 | 15:18 | 15:28 | 0.17 | 11037 | 11037 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 15:28 | 16:35 | 1.12 | 11037 | 11131 | 94 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11037.00 t/11131.00, TF -70.00G, w/WOB 26.00,Flow 300.00, Press 3600.00, Tq 0.00, ROP 84.18, Diff 1000.00, Temp 235.00
09/24/2021 | 16:35 | 16:47 | 0.2 | 11131 | 11131 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 16:47 | 17:15 | 0.47 | 11131 | 11171 | 40 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11131.00 t/11171.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 85.71, Diff 800.00, Temp 239.00
09/24/2021 | 17:15 | 17:49 | 0.57 | 11171 | 11226 | 55 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11171.00 t/11226.00, TF -60.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 97.06, Diff 800.00, Temp 239.00
09/24/2021 | 17:49 | 18:04 | 0.25 | 11226 | 11226 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 18:04 | 18:27 | 0.38 | 11226 | 11256 | 30 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11226.00 t/11256.00, TF 0.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 78.26, Diff 800.00, Temp 239.00
09/24/2021 | 18:27 | 18:55 | 0.47 | 11256 | 11321 | 65 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11256.00 t/11321.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 139.29, Diff 800.00, Temp 239.00
09/24/2021 | 18:55 | 19:11 | 0.27 | 11321 | 11321 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 19:11 | 19:20 | 0.15 | 11321 | 11331 | 10 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11321.00 t/11331.00, TF 0.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 66.67, Diff 800.00, Temp 239.00
09/24/2021 | 19:20 | 19:50 | 0.5 | 11331 | 11416 | 85 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11331.00 t/11416.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 170.00, Diff 800.00, Temp 239.00
09/24/2021 | 19:50 | 20:00 | 0.17 | 11416 | 11416 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 20:00 | 20:30 | 0.5 | 11416 | 11463 | 47 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11416.00 t/11463.00, TF -30.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 94.00, Diff 800.00, Temp 239.00
09/24/2021 | 20:30 | 20:50 | 0.33 | 11463 | 11510 | 47 | CRV2 | 3: BHA 3 | 2K | Rotary Drill f/11463.00 t/11510.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 141.00, Diff 800.00, Temp 239.00
09/24/2021 | 20:50 | 21:03 | 0.22 | 11510 | 11510 | 0 | CRV2 | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 21:03 | 21:33 | 0.5 | 11510 | 11565 | 55 | CRV2 | 3: BHA 3 | 2J | Slide Drill f/11510.00 t/11565.00, TF -20.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 110.00, Diff 800.00, Temp 239.00
09/24/2021 | 21:33 | 21:50 | 0.28 | 11565 | 11605 | 40 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11565.00 t/11605.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 141.18, Diff 800.00, Temp 239.00
09/24/2021 | 21:50 | 22:02 | 0.2 | 11605 | 11605 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 22:02 | 22:18 | 0.27 | 11605 | 11627 | 22 | LAT | 3: BHA 3 | 2J | Slide Drill f/11605.00 t/11627.00, TF 0.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 82.50, Diff 800.00, Temp 239.00
09/24/2021 | 22:18 | 22:45 | 0.45 | 11627 | 11699 | 72 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11627.00 t/11699.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 160.00, Diff 800.00, Temp 239.00
09/24/2021 | 22:45 | 22:58 | 0.22 | 11699 | 11699 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 22:58 | 23:10 | 0.2 | 11699 | 11714 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/11699.00 t/11714.00, TF 0.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 75.00, Diff 800.00, Temp 239.00
09/24/2021 | 23:10 | 23:40 | 0.5 | 11714 | 11794 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11714.00 t/11794.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 160.00, Diff 800.00, Temp 239.00
09/24/2021 | 23:40 | 23:53 | 0.22 | 11794 | 11794 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/24/2021 | 23:53 | 24:00 | 0.12 | 11794 | 11802 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/11794.00 t/11802.00, TF -20.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 68.57, Diff 800.00, Temp 239.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_25_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/25/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 79280
|  |  |  | 24hr Summary: |  | Land Curve & Drill Lateral
|  |  |  | 24hr Lookahead: |  | Drill Ahead in Lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11802 |  | 10936 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 49 | PV: | 19
End Depth (Usft): |  | 15183 |  | 15183 |  | OD (in): |  | 10.75 |  | 300: | 30 | YP: | 11
Total Drilled (Usft): |  | 3381 |  | 4247 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 20 | Viscosity: | 52
Slide Drilled (Usft): |  | 208 |  | 645 | [5 empty] | 100: | 14 | Chlorides: | 53000
Rotary Drilled (Usft): |  | 3173 |  | 3602 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 12.80
Drlg/Circ Hrs: |  | 21.25 / 2.75 |  | 29.18 / 6.82 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 74/26
Slide Drilling Hrs: |  | 3.28 |  | 8.22 |  | SN: |  | 13635755 |  | 10s Gel: | 5 | Weight (ppg): | 10.3
Rotary Drilling Hrs: |  | 17.97 |  | 20.97 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.4 / 257.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 176.60 / 63.35 |  | 171.80 / 78.50 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 43.33 |  | Grade In: |  | New
% Slide: |  | 6.15 |  | 15.19 |  | Grade Out:
% Rotary: |  | 93.85 |  | 84.81 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 TS HS88 +.011 |  |  |  | 5.5 | 2 |  |  | 45.34 |  | 33.27 |  | 34.27
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.91
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 7.49 |  | 43.4
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 3.83 |  | 47.23
NMDC |  |  |  | 5.25 | 2.75 |  |  | 48.69 |  | 31.23 |  | 78.46
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.88 |  | 88.34
NMDC |  |  |  | 5.25 | 2.625 |  |  | 48.7 |  | 30.54 |  | 118.88
Filter Sub |  |  |  | 5 | 2.25 |  |  | 68.63 |  | 4.95 |  | 123.83
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.94 |  | 141.77
Crossover |  |  |  | 5.375 | 2.688 |  |  | 57.69 |  | 2.6 |  | 144.37
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 332.19
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 340.82
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2795.06
Agitator |  |  |  | 5.25 | 2.688 |  |  | 55.38 |  | 21.67 |  | 2816.73
2816.73
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 3.97 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11823 | 84.85 | 143.15 | 11209.7 | -813.23 | -551.54 | 4.12 |  | 3.06 | 462.44 | 4.12 |  | 0.22 | 95
11917 | 86.62 | 144.18 | 11216.69 | -888.74 | -496 | 2.18 |  | 30.17 | 555.13 | 1.88 |  | 1.1 | 94
12012 | 84.62 | 144.11 | 11223.95 | -965.51 | -440.52 | 2.11 |  | -178 | 648.91 | -2.11 |  | -0.07 | 95
12107 | 84.6 | 144.15 | 11232.87 | -1042.15 | -385.1 | 0.05 |  | 0 | 742.55 | -0.02 |  | 0.04 | 95
12202 | 84.4 | 144.41 | 11241.98 | -1118.92 | -329.89 | 0.34 |  | 127.71 | 836.2 | -0.21 |  | 0.27 | 95
12297 | 84.13 | 144.29 | 11251.47 | -1195.73 | -274.8 | 0.31 |  | -156.15 | 929.84 | -0.28 |  | -0.13 | 95
12391 | 85.55 | 146.42 | 11259.92 | -1272.75 | -221.59 | 2.72 |  | 56.3 | 1022.78 | 1.51 |  | 2.27 | 94
12483 | 86.35 | 147.74 | 11266.42 | -1349.78 | -171.71 | 1.67 |  | 58.77 | 1114.18 | 0.87 |  | 1.43 | 92
12578 | 86.32 | 148.26 | 11272.49 | -1430.18 | -121.48 | 0.55 |  | 93.33 | 1208.72 | -0.03 |  | 0.55 | 95
12672 | 86.32 | 147.71 | 11278.53 | -1509.72 | -71.74 | 0.58 |  | -90.02 | 1302.27 | 0 |  | -0.59 | 94
12764 | 86.45 | 149.32 | 11284.33 | -1588.01 | -23.79 | 1.75 |  | 85.43 | 1393.9 | 0.14 |  | 1.75 | 92
12859 | 86.52 | 149.46 | 11290.15 | -1669.62 | 24.49 | 0.16 |  | 63.4 | 1488.6 | 0.07 |  | 0.15 | 95
12953 | 84.54 | 151.22 | 11297.48 | -1751.05 | 70.86 | 2.81 |  | 138.52 | 1582.26 | -2.11 |  | 1.87 | 94
13048 | 84.44 | 151.64 | 11306.6 | -1834.1 | 116.08 | 0.45 |  | 103.47 | 1676.81 | -0.11 |  | 0.44 | 95
13142 | 84.45 | 151.58 | 11315.7 | -1916.4 | 160.57 | 0.06 |  | -80.5 | 1770.36 | 0.01 |  | -0.06 | 94
13237 | 85.17 | 152.63 | 11324.29 | -2000.02 | 204.83 | 1.34 |  | 55.5 | 1864.97 | 0.76 |  | 1.11 | 95
13332 | 85.83 | 153 | 11331.75 | -2084.26 | 248.1 | 0.8 |  | 29.21 | 1959.67 | 0.69 |  | 0.39 | 95
13427 | 85.54 | 153.08 | 11338.9 | -2168.7 | 291.05 | 0.32 |  | 164.62 | 2054.39 | -0.31 |  | 0.08 | 95
13521 | 89.34 | 152.46 | 11343.09 | -2252.18 | 334.01 | 4.1 |  | -9.27 | 2148.28 | 4.04 |  | -0.66 | 94
13616 | 89.02 | 151.01 | 11344.45 | -2335.84 | 378.99 | 1.56 |  | -102.46 | 2243.26 | -0.34 |  | -1.53 | 95
13711 | 87.67 | 150.23 | 11347.2 | -2418.59 | 425.57 | 1.64 |  | -150 | 2338.18 | -1.42 |  | -0.82 | 95
13805 | 88.48 | 150.2 | 11350.35 | -2500.12 | 472.24 | 0.86 |  | -2.12 | 2432.07 | 0.86 |  | -0.03 | 94
13899 | 86.87 | 151.22 | 11354.17 | -2582.04 | 518.19 | 2.03 |  | 147.68 | 2525.96 | -1.71 |  | 1.09 | 94
13993 | 87.48 | 151 | 11358.8 | -2664.24 | 563.55 | 0.69 |  | -19.82 | 2619.82 | 0.65 |  | -0.23 | 94
14086 | 86.27 | 151.36 | 11363.87 | -2745.59 | 608.31 | 1.36 |  | 163.46 | 2712.67 | -1.3 |  | 0.39 | 93
14181 | 86.38 | 150.68 | 11369.96 | -2828.53 | 654.25 | 0.72 |  | -80.81 | 2807.45 | 0.12 |  | -0.72 | 95
14275 | 86.11 | 149.93 | 11376.12 | -2910.01 | 700.71 | 0.85 |  | -109.86 | 2901.2 | -0.29 |  | -0.8 | 94
14370 | 86.32 | 148.83 | 11382.39 | -2991.58 | 748.99 | 1.18 |  | -79.21 | 2995.87 | 0.22 |  | -1.16 | 95
14466 | 86.47 | 152 | 11388.42 | -3074.89 | 796.29 | 3.3 |  | 87.39 | 3091.62 | 0.16 |  | 3.3 | 96
14560 | 86.66 | 151.69 | 11394.06 | -3157.62 | 840.56 | 0.39 |  | -58.46 | 3185.45 | 0.2 |  | -0.33 | 94
14654 | 86.35 | 151.16 | 11399.79 | -3240.01 | 885.44 | 0.65 |  | -120.39 | 3279.27 | -0.33 |  | -0.56 | 94
14749 | 86.91 | 150.37 | 11405.37 | -3322.77 | 931.76 | 1.02 |  | -54.65 | 3374.07 | 0.59 |  | -0.83 | 95
14842 | 86.42 | 149.01 | 11410.78 | -3402.92 | 978.61 | 1.55 |  | -109.88 | 3466.82 | -0.53 |  | -1.46 | 93
14936 | 86.86 | 150.53 | 11416.29 | -3483.99 | 1025.86 | 1.68 |  | 73.87 | 3560.57 | 0.47 |  | 1.62 | 94
15031 | 85.39 | 154.29 | 11422.71 | -3567.98 | 1069.75 | 4.24 |  | 111.52 | 3655.33 | -1.55 |  | 3.96 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 159.11 | 25.65 | 78.78 | 390 | 350 | 4945.45 | 3980 | 140 | 233.64 | 215.91 | 190 | 8.33 | 3
Run | 145.53 | 24.49 | 71.67 | 382 | 348.61 | 4815.28 | 3883.33 | 140 | 229.24 | 221.6 | 190 | 7.92 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 09/25/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 09/25/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/25/2021 |  | 4 |  | 6850 |  | 1 | 6850
Real Time Survey Management |  |  |  |  | 09/25/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/25/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/25/2021 | 00:00 | 00:07 | 0.12 | 11802 | 11816 | 14 | LAT | 3: BHA 3 | 2J | Slide Drill f/11802.00 t/11816.00, TF -20.00G, w/WOB 20.00,Flow 350.00, Press 4500.00, Tq 5.50, ROP 120.00, Diff 800.00
09/25/2021 | 00:07 | 00:37 | 0.5 | 11816 | 11889 | 73 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11816.00 t/11889.00, w/WOB 20.00,Flow 350.00, RPM 30.00, Press 4500.00, Tq 5.50, ROP 146.00, Diff 800.00
09/25/2021 | 00:37 | 00:41 | 0.07 | 11889 | 11889 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 00:41 | 01:21 | 0.67 | 11889 | 11983 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11889.00 t/11983.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 141.00, Diff 800.00, Temp 257.00
09/25/2021 | 01:21 | 01:25 | 0.07 | 11983 | 11983 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 01:25 | 01:30 | 0.08 | 11983 | 11996 | 13 | LAT | 3: BHA 3 | 2K | Rotary Drill f/11983.00 t/11996.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 156.00, Diff 800.00, Temp 257.00
09/25/2021 | 01:30 | 01:43 | 0.22 | 11996 | 12008 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/11996.00 t/12008.00, TF 180.00G, w/WOB 20.00,Flow 350.00, Press 4700.00, Tq 7.50, ROP 55.38, Diff 800.00, Temp 257.00
09/25/2021 | 01:43 | 02:06 | 0.38 | 12008 | 12078 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12008.00 t/12078.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 182.61, Diff 800.00, Temp 257.00
09/25/2021 | 02:06 | 02:09 | 0.05 | 12078 | 12078 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 02:09 | 02:40 | 0.52 | 12078 | 12173 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12078.00 t/12173.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 183.87, Diff 800.00, Temp 257.00
09/25/2021 | 02:40 | 02:43 | 0.05 | 12173 | 12173 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 02:43 | 03:15 | 0.53 | 12173 | 12268 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12173.00 t/12268.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 178.13, Diff 800.00, Temp 257.00
09/25/2021 | 03:15 | 03:18 | 0.05 | 12268 | 12268 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 03:18 | 03:46 | 0.47 | 12268 | 12363 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12268.00 t/12363.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 203.57, Diff 800.00, Temp 257.00
09/25/2021 | 03:46 | 03:49 | 0.05 | 12363 | 12363 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 03:49 | 03:55 | 0.1 | 12363 | 12380 | 17 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12363.00 t/12380.00, w/WOB 20.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 170.00, Diff 800.00, Temp 257.00
09/25/2021 | 03:55 | 04:14 | 0.32 | 12380 | 12400 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/12380.00 t/12400.00, TF 70.00G, w/WOB 25.00,Flow 350.00, Press 4700.00, Tq 7.50, ROP 63.16, Diff 800.00, Temp 257.00
09/25/2021 | 04:14 | 04:33 | 0.32 | 12400 | 12457 | 57 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12400.00 t/12457.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 180.00, Diff 800.00, Temp 257.00
09/25/2021 | 04:33 | 04:38 | 0.08 | 12457 | 12457 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 04:38 | 05:08 | 0.5 | 12457 | 12549 | 92 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12457.00 t/12549.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 184.00, Diff 800.00, Temp 257.00
09/25/2021 | 05:08 | 05:11 | 0.05 | 12549 | 12549 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 05:11 | 05:43 | 0.53 | 12549 | 12644 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12549.00 t/12644.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 4700.00, Tq 7.50, ROP 178.13, Diff 800.00, Temp 257.00
09/25/2021 | 05:43 | 05:47 | 0.07 | 12644 | 12644 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 05:47 | 06:18 | 0.52 | 12644 | 12738 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12644.00 t/12738.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 8.00, ROP 181.94, Diff 1050.00, Temp 279.00
09/25/2021 | 06:18 | 06:22 | 0.07 | 12738 | 12738 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 06:22 | 06:34 | 0.2 | 12738 | 12753 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12738.00 t/12753.00, TF 90.00G, w/WOB 33.00,Flow 350.00, Press 5000.00, Tq 8.00, ROP 75.00, Diff 1050.00, Temp 279.00
09/25/2021 | 06:34 | 07:05 | 0.52 | 12753 | 12830 | 77 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12753.00 t/12830.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 8.00, ROP 149.03, Diff 1050.00, Temp 279.00
09/25/2021 | 07:05 | 07:09 | 0.07 | 12830 | 12830 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 07:09 | 07:42 | 0.55 | 12830 | 12925 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12830.00 t/12925.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 8.00, ROP 172.73, Diff 1050.00, Temp 279.00
09/25/2021 | 07:42 | 07:46 | 0.07 | 12925 | 12925 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 07:46 | 07:59 | 0.22 | 12925 | 12940 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/12925.00 t/12940.00, TF 130.00G, w/WOB 33.00,Flow 350.00, Press 5000.00, Tq 8.00, ROP 69.23, Diff 1050.00, Temp 279.00
09/25/2021 | 07:59 | 08:32 | 0.55 | 12940 | 13019 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/12940.00 t/13019.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 8.00, ROP 143.64, Diff 1050.00, Temp 279.00
09/25/2021 | 08:32 | 08:36 | 0.07 | 13019 | 13019 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 08:36 | 09:00 | 0.4 | 13019 | 13114 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13019.00 t/13114.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 8.00, ROP 237.50, Diff 1050.00, Temp 279.00
09/25/2021 | 09:00 | 09:04 | 0.07 | 13114 | 13114 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 09:04 | 09:36 | 0.53 | 13114 | 13208 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13114.00 t/13208.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5000.00, Tq 8.00, ROP 176.25, Diff 1050.00, Temp 279.00
09/25/2021 | 09:36 | 09:40 | 0.07 | 13208 | 13208 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 09:40 | 09:50 | 0.17 | 13208 | 13218 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/13208.00 t/13218.00, TF 40.00G, w/WOB 35.00,Flow 350.00, Press 5000.00, Tq 8.00, ROP 60.00, Diff 1050.00, Temp 279.00
09/25/2021 | 09:50 | 10:25 | 0.58 | 13218 | 13303 | 85 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13218.00 t/13303.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 8.50, ROP 145.71, Diff 1050.00, Temp 284.00
09/25/2021 | 10:25 | 10:29 | 0.07 | 13303 | 13303 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 10:29 | 10:56 | 0.45 | 13303 | 13398 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13303.00 t/13398.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 8.50, ROP 211.11, Diff 1050.00, Temp 284.00
09/25/2021 | 10:56 | 11:00 | 0.07 | 13398 | 13398 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 11:00 | 11:28 | 0.47 | 13398 | 13493 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13398.00 t/13493.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 8.50, ROP 203.57, Diff 1050.00, Temp 284.00
09/25/2021 | 11:28 | 11:32 | 0.07 | 13493 | 13493 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 11:32 | 11:43 | 0.18 | 13493 | 13505 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/13493.00 t/13505.00, TF -30.00G, w/WOB 35.00,Flow 350.00, Press 5050.00, Tq 8.50, ROP 65.45, Diff 1050.00, Temp 284.00
09/25/2021 | 11:43 | 12:15 | 0.53 | 13505 | 13587 | 82 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13505.00 t/13587.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 8.50, ROP 153.75, Diff 1050.00, Temp 284.00
09/25/2021 | 12:15 | 12:19 | 0.07 | 13587 | 13587 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 12:19 | 12:32 | 0.22 | 13587 | 13602 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/13587.00 t/13602.00, TF 180.00G, w/WOB 35.00,Flow 350.00, Press 5050.00, Tq 8.50, ROP 69.23, Diff 1050.00, Temp 284.00
09/25/2021 | 12:32 | 13:00 | 0.47 | 13602 | 13682 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13602.00 t/13682.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 8.50, ROP 171.43, Diff 1050.00, Temp 284.00
09/25/2021 | 13:00 | 13:04 | 0.07 | 13682 | 13682 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 13:04 | 13:12 | 0.13 | 13682 | 13690 | 8 | LAT | 3: BHA 3 | 2J | Slide Drill f/13682.00 t/13690.00, TF 180.00G, w/WOB 35.00,Flow 350.00, Press 5050.00, Tq 8.50, ROP 60.00, Diff 1050.00, Temp 284.00
09/25/2021 | 13:12 | 13:40 | 0.47 | 13690 | 13777 | 87 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13690.00 t/13777.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 8.50, ROP 186.43, Diff 1050.00, Temp 284.00
09/25/2021 | 13:40 | 13:45 | 0.08 | 13777 | 13777 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 13:45 | 14:12 | 0.45 | 13777 | 13871 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13777.00 t/13871.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 208.89, Diff 1000.00, Temp 291.00
09/25/2021 | 14:12 | 14:16 | 0.07 | 13871 | 13871 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 14:16 | 14:29 | 0.22 | 13871 | 13886 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/13871.00 t/13886.00, TF 150.00G, w/WOB 40.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 69.23, Diff 1000.00, Temp 291.00
09/25/2021 | 14:29 | 14:58 | 0.48 | 13886 | 13965 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13886.00 t/13965.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 163.45, Diff 1000.00, Temp 293.00
09/25/2021 | 14:58 | 15:02 | 0.07 | 13965 | 13965 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 15:02 | 15:26 | 0.4 | 13965 | 14059 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/13965.00 t/14059.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 235.00, Diff 1000.00, Temp 293.00
09/25/2021 | 15:26 | 15:30 | 0.07 | 14059 | 14059 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 15:30 | 15:42 | 0.2 | 14059 | 14071 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/14059.00 t/14071.00, TF 150.00G, w/WOB 40.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 60.00, Diff 1000.00, Temp 293.00
09/25/2021 | 15:42 | 16:13 | 0.52 | 14071 | 14152 | 81 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14071.00 t/14152.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 156.77, Diff 1000.00, Temp 293.00
09/25/2021 | 16:13 | 16:17 | 0.07 | 14152 | 14152 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 16:17 | 16:41 | 0.4 | 14152 | 14247 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14152.00 t/14247.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 237.50, Diff 1000.00, Temp 293.00
09/25/2021 | 16:41 | 17:22 | 0.68 | 14247 | 14247 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 17:22 | 17:55 | 0.55 | 14247 | 14341 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14247.00 t/14341.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 170.91, Diff 1000.00, Temp 293.00
09/25/2021 | 17:55 | 17:58 | 0.05 | 14341 | 14341 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 17:58 | 18:24 | 0.43 | 14341 | 14410 | 69 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14341.00 t/14410.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 159.23, Diff 1000.00, Temp 293.00
09/25/2021 | 18:24 | 18:47 | 0.38 | 14410 | 14430 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/14410.00 t/14430.00, TF 90.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 52.17, Diff 1000.00, Temp 293.00
09/25/2021 | 18:47 | 18:51 | 0.07 | 14430 | 14436 | 6 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14430.00 t/14436.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 90.00, Diff 1000.00, Temp 293.00
09/25/2021 | 18:51 | 18:54 | 0.05 | 14436 | 14436 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 18:54 | 19:25 | 0.52 | 14436 | 14532 | 96 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14436.00 t/14532.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 185.81, Diff 1000.00, Temp 293.00
09/25/2021 | 19:25 | 19:28 | 0.05 | 14532 | 14532 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 19:28 | 19:57 | 0.48 | 14532 | 14626 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14532.00 t/14626.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 194.48, Diff 1000.00, Temp 293.00
09/25/2021 | 19:57 | 20:00 | 0.05 | 14626 | 14626 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 20:00 | 20:33 | 0.55 | 14626 | 14720 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14626.00 t/14720.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 170.91, Diff 1000.00, Temp 293.00
09/25/2021 | 20:33 | 20:36 | 0.05 | 14720 | 14720 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 20:36 | 21:08 | 0.53 | 14720 | 14815 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14720.00 t/14815.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 178.13, Diff 1000.00, Temp 293.00
09/25/2021 | 21:08 | 21:11 | 0.05 | 14815 | 14815 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 21:11 | 21:42 | 0.52 | 14815 | 14908 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14815.00 t/14908.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 180.00, Diff 1000.00, Temp 293.00
09/25/2021 | 21:42 | 21:45 | 0.05 | 14908 | 14908 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 21:45 | 21:49 | 0.07 | 14908 | 14916 | 8 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14908.00 t/14916.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 120.00, Diff 1000.00, Temp 293.00
09/25/2021 | 21:49 | 22:11 | 0.37 | 14916 | 14936 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/14916.00 t/14936.00, TF 70.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 54.55, Diff 1000.00, Temp 293.00
09/25/2021 | 22:11 | 22:32 | 0.35 | 14936 | 15002 | 66 | LAT | 3: BHA 3 | 2K | Rotary Drill f/14936.00 t/15002.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 188.57, Diff 1000.00, Temp 293.00
09/25/2021 | 22:32 | 22:35 | 0.05 | 15002 | 15002 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 22:35 | 22:40 | 0.08 | 15002 | 15007 | 5 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15002.00 t/15007.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 60.00, Diff 1000.00, Temp 293.00
09/25/2021 | 22:40 | 23:01 | 0.35 | 15007 | 15027 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/15007.00 t/15027.00, TF 90.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 57.14, Diff 1000.00, Temp 293.00
09/25/2021 | 23:01 | 23:27 | 0.43 | 15027 | 15097 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15027.00 t/15097.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 161.54, Diff 1000.00, Temp 293.00
09/25/2021 | 23:27 | 23:30 | 0.05 | 15097 | 15097 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/25/2021 | 23:30 | 24:00 | 0.5 | 15097 | 15183 | 86 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15097.00 t/15183.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 172.00, Diff 1000.00, Temp 293.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_26_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/26/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 88730
|  |  |  | 24hr Summary: |  | Drill lateral to 17,133 - POOH for Motor Failure
|  |  |  | 24hr Lookahead: |  | POOH - Change BHA - TIH - Drill ahead in lateral
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15183 |  | 10936 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 53 | PV: | 21
End Depth (Usft): |  | 17133 |  | 17133 |  | OD (in): |  | 10.75 |  | 300: | 32 | YP: | 11
Total Drilled (Usft): |  | 1950 |  | 6197 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 23 | Viscosity: | 55
Slide Drilled (Usft): |  | 115 |  | 760 | [5 empty] | 100: | 14 | Chlorides: | 53000
Rotary Drilled (Usft): |  | 1835 |  | 5437 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.30
Drlg/Circ Hrs: |  | 14.48 / 5.50 |  | 43.67 / 12.32 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 2.8 |  | 11.02 |  | SN: |  | 13635755 |  | 10s Gel: | 5 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 11.68 |  | 32.65 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.4 / 300.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 157.06 / 41.07 |  | 166.52 / 68.99 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 67.33 |  | Grade In: |  | New
% Slide: |  | 5.9 |  | 12.26 |  | Grade Out:
% Rotary: |  | 94.1 |  | 87.74 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 TS HS88 +.011 |  |  |  | 5.5 | 2 |  |  | 45.34 |  | 33.27 |  | 34.27
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.91
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 7.49 |  | 43.4
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 3.83 |  | 47.23
NMDC |  |  |  | 5.25 | 2.75 |  |  | 48.69 |  | 31.23 |  | 78.46
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.88 |  | 88.34
NMDC |  |  |  | 5.25 | 2.625 |  |  | 48.7 |  | 30.54 |  | 118.88
Filter Sub |  |  |  | 5 | 2.25 |  |  | 68.63 |  | 4.95 |  | 123.83
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.94 |  | 141.77
Crossover |  |  |  | 5.375 | 2.688 |  |  | 57.69 |  | 2.6 |  | 144.37
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 332.19
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 340.82
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2795.06
Agitator |  |  |  | 5.25 | 2.688 |  |  | 55.38 |  | 21.67 |  | 2816.73
2816.73
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 3.97 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15125 | 85.42 | 154.63 | 11430.24 | -3652.52 | 1110.14 | 0.36 |  | 84.96 | 3748.96 | 0.03 |  | 0.36 | 94
15220 | 87.47 | 154.37 | 11436.13 | -3738.1 | 1150.96 | 2.18 |  | -7.22 | 3843.7 | 2.16 |  | -0.27 | 95
15315 | 87.37 | 154.46 | 11440.41 | -3823.69 | 1191.95 | 0.14 |  | 138.04 | 3938.53 | -0.11 |  | 0.09 | 95
15410 | 84.62 | 152.31 | 11447.05 | -3908.41 | 1234.39 | 3.67 |  | -142.12 | 4033.26 | -2.89 |  | -2.26 | 95
15505 | 84.63 | 152.35 | 11455.95 | -3992.17 | 1278.31 | 0.04 |  | 0 | 4127.85 | 0.01 |  | 0.04 | 95
15599 | 85.28 | 151.78 | 11464.21 | -4074.9 | 1322.18 | 0.92 |  | -41.16 | 4221.48 | 0.69 |  | -0.61 | 94
15693 | 86.07 | 151.72 | 11471.3 | -4157.47 | 1366.54 | 0.84 |  | -4.33 | 4315.21 | 0.84 |  | -0.06 | 94
15788 | 87.6 | 151.72 | 11476.55 | -4241 | 1411.48 | 1.61 |  | 0 | 4410.06 | 1.61 |  | 0 | 95
15881 | 86.43 | 151.3 | 11481.39 | -4322.62 | 1455.78 | 1.34 |  | -160.29 | 4502.92 | -1.26 |  | -0.45 | 93
15976 | 86.51 | 151.15 | 11487.24 | -4405.73 | 1501.43 | 0.18 |  | -61.89 | 4597.73 | 0.08 |  | -0.16 | 95
16070 | 84.24 | 150.69 | 11494.82 | -4487.61 | 1546.96 | 2.46 |  | -168.6 | 4691.39 | -2.41 |  | -0.49 | 94
16165 | 84.66 | 153.88 | 11504.01 | -4571.31 | 1590.93 | 3.37 |  | 82.62 | 4785.93 | 0.44 |  | 3.36 | 95
16260 | 84.63 | 154.41 | 11512.87 | -4656.42 | 1632.18 | 0.56 |  | 93.28 | 4880.46 | -0.03 |  | 0.56 | 95
16355 | 86.67 | 155.9 | 11520.08 | -4742.38 | 1671.97 | 2.66 |  | 36.12 | 4975.06 | 2.15 |  | 1.57 | 95
16448 | 88.64 | 155.92 | 11523.88 | -4827.2 | 1709.9 | 2.12 |  | 0.58 | 5067.78 | 2.12 |  | 0.02 | 93
16542 | 86.17 | 154.58 | 11528.14 | -4912.47 | 1749.21 | 2.99 |  | -151.57 | 5161.55 | -2.63 |  | -1.43 | 94
16635 | 86.65 | 154.39 | 11533.96 | -4996.24 | 1789.19 | 0.55 |  | -21.56 | 5254.29 | 0.52 |  | -0.2 | 93
16729 | 87.35 | 154.12 | 11538.88 | -5080.79 | 1829.96 | 0.8 |  | -21.07 | 5348.1 | 0.74 |  | -0.29 | 94
16824 | 88.15 | 153.99 | 11542.61 | -5166.15 | 1871.49 | 0.85 |  | -9.23 | 5442.98 | 0.84 |  | -0.14 | 95
16919 | 86.59 | 152.77 | 11546.97 | -5250.98 | 1914.01 | 2.08 |  | -142.03 | 5537.86 | -1.64 |  | -1.28 | 95
17014 | 87.42 | 152.17 | 11551.94 | -5335.11 | 1957.86 | 1.08 |  | -35.84 | 5632.72 | 0.87 |  | -0.63 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 134.64 | 28 | 80 | 392 | 350 | 5114.29 | 4157.14 | 140 | 250.71 | 216.86 | 177.14 | 10.27 | 3
Run | 141.92 | 25.64 | 74.59 | 385 | 349.07 | 4913.08 | 3972.9 | 140 | 236.26 | 220.05 | 185.79 | 8.74 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 09/26/2021 |  | 5 |  | 100 |  | 4 | 400
Dir & MWD /Gamma |  |  |  |  | 09/26/2021 |  | 4 |  | 6850 |  | 1 | 6850
Multi Rig Discount |  |  |  |  | 09/26/2021 |  | 20 |  | -400 |  | 1 | -400
5.5 Premium Motor Reline |  |  |  |  | 09/26/2021 |  | 9 |  | 9000
Real Time Survey Management |  |  |  |  | 09/26/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/26/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/26/2021 | 00:00 | 00:03 | 0.05 | 15183 | 15191 | 8 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15183.00 t/15191.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 160.00, Diff 1000.00, Temp 300.00
09/26/2021 | 00:03 | 00:06 | 0.05 | 15191 | 15191 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 00:06 | 00:11 | 0.08 | 15191 | 15199 | 8 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15191.00 t/15199.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 96.00, Diff 1000.00, Temp 300.00
09/26/2021 | 00:11 | 00:30 | 0.32 | 15199 | 15209 | 10 | LAT | 3: BHA 3 | 2J | Slide Drill f/15199.00 t/15209.00, TF 0.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 31.58, Diff 1000.00, Temp 300.00
09/26/2021 | 00:30 | 00:56 | 0.43 | 15209 | 15286 | 77 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15209.00 t/15286.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 177.69, Diff 1000.00, Temp 300.00
09/26/2021 | 00:56 | 01:00 | 0.07 | 15286 | 15286 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 01:00 | 01:05 | 0.08 | 15286 | 15295 | 9 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15286.00 t/15295.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 108.00, Diff 1000.00, Temp 300.00
09/26/2021 | 01:05 | 01:17 | 0.2 | 15295 | 15302 | 7 | LAT | 3: BHA 3 | 2J | Slide Drill f/15295.00 t/15302.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 35.00, Diff 1000.00, Temp 300.00
09/26/2021 | 01:17 | 01:42 | 0.42 | 15302 | 15381 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15302.00 t/15381.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 189.60, Diff 1000.00, Temp 300.00
09/26/2021 | 01:42 | 01:46 | 0.07 | 15381 | 15381 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 01:46 | 01:50 | 0.07 | 15381 | 15387 | 6 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15381.00 t/15387.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 90.00, Diff 1000.00, Temp 302.00
09/26/2021 | 01:50 | 02:05 | 0.25 | 15387 | 15399 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/15387.00 t/15399.00, TF 180.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 48.00, Diff 1000.00, Temp 302.00
09/26/2021 | 02:05 | 02:30 | 0.42 | 15399 | 15476 | 77 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15399.00 t/15476.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 184.80, Diff 1000.00, Temp 302.00
09/26/2021 | 02:30 | 02:34 | 0.07 | 15476 | 15476 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 02:34 | 03:05 | 0.52 | 15476 | 15571 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15476.00 t/15571.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 183.87, Diff 1000.00, Temp 306.00
09/26/2021 | 03:05 | 03:09 | 0.07 | 15571 | 15571 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 03:09 | 03:39 | 0.5 | 15571 | 15665 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15571.00 t/15665.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 188.00, Diff 1000.00, Temp 306.00
09/26/2021 | 03:39 | 03:43 | 0.07 | 15665 | 15665 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 03:43 | 04:18 | 0.58 | 15665 | 15759 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15665.00 t/15759.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 161.14, Diff 1000.00, Temp 306.00
09/26/2021 | 04:18 | 04:21 | 0.05 | 15759 | 15759 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 04:21 | 04:53 | 0.53 | 15759 | 15854 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15759.00 t/15854.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 178.12, Diff 1000.00, Temp 306.00
09/26/2021 | 04:53 | 04:57 | 0.07 | 15854 | 15854 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 04:57 | 05:03 | 0.1 | 15854 | 15865 | 11 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15854.00 t/15865.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 110.00, Diff 1000.00, Temp 307.00
09/26/2021 | 05:03 | 05:17 | 0.23 | 15865 | 15877 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/15865.00 t/15877.00, TF 150.00G, w/WOB 25.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 51.43, Diff 1000.00, Temp 307.00
09/26/2021 | 05:17 | 05:42 | 0.42 | 15877 | 15947 | 70 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15877.00 t/15947.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 168.00, Diff 1000.00, Temp 307.00
09/26/2021 | 05:42 | 05:46 | 0.07 | 15947 | 15947 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 05:46 | 06:18 | 0.53 | 15947 | 16042 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/15947.00 t/16042.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 178.13, Diff 1000.00, Temp 309.00
09/26/2021 | 06:18 | 06:22 | 0.07 | 16042 | 16042 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 06:22 | 06:40 | 0.3 | 16042 | 16057 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/16042.00 t/16057.00, TF 130.00G, w/WOB 50.00,Flow 350.00, Press 5050.00, Tq 9.00, ROP 50.00, Diff 1000.00, Temp 309.00
09/26/2021 | 06:40 | 07:15 | 0.58 | 16057 | 16136 | 79 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16057.00 t/16136.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5050.00, Tq 9.00, ROP 135.43, Diff 1000.00, Temp 307.00
09/26/2021 | 07:15 | 07:19 | 0.07 | 16136 | 16136 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 07:19 | 07:39 | 0.33 | 16136 | 16156 | 20 | LAT | 3: BHA 3 | 2J | Slide Drill f/16136.00 t/16156.00, TF 65.00G, w/WOB 50.00,Flow 350.00, Press 5200.00, Tq 9.00, ROP 60.00, Diff 900.00, Temp 307.00
09/26/2021 | 07:39 | 08:12 | 0.55 | 16156 | 16231 | 75 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16156.00 t/16231.00, w/WOB 25.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 136.36, Diff 900.00, Temp 309.00
09/26/2021 | 08:12 | 08:16 | 0.07 | 16231 | 16231 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 08:16 | 08:51 | 0.58 | 16231 | 16326 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16231.00 t/16326.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 162.86, Diff 900.00, Temp 309.00
09/26/2021 | 08:51 | 08:55 | 0.07 | 16326 | 16326 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 08:55 | 09:23 | 0.47 | 16326 | 16341 | 15 | LAT | 3: BHA 3 | 2J | Slide Drill f/16326.00 t/16341.00, TF 30.00G, w/WOB 50.00,Flow 350.00, Press 5200.00, Tq 12.00, ROP 32.14, Diff 900.00, Temp 309.00
09/26/2021 | 09:23 | 09:52 | 0.48 | 16341 | 16421 | 80 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16341.00 t/16421.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 165.52, Diff 900.00, Temp 309.00
09/26/2021 | 09:52 | 09:56 | 0.07 | 16421 | 16421 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 09:56 | 10:31 | 0.58 | 16421 | 16514 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16421.00 t/16514.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 159.43, Diff 900.00, Temp 311.00
09/26/2021 | 10:31 | 10:35 | 0.07 | 16514 | 16514 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 10:35 | 10:52 | 0.28 | 16514 | 16526 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/16514.00 t/16526.00, TF 180.00G, w/WOB 50.00,Flow 350.00, Press 5200.00, Tq 12.00, ROP 42.35, Diff 900.00, Temp 309.00
09/26/2021 | 10:52 | 11:26 | 0.57 | 16526 | 16608 | 82 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16526.00 t/16608.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 144.71, Diff 900.00, Temp 309.00
09/26/2021 | 11:26 | 11:30 | 0.07 | 16608 | 16608 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 11:30 | 12:02 | 0.53 | 16608 | 16701 | 93 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16608.00 t/16701.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 174.38, Diff 900.00, Temp 313.00
09/26/2021 | 12:02 | 12:06 | 0.07 | 16701 | 16701 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 12:06 | 12:44 | 0.63 | 16701 | 16795 | 94 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16701.00 t/16795.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 148.42, Diff 900.00, Temp 313.00
09/26/2021 | 12:44 | 12:48 | 0.07 | 16795 | 16795 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 12:48 | 13:27 | 0.65 | 16795 | 16890 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16795.00 t/16890.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 146.15, Diff 900.00, Temp 313.00
09/26/2021 | 13:27 | 13:31 | 0.07 | 16890 | 16890 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 13:31 | 13:56 | 0.42 | 16890 | 16902 | 12 | LAT | 3: BHA 3 | 2J | Slide Drill f/16890.00 t/16902.00, TF 180.00G, w/WOB 50.00,Flow 350.00, Press 5200.00, Tq 12.00, ROP 28.80, Diff 900.00, Temp 311.00
09/26/2021 | 13:56 | 14:37 | 0.68 | 16902 | 16985 | 83 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16902.00 t/16985.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 121.46, Diff 900.00, Temp 311.00
09/26/2021 | 14:37 | 14:41 | 0.07 | 16985 | 16985 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 14:41 | 15:22 | 0.68 | 16985 | 17080 | 95 | LAT | 3: BHA 3 | 2K | Rotary Drill f/16985.00 t/17080.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 139.02, Diff 900.00, Temp 311.00
09/26/2021 | 15:22 | 15:26 | 0.07 | 17080 | 17080 | 0 | LAT | 3: BHA 3 | 5A | Survey & Connection
09/26/2021 | 15:26 | 15:51 | 0.42 | 17080 | 17133 | 53 | LAT | 3: BHA 3 | 2K | Rotary Drill f/17080.00 t/17133.00, w/WOB 23.00,Flow 350.00, RPM 80.00, Press 5200.00, Tq 12.00, ROP 127.20, Diff 900.00
09/26/2021 | 15:51 | 18:07 | 2.27 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 5A | Circulate to POOH for Motor Failure
09/26/2021 | 18:07 | 21:39 | 3.53 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 6B | POOH to Casing Shoe
09/26/2021 | 21:39 | 22:38 | 0.98 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 5A | Circulate at Casing Shoe
09/26/2021 | 22:38 | 23:07 | 0.48 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 6I | Flow Check
09/26/2021 | 23:07 | 24:00 | 0.88 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 5A | Spot Mud Cap
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_27_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/27/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 18450 |  |  | Well Cost($): |  | 107180
|  |  |  | 24hr Summary: |  | POOH - Change BHA - TIH - Drill Ahead in Lateral
|  |  |  | 24hr Lookahead: |  | Drill Ahead in Lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17133 |  | 17133 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 53 | PV: | 21
End Depth (Usft): |  | 17334 |  | 17334 |  | OD (in): |  | 10.75 |  | 300: | 32 | YP: | 11
Total Drilled (Usft): |  | 201 |  | 201 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 23 | Viscosity: | 55
Slide Drilled (Usft): | [9 empty] | 100: | 14 | Chlorides: | 53000
Rotary Drilled (Usft): |  | 201 |  | 201 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.30
Drlg/Circ Hrs: |  | 1.15 / 3.60 |  | 1.15 / 3.60 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: | [5 empty] | SN: |  | 13635755 |  | 10s Gel: | 5 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 1.15 |  | 1.15 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.4 / 300.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 174.78 / 0.00 |  | 174.78 / 0.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 14.5 |  | 14.5 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: |  | 100 |  | 100 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 11.7 2.12 TS HS88 +.011 |  |  |  | 5.5 | 2 |  |  | 45.34 |  | 33.27 |  | 34.27
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 35.91
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 7.49 |  | 43.4
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 3.83 |  | 47.23
NMDC |  |  |  | 5.25 | 2.75 |  |  | 48.69 |  | 31.23 |  | 78.46
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.88 |  | 88.34
NMDC |  |  |  | 5.25 | 2.625 |  |  | 48.7 |  | 30.54 |  | 118.88
Filter Sub |  |  |  | 5 | 2.25 |  |  | 68.63 |  | 4.95 |  | 123.83
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.94 |  | 141.77
Crossover |  |  |  | 5.375 | 2.688 |  |  | 57.69 |  | 2.6 |  | 144.37
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 332.19
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 340.82
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2795.06
Agitator |  |  |  | 5.25 | 2.688 |  |  | 55.38 |  | 21.67 |  | 2816.73
2816.73
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250003 |  | PDCI |  | 6/7 11.7 |  | 6/7 | 3.97 |  | 2.12 |  | 0.89 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17107 | 86.63 | 152.05 | 11556.76 | -5417.2 | 2001.31 | 0.86 |  | -171.38 | 5725.6 | -0.85 |  | -0.13 | 93
17203 | 87.35 | 152.4 | 11561.8 | -5502.02 | 2045.98 | 0.83 |  | 25.9 | 5821.46 | 0.75 |  | 0.36 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30 | 80 | 323 | 356.67 | 5733.33 | 4900 | 140 | 250 | 200 | 190 | 17.8 | 3
Run | 141.92 | 30 | 80 | 323 | 356.67 | 5733.33 | 4900 | 140 | 250 | 200 | 190 | 17.8 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
5.5 Premium Motor Reline |  |  |  |  | 09/27/2021 |  | 9 |  | 9000 |  | 1 | 9000
Real Time Survey Management |  |  |  |  | 09/27/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/27/2021 |  | 14 |  | 2000 |  | 1 | 2000
Perdiem |  |  |  |  | 09/27/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 09/27/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/27/2021 |  | 4 |  | 6850 |  | 1 | 6850
Total | [11 empty] | 18450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/27/2021 | 00:00 | 06:30 | 6.5 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 6B | POOH
09/27/2021 | 06:30 | 08:00 | 1.5 | 17133 | 17133 | 0 | LAT | 3: BHA 3 | 6P | Lay Down BHA #3
09/27/2021 | 08:00 | 09:30 | 1.5 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 6O | Pick Up BHA #4
09/27/2021 | 09:30 | 17:00 | 7.5 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 6A | TIH t/ 11,037
09/27/2021 | 17:00 | 19:00 | 2 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 5D | Circulate Mud Cap Out of Hole
09/27/2021 | 19:00 | 20:30 | 1.5 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 6A | TIH t/ 14,930
09/27/2021 | 20:30 | 21:30 | 1 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 5A | Circulate Bottoms Up
09/27/2021 | 21:30 | 22:15 | 0.75 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 6A | TIH t/ 16,890
09/27/2021 | 22:15 | 22:43 | 0.47 | 17133 | 17133 | 0 | LAT | 4: BHA 4 | 3C | Wash & Ream to Bottom
09/27/2021 | 22:43 | 22:58 | 0.25 | 17133 | 17173 | 40 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17133.00 t/17173.00, w/WOB 30.00,Flow 350.00, RPM 80.00, Press 5600.00, Tq 17.80, ROP 160.00, Diff 800.00, Temp 311.00
09/27/2021 | 22:58 | 23:01 | 0.05 | 17173 | 17173 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/27/2021 | 23:01 | 23:35 | 0.57 | 17173 | 17269 | 96 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17173.00 t/17269.00, w/WOB 30.00,Flow 350.00, RPM 80.00, Press 5600.00, Tq 17.80, ROP 169.41, Diff 800.00, Temp 311.00
09/27/2021 | 23:35 | 23:40 | 0.08 | 17269 | 17269 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/27/2021 | 23:40 | 24:00 | 0.33 | 17269 | 17334 | 65 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17269.00 t/17334.00, w/WOB 30.00,Flow 370, RPM 80.00, Press 6000, Tq 17.80, ROP 195.00, Diff 900.00, Temp 311.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_28_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 116630
|  |  |  | 24hr Summary: |  | Drilling Lateral
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17334 |  | 17133 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 53 | PV: | 21
End Depth (Usft): |  | 19389 |  | 19389 |  | OD (in): |  | 10.75 |  | 300: | 32 | YP: | 11
Total Drilled (Usft): |  | 2055 |  | 2256 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 23 | Viscosity: | 55
Slide Drilled (Usft): |  | 243 |  | 243 | [5 empty] | 100: | 14 | Chlorides: | 53000
Rotary Drilled (Usft): |  | 1812 |  | 2013 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.30
Drlg/Circ Hrs: |  | 21.55 / 2.45 |  | 22.70 / 6.05 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 8.2 |  | 8.2 |  | SN: |  | 13601237 |  | 10s Gel: | 5 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 13.35 |  | 14.5 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.4 / 300.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  | 135.73 / 29.63 |  | 138.83 / 29.63 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 38.5 |  | Grade In: |  | New
% Slide: |  | 11.82 |  | 10.77 |  | Grade Out: |  | 0-1-WT-A-N-I-NO-TD
% Rotary: |  | 88.18 |  | 89.23 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 2.64
6/7 8.8 2.12 TS HS88 +.022 |  |  |  | 5.5 | 2 |  |  | 45.25 |  | 33.15 |  | 35.79
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 7.49 |  | 43.28
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 3.83 |  | 47.11
NMDC |  |  |  | 5.25 | 2.75 |  |  | 48.69 |  | 31.23 |  | 78.34
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.88 |  | 88.22
NMDC |  |  |  | 5.25 | 2.625 |  |  | 48.7 |  | 30.54 |  | 118.76
Filter Sub |  |  |  | 5 | 2.25 |  |  | 68.63 |  | 4.95 |  | 123.71
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.94 |  | 141.65
Crossover |  |  |  | 5.375 | 2.688 |  |  | 57.69 |  | 2.6 |  | 144.25
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 332.07
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 340.7
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2794.94
Agitator |  |  |  | 5.35 | 2.688 |  |  | 55.38 |  | 21.97 |  | 2816.91
2816.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250015 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.56 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17298 | 86.99 | 152.06 | 11566.49 | -5585.98 | 2090.19 | 0.52 |  | -136.68 | 5916.35 | -0.38 |  | -0.36 | 95
17392 | 86.73 | 151.45 | 11571.64 | -5668.66 | 2134.61 | 0.7 |  | -113.13 | 6010.2 | -0.28 |  | -0.65 | 94
17487 | 86.91 | 150.9 | 11576.91 | -5751.76 | 2180.34 | 0.61 |  | -71.87 | 6105.04 | 0.19 |  | -0.58 | 95
17582 | 85.04 | 152.93 | 11583.58 | -5835.36 | 2224.95 | 2.9 |  | 132.79 | 6199.8 | -1.97 |  | 2.14 | 95
17676 | 83.87 | 152.5 | 11592.66 | -5918.51 | 2267.84 | 1.33 |  | -159.93 | 6293.35 | -1.24 |  | -0.46 | 94
17771 | 84.76 | 154.33 | 11602.07 | -6003.04 | 2310.14 | 2.13 |  | 64.05 | 6387.86 | 0.94 |  | 1.93 | 95
17866 | 86.96 | 155.09 | 11608.93 | -6088.7 | 2350.62 | 2.45 |  | 19.04 | 6482.51 | 2.32 |  | 0.8 | 95
17961 | 86.49 | 154.59 | 11614.36 | -6174.55 | 2390.94 | 0.72 |  | -133.29 | 6577.26 | -0.49 |  | -0.53 | 95
18055 | 86.54 | 154.81 | 11620.07 | -6259.38 | 2431.04 | 0.24 |  | 77.18 | 6671 | 0.05 |  | 0.23 | 94
18151 | 86.73 | 155.59 | 11625.71 | -6346.37 | 2471.23 | 0.83 |  | 76.31 | 6766.7 | 0.2 |  | 0.81 | 96
18246 | 86.42 | 153.74 | 11631.39 | -6432.08 | 2511.81 | 1.97 |  | -99.58 | 6861.44 | -0.33 |  | -1.95 | 95
18340 | 86.75 | 155.13 | 11636.98 | -6516.72 | 2552.3 | 1.52 |  | 76.66 | 6955.2 | 0.35 |  | 1.48 | 94
18435 | 86.91 | 150.49 | 11642.24 | -6601.07 | 2595.63 | 4.88 |  | -88.15 | 7050.02 | 0.17 |  | -4.88 | 95
18529 | 87.06 | 146.36 | 11647.19 | -6681.03 | 2644.77 | 4.39 |  | -88.03 | 7143.67 | 0.16 |  | -4.39 | 94
18622 | 86.64 | 144.35 | 11652.3 | -6757.42 | 2697.56 | 2.2 |  | -101.87 | 7235.86 | -0.45 |  | -2.16 | 93
18718 | 85.54 | 146.87 | 11658.85 | -6836.45 | 2751.65 | 2.86 |  | 113.71 | 7330.99 | -1.15 |  | 2.63 | 96
18810 | 85.84 | 151.34 | 11665.76 | -6915.15 | 2798.75 | 4.86 |  | 86.32 | 7422.57 | 0.33 |  | 4.86 | 92
18904 | 86.26 | 155.74 | 11672.24 | -6999.08 | 2840.52 | 4.69 |  | 84.69 | 7516.3 | 0.45 |  | 4.68 | 94
18998 | 87.74 | 157.79 | 11677.16 | -7085.33 | 2877.55 | 2.69 |  | 54.19 | 7609.86 | 1.57 |  | 2.18 | 94
19093 | 89.38 | 150.69 | 11679.55 | -7170.81 | 2918.8 | 7.67 |  | -77.1 | 7704.71 | 1.73 |  | -7.47 | 95
19188 | 88.94 | 143.77 | 11680.95 | -7250.63 | 2970.18 | 7.3 |  | -93.68 | 7799.28 | -0.46 |  | -7.28 | 95
19283 | 90.12 | 142.71 | 11681.73 | -7326.73 | 3027.03 | 1.67 |  | -41.94 | 7893.11 | 1.24 |  | -1.12 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30 | 80 | 323 | 356.67 | 5733.33 | 4900 | 140 | 250 | 200 | 190 | 17.8 | 3
Run | 174.78 | 30 | 80 | 323 | 356.67 | 5733.33 | 4900 | 140 | 250 | 200 | 190 | 17.8 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 09/28/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 09/28/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/28/2021 |  | 4 |  | 6850 |  | 1 | 6850
Real Time Survey Management |  |  |  |  | 09/28/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/28/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/28/2021 | 00:00 | 00:10 | 0.17 | 17334 | 17364 | 30 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17334.00 t/17364.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 180.00, Diff 900.00, Temp 311.00
09/28/2021 | 00:10 | 00:14 | 0.07 | 17364 | 17364 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 00:14 | 00:41 | 0.45 | 17364 | 17458 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17364.00 t/17458.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 208.89, Diff 900.00, Temp 311.00
09/28/2021 | 00:41 | 00:45 | 0.07 | 17458 | 17458 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 00:45 | 01:17 | 0.53 | 17458 | 17553 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17458.00 t/17553.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 178.13, Diff 900.00, Temp 311.00
09/28/2021 | 01:17 | 01:22 | 0.08 | 17553 | 17553 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 01:22 | 01:27 | 0.08 | 17553 | 17560 | 7 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17553.00 t/17560.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 84.00, Diff 900.00, Temp 320.00
09/28/2021 | 01:27 | 01:52 | 0.42 | 17560 | 17578 | 18 | LAT | 4: BHA 4 | 2J | Slide Drill f/17560.00 t/17578.00, TF 120.00G, w/WOB 55.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 43.20, Diff 900.00, Temp 320.00
09/28/2021 | 01:52 | 02:15 | 0.38 | 17578 | 17648 | 70 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17578.00 t/17648.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 182.61, Diff 900.00, Temp 320.00
09/28/2021 | 02:15 | 02:20 | 0.08 | 17648 | 17648 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 02:20 | 02:51 | 0.52 | 17648 | 17742 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17648.00 t/17742.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 181.94, Diff 900.00, Temp 320.00
09/28/2021 | 02:51 | 02:55 | 0.07 | 17742 | 17742 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 02:55 | 03:00 | 0.08 | 17742 | 17753 | 11 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17742.00 t/17753.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 132.00, Diff 900.00, Temp 320.00
09/28/2021 | 03:00 | 03:28 | 0.47 | 17753 | 17770 | 17 | LAT | 4: BHA 4 | 2J | Slide Drill f/17753.00 t/17770.00, TF 30.00G, w/WOB 30.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 36.43, Diff 900.00, Temp 320.00
09/28/2021 | 03:28 | 03:51 | 0.38 | 17770 | 17837 | 67 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17770.00 t/17837.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 174.78, Diff 900.00, Temp 325.00
09/28/2021 | 03:51 | 03:55 | 0.07 | 17837 | 17837 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 03:55 | 04:00 | 0.08 | 17837 | 17844 | 7 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17837.00 t/17844.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 84.00, Diff 900.00, Temp 325.00
09/28/2021 | 04:00 | 04:25 | 0.42 | 17844 | 17859 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/17844.00 t/17859.00, TF 0.00G, w/WOB 30.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 36.00, Diff 900.00, Temp 325.00
09/28/2021 | 04:25 | 04:50 | 0.42 | 17859 | 17932 | 73 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17859.00 t/17932.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 175.20, Diff 900.00, Temp 327.00
09/28/2021 | 04:50 | 04:55 | 0.08 | 17932 | 17932 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 04:55 | 05:31 | 0.6 | 17932 | 18027 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/17932.00 t/18027.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 158.33, Diff 900.00, Temp 327.00
09/28/2021 | 05:31 | 05:35 | 0.07 | 18027 | 18027 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 05:35 | 06:11 | 0.6 | 18027 | 18121 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18027.00 t/18121.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 156.67, Diff 900.00, Temp 327.00
09/28/2021 | 06:11 | 06:15 | 0.07 | 18121 | 18121 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 06:15 | 06:53 | 0.63 | 18121 | 18217 | 96 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18121.00 t/18217.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 151.58, Diff 900.00, Temp 327.00
09/28/2021 | 06:53 | 06:57 | 0.07 | 18217 | 18217 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 06:57 | 07:35 | 0.63 | 18217 | 18312 | 95 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18217.00 t/18312.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 150.00, Diff 900.00, Temp 327.00
09/28/2021 | 07:35 | 07:39 | 0.07 | 18312 | 18312 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 07:39 | 08:19 | 0.67 | 18312 | 18406 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18312.00 t/18406.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 141.00, Diff 900.00, Temp 327.00
09/28/2021 | 08:19 | 08:23 | 0.07 | 18406 | 18406 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 08:23 | 09:01 | 0.63 | 18406 | 18431 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/18406.00 t/18431.00, TF -90.00G, w/WOB 55.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 39.47, Diff 900.00, Temp 327.00
09/28/2021 | 09:01 | 09:39 | 0.63 | 18431 | 18501 | 70 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18431.00 t/18501.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 110.53, Diff 900.00, Temp 327.00
09/28/2021 | 09:39 | 09:43 | 0.07 | 18501 | 18501 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 09:43 | 09:55 | 0.2 | 18501 | 18520 | 19 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18501.00 t/18520.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 95.00, Diff 900.00, Temp 327.00
09/28/2021 | 09:55 | 10:19 | 0.4 | 18520 | 18530 | 10 | LAT | 4: BHA 4 | 2J | Slide Drill f/18520.00 t/18530.00, TF -90.00G, w/WOB 55.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 25.00, Diff 900.00, Temp 327.00
09/28/2021 | 10:19 | 10:50 | 0.52 | 18530 | 18595 | 65 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18530.00 t/18595.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 125.81, Diff 900.00, Temp 327.00
09/28/2021 | 10:50 | 10:54 | 0.07 | 18595 | 18595 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 10:54 | 11:33 | 0.65 | 18595 | 18688 | 93 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18595.00 t/18688.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 143.08, Diff 900.00, Temp 329.00
09/28/2021 | 11:33 | 11:37 | 0.07 | 18688 | 18688 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 11:37 | 12:17 | 0.67 | 18688 | 18708 | 20 | LAT | 4: BHA 4 | 2J | Slide Drill f/18688.00 t/18708.00, TF 90.00G, w/WOB 50.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 30.00, Diff 900.00, Temp 327.00
09/28/2021 | 12:17 | 12:59 | 0.7 | 18708 | 18784 | 76 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18708.00 t/18784.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 108.57, Diff 900.00, Temp 327.00
09/28/2021 | 12:59 | 13:03 | 0.07 | 18784 | 18784 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 13:03 | 13:33 | 0.5 | 18784 | 18799 | 15 | LAT | 4: BHA 4 | 2J | Slide Drill f/18784.00 t/18799.00, TF 60.00G, w/WOB 50.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 30.00, Diff 900.00, Temp 327.00
09/28/2021 | 13:33 | 14:16 | 0.72 | 18799 | 18876 | 77 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18799.00 t/18876.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 107.44, Diff 900.00, Temp 329.00
09/28/2021 | 14:16 | 14:20 | 0.07 | 18876 | 18876 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 14:20 | 15:01 | 0.68 | 18876 | 18970 | 94 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18876.00 t/18970.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 137.56, Diff 900.00, Temp 329.00
09/28/2021 | 15:01 | 15:05 | 0.07 | 18970 | 18970 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 15:05 | 15:45 | 0.67 | 18970 | 18990 | 20 | LAT | 4: BHA 4 | 2J | Slide Drill f/18970.00 t/18990.00, TF -90.00G, w/WOB 40.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 30.00, Diff 900.00, Temp 329.00
09/28/2021 | 15:45 | 16:09 | 0.4 | 18990 | 19028 | 38 | LAT | 4: BHA 4 | 2K | Rotary Drill f/18990.00 t/19028.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 95.00, Diff 900.00, Temp 327.00
09/28/2021 | 16:09 | 16:48 | 0.65 | 19028 | 19041 | 13 | LAT | 4: BHA 4 | 2J | Slide Drill f/19028.00 t/19041.00, TF -90.00G, w/WOB 40.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 20.00, Diff 900.00, Temp 327.00
09/28/2021 | 16:48 | 17:01 | 0.22 | 19041 | 19064 | 23 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19041.00 t/19064.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 106.15, Diff 900.00, Temp 327.00
09/28/2021 | 17:01 | 17:10 | 0.15 | 19064 | 19064 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 17:10 | 18:02 | 0.87 | 19064 | 19089 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/19064.00 t/19089.00, TF -90.00G, w/WOB 40.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 28.85, Diff 900.00, Temp 324.00
09/28/2021 | 18:02 | 18:14 | 0.2 | 19089 | 19113 | 24 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19089.00 t/19113.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 120.00, Diff 900.00, Temp 324.00
09/28/2021 | 18:14 | 19:05 | 0.85 | 19113 | 19138 | 25 | LAT | 4: BHA 4 | 2J | Slide Drill f/19113.00 t/19138.00, TF -90.00G, w/WOB 30.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 29.41, Diff 900.00, Temp 324.00
09/28/2021 | 19:05 | 19:24 | 0.32 | 19138 | 19159 | 21 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19138.00 t/19159.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 66.32, Diff 900.00, Temp 324.00
09/28/2021 | 19:24 | 19:29 | 0.08 | 19159 | 19159 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 19:29 | 19:33 | 0.07 | 19159 | 19164 | 5 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19159.00 t/19164.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 75.00, Diff 900.00, Temp 324.00
09/28/2021 | 19:33 | 20:29 | 0.93 | 19164 | 19188 | 24 | LAT | 4: BHA 4 | 2J | Slide Drill f/19164.00 t/19188.00, TF -110.00G, w/WOB 30.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 25.71, Diff 900.00, Temp 324.00
09/28/2021 | 20:29 | 21:06 | 0.62 | 19188 | 19254 | 66 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19188.00 t/19254.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 107.03, Diff 900.00, Temp 324.00
09/28/2021 | 21:06 | 21:12 | 0.1 | 19254 | 19254 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 21:12 | 21:46 | 0.57 | 19254 | 19307 | 53 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19254.00 t/19307.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 93.53, Diff 900.00, Temp 324.00
09/28/2021 | 21:46 | 22:30 | 0.73 | 19307 | 19323 | 16 | LAT | 4: BHA 4 | 2J | Slide Drill f/19307.00 t/19323.00, TF -110.00G, w/WOB 30.00,Flow 370.00, Press 6000.00, Tq 17.80, ROP 21.82, Diff 900.00, Temp 324.00
09/28/2021 | 22:30 | 22:46 | 0.27 | 19323 | 19349 | 26 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19323.00 t/19349.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 97.50, Diff 900.00, Temp 324.00
09/28/2021 | 22:46 | 22:50 | 0.07 | 19349 | 19349 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 22:50 | 23:12 | 0.37 | 19349 | 19389 | 40 | LAT | 4: BHA 4 | 2K | Rotary Drill f/19349.00 t/19389.00, w/WOB 30.00,Flow 370.00, RPM 80.00, Press 6000.00, Tq 17.80, ROP 109.09, Diff 900.00, Temp 324.00
09/28/2021 | 23:12 | 23:16 | 0.07 | 19389 | 19389 | 0 | LAT | 4: BHA 4 | 5A | Survey & Connection
09/28/2021 | 23:16 | 24:00 | 0.73 | 19389 | 19389 | 0 | LAT | 4: BHA 4 | 5A | Circulate @ TD
Well Seeker PRO 2.0.8.0 - Pro Directional

## 9_29_2021_DDR
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31163 / 20DD0220MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 13 |  |  | Well: |  | Redwood B1H
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Longitude: |  | 96° 37' 52.773" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 09/29/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 126080
|  |  |  | 24hr Summary: |  | POOH - Rig Down End of Job
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 19389 |  | 17133 |  | Csg Shoe MD(Usft): |  | 3482 |  | 600: | 53 | PV: | 21
End Depth (Usft): |  | 19389 |  | 19389 |  | OD (in): |  | 10.75 |  | 300: | 32 | YP: | 11
Total Drilled (Usft): |  |  |  | 2256 |  | Weight (ft/lbs): |  | 45.5 |  | 200: | 23 | Viscosity: | 55
Slide Drilled (Usft): |  |  |  | 243 | [5 empty] | 100: | 14 | Chlorides: | 53000
Rotary Drilled (Usft): |  |  |  | 2013 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.30
Drlg/Circ Hrs: |  |  |  | 22.70 / 6.05 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  |  |  | 8.2 |  | SN: |  | 13601237 |  | 10s Gel: | 5 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  |  |  | 14.5 |  | Bit # |  | 4 |  | PH / Temp(F) | 7.4 / 300.00 | Fluid Loss / Mud Type: | 10 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 138.83 / 29.63 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 17.5 |  | 56 |  | Grade In: |  | New
% Slide: |  |  |  | 10.77 |  | Grade Out: |  | 0-1-WT-A-N-I-NO-TD
% Rotary: |  |  |  | 89.23 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | NA |  | Bill Trey |  | Bobby Lewis
James Dyer |  | Marshall Adams |  | Jason Smetters | [7 empty] | Casey Gollan
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
BTI |  |  |  | 4.875 | 2.125 |  |  | 42.13 |  | 1.64 |  | 2.64
6/7 8.8 2.12 TS HS88 +.022 |  |  |  | 5.5 | 2 |  |  | 45.25 |  | 33.15 |  | 35.79
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 7.49 |  | 43.28
UBHO |  |  |  | 5.25 | 2.5 |  |  | 12.5 |  | 3.83 |  | 47.11
NMDC |  |  |  | 5.25 | 2.75 |  |  | 48.69 |  | 31.23 |  | 78.34
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.88 |  | 88.22
NMDC |  |  |  | 5.25 | 2.625 |  |  | 48.7 |  | 30.54 |  | 118.76
Filter Sub |  |  |  | 5 | 2.25 |  |  | 68.63 |  | 4.95 |  | 123.71
Tomax |  |  |  | 5.25 | 2.5 |  |  | 54.67 |  | 17.94 |  | 141.65
Crossover |  |  |  | 5.375 | 2.688 |  |  | 57.69 |  | 2.6 |  | 144.25
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 332.07
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 46.35 |  | 8.63 |  | 340.7
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 17.84 |  | 2454.24 |  | 2794.94
Agitator |  |  |  | 5.35 | 2.688 |  |  | 55.38 |  | 21.97 |  | 2816.91
2816.91
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250015 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 3.56 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 30 | 80 | 323 | 356.67 | 5733.33 | 4900 | 140 | 250 | 200 | 190 | 17.8 | 3
Run | 99.38 | 30 | 80 | 323 | 356.67 | 5733.33 | 4900 | 140 | 250 | 200 | 190 | 17.8 | 3
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
2 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
3 | Triplex |  |  | 95 | 12 | 5.25 | 5692 |  | 5000 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 09/29/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 09/29/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 09/29/2021 |  | 4 |  | 6850 |  | 1 | 6850
Real Time Survey Management |  |  |  |  | 09/29/2021 |  | 10 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 09/29/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
09/29/2021 | 00:00 | 16:00 | 16 | 19389 | 19389 | 0 | LAT | 4: BHA 4 | 6B | POOH
09/29/2021 | 16:00 | 17:30 | 1.5 | 19389 | 19389 | 0 | LAT | 4: BHA 4 | 6P | Lay Down BHA
09/29/2021 | 17:30 | 24:00 | 6.5 | 19389 | 19389 | 0 | LAT |  | 1I | Rig Down for End of Job
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 392.08 (Usft)
Well: |  |  | Redwood B1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1125621 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/17/2021 | Depth In: |  | 108 | Total Drilled: |  | 3384.00 (Usft)
Date Out: |  |  | 07/18/2021 | Depth Out: |  | 3492 | Drilling / Circ Hours: |  | 6.62 / 3.72
Survey Offset: |  |  | 71
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 47424 | U616S | 13.5 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800017 | 7/8 5.9 1.50 Stab HPO -.011 NBS 13 | 8 |  | 8.000 / 1.85 | 6 5/8 REG / 6 5/8 REG |  | 37.43 | 38.93
| 3 | SD603251 | 13 Stab | 8.125 | 3 | 8.125 / 2.57 | 6 5/8 REG / 6 5/8 REG |  | 6.34 | 45.27
| 4 | SD55524 | NMPC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 8.58 | 53.85
| 5 | 775213 | UBHO Sub UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.66 | 57.51
| 6 | SD56120 | NMDC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 28.83 | 86.34
| 7 | SD55920 | NMDC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 28.99 | 115.33
| 8 | SD117248 | Crossover Sub | 6.75 | 2.875 | 6.750 / 1.44 | 4 1/2 IF / 6 5/8 REG |  | 2.13 | 117.46
| 9 |  | 9 Jts HWDP | 5 | 3 |  |  |  | 274.62 | 392.08
| 10 | [8 empty] | 392.08
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | U616S | 0-0- | 0-0-NO-A-X-I-NO-TD | 3384
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.50 Stab HPO -.011 NBS 13 |  |  | PDCI / 7/8 5.9 | 5.80 / 1.50 |  | 13 | 8.38 | 250 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 600 | 100 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.011
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7/8 5.9 1.50 Stab HPO -.011 NBS 13 | 13 |  | 0 |  |  | 3.82
3 |  |  | 13 Stab | 13 |  | 0 |  |  | 40.64

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2666.20 (Usft)
Well: |  |  | Redwood B1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 44.36 / 38.67 (klbs)
Job #: |  |  | LTX1125621 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 44.36 / 38.67 (klbs)
Date In: |  |  | 07/19/2021 | Depth In: |  | 3492 | Total Drilled: |  | 7444.00 (Usft)
Date Out: |  |  | 07/22/2021 | Depth Out: |  | 10936 | Drilling / Circ Hours: |  | 42.52 / 9.05
Survey Offset: |  |  | 63 | Gamma Offset: |  | 59
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 55156 | SPL613 | 9.875 | 2 |  | 6 5/8 REG | 125.00 / 0.19 / 0.19 | 1.5 | 1.5
| 2 | PPM800011 | 7/8 5.9 2.00 Slick HPO -.006 | 8 | 2 | 8.000 / 1.80 | 6 5/8 REG / 6 5/8 REG | 100.00 / 3.73 / 3.92 | 37.34 | 38.84
| 3 | SD55524 | NMPC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 1.29 / 5.21 | 8.58 | 47.42
| 4 | 775213 | UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 0.55 / 5.76 | 3.66 | 51.08
| 5 | SD56120 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 4.32 / 10.08 | 28.83 | 79.91
| 6 | SD55920 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 4.35 / 14.43 | 28.99 | 108.9
| 7 | SD103353 | Crossover Sub | 7.875 | 2.875 | 6.750 / 1.48 | 4 1/2 XH / 6 5/8 REG | 100.00 / 0.24 / 14.67 | 2.36 | 111.26
| 8 |  | 6.5 DC 6 Jts | 6.5 | 2.375 |  | 4 1/2 XH / 4 1/2 XH | 95.00 / 17.65 / 32.32 | 185.81 | 297.07
| 9 | SD103463 | Crossover Sub | 6.75 | 2.875 |  | 4 1/2 IF / 4 1/2 XH | 95.00 / 0.23 / 32.55 | 2.46 | 299.53
| 10 |  | HWDP 9 Jts | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF | 43.00 / 11.81 / 44.36 | 274.62 | 574.15
| 11 |  | DP 22 Stds | 5 | 3.5 |  | 4 1/2 IF / 4 1/2 IF | 19.60 / 40.52 / 84.88 | 2067.4 | 2641.55
| 12 | PG675-0022 | Agitator | 6.75 | 3.75 | 6.688 / 1.82 | 4 1/2 IF / 4 1/2 IF | 80.00 / 1.97 / 86.85 | 24.65 | 2666.2
| 13 | [8 empty] | 2666.2
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 1-1-BT-N-X-I-CT-TD | 7444
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.00 Slick HPO -.006 |  |  | PDCI / 7/8 5.9 | 5.82 / 2.00 |  | 0 | 8.38 | 250 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 80 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.006
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
PDCI
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2816.73 (Usft)
Well: |  |  | Redwood B1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 10.58 / 8.88 (klbs)
Job #: |  |  | LTX1125621 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 10.58 / 8.88 (klbs)
Date In: |  |  | 09/24/2021 | Depth In: |  | 10936 | Total Drilled: |  | 6197.00 (Usft)
Date Out: |  |  | 09/27/2021 | Depth Out: |  | 17133 | Drilling / Circ Hours: |  | 43.67 / 12.32
Survey Offset: |  |  | 66 | Gamma Offset: |  | 53
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13635755 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250003 | 6/7 11.7 2.12 TS HS88 +.011 | 5.5 | 2 | 5.250 / 2.04 | XT39 / 3 1/2 Reg | 45.34 / 1.51 / 1.56 | 33.27 | 34.27
| 3 | BTI3 | BTI | 4.875 | 2.125 |  | XT39 / XT39 | 42.13 / 0.07 / 1.63 | 1.64 | 35.91
| 4 | GT5110622 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 54.53 / 0.41 / 2.04 | 7.49 | 43.4
| 5 | 500046 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 12.50 / 0.05 / 2.08 | 3.83 | 47.23
| 6 | GT5130618 | NMDC | 5.25 | 2.75 |  | XT39 / XT39 | 48.69 / 1.52 / 3.60 | 31.23 | 78.46
| 7 | GT5010533 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 50.66 / 0.50 / 4.10 | 9.88 | 88.34
| 8 | GT5230458 | NMDC | 5.25 | 2.625 |  | XT39 / XT39 | 48.70 / 1.49 / 5.59 | 30.54 | 118.88
| 9 | GT5033743 | Filter Sub | 5 | 2.25 |  | XT39 / XT39 | 68.63 / 0.34 / 5.93 | 4.95 | 123.83
| 10 | A52130 | Tomax | 5.25 | 2.5 |  | XT39 / XT39 | 54.67 / 0.98 / 6.91 | 17.94 | 141.77
| 11 | GT52331100 | Crossover | 5.375 | 2.688 |  | CET43 / XT39 | 57.69 / 0.15 / 7.06 | 2.6 | 144.37
| 12 | Rig | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.12 / 10.18 | 187.82 | 332.19
| 13 | 531 | Drill-N-Ream | 5.375 | 2.625 |  | CET43 / CET43 | 46.35 / 0.40 / 10.58 | 8.63 | 340.82
| 14 | Rig 26 | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 17.84 / 43.78 / 54.36 | 2454.24 | 2795.06
| 15 | PG525-0057 | Agitator | 5.25 | 2.688 |  | CET43 / CET43 | 55.38 / 1.20 / 55.56 | 21.67 | 2816.73
| 16 | [8 empty] | 2816.73
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New |  | 6197
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 11.7 2.12 TS HS88 +.011 |  |  | PDCI / 6/7 11.7 | 3.97 / 2.12 |  | 0 | 5.56 | 200 | 2905
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
7623 |  |  | 1000 | 80 |  | 150-350 | 0.89 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluid | HS88 |  | 0.011
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2816.91 (Usft)
Well: |  |  | Redwood B1H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 10.57 / 8.88 (klbs)
Job #: |  |  | LTX1125621 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 10.57 / 8.88 (klbs)
Date In: |  |  | 09/27/2021 | Depth In: |  | 17133 | Total Drilled: |  | 2256.00 (Usft)
Date Out: |  |  | 09/29/2021 | Depth Out: |  | 19389 | Drilling / Circ Hours: |  | 22.70 / 6.05
Survey Offset: |  |  | 66 | Gamma Offset: |  | 53
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13601237 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | BTI3 | BTI | 4.875 | 2.125 |  | XT39 / XT39 | 42.13 / 0.07 / 0.12 | 1.64 | 2.64
| 3 | PPM250015 | 6/7 8.8 2.12 TS HS88 +.022 | 5.5 | 2 | 5.000 / 1.94 | XT39 / 3 1/2 Reg | 45.25 / 1.50 / 1.62 | 33.15 | 35.79
| 4 | GT5110622 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 54.53 / 0.41 / 2.03 | 7.49 | 43.28
| 5 | 500046 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 12.50 / 0.05 / 2.08 | 3.83 | 47.11
| 6 | GT5130618 | NMDC | 5.25 | 2.75 |  | XT39 / XT39 | 48.69 / 1.52 / 3.60 | 31.23 | 78.34
| 7 | GT5010533 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 50.66 / 0.50 / 4.10 | 9.88 | 88.22
| 8 | GT5230458 | NMDC | 5.25 | 2.625 |  | XT39 / XT39 | 48.70 / 1.49 / 5.58 | 30.54 | 118.76
| 9 | GT5033743 | Filter Sub | 5 | 2.25 |  | XT39 / XT39 | 68.63 / 0.34 / 5.92 | 4.95 | 123.71
| 10 | A52130 | Tomax | 5.25 | 2.5 |  | XT39 / XT39 | 54.67 / 0.98 / 6.90 | 17.94 | 141.65
| 11 | GT52331100 | Crossover | 5.375 | 2.688 |  | CET43 / XT39 | 57.69 / 0.15 / 7.05 | 2.6 | 144.25
| 12 | Rig | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.12 / 10.17 | 187.82 | 332.07
| 13 | 531 | Drill-N-Ream | 5.375 | 2.625 |  | CET43 / CET43 | 46.35 / 0.40 / 10.57 | 8.63 | 340.7
| 14 | Rig 26 | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 17.84 / 43.78 / 54.36 | 2454.24 | 2794.94
| 15 | ST5250050 | Agitator | 5.35 | 2.688 | 5.350 / 1.82 | CET43 / CET43 | 55.38 / 1.22 / 55.57 | 21.97 | 2816.91
| 16 | [8 empty] | 2816.91
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Halliburton | GTD64M | New | 0-1-WT-A-N-I-NO-TD | 2256
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 TS HS88 +.022 |  |  | PDCI / 6/7 8.8 | 3.56 / 2.12 |  | 0 | 5.5 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1000 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluid | HS88 |  | 0.022
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Well: |  | Redwood B1H
|  |  |  | Longitude: |  | 96° 37' 52.773" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 102.00/112.91/120.00
Date In: |  | 07/17/2021 16:00 |  | SN: |  | PPM800017 |  |  |  | WOB Rotate (klbs): |  | 16.00
Date Out: |  | 07/18/2021 05:40 |  | Description: |  | 7/8 5.9 1.50 Stab HPO -.011 NBS 13 |  |  |  | WOB Slide (klbs): |  | 9.94
Depth In/Out(Usft): |  | 108.00 / 3492.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 97.50
Inc In/Out: |  | 0.02 / 14.41 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 873.71
Azi In/Out: |  | 359.23 / 269.52 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1665.29
Total Drilled (Usft): |  | 3384 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 2021.91
%Slide (Ftg): |  | 10.73 |  | Bit to Bend (Usft): |  | 5.8 |  |  |  | Tq On Btm (kftlbs): |  | 9130.47
%Slide (Time): |  | 25.69 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 363 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 600
Slide Hours: |  | 1.7 |  | Stab to Bit (Usft): |  | 2.32 |  |  |  | Bit Data
%Rotary (Ftg): |  | 89.27 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 74.36 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 3021 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 4.92 |  | Length (Usft): |  | 37.43 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 6.62 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 3.72 / 13.67 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | 0-0-
Slide ROP (Usft/hr): |  | 213.53 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-0-NO-A-X-I-NO-TD
Rot ROP (Usft/hr): |  | 614.02 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.011 |  |  |  | Drill Hrs: |  | 6.62
Avg ROP (Usft/hr): |  | 511.18 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.72
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
7 / 5 | 3 / 2 | 1 / 1 |  | 0/100 |  | 2 | 3 | 9.1 | 400 | WBM | 5.6 | 0.4 | 120
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
71 | [9 empty] | 5 |  | 5.00 / 1.43
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 47424 |  | 13.5 |  |  |  |  | 1.5 | 1.5
7/8 5.9 1.50 Stab HPO -.011 NBS 13 0.00 |  |  |  | PPM800017 |  | 8 |  |  |  |  | 37.43 | 38.93
13 Stab 0.00 |  |  |  | SD603251 |  | 8.125 | 3 |  |  |  | 6.34 | 45.27
NMPC 0.00 |  |  |  | SD55524 |  | 8 | 3.25 |  |  |  | 8.58 | 53.85
UBHO Sub UBHO Sub 0.00 |  |  |  | 775213 |  | 7.75 | 2.875 |  |  |  | 3.66 | 57.51
NMDC 0.00 |  |  |  | SD56120 |  | 8 | 3.25 |  |  |  | 28.83 | 86.34
NMDC 0.00 |  |  |  | SD55920 |  | 8 | 3.25 |  |  |  | 28.99 | 115.33
Crossover Sub 0.00 |  |  |  | SD117248 |  | 6.75 | 2.875 |  |  |  | 2.13 | 117.46
9 Jts HWDP 0.00 | [5 empty] | 5 | 3 |  |  |  | 274.62 | 392.08
-1.00 | [11 empty] | 392.08
Additional Comments
Reason POOH: TD Surface hole. POOH f/ Casing ops How did motor drain: Motor was dry. No fluid to drain out of motor Visual Wear: One stabilizer blade on the back side ( wear pad side) of motor was starting to wear. 75% of the cutright was gone off the blade. Axial play in bearing was tight with little movement and approximately 1/16 inch play in thrust bearings Run description: Assembly drilled well and slides were yielding 5?s. Overall motor yields were what was expected. Max Temp: 120 Stalls: 0 Motor Yield: 5?/100? Max Drilling Diff: 900 Average Drilling Diff: 600 Condition of bit: Bit graded 0-0 -NO-A-X-I-NO-TD.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Well: |  | Redwood B1H
|  |  |  | Longitude: |  | 96° 37' 52.773" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 120.00/191.58/242.00
Date In: |  | 07/19/2021 13:50 |  | SN: |  | PPM800011 |  |  |  | WOB Rotate (klbs): |  | 24.00
Date Out: |  | 07/22/2021 18:00 |  | Description: |  | 7/8 5.9 2.00 Slick HPO -.006 |  |  |  | WOB Slide (klbs): |  | 13.92
Depth In/Out(Usft): |  | 3492.00 / 10936.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 79.18
Inc In/Out: |  | 14.41 / 31.91 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 832.93
Azi In/Out: |  | 269.52 / 188.80 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 4067.65
Total Drilled (Usft): |  | 7444 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4561.26
%Slide (Ftg): |  | 13.11 |  | Bit to Bend (Usft): |  | 5.82 |  |  |  | Tq On Btm (kftlbs): |  | 13743.28
%Slide (Time): |  | 56.21 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 976 |  | Bearing Gap (in): |  | 0.7 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 23.9 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 86.89 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 43.79 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6468 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 18.62 |  | Length (Usft): |  | 37.34 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 42.52 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 9.05 / 76.17 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 40.84 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-BT-N-X-I-CT-TD
Rot ROP (Usft/hr): |  | 347.37 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.006 |  |  |  | Drill Hrs: |  | 42.52
Avg ROP (Usft/hr): |  | 175.07 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 9.05
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
23 / 14 | 11 / 7 | 2 / 1 |  | 68/32 |  | 9 | 5 | 8.8 | 70000 | OBM | 4.2 | 0.4 | 242
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
63 | 59 | [8 empty] | 5 |  | 7.61 / 7.62
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 55156 |  | 9.875 | 2 |  |  | 125 | 1.5 | 1.5
7/8 5.9 2.00 Slick HPO -.006 0.00 |  |  |  | PPM800011 |  | 8 | 2 |  |  | 100 | 37.34 | 38.84
NMPC 0.00 |  |  |  | SD55524 |  | 8 | 3.25 |  |  | 150 | 8.58 | 47.42
UBHO Sub 0.00 |  |  |  | 775213 |  | 7.75 | 2.875 |  |  | 150 | 3.66 | 51.08
NMDC 0.00 |  |  |  | SD56120 |  | 8 | 3.25 |  |  | 150 | 28.83 | 79.91
NMDC 0.00 |  |  |  | SD55920 |  | 8 | 3.25 |  |  | 150 | 28.99 | 108.9
Crossover Sub 0.00 |  |  |  | SD103353 |  | 7.875 | 2.875 |  |  | 100 | 2.36 | 111.26
6.5 DC 6 Jts 0.00 | [5 empty] | 6.5 | 2.375 |  |  | 95 | 185.81 | 297.07
Crossover Sub 0.00 |  |  |  | SD103463 |  | 6.75 | 2.875 |  |  | 95 | 2.46 | 299.53
HWDP 9 Jts 0.00 | [5 empty] | 5 | 3 |  |  | 43 | 274.62 | 574.15
DP 22 Stds 0.00 | [5 empty] | 5 | 3.5 |  |  | 19.6 | 2067.4 | 2641.55
Agitator 0.00 |  |  |  | PG675-0022 |  | 6.75 | 3.75 |  |  | 80 | 24.65 | 2666.2
0.00 | [11 empty] | 2666.2
Additional Comments
-No visual damage and motor drained. -Objective to huld tangent and drop 1*/100. Hold verticle to KOP and build 5*/100 to 27.5*. -Motor held tangent, dropped and held verticle as expected. @8578 there was a pressure spike of 900psi while drilling. Driller picked up and surface equipment was checked. Drilling resumed while slowly increasing pump rate back to previous drilling parameters @900 GPM. Drilling ROP was not effected by this spike in pressure. At KOP while sliding. Formation was ratty and hanging up. At points it would take 80-100k overpull to break it loose. Motor wanted to lay 30R-120R GTF and would flop back around whenever we would get on the left side of 0 GTF for the first 150-200. Slide got better the deep we drilled but was still diffuclt in holding left. -While POOH hit a tight spot A 6924. Companyman had driller bring pumps upto 900 GPM and attempt to ream throught tight spot. Torque increased to 22-24k and a 1330 PSI increase in pressue. Pumps kicked out and pipe backed out and feel back to bottom (10936) TIH and reterive fish. Several joint of DP was bent and HWDP damaged.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Well: |  | Redwood B1H
|  |  |  | Longitude: |  | 96° 37' 52.773" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Motor Incident |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 224.00/282.68/313.00
Date In: |  | 09/24/2021 04:40 |  | SN: |  | PPM250003 |  |  |  | WOB Rotate (klbs): |  | 25.00
Date Out: |  | 09/27/2021 08:00 |  | Description: |  | 6/7 11.7 2.12 TS HS88 +.011 |  |  |  | WOB Slide (klbs): |  | 29.94
Depth In/Out(Usft): |  | 10936.00 / 17133.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 74.59
Inc In/Out: |  | 31.93 / 86.82 |  | Model: |  | 6/7 11.7 |  |  |  | Flow Rate (gpm): |  | 349.07
Azi In/Out: |  | 188.79 / 152.14 |  | Lobes / Stages: |  | 6/7 / 11.7 |  |  |  | Off Btm Press (psi): |  | 3972.9
Total Drilled (Usft): |  | 6197 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4913.08
%Slide (Ftg): |  | 12.26 |  | Bit to Bend (Usft): |  | 3.97 |  |  |  | Tq On Btm (kftlbs): |  | 8.74
%Slide (Time): |  | 25.24 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 760 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 11.02 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 87.74 |  | Kickpad OD (in): |  | 5.562 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 74.77 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 5437 |  | Fishneck OD (in): |  | 5.25 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 32.65 |  | Length (Usft): |  | 33.27 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 43.67 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 12.32 / 75.33 |  | Rev per Gal: |  | 0.89 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 68.97 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 166.52 |  | Stator Vendor/Type/Fit: |  | PV Fluid / HS88 / 0.011 |  |  |  | Drill Hrs: |  | 43.67
Avg ROP (Usft/hr): |  | 141.91 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 12.32
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
31 / 20 | 15 / 10 | 5 / 4 |  | 66/34 |  | 11 | 9 | 9.6 | 80000 | OBM | 9.7 | 0.4 | 313
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
66 | 53 | [8 empty] | 9 |  | 12.00 / 16.83
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13635755 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 11.7 2.12 TS HS88 +.011 0.00 |  |  |  | PPM250003 |  | 5.5 | 2 |  |  | 45.34 | 33.27 | 34.27
BTI 0.00 |  |  |  | BTI3 |  | 4.875 | 2.125 |  |  | 42.13 | 1.64 | 35.91
NMPC 0.00 |  |  |  | GT5110622 |  | 5 | 2.688 |  |  | 54.53 | 7.49 | 43.4
UBHO 0.00 |  |  |  | 500046 |  | 5.25 | 2.5 |  |  | 12.5 | 3.83 | 47.23
NMDC 0.00 |  |  |  | GT5130618 |  | 5.25 | 2.75 |  |  | 48.69 | 31.23 | 78.46
NMPC 0.00 |  |  |  | GT5010533 |  | 5 | 2.688 |  |  | 50.66 | 9.88 | 88.34
NMDC 0.00 |  |  |  | GT5230458 |  | 5.25 | 2.625 |  |  | 48.7 | 30.54 | 118.88
Filter Sub 0.00 |  |  |  | GT5033743 |  | 5 | 2.25 |  |  | 68.63 | 4.95 | 123.83
Tomax 0.00 |  |  |  | A52130 |  | 5.25 | 2.5 |  |  | 54.67 | 17.94 | 141.77
Crossover 0.00 |  |  |  | GT52331100 |  | 5.375 | 2.688 |  |  | 57.69 | 2.6 | 144.37
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3.8 |  |  | 16.6 | 187.82 | 332.19
Drill-N-Ream 0.00 |  |  |  | 531 |  | 5.375 | 2.625 |  |  | 46.35 | 8.63 | 340.82
26 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig 26 |  | 4.5 | 3.8 |  |  | 17.84 | 2454.24 | 2795.06
Agitator 0.00 |  |  |  | PG525-0057 |  | 5.25 | 2.688 |  |  | 55.38 | 21.67 | 2816.73
0.00 | [11 empty] | 2816.73
Additional Comments
? Reason POOH - Motor stop drilling. WOB increased and diff decreased 100-150psi. Picked off bottom and off bottom pressure was the same (4950). Driller slowly put it back on bottom upto 15k WOB and it wouldnt drill off. ? How did motor drain - Motor didnt drain ? Visual wear - No wear ? Run Description - BHA Built and walked to the left in rotations. ? Max temp on run- 315 Degrees ? How Many Stalls and what pressure was seen on stalls - no stalls ? Motor Yields - 11-17 degrees per 100. ? Max Drilling Diff - 1050 psi ? Average Drilling Diff - 850 ? Bit Condition- Bit looked green. No wear or plugged jets.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1125621 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31163 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.450" N |  |  | Well: |  | Redwood B1H
|  |  |  | Longitude: |  | 96° 37' 52.773" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 311.00/323.40/329.00
Date In: |  | 09/27/2021 09:30 |  | SN: |  | PPM250015 |  |  |  | WOB Rotate (klbs): |  | 33.00
Date Out: |  | 09/29/2021 17:30 |  | Description: |  | 6/7 8.8 2.12 TS HS88 +.022 |  |  |  | WOB Slide (klbs): |  | 41.15
Depth In/Out(Usft): |  | 17133.00 / 19389.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 80.00
Inc In/Out: |  | 86.83 / 90.95 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 369.15
Azi In/Out: |  | 152.15 / 140.73 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 5087.23
Total Drilled (Usft): |  | 2256 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5982.98
%Slide (Ftg): |  | 10.77 |  | Bit to Bend (Usft): |  | 3.56 |  |  |  | Tq On Btm (kftlbs): |  | 17.8
%Slide (Time): |  | 36.12 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 243 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1000
Slide Hours: |  | 8.2 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 89.23 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 63.88 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2013 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 14.5 |  | Length (Usft): |  | 33.15 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 22.70 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 6.05 / 56.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 29.63 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-WT-A-N-I-NO-TD
Rot ROP (Usft/hr): |  | 138.83 |  | Stator Vendor/Type/Fit: |  | PV Fluid / HS88 / 0.022 |  |  |  | Drill Hrs: |  | 22.70
Avg ROP (Usft/hr): |  | 99.38 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 6.05
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
53 / 32 | 23 / 14 | 6 / 5 |  | 75/25 |  | 21 | 11 | 10.5 | 53000 | OBM | 13.3 | 0.4 | 329
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
66 | 53 | [10 empty] | 0.00 / 7.67
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13601237 |  | 6.75 | 2 |  |  | 50 | 1 | 1
BTI 0.00 |  |  |  | BTI3 |  | 4.875 | 2.125 |  |  | 42.13 | 1.64 | 2.64
6/7 8.8 2.12 TS HS88 +.022 0.00 |  |  |  | PPM250015 |  | 5.5 | 2 |  |  | 45.25 | 33.15 | 35.79
NMPC 0.00 |  |  |  | GT5110622 |  | 5 | 2.688 |  |  | 54.53 | 7.49 | 43.28
UBHO 0.00 |  |  |  | 500046 |  | 5.25 | 2.5 |  |  | 12.5 | 3.83 | 47.11
NMDC 0.00 |  |  |  | GT5130618 |  | 5.25 | 2.75 |  |  | 48.69 | 31.23 | 78.34
NMPC 0.00 |  |  |  | GT5010533 |  | 5 | 2.688 |  |  | 50.66 | 9.88 | 88.22
NMDC 0.00 |  |  |  | GT5230458 |  | 5.25 | 2.625 |  |  | 48.7 | 30.54 | 118.76
Filter Sub 0.00 |  |  |  | GT5033743 |  | 5 | 2.25 |  |  | 68.63 | 4.95 | 123.71
Tomax 0.00 |  |  |  | A52130 |  | 5.25 | 2.5 |  |  | 54.67 | 17.94 | 141.65
Crossover 0.00 |  |  |  | GT52331100 |  | 5.375 | 2.688 |  |  | 57.69 | 2.6 | 144.25
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig |  | 4.5 | 3.8 |  |  | 16.6 | 187.82 | 332.07
Drill-N-Ream 0.00 |  |  |  | 531 |  | 5.375 | 2.625 |  |  | 46.35 | 8.63 | 340.7
26 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | Rig 26 |  | 4.5 | 3.8 |  |  | 17.84 | 2454.24 | 2794.94
Agitator 0.00 |  |  |  | ST5250050 |  | 5.35 | 2.688 |  |  | 55.38 | 21.97 | 2816.91
0.00 | [11 empty] | 2816.91
Additional Comments
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3384
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 363
Well Name: |  |  |  |  | Redwood B1H |  |  | Survey / Gamma Offset: |  |  |  |  | 71.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.22 |  | Rotate: |  | 3021
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/17/2021 | 16:00 | 16:35 | 0.58333 | 108 | 270 | 162 | Rotate |  | 198 | 0.04 | 359.23 | 198 | 0.07 | 0 | 0.07 | 0.02 |  |  | 3 | 60 | 600 | 1500 | 277.71 | 650 | 575 | 75 | 106 | 70 | 65 | 60
07/17/2021 | 16:40 | 16:48 | 0.13333 | 270 | 361 | 91 | Rotate |  | 289 | 0.04 | 292.44 | 289 | 0.11 | -0.03 | 0.11 | 0.05 |  |  | 5 | 70 | 700 | 1500 | 682.5 | 900 | 800 | 100 | 106 | 70 | 65 | 60
07/17/2021 | 16:53 | 17:01 | 0.13333 | 361 | 454 | 93 | Rotate |  | 382 | 0.26 | 240.76 | 382 | 0.02 | -0.24 | 0.02 | 0.26 |  |  | 5 | 80 | 800 | 2500 | 697.5 | 1200 | 1000 | 200 | 102 | 70 | 65 | 60
07/17/2021 | 17:05 | 17:23 | 0.3 | 454 | 579 | 125 | Rotate |  | 507 | 0.35 | 252.71 | 507 | -0.23 | -0.86 | -0.23 | 0.09 |  |  | 5 | 100 | 900 | 2500 | 416.67 | 1500 | 1200 | 300 | 102 | 75 | 70 | 65
07/17/2021 | 17:27 | 17:35 | 0.13333 | 579 | 673 | 94 | Rotate |  | 601 | 0.26 | 244.98 | 601 | -0.41 | -1.32 | -0.41 | 0.11 |  |  | 8 | 100 | 900 | 2500 | 705 | 1500 | 1200 | 300 | 102 | 75 | 70 | 65
07/17/2021 | 17:39 | 17:45 | 0.1 | 673 | 767 | 94 | Rotate |  | 695 | 0.26 | 250.43 | 695 | -0.57 | -1.72 | -0.57 | 0.03 |  |  | 5 | 100 | 900 | 2500 | 940 | 1500 | 1200 | 300 | 104 | 75 | 70 | 65
07/17/2021 | 17:50 | 17:54 | 0.066667 | 767 | 861 | 94 | Rotate |  | 789 | 0.35 | 261.06 | 788.99 | -0.68 | -2.2 | -0.68 | 0.11 |  |  | 15 | 100 | 900 | 10229 | 1410 | 2000 | 1500 | 500 | 104 | 75 | 70 | 65
07/17/2021 | 17:59 | 18:05 | 0.1 | 861 | 955 | 94 | Rotate |  | 883 | 0.35 | 299.73 | 882.99 | -0.59 | -2.74 | -0.59 | 0.25 |  |  | 15.2 | 100 | 900 | 5746 | 940 | 1800 | 1500 | 300 | 104 | 75 | 70 | 65
07/17/2021 | 18:10 | 18:13 | 0.05 | 955 | 970 | 15 | Slide | TTF: 270; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 300 | 1700 | 1500 | 200 | 104 | 75 | 70 | 65
07/17/2021 | 18:13 | 18:19 | 0.1 | 970 | 1049 | 79 | Rotate |  | 977 | 1.01 | 279.34 | 976.99 | -0.31 | -3.8 | -0.31 | 0.74 |  |  | 20 | 100 | 900 | 7230 | 790 | 1900 | 1500 | 400 | 104 | 75 | 70 | 65
07/17/2021 | 18:24 | 18:27 | 0.05 | 1049 | 1064 | 15 | Slide | TTF: 260; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 300 | 1700 | 1500 | 200 | 104 | 75 | 70 | 65
07/17/2021 | 18:27 | 18:33 | 0.1 | 1064 | 1143 | 79 | Rotate |  | 1071 | 1.93 | 270.38 | 1070.95 | -0.16 | -6.2 | -0.16 | 1.01 |  |  | 20 | 100 | 900 | 9736 | 790 | 2000 | 1500 | 500 | 107 | 75 | 70 | 65
07/17/2021 | 18:38 | 18:41 | 0.05 | 1143 | 1157 | 14 | Slide | TTF: 260; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 280 | 1700 | 1500 | 200 | 107 | 75 | 70 | 65
07/17/2021 | 18:41 | 18:47 | 0.1 | 1157 | 1238 | 81 | Rotate |  | 1166 | 3.12 | 278.99 | 1165.86 | 0.25 | -10.36 | 0.25 | 1.31 |  |  | 18 | 100 | 900 | 6515 | 810 | 2041 | 1500 | 541 | 107 | 75 | 70 | 65
07/17/2021 | 18:51 | 18:57 | 0.1 | 1238 | 1331 | 93 | Rotate |  | 1259 | 3.34 | 283.47 | 1258.71 | 1.28 | -15.49 | 1.28 | 0.36 |  |  | 18 | 100 | 900 | 6233 | 930 | 2064 | 1500 | 564 | 107 | 75 | 70 | 65
07/17/2021 | 19:02 | 19:05 | 0.05 | 1331 | 1343 | 12 | Slide | TTF: -20; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 1733 | 1500 | 233 | 109 | 75 | 70 | 65
07/17/2021 | 19:05 | 19:11 | 0.1 | 1343 | 1425 | 82 | Rotate |  | 1353 | 3.74 | 285.05 | 1352.53 | 2.71 | -21.11 | 2.71 | 0.44 |  |  | 21.4 | 100 | 900 | 9004 | 820 | 2104 | 1500 | 604 | 111 | 95 | 90 | 88
07/17/2021 | 19:16 | 19:19 | 0.05 | 1425 | 1440 | 15 | Slide | TTF: -40; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 300 | 1600 | 1500 | 100 | 111 | 95 | 90 | 88
07/17/2021 | 19:19 | 19:25 | 0.1 | 1440 | 1519 | 79 | Rotate |  | 1447 | 4.48 | 286.64 | 1446.29 | 4.56 | -27.59 | 4.56 | 0.8 |  |  | 22 | 100 | 900 | 8435 | 790 | 2098 | 1634 | 464 | 111 | 95 | 90 | 88
07/17/2021 | 19:30 | 19:34 | 0.066667 | 1519 | 1539 | 20 | Slide | TTF: -60; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 300 | 1788 | 1634 | 154 | 111 | 95 | 90 | 88
07/17/2021 | 19:34 | 19:40 | 0.1 | 1539 | 1614 | 75 | Rotate |  | 1542 | 5.76 | 281.36 | 1540.91 | 6.56 | -35.82 | 6.56 | 1.43 |  |  | 23.9 | 100 | 900 | 8097 | 750 | 2104 | 1634 | 470 | 111 | 95 | 90 | 88
07/17/2021 | 19:45 | 19:49 | 0.066667 | 1614 | 1629 | 15 | Slide | TTF: -60; Drilling Parameters WOB: 4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 225 | 1798 | 1634 | 164 | 111 | 95 | 90 | 88
07/17/2021 | 19:49 | 19:55 | 0.1 | 1629 | 1707 | 78 | Rotate |  | 1635 | 6.42 | 274.42 | 1633.39 | 7.88 | -45.58 | 7.88 | 1.06 |  |  | 27.4 | 100 | 900 | 9448 | 780 | 2186 | 1652 | 534 | 111 | 95 | 90 | 88
07/17/2021 | 20:00 | 20:04 | 0.066667 | 1707 | 1719 | 12 | Slide | TTF: -30; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 715; Drilling Parameters ROP: 180 | 1220 | 1154 | 66 | 111 | 95 | 90 | 88 | 2 Pumps on hole
07/17/2021 | 20:04 | 20:16 | 0.2 | 1719 | 1801 | 82 | Rotate |  | 1729 | 7.08 | 270.38 | 1726.73 | 8.32 | -56.61 | 8.32 | 0.86 |  |  | 13.2 | 100 | 715 | 5008 | 410 | 1419 | 1154 | 265 | 113 | 95 | 90 | 88 | 2 pumps on hole
07/17/2021 | 20:21 | 20:25 | 0.066667 | 1801 | 1816 | 15 | Slide | TTF: -20; Drilling Parameters WOB: 11; Drilling Parameters FLOW: 715; Drilling Parameters ROP: 225 | 1290 | 1154 | 136 | 113 | 95 | 90 | 88 | 2 pumps on hole
07/17/2021 | 20:25 | 20:37 | 0.2 | 1816 | 1894 | 78 | Rotate |  | 1822 | 7.69 | 269.76 | 1818.96 | 8.34 | -68.57 | 8.34 | 0.66 |  |  | 13.9 | 100 | 715 | 4327 | 390 | 1517 | 1154 | 363 | 113 | 95 | 90 | 88 | 2 pumps on hole
07/17/2021 | 20:43 | 20:49 | 0.1 | 1894 | 1914 | 20 | Slide | TTF: -20; Drilling Parameters WOB: 5.2; Drilling Parameters FLOW: 715; Drilling Parameters ROP: 200 | 1341 | 1154 | 187 | 113 | 95 | 90 | 88 | 2 pumps on hole
07/17/2021 | 20:49 | 20:59 | 0.16667 | 1914 | 1988 | 74 | Rotate |  | 1916 | 8.83 | 267.74 | 1911.99 | 8.03 | -82.07 | 8.03 | 1.25 |  |  | 13.9 | 100 | 900 | 8753 | 444 | 2319 | 1952 | 367 | 115 | 95 | 90 | 88
07/17/2021 | 21:05 | 21:09 | 0.066667 | 1988 | 2003 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 7.4; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 225 | 1921 | 1819 | 102 | 115 | 95 | 90 | 88
07/17/2021 | 21:09 | 21:16 | 0.11667 | 2003 | 2083 | 80 | Rotate |  | 2011 | 9.62 | 270.03 | 2005.76 | 7.74 | -97.29 | 7.74 | 0.92 |  |  | 30.6 | 100 | 900 | 11079 | 685.71 | 2340 | 1819 | 521 | 115 | 95 | 90 | 88
07/17/2021 | 21:21 | 21:25 | 0.066667 | 2083 | 2098 | 15 | Slide | TTF: -20; Drilling Parameters WOB: 14.6; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 225 | 2049 | 1819 | 230 | 115 | 95 | 90 | 88
07/17/2021 | 21:25 | 21:33 | 0.13333 | 2098 | 2178 | 80 | Rotate |  | 2106 | 9.98 | 268.62 | 2099.37 | 7.55 | -113.46 | 7.55 | 0.46 |  |  | 25 | 100 | 900 | 9129 | 600 | 2355 | 1819 | 536 | 115 | 95 | 90 | 88
07/17/2021 | 21:38 | 21:44 | 0.1 | 2178 | 2198 | 20 | Slide | TTF: -10; Drilling Parameters WOB: 12.1; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 200 | 2091 | 1915 | 176 | 115 | 95 | 90 | 88
07/17/2021 | 21:44 | 21:53 | 0.15 | 2198 | 2272 | 74 | Rotate |  | 2200 | 10.63 | 267.56 | 2191.85 | 6.98 | -130.26 | 6.98 | 0.72 |  |  | 29.3 | 100 | 900 | 9416 | 493.33 | 2381 | 1819 | 562 | 115 | 95 | 90 | 88
07/17/2021 | 21:58 | 22:04 | 0.1 | 2272 | 2292 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 11.6; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 200 | 2059 | 1915 | 144 | 115 | 95 | 90 | 88
07/17/2021 | 22:04 | 22:11 | 0.11667 | 2292 | 2365 | 73 | Rotate |  | 2293 | 11.47 | 270.11 | 2283.13 | 6.63 | -148.08 | 6.63 | 1.04 |  |  | 17.5 | 100 | 900 | 7784 | 625.71 | 2232 | 1915 | 317 | 115 | 95 | 90 | 88
07/17/2021 | 22:21 | 22:28 | 0.11667 | 2365 | 2385 | 20 | Slide | TTF: -20; Drilling Parameters WOB: 12.5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 171.43 | 2087 | 1915 | 172 | 115 | 95 | 90 | 88
07/17/2021 | 22:28 | 22:33 | 0.083333 | 2385 | 2459 | 74 | Rotate |  | 2387 | 12.57 | 271.52 | 2375.07 | 6.92 | -167.65 | 6.92 | 1.21 |  |  | 32.3 | 100 | 900 | 15011 | 888 | 2469 | 1915 | 554 | 115 | 95 | 90 | 88
07/17/2021 | 22:37 | 22:42 | 0.083333 | 2459 | 2479 | 20 | Slide | TTF: -20; Drilling Parameters WOB: 6.8; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 1995 | 1873 | 122 | 115 | 115 | 110 | 105
07/17/2021 | 22:42 | 22:47 | 0.083333 | 2479 | 2553 | 74 | Rotate |  | 2481 | 13.67 | 271.96 | 2466.61 | 7.58 | -188.98 | 7.58 | 1.18 |  |  | 23 | 100 | 900 | 17763 | 888 | 2276 | 1873 | 403 | 115 | 115 | 110 | 105
07/17/2021 | 22:52 | 22:56 | 0.066667 | 2553 | 2565 | 12 | Slide | TTF: -60; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 1950 | 1873 | 77 | 115 | 115 | 110 | 105
07/17/2021 | 22:56 | 23:03 | 0.11667 | 2565 | 2647 | 82 | Rotate |  | 2575 | 13.89 | 268.27 | 2557.91 | 7.61 | -211.36 | 7.61 | 0.96 |  |  | 23.6 | 100 | 900 | 8879 | 702.86 | 2327 | 1873 | 454 | 120 | 115 | 110 | 105
07/17/2021 | 23:08 | 23:15 | 0.11667 | 2647 | 2741 | 94 | Rotate |  | 2669 | 13.93 | 265.98 | 2649.15 | 6.48 | -233.92 | 6.48 | 0.59 |  |  | 34.5 | 100 | 900 | 13768 | 805.71 | 2409 | 1873 | 536 | 120 | 115 | 110 | 105
07/17/2021 | 23:19 | 23:26 | 0.11667 | 2741 | 2835 | 94 | Rotate |  | 2763 | 13.4 | 265.37 | 2740.49 | 4.81 | -256.07 | 4.81 | 0.58 |  |  | 31.8 | 100 | 900 | 11961 | 805.71 | 2579 | 1845 | 734 | 120 | 115 | 110 | 105
07/17/2021 | 23:30 | 23:35 | 0.083333 | 2835 | 2855 | 20 | Slide | TTF: 20; Drilling Parameters WOB: 11.1; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 2179 | 1845 | 334 | 120 | 115 | 110 | 105
07/17/2021 | 23:35 | 23:45 | 0.16667 | 2855 | 2929 | 74 | Rotate |  | 2857 | 13.45 | 265.19 | 2831.92 | 3.01 | -277.82 | 3.01 | 0.07 |  |  | 33.7 | 100 | 900 | 13080 | 444 | 2660 | 1845 | 815 | 120 | 115 | 110 | 105
07/17/2021 | 23:50 | 23:56 | 0.1 | 2929 | 2949 | 20 | Slide | TTF: 30; Drilling Parameters WOB: 12.8; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 200 | 2288 | 2014 | 274 | 120 | 115 | 110 | 105
07/17/2021 | 23:56 | 24:00 | 0.066667 | 2949 | 2975 | 26 | Rotate |  | 2952 | 13.97 | 269.06 | 2924.22 | 1.9 | -300.29 | 1.9 | 1.11 |  |  | 18.4 | 100 | 900 | 13099 | 390 | 2490 | 2014 | 476 | 120 | 115 | 110 | 105
07/18/2021 | 00:00 | 00:05 | 0.083333 | 2975 | 3024 | 49 | Rotate | Drilling Parameters WOB: 18.6; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 13099; Drilling Parameters ROP: 588 | 2490 | 2014 | 476 | 120 | 115 | 110 | 105
07/18/2021 | 00:08 | 00:15 | 0.11667 | 3024 | 3117 | 93 | Rotate |  | 3045 | 14.46 | 271.7 | 3014.37 | 2.06 | -323.12 | 2.06 | 0.87 |  |  | 33.7 | 100 | 900 | 14531 | 797.14 | 2721 | 2116 | 605 | 120 | 115 | 110 | 105
07/18/2021 | 00:18 | 00:25 | 0.11667 | 3117 | 3211 | 94 | Rotate |  | 3139 | 14.11 | 269.85 | 3105.46 | 2.38 | -346.31 | 2.38 | 0.61 |  |  | 29.2 | 100 | 900 | 15487 | 805.71 | 2804 | 2116 | 688 | 120 | 115 | 110 | 105
07/18/2021 | 00:28 | 00:33 | 0.083333 | 3211 | 3226 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 2402 | 2132 | 270 | 120 | 115 | 110 | 105
07/18/2021 | 00:33 | 00:42 | 0.15 | 3226 | 3305 | 79 | Rotate |  | 3233 | 13.84 | 269.76 | 3196.68 | 2.3 | -369.01 | 2.3 | 0.29 |  |  | 35.2 | 100 | 900 | 13744 | 526.67 | 2639 | 2132 | 507 | 120 | 115 | 110 | 105
07/18/2021 | 00:47 | 00:54 | 0.11667 | 3305 | 3323 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 19.2; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 154.29 | 2330 | 2132 | 198 | 120 | 115 | 110 | 105
07/18/2021 | 00:54 | 01:02 | 0.13333 | 3323 | 3398 | 75 | Rotate |  | 3326 | 13.67 | 269.15 | 3287.02 | 2.09 | -391.12 | 2.09 | 0.24 |  |  | 30.7 | 100 | 900 | 16495 | 562.5 | 2874 | 2132 | 742 | 120 | 115 | 110 | 105
07/18/2021 | 01:07 | 01:13 | 0.1 | 3398 | 3413 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 17.3; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2422 | 2198 | 224 | 120 | 115 | 110 | 105
07/18/2021 | 01:13 | 01:21 | 0.13333 | 3413 | 3492 | 79 | Rotate |  | 3420 | 14.28 | 270.03 | 3378.23 | 1.93 | -413.82 | 1.93 | 0.69 |  |  | 28.9 | 100 | 900 | 12611 | 592.5 | 2780 | 2132 | 648 | 120 | 115 | 110 | 105

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7444
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 976
Well Name: |  |  |  |  | Redwood B1H |  |  | Survey / Gamma Offset: |  |  |  |  | 63.00 / 59.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.22 |  | Rotate: |  | 6468
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/19/2021 | 20:05 | 20:10 | 0.083333 | 3492 | 3502 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 420; Drilling Parameters Tq: 4000; Drilling Parameters ROP: 120 | 1252 | 1048 | 204 | 120 | 147 | 145 | 142
07/19/2021 | 20:50 | 21:10 | 0.33333 | 3502 | 3605 | 103 | Rotate |  | 3542 | 14.5 | 269.17 | 3496.41 | 1.72 | -444.14 | 1.72 | 0.25 |  |  | 20 | 60 | 600 | 4000 | 309 | 2244 | 2002 | 242 | 120 | 147 | 145 | 142
07/19/2021 | 21:15 | 21:25 | 0.16667 | 3605 | 3699 | 94 | Rotate |  | 3636 | 14.52 | 270.47 | 3587.41 | 1.64 | -467.69 | 1.64 | 0.35 |  |  | 21 | 80 | 600 | 8059 | 564 | 2451 | 2002 | 449 | 120 | 147 | 145 | 142
07/19/2021 | 21:30 | 21:40 | 0.16667 | 3699 | 3793 | 94 | Rotate |  | 3730 | 14.61 | 269.44 | 3678.39 | 1.62 | -491.33 | 1.62 | 0.29 |  |  | 29.1 | 80 | 718 | 8772 | 564 | 3221 | 2847 | 374 | 120 | 147 | 145 | 142
07/19/2021 | 21:44 | 21:55 | 0.18333 | 3793 | 3887 | 94 | Rotate |  | 3824 | 14.55 | 269.65 | 3769.36 | 1.44 | -514.99 | 1.44 | 0.09 |  |  | 24.2 | 80 | 718 | 7096 | 512.73 | 3151 | 2801 | 350 | 131 | 147 | 145 | 142
07/19/2021 | 21:58 | 22:08 | 0.16667 | 3887 | 3982 | 95 | Rotate |  | 3919 | 14.73 | 268.83 | 3861.28 | 1.12 | -539 | 1.12 | 0.29 |  |  | 29.3 | 80 | 766 | 6184 | 570 | 3520 | 3127 | 393 | 131 | 147 | 145 | 142
07/19/2021 | 22:11 | 22:21 | 0.16667 | 3982 | 4075 | 93 | Rotate |  | 4012 | 14.85 | 268.82 | 3951.19 | 0.63 | -562.73 | 0.63 | 0.13 |  |  | 30.1 | 80 | 766 | 9654 | 558 | 3617 | 3127 | 490 | 136 | 147 | 145 | 142
07/19/2021 | 22:24 | 22:33 | 0.15 | 4075 | 4168 | 93 | Rotate |  | 4105 | 14.79 | 268.59 | 4041.1 | 0.09 | -586.52 | 0.09 | 0.09 |  |  | 28.7 | 80 | 815 | 11286 | 620 | 4066 | 3510 | 556 | 136 | 147 | 145 | 142
07/19/2021 | 22:36 | 22:47 | 0.18333 | 4168 | 4260 | 92 | Rotate |  | 4197 | 14.56 | 268.97 | 4130.1 | -0.4 | -609.82 | -0.4 | 0.27 |  |  | 29.4 | 80 | 718 | 8241 | 501.82 | 3315 | 2982 | 333 | 141 | 147 | 145 | 142
07/19/2021 | 22:49 | 22:59 | 0.16667 | 4260 | 4353 | 93 | Rotate |  | 4290 | 14.43 | 268.77 | 4220.14 | -0.86 | -633.09 | -0.86 | 0.15 |  |  | 25.4 | 80 | 718 | 8172 | 558 | 3353 | 2913 | 440 | 143 | 147 | 145 | 142
07/19/2021 | 23:03 | 23:06 | 0.05 | 4353 | 4361 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 815; Drilling Parameters ROP: 160 | 3806 | 3678 | 128 | 143 | 160 | 155 | 150
07/19/2021 | 23:06 | 23:16 | 0.16667 | 4361 | 4447 | 86 | Rotate |  | 4384 | 13.74 | 269.81 | 4311.31 | -1.15 | -655.96 | -1.15 | 0.78 |  |  | 27.2 | 80 | 815 | 9548 | 516 | 3900 | 3678 | 222 | 145 | 160 | 155 | 150
07/19/2021 | 23:20 | 23:41 | 0.35 | 4447 | 4540 | 93 | Rotate |  | 4477 | 13.89 | 269.9 | 4401.62 | -1.21 | -678.17 | -1.21 | 0.16 |  |  | 28.5 | 80 | 670 | 10198 | 265.71 | 3027 | 2540 | 487 | 145 | 160 | 155 | 150
07/19/2021 | 23:45 | 23:49 | 0.066667 | 4540 | 4552 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 670; Drilling Parameters ROP: 180 | 2792 | 2540 | 252 | 145 | 160 | 155 | 150
07/19/2021 | 23:49 | 24:00 | 0.18333 | 4552 | 4582 | 30 | Rotate |  | 4571 | 12.99 | 269.51 | 4493.05 | -1.32 | -700.02 | -1.32 | 0.96 |  |  | 26.8 | 80 | 815 | 11548 | 163.64 | 4112 | 3638 | 474 | 145 | 160 | 155 | 150
07/20/2021 | 00:00 | 00:05 | 0.083333 | 4582 | 4634 | 52 | Rotate | Drilling Parameters WOB: 26.8; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 815; Drilling Parameters Tq: 11548; Drilling Parameters ROP: 624 | 4112 | 3638 | 474 | 145 | 160 | 155 | 150
07/20/2021 | 00:08 | 00:11 | 0.05 | 4634 | 4644 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 815; Drilling Parameters ROP: 200 | 3787 | 3638 | 149 | 149 | 160 | 155 | 150
07/20/2021 | 00:11 | 00:21 | 0.16667 | 4644 | 4727 | 83 | Rotate |  | 4664 | 12.77 | 264.24 | 4583.71 | -2.44 | -720.7 | -2.44 | 1.28 |  |  | 25.4 | 80 | 815 | 12205 | 498 | 4003 | 3638 | 365 | 149 | 160 | 155 | 150
07/20/2021 | 00:24 | 00:28 | 0.066667 | 4727 | 4739 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 815; Drilling Parameters ROP: 180 | 3864 | 3638 | 226 | 152 | 160 | 155 | 150
07/20/2021 | 00:28 | 00:39 | 0.18333 | 4739 | 4822 | 83 | Rotate |  | 4759 | 13.2 | 262.3 | 4676.28 | -4.95 | -741.89 | -4.95 | 0.64 |  |  | 25.2 | 80 | 815 | 11029 | 452.73 | 4049 | 3638 | 411 | 152 | 160 | 155 | 150
07/20/2021 | 00:43 | 00:50 | 0.11667 | 4822 | 4834 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 861; Drilling Parameters ROP: 102.86 | 4115 | 3863 | 252 | 156 | 160 | 155 | 150
07/20/2021 | 00:50 | 00:59 | 0.15 | 4834 | 4916 | 82 | Rotate |  | 4853 | 12.02 | 262.45 | 4768.01 | -7.67 | -762.23 | -7.67 | 1.26 |  |  | 28.9 | 80 | 861 | 13324 | 546.67 | 4433 | 3863 | 570 | 156 | 160 | 155 | 150
07/20/2021 | 01:02 | 01:07 | 0.083333 | 4916 | 4928 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 861; Drilling Parameters ROP: 144 | 4221 | 3885 | 336 | 156 | 160 | 155 | 150
07/20/2021 | 01:07 | 01:18 | 0.18333 | 4928 | 5010 | 82 | Rotate |  | 4947 | 11.14 | 257.78 | 4860.1 | -10.88 | -780.81 | -10.88 | 1.37 |  |  | 26.8 | 80 | 861 | 11067 | 447.27 | 4120 | 3863 | 257 | 161 | 160 | 155 | 150
07/20/2021 | 01:27 | 01:33 | 0.1 | 5010 | 5024 | 14 | Slide | TTF: 140; Drilling Parameters WOB: 8; Drilling Parameters FLOW: 815; Drilling Parameters ROP: 140 | 3923 | 3764 | 159 | 163 | 160 | 155 | 150
07/20/2021 | 01:33 | 01:43 | 0.16667 | 5024 | 5104 | 80 | Rotate |  | 5041 | 10.23 | 255.57 | 4952.47 | -14.88 | -797.77 | -14.88 | 1.06 |  |  | 27.9 | 80 | 815 | 12324 | 480 | 4152 | 3764 | 388 | 163 | 160 | 155 | 150
07/20/2021 | 01:46 | 01:57 | 0.18333 | 5104 | 5119 | 15 | Slide | TTF: 140; Drilling Parameters WOB: 2; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 81.82 | 4501 | 4374 | 127 | 165 | 180 | 170 | 165
07/20/2021 | 01:57 | 02:04 | 0.11667 | 5119 | 5197 | 78 | Rotate |  | 5134 | 9.77 | 252.98 | 5044.06 | -19.25 | -813.31 | -19.25 | 0.69 |  |  | 33.2 | 80 | 900 | 12424 | 668.57 | 4866 | 4374 | 492 | 165 | 180 | 170 | 165
07/20/2021 | 02:08 | 02:16 | 0.13333 | 5197 | 5215 | 18 | Slide | TTF: 130; Drilling Parameters WOB: 12.3; Drilling Parameters FLOW: 765; Drilling Parameters ROP: 135 | 3537 | 3221 | 316 | 165 | 180 | 170 | 165
07/20/2021 | 02:16 | 02:29 | 0.21667 | 5215 | 5292 | 77 | Rotate |  | 5229 | 8.1 | 255.26 | 5137.9 | -23.31 | -827.49 | -23.31 | 1.8 |  |  | 30.1 | 80 | 900 | 13227 | 355.38 | 4677 | 4377 | 300 | 168 | 180 | 170 | 165
07/20/2021 | 02:33 | 02:40 | 0.11667 | 5292 | 5310 | 18 | Slide | TTF: 130; Drilling Parameters WOB: 14; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 154.29 | 4672 | 4377 | 295 | 168 | 180 | 170 | 165
07/20/2021 | 02:40 | 02:50 | 0.16667 | 5310 | 5385 | 75 | Rotate |  | 5322 | 6.71 | 257.59 | 5230.12 | -26.15 | -839.14 | -26.15 | 1.53 |  |  | 28 | 80 | 900 | 12461 | 450 | 4828 | 4377 | 451 | 172 | 180 | 170 | 165
07/20/2021 | 02:54 | 03:00 | 0.1 | 5385 | 5403 | 18 | Slide | TTF: 130; Drilling Parameters WOB: 2; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 4545 | 4431 | 114 | 172 | 180 | 170 | 165
07/20/2021 | 03:00 | 03:11 | 0.18333 | 5403 | 5479 | 76 | Rotate |  | 5416 | 4.88 | 256.17 | 5323.64 | -28.28 | -848.38 | -28.28 | 1.95 |  |  | 34.3 | 80 | 900 | 15137 | 414.55 | 4804 | 4431 | 373 | 172 | 180 | 170 | 165
07/20/2021 | 03:14 | 03:20 | 0.1 | 5479 | 5497 | 18 | Slide | TTF: 120; Drilling Parameters WOB: 16; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 4551 | 4319 | 232 | 176 | 180 | 170 | 165
07/20/2021 | 03:20 | 03:30 | 0.16667 | 5497 | 5573 | 76 | Rotate |  | 5510 | 3.7 | 274.01 | 5417.38 | -29.03 | -855.29 | -29.03 | 1.88 |  |  | 28.3 | 80 | 900 | 12155 | 456 | 4757 | 4319 | 438 | 178 | 180 | 170 | 165
07/20/2021 | 03:33 | 03:40 | 0.11667 | 5573 | 5591 | 18 | Slide | TTF: 130; Drilling Parameters WOB: 16; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 154.29 | 4687 | 4319 | 368 | 179 | 192 | 175 | 165
07/20/2021 | 03:40 | 03:50 | 0.16667 | 5591 | 5667 | 76 | Rotate |  | 5604 | 2.06 | 298.6 | 5511.26 | -28 | -859.8 | -28 | 2.15 |  |  | 25.7 | 80 | 900 | 15025 | 456 | 4871 | 4319 | 552 | 179 | 192 | 175 | 165
07/20/2021 | 03:53 | 03:59 | 0.1 | 5667 | 5682 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 4703 | 4319 | 384 | 181 | 192 | 175 | 165
07/20/2021 | 03:59 | 04:09 | 0.16667 | 5682 | 5762 | 80 | Rotate |  | 5699 | 1.96 | 325.57 | 5606.2 | -25.85 | -862.22 | -25.85 | 0.99 |  |  | 29.2 | 80 | 900 | 14700 | 480 | 4931 | 4319 | 612 | 183 | 192 | 175 | 165
07/20/2021 | 04:12 | 04:19 | 0.11667 | 5762 | 5777 | 15 | Slide | TTF: 90; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 128.57 | 4727 | 4319 | 408 | 183 | 192 | 175 | 165
07/20/2021 | 04:19 | 04:34 | 0.25 | 5777 | 5855 | 78 | Rotate |  | 5792 | 2 | 352.82 | 5699.15 | -22.92 | -863.32 | -22.92 | 1 |  |  | 33.1 | 80 | 900 | 11692 | 312 | 4953 | 4319 | 634 | 183 | 192 | 175 | 165
07/20/2021 | 04:38 | 04:46 | 0.13333 | 5855 | 5870 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 112.5 | 4672 | 4319 | 353 | 185 | 192 | 175 | 165
07/20/2021 | 04:46 | 04:56 | 0.16667 | 5870 | 5949 | 79 | Rotate |  | 5886 | 2.42 | 347.57 | 5793.08 | -19.36 | -863.95 | -19.36 | 0.5 |  |  | 30.3 | 80 | 900 | 15442 | 474 | 4981 | 4319 | 662 | 185 | 192 | 175 | 165
07/20/2021 | 05:00 | 05:07 | 0.11667 | 5949 | 5967 | 18 | Slide | TTF: 150; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 154.29 | 4520 | 4380 | 140 | 187 | 192 | 175 | 165
07/20/2021 | 05:07 | 05:18 | 0.18333 | 5967 | 6043 | 76 | Rotate |  | 5980 | 0.95 | 309.7 | 5887.04 | -16.92 | -864.98 | -16.92 | 1.88 |  |  | 31.4 | 80 | 900 | 14337 | 414.55 | 4874 | 4380 | 494 | 187 | 192 | 175 | 165
07/20/2021 | 05:22 | 05:34 | 0.2 | 6043 | 6137 | 94 | Rotate |  | 6074 | 1.17 | 285.97 | 5981.02 | -16.16 | -866.5 | -16.16 | 0.52 |  |  | 30.9 | 80 | 900 | 11217 | 470 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 05:37 | 05:50 | 0.21667 | 6137 | 6232 | 95 | Rotate |  | 6168 | 1.46 | 302.88 | 6075 | -15.25 | -868.43 | -15.25 | 0.51 |  |  | 28 | 80 | 900 | 11217 | 438.46 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 05:53 | 06:05 | 0.2 | 6232 | 6325 | 93 | Rotate |  | 6262 | 1.61 | 303.64 | 6168.96 | -13.87 | -870.54 | -13.87 | 0.16 |  |  | 28 | 80 | 900 | 12000 | 465 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 06:08 | 06:20 | 0.2 | 6325 | 6418 | 93 | Rotate |  | 6355 | 1.73 | 307.7 | 6261.92 | -12.28 | -872.74 | -12.28 | 0.18 |  |  | 28 | 80 | 900 | 12000 | 465 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 06:23 | 06:26 | 0.05 | 6418 | 6441 | 23 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 460 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 06:26 | 06:36 | 0.16667 | 6441 | 6451 | 10 | Slide | 120 | 6449 | 0.92 | 279.91 | 6355.9 | -11.29 | -874.6 | -11.29 | 1.08 |  |  | 18 | 80 | 900 | 12000 | 60 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 06:36 | 06:45 | 0.15 | 6451 | 6512 | 61 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 406.67 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 06:48 | 06:53 | 0.083333 | 6512 | 6535 | 23 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 276 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 06:53 | 07:03 | 0.16667 | 6535 | 6545 | 10 | Slide | 90 | 6543 | 0.85 | 219.9 | 6449.89 | -11.69 | -875.79 | -11.69 | 0.94 |  |  | 28 | 80 | 900 | 12000 | 60 | 5050 | 4380 | 670 | 189 | 210 | 190 | 175
07/20/2021 | 07:03 | 07:15 | 0.2 | 6545 | 6606 | 61 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 305 | 5050 | 4380 | 670 | 196 | 210 | 190 | 175
07/20/2021 | 07:18 | 07:30 | 0.2 | 6606 | 6700 | 94 | Rotate |  | 6637 | 0.72 | 167.1 | 6543.88 | -12.8 | -876.11 | -12.8 | 0.75 |  |  | 28 | 80 | 900 | 12000 | 470 | 5050 | 4380 | 670 | 196 | 210 | 190 | 175
07/20/2021 | 07:43 | 07:57 | 0.23333 | 6700 | 6795 | 95 | Rotate |  | 6732 | 0.47 | 206.33 | 6638.88 | -13.73 | -876.15 | -13.73 | 0.49 |  |  | 28 | 80 | 900 | 12000 | 407.14 | 5050 | 4380 | 670 | 196 | 210 | 190 | 175
07/20/2021 | 08:00 | 08:09 | 0.15 | 6795 | 6864 | 69 | Rotate |  | 6826 | 0.51 | 217.69 | 6732.87 | -14.41 | -876.57 | -14.41 | 0.11 |  |  | 25 | 80 | 900 | 13000 | 460 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 08:20 | 08:24 | 0.066667 | 6864 | 6889 | 25 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 375 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 08:28 | 08:32 | 0.066667 | 6889 | 6906 | 17 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 255 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 08:32 | 08:40 | 0.13333 | 6906 | 6919 | 13 | Slide | TTF: 90; Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 97.5 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 08:40 | 08:54 | 0.23333 | 6919 | 6982 | 63 | Rotate |  | 6919 | 0.59 | 125.8 | 6825.87 | -15.02 | -876.44 | -15.02 | 0.85 |  |  | 25 | 80 | 900 | 13000 | 270 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 08:58 | 09:10 | 0.2 | 6982 | 7077 | 95 | Rotate |  | 7014 | 1.03 | 111.51 | 6920.86 | -15.62 | -875.25 | -15.62 | 0.51 |  |  | 25 | 80 | 900 | 13000 | 475 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 09:17 | 09:40 | 0.38333 | 7077 | 7171 | 94 | Rotate |  | 7108 | 0.82 | 104.26 | 7014.85 | -16.09 | -873.81 | -16.09 | 0.26 |  |  | 25 | 80 | 900 | 13000 | 245.22 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 09:44 | 09:55 | 0.18333 | 7171 | 7264 | 93 | Rotate |  | 7201 | 0.7 | 82.9 | 7107.84 | -16.19 | -872.6 | -16.19 | 0.33 |  |  | 25 | 80 | 900 | 13000 | 507.27 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 09:59 | 10:15 | 0.26667 | 7264 | 7358 | 94 | Rotate |  | 7295 | 0.76 | 61.92 | 7201.83 | -15.82 | -871.48 | -15.82 | 0.29 |  |  | 25 | 80 | 900 | 13000 | 352.5 | 5300 | 4500 | 800 | 199 | 210 | 190 | 175
07/20/2021 | 10:19 | 10:38 | 0.31667 | 7358 | 7452 | 94 | Rotate |  | 7389 | 0.82 | 59.15 | 7295.83 | -15.18 | -870.35 | -15.18 | 0.08 |  |  | 20 | 80 | 700 | 15000 | 296.84 | 3800 | 3250 | 550 | 201 | 220 | 200 | 180
07/20/2021 | 10:42 | 11:01 | 0.31667 | 7452 | 7546 | 94 | Rotate |  | 7483 | 0.69 | 44.51 | 7389.82 | -14.43 | -869.38 | -14.43 | 0.25 |  |  | 20 | 80 | 700 | 15000 | 296.84 | 3800 | 3250 | 550 | 201 | 220 | 200 | 180
07/20/2021 | 11:06 | 11:16 | 0.16667 | 7546 | 7640 | 94 | Rotate |  | 7577 | 0.76 | 40.21 | 7483.81 | -13.55 | -868.58 | -13.55 | 0.09 |  |  | 20 | 80 | 700 | 15000 | 564 | 3800 | 3250 | 550 | 201 | 220 | 200 | 180
07/20/2021 | 11:20 | 11:42 | 0.36667 | 7640 | 7733 | 93 | Rotate |  | 7670 | 0.95 | 9.95 | 7576.8 | -12.32 | -868.05 | -12.32 | 0.52 |  |  | 20 | 80 | 700 | 15000 | 253.64 | 3800 | 3250 | 550 | 203 | 220 | 200 | 180
07/20/2021 | 11:46 | 12:00 | 0.23333 | 7733 | 7827 | 94 | Rotate |  | 7764 | 1.16 | 340.87 | 7670.78 | -10.66 | -868.23 | -10.66 | 0.6 |  |  | 20 | 80 | 700 | 15000 | 402.86 | 3800 | 3250 | 550 | 203 | 220 | 200 | 180
07/20/2021 | 12:08 | 12:12 | 0.066667 | 7827 | 7844 | 17 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 255 | 4800 | 4200 | 600 | 203 | 220 | 200 | 180
07/20/2021 | 12:12 | 12:22 | 0.16667 | 7844 | 7854 | 10 | Slide | TTF: 90; Drilling Parameters WOB: 15; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 60 | 4800 | 4200 | 600 | 203 | 220 | 200 | 180
07/20/2021 | 12:22 | 12:34 | 0.2 | 7854 | 7920 | 66 | Rotate |  | 7857 | 0.58 | 339.92 | 7763.77 | -9.33 | -868.7 | -9.33 | 0.62 |  |  | 25 | 80 | 900 | 15000 | 330 | 4800 | 4200 | 600 | 205 | 220 | 200 | 180
07/20/2021 | 12:38 | 13:01 | 0.38333 | 7920 | 8014 | 94 | Rotate |  | 7951 | 0.92 | 322.02 | 7857.77 | -8.28 | -869.32 | -8.28 | 0.44 |  |  | 30 | 80 | 900 | 16500 | 245.22 | 4800 | 4200 | 600 | 205 | 220 | 200 | 180
07/20/2021 | 13:05 | 13:16 | 0.18333 | 8014 | 8108 | 94 | Rotate |  | 8045 | 1.6 | 330.4 | 7951.74 | -6.55 | -870.44 | -6.55 | 0.75 |  |  | 30 | 80 | 900 | 16500 | 512.73 | 4800 | 4200 | 600 | 205 | 220 | 200 | 180
07/20/2021 | 13:20 | 13:23 | 0.05 | 8108 | 8132 | 24 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 480 | 4800 | 4200 | 600 | 205 | 220 | 200 | 180
07/20/2021 | 13:23 | 13:33 | 0.16667 | 8132 | 8142 | 10 | Slide | 180 | 8139 | 1.67 | 344.01 | 8045.7 | -4.09 | -871.46 | -4.09 | 0.42 |  |  | 20 | 80 | 900 | 16500 | 60 | 4800 | 4200 | 600 | 205 | 220 | 200 | 180
07/20/2021 | 13:33 | 13:45 | 0.2 | 8142 | 8202 | 60 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 300 | 4800 | 4200 | 600 | 205 | 220 | 200 | 180
07/20/2021 | 13:49 | 13:52 | 0.05 | 8202 | 8213 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 220 | 4800 | 4200 | 600 | 212 | 220 | 200 | 180
07/20/2021 | 13:52 | 14:02 | 0.16667 | 8213 | 8228 | 15 | Slide | TTF: 90; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 90 | 4800 | 4200 | 600 | 212 | 220 | 200 | 180
07/20/2021 | 14:02 | 14:14 | 0.2 | 8228 | 8295 | 67 | Rotate |  | 8232 | 1.47 | 51.42 | 8138.68 | -2.04 | -870.9 | -2.04 | 1.88 |  |  | 30 | 80 | 900 | 16500 | 335 | 4800 | 4200 | 600 | 212 | 220 | 200 | 180
07/20/2021 | 14:17 | 14:30 | 0.21667 | 8295 | 8389 | 94 | Rotate |  | 8326 | 1.48 | 60.76 | 8232.65 | -0.7 | -868.9 | -0.7 | 0.26 |  |  | 30 | 80 | 900 | 16500 | 433.85 | 4800 | 4200 | 600 | 212 | 220 | 200 | 180
07/20/2021 | 14:34 | 14:51 | 0.28333 | 8389 | 8483 | 94 | Rotate |  | 8420 | 1.39 | 53.58 | 8326.62 | 0.57 | -866.92 | 0.57 | 0.21 |  |  | 33 | 80 | 900 | 16500 | 331.76 | 4800 | 4200 | 600 | 212 | 220 | 200 | 180
07/20/2021 | 14:55 | 15:09 | 0.23333 | 8483 | 8578 | 95 | Rotate |  | 8515 | 1.43 | 61.1 | 8421.59 | 1.83 | -864.96 | 1.83 | 0.2 |  |  | 33 | 80 | 900 | 16500 | 407.14 | 4800 | 4200 | 600 | 212 | 220 | 200 | 180
07/20/2021 | 15:13 | 15:48 | 0.58333 | 8578 | 8672 | 94 | Rotate |  | 8609 | 1.07 | 50.44 | 8515.56 | 2.95 | -863.26 | 2.95 | 0.45 |  |  | 38 | 80 | 900 | 19000 | 161.14 | 5700 | 5000 | 700 | 219 | 220 | 200 | 180
07/20/2021 | 15:52 | 16:06 | 0.23333 | 8672 | 8766 | 94 | Rotate |  | 8703 | 1.06 | 40.28 | 8609.55 | 4.18 | -862.02 | 4.18 | 0.2 |  |  | 38 | 80 | 900 | 19000 | 402.86 | 5700 | 5000 | 700 | 219 | 220 | 200 | 180
07/20/2021 | 16:10 | 16:34 | 0.4 | 8766 | 8860 | 94 | Rotate |  | 8797 | 1.13 | 16.53 | 8703.53 | 5.73 | -861.19 | 5.73 | 0.48 |  |  | 38 | 80 | 900 | 19000 | 235 | 5700 | 5000 | 700 | 219 | 220 | 200 | 180
07/20/2021 | 16:38 | 17:17 | 0.65 | 8860 | 8954 | 94 | Rotate |  | 8891 | 1.08 | 15.41 | 8797.51 | 7.47 | -860.69 | 7.47 | 0.06 |  |  | 38 | 80 | 900 | 19000 | 144.62 | 5700 | 5000 | 700 | 219 | 220 | 200 | 180
07/20/2021 | 17:56 | 18:14 | 0.3 | 8954 | 9049 | 95 | Rotate |  | 8986 | 0.86 | 3.85 | 8892.5 | 9.05 | -860.41 | 9.05 | 0.31 |  |  | 29.2 | 80 | 880 | 17063 | 316.67 | 5437 | 4810 | 627 | 219 | 220 | 200 | 180
07/20/2021 | 18:18 | 18:33 | 0.25 | 9049 | 9142 | 93 | Rotate |  | 9079 | 0.83 | 1.52 | 8985.49 | 10.41 | -860.34 | 10.41 | 0.05 |  |  | 25.4 | 80 | 880 | 17438 | 372 | 5449 | 4810 | 639 | 219 | 220 | 200 | 180
07/20/2021 | 18:37 | 18:50 | 0.21667 | 9142 | 9236 | 94 | Rotate |  | 9173 | 1.15 | 4.62 | 9079.48 | 12.04 | -860.25 | 12.04 | 0.35 |  |  | 25.4 | 80 | 880 | 17338 | 433.85 | 5500 | 4810 | 690 | 219 | 220 | 200 | 180
07/20/2021 | 18:53 | 19:09 | 0.26667 | 9236 | 9330 | 94 | Rotate |  | 9267 | 0.99 | 355.47 | 9173.46 | 13.79 | -860.24 | 13.79 | 0.25 |  |  | 27.8 | 80 | 880 | 16682 | 352.5 | 5348 | 4810 | 538 | 221 | 220 | 200 | 180
07/20/2021 | 19:12 | 19:28 | 0.26667 | 9330 | 9423 | 93 | Rotate |  | 9360 | 1.29 | 328.24 | 9266.44 | 15.48 | -860.85 | 15.48 | 0.66 |  |  | 27.2 | 80 | 880 | 16006 | 348.75 | 5324 | 4781 | 543 | 223 | 245 | 225 | 175
07/20/2021 | 19:38 | 19:56 | 0.3 | 9423 | 9517 | 94 | Rotate |  | 9454 | 1.42 | 321.16 | 9360.42 | 17.28 | -862.14 | 17.28 | 0.23 |  |  | 28.2 | 80 | 880 | 16669 | 313.33 | 5342 | 4781 | 561 | 225 | 245 | 225 | 175
07/20/2021 | 19:59 | 20:14 | 0.25 | 9517 | 9612 | 95 | Rotate |  | 9549 | 0.75 | 313.13 | 9455.4 | 18.63 | -863.33 | 18.63 | 0.72 |  |  | 35 | 80 | 860 | 17301 | 380 | 5393 | 4685 | 708 | 226 | 245 | 225 | 175
07/20/2021 | 20:18 | 20:34 | 0.26667 | 9612 | 9707 | 95 | Rotate |  | 9644 | 0.95 | 325.24 | 9550.39 | 19.7 | -864.23 | 19.7 | 0.28 |  |  | 35 | 80 | 860 | 17301 | 356.25 | 5393 | 4685 | 708 | 226 | 290 | 255 | 230
07/20/2021 | 20:37 | 20:41 | 0.066667 | 9707 | 9723 | 16 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 860; Drilling Parameters Tq: 17301; Drilling Parameters ROP: 240 | 5393 | 4685 | 708 | 226 | 290 | 255 | 230
07/20/2021 | 20:41 | 20:55 | 0.23333 | 9723 | 9731 | 8 | Slide | TTF: 150; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 860; Drilling Parameters ROP: 34.29 | 4897 | 4685 | 212 | 226 | 290 | 255 | 230
07/20/2021 | 21:10 | 21:25 | 0.25 | 9731 | 9801 | 70 | Rotate |  | 9738 | 0.52 | 4 | 9644.38 | 20.76 | -864.65 | 20.76 | 0.67 |  |  | 30 | 80 | 691 | 16038 | 280 | 3769 | 3320 | 449 | 225 | 290 | 255 | 230
07/20/2021 | 21:28 | 21:47 | 0.31667 | 9801 | 9894 | 93 | Rotate |  | 9831 | 0.38 | 345.1 | 9737.38 | 21.48 | -864.7 | 21.48 | 0.22 |  |  | 34 | 80 | 860 | 16926 | 293.68 | 5394 | 4834 | 560 | 226 | 290 | 255 | 230
07/20/2021 | 21:50 | 22:19 | 0.48333 | 9894 | 9987 | 93 | Rotate |  | 9924 | 0.51 | 336.31 | 9830.38 | 22.16 | -864.94 | 22.16 | 0.16 |  |  | 35 | 80 | 860 | 15844 | 192.41 | 5198 | 4834 | 364 | 232 | 290 | 255 | 230
07/20/2021 | 22:22 | 22:46 | 0.4 | 9987 | 10082 | 95 | Rotate |  | 10019 | 0.96 | 304.32 | 9925.37 | 22.99 | -865.77 | 22.99 | 0.62 |  |  | 35 | 80 | 860 | 15844 | 237.5 | 5198 | 4834 | 364 | 232 | 290 | 255 | 230
07/20/2021 | 22:50 | 22:55 | 0.083333 | 10082 | 10094 | 12 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 691; Drilling Parameters Tq: 16875; Drilling Parameters ROP: 144 | 3836 | 3318 | 518 | 232 | 290 | 255 | 230
07/20/2021 | 22:55 | 23:20 | 0.41667 | 10094 | 10105 | 11 | Slide | TTF: 150; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 691; Drilling Parameters ROP: 26.4 | 3523 | 3318 | 205 | 232 | 290 | 255 | 230
07/20/2021 | 23:20 | 23:49 | 0.48333 | 10105 | 10175 | 70 | Rotate |  | 10112 | 1.04 | 257.64 | 10018.35 | 23.25 | -867.24 | 23.25 | 0.86 |  |  | 25 | 80 | 765 | 16382 | 144.83 | 4957 | 4570 | 387 | 232 | 290 | 255 | 230
07/20/2021 | 23:52 | 24:00 | 0.13333 | 10175 | 10210 | 35 | Rotate |  | 10207 | 1.16 | 264.5 | 10113.34 | 22.98 | -869.04 | 22.98 | 0.19 |  |  | 25 | 80 | 784 | 16382 | 262.5 | 5144 | 4730 | 414 | 232 | 290 | 255 | 230
07/21/2021 | 00:00 | 00:15 | 0.25 | 10210 | 10270 | 60 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 784; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 240 | 5411 | 4730 | 681 | 232 | 290 | 255 | 230
07/21/2021 | 00:18 | 00:23 | 0.083333 | 10270 | 10280 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 784; Drilling Parameters Tq: 17000; Drilling Parameters ROP: 120 | 5411 | 4730 | 681 | 232 | 290 | 255 | 230
07/21/2021 | 00:23 | 02:55 | 2.5333 | 10280 | 10363 | 83 | Slide | 150 | 10300 | 1.75 | 188.09 | 10206.31 | 21.48 | -870.17 | 21.48 | 2 |  |  | 12 |  | 784 |  | 32.76 | 4804 | 4661 | 143 | 230 | 310 | 260 | 245
07/21/2021 | 02:58 | 04:20 | 1.3667 | 10363 | 10410 | 47 | Slide | 150 | 10394 | 8.87 | 176.55 | 10299.85 | 12.81 | -869.94 | 12.81 | 7.62 |  |  | 14 |  | 717 |  | 34.39 | 4149 | 3832 | 317 | 230 | 310 | 260 | 245
07/21/2021 | 04:24 | 05:28 | 1.0667 | 10410 | 10457 | 47 | Slide | TTF: -40; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 717; Drilling Parameters ROP: 44.06 | 4180 | 3832 | 348 | 230 | 310 | 260 | 245
07/21/2021 | 05:36 | 05:45 | 0.15 | 10457 | 10472 | 15 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters FLOW: 717; Drilling Parameters ROP: 100 | 4180 | 3832 | 348 | 230 | 310 | 260 | 245
07/21/2021 | 05:45 | 07:36 | 1.85 | 10472 | 10552 | 80 | Slide | 0 | 10489 | 13.68 | 180.07 | 10392.99 | -5.74 | -869.51 | -5.74 | 5.11 |  |  | 18 |  | 717 |  | 43.24 | 4180 | 3832 | 348 | 230 | 310 | 260 | 245
07/21/2021 | 07:43 | 10:23 | 2.6667 | 10552 | 10646 | 94 | Slide | -60 | 10583 | 16.65 | 200.72 | 10483.77 | -29.48 | -874.29 | -29.48 | 6.51 |  |  | 18 |  | 717 |  | 35.25 | 4180 | 3832 | 348 | 230 | 310 | 260 | 245
07/21/2021 | 10:30 | 13:42 | 3.2 | 10646 | 10740 | 94 | Slide | -60 | 10677 | 20.55 | 198.52 | 10572.85 | -57.73 | -884.3 | -57.73 | 4.21 |  |  | 18 |  | 717 |  | 29.38 | 4180 | 3832 | 348 | 230 | 310 | 260 | 245
07/21/2021 | 13:49 | 16:52 | 3.05 | 10740 | 10835 | 95 | Slide | -40 | 10772 | 21.39 | 193.16 | 10661.56 | -90.41 | -893.54 | -90.41 | 2.2 |  |  | 20 |  | 800 |  | 31.15 | 5200 | 5000 | 200 | 230 | 310 | 260 | 245
07/21/2021 | 17:52 | 22:00 | 4.1333 | 10835 | 10929 | 94 | Slide | -30 | 10873 | 27.54 | 191.21 | 10753.45 | -131.29 | -902.29 | -131.29 | 6.14 |  |  | 12 |  | 669 |  | 22.74 | 3709 | 3529 | 180 | 242 | 310 | 260 | 245 | Drilled most of it on 2 pumps
07/21/2021 | 22:10 | 22:50 | 0.66667 | 10929 | 10936 | 7 | Slide | TTF: -30; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 669; Drilling Parameters ROP: 10.5 | 3709 | 3529 | 180 | 242 | 310 | 260 | 245

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6187
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 750
Well Name: |  |  |  |  | Redwood B1H |  |  | Survey / Gamma Offset: |  |  |  |  | 66.00 / 53.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.22 |  | Rotate: |  | 5437
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
09/24/2021 | 14:10 | 15:18 | 1.1333 | 10946 | 11037 | 91 | Slide | -60 | 10971 | 34.37 | 187.7 | 10837.45 | -180.99 | -910.41 | -180.99 | 7.21 |  |  | 26 |  | 300 |  | 80.29 | 3600 | 2600 | 1000 | 224 | 215 | 240 | 190
09/24/2021 | 15:28 | 16:35 | 1.1167 | 11037 | 11131 | 94 | Slide | -70 | 11065 | 46.48 | 171.82 | 10909.07 | -241.4 | -909.1 | -241.4 | 16.83 |  |  | 26 |  | 300 |  | 84.18 | 3600 | 2600 | 1000 | 235 | 215 | 240 | 190
09/24/2021 | 16:47 | 17:15 | 0.46667 | 11131 | 11171 | 40 | Rotate |  | 11160 | 52.12 | 158.41 | 10971.15 | -310.59 | -890.34 | -310.59 | 12.22 |  |  | 20 | 30 | 350 | 5.5 | 85.71 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 17:15 | 17:49 | 0.56667 | 11171 | 11226 | 55 | Slide | TTF: -60; Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 97.06 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 18:04 | 18:27 | 0.38333 | 11226 | 11256 | 30 | Slide | 0 | 11255 | 58.27 | 149.11 | 11025.43 | -380.29 | -855.72 | -380.29 | 10.31 |  |  | 20 | 30 | 350 | 5.5 | 78.26 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 18:27 | 18:55 | 0.46667 | 11256 | 11321 | 65 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 139.29 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 19:11 | 19:20 | 0.15 | 11321 | 11331 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 66.67 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 19:20 | 19:50 | 0.5 | 11331 | 11416 | 85 | Rotate |  | 11350 | 59.92 | 149.47 | 11074.22 | -450.37 | -814.1 | -450.37 | 1.77 |  |  | 20 | 30 | 350 | 5.5 | 170 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 20:00 | 20:30 | 0.5 | 11416 | 11463 | 47 | Slide | -30 | 11444 | 63.22 | 147.37 | 11118.97 | -520.77 | -770.8 | -520.77 | 4.02 |  |  | 20 | 30 | 350 | 5.5 | 94 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 20:30 | 20:50 | 0.33333 | 11463 | 11510 | 47 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 141 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 21:03 | 21:33 | 0.5 | 11510 | 11565 | 55 | Slide | -20 | 11539 | 70.52 | 142.47 | 11156.29 | -592.12 | -720.56 | -592.12 | 9.03 |  |  | 20 | 30 | 350 | 5.5 | 110 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 21:33 | 21:50 | 0.28333 | 11565 | 11605 | 40 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 141.18 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 22:02 | 22:18 | 0.26667 | 11605 | 11627 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 82.5 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 22:18 | 22:45 | 0.45 | 11627 | 11699 | 72 | Rotate |  | 11633 | 78.73 | 142.05 | 11181.19 | -663.73 | -665.13 | -663.73 | 8.74 |  |  | 20 | 30 | 350 | 5.5 | 160 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 22:58 | 23:10 | 0.2 | 11699 | 11714 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 75 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 23:10 | 23:40 | 0.5 | 11714 | 11794 | 80 | Rotate |  | 11728 | 80.94 | 142.94 | 11197.95 | -737.91 | -608.2 | -737.91 | 2.5 |  |  | 20 | 30 | 350 | 5.5 | 160 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/24/2021 | 23:53 | 24:00 | 0.11667 | 11794 | 11802 | 8 | Slide | TTF: -20; Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 68.57 | 4500 | 3700 | 800 | 239 | 215 | 240 | 190
09/25/2021 | 00:00 | 00:07 | 0.11667 | 11802 | 11816 | 14 | Slide | TTF: -20; Drilling Parameters WOB: 20; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 5.5; Drilling Parameters ROP: 120 | 4500 | 3700 | 800 |  | 215 | 240 | 190
09/25/2021 | 00:07 | 00:37 | 0.5 | 11816 | 11889 | 73 | Rotate |  | 11823 | 84.85 | 143.15 | 11209.7 | -813.23 | -551.54 | -813.23 | 4.12 |  |  | 20 | 30 | 350 | 5.5 | 146 | 4500 | 3700 | 800 |  | 215 | 240 | 190
09/25/2021 | 00:41 | 01:21 | 0.66667 | 11889 | 11983 | 94 | Rotate |  | 11917 | 86.62 | 144.18 | 11216.69 | -888.74 | -496 | -888.74 | 2.18 |  |  | 20 | 80 | 350 | 7.5 | 141 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 01:25 | 01:30 | 0.083333 | 11983 | 11996 | 13 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 156 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 01:30 | 01:43 | 0.21667 | 11996 | 12008 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 55.38 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 01:43 | 02:06 | 0.38333 | 12008 | 12078 | 70 | Rotate |  | 12012 | 84.62 | 144.11 | 11223.95 | -965.51 | -440.52 | -965.51 | 2.11 |  |  | 20 | 80 | 350 | 7.5 | 182.61 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 02:09 | 02:40 | 0.51667 | 12078 | 12173 | 95 | Rotate |  | 12107 | 84.6 | 144.15 | 11232.87 | -1042.15 | -385.1 | -1042.15 | 0.05 |  |  | 20 | 80 | 350 | 7.5 | 183.87 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 02:43 | 03:15 | 0.53333 | 12173 | 12268 | 95 | Rotate |  | 12202 | 84.4 | 144.41 | 11241.98 | -1118.92 | -329.89 | -1118.92 | 0.34 |  |  | 20 | 80 | 350 | 7.5 | 178.13 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 03:18 | 03:46 | 0.46667 | 12268 | 12363 | 95 | Rotate |  | 12297 | 84.13 | 144.29 | 11251.47 | -1195.73 | -274.8 | -1195.73 | 0.31 |  |  | 20 | 80 | 350 | 7.5 | 203.57 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 03:49 | 03:55 | 0.1 | 12363 | 12380 | 17 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 170 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 03:55 | 04:14 | 0.31667 | 12380 | 12400 | 20 | Slide | 70 | 12391 | 85.55 | 146.42 | 11259.92 | -1272.75 | -221.59 | -1272.75 | 2.72 |  |  | 25 | 80 | 350 | 7.5 | 63.16 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 04:14 | 04:33 | 0.31667 | 12400 | 12457 | 57 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 7.5; Drilling Parameters ROP: 180 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 04:38 | 05:08 | 0.5 | 12457 | 12549 | 92 | Rotate |  | 12483 | 86.35 | 147.74 | 11266.42 | -1349.78 | -171.71 | -1349.78 | 1.67 |  |  | 25 | 80 | 350 | 7.5 | 184 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 05:11 | 05:43 | 0.53333 | 12549 | 12644 | 95 | Rotate |  | 12578 | 86.32 | 148.26 | 11272.49 | -1430.18 | -121.48 | -1430.18 | 0.55 |  |  | 25 | 80 | 350 | 7.5 | 178.13 | 4700 | 3900 | 800 | 257 | 215 | 215 | 190
09/25/2021 | 05:47 | 06:18 | 0.51667 | 12644 | 12738 | 94 | Rotate |  | 12672 | 86.32 | 147.71 | 11278.53 | -1509.72 | -71.74 | -1509.72 | 0.58 |  |  | 25 | 80 | 350 | 8 | 181.94 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 06:22 | 06:34 | 0.2 | 12738 | 12753 | 15 | Slide | TTF: 90; Drilling Parameters WOB: 33; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8; Drilling Parameters ROP: 75 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 06:34 | 07:05 | 0.51667 | 12753 | 12830 | 77 | Rotate |  | 12764 | 86.45 | 149.32 | 11284.33 | -1588.01 | -23.79 | -1588.01 | 1.75 |  |  | 25 | 80 | 350 | 8 | 149.03 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 07:09 | 07:42 | 0.55 | 12830 | 12925 | 95 | Rotate |  | 12859 | 86.52 | 149.46 | 11290.15 | -1669.62 | 24.49 | -1669.62 | 0.16 |  |  | 25 | 80 | 350 | 8 | 172.73 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 07:46 | 07:59 | 0.21667 | 12925 | 12940 | 15 | Slide | TTF: 130; Drilling Parameters WOB: 33; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8; Drilling Parameters ROP: 69.23 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 07:59 | 08:32 | 0.55 | 12940 | 13019 | 79 | Rotate |  | 12953 | 84.54 | 151.22 | 11297.48 | -1751.05 | 70.86 | -1751.05 | 2.81 |  |  | 25 | 80 | 350 | 8 | 143.64 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 08:36 | 09:00 | 0.4 | 13019 | 13114 | 95 | Rotate |  | 13048 | 84.44 | 151.64 | 11306.6 | -1834.1 | 116.08 | -1834.1 | 0.45 |  |  | 25 | 80 | 350 | 8 | 237.5 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 09:04 | 09:36 | 0.53333 | 13114 | 13208 | 94 | Rotate |  | 13142 | 84.45 | 151.58 | 11315.7 | -1916.4 | 160.57 | -1916.4 | 0.06 |  |  | 25 | 80 | 350 | 8 | 176.25 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 09:40 | 09:50 | 0.16667 | 13208 | 13218 | 10 | Slide | TTF: 40; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8; Drilling Parameters ROP: 60 | 5000 | 3950 | 1050 | 279 | 240 | 215 | 190
09/25/2021 | 09:50 | 10:25 | 0.58333 | 13218 | 13303 | 85 | Rotate |  | 13237 | 85.17 | 152.63 | 11324.29 | -2000.02 | 204.83 | -2000.02 | 1.34 |  |  | 25 | 80 | 350 | 8.5 | 145.71 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 10:29 | 10:56 | 0.45 | 13303 | 13398 | 95 | Rotate |  | 13332 | 85.83 | 153 | 11331.75 | -2084.26 | 248.1 | -2084.26 | 0.8 |  |  | 25 | 80 | 350 | 8.5 | 211.11 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 11:00 | 11:28 | 0.46667 | 13398 | 13493 | 95 | Rotate |  | 13427 | 85.54 | 153.08 | 11338.9 | -2168.7 | 291.05 | -2168.7 | 0.32 |  |  | 25 | 80 | 350 | 8.5 | 203.57 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 11:32 | 11:43 | 0.18333 | 13493 | 13505 | 12 | Slide | TTF: -30; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8.5; Drilling Parameters ROP: 65.45 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 11:43 | 12:15 | 0.53333 | 13505 | 13587 | 82 | Rotate |  | 13521 | 89.34 | 152.46 | 11343.09 | -2252.18 | 334.01 | -2252.18 | 4.1 |  |  | 25 | 80 | 350 | 8.5 | 153.75 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 12:19 | 12:32 | 0.21667 | 13587 | 13602 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8.5; Drilling Parameters ROP: 69.23 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 12:32 | 13:00 | 0.46667 | 13602 | 13682 | 80 | Rotate |  | 13616 | 89.02 | 151.01 | 11344.45 | -2335.84 | 378.99 | -2335.84 | 1.56 |  |  | 25 | 80 | 350 | 8.5 | 171.43 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 13:04 | 13:12 | 0.13333 | 13682 | 13690 | 8 | Slide | TTF: 180; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8.5; Drilling Parameters ROP: 60 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 13:12 | 13:40 | 0.46667 | 13690 | 13777 | 87 | Rotate |  | 13711 | 87.67 | 150.23 | 11347.2 | -2418.59 | 425.57 | -2418.59 | 1.64 |  |  | 25 | 80 | 350 | 8.5 | 186.43 | 5050 | 4000 | 1050 | 284 | 240 | 215 | 190
09/25/2021 | 13:45 | 14:12 | 0.45 | 13777 | 13871 | 94 | Rotate |  | 13805 | 88.48 | 150.2 | 11350.35 | -2500.12 | 472.24 | -2500.12 | 0.86 |  |  | 25 | 80 | 350 | 9 | 208.89 | 5050 | 4050 | 1000 | 291 | 240 | 215 | 190
09/25/2021 | 14:16 | 14:29 | 0.21667 | 13871 | 13886 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 69.23 | 5050 | 4050 | 1000 | 291 | 240 | 215 | 190
09/25/2021 | 14:29 | 14:58 | 0.48333 | 13886 | 13965 | 79 | Rotate |  | 13899 | 86.87 | 151.22 | 11354.17 | -2582.04 | 518.19 | -2582.04 | 2.03 |  |  | 25 | 80 | 350 | 9 | 163.45 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 15:02 | 15:26 | 0.4 | 13965 | 14059 | 94 | Rotate |  | 13993 | 87.48 | 151 | 11358.8 | -2664.24 | 563.55 | -2664.24 | 0.69 |  |  | 25 | 80 | 350 | 9 | 235 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 15:30 | 15:42 | 0.2 | 14059 | 14071 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 60 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 15:42 | 16:13 | 0.51667 | 14071 | 14152 | 81 | Rotate |  | 14086 | 86.27 | 151.36 | 11363.87 | -2745.59 | 608.31 | -2745.59 | 1.36 |  |  | 25 | 80 | 350 | 9 | 156.77 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 16:17 | 16:41 | 0.4 | 14152 | 14247 | 95 | Rotate |  | 14181 | 86.38 | 150.68 | 11369.96 | -2828.53 | 654.25 | -2828.53 | 0.72 |  |  | 25 | 80 | 350 | 9 | 237.5 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 17:22 | 17:55 | 0.55 | 14247 | 14341 | 94 | Rotate |  | 14275 | 86.11 | 149.93 | 11376.12 | -2910.01 | 700.71 | -2910.01 | 0.85 |  |  | 25 | 80 | 350 | 9 | 170.91 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 17:58 | 18:24 | 0.43333 | 14341 | 14410 | 69 | Rotate |  | 14370 | 86.32 | 148.83 | 11382.39 | -2991.58 | 748.99 | -2991.58 | 1.18 |  |  | 25 | 80 | 350 | 9 | 159.23 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 18:24 | 18:47 | 0.38333 | 14410 | 14430 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 52.17 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 18:47 | 18:51 | 0.066667 | 14430 | 14436 | 6 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 90 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 18:54 | 19:25 | 0.51667 | 14436 | 14532 | 96 | Rotate |  | 14466 | 86.47 | 152 | 11388.42 | -3074.89 | 796.29 | -3074.89 | 3.3 |  |  | 25 | 80 | 350 | 9 | 185.81 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 19:28 | 19:57 | 0.48333 | 14532 | 14626 | 94 | Rotate |  | 14560 | 86.66 | 151.69 | 11394.06 | -3157.62 | 840.56 | -3157.62 | 0.39 |  |  | 25 | 80 | 350 | 9 | 194.48 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 20:00 | 20:33 | 0.55 | 14626 | 14720 | 94 | Rotate |  | 14654 | 86.35 | 151.16 | 11399.79 | -3240.01 | 885.44 | -3240.01 | 0.65 |  |  | 25 | 80 | 350 | 9 | 161.14 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 20:36 | 21:08 | 0.53333 | 14720 | 14815 | 95 | Rotate |  | 14749 | 86.91 | 150.37 | 11405.37 | -3322.77 | 931.76 | -3322.77 | 1.02 |  |  | 25 | 80 | 350 | 9 | 167.65 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 21:11 | 21:42 | 0.51667 | 14815 | 14908 | 93 | Rotate |  | 14842 | 86.42 | 149.01 | 11410.78 | -3402.92 | 978.61 | -3402.92 | 1.55 |  |  | 25 | 80 | 350 | 9 | 180 | 5050 | 4050 | 1000 | 293 | 240 | 215 | 190
09/25/2021 | 21:45 | 21:49 | 0.066667 | 14908 | 14916 | 8 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 120 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/25/2021 | 21:49 | 22:11 | 0.36667 | 14916 | 14936 | 20 | Slide | TTF: 70; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 54.55 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/25/2021 | 22:11 | 22:32 | 0.35 | 14936 | 15002 | 66 | Rotate |  | 14936 | 86.86 | 150.53 | 11416.29 | -3483.99 | 1025.86 | -3483.99 | 1.68 |  |  | 25 | 80 | 350 | 9 | 188.57 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/25/2021 | 22:35 | 22:40 | 0.083333 | 15002 | 15007 | 5 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 60 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/25/2021 | 22:40 | 23:01 | 0.35 | 15007 | 15027 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 57.14 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/25/2021 | 23:01 | 23:27 | 0.43333 | 15027 | 15097 | 70 | Rotate |  | 15031 | 85.39 | 154.29 | 11422.71 | -3567.98 | 1069.75 | -3567.98 | 4.24 |  |  | 25 | 80 | 350 | 9 | 161.54 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/25/2021 | 23:30 | 24:00 | 0.5 | 15097 | 15183 | 86 | Rotate |  | 15125 | 85.42 | 154.63 | 11430.24 | -3652.52 | 1110.14 | -3652.52 | 0.36 |  |  | 25 | 80 | 350 | 9 | 172 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 00:00 | 00:03 | 0.05 | 15183 | 15191 | 8 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 160 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 00:06 | 00:11 | 0.083333 | 15191 | 15199 | 8 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 96 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 00:11 | 00:30 | 0.31667 | 15199 | 15209 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 31.58 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 00:30 | 00:56 | 0.43333 | 15209 | 15286 | 77 | Rotate |  | 15220 | 87.47 | 154.37 | 11436.13 | -3738.1 | 1150.96 | -3738.1 | 2.18 |  |  | 25 | 80 | 350 | 9 | 177.69 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 01:00 | 01:05 | 0.083333 | 15286 | 15295 | 9 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 108 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 01:05 | 01:17 | 0.2 | 15295 | 15302 | 7 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 35 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 01:17 | 01:42 | 0.41667 | 15302 | 15381 | 79 | Rotate |  | 15315 | 87.37 | 154.46 | 11440.41 | -3823.69 | 1191.95 | -3823.69 | 0.14 |  |  | 25 | 80 | 350 | 9 | 189.6 | 5050 | 4050 | 1000 | 300 | 240 | 215 | 190
09/26/2021 | 01:46 | 01:50 | 0.066667 | 15381 | 15387 | 6 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 90 | 5050 | 4050 | 1000 | 302 | 240 | 215 | 190
09/26/2021 | 01:50 | 02:05 | 0.25 | 15387 | 15399 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 48 | 5050 | 4050 | 1000 | 302 | 240 | 215 | 190
09/26/2021 | 02:05 | 02:30 | 0.41667 | 15399 | 15476 | 77 | Rotate |  | 15410 | 84.62 | 152.31 | 11447.05 | -3908.41 | 1234.39 | -3908.41 | 3.67 |  |  | 25 | 80 | 350 | 9 | 184.8 | 5050 | 4050 | 1000 | 302 | 240 | 215 | 190
09/26/2021 | 02:34 | 03:05 | 0.51667 | 15476 | 15571 | 95 | Rotate |  | 15505 | 84.63 | 152.35 | 11455.95 | -3992.17 | 1278.31 | -3992.17 | 0.04 |  |  | 25 | 80 | 350 | 9 | 183.87 | 5050 | 4050 | 1000 | 306 | 240 | 215 | 190
09/26/2021 | 03:09 | 03:39 | 0.5 | 15571 | 15665 | 94 | Rotate |  | 15599 | 85.28 | 151.78 | 11464.21 | -4074.9 | 1322.18 | -4074.9 | 0.92 |  |  | 25 | 80 | 350 | 9 | 188 | 5050 | 4050 | 1000 | 306 | 240 | 215 | 190
09/26/2021 | 03:43 | 04:18 | 0.58333 | 15665 | 15759 | 94 | Rotate |  | 15693 | 86.07 | 151.72 | 11471.3 | -4157.47 | 1366.54 | -4157.47 | 0.84 |  |  | 25 | 80 | 350 | 9 | 161.14 | 5050 | 4050 | 1000 | 306 | 240 | 215 | 190
09/26/2021 | 04:21 | 04:53 | 0.53333 | 15759 | 15854 | 95 | Rotate |  | 15788 | 87.6 | 151.72 | 11476.55 | -4241 | 1411.48 | -4241 | 1.61 |  |  | 25 | 80 | 350 | 9 | 178.13 | 5050 | 4050 | 1000 | 306 | 240 | 215 | 190
09/26/2021 | 04:57 | 05:03 | 0.1 | 15854 | 15865 | 11 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 110 | 5050 | 4050 | 1000 | 307 | 240 | 215 | 190
09/26/2021 | 05:03 | 05:17 | 0.23333 | 15865 | 15877 | 12 | Slide | TTF: 150; Drilling Parameters WOB: 25; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 51.43 | 5050 | 4050 | 1000 | 307 | 240 | 215 | 190
09/26/2021 | 05:17 | 05:42 | 0.41667 | 15877 | 15947 | 70 | Rotate |  | 15881 | 86.43 | 151.3 | 11481.39 | -4322.62 | 1455.78 | -4322.62 | 1.34 |  |  | 25 | 80 | 350 | 9 | 168 | 5050 | 4050 | 1000 | 307 | 240 | 215 | 190
09/26/2021 | 05:46 | 06:18 | 0.53333 | 15947 | 16042 | 95 | Rotate |  | 15976 | 86.51 | 151.15 | 11487.24 | -4405.73 | 1501.43 | -4405.73 | 0.18 |  |  | 25 | 80 | 350 | 9 | 178.13 | 5050 | 4050 | 1000 | 309 | 240 | 215 | 190
09/26/2021 | 06:22 | 06:40 | 0.3 | 16042 | 16057 | 15 | Slide | TTF: 130; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 50 | 5050 | 4050 | 1000 | 309 | 240 | 215 | 190
09/26/2021 | 06:40 | 07:15 | 0.58333 | 16057 | 16136 | 79 | Rotate |  | 16070 | 84.24 | 150.69 | 11494.82 | -4487.61 | 1546.96 | -4487.61 | 2.46 |  |  | 25 | 80 | 350 | 9 | 135.43 | 5050 | 4050 | 1000 | 307 | 240 | 215 | 190
09/26/2021 | 07:19 | 07:39 | 0.33333 | 16136 | 16156 | 20 | Slide | TTF: 65; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 9; Drilling Parameters ROP: 60 | 5200 | 4300 | 900 | 307 | 265 | 215 | 160
09/26/2021 | 07:39 | 08:12 | 0.55 | 16156 | 16231 | 75 | Rotate |  | 16165 | 84.66 | 153.88 | 11504.01 | -4571.31 | 1590.93 | -4571.31 | 3.37 |  |  | 25 | 80 | 350 | 12 | 136.36 | 5200 | 4300 | 900 | 309 | 265 | 215 | 160
09/26/2021 | 08:16 | 08:51 | 0.58333 | 16231 | 16326 | 95 | Rotate |  | 16260 | 84.63 | 154.41 | 11512.87 | -4656.42 | 1632.18 | -4656.42 | 0.56 |  |  | 23 | 80 | 350 | 12 | 162.86 | 5200 | 4300 | 900 | 309 | 265 | 220 | 160
09/26/2021 | 08:55 | 09:23 | 0.46667 | 16326 | 16341 | 15 | Slide | TTF: 30; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12; Drilling Parameters ROP: 32.14 | 5200 | 4300 | 900 | 309 | 265 | 220 | 160
09/26/2021 | 09:23 | 09:52 | 0.48333 | 16341 | 16421 | 80 | Rotate |  | 16355 | 86.67 | 155.9 | 11520.08 | -4742.38 | 1671.97 | -4742.38 | 2.66 |  |  | 23 | 80 | 350 | 12 | 165.52 | 5200 | 4300 | 900 | 309 | 265 | 220 | 160
09/26/2021 | 09:56 | 10:31 | 0.58333 | 16421 | 16514 | 93 | Rotate |  | 16448 | 88.64 | 155.92 | 11523.88 | -4827.2 | 1709.9 | -4827.2 | 2.12 |  |  | 23 | 80 | 350 | 12 | 159.43 | 5200 | 4300 | 900 | 311 | 265 | 220 | 160
09/26/2021 | 10:35 | 10:52 | 0.28333 | 16514 | 16526 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12; Drilling Parameters ROP: 42.35 | 5200 | 4300 | 900 | 309 | 265 | 220 | 160
09/26/2021 | 10:52 | 11:26 | 0.56667 | 16526 | 16608 | 82 | Rotate |  | 16542 | 86.17 | 154.58 | 11528.14 | -4912.47 | 1749.21 | -4912.47 | 2.99 |  |  | 23 | 80 | 350 | 12 | 144.71 | 5200 | 4300 | 900 | 309 | 265 | 220 | 160
09/26/2021 | 11:30 | 12:02 | 0.53333 | 16608 | 16701 | 93 | Rotate |  | 16635 | 86.65 | 154.39 | 11533.96 | -4996.24 | 1789.19 | -4996.24 | 0.55 |  |  | 23 | 80 | 350 | 12 | 174.38 | 5200 | 4300 | 900 | 313 | 265 | 220 | 160
09/26/2021 | 12:06 | 12:44 | 0.63333 | 16701 | 16795 | 94 | Rotate |  | 16729 | 87.35 | 154.12 | 11538.88 | -5080.79 | 1829.96 | -5080.79 | 0.8 |  |  | 23 | 80 | 350 | 12 | 148.42 | 5200 | 4300 | 900 | 313 | 265 | 220 | 160
09/26/2021 | 12:48 | 13:27 | 0.65 | 16795 | 16890 | 95 | Rotate |  | 16824 | 88.15 | 153.99 | 11542.61 | -5166.15 | 1871.49 | -5166.15 | 0.85 |  |  | 23 | 80 | 350 | 12 | 146.15 | 5200 | 4300 | 900 | 313 | 265 | 220 | 160
09/26/2021 | 13:31 | 13:56 | 0.41667 | 16890 | 16902 | 12 | Slide | TTF: 180; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 12; Drilling Parameters ROP: 28.8 | 5200 | 4300 | 900 | 311 | 265 | 220 | 160
09/26/2021 | 13:56 | 14:37 | 0.68333 | 16902 | 16985 | 83 | Rotate |  | 16919 | 86.59 | 152.77 | 11546.97 | -5250.98 | 1914.01 | -5250.98 | 2.08 |  |  | 23 | 80 | 350 | 12 | 121.46 | 5200 | 4300 | 900 | 311 | 265 | 220 | 160
09/26/2021 | 14:41 | 15:22 | 0.68333 | 16985 | 17080 | 95 | Rotate |  | 17014 | 87.42 | 152.17 | 11551.94 | -5335.11 | 1957.86 | -5335.11 | 1.08 |  |  | 23 | 80 | 350 | 12 | 139.02 | 5200 | 4300 | 900 | 311 | 265 | 220 | 160
09/26/2021 | 15:26 | 15:51 | 0.41667 | 17080 | 17133 | 53 | Rotate |  | 17107 | 86.63 | 152.05 | 11556.76 | -5417.2 | 2001.31 | -5417.2 | 0.86 |  |  | 23 | 80 | 350 | 12 | 127.2 | 5200 | 4300 | 900 |  | 265 | 220 | 160

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2256
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 243
Well Name: |  |  |  |  | Redwood B1H |  |  | Survey / Gamma Offset: |  |  |  |  | 66.00 / 53.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.22 |  | Rotate: |  | 2013
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
09/27/2021 | 22:43 | 22:58 | 0.25 | 17133 | 17173 | 40 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 160 | 5600 | 4800 | 800 | 311 | 250 | 200 | 190
09/27/2021 | 23:01 | 23:35 | 0.56667 | 17173 | 17269 | 96 | Rotate |  | 17203 | 87.35 | 152.4 | 11561.8 | -5502.02 | 2045.98 | -5502.02 | 0.83 |  |  | 30 | 80 | 350 | 17.8 | 169.41 | 5600 | 4800 | 800 | 311 | 250 | 200 | 190
09/27/2021 | 23:40 | 24:00 | 0.33333 | 17269 | 17334 | 65 | Rotate |  | 17298 | 86.99 | 152.06 | 11566.49 | -5585.98 | 2090.19 | -5585.98 | 0.52 |  |  | 30 | 80 | 370 | 17.8 | 195 | 6000 | 5100 | 900 | 311 | 250 | 200 | 190
09/28/2021 | 00:00 | 00:10 | 0.16667 | 17334 | 17364 | 30 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 180 | 6000 | 5100 | 900 | 311 | 250 | 200 | 190
09/28/2021 | 00:14 | 00:41 | 0.45 | 17364 | 17458 | 94 | Rotate |  | 17392 | 86.73 | 151.45 | 11571.64 | -5668.66 | 2134.61 | -5668.66 | 0.7 |  |  | 30 | 80 | 370 | 17.8 | 208.89 | 6000 | 5100 | 900 | 311 | 250 | 200 | 190
09/28/2021 | 00:45 | 01:17 | 0.53333 | 17458 | 17553 | 95 | Rotate |  | 17487 | 86.91 | 150.9 | 11576.91 | -5751.76 | 2180.34 | -5751.76 | 0.61 |  |  | 30 | 80 | 370 | 17.8 | 178.13 | 6000 | 5100 | 900 | 311 | 250 | 200 | 190
09/28/2021 | 01:22 | 01:27 | 0.083333 | 17553 | 17560 | 7 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 84 | 6000 | 5100 | 900 | 320 | 250 | 200 | 190
09/28/2021 | 01:27 | 01:52 | 0.41667 | 17560 | 17578 | 18 | Slide | TTF: 120; Drilling Parameters WOB: 55; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 43.2 | 6000 | 5100 | 900 | 320 | 250 | 200 | 190
09/28/2021 | 01:52 | 02:15 | 0.38333 | 17578 | 17648 | 70 | Rotate |  | 17582 | 85.04 | 152.93 | 11583.58 | -5835.36 | 2224.95 | -5835.36 | 2.9 |  |  | 30 | 80 | 370 | 17.8 | 182.61 | 6000 | 5100 | 900 | 320 | 250 | 200 | 190
09/28/2021 | 02:20 | 02:51 | 0.51667 | 17648 | 17742 | 94 | Rotate |  | 17676 | 83.87 | 152.5 | 11592.66 | -5918.51 | 2267.84 | -5918.51 | 1.33 |  |  | 30 | 80 | 370 | 17.8 | 181.94 | 6000 | 5100 | 900 | 320 | 250 | 200 | 190
09/28/2021 | 02:55 | 03:00 | 0.083333 | 17742 | 17753 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 132 | 6000 | 5100 | 900 | 320 | 250 | 200 | 190
09/28/2021 | 03:00 | 03:28 | 0.46667 | 17753 | 17770 | 17 | Slide | TTF: 30; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 36.43 | 6000 | 5100 | 900 | 320 | 250 | 200 | 190
09/28/2021 | 03:28 | 03:51 | 0.38333 | 17770 | 17837 | 67 | Rotate |  | 17771 | 84.76 | 154.33 | 11602.07 | -6003.04 | 2310.14 | -6003.04 | 2.13 |  |  | 30 | 80 | 370 | 17.8 | 174.78 | 6000 | 5100 | 900 | 325 | 250 | 200 | 190
09/28/2021 | 03:55 | 04:00 | 0.083333 | 17837 | 17844 | 7 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 84 | 6000 | 5100 | 900 | 325 | 250 | 200 | 190
09/28/2021 | 04:00 | 04:25 | 0.41667 | 17844 | 17859 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 36 | 6000 | 5100 | 900 | 325 | 250 | 200 | 190
09/28/2021 | 04:25 | 04:50 | 0.41667 | 17859 | 17932 | 73 | Rotate |  | 17866 | 86.96 | 155.09 | 11608.93 | -6088.7 | 2350.62 | -6088.7 | 2.45 |  |  | 30 | 80 | 370 | 17.8 | 175.2 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 04:55 | 05:31 | 0.6 | 17932 | 18027 | 95 | Rotate |  | 17961 | 86.49 | 154.59 | 11614.36 | -6174.55 | 2390.94 | -6174.55 | 0.72 |  |  | 30 | 80 | 370 | 17.8 | 158.33 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 05:35 | 06:11 | 0.6 | 18027 | 18121 | 94 | Rotate |  | 18055 | 86.54 | 154.81 | 11620.07 | -6259.38 | 2431.04 | -6259.38 | 0.24 |  |  | 30 | 80 | 370 | 17.8 | 156.67 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 06:15 | 06:53 | 0.63333 | 18121 | 18217 | 96 | Rotate |  | 18151 | 86.73 | 155.59 | 11625.71 | -6346.37 | 2471.23 | -6346.37 | 0.83 |  |  | 30 | 80 | 370 | 17.8 | 151.58 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 06:57 | 07:35 | 0.63333 | 18217 | 18312 | 95 | Rotate |  | 18246 | 86.42 | 153.74 | 11631.39 | -6432.08 | 2511.81 | -6432.08 | 1.97 |  |  | 30 | 80 | 370 | 17.8 | 150 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 07:39 | 08:19 | 0.66667 | 18312 | 18406 | 94 | Rotate |  | 18340 | 86.75 | 155.13 | 11636.98 | -6516.72 | 2552.3 | -6516.72 | 1.52 |  |  | 30 | 80 | 370 | 17.8 | 141 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 08:23 | 09:01 | 0.63333 | 18406 | 18431 | 25 | Slide | TTF: -90; Drilling Parameters WOB: 55; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 39.47 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 09:01 | 09:39 | 0.63333 | 18431 | 18501 | 70 | Rotate |  | 18435 | 86.91 | 150.49 | 11642.24 | -6601.07 | 2595.63 | -6601.07 | 4.88 |  |  | 30 | 80 | 370 | 17.8 | 110.53 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 09:43 | 09:55 | 0.2 | 18501 | 18520 | 19 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 95 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 09:55 | 10:19 | 0.4 | 18520 | 18530 | 10 | Slide | -90 | 18529 | 87.06 | 146.36 | 11647.19 | -6681.03 | 2644.77 | -6681.03 | 4.39 |  |  | 55 | 80 | 370 | 17.8 | 25 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 10:19 | 10:50 | 0.51667 | 18530 | 18595 | 65 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 125.81 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 10:54 | 11:33 | 0.65 | 18595 | 18688 | 93 | Rotate |  | 18622 | 86.64 | 144.35 | 11652.3 | -6757.42 | 2697.56 | -6757.42 | 2.2 |  |  | 30 | 80 | 370 | 17.8 | 143.08 | 6000 | 5100 | 900 | 329 | 250 | 200 | 190
09/28/2021 | 11:37 | 12:17 | 0.66667 | 18688 | 18708 | 20 | Slide | TTF: 90; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 30 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 12:17 | 12:59 | 0.7 | 18708 | 18784 | 76 | Rotate |  | 18718 | 85.54 | 146.87 | 11658.85 | -6836.45 | 2751.65 | -6836.45 | 2.86 |  |  | 30 | 80 | 370 | 17.8 | 108.57 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 13:03 | 13:33 | 0.5 | 18784 | 18799 | 15 | Slide | TTF: 60; Drilling Parameters WOB: 50; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 30 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 13:33 | 14:16 | 0.71667 | 18799 | 18876 | 77 | Rotate |  | 18810 | 85.84 | 151.34 | 11665.76 | -6915.15 | 2798.75 | -6915.15 | 4.86 |  |  | 30 | 80 | 370 | 17.8 | 107.44 | 6000 | 5100 | 900 | 329 | 250 | 200 | 190
09/28/2021 | 14:20 | 15:01 | 0.68333 | 18876 | 18970 | 94 | Rotate |  | 18904 | 86.26 | 155.74 | 11672.24 | -6999.08 | 2840.52 | -6999.08 | 4.69 |  |  | 30 | 80 | 370 | 17.8 | 137.56 | 6000 | 5100 | 900 | 329 | 250 | 200 | 190
09/28/2021 | 15:05 | 15:45 | 0.66667 | 18970 | 18990 | 20 | Slide | TTF: -90; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 30 | 6000 | 5100 | 900 | 329 | 250 | 200 | 190
09/28/2021 | 15:45 | 16:09 | 0.4 | 18990 | 19028 | 38 | Rotate |  | 18998 | 87.74 | 157.79 | 11677.16 | -7085.33 | 2877.55 | -7085.33 | 2.69 |  |  | 30 | 80 | 370 | 17.8 | 95 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 16:09 | 16:48 | 0.65 | 19028 | 19041 | 13 | Slide | TTF: -90; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 20 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 16:48 | 17:01 | 0.21667 | 19041 | 19064 | 23 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 106.15 | 6000 | 5100 | 900 | 327 | 250 | 200 | 190
09/28/2021 | 17:10 | 18:02 | 0.86667 | 19064 | 19089 | 25 | Slide | TTF: -90; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 28.85 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 18:02 | 18:14 | 0.2 | 19089 | 19113 | 24 | Rotate |  | 19093 | 89.38 | 150.69 | 11679.55 | -7170.81 | 2918.8 | -7170.81 | 7.67 |  |  | 30 | 80 | 370 | 17.8 | 120 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 18:14 | 19:05 | 0.85 | 19113 | 19138 | 25 | Slide | TTF: -90; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 29.41 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 19:05 | 19:24 | 0.31667 | 19138 | 19159 | 21 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 66.32 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 19:29 | 19:33 | 0.066667 | 19159 | 19164 | 5 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 75 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 19:33 | 20:29 | 0.93333 | 19164 | 19188 | 24 | Slide | TTF: -110; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 25.71 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 20:29 | 21:06 | 0.61667 | 19188 | 19254 | 66 | Rotate |  | 19188 | 88.94 | 143.77 | 11680.95 | -7250.63 | 2970.18 | -7250.63 | 7.3 |  |  | 30 | 80 | 370 | 17.8 | 107.03 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 21:12 | 21:46 | 0.56667 | 19254 | 19307 | 53 | Rotate |  | 19283 | 90.12 | 142.71 | 11681.73 | -7326.73 | 3027.03 | -7326.73 | 1.67 |  |  | 30 | 80 | 370 | 17.8 | 93.53 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 21:46 | 22:30 | 0.73333 | 19307 | 19323 | 16 | Slide | TTF: -110; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 21.82 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 22:30 | 22:46 | 0.26667 | 19323 | 19349 | 26 | Rotate |  | 19323 | 90.95 | 140.73 | 11681.35 | -7358.13 | 3051.81 | -7358.13 | 5.37 |  |  | 30 | 80 | 370 | 17.8 | 97.5 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190
09/28/2021 | 22:50 | 23:12 | 0.36667 | 19349 | 19389 | 40 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 370; Drilling Parameters Tq: 17.8; Drilling Parameters ROP: 109.09 | 6000 | 5100 | 900 | 324 | 250 | 200 | 190