## Summary
Magnolia Oil & Gas / Rommel 3H / LTX1125821 / Patterson 248
Report Date: | 08/29/2021 | Current Depth: | 20514
Start Date: | 07/14/2021 | Casing Depth: | 11014
Daily Cost: | 10700 | Distance to TD:
Well Cost: | 187330 | Average ROP: | 0
Drilling Hours: | 27.27 | Svy MD: | 20516
24Hr Forcast: | Standby | Svy Inc: | 86.97
Current BHA: | BHA 7 | Svy Azi: | 152.22
Current BRT Hrs: | 72 | Svy TVD: | 11869.37
Bit Make / Model: | Security / GTD64M | Svy NS: | -8731.22
POOH in last 24Hrs: | Yes | Svy EW: | 5303.99
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Josh Ray | MWD Day: | Danny Veronie
Directional Driller Night: | Chris Day | MWD Night: | Chris Inman
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 333
24Hr Summary: | TD, circulate, POOH and LD BHA | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
775213 | UBHO Sub | PDCI |  | Dirty |  | 11.82 | 11.82
775225 | UBHO Sub | PDCI |  | Dirty |  | 49.03 | 49.03
500031 | UBHO Sub | PDCI |  | Clean
500046 | UBHO Sub | PDCI |  | Dirty |  | 146.73 | 146.73
775225 | UBHO Sub | PDCI |  | Dirty |  | 49.03 | 49.03
775219 | UBHO Sub | PDCI |  | Clean
500031 | UBHO Sub | PDCI |  | Clean
500046 | UBHO Sub | PDCI |  | Dirty |  | 146.73 | 146.73
500031 | UBHO | PDCI |  | Clean
500046 | UBHO | PDCI |  | Dirty |  | 146.73 | 146.73
500048 | UBHO | Pro Directional |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Rommel 3H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Total Drilled (Usft): |  | 20406 |  |  | Total Days: |  | 17
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 108 | 3523 | 3415 |  | 419.88 |  | 10.83 | 8.13 | 3.68 | 15.33
2 | 2 | 9.875 | 3523 | 11022 | 7499 |  | 190.25 |  | 8.73 | 39.42 | 9.62 | 60.75
4 | 4 | 6.75 | 11022 | 11265 | 243 |  | 11.53 |  | 100 | 21.08 | 2.42 | 31.5
5 | 5 | 6.75 | 11265 | 17945 | 6680 |  | 98.26 |  | 12.65 | 67.98 | 10.72 | 104.25
6 | 5 | 6.75 | 17945 | 17945 | 0 |  | 0 |  | 0 | 0 | 0.25 | 25.67
7 | 5 | 6.75 | 17945 | 20514 | 2569 |  | 94.22 |  | 5.76 | 27.27 | 17.02 | 72
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | 0-0- |  | 1-3-CT-S-X-I-TD |  | 1.353 | 3415 | 8.1333 | 419.88
2 | Ulterra |  | SPL613 |  | 9.875 | New |  | 0-1-CT-S-X-I-WT-TD |  | 1.491 | 7499 | 39.4167 | 190.25
4 | Security |  | GTD64M |  | 6.75 | New |  | 1-1-NO-A-X-I-NO-BHA |  | 1.491 | 243 | 21.0833 | 11.53
5 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 6680 | 67.9833 | 98.26
5 | Security |  | GTD64M |  | 6.75 |  |  |  |  | 1.491 | 0 | 0 | 0
5 | Security |  | GTD64M |  | 6.75 |  |  |  |  | 1.491 | 2569 | 27.2667 | 94.22
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 1.5 | 6.08 | 3415 |  | 419.88
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 | 8 | 2 | 6.04 | 7499 |  | 190.25
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.25 | 4.05 | 243 |  | 11.53
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.08 | 6680 |  | 98.26
6 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4.06 | 0 |  | 0
7 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2.12 | 4 | 2569 |  | 94.22
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jesse Taylor |  | Chris Day |  | Danny Veronie |  | Chris Inman |  | Brandon Parks |  | James Dyer |  | Peter Langille
Jesse Taylor Josh Ray |  | Jesse Taylor |  | Jason Smetters |  | Jason Smetters |  | Kevin Burt |  | Kevin
Josh Ray |  | Josh Ray |  |  |  | Jason Smitters |  |  |  | Kevin Cooper
Xavier Cantu
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.52 |  | 3415 |  | 419.02 |  | 1.43 / 0.00 |  | 1 |  | 8.15
INT: INTERMEDIATE |  |  | 3.99 / 1.98 |  | 7499 |  | 190.38 |  | 0.30 / 0.00 |  | 1 |  | 39.39
CRV: CURVE |  |  | 1.67 / 0.90 |  | 243 |  | 11.53 |  |  |  | 1 |  | 21.08
CRV2: CURVE 2 |  |  | 0.72 / 0.33 |  | 539 |  | 75.92 |  |  |  | 1 |  | 7.1
LAT: LATERAL |  |  | 8.61 / 7.00 |  | 8710 |  | 98.82 |  | 0.27 / 0.00 |  | 3 |  | 88.14
Total |  |  | 16.98 |  | 20406 |  | 124.53 |  | 2.00 / 0.00 |  | 6 |  | 163.86
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 108.00 | 3523.00 | 521.40 | 3045.00 | 160.17 | 370.00 | 10.83 | 3415.00 | 419.02 | 8.15 | 2.31
INT: INTERMEDIATE-BHA 2 |  |  | 3523.00 | 11022.00 | 367.36 | 6844.00 | 31.55 | 655.00 | 8.73 | 7499.00 | 190.38 | 39.39 | 20.76
CRV: CURVE-BHA 4 |  |  | 11022.00 | 11265.00 | 0.00 | 0.00 | 11.53 | 243.00 | 100.00 | 243.00 | 11.53 | 21.08 | 21.08
CRV2: CURVE 2-BHA 5 |  |  | 11265.00 | 11804.00 | 78.57 | 209.00 | 74.32 | 330.00 | 61.22 | 539.00 | 75.92 | 7.10 | 4.44
LAT: LATERAL-BHA 5 |  |  | 11804.00 | 17945.00 | 119.37 | 5626.00 | 37.40 | 515.00 | 8.39 | 6141.00 | 100.84 | 60.90 | 13.77
LAT: LATERAL-BHA 6 |  |  | 17945.00 | 17945.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
LAT: LATERAL-BHA 7 |  |  | 17945.00 | 20514.00 | 106.89 | 2421.00 | 32.24 | 148.00 | 5.76 | 2569.00 | 94.31 | 27.24 | 4.59
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1125821 | Total Drilled(Usft) | 20406.00
Operator | Magnolia Oil & Gas | Drilling Hours | 163.88
Well Name | Rommel 3H | Avg ROP(Usft/hr) | 124.52
Rig | Patterson 248 | Rotary Drilled(Usft) | 18145.00
State | Texas | Rotary Hours | 96.90
County | Washington | Rotary ROP(Usft/hr) | 187.25
Formation | Austin Chalk | Rotary % | 88.92
Start Date | 07/14/2021 | Slide Drilled(Usft) | 2261.00
End Date | 08/29/2021 | Slide Hours | 66.98
Days On Well | 17 | Slide ROP(Usft/hr) | 33.75
Start Depth (Usft) | 108.00 | Slide % | 11.08
End Depth (Usft) | 20514.00
Total Drilled (Usft) | 20406.00
# BHA's | 6
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 5.70 / 0.00
Phase Data
Phase | SUR | INT | CRV | CRV2 | LAT
Start Date | 07/14/2021 | 08/02/2021 | 08/19/2021 | 08/20/2021 | 08/21/2021
End Date | 07/15/2021 | 08/05/2021 | 08/20/2021 | 08/21/2021 | 08/29/2021
Total Days | 2.00 | 4.00 | 1.67 | 0.72 | 8.62
Start Depth (Usft) | 108.00 | 3523.00 | 11022.00 | 11265.00 | 11804.00
End Depth (Usft) | 3523.00 | 11022.00 | 11265.00 | 11804.00 | 20514.00
Total Drilled(Usft) | 3415.00 | 7499.00 | 243.00 | 539.00 | 8710.00
Drilling Hours | 8.13 | 39.42 | 21.08 | 7.10 | 88.15
Circulating Hours | 3.68 | 9.62 | 2.42 | 1.23 | 26.75
Total D&C Hours | 11.82 | 49.03 | 23.50 | 8.33 | 114.90
Avg ROP(Usft/hr) | 419.88 | 190.25 | 11.53 | 75.92 | 98.81
Rotary Drilled(Usft) | 3045.00 | 6844.00 | 0.00 | 209.00 | 8047.00
Rotary Hours | 5.82 | 18.63 | 0.00 | 2.67 | 69.78
Rotary ROP(Usft/hr) | 523.50 | 367.30 | 0.00 | 78.37 | 115.31
Rotary % | 89.17 | 91.27 | 0.00 | 38.78 | 92.39
Slide Drilled(Usft) | 370.00 | 655.00 | 243.00 | 330.00 | 663.00
Slide Hours | 2.32 | 20.78 | 21.08 | 4.43 | 18.37
Slide ROP(Usft/hr) | 159.71 | 31.52 | 11.53 | 74.44 | 36.10
Slide % | 10.83 | 8.73 | 100.00 | 61.22 | 7.61
# BHA | 1 | 1 | 1 | 1 | 3
# Motor Failures | 0 | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 1.43 / 0.00 | 1.30 / 0.00 | 0.00 / 0.00 | 0.00 / 0.00 | 2.97 / 0.00
Total Phase Hrs | 12.38 | 47.50 | 21.50 | 7.92 | 168.00
Phase ROP (Usft/hr) | 275.77 | 157.87 | 11.30 | 68.08 | 51.85
Avg Motor Yield (°/100ft) | 4.05 | 8.64 | 15.57 | 10.88 | 16.46
Avg Rotary DLS (°/100ft) | 0.33 | 0.64 | 0.00 | 0.00 | 1.38
Avg Rotary TF | 156.45 | -138.11 | 0.00 | 0.00 | 3.91
Avg Slide Length (Usft) | 17.62 | 18.71 | 60.75 | 47.14 | 14.11
# Slides | 21 | 35 | 4 | 7 | 47
BHA Data
BHA# | 1 | 2 | 4 | 5 | 6 | 7
Description | BHA 1 | BHA 2 | BHA 4 | BHA 5 | BHA 6 | BHA 7
Bit Size | 13.500 | 9.875 | 6.750 | 6.750 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Security / GTD64M | Security / GTD64M | Security / GTD64M | Security / GTD64M
Bit TFA | 1.353 | 1.491 | 1.491 | 1.491 | 1.491 | 1.491
Grade In | 0-0- | New | New | New
Grade Out | 1-3-CT-S-X-I-TD | 0-1-CT-S-X-I-WT-TD | 1-1-NO-A-X-I-NO-BHA
Motor SN | MTR775044 | PPM800058 | PPM250024 | PPM250012 | PPM250004 | PPM250016
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.9 | 7/8 / 5.9 | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 5.00 / 12.83 / 32.00 | 10.00 / 25.44 / 45.00 | 5.00 / 13.00 / 20.00 | 22.00 / 28.40 / 40.00 | 999999.00 / 0.00 / -999999.00 | 12.00 / 29.59 / 38.00
Diff P (psi) | 100.00 / 361.72 / 400.00 | 103.00 / 719.23 / 10300.00 | 100.00 / 275.00 / 450.00 | 330.00 / 656.43 / 900.00 | 999999.00 / 0.00 / -999999.00 | 150.00 / 622.96 / 761.00
Bend | 1.500 | 2.000 | 2.250 | 2.120 | 2.120 | 2.120
Date In | 07/14/2021 | 08/02/2021 | 08/19/2021 | 08/20/2021 | 08/25/2021 | 08/26/2021
Date Out | 07/15/2021 | 08/05/2021 | 08/20/2021 | 08/25/2021 | 08/26/2021 | 08/29/2021
Time In | 13:00 | 14:00 | 08:30 | 17:00 | 02:20 | 06:00
Time Out | 04:20 | 02:45 | 16:00 | 01:15 | 04:00 | 06:00
BRT Hrs | 15.33 | 60.75 | 31.50 | 104.25 | 25.67 | 72.00
Start Depth (Usft) | 108.00 | 3523.00 | 11022.00 | 11265.00 | 17945.00 | 17945.00
End Depth (Usft) | 3523.00 | 11022.00 | 11265.00 | 17945.00 | 17945.00 | 20514.00
Total Drilled(Usft) | 3415.00 | 7499.00 | 243.00 | 6680.00 | 0.00 | 2569.00
Drilling Hours | 8.13 | 39.42 | 21.08 | 67.98 | 0.00 | 27.27
Circulating Hours | 3.68 | 9.62 | 2.42 | 10.72 | 0.25 | 17.02
Total D&C Hours | 11.82 | 49.03 | 23.50 | 78.70 | 0.25 | 44.28
Avg ROP(Usft/hr) | 419.88 | 190.25 | 11.53 | 98.26 | 0.00 | 94.22
Rotary Drilled(Usft) | 3045.00 | 6844.00 | 0.00 | 5835.00 | 0.00 | 2421.00
Rotary Hours | 5.82 | 18.63 | 0.00 | 49.78 | 0.00 | 22.67
Rotary ROP(Usft/hr) | 523.50 | 367.30 | 0.00 | 117.21 | 0.00 | 106.81
Rotary % | 89.17 | 91.27 | 0.00 | 87.35 | 0.00 | 94.24
Slide Drilled(Usft) | 370.00 | 655.00 | 243.00 | 845.00 | 0.00 | 148.00
Slide Hours | 2.32 | 20.78 | 21.08 | 18.20 | 0.00 | 4.60
Slide ROP(Usft/hr) | 159.71 | 31.52 | 11.53 | 46.43 | 0.00 | 32.17
Slide % | 10.83 | 8.73 | 100.00 | 12.65 | 0.00 | 5.76
Motor Failure | NO | NO | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO | NO | NO
Unplanned Trip | NO | NO | NO | NO | YES | NO
LIH | NO | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 4.05 | 8.64 | 15.57 | 12.67 | 0.00 | 26.36
Avg Rotary DLS (°/100ft) | 0.33 | 0.64 | 0.00 | 1.01 | 0.00 | 1.11
Avg Rotary TF | 156.45 | -138.11 | 0.00 | 0.55 | 0.00 | 7.93
Avg Slide Length (Usft) | 17.62 | 18.71 | 60.75 | 19.65 | 0.00 | 13.45
# Slides | 21 | 35 | 4 | 43 | 0 | 11

## Personnel Report
|  | Job # | LTX1125821 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31159 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Rommel 3H
|  | Date: | 08/29/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Rommel 3H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Chris Day | Night DD |  | 08/21/2021 - 00:00 | 08/29/2021 - 00:00 |  | 9.00 / 0.00
Chris Inman | Night MWD |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
Chris Inman | Night MWD |  | 08/28/2021 - 00:00 | 08/29/2021 - 00:00 |  | 2.00 / 0.00
Danny Veronie | Day MWD |  | 07/14/2021 - 00:00 | 07/15/2021 - 00:00 |  | 2.00 / 0.00
Danny Veronie | Day MWD |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
Jason Smetters | Day MWD |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
Jason Smetters | Night MWD |  | 08/19/2021 - 00:00 | 08/27/2021 - 00:00 |  | 9.00 / 0.00
Jason Smitters | Night MWD |  | 07/14/2021 - 00:00 | 07/15/2021 - 00:00 |  | 2.00 / 0.00
Jesse Taylor | Day DD |  | 07/14/2021 - 00:00 | 07/15/2021 - 00:00 |  | 2.00 / 0.00
Jesse Taylor | Day DD |  | 08/21/2021 - 00:00 | 08/25/2021 - 00:00 |  | 5.00 / 0.00
Jesse Taylor | Night DD |  | 08/19/2021 - 00:00 | 08/20/2021 - 00:00 |  | 2.00 / 0.00
Jesse Taylor Josh Ray | Day DD |  | 08/26/2021 - 00:00 | 08/26/2021 - 00:00 |  | 1.00 / 0.00
Josh Ray | Day DD |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
Josh Ray | Day DD |  | 08/19/2021 - 00:00 | 08/20/2021 - 00:00 |  | 2.00 / 0.00
Josh Ray | Day DD |  | 08/27/2021 - 00:00 | 08/29/2021 - 00:00 |  | 3.00 / 0.00
Josh Ray | Night DD |  | 07/14/2021 - 00:00 | 07/15/2021 - 00:00 |  | 2.00 / 0.00
NA | Trainee 1 |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
NA | Trainee 1 |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
NA | Trainee 2 |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
NA | Trainee 2 |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
NA | Rss Eng. 1 |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
NA | Rss Eng. 1 |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
NA | Rss Eng. 2 |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
NA | Rss Eng. 2 |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
NA | Third Man |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
NA | Third Man |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
NA | Fourth Man |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
NA | Fourth Man |  | 08/19/2021 - 00:00 | 08/29/2021 - 00:00 |  | 11.00 / 0.00
Xavier Cantu | Night DD |  | 08/02/2021 - 00:00 | 08/05/2021 - 00:00 |  | 4.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1125821 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Rommel 3H | [7 empty] | Day DD: |  |  |  |  | Josh Ray | [5 empty] | API #: |  |  |  | 42-477-31159
|  |  |  | AFE #: |  |  | 20DD0327MG | [7 empty] | Night DD: |  |  |  |  | Chris Day | [5 empty] | Company Man: |  |  |  | Brandon Parks
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Danny Veronie | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Chris Inman | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 07/14/2021 | 07/15/2021 | 07/16/2021 | 07/17/2021 | 07/18/2021 | 07/19/2021 | 07/20/2021 | 07/21/2021 | 07/22/2021 | 07/23/2021 | 07/24/2021 | 07/25/2021 | 07/26/2021 | 07/27/2021 | 07/28/2021 | 07/29/2021 | 07/30/2021 | 07/31/2021 | 08/01/2021 | 08/02/2021 | 08/03/2021 | 08/04/2021 | 08/05/2021 | 08/06/2021 | 08/07/2021 | 08/08/2021 | 08/09/2021 | 08/10/2021 | 08/11/2021 | 08/12/2021 | 08/13/2021 | 08/14/2021 | 08/15/2021 | 08/16/2021 | 08/17/2021 | 08/18/2021 | 08/19/2021 | 08/20/2021 | 08/21/2021 | 08/22/2021 | 08/23/2021 | 08/24/2021 | 08/25/2021 | 08/26/2021 | 08/27/2021 | 08/28/2021 | 08/29/2021 | 08/30/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 9.875 | SPL613 |  | Steel | 56410 | 4 | 4 | [18 empty] | O | X | X | X | X
Bit | Security | 6.75 | GTD64M |  | Steel | 13618580 | 5 | 10 | [37 empty] | O | O | O | O | O | X | X | X | X | X
Bit | Security | 6.75 | GTD64M |  | Steel | 13601236 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit | Security | 6.75 | GTD64M |  | Steel | 13628581 | 7 | 12 | [35 empty] | O | X | X | X | X | X | X | X | O | O | O | O
Cross Over | Stabil Drill | 6.75 | Crossover Sub |  | Steel | SD117248 | 2 | 2 | X | X
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD117749 | 0 | 2 | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD103353 | 0 | 2 | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD118418 | 0 | 2 | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD103463 | 0 | 2 | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD107702 | 4 | 2 | O | O | [17 empty] | X | X | X | X
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD110296 | 0 | 2 | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD110972 | 0 | 2 | O | O
Cross Over | Stabil Drill | 6.75 | Crossover Sub |  | Steel | SD115348 | 0 | 4 | [18 empty] | O | O | O | O
Cross Over | Stabil Drill | 6.625 | Crossover Sub |  | Steel | SD4555 | 0 | 4 | [18 empty] | O | O | O | O
Cross Over | Stabil Drill | 6.75 | Crossover Sub |  | Steel | SD117248 | 2 | 4 | X | X | [16 empty] | O | O | O | O
Cross Over | Stabil Drill |  | Crossover Sub |  | Steel | SD117749 | 0 | 4 | [18 empty] | O | O | O | O
Cross Over | Stabil Drill | 6.5 | Crossover Sub |  | Steel | SD107702 | 4 | 4 | [18 empty] | O | X | X | X | X
Cross Over | Stabil Drill | 6.5 | Crossover Sub |  | Steel | SD110296 | 0 | 4 | [18 empty] | O | O | O | O
Cross Over | Stabil Drill | 6.5 | Crossover Sub |  | Steel | SD110972 | 0 | 4 | [18 empty] | O | O | O | O
Cross Over | Stabil Drill | 6.75 | Crossover Sub |  | Steel | SD118447 | 4 | 4 | [18 empty] | O | X | X | X | X
Cross Over | Stabil Drill | 6.625 | Crossover Sub |  | Steel | SD105593 | 0 | 4 | [18 empty] | O | O | O | O
Cross Over | Gator Tech |  | Crossover |  | Steel | GT52331059 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over | Gator Tech |  | Crossover |  | Steel | GT5233782 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over | Gator Tech | 5.188 | Crossover |  | Steel | GT52331432 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over | Gator Tech | 5.25 | Crossover |  | Steel | GT52331429 | 11 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X | X
MWD / LWD | PDCI | 7.75 | UBHO Sub |  | Steel | 775213 | 2 | 1 | X | X
MWD / LWD | PDCI |  | UBHO Sub |  | Steel | 775225 | 4 | 2 | O | O | [17 empty] | X | X | X | X
MWD / LWD | PDCI |  | UBHO Sub |  | Steel | 500031 | 0 | 2 | O | O
MWD / LWD | PDCI |  | UBHO Sub |  | Steel | 500046 | 11 | 2 | O | O | [34 empty] | X | X | X | X | X | X | X | X | X | X | X
MWD / LWD | PDCI | 7.75 | UBHO Sub |  | Steel | 775225 | 4 | 4 | [18 empty] | O | X | X | X | X
MWD / LWD | PDCI | 7.75 | UBHO Sub |  | Steel | 775219 | 0 | 4 | [18 empty] | O | O | O | O
MWD / LWD | PDCI |  | UBHO Sub |  | Steel | 500031 | 0 | 4 | [18 empty] | O | O | O | O
MWD / LWD | PDCI |  | UBHO Sub |  | Steel | 500046 | 11 | 4 | [18 empty] | O | O | O | O | [14 empty] | X | X | X | X | X | X | X | X | X | X | X
MWD / LWD | PDCI | 5.25 | UBHO |  | Steel | 500031 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD | PDCI | 5.25 | UBHO |  | Steel | 500046 | 11 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X | X
MWD / LWD | Pro Directional | 4.75 | UBHO |  | Steel | 500048 | 0 | 1 | [46 empty] | O
Motor | PDCI | 8 | 7/8 5.9 1.50 Stab HPO -.016 NBS 13 |  | Steel | MTR775044 | 2 | 2 | X | X
Motor | PDCI | 8 | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  | Steel | PPM800067 | 0 | 2 | O | O
Motor | PDCI | 8 | 7/8 5.9 1.50 Stab HPO -.011 NBS 13 |  | Steel | PPM800017 | 0 | 2 | O | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPW .006 |  | Steel | PPM800011 | 0 | 4 | [18 empty] | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPW .003 |  | Steel | PPM800034 | 0 | 4 | [18 empty] | O | O | O | O
Motor | PDCI | 8 | 7/8 5.9 2.00 Slick HPO -.014 |  | Steel | PPM800058 | 4 | 4 | [18 empty] | O | X | X | X | X
Motor | PDCI | 5.5 | 6/7 8.8 2.00 TS HS88 -.004 |  | Steel | PPM250015 | 0 | 5 | [27 empty] | O | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 .004 |  | Steel | PPM250012 | 6 | 16 | [31 empty] | O | O | O | O | O | O | X | X | X | X | X | X | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.25 TS HS88 .000 |  | Steel | PPM250024 | 2 | 15 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | O | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 .030 |  | Steel | PPM250020 | 0 | 3 | [44 empty] | O | O | O
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 .020 |  | Steel | PPM250016 | 4 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Motor | PDCI | 5.5 | 6/7 8.8 2.12 TS HS88 .026 |  | Steel | PPM250004 | 2 | 17 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X
Motor | PDCI | 5 | 7/8 3.8 2.50 TS HS88 -.004 |  | Steel | MTR500028 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor | Bico | 5.25 | 5/6 9.5 1.83 TS EW |  | Steel | BPB5550-0003 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor | Pro Power | 5.5 | 6/7 8.8 2.12 TS HS88 0.0 |  | Steel | PPM250011 | 0 | 1 | [46 empty] | O
Motor | Pro Power | 5.5 | 6/7 8.8 2.12 TS HS88 -0.001 |  | Steel | PPM250004 | 2 | 1 | [42 empty] | X | X |  |  | O
Motor | Pro Power | 5.5 | 6/7 8.8 2.12 TS HS88 +.024 |  | Steel | PPM250017 | 0 | 1 | [46 empty] | O
Stab | Stabil Drill | 8.125 | 13 Stab |  | Steel | SD603251 | 2 | 2 | X | X
Stab | Stabil Drill |  | 13 Stab |  | Steel | SD610218 | 0 | 2 | O | O
Collar | Stabil Drill | 8 | NMDC |  | Non-Mag | SD56120 | 2 | 2 | X | X
Collar | Stabil Drill | 8 | NMDC |  | Non-Mag | SD55920 | 2 | 2 | X | X
Collar | Stabil Drill |  | NMDC |  | Non-Mag | SD50132 | 0 | 2 | O | O
Collar | Stabil Drill |  | NMDC |  | Non-Mag | SD55704 | 0 | 2 | O | O
Collar | Stabil Drill | 8 | NMPC |  | Steel | SD55524 | 2 | 2 | X | X
Collar | Stabil Drill |  | NMPC |  | Steel | SD54585 | 4 | 2 | O | O | [17 empty] | X | X | X | X
Collar | Stabil Drill | 8 | NMDC |  | Non-Mag | SD50132 | 0 | 4 | [18 empty] | O | O | O | O
Collar | Stabil Drill | 8 | NMDC |  | Non-Mag | SD56047 | 0 | 4 | [18 empty] | O | O | O | O
Collar | Stabil Drill | 8 | NMDC |  | Non-Mag | SD46074 | 4 | 4 | [18 empty] | O | X | X | X | X
Collar | Stabil Drill | 7.812 | NMDC |  | Non-Mag | SD53215 | 4 | 4 | [18 empty] | O | X | X | X | X
Collar | Stabil Drill | 7.938 | NMPC |  | Steel | SD54326 | 0 | 4 | [18 empty] | O | O | O | O
Collar | Stabil Drill | 8 | NMPC |  | Steel | SD54585 | 4 | 4 | [18 empty] | O | X | X | X | X
Collar | Gator Tech | 5.25 | NMDC (NO HARDBANDING) |  | Non-Mag | GT52-30-606 | 11 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X | X
Collar | Gator Tech | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-586 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Gator Tech | 5.125 | NMDC (NO HARDBANDING) |  | Non-Mag | GT51-30-618 | 4 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Collar | Gator Tech | 5.25 | NMDC (NO HARDBANDING) |  | Non-Mag | GT52-30-458 | 8 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | O | O | O
Collar | Gator Tech | 5.25 | NMDC (NO HARDBANDING) |  | Non-Mag | GT52-30-592 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMDC (NO HARDBANDING) |  | Non-Mag | GT50-30-588 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMPC |  | Steel | GT50-10-652 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Gator Tech | 4.938 | NMPC |  | Steel | GT50-20-533 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar | Gator Tech | 5 | NMPC |  | Steel | GT50-10-479 | 5 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X
Collar | Gator Tech | 5 | NMPC |  | Steel | GT50-10-637 | 11 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X | X
Collar |  | 4.75 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT51-30-616 | 0 | 1 | [46 empty] | O
Collar |  | 4.75 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | GT50-30-481 | 0 | 1 | [46 empty] | O
Collar |  | 4.75 | Pony Collar 10' |  | Steel | GT50-10-585 | 0 | 1 | [46 empty] | O
Collar |  | 4.75 | Pony Collar 8' |  | Steel | GT51-10-622 | 0 | 1 | [46 empty] | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD105081 | 0 | 2 | O | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD119499 | 0 | 2 | O | O
Sub | Stabil Drill |  | Lift Sub |  | Steel | SD100672 | 0 | 2 | O | O
Sub | Stabil Drill |  | Lift Sub |  | Steel | SD103938 | 0 | 2 | O | O
Sub | Stabil Drill |  | Lift Cap |  | Steel | LC3377 | 0 | 2 | O | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD105081 | 0 | 4 | [18 empty] | O | O | O | O
Sub | Stabil Drill |  | Float Sub |  | Steel | SD119499 | 0 | 4 | [18 empty] | O | O | O | O
Sub | Stabil Drill | 6.625 | Lift Sub |  | Steel | SD100672 | 0 | 4 | [18 empty] | O | O | O | O
Sub | Stabil Drill | 6.625 | Lift Sub |  | Steel | SD103938 | 0 | 4 | [18 empty] | O | O | O | O
Sub | Stabil Drill |  | Lift Cap |  | Steel | LC3377 | 0 | 4 | [18 empty] | O | O | O | O
Sub | Gator Tech | 5 | Float Sub |  | Steel | GT50331370FF | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub | Gator Tech | 5 | Float Sub |  | Steel | GT50331372FF | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub | Gator Tech | 5 | Filter Sub |  | Steel | GT5033740 | 4 | 14 | [33 empty] | O | O | O | O | O | O | O | O | O | O | X | X | X | X
Sub | Gator Tech | 5 | Filter Sub |  | Steel | GT5033743 | 2 | 14 | [33 empty] | O | O | O | X | X | O | O | O | O | O | O | O | O | O
Sub | Gator Tech | 5.5 | Lift Sub |  | Steel | GT551232 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub | Gator Tech | 5.5 | Lift Sub |  | Steel | GT551251 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI Valve |  | Steel | BTI1 | 8 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | O | O | O
Sub |  | 4.875 | BTI Valve |  | Steel | 306842 | 0 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub | Tomax | 5.25 | Tomax |  | Steel | A52137 | 10 | 10 | [37 empty] | X | X | X | X | X | X | X | X | X | X
Sub |  | 4.875 | BTI Valve |  | Steel | BTI2 | 4 | 4 | [43 empty] | X | X | X | X
Sub |  | 5.25 | Tomax |  | Steel | A52123 | 0 | 2 | [45 empty] | O | O
Sub |  | 4.75 | Filter Sub |  | Steel | GT50331343 | 0 | 1 | [46 empty] | O
Sub |  | 4.75 | Filter Sub |  | Steel | GT50331291 | 0 | 1 | [46 empty] | O
Sub |  | 4.75 | Crossover |  | Steel | GT52331430 | 0 | 1 | [46 empty] | O
Sub |  | 4.75 | Crossover |  | Steel | GT52331431 | 0 | 1 | [46 empty] | O
Agitator | DWS | 6.75 | Agitator |  | Steel | PG675-0027 | 4 | 4 | [18 empty] | O | X | X | X | X
Agitator | DWS | 5.312 | Agitator |  | Steel | PG525-0051 | 6 | 12 | [35 empty] | O | O | X | X | X | X | X | X | O | O | O | O
Agitator |  | 5.312 | Agitator (On Demand) |  | Steel | PG525-0054 | 2 | 6 | [41 empty] | O | X | X | O | O | O
Agitator |  | 5.312 | Agitator (On Demand) |  | Steel | PG525-0055 | 4 | 4 | [43 empty] | X | X | X | X
Agitator |  | 5.312 | Agitator |  | Steel | PG525-0037 | 4 | 4 | [43 empty] | X | X | X | X
Agitator |  | 5.312 | Agitator |  | Steel | PG525-0050 | 0 | 2 | [45 empty] | O | O
Agitator |  | 5.312 | Agitator (Ball Drop) |  | Steel | PG525-0049 | 0 | 2 | [45 empty] | O | O
Reamer | DTI | 5.375 | Drill-N-Ream |  | Steel | 532 | 10 | 20 | [27 empty] | O | O | O | O | O | O | O | O | O | O | X | X | X | X | X | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jesse Taylor |  |  |  | 7 |  | 1 | 1 | [36 empty] | 1 | 1 | 1 | 1 | 1
Day DD |  |  | Jesse Taylor Josh Ray |  |  |  | 1 | [44 empty] | 1
Day DD |  |  | Josh Ray |  |  |  | 9 | [20 empty] | 1 | 1 | 1 | 1 | [13 empty] | 1 | 1 | [6 empty] | 1 | 1 | 1
Night DD |  |  | Chris Day |  |  |  | 9 | [39 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Jesse Taylor |  |  |  | 2 | [37 empty] | 1 | 1
Night DD |  |  | Josh Ray |  |  |  | 2 |  | 1 | 1
Night DD |  |  | Xavier Cantu |  |  |  | 4 | [20 empty] | 1 | 1 | 1 | 1
Day MWD |  |  | Danny Veronie |  |  |  | 13 |  | 1 | 1 | [34 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Day MWD |  |  | Jason Smetters |  |  |  | 4 | [20 empty] | 1 | 1 | 1 | 1
Night MWD |  |  | Chris Inman |  |  |  | 6 | [20 empty] | 1 | 1 | 1 | 1 | [22 empty] | 1 | 1
Night MWD |  |  | Jason Smetters |  |  |  | 9 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jason Smitters |  |  |  | 2 |  | 1 | 1
Third Man |  |  | NA |  |  |  | 15 | [20 empty] | 1 | 1 | 1 | 1 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Fourth Man |  |  | NA |  |  |  | 15 | [20 empty] | 1 | 1 | 1 | 1 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Rommel 3H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0327MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
SD56120 | NMDC | 8 | 28.83 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD55920 | NMDC | 8 | 28.99 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD50132 | NMDC |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD55704 | NMDC |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD55524 | NMPC | 8 | 8.58 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD54585 | NMPC |  |  |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD603251 | 13 Stab | 8.125 | 6.34 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD610218 | 13 Stab |  |  |  |  | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD117248 | Crossover Sub | 6.75 | 2.13 |  | 4 1/2 IF / 6 5/8 REG | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD117749 | Crossover Sub |  |  |  | 4 1/2 IF / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD103353 | Crossover Sub |  |  |  | 4 1/2 XH / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD118418 | Crossover Sub |  |  |  | 4 1/2 XH / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD103463 | Crossover Sub |  |  |  |  | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD107702 | Crossover Sub |  |  |  |  | Dirty | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD110296 | Crossover Sub |  |  |  |  | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD110972 | Crossover Sub |  |  |  |  | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD105081 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD119499 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD100672 | Lift Sub |  |  |  | 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
SD103938 | Lift Sub |  |  |  | 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
LC3377 | Lift Cap |  |  |  | 6 5/8 REG | Clean | Stabil Drill | 07/14/2021 |  | 07/15/2021
775213 | UBHO Sub | 7.75 | 3.66 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / UBHO Sub | 07/15/2021 |  | 07/15/2021
775225 | UBHO Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / UBHO Sub | 07/14/2021 |  | 07/15/2021
500031 | UBHO Sub |  |  |  |  | Clean | PDCI / UBHO Sub | 07/14/2021 |  | 07/15/2021
500046 | UBHO Sub |  |  |  |  | Dirty | PDCI / UBHO Sub | 07/14/2021 |  | 07/15/2021
MTR775044 | 7/8 5.9 1.50 Stab HPO -.016 NBS 13 | 8 | 37.55 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / Pro Power | 07/14/2021 |  | 07/15/2021
PPM800067 | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 | 8 | 37.27 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 07/14/2021 |  | 07/15/2021
PPM800017 | 7/8 5.9 1.50 Stab HPO -.011 NBS 13 | 8 |  |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 07/14/2021 |  | 07/15/2021
SD50132 | NMDC | 8 | 28.66 |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD56047 | NMDC | 8 | 29.12 |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD46074 | NMDC | 8 | 28.75 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD53215 | NMDC | 7.812 | 27.55 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD54326 | NMPC | 7.938 | 9.5 |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD54585 | NMPC | 8 | 9.21 |  | 6 5/8 REG / 6 5/8 REG | Dirty | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD115348 | Crossover Sub | 6.75 | 2.25 |  | 4 1/2 XH / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD4555 | Crossover Sub | 6.625 | 3 |  | 4 1/2 IF / 4 1/2 XH | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD117248 | Crossover Sub | 6.75 | 2.13 |  | 4 1/2 IF / 6 5/8 REG | Dirty | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD117749 | Crossover Sub |  |  |  | 4 1/2 IF / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD107702 | Crossover Sub | 6.5 | 2.67 |  | 4 1/2 IF / 4 1/2 XH | Dirty | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD110296 | Crossover Sub | 6.5 | 2.4 |  | 4 1/2 XH / 4 1/2 IF | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD110972 | Crossover Sub | 6.5 | 2.71 |  | 4 1/2 XH / 4 1/2 IF | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD118447 | Crossover Sub | 6.75 | 2.55 |  | 4 1/2 XH / 6 5/8 REG | Dirty | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD105593 | Crossover Sub | 6.625 | 2.56 |  | 4 1/2 IF / 4 1/2 XH | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD105081 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD119499 | Float Sub |  |  |  | 6 5/8 REG / 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD100672 | Lift Sub | 6.625 | 3.04 |  | 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
SD103938 | Lift Sub | 6.625 | 2.71 |  | 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
LC3377 | Lift Cap |  |  |  | 6 5/8 REG | Clean | Stabil Drill | 08/01/2021 |  | 08/04/2021
775225 | UBHO Sub | 7.75 | 3.97 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / UBHO Sub | 08/01/2021 |  | 08/04/2021
775219 | UBHO Sub | 7.75 | 3.78 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / UBHO Sub | 08/01/2021 |  | 08/04/2021
500031 | UBHO Sub |  |  |  | XT39 / XT39 | Clean | PDCI / UBHO Sub | 08/01/2021 |  | 08/04/2021
500046 | UBHO Sub |  |  |  | XT39 / XT39 | Dirty | PDCI / UBHO Sub | 08/01/2021 |  | 08/04/2021
PPM800011 | 7/8 5.9 2.00 Slick HPW .006 | 8 | 37.3 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 08/01/2021 |  | 08/04/2021
PPM800034 | 7/8 5.9 2.00 Slick HPW .003 | 8 | 37.72 |  | 6 5/8 REG / 6 5/8 REG | Clean | PDCI / Pro Power | 08/01/2021 |  | 08/04/2021
PPM800058 | 7/8 5.9 2.00 Slick HPO -.014 | 8 | 37.56 |  | 6 5/8 REG / 6 5/8 REG | Dirty | PDCI / Pro Power | 08/01/2021 |  | 08/04/2021
PG675-0027 | Agitator | 6.75 | 24.65 |  | 4 1/2 IF / 4 1/2 IF | Dirty | DWS / Power Glide | 08/01/2021 |  | 08/04/2021
56410 | SPL613 | 9.875 | 1.5 |  | 6 5/8 REG | Dirty |  | 08/01/2021 |  | 08/04/2021
PPM250015 | 6/7 8.8 2.00 TS HS88 -.004 | 5.5 | 33.07 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 08/10/2021 |  | 08/14/2021
PPM250012 | 6/7 8.8 2.12 TS HS88 .004 | 5.5 | 33.07 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 08/14/2021 |  | 08/29/2021
PPM250024 | 6/7 8.8 2.25 TS HS88 .000 | 5.5 | 33.07 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 08/10/2021 |  | 08/24/2021
PPM250020 | 6/7 8.8 2.12 TS HS88 .030 | 5.5 | 32.92 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 08/27/2021 |  | 08/31/2021
PPM250016 | 6/7 8.8 2.12 TS HS88 .020 | 5.5 | 33.33 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 08/10/2021 |  | 08/29/2021
PPM250004 | 6/7 8.8 2.12 TS HS88 .026 | 5.5 | 32.92 |  | XT39 / 3 1/2 Reg | Dirty | PDCI / Pro Power | 08/10/2021 |  | 08/26/2021
MTR500028 | 7/8 3.8 2.50 TS HS88 -.004 | 5 | 26.11 |  | XT39 / 3 1/2 Reg | Clean | PDCI / Pro Power | 08/10/2021 |  | 08/31/2021
BPB5550-0003 | 5/6 9.5 1.83 TS EW | 5.25 | 32 |  | XT39 / 3 1/2 Reg | Clean | Bico / SSS170 | 08/10/2021 |  | 08/31/2021
GT52-30-606 | NMDC (NO HARDBANDING) | 5.25 | 31.35 |  | XT39 / XT39 | Dirty | Gator Tech | 08/10/2021 |  | 08/29/2021
GT50-30-586 | NMDC (NO HARDBANDING) | 5 | 30.72 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT51-30-618 | NMDC (NO HARDBANDING) | 5.125 | 31.34 |  | XT39 / XT39 | Dirty | Gator Tech | 08/10/2021 |  | 08/29/2021
GT52-30-458 | NMDC (NO HARDBANDING) | 5.25 | 30.75 |  | XT39 / XT39 | Dirty | Gator Tech | 08/10/2021
GT52-30-592 | NMDC (NO HARDBANDING) | 5.25 | 31.11 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT50-30-588 | NMDC (NO HARDBANDING) | 5 | 30.7 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT50-10-652 | NMPC | 5 | 9.6 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT50-20-533 | NMPC | 4.938 | 10 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT50-10-479 | NMPC | 5 | 9.87 |  | XT39 / XT39 | Dirty | Gator Tech | 08/10/2021 |  | 08/29/2021
GT50-10-637 | NMPC | 5 | 9.17 |  | XT39 / XT39 | Dirty | Gator Tech | 08/10/2021 |  | 08/29/2021
GT52331059 | Crossover |  |  |  | DS42 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/29/2021
GT5233782 | Crossover |  |  |  | DS42 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/29/2021
GT52331432 | Crossover | 5.188 | 3.64 |  | CET43 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT52331429 | Crossover | 5.25 | 3.38 |  | CET43 / XT39 | Dirty | Gator Tech | 08/10/2021 |  | 08/29/2021
GT50331370FF | Float Sub | 5 | 3.08 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT50331372FF | Float Sub | 5 | 3.1 |  | XT39 / XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT5033740 | Filter Sub | 5 | 5.12 |  | XT39 / XT39 | Dirty | Gator Tech / Filter | 08/16/2021 |  | 08/29/2021
GT5033743 | Filter Sub | 5 | 4.95 |  | XT39 / XT39 | Dirty | Gator Tech / Filter | 08/16/2021 |  | 08/31/2021
500031 | UBHO | 5.25 | 3.7 |  | XT39 / XT39 | Clean | PDCI | 08/10/2021 |  | 08/31/2021
500046 | UBHO | 5.25 | 3.88 |  | XT39 / XT39 | Dirty | PDCI | 08/10/2021 |  | 08/29/2021
GT551232 | Lift Sub | 5.5 | 3.3 |  | XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT551251 | Lift Sub | 5.5 | 3.35 |  | XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
GT180 | Lift Cap |  |  |  | XT39 | Clean | Gator Tech | 08/10/2021 |  | 08/31/2021
532 | Drill-N-Ream | 5.375 | 8.45 |  | CET43 / CET43 | Dirty | DTI / DNR | 08/10/2021
BTI1 | BTI Valve | 4.875 | 2.03 |  | XT39 / XT39 | Dirty |  | 08/10/2021
306842 | BTI Valve | 4.875 | 2.09 |  | XT39 / XT39 | Clean |  | 08/10/2021
13618580 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Dirty | Security / GTD64M | 08/20/2021
13601236 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Clean | Security / GTD64M | 08/10/2021
13628581 | GTD64M | 6.75 | 1 |  | 3 1/2 Reg | Dirty | Security / GTD64M | 08/18/2021
PG525-0051 | Agitator | 5.312 | 21.42 |  | CET43 / CET43 | Dirty | DWS / Power Glide | 08/18/2021
A52137 | Tomax | 5.25 | 18.02 |  | XT39 / XT39 | Dirty | Tomax / Anti-Stick Slip | 08/20/2021
PG525-0054 | Agitator (On Demand) | 5.312 | 21.94 |  | CET43 / CET43 | Dirty |  | 08/24/2021
BTI2 | BTI Valve | 4.875 | 1.62 |  | XT39 / XT39 | Dirty |  | 08/26/2021
PG525-0055 | Agitator (On Demand) | 5.312 | 21.39 |  | CET43 / CET43 | Dirty |  | 08/26/2021
PG525-0037 | Agitator | 5.312 | 20.91 |  | CET43 / CET43 | Dirty |  | 08/26/2021
PG525-0050 | Agitator | 5.312 | 21.39 |  | CET43 / CET43 | Clean |  | 08/28/2021
PG525-0049 | Agitator (Ball Drop) | 5.312 | 21.39 |  | CET43 / CET43 | Clean |  | 08/28/2021
A52123 | Tomax | 5.25 | 18.02 |  | XT39 / XT39 | Clean |  | 08/28/2021
PPM250011 | 6/7 8.8 2.12 TS HS88 0.0 | 5.5 |  |  | XT39 / XT39 | Clean | Pro Power | 08/29/2021 |  | 08/31/2021
PPM250004 | 6/7 8.8 2.12 TS HS88 -0.001 | 5.5 |  |  | XT39 / XT39 | Dirty | Pro Power / Pro Power | 08/29/2021 |  | 08/31/2021
PPM250017 | 6/7 8.8 2.12 TS HS88 +.024 | 5.5 |  |  | XT39 / XT39 | Clean | Pro Power / Pro Power | 08/29/2021 |  | 08/31/2021
500048 | UBHO | 4.75 |  |  | XT39 / XT39 | Clean | Pro Directional | 08/29/2021 |  | 08/31/2021
GT51-30-616 | Non Mag Drill Collar (NO HARDBANDING) | 4.75 |  |  | XT39 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT50-30-481 | Non Mag Drill Collar (NO HARDBANDING) | 4.75 |  |  | XT39 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT50-10-585 | Pony Collar 10' | 4.75 |  |  | XT39 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT51-10-622 | Pony Collar 8' | 4.75 |  |  | XT39 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT50331343 | Filter Sub | 4.75 |  |  | XT39 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT50331291 | Filter Sub | 4.75 |  |  | XT39 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT52331430 | Crossover | 4.75 |  |  | CET43 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
GT52331431 | Crossover | 4.75 |  |  | CET43 / XT39 | Clean |  | 08/29/2021 |  | 08/31/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Rommel 3H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
U616S | 38426 | 07/14/2021 | 08/29/2021 | 47 | 1 | 1 |  | 3.68 | 8.13 | 15.33
7/8 5.9 1.50 Stab HPO -.015 NBS 13 | MTR775044 | 07/14/2021 | 07/15/2021 | 2 | 1 | 1 |  | 3.68 | 8.13 | 15.33
13 Stab | SD603251 | 07/14/2021 | 07/15/2021 | 2 | 1 | 1 |  | 3.68 | 8.13 | 15.33
NMPC | SD55524 | 07/14/2021 | 07/15/2021 | 2 | 1 | 1 |  | 3.68 | 8.13 | 15.33
UBHO Sub UBHO Sub | 775213 | 07/15/2021 | 07/15/2021 | 1 | 1 | 1 |  | 3.68 | 8.13 | 15.33
NMDC | SD56120 | 07/14/2021 | 07/15/2021 | 2 | 1 | 1 |  | 3.68 | 8.13 | 15.33
NMDC | SD55920 | 07/14/2021 | 07/15/2021 | 2 | 1 | 1 |  | 3.68 | 8.13 | 15.33
Crossover Sub | SD117248 | 08/01/2021 | 08/04/2021 | 4 | 1 | 1 |  | 3.68 | 8.13 | 15.33
SPL613 | 56410 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
7/8 5.9 2.00 Slick HPO -.014 | PPM800058 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
NMPC | SD54585 | 07/14/2021 | 07/15/2021 | 2 | 3 | 2 |  | 9.62 | 39.42 | 60.75
UBHO Sub | 775225 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Helix | 351 | 08/01/2021 | 08/04/2021 | 3 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Pulser | 6109 | 08/01/2021 | 08/04/2021 | 3 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Battery - Plug In Hrs 0.00 | 1349 | 08/01/2021 | 08/04/2021 | 3 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Gamma | 1125 | 08/01/2021 | 08/04/2021 | 3 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Directional Module | 7399 | 08/01/2021 | 08/04/2021 | 3 | 3 | 2 |  | 9.62 | 39.42 | 60.75
NMDC | SD53215 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
NMDC | SD46074 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Crossover Sub | SD118447 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Crossover Sub | SD107702 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
Agitator | PG675-0027 | 08/01/2021 | 08/04/2021 | 4 | 3 | 2 |  | 9.62 | 39.42 | 60.75
GTD64M | 13628581 | 08/18/2021 | 08/29/2021 | 12 | 6 | 4 ,5 |  | 13.13 | 89.07 | 135.75
BTI Valve | BTI1 | 08/10/2021 | 08/29/2021 | 20 | 7 | 4 ,5 ,6 |  | 13.38 | 89.07 | 161.42
6/7 8.8 2.25 TS HS88 .000 | PPM250024 | 08/10/2021 | 08/24/2021 | 15 | 1 | 4 |  | 2.42 | 21.08 | 31.5
NMPC | GT50-10-637 | 08/10/2021 | 08/29/2021 | 20 | 10 | 4 ,5 ,6 ,7 |  | 30.4 | 116.33 | 233.42
UBHO | 500046 | 07/14/2021 | 07/15/2021 | 2 | 10 | 4 ,5 ,6 ,7 |  | 30.4 | 116.33 | 233.42
Pulser | 6221 | 07/14/2021 | 07/15/2021 | 1 | 1 | 4 |  | 2.42 | 21.08 | 31.5
Battery - Plug In Hrs 0.00 | 2055 | 07/14/2021 | 07/15/2021 | 1 | 1 | 4 |  | 2.42 | 21.08 | 31.5
Gamma | 1103 | 07/14/2021 | 07/15/2021 | 1 | 1 | 4 |  | 2.42 | 21.08 | 31.5
Directional Module | 7426 | 07/14/2021 | 07/15/2021 | 1 | 1 | 4 |  | 2.42 | 21.08 | 31.5
NMDC (NO HARDBANDING) | GT52-30-606 | 08/10/2021 | 08/29/2021 | 20 | 10 | 4 ,5 ,6 ,7 |  | 30.4 | 116.33 | 233.42
NMDC (NO HARDBANDING) | GT52-30-458 | 08/10/2021 | 08/29/2021 | 20 | 7 | 4 ,5 ,6 |  | 13.38 | 89.07 | 161.42
Filter Sub | GT5033743 | 08/16/2021 | 08/31/2021 | 16 | 1 | 4 |  | 2.42 | 21.08 | 31.5
Crossover | GT52331429 | 08/10/2021 | 08/29/2021 | 20 | 10 | 4 ,5 ,6 ,7 |  | 30.4 | 116.33 | 233.42
6/7 8.8 2.12 TS HS88 .004 | PPM250012 | 08/14/2021 | 08/29/2021 | 16 | 4 | 5 |  | 10.72 | 67.98 | 104.25
Tomax | A52137 | 08/20/2021 | 08/29/2021 | 10 | 8 | 5 ,6 ,7 |  | 27.98 | 95.25 | 201.92
Drill-N-Ream | 532 | 08/10/2021 | 08/29/2021 | 20 | 8 | 5 ,6 ,7 |  | 27.98 | 95.25 | 201.92
Agitator | PG525-0051 | 08/18/2021 | 08/29/2021 | 12 | 4 | 5 |  | 10.72 | 67.98 | 104.25
GTD64M | 13618580 | 08/20/2021 | 08/29/2021 | 10 | 4 | 6 ,7 |  | 17.27 | 27.27 | 97.67
6/7 8.8 2.12 TS HS88 .026 | PPM250004 | 08/10/2021 | 08/26/2021 | 17 | 1 | 6 |  | 0.25 | 0 | 25.67
NMPC | GT50-10-479 | 08/10/2021 | 08/29/2021 | 20 | 4 | 6 ,7 |  | 17.27 | 27.27 | 97.67
Agitator | PG525-0057 | 07/14/2021 | 08/29/2021 | 47 | 1 | 6 |  | 0.25 | 0 | 25.67
Agitator (On Demand) | PG525-0054 | 08/24/2021 | 08/29/2021 | 6 | 1 | 6 |  | 0.25 | 0 | 25.67
6/7 8.8 2.12 TS HS88 .020 | PPM250016 | 08/10/2021 | 08/29/2021 | 20 | 3 | 7 |  | 17.02 | 27.27 | 72
BTI Valve | BTI2 | 08/26/2021 | 08/29/2021 | 4 | 3 | 7 |  | 17.02 | 27.27 | 72
NMDC (NO HARDBANDING) | GT51-30-618 | 08/10/2021 | 08/29/2021 | 20 | 3 | 7 |  | 17.02 | 27.27 | 72
Filter Sub | GT5033740 | 08/16/2021 | 08/29/2021 | 14 | 3 | 7 |  | 17.02 | 27.27 | 72
Agitator | PG525-0037 | 08/26/2021 | 08/29/2021 | 4 | 3 | 7 |  | 17.02 | 27.27 | 72
Agitator (On Demand) | PG525-0055 | 08/26/2021 | 08/29/2021 | 4 | 3 | 7 |  | 17.02 | 27.27 | 72
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Welll-GL: 359 + KB: 28 (Pat248)
Facility |  |  | Rommel-Redwood - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Rommel 3H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Rommel 3H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 387.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Rommel-Redwood - Washington County, TX
Map Northing |  |  | 224504.93 US survey foot |  |  | Map Easting |  |  | 3168972.23 US survey foot
Latitude |  |  | 30° 13' 49.70133" N |  |  | Longitude |  |  | 96° 37' 52.49452" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.907
Well: |  |  | Rommel 3H
Local North |  |  | 13.82 Usft |  |  | Local East |  |  | 21.29 Usft
Map Northing |  |  | 224518.30 US survey foot |  |  | Map Easting |  |  | 3168987.18 US survey foot
Latitude |  |  | 30° 13' 49.83102" N |  |  | Longitude |  |  | 96° 37' 52.24675" W
Depth Datum |  |  | Welll-GL: 359 + KB: 28 (Pat248) |  |  | Datum Elevation |  |  | 387.00 Usft
GL Elevation |  |  | 359.00 Usft
Grid Convergence |  |  | 1.907
Well bore: |  |  | Rommel 3H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 04/07/2021
Total Field (nT) |  |  | 46654.9 |  |  | Dip Angle (°) |  |  | 58.867
Declination (°) |  |  | 2.983
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 152.56
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Rommel 3H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3451 |  |  | Rommel 3H Lateral S1 |  |  | MWD+HDGM
3451 |  |  | 10956 |  |  | Rommel 3H Lateral S2 |  |  | MWD+HDGM
10956 |  |  | 11205 |  |  | Rommel 3H Lateral S3 |  |  | MWD+HDGM
11205 |  |  | 17858 |  |  | Rommel 3H Lateral S4 |  |  | MWD+HDGM
17858 |  |  | 20516 |  |  | Rommel 3H Lateral S5 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -387 | 224518.3 | 3168987.18 | 30.2305 | -96.6312 | 0
198 | 0.31 | 323.38 | 198 | 0.43 | -0.32 | -0.53 | 0.16 | 0.16 | 18.49 | 323.38 | 198 | -189 | 224518.73 | 3168986.86 | 30.2305 | -96.6312 | 323.38
289 | 0.17 | 338.7 | 289 | 0.75 | -0.52 | -0.91 | 0.17 | -0.15 | 16.84 | 162.9 | 91 | -98 | 224519.05 | 3168986.66 | 30.2305 | -96.6312 | 325.62
413 | 0.27 | 1.14 | 413 | 1.22 | -0.58 | -1.35 | 0.1 | 0.08 | 18.1 | 52.33 | 124 | 26 | 224519.52 | 3168986.6 | 30.2305 | -96.6312 | 334.65
507 | 0.1 | 29.53 | 507 | 1.51 | -0.53 | -1.58 | 0.2 | -0.18 | 30.2 | 165.36 | 94 | 120 | 224519.81 | 3168986.65 | 30.2305 | -96.6312 | 340.6
601 | 0.2 | 84.04 | 601 | 1.6 | -0.33 | -1.57 | 0.17 | 0.11 | 57.99 | 84.35 | 94 | 214 | 224519.9 | 3168986.85 | 30.2305 | -96.6312 | 348.4
695 | 0.81 | 74.28 | 694.99 | 1.8 | 0.47 | -1.37 | 0.65 | 0.65 | -10.38 | -12.93 | 94 | 307.99 | 224520.1 | 3168987.65 | 30.2305 | -96.6312 | 14.82
789 | 0.87 | 95.23 | 788.98 | 1.91 | 1.83 | -0.85 | 0.33 | 0.06 | 22.29 | 89.54 | 94 | 401.98 | 224520.21 | 3168989.01 | 30.2305 | -96.6312 | 43.7
884 | 0.68 | 103.73 | 883.97 | 1.71 | 3.09 | -0.09 | 0.23 | -0.2 | 8.95 | 153.02 | 95 | 496.97 | 224520.01 | 3168990.27 | 30.2305 | -96.6312 | 61.04
977 | 0.6 | 92.05 | 976.97 | 1.56 | 4.11 | 0.51 | 0.16 | -0.09 | -12.56 | -127.27 | 93 | 589.97 | 224519.86 | 3168991.29 | 30.2305 | -96.6312 | 69.21
1071 | 0.27 | 110.88 | 1070.97 | 1.47 | 4.81 | 0.92 | 0.38 | -0.35 | 20.03 | 165.8 | 94 | 683.97 | 224519.77 | 3168991.99 | 30.2305 | -96.6312 | 73.06
1166 | 0.76 | 129.55 | 1165.96 | 0.98 | 5.51 | 1.66 | 0.54 | 0.52 | 19.65 | 28.4 | 95 | 778.96 | 224519.28 | 3168992.69 | 30.2305 | -96.6312 | 79.86
1259 | 1.36 | 120.17 | 1258.94 | 0.04 | 6.94 | 3.16 | 0.67 | 0.65 | -10.09 | -20.85 | 93 | 871.94 | 224518.34 | 3168994.12 | 30.2305 | -96.6312 | 89.69
1354 | 2.07 | 118.8 | 1353.9 | -1.36 | 9.42 | 5.54 | 0.75 | 0.75 | -1.44 | -3.99 | 95 | 966.9 | 224516.94 | 3168996.6 | 30.2305 | -96.6312 | 98.2
1447 | 3.26 | 111.32 | 1446.8 | -3.13 | 13.35 | 8.93 | 1.33 | 1.28 | -8.04 | -20.05 | 93 | 1059.8 | 224515.17 | 3169000.53 | 30.2305 | -96.6312 | 103.18
1542 | 4.5 | 111.66 | 1541.58 | -5.48 | 19.33 | 13.78 | 1.31 | 1.31 | 0.36 | 1.23 | 95 | 1154.58 | 224512.82 | 3169006.51 | 30.2305 | -96.6311 | 105.84
1635 | 5.33 | 112.56 | 1634.24 | -8.49 | 26.71 | 19.84 | 0.9 | 0.89 | 0.97 | 5.76 | 93 | 1247.24 | 224509.81 | 3169013.89 | 30.2305 | -96.6311 | 107.63
1729 | 6.09 | 113.29 | 1727.77 | -12.13 | 35.32 | 27.05 | 0.81 | 0.81 | 0.78 | 5.82 | 94 | 1340.77 | 224506.17 | 3169022.5 | 30.2305 | -96.6311 | 108.96
1822 | 7.04 | 114.59 | 1820.16 | -16.46 | 45.04 | 35.36 | 1.03 | 1.02 | 1.4 | 9.54 | 93 | 1433.16 | 224501.84 | 3169032.22 | 30.2305 | -96.6311 | 110.07
1917 | 7.77 | 112.92 | 1914.37 | -21.38 | 56.25 | 44.89 | 0.8 | 0.77 | -1.76 | -17.26 | 95 | 1527.37 | 224496.92 | 3169043.43 | 30.2304 | -96.631 | 110.81
2012 | 8.11 | 114.64 | 2008.46 | -26.68 | 68.25 | 55.13 | 0.44 | 0.36 | 1.81 | 35.8 | 95 | 1621.46 | 224491.62 | 3169055.43 | 30.2304 | -96.631 | 111.35
2106 | 8.81 | 113.04 | 2101.43 | -32.26 | 80.9 | 65.91 | 0.79 | 0.74 | -1.7 | -19.38 | 94 | 1714.43 | 224486.04 | 3169068.08 | 30.2304 | -96.6309 | 111.74
2200 | 9.8 | 109.52 | 2194.2 | -37.75 | 95.07 | 77.31 | 1.21 | 1.05 | -3.74 | -31.64 | 94 | 1807.2 | 224480.55 | 3169082.25 | 30.2304 | -96.6309 | 111.66
2293 | 10.84 | 107.76 | 2285.69 | -43.06 | 110.86 | 89.3 | 1.17 | 1.12 | -1.89 | -17.73 | 93 | 1898.69 | 224475.24 | 3169098.04 | 30.2304 | -96.6309 | 111.23
2387 | 10.73 | 111.73 | 2378.03 | -49 | 127.4 | 102.19 | 0.8 | -0.12 | 4.22 | 100.37 | 94 | 1991.03 | 224469.3 | 3169114.58 | 30.2304 | -96.6308 | 111.04
2481 | 10.69 | 112.44 | 2470.39 | -55.56 | 143.59 | 115.48 | 0.15 | -0.04 | 0.76 | 107.21 | 94 | 2083.39 | 224462.74 | 3169130.77 | 30.2303 | -96.6308 | 111.15
2575 | 10.32 | 110.42 | 2562.82 | -61.83 | 159.54 | 128.39 | 0.56 | -0.39 | -2.15 | -136.12 | 94 | 2175.82 | 224456.47 | 3169146.72 | 30.2303 | -96.6307 | 111.18
2669 | 9.97 | 109.93 | 2655.35 | -67.54 | 175.08 | 140.62 | 0.38 | -0.37 | -0.52 | -166.39 | 94 | 2268.35 | 224450.76 | 3169162.26 | 30.2303 | -96.6307 | 111.1
2763 | 9.2 | 107.55 | 2748.04 | -72.58 | 189.89 | 151.92 | 0.92 | -0.82 | -2.53 | -153.94 | 94 | 2361.04 | 224445.72 | 3169177.07 | 30.2303 | -96.6306 | 110.92
2857 | 9.09 | 107.44 | 2840.84 | -77.07 | 204.14 | 162.47 | 0.12 | -0.12 | -0.12 | -171.02 | 94 | 2453.84 | 224441.23 | 3169191.32 | 30.2303 | -96.6306 | 110.68
2952 | 9.3 | 109.74 | 2934.62 | -81.91 | 218.53 | 173.4 | 0.45 | 0.22 | 2.42 | 61.4 | 95 | 2547.62 | 224436.39 | 3169205.71 | 30.2303 | -96.6305 | 110.55
3046 | 9.75 | 110.2 | 3027.32 | -87.23 | 233.15 | 184.85 | 0.49 | 0.48 | 0.49 | 9.83 | 94 | 2640.32 | 224431.07 | 3169220.33 | 30.2302 | -96.6305 | 110.51
3139 | 9.73 | 111.92 | 3118.98 | -92.88 | 247.83 | 196.63 | 0.31 | -0.02 | 1.85 | 94.78 | 93 | 2731.98 | 224425.42 | 3169235.01 | 30.2302 | -96.6304 | 110.54
3233 | 9.06 | 111.75 | 3211.72 | -98.59 | 262.07 | 208.26 | 0.71 | -0.71 | -0.18 | -177.71 | 94 | 2824.72 | 224419.71 | 3169249.25 | 30.2302 | -96.6304 | 110.62
3326 | 9.01 | 109.77 | 3303.57 | -103.76 | 275.72 | 219.15 | 0.34 | -0.05 | -2.13 | -100.11 | 93 | 2916.57 | 224414.54 | 3169262.9 | 30.2302 | -96.6303 | 110.62
3451 | 9.26 | 111.97 | 3426.98 | -110.84 | 294.26 | 233.97 | 0.34 | 0.2 | 1.76 | 55.5 | 125 | 3039.98 | 224407.46 | 3169281.44 | 30.2302 | -96.6303 | 110.64
3538 | 9.17 | 111.33 | 3512.86 | -115.98 | 307.21 | 244.5 | 0.16 | -0.1 | -0.74 | -131.6 | 87 | 3125.86 | 224402.32 | 3169294.39 | 30.2302 | -96.6302 | 110.68
3632 | 8.31 | 121.5 | 3605.77 | -122.25 | 319.98 | 255.95 | 1.88 | -0.91 | 10.82 | 124.06 | 94 | 3218.77 | 224396.05 | 3169307.16 | 30.2301 | -96.6302 | 110.91
3726 | 9.38 | 115.82 | 3698.66 | -129.14 | 332.67 | 267.91 | 1.47 | 1.14 | -6.04 | -42.05 | 94 | 3311.66 | 224389.16 | 3169319.85 | 30.2301 | -96.6302 | 111.22
3819 | 9.9 | 111.35 | 3790.34 | -135.35 | 346.94 | 280 | 0.98 | 0.56 | -4.81 | -57.43 | 93 | 3403.34 | 224382.95 | 3169334.12 | 30.2301 | -96.6301 | 111.31
3913 | 10.17 | 111.79 | 3882.91 | -141.37 | 362.17 | 292.36 | 0.3 | 0.29 | 0.47 | 16.07 | 94 | 3495.91 | 224376.93 | 3169349.35 | 30.2301 | -96.6301 | 111.32
4007 | 10.25 | 111.21 | 3975.42 | -147.48 | 377.67 | 304.92 | 0.14 | 0.09 | -0.62 | -52.4 | 94 | 3588.42 | 224370.82 | 3169364.85 | 30.2301 | -96.63 | 111.33
4102 | 10.06 | 113.58 | 4068.93 | -153.86 | 393.16 | 317.72 | 0.48 | -0.2 | 2.49 | 115.61 | 95 | 3681.93 | 224364.44 | 3169380.34 | 30.23 | -96.63 | 111.37
4195 | 11.11 | 113.5 | 4160.35 | -160.68 | 408.82 | 330.99 | 1.13 | 1.13 | -0.09 | -0.84 | 93 | 3773.35 | 224357.62 | 3169396 | 30.23 | -96.6299 | 111.46
4289 | 11.42 | 111.41 | 4252.54 | -167.69 | 425.79 | 345.03 | 0.55 | 0.33 | -2.22 | -53.82 | 94 | 3865.54 | 224350.61 | 3169412.97 | 30.23 | -96.6299 | 111.5
4382 | 11.08 | 112.44 | 4343.75 | -174.46 | 442.62 | 358.8 | 0.42 | -0.37 | 1.11 | 149.92 | 93 | 3956.75 | 224343.84 | 3169429.8 | 30.23 | -96.6298 | 111.51
4476 | 11.16 | 111.87 | 4435.98 | -181.29 | 459.41 | 372.6 | 0.14 | 0.09 | -0.61 | -54.24 | 94 | 4048.98 | 224337.01 | 3169446.59 | 30.23 | -96.6298 | 111.54
4571 | 10.92 | 109.62 | 4529.23 | -187.74 | 476.42 | 386.16 | 0.52 | -0.25 | -2.37 | -120.22 | 95 | 4142.23 | 224330.56 | 3169463.6 | 30.2299 | -96.6297 | 111.51
4666 | 10.4 | 108.74 | 4622.59 | -193.52 | 493.01 | 398.94 | 0.57 | -0.55 | -0.93 | -163.05 | 95 | 4235.59 | 224324.78 | 3169480.19 | 30.2299 | -96.6297 | 111.43
4759 | 10.18 | 108.84 | 4714.09 | -198.87 | 508.74 | 410.93 | 0.24 | -0.24 | 0.11 | 175.41 | 93 | 4327.09 | 224319.43 | 3169495.92 | 30.2299 | -96.6296 | 111.35
4853 | 9.64 | 107.04 | 4806.69 | -203.86 | 524.13 | 422.45 | 0.66 | -0.57 | -1.91 | -151.04 | 94 | 4419.69 | 224314.44 | 3169511.31 | 30.2299 | -96.6296 | 111.25
4947 | 10.91 | 109.38 | 4899.18 | -209.12 | 540.04 | 434.45 | 1.42 | 1.35 | 2.49 | 19.35 | 94 | 4512.18 | 224309.18 | 3169527.22 | 30.2299 | -96.6295 | 111.17
5041 | 10.65 | 109.8 | 4991.52 | -215.01 | 556.61 | 447.32 | 0.29 | -0.28 | 0.45 | 163.39 | 94 | 4604.52 | 224303.29 | 3169543.79 | 30.2299 | -96.6295 | 111.12
5134 | 10.93 | 110.12 | 5082.88 | -220.95 | 572.97 | 460.13 | 0.31 | 0.3 | 0.34 | 12.23 | 93 | 4695.88 | 224297.35 | 3169560.15 | 30.2298 | -96.6294 | 111.09
5228 | 10.44 | 108.07 | 5175.25 | -226.66 | 589.44 | 472.78 | 0.66 | -0.52 | -2.18 | -143.2 | 94 | 4788.25 | 224291.64 | 3169576.62 | 30.2298 | -96.6294 | 111.03
5322 | 9.92 | 106.59 | 5267.77 | -231.61 | 605.29 | 484.49 | 0.62 | -0.55 | -1.57 | -154.02 | 94 | 4880.77 | 224286.69 | 3169592.47 | 30.2298 | -96.6293 | 110.94
5416 | 9.98 | 105.56 | 5360.35 | -236.11 | 620.9 | 495.67 | 0.2 | 0.06 | -1.1 | -71.88 | 94 | 4973.35 | 224282.19 | 3169608.08 | 30.2298 | -96.6293 | 110.82
5510 | 10.24 | 114.11 | 5452.9 | -241.71 | 636.37 | 507.77 | 1.62 | 0.28 | 9.1 | 84.4 | 94 | 5065.9 | 224276.59 | 3169623.55 | 30.2298 | -96.6292 | 110.8
5603 | 10.76 | 115.3 | 5544.34 | -248.8 | 651.77 | 521.15 | 0.61 | 0.56 | 1.28 | 23.22 | 93 | 5157.34 | 224269.5 | 3169638.95 | 30.2298 | -96.6292 | 110.89
5697 | 10.9 | 113.21 | 5636.67 | -256.05 | 667.87 | 535.01 | 0.44 | 0.15 | -2.22 | -71.41 | 94 | 5249.67 | 224262.25 | 3169655.05 | 30.2297 | -96.6291 | 110.98
5791 | 10.06 | 108.74 | 5729.1 | -262.19 | 683.81 | 547.81 | 1.24 | -0.89 | -4.76 | -138.12 | 94 | 5342.1 | 224256.11 | 3169670.99 | 30.2297 | -96.6291 | 110.98
5885 | 8.85 | 105.16 | 5821.82 | -266.72 | 698.57 | 558.62 | 1.43 | -1.29 | -3.81 | -155.84 | 94 | 5434.82 | 224251.58 | 3169685.75 | 30.2297 | -96.629 | 110.9
5978 | 9.82 | 115.15 | 5913.59 | -271.96 | 712.65 | 569.77 | 2.03 | 1.04 | 10.74 | 64.09 | 93 | 5526.59 | 224246.34 | 3169699.83 | 30.2297 | -96.629 | 110.89
6072 | 10.23 | 116.84 | 6006.16 | -279.14 | 727.36 | 582.91 | 0.54 | 0.44 | 1.8 | 36.5 | 94 | 5619.16 | 224239.16 | 3169714.54 | 30.2297 | -96.6289 | 111
6166 | 9.62 | 114.42 | 6098.75 | -286.15 | 741.96 | 595.87 | 0.79 | -0.65 | -2.57 | -146.82 | 94 | 5711.75 | 224232.15 | 3169729.14 | 30.2297 | -96.6289 | 111.09
6260 | 8.72 | 111.01 | 6191.55 | -291.95 | 755.76 | 607.38 | 1.12 | -0.96 | -3.63 | -150.55 | 94 | 5804.55 | 224226.35 | 3169742.94 | 30.2296 | -96.6288 | 111.12
6353 | 8.63 | 114.52 | 6283.49 | -297.38 | 768.69 | 618.15 | 0.58 | -0.1 | 3.77 | 101.38 | 93 | 5896.49 | 224220.92 | 3169755.87 | 30.2296 | -96.6288 | 111.15
6448 | 8.25 | 114.69 | 6377.46 | -303.18 | 781.37 | 629.14 | 0.4 | -0.4 | 0.18 | 176.33 | 95 | 5990.46 | 224215.12 | 3169768.55 | 30.2296 | -96.6288 | 111.21
6542 | 8.74 | 115.12 | 6470.43 | -309.03 | 793.96 | 640.14 | 0.53 | 0.52 | 0.46 | 7.6 | 94 | 6083.43 | 224209.27 | 3169781.14 | 30.2296 | -96.6287 | 111.27
6636 | 8.46 | 111.54 | 6563.37 | -314.6 | 806.86 | 651.02 | 0.64 | -0.3 | -3.81 | -119.37 | 94 | 6176.37 | 224203.7 | 3169794.04 | 30.2296 | -96.6287 | 111.3
6731 | 8.43 | 111.86 | 6657.34 | -319.76 | 819.82 | 661.58 | 0.06 | -0.03 | 0.34 | 122.71 | 95 | 6270.34 | 224198.54 | 3169807 | 30.2296 | -96.6286 | 111.31
6825 | 7.46 | 114.02 | 6750.44 | -324.81 | 831.79 | 671.57 | 1.08 | -1.03 | 2.3 | 163.96 | 94 | 6363.44 | 224193.49 | 3169818.97 | 30.2295 | -96.6286 | 111.33
6919 | 7.44 | 111.9 | 6843.64 | -329.56 | 843.01 | 680.96 | 0.29 | -0.02 | -2.26 | -95.21 | 94 | 6456.64 | 224188.74 | 3169830.19 | 30.2295 | -96.6286 | 111.35
7013 | 7.41 | 106.37 | 6936.86 | -333.54 | 854.48 | 689.77 | 0.76 | -0.03 | -5.88 | -95.14 | 94 | 6549.86 | 224184.76 | 3169841.66 | 30.2295 | -96.6285 | 111.32
7106 | 8.04 | 104.56 | 7029.01 | -336.87 | 866.52 | 698.28 | 0.73 | 0.68 | -1.95 | -22.01 | 93 | 6642.01 | 224181.43 | 3169853.7 | 30.2295 | -96.6285 | 111.24
7200 | 8.57 | 107.09 | 7122.03 | -340.58 | 879.58 | 707.59 | 0.68 | 0.56 | 2.69 | 35.84 | 94 | 6735.03 | 224177.72 | 3169866.76 | 30.2295 | -96.6285 | 111.17
7294 | 9 | 109.96 | 7214.92 | -345.15 | 893.19 | 717.91 | 0.65 | 0.46 | 3.05 | 46.97 | 94 | 6827.92 | 224173.15 | 3169880.37 | 30.2295 | -96.6284 | 111.13
7388 | 8.47 | 114.49 | 7307.83 | -350.53 | 906.4 | 728.77 | 0.92 | -0.56 | 4.82 | 129.84 | 94 | 6920.83 | 224167.77 | 3169893.58 | 30.2295 | -96.6284 | 111.14
7482 | 8.8 | 118.36 | 7400.77 | -356.81 | 919.03 | 740.17 | 0.71 | 0.35 | 4.12 | 62.33 | 94 | 7013.77 | 224161.49 | 3169906.2 | 30.2294 | -96.6283 | 111.22
7577 | 8.01 | 116.52 | 7494.75 | -363.22 | 931.34 | 751.53 | 0.88 | -0.83 | -1.94 | -162.11 | 95 | 7107.75 | 224155.08 | 3169918.52 | 30.2294 | -96.6283 | 111.31
7671 | 8.46 | 119.84 | 7587.78 | -369.58 | 943.2 | 762.65 | 0.7 | 0.48 | 3.53 | 48.23 | 94 | 7200.78 | 224148.72 | 3169930.38 | 30.2294 | -96.6283 | 111.4
7764 | 7.21 | 121.34 | 7679.91 | -376.02 | 954.12 | 773.39 | 1.36 | -1.34 | 1.61 | 171.45 | 93 | 7292.91 | 224142.28 | 3169941.3 | 30.2294 | -96.6282 | 111.51
7858 | 7.16 | 115.38 | 7773.17 | -381.6 | 964.45 | 783.11 | 0.79 | -0.05 | -6.34 | -96.79 | 94 | 7386.17 | 224136.7 | 3169951.63 | 30.2294 | -96.6282 | 111.59
7952 | 6.39 | 116.22 | 7866.52 | -386.42 | 974.44 | 791.99 | 0.83 | -0.82 | 0.89 | 173.08 | 94 | 7479.52 | 224131.88 | 3169961.62 | 30.2294 | -96.6282 | 111.63
8046 | 4.42 | 110.76 | 7960.09 | -390.02 | 982.52 | 798.9 | 2.16 | -2.1 | -5.81 | -168.08 | 94 | 7573.09 | 224128.28 | 3169969.7 | 30.2293 | -96.6281 | 111.65
8140 | 2.35 | 117.88 | 8053.93 | -392.2 | 987.61 | 803.19 | 2.24 | -2.2 | 7.57 | 172.06 | 94 | 7666.93 | 224126.1 | 3169974.79 | 30.2293 | -96.6281 | 111.66
8234 | 2.73 | 120.61 | 8147.83 | -394.25 | 991.24 | 806.67 | 0.42 | 0.4 | 2.9 | 19.03 | 94 | 7760.83 | 224124.05 | 3169978.42 | 30.2293 | -96.6281 | 111.69
8328 | 3.42 | 113.53 | 8241.7 | -396.5 | 995.74 | 810.75 | 0.84 | 0.73 | -7.53 | -32.4 | 94 | 7854.7 | 224121.8 | 3169982.92 | 30.2293 | -96.6281 | 111.71
8422 | 2.88 | 113.85 | 8335.56 | -398.58 | 1000.47 | 814.77 | 0.57 | -0.57 | 0.34 | 178.29 | 94 | 7948.56 | 224119.72 | 3169987.65 | 30.2293 | -96.6281 | 111.72
8516 | 2.76 | 107.26 | 8429.44 | -400.21 | 1004.79 | 818.2 | 0.37 | -0.13 | -7.01 | -113.58 | 94 | 8042.44 | 224118.09 | 3169991.97 | 30.2293 | -96.6281 | 111.72
8610 | 2.37 | 96.66 | 8523.35 | -401.1 | 1008.88 | 820.89 | 0.65 | -0.41 | -11.28 | -134.64 | 94 | 8136.35 | 224117.2 | 3169996.06 | 30.2293 | -96.628 | 111.68
8705 | 1.46 | 85.59 | 8618.29 | -401.24 | 1012.04 | 822.46 | 1.03 | -0.96 | -11.65 | -163.35 | 95 | 8231.29 | 224117.06 | 3169999.22 | 30.2293 | -96.628 | 111.63
8799 | 1.07 | 42.42 | 8712.27 | -400.5 | 1013.82 | 822.63 | 1.06 | -0.41 | -45.93 | -132.87 | 94 | 8325.27 | 224117.8 | 3170001 | 30.2293 | -96.628 | 111.56
8893 | 1.63 | 14.92 | 8806.25 | -398.56 | 1014.76 | 821.34 | 0.89 | 0.6 | -29.26 | -63.46 | 94 | 8419.25 | 224119.74 | 3170001.94 | 30.2293 | -96.628 | 111.44
8987 | 1.78 | 351.48 | 8900.21 | -395.82 | 1014.89 | 818.97 | 0.75 | 0.16 | 24.94 | -89.74 | 94 | 8513.21 | 224122.48 | 3170002.07 | 30.2293 | -96.628 | 111.31
9080 | 2.3 | 339.93 | 8993.15 | -392.64 | 1014.03 | 815.75 | 0.71 | 0.56 | -12.42 | -44.2 | 93 | 8606.15 | 224125.66 | 3170001.21 | 30.2293 | -96.628 | 111.17
9174 | 2.59 | 325.39 | 9087.06 | -389.12 | 1012.18 | 811.77 | 0.73 | 0.31 | -15.47 | -72.32 | 94 | 8700.06 | 224129.18 | 3169999.36 | 30.2293 | -96.628 | 111.03
9268 | 2.23 | 334.46 | 9180.98 | -385.72 | 1010.18 | 807.84 | 0.56 | -0.38 | 9.65 | 137.82 | 94 | 8793.98 | 224132.58 | 3169997.36 | 30.2294 | -96.628 | 110.9
9362 | 2.59 | 325.52 | 9274.9 | -382.32 | 1008.19 | 803.9 | 0.55 | 0.38 | -9.51 | -50.76 | 94 | 8887.9 | 224135.98 | 3169995.37 | 30.2294 | -96.6281 | 110.77
9455 | 2.41 | 326.2 | 9367.81 | -378.96 | 1005.92 | 799.87 | 0.2 | -0.19 | 0.73 | 170.98 | 93 | 8980.81 | 224139.34 | 3169993.1 | 30.2294 | -96.6281 | 110.64
9549 | 2.27 | 285.28 | 9461.74 | -376.83 | 1003.02 | 796.65 | 1.75 | -0.15 | -43.53 | -115.03 | 94 | 9074.74 | 224141.47 | 3169990.2 | 30.2294 | -96.6281 | 110.59
9643 | 2.63 | 279.07 | 9555.65 | -376 | 999.09 | 794.1 | 0.48 | 0.38 | -6.61 | -39.53 | 94 | 9168.65 | 224142.3 | 3169986.27 | 30.2294 | -96.6281 | 110.62
9737 | 1.81 | 247.53 | 9649.58 | -376.23 | 995.59 | 792.69 | 1.53 | -0.87 | -33.55 | -138.95 | 94 | 9262.58 | 224142.07 | 3169982.77 | 30.2294 | -96.6281 | 110.7
9830 | 1.45 | 239.48 | 9742.55 | -377.39 | 993.22 | 792.62 | 0.46 | -0.39 | -8.66 | -151.52 | 93 | 9355.55 | 224140.91 | 3169980.4 | 30.2294 | -96.6281 | 110.8
9924 | 1.03 | 228.29 | 9836.52 | -378.55 | 991.57 | 792.9 | 0.51 | -0.45 | -11.9 | -155.55 | 94 | 9449.52 | 224139.75 | 3169978.75 | 30.2294 | -96.6281 | 110.9
10018 | 0.84 | 238.15 | 9930.51 | -379.48 | 990.35 | 793.16 | 0.26 | -0.2 | 10.49 | 144.6 | 94 | 9543.51 | 224138.82 | 3169977.53 | 30.2294 | -96.6281 | 110.97
10111 | 1.28 | 261.06 | 10023.49 | -380 | 988.75 | 792.88 | 0.65 | 0.47 | 24.63 | 55.77 | 93 | 9636.49 | 224138.3 | 3169975.93 | 30.2294 | -96.6281 | 111.02
10205 | 1.26 | 267.74 | 10117.47 | -380.2 | 986.68 | 792.11 | 0.16 | -0.02 | 7.11 | 101.02 | 94 | 9730.47 | 224138.1 | 3169973.86 | 30.2294 | -96.6281 | 111.07
10299 | 1.69 | 304.48 | 10211.44 | -379.46 | 984.5 | 790.45 | 1.08 | 0.46 | 39.09 | 84.66 | 94 | 9824.44 | 224138.84 | 3169971.68 | 30.2294 | -96.6281 | 111.08
10393 | 1.8 | 296.49 | 10305.4 | -378.02 | 982.04 | 788.03 | 0.28 | 0.12 | -8.5 | -69.7 | 94 | 9918.4 | 224140.28 | 3169969.22 | 30.2294 | -96.6281 | 111.05
10487 | 1.01 | 308.82 | 10399.37 | -376.84 | 980.07 | 786.08 | 0.9 | -0.84 | 13.12 | 165.15 | 94 | 10012.37 | 224141.46 | 3169967.25 | 30.2294 | -96.6281 | 111.03
10581 | 1.53 | 108.37 | 10493.36 | -376.72 | 980.62 | 786.22 | 2.66 | 0.55 | 169.73 | 167.66 | 94 | 10106.36 | 224141.58 | 3169967.8 | 30.2294 | -96.6281 | 111.01
10675 | 6.8 | 127.47 | 10587.08 | -380.5 | 986.23 | 792.16 | 5.72 | 5.61 | 20.32 | 24.42 | 94 | 10200.08 | 224137.8 | 3169973.41 | 30.2294 | -96.6281 | 111.1
10769 | 13.04 | 138.23 | 10679.64 | -391.81 | 997.72 | 807.49 | 6.9 | 6.64 | 11.45 | 21.91 | 94 | 10292.64 | 224126.49 | 3169984.9 | 30.2293 | -96.6281 | 111.44
10863 | 14.75 | 147.45 | 10770.9 | -409.8 | 1011.23 | 829.69 | 2.97 | 1.82 | 9.81 | 56.86 | 94 | 10383.9 | 224108.5 | 3169998.41 | 30.2293 | -96.628 | 112.06
10956 | 16.39 | 150.04 | 10860.48 | -431.15 | 1024.15 | 854.59 | 1.91 | 1.76 | 2.78 | 24.22 | 93 | 10473.48 | 224087.15 | 3170011.33 | 30.2292 | -96.628 | 112.83
11110 | 27.89 | 151.95 | 11002.89 | -481.94 | 1052.03 | 912.51 | 7.48 | 7.47 | 1.24 | 4.48 | 154 | 10615.89 | 224036.36 | 3170039.21 | 30.2291 | -96.6279 | 114.61
11205 | 42.79 | 149.26 | 11080.17 | -529.55 | 1079.13 | 967.26 | 15.77 | 15.68 | -2.83 | -7.09 | 95 | 10693.17 | 223988.75 | 3170066.31 | 30.229 | -96.6278 | 116.14
11248 | 50.44 | 150.22 | 11109.68 | -556.53 | 1094.85 | 998.45 | 17.86 | 17.79 | 2.23 | 5.55 | 43 | 10722.68 | 223961.77 | 3170082.03 | 30.2289 | -96.6278 | 116.95
11342 | 54.61 | 151.34 | 11166.86 | -621.63 | 1131.24 | 1072.99 | 4.54 | 4.44 | 1.19 | 12.38 | 94 | 10779.86 | 223896.67 | 3170118.42 | 30.2287 | -96.6277 | 118.79
11437 | 65.54 | 154.65 | 11214.19 | -694.92 | 1168.44 | 1155.18 | 11.89 | 11.51 | 3.48 | 15.56 | 95 | 10827.19 | 223823.38 | 3170155.62 | 30.2285 | -96.6276 | 120.74
11531 | 69.07 | 154.8 | 11250.46 | -773.33 | 1205.46 | 1241.83 | 3.76 | 3.76 | 0.16 | 2.27 | 94 | 10863.46 | 223744.97 | 3170192.64 | 30.2283 | -96.6275 | 122.68
11626 | 70.2 | 155.18 | 11283.52 | -854.04 | 1243.11 | 1330.81 | 1.25 | 1.19 | 0.4 | 17.56 | 95 | 10896.52 | 223664.26 | 3170230.29 | 30.228 | -96.6274 | 124.49
11721 | 79.14 | 154.15 | 11308.61 | -936.76 | 1282.3 | 1422.27 | 9.47 | 9.41 | -1.08 | -6.48 | 95 | 10921.61 | 223581.54 | 3170269.48 | 30.2278 | -96.6272 | 126.15
11815 | 94.01 | 154.96 | 11314.21 | -1021.25 | 1322.49 | 1515.78 | 15.84 | 15.82 | 0.86 | 3.15 | 94 | 10927.21 | 223497.05 | 3170309.67 | 30.2276 | -96.6271 | 127.68
11910 | 92.3 | 154.01 | 11308.98 | -1106.85 | 1363.35 | 1610.58 | 2.06 | -1.8 | -1 | -150.95 | 95 | 10921.98 | 223411.45 | 3170350.53 | 30.2273 | -96.627 | 129.07
12005 | 90.05 | 153.42 | 11307.03 | -1192 | 1405.41 | 1705.54 | 2.45 | -2.37 | -0.62 | -165.3 | 95 | 10920.03 | 223326.3 | 3170392.59 | 30.2271 | -96.6269 | 130.3
12100 | 86.86 | 153.31 | 11309.59 | -1276.88 | 1447.98 | 1800.48 | 3.36 | -3.36 | -0.12 | -178.03 | 95 | 10922.59 | 223241.42 | 3170435.16 | 30.2269 | -96.6268 | 131.41
12194 | 80.74 | 151.24 | 11319.74 | -1359.56 | 1491.42 | 1893.88 | 6.87 | -6.51 | -2.2 | -161.52 | 94 | 10932.74 | 223158.74 | 3170478.6 | 30.2266 | -96.6266 | 132.35
12289 | 82.38 | 151.68 | 11333.68 | -1442.11 | 1536.31 | 1987.83 | 1.79 | 1.73 | 0.46 | 14.9 | 95 | 10946.68 | 223076.19 | 3170523.49 | 30.2264 | -96.6265 | 133.19
12384 | 84.7 | 152.1 | 11344.37 | -1525.37 | 1580.79 | 2082.21 | 2.48 | 2.44 | 0.44 | 10.22 | 95 | 10957.37 | 222992.93 | 3170567.97 | 30.2262 | -96.6264 | 133.98
12475 | 84.93 | 151.82 | 11352.59 | -1605.36 | 1623.39 | 2172.84 | 0.4 | 0.25 | -0.31 | -50.5 | 91 | 10965.59 | 222912.94 | 3170610.57 | 30.2259 | -96.6262 | 134.68
12570 | 86.6 | 151.72 | 11359.61 | -1688.83 | 1668.2 | 2267.56 | 1.76 | 1.76 | -0.11 | -3.42 | 95 | 10972.61 | 222829.47 | 3170655.38 | 30.2257 | -96.6261 | 135.35
12665 | 86.46 | 150.72 | 11365.36 | -1771.94 | 1713.85 | 2362.36 | 1.06 | -0.15 | -1.05 | -98.01 | 95 | 10978.36 | 222746.36 | 3170701.03 | 30.2255 | -96.626 | 135.95
12757 | 86.46 | 148.95 | 11371.04 | -1851.33 | 1759.99 | 2454.08 | 1.92 | 0 | -1.92 | -90.05 | 92 | 10984.04 | 222666.97 | 3170747.17 | 30.2253 | -96.6258 | 136.45
12852 | 86.6 | 147.38 | 11376.79 | -1931.88 | 1810.01 | 2548.62 | 1.66 | 0.15 | -1.65 | -84.94 | 95 | 10989.79 | 222586.42 | 3170797.19 | 30.225 | -96.6257 | 136.87
12946 | 86.77 | 147.58 | 11382.23 | -2011.01 | 1860.46 | 2642.1 | 0.28 | 0.18 | 0.21 | 49.59 | 94 | 10995.23 | 222507.29 | 3170847.64 | 30.2248 | -96.6255 | 137.23
13041 | 86.79 | 149.08 | 11387.56 | -2091.74 | 1910.26 | 2736.69 | 1.58 | 0.02 | 1.58 | 89.28 | 95 | 11000.56 | 222426.56 | 3170897.44 | 30.2246 | -96.6254 | 137.6
13135 | 88.52 | 151.77 | 11391.41 | -2173.41 | 1956.61 | 2830.53 | 3.4 | 1.84 | 2.86 | 57.29 | 94 | 11004.41 | 222344.89 | 3170943.79 | 30.2244 | -96.6252 | 138
13230 | 87.97 | 153.32 | 11394.32 | -2257.67 | 2000.38 | 2925.48 | 1.73 | -0.58 | 1.63 | 109.57 | 95 | 11007.32 | 222260.63 | 3170987.56 | 30.2241 | -96.6251 | 138.46
13325 | 87.38 | 153.96 | 11398.17 | -2342.72 | 2042.53 | 3020.39 | 0.92 | -0.62 | 0.67 | 132.71 | 95 | 11011.17 | 222175.58 | 3171029.71 | 30.2239 | -96.625 | 138.92
13419 | 86.57 | 154.88 | 11403.13 | -2427.39 | 2083.06 | 3114.2 | 1.3 | -0.86 | 0.98 | 131.42 | 94 | 11016.13 | 222090.91 | 3171070.24 | 30.2236 | -96.6249 | 139.37
13514 | 83.15 | 151.6 | 11411.65 | -2511.85 | 2125.64 | 3208.79 | 4.98 | -3.6 | -3.45 | -136.45 | 95 | 11024.65 | 222006.45 | 3171112.82 | 30.2234 | -96.6247 | 139.76
13609 | 83.66 | 152.27 | 11422.56 | -2595.12 | 2170.04 | 3303.15 | 0.88 | 0.54 | 0.71 | 52.58 | 95 | 11035.56 | 221923.18 | 3171157.22 | 30.2232 | -96.6246 | 140.1
13703 | 83.86 | 152.04 | 11432.77 | -2677.75 | 2213.69 | 3396.59 | 0.32 | 0.21 | -0.24 | -48.83 | 94 | 11045.77 | 221840.55 | 3171200.87 | 30.2229 | -96.6245 | 140.42
13798 | 85.81 | 152.81 | 11441.33 | -2761.61 | 2257.48 | 3491.2 | 2.21 | 2.05 | 0.81 | 21.5 | 95 | 11054.33 | 221756.69 | 3171244.66 | 30.2227 | -96.6243 | 140.74
13891 | 86.91 | 152.5 | 11447.23 | -2844.05 | 2300.11 | 3584.01 | 1.23 | 1.18 | -0.33 | -15.72 | 93 | 11060.23 | 221674.25 | 3171287.29 | 30.2225 | -96.6242 | 141.04
13985 | 85.91 | 153.17 | 11453.12 | -2927.51 | 2342.94 | 3677.83 | 1.28 | -1.06 | 0.71 | 146.25 | 94 | 11066.12 | 221590.79 | 3171330.12 | 30.2222 | -96.6241 | 141.33
14079 | 86.25 | 153.3 | 11459.54 | -3011.25 | 2385.18 | 3771.6 | 0.39 | 0.36 | 0.14 | 20.88 | 94 | 11072.54 | 221507.05 | 3171372.36 | 30.222 | -96.624 | 141.62
14173 | 87.6 | 153.56 | 11464.58 | -3095.2 | 2427.16 | 3865.45 | 1.46 | 1.44 | 0.28 | 10.89 | 94 | 11077.58 | 221423.1 | 3171414.34 | 30.2218 | -96.6238 | 141.9
14268 | 85.61 | 153.75 | 11470.21 | -3180.18 | 2469.24 | 3960.26 | 2.1 | -2.09 | 0.2 | 174.56 | 95 | 11083.21 | 221338.12 | 3171456.42 | 30.2215 | -96.6237 | 142.17
14363 | 85.62 | 153.8 | 11477.47 | -3265.15 | 2511.1 | 4054.96 | 0.05 | 0.01 | 0.05 | 78.66 | 95 | 11090.47 | 221253.15 | 3171498.28 | 30.2213 | -96.6236 | 142.44
14458 | 85.39 | 153.92 | 11484.92 | -3350.17 | 2552.83 | 4149.65 | 0.27 | -0.24 | 0.13 | 152.52 | 95 | 11097.92 | 221168.13 | 3171540.01 | 30.2211 | -96.6235 | 142.69
14552 | 85.51 | 153.61 | 11492.38 | -3434.22 | 2594.25 | 4243.33 | 0.35 | 0.13 | -0.33 | -68.79 | 94 | 11105.38 | 221084.08 | 3171581.43 | 30.2208 | -96.6234 | 142.93
14647 | 85.7 | 153.6 | 11499.66 | -3519.07 | 2636.36 | 4338.03 | 0.2 | 0.2 | -0.01 | -3 | 95 | 11112.66 | 220999.23 | 3171623.54 | 30.2206 | -96.6232 | 143.16
14742 | 88.01 | 154.35 | 11504.87 | -3604.3 | 2677.97 | 4432.85 | 2.56 | 2.43 | 0.79 | 17.98 | 95 | 11117.87 | 220914 | 3171665.15 | 30.2204 | -96.6231 | 143.39
14834 | 85.89 | 153.98 | 11509.76 | -3686.98 | 2718 | 4524.68 | 2.34 | -2.3 | -0.4 | -170.12 | 92 | 11122.76 | 220831.32 | 3171705.18 | 30.2201 | -96.623 | 143.6
14928 | 86.05 | 154.14 | 11516.37 | -3771.3 | 2759.02 | 4618.42 | 0.24 | 0.17 | 0.17 | 44.93 | 94 | 11129.37 | 220747 | 3171746.2 | 30.2199 | -96.6229 | 143.81
15023 | 84.8 | 153.39 | 11523.95 | -3856.24 | 2800.88 | 4713.09 | 1.53 | -1.32 | -0.79 | -149.15 | 95 | 11136.95 | 220662.06 | 3171788.06 | 30.2197 | -96.6227 | 144.01
15117 | 85.2 | 153.11 | 11532.14 | -3939.86 | 2843.03 | 4806.73 | 0.52 | 0.43 | -0.3 | -34.9 | 94 | 11145.14 | 220578.44 | 3171830.21 | 30.2194 | -96.6226 | 144.19
15213 | 86.97 | 154.37 | 11538.69 | -4025.75 | 2885.4 | 4902.48 | 2.26 | 1.84 | 1.31 | 35.43 | 96 | 11151.69 | 220492.55 | 3171872.58 | 30.2192 | -96.6225 | 144.37
15307 | 88.26 | 154.1 | 11542.61 | -4110.33 | 2926.23 | 4996.35 | 1.4 | 1.37 | -0.29 | -11.82 | 94 | 11155.61 | 220407.97 | 3171913.41 | 30.2189 | -96.6224 | 144.55
15402 | 87.35 | 153.43 | 11546.24 | -4195.48 | 2968.19 | 5091.26 | 1.19 | -0.96 | -0.71 | -143.67 | 95 | 11159.24 | 220322.82 | 3171955.37 | 30.2187 | -96.6222 | 144.72
15497 | 85.58 | 152.26 | 11552.1 | -4279.84 | 3011.46 | 5186.07 | 2.23 | -1.86 | -1.23 | -146.62 | 95 | 11165.1 | 220238.46 | 3171998.64 | 30.2185 | -96.6221 | 144.87
15591 | 85.67 | 151.95 | 11559.27 | -4362.68 | 3055.31 | 5279.8 | 0.34 | 0.1 | -0.33 | -73.78 | 94 | 11172.27 | 220155.62 | 3172042.49 | 30.2182 | -96.622 | 145
15686 | 86.15 | 152.06 | 11566.05 | -4446.35 | 3099.79 | 5374.55 | 0.52 | 0.51 | 0.12 | 12.88 | 95 | 11179.05 | 220071.95 | 3172086.97 | 30.218 | -96.6219 | 145.12
15780 | 87.08 | 152.45 | 11571.6 | -4529.39 | 3143.47 | 5468.38 | 1.07 | 0.99 | 0.41 | 22.73 | 94 | 11184.6 | 219988.91 | 3172130.65 | 30.2178 | -96.6217 | 145.24
15874 | 87.79 | 152.52 | 11575.8 | -4612.68 | 3186.86 | 5562.29 | 0.76 | 0.76 | 0.07 | 5.63 | 94 | 11188.8 | 219905.62 | 3172174.04 | 30.2175 | -96.6216 | 145.36
15968 | 86.29 | 152.66 | 11580.66 | -4696.01 | 3230.07 | 5656.16 | 1.6 | -1.6 | 0.15 | 174.68 | 94 | 11193.66 | 219822.29 | 3172217.25 | 30.2173 | -96.6215 | 145.48
16063 | 85.33 | 152.6 | 11587.6 | -4780.15 | 3273.63 | 5750.91 | 1.01 | -1.01 | -0.06 | -176.44 | 95 | 11200.6 | 219738.15 | 3172260.81 | 30.2171 | -96.6213 | 145.6
16158 | 85.42 | 152.19 | 11595.26 | -4864.06 | 3317.5 | 5845.6 | 0.44 | 0.09 | -0.43 | -77.6 | 95 | 11208.26 | 219654.24 | 3172304.68 | 30.2168 | -96.6212 | 145.7
16252 | 86.36 | 152.79 | 11602 | -4947.22 | 3360.81 | 5939.35 | 1.19 | 1 | 0.64 | 32.51 | 94 | 11215 | 219571.08 | 3172347.99 | 30.2166 | -96.6211 | 145.81
16347 | 87.43 | 153.35 | 11607.14 | -5031.79 | 3403.77 | 6034.21 | 1.27 | 1.13 | 0.59 | 27.61 | 95 | 11220.14 | 219486.51 | 3172390.95 | 30.2164 | -96.621 | 145.92
16440 | 85.99 | 152.73 | 11612.48 | -5114.54 | 3445.86 | 6127.05 | 1.69 | -1.55 | -0.67 | -156.76 | 93 | 11225.48 | 219403.76 | 3172433.04 | 30.2161 | -96.6208 | 146.03
16534 | 86.75 | 152.95 | 11618.43 | -5198.01 | 3488.69 | 6220.86 | 0.84 | 0.81 | 0.23 | 16.12 | 94 | 11231.43 | 219320.29 | 3172475.87 | 30.2159 | -96.6207 | 146.13
16627 | 85.41 | 153.16 | 11624.79 | -5280.72 | 3530.73 | 6313.63 | 1.46 | -1.44 | 0.23 | 171.12 | 93 | 11237.79 | 219237.58 | 3172517.91 | 30.2157 | -96.6206 | 146.23
16722 | 87.13 | 154.02 | 11630.97 | -5365.62 | 3572.89 | 6408.41 | 2.02 | 1.81 | 0.91 | 26.55 | 95 | 11243.97 | 219152.68 | 3172560.07 | 30.2154 | -96.6205 | 146.34
16816 | 83.63 | 152.51 | 11638.54 | -5449.28 | 3615.03 | 6502.08 | 4.05 | -3.72 | -1.61 | -156.79 | 94 | 11251.54 | 219069.02 | 3172602.21 | 30.2152 | -96.6203 | 146.44
16911 | 85.5 | 152.78 | 11647.54 | -5533.28 | 3658.49 | 6596.65 | 1.99 | 1.97 | 0.28 | 8.19 | 95 | 11260.54 | 218985.02 | 3172645.67 | 30.215 | -96.6202 | 146.53
17006 | 86.06 | 153.57 | 11654.53 | -5617.82 | 3701.24 | 6691.39 | 1.02 | 0.59 | 0.83 | 54.62 | 95 | 11267.53 | 218900.48 | 3172688.42 | 30.2147 | -96.6201 | 146.62
17100 | 86.56 | 155.35 | 11660.58 | -5702.46 | 3741.68 | 6785.14 | 1.96 | 0.53 | 1.89 | 74.34 | 94 | 11273.58 | 218815.84 | 3172728.86 | 30.2145 | -96.62 | 146.73
17195 | 86.63 | 154.94 | 11666.22 | -5788.51 | 3781.54 | 6879.87 | 0.44 | 0.07 | -0.43 | -80.31 | 95 | 11279.22 | 218729.79 | 3172768.72 | 30.2143 | -96.6198 | 146.84
17290 | 87.1 | 152.89 | 11671.42 | -5873.7 | 3823.25 | 6974.7 | 2.21 | 0.49 | -2.16 | -77.13 | 95 | 11284.42 | 218644.6 | 3172810.43 | 30.214 | -96.6197 | 146.94
17385 | 88.65 | 152.48 | 11674.94 | -5958.05 | 3866.81 | 7069.63 | 1.69 | 1.63 | -0.43 | -14.81 | 95 | 11287.94 | 218560.25 | 3172853.99 | 30.2138 | -96.6196 | 147.02
17479 | 88.57 | 152.6 | 11677.22 | -6041.43 | 3910.14 | 7163.6 | 0.15 | -0.09 | 0.13 | 123.7 | 94 | 11290.22 | 218476.87 | 3172897.32 | 30.2135 | -96.6195 | 147.09
17574 | 86.35 | 153.83 | 11681.43 | -6126.15 | 3952.91 | 7258.5 | 2.67 | -2.34 | 1.29 | 151.06 | 95 | 11294.43 | 218392.15 | 3172940.09 | 30.2133 | -96.6193 | 147.17
17668 | 86.2 | 154.14 | 11687.54 | -6210.44 | 3994.05 | 7352.27 | 0.37 | -0.16 | 0.33 | 115.88 | 94 | 11300.54 | 218307.86 | 3172981.23 | 30.2131 | -96.6192 | 147.25
17763 | 87.04 | 154.3 | 11693.14 | -6295.84 | 4035.3 | 7447.06 | 0.9 | 0.88 | 0.17 | 10.77 | 95 | 11306.14 | 218222.46 | 3173022.48 | 30.2128 | -96.6191 | 147.34
17858 | 86.26 | 153.08 | 11698.69 | -6380.85 | 4077.33 | 7541.88 | 1.52 | -0.82 | -1.28 | -122.67 | 95 | 11311.69 | 218137.45 | 3173064.51 | 30.2126 | -96.619 | 147.42
17983 | 87.17 | 152.41 | 11705.85 | -6491.79 | 4134.48 | 7666.67 | 0.9 | 0.73 | -0.54 | -36.34 | 125 | 11318.85 | 218026.51 | 3173121.66 | 30.2123 | -96.6188 | 147.51
18077 | 85.37 | 151.96 | 11711.97 | -6574.75 | 4178.25 | 7760.46 | 1.97 | -1.91 | -0.48 | -166.01 | 94 | 11324.97 | 217943.55 | 3173165.43 | 30.2121 | -96.6187 | 147.56
18173 | 86.81 | 152.69 | 11718.51 | -6659.56 | 4222.73 | 7856.24 | 1.68 | 1.5 | 0.76 | 26.85 | 96 | 11331.51 | 217858.74 | 3173209.91 | 30.2118 | -96.6185 | 147.62
18267 | 84.3 | 152.45 | 11725.8 | -6742.74 | 4265.9 | 7949.95 | 2.68 | -2.67 | -0.26 | -174.56 | 94 | 11338.8 | 217775.56 | 3173253.08 | 30.2116 | -96.6184 | 147.68
18362 | 83.92 | 152.3 | 11735.55 | -6826.46 | 4309.71 | 8044.44 | 0.43 | -0.4 | -0.16 | -158.57 | 95 | 11348.55 | 217691.84 | 3173296.89 | 30.2114 | -96.6183 | 147.73
18457 | 83.52 | 152.12 | 11745.94 | -6910 | 4353.74 | 8138.87 | 0.46 | -0.42 | -0.19 | -155.91 | 95 | 11358.94 | 217608.3 | 3173340.92 | 30.2111 | -96.6182 | 147.79
18551 | 84.65 | 152.96 | 11755.62 | -6992.97 | 4396.85 | 8232.37 | 1.5 | 1.2 | 0.89 | 36.52 | 94 | 11368.62 | 217525.33 | 3173384.03 | 30.2109 | -96.618 | 147.84
18644 | 84.99 | 153.32 | 11764.02 | -7075.59 | 4438.7 | 8324.99 | 0.53 | 0.37 | 0.39 | 46.54 | 93 | 11377.02 | 217442.71 | 3173425.88 | 30.2107 | -96.6179 | 147.9
18740 | 86.01 | 151.1 | 11771.55 | -7160.25 | 4483.32 | 8420.68 | 2.54 | 1.06 | -2.31 | -65.35 | 96 | 11384.55 | 217358.05 | 3173470.5 | 30.2104 | -96.6178 | 147.95
18832 | 85.99 | 151.23 | 11777.97 | -7240.65 | 4527.58 | 8512.43 | 0.14 | -0.02 | 0.14 | 98.77 | 92 | 11390.97 | 217277.65 | 3173514.76 | 30.2102 | -96.6176 | 147.98
18926 | 88.75 | 152.36 | 11782.29 | -7323.39 | 4571.95 | 8606.31 | 3.17 | 2.94 | 1.2 | 22.27 | 94 | 11395.29 | 217194.91 | 3173559.13 | 30.21 | -96.6175 | 148.02
19020 | 87.11 | 153.11 | 11785.68 | -7406.89 | 4614.99 | 8700.25 | 1.92 | -1.74 | 0.8 | 155.45 | 94 | 11398.68 | 217111.41 | 3173602.17 | 30.2097 | -96.6174 | 148.07
19115 | 87.85 | 154.13 | 11789.86 | -7491.91 | 4657.16 | 8795.14 | 1.33 | 0.78 | 1.07 | 54.04 | 95 | 11402.86 | 217026.39 | 3173644.34 | 30.2095 | -96.6173 | 148.13
19210 | 84.98 | 153.46 | 11795.8 | -7576.97 | 4699.02 | 8889.92 | 3.1 | -3.02 | -0.71 | -166.9 | 95 | 11408.8 | 216941.33 | 3173686.2 | 30.2093 | -96.6171 | 148.19
19305 | 87.32 | 155.14 | 11802.18 | -7662.37 | 4740.12 | 8984.65 | 3.03 | 2.46 | 1.77 | 35.68 | 95 | 11415.18 | 216855.93 | 3173727.3 | 30.209 | -96.617 | 148.26
19399 | 88.27 | 153.81 | 11805.79 | -7747.13 | 4780.59 | 9078.52 | 1.74 | 1.01 | -1.41 | -54.47 | 94 | 11418.79 | 216771.17 | 3173767.77 | 30.2088 | -96.6169 | 148.32
19494 | 90.01 | 153.72 | 11807.22 | -7832.33 | 4822.58 | 9173.49 | 1.83 | 1.83 | -0.09 | -2.96 | 95 | 11420.22 | 216685.97 | 3173809.76 | 30.2085 | -96.6168 | 148.38
19589 | 88.92 | 152.63 | 11808.11 | -7917.11 | 4865.45 | 9268.48 | 1.62 | -1.15 | -1.15 | -135.01 | 95 | 11421.11 | 216601.19 | 3173852.63 | 30.2083 | -96.6166 | 148.43
19683 | 87.72 | 150.53 | 11810.86 | -7999.73 | 4910.16 | 9362.41 | 2.57 | -1.28 | -2.23 | -119.78 | 94 | 11423.86 | 216518.57 | 3173897.34 | 30.2081 | -96.6165 | 148.46
19778 | 85.2 | 151.41 | 11816.73 | -8082.63 | 4956.17 | 9457.19 | 2.81 | -2.65 | 0.93 | 160.81 | 95 | 11429.73 | 216435.67 | 3173943.35 | 30.2078 | -96.6164 | 148.48
19873 | 84.83 | 150.91 | 11824.98 | -8165.54 | 5001.82 | 9551.8 | 0.65 | -0.39 | -0.53 | -126.63 | 95 | 11437.98 | 216352.76 | 3173989 | 30.2076 | -96.6162 | 148.51
19967 | 84.81 | 151.53 | 11833.47 | -8247.59 | 5046.89 | 9645.39 | 0.66 | -0.02 | 0.66 | 91.88 | 94 | 11446.47 | 216270.71 | 3174034.07 | 30.2074 | -96.6161 | 148.54
20062 | 85.07 | 151.25 | 11841.85 | -8330.66 | 5092.21 | 9740 | 0.4 | 0.27 | -0.29 | -47.02 | 95 | 11454.85 | 216187.64 | 3174079.39 | 30.2071 | -96.616 | 148.56
20154 | 85.55 | 151.41 | 11849.37 | -8411.11 | 5136.2 | 9831.67 | 0.55 | 0.52 | 0.17 | 18.38 | 92 | 11462.37 | 216107.19 | 3174123.38 | 30.2069 | -96.6158 | 148.59
20249 | 86.43 | 152.12 | 11856.01 | -8494.6 | 5181.03 | 9926.43 | 1.19 | 0.93 | 0.75 | 38.85 | 95 | 11469.01 | 216023.7 | 3174168.21 | 30.2067 | -96.6157 | 148.62
20344 | 87.7 | 153.17 | 11860.88 | -8578.87 | 5224.62 | 10021.3 | 1.73 | 1.34 | 1.11 | 39.57 | 95 | 11473.88 | 215939.43 | 3174211.8 | 30.2065 | -96.6156 | 148.66
20439 | 86.97 | 152.22 | 11865.3 | -8663.19 | 5268.15 | 10116.19 | 1.26 | -0.77 | -1 | -127.59 | 95 | 11478.3 | 215855.11 | 3174255.33 | 30.2062 | -96.6154 | 148.7
20516 | 86.97 | 152.22 | 11869.37 | -8731.22 | 5303.99 | 10193.09 | 0 | 0 | 0 | 0 | 77 | 11482.37 | 215787.08 | 3174291.17 | 30.206 | -96.6153 | 148.72

## 7_14_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/14/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 15630 |  |  | Well Cost($): |  | 15630
|  |  |  | 24hr Summary: |  | P/U BHA #1, Drill Surface
|  |  |  | 24hr Lookahead: |  | Drill Surface, Casing ops, Rig Skid
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 108 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 7 | PV: | 2
End Depth (Usft): |  | 3211 |  | 3211 |  | OD (in): |  |  |  | 300: | 5 | YP: | 3
Total Drilled (Usft): |  | 3103 |  | 3103 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 35
Slide Drilled (Usft): |  | 315 |  | 315 | [5 empty] | 100: | 2 | Chlorides: | 410
Rotary Drilled (Usft): |  | 2788 |  | 2788 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.40 / 5.70
Drlg/Circ Hrs: |  | 7.00 / 2.57 |  | 7.00 / 2.57 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 5.6/94.3
Slide Drilling Hrs: |  | 1.85 |  | 1.85 |  | SN: |  | 38426 |  | 10s Gel: | 1 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 5.15 |  | 5.15 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.4 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 541.36 / 170.27 |  | 541.36 / 170.27 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 11 |  | 11 |  | Grade In: |  | 0-0-
% Slide: |  | 10.15 |  | 10.15 |  | Grade Out: |  | 1-3-CT-S-X-I-TD
% Rotary: |  | 89.85 |  | 89.85 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  |  | 8 | [5 empty] | 37.55 |  | 39.05
13 Stab |  |  |  | 8.125 | 3 |  |  |  |  | 6.34 |  | 45.39
NMPC |  |  |  | 8 | 3.25 |  |  |  |  | 8.58 |  | 53.97
UBHO Sub UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.66 |  | 57.63
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.83 |  | 86.46
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.99 |  | 115.45
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.13 |  | 117.58
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 274.62 |  | 392.2
392.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR775044 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.08 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
198 | 0.31 | 323.38 | 198 | 0.43 | -0.32 | 0.16 |  | 323.38 | -0.53 | 0.16 |  | 0 | 198
289 | 0.17 | 338.7 | 289 | 0.75 | -0.52 | 0.17 |  | 162.9 | -0.91 | -0.15 |  | 0 | 91
413 | 0.27 | 1.14 | 413 | 1.22 | -0.58 | 0.1 |  | 52.33 | -1.35 | 0.08 |  | 0 | 124
507 | 0.1 | 29.53 | 507 | 1.51 | -0.53 | 0.2 |  | 165.36 | -1.58 | -0.18 |  | 0 | 94
601 | 0.2 | 84.04 | 601 | 1.6 | -0.33 | 0.17 |  | 84.35 | -1.57 | 0.11 |  | 0 | 94
695 | 0.81 | 74.28 | 694.99 | 1.8 | 0.47 | 0.65 |  | -12.93 | -1.37 | 0.65 |  | 0 | 94
789 | 0.87 | 95.23 | 788.98 | 1.91 | 1.83 | 0.33 |  | 89.54 | -0.85 | 0.06 |  | 0 | 94
884 | 0.68 | 103.73 | 883.97 | 1.71 | 3.09 | 0.23 |  | 153.02 | -0.09 | -0.2 |  | 0 | 95
977 | 0.6 | 92.05 | 976.97 | 1.56 | 4.11 | 0.16 |  | -127.27 | 0.51 | -0.09 |  | 0 | 93
1071 | 0.27 | 110.88 | 1070.97 | 1.47 | 4.81 | 0.38 |  | 165.8 | 0.92 | -0.35 |  | 0 | 94
1166 | 0.76 | 129.55 | 1165.96 | 0.98 | 5.51 | 0.54 |  | 28.4 | 1.66 | 0.52 |  | 0 | 95
1259 | 1.36 | 120.17 | 1258.94 | 0.04 | 6.94 | 0.67 |  | -20.85 | 3.16 | 0.65 |  | 0 | 93
1354 | 2.07 | 118.8 | 1353.9 | -1.36 | 9.42 | 0.75 |  | -3.99 | 5.54 | 0.75 |  | 0 | 95
1447 | 3.26 | 111.32 | 1446.8 | -3.13 | 13.35 | 1.33 |  | -20.05 | 8.93 | 1.28 |  | -8.04 | 93
1542 | 4.5 | 111.66 | 1541.58 | -5.48 | 19.33 | 1.31 |  | 1.23 | 13.78 | 1.31 |  | 0.36 | 95
1635 | 5.33 | 112.56 | 1634.24 | -8.49 | 26.71 | 0.9 |  | 5.76 | 19.84 | 0.89 |  | 0.97 | 93
1729 | 6.09 | 113.29 | 1727.77 | -12.13 | 35.32 | 0.81 |  | 5.82 | 27.05 | 0.81 |  | 0.78 | 94
1822 | 7.04 | 114.59 | 1820.16 | -16.46 | 45.04 | 1.03 |  | 9.54 | 35.36 | 1.02 |  | 1.4 | 93
1917 | 7.77 | 112.92 | 1914.37 | -21.38 | 56.25 | 0.8 |  | -17.26 | 44.89 | 0.77 |  | -1.76 | 95
2012 | 8.11 | 114.64 | 2008.46 | -26.68 | 68.25 | 0.44 |  | 35.8 | 55.13 | 0.36 |  | 1.81 | 95
2106 | 8.81 | 113.04 | 2101.43 | -32.26 | 80.9 | 0.79 |  | -19.38 | 65.91 | 0.74 |  | -1.7 | 94
2200 | 9.8 | 109.52 | 2194.2 | -37.75 | 95.07 | 1.21 |  | -31.64 | 77.31 | 1.05 |  | -3.74 | 94
2293 | 10.84 | 107.76 | 2285.69 | -43.06 | 110.86 | 1.17 |  | -17.73 | 89.3 | 1.12 |  | -1.89 | 93
2387 | 10.73 | 111.73 | 2378.03 | -49 | 127.4 | 0.8 |  | 100.37 | 102.19 | -0.12 |  | 4.22 | 94
2481 | 10.69 | 112.44 | 2470.39 | -55.56 | 143.59 | 0.15 |  | 107.21 | 115.48 | -0.04 |  | 0.76 | 94
2575 | 10.32 | 110.42 | 2562.82 | -61.83 | 159.54 | 0.56 |  | -136.12 | 128.39 | -0.39 |  | -2.15 | 94
2669 | 9.97 | 109.93 | 2655.35 | -67.54 | 175.08 | 0.38 |  | -166.39 | 140.62 | -0.37 |  | -0.52 | 94
2763 | 9.2 | 107.55 | 2748.04 | -72.58 | 189.89 | 0.92 |  | -153.94 | 151.92 | -0.82 |  | -2.53 | 94
2857 | 9.09 | 107.44 | 2840.84 | -77.07 | 204.14 | 0.12 |  | -171.02 | 162.47 | -0.12 |  | -0.12 | 94
2952 | 9.3 | 109.74 | 2934.62 | -81.91 | 218.53 | 0.45 |  | 61.4 | 173.4 | 0.22 |  | 2.42 | 95
3046 | 9.75 | 110.2 | 3027.32 | -87.23 | 233.15 | 0.49 |  | 9.83 | 184.85 | 0.48 |  | 0.49 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 443.29 | 11.63 | 97.35 | 240 | 858.37 | 2094.23 | 1736.92 | 0 | 84.42 | 79.71 | 75 | 5396.62 | 0
Run | 443.29 | 11.63 | 97.35 | 240 | 858.37 | 2094.23 | 1736.92 | 0 | 84.42 | 79.71 | 75 | 5396.62 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 07/14/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 07/14/2021 |  | 5 |  | 100 |  | 4 | 400
Mob/DeMob |  |  |  |  | 07/14/2021 |  | 1 |  | 6000 |  | 1 | 6000
Mileage |  |  |  |  | 07/14/2021 |  | 16 |  | 2 |  | 700 | 1400
Multi Rig Discount |  |  |  |  | 07/14/2021 |  | 20 |  | -400 |  | 1 | -400
13 Stab Rental (Used) |  |  |  |  | 07/14/2021 |  | 7 |  | 1150 |  | 1 | 1150
13 Stab Rental (Not Used) |  |  |  |  | 07/14/2021 |  | 8 |  | 230 |  | 1 | 230
Total | [11 empty] | 15630
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/14/2021 | 00:00 | 12:30 | 12.5 | 108 | 108 | 0 | SUR |  | 24B | STBY
07/14/2021 | 12:30 | 13:00 | 0.5 | 108 | 108 | 0 | SUR | 1: BHA 1 | 6O | P/U BHA 1
07/14/2021 | 13:00 | 13:28 | 0.47 | 108 | 270 | 162 | SUR | 1: BHA 1 | 2K | Rotary Drill f/108.00 t/270.00, w/WOB 5.00,Flow 500.00, RPM 50.00, Press 550.00, Tq 2000.00, ROP 347.14, Diff 260.00, Temp 91.00
07/14/2021 | 13:28 | 13:40 | 0.2 | 270 | 270 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 13:40 | 13:45 | 0.08 | 270 | 302 | 32 | SUR | 1: BHA 1 | 2K | Rotary Drill f/270.00 t/302.00, w/WOB 5.00,Flow 665.00, RPM 80.00, Press 900.00, Tq 5000.00, ROP 384.00, Diff 150.00, Temp 93.00
07/14/2021 | 13:45 | 14:17 | 0.53 | 302 | 302 | 0 | SUR | 1: BHA 1 | 8A | Work on TD
07/14/2021 | 14:17 | 14:21 | 0.07 | 302 | 361 | 59 | SUR | 1: BHA 1 | 2K | Rotary Drill f/302.00 t/361.00, w/WOB 5.00,Flow 665.00, RPM 80.00, Press 900.00, Tq 3000.00, ROP 885.00, Diff 150.00, Temp 93.00
07/14/2021 | 14:21 | 14:25 | 0.07 | 361 | 361 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 14:25 | 14:43 | 0.3 | 361 | 485 | 124 | SUR | 1: BHA 1 | 2K | Rotary Drill f/361.00 t/485.00, w/WOB 5.00,Flow 715.00, RPM 100.00, Press 950.00, Tq 3000.00, ROP 413.33, Diff 100.00, Temp 95.00
07/14/2021 | 14:43 | 14:56 | 0.22 | 485 | 579 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/485.00 t/579.00, w/WOB 5.00,Flow 715.00, RPM 100.00, Press 1200.00, Tq 3000.00, ROP 433.85, Diff 270.00, Temp 97.00
07/14/2021 | 14:56 | 15:00 | 0.07 | 579 | 579 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 15:00 | 15:08 | 0.13 | 579 | 673 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/579.00 t/673.00, w/WOB 5.00,Flow 715.00, RPM 100.00, Press 1200.00, Tq 3000.00, ROP 705.00, Diff 270.00, Temp 97.00
07/14/2021 | 15:08 | 15:12 | 0.07 | 673 | 673 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 15:12 | 15:21 | 0.15 | 673 | 767 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/673.00 t/767.00, w/WOB 5.00,Flow 715.00, RPM 100.00, Press 1200.00, Tq 3000.00, ROP 626.67, Diff 270.00, Temp 97.00
07/14/2021 | 15:21 | 15:25 | 0.07 | 767 | 767 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 15:25 | 15:34 | 0.15 | 767 | 861 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/767.00 t/861.00, w/WOB 5.00,Flow 715.00, RPM 100.00, Press 1200.00, Tq 3000.00, ROP 626.67, Diff 270.00, Temp 97.00
07/14/2021 | 15:34 | 15:37 | 0.05 | 861 | 861 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 15:37 | 15:47 | 0.17 | 861 | 956 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/861.00 t/956.00, w/WOB 7.00,Flow 715.00, RPM 100.00, Press 1200.00, Tq 3000.00, ROP 570.00, Diff 270.00, Temp 99.00
07/14/2021 | 15:47 | 15:51 | 0.07 | 956 | 956 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 15:51 | 16:01 | 0.17 | 956 | 1049 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/956.00 t/1049.00, w/WOB 7.00,Flow 715.00, RPM 100.00, Press 1200.00, Tq 3000.00, ROP 558.00, Diff 270.00, Temp 99.00
07/14/2021 | 16:01 | 16:05 | 0.07 | 1049 | 1049 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 16:05 | 16:12 | 0.12 | 1049 | 1143 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1049.00 t/1143.00, w/WOB 7.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 5000.00, ROP 805.71, Diff 350.00, Temp 99.00
07/14/2021 | 16:12 | 16:16 | 0.07 | 1143 | 1143 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 16:16 | 16:20 | 0.07 | 1143 | 1158 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1143.00 t/1158.00, TF 110.00M, w/WOB 5.00,Flow 900.00, Press 2100.00, Tq 5000.00, ROP 225.00, Diff 350.00, Temp 100.00
07/14/2021 | 16:20 | 16:26 | 0.1 | 1158 | 1238 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1158.00 t/1238.00, w/WOB 7.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 5000.00, ROP 800.00, Diff 350.00, Temp 100.00
07/14/2021 | 16:26 | 16:31 | 0.08 | 1238 | 1238 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 16:31 | 16:36 | 0.08 | 1238 | 1253 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1238.00 t/1253.00, TF 110.00M, w/WOB 7.00,Flow 900.00, Press 2100.00, Tq 5000.00, ROP 180.00, Diff 350.00, Temp 100.00
07/14/2021 | 16:36 | 16:43 | 0.12 | 1253 | 1331 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1253.00 t/1331.00, w/WOB 7.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 5000.00, ROP 668.57, Diff 350.00, Temp 100.00
07/14/2021 | 16:43 | 16:48 | 0.08 | 1331 | 1331 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 16:48 | 16:53 | 0.08 | 1331 | 1351 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1331.00 t/1351.00, TF 110M, w/WOB 7.00,Flow 900.00, Press 2100.00, Tq 5000.00, ROP 240.00, Diff 350.00, Temp 100.00
07/14/2021 | 16:53 | 16:59 | 0.1 | 1351 | 1426 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1351.00 t/1426.00, w/WOB 7.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 5000.00, ROP 750.00, Diff 350.00, Temp 100.00
07/14/2021 | 16:59 | 17:04 | 0.08 | 1426 | 1426 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 17:04 | 17:09 | 0.08 | 1426 | 1446 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1426.00 t/1446.00, TF 110.00M, w/WOB 7.00,Flow 900.00, Press 2100.00, Tq 5000.00, ROP 240.00, Diff 350.00, Temp 100.00
07/14/2021 | 17:09 | 17:15 | 0.1 | 1446 | 1519 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1446.00 t/1519.00, w/WOB 7.00,Flow 900.00, RPM 100.00, Press 2100.00, Tq 5000.00, ROP 730.00, Diff 350.00, Temp 100.00
07/14/2021 | 17:15 | 17:20 | 0.08 | 1519 | 1519 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 17:20 | 17:24 | 0.07 | 1519 | 1534 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1519.00 t/1534.00, TF 0.00G, w/WOB 7.00,Flow 900.00, Press 2100.00, Tq 5000.00, ROP 225.00, Diff 350.00, Temp 100.00
07/14/2021 | 17:24 | 17:31 | 0.12 | 1534 | 1614 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1534.00 t/1614.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 5000.00, ROP 685.71, Diff 400.00, Temp 105.00
07/14/2021 | 17:31 | 17:36 | 0.08 | 1614 | 1614 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 17:36 | 17:41 | 0.08 | 1614 | 1629 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1614.00 t/1629.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2200.00, Tq 5000.00, ROP 180.00, Diff 400.00, Temp 105.00
07/14/2021 | 17:41 | 17:48 | 0.12 | 1629 | 1707 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1629.00 t/1707.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 5000.00, ROP 668.57, Diff 400.00, Temp 105.00
07/14/2021 | 17:48 | 17:53 | 0.08 | 1707 | 1707 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 17:53 | 17:59 | 0.1 | 1707 | 1722 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1707.00 t/1722.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2200.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 105.00
07/14/2021 | 17:59 | 18:08 | 0.15 | 1722 | 1801 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1722.00 t/1801.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 5000.00, ROP 526.67, Diff 400.00, Temp 105.00
07/14/2021 | 18:08 | 18:16 | 0.13 | 1801 | 1801 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 18:16 | 18:21 | 0.08 | 1801 | 1821 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/1801.00 t/1821.00, TF 0.00G, w/WOB 10.00,Flow 900.00, Press 2200.00, Tq 0.00, ROP 240.00, Diff 400.00, Temp 105.00
07/14/2021 | 18:21 | 18:29 | 0.13 | 1821 | 1894 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1821.00 t/1894.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 5000.00, ROP 547.50, Diff 400.00, Temp 105.00
07/14/2021 | 18:29 | 18:34 | 0.08 | 1894 | 1894 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection. Recycle
07/14/2021 | 18:34 | 18:40 | 0.1 | 1894 | 1909 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1894.00 t/1909.00, TF -20.00G, w/WOB 5.00,Flow 900.00, Press 2400.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 113.00
07/14/2021 | 18:40 | 18:47 | 0.12 | 1909 | 1989 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1909.00 t/1989.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 685.71, Diff 400.00, Temp 113.00
07/14/2021 | 18:47 | 18:52 | 0.08 | 1989 | 1989 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 18:52 | 18:58 | 0.1 | 1989 | 2004 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/1989.00 t/2004.00, TF 0.00G, w/WOB 5.00,Flow 900.00, Press 2400.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 113.00
07/14/2021 | 18:58 | 19:05 | 0.12 | 2004 | 2084 | 80 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2004.00 t/2084.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 685.71, Diff 400.00, Temp 113.00
07/14/2021 | 19:05 | 19:13 | 0.13 | 2084 | 2084 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 19:13 | 19:20 | 0.12 | 2084 | 2104 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2084.00 t/2104.00, TF -20.00G, w/WOB 5,Flow 900.00, Press 2400.00, Tq 0.00, ROP 171.43, Diff 400.00, Temp 113.00
07/14/2021 | 19:20 | 19:32 | 0.2 | 2104 | 2178 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2104.00 t/2178.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 370.00, Diff 400.00, Temp 113.00
07/14/2021 | 19:32 | 19:37 | 0.08 | 2178 | 2178 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 19:37 | 19:44 | 0.12 | 2178 | 2198 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2178.00 t/2198.00, TF 0G, w/WOB 5,Flow 900, Press 2400.00, Tq 0, ROP 171.43, Diff 400.00, Temp 113.00
07/14/2021 | 19:44 | 19:46 | 0.03 | 2198 | 2217 | 19 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2198.00 t/2217.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 570.00, Diff 400.00, Temp 113.00
07/14/2021 | 19:46 | 20:40 | 0.9 | 2217 | 2217 | 0 | SUR | 1: BHA 1 | 8A | Work on top drive
07/14/2021 | 20:40 | 20:47 | 0.12 | 2217 | 2272 | 55 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2217.00 t/2272.00, w/WOB 15.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 471.43, Diff 400.00, Temp 113.00
07/14/2021 | 20:47 | 20:52 | 0.08 | 2272 | 2272 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 20:52 | 20:59 | 0.12 | 2272 | 2287 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2272.00 t/2287.00, TF 0.00G, w/WOB 5.00,Flow 900.00, Press 2400.00, Tq 0.00, ROP 128.57, Diff 400.00, Temp 113.00
07/14/2021 | 20:59 | 21:08 | 0.15 | 2287 | 2365 | 78 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2287.00 t/2365.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 520.00, Diff 400.00, Temp 113.00
07/14/2021 | 21:08 | 21:13 | 0.08 | 2365 | 2365 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 21:13 | 21:19 | 0.1 | 2365 | 2380 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/2365.00 t/2380.00, TF 70.00G, w/WOB 5.00,Flow 900.00, Press 2400.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 113.00
07/14/2021 | 21:19 | 21:30 | 0.18 | 2380 | 2459 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2380.00 t/2459.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 430.91, Diff 400.00, Temp 122.00
07/14/2021 | 21:30 | 21:35 | 0.08 | 2459 | 2459 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 21:35 | 21:43 | 0.13 | 2459 | 2553 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2459.00 t/2553.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 5000.00, ROP 705.00, Diff 400.00, Temp 122.00
07/14/2021 | 21:43 | 21:48 | 0.08 | 2553 | 2553 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 21:48 | 21:59 | 0.18 | 2553 | 2647 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2553.00 t/2647.00, w/WOB 16.00,Flow 900.00, RPM 100.00, Press 2400.00, Tq 9329.00, ROP 512.73, Diff 400.00, Temp 122.00
07/14/2021 | 21:59 | 22:04 | 0.08 | 2647 | 2647 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 22:04 | 22:13 | 0.15 | 2647 | 2741 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2647.00 t/2741.00, w/WOB 27.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 9329.00, ROP 626.67, Diff 400.00, Temp 122.00
07/14/2021 | 22:13 | 22:18 | 0.08 | 2741 | 2741 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 22:18 | 22:27 | 0.15 | 2741 | 2835 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2741.00 t/2835.00, w/WOB 32.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 9329.00, ROP 626.67, Diff 400.00, Temp 123.00
07/14/2021 | 22:27 | 22:32 | 0.08 | 2835 | 2835 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 22:32 | 22:40 | 0.13 | 2835 | 2855 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2835.00 t/2855.00, TF 60.00G, w/WOB 15.00,Flow 900.00, Press 2600.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 123.00
07/14/2021 | 22:40 | 22:53 | 0.22 | 2855 | 2929 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2855.00 t/2929.00, w/WOB 25.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 9329.00, ROP 341.54, Diff 400.00, Temp 123.00
07/14/2021 | 22:53 | 22:58 | 0.08 | 2929 | 2929 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 22:58 | 23:06 | 0.13 | 2929 | 2949 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/2929.00 t/2949.00, TF 60.00G, w/WOB 15.00,Flow 900.00, Press 2600.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 123.00
07/14/2021 | 23:06 | 23:16 | 0.17 | 2949 | 3024 | 75 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2949.00 t/3024.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 9329.00, ROP 450.00, Diff 400.00, Temp 123.00
07/14/2021 | 23:16 | 23:21 | 0.08 | 3024 | 3024 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 23:21 | 23:30 | 0.15 | 3024 | 3044 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3024.00 t/3044.00, TF 60.00G, w/WOB 12.00,Flow 900.00, Press 2600.00, Tq 0.00, ROP 133.33, Diff 400.00, Temp 123.00
07/14/2021 | 23:30 | 23:38 | 0.13 | 3044 | 3118 | 74 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3044.00 t/3118.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 10420.00, ROP 555.00, Diff 400.00, Temp 123.00
07/14/2021 | 23:38 | 23:43 | 0.08 | 3118 | 3118 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/14/2021 | 23:43 | 23:51 | 0.13 | 3118 | 3138 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3118.00 t/3138.00, TF 60.00G, w/WOB 18.00,Flow 900.00, Press 2600.00, Tq 0.00, ROP 150.00, Diff 400.00, Temp 123.00
07/14/2021 | 23:51 | 24:00 | 0.15 | 3138 | 3211 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3138.00 t/3211.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 10420.00, ROP 486.67, Diff 400.00, Temp 123.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 7_15_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 07/15/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 15630
|  |  |  | 24hr Summary: |  | Drill ahead to Casing point, POOH, Rack back BHA, Standby for casing ops
|  |  |  | 24hr Lookahead: |  | Standby for Casing Ops and rig skid
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3211 |  | 108 |  | Csg Shoe MD(Usft): |  | 108 |  | 600: | 7 | PV: | 2
End Depth (Usft): |  | 3523 |  | 3523 |  | OD (in): |  |  |  | 300: | 5 | YP: | 3
Total Drilled (Usft): |  | 312 |  | 3415 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 35
Slide Drilled (Usft): |  | 55 |  | 370 | [5 empty] | 100: | 2 | Chlorides: | 410
Rotary Drilled (Usft): |  | 257 |  | 3045 | [5 empty] | 6: | 1 | % Sand/Solids: | 0.40 / 5.70
Drlg/Circ Hrs: |  | 1.13 / 1.12 |  | 8.13 / 3.68 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 5.6/94.3
Slide Drilling Hrs: |  | 0.47 |  | 2.32 |  | SN: |  | 38426 |  | 10s Gel: | 1 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 0.67 |  | 5.82 |  | Bit # |  | 1 |  | PH / Temp(F) | 7.4 / 0.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 385.50 / 117.86 |  | 523.50 / 159.71 |  | OD (in) / TFA: |  | 13.500 / 1.353
BRT Hrs: |  | 4.33 |  | 15.33 |  | Grade In: |  | 0-0-
% Slide: |  | 17.63 |  | 10.83 |  | Grade Out: |  | 1-3-CT-S-X-I-TD
% Rotary: |  | 82.37 |  | 89.17 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  |  |  | BillTrey
Kevin |  | Josh Ray |  | Jason Smitters
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
U616S - TFA 1.35 |  |  |  | 13.5 | [5 empty] | 1.5 |  | 1.5
7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  |  | 8 | [5 empty] | 37.55 |  | 39.05
13 Stab |  |  |  | 8.125 | 3 |  |  |  |  | 6.34 |  | 45.39
NMPC |  |  |  | 8 | 3.25 |  |  |  |  | 8.58 |  | 53.97
UBHO Sub UBHO Sub |  |  |  | 7.75 | 2.875 |  |  |  |  | 3.66 |  | 57.63
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.83 |  | 86.46
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.99 |  | 115.45
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  |  |  | 2.13 |  | 117.58
9 Jts HWDP |  |  |  | 5 | 3 |  |  |  |  | 274.62 |  | 392.2
392.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
MTR775044 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.08 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3139 | 9.73 | 111.92 | 3118.98 | -92.88 | 247.83 | 0.31 |  | 94.78 | 196.63 | -0.02 |  | 1.85 | 93
3233 | 9.06 | 111.75 | 3211.72 | -98.59 | 262.07 | 0.71 |  | -177.71 | 208.26 | -0.71 |  | -0.18 | 94
3326 | 9.01 | 109.77 | 3303.57 | -103.76 | 275.72 | 0.34 |  | -100.11 | 219.15 | -0.05 |  | -2.13 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 275.29 | 11.63 | 97.35 | 240 | 858.37 | 2094.23 | 1736.92 | 0 | 84.42 | 79.71 | 75 | 5396.62 | 0
Run | 419.88 | 11.63 | 97.35 | 240 | 858.37 | 2094.23 | 1736.92 | 0 | 84.42 | 79.71 | 75 | 5396.62 | 0
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
07/15/2021 | 00:00 | 00:05 | 0.08 | 3211 | 3211 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 00:05 | 00:15 | 0.17 | 3211 | 3226 | 15 | SUR | 1: BHA 1 | 2J | Slide Drill f/3211.00 t/3226.00, TF 0.00G, w/WOB 15.00,Flow 900.00, Press 2600.00, Tq 0.00, ROP 90.00, Diff 400.00, Temp 123.00
07/15/2021 | 00:15 | 00:25 | 0.17 | 3226 | 3305 | 79 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3226.00 t/3305.00, w/WOB 30.00,Flow 900.00, RPM 100.00, Press 2600.00, Tq 10500.00, ROP 474.00, Diff 400.00, Temp 123.00
07/15/2021 | 00:25 | 00:30 | 0.08 | 3305 | 3305 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 00:30 | 00:39 | 0.15 | 3305 | 3325 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3305.00 t/3325.00, TF 60.00G, w/WOB 15.00,Flow 900.00, Press 2600.00, Tq 0.00, ROP 133.33, Diff 400.00, Temp 123.00
07/15/2021 | 00:39 | 00:49 | 0.17 | 3325 | 3398 | 73 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3325.00 t/3398.00, w/WOB 32.00,Flow 900.00, RPM 100.00, Press 2700.00, Tq 10500.00, ROP 438.00, Diff 400.00, Temp 123.00
07/15/2021 | 00:49 | 00:54 | 0.08 | 3398 | 3398 | 0 | SUR | 1: BHA 1 | 5A | Survey & Connection
07/15/2021 | 00:54 | 01:03 | 0.15 | 3398 | 3418 | 20 | SUR | 1: BHA 1 | 2J | Slide Drill f/3398.00 t/3418.00, TF 60.00G, w/WOB 15.00,Flow 900.00, Press 2700.00, Tq 0.00, ROP 133.33, Diff 400.00, Temp 123.00
07/15/2021 | 01:03 | 01:23 | 0.33 | 3418 | 3523 | 105 | SUR | 1: BHA 1 | 2K | Rotary Drill f/3418.00 t/3523.00, w/WOB 32.00,Flow 900.00, RPM 100.00, Press 2700.00, Tq 10500.00, ROP 315.00, Diff 400.00, Temp 127.00
07/15/2021 | 01:23 | 01:27 | 0.07 | 3523 | 3523 | 0 | SUR | 1: BHA 1 | 5A | Survey on bottom
07/15/2021 | 01:27 | 02:15 | 0.8 | 3523 | 3523 | 0 | SUR | 1: BHA 1 | 5A | Circulate B/U to POOH f/ casing ops
07/15/2021 | 02:15 | 03:45 | 1.5 | 3523 | 3523 | 0 | SUR | 1: BHA 1 | 6B | POOH
07/15/2021 | 03:45 | 04:20 | 0.58 | 3523 | 3523 | 0 | SUR | 1: BHA 1 | 6P | L/D MWD tool, drain motor, break bit, rack back monels and motor in derrick
07/15/2021 | 04:20 | 24:00 | 19.67 | 3523 | 3523 | 0 | SUR |  | 24B | Standby for casing ops and rig skid to the Redwood A1H
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_2_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/02/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17350 |  |  | Well Cost($): |  | 32980
24hr Summary:
|  |  |  | 24hr Lookahead: |  | Pick up BHA #2
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3523 |  | 3523 |  | Csg Shoe MD(Usft): |  | 3513 |  | 600: | 37 | PV: | 14
End Depth (Usft): |  | 5494 |  | 5494 |  | OD (in): |  | 10.75 |  | 300: | 23 | YP: | 9
Total Drilled (Usft): |  | 1971 |  | 1971 |  | Weight (ft/lbs): |  | 44.5 |  | 200: | 16 | Viscosity: | 47
Slide Drilled (Usft): |  | 52 |  | 52 | [5 empty] | 100: | 11 | Chlorides: | 69000
Rotary Drilled (Usft): |  | 1919 |  | 1919 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 9.20
Drlg/Circ Hrs: |  | 3.83 / 2.67 |  | 3.83 / 2.67 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 0.55 |  | 0.55 |  | SN: |  | 56410 |  | 10s Gel: | 5 | Weight (ppg): | 9.7
Rotary Drilling Hrs: |  | 3.28 |  | 3.28 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 110.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 584.47 / 94.55 |  | 584.47 / 94.55 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 10 |  | 10 |  | Grade In: |  | New
% Slide: |  | 2.64 |  | 2.64 |  | Grade Out: |  | 0-1-CT-S-X-I-WT-TD
% Rotary: |  | 97.36 |  | 97.36 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  |  |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Xavier Cantu |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.014 |  |  |  | 8 | 2 |  |  | 100 |  | 37.56 |  | 39.06
NMPC |  |  |  | 8 | 3.25 |  |  | 162.87 |  | 9.21 |  | 48.27
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.97 |  | 52.24
NMDC |  |  |  | 7.812 | 3.312 |  |  | 157.9 |  | 27.55 |  | 79.79
NMDC |  |  |  | 8 | 3.312 |  |  | 151.3 |  | 28.75 |  | 108.54
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 100 |  | 2.55 |  | 111.09
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 298.32
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 573.17
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 575.84
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2637.54
Agitator |  |  |  | 6.562 | 3.75 |  |  | 80 |  | 24.65 |  | 2662.19
2662.19
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800058 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3538 | 9.17 | 111.33 | 3512.86 | -115.98 | 307.21 | 0.16 |  | -131.6 | 244.5 | -0.1 |  | -0.74 | 87
3632 | 8.31 | 121.5 | 3605.77 | -122.25 | 319.98 | 1.88 |  | 124.06 | 255.95 | -0.91 |  | 10.82 | 94
3726 | 9.38 | 115.82 | 3698.66 | -129.14 | 332.67 | 1.47 |  | -42.05 | 267.91 | 1.14 |  | -6.04 | 94
3819 | 9.9 | 111.35 | 3790.34 | -135.35 | 346.94 | 0.98 |  | -57.43 | 280 | 0.56 |  | -4.81 | 93
3913 | 10.17 | 111.79 | 3882.91 | -141.37 | 362.17 | 0.3 |  | 16.07 | 292.36 | 0.29 |  | 0.47 | 94
4007 | 10.25 | 111.21 | 3975.42 | -147.48 | 377.67 | 0.14 |  | -52.4 | 304.92 | 0.09 |  | -0.62 | 94
4102 | 10.06 | 113.58 | 4068.93 | -153.86 | 393.16 | 0.48 |  | 115.61 | 317.72 | -0.2 |  | 2.49 | 95
4195 | 11.11 | 113.5 | 4160.35 | -160.68 | 408.82 | 1.13 |  | -0.84 | 330.99 | 1.13 |  | -0.09 | 93
4289 | 11.42 | 111.41 | 4252.54 | -167.69 | 425.79 | 0.55 |  | -53.82 | 345.03 | 0.33 |  | -2.22 | 94
4382 | 11.08 | 112.44 | 4343.75 | -174.46 | 442.62 | 0.42 |  | 149.92 | 358.8 | -0.37 |  | 1.11 | 93
4476 | 11.16 | 111.87 | 4435.98 | -181.29 | 459.41 | 0.14 |  | -54.24 | 372.6 | 0.09 |  | -0.61 | 94
4571 | 10.92 | 109.62 | 4529.23 | -187.74 | 476.42 | 0.52 |  | -120.22 | 386.16 | -0.25 |  | -2.37 | 95
4666 | 10.4 | 108.74 | 4622.59 | -193.52 | 493.01 | 0.57 |  | -163.05 | 398.94 | -0.55 |  | -0.93 | 95
4759 | 10.18 | 108.84 | 4714.09 | -198.87 | 508.74 | 0.24 |  | 175.41 | 410.93 | -0.24 |  | 0.11 | 93
4853 | 9.64 | 107.04 | 4806.69 | -203.86 | 524.13 | 0.66 |  | -151.04 | 422.45 | -0.57 |  | -1.91 | 94
4947 | 10.91 | 109.38 | 4899.18 | -209.12 | 540.04 | 1.42 |  | 19.35 | 434.45 | 1.35 |  | 2.49 | 94
5041 | 10.65 | 109.8 | 4991.52 | -215.01 | 556.61 | 0.29 |  | 163.39 | 447.32 | -0.28 |  | 0.45 | 94
5134 | 10.93 | 110.12 | 5082.88 | -220.95 | 572.97 | 0.31 |  | 12.23 | 460.13 | 0.3 |  | 0.34 | 93
5228 | 10.44 | 108.07 | 5175.25 | -226.66 | 589.44 | 0.66 |  | -143.2 | 472.78 | -0.52 |  | -2.18 | 94
5322 | 9.92 | 106.59 | 5267.77 | -231.61 | 605.29 | 0.62 |  | -154.02 | 484.49 | -0.55 |  | -1.57 | 94
5416 | 9.98 | 105.56 | 5360.35 | -236.11 | 620.9 | 0.2 |  | -71.88 | 495.67 | 0.06 |  | -1.1 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 430.04 | 27.83 | 79.2 | 214 | 814.5 | 4533.33 | 3193.33 | 0 | 160.67 | 150.67 | 140.67 | 8920 | 0
Run | 430.04 | 27.83 | 79.2 | 214 | 814.5 | 4533.33 | 3193.33 | 0 | 160.67 | 150.67 | 140.67 | 8920 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/02/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/02/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/02/2021 |  | 20 |  | -400 |  | 1 | -400
8 Motor Reline |  |  |  |  | 08/02/2021 |  | 6 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17350
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/02/2021 | 00:00 | 12:00 | 12 | 3523 | 3523 | 0 | INT |  | 24B | Stand by
08/02/2021 | 12:00 | 14:00 | 2 | 3523 | 3523 | 0 | INT | 2: BHA 2 | 6O | Pick up BHA #2
08/02/2021 | 14:00 | 14:10 | 0.17 | 3523 | 3523 | 0 | INT | 2: BHA 2 | 6L | Test MWD & motor
08/02/2021 | 14:10 | 17:15 | 3.08 | 3523 | 3523 | 0 | INT | 2: BHA 2 | 6A | TIH t/3429
08/02/2021 | 17:15 | 18:00 | 0.75 | 3523 | 3523 | 0 | INT | 2: BHA 2 | 5A | Drill shoe track
08/02/2021 | 18:00 | 18:15 | 0.25 | 3523 | 3523 | 0 | INT | 2: BHA 2 | 5A | Circ bottoms up
08/02/2021 | 18:15 | 18:30 | 0.25 | 3523 | 3523 | 0 | INT | 2: BHA 2 | 15D | FIT
08/02/2021 | 18:30 | 18:50 | 0.33 | 3523 | 3612 | 89 | INT | 2: BHA 2 | 2K | Rotary Drill f/3523.00 t/3612.00, w/WOB 20.00,Flow 550.00, RPM 60.00, Press 12000.00, Tq 6000.00, ROP 267.00, Diff 10300.00, Temp 125.00
08/02/2021 | 18:50 | 18:55 | 0.08 | 3612 | 3624 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/3612.00 t/3624.00, TF 0.00G, w/WOB 20.00,Flow 550.00, Press 12000.00, Tq 6000.00, ROP 144.00, Diff 10300.00, Temp 125.00
08/02/2021 | 18:55 | 19:05 | 0.17 | 3624 | 3696 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/3624.00 t/3696.00, w/WOB 20.00,Flow 725.00, RPM 80.00, Press 3300.00, Tq 8000.00, ROP 432.00, Diff 600.00, Temp 125.00
08/02/2021 | 19:05 | 19:10 | 0.08 | 3696 | 3696 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 19:10 | 19:15 | 0.08 | 3696 | 3706 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3696.00 t/3706.00, w/WOB 20.00,Flow 725.00, RPM 80.00, Press 3300.00, Tq 8000.00, ROP 120.00, Diff 600.00, Temp 130.00
08/02/2021 | 19:15 | 19:20 | 0.08 | 3706 | 3716 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/3706.00 t/3716.00, TF -20.00G, w/WOB 20.00,Flow 725.00, Press 3300.00, Tq 8000.00, ROP 120.00, Diff 600.00, Temp 130.00
08/02/2021 | 19:20 | 19:30 | 0.17 | 3716 | 3790 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/3716.00 t/3790.00, w/WOB 20.00,Flow 725.00, RPM 80.00, Press 3300.00, Tq 8000.00, ROP 444.00, Diff 600.00, Temp 130.00
08/02/2021 | 19:30 | 19:35 | 0.08 | 3790 | 3790 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 19:35 | 19:40 | 0.08 | 3790 | 3883 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3790.00 t/3883.00, w/WOB 25.00,Flow 725.00, RPM 80.00, Press 3300.00, Tq 8000.00, ROP 1116.00, Diff 600.00, Temp 130.00
08/02/2021 | 19:40 | 19:45 | 0.08 | 3883 | 3883 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 19:45 | 19:50 | 0.08 | 3883 | 3977 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3883.00 t/3977.00, w/WOB 30.00,Flow 820.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 1128.00, Diff 600.00, Temp 130.00
08/02/2021 | 19:50 | 19:55 | 0.08 | 3977 | 3977 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 19:55 | 20:05 | 0.17 | 3977 | 4071 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3977.00 t/4071.00, w/WOB 30.00,Flow 820.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 564.00, Diff 600.00, Temp 138.00
08/02/2021 | 20:05 | 20:10 | 0.08 | 4071 | 4071 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 20:10 | 20:15 | 0.08 | 4071 | 4166 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4071.00 t/4166.00, w/WOB 30.00,Flow 820.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 1140.00, Diff 600.00, Temp 138.00
08/02/2021 | 20:15 | 20:20 | 0.08 | 4166 | 4166 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 20:20 | 20:22 | 0.03 | 4166 | 4176 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/4166.00 t/4176.00, w/WOB 30.00,Flow 820.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 300.00, Diff 600.00, Temp 138.00
08/02/2021 | 20:22 | 20:25 | 0.05 | 4176 | 4186 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4176.00 t/4186.00, TF 0.00G, w/WOB 30.00,Flow 820.00, Press 3900.00, Tq 9000.00, ROP 200.00, Diff 600.00, Temp 138.00
08/02/2021 | 20:25 | 20:35 | 0.17 | 4186 | 4259 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/4186.00 t/4259.00, w/WOB 30.00,Flow 820.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 438.00, Diff 600.00, Temp 138.00
08/02/2021 | 20:35 | 20:40 | 0.08 | 4259 | 4259 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 20:40 | 20:50 | 0.17 | 4259 | 4353 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4259.00 t/4353.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 564.00, Diff 600.00, Temp 138.00
08/02/2021 | 20:50 | 20:55 | 0.08 | 4353 | 4353 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 20:55 | 21:00 | 0.08 | 4353 | 4446 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4353.00 t/4446.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 1116.00, Diff 600.00, Temp 138.00
08/02/2021 | 21:00 | 21:05 | 0.08 | 4446 | 4446 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 21:05 | 21:15 | 0.17 | 4446 | 4540 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4446.00 t/4540.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 3900.00, Tq 9000.00, ROP 564.00, Diff 600.00, Temp 138.00
08/02/2021 | 21:15 | 21:20 | 0.08 | 4540 | 4540 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 21:20 | 21:25 | 0.08 | 4540 | 4635 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4540.00 t/4635.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4200.00, Tq 9000.00, ROP 1140.00, Diff 800.00, Temp 154.00
08/02/2021 | 21:25 | 21:30 | 0.08 | 4635 | 4635 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 21:30 | 21:35 | 0.08 | 4635 | 4730 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/4635.00 t/4730.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4200.00, Tq 9000.00, ROP 1140.00, Diff 800.00, Temp 154.00
08/02/2021 | 21:35 | 21:40 | 0.08 | 4730 | 4730 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 21:40 | 21:50 | 0.17 | 4730 | 4823 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4730.00 t/4823.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4200.00, Tq 9000.00, ROP 558.00, Diff 800.00, Temp 154.00
08/02/2021 | 21:50 | 21:55 | 0.08 | 4823 | 4823 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 21:55 | 22:00 | 0.08 | 4823 | 4917 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4823.00 t/4917.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4200.00, Tq 9000.00, ROP 1128.00, Diff 800.00, Temp 154.00
08/02/2021 | 22:00 | 22:05 | 0.08 | 4917 | 4917 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 22:05 | 22:10 | 0.08 | 4917 | 4927 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/4917.00 t/4927.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4200.00, Tq 9000.00, ROP 120.00, Diff 800.00, Temp 154.00
08/02/2021 | 22:10 | 22:15 | 0.08 | 4927 | 4937 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/4927.00 t/4937.00, TF 20.00G, w/WOB 30.00,Flow 870.00, Press 4200.00, Tq 9000.00, ROP 120.00, Diff 800.00, Temp 165.00
08/02/2021 | 22:15 | 22:20 | 0.08 | 4937 | 5011 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/4937.00 t/5011.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 888.00, Diff 800.00, Temp 165.00
08/02/2021 | 22:20 | 22:25 | 0.08 | 5011 | 5011 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 22:25 | 22:35 | 0.17 | 5011 | 5105 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5011.00 t/5105.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 9000.00, ROP 564.00, Diff 800.00, Temp 165.00
08/02/2021 | 22:35 | 22:40 | 0.08 | 5105 | 5105 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 22:40 | 22:50 | 0.17 | 5105 | 5198 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5105.00 t/5198.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 558.00, Diff 800.00, Temp 165.00
08/02/2021 | 22:50 | 22:55 | 0.08 | 5198 | 5198 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 22:55 | 23:05 | 0.17 | 5198 | 5292 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5198.00 t/5292.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 564.00, Diff 800.00, Temp 165.00
08/02/2021 | 23:05 | 23:10 | 0.08 | 5292 | 5292 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 23:10 | 23:15 | 0.08 | 5292 | 5386 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5292.00 t/5386.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 1128.00, Diff 800.00, Temp 165.00
08/02/2021 | 23:15 | 23:20 | 0.08 | 5386 | 5386 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/02/2021 | 23:20 | 23:25 | 0.08 | 5386 | 5396 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/5386.00 t/5396.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 120.00, Diff 800.00, Temp 165.00
08/02/2021 | 23:25 | 23:40 | 0.25 | 5396 | 5406 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5396.00 t/5406.00, TF 80.00G, w/WOB 30.00,Flow 870.00, Press 4400.00, Tq 10000.00, ROP 40.00, Diff 800.00, Temp 165.00
08/02/2021 | 23:40 | 23:55 | 0.25 | 5406 | 5494 | 88 | INT | 2: BHA 2 | 2K | Rotary Drill f/5406.00 t/5494.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 352.00, Diff 800.00, Temp 165.00
08/02/2021 | 23:55 | 24:00 | 0.08 | 5494 | 5494 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_3_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/03/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 39830
|  |  |  | 24hr Summary: |  | Drill ahead in Intermediate
|  |  |  | 24hr Lookahead: |  | Finish drilling vertical section & start curve
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 5494 |  | 3523 |  | Csg Shoe MD(Usft): |  | 3513 |  | 600: | 43 | PV: | 16
End Depth (Usft): |  | 9452 |  | 9452 |  | OD (in): |  | 10.75 |  | 300: | 27 | YP: | 11
Total Drilled (Usft): |  | 3958 |  | 5929 |  | Weight (ft/lbs): |  | 44.5 |  | 200: | 20 | Viscosity: | 47
Slide Drilled (Usft): |  | 271 |  | 323 | [5 empty] | 100: | 15 | Chlorides: | 69200
Rotary Drilled (Usft): |  | 3687 |  | 5606 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.40 / 9.20
Drlg/Circ Hrs: |  | 19.97 / 3.73 |  | 23.80 / 6.40 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 10.2 |  | 10.75 |  | SN: |  | 56410 |  | 10s Gel: | 6 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 9.77 |  | 13.05 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 377.51 / 26.57 |  | 429.58 / 30.05 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 34 |  | Grade In: |  | New
% Slide: |  | 6.85 |  | 5.45 |  | Grade Out: |  | 0-1-CT-S-X-I-WT-TD
% Rotary: |  | 93.15 |  | 94.55 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  |  |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Xavier Cantu |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.014 |  |  |  | 8 | 2 |  |  | 100 |  | 37.56 |  | 39.06
NMPC |  |  |  | 8 | 3.25 |  |  | 162.87 |  | 9.21 |  | 48.27
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.97 |  | 52.24
NMDC |  |  |  | 7.812 | 3.312 |  |  | 157.9 |  | 27.55 |  | 79.79
NMDC |  |  |  | 8 | 3.312 |  |  | 151.3 |  | 28.75 |  | 108.54
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 100 |  | 2.55 |  | 111.09
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 298.32
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 573.17
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 575.84
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2637.54
Agitator |  |  |  | 6.562 | 3.75 |  |  | 80 |  | 24.65 |  | 2662.19
2662.19
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800058 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
5510 | 10.24 | 114.11 | 5452.9 | -241.71 | 636.37 | 1.62 |  | 84.4 | 507.77 | 0.28 |  | 9.1 | 94
5603 | 10.76 | 115.3 | 5544.34 | -248.8 | 651.77 | 0.61 |  | 23.22 | 521.15 | 0.56 |  | 1.28 | 93
5697 | 10.9 | 113.21 | 5636.67 | -256.05 | 667.87 | 0.44 |  | -71.41 | 535.01 | 0.15 |  | -2.22 | 94
5791 | 10.06 | 108.74 | 5729.1 | -262.19 | 683.81 | 1.24 |  | -138.12 | 547.81 | -0.89 |  | -4.76 | 94
5885 | 8.85 | 105.16 | 5821.82 | -266.72 | 698.57 | 1.43 |  | -155.84 | 558.62 | -1.29 |  | -3.81 | 94
5978 | 9.82 | 115.15 | 5913.59 | -271.96 | 712.65 | 2.03 |  | 64.09 | 569.77 | 1.04 |  | 10.74 | 93
6072 | 10.23 | 116.84 | 6006.16 | -279.14 | 727.36 | 0.54 |  | 36.5 | 582.91 | 0.44 |  | 1.8 | 94
6166 | 9.62 | 114.42 | 6098.75 | -286.15 | 741.96 | 0.79 |  | -146.82 | 595.87 | -0.65 |  | -2.57 | 94
6260 | 8.72 | 111.01 | 6191.55 | -291.95 | 755.76 | 1.12 |  | -150.55 | 607.38 | -0.96 |  | -3.63 | 94
6353 | 8.63 | 114.52 | 6283.49 | -297.38 | 768.69 | 0.58 |  | 101.38 | 618.15 | -0.1 |  | 3.77 | 93
6448 | 8.25 | 114.69 | 6377.46 | -303.18 | 781.37 | 0.4 |  | 176.33 | 629.14 | -0.4 |  | 0.18 | 95
6542 | 8.74 | 115.12 | 6470.43 | -309.03 | 793.96 | 0.53 |  | 7.6 | 640.14 | 0.52 |  | 0.46 | 94
6636 | 8.46 | 111.54 | 6563.37 | -314.6 | 806.86 | 0.64 |  | -119.37 | 651.02 | -0.3 |  | -3.81 | 94
6731 | 8.43 | 111.86 | 6657.34 | -319.76 | 819.82 | 0.06 |  | 122.71 | 661.58 | -0.03 |  | 0.34 | 95
6825 | 7.46 | 114.02 | 6750.44 | -324.81 | 831.79 | 1.08 |  | 163.96 | 671.57 | -1.03 |  | 2.3 | 94
6919 | 7.44 | 111.9 | 6843.64 | -329.56 | 843.01 | 0.29 |  | -95.21 | 680.96 | -0.02 |  | -2.26 | 94
7013 | 7.41 | 106.37 | 6936.86 | -333.54 | 854.48 | 0.76 |  | -95.14 | 689.77 | -0.03 |  | -5.88 | 94
7106 | 8.04 | 104.56 | 7029.01 | -336.87 | 866.52 | 0.73 |  | -22.01 | 698.28 | 0.68 |  | -1.95 | 93
7200 | 8.57 | 107.09 | 7122.03 | -340.58 | 879.58 | 0.68 |  | 35.84 | 707.59 | 0.56 |  | 2.69 | 94
7294 | 9 | 109.96 | 7214.92 | -345.15 | 893.19 | 0.65 |  | 46.97 | 717.91 | 0.46 |  | 3.05 | 94
7388 | 8.47 | 114.49 | 7307.83 | -350.53 | 906.4 | 0.92 |  | 129.84 | 728.77 | -0.56 |  | 4.82 | 94
7482 | 8.8 | 118.36 | 7400.77 | -356.81 | 919.03 | 0.71 |  | 62.33 | 740.17 | 0.35 |  | 4.12 | 94
7577 | 8.01 | 116.52 | 7494.75 | -363.22 | 931.34 | 0.88 |  | -162.11 | 751.53 | -0.83 |  | -1.94 | 95
7671 | 8.46 | 119.84 | 7587.78 | -369.58 | 943.2 | 0.7 |  | 48.23 | 762.65 | 0.48 |  | 3.53 | 94
7764 | 7.21 | 121.34 | 7679.91 | -376.02 | 954.12 | 1.36 |  | 171.45 | 773.39 | -1.34 |  | 1.61 | 93
7858 | 7.16 | 115.38 | 7773.17 | -381.6 | 964.45 | 0.79 |  | -96.79 | 783.11 | -0.05 |  | -6.34 | 94
7952 | 6.39 | 116.22 | 7866.52 | -386.42 | 974.44 | 0.83 |  | 173.08 | 791.99 | -0.82 |  | 0.89 | 94
8046 | 4.42 | 110.76 | 7960.09 | -390.02 | 982.52 | 2.16 |  | -168.08 | 798.9 | -2.1 |  | -5.81 | 94
8140 | 2.35 | 117.88 | 8053.93 | -392.2 | 987.61 | 2.24 |  | 172.06 | 803.19 | -2.2 |  | 7.57 | 94
8234 | 2.73 | 120.61 | 8147.83 | -394.25 | 991.24 | 0.42 |  | 19.03 | 806.67 | 0.4 |  | 2.9 | 94
8328 | 3.42 | 113.53 | 8241.7 | -396.5 | 995.74 | 0.84 |  | -32.4 | 810.75 | 0.73 |  | -7.53 | 94
8422 | 2.88 | 113.85 | 8335.56 | -398.58 | 1000.47 | 0.57 |  | 178.29 | 814.77 | -0.57 |  | 0.34 | 94
8516 | 2.76 | 107.26 | 8429.44 | -400.21 | 1004.79 | 0.37 |  | -113.58 | 818.2 | -0.13 |  | -7.01 | 94
8610 | 2.37 | 96.66 | 8523.35 | -401.1 | 1008.88 | 0.65 |  | -134.64 | 820.89 | -0.41 |  | -11.28 | 94
8705 | 1.46 | 85.59 | 8618.29 | -401.24 | 1012.04 | 1.03 |  | -163.35 | 822.46 | -0.96 |  | -11.65 | 95
8799 | 1.07 | 42.42 | 8712.27 | -400.5 | 1013.82 | 1.06 |  | -132.87 | 822.63 | -0.41 |  | 0 | 94
8893 | 1.63 | 14.92 | 8806.25 | -398.56 | 1014.76 | 0.89 |  | -63.46 | 821.34 | 0.6 |  | 0 | 94
8987 | 1.78 | 351.48 | 8900.21 | -395.82 | 1014.89 | 0.75 |  | -89.74 | 818.97 | 0.16 |  | -24.94 | 94
9080 | 2.3 | 339.93 | 8993.15 | -392.64 | 1014.03 | 0.71 |  | -44.2 | 815.75 | 0.56 |  | -12.42 | 93
9174 | 2.59 | 325.39 | 9087.06 | -389.12 | 1012.18 | 0.73 |  | -72.32 | 811.77 | 0.31 |  | -15.47 | 94
9268 | 2.23 | 334.46 | 9180.98 | -385.72 | 1010.18 | 0.56 |  | 137.82 | 807.84 | -0.38 |  | 9.65 | 94
9362 | 2.59 | 325.52 | 9274.9 | -382.32 | 1008.19 | 0.55 |  | -50.76 | 803.9 | 0.38 |  | -9.51 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 198.23 | 26.69 | 80 | 224 | 868 | 4909.75 | 4263.82 | 0 | 219.12 | 190.94 | 192.82 | 15287.44 | 0
Run | 241.51 | 26.99 | 79.78 | 222 | 854.04 | 4811.56 | 3984.57 | 0 | 203.87 | 180.43 | 179.22 | 13498.83 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/03/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/03/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/03/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/03/2021 | 00:00 | 00:05 | 0.08 | 5494 | 5504 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5494.00 t/5504.00, TF 80.00G, w/WOB 30.00,Flow 870.00, Press 4400.00, Tq 10000.00, ROP 120.00, Diff 800.00, Temp 165.00
08/03/2021 | 00:05 | 00:10 | 0.08 | 5504 | 5574 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/5504.00 t/5574.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 840.00, Diff 800.00, Temp 165.00
08/03/2021 | 00:10 | 00:15 | 0.08 | 5574 | 5574 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 00:15 | 00:25 | 0.17 | 5574 | 5667 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5574.00 t/5667.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 558.00, Diff 800.00, Temp 165.00
08/03/2021 | 00:25 | 00:30 | 0.08 | 5667 | 5667 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 00:30 | 00:35 | 0.08 | 5667 | 5761 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5667.00 t/5761.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 1128.00, Diff 800.00, Temp 165.00
08/03/2021 | 00:35 | 00:40 | 0.08 | 5761 | 5761 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 00:40 | 00:50 | 0.17 | 5761 | 5855 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5761.00 t/5855.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 564.00, Diff 800.00, Temp 165.00
08/03/2021 | 00:50 | 00:55 | 0.08 | 5855 | 5855 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 00:55 | 01:00 | 0.08 | 5855 | 5866 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/5855.00 t/5866.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 132.00, Diff 800.00, Temp 165.00
08/03/2021 | 01:00 | 01:05 | 0.08 | 5866 | 5871 | 5 | INT | 2: BHA 2 | 2J | Slide Drill f/5866.00 t/5871.00, TF 80.00G, w/WOB 30.00,Flow 870.00, Press 4400.00, Tq 10000.00, ROP 60.00, Diff 800.00, Temp 165.00
08/03/2021 | 01:05 | 01:15 | 0.17 | 5871 | 5949 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/5871.00 t/5949.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 468.00, Diff 800.00, Temp 165.00
08/03/2021 | 01:15 | 01:20 | 0.08 | 5949 | 5949 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 01:20 | 01:25 | 0.08 | 5949 | 5960 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/5949.00 t/5960.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 132.00, Diff 800.00, Temp 165.00
08/03/2021 | 01:25 | 01:35 | 0.17 | 5960 | 5970 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/5960.00 t/5970.00, TF 70.00G, w/WOB 30.00,Flow 870.00, Press 4400.00, Tq 10000.00, ROP 60.00, Diff 800.00, Temp 181.00
08/03/2021 | 01:35 | 01:45 | 0.17 | 5970 | 6042 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/5970.00 t/6042.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 432.00, Diff 800.00, Temp 181.00
08/03/2021 | 01:45 | 01:50 | 0.08 | 6042 | 6042 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 01:50 | 01:55 | 0.08 | 6042 | 6136 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6042.00 t/6136.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4400.00, Tq 10000.00, ROP 1128.00, Diff 800.00, Temp 181.00
08/03/2021 | 01:55 | 02:00 | 0.08 | 6136 | 6136 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 02:00 | 02:10 | 0.17 | 6136 | 6230 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6136.00 t/6230.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 564.00, Diff 800.00, Temp 181.00
08/03/2021 | 02:10 | 02:15 | 0.08 | 6230 | 6230 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 02:15 | 02:25 | 0.17 | 6230 | 6324 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6230.00 t/6324.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 564.00, Diff 800.00, Temp 181.00
08/03/2021 | 02:25 | 02:30 | 0.08 | 6324 | 6324 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 02:30 | 02:35 | 0.08 | 6324 | 6335 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/6324.00 t/6335.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 132.00, Diff 800.00, Temp 181.00
08/03/2021 | 02:35 | 02:50 | 0.25 | 6335 | 6344 | 9 | INT | 2: BHA 2 | 2J | Slide Drill f/6335.00 t/6344.00, TF 45.00G, w/WOB 30.00,Flow 870.00, Press 4600.00, Tq 12000.00, ROP 36.00, Diff 800.00, Temp 190.00
08/03/2021 | 02:50 | 02:55 | 0.08 | 6344 | 6417 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/6344.00 t/6417.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 876.00, Diff 800.00, Temp 190.00
08/03/2021 | 02:55 | 03:00 | 0.08 | 6417 | 6417 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 03:00 | 03:10 | 0.17 | 6417 | 6512 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/6417.00 t/6512.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 570.00, Diff 800.00, Temp 181.00
08/03/2021 | 03:10 | 03:15 | 0.08 | 6512 | 6512 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 03:15 | 03:20 | 0.08 | 6512 | 6523 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/6512.00 t/6523.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 132.00, Diff 800.00, Temp 181.00
08/03/2021 | 03:20 | 03:35 | 0.25 | 6523 | 6533 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/6523.00 t/6533.00, TF 0.00G, w/WOB 30.00,Flow 870.00, Press 4600.00, Tq 12000.00, ROP 40.00, Diff 800.00, Temp 181.00
08/03/2021 | 03:35 | 03:45 | 0.17 | 6533 | 6606 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/6533.00 t/6606.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 438.00, Diff 800.00, Temp 181.00
08/03/2021 | 03:45 | 03:50 | 0.08 | 6606 | 6606 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 03:50 | 03:55 | 0.08 | 6606 | 6617 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/6606.00 t/6617.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 132.00, Diff 800.00, Temp 181.00
08/03/2021 | 03:55 | 04:15 | 0.33 | 6617 | 6627 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/6617.00 t/6627.00, TF 0.00G, w/WOB 30.00,Flow 870.00, Press 4600.00, Tq 12000.00, ROP 30.00, Diff 800.00, Temp 181.00
08/03/2021 | 04:15 | 04:25 | 0.17 | 6627 | 6700 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/6627.00 t/6700.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 438.00, Diff 800.00, Temp 181.00
08/03/2021 | 04:25 | 04:30 | 0.08 | 6700 | 6700 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 04:30 | 04:35 | 0.08 | 6700 | 6712 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/6700.00 t/6712.00, w/WOB 30.00,Flow 870.00, RPM 80.00, Press 4600.00, Tq 12000.00, ROP 144.00, Diff 800.00, Temp 181.00
08/03/2021 | 04:35 | 05:00 | 0.42 | 6712 | 6722 | 10 | INT | 2: BHA 2 | 2J | Slide Drill f/6712.00 t/6722.00, TF 0.00G, w/WOB 30.00,Flow 870.00, Press 4600.00, Tq 0.00, ROP 24.00, Diff 800.00, Temp 181.00
08/03/2021 | 05:00 | 05:10 | 0.17 | 6722 | 6795 | 73 | INT | 2: BHA 2 | 2K | Rotary Drill f/6722.00 t/6795.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 4933.00, Tq 15000.00, ROP 438.00, Diff 642.00, Temp 201.00
08/03/2021 | 05:10 | 05:15 | 0.08 | 6795 | 6795 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 05:15 | 05:20 | 0.08 | 6795 | 6810 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/6795.00 t/6810.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 4933.00, Tq 15000.00, ROP 180.00, Diff 642.00, Temp 201.00
08/03/2021 | 05:20 | 06:25 | 1.08 | 6810 | 6830 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/6810.00 t/6830.00, TF 0.00G, w/WOB 25.00,Flow 870.00, Press 4400.00, Tq 0.00, ROP 18.46, Diff 109.00, Temp 201.00
08/03/2021 | 06:25 | 06:35 | 0.17 | 6830 | 6889 | 59 | INT | 2: BHA 2 | 2K | Rotary Drill f/6830.00 t/6889.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 4933.00, Tq 15000.00, ROP 354.00, Diff 642.00, Temp 201.00
08/03/2021 | 06:35 | 06:38 | 0.05 | 6889 | 6889 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 06:38 | 06:41 | 0.05 | 6889 | 6903 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/6889.00 t/6903.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 4933.00, Tq 15000.00, ROP 280.00, Diff 642.00, Temp 201.00
08/03/2021 | 06:41 | 07:05 | 0.4 | 6903 | 6918 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6903.00 t/6918.00, TF 0.00G, w/WOB 15.00,Flow 870.00, Press 4700.00, Tq 0.00, ROP 37.50, Diff 204.00, Temp 201.00
08/03/2021 | 07:05 | 07:12 | 0.12 | 6918 | 6983 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/6918.00 t/6983.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 5144.00, Tq 15000.00, ROP 557.14, Diff 648.00, Temp 201.00
08/03/2021 | 07:12 | 07:15 | 0.05 | 6983 | 6983 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 07:15 | 07:18 | 0.05 | 6983 | 6998 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/6983.00 t/6998.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 5144.00, Tq 15000.00, ROP 300.00, Diff 648.00, Temp 201.00
08/03/2021 | 07:18 | 08:00 | 0.7 | 6998 | 7013 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/6998.00 t/7013.00, TF 0.00G, w/WOB 15.00,Flow 870.00, Press 4600.00, Tq 0.00, ROP 21.43, Diff 104.00, Temp 204.00
08/03/2021 | 08:00 | 08:09 | 0.15 | 7013 | 7077 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/7013.00 t/7077.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 5222.00, Tq 15000.00, ROP 426.67, Diff 726.00, Temp 204.00
08/03/2021 | 08:09 | 08:12 | 0.05 | 7077 | 7077 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 08:12 | 08:15 | 0.05 | 7077 | 7090 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/7077.00 t/7090.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 5150.00, Tq 15000.00, ROP 260.00, Diff 654.00, Temp 204.00
08/03/2021 | 08:15 | 09:00 | 0.75 | 7090 | 7105 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7090.00 t/7105.00, TF 0.00G, w/WOB 20.00,Flow 870.00, Press 4500.00, Tq 0.00, ROP 20.00, Diff 103.00, Temp 204.00
08/03/2021 | 09:00 | 09:08 | 0.13 | 7105 | 7170 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/7105.00 t/7170.00, w/WOB 45.00,Flow 870.00, RPM 80.00, Press 5271.00, Tq 15000.00, ROP 487.50, Diff 874.00, Temp 204.00
08/03/2021 | 09:08 | 09:11 | 0.05 | 7170 | 7170 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 09:11 | 09:14 | 0.05 | 7170 | 7184 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/7170.00 t/7184.00, w/WOB 45.00,Flow 870.00, RPM 80.00, Press 5271.00, Tq 15000.00, ROP 280.00, Diff 874.00, Temp 204.00
08/03/2021 | 09:14 | 09:51 | 0.62 | 7184 | 7199 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7184.00 t/7199.00, TF 60.00G, w/WOB 12.00,Flow 870.00, Press 4554.00, Tq 0.00, ROP 24.32, Diff 150.00, Temp 204.00
08/03/2021 | 09:51 | 10:00 | 0.15 | 7199 | 7264 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/7199.00 t/7264.00, w/WOB 45.00,Flow 870.00, RPM 80.00, Press 5188.00, Tq 15000.00, ROP 433.33, Diff 784.00, Temp 204.00
08/03/2021 | 10:00 | 10:18 | 0.3 | 7264 | 7264 | 0 | INT | 2: BHA 2 | 8D | Change O-ring on vibrator hose
08/03/2021 | 10:18 | 10:22 | 0.07 | 7264 | 7264 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 10:22 | 10:27 | 0.08 | 7264 | 7291 | 27 | INT | 2: BHA 2 | 2K | Rotary Drill f/7264.00 t/7291.00, w/WOB 45.00,Flow 870.00, RPM 80.00, Press 5188.00, Tq 15000.00, ROP 324.00, Diff 784.00, Temp 210.00
08/03/2021 | 10:27 | 11:27 | 1 | 7291 | 7306 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7291.00 t/7306.00, TF 60.00G, w/WOB 15.00,Flow 700.00, Press 3310.00, Tq 0.00, ROP 15.00, Diff 150.00, Temp 210.00
08/03/2021 | 11:27 | 11:39 | 0.2 | 7306 | 7358 | 52 | INT | 2: BHA 2 | 2K | Rotary Drill f/7306.00 t/7358.00, w/WOB 45.00,Flow 870.00, RPM 80.00, Press 5322.00, Tq 15000.00, ROP 260.00, Diff 884.00, Temp 210.00
08/03/2021 | 11:39 | 11:42 | 0.05 | 7358 | 7358 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 11:42 | 11:46 | 0.07 | 7358 | 7372 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/7358.00 t/7372.00, w/WOB 45.00,Flow 870.00, RPM 80.00, Press 5322.00, Tq 15694.00, ROP 210.00, Diff 884.00, Temp 210.00
08/03/2021 | 11:46 | 12:19 | 0.55 | 7372 | 7387 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/7372.00 t/7387.00, TF 70.00G, w/WOB 12.00,Flow 870.00, Press 4620.00, Tq 0.00, ROP 27.27, Diff 182.00, Temp 210.00
08/03/2021 | 12:19 | 12:31 | 0.2 | 7387 | 7452 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/7387.00 t/7452.00, w/WOB 42.00,Flow 870.00, RPM 80.00, Press 5333.00, Tq 16211.00, ROP 325.00, Diff 895.00, Temp 213.00
08/03/2021 | 12:31 | 12:35 | 0.07 | 7452 | 7452 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 12:35 | 12:39 | 0.07 | 7452 | 7466 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/7452.00 t/7466.00, w/WOB 42.00,Flow 870.00, RPM 80.00, Press 5333.00, Tq 16211.00, ROP 210.00, Diff 895.00, Temp 213.00
08/03/2021 | 12:39 | 12:54 | 0.25 | 7466 | 7478 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7466.00 t/7478.00, TF 30.00G, w/WOB 12.00,Flow 870.00, Press 4620.00, Tq 0.00, ROP 48.00, Diff 182.00, Temp 213.00
08/03/2021 | 12:54 | 13:08 | 0.23 | 7478 | 7546 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/7478.00 t/7546.00, w/WOB 44.00,Flow 870.00, RPM 80.00, Press 5426.00, Tq 18074.00, ROP 291.43, Diff 878.00, Temp 213.00
08/03/2021 | 13:08 | 13:11 | 0.05 | 7546 | 7546 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 13:11 | 13:26 | 0.25 | 7546 | 7641 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/7546.00 t/7641.00, w/WOB 43.00,Flow 870.00, RPM 80.00, Press 5455.00, Tq 18603.00, ROP 380.00, Diff 907.00, Temp 213.00
08/03/2021 | 13:26 | 13:29 | 0.05 | 7641 | 7641 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 13:29 | 13:33 | 0.07 | 7641 | 7653 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/7641.00 t/7653.00, w/WOB 43.00,Flow 870.00, RPM 80.00, Press 5455.00, Tq 18603.00, ROP 180.00, Diff 907.00, Temp 213.00
08/03/2021 | 13:33 | 13:48 | 0.25 | 7653 | 7665 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7653.00 t/7665.00, TF 30.00G, w/WOB 12.00,Flow 870.00, Press 4750.00, Tq 0.00, ROP 48.00, Diff 202.00, Temp 215.00
08/03/2021 | 13:48 | 13:56 | 0.13 | 7665 | 7735 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/7665.00 t/7735.00, w/WOB 41.00,Flow 870.00, RPM 80.00, Press 5455.00, Tq 17987.00, ROP 525.00, Diff 907.00, Temp 218.00
08/03/2021 | 13:56 | 13:59 | 0.05 | 7735 | 7735 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 13:59 | 14:14 | 0.25 | 7735 | 7828 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/7735.00 t/7828.00, w/WOB 40.00,Flow 870.00, RPM 80.00, Press 5455.00, Tq 18603.00, ROP 372.00, Diff 907.00, Temp 219.00
08/03/2021 | 14:14 | 14:17 | 0.05 | 7828 | 7828 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 14:17 | 14:21 | 0.07 | 7828 | 7842 | 14 | INT | 2: BHA 2 | 2K | Rotary Drill f/7828.00 t/7842.00, w/WOB 35.00,Flow 870.00, RPM 80.00, Press 5455.00, Tq 18603.00, ROP 210.00, Diff 907.00, Temp 219.00
08/03/2021 | 14:21 | 14:33 | 0.2 | 7842 | 7854 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/7842.00 t/7854.00, TF 0.00G, w/WOB 12.00,Flow 870.00, Press 4766.00, Tq 0.00, ROP 60.00, Diff 218.00, Temp 219.00
08/03/2021 | 14:33 | 14:48 | 0.25 | 7854 | 7922 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/7854.00 t/7922.00, w/WOB 32.00,Flow 870.00, RPM 80.00, Press 5122.00, Tq 17141.00, ROP 272.00, Diff 574.00, Temp 219.00
08/03/2021 | 14:48 | 14:51 | 0.05 | 7922 | 7922 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 14:51 | 15:03 | 0.2 | 7922 | 8016 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7922.00 t/8016.00, w/WOB 45,Flow 870.00, RPM 80.00, Press 5622, Tq 18833, ROP 470.00, Diff 954.00, Temp 221.00
08/03/2021 | 15:03 | 15:07 | 0.07 | 8016 | 8016 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 15:07 | 15:27 | 0.33 | 8016 | 8110 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8016.00 t/8110.00, w/WOB 42.00,Flow 870.00, RPM 80.00, Press 5622.00, Tq 18833.00, ROP 282.00, Diff 954.00, Temp 221.00
08/03/2021 | 15:27 | 15:30 | 0.05 | 8110 | 8110 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 15:30 | 15:34 | 0.07 | 8110 | 8122 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/8110.00 t/8122.00, w/WOB 38.00,Flow 870.00, RPM 80.00, Press 5622.00, Tq 18000.00, ROP 180.00, Diff 954.00, Temp 221.00
08/03/2021 | 15:34 | 16:08 | 0.57 | 8122 | 8134 | 12 | INT | 2: BHA 2 | 2J | Slide Drill f/8122.00 t/8134.00, TF 30.00G, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 21.18, Diff 171.00, Temp 221.00
08/03/2021 | 16:08 | 16:16 | 0.13 | 8134 | 8204 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/8134.00 t/8204.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 525.00, Diff 571.00, Temp 221.00
08/03/2021 | 16:16 | 17:00 | 0.73 | 8204 | 8204 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 17:00 | 17:04 | 0.07 | 8204 | 8216 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/8204.00 t/8216.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 180.00, Diff 571.00, Temp 221.00
08/03/2021 | 17:04 | 17:25 | 0.35 | 8216 | 8231 | 15 | INT | 2: BHA 2 | 2K | Rotary Drill f/8216.00 t/8231.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 42.86, Diff 571.00, Temp 221.00
08/03/2021 | 17:25 | 17:35 | 0.17 | 8231 | 8298 | 67 | INT | 2: BHA 2 | 2K | Rotary Drill f/8231.00 t/8298.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 402.00, Diff 571.00, Temp 230.00
08/03/2021 | 17:35 | 17:40 | 0.08 | 8298 | 8298 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 17:40 | 17:55 | 0.25 | 8298 | 8392 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8298.00 t/8392.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 376.00, Diff 571.00, Temp 230.00
08/03/2021 | 17:55 | 18:00 | 0.08 | 8392 | 8392 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 18:00 | 18:10 | 0.17 | 8392 | 8486 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8392.00 t/8486.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 564.00, Diff 571.00, Temp 230.00
08/03/2021 | 18:10 | 18:15 | 0.08 | 8486 | 8486 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 18:15 | 18:30 | 0.25 | 8486 | 8580 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8486.00 t/8580.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 376.00, Diff 571.00, Temp 230.00
08/03/2021 | 18:30 | 18:35 | 0.08 | 8580 | 8580 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 18:35 | 18:55 | 0.33 | 8580 | 8674 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8580.00 t/8674.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 282.00, Diff 571.00, Temp 230.00
08/03/2021 | 18:55 | 19:00 | 0.08 | 8674 | 8674 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 19:00 | 19:10 | 0.17 | 8674 | 8769 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/8674.00 t/8769.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 570.00, Diff 571.00, Temp 230.00
08/03/2021 | 19:10 | 19:15 | 0.08 | 8769 | 8769 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 19:15 | 19:30 | 0.25 | 8769 | 8863 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8769.00 t/8863.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 376.00, Diff 571.00, Temp 230.00
08/03/2021 | 19:30 | 19:35 | 0.08 | 8863 | 8863 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 19:35 | 19:50 | 0.25 | 8863 | 8957 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8863.00 t/8957.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 376.00, Diff 571.00, Temp 230.00
08/03/2021 | 19:50 | 19:55 | 0.08 | 8957 | 8957 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 19:55 | 20:10 | 0.25 | 8957 | 9051 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8957.00 t/9051.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 376.00, Diff 571.00, Temp 230.00
08/03/2021 | 20:10 | 20:15 | 0.08 | 9051 | 9051 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 20:15 | 20:30 | 0.25 | 9051 | 9144 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9051.00 t/9144.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 372.00, Diff 571.00, Temp 230.00
08/03/2021 | 20:30 | 20:35 | 0.08 | 9144 | 9144 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 20:35 | 20:40 | 0.08 | 9144 | 9155 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/9144.00 t/9155.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 132.00, Diff 571.00, Temp 230.00
08/03/2021 | 20:40 | 21:25 | 0.75 | 9155 | 9175 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9155.00 t/9175.00, TF 150M, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 26.67, Diff 171.00, Temp 230.00
08/03/2021 | 21:25 | 21:40 | 0.25 | 9175 | 9238 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/9175.00 t/9238.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 252.00, Diff 571.00, Temp 230.00
08/03/2021 | 21:40 | 21:45 | 0.08 | 9238 | 9238 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 21:45 | 21:50 | 0.08 | 9238 | 9256 | 18 | INT | 2: BHA 2 | 2K | Rotary Drill f/9238.00 t/9256.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 216.00, Diff 571.00, Temp 230.00
08/03/2021 | 21:50 | 22:45 | 0.92 | 9256 | 9271 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/9256.00 t/9271.00, TF 150M, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 16.36, Diff 171.00, Temp 230.00
08/03/2021 | 22:45 | 22:55 | 0.17 | 9271 | 9332 | 61 | INT | 2: BHA 2 | 2K | Rotary Drill f/9271.00 t/9332.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 366.00, Diff 571.00, Temp 230.00
08/03/2021 | 22:55 | 23:00 | 0.08 | 9332 | 9332 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 23:00 | 23:15 | 0.25 | 9332 | 9426 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9332.00 t/9426.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 376.00, Diff 571.00, Temp 230.00
08/03/2021 | 23:15 | 23:20 | 0.08 | 9426 | 9426 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/03/2021 | 23:20 | 23:25 | 0.08 | 9426 | 9438 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/9426.00 t/9438.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 5200, Tq 18000, ROP 144.00, Diff 571.00, Temp 235.00
08/03/2021 | 23:25 | 24:00 | 0.58 | 9438 | 9452 | 14 | INT | 2: BHA 2 | 2J | Slide Drill f/9438.00 t/9452.00, TF 150M, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 24.00, Diff 171.00, Temp 235.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_4_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/04/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 46680
|  |  |  | 24hr Summary: |  | Drill to KOP & build curve
|  |  |  | 24hr Lookahead: |  | Standby for casing ops and rig skid
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9452 |  | 3523 |  | Csg Shoe MD(Usft): |  | 3513 |  | 600: | 43 | PV: | 16
End Depth (Usft): |  | 11022 |  | 11022 |  | OD (in): |  | 10.75 |  | 300: | 27 | YP: | 11
Total Drilled (Usft): |  | 1570 |  | 7499 |  | Weight (ft/lbs): |  | 44.5 |  | 200: | 20 | Viscosity: | 47
Slide Drilled (Usft): |  | 332 |  | 655 | [5 empty] | 100: | 15 | Chlorides: | 69200
Rotary Drilled (Usft): |  | 1238 |  | 6844 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.40 / 9.20
Drlg/Circ Hrs: |  | 15.62 / 3.22 |  | 39.42 / 9.62 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 69/31
Slide Drilling Hrs: |  | 10.03 |  | 20.78 |  | SN: |  | 56410 |  | 10s Gel: | 6 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 5.58 |  | 18.63 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 221.73 / 33.09 |  | 367.30 / 31.52 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 58 |  | Grade In: |  | New
% Slide: |  | 21.15 |  | 8.73 |  | Grade Out: |  | 0-1-CT-S-X-I-WT-TD
% Rotary: |  | 78.85 |  | 91.27 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  |  |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Xavier Cantu |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.014 |  |  |  | 8 | 2 |  |  | 100 |  | 37.56 |  | 39.06
NMPC |  |  |  | 8 | 3.25 |  |  | 162.87 |  | 9.21 |  | 48.27
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.97 |  | 52.24
NMDC |  |  |  | 7.812 | 3.312 |  |  | 157.9 |  | 27.55 |  | 79.79
NMDC |  |  |  | 8 | 3.312 |  |  | 151.3 |  | 28.75 |  | 108.54
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 100 |  | 2.55 |  | 111.09
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 298.32
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 573.17
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 575.84
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2637.54
Agitator |  |  |  | 6.562 | 3.75 |  |  | 80 |  | 24.65 |  | 2662.19
2662.19
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800058 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9455 | 2.41 | 326.2 | 9367.81 | -378.96 | 1005.92 | 0.2 |  | 170.98 | 799.87 | -0.19 |  | 0.73 | 93
9549 | 2.27 | 285.28 | 9461.74 | -376.83 | 1003.02 | 1.75 |  | -115.03 | 796.65 | -0.15 |  | -43.53 | 94
9643 | 2.63 | 279.07 | 9555.65 | -376 | 999.09 | 0.48 |  | -39.53 | 794.1 | 0.38 |  | -6.61 | 94
9737 | 1.81 | 247.53 | 9649.58 | -376.23 | 995.59 | 1.53 |  | -138.95 | 792.69 | -0.87 |  | -33.55 | 94
9830 | 1.45 | 239.48 | 9742.55 | -377.39 | 993.22 | 0.46 |  | -151.52 | 792.62 | -0.39 |  | -8.66 | 93
9924 | 1.03 | 228.29 | 9836.52 | -378.55 | 991.57 | 0.51 |  | -155.55 | 792.9 | -0.45 |  | 0 | 94
10018 | 0.84 | 238.15 | 9930.51 | -379.48 | 990.35 | 0.26 |  | 144.6 | 793.16 | -0.2 |  | 0 | 94
10111 | 1.28 | 261.06 | 10023.49 | -380 | 988.75 | 0.65 |  | 55.77 | 792.88 | 0.47 |  | 0 | 93
10205 | 1.26 | 267.74 | 10117.47 | -380.2 | 986.68 | 0.16 |  | 101.02 | 792.11 | -0.02 |  | 0 | 94
10299 | 1.69 | 304.48 | 10211.44 | -379.46 | 984.5 | 1.08 |  | 84.66 | 790.45 | 0.46 |  | 0 | 94
10393 | 1.8 | 296.49 | 10305.4 | -378.02 | 982.04 | 0.28 |  | -69.7 | 788.03 | 0.12 |  | -8.5 | 94
10487 | 1.01 | 308.82 | 10399.37 | -376.84 | 980.07 | 0.9 |  | 165.15 | 786.08 | -0.84 |  | 13.12 | 94
10581 | 1.53 | 108.37 | 10493.36 | -376.72 | 980.62 | 2.66 |  | 167.66 | 786.22 | 0.55 |  | 0 | 94
10675 | 6.8 | 127.47 | 10587.08 | -380.5 | 986.23 | 5.72 |  | 24.42 | 792.16 | 5.61 |  | 20.32 | 94
10769 | 13.04 | 138.23 | 10679.64 | -391.81 | 997.72 | 6.9 |  | 21.91 | 807.49 | 6.64 |  | 11.45 | 94
10863 | 14.75 | 147.45 | 10770.9 | -409.8 | 1011.23 | 2.97 |  | 56.86 | 829.69 | 1.82 |  | 9.81 | 94
10956 | 16.39 | 150.04 | 10860.48 | -431.15 | 1024.15 | 1.91 |  | 24.22 | 854.59 | 1.76 |  | 2.78 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 100.53 | 19.68 | 70.48 | 207 | 823.61 | 4787.48 | 4468.03 | 0 | 300.81 | 265.81 | 230.32 | 18457.09 | 0
Run | 190.25 | 25.44 | 78 | 219 | 847.58 | 4806.45 | 4087.22 | 0 | 224.45 | 198.56 | 190.07 | 14481.55 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/04/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/04/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/04/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/04/2021 | 00:00 | 00:10 | 0.17 | 9452 | 9454 | 2 | INT | 2: BHA 2 | 2J | Slide Drill f/9452.00 t/9454.00, TF 150.00M, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 12.00, Diff 171.00, Temp 235.00
08/04/2021 | 00:10 | 00:20 | 0.17 | 9454 | 9519 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/9454.00 t/9519.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 390.00, Diff 171.00, Temp 235.00
08/04/2021 | 00:20 | 00:25 | 0.08 | 9519 | 9519 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 00:25 | 00:30 | 0.08 | 9519 | 9530 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/9519.00 t/9530.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 132.00, Diff 171.00, Temp 235.00
08/04/2021 | 00:30 | 01:15 | 0.75 | 9530 | 9548 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/9530.00 t/9548.00, TF 150.00M, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 24.00, Diff 171.00, Temp 235.00
08/04/2021 | 01:15 | 01:25 | 0.17 | 9548 | 9613 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/9548.00 t/9613.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 390.00, Diff 171.00, Temp 235.00
08/04/2021 | 01:25 | 01:30 | 0.08 | 9613 | 9613 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 01:30 | 01:35 | 0.08 | 9613 | 9625 | 12 | INT | 2: BHA 2 | 2K | Rotary Drill f/9613.00 t/9625.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 144.00, Diff 171.00, Temp 235.00
08/04/2021 | 01:35 | 02:40 | 1.08 | 9625 | 9645 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9625.00 t/9645.00, TF 180.00M, w/WOB 10.00,Flow 870.00, Press 4800.00, Tq 0.00, ROP 18.46, Diff 171.00, Temp 235.00
08/04/2021 | 02:40 | 02:50 | 0.17 | 9645 | 9707 | 62 | INT | 2: BHA 2 | 2K | Rotary Drill f/9645.00 t/9707.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 372.00, Diff 171.00, Temp 235.00
08/04/2021 | 02:50 | 02:55 | 0.08 | 9707 | 9707 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 02:55 | 03:00 | 0.08 | 9707 | 9720 | 13 | INT | 2: BHA 2 | 2K | Rotary Drill f/9707.00 t/9720.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 156.00, Diff 171.00, Temp 235.00
08/04/2021 | 03:00 | 04:00 | 1 | 9720 | 9740 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9720.00 t/9740.00, TF 120M, w/WOB 10.00,Flow 745, Press 3900, Tq 0.00, ROP 20.00, Diff 200.00, Temp 235.00
08/04/2021 | 04:00 | 04:15 | 0.25 | 9740 | 9801 | 61 | INT | 2: BHA 2 | 2K | Rotary Drill f/9740.00 t/9801.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 244.00, Diff 171.00, Temp 235.00
08/04/2021 | 04:15 | 04:20 | 0.08 | 9801 | 9801 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 04:20 | 04:30 | 0.17 | 9801 | 9894 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9801.00 t/9894.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 558.00, Diff 171.00, Temp 235.00
08/04/2021 | 04:30 | 04:35 | 0.08 | 9894 | 9894 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 04:35 | 04:55 | 0.33 | 9894 | 9988 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9894.00 t/9988.00, w/WOB 10.00,Flow 870.00, RPM 80, Press 4800.00, Tq 18000, ROP 282.00, Diff 171.00, Temp 235.00
08/04/2021 | 04:55 | 05:00 | 0.08 | 9988 | 9988 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 05:00 | 05:25 | 0.42 | 9988 | 10082 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9988.00 t/10082.00, w/WOB 10.00,Flow 870.00, RPM 80.00, Press 4800.00, Tq 18000.00, ROP 225.60, Diff 171.00, Temp 235.00
08/04/2021 | 05:25 | 05:30 | 0.08 | 10082 | 10082 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 05:30 | 06:04 | 0.57 | 10082 | 10175 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/10082.00 t/10175.00, w/WOB 40.00,Flow 670, RPM 80.00, Press 4021.00, Tq 19308.00, ROP 164.12, Diff 702.00, Temp 243.00
08/04/2021 | 06:04 | 06:09 | 0.08 | 10175 | 10175 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 06:09 | 06:32 | 0.38 | 10175 | 10269 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10175.00 t/10269.00, w/WOB 40.00,Flow 813.00, RPM 80.00, Press 5408.00, Tq 19032.00, ROP 245.22, Diff 665.00, Temp 244.00
08/04/2021 | 06:32 | 06:37 | 0.08 | 10269 | 10269 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 06:37 | 06:58 | 0.35 | 10269 | 10363 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10269.00 t/10363.00, w/WOB 38,Flow 670, RPM 80.00, Press 4232, Tq 2020, ROP 268.57, Diff 632.00, Temp 246.00
08/04/2021 | 06:58 | 07:02 | 0.07 | 10363 | 10363 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 07:02 | 07:28 | 0.43 | 10363 | 10457 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10363.00 t/10457.00, w/WOB 38.00,Flow 870.00, RPM 80.00, Press 5322.00, Tq 20200.00, ROP 216.92, Diff 579.00, Temp 246.00
08/04/2021 | 07:28 | 07:32 | 0.07 | 10457 | 10457 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 07:32 | 07:37 | 0.08 | 10457 | 10466 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/10457.00 t/10466.00, w/WOB 38.00,Flow 870.00, RPM 80.00, Press 5322.00, Tq 20200.00, ROP 108.00, Diff 581.00, Temp 246.00
08/04/2021 | 07:37 | 08:09 | 0.53 | 10466 | 10481 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/10466.00 t/10481.00, TF 120.00M, w/WOB 12.00,Flow 727.00, Press 4122.00, Tq 0.00, ROP 28.12, Diff 202.00, Temp 246.00
08/04/2021 | 08:09 | 08:28 | 0.32 | 10481 | 10551 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/10481.00 t/10551.00, w/WOB 40.00,Flow 813.00, RPM 80.00, Press 5400.00, Tq 19874.00, ROP 221.05, Diff 657.00, Temp 246.00
08/04/2021 | 08:28 | 08:31 | 0.05 | 10551 | 10551 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 08:31 | 08:35 | 0.07 | 10551 | 10561 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/10551.00 t/10561.00, w/WOB 40.00,Flow 813.00, RPM 80.00, Press 5400.00, Tq 19874.00, ROP 150.00, Diff 657.00, Temp 246.00
08/04/2021 | 08:35 | 09:55 | 1.33 | 10561 | 10645 | 84 | INT | 2: BHA 2 | 2J | Slide Drill f/10561.00 t/10645.00, TF 120.00M, w/WOB 12.00,Flow 727.00, Press 4130.00, Tq 0.00, ROP 63.00, Diff 210.00, Temp 246.00
08/04/2021 | 09:55 | 10:55 | 1 | 10645 | 10645 | 0 | INT | 2: BHA 2 | 8P | Rig Service
08/04/2021 | 10:55 | 11:00 | 0.08 | 10645 | 10645 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 11:00 | 11:10 | 0.17 | 10645 | 10670 | 25 | INT | 2: BHA 2 | 2K | Rotary Drill f/10645.00 t/10670.00, w/WOB 35.00,Flow 813.00, RPM 30.00, Press 4920.00, Tq 17744.00, ROP 150.00, Diff 400.00, Temp 246.00
08/04/2021 | 11:10 | 13:10 | 2 | 10670 | 10739 | 69 | INT | 2: BHA 2 | 2J | Slide Drill f/10670.00 t/10739.00, TF 150.00M, w/WOB 15.00,Flow 813.00, Press 4715.00, Tq 0.00, ROP 34.50, Diff 195.00, Temp 246.00
08/04/2021 | 13:10 | 13:15 | 0.08 | 10739 | 10739 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 13:15 | 13:23 | 0.13 | 10739 | 10759 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/10739.00 t/10759.00, w/WOB 30.00,Flow 813.00, RPM 30.00, Press 5000.00, Tq 17124.00, ROP 150.00, Diff 480.00, Temp 246.00
08/04/2021 | 13:23 | 14:25 | 1.03 | 10759 | 10813 | 54 | INT | 2: BHA 2 | 2J | Slide Drill f/10759.00 t/10813.00, TF 30.00G, w/WOB 12.00,Flow 813.00, Press 4720.00, Tq 0.00, ROP 52.26, Diff 200.00, Temp 246.00
08/04/2021 | 14:25 | 14:30 | 0.08 | 10813 | 10813 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 14:30 | 14:42 | 0.2 | 10813 | 10833 | 20 | INT | 2: BHA 2 | 2K | Rotary Drill f/10813.00 t/10833.00, w/WOB 25.00,Flow 813.00, RPM 30.00, Press 5000.00, Tq 17500.00, ROP 100.00, Diff 480.00, Temp 246.00
08/04/2021 | 14:42 | 14:46 | 0.07 | 10833 | 10833 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 14:46 | 15:26 | 0.67 | 10833 | 10927 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/10833.00 t/10927.00, w/WOB 25.00,Flow 813.00, RPM 30.00, Press 5000.00, Tq 17500.00, ROP 141.00, Diff 480.00, Temp 246.00
08/04/2021 | 15:26 | 15:34 | 0.13 | 10927 | 10927 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 15:34 | 17:42 | 2.13 | 10927 | 10977 | 50 | INT | 2: BHA 2 | 2J | Slide Drill f/10927.00 t/10977.00, TF 20.00G, w/WOB 15.00,Flow 813.00, Press 4700.00, Tq 0.00, ROP 23.44, Diff 180.00, Temp 246.00
08/04/2021 | 17:42 | 18:00 | 0.3 | 10977 | 11022 | 45 | INT | 2: BHA 2 | 2K | Rotary Drill f/10977.00 t/11022.00, w/WOB 15.00,Flow 813.00, RPM 0.00, Press 4700.00, Tq 17500, ROP 150.00, Diff 180.00, Temp 246.00
08/04/2021 | 18:00 | 18:05 | 0.08 | 11022 | 11022 | 0 | INT | 2: BHA 2 | 5A | Survey & Connection
08/04/2021 | 18:05 | 19:50 | 1.75 | 11022 | 11022 | 0 | INT | 2: BHA 2 | 5A | Circ (TD)
08/04/2021 | 19:50 | 24:00 | 4.17 | 11022 | 11022 | 0 | INT | 2: BHA 2 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_5_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/05/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4200 |  |  | Well Cost($): |  | 50880
|  |  |  | 24hr Summary: |  | Rack back tools, Standby
|  |  |  | 24hr Lookahead: |  | Standby for casing ops and rig skid
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11022 |  | 3523 |  | Csg Shoe MD(Usft): |  | 3513 |  | 600: | 43 | PV: | 16
End Depth (Usft): |  | 11022 |  | 11022 |  | OD (in): |  | 10.75 |  | 300: | 27 | YP: | 11
Total Drilled (Usft): |  |  |  | 7499 |  | Weight (ft/lbs): |  | 44.5 |  | 200: | 20 | Viscosity: | 47
Slide Drilled (Usft): |  |  |  | 655 | [5 empty] | 100: | 15 | Chlorides: | 69200
Rotary Drilled (Usft): |  |  |  | 6844 | [5 empty] | 6: | 7 | % Sand/Solids: | 0.40 / 9.20
Drlg/Circ Hrs: |  |  |  | 39.42 / 9.62 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 69/31
Slide Drilling Hrs: |  |  |  | 20.78 |  | SN: |  | 56410 |  | 10s Gel: | 6 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  |  |  | 18.63 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 367.30 / 31.52 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 2.75 |  | 60.75 |  | Grade In: |  | New
% Slide: |  |  |  | 8.73 |  | Grade Out: |  | 0-1-CT-S-X-I-WT-TD
% Rotary: |  |  |  | 91.27 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Jason Smetters |  | Peter Langille |  |  |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Xavier Cantu |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
SPL613 - TFA 1.49 |  |  |  | 9.875 | 2 |  |  | 125 |  | 1.5 |  | 1.5
7/8 5.9 2.00 Slick HPO -.014 |  |  |  | 8 | 2 |  |  | 100 |  | 37.56 |  | 39.06
NMPC |  |  |  | 8 | 3.25 |  |  | 162.87 |  | 9.21 |  | 48.27
UBHO Sub |  |  |  | 7.75 | 3 |  |  | 150 |  | 3.97 |  | 52.24
NMDC |  |  |  | 7.812 | 3.312 |  |  | 157.9 |  | 27.55 |  | 79.79
NMDC |  |  |  | 8 | 3.312 |  |  | 151.3 |  | 28.75 |  | 108.54
Crossover Sub |  |  |  | 6.75 | 2.875 |  |  | 100 |  | 2.55 |  | 111.09
6.5 DC 6 Jts |  |  |  | 6.5 | 2.375 |  |  | 95 |  | 187.23 |  | 298.32
HWDP 9 Jts |  |  |  | 5 | 3 |  |  | 43 |  | 274.85 |  | 573.17
Crossover Sub |  |  |  | 6.5 | 2.875 |  |  | 95 |  | 2.67 |  | 575.84
DP 22 Stds |  |  |  | 5 | 3.5 |  |  | 19.6 |  | 2061.7 |  | 2637.54
Agitator |  |  |  | 6.562 | 3.75 |  |  | 80 |  | 24.65 |  | 2662.19
2662.19
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800058 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.04 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 19.68 | 70.48 | 207 | 823.61 | 4787.48 | 4468.03 | 0 | 300.81 | 265.81 | 230.32 | 18457.09 | 0
Run | 190.25 | 25.44 | 78 | 219 | 847.58 | 4806.45 | 4087.22 | 0 | 224.45 | 198.56 | 190.07 | 14481.55 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
STBY |  |  |  |  | 08/05/2021 |  | 2 |  | 3800 |  | 1 | 3800
Perdiem |  |  |  |  | 08/05/2021 |  | 5 |  | 100 |  | 4 | 400
Total | [11 empty] | 4200
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/05/2021 | 00:00 | 01:30 | 1.5 | 11022 | 11022 | 0 | INT | 2: BHA 2 | 6B | POOH
08/05/2021 | 01:30 | 02:45 | 1.25 | 11022 | 11022 | 0 | INT | 2: BHA 2 | 6P | Swap motor & high side new UBHO insert, rack back BHA in derrick
08/05/2021 | 02:45 | 24:00 | 21.25 | 11022 | 11022 | 0 | INT |  | 24B | Stand by
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_19_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 16 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 6850 |  |  | Well Cost($): |  | 57730
|  |  |  | 24hr Summary: |  | TIH and Time Drill
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11022 |  | 11022 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 62 | PV: | 25
End Depth (Usft): |  | 11041 |  | 11041 |  | OD (in): |  | 7.625 |  | 300: | 37 | YP: | 12
Total Drilled (Usft): |  | 19 |  | 19 |  | Weight (ft/lbs): |  | 45 |  | 200: | 28 | Viscosity: | 72
Slide Drilled (Usft): |  | 19 |  | 19 | [5 empty] | 100: | 19 | Chlorides: | 70000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.40 / 11.60
Drlg/Circ Hrs: |  | 15.50 / 0.00 |  | 15.50 / 0.00 |  | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 71/29
Slide Drilling Hrs: |  | 15.5 |  | 15.5 |  | SN: |  | 13628581 |  | 10s Gel: | 8 | Weight (ppg): | 10.1
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 0.00 / 1.23 |  | 0.00 / 1.23 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 15.5 |  | 15.5 |  | Grade In: |  | New
% Slide: |  | 100 |  | 100 |  | Grade Out: |  | 1-1-NO-A-X-I-NO-BHA
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 3.03
6/7 8.8 2.25 TS HS88 .000 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Filter Sub |  |  |  | 5 | 2.688 |  |  | 35.35 |  | 4.95 |  | 116.2
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 119.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.05 |  | 2.25 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/19/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/19/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/19/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 6850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/19/2021 | 00:00 | 08:30 | 8.5 | 11022 | 11022 | 0 | CRV | 3: BHA 4 | 6O | TIH
08/19/2021 | 08:30 | 24:00 | 15.5 | 11022 | 11041 | 19 | CRV | 3: BHA 4 | 2J | Slide Drill f/11022.00 t/11041.00, TF 80.00G, w/WOB 5.00,Flow 275.00, Press 1900.00, Tq 0.00, ROP 1.23, Diff 100.00, Temp 217.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_20_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 17 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17650 |  |  | Well Cost($): |  | 75380
|  |  |  | 24hr Summary: |  | TimeDrill and Side Track
|  |  |  | 24hr Lookahead: |  | Continue Building curve with side track assembly. POOH and P/U Curve/ Lateral BHA
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11041 |  | 11265 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 62 | PV: | 25
End Depth (Usft): |  | 11265 |  | 11265 |  | OD (in): |  | 7.625 |  | 300: | 37 | YP: | 12
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45 |  | 200: | 28 | Viscosity: | 72
Slide Drilled (Usft): | [9 empty] | 100: | 19 | Chlorides: | 70000
Rotary Drilled (Usft): | [9 empty] | 6: | 7 | % Sand/Solids: | 0.40 / 11.60
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 6 | Oil/Water: | 71/29
Slide Drilling Hrs: | [5 empty] | SN: |  | 13628581 |  | 10s Gel: | 8 | Weight (ppg): | 10.1
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 4 |  | PH / Temp(F) | 0.0 / 170.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 7 |  | 7 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out: |  | 1-1-NO-A-X-I-NO-BHA
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Jesse Taylor |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 3.03
6/7 8.8 2.25 TS HS88 .000 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Filter Sub |  |  |  | 5 | 2.688 |  |  | 35.35 |  | 4.95 |  | 116.2
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 119.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.05 |  | 2.25 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11110 | 27.89 | 151.95 | 11002.89 | -481.94 | 1052.03 | 7.48 |  | 4.48 | 912.51 | 7.47 |  | 1.24 | 154
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 40.12 | 15.67 | 0 | 198 | 291.67 | 2400 | 2066.67 | 0 | 225 | 195 | 170 | 0 | 0
Run | 11.53 | 13 | 0 | 196 | 287.5 | 2275 | 2000 | 0 | 225 | 195 | 170 | 0 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/20/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/20/2021 |  | 5 |  | 100 |  | 4 | 400
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 08/20/2021 | PPM250012 | 15 |  | 1000 |  | 1 | 1000
5.5 Premium Motor Reline |  |  |  |  | 08/20/2021 | PPM250012 | 9 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 08/20/2021 |  | 11 |  | 800 |  | 1 | 800
Multi Rig Discount |  |  |  |  | 08/20/2021 |  | 20 |  | -400 |  | 1 | -400
Total | [11 empty] | 17650
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/20/2021 | 00:00 | 02:00 | 2 | 11041 | 11076 | 35 | CRV | 3: BHA 4 | 2J | Slide Drill f/11041.00 t/11076.00, TF 30G, w/WOB 7.00,Flow 275.00, Press 1900.00, Tq 0.00, ROP 17.50, Diff 100.00, Temp 217.00
08/20/2021 | 02:00 | 02:15 | 0.25 | 11076 | 11076 | 0 | CRV | 3: BHA 4 | 5A | Survey & Connection
08/20/2021 | 02:15 | 04:00 | 1.75 | 11076 | 11171 | 95 | CRV | 3: BHA 4 | 2J | Slide Drill f/11076.00 t/11171.00, TF 0G, w/WOB 20,Flow 300, Press 2650, Tq 0.00, ROP 54.29, Diff 450.00, Temp 219.00
08/20/2021 | 04:00 | 04:10 | 0.17 | 11171 | 11171 | 0 | CRV | 3: BHA 4 | 5A | Survey & Connection
08/20/2021 | 04:10 | 06:00 | 1.83 | 11171 | 11265 | 94 | CRV | 3: BHA 4 | 2J | Slide Drill f/11171.00 t/11265.00, TF 0.00G, w/WOB 20.00,Flow 300.00, Press 2650.00, Tq 0.00, ROP 51.27, Diff 450.00, Temp 219.00
08/20/2021 | 06:00 | 06:05 | 0.08 | 11265 | 11265 | 0 | CRV | 3: BHA 4 | 5A | Survey & Connection
08/20/2021 | 06:05 | 08:00 | 1.92 | 11265 | 11265 | 0 | CRV | 3: BHA 4 | 5A | Circulate
08/20/2021 | 08:00 | 15:00 | 7 | 11265 | 11265 | 0 | CRV | 3: BHA 4 | 6B | POOH
08/20/2021 | 15:00 | 16:00 | 1 | 11265 | 11265 | 0 | CRV | 3: BHA 4 | 6P | L/D BHA
08/20/2021 | 16:00 | 17:00 | 1 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 6O | P/U BHA
08/20/2021 | 17:00 | 22:25 | 5.42 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 6A | TIH
08/20/2021 | 22:25 | 24:00 | 1.58 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 9A | Slip and Cut
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_21_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 18 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/21/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7450 |  |  | Well Cost($): |  | 82830
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 11265 |  | 11265 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 49 | PV: | 19
End Depth (Usft): |  | 13386 |  | 13386 |  | OD (in): |  | 7.625 |  | 300: | 30 | YP: | 11
Total Drilled (Usft): |  | 2121 |  | 2121 |  | Weight (ft/lbs): |  | 45 |  | 200: | 22 | Viscosity: | 61
Slide Drilled (Usft): |  | 526 |  | 526 | [5 empty] | 100: | 14 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 1595 |  | 1595 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.60
Drlg/Circ Hrs: |  | 19.68 / 3.48 |  | 19.68 / 3.48 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73/27
Slide Drilling Hrs: |  | 7.7 |  | 7.7 |  | SN: |  | 13628581 |  | 10s Gel: | 8 | Weight (ppg): | 9.8
Rotary Drilling Hrs: |  | 11.98 |  | 11.98 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 124.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 133.10 / 68.31 |  | 133.10 / 68.31 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 31 |  | Grade In: |  | New
% Slide: |  | 24.8 |  | 24.8 |  | Grade Out:
% Rotary: |  | 75.2 |  | 75.2 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .004 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 34.07
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 129.27
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 132.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 320.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 328.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2783.16
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 21.42 |  | 2804.58
2804.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
11205 | 42.79 | 149.26 | 11080.17 | -529.55 | 1079.13 | 15.77 |  | -7.09 | 967.26 | 15.68 |  | -2.83 | 95
11248 | 50.44 | 150.22 | 11109.68 | -556.53 | 1094.85 | 17.86 |  | 5.55 | 998.45 | 17.79 |  | 2.23 | 43
11342 | 54.61 | 151.34 | 11166.86 | -621.63 | 1131.24 | 4.54 |  | 12.38 | 1072.99 | 4.44 |  | 1.19 | 94
11437 | 65.54 | 154.65 | 11214.19 | -694.92 | 1168.44 | 11.89 |  | 15.56 | 1155.18 | 11.51 |  | 3.48 | 95
11531 | 69.07 | 154.8 | 11250.46 | -773.33 | 1205.46 | 3.76 |  | 2.27 | 1241.83 | 3.76 |  | 0.16 | 94
11626 | 70.2 | 155.18 | 11283.52 | -854.04 | 1243.11 | 1.25 |  | 17.56 | 1330.81 | 1.19 |  | 0.4 | 95
11721 | 79.14 | 154.15 | 11308.61 | -936.76 | 1282.3 | 9.47 |  | -6.48 | 1422.27 | 9.41 |  | -1.08 | 95
11815 | 94.01 | 154.96 | 11314.21 | -1021.25 | 1322.49 | 15.84 |  | 3.15 | 1515.78 | 15.82 |  | 0.86 | 94
11910 | 92.3 | 154.01 | 11308.98 | -1106.85 | 1363.35 | 2.06 |  | -150.95 | 1610.58 | -1.8 |  | -1 | 95
12005 | 90.05 | 153.42 | 11307.03 | -1192 | 1405.41 | 2.45 |  | -165.3 | 1705.54 | -2.37 |  | -0.62 | 95
12100 | 86.86 | 153.31 | 11309.59 | -1276.88 | 1447.98 | 3.36 |  | -178.03 | 1800.48 | -3.36 |  | -0.12 | 95
12194 | 80.74 | 151.24 | 11319.74 | -1359.56 | 1491.42 | 6.87 |  | -161.52 | 1893.88 | -6.51 |  | -2.2 | 94
12289 | 82.38 | 151.68 | 11333.68 | -1442.11 | 1536.31 | 1.79 |  | 14.9 | 1987.83 | 1.73 |  | 0.46 | 95
12384 | 84.7 | 152.1 | 11344.37 | -1525.37 | 1580.79 | 2.48 |  | 10.22 | 2082.21 | 2.44 |  | 0.44 | 95
12475 | 84.93 | 151.82 | 11352.59 | -1605.36 | 1623.39 | 0.4 |  | -50.5 | 2172.84 | 0.25 |  | -0.31 | 91
12570 | 86.6 | 151.72 | 11359.61 | -1688.83 | 1668.2 | 1.76 |  | -3.42 | 2267.56 | 1.76 |  | -0.11 | 95
12665 | 86.46 | 150.72 | 11365.36 | -1771.94 | 1713.85 | 1.06 |  | -98.01 | 2362.36 | -0.15 |  | -1.05 | 95
12757 | 86.46 | 148.95 | 11371.04 | -1851.33 | 1759.99 | 1.92 |  | -90.05 | 2454.08 | 0 |  | -1.92 | 92
12852 | 86.6 | 147.38 | 11376.79 | -1931.88 | 1810.01 | 1.66 |  | -84.94 | 2548.62 | 0.15 |  | -1.65 | 95
12946 | 86.77 | 147.58 | 11382.23 | -2011.01 | 1860.46 | 0.28 |  | 49.59 | 2642.1 | 0.18 |  | 0.21 | 94
13041 | 86.79 | 149.08 | 11387.56 | -2091.74 | 1910.26 | 1.58 |  | 89.28 | 2736.69 | 0.02 |  | 1.58 | 95
13135 | 88.52 | 151.77 | 11391.41 | -2173.41 | 1956.61 | 3.4 |  | 57.29 | 2830.53 | 1.84 |  | 2.86 | 94
13230 | 87.97 | 153.32 | 11394.32 | -2257.67 | 2000.38 | 1.73 |  | 109.57 | 2925.48 | -0.58 |  | 1.63 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 107.76 | 22.61 | 63.5 | 336 | 400 | 4726.37 | 4065.88 | 0 | 246.67 | 205 | 186.67 | 6850 | 0
Run | 107.76 | 22.61 | 63.5 | 336 | 400 | 4726.37 | 4065.88 | 0 | 246.67 | 205 | 186.67 | 6850 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 08/21/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/21/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 08/21/2021 |  | 4 |  | 6850 |  | 1 | 6850
Real Time Survey Management |  |  |  |  | 08/21/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 7450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/21/2021 | 00:00 | 00:15 | 0.25 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 9A | Slip & Cut DL
08/21/2021 | 00:15 | 00:35 | 0.33 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 24A | Line up pumps and choke
08/21/2021 | 00:35 | 00:45 | 0.17 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 5A | Fill Pipe
08/21/2021 | 00:45 | 01:00 | 0.25 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 5A | Orient to HS
08/21/2021 | 01:00 | 01:15 | 0.25 | 11265 | 11265 | 0 | CRV2 | 4: BHA 5 | 6A | TIH
08/21/2021 | 01:15 | 01:50 | 0.58 | 11265 | 11295 | 30 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11265.00 t/11295.00, w/WOB 22,Flow 400, RPM 35, Press 4550, Tq 6000, ROP 51.43, Diff 530.00, Temp 243.00
08/21/2021 | 01:50 | 02:15 | 0.42 | 11295 | 11309 | 14 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11295.00 t/11309.00, TF 0G, w/WOB 22,Flow 400, Press 4550, Tq 6000, ROP 33.60, Diff 530.00, Temp 243.00
08/21/2021 | 02:15 | 02:22 | 0.12 | 11309 | 11309 | 0 | CRV2 | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 02:22 | 02:40 | 0.3 | 11309 | 11324 | 15 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11309.00 t/11324.00, w/WOB 22,Flow 400, RPM 35, Press 4550, Tq 6000, ROP 50.00, Diff 530.00, Temp 243.00
08/21/2021 | 02:40 | 03:50 | 1.17 | 11324 | 11403 | 79 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11324.00 t/11403.00, TF 20G, w/WOB 22,Flow 400, Press 4550, Tq 6000, ROP 67.71, Diff 530.00, Temp 243.00
08/21/2021 | 03:50 | 03:58 | 0.13 | 11403 | 11403 | 0 | CRV2 | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 03:58 | 04:23 | 0.42 | 11403 | 11423 | 20 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11403.00 t/11423.00, w/WOB 22,Flow 400, RPM 35, Press 4550, Tq 6000, ROP 48.00, Diff 530.00, Temp 243.00
08/21/2021 | 04:23 | 04:57 | 0.57 | 11423 | 11473 | 50 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11423.00 t/11473.00, TF 10.00G, w/WOB 22.00,Flow 400.00, Press 4575, Tq 3100, ROP 88.24, Diff 555.00, Temp 243.00
08/21/2021 | 04:57 | 05:18 | 0.35 | 11473 | 11498 | 25 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11473.00 t/11498.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 71.43, Diff 630.00, Temp 244.40
08/21/2021 | 05:18 | 05:27 | 0.15 | 11498 | 11498 | 0 | CRV2 | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 05:27 | 06:00 | 0.55 | 11498 | 11560 | 62 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11498.00 t/11560.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 112.73, Diff 630.00, Temp 244.40
08/21/2021 | 06:00 | 06:28 | 0.47 | 11560 | 11592 | 32 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11560.00 t/11592.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 68.57, Diff 630.00, Temp 244.40
08/21/2021 | 06:28 | 06:38 | 0.17 | 11592 | 11592 | 0 | CRV2 | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 06:38 | 07:01 | 0.38 | 11592 | 11644 | 52 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11592.00 t/11644.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 135.65, Diff 630.00, Temp 244.40
08/21/2021 | 07:01 | 07:30 | 0.48 | 11644 | 11687 | 43 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11644.00 t/11687.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 88.97, Diff 630.00, Temp 244.40
08/21/2021 | 07:30 | 07:35 | 0.08 | 11687 | 11687 | 0 | CRV2 | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 07:35 | 07:40 | 0.08 | 11687 | 11692 | 5 | CRV2 | 4: BHA 5 | 2K | Rotary Drill f/11687.00 t/11692.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 60.00, Diff 630.00, Temp 244.40
08/21/2021 | 07:40 | 08:40 | 1 | 11692 | 11782 | 90 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11692.00 t/11782.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 90.00, Diff 630.00, Temp 244.40
08/21/2021 | 08:40 | 08:50 | 0.17 | 11782 | 11782 | 0 | CRV2 | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 08:50 | 09:10 | 0.33 | 11782 | 11804 | 22 | CRV2 | 4: BHA 5 | 2J | Slide Drill f/11782.00 t/11804.00, TF 0.00G, w/WOB 22.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 66.00, Diff 630.00, Temp 244.40
08/21/2021 | 09:10 | 09:40 | 0.5 | 11804 | 11876 | 72 | LAT | 4: BHA 5 | 2K | Rotary Drill f/11804.00 t/11876.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 144.00, Diff 630.00, Temp 253.00
08/21/2021 | 09:40 | 09:45 | 0.08 | 11876 | 11876 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 09:45 | 10:05 | 0.33 | 11876 | 11891 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/11876.00 t/11891.00, TF 210.00G, w/WOB 22.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 45.00, Diff 630.00, Temp 253.00
08/21/2021 | 10:05 | 10:30 | 0.42 | 11891 | 11971 | 80 | LAT | 4: BHA 5 | 2K | Rotary Drill f/11891.00 t/11971.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 6500.00, ROP 192.00, Diff 780.00, Temp 253.00
08/21/2021 | 10:30 | 10:35 | 0.08 | 11971 | 11971 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 10:35 | 10:50 | 0.25 | 11971 | 11991 | 20 | LAT | 4: BHA 5 | 2J | Slide Drill f/11971.00 t/11991.00, TF 210.00G, w/WOB 22.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 80.00, Diff 630.00, Temp 253.00
08/21/2021 | 10:50 | 11:15 | 0.42 | 11991 | 12066 | 75 | LAT | 4: BHA 5 | 2K | Rotary Drill f/11991.00 t/12066.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 180.00, Diff 630.00, Temp 253.00
08/21/2021 | 11:15 | 11:20 | 0.08 | 12066 | 12066 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 11:20 | 11:45 | 0.42 | 12066 | 12091 | 25 | LAT | 4: BHA 5 | 2J | Slide Drill f/12066.00 t/12091.00, TF 180.00G, w/WOB 25.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 60.00, Diff 630.00, Temp 253.00
08/21/2021 | 11:45 | 11:55 | 0.17 | 12091 | 12122 | 31 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12091.00 t/12122.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 186.00, Diff 630.00, Temp 253.00
08/21/2021 | 11:55 | 12:05 | 0.17 | 12122 | 12122 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 12:05 | 12:20 | 0.25 | 12122 | 12142 | 20 | LAT | 4: BHA 5 | 2J | Slide Drill f/12122.00 t/12142.00, TF 180.00G, w/WOB 25.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 80.00, Diff 630.00, Temp 253.00
08/21/2021 | 12:20 | 12:30 | 0.17 | 12142 | 12161 | 19 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12142.00 t/12161.00, w/WOB 22.00,Flow 400.00, RPM 35.00, Press 4650.00, Tq 6500.00, ROP 114.00, Diff 630.00, Temp 253.00
08/21/2021 | 12:30 | 13:05 | 0.58 | 12161 | 12161 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 13:05 | 13:20 | 0.25 | 12161 | 12171 | 10 | LAT | 4: BHA 5 | 2J | Slide Drill f/12161.00 t/12171.00, TF 180.00G, w/WOB 25.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 40.00, Diff 630.00, Temp 253.00
08/21/2021 | 13:20 | 13:45 | 0.42 | 12171 | 12255 | 84 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12171.00 t/12255.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 6500.00, ROP 201.60, Diff 630.00, Temp 253.00
08/21/2021 | 13:45 | 13:50 | 0.08 | 12255 | 12255 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 13:50 | 14:10 | 0.33 | 12255 | 12270 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/12255.00 t/12270.00, TF 0.00G, w/WOB 30.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 45.00, Diff 630.00, Temp 253.00
08/21/2021 | 14:10 | 14:35 | 0.42 | 12270 | 12350 | 80 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12270.00 t/12350.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 6500.00, ROP 192.00, Diff 630.00, Temp 259.00
08/21/2021 | 14:35 | 14:40 | 0.08 | 12350 | 12350 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 14:40 | 14:55 | 0.25 | 12350 | 12362 | 12 | LAT | 4: BHA 5 | 2J | Slide Drill f/12350.00 t/12362.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 48.00, Diff 630.00, Temp 259.00
08/21/2021 | 14:55 | 15:25 | 0.5 | 12362 | 12445 | 83 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12362.00 t/12445.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 6500.00, ROP 166.00, Diff 630.00, Temp 259.00
08/21/2021 | 15:25 | 15:30 | 0.08 | 12445 | 12445 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 15:30 | 16:05 | 0.58 | 12445 | 12536 | 91 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12445.00 t/12536.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 6500.00, ROP 156.00, Diff 630.00, Temp 259.00
08/21/2021 | 16:05 | 16:10 | 0.08 | 12536 | 12536 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 16:10 | 16:20 | 0.17 | 12536 | 12546 | 10 | LAT | 4: BHA 5 | 2J | Slide Drill f/12536.00 t/12546.00, TF 0.00G, w/WOB 25.00,Flow 400.00, Press 4650.00, Tq 6500.00, ROP 60.00, Diff 630.00, Temp 259.00
08/21/2021 | 16:20 | 16:55 | 0.58 | 12546 | 12631 | 85 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12546.00 t/12631.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 6500.00, ROP 145.71, Diff 630.00, Temp 264.00
08/21/2021 | 16:55 | 17:00 | 0.08 | 12631 | 12631 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 17:00 | 17:30 | 0.5 | 12631 | 12726 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12631.00 t/12726.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 6500.00, ROP 190.00, Diff 630.00, Temp 268.00
08/21/2021 | 17:30 | 17:50 | 0.33 | 12726 | 12726 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 17:50 | 18:24 | 0.57 | 12726 | 12818 | 92 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12726.00 t/12818.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 8500.00, ROP 162.35, Diff 840.00, Temp 264.00
08/21/2021 | 18:24 | 18:27 | 0.05 | 12818 | 12818 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 18:27 | 19:11 | 0.73 | 12818 | 12913 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12818.00 t/12913.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 6500.00, ROP 129.55, Diff 840.00, Temp 264.00
08/21/2021 | 19:11 | 19:13 | 0.03 | 12913 | 12913 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 19:13 | 19:22 | 0.15 | 12913 | 12928 | 15 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12913.00 t/12928.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 6500.00, ROP 100.00, Diff 840.00, Temp 264.00
08/21/2021 | 19:22 | 19:34 | 0.2 | 12928 | 12940 | 12 | LAT | 4: BHA 5 | 2J | Slide Drill f/12928.00 t/12940.00, TF 80.00G, w/WOB 22.00,Flow 400.00, Press 4990.00, Tq 4500.00, ROP 60.00, Diff 840.00, Temp 268.00
08/21/2021 | 19:34 | 20:03 | 0.48 | 12940 | 13007 | 67 | LAT | 4: BHA 5 | 2K | Rotary Drill f/12940.00 t/13007.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 6500.00, ROP 138.62, Diff 840.00, Temp 268.00
08/21/2021 | 20:03 | 20:07 | 0.07 | 13007 | 13007 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 20:07 | 20:12 | 0.08 | 13007 | 13021 | 14 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13007.00 t/13021.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 6500.00, ROP 168.00, Diff 840.00, Temp 268.00
08/21/2021 | 20:12 | 20:26 | 0.23 | 13021 | 13036 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/13021.00 t/13036.00, TF 70.00G, w/WOB 22.00,Flow 400.00, Press 4650, Tq 4000, ROP 64.29, Diff 500.00, Temp 271.00
08/21/2021 | 20:26 | 20:57 | 0.52 | 13036 | 13102 | 66 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13036.00 t/13102.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 6500.00, ROP 127.74, Diff 840.00, Temp 272.00
08/21/2021 | 20:57 | 21:00 | 0.05 | 13102 | 13102 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 21:00 | 21:03 | 0.05 | 13102 | 13105 | 3 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13102.00 t/13105.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 4990.00, Tq 6500.00, ROP 60.00, Diff 840.00, Temp 272.00
08/21/2021 | 21:03 | 21:18 | 0.25 | 13105 | 13123 | 18 | LAT | 4: BHA 5 | 2J | Slide Drill f/13105.00 t/13123.00, TF 70G, w/WOB 22.00,Flow 400.00, Press 4650, Tq 4500, ROP 72.00, Diff 500.00, Temp 277.00
08/21/2021 | 21:18 | 21:40 | 0.37 | 13123 | 13174 | 51 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13123.00 t/13174.00, w/WOB 22.00,Flow 400.00, RPM 80, Press 4990.00, Tq 8500, ROP 139.09, Diff 840.00, Temp 277.00
08/21/2021 | 21:40 | 21:49 | 0.15 | 13174 | 13174 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 21:49 | 22:00 | 0.18 | 13174 | 13186 | 12 | LAT | 4: BHA 5 | 2J | Slide Drill f/13174.00 t/13186.00, TF 120G, w/WOB 22.00,Flow 400.00, Press 4650, Tq 4500, ROP 65.45, Diff 500.00, Temp 277.00
08/21/2021 | 22:00 | 22:15 | 0.25 | 13186 | 13196 | 10 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13186.00 t/13196.00, w/WOB 22.00,Flow 400.00, RPM 80, Press 4990.00, Tq 8500, ROP 40.00, Diff 840.00, Temp 277.00
08/21/2021 | 22:15 | 22:18 | 0.05 | 13196 | 13196 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 22:18 | 22:53 | 0.58 | 13196 | 13268 | 72 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13196.00 t/13268.00, w/WOB 22.00,Flow 400.00, RPM 80, Press 4990.00, Tq 8500, ROP 123.43, Diff 840.00, Temp 277.00
08/21/2021 | 22:53 | 23:02 | 0.15 | 13268 | 13280 | 12 | LAT | 4: BHA 5 | 2J | Slide Drill f/13268.00 t/13280.00, TF 160G, w/WOB 22.00,Flow 400.00, Press 4650, Tq 4500, ROP 80.00, Diff 500.00, Temp 277.00
08/21/2021 | 23:02 | 23:12 | 0.17 | 13280 | 13291 | 11 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13280.00 t/13291.00, w/WOB 22.00,Flow 400.00, RPM 80, Press 4990.00, Tq 8500, ROP 66.00, Diff 840.00, Temp 277.00
08/21/2021 | 23:12 | 23:15 | 0.05 | 13291 | 13291 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/21/2021 | 23:15 | 23:57 | 0.7 | 13291 | 13386 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13291.00 t/13386.00, w/WOB 22.00,Flow 400.00, RPM 80, Press 4990.00, Tq 8500, ROP 135.71, Diff 840.00, Temp 277.00
08/21/2021 | 23:57 | 24:00 | 0.05 | 13386 | 13386 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_22_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 19 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/22/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7450 |  |  | Well Cost($): |  | 90280
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13386 |  | 11265 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 49 | PV: | 19
End Depth (Usft): |  | 15960 |  | 15960 |  | OD (in): |  | 7.625 |  | 300: | 30 | YP: | 11
Total Drilled (Usft): |  | 2574 |  | 4695 |  | Weight (ft/lbs): |  | 45 |  | 200: | 22 | Viscosity: | 61
Slide Drilled (Usft): |  | 164 |  | 690 | [5 empty] | 100: | 14 | Chlorides: | 58000
Rotary Drilled (Usft): |  | 2410 |  | 4005 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.60
Drlg/Circ Hrs: |  | 20.72 / 1.85 |  | 40.40 / 5.33 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73/27
Slide Drilling Hrs: |  | 3.35 |  | 11.05 |  | SN: |  | 13628581 |  | 10s Gel: | 7 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 17.37 |  | 29.35 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 124.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 138.77 / 48.96 |  | 136.46 / 62.44 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 55 |  | Grade In: |  | New
% Slide: |  | 6.37 |  | 14.7 |  | Grade Out:
% Rotary: |  | 93.63 |  | 85.3 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .004 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 34.07
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 129.27
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 132.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 320.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 328.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2783.16
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 21.42 |  | 2804.58
2804.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13325 | 87.38 | 153.96 | 11398.17 | -2342.72 | 2042.53 | 0.92 |  | 132.71 | 3020.39 | -0.62 |  | 0.67 | 95
13419 | 86.57 | 154.88 | 11403.13 | -2427.39 | 2083.06 | 1.3 |  | 131.42 | 3114.2 | -0.86 |  | 0.98 | 94
13514 | 83.15 | 151.6 | 11411.65 | -2511.85 | 2125.64 | 4.98 |  | -136.45 | 3208.79 | -3.6 |  | -3.45 | 95
13609 | 83.66 | 152.27 | 11422.56 | -2595.12 | 2170.04 | 0.88 |  | 52.58 | 3303.15 | 0.54 |  | 0.71 | 95
13703 | 83.86 | 152.04 | 11432.77 | -2677.75 | 2213.69 | 0.32 |  | -48.83 | 3396.59 | 0.21 |  | -0.24 | 94
13798 | 85.81 | 152.81 | 11441.33 | -2761.61 | 2257.48 | 2.21 |  | 21.5 | 3491.2 | 2.05 |  | 0.81 | 95
13891 | 86.91 | 152.5 | 11447.23 | -2844.05 | 2300.11 | 1.23 |  | -15.72 | 3584.01 | 1.18 |  | -0.33 | 93
13985 | 85.91 | 153.17 | 11453.12 | -2927.51 | 2342.94 | 1.28 |  | 146.25 | 3677.83 | -1.06 |  | 0.71 | 94
14079 | 86.25 | 153.3 | 11459.54 | -3011.25 | 2385.18 | 0.39 |  | 20.88 | 3771.6 | 0.36 |  | 0.14 | 94
14173 | 87.6 | 153.56 | 11464.58 | -3095.2 | 2427.16 | 1.46 |  | 10.89 | 3865.45 | 1.44 |  | 0.28 | 94
14268 | 85.61 | 153.75 | 11470.21 | -3180.18 | 2469.24 | 2.1 |  | 174.56 | 3960.26 | -2.09 |  | 0.2 | 95
14363 | 85.62 | 153.8 | 11477.47 | -3265.15 | 2511.1 | 0.05 |  | 0 | 4054.96 | 0.01 |  | 0.05 | 95
14458 | 85.39 | 153.92 | 11484.92 | -3350.17 | 2552.83 | 0.27 |  | 152.52 | 4149.65 | -0.24 |  | 0.13 | 95
14552 | 85.51 | 153.61 | 11492.38 | -3434.22 | 2594.25 | 0.35 |  | -68.79 | 4243.33 | 0.13 |  | -0.33 | 94
14647 | 85.7 | 153.6 | 11499.66 | -3519.07 | 2636.36 | 0.2 |  | -3 | 4338.03 | 0.2 |  | -0.01 | 95
14742 | 88.01 | 154.35 | 11504.87 | -3604.3 | 2677.97 | 2.56 |  | 17.98 | 4432.85 | 2.43 |  | 0.79 | 95
14834 | 85.89 | 153.98 | 11509.76 | -3686.98 | 2718 | 2.34 |  | -170.12 | 4524.68 | -2.3 |  | -0.4 | 92
14928 | 86.05 | 154.14 | 11516.37 | -3771.3 | 2759.02 | 0.24 |  | 44.93 | 4618.42 | 0.17 |  | 0.17 | 94
15023 | 84.8 | 153.39 | 11523.95 | -3856.24 | 2800.88 | 1.53 |  | -149.15 | 4713.09 | -1.32 |  | -0.79 | 95
15117 | 85.2 | 153.11 | 11532.14 | -3939.86 | 2843.03 | 0.52 |  | -34.9 | 4806.73 | 0.43 |  | -0.3 | 94
15213 | 86.97 | 154.37 | 11538.69 | -4025.75 | 2885.4 | 2.26 |  | 35.43 | 4902.48 | 1.84 |  | 1.31 | 96
15307 | 88.26 | 154.1 | 11542.61 | -4110.33 | 2926.23 | 1.4 |  | -11.82 | 4996.35 | 1.37 |  | -0.29 | 94
15402 | 87.35 | 153.43 | 11546.24 | -4195.48 | 2968.19 | 1.19 |  | -143.67 | 5091.26 | -0.96 |  | -0.71 | 95
15497 | 85.58 | 152.26 | 11552.1 | -4279.84 | 3011.46 | 2.23 |  | -146.62 | 5186.07 | -1.86 |  | -1.23 | 95
15591 | 85.67 | 151.95 | 11559.27 | -4362.68 | 3055.31 | 0.34 |  | -73.78 | 5279.8 | 0.1 |  | -0.33 | 94
15686 | 86.15 | 152.06 | 11566.05 | -4446.35 | 3099.79 | 0.52 |  | 12.88 | 5374.55 | 0.51 |  | 0.12 | 95
15780 | 87.08 | 152.45 | 11571.6 | -4529.39 | 3143.47 | 1.07 |  | 22.73 | 5468.38 | 0.99 |  | 0.41 | 94
15874 | 87.79 | 152.52 | 11575.8 | -4612.68 | 3186.86 | 0.76 |  | 5.63 | 5562.29 | 0.76 |  | 0.07 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 124.25 | 32.62 | 80 | 352 | 400 | 5293.11 | 4521.11 | 0 | 278.67 | 185.44 | 165.11 | 9647.06 | 0
Run | 116.21 | 27.27 | 72.27 | 344 | 400 | 4995.63 | 4280.63 | 0 | 261.68 | 195.84 | 176.63 | 8335.94 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/22/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/22/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/22/2021 |  | 20 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 08/22/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 7450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/22/2021 | 00:00 | 00:18 | 0.3 | 13386 | 13401 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/13386.00 t/13401.00, TF 180.00G, w/WOB 30.00,Flow 400.00, Press 4650.00, Tq 4500.00, ROP 50.00, Diff 500.00, Temp 277.00
08/22/2021 | 00:18 | 00:52 | 0.57 | 13401 | 13480 | 79 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13401.00 t/13480.00, w/WOB 22.00,Flow 400.00, RPM 80.00, Press 5020.00, Tq 8500.00, ROP 139.41, Diff 870.00, Temp 277.00
08/22/2021 | 00:52 | 00:56 | 0.07 | 13480 | 13480 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 00:56 | 01:00 | 0.07 | 13480 | 13485 | 5 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13480.00 t/13485.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5020.00, Tq 8500.00, ROP 75.00, Diff 870.00, Temp 277.00
08/22/2021 | 01:00 | 01:17 | 0.28 | 13485 | 13503 | 18 | LAT | 4: BHA 5 | 2J | Slide Drill f/13485.00 t/13503.00, TF 180.00G, w/WOB 32.00,Flow 400.00, Press 4650.00, Tq 4500.00, ROP 63.53, Diff 500.00, Temp 277.00
08/22/2021 | 01:17 | 01:44 | 0.45 | 13503 | 13575 | 72 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13503.00 t/13575.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5100.00, Tq 8500.00, ROP 160.00, Diff 850.00, Temp 279.00
08/22/2021 | 01:44 | 01:47 | 0.05 | 13575 | 13575 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 01:47 | 01:58 | 0.18 | 13575 | 13601 | 26 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13575.00 t/13601.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5100.00, Tq 8500.00, ROP 141.82, Diff 850.00, Temp 279.00
08/22/2021 | 01:58 | 02:08 | 0.17 | 13601 | 13609 | 8 | LAT | 4: BHA 5 | 2J | Slide Drill f/13601.00 t/13609.00, TF 0.00G, w/WOB 32.00,Flow 400.00, Press 5050.00, Tq 4500.00, ROP 48.00, Diff 800.00, Temp 279.00
08/22/2021 | 02:08 | 02:28 | 0.33 | 13609 | 13670 | 61 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13609.00 t/13670.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5050.00, Tq 8500.00, ROP 183.00, Diff 800.00, Temp 279.00
08/22/2021 | 02:28 | 02:31 | 0.05 | 13670 | 13670 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 02:31 | 03:19 | 0.8 | 13670 | 13764 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13670.00 t/13764.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5050.00, Tq 8500.00, ROP 117.50, Diff 800.00, Temp 279.00
08/22/2021 | 03:19 | 03:22 | 0.05 | 13764 | 13764 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 03:22 | 03:27 | 0.08 | 13764 | 13778 | 14 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13764.00 t/13778.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5050.00, Tq 8500.00, ROP 168.00, Diff 800.00, Temp 279.00
08/22/2021 | 03:27 | 03:46 | 0.32 | 13778 | 13794 | 16 | LAT | 4: BHA 5 | 2J | Slide Drill f/13778.00 t/13794.00, TF 30.00G, w/WOB 32.00,Flow 400.00, Press 5050.00, Tq 4500.00, ROP 50.53, Diff 700.00, Temp 279.00
08/22/2021 | 03:46 | 04:08 | 0.37 | 13794 | 13859 | 65 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13794.00 t/13859.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 177.27, Diff 900.00, Temp 279.00
08/22/2021 | 04:08 | 05:18 | 1.17 | 13859 | 13859 | 0 | LAT | 4: BHA 5 | 8P | Rig Service
08/22/2021 | 05:18 | 06:00 | 0.7 | 13859 | 13952 | 93 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13859.00 t/13952.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 132.86, Diff 900.00, Temp 279.00
08/22/2021 | 06:00 | 06:05 | 0.08 | 13952 | 13952 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 06:05 | 06:30 | 0.42 | 13952 | 13967 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/13952.00 t/13967.00, TF 130.00G, w/WOB 40.00,Flow 400.00, Press 5250.00, Tq 8500.00, ROP 36.00, Diff 900.00, Temp 279.00
08/22/2021 | 06:30 | 07:00 | 0.5 | 13967 | 14046 | 79 | LAT | 4: BHA 5 | 2K | Rotary Drill f/13967.00 t/14046.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 158.00, Diff 900.00, Temp 279.00
08/22/2021 | 07:00 | 07:05 | 0.08 | 14046 | 14046 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 07:05 | 07:45 | 0.67 | 14046 | 14140 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14046.00 t/14140.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 141.00, Diff 900.00, Temp 279.00
08/22/2021 | 07:45 | 07:50 | 0.08 | 14140 | 14140 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 07:50 | 08:25 | 0.58 | 14140 | 14234 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14140.00 t/14234.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 161.14, Diff 900.00, Temp 279.00
08/22/2021 | 08:25 | 08:30 | 0.08 | 14234 | 14234 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 08:30 | 08:50 | 0.33 | 14234 | 14249 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/14234.00 t/14249.00, TF 150.00G, w/WOB 40.00,Flow 400.00, Press 5250.00, Tq 8500.00, ROP 45.00, Diff 900.00, Temp 279.00
08/22/2021 | 08:50 | 09:25 | 0.58 | 14249 | 14329 | 80 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14249.00 t/14329.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 137.14, Diff 900.00, Temp 279.00
08/22/2021 | 09:25 | 09:30 | 0.08 | 14329 | 14329 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 09:30 | 10:05 | 0.58 | 14329 | 14424 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14329.00 t/14424.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 162.86, Diff 900.00, Temp 288.00
08/22/2021 | 10:05 | 10:10 | 0.08 | 14424 | 14424 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 10:10 | 10:45 | 0.58 | 14424 | 14519 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14424.00 t/14519.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 162.86, Diff 900.00, Temp 288.00
08/22/2021 | 10:45 | 10:50 | 0.08 | 14519 | 14519 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 10:50 | 11:20 | 0.5 | 14519 | 14613 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14519.00 t/14613.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5250.00, Tq 8500.00, ROP 188.00, Diff 900.00, Temp 291.00
08/22/2021 | 11:20 | 11:25 | 0.08 | 14613 | 14613 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 11:25 | 12:00 | 0.58 | 14613 | 14708 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14613.00 t/14708.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 10000.00, ROP 162.86, Diff 850.00, Temp 293.00
08/22/2021 | 12:00 | 12:05 | 0.08 | 14708 | 14708 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 12:05 | 12:45 | 0.67 | 14708 | 14803 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14708.00 t/14803.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 10000.00, ROP 142.50, Diff 850.00, Temp 293.00
08/22/2021 | 12:45 | 12:50 | 0.08 | 14803 | 14803 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 12:50 | 13:15 | 0.42 | 14803 | 14823 | 20 | LAT | 4: BHA 5 | 2J | Slide Drill f/14803.00 t/14823.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 5300.00, Tq 10000.00, ROP 48.00, Diff 850.00, Temp 293.00
08/22/2021 | 13:15 | 13:50 | 0.58 | 14823 | 14895 | 72 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14823.00 t/14895.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 10000.00, ROP 123.43, Diff 850.00, Temp 293.00
08/22/2021 | 13:50 | 13:55 | 0.08 | 14895 | 14895 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 13:55 | 14:30 | 0.58 | 14895 | 14989 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14895.00 t/14989.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 10000.00, ROP 161.14, Diff 850.00, Temp 293.00
08/22/2021 | 14:30 | 14:35 | 0.08 | 14989 | 14989 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 14:35 | 14:45 | 0.17 | 14989 | 14999 | 10 | LAT | 4: BHA 5 | 2J | Slide Drill f/14989.00 t/14999.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 5300.00, Tq 10000.00, ROP 60.00, Diff 850.00, Temp 293.00
08/22/2021 | 14:45 | 15:25 | 0.67 | 14999 | 15084 | 85 | LAT | 4: BHA 5 | 2K | Rotary Drill f/14999.00 t/15084.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 10000.00, ROP 127.50, Diff 700.00, Temp 293.00
08/22/2021 | 15:25 | 15:30 | 0.08 | 15084 | 15084 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 15:30 | 16:15 | 0.75 | 15084 | 15178 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15084.00 t/15178.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 10000.00, ROP 125.33, Diff 700.00, Temp 297.00
08/22/2021 | 16:15 | 16:20 | 0.08 | 15178 | 15178 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 16:20 | 17:00 | 0.67 | 15178 | 15274 | 96 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15178.00 t/15274.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 144.00, Diff 700.00, Temp 298.00
08/22/2021 | 17:00 | 17:05 | 0.08 | 15274 | 15274 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 17:05 | 17:50 | 0.75 | 15274 | 15368 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15274.00 t/15368.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 125.33, Diff 700.00, Temp 298.00
08/22/2021 | 17:50 | 17:55 | 0.08 | 15368 | 15368 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 17:55 | 18:02 | 0.12 | 15368 | 15382 | 14 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15368.00 t/15382.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 120.00, Diff 700.00, Temp 298.00
08/22/2021 | 18:02 | 18:28 | 0.43 | 15382 | 15400 | 18 | LAT | 4: BHA 5 | 2J | Slide Drill f/15382.00 t/15400.00, TF 180G, w/WOB 32.00,Flow 400.00, Press 5550, Tq 11000.00, ROP 41.54, Diff 700.00, Temp 298.00
08/22/2021 | 18:28 | 18:36 | 0.13 | 15400 | 15422 | 22 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15400.00 t/15422.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 165.00, Diff 700.00, Temp 300.00
08/22/2021 | 18:36 | 18:52 | 0.27 | 15422 | 15422 | 0 | LAT | 4: BHA 5 | 8D | Pump repair
08/22/2021 | 18:52 | 19:14 | 0.37 | 15422 | 15463 | 41 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15422.00 t/15463.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 111.82, Diff 700.00, Temp 300.00
08/22/2021 | 19:14 | 19:17 | 0.05 | 15463 | 15463 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 19:17 | 19:29 | 0.2 | 15463 | 15478 | 15 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15463.00 t/15478.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 75.00, Diff 700.00, Temp 301.00
08/22/2021 | 19:29 | 19:51 | 0.37 | 15478 | 15498 | 20 | LAT | 4: BHA 5 | 2J | Slide Drill f/15478.00 t/15498.00, TF 180G, w/WOB 32.00,Flow 400.00, Press 5250, Tq 6500, ROP 54.55, Diff 400.00, Temp 301.00
08/22/2021 | 19:51 | 20:22 | 0.52 | 15498 | 15558 | 60 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15498.00 t/15558.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 116.13, Diff 700.00, Temp 301.00
08/22/2021 | 20:22 | 20:25 | 0.05 | 15558 | 15558 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 20:25 | 21:14 | 0.82 | 15558 | 15652 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15558.00 t/15652.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 115.10, Diff 700.00, Temp 301.00
08/22/2021 | 21:14 | 21:17 | 0.05 | 15652 | 15652 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 21:17 | 22:02 | 0.75 | 15652 | 15747 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15652.00 t/15747.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 126.67, Diff 700.00, Temp 301.00
08/22/2021 | 22:02 | 22:05 | 0.05 | 15747 | 15747 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 22:05 | 22:50 | 0.75 | 15747 | 15841 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15747.00 t/15841.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 125.33, Diff 700.00, Temp 301.00
08/22/2021 | 22:50 | 22:53 | 0.05 | 15841 | 15841 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 22:53 | 23:38 | 0.75 | 15841 | 15935 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15841.00 t/15935.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 125.33, Diff 700.00, Temp 301.00
08/22/2021 | 23:38 | 23:41 | 0.05 | 15935 | 15935 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/22/2021 | 23:41 | 23:51 | 0.17 | 15935 | 15951 | 16 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15935.00 t/15951.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 96.00, Diff 700.00, Temp 301.00
08/22/2021 | 23:51 | 24:00 | 0.15 | 15951 | 15960 | 9 | LAT | 4: BHA 5 | 2J | Slide Drill f/15951.00 t/15960.00, TF 180G, w/WOB 40,Flow 400.00, Press 5350, Tq 6500, ROP 60.00, Diff 500.00, Temp 301.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_23_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 20 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/23/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7450 |  |  | Well Cost($): |  | 97730
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15960 |  | 11265 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 52 | PV: | 21
End Depth (Usft): |  | 17615 |  | 17615 |  | OD (in): |  | 7.625 |  | 300: | 31 | YP: | 10
Total Drilled (Usft): |  | 1655 |  | 6350 |  | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 66
Slide Drilled (Usft): |  | 135 |  | 825 | [5 empty] | 100: | 15 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 1520 |  | 5525 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.80
Drlg/Circ Hrs: |  | 21.32 / 1.15 |  | 61.72 / 6.48 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73/27
Slide Drilling Hrs: |  | 5.68 |  | 16.73 |  | SN: |  | 13628581 |  | 10s Gel: | 7 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 15.63 |  | 44.98 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 120.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 97.23 / 23.75 |  | 122.82 / 49.30 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 79 |  | Grade In: |  | New
% Slide: |  | 8.16 |  | 12.99 |  | Grade Out:
% Rotary: |  | 91.84 |  | 87.01 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .004 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 34.07
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 129.27
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 132.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 320.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 328.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2783.16
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 21.42 |  | 2804.58
2804.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15968 | 86.29 | 152.66 | 11580.66 | -4696.01 | 3230.07 | 1.6 |  | 174.68 | 5656.16 | -1.6 |  | 0.15 | 94
16063 | 85.33 | 152.6 | 11587.6 | -4780.15 | 3273.63 | 1.01 |  | -176.44 | 5750.91 | -1.01 |  | -0.06 | 95
16158 | 85.42 | 152.19 | 11595.26 | -4864.06 | 3317.5 | 0.44 |  | -77.6 | 5845.6 | 0.09 |  | -0.43 | 95
16252 | 86.36 | 152.79 | 11602 | -4947.22 | 3360.81 | 1.19 |  | 32.51 | 5939.35 | 1 |  | 0.64 | 94
16347 | 87.43 | 153.35 | 11607.14 | -5031.79 | 3403.77 | 1.27 |  | 27.61 | 6034.21 | 1.13 |  | 0.59 | 95
16440 | 85.99 | 152.73 | 11612.48 | -5114.54 | 3445.86 | 1.69 |  | -156.76 | 6127.05 | -1.55 |  | -0.67 | 93
16534 | 86.75 | 152.95 | 11618.43 | -5198.01 | 3488.69 | 0.84 |  | 16.12 | 6220.86 | 0.81 |  | 0.23 | 94
16627 | 85.41 | 153.16 | 11624.79 | -5280.72 | 3530.73 | 1.46 |  | 171.12 | 6313.63 | -1.44 |  | 0.23 | 93
16722 | 87.13 | 154.02 | 11630.97 | -5365.62 | 3572.89 | 2.02 |  | 26.55 | 6408.41 | 1.81 |  | 0.91 | 95
16816 | 83.63 | 152.51 | 11638.54 | -5449.28 | 3615.03 | 4.05 |  | -156.79 | 6502.08 | -3.72 |  | -1.61 | 94
16911 | 85.5 | 152.78 | 11647.54 | -5533.28 | 3658.49 | 1.99 |  | 8.19 | 6596.65 | 1.97 |  | 0.28 | 95
17006 | 86.06 | 153.57 | 11654.53 | -5617.82 | 3701.24 | 1.02 |  | 54.62 | 6691.39 | 0.59 |  | 0.83 | 95
17100 | 86.56 | 155.35 | 11660.58 | -5702.46 | 3741.68 | 1.96 |  | 74.34 | 6785.14 | 0.53 |  | 1.89 | 94
17195 | 86.63 | 154.94 | 11666.22 | -5788.51 | 3781.54 | 0.44 |  | -80.31 | 6879.87 | 0.07 |  | -0.43 | 95
17290 | 87.1 | 152.89 | 11671.42 | -5873.7 | 3823.25 | 2.21 |  | -77.13 | 6974.7 | 0.49 |  | -2.16 | 95
17385 | 88.65 | 152.48 | 11674.94 | -5958.05 | 3866.81 | 1.69 |  | -14.81 | 7069.63 | 1.63 |  | -0.43 | 95
17479 | 88.57 | 152.6 | 11677.22 | -6041.43 | 3910.14 | 0.15 |  | 123.7 | 7163.6 | -0.09 |  | 0.13 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 100.28 | 31.12 | 80 | 352 | 400 | 5434.38 | 4879.69 | 0 | 280 | 185 | 165 | 14045.45 | 0
Run | 114.55 | 28.24 | 74.24 | 346 | 400 | 5106.18 | 4431.57 | 0 | 266.3 | 193.11 | 173.7 | 9796.51 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/23/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/23/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/23/2021 |  | 20 |  | -400 |  | 1 | -400
Real Time Survey Management |  |  |  |  | 08/23/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 7450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/23/2021 | 00:00 | 00:24 | 0.4 | 15960 | 15969 | 9 | LAT | 4: BHA 5 | 2J | Slide Drill f/15960.00 t/15969.00, TF 180G, w/WOB 40,Flow 400.00, Press 5350, Tq 6500, ROP 22.50, Diff 500.00, Temp 301.00
08/23/2021 | 00:24 | 00:55 | 0.52 | 15969 | 16029 | 60 | LAT | 4: BHA 5 | 2K | Rotary Drill f/15969.00 t/16029.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 116.13, Diff 700.00, Temp 303.00
08/23/2021 | 00:55 | 00:58 | 0.05 | 16029 | 16029 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 00:58 | 01:07 | 0.15 | 16029 | 16048 | 19 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16029.00 t/16048.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11000.00, ROP 126.67, Diff 700.00, Temp 303.00
08/23/2021 | 01:07 | 01:19 | 0.2 | 16048 | 16056 | 8 | LAT | 4: BHA 5 | 2J | Slide Drill f/16048.00 t/16056.00, TF G, w/WOB 32.00,Flow 400.00, Press 5350, Tq 6500, ROP 40.00, Diff 500.00, Temp 303.00
08/23/2021 | 01:19 | 01:56 | 0.62 | 16056 | 16124 | 68 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16056.00 t/16124.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11500, ROP 110.27, Diff 700.00, Temp 303.00
08/23/2021 | 01:56 | 01:59 | 0.05 | 16124 | 16124 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 01:59 | 02:48 | 0.82 | 16124 | 16219 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16124.00 t/16219.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550, Tq 11500, ROP 116.33, Diff 700.00, Temp 303.00
08/23/2021 | 02:48 | 02:51 | 0.05 | 16219 | 16219 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 02:51 | 03:38 | 0.78 | 16219 | 16313 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16219.00 t/16313.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550.00, Tq 11500.00, ROP 120.00, Diff 700.00, Temp 303.00
08/23/2021 | 03:38 | 03:41 | 0.05 | 16313 | 16313 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 03:41 | 04:29 | 0.8 | 16313 | 16408 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16313.00 t/16408.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550.00, Tq 11500.00, ROP 118.75, Diff 700.00, Temp 303.00
08/23/2021 | 04:29 | 05:16 | 0.78 | 16408 | 16408 | 0 | LAT | 4: BHA 5 | 8P | Rig Service
08/23/2021 | 05:16 | 05:22 | 0.1 | 16408 | 16420 | 12 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16408.00 t/16420.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5550.00, Tq 11500.00, ROP 120.00, Diff 700.00, Temp 303.00
08/23/2021 | 05:22 | 05:25 | 0.05 | 16420 | 16420 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 05:25 | 05:45 | 0.33 | 16420 | 16433 | 13 | LAT | 4: BHA 5 | 2J | Slide Drill f/16420.00 t/16433.00, TF 180G, w/WOB 32.00,Flow 400.00, Press 5350, Tq 8100, ROP 39.00, Diff 500.00, Temp 303.00
08/23/2021 | 05:45 | 06:30 | 0.75 | 16433 | 16501 | 68 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16433.00 t/16501.00, w/WOB 32.00,Flow 400.00, RPM 80.00, Press 5350.00, Tq 11500.00, ROP 90.67, Diff 500.00, Temp 303.00
08/23/2021 | 06:30 | 06:35 | 0.08 | 16501 | 16501 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 06:35 | 07:25 | 0.83 | 16501 | 16595 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16501.00 t/16595.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5350.00, Tq 11500.00, ROP 112.80, Diff 500.00, Temp 303.00
08/23/2021 | 07:25 | 07:30 | 0.08 | 16595 | 16595 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 07:30 | 07:55 | 0.42 | 16595 | 16605 | 10 | LAT | 4: BHA 5 | 2J | Slide Drill f/16595.00 t/16605.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 5350.00, Tq 11500.00, ROP 24.00, Diff 500.00, Temp 303.00
08/23/2021 | 07:55 | 08:40 | 0.75 | 16605 | 16688 | 83 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16605.00 t/16688.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 14000.00, ROP 110.67, Diff 550.00, Temp 303.00
08/23/2021 | 08:40 | 08:45 | 0.08 | 16688 | 16688 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 08:45 | 09:40 | 0.92 | 16688 | 16783 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16688.00 t/16783.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 14000.00, ROP 103.64, Diff 550.00, Temp 303.00
08/23/2021 | 09:40 | 09:45 | 0.08 | 16783 | 16783 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 09:45 | 10:15 | 0.5 | 16783 | 16798 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/16783.00 t/16798.00, TF 180.00G, w/WOB 40.00,Flow 400.00, Press 5450.00, Tq 14000.00, ROP 30.00, Diff 550.00, Temp 303.00
08/23/2021 | 10:15 | 11:05 | 0.83 | 16798 | 16877 | 79 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16798.00 t/16877.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 14500.00, ROP 94.80, Diff 550.00, Temp 304.00
08/23/2021 | 11:05 | 11:10 | 0.08 | 16877 | 16877 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 11:10 | 12:00 | 0.83 | 16877 | 16892 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/16877.00 t/16892.00, TF 0.00G, w/WOB 40.00,Flow 400.00, Press 5450.00, Tq 14500.00, ROP 18.00, Diff 550.00, Temp 304.00
08/23/2021 | 12:00 | 12:40 | 0.67 | 16892 | 16972 | 80 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16892.00 t/16972.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 14500.00, ROP 120.00, Diff 550.00, Temp 304.00
08/23/2021 | 12:40 | 12:45 | 0.08 | 16972 | 16972 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 12:45 | 13:40 | 0.92 | 16972 | 17067 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/16972.00 t/17067.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 17500, ROP 103.64, Diff 550.00, Temp 304.00
08/23/2021 | 13:40 | 13:45 | 0.08 | 17067 | 17067 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 13:45 | 14:45 | 1 | 17067 | 17161 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17067.00 t/17161.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 17500, ROP 94.00, Diff 550.00, Temp 309.00
08/23/2021 | 14:45 | 14:50 | 0.08 | 17161 | 17161 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 14:50 | 15:25 | 0.58 | 17161 | 17176 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/17161.00 t/17176.00, TF 90.00G, w/WOB 40.00,Flow 400.00, Press 5450.00, Tq 14500.00, ROP 25.71, Diff 550.00, Temp 309.00
08/23/2021 | 15:25 | 16:15 | 0.83 | 17176 | 17256 | 80 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17176.00 t/17256.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 17500, ROP 96.00, Diff 550.00, Temp 309.00
08/23/2021 | 16:15 | 17:00 | 0.75 | 17256 | 17256 | 0 | LAT | 4: BHA 5 | 8P | Rig Servive
08/23/2021 | 17:00 | 17:05 | 0.08 | 17256 | 17256 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 17:05 | 17:45 | 0.67 | 17256 | 17271 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/17256.00 t/17271.00, TF 60G, w/WOB 28.00,Flow 400.00, Press 5250, Tq 9500, ROP 22.50, Diff 350.00, Temp 309.00
08/23/2021 | 17:45 | 18:50 | 1.08 | 17271 | 17351 | 80 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17271.00 t/17351.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 17500, ROP 73.85, Diff 550.00, Temp 309.00
08/23/2021 | 18:50 | 18:53 | 0.05 | 17351 | 17351 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 18:53 | 20:04 | 1.18 | 17351 | 17446 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17351.00 t/17446.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 17500, ROP 80.28, Diff 550.00, Temp 309.00
08/23/2021 | 20:04 | 20:07 | 0.05 | 17446 | 17446 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 20:07 | 20:33 | 0.43 | 17446 | 17465 | 19 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17446.00 t/17465.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5450.00, Tq 17500, ROP 43.85, Diff 550.00, Temp 309.00
08/23/2021 | 20:33 | 21:20 | 0.78 | 17465 | 17480 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/17465.00 t/17480.00, TF 180G, w/WOB 28.00,Flow 400.00, Press 5250, Tq 11500, ROP 19.15, Diff 350.00, Temp 309.00
08/23/2021 | 21:20 | 22:08 | 0.8 | 17480 | 17540 | 60 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17480.00 t/17540.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5500, Tq 17500, ROP 75.00, Diff 600.00, Temp 309.00
08/23/2021 | 22:08 | 22:11 | 0.05 | 17540 | 17540 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/23/2021 | 22:11 | 22:26 | 0.25 | 17540 | 17554 | 14 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17540.00 t/17554.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5500, Tq 13500, ROP 56.00, Diff 600.00, Temp 311.00
08/23/2021 | 22:26 | 23:24 | 0.97 | 17554 | 17574 | 20 | LAT | 4: BHA 5 | 2J | Slide Drill f/17554.00 t/17574.00, TF 180G, w/WOB 28.00,Flow 400.00, Press 5300, Tq 8500, ROP 20.69, Diff 400.00, Temp 311.00
08/23/2021 | 23:24 | 24:00 | 0.6 | 17574 | 17615 | 41 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17574.00 t/17615.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300, Tq 13500, ROP 68.33, Diff 400.00, Temp 311.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_24_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 21 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/24/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7450 |  |  | Well Cost($): |  | 105180
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17615 |  | 11265 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 52 | PV: | 21
End Depth (Usft): |  | 17945 |  | 17945 |  | OD (in): |  | 7.625 |  | 300: | 31 | YP: | 10
Total Drilled (Usft): |  | 330 |  | 6680 |  | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 66
Slide Drilled (Usft): |  | 20 |  | 845 | [5 empty] | 100: | 15 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 310 |  | 5835 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.80
Drlg/Circ Hrs: |  | 6.27 / 4.23 |  | 67.98 / 10.72 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73/27
Slide Drilling Hrs: |  | 1.47 |  | 18.2 |  | SN: |  | 13628581 |  | 10s Gel: | 7 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 4.8 |  | 49.78 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 120.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 64.58 / 13.64 |  | 117.21 / 46.43 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 103 |  | Grade In: |  | New
% Slide: |  | 6.06 |  | 12.65 |  | Grade Out:
% Rotary: |  | 93.94 |  | 87.35 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .004 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 34.07
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 129.27
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 132.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 320.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 328.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2783.16
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 21.42 |  | 2804.58
2804.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17574 | 86.35 | 153.83 | 11681.43 | -6126.15 | 3952.91 | 2.67 |  | 151.06 | 7258.5 | -2.34 |  | 1.29 | 95
17668 | 86.2 | 154.14 | 11687.54 | -6210.44 | 3994.05 | 0.37 |  | 115.88 | 7352.27 | -0.16 |  | 0.33 | 94
17763 | 87.04 | 154.3 | 11693.14 | -6295.84 | 4035.3 | 0.9 |  | 10.77 | 7447.06 | 0.88 |  | 0.17 | 95
17858 | 86.26 | 153.08 | 11698.69 | -6380.85 | 4077.33 | 1.52 |  | -122.67 | 7541.88 | -0.82 |  | -1.28 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 52.66 | 30.67 | 80 | 352 | 400 | 5300 | 4900 | 0 | 280 | 185 | 165 | 13071.43 | 0
Run | 98.26 | 28.4 | 74.68 | 347 | 400 | 5119.01 | 4462.57 | 0 | 267.21 | 192.57 | 173.12 | 10043.01 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Multi Rig Discount |  |  |  |  | 08/24/2021 |  | 20 |  | -400 |  | 1 | -400
Dir & MWD /Gamma |  |  |  |  | 08/24/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/24/2021 |  | 5 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 08/24/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 7450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/24/2021 | 00:00 | 00:16 | 0.27 | 17615 | 17635 | 20 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17615.00 t/17635.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 13500.00, ROP 75.00, Diff 400.00, Temp 311.00
08/24/2021 | 00:16 | 00:19 | 0.05 | 17635 | 17635 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/24/2021 | 00:19 | 01:36 | 1.28 | 17635 | 17729 | 94 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17635.00 t/17729.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 17500.00, ROP 73.25, Diff 400.00, Temp 311.00
08/24/2021 | 01:36 | 01:39 | 0.05 | 17729 | 17729 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/24/2021 | 01:39 | 02:59 | 1.33 | 17729 | 17824 | 95 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17729.00 t/17824.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 17500.00, ROP 71.25, Diff 400.00, Temp 311.00
08/24/2021 | 02:59 | 03:02 | 0.05 | 17824 | 17824 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/24/2021 | 03:02 | 03:17 | 0.25 | 17824 | 17836 | 12 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17824.00 t/17836.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 17500.00, ROP 48.00, Diff 400.00, Temp 311.00
08/24/2021 | 03:17 | 04:03 | 0.77 | 17836 | 17851 | 15 | LAT | 4: BHA 5 | 2J | Slide Drill f/17836.00 t/17851.00, TF -150.00G, w/WOB 28.00,Flow 400.00, Press 5300.00, Tq 11500.00, ROP 19.57, Diff 400.00, Temp 311.00
08/24/2021 | 04:03 | 05:03 | 1 | 17851 | 17919 | 68 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17851.00 t/17919.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 8500.00, ROP 68.00, Diff 400.00, Temp 311.00
08/24/2021 | 05:03 | 05:08 | 0.08 | 17919 | 17919 | 0 | LAT | 4: BHA 5 | 5A | Survey & Connection
08/24/2021 | 05:08 | 05:18 | 0.17 | 17919 | 17925 | 6 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17919.00 t/17925.00, w/WOB 28.00,Flow 400.00, RPM 80.00, Press 5300.00, Tq 8500.00, ROP 36.00, Diff 400.00, Temp 311.00
08/24/2021 | 05:18 | 06:00 | 0.7 | 17925 | 17930 | 5 | LAT | 4: BHA 5 | 2J | Slide Drill f/17925.00 t/17930.00, TF 200G, w/WOB 40,Flow 400.00, Press 5300.00, Tq 8500.00, ROP 7.14, Diff 400.00, Temp 311.00
08/24/2021 | 06:00 | 06:30 | 0.5 | 17930 | 17945 | 15 | LAT | 4: BHA 5 | 2K | Rotary Drill f/17930.00 t/17945.00, w/WOB 40,Flow 400.00, RPM 80.00, Press 5300.00, Tq 8500.00, ROP 30.00, Diff 400.00
08/24/2021 | 06:30 | 10:30 | 4 | 17945 | 17945 | 0 | LAT | 4: BHA 5 | 5A | Circulate
08/24/2021 | 10:30 | 24:00 | 13.5 | 17945 | 17945 | 0 | LAT | 4: BHA 5 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_25_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 22 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/25/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19650 |  |  | Well Cost($): |  | 124830
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 6) |  | Run (BHA 6) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17945 |  | 17945 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 52 | PV: | 21
End Depth (Usft): |  | 17945 |  | 17945 |  | OD (in): |  | 7.625 |  | 300: | 31 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 66
Slide Drilled (Usft): | [9 empty] | 100: | 15 | Chlorides: | 54000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.80
Drlg/Circ Hrs: |  | 0.00 / 0.25 |  | 0.00 / 0.25 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73/27
Slide Drilling Hrs: | [5 empty] | SN: |  | 13628581 |  | 10s Gel: | 7 | Weight (ppg): | 10.5
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 120.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 21.67 |  | 21.67 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .004 |  |  |  | 5.5 | 2 |  |  | 45.36 |  | 33.07 |  | 34.07
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 36.1
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.27
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49.15
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.5
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 111.25
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 129.27
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 132.65
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 320.47
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 328.92
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2783.16
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 21.42 |  | 2804.58
2804.58
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250012 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 98.26 | 28.4 | 74.68 | 347 | 400 | 5119.01 | 4462.57 | 0 | 267.21 | 192.57 | 173.12 | 10043.01 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Perdiem |  |  |  |  | 08/25/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/25/2021 |  | 20 |  | -400 |  | 1 | -400
5.5 Premium Motor Reline |  |  |  |  | 08/25/2021 |  | 9 |  | 9000 |  | 1 | 9000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 08/25/2021 |  | 11 |  | 800 |  | 1 | 800
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 08/25/2021 |  | 15 |  | 1000 |  | 1 | 1000
Dir & MWD /Gamma |  |  |  |  | 08/25/2021 |  | 4 |  | 6850 |  | 1 | 6850
Pro Azimuthal Gamma Ray |  |  |  |  | 08/25/2021 |  | 14 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 19650
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/25/2021 | 00:00 | 01:15 | 1.25 | 17945 | 17945 | 0 | LAT | 4: BHA 5 | 6P | LD BHA 5
08/25/2021 | 01:15 | 02:20 | 1.08 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 6O | PU BHA 6
08/25/2021 | 02:20 | 02:35 | 0.25 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 5A | TEST MWD
08/25/2021 | 02:35 | 09:00 | 6.42 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 6A | TIH
08/25/2021 | 09:00 | 11:00 | 2 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 9A | Slip and Cut
08/25/2021 | 11:00 | 14:00 | 3 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 24A | Building Kill Mud
08/25/2021 | 14:00 | 24:00 | 10 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_26_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 23 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/26/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19650 |  |  | Well Cost($): |  | 144480
|  |  |  | 24hr Summary: |  | POOH due to UBHO being packed off.
|  |  |  | 24hr Lookahead: |  | TIH & Continue Lateral
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17945 |  | 17945 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 52 | PV: | 21
End Depth (Usft): |  | 17945 |  | 17945 |  | OD (in): |  | 7.625 |  | 300: | 31 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 66
Slide Drilled (Usft): | [9 empty] | 100: | 15 | Chlorides: | 54000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 13.80
Drlg/Circ Hrs: |  | 0.00 / 6.15 |  | 0.00 / 6.15 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 73/27
Slide Drilling Hrs: | [5 empty] | SN: |  | 13618580 |  | 10s Gel: | 7 | Weight (ppg): | 10.5
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 120.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 18 |  | 18 |  | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jesse Taylor Josh Ray |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .026 |  |  |  | 5.5 | 2 |  |  | 45.56 |  | 32.92 |  | 33.92
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 2.03 |  | 35.95
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.12
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.35
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.87 |  | 90.22
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 48.78 |  | 30.75 |  | 120.97
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 138.99
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 142.37
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 330.19
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 338.64
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2792.88
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 21.95 |  | 2814.83
33 Stands 4 1/2 Dril Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 3116.43 |  | 5931.26
Agitator (On Demand) |  |  |  | 5.312 | 2.5 |  |  | 68.37 |  | 21.94 |  | 5953.2
5953.2
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.06 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 0 | 28.4 | 74.68 | 347 | 400 | 5119.01 | 4462.57 | 0 | 267.21 | 192.57 | 173.12 | 10043.01 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/26/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/26/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/26/2021 |  | 20 |  | -400 |  | 1 | -400
5.5 Premium Motor Stator Reline |  |  |  |  | 08/26/2021 |  | 12 |  | 9000 |  | 1 | 9000
Pro Azimuthal Gamma Ray |  |  |  |  | 08/26/2021 |  | 14 |  | 2000 |  | 1 | 2000
Used Mud Motor Inspection (first 3 Included In Mob / DeMob |  |  |  |  | 08/26/2021 |  | 15 |  | 1000 |  | 1 | 1000
MWD Inspection Fee Per Run (First 3 im mob/Demob) |  |  |  |  | 08/26/2021 |  | 11 |  | 800 |  | 1 | 800
Total | [11 empty] | 19650
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/26/2021 | 00:00 | 04:00 | 4 | 17945 | 17945 | 0 | LAT | 5: BHA 6 | 6P | L/D BHA 6
08/26/2021 | 04:00 | 06:00 | 2 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6O | P/U BHA 7
08/26/2021 | 06:00 | 06:15 | 0.25 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Test MWD
08/26/2021 | 06:15 | 08:20 | 2.08 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6A | TIH
08/26/2021 | 08:20 | 08:45 | 0.42 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Test without/with agitator Psi 1633 - 1756
08/26/2021 | 08:45 | 10:55 | 2.17 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6A | TIH
08/26/2021 | 10:55 | 11:21 | 0.43 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Test without/with agitator Psi 2695 - 2877
08/26/2021 | 11:21 | 15:54 | 4.55 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6A | TIH
08/26/2021 | 15:54 | 17:48 | 1.9 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Circulate kill mud
08/26/2021 | 17:48 | 20:32 | 2.73 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6A | TIH
08/26/2021 | 20:32 | 23:41 | 3.15 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Circulate Gas MW 10.7
08/26/2021 | 23:41 | 24:00 | 0.32 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_27_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 24 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/27/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9450 |  |  | Well Cost($): |  | 153930
|  |  |  | 24hr Summary: |  | TIH & Continue Lateral
|  |  |  | 24hr Lookahead: |  | TD, Circulate & POOH
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 17945 |  | 17945 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 19700 |  | 19700 |  | OD (in): |  | 7.625 |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 1755 |  | 1755 |  | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 62
Slide Drilled (Usft): |  | 128 |  | 128 | [5 empty] | 100: | 15 | Chlorides: | 51600
Rotary Drilled (Usft): |  | 1627 |  | 1627 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 14.40
Drlg/Circ Hrs: |  | 18.77 / 3.15 |  | 18.77 / 9.30 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 3.9 |  | 3.9 |  | SN: |  | 13618580 |  | 10s Gel: | 6 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 14.87 |  | 14.87 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 92.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 109.44 / 32.82 |  | 109.44 / 32.82 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 42 |  | Grade In:
% Slide: |  | 7.29 |  | 7.29 |  | Grade Out:
% Rotary: |  | 92.71 |  | 92.71 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
Kevin Cooper |  | Chris Day |  | Jason Smetters | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .020 |  |  |  | 5.5 | 2 |  |  | 45.01 |  | 33.33 |  | 34.33
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 1.62 |  | 35.95
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.12
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.35
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.87 |  | 90.22
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 47.86 |  | 31.34 |  | 121.56
Filter Sub |  |  |  | 5 | 2.688 |  |  | 34.18 |  | 5.12 |  | 126.68
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 144.7
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 148.08
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 335.9
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 344.35
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2798.59
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 20.91 |  | 2819.5
33 Stands 4 1/2 Dril Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 3116.43 |  | 5935.93
5935.93
Agitator (On Demand) |  |  |  | 5.312 | 2.5 |  |  | 68.37 |  | 21.39 |  | 5957.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
17983 | 87.17 | 152.41 | 11705.85 | -6491.79 | 4134.48 | 0.9 |  | -36.34 | 7666.67 | 0.73 |  | -0.54 | 125
18077 | 85.37 | 151.96 | 11711.97 | -6574.75 | 4178.25 | 1.97 |  | -166.01 | 7760.46 | -1.91 |  | -0.48 | 94
18173 | 86.81 | 152.69 | 11718.51 | -6659.56 | 4222.73 | 1.68 |  | 26.85 | 7856.24 | 1.5 |  | 0.76 | 96
18267 | 84.3 | 152.45 | 11725.8 | -6742.74 | 4265.9 | 2.68 |  | -174.56 | 7949.95 | -2.67 |  | -0.26 | 94
18362 | 83.92 | 152.3 | 11735.55 | -6826.46 | 4309.71 | 0.43 |  | -158.57 | 8044.44 | -0.4 |  | -0.16 | 95
18457 | 83.52 | 152.12 | 11745.94 | -6910 | 4353.74 | 0.46 |  | -155.91 | 8138.87 | -0.42 |  | -0.19 | 95
18551 | 84.65 | 152.96 | 11755.62 | -6992.97 | 4396.85 | 1.5 |  | 36.52 | 8232.37 | 1.2 |  | 0.89 | 94
18644 | 84.99 | 153.32 | 11764.02 | -7075.59 | 4438.7 | 0.53 |  | 46.54 | 8324.99 | 0.37 |  | 0.39 | 93
18740 | 86.01 | 151.1 | 11771.55 | -7160.25 | 4483.32 | 2.54 |  | -65.35 | 8420.68 | 1.06 |  | -2.31 | 96
18832 | 85.99 | 151.23 | 11777.97 | -7240.65 | 4527.58 | 0.14 |  | 98.77 | 8512.43 | -0.02 |  | 0.14 | 92
18926 | 88.75 | 152.36 | 11782.28 | -7323.39 | 4571.95 | 3.17 |  | 22.27 | 8606.31 | 2.94 |  | 1.2 | 94
19020 | 87.11 | 153.11 | 11785.68 | -7406.89 | 4614.99 | 1.92 |  | 155.45 | 8700.25 | -1.74 |  | 0.8 | 94
19115 | 87.85 | 154.13 | 11789.86 | -7491.91 | 4657.16 | 1.33 |  | 54.04 | 8795.14 | 0.78 |  | 1.07 | 95
19210 | 84.98 | 153.46 | 11795.8 | -7576.97 | 4699.02 | 3.1 |  | -166.9 | 8889.92 | -3.02 |  | -0.71 | 95
19305 | 87.32 | 155.14 | 11802.18 | -7662.37 | 4740.12 | 3.03 |  | 35.68 | 8984.65 | 2.46 |  | 1.77 | 95
19399 | 88.27 | 153.81 | 11805.79 | -7747.13 | 4780.59 | 1.74 |  | -54.47 | 9078.52 | 1.01 |  | -1.41 | 94
19494 | 90.01 | 153.72 | 11807.22 | -7832.33 | 4822.58 | 1.83 |  | -2.96 | 9173.49 | 1.83 |  | -0.09 | 95
19589 | 88.92 | 152.63 | 11808.11 | -7917.11 | 4865.45 | 1.62 |  | -135.01 | 9268.48 | -1.15 |  | -1.15 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 93.52 | 28.76 | 75.71 | 309 | 342.74 | 5534.29 | 4910 | 0 | 306.84 | 203.21 | 151.89 | 782.49 | 0
Run | 93.52 | 28.76 | 75.71 | 309 | 342.74 | 5534.29 | 4910 | 0 | 306.84 | 203.21 | 151.89 | 782.49 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
MWD Comments
Max Temp 327.2
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/27/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/27/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/27/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 08/27/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/27/2021 |  | 10 |  | 600 |  | 1 | 600
Total | [11 empty] | 9450
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/27/2021 | 00:00 | 02:05 | 2.08 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 6A | TIH
08/27/2021 | 02:05 | 02:26 | 0.35 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Circulate
08/27/2021 | 02:26 | 02:47 | 0.35 | 17945 | 17945 | 0 | LAT | 6: BHA 7 | 5A | Troubleshoot MWD (Downlinked during trip)
08/27/2021 | 02:47 | 04:36 | 1.82 | 17945 | 18051 | 106 | LAT | 6: BHA 7 | 2K | Rotary Drill f/17945.00 t/18051.00, w/WOB 12.00,Flow 352.00, RPM 80.00, Press 5565.00, Tq 10770.00, ROP 58.35, Diff 615.00, Temp 312.00
08/27/2021 | 04:36 | 04:39 | 0.05 | 18051 | 18051 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 04:39 | 04:46 | 0.12 | 18051 | 18060 | 9 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18051.00 t/18060.00, w/WOB 20.00,Flow 352.00, RPM 80.00, Press 5565.00, Tq 10770.00, ROP 77.14, Diff 615.00, Temp 312.00
08/27/2021 | 04:46 | 05:07 | 0.35 | 18060 | 18075 | 15 | LAT | 6: BHA 7 | 2J | Slide Drill f/18060.00 t/18075.00, TF 180G, w/WOB 38,Flow 352.00, Press 5350, Tq 8.3, ROP 42.86, Diff 400.00, Temp 316.00
08/27/2021 | 05:07 | 05:43 | 0.6 | 18075 | 18145 | 70 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18075.00 t/18145.00, w/WOB 38,Flow 352.00, RPM 80.00, Press 5350, Tq 8.3, ROP 116.67, Diff 400.00, Temp 316.00
08/27/2021 | 05:43 | 05:46 | 0.05 | 18145 | 18145 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 05:46 | 06:40 | 0.9 | 18145 | 18241 | 96 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18145.00 t/18241.00, w/WOB 25.00,Flow 352.00, RPM 80.00, Press 5800.00, Tq 11.50, ROP 106.67, Diff 650.00, Temp 316.00
08/27/2021 | 06:40 | 06:45 | 0.08 | 18241 | 18241 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 06:45 | 07:15 | 0.5 | 18241 | 18256 | 15 | LAT | 6: BHA 7 | 2J | Slide Drill f/18241.00 t/18256.00, TF -130.00G, w/WOB 20.00,Flow 352.00, Press 5400.00, Tq 0.00, ROP 30.00, Diff 250.00, Temp 316.00
08/27/2021 | 07:15 | 07:50 | 0.58 | 18256 | 18335 | 79 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18256.00 t/18335.00, w/WOB 25.00,Flow 352.00, RPM 80.00, Press 5800.00, Tq 12.20, ROP 135.43, Diff 650.00, Temp 316.00
08/27/2021 | 07:50 | 07:55 | 0.08 | 18335 | 18335 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 07:55 | 08:35 | 0.67 | 18335 | 18430 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18335.00 t/18430.00, w/WOB 25.00,Flow 352.00, RPM 80.00, Press 5800.00, Tq 11.50, ROP 142.50, Diff 650.00, Temp 316.00
08/27/2021 | 08:35 | 08:45 | 0.17 | 18430 | 18430 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection: Recycle 3 times due to noise.
08/27/2021 | 08:45 | 09:30 | 0.75 | 18430 | 18525 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18430.00 t/18525.00, w/WOB 30.00,Flow 352.00, RPM 80.00, Press 5800.00, Tq 17.40, ROP 126.67, Diff 650.00, Temp 320.00
08/27/2021 | 09:30 | 09:36 | 0.1 | 18525 | 18525 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 09:36 | 09:42 | 0.1 | 18525 | 18536 | 11 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18525.00 t/18536.00, w/WOB 30.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 17.50, ROP 110.00, Diff 750.00, Temp 322.00
08/27/2021 | 09:42 | 10:06 | 0.4 | 18536 | 18548 | 12 | LAT | 6: BHA 7 | 2J | Slide Drill f/18536.00 t/18548.00, TF 0.00G, w/WOB 20.00,Flow 352.00, Press 5350.00, Tq 0.00, ROP 30.00, Diff 200.00, Temp 322.00
08/27/2021 | 10:06 | 10:32 | 0.43 | 18548 | 18619 | 71 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18548.00 t/18619.00, w/WOB 30.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 14.80, ROP 163.85, Diff 750.00, Temp 324.00
08/27/2021 | 10:32 | 10:37 | 0.08 | 18619 | 18619 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 10:37 | 11:10 | 0.55 | 18619 | 18712 | 93 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18619.00 t/18712.00, w/WOB 30.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 14.90, ROP 169.09, Diff 750.00, Temp 325.00
08/27/2021 | 11:10 | 11:20 | 0.17 | 18712 | 18712 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 11:20 | 11:30 | 0.17 | 18712 | 18722 | 10 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18712.00 t/18722.00, w/WOB 30.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 14.90, ROP 60.00, Diff 750.00, Temp 325.00
08/27/2021 | 11:30 | 11:50 | 0.33 | 18722 | 18732 | 10 | LAT | 6: BHA 7 | 2J | Slide Drill f/18722.00 t/18732.00, TF 0.00G, w/WOB 20.00,Flow 352.00, Press 5300.00, Tq 0.00, ROP 30.00, Diff 150.00, Temp 325.00
08/27/2021 | 11:50 | 12:20 | 0.5 | 18732 | 18808 | 76 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18732.00 t/18808.00, w/WOB 32.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 15.28, ROP 152.00, Diff 750.00, Temp 325.00
08/27/2021 | 12:20 | 12:25 | 0.08 | 18808 | 18808 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 12:25 | 13:00 | 0.58 | 18808 | 18900 | 92 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18808.00 t/18900.00, w/WOB 32.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 15.40, ROP 157.71, Diff 750.00, Temp 327.00
08/27/2021 | 13:00 | 13:05 | 0.08 | 18900 | 18900 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 13:05 | 13:10 | 0.08 | 18900 | 18910 | 10 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18900.00 t/18910.00, w/WOB 32.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 16.20, ROP 120.00, Diff 750.00, Temp 327.00
08/27/2021 | 13:10 | 13:33 | 0.38 | 18910 | 18918 | 8 | LAT | 6: BHA 7 | 2J | Slide Drill f/18910.00 t/18918.00, TF 30.00G, w/WOB 20.00,Flow 352.00, Press 5400.00, Tq 0.00, ROP 20.87, Diff 250.00, Temp 327.00
08/27/2021 | 13:33 | 14:00 | 0.45 | 18918 | 18994 | 76 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18918.00 t/18994.00, w/WOB 32.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 16.33, ROP 168.89, Diff 750.00, Temp 327.00
08/27/2021 | 14:00 | 14:05 | 0.08 | 18994 | 18994 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 14:05 | 14:12 | 0.12 | 18994 | 19006 | 12 | LAT | 6: BHA 7 | 2K | Rotary Drill f/18994.00 t/19006.00, w/WOB 32.00,Flow 352.00, RPM 80.00, Press 5900.00, Tq 16.33, ROP 102.86, Diff 750.00, Temp 327.00
08/27/2021 | 14:12 | 14:40 | 0.47 | 19006 | 19021 | 15 | LAT | 6: BHA 7 | 2J | Slide Drill f/19006.00 t/19021.00, TF 180.00G, w/WOB 20.00,Flow 352.00, Press 5450.00, Tq 0.00, ROP 32.14, Diff 300.00, Temp 325.00
08/27/2021 | 14:40 | 15:10 | 0.5 | 19021 | 19088 | 67 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19021.00 t/19088.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 134.00, Diff 761.00, Temp 327.00
08/27/2021 | 15:10 | 15:15 | 0.08 | 19088 | 19088 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 15:15 | 16:20 | 1.08 | 19088 | 19183 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19088.00 t/19183.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 12.30, ROP 87.69, Diff 761.00, Temp 329.00
08/27/2021 | 16:20 | 17:25 | 1.08 | 19183 | 19183 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 17:25 | 17:35 | 0.17 | 19183 | 19193 | 10 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19183.00 t/19193.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 12.30, ROP 60.00, Diff 761.00, Temp 320.00
08/27/2021 | 17:35 | 17:55 | 0.33 | 19193 | 19205 | 12 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19193.00 t/19205.00, w/WOB 20.00,Flow 330.00, RPM 0.00, Press 4850.00, Tq 0.00, ROP 36.00, Diff 220.00, Temp 320.00
08/27/2021 | 17:55 | 18:25 | 0.5 | 19205 | 19278 | 73 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19205.00 t/19278.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 146.00, Diff 761.00, Temp 327.00
08/27/2021 | 18:25 | 18:28 | 0.05 | 19278 | 19278 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 18:28 | 18:45 | 0.28 | 19278 | 19285 | 7 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19278.00 t/19285.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 24.71, Diff 761.00, Temp 327.20
08/27/2021 | 18:45 | 19:08 | 0.38 | 19285 | 19300 | 15 | LAT | 6: BHA 7 | 2J | Slide Drill f/19285.00 t/19300.00, TF 0.00G, w/WOB 32.00,Flow 330.00, Press 5130.00, Tq 11500.00, ROP 39.13, Diff 500.00, Temp 325.00
08/27/2021 | 19:08 | 19:40 | 0.53 | 19300 | 19373 | 73 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19300.00 t/19373.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 136.88, Diff 761.00, Temp 327.00
08/27/2021 | 19:40 | 19:43 | 0.05 | 19373 | 19373 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 19:43 | 20:36 | 0.88 | 19373 | 19467 | 94 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19373.00 t/19467.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 106.42, Diff 761.00, Temp 327.00
08/27/2021 | 20:36 | 20:39 | 0.05 | 19467 | 19467 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 20:39 | 21:33 | 0.9 | 19467 | 19562 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19467.00 t/19562.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 105.56, Diff 761.00, Temp 327.00
08/27/2021 | 21:33 | 21:36 | 0.05 | 19562 | 19562 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 21:36 | 21:49 | 0.22 | 19562 | 19570 | 8 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19562.00 t/19570.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 36.92, Diff 761.00, Temp 327.00
08/27/2021 | 21:49 | 22:22 | 0.55 | 19570 | 19588 | 18 | LAT | 6: BHA 7 | 2J | Slide Drill f/19570.00 t/19588.00, TF -160.00G, w/WOB 32.00,Flow 330.00, Press 5130.00, Tq 14.25, ROP 32.73, Diff 500.00, Temp 325.40
08/27/2021 | 22:22 | 22:58 | 0.6 | 19588 | 19657 | 69 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19588.00 t/19657.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 115.00, Diff 761.00, Temp 327.00
08/27/2021 | 22:58 | 23:01 | 0.05 | 19657 | 19657 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/27/2021 | 23:01 | 23:19 | 0.3 | 19657 | 19673 | 16 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19657.00 t/19673.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 53.33, Diff 761.00, Temp 327.00
08/27/2021 | 23:19 | 23:51 | 0.53 | 19673 | 19693 | 20 | LAT | 6: BHA 7 | 2J | Slide Drill f/19673.00 t/19693.00, TF -160.00G, w/WOB 32.00,Flow 330.00, Press 5391.00, Tq 14.25, ROP 37.50, Diff 761.00, Temp 325.40
08/27/2021 | 23:51 | 24:00 | 0.15 | 19693 | 19700 | 7 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19693.00 t/19700.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 46.67, Diff 761.00, Temp 325.40
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_28_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 25 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/28/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 22700 |  |  | Well Cost($): |  | 176630
|  |  |  | 24hr Summary: |  | Drilling lateral
|  |  |  | 24hr Lookahead: |  | TD well, Circulate & POOH
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 19700 |  | 17945 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 20514 |  | 20514 |  | OD (in): |  | 7.625 |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  | 814 |  | 2569 |  | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 62
Slide Drilled (Usft): |  | 20 |  | 148 | [5 empty] | 100: | 15 | Chlorides: | 51600
Rotary Drilled (Usft): |  | 794 |  | 2421 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 14.40
Drlg/Circ Hrs: |  | 8.50 / 7.72 |  | 27.27 / 17.02 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  | 0.7 |  | 4.6 |  | SN: |  | 13618580 |  | 10s Gel: | 6 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  | 7.8 |  | 22.67 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 92.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 101.79 / 28.57 |  | 106.81 / 32.17 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 66 |  | Grade In:
% Slide: |  | 2.46 |  | 5.76 |  | Grade Out:
% Rotary: |  | 97.54 |  | 94.24 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Chris Day |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .020 |  |  |  | 5.5 | 2 |  |  | 45.01 |  | 33.33 |  | 34.33
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 1.62 |  | 35.95
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.12
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.35
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.87 |  | 90.22
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 47.86 |  | 31.34 |  | 121.56
Filter Sub |  |  |  | 5 | 2.688 |  |  | 34.18 |  | 5.12 |  | 126.68
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 144.7
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 148.08
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 335.9
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 344.35
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2798.59
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 20.91 |  | 2819.5
33 Stands 4 1/2 Dril Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 3116.43 |  | 5935.93
5935.93
Agitator (On Demand) |  |  |  | 5.312 | 2.5 |  |  | 68.37 |  | 21.39 |  | 5957.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
19683 | 87.72 | 150.53 | 11810.86 | -7999.73 | 4910.16 | 2.57 |  | -119.78 | 9362.41 | -1.28 |  | -2.23 | 94
19778 | 85.2 | 151.41 | 11816.73 | -8082.63 | 4956.17 | 2.81 |  | 160.81 | 9457.19 | -2.65 |  | 0.93 | 95
19873 | 84.83 | 150.91 | 11824.98 | -8165.54 | 5001.82 | 0.65 |  | -126.63 | 9551.8 | -0.39 |  | -0.53 | 95
19967 | 84.81 | 151.53 | 11833.47 | -8247.59 | 5046.89 | 0.66 |  | 91.88 | 9645.39 | -0.02 |  | 0.66 | 94
20062 | 85.07 | 151.25 | 11841.85 | -8330.66 | 5092.21 | 0.4 |  | -47.02 | 9740 | 0.27 |  | -0.29 | 95
20154 | 85.55 | 151.41 | 11849.37 | -8411.11 | 5136.2 | 0.55 |  | 18.38 | 9831.67 | 0.52 |  | 0.17 | 92
20249 | 86.43 | 152.12 | 11856.01 | -8494.6 | 5181.03 | 1.19 |  | 38.85 | 9926.43 | 0.93 |  | 0.75 | 95
20344 | 87.7 | 153.17 | 11860.88 | -8578.87 | 5224.62 | 1.73 |  | 39.57 | 10021.3 | 1.34 |  | 1.11 | 95
20439 | 86.97 | 152.22 | 11865.3 | -8663.19 | 5268.15 | 1.26 |  | -127.59 | 10116.19 | -0.77 |  | -1 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 95.76 | 32 | 70 | 294 | 330 | 5233.85 | 4583.85 | 0 | 311.15 | 205 | 150 | 1513.37 | 0
Run | 94.22 | 29.59 | 74.1 | 305 | 339.49 | 5449.82 | 4826.86 | 0 | 307.94 | 203.67 | 151.41 | 988.63 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
MWD Comments
Max temp 331
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/28/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/28/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/28/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 08/28/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/28/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 08/28/2021 |  | 18 |  | 1250 |  | 1 | 1250
Pro Azimuthal Gamma Ray Core charge >330F |  |  |  |  | 08/28/2021 |  | 19 |  | 12000 |  | 1 | 12000
Total | [11 empty] | 22700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/28/2021 | 00:00 | 00:23 | 0.38 | 19700 | 19751 | 51 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19700.00 t/19751.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5391.00, Tq 14.25, ROP 133.04, Diff 761.00, Temp 325.40
08/28/2021 | 00:23 | 00:26 | 0.05 | 19751 | 19751 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 00:26 | 00:34 | 0.13 | 19751 | 19761 | 10 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19751.00 t/19761.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5240, Tq 14.25, ROP 75.00, Diff 660.00, Temp 327.20
08/28/2021 | 00:34 | 01:00 | 0.43 | 19761 | 19776 | 15 | LAT | 6: BHA 7 | 2J | Slide Drill f/19761.00 t/19776.00, TF 180G, w/WOB 32.00,Flow 330.00, Press 5160, Tq 10800, ROP 34.62, Diff 580.00, Temp 325.40
08/28/2021 | 01:00 | 01:35 | 0.58 | 19776 | 19846 | 70 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19776.00 t/19846.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 16500.00, ROP 120.00, Diff 650.00, Temp 329.00
08/28/2021 | 01:35 | 01:38 | 0.05 | 19846 | 19846 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 01:38 | 01:50 | 0.2 | 19846 | 19865 | 19 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19846.00 t/19865.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 14.25, ROP 95.00, Diff 650.00, Temp 329.00
08/28/2021 | 01:50 | 02:06 | 0.27 | 19865 | 19870 | 5 | LAT | 6: BHA 7 | 2J | Slide Drill f/19865.00 t/19870.00, TF 180.00G, w/WOB 32.00,Flow 330.00, Press 5230.00, Tq 14.25, ROP 18.75, Diff 650.00, Temp 329.00
08/28/2021 | 02:06 | 02:09 | 0.05 | 19870 | 19870 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 02:09 | 02:48 | 0.65 | 19870 | 19941 | 71 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19870.00 t/19941.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 14.25, ROP 109.23, Diff 650.00, Temp 329.00
08/28/2021 | 02:48 | 02:51 | 0.05 | 19941 | 19941 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 02:51 | 03:49 | 0.97 | 19941 | 20035 | 94 | LAT | 6: BHA 7 | 2K | Rotary Drill f/19941.00 t/20035.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 14.25, ROP 97.24, Diff 650.00, Temp 331.00
08/28/2021 | 03:49 | 03:51 | 0.03 | 20035 | 20035 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 03:51 | 04:52 | 1.02 | 20035 | 20130 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/20035.00 t/20130.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 14.25, ROP 93.44, Diff 650.00, Temp 331.00
08/28/2021 | 04:52 | 04:55 | 0.05 | 20130 | 20130 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 04:55 | 05:46 | 0.85 | 20130 | 20222 | 92 | LAT | 6: BHA 7 | 2K | Rotary Drill f/20130.00 t/20222.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 14.25, ROP 108.24, Diff 650.00, Temp 331.00
08/28/2021 | 05:46 | 05:49 | 0.05 | 20222 | 20222 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 05:49 | 06:45 | 0.93 | 20222 | 20317 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/20222.00 t/20317.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 16.30, ROP 101.79, Diff 650.00, Temp 333.00
08/28/2021 | 06:45 | 06:50 | 0.08 | 20317 | 20317 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection
08/28/2021 | 06:50 | 07:50 | 1 | 20317 | 20412 | 95 | LAT | 6: BHA 7 | 2K | Rotary Drill f/20317.00 t/20412.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 15.53, ROP 95.00, Diff 650.00, Temp 333.00
08/28/2021 | 07:50 | 08:05 | 0.25 | 20412 | 20412 | 0 | LAT | 6: BHA 7 | 5A | Survey & Connection. Recycle 3xs for noise
08/28/2021 | 08:05 | 09:10 | 1.08 | 20412 | 20514 | 102 | LAT | 6: BHA 7 | 2K | Rotary Drill f/20412.00 t/20514.00, w/WOB 32.00,Flow 330.00, RPM 70.00, Press 5230.00, Tq 15.50, ROP 94.15, Diff 650.00, Temp 333.00
08/28/2021 | 09:10 | 09:15 | 0.08 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 5A | Survey @ TD
08/28/2021 | 09:15 | 13:10 | 3.92 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 5A | Circulate at TD
08/28/2021 | 13:10 | 19:13 | 6.05 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 6B | POOH
08/28/2021 | 19:13 | 22:16 | 3.05 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 5A | Circualte Gas
08/28/2021 | 22:16 | 24:00 | 1.73 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 24B | Standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 8_29_2021_DDR
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31159 / 20DD0327MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 26 |  |  | Well: |  | Rommel 3H
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Longitude: |  | 96° 37' 52.247" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 08/29/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 10700 |  |  | Well Cost($): |  | 187330
|  |  |  | 24hr Summary: |  | TD, circulate, POOH and LD BHA
|  |  |  | 24hr Lookahead: |  | Standby
Drilling Summary |  | 24Hr (BHA 7) |  | Run (BHA 7) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 20514 |  | 17945 |  | Csg Shoe MD(Usft): |  | 11014 |  | 600: | 50 | PV: | 20
End Depth (Usft): |  | 20514 |  | 20514 |  | OD (in): |  | 7.625 |  | 300: | 30 | YP: | 10
Total Drilled (Usft): |  |  |  | 2569 |  | Weight (ft/lbs): |  | 45 |  | 200: | 23 | Viscosity: | 62
Slide Drilled (Usft): |  |  |  | 148 | [5 empty] | 100: | 15 | Chlorides: | 51600
Rotary Drilled (Usft): |  |  |  | 2421 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.40 / 14.40
Drlg/Circ Hrs: |  |  |  | 27.27 / 17.02 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 75/25
Slide Drilling Hrs: |  |  |  | 4.6 |  | SN: |  | 13618580 |  | 10s Gel: | 6 | Weight (ppg): | 10.5
Rotary Drilling Hrs: |  |  |  | 22.67 |  | Bit # |  | 5 |  | PH / Temp(F) | 0.0 / 92.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 106.81 / 32.17 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 6 |  | 72 |  | Grade In:
% Slide: |  |  |  | 5.76 |  | Grade Out:
% Rotary: |  |  |  | 94.24 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Brandon Parks |  | Josh Ray |  | Danny Veronie |  | Peter Langille |  | Patrick Chris |  | Bill Trey |  | Daniel Alvarado
James Dyer |  | Chris Day |  | Chris Inman | [7 empty] | Jorge Lozano
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
NA |  | NA |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  | 50 |  | 1 |  | 1
6/7 8.8 2.12 TS HS88 .020 |  |  |  | 5.5 | 2 |  |  | 45.01 |  | 33.33 |  | 34.33
BTI Valve |  |  |  | 4.875 | 2 |  |  | 49.26 |  | 1.62 |  | 35.95
NMPC |  |  |  | 5 | 2.688 |  |  | 54.53 |  | 9.17 |  | 45.12
UBHO |  |  |  | 5.25 | 2.5 |  |  | 45.1 |  | 3.88 |  | 49
NMDC (NO HARDBANDING) |  |  |  | 5.25 | 2.688 |  |  | 47.85 |  | 31.35 |  | 80.35
NMPC |  |  |  | 5 | 2.688 |  |  | 50.66 |  | 9.87 |  | 90.22
NMDC (NO HARDBANDING) |  |  |  | 5.125 | 2.688 |  |  | 47.86 |  | 31.34 |  | 121.56
Filter Sub |  |  |  | 5 | 2.688 |  |  | 34.18 |  | 5.12 |  | 126.68
Tomax |  |  |  | 5.25 | 2.5 |  |  | 55.49 |  | 18.02 |  | 144.7
Crossover |  |  |  | 5.25 | 2.688 |  |  | 48.82 |  | 3.38 |  | 148.08
2 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 187.82 |  | 335.9
Drill-N-Ream |  |  |  | 5.375 | 2.625 |  |  | 47.34 |  | 8.45 |  | 344.35
26 Stands 4 1/2 Drill Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 2454.24 |  | 2798.59
Agitator |  |  |  | 5.312 | 2.5 |  |  | 70.03 |  | 20.91 |  | 2819.5
33 Stands 4 1/2 Dril Pipe |  |  |  | 4.5 | 3.8 |  |  | 16.6 |  | 3116.43 |  | 5935.93
5935.93
Agitator (On Demand) |  |  |  | 5.312 | 2.5 |  |  | 68.37 |  | 21.39 |  | 5957.32
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 94.22 | 29.59 | 74.1 | 305 | 339.49 | 5449.82 | 4826.86 | 0 | 307.94 | 203.67 | 151.41 | 988.63 | 0
Pump Data
# | Type |  |  | Effeciency (%) | Stroke (in) | Liner (in) | Liner Rating (psi) |  | Pop Offs (psi) |  | Output bbls/stk / gal/stk
1 | Triplex |  |  | 95 | 12 | 5.25 | 5600 |  | 0 |  | 0.0760 / 3.1920
MWD Comments
Max temp 333
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Dir & MWD /Gamma |  |  |  |  | 08/29/2021 |  | 4 |  | 6850 |  | 1 | 6850
Perdiem |  |  |  |  | 08/29/2021 |  | 5 |  | 100 |  | 4 | 400
Multi Rig Discount |  |  |  |  | 08/29/2021 |  | 20 |  | -400 |  | 1 | -400
Pro Azimuthal Gamma Ray |  |  |  |  | 08/29/2021 |  | 14 |  | 2000 |  | 1 | 2000
Real Time Survey Management |  |  |  |  | 08/29/2021 |  | 10 |  | 600 |  | 1 | 600
MWD hot hole charge |  |  |  |  | 08/29/2021 |  | 18 |  | 1250 |  | 1 | 1250
Total | [11 empty] | 10700
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
08/29/2021 | 00:00 | 04:45 | 4.75 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 6B | POOH
08/29/2021 | 04:45 | 06:00 | 1.25 | 20514 | 20514 | 0 | LAT | 6: BHA 7 | 6P | LD BHA 7
08/29/2021 | 06:00 | 24:00 | 18 | 20514 | 20514 | 0 | LAT |  | 24B | Standby for casing and rig skid
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 392.20 (Usft)
Well: |  |  | Rommel 3H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1125821 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 07/14/2021 | Depth In: |  | 108 | Total Drilled: |  | 3415.00 (Usft)
Date Out: |  |  | 07/15/2021 | Depth Out: |  | 3523 | Drilling / Circ Hours: |  | 8.13 / 3.68
Survey Offset: |  |  | 72
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 38426 | U616S | 13.5 |  |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | MTR775044 | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 | 8 |  | 8.000 / 1.73 | 6 5/8 REG / 6 5/8 REG |  | 37.55 | 39.05
| 3 | SD603251 | 13 Stab | 8.125 | 3 | 8.125 / 2.57 | 6 5/8 REG / 6 5/8 REG |  | 6.34 | 45.39
| 4 | SD55524 | NMPC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 8.58 | 53.97
| 5 | 775213 | UBHO Sub UBHO Sub | 7.75 | 2.875 |  | 6 5/8 REG / 6 5/8 REG |  | 3.66 | 57.63
| 6 | SD56120 | NMDC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 28.83 | 86.46
| 7 | SD55920 | NMDC | 8 | 3.25 | 8.000 | 6 5/8 REG / 6 5/8 REG |  | 28.99 | 115.45
| 8 | SD117248 | Crossover Sub | 6.75 | 2.875 | 6.750 / 1.44 | 4 1/2 IF / 6 5/8 REG |  | 2.13 | 117.58
| 9 |  | 9 Jts HWDP | 5 | 3 |  |  |  | 274.62 | 392.2
| 10 | [8 empty] | 392.2
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | U616S | 1.35 | Ulterra | U616S | 0-0- | 1-3-CT-S-X-I-TD | 3415
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  | PDCI / 7/8 5.9 | 6.08 / 1.50 |  | 13 | 8.5 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 100 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.016
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 | 13 |  | 0 |  |  | 3.81
3 |  |  | 13 Stab | 13 |  | 0 |  |  | 40.76

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2662.19 (Usft)
Well: |  |  | Rommel 3H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 44.85 / 38.28 (klbs)
Job #: |  |  | LTX1125821 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 44.85 / 38.28 (klbs)
Date In: |  |  | 08/02/2021 | Depth In: |  | 3523 | Total Drilled: |  | 7499.00 (Usft)
Date Out: |  |  | 08/05/2021 | Depth Out: |  | 11022 | Drilling / Circ Hours: |  | 39.42 / 9.62
Survey Offset: |  |  | 64 | Gamma Offset: |  | 60
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 56410 | SPL613 | 9.875 | 2 |  | 6 5/8 REG | 125.00 / 0.19 / 0.19 | 1.5 | 1.5
| 2 | PPM800058 | 7/8 5.9 2.00 Slick HPO -.014 | 8 | 2 | 8.000 / 2.07 | 6 5/8 REG / 6 5/8 REG | 100.00 / 3.76 / 3.94 | 37.56 | 39.06
| 3 | SD54585 | NMPC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG | 162.87 / 1.50 / 5.44 | 9.21 | 48.27
| 4 | 775225 | UBHO Sub | 7.75 | 3 |  | 6 5/8 REG / 6 5/8 REG | 150.00 / 0.60 / 6.04 | 3.97 | 52.24
| 5 | SD53215 | NMDC | 7.812 | 3.312 |  | 6 5/8 REG / 6 5/8 REG | 157.90 / 4.35 / 10.39 | 27.55 | 79.79
| 6 | SD46074 | NMDC | 8 | 3.312 |  | 6 5/8 REG / 6 5/8 REG | 151.30 / 4.35 / 14.74 | 28.75 | 108.54
| 7 | SD118447 | Crossover Sub | 6.75 | 2.875 | 6.750 / 1.50 | 4 1/2 XH / 6 5/8 REG | 100.00 / 0.25 / 14.99 | 2.55 | 111.09
| 8 |  | 6.5 DC 6 Jts | 6.5 | 2.375 |  | 4 1/2 XH / 4 1/2 XH | 95.00 / 17.79 / 32.78 | 187.23 | 298.32
| 9 |  | HWDP 9 Jts | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF | 43.00 / 11.82 / 44.60 | 274.85 | 573.17
| 10 | SD107702 | Crossover Sub | 6.5 | 2.875 |  | 4 1/2 IF / 4 1/2 XH | 95.00 / 0.25 / 44.85 | 2.67 | 575.84
| 11 |  | DP 22 Stds | 5 | 3.5 |  | 4 1/2 IF / 4 1/2 IF | 19.60 / 40.41 / 85.26 | 2061.7 | 2637.54
| 12 | PG675-0027 | Agitator | 6.562 | 3.75 | 6.562 / 1.85 | 4 1/2 IF / 4 1/2 IF | 80.00 / 1.97 / 87.23 | 24.65 | 2662.19
| 13 | [8 empty] | 2662.19
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | SPL613 | 1.49 | Ulterra | SPL613 | New | 0-1-CT-S-X-I-WT-TD | 7499
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 5.9 2.00 Slick HPO -.014 |  |  | PDCI / 7/8 5.9 | 6.04 / 2.00 |  | 0 | 8.19 | 250 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 800 | 80 |  | 400-900 | 0.166 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | Abaco | HPO |  | -0.014
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
|  |  | 1.4 |  |  | 1.122
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6109 |  |  |  | 7399 |  | 1349 |  |  | 351
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
1125
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 119.58 (Usft)
Well: |  |  | Rommel 3H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 5.66 / 4.83 (klbs)
Job #: |  |  | LTX1125821 | Bit #: |  | 4 | Wt. Below Jars (Air/Mud): |  | 5.66 / 4.83 (klbs)
Date In: |  |  | 08/19/2021 | Depth In: |  | 11022 | Total Drilled: |  | 243.00 (Usft)
Date Out: |  |  | 08/20/2021 | Depth Out: |  | 11265 | Drilling / Circ Hours: |  | 21.08 / 2.42
Survey Offset: |  |  | 61 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13628581 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | BTI1 | BTI Valve | 4.875 | 2 |  | XT39 / XT39 | 49.26 / 0.10 / 0.15 | 2.03 | 3.03
| 3 | PPM250024 | 6/7 8.8 2.25 TS HS88 .000 | 5.5 | 2 | 5.000 / 1.90 | XT39 / 3 1/2 Reg | 45.36 / 1.50 / 1.65 | 33.07 | 36.1
| 4 | GT50-10-637 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 54.53 / 0.50 / 2.15 | 9.17 | 45.27
| 5 | 500046 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 45.10 / 0.17 / 2.32 | 3.88 | 49.15
| 6 | GT52-30-606 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 0.99 | XT39 / XT39 | 47.85 / 1.50 / 3.82 | 31.35 | 80.5
| 7 | GT52-30-458 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 1.40 | XT39 / XT39 | 48.78 / 1.50 / 5.32 | 30.75 | 111.25
| 8 | GT5033743 | Filter Sub | 5 | 2.688 |  | XT39 / XT39 | 35.35 / 0.18 / 5.50 | 4.95 | 116.2
| 9 | GT52331429 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 | 48.82 / 0.17 / 5.66 | 3.38 | 119.58
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New | 1-1-NO-A-X-I-NO-BHA | 243
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.25 TS HS88 .000 |  |  | PDCI / 6/7 8.8 | 4.05 / 2.25 |  | 0 | 5.5 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1200 | 30 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV | HS88
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.122 | PDCI | UBHO | 2.5
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6221 |  |  |  | 7426 |  | 2055
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
1103 |  |  |  | 0.5 |  |  |  |  | No
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2804.58 (Usft)
Well: |  |  | Rommel 3H | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 10.01 / 8.40 (klbs)
Job #: |  |  | LTX1125821 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 10.01 / 8.40 (klbs)
Date In: |  |  | 08/20/2021 | Depth In: |  | 11265 | Total Drilled: |  | 6680.00 (Usft)
Date Out: |  |  | 08/25/2021 | Depth Out: |  | 17945 | Drilling / Circ Hours: |  | 67.98 / 10.72
Survey Offset: |  |  | 61 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13628581 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250012 | 6/7 8.8 2.12 TS HS88 .004 | 5.5 | 2 | 5.000 / 1.87 | XT39 / 3 1/2 Reg | 45.36 / 1.50 / 1.55 | 33.07 | 34.07
| 3 | BTI1 | BTI Valve | 4.875 | 2 |  | XT39 / XT39 | 49.26 / 0.10 / 1.65 | 2.03 | 36.1
| 4 | GT50-10-637 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 54.53 / 0.50 / 2.15 | 9.17 | 45.27
| 5 | 500046 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 45.10 / 0.17 / 2.32 | 3.88 | 49.15
| 6 | GT52-30-606 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 0.99 | XT39 / XT39 | 47.85 / 1.50 / 3.82 | 31.35 | 80.5
| 7 | GT52-30-458 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 1.40 | XT39 / XT39 | 48.78 / 1.50 / 5.32 | 30.75 | 111.25
| 8 | A52137 | Tomax | 5.25 | 2.5 | 5.000 / 2.02 | XT39 / XT39 | 55.49 / 1.00 / 6.32 | 18.02 | 129.27
| 9 | GT52331429 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 | 48.82 / 0.17 / 6.49 | 3.38 | 132.65
| 10 | RIG | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.12 / 9.61 | 187.82 | 320.47
| 11 | 532 | Drill-N-Ream | 5.375 | 2.625 | 5.375 / 1.25 | CET43 / CET43 | 47.34 / 0.40 / 10.01 | 8.45 | 328.92
| 12 |  | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 40.74 / 50.75 | 2454.24 | 2783.16
| 13 | PG525-0051 | Agitator | 5.312 | 2.5 | 5.312 / 1.79 | CET43 / CET43 | 70.03 / 1.50 / 52.25 | 21.42 | 2804.58
| 14 | [8 empty] | 2804.58
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New |  | 6680
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 TS HS88 .004 |  |  | PDCI / 6/7 8.8 | 4.08 / 2.12 |  | 0 | 5.62 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1200 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV | HS88 |  | 0.004
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.122 | PDCI | UBHO | 2.5
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
|  |  |  | 0.5 |  |  |  |  | No
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_6
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5953.20 (Usft)
Well: |  |  | Rommel 3H | BHA #: |  | 6 | BHA Weight (Air/Mud): |  | 52.79 / 44.32 (klbs)
Job #: |  |  | LTX1125821 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 52.79 / 44.32 (klbs)
Date In: |  |  | 08/25/2021 | Depth In: |  | 17945 | Total Drilled: |  | 0.00 (Usft)
Date Out: |  |  | 08/26/2021 | Depth Out: |  | 17945 | Drilling / Circ Hours: |  | 0.00 / 0.25
Survey Offset: |  |  | 68 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618580 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250004 | 6/7 8.8 2.12 TS HS88 .026 | 5.5 | 2 | 5.000 / 1.87 | XT39 / 3 1/2 Reg | 45.56 / 1.50 / 1.55 | 32.92 | 33.92
| 3 | BTI1 | BTI Valve | 4.875 | 2 |  | XT39 / XT39 | 49.26 / 0.10 / 1.65 | 2.03 | 35.95
| 4 | GT50-10-637 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 54.53 / 0.50 / 2.15 | 9.17 | 45.12
| 5 | 500046 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 45.10 / 0.17 / 2.33 | 3.88 | 49
| 6 | GT52-30-606 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 0.99 | XT39 / XT39 | 47.85 / 1.50 / 3.83 | 31.35 | 80.35
| 7 | GT50-10-479 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 50.66 / 0.50 / 4.33 | 9.87 | 90.22
| 8 | GT52-30-458 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 1.40 | XT39 / XT39 | 48.78 / 1.50 / 5.82 | 30.75 | 120.97
| 9 | A52137 | Tomax | 5.25 | 2.5 | 5.000 / 2.02 | XT39 / XT39 | 55.49 / 1.00 / 6.82 | 18.02 | 138.99
| 10 | GT52331429 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 | 48.82 / 0.17 / 6.99 | 3.38 | 142.37
| 11 | RIG | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.12 / 10.11 | 187.82 | 330.19
| 12 | 532 | Drill-N-Ream | 5.375 | 2.625 | 5.375 / 1.25 | CET43 / CET43 | 47.34 / 0.40 / 10.51 | 8.45 | 338.64
| 13 |  | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 40.74 / 51.25 | 2454.24 | 2792.88
| 14 | PG525-0057 | Agitator | 5.312 | 2.5 | 5.312 / 1.83 | CET43 / CET43 | 70.03 / 1.54 / 52.79 | 21.95 | 2814.83
| 15 |  | 33 Stands 4 1/2 Dril Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 51.73 / 104.52 | 3116.43 | 5931.26
| 16 | PG525-0054 | Agitator (On Demand) | 5.312 | 2.5 | 5.312 / 1.83 | v / CET43 | 68.37 / 1.50 / 106.02 | 21.94 | 5953.2
| 17 | [8 empty] | 5953.2
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M |  |  | 0
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 TS HS88 .026 |  |  | PDCI / 6/7 8.8 | 4.06 / 2.12 |  | 0 | 5.62 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1200 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV | HS88 |  | 0.024
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.122 | PDCI | UBHO | 2.5
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
|  |  |  | 0.5 |  |  |  |  | Yes
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_7
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 5957.32 (Usft)
Well: |  |  | Rommel 3H | BHA #: |  | 7 | BHA Weight (Air/Mud): |  | 52.87 / 44.39 (klbs)
Job #: |  |  | LTX1125821 | Bit #: |  | 5 | Wt. Below Jars (Air/Mud): |  | 52.87 / 44.39 (klbs)
Date In: |  |  | 08/26/2021 | Depth In: |  | 17945 | Total Drilled: |  | 2569.00 (Usft)
Date Out: |  |  | 08/29/2021 | Depth Out: |  | 20514 | Drilling / Circ Hours: |  | 27.27 / 17.02
Survey Offset: |  |  | 68 | Gamma Offset: |  | 57
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13618580 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg | 50.00 / 0.05 / 0.05 | 1 | 1
| 2 | PPM250016 | 6/7 8.8 2.12 TS HS88 .020 | 5.5 | 2 | 5.000 / 1.87 | XT39 / 3 1/2 Reg | 45.01 / 1.50 / 1.55 | 33.33 | 34.33
| 3 | BTI2 | BTI Valve | 4.875 | 2 |  | XT39 / XT39 | 49.26 / 0.08 / 1.63 | 1.62 | 35.95
| 4 | GT50-10-637 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 54.53 / 0.50 / 2.13 | 9.17 | 45.12
| 5 | 500046 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 | 45.10 / 0.17 / 2.30 | 3.88 | 49
| 6 | GT52-30-606 | NMDC (NO HARDBANDING) | 5.25 | 2.688 | 5.000 / 0.99 | XT39 / XT39 | 47.85 / 1.50 / 3.80 | 31.35 | 80.35
| 7 | GT50-10-479 | NMPC | 5 | 2.688 |  | XT39 / XT39 | 50.66 / 0.50 / 4.30 | 9.87 | 90.22
| 8 | GT51-30-618 | NMDC (NO HARDBANDING) | 5.125 | 2.688 | 5.000 / 1.40 | XT39 / XT39 | 47.86 / 1.50 / 5.80 | 31.34 | 121.56
| 9 | GT5033740 | Filter Sub | 5 | 2.688 |  | XT39 / XT39 | 34.18 / 0.18 / 5.98 | 5.12 | 126.68
| 10 | A52137 | Tomax | 5.25 | 2.5 | 5.000 / 2.02 | XT39 / XT39 | 55.49 / 1.00 / 6.98 | 18.02 | 144.7
| 11 | GT52331429 | Crossover | 5.25 | 2.688 |  | CET43 / XT39 | 48.82 / 0.17 / 7.14 | 3.38 | 148.08
| 12 | RIG | 2 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 3.12 / 10.26 | 187.82 | 335.9
| 13 | 532 | Drill-N-Ream | 5.375 | 2.625 | 5.375 / 1.25 | CET43 / CET43 | 47.34 / 0.40 / 10.66 | 8.45 | 344.35
| 14 |  | 26 Stands 4 1/2 Drill Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 40.74 / 51.40 | 2454.24 | 2798.59
| 15 | PG525-0037 | Agitator | 5.312 | 2.5 | 5.312 / 1.83 | CET43 / CET43 | 70.03 / 1.46 / 52.87 | 20.91 | 2819.5
| 16 |  | 33 Stands 4 1/2 Dril Pipe | 4.5 | 3.8 |  | CET43 / CET43 | 16.60 / 51.73 / 104.60 | 3116.43 | 5935.93
| 17 | [8 empty] | 5935.93
| 18 | PG525-0055 | Agitator (On Demand) | 5.312 | 2.5 | 5.312 / 1.83 | CET43 / CET43 | 68.37 / 1.46 / 106.06 | 21.39 | 5957.32
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M |  |  | 2569
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.12 TS HS88 .020 |  |  | PDCI / 6/7 8.8 | 4.00 / 2.12 |  | 0 | 5.62 | 200 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 1200 | 80 |  | 150-400 | 0.68 | FBH | Mud Lube
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV | HS88 |  | 0.02
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Positive Pulse |  |  | 1.28 |  |  | 1.122 | PDCI | UBHO | 2.5
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
|  |  |  | 0.5 |  |  |  |  | Yes
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Well: |  | Rommel 3H
|  |  |  | Longitude: |  | 96° 37' 52.247" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 91.00/110.09/127.00
Date In: |  | 07/14/2021 13:00 |  | SN: |  | MTR775044 |  |  |  | WOB Rotate (klbs): |  | 12.00
Date Out: |  | 07/15/2021 04:20 |  | Description: |  | 7/8 5.9 1.50 Stab HPO -.015 NBS 13 |  |  |  | WOB Slide (klbs): |  | 9.43
Depth In/Out(Usft): |  | 108.00 / 3523.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 97.57
Inc In/Out: |  | 0.17 / 9.19 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 862.67
Azi In/Out: |  | 323.38 / 111.44 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 1790
Total Drilled (Usft): |  | 3415 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 2151.72
%Slide (Ftg): |  | 10.83 |  | Bit to Bend (Usft): |  | 6.08 |  |  |  | Tq On Btm (kftlbs): |  | 5810.41
%Slide (Time): |  | 28.52 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 370 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 2.32 |  | Stab to Bit (Usft): |  | 2.31 |  |  |  | Bit Data
%Rotary (Ftg): |  | 89.17 |  | Kickpad OD (in): |  | 8.5 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 71.43 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 3045 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 5.81 |  | Length (Usft): |  | 37.55 |  |  |  | TFA: |  | 1.35
Total Drlg Hrs: |  | 8.13 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 3.68 / 15.33 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | 0-0-
Slide ROP (Usft/hr): |  | 159.48 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-3-CT-S-X-I-TD
Rot ROP (Usft/hr): |  | 524.1 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.016 |  |  |  | Drill Hrs: |  | 8.13
Avg ROP (Usft/hr): |  | 420.05 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.68
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
7 / 5 | 3 / 2 | 1 / 1 |  | 5.6/94.3 |  | 2 | 3 | 9.1 | 410 | WBM | 5.7 | 0.4 | 127
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
72 | [9 empty] | 5 |  | 5.00 / 1.33
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
U616S 1.35 |  |  |  | 38426 |  | 13.5 |  |  |  |  | 1.5 | 1.5
7/8 5.9 1.50 Stab HPO -.015 NBS 13 0.00 |  |  |  | MTR775044 |  | 8 |  |  |  |  | 37.55 | 39.05
13 Stab 0.00 |  |  |  | SD603251 |  | 8.125 | 3 |  |  |  | 6.34 | 45.39
NMPC 0.00 |  |  |  | SD55524 |  | 8 | 3.25 |  |  |  | 8.58 | 53.97
UBHO Sub UBHO Sub 0.00 |  |  |  | 775213 |  | 7.75 | 2.875 |  |  |  | 3.66 | 57.63
NMDC 0.00 |  |  |  | SD56120 |  | 8 | 3.25 |  |  |  | 28.83 | 86.46
NMDC 0.00 |  |  |  | SD55920 |  | 8 | 3.25 |  |  |  | 28.99 | 115.45
Crossover Sub 0.00 |  |  |  | SD117248 |  | 6.75 | 2.875 |  |  |  | 2.13 | 117.58
9 Jts HWDP 0.00 | [5 empty] | 5 | 3 |  |  |  | 274.62 | 392.2
-1.00 | [11 empty] | 392.2
Additional Comments
Reason POOH: TD Surface hole. POOH f/ Casing ops How did motor drain: Motor drained strong and was full of fluid Visual Wear: No visual wear was observed. Axial play in bearing was tight with little movement and approximately 1/16 inch play in thrust bearings Run description: Assembly drilled well and slides were yielding 5?s at best. In rotation it wanted to walk to the left off of a hole direction of 111. It dropped .4/100. Max Temp: 127 Stalls: 0 Motor Yield: 5?/100? Max Drilling Diff: 800 Average Drilling Diff: 500 Condition of bit: Bit graded 0-1-BT-G-X-I-NO-TD. A couple of broken cutters on the gauge
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Well: |  | Rommel 3H
|  |  |  | Longitude: |  | 96° 37' 52.247" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Brandon Parks
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 125.00/200.24/246.00
Date In: |  | 08/02/2021 14:00 |  | SN: |  | PPM800058 |  |  |  | WOB Rotate (klbs): |  | 25.00
Date Out: |  | 08/05/2021 02:45 |  | Description: |  | 7/8 5.9 2.00 Slick HPO -.014 |  |  |  | WOB Slide (klbs): |  | 18.17
Depth In/Out(Usft): |  | 3523.00 / 11022.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 78.00
Inc In/Out: |  | 9.19 / 21.31 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 847.58
Azi In/Out: |  | 111.44 / 151.10 |  | Lobes / Stages: |  | 7/8 / 5.9 |  |  |  | Off Btm Press (psi): |  | 4087.22
Total Drilled (Usft): |  | 7499 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4806.45
%Slide (Ftg): |  | 8.73 |  | Bit to Bend (Usft): |  | 6.04 |  |  |  | Tq On Btm (kftlbs): |  | 14481.55
%Slide (Time): |  | 52.72 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 655 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 800
Slide Hours: |  | 20.78 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 91.27 |  | Kickpad OD (in): |  | 8.188 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 47.29 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6844 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 18.64 |  | Length (Usft): |  | 37.56 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 39.42 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 9.62 / 60.75 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 31.52 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-CT-S-X-I-WT-TD
Rot ROP (Usft/hr): |  | 367.17 |  | Stator Vendor/Type/Fit: |  | Abaco / HPO / -0.014 |  |  |  | Drill Hrs: |  | 39.42
Avg ROP (Usft/hr): |  | 190.23 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 9.62
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
37 / 23 | 16 / 11 | 6 / 5 |  | 69/31 |  | 14 | 9 | 9.7 | 69000 | OBM | 9.2 | 0.4 | 246
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
64 | 60 | [10 empty] | 0.00 / 6.90
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
SPL613 1.49 |  |  |  | 56410 |  | 9.875 | 2 |  |  | 125 | 1.5 | 1.5
7/8 5.9 2.00 Slick HPO -.014 0.00 |  |  |  | PPM800058 |  | 8 | 2 |  |  | 100 | 37.56 | 39.06
NMPC 0.00 |  |  |  | SD54585 |  | 8 | 3.25 |  |  | 162.87 | 9.21 | 48.27
UBHO Sub 0.00 |  |  |  | 775225 |  | 7.75 | 3 |  |  | 150 | 3.97 | 52.24
NMDC 0.00 |  |  |  | SD53215 |  | 7.812 | 3.312 |  |  | 157.9 | 27.55 | 79.79
NMDC 0.00 |  |  |  | SD46074 |  | 8 | 3.312 |  |  | 151.3 | 28.75 | 108.54
Crossover Sub 0.00 |  |  |  | SD118447 |  | 6.75 | 2.875 |  |  | 100 | 2.55 | 111.09
6.5 DC 6 Jts 0.00 | [5 empty] | 6.5 | 2.375 |  |  | 95 | 187.23 | 298.32
HWDP 9 Jts 0.00 | [5 empty] | 5 | 3 |  |  | 43 | 274.85 | 573.17
Crossover Sub 0.00 |  |  |  | SD107702 |  | 6.5 | 2.875 |  |  | 95 | 2.67 | 575.84
DP 22 Stds 0.00 | [5 empty] | 5 | 3.5 |  |  | 19.6 | 2061.7 | 2637.54
Agitator 0.00 |  |  |  | PG675-0027 |  | 6.562 | 3.75 |  |  | 80 | 24.65 | 2662.19
-1.00 | [11 empty] | 2662.19
Additional Comments
Reason POOH: TD intermediate hole. POOH to log and casing ops How did motor drain: Motor drained fine. Visual Wear: None. Axial play in bearing was tight with little movement and approximately 1/16 inch play in thrust bearings Run description: Assembly drilled well and slides were yielding 7-8?s. Motor had a tendency to hang up about the 3-5? mark on most slides. GPM was reduced to try and mitigate issue. Max Temp: 246 Stalls: 0 Motor Yield: 7.5?/100? Max Drilling Diff: 900 Average Drilling Diff: 600 Condition of bit: Bit graded 0-1 -CT-S-X-I-WT-TD.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Well: |  | Rommel 3H
|  |  |  | Longitude: |  | 96° 37' 52.247" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 217.00/218.00/219.00
Date In: |  | 08/19/2021 08:30 |  | SN: |  | PPM250024 |  |  |  | WOB Rotate (klbs): |  | 13.00
Date Out: |  | 08/20/2021 16:00 |  | Description: |  | 6/7 8.8 2.25 TS HS88 .000 |  |  |  | WOB Slide (klbs): |  | 13.00
Depth In/Out(Usft): |  | 11022.00 / 11265.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 21.32 / 51.19 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 287.5
Azi In/Out: |  | 151.10 / 150.43 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 2000
Total Drilled (Usft): |  | 243 |  | Bend Angle: |  | 2.25 |  |  |  | On Btm Press (psi): |  | 2275
%Slide (Ftg): |  | 100.00 |  | Bit to Bend (Usft): |  | 4.05 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 99.98 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 243 |  | Bearing Gap (in): |  | 0.1 |  |  |  | Avg Diff Press (psi): |  | 1200
Slide Hours: |  | 21.08 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | -0.00 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 0.00 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 0 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0 |  | Length (Usft): |  | 33.07 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 21.08 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 4
Circ/BRT Hrs: |  | 2.42 / 31.50 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 11.53 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 1-1-NO-A-X-I-NO-BHA
Rot ROP (Usft/hr): |  | 0 |  | Stator Vendor/Type/Fit: |  | PV / HS88 / 0.000 |  |  |  | Drill Hrs: |  | 21.08
Avg ROP (Usft/hr): |  | 11.53 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.42
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
62 / 37 | 28 / 19 | 7 / 6 |  | 71/29 |  | 25 | 12 | 10.1 | 70000 | OBM | 11.6 | 0.4 | 219
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
61 | 57 | [10 empty] | 0.00 / 17.86
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13628581 |  | 6.75 | 2 |  |  | 50 | 1 | 1
BTI Valve 0.00 |  |  |  | BTI1 |  | 4.875 | 2 |  |  | 49.26 | 2.03 | 3.03
6/7 8.8 2.25 TS HS88 .000 0.00 |  |  |  | PPM250024 |  | 5.5 | 2 |  |  | 45.36 | 33.07 | 36.1
NMPC 0.00 |  |  |  | GT50-10-637 |  | 5 | 2.688 |  |  | 54.53 | 9.17 | 45.27
UBHO 0.00 |  |  |  | 500046 |  | 5.25 | 2.5 |  |  | 45.1 | 3.88 | 49.15
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-606 |  | 5.25 | 2.688 |  |  | 47.85 | 31.35 | 80.5
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-458 |  | 5.25 | 2.688 |  |  | 48.78 | 30.75 | 111.25
Filter Sub 0.00 |  |  |  | GT5033743 |  | 5 | 2.688 |  |  | 35.35 | 4.95 | 116.2
Crossover 0.00 |  |  |  | GT52331429 |  | 5.25 | 2.688 |  |  | 48.82 | 3.38 | 119.58
Additional Comments
Motor Drain and No Visual Signs of Wear Kick off cement plug and time drilled for 19. Motor slide with 6-20 WOB and 200-600 Diff @ 50-70/hr. POOH when needing 6.1 to land.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Well: |  | Rommel 3H
|  |  |  | Longitude: |  | 96° 37' 52.247" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | ROP / Formation |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Josh Ray |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 243.00/283.00/311.00
Date In: |  | 08/20/2021 17:00 |  | SN: |  | PPM250012 |  |  |  | WOB Rotate (klbs): |  | 28.00
Date Out: |  | 08/25/2021 01:15 |  | Description: |  | 6/7 8.8 2.12 TS HS88 .004 |  |  |  | WOB Slide (klbs): |  | 29.51
Depth In/Out(Usft): |  | 11265.00 / 17945.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 75.00
Inc In/Out: |  | 51.20 / 86.89 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 400
Azi In/Out: |  | 150.43 / 152.61 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4462.57
Total Drilled (Usft): |  | 6680 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5119.01
%Slide (Ftg): |  | 12.65 |  | Bit to Bend (Usft): |  | 4.08 |  |  |  | Tq On Btm (kftlbs): |  | 10043.01
%Slide (Time): |  | 26.77 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 845 |  | Bearing Gap (in): |  | 0.09 |  |  |  | Avg Diff Press (psi): |  | 1200
Slide Hours: |  | 18.2 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 87.35 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 73.22 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 5835 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 49.78 |  | Length (Usft): |  | 33.07 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 67.98 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 10.72 / 104.25 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 46.43 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 117.22 |  | Stator Vendor/Type/Fit: |  | PV / HS88 / 0.004 |  |  |  | Drill Hrs: |  | 67.98
Avg ROP (Usft/hr): |  | 98.26 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 10.72
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
62 / 37 | 28 / 19 | 7 / 6 |  | 71/29 |  | 25 | 12 | 10.1 | 70000 | OBM | 11.6 | 0.4 | 311
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
61 | 57 | [8 empty] | 8 |  | 0.00 / 15.84
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13628581 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 8.8 2.12 TS HS88 .004 0.00 |  |  |  | PPM250012 |  | 5.5 | 2 |  |  | 45.36 | 33.07 | 34.07
BTI Valve 0.00 |  |  |  | BTI1 |  | 4.875 | 2 |  |  | 49.26 | 2.03 | 36.1
NMPC 0.00 |  |  |  | GT50-10-637 |  | 5 | 2.688 |  |  | 54.53 | 9.17 | 45.27
UBHO 0.00 |  |  |  | 500046 |  | 5.25 | 2.5 |  |  | 45.1 | 3.88 | 49.15
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-606 |  | 5.25 | 2.688 |  |  | 47.85 | 31.35 | 80.5
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-458 |  | 5.25 | 2.688 |  |  | 48.78 | 30.75 | 111.25
Tomax 0.00 |  |  |  | A52137 |  | 5.25 | 2.5 |  |  | 55.49 | 18.02 | 129.27
Crossover 0.00 |  |  |  | GT52331429 |  | 5.25 | 2.688 |  |  | 48.82 | 3.38 | 132.65
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | RIG |  | 4.5 | 3.8 |  |  | 16.6 | 187.82 | 320.47
Drill-N-Ream 0.00 |  |  |  | 532 |  | 5.375 | 2.625 |  |  | 47.34 | 8.45 | 328.92
26 Stands 4 1/2 Drill Pipe 0.00 | [5 empty] | 4.5 | 3.8 |  |  | 16.6 | 2454.24 | 2783.16
Agitator 0.00 |  |  |  | PG525-0051 |  | 5.312 | 2.5 |  |  | 70.03 | 21.42 | 2804.58
-1.00 | [11 empty] | 2804.58
Additional Comments
Reason POOH: ROP slowed to 30 FPH. Although this was a trip before TD, a trip was planned in the lateral due to the latera length. How did motor drain: Motor drained normal with the rotary. Visual Wear: None. Run description: BHA drilled 175 FPH until the last 16 hours. During rotation the assembly tracked great and sliding was 90-60 FPH until the ROP slowed the last 16 hours. Max Temp: 311 Stalls: 0 Motor Yield: 4 to 15 DLS in the lateral, variance was due to formation. When the wellbore approached the Ash buffer above motor yields fell off to 4?s. When the wellbore was over 8? from the Ash buffer slides yielded 15. Max Drilling Diff: 1100 Average Drilling Diff: 850 Bit was a 1-1 with no dull characteristic
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 6
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Well: |  | Rommel 3H
|  |  |  | Longitude: |  | 96° 37' 52.247" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Hole Conditions |  |  | BHA # |  | 6
|  |  |  | Lead DD: |  | Jesse Taylor |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 08/25/2021 02:20 |  | SN: |  | PPM250004 |  |  |  | WOB Rotate (klbs):
Date Out: |  | 08/26/2021 04:00 |  | Description: |  | 6/7 8.8 2.12 TS HS88 .026 |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 17945.00 / 17945.00 |  | Make: |  | PDCI |  |  |  | RPM:
Inc In/Out: |  | 86.89 / 86.89 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm):
Azi In/Out: |  | 152.61 / 152.61 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi):
Total Drilled (Usft): |  | 0 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi):
%Slide (Ftg): |  | 0 |  | Bit to Bend (Usft): |  | 4.06 |  |  |  | Tq On Btm (kftlbs):
%Slide (Time): |  | 0 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 0 |  | Bearing Gap (in): |  | 0.09 |  |  |  | Avg Diff Press (psi): |  | 1200
Slide Hours: |  | 0 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 0 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 0 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 0 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 0 |  | Length (Usft): |  | 32.92 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 0.00 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 0.25 / 25.67 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In:
Slide ROP (Usft/hr): |  | 0 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 0 |  | Stator Vendor/Type/Fit: |  | PV / HS88 / 0.024 |  |  |  | Drill Hrs: |  | 0.00
Avg ROP (Usft/hr): |  | 0 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 0.25
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
52 / 31 | 23 / 15 | 6 / 5 |  | 73/27 |  | 21 | 10 | 10.5 | 54000 | OBM | 13.8 | 0.4
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 57
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618580 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 8.8 2.12 TS HS88 .026 0.00 |  |  |  | PPM250004 |  | 5.5 | 2 |  |  | 45.56 | 32.92 | 33.92
BTI Valve 0.00 |  |  |  | BTI1 |  | 4.875 | 2 |  |  | 49.26 | 2.03 | 35.95
NMPC 0.00 |  |  |  | GT50-10-637 |  | 5 | 2.688 |  |  | 54.53 | 9.17 | 45.12
UBHO 0.00 |  |  |  | 500046 |  | 5.25 | 2.5 |  |  | 45.1 | 3.88 | 49
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-606 |  | 5.25 | 2.688 |  |  | 47.85 | 31.35 | 80.35
NMPC 0.00 |  |  |  | GT50-10-479 |  | 5 | 2.688 |  |  | 50.66 | 9.87 | 90.22
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-458 |  | 5.25 | 2.688 |  |  | 48.78 | 30.75 | 120.97
Tomax 0.00 |  |  |  | A52137 |  | 5.25 | 2.5 |  |  | 55.49 | 18.02 | 138.99
Crossover 0.00 |  |  |  | GT52331429 |  | 5.25 | 2.688 |  |  | 48.82 | 3.38 | 142.37
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | RIG |  | 4.5 | 3.8 |  |  | 16.6 | 187.82 | 330.19
Drill-N-Ream 0.00 |  |  |  | 532 |  | 5.375 | 2.625 |  |  | 47.34 | 8.45 | 338.64
26 Stands 4 1/2 Drill Pipe 0.00 | [5 empty] | 4.5 | 3.8 |  |  | 16.6 | 2454.24 | 2792.88
Agitator 0.00 |  |  |  | PG525-0057 |  | 5.312 | 2.5 |  |  | 70.03 | 21.95 | 2814.83
33 Stands 4 1/2 Dril Pipe 0.00 | [5 empty] | 4.5 | 3.8 |  |  | 16.6 | 3116.43 | 5931.26
Agitator (On Demand) 0.00 |  |  |  | PG525-0054 |  | 5.312 | 2.5 |  |  | 68.37 | 21.94 | 5953.2
-1.00 | [11 empty] | 5953.2
Additional Comments
Reason POOH: BHA pressured up when attempting to circulate the kill mud out of the hole. How did motor drain: Motor drained normal with rotary. Run description: The BHA tested file after picking up both agitators. Then the BHA pressured up at 11,022. When POOH the BHA was still pressuring up after laying down both agitators. At surface there was cement plugged up around the mule shoe in the UBHO. (Pic UBHO with the bit pics) Max Temp: 240 (motor was laid down due to high temp, then coming to surface) Stalls: 0 Motor Yield: N/A Max Drilling Diff: N/A Average Drilling Diff: N/A Bit was a 1-1 with no dull characteristic and re-ran on BHA 6
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 7
|  |  |  | Job # |  | LTX1125821 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31159 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 13' 49.831" N |  |  | Well: |  | Rommel 3H
|  |  |  | Longitude: |  | 96° 37' 52.247" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 7
|  |  |  | Lead DD: |  | Jesse Taylor Josh Ray |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 312.00/324.85/333.00
Date In: |  | 08/26/2021 06:00 |  | SN: |  | PPM250016 |  |  |  | WOB Rotate (klbs): |  | 29.00
Date Out: |  | 08/29/2021 06:00 |  | Description: |  | 6/7 8.8 2.12 TS HS88 .020 |  |  |  | WOB Slide (klbs): |  | 27.09
Depth In/Out(Usft): |  | 17945.00 / 20514.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 74.10
Inc In/Out: |  | 86.89 / 86.97 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 339.49
Azi In/Out: |  | 152.61 / 152.22 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 4826.86
Total Drilled (Usft): |  | 2569 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 5449.82
%Slide (Ftg): |  | 5.76 |  | Bit to Bend (Usft): |  | 4 |  |  |  | Tq On Btm (kftlbs): |  | 988.63
%Slide (Time): |  | 16.87 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 148 |  | Bearing Gap (in): |  | 0.09 |  |  |  | Avg Diff Press (psi): |  | 1200
Slide Hours: |  | 4.6 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 94.24 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 83.14 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 2421 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 22.67 |  | Length (Usft): |  | 33.33 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 27.27 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 5
Circ/BRT Hrs: |  | 17.02 / 72.00 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In:
Slide ROP (Usft/hr): |  | 32.17 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 106.79 |  | Stator Vendor/Type/Fit: |  | PV / HS88 / 0.020 |  |  |  | Drill Hrs: |  | 27.27
Avg ROP (Usft/hr): |  | 94.21 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 17.02
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
52 / 31 | 23 / 15 | 6 / 5 |  | 73/27 |  | 21 | 10 | 10.5 | 54000 | OBM | 13.8 | 0.4 | 333
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
68 | 57 | [10 empty] | 0.00 / 3.17
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13618580 |  | 6.75 | 2 |  |  | 50 | 1 | 1
6/7 8.8 2.12 TS HS88 .020 0.00 |  |  |  | PPM250016 |  | 5.5 | 2 |  |  | 45.01 | 33.33 | 34.33
BTI Valve 0.00 |  |  |  | BTI2 |  | 4.875 | 2 |  |  | 49.26 | 1.62 | 35.95
NMPC 0.00 |  |  |  | GT50-10-637 |  | 5 | 2.688 |  |  | 54.53 | 9.17 | 45.12
UBHO 0.00 |  |  |  | 500046 |  | 5.25 | 2.5 |  |  | 45.1 | 3.88 | 49
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT52-30-606 |  | 5.25 | 2.688 |  |  | 47.85 | 31.35 | 80.35
NMPC 0.00 |  |  |  | GT50-10-479 |  | 5 | 2.688 |  |  | 50.66 | 9.87 | 90.22
NMDC (NO HARDBANDING) 0.00 |  |  |  | GT51-30-618 |  | 5.125 | 2.688 |  |  | 47.86 | 31.34 | 121.56
Filter Sub 0.00 |  |  |  | GT5033740 |  | 5 | 2.688 |  |  | 34.18 | 5.12 | 126.68
Tomax 0.00 |  |  |  | A52137 |  | 5.25 | 2.5 |  |  | 55.49 | 18.02 | 144.7
Crossover 0.00 |  |  |  | GT52331429 |  | 5.25 | 2.688 |  |  | 48.82 | 3.38 | 148.08
2 Stands 4 1/2 Drill Pipe 0.00 |  |  |  | RIG |  | 4.5 | 3.8 |  |  | 16.6 | 187.82 | 335.9
Drill-N-Ream 0.00 |  |  |  | 532 |  | 5.375 | 2.625 |  |  | 47.34 | 8.45 | 344.35
26 Stands 4 1/2 Drill Pipe 0.00 | [5 empty] | 4.5 | 3.8 |  |  | 16.6 | 2454.24 | 2798.59
Agitator 0.00 |  |  |  | PG525-0037 |  | 5.312 | 2.5 |  |  | 70.03 | 20.91 | 2819.5
33 Stands 4 1/2 Dril Pipe 0.00 | [5 empty] | 4.5 | 3.8 |  |  | 16.6 | 3116.43 | 5935.93
-1.00 | [11 empty] | 5935.93
Agitator (On Demand) 0.00 |  |  |  | PG525-0055 |  | 5.312 | 2.5 |  |  | 68.37 | 21.39 | 5957.32
Additional Comments
Reason POOH: TD well How did motor drain: Motor drained above the rotary while hanging from top drive. When turning with the rotary a little fluid was still in the motor. After Four rotations the motor was fully drained. Visual Wear: None. Run description: BHA drilled in the same ROP range as the previous BHA at the start of the lateral. Sliding was easy and the BHA tracked very good. 80 RPM with 850 diff built .5 to 1.0 in rotation. 70 RPM with 850 diff the BHA built 1.8 in rotation. 70 RPM with 600 diff dropped .5 to 1.2 in rotation. Max Temp: 333 Stalls: 0 Motor Yield: 4 to 15 DLS in the lateral, variance was due to formation. When the wellbore approached the Ash buffer above motor yields fell off to 4?s. When the wellbore was over 8? from the Ash buffer slides yielded 15. Max Drilling Diff: 850 Average Drilling Diff: 600 Bit was a 1-1 with damage to the matrix surrounding the up ream cutter. The matrix for the up ream cutter was delimited ? of an inch above the cutter pocket. The matrix for the cutter pocket was also delimited. This bit was a rerun and the cutter was missing on the previous run, however no damage to the matrix was present prior to rerun. The last few hundred feet of the lateral behaved erratically, this could be related to the gauge pad damage around the up ream cutter.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3415
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 370
Well Name: |  |  |  |  | Rommel 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 72.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.56 |  | Rotate: |  | 3045
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
07/14/2021 | 13:00 | 13:28 | 0.46667 | 108 | 270 | 162 | Rotate |  | 198 | 0.31 | 323.38 | 198 | 0.43 | -0.32 | 0.43 | 0.16 |  |  | 5 | 50 | 500 | 2000 | 347.14 | 550 | 290 | 260 | 91 | 40 | 40 | 40
07/14/2021 | 13:40 | 13:45 | 0.083333 | 270 | 302 | 32 | Rotate |  | 289 | 0.17 | 338.7 | 289 | 0.75 | -0.52 | 0.75 | 0.17 |  |  | 5 | 80 | 665 | 5000 | 384 | 900 | 750 | 150 | 93 | 40 | 40 | 40
07/14/2021 | 14:17 | 14:21 | 0.066667 | 302 | 361 | 59 | Rotate | Drilling Parameters WOB: 5; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 665; Drilling Parameters Tq: 3000; Drilling Parameters ROP: 885 | 900 | 750 | 150 | 93 | 40 | 40 | 40
07/14/2021 | 14:25 | 14:43 | 0.3 | 361 | 485 | 124 | Rotate |  | 413 | 0.27 | 1.14 | 413 | 1.22 | -0.58 | 1.22 | 0.1 |  |  | 5 | 100 | 715 | 3000 | 744 | 950 | 850 | 100 | 95 | 65 | 60 | 55
07/14/2021 | 14:43 | 14:56 | 0.21667 | 485 | 579 | 94 | Rotate |  | 507 | 0.1 | 29.53 | 507 | 1.51 | -0.53 | 1.51 | 0.2 |  |  | 5 | 100 | 715 | 3000 | 433.85 | 1200 | 930 | 270 | 97 | 65 | 60 | 55
07/14/2021 | 15:00 | 15:08 | 0.13333 | 579 | 673 | 94 | Rotate |  | 601 | 0.2 | 84.04 | 601 | 1.6 | -0.33 | 1.6 | 0.17 |  |  | 5 | 100 | 715 | 3000 | 705 | 1200 | 930 | 270 | 97 | 65 | 60 | 55
07/14/2021 | 15:12 | 15:21 | 0.15 | 673 | 767 | 94 | Rotate |  | 695 | 0.81 | 74.28 | 694.99 | 1.8 | 0.47 | 1.8 | 0.65 |  |  | 5 | 100 | 715 | 3000 | 626.67 | 1200 | 930 | 270 | 97 | 65 | 60 | 55
07/14/2021 | 15:25 | 15:34 | 0.15 | 767 | 861 | 94 | Rotate |  | 789 | 0.87 | 95.23 | 788.98 | 1.91 | 1.83 | 1.91 | 0.33 |  |  | 5 | 100 | 715 | 3000 | 626.67 | 1200 | 930 | 270 | 97 | 65 | 60 | 55
07/14/2021 | 15:37 | 15:47 | 0.16667 | 861 | 956 | 95 | Rotate |  | 884 | 0.68 | 103.73 | 883.97 | 1.71 | 3.09 | 1.71 | 0.23 |  |  | 7 | 100 | 715 | 3000 | 570 | 1200 | 930 | 270 | 99 | 65 | 60 | 55
07/14/2021 | 15:51 | 16:01 | 0.16667 | 956 | 1049 | 93 | Rotate |  | 977 | 0.6 | 92.05 | 976.97 | 1.56 | 4.11 | 1.56 | 0.16 |  |  | 7 | 100 | 715 | 3000 | 558 | 1200 | 930 | 270 | 99 | 65 | 60 | 55
07/14/2021 | 16:05 | 16:12 | 0.11667 | 1049 | 1143 | 94 | Rotate |  | 1071 | 0.27 | 110.88 | 1070.97 | 1.47 | 4.81 | 1.47 | 0.38 |  |  | 7 | 100 | 900 | 5000 | 805.71 | 2100 | 1750 | 350 | 99 | 70 | 65 | 60
07/14/2021 | 16:16 | 16:20 | 0.066667 | 1143 | 1158 | 15 | Slide | TTF: 110; Drilling Parameters WOB: 5; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 225 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 16:20 | 16:26 | 0.1 | 1158 | 1238 | 80 | Rotate |  | 1166 | 0.76 | 129.55 | 1165.96 | 0.98 | 5.51 | 0.98 | 0.54 |  |  | 7 | 100 | 900 | 5000 | 800 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 16:31 | 16:36 | 0.083333 | 1238 | 1253 | 15 | Slide | TTF: 110; Drilling Parameters WOB: 7; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 180 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 16:36 | 16:43 | 0.11667 | 1253 | 1331 | 78 | Rotate |  | 1259 | 1.36 | 120.17 | 1258.94 | 0.04 | 6.94 | 0.04 | 0.67 |  |  | 7 | 100 | 900 | 5000 | 668.57 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 16:48 | 16:53 | 0.083333 | 1331 | 1351 | 20 | Slide | TTF: 110; Drilling Parameters WOB: 7; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 240 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 16:53 | 16:59 | 0.1 | 1351 | 1426 | 75 | Rotate |  | 1354 | 2.07 | 118.8 | 1353.9 | -1.36 | 9.42 | -1.36 | 0.75 |  |  | 7 | 100 | 900 | 5000 | 750 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 17:04 | 17:09 | 0.083333 | 1426 | 1446 | 20 | Slide | TTF: 110; Drilling Parameters WOB: 7; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 240 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 17:09 | 17:15 | 0.1 | 1446 | 1519 | 73 | Rotate |  | 1447 | 3.26 | 111.32 | 1446.8 | -3.13 | 13.35 | -3.13 | 1.33 |  |  | 7 | 100 | 900 | 5000 | 730 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 17:20 | 17:24 | 0.066667 | 1519 | 1534 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 7; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 225 | 2100 | 1750 | 350 | 100 | 70 | 65 | 60
07/14/2021 | 17:24 | 17:31 | 0.11667 | 1534 | 1614 | 80 | Rotate |  | 1542 | 4.5 | 111.66 | 1541.58 | -5.48 | 19.33 | -5.48 | 1.31 |  |  | 10 | 100 | 900 | 5000 | 685.71 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 17:36 | 17:41 | 0.083333 | 1614 | 1629 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 180 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 17:41 | 17:48 | 0.11667 | 1629 | 1707 | 78 | Rotate |  | 1635 | 5.33 | 112.56 | 1634.24 | -8.49 | 26.71 | -8.49 | 0.9 |  |  | 10 | 100 | 900 | 5000 | 668.57 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 17:53 | 17:59 | 0.1 | 1707 | 1722 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 17:59 | 18:08 | 0.15 | 1722 | 1801 | 79 | Rotate |  | 1729 | 6.09 | 113.29 | 1727.77 | -12.13 | 35.32 | -12.13 | 0.81 |  |  | 15 | 100 | 900 | 5000 | 526.67 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 18:16 | 18:21 | 0.083333 | 1801 | 1821 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 240 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 18:21 | 18:29 | 0.13333 | 1821 | 1894 | 73 | Rotate |  | 1822 | 7.04 | 114.59 | 1820.16 | -16.46 | 45.04 | -16.46 | 1.03 |  |  | 15 | 100 | 900 | 5000 | 547.5 | 2200 | 1800 | 400 | 105 | 70 | 65 | 60
07/14/2021 | 18:34 | 18:40 | 0.1 | 1894 | 1909 | 15 | Slide | TTF: -20; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 18:40 | 18:47 | 0.11667 | 1909 | 1989 | 80 | Rotate |  | 1917 | 7.77 | 112.92 | 1914.37 | -21.38 | 56.25 | -21.38 | 0.8 |  |  | 15 | 100 | 900 | 5000 | 685.71 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 18:52 | 18:58 | 0.1 | 1989 | 2004 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 18:58 | 19:05 | 0.11667 | 2004 | 2084 | 80 | Rotate |  | 2012 | 8.11 | 114.64 | 2008.46 | -26.68 | 68.25 | -26.68 | 0.44 |  |  | 15 | 100 | 900 | 5000 | 685.71 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 19:13 | 19:20 | 0.11667 | 2084 | 2104 | 20 | Slide | TTF: -20; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 171.43 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 19:20 | 19:32 | 0.2 | 2104 | 2178 | 74 | Rotate |  | 2106 | 8.81 | 113.04 | 2101.43 | -32.26 | 80.9 | -32.26 | 0.79 |  |  | 15 | 100 | 900 | 5000 | 370 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 19:37 | 19:44 | 0.11667 | 2178 | 2198 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 171.43 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 19:44 | 19:46 | 0.033333 | 2198 | 2217 | 19 | Rotate |  | 2200 | 9.8 | 109.52 | 2194.2 | -37.75 | 95.07 | -37.75 | 1.21 |  |  | 15 | 100 | 900 | 5000 | 570 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 20:40 | 20:47 | 0.11667 | 2217 | 2272 | 55 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 471.43 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 20:52 | 20:59 | 0.11667 | 2272 | 2287 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 128.57 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 20:59 | 21:08 | 0.15 | 2287 | 2365 | 78 | Rotate |  | 2293 | 10.84 | 107.76 | 2285.69 | -43.06 | 110.86 | -43.06 | 1.17 |  |  | 18 | 100 | 900 | 5000 | 520 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 21:13 | 21:19 | 0.1 | 2365 | 2380 | 15 | Slide | TTF: 70; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2400 | 2000 | 400 | 113 | 105 | 100 | 95
07/14/2021 | 21:19 | 21:30 | 0.18333 | 2380 | 2459 | 79 | Rotate |  | 2387 | 10.73 | 111.73 | 2378.03 | -49 | 127.4 | -49 | 0.8 |  |  | 18 | 100 | 900 | 5000 | 430.91 | 2400 | 2000 | 400 | 122 | 105 | 100 | 95
07/14/2021 | 21:35 | 21:43 | 0.13333 | 2459 | 2553 | 94 | Rotate |  | 2481 | 10.69 | 112.44 | 2470.39 | -55.56 | 143.59 | -55.56 | 0.15 |  |  | 12 | 100 | 900 | 5000 | 705 | 2400 | 2000 | 400 | 122 | 105 | 100 | 95
07/14/2021 | 21:48 | 21:59 | 0.18333 | 2553 | 2647 | 94 | Rotate |  | 2575 | 10.32 | 110.42 | 2562.82 | -61.83 | 159.54 | -61.83 | 0.56 |  |  | 16 | 100 | 900 | 9329 | 512.73 | 2400 | 2000 | 400 | 122 | 105 | 100 | 95
07/14/2021 | 22:04 | 22:13 | 0.15 | 2647 | 2741 | 94 | Rotate |  | 2669 | 9.97 | 109.93 | 2655.35 | -67.54 | 175.08 | -67.54 | 0.38 |  |  | 27 | 100 | 900 | 9329 | 626.67 | 2600 | 2200 | 400 | 122 | 105 | 100 | 95
07/14/2021 | 22:18 | 22:27 | 0.15 | 2741 | 2835 | 94 | Rotate |  | 2763 | 9.2 | 107.55 | 2748.04 | -72.58 | 189.89 | -72.58 | 0.92 |  |  | 32 | 100 | 900 | 9329 | 626.67 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 22:32 | 22:40 | 0.13333 | 2835 | 2855 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 22:40 | 22:53 | 0.21667 | 2855 | 2929 | 74 | Rotate |  | 2857 | 9.09 | 107.44 | 2840.84 | -77.07 | 204.14 | -77.07 | 0.12 |  |  | 25 | 100 | 900 | 9329 | 341.54 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 22:58 | 23:06 | 0.13333 | 2929 | 2949 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 23:06 | 23:16 | 0.16667 | 2949 | 3024 | 75 | Rotate |  | 2952 | 9.3 | 109.74 | 2934.62 | -81.91 | 218.53 | -81.91 | 0.45 |  |  | 30 | 100 | 900 | 9329 | 450 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 23:21 | 23:30 | 0.15 | 3024 | 3044 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 23:30 | 23:38 | 0.13333 | 3044 | 3118 | 74 | Rotate |  | 3046 | 9.75 | 110.2 | 3027.32 | -87.23 | 233.15 | -87.23 | 0.49 |  |  | 30 | 100 | 900 | 10420 | 555 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 23:43 | 23:51 | 0.13333 | 3118 | 3138 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/14/2021 | 23:51 | 24:00 | 0.15 | 3138 | 3211 | 73 | Rotate |  | 3139 | 9.73 | 111.92 | 3118.98 | -92.88 | 247.83 | -92.88 | 0.31 |  |  | 30 | 100 | 900 | 10420 | 486.67 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/15/2021 | 00:05 | 00:15 | 0.16667 | 3211 | 3226 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 90 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/15/2021 | 00:15 | 00:25 | 0.16667 | 3226 | 3305 | 79 | Rotate |  | 3233 | 9.06 | 111.75 | 3211.72 | -98.59 | 262.07 | -98.59 | 0.71 |  |  | 30 | 100 | 900 | 10500 | 474 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/15/2021 | 00:30 | 00:39 | 0.15 | 3305 | 3325 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2600 | 2200 | 400 | 123 | 105 | 100 | 95
07/15/2021 | 00:39 | 00:49 | 0.16667 | 3325 | 3398 | 73 | Rotate |  | 3326 | 9.01 | 109.77 | 3303.57 | -103.76 | 275.72 | -103.76 | 0.34 |  |  | 32 | 100 | 900 | 10500 | 438 | 2700 | 2300 | 400 | 123 | 120 | 115 | 110
07/15/2021 | 00:54 | 01:03 | 0.15 | 3398 | 3418 | 20 | Slide | TTF: 60; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 133.33 | 2700 | 2300 | 400 | 123 | 120 | 115 | 110
07/15/2021 | 01:03 | 01:23 | 0.33333 | 3418 | 3523 | 105 | Rotate |  | 3451 | 9.26 | 111.97 | 3426.98 | -110.84 | 294.26 | -110.84 | 0.34 |  |  | 32 | 100 | 900 | 10500 | 315 | 2700 | 2300 | 400 | 127 | 120 | 115 | 110

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7499
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 655
Well Name: |  |  |  |  | Rommel 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 64.00 / 60.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.56 |  | Rotate: |  | 6844
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/02/2021 | 18:30 | 18:50 | 0.33333 | 3523 | 3612 | 89 | Rotate |  | 3538 | 9.17 | 111.33 | 3512.86 | -115.98 | 307.21 | -115.98 | 0.16 |  |  | 20 | 60 | 550 | 6000 | 267 | 12000 | 1700 | 10300 | 125 | 155 | 145 | 135
08/02/2021 | 18:50 | 18:55 | 0.083333 | 3612 | 3624 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters RPM: 60; Drilling Parameters FLOW: 550; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 144 | 12000 | 1700 | 10300 | 125 | 155 | 145 | 135
08/02/2021 | 18:55 | 19:05 | 0.16667 | 3624 | 3696 | 72 | Rotate |  | 3632 | 8.31 | 121.5 | 3605.77 | -122.25 | 319.98 | -122.25 | 1.88 |  |  | 20 | 80 | 725 | 8000 | 432 | 3300 | 2700 | 600 | 125 | 155 | 145 | 135
08/02/2021 | 19:10 | 19:15 | 0.083333 | 3696 | 3706 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 725; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 120 | 3300 | 2700 | 600 | 130 | 155 | 145 | 135
08/02/2021 | 19:15 | 19:20 | 0.083333 | 3706 | 3716 | 10 | Slide | TTF: -20; Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 725; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 120 | 3300 | 2700 | 600 | 130 | 155 | 145 | 135
08/02/2021 | 19:20 | 19:30 | 0.16667 | 3716 | 3790 | 74 | Rotate |  | 3726 | 9.38 | 115.82 | 3698.66 | -129.14 | 332.67 | -129.14 | 1.47 |  |  | 20 | 80 | 725 | 8000 | 444 | 3300 | 2700 | 600 | 130 | 155 | 145 | 135
08/02/2021 | 19:35 | 19:40 | 0.083333 | 3790 | 3883 | 93 | Rotate |  | 3819 | 9.9 | 111.35 | 3790.34 | -135.35 | 346.94 | -135.35 | 0.98 |  |  | 25 | 80 | 725 | 8000 | 1116 | 3300 | 2700 | 600 | 130 | 155 | 145 | 135
08/02/2021 | 19:45 | 19:50 | 0.083333 | 3883 | 3977 | 94 | Rotate |  | 3913 | 10.17 | 111.79 | 3882.91 | -141.37 | 362.17 | -141.37 | 0.3 |  |  | 30 | 80 | 820 | 9000 | 1128 | 3900 | 3300 | 600 | 130 | 155 | 145 | 135
08/02/2021 | 19:55 | 20:05 | 0.16667 | 3977 | 4071 | 94 | Rotate |  | 4007 | 10.25 | 111.21 | 3975.42 | -147.48 | 377.67 | -147.48 | 0.14 |  |  | 30 | 80 | 820 | 9000 | 564 | 3900 | 3300 | 600 | 138 | 155 | 145 | 135
08/02/2021 | 20:10 | 20:15 | 0.083333 | 4071 | 4166 | 95 | Rotate |  | 4102 | 10.06 | 113.58 | 4068.93 | -153.86 | 393.16 | -153.86 | 0.48 |  |  | 30 | 80 | 820 | 9000 | 1140 | 3900 | 3300 | 600 | 138 | 155 | 145 | 135
08/02/2021 | 20:20 | 20:22 | 0.033333 | 4166 | 4176 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 300 | 3900 | 3300 | 600 | 138 | 155 | 145 | 135
08/02/2021 | 20:22 | 20:25 | 0.05 | 4176 | 4186 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 820; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 200 | 3900 | 3300 | 600 | 138 | 155 | 145 | 135
08/02/2021 | 20:25 | 20:35 | 0.16667 | 4186 | 4259 | 73 | Rotate |  | 4195 | 11.11 | 113.5 | 4160.35 | -160.68 | 408.82 | -160.68 | 1.13 |  |  | 30 | 80 | 820 | 9000 | 438 | 3900 | 3300 | 600 | 138 | 155 | 145 | 135
08/02/2021 | 20:40 | 20:50 | 0.16667 | 4259 | 4353 | 94 | Rotate |  | 4289 | 11.42 | 111.41 | 4252.54 | -167.69 | 425.79 | -167.69 | 0.55 |  |  | 30 | 80 | 870 | 9000 | 564 | 3900 | 3300 | 600 | 138 | 165 | 155 | 145
08/02/2021 | 20:55 | 21:00 | 0.083333 | 4353 | 4446 | 93 | Rotate |  | 4382 | 11.08 | 112.44 | 4343.75 | -174.46 | 442.62 | -174.46 | 0.42 |  |  | 30 | 80 | 870 | 9000 | 1116 | 3900 | 3300 | 600 | 138 | 165 | 155 | 145
08/02/2021 | 21:05 | 21:15 | 0.16667 | 4446 | 4540 | 94 | Rotate |  | 4476 | 11.16 | 111.87 | 4435.98 | -181.29 | 459.41 | -181.29 | 0.14 |  |  | 30 | 80 | 870 | 9000 | 564 | 3900 | 3300 | 600 | 138 | 165 | 155 | 145
08/02/2021 | 21:20 | 21:25 | 0.083333 | 4540 | 4635 | 95 | Rotate |  | 4571 | 10.92 | 109.62 | 4529.23 | -187.74 | 476.42 | -187.74 | 0.52 |  |  | 30 | 80 | 870 | 9000 | 1140 | 4200 | 3400 | 800 | 154 | 165 | 155 | 145
08/02/2021 | 21:30 | 21:35 | 0.083333 | 4635 | 4730 | 95 | Rotate |  | 4666 | 10.4 | 108.74 | 4622.59 | -193.52 | 493.01 | -193.52 | 0.57 |  |  | 30 | 80 | 870 | 9000 | 1140 | 4200 | 3400 | 800 | 154 | 165 | 155 | 145
08/02/2021 | 21:40 | 21:50 | 0.16667 | 4730 | 4823 | 93 | Rotate |  | 4759 | 10.18 | 108.84 | 4714.09 | -198.87 | 508.74 | -198.87 | 0.24 |  |  | 30 | 80 | 870 | 9000 | 558 | 4200 | 3400 | 800 | 154 | 165 | 155 | 145
08/02/2021 | 21:55 | 22:00 | 0.083333 | 4823 | 4917 | 94 | Rotate |  | 4853 | 9.64 | 107.04 | 4806.69 | -203.86 | 524.13 | -203.86 | 0.66 |  |  | 30 | 80 | 870 | 9000 | 1128 | 4200 | 3400 | 800 | 154 | 165 | 155 | 145
08/02/2021 | 22:05 | 22:10 | 0.083333 | 4917 | 4927 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 120 | 4200 | 3400 | 800 | 154 | 165 | 155 | 145
08/02/2021 | 22:10 | 22:15 | 0.083333 | 4927 | 4937 | 10 | Slide | TTF: 20; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 9000; Drilling Parameters ROP: 120 | 4200 | 3400 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 22:15 | 22:20 | 0.083333 | 4937 | 5011 | 74 | Rotate |  | 4947 | 10.91 | 109.38 | 4899.18 | -209.12 | 540.04 | -209.12 | 1.42 |  |  | 30 | 80 | 870 | 9000 | 888 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 22:25 | 22:35 | 0.16667 | 5011 | 5105 | 94 | Rotate |  | 5041 | 10.65 | 109.8 | 4991.52 | -215.01 | 556.61 | -215.01 | 0.29 |  |  | 30 | 80 | 870 | 9000 | 564 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 22:40 | 22:50 | 0.16667 | 5105 | 5198 | 93 | Rotate |  | 5134 | 10.93 | 110.12 | 5082.88 | -220.95 | 572.97 | -220.95 | 0.31 |  |  | 30 | 80 | 870 | 10000 | 558 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 22:55 | 23:05 | 0.16667 | 5198 | 5292 | 94 | Rotate |  | 5228 | 10.44 | 108.07 | 5175.25 | -226.66 | 589.44 | -226.66 | 0.66 |  |  | 30 | 80 | 870 | 10000 | 564 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 23:10 | 23:15 | 0.083333 | 5292 | 5386 | 94 | Rotate |  | 5322 | 9.92 | 106.59 | 5267.77 | -231.61 | 605.29 | -231.61 | 0.62 |  |  | 30 | 80 | 870 | 10000 | 1128 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 23:20 | 23:25 | 0.083333 | 5386 | 5396 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 23:25 | 23:40 | 0.25 | 5396 | 5406 | 10 | Slide | TTF: 80; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 40 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/02/2021 | 23:40 | 23:55 | 0.25 | 5406 | 5494 | 88 | Rotate |  | 5416 | 9.98 | 105.56 | 5360.35 | -236.11 | 620.9 | -236.11 | 0.2 |  |  | 30 | 80 | 870 | 10000 | 352 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 00:00 | 00:05 | 0.083333 | 5494 | 5504 | 10 | Slide | TTF: 80; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 120 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 00:05 | 00:10 | 0.083333 | 5504 | 5574 | 70 | Rotate |  | 5510 | 10.24 | 114.11 | 5452.9 | -241.71 | 636.37 | -241.71 | 1.62 |  |  | 30 | 80 | 870 | 10000 | 840 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 00:15 | 00:25 | 0.16667 | 5574 | 5667 | 93 | Rotate |  | 5603 | 10.76 | 115.3 | 5544.34 | -248.8 | 651.77 | -248.8 | 0.61 |  |  | 30 | 80 | 870 | 10000 | 558 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 00:30 | 00:35 | 0.083333 | 5667 | 5761 | 94 | Rotate |  | 5697 | 10.9 | 113.21 | 5636.67 | -256.05 | 667.87 | -256.05 | 0.44 |  |  | 30 | 80 | 870 | 10000 | 1128 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 00:40 | 00:50 | 0.16667 | 5761 | 5855 | 94 | Rotate |  | 5791 | 10.06 | 108.74 | 5729.1 | -262.19 | 683.81 | -262.19 | 1.24 |  |  | 30 | 80 | 870 | 10000 | 564 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 00:55 | 01:00 | 0.083333 | 5855 | 5866 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 132 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 01:00 | 01:05 | 0.083333 | 5866 | 5871 | 5 | Slide | TTF: 80; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 60 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 01:05 | 01:15 | 0.16667 | 5871 | 5949 | 78 | Rotate |  | 5885 | 8.85 | 105.16 | 5821.82 | -266.72 | 698.57 | -266.72 | 1.43 |  |  | 30 | 80 | 870 | 10000 | 468 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 01:20 | 01:25 | 0.083333 | 5949 | 5960 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 132 | 4400 | 3600 | 800 | 165 | 165 | 155 | 145
08/03/2021 | 01:25 | 01:35 | 0.16667 | 5960 | 5970 | 10 | Slide | TTF: 70; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 60 | 4400 | 3600 | 800 | 181 | 165 | 155 | 145
08/03/2021 | 01:35 | 01:45 | 0.16667 | 5970 | 6042 | 72 | Rotate |  | 5978 | 9.82 | 115.15 | 5913.59 | -271.96 | 712.65 | -271.96 | 2.03 |  |  | 30 | 80 | 870 | 10000 | 432 | 4400 | 3600 | 800 | 181 | 165 | 155 | 145
08/03/2021 | 01:50 | 01:55 | 0.083333 | 6042 | 6136 | 94 | Rotate |  | 6072 | 10.23 | 116.84 | 6006.16 | -279.14 | 727.36 | -279.14 | 0.54 |  |  | 30 | 80 | 870 | 10000 | 1128 | 4400 | 3600 | 800 | 181 | 165 | 155 | 145
08/03/2021 | 02:00 | 02:10 | 0.16667 | 6136 | 6230 | 94 | Rotate |  | 6166 | 9.62 | 114.42 | 6098.75 | -286.15 | 741.96 | -286.15 | 0.79 |  |  | 30 | 80 | 870 | 12000 | 564 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 02:15 | 02:25 | 0.16667 | 6230 | 6324 | 94 | Rotate |  | 6260 | 8.72 | 111.01 | 6191.55 | -291.95 | 755.76 | -291.95 | 1.12 |  |  | 30 | 80 | 870 | 12000 | 564 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 02:30 | 02:35 | 0.083333 | 6324 | 6335 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 132 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 02:35 | 02:50 | 0.25 | 6335 | 6344 | 9 | Slide | TTF: 45; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 36 | 4600 | 3800 | 800 | 190 | 190 | 175 | 160
08/03/2021 | 02:50 | 02:55 | 0.083333 | 6344 | 6417 | 73 | Rotate |  | 6353 | 8.63 | 114.52 | 6283.49 | -297.38 | 768.69 | -297.38 | 0.58 |  |  | 30 | 80 | 870 | 12000 | 876 | 4600 | 3800 | 800 | 190 | 190 | 175 | 160
08/03/2021 | 03:00 | 03:10 | 0.16667 | 6417 | 6512 | 95 | Rotate |  | 6448 | 8.25 | 114.69 | 6377.46 | -303.18 | 781.37 | -303.18 | 0.4 |  |  | 30 | 80 | 870 | 12000 | 570 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 03:15 | 03:20 | 0.083333 | 6512 | 6523 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 132 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 03:20 | 03:35 | 0.25 | 6523 | 6533 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 40 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 03:35 | 03:45 | 0.16667 | 6533 | 6606 | 73 | Rotate |  | 6542 | 8.74 | 115.12 | 6470.43 | -309.03 | 793.96 | -309.03 | 0.53 |  |  | 30 | 80 | 870 | 12000 | 438 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 03:50 | 03:55 | 0.083333 | 6606 | 6617 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 132 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 03:55 | 04:15 | 0.33333 | 6617 | 6627 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 30 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 04:15 | 04:25 | 0.16667 | 6627 | 6700 | 73 | Rotate |  | 6636 | 8.46 | 111.54 | 6563.37 | -314.6 | 806.86 | -314.6 | 0.64 |  |  | 30 | 80 | 870 | 12000 | 438 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 04:30 | 04:35 | 0.083333 | 6700 | 6712 | 12 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 144 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 04:35 | 05:00 | 0.41667 | 6712 | 6722 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 24 | 4600 | 3800 | 800 | 181 | 190 | 175 | 160
08/03/2021 | 05:00 | 05:10 | 0.16667 | 6722 | 6795 | 73 | Rotate |  | 6731 | 8.43 | 111.86 | 6657.34 | -319.76 | 819.82 | -319.76 | 0.06 |  |  | 44 | 80 | 870 | 15000 | 438 | 4933 | 4291 | 642 | 201 | 235 | 200 | 210
08/03/2021 | 05:15 | 05:20 | 0.083333 | 6795 | 6810 | 15 | Rotate | Drilling Parameters WOB: 44; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 180 | 4933 | 4291 | 642 | 201 | 235 | 200 | 210
08/03/2021 | 05:20 | 06:25 | 1.0833 | 6810 | 6830 | 20 | Slide | 0 | 6825 | 7.46 | 114.02 | 6750.44 | -324.81 | 831.79 | -324.81 | 1.08 |  |  | 25 |  | 870 |  | 18.46 | 4400 | 4291 | 109 | 201 | 235 | 200 | 210
08/03/2021 | 06:25 | 06:35 | 0.16667 | 6830 | 6889 | 59 | Rotate | Drilling Parameters WOB: 44; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 354 | 4933 | 4291 | 642 | 201 | 235 | 200 | 210
08/03/2021 | 06:38 | 06:41 | 0.05 | 6889 | 6903 | 14 | Rotate | Drilling Parameters WOB: 44; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 280 | 4933 | 4291 | 642 | 201 | 235 | 200 | 210
08/03/2021 | 06:41 | 07:05 | 0.4 | 6903 | 6918 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 37.5 | 4700 | 4496 | 204 | 201 | 235 | 200 | 210
08/03/2021 | 07:05 | 07:12 | 0.11667 | 6918 | 6983 | 65 | Rotate |  | 6919 | 7.44 | 111.9 | 6843.64 | -329.56 | 843.01 | -329.56 | 0.29 |  |  | 44 | 80 | 870 | 15000 | 557.14 | 5144 | 4496 | 648 | 201 | 235 | 200 | 210
08/03/2021 | 07:15 | 07:18 | 0.05 | 6983 | 6998 | 15 | Rotate | Drilling Parameters WOB: 44; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 300 | 5144 | 4496 | 648 | 201 | 235 | 200 | 210
08/03/2021 | 07:18 | 08:00 | 0.7 | 6998 | 7013 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 21.43 | 4600 | 4496 | 104 | 204 | 235 | 200 | 210
08/03/2021 | 08:00 | 08:09 | 0.15 | 7013 | 7077 | 64 | Rotate |  | 7013 | 7.41 | 106.37 | 6936.86 | -333.54 | 854.48 | -333.54 | 0.76 |  |  | 44 | 80 | 870 | 15000 | 426.67 | 5222 | 4496 | 726 | 204 | 235 | 200 | 210
08/03/2021 | 08:12 | 08:15 | 0.05 | 7077 | 7090 | 13 | Rotate | Drilling Parameters WOB: 44; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 260 | 5150 | 4496 | 654 | 204 | 235 | 200 | 210
08/03/2021 | 08:15 | 09:00 | 0.75 | 7090 | 7105 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 20 | 4500 | 4397 | 103 | 204 | 235 | 200 | 210
08/03/2021 | 09:00 | 09:08 | 0.13333 | 7105 | 7170 | 65 | Rotate |  | 7106 | 8.04 | 104.56 | 7029.01 | -336.87 | 866.52 | -336.87 | 0.73 |  |  | 45 | 80 | 870 | 15000 | 487.5 | 5271 | 4397 | 874 | 204 | 235 | 200 | 210
08/03/2021 | 09:11 | 09:14 | 0.05 | 7170 | 7184 | 14 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 280 | 5271 | 4397 | 874 | 204 | 235 | 200 | 210
08/03/2021 | 09:14 | 09:51 | 0.61667 | 7184 | 7199 | 15 | Slide | TTF: 60; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 24.32 | 4554 | 4404 | 150 | 204 | 235 | 200 | 210
08/03/2021 | 09:51 | 10:00 | 0.15 | 7199 | 7264 | 65 | Rotate |  | 7200 | 8.57 | 107.09 | 7122.03 | -340.58 | 879.58 | -340.58 | 0.68 |  |  | 45 | 80 | 870 | 15000 | 433.33 | 5188 | 4404 | 784 | 204 | 235 | 200 | 210
08/03/2021 | 10:22 | 10:27 | 0.083333 | 7264 | 7291 | 27 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 324 | 5188 | 4404 | 784 | 210 | 235 | 200 | 210
08/03/2021 | 10:27 | 11:27 | 1 | 7291 | 7306 | 15 | Slide | 60 | 7294 | 9 | 109.96 | 7214.92 | -345.15 | 893.19 | -345.15 | 0.65 |  |  | 15 |  | 700 |  | 15 | 3310 | 3160 | 150 | 210 | 235 | 200 | 210 | Slide on 2 pumps
08/03/2021 | 11:27 | 11:39 | 0.2 | 7306 | 7358 | 52 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 260 | 5322 | 4438 | 884 | 210 | 235 | 200 | 210
08/03/2021 | 11:42 | 11:46 | 0.066667 | 7358 | 7372 | 14 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 15694; Drilling Parameters ROP: 210 | 5322 | 4438 | 884 | 210 | 235 | 200 | 210
08/03/2021 | 11:46 | 12:19 | 0.55 | 7372 | 7387 | 15 | Slide | TTF: 70; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 27.27 | 4620 | 4438 | 182 | 210 | 235 | 200 | 210
08/03/2021 | 12:19 | 12:31 | 0.2 | 7387 | 7452 | 65 | Rotate |  | 7388 | 8.47 | 114.49 | 7307.83 | -350.53 | 906.4 | -350.53 | 0.92 |  |  | 42 | 80 | 870 | 16211 | 325 | 5333 | 4438 | 895 | 213 | 235 | 200 | 210
08/03/2021 | 12:35 | 12:39 | 0.066667 | 7452 | 7466 | 14 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 16211; Drilling Parameters ROP: 210 | 5333 | 4438 | 895 | 213 | 235 | 200 | 210
08/03/2021 | 12:39 | 12:54 | 0.25 | 7466 | 7478 | 12 | Slide | TTF: 30; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 48 | 4620 | 4438 | 182 | 213 | 235 | 200 | 210
08/03/2021 | 12:54 | 13:08 | 0.23333 | 7478 | 7546 | 68 | Rotate |  | 7482 | 8.8 | 118.36 | 7400.77 | -356.81 | 919.03 | -356.81 | 0.71 |  |  | 44 | 80 | 870 | 18074 | 291.43 | 5426 | 4548 | 878 | 213 | 235 | 200 | 210
08/03/2021 | 13:11 | 13:26 | 0.25 | 7546 | 7641 | 95 | Rotate |  | 7577 | 8.01 | 116.52 | 7494.75 | -363.22 | 931.34 | -363.22 | 0.88 |  |  | 43 | 80 | 870 | 18603 | 380 | 5455 | 4548 | 907 | 213 | 235 | 200 | 210
08/03/2021 | 13:29 | 13:33 | 0.066667 | 7641 | 7653 | 12 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18603; Drilling Parameters ROP: 180 | 5455 | 4548 | 907 | 213 | 235 | 200 | 210
08/03/2021 | 13:33 | 13:48 | 0.25 | 7653 | 7665 | 12 | Slide | TTF: 30; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 48 | 4750 | 4548 | 202 | 215 | 235 | 200 | 210
08/03/2021 | 13:48 | 13:56 | 0.13333 | 7665 | 7735 | 70 | Rotate |  | 7671 | 8.46 | 119.84 | 7587.78 | -369.58 | 943.2 | -369.58 | 0.7 |  |  | 41 | 80 | 870 | 17987 | 525 | 5455 | 4548 | 907 | 218 | 235 | 200 | 210
08/03/2021 | 13:59 | 14:14 | 0.25 | 7735 | 7828 | 93 | Rotate |  | 7764 | 7.21 | 121.34 | 7679.91 | -376.02 | 954.12 | -376.02 | 1.36 |  |  | 40 | 80 | 870 | 18603 | 372 | 5455 | 4548 | 907 | 219 | 235 | 200 | 210
08/03/2021 | 14:17 | 14:21 | 0.066667 | 7828 | 7842 | 14 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18603; Drilling Parameters ROP: 210 | 5455 | 4548 | 907 | 219 | 235 | 200 | 210
08/03/2021 | 14:21 | 14:33 | 0.2 | 7842 | 7854 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 60 | 4766 | 4548 | 218 | 219 | 235 | 200 | 210
08/03/2021 | 14:33 | 14:48 | 0.25 | 7854 | 7922 | 68 | Rotate |  | 7858 | 7.16 | 115.38 | 7773.17 | -381.6 | 964.45 | -381.6 | 0.79 |  |  | 32 | 80 | 870 | 17141 | 272 | 5122 | 4548 | 574 | 219 | 235 | 200 | 210
08/03/2021 | 14:51 | 15:03 | 0.2 | 7922 | 8016 | 94 | Rotate |  | 7952 | 6.39 | 116.22 | 7866.52 | -386.42 | 974.44 | -386.42 | 0.83 |  |  | 45 | 80 | 870 | 18833 | 470 | 5622 | 4668 | 954 | 221 | 235 | 200 | 210
08/03/2021 | 15:07 | 15:27 | 0.33333 | 8016 | 8110 | 94 | Rotate |  | 8046 | 4.42 | 110.76 | 7960.09 | -390.02 | 982.52 | -390.02 | 2.16 |  |  | 42 | 80 | 870 | 18833 | 282 | 5622 | 4668 | 954 | 221 | 235 | 200 | 210
08/03/2021 | 15:30 | 15:34 | 0.066667 | 8110 | 8122 | 12 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 180 | 5622 | 4668 | 954 | 221 | 235 | 200 | 210
08/03/2021 | 15:34 | 16:08 | 0.56667 | 8122 | 8134 | 12 | Slide | TTF: 30; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 21.18 | 4800 | 4629 | 171 | 221 | 235 | 200 | 210
08/03/2021 | 16:08 | 16:16 | 0.13333 | 8134 | 8204 | 70 | Rotate |  | 8140 | 2.35 | 117.88 | 8053.93 | -392.2 | 987.61 | -392.2 | 2.24 |  |  | 10 | 80 | 870 | 18000 | 525 | 5200 | 4629 | 571 | 221 | 235 | 200 | 210
08/03/2021 | 17:00 | 17:04 | 0.066667 | 8204 | 8216 | 12 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 180 | 5200 | 4629 | 571 | 221 | 235 | 200 | 210
08/03/2021 | 17:04 | 17:25 | 0.35 | 8216 | 8231 | 15 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 42.86 | 5200 | 4629 | 571 | 221 | 235 | 200 | 210
08/03/2021 | 17:25 | 17:35 | 0.16667 | 8231 | 8298 | 67 | Rotate |  | 8234 | 2.73 | 120.61 | 8147.83 | -394.25 | 991.24 | -394.25 | 0.42 |  |  | 10 | 80 | 870 | 18000 | 402 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 17:40 | 17:55 | 0.25 | 8298 | 8392 | 94 | Rotate |  | 8328 | 3.42 | 113.53 | 8241.7 | -396.5 | 995.74 | -396.5 | 0.84 |  |  | 10 | 80 | 870 | 18000 | 376 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 18:00 | 18:10 | 0.16667 | 8392 | 8486 | 94 | Rotate |  | 8422 | 2.88 | 113.85 | 8335.56 | -398.58 | 1000.47 | -398.58 | 0.57 |  |  | 10 | 80 | 870 | 18000 | 564 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 18:15 | 18:30 | 0.25 | 8486 | 8580 | 94 | Rotate |  | 8516 | 2.76 | 107.26 | 8429.44 | -400.21 | 1004.79 | -400.21 | 0.37 |  |  | 10 | 80 | 870 | 18000 | 376 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 18:35 | 18:55 | 0.33333 | 8580 | 8674 | 94 | Rotate |  | 8610 | 2.37 | 96.66 | 8523.35 | -401.1 | 1008.88 | -401.1 | 0.65 |  |  | 10 | 80 | 870 | 18000 | 282 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 19:00 | 19:10 | 0.16667 | 8674 | 8769 | 95 | Rotate |  | 8705 | 1.46 | 85.59 | 8618.29 | -401.24 | 1012.04 | -401.24 | 1.03 |  |  | 10 | 80 | 870 | 18000 | 570 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 19:15 | 19:30 | 0.25 | 8769 | 8863 | 94 | Rotate |  | 8799 | 1.07 | 42.42 | 8712.27 | -400.5 | 1013.82 | -400.5 | 1.06 |  |  | 10 | 80 | 870 | 18000 | 376 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 19:35 | 19:50 | 0.25 | 8863 | 8957 | 94 | Rotate |  | 8893 | 1.63 | 14.92 | 8806.25 | -398.56 | 1014.76 | -398.56 | 0.89 |  |  | 10 | 80 | 870 | 18000 | 376 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 19:55 | 20:10 | 0.25 | 8957 | 9051 | 94 | Rotate |  | 8987 | 1.78 | 351.48 | 8900.21 | -395.82 | 1014.89 | -395.82 | 0.75 |  |  | 10 | 80 | 870 | 18000 | 376 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 20:15 | 20:30 | 0.25 | 9051 | 9144 | 93 | Rotate |  | 9080 | 2.3 | 339.93 | 8993.15 | -392.64 | 1014.03 | -392.64 | 0.71 |  |  | 10 | 80 | 870 | 18000 | 372 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 20:35 | 20:40 | 0.083333 | 9144 | 9155 | 11 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 132 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 20:40 | 21:25 | 0.75 | 9155 | 9175 | 20 | Slide | 150 | 9174 | 2.59 | 325.39 | 9087.06 | -389.12 | 1012.18 | -389.12 | 0.73 |  |  | 10 |  | 870 |  | 26.67 | 4800 | 4629 | 171 | 230 | 235 | 200 | 210
08/03/2021 | 21:25 | 21:40 | 0.25 | 9175 | 9238 | 63 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 252 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 21:45 | 21:50 | 0.083333 | 9238 | 9256 | 18 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 216 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 21:50 | 22:45 | 0.91667 | 9256 | 9271 | 15 | Slide | 150 | 9268 | 2.23 | 334.46 | 9180.98 | -385.72 | 1010.18 | -385.72 | 0.56 |  |  | 10 |  | 870 |  | 16.36 | 4800 | 4629 | 171 | 230 | 235 | 200 | 210
08/03/2021 | 22:45 | 22:55 | 0.16667 | 9271 | 9332 | 61 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 366 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 23:00 | 23:15 | 0.25 | 9332 | 9426 | 94 | Rotate |  | 9362 | 2.59 | 325.52 | 9274.9 | -382.32 | 1008.19 | -382.32 | 0.55 |  |  | 10 | 80 | 870 | 18000 | 376 | 5200 | 4629 | 571 | 230 | 235 | 200 | 210
08/03/2021 | 23:20 | 23:25 | 0.083333 | 9426 | 9438 | 12 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 144 | 5200 | 4629 | 571 | 235 | 295 | 260 | 220
08/03/2021 | 23:25 | 24:00 | 0.58333 | 9438 | 9452 | 14 | Slide | TTF: 150; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 24 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 00:00 | 00:10 | 0.16667 | 9452 | 9454 | 2 | Slide | TTF: 150; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 12 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 00:10 | 00:20 | 0.16667 | 9454 | 9519 | 65 | Rotate |  | 9455 | 2.41 | 326.2 | 9367.81 | -378.96 | 1005.92 | -378.96 | 0.2 |  |  | 10 | 80 | 870 | 18000 | 390 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 00:25 | 00:30 | 0.083333 | 9519 | 9530 | 11 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 132 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 00:30 | 01:15 | 0.75 | 9530 | 9548 | 18 | Slide | TTF: 150; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 870; Drilling Parameters ROP: 24 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 01:15 | 01:25 | 0.16667 | 9548 | 9613 | 65 | Rotate |  | 9549 | 2.27 | 285.28 | 9461.74 | -376.83 | 1003.02 | -376.83 | 1.75 |  |  | 10 | 80 | 870 | 18000 | 390 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 01:30 | 01:35 | 0.083333 | 9613 | 9625 | 12 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 144 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 01:35 | 02:40 | 1.0833 | 9625 | 9645 | 20 | Slide | 180 | 9643 | 2.63 | 279.07 | 9555.65 | -376 | 999.09 | -376 | 0.48 |  |  | 10 |  | 870 |  | 18.46 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 02:40 | 02:50 | 0.16667 | 9645 | 9707 | 62 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 372 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 02:55 | 03:00 | 0.083333 | 9707 | 9720 | 13 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 156 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 03:00 | 04:00 | 1 | 9720 | 9740 | 20 | Slide | 120 | 9737 | 1.81 | 247.53 | 9649.58 | -376.23 | 995.59 | -376.23 | 1.53 |  |  | 10 |  | 745 |  | 20 | 3900 | 3700 | 200 | 235 | 295 | 260 | 220
08/04/2021 | 04:00 | 04:15 | 0.25 | 9740 | 9801 | 61 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 244 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 04:20 | 04:30 | 0.16667 | 9801 | 9894 | 93 | Rotate |  | 9830 | 1.45 | 239.48 | 9742.55 | -377.39 | 993.22 | -377.39 | 0.46 |  |  | 10 | 80 | 870 | 18000 | 558 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 04:35 | 04:55 | 0.33333 | 9894 | 9988 | 94 | Rotate |  | 9924 | 1.03 | 228.29 | 9836.52 | -378.55 | 991.57 | -378.55 | 0.51 |  |  | 10 | 80 | 870 | 18000 | 282 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 05:00 | 05:25 | 0.41667 | 9988 | 10082 | 94 | Rotate |  | 10018 | 0.84 | 238.15 | 9930.51 | -379.48 | 990.35 | -379.48 | 0.26 |  |  | 10 | 80 | 870 | 18000 | 225.6 | 4800 | 4629 | 171 | 235 | 295 | 260 | 220
08/04/2021 | 05:30 | 06:04 | 0.56667 | 10082 | 10175 | 93 | Rotate |  | 10111 | 1.28 | 261.06 | 10023.49 | -380 | 988.75 | -380 | 0.65 |  |  | 40 | 80 | 670 | 19308 | 164.12 | 4021 | 3319 | 702 | 243 | 295 | 260 | 220
08/04/2021 | 06:09 | 06:32 | 0.38333 | 10175 | 10269 | 94 | Rotate |  | 10205 | 1.26 | 267.74 | 10117.47 | -380.2 | 986.68 | -380.2 | 0.16 |  |  | 40 | 80 | 813 | 19032 | 245.22 | 5408 | 4743 | 665 | 244 | 295 | 260 | 220
08/04/2021 | 06:37 | 06:58 | 0.35 | 10269 | 10363 | 94 | Rotate |  | 10299 | 1.69 | 304.48 | 10211.44 | -379.46 | 984.5 | -379.46 | 1.08 |  |  | 38 | 80 | 670 | 20200 | 268.57 | 4232 | 3600 | 632 | 246 | 295 | 260 | 220
08/04/2021 | 07:02 | 07:28 | 0.43333 | 10363 | 10457 | 94 | Rotate |  | 10393 | 1.8 | 296.49 | 10305.4 | -378.02 | 982.04 | -378.02 | 0.28 |  |  | 38 | 80 | 870 | 20200 | 216.92 | 5322 | 4743 | 579 | 246 | 295 | 260 | 220
08/04/2021 | 07:32 | 07:37 | 0.083333 | 10457 | 10466 | 9 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 870; Drilling Parameters Tq: 20200; Drilling Parameters ROP: 108 | 5322 | 4741 | 581 | 246 | 295 | 260 | 220
08/04/2021 | 07:37 | 08:09 | 0.53333 | 10466 | 10481 | 15 | Slide | TTF: 120; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 727; Drilling Parameters ROP: 28.13 | 4122 | 3920 | 202 | 246 | 310 | 275 | 245
08/04/2021 | 08:09 | 08:28 | 0.31667 | 10481 | 10551 | 70 | Rotate |  | 10487 | 1.01 | 308.82 | 10399.37 | -376.84 | 980.07 | -376.84 | 0.9 |  |  | 40 | 80 | 813 | 19874 | 221.05 | 5400 | 4743 | 657 | 246 | 310 | 275 | 245
08/04/2021 | 08:31 | 08:35 | 0.066667 | 10551 | 10561 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 813; Drilling Parameters Tq: 19874; Drilling Parameters ROP: 150 | 5400 | 4743 | 657 | 246 | 310 | 275 | 245
08/04/2021 | 08:35 | 09:55 | 1.3333 | 10561 | 10645 | 84 | Slide | 120 | 10581 | 1.53 | 108.37 | 10493.36 | -376.72 | 980.62 | -376.72 | 2.66 |  |  | 12 |  | 727 |  | 63 | 4130 | 3920 | 210 | 246 | 310 | 275 | 245
08/04/2021 | 11:00 | 11:10 | 0.16667 | 10645 | 10670 | 25 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 813; Drilling Parameters Tq: 17744; Drilling Parameters ROP: 150 | 4920 | 4520 | 400 | 246 | 310 | 275 | 245
08/04/2021 | 11:10 | 13:10 | 2 | 10670 | 10739 | 69 | Slide | 150 | 10675 | 6.8 | 127.47 | 10587.08 | -380.5 | 986.23 | -380.5 | 5.72 |  |  | 15 |  | 813 |  | 34.5 | 4715 | 4520 | 195 | 246 | 310 | 275 | 245
08/04/2021 | 13:15 | 13:23 | 0.13333 | 10739 | 10759 | 20 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 813; Drilling Parameters Tq: 17124; Drilling Parameters ROP: 150 | 5000 | 4520 | 480 | 246 | 310 | 275 | 245
08/04/2021 | 13:23 | 14:25 | 1.0333 | 10759 | 10813 | 54 | Slide | 30 | 10769 | 13.04 | 138.23 | 10679.64 | -391.81 | 997.72 | -391.81 | 6.9 |  |  | 12 |  | 813 |  | 52.26 | 4720 | 4520 | 200 | 246 | 310 | 275 | 245
08/04/2021 | 14:30 | 14:42 | 0.2 | 10813 | 10833 | 20 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 813; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 100 | 5000 | 4520 | 480 | 246 | 310 | 275 | 245
08/04/2021 | 14:46 | 15:26 | 0.66667 | 10833 | 10927 | 94 | Rotate |  | 10863 | 14.75 | 147.45 | 10770.9 | -409.8 | 1011.23 | -409.8 | 2.97 |  |  | 25 | 30 | 813 | 17500 | 141 | 5000 | 4520 | 480 | 246 | 310 | 275 | 245
08/04/2021 | 15:34 | 17:42 | 2.1333 | 10927 | 10977 | 50 | Slide | 20 | 10956 | 16.39 | 150.04 | 10860.48 | -431.15 | 1024.15 | -431.15 | 1.91 |  |  | 15 |  | 813 |  | 23.44 | 4700 | 4520 | 180 | 246 | 310 | 275 | 255
08/04/2021 | 17:42 | 18:00 | 0.3 | 10977 | 11022 | 45 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters FLOW: 813; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 150 | 4700 | 4520 | 180 | 246 | 310 | 275 | 255

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 243
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 243
Well Name: |  |  |  |  | Rommel 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 61.00 / 57.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.56 |  | Rotate: |  | 0
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/19/2021 | 08:30 | 24:00 | 15.5 | 11022 | 11041 | 19 | Slide | TTF: 80; Drilling Parameters WOB: 5; Drilling Parameters FLOW: 275; Drilling Parameters ROP: 1.23 | 1900 | 1800 | 100 | 217 | 225 | 195 | 170
08/20/2021 | 00:00 | 02:00 | 2 | 11041 | 11076 | 35 | Slide | TTF: 30; Drilling Parameters WOB: 7; Drilling Parameters FLOW: 275; Drilling Parameters ROP: 17.5 | 1900 | 1800 | 100 | 217 | 225 | 195 | 170
08/20/2021 | 02:15 | 04:00 | 1.75 | 11076 | 11171 | 95 | Slide | 0 | 11110 | 27.89 | 151.95 | 11002.89 | -481.94 | 1052.03 | -481.94 | 7.48 |  |  | 20 |  | 300 |  | 54.29 | 2650 | 2200 | 450 | 219 | 225 | 195 | 170
08/20/2021 | 04:10 | 06:00 | 1.8333 | 11171 | 11265 | 94 | Slide | 0 | 11205 | 42.79 | 149.26 | 11080.17 | -529.55 | 1079.13 | -529.55 | 15.77 |  |  | 20 |  | 300 |  | 51.27 | 2650 | 2200 | 450 | 219 | 225 | 195 | 170

## BHA_5_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6680
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 845
Well Name: |  |  |  |  | Rommel 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 61.00 / 57.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.56 |  | Rotate: |  | 5835
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/21/2021 | 01:15 | 01:50 | 0.58333 | 11265 | 11295 | 30 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 51.43 | 4550 | 4020 | 530 | 243 | 240 | 210 | 195
08/21/2021 | 01:50 | 02:15 | 0.41667 | 11295 | 11309 | 14 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 33.6 | 4350 | 4020 | 330 | 243 | 240 | 210 | 195
08/21/2021 | 02:22 | 02:40 | 0.3 | 11309 | 11324 | 15 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 50 | 4550 | 4020 | 530 | 243 | 240 | 210 | 195
08/21/2021 | 02:40 | 03:50 | 1.1667 | 11324 | 11403 | 79 | Slide | 20 | 11342 | 54.61 | 151.34 | 11166.86 | -621.63 | 1131.24 | -621.63 | 4.54 |  |  | 22 | 35 | 400 | 6000 | 67.71 | 4550 | 4020 | 530 | 243 | 240 | 210 | 195
08/21/2021 | 03:58 | 04:23 | 0.41667 | 11403 | 11423 | 20 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 48 | 4650 | 4020 | 630 | 243 | 240 | 210 | 195
08/21/2021 | 04:23 | 04:57 | 0.56667 | 11423 | 11473 | 50 | Slide | 10 | 11437 | 65.54 | 154.65 | 11214.19 | -694.92 | 1168.44 | -694.92 | 11.89 |  |  | 22 | 35 | 400 | 3100 | 88.24 | 4575 | 4020 | 555 | 243 | 240 | 210 | 195
08/21/2021 | 04:57 | 05:18 | 0.35 | 11473 | 11498 | 25 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 71.43 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 05:27 | 06:00 | 0.55 | 11498 | 11560 | 62 | Rotate |  | 11531 | 69.07 | 154.8 | 11250.46 | -773.33 | 1205.46 | -773.33 | 3.76 |  |  | 22 | 35 | 400 | 6500 | 112.73 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 06:00 | 06:28 | 0.46667 | 11560 | 11592 | 32 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 68.57 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 06:38 | 07:01 | 0.38333 | 11592 | 11644 | 52 | Rotate |  | 11626 | 70.2 | 155.18 | 11283.52 | -854.04 | 1243.11 | -854.04 | 1.25 |  |  | 22 | 35 | 400 | 6500 | 135.65 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 07:01 | 07:30 | 0.48333 | 11644 | 11687 | 43 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 88.97 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 07:35 | 07:40 | 0.083333 | 11687 | 11692 | 5 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 60 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 07:40 | 08:40 | 1 | 11692 | 11782 | 90 | Slide | 0 | 11721 | 79.14 | 154.15 | 11308.61 | -936.76 | 1282.3 | -936.76 | 9.47 |  |  | 22 | 35 | 400 | 6500 | 90 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 08:50 | 09:10 | 0.33333 | 11782 | 11804 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 66 | 4650 | 4020 | 630 | 244.4 | 240 | 210 | 195
08/21/2021 | 09:10 | 09:40 | 0.5 | 11804 | 11876 | 72 | Rotate |  | 11815 | 94.01 | 154.96 | 11314.21 | -1021.25 | 1322.49 | -1021.25 | 15.84 |  |  | 22 | 35 | 400 | 6500 | 144 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 09:45 | 10:05 | 0.33333 | 11876 | 11891 | 15 | Slide | TTF: 210; Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 45 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 10:05 | 10:30 | 0.41667 | 11891 | 11971 | 80 | Rotate |  | 11910 | 92.3 | 154.01 | 11308.98 | -1106.85 | 1363.35 | -1106.85 | 2.06 |  |  | 22 | 80 | 400 | 6500 | 192 | 4800 | 4020 | 780 | 253 | 240 | 210 | 195
08/21/2021 | 10:35 | 10:50 | 0.25 | 11971 | 11991 | 20 | Slide | TTF: 210; Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 80 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 10:50 | 11:15 | 0.41667 | 11991 | 12066 | 75 | Rotate |  | 12005 | 90.05 | 153.42 | 11307.03 | -1192 | 1405.41 | -1192 | 2.45 |  |  | 22 | 35 | 400 | 6500 | 180 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 11:20 | 11:45 | 0.41667 | 12066 | 12091 | 25 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 60 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 11:45 | 11:55 | 0.16667 | 12091 | 12122 | 31 | Rotate |  | 12100 | 86.86 | 153.31 | 11309.59 | -1276.88 | 1447.98 | -1276.88 | 3.36 |  |  | 22 | 35 | 400 | 6500 | 186 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 12:05 | 12:20 | 0.25 | 12122 | 12142 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 80 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 12:20 | 12:30 | 0.16667 | 12142 | 12161 | 19 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 114 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 13:05 | 13:20 | 0.25 | 12161 | 12171 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 25; Drilling Parameters RPM: 35; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 40 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 13:20 | 13:45 | 0.41667 | 12171 | 12255 | 84 | Rotate |  | 12194 | 80.74 | 151.24 | 11319.74 | -1359.56 | 1491.42 | -1359.56 | 6.87 |  |  | 22 | 80 | 400 | 6500 | 201.6 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 13:50 | 14:10 | 0.33333 | 12255 | 12270 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters RPM: 55; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 45 | 4650 | 4020 | 630 | 253 | 240 | 210 | 195
08/21/2021 | 14:10 | 14:35 | 0.41667 | 12270 | 12350 | 80 | Rotate |  | 12289 | 82.38 | 151.68 | 11333.68 | -1442.11 | 1536.31 | -1442.11 | 1.79 |  |  | 22 | 80 | 400 | 6500 | 192 | 4650 | 4020 | 630 | 259 | 240 | 210 | 195
08/21/2021 | 14:40 | 14:55 | 0.25 | 12350 | 12362 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 55; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 48 | 4650 | 4020 | 630 | 259 | 240 | 210 | 195
08/21/2021 | 14:55 | 15:25 | 0.5 | 12362 | 12445 | 83 | Rotate |  | 12384 | 84.7 | 152.1 | 11344.37 | -1525.37 | 1580.79 | -1525.37 | 2.48 |  |  | 22 | 80 | 400 | 6500 | 166 | 4650 | 4020 | 630 | 259 | 240 | 210 | 195
08/21/2021 | 15:30 | 16:05 | 0.58333 | 12445 | 12536 | 91 | Rotate |  | 12475 | 84.93 | 151.82 | 11352.59 | -1605.36 | 1623.39 | -1605.36 | 0.4 |  |  | 22 | 80 | 400 | 6500 | 156 | 4650 | 4020 | 630 | 259 | 240 | 210 | 195
08/21/2021 | 16:10 | 16:20 | 0.16667 | 12536 | 12546 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters RPM: 5; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 60 | 4650 | 4020 | 630 | 259 | 240 | 210 | 195
08/21/2021 | 16:20 | 16:55 | 0.58333 | 12546 | 12631 | 85 | Rotate |  | 12570 | 86.6 | 151.72 | 11359.61 | -1688.83 | 1668.2 | -1688.83 | 1.76 |  |  | 22 | 80 | 400 | 6500 | 145.71 | 4650 | 4020 | 630 | 264 | 240 | 210 | 195
08/21/2021 | 17:00 | 17:30 | 0.5 | 12631 | 12726 | 95 | Rotate |  | 12665 | 86.46 | 150.72 | 11365.36 | -1771.94 | 1713.85 | -1771.94 | 1.06 |  |  | 22 | 80 | 400 | 6500 | 190 | 4650 | 4020 | 630 | 268 | 240 | 210 | 195
08/21/2021 | 17:50 | 18:24 | 0.56667 | 12726 | 12818 | 92 | Rotate |  | 12757 | 86.46 | 148.95 | 11371.04 | -1851.33 | 1759.99 | -1851.33 | 1.92 |  |  | 22 | 80 | 400 | 8500 | 162.35 | 4990 | 4150 | 840 | 264 | 240 | 210 | 195
08/21/2021 | 18:27 | 19:11 | 0.73333 | 12818 | 12913 | 95 | Rotate |  | 12852 | 86.6 | 147.38 | 11376.79 | -1931.88 | 1810.01 | -1931.88 | 1.66 |  |  | 22 | 80 | 400 | 6500 | 129.55 | 4990 | 4150 | 840 | 264 | 260 | 195 | 170
08/21/2021 | 19:13 | 19:22 | 0.15 | 12913 | 12928 | 15 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 100 | 4990 | 4150 | 840 | 264 | 260 | 195 | 170
08/21/2021 | 19:22 | 19:34 | 0.2 | 12928 | 12940 | 12 | Slide | TTF: 80; Drilling Parameters WOB: 22; Drilling Parameters RPM: 55; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 60 | 4990 | 4150 | 840 | 268 | 260 | 195 | 170
08/21/2021 | 19:34 | 20:03 | 0.48333 | 12940 | 13007 | 67 | Rotate |  | 12946 | 86.77 | 147.58 | 11382.23 | -2011.01 | 1860.46 | -2011.01 | 0.28 |  |  | 22 | 80 | 400 | 6500 | 138.62 | 4990 | 4150 | 840 | 268 | 260 | 195 | 170
08/21/2021 | 20:07 | 20:12 | 0.083333 | 13007 | 13021 | 14 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 168 | 4990 | 4150 | 840 | 268 | 260 | 195 | 170
08/21/2021 | 20:12 | 20:26 | 0.23333 | 13021 | 13036 | 15 | Slide | TTF: 70; Drilling Parameters WOB: 22; Drilling Parameters RPM: 62; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4000; Drilling Parameters ROP: 64.29 | 4650 | 4150 | 500 | 271 | 260 | 195 | 170
08/21/2021 | 20:26 | 20:57 | 0.51667 | 13036 | 13102 | 66 | Rotate |  | 13041 | 86.79 | 149.08 | 11387.56 | -2091.74 | 1910.26 | -2091.74 | 1.58 |  |  | 22 | 80 | 400 | 6500 | 127.74 | 4990 | 4150 | 840 | 272 | 260 | 195 | 170
08/21/2021 | 21:00 | 21:03 | 0.05 | 13102 | 13105 | 3 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 60 | 4990 | 4150 | 840 | 272 | 260 | 195 | 170
08/21/2021 | 21:03 | 21:18 | 0.25 | 13105 | 13123 | 18 | Slide | TTF: 70; Drilling Parameters WOB: 22; Drilling Parameters RPM: 65; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 72 | 4650 | 4150 | 500 | 277 | 260 | 195 | 170
08/21/2021 | 21:18 | 21:40 | 0.36667 | 13123 | 13174 | 51 | Rotate |  | 13135 | 88.52 | 151.77 | 11391.41 | -2173.41 | 1956.61 | -2173.41 | 3.4 |  |  | 22 | 80 | 400 | 8500 | 139.09 | 4990 | 4150 | 840 | 277 | 260 | 195 | 170
08/21/2021 | 21:49 | 22:00 | 0.18333 | 13174 | 13186 | 12 | Slide | TTF: 120; Drilling Parameters WOB: 22; Drilling Parameters RPM: 65; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 65.45 | 4650 | 4150 | 500 | 277 | 260 | 195 | 170
08/21/2021 | 22:00 | 22:15 | 0.25 | 13186 | 13196 | 10 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 40 | 4990 | 4150 | 840 | 277 | 260 | 195 | 170
08/21/2021 | 22:18 | 22:53 | 0.58333 | 13196 | 13268 | 72 | Rotate |  | 13230 | 87.97 | 153.32 | 11394.32 | -2257.67 | 2000.38 | -2257.67 | 1.73 |  |  | 22 | 80 | 400 | 8500 | 123.43 | 4990 | 4150 | 840 | 277 | 260 | 195 | 170
08/21/2021 | 22:53 | 23:02 | 0.15 | 13268 | 13280 | 12 | Slide | TTF: 160; Drilling Parameters WOB: 22; Drilling Parameters RPM: 65; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 80 | 4650 | 4150 | 500 | 277 | 260 | 195 | 170
08/21/2021 | 23:02 | 23:12 | 0.16667 | 13280 | 13291 | 11 | Rotate | Drilling Parameters WOB: 22; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 66 | 4990 | 4150 | 840 | 277 | 260 | 195 | 170
08/21/2021 | 23:15 | 23:57 | 0.7 | 13291 | 13386 | 95 | Rotate |  | 13325 | 87.38 | 153.96 | 11398.17 | -2342.72 | 2042.53 | -2342.72 | 0.92 |  |  | 22 | 80 | 400 | 8500 | 135.71 | 4990 | 4150 | 840 | 277 | 260 | 195 | 170
08/22/2021 | 00:00 | 00:18 | 0.3 | 13386 | 13401 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 30; Drilling Parameters RPM: 65; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 50 | 4650 | 4150 | 500 | 277 | 260 | 195 | 170
08/22/2021 | 00:18 | 00:52 | 0.56667 | 13401 | 13480 | 79 | Rotate |  | 13419 | 86.57 | 154.88 | 11403.13 | -2427.39 | 2083.06 | -2427.39 | 1.3 |  |  | 22 | 80 | 400 | 8500 | 139.41 | 5020 | 4150 | 870 | 277 | 260 | 195 | 170
08/22/2021 | 00:56 | 01:00 | 0.066667 | 13480 | 13485 | 5 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 75 | 5020 | 4150 | 870 | 277 | 260 | 195 | 170
08/22/2021 | 01:00 | 01:17 | 0.28333 | 13485 | 13503 | 18 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 65; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 63.53 | 4650 | 4150 | 500 | 277 | 280 | 185 | 165
08/22/2021 | 01:17 | 01:44 | 0.45 | 13503 | 13575 | 72 | Rotate |  | 13514 | 83.15 | 151.6 | 11411.65 | -2511.85 | 2125.64 | -2511.85 | 4.98 |  |  | 32 | 80 | 400 | 8500 | 160 | 5100 | 4250 | 850 | 279 | 280 | 185 | 165
08/22/2021 | 01:47 | 01:58 | 0.18333 | 13575 | 13601 | 26 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 141.82 | 5100 | 4250 | 850 | 279 | 280 | 185 | 165
08/22/2021 | 01:58 | 02:08 | 0.16667 | 13601 | 13609 | 8 | Slide | 0 | 13609 | 83.66 | 152.27 | 11422.56 | -2595.12 | 2170.04 | -2595.12 | 0.88 |  |  | 32 | 65 | 400 | 4500 | 48 | 5050 | 4250 | 800 | 279 | 280 | 185 | 165
08/22/2021 | 02:08 | 02:28 | 0.33333 | 13609 | 13670 | 61 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 183 | 5050 | 4250 | 800 | 279 | 280 | 185 | 165
08/22/2021 | 02:31 | 03:19 | 0.8 | 13670 | 13764 | 94 | Rotate |  | 13703 | 83.86 | 152.04 | 11432.77 | -2677.75 | 2213.69 | -2677.75 | 0.32 |  |  | 32 | 80 | 400 | 8500 | 117.5 | 5050 | 4250 | 800 | 279 | 280 | 185 | 165
08/22/2021 | 03:22 | 03:27 | 0.083333 | 13764 | 13778 | 14 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 168 | 5050 | 4250 | 800 | 279 | 280 | 185 | 165
08/22/2021 | 03:27 | 03:46 | 0.31667 | 13778 | 13794 | 16 | Slide | TTF: 30; Drilling Parameters WOB: 32; Drilling Parameters RPM: 65; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 4500; Drilling Parameters ROP: 50.53 | 5050 | 4350 | 700 | 279 | 280 | 185 | 165
08/22/2021 | 03:46 | 04:08 | 0.36667 | 13794 | 13859 | 65 | Rotate |  | 13798 | 85.81 | 152.81 | 11441.33 | -2761.61 | 2257.48 | -2761.61 | 2.21 |  |  | 32 | 80 | 400 | 8500 | 220.91 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 05:18 | 06:00 | 0.7 | 13859 | 13952 | 93 | Rotate |  | 13891 | 86.91 | 152.5 | 11447.23 | -2844.05 | 2300.11 | -2844.05 | 1.23 |  |  | 32 | 80 | 400 | 8500 | 132.86 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 06:05 | 06:30 | 0.41667 | 13952 | 13967 | 15 | Slide | TTF: 130; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 36 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 06:30 | 07:00 | 0.5 | 13967 | 14046 | 79 | Rotate |  | 13985 | 85.91 | 153.17 | 11453.12 | -2927.51 | 2342.94 | -2927.51 | 1.28 |  |  | 32 | 80 | 400 | 8500 | 158 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 07:05 | 07:45 | 0.66667 | 14046 | 14140 | 94 | Rotate |  | 14079 | 86.25 | 153.3 | 11459.54 | -3011.25 | 2385.18 | -3011.25 | 0.39 |  |  | 32 | 80 | 400 | 8500 | 141 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 07:50 | 08:25 | 0.58333 | 14140 | 14234 | 94 | Rotate |  | 14173 | 87.6 | 153.56 | 11464.58 | -3095.2 | 2427.16 | -3095.2 | 1.46 |  |  | 32 | 80 | 400 | 8500 | 161.14 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 08:30 | 08:50 | 0.33333 | 14234 | 14249 | 15 | Slide | TTF: 150; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 45 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 08:50 | 09:25 | 0.58333 | 14249 | 14329 | 80 | Rotate |  | 14268 | 85.61 | 153.75 | 11470.21 | -3180.18 | 2469.24 | -3180.18 | 2.1 |  |  | 32 | 80 | 400 | 8500 | 137.14 | 5250 | 4350 | 900 | 279 | 280 | 185 | 165
08/22/2021 | 09:30 | 10:05 | 0.58333 | 14329 | 14424 | 95 | Rotate |  | 14363 | 85.62 | 153.8 | 11477.47 | -3265.15 | 2511.1 | -3265.15 | 0.05 |  |  | 32 | 80 | 400 | 8500 | 162.86 | 5250 | 4350 | 900 | 288 | 280 | 185 | 165
08/22/2021 | 10:10 | 10:45 | 0.58333 | 14424 | 14519 | 95 | Rotate |  | 14458 | 85.39 | 153.92 | 11484.92 | -3350.17 | 2552.83 | -3350.17 | 0.27 |  |  | 32 | 80 | 400 | 8500 | 162.86 | 5250 | 4350 | 900 | 288 | 280 | 185 | 165
08/22/2021 | 10:50 | 11:20 | 0.5 | 14519 | 14613 | 94 | Rotate |  | 14552 | 85.51 | 153.61 | 11492.38 | -3434.22 | 2594.25 | -3434.22 | 0.35 |  |  | 32 | 80 | 400 | 8500 | 188 | 5250 | 4350 | 900 | 291 | 280 | 185 | 165
08/22/2021 | 11:25 | 12:00 | 0.58333 | 14613 | 14708 | 95 | Rotate |  | 14647 | 85.7 | 153.6 | 11499.66 | -3519.07 | 2636.36 | -3519.07 | 0.2 |  |  | 32 | 80 | 400 | 10000 | 162.86 | 5300 | 4450 | 850 | 293 | 280 | 185 | 165
08/22/2021 | 12:05 | 12:45 | 0.66667 | 14708 | 14803 | 95 | Rotate |  | 14742 | 88.01 | 154.35 | 11504.87 | -3604.3 | 2677.97 | -3604.3 | 2.56 |  |  | 32 | 80 | 400 | 10000 | 142.5 | 5300 | 4450 | 850 | 293 | 280 | 185 | 165
08/22/2021 | 12:50 | 13:15 | 0.41667 | 14803 | 14823 | 20 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 48 | 5300 | 4450 | 850 | 293 | 280 | 185 | 165
08/22/2021 | 13:15 | 13:50 | 0.58333 | 14823 | 14895 | 72 | Rotate |  | 14834 | 85.89 | 153.98 | 11509.76 | -3686.98 | 2718 | -3686.98 | 2.34 |  |  | 32 | 80 | 400 | 10000 | 123.43 | 5300 | 4450 | 850 | 293 | 280 | 185 | 165
08/22/2021 | 13:55 | 14:30 | 0.58333 | 14895 | 14989 | 94 | Rotate |  | 14928 | 86.05 | 154.14 | 11516.37 | -3771.3 | 2759.02 | -3771.3 | 0.24 |  |  | 32 | 80 | 400 | 10000 | 161.14 | 5300 | 4450 | 850 | 293 | 280 | 185 | 165
08/22/2021 | 14:35 | 14:45 | 0.16667 | 14989 | 14999 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 60 | 5300 | 4450 | 850 | 293 | 280 | 185 | 165
08/22/2021 | 14:45 | 15:25 | 0.66667 | 14999 | 15084 | 85 | Rotate |  | 15023 | 84.8 | 153.39 | 11523.95 | -3856.24 | 2800.88 | -3856.24 | 1.53 |  |  | 32 | 80 | 400 | 10000 | 127.5 | 5550 | 4850 | 700 | 293 | 280 | 185 | 165
08/22/2021 | 15:30 | 16:15 | 0.75 | 15084 | 15178 | 94 | Rotate |  | 15117 | 85.2 | 153.11 | 11532.14 | -3939.86 | 2843.03 | -3939.86 | 0.52 |  |  | 32 | 80 | 400 | 10000 | 125.33 | 5550 | 4850 | 700 | 297 | 280 | 185 | 165
08/22/2021 | 16:20 | 17:00 | 0.66667 | 15178 | 15274 | 96 | Rotate |  | 15213 | 86.97 | 154.37 | 11538.69 | -4025.75 | 2885.4 | -4025.75 | 2.26 |  |  | 32 | 80 | 400 | 11000 | 144 | 5550 | 4850 | 700 | 298 | 280 | 185 | 165
08/22/2021 | 17:05 | 17:50 | 0.75 | 15274 | 15368 | 94 | Rotate |  | 15307 | 88.26 | 154.1 | 11542.61 | -4110.33 | 2926.23 | -4110.33 | 1.4 |  |  | 32 | 80 | 400 | 11000 | 125.33 | 5550 | 4850 | 700 | 298 | 280 | 185 | 165
08/22/2021 | 17:55 | 18:02 | 0.11667 | 15368 | 15382 | 14 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 120 | 5550 | 4850 | 700 | 298 | 280 | 175 | 155
08/22/2021 | 18:02 | 18:28 | 0.43333 | 15382 | 15400 | 18 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 41.54 | 5550 | 4850 | 700 | 298 | 280 | 185 | 165
08/22/2021 | 18:28 | 18:36 | 0.13333 | 15400 | 15422 | 22 | Rotate |  | 15402 | 87.35 | 153.43 | 11546.24 | -4195.48 | 2968.19 | -4195.48 | 1.19 |  |  | 32 | 80 | 400 | 11000 | 165 | 5550 | 4850 | 700 | 300 | 280 | 185 | 165
08/22/2021 | 18:52 | 19:14 | 0.36667 | 15422 | 15463 | 41 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 111.82 | 5550 | 4850 | 700 | 300 | 280 | 185 | 165
08/22/2021 | 19:17 | 19:29 | 0.2 | 15463 | 15478 | 15 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 75 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 19:29 | 19:51 | 0.36667 | 15478 | 15498 | 20 | Slide | 180 | 15497 | 85.58 | 152.26 | 11552.1 | -4279.84 | 3011.46 | -4279.84 | 2.23 |  |  | 32 | 80 | 400 | 6500 | 54.55 | 5250 | 4850 | 400 | 301 | 280 | 185 | 165
08/22/2021 | 19:51 | 20:22 | 0.51667 | 15498 | 15558 | 60 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 116.13 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 20:25 | 21:14 | 0.81667 | 15558 | 15652 | 94 | Rotate |  | 15591 | 85.67 | 151.95 | 11559.27 | -4362.68 | 3055.31 | -4362.68 | 0.34 |  |  | 32 | 80 | 400 | 11000 | 115.1 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 21:17 | 22:02 | 0.75 | 15652 | 15747 | 95 | Rotate |  | 15686 | 86.15 | 152.06 | 11566.05 | -4446.35 | 3099.79 | -4446.35 | 0.52 |  |  | 32 | 80 | 400 | 11000 | 126.67 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 22:05 | 22:50 | 0.75 | 15747 | 15841 | 94 | Rotate |  | 15780 | 87.08 | 152.45 | 11571.6 | -4529.39 | 3143.47 | -4529.39 | 1.07 |  |  | 32 | 80 | 400 | 11000 | 125.33 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 22:53 | 23:38 | 0.75 | 15841 | 15935 | 94 | Rotate |  | 15874 | 87.79 | 152.52 | 11575.8 | -4612.68 | 3186.86 | -4612.68 | 0.76 |  |  | 32 | 80 | 400 | 11000 | 125.33 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 23:41 | 23:51 | 0.16667 | 15935 | 15951 | 16 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 96 | 5550 | 4850 | 700 | 301 | 280 | 185 | 165
08/22/2021 | 23:51 | 24:00 | 0.15 | 15951 | 15960 | 9 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 60 | 5350 | 4850 | 500 | 301 | 280 | 185 | 165
08/23/2021 | 00:00 | 00:24 | 0.4 | 15960 | 15969 | 9 | Slide | 180 | 15968 | 86.29 | 152.66 | 11580.66 | -4696.01 | 3230.07 | -4696.01 | 1.6 |  |  | 40 | 80 | 400 | 6500 | 22.5 | 5350 | 4850 | 500 | 301 | 280 | 185 | 165
08/23/2021 | 00:24 | 00:55 | 0.51667 | 15969 | 16029 | 60 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 116.13 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 00:58 | 01:07 | 0.15 | 16029 | 16048 | 19 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 126.67 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 01:07 | 01:19 | 0.2 | 16048 | 16056 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 40 | 5350 | 4850 | 500 | 303 | 280 | 185 | 165
08/23/2021 | 01:19 | 01:56 | 0.61667 | 16056 | 16124 | 68 | Rotate |  | 16063 | 85.33 | 152.6 | 11587.6 | -4780.15 | 3273.63 | -4780.15 | 1.01 |  |  | 32 | 80 | 400 | 11500 | 110.27 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 01:59 | 02:48 | 0.81667 | 16124 | 16219 | 95 | Rotate |  | 16158 | 85.42 | 152.19 | 11595.26 | -4864.06 | 3317.5 | -4864.06 | 0.44 |  |  | 32 | 80 | 400 | 11500 | 116.33 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 02:51 | 03:38 | 0.78333 | 16219 | 16313 | 94 | Rotate |  | 16252 | 86.36 | 152.79 | 11602 | -4947.22 | 3360.81 | -4947.22 | 1.19 |  |  | 32 | 80 | 400 | 11500 | 120 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 03:41 | 04:29 | 0.8 | 16313 | 16408 | 95 | Rotate |  | 16347 | 87.43 | 153.35 | 11607.14 | -5031.79 | 3403.77 | -5031.79 | 1.27 |  |  | 32 | 80 | 400 | 11500 | 118.75 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 05:16 | 05:22 | 0.1 | 16408 | 16420 | 12 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11500; Drilling Parameters ROP: 120 | 5550 | 4850 | 700 | 303 | 280 | 185 | 165
08/23/2021 | 05:25 | 05:45 | 0.33333 | 16420 | 16433 | 13 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8100; Drilling Parameters ROP: 39 | 5350 | 4850 | 500 | 303 | 280 | 185 | 165
08/23/2021 | 05:45 | 06:30 | 0.75 | 16433 | 16501 | 68 | Rotate |  | 16440 | 85.99 | 152.73 | 11612.48 | -5114.54 | 3445.86 | -5114.54 | 1.69 |  |  | 32 | 80 | 400 | 11500 | 90.67 | 5350 | 4850 | 500 | 303 | 280 | 185 | 165
08/23/2021 | 06:35 | 07:25 | 0.83333 | 16501 | 16595 | 94 | Rotate |  | 16534 | 86.75 | 152.95 | 11618.43 | -5198.01 | 3488.69 | -5198.01 | 0.84 |  |  | 28 | 80 | 400 | 11500 | 112.8 | 5350 | 4850 | 500 | 303 | 280 | 185 | 165
08/23/2021 | 07:30 | 07:55 | 0.41667 | 16595 | 16605 | 10 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11500; Drilling Parameters ROP: 24 | 5350 | 4850 | 500 | 303 | 280 | 185 | 165
08/23/2021 | 07:55 | 08:40 | 0.75 | 16605 | 16688 | 83 | Rotate |  | 16627 | 85.41 | 153.16 | 11624.79 | -5280.72 | 3530.73 | -5280.72 | 1.46 |  |  | 28 | 80 | 400 | 14000 | 110.67 | 5450 | 4900 | 550 | 303 | 280 | 185 | 165
08/23/2021 | 08:45 | 09:40 | 0.91667 | 16688 | 16783 | 95 | Rotate |  | 16722 | 87.13 | 154.02 | 11630.97 | -5365.62 | 3572.89 | -5365.62 | 2.02 |  |  | 28 | 80 | 400 | 14000 | 103.64 | 5450 | 4900 | 550 | 303 | 280 | 185 | 165
08/23/2021 | 09:45 | 10:15 | 0.5 | 16783 | 16798 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 30 | 5450 | 4900 | 550 | 303 | 280 | 185 | 165
08/23/2021 | 10:15 | 11:05 | 0.83333 | 16798 | 16877 | 79 | Rotate |  | 16816 | 83.63 | 152.51 | 11638.54 | -5449.28 | 3615.03 | -5449.28 | 4.05 |  |  | 28 | 80 | 400 | 14500 | 94.8 | 5450 | 4900 | 550 | 304 | 280 | 185 | 165
08/23/2021 | 11:10 | 12:00 | 0.83333 | 16877 | 16892 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14500; Drilling Parameters ROP: 18 | 5450 | 4900 | 550 | 304 | 280 | 185 | 165
08/23/2021 | 12:00 | 12:40 | 0.66667 | 16892 | 16972 | 80 | Rotate |  | 16911 | 85.5 | 152.78 | 11647.54 | -5533.28 | 3658.49 | -5533.28 | 1.99 |  |  | 28 | 80 | 400 | 14500 | 120 | 5450 | 4900 | 550 | 304 | 280 | 185 | 165
08/23/2021 | 12:45 | 13:40 | 0.91667 | 16972 | 17067 | 95 | Rotate |  | 17006 | 86.06 | 153.57 | 11654.53 | -5617.82 | 3701.24 | -5617.82 | 1.02 |  |  | 28 | 80 | 400 | 17500 | 103.64 | 5450 | 4900 | 550 | 304 | 280 | 185 | 165
08/23/2021 | 13:45 | 14:45 | 1 | 17067 | 17161 | 94 | Rotate |  | 17100 | 86.56 | 155.35 | 11660.58 | -5702.46 | 3741.68 | -5702.46 | 1.96 |  |  | 28 | 80 | 400 | 17500 | 94 | 5450 | 4900 | 550 | 309 | 280 | 185 | 165
08/23/2021 | 14:50 | 15:25 | 0.58333 | 17161 | 17176 | 15 | Slide | TTF: 90; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14500; Drilling Parameters ROP: 25.71 | 5450 | 4900 | 550 | 309 | 280 | 185 | 165
08/23/2021 | 15:25 | 16:15 | 0.83333 | 17176 | 17256 | 80 | Rotate |  | 17195 | 86.63 | 154.94 | 11666.22 | -5788.51 | 3781.54 | -5788.51 | 0.44 |  |  | 28 | 80 | 400 | 17500 | 96 | 5450 | 4900 | 550 | 309 | 280 | 185 | 165
08/23/2021 | 17:05 | 17:45 | 0.66667 | 17256 | 17271 | 15 | Slide | TTF: 60; Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 22.5 | 5250 | 4900 | 350 | 309 | 280 | 185 | 165
08/23/2021 | 17:45 | 18:50 | 1.0833 | 17271 | 17351 | 80 | Rotate |  | 17290 | 87.1 | 152.89 | 11671.42 | -5873.7 | 3823.25 | -5873.7 | 2.21 |  |  | 28 | 80 | 400 | 17500 | 73.85 | 5450 | 4900 | 550 | 309 | 280 | 185 | 165
08/23/2021 | 18:53 | 20:04 | 1.1833 | 17351 | 17446 | 95 | Rotate |  | 17385 | 88.65 | 152.48 | 11674.94 | -5958.05 | 3866.81 | -5958.05 | 1.69 |  |  | 28 | 80 | 400 | 17500 | 80.28 | 5450 | 4900 | 550 | 309 | 280 | 185 | 165
08/23/2021 | 20:07 | 20:33 | 0.43333 | 17446 | 17465 | 19 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 43.85 | 5450 | 4900 | 550 | 309 | 280 | 185 | 165
08/23/2021 | 20:33 | 21:20 | 0.78333 | 17465 | 17480 | 15 | Slide | 180 | 17479 | 88.57 | 152.6 | 11677.22 | -6041.43 | 3910.14 | -6041.43 | 0.15 |  |  | 28 | 80 | 400 | 11500 | 19.15 | 5250 | 4900 | 350 | 309 | 280 | 185 | 165
08/23/2021 | 21:20 | 22:08 | 0.8 | 17480 | 17540 | 60 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 75 | 5500 | 4900 | 600 | 309 | 280 | 185 | 165
08/23/2021 | 22:11 | 22:26 | 0.25 | 17540 | 17554 | 14 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 56 | 5500 | 4900 | 600 | 311 | 280 | 185 | 165 | Torque dropped and range was tighter (11,300 - 13,500) 17,546
08/23/2021 | 22:26 | 23:24 | 0.96667 | 17554 | 17574 | 20 | Slide | 180 | 17574 | 86.35 | 153.83 | 11681.43 | -6126.15 | 3952.91 | -6126.15 | 2.67 |  |  | 28 | 80 | 400 | 8500 | 20.69 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/23/2021 | 23:24 | 24:00 | 0.6 | 17574 | 17615 | 41 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 68.33 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 00:00 | 00:16 | 0.26667 | 17615 | 17635 | 20 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 75 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 00:19 | 01:36 | 1.2833 | 17635 | 17729 | 94 | Rotate |  | 17668 | 86.2 | 154.14 | 11687.54 | -6210.44 | 3994.05 | -6210.44 | 0.37 |  |  | 28 | 80 | 400 | 17500 | 73.25 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165 | Torque jumped up when cutting down in section.
08/24/2021 | 01:39 | 02:59 | 1.3333 | 17729 | 17824 | 95 | Rotate |  | 17763 | 87.04 | 154.3 | 11693.14 | -6295.84 | 4035.3 | -6295.84 | 0.9 |  |  | 28 | 80 | 400 | 17500 | 71.25 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 03:02 | 03:17 | 0.25 | 17824 | 17836 | 12 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 48 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 03:17 | 04:03 | 0.76667 | 17836 | 17851 | 15 | Slide | TTF: -150; Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 11500; Drilling Parameters ROP: 19.57 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 04:03 | 05:03 | 1 | 17851 | 17919 | 68 | Rotate |  | 17858 | 86.26 | 153.08 | 11698.69 | -6380.85 | 4077.33 | -6380.85 | 1.52 |  |  | 28 | 80 | 400 | 8500 | 68 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 05:08 | 05:18 | 0.16667 | 17919 | 17925 | 6 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 36 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 05:18 | 06:00 | 0.7 | 17925 | 17930 | 5 | Slide | TTF: 200; Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 7.14 | 5300 | 4900 | 400 | 311 | 280 | 185 | 165
08/24/2021 | 06:00 | 06:30 | 0.5 | 17930 | 17945 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 30 | 5300 | 4900 | 400 |  | 280 | 185 | 165

## BHA_7_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 7 |  |  |  |  | RKB: |  |  |  | 387 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2569
Site: |  |  |  |  | Rommel-Redwood - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 148
Well Name: |  |  |  |  | Rommel 3H |  |  | Survey / Gamma Offset: |  |  |  |  | 68.00 / 57.00 |  |  |  |  | Grid Conv: |  |  |  | 387 |  | VS Azimuth: |  | 152.56 |  | Rotate: |  | 2421
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
08/27/2021 | 02:47 | 04:36 | 1.8167 | 17945 | 18051 | 106 | Rotate |  | 17983 | 87.17 | 152.41 | 11705.85 | -6491.79 | 4134.48 | -6491.79 | 0.9 |  |  | 12 | 80 | 352 | 10770 | 58.35 | 5565 | 4950 | 615 | 312 | 280 | 188 | 168
08/27/2021 | 04:39 | 04:46 | 0.11667 | 18051 | 18060 | 9 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 352; Drilling Parameters Tq: 10770; Drilling Parameters ROP: 77.14 | 5565 | 4950 | 615 | 312 | 280 | 188 | 168
08/27/2021 | 04:46 | 05:07 | 0.35 | 18060 | 18075 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 352; Drilling Parameters Tq: 8.3; Drilling Parameters ROP: 42.86 | 5250 | 4950 | 300 | 316 | 280 | 188 | 168
08/27/2021 | 05:07 | 05:43 | 0.6 | 18075 | 18145 | 70 | Rotate |  | 18077 | 85.37 | 151.96 | 11711.97 | -6574.75 | 4178.25 | -6574.75 | 1.97 |  |  | 38 | 80 | 352 | 8.3 | 116.67 | 5530 | 4950 | 580 | 316 | 280 | 188 | 168
08/27/2021 | 05:46 | 06:40 | 0.9 | 18145 | 18241 | 96 | Rotate |  | 18173 | 86.81 | 152.69 | 11718.51 | -6659.56 | 4222.73 | -6659.56 | 1.68 |  |  | 25 | 80 | 352 | 11.5 | 106.67 | 5800 | 5150 | 650 | 316 | 310 | 205 | 150
08/27/2021 | 06:45 | 07:15 | 0.5 | 18241 | 18256 | 15 | Slide | TTF: -130; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 352; Drilling Parameters ROP: 30 | 5400 | 5150 | 250 | 316 | 310 | 205 | 150
08/27/2021 | 07:15 | 07:50 | 0.58333 | 18256 | 18335 | 79 | Rotate |  | 18267 | 84.3 | 152.45 | 11725.8 | -6742.74 | 4265.9 | -6742.74 | 2.68 |  |  | 25 | 80 | 352 | 12.2 | 135.43 | 5800 | 5150 | 650 | 316 | 310 | 205 | 150
08/27/2021 | 07:55 | 08:35 | 0.66667 | 18335 | 18430 | 95 | Rotate |  | 18362 | 83.92 | 152.3 | 11735.55 | -6826.46 | 4309.71 | -6826.46 | 0.43 |  |  | 25 | 80 | 352 | 11.5 | 142.5 | 5800 | 5150 | 650 | 316 | 310 | 205 | 150
08/27/2021 | 08:45 | 09:30 | 0.75 | 18430 | 18525 | 95 | Rotate |  | 18457 | 83.52 | 152.12 | 11745.94 | -6910 | 4353.74 | -6910 | 0.46 |  |  | 30 | 80 | 352 | 17.4 | 126.67 | 5800 | 5150 | 650 | 320 | 310 | 205 | 150
08/27/2021 | 09:36 | 09:42 | 0.1 | 18525 | 18536 | 11 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 352; Drilling Parameters Tq: 17.5; Drilling Parameters ROP: 110 | 5900 | 5150 | 750 | 322 | 310 | 205 | 150
08/27/2021 | 09:42 | 10:06 | 0.4 | 18536 | 18548 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 352; Drilling Parameters ROP: 30 | 5350 | 5150 | 200 | 322 | 310 | 205 | 150
08/27/2021 | 10:06 | 10:32 | 0.43333 | 18548 | 18619 | 71 | Rotate |  | 18551 | 84.65 | 152.96 | 11755.62 | -6992.97 | 4396.85 | -6992.97 | 1.5 |  |  | 30 | 80 | 352 | 14.8 | 163.85 | 5900 | 5150 | 750 | 324 | 310 | 205 | 150
08/27/2021 | 10:37 | 11:10 | 0.55 | 18619 | 18712 | 93 | Rotate |  | 18644 | 84.99 | 153.32 | 11764.02 | -7075.59 | 4438.7 | -7075.59 | 0.53 |  |  | 30 | 80 | 352 | 14.9 | 169.09 | 5900 | 5150 | 750 | 325 | 310 | 205 | 150
08/27/2021 | 11:20 | 11:30 | 0.16667 | 18712 | 18722 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 352; Drilling Parameters Tq: 14.9; Drilling Parameters ROP: 60 | 5900 | 5150 | 750 | 325 | 310 | 205 | 150
08/27/2021 | 11:30 | 11:50 | 0.33333 | 18722 | 18732 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 352; Drilling Parameters ROP: 30 | 5300 | 5150 | 150 | 325 | 310 | 205 | 150
08/27/2021 | 11:50 | 12:20 | 0.5 | 18732 | 18808 | 76 | Rotate |  | 18740 | 86.01 | 151.1 | 11771.55 | -7160.25 | 4483.32 | -7160.25 | 2.54 |  |  | 32 | 80 | 352 | 15.28 | 152 | 5900 | 5150 | 750 | 325 | 310 | 205 | 150
08/27/2021 | 12:25 | 13:00 | 0.58333 | 18808 | 18900 | 92 | Rotate |  | 18832 | 85.99 | 151.23 | 11777.97 | -7240.65 | 4527.58 | -7240.65 | 0.14 |  |  | 32 | 80 | 352 | 15.4 | 157.71 | 5900 | 5150 | 750 | 327 | 310 | 205 | 150
08/27/2021 | 13:05 | 13:10 | 0.083333 | 18900 | 18910 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 352; Drilling Parameters Tq: 16.2; Drilling Parameters ROP: 120 | 5900 | 5150 | 750 | 327 | 310 | 205 | 150
08/27/2021 | 13:10 | 13:33 | 0.38333 | 18910 | 18918 | 8 | Slide | TTF: 30; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 352; Drilling Parameters ROP: 20.87 | 5400 | 5150 | 250 | 327 | 310 | 205 | 150
08/27/2021 | 13:33 | 14:00 | 0.45 | 18918 | 18994 | 76 | Rotate |  | 18926 | 88.75 | 152.36 | 11782.28 | -7323.39 | 4571.95 | -7323.39 | 3.17 |  |  | 32 | 80 | 352 | 16.33 | 168.89 | 5900 | 5150 | 750 | 327 | 310 | 205 | 150
08/27/2021 | 14:05 | 14:12 | 0.11667 | 18994 | 19006 | 12 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 352; Drilling Parameters Tq: 16.33; Drilling Parameters ROP: 102.86 | 5900 | 5150 | 750 | 327 | 310 | 205 | 150
08/27/2021 | 14:12 | 14:40 | 0.46667 | 19006 | 19021 | 15 | Slide | 180 | 19020 | 87.11 | 153.11 | 11785.68 | -7406.89 | 4614.99 | -7406.89 | 1.92 |  |  | 20 |  | 352 |  | 32.14 | 5450 | 5150 | 300 | 325 | 310 | 205 | 150
08/27/2021 | 14:40 | 15:10 | 0.5 | 19021 | 19088 | 67 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 134 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150
08/27/2021 | 15:15 | 16:20 | 1.0833 | 19088 | 19183 | 95 | Rotate |  | 19115 | 87.85 | 154.13 | 11789.86 | -7491.91 | 4657.16 | -7491.91 | 1.33 |  |  | 32 | 70 | 330 | 12.3 | 87.69 | 5391 | 4630 | 761 | 329 | 310 | 205 | 150
08/27/2021 | 17:25 | 17:35 | 0.16667 | 19183 | 19193 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 12.3; Drilling Parameters ROP: 60 | 5391 | 4630 | 761 | 320 | 310 | 205 | 150
08/27/2021 | 17:35 | 17:55 | 0.33333 | 19193 | 19205 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters FLOW: 330; Drilling Parameters ROP: 36 | 4850 | 4630 | 220 | 320 | 310 | 205 | 150
08/27/2021 | 17:55 | 18:25 | 0.5 | 19205 | 19278 | 73 | Rotate |  | 19210 | 84.98 | 153.46 | 11795.8 | -7576.97 | 4699.02 | -7576.97 | 3.1 |  |  | 32 | 70 | 330 | 14.25 | 876 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150
08/27/2021 | 18:28 | 18:45 | 0.28333 | 19278 | 19285 | 7 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 24.71 | 5391 | 4630 | 761 | 327.2 | 310 | 205 | 150
08/27/2021 | 18:45 | 19:08 | 0.38333 | 19285 | 19300 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 11500; Drilling Parameters ROP: 39.13 | 5130 | 4630 | 500 | 325 | 310 | 205 | 150
08/27/2021 | 19:08 | 19:40 | 0.53333 | 19300 | 19373 | 73 | Rotate |  | 19305 | 87.32 | 155.14 | 11802.18 | -7662.37 | 4740.12 | -7662.37 | 3.03 |  |  | 32 | 70 | 330 | 14.25 | 136.87 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150 | Backed off RPM, attempt to control temperature
08/27/2021 | 19:43 | 20:36 | 0.88333 | 19373 | 19467 | 94 | Rotate |  | 19399 | 88.27 | 153.81 | 11805.79 | -7747.13 | 4780.59 | -7747.13 | 1.74 |  |  | 32 | 70 | 330 | 14.25 | 106.42 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150 | Decreasing RPM after sliding up resulted in 1.8 deg of rotational build.
08/27/2021 | 20:39 | 21:33 | 0.9 | 19467 | 19562 | 95 | Rotate |  | 19494 | 90.01 | 153.72 | 11807.22 | -7832.33 | 4822.58 | -7832.33 | 1.83 |  |  | 32 | 70 | 330 | 14.25 | 105.56 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150
08/27/2021 | 21:36 | 21:49 | 0.21667 | 19562 | 19570 | 8 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 36.92 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150
08/27/2021 | 21:49 | 22:22 | 0.55 | 19570 | 19588 | 18 | Slide | TTF: -160; Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 32.73 | 5130 | 4630 | 500 | 325.4 | 310 | 205 | 150 | Lower RPM continued to build in rotation supressing the motor yield when sliding down.
08/27/2021 | 22:22 | 22:58 | 0.6 | 19588 | 19657 | 69 | Rotate |  | 19589 | 88.92 | 152.63 | 11808.11 | -7917.11 | 4865.45 | -7917.11 | 1.62 |  |  | 32 | 70 | 330 | 14.25 | 115 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150
08/27/2021 | 23:01 | 23:19 | 0.3 | 19657 | 19673 | 16 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 53.33 | 5391 | 4630 | 761 | 327 | 310 | 205 | 150
08/27/2021 | 23:19 | 23:51 | 0.53333 | 19673 | 19693 | 20 | Slide | -160 | 19683 | 87.72 | 150.53 | 11810.86 | -7999.73 | 4910.16 | -7999.73 | 2.57 |  |  | 32 | 70 | 330 | 14.25 | 37.5 | 5130 | 4630 | 500 | 325.4 | 310 | 205 | 150 | Lower RPM continued to build in rotation supressing the motor yield when sliding down.
08/27/2021 | 23:51 | 24:00 | 0.15 | 19693 | 19700 | 7 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 46.67 | 5250 | 4630 | 620 | 325.4 | 310 | 205 | 150
08/28/2021 | 00:00 | 00:23 | 0.38333 | 19700 | 19751 | 51 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 133.04 | 5350 | 4630 | 720 | 325.4 | 310 | 205 | 150
08/28/2021 | 00:26 | 00:34 | 0.13333 | 19751 | 19761 | 10 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 75 | 5230 | 4580 | 650 | 327.2 | 310 | 205 | 150 | Decreased differential, attempt to control temperature gain.
08/28/2021 | 00:34 | 01:00 | 0.43333 | 19761 | 19776 | 15 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 10800; Drilling Parameters ROP: 34.62 | 5160 | 4580 | 580 | 325.4 | 310 | 205 | 150
08/28/2021 | 01:00 | 01:35 | 0.58333 | 19776 | 19846 | 70 | Rotate |  | 19778 | 85.2 | 151.41 | 11816.73 | -8082.63 | 4956.17 | -8082.63 | 2.81 |  |  | 32 | 70 | 330 | 16500 | 120 | 5230 | 4580 | 650 | 329 | 310 | 205 | 150
08/28/2021 | 01:38 | 01:50 | 0.2 | 19846 | 19865 | 19 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 95 | 5230 | 4580 | 650 | 329 | 310 | 205 | 150
08/28/2021 | 01:50 | 02:06 | 0.26667 | 19865 | 19870 | 5 | Slide | TTF: 180; Drilling Parameters WOB: 32; Drilling Parameters RPM: 70; Drilling Parameters FLOW: 330; Drilling Parameters Tq: 14.25; Drilling Parameters ROP: 18.75 | 5230 | 4580 | 650 | 329 | 310 | 205 | 150 | The lower RPM rotational build was offset when differential was lowered. During the slide continous inclintion indicated the wellbore was dropping in rotation and slide was cut short.
08/28/2021 | 02:09 | 02:48 | 0.65 | 19870 | 19941 | 71 | Rotate |  | 19873 | 84.83 | 150.91 | 11824.98 | -8165.54 | 5001.82 | -8165.54 | 0.65 |  |  | 32 | 70 | 330 | 14.25 | 109.23 | 5230 | 4580 | 650 | 329 | 310 | 205 | 150
08/28/2021 | 02:51 | 03:49 | 0.96667 | 19941 | 20035 | 94 | Rotate |  | 19967 | 84.81 | 151.53 | 11833.47 | -8247.59 | 5046.89 | -8247.59 | 0.66 |  |  | 32 | 70 | 330 | 14.25 | 97.24 | 5230 | 4580 | 650 | 331 | 310 | 205 | 150
08/28/2021 | 03:51 | 04:52 | 1.0167 | 20035 | 20130 | 95 | Rotate |  | 20062 | 85.07 | 151.25 | 11841.85 | -8330.66 | 5092.21 | -8330.66 | 0.4 |  |  | 32 | 70 | 330 | 14.25 | 93.44 | 5230 | 4580 | 650 | 331 | 310 | 205 | 150
08/28/2021 | 04:55 | 05:46 | 0.85 | 20130 | 20222 | 92 | Rotate |  | 20154 | 85.55 | 151.41 | 11849.37 | -8411.11 | 5136.2 | -8411.11 | 0.55 |  |  | 32 | 70 | 330 | 14.25 | 108.24 | 5230 | 4580 | 650 | 331 | 310 | 205 | 150
08/28/2021 | 05:49 | 06:45 | 0.93333 | 20222 | 20317 | 95 | Rotate |  | 20249 | 86.43 | 152.12 | 11856.01 | -8494.6 | 5181.03 | -8494.6 | 1.19 |  |  | 32 | 70 | 330 | 16.3 | 101.79 | 5230 | 4580 | 650 | 333 | 315 | 205 | 150
08/28/2021 | 06:50 | 07:50 | 1 | 20317 | 20412 | 95 | Rotate |  | 20344 | 87.7 | 153.17 | 11860.88 | -8578.87 | 5224.62 | -8578.87 | 1.73 |  |  | 32 | 70 | 330 | 15.53 | 95 | 5230 | 4580 | 650 | 333 | 315 | 205 | 150
08/28/2021 | 08:05 | 09:10 | 1.0833 | 20412 | 20514 | 102 | Rotate |  | 20439 | 86.97 | 152.22 | 11865.3 | -8663.19 | 5268.15 | -8663.19 | 1.26 |  |  | 32 | 70 | 330 | 15.5 | 94.15 | 5230 | 4580 | 650 | 333 | 315 | 205 | 150