## Summary
Magnolia Oil & Gas / Sabine D 4H / LTX1100921 / Patterson 248
Report Date: | 03/17/2021 | Current Depth: | 15209
Start Date: | 01/16/2021 | Casing Depth: | 10148
Daily Cost: | 9250 | Distance to TD:
Well Cost: | 124730 | Average ROP: | 58.55
Drilling Hours: | 47.07 | Svy MD: | 15136
24Hr Forcast: | SideTrack and cont Drilling ahead | Svy Inc: | 86.26
Current BHA: | BHA 5 | Svy Azi: | 136.43
Current BRT Hrs: | 69.83 | Svy TVD: | 10751.69
Bit Make / Model: | Security / GTD64M | Svy NS: | -2154.89
POOH in last 24Hrs: | No | Svy EW: | 2300.74
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Nathan Marks | MWD Day: | Russell Arnold
Directional Driller Night: | Jesse Taylor | MWD Night: | Ramon Reis
RSS Engineer 1: | NA | Third Man: | NA
RSS Engineer 2: | NA | Fourth Man: | NA
Principal Plan: |  | Max BHT Well: | 288
24Hr Summary: | Drill lateral section, Prepare to ST | Max BHT 24Hrs: | 288
Comments
Current Target= 10499 0 V/S @ 85.21?- 0 Up 10 Down
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
500043 | UBHO |  |  | Dirty |  | 16.67 | 16.67
500029 | Pro UBHO |  |  | Clean
500042 | UBHO |  |  | Dirty |  | 52.93 | 52.93
500033 | UBHO |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Sabine D 4H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Total Drilled (Usft): |  | 15104 |  |  | Total Days: |  | 12
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 1 | 13.5 | 105 | 2916 | 2811 |  | 575.63 |  | 14.94 | 4.88 | 5.82 | 11.2
2 | 2 | 9.875 | 2916 | 9904 | 6988 |  | 239.59 |  | 6.7 | 29.17 | 31.17 | 53.92
3 | 2 | 9.875 | 9904 | 10171 | 267 |  | 51.51 |  | 55.81 | 5.18 | 6.42 | 17
4 | 3 | 6.75 | 10171 | 10920 | 749 |  | 63.12 |  | 68.89 | 11.87 | 16.67 | 46.83
5 | 3 | 6.75 | 10920 | 15209 | 4289 |  | 91.13 |  | 18.16 | 47.07 | 52.93 | 69.83
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
1 | Ulterra |  | U616S |  | 13.5 | New |  |  |  | 1.178 | 2811 | 4.8833 | 575.63
2 | Ulterra |  | SPL613 |  | 9.875 | New |  |  |  | 1.491 | 6988 | 29.1667 | 239.59
2 | Ulterra |  | SPL613 |  | 9.875 | New |  |  |  | 1.491 | 267 | 5.1833 | 51.51
3 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 749 | 11.8667 | 63.12
3 | Security |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 4289 | 47.0667 | 91.13
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 1.5 | 6.01 | 2811 |  | 575.63
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 2 | 5.9 | 6988 |  | 239.59
3 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 8 | 2 | 5.9 | 267 |  | 51.51
4 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2 | 4.03 | 749 |  | 63.12
5 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.8 | 5.5 | 2 | 4.1 | 4289 |  | 91.13
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Nathan Marks |  | Billy McFarland |  | Russell Arnold |  | Jeff Campbell |  | Jim |  | James Dyer |  | David LeBlanc
|  | Chris Day |  |  |  | Ramon Reis
Chris Day Jesse Taylor
Jesse Taylor
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.29 |  | 2811 |  | 571.34 |  |  |  | 1 |  | 4.92
INT: INTERMEDIATE |  |  | 4.00 / 2.52 |  | 7255 |  | 211.15 |  | 2.15 / 0.00 |  | 2 |  | 34.36
CRV: CURVE |  |  | 2.92 / 0.60 |  | 749 |  | 63.21 |  | 19.25 / 0.00 |  | 1 |  | 11.85
LAT: LATERAL |  |  | 3.08 / 2.30 |  | 4289 |  | 91.12 |  |  |  | 1 |  | 47.07
Total |  |  | 12.01 |  | 15104 |  | 153.81 |  | 21.40 / 0.00 |  | 5 |  | 98.2
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 |  |  | 105.00 | 2916.00 | 1004.62 | 2391.00 | 165.35 | 420.00 | 14.94 | 2811.00 | 571.34 | 4.92 | 2.54
INT: INTERMEDIATE-BHA 2 |  |  | 2916.00 | 9904.00 | 308.57 | 6520.00 | 58.14 | 468.00 | 6.70 | 6988.00 | 239.48 | 29.18 | 8.05
INT: INTERMEDIATE-BHA 3 |  |  | 9904.00 | 10171.00 | 88.72 | 118.00 | 38.70 | 149.00 | 55.81 | 267.00 | 51.54 | 5.18 | 3.85
CRV: CURVE-BHA 4 |  |  | 10171.00 | 10920.00 | 128.73 | 233.00 | 51.39 | 516.00 | 68.89 | 749.00 | 63.21 | 11.85 | 10.04
LAT: LATERAL-BHA 5 |  |  | 10920.00 | 15209.00 | 181.40 | 3510.00 | 28.10 | 779.00 | 18.16 | 4289.00 | 91.12 | 47.07 | 27.72
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1100921 | Total Drilled(Usft) | 15104.00
Operator | Magnolia Oil & Gas | Drilling Hours | 98.17
Well Name | Sabine D 4H | Avg ROP(Usft/hr) | 153.86
Rig | Patterson 248 | Rotary Drilled(Usft) | 12772.00
State | Texas | Rotary Hours | 45.95
County | Washington | Rotary ROP(Usft/hr) | 277.95
Formation | Austin Chalk | Rotary % | 84.56
Start Date | 01/16/2021 | Slide Drilled(Usft) | 2332.00
End Date | 03/17/2021 | Slide Hours | 52.22
Days On Well | 12 | Slide ROP(Usft/hr) | 44.66
Start Depth (Usft) | 105.00 | Slide % | 15.44
End Depth (Usft) | 15209.00
Total Drilled (Usft) | 15104.00
# BHA's | 5
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 22.00 / 0.00
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 01/16/2021 | 01/18/2021 | 03/12/2021 | 03/14/2021
End Date | 01/17/2021 | 01/21/2021 | 03/14/2021 | 03/17/2021
Total Days | 2.00 | 4.00 | 2.92 | 3.08
Start Depth (Usft) | 105.00 | 2916.00 | 10171.00 | 10920.00
End Depth (Usft) | 2916.00 | 10171.00 | 10920.00 | 15209.00
Total Drilled(Usft) | 2811.00 | 7255.00 | 749.00 | 4289.00
Drilling Hours | 4.88 | 34.35 | 11.87 | 47.07
Circulating Hours | 0.93 | 3.23 | 4.80 | 5.87
Total D&C Hours | 5.82 | 37.58 | 16.67 | 52.93
Avg ROP(Usft/hr) | 575.63 | 211.21 | 63.12 | 91.13
Rotary Drilled(Usft) | 2391.00 | 6638.00 | 233.00 | 3510.00
Rotary Hours | 2.33 | 22.47 | 1.82 | 19.33
Rotary ROP(Usft/hr) | 1024.71 | 295.46 | 128.26 | 181.55
Rotary % | 85.06 | 91.50 | 31.11 | 81.84
Slide Drilled(Usft) | 420.00 | 617.00 | 516.00 | 779.00
Slide Hours | 2.55 | 11.88 | 10.05 | 27.73
Slide ROP(Usft/hr) | 164.71 | 51.92 | 51.34 | 28.09
Slide % | 14.94 | 8.50 | 68.89 | 18.16
# BHA | 1 | 2 | 1 | 1
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 2.15 / 0.00 | 19.25 / 0.00 | 0.60 / 0.00
Total Phase Hrs | 6.87 | 60.37 | 14.50 | 55.25
Phase ROP (Usft/hr) | 409.37 | 120.18 | 51.66 | 77.63
Avg Motor Yield (°/100ft) | 6.77 | 13.06 | 10.97 | 19.39
Avg Rotary DLS (°/100ft) | 0.27 | 0.55 | 0.00 | 1.11
Avg Rotary TF | -136.63 | -146.08 | 0.00 | 96.56
Avg Slide Length (Usft) | 32.31 | 24.68 | 64.50 | 21.64
# Slides | 13 | 25 | 8 | 36
BHA Data
BHA# | 1 | 2 | 3 | 4 | 5
Description | BHA 1 | BHA 2 | BHA 3 | BHA 4 | BHA 5
Bit Size | 13.500 | 9.875 | 9.875 | 6.750 | 6.750
Bit Make/Model | Ulterra / U616S | Ulterra / SPL613 | Ulterra / SPL613 | Security / GTD64M | Security / GTD64M
Bit TFA | 1.178 | 1.491 | 1.491 | 1.491 | 1.491
Grade In | New | New | New | New | New
Grade Out
Motor SN | PPM800001 | PPM800012 | PPM800012 | PPM250004 | PPM250024
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.90 | 7/8 / 5.90 | 7/8 / 5.90 | 6/7 / 8.8 | 6/7 / 8.8
WOB (klbs) | 5.00 / 15.66 / 20.00 | 12.00 / 34.97 / 40.00 | 18.00 / 18.00 / 18.00 | 10.00 / 36.07 / 45.00 | 35.00 / 40.49 / 50.00
Diff P (psi) | 50.00 / 288.12 / 400.00 | 100.00 / 520.68 / 800.00 | 300.00 / 510.00 / 650.00 | 105.00 / 639.64 / 900.00 | 200.00 / 778.24 / 1050.00
Bend | 1.500 | 2.000 | 2.000 | 2.000 | 2.000
Date In | 01/16/2021 | 01/18/2021 | 01/20/2021 | 03/12/2021 | 03/14/2021
Date Out | 01/16/2021 | 01/20/2021 | 01/21/2021 | 03/14/2021 | 03/17/2021
Time In | 08:30 | 04:20 | 10:30 | 23:15 | 23:30
Time Out | 19:42 | 10:15 | 03:30 | 22:05 | 21:20
BRT Hrs | 11.20 | 53.92 | 17.00 | 46.83 | 69.83
Start Depth (Usft) | 105.00 | 2916.00 | 9904.00 | 10171.00 | 10920.00
End Depth (Usft) | 2916.00 | 9904.00 | 10171.00 | 10920.00 | 15209.00
Total Drilled(Usft) | 2811.00 | 6988.00 | 267.00 | 749.00 | 4289.00
Drilling Hours | 4.88 | 29.17 | 5.18 | 11.87 | 47.07
Circulating Hours | 0.93 | 2.00 | 1.23 | 4.80 | 5.87
Total D&C Hours | 5.82 | 31.17 | 6.42 | 16.67 | 52.93
Avg ROP(Usft/hr) | 575.63 | 239.59 | 51.51 | 63.12 | 91.13
Rotary Drilled(Usft) | 2391.00 | 6520.00 | 118.00 | 233.00 | 3510.00
Rotary Hours | 2.33 | 21.13 | 1.33 | 1.82 | 19.33
Rotary ROP(Usft/hr) | 1024.71 | 308.52 | 88.50 | 128.26 | 181.55
Rotary % | 85.06 | 93.30 | 44.19 | 31.11 | 81.84
Slide Drilled(Usft) | 420.00 | 468.00 | 149.00 | 516.00 | 779.00
Slide Hours | 2.55 | 8.03 | 3.85 | 10.05 | 27.73
Slide ROP(Usft/hr) | 164.71 | 58.26 | 38.70 | 51.34 | 28.09
Slide % | 14.94 | 6.70 | 55.81 | 68.89 | 18.16
Motor Failure | NO | NO | NO | NO | NO
MWD Failure | NO | NO | NO | NO | NO
Unplanned Trip | NO | YES | NO | YES | YES
LIH | NO | NO | NO | NO | NO
Avg Motor Yield (°/100ft) | 6.77 | 13.66 | 6.22 | 10.97 | 19.39
Avg Rotary DLS (°/100ft) | 0.27 | 0.55 | 0.00 | 0.00 | 1.11
Avg Rotary TF | -136.63 | -146.08 | 0.00 | 0.00 | 96.56
Avg Slide Length (Usft) | 32.31 | 20.35 | 74.50 | 64.50 | 21.64
# Slides | 13 | 23 | 2 | 8 | 36

## Personnel Report
|  | Job # | LTX1100921 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31146 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Sabine D 4H
|  | Date: | 03/17/2021 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Sabine D 4H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Billy McFarland | Night DD |  | 01/16/2021 - 00:00 | 01/21/2021 - 00:00 |  | 6.00 / 0.00
Chris Day | Night DD |  | 03/12/2021 - 00:00 | 03/15/2021 - 00:00 |  | 4.00 / 0.00
Chris Day Jesse Taylor | Night DD |  | 03/16/2021 - 00:00 | 03/16/2021 - 00:00 |  | 1.00 / 0.00
Jeff Campbell | Night MWD |  | 01/16/2021 - 00:00 | 01/21/2021 - 00:00 |  | 6.00 / 0.00
Jeff Campbell | Night MWD |  | 03/12/2021 - 00:00 | 03/16/2021 - 00:00 |  | 5.00 / 0.00
Jesse Taylor | Night DD |  | 03/17/2021 - 00:00 | 03/17/2021 - 00:00 |  | 1.00 / 0.00
NA | Rss Eng. 1 |  | 03/17/2021 - 00:00 | 03/17/2021 - 00:00 |  | 1.00 / 0.00
NA | Rss Eng. 2 |  | 03/17/2021 - 00:00 | 03/17/2021 - 00:00 |  | 1.00 / 0.00
NA | Third Man |  | 03/17/2021 - 00:00 | 03/17/2021 - 00:00 |  | 1.00 / 0.00
NA | Fourth Man |  | 03/17/2021 - 00:00 | 03/17/2021 - 00:00 |  | 1.00 / 0.00
Nathan Marks | Day DD |  | 01/16/2021 - 00:00 | 01/21/2021 - 00:00 |  | 6.00 / 0.00
Nathan Marks | Day DD |  | 03/12/2021 - 00:00 | 03/17/2021 - 00:00 |  | 6.00 / 0.00
Ramon Reis | Night MWD |  | 03/17/2021 - 00:00 | 03/17/2021 - 00:00 |  | 1.00 / 0.00
Russell Arnold | Day MWD |  | 01/16/2021 - 00:00 | 01/21/2021 - 00:00 |  | 6.00 / 0.00
Russell Arnold | Day MWD |  | 03/12/2021 - 00:00 | 03/17/2021 - 00:00 |  | 6.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1100921 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Sabine D 4H | [7 empty] | Day DD: |  |  |  |  | Nathan Marks | [5 empty] | API #: |  |  |  | 42-477-31146
|  |  |  | AFE #: |  |  | 20DD0331MG | [7 empty] | Night DD: |  |  |  |  | Jesse Taylor | [5 empty] | Company Man: |  |  |  | Jim
|  |  |  | PO #: | [10 empty] | Day MWD: |  |  |  |  | Russell Arnold | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Ramon Reis | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 01/16/2021 | 01/17/2021 | 01/18/2021 | 01/19/2021 | 01/20/2021 | 01/21/2021 | 01/22/2021 | 01/23/2021 | 01/24/2021 | 01/25/2021 | 01/26/2021 | 01/27/2021 | 01/28/2021 | 01/29/2021 | 01/30/2021 | 01/31/2021 | 02/01/2021 | 02/02/2021 | 02/03/2021 | 02/04/2021 | 02/05/2021 | 02/06/2021 | 02/07/2021 | 02/08/2021 | 02/09/2021 | 02/10/2021 | 02/11/2021 | 02/12/2021 | 02/13/2021 | 02/14/2021 | 02/15/2021 | 02/16/2021 | 02/17/2021 | 02/18/2021 | 02/19/2021 | 02/20/2021 | 02/21/2021 | 02/22/2021 | 02/23/2021 | 02/24/2021 | 02/25/2021 | 02/26/2021 | 02/27/2021 | 02/28/2021 | 03/01/2021 | 03/02/2021 | 03/03/2021 | 03/04/2021 | 03/05/2021 | 03/06/2021 | 03/07/2021 | 03/08/2021 | 03/09/2021 | 03/10/2021 | 03/11/2021 | 03/12/2021 | 03/13/2021 | 03/14/2021 | 03/15/2021 | 03/16/2021 | 03/17/2021 | 03/18/2021
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | GTD64M |  | Steel | 13446789 | 0 | 13 | [48 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13522000 | 3 | 7 | [54 empty] | O | X | X | X | O | O | O
Bit |  | 6.75 | GTD64M |  | Steel | 13401055 | 4 | 4 | [57 empty] | X | X | X | X
Hole Opener |  | 5.25 | Drill N Ream Reamer |  | Steel | 051916-02 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
Cross Over |  | 5.25 | XO- XT39Pin x DS42Box |  | Steel | SD119313 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Cross Over |  | 5.5 | XO- XT39Pin x DS42Box |  | Steel | 119312 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
MWD / LWD |  | 5.25 | UBHO |  | Steel | 500043 | 3 | 14 | [47 empty] | O | O | O | O | O | O | O | O | X | X | X | O | O | O
MWD / LWD |  | 5.25 | Pro UBHO |  | Steel | 500029 | 0 | 14 | [47 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O
MWD / LWD |  | 5.23 | UBHO |  | Steel | 500042 | 4 | 4 | [57 empty] | X | X | X | X
MWD / LWD |  | 5.2 | UBHO |  | Steel | 500033 | 0 | 4 | [57 empty] | O | O | O | O
Motor |  | 5.5 | 7/8, 3.8 2.5 Slick, HS88 -.001 |  | Steel | MTR475013 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 7/8 3.8 0 Slick. Fit. .004 |  | Steel | BPG2475-0004 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5 | 6/7 8.8 2.12 Slick HS88 .007 |  | Steel | PPM250016 | 0 | 14 | [47 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 8.8 2.00 Slick HS88 .017 |  | Steel | PPM250004 | 3 | 23 | [38 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | X | X | X | O | O | O
Motor |  | 5.5 | 6/7 8.8 2.00 Slick HS88 .006 |  | Steel | PPM250024 | 4 | 4 | [57 empty] | X | X | X | X
Collar |  | 4.75 | NM Drill Collar |  | Non-Mag | SD56630 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 4.75 | NM Drill Collar |  | Non-Mag | SD56699 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5.063 | NM Drill Collar |  | Non-Mag | SD55955 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD56785 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
Collar |  | 5 | NM Drill Collar |  | Non-Mag | SD56702 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
Collar |  | 5 | NM Pony Drill Collar |  | Non-Mag | SD56727 | 0 | 14 | [47 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Collar |  | 5 | NM Pony Drill Collar |  | Non-Mag | SD56870 | 0 | 7 | [54 empty] | O | O | O | O | O | O | O
Collar |  | 5 | NM Pony Drill Collar |  | Non-Mag | SD56841 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
Drill Pipe |  | 4.5 | 2 Stands of Drill Pipe |  | Steel | Rig-6 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 25 stands of Drill Pipe |  | Steel | Rig 1 | 0 | 13 | [48 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax Thruster |  | Steel | A52101 | 6 | 14 | [47 empty] | O | O | O | O | O | O | O | O | X | X | X | X | X | X
Accelerator |  | 5 | Cougar Thruster |  | Steel | DSMT3X500-025 | 0 | 13 | [48 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Accelerator |  | 5 | Tomax Thruster |  | Steel | A52101 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
Sub |  | 4.75 | Float Sub |  | Steel | SD118583 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.75 | Float Sub |  | Steel | SD45160 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 5.5 | Lift Sub |  | Steel | SD119466 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 5.5 | Lift Sub |  | Steel | SD119467 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.75 | Lift Cap |  | Steel | SDLC3361 | 0 | 32 | [29 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.875 | BTI Valve |  | Steel | 306844 | 0 | 13 | [48 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O
Sub |  | 4.938 | BTI Valve |  | Steel | Rig- 2 | 3 | 7 | [54 empty] | O | X | X | X | O | O | O
Sub |  | 4.86 | BTI Valve |  | Steel | RIG-3 | 4 | 4 | [57 empty] | X | X | X | X
Agitator |  | 5.25 | Agitator-Shock Sub-Safety Joint |  | Steel | AGOD525-0058 | 0 | 14 | [47 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Agitator |  | 5.375 | Agitator-Shock Sub-Safety Joint |  | Steel | AGOD525-OD006 | 6 | 7 | [54 empty] | O | X | X | X | X | X | X
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Nathan Marks |  |  |  | 12 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Billy McFarland |  |  |  | 6 |  | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Chris Day |  |  |  | 4 | [56 empty] | 1 | 1 | 1 | 1
Night DD |  |  | Chris Day Jesse Taylor |  |  |  | 1 | [60 empty] | 1
Night DD |  |  | Jesse Taylor |  |  |  | 1 | [61 empty] | 1
Day MWD |  |  | Russell Arnold |  |  |  | 12 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Jeff Campbell |  |  |  | 11 |  | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Ramon Reis |  |  |  | 1 | [61 empty] | 1
Third Man |  |  | NA |  |  |  | 1 | [61 empty] | 1
Fourth Man |  |  | NA |  |  |  | 1 | [61 empty] | 1

## Tool Inventory
|  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Sabine D 4H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0331MG |  |  | PO #:
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
MTR475013 | 7/8, 3.8 2.5 Slick, HS88 -.001 | 5.5 |  |  | XT39 / 3 1/2 Reg | Clean |  | 02/14/2021 |  | 03/18/2021
SD56630 | NM Drill Collar | 4.75 | 30.31 |  | XT39 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD56699 | NM Drill Collar | 4.75 | 30.71 |  | XT39 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD118583 | Float Sub | 4.75 |  |  | XT39 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD45160 | Float Sub | 4.75 |  |  | XT39 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD119313 | XO- XT39Pin x DS42Box | 5.25 | 3.59 |  | DS42 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD119466 | Lift Sub | 5.5 |  |  | XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD119467 | Lift Sub | 5.5 |  |  | XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SDLC3361 | Lift Cap | 4.75 |  |  | XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
BPG2475-0004 | 7/8 3.8 0 Slick. Fit. .004 | 5 |  |  | XT39 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
SD55955 | NM Drill Collar | 5.063 | 30.37 |  | XT39 / XT39 | Clean |  | 02/14/2021 |  | 03/18/2021
Rig-6 | 2 Stands of Drill Pipe | 4.5 | 190.36 |  | DS42 / DS42 | Dirty |  | 02/14/2021 |  | 03/18/2021
051916-02 | Drill N Ream Reamer | 5.25 | 7.93 |  | DS42 / DS42 | Dirty |  | 03/11/2021 |  | 03/18/2021
SD56785 | NM Drill Collar | 5 | 30.98 |  | XT39 / XT39 | Dirty |  | 03/11/2021 |  | 03/18/2021
SD56702 | NM Drill Collar | 5 | 30.38 |  | XT39 / XT39 | Dirty |  | 03/11/2021 |  | 03/18/2021
SD56727 | NM Pony Drill Collar | 5 | 11.77 |  | XT39 / XT39 | Clean |  | 03/04/2021 |  | 03/18/2021
SD56870 | NM Pony Drill Collar | 5 | 9.97 |  | XT39 / XT39 | Clean |  | 03/11/2021 |  | 03/18/2021
SD56841 | NM Pony Drill Collar | 5 |  |  | XT39 / XT39 | Dirty |  | 03/11/2021 |  | 03/18/2021
119312 | XO- XT39Pin x DS42Box | 5.5 | 3.24 |  | DS42 / XT39 | Dirty |  | 03/11/2021 |  | 03/18/2021
PPM250016 | 6/7 8.8 2.12 Slick HS88 .007 | 5 | 33.13 |  | XT39 / 3 1/2 Reg | Clean |  | 03/04/2021 |  | 03/18/2021
500043 | UBHO | 5.25 | 4 |  | XT39 / XT39 | Dirty |  | 03/04/2021 |  | 03/18/2021
500029 | Pro UBHO | 5.25 | 3.27 |  | XT39 / XT39 | Clean |  | 03/04/2021 |  | 03/18/2021
A52101 | Tomax Thruster | 5 | 17.93 |  | XT39 / XT39 | Dirty |  | 03/04/2021 |  | 03/18/2021
AGOD525-0058 | Agitator-Shock Sub-Safety Joint | 5.25 | 28.89 |  | DS42 / DS42 | Clean |  | 03/04/2021 |  | 03/18/2021
DSMT3X500-025 | Cougar Thruster | 5 | 23.88 |  | XT39 / XT39 | Clean |  | 03/05/2021 |  | 03/18/2021
306844 | BTI Valve | 4.875 | 2.33 |  | XT39 / XT39 | Clean |  | 03/05/2021 |  | 03/18/2021
13446789 | GTD64M | 6.75 | 0.72 |  | 3 1/2 Reg | Clean |  | 03/05/2021 |  | 03/18/2021
Rig 1 | 25 stands of Drill Pipe | 4.5 | 2378.29 |  | DS42 / DS42 | Dirty |  | 03/05/2021 |  | 03/18/2021
AGOD525-OD006 | Agitator-Shock Sub-Safety Joint | 5.375 | 29.12 |  | DS42 / DS42 | Dirty |  | 03/11/2021 |  | 03/18/2021
A52101 | Tomax Thruster | 5 | 17.95 |  | XT39 / XT39 | Dirty |  | 03/11/2021 |  | 03/18/2021
Rig- 2 | BTI Valve | 4.938 | 2.43 |  | XT39 / XT39 | Dirty |  | 03/11/2021 |  | 03/18/2021
13522000 | GTD64M | 6.75 | 0.72 |  | 3 1/2 Reg | Dirty |  | 03/11/2021 |  | 03/18/2021
PPM250004 | 6/7 8.8 2.00 Slick HS88 .017 | 5.5 | 33.04 |  | XT39 / 3 1/2 Reg | Dirty |  | 02/23/2021 |  | 03/18/2021
PPM250024 | 6/7 8.8 2.00 Slick HS88 .006 | 5.5 | 33.2 |  | XT39 / 3 1/2 Reg | Dirty |  | 03/14/2021 |  | 03/18/2021
500042 | UBHO | 5.23 | 3.97 |  | XT39 / XT39 | Dirty |  | 03/14/2021 |  | 03/18/2021
500033 | UBHO | 5.2 |  |  |  | Clean |  | 03/14/2021 |  | 03/18/2021
RIG-3 | BTI Valve | 4.86 | 2.36 |  | XT39 / XT39 | Dirty |  | 03/14/2021 |  | 03/18/2021
13401055 | GTD64M | 6.75 | 0.76 |  | XT39 / XT39 | Dirty |  | 03/14/2021 |  | 03/18/2021
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Sabine D 4H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
13 1/2" Ulterra- U616S- Jetted 6x16s | 37295 | 01/16/2021 | 03/17/2021 | 61 |  | 1 |  | 0.93 | 4.88 | 11.2
7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) | PPM800001 | 01/16/2021 | 03/17/2021 | 61 |  | 1 |  | 0.93 | 4.88 | 11.2
13" - 4 Blade Nortrak Stabilizer (BFF) | SD610467 | 01/16/2021 | 03/17/2021 | 61 |  | 1 |  | 0.93 | 4.88 | 11.2
8" - NMPDC | SD45067 | 01/16/2021 | 03/17/2021 | 61 | 3 | 1 ,2 ,3 |  | 4.17 | 39.23 | 82.12
7 3/4" UBHO | 775210 | 01/16/2021 | 03/17/2021 | 61 | 3 | 1 ,2 ,3 |  | 4.17 | 39.23 | 82.12
8" - NMDC | SD55685 | 01/16/2021 | 03/17/2021 | 61 | 3 | 1 ,2 ,3 |  | 4.17 | 39.23 | 82.12
8" - NMDC | SD55520 | 01/16/2021 | 03/17/2021 | 61 | 3 | 1 ,2 ,3 |  | 4.17 | 39.23 | 82.12
X/O- 4 1/2 IFB x 6 5/8 RegP | SD114192 | 01/16/2021 | 03/17/2021 | 61 |  | 1 |  | 0.93 | 4.88 | 11.2
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s | 54300 | 01/16/2021 | 03/17/2021 | 61 | 3 | 2 ,3 |  | 3.23 | 34.35 | 70.92
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 | PPM800012 | 01/16/2021 | 03/17/2021 | 61 | 3 | 2 ,3 |  | 3.23 | 34.35 | 70.92
X/O- 4 1/2 XHB x 6 5/8 RegP | SD107481 | 01/16/2021 | 03/17/2021 | 61 | 3 | 2 ,3 |  | 3.23 | 34.35 | 70.92
6 Joints of 6.5" Drill Collars | Rig 1 | 01/16/2021 | 03/17/2021 | 61 | 3 | 2 ,3 |  | 3.23 | 34.35 | 70.92
X/O- 4 1/2 IFB x 4 1/2 XHP | SD107702 | 01/16/2021 | 03/17/2021 | 61 | 3 | 2 ,3 |  | 3.23 | 34.35 | 70.92
NOV Agitator-Shock Sub- Safety Joint | AGHF-0675-0034 | 01/16/2021 | 03/17/2021 | 61 | 3 | 2 ,3 |  | 3.23 | 34.35 | 70.92
GTD64M | 13522000 | 03/11/2021 | 03/18/2021 | 8 | 2 | 4 |  | 4.8 | 11.87 | 46.83
6/7 8.8 2.00 Slick HS88 .017 | PPM250004 | 02/23/2021 | 03/18/2021 | 24 | 2 | 4 |  | 4.8 | 11.87 | 46.83
BTI Valve | Rig- 2 | 03/11/2021 | 03/18/2021 | 8 | 2 | 4 |  | 4.8 | 11.87 | 46.83
NM Pony Drill Collar | SD56841 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
UBHO | 500043 | 03/04/2021 | 03/18/2021 | 15 | 2 | 4 |  | 4.8 | 11.87 | 46.83
Helix | 424 | 03/04/2021 | 03/18/2021 | 14 | 2 | 4 |  | 4.8 | 11.87 | 46.83
Pulser | 6044 | 03/04/2021 | 03/18/2021 | 14 | 2 | 4 |  | 4.8 | 11.87 | 46.83
Battery - Plug In Hrs 0.00 | 1106 | 03/04/2021 | 03/18/2021 | 14 | 2 | 4 |  | 4.8 | 11.87 | 46.83
Battery - Plug In Hrs 0.00 | 1056 | 03/04/2021 | 03/18/2021 | 14 | 2 | 4 |  | 4.8 | 11.87 | 46.83
Gamma | 3006/4002 | 03/04/2021 | 03/18/2021 | 14 | 2 | 4 |  | 4.8 | 11.87 | 46.83
Directional Module | 9011 | 03/04/2021 | 03/18/2021 | 14 | 2 | 4 |  | 4.8 | 11.87 | 46.83
NM Drill Collar | SD56785 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
NM Drill Collar | SD56702 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
Tomax Thruster | A52101 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
XO- XT39Pin x DS42Box | 119312 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
Drill N Ream Reamer | 051916-02 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
Agitator-Shock Sub-Safety Joint | AGOD525-OD006 | 03/11/2021 | 03/18/2021 | 8 | 5 | 4 ,5 |  | 10.67 | 58.93 | 116.67
GTD64M | 13401055 | 03/14/2021 | 03/18/2021 | 5 | 3 | 5 |  | 5.87 | 47.07 | 69.83
6/7 8.8 2.00 Slick HS88 .006 | PPM250024 | 03/14/2021 | 03/18/2021 | 5 | 3 | 5 |  | 5.87 | 47.07 | 69.83
YES | RIG-3 | 03/14/2021 | 03/18/2021 | 5 | 3 | 5 |  | 5.87 | 47.07 | 69.83
UBHO | 500042 | 03/14/2021 | 03/18/2021 | 5 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Helix | 246 | 03/14/2021 | 03/18/2021 | 4 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Pulser | 6067 | 03/14/2021 | 03/18/2021 | 4 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Battery - Plug In Hrs 0.00 | 1111 | 03/14/2021 | 03/18/2021 | 4 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Battery - Plug In Hrs 0.00 | 1121 | 03/14/2021 | 03/18/2021 | 4 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Gamma | 3113/4001 | 03/14/2021 | 03/18/2021 | 4 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Directional Module | 9013 | 03/14/2021 | 03/18/2021 | 4 | 3 | 5 |  | 5.87 | 47.07 | 69.83
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well
Facility |  |  | Sabine - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Sabine D 4H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Sabine D 4H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 487.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Sabine - Washington County, TX
Map Northing |  |  | 191087.73 US survey foot |  |  | Map Easting |  |  | 3128495.27 US survey foot
Latitude |  |  | 30° 8' 32.18197" N |  |  | Longitude |  |  | 96° 45' 45.87603" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.839
Well: |  |  | Sabine D 4H
Local North |  |  | 44.80 Usft |  |  | Local East |  |  | 39.95 Usft
Map Northing |  |  | 191132.53 US survey foot |  |  | Map Easting |  |  | 3128535.22 US survey foot
Latitude |  |  | 30° 8' 32.612" N |  |  | Longitude |  |  | 96° 45' 45.405" W
Depth Datum |  |  | Well |  |  | Datum Elevation |  |  | 487.00 Usft
GL Elevation |  |  | 459.00 Usft
Grid Convergence |  |  | 1.839
Well bore: |  |  | Sabine D 4H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 31/01/2021
Total Field (nT) |  |  | 46586.8 |  |  | Dip Angle (°) |  |  | 58.783
Declination (°) |  |  | 2.9
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 136.56
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Sabine D 4H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 2840 |  |  | Sabine D 4H S1 |  |  | MWD+HDGM
2840 |  |  | 10100 |  |  | Sabine D 4H S2 |  |  | MWD+HDGM
10100 |  |  | 10758 |  |  | Sabine D 4H S3 |  |  | MWD+HDGM
10758 |  |  | 15136 |  |  | Sabine D 4H S4 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -487 | 191132.53 | 3128535.22 | 30.1424 | -96.7626 | 0
136 | 0.15 | 315.57 | 136 | 0.13 | -0.12 | -0.18 | 0.11 | 0.11 | 32.67 | 315.57 | 136 | -351 | 191132.66 | 3128535.1 | 30.1424 | -96.7626 | 315.57
228 | 0.16 | 66.18 | 228 | 0.27 | -0.09 | -0.26 | 0.28 | 0.01 | 120.23 | 144.03 | 92 | -259 | 191132.8 | 3128535.13 | 30.1424 | -96.7626 | 340.97
319 | 0.15 | 252.93 | 319 | 0.28 | -0.09 | -0.27 | 0.34 | -0.01 | 190.38 | -176.73 | 91 | -168 | 191132.81 | 3128535.13 | 30.1424 | -96.7626 | 342.44
413 | 0.36 | 228.59 | 413 | 0.05 | -0.43 | -0.33 | 0.25 | 0.22 | -25.89 | -39.81 | 94 | -74 | 191132.58 | 3128534.79 | 30.1424 | -96.7626 | 276.65
507 | 0.62 | 127.87 | 507 | -0.46 | -0.25 | 0.16 | 0.82 | 0.28 | -107.15 | -127.96 | 94 | 20 | 191132.07 | 3128534.97 | 30.1424 | -96.7626 | 208.47
600 | 1.87 | 94.05 | 599.97 | -0.87 | 1.66 | 1.78 | 1.5 | 1.34 | -36.37 | -48.1 | 93 | 112.97 | 191131.66 | 3128536.88 | 30.1424 | -96.7626 | 117.72
693 | 3.48 | 88.52 | 692.87 | -0.91 | 6 | 4.78 | 1.75 | 1.73 | -5.95 | -11.88 | 93 | 205.87 | 191131.62 | 3128541.22 | 30.1424 | -96.7626 | 98.61
786 | 4.43 | 85.9 | 785.65 | -0.58 | 12.4 | 8.95 | 1.04 | 1.02 | -2.82 | -12.08 | 93 | 298.65 | 191131.95 | 3128547.62 | 30.1424 | -96.7626 | 92.67
880 | 4.44 | 87.8 | 879.37 | -0.18 | 19.66 | 13.65 | 0.16 | 0.01 | 2.02 | 87.05 | 94 | 392.37 | 191132.35 | 3128554.88 | 30.1424 | -96.7626 | 90.52
974 | 4.93 | 81.11 | 973.05 | 0.58 | 27.29 | 18.34 | 0.78 | 0.52 | -7.12 | -51.48 | 94 | 486.05 | 191133.11 | 3128562.51 | 30.1424 | -96.7625 | 88.77
1068 | 5.92 | 74.28 | 1066.63 | 2.52 | 35.94 | 22.88 | 1.26 | 1.05 | -7.27 | -36.55 | 94 | 579.63 | 191135.05 | 3128571.16 | 30.1424 | -96.7625 | 85.99
1162 | 5.96 | 73.21 | 1160.13 | 5.25 | 45.28 | 27.33 | 0.13 | 0.04 | -1.14 | -70.67 | 94 | 673.13 | 191137.78 | 3128580.5 | 30.1424 | -96.7625 | 83.39
1257 | 5.6 | 72.7 | 1254.64 | 8.05 | 54.43 | 31.58 | 0.38 | -0.38 | -0.54 | -172.13 | 95 | 767.64 | 191140.58 | 3128589.65 | 30.1424 | -96.7624 | 81.59
1350 | 5.44 | 72.26 | 1347.21 | 10.74 | 62.96 | 35.49 | 0.18 | -0.17 | -0.47 | -165.4 | 93 | 860.21 | 191143.27 | 3128598.18 | 30.1424 | -96.7624 | 80.32
1444 | 5.34 | 71.41 | 1440.8 | 13.49 | 71.35 | 39.26 | 0.14 | -0.11 | -0.9 | -141.82 | 94 | 953.8 | 191146.02 | 3128606.57 | 30.1424 | -96.7624 | 79.29
1538 | 5.16 | 64.16 | 1534.4 | 16.73 | 79.3 | 42.38 | 0.73 | -0.19 | -7.71 | -108.77 | 94 | 1047.4 | 191149.26 | 3128614.52 | 30.1424 | -96.7624 | 78.09
1632 | 5.4 | 47.32 | 1628.01 | 21.57 | 86.36 | 43.72 | 1.66 | 0.26 | -17.91 | -89.64 | 94 | 1141.01 | 191154.1 | 3128621.58 | 30.1424 | -96.7623 | 75.97
1726 | 5.08 | 28.8 | 1721.62 | 28.22 | 91.61 | 42.5 | 1.82 | -0.34 | -19.7 | -109.84 | 94 | 1234.62 | 191160.75 | 3128626.83 | 30.1425 | -96.7623 | 72.88
1820 | 5.48 | 8.65 | 1815.23 | 36.3 | 94.29 | 38.48 | 2.01 | 0.43 | -21.44 | -87.98 | 94 | 1328.23 | 191168.83 | 3128629.51 | 30.1425 | -96.7623 | 68.94
1914 | 6.46 | 345.29 | 1908.73 | 45.86 | 93.63 | 31.08 | 2.76 | 1.04 | 24.85 | -79.93 | 94 | 1421.73 | 191178.39 | 3128628.85 | 30.1425 | -96.7623 | 63.91
2008 | 7.42 | 325.26 | 2002.06 | 55.96 | 88.82 | 20.44 | 2.75 | 1.02 | -21.31 | -78.51 | 94 | 1515.06 | 191188.49 | 3128624.04 | 30.1425 | -96.7623 | 57.79
2102 | 7.52 | 315.65 | 2095.26 | 65.35 | 81.06 | 8.29 | 1.33 | 0.11 | -10.22 | -90.2 | 94 | 1608.26 | 191197.88 | 3128616.28 | 30.1426 | -96.7623 | 51.13
2195 | 8.11 | 316.46 | 2187.4 | 74.45 | 72.29 | -4.35 | 0.65 | 0.63 | 0.87 | 10.98 | 93 | 1700.4 | 191206.98 | 3128607.51 | 30.1426 | -96.7624 | 44.16
2289 | 9.86 | 317.56 | 2280.24 | 85.2 | 62.29 | -19.03 | 1.87 | 1.86 | 1.17 | 6.15 | 94 | 1793.24 | 191217.73 | 3128597.51 | 30.1426 | -96.7624 | 36.17
2383 | 12.07 | 319.23 | 2372.52 | 98.58 | 50.44 | -36.9 | 2.37 | 2.35 | 1.78 | 9 | 94 | 1885.52 | 191231.11 | 3128585.66 | 30.1427 | -96.7624 | 27.1
2477 | 13.34 | 319.66 | 2464.22 | 114.29 | 37 | -57.55 | 1.35 | 1.35 | 0.46 | 4.47 | 94 | 1977.22 | 191246.82 | 3128572.22 | 30.1427 | -96.7625 | 17.94
2571 | 13.13 | 319.64 | 2555.72 | 130.7 | 23.07 | -79.03 | 0.22 | -0.22 | -0.02 | -178.76 | 94 | 2068.72 | 191263.23 | 3128558.29 | 30.1427 | -96.7625 | 10.01
2664 | 13.74 | 319.21 | 2646.18 | 147.11 | 9.01 | -100.62 | 0.66 | 0.66 | -0.46 | -9.51 | 93 | 2159.18 | 191279.64 | 3128544.23 | 30.1428 | -96.7626 | 3.51
2758 | 14.63 | 318.26 | 2737.31 | 164.42 | -6.18 | -123.63 | 0.98 | 0.95 | -1.01 | -15.12 | 94 | 2250.31 | 191296.95 | 3128529.04 | 30.1428 | -96.7626 | 357.85
2840 | 14.49 | 317.18 | 2816.68 | 179.67 | -20.05 | -144.24 | 0.37 | -0.17 | -1.32 | -117.8 | 82 | 2329.68 | 191312.2 | 3128515.17 | 30.1429 | -96.7627 | 353.63
2976 | 13.78 | 317.7 | 2948.56 | 204.13 | -42.52 | -177.45 | 0.53 | -0.52 | 0.38 | 170.11 | 136 | 2461.56 | 191336.66 | 3128492.7 | 30.143 | -96.7627 | 348.23
3069 | 13.33 | 316.32 | 3038.97 | 220.07 | -57.37 | -199.24 | 0.6 | -0.48 | -1.48 | -144.96 | 93 | 2551.97 | 191352.6 | 3128477.85 | 30.143 | -96.7628 | 345.39
3163 | 14.48 | 318.15 | 3130.21 | 236.67 | -72.7 | -221.83 | 1.31 | 1.22 | 1.95 | 21.82 | 94 | 2643.21 | 191369.2 | 3128462.52 | 30.143 | -96.7628 | 342.92
3257 | 15.1 | 317.76 | 3221.1 | 254.48 | -88.77 | -245.82 | 0.67 | 0.66 | -0.41 | -9.31 | 94 | 2734.1 | 191387.01 | 3128446.45 | 30.1431 | -96.7629 | 340.77
3351 | 15.47 | 316.7 | 3311.77 | 272.67 | -105.6 | -270.6 | 0.49 | 0.39 | -1.13 | -37.57 | 94 | 2824.77 | 191405.2 | 3128429.62 | 30.1432 | -96.7629 | 338.83
3444 | 15.68 | 315.63 | 3401.36 | 290.68 | -122.89 | -295.56 | 0.38 | 0.23 | -1.15 | -54.35 | 93 | 2914.36 | 191423.21 | 3128412.33 | 30.1432 | -96.763 | 337.08
3538 | 15.77 | 320.74 | 3491.84 | 309.65 | -139.86 | -321.01 | 1.48 | 0.1 | 5.44 | 88.74 | 94 | 3004.84 | 191442.18 | 3128395.36 | 30.1433 | -96.763 | 335.69
3632 | 15.99 | 322.2 | 3582.26 | 329.77 | -155.88 | -346.63 | 0.49 | 0.23 | 1.55 | 61.86 | 94 | 3095.26 | 191462.3 | 3128379.34 | 30.1433 | -96.7631 | 334.7
3726 | 16.09 | 321.49 | 3672.6 | 350.2 | -171.93 | -372.49 | 0.23 | 0.11 | -0.76 | -63.33 | 94 | 3185.6 | 191482.73 | 3128363.29 | 30.1434 | -96.7631 | 333.85
3820 | 14.58 | 319.19 | 3763.25 | 369.35 | -187.77 | -397.29 | 1.73 | -1.61 | -2.45 | -159.17 | 94 | 3276.25 | 191501.88 | 3128347.45 | 30.1434 | -96.7632 | 333.05
3914 | 14.49 | 318.71 | 3854.24 | 387.14 | -203.26 | -420.86 | 0.16 | -0.1 | -0.51 | -127 | 94 | 3367.24 | 191519.67 | 3128331.96 | 30.1435 | -96.7632 | 332.3
4009 | 14.79 | 318.9 | 3946.15 | 405.21 | -219.08 | -444.85 | 0.32 | 0.32 | 0.2 | 9.19 | 95 | 3459.15 | 191537.74 | 3128316.14 | 30.1435 | -96.7633 | 331.6
4103 | 14.11 | 322.63 | 4037.18 | 423.35 | -233.92 | -468.24 | 1.23 | -0.72 | 3.97 | 127.95 | 94 | 3550.18 | 191555.88 | 3128301.3 | 30.1436 | -96.7633 | 331.08
4197 | 13.32 | 323.39 | 4128.5 | 441.15 | -247.33 | -490.38 | 0.86 | -0.84 | 0.81 | 167.52 | 94 | 3641.5 | 191573.68 | 3128287.89 | 30.1436 | -96.7634 | 330.72
4291 | 13.05 | 322.46 | 4220.02 | 458.26 | -260.25 | -511.69 | 0.37 | -0.29 | -0.99 | -142.3 | 94 | 3733.02 | 191590.79 | 3128274.97 | 30.1437 | -96.7634 | 330.41
4385 | 12.97 | 322.74 | 4311.61 | 475.07 | -273.11 | -532.73 | 0.11 | -0.09 | 0.3 | 141.9 | 94 | 3824.61 | 191607.6 | 3128262.11 | 30.1437 | -96.7634 | 330.11
4479 | 13.02 | 323.26 | 4403.2 | 491.95 | -285.83 | -553.74 | 0.14 | 0.05 | 0.55 | 67.1 | 94 | 3916.2 | 191624.48 | 3128249.39 | 30.1438 | -96.7635 | 329.84
4572 | 12.83 | 323.85 | 4493.85 | 508.68 | -298.19 | -574.38 | 0.25 | -0.2 | 0.63 | 145.5 | 93 | 4006.85 | 191641.21 | 3128237.03 | 30.1438 | -96.7635 | 329.62
4667 | 12.58 | 324.01 | 4586.52 | 525.57 | -310.49 | -595.1 | 0.27 | -0.26 | 0.17 | 172.07 | 95 | 4099.52 | 191658.1 | 3128224.73 | 30.1439 | -96.7635 | 329.43
4760 | 12.42 | 323.95 | 4677.32 | 541.85 | -322.33 | -615.06 | 0.17 | -0.17 | -0.06 | -175.39 | 93 | 4190.32 | 191674.38 | 3128212.89 | 30.1439 | -96.7636 | 329.25
4854 | 13.85 | 321.45 | 4768.86 | 558.82 | -335.29 | -636.3 | 1.64 | 1.52 | -2.66 | -22.89 | 94 | 4281.86 | 191691.35 | 3128199.93 | 30.144 | -96.7636 | 329.04
4948 | 15.09 | 320.65 | 4859.87 | 577.09 | -350.06 | -659.72 | 1.34 | 1.32 | -0.85 | -9.55 | 94 | 4372.87 | 191709.62 | 3128185.16 | 30.144 | -96.7637 | 328.76
5042 | 14.95 | 320.38 | 4950.66 | 595.89 | -365.55 | -684.02 | 0.17 | -0.15 | -0.29 | -153.57 | 94 | 4463.66 | 191728.42 | 3128169.67 | 30.1441 | -96.7637 | 328.47
5136 | 14.6 | 319.1 | 5041.55 | 614.18 | -381.04 | -707.95 | 0.51 | -0.37 | -1.36 | -137.61 | 94 | 4554.55 | 191746.71 | 3128154.18 | 30.1441 | -96.7638 | 328.18
5230 | 14.6 | 317.44 | 5132.52 | 631.86 | -396.81 | -731.63 | 0.45 | 0 | -1.77 | -90.8 | 94 | 4645.52 | 191764.39 | 3128138.41 | 30.1442 | -96.7638 | 327.87
5325 | 14.85 | 315.46 | 5224.4 | 649.36 | -413.44 | -755.78 | 0.59 | 0.26 | -2.08 | -64.54 | 95 | 4737.4 | 191781.89 | 3128121.78 | 30.1442 | -96.7639 | 327.52
5419 | 15.22 | 314.35 | 5315.18 | 666.57 | -430.71 | -780.15 | 0.5 | 0.39 | -1.18 | -38.43 | 94 | 4828.18 | 191799.1 | 3128104.51 | 30.1443 | -96.7639 | 327.13
5512 | 15.48 | 312.47 | 5404.86 | 683.48 | -448.6 | -804.73 | 0.6 | 0.28 | -2.02 | -63.32 | 93 | 4917.86 | 191816.01 | 3128086.62 | 30.1443 | -96.764 | 326.72
5607 | 14.1 | 314.15 | 5496.71 | 700.11 | -466.25 | -828.94 | 1.52 | -1.45 | 1.77 | 163.55 | 95 | 5009.71 | 191832.64 | 3128068.97 | 30.1444 | -96.764 | 326.34
5701 | 13.68 | 314.96 | 5587.97 | 715.94 | -482.34 | -851.49 | 0.49 | -0.45 | 0.86 | 155.55 | 94 | 5100.97 | 191848.47 | 3128052.88 | 30.1444 | -96.7641 | 326.03
5795 | 12.73 | 319.47 | 5679.48 | 731.66 | -496.93 | -872.94 | 1.49 | -1.01 | 4.8 | 134.86 | 94 | 5192.48 | 191864.19 | 3128038.29 | 30.1444 | -96.7641 | 325.82
5888 | 12.95 | 319.5 | 5770.16 | 747.37 | -510.36 | -893.58 | 0.24 | 0.24 | 0.03 | 1.75 | 93 | 5283.16 | 191879.9 | 3128024.86 | 30.1445 | -96.7642 | 325.67
5982 | 12.14 | 318.99 | 5861.91 | 762.84 | -523.68 | -913.98 | 0.87 | -0.86 | -0.54 | -172.46 | 94 | 5374.91 | 191895.37 | 3128011.54 | 30.1445 | -96.7642 | 325.53
6077 | 14.09 | 319.94 | 5954.43 | 779.23 | -537.68 | -935.5 | 2.07 | 2.05 | 1 | 6.77 | 95 | 5467.43 | 191911.76 | 3127997.54 | 30.1446 | -96.7642 | 325.39
6171 | 13.62 | 319.07 | 6045.69 | 796.35 | -552.3 | -957.98 | 0.55 | -0.5 | -0.93 | -156.52 | 94 | 5558.69 | 191928.88 | 3127982.92 | 30.1446 | -96.7643 | 325.26
6265 | 12.61 | 318.85 | 6137.24 | 812.44 | -566.3 | -979.29 | 1.08 | -1.07 | -0.23 | -177.28 | 94 | 5650.24 | 191944.97 | 3127968.92 | 30.1447 | -96.7643 | 325.12
6360 | 12.47 | 317.02 | 6229.97 | 827.75 | -580.12 | -999.91 | 0.44 | -0.15 | -1.93 | -110.3 | 95 | 5742.97 | 191960.28 | 3127955.1 | 30.1447 | -96.7644 | 324.98
6454 | 13.6 | 321.68 | 6321.55 | 843.85 | -593.89 | -1021.07 | 1.64 | 1.2 | 4.96 | 45.21 | 94 | 5834.55 | 191976.38 | 3127941.33 | 30.1448 | -96.7644 | 324.86
6548 | 15.1 | 321.89 | 6412.62 | 862.15 | -608.3 | -1044.27 | 1.6 | 1.6 | 0.22 | 2.09 | 94 | 5925.62 | 191994.68 | 3127926.92 | 30.1448 | -96.7644 | 324.79
6642 | 15.07 | 321.3 | 6503.38 | 881.32 | -623.5 | -1068.64 | 0.17 | -0.03 | -0.63 | -101.34 | 94 | 6016.38 | 192013.85 | 3127911.72 | 30.1449 | -96.7645 | 324.72
6735 | 14.25 | 319.29 | 6593.35 | 899.44 | -638.52 | -1092.12 | 1.04 | -0.88 | -2.16 | -149.16 | 93 | 6106.35 | 192031.97 | 3127896.7 | 30.1449 | -96.7645 | 324.63
6829 | 13.39 | 318.36 | 6684.63 | 916.34 | -653.3 | -1114.56 | 0.94 | -0.91 | -0.99 | -165.97 | 94 | 6197.63 | 192048.87 | 3127881.92 | 30.145 | -96.7646 | 324.51
6923 | 14.16 | 319.81 | 6775.93 | 933.26 | -667.95 | -1136.91 | 0.9 | 0.82 | 1.54 | 24.86 | 94 | 6288.93 | 192065.79 | 3127867.27 | 30.145 | -96.7646 | 324.41
7016 | 13.95 | 321.21 | 6866.14 | 950.69 | -682.31 | -1159.44 | 0.43 | -0.23 | 1.51 | 122.38 | 93 | 6379.14 | 192083.22 | 3127852.91 | 30.1451 | -96.7647 | 324.33
7110 | 13.19 | 320.87 | 6957.52 | 967.84 | -696.18 | -1181.43 | 0.81 | -0.81 | -0.36 | -174.17 | 94 | 6470.52 | 192100.37 | 3127839.04 | 30.1451 | -96.7647 | 324.27
7204 | 14.43 | 320.64 | 7048.8 | 985.21 | -710.38 | -1203.81 | 1.32 | 1.32 | -0.24 | -2.65 | 94 | 6561.8 | 192117.74 | 3127824.84 | 30.1452 | -96.7648 | 324.21
7298 | 13.66 | 321.02 | 7139.99 | 1002.9 | -724.79 | -1226.56 | 0.82 | -0.82 | 0.4 | 173.35 | 94 | 6652.99 | 192135.43 | 3127810.43 | 30.1452 | -96.7648 | 324.14
7392 | 14.12 | 320.34 | 7231.24 | 1020.35 | -739.09 | -1249.06 | 0.52 | 0.49 | -0.72 | -19.87 | 94 | 6744.24 | 192152.88 | 3127796.13 | 30.1453 | -96.7648 | 324.08
7487 | 13.54 | 319.48 | 7323.48 | 1037.73 | -753.71 | -1271.73 | 0.65 | -0.61 | -0.91 | -160.9 | 95 | 6836.48 | 192170.26 | 3127781.51 | 30.1453 | -96.7649 | 324.01
7580 | 13.36 | 318.35 | 7413.93 | 1054.03 | -767.92 | -1293.35 | 0.34 | -0.19 | -1.22 | -124.95 | 93 | 6926.93 | 192186.56 | 3127767.3 | 30.1454 | -96.7649 | 323.92
7674 | 12.47 | 317.14 | 7505.55 | 1069.59 | -782.04 | -1314.35 | 0.99 | -0.95 | -1.29 | -163.69 | 94 | 7018.55 | 192202.12 | 3127753.18 | 30.1454 | -96.765 | 323.83
7768 | 12.32 | 311.61 | 7597.37 | 1083.68 | -796.45 | -1334.49 | 1.27 | -0.16 | -5.88 | -99.9 | 94 | 7110.37 | 192216.21 | 3127738.77 | 30.1454 | -96.765 | 323.69
7862 | 13.19 | 314.01 | 7689.05 | 1097.8 | -811.66 | -1355.2 | 1.08 | 0.93 | 2.55 | 32.52 | 94 | 7202.05 | 192230.33 | 3127723.56 | 30.1455 | -96.7651 | 323.52
7956 | 12.13 | 314.95 | 7780.76 | 1112.22 | -826.36 | -1375.78 | 1.15 | -1.13 | 1 | 169.46 | 94 | 7293.76 | 192244.75 | 3127708.86 | 30.1455 | -96.7651 | 323.39
8050 | 12.6 | 316.22 | 7872.58 | 1126.6 | -840.44 | -1395.91 | 0.58 | 0.5 | 1.35 | 30.68 | 94 | 7385.58 | 192259.13 | 3127694.78 | 30.1456 | -96.7652 | 323.28
8144 | 12.84 | 318.82 | 7964.27 | 1141.87 | -854.42 | -1416.6 | 0.66 | 0.26 | 2.77 | 68.53 | 94 | 7477.27 | 192274.4 | 3127680.8 | 30.1456 | -96.7652 | 323.19
8238 | 11.84 | 319.05 | 8056.1 | 1157.01 | -867.61 | -1436.67 | 1.07 | -1.06 | 0.24 | 177.3 | 94 | 7569.1 | 192289.54 | 3127667.61 | 30.1456 | -96.7652 | 323.13
8331 | 10.25 | 317.74 | 8147.37 | 1170.34 | -879.43 | -1454.47 | 1.73 | -1.71 | -1.41 | -171.67 | 93 | 7660.37 | 192302.87 | 3127655.79 | 30.1457 | -96.7653 | 323.08
8424 | 9.33 | 317.37 | 8239.02 | 1182.01 | -890.1 | -1470.28 | 0.99 | -0.99 | -0.4 | -176.27 | 93 | 7752.02 | 192314.54 | 3127645.12 | 30.1457 | -96.7653 | 323.02
8518 | 8.35 | 315.9 | 8331.9 | 1192.52 | -900.01 | -1484.73 | 1.07 | -1.04 | -1.56 | -167.74 | 94 | 7844.9 | 192325.05 | 3127635.21 | 30.1457 | -96.7653 | 322.96
8612 | 7.69 | 320.17 | 8424.98 | 1202.25 | -908.79 | -1497.83 | 0.95 | -0.7 | 4.54 | 140.03 | 94 | 7937.98 | 192334.78 | 3127626.43 | 30.1458 | -96.7654 | 322.91
8705 | 7.86 | 323.81 | 8517.13 | 1212.16 | -916.53 | -1510.35 | 0.56 | 0.18 | 3.91 | 72.76 | 93 | 8030.13 | 192344.69 | 3127618.69 | 30.1458 | -96.7654 | 322.91
8799 | 7.93 | 317.42 | 8610.24 | 1222.13 | -924.71 | -1523.21 | 0.94 | 0.07 | -6.8 | -88.61 | 94 | 8123.24 | 192354.66 | 3127610.51 | 30.1458 | -96.7654 | 322.89
8893 | 5.73 | 317.49 | 8703.57 | 1230.36 | -932.27 | -1534.38 | 2.34 | -2.34 | 0.07 | 179.82 | 94 | 8216.57 | 192362.89 | 3127602.95 | 30.1459 | -96.7654 | 322.85
8987 | 2.69 | 321.03 | 8797.3 | 1235.54 | -936.83 | -1541.28 | 3.24 | -3.23 | 3.77 | 176.88 | 94 | 8310.3 | 192368.07 | 3127598.39 | 30.1459 | -96.7654 | 322.83
9081 | 2.63 | 304.3 | 8891.2 | 1238.47 | -940 | -1545.58 | 0.83 | -0.06 | -17.8 | -102.74 | 94 | 8404.2 | 192371 | 3127595.22 | 30.1459 | -96.7655 | 322.8
9174 | 2.49 | 298.62 | 8984.11 | 1240.64 | -943.54 | -1549.59 | 0.31 | -0.15 | -6.11 | -121.71 | 93 | 8497.11 | 192373.17 | 3127591.68 | 30.1459 | -96.7655 | 322.75
9268 | 2.41 | 299.98 | 9078.02 | 1242.6 | -947.04 | -1553.43 | 0.11 | -0.09 | 1.45 | 144.67 | 94 | 8591.02 | 192375.13 | 3127588.18 | 30.1459 | -96.7655 | 322.69
9362 | 0.91 | 319.62 | 9171.98 | 1244.16 | -949.24 | -1556.07 | 1.68 | -1.6 | 20.89 | 168.86 | 94 | 8684.98 | 192376.69 | 3127585.98 | 30.1459 | -96.7655 | 322.66
9457 | 0.4 | 302.98 | 9266.98 | 1244.91 | -950 | -1557.14 | 0.57 | -0.54 | -17.52 | -167.73 | 95 | 8779.98 | 192377.44 | 3127585.22 | 30.1459 | -96.7655 | 322.65
9551 | 0.72 | 257.8 | 9360.97 | 1244.97 | -950.86 | -1557.77 | 0.56 | 0.34 | -48.06 | -78.11 | 94 | 8873.97 | 192377.5 | 3127584.36 | 30.1459 | -96.7655 | 322.63
9645 | 0.02 | 262.97 | 9454.97 | 1244.84 | -951.45 | -1558.08 | 0.74 | -0.74 | 5.5 | 179.85 | 94 | 8967.97 | 192377.37 | 3127583.77 | 30.1459 | -96.7655 | 322.61
9739 | 0.06 | 222.7 | 9548.97 | 1244.8 | -951.5 | -1558.09 | 0.05 | 0.04 | -42.84 | -56.39 | 94 | 9061.97 | 192377.33 | 3127583.72 | 30.1459 | -96.7655 | 322.61
9833 | 0.34 | 254.27 | 9642.97 | 1244.69 | -951.8 | -1558.22 | 0.31 | 0.3 | 33.59 | 37.78 | 94 | 9155.97 | 192377.22 | 3127583.42 | 30.1459 | -96.7655 | 322.6
9927 | 0.7 | 162.6 | 9736.97 | 1244.07 | -951.9 | -1557.83 | 0.84 | 0.38 | -97.52 | -117.25 | 94 | 9249.97 | 192376.6 | 3127583.32 | 30.1459 | -96.7655 | 322.58
10022 | 8.2 | 145.7 | 9831.61 | 1237.91 | -947.9 | -1550.61 | 7.93 | 7.89 | -17.79 | -18.44 | 95 | 9344.61 | 192370.44 | 3127587.32 | 30.1459 | -96.7655 | 322.56
10100 | 10.8 | 147.2 | 9908.54 | 1227.17 | -940.81 | -1537.93 | 3.35 | 3.33 | 1.92 | 6.18 | 78 | 9421.54 | 192359.7 | 3127594.41 | 30.1458 | -96.7655 | 322.52
10190 | 10.23 | 148.13 | 9997.02 | 1213.29 | -932.02 | -1521.82 | 0.66 | -0.63 | 1.03 | 163.88 | 90 | 9510.02 | 192345.82 | 3127603.2 | 30.1458 | -96.7654 | 322.47
10285 | 21.74 | 141.6 | 10088.2 | 1192.27 | -916.58 | -1495.94 | 12.24 | 12.12 | -6.87 | -12.06 | 95 | 9601.2 | 192324.8 | 3127618.64 | 30.1457 | -96.7654 | 322.45
10380 | 30.83 | 135.54 | 10173.31 | 1161.03 | -888.54 | -1453.98 | 9.97 | 9.57 | -6.38 | -19.2 | 95 | 9686.31 | 192293.56 | 3127646.68 | 30.1457 | -96.7653 | 322.57
10474 | 36.71 | 135.57 | 10251.41 | 1123.75 | -851.97 | -1401.76 | 6.26 | 6.26 | 0.03 | 0.18 | 94 | 9764.41 | 192256.28 | 3127683.25 | 30.1456 | -96.7652 | 322.83
10569 | 42.31 | 133.84 | 10324.68 | 1081.29 | -809 | -1341.38 | 6.01 | 5.89 | -1.82 | -11.79 | 95 | 9837.68 | 192213.82 | 3127726.22 | 30.1454 | -96.7651 | 323.2
10663 | 53.34 | 133.63 | 10387.69 | 1033.21 | -758.73 | -1271.91 | 11.74 | 11.73 | -0.22 | -0.88 | 94 | 9900.69 | 192165.74 | 3127776.49 | 30.1453 | -96.7649 | 323.71
10758 | 61.23 | 135.83 | 10439 | 976.96 | -702.04 | -1192.09 | 8.53 | 8.31 | 2.32 | 13.81 | 95 | 9952 | 192109.49 | 3127833.18 | 30.1451 | -96.7647 | 324.3
10853 | 61.59 | 135.73 | 10484.46 | 917.18 | -643.87 | -1108.68 | 0.39 | 0.38 | -0.11 | -13.73 | 95 | 9997.46 | 192049.71 | 3127891.35 | 30.145 | -96.7646 | 324.93
10948 | 66.06 | 130.01 | 10526.39 | 859.28 | -581.38 | -1023.67 | 7.16 | 4.71 | -6.02 | -50.25 | 95 | 10039.39 | 191991.81 | 3127953.84 | 30.1448 | -96.7644 | 325.92
11042 | 74.19 | 135.3 | 10558.34 | 799.38 | -516.52 | -935.58 | 10.14 | 8.65 | 5.63 | 32.4 | 94 | 10071.34 | 191931.91 | 3128018.7 | 30.1446 | -96.7642 | 327.13
11136 | 83.67 | 140.77 | 10576.38 | 730.85 | -454.98 | -843.51 | 11.59 | 10.09 | 5.82 | 30.1 | 94 | 10089.38 | 191863.38 | 3128080.24 | 30.1444 | -96.764 | 328.1
11230 | 86.14 | 137.11 | 10584.73 | 660.27 | -393.49 | -749.98 | 4.68 | 2.63 | -3.89 | -56.05 | 94 | 10097.73 | 191792.8 | 3128141.73 | 30.1442 | -96.7638 | 329.21
11324 | 86.22 | 135.17 | 10590.99 | 592.65 | -328.51 | -656.2 | 2.06 | 0.09 | -2.06 | -87.7 | 94 | 10103.99 | 191725.18 | 3128206.71 | 30.1441 | -96.7636 | 331
11419 | 85.59 | 135.57 | 10597.77 | 525.21 | -261.94 | -561.46 | 0.78 | -0.66 | 0.42 | 147.67 | 95 | 10110.77 | 191657.74 | 3128273.28 | 30.1439 | -96.7634 | 333.49
11514 | 87.86 | 135.1 | 10603.2 | 457.76 | -195.27 | -466.65 | 2.44 | 2.39 | -0.49 | -11.69 | 95 | 10116.2 | 191590.29 | 3128339.95 | 30.1437 | -96.7632 | 336.9
11609 | 88.95 | 135.23 | 10605.85 | 390.42 | -128.32 | -371.71 | 1.16 | 1.15 | 0.14 | 6.8 | 95 | 10118.85 | 191522.95 | 3128406.9 | 30.1435 | -96.763 | 341.81
11704 | 87.62 | 136.42 | 10608.69 | 322.32 | -62.15 | -276.77 | 1.88 | -1.4 | 1.25 | 138.21 | 95 | 10121.69 | 191454.85 | 3128473.07 | 30.1433 | -96.7628 | 349.09
11798 | 87.08 | 136.55 | 10613.04 | 254.22 | 2.51 | -182.87 | 0.59 | -0.57 | 0.14 | 166.48 | 94 | 10126.04 | 191386.75 | 3128537.73 | 30.1431 | -96.7626 | 0.56
11893 | 87.17 | 137.21 | 10617.8 | 184.97 | 67.36 | -87.99 | 0.7 | 0.09 | 0.69 | 82.24 | 95 | 10130.8 | 191317.5 | 3128602.58 | 30.1429 | -96.7624 | 20.01
11987 | 86.84 | 137.31 | 10622.71 | 116.03 | 131.07 | 5.87 | 0.37 | -0.35 | 0.11 | 163.17 | 94 | 10135.71 | 191248.56 | 3128666.29 | 30.1427 | -96.7622 | 48.48
12083 | 89.03 | 136.92 | 10626.17 | 45.74 | 196.35 | 101.8 | 2.32 | 2.28 | -0.41 | -10.1 | 96 | 10139.17 | 191178.27 | 3128731.57 | 30.1425 | -96.762 | 76.89
12180 | 90.24 | 136.82 | 10626.79 | -25.05 | 262.66 | 198.8 | 1.25 | 1.25 | -0.1 | -4.72 | 97 | 10139.79 | 191107.48 | 3128797.88 | 30.1423 | -96.7618 | 95.45
12276 | 89.06 | 136.93 | 10627.37 | -95.12 | 328.29 | 294.79 | 1.23 | -1.23 | 0.11 | 174.67 | 96 | 10140.37 | 191037.41 | 3128863.51 | 30.1421 | -96.7616 | 106.16
12373 | 87.83 | 136.06 | 10630.01 | -165.44 | 395.04 | 391.75 | 1.55 | -1.27 | -0.9 | -144.75 | 97 | 10143.01 | 190967.09 | 3128930.26 | 30.1419 | -96.7614 | 112.72
12470 | 89.04 | 136.42 | 10632.66 | -235.47 | 462.1 | 488.71 | 1.3 | 1.25 | 0.37 | 16.57 | 97 | 10145.66 | 190897.06 | 3128997.32 | 30.1417 | -96.7612 | 117
12565 | 87.19 | 137.23 | 10635.78 | -304.71 | 527.06 | 583.66 | 2.13 | -1.95 | 0.85 | 156.38 | 95 | 10148.78 | 190827.82 | 3129062.28 | 30.1415 | -96.761 | 120.03
12662 | 86.03 | 136.96 | 10641.52 | -375.64 | 592.98 | 680.48 | 1.23 | -1.2 | -0.28 | -166.93 | 97 | 10154.52 | 190756.89 | 3129128.2 | 30.1413 | -96.7608 | 122.35
12757 | 84.32 | 136.79 | 10649.51 | -444.73 | 657.69 | 775.14 | 1.81 | -1.8 | -0.18 | -174.35 | 95 | 10162.51 | 190687.8 | 3129192.91 | 30.1411 | -96.7606 | 124.07
12852 | 81.93 | 136.45 | 10660.88 | -513.27 | 722.46 | 869.45 | 2.54 | -2.52 | -0.36 | -171.98 | 95 | 10173.88 | 190619.26 | 3129257.68 | 30.1409 | -96.7604 | 125.39
12946 | 81.8 | 136.52 | 10674.18 | -580.76 | 786.54 | 962.5 | 0.16 | -0.14 | 0.07 | 151.95 | 94 | 10187.18 | 190551.77 | 3129321.76 | 30.1407 | -96.7602 | 126.44
13041 | 82.89 | 136.77 | 10686.83 | -649.22 | 851.17 | 1056.65 | 1.18 | 1.15 | 0.26 | 12.82 | 95 | 10199.83 | 190483.31 | 3129386.39 | 30.1405 | -96.76 | 127.33
13136 | 87.9 | 137.29 | 10694.46 | -718.48 | 915.7 | 1151.31 | 5.3 | 5.27 | 0.55 | 5.93 | 95 | 10207.46 | 190414.05 | 3129450.92 | 30.1403 | -96.7598 | 128.12
13232 | 92.34 | 135.99 | 10694.26 | -788.26 | 981.59 | 1247.29 | 4.82 | 4.62 | -1.35 | -16.32 | 96 | 10207.26 | 190344.27 | 3129516.81 | 30.1401 | -96.7596 | 128.77
13327 | 96.11 | 135.46 | 10687.26 | -856.08 | 1047.72 | 1342 | 4.01 | 3.97 | -0.56 | -7.96 | 95 | 10200.26 | 190276.45 | 3129582.94 | 30.1399 | -96.7594 | 129.25
13423 | 92.78 | 135.17 | 10679.82 | -924.12 | 1115.01 | 1437.68 | 3.48 | -3.47 | -0.3 | -175.03 | 96 | 10192.82 | 190208.41 | 3129650.23 | 30.1398 | -96.7592 | 129.65
13517 | 88.19 | 136.38 | 10679.03 | -991.46 | 1180.55 | 1531.64 | 5.05 | -4.88 | 1.29 | 165.22 | 94 | 10192.03 | 190141.07 | 3129715.77 | 30.1396 | -96.759 | 130.02
13611 | 89.77 | 136.17 | 10680.7 | -1059.38 | 1245.51 | 1625.62 | 1.7 | 1.68 | -0.22 | -7.57 | 94 | 10193.7 | 190073.15 | 3129780.73 | 30.1394 | -96.7588 | 130.38
13706 | 88.05 | 135.52 | 10682.51 | -1127.52 | 1311.68 | 1720.59 | 1.94 | -1.81 | -0.68 | -159.31 | 95 | 10195.51 | 190005.01 | 3129846.9 | 30.1392 | -96.7586 | 130.68
13802 | 88.63 | 136.66 | 10685.29 | -1196.65 | 1378.22 | 1816.54 | 1.33 | 0.6 | 1.19 | 63.04 | 96 | 10198.29 | 189935.88 | 3129913.44 | 30.139 | -96.7584 | 130.97
13900 | 86.84 | 137.31 | 10689.16 | -1268.25 | 1445.02 | 1914.46 | 1.94 | -1.83 | 0.66 | 160.07 | 98 | 10202.16 | 189864.28 | 3129980.24 | 30.1388 | -96.7582 | 131.27
13996 | 87.06 | 137.26 | 10694.27 | -1338.69 | 1510.05 | 2010.32 | 0.23 | 0.23 | -0.05 | -12.79 | 96 | 10207.27 | 189793.84 | 3130045.27 | 30.1386 | -96.758 | 131.56
14092 | 83.77 | 136.79 | 10701.94 | -1408.69 | 1575.28 | 2105.99 | 3.46 | -3.43 | -0.49 | -171.91 | 96 | 10214.94 | 189723.84 | 3130110.5 | 30.1384 | -96.7578 | 131.8
14187 | 83.16 | 136.38 | 10712.75 | -1477.25 | 1640.14 | 2200.38 | 0.77 | -0.64 | -0.43 | -146.29 | 95 | 10225.75 | 189655.28 | 3130175.36 | 30.1382 | -96.7576 | 132.01
14282 | 83.78 | 136.06 | 10723.56 | -1545.39 | 1705.45 | 2294.76 | 0.73 | 0.65 | -0.34 | -27.17 | 95 | 10236.56 | 189587.14 | 3130240.67 | 30.138 | -96.7574 | 132.18
14379 | 83.56 | 136.09 | 10734.25 | -1614.83 | 1772.33 | 2391.16 | 0.23 | -0.23 | 0.03 | 172.28 | 97 | 10247.25 | 189517.7 | 3130307.55 | 30.1378 | -96.7572 | 132.34
14474 | 83.08 | 136.58 | 10745.3 | -1683.09 | 1837.47 | 2485.52 | 0.72 | -0.51 | 0.52 | 134.63 | 95 | 10258.3 | 189449.44 | 3130372.69 | 30.1376 | -96.757 | 132.49
14568 | 88.69 | 135.85 | 10752.04 | -1750.74 | 1902.32 | 2579.23 | 6.02 | 5.97 | -0.78 | -7.42 | 94 | 10265.04 | 189381.79 | 3130437.54 | 30.1374 | -96.7568 | 132.62
14663 | 92.92 | 135.92 | 10750.71 | -1818.93 | 1968.43 | 2674.2 | 4.45 | 4.45 | 0.07 | 0.95 | 95 | 10263.71 | 189313.6 | 3130503.65 | 30.1372 | -96.7566 | 132.74
14758 | 92.44 | 135.66 | 10746.27 | -1886.95 | 2034.6 | 2769.08 | 0.57 | -0.51 | -0.27 | -151.58 | 95 | 10259.27 | 189245.58 | 3130569.82 | 30.137 | -96.7564 | 132.84
14852 | 91.43 | 134.3 | 10743.09 | -1953.35 | 2101.05 | 2862.99 | 1.8 | -1.07 | -1.45 | -126.59 | 94 | 10256.09 | 189179.18 | 3130636.27 | 30.1368 | -96.7562 | 132.91
14947 | 88.87 | 133.89 | 10742.85 | -2019.45 | 2169.27 | 2957.89 | 2.73 | -2.69 | -0.43 | -170.9 | 95 | 10255.85 | 189113.08 | 3130704.49 | 30.1367 | -96.756 | 132.95
15041 | 87.08 | 136.54 | 10746.17 | -2086.12 | 2235.44 | 3051.8 | 3.4 | -1.9 | 2.82 | 124.1 | 94 | 10259.17 | 189046.41 | 3130770.66 | 30.1365 | -96.7558 | 133.02
15136 | 86.26 | 136.43 | 10751.69 | -2154.89 | 2300.74 | 3146.64 | 0.87 | -0.86 | -0.12 | -172.38 | 95 | 10264.69 | 188977.64 | 3130835.96 | 30.1363 | -96.7556 | 133.13

## 1_16_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 01/16/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 13030 |  |  | Well Cost($): |  | 13030
|  |  |  | 24hr Summary: |  | Standby; P/U BHA; Drill Surface Section; TOH; L/D BHA; Standby
|  |  |  | 24hr Lookahead: |  | Standby
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 2916 |  | 2916 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): |  | 2811 |  | 2811 |  | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): |  | 420 |  | 420 | [5 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): |  | 2391 |  | 2391 | [5 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.88 / 0.93 |  | 4.88 / 0.93 |  | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 2.55 |  | 2.55 |  | SN: |  | 37295 |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: |  | 2.33 |  | 2.33 |  | Bit # |  | 1 |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): |  | 1024.71 / 164.71 |  | 1024.71 / 164.71 |  | OD (in) / TFA: |  | 13.500 / 1.178
BRT Hrs: |  | 11.2 |  | 11.2 |  | Grade In: |  | New
% Slide: |  | 14.94 |  | 14.94 |  | Grade Out:
% Rotary: |  | 85.06 |  | 85.06 |  | Make / Model: |  | Ulterra / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2" Ulterra- U616S- Jetted 6x16s - TFA 1.18 |  |  |  | 13.5 | 2 |  |  |  |  | 1.5 |  | 1.5
7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) |  |  |  | 8 | 2 |  |  |  |  | 37.68 |  | 39.18
13" - 4 Blade Nortrak Stabilizer (BFF) |  |  |  | 8 | 2.813 |  |  |  |  | 7.23 |  | 46.41
8" - NMPDC |  |  |  | 7.938 | 3.188 |  |  |  |  | 10.67 |  | 57.08
7 3/4" UBHO |  |  |  | 7.75 | 2.75 |  |  |  |  | 3.84 |  | 60.92
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.58 |  | 89.5
8" - NMDC |  |  |  | 7.938 | 3.125 |  |  |  |  | 28.91 |  | 118.41
X/O- 4 1/2 IFB x 6 5/8 RegP |  |  |  | 8 | 3 |  |  |  |  | 3.12 |  | 121.53
9 joints of 5" HWDP |  |  |  | 5 | 3 |  |  |  |  | 273.99 |  | 395.52
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800001 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.01 |  | 1.5 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
136 | 0.15 | 315.57 | 136 | 0.13 | -0.12 | 0.11 |  | 315.57 | -0.18 | 0.11 |  | 0 | 136
228 | 0.16 | 66.18 | 228 | 0.27 | -0.09 | 0.28 |  | 144.03 | -0.26 | 0.01 |  | 0 | 92
319 | 0.15 | 252.93 | 319 | 0.28 | -0.09 | 0.34 |  | -176.73 | -0.27 | -0.01 |  | 0 | 91
413 | 0.36 | 228.59 | 413 | 0.05 | -0.43 | 0.25 |  | -39.81 | -0.33 | 0.22 |  | 0 | 94
507 | 0.62 | 127.87 | 507 | -0.46 | -0.25 | 0.82 |  | -127.96 | 0.16 | 0.28 |  | 0 | 94
600 | 1.87 | 94.05 | 599.97 | -0.87 | 1.66 | 1.5 |  | -48.1 | 1.78 | 1.34 |  | 0 | 93
693 | 3.48 | 88.52 | 692.87 | -0.91 | 6 | 1.75 |  | -11.88 | 4.78 | 1.73 |  | -5.95 | 93
786 | 4.43 | 85.9 | 785.65 | -0.58 | 12.4 | 1.04 |  | -12.08 | 8.95 | 1.02 |  | -2.82 | 93
880 | 4.44 | 87.8 | 879.37 | -0.18 | 19.66 | 0.16 |  | 87.05 | 13.65 | 0.01 |  | 2.02 | 94
974 | 4.93 | 81.11 | 973.05 | 0.58 | 27.29 | 0.78 |  | -51.48 | 18.34 | 0.52 |  | -7.12 | 94
1068 | 5.92 | 74.28 | 1066.63 | 2.52 | 35.94 | 1.26 |  | -36.55 | 22.88 | 1.05 |  | -7.27 | 94
1162 | 5.96 | 73.21 | 1160.13 | 5.25 | 45.28 | 0.13 |  | -70.67 | 27.33 | 0.04 |  | -1.14 | 94
1257 | 5.6 | 72.7 | 1254.64 | 8.05 | 54.43 | 0.38 |  | -172.13 | 31.58 | -0.38 |  | -0.54 | 95
1350 | 5.44 | 72.26 | 1347.21 | 10.74 | 62.96 | 0.18 |  | -165.4 | 35.49 | -0.17 |  | -0.47 | 93
1444 | 5.34 | 71.41 | 1440.8 | 13.49 | 71.35 | 0.14 |  | -141.82 | 39.26 | -0.11 |  | -0.9 | 94
1538 | 5.16 | 64.16 | 1534.4 | 16.73 | 79.3 | 0.73 |  | -108.77 | 42.38 | -0.19 |  | -7.71 | 94
1632 | 5.4 | 47.32 | 1628.01 | 21.57 | 86.36 | 1.66 |  | -89.64 | 43.72 | 0.26 |  | -17.91 | 94
1726 | 5.08 | 28.8 | 1721.62 | 28.22 | 91.61 | 1.82 |  | -109.84 | 42.5 | -0.34 |  | -19.7 | 94
1820 | 5.48 | 8.65 | 1815.23 | 36.3 | 94.29 | 2.01 |  | -87.98 | 38.48 | 0.43 |  | -21.44 | 94
1914 | 6.46 | 345.29 | 1908.73 | 45.86 | 93.63 | 2.76 |  | -79.93 | 31.08 | 1.04 |  | -24.85 | 94
2008 | 7.42 | 325.26 | 2002.06 | 55.96 | 88.82 | 2.75 |  | -78.51 | 20.44 | 1.02 |  | -21.31 | 94
2102 | 7.52 | 315.65 | 2095.26 | 65.35 | 81.06 | 1.33 |  | -90.2 | 8.29 | 0.11 |  | -10.22 | 94
2195 | 8.11 | 316.46 | 2187.4 | 74.45 | 72.29 | 0.65 |  | 10.98 | -4.35 | 0.63 |  | 0.87 | 93
2289 | 9.86 | 317.56 | 2280.24 | 85.2 | 62.29 | 1.87 |  | 6.15 | -19.03 | 1.86 |  | 1.17 | 94
2383 | 12.07 | 319.23 | 2372.52 | 98.58 | 50.44 | 2.37 |  | 9 | -36.9 | 2.35 |  | 1.78 | 94
2477 | 13.34 | 319.66 | 2464.22 | 114.29 | 37 | 1.35 |  | 4.47 | -57.55 | 1.35 |  | 0.46 | 94
2571 | 13.13 | 319.64 | 2555.72 | 130.7 | 23.07 | 0.22 |  | -178.76 | -79.03 | -0.22 |  | -0.02 | 94
2664 | 13.74 | 319.21 | 2646.18 | 147.11 | 9.01 | 0.66 |  | -9.51 | -100.62 | 0.66 |  | -0.46 | 93
2758 | 14.63 | 318.26 | 2737.31 | 164.42 | -6.18 | 0.98 |  | -15.12 | -123.63 | 0.95 |  | -1.01 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 575.63 | 15.66 | 97.21 | 244 | 882.86 | 2063.39 | 1775.27 | 0 | 90.36 | 85.36 | 80.36 | 4209.3 | 0
Run | 575.63 | 15.66 | 97.21 | 244 | 882.86 | 2063.39 | 1775.27 | 0 | 90.36 | 85.36 | 80.36 | 4209.3 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Mob/DeMob |  |  |  |  | 01/16/2021 |  | 1 |  | 6000 |  | 1 | 6000
Directional Services Men and Motors |  |  |  |  | 01/16/2021 |  | 3 |  | 5250 |  | 1 | 5250
Perdiem Per Hand |  |  |  |  | 01/16/2021 |  | 6 |  | 100 |  | 4 | 400
Stabilizer Rental 13 Not Used |  |  |  |  | 01/16/2021 |  | 17 |  | 230 |  | 1 | 230
Stabilizer Rental 13 Used |  |  |  |  | 01/16/2021 |  | 16 |  | 1150 |  | 1 | 1150
Total | [11 empty] | 13030
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/16/2021 | 00:00 | 08:00 | 8 | 105 | 105 | 0 | SUR |  | 24B | Standby for rig skid
01/16/2021 | 08:00 | 08:30 | 0.5 | 105 | 105 | 0 | SUR | 1: BHA 1 | 6O | Latch up BHA #1 out of derrick, set MWD tool
01/16/2021 | 08:30 | 08:32 | 0.03 | 105 | 212 | 107 | SUR | 1: BHA 1 | 2K | Rotary Drill f/105.00 t/212.00, w/WOB 5.00,Flow 450.00, RPM 40.00, Press 550.00, Tq 2500.00, ROP 3210.00
01/16/2021 | 08:32 | 08:36 | 0.07 | 212 | 212 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 08:36 | 08:38 | 0.03 | 212 | 304 | 92 | SUR | 1: BHA 1 | 2K | Rotary Drill f/212.00 t/304.00, w/WOB 5.00,Flow 570.00, RPM 60.00, Press 900.00, Tq 2500.00, ROP 2760.00
01/16/2021 | 08:38 | 08:43 | 0.08 | 304 | 304 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 08:43 | 08:46 | 0.05 | 304 | 395 | 91 | SUR | 1: BHA 1 | 2K | Rotary Drill f/304.00 t/395.00, w/WOB 5.00,Flow 720.00, RPM 80.00, Press 1200.00, Tq 3000.00, ROP 1820.00
01/16/2021 | 08:46 | 08:50 | 0.07 | 395 | 395 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 08:50 | 08:55 | 0.08 | 395 | 489 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/395.00 t/489.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 1128.00
01/16/2021 | 08:55 | 08:59 | 0.07 | 489 | 489 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 08:59 | 09:00 | 0.02 | 489 | 500 | 11 | SUR | 1: BHA 1 | 2K | Rotary Drill f/489.00 t/500.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 660.00
01/16/2021 | 09:00 | 09:05 | 0.08 | 500 | 525 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/500.00 t/525.00, TF 80.00, w/WOB 5.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 300.00
01/16/2021 | 09:05 | 09:10 | 0.08 | 525 | 583 | 58 | SUR | 1: BHA 1 | 2K | Rotary Drill f/525.00 t/583.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 696.00
01/16/2021 | 09:10 | 09:14 | 0.07 | 583 | 583 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 09:14 | 09:15 | 0.02 | 583 | 595 | 12 | SUR | 1: BHA 1 | 2K | Rotary Drill f/583.00 t/595.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 720.00
01/16/2021 | 09:15 | 09:21 | 0.1 | 595 | 620 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/595.00 t/620.00, TF 80.00, w/WOB 5.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 250.00
01/16/2021 | 09:21 | 09:23 | 0.03 | 620 | 676 | 56 | SUR | 1: BHA 1 | 2K | Rotary Drill f/620.00 t/676.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 1680.00
01/16/2021 | 09:23 | 09:27 | 0.07 | 676 | 676 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 09:27 | 09:28 | 0.02 | 676 | 685 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/676.00 t/685.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 540.00
01/16/2021 | 09:28 | 09:34 | 0.1 | 685 | 710 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/685.00 t/710.00, TF , w/WOB 5.00,Flow 900.00, Press 1750.00, Tq 0.00, ROP 250.00
01/16/2021 | 09:34 | 09:38 | 0.07 | 710 | 769 | 59 | SUR | 1: BHA 1 | 2K | Rotary Drill f/710.00 t/769.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 885.00
01/16/2021 | 09:38 | 09:42 | 0.07 | 769 | 769 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 09:42 | 09:46 | 0.07 | 769 | 862 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/769.00 t/862.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 1395.00
01/16/2021 | 09:46 | 09:50 | 0.07 | 862 | 862 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 09:50 | 09:54 | 0.07 | 862 | 956 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/862.00 t/956.00, w/WOB 12.00,Flow 900.00, RPM 100.00, Press 2000.00, Tq 3500.00, ROP 1410.00
01/16/2021 | 09:54 | 09:58 | 0.07 | 956 | 956 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 09:58 | 09:59 | 0.02 | 956 | 965 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/956.00 t/965.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 540.00
01/16/2021 | 09:59 | 10:04 | 0.08 | 965 | 990 | 25 | SUR | 1: BHA 1 | 2J | Slide Drill f/965.00 t/990.00, TF , w/WOB 7,Flow 900, Press 1800, Tq 0, ROP 300.00
01/16/2021 | 10:04 | 10:07 | 0.05 | 990 | 1050 | 60 | SUR | 1: BHA 1 | 2K | Rotary Drill f/990.00 t/1050.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 1200.00
01/16/2021 | 10:07 | 10:11 | 0.07 | 1050 | 1050 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 10:11 | 10:15 | 0.07 | 1050 | 1144 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1050.00 t/1144.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 1410.00
01/16/2021 | 10:15 | 10:19 | 0.07 | 1144 | 1144 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 10:19 | 10:23 | 0.07 | 1144 | 1238 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1144.00 t/1238.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 1410.00
01/16/2021 | 10:23 | 10:27 | 0.07 | 1238 | 1238 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 10:27 | 10:32 | 0.08 | 1238 | 1333 | 95 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1238.00 t/1333.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 1140.00
01/16/2021 | 10:32 | 10:36 | 0.07 | 1333 | 1333 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 10:36 | 10:42 | 0.1 | 1333 | 1426 | 93 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1333.00 t/1426.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 930.00
01/16/2021 | 10:42 | 10:46 | 0.07 | 1426 | 1426 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 10:46 | 10:53 | 0.12 | 1426 | 1520 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1426.00 t/1520.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 805.71
01/16/2021 | 10:53 | 10:57 | 0.07 | 1520 | 1520 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 10:57 | 10:58 | 0.02 | 1520 | 1540 | 20 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1520.00 t/1540.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 1200.00
01/16/2021 | 10:58 | 11:07 | 0.15 | 1540 | 1575 | 35 | SUR | 1: BHA 1 | 2J | Slide Drill f/1540.00 t/1575.00, TF , w/WOB 7,Flow 900, Press 1800, Tq 0, ROP 233.33
01/16/2021 | 11:07 | 11:12 | 0.08 | 1575 | 1614 | 39 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1575.00 t/1614.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 468.00
01/16/2021 | 11:12 | 11:16 | 0.07 | 1614 | 1614 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 11:16 | 11:22 | 0.1 | 1614 | 1708 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1614.00 t/1708.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 2000.00, Tq 5000, ROP 940.00
01/16/2021 | 11:22 | 11:26 | 0.07 | 1708 | 1708 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 11:26 | 11:27 | 0.02 | 1708 | 1715 | 7 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1708.00 t/1715.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350, Tq 6500, ROP 420.00
01/16/2021 | 11:27 | 11:39 | 0.2 | 1715 | 1750 | 35 | SUR | 1: BHA 1 | 2J | Slide Drill f/1715.00 t/1750.00, TF , w/WOB 12,Flow 900.00, Press 2050, Tq 0, ROP 175.00
01/16/2021 | 11:39 | 11:42 | 0.05 | 1750 | 1802 | 52 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1750.00 t/1802.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350, Tq 6500, ROP 1040.00
01/16/2021 | 11:42 | 11:46 | 0.07 | 1802 | 1802 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 11:46 | 11:47 | 0.02 | 1802 | 1815 | 13 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1802.00 t/1815.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350, Tq 6500, ROP 780.00
01/16/2021 | 11:47 | 12:04 | 0.28 | 1815 | 1855 | 40 | SUR | 1: BHA 1 | 2J | Slide Drill f/1815.00 t/1855.00, TF , w/WOB 12,Flow 900.00, Press 2050, Tq 0, ROP 141.18
01/16/2021 | 12:04 | 12:07 | 0.05 | 1855 | 1896 | 41 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1855.00 t/1896.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350, Tq 6500, ROP 820.00
01/16/2021 | 12:07 | 12:11 | 0.07 | 1896 | 1896 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 12:11 | 12:12 | 0.02 | 1896 | 1905 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1896.00 t/1905.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 6500.00, ROP 540.00
01/16/2021 | 12:12 | 12:24 | 0.2 | 1905 | 1945 | 40 | SUR | 1: BHA 1 | 2J | Slide Drill f/1905.00 t/1945.00, TF , w/WOB 12.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 200.00
01/16/2021 | 12:24 | 12:28 | 0.07 | 1945 | 1990 | 45 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1945.00 t/1990.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 6500.00, ROP 675.00
01/16/2021 | 12:28 | 12:32 | 0.07 | 1990 | 1990 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 12:32 | 12:33 | 0.02 | 1990 | 2000 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/1990.00 t/2000.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 8500, ROP 600.00
01/16/2021 | 12:33 | 12:46 | 0.22 | 2000 | 2030 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2000.00 t/2030.00, TF , w/WOB 12.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 138.46
01/16/2021 | 12:46 | 12:49 | 0.05 | 2030 | 2084 | 54 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2030.00 t/2084.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 8500, ROP 1080.00
01/16/2021 | 12:49 | 12:53 | 0.07 | 2084 | 2084 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 12:53 | 12:59 | 0.1 | 2084 | 2178 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2084.00 t/2178.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 8500, ROP 940.00
01/16/2021 | 12:59 | 13:03 | 0.07 | 2178 | 2178 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 13:03 | 13:04 | 0.02 | 2178 | 2185 | 7 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2178.00 t/2185.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 8500, ROP 420.00
01/16/2021 | 13:04 | 13:16 | 0.2 | 2185 | 2215 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2185.00 t/2215.00, TF , w/WOB 12.00,Flow 900.00, Press 2050.00, Tq 0.00, ROP 150.00
01/16/2021 | 13:16 | 13:19 | 0.05 | 2215 | 2271 | 56 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2215.00 t/2271.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 8500, ROP 1120.00
01/16/2021 | 13:19 | 13:23 | 0.07 | 2271 | 2271 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 13:23 | 13:24 | 0.02 | 2271 | 2280 | 9 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2271.00 t/2280.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 540.00
01/16/2021 | 13:24 | 13:44 | 0.33 | 2280 | 2320 | 40 | SUR | 1: BHA 1 | 2J | Slide Drill f/2280.00 t/2320.00, TF 20.00, w/WOB 15.00,Flow 900.00, Press 2150.00, Tq 0.00, ROP 120.00
01/16/2021 | 13:44 | 13:47 | 0.05 | 2320 | 2365 | 45 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2320.00 t/2365.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 900.00
01/16/2021 | 13:47 | 13:52 | 0.08 | 2365 | 2365 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 13:52 | 13:53 | 0.02 | 2365 | 2375 | 10 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2365.00 t/2375.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 600.00
01/16/2021 | 13:53 | 14:14 | 0.35 | 2375 | 2415 | 40 | SUR | 1: BHA 1 | 2J | Slide Drill f/2375.00 t/2415.00, TF 0.00, w/WOB 15.00,Flow 900.00, Press 2150.00, Tq 0.00, ROP 114.29
01/16/2021 | 14:14 | 14:18 | 0.07 | 2415 | 2459 | 44 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2415.00 t/2459.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 660.00
01/16/2021 | 14:18 | 14:22 | 0.07 | 2459 | 2459 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 14:22 | 14:28 | 0.1 | 2459 | 2553 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2459.00 t/2553.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 940.00
01/16/2021 | 14:28 | 14:32 | 0.07 | 2553 | 2553 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 14:32 | 14:38 | 0.1 | 2553 | 2643 | 90 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2553.00 t/2643.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 900.00
01/16/2021 | 14:38 | 14:42 | 0.07 | 2643 | 2643 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 14:42 | 14:43 | 0.02 | 2643 | 2655 | 12 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2643.00 t/2655.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 720.00
01/16/2021 | 14:43 | 14:58 | 0.25 | 2655 | 2685 | 30 | SUR | 1: BHA 1 | 2J | Slide Drill f/2655.00 t/2685.00, TF , w/WOB 15.00,Flow 900.00, Press 2150.00, Tq 0.00, ROP 120.00
01/16/2021 | 14:58 | 15:04 | 0.1 | 2685 | 2740 | 55 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2685.00 t/2740.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 550.00
01/16/2021 | 15:04 | 15:09 | 0.08 | 2740 | 2740 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 15:09 | 15:13 | 0.07 | 2740 | 2834 | 94 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2740.00 t/2834.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 1410.00
01/16/2021 | 15:13 | 15:17 | 0.07 | 2834 | 2834 | 0 | SUR | 1: BHA 1 | 10D | Survey & Connection
01/16/2021 | 15:17 | 15:22 | 0.08 | 2834 | 2916 | 82 | SUR | 1: BHA 1 | 2K | Rotary Drill f/2834.00 t/2916.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2350.00, Tq 1000.00, ROP 984.00
01/16/2021 | 15:22 | 15:24 | 0.03 | 2916 | 2916 | 0 | SUR | 1: BHA 1 | 10D | Survey @ TD
01/16/2021 | 15:24 | 16:20 | 0.93 | 2916 | 2916 | 0 | SUR | 1: BHA 1 | 5A | Circulate Hole Clean @ Section TD
01/16/2021 | 16:20 | 18:40 | 2.33 | 2916 | 2916 | 0 | SUR | 1: BHA 1 | 6B | TOH
01/16/2021 | 18:40 | 19:42 | 1.03 | 2916 | 2916 | 0 | SUR | 1: BHA 1 | 6P | L/D BHA #1
01/16/2021 | 19:42 | 24:00 | 4.3 | 2916 | 2916 | 0 | SUR |  | 24B | Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_17_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 01/17/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 17830
|  |  |  | 24hr Summary: |  | Standby
|  |  |  | 24hr Lookahead: |  | Standby; Handle BHA #2; TIH; Begin Drilling Intermediate Section
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2916 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: |  | PV:
End Depth (Usft): |  | 2916 |  | 2916 |  | OD (in): |  |  |  | 300: |  | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: |  | Viscosity:
Slide Drilled (Usft): | [9 empty] | 100: |  | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: |  | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: |  | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: |  | Weight (ppg):
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) |  | Mud Type:
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 15.66 | 97.21 | 244 | 882.86 | 2063.39 | 1775.27 | 0 | 90.36 | 85.36 | 80.36 | 4209.3 | 0
Run | 0 | 15.66 | 97.21 | 244 | 882.86 | 2063.39 | 1775.27 | 0 | 90.36 | 85.36 | 80.36 | 4209.3 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 01/17/2021 |  | 4 |  | 4400 |  | 1 | 4400
Perdiem Per Hand |  |  |  |  | 01/17/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/17/2021 | 00:00 | 24:00 | 24 | 2916 | 2916 | 0 | SUR |  | 24B | Standby for Casing and Cement ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_18_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 01/18/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 25080
|  |  |  | 24hr Summary: |  | Standby; P/U BHA #2; TIH; Drill Out Shoe Track; Begin Drilling Intermediate Section
|  |  |  | 24hr Lookahead: |  | Drill Intermediate Section
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 2916 |  | 2916 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 6459 |  | 6459 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 3543 |  | 3543 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): |  | 166 |  | 166 | [5 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 3377 |  | 3377 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  | 9.08 / 1.43 |  | 9.08 / 1.43 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: |  | 2.22 |  | 2.22 |  | SN: |  | 54300 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 6.87 |  | 6.87 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 491.80 / 74.89 |  | 491.80 / 74.89 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 19.67 |  | 19.67 |  | Grade In: |  | New
% Slide: |  | 4.69 |  | 4.69 |  | Grade Out:
% Rotary: |  | 95.31 |  | 95.31 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.2 |  | 1.2
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  |  | 8 | 2 |  |  |  |  | 37.56 |  | 38.76
8" - NMPDC |  |  |  | 7.938 | 3.188 |  |  |  |  | 10.67 |  | 49.43
7 3/4" UBHO |  |  |  | 7.75 | 2.75 |  |  |  |  | 3.84 |  | 53.27
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.58 |  | 81.85
8" - NMDC |  |  |  | 7.938 | 3.125 |  |  |  |  | 28.91 |  | 110.76
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.28 |  | 113.04
6 Joints of 6.5" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 188.21 |  | 301.25
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.438 | 2.875 |  |  |  |  | 2.97 |  | 304.22
9 joints of 5" HWDP |  |  |  | 5 | 3 |  |  |  |  | 273.99 |  | 578.21
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2063.61 |  | 2641.82
NOV Agitator-Shock Sub- Safety Joint |  |  |  | 6.75 | 2 |  |  |  |  | 30.02 |  | 2671.84
2671.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800012 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
2976 | 13.78 | 317.7 | 2948.56 | 204.13 | -42.52 | 0.53 |  | 170.11 | -177.45 | -0.52 |  | 0.38 | 136
3069 | 13.33 | 316.32 | 3038.97 | 220.07 | -57.37 | 0.6 |  | -144.96 | -199.24 | -0.48 |  | -1.48 | 93
3163 | 14.48 | 318.15 | 3130.21 | 236.67 | -72.7 | 1.31 |  | 21.82 | -221.83 | 1.22 |  | 1.95 | 94
3257 | 15.1 | 317.76 | 3221.1 | 254.48 | -88.77 | 0.67 |  | -9.31 | -245.82 | 0.66 |  | -0.41 | 94
3351 | 15.47 | 316.7 | 3311.77 | 272.67 | -105.6 | 0.49 |  | -37.57 | -270.6 | 0.39 |  | -1.13 | 94
3444 | 15.68 | 315.63 | 3401.36 | 290.68 | -122.89 | 0.38 |  | -54.35 | -295.56 | 0.23 |  | -1.15 | 93
3538 | 15.77 | 320.74 | 3491.84 | 309.65 | -139.86 | 1.48 |  | 88.74 | -321.01 | 0.1 |  | 5.44 | 94
3632 | 15.99 | 322.2 | 3582.26 | 329.77 | -155.88 | 0.49 |  | 61.86 | -346.63 | 0.23 |  | 1.55 | 94
3726 | 16.09 | 321.49 | 3672.6 | 350.2 | -171.93 | 0.23 |  | -63.33 | -372.49 | 0.11 |  | -0.76 | 94
3820 | 14.58 | 319.19 | 3763.25 | 369.35 | -187.77 | 1.73 |  | -159.17 | -397.29 | -1.61 |  | -2.45 | 94
3914 | 14.49 | 318.71 | 3854.24 | 387.14 | -203.26 | 0.16 |  | -127 | -420.86 | -0.1 |  | -0.51 | 94
4009 | 14.79 | 318.9 | 3946.15 | 405.21 | -219.08 | 0.32 |  | 9.19 | -444.85 | 0.32 |  | 0.2 | 95
4103 | 14.11 | 322.63 | 4037.18 | 423.35 | -233.92 | 1.23 |  | 127.95 | -468.24 | -0.72 |  | 3.97 | 94
4197 | 13.32 | 323.39 | 4128.5 | 441.15 | -247.33 | 0.86 |  | 167.52 | -490.38 | -0.84 |  | 0.81 | 94
4291 | 13.05 | 322.46 | 4220.02 | 458.26 | -260.25 | 0.37 |  | -142.3 | -511.69 | -0.29 |  | -0.99 | 94
4385 | 12.97 | 322.74 | 4311.61 | 475.07 | -273.11 | 0.11 |  | 141.9 | -532.73 | -0.09 |  | 0.3 | 94
4479 | 13.02 | 323.26 | 4403.2 | 491.95 | -285.83 | 0.14 |  | 67.1 | -553.74 | 0.05 |  | 0.55 | 94
4572 | 12.83 | 323.85 | 4493.85 | 508.68 | -298.19 | 0.25 |  | 145.5 | -574.38 | -0.2 |  | 0.63 | 93
4667 | 12.58 | 324.01 | 4586.52 | 525.57 | -310.49 | 0.27 |  | 172.07 | -595.1 | -0.26 |  | 0.17 | 95
4760 | 12.42 | 323.95 | 4677.32 | 541.85 | -322.33 | 0.17 |  | -175.39 | -615.06 | -0.17 |  | -0.06 | 93
4854 | 13.85 | 321.45 | 4768.86 | 558.82 | -335.29 | 1.64 |  | -22.89 | -636.3 | 1.52 |  | -2.66 | 94
4948 | 15.09 | 320.65 | 4859.87 | 577.09 | -350.06 | 1.34 |  | -9.55 | -659.72 | 1.32 |  | -0.85 | 94
5042 | 14.95 | 320.38 | 4950.66 | 595.89 | -365.55 | 0.17 |  | -153.57 | -684.02 | -0.15 |  | -0.29 | 94
5136 | 14.6 | 319.1 | 5041.55 | 614.18 | -381.04 | 0.51 |  | -137.61 | -707.95 | -0.37 |  | -1.36 | 94
5230 | 14.6 | 317.44 | 5132.52 | 631.86 | -396.81 | 0.45 |  | -90.8 | -731.63 | 0 |  | -1.77 | 94
5325 | 14.85 | 315.46 | 5224.4 | 649.36 | -413.44 | 0.59 |  | -64.54 | -755.78 | 0.26 |  | -2.08 | 95
5419 | 15.22 | 314.35 | 5315.18 | 666.57 | -430.71 | 0.5 |  | -38.43 | -780.15 | 0.39 |  | -1.18 | 94
5512 | 15.48 | 312.47 | 5404.86 | 683.48 | -448.6 | 0.6 |  | -63.32 | -804.73 | 0.28 |  | -2.02 | 93
5607 | 14.1 | 314.15 | 5496.71 | 700.11 | -466.25 | 1.52 |  | 163.55 | -828.94 | -1.45 |  | 1.77 | 95
5701 | 13.68 | 314.96 | 5587.97 | 715.94 | -482.34 | 0.49 |  | 155.55 | -851.49 | -0.45 |  | 0.86 | 94
5795 | 12.73 | 319.47 | 5679.48 | 731.66 | -496.93 | 1.49 |  | 134.86 | -872.94 | -1.01 |  | 4.8 | 94
5888 | 12.95 | 319.5 | 5770.16 | 747.37 | -510.36 | 0.24 |  | 1.75 | -893.58 | 0.24 |  | 0.03 | 93
5982 | 12.14 | 318.99 | 5861.91 | 762.84 | -523.68 | 0.87 |  | -172.46 | -913.98 | -0.86 |  | -0.54 | 94
6077 | 14.09 | 319.94 | 5954.43 | 779.23 | -537.68 | 2.07 |  | 6.77 | -935.5 | 2.05 |  | 1 | 95
6171 | 13.62 | 319.07 | 6045.69 | 796.35 | -552.3 | 0.55 |  | -156.52 | -957.98 | -0.5 |  | -0.93 | 94
6265 | 12.61 | 318.85 | 6137.24 | 812.44 | -566.3 | 1.08 |  | -177.28 | -979.29 | -1.07 |  | -0.23 | 94
6360 | 12.47 | 317.02 | 6229.97 | 827.75 | -580.12 | 0.44 |  | -110.3 | -999.91 | -0.15 |  | -1.93 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 390.2 | 34.31 | 79.39 | 217 | 826 | 4369.49 | 3883.56 | 0 | 183.14 | 159.07 | 139.49 | 10959.18 | 0
Run | 390.2 | 34.31 | 79.39 | 217 | 826 | 4369.49 | 3883.56 | 0 | 183.14 | 159.07 | 139.49 | 10959.18 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 01/18/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 01/18/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/18/2021 | 00:00 | 03:00 | 3 | 2916 | 2916 | 0 | INT |  | 24B | Standby for Nipple up
01/18/2021 | 03:00 | 04:20 | 1.33 | 2916 | 2916 | 0 | INT | 2: BHA 2 | 6O | P/U BHA #2
01/18/2021 | 04:20 | 04:50 | 0.5 | 2916 | 2916 | 0 | INT | 2: BHA 2 | 6J | P/U 6.5 DC
01/18/2021 | 04:50 | 05:20 | 0.5 | 2916 | 2916 | 0 | INT | 2: BHA 2 | 5A | Surface Test MWD (OK)
01/18/2021 | 05:20 | 08:11 | 2.85 | 2916 | 2916 | 0 | INT | 2: BHA 2 | 6A | TIH to 2822
01/18/2021 | 08:11 | 08:52 | 0.68 | 2916 | 2916 | 0 | INT | 2: BHA 2 | 5A | Drill out float and shoe track
01/18/2021 | 08:52 | 08:56 | 0.07 | 2916 | 2926 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/2916.00 t/2926.00, w/WOB 20,Flow 480, RPM 50, Press 1700, Tq 5000, ROP 150.00
01/18/2021 | 08:56 | 09:11 | 0.25 | 2926 | 2926 | 0 | INT | 2: BHA 2 | 5A | Circulate
01/18/2021 | 09:11 | 09:29 | 0.3 | 2926 | 2926 | 0 | INT | 2: BHA 2 | 15D | Perform FIT
01/18/2021 | 09:29 | 09:48 | 0.32 | 2926 | 3047 | 121 | INT | 2: BHA 2 | 2K | Rotary Drill f/2926.00 t/3047.00, w/WOB 20.00,Flow 575, RPM 80, Press 2450, Tq 5800, ROP 382.11
01/18/2021 | 09:48 | 09:54 | 0.1 | 3047 | 3047 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 09:54 | 10:01 | 0.12 | 3047 | 3140 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3047.00 t/3140.00, w/WOB 30,Flow 673, RPM 80, Press 3200, Tq 5800, ROP 797.14
01/18/2021 | 10:01 | 10:05 | 0.07 | 3140 | 3140 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 10:05 | 10:07 | 0.03 | 3140 | 3150 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3140.00 t/3150.00, w/WOB 30,Flow 673, RPM 80, Press 3200, Tq 5800, ROP 300.00
01/18/2021 | 10:07 | 10:14 | 0.12 | 3150 | 3165 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3150.00 t/3165.00, TF , w/WOB 12,Flow 673, Press 2800, Tq 0, ROP 128.57
01/18/2021 | 10:14 | 10:16 | 0.03 | 3165 | 3182 | 17 | INT | 2: BHA 2 | 2K | Rotary Drill f/3165.00 t/3182.00, w/WOB 30,Flow 673, RPM 80, Press 3200, Tq 5800, ROP 510.00
01/18/2021 | 10:16 | 11:27 | 1.18 | 3182 | 3182 | 0 | INT | 2: BHA 2 | 24A | Repair flow line sensor
01/18/2021 | 11:27 | 11:34 | 0.12 | 3182 | 3234 | 52 | INT | 2: BHA 2 | 2K | Rotary Drill f/3182.00 t/3234.00, w/WOB 30.00,Flow 673.00, RPM 80.00, Press 3200.00, Tq 5800.00, ROP 445.71
01/18/2021 | 11:34 | 11:40 | 0.1 | 3234 | 3234 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 11:40 | 11:53 | 0.22 | 3234 | 3328 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3234.00 t/3328.00, w/WOB 38,Flow 900, RPM 80.00, Press 4900, Tq 6500, ROP 433.85
01/18/2021 | 11:53 | 11:57 | 0.07 | 3328 | 3328 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 11:57 | 12:06 | 0.15 | 3328 | 3422 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3328.00 t/3422.00, w/WOB 38,Flow 900, RPM 80.00, Press 4900, Tq 6500, ROP 626.67
01/18/2021 | 12:06 | 12:10 | 0.07 | 3422 | 3422 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 12:10 | 12:18 | 0.13 | 3422 | 3515 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/3422.00 t/3515.00, w/WOB 38,Flow 900, RPM 80.00, Press 4900, Tq 6500, ROP 697.50
01/18/2021 | 12:18 | 12:22 | 0.07 | 3515 | 3515 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 12:22 | 12:23 | 0.02 | 3515 | 3525 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/3515.00 t/3525.00, w/WOB 38,Flow 900, RPM 80.00, Press 4900, Tq 6500, ROP 600.00
01/18/2021 | 12:23 | 12:30 | 0.12 | 3525 | 3540 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3525.00 t/3540.00, TF , w/WOB 15,Flow 900, Press 4500, Tq 0, ROP 128.57
01/18/2021 | 12:30 | 12:36 | 0.1 | 3540 | 3609 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/3540.00 t/3609.00, w/WOB 38,Flow 900, RPM 80.00, Press 4900, Tq 6500, ROP 690.00
01/18/2021 | 12:36 | 12:40 | 0.07 | 3609 | 3609 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 12:40 | 12:48 | 0.13 | 3609 | 3703 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3609.00 t/3703.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 705.00
01/18/2021 | 12:48 | 12:52 | 0.07 | 3703 | 3703 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 12:52 | 13:00 | 0.13 | 3703 | 3797 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3703.00 t/3797.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 705.00
01/18/2021 | 13:00 | 13:04 | 0.07 | 3797 | 3797 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 13:04 | 13:06 | 0.03 | 3797 | 3805 | 8 | INT | 2: BHA 2 | 2K | Rotary Drill f/3797.00 t/3805.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 240.00
01/18/2021 | 13:06 | 13:12 | 0.1 | 3805 | 3820 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/3805.00 t/3820.00, TF , w/WOB 15,Flow 900.00, Press 4500, Tq 0, ROP 150.00
01/18/2021 | 13:12 | 13:18 | 0.1 | 3820 | 3891 | 71 | INT | 2: BHA 2 | 2K | Rotary Drill f/3820.00 t/3891.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 710.00
01/18/2021 | 13:18 | 13:22 | 0.07 | 3891 | 3891 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 13:22 | 13:30 | 0.13 | 3891 | 3985 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/3891.00 t/3985.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 705.00
01/18/2021 | 13:30 | 13:34 | 0.07 | 3985 | 3985 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 13:34 | 13:41 | 0.12 | 3985 | 4080 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/3985.00 t/4080.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 814.29
01/18/2021 | 13:41 | 13:45 | 0.07 | 4080 | 4080 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 13:45 | 13:47 | 0.03 | 4080 | 4090 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/4080.00 t/4090.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 10000.00, ROP 300.00
01/18/2021 | 13:47 | 13:56 | 0.15 | 4090 | 4105 | 15 | INT | 2: BHA 2 | 2J | Slide Drill f/4090.00 t/4105.00, TF 140.00, w/WOB 15.00,Flow 900.00, Press 4500.00, Tq 0.00, ROP 100.00
01/18/2021 | 13:56 | 14:04 | 0.13 | 4105 | 4174 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/4105.00 t/4174.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 10000.00, ROP 517.50
01/18/2021 | 14:04 | 14:10 | 0.1 | 4174 | 4174 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 14:10 | 14:16 | 0.1 | 4174 | 4268 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4174.00 t/4268.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 4900.00, Tq 6500.00, ROP 940.00
01/18/2021 | 14:16 | 14:20 | 0.07 | 4268 | 4268 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 14:20 | 14:26 | 0.1 | 4268 | 4362 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4268.00 t/4362.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 940.00
01/18/2021 | 14:26 | 14:36 | 0.17 | 4362 | 4362 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 14:36 | 14:45 | 0.15 | 4362 | 4456 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4362.00 t/4456.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 626.67
01/18/2021 | 14:45 | 14:49 | 0.07 | 4456 | 4456 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 14:49 | 14:56 | 0.12 | 4456 | 4550 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4456.00 t/4550.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 805.71
01/18/2021 | 14:56 | 15:00 | 0.07 | 4550 | 4550 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 15:00 | 15:09 | 0.15 | 4550 | 4643 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/4550.00 t/4643.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 620.00
01/18/2021 | 15:09 | 15:10 | 0.02 | 4643 | 4643 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 15:10 | 15:21 | 0.18 | 4643 | 4737 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4643.00 t/4737.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 512.73
01/18/2021 | 15:21 | 15:25 | 0.07 | 4737 | 4737 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 15:25 | 15:36 | 0.18 | 4737 | 4831 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4737.00 t/4831.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 512.73
01/18/2021 | 15:36 | 15:40 | 0.07 | 4831 | 4831 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 15:40 | 15:43 | 0.05 | 4831 | 4840 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/4831.00 t/4840.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 180.00
01/18/2021 | 15:43 | 15:53 | 0.17 | 4840 | 4860 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/4840.00 t/4860.00, TF , w/WOB 18,Flow 900.00, Press 4700, Tq 0, ROP 120.00
01/18/2021 | 15:53 | 15:59 | 0.1 | 4860 | 4925 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/4860.00 t/4925.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5100, Tq 10000, ROP 650.00
01/18/2021 | 15:59 | 16:04 | 0.08 | 4925 | 4925 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 16:04 | 16:12 | 0.13 | 4925 | 5019 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/4925.00 t/5019.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 13500, ROP 705.00
01/18/2021 | 16:12 | 16:15 | 0.05 | 5019 | 5019 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 16:15 | 16:26 | 0.18 | 5019 | 5113 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5019.00 t/5113.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 13500.00, ROP 512.73
01/18/2021 | 16:26 | 16:30 | 0.07 | 5113 | 5113 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 16:30 | 16:38 | 0.13 | 5113 | 5207 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5113.00 t/5207.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 13500.00, ROP 705.00
01/18/2021 | 16:38 | 16:43 | 0.08 | 5207 | 5207 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 16:43 | 16:52 | 0.15 | 5207 | 5301 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5207.00 t/5301.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 10000.00, ROP 626.67
01/18/2021 | 16:52 | 16:56 | 0.07 | 5301 | 5301 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 16:56 | 17:13 | 0.28 | 5301 | 5396 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/5301.00 t/5396.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 10000.00, ROP 335.29
01/18/2021 | 17:13 | 17:57 | 0.73 | 5396 | 5396 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 17:57 | 18:16 | 0.32 | 5396 | 5490 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5396.00 t/5490.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 10000.00, ROP 296.84
01/18/2021 | 18:16 | 18:25 | 0.15 | 5490 | 5490 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 18:25 | 18:36 | 0.18 | 5490 | 5583 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5490.00 t/5583.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 15000.00, ROP 507.27
01/18/2021 | 18:36 | 18:42 | 0.1 | 5583 | 5583 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 18:42 | 18:48 | 0.1 | 5583 | 5592 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/5583.00 t/5592.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 15000.00, ROP 90.00
01/18/2021 | 18:48 | 19:00 | 0.2 | 5592 | 5608 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/5592.00 t/5608.00, TF 140.00, w/WOB 12.00,Flow 674.00, Press 2950.00, Tq 0.00, ROP 80.00
01/18/2021 | 19:00 | 19:10 | 0.17 | 5608 | 5678 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/5608.00 t/5678.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 15000.00, ROP 420.00
01/18/2021 | 19:10 | 19:13 | 0.05 | 5678 | 5678 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 19:13 | 19:26 | 0.22 | 5678 | 5772 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/5678.00 t/5772.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 15000.00, ROP 433.85
01/18/2021 | 19:26 | 19:31 | 0.08 | 5772 | 5772 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 19:31 | 19:46 | 0.25 | 5772 | 5788 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/5772.00 t/5788.00, TF 90.00, w/WOB 12.00,Flow 674.00, Press 3200.00, Tq 0.00, ROP 64.00
01/18/2021 | 19:46 | 19:58 | 0.2 | 5788 | 5866 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/5788.00 t/5866.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 17500.00, ROP 390.00
01/18/2021 | 19:58 | 20:02 | 0.07 | 5866 | 5866 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 20:02 | 20:23 | 0.35 | 5866 | 5959 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5866.00 t/5959.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 17500.00, ROP 265.71
01/18/2021 | 20:23 | 20:27 | 0.07 | 5959 | 5959 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 20:27 | 20:36 | 0.15 | 5959 | 6052 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/5959.00 t/6052.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 17500.00, ROP 620.00
01/18/2021 | 20:36 | 21:14 | 0.63 | 6052 | 6052 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 21:14 | 21:15 | 0.02 | 6052 | 6053 | 1 | INT | 2: BHA 2 | 2K | Rotary Drill f/6052.00 t/6053.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 17500.00, ROP 60.00
01/18/2021 | 21:15 | 21:20 | 0.08 | 6053 | 6053 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 21:20 | 21:21 | 0.02 | 6053 | 6060 | 7 | INT | 2: BHA 2 | 2K | Rotary Drill f/6053.00 t/6060.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 17500.00, ROP 420.00
01/18/2021 | 21:21 | 21:36 | 0.25 | 6060 | 6078 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/6060.00 t/6078.00, TF 20.00, w/WOB 40.00,Flow 674.00, Press 3000.00, Tq 0.00, ROP 72.00
01/18/2021 | 21:36 | 21:44 | 0.13 | 6078 | 6148 | 70 | INT | 2: BHA 2 | 2K | Rotary Drill f/6078.00 t/6148.00, w/WOB 40.00,Flow 674.00, RPM 80.00, Press 3200.00, Tq 17500.00, ROP 525.00
01/18/2021 | 21:44 | 22:00 | 0.27 | 6148 | 6148 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 22:00 | 22:19 | 0.32 | 6148 | 6242 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6148.00 t/6242.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 17500.00, ROP 296.84
01/18/2021 | 22:19 | 22:24 | 0.08 | 6242 | 6242 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 22:24 | 22:38 | 0.23 | 6242 | 6336 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6242.00 t/6336.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 18000.00, ROP 402.86
01/18/2021 | 22:38 | 22:41 | 0.05 | 6336 | 6336 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 22:41 | 22:43 | 0.03 | 6336 | 6345 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/6336.00 t/6345.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 18000.00, ROP 270.00
01/18/2021 | 22:43 | 23:11 | 0.47 | 6345 | 6363 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/6345.00 t/6363.00, TF 0.00, w/WOB 18.00,Flow 900.00, Press 4700.00, Tq 0.00, ROP 38.57
01/18/2021 | 23:11 | 23:25 | 0.23 | 6363 | 6431 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/6363.00 t/6431.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 18000.00, ROP 291.43
01/18/2021 | 23:25 | 23:32 | 0.12 | 6431 | 6431 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/18/2021 | 23:32 | 23:56 | 0.4 | 6431 | 6449 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/6431.00 t/6449.00, TF 20.00, w/WOB 15.00,Flow 900.00, Press 4700.00, Tq 0.00, ROP 45.00
01/18/2021 | 23:56 | 24:00 | 0.07 | 6449 | 6459 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/6449.00 t/6459.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 18000.00, ROP 150.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_19_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 01/19/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 32330
|  |  |  | 24hr Summary: |  | Drilling Intermediate Section as per plan
|  |  |  | 24hr Lookahead: |  | Finish Drilling Intermediate Section; Circulate Hole Clean; TOH; L/D BHA #2; Standby for Skid Ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 6459 |  | 2916 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 9783 |  | 9783 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 3324 |  | 6867 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): |  | 302 |  | 468 | [5 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 3022 |  | 6399 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  | 19.45 / 0.00 |  | 28.53 / 1.43 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: |  | 5.82 |  | 8.03 |  | SN: |  | 54300 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 13.63 |  | 20.5 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 221.66 / 51.92 |  | 312.15 / 58.26 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 43.67 |  | Grade In: |  | New
% Slide: |  | 9.09 |  | 6.82 |  | Grade Out:
% Rotary: |  | 90.91 |  | 93.18 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.2 |  | 1.2
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  |  | 8 | 2 |  |  |  |  | 37.56 |  | 38.76
8" - NMPDC |  |  |  | 7.938 | 3.188 |  |  |  |  | 10.67 |  | 49.43
7 3/4" UBHO |  |  |  | 7.75 | 2.75 |  |  |  |  | 3.84 |  | 53.27
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.58 |  | 81.85
8" - NMDC |  |  |  | 7.938 | 3.125 |  |  |  |  | 28.91 |  | 110.76
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.28 |  | 113.04
6 Joints of 6.5" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 188.21 |  | 301.25
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.438 | 2.875 |  |  |  |  | 2.97 |  | 304.22
9 joints of 5" HWDP |  |  |  | 5 | 3 |  |  |  |  | 273.99 |  | 578.21
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2063.61 |  | 2641.82
NOV Agitator-Shock Sub- Safety Joint |  |  |  | 6.75 | 2 |  |  |  |  | 30.02 |  | 2671.84
2671.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800012 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
6454 | 13.6 | 321.68 | 6321.55 | 843.85 | -593.89 | 1.64 |  | 45.21 | -1021.07 | 1.2 |  | 4.96 | 94
6548 | 15.1 | 321.89 | 6412.62 | 862.15 | -608.3 | 1.6 |  | 2.09 | -1044.27 | 1.6 |  | 0.22 | 94
6642 | 15.07 | 321.3 | 6503.38 | 881.32 | -623.5 | 0.17 |  | -101.34 | -1068.64 | -0.03 |  | -0.63 | 94
6735 | 14.25 | 319.29 | 6593.35 | 899.44 | -638.52 | 1.04 |  | -149.16 | -1092.12 | -0.88 |  | -2.16 | 93
6829 | 13.39 | 318.36 | 6684.63 | 916.34 | -653.3 | 0.94 |  | -165.97 | -1114.56 | -0.91 |  | -0.99 | 94
6923 | 14.16 | 319.81 | 6775.93 | 933.26 | -667.95 | 0.9 |  | 24.86 | -1136.91 | 0.82 |  | 1.54 | 94
7016 | 13.95 | 321.21 | 6866.14 | 950.69 | -682.31 | 0.43 |  | 122.38 | -1159.44 | -0.23 |  | 1.51 | 93
7110 | 13.19 | 320.87 | 6957.52 | 967.84 | -696.18 | 0.81 |  | -174.17 | -1181.43 | -0.81 |  | -0.36 | 94
7204 | 14.43 | 320.64 | 7048.8 | 985.21 | -710.38 | 1.32 |  | -2.65 | -1203.81 | 1.32 |  | -0.24 | 94
7298 | 13.66 | 321.02 | 7139.99 | 1002.9 | -724.79 | 0.82 |  | 173.35 | -1226.56 | -0.82 |  | 0.4 | 94
7392 | 14.12 | 320.34 | 7231.24 | 1020.35 | -739.09 | 0.52 |  | -19.87 | -1249.06 | 0.49 |  | -0.72 | 94
7487 | 13.54 | 319.48 | 7323.48 | 1037.73 | -753.71 | 0.65 |  | -160.9 | -1271.73 | -0.61 |  | -0.91 | 95
7580 | 13.36 | 318.35 | 7413.93 | 1054.03 | -767.92 | 0.34 |  | -124.95 | -1293.35 | -0.19 |  | -1.22 | 93
7674 | 12.47 | 317.14 | 7505.55 | 1069.59 | -782.04 | 0.99 |  | -163.69 | -1314.35 | -0.95 |  | -1.29 | 94
7768 | 12.32 | 311.61 | 7597.37 | 1083.68 | -796.45 | 1.27 |  | -99.9 | -1334.49 | -0.16 |  | -5.88 | 94
7862 | 13.19 | 314.01 | 7689.05 | 1097.8 | -811.66 | 1.08 |  | 32.52 | -1355.2 | 0.93 |  | 2.55 | 94
7956 | 12.13 | 314.95 | 7780.76 | 1112.22 | -826.36 | 1.15 |  | 169.46 | -1375.78 | -1.13 |  | 1 | 94
8050 | 12.6 | 316.22 | 7872.58 | 1126.6 | -840.44 | 0.58 |  | 30.68 | -1395.91 | 0.5 |  | 1.35 | 94
8144 | 12.84 | 318.82 | 7964.27 | 1141.87 | -854.42 | 0.66 |  | 68.53 | -1416.6 | 0.26 |  | 2.77 | 94
8238 | 11.84 | 319.05 | 8056.1 | 1157.01 | -867.61 | 1.07 |  | 177.3 | -1436.67 | -1.06 |  | 0.24 | 94
8331 | 10.25 | 317.74 | 8147.37 | 1170.34 | -879.43 | 1.73 |  | -171.67 | -1454.47 | -1.71 |  | -1.41 | 93
8424 | 9.33 | 317.37 | 8239.02 | 1182.01 | -890.1 | 0.99 |  | -176.27 | -1470.28 | -0.99 |  | -0.4 | 93
8518 | 8.35 | 315.9 | 8331.9 | 1192.52 | -900.01 | 1.07 |  | -167.74 | -1484.73 | -1.04 |  | -1.56 | 94
8612 | 7.69 | 320.17 | 8424.98 | 1202.25 | -908.79 | 0.95 |  | 140.03 | -1497.83 | -0.7 |  | 4.54 | 94
8705 | 7.86 | 323.81 | 8517.13 | 1212.16 | -916.53 | 0.56 |  | 72.76 | -1510.35 | 0.18 |  | 3.91 | 93
8799 | 7.93 | 317.42 | 8610.24 | 1222.13 | -924.71 | 0.94 |  | -88.61 | -1523.21 | 0.07 |  | -6.8 | 94
8893 | 5.73 | 317.49 | 8703.57 | 1230.36 | -932.27 | 2.34 |  | 179.82 | -1534.38 | -2.34 |  | 0.07 | 94
8987 | 2.69 | 321.03 | 8797.3 | 1235.54 | -936.83 | 3.24 |  | 176.88 | -1541.28 | -3.23 |  | 3.77 | 94
9081 | 2.63 | 304.3 | 8891.2 | 1238.47 | -940 | 0.83 |  | -102.74 | -1545.58 | -0.06 |  | -17.8 | 94
9174 | 2.49 | 298.62 | 8984.11 | 1240.64 | -943.54 | 0.31 |  | -121.71 | -1549.59 | -0.15 |  | -6.11 | 93
9268 | 2.41 | 299.98 | 9078.02 | 1242.6 | -947.04 | 0.11 |  | 144.67 | -1553.43 | -0.09 |  | 1.45 | 94
9362 | 0.91 | 319.62 | 9171.98 | 1244.16 | -949.24 | 1.68 |  | 168.86 | -1556.07 | -1.6 |  | 20.89 | 94
9457 | 0.4 | 302.98 | 9266.98 | 1244.91 | -950 | 0.57 |  | -167.73 | -1557.14 | -0.54 |  | 0 | 95
9551 | 0.72 | 257.8 | 9360.97 | 1244.97 | -950.86 | 0.56 |  | -78.11 | -1557.77 | 0.34 |  | 0 | 94
9645 | 0.02 | 262.97 | 9454.97 | 1244.84 | -951.45 | 0.74 |  | 179.85 | -1558.08 | -0.74 |  | 0 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 170.9 | 37.73 | 80 | 229 | 900 | 5336.36 | 4745.45 | 0 | 235 | 190 | 155 | 18888.89 | 0
Run | 235.04 | 34.84 | 79.48 | 219 | 837.63 | 4521.43 | 4019 | 0 | 191.29 | 163.93 | 141.93 | 12189.66 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 01/19/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 01/19/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/19/2021 | 00:00 | 00:25 | 0.42 | 6459 | 6525 | 66 | INT | 2: BHA 2 | 2K | Rotary Drill f/6459.00 t/6525.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 18000.00, ROP 158.40
01/19/2021 | 00:25 | 00:30 | 0.08 | 6525 | 6525 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 00:30 | 00:31 | 0.02 | 6525 | 6528 | 3 | INT | 2: BHA 2 | 2K | Rotary Drill f/6525.00 t/6528.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5100.00, Tq 19000, ROP 180.00
01/19/2021 | 00:31 | 00:55 | 0.4 | 6528 | 6544 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/6528.00 t/6544.00, TF , w/WOB 40.00,Flow 900.00, Press 4900, Tq 0, ROP 40.00
01/19/2021 | 00:55 | 01:06 | 0.18 | 6544 | 6619 | 75 | INT | 2: BHA 2 | 2K | Rotary Drill f/6544.00 t/6619.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500, Tq 19000, ROP 409.09
01/19/2021 | 01:06 | 01:08 | 0.03 | 6619 | 6619 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 01:08 | 01:25 | 0.28 | 6619 | 6713 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6619.00 t/6713.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 331.76
01/19/2021 | 01:25 | 01:28 | 0.05 | 6713 | 6713 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 01:28 | 01:43 | 0.25 | 6713 | 6806 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6713.00 t/6806.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 372.00
01/19/2021 | 01:43 | 01:46 | 0.05 | 6806 | 6806 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 01:46 | 01:57 | 0.18 | 6806 | 6900 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/6806.00 t/6900.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 512.73
01/19/2021 | 01:57 | 02:04 | 0.12 | 6900 | 6900 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 02:04 | 02:08 | 0.07 | 6900 | 6910 | 10 | INT | 2: BHA 2 | 2K | Rotary Drill f/6900.00 t/6910.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 150.00
01/19/2021 | 02:08 | 02:25 | 0.28 | 6910 | 6926 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/6910.00 t/6926.00, TF , w/WOB 15,Flow 900.00, Press 5100, Tq 0, ROP 56.47
01/19/2021 | 02:25 | 02:39 | 0.23 | 6926 | 6994 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/6926.00 t/6994.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 291.43
01/19/2021 | 02:39 | 02:42 | 0.05 | 6994 | 6994 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 02:42 | 02:55 | 0.22 | 6994 | 7087 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/6994.00 t/7087.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 429.23
01/19/2021 | 02:55 | 02:58 | 0.05 | 7087 | 7087 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 02:58 | 03:11 | 0.22 | 7087 | 7181 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7087.00 t/7181.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 19000.00, ROP 433.85
01/19/2021 | 03:11 | 03:16 | 0.08 | 7181 | 7181 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 03:16 | 03:38 | 0.37 | 7181 | 7199 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/7181.00 t/7199.00, TF 0.00, w/WOB 18.00,Flow 674.00, Press 3400.00, Tq 0.00, ROP 49.09
01/19/2021 | 03:38 | 03:52 | 0.23 | 7199 | 7275 | 76 | INT | 2: BHA 2 | 2K | Rotary Drill f/7199.00 t/7275.00, w/WOB 35.00,Flow 674.00, RPM 80.00, Press 3800.00, Tq 19000.00, ROP 325.71
01/19/2021 | 03:52 | 03:55 | 0.05 | 7275 | 7275 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 03:55 | 04:13 | 0.3 | 7275 | 7369 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7275.00 t/7369.00, w/WOB 35.00,Flow 674.00, RPM 80.00, Press 3800.00, Tq 19000.00, ROP 313.33
01/19/2021 | 04:13 | 04:15 | 0.03 | 7369 | 7369 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 04:15 | 04:18 | 0.05 | 7369 | 7375 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/7369.00 t/7375.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 120.00
01/19/2021 | 04:18 | 04:30 | 0.2 | 7375 | 7391 | 16 | INT | 2: BHA 2 | 2J | Slide Drill f/7375.00 t/7391.00, TF , w/WOB 22,Flow 900.00, Press 5200, Tq 0, ROP 80.00
01/19/2021 | 04:30 | 04:43 | 0.22 | 7391 | 7463 | 72 | INT | 2: BHA 2 | 2K | Rotary Drill f/7391.00 t/7463.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 332.31
01/19/2021 | 04:43 | 04:46 | 0.05 | 7463 | 7463 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 04:46 | 04:59 | 0.22 | 7463 | 7558 | 95 | INT | 2: BHA 2 | 2K | Rotary Drill f/7463.00 t/7558.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 438.46
01/19/2021 | 04:59 | 05:01 | 0.03 | 7558 | 7558 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 05:01 | 05:04 | 0.05 | 7558 | 7564 | 6 | INT | 2: BHA 2 | 2K | Rotary Drill f/7558.00 t/7564.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 120.00
01/19/2021 | 05:04 | 05:25 | 0.35 | 7564 | 7582 | 18 | INT | 2: BHA 2 | 2J | Slide Drill f/7564.00 t/7582.00, TF , w/WOB 22.00,Flow 900.00, Press 5200.00, Tq 0.00, ROP 51.43
01/19/2021 | 05:25 | 05:36 | 0.18 | 7582 | 7651 | 69 | INT | 2: BHA 2 | 2K | Rotary Drill f/7582.00 t/7651.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 376.36
01/19/2021 | 05:36 | 05:40 | 0.07 | 7651 | 7651 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 05:40 | 05:52 | 0.2 | 7651 | 7745 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7651.00 t/7745.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5500.00, Tq 20000.00, ROP 470.00
01/19/2021 | 05:52 | 05:56 | 0.07 | 7745 | 7745 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 05:56 | 06:40 | 0.73 | 7745 | 7745 | 0 | INT | 2: BHA 2 | 8E | Troubleshoot gens
01/19/2021 | 06:40 | 07:17 | 0.62 | 7745 | 7775 | 30 | INT | 2: BHA 2 | 2J | Slide Drill f/7745.00 t/7775.00, TF , w/WOB 22,Flow 674, Press 3400, Tq 0, ROP 48.65
01/19/2021 | 07:17 | 07:45 | 0.47 | 7775 | 7839 | 64 | INT | 2: BHA 2 | 2K | Rotary Drill f/7775.00 t/7839.00, w/WOB 40.00,Flow 674, RPM 80.00, Press 3850, Tq 20000.00, ROP 137.14
01/19/2021 | 07:45 | 07:55 | 0.17 | 7839 | 7839 | 0 | INT | 2: BHA 2 | 24A | Calibrate blocks
01/19/2021 | 07:55 | 08:00 | 0.08 | 7839 | 7839 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 08:00 | 08:40 | 0.67 | 7839 | 7870 | 31 | INT | 2: BHA 2 | 2J | Slide Drill f/7839.00 t/7870.00, TF , w/WOB 22,Flow 900, Press 5250, Tq 0, ROP 46.50
01/19/2021 | 08:40 | 08:52 | 0.2 | 7870 | 7933 | 63 | INT | 2: BHA 2 | 2K | Rotary Drill f/7870.00 t/7933.00, w/WOB 40.00,Flow 900, RPM 80.00, Press 5800, Tq 20000.00, ROP 315.00
01/19/2021 | 08:52 | 08:59 | 0.12 | 7933 | 7933 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 08:59 | 09:13 | 0.23 | 7933 | 8027 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/7933.00 t/8027.00, w/WOB 40.00,Flow 900, RPM 80.00, Press 5800, Tq 20000.00, ROP 402.86
01/19/2021 | 09:13 | 09:18 | 0.08 | 8027 | 8027 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 09:18 | 09:22 | 0.07 | 8027 | 8035 | 8 | INT | 2: BHA 2 | 2K | Rotary Drill f/8027.00 t/8035.00, w/WOB 40.00,Flow 900, RPM 80.00, Press 5800, Tq 20000.00, ROP 120.00
01/19/2021 | 09:22 | 09:46 | 0.4 | 8035 | 8070 | 35 | INT | 2: BHA 2 | 2J | Slide Drill f/8035.00 t/8070.00, TF , w/WOB 22,Flow 900, Press 5250, Tq 0, ROP 87.50
01/19/2021 | 09:46 | 09:56 | 0.17 | 8070 | 8121 | 51 | INT | 2: BHA 2 | 2K | Rotary Drill f/8070.00 t/8121.00, w/WOB 40.00,Flow 900, RPM 80.00, Press 5800, Tq 20000.00, ROP 306.00
01/19/2021 | 09:56 | 10:00 | 0.07 | 8121 | 8121 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 10:00 | 10:31 | 0.52 | 8121 | 8215 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8121.00 t/8215.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 181.94
01/19/2021 | 10:31 | 10:35 | 0.07 | 8215 | 8215 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 10:35 | 10:54 | 0.32 | 8215 | 8309 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8215.00 t/8309.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 296.84
01/19/2021 | 10:54 | 11:00 | 0.1 | 8309 | 8309 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 11:00 | 11:16 | 0.27 | 8309 | 8402 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8309.00 t/8402.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 348.75
01/19/2021 | 11:16 | 11:20 | 0.07 | 8402 | 8402 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 11:20 | 11:50 | 0.5 | 8402 | 8495 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8402.00 t/8495.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 186.00
01/19/2021 | 11:50 | 11:54 | 0.07 | 8495 | 8495 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 11:54 | 12:08 | 0.23 | 8495 | 8589 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8495.00 t/8589.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 402.86
01/19/2021 | 12:08 | 12:13 | 0.08 | 8589 | 8589 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 12:13 | 12:26 | 0.22 | 8589 | 8683 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/8589.00 t/8683.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 433.85
01/19/2021 | 12:26 | 12:30 | 0.07 | 8683 | 8683 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 12:30 | 12:44 | 0.23 | 8683 | 8776 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/8683.00 t/8776.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 398.57
01/19/2021 | 12:44 | 12:50 | 0.1 | 8776 | 8776 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 12:50 | 12:55 | 0.08 | 8776 | 8785 | 9 | INT | 2: BHA 2 | 2K | Rotary Drill f/8776.00 t/8785.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 108.00
01/19/2021 | 12:55 | 13:26 | 0.52 | 8785 | 8805 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8785.00 t/8805.00, TF , w/WOB 18,Flow 800.00, Press 4600, Tq 0, ROP 38.71
01/19/2021 | 13:26 | 13:35 | 0.15 | 8805 | 8870 | 65 | INT | 2: BHA 2 | 2K | Rotary Drill f/8805.00 t/8870.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 433.33
01/19/2021 | 13:35 | 13:40 | 0.08 | 8870 | 8870 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 13:40 | 14:24 | 0.73 | 8870 | 8907 | 37 | INT | 2: BHA 2 | 2J | Slide Drill f/8870.00 t/8907.00, TF , w/WOB 18,Flow 800.00, Press 4600, Tq 0, ROP 50.45
01/19/2021 | 14:24 | 14:34 | 0.17 | 8907 | 8964 | 57 | INT | 2: BHA 2 | 2K | Rotary Drill f/8907.00 t/8964.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 342.00
01/19/2021 | 14:34 | 14:40 | 0.1 | 8964 | 8964 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 14:40 | 15:06 | 0.43 | 8964 | 8984 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/8964.00 t/8984.00, TF , w/WOB 18,Flow 800.00, Press 4600, Tq 0, ROP 46.15
01/19/2021 | 15:06 | 15:17 | 0.18 | 8984 | 9058 | 74 | INT | 2: BHA 2 | 2K | Rotary Drill f/8984.00 t/9058.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 403.64
01/19/2021 | 15:17 | 15:20 | 0.05 | 9058 | 9058 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 15:20 | 15:36 | 0.27 | 9058 | 9152 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9058.00 t/9152.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 352.50
01/19/2021 | 15:36 | 15:40 | 0.07 | 9152 | 9152 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 15:40 | 15:55 | 0.25 | 9152 | 9245 | 93 | INT | 2: BHA 2 | 2K | Rotary Drill f/9152.00 t/9245.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 372.00
01/19/2021 | 15:55 | 16:00 | 0.08 | 9245 | 9245 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 16:00 | 16:16 | 0.27 | 9245 | 9339 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9245.00 t/9339.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 352.50
01/19/2021 | 16:16 | 16:20 | 0.07 | 9339 | 9339 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 16:20 | 16:23 | 0.05 | 9339 | 9350 | 11 | INT | 2: BHA 2 | 2K | Rotary Drill f/9339.00 t/9350.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 220.00
01/19/2021 | 16:23 | 16:42 | 0.32 | 9350 | 9375 | 25 | INT | 2: BHA 2 | 2J | Slide Drill f/9350.00 t/9375.00, TF 120.00, w/WOB 26.00,Flow 800.00, Press 4550.00, Tq 0.00, ROP 78.95
01/19/2021 | 16:42 | 16:54 | 0.2 | 9375 | 9443 | 68 | INT | 2: BHA 2 | 2K | Rotary Drill f/9375.00 t/9443.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 340.00
01/19/2021 | 16:54 | 17:00 | 0.1 | 9443 | 9443 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 17:00 | 17:28 | 0.47 | 9443 | 9528 | 85 | INT | 2: BHA 2 | 2K | Rotary Drill f/9443.00 t/9528.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 182.14
01/19/2021 | 17:28 | 17:32 | 0.07 | 9528 | 9528 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 17:32 | 18:19 | 0.78 | 9528 | 9622 | 94 | INT | 2: BHA 2 | 2K | Rotary Drill f/9528.00 t/9622.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 120.00
01/19/2021 | 18:19 | 18:23 | 0.07 | 9622 | 9622 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/19/2021 | 18:23 | 18:55 | 0.53 | 9622 | 9642 | 20 | INT | 2: BHA 2 | 2J | Slide Drill f/9622.00 t/9642.00, TF , w/WOB 20,Flow 800.00, Press 4650, Tq 0, ROP 37.50
01/19/2021 | 18:55 | 22:45 | 3.83 | 9642 | 9783 | 141 | INT | 2: BHA 2 | 2K | Rotary Drill f/9642.00 t/9783.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 36.78
01/19/2021 | 22:45 | 24:00 | 1.25 | 9783 | 9783 | 0 | INT | 2: BHA 2 | 8A | Repair Top Drive Blower Motor Plug
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_20_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 01/20/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 39580
|  |  |  | 24hr Summary: |  | Continue Drilling Intermediate Section; Circulate Hole Clean; TOH; L/D BHA #2; Standby
|  |  |  | 24hr Lookahead: |  | Standby
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 9783 |  | 9904 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 10171 |  | 10171 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 267 |  | 267 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): |  | 149 |  | 149 | [5 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 118 |  | 118 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  | 5.18 / 1.23 |  | 5.18 / 1.23 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: |  | 3.85 |  | 3.85 |  | SN: |  | 54300 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 1.33 |  | 1.33 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 88.50 / 38.70 |  | 88.50 / 38.70 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 13.5 |  | 13.5 |  | Grade In: |  | New
% Slide: |  | 55.81 |  | 55.81 |  | Grade Out:
% Rotary: |  | 44.19 |  | 44.19 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.2 |  | 1.2
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  |  | 8 | 2 |  |  |  |  | 37.56 |  | 38.76
8" - NMPDC |  |  |  | 7.938 | 3.188 |  |  |  |  | 10.67 |  | 49.43
7 3/4" UBHO |  |  |  | 7.75 | 2.75 |  |  |  |  | 3.84 |  | 53.27
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.58 |  | 81.85
8" - NMDC |  |  |  | 7.938 | 3.125 |  |  |  |  | 28.91 |  | 110.76
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.28 |  | 113.04
6 Joints of 6.5" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 188.21 |  | 301.25
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.438 | 2.875 |  |  |  |  | 2.97 |  | 304.22
9 joints of 5" HWDP |  |  |  | 5 | 3 |  |  |  |  | 273.99 |  | 578.21
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2063.61 |  | 2641.82
NOV Agitator-Shock Sub- Safety Joint |  |  |  | 6.75 | 2 |  |  |  |  | 30.02 |  | 2671.84
2671.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800012 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
9739 | 0.06 | 222.7 | 9548.97 | 1244.8 | -951.5 | 0.05 |  | -56.39 | -1558.09 | 0.04 |  | 0 | 94
9833 | 0.34 | 254.27 | 9642.97 | 1244.69 | -951.8 | 0.31 |  | 37.78 | -1558.22 | 0.3 |  | 0 | 94
9927 | 0.7 | 162.6 | 9736.97 | 1244.07 | -951.9 | 0.84 |  | -117.25 | -1557.83 | 0.38 |  | 0 | 94
10022 | 8.2 | 145.7 | 9831.61 | 1237.91 | -947.9 | 7.93 |  | -18.44 | -1550.61 | 7.89 |  | 0 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 191.05 | 40 | 80 | 213 | 800 | 4950 | 4300 | 0 | 300 | 245 | 180 | 20000 | 0
Run | 234.1 | 34.97 | 79.68 | 218 | 831.07 | 4699.57 | 4179.57 | 0 | 225.91 | 190.09 | 156.03 | 15096.77 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 01/20/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 01/20/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/20/2021 | 00:00 | 00:10 | 0.17 | 9783 | 9783 | 0 | INT | 2: BHA 2 | 8A | Repair Top Drive Blower Motor Plug
01/20/2021 | 00:10 | 00:18 | 0.13 | 9783 | 9810 | 27 | INT | 2: BHA 2 | 2K | Rotary Drill f/9783.00 t/9810.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 202.50
01/20/2021 | 00:18 | 00:21 | 0.05 | 9810 | 9810 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/20/2021 | 00:21 | 00:24 | 0.05 | 9810 | 9826 | 16 | INT | 2: BHA 2 | 2K | Rotary Drill f/9810.00 t/9826.00, w/WOB 40.00,Flow 800.00, RPM 80.00, Press 4950.00, Tq 20000.00, ROP 320.00
01/20/2021 | 00:24 | 03:10 | 2.77 | 9826 | 9826 | 0 | INT | 2: BHA 2 | 20C | Troubleshoot MWD
01/20/2021 | 03:10 | 03:37 | 0.45 | 9826 | 9904 | 78 | INT | 2: BHA 2 | 2K | Rotary Drill f/9826.00 t/9904.00, w/WOB 35,Flow 800.00, RPM 80.00, Press 5100, Tq 20000.00, ROP 173.33
01/20/2021 | 03:37 | 04:02 | 0.42 | 9904 | 9904 | 0 | INT | 2: BHA 2 | 20C | Troubleshoot MWD
01/20/2021 | 04:02 | 04:06 | 0.07 | 9904 | 9904 | 0 | INT | 2: BHA 2 | 10D | Survey & Connection
01/20/2021 | 04:06 | 04:40 | 0.57 | 9904 | 9904 | 0 | INT | 2: BHA 2 | 5A | Circulate. prepare to TOH to c/o MWD tool
01/20/2021 | 04:40 | 09:30 | 4.83 | 9904 | 9904 | 0 | INT | 2: BHA 2 | 6B | TOH to change out MWD tool
01/20/2021 | 09:30 | 10:15 | 0.75 | 9904 | 9904 | 0 | INT | 2: BHA 2 | 6P | Pull MWD, drin motor and inspect bit
01/20/2021 | 10:15 | 10:30 | 0.25 | 9904 | 9904 | 0 | INT | 3: BHA 3 | 6O | Set MWD tool and test same
01/20/2021 | 10:30 | 15:50 | 5.33 | 9904 | 9904 | 0 | INT | 3: BHA 3 | 6A | TIH to 9924
01/20/2021 | 15:50 | 18:12 | 2.37 | 9904 | 9998 | 94 | INT | 3: BHA 3 | 2J | Slide Drill f/9924.00 t/9998.00, TF , w/WOB 18,Flow 675, Press 3950, Tq 0, ROP 31.27
01/20/2021 | 18:12 | 18:18 | 0.1 | 9998 | 9998 | 0 | INT | 3: BHA 3 | 10D | Survey & Connection
01/20/2021 | 18:18 | 18:26 | 0.13 | 9998 | 10008 | 10 | INT | 3: BHA 3 | 2K | Rotary Drill f/9998.00 t/10008.00, w/WOB 40,Flow 675, RPM 50, Press 4300, Tq 21000, ROP 75.00
01/20/2021 | 18:26 | 19:55 | 1.48 | 10008 | 10063 | 55 | INT | 3: BHA 3 | 2J | Slide Drill f/10008.00 t/10063.00, TF , w/WOB 18,Flow 675, Press 3950, Tq 0, ROP 37.08
01/20/2021 | 19:55 | 20:11 | 0.27 | 10063 | 10093 | 30 | INT | 3: BHA 3 | 2K | Rotary Drill f/10063.00 t/10093.00, w/WOB 40,Flow 675, RPM 50, Press 4300, Tq 21000, ROP 112.50
01/20/2021 | 20:11 | 20:18 | 0.12 | 10093 | 10093 | 0 | INT | 3: BHA 3 | 10D | Survey & Connection
01/20/2021 | 20:18 | 21:14 | 0.93 | 10093 | 10171 | 78 | INT | 3: BHA 3 | 2K | Rotary Drill f/10093.00 t/10171.00, w/WOB 40,Flow 675, RPM 50, Press 4300, Tq 21000, ROP 83.57
01/20/2021 | 21:14 | 21:20 | 0.1 | 10171 | 10171 | 0 | INT | 3: BHA 3 | 5A | MWD Survey @ TD of intermediate
01/20/2021 | 21:20 | 22:28 | 1.13 | 10171 | 10171 | 0 | INT | 3: BHA 3 | 5A | Circulate hole clean, prpeare to TOH to run intermediate casing
01/20/2021 | 22:28 | 24:00 | 1.53 | 10171 | 10171 | 0 | INT | 3: BHA 3 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 1_21_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 01/21/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 46830
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10171 |  | 9904 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 10171 |  | 10171 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  |  |  | 267 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): |  |  |  | 149 | [5 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): |  |  |  | 118 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  |  |  | 5.18 / 1.23 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: |  |  |  | 3.85 |  | SN: |  | 54300 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  |  |  | 1.33 |  | Bit # |  | 2 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 88.50 / 38.70 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 3.5 |  | 17 |  | Grade In: |  | New
% Slide: |  |  |  | 55.81 |  | Grade Out:
% Rotary: |  |  |  | 44.19 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Billy McFarland |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s - TFA 1.49 |  |  |  | 9.875 | 2 |  |  |  |  | 1.2 |  | 1.2
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  |  | 8 | 2 |  |  |  |  | 37.56 |  | 38.76
8" - NMPDC |  |  |  | 7.938 | 3.188 |  |  |  |  | 10.67 |  | 49.43
7 3/4" UBHO |  |  |  | 7.75 | 2.75 |  |  |  |  | 3.84 |  | 53.27
8" - NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 28.58 |  | 81.85
8" - NMDC |  |  |  | 7.938 | 3.125 |  |  |  |  | 28.91 |  | 110.76
X/O- 4 1/2 XHB x 6 5/8 RegP |  |  |  | 6.5 | 2.875 |  |  |  |  | 2.28 |  | 113.04
6 Joints of 6.5" Drill Collars |  |  |  | 6.5 | 2.875 |  |  |  |  | 188.21 |  | 301.25
X/O- 4 1/2 IFB x 4 1/2 XHP |  |  |  | 6.438 | 2.875 |  |  |  |  | 2.97 |  | 304.22
9 joints of 5" HWDP |  |  |  | 5 | 3 |  |  |  |  | 273.99 |  | 578.21
22 Stands of Drill Pipe |  |  |  | 5 | 2.75 |  |  |  |  | 2063.61 |  | 2641.82
NOV Agitator-Shock Sub- Safety Joint |  |  |  | 6.75 | 2 |  |  |  |  | 30.02 |  | 2671.84
2671.84
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800012 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 5.9 |  | 2 |  | 0.17 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 40 | 80 | 213 | 800 | 4950 | 4300 | 0 | 300 | 245 | 180 | 20000 | 0
Run | 51.51 | 34.97 | 79.68 | 218 | 831.07 | 4699.57 | 4179.57 | 0 | 225.91 | 190.09 | 156.03 | 15096.77 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 01/21/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 01/21/2021 |  | 6 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
01/21/2021 | 00:00 | 03:00 | 3 | 10171 | 10171 | 0 | INT | 3: BHA 3 | 6B | TOH
01/21/2021 | 03:00 | 03:30 | 0.5 | 10171 | 10171 | 0 | INT | 3: BHA 3 | 6P | Lay down MWD tool, rack back BHA in derrick
01/21/2021 | 03:30 | 24:00 | 20.5 | 10171 | 10171 | 0 | INT |  | 24B | Standby for casing opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_12_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/12/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19850 |  |  | Well Cost($): |  | 66680
|  |  |  | 24hr Summary: |  | Standby for casing opps.
|  |  |  | 24hr Lookahead: |  | Standby for rig skid. Nipple up BOPs, test same. Pick up BHA 4. TIH
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10171 |  | 10171 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 10171 |  | 10171 |  | OD (in): |  |  |  | 300: | 20 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): | [9 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  | 0.00 / 0.33 |  | 0.00 / 0.33 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: | [5 empty] | SN: |  | 13522000 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 0.75 |  | 0.75 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Chris Day |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.72 |  | 0.72
6/7 8.8 2.00 Slick HS88 .017 |  |  |  | 5.5 | 2 |  |  |  |  | 33.04 |  | 33.76
BTI Valve |  |  |  | 4.938 | 2.563 |  |  |  |  | 2.43 |  | 36.19
NM Pony Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 11.51 |  | 47.7
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 51.7
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.98 |  | 82.68
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.38 |  | 113.06
Tomax Thruster |  |  |  | 5 | 2.25 |  |  |  |  | 17.95 |  | 131.01
XO- XT39Pin x DS42Box |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.24 |  | 134.25
2 Stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 190.36 |  | 324.61
Drill N Ream Reamer |  |  |  | 5.25 | 2.75 |  |  |  |  | 7.93 |  | 332.54
25 stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2378.29 |  | 2710.83
Agitator-Shock Sub-Safety Joint |  |  |  | 5.375 | 3 |  |  |  |  | 29.12 |  | 2739.95
2739.95
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 40 | 80 | 624 | 800 | 4950 | 4300 | 0 | 300 | 245 | 180 | 20000 | 0
Run | 0 | 34.97 | 79.68 | 645 | 831.07 | 4699.57 | 4179.57 | 0 | 225.91 | 190.09 | 156.03 | 15096.77 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 03/12/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 03/12/2021 |  | 6 |  | 100 |  | 4 | 400
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 03/12/2021 |  | 8 |  | 1500 |  | 1 | 1500
5 Premium Motor Stator Reline |  |  |  |  | 03/12/2021 |  | 12 |  | 10500 |  | 1 | 10500
Real Time Survey Management |  |  |  |  | 03/12/2021 |  | 22 |  | 600 |  | 1 | 600
Total | [11 empty] | 19850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/12/2021 | 00:00 | 21:45 | 21.75 | 10171 | 10171 | 0 | CRV |  | 24B | Standby for rig skid, nipple up BOPs, test same
03/12/2021 | 21:45 | 23:15 | 1.5 | 10171 | 10171 | 0 | CRV | 4: BHA 4 | 6O | PU BHA 4
03/12/2021 | 23:15 | 23:35 | 0.33 | 10171 | 10171 | 0 | CRV | 4: BHA 4 | 5A | Test MWD
03/12/2021 | 23:35 | 24:00 | 0.42 | 10171 | 10171 | 0 | CRV | 4: BHA 4 | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_13_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/13/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 76530
|  |  |  | 24hr Summary: |  | Standby, PU BHA & TIH
|  |  |  | 24hr Lookahead: |  | Drill Curve & Begin Lateral
Drilling Summary |  | 24Hr (BHA 4) |  | Run (BHA 4) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10171 |  | 10171 |  | Csg Shoe MD(Usft): |  | 10148 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 10920 |  | 10920 |  | OD (in): |  | 7.625 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): |  | 749 |  | 749 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): |  | 516 |  | 516 | [5 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): |  | 233 |  | 233 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  | 11.87 / 4.47 |  | 11.87 / 4.80 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: |  | 10.05 |  | 10.05 |  | SN: |  | 13522000 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 1.82 |  | 1.82 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 128.26 / 51.34 |  | 128.26 / 51.34 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 24.75 |  | Grade In: |  | New
% Slide: |  | 68.89 |  | 68.89 |  | Grade Out:
% Rotary: |  | 31.11 |  | 31.11 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Chris Day |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.72 |  | 0.72
6/7 8.8 2.00 Slick HS88 .017 |  |  |  | 5.5 | 2 |  |  |  |  | 33.04 |  | 33.76
BTI Valve |  |  |  | 4.938 | 2.563 |  |  |  |  | 2.43 |  | 36.19
NM Pony Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 11.51 |  | 47.7
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 51.7
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.98 |  | 82.68
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.38 |  | 113.06
Tomax Thruster |  |  |  | 5 | 2.25 |  |  |  |  | 17.95 |  | 131.01
XO- XT39Pin x DS42Box |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.24 |  | 134.25
2 Stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 190.36 |  | 324.61
Drill N Ream Reamer |  |  |  | 5.25 | 2.75 |  |  |  |  | 7.93 |  | 332.54
25 stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2378.29 |  | 2710.83
Agitator-Shock Sub-Safety Joint |  |  |  | 5.375 | 3 |  |  |  |  | 29.12 |  | 2739.95
2739.95
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10190 | 10.23 | 148.13 | 9997.02 | 1213.29 | -932.02 | 0.66 |  | 163.88 | -1521.82 | -0.63 |  | 1.03 | 90
10285 | 21.74 | 141.6 | 10088.2 | 1192.27 | -916.58 | 12.24 |  | -12.06 | -1495.94 | 12.12 |  | -6.87 | 95
10380 | 30.83 | 135.54 | 10173.31 | 1161.03 | -888.54 | 9.97 |  | -19.2 | -1453.98 | 9.57 |  | -6.38 | 95
10474 | 36.71 | 135.57 | 10251.41 | 1123.75 | -851.97 | 6.26 |  | 0.18 | -1401.76 | 6.26 |  | 0.03 | 94
10569 | 42.31 | 133.84 | 10324.68 | 1081.29 | -809 | 6.01 |  | -11.79 | -1341.38 | 5.89 |  | -1.82 | 95
10663 | 53.34 | 133.63 | 10387.69 | 1033.21 | -758.73 | 11.74 |  | -0.88 | -1271.91 | 11.73 |  | -0.22 | 94
10758 | 61.23 | 135.83 | 10439 | 976.96 | -702.04 | 8.53 |  | 13.81 | -1192.09 | 8.31 |  | 2.32 | 95
10853 | 61.59 | 135.73 | 10484.46 | 917.18 | -643.87 | 0.39 |  | -13.73 | -1108.68 | 0.38 |  | -0.11 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 63.12 | 36.07 | 30 | 283 | 371.43 | 3792.86 | 3153.21 | 0 | 239.64 | 199.64 | 166.07 | 13200 | 0
Run | 63.12 | 36.07 | 30 | 283 | 371.43 | 3792.86 | 3153.21 | 0 | 239.64 | 199.64 | 166.07 | 13200 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 03/13/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 03/13/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 03/13/2021 |  | 22 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/13/2021 |  | 18 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/13/2021 | 00:00 | 04:00 | 4 | 10171 | 10171 | 0 | CRV | 4: BHA 4 | 6A | TIH
03/13/2021 | 04:00 | 05:10 | 1.17 | 10171 | 10171 | 0 | CRV | 4: BHA 4 | 5A | Drill Float, Cement and Shoe Track
03/13/2021 | 05:10 | 05:12 | 0.03 | 10171 | 10181 | 10 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10171.00 t/10181.00, w/WOB 10,Flow 250, RPM 30, Press 2100, Tq 10000, ROP 300.00
03/13/2021 | 05:12 | 06:05 | 0.88 | 10181 | 10181 | 0 | CRV | 4: BHA 4 | 5A | Circulate for FIT
03/13/2021 | 06:05 | 06:30 | 0.42 | 10181 | 10181 | 0 | CRV | 4: BHA 4 | 15D | FIT
03/13/2021 | 06:30 | 09:30 | 3 | 10181 | 10257 | 76 | CRV | 4: BHA 4 | 2J | Slide Drill f/10181.00 t/10257.00, TF , w/WOB 35,Flow 350, Press 3400, Tq 0, ROP 25.33
03/13/2021 | 09:30 | 09:40 | 0.17 | 10257 | 10257 | 0 | CRV | 4: BHA 4 | 10D | Survey & Connection
03/13/2021 | 09:40 | 11:15 | 1.58 | 10257 | 10352 | 95 | CRV | 4: BHA 4 | 2J | Slide Drill f/10257.00 t/10352.00, TF , w/WOB 35.00,Flow 350.00, Press 3400.00, Tq 0.00, ROP 60.00
03/13/2021 | 11:15 | 11:25 | 0.17 | 10352 | 10352 | 0 | CRV | 4: BHA 4 | 10D | Survey & Connection
03/13/2021 | 11:25 | 11:50 | 0.42 | 10352 | 10387 | 35 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10352.00 t/10387.00, w/WOB 35.00,Flow 350.00, RPM 30.00, Press 3700.00, Tq 13000.00, ROP 84.00
03/13/2021 | 11:50 | 12:46 | 0.93 | 10387 | 10447 | 60 | CRV | 4: BHA 4 | 2J | Slide Drill f/10387.00 t/10447.00, TF 0.00, w/WOB 35.00,Flow 350.00, Press 3400.00, Tq 0.00, ROP 64.29
03/13/2021 | 12:46 | 12:56 | 0.17 | 10447 | 10447 | 0 | CRV | 4: BHA 4 | 10D | Survey & Connection
03/13/2021 | 12:56 | 13:25 | 0.48 | 10447 | 10497 | 50 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10447.00 t/10497.00, w/WOB 35.00,Flow 350.00, RPM 30.00, Press 3700.00, Tq 13000.00, ROP 103.45
03/13/2021 | 13:25 | 13:47 | 0.37 | 10497 | 10541 | 44 | CRV | 4: BHA 4 | 2J | Slide Drill f/10497.00 t/10541.00, TF , w/WOB 35.00,Flow 350.00, Press 3400.00, Tq 0.00, ROP 120.00
03/13/2021 | 13:47 | 13:57 | 0.17 | 10541 | 10541 | 0 | CRV | 4: BHA 4 | 10D | Survey & Connection
03/13/2021 | 13:57 | 15:14 | 1.28 | 10541 | 10636 | 95 | CRV | 4: BHA 4 | 2J | Slide Drill f/10541.00 t/10636.00, TF , w/WOB 35.00,Flow 350.00, Press 3400.00, Tq 0.00, ROP 74.03
03/13/2021 | 15:14 | 15:24 | 0.17 | 10636 | 10636 | 0 | CRV | 4: BHA 4 | 10D | Survey & Connection
03/13/2021 | 15:24 | 16:09 | 0.75 | 10636 | 10697 | 61 | CRV | 4: BHA 4 | 2J | Slide Drill f/10636.00 t/10697.00, TF , w/WOB 45,Flow 400.00, Press 4100.00, Tq 0.00, ROP 81.33
03/13/2021 | 16:09 | 16:19 | 0.17 | 10697 | 10697 | 0 | CRV | 4: BHA 4 | 1G | Check Shot
03/13/2021 | 16:19 | 16:28 | 0.15 | 10697 | 10730 | 33 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10697.00 t/10730.00, w/WOB 35.00,Flow 400.00, RPM 30, Press 4400, Tq 15000, ROP 220.00
03/13/2021 | 16:28 | 16:38 | 0.17 | 10730 | 10730 | 0 | CRV | 4: BHA 4 | 10D | Survey & Connection
03/13/2021 | 16:38 | 16:58 | 0.33 | 10730 | 10800 | 70 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10730.00 t/10800.00, w/WOB 35.00,Flow 400.00, RPM 30, Press 4400, Tq 15000, ROP 210.00
03/13/2021 | 16:58 | 17:08 | 0.17 | 10800 | 10800 | 0 | CRV | 4: BHA 4 | 1G | Check Shot
03/13/2021 | 17:08 | 17:28 | 0.33 | 10800 | 10825 | 25 | CRV | 4: BHA 4 | 2J | Slide Drill f/10800.00 t/10825.00, TF , w/WOB 45,Flow 400.00, Press 4100.00, Tq 0.00, ROP 75.00
03/13/2021 | 17:28 | 17:52 | 0.4 | 10825 | 10860 | 35 | CRV | 4: BHA 4 | 2K | Rotary Drill f/10825.00 t/10860.00, w/WOB 45.00,Flow 400.00, RPM 0.00, Press 4100.00, Tq 0.00, ROP 87.50
03/13/2021 | 17:52 | 19:40 | 1.8 | 10860 | 10920 | 60 | CRV | 4: BHA 4 | 2J | Slide Drill f/10860.00 t/10920.00, TF , w/WOB 45.00,Flow 400.00, Press 4100.00, Tq 0.00, ROP 33.33
03/13/2021 | 19:40 | 20:30 | 0.83 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 5A | Trouble Shoot MWD
03/13/2021 | 20:30 | 22:05 | 1.58 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 5A | Circulate to POOH
03/13/2021 | 22:05 | 24:00 | 1.92 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 6B | POOH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_14_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/14/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 19850 |  |  | Well Cost($): |  | 96380
|  |  |  | 24hr Summary: |  | Drill Curve, POOh MWD issue
|  |  |  | 24hr Lookahead: |  | PU BHA, finishe curve & begin lateral
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10920 |  | 10920 |  | Csg Shoe MD(Usft): |  | 10148 |  | 600: | 30 | PV: | 10
End Depth (Usft): |  | 10920 |  | 10920 |  | OD (in): |  | 7.625 |  | 300: | 20 | YP: | 10
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  | 29.7 |  | 200: | 15 | Viscosity: | 45
Slide Drilled (Usft): | [9 empty] | 100: | 10 | Chlorides: | 52000
Rotary Drilled (Usft): | [9 empty] | 6: | 5 | % Sand/Solids: | 0.00 / 7.90
Drlg/Circ Hrs: |  | 0.00 / 0.25 |  | 0.00 / 0.25 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 76.00
Slide Drilling Hrs: | [5 empty] | SN: |  | 13522000 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 0.5 |  | 0.5 |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Chris Day |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.72 |  | 0.72
6/7 8.8 2.00 Slick HS88 .017 |  |  |  | 5.5 | 2 |  |  |  |  | 33.04 |  | 33.76
BTI Valve |  |  |  | 4.938 | 2.563 |  |  |  |  | 2.43 |  | 36.19
NM Pony Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 11.51 |  | 47.7
UBHO |  |  |  | 5.25 | 2.5 |  |  |  |  | 4 |  | 51.7
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.98 |  | 82.68
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.38 |  | 113.06
Tomax Thruster |  |  |  | 5 | 2.25 |  |  |  |  | 17.95 |  | 131.01
XO- XT39Pin x DS42Box |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.24 |  | 134.25
2 Stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 190.36 |  | 324.61
Drill N Ream Reamer |  |  |  | 5.25 | 2.75 |  |  |  |  | 7.93 |  | 332.54
25 stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2378.29 |  | 2710.83
Agitator-Shock Sub-Safety Joint |  |  |  | 5.375 | 3 |  |  |  |  | 29.12 |  | 2739.95
2739.95
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250004 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.03 |  | 2 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 0 | 0 | 283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run | 63.12 | 36.07 | 30 | 283 | 371.43 | 3792.86 | 3153.21 | 0 | 239.64 | 199.64 | 166.07 | 13200 | 0
Comments
Drilling Plan 2
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 03/14/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 03/14/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 03/14/2021 |  | 22 |  | 600 |  | 1 | 600
Used Mud Motor Inspection(First 3 included in Mob/DeMob) |  |  |  |  | 03/14/2021 |  | 8 |  | 1500 |  | 1 | 1500
5 Premium Motor Stator Reline |  |  |  |  | 03/14/2021 |  | 12 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 19850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/14/2021 | 00:00 | 00:30 | 0.5 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 6B | POOH
03/14/2021 | 00:30 | 19:45 | 19.25 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 8A | Repair Top Drive Leak
03/14/2021 | 19:45 | 21:30 | 1.75 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 6B | POOH
03/14/2021 | 21:30 | 22:05 | 0.58 | 10920 | 10920 | 0 | CRV | 4: BHA 4 | 6P | LD BHA
03/14/2021 | 22:05 | 23:30 | 1.42 | 10920 | 10920 | 0 | LAT | 5: BHA 5 | 6O | PU BHA 5
03/14/2021 | 23:30 | 23:45 | 0.25 | 10920 | 10920 | 0 | LAT | 5: BHA 5 | 5A | Test MWD
03/14/2021 | 23:45 | 24:00 | 0.25 | 10920 | 10920 | 0 | LAT | 5: BHA 5 | 6A | TIH
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_15_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/15/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9850 |  |  | Well Cost($): |  | 106230
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10920 |  | 10920 |  | Csg Shoe MD(Usft): |  | 10148 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 13140 |  | 13140 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  | 2220 |  | 2220 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 47
Slide Drilled (Usft): |  | 369 |  | 369 | [5 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 1851 |  | 1851 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 8.80
Drlg/Circ Hrs: |  | 15.43 / 0.00 |  | 15.43 / 0.25 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67.22
Slide Drilling Hrs: |  | 6.83 |  | 6.83 |  | SN: |  | 13401055 |  | 10s Gel: | 6 | Weight (ppg): | 9.8
Rotary Drilling Hrs: |  | 8.6 |  | 8.6 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 215.23 / 54.00 |  | 215.23 / 54.00 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 24.5 |  | Grade In: |  | New
% Slide: |  | 16.62 |  | 16.62 |  | Grade Out:
% Rotary: |  | 83.38 |  | 83.38 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Chris Day |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.76 |  | 0.76
6/7 8.8 2.00 Slick HS88 .006 |  |  |  | 5.5 | 2 |  |  |  |  | 33.2 |  | 33.96
YES |  |  |  | 4.86 | 2 |  |  |  |  | 2.36 |  | 36.32
NM Pony Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 11.51 |  | 47.83
UBHO |  |  |  | 5.23 | 2.5 |  |  |  |  | 3.97 |  | 51.8
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.98 |  | 82.78
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.38 |  | 113.16
Tomax Thruster |  |  |  | 5 | 2.25 |  |  |  |  | 17.95 |  | 131.11
XO- XT39Pin x DS42Box |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.24 |  | 134.35
2 Stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 190.36 |  | 324.71
Drill N Ream Reamer |  |  |  | 5.25 | 2.75 |  |  |  |  | 7.93 |  | 332.64
25 stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2378.29 |  | 2710.93
Agitator-Shock Sub-Safety Joint |  |  |  | 5.375 | 3 |  |  |  |  | 29.12 |  | 2740.05
2740.05
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10948 | 66.06 | 130.01 | 10526.39 | 859.28 | -581.38 | 7.16 |  | -50.25 | -1023.67 | 4.71 |  | -6.02 | 95
11042 | 74.19 | 135.3 | 10558.34 | 799.38 | -516.52 | 10.14 |  | 32.4 | -935.58 | 8.65 |  | 5.63 | 94
11136 | 83.67 | 140.77 | 10576.38 | 730.85 | -454.98 | 11.59 |  | 30.1 | -843.51 | 10.09 |  | 5.82 | 94
11230 | 86.14 | 137.11 | 10584.73 | 660.27 | -393.49 | 4.68 |  | -56.05 | -749.98 | 2.63 |  | -3.89 | 94
11324 | 86.22 | 135.17 | 10590.99 | 592.65 | -328.51 | 2.06 |  | -87.7 | -656.2 | 0.09 |  | -2.06 | 94
11419 | 85.59 | 135.57 | 10597.77 | 525.21 | -261.94 | 0.78 |  | 147.67 | -561.46 | -0.66 |  | 0.42 | 95
11514 | 87.86 | 135.1 | 10603.2 | 457.76 | -195.27 | 2.44 |  | -11.69 | -466.65 | 2.39 |  | -0.49 | 95
11609 | 88.95 | 135.23 | 10605.85 | 390.42 | -128.32 | 1.16 |  | 6.8 | -371.71 | 1.15 |  | 0.14 | 95
11704 | 87.62 | 136.42 | 10608.69 | 322.32 | -62.15 | 1.88 |  | 138.21 | -276.77 | -1.4 |  | 1.25 | 95
11798 | 87.08 | 136.55 | 10613.03 | 254.22 | 2.51 | 0.59 |  | 166.48 | -182.87 | -0.57 |  | 0.14 | 94
11893 | 87.17 | 137.21 | 10617.8 | 184.97 | 67.36 | 0.7 |  | 82.24 | -87.99 | 0.09 |  | 0.69 | 95
11987 | 86.84 | 137.31 | 10622.71 | 116.03 | 131.07 | 0.37 |  | 163.17 | 5.87 | -0.35 |  | 0.11 | 94
12083 | 89.03 | 136.92 | 10626.17 | 45.74 | 196.35 | 2.32 |  | -10.1 | 101.8 | 2.28 |  | -0.41 | 96
12180 | 90.24 | 136.82 | 10626.79 | -25.05 | 262.66 | 1.25 |  | -4.72 | 198.8 | 1.25 |  | -0.1 | 97
12276 | 89.06 | 136.93 | 10627.37 | -95.12 | 328.29 | 1.23 |  | 174.67 | 294.79 | -1.23 |  | 0.11 | 96
12373 | 87.83 | 136.06 | 10630.01 | -165.44 | 395.04 | 1.55 |  | -144.75 | 391.75 | -1.27 |  | -0.9 | 97
12470 | 89.04 | 136.42 | 10632.66 | -235.47 | 462.1 | 1.3 |  | 16.57 | 488.71 | 1.25 |  | 0.37 | 97
12565 | 87.19 | 137.23 | 10635.78 | -304.71 | 527.06 | 2.13 |  | 156.38 | 583.66 | -1.95 |  | 0.85 | 95
12662 | 86.03 | 136.96 | 10641.52 | -375.64 | 592.98 | 1.23 |  | -166.93 | 680.48 | -1.2 |  | -0.28 | 97
12757 | 84.32 | 136.79 | 10649.51 | -444.73 | 657.69 | 1.81 |  | -174.35 | 775.14 | -1.8 |  | -0.18 | 95
12852 | 81.93 | 136.45 | 10660.88 | -513.27 | 722.46 | 2.54 |  | -171.98 | 869.45 | -2.52 |  | -0.36 | 95
12946 | 81.8 | 136.52 | 10674.18 | -580.76 | 786.54 | 0.16 |  | 151.95 | 962.5 | -0.14 |  | 0.07 | 94
13041 | 82.89 | 136.77 | 10686.83 | -649.22 | 851.17 | 1.18 |  | 12.82 | 1056.65 | 1.15 |  | 0.26 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 143.84 | 42.36 | 71.43 | 343 | 400 | 4448 | 3600 | 0 | 292.8 | 215 | 177.2 | 13914.29 | 0
Run | 143.84 | 42.36 | 71.43 | 343 | 400 | 4448 | 3600 | 0 | 292.8 | 215 | 177.2 | 13914.29 | 0
Comments
Drilling Plan 2
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 03/15/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 03/15/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 03/15/2021 |  | 22 |  | 600 |  | 1 | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/15/2021 |  | 18 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9850
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/15/2021 | 00:00 | 04:50 | 4.83 | 10920 | 10920 | 0 | LAT | 5: BHA 5 | 6A | TIH
03/15/2021 | 04:50 | 05:05 | 0.25 | 10920 | 10940 | 20 | LAT | 5: BHA 5 | 2K | Rotary Drill f/10920.00 t/10940.00, w/WOB 35.00,Flow 400.00, RPM 30.00, Press 4400.00, Tq 13500.00, ROP 80.00
03/15/2021 | 05:05 | 05:46 | 0.68 | 10940 | 11000 | 60 | LAT | 5: BHA 5 | 2J | Slide Drill f/10940.00 t/11000.00, TF 0.00, w/WOB 35.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 87.80
03/15/2021 | 05:46 | 05:56 | 0.17 | 11000 | 11015 | 15 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11000.00 t/11015.00, w/WOB 35.00,Flow 400.00, RPM 30.00, Press 4400.00, Tq 13500.00, ROP 90.00
03/15/2021 | 05:56 | 06:06 | 0.17 | 11015 | 11015 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 06:06 | 06:10 | 0.07 | 11015 | 11025 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11015.00 t/11025.00, w/WOB 35.00,Flow 400.00, RPM 30.00, Press 4400.00, Tq 13500.00, ROP 150.00
03/15/2021 | 06:10 | 06:57 | 0.78 | 11025 | 11109 | 84 | LAT | 5: BHA 5 | 2J | Slide Drill f/11025.00 t/11109.00, TF 20.00, w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 107.23
03/15/2021 | 06:57 | 07:07 | 0.17 | 11109 | 11109 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 07:07 | 07:43 | 0.6 | 11109 | 11203 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11109.00 t/11203.00, w/WOB 35.00,Flow 400.00, RPM 30.00, Press 4400.00, Tq 13500.00, ROP 156.67
03/15/2021 | 07:43 | 07:53 | 0.17 | 11203 | 11203 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 07:53 | 08:20 | 0.45 | 11203 | 11243 | 40 | LAT | 5: BHA 5 | 2J | Slide Drill f/11203.00 t/11243.00, TF -60.00, w/WOB 50.00,Flow 400.00, Press 4000.00, Tq 0.00, ROP 88.89
03/15/2021 | 08:20 | 08:39 | 0.32 | 11243 | 11297 | 54 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11243.00 t/11297.00, w/WOB 35.00,Flow 400.00, RPM 30.00, Press 4400.00, Tq 13500.00, ROP 170.53
03/15/2021 | 08:39 | 08:49 | 0.17 | 11297 | 11297 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 08:49 | 09:15 | 0.43 | 11297 | 11391 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11297.00 t/11391.00, w/WOB 35.00,Flow 400.00, RPM 30.00, Press 4400.00, Tq 13500.00, ROP 216.92
03/15/2021 | 09:15 | 09:25 | 0.17 | 11391 | 11391 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 09:25 | 09:50 | 0.42 | 11391 | 11486 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11391.00 t/11486.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 228.00
03/15/2021 | 09:50 | 10:00 | 0.17 | 11486 | 11486 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 10:00 | 10:03 | 0.05 | 11486 | 11496 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11486.00 t/11496.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 200.00
03/15/2021 | 10:03 | 10:12 | 0.15 | 11496 | 11514 | 18 | LAT | 5: BHA 5 | 2J | Slide Drill f/11496.00 t/11514.00, TF 20.00, w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 120.00
03/15/2021 | 10:12 | 10:34 | 0.37 | 11514 | 11581 | 67 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11514.00 t/11581.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 182.73
03/15/2021 | 10:34 | 10:44 | 0.17 | 11581 | 11581 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 10:44 | 11:02 | 0.3 | 11581 | 11676 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11581.00 t/11676.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 316.67
03/15/2021 | 11:02 | 11:12 | 0.17 | 11676 | 11676 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 11:12 | 11:14 | 0.03 | 11676 | 11686 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11676.00 t/11686.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 300.00
03/15/2021 | 11:14 | 11:26 | 0.2 | 11686 | 11698 | 12 | LAT | 5: BHA 5 | 2J | Slide Drill f/11686.00 t/11698.00, TF 180.00, w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 60.00
03/15/2021 | 11:26 | 11:48 | 0.37 | 11698 | 11771 | 73 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11698.00 t/11771.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 199.09
03/15/2021 | 11:48 | 11:58 | 0.17 | 11771 | 11771 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 11:58 | 12:15 | 0.28 | 11771 | 11865 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11771.00 t/11865.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4400.00, Tq 14000.00, ROP 331.76
03/15/2021 | 12:15 | 12:25 | 0.17 | 11865 | 11865 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 12:25 | 12:38 | 0.22 | 11865 | 11960 | 95 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11865.00 t/11960.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650, Tq 14000.00, ROP 438.46
03/15/2021 | 12:38 | 12:48 | 0.17 | 11960 | 11960 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 12:48 | 13:07 | 0.32 | 11960 | 12054 | 94 | LAT | 5: BHA 5 | 2K | Rotary Drill f/11960.00 t/12054.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650, Tq 14000.00, ROP 296.84
03/15/2021 | 13:07 | 13:17 | 0.17 | 12054 | 12054 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 13:17 | 13:19 | 0.03 | 12054 | 12064 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12054.00 t/12064.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650, Tq 14000.00, ROP 300.00
03/15/2021 | 13:19 | 13:37 | 0.3 | 12064 | 12079 | 15 | LAT | 5: BHA 5 | 2J | Slide Drill f/12064.00 t/12079.00, TF , w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 50.00
03/15/2021 | 13:37 | 13:56 | 0.32 | 12079 | 12150 | 71 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12079.00 t/12150.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650, Tq 14000.00, ROP 224.21
03/15/2021 | 13:56 | 14:06 | 0.17 | 12150 | 12150 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 14:06 | 14:21 | 0.25 | 12150 | 12247 | 97 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12150.00 t/12247.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650, Tq 14000.00, ROP 388.00
03/15/2021 | 14:21 | 14:31 | 0.17 | 12247 | 12247 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 14:31 | 14:33 | 0.03 | 12247 | 12257 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12247.00 t/12257.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650, Tq 14000.00, ROP 300.00
03/15/2021 | 14:33 | 14:48 | 0.25 | 12257 | 12270 | 13 | LAT | 5: BHA 5 | 2J | Slide Drill f/12257.00 t/12270.00, TF , w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 52.00
03/15/2021 | 14:48 | 15:08 | 0.33 | 12270 | 12343 | 73 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12270.00 t/12343.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 219.00
03/15/2021 | 15:08 | 15:18 | 0.17 | 12343 | 12343 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 15:18 | 15:23 | 0.08 | 12343 | 12353 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12343.00 t/12353.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 120.00
03/15/2021 | 15:23 | 15:30 | 0.12 | 12353 | 12360 | 7 | LAT | 5: BHA 5 | 2J | Slide Drill f/12353.00 t/12360.00, TF 180.00, w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 60.00
03/15/2021 | 15:30 | 15:50 | 0.33 | 12360 | 12440 | 80 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12360.00 t/12440.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 240.00
03/15/2021 | 15:50 | 16:00 | 0.17 | 12440 | 12440 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 16:00 | 16:16 | 0.27 | 12440 | 12537 | 97 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12440.00 t/12537.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 363.75
03/15/2021 | 16:16 | 16:26 | 0.17 | 12537 | 12537 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 16:26 | 16:30 | 0.07 | 12537 | 12547 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12537.00 t/12547.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 150.00
03/15/2021 | 16:30 | 16:54 | 0.4 | 12547 | 12562 | 15 | LAT | 5: BHA 5 | 2J | Slide Drill f/12547.00 t/12562.00, TF 180.00, w/WOB 50.00,Flow 400.00, Press 4400.00, Tq 0.00, ROP 37.50
03/15/2021 | 16:54 | 17:14 | 0.33 | 12562 | 12632 | 70 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12562.00 t/12632.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 210.00
03/15/2021 | 17:14 | 17:50 | 0.6 | 12632 | 12632 | 0 | LAT | 5: BHA 5 | 8P | Rig Service
03/15/2021 | 17:50 | 17:53 | 0.05 | 12632 | 12632 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 17:53 | 18:00 | 0.12 | 12632 | 12642 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12632.00 t/12642.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 85.71
03/15/2021 | 18:00 | 18:26 | 0.43 | 12642 | 12652 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/12642.00 t/12652.00, TF , w/WOB 43.00,Flow 400.00, Press 3950, Tq 9500, ROP 23.08
03/15/2021 | 18:26 | 18:47 | 0.35 | 12652 | 12729 | 77 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12652.00 t/12729.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 220.00
03/15/2021 | 18:47 | 18:50 | 0.05 | 12729 | 12729 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 18:50 | 18:54 | 0.07 | 12729 | 12729 | 0 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12729.00 t/12729.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 0.00
03/15/2021 | 18:54 | 19:00 | 0.1 | 12729 | 12750 | 21 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12729.00 t/12750.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 210.00
03/15/2021 | 19:00 | 19:16 | 0.27 | 12750 | 12760 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/12750.00 t/12760.00, TF , w/WOB 43.00,Flow 400.00, Press 3950, Tq 9500, ROP 37.50
03/15/2021 | 19:16 | 19:33 | 0.28 | 12760 | 12824 | 64 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12760.00 t/12824.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 225.88
03/15/2021 | 19:33 | 19:35 | 0.03 | 12824 | 12824 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 19:35 | 20:10 | 0.58 | 12824 | 12920 | 96 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12824.00 t/12920.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 164.57
03/15/2021 | 20:10 | 20:12 | 0.03 | 12920 | 12920 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 20:12 | 20:39 | 0.45 | 12920 | 12940 | 20 | LAT | 5: BHA 5 | 2J | Slide Drill f/12920.00 t/12940.00, TF , w/WOB 35,Flow 400.00, Press 3950, Tq 9500, ROP 44.44
03/15/2021 | 20:39 | 21:00 | 0.35 | 12940 | 13010 | 70 | LAT | 5: BHA 5 | 2K | Rotary Drill f/12940.00 t/13010.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 200.00
03/15/2021 | 21:00 | 21:03 | 0.05 | 13010 | 13010 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 21:03 | 21:11 | 0.13 | 13010 | 13015 | 5 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13010.00 t/13015.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 37.50
03/15/2021 | 21:11 | 22:18 | 1.12 | 13015 | 13045 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/13015.00 t/13045.00, TF , w/WOB 35,Flow 400.00, Press 3950, Tq 9500, ROP 26.87
03/15/2021 | 22:18 | 22:35 | 0.28 | 13045 | 13085 | 40 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13045.00 t/13085.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 141.18
03/15/2021 | 22:35 | 23:20 | 0.75 | 13085 | 13105 | 20 | LAT | 5: BHA 5 | 2J | Slide Drill f/13085.00 t/13105.00, TF , w/WOB 35,Flow 400.00, Press 3950, Tq 9500, ROP 26.67
03/15/2021 | 23:20 | 23:25 | 0.08 | 13105 | 13105 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/15/2021 | 23:25 | 23:54 | 0.48 | 13105 | 13120 | 15 | LAT | 5: BHA 5 | 2J | Slide Drill f/13105.00 t/13120.00, TF , w/WOB 35,Flow 400.00, Press 3950, Tq 9500, ROP 31.03
03/15/2021 | 23:54 | 24:00 | 0.1 | 13120 | 13140 | 20 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13120.00 t/13140.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 200.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_16_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/16/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9250 |  |  | Well Cost($): |  | 115480
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 13140 |  | 10920 |  | Csg Shoe MD(Usft): |  | 10148 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 14562 |  | 14562 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  | 1422 |  | 3642 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 47
Slide Drilled (Usft): |  | 270 |  | 639 | [5 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 1152 |  | 3003 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 8.80
Drlg/Circ Hrs: |  | 20.58 / 0.00 |  | 36.02 / 0.25 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67.22
Slide Drilling Hrs: |  | 13.38 |  | 20.22 |  | SN: |  | 13401055 |  | 10s Gel: | 6 | Weight (ppg): | 9.8
Rotary Drilling Hrs: |  | 7.2 |  | 15.8 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 160.00 / 20.17 |  | 190.06 / 31.61 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 48.5 |  | Grade In: |  | New
% Slide: |  | 18.99 |  | 17.55 |  | Grade Out:
% Rotary: |  | 81.01 |  | 82.45 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Chris Day Jesse Taylor |  | Jeff Campbell
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.76 |  | 0.76
6/7 8.8 2.00 Slick HS88 .006 |  |  |  | 5.5 | 2 |  |  |  |  | 33.2 |  | 33.96
YES |  |  |  | 4.86 | 2 |  |  |  |  | 2.36 |  | 36.32
NM Pony Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 11.51 |  | 47.83
UBHO |  |  |  | 5.23 | 2.5 |  |  |  |  | 3.97 |  | 51.8
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.98 |  | 82.78
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.38 |  | 113.16
Tomax Thruster |  |  |  | 5 | 2.25 |  |  |  |  | 17.95 |  | 131.11
XO- XT39Pin x DS42Box |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.24 |  | 134.35
2 Stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 190.36 |  | 324.71
Drill N Ream Reamer |  |  |  | 5.25 | 2.75 |  |  |  |  | 7.93 |  | 332.64
25 stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2378.29 |  | 2710.93
Agitator-Shock Sub-Safety Joint |  |  |  | 5.375 | 3 |  |  |  |  | 29.12 |  | 2740.05
2740.05
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13136 | 87.9 | 137.29 | 10694.46 | -718.48 | 915.7 | 5.3 |  | 5.93 | 1151.31 | 5.27 |  | 0.55 | 95
13232 | 92.34 | 135.99 | 10694.26 | -788.26 | 981.59 | 4.82 |  | -16.32 | 1247.29 | 4.63 |  | -1.35 | 96
13327 | 96.11 | 135.46 | 10687.26 | -856.08 | 1047.72 | 4.01 |  | -7.96 | 1342 | 3.97 |  | -0.56 | 95
13423 | 92.78 | 135.17 | 10679.82 | -924.12 | 1115.01 | 3.48 |  | -175.03 | 1437.68 | -3.47 |  | -0.3 | 96
13517 | 88.19 | 136.38 | 10679.03 | -991.46 | 1180.55 | 5.05 |  | 165.22 | 1531.64 | -4.88 |  | 1.29 | 94
13611 | 89.77 | 136.17 | 10680.7 | -1059.38 | 1245.51 | 1.7 |  | -7.57 | 1625.62 | 1.68 |  | -0.22 | 94
13706 | 88.05 | 135.52 | 10682.51 | -1127.52 | 1311.68 | 1.94 |  | -159.31 | 1720.59 | -1.81 |  | -0.68 | 95
13802 | 88.63 | 136.66 | 10685.29 | -1196.65 | 1378.22 | 1.33 |  | 63.04 | 1816.54 | 0.6 |  | 1.19 | 96
13900 | 86.84 | 137.31 | 10689.16 | -1268.25 | 1445.02 | 1.94 |  | 160.07 | 1914.46 | -1.83 |  | 0.66 | 98
13996 | 87.06 | 137.26 | 10694.27 | -1338.69 | 1510.05 | 0.23 |  | -12.79 | 2010.32 | 0.23 |  | -0.05 | 96
14092 | 83.77 | 136.79 | 10701.94 | -1408.69 | 1575.28 | 3.46 |  | -171.91 | 2105.99 | -3.43 |  | -0.49 | 96
14187 | 83.16 | 136.38 | 10712.75 | -1477.25 | 1640.14 | 0.77 |  | -146.29 | 2200.38 | -0.64 |  | -0.43 | 95
14282 | 83.78 | 136.06 | 10723.56 | -1545.39 | 1705.45 | 0.73 |  | -27.17 | 2294.76 | 0.65 |  | -0.34 | 95
14379 | 83.56 | 136.09 | 10734.25 | -1614.83 | 1772.33 | 0.23 |  | 172.28 | 2391.16 | -0.23 |  | 0.03 | 97
14474 | 83.08 | 136.58 | 10745.3 | -1683.09 | 1837.47 | 0.72 |  | 134.63 | 2485.52 | -0.51 |  | 0.52 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 69.09 | 42.36 | 71.43 | 343 | 400 | 4448 | 3600 | 0 | 292.8 | 215 | 177.2 | 13914.29 | 0
Run | 101.12 | 42.36 | 71.43 | 343 | 400 | 4448 | 3600 | 0 | 292.8 | 215 | 177.2 | 13914.29 | 0
Comments
Drilling Plan 2
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 03/16/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 03/16/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 03/16/2021 |  | 22 |  | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/16/2021 |  | 18 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/16/2021 | 00:00 | 00:09 | 0.15 | 13140 | 13155 | 15 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13140.00 t/13155.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 100.00
03/16/2021 | 00:09 | 00:42 | 0.55 | 13155 | 13168 | 13 | LAT | 5: BHA 5 | 2J | Slide Drill f/13155.00 t/13168.00, TF , w/WOB 35,Flow 400.00, Press 3950, Tq 9500, ROP 23.64
03/16/2021 | 00:42 | 01:06 | 0.4 | 13168 | 13203 | 35 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13168.00 t/13203.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 87.50
03/16/2021 | 01:06 | 01:08 | 0.03 | 13203 | 13203 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 01:08 | 01:11 | 0.05 | 13203 | 13210 | 7 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13203.00 t/13210.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 140.00
03/16/2021 | 01:11 | 01:58 | 0.78 | 13210 | 13230 | 20 | LAT | 5: BHA 5 | 2J | Slide Drill f/13210.00 t/13230.00, TF , w/WOB 43.00,Flow 400.00, Press 4650.00, Tq 14000.00, ROP 25.53
03/16/2021 | 01:58 | 02:31 | 0.55 | 13230 | 13299 | 69 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13230.00 t/13299.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 125.45
03/16/2021 | 02:31 | 02:33 | 0.03 | 13299 | 13299 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 02:33 | 02:46 | 0.22 | 13299 | 13333 | 34 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13299.00 t/13333.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 156.92
03/16/2021 | 02:46 | 03:34 | 0.8 | 13333 | 13345 | 12 | LAT | 5: BHA 5 | 2J | Slide Drill f/13333.00 t/13345.00, TF , w/WOB 35,Flow 400.00, Press 3950, Tq 9500, ROP 15.00
03/16/2021 | 03:34 | 04:08 | 0.57 | 13345 | 13394 | 49 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13345.00 t/13394.00, w/WOB 43.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 14000.00, ROP 86.47
03/16/2021 | 04:08 | 04:10 | 0.03 | 13394 | 13394 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 04:10 | 06:32 | 2.37 | 13394 | 13424 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/13394.00 t/13424.00, TF 180.00, w/WOB 43.00,Flow 400.00, Press 4650.00, Tq 14000.00, ROP 12.68
03/16/2021 | 06:32 | 06:44 | 0.2 | 13424 | 13457 | 33 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13424.00 t/13457.00, w/WOB 35,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500, ROP 165.00
03/16/2021 | 06:44 | 06:50 | 0.1 | 13457 | 13457 | 0 | LAT | 5: BHA 5 | 1G | Check Shot
03/16/2021 | 06:50 | 07:34 | 0.73 | 13457 | 13472 | 15 | LAT | 5: BHA 5 | 2J | Slide Drill f/13457.00 t/13472.00, TF , w/WOB 43.00,Flow 400, Press 3800, Tq 0, ROP 20.45
03/16/2021 | 07:34 | 07:43 | 0.15 | 13472 | 13490 | 18 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13472.00 t/13490.00, w/WOB 35,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500, ROP 120.00
03/16/2021 | 07:43 | 07:53 | 0.17 | 13490 | 13490 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 07:53 | 07:58 | 0.08 | 13490 | 13500 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13490.00 t/13500.00, w/WOB 35,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500, ROP 120.00
03/16/2021 | 07:58 | 08:40 | 0.7 | 13500 | 13520 | 20 | LAT | 5: BHA 5 | 2J | Slide Drill f/13500.00 t/13520.00, TF , w/WOB 43.00,Flow 400, Press 3800, Tq 0, ROP 28.57
03/16/2021 | 08:40 | 08:48 | 0.13 | 13520 | 13520 | 0 | LAT | 5: BHA 5 | 1G | Check Shot
03/16/2021 | 08:48 | 09:00 | 0.2 | 13520 | 13534 | 14 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13520.00 t/13534.00, w/WOB 35,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500, ROP 70.00
03/16/2021 | 09:00 | 09:08 | 0.13 | 13534 | 13534 | 0 | LAT | 5: BHA 5 | 1G | Check Shot
03/16/2021 | 09:08 | 09:16 | 0.13 | 13534 | 13584 | 50 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13534.00 t/13584.00, w/WOB 35,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500, ROP 375.00
03/16/2021 | 09:16 | 09:23 | 0.12 | 13584 | 13584 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 09:23 | 09:34 | 0.18 | 13584 | 13617 | 33 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13584.00 t/13617.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 180.00
03/16/2021 | 09:34 | 09:42 | 0.13 | 13617 | 13617 | 0 | LAT | 5: BHA 5 | 1G | Check Shot
03/16/2021 | 09:42 | 09:48 | 0.1 | 13617 | 13649 | 32 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13617.00 t/13649.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 320.00
03/16/2021 | 09:48 | 09:53 | 0.08 | 13649 | 13649 | 0 | LAT | 5: BHA 5 | 1G | Check Shot
03/16/2021 | 09:53 | 10:02 | 0.15 | 13649 | 13678 | 29 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13649.00 t/13678.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 193.33
03/16/2021 | 10:02 | 10:12 | 0.17 | 13678 | 13678 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 10:12 | 11:29 | 1.28 | 13678 | 13708 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/13678.00 t/13708.00, TF 180.00, w/WOB 43.00,Flow 400.00, Press 3800.00, Tq 0.00, ROP 23.38
03/16/2021 | 11:29 | 11:51 | 0.37 | 13708 | 13773 | 65 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13708.00 t/13773.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 177.27
03/16/2021 | 11:51 | 12:00 | 0.15 | 13773 | 13773 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 12:00 | 12:05 | 0.08 | 13773 | 13783 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13773.00 t/13783.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 120.00
03/16/2021 | 12:05 | 13:07 | 1.03 | 13783 | 13798 | 15 | LAT | 5: BHA 5 | 2J | Slide Drill f/13783.00 t/13798.00, TF , w/WOB 43,Flow 400.00, Press 3800, Tq 0, ROP 14.52
03/16/2021 | 13:07 | 13:32 | 0.42 | 13798 | 13869 | 71 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13798.00 t/13869.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 170.40
03/16/2021 | 13:32 | 13:42 | 0.17 | 13869 | 13869 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 13:42 | 15:00 | 1.3 | 13869 | 13890 | 21 | LAT | 5: BHA 5 | 2J | Slide Drill f/13869.00 t/13890.00, TF , w/WOB 43,Flow 400.00, Press 3800, Tq 0, ROP 16.15
03/16/2021 | 15:00 | 15:16 | 0.27 | 13890 | 13890 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 15:16 | 16:16 | 1 | 13890 | 13915 | 25 | LAT | 5: BHA 5 | 2J | Slide Drill f/13890.00 t/13915.00, TF , w/WOB 43,Flow 400.00, Press 3800, Tq 0, ROP 25.00
03/16/2021 | 16:16 | 16:26 | 0.17 | 13915 | 13934 | 19 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13915.00 t/13934.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 114.00
03/16/2021 | 16:26 | 16:34 | 0.13 | 13934 | 13934 | 0 | LAT | 5: BHA 5 | 1G | Check Shot
03/16/2021 | 16:34 | 16:49 | 0.25 | 13934 | 13967 | 33 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13934.00 t/13967.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 132.00
03/16/2021 | 16:49 | 16:59 | 0.17 | 13967 | 13967 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 16:59 | 17:08 | 0.15 | 13967 | 13999 | 32 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13967.00 t/13999.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 213.33
03/16/2021 | 17:08 | 17:12 | 0.07 | 13999 | 13999 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 17:12 | 17:30 | 0.3 | 13999 | 14063 | 64 | LAT | 5: BHA 5 | 2K | Rotary Drill f/13999.00 t/14063.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 213.33
03/16/2021 | 17:30 | 17:35 | 0.08 | 14063 | 14063 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 17:35 | 18:35 | 1 | 14063 | 14093 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/14063.00 t/14093.00, TF 180.00, w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 30.00
03/16/2021 | 18:35 | 19:00 | 0.42 | 14093 | 14159 | 66 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14093.00 t/14159.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 158.40
03/16/2021 | 19:00 | 19:45 | 0.75 | 14159 | 14159 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 19:45 | 19:55 | 0.17 | 14159 | 14191 | 32 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14159.00 t/14191.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 192.00
03/16/2021 | 19:55 | 20:00 | 0.08 | 14191 | 14191 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 20:00 | 20:15 | 0.25 | 14191 | 14254 | 63 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14191.00 t/14254.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 252.00
03/16/2021 | 20:15 | 20:20 | 0.08 | 14254 | 14254 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 20:20 | 20:25 | 0.08 | 14254 | 14260 | 6 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14254.00 t/14260.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 72.00
03/16/2021 | 20:25 | 20:55 | 0.5 | 14260 | 14270 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/14260.00 t/14270.00, TF 0.00, w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 20.00
03/16/2021 | 20:55 | 21:20 | 0.42 | 14270 | 14349 | 79 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14270.00 t/14349.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 189.60
03/16/2021 | 21:20 | 21:25 | 0.08 | 14349 | 14349 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 21:25 | 21:55 | 0.5 | 14349 | 14446 | 97 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14349.00 t/14446.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 194.00
03/16/2021 | 21:55 | 22:00 | 0.08 | 14446 | 14446 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 22:00 | 22:30 | 0.5 | 14446 | 14533 | 87 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14446.00 t/14533.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 174.00
03/16/2021 | 22:30 | 23:00 | 0.5 | 14533 | 14541 | 8 | LAT | 5: BHA 5 | 2J | Slide Drill f/14533.00 t/14541.00, TF 0.00, w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 16.00
03/16/2021 | 23:00 | 23:10 | 0.17 | 14541 | 14541 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/16/2021 | 23:10 | 24:00 | 0.83 | 14541 | 14562 | 21 | LAT | 5: BHA 5 | 2J | Slide Drill f/14541.00 t/14562.00, TF 0.00, w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 25.20
Well Seeker PRO 2.0.8.0 - Pro Directional

## 3_17_2021_DDR
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31146 / 20DD0331MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Sabine D 4H
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Longitude: |  | 96° 45' 45.405" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 03/17/2021 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9250 |  |  | Well Cost($): |  | 124730
|  |  |  | 24hr Summary: |  | Drill lateral section, Prepare to ST
|  |  |  | 24hr Lookahead: |  | SideTrack and cont Drilling ahead
Drilling Summary |  | 24Hr (BHA 5) |  | Run (BHA 5) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 14562 |  | 10920 |  | Csg Shoe MD(Usft): |  | 10148 |  | 600: | 34 | PV: | 12
End Depth (Usft): |  | 15209 |  | 15209 |  | OD (in): |  | 7.625 |  | 300: | 22 | YP: | 10
Total Drilled (Usft): |  | 647 |  | 4289 |  | Weight (ft/lbs): |  | 29.7 |  | 200: | 16 | Viscosity: | 47
Slide Drilled (Usft): |  | 140 |  | 779 | [5 empty] | 100: | 12 | Chlorides: | 54000
Rotary Drilled (Usft): |  | 507 |  | 3510 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.00 / 8.80
Drlg/Circ Hrs: |  | 11.05 / 5.62 |  | 47.07 / 5.87 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 67.22
Slide Drilling Hrs: |  | 7.52 |  | 27.73 |  | SN: |  | 13401055 |  | 10s Gel: | 6 | Weight (ppg): | 9.8
Rotary Drilling Hrs: |  | 3.53 |  | 19.33 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 125.00 | Fluid Loss / Mud Type: | 9 / OBM
ROP Rot/Slide (Usft/hr): |  | 143.49 / 18.63 |  | 181.55 / 28.09 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 21.33 |  | 69.83 |  | Grade In: |  | New
% Slide: |  | 21.64 |  | 18.16 |  | Grade Out:
% Rotary: |  | 78.36 |  | 81.84 |  | Make / Model: |  | Security / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc
James Dyer |  | Jesse Taylor |  | Ramon Reis
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
|  |  |  | NA |  | NA |  | NA |  | NA
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
GTD64M - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.76 |  | 0.76
6/7 8.8 2.00 Slick HS88 .006 |  |  |  | 5.5 | 2 |  |  |  |  | 33.2 |  | 33.96
YES |  |  |  | 4.86 | 2 |  |  |  |  | 2.36 |  | 36.32
NM Pony Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 11.51 |  | 47.83
UBHO |  |  |  | 5.23 | 2.5 |  |  |  |  | 3.97 |  | 51.8
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.98 |  | 82.78
NM Drill Collar |  |  |  | 5 | 2.75 |  |  |  |  | 30.38 |  | 113.16
Tomax Thruster |  |  |  | 5 | 2.25 |  |  |  |  | 17.95 |  | 131.11
XO- XT39Pin x DS42Box |  |  |  | 5.5 | 2.75 |  |  |  |  | 3.24 |  | 134.35
2 Stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 190.36 |  | 324.71
Drill N Ream Reamer |  |  |  | 5.25 | 2.75 |  |  |  |  | 7.93 |  | 332.64
25 stands of Drill Pipe |  |  |  | 4.5 | 2.5 |  |  |  |  | 2378.29 |  | 2710.93
Agitator-Shock Sub-Safety Joint |  |  |  | 5.375 | 3 |  |  |  |  | 29.12 |  | 2740.05
2740.05
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250024 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.1 |  | 2 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
14568 | 88.69 | 135.85 | 10752.04 | -1750.74 | 1902.32 | 6.02 |  | -7.42 | 2579.23 | 5.97 |  | -0.78 | 94
14663 | 92.92 | 135.92 | 10750.71 | -1818.93 | 1968.43 | 4.45 |  | 0.95 | 2674.2 | 4.45 |  | 0.07 | 95
14758 | 92.44 | 135.66 | 10746.27 | -1886.95 | 2034.6 | 0.57 |  | -151.58 | 2769.08 | -0.51 |  | -0.27 | 95
14852 | 91.43 | 134.3 | 10743.09 | -1953.35 | 2101.05 | 1.8 |  | -126.59 | 2862.99 | -1.07 |  | -1.45 | 94
14947 | 88.87 | 133.89 | 10742.85 | -2019.45 | 2169.27 | 2.73 |  | -170.9 | 2957.89 | -2.69 |  | -0.43 | 95
15041 | 87.08 | 136.54 | 10746.17 | -2086.12 | 2235.44 | 3.4 |  | 124.1 | 3051.8 | -1.9 |  | 2.82 | 94
15136 | 86.26 | 136.43 | 10751.69 | -2154.89 | 2300.74 | 0.87 |  | -172.38 | 3146.64 | -0.86 |  | -0.12 | 95
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 58.55 | 42.36 | 71.43 | 343 | 400 | 4448 | 3600 | 0 | 292.8 | 215 | 177.2 | 13914.29 | 0
Run | 91.13 | 42.36 | 71.43 | 343 | 400 | 4448 | 3600 | 0 | 292.8 | 215 | 177.2 | 13914.29 | 0
Comments
Current Target= 10499 0 V/S @ 85.21?- 0 Up 10 Down
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 03/17/2021 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 03/17/2021 |  | 6 |  | 100 |  | 4 | 400
Real Time Survey Management |  |  |  |  | 03/17/2021 |  | 22 |  | 600
Pro Azimuthal Gamma Ray |  |  |  |  | 03/17/2021 |  | 18 |  | 2000 |  | 1 | 2000
Total | [11 empty] | 9250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
03/17/2021 | 00:00 | 00:25 | 0.42 | 14562 | 14576 | 14 | LAT | 5: BHA 5 | 2J | Slide Drill f/14562.00 t/14576.00, TF 0.00, w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 33.60
03/17/2021 | 00:25 | 00:50 | 0.42 | 14576 | 14635 | 59 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14576.00 t/14635.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 141.60
03/17/2021 | 00:50 | 00:55 | 0.08 | 14635 | 14635 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 00:55 | 01:00 | 0.08 | 14635 | 14645 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14635.00 t/14645.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 120.00
03/17/2021 | 01:00 | 01:05 | 0.08 | 14645 | 14645 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 01:05 | 01:40 | 0.58 | 14645 | 14730 | 85 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14645.00 t/14730.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 145.71
03/17/2021 | 01:40 | 01:45 | 0.08 | 14730 | 14730 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 01:45 | 02:40 | 0.92 | 14730 | 14755 | 25 | LAT | 5: BHA 5 | 2J | Slide Drill f/14730.00 t/14755.00, TF 180.00, w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 27.27
03/17/2021 | 02:40 | 03:10 | 0.5 | 14755 | 14825 | 70 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14755.00 t/14825.00, w/WOB 35,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 140.00
03/17/2021 | 03:10 | 04:10 | 1 | 14825 | 14850 | 25 | LAT | 5: BHA 5 | 2J | Slide Drill f/14825.00 t/14850.00, TF , w/WOB 40.00,Flow 400.00, Press 4650.00, Tq 16500.00, ROP 25.00
03/17/2021 | 04:10 | 04:40 | 0.5 | 14850 | 14919 | 69 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14850.00 t/14919.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 4650.00, Tq 16500.00, ROP 138.00
03/17/2021 | 04:40 | 04:45 | 0.08 | 14919 | 14919 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 04:45 | 06:05 | 1.33 | 14919 | 14949 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/14919.00 t/14949.00, TF 180.00, w/WOB 43.00,Flow 400.00, Press 3800.00, Tq 0.00, ROP 22.50
03/17/2021 | 06:05 | 06:27 | 0.37 | 14949 | 15014 | 65 | LAT | 5: BHA 5 | 2K | Rotary Drill f/14949.00 t/15014.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 3800.00, Tq 21000.00, ROP 177.27
03/17/2021 | 06:27 | 06:37 | 0.17 | 15014 | 15014 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 06:37 | 06:40 | 0.05 | 15014 | 15024 | 10 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15014.00 t/15024.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 3800.00, Tq 21000.00, ROP 200.00
03/17/2021 | 06:40 | 06:52 | 0.2 | 15024 | 15024 | 0 | LAT | 5: BHA 5 | 5A | Circulate; put in target change
03/17/2021 | 06:52 | 07:59 | 1.12 | 15024 | 15054 | 30 | LAT | 5: BHA 5 | 2J | Slide Drill f/15024.00 t/15054.00, TF 140.00, w/WOB 43.00,Flow 400.00, Press 3800.00, Tq 0.00, ROP 26.87
03/17/2021 | 07:59 | 08:27 | 0.47 | 15054 | 15108 | 54 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15054.00 t/15108.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 3800.00, Tq 21000.00, ROP 115.71
03/17/2021 | 08:27 | 08:37 | 0.17 | 15108 | 15108 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 08:37 | 09:51 | 1.23 | 15108 | 15118 | 10 | LAT | 5: BHA 5 | 2J | Slide Drill f/15108.00 t/15118.00, TF 180.00, w/WOB 43.00,Flow 400.00, Press 3800.00, Tq 0.00, ROP 8.11
03/17/2021 | 09:51 | 10:25 | 0.57 | 15118 | 15203 | 85 | LAT | 5: BHA 5 | 2K | Rotary Drill f/15118.00 t/15203.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 3800.00, Tq 21000.00, ROP 150.00
03/17/2021 | 10:25 | 10:35 | 0.17 | 15203 | 15203 | 0 | LAT | 5: BHA 5 | 10D | Survey & Connection
03/17/2021 | 10:35 | 12:05 | 1.5 | 15203 | 15209 | 6 | LAT | 5: BHA 5 | 2J | Slide Drill f/15203.00 t/15209.00, TF 180.00, w/WOB 43.00,Flow 400.00, Press 3800.00, Tq 0.00, ROP 4.00
03/17/2021 | 12:05 | 15:30 | 3.42 | 15209 | 15209 | 0 | LAT | 5: BHA 5 | 3D | Back ream out 10 Stands, and ream back to 14538
03/17/2021 | 15:30 | 17:30 | 2 | 15209 | 15209 | 0 | LAT | 5: BHA 5 | 5A | Attempt to Trough SideTrack
03/17/2021 | 17:30 | 21:20 | 3.83 | 15209 | 15209 | 0 | LAT | 5: BHA 5 | 6P | 10 Std Wiper Trip
03/17/2021 | 21:20 | 24:00 | 2.67 | 15209 | 15209 | 0 | LAT |  | 24B
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 395.52 (Usft)
Well: |  |  | Sabine D 4H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1100921 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 01/16/2021 | Depth In: |  | 105 | Total Drilled: |  | 2811.00 (Usft)
Date Out: |  |  | 01/16/2021 | Depth Out: |  | 2916 | Drilling / Circ Hours: |  | 4.88 / 0.93
Survey Offset: |  |  | 76
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 37295 | 13 1/2" Ulterra- U616S- Jetted 6x16s | 13.5 | 2 |  | 6 5/8 REG |  | 1.5 | 1.5
| 2 | PPM800001 | 7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) | 8 | 2 | 8.000 / 1.98 | 6 5/8 REG / 6 5/8 REG |  | 37.68 | 39.18
| 3 | SD610467 | 13" - 4 Blade Nortrak Stabilizer (BFF) | 8 | 2.813 | 8.000 / 3.16 | 6 5/8 REG / 6 5/8 REG |  | 7.23 | 46.41
| 4 | SD45067 | 8" - NMPDC | 7.938 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 10.67 | 57.08
| 5 | 775210 | 7 3/4" UBHO | 7.75 | 2.75 | 7.750 / 2.04 | 6 5/8 REG / 6 5/8 REG |  | 3.84 | 60.92
| 6 | SD55685 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.58 | 89.5
| 7 | SD55520 | 8" - NMDC | 7.938 | 3.125 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 118.41
| 8 | SD114192 | X/O- 4 1/2 IFB x 6 5/8 RegP | 8 | 3 |  | 4 1/2 IF / 6 5/8 REG |  | 3.12 | 121.53
| 9 | Rig | 9 joints of 5" HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 273.99 | 395.52
Comments
Bit Info= 13 1/2" -Ulterra-U616S SN= 37295 Jets= 6x16's TFA= 1.178 Motor Info= 8", 7/8, 5.9 Stg. @ 1.5? w/ 13"NBS Bit To Bend= 6.01' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  | PDC | 13 1/2" Ulterra- U616S- Jetted 6x16s | 1.18 | Ulterra | U616S | New |  | 2811
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) |  |  | PDCI / 7/8 5.9 | 6.01 / 1.50 |  | 13 | 8.38 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 100 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]
2 |  |  | 7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) | 13 |  | 0 |  |  | 1.5
3 |  |  | 13" - 4 Blade Nortrak Stabilizer (BFF) | 13 |  | 0 |  |  | 40.68

## BHA_2
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2671.84 (Usft)
Well: |  |  | Sabine D 4H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1100921 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 01/18/2021 | Depth In: |  | 2916 | Total Drilled: |  | 6988.00 (Usft)
Date Out: |  |  | 01/20/2021 | Depth Out: |  | 9904 | Drilling / Circ Hours: |  | 29.17 / 2.00
Survey Offset: |  |  | 71 | Gamma Offset: |  | 61
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 54300 | 9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s | 9.875 | 2 |  | 6 5/8 REG |  | 1.2 | 1.2
| 2 | PPM800012 | 7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 | 8 | 2 | 1.69 | 6 5/8 REG / 6 5/8 REG |  | 37.56 | 38.76
| 3 | SD45067 | 8" - NMPDC | 7.938 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 10.67 | 49.43
| 4 | 775210 | 7 3/4" UBHO | 7.75 | 2.75 |  | 6 5/8 REG / 6 5/8 REG |  | 3.84 | 53.27
| 5 | SD55685 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.58 | 81.85
| 6 | SD55520 | 8" - NMDC | 7.938 | 3.125 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 110.76
| 7 | SD107481 | X/O- 4 1/2 XHB x 6 5/8 RegP | 6.5 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.28 | 113.04
| 8 | Rig 1 | 6 Joints of 6.5" Drill Collars | 6.5 | 2.875 |  | 4 1/2 XH / 4 1/2 XH |  | 188.21 | 301.25
| 9 | SD107702 | X/O- 4 1/2 IFB x 4 1/2 XHP | 6.438 | 2.875 |  | 4 1/2 XH / 4 1/2 IF |  | 2.97 | 304.22
| 10 | Rig | 9 joints of 5" HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 273.99 | 578.21
| 11 | Rig 2 | 22 Stands of Drill Pipe | 5 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2063.61 | 2641.82
| 12 | AGHF-0675-0034 | NOV Agitator-Shock Sub- Safety Joint | 6.75 | 2 |  | 4 1/2 IF / 4 1/2 IF |  | 30.02 | 2671.84
| 13 | [8 empty] | 2671.84
Comments
Bit Info= 9 7/8" - Ulterra - SPL613 SN= 54300 Jets= 6x14's & 3x16's TFA= 1.491 Motor Info= 8", 7/8, 5.9 Stg. @ 2.00? Slick Bit To Bend= 5.90' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s | 1.49 | Ulterra | SPL613 | New |  | 6988
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  | PDCI / 7/8 5.9 | 5.90 / 2.00 |  | 0 | 8.38 | 0 | 1
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 80 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_3
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2671.84 (Usft)
Well: |  |  | Sabine D 4H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1100921 | Bit #: |  | 2 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 01/20/2021 | Depth In: |  | 9904 | Total Drilled: |  | 267.00 (Usft)
Date Out: |  |  | 01/21/2021 | Depth Out: |  | 10171 | Drilling / Circ Hours: |  | 5.18 / 1.23
Survey Offset: |  |  | 71 | Gamma Offset: |  | 61
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 54300 | 9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s | 9.875 | 2 |  | 6 5/8 REG |  | 1.2 | 1.2
| 2 | PPM800012 | 7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 | 8 | 2 | 1.69 | 6 5/8 REG / 6 5/8 REG |  | 37.56 | 38.76
| 3 | SD45067 | 8" - NMPDC | 7.938 | 3.188 |  | 6 5/8 REG / 6 5/8 REG |  | 10.67 | 49.43
| 4 | 775210 | 7 3/4" UBHO | 7.75 | 2.75 |  | 6 5/8 REG / 6 5/8 REG |  | 3.84 | 53.27
| 5 | SD55685 | 8" - NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 28.58 | 81.85
| 6 | SD55520 | 8" - NMDC | 7.938 | 3.125 |  | 6 5/8 REG / 6 5/8 REG |  | 28.91 | 110.76
| 7 | SD107481 | X/O- 4 1/2 XHB x 6 5/8 RegP | 6.5 | 2.875 |  | 4 1/2 XH / 6 5/8 REG |  | 2.28 | 113.04
| 8 | Rig 1 | 6 Joints of 6.5" Drill Collars | 6.5 | 2.875 |  | 4 1/2 XH / 4 1/2 XH |  | 188.21 | 301.25
| 9 | SD107702 | X/O- 4 1/2 IFB x 4 1/2 XHP | 6.438 | 2.875 |  | 4 1/2 XH / 4 1/2 IF |  | 2.97 | 304.22
| 10 | Rig | 9 joints of 5" HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 273.99 | 578.21
| 11 | Rig 2 | 22 Stands of Drill Pipe | 5 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2063.61 | 2641.82
| 12 | AGHF-0675-0034 | NOV Agitator-Shock Sub- Safety Joint | 6.75 | 2 |  | 4 1/2 IF / 4 1/2 IF |  | 30.02 | 2671.84
| 13 | [8 empty] | 2671.84
Comments
Bit Info= 9 7/8" - Ulterra - SPL613 SN= 54300 Jets= 6x14's & 3x16's TFA= 1.491 Motor Info= 8", 7/8, 5.9 Stg. @ 2.00? Slick Bit To Bend= 5.90' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s | 1.49 | Ulterra | SPL613 | New |  | 267
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  | PDCI / 7/8 5.9 | 5.90 / 2.00 |  | 0 | 8.38 | 0 | 1
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22 |  |  | 0 | 80 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_4
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2739.95 (Usft)
Well: |  |  | Sabine D 4H | BHA #: |  | 4 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1100921 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 03/12/2021 | Depth In: |  | 10171 | Total Drilled: |  | 749.00 (Usft)
Date Out: |  |  | 03/14/2021 | Depth Out: |  | 10920 | Drilling / Circ Hours: |  | 11.87 / 4.80
Survey Offset: |  |  | 67 | Gamma Offset: |  | 58
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13522000 | GTD64M | 6.75 | 2 |  | 3 1/2 Reg |  | 0.72 | 0.72
| 2 | PPM250004 | 6/7 8.8 2.00 Slick HS88 .017 | 5.5 | 2 | 4.938 / 1.87 | XT39 / 3 1/2 Reg |  | 33.04 | 33.76
| 3 | Rig- 2 | BTI Valve | 4.938 | 2.563 |  | XT39 / XT39 |  | 2.43 | 36.19
| 4 | SD56841 | NM Pony Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 11.51 | 47.7
| 5 | 500043 | UBHO | 5.25 | 2.5 |  | XT39 / XT39 |  | 4 | 51.7
| 6 | SD56785 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.98 | 82.68
| 7 | SD56702 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.38 | 113.06
| 8 | A52101 | Tomax Thruster | 5 | 2.25 |  | XT39 / XT39 |  | 17.95 | 131.01
| 9 | 119312 | XO- XT39Pin x DS42Box | 5.5 | 2.75 |  | DS42 / XT39 |  | 3.24 | 134.25
| 10 | Rig-6 | 2 Stands of Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 190.36 | 324.61
| 11 | 051916-02 | Drill N Ream Reamer | 5.25 | 2.75 |  | DS42 / DS42 |  | 7.93 | 332.54
| 12 | Rig 1 | 25 stands of Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2378.29 | 2710.83
| 13 | AGOD525-OD006 | Agitator-Shock Sub-Safety Joint | 5.375 | 3 |  | DS42 / DS42 |  | 29.12 | 2739.95
| 14 | [8 empty] | 2739.95
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New |  | 749
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.00 Slick HS88 .017 |  |  | PDCI / 6/7 8.8 | 4.03 / 2.00 |  | 0 | 5.5 | 150 | 2
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Plus) |  | 0.017
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Mud Pulse
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6044 |  |  |  | 9011 |  | 1106 | 1056 |  | 424
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
3006/4002
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## BHA_5
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2740.05 (Usft)
Well: |  |  | Sabine D 4H | BHA #: |  | 5 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1100921 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 03/14/2021 | Depth In: |  | 10920 | Total Drilled: |  | 4289.00 (Usft)
Date Out: |  |  | 03/17/2021 | Depth Out: |  | 15209 | Drilling / Circ Hours: |  | 47.07 / 5.87
Survey Offset: |  |  | 67 | Gamma Offset: |  | 58
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13401055 | GTD64M | 6.75 | 2 |  | XT39 |  | 0.76 | 0.76
| 2 | PPM250024 | 6/7 8.8 2.00 Slick HS88 .006 | 5.5 | 2 | 4.938 / 1.87 | XT39 / 3 1/2 Reg |  | 33.2 | 33.96
| 3 | RIG-3 | YES | 4.86 | 2 |  | XT39 / XT39 |  | 2.36 | 36.32
| 4 | SD56841 | NM Pony Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 11.51 | 47.83
| 5 | 500042 | UBHO | 5.23 | 2.5 |  | XT39 / XT39 |  | 3.97 | 51.8
| 6 | SD56785 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.98 | 82.78
| 7 | SD56702 | NM Drill Collar | 5 | 2.75 |  | XT39 / XT39 |  | 30.38 | 113.16
| 8 | A52101 | Tomax Thruster | 5 | 2.25 |  | XT39 / XT39 |  | 17.95 | 131.11
| 9 | 119312 | XO- XT39Pin x DS42Box | 5.5 | 2.75 |  | DS42 / XT39 |  | 3.24 | 134.35
| 10 | Rig-6 | 2 Stands of Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 190.36 | 324.71
| 11 | 051916-02 | Drill N Ream Reamer | 5.25 | 2.75 |  | DS42 / DS42 |  | 7.93 | 332.64
| 12 | Rig 1 | 25 stands of Drill Pipe | 4.5 | 2.5 |  | DS42 / DS42 |  | 2378.29 | 2710.93
| 13 | AGOD525-OD006 | Agitator-Shock Sub-Safety Joint | 5.375 | 3 |  | DS42 / DS42 |  | 29.12 | 2740.05
| 14 | [8 empty] | 2740.05
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | GTD64M | 1.49 | Security | GTD64M | New |  | 4289
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 8.8 2.00 Slick HS88 .006 |  |  | PDCI / 6/7 8.8 | 4.10 / 2.00 |  | 0 | 5.52 | 150 | 2
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8 |  |  | 0 | 80 |  | 150-400 | 0.68 | FBH | Mud Loop
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
|  |  | PV Fluids | HS88 (Plus) |  | 0.006
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Mud Pulse
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
6067 |  |  |  | 9013 |  | 1111 | 1121 |  | 246
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
3113/4001
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Well: |  | Sabine D 4H
|  |  |  | Longitude: |  | 96° 45' 45.405" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 82.00/95.02/113.00
Date In: |  | 01/16/2021 08:30 |  | SN: |  | PPM800001 |  |  |  | WOB Rotate (klbs): |  | 15.00
Date Out: |  | 01/16/2021 19:42 |  | Description: |  | 7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) |  |  |  | WOB Slide (klbs): |  | 10.31
Depth In/Out(Usft): |  | 105.00 / 2916.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 100.00 / 97.21
Inc In/Out: |  | 0.12 / 14.09 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 882.86
Azi In/Out: |  | 315.57 / 317.46 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 1775.27
Total Drilled (Usft): |  | 2811 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 2063.39
%Slide (Ftg): |  | 14.94 |  | Bit to Bend (Usft): |  | 6.01 |  |  |  | Tq On Btm (kftlbs): |  | 4209.3
%Slide (Time): |  | 52.22 |  | Sleeve Stab OD (in): |  | 13 |  |  |  | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 420 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 2.55 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 85.06 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 47.71 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2391 |  | Fishneck OD (in): |  | 8 |  |  |  | OD (in): |  | 13.5
Rotary Hours: |  | 2.33 |  | Length (Usft): |  | 37.68 |  |  |  | TFA: |  | 1.18
Total Drlg Hrs: |  | 4.88 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 0.93 / 11.20 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 164.71 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 1026.18 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 4.88
Avg ROP (Usft/hr): |  | 576.02 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 0.93
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
|  |  |  | 0.00 | [8 empty] | 113
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
76 | [11 empty] | 0.00 / 2.76
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
13 1/2" Ulterra- U616S- Jetted 6x16s 1.18 |  |  |  | 37295 |  | 13.5 | 2 |  |  |  | 1.5 | 1.5
7 3/4" - 7/8, 5.9 Stg. @ 1.50? (Float Installed) 0.00 |  |  |  | PPM800001 |  | 8 | 2 |  |  |  | 37.68 | 39.18
13" - 4 Blade Nortrak Stabilizer (BFF) 0.00 |  |  |  | SD610467 |  | 8 | 2.813 |  |  |  | 7.23 | 46.41
8" - NMPDC 0.00 |  |  |  | SD45067 |  | 7.938 | 3.188 |  |  |  | 10.67 | 57.08
7 3/4" UBHO 0.00 |  |  |  | 775210 |  | 7.75 | 2.75 |  |  |  | 3.84 | 60.92
8" - NMDC 0.00 |  |  |  | SD55685 |  | 8 | 3.25 |  |  |  | 28.58 | 89.5
8" - NMDC 0.00 |  |  |  | SD55520 |  | 7.938 | 3.125 |  |  |  | 28.91 | 118.41
X/O- 4 1/2 IFB x 6 5/8 RegP 0.00 |  |  |  | SD114192 |  | 8 | 3 |  |  |  | 3.12 | 121.53
9 joints of 5" HWDP 0.00 |  |  |  | Rig |  | 5 | 3 |  |  |  | 273.99 | 395.52
Additional Comments
BHA performed as expected; Motor drained well on surface w/ minimal slack in bearing and showed no visible signs of wear; Bit was green w/ no dull characteristics
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Well: |  | Sabine D 4H
|  |  |  | Longitude: |  | 96° 45' 45.405" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | MWD Incident |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 102.00/186.31/225.00
Date In: |  | 01/18/2021 04:20 |  | SN: |  | PPM800012 |  |  |  | WOB Rotate (klbs): |  | 34.00
Date Out: |  | 01/20/2021 10:15 |  | Description: |  | 7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  |  | WOB Slide (klbs): |  | 19.78
Depth In/Out(Usft): |  | 2916.00 / 9904.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 79.68
Inc In/Out: |  | 14.09 / 0.53 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 830.8
Azi In/Out: |  | 317.46 / 171.63 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 4182.31
Total Drilled (Usft): |  | 6988 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4702.99
%Slide (Ftg): |  | 6.70 |  | Bit to Bend (Usft): |  | 5.9 |  |  |  | Tq On Btm (kftlbs): |  | 15148.94
%Slide (Time): |  | 27.53 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 468 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 8.03 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 93.30 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 72.48 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6520 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 9.875
Rotary Hours: |  | 21.14 |  | Length (Usft): |  | 37.56 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 29.17 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 2.00 / 53.92 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 58.28 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 308.42 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 29.17
Avg ROP (Usft/hr): |  | 239.56 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.00
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 15 / 10 | 5 / 4 |  | 76.00 |  | 10 | 10 | 9.4 | 52000 | OBM | 7.9 |  | 225
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
71 | 61 | [10 empty] | 0.00 / 3.24
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s 1.49 |  |  |  | 54300 |  | 9.875 | 2 |  |  |  | 1.2 | 1.2
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 0.00 |  |  |  | PPM800012 |  | 8 | 2 |  |  |  | 37.56 | 38.76
8" - NMPDC 0.00 |  |  |  | SD45067 |  | 7.938 | 3.188 |  |  |  | 10.67 | 49.43
7 3/4" UBHO 0.00 |  |  |  | 775210 |  | 7.75 | 2.75 |  |  |  | 3.84 | 53.27
8" - NMDC 0.00 |  |  |  | SD55685 |  | 8 | 3.25 |  |  |  | 28.58 | 81.85
8" - NMDC 0.00 |  |  |  | SD55520 |  | 7.938 | 3.125 |  |  |  | 28.91 | 110.76
X/O- 4 1/2 XHB x 6 5/8 RegP 0.00 |  |  |  | SD107481 |  | 6.5 | 2.875 |  |  |  | 2.28 | 113.04
6 Joints of 6.5" Drill Collars 0.00 |  |  |  | Rig 1 |  | 6.5 | 2.875 |  |  |  | 188.21 | 301.25
X/O- 4 1/2 IFB x 4 1/2 XHP 0.00 |  |  |  | SD107702 |  | 6.438 | 2.875 |  |  |  | 2.97 | 304.22
9 joints of 5" HWDP 0.00 |  |  |  | Rig |  | 5 | 3 |  |  |  | 273.99 | 578.21
22 Stands of Drill Pipe 0.00 |  |  |  | Rig 2 |  | 5 | 2.75 |  |  |  | 2063.61 | 2641.82
NOV Agitator-Shock Sub- Safety Joint 0.00 |  |  |  | AGHF-0675-0034 |  | 6.75 | 2 |  |  |  | 30.02 | 2671.84
-1.00 | [11 empty] | 2671.84
Additional Comments
BHA performed as expected, drilling out vertical section per plan, had to troubleshoot MWD tool with no success. Desicion was made to TOH to replace tool. At surface, motor drained strong, bit had 2 chipped cutters. Desicion was made to rerun assembly and bit to finish remaining 235.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Well: |  | Sabine D 4H
|  |  |  | Longitude: |  | 96° 45' 45.405" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 225.00/225.00/225.00
Date In: |  | 01/20/2021 10:30 |  | SN: |  | PPM800012 |  |  |  | WOB Rotate (klbs): |  | 18.00
Date Out: |  | 01/21/2021 03:30 |  | Description: |  | 7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 |  |  |  | WOB Slide (klbs): |  | 18.00
Depth In/Out(Usft): |  | 9904.00 / 10171.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 50.00
Inc In/Out: |  | 0.53 / 10.35 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 675
Azi In/Out: |  | 171.53 / 147.92 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 3650
Total Drilled (Usft): |  | 267 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4160
%Slide (Ftg): |  | 55.81 |  | Bit to Bend (Usft): |  | 5.9 |  |  |  | Tq On Btm (kftlbs): |  | 21000
%Slide (Time): |  | 74.28 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 149 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 3.85 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 44.19 |  | Kickpad OD (in): |  | 8.375 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 25.66 |  | Body OD (in): |  | 8 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 118 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 9.875
Rotary Hours: |  | 1.33 |  | Length (Usft): |  | 37.56 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 5.18 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 2
Circ/BRT Hrs: |  | 1.23 / 17.00 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 38.7 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 88.72 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 5.18
Avg ROP (Usft/hr): |  | 51.54 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 1.23
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 15 / 10 | 5 / 4 |  | 76.00 |  | 10 | 10 | 9.4 | 52000 | OBM | 7.9 |  | 225
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
71 | 61 | [10 empty] | 0.00 / 7.93
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8" Ulterra- SPL613- Jetted 6x14s & 3x16s 1.49 |  |  |  | 54300 |  | 9.875 | 2 |  |  |  | 1.2 | 1.2
7 3/4" - 7/8, 5.9 Stg. @ 2.00? Slick- -.014 0.00 |  |  |  | PPM800012 |  | 8 | 2 |  |  |  | 37.56 | 38.76
8" - NMPDC 0.00 |  |  |  | SD45067 |  | 7.938 | 3.188 |  |  |  | 10.67 | 49.43
7 3/4" UBHO 0.00 |  |  |  | 775210 |  | 7.75 | 2.75 |  |  |  | 3.84 | 53.27
8" - NMDC 0.00 |  |  |  | SD55685 |  | 8 | 3.25 |  |  |  | 28.58 | 81.85
8" - NMDC 0.00 |  |  |  | SD55520 |  | 7.938 | 3.125 |  |  |  | 28.91 | 110.76
X/O- 4 1/2 XHB x 6 5/8 RegP 0.00 |  |  |  | SD107481 |  | 6.5 | 2.875 |  |  |  | 2.28 | 113.04
6 Joints of 6.5" Drill Collars 0.00 |  |  |  | Rig 1 |  | 6.5 | 2.875 |  |  |  | 188.21 | 301.25
X/O- 4 1/2 IFB x 4 1/2 XHP 0.00 |  |  |  | SD107702 |  | 6.438 | 2.875 |  |  |  | 2.97 | 304.22
9 joints of 5" HWDP 0.00 |  |  |  | Rig |  | 5 | 3 |  |  |  | 273.99 | 578.21
22 Stands of Drill Pipe 0.00 |  |  |  | Rig 2 |  | 5 | 2.75 |  |  |  | 2063.61 | 2641.82
NOV Agitator-Shock Sub- Safety Joint 0.00 |  |  |  | AGHF-0675-0034 |  | 6.75 | 2 |  |  |  | 30.02 | 2671.84
-1.00 | [11 empty] | 2671.84
Additional Comments
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 4
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Well: |  | Sabine D 4H
|  |  |  | Longitude: |  | 96° 45' 45.405" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | MWD Incident |  |  | BHA # |  | 4
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 98.00/223.57/244.00
Date In: |  | 03/12/2021 23:15 |  | SN: |  | PPM250004 |  |  |  | WOB Rotate (klbs): |  | 36.00
Date Out: |  | 03/14/2021 22:05 |  | Description: |  | 6/7 8.8 2.00 Slick HS88 .017 |  |  |  | WOB Slide (klbs): |  | 38.75
Depth In/Out(Usft): |  | 10171.00 / 10920.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 30.00
Inc In/Out: |  | 10.35 / 64.71 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 371.43
Azi In/Out: |  | 147.93 / 131.66 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3153.21
Total Drilled (Usft): |  | 749 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 3792.86
%Slide (Ftg): |  | 68.89 |  | Bit to Bend (Usft): |  | 4.03 |  |  |  | Tq On Btm (kftlbs): |  | 13200
%Slide (Time): |  | 84.69 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 516 |  | Bearing Gap (in): |  | 1.25 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 10.05 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 31.11 |  | Kickpad OD (in): |  | 5.5 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 15.34 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 233 |  | Fishneck OD (in): |  | 4.938 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 1.82 |  | Length (Usft): |  | 33.04 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 11.87 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 4.80 / 46.83 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 51.34 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 128.02 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Plus) / 0.017 |  |  |  | Drill Hrs: |  | 11.87
Avg ROP (Usft/hr): |  | 63.1 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 4.80
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 15 / 10 | 5 / 4 |  | 76.00 |  | 10 | 10 | 9.4 | 52000 | OBM | 7.9 |  | 244
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
67 | 58 | [8 empty] | 8 |  | 16.00 / 12.24
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13522000 |  | 6.75 | 2 |  |  |  | 0.72 | 0.72
6/7 8.8 2.00 Slick HS88 .017 0.00 |  |  |  | PPM250004 |  | 5.5 | 2 |  |  |  | 33.04 | 33.76
BTI Valve 0.00 |  |  |  | Rig- 2 |  | 4.938 | 2.563 |  |  |  | 2.43 | 36.19
NM Pony Drill Collar 0.00 |  |  |  | SD56841 |  | 5 | 2.75 |  |  |  | 11.51 | 47.7
UBHO 0.00 |  |  |  | 500043 |  | 5.25 | 2.5 |  |  |  | 4 | 51.7
NM Drill Collar 0.00 |  |  |  | SD56785 |  | 5 | 2.75 |  |  |  | 30.98 | 82.68
NM Drill Collar 0.00 |  |  |  | SD56702 |  | 5 | 2.75 |  |  |  | 30.38 | 113.06
Tomax Thruster 0.00 |  |  |  | A52101 |  | 5 | 2.25 |  |  |  | 17.95 | 131.01
XO- XT39Pin x DS42Box 0.00 |  |  |  | 119312 |  | 5.5 | 2.75 |  |  |  | 3.24 | 134.25
2 Stands of Drill Pipe 0.00 |  |  |  | Rig-6 |  | 4.5 | 2.5 |  |  |  | 190.36 | 324.61
Drill N Ream Reamer 0.00 |  |  |  | 051916-02 |  | 5.25 | 2.75 |  |  |  | 7.93 | 332.54
25 stands of Drill Pipe 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 2378.29 | 2710.83
Agitator-Shock Sub-Safety Joint 0.00 |  |  |  | AGOD525-OD006 |  | 5.375 | 3 |  |  |  | 29.12 | 2739.95
-1.00 | [11 empty] | 2739.95
Additional Comments
Reason POOH - MWD was pumping up bad Dip, gravity and INC/AZM was incorrect. How did motor drain - Drained good, no problems seen Visual wear - No Visual Wear Run Description - BHA performed good int he curve with 16 Yields Max temp on run- 254 How Many Stalls - Zero Stalls Motor Yields - 16 in the curve, no other section was drilled. Max Drilling Diff - 1100 psi Average Drilling Diff - 450 Condition of bit on surface - Bit was a 1-1 with no wear. Bit was changed out of caution and not due to wear.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 5
|  |  |  | Job # |  | LTX1100921 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31146 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 8' 32.612" N |  |  | Well: |  | Sabine D 4H
|  |  |  | Longitude: |  | 96° 45' 45.405" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | Hole Conditions |  |  | BHA # |  | 5
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 248.00/271.89/288.00
Date In: |  | 03/14/2021 23:30 |  | SN: |  | PPM250024 |  |  |  | WOB Rotate (klbs): |  | 40.00
Date Out: |  | 03/17/2021 21:20 |  | Description: |  | 6/7 8.8 2.00 Slick HS88 .006 |  |  |  | WOB Slide (klbs): |  | 43.00
Depth In/Out(Usft): |  | 10920.00 / 15209.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 80.00 / 75.83
Inc In/Out: |  | 64.72 / 86.26 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 400
Azi In/Out: |  | 131.65 / 136.43 |  | Lobes / Stages: |  | 6/7 / 8.8 |  |  |  | Off Btm Press (psi): |  | 3600
Total Drilled (Usft): |  | 4289 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 4378.24
%Slide (Ftg): |  | 18.16 |  | Bit to Bend (Usft): |  | 4.1 |  |  |  | Tq On Btm (kftlbs): |  | 15284.72
%Slide (Time): |  | 58.92 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 779 |  | Bearing Gap (in): |  | 1.25 |  |  |  | Avg Diff Press (psi):
Slide Hours: |  | 27.73 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 81.84 |  | Kickpad OD (in): |  | 5.52 |  |  |  | Make: |  | Security
%Rotary (Time): |  | 41.09 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 3510 |  | Fishneck OD (in): |  | 4.938 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 19.34 |  | Length (Usft): |  | 33.2 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 47.07 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 5.87 / 69.83 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 28.09 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 181.49 |  | Stator Vendor/Type/Fit: |  | PV Fluids / HS88 (Plus) / 0.006 |  |  |  | Drill Hrs: |  | 47.07
Avg ROP (Usft/hr): |  | 91.12 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 5.87
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
30 / 20 | 15 / 10 | 5 / 4 |  | 76.00 |  | 10 | 10 | 9.4 | 52000 | OBM | 7.9 |  | 288
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
67 | 58 | [10 empty] | 0.00 / 11.59
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
GTD64M 1.49 |  |  |  | 13401055 |  | 6.75 | 2 |  |  |  | 0.76 | 0.76
6/7 8.8 2.00 Slick HS88 .006 0.00 |  |  |  | PPM250024 |  | 5.5 | 2 |  |  |  | 33.2 | 33.96
YES 0.00 |  |  |  | RIG-3 |  | 4.86 | 2 |  |  |  | 2.36 | 36.32
NM Pony Drill Collar 0.00 |  |  |  | SD56841 |  | 5 | 2.75 |  |  |  | 11.51 | 47.83
UBHO 0.00 |  |  |  | 500042 |  | 5.23 | 2.5 |  |  |  | 3.97 | 51.8
NM Drill Collar 0.00 |  |  |  | SD56785 |  | 5 | 2.75 |  |  |  | 30.98 | 82.78
NM Drill Collar 0.00 |  |  |  | SD56702 |  | 5 | 2.75 |  |  |  | 30.38 | 113.16
Tomax Thruster 0.00 |  |  |  | A52101 |  | 5 | 2.25 |  |  |  | 17.95 | 131.11
XO- XT39Pin x DS42Box 0.00 |  |  |  | 119312 |  | 5.5 | 2.75 |  |  |  | 3.24 | 134.35
2 Stands of Drill Pipe 0.00 |  |  |  | Rig-6 |  | 4.5 | 2.5 |  |  |  | 190.36 | 324.71
Drill N Ream Reamer 0.00 |  |  |  | 051916-02 |  | 5.25 | 2.75 |  |  |  | 7.93 | 332.64
25 stands of Drill Pipe 0.00 |  |  |  | Rig 1 |  | 4.5 | 2.5 |  |  |  | 2378.29 | 2710.93
Agitator-Shock Sub-Safety Joint 0.00 |  |  |  | AGOD525-OD006 |  | 5.375 | 3 |  |  |  | 29.12 | 2740.05
-1.00 | [11 empty] | 2740.05
Additional Comments
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 |  |  |  |  | RKB: |  |  |  | 487 |  | North Reference: |  | GRID |  | Total Drilled: |  | 2811
Site: |  |  |  |  | Sabine - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 420
Well Name: |  |  |  |  | Sabine D 4H |  |  | Survey / Gamma Offset: |  |  |  |  | 76.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 487 |  | VS Azimuth: |  | 136.56 |  | Rotate: |  | 2391
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
01/16/2021 | 08:30 | 08:32 | 0.033333 | 105 | 212 | 107 | Rotate |  | 136 | 0.15 | 315.57 | 136 | 0.13 | -0.12 | 0.13 | 0.11 |  |  | 5 | 40 | 450 | 2500 | 3209.99 | 550 | 465 | 85 | 82 | 60 | 60 | 60
01/16/2021 | 08:36 | 08:38 | 0.033333 | 212 | 304 | 92 | Rotate |  | 228 | 0.16 | 66.18 | 228 | 0.27 | -0.09 | 0.27 | 0.28 |  |  | 5 | 60 | 570 | 2500 | 2759.99 | 900 | 700 | 200 | 82 | 60 | 60 | 60
01/16/2021 | 08:43 | 08:46 | 0.05 | 304 | 395 | 91 | Rotate |  | 319 | 0.15 | 252.93 | 319 | 0.28 | -0.09 | 0.28 | 0.34 |  |  | 5 | 80 | 720 | 3000 | 1820 | 1200 | 900 | 300 | 82 | 60 | 60 | 60
01/16/2021 | 08:50 | 08:55 | 0.083333 | 395 | 489 | 94 | Rotate |  | 413 | 0.36 | 228.59 | 413 | 0.05 | -0.43 | 0.05 | 0.25 |  |  | 12 | 100 | 900 | 3500 | 1128 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 08:59 | 09:00 | 0.016667 | 489 | 500 | 11 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 660 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 09:00 | 09:05 | 0.083333 | 500 | 525 | 25 | Slide | 0 | 507 | 0.62 | 127.87 | 507 | -0.46 | -0.25 | -0.46 | 0.82 |  |  | 5 |  | 900 |  | 300 | 1750 | 1700 | 50 | 84 | 60 | 60 | 60
01/16/2021 | 09:05 | 09:10 | 0.083333 | 525 | 583 | 58 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 696 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 09:14 | 09:15 | 0.016667 | 583 | 595 | 12 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 720 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 09:15 | 09:21 | 0.1 | 595 | 620 | 25 | Slide | 0 | 600 | 1.87 | 94.05 | 599.97 | -0.87 | 1.66 | -0.87 | 1.5 |  |  | 5 |  | 900 |  | 250 | 1750 | 1700 | 50 | 84 | 60 | 60 | 60
01/16/2021 | 09:21 | 09:23 | 0.033333 | 620 | 676 | 56 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 1680 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 09:27 | 09:28 | 0.016667 | 676 | 685 | 9 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 540 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 09:28 | 09:34 | 0.1 | 685 | 710 | 25 | Slide | 0 | 693 | 3.48 | 88.52 | 692.87 | -0.91 | 6 | -0.91 | 1.75 |  |  | 5 |  | 900 |  | 250 | 1750 | 1700 | 50 | 84 | 60 | 60 | 60
01/16/2021 | 09:34 | 09:38 | 0.066667 | 710 | 769 | 59 | Rotate | Drilling Parameters WOB: 12; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 3500; Drilling Parameters ROP: 885 | 2000 | 1700 | 300 | 84 | 60 | 60 | 60
01/16/2021 | 09:42 | 09:46 | 0.066667 | 769 | 862 | 93 | Rotate |  | 786 | 4.43 | 85.9 | 785.65 | -0.58 | 12.4 | -0.58 | 1.04 |  |  | 12 | 100 | 900 | 3500 | 1395 | 2000 | 1700 | 300 | 84 | 80 | 75 | 70
01/16/2021 | 09:50 | 09:54 | 0.066667 | 862 | 956 | 94 | Rotate |  | 880 | 4.44 | 87.8 | 879.37 | -0.18 | 19.66 | -0.18 | 0.16 |  |  | 12 | 100 | 900 | 3500 | 1410 | 2000 | 1700 | 300 | 84 | 80 | 75 | 70
01/16/2021 | 09:58 | 09:59 | 0.016667 | 956 | 965 | 9 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 540 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 09:59 | 10:04 | 0.083333 | 965 | 990 | 25 | Slide | 0 | 974 | 4.93 | 81.11 | 973.05 | 0.58 | 27.29 | 0.58 | 0.78 |  |  | 7 |  | 900 |  | 300 | 1800 | 1700 | 100 | 87 | 80 | 75 | 70
01/16/2021 | 10:04 | 10:07 | 0.05 | 990 | 1050 | 60 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 1200 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:11 | 10:15 | 0.066667 | 1050 | 1144 | 94 | Rotate |  | 1068 | 5.92 | 74.28 | 1066.63 | 2.52 | 35.94 | 2.52 | 1.26 |  |  | 20 | 100 | 900 | 5000 | 1410 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:19 | 10:23 | 0.066667 | 1144 | 1238 | 94 | Rotate |  | 1162 | 5.96 | 73.21 | 1160.13 | 5.25 | 45.28 | 5.25 | 0.13 |  |  | 20 | 100 | 900 | 5000 | 1410 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:27 | 10:32 | 0.083333 | 1238 | 1333 | 95 | Rotate |  | 1257 | 5.6 | 72.7 | 1254.64 | 8.05 | 54.43 | 8.05 | 0.38 |  |  | 20 | 100 | 900 | 5000 | 1140 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:36 | 10:42 | 0.1 | 1333 | 1426 | 93 | Rotate |  | 1350 | 5.44 | 72.26 | 1347.21 | 10.74 | 62.96 | 10.74 | 0.18 |  |  | 20 | 100 | 900 | 5000 | 930 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:46 | 10:53 | 0.11667 | 1426 | 1520 | 94 | Rotate |  | 1444 | 5.34 | 71.41 | 1440.8 | 13.49 | 71.35 | 13.49 | 0.14 |  |  | 20 | 100 | 900 | 5000 | 805.71 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:57 | 10:58 | 0.016667 | 1520 | 1540 | 20 | Rotate |  | 1538 | 5.16 | 64.16 | 1534.4 | 16.73 | 79.3 | 16.73 | 0.73 |  |  | 20 | 100 | 900 | 5000 | 1200 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 10:58 | 11:07 | 0.15 | 1540 | 1575 | 35 | Slide | TTF: 0; Drilling Parameters WOB: 7; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 233.33 | 1800 | 1700 | 100 | 87 | 80 | 75 | 70
01/16/2021 | 11:07 | 11:12 | 0.083333 | 1575 | 1614 | 39 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 468 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 11:16 | 11:22 | 0.1 | 1614 | 1708 | 94 | Rotate |  | 1632 | 5.4 | 47.32 | 1628.01 | 21.57 | 86.36 | 21.57 | 1.66 |  |  | 20 | 100 | 900 | 5000 | 940 | 2000 | 1700 | 300 | 87 | 80 | 75 | 70
01/16/2021 | 11:26 | 11:27 | 0.016667 | 1708 | 1715 | 7 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 420 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 11:27 | 11:39 | 0.2 | 1715 | 1750 | 35 | Slide | 0 | 1726 | 5.08 | 28.8 | 1721.62 | 28.22 | 91.61 | 28.22 | 1.82 |  |  | 12 |  | 900 |  | 175 | 2050 | 1950 | 100 | 96 | 100 | 95 | 90
01/16/2021 | 11:39 | 11:42 | 0.05 | 1750 | 1802 | 52 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 1040 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 11:46 | 11:47 | 0.016667 | 1802 | 1815 | 13 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 780 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 11:47 | 12:04 | 0.28333 | 1815 | 1855 | 40 | Slide | 0 | 1820 | 5.48 | 8.65 | 1815.23 | 36.3 | 94.29 | 36.3 | 2.01 |  |  | 12 |  | 900 |  | 141.18 | 2050 | 1950 | 100 | 96 | 100 | 95 | 90
01/16/2021 | 12:04 | 12:07 | 0.05 | 1855 | 1896 | 41 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 820 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 12:11 | 12:12 | 0.016667 | 1896 | 1905 | 9 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 540 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 12:12 | 12:24 | 0.2 | 1905 | 1945 | 40 | Slide | 0 | 1914 | 6.46 | 345.29 | 1908.73 | 45.86 | 93.63 | 45.86 | 2.76 |  |  | 12 |  | 900 |  | 200 | 2050 | 1950 | 100 | 96 | 100 | 95 | 90
01/16/2021 | 12:24 | 12:28 | 0.066667 | 1945 | 1990 | 45 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 675 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 12:32 | 12:33 | 0.016667 | 1990 | 2000 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 600 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 12:33 | 12:46 | 0.21667 | 2000 | 2030 | 30 | Slide | 0 | 2008 | 7.42 | 325.26 | 2002.06 | 55.96 | 88.82 | 55.96 | 2.75 |  |  | 12 |  | 900 |  | 138.46 | 2050 | 1950 | 100 | 96 | 100 | 95 | 90
01/16/2021 | 12:46 | 12:49 | 0.05 | 2030 | 2084 | 54 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 1080 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 12:53 | 12:59 | 0.1 | 2084 | 2178 | 94 | Rotate |  | 2102 | 7.52 | 315.65 | 2095.26 | 65.35 | 81.06 | 65.35 | 1.33 |  |  | 20 | 100 | 900 | 8500 | 940 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 13:03 | 13:04 | 0.016667 | 2178 | 2185 | 7 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 420 | 2350 | 1950 | 400 | 96 | 100 | 95 | 90
01/16/2021 | 13:04 | 13:16 | 0.2 | 2185 | 2215 | 30 | Slide | 0 | 2195 | 8.11 | 316.46 | 2187.4 | 74.45 | 72.29 | 74.45 | 0.65 |  |  | 12 |  | 900 |  | 150 | 2050 | 1950 | 100 | 105 | 100 | 95 | 90
01/16/2021 | 13:16 | 13:19 | 0.05 | 2215 | 2271 | 56 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 8500; Drilling Parameters ROP: 1120 | 2350 | 1950 | 400 | 105 | 100 | 95 | 90
01/16/2021 | 13:23 | 13:24 | 0.016667 | 2271 | 2280 | 9 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 1000; Drilling Parameters ROP: 540 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 13:24 | 13:44 | 0.33333 | 2280 | 2320 | 40 | Slide | 0 | 2289 | 9.86 | 317.56 | 2280.24 | 85.2 | 62.29 | 85.2 | 1.87 |  |  | 15 |  | 900 |  | 120 | 2150 | 1950 | 200 | 113 | 120 | 110 | 100
01/16/2021 | 13:44 | 13:47 | 0.05 | 2320 | 2365 | 45 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 1000; Drilling Parameters ROP: 900 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 13:52 | 13:53 | 0.016667 | 2365 | 2375 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 1000; Drilling Parameters ROP: 600 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 13:53 | 14:14 | 0.35 | 2375 | 2415 | 40 | Slide | 0 | 2383 | 12.07 | 319.23 | 2372.52 | 98.58 | 50.44 | 98.58 | 2.37 |  |  | 15 |  | 900 |  | 114.29 | 2150 | 1950 | 200 | 113 | 120 | 110 | 100
01/16/2021 | 14:14 | 14:18 | 0.066667 | 2415 | 2459 | 44 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 1000; Drilling Parameters ROP: 660 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 14:22 | 14:28 | 0.1 | 2459 | 2553 | 94 | Rotate |  | 2477 | 13.34 | 319.66 | 2464.22 | 114.29 | 37 | 114.29 | 1.35 |  |  | 20 | 100 | 900 | 1000 | 940 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 14:32 | 14:38 | 0.1 | 2553 | 2643 | 90 | Rotate |  | 2571 | 13.13 | 319.64 | 2555.72 | 130.7 | 23.07 | 130.7 | 0.22 |  |  | 20 | 100 | 900 | 1000 | 900 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 14:42 | 14:43 | 0.016667 | 2643 | 2655 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 1000; Drilling Parameters ROP: 720 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 14:43 | 14:58 | 0.25 | 2655 | 2685 | 30 | Slide | 0 | 2664 | 13.74 | 319.21 | 2646.18 | 147.11 | 9.01 | 147.11 | 0.66 |  |  | 15 |  | 900 |  | 120 | 2150 | 1950 | 200 | 113 | 120 | 110 | 100
01/16/2021 | 14:58 | 15:04 | 0.1 | 2685 | 2740 | 55 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 1000; Drilling Parameters ROP: 550 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 15:09 | 15:13 | 0.066667 | 2740 | 2834 | 94 | Rotate |  | 2758 | 14.63 | 318.26 | 2737.31 | 164.42 | -6.18 | 164.42 | 0.98 |  |  | 20 | 100 | 900 | 1000 | 1410 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100
01/16/2021 | 15:17 | 15:22 | 0.083333 | 2834 | 2916 | 82 | Rotate |  | 2840 | 14.49 | 317.18 | 2816.68 | 179.67 | -20.05 | 179.67 | 0.37 |  |  | 20 | 100 | 900 | 1000 | 984 | 2350 | 1950 | 400 | 113 | 120 | 110 | 100

## BHA_2_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 |  |  |  |  | RKB: |  |  |  | 487 |  | North Reference: |  | GRID |  | Total Drilled: |  | 6988
Site: |  |  |  |  | Sabine - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 468
Well Name: |  |  |  |  | Sabine D 4H |  |  | Survey / Gamma Offset: |  |  |  |  | 71.00 / 61.00 |  |  |  |  | Grid Conv: |  |  |  | 487 |  | VS Azimuth: |  | 136.56 |  | Rotate: |  | 6520
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
01/18/2021 | 08:52 | 08:56 | 0.066667 | 2916 | 2926 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 480; Drilling Parameters Tq: 5000; Drilling Parameters ROP: 150 | 1700 | 1480 | 220 | 102 | 145 | 135 | 125
01/18/2021 | 09:29 | 09:48 | 0.31667 | 2926 | 3047 | 121 | Rotate |  | 2976 | 13.78 | 317.7 | 2948.56 | 204.13 | -42.52 | 204.13 | 0.53 |  |  | 20 | 80 | 575 | 5800 | 382.11 | 2450 | 1950 | 500 | 102 | 145 | 135 | 125
01/18/2021 | 09:54 | 10:01 | 0.11667 | 3047 | 3140 | 93 | Rotate |  | 3069 | 13.33 | 316.32 | 3038.97 | 220.07 | -57.37 | 220.07 | 0.6 |  |  | 30 | 80 | 673 | 5800 | 797.14 | 3200 | 2650 | 550 | 102 | 145 | 135 | 125
01/18/2021 | 10:05 | 10:07 | 0.033333 | 3140 | 3150 | 10 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 673; Drilling Parameters Tq: 5800; Drilling Parameters ROP: 300 | 3200 | 2650 | 550 | 102 | 145 | 135 | 125
01/18/2021 | 10:07 | 10:14 | 0.11667 | 3150 | 3165 | 15 | Slide | 0 | 3163 | 14.48 | 318.15 | 3130.21 | 236.67 | -72.7 | 236.67 | 1.31 |  |  | 12 |  | 673 |  | 128.57 | 2800 | 2650 | 150 | 102 | 145 | 135 | 125
01/18/2021 | 10:14 | 10:16 | 0.033333 | 3165 | 3182 | 17 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 673; Drilling Parameters Tq: 5800; Drilling Parameters ROP: 510 | 3200 | 2650 | 550 | 102 | 145 | 135 | 125
01/18/2021 | 11:27 | 11:34 | 0.11667 | 3182 | 3234 | 52 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 673; Drilling Parameters Tq: 5800; Drilling Parameters ROP: 445.71 | 3200 | 2650 | 550 | 102 | 145 | 135 | 125
01/18/2021 | 11:40 | 11:53 | 0.21667 | 3234 | 3328 | 94 | Rotate |  | 3257 | 15.1 | 317.76 | 3221.1 | 254.48 | -88.77 | 254.48 | 0.67 |  |  | 38 | 80 | 900 | 6500 | 433.85 | 4900 | 4300 | 600 | 134 | 155 | 140 | 130
01/18/2021 | 11:57 | 12:06 | 0.15 | 3328 | 3422 | 94 | Rotate |  | 3351 | 15.47 | 316.7 | 3311.77 | 272.67 | -105.6 | 272.67 | 0.49 |  |  | 38 | 80 | 900 | 6500 | 626.67 | 4900 | 4300 | 600 | 134 | 155 | 140 | 130
01/18/2021 | 12:10 | 12:18 | 0.13333 | 3422 | 3515 | 93 | Rotate |  | 3444 | 15.68 | 315.63 | 3401.36 | 290.68 | -122.89 | 290.68 | 0.38 |  |  | 38 | 80 | 900 | 6500 | 697.5 | 4900 | 4300 | 600 | 134 | 155 | 140 | 130
01/18/2021 | 12:22 | 12:23 | 0.016667 | 3515 | 3525 | 10 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 600 | 4900 | 4300 | 600 | 134 | 155 | 140 | 130
01/18/2021 | 12:23 | 12:30 | 0.11667 | 3525 | 3540 | 15 | Slide | 0 | 3538 | 15.77 | 320.74 | 3491.84 | 309.65 | -139.86 | 309.65 | 1.48 |  |  | 15 |  | 900 |  | 128.57 | 4500 | 4300 | 200 | 134 | 155 | 140 | 130
01/18/2021 | 12:30 | 12:36 | 0.1 | 3540 | 3609 | 69 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 690 | 4900 | 4300 | 600 | 134 | 155 | 140 | 130
01/18/2021 | 12:40 | 12:48 | 0.13333 | 3609 | 3703 | 94 | Rotate |  | 3632 | 15.99 | 322.2 | 3582.26 | 329.77 | -155.88 | 329.77 | 0.49 |  |  | 38 | 80 | 900 | 6500 | 705 | 4900 | 4300 | 600 | 149 | 155 | 140 | 130
01/18/2021 | 12:52 | 13:00 | 0.13333 | 3703 | 3797 | 94 | Rotate |  | 3726 | 16.09 | 321.49 | 3672.6 | 350.2 | -171.93 | 350.2 | 0.23 |  |  | 38 | 80 | 900 | 6500 | 705 | 4900 | 4300 | 600 | 149 | 155 | 140 | 130
01/18/2021 | 13:04 | 13:06 | 0.033333 | 3797 | 3805 | 8 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 6500; Drilling Parameters ROP: 240 | 4900 | 4300 | 600 | 149 | 155 | 140 | 130
01/18/2021 | 13:06 | 13:12 | 0.1 | 3805 | 3820 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 150 | 4500 | 4300 | 200 | 149 | 155 | 140 | 130
01/18/2021 | 13:12 | 13:18 | 0.1 | 3820 | 3891 | 71 | Rotate |  | 3820 | 14.58 | 319.19 | 3763.25 | 369.35 | -187.77 | 369.35 | 1.73 |  |  | 38 | 80 | 900 | 6500 | 710 | 4900 | 4300 | 600 | 149 | 155 | 140 | 130
01/18/2021 | 13:22 | 13:30 | 0.13333 | 3891 | 3985 | 94 | Rotate |  | 3914 | 14.49 | 318.71 | 3854.24 | 387.14 | -203.26 | 387.14 | 0.16 |  |  | 38 | 80 | 900 | 6500 | 705 | 4900 | 4300 | 600 | 149 | 155 | 140 | 130
01/18/2021 | 13:34 | 13:41 | 0.11667 | 3985 | 4080 | 95 | Rotate |  | 4009 | 14.79 | 318.9 | 3946.15 | 405.21 | -219.08 | 405.21 | 0.32 |  |  | 38 | 80 | 900 | 6500 | 814.29 | 4900 | 4300 | 600 | 149 | 155 | 140 | 130
01/18/2021 | 13:45 | 13:47 | 0.033333 | 4080 | 4090 | 10 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 300 | 4900 | 4300 | 600 | 154 | 160 | 150 | 140
01/18/2021 | 13:47 | 13:56 | 0.15 | 4090 | 4105 | 15 | Slide | 0 | 4103 | 14.11 | 322.63 | 4037.18 | 423.35 | -233.92 | 423.35 | 1.23 |  |  | 15 |  | 900 |  | 100 | 4500 | 4300 | 200 | 154 | 160 | 150 | 140
01/18/2021 | 13:56 | 14:04 | 0.13333 | 4105 | 4174 | 69 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 517.5 | 4900 | 4300 | 600 | 154 | 160 | 150 | 140
01/18/2021 | 14:10 | 14:16 | 0.1 | 4174 | 4268 | 94 | Rotate |  | 4197 | 13.32 | 323.39 | 4128.5 | 441.15 | -247.33 | 441.15 | 0.86 |  |  | 38 | 80 | 900 | 6500 | 940 | 4900 | 4300 | 600 | 154 | 155 | 140 | 130
01/18/2021 | 14:20 | 14:26 | 0.1 | 4268 | 4362 | 94 | Rotate |  | 4291 | 13.05 | 322.46 | 4220.02 | 458.26 | -260.25 | 458.26 | 0.37 |  |  | 40 | 80 | 900 | 10000 | 940 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 14:36 | 14:45 | 0.15 | 4362 | 4456 | 94 | Rotate |  | 4385 | 12.97 | 322.74 | 4311.61 | 475.07 | -273.11 | 475.07 | 0.11 |  |  | 40 | 80 | 900 | 10000 | 626.67 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 14:49 | 14:56 | 0.11667 | 4456 | 4550 | 94 | Rotate |  | 4479 | 13.02 | 323.26 | 4403.2 | 491.95 | -285.83 | 491.95 | 0.14 |  |  | 40 | 80 | 900 | 10000 | 805.71 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 15:00 | 15:09 | 0.15 | 4550 | 4643 | 93 | Rotate |  | 4572 | 12.83 | 323.85 | 4493.85 | 508.68 | -298.19 | 508.68 | 0.25 |  |  | 40 | 80 | 900 | 10000 | 620 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 15:10 | 15:21 | 0.18333 | 4643 | 4737 | 94 | Rotate |  | 4667 | 12.58 | 324.01 | 4586.52 | 525.57 | -310.49 | 525.57 | 0.27 |  |  | 40 | 80 | 900 | 10000 | 512.73 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 15:25 | 15:36 | 0.18333 | 4737 | 4831 | 94 | Rotate |  | 4760 | 12.42 | 323.95 | 4677.32 | 541.85 | -322.33 | 541.85 | 0.17 |  |  | 40 | 80 | 900 | 10000 | 512.73 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 15:40 | 15:43 | 0.05 | 4831 | 4840 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 180 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 15:43 | 15:53 | 0.16667 | 4840 | 4860 | 20 | Slide | 0 | 4854 | 13.85 | 321.45 | 4768.86 | 558.82 | -335.29 | 558.82 | 1.64 |  |  | 18 |  | 900 |  | 120 | 4700 | 4500 | 200 | 170 | 200 | 170 | 145
01/18/2021 | 15:53 | 15:59 | 0.1 | 4860 | 4925 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 650 | 5100 | 4500 | 600 | 170 | 200 | 170 | 145
01/18/2021 | 16:04 | 16:12 | 0.13333 | 4925 | 5019 | 94 | Rotate |  | 4948 | 15.09 | 320.65 | 4859.87 | 577.09 | -350.06 | 577.09 | 1.34 |  |  | 40 | 80 | 900 | 13500 | 705 | 5100 | 4500 | 600 | 181 | 200 | 170 | 145
01/18/2021 | 16:15 | 16:26 | 0.18333 | 5019 | 5113 | 94 | Rotate |  | 5042 | 14.95 | 320.38 | 4950.66 | 595.89 | -365.55 | 595.89 | 0.17 |  |  | 40 | 80 | 900 | 13500 | 512.73 | 5100 | 4500 | 600 | 181 | 200 | 170 | 145
01/18/2021 | 16:30 | 16:38 | 0.13333 | 5113 | 5207 | 94 | Rotate |  | 5136 | 14.6 | 319.1 | 5041.55 | 614.18 | -381.04 | 614.18 | 0.51 |  |  | 40 | 80 | 900 | 13500 | 705 | 5100 | 4500 | 600 | 181 | 200 | 170 | 145
01/18/2021 | 16:43 | 16:52 | 0.15 | 5207 | 5301 | 94 | Rotate |  | 5230 | 14.6 | 317.44 | 5132.52 | 631.86 | -396.81 | 631.86 | 0.45 |  |  | 40 | 80 | 900 | 10000 | 626.67 | 5100 | 4500 | 600 |  | 200 | 170 | 145
01/18/2021 | 16:56 | 17:13 | 0.28333 | 5301 | 5396 | 95 | Rotate |  | 5325 | 14.85 | 315.46 | 5224.4 | 649.36 | -413.44 | 649.36 | 0.59 |  |  | 40 | 80 | 900 | 10000 | 335.29 | 5100 | 4500 | 600 | 181 | 200 | 170 | 145
01/18/2021 | 17:57 | 18:16 | 0.31667 | 5396 | 5490 | 94 | Rotate |  | 5419 | 15.22 | 314.35 | 5315.18 | 666.57 | -430.71 | 666.57 | 0.5 |  |  | 40 | 80 | 900 | 10000 | 296.84 | 5100 | 4500 | 600 | 181 | 200 | 170 | 145
01/18/2021 | 18:25 | 18:36 | 0.18333 | 5490 | 5583 | 93 | Rotate |  | 5512 | 15.48 | 312.47 | 5404.86 | 683.48 | -448.6 | 683.48 | 0.6 |  |  | 40 | 80 | 674 | 15000 | 507.27 | 3200 | 2850 | 350 | 181 | 200 | 170 | 145
01/18/2021 | 18:42 | 18:48 | 0.1 | 5583 | 5592 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 674; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 90 | 3200 | 2850 | 350 | 181 | 200 | 170 | 145
01/18/2021 | 18:48 | 19:00 | 0.2 | 5592 | 5608 | 16 | Slide | 0 | 5607 | 14.1 | 314.15 | 5496.71 | 700.11 | -466.25 | 700.11 | 1.52 |  |  | 12 |  | 674 |  | 80 | 2950 | 2850 | 100 | 181 | 200 | 170 | 145
01/18/2021 | 19:00 | 19:10 | 0.16667 | 5608 | 5678 | 70 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 674; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 420 | 3200 | 2850 | 350 | 181 | 200 | 170 | 145
01/18/2021 | 19:13 | 19:26 | 0.21667 | 5678 | 5772 | 94 | Rotate |  | 5701 | 13.68 | 314.96 | 5587.97 | 715.94 | -482.34 | 715.94 | 0.49 |  |  | 40 | 80 | 674 | 15000 | 433.85 | 3200 | 2850 | 350 | 181 | 200 | 170 | 145
01/18/2021 | 19:31 | 19:46 | 0.25 | 5772 | 5788 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 674; Drilling Parameters ROP: 64 | 3200 | 2850 | 350 | 181 | 200 | 170 | 145
01/18/2021 | 19:46 | 19:58 | 0.2 | 5788 | 5866 | 78 | Rotate |  | 5795 | 12.73 | 319.47 | 5679.48 | 731.66 | -496.93 | 731.66 | 1.49 |  |  | 40 | 80 | 900 | 17500 | 390 | 5100 | 4500 | 600 | 182 | 200 | 170 | 145
01/18/2021 | 20:02 | 20:23 | 0.35 | 5866 | 5959 | 93 | Rotate |  | 5888 | 12.95 | 319.5 | 5770.16 | 747.37 | -510.36 | 747.37 | 0.24 |  |  | 40 | 80 | 900 | 17500 | 265.71 | 5100 | 4500 | 600 | 182 | 200 | 170 | 145
01/18/2021 | 20:27 | 20:36 | 0.15 | 5959 | 6052 | 93 | Rotate |  | 5982 | 12.14 | 318.99 | 5861.91 | 762.84 | -523.68 | 762.84 | 0.87 |  |  | 40 | 80 | 674 | 17500 | 620 | 3200 | 2850 | 350 | 182 | 200 | 170 | 145
01/18/2021 | 21:14 | 21:15 | 0.016667 | 6052 | 6053 | 1 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 674; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 60 | 3200 | 2850 | 350 | 182 | 200 | 170 | 145
01/18/2021 | 21:20 | 21:21 | 0.016667 | 6053 | 6060 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 674; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 420 | 3200 | 2850 | 350 | 182 | 200 | 170 | 145
01/18/2021 | 21:21 | 21:36 | 0.25 | 6060 | 6078 | 18 | Slide | 0 | 6077 | 14.09 | 319.94 | 5954.43 | 779.23 | -537.68 | 779.23 | 2.07 |  |  | 40 |  | 674 |  | 72 | 3000 | 2850 | 150 | 182 | 200 | 170 | 145
01/18/2021 | 21:36 | 21:44 | 0.13333 | 6078 | 6148 | 70 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 674; Drilling Parameters Tq: 17500; Drilling Parameters ROP: 525 | 3200 | 2850 | 350 | 182 | 200 | 170 | 145
01/18/2021 | 22:00 | 22:19 | 0.31667 | 6148 | 6242 | 94 | Rotate |  | 6171 | 13.62 | 319.07 | 6045.69 | 796.35 | -552.3 | 796.35 | 0.55 |  |  | 40 | 80 | 900 | 17500 | 296.84 | 5100 | 4500 | 600 | 182 | 200 | 170 | 145
01/18/2021 | 22:24 | 22:38 | 0.23333 | 6242 | 6336 | 94 | Rotate |  | 6265 | 12.61 | 318.85 | 6137.24 | 812.44 | -566.3 | 812.44 | 1.08 |  |  | 40 | 80 | 900 | 18000 | 402.86 | 5100 | 4500 | 600 | 182 | 200 | 170 | 145
01/18/2021 | 22:41 | 22:43 | 0.033333 | 6336 | 6345 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 270 | 5100 | 4500 | 600 | 182 | 200 | 170 | 145
01/18/2021 | 22:43 | 23:11 | 0.46667 | 6345 | 6363 | 18 | Slide | 0 | 6360 | 12.47 | 317.02 | 6229.97 | 827.75 | -580.12 | 827.75 | 0.44 |  |  | 18 |  | 900 |  | 38.57 | 4700 | 4500 | 200 | 190 | 235 | 190 | 155
01/18/2021 | 23:11 | 23:25 | 0.23333 | 6363 | 6431 | 68 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 291.43 | 5100 | 4500 | 600 | 190 | 235 | 190 | 155
01/18/2021 | 23:32 | 23:56 | 0.4 | 6431 | 6449 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 45 | 4700 | 4500 | 200 | 194 | 235 | 190 | 155
01/18/2021 | 23:56 | 24:00 | 0.066667 | 6449 | 6459 | 10 | Rotate |  | 6454 | 13.6 | 321.68 | 6321.55 | 843.85 | -593.89 | 843.85 | 1.64 |  |  | 40 | 80 | 900 | 18000 | 150 | 5100 | 4500 | 600 | 194 | 235 | 190 | 155
01/19/2021 | 00:00 | 00:25 | 0.41667 | 6459 | 6525 | 66 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 158.4 | 5100 | 4500 | 600 | 194 | 235 | 190 | 155
01/19/2021 | 00:30 | 00:31 | 0.016667 | 6525 | 6528 | 3 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 180 | 5100 | 4500 | 600 | 194 | 235 | 190 | 155
01/19/2021 | 00:31 | 00:55 | 0.4 | 6528 | 6544 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 40 | 4900 | 4800 | 100 | 194 | 235 | 190 | 155
01/19/2021 | 00:55 | 01:06 | 0.18333 | 6544 | 6619 | 75 | Rotate |  | 6548 | 15.1 | 321.89 | 6412.62 | 862.15 | -608.3 | 862.15 | 1.6 |  |  | 40 | 80 | 900 | 19000 | 409.09 | 5500 | 4800 | 700 | 194 | 235 | 190 | 155
01/19/2021 | 01:08 | 01:25 | 0.28333 | 6619 | 6713 | 94 | Rotate |  | 6642 | 15.07 | 321.3 | 6503.38 | 881.32 | -623.5 | 881.32 | 0.17 |  |  | 40 | 80 | 900 | 19000 | 331.76 | 5500 | 4800 | 700 | 194 | 235 | 190 | 155
01/19/2021 | 01:28 | 01:43 | 0.25 | 6713 | 6806 | 93 | Rotate |  | 6735 | 14.25 | 319.29 | 6593.35 | 899.44 | -638.52 | 899.44 | 1.04 |  |  | 40 | 80 | 900 | 19000 | 372 | 5500 | 4800 | 700 | 194 | 235 | 190 | 155
01/19/2021 | 01:46 | 01:57 | 0.18333 | 6806 | 6900 | 94 | Rotate |  | 6829 | 13.39 | 318.36 | 6684.63 | 916.34 | -653.3 | 916.34 | 0.94 |  |  | 40 | 80 | 900 | 19000 | 512.73 | 5500 | 4800 | 700 | 194 | 235 | 190 | 155
01/19/2021 | 02:04 | 02:08 | 0.066667 | 6900 | 6910 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 150 | 5500 | 4800 | 700 | 194 | 235 | 190 | 155
01/19/2021 | 02:08 | 02:25 | 0.28333 | 6910 | 6926 | 16 | Slide | 0 | 6923 | 14.16 | 319.81 | 6775.93 | 933.26 | -667.95 | 933.26 | 0.9 |  |  | 15 |  | 900 |  | 56.47 | 5100 | 4800 | 300 | 194 | 235 | 190 | 155
01/19/2021 | 02:25 | 02:39 | 0.23333 | 6926 | 6994 | 68 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 291.43 | 5500 | 4800 | 700 | 194 | 235 | 190 | 155
01/19/2021 | 02:42 | 02:55 | 0.21667 | 6994 | 7087 | 93 | Rotate |  | 7016 | 13.95 | 321.21 | 6866.14 | 950.69 | -682.31 | 950.69 | 0.43 |  |  | 40 | 80 | 900 | 19000 | 429.23 | 5500 | 4800 | 700 | 198 | 235 | 190 | 155
01/19/2021 | 02:58 | 03:11 | 0.21667 | 7087 | 7181 | 94 | Rotate |  | 7110 | 13.19 | 320.87 | 6957.52 | 967.84 | -696.18 | 967.84 | 0.81 |  |  | 40 | 80 | 900 | 19000 | 433.85 | 5500 | 5000 | 500 | 198 | 235 | 190 | 155
01/19/2021 | 03:16 | 03:38 | 0.36667 | 7181 | 7199 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 674; Drilling Parameters ROP: 49.09 | 3400 | 3200 | 200 | 198 | 235 | 190 | 155
01/19/2021 | 03:38 | 03:52 | 0.23333 | 7199 | 7275 | 76 | Rotate |  | 7204 | 14.43 | 320.64 | 7048.8 | 985.21 | -710.38 | 985.21 | 1.32 |  |  | 35 | 80 | 674 | 19000 | 325.71 | 3800 | 3200 | 600 | 198 | 235 | 190 | 155
01/19/2021 | 03:55 | 04:13 | 0.3 | 7275 | 7369 | 94 | Rotate |  | 7298 | 13.66 | 321.02 | 7139.99 | 1002.9 | -724.79 | 1002.9 | 0.82 |  |  | 35 | 80 | 674 | 19000 | 313.33 | 3800 | 3200 | 600 | 208 | 235 | 190 | 155
01/19/2021 | 04:15 | 04:18 | 0.05 | 7369 | 7375 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 5500 | 5000 | 500 | 208 | 250 | 210 | 170
01/19/2021 | 04:18 | 04:30 | 0.2 | 7375 | 7391 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 22; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 80 | 5200 | 5000 | 200 | 208 | 250 | 210 | 170
01/19/2021 | 04:30 | 04:43 | 0.21667 | 7391 | 7463 | 72 | Rotate |  | 7392 | 14.12 | 320.34 | 7231.24 | 1020.35 | -739.09 | 1020.35 | 0.52 |  |  | 40 | 80 | 900 | 20000 | 332.31 | 5500 | 5000 | 500 | 208 | 250 | 210 | 170
01/19/2021 | 04:46 | 04:59 | 0.21667 | 7463 | 7558 | 95 | Rotate |  | 7487 | 13.54 | 319.48 | 7323.48 | 1037.73 | -753.71 | 1037.73 | 0.65 |  |  | 40 | 80 | 900 | 20000 | 438.46 | 5500 | 5000 | 500 | 208 | 250 | 210 | 170
01/19/2021 | 05:01 | 05:04 | 0.05 | 7558 | 7564 | 6 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 5500 | 5000 | 500 | 208 | 250 | 210 | 170
01/19/2021 | 05:04 | 05:25 | 0.35 | 7564 | 7582 | 18 | Slide | 0 | 7580 | 13.36 | 318.35 | 7413.93 | 1054.03 | -767.92 | 1054.03 | 0.34 |  |  | 22 |  | 900 |  | 51.43 | 5200 | 5000 | 200 | 208 | 250 | 210 | 170
01/19/2021 | 05:25 | 05:36 | 0.18333 | 7582 | 7651 | 69 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 376.36 | 5500 | 5000 | 500 | 208 | 250 | 210 | 170
01/19/2021 | 05:40 | 05:52 | 0.2 | 7651 | 7745 | 94 | Rotate |  | 7674 | 12.47 | 317.14 | 7505.55 | 1069.59 | -782.04 | 1069.59 | 0.99 |  |  | 40 | 80 | 900 | 20000 | 470 | 5500 | 5000 | 500 | 208 | 250 | 210 | 170
01/19/2021 | 06:32 | 07:17 | 0.75 | 7745 | 7775 | 30 | Slide | 0 | 7768 | 12.32 | 311.61 | 7597.37 | 1083.68 | -796.45 | 1083.68 | 1.27 |  |  | 22 |  | 674 |  | 40 | 3400 | 3200 | 200 | 208 | 275 | 230 | 185
01/19/2021 | 07:17 | 07:45 | 0.46667 | 7775 | 7839 | 64 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 674; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 137.14 | 3850 | 3200 | 650 | 208 | 275 | 230 | 185
01/19/2021 | 08:00 | 08:40 | 0.66667 | 7839 | 7870 | 31 | Slide | 0 | 7862 | 13.19 | 314.01 | 7689.05 | 1097.8 | -811.66 | 1097.8 | 1.08 |  |  | 22 |  | 900 |  | 46.5 | 5250 | 5000 | 250 | 215 | 275 | 230 | 185
01/19/2021 | 08:40 | 08:52 | 0.2 | 7870 | 7933 | 63 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 315 | 5800 | 5000 | 800 | 215 | 275 | 230 | 185
01/19/2021 | 08:59 | 09:13 | 0.23333 | 7933 | 8027 | 94 | Rotate |  | 7956 | 12.13 | 314.95 | 7780.76 | 1112.22 | -826.36 | 1112.22 | 1.15 |  |  | 40 | 80 | 900 | 20000 | 402.86 | 5800 | 5000 | 800 | 215 | 275 | 230 | 185
01/19/2021 | 09:18 | 09:22 | 0.066667 | 8027 | 8035 | 8 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 120 | 5800 | 5000 | 800 | 215 | 275 | 230 | 185
01/19/2021 | 09:22 | 09:46 | 0.4 | 8035 | 8070 | 35 | Slide | 0 | 8050 | 12.6 | 316.22 | 7872.58 | 1126.6 | -840.44 | 1126.6 | 0.58 |  |  | 22 |  | 900 |  | 87.5 | 5250 | 5000 | 250 | 215 | 275 | 230 | 185
01/19/2021 | 09:46 | 09:56 | 0.16667 | 8070 | 8121 | 51 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 306 | 5800 | 5000 | 800 | 215 | 275 | 230 | 185
01/19/2021 | 10:00 | 10:31 | 0.51667 | 8121 | 8215 | 94 | Rotate |  | 8144 | 12.84 | 318.82 | 7964.27 | 1141.87 | -854.42 | 1141.87 | 0.66 |  |  | 40 | 80 | 900 | 20000 | 181.94 | 5800 | 5000 | 800 | 215 | 275 | 230 | 185
01/19/2021 | 10:35 | 10:54 | 0.31667 | 8215 | 8309 | 94 | Rotate |  | 8238 | 11.84 | 319.05 | 8056.1 | 1157.01 | -867.61 | 1157.01 | 1.07 |  |  | 40 | 80 | 800 | 20000 | 296.84 | 4950 | 4300 | 650 | 215 | 275 | 230 | 185
01/19/2021 | 11:00 | 11:16 | 0.26667 | 8309 | 8402 | 93 | Rotate |  | 8331 | 10.25 | 317.74 | 8147.37 | 1170.34 | -879.43 | 1170.34 | 1.73 |  |  | 40 | 80 | 800 | 20000 | 348.75 | 4950 | 4300 | 650 | 215 | 275 | 230 | 185
01/19/2021 | 11:20 | 11:50 | 0.5 | 8402 | 8495 | 93 | Rotate |  | 8424 | 9.33 | 317.37 | 8239.02 | 1182.01 | -890.1 | 1182.01 | 0.99 |  |  | 40 | 80 | 800 | 20000 | 186 | 4950 | 4300 | 650 | 221 | 275 | 230 | 185
01/19/2021 | 11:54 | 12:08 | 0.23333 | 8495 | 8589 | 94 | Rotate |  | 8518 | 8.35 | 315.9 | 8331.9 | 1192.52 | -900.01 | 1192.52 | 1.07 |  |  | 40 | 80 | 800 | 20000 | 402.86 | 4950 | 4300 | 650 | 221 | 275 | 230 | 185
01/19/2021 | 12:13 | 12:26 | 0.21667 | 8589 | 8683 | 94 | Rotate |  | 8612 | 7.69 | 320.17 | 8424.98 | 1202.25 | -908.79 | 1202.25 | 0.95 |  |  | 40 | 80 | 800 | 20000 | 433.85 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 12:30 | 12:44 | 0.23333 | 8683 | 8776 | 93 | Rotate |  | 8705 | 7.86 | 323.81 | 8517.13 | 1212.16 | -916.53 | 1212.16 | 0.56 |  |  | 40 | 80 | 800 | 20000 | 398.57 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 12:50 | 12:55 | 0.083333 | 8776 | 8785 | 9 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 108 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 12:55 | 13:26 | 0.51667 | 8785 | 8805 | 20 | Slide | 0 | 8799 | 7.93 | 317.42 | 8610.24 | 1222.13 | -924.71 | 1222.13 | 0.94 |  |  | 18 |  | 800 |  | 38.71 | 4600 | 4300 | 300 | 224 | 300 | 245 | 180
01/19/2021 | 13:26 | 13:35 | 0.15 | 8805 | 8870 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 433.33 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 13:40 | 14:24 | 0.73333 | 8870 | 8907 | 37 | Slide | 0 | 8893 | 5.73 | 317.49 | 8703.57 | 1230.36 | -932.27 | 1230.36 | 2.34 |  |  | 18 |  | 800 |  | 50.45 | 4600 | 4300 | 300 | 224 | 300 | 245 | 180
01/19/2021 | 14:24 | 14:34 | 0.16667 | 8907 | 8964 | 57 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 342 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 14:40 | 15:06 | 0.43333 | 8964 | 8984 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 46.15 | 4600 | 4300 | 300 | 224 | 300 | 245 | 180
01/19/2021 | 15:06 | 15:17 | 0.18333 | 8984 | 9058 | 74 | Rotate |  | 8987 | 2.69 | 321.03 | 8797.3 | 1235.54 | -936.83 | 1235.54 | 3.24 |  |  | 40 | 80 | 800 | 20000 | 403.64 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 15:20 | 15:36 | 0.26667 | 9058 | 9152 | 94 | Rotate |  | 9081 | 2.63 | 304.3 | 8891.2 | 1238.47 | -940 | 1238.47 | 0.83 |  |  | 40 | 80 | 800 | 20000 | 352.5 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 15:40 | 15:55 | 0.25 | 9152 | 9245 | 93 | Rotate |  | 9174 | 2.49 | 298.62 | 8984.11 | 1240.64 | -943.54 | 1240.64 | 0.31 |  |  | 40 | 80 | 800 | 20000 | 372 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 16:00 | 16:16 | 0.26667 | 9245 | 9339 | 94 | Rotate |  | 9268 | 2.41 | 299.98 | 9078.02 | 1242.6 | -947.04 | 1242.6 | 0.11 |  |  | 40 | 80 | 800 | 20000 | 352.5 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 16:20 | 16:23 | 0.05 | 9339 | 9350 | 11 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 220 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 16:23 | 16:42 | 0.31667 | 9350 | 9375 | 25 | Slide | 0 | 9362 | 0.91 | 319.62 | 9171.98 | 1244.16 | -949.24 | 1244.16 | 1.68 |  |  | 26 |  | 800 |  | 78.95 | 4550 | 4300 | 250 | 224 | 300 | 245 | 180
01/19/2021 | 16:42 | 16:54 | 0.2 | 9375 | 9443 | 68 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 340 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 17:00 | 17:28 | 0.46667 | 9443 | 9528 | 85 | Rotate |  | 9457 | 0.4 | 302.98 | 9266.98 | 1244.91 | -950 | 1244.91 | 0.57 |  |  | 40 | 80 | 800 | 20000 | 182.14 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 17:32 | 18:19 | 0.78333 | 9528 | 9622 | 94 | Rotate |  | 9551 | 0.72 | 257.8 | 9360.97 | 1244.97 | -950.86 | 1244.97 | 0.56 |  |  | 40 | 80 | 800 | 20000 | 120 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/19/2021 | 18:23 | 18:55 | 0.53333 | 9622 | 9642 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 20; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 37.5 | 4650 | 4300 | 350 | 224 | 300 | 245 | 180
01/19/2021 | 18:55 | 22:45 | 3.8333 | 9642 | 9783 | 141 | Rotate |  | 9645 | 0.02 | 262.97 | 9454.97 | 1244.84 | -951.45 | 1244.84 | 0.74 |  |  | 40 | 80 | 800 | 20000 | 36.78 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/20/2021 | 00:10 | 00:18 | 0.13333 | 9783 | 9810 | 27 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 202.5 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/20/2021 | 00:21 | 00:24 | 0.05 | 9810 | 9826 | 16 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 800; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 320 | 4950 | 4300 | 650 | 224 | 300 | 245 | 180
01/20/2021 | 03:10 | 03:37 | 0.45 | 9826 | 9904 | 78 | Rotate |  | 9833 | 0.34 | 254.27 | 9642.97 | 1244.69 | -951.8 | 1244.69 | 0.31 |  |  | 35 | 80 | 800 | 20000 | 173.33 | 5100 | 4500 | 600 | 225 | 345 | 255 | 200

## BHA_3_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 3 |  |  |  |  | RKB: |  |  |  | 487 |  | North Reference: |  | GRID |  | Total Drilled: |  | 267
Site: |  |  |  |  | Sabine - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 149
Well Name: |  |  |  |  | Sabine D 4H |  |  | Survey / Gamma Offset: |  |  |  |  | 71.00 / 61.00 |  |  |  |  | Grid Conv: |  |  |  | 487 |  | VS Azimuth: |  | 136.56 |  | Rotate: |  | 118
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
01/20/2021 | 15:50 | 18:12 | 2.3667 | 9904 | 9998 | 94 | Slide | 0 | 9927 | 0.7 | 162.6 | 9736.97 | 1244.07 | -951.9 | 1244.07 | 0.84 |  |  | 18 |  | 675 | 5000 | 39.72 | 3950 | 3650 | 300 | 225 | 320 | 250 | 190
01/20/2021 | 18:18 | 18:26 | 0.13333 | 9998 | 10008 | 10 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 675; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 75 | 4300 | 3650 | 650 | 225 | 320 | 250 | 190
01/20/2021 | 18:26 | 19:55 | 1.4833 | 10008 | 10063 | 55 | Slide | 0 | 10022 | 8.2 | 145.7 | 9831.61 | 1237.91 | -947.9 | 1237.91 | 7.93 |  |  | 18 |  | 675 | 5000 | 37.08 | 3950 | 3650 | 300 | 225 | 320 | 250 | 190
01/20/2021 | 19:55 | 20:11 | 0.26667 | 10063 | 10093 | 30 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 50; Drilling Parameters FLOW: 675; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 112.5 | 4300 | 3650 | 650 | 225 | 320 | 250 | 190
01/20/2021 | 20:18 | 21:14 | 0.93333 | 10093 | 10171 | 78 | Rotate |  | 10100 | 10.8 | 147.2 | 9908.54 | 1227.17 | -940.81 | 1227.17 | 3.35 |  |  | 18 | 50 | 675 | 21000 | 83.57 | 4300 | 3650 | 650 | 225 | 320 | 250 | 190

## BHA_4_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 4 |  |  |  |  | RKB: |  |  |  | 487 |  | North Reference: |  | GRID |  | Total Drilled: |  | 749
Site: |  |  |  |  | Sabine - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 516
Well Name: |  |  |  |  | Sabine D 4H |  |  | Survey / Gamma Offset: |  |  |  |  | 67.00 / 58.00 |  |  |  |  | Grid Conv: |  |  |  | 487 |  | VS Azimuth: |  | 136.56 |  | Rotate: |  | 233
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
03/13/2021 | 05:10 | 05:12 | 0.033333 | 10171 | 10181 | 10 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 250; Drilling Parameters Tq: 10000; Drilling Parameters ROP: 300 | 2100 | 1995 | 105 | 98 | 185 | 180 | 175 | Drill 10 For FIT
03/13/2021 | 06:30 | 09:30 | 3 | 10181 | 10257 | 76 | Slide | 0 | 10190 | 10.23 | 148.13 | 9997.02 | 1213.29 | -932.02 | 1213.29 | 0.66 |  |  | 35 |  | 350 |  | 25.33 | 3400 | 2830 | 570 | 224 | 210 | 180 | 140
03/13/2021 | 09:40 | 11:15 | 1.5833 | 10257 | 10352 | 95 | Slide | 0 | 10285 | 21.74 | 141.6 | 10088.2 | 1192.27 | -916.58 | 1192.27 | 12.24 |  |  | 35 |  | 350 |  | 60 | 3400 | 2830 | 570 | 224 | 210 | 180 | 140
03/13/2021 | 11:25 | 11:50 | 0.41667 | 10352 | 10387 | 35 | Rotate |  | 10380 | 30.83 | 135.54 | 10173.31 | 1161.03 | -888.54 | 1161.03 | 9.97 |  |  | 35 | 30 | 350 | 13000 | 84 | 3700 | 2830 | 870 | 224 | 250 | 205 | 170
03/13/2021 | 11:50 | 12:46 | 0.93333 | 10387 | 10447 | 60 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 350; Drilling Parameters ROP: 64.29 | 3400 | 2830 | 570 | 224 | 250 | 205 | 170
03/13/2021 | 12:56 | 13:25 | 0.48333 | 10447 | 10497 | 50 | Rotate |  | 10474 | 36.71 | 135.57 | 10251.41 | 1123.75 | -851.97 | 1123.75 | 6.26 |  |  | 35 | 30 | 350 | 13000 | 103.45 | 3700 | 2830 | 870 | 224 | 250 | 205 | 170
03/13/2021 | 13:25 | 13:47 | 0.36667 | 10497 | 10541 | 44 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 120 | 4100 | 3500 | 600 | 224 | 250 | 205 | 170
03/13/2021 | 13:57 | 15:14 | 1.2833 | 10541 | 10636 | 95 | Slide | 0 | 10569 | 42.31 | 133.84 | 10324.68 | 1081.29 | -809 | 1081.29 | 6.01 |  |  | 35 |  | 400 |  | 74.03 | 4100 | 3500 | 600 | 224 | 250 | 205 | 170
03/13/2021 | 15:24 | 16:09 | 0.75 | 10636 | 10697 | 61 | Slide | 0 | 10663 | 53.34 | 133.63 | 10387.69 | 1033.21 | -758.73 | 1033.21 | 11.74 |  |  | 45 |  | 400 |  | 81.33 | 4100 | 3500 | 600 | 244 | 250 | 205 | 170
03/13/2021 | 16:19 | 16:28 | 0.15 | 10697 | 10730 | 33 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 220 | 4400 | 3500 | 900 | 244 | 250 | 205 | 170
03/13/2021 | 16:38 | 16:58 | 0.33333 | 10730 | 10800 | 70 | Rotate |  | 10758 | 61.23 | 135.83 | 10439 | 976.96 | -702.04 | 976.96 | 8.53 |  |  | 35 | 30 | 400 | 15000 | 210 | 4400 | 3500 | 900 | 244 | 250 | 205 | 170
03/13/2021 | 17:08 | 17:28 | 0.33333 | 10800 | 10825 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 75 | 4100 | 3500 | 600 | 244 | 250 | 205 | 170
03/13/2021 | 17:28 | 17:52 | 0.4 | 10825 | 10860 | 35 | Rotate |  | 10853 | 61.59 | 135.73 | 10484.46 | 917.18 | -643.87 | 917.18 | 0.39 |  |  | 45 |  | 400 |  | 87.5 | 4100 | 3500 | 600 | 244 | 250 | 205 | 170
03/13/2021 | 17:52 | 19:40 | 1.8 | 10860 | 10920 | 60 | Slide | TTF: 0; Drilling Parameters WOB: 45; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 33.33 | 4100 | 3500 | 600 | 244 | 250 | 205 | 170

## BHA_5_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 5 |  |  |  |  | RKB: |  |  |  | 487 |  | North Reference: |  | GRID |  | Total Drilled: |  | 4289
Site: |  |  |  |  | Sabine - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 779
Well Name: |  |  |  |  | Sabine D 4H |  |  | Survey / Gamma Offset: |  |  |  |  | 67.00 / 58.00 |  |  |  |  | Grid Conv: |  |  |  | 487 |  | VS Azimuth: |  | 136.56 |  | Rotate: |  | 3510
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
03/15/2021 | 04:50 | 05:05 | 0.25 | 10920 | 10940 | 20 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 80 | 4400 | 3600 | 800 | 248 | 280 | 215 | 190
03/15/2021 | 05:05 | 05:46 | 0.68333 | 10940 | 11000 | 60 | Slide | 0 | 10948 | 66.06 | 130.01 | 10526.39 | 859.28 | -581.38 | 859.28 | 7.16 |  |  | 35 |  | 400 |  | 87.8 | 4400 | 3600 | 800 | 248 | 280 | 215 | 190
03/15/2021 | 05:46 | 05:56 | 0.16667 | 11000 | 11015 | 15 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 90 | 4400 | 3600 | 800 | 248 | 280 | 215 | 190
03/15/2021 | 06:06 | 06:10 | 0.066667 | 11015 | 11025 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 150 | 4400 | 3600 | 800 | 248 | 280 | 215 | 190
03/15/2021 | 06:10 | 06:57 | 0.78333 | 11025 | 11109 | 84 | Slide | 0 | 11042 | 74.19 | 135.3 | 10558.34 | 799.38 | -516.52 | 799.38 | 10.14 |  |  | 50 |  | 400 |  | 107.23 | 4400 | 3600 | 800 | 248 | 280 | 215 | 190
03/15/2021 | 07:07 | 07:43 | 0.6 | 11109 | 11203 | 94 | Rotate |  | 11136 | 83.67 | 140.77 | 10576.38 | 730.85 | -454.98 | 730.85 | 11.59 |  |  | 35 | 30 | 400 | 13500 | 156.67 | 4400 | 3600 | 800 | 248 | 280 | 215 | 190
03/15/2021 | 07:53 | 08:20 | 0.45 | 11203 | 11243 | 40 | Slide | 0 | 11230 | 86.14 | 137.11 | 10584.73 | 660.27 | -393.49 | 660.27 | 4.68 |  |  | 50 |  | 400 |  | 88.89 | 4000 | 3600 | 400 | 253 | 280 | 215 | 190
03/15/2021 | 08:20 | 08:39 | 0.31667 | 11243 | 11297 | 54 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 30; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 13500; Drilling Parameters ROP: 170.53 | 4400 | 3600 | 800 | 253 | 280 | 215 | 190
03/15/2021 | 08:49 | 09:15 | 0.43333 | 11297 | 11391 | 94 | Rotate |  | 11324 | 86.22 | 135.17 | 10590.99 | 592.65 | -328.51 | 592.65 | 2.06 |  |  | 35 | 30 | 400 | 13500 | 216.92 | 4400 | 3600 | 800 | 253 | 280 | 215 | 190
03/15/2021 | 09:25 | 09:50 | 0.41667 | 11391 | 11486 | 95 | Rotate |  | 11419 | 85.59 | 135.57 | 10597.77 | 525.21 | -261.94 | 525.21 | 0.78 |  |  | 43 | 80 | 400 | 14000 | 228 | 4400 | 3600 | 800 | 253 | 280 | 215 | 190
03/15/2021 | 10:00 | 10:03 | 0.05 | 11486 | 11496 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 200 | 4400 | 3600 | 800 | 253 | 280 | 215 | 190
03/15/2021 | 10:03 | 10:12 | 0.15 | 11496 | 11514 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 120 | 4400 | 3600 | 800 | 253 | 280 | 215 | 190
03/15/2021 | 10:12 | 10:34 | 0.36667 | 11514 | 11581 | 67 | Rotate |  | 11514 | 87.86 | 135.1 | 10603.2 | 457.76 | -195.27 | 457.76 | 2.44 |  |  | 43 | 80 | 400 | 14000 | 182.73 | 4400 | 3600 | 800 | 253 | 280 | 215 | 190
03/15/2021 | 10:44 | 11:02 | 0.3 | 11581 | 11676 | 95 | Rotate |  | 11609 | 88.95 | 135.23 | 10605.85 | 390.42 | -128.32 | 390.42 | 1.16 |  |  | 43 | 80 | 400 | 14000 | 316.67 | 4400 | 3600 | 800 | 269 | 280 | 215 | 190
03/15/2021 | 11:12 | 11:14 | 0.033333 | 11676 | 11686 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 300 | 4400 | 3600 | 800 | 269 | 280 | 215 | 190
03/15/2021 | 11:14 | 11:26 | 0.2 | 11686 | 11698 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 4400 | 3600 | 800 | 269 | 280 | 215 | 190
03/15/2021 | 11:26 | 11:48 | 0.36667 | 11698 | 11771 | 73 | Rotate |  | 11704 | 87.62 | 136.42 | 10608.69 | 322.32 | -62.15 | 322.32 | 1.88 |  |  | 43 | 80 | 400 | 14000 | 199.09 | 4400 | 3600 | 800 | 269 | 280 | 215 | 190
03/15/2021 | 11:58 | 12:15 | 0.28333 | 11771 | 11865 | 94 | Rotate |  | 11798 | 87.08 | 136.55 | 10613.03 | 254.22 | 2.51 | 254.22 | 0.59 |  |  | 43 | 80 | 400 | 14000 | 331.76 | 4400 | 3600 | 800 | 269 | 280 | 215 | 190
03/15/2021 | 12:25 | 12:38 | 0.21667 | 11865 | 11960 | 95 | Rotate |  | 11893 | 87.17 | 137.21 | 10617.8 | 184.97 | 67.36 | 184.97 | 0.7 |  |  | 43 | 80 | 400 | 14000 | 438.46 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 12:48 | 13:07 | 0.31667 | 11960 | 12054 | 94 | Rotate |  | 11987 | 86.84 | 137.31 | 10622.71 | 116.03 | 131.07 | 116.03 | 0.37 |  |  | 43 | 80 | 400 | 14000 | 296.84 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 13:17 | 13:19 | 0.033333 | 12054 | 12064 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 300 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 13:19 | 13:37 | 0.3 | 12064 | 12079 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 50 | 4400 | 3600 | 800 | 273 | 300 | 215 | 170
03/15/2021 | 13:37 | 13:56 | 0.31667 | 12079 | 12150 | 71 | Rotate |  | 12083 | 89.03 | 136.92 | 10626.17 | 45.74 | 196.35 | 45.74 | 2.32 |  |  | 43 | 80 | 400 | 14000 | 224.21 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 14:06 | 14:21 | 0.25 | 12150 | 12247 | 97 | Rotate |  | 12180 | 90.24 | 136.82 | 10626.79 | -25.05 | 262.66 | -25.05 | 1.25 |  |  | 43 | 80 | 400 | 14000 | 388 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 14:31 | 14:33 | 0.033333 | 12247 | 12257 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 300 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 14:33 | 14:48 | 0.25 | 12257 | 12270 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 52 | 4400 | 3600 | 800 | 273 | 300 | 215 | 170
03/15/2021 | 14:48 | 15:08 | 0.33333 | 12270 | 12343 | 73 | Rotate |  | 12276 | 89.06 | 136.93 | 10627.37 | -95.12 | 328.29 | -95.12 | 1.23 |  |  | 43 | 80 | 400 | 14000 | 219 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 15:18 | 15:23 | 0.083333 | 12343 | 12353 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 120 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 15:23 | 15:30 | 0.11667 | 12353 | 12360 | 7 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 4400 | 3600 | 800 | 273 | 300 | 215 | 170
03/15/2021 | 15:30 | 15:50 | 0.33333 | 12360 | 12440 | 80 | Rotate |  | 12373 | 87.83 | 136.06 | 10630.01 | -165.44 | 395.04 | -165.44 | 1.55 |  |  | 43 | 80 | 400 | 14000 | 240 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 16:00 | 16:16 | 0.26667 | 12440 | 12537 | 97 | Rotate |  | 12470 | 89.04 | 136.42 | 10632.66 | -235.47 | 462.1 | -235.47 | 1.3 |  |  | 43 | 80 | 400 | 14000 | 363.75 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 16:26 | 16:30 | 0.066667 | 12537 | 12547 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 150 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 16:30 | 16:54 | 0.4 | 12547 | 12562 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 37.5 | 4400 | 3600 | 800 | 273 | 300 | 215 | 170
03/15/2021 | 16:54 | 17:50 | 0.93333 | 12562 | 12632 | 70 | Rotate |  | 12565 | 87.19 | 137.23 | 10635.78 | -304.71 | 527.06 | -304.71 | 2.13 |  |  | 43 | 80 | 400 | 14000 | 210 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 17:53 | 18:00 | 0.11667 | 12632 | 12642 | 10 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 85.71 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 18:00 | 18:26 | 0.43333 | 12642 | 12652 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 23.08 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170
03/15/2021 | 18:26 | 18:47 | 0.35 | 12652 | 12729 | 77 | Rotate |  | 12662 | 86.03 | 136.96 | 10641.52 | -375.64 | 592.98 | -375.64 | 1.23 |  |  | 43 | 80 | 400 | 14000 | 220 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 18:50 | 18:54 | 0.066667 | 12729 | 12729 |  | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 18:54 | 19:00 | 0.1 | 12729 | 12750 | 21 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 210 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 19:00 | 19:16 | 0.26667 | 12750 | 12760 | 10 | Slide | 0 | 12757 | 84.32 | 136.79 | 10649.51 | -444.73 | 657.69 | -444.73 | 1.81 |  |  | 43 | 80 | 400 | 9500 | 37.5 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170
03/15/2021 | 19:16 | 19:33 | 0.28333 | 12760 | 12824 | 64 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 225.88 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 19:35 | 20:10 | 0.58333 | 12824 | 12920 | 96 | Rotate |  | 12852 | 81.93 | 136.45 | 10660.88 | -513.27 | 722.46 | -513.27 | 2.54 |  |  | 43 | 80 | 400 | 14000 | 164.57 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 20:12 | 20:39 | 0.45 | 12920 | 12940 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 44.44 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170
03/15/2021 | 20:39 | 21:00 | 0.35 | 12940 | 13010 | 70 | Rotate |  | 12946 | 81.8 | 136.52 | 10674.18 | -580.76 | 786.54 | -580.76 | 0.16 |  |  | 43 | 80 | 400 | 14000 | 200 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 21:03 | 21:11 | 0.13333 | 13010 | 13015 | 5 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 37.5 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 21:11 | 22:18 | 1.1167 | 13015 | 13045 | 30 | Slide | 0 | 13041 | 82.89 | 136.77 | 10686.83 | -649.22 | 851.17 | -649.22 | 1.18 |  |  | 35 | 80 | 400 | 9500 | 26.87 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170
03/15/2021 | 22:18 | 22:35 | 0.28333 | 13045 | 13085 | 40 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 141.18 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/15/2021 | 22:35 | 23:20 | 0.75 | 13085 | 13105 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 26.67 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170 | Cont Inc While sliding was 12,927 81.7 End of slide Cont Inc 13,038 82.8 Result SD 13,041 82.89
03/15/2021 | 23:25 | 23:54 | 0.48333 | 13105 | 13120 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 31.03 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170
03/15/2021 | 23:54 | 24:00 | 0.1 | 13120 | 13140 | 20 | Rotate |  | 13136 | 87.9 | 137.29 | 10694.46 | -718.48 | 915.7 | -718.48 | 5.3 |  |  | 43 | 80 | 400 | 14000 | 200 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 00:00 | 00:09 | 0.15 | 13140 | 13155 | 15 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 100 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 00:09 | 00:42 | 0.55 | 13155 | 13168 | 13 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 23.64 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170 | Cont Inc during slide 13,091 84.8 End of Slide Cont Inc 13099 85.8 Porjected 88.5 for suvey. Result was SD 13,136 Inc 87.8 (This is not the slide for the survey, this is the slide cont inc was viewed)
03/16/2021 | 00:42 | 01:06 | 0.4 | 13168 | 13203 | 35 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 87.5 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 01:08 | 01:11 | 0.05 | 13203 | 13210 | 7 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 140 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 01:11 | 01:58 | 0.78333 | 13210 | 13230 | 20 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 25.53 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 01:58 | 02:31 | 0.55 | 13230 | 13299 | 69 | Rotate |  | 13232 | 92.34 | 135.99 | 10694.26 | -788.26 | 981.59 | -788.26 | 4.82 |  |  | 43 | 80 | 400 | 14000 | 125.45 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 02:33 | 02:46 | 0.21667 | 13299 | 13333 | 34 | Rotate |  | 13327 | 96.11 | 135.46 | 10687.26 | -856.08 | 1047.72 | -856.08 | 4.01 |  |  | 43 | 80 | 400 | 14000 | 156.92 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170 | Rotated 34 after survey and slid down, used cont inc in place of check shot
03/16/2021 | 02:46 | 03:34 | 0.8 | 13333 | 13345 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 9500; Drilling Parameters ROP: 15 | 3950 | 3600 | 350 | 273 | 300 | 215 | 170 | Cont Inc at start of slide 13,266 Sensor 92.8 End of slide 13,278 93.8
03/16/2021 | 03:34 | 04:08 | 0.56667 | 13345 | 13394 | 49 | Rotate | Drilling Parameters WOB: 43; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 14000; Drilling Parameters ROP: 86.47 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 04:10 | 06:32 | 2.3667 | 13394 | 13424 | 30 | Slide | 0 | 13423 | 92.78 | 135.17 | 10679.82 | -924.12 | 1115.01 | -924.12 | 3.48 |  |  | 43 | 80 | 400 | 14000 | 12.68 | 4650 | 3600 | 1050 | 266 | 300 | 215 | 170
03/16/2021 | 06:32 | 06:44 | 0.2 | 13424 | 13457 | 33 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 165 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 06:50 | 07:34 | 0.73333 | 13457 | 13472 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 20.45 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 07:34 | 07:43 | 0.15 | 13472 | 13490 | 18 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 120 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 07:53 | 07:58 | 0.083333 | 13490 | 13500 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 120 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 07:58 | 08:40 | 0.7 | 13500 | 13520 | 20 | Slide | 0 | 13517 | 88.19 | 136.38 | 10679.03 | -991.46 | 1180.55 | -991.46 | 5.05 |  |  | 43 |  | 400 |  | 28.57 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 08:48 | 09:00 | 0.2 | 13520 | 13534 | 14 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 70 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 09:08 | 09:16 | 0.13333 | 13534 | 13584 | 50 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 375 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 09:23 | 09:34 | 0.18333 | 13584 | 13617 | 33 | Rotate |  | 13611 | 89.77 | 136.17 | 10680.7 | -1059.38 | 1245.51 | -1059.38 | 1.7 |  |  | 35 | 80 | 400 | 16500 | 180 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 09:42 | 09:48 | 0.1 | 13617 | 13649 | 32 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 320 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 09:53 | 10:02 | 0.15 | 13649 | 13678 | 29 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 193.33 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 10:12 | 11:29 | 1.2833 | 13678 | 13708 | 30 | Slide | 0 | 13706 | 88.05 | 135.52 | 10682.51 | -1127.52 | 1311.68 | -1127.52 | 1.94 |  |  | 43 |  | 400 |  | 19.48 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 11:29 | 11:51 | 0.36667 | 13708 | 13773 | 65 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 177.27 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 12:00 | 12:05 | 0.083333 | 13773 | 13783 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 120 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 12:05 | 13:07 | 1.0333 | 13783 | 13798 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 14.52 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 13:07 | 13:32 | 0.41667 | 13798 | 13869 | 71 | Rotate |  | 13802 | 88.63 | 136.66 | 10685.29 | -1196.65 | 1378.22 | -1196.65 | 1.33 |  |  | 35 | 80 | 400 | 16500 | 170.4 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 13:42 | 15:00 | 1.3 | 13869 | 13890 | 21 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 16.15 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 15:16 | 16:16 | 1 | 13890 | 13915 | 25 | Slide | 0 | 13900 | 86.84 | 137.31 | 10689.16 | -1268.25 | 1445.02 | -1268.25 | 1.94 |  |  | 43 |  | 400 |  | 25 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 16:16 | 16:26 | 0.16667 | 13915 | 13934 | 19 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 114 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 16:34 | 16:49 | 0.25 | 13934 | 13967 | 33 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 132 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 16:59 | 17:08 | 0.15 | 13967 | 13999 | 32 | Rotate |  | 13996 | 87.06 | 137.26 | 10694.27 | -1338.69 | 1510.05 | -1338.69 | 0.23 |  |  | 35 | 80 | 400 | 16500 | 213.33 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 17:12 | 17:30 | 0.3 | 13999 | 14063 | 64 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 213.33 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 17:35 | 18:35 | 1 | 14063 | 14093 | 30 | Slide | 0 | 14092 | 83.77 | 136.79 | 10701.94 | -1408.69 | 1575.28 | -1408.69 | 3.46 |  |  | 43 |  | 400 |  | 30 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 18:35 | 19:00 | 0.41667 | 14093 | 14159 | 66 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 158.4 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 19:45 | 19:55 | 0.16667 | 14159 | 14191 | 32 | Rotate |  | 14187 | 83.16 | 136.38 | 10712.75 | -1477.25 | 1640.14 | -1477.25 | 0.77 |  |  | 35 | 80 | 400 | 16500 | 192 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 20:00 | 20:15 | 0.25 | 14191 | 14254 | 63 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 252 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 20:20 | 20:25 | 0.083333 | 14254 | 14260 | 6 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 72 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 20:25 | 20:55 | 0.5 | 14260 | 14270 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 20 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 20:55 | 21:20 | 0.41667 | 14270 | 14349 | 79 | Rotate |  | 14282 | 83.78 | 136.06 | 10723.56 | -1545.39 | 1705.45 | -1545.39 | 0.73 |  |  | 35 | 80 | 400 | 16500 | 189.6 | 4650 | 3600 | 1050 | 273 | 300 | 215 | 170
03/16/2021 | 21:25 | 21:55 | 0.5 | 14349 | 14446 | 97 | Rotate |  | 14379 | 83.56 | 136.09 | 10734.25 | -1614.83 | 1772.33 | -1614.83 | 0.23 |  |  | 35 | 80 | 400 | 16500 | 194 | 4650 | 3600 | 1050 | 288 | 300 | 215 | 170
03/16/2021 | 22:00 | 22:30 | 0.5 | 14446 | 14533 | 87 | Rotate |  | 14474 | 83.08 | 136.58 | 10745.3 | -1683.09 | 1837.47 | -1683.09 | 0.72 |  |  | 35 | 80 | 400 | 16500 | 174 | 4650 | 3600 | 1050 | 288 | 300 | 215 | 170
03/16/2021 | 22:30 | 23:00 | 0.5 | 14533 | 14541 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 16 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/16/2021 | 23:10 | 24:00 | 0.83333 | 14541 | 14562 | 21 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 25.2 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/17/2021 | 00:00 | 00:25 | 0.41667 | 14562 | 14576 | 14 | Slide | 0 | 14568 | 88.69 | 135.85 | 10752.04 | -1750.74 | 1902.32 | -1750.74 | 6.02 |  |  | 43 |  | 400 |  | 33.6 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/17/2021 | 00:25 | 00:50 | 0.41667 | 14576 | 14635 | 59 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 141.6 | 4650 | 3600 | 1050 | 288 | 300 | 215 | 170
03/17/2021 | 00:55 | 01:00 | 0.083333 | 14635 | 14645 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16500; Drilling Parameters ROP: 120 | 4650 | 3600 | 1050 | 288 | 300 | 215 | 170
03/17/2021 | 01:05 | 01:40 | 0.58333 | 14645 | 14730 | 85 | Rotate |  | 14663 | 92.92 | 135.92 | 10750.71 | -1818.93 | 1968.43 | -1818.93 | 4.45 |  |  | 35 | 80 | 400 | 16500 | 145.71 | 4650 | 3600 | 1050 | 288 | 300 | 215 | 170
03/17/2021 | 01:45 | 02:40 | 0.91667 | 14730 | 14755 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 27.27 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/17/2021 | 02:40 | 03:10 | 0.5 | 14755 | 14825 | 70 | Rotate |  | 14758 | 92.44 | 135.66 | 10746.27 | -1886.95 | 2034.6 | -1886.95 | 0.57 |  |  | 35 | 80 | 400 | 16500 | 140 | 4650 | 3600 | 1050 | 288 | 300 | 215 | 170
03/17/2021 | 03:10 | 04:10 | 1 | 14825 | 14850 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 25 | 3800 | 3600 | 200 | 273 | 300 | 215 | 170
03/17/2021 | 04:10 | 04:40 | 0.5 | 14850 | 14919 | 69 | Rotate |  | 14852 | 91.43 | 134.3 | 10743.09 | -1953.35 | 2101.05 | -1953.35 | 1.8 |  |  | 40 | 80 | 400 | 16500 | 138 | 4650 | 3600 | 1050 | 284 | 300 | 215 | 170
03/17/2021 | 04:45 | 06:05 | 1.3333 | 14919 | 14949 | 30 | Slide | 0 | 14947 | 88.87 | 133.89 | 10742.85 | -2019.45 | 2169.27 | -2019.45 | 2.73 |  |  | 43 |  | 400 |  | 22.5 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 06:05 | 06:27 | 0.36667 | 14949 | 15014 | 65 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 177.27 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 06:37 | 06:40 | 0.05 | 15014 | 15024 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 200 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 06:52 | 07:59 | 1.1167 | 15024 | 15054 | 30 | Slide | 0 | 15041 | 87.08 | 136.54 | 10746.17 | -2086.12 | 2235.44 | -2086.12 | 3.4 |  |  | 43 |  | 400 |  | 26.87 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 07:59 | 08:27 | 0.46667 | 15054 | 15108 | 54 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 21000; Drilling Parameters ROP: 115.71 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 08:37 | 09:51 | 1.2333 | 15108 | 15118 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 8.11 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 09:51 | 10:25 | 0.56667 | 15118 | 15203 | 85 | Rotate |  | 15136 | 86.26 | 136.43 | 10751.69 | -2154.89 | 2300.74 | -2154.89 | 0.87 |  |  | 40 | 80 | 400 | 21000 | 150 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150
03/17/2021 | 10:35 | 12:05 | 1.5 | 15203 | 15209 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 43; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 4 | 3800 | 3600 | 200 | 285 | 320 | 220 | 150