## Summary
Magnolia Oil & Gas / Yukon A 1H / LTX1141420 / Patterson 248
Report Date: | 11/19/2020 | Current Depth: | 16041
Start Date: | 11/02/2020 | Casing Depth: | 0
Daily Cost: | 4800 | Distance to TD:
Well Cost: | 94650 | Average ROP: | 0
Drilling Hours: | 0 | Svy MD: | 16041
24Hr Forcast: |  | Svy Inc: | 94.7
Current BHA: |  | Svy Azi: | 314.3
Current BRT Hrs: | 0 | Svy TVD: | 10727.5
Bit Make / Model: |  | Svy NS: | 3601.45
POOH in last 24Hrs: | No | Svy EW: | -4557.77
Rig Down Time: | No | Svy Hi/Lo: | 0
Mud Type: | OBM | Svy Left/Right: | 0
Directional Driller Day: | Nathan Marks | MWD Day: | Russell Arnold
Directional Driller Night: | Billy McFarland | MWD Night: | Chris Hendrix
RSS Engineer 1: |  | Third Man:
RSS Engineer 2: |  | Fourth Man:
Principal Plan: |  | Max BHT Well: | 309
24Hr Summary: |  | Max BHT 24Hrs: | 0
Comments
Motors On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
PPM250014 | 6/7 Lobe 8.8 Stage |  |  | Clean
PPM2500004 | 6/7 Lobe 8.8 Stage |  |  | Clean
PPM250001 | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  | Clean
MTR475035 | 7/8 Lobe 3.8 Stage |  |  | Clean
MWD On Location
SN | Description | Make | Comments | Status | Prev Hrs | Well Hrs | Total Hrs
500037 | UBHO/ Muleshoe |  |  | Dirty |  | 57.93 | 57.93
500042 | UBHO/ Muleshoe |  |  | Clean

## Well Summary
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31140 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Rig: |  | Patterson 248 |  |  | Well: |  | Yukon A 1H
|  |  |  | County: |  | Washington |  |  | State: |  | Texas
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Total Drilled (Usft): |  | 15936 |  |  | Total Days: |  | 12
BHA Summary
BHA # | Bit # | Hole Size (in) | Start (Usft) | End (Usft) | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | Slide % | Drlg Hrs | Circ Hrs | BRT Hrs | Failed
1 | 0 | 13.5 | 105 | 3170 | 3065 |  | 625.51 |  | 7.47 | 4.9 | 8.28 | 15.58
2 | 1 | 9.875 | 3170 | 10528 | 7358 |  | 287.05 |  | 6.86 | 25.63 | 28.32 | 49.5
3 | 3 | 6.75 | 10528 | 16041 | 5513 |  | 129.92 |  | 15.69 | 42.43 | 57.93 | 80.33
Bit Run Record
Bit # | Make |  | Model |  | Size (in) | Grade In |  | Grade Out |  | TFA | Drilled | Drlg Hrs | ROP
0 | Baker Hughes |  | U616S |  | 13.5 |  |  |  |  | 0 | 3065 | 4.9 | 625.51
1 | Ulterra |  | SPL613 |  | 9.875 | New |  | 0-1-CT-S-X-1/16-TD |  | 1.491 | 7358 | 25.6333 | 287.05
3 | Halliburton |  | GTD64M |  | 6.75 | New |  |  |  | 1.491 | 5513 | 42.4333 | 129.92
Motor Record
BHA # | Make |  | Model |  | Lobes | Stages | OD (in) | Bend | Bit to Bend | Drilled (Usft) |  | ROP (Usft/hr)
1 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 7.875 | 1.5 | 0 | 3065 |  | 625.51
2 | PDCI |  | 7/8 5.9 |  | 7/8 | 5.90 | 7.875 | 2 | 6.02 | 7358 |  | 287.05
3 | PDCI |  | 6/7 8.8 |  | 6/7 | 8.80 | 5.5 | 2.12 | 4.08 | 5513 |  | 129.92
Personnel Summary
Day DD |  | Night DD |  | Day MWD |  | Night MWD |  | Day Co Man |  | Night CO Man |  | Drilling Eng
Jeff Wells |  | Billy McFarland |  | Billy McFarland |  | Chris Hendrix |  | Jim |  | Bobby Guin |  | David LeBlanc
Nathan Marks |  | Jeff Wells |  | Russell Arnold |  | Kyle Novosad |  | Kevin Burt |  | James
Phase Summary
Phase |  |  | Total Days / Phase Days |  | Drilled (Usft) |  | Avg ROP (Usft/hr) |  | NPT(Rig/Dir) |  | # BHA's |  | Drlg Hrs
SUR: SURFACE |  |  | 2.00 / 0.48 |  | 3065 |  | 624.24 |  |  |  | 1 |  | 4.91
INT: INTERMEDIATE |  |  | 4.00 / 1.36 |  | 7358 |  | 286.64 |  | 0.48 / 0.00 |  | 1 |  | 25.67
CRV: CURVE |  |  | 1.62 / 0.52 |  | 989 |  | 102.7 |  |  |  | 1 |  | 9.63
LAT: LATERAL |  |  | 4.38 / 1.96 |  | 4524 |  | 138.22 |  |  |  | 1 |  | 32.73
Total |  |  | 12 |  | 15936 |  | 218.48 |  | 0.48 / 0.00 |  | 3 |  | 72.94
Phase Summary - Per BHA
Phase / BHA |  |  | From (Usft) | To(Usft) | Rot ROP | Rot Dist | Slide ROP | Slide Dist | Slide % | Tot Drill | Avg ROP | Tot Hrs | Slide Hrs
SUR: SURFACE-BHA 1 (Surface) |  |  | 105.00 | 3170.00 | 781.27 | 2836.00 | 178.91 | 229.00 | 7.47 | 3065.00 | 624.24 | 4.91 | 1.28
INT: INTERMEDIATE-BHA 2 (Intermediate) |  |  | 3170.00 | 10528.00 | 376.33 | 6853.00 | 67.69 | 505.00 | 6.86 | 7358.00 | 286.64 | 25.67 | 7.46
CRV: CURVE-BHA #3 (Curve and Lateral) |  |  | 10528.00 | 11517.00 | 175.85 | 415.00 | 78.95 | 574.00 | 58.04 | 989.00 | 102.70 | 9.63 | 7.27
LAT: LATERAL-BHA #3 (Curve and Lateral) |  |  | 11517.00 | 16041.00 | 242.02 | 4233.00 | 19.09 | 291.00 | 6.43 | 4524.00 | 138.22 | 32.73 | 15.24
Well Seeker PRO 2.0.8.0 - Pro Directional

## Well Statistics
Well Data |  | Drilling Data
Job Number | LTX1141420 | Total Drilled(Usft) | 15936.00
Operator | Magnolia Oil & Gas | Drilling Hours | 72.97
Well Name | Yukon A 1H | Avg ROP(Usft/hr) | 218.40
Rig | Patterson 248 | Rotary Drilled(Usft) | 14337.00
State | Texas | Rotary Hours | 41.67
County | Washington | Rotary ROP(Usft/hr) | 344.09
Formation | Austin Chalk | Rotary % | 89.97
Start Date | 11/02/2020 | Slide Drilled(Usft) | 1599.00
End Date | 11/19/2020 | Slide Hours | 31.30
Days On Well | 12 | Slide ROP(Usft/hr) | 51.09
Start Depth (Usft) | 105.00 | Slide % | 10.03
End Depth (Usft) | 16041.00
Total Drilled (Usft) | 15936.00
# BHA's | 3
# Motor Failures | 0
# MWD Failures | 0
NPT hrs (Rig/Dir) | 3.82 / 0.00
Phase Data
Phase | SUR | INT | CRV | LAT
Start Date | 11/02/2020 | 11/10/2020 | 11/14/2020 | 11/15/2020
End Date | 11/03/2020 | 11/13/2020 | 11/15/2020 | 11/19/2020
Total Days | 2.00 | 4.00 | 1.62 | 4.38
Start Depth (Usft) | 105.00 | 3170.00 | 10528.00 | 11517.00
End Depth (Usft) | 3170.00 | 10528.00 | 11517.00 | 16041.00
Total Drilled(Usft) | 3065.00 | 7358.00 | 989.00 | 4524.00
Drilling Hours | 4.90 | 25.63 | 9.65 | 32.78
Circulating Hours | 3.38 | 2.68 | 0.50 | 15.00
Total D&C Hours | 8.28 | 28.32 | 10.15 | 47.78
Avg ROP(Usft/hr) | 625.51 | 287.05 | 102.49 | 138.00
Rotary Drilled(Usft) | 2836.00 | 6853.00 | 415.00 | 4233.00
Rotary Hours | 3.62 | 18.17 | 2.37 | 17.52
Rotary ROP(Usft/hr) | 784.15 | 377.23 | 175.35 | 241.66
Rotary % | 92.53 | 93.14 | 41.96 | 93.57
Slide Drilled(Usft) | 229.00 | 505.00 | 574.00 | 291.00
Slide Hours | 1.28 | 7.47 | 7.28 | 15.27
Slide ROP(Usft/hr) | 178.44 | 67.63 | 78.81 | 19.06
Slide % | 7.47 | 6.86 | 58.04 | 6.43
# BHA | 1 | 1 | 1 | 1
# Motor Failures | 0 | 0 | 0 | 0
# MWD Failures | 0 | 0 | 0 | 0
NPT hrs (Rig/Dir) | 0.00 / 0.00 | 2.07 / 0.00 | 0.67 / 0.00 | 1.08 / 0.00
Total Phase Hrs | 11.45 | 32.67 | 12.38 | 47.12
Phase ROP (Usft/hr) | 267.69 | 225.24 | 79.87 | 96.02
Avg Motor Yield (°/100ft) | 5.99 | 13.79 | 14.01 | 14.17
Avg Rotary DLS (°/100ft) | 0.30 | 0.47 | 0.00 | 1.10
Avg Rotary TF | -179.74 | -157.74 | 0.00 | 12.81
Avg Slide Length (Usft) | 22.90 | 22.95 | 57.40 | 13.38
# Slides | 10 | 22 | 10 | 21
BHA Data
BHA# | 1 | 2 | 3
Description | BHA 1 (Surface) | BHA 2 (Intermediate) | BHA #3 (Curve and Lateral)
Bit Size | 13.500 | 9.875 | 6.750
Bit Make/Model | Baker Hughes / U616S | Ulterra / SPL613 | Halliburton / GTD64M
Bit TFA | 0.000 | 1.491 | 1.491
Grade In |  | New | New
Grade Out |  | 0-1-CT-S-X-1/16-TD
Motor SN | PPM800015 | PPM800038 | PPM250016
Motor Make/Model | PDCI / 7/8 5.9 | PDCI / 7/8 5.9 | PDCI / 6/7 8.8
Lobes/Stages | 7/8 / 5.90 | 7/8 / 5.90 | 6/7 / 8.80
WOB (klbs) | 5.00 / 16.91 / 20.00 | 12.00 / 36.93 / 48.00 | 15.00 / 40.69 / 65.00
Diff P (psi) | 130.00 / 361.48 / 380.00 | 150.00 / 666.24 / 900.00 | 100.00 / 862.50 / 1200.00
Bend | 1.500 | 2.000 | 2.120
Date In | 11/02/2020 | 11/10/2020 | 11/14/2020
Date Out | 11/02/2020 | 11/12/2020 | 11/18/2020
Time In | 02:25 | 15:10 | 09:50
Time Out | 18:00 | 16:40 | 10:30
BRT Hrs | 15.58 | 49.50 | 96.67
Start Depth (Usft) | 105.00 | 3170.00 | 10528.00
End Depth (Usft) | 3170.00 | 10528.00 | 16041.00
Total Drilled(Usft) | 3065.00 | 7358.00 | 5513.00
Drilling Hours | 4.90 | 25.63 | 42.43
Circulating Hours | 3.38 | 2.68 | 15.50
Total D&C Hours | 8.28 | 28.32 | 57.93
Avg ROP(Usft/hr) | 625.51 | 287.05 | 129.92
Rotary Drilled(Usft) | 2836.00 | 6853.00 | 4648.00
Rotary Hours | 3.62 | 18.17 | 19.88
Rotary ROP(Usft/hr) | 784.15 | 377.23 | 233.76
Rotary % | 92.53 | 93.14 | 84.31
Slide Drilled(Usft) | 229.00 | 505.00 | 865.00
Slide Hours | 1.28 | 7.47 | 22.55
Slide ROP(Usft/hr) | 178.44 | 67.63 | 38.36
Slide % | 7.47 | 6.86 | 15.69
Motor Failure | NO | NO | NO
MWD Failure | NO | NO | NO
Unplanned Trip | NO | NO | NO
LIH | NO | NO | NO
Avg Motor Yield (°/100ft) | 5.99 | 13.79 | 14.33
Avg Rotary DLS (°/100ft) | 0.29 | 0.47 | 0.98
Avg Rotary TF | 179.99 | -157.74 | 13.91
Avg Slide Length (Usft) | 22.90 | 22.95 | 27.58
# Slides | 10 | 22 | 31

## Personnel Report
|  | Job # | LTX1141420 |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # | 42-477-31140 |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: | Patterson 248 |  | Well: |  | Yukon A 1H
|  | Date: | 11/19/2020 |  | State: |  | Texas
[5 empty] | County: |  | Washington
Yukon A 1H - Personnel Utilization
Name | Position |  | Date/Time Arrived | Date/Time Left |  | Total Days / Hours
Billy McFarland | Night DD |  | 11/11/2020 - 00:00 | 11/19/2020 - 00:00 |  | 9.00 / 0.00
Billy McFarland | Day MWD |  | 11/10/2020 - 00:00 | 11/10/2020 - 00:00 |  | 1.00 / 0.00
Chris Hendrix | Night MWD |  | 11/17/2020 - 00:00 | 11/19/2020 - 00:00 |  | 3.00 / 0.00
Jeff Wells | Day DD |  | 11/10/2020 - 00:00 | 11/12/2020 - 00:00 |  | 3.00 / 0.00
Jeff Wells | Night DD |  | 11/02/2020 - 00:00 | 11/03/2020 - 00:00 |  | 2.00 / 0.00
Jeff Wells | Night DD |  | 11/10/2020 - 00:00 | 11/10/2020 - 00:00 |  | 1.00 / 0.00
Kyle Novosad | Night MWD |  | 11/02/2020 - 00:00 | 11/03/2020 - 00:00 |  | 2.00 / 0.00
Kyle Novosad | Night MWD |  | 11/10/2020 - 00:00 | 11/12/2020 - 00:00 |  | 3.00 / 0.00
Nathan Marks | Day DD |  | 11/02/2020 - 00:00 | 11/03/2020 - 00:00 |  | 2.00 / 0.00
Nathan Marks | Day DD |  | 11/13/2020 - 00:00 | 11/19/2020 - 00:00 |  | 7.00 / 0.00
Russell Arnold | Day MWD |  | 11/02/2020 - 00:00 | 11/03/2020 - 00:00 |  | 2.00 / 0.00
Russell Arnold | Day MWD |  | 11/11/2020 - 00:00 | 11/19/2020 - 00:00 |  | 9.00 / 0.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Tracking
|  |  |  | Operator: |  |  | Magnolia Oil & Gas | [7 empty] | Job #: |  |  |  |  | LTX1141420 | [5 empty] | State / County: |  |  |  | Texas / Washington
|  |  |  | Well Name: |  |  | Yukon A 1H | [7 empty] | Day DD: |  |  |  |  | Nathan Marks | [5 empty] | API #: |  |  |  | 42-477-31140
|  |  |  | AFE #: |  |  | 20DD0308MG | [7 empty] | Night DD: |  |  |  |  | Billy McFarland | [5 empty] | Company Man: |  |  |  | Jim
|  |  |  | PO #: |  |  | ProDirectional | [7 empty] | Day MWD: |  |  |  |  | Russell Arnold | [5 empty] | Company Rep
|  |  |  | Rig: |  |  | Patterson 248 | [7 empty] | Night DD: |  |  |  |  | Chris Hendrix | [5 empty] | Signature
This document is a FIELD ESTIMATE ONLY. Prices and terms are subject to change once reviewed by management
[9 empty] | 11/02/2020 | 11/03/2020 | 11/04/2020 | 11/05/2020 | 11/06/2020 | 11/07/2020 | 11/08/2020 | 11/09/2020 | 11/10/2020 | 11/11/2020 | 11/12/2020 | 11/13/2020 | 11/14/2020 | 11/15/2020 | 11/16/2020 | 11/17/2020 | 11/18/2020 | 11/19/2020 | 11/20/2020 | 11/21/2020 | 11/22/2020 | 11/23/2020 | 11/24/2020 | 11/25/2020 | 11/26/2020 | 11/27/2020 | 11/28/2020 | 11/29/2020 | 11/30/2020 | 12/01/2020 | 12/02/2020
Type | Vendor | Size (in) | Description |  | Mag | SN | In Hole | On Location
Bit |  | 6.75 | 6 3/4 Halliburton- GTD64M w/ 6 x 18s |  | Steel | 13509567 | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
Cross Over |  | 5.25 | Crossover (XT39 Pin x DS42 Box) |  | Steel | SD119319 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Cross Over |  | 5.25 | Crossover (XT39 Pin x DS42 Box) |  | Steel | SD119321 | 5 | 8 | X | [9 empty] | O | O | O | X | X | X | X | O
Cross Over |  | 5.375 | Crossover (XT39 Pin x DS 42 Box) |  | Steel | PS22199-DTI | 0 | 7 | [11 empty] | O | O | O | O | O | O | O
Cross Over |  | 5.25 | Crossover (DS42 Pin x XT39 Box) |  | Steel | PS22006-DTI | 0 | 7 | [11 empty] | O | O | O | O | O | O | O
MWD / LWD |  | 5.375 | UBHO/ Muleshoe |  | Steel | 500037 | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
MWD / LWD |  | 5.25 | UBHO/ Muleshoe |  | Steel | 500042 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 Lobe 8.8 Stage |  | Steel | PPM250014 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 Lobe 8.8 Stage |  | Steel | PPM2500004 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  | Steel | PPM250016 | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
Motor |  | 5 | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  | Steel | PPM250001 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Motor |  | 5.5 | 7/8 Lobe 3.8 Stage |  | Steel | MTR475035 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Collar |  | 5 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | SD56630 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Collar |  | 5.125 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | SD56702 | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
Collar |  | 5.125 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | SD56709 | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
Collar |  | 5.063 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | SD56784 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Collar |  | 4.75 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | SD56785 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Collar |  | 4.75 | Non Mag Drill Collar (NO HARDBANDING) |  | Non-Mag | NA | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Collar |  | 5.063 | Pony Collar |  | Steel | SD56727 | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
Collar |  | 5.063 | Pony Collar |  | Steel | SD56841 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Drill Pipe |  | 4.5 | 27 Stands of 4 1/2 DP |  | Steel | Rig1 | 0 | 7 | [11 empty] | O | O | O | O | O | O | O
Accelerator |  | 5 | Cougar Thruster |  | Steel | DS MT3X-500-049 | 5 | 7 | X | [10 empty] | O | O | X | X | X | X | O
Accelerator |  | 5 | Cougar Thruster |  | Steel | MT3X500012 | 0 | 2 | [16 empty] | O | O
Sub |  | 4.75 | Float Sub |  | Steel | SD115658 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Sub |  | 4.75 | Float Sub |  | Steel | SD119067 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Sub |  | 4.75 | XT39 Lift Sub |  | Steel | GT551232 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Sub |  | 4.75 | XT39 Lift Sub |  | Steel | GT551251 | 0 | 8 | [10 empty] | O | O | O | O | O | O | O | O
Sub |  | 5 | BTI Valve |  | Steel | Rig | 4 | 8 | [10 empty] | O | O | O | X | X | X | X | O
Sub |  | 4.875 | BTI Balve |  | Steel | XXX | 0 | 2 | [16 empty] | O | O
Agitator |  | 5 | NOV Shock Sub/ Agitator/ Safety Joint |  | Steel | AG000525-0013 | 5 | 8 | X | [9 empty] | O | O | O | X | X | X | X | O
Agitator |  | 5.25 | NOV Shock Sub/ Agitator/ Safety Joint |  | Steel | 525-00-007 | 0 | 3 | [15 empty] | O | O | O
Position |  |  | Name |  |  |  | Days
Day DD |  |  | Jeff Wells |  |  |  | 3 | [9 empty] | 1 | 1 | 1
Day DD |  |  | Nathan Marks |  |  |  | 9 |  | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Billy McFarland |  |  |  | 9 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night DD |  |  | Jeff Wells |  |  |  | 3 |  | 1 | 1 | [6 empty] | 1
Day MWD |  |  | Billy McFarland |  |  |  | 1 | [9 empty] | 1
Day MWD |  |  | Russell Arnold |  |  |  | 11 |  | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Night MWD |  |  | Chris Hendrix |  |  |  | 3 | [16 empty] | 1 | 1 | 1
Night MWD |  |  | Kyle Novosad |  |  |  | 5 |  | 1 | 1 | [6 empty] | 1 | 1 | 1

## Tool Inventory
|  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31140 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Yukon A 1H
|  | County: |  | Washington |  |  | State: |  | Texas
|  | AFE #: |  | 20DD0308MG |  |  | PO #: |  | ProDirectional
Tool Inventory
S/N | Description | OD (in) | Length (Usft) |  | Cnx Top / Bot | Status | Make / Model | Date Arrived |  | Date Left
PPM250014 | 6/7 Lobe 8.8 Stage | 5.5 |  |  | 4 XT39 / 3 1/2 Reg | Clean |  | 11/12/2020
PPM2500004 | 6/7 Lobe 8.8 Stage | 5.5 | 33.12 |  | 4 XT39 / 3 1/2 Reg | Clean |  | 11/12/2020
PPM250016 | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS | 5.5 | 32.96 |  | 4 XT39 / 3 1/2 Reg | Dirty |  | 11/12/2020 |  | 11/19/2020
PPM250001 | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS | 5 | 32.94 |  | 4 XT39 / 3 1/2 Reg | Clean |  | 11/12/2020
MTR475035 | 7/8 Lobe 3.8 Stage | 5.5 |  |  | 4 XT39 / 3 1/2 Reg | Clean |  | 11/12/2020
500037 | UBHO/ Muleshoe | 5.375 | 4.02 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/12/2020
500042 | UBHO/ Muleshoe | 5.25 | 4 |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD56630 | Non Mag Drill Collar (NO HARDBANDING) | 5 | 30.32 |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD56702 | Non Mag Drill Collar (NO HARDBANDING) | 5.125 | 30.64 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/12/2020 |  | 11/19/2020
SD56709 | Non Mag Drill Collar (NO HARDBANDING) | 5.125 | 30.29 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/12/2020 |  | 11/19/2020
SD56784 | Non Mag Drill Collar (NO HARDBANDING) | 5.063 | 31.14 |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD56785 | Non Mag Drill Collar (NO HARDBANDING) | 4.75 |  |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
NA | Non Mag Drill Collar (NO HARDBANDING) | 4.75 |  |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD56727 | Pony Collar | 5.063 | 11.8 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/12/2020 |  | 11/19/2020
SD56841 | Pony Collar | 5.063 | 10.65 |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD115658 | Float Sub | 4.75 |  |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD119067 | Float Sub | 4.75 |  |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
SD119319 | Crossover (XT39 Pin x DS42 Box) | 5.25 | 3.61 |  | DS42 / 4 XT39 | Clean |  | 11/12/2020
SD119321 | Crossover (XT39 Pin x DS42 Box) | 5.25 | 3.65 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/12/2020 |  | 11/19/2020
GT551232 | XT39 Lift Sub | 4.75 |  |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
GT551251 | XT39 Lift Sub | 4.75 |  |  | 4 XT39 / 4 XT39 | Clean |  | 11/12/2020
LC3355 | XT39 Lift Cap |  |  |  |  | Clean |  | 11/12/2020
AG000525-0013 | NOV Shock Sub/ Agitator/ Safety Joint | 5 | 28.71 |  | DS42 / DS 42 | Dirty |  | 11/12/2020
13509567 | 6 3/4 Halliburton- GTD64M w/ 6 x 18s | 6.75 | 0.75 |  | 3 1/2 Reg | Dirty |  | 11/12/2020
Rig | BTI Valve | 5 | 2.37 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/12/2020
DS MT3X-500-049 | Cougar Thruster | 5 | 24.21 |  | 4 XT39 / 4 XT39 | Dirty |  | 11/13/2020
PS22199-DTI | Crossover (XT39 Pin x DS 42 Box) | 5.375 | 3.55 |  | DS42 / 4 XT39 | Clean |  | 11/13/2020
PS22006-DTI | Crossover (DS42 Pin x XT39 Box) | 5.25 | 3.56 |  | 4 XT39 / DS42 | Clean |  | 11/13/2020
Rig1 | 27 Stands of 4 1/2 DP | 4.5 | 2556.83 |  | DS42 / DS42 | Dirty |  | 11/13/2020
525-00-007 | NOV Shock Sub/ Agitator/ Safety Joint | 5.25 | 28.98 |  | DS42 / DS42 | Clean |  | 11/17/2020
MT3X500012 | Cougar Thruster | 5 | 23.88 |  | 4 XT39 / 4 XT39 | Clean |  | 11/18/2020
XXX | BTI Balve | 4.875 | 2.37 |  | 4 XT39 / 4 XT39 | Clean |  | 11/18/2020
Well Seeker PRO 2.0.8.0 - Pro Directional

## Tool Utilization
|  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  | API Job # |  | 42-477-31140 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  | Rig: |  | Patterson 248 |  |  | Well: |  | Yukon A 1H
|  | County: |  | Washington |  |  | State: |  | Texas
Tool Utilization Report
Description | S/N | Date Arrived | Date Left | Days on Loc. | Days DH | Runs |  | Circ Hrs | Drlg Hrs | BRT Hrs
13 1/2 Ulterra U616S 9 x 14s | 43518 | 11/02/2020 | 11/19/2020 | 18 | 1 | 1 |  | 3.38 | 4.9 | 15.58
7/8 Lobe 5.9 Stage | PPM800015 | 11/02/2020 | 11/19/2020 | 18 | 1 | 1 |  | 3.38 | 4.9 | 15.58
13" Stabilizer | SD610469 | 11/02/2020 | 11/19/2020 | 18 | 1 | 1 |  | 3.38 | 4.9 | 15.58
NM Pony | SD56559 | 11/02/2020 | 11/19/2020 | 18 | 3 | 1 ,2 |  | 6.07 | 30.53 | 65.08
UBHO/Muleshoe | 775210 | 11/02/2020 | 11/19/2020 | 18 | 3 | 1 ,2 |  | 6.07 | 30.53 | 65.08
NMDC | SD56047 | 11/02/2020 | 11/19/2020 | 18 | 3 | 1 ,2 |  | 6.07 | 30.53 | 65.08
NMDC | SD56067 | 11/02/2020 | 11/19/2020 | 18 | 3 | 1 ,2 |  | 6.07 | 30.53 | 65.08
Cougar Thruster | DS MT3X-500-049 | 11/13/2020 | 11/19/2020 | 7 | 4 | 1 ,3 |  | 18.88 | 47.33 | 95.92
Crossover (XT39 Pin x DS42 Box) | SD119321 | 11/12/2020 | 11/19/2020 | 8 | 4 | 1 ,3 |  | 18.88 | 47.33 | 95.92
NOV Shock Sub/ Agitator/ Safety Joint | AG000525-0013 | 11/12/2020 | 11/19/2020 | 8 | 4 | 1 ,3 |  | 18.88 | 47.33 | 95.92
9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s | 53502 | 11/02/2020 | 11/19/2020 | 18 | 2 | 2 |  | 2.68 | 25.63 | 49.5
7/8 Lobe 5.9 Stage | PPM800038 | 11/02/2020 | 11/19/2020 | 18 | 2 | 2 |  | 2.68 | 25.63 | 49.5
4 1/2 XH P x 6 5/8 Reg B | SD102057 | 11/02/2020 | 11/19/2020 | 18 | 2 | 2 |  | 2.68 | 25.63 | 49.5
2 stands of 6 1/2 in Collars | Rig 2 | 11/02/2020 | 11/19/2020 | 18 | 2 | 2 |  | 2.68 | 25.63 | 49.5
4 1/2 IF B x 4 1/2 XH P | SD109796 | 11/02/2020 | 11/19/2020 | 18 | 2 | 2 |  | 2.68 | 25.63 | 49.5
NOV Agitator and Shock Sub | AGHF0675-0034 | 11/02/2020 | 11/19/2020 | 18 | 2 | 2 |  | 2.68 | 25.63 | 49.5
6 3/4" Halliburton- GTD64M w/ 6 x 18s | 13509567 | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
6/7 Lobe 8.8 Stage FBH @ 2.12? TS | PPM250016 | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
BTI Valve | Rig | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
Pony Collar | SD56727 | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
UBHO/ Muleshoe | 500037 | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
Non Mag Drill Collar (NO HARDBANDING) | SD56702 | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
Non Mag Drill Collar (NO HARDBANDING) | SD56709 | 11/12/2020 | 11/19/2020 | 8 | 3 | 3 |  | 15.5 | 42.43 | 80.33
Well Seeker PRO 2.0.8.0 - Pro Directional

## Survey Report
Operator |  |  | Magnolia Oil & Gas |  |  | Local co-ord ref |  |  | Well Centered
Field |  |  | Washington County, TX - Magnolia Oil & Gas |  |  | TVD Reference |  |  | Well
Facility |  |  | Yukon - Washington County, TX |  |  | North Reference |  |  | GRID
Well |  |  | Yukon A 1H |  |  | Survey Calc Method |  |  | Minimum Curvature
Wellbore |  |  | Yukon A 1H
Field: |  |  | Washington County, TX - Magnolia Oil & Gas
CRS |  |  | US-SPC27-EXACT / Texas Central 4203
Apply Scale Factor |  |  | NO |  |  | Scale Factor |  |  | 0
System Datum |  |  | Mean Sea Level |  |  | Depth Datum->MSL |  |  | 418.00 Usft
Map Northing |  |  | 208438.99 US survey foot |  |  | Map Easting |  |  | 3142363.88 US survey foot
Latitude |  |  | 30° 11' 19.41538" N |  |  | Longitude |  |  | 96° 43' 1.59360" W
Grid Convergence |  |  | 1.863
Facility: |  |  | Yukon - Washington County, TX
Map Northing |  |  | 199764.07 US survey foot |  |  | Map Easting |  |  | 3143643.49 US survey foot
Latitude |  |  | 30° 9' 53.17743" N |  |  | Longitude |  |  | 96° 42' 50.23681" W
Vertical Uncertainty |  |  | 0.00 Usft |  |  | Horizontal Uncertainty |  |  | 0.00 Usft
Grid Convergence |  |  | 1.864
Well: |  |  | Yukon A 1H
Local North |  |  | 0.41 Usft |  |  | Local East |  |  | 6.29 Usft
Map Northing |  |  | 199764.08 US survey foot |  |  | Map Easting |  |  | 3143643.49 US survey foot
Latitude |  |  | 30° 9' 53.17943" N |  |  | Longitude |  |  | 96° 42' 50.16508" W
Depth Datum |  |  | Well |  |  | Datum Elevation |  |  | 418.00 Usft
GL Elevation |  |  | 390.00 Usft
Grid Convergence |  |  | 1.864
Well bore: |  |  | Yukon A 1H
Magnetic Model |  |  | User defined |  |  | Date |  |  | 05/11/2020
Total Field (nT) |  |  | 46632 |  |  | Dip Angle (°) |  |  | 58.817
Declination (°) |  |  | 3
VS Origin |  |  | User Defined |  |  | VS Azimuth |  |  | 313.12
VS Orgin NS |  |  | 0.00 Usft |  |  | VS Origin EW |  |  | 0.00 Usft
Survey Program: |  |  | Yukon A 1H
Depth From (Usft) |  |  | Depth To (Usft) |  |  | Survey |  |  | Survey Tool
0 |  |  | 3094 |  |  | Yukon A 1H S1 |  |  | MWD+HDGM
3094 |  |  | 10457 |  |  | Yunkon A 1H S2 |  |  | MWD+HDGM
10457 |  |  | 16041 |  |  | Yukon A 1H S3 |  |  | MWD+HDGM
MD | Inc | Azi | TVD | NS | EW | VS | DLS | BR | TR | TF | CL | TVD SS | Map Northing | Map Easting | Latitude | Longitude | Closure Azi | Up/Dn | Left/Right
Usft | ° | ° | Usft | Usft | Usft | Usft | (°/100ft) | (°/100ft) | (°/100ft) | ° | Usft | Usft | US survey foot | US survey foot |  |  | ° | Usft | Usft
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -418 | 199764.08 | 3143643.49 | 30.1648 | -96.714 | 0
138 | 0.2 | 178.2 | 138 | -0.24 | 0.01 | -0.17 | 0.14 | 0.14 | 129.13 | 178.2 | 138 | -280 | 199763.84 | 3143643.5 | 30.1648 | -96.714 | 178.2
230 | 0.3 | 202.9 | 230 | -0.62 | -0.08 | -0.37 | 0.16 | 0.11 | 26.85 | 59.94 | 92 | -188 | 199763.46 | 3143643.41 | 30.1648 | -96.714 | 187.42
322 | 0.5 | 200.3 | 322 | -1.22 | -0.31 | -0.61 | 0.22 | 0.22 | -2.83 | -6.49 | 92 | -96 | 199762.86 | 3143643.18 | 30.1648 | -96.714 | 194.42
416 | 0.4 | 186.2 | 415.99 | -1.93 | -0.49 | -0.96 | 0.16 | -0.11 | -15 | -138.99 | 94 | -2.01 | 199762.15 | 3143643 | 30.1648 | -96.714 | 194.28
510 | 0.7 | 224.1 | 509.99 | -2.67 | -0.93 | -1.15 | 0.49 | 0.32 | 40.32 | 70.49 | 94 | 91.99 | 199761.41 | 3143642.56 | 30.1648 | -96.714 | 199.14
603 | 1.4 | 247.9 | 602.97 | -3.51 | -2.37 | -0.66 | 0.87 | 0.75 | 25.59 | 44.2 | 93 | 184.97 | 199760.57 | 3143641.12 | 30.1648 | -96.714 | 214.11
697 | 2.4 | 264.7 | 696.92 | -4.12 | -5.4 | 1.12 | 1.21 | 1.06 | 17.87 | 37.69 | 94 | 278.92 | 199759.96 | 3143638.09 | 30.1648 | -96.714 | 232.65
791 | 4 | 270.8 | 790.77 | -4.26 | -10.64 | 4.85 | 1.74 | 1.7 | 6.49 | 15.07 | 94 | 372.77 | 199759.82 | 3143632.85 | 30.1648 | -96.714 | 248.19
885 | 5 | 264.5 | 884.48 | -4.6 | -17.99 | 9.99 | 1.19 | 1.06 | -6.7 | -29.47 | 94 | 466.48 | 199759.48 | 3143625.5 | 30.1648 | -96.714 | 255.65
980 | 6.9 | 262.9 | 978.97 | -5.71 | -27.78 | 16.38 | 2.01 | 2 | -1.68 | -5.79 | 95 | 560.97 | 199758.37 | 3143615.71 | 30.1648 | -96.714 | 258.39
1074 | 8.7 | 267.2 | 1072.09 | -6.75 | -40.48 | 24.93 | 2.01 | 1.91 | 4.57 | 20.1 | 94 | 654.09 | 199757.33 | 3143603.01 | 30.1648 | -96.7141 | 260.53
1167 | 10.2 | 266.7 | 1163.83 | -7.57 | -55.73 | 35.51 | 1.62 | 1.61 | -0.54 | -3.38 | 93 | 745.83 | 199756.51 | 3143587.76 | 30.1648 | -96.7141 | 262.27
1261 | 10.7 | 266.7 | 1256.27 | -8.55 | -72.75 | 47.26 | 0.53 | 0.53 | 0 | 0 | 94 | 838.27 | 199755.53 | 3143570.74 | 30.1648 | -96.7142 | 263.3
1355 | 10.8 | 266.9 | 1348.62 | -9.53 | -90.26 | 59.37 | 0.11 | 0.11 | 0.21 | 20.56 | 94 | 930.62 | 199754.55 | 3143553.23 | 30.1648 | -96.7142 | 263.97
1448 | 10.5 | 266.8 | 1440.02 | -10.47 | -107.42 | 71.25 | 0.32 | -0.32 | -0.11 | -176.52 | 93 | 1022.02 | 199753.61 | 3143536.07 | 30.1648 | -96.7143 | 264.43
1543 | 10.3 | 267.4 | 1533.46 | -11.34 | -124.54 | 83.16 | 0.24 | -0.21 | 0.63 | 151.86 | 95 | 1115.46 | 199752.74 | 3143518.95 | 30.1648 | -96.7143 | 264.8
1637 | 10.2 | 268.3 | 1625.96 | -11.97 | -141.26 | 94.93 | 0.2 | -0.11 | 0.96 | 122.42 | 94 | 1207.96 | 199752.11 | 3143502.23 | 30.1648 | -96.7144 | 265.16
1731 | 10.8 | 268.2 | 1718.38 | -12.49 | -158.38 | 107.07 | 0.64 | 0.64 | -0.11 | -1.79 | 94 | 1300.38 | 199751.59 | 3143485.11 | 30.1648 | -96.7145 | 265.49
1825 | 11.1 | 267.8 | 1810.67 | -13.12 | -176.23 | 119.67 | 0.33 | 0.32 | -0.43 | -14.41 | 94 | 1392.67 | 199750.96 | 3143467.26 | 30.1648 | -96.7145 | 265.74
1918 | 10.6 | 267.7 | 1902.01 | -13.8 | -193.72 | 131.96 | 0.54 | -0.54 | -0.11 | -177.89 | 93 | 1484.01 | 199750.28 | 3143449.77 | 30.1648 | -96.7146 | 265.92
2013 | 10.4 | 268.1 | 1995.42 | -14.44 | -211.02 | 144.16 | 0.22 | -0.21 | 0.42 | 160.17 | 95 | 1577.42 | 199749.64 | 3143432.47 | 30.1648 | -96.7146 | 266.09
2106 | 10.2 | 267.8 | 2086.92 | -15.03 | -227.64 | 155.88 | 0.22 | -0.22 | -0.32 | -165.13 | 93 | 1668.92 | 199749.05 | 3143415.85 | 30.1648 | -96.7147 | 266.22
2199 | 9.9 | 267.1 | 2178.49 | -15.75 | -243.85 | 167.22 | 0.35 | -0.32 | -0.75 | -158.19 | 93 | 1760.49 | 199748.33 | 3143399.64 | 30.1648 | -96.7147 | 266.3
2293 | 9.5 | 266.7 | 2271.15 | -16.61 | -259.66 | 178.18 | 0.43 | -0.43 | -0.43 | -170.63 | 94 | 1853.15 | 199747.47 | 3143383.83 | 30.1647 | -96.7148 | 266.34
2387 | 10.5 | 266 | 2363.72 | -17.65 | -275.95 | 189.36 | 1.07 | 1.06 | -0.74 | -7.28 | 94 | 1945.72 | 199746.43 | 3143367.54 | 30.1647 | -96.7148 | 266.34
2480 | 10.9 | 263.7 | 2455.1 | -19.21 | -293.15 | 200.84 | 0.63 | 0.43 | -2.47 | -48.01 | 93 | 2037.1 | 199744.87 | 3143350.34 | 30.1647 | -96.7149 | 266.25
2574 | 10.5 | 262.5 | 2547.47 | -21.3 | -310.47 | 212.06 | 0.49 | -0.43 | -1.28 | -151.47 | 94 | 2129.47 | 199742.78 | 3143333.02 | 30.1647 | -96.7149 | 266.07
2668 | 10.1 | 262.5 | 2639.95 | -23.5 | -327.14 | 222.72 | 0.43 | -0.43 | 0 | 180 | 94 | 2221.95 | 199740.58 | 3143316.35 | 30.1647 | -96.715 | 265.89
2763 | 9.8 | 263.3 | 2733.52 | -25.53 | -343.42 | 233.23 | 0.35 | -0.32 | 0.84 | 155.65 | 95 | 2315.52 | 199738.55 | 3143300.07 | 30.1647 | -96.715 | 265.75
2857 | 10 | 262.5 | 2826.12 | -27.53 | -359.46 | 243.57 | 0.26 | 0.21 | -0.85 | -34.91 | 94 | 2408.12 | 199736.55 | 3143284.03 | 30.1647 | -96.7151 | 265.62
2951 | 9.8 | 262.6 | 2918.72 | -29.62 | -375.49 | 253.83 | 0.21 | -0.21 | 0.11 | 175.14 | 94 | 2500.72 | 199734.46 | 3143268 | 30.1647 | -96.7151 | 265.49
3094 | 9.2 | 260.6 | 3059.76 | -33.06 | -398.83 | 268.52 | 0.48 | -0.42 | -1.4 | -152.17 | 143 | 2641.76 | 199731.02 | 3143244.66 | 30.1647 | -96.7152 | 265.26
3262 | 8.9 | 260.6 | 3225.67 | -37.37 | -424.9 | 284.6 | 0.18 | -0.18 | 0 | 180 | 168 | 2807.67 | 199726.71 | 3143218.59 | 30.1647 | -96.7153 | 264.97
3356 | 11.3 | 258.7 | 3318.21 | -40.36 | -441.11 | 294.39 | 2.58 | 2.55 | -2.02 | -8.84 | 94 | 2900.21 | 199723.72 | 3143202.38 | 30.1647 | -96.7154 | 264.77
3450 | 11.7 | 256.5 | 3410.32 | -44.39 | -459.41 | 304.99 | 0.63 | 0.43 | -2.34 | -48.72 | 94 | 2992.32 | 199719.69 | 3143184.08 | 30.1647 | -96.7154 | 264.48
3543 | 11.7 | 255.3 | 3501.39 | -48.99 | -477.7 | 315.2 | 0.26 | 0 | -1.29 | -90.59 | 93 | 3083.39 | 199715.09 | 3143165.79 | 30.1647 | -96.7155 | 264.14
3637 | 11.9 | 257 | 3593.4 | -53.59 | -496.36 | 325.68 | 0.43 | 0.21 | 1.81 | 60.92 | 94 | 3175.4 | 199710.49 | 3143147.13 | 30.1647 | -96.7155 | 263.84
3732 | 12.1 | 255.7 | 3686.33 | -58.25 | -515.55 | 336.5 | 0.35 | 0.21 | -1.37 | -54.14 | 95 | 3268.33 | 199705.83 | 3143127.94 | 30.1647 | -96.7156 | 263.55
3826 | 12.3 | 257 | 3778.2 | -62.93 | -534.86 | 347.39 | 0.36 | 0.21 | 1.38 | 54.58 | 94 | 3360.2 | 199701.15 | 3143108.63 | 30.1646 | -96.7157 | 263.29
3920 | 10.8 | 262.5 | 3870.3 | -66.34 | -553.35 | 358.56 | 1.98 | -1.6 | 5.85 | 146.39 | 94 | 3452.3 | 199697.74 | 3143090.14 | 30.1646 | -96.7157 | 263.16
4015 | 10.2 | 262.8 | 3963.71 | -68.55 | -570.52 | 369.58 | 0.63 | -0.63 | 0.32 | 174.94 | 95 | 3545.71 | 199695.53 | 3143072.97 | 30.1646 | -96.7158 | 263.15
4108 | 10.3 | 261.4 | 4055.22 | -70.83 | -586.91 | 379.98 | 0.29 | 0.11 | -1.51 | -68.82 | 93 | 3637.22 | 199693.25 | 3143056.58 | 30.1646 | -96.7158 | 263.12
4202 | 8.5 | 265.5 | 4147.96 | -72.63 | -602.14 | 389.87 | 2.04 | -1.91 | 4.36 | 161.61 | 94 | 3729.96 | 199691.45 | 3143041.35 | 30.1646 | -96.7159 | 263.12
4296 | 6.5 | 273.8 | 4241.15 | -72.82 | -614.38 | 398.67 | 2.41 | -2.13 | 8.83 | 155.63 | 94 | 3823.15 | 199691.26 | 3143029.11 | 30.1646 | -96.7159 | 263.24
4389 | 6.6 | 276.2 | 4333.55 | -71.9 | -624.94 | 407.02 | 0.31 | 0.11 | 2.58 | 71.13 | 93 | 3915.55 | 199692.18 | 3143018.55 | 30.1646 | -96.7159 | 263.44
4483 | 4.3 | 275.5 | 4427.12 | -70.98 | -633.82 | 414.13 | 2.45 | -2.45 | -0.74 | -178.69 | 94 | 4009.12 | 199693.1 | 3143009.67 | 30.1646 | -96.716 | 263.61
4577 | 1.6 | 276.3 | 4520.98 | -70.49 | -638.64 | 417.97 | 2.87 | -2.87 | 0.85 | 179.53 | 94 | 4102.98 | 199693.59 | 3143004.85 | 30.1646 | -96.716 | 263.7
4672 | 0.7 | 20.5 | 4615.97 | -69.8 | -639.75 | 419.26 | 2 | -0.95 | 109.68 | 159.04 | 95 | 4197.97 | 199694.28 | 3143003.74 | 30.1646 | -96.716 | 263.77
4766 | 1.5 | 41.7 | 4709.95 | -68.35 | -638.73 | 419.51 | 0.94 | 0.85 | 22.55 | 37.83 | 94 | 4291.95 | 199695.73 | 3143004.76 | 30.1646 | -96.716 | 263.89
4861 | 1.5 | 22.8 | 4804.92 | -66.27 | -637.42 | 419.97 | 0.52 | 0 | -19.89 | -99.45 | 95 | 4386.92 | 199697.81 | 3143006.07 | 30.1646 | -96.716 | 264.06
4954 | 0.7 | 267.7 | 4897.91 | -65.17 | -637.52 | 420.79 | 2.05 | -0.86 | 123.76 | -160.57 | 93 | 4479.91 | 199698.91 | 3143005.97 | 30.1646 | -96.716 | 264.16
5048 | 1.3 | 234.7 | 4991.89 | -65.81 | -638.96 | 421.41 | 0.86 | 0.64 | -35.11 | -61.13 | 94 | 4573.89 | 199698.27 | 3143004.53 | 30.1646 | -96.716 | 264.12
5142 | 1.3 | 222.2 | 5085.87 | -67.22 | -640.55 | 421.61 | 0.3 | 0 | -13.3 | -96.25 | 94 | 4667.87 | 199696.86 | 3143002.94 | 30.1646 | -96.716 | 264.01
5236 | 1.2 | 249.1 | 5179.85 | -68.36 | -642.19 | 422.02 | 0.63 | -0.11 | 28.62 | 112.94 | 94 | 4761.85 | 199695.72 | 3143001.3 | 30.1646 | -96.716 | 263.92
5329 | 1.4 | 245.8 | 5272.82 | -69.17 | -644.13 | 422.89 | 0.23 | 0.22 | -3.55 | -22.18 | 93 | 4854.82 | 199694.91 | 3142999.36 | 30.1646 | -96.716 | 263.87
5423 | 1.7 | 242 | 5366.79 | -70.3 | -646.41 | 423.78 | 0.34 | 0.32 | -4.04 | -20.82 | 94 | 4948.79 | 199693.78 | 3142997.08 | 30.1646 | -96.716 | 263.79
5518 | 0.8 | 246.3 | 5461.77 | -71.23 | -648.26 | 424.5 | 0.95 | -0.95 | 4.53 | 176.2 | 95 | 5043.77 | 199692.85 | 3142995.23 | 30.1646 | -96.716 | 263.73
5611 | 0.4 | 246.8 | 5554.76 | -71.62 | -649.15 | 424.88 | 0.43 | -0.43 | 0.54 | 179.5 | 93 | 5136.76 | 199692.46 | 3142994.34 | 30.1646 | -96.716 | 263.7
5705 | 0.5 | 261 | 5648.76 | -71.81 | -649.86 | 425.27 | 0.16 | 0.11 | 15.11 | 55.36 | 94 | 5230.76 | 199692.27 | 3142993.63 | 30.1646 | -96.716 | 263.69
5800 | 0.7 | 268.2 | 5743.75 | -71.89 | -650.85 | 425.93 | 0.22 | 0.21 | 7.58 | 24.28 | 95 | 5325.75 | 199692.19 | 3142992.64 | 30.1646 | -96.716 | 263.7
5894 | 0.9 | 288.2 | 5837.74 | -71.68 | -652.13 | 427.01 | 0.36 | 0.21 | 21.28 | 64.66 | 94 | 5419.74 | 199692.4 | 3142991.36 | 30.1646 | -96.716 | 263.73
5988 | 0.6 | 64.1 | 5931.74 | -71.23 | -652.38 | 427.5 | 1.48 | -0.32 | 144.57 | 162.58 | 94 | 5513.74 | 199692.85 | 3142991.11 | 30.1646 | -96.716 | 263.77
6083 | 0.8 | 101.4 | 6026.73 | -71.15 | -651.29 | 426.76 | 0.51 | 0.21 | 39.26 | 85.71 | 95 | 5608.73 | 199692.93 | 3142992.2 | 30.1646 | -96.716 | 263.77
6176 | 1.2 | 105.3 | 6119.72 | -71.53 | -649.71 | 425.34 | 0.44 | 0.43 | 4.19 | 11.61 | 93 | 5701.72 | 199692.55 | 3142993.78 | 30.1646 | -96.716 | 263.72
6271 | 0.6 | 102.4 | 6214.71 | -71.9 | -648.27 | 424.04 | 0.63 | -0.63 | -3.05 | -177.11 | 95 | 5796.71 | 199692.18 | 3142995.22 | 30.1646 | -96.716 | 263.67
6364 | 1 | 125.7 | 6307.7 | -72.48 | -647.13 | 422.81 | 0.55 | 0.43 | 25.05 | 51.16 | 93 | 5889.7 | 199691.6 | 3142996.36 | 30.1646 | -96.716 | 263.61
6459 | 0.7 | 142.7 | 6402.69 | -73.43 | -646.11 | 421.42 | 0.41 | -0.32 | 17.89 | 148.24 | 95 | 5984.69 | 199690.65 | 3142997.38 | 30.1646 | -96.716 | 263.52
6553 | 0.6 | 94.5 | 6496.68 | -73.92 | -645.27 | 420.47 | 0.57 | -0.11 | -51.28 | -123.86 | 94 | 6078.68 | 199690.16 | 3142998.22 | 30.1646 | -96.716 | 263.46
6647 | 0.6 | 88.7 | 6590.68 | -73.95 | -644.28 | 419.73 | 0.06 | 0 | -6.17 | -92.9 | 94 | 6172.68 | 199690.13 | 3142999.2 | 30.1646 | -96.716 | 263.45
6741 | 0.2 | 161.6 | 6684.67 | -74.09 | -643.74 | 419.24 | 0.61 | -0.43 | 77.55 | 160.55 | 94 | 6266.67 | 199689.99 | 3142999.75 | 30.1646 | -96.716 | 263.43
6835 | 0.3 | 27.6 | 6778.67 | -74.03 | -643.58 | 419.16 | 0.49 | 0.11 | -142.55 | -152.15 | 94 | 6360.67 | 199690.05 | 3142999.91 | 30.1646 | -96.716 | 263.44
6929 | 0.5 | 61.1 | 6872.67 | -73.61 | -643.1 | 419.1 | 0.32 | 0.21 | 35.64 | 67.03 | 94 | 6454.67 | 199690.47 | 3143000.39 | 30.1646 | -96.716 | 263.47
7023 | 0.4 | 53.1 | 6966.67 | -73.22 | -642.48 | 418.91 | 0.13 | -0.11 | -8.51 | -151.82 | 94 | 6548.67 | 199690.86 | 3143001.01 | 30.1646 | -96.716 | 263.5
7118 | 0.5 | 10 | 7061.67 | -72.61 | -642.14 | 419.08 | 0.36 | 0.11 | -45.37 | -95.84 | 95 | 6643.67 | 199691.47 | 3143001.35 | 30.1646 | -96.716 | 263.55
7212 | 0.1 | 356.8 | 7155.67 | -72.13 | -642.08 | 419.37 | 0.43 | -0.43 | 14.04 | -176.75 | 94 | 6737.67 | 199691.95 | 3143001.41 | 30.1646 | -96.716 | 263.59
7305 | 0.5 | 306 | 7248.66 | -71.81 | -642.41 | 419.83 | 0.48 | 0.43 | -54.62 | -60.86 | 93 | 6830.66 | 199692.27 | 3143001.08 | 30.1646 | -96.716 | 263.62
7399 | 0.5 | 334.2 | 7342.66 | -71.2 | -642.92 | 420.62 | 0.26 | 0 | 30 | 104.1 | 94 | 6924.66 | 199692.88 | 3143000.57 | 30.1646 | -96.716 | 263.68
7493 | 0.7 | 331.5 | 7436.66 | -70.32 | -643.37 | 421.55 | 0.21 | 0.21 | -2.87 | -9.4 | 94 | 7018.66 | 199693.76 | 3143000.12 | 30.1646 | -96.716 | 263.76
7587 | 1.1 | 307.1 | 7530.64 | -69.27 | -644.37 | 422.99 | 0.58 | 0.43 | -25.96 | -56.41 | 94 | 7112.64 | 199694.81 | 3142999.12 | 30.1646 | -96.716 | 263.86
7681 | 1.3 | 290.3 | 7624.62 | -68.36 | -646.09 | 424.87 | 0.43 | 0.21 | -17.87 | -68.96 | 94 | 7206.62 | 199695.72 | 3142997.4 | 30.1646 | -96.716 | 263.96
7775 | 1.1 | 332 | 7718.6 | -67.19 | -647.51 | 426.7 | 0.93 | -0.21 | 44.36 | 123.19 | 94 | 7300.6 | 199696.89 | 3142995.98 | 30.1646 | -96.716 | 264.08
7869 | 0.2 | 187.6 | 7812.6 | -66.56 | -647.96 | 427.46 | 1.35 | -0.96 | -153.62 | -174.73 | 94 | 7394.6 | 199697.52 | 3142995.53 | 30.1646 | -96.716 | 264.14
7963 | 0.9 | 205.4 | 7906.59 | -67.39 | -648.29 | 427.14 | 0.76 | 0.74 | 18.94 | 22.72 | 94 | 7488.59 | 199696.69 | 3142995.2 | 30.1646 | -96.716 | 264.07
8058 | 2.2 | 173.2 | 8001.56 | -69.87 | -648.4 | 425.52 | 1.6 | 1.37 | -33.89 | -50.63 | 95 | 7583.56 | 199694.21 | 3142995.09 | 30.1646 | -96.716 | 263.85
8151 | 2.8 | 162.7 | 8094.47 | -73.81 | -647.51 | 422.18 | 0.81 | 0.65 | -11.29 | -42.68 | 93 | 7676.47 | 199690.27 | 3142995.98 | 30.1646 | -96.716 | 263.5
8245 | 2.2 | 173.7 | 8188.38 | -77.8 | -646.63 | 418.81 | 0.81 | -0.64 | 11.7 | 146.76 | 94 | 7770.38 | 199686.28 | 3142996.86 | 30.1646 | -96.716 | 263.14
8339 | 1.6 | 186.3 | 8282.33 | -80.9 | -646.58 | 416.66 | 0.77 | -0.64 | 13.4 | 151.34 | 94 | 7864.33 | 199683.18 | 3142996.91 | 30.1646 | -96.716 | 262.87
8434 | 0.4 | 216.2 | 8377.31 | -82.48 | -646.92 | 415.82 | 1.34 | -1.26 | 31.47 | 170.96 | 95 | 7959.31 | 199681.6 | 3142996.57 | 30.1646 | -96.716 | 262.73
8528 | 0.5 | 286.1 | 8471.31 | -82.63 | -647.51 | 416.15 | 0.56 | 0.11 | 74.36 | 115.92 | 94 | 8053.31 | 199681.45 | 3142995.98 | 30.1646 | -96.716 | 262.73
8622 | 1.1 | 267.5 | 8565.3 | -82.56 | -648.8 | 417.14 | 0.69 | 0.64 | -19.79 | -32.89 | 94 | 8147.3 | 199681.52 | 3142994.69 | 30.1646 | -96.716 | 262.75
8716 | 0.7 | 4 | 8659.29 | -82.03 | -649.66 | 418.14 | 1.46 | -0.43 | 102.66 | 149.47 | 94 | 8241.29 | 199682.05 | 3142993.83 | 30.1646 | -96.716 | 262.8
8810 | 1.4 | 25.4 | 8753.28 | -80.42 | -649.13 | 418.85 | 0.84 | 0.74 | 22.77 | 40.24 | 94 | 8335.28 | 199683.66 | 3142994.36 | 30.1646 | -96.716 | 262.94
8903 | 1.4 | 14.7 | 8846.25 | -78.29 | -648.35 | 419.73 | 0.28 | 0 | -11.51 | -95.35 | 93 | 8428.25 | 199685.79 | 3142995.14 | 30.1646 | -96.716 | 263.11
8997 | 1.8 | 16.8 | 8940.21 | -75.77 | -647.64 | 420.94 | 0.43 | 0.43 | 2.23 | 9.39 | 94 | 8522.21 | 199688.31 | 3142995.85 | 30.1646 | -96.716 | 263.33
9090 | 1.6 | 1.3 | 9033.17 | -73.07 | -647.18 | 422.45 | 0.54 | -0.22 | -16.67 | -121.13 | 93 | 8615.17 | 199691.01 | 3142996.31 | 30.1646 | -96.716 | 263.56
9184 | 0.5 | 316.1 | 9127.16 | -71.46 | -647.44 | 423.73 | 1.38 | -1.17 | 48.09 | -164.13 | 94 | 8709.16 | 199692.62 | 3142996.05 | 30.1646 | -96.716 | 263.7
9278 | 1.3 | 252.2 | 9221.15 | -71.49 | -648.74 | 424.66 | 1.24 | 0.85 | -67.98 | -86.47 | 94 | 8803.15 | 199692.59 | 3142994.75 | 30.1646 | -96.716 | 263.71
9371 | 1.2 | 221.4 | 9314.13 | -72.55 | -650.39 | 425.15 | 0.72 | -0.11 | -33.12 | -113.66 | 93 | 8896.13 | 199691.53 | 3142993.1 | 30.1646 | -96.716 | 263.64
9465 | 0.7 | 222.3 | 9408.11 | -73.71 | -651.42 | 425.11 | 0.53 | -0.53 | 0.96 | 178.74 | 94 | 8990.11 | 199690.37 | 3142992.07 | 30.1646 | -96.716 | 263.54
9559 | 0.4 | 229.7 | 9502.11 | -74.35 | -652.06 | 425.14 | 0.33 | -0.32 | 7.87 | 170.36 | 94 | 9084.11 | 199689.73 | 3142991.43 | 30.1646 | -96.716 | 263.5
9652 | 0.7 | 255.8 | 9595.1 | -74.7 | -652.86 | 425.48 | 0.41 | 0.32 | 28.06 | 53.41 | 93 | 9177.1 | 199689.38 | 3142990.63 | 30.1646 | -96.716 | 263.47
9746 | 0.4 | 130.6 | 9689.1 | -75.05 | -653.17 | 425.46 | 1.05 | -0.32 | -133.19 | -160.65 | 94 | 9271.1 | 199689.03 | 3142990.32 | 30.1646 | -96.716 | 263.45
9840 | 0.4 | 164.4 | 9783.1 | -75.58 | -652.83 | 424.85 | 0.25 | 0 | 35.96 | 106.9 | 94 | 9365.1 | 199688.5 | 3142990.66 | 30.1646 | -96.716 | 263.4
9934 | 0.2 | 156 | 9877.1 | -76.05 | -652.67 | 424.42 | 0.22 | -0.21 | -8.94 | -171.78 | 94 | 9459.1 | 199688.03 | 3142990.82 | 30.1646 | -96.716 | 263.35
10028 | 0.6 | 293.6 | 9971.1 | -76 | -653.06 | 424.74 | 0.81 | 0.43 | 146.38 | 147.82 | 94 | 9553.1 | 199688.08 | 3142990.43 | 30.1646 | -96.716 | 263.36
10122 | 1.5 | 312.5 | 10065.08 | -74.97 | -654.42 | 426.43 | 1.01 | 0.96 | 20.11 | 30.67 | 94 | 9647.08 | 199689.11 | 3142989.07 | 30.1646 | -96.716 | 263.46
10215 | 6.7 | 309.8 | 10157.81 | -70.67 | -659.49 | 433.07 | 5.59 | 5.59 | -2.9 | -3.48 | 93 | 9739.81 | 199693.41 | 3142984 | 30.1646 | -96.716 | 263.88
10308 | 9.2 | 317.5 | 10249.91 | -61.72 | -668.68 | 445.9 | 2.92 | 2.69 | 8.28 | 26.92 | 93 | 9831.91 | 199702.36 | 3142974.81 | 30.1647 | -96.7161 | 264.73
10402 | 13.3 | 315.1 | 10342.09 | -48.51 | -681.39 | 464.21 | 4.39 | 4.36 | -2.55 | -7.69 | 94 | 9924.09 | 199715.57 | 3142962.1 | 30.1647 | -96.7161 | 265.93
10457 | 15.8 | 315.3 | 10395.32 | -38.71 | -691.13 | 478.01 | 4.55 | 4.55 | 0.36 | 1.25 | 55 | 9977.32 | 199725.37 | 3142952.36 | 30.1647 | -96.7161 | 266.79
10548 | 16.8 | 315.4 | 10482.66 | -20.54 | -709.08 | 503.53 | 1.1 | 1.1 | 0.11 | 1.66 | 91 | 10064.66 | 199743.54 | 3142934.41 | 30.1648 | -96.7162 | 268.34
10643 | 26.2 | 315.5 | 10570.95 | 4.25 | -733.47 | 538.28 | 9.89 | 9.89 | 0.11 | 0.27 | 95 | 10152.95 | 199768.33 | 3142910.02 | 30.1648 | -96.7163 | 270.33
10738 | 31.2 | 315 | 10654.25 | 36.63 | -765.59 | 583.86 | 5.27 | 5.26 | -0.53 | -2.97 | 95 | 10236.25 | 199800.71 | 3142877.9 | 30.1649 | -96.7164 | 272.74
10833 | 46.4 | 316.2 | 10728.07 | 79.11 | -807.04 | 643.15 | 16.02 | 16 | 1.26 | 3.31 | 95 | 10310.07 | 199843.19 | 3142836.45 | 30.1651 | -96.7165 | 275.6
10927 | 56 | 316.1 | 10786.91 | 131.87 | -857.73 | 716.22 | 10.21 | 10.21 | -0.11 | -0.5 | 94 | 10368.91 | 199895.95 | 3142785.76 | 30.1652 | -96.7167 | 278.74
11022 | 63 | 313.6 | 10835.1 | 189.51 | -915.77 | 797.98 | 7.71 | 7.37 | -2.63 | -17.75 | 95 | 10417.1 | 199953.59 | 3142727.72 | 30.1654 | -96.7168 | 281.69
11117 | 65.2 | 312 | 10876.59 | 247.56 | -978.47 | 883.43 | 2.77 | 2.32 | -1.68 | -33.55 | 95 | 10458.59 | 200011.64 | 3142665.02 | 30.1655 | -96.717 | 284.2
11212 | 67.8 | 312.4 | 10914.47 | 306.08 | -1043 | 970.53 | 2.76 | 2.74 | 0.42 | 8.11 | 95 | 10496.47 | 200070.16 | 3142600.49 | 30.1657 | -96.7172 | 286.35
11308 | 81.2 | 314.8 | 10940.07 | 369.77 | -1109.79 | 1062.81 | 14.16 | 13.96 | 2.5 | 10.14 | 96 | 10522.07 | 200133.85 | 3142533.7 | 30.1659 | -96.7174 | 288.43
11403 | 96 | 315.3 | 10942.39 | 436.8 | -1176.7 | 1157.47 | 15.59 | 15.58 | 0.53 | 1.95 | 95 | 10524.39 | 200200.88 | 3142466.79 | 30.1661 | -96.7176 | 290.37
11498 | 93 | 313.9 | 10934.93 | 503.29 | -1244.13 | 1252.13 | 3.48 | -3.16 | -1.47 | -154.99 | 95 | 10516.93 | 200267.37 | 3142399.36 | 30.1663 | -96.7178 | 292.02
11592 | 89.8 | 311.6 | 10932.64 | 567.06 | -1313.12 | 1346.08 | 4.19 | -3.4 | -2.45 | -144.27 | 94 | 10514.64 | 200331.14 | 3142330.37 | 30.1664 | -96.718 | 293.36
11687 | 90.6 | 311.7 | 10932.3 | 630.19 | -1384.11 | 1441.05 | 0.85 | 0.84 | 0.11 | 7.12 | 95 | 10514.3 | 200394.27 | 3142259.38 | 30.1666 | -96.7183 | 294.48
11781 | 90.1 | 312.2 | 10931.73 | 693.03 | -1454.02 | 1535.03 | 0.75 | -0.53 | 0.53 | 135 | 94 | 10513.73 | 200457.11 | 3142189.47 | 30.1668 | -96.7185 | 295.48
11876 | 93 | 313 | 10929.16 | 757.3 | -1523.91 | 1629.98 | 3.17 | 3.05 | 0.84 | 15.41 | 95 | 10511.16 | 200521.38 | 3142119.58 | 30.167 | -96.7187 | 296.42
11970 | 92.5 | 314.5 | 10924.65 | 822.23 | -1591.73 | 1723.86 | 1.68 | -0.53 | 1.6 | 108.42 | 94 | 10506.65 | 200586.31 | 3142051.76 | 30.1672 | -96.7189 | 297.32
12064 | 91.2 | 314 | 10921.62 | 887.78 | -1659.03 | 1817.79 | 1.48 | -1.38 | -0.53 | -158.96 | 94 | 10503.62 | 200651.86 | 3141984.46 | 30.1674 | -96.7191 | 298.15
12158 | 91.4 | 314.2 | 10919.48 | 953.18 | -1726.52 | 1911.75 | 0.3 | 0.21 | 0.21 | 44.99 | 94 | 10501.48 | 200717.26 | 3141916.97 | 30.1675 | -96.7193 | 298.9
12253 | 91.7 | 314.3 | 10916.91 | 1019.45 | -1794.54 | 2006.7 | 0.33 | 0.32 | 0.11 | 18.43 | 95 | 10498.91 | 200783.53 | 3141848.95 | 30.1677 | -96.7195 | 299.6
12347 | 93.1 | 314.8 | 10912.98 | 1085.33 | -1861.47 | 2100.58 | 1.58 | 1.49 | 0.53 | 19.63 | 94 | 10494.98 | 200849.41 | 3141782.02 | 30.1679 | -96.7197 | 300.24
12441 | 90.4 | 314.1 | 10910.11 | 1151.12 | -1928.53 | 2194.51 | 2.97 | -2.87 | -0.74 | -165.46 | 94 | 10492.11 | 200915.2 | 3141714.96 | 30.1681 | -96.7199 | 300.83
12536 | 91 | 313.8 | 10908.95 | 1217.05 | -1996.92 | 2289.49 | 0.71 | 0.63 | -0.32 | -26.56 | 95 | 10490.95 | 200981.13 | 3141646.57 | 30.1683 | -96.7201 | 301.36
12631 | 93.8 | 312.1 | 10904.97 | 1281.71 | -2066.39 | 2384.39 | 3.45 | 2.95 | -1.79 | -31.21 | 95 | 10486.97 | 201045.79 | 3141577.1 | 30.1685 | -96.7204 | 301.81
12727 | 93.2 | 312.4 | 10899.11 | 1346.14 | -2137.31 | 2480.2 | 0.7 | -0.62 | 0.31 | 153.47 | 96 | 10481.11 | 201110.22 | 3141506.18 | 30.1687 | -96.7206 | 302.2
12822 | 94 | 312.2 | 10893.14 | 1409.95 | -2207.44 | 2575 | 0.87 | 0.84 | -0.21 | -14 | 95 | 10475.14 | 201174.03 | 3141436.05 | 30.1688 | -96.7208 | 302.57
12918 | 95 | 312 | 10885.61 | 1474.11 | -2278.45 | 2670.69 | 1.06 | 1.04 | -0.21 | -11.27 | 96 | 10467.61 | 201238.19 | 3141365.04 | 30.169 | -96.721 | 302.9
13014 | 94.1 | 310.4 | 10877.99 | 1537.14 | -2350.45 | 2766.33 | 1.91 | -0.94 | -1.67 | -119.37 | 96 | 10459.99 | 201301.22 | 3141293.04 | 30.1692 | -96.7212 | 303.18
13109 | 92.3 | 312.7 | 10872.69 | 1600.05 | -2421.43 | 2861.14 | 3.07 | -1.89 | 2.42 | 128.02 | 95 | 10454.69 | 201364.13 | 3141222.06 | 30.1694 | -96.7214 | 303.46
13203 | 93 | 313.2 | 10868.35 | 1664.03 | -2490.15 | 2955.03 | 0.91 | 0.74 | 0.53 | 35.5 | 94 | 10450.35 | 201428.11 | 3141153.34 | 30.1696 | -96.7217 | 303.75
13299 | 93.7 | 313.5 | 10862.74 | 1729.82 | -2559.84 | 3050.87 | 0.79 | 0.73 | 0.31 | 23.15 | 96 | 10444.74 | 201493.9 | 3141083.65 | 30.1698 | -96.7219 | 304.05
13395 | 91.9 | 312.8 | 10858.05 | 1795.39 | -2629.8 | 3146.75 | 2.01 | -1.88 | -0.73 | -158.75 | 96 | 10440.05 | 201559.47 | 3141013.69 | 30.1699 | -96.7221 | 304.32
13489 | 92.5 | 312.7 | 10854.44 | 1859.15 | -2698.77 | 3240.68 | 0.65 | 0.64 | -0.11 | -9.45 | 94 | 10436.44 | 201623.23 | 3140944.72 | 30.1701 | -96.7223 | 304.56
13583 | 92.3 | 311.9 | 10850.5 | 1922.36 | -2768.23 | 3334.59 | 0.88 | -0.21 | -0.85 | -104.03 | 94 | 10432.5 | 201686.44 | 3140875.26 | 30.1703 | -96.7225 | 304.78
13679 | 93.2 | 311.8 | 10845.9 | 1986.33 | -2839.66 | 3430.45 | 0.94 | 0.94 | -0.1 | -6.33 | 96 | 10427.9 | 201750.41 | 3140803.83 | 30.1705 | -96.7227 | 304.97
13774 | 92.5 | 312.6 | 10841.17 | 2050.07 | -2909.95 | 3525.32 | 1.12 | -0.74 | 0.84 | 131.2 | 95 | 10423.17 | 201814.15 | 3140733.54 | 30.1707 | -96.7229 | 305.16
13868 | 93 | 312.9 | 10836.66 | 2113.8 | -2978.9 | 3619.21 | 0.62 | 0.53 | 0.32 | 30.93 | 94 | 10418.66 | 201877.88 | 3140664.59 | 30.1708 | -96.7232 | 305.36
13963 | 91.7 | 311.5 | 10832.77 | 2177.56 | -3049.21 | 3714.11 | 2.01 | -1.37 | -1.47 | -132.87 | 95 | 10414.77 | 201941.64 | 3140594.28 | 30.171 | -96.7234 | 305.53
14058 | 91.7 | 311.1 | 10829.95 | 2240.23 | -3120.55 | 3809.02 | 0.42 | 0 | -0.42 | -89.99 | 95 | 10411.95 | 202004.31 | 3140522.94 | 30.1712 | -96.7236 | 305.67
14154 | 92.3 | 311.6 | 10826.6 | 2303.61 | -3192.57 | 3904.92 | 0.81 | 0.62 | 0.52 | 39.78 | 96 | 10408.6 | 202067.69 | 3140450.92 | 30.1714 | -96.7238 | 305.81
14248 | 93.8 | 311.7 | 10821.6 | 2365.99 | -3262.71 | 3998.75 | 1.6 | 1.6 | 0.11 | 3.81 | 94 | 10403.6 | 202130.07 | 3140380.78 | 30.1716 | -96.724 | 305.95
14342 | 91.8 | 313.4 | 10817 | 2429.48 | -3331.87 | 4092.63 | 2.79 | -2.13 | 1.81 | 139.62 | 94 | 10399 | 202193.56 | 3140311.62 | 30.1717 | -96.7242 | 306.1
14437 | 90.8 | 313.8 | 10814.85 | 2494.97 | -3400.64 | 4187.6 | 1.13 | -1.05 | 0.42 | 158.2 | 95 | 10396.85 | 202259.05 | 3140242.85 | 30.1719 | -96.7245 | 306.27
14531 | 91.5 | 314.1 | 10812.96 | 2560.2 | -3468.3 | 4281.57 | 0.81 | 0.74 | 0.32 | 23.19 | 94 | 10394.96 | 202324.28 | 3140175.19 | 30.1721 | -96.7247 | 306.43
14626 | 92.7 | 314.4 | 10809.48 | 2626.44 | -3536.31 | 4376.48 | 1.3 | 1.26 | 0.32 | 14.02 | 95 | 10391.48 | 202390.52 | 3140107.18 | 30.1723 | -96.7249 | 306.6
14721 | 94.4 | 314.6 | 10803.6 | 2692.9 | -3603.93 | 4471.27 | 1.8 | 1.79 | 0.21 | 6.69 | 95 | 10385.6 | 202456.98 | 3140039.56 | 30.1725 | -96.7251 | 306.77
14816 | 93.6 | 313.4 | 10796.97 | 2758.73 | -3672.1 | 4566.02 | 1.52 | -0.84 | -1.26 | -123.71 | 95 | 10378.97 | 202522.81 | 3139971.39 | 30.1727 | -96.7253 | 306.92
14912 | 94.4 | 313.2 | 10790.28 | 2824.41 | -3741.8 | 4661.79 | 0.86 | 0.83 | -0.21 | -14 | 96 | 10372.28 | 202588.49 | 3139901.69 | 30.1729 | -96.7255 | 307.05
15008 | 95.5 | 313.2 | 10781.99 | 2889.88 | -3811.52 | 4757.43 | 1.15 | 1.15 | 0 | 0 | 96 | 10363.99 | 202653.96 | 3139831.97 | 30.1731 | -96.7257 | 307.17
15104 | 92.9 | 313.2 | 10774.96 | 2955.41 | -3881.3 | 4853.16 | 2.71 | -2.71 | 0 | 180 | 96 | 10356.96 | 202719.49 | 3139762.19 | 30.1732 | -96.7259 | 307.29
15200 | 90.5 | 313.5 | 10772.11 | 3021.28 | -3951.08 | 4949.11 | 2.52 | -2.5 | 0.31 | 172.87 | 96 | 10354.11 | 202785.36 | 3139692.41 | 30.1734 | -96.7261 | 307.4
15295 | 90.6 | 313.8 | 10771.2 | 3086.85 | -4019.81 | 5044.1 | 0.33 | 0.11 | 0.32 | 71.56 | 95 | 10353.2 | 202850.93 | 3139623.68 | 30.1736 | -96.7264 | 307.52
15391 | 91.7 | 313.9 | 10769.28 | 3153.34 | -4089.03 | 5140.08 | 1.15 | 1.15 | 0.1 | 5.19 | 96 | 10351.28 | 202917.42 | 3139554.46 | 30.1738 | -96.7266 | 307.64
15487 | 93 | 314.1 | 10765.34 | 3219.97 | -4158.03 | 5235.98 | 1.37 | 1.35 | 0.21 | 8.74 | 96 | 10347.34 | 202984.05 | 3139485.46 | 30.174 | -96.7268 | 307.75
15584 | 91.5 | 312.7 | 10761.53 | 3286.56 | -4228.45 | 5332.9 | 2.11 | -1.55 | -1.44 | -136.97 | 97 | 10343.53 | 203050.64 | 3139415.04 | 30.1742 | -96.727 | 307.86
15678 | 93.5 | 313.5 | 10757.43 | 3350.72 | -4297.01 | 5426.81 | 2.29 | 2.13 | 0.85 | 21.77 | 94 | 10339.43 | 203114.8 | 3139346.48 | 30.1744 | -96.7272 | 307.95
15773 | 94.5 | 313.7 | 10750.8 | 3416.08 | -4365.64 | 5521.57 | 1.07 | 1.05 | 0.21 | 11.28 | 95 | 10332.8 | 203180.16 | 3139277.85 | 30.1745 | -96.7274 | 308.04
15870 | 95.6 | 313.7 | 10742.27 | 3482.83 | -4435.49 | 5618.19 | 1.13 | 1.13 | 0 | 0 | 97 | 10324.27 | 203246.91 | 3139208 | 30.1747 | -96.7276 | 308.14
15966 | 94.7 | 314.3 | 10733.65 | 3549.25 | -4504.27 | 5713.79 | 1.13 | -0.94 | 0.62 | 146.39 | 96 | 10315.65 | 203313.33 | 3139139.22 | 30.1749 | -96.7278 | 308.24
16041 | 94.7 | 314.3 | 10727.5 | 3601.45 | -4557.77 | 5788.52 | 0 | 0 | 0 | 0 | 75 | 10309.5 | 203365.53 | 3139085.72 | 30.1751 | -96.728 | 308.32

## 11_2_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 1 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/02/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 13250 |  |  | Well Cost($): |  | 13250
|  |  |  | 24hr Summary: |  | Drill surface, run casing, cement same
|  |  |  | 24hr Lookahead: |  | Skid rig back to Yukon c 3H
Drilling Summary |  | 24Hr (BHA 1) |  | Run (BHA 1) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 105 |  | 105 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV:
End Depth (Usft): |  | 3170 |  | 3170 |  | OD (in): |  |  |  | 300: | 4 | YP:
Total Drilled (Usft): |  | 3065 |  | 3065 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): |  | 229 |  | 229 | [5 empty] | 100: | 2 | Chlorides:
Rotary Drilled (Usft): |  | 2836 |  | 2836 | [5 empty] | 6: | 1 | % Sand/Solids:
Drlg/Circ Hrs: |  | 4.90 / 3.38 |  | 4.90 / 3.38 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 1.28 |  | 1.28 |  | SN: |  | 43518 |  | 10s Gel: | 1 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 3.62 |  | 3.62 |  | Bit # |  |  |  | PH / Temp(F) | 0.0 / 117.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): |  | 784.15 / 178.44 |  | 784.15 / 178.44 |  | OD (in) / TFA: |  | 13.500 / 0.000
BRT Hrs: |  | 15.58 |  | 15.58 |  | Grade In:
% Slide: |  | 7.47 |  | 7.47 |  | Grade Out:
% Rotary: |  | 92.53 |  | 92.53 |  | Make / Model: |  | Baker Hughes / U616S
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
Bobby Guin |  | Jeff Wells |  | Kyle Novosad
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
13 1/2 Ulterra U616S 9 x 14s |  |  |  | 13.5 | 2.75 |  |  |  |  | 1.35 |  | 1.35
7/8 Lobe 5.9 Stage |  |  |  | 7.875 | [5 empty] | 37.27 |  | 38.62
13" Stabilizer |  |  |  | 7.813 | 2.813 |  |  |  |  | 7.45 |  | 46.07
NM Pony |  |  |  | 7.813 | 3.438 |  |  |  |  | 9.7 |  | 55.77
UBHO/Muleshoe |  |  |  | 7.688 | 2.75 |  |  |  |  | 3.9 |  | 59.67
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.6 |  | 89.27
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.89 |  | 119.16
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 24.21 |  | 143.37
Crossover (XT39 Pin x DS42 Box) |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.65 |  | 147.02
27 Stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2558.32 |  | 2705.34
NOV Shock Sub/ Agitator/ Safety Joint |  |  |  | 5 | 2 |  |  |  |  | 28.71 |  | 2734.05
2734.05
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800015 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 0 |  | 1.5 |  | 0 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
138 | 0.2 | 178.2 | 138 | -0.24 | 0.01 | 0.14 |  | 178.2 | -0.17 | 0.14 |  | 0 | 138
230 | 0.3 | 202.9 | 230 | -0.62 | -0.08 | 0.16 |  | 59.94 | -0.37 | 0.11 |  | 0 | 92
322 | 0.5 | 200.3 | 322 | -1.22 | -0.31 | 0.22 |  | -6.49 | -0.61 | 0.22 |  | 0 | 92
416 | 0.4 | 186.2 | 415.99 | -1.93 | -0.49 | 0.16 |  | -138.99 | -0.96 | -0.11 |  | 0 | 94
510 | 0.7 | 224.1 | 509.99 | -2.67 | -0.93 | 0.49 |  | 70.49 | -1.15 | 0.32 |  | 0 | 94
603 | 1.4 | 247.9 | 602.97 | -3.51 | -2.37 | 0.87 |  | 44.2 | -0.66 | 0.75 |  | 0 | 93
697 | 2.4 | 264.7 | 696.92 | -4.12 | -5.4 | 1.21 |  | 37.69 | 1.12 | 1.06 |  | 0 | 94
791 | 4 | 270.8 | 790.77 | -4.26 | -10.64 | 1.74 |  | 15.07 | 4.85 | 1.7 |  | 6.49 | 94
885 | 5 | 264.5 | 884.48 | -4.6 | -17.99 | 1.19 |  | -29.47 | 9.99 | 1.06 |  | -6.7 | 94
980 | 6.9 | 262.9 | 978.97 | -5.71 | -27.78 | 2.01 |  | -5.79 | 16.38 | 2 |  | -1.68 | 95
1074 | 8.7 | 267.2 | 1072.09 | -6.75 | -40.48 | 2.01 |  | 20.1 | 24.93 | 1.91 |  | 4.57 | 94
1167 | 10.2 | 266.7 | 1163.83 | -7.57 | -55.73 | 1.62 |  | -3.38 | 35.51 | 1.61 |  | -0.54 | 93
1261 | 10.7 | 266.7 | 1256.27 | -8.55 | -72.75 | 0.53 |  | 0 | 47.26 | 0.53 |  | 0 | 94
1355 | 10.8 | 266.9 | 1348.62 | -9.53 | -90.26 | 0.11 |  | 20.56 | 59.37 | 0.11 |  | 0.21 | 94
1448 | 10.5 | 266.8 | 1440.02 | -10.47 | -107.42 | 0.32 |  | -176.52 | 71.25 | -0.32 |  | -0.11 | 93
1543 | 10.3 | 267.4 | 1533.46 | -11.34 | -124.54 | 0.24 |  | 151.86 | 83.16 | -0.21 |  | 0.63 | 95
1637 | 10.2 | 268.3 | 1625.96 | -11.97 | -141.26 | 0.2 |  | 122.42 | 94.93 | -0.11 |  | 0.96 | 94
1731 | 10.8 | 268.2 | 1718.38 | -12.49 | -158.38 | 0.64 |  | -1.79 | 107.07 | 0.64 |  | -0.11 | 94
1825 | 11.1 | 267.8 | 1810.67 | -13.12 | -176.23 | 0.33 |  | -14.41 | 119.67 | 0.32 |  | -0.43 | 94
1918 | 10.6 | 267.7 | 1902.01 | -13.8 | -193.72 | 0.54 |  | -177.89 | 131.96 | -0.54 |  | -0.11 | 93
2013 | 10.4 | 268.1 | 1995.42 | -14.44 | -211.02 | 0.22 |  | 160.17 | 144.16 | -0.21 |  | 0.42 | 95
2106 | 10.2 | 267.8 | 2086.92 | -15.03 | -227.64 | 0.22 |  | -165.13 | 155.88 | -0.22 |  | -0.32 | 93
2199 | 9.9 | 267.1 | 2178.49 | -15.75 | -243.85 | 0.35 |  | -158.19 | 167.22 | -0.32 |  | -0.75 | 93
2293 | 9.5 | 266.7 | 2271.15 | -16.61 | -259.66 | 0.43 |  | -170.63 | 178.18 | -0.43 |  | -0.43 | 94
2387 | 10.5 | 266 | 2363.72 | -17.65 | -275.95 | 1.07 |  | -7.28 | 189.36 | 1.06 |  | -0.74 | 94
2480 | 10.9 | 263.7 | 2455.1 | -19.21 | -293.15 | 0.63 |  | -48.01 | 200.84 | 0.43 |  | -2.47 | 93
2574 | 10.5 | 262.5 | 2547.47 | -21.3 | -310.47 | 0.49 |  | -151.47 | 212.06 | -0.43 |  | -1.28 | 94
2668 | 10.1 | 262.5 | 2639.95 | -23.5 | -327.14 | 0.43 |  | 180 | 222.72 | -0.43 |  | 0 | 94
2763 | 9.8 | 263.3 | 2733.52 | -25.53 | -343.42 | 0.35 |  | 155.65 | 233.23 | -0.32 |  | 0.84 | 95
2857 | 10 | 262.5 | 2826.12 | -27.53 | -359.46 | 0.26 |  | -34.91 | 243.57 | 0.21 |  | -0.85 | 94
2951 | 9.8 | 262.6 | 2918.72 | -29.62 | -375.49 | 0.21 |  | 175.14 | 253.83 | -0.21 |  | 0.11 | 94
3094 | 9.2 | 260.6 | 3059.76 | -33.06 | -398.83 | 0.48 |  | -152.17 | 268.52 | -0.42 |  | -1.4 | 143
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 646.94 | 14.38 | 89.41 | 89 | 874.29 | 1308.33 | 1685.42 | 276 | 50000 | 50000 | 50000 | 10882.35 | 0
Run | 646.94 | 14.38 | 89.41 | 89 | 874.29 | 1308.33 | 1685.42 | 276 | 50000 | 50000 | 50000 | 10882.35 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Mob/DeMob |  |  |  |  | 11/02/2020 |  | 1 |  | 6000 |  | 1 | 6000
Directional & MWD / Gamma Services |  |  |  |  | 11/02/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/02/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 13250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/02/2020 | 00:00 | 01:45 | 1.75 | 105 | 105 | 0 | SUR |  | 24B | Standby for skid operations
11/02/2020 | 01:45 | 02:25 | 0.67 | 105 | 105 | 0 | SUR | 1: BHA 1 (Surface) | 6O | P/U BHA
11/02/2020 | 02:25 | 02:45 | 0.33 | 105 | 214 | 109 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/0.00 t/214.00, w/WOB 5.00,Flow 570.00, RPM 40.00, Press 500.00, Tq 5.00, ROP 642.00
11/02/2020 | 02:45 | 02:51 | 0.1 | 214 | 214 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 02:51 | 02:59 | 0.13 | 214 | 306 | 92 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/214.00 t/306.00, w/WOB 5.00,Flow 705, RPM 40.00, Press 500.00, Tq 5.00, ROP 690.00
11/02/2020 | 02:59 | 03:04 | 0.08 | 306 | 306 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 03:04 | 03:10 | 0.1 | 306 | 398 | 92 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/306.00 t/398.00, w/WOB 5.00,Flow 808, RPM 40.00, Press 1000, Tq 5.00, ROP 920.00
11/02/2020 | 03:10 | 03:15 | 0.08 | 398 | 398 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 03:15 | 03:19 | 0.07 | 398 | 492 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/398.00 t/492.00, w/WOB 10,Flow 900, RPM 100, Press 1400, Tq 120000, ROP 1410.00
11/02/2020 | 03:19 | 03:23 | 0.07 | 492 | 492 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 03:23 | 03:24 | 0.02 | 492 | 495 | 3 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/492.00 t/495.00, w/WOB 10,Flow 900, RPM 100, Press 1400, Tq 120000, ROP 180.00
11/02/2020 | 03:24 | 03:29 | 0.08 | 495 | 513 | 18 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/495.00 t/513.00, TF , w/WOB 10,Flow 900, Press 1400, Tq 0, ROP 216.00
11/02/2020 | 03:29 | 03:33 | 0.07 | 513 | 586 | 73 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/513.00 t/586.00, w/WOB 10,Flow 900, RPM 100, Press 1400, Tq 120000, ROP 1095.00
11/02/2020 | 03:33 | 03:37 | 0.07 | 586 | 586 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 03:37 | 03:42 | 0.08 | 586 | 602 | 16 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/586.00 t/602.00, TF , w/WOB 10.00,Flow 900.00, Press 1400.00, Tq 0, ROP 192.00
11/02/2020 | 03:42 | 03:46 | 0.07 | 602 | 679 | 77 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/602.00 t/679.00, w/WOB 10.00,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000, ROP 1155.00
11/02/2020 | 03:46 | 03:51 | 0.08 | 679 | 679 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 03:51 | 03:53 | 0.03 | 679 | 684 | 5 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/679.00 t/684.00, w/WOB 18,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000, ROP 150.00
11/02/2020 | 03:53 | 04:00 | 0.12 | 684 | 704 | 20 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/684.00 t/704.00, TF , w/WOB 18,Flow 900.00, Press 1400.00, Tq 0, ROP 171.43
11/02/2020 | 04:00 | 04:03 | 0.05 | 704 | 773 | 69 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/704.00 t/773.00, w/WOB 18,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000, ROP 1380.00
11/02/2020 | 04:03 | 04:05 | 0.03 | 773 | 773 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 04:05 | 04:06 | 0.02 | 773 | 778 | 5 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/773.00 t/778.00, w/WOB 18,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000, ROP 300.00
11/02/2020 | 04:06 | 04:13 | 0.12 | 778 | 798 | 20 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/778.00 t/798.00, TF , w/WOB 18,Flow 900.00, Press 1400.00, Tq 0, ROP 171.43
11/02/2020 | 04:13 | 04:18 | 0.08 | 798 | 867 | 69 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/798.00 t/867.00, w/WOB 18,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000, ROP 828.00
11/02/2020 | 04:18 | 04:22 | 0.07 | 867 | 867 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 04:22 | 04:24 | 0.03 | 867 | 872 | 5 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/867.00 t/872.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 150.00
11/02/2020 | 04:24 | 04:32 | 0.13 | 872 | 897 | 25 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/872.00 t/897.00, TF , w/WOB 18.00,Flow 900.00, Press 1400.00, Tq 12000.00, ROP 187.50
11/02/2020 | 04:32 | 04:35 | 0.05 | 897 | 961 | 64 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/897.00 t/961.00, w/WOB 18.00,Flow 900.00, RPM 100, Press 1400.00, Tq 12000.00, ROP 1280.00
11/02/2020 | 04:35 | 04:38 | 0.05 | 961 | 961 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 04:38 | 04:40 | 0.03 | 961 | 965 | 4 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/961.00 t/965.00, w/WOB 18.00,Flow 900.00, RPM 100, Press 1400.00, Tq 12000.00, ROP 120.00
11/02/2020 | 04:40 | 04:49 | 0.15 | 965 | 995 | 30 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/965.00 t/995.00, TF , w/WOB 18.00,Flow 900.00, Press 1400.00, Tq 0, ROP 200.00
11/02/2020 | 04:49 | 04:52 | 0.05 | 995 | 1056 | 61 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/995.00 t/1056.00, w/WOB 18.00,Flow 900.00, RPM 100, Press 1400.00, Tq 12000.00, ROP 1220.00
11/02/2020 | 04:52 | 04:55 | 0.05 | 1056 | 1056 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 04:55 | 04:57 | 0.03 | 1056 | 1061 | 5 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1056.00 t/1061.00, w/WOB 18.00,Flow 900.00, RPM 100, Press 1400.00, Tq 12000.00, ROP 150.00
11/02/2020 | 04:57 | 05:05 | 0.13 | 1061 | 1091 | 30 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/1061.00 t/1091.00, TF , w/WOB 18.00,Flow 900.00, Press 1400.00, Tq 0, ROP 225.00
11/02/2020 | 05:05 | 05:09 | 0.07 | 1091 | 1150 | 59 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1091.00 t/1150.00, w/WOB 18.00,Flow 900.00, RPM 100, Press 1400.00, Tq 12000.00, ROP 885.00
11/02/2020 | 05:09 | 05:12 | 0.05 | 1150 | 1150 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 05:12 | 05:13 | 0.02 | 1150 | 1154 | 4 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1150.00 t/1154.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 240.00
11/02/2020 | 05:13 | 05:20 | 0.12 | 1154 | 1179 | 25 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/1154.00 t/1179.00, TF , w/WOB 18.00,Flow 900.00, Press 1400.00, Tq 0, ROP 214.29
11/02/2020 | 05:20 | 05:23 | 0.05 | 1179 | 1243 | 64 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1179.00 t/1243.00, w/WOB 18.00,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 1280.00
11/02/2020 | 05:23 | 05:26 | 0.05 | 1243 | 1243 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 05:26 | 05:30 | 0.07 | 1243 | 1337 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1243.00 t/1337.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 1410.00
11/02/2020 | 05:30 | 05:33 | 0.05 | 1337 | 1337 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 05:33 | 05:39 | 0.1 | 1337 | 1431 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1337.00 t/1431.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 940.00
11/02/2020 | 05:39 | 05:43 | 0.07 | 1431 | 1431 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 05:43 | 05:50 | 0.12 | 1431 | 1524 | 93 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1431.00 t/1524.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 797.14
11/02/2020 | 05:50 | 05:53 | 0.05 | 1524 | 1524 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 05:53 | 05:57 | 0.07 | 1524 | 1619 | 95 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1524.00 t/1619.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 1425.00
11/02/2020 | 05:57 | 06:01 | 0.07 | 1619 | 1619 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 06:01 | 06:06 | 0.08 | 1619 | 1713 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1619.00 t/1713.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 1128.00
11/02/2020 | 06:06 | 06:10 | 0.07 | 1713 | 1713 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 06:10 | 06:11 | 0.02 | 1713 | 1725 | 12 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1713.00 t/1725.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 720.00
11/02/2020 | 06:11 | 06:17 | 0.1 | 1725 | 1745 | 20 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/1725.00 t/1745.00, TF , w/WOB 5,Flow 900.00, Press 1950, Tq 0, ROP 200.00
11/02/2020 | 06:17 | 06:23 | 0.1 | 1745 | 1807 | 62 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1745.00 t/1807.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 620.00
11/02/2020 | 06:23 | 06:27 | 0.07 | 1807 | 1807 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 06:27 | 06:30 | 0.05 | 1807 | 1901 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1807.00 t/1901.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 1880.00
11/02/2020 | 06:30 | 06:34 | 0.07 | 1901 | 1901 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 06:34 | 06:39 | 0.08 | 1901 | 1994 | 93 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1901.00 t/1994.00, w/WOB 20,Flow 900.00, RPM 100.00, Press 1400.00, Tq 12000.00, ROP 1116.00
11/02/2020 | 06:39 | 06:43 | 0.07 | 1994 | 1994 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 06:43 | 06:47 | 0.07 | 1994 | 2089 | 95 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/1994.00 t/2089.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200, Tq 12000.00, ROP 1425.00
11/02/2020 | 06:47 | 06:51 | 0.07 | 2089 | 2089 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 06:51 | 06:56 | 0.08 | 2089 | 2182 | 93 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2089.00 t/2182.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200, Tq 12000.00, ROP 1116.00
11/02/2020 | 06:56 | 07:00 | 0.07 | 2182 | 2182 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 07:00 | 07:17 | 0.28 | 2182 | 2275 | 93 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2182.00 t/2275.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200, Tq 12000.00, ROP 328.24
11/02/2020 | 07:17 | 07:21 | 0.07 | 2275 | 2275 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 07:21 | 07:25 | 0.07 | 2275 | 2279 | 4 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2275.00 t/2279.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200, Tq 12000.00, ROP 60.00
11/02/2020 | 07:25 | 08:00 | 0.58 | 2279 | 2279 | 0 | SUR | 1: BHA 1 (Surface) | 24A | Work pipe
11/02/2020 | 08:00 | 08:25 | 0.42 | 2279 | 2279 | 0 | SUR | 1: BHA 1 (Surface) | 6B | POOH 5 stands.
11/02/2020 | 08:25 | 11:13 | 2.8 | 2279 | 2279 | 0 | SUR | 1: BHA 1 (Surface) | 5A | Circulate. Wait on cement on hte Liebsher 3H
11/02/2020 | 11:13 | 11:50 | 0.62 | 2279 | 2279 | 0 | SUR | 1: BHA 1 (Surface) | 6A | TIH to 2279
11/02/2020 | 11:50 | 12:00 | 0.17 | 2279 | 2369 | 90 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2279.00 t/2369.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 540.00
11/02/2020 | 12:00 | 12:04 | 0.07 | 2369 | 2369 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 12:04 | 12:05 | 0.02 | 2369 | 2375 | 6 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2369.00 t/2375.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 360.00
11/02/2020 | 12:05 | 12:20 | 0.25 | 2375 | 2400 | 25 | SUR | 1: BHA 1 (Surface) | 2J | Slide Drill f/2375.00 t/2400.00, TF 0.00, w/WOB 12.00,Flow 900.00, Press 1950.00, Tq 0.00, ROP 100.00
11/02/2020 | 12:20 | 12:27 | 0.12 | 2400 | 2463 | 63 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2400.00 t/2463.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 540.00
11/02/2020 | 12:27 | 12:32 | 0.08 | 2463 | 2463 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 12:32 | 12:37 | 0.08 | 2463 | 2556 | 93 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2463.00 t/2556.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 1116.00
11/02/2020 | 12:37 | 12:41 | 0.07 | 2556 | 2556 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 12:41 | 12:49 | 0.13 | 2556 | 2650 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2556.00 t/2650.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 705.00
11/02/2020 | 12:49 | 12:53 | 0.07 | 2650 | 2650 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 12:53 | 13:00 | 0.12 | 2650 | 2744 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2650.00 t/2744.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 805.71
11/02/2020 | 13:00 | 13:04 | 0.07 | 2744 | 2744 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 13:04 | 13:11 | 0.12 | 2744 | 2839 | 95 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2744.00 t/2839.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 814.29
11/02/2020 | 13:11 | 13:15 | 0.07 | 2839 | 2839 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 13:15 | 13:21 | 0.1 | 2839 | 2933 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2839.00 t/2933.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 940.00
11/02/2020 | 13:21 | 13:25 | 0.07 | 2933 | 2933 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 13:25 | 13:31 | 0.1 | 2933 | 3027 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/2933.00 t/3027.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 940.00
11/02/2020 | 13:31 | 13:35 | 0.07 | 3027 | 3027 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 13:35 | 13:44 | 0.15 | 3027 | 3121 | 94 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/3027.00 t/3121.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 626.67
11/02/2020 | 13:44 | 13:50 | 0.1 | 3121 | 3121 | 0 | SUR | 1: BHA 1 (Surface) | 10D | Survey & Connection
11/02/2020 | 13:50 | 13:52 | 0.03 | 3121 | 3170 | 49 | SUR | 1: BHA 1 (Surface) | 2K | Rotary Drill f/3121.00 t/3170.00, w/WOB 20.00,Flow 900.00, RPM 100.00, Press 2200.00, Tq 12000.00, ROP 1470.00
11/02/2020 | 13:52 | 13:55 | 0.05 | 3170 | 3170 | 0 | SUR | 1: BHA 1 (Surface) | 1G | MWD Survey @ TD of surface section
11/02/2020 | 13:55 | 14:30 | 0.58 | 3170 | 3170 | 0 | SUR | 1: BHA 1 (Surface) | 5A | Circulate
11/02/2020 | 14:30 | 16:35 | 2.08 | 3170 | 3170 | 0 | SUR | 1: BHA 1 (Surface) | 6B | POOH
11/02/2020 | 16:35 | 18:00 | 1.42 | 3170 | 3170 | 0 | SUR | 1: BHA 1 (Surface) | 6P | L/D BHA
11/02/2020 | 18:00 | 24:00 | 6 | 3170 | 3170 | 0 | SUR |  | 24B | Attended standby for casing operations
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_3_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 2 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/03/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  |  |  |  | Well Cost($): |  | 13250
|  |  |  | 24hr Summary: |  | Run casing, cement same
|  |  |  | 24hr Lookahead: |  | Prep and skid rig to Yukon C 3H
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3170 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV:
End Depth (Usft): |  | 3170 |  | 3170 |  | OD (in): |  |  |  | 300: | 4 | YP:
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): | [9 empty] | 100: | 2 | Chlorides:
Rotary Drilled (Usft): | [9 empty] | 6: | 1 | % Sand/Solids:
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 1 | Weight (ppg): | 9.2
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 117.00 | Mud Type: | WBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
Bobby Guin |  | Jeff Wells |  | Kyle Novosad
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 14.38 | 89.41 | 89 | 874.29 | 1308.33 | 1685.42 | 276 | 50000 | 50000 | 50000 | 10882.35 | 0
Run | 0 | 14.38 | 89.41 | 89 | 874.29 | 1308.33 | 1685.42 | 276 | 50000 | 50000 | 50000 | 10882.35 | 0
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/03/2020 | 00:00 | 05:00 | 5 | 3170 | 3170 | 0 | SUR |  | 24B | Attended standby for cement and skid operations
11/03/2020 | 05:00 | 24:00 | 19 | 3170 | 3170 | 0 | SUR |  | 24B | 24B: Standby
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_10_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 3 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/10/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 20500
|  |  |  | 24hr Summary: |  | Skid from Liebscher 3H; Handle BHA #2; TIH; Drill out float equipment; Begin Drilling Intermediate Section
|  |  |  | 24hr Lookahead: |  | Drill Ahead in Intermediate Section as per plan
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 3170 |  | 3170 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 5 | PV:
End Depth (Usft): |  | 5119 |  | 5119 |  | OD (in): |  |  |  | 300: | 4 | YP:
Total Drilled (Usft): |  | 1949 |  | 1949 |  | Weight (ft/lbs): |  |  |  | 200: | 3 | Viscosity: | 36
Slide Drilled (Usft): |  | 138 |  | 138 | [5 empty] | 100: | 2 | Chlorides:
Rotary Drilled (Usft): |  | 1811 |  | 1811 | [5 empty] | 6: | 1 | % Sand/Solids:
Drlg/Circ Hrs: |  | 3.72 / 0.87 |  | 3.72 / 0.87 |  | Bit Details |  |  |  | 3: | 1 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 0.85 |  | 0.85 |  | SN: |  | 53502 |  | 10s Gel: | 1 | Weight (ppg): | 9.2
Rotary Drilling Hrs: |  | 2.87 |  | 2.87 |  | Bit # |  | 1 |  | PH / Temp(F) | 0.0 / 117.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 631.74 / 162.35 |  | 631.74 / 162.35 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 8.83 |  | 8.83 |  | Grade In: |  | New
% Slide: |  | 7.08 |  | 7.08 |  | Grade Out: |  | 0-1-CT-S-X-1/16-TD
% Rotary: |  | 92.92 |  | 92.92 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jeff Wells |  | Billy McFarland |  | David LeBlanc | [5 empty] | Bobby Lewis
Bobby Guin |  | Jeff Wells |  | Kyle Novosad
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s - TFA 1.49 |  |  |  | 9.875 | 2.5 |  |  |  |  | 1.3 |  | 1.3
7/8 Lobe 5.9 Stage |  |  |  | 7.875 | [5 empty] | 37.69 |  | 38.99
NM Pony |  |  |  | 7.813 | 3.438 |  |  |  |  | 9.7 |  | 48.69
UBHO/Muleshoe |  |  |  | 7.688 | 2.75 |  |  |  |  | 3.9 |  | 52.59
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.6 |  | 82.19
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.89 |  | 112.08
4 1/2 XH P x 6 5/8 Reg B |  |  |  | 6.438 | 2.75 |  |  |  |  | 2.34 |  | 114.42
2 stands of 6 1/2 in Collars |  |  |  | 6.5 | 2.375 |  |  |  |  | 185.52 |  | 299.94
4 1/2 IF B x 4 1/2 XH P |  |  |  | 6.438 | 2.75 |  |  |  |  | 2.33 |  | 302.27
9 joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 276.52 |  | 578.79
22 stands of Drill pipe |  |  |  | 6 | 2.75 |  |  |  |  | 2064.94 |  | 2643.73
NOV Agitator and Shock Sub |  |  |  | 6.75 | 2 |  |  |  |  | 30.42 |  | 2674.15
2674.15
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800038 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.02 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
3262 | 8.9 | 260.6 | 3225.67 | -37.37 | -424.9 | 0.18 |  | 180 | 284.6 | -0.18 |  | 0 | 168
3356 | 11.3 | 258.7 | 3318.21 | -40.36 | -441.11 | 2.58 |  | -8.84 | 294.39 | 2.55 |  | -2.02 | 94
3450 | 11.7 | 256.5 | 3410.32 | -44.39 | -459.41 | 0.63 |  | -48.72 | 304.99 | 0.43 |  | -2.34 | 94
3543 | 11.7 | 255.3 | 3501.39 | -48.99 | -477.7 | 0.26 |  | -90.59 | 315.2 | 0 |  | -1.29 | 93
3637 | 11.9 | 257 | 3593.4 | -53.59 | -496.36 | 0.43 |  | 60.92 | 325.68 | 0.21 |  | 1.81 | 94
3732 | 12.1 | 255.7 | 3686.33 | -58.25 | -515.55 | 0.35 |  | -54.14 | 336.5 | 0.21 |  | -1.37 | 95
3826 | 12.3 | 257 | 3778.2 | -62.93 | -534.86 | 0.36 |  | 54.58 | 347.39 | 0.21 |  | 1.38 | 94
3920 | 10.8 | 262.5 | 3870.3 | -66.34 | -553.35 | 1.98 |  | 146.39 | 358.56 | -1.6 |  | 5.85 | 94
4015 | 10.2 | 262.8 | 3963.71 | -68.55 | -570.52 | 0.63 |  | 174.94 | 369.58 | -0.63 |  | 0.32 | 95
4108 | 10.3 | 261.4 | 4055.22 | -70.83 | -586.91 | 0.29 |  | -68.82 | 379.98 | 0.11 |  | -1.51 | 93
4202 | 8.5 | 265.5 | 4147.96 | -72.63 | -602.14 | 2.04 |  | 161.61 | 389.87 | -1.91 |  | 4.36 | 94
4296 | 6.5 | 273.8 | 4241.15 | -72.82 | -614.38 | 2.41 |  | 155.63 | 398.67 | -2.13 |  | 8.83 | 94
4389 | 6.6 | 276.2 | 4333.55 | -71.9 | -624.94 | 0.31 |  | 71.13 | 407.02 | 0.11 |  | 2.58 | 93
4483 | 4.3 | 275.5 | 4427.12 | -70.98 | -633.82 | 2.45 |  | -178.69 | 414.13 | -2.45 |  | -0.74 | 94
4577 | 1.6 | 276.3 | 4520.98 | -70.49 | -638.64 | 2.87 |  | 179.53 | 417.97 | -2.87 |  | 0.85 | 94
4672 | 0.7 | 20.5 | 4615.97 | -69.8 | -639.75 | 2 |  | 159.04 | 419.26 | -0.95 |  | 109.68 | 95
4766 | 1.5 | 41.7 | 4709.95 | -68.35 | -638.73 | 0.94 |  | 37.83 | 419.51 | 0.85 |  | 0 | 94
4861 | 1.5 | 22.8 | 4804.92 | -66.27 | -637.42 | 0.52 |  | -99.45 | 419.97 | 0 |  | -19.89 | 95
4954 | 0.7 | 267.7 | 4897.91 | -65.17 | -637.52 | 2.05 |  | -160.57 | 420.79 | -0.86 |  | -123.76 | 93
5048 | 1.3 | 234.7 | 4991.89 | -65.81 | -638.96 | 0.86 |  | -61.13 | 421.41 | 0.64 |  | 0 | 94
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 477.31 | 35.89 | 75.86 | 218 | 855.41 | 4445.95 | 3987.84 | 276 | 160.27 | 154 | 149.59 | 11413.79 | 0
Run | 477.31 | 35.89 | 75.86 | 218 | 855.41 | 4445.95 | 3987.84 | 276 | 160.27 | 154 | 149.59 | 11413.79 | 0
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/10/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/10/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/10/2020 | 00:00 | 14:00 | 14 | 3170 | 3170 | 0 | INT |  | 24B | Attended standby
11/10/2020 | 14:00 | 15:10 | 1.17 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 6O | P/U BHA
11/10/2020 | 15:10 | 15:20 | 0.17 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 5A | Shallow test MWD. Good test
11/10/2020 | 15:20 | 16:15 | 0.92 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 6A | TIH
11/10/2020 | 16:15 | 16:50 | 0.58 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 6L | P/U & Test Agitator
11/10/2020 | 16:50 | 17:45 | 0.92 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 8P | Rig Service & BOP Drill
11/10/2020 | 17:45 | 18:08 | 0.38 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 6A | TIH t/ 3,082
11/10/2020 | 18:08 | 18:30 | 0.37 | 3170 | 3170 | 0 | INT | 2: BHA 2 (Intermediate) | 5A | Drlg Shoe Track and Float Equipment
11/10/2020 | 18:30 | 18:32 | 0.03 | 3170 | 3180 | 10 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3170.00 t/3180.00, w/WOB 20,Flow 450, RPM 40, Press 1500, Tq 7000, ROP 300.00
11/10/2020 | 18:32 | 18:52 | 0.33 | 3180 | 3180 | 0 | INT | 2: BHA 2 (Intermediate) | 5A | Circ Btms Up
11/10/2020 | 18:52 | 19:05 | 0.22 | 3180 | 3180 | 0 | INT | 2: BHA 2 (Intermediate) | 15D | FIT t/ 406 psi
11/10/2020 | 19:05 | 19:17 | 0.2 | 3180 | 3240 | 60 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3180.00 t/3240.00, w/WOB 25,Flow 450.00, RPM 40.00, Press 1600, Tq 7000.00, ROP 300.00
11/10/2020 | 19:17 | 19:22 | 0.08 | 3240 | 3240 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Connection
11/10/2020 | 19:22 | 19:37 | 0.25 | 3240 | 3333 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3240.00 t/3333.00, w/WOB 32,Flow 450, RPM 40.00, Press 1600.00, Tq 7000.00, ROP 372.00
11/10/2020 | 19:37 | 19:41 | 0.07 | 3333 | 3333 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 19:41 | 19:46 | 0.08 | 3333 | 3349 | 16 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/3333.00 t/3349.00, TF , w/WOB 12,Flow 800, Press 1500, Tq 0, ROP 192.00
11/10/2020 | 19:46 | 19:55 | 0.15 | 3349 | 3427 | 78 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3349.00 t/3427.00, w/WOB 35,Flow 800.00, RPM 80, Press 3800, Tq 13.5, ROP 520.00
11/10/2020 | 19:55 | 19:58 | 0.05 | 3427 | 3427 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 19:58 | 20:08 | 0.17 | 3427 | 3521 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3427.00 t/3521.00, w/WOB 38,Flow 800.00, RPM 80.00, Press 3800.00, Tq 13500, ROP 564.00
11/10/2020 | 20:08 | 20:11 | 0.05 | 3521 | 3521 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 20:11 | 20:19 | 0.13 | 3521 | 3614 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3521.00 t/3614.00, w/WOB 42,Flow 900, RPM 80.00, Press 4700, Tq 11000, ROP 697.50
11/10/2020 | 20:19 | 20:22 | 0.05 | 3614 | 3614 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 20:22 | 20:28 | 0.1 | 3614 | 3708 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3614.00 t/3708.00, w/WOB 45,Flow 900.00, RPM 80.00, Press 4700.00, Tq 11000.00, ROP 940.00
11/10/2020 | 20:28 | 20:32 | 0.07 | 3708 | 3708 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 20:32 | 20:36 | 0.07 | 3708 | 3803 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3708.00 t/3803.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 4800, Tq 11000.00, ROP 1425.00
11/10/2020 | 20:36 | 20:40 | 0.07 | 3803 | 3803 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 20:40 | 20:46 | 0.1 | 3803 | 3897 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3803.00 t/3897.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 4800, Tq 11000.00, ROP 940.00
11/10/2020 | 20:46 | 20:49 | 0.05 | 3897 | 3897 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 20:49 | 20:50 | 0.02 | 3897 | 3900 | 3 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3897.00 t/3900.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 180.00
11/10/2020 | 20:50 | 20:58 | 0.13 | 3900 | 3918 | 18 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/3900.00 t/3918.00, TF , w/WOB 15,Flow 900.00, Press 4500, Tq 0, ROP 135.00
11/10/2020 | 20:58 | 21:02 | 0.07 | 3918 | 3991 | 73 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3918.00 t/3991.00, w/WOB 42,Flow 900.00, RPM 80, Press 4800, Tq 11000, ROP 1095.00
11/10/2020 | 21:02 | 21:05 | 0.05 | 3991 | 3991 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 21:05 | 21:12 | 0.12 | 3991 | 4086 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/3991.00 t/4086.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 814.29
11/10/2020 | 21:12 | 21:15 | 0.05 | 4086 | 4086 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 21:15 | 21:22 | 0.12 | 4086 | 4179 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4086.00 t/4179.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 797.14
11/10/2020 | 21:22 | 21:25 | 0.05 | 4179 | 4179 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 21:25 | 21:26 | 0.02 | 4179 | 4182 | 3 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4179.00 t/4182.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 180.00
11/10/2020 | 21:26 | 21:32 | 0.1 | 4182 | 4200 | 18 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/4182.00 t/4200.00, TF , w/WOB 25,Flow 900.00, Press 4500, Tq 0, ROP 180.00
11/10/2020 | 21:32 | 21:36 | 0.07 | 4200 | 4273 | 73 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4200.00 t/4273.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 1095.00
11/10/2020 | 21:36 | 21:39 | 0.05 | 4273 | 4273 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 21:39 | 21:40 | 0.02 | 4273 | 4275 | 2 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4273.00 t/4275.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 120.00
11/10/2020 | 21:40 | 21:46 | 0.1 | 4275 | 4293 | 18 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/4275.00 t/4293.00, TF , w/WOB 25,Flow 900.00, Press 4500, Tq 0, ROP 180.00
11/10/2020 | 21:46 | 21:53 | 0.12 | 4293 | 4367 | 74 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4293.00 t/4367.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 11000.00, ROP 634.29
11/10/2020 | 21:53 | 21:56 | 0.05 | 4367 | 4367 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 21:56 | 22:03 | 0.12 | 4367 | 4460 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4367.00 t/4460.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 12500, ROP 797.14
11/10/2020 | 22:03 | 22:06 | 0.05 | 4460 | 4460 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 22:06 | 22:07 | 0.02 | 4460 | 4462 | 2 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4460.00 t/4462.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 4800.00, Tq 12500, ROP 120.00
11/10/2020 | 22:07 | 22:13 | 0.1 | 4462 | 4480 | 18 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/4462.00 t/4480.00, TF , w/WOB 18,Flow 900.00, Press 4500, Tq 0, ROP 180.00
11/10/2020 | 22:13 | 22:17 | 0.07 | 4480 | 4554 | 74 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4480.00 t/4554.00, w/WOB 42,Flow 900.00, RPM 80, Press 4800, Tq 12500, ROP 1110.00
11/10/2020 | 22:17 | 22:20 | 0.05 | 4554 | 4554 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 22:20 | 22:21 | 0.02 | 4554 | 4558 | 4 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4554.00 t/4558.00, w/WOB 42,Flow 900.00, RPM 80, Press 4800, Tq 12500, ROP 240.00
11/10/2020 | 22:21 | 22:28 | 0.12 | 4558 | 4576 | 18 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/4558.00 t/4576.00, TF , w/WOB 15,Flow 900.00, Press 4500.00, Tq 0.00, ROP 154.29
11/10/2020 | 22:28 | 22:34 | 0.1 | 4576 | 4648 | 72 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4576.00 t/4648.00, w/WOB 42,Flow 900.00, RPM 80, Press 5000, Tq 12500, ROP 720.00
11/10/2020 | 22:34 | 22:37 | 0.05 | 4648 | 4648 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 22:37 | 22:38 | 0.02 | 4648 | 4652 | 4 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4648.00 t/4652.00, w/WOB 42,Flow 900.00, RPM 80, Press 5000, Tq 12500, ROP 240.00
11/10/2020 | 22:38 | 22:43 | 0.08 | 4652 | 4668 | 16 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/4652.00 t/4668.00, TF , w/WOB 15.00,Flow 900.00, Press 4500.00, Tq 0.00, ROP 192.00
11/10/2020 | 22:43 | 22:52 | 0.15 | 4668 | 4743 | 75 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4668.00 t/4743.00, w/WOB 45,Flow 900.00, RPM 80, Press 5000, Tq 12500, ROP 500.00
11/10/2020 | 22:52 | 22:55 | 0.05 | 4743 | 4743 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 22:55 | 23:04 | 0.15 | 4743 | 4837 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4743.00 t/4837.00, w/WOB 45,Flow 900.00, RPM 80, Press 5000, Tq 12500, ROP 626.67
11/10/2020 | 23:04 | 23:07 | 0.05 | 4837 | 4837 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 23:07 | 23:18 | 0.18 | 4837 | 4932 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4837.00 t/4932.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5000.00, Tq 12500.00, ROP 518.18
11/10/2020 | 23:18 | 23:22 | 0.07 | 4932 | 4932 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 23:22 | 23:23 | 0.02 | 4932 | 4940 | 8 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4932.00 t/4940.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5000.00, Tq 12500.00, ROP 480.00
11/10/2020 | 23:23 | 23:31 | 0.13 | 4940 | 4956 | 16 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/4940.00 t/4956.00, TF , w/WOB 15,Flow 900.00, Press 5000.00, Tq 0, ROP 120.00
11/10/2020 | 23:31 | 23:40 | 0.15 | 4956 | 5025 | 69 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/4956.00 t/5025.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5000.00, Tq 13000, ROP 460.00
11/10/2020 | 23:40 | 23:44 | 0.07 | 5025 | 5025 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/10/2020 | 23:44 | 23:53 | 0.15 | 5025 | 5119 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5025.00 t/5119.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5000.00, Tq 13000, ROP 626.67
11/10/2020 | 23:53 | 24:00 | 0.12 | 5119 | 5119 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_11_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 4 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/11/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 27750
|  |  |  | 24hr Summary: |  | Drilling Ahead in Intermediate Section as per plan
|  |  |  | 24hr Lookahead: |  | Continue Drilling Intermediate Section t/ Section TD
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 5119 |  | 3170 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10286 |  | 10286 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 5167 |  | 7116 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 42
Slide Drilled (Usft): |  | 268 |  | 406 | [5 empty] | 100: | 11 | Chlorides: | 50000
Rotary Drilled (Usft): |  | 4899 |  | 6710 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.25 / 8.30
Drlg/Circ Hrs: |  | 18.92 / 0.00 |  | 22.63 / 0.87 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 4.8 |  | 5.65 |  | SN: |  | 53502 |  | 10s Gel: | 5 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 14.12 |  | 16.98 |  | Bit # |  | 1 |  | PH / Temp(F) | 1.9 / 216.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 347.04 / 55.83 |  | 395.09 / 71.86 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 24 |  | 32.83 |  | Grade In: |  | New
% Slide: |  | 5.19 |  | 5.71 |  | Grade Out: |  | 0-1-CT-S-X-1/16-TD
% Rotary: |  | 94.81 |  | 94.29 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jeff Wells |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
Bobby Guin |  | Billy McFarland |  | Kyle Novosad
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s - TFA 1.49 |  |  |  | 9.875 | 2.5 |  |  |  |  | 1.3 |  | 1.3
7/8 Lobe 5.9 Stage |  |  |  | 7.875 | [5 empty] | 37.69 |  | 38.99
NM Pony |  |  |  | 7.813 | 3.438 |  |  |  |  | 9.7 |  | 48.69
UBHO/Muleshoe |  |  |  | 7.688 | 2.75 |  |  |  |  | 3.9 |  | 52.59
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.6 |  | 82.19
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.89 |  | 112.08
4 1/2 XH P x 6 5/8 Reg B |  |  |  | 6.438 | 2.75 |  |  |  |  | 2.34 |  | 114.42
2 stands of 6 1/2 in Collars |  |  |  | 6.5 | 2.375 |  |  |  |  | 185.52 |  | 299.94
4 1/2 IF B x 4 1/2 XH P |  |  |  | 6.438 | 2.75 |  |  |  |  | 2.33 |  | 302.27
9 joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 276.52 |  | 578.79
22 stands of Drill pipe |  |  |  | 6 | 2.75 |  |  |  |  | 2064.94 |  | 2643.73
NOV Agitator and Shock Sub |  |  |  | 6.75 | 2 |  |  |  |  | 30.42 |  | 2674.15
2674.15
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800038 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.02 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
5142 | 1.3 | 222.2 | 5085.87 | -67.22 | -640.55 | 0.3 |  | -96.25 | 421.61 | 0 |  | 0 | 94
5236 | 1.2 | 249.1 | 5179.85 | -68.36 | -642.19 | 0.63 |  | 112.94 | 422.02 | -0.11 |  | 0 | 94
5329 | 1.4 | 245.8 | 5272.82 | -69.17 | -644.13 | 0.23 |  | -22.18 | 422.89 | 0.22 |  | 0 | 93
5423 | 1.7 | 242 | 5366.79 | -70.3 | -646.41 | 0.34 |  | -20.82 | 423.78 | 0.32 |  | 0 | 94
5518 | 0.8 | 246.3 | 5461.77 | -71.23 | -648.26 | 0.95 |  | 176.2 | 424.5 | -0.95 |  | 4.53 | 95
5611 | 0.4 | 246.8 | 5554.76 | -71.62 | -649.15 | 0.43 |  | 179.5 | 424.88 | -0.43 |  | 0 | 93
5705 | 0.5 | 261 | 5648.76 | -71.81 | -649.86 | 0.16 |  | 55.36 | 425.27 | 0.11 |  | 0 | 94
5800 | 0.7 | 268.2 | 5743.75 | -71.89 | -650.85 | 0.22 |  | 24.28 | 425.93 | 0.21 |  | 0 | 95
5894 | 0.9 | 288.2 | 5837.74 | -71.68 | -652.13 | 0.36 |  | 64.66 | 427.01 | 0.21 |  | 0 | 94
5988 | 0.6 | 64.1 | 5931.74 | -71.23 | -652.38 | 1.48 |  | 162.58 | 427.5 | -0.32 |  | 0 | 94
6083 | 0.8 | 101.4 | 6026.73 | -71.15 | -651.29 | 0.51 |  | 85.71 | 426.76 | 0.21 |  | 0 | 95
6176 | 1.2 | 105.3 | 6119.72 | -71.53 | -649.71 | 0.44 |  | 11.61 | 425.34 | 0.43 |  | 0 | 93
6271 | 0.6 | 102.4 | 6214.71 | -71.9 | -648.27 | 0.63 |  | -177.11 | 424.04 | -0.63 |  | 0 | 95
6364 | 1 | 125.7 | 6307.7 | -72.48 | -647.13 | 0.55 |  | 51.16 | 422.81 | 0.43 |  | 0 | 93
6459 | 0.7 | 142.7 | 6402.69 | -73.43 | -646.11 | 0.41 |  | 148.24 | 421.42 | -0.32 |  | 0 | 95
6553 | 0.6 | 94.5 | 6496.68 | -73.92 | -645.27 | 0.57 |  | -123.86 | 420.47 | -0.11 |  | 0 | 94
6647 | 0.6 | 88.7 | 6590.68 | -73.95 | -644.28 | 0.06 |  | -92.9 | 419.73 | 0 |  | 0 | 94
6741 | 0.2 | 161.6 | 6684.67 | -74.09 | -643.74 | 0.61 |  | 160.55 | 419.24 | -0.43 |  | 0 | 94
6835 | 0.3 | 27.6 | 6778.67 | -74.03 | -643.58 | 0.49 |  | -152.15 | 419.16 | 0.11 |  | 0 | 94
6929 | 0.5 | 61.1 | 6872.67 | -73.61 | -643.1 | 0.32 |  | 67.03 | 419.1 | 0.21 |  | 0 | 94
7023 | 0.4 | 53.1 | 6966.67 | -73.22 | -642.48 | 0.13 |  | -151.82 | 418.91 | -0.11 |  | 0 | 94
7118 | 0.5 | 10 | 7061.67 | -72.61 | -642.14 | 0.36 |  | -95.84 | 419.08 | 0.11 |  | 0 | 95
7212 | 0.1 | 356.8 | 7155.67 | -72.13 | -642.08 | 0.43 |  | -176.75 | 419.37 | -0.43 |  | 0 | 94
7305 | 0.5 | 306 | 7248.66 | -71.81 | -642.41 | 0.48 |  | -60.86 | 419.83 | 0.43 |  | 0 | 93
7399 | 0.5 | 334.2 | 7342.66 | -71.2 | -642.92 | 0.26 |  | 104.1 | 420.62 | 0 |  | 0 | 94
7493 | 0.7 | 331.5 | 7436.66 | -70.32 | -643.37 | 0.21 |  | -9.4 | 421.55 | 0.21 |  | 0 | 94
7587 | 1.1 | 307.1 | 7530.64 | -69.27 | -644.37 | 0.58 |  | -56.41 | 422.99 | 0.43 |  | 0 | 94
7681 | 1.3 | 290.3 | 7624.62 | -68.36 | -646.09 | 0.43 |  | -68.96 | 424.87 | 0.21 |  | 0 | 94
7775 | 1.1 | 332 | 7718.6 | -67.19 | -647.51 | 0.93 |  | 123.19 | 426.7 | -0.21 |  | 0 | 94
7869 | 0.2 | 187.6 | 7812.6 | -66.56 | -647.96 | 1.35 |  | -174.73 | 427.46 | -0.96 |  | 0 | 94
7963 | 0.9 | 205.4 | 7906.59 | -67.39 | -648.29 | 0.76 |  | 22.72 | 427.14 | 0.74 |  | 0 | 94
8058 | 2.2 | 173.2 | 8001.56 | -69.87 | -648.4 | 1.6 |  | -50.63 | 425.52 | 1.37 |  | 0 | 95
8151 | 2.8 | 162.7 | 8094.47 | -73.81 | -647.51 | 0.81 |  | -42.68 | 422.18 | 0.65 |  | -11.29 | 93
8245 | 2.2 | 173.7 | 8188.38 | -77.8 | -646.63 | 0.81 |  | 146.76 | 418.81 | -0.64 |  | 11.7 | 94
8339 | 1.6 | 186.3 | 8282.33 | -80.9 | -646.58 | 0.77 |  | 151.34 | 416.66 | -0.64 |  | 13.4 | 94
8434 | 0.4 | 216.2 | 8377.31 | -82.48 | -646.92 | 1.34 |  | 170.96 | 415.82 | -1.26 |  | 31.47 | 95
8528 | 0.5 | 286.1 | 8471.31 | -82.63 | -647.51 | 0.56 |  | 115.92 | 416.15 | 0.11 |  | 0 | 94
8622 | 1.1 | 267.5 | 8565.3 | -82.56 | -648.8 | 0.69 |  | -32.89 | 417.14 | 0.64 |  | 0 | 94
8716 | 0.7 | 4 | 8659.29 | -82.03 | -649.66 | 1.46 |  | 149.47 | 418.14 | -0.43 |  | 0 | 94
8810 | 1.4 | 25.4 | 8753.28 | -80.42 | -649.13 | 0.84 |  | 40.24 | 418.85 | 0.74 |  | 0 | 94
8903 | 1.4 | 14.7 | 8846.25 | -78.29 | -648.35 | 0.28 |  | -95.35 | 419.73 | 0 |  | 0 | 93
8997 | 1.8 | 16.8 | 8940.21 | -75.77 | -647.64 | 0.43 |  | 9.39 | 420.94 | 0.43 |  | 0 | 94
9090 | 1.6 | 1.3 | 9033.17 | -73.07 | -647.18 | 0.54 |  | -121.13 | 422.45 | -0.22 |  | -16.67 | 93
9184 | 0.5 | 316.1 | 9127.16 | -71.46 | -647.44 | 1.38 |  | -164.13 | 423.73 | -1.17 |  | -48.09 | 94
9278 | 1.3 | 252.2 | 9221.15 | -71.49 | -648.74 | 1.24 |  | -86.47 | 424.66 | 0.85 |  | 0 | 94
9371 | 1.2 | 221.4 | 9314.13 | -72.55 | -650.39 | 0.72 |  | -113.66 | 425.15 | -0.11 |  | 0 | 93
9465 | 0.7 | 222.3 | 9408.11 | -73.71 | -651.42 | 0.53 |  | 178.74 | 425.11 | -0.53 |  | 0 | 94
9559 | 0.4 | 229.7 | 9502.11 | -74.35 | -652.06 | 0.33 |  | 170.36 | 425.14 | -0.32 |  | 0 | 94
9652 | 0.7 | 255.8 | 9595.1 | -74.7 | -652.86 | 0.41 |  | 53.41 | 425.48 | 0.32 |  | 0 | 93
9746 | 0.4 | 130.6 | 9689.1 | -75.05 | -653.17 | 1.05 |  | -160.65 | 425.46 | -0.32 |  | 0 | 94
9840 | 0.4 | 164.4 | 9783.1 | -75.58 | -652.83 | 0.25 |  | 106.9 | 424.85 | 0 |  | 0 | 94
9934 | 0.2 | 156 | 9877.1 | -76.05 | -652.67 | 0.22 |  | -171.78 | 424.42 | -0.21 |  | 0 | 94
10028 | 0.6 | 293.6 | 9971.1 | -76 | -653.06 | 0.81 |  | 147.82 | 424.74 | 0.43 |  | 0 | 94
10122 | 1.5 | 312.5 | 10065.08 | -74.97 | -654.42 | 1.01 |  | 30.67 | 426.43 | 0.96 |  | 0 | 94
10215 | 6.7 | 309.8 | 10157.81 | -70.67 | -659.49 | 5.59 |  | -3.48 | 433.07 | 5.59 |  | -2.9 | 93
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 273.15 | 37.72 | 78.03 | 227 | 896.67 | 5477.78 | 4697.22 | 276 | 229.17 | 212.14 | 199.79 | 17557.38 | 2000
Run | 314.4 | 37.1 | 77.33 | 224 | 882.66 | 5127.52 | 4456.42 | 276 | 205.78 | 192.4 | 182.75 | 15577.78 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/11/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/11/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/11/2020 | 00:00 | 00:09 | 0.15 | 5119 | 5213 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5119.00 t/5213.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5000.00, Tq 13000.00, ROP 626.67
11/11/2020 | 00:09 | 00:13 | 0.07 | 5213 | 5213 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 00:13 | 00:21 | 0.13 | 5213 | 5307 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5213.00 t/5307.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200, Tq 13000.00, ROP 705.00
11/11/2020 | 00:21 | 00:25 | 0.07 | 5307 | 5307 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 00:25 | 00:34 | 0.15 | 5307 | 5400 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5307.00 t/5400.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200, Tq 13000.00, ROP 620.00
11/11/2020 | 00:34 | 00:38 | 0.07 | 5400 | 5400 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 00:38 | 00:47 | 0.15 | 5400 | 5494 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5400.00 t/5494.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 13000.00, ROP 626.67
11/11/2020 | 00:47 | 00:52 | 0.08 | 5494 | 5494 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 00:52 | 00:53 | 0.02 | 5494 | 5503 | 9 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5494.00 t/5503.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 13000.00, ROP 540.00
11/11/2020 | 00:53 | 01:02 | 0.15 | 5503 | 5517 | 14 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/5503.00 t/5517.00, TF , w/WOB 18,Flow 900.00, Press 4800, Tq 0, ROP 93.33
11/11/2020 | 01:02 | 01:15 | 0.22 | 5517 | 5589 | 72 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5517.00 t/5589.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 13000.00, ROP 332.31
11/11/2020 | 01:15 | 01:19 | 0.07 | 5589 | 5589 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 01:19 | 01:28 | 0.15 | 5589 | 5682 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5589.00 t/5682.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 15000, ROP 620.00
11/11/2020 | 01:28 | 01:31 | 0.05 | 5682 | 5682 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 01:31 | 01:44 | 0.22 | 5682 | 5776 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5682.00 t/5776.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 15000, ROP 433.85
11/11/2020 | 01:44 | 01:48 | 0.07 | 5776 | 5776 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 01:48 | 01:58 | 0.17 | 5776 | 5871 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5776.00 t/5871.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 15000, ROP 570.00
11/11/2020 | 01:58 | 02:01 | 0.05 | 5871 | 5871 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 02:01 | 02:12 | 0.18 | 5871 | 5965 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5871.00 t/5965.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 15000.00, ROP 512.73
11/11/2020 | 02:12 | 02:16 | 0.07 | 5965 | 5965 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 02:16 | 02:18 | 0.03 | 5965 | 5972 | 7 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5965.00 t/5972.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 15000.00, ROP 210.00
11/11/2020 | 02:18 | 02:25 | 0.12 | 5972 | 5988 | 16 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/5972.00 t/5988.00, TF , w/WOB 20,Flow 900.00, Press 4800, Tq 0, ROP 137.14
11/11/2020 | 02:25 | 02:35 | 0.17 | 5988 | 6059 | 71 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/5988.00 t/6059.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5200.00, Tq 15000.00, ROP 426.00
11/11/2020 | 02:35 | 02:39 | 0.07 | 6059 | 6059 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 02:39 | 02:51 | 0.2 | 6059 | 6154 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6059.00 t/6154.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5400, Tq 18000, ROP 475.00
11/11/2020 | 02:51 | 02:55 | 0.07 | 6154 | 6154 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 02:55 | 03:07 | 0.2 | 6154 | 6247 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6154.00 t/6247.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 465.00
11/11/2020 | 03:07 | 03:10 | 0.05 | 6247 | 6247 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 03:10 | 03:20 | 0.17 | 6247 | 6342 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6247.00 t/6342.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 570.00
11/11/2020 | 03:20 | 03:24 | 0.07 | 6342 | 6342 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 03:24 | 03:35 | 0.18 | 6342 | 6435 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6342.00 t/6435.00, w/WOB 40,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 507.27
11/11/2020 | 03:35 | 03:39 | 0.07 | 6435 | 6435 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 03:39 | 03:51 | 0.2 | 6435 | 6530 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6435.00 t/6530.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 475.00
11/11/2020 | 03:51 | 03:54 | 0.05 | 6530 | 6530 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 03:54 | 04:05 | 0.18 | 6530 | 6624 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6530.00 t/6624.00, w/WOB 40.00,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 512.73
11/11/2020 | 04:05 | 04:10 | 0.08 | 6624 | 6624 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 04:10 | 04:21 | 0.18 | 6624 | 6718 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6624.00 t/6718.00, w/WOB 38,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 512.73
11/11/2020 | 04:21 | 04:25 | 0.07 | 6718 | 6718 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 04:25 | 04:36 | 0.18 | 6718 | 6812 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6718.00 t/6812.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 512.73
11/11/2020 | 04:36 | 04:40 | 0.07 | 6812 | 6812 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 04:40 | 04:51 | 0.18 | 6812 | 6906 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6812.00 t/6906.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5400.00, Tq 18000.00, ROP 512.73
11/11/2020 | 04:51 | 04:54 | 0.05 | 6906 | 6906 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 04:54 | 05:07 | 0.22 | 6906 | 7000 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/6906.00 t/7000.00, w/WOB 35,Flow 900.00, RPM 80.00, Press 5600, Tq 18000.00, ROP 433.85
11/11/2020 | 05:07 | 05:09 | 0.03 | 7000 | 7000 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 05:09 | 05:21 | 0.2 | 7000 | 7094 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7000.00 t/7094.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 470.00
11/11/2020 | 05:21 | 05:24 | 0.05 | 7094 | 7094 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 05:24 | 05:44 | 0.33 | 7094 | 7189 | 95 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7094.00 t/7189.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 285.00
11/11/2020 | 05:44 | 05:49 | 0.08 | 7189 | 7189 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 05:49 | 06:06 | 0.28 | 7189 | 7283 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7189.00 t/7283.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 331.76
11/11/2020 | 06:06 | 06:17 | 0.18 | 7283 | 7283 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 06:17 | 06:25 | 0.13 | 7283 | 7303 | 20 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7283.00 t/7303.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 150.00
11/11/2020 | 06:25 | 06:33 | 0.13 | 7303 | 7303 | 0 | INT | 2: BHA 2 (Intermediate) | 8D | Mud pump issues
11/11/2020 | 06:33 | 06:45 | 0.2 | 7303 | 7376 | 73 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7303.00 t/7376.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 365.00
11/11/2020 | 06:45 | 06:50 | 0.08 | 7376 | 7376 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 06:50 | 07:15 | 0.42 | 7376 | 7470 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7376.00 t/7470.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 225.60
11/11/2020 | 07:15 | 07:20 | 0.08 | 7470 | 7470 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 07:20 | 08:10 | 0.83 | 7470 | 7658 | 188 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7470.00 t/7658.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 225.60
11/11/2020 | 08:10 | 08:15 | 0.08 | 7658 | 7658 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 08:15 | 08:30 | 0.25 | 7658 | 7752 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7658.00 t/7752.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 376.00
11/11/2020 | 08:30 | 08:35 | 0.08 | 7752 | 7752 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 08:35 | 08:50 | 0.25 | 7752 | 7763 | 11 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/7752.00 t/7763.00, TF , w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0, ROP 44.00
11/11/2020 | 08:50 | 09:21 | 0.52 | 7763 | 7844 | 81 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7763.00 t/7844.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 156.77
11/11/2020 | 09:21 | 09:26 | 0.08 | 7844 | 7844 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 09:26 | 09:58 | 0.53 | 7844 | 7866 | 22 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/7844.00 t/7866.00, TF , w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0, ROP 41.25
11/11/2020 | 09:58 | 10:28 | 0.5 | 7866 | 7940 | 74 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7866.00 t/7940.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 148.00
11/11/2020 | 10:28 | 10:33 | 0.08 | 7940 | 7940 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 10:33 | 10:36 | 0.05 | 7940 | 7945 | 5 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7940.00 t/7945.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 100.00
11/11/2020 | 10:36 | 10:54 | 0.3 | 7945 | 7962 | 17 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/7945.00 t/7962.00, TF 140.00, w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0.00, ROP 56.67
11/11/2020 | 10:54 | 11:10 | 0.27 | 7962 | 8034 | 72 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/7962.00 t/8034.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 270.00
11/11/2020 | 11:10 | 11:19 | 0.15 | 8034 | 8034 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 11:19 | 11:52 | 0.55 | 8034 | 8059 | 25 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/8034.00 t/8059.00, TF 150.00, w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0.00, ROP 45.45
11/11/2020 | 11:52 | 12:08 | 0.27 | 8059 | 8129 | 70 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8059.00 t/8129.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 262.50
11/11/2020 | 12:08 | 12:12 | 0.07 | 8129 | 8129 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 12:12 | 12:42 | 0.5 | 8129 | 8316 | 187 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8129.00 t/8316.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 374.00
11/11/2020 | 12:42 | 12:47 | 0.08 | 8316 | 8316 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 12:47 | 13:03 | 0.27 | 8316 | 8410 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8316.00 t/8410.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 352.50
11/11/2020 | 13:03 | 13:08 | 0.08 | 8410 | 8410 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 13:08 | 13:11 | 0.05 | 8410 | 8412 | 2 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8410.00 t/8412.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 40.00
11/11/2020 | 13:11 | 13:29 | 0.3 | 8412 | 8428 | 16 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/8412.00 t/8428.00, TF 0.00, w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0.00, ROP 53.33
11/11/2020 | 13:29 | 13:45 | 0.27 | 8428 | 8505 | 77 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8428.00 t/8505.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 288.75
11/11/2020 | 13:45 | 13:50 | 0.08 | 8505 | 8505 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 13:50 | 14:03 | 0.22 | 8505 | 8599 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8505.00 t/8599.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 433.85
11/11/2020 | 14:03 | 14:08 | 0.08 | 8599 | 8599 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 14:08 | 14:23 | 0.25 | 8599 | 8695 | 96 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8599.00 t/8695.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 384.00
11/11/2020 | 14:23 | 14:28 | 0.08 | 8695 | 8695 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 14:28 | 14:33 | 0.08 | 8695 | 8704 | 9 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8695.00 t/8704.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 108.00
11/11/2020 | 14:33 | 15:00 | 0.45 | 8704 | 8729 | 25 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/8704.00 t/8729.00, TF 70.00, w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0.00, ROP 55.56
11/11/2020 | 15:00 | 15:16 | 0.27 | 8729 | 8787 | 58 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8729.00 t/8787.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 217.50
11/11/2020 | 15:16 | 15:21 | 0.08 | 8787 | 8787 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 15:21 | 15:38 | 0.28 | 8787 | 8881 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8787.00 t/8881.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 331.76
11/11/2020 | 15:38 | 15:42 | 0.07 | 8881 | 8881 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 15:42 | 15:55 | 0.22 | 8881 | 8974 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8881.00 t/8974.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 429.23
11/11/2020 | 15:55 | 16:00 | 0.08 | 8974 | 8974 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 16:00 | 16:15 | 0.25 | 8974 | 9068 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/8974.00 t/9068.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 376.00
11/11/2020 | 16:15 | 16:20 | 0.08 | 9068 | 9068 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 16:20 | 16:33 | 0.22 | 9068 | 9161 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9068.00 t/9161.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 429.23
11/11/2020 | 16:33 | 16:40 | 0.12 | 9161 | 9161 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 16:40 | 16:55 | 0.25 | 9161 | 9179 | 18 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/9161.00 t/9179.00, TF , w/WOB 35.00,Flow 900.00, Press 5600.00, Tq 0, ROP 72.00
11/11/2020 | 16:55 | 17:14 | 0.32 | 9179 | 9255 | 76 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9179.00 t/9255.00, w/WOB 35.00,Flow 900.00, RPM 80.00, Press 5600.00, Tq 18000.00, ROP 240.00
11/11/2020 | 17:14 | 17:54 | 0.67 | 9255 | 9255 | 0 | INT | 2: BHA 2 (Intermediate) | 8P | Rig Service
11/11/2020 | 17:54 | 17:58 | 0.07 | 9255 | 9255 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 17:58 | 18:10 | 0.2 | 9255 | 9349 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9255.00 t/9349.00, w/WOB 45,Flow 900.00, RPM 80.00, Press 5600.00, Tq 20000, ROP 470.00
11/11/2020 | 18:10 | 18:14 | 0.07 | 9349 | 9349 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 18:14 | 18:26 | 0.2 | 9349 | 9442 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9349.00 t/9442.00, w/WOB 45.00,Flow 900.00, RPM 80.00, Press 5800, Tq 20000.00, ROP 465.00
11/11/2020 | 18:26 | 18:30 | 0.07 | 9442 | 9442 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 18:30 | 18:45 | 0.25 | 9442 | 9536 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9442.00 t/9536.00, w/WOB 42,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 376.00
11/11/2020 | 18:45 | 18:48 | 0.05 | 9536 | 9536 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 18:48 | 19:02 | 0.23 | 9536 | 9630 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9536.00 t/9630.00, w/WOB 42,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 402.86
11/11/2020 | 19:02 | 19:06 | 0.07 | 9630 | 9630 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 19:06 | 19:21 | 0.25 | 9630 | 9723 | 93 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9630.00 t/9723.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 372.00
11/11/2020 | 19:21 | 19:25 | 0.07 | 9723 | 9723 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 19:25 | 19:45 | 0.33 | 9723 | 9817 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9723.00 t/9817.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 282.00
11/11/2020 | 19:45 | 19:49 | 0.07 | 9817 | 9817 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 19:49 | 20:13 | 0.4 | 9817 | 9911 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9817.00 t/9911.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 235.00
11/11/2020 | 20:13 | 20:17 | 0.07 | 9911 | 9911 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 20:17 | 20:38 | 0.35 | 9911 | 10005 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/9911.00 t/10005.00, w/WOB 42.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 268.57
11/11/2020 | 20:38 | 20:41 | 0.05 | 10005 | 10005 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 20:41 | 21:00 | 0.32 | 10005 | 10099 | 94 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10005.00 t/10099.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 296.84
11/11/2020 | 21:00 | 21:04 | 0.07 | 10099 | 10099 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 21:04 | 21:08 | 0.07 | 10099 | 10118 | 19 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10099.00 t/10118.00, w/WOB 38.00,Flow 900.00, RPM 80.00, Press 5800.00, Tq 20000.00, ROP 285.00
11/11/2020 | 21:08 | 22:10 | 1.03 | 10118 | 10178 | 60 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/10118.00 t/10178.00, TF , w/WOB 25,Flow 900.00, Press 5400, Tq 0, ROP 58.06
11/11/2020 | 22:10 | 22:20 | 0.17 | 10178 | 10193 | 15 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10178.00 t/10193.00, w/WOB 38.00,Flow 900.00, RPM 40, Press 5500, Tq 18000, ROP 90.00
11/11/2020 | 22:20 | 22:24 | 0.07 | 10193 | 10193 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/11/2020 | 22:24 | 22:32 | 0.13 | 10193 | 10215 | 22 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10193.00 t/10215.00, w/WOB 38.00,Flow 900.00, RPM 40, Press 5600, Tq 18000, ROP 165.00
11/11/2020 | 22:32 | 23:24 | 0.87 | 10215 | 10259 | 44 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/10215.00 t/10259.00, TF , w/WOB 28,Flow 900.00, Press 5300, Tq 0, ROP 50.77
11/11/2020 | 23:24 | 23:45 | 0.35 | 10259 | 10259 | 0 | INT | 2: BHA 2 (Intermediate) | 8D | Pump #2 Swab
11/11/2020 | 23:45 | 23:54 | 0.15 | 10259 | 10286 | 27 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10259.00 t/10286.00, w/WOB 32,Flow 660, RPM 40, Press 4000, Tq 19000, ROP 180.00
11/11/2020 | 23:54 | 24:00 | 0.1 | 10286 | 10286 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_12_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 5 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/12/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 35000
|  |  |  | 24hr Summary: |  | Drilling Ahead in Intermediate Section as per plan
|  |  |  | 24hr Lookahead: |  | Finish Intermediate Section; TOH; L/D BHA #2; Standby for Casing and Cement Ops
Drilling Summary |  | 24Hr (BHA 2) |  | Run (BHA 2) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10286 |  | 3170 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10528 |  | 10528 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): |  | 242 |  | 7358 |  | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 42
Slide Drilled (Usft): |  | 99 |  | 505 | [5 empty] | 100: | 11 | Chlorides: | 50000
Rotary Drilled (Usft): |  | 143 |  | 6853 | [5 empty] | 6: | 5 | % Sand/Solids: | 0.25 / 8.30
Drlg/Circ Hrs: |  | 3.00 / 1.82 |  | 25.63 / 2.68 |  | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 1.82 |  | 7.47 |  | SN: |  | 53502 |  | 10s Gel: | 5 | Weight (ppg): | 9.1
Rotary Drilling Hrs: |  | 1.18 |  | 18.17 |  | Bit # |  | 1 |  | PH / Temp(F) | 1.9 / 216.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): |  | 120.85 / 54.50 |  | 377.23 / 67.63 |  | OD (in) / TFA: |  | 9.875 / 1.491
BRT Hrs: |  | 16.67 |  | 49.5 |  | Grade In: |  | New
% Slide: |  | 40.91 |  | 6.86 |  | Grade Out: |  | 0-1-CT-S-X-1/16-TD
% Rotary: |  | 59.09 |  | 93.14 |  | Make / Model: |  | Ulterra / SPL613
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Jeff Wells |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
Bobby Guin |  | Billy McFarland |  | Kyle Novosad
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s - TFA 1.49 |  |  |  | 9.875 | 2.5 |  |  |  |  | 1.3 |  | 1.3
7/8 Lobe 5.9 Stage |  |  |  | 7.875 | [5 empty] | 37.69 |  | 38.99
NM Pony |  |  |  | 7.813 | 3.438 |  |  |  |  | 9.7 |  | 48.69
UBHO/Muleshoe |  |  |  | 7.688 | 2.75 |  |  |  |  | 3.9 |  | 52.59
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.6 |  | 82.19
NMDC |  |  |  | 8 | 3.25 |  |  |  |  | 29.89 |  | 112.08
4 1/2 XH P x 6 5/8 Reg B |  |  |  | 6.438 | 2.75 |  |  |  |  | 2.34 |  | 114.42
2 stands of 6 1/2 in Collars |  |  |  | 6.5 | 2.375 |  |  |  |  | 185.52 |  | 299.94
4 1/2 IF B x 4 1/2 XH P |  |  |  | 6.438 | 2.75 |  |  |  |  | 2.33 |  | 302.27
9 joints of HWDP |  |  |  | 5 | 3 |  |  |  |  | 276.52 |  | 578.79
22 stands of Drill pipe |  |  |  | 6 | 2.75 |  |  |  |  | 2064.94 |  | 2643.73
NOV Agitator and Shock Sub |  |  |  | 6.75 | 2 |  |  |  |  | 30.42 |  | 2674.15
2674.15
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM800038 |  | PDCI |  | 7/8 5.9 |  | 7/8 | 6.02 |  | 2 |  | 0.17 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10308 | 9.2 | 317.5 | 10249.91 | -61.72 | -668.68 | 2.92 |  | 26.92 | 445.9 | 2.69 |  | 8.28 | 93
10402 | 13.3 | 315.1 | 10342.09 | -48.51 | -681.39 | 4.39 |  | -7.69 | 464.21 | 4.36 |  | -2.55 | 94
10457 | 15.8 | 315.3 | 10395.32 | -38.71 | -691.13 | 4.55 |  | 1.25 | 478.01 | 4.55 |  | 0.36 | 55
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 80.67 | 34.63 | 40 | 150 | 660 | 3800 | 3200 | 276 | 310 | 280 | 260 | 19200 | 2000
Run | 287.05 | 36.93 | 75.37 | 219 | 867.44 | 5036.75 | 4370.51 | 276 | 212.91 | 198.39 | 188.03 | 15768.42 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/12/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/12/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/12/2020 | 00:00 | 00:05 | 0.08 | 10286 | 10308 | 22 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10286.00 t/10308.00, w/WOB 32.00,Flow 660.00, RPM 40.00, Press 4000.00, Tq 19000.00, ROP 264.00
11/12/2020 | 00:05 | 00:35 | 0.5 | 10308 | 10336 | 28 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/10308.00 t/10336.00, TF , w/WOB 30,Flow 660.00, Press 3500, Tq 0, ROP 56.00
11/12/2020 | 00:35 | 00:47 | 0.2 | 10336 | 10379 | 43 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10336.00 t/10379.00, w/WOB 32.00,Flow 660.00, RPM 40.00, Press 4000.00, Tq 19000.00, ROP 215.00
11/12/2020 | 00:47 | 00:53 | 0.1 | 10379 | 10379 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/12/2020 | 00:53 | 00:58 | 0.08 | 10379 | 10385 | 6 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10379.00 t/10385.00, w/WOB 32.00,Flow 660.00, RPM 40.00, Press 4000.00, Tq 19000.00, ROP 72.00
11/12/2020 | 00:58 | 01:44 | 0.77 | 10385 | 10440 | 55 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/10385.00 t/10440.00, TF , w/WOB 26,Flow 660.00, Press 3500, Tq 0, ROP 71.74
11/12/2020 | 01:44 | 02:01 | 0.28 | 10440 | 10475 | 35 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10440.00 t/10475.00, w/WOB 32.00,Flow 660.00, RPM 40.00, Press 4000.00, Tq 19000.00, ROP 123.53
11/12/2020 | 02:01 | 02:05 | 0.07 | 10475 | 10475 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey & Connection
11/12/2020 | 02:05 | 02:37 | 0.53 | 10475 | 10512 | 37 | INT | 2: BHA 2 (Intermediate) | 2K | Rotary Drill f/10475.00 t/10512.00, w/WOB 45,Flow 660.00, RPM 40.00, Press 4000.00, Tq 20000, ROP 69.38
11/12/2020 | 02:37 | 03:10 | 0.55 | 10512 | 10528 | 16 | INT | 2: BHA 2 (Intermediate) | 2J | Slide Drill f/10512.00 t/10528.00, TF , w/WOB 48,Flow 660.00, Press 3400, Tq 0, ROP 29.09
11/12/2020 | 03:10 | 03:16 | 0.1 | 10528 | 10528 | 0 | INT | 2: BHA 2 (Intermediate) | 10D | Survey @ 10,457 SD
11/12/2020 | 03:16 | 05:05 | 1.82 | 10528 | 10528 | 0 | INT | 2: BHA 2 (Intermediate) | 5A | Circulating Hole Clean @ Section TD
11/12/2020 | 05:05 | 05:15 | 0.17 | 10528 | 10528 | 0 | INT | 2: BHA 2 (Intermediate) | 6I | Flow Check (No Flow)
11/12/2020 | 05:15 | 15:07 | 9.87 | 10528 | 10528 | 0 | INT | 2: BHA 2 (Intermediate) | 6K | L/D 5 DP
11/12/2020 | 15:07 | 16:40 | 1.55 | 10528 | 10528 | 0 | INT | 2: BHA 2 (Intermediate) | 6P | L/D 8 Directional Tools
11/12/2020 | 16:40 | 24:00 | 7.33 | 10528 | 10528 | 0 | INT |  | 24B | Attended Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_13_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 6 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/13/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 39800
|  |  |  | 24hr Summary: |  | Standby for Casing and Cement Ops
|  |  |  | 24hr Lookahead: |  | Standby for Casing and Cement Ops
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10528 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 33 | PV: | 12
End Depth (Usft): |  | 10528 |  | 10528 |  | OD (in): |  |  |  | 300: | 21 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 16 | Viscosity: | 42
Slide Drilled (Usft): | [9 empty] | 100: | 11 | Chlorides: | 50000
Rotary Drilled (Usft): | [9 empty] | 6: | 5 | % Sand/Solids: | 0.25 / 8.30
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 4 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 5 | Weight (ppg): | 9.1
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 1.9 / 216.00 | Mud Type: | OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Kevin Burt |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
Bobby Guin |  | Billy McFarland
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 34.63 | 40 | 150 | 660 | 3800 | 3200 | 276 | 310 | 280 | 260 | 19200 | 2000
Run | 0 | 36.93 | 75.37 | 219 | 867.44 | 5036.75 | 4370.51 | 276 | 212.91 | 198.39 | 188.03 | 15768.42 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 11/13/2020 |  | 4 |  | 4400 |  | 1 | 4400
Perdiem Per Hand |  |  |  |  | 11/13/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/13/2020 | 00:00 | 24:00 | 24 | 10528 | 10528 | 0 | INT |  | 24B | Attended Standby for Casing and Cement Ops
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_14_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 7 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/14/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 17650 |  |  | Well Cost($): |  | 57450
|  |  |  | 24hr Summary: |  | Standby; P/U BHA #3 (C&L); TIH; S/C Drill Line
|  |  |  | 24hr Lookahead: |  | Finish TIH; Drill and Land Curve; Begin Drilling Ahead in Lateral Section as per plan
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10528 |  | 10528 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 10
End Depth (Usft): |  | 10528 |  | 10528 |  | OD (in): |  |  |  | 300: | 19 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 13 | Viscosity: | 47
Slide Drilled (Usft): | [9 empty] | 100: | 10 | Chlorides: | 44000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 10.20
Drlg/Circ Hrs: |  | 0.00 / 0.17 |  | 0.00 / 0.17 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  | 13509567 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: | [5 empty] | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 216.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 14.17 |  |  |  | Grade In: |  | New
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
James |  | Billy McFarland
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" Halliburton- GTD64M w/ 6 x 18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  |  | 5.5 | 2 |  |  |  |  | 32.96 |  | 33.71
BTI Valve |  |  |  | 5 | 2.375 |  |  |  |  | 2.37 |  | 36.08
Pony Collar |  |  |  | 5.063 | 2.125 |  |  |  |  | 11.8 |  | 47.88
UBHO/ Muleshoe |  |  |  | 5.375 | 2.375 |  |  |  |  | 4.02 |  | 51.9
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.188 |  |  |  |  | 30.64 |  | 82.54
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.25 |  |  |  |  | 30.29 |  | 112.83
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 24.21 |  | 137.04
Crossover (XT39 Pin x DS42 Box) |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.65 |  | 140.69
27 Stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2556.83 |  | 2697.52
NOV Shock Sub/ Agitator/ Safety Joint |  |  |  | 5 | 2 |  |  |  |  | 28.71 |  | 2726.23
2726.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 34.63 | 40 | 489 | 660 | 3800 | 3200 | 276 | 310 | 280 | 260 | 19200 | 2000
Run | 0 | 36.93 | 75.37 | 665 | 867.44 | 5036.75 | 4370.51 | 276 | 212.91 | 198.39 | 188.03 | 15768.42 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/14/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/14/2020 |  | 3 |  | 100 |  | 3 | 300
5 Premium Motor Stator Reline |  |  |  |  | 11/14/2020 |  | 5 |  | 10500 |  | 1 | 10500
Total | [11 empty] | 17650
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/14/2020 | 00:00 | 08:15 | 8.25 | 10528 | 10528 | 0 | CRV |  | 24B | Standby (Testing BOPs)
11/14/2020 | 08:15 | 08:30 | 0.25 | 10528 | 10528 | 0 | CRV |  | 24A | Gather tools on rig floor
11/14/2020 | 08:30 | 09:50 | 1.33 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6O | Pick up BHA #3
11/14/2020 | 09:50 | 10:00 | 0.17 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 5A | Surface test MWD
11/14/2020 | 10:00 | 21:35 | 11.58 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6J | P/U 4 1/2 DP t/ 8,630
11/14/2020 | 21:35 | 23:20 | 1.75 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 9A | S/C Drill Line (10 wraps)
11/14/2020 | 23:20 | 24:00 | 0.67 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 8P | Rig Service
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_15_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 8 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/15/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7150 |  |  | Well Cost($): |  | 64600
|  |  |  | 24hr Summary: |  | Finish TIH; Drill and Land Curve; Begin Drilling Ahead in Lateral Section
|  |  |  | 24hr Lookahead: |  | Drill Lateral Section as per plan
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 10528 |  | 10528 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 10
End Depth (Usft): |  | 12995 |  | 12995 |  | OD (in): |  |  |  | 300: | 19 | YP: | 9
Total Drilled (Usft): |  | 2467 |  | 2467 |  | Weight (ft/lbs): |  |  |  | 200: | 13 | Viscosity: | 47
Slide Drilled (Usft): |  | 652 |  | 652 | [5 empty] | 100: | 10 | Chlorides: | 44000
Rotary Drilled (Usft): |  | 1815 |  | 1815 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 10.20
Drlg/Circ Hrs: |  | 16.52 / 0.33 |  | 16.52 / 0.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 8.75 |  | 8.75 |  | SN: |  | 13509567 |  | 10s Gel: | 5 | Weight (ppg): | 9.6
Rotary Drilling Hrs: |  | 7.77 |  | 7.77 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 216.00 | Fluid Loss / Mud Type: | 7 / OBM
ROP Rot/Slide (Usft/hr): |  | 233.69 / 74.51 |  | 233.69 / 74.51 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 21.83 |  | 21.83 |  | Grade In: |  | New
% Slide: |  | 26.43 |  | 26.43 |  | Grade Out:
% Rotary: |  | 73.57 |  | 73.57 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
James |  | Billy McFarland
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" Halliburton- GTD64M w/ 6 x 18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  |  | 5.5 | 2 |  |  |  |  | 32.96 |  | 33.71
BTI Valve |  |  |  | 5 | 2.375 |  |  |  |  | 2.37 |  | 36.08
Pony Collar |  |  |  | 5.063 | 2.125 |  |  |  |  | 11.8 |  | 47.88
UBHO/ Muleshoe |  |  |  | 5.375 | 2.375 |  |  |  |  | 4.02 |  | 51.9
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.188 |  |  |  |  | 30.64 |  | 82.54
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.25 |  |  |  |  | 30.29 |  | 112.83
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 24.21 |  | 137.04
Crossover (XT39 Pin x DS42 Box) |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.65 |  | 140.69
27 Stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2556.83 |  | 2697.52
NOV Shock Sub/ Agitator/ Safety Joint |  |  |  | 5 | 2 |  |  |  |  | 28.71 |  | 2726.23
2726.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
10548 | 16.8 | 315.4 | 10482.66 | -20.54 | -709.08 | 1.1 |  | 1.66 | 503.53 | 1.1 |  | 0.11 | 91
10643 | 26.2 | 315.5 | 10570.95 | 4.25 | -733.47 | 9.89 |  | 0.27 | 538.28 | 9.89 |  | 0.11 | 95
10738 | 31.2 | 315 | 10654.25 | 36.63 | -765.59 | 5.27 |  | -2.97 | 583.86 | 5.26 |  | -0.53 | 95
10833 | 46.4 | 316.2 | 10728.07 | 79.11 | -807.04 | 16.02 |  | 3.31 | 643.15 | 16 |  | 1.26 | 95
10927 | 56 | 316.1 | 10786.91 | 131.87 | -857.73 | 10.21 |  | -0.5 | 716.22 | 10.21 |  | -0.11 | 94
11022 | 63 | 313.6 | 10835.1 | 189.51 | -915.77 | 7.71 |  | -17.75 | 797.98 | 7.37 |  | -2.63 | 95
11117 | 65.2 | 312 | 10876.59 | 247.56 | -978.47 | 2.77 |  | -33.55 | 883.43 | 2.32 |  | -1.68 | 95
11212 | 67.8 | 312.4 | 10914.47 | 306.08 | -1043 | 2.76 |  | 8.11 | 970.53 | 2.74 |  | 0.42 | 95
11308 | 81.2 | 314.8 | 10940.07 | 369.77 | -1109.79 | 14.16 |  | 10.14 | 1062.81 | 13.96 |  | 2.5 | 96
11403 | 96 | 315.3 | 10942.39 | 436.8 | -1176.7 | 15.59 |  | 1.95 | 1157.47 | 15.58 |  | 0.53 | 95
11498 | 93 | 313.9 | 10934.93 | 503.29 | -1244.13 | 3.48 |  | -154.99 | 1252.13 | -3.16 |  | -1.47 | 95
11592 | 89.8 | 311.6 | 10932.64 | 567.06 | -1313.12 | 4.19 |  | -144.27 | 1346.08 | -3.4 |  | -2.45 | 94
11687 | 90.6 | 311.7 | 10932.3 | 630.19 | -1384.11 | 0.85 |  | 7.12 | 1441.05 | 0.84 |  | 0.11 | 95
11781 | 90.1 | 312.2 | 10931.73 | 693.03 | -1454.02 | 0.75 |  | 135 | 1535.03 | -0.53 |  | 0.53 | 94
11876 | 93 | 313 | 10929.16 | 757.3 | -1523.91 | 3.17 |  | 15.41 | 1629.98 | 3.05 |  | 0.84 | 95
11970 | 92.5 | 314.5 | 10924.65 | 822.23 | -1591.73 | 1.68 |  | 108.42 | 1723.86 | -0.53 |  | 1.6 | 94
12064 | 91.2 | 314 | 10921.62 | 887.78 | -1659.03 | 1.48 |  | -158.96 | 1817.79 | -1.38 |  | -0.53 | 94
12158 | 91.4 | 314.2 | 10919.48 | 953.18 | -1726.52 | 0.3 |  | 44.99 | 1911.75 | 0.21 |  | 0.21 | 94
12253 | 91.7 | 314.3 | 10916.91 | 1019.45 | -1794.54 | 0.33 |  | 18.43 | 2006.7 | 0.32 |  | 0.11 | 95
12347 | 93.1 | 314.8 | 10912.98 | 1085.33 | -1861.47 | 1.58 |  | 19.63 | 2100.58 | 1.49 |  | 0.53 | 94
12441 | 90.4 | 314.1 | 10910.11 | 1151.12 | -1928.53 | 2.97 |  | -165.46 | 2194.51 | -2.87 |  | -0.74 | 94
12536 | 91 | 313.8 | 10908.95 | 1217.05 | -1996.92 | 0.71 |  | -26.56 | 2289.49 | 0.63 |  | -0.32 | 95
12631 | 93.8 | 312.1 | 10904.97 | 1281.71 | -2066.39 | 3.45 |  | -31.21 | 2384.39 | 2.95 |  | -1.79 | 95
12727 | 93.2 | 312.4 | 10899.11 | 1346.14 | -2137.31 | 0.7 |  | 153.47 | 2480.2 | -0.63 |  | 0.31 | 96
12822 | 94 | 312.2 | 10893.14 | 1409.95 | -2207.44 | 0.87 |  | -14 | 2575 | 0.84 |  | -0.21 | 95
12918 | 95 | 312 | 10885.61 | 1474.11 | -2278.45 | 1.06 |  | -11.27 | 2670.69 | 1.04 |  | -0.21 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 146.41 | 34.87 | 63.33 | 328 | 389.78 | 4395.65 | 3592.39 | 276 | 258.35 | 221.41 | 195 | 11466.67 | 2000
Run | 146.41 | 34.87 | 63.33 | 328 | 389.78 | 4395.65 | 3592.39 | 276 | 258.35 | 221.41 | 195 | 11466.67 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/15/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/15/2020 |  | 3 |  | 100 |  | 3 | 300
Total | [11 empty] | 7150
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/15/2020 | 00:00 | 02:10 | 2.17 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 6O | P/U 4 1/2 DP
11/15/2020 | 02:10 | 02:30 | 0.33 | 10528 | 10528 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 5A | Drlg Out Shoe Track
11/15/2020 | 02:30 | 02:35 | 0.08 | 10528 | 10538 | 10 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10528.00 t/10538.00, w/WOB 15.00,Flow 230.00, RPM 40.00, Press 1900.00, Tq 6000.00, ROP 120.00
11/15/2020 | 02:35 | 03:35 | 1 | 10538 | 10538 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 15D | FIT @ 1,902 psi
11/15/2020 | 03:35 | 04:25 | 0.83 | 10538 | 10598 | 60 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10538.00 t/10598.00, TF 0.00, w/WOB 32.00,Flow 350.00, Press 3800.00, Tq 0.00, ROP 72.00
11/15/2020 | 04:25 | 04:30 | 0.08 | 10598 | 10617 | 19 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10598.00 t/10617.00, w/WOB 28.00,Flow 350.00, RPM 40.00, Press 4000.00, Tq 8000.00, ROP 228.00
11/15/2020 | 04:30 | 04:40 | 0.17 | 10617 | 10617 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 04:40 | 04:45 | 0.08 | 10617 | 10620 | 3 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10617.00 t/10620.00, w/WOB 28.00,Flow 350.00, RPM 40.00, Press 4000.00, Tq 8000.00, ROP 36.00
11/15/2020 | 04:45 | 05:45 | 1 | 10620 | 10685 | 65 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10620.00 t/10685.00, TF , w/WOB 28.00,Flow 350.00, Press 3800, Tq 0, ROP 65.00
11/15/2020 | 05:45 | 06:00 | 0.25 | 10685 | 10712 | 27 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10685.00 t/10712.00, w/WOB 28.00,Flow 350.00, RPM 40.00, Press 4000.00, Tq 8000.00, ROP 108.00
11/15/2020 | 06:00 | 06:10 | 0.17 | 10712 | 10712 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 06:10 | 06:18 | 0.13 | 10712 | 10732 | 20 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10712.00 t/10732.00, w/WOB 28.00,Flow 350.00, RPM 40.00, Press 4000.00, Tq 8000.00, ROP 150.00
11/15/2020 | 06:18 | 07:11 | 0.88 | 10732 | 10807 | 75 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10732.00 t/10807.00, TF , w/WOB 28.00,Flow 400, Press 4100, Tq 0, ROP 84.91
11/15/2020 | 07:11 | 07:20 | 0.15 | 10807 | 10807 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 07:20 | 08:17 | 0.95 | 10807 | 10890 | 83 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10807.00 t/10890.00, TF , w/WOB 28.00,Flow 400, Press 4100, Tq 0, ROP 87.37
11/15/2020 | 08:17 | 08:24 | 0.12 | 10890 | 10902 | 12 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10890.00 t/10902.00, w/WOB 28.00,Flow 400.00, RPM 40, Press 4600, Tq 12000, ROP 102.86
11/15/2020 | 08:24 | 08:34 | 0.17 | 10902 | 10902 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 08:34 | 08:45 | 0.18 | 10902 | 10957 | 55 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10902.00 t/10957.00, w/WOB 28.00,Flow 400.00, RPM 40, Press 4600, Tq 12000, ROP 300.00
11/15/2020 | 08:45 | 09:26 | 0.68 | 10957 | 10996 | 39 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/10957.00 t/10996.00, TF , w/WOB 32,Flow 400.00, Press 4100.00, Tq 0.00, ROP 57.07
11/15/2020 | 09:26 | 09:36 | 0.17 | 10996 | 10996 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 09:36 | 09:58 | 0.37 | 10996 | 11056 | 60 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/10996.00 t/11056.00, w/WOB 28.00,Flow 400.00, RPM 40, Press 4600, Tq 12000, ROP 163.64
11/15/2020 | 09:58 | 10:20 | 0.37 | 11056 | 11091 | 35 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11056.00 t/11091.00, TF , w/WOB 32,Flow 400.00, Press 4100.00, Tq 0.00, ROP 95.45
11/15/2020 | 10:20 | 10:25 | 0.08 | 11091 | 11091 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 24A | Recalibrate Blocks
11/15/2020 | 10:25 | 10:35 | 0.17 | 11091 | 11091 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 10:35 | 10:57 | 0.37 | 11091 | 11158 | 67 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11091.00 t/11158.00, w/WOB 30.00,Flow 400.00, RPM 40.00, Press 4100.00, Tq 12000.00, ROP 182.73
11/15/2020 | 10:57 | 11:24 | 0.45 | 11158 | 11186 | 28 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11158.00 t/11186.00, TF 0.00, w/WOB 32.00,Flow 400.00, Press 4100.00, Tq 0.00, ROP 62.22
11/15/2020 | 11:24 | 11:34 | 0.17 | 11186 | 11186 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 11:34 | 11:48 | 0.23 | 11186 | 11233 | 47 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11186.00 t/11233.00, w/WOB 30.00,Flow 400.00, RPM 40.00, Press 4100.00, Tq 12000.00, ROP 201.43
11/15/2020 | 11:48 | 12:20 | 0.53 | 11233 | 11281 | 48 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11233.00 t/11281.00, TF , w/WOB 32.00,Flow 400.00, Press 4100.00, Tq 0.00, ROP 90.00
11/15/2020 | 12:20 | 12:30 | 0.17 | 11281 | 11281 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 12:30 | 13:32 | 1.03 | 11281 | 11377 | 96 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11281.00 t/11377.00, TF , w/WOB 32.00,Flow 400.00, Press 4100.00, Tq 0.00, ROP 92.90
11/15/2020 | 13:32 | 13:42 | 0.17 | 11377 | 11377 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 13:42 | 14:10 | 0.47 | 11377 | 11472 | 95 | CRV | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11377.00 t/11472.00, w/WOB 30.00,Flow 400.00, RPM 40.00, Press 4650, Tq 12000.00, ROP 203.57
11/15/2020 | 14:10 | 14:20 | 0.17 | 11472 | 11472 | 0 | CRV | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 14:20 | 14:53 | 0.55 | 11472 | 11517 | 45 | CRV | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11472.00 t/11517.00, TF , w/WOB 32.00,Flow 400.00, Press 4100.00, Tq 0.00, ROP 81.82
11/15/2020 | 14:53 | 15:08 | 0.25 | 11517 | 11567 | 50 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11517.00 t/11567.00, w/WOB 30.00,Flow 400.00, RPM 40.00, Press 4650, Tq 12000.00, ROP 200.00
11/15/2020 | 15:08 | 15:18 | 0.17 | 11567 | 11567 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 15:18 | 15:39 | 0.35 | 11567 | 11661 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11567.00 t/11661.00, w/WOB 35,Flow 400.00, RPM 70, Press 4650, Tq 12000.00, ROP 268.57
11/15/2020 | 15:39 | 15:50 | 0.18 | 11661 | 11661 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 15:50 | 16:04 | 0.23 | 11661 | 11756 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11661.00 t/11756.00, w/WOB 35.00,Flow 400.00, RPM 70.00, Press 4650.00, Tq 12000.00, ROP 407.14
11/15/2020 | 16:04 | 16:14 | 0.17 | 11756 | 11756 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 16:14 | 16:31 | 0.28 | 11756 | 11850 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11756.00 t/11850.00, w/WOB 35.00,Flow 400.00, RPM 70.00, Press 4650.00, Tq 12000.00, ROP 331.76
11/15/2020 | 16:31 | 16:40 | 0.15 | 11850 | 11850 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 16:40 | 16:43 | 0.05 | 11850 | 11860 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11850.00 t/11860.00, w/WOB 35.00,Flow 400.00, RPM 80, Press 4650.00, Tq 12000.00, ROP 200.00
11/15/2020 | 16:43 | 16:54 | 0.18 | 11860 | 11870 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11860.00 t/11870.00, TF , w/WOB 40,Flow 400.00, Press 4000, Tq 0, ROP 54.55
11/15/2020 | 16:54 | 17:10 | 0.27 | 11870 | 11945 | 75 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11870.00 t/11945.00, w/WOB 40.00,Flow 400.00, RPM 80, Press 4000.00, Tq 12000, ROP 281.25
11/15/2020 | 17:10 | 17:40 | 0.5 | 11945 | 11945 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 8P | Rig Service
11/15/2020 | 17:40 | 17:45 | 0.08 | 11945 | 11945 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 17:45 | 17:50 | 0.08 | 11945 | 11952 | 7 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11945.00 t/11952.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 4000.00, Tq 12000.00, ROP 84.00
11/15/2020 | 17:50 | 18:10 | 0.33 | 11952 | 11967 | 15 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/11952.00 t/11967.00, TF 180.00, w/WOB 48.00,Flow 400.00, Press 4800.00, Tq 0.00, ROP 45.00
11/15/2020 | 18:10 | 18:25 | 0.25 | 11967 | 12039 | 72 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/11967.00 t/12039.00, w/WOB 48.00,Flow 400.00, RPM 80, Press 4800.00, Tq 12000, ROP 288.00
11/15/2020 | 18:25 | 18:30 | 0.08 | 12039 | 12039 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 18:30 | 18:45 | 0.25 | 12039 | 12054 | 15 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12039.00 t/12054.00, TF , w/WOB 48.00,Flow 400.00, Press 4800.00, Tq 0.00, ROP 60.00
11/15/2020 | 18:45 | 19:10 | 0.42 | 12054 | 12133 | 79 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12054.00 t/12133.00, w/WOB 38,Flow 400.00, RPM 80, Press 4800.00, Tq 12000, ROP 189.60
11/15/2020 | 19:10 | 19:15 | 0.08 | 12133 | 12133 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 19:15 | 19:45 | 0.5 | 12133 | 12227 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12133.00 t/12227.00, w/WOB 38.00,Flow 400.00, RPM 80.00, Press 4800.00, Tq 12000.00, ROP 188.00
11/15/2020 | 19:45 | 20:05 | 0.33 | 12227 | 12322 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12227.00 t/12322.00, w/WOB 38.00,Flow 400.00, RPM 80.00, Press 4900, Tq 12000.00, ROP 285.00
11/15/2020 | 20:05 | 20:20 | 0.25 | 12322 | 12322 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 20:20 | 20:40 | 0.33 | 12322 | 12416 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12322.00 t/12416.00, w/WOB 38.00,Flow 400.00, RPM 80.00, Press 4900, Tq 12000.00, ROP 282.00
11/15/2020 | 20:40 | 20:45 | 0.08 | 12416 | 12416 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 20:45 | 20:48 | 0.05 | 12416 | 12420 | 4 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12416.00 t/12420.00, w/WOB 38.00,Flow 400.00, RPM 80.00, Press 4900, Tq 12000.00, ROP 80.00
11/15/2020 | 20:48 | 21:05 | 0.28 | 12420 | 12438 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12420.00 t/12438.00, TF , w/WOB 50,Flow 400.00, Press 4200, Tq 0, ROP 63.53
11/15/2020 | 21:05 | 21:25 | 0.33 | 12438 | 12510 | 72 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12438.00 t/12510.00, w/WOB 38.00,Flow 400.00, RPM 80.00, Press 4900, Tq 12000.00, ROP 216.00
11/15/2020 | 21:25 | 21:30 | 0.08 | 12510 | 12510 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 21:30 | 21:50 | 0.33 | 12510 | 12605 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12510.00 t/12605.00, w/WOB 38.00,Flow 400.00, RPM 80.00, Press 4900, Tq 12000.00, ROP 285.00
11/15/2020 | 21:50 | 21:55 | 0.08 | 12605 | 12605 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 21:55 | 22:10 | 0.25 | 12605 | 12617 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12605.00 t/12617.00, TF , w/WOB 50,Flow 400.00, Press 4200, Tq 0, ROP 48.00
11/15/2020 | 22:10 | 22:30 | 0.33 | 12617 | 12700 | 83 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12617.00 t/12700.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4900.00, Tq 13500.00, ROP 249.00
11/15/2020 | 22:30 | 22:35 | 0.08 | 12700 | 12700 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 22:35 | 22:55 | 0.33 | 12700 | 12796 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12700.00 t/12796.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4900.00, Tq 13500.00, ROP 288.00
11/15/2020 | 22:55 | 23:00 | 0.08 | 12796 | 12796 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 23:00 | 23:20 | 0.33 | 12796 | 12891 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12796.00 t/12891.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4900.00, Tq 13500.00, ROP 285.00
11/15/2020 | 23:20 | 23:25 | 0.08 | 12891 | 12891 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 23:25 | 23:45 | 0.33 | 12891 | 12987 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/12891.00 t/12987.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4900.00, Tq 13500.00, ROP 288.00
11/15/2020 | 23:45 | 23:50 | 0.08 | 12987 | 12987 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/15/2020 | 23:50 | 24:00 | 0.17 | 12987 | 12995 | 8 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12987.00 t/12995.00, TF , w/WOB 55,Flow 400.00, Press 4400, Tq 0, ROP 48.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_16_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 9 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/16/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9000 |  |  | Well Cost($): |  | 73600
|  |  |  | 24hr Summary: |  | Drilling Ahead in Lateral
|  |  |  | 24hr Lookahead: |  | Drill Lateral Section as per plan
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 12995 |  | 10528 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 28 | PV: | 10
End Depth (Usft): |  | 15541 |  | 15541 |  | OD (in): |  |  |  | 300: | 18 | YP: | 8
Total Drilled (Usft): |  | 2546 |  | 5013 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 43
Slide Drilled (Usft): |  | 173 |  | 825 | [5 empty] | 100: | 11 | Chlorides: | 48000
Rotary Drilled (Usft): |  | 2373 |  | 4188 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.10
Drlg/Circ Hrs: |  | 16.83 / 0.00 |  | 33.35 / 0.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 7.28 |  | 16.03 |  | SN: |  | 13509567 |  | 10s Gel: | 6 | Weight (ppg): | 9.4
Rotary Drilling Hrs: |  | 9.55 |  | 17.32 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 248.48 / 23.75 |  | 241.85 / 51.46 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 45.83 |  | Grade In: |  | New
% Slide: |  | 6.79 |  | 16.46 |  | Grade Out:
% Rotary: |  | 93.21 |  | 83.54 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
James |  | Billy McFarland
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" Halliburton- GTD64M w/ 6 x 18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  |  | 5.5 | 2 |  |  |  |  | 32.96 |  | 33.71
BTI Valve |  |  |  | 5 | 2.375 |  |  |  |  | 2.37 |  | 36.08
Pony Collar |  |  |  | 5.063 | 2.125 |  |  |  |  | 11.8 |  | 47.88
UBHO/ Muleshoe |  |  |  | 5.375 | 2.375 |  |  |  |  | 4.02 |  | 51.9
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.188 |  |  |  |  | 30.64 |  | 82.54
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.25 |  |  |  |  | 30.29 |  | 112.83
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 24.21 |  | 137.04
Crossover (XT39 Pin x DS42 Box) |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.65 |  | 140.69
27 Stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2556.83 |  | 2697.52
NOV Shock Sub/ Agitator/ Safety Joint |  |  |  | 5 | 2 |  |  |  |  | 28.71 |  | 2726.23
2726.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
13014 | 94.1 | 310.4 | 10877.99 | 1537.14 | -2350.45 | 1.91 |  | -119.37 | 2766.33 | -0.94 |  | -1.67 | 96
13109 | 92.3 | 312.7 | 10872.69 | 1600.05 | -2421.43 | 3.07 |  | 128.02 | 2861.14 | -1.89 |  | 2.42 | 95
13203 | 93 | 313.2 | 10868.35 | 1664.03 | -2490.15 | 0.91 |  | 35.5 | 2955.03 | 0.74 |  | 0.53 | 94
13299 | 93.7 | 313.5 | 10862.74 | 1729.82 | -2559.84 | 0.79 |  | 23.15 | 3050.87 | 0.73 |  | 0.31 | 96
13395 | 91.9 | 312.8 | 10858.05 | 1795.39 | -2629.8 | 2.01 |  | -158.75 | 3146.75 | -1.88 |  | -0.73 | 96
13489 | 92.5 | 312.7 | 10854.44 | 1859.15 | -2698.77 | 0.65 |  | -9.45 | 3240.68 | 0.64 |  | -0.11 | 94
13583 | 92.3 | 311.9 | 10850.5 | 1922.36 | -2768.23 | 0.88 |  | -104.03 | 3334.59 | -0.21 |  | -0.85 | 94
13679 | 93.2 | 311.8 | 10845.9 | 1986.33 | -2839.66 | 0.94 |  | -6.33 | 3430.45 | 0.94 |  | -0.1 | 96
13774 | 92.5 | 312.6 | 10841.17 | 2050.07 | -2909.95 | 1.12 |  | 131.2 | 3525.32 | -0.74 |  | 0.84 | 95
13868 | 93 | 312.9 | 10836.66 | 2113.8 | -2978.9 | 0.62 |  | 30.93 | 3619.21 | 0.53 |  | 0.32 | 94
13963 | 91.7 | 311.5 | 10832.77 | 2177.56 | -3049.21 | 2.01 |  | -132.87 | 3714.11 | -1.37 |  | -1.47 | 95
14058 | 91.7 | 311.1 | 10829.95 | 2240.23 | -3120.55 | 0.42 |  | -89.99 | 3809.02 | 0 |  | -0.42 | 95
14154 | 92.3 | 311.6 | 10826.6 | 2303.61 | -3192.57 | 0.81 |  | 39.78 | 3904.92 | 0.63 |  | 0.52 | 96
14248 | 93.8 | 311.7 | 10821.6 | 2365.99 | -3262.71 | 1.6 |  | 3.81 | 3998.75 | 1.6 |  | 0.11 | 94
14342 | 91.8 | 313.4 | 10817 | 2429.48 | -3331.87 | 2.79 |  | 139.62 | 4092.63 | -2.13 |  | 1.81 | 94
14437 | 90.8 | 313.8 | 10814.85 | 2494.97 | -3400.64 | 1.13 |  | 158.2 | 4187.6 | -1.05 |  | 0.42 | 95
14531 | 91.5 | 314.1 | 10812.96 | 2560.2 | -3468.3 | 0.81 |  | 23.19 | 4281.57 | 0.74 |  | 0.32 | 94
14626 | 92.7 | 314.4 | 10809.48 | 2626.44 | -3536.31 | 1.3 |  | 14.02 | 4376.48 | 1.26 |  | 0.32 | 95
14721 | 94.4 | 314.6 | 10803.6 | 2692.9 | -3603.93 | 1.8 |  | 6.69 | 4471.27 | 1.79 |  | 0.21 | 95
14816 | 93.6 | 313.4 | 10796.97 | 2758.73 | -3672.1 | 1.52 |  | -123.71 | 4566.02 | -0.84 |  | -1.26 | 95
14912 | 94.4 | 313.2 | 10790.28 | 2824.41 | -3741.8 | 0.86 |  | -14 | 4661.79 | 0.83 |  | -0.21 | 96
15008 | 95.5 | 313.2 | 10781.99 | 2889.88 | -3811.52 | 1.15 |  | 0 | 4757.43 | 1.15 |  | 0 | 96
15104 | 92.9 | 313.2 | 10774.96 | 2955.41 | -3881.3 | 2.71 |  | 180 | 4853.16 | -2.71 |  | 0 | 96
15200 | 90.5 | 313.5 | 10772.11 | 3021.28 | -3951.08 | 2.52 |  | 172.87 | 4949.11 | -2.5 |  | 0.31 | 96
15295 | 90.6 | 313.8 | 10771.2 | 3086.85 | -4019.81 | 0.33 |  | 71.56 | 5044.1 | 0.11 |  | 0.32 | 95
15391 | 91.7 | 313.9 | 10769.28 | 3153.34 | -4089.03 | 1.15 |  | 5.19 | 5140.08 | 1.15 |  | 0.1 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 151.25 | 44.5 | 80 | 352 | 400 | 4750 | 3800 | 276 | 300 | 225 | 176.5 | 15950 | 2000
Run | 150.31 | 39.35 | 71.67 | 340 | 394.53 | 4560.47 | 3688.95 | 276 | 277.72 | 223.08 | 186.4 | 13708.33 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/16/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/16/2020 |  | 3 |  | 100 |  | 4 | 400
Hot Hole/ 300-347?F |  |  |  |  | 11/16/2020 |  | 6 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 9000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/16/2020 | 00:00 | 00:20 | 0.33 | 12995 | 13005 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/12995.00 t/13005.00, TF , w/WOB 55,Flow 400.00, Press 4400, Tq 0, ROP 30.00
11/16/2020 | 00:20 | 00:40 | 0.33 | 13005 | 13083 | 78 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13005.00 t/13083.00, w/WOB 35.00,Flow 400.00, RPM 80.00, Press 4900.00, Tq 13500.00, ROP 234.00
11/16/2020 | 00:40 | 00:45 | 0.08 | 13083 | 13083 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 00:45 | 01:30 | 0.75 | 13083 | 13099 | 16 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13083.00 t/13099.00, TF , w/WOB 58,Flow 400.00, Press 4400, Tq 0, ROP 21.33
11/16/2020 | 01:30 | 01:45 | 0.25 | 13099 | 13178 | 79 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13099.00 t/13178.00, w/WOB 40,Flow 400.00, RPM 80.00, Press 4900.00, Tq 14000, ROP 316.00
11/16/2020 | 01:45 | 01:50 | 0.08 | 13178 | 13178 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 01:50 | 02:15 | 0.42 | 13178 | 13272 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13178.00 t/13272.00, w/WOB 40,Flow 400.00, RPM 80.00, Press 4900.00, Tq 14000, ROP 225.60
11/16/2020 | 02:15 | 02:20 | 0.08 | 13272 | 13272 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 02:20 | 02:45 | 0.42 | 13272 | 13368 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13272.00 t/13368.00, w/WOB 40,Flow 400.00, RPM 80.00, Press 4900.00, Tq 14000, ROP 230.40
11/16/2020 | 02:45 | 02:50 | 0.08 | 13368 | 13368 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 02:50 | 03:25 | 0.58 | 13368 | 13386 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13368.00 t/13386.00, TF , w/WOB 58,Flow 400.00, Press 4000, Tq 0, ROP 30.86
11/16/2020 | 03:25 | 03:45 | 0.33 | 13386 | 13464 | 78 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13386.00 t/13464.00, w/WOB 40,Flow 400.00, RPM 80.00, Press 4900.00, Tq 14000, ROP 234.00
11/16/2020 | 03:45 | 03:50 | 0.08 | 13464 | 13464 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 03:50 | 04:05 | 0.25 | 13464 | 13558 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13464.00 t/13558.00, w/WOB 40,Flow 400.00, RPM 80.00, Press 4900.00, Tq 14000, ROP 376.00
11/16/2020 | 04:05 | 04:10 | 0.08 | 13558 | 13558 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 04:10 | 04:45 | 0.58 | 13558 | 13573 | 15 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13558.00 t/13573.00, TF , w/WOB 60,Flow 400.00, Press 4000, Tq 0, ROP 25.71
11/16/2020 | 04:45 | 05:05 | 0.33 | 13573 | 13652 | 79 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13573.00 t/13652.00, w/WOB 40,Flow 400.00, RPM 80, Press 4900, Tq 14000, ROP 237.00
11/16/2020 | 05:05 | 05:10 | 0.08 | 13652 | 13652 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 05:10 | 05:30 | 0.33 | 13652 | 13748 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13652.00 t/13748.00, w/WOB 42,Flow 400.00, RPM 80.00, Press 4900.00, Tq 14000.00, ROP 288.00
11/16/2020 | 05:30 | 06:00 | 0.5 | 13748 | 13760 | 12 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13748.00 t/13760.00, TF , w/WOB 58,Flow 400.00, Press 4000, Tq 0, ROP 24.00
11/16/2020 | 06:00 | 06:18 | 0.3 | 13760 | 13843 | 83 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13760.00 t/13843.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 16000, ROP 276.67
11/16/2020 | 06:18 | 06:28 | 0.17 | 13843 | 13843 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 06:28 | 06:44 | 0.27 | 13843 | 13937 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13843.00 t/13937.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 16000, ROP 352.50
11/16/2020 | 06:44 | 06:54 | 0.17 | 13937 | 13937 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 06:54 | 07:00 | 0.1 | 13937 | 13947 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13937.00 t/13947.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 16000, ROP 100.00
11/16/2020 | 07:00 | 08:00 | 1 | 13947 | 13965 | 18 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/13947.00 t/13965.00, TF , w/WOB 58.00,Flow 400.00, Press 4000.00, Tq 0.00, ROP 18.00
11/16/2020 | 08:00 | 08:25 | 0.42 | 13965 | 14032 | 67 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/13965.00 t/14032.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 16000, ROP 160.80
11/16/2020 | 08:25 | 08:35 | 0.17 | 14032 | 14032 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 08:35 | 08:56 | 0.35 | 14032 | 14127 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14032.00 t/14127.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 271.43
11/16/2020 | 08:56 | 09:06 | 0.17 | 14127 | 14127 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 09:06 | 09:30 | 0.4 | 14127 | 14223 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14127.00 t/14223.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 240.00
11/16/2020 | 09:30 | 09:40 | 0.17 | 14223 | 14223 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 09:40 | 09:55 | 0.25 | 14223 | 14317 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14223.00 t/14317.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 376.00
11/16/2020 | 09:55 | 10:05 | 0.17 | 14317 | 14317 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 10:05 | 10:10 | 0.08 | 14317 | 14327 | 10 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14317.00 t/14327.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 120.00
11/16/2020 | 10:10 | 11:19 | 1.15 | 14327 | 14352 | 25 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14327.00 t/14352.00, TF 150.00, w/WOB 58.00,Flow 400.00, Press 4000.00, Tq 0.00, ROP 21.74
11/16/2020 | 11:19 | 11:35 | 0.27 | 14352 | 14411 | 59 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14352.00 t/14411.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 221.25
11/16/2020 | 11:35 | 11:45 | 0.17 | 14411 | 14411 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 11:45 | 12:02 | 0.28 | 14411 | 14506 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14411.00 t/14506.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 335.29
11/16/2020 | 12:02 | 12:12 | 0.17 | 14506 | 14506 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 12:12 | 12:30 | 0.3 | 14506 | 14600 | 94 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14506.00 t/14600.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 313.33
11/16/2020 | 12:30 | 12:40 | 0.17 | 14600 | 14600 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 12:40 | 12:56 | 0.27 | 14600 | 14695 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14600.00 t/14695.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 356.25
11/16/2020 | 12:56 | 13:25 | 0.48 | 14695 | 14695 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 24A | Repair flare stack ignitor
11/16/2020 | 13:25 | 13:30 | 0.08 | 14695 | 14695 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 13:30 | 13:52 | 0.37 | 14695 | 14790 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14695.00 t/14790.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 259.09
11/16/2020 | 13:52 | 14:07 | 0.25 | 14790 | 14790 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 24A | Repair flare stack ignitor
11/16/2020 | 14:07 | 14:52 | 0.75 | 14790 | 14790 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 14:52 | 15:30 | 0.63 | 14790 | 14810 | 20 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/14800.00 t/14810.00, TF , w/WOB 58.00,Flow 400.00, Press 4000.00, Tq 0.00, ROP 15.79
11/16/2020 | 15:30 | 15:53 | 0.38 | 14810 | 14885 | 75 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14810.00 t/14885.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 19000, ROP 195.65
11/16/2020 | 15:53 | 16:03 | 0.17 | 14885 | 14885 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 16:03 | 16:25 | 0.37 | 14885 | 14981 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14885.00 t/14981.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 261.82
11/16/2020 | 16:25 | 16:35 | 0.17 | 14981 | 14981 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 16:35 | 16:54 | 0.32 | 14981 | 15077 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/14981.00 t/15077.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 16000.00, ROP 303.16
11/16/2020 | 16:54 | 17:00 | 0.1 | 15077 | 15077 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | MWD Survey @ 15,008
11/16/2020 | 17:00 | 19:40 | 2.67 | 15077 | 15077 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6F | Wiper Trip (10 Stands)
11/16/2020 | 19:40 | 20:45 | 1.08 | 15077 | 15102 | 25 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15077.00 t/15102.00, TF , w/WOB 60,Flow 400.00, Press 4000, Tq 0, ROP 23.08
11/16/2020 | 20:45 | 21:10 | 0.42 | 15102 | 15173 | 71 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15102.00 t/15173.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 17000, ROP 170.40
11/16/2020 | 21:10 | 21:20 | 0.17 | 15173 | 15173 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 21:20 | 22:00 | 0.67 | 15173 | 15187 | 14 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15173.00 t/15187.00, TF , w/WOB 60,Flow 400.00, Press 4000, Tq 0, ROP 21.00
11/16/2020 | 22:00 | 22:30 | 0.5 | 15187 | 15269 | 82 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15187.00 t/15269.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 17000, ROP 164.00
11/16/2020 | 22:30 | 22:35 | 0.08 | 15269 | 15269 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 22:35 | 23:00 | 0.42 | 15269 | 15364 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15269.00 t/15364.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 17000, ROP 228.00
11/16/2020 | 23:00 | 23:05 | 0.08 | 15364 | 15364 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 23:05 | 23:35 | 0.5 | 15364 | 15460 | 96 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15364.00 t/15460.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 17000, ROP 192.00
11/16/2020 | 23:35 | 23:40 | 0.08 | 15460 | 15460 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/16/2020 | 23:40 | 24:00 | 0.33 | 15460 | 15541 | 81 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15460.00 t/15541.00, w/WOB 40,Flow 400.00, RPM 80, Press 5000, Tq 17000, ROP 243.00
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_17_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 10 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/17/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 9000 |  |  | Well Cost($): |  | 82600
|  |  |  | 24hr Summary: |  | Drilling Lateral Section as per plan t/ TD
|  |  |  | 24hr Lookahead: |  | Circulate Hole Clean @ TD; TOH
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 15541 |  | 10528 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 10
End Depth (Usft): |  | 16041 |  | 16041 |  | OD (in): |  |  |  | 300: | 19 | YP: | 9
Total Drilled (Usft): |  | 500 |  | 5513 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 44
Slide Drilled (Usft): |  | 40 |  | 865 | [5 empty] | 100: | 12 | Chlorides: | 49000
Rotary Drilled (Usft): |  | 460 |  | 4648 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.10
Drlg/Circ Hrs: |  | 9.08 / 11.32 |  | 42.43 / 11.82 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: |  | 6.52 |  | 22.55 |  | SN: |  | 13509567 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  | 2.57 |  | 19.88 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  | 179.22 / 6.14 |  | 233.76 / 38.36 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 24 |  | 69.83 |  | Grade In: |  | New
% Slide: |  | 8 |  | 15.69 |  | Grade Out:
% Rotary: |  | 92 |  | 84.31 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
James |  | Billy McFarland |  | Chris Hendrix
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" Halliburton- GTD64M w/ 6 x 18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  |  | 5.5 | 2 |  |  |  |  | 32.96 |  | 33.71
BTI Valve |  |  |  | 5 | 2.375 |  |  |  |  | 2.37 |  | 36.08
Pony Collar |  |  |  | 5.063 | 2.125 |  |  |  |  | 11.8 |  | 47.88
UBHO/ Muleshoe |  |  |  | 5.375 | 2.375 |  |  |  |  | 4.02 |  | 51.9
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.188 |  |  |  |  | 30.64 |  | 82.54
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.25 |  |  |  |  | 30.29 |  | 112.83
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 24.21 |  | 137.04
Crossover (XT39 Pin x DS42 Box) |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.65 |  | 140.69
27 Stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2556.83 |  | 2697.52
NOV Shock Sub/ Agitator/ Safety Joint |  |  |  | 5 | 2 |  |  |  |  | 28.71 |  | 2726.23
2726.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Survey Data
MD (Usft) | INC | AZI | TVD (Usft) | NS (Usft) | EW (Usft) | DLS (°/100ft) |  | TFO | VS (Usft) | BR (°/100ft) |  | TR (°/100ft) | CL (Usft)
15487 | 93 | 314.1 | 10765.34 | 3219.97 | -4158.02 | 1.37 |  | 8.74 | 5235.98 | 1.35 |  | 0.21 | 96
15584 | 91.5 | 312.7 | 10761.53 | 3286.56 | -4228.45 | 2.11 |  | -136.97 | 5332.9 | -1.55 |  | -1.44 | 97
15678 | 93.5 | 313.5 | 10757.43 | 3350.72 | -4297.01 | 2.29 |  | 21.77 | 5426.81 | 2.13 |  | 0.85 | 94
15773 | 94.5 | 313.7 | 10750.8 | 3416.08 | -4365.64 | 1.07 |  | 11.28 | 5521.57 | 1.05 |  | 0.21 | 95
15870 | 95.6 | 313.7 | 10742.27 | 3482.83 | -4435.49 | 1.13 |  | 0 | 5618.19 | 1.13 |  | 0 | 97
15966 | 94.7 | 314.3 | 10733.65 | 3549.25 | -4504.27 | 1.13 |  | 146.39 | 5713.79 | -0.94 |  | 0.63 | 96
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 55.05 | 48.93 | 80 | 352 | 400 | 4607.14 | 3800 | 276 | 320 | 225 | 160 | 18000 | 2000
Run | 129.92 | 40.69 | 72.75 | 342 | 395.3 | 4567 | 3704.5 | 276 | 283.64 | 223.35 | 182.7 | 14268.12 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/17/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/17/2020 |  | 3 |  | 100 |  | 4 | 400
Hot Hole/ 300-347?F |  |  |  |  | 11/17/2020 |  | 6 |  | 1750 |  | 1 | 1750
Total | [11 empty] | 9000
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/17/2020 | 00:00 | 00:05 | 0.08 | 15541 | 15556 | 15 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15541.00 t/15556.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 180.00
11/17/2020 | 00:05 | 00:10 | 0.08 | 15556 | 15556 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/17/2020 | 00:10 | 00:35 | 0.42 | 15556 | 15653 | 97 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15556.00 t/15653.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 232.80
11/17/2020 | 00:35 | 00:40 | 0.08 | 15653 | 15653 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/17/2020 | 00:40 | 00:45 | 0.08 | 15653 | 15658 | 5 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15653.00 t/15658.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 60.00
11/17/2020 | 00:45 | 01:50 | 1.08 | 15658 | 15664 | 6 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15658.00 t/15664.00, TF , w/WOB 65,Flow 400.00, Press 3900, Tq 0, ROP 5.54
11/17/2020 | 01:50 | 01:55 | 0.08 | 15664 | 15668 | 4 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15664.00 t/15668.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 48.00
11/17/2020 | 01:55 | 03:25 | 1.5 | 15668 | 15676 | 8 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15668.00 t/15676.00, TF , w/WOB 65,Flow 400.00, Press 3900, Tq 0, ROP 5.33
11/17/2020 | 03:25 | 03:50 | 0.42 | 15676 | 15747 | 71 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15676.00 t/15747.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 170.40
11/17/2020 | 03:50 | 03:55 | 0.08 | 15747 | 15747 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/17/2020 | 03:55 | 04:25 | 0.5 | 15747 | 15842 | 95 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15747.00 t/15842.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 190.00
11/17/2020 | 04:25 | 04:30 | 0.08 | 15842 | 15842 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/17/2020 | 04:30 | 05:00 | 0.5 | 15842 | 15939 | 97 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15842.00 t/15939.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 194.00
11/17/2020 | 05:00 | 05:35 | 0.58 | 15939 | 15939 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 8P | Rig Service
11/17/2020 | 05:35 | 06:24 | 0.82 | 15939 | 15939 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Clean up cycle
11/17/2020 | 06:24 | 08:00 | 1.6 | 15939 | 15948 | 9 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15939.00 t/15948.00, TF , w/WOB 65.00,Flow 400.00, Press 3900.00, Tq 0.00, ROP 5.63
11/17/2020 | 08:00 | 08:30 | 0.5 | 15948 | 15948 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Circulate
11/17/2020 | 08:30 | 11:02 | 2.53 | 15948 | 15948 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6F | Wiper Trip (10Stands)
11/17/2020 | 11:02 | 12:32 | 1.5 | 15948 | 15959 | 11 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/15948.00 t/15959.00, TF 180.00, w/WOB 65.00,Flow 400.00, Press 3900.00, Tq 0.00, ROP 7.33
11/17/2020 | 12:32 | 13:01 | 0.48 | 15959 | 16035 | 76 | LAT | 3: BHA #3 (Curve and Lateral) | 2K | Rotary Drill f/15959.00 t/16035.00, w/WOB 40.00,Flow 400.00, RPM 80.00, Press 5000.00, Tq 18000.00, ROP 157.24
11/17/2020 | 13:01 | 13:10 | 0.15 | 16035 | 16035 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 10D | Survey & Connection
11/17/2020 | 13:10 | 14:00 | 0.83 | 16035 | 16041 | 6 | LAT | 3: BHA #3 (Curve and Lateral) | 2J | Slide Drill f/16035.00 t/16041.00, TF , w/WOB 65.00,Flow 400.00, Press 3900.00, Tq 0.00, ROP 7.20
11/17/2020 | 14:00 | 14:50 | 0.83 | 16041 | 16041 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 3D | Back ream out 3 stands
11/17/2020 | 14:50 | 24:00 | 9.17 | 16041 | 16041 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Called TD @ 16041 due to hitting ash bed. Circulate hole clean to POOH to lay down tools
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_18_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 11 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/18/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 7250 |  |  | Well Cost($): |  | 89850
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr (BHA 3) |  | Run (BHA 3) |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16041 |  | 10528 |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 10
End Depth (Usft): |  | 16041 |  | 16041 |  | OD (in): |  |  |  | 300: | 19 | YP: | 9
Total Drilled (Usft): |  |  |  | 5513 |  | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 44
Slide Drilled (Usft): |  |  |  | 865 | [5 empty] | 100: | 12 | Chlorides: | 49000
Rotary Drilled (Usft): |  |  |  | 4648 | [5 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.10
Drlg/Circ Hrs: |  | 0.00 / 3.68 |  | 42.43 / 15.50 |  | Bit Details |  |  |  | 3: | 5 | Oil/Water:
Slide Drilling Hrs: |  |  |  | 22.55 |  | SN: |  | 13509567 |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: |  |  |  | 19.88 |  | Bit # |  | 3 |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): |  |  |  | 233.76 / 38.36 |  | OD (in) / TFA: |  | 6.750 / 1.491
BRT Hrs: |  | 10.5 |  | 80.33 |  | Grade In: |  | New
% Slide: |  |  |  | 15.69 |  | Grade Out:
% Rotary: |  |  |  | 84.31 |  | Make / Model: |  | Halliburton / GTD64M
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
James |  | Billy McFarland |  | Chris Hendrix
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
BHA Details
Description |  |  |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Weight (ft/lbs) |  | Length (Usft) |  | Total Length (Usft)
6 3/4" Halliburton- GTD64M w/ 6 x 18s - TFA 1.49 |  |  |  | 6.75 | 2 |  |  |  |  | 0.75 |  | 0.75
6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  |  | 5.5 | 2 |  |  |  |  | 32.96 |  | 33.71
BTI Valve |  |  |  | 5 | 2.375 |  |  |  |  | 2.37 |  | 36.08
Pony Collar |  |  |  | 5.063 | 2.125 |  |  |  |  | 11.8 |  | 47.88
UBHO/ Muleshoe |  |  |  | 5.375 | 2.375 |  |  |  |  | 4.02 |  | 51.9
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.188 |  |  |  |  | 30.64 |  | 82.54
Non Mag Drill Collar (NO HARDBANDING) |  |  |  | 5.125 | 2.25 |  |  |  |  | 30.29 |  | 112.83
Cougar Thruster |  |  |  | 5 | 2 |  |  |  |  | 24.21 |  | 137.04
Crossover (XT39 Pin x DS42 Box) |  |  |  | 5.25 | 2.5 |  |  |  |  | 3.65 |  | 140.69
27 Stands of 4 1/2" DP |  |  |  | 4.5 | 2.5 |  |  |  |  | 2556.83 |  | 2697.52
NOV Shock Sub/ Agitator/ Safety Joint |  |  |  | 5 | 2 |  |  |  |  | 28.71 |  | 2726.23
2726.23
Motor Details
SN |  | Make |  | Model |  | Lobes | Bit to Bend(Usft) |  | Bend Angle |  | Rev Per Gal |  | Housing
PPM250016 |  | PDCI |  | 6/7 8.8 |  | 6/7 | 4.08 |  | 2.12 |  | 0.68 |  | FBH
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 48.93 | 80 | 352 | 400 | 4607.14 | 3800 | 276 | 320 | 225 | 160 | 18000 | 2000
Run | 128.91 | 40.69 | 72.75 | 342 | 395.3 | 4567 | 3704.5 | 276 | 283.64 | 223.35 | 182.7 | 14268.12 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional & MWD / Gamma Services |  |  |  |  | 11/18/2020 |  | 2 |  | 6850 |  | 1 | 6850
Perdiem Per Hand |  |  |  |  | 11/18/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 7250
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/18/2020 | 00:00 | 03:41 | 3.68 | 16041 | 16041 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 5A | Circulate
11/18/2020 | 03:41 | 09:30 | 5.82 | 16041 | 16041 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6B | TOH to lay down tools
11/18/2020 | 09:30 | 10:30 | 1 | 16041 | 16041 | 0 | LAT | 3: BHA #3 (Curve and Lateral) | 6P | Lay down BHA #3
11/18/2020 | 10:30 | 24:00 | 13.5 | 16041 | 16041 | 0 | LAT |  | 24B | Standby for production casing opps
Well Seeker PRO 2.0.8.0 - Pro Directional

## 11_19_2020_DDR
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # / AFE # |  | 42-477-31140 / 20DD0308MG |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Report # |  | 12 |  |  | Well: |  | Yukon A 1H
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Longitude: |  | 96° 42' 50.165" W
|  |  |  | Rig: |  | Patterson 248 |  |  | County / State: |  | Washington / Texas
|  |  |  | Date: |  | 11/19/2020 |  |  | Report Time: |  | 00:00-24:00
|  |  |  | Daily Cost($): |  | 4800 |  |  | Well Cost($): |  | 94650
24hr Summary:
24hr Lookahead:
Drilling Summary |  | 24Hr () |  | Run () |  | Casing Data |  |  |  | Fluids
Start Depth (Usft): |  | 16041 |  |  |  | Csg Shoe MD(Usft): |  |  |  | 600: | 29 | PV: | 10
End Depth (Usft): |  | 16041 |  | 16041 |  | OD (in): |  |  |  | 300: | 19 | YP: | 9
Total Drilled (Usft): | [5 empty] | Weight (ft/lbs): |  |  |  | 200: | 15 | Viscosity: | 44
Slide Drilled (Usft): | [9 empty] | 100: | 12 | Chlorides: | 49000
Rotary Drilled (Usft): | [9 empty] | 6: | 6 | % Sand/Solids: | 0.25 / 9.10
Drlg/Circ Hrs: | [5 empty] | Bit Details |  |  |  | 3: | 5 | Oil/Water: | 0.00
Slide Drilling Hrs: | [5 empty] | SN: |  |  |  | 10s Gel: | 5 | Weight (ppg): | 9.3
Rotary Drilling Hrs: | [5 empty] | Bit # |  |  |  | PH / Temp(F) | 0.0 / 130.00 | Fluid Loss / Mud Type: | 6 / OBM
ROP Rot/Slide (Usft/hr): | [5 empty] | OD (in) / TFA:
BRT Hrs: | [5 empty] | Grade In:
% Slide: | [5 empty] | Grade Out:
% Rotary: | [5 empty] | Make / Model:
Personnel
Company Man |  | Directional Driller |  | MWD Engineer |  | Drilling Engineer |  | Mud Engineer |  | Geologist |  | Tool Pusher
Jim |  | Nathan Marks |  | Russell Arnold |  | David LeBlanc | [5 empty] | Bobby Lewis
James |  | Billy McFarland |  | Chris Hendrix
Trainee 1 |  | Trainee 2 |  | RSS Eng. 1 |  | Rss Eng. 2 |  | Third Man |  | Fourth Man
Drilling Parameters
| ROP | WOB | RPM | RPM DH | FLOW | SPP ON | SPP OFF | SPM | PU | ROT | SO | TQ ON | TQ OFF
| (Usft/hr) | (klbs) |  |  | (gpm) | (psi) | (psi) |  | (klbs) | (klbs) | (klbs) | (kftlbs) | (kftlbs)
24 Hrs | 0 | 48.93 | 80 | 80 | 400 | 4607.14 | 3800 | 276 | 320 | 225 | 160 | 18000 | 2000
Run | 0 | 40.69 | 72.75 | 73 | 395.3 | 4567 | 3704.5 | 276 | 283.64 | 223.35 | 182.7 | 14268.12 | 2000
Daily Costs
Description |  |  |  |  | Date | Serial # | Cost Code |  | Unit Cost($) |  | Qty | Total Cost ($)
Directional Standby |  |  |  |  | 11/19/2020 |  | 4 |  | 4400 |  | 1 | 4400
Perdiem Per Hand |  |  |  |  | 11/19/2020 |  | 3 |  | 100 |  | 4 | 400
Total | [11 empty] | 4800
Daily Activity
Date | From | To | Hrs | Start (Usft) | End (Usft) | CL | Phase | BHA | Code | Description
11/19/2020 | 00:00 | 24:00 | 24 | 16041 | 16041 | 0 | LAT |  | 24B | Standby for production casing opps.
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2734.05 (Usft)
Well: |  |  | Yukon A 1H | BHA #: |  | 1 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1141420 | Bit #: |  |  | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 11/02/2020 | Depth In: |  | 105 | Total Drilled: |  | 3065.00 (Usft)
Date Out: |  |  | 11/02/2020 | Depth Out: |  | 3170 | Drilling / Circ Hours: |  | 4.90 / 3.38
Survey Offset: |  |  | 0
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 43518 | 13 1/2 Ulterra U616S 9 x 14s | 13.5 | 2.75 |  | 6 5/8 REG |  | 1.35 | 1.35
| 2 | PPM800015 | 7/8 Lobe 5.9 Stage | 7.875 |  |  | 6 5/8 REG / 6 5/8 REG |  | 37.27 | 38.62
| 3 | SD610469 | 13" Stabilizer | 7.813 | 2.813 |  | 6 5/8 REG / 6 5/8 REG |  | 7.45 | 46.07
| 4 | SD56559 | NM Pony | 7.813 | 3.438 |  | 6 5/8 REG / 6 5/8 REG |  | 9.7 | 55.77
| 5 | 775210 | UBHO/Muleshoe | 7.688 | 2.75 |  | 6 5/8 REG / 6 5/8 REG |  | 3.9 | 59.67
| 6 | SD56047 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.6 | 89.27
| 7 | SD56067 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.89 | 119.16
| 8 | DS MT3X-500-049 | Cougar Thruster | 5 | 2 |  | 4 XT39 / 4 XT39 |  | 24.21 | 143.37
| 9 | SD119321 | Crossover (XT39 Pin x DS42 Box) | 5.25 | 2.5 |  | 4 XT39 / 4 XT39 |  | 3.65 | 147.02
| 10 | Rig1 | 27 Stands of 4 1/2" DP | 4.5 | 2.5 |  | DS42 / DS42 |  | 2558.32 | 2705.34
| 11 | AG000525-0013 | NOV Shock Sub/ Agitator/ Safety Joint | 5 | 2 |  | DS42 / DS 42 |  | 28.71 | 2734.05
| 12 | [8 empty] | 2734.05
Comments
Bit Info= 13 1/2" -Ulterra-U616S SN= 43518 Jets= 9x14's TFA= 1.353 Motor Info= 8", 7/8, 5.9 Stg. @ 1.5? w/ 13" NBS Bit To Bend= 6.04' Pad OD= 8 3/8" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
13.5 |  |  | 13 1/2 Ulterra U616S 9 x 14s | 0.00 | Baker Hughes | U616S |  |  | 3065
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 Lobe 5.9 Stage |  |  | PDCI / 7/8 5.9 | 0.00 / 1.50 |  | 0 | 0 | 0 | 0
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
0 |  |  | 0 | 0 |  |  | 0 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
Stabilizer Details
Component Number |  |  | Description | OD[in] |  | Blade Length[in] |  |  | Stab -> Bit[Usft]

## BHA_2_Intermediate
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2674.15 (Usft)
Well: |  |  | Yukon A 1H | BHA #: |  | 2 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1141420 | Bit #: |  | 1 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 11/10/2020 | Depth In: |  | 3170 | Total Drilled: |  | 7358.00 (Usft)
Date Out: |  |  | 11/12/2020 | Depth Out: |  | 10528 | Drilling / Circ Hours: |  | 25.63 / 2.68
Survey Offset: |  |  | 0
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 53502 | 9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s | 9.875 | 2.5 |  | 6 5/8 REG |  | 1.3 | 1.3
| 2 | PPM800038 | 7/8 Lobe 5.9 Stage | 7.875 |  | 7.938 / 1.89 | 6 5/8 REG / 6 5/8 REG |  | 37.69 | 38.99
| 3 | SD56559 | NM Pony | 7.813 | 3.438 |  | 6 5/8 REG / 6 5/8 REG |  | 9.7 | 48.69
| 4 | 775210 | UBHO/Muleshoe | 7.688 | 2.75 |  | 6 5/8 REG / 6 5/8 REG |  | 3.9 | 52.59
| 5 | SD56047 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.6 | 82.19
| 6 | SD56067 | NMDC | 8 | 3.25 |  | 6 5/8 REG / 6 5/8 REG |  | 29.89 | 112.08
| 7 | SD102057 | 4 1/2 XH P x 6 5/8 Reg B | 6.438 | 2.75 |  | 4 1/2 XH / 6 5/8 REG |  | 2.34 | 114.42
| 8 | Rig 2 | 2 stands of 6 1/2 in Collars | 6.5 | 2.375 |  | 4 1/2 XH / 4 1/2 XH |  | 185.52 | 299.94
| 9 | SD109796 | 4 1/2 IF B x 4 1/2 XH P | 6.438 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2.33 | 302.27
| 10 | Rig 1 | 9 joints of HWDP | 5 | 3 |  | 4 1/2 IF / 4 1/2 IF |  | 276.52 | 578.79
| 11 | Rig 3 | 22 stands of Drill pipe | 6 | 2.75 |  | 4 1/2 IF / 4 1/2 IF |  | 2064.94 | 2643.73
| 12 | AGHF0675-0034 | NOV Agitator and Shock Sub | 6.75 | 2 |  | 4 1/2 IF / 4 1/2 IF |  | 30.42 | 2674.15
| 13 | [8 empty] | 2674.15
Comments
Bit Info= 9 7/8" -Ulterra-SPL613 SN= 53502 Jets= 6x14s & 3x16's TFA= 1.491 PN= U03494 Motor Info= 8", 7/8, 5.9 Stg. @ 2? FBH TS Bit To Bend= 6.02' Pad OD= 8 5/16" Rev / Gal= 0.166 Flow Range= 400-900 Gpm Max Diff= 1,330 Stall Torque= 33,030 Max torque= 22,020
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
9.875 |  | PDC | 9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s | 1.49 | Ulterra | SPL613 | New | 0-1-CT-S-X-1/16-TD | 7358
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
7/8 Lobe 5.9 Stage |  |  | PDCI / 7/8 5.9 | 6.02 / 2.00 |  | 0 | 8.31 | 0 | 1330
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
22020 |  |  | 0 | 0 |  | 400-900 | 0.166 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit

## BHA_3_Curve_and_Lateral
BOTTOM HOLE ASSEMBLY
Operator: |  |  | Magnolia Oil & Gas | Rig: |  | Patterson 248 | Total Length: |  | 2726.23 (Usft)
Well: |  |  | Yukon A 1H | BHA #: |  | 3 | BHA Weight (Air/Mud): |  | 0.00 / 0.00 (klbs)
Job #: |  |  | LTX1141420 | Bit #: |  | 3 | Wt. Below Jars (Air/Mud): |  | 0.00 / 0.00 (klbs)
Date In: |  |  | 11/15/2020 | Depth In: |  | 10528 | Total Drilled: |  | 5513.00 (Usft)
Date Out: |  |  | 11/18/2020 | Depth Out: |  | 16041 | Drilling / Circ Hours: |  | 42.43 / 15.50
Survey Offset: |  |  | 69 | Gamma Offset: |  | 59
Proposed BHA | # | SN | Description | OD [in] | ID [in] | FN OD [in] / FN Len [Usft] | Cnx Up / Cnx Dn | Wt[lb/ft] / Comp Wt[klbs] / Tot Wt[klbs] | Length [Usft] | Total Length [Usft]
| 1 | 13509567 | 6 3/4" Halliburton- GTD64M w/ 6 x 18s | 6.75 | 2 |  | 3 1/2 Reg |  | 0.75 | 0.75
| 2 | PPM250016 | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS | 5.5 | 2 | 5.000 / 1.97 | 4 XT39 / 3 1/2 Reg |  | 32.96 | 33.71
| 3 | Rig | BTI Valve | 5 | 2.375 |  | 4 XT39 / 4 XT39 |  | 2.37 | 36.08
| 4 | SD56727 | Pony Collar | 5.063 | 2.125 |  | 4 XT39 / 4 XT39 |  | 11.8 | 47.88
| 5 | 500037 | UBHO/ Muleshoe | 5.375 | 2.375 | 1.88 | 4 XT39 / 4 XT39 |  | 4.02 | 51.9
| 6 | SD56702 | Non Mag Drill Collar (NO HARDBANDING) | 5.125 | 2.188 |  | 4 XT39 / 4 XT39 |  | 30.64 | 82.54
| 7 | SD56709 | Non Mag Drill Collar (NO HARDBANDING) | 5.125 | 2.25 |  | 4 XT39 / 4 XT39 |  | 30.29 | 112.83
| 8 | DS MT3X-500-049 | Cougar Thruster | 5 | 2 | 5.000 / 1.56 | 4 XT39 / 4 XT39 |  | 24.21 | 137.04
| 9 | SD119321 | Crossover (XT39 Pin x DS42 Box) | 5.25 | 2.5 |  | 4 XT39 / 4 XT39 |  | 3.65 | 140.69
| 10 | Rig1 | 27 Stands of 4 1/2" DP | 4.5 | 2.5 |  | DS42 / DS42 |  | 2556.83 | 2697.52
| 11 | AG000525-0013 | NOV Shock Sub/ Agitator/ Safety Joint | 5 | 2 | 5.500 / 1.95 | DS42 / DS 42 |  | 28.71 | 2726.23
| 12 | [8 empty] | 2726.23
Comments
Bit Info= 6 3/4" Security - GTD64M SN=13509567 Jets=6-18's TFA= 1.491 PN= 1138553 Motor Info= 5", 6/7, 8.8 Stg. @ 2.12? w/ True Slick Bit To Bend= 4.08' Pad OD= 5 5/8" Rev / Gal= 0.68 Flow Range= 150-400 Gpm Max Diff=2,240
Bit Details
Size [in] |  | Type | Description | TFA | Make | Model | Grade In | Grade Out | Drilled [Usft]
6.75 |  | PDC | 6 3/4" Halliburton- GTD64M w/ 6 x 18s | 1.49 | Halliburton | GTD64M | New |  | 5513
Motor Details
Description |  |  | Make / Model | Bit to Bend [Usft] / Bend (deg) |  | Stab OD[in] | Kick Pad OD[in] | Press. Loss (psi) | Max Diff Press. (psi)
6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  | PDCI / 6/7 8.8 | 4.08 / 2.12 |  | 0 | 5.62 | 0 | 2240
Max Torque[kft-lbs] |  |  | Diff Press (psi) | Max RPM |  | Flow Range | Rev/Gal | Bend Housing | Bearing Type
8014 |  |  | 0 | 272 |  | 150-400 | 0.68 | FBH
Pre Run Dyno HP% |  |  | Stator Vendor | Stator Type |  | Stator Fit
MWD Details
MWD Type |  |  | Orifice | Orifice Type |  | Poppet | Make | Model | Fin Size
Pulser SN |  |  | Driver SN | Dir. Module SN |  | Battery 1 SN | Battery 2 SN | Battery 3 SN | Helix SN
Gamma SN |  |  | EM SN | Pulse Width |  | Data Rate | EM Power | EM Freq | Retrievable
Plug In Date |  |  | Plug In Time | Plug Out Date |  | Plug Out Time | Plug In Hrs

## Perf Rep BHA 1
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31140 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Well: |  | Yukon A 1H
|  |  |  | Longitude: |  | 96° 42' 50.165" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 1
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 11/02/2020 02:25 |  | SN: |  | PPM800015 |  |  |  | WOB Rotate (klbs): |  | 14.00
Date Out: |  | 11/02/2020 18:00 |  | Description: |  | 7/8 Lobe 5.9 Stage |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 105.00 / 3170.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 89.41
Inc In/Out: |  | 0.15 / 9.06 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 874.29
Azi In/Out: |  | 178.20 / 260.60 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 1685.42
Total Drilled (Usft): |  | 3065 |  | Bend Angle: |  | 1.5 |  |  |  | On Btm Press (psi): |  | 1308.33
%Slide (Ftg): |  | 7.47 |  | Bit to Bend (Usft): | [5 empty] | Tq On Btm (kftlbs): |  | 10882.35
%Slide (Time): |  | 26.12 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs):
Slide Drilled (Usft): |  | 229 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 1.28 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 92.53 |  | Kickpad OD (in): | [5 empty] | Make: |  | Baker Hughes
%Rotary (Time): |  | 73.88 |  | Body OD (in): |  | 7.875 |  |  |  | Model: |  | U616S
Rotary Drilled (Usft): |  | 2836 |  | Fishneck OD (in): | [5 empty] | OD (in): |  | 13.5
Rotary Hours: |  | 3.62 |  | Length (Usft): |  | 37.27 |  |  |  | TFA: |  | 0.00
Total Drlg Hrs: |  | 4.90 |  | Integral Float: |  | NO |  |  |  | Bit #
Circ/BRT Hrs: |  | 3.38 / 15.58 |  | Rev per Gal: | [5 empty] | Grade In:
Slide ROP (Usft/hr): |  | 178.91 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 783.43 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 4.90
Avg ROP (Usft/hr): |  | 625.51 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 3.38
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
5 / 4 | 3 / 2 | 1 / 1 |  | 0.00 |  |  |  | 9.2 |  | WBM |  |  | 117
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
[10 empty] | 2 |  | 2.00 / 2.01
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
13 1/2 Ulterra U616S 9 x 14s 0.00 |  |  |  | 43518 |  | 13.5 | 2.75 |  |  |  | 1.35 | 1.35
7/8 Lobe 5.9 Stage 0.00 |  |  |  | PPM800015 |  | 7.875 |  |  |  |  | 37.27 | 38.62
13" Stabilizer 0.00 |  |  |  | SD610469 |  | 7.813 | 2.813 |  |  |  | 7.45 | 46.07
NM Pony 0.00 |  |  |  | SD56559 |  | 7.813 | 3.438 |  |  |  | 9.7 | 55.77
UBHO/Muleshoe 0.00 |  |  |  | 775210 |  | 7.688 | 2.75 |  |  |  | 3.9 | 59.67
NMDC 0.00 |  |  |  | SD56047 |  | 8 | 3.25 |  |  |  | 29.6 | 89.27
NMDC 0.00 |  |  |  | SD56067 |  | 8 | 3.25 |  |  |  | 29.89 | 119.16
Cougar Thruster 0.00 |  |  |  | DS MT3X-500-049 |  | 5 | 2 |  |  |  | 24.21 | 143.37
Crossover (XT39 Pin x DS42 Box) 0.00 |  |  |  | SD119321 |  | 5.25 | 2.5 |  |  |  | 3.65 | 147.02
27 Stands of 4 1/2" DP 0.00 |  |  |  | Rig1 |  | 4.5 | 2.5 |  |  |  | 2558.32 | 2705.34
NOV Shock Sub/ Agitator/ Safety Joint 0.00 |  |  |  | AG000525-0013 |  | 5 | 2 |  |  |  | 28.71 | 2734.05
-1.00 | [11 empty] | 2734.05
Additional Comments
Motor drained at surface with no visible damage. Motor was subjected to WBM @ 9.2ppg. Motor was ran for 3 surfaces. Totals are as follows Footage 9527 Circ Hrs 19.5 Drilling hrs 14.47
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 2
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31140 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Well: |  | Yukon A 1H
|  |  |  | Longitude: |  | 96° 42' 50.165" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD of Section |  |  | BHA # |  | 2
|  |  |  | Lead DD: |  | Jeff Wells |  |  | Company Man: |  | Kevin Burt
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 11/10/2020 15:10 |  | SN: |  | PPM800038 |  |  |  | WOB Rotate (klbs): |  | 36.00
Date Out: |  | 11/12/2020 16:40 |  | Description: |  | 7/8 Lobe 5.9 Stage |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 3170.00 / 10528.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 0.00 / 75.37
Inc In/Out: |  | 9.06 / 16.58 |  | Model: |  | 7/8 5.9 |  |  |  | Flow Rate (gpm): |  | 867.44
Azi In/Out: |  | 260.60 / 315.38 |  | Lobes / Stages: |  | 7/8 / 5.90 |  |  |  | Off Btm Press (psi): |  | 4370.51
Total Drilled (Usft): |  | 7358 |  | Bend Angle: |  | 2 |  |  |  | On Btm Press (psi): |  | 5036.75
%Slide (Ftg): |  | 6.86 |  | Bit to Bend (Usft): |  | 6.02 |  |  |  | Tq On Btm (kftlbs): |  | 15768.42
%Slide (Time): |  | 29.14 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 505 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 7.47 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 93.14 |  | Kickpad OD (in): |  | 8.313 |  |  |  | Make: |  | Ulterra
%Rotary (Time): |  | 70.85 |  | Body OD (in): |  | 7.875 |  |  |  | Model: |  | SPL613
Rotary Drilled (Usft): |  | 6853 |  | Fishneck OD (in): |  | 7.938 |  |  |  | OD (in): |  | 9.875
Rotary Hours: |  | 18.16 |  | Length (Usft): |  | 37.69 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 25.63 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 1
Circ/BRT Hrs: |  | 2.68 / 49.50 |  | Rev per Gal: |  | 0.166 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 67.6 |  | # Stalls / Pressure: | [5 empty] | Grade Out: |  | 0-1-CT-S-X-1/16-TD
Rot ROP (Usft/hr): |  | 377.37 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 25.63
Avg ROP (Usft/hr): |  | 287.09 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 2.68
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
33 / 21 | 16 / 11 | 5 / 4 |  | 0.00 |  | 12 | 9 | 9.1 | 50000 | OBM | 8.3 | 0.25 | 257
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
[10 empty] | 5 |  | 6.20 / 5.59
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
9 7/8 Ulterra SPL613 Jetted 6*14s 3*16s 1.49 |  |  |  | 53502 |  | 9.875 | 2.5 |  |  |  | 1.3 | 1.3
7/8 Lobe 5.9 Stage 0.00 |  |  |  | PPM800038 |  | 7.875 |  |  |  |  | 37.69 | 38.99
NM Pony 0.00 |  |  |  | SD56559 |  | 7.813 | 3.438 |  |  |  | 9.7 | 48.69
UBHO/Muleshoe 0.00 |  |  |  | 775210 |  | 7.688 | 2.75 |  |  |  | 3.9 | 52.59
NMDC 0.00 |  |  |  | SD56047 |  | 8 | 3.25 |  |  |  | 29.6 | 82.19
NMDC 0.00 |  |  |  | SD56067 |  | 8 | 3.25 |  |  |  | 29.89 | 112.08
4 1/2 XH P x 6 5/8 Reg B 0.00 |  |  |  | SD102057 |  | 6.438 | 2.75 |  |  |  | 2.34 | 114.42
2 stands of 6 1/2 in Collars 0.00 |  |  |  | Rig 2 |  | 6.5 | 2.375 |  |  |  | 185.52 | 299.94
4 1/2 IF B x 4 1/2 XH P 0.00 |  |  |  | SD109796 |  | 6.438 | 2.75 |  |  |  | 2.33 | 302.27
9 joints of HWDP 0.00 |  |  |  | Rig 1 |  | 5 | 3 |  |  |  | 276.52 | 578.79
22 stands of Drill pipe 0.00 |  |  |  | Rig 3 |  | 6 | 2.75 |  |  |  | 2064.94 | 2643.73
NOV Agitator and Shock Sub 0.00 |  |  |  | AGHF0675-0034 |  | 6.75 | 2 |  |  |  | 30.42 | 2674.15
-1.00 | [11 empty] | 2674.15
Additional Comments
Motor Drained on surface and showed no visible signs of wear
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## Perf Rep BHA 3
|  |  |  | Job # |  | LTX1141420 |  |  | Operator: |  | Magnolia Oil & Gas
|  |  |  | API Job # |  | 42-477-31140 |  |  | Field: |  | Washington County, TX - Magnolia Oil & Gas
|  |  |  | Latitude: |  | 30° 9' 53.179" N |  |  | Well: |  | Yukon A 1H
|  |  |  | Longitude: |  | 96° 42' 50.165" W |  |  | State: |  | Texas
|  |  |  | Rig: |  | Patterson 248 |  |  | County: |  | Washington
|  |  |  | Reason POOH: |  | TD Well |  |  | BHA # |  | 3
|  |  |  | Lead DD: |  | Nathan Marks |  |  | Company Man: |  | Jim
BHA Performance Report | [9 empty] | Drilling Parameters
Run Data |  |  |  | Motor data | [5 empty] | Temperature (degF): |  | 0.00/0.00/0.00
Date In: |  | 11/15/2020 02:10 |  | SN: |  | PPM250016 |  |  |  | WOB Rotate (klbs): |  | 40.00
Date Out: |  | 11/18/2020 10:30 |  | Description: |  | 6/7 Lobe 8.8 Stage FBH @ 2.12? TS |  |  |  | WOB Slide (klbs):
Depth In/Out(Usft): |  | 10528.00 / 16041.00 |  | Make: |  | PDCI |  |  |  | RPM: |  | 272.00 / 72.75
Inc In/Out: |  | 16.58 / 94.70 |  | Model: |  | 6/7 8.8 |  |  |  | Flow Rate (gpm): |  | 395.3
Azi In/Out: |  | 315.38 / 314.30 |  | Lobes / Stages: |  | 6/7 / 8.80 |  |  |  | Off Btm Press (psi): |  | 3704.5
Total Drilled (Usft): |  | 5513 |  | Bend Angle: |  | 2.12 |  |  |  | On Btm Press (psi): |  | 4567
%Slide (Ftg): |  | 15.69 |  | Bit to Bend (Usft): |  | 4.08 |  |  |  | Tq On Btm (kftlbs): |  | 14268.12
%Slide (Time): |  | 53.14 |  | Sleeve Stab OD (in): | [5 empty] | Tq Off Btm (kftlbs): |  | 2000
Slide Drilled (Usft): |  | 865 |  | Bearing Gap (in): | [5 empty] | Avg Diff Press (psi):
Slide Hours: |  | 22.55 |  | Stab to Bit (Usft): | [5 empty] | Bit Data
%Rotary (Ftg): |  | 84.31 |  | Kickpad OD (in): |  | 5.625 |  |  |  | Make: |  | Halliburton
%Rotary (Time): |  | 46.85 |  | Body OD (in): |  | 5.5 |  |  |  | Model: |  | GTD64M
Rotary Drilled (Usft): |  | 4648 |  | Fishneck OD (in): |  | 5 |  |  |  | OD (in): |  | 6.75
Rotary Hours: |  | 19.88 |  | Length (Usft): |  | 32.96 |  |  |  | TFA: |  | 1.49
Total Drlg Hrs: |  | 42.43 |  | Integral Float: |  | YES |  |  |  | Bit # |  | 3
Circ/BRT Hrs: |  | 15.50 / 80.33 |  | Rev per Gal: |  | 0.68 |  |  |  | Grade In: |  | New
Slide ROP (Usft/hr): |  | 38.36 |  | # Stalls / Pressure: | [5 empty] | Grade Out:
Rot ROP (Usft/hr): |  | 233.8 |  | Stator Vendor/Type/Fit: |  | / / 0.000 |  |  |  | Drill Hrs: |  | 42.43
Avg ROP (Usft/hr): |  | 129.93 |  | Pre Run Dyno HP%: | [5 empty] | Circ Hrs: |  | 15.50
Mud Data
600/300 | 200/100 | 6/3 | PH | Oil/Water |  | PV | YP | Wt (ppg) | Chlorides | Type | %Solids | %Sand | Temp (degF)
29 / 19 | 15 / 12 | 6 / 5 |  | 0.00 |  | 10 | 9 | 9.3 | 49000 | OBM | 9.1 | 0.25 | 309
Sensor Offsets(Usft) | [9 empty] | Motor Yield
Svy | Gam | Res | PWD | Dens | Neu | Sonic | NB Inc | NB Azi | Gyro | Plan MY (°/100ft) |  | Act MY (°/100ft)
69 | 59 | [10 empty] | 0.00 / 16.02
BHA Details
Description |  |  |  | SN |  | OD (in) | ID (in) | TJ OD (in) | TJ ID (in) | Wt (ft/lbs) | Len (Usft) | Total Length (Usft)
6 3/4" Halliburton- GTD64M w/ 6 x 18s 1.49 |  |  |  | 13509567 |  | 6.75 | 2 |  |  |  | 0.75 | 0.75
6/7 Lobe 8.8 Stage FBH @ 2.12? TS 0.00 |  |  |  | PPM250016 |  | 5.5 | 2 |  |  |  | 32.96 | 33.71
BTI Valve 0.00 |  |  |  | Rig |  | 5 | 2.375 |  |  |  | 2.37 | 36.08
Pony Collar 0.00 |  |  |  | SD56727 |  | 5.063 | 2.125 |  |  |  | 11.8 | 47.88
UBHO/ Muleshoe 0.00 |  |  |  | 500037 |  | 5.375 | 2.375 |  |  |  | 4.02 | 51.9
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD56702 |  | 5.125 | 2.188 |  |  |  | 30.64 | 82.54
Non Mag Drill Collar (NO HARDBANDING) 0.00 |  |  |  | SD56709 |  | 5.125 | 2.25 |  |  |  | 30.29 | 112.83
Cougar Thruster 0.00 |  |  |  | DS MT3X-500-049 |  | 5 | 2 |  |  |  | 24.21 | 137.04
Crossover (XT39 Pin x DS42 Box) 0.00 |  |  |  | SD119321 |  | 5.25 | 2.5 |  |  |  | 3.65 | 140.69
27 Stands of 4 1/2" DP 0.00 |  |  |  | Rig1 |  | 4.5 | 2.5 |  |  |  | 2556.83 | 2697.52
NOV Shock Sub/ Agitator/ Safety Joint 0.00 |  |  |  | AG000525-0013 |  | 5 | 2 |  |  |  | 28.71 | 2726.23
-1.00 | [11 empty] | 2726.23
Additional Comments
BHA performed as expected drilled curve and lateral section per plan. In curve motor averaged 13? / 100. In lateral yields avergaged 10? / 100.. At surface motor drained strong with no visuable signs of damage to motor at surface. BHA was subject to 311? oil base mud.
Images
Well Seeker PRO 2.0.8.0 - Pro Directional

## BHA_1_Surface_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 1 (Surface) |  |  |  |  | RKB: |  |  |  | 418 |  | North Reference: |  | GRID |  | Total Drilled: |  | 3170
Site: |  |  |  |  | Yukon - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 229
Well Name: |  |  |  |  | Yukon A 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 0.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 418 |  | VS Azimuth: |  | 313.12 |  | Rotate: |  | 2941
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
11/02/2020 | 02:25 | 02:45 | 0.33333 |  | 214 | 214 | Rotate |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | 40 | 570 | 5000 | 642 | 500 | 580 | -80 | 100 | 50000 | 50000 | 50000
11/02/2020 | 02:51 | 02:59 | 0.13333 | 214 | 306 | 92 | Rotate |  | 230 | 0.3 | 202.9 | 230 | -0.62 | -0.08 | -0.62 | 0.16 |  |  | 5 | 40 | 705 | 5000 | 690 | 500 | 580 | -80 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:04 | 03:10 | 0.1 | 306 | 398 | 92 | Rotate |  | 322 | 0.5 | 200.3 | 322 | -1.22 | -0.31 | -1.22 | 0.22 |  |  | 5 | 40 | 808 | 7000 | 920 | 1000 | 1070 | -70 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:15 | 03:19 | 0.066667 | 398 | 492 | 94 | Rotate |  | 416 | 0.4 | 186.2 | 415.99 | -1.93 | -0.49 | -1.93 | 0.16 |  |  | 10 | 100 | 900 | 12000 | 1410 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:23 | 03:24 | 0.016667 | 492 | 495 | 3 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 180 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:24 | 03:29 | 0.083333 | 495 | 513 | 18 | Slide | 0 | 510 | 0.7 | 224.1 | 509.99 | -2.67 | -0.93 | -2.67 | 0.49 |  |  | 10 |  | 900 |  | 216 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:29 | 03:33 | 0.066667 | 513 | 586 | 73 | Rotate | Drilling Parameters WOB: 10; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 1095 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:37 | 03:42 | 0.083333 | 586 | 602 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 10; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 192 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:42 | 03:46 | 0.066667 | 602 | 679 | 77 | Rotate |  | 603 | 1.4 | 247.9 | 602.97 | -3.51 | -2.37 | -3.51 | 0.87 |  |  | 10 | 100 | 900 | 12000 | 1155 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:51 | 03:53 | 0.033333 | 679 | 684 | 5 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 150 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 03:53 | 04:00 | 0.11667 | 684 | 704 | 20 | Slide | 0 | 697 | 2.4 | 264.7 | 696.92 | -4.12 | -5.4 | -4.12 | 1.21 |  |  | 18 |  | 900 |  | 171.43 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:00 | 04:03 | 0.05 | 704 | 773 | 69 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 1380 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:05 | 04:06 | 0.016667 | 773 | 778 | 5 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 300 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:06 | 04:13 | 0.11667 | 778 | 798 | 20 | Slide | 0 | 791 | 4 | 270.8 | 790.77 | -4.26 | -10.64 | -4.26 | 1.74 |  |  | 18 |  | 900 |  | 171.43 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:13 | 04:18 | 0.083333 | 798 | 867 | 69 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 828 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:22 | 04:24 | 0.033333 | 867 | 872 | 5 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 150 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:24 | 04:32 | 0.13333 | 872 | 897 | 25 | Slide | 0 | 885 | 5 | 264.5 | 884.48 | -4.6 | -17.99 | -4.6 | 1.19 |  |  | 18 |  | 900 | 12000 | 187.5 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:32 | 04:35 | 0.05 | 897 | 961 | 64 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 1280 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:38 | 04:40 | 0.033333 | 961 | 965 | 4 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 120 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:40 | 04:49 | 0.15 | 965 | 995 | 30 | Slide | 0 | 980 | 6.9 | 262.9 | 978.97 | -5.71 | -27.78 | -5.71 | 2.01 |  |  | 18 |  | 900 |  | 200 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:49 | 04:52 | 0.05 | 995 | 1056 | 61 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 1220 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:55 | 04:57 | 0.033333 | 1056 | 1061 | 5 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 150 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 04:57 | 05:05 | 0.13333 | 1061 | 1091 | 30 | Slide | 0 | 1074 | 8.7 | 267.2 | 1072.09 | -6.75 | -40.48 | -6.75 | 2.01 |  |  | 18 |  | 900 |  | 225 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 05:05 | 05:09 | 0.066667 | 1091 | 1150 | 59 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 885 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 05:12 | 05:13 | 0.016667 | 1150 | 1154 | 4 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 240 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 05:13 | 05:20 | 0.11667 | 1154 | 1179 | 25 | Slide | 0 | 1167 | 10.2 | 266.7 | 1163.83 | -7.57 | -55.73 | -7.57 | 1.62 |  |  | 18 |  | 900 |  | 214.29 | 1400 | 1820 | -420 | 100 | 50000 | 50000 | 50000
11/02/2020 | 05:20 | 05:23 | 0.05 | 1179 | 1243 | 64 | Rotate | Drilling Parameters WOB: 18; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 1280 | 2200 | 1820 | 380 | 100 | 50000 | 50000 | 50000
11/02/2020 | 05:26 | 05:30 | 0.066667 | 1243 | 1337 | 94 | Rotate |  | 1261 | 10.7 | 266.7 | 1256.27 | -8.55 | -72.75 | -8.55 | 0.53 |  |  | 20 | 100 | 900 | 12000 | 1410 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 05:33 | 05:39 | 0.1 | 1337 | 1431 | 94 | Rotate |  | 1355 | 10.8 | 266.9 | 1348.62 | -9.53 | -90.26 | -9.53 | 0.11 |  |  | 20 | 100 | 900 | 12000 | 940 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 05:43 | 05:50 | 0.11667 | 1431 | 1524 | 93 | Rotate |  | 1448 | 10.5 | 266.8 | 1440.02 | -10.47 | -107.42 | -10.47 | 0.32 |  |  | 20 | 100 | 900 | 12000 | 797.14 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 05:53 | 05:57 | 0.066667 | 1524 | 1619 | 95 | Rotate |  | 1543 | 10.3 | 267.4 | 1533.46 | -11.34 | -124.54 | -11.34 | 0.24 |  |  | 20 | 100 | 900 | 12000 | 1425 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 06:01 | 06:06 | 0.083333 | 1619 | 1713 | 94 | Rotate |  | 1637 | 10.2 | 268.3 | 1625.96 | -11.97 | -141.26 | -11.97 | 0.2 |  |  | 20 | 100 | 900 | 12000 | 1128 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 06:10 | 06:11 | 0.016667 | 1713 | 1725 | 12 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 720 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 06:11 | 06:17 | 0.1 | 1725 | 1745 | 20 | Slide | 0 | 1731 | 10.8 | 268.2 | 1718.38 | -12.49 | -158.38 | -12.49 | 0.64 |  |  | 5 |  | 900 |  | 200 | 1950 | 1820 | 130 | 100 | 70 | 65 | 60
11/02/2020 | 06:17 | 06:23 | 0.1 | 1745 | 1807 | 62 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 620 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 06:27 | 06:30 | 0.05 | 1807 | 1901 | 94 | Rotate |  | 1825 | 11.1 | 267.8 | 1810.67 | -13.12 | -176.23 | -13.12 | 0.33 |  |  | 20 | 100 | 900 | 12000 | 1880 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 06:34 | 06:39 | 0.083333 | 1901 | 1994 | 93 | Rotate |  | 1918 | 10.6 | 267.7 | 1902.01 | -13.8 | -193.72 | -13.8 | 0.54 |  |  | 20 | 100 | 900 | 12000 | 1116 | 2200 | 1820 | 380 | 100 | 70 | 65 | 60
11/02/2020 | 06:43 | 06:47 | 0.066667 | 1994 | 2089 | 95 | Rotate |  | 2013 | 10.4 | 268.1 | 1995.42 | -14.44 | -211.02 | -14.44 | 0.22 |  |  | 20 | 100 | 900 | 12000 | 1425 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 06:51 | 06:56 | 0.083333 | 2089 | 2182 | 93 | Rotate |  | 2106 | 10.2 | 267.8 | 2086.92 | -15.03 | -227.64 | -15.03 | 0.22 |  |  | 20 | 100 | 900 | 12000 | 1116 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 07:00 | 07:17 | 0.28333 | 2182 | 2275 | 93 | Rotate |  | 2199 | 9.9 | 267.1 | 2178.49 | -15.75 | -243.85 | -15.75 | 0.35 |  |  | 20 | 100 | 900 | 12000 | 328.24 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 07:21 | 07:25 | 0.066667 | 2275 | 2279 | 4 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 60 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 11:50 | 12:00 | 0.16667 | 2279 | 2369 | 90 | Rotate |  | 2293 | 9.5 | 266.7 | 2271.15 | -16.61 | -259.66 | -16.61 | 0.43 |  |  | 20 | 100 | 900 | 12000 | 540 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 12:04 | 12:05 | 0.016667 | 2369 | 2375 | 6 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 360 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 12:05 | 12:20 | 0.25 | 2375 | 2400 | 25 | Slide | 0 | 2387 | 10.5 | 266 | 2363.72 | -17.65 | -275.95 | -17.65 | 1.07 |  |  | 12 |  | 900 |  | 100 | 1950 | 1820 | 130 | 100 | 100 | 95 | 90
11/02/2020 | 12:20 | 12:27 | 0.11667 | 2400 | 2463 | 63 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 540 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 12:32 | 12:37 | 0.083333 | 2463 | 2556 | 93 | Rotate |  | 2480 | 10.9 | 263.7 | 2455.1 | -19.21 | -293.15 | -19.21 | 0.63 |  |  | 20 | 100 | 900 | 12000 | 1116 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 12:41 | 12:49 | 0.13333 | 2556 | 2650 | 94 | Rotate |  | 2574 | 10.5 | 262.5 | 2547.47 | -21.3 | -310.47 | -21.3 | 0.49 |  |  | 20 | 100 | 900 | 12000 | 705 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 12:53 | 13:00 | 0.11667 | 2650 | 2744 | 94 | Rotate |  | 2668 | 10.1 | 262.5 | 2639.95 | -23.5 | -327.14 | -23.5 | 0.43 |  |  | 20 | 100 | 900 | 12000 | 805.71 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 13:04 | 13:11 | 0.11667 | 2744 | 2839 | 95 | Rotate |  | 2763 | 9.8 | 263.3 | 2733.52 | -25.53 | -343.42 | -25.53 | 0.35 |  |  | 20 | 100 | 900 | 12000 | 814.29 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 13:15 | 13:21 | 0.1 | 2839 | 2933 | 94 | Rotate |  | 2857 | 10 | 262.5 | 2826.12 | -27.53 | -359.46 | -27.53 | 0.26 |  |  | 20 | 100 | 900 | 12000 | 940 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 13:25 | 13:31 | 0.1 | 2933 | 3027 | 94 | Rotate |  | 2951 | 9.8 | 262.6 | 2918.72 | -29.62 | -375.49 | -29.62 | 0.21 |  |  | 20 | 100 | 900 | 12000 | 940 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 13:35 | 13:44 | 0.15 | 3027 | 3121 | 94 | Rotate |  | 3094 | 9.2 | 260.6 | 3059.76 | -33.06 | -398.83 | -33.06 | 0.48 |  |  | 20 | 100 | 900 | 12000 | 626.67 | 2200 | 1820 | 380 | 100 | 100 | 95 | 90
11/02/2020 | 13:50 | 13:52 | 0.033333 | 3121 | 3170 | 49 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 100; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 1470 | 2200 | 1820 | 380 |  | 100 | 95 | 90

## BHA_2_Intermediate_Slide_Sheet
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA 2 (Intermediate) |  |  |  |  | RKB: |  |  |  | 418 |  | North Reference: |  | GRID |  | Total Drilled: |  | 7358
Site: |  |  |  |  | Yukon - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 505
Well Name: |  |  |  |  | Yukon A 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 0.00 / 0.00 |  |  |  |  | Grid Conv: |  |  |  | 418 |  | VS Azimuth: |  | 313.12 |  | Rotate: |  | 6853
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
11/10/2020 | 18:30 | 18:32 | 0.033333 | 3170 | 3180 | 10 | Rotate | Drilling Parameters WOB: 20; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 450; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 300 | 1500 | 1300 | 200 | 118 | 148 | 145 | 142
11/10/2020 | 19:05 | 19:17 | 0.2 | 3180 | 3240 | 60 | Rotate | Drilling Parameters WOB: 25; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 450; Drilling Parameters Tq: 7000; Drilling Parameters ROP: 300 | 1600 | 1300 | 300 | 118 | 148 | 145 | 142
11/10/2020 | 19:22 | 19:37 | 0.25 | 3240 | 3333 | 93 | Rotate |  | 3262 | 8.9 | 260.6 | 3225.67 | -37.37 | -424.9 | -37.37 | 0.18 |  |  | 32 | 40 | 450 | 7000 | 372 | 1600 | 1300 | 300 | 118 | 148 | 145 | 142
11/10/2020 | 19:41 | 19:46 | 0.083333 | 3333 | 3349 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 12; Drilling Parameters FLOW: 800; Drilling Parameters ROP: 192 | 3600 | 3450 | 150 | 118 | 148 | 145 | 142
11/10/2020 | 19:46 | 19:55 | 0.15 | 3349 | 3427 | 78 | Rotate |  | 3356 | 11.3 | 258.7 | 3318.21 | -40.36 | -441.11 | -40.36 | 2.58 |  |  | 35 | 80 | 800 | 13500 | 520 | 3800 | 3450 | 350 | 118 | 148 | 145 | 142
11/10/2020 | 19:58 | 20:08 | 0.16667 | 3427 | 3521 | 94 | Rotate |  | 3450 | 11.7 | 256.5 | 3410.32 | -44.39 | -459.41 | -44.39 | 0.63 |  |  | 38 | 80 | 800 | 13500 | 564 | 3800 | 3450 | 350 | 118 | 148 | 145 | 142
11/10/2020 | 20:11 | 20:19 | 0.13333 | 3521 | 3614 | 93 | Rotate |  | 3543 | 11.7 | 255.3 | 3501.39 | -48.99 | -477.7 | -48.99 | 0.26 |  |  | 42 | 80 | 900 | 11000 | 697.5 | 4700 | 4300 | 400 | 131 | 148 | 145 | 142
11/10/2020 | 20:22 | 20:28 | 0.1 | 3614 | 3708 | 94 | Rotate |  | 3637 | 11.9 | 257 | 3593.4 | -53.59 | -496.36 | -53.59 | 0.43 |  |  | 45 | 80 | 900 | 11000 | 940 | 4700 | 4300 | 400 | 131 | 148 | 145 | 142
11/10/2020 | 20:32 | 20:36 | 0.066667 | 3708 | 3803 | 95 | Rotate |  | 3732 | 12.1 | 255.7 | 3686.33 | -58.25 | -515.55 | -58.25 | 0.35 |  |  | 45 | 80 | 900 | 11000 | 1425 | 4800 | 4300 | 500 | 131 | 148 | 145 | 142
11/10/2020 | 20:40 | 20:46 | 0.1 | 3803 | 3897 | 94 | Rotate |  | 3826 | 12.3 | 257 | 3778.2 | -62.93 | -534.86 | -62.93 | 0.36 |  |  | 45 | 80 | 900 | 11000 | 940 | 4800 | 4300 | 500 | 131 | 148 | 145 | 142
11/10/2020 | 20:49 | 20:50 | 0.016667 | 3897 | 3900 | 3 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 180 | 4800 | 4300 | 500 | 131 | 152 | 148 | 144
11/10/2020 | 20:50 | 20:58 | 0.13333 | 3900 | 3918 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 135 | 4500 | 4300 | 200 | 131 | 152 | 148 | 144
11/10/2020 | 20:58 | 21:02 | 0.066667 | 3918 | 3991 | 73 | Rotate |  | 3920 | 10.8 | 262.5 | 3870.3 | -66.34 | -553.35 | -66.34 | 1.98 |  |  | 42 | 80 | 900 | 11000 | 1095 | 4800 | 4300 | 500 | 131 | 152 | 148 | 144
11/10/2020 | 21:05 | 21:12 | 0.11667 | 3991 | 4086 | 95 | Rotate |  | 4015 | 10.2 | 262.8 | 3963.71 | -68.55 | -570.52 | -68.55 | 0.63 |  |  | 42 | 80 | 900 | 11000 | 814.29 | 4800 | 4300 | 500 | 131 | 152 | 148 | 144
11/10/2020 | 21:15 | 21:22 | 0.11667 | 4086 | 4179 | 93 | Rotate |  | 4108 | 10.3 | 261.4 | 4055.22 | -70.83 | -586.91 | -70.83 | 0.29 |  |  | 42 | 80 | 900 | 11000 | 797.14 | 4800 | 4300 | 500 | 131 | 152 | 148 | 144
11/10/2020 | 21:25 | 21:26 | 0.016667 | 4179 | 4182 | 3 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 180 | 4800 | 4300 | 500 | 131 | 152 | 148 | 144
11/10/2020 | 21:26 | 21:32 | 0.1 | 4182 | 4200 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 4500 | 4300 | 200 | 131 | 152 | 148 | 144
11/10/2020 | 21:32 | 21:36 | 0.066667 | 4200 | 4273 | 73 | Rotate |  | 4202 | 8.5 | 265.5 | 4147.96 | -72.63 | -602.14 | -72.63 | 2.04 |  |  | 42 | 80 | 900 | 11000 | 1095 | 4800 | 4300 | 500 | 131 | 152 | 148 | 144
11/10/2020 | 21:39 | 21:40 | 0.016667 | 4273 | 4275 | 2 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 11000; Drilling Parameters ROP: 120 | 4800 | 4300 | 500 | 158 | 152 | 148 | 144
11/10/2020 | 21:40 | 21:46 | 0.1 | 4275 | 4293 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 25; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 4500 | 4300 | 200 | 158 | 170 | 160 | 155
11/10/2020 | 21:46 | 21:53 | 0.11667 | 4293 | 4367 | 74 | Rotate |  | 4296 | 6.5 | 273.8 | 4241.15 | -72.82 | -614.38 | -72.82 | 2.41 |  |  | 42 | 80 | 900 | 11000 | 634.29 | 4800 | 4300 | 500 | 158 | 152 | 148 | 144
11/10/2020 | 21:56 | 22:03 | 0.11667 | 4367 | 4460 | 93 | Rotate |  | 4389 | 6.6 | 276.2 | 4333.55 | -71.9 | -624.94 | -71.9 | 0.31 |  |  | 42 | 80 | 900 | 12500 | 797.14 | 4800 | 4300 | 500 | 158 | 170 | 160 | 155
11/10/2020 | 22:06 | 22:07 | 0.016667 | 4460 | 4462 | 2 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 120 | 4800 | 4300 | 500 | 158 | 170 | 160 | 155
11/10/2020 | 22:07 | 22:13 | 0.1 | 4462 | 4480 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 180 | 4500 | 4300 | 200 | 162 | 170 | 160 | 155
11/10/2020 | 22:13 | 22:17 | 0.066667 | 4480 | 4554 | 74 | Rotate |  | 4483 | 4.3 | 275.5 | 4427.12 | -70.98 | -633.82 | -70.98 | 2.45 |  |  | 42 | 80 | 900 | 12500 | 1110 | 4800 | 4300 | 500 | 162 | 170 | 160 | 155
11/10/2020 | 22:20 | 22:21 | 0.016667 | 4554 | 4558 | 4 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 240 | 4800 | 4300 | 500 | 162 | 170 | 160 | 155
11/10/2020 | 22:21 | 22:28 | 0.11667 | 4558 | 4576 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 154.29 | 4500 | 4300 | 200 | 162 | 170 | 160 | 155
11/10/2020 | 22:28 | 22:34 | 0.1 | 4576 | 4648 | 72 | Rotate |  | 4577 | 1.6 | 276.3 | 4520.98 | -70.49 | -638.64 | -70.49 | 2.87 |  |  | 42 | 80 | 900 | 12500 | 720 | 5000 | 4300 | 700 | 162 | 170 | 160 | 155
11/10/2020 | 22:37 | 22:38 | 0.016667 | 4648 | 4652 | 4 | Rotate | Drilling Parameters WOB: 42; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 240 | 5000 | 4300 | 700 | 162 | 170 | 160 | 155
11/10/2020 | 22:38 | 22:43 | 0.083333 | 4652 | 4668 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 15; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 192 | 4500 | 4300 | 200 | 162 | 170 | 160 | 155
11/10/2020 | 22:43 | 22:52 | 0.15 | 4668 | 4743 | 75 | Rotate |  | 4672 | 0.7 | 20.5 | 4615.97 | -69.8 | -639.75 | -69.8 | 2 |  |  | 45 | 80 | 900 | 12500 | 500 | 5000 | 4300 | 700 | 162 | 170 | 160 | 155
11/10/2020 | 22:55 | 23:04 | 0.15 | 4743 | 4837 | 94 | Rotate |  | 4766 | 1.5 | 41.7 | 4709.95 | -68.35 | -638.73 | -68.35 | 0.94 |  |  | 45 | 80 | 900 | 12500 | 626.67 | 5000 | 4300 | 700 | 171 | 170 | 160 | 155
11/10/2020 | 23:07 | 23:18 | 0.18333 | 4837 | 4932 | 95 | Rotate |  | 4861 | 1.5 | 22.8 | 4804.92 | -66.27 | -637.42 | -66.27 | 0.52 |  |  | 45 | 80 | 900 | 12500 | 518.18 | 5000 | 4300 | 700 | 171 | 170 | 160 | 155
11/10/2020 | 23:22 | 23:23 | 0.016667 | 4932 | 4940 | 8 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 12500; Drilling Parameters ROP: 480 | 5000 | 4300 | 700 | 171 | 180 | 172 | 165
11/10/2020 | 23:23 | 23:31 | 0.13333 | 4940 | 4956 | 16 | Slide | 0 | 4954 | 0.7 | 267.7 | 4897.91 | -65.17 | -637.52 | -65.17 | 2.05 |  |  | 15 |  | 900 |  | 120 | 5000 | 4300 | 700 | 178 | 180 | 172 | 165
11/10/2020 | 23:31 | 23:40 | 0.15 | 4956 | 5025 | 69 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 460 | 5000 | 4300 | 700 | 178 | 180 | 172 | 165
11/10/2020 | 23:44 | 23:53 | 0.15 | 5025 | 5119 | 94 | Rotate |  | 5048 | 1.3 | 234.7 | 4991.89 | -65.81 | -638.96 | -65.81 | 0.86 |  |  | 45 | 80 | 900 | 13000 | 626.67 | 5000 | 4300 | 700 | 178 | 180 | 172 | 165
11/11/2020 | 00:00 | 00:09 | 0.15 | 5119 | 5213 | 94 | Rotate |  | 5142 | 1.3 | 222.2 | 5085.87 | -67.22 | -640.55 | -67.22 | 0.3 |  |  | 45 | 80 | 900 | 13000 | 626.67 | 5000 | 4300 | 700 | 178 | 180 | 172 | 165
11/11/2020 | 00:13 | 00:21 | 0.13333 | 5213 | 5307 | 94 | Rotate |  | 5236 | 1.2 | 249.1 | 5179.85 | -68.36 | -642.19 | -68.36 | 0.63 |  |  | 45 | 80 | 900 | 13000 | 705 | 5200 | 4600 | 600 | 178 | 180 | 172 | 165
11/11/2020 | 00:25 | 00:34 | 0.15 | 5307 | 5400 | 93 | Rotate |  | 5329 | 1.4 | 245.8 | 5272.82 | -69.17 | -644.13 | -69.17 | 0.23 |  |  | 45 | 80 | 900 | 13000 | 620 | 5200 | 4600 | 600 | 178 | 180 | 172 | 165
11/11/2020 | 00:38 | 00:47 | 0.15 | 5400 | 5494 | 94 | Rotate |  | 5423 | 1.7 | 242 | 5366.79 | -70.3 | -646.41 | -70.3 | 0.34 |  |  | 45 | 80 | 900 | 13000 | 626.67 | 5200 | 4600 | 600 | 178 | 180 | 172 | 165
11/11/2020 | 00:52 | 00:53 | 0.016667 | 5494 | 5503 | 9 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 13000; Drilling Parameters ROP: 540 | 5200 | 4600 | 600 | 178 | 180 | 172 | 165
11/11/2020 | 00:53 | 01:02 | 0.15 | 5503 | 5517 | 14 | Slide | TTF: 0; Drilling Parameters WOB: 18; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 93.33 | 4800 | 4600 | 200 | 178 | 180 | 172 | 165
11/11/2020 | 01:02 | 01:15 | 0.21667 | 5517 | 5589 | 72 | Rotate |  | 5518 | 0.8 | 246.3 | 5461.77 | -71.23 | -648.26 | -71.23 | 0.95 |  |  | 45 | 80 | 900 | 13000 | 332.31 | 5200 | 4600 | 600 | 178 | 180 | 172 | 165
11/11/2020 | 01:19 | 01:28 | 0.15 | 5589 | 5682 | 93 | Rotate |  | 5611 | 0.4 | 246.8 | 5554.76 | -71.62 | -649.15 | -71.62 | 0.43 |  |  | 45 | 80 | 900 | 15000 | 620 | 5200 | 4600 | 600 | 182 | 200 | 190 | 180
11/11/2020 | 01:31 | 01:44 | 0.21667 | 5682 | 5776 | 94 | Rotate |  | 5705 | 0.5 | 261 | 5648.76 | -71.81 | -649.86 | -71.81 | 0.16 |  |  | 45 | 80 | 900 | 15000 | 433.85 | 5200 | 4600 | 600 | 182 | 200 | 190 | 180
11/11/2020 | 01:48 | 01:58 | 0.16667 | 5776 | 5871 | 95 | Rotate |  | 5800 | 0.7 | 268.2 | 5743.75 | -71.89 | -650.85 | -71.89 | 0.22 |  |  | 45 | 80 | 900 | 15000 | 570 | 5200 | 4600 | 600 | 182 | 200 | 190 | 180
11/11/2020 | 02:01 | 02:12 | 0.18333 | 5871 | 5965 | 94 | Rotate |  | 5894 | 0.9 | 288.2 | 5837.74 | -71.68 | -652.13 | -71.68 | 0.36 |  |  | 45 | 80 | 900 | 15000 | 512.73 | 5200 | 4600 | 600 | 182 | 200 | 190 | 180
11/11/2020 | 02:16 | 02:18 | 0.033333 | 5965 | 5972 | 7 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 210 | 5200 | 4600 | 600 | 182 | 200 | 190 | 180
11/11/2020 | 02:18 | 02:25 | 0.11667 | 5972 | 5988 | 16 | Slide | 0 | 5988 | 0.6 | 64.1 | 5931.74 | -71.23 | -652.38 | -71.23 | 1.48 |  |  | 20 |  | 900 |  | 137.14 | 4800 | 4600 | 200 | 182 | 200 | 190 | 180
11/11/2020 | 02:25 | 02:35 | 0.16667 | 5988 | 6059 | 71 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 15000; Drilling Parameters ROP: 426 | 5200 | 4600 | 600 | 182 | 200 | 190 | 180
11/11/2020 | 02:39 | 02:51 | 0.2 | 6059 | 6154 | 95 | Rotate |  | 6083 | 0.8 | 101.4 | 6026.73 | -71.15 | -651.29 | -71.15 | 0.51 |  |  | 45 | 80 | 900 | 18000 | 475 | 5400 | 4600 | 800 | 187 | 200 | 190 | 180
11/11/2020 | 02:55 | 03:07 | 0.2 | 6154 | 6247 | 93 | Rotate |  | 6176 | 1.2 | 105.3 | 6119.72 | -71.53 | -649.71 | -71.53 | 0.44 |  |  | 45 | 80 | 900 | 18000 | 465 | 5400 | 4600 | 800 | 187 | 200 | 190 | 180
11/11/2020 | 03:10 | 03:20 | 0.16667 | 6247 | 6342 | 95 | Rotate |  | 6271 | 0.6 | 102.4 | 6214.71 | -71.9 | -648.27 | -71.9 | 0.63 |  |  | 45 | 80 | 900 | 18000 | 570 | 5400 | 4600 | 800 | 187 | 200 | 190 | 180
11/11/2020 | 03:24 | 03:35 | 0.18333 | 6342 | 6435 | 93 | Rotate |  | 6364 | 1 | 125.7 | 6307.7 | -72.48 | -647.13 | -72.48 | 0.55 |  |  | 40 | 80 | 900 | 18000 | 507.27 | 5400 | 4600 | 800 | 199 | 200 | 190 | 180
11/11/2020 | 03:39 | 03:51 | 0.2 | 6435 | 6530 | 95 | Rotate |  | 6459 | 0.7 | 142.7 | 6402.69 | -73.43 | -646.11 | -73.43 | 0.41 |  |  | 40 | 80 | 900 | 18000 | 475 | 5400 | 4600 | 800 | 199 | 200 | 190 | 180
11/11/2020 | 03:54 | 04:05 | 0.18333 | 6530 | 6624 | 94 | Rotate |  | 6553 | 0.6 | 94.5 | 6496.68 | -73.92 | -645.27 | -73.92 | 0.57 |  |  | 40 | 80 | 900 | 18000 | 512.73 | 5400 | 4600 | 800 | 199 | 200 | 190 | 180
11/11/2020 | 04:10 | 04:21 | 0.18333 | 6624 | 6718 | 94 | Rotate |  | 6647 | 0.6 | 88.7 | 6590.68 | -73.95 | -644.28 | -73.95 | 0.06 |  |  | 38 | 80 | 900 | 18000 | 512.73 | 5400 | 4600 | 800 | 207 | 210 | 200 | 190
11/11/2020 | 04:25 | 04:36 | 0.18333 | 6718 | 6812 | 94 | Rotate |  | 6741 | 0.2 | 161.6 | 6684.67 | -74.09 | -643.74 | -74.09 | 0.61 |  |  | 38 | 80 | 900 | 18000 | 512.73 | 5400 | 4600 | 800 | 207 | 210 | 200 | 190
11/11/2020 | 04:40 | 04:51 | 0.18333 | 6812 | 6906 | 94 | Rotate |  | 6835 | 0.3 | 27.6 | 6778.67 | -74.03 | -643.58 | -74.03 | 0.49 |  |  | 38 | 80 | 900 | 18000 | 512.73 | 5400 | 4600 | 800 | 207 | 210 | 200 | 190
11/11/2020 | 04:54 | 05:07 | 0.21667 | 6906 | 7000 | 94 | Rotate |  | 6929 | 0.5 | 61.1 | 6872.67 | -73.61 | -643.1 | -73.61 | 0.32 |  |  | 35 | 80 | 900 | 18000 | 433.85 | 5600 | 4700 | 900 | 208 | 220 | 210 | 200
11/11/2020 | 05:09 | 05:21 | 0.2 | 7000 | 7094 | 94 | Rotate |  | 7023 | 0.4 | 53.1 | 6966.67 | -73.22 | -642.48 | -73.22 | 0.13 |  |  | 35 | 80 | 900 | 18000 | 470 | 5600 | 4700 | 900 | 208 | 220 | 210 | 200
11/11/2020 | 05:24 | 05:44 | 0.33333 | 7094 | 7189 | 95 | Rotate |  | 7118 | 0.5 | 10 | 7061.67 | -72.61 | -642.14 | -72.61 | 0.36 |  |  | 35 | 80 | 900 | 18000 | 285 | 5600 | 4700 | 900 | 210 | 220 | 210 | 200
11/11/2020 | 05:49 | 06:06 | 0.28333 | 7189 | 7283 | 94 | Rotate |  | 7212 | 0.1 | 356.8 | 7155.67 | -72.13 | -642.08 | -72.13 | 0.43 |  |  | 35 | 80 | 900 | 18000 | 331.76 | 5600 | 4700 | 900 | 212 | 220 | 210 | 200
11/11/2020 | 06:17 | 06:25 | 0.13333 | 7283 | 7303 | 20 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 150 | 5600 | 4700 | 900 | 218 | 220 | 210 | 200
11/11/2020 | 06:33 | 06:45 | 0.2 | 7303 | 7376 | 73 | Rotate |  | 7305 | 0.5 | 306 | 7248.66 | -71.81 | -642.41 | -71.81 | 0.48 |  |  | 35 | 80 | 900 | 18000 | 365 | 5600 | 4700 | 900 | 218 | 220 | 210 | 200
11/11/2020 | 06:50 | 07:15 | 0.41667 | 7376 | 7470 | 94 | Rotate |  | 7399 | 0.5 | 334.2 | 7342.66 | -71.2 | -642.92 | -71.2 | 0.26 |  |  | 35 | 80 | 900 | 18000 | 225.6 | 5600 | 4700 | 900 | 218 | 220 | 210 | 200
11/11/2020 | 07:20 | 08:10 | 0.83333 | 7470 | 7658 | 188 | Rotate |  | 7493 | 0.7 | 331.5 | 7436.66 | -70.32 | -643.37 | -70.32 | 0.21 |  |  | 35 | 80 | 900 | 18000 | 225.6 | 5600 | 4700 | 900 | 218 | 220 | 210 | 200
11/11/2020 | 08:15 | 08:30 | 0.25 | 7658 | 7752 | 94 | Rotate |  | 7681 | 1.3 | 290.3 | 7624.62 | -68.36 | -646.09 | -68.36 | 0.43 |  |  | 35 | 80 | 900 | 18000 | 376 | 5600 | 4700 | 900 | 219 | 220 | 210 | 200
11/11/2020 | 08:35 | 08:50 | 0.25 | 7752 | 7763 | 11 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 44 | 5600 | 4700 | 900 | 219 | 220 | 210 | 200
11/11/2020 | 08:50 | 09:21 | 0.51667 | 7763 | 7844 | 81 | Rotate |  | 7775 | 1.1 | 332 | 7718.6 | -67.19 | -647.51 | -67.19 | 0.93 |  |  | 35 | 80 | 900 | 18000 | 156.77 | 5600 | 4700 | 900 | 219 | 220 | 210 | 200
11/11/2020 | 09:26 | 09:58 | 0.53333 | 7844 | 7866 | 22 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 41.25 | 5600 | 4700 | 900 | 219 | 220 | 210 | 200
11/11/2020 | 09:58 | 10:28 | 0.5 | 7866 | 7940 | 74 | Rotate |  | 7869 | 0.2 | 187.6 | 7812.6 | -66.56 | -647.96 | -66.56 | 1.35 |  |  | 35 | 80 | 900 | 18000 | 148 | 5600 | 4700 | 900 | 219 | 250 | 210 | 210
11/11/2020 | 10:33 | 10:36 | 0.05 | 7940 | 7945 | 5 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 100 | 5600 | 4700 | 900 | 220 | 250 | 210 | 210
11/11/2020 | 10:36 | 10:54 | 0.3 | 7945 | 7962 | 17 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 56.67 | 5600 | 4700 | 900 | 220 | 250 | 210 | 210
11/11/2020 | 10:54 | 11:10 | 0.26667 | 7962 | 8034 | 72 | Rotate |  | 7963 | 0.9 | 205.4 | 7906.59 | -67.39 | -648.29 | -67.39 | 0.76 |  |  | 35 | 80 | 900 | 18000 | 270 | 5600 | 4700 | 900 | 222 | 250 | 210 | 210
11/11/2020 | 11:19 | 11:52 | 0.55 | 8034 | 8059 | 25 | Slide | 0 | 8058 | 2.2 | 173.2 | 8001.56 | -69.87 | -648.4 | -69.87 | 1.6 |  |  | 35 |  | 900 |  | 45.45 | 5600 | 4700 | 900 | 222 | 250 | 210 | 210
11/11/2020 | 11:52 | 12:08 | 0.26667 | 8059 | 8129 | 70 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 262.5 | 5600 | 4700 | 900 | 224 | 250 | 210 | 210
11/11/2020 | 12:12 | 12:42 | 0.5 | 8129 | 8316 | 187 | Rotate |  | 8151 | 2.8 | 162.7 | 8094.47 | -73.81 | -647.51 | -73.81 | 0.81 |  |  | 35 | 80 | 900 | 18000 | 374 | 5600 | 4700 | 900 | 224 | 250 | 210 | 210
11/11/2020 | 12:47 | 13:03 | 0.26667 | 8316 | 8410 | 94 | Rotate |  | 8339 | 1.6 | 186.3 | 8282.33 | -80.9 | -646.58 | -80.9 | 0.77 |  |  | 35 | 80 | 900 | 18000 | 352.5 | 5600 | 4700 | 900 | 226 | 250 | 210 | 210
11/11/2020 | 13:08 | 13:11 | 0.05 | 8410 | 8412 | 2 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 40 | 5600 | 4700 | 900 | 227 | 250 | 230 | 210
11/11/2020 | 13:11 | 13:29 | 0.3 | 8412 | 8428 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 53.33 | 5600 | 4700 | 900 | 228 | 250 | 230 | 210
11/11/2020 | 13:29 | 13:45 | 0.26667 | 8428 | 8505 | 77 | Rotate |  | 8434 | 0.4 | 216.2 | 8377.31 | -82.48 | -646.92 | -82.48 | 1.34 |  |  | 35 | 80 | 900 | 18000 | 288.75 | 5600 | 4700 | 900 | 229 | 250 | 230 | 210
11/11/2020 | 13:50 | 14:03 | 0.21667 | 8505 | 8599 | 94 | Rotate |  | 8528 | 0.5 | 286.1 | 8471.31 | -82.63 | -647.51 | -82.63 | 0.56 |  |  | 35 | 80 | 900 | 18000 | 433.85 | 5600 | 4700 | 900 | 230 | 250 | 230 | 210
11/11/2020 | 14:08 | 14:23 | 0.25 | 8599 | 8695 | 96 | Rotate |  | 8622 | 1.1 | 267.5 | 8565.3 | -82.56 | -648.8 | -82.56 | 0.69 |  |  | 35 | 80 | 900 | 18000 | 384 | 5600 | 4700 | 900 | 232 | 250 | 230 | 210
11/11/2020 | 14:28 | 14:33 | 0.083333 | 8695 | 8704 | 9 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 108 | 5600 | 4700 | 900 | 232 | 250 | 230 | 210
11/11/2020 | 14:33 | 15:00 | 0.45 | 8704 | 8729 | 25 | Slide | 0 | 8716 | 0.7 | 4 | 8659.29 | -82.03 | -649.66 | -82.03 | 1.46 |  |  | 35 |  | 900 |  | 55.56 | 5600 | 4700 | 900 | 234 | 250 | 230 | 210
11/11/2020 | 15:00 | 15:16 | 0.26667 | 8729 | 8787 | 58 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 217.5 | 5600 | 4700 | 900 | 235 | 250 | 230 | 210
11/11/2020 | 15:21 | 15:38 | 0.28333 | 8787 | 8881 | 94 | Rotate |  | 8810 | 1.4 | 25.4 | 8753.28 | -80.42 | -649.13 | -80.42 | 0.84 |  |  | 35 | 80 | 900 | 18000 | 331.76 | 5600 | 4700 | 900 | 235 | 250 | 230 | 210
11/11/2020 | 15:42 | 15:55 | 0.21667 | 8881 | 8974 | 93 | Rotate |  | 8903 | 1.4 | 14.7 | 8846.25 | -78.29 | -648.35 | -78.29 | 0.28 |  |  | 35 | 80 | 900 | 18000 | 429.23 | 5600 | 4700 | 900 | 235 | 250 | 230 | 210
11/11/2020 | 16:00 | 16:15 | 0.25 | 8974 | 9068 | 94 | Rotate |  | 8997 | 1.8 | 16.8 | 8940.21 | -75.77 | -647.64 | -75.77 | 0.43 |  |  | 35 | 80 | 900 | 18000 | 376 | 5600 | 4700 | 900 | 236 | 250 | 230 | 210
11/11/2020 | 16:20 | 16:33 | 0.21667 | 9068 | 9161 | 93 | Rotate |  | 9090 | 1.6 | 1.3 | 9033.17 | -73.07 | -647.18 | -73.07 | 0.54 |  |  | 35 | 80 | 900 | 18000 | 429.23 | 5600 | 4700 | 900 | 236 | 250 | 230 | 210
11/11/2020 | 16:40 | 16:55 | 0.25 | 9161 | 9179 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 35; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 72 | 5600 | 4700 | 900 | 238 | 250 | 230 | 210
11/11/2020 | 16:55 | 17:14 | 0.31667 | 9179 | 9255 | 76 | Rotate |  | 9184 | 0.5 | 316.1 | 9127.16 | -71.46 | -647.44 | -71.46 | 1.38 |  |  | 35 | 80 | 900 | 18000 | 240 | 5600 | 4700 | 900 | 238 | 250 | 230 | 210
11/11/2020 | 17:58 | 18:10 | 0.2 | 9255 | 9349 | 94 | Rotate |  | 9278 | 1.3 | 252.2 | 9221.15 | -71.49 | -648.74 | -71.49 | 1.24 |  |  | 45 | 80 | 900 | 20000 | 470 | 5600 | 4700 | 900 | 238 | 250 | 230 | 210
11/11/2020 | 18:14 | 18:26 | 0.2 | 9349 | 9442 | 93 | Rotate |  | 9371 | 1.2 | 221.4 | 9314.13 | -72.55 | -650.39 | -72.55 | 0.72 |  |  | 45 | 80 | 900 | 20000 | 465 | 5800 | 5000 | 800 | 238 | 250 | 230 | 210
11/11/2020 | 18:30 | 18:45 | 0.25 | 9442 | 9536 | 94 | Rotate |  | 9465 | 0.7 | 222.3 | 9408.11 | -73.71 | -651.42 | -73.71 | 0.53 |  |  | 42 | 80 | 900 | 20000 | 376 | 5800 | 5000 | 800 | 238 | 250 | 230 | 210
11/11/2020 | 18:48 | 19:02 | 0.23333 | 9536 | 9630 | 94 | Rotate |  | 9559 | 0.4 | 229.7 | 9502.11 | -74.35 | -652.06 | -74.35 | 0.33 |  |  | 42 | 80 | 900 | 20000 | 402.86 | 5800 | 5000 | 800 | 238 | 250 | 230 | 210
11/11/2020 | 19:06 | 19:21 | 0.25 | 9630 | 9723 | 93 | Rotate |  | 9652 | 0.7 | 255.8 | 9595.1 | -74.7 | -652.86 | -74.7 | 0.41 |  |  | 42 | 80 | 900 | 20000 | 372 | 5800 | 5000 | 800 | 238 | 250 | 230 | 210
11/11/2020 | 19:25 | 19:45 | 0.33333 | 9723 | 9817 | 94 | Rotate |  | 9746 | 0.4 | 130.6 | 9689.1 | -75.05 | -653.17 | -75.05 | 1.05 |  |  | 42 | 80 | 900 | 20000 | 282 | 5800 | 5000 | 800 | 238 | 250 | 230 | 210
11/11/2020 | 19:49 | 20:13 | 0.4 | 9817 | 9911 | 94 | Rotate |  | 9840 | 0.4 | 164.4 | 9783.1 | -75.58 | -652.83 | -75.58 | 0.25 |  |  | 42 | 80 | 900 | 20000 | 235 | 5800 | 5000 | 800 | 257 | 250 | 230 | 210
11/11/2020 | 20:17 | 20:38 | 0.35 | 9911 | 10005 | 94 | Rotate |  | 9934 | 0.2 | 156 | 9877.1 | -76.05 | -652.67 | -76.05 | 0.22 |  |  | 42 | 80 | 900 | 20000 | 268.57 | 5800 | 5000 | 800 | 257 | 250 | 230 | 210
11/11/2020 | 20:41 | 21:00 | 0.31667 | 10005 | 10099 | 94 | Rotate |  | 10028 | 0.6 | 293.6 | 9971.1 | -76 | -653.06 | -76 | 0.81 |  |  | 38 | 80 | 900 | 20000 | 296.84 | 5800 | 5000 | 800 | 257 | 250 | 230 | 210
11/11/2020 | 21:04 | 21:08 | 0.066667 | 10099 | 10118 | 19 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 285 | 5800 | 5000 | 800 | 257 | 250 | 230 | 210
11/11/2020 | 21:08 | 22:10 | 1.0333 | 10118 | 10178 | 60 | Slide | 0 | 10122 | 1.5 | 312.5 | 10065.08 | -74.97 | -654.42 | -74.97 | 1.01 |  |  | 25 |  | 900 |  | 58.06 | 5400 | 5000 | 400 | 257 | 250 | 230 | 210
11/11/2020 | 22:10 | 22:20 | 0.16667 | 10178 | 10193 | 15 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 900; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 90 | 5500 | 5000 | 500 | 257 | 250 | 230 | 210
11/11/2020 | 22:24 | 22:32 | 0.13333 | 10193 | 10215 | 22 | Rotate |  | 10215 | 6.7 | 309.8 | 10157.81 | -70.67 | -659.49 | -70.67 | 5.59 |  |  | 38 | 40 | 900 | 18000 | 165 | 5600 | 5000 | 600 | 257 | 280 | 270 | 260
11/11/2020 | 22:32 | 23:24 | 0.86667 | 10215 | 10259 | 44 | Slide | TTF: 0; Drilling Parameters WOB: 28; Drilling Parameters FLOW: 900; Drilling Parameters ROP: 50.77 | 5300 | 5000 | 300 | 255 | 280 | 270 | 260
11/11/2020 | 23:45 | 23:54 | 0.15 | 10259 | 10286 | 27 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 660; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 180 | 4000 | 3200 | 800 | 255 | 310 | 280 | 260
11/12/2020 | 00:00 | 00:05 | 0.083333 | 10286 | 10308 | 22 | Rotate |  | 10308 | 9.2 | 317.5 | 10249.91 | -61.72 | -668.68 | -61.72 | 2.92 |  |  | 32 | 40 | 660 | 19000 | 264 | 4000 | 3200 | 800 | 255 | 310 | 280 | 260
11/12/2020 | 00:05 | 00:35 | 0.5 | 10308 | 10336 | 28 | Slide | TTF: 0; Drilling Parameters WOB: 30; Drilling Parameters FLOW: 660; Drilling Parameters ROP: 56 | 3500 | 3200 | 300 | 255 | 310 | 280 | 260
11/12/2020 | 00:35 | 00:47 | 0.2 | 10336 | 10379 | 43 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 660; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 215 | 4000 | 3200 | 800 | 255 | 310 | 280 | 260
11/12/2020 | 00:53 | 00:58 | 0.083333 | 10379 | 10385 | 6 | Rotate | Drilling Parameters WOB: 32; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 660; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 72 | 4000 | 3200 | 800 | 255 | 310 | 280 | 260
11/12/2020 | 00:58 | 01:44 | 0.76667 | 10385 | 10440 | 55 | Slide | 0 | 10402 | 13.3 | 315.1 | 10342.09 | -48.51 | -681.39 | -48.51 | 4.39 |  |  | 26 |  | 660 |  | 71.74 | 3500 | 3200 | 300 | 248 | 310 | 280 | 260
11/12/2020 | 01:44 | 02:01 | 0.28333 | 10440 | 10475 | 35 | Rotate |  | 10457 | 15.8 | 315.3 | 10395.32 | -38.71 | -691.13 | -38.71 | 4.55 |  |  | 32 | 40 | 660 | 19000 | 123.53 | 4000 | 3200 | 800 | 248 | 310 | 280 | 260
11/12/2020 | 02:05 | 02:37 | 0.53333 | 10475 | 10512 | 37 | Rotate | Drilling Parameters WOB: 45; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 660; Drilling Parameters Tq: 20000; Drilling Parameters ROP: 69.38 | 4000 | 3200 | 800 | 248 | 310 | 280 | 260
11/12/2020 | 02:37 | 03:10 | 0.55 | 10512 | 10528 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 48; Drilling Parameters FLOW: 660; Drilling Parameters ROP: 29.09 | 3400 | 3200 | 200 | 242 | 310 | 280 | 260

## BHA_3_Curve_and_Lateral_Slide_S
Slide Report
Operator: |  |  |  |  | Magnolia Oil & Gas |  |  | BHA Description: |  |  |  |  | BHA #3 (Curve and Lateral) |  |  |  |  | RKB: |  |  |  | 418 |  | North Reference: |  | GRID |  | Total Drilled: |  | 8136
Site: |  |  |  |  | Yukon - Washington County, TX |  |  | BHA / Bit Type: |  |  |  |  | Motor / PDC |  |  |  |  | Units: |  |  |  | Us Feet |  | Declination: |  | 0 |  | Slide: |  | 855
Well Name: |  |  |  |  | Yukon A 1H |  |  | Survey / Gamma Offset: |  |  |  |  | 69.00 / 59.00 |  |  |  |  | Grid Conv: |  |  |  | 418 |  | VS Azimuth: |  | 313.12 |  | Rotate: |  | 7281
[9 empty] | Survey Data | [8 empty] | Drilling Parameters | [8 empty] | Weights |  |  |  | Comments
Date | Start Time | End Time | Hrs | Start Depth | End Depth | CL | Operation | TTF | MD | INC | AZI | TVD | NS | EW | VS | DLS | UD | LR | WOB | RPM | FLOW | Tq | ROP | On Btm Press | Off Btm Press | Diff | Temp | PU | ROT | SO | Comments
11/15/2020 | 02:30 | 02:35 | 0.083333 | 10528 | 10538 | 10 | Rotate | Drilling Parameters WOB: 15; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 230; Drilling Parameters Tq: 6000; Drilling Parameters ROP: 120 | 1900 | 1650 | 250 | 242 | 230 | 220 | 200
11/15/2020 | 03:35 | 04:25 | 0.83333 | 10538 | 10598 | 60 | Slide | 0 | 10548 | 16.8 | 315.4 | 10482.66 | -20.54 | -709.08 | -20.54 | 1.1 |  |  | 32 |  | 350 |  | 72 | 3800 | 3200 | 600 | 242 | 230 | 220 | 200
11/15/2020 | 04:25 | 04:30 | 0.083333 | 10598 | 10617 | 19 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 228 | 4000 | 3200 | 800 | 242 | 230 | 220 | 200
11/15/2020 | 04:40 | 04:45 | 0.083333 | 10617 | 10620 | 3 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 36 | 4000 | 3200 | 800 | 246 | 230 | 220 | 200
11/15/2020 | 04:45 | 05:45 | 1 | 10620 | 10685 | 65 | Slide | 0 | 10643 | 26.2 | 315.5 | 10570.95 | 4.25 | -733.47 | 4.25 | 9.89 |  |  | 28 |  | 350 |  | 65 | 3800 | 3200 | 600 | 246 | 230 | 220 | 200
11/15/2020 | 05:45 | 06:00 | 0.25 | 10685 | 10712 | 27 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 108 | 4000 | 3200 | 800 | 246 | 230 | 220 | 200
11/15/2020 | 06:10 | 06:18 | 0.13333 | 10712 | 10732 | 20 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 350; Drilling Parameters Tq: 8000; Drilling Parameters ROP: 150 | 4000 | 3200 | 800 | 246 | 230 | 220 | 200
11/15/2020 | 06:18 | 07:11 | 0.88333 | 10732 | 10807 | 75 | Slide | 0 | 10738 | 31.2 | 315 | 10654.25 | 36.63 | -765.59 | 36.63 | 5.27 |  |  | 28 |  | 400 |  | 84.91 | 4100 | 3650 | 450 | 246 | 255 | 220 | 195
11/15/2020 | 07:20 | 08:17 | 0.95 | 10807 | 10890 | 83 | Slide | 0 | 10833 | 46.4 | 316.2 | 10728.07 | 79.11 | -807.04 | 79.11 | 16.02 |  |  | 28 |  | 400 |  | 87.37 | 4100 | 3650 | 450 | 246 | 255 | 220 | 195
11/15/2020 | 08:17 | 08:24 | 0.11667 | 10890 | 10902 | 12 | Rotate | Drilling Parameters WOB: 28; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 102.86 | 4600 | 3650 | 950 | 246 | 255 | 220 | 195
11/15/2020 | 08:34 | 08:45 | 0.18333 | 10902 | 10957 | 55 | Rotate |  | 10927 | 56 | 316.1 | 10786.91 | 131.87 | -857.73 | 131.87 | 10.21 |  |  | 28 | 40 | 400 | 12000 | 300 | 4600 | 3650 | 950 | 246 | 255 | 220 | 195
11/15/2020 | 08:45 | 09:26 | 0.68333 | 10957 | 10996 | 39 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 57.07 | 4100 | 3650 | 450 | 246 | 255 | 220 | 195
11/15/2020 | 09:36 | 09:58 | 0.36667 | 10996 | 11056 | 60 | Rotate |  | 11022 | 63 | 313.6 | 10835.1 | 189.51 | -915.77 | 189.51 | 7.71 |  |  | 28 | 40 | 400 | 12000 | 163.64 | 4600 | 3650 | 950 | 246 | 255 | 220 | 195
11/15/2020 | 09:58 | 10:20 | 0.36667 | 11056 | 11091 | 35 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 95.45 | 4100 | 3650 | 450 | 246 | 255 | 220 | 195
11/15/2020 | 10:35 | 10:57 | 0.36667 | 11091 | 11158 | 67 | Rotate |  | 11117 | 65.2 | 312 | 10876.59 | 247.56 | -978.47 | 247.56 | 2.77 |  |  | 30 | 40 | 400 | 12000 | 182.73 | 4650 | 3650 | 1000 | 260 | 255 | 220 | 195
11/15/2020 | 10:57 | 11:24 | 0.45 | 11158 | 11186 | 28 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 62.22 | 4100 | 3650 | 450 | 260 | 255 | 220 | 195
11/15/2020 | 11:34 | 11:48 | 0.23333 | 11186 | 11233 | 47 | Rotate |  | 11212 | 67.8 | 312.4 | 10914.47 | 306.08 | -1043 | 306.08 | 2.76 |  |  | 30 | 40 | 400 | 12000 | 201.43 | 4650 | 3650 | 1000 | 260 | 255 | 220 | 195
11/15/2020 | 11:48 | 12:20 | 0.53333 | 11233 | 11281 | 48 | Slide | TTF: 0; Drilling Parameters WOB: 32; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 90 | 4100 | 3650 | 450 | 260 | 255 | 220 | 195
11/15/2020 | 12:30 | 13:32 | 1.0333 | 11281 | 11377 | 96 | Slide | 0 | 11308 | 81.2 | 314.8 | 10940.07 | 369.77 | -1109.79 | 369.77 | 14.16 |  |  | 32 |  | 400 |  | 92.9 | 4100 | 3650 | 450 | 260 | 255 | 220 | 195
11/15/2020 | 13:42 | 14:10 | 0.46667 | 11377 | 11472 | 95 | Rotate |  | 11403 | 96 | 315.3 | 10942.39 | 436.8 | -1176.7 | 436.8 | 15.59 |  |  | 30 | 40 | 400 | 12000 | 203.57 | 4650 | 3650 | 1000 | 268 | 255 | 220 | 195
11/15/2020 | 14:20 | 14:53 | 0.55 | 11472 | 11517 | 45 | Slide | 0 | 11498 | 93 | 313.9 | 10934.93 | 503.29 | -1244.13 | 503.29 | 3.48 |  |  | 32 |  | 400 |  | 81.82 | 4100 | 3650 | 450 | 268 | 255 | 220 | 195
11/15/2020 | 14:53 | 15:08 | 0.25 | 11517 | 11567 | 50 | Rotate | Drilling Parameters WOB: 30; Drilling Parameters RPM: 40; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 200 | 4650 | 3650 | 1000 | 268 | 255 | 220 | 195
11/15/2020 | 15:18 | 15:39 | 0.35 | 11567 | 11661 | 94 | Rotate |  | 11592 | 89.8 | 311.6 | 10932.64 | 567.06 | -1313.12 | 567.06 | 4.19 |  |  | 35 | 70 | 400 | 12000 | 268.57 | 4650 | 3650 | 1000 | 268 | 255 | 220 | 195
11/15/2020 | 15:50 | 16:04 | 0.23333 | 11661 | 11756 | 95 | Rotate |  | 11687 | 90.6 | 311.7 | 10932.3 | 630.19 | -1384.11 | 630.19 | 0.85 |  |  | 35 | 70 | 400 | 12000 | 407.14 | 4650 | 3650 | 1000 | 278 | 255 | 220 | 195
11/15/2020 | 16:14 | 16:31 | 0.28333 | 11756 | 11850 | 94 | Rotate |  | 11781 | 90.1 | 312.2 | 10931.73 | 693.03 | -1454.02 | 693.03 | 0.75 |  |  | 35 | 80 | 400 | 12000 | 331.76 | 4650 | 3650 | 1000 | 278 | 255 | 220 | 195
11/15/2020 | 16:40 | 16:43 | 0.05 | 11850 | 11860 | 10 | Rotate | Drilling Parameters WOB: 35; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 200 | 4650 | 3650 | 1000 | 278 | 255 | 220 | 195
11/15/2020 | 16:43 | 16:54 | 0.18333 | 11860 | 11870 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 40; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 54.55 | 4000 | 3650 | 350 | 278 | 255 | 220 | 195
11/15/2020 | 16:54 | 17:10 | 0.26667 | 11870 | 11945 | 75 | Rotate |  | 11876 | 93 | 313 | 10929.16 | 757.3 | -1523.91 | 757.3 | 3.17 |  |  | 40 | 80 | 400 | 12000 | 281.25 | 4000 | 3650 | 350 | 278 | 255 | 220 | 195
11/15/2020 | 17:45 | 17:50 | 0.083333 | 11945 | 11952 | 7 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 84 | 4000 | 3650 | 350 | 278 | 255 | 220 | 195
11/15/2020 | 17:50 | 18:10 | 0.33333 | 11952 | 11967 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 48; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 45 | 4800 | 3700 | 1100 | 273 | 272 | 220 | 195
11/15/2020 | 18:10 | 18:25 | 0.25 | 11967 | 12039 | 72 | Rotate |  | 11970 | 92.5 | 314.5 | 10924.65 | 822.23 | -1591.73 | 822.23 | 1.68 |  |  | 48 | 80 | 400 | 12000 | 288 | 4800 | 3700 | 1100 | 273 | 272 | 220 | 195
11/15/2020 | 18:30 | 18:45 | 0.25 | 12039 | 12054 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 48; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 60 | 4800 | 3700 | 1100 | 273 | 272 | 220 | 195
11/15/2020 | 18:45 | 19:10 | 0.41667 | 12054 | 12133 | 79 | Rotate |  | 12064 | 91.2 | 314 | 10921.62 | 887.78 | -1659.03 | 887.78 | 1.48 |  |  | 38 | 80 | 400 | 12000 | 189.6 | 4800 | 3700 | 1100 | 278 | 272 | 220 | 195
11/15/2020 | 19:15 | 19:45 | 0.5 | 12133 | 12227 | 94 | Rotate |  | 12158 | 91.4 | 314.2 | 10919.48 | 953.18 | -1726.52 | 953.18 | 0.3 |  |  | 38 | 80 | 400 | 12000 | 188 | 4800 | 3700 | 1100 | 284 | 272 | 225 | 200
11/15/2020 | 19:45 | 20:05 | 0.33333 | 12227 | 12322 | 95 | Rotate |  | 12253 | 91.7 | 314.3 | 10916.91 | 1019.45 | -1794.54 | 1019.45 | 0.33 |  |  | 38 | 80 | 400 | 12000 | 285 | 4900 | 3800 | 1100 | 287 | 272 | 225 | 200
11/15/2020 | 20:20 | 20:40 | 0.33333 | 12322 | 12416 | 94 | Rotate |  | 12347 | 93.1 | 314.8 | 10912.98 | 1085.33 | -1861.47 | 1085.33 | 1.58 |  |  | 38 | 80 | 400 | 12000 | 282 | 4900 | 3800 | 1100 | 287 | 272 | 225 | 200
11/15/2020 | 20:45 | 20:48 | 0.05 | 12416 | 12420 | 4 | Rotate | Drilling Parameters WOB: 38; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 12000; Drilling Parameters ROP: 80 | 4900 | 3800 | 1100 | 287 | 272 | 225 | 200
11/15/2020 | 20:48 | 21:05 | 0.28333 | 12420 | 12438 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 63.53 | 4200 | 3800 | 400 | 287 | 272 | 225 | 200
11/15/2020 | 21:05 | 21:25 | 0.33333 | 12438 | 12510 | 72 | Rotate |  | 12441 | 90.4 | 314.1 | 10910.11 | 1151.12 | -1928.53 | 1151.12 | 2.97 |  |  | 38 | 80 | 400 | 12000 | 216 | 4900 | 3800 | 1100 | 287 | 272 | 225 | 200
11/15/2020 | 21:30 | 21:50 | 0.33333 | 12510 | 12605 | 95 | Rotate |  | 12536 | 91 | 313.8 | 10908.95 | 1217.05 | -1996.92 | 1217.05 | 0.71 |  |  | 38 | 80 | 400 | 12000 | 285 | 4900 | 3800 | 1100 | 287 | 272 | 225 | 200
11/15/2020 | 21:55 | 22:10 | 0.25 | 12605 | 12617 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 50; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 48 | 4200 | 3800 | 400 | 287 | 272 | 225 | 200
11/15/2020 | 22:10 | 22:30 | 0.33333 | 12617 | 12700 | 83 | Rotate |  | 12631 | 93.8 | 312.1 | 10904.97 | 1281.71 | -2066.39 | 1281.71 | 3.45 |  |  | 35 | 80 | 400 | 13500 | 249 | 4900 | 3800 | 1100 | 287 | 280 | 225 | 180
11/15/2020 | 22:35 | 22:55 | 0.33333 | 12700 | 12796 | 96 | Rotate |  | 12727 | 93.2 | 312.4 | 10899.11 | 1346.14 | -2137.31 | 1346.14 | 0.7 |  |  | 35 | 80 | 400 | 13500 | 288 | 4900 | 3800 | 1100 | 287 | 280 | 225 | 180
11/15/2020 | 23:00 | 23:20 | 0.33333 | 12796 | 12891 | 95 | Rotate |  | 12822 | 94 | 312.2 | 10893.14 | 1409.95 | -2207.44 | 1409.95 | 0.87 |  |  | 35 | 80 | 400 | 13500 | 285 | 4900 | 3800 | 1100 | 297 | 280 | 225 | 180
11/15/2020 | 23:25 | 23:45 | 0.33333 | 12891 | 12987 | 96 | Rotate |  | 12918 | 95 | 312 | 10885.61 | 1474.11 | -2278.45 | 1474.11 | 1.06 |  |  | 35 | 80 | 400 | 13500 | 288 | 4900 | 3800 | 1100 | 297 | 280 | 225 | 180
11/15/2020 | 23:50 | 24:00 | 0.16667 | 12987 | 12995 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 55; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 48 | 4400 | 3800 | 600 | 297 | 280 | 225 | 180
11/16/2020 | 00:00 | 00:20 | 0.33333 | 12995 | 13005 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 55; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 30 | 4400 | 3800 | 600 | 297 | 280 | 225 | 180
11/16/2020 | 00:20 | 00:40 | 0.33333 | 13005 | 13083 | 78 | Rotate |  | 13014 | 94.1 | 310.4 | 10877.99 | 1537.14 | -2350.45 | 1537.14 | 1.91 |  |  | 35 | 80 | 400 | 13500 | 234 | 4900 | 3800 | 1100 | 297 | 280 | 225 | 180
11/16/2020 | 00:45 | 01:30 | 0.75 | 13083 | 13099 | 16 | Slide | TTF: 0; Drilling Parameters WOB: 58; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 21.33 | 4400 | 3800 | 600 | 289 | 280 | 225 | 180
11/16/2020 | 01:30 | 01:45 | 0.25 | 13099 | 13178 | 79 | Rotate |  | 13109 | 92.3 | 312.7 | 10872.69 | 1600.05 | -2421.43 | 1600.05 | 3.07 |  |  | 40 | 80 | 400 | 14000 | 316 | 4900 | 3800 | 1100 | 290 | 290 | 225 | 180
11/16/2020 | 01:50 | 02:15 | 0.41667 | 13178 | 13272 | 94 | Rotate |  | 13203 | 93 | 313.2 | 10868.35 | 1664.03 | -2490.15 | 1664.03 | 0.91 |  |  | 40 | 80 | 400 | 14000 | 225.6 | 4900 | 3800 | 1100 | 290 | 290 | 225 | 180
11/16/2020 | 02:20 | 02:45 | 0.41667 | 13272 | 13368 | 96 | Rotate |  | 13299 | 93.7 | 313.5 | 10862.74 | 1729.82 | -2559.84 | 1729.82 | 0.79 |  |  | 40 | 80 | 400 | 14000 | 230.4 | 4900 | 3800 | 1100 | 290 | 290 | 225 | 180
11/16/2020 | 02:50 | 03:25 | 0.58333 | 13368 | 13386 | 18 | Slide | TTF: 0; Drilling Parameters WOB: 58; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 30.86 | 4000 | 3800 | 200 | 285 | 290 | 225 | 180
11/16/2020 | 03:25 | 03:45 | 0.33333 | 13386 | 13464 | 78 | Rotate |  | 13395 | 91.9 | 312.8 | 10858.05 | 1795.39 | -2629.8 | 1795.39 | 2.01 |  |  | 40 | 80 | 400 | 14000 | 234 | 4900 | 3800 | 1100 | 287 | 290 | 225 | 180
11/16/2020 | 03:50 | 04:05 | 0.25 | 13464 | 13558 | 94 | Rotate |  | 13489 | 92.5 | 312.7 | 10854.44 | 1859.15 | -2698.77 | 1859.15 | 0.65 |  |  | 40 | 80 | 400 | 14000 | 376 | 4900 | 3800 | 1100 | 291 | 290 | 225 | 180
11/16/2020 | 04:10 | 04:45 | 0.58333 | 13558 | 13573 | 15 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 25.71 | 4000 | 3800 | 200 | 291 | 290 | 225 | 180
11/16/2020 | 04:45 | 05:05 | 0.33333 | 13573 | 13652 | 79 | Rotate |  | 13583 | 92.3 | 311.9 | 10850.5 | 1922.36 | -2768.23 | 1922.36 | 0.88 |  |  | 40 | 80 | 400 | 14000 | 237 | 4900 | 3800 | 1100 | 293 | 290 | 225 | 180
11/16/2020 | 05:10 | 05:30 | 0.33333 | 13652 | 13748 | 96 | Rotate |  | 13679 | 93.2 | 311.8 | 10845.9 | 1986.33 | -2839.66 | 1986.33 | 0.94 |  |  | 42 | 80 | 400 | 14000 | 288 | 4900 | 3800 | 1100 | 293 | 300 | 225 | 180
11/16/2020 | 05:30 | 06:00 | 0.5 | 13748 | 13760 | 12 | Slide | TTF: 0; Drilling Parameters WOB: 58; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 24 | 4000 | 3800 | 200 | 293 | 300 | 225 | 180
11/16/2020 | 06:00 | 06:18 | 0.3 | 13760 | 13843 | 83 | Rotate |  | 13774 | 92.5 | 312.6 | 10841.17 | 2050.07 | -2909.95 | 2050.07 | 1.12 |  |  | 40 | 80 | 400 | 16000 | 276.67 | 5000 | 3800 | 1200 | 293 | 300 | 225 | 180
11/16/2020 | 06:28 | 06:44 | 0.26667 | 13843 | 13937 | 94 | Rotate |  | 13868 | 93 | 312.9 | 10836.66 | 2113.8 | -2978.9 | 2113.8 | 0.62 |  |  | 40 | 80 | 400 | 16000 | 352.5 | 5000 | 3800 | 1200 | 293 | 300 | 225 | 180
11/16/2020 | 06:54 | 07:00 | 0.1 | 13937 | 13947 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 100 | 5000 | 3800 | 1200 | 293 | 300 | 225 | 180
11/16/2020 | 07:00 | 08:00 | 1 | 13947 | 13965 | 18 | Slide | 0 | 13963 | 91.7 | 311.5 | 10832.77 | 2177.56 | -3049.21 | 2177.56 | 2.01 |  |  | 58 |  | 400 |  | 18 | 4000 | 3800 | 200 | 293 | 300 | 225 | 180
11/16/2020 | 08:00 | 08:25 | 0.41667 | 13965 | 14032 | 67 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 160.8 | 5000 | 3800 | 1200 | 293 | 300 | 225 | 180
11/16/2020 | 08:35 | 08:56 | 0.35 | 14032 | 14127 | 95 | Rotate |  | 14058 | 91.7 | 311.1 | 10829.95 | 2240.23 | -3120.55 | 2240.23 | 0.42 |  |  | 40 | 80 | 400 | 16000 | 271.43 | 5000 | 3800 | 1200 | 295 | 300 | 225 | 180
11/16/2020 | 09:06 | 09:30 | 0.4 | 14127 | 14223 | 96 | Rotate |  | 14154 | 92.3 | 311.6 | 10826.6 | 2303.61 | -3192.57 | 2303.61 | 0.81 |  |  | 40 | 80 | 400 | 16000 | 240 | 5000 | 3800 | 1200 | 295 | 300 | 225 | 180
11/16/2020 | 09:40 | 09:55 | 0.25 | 14223 | 14317 | 94 | Rotate |  | 14248 | 93.8 | 311.7 | 10821.6 | 2365.99 | -3262.71 | 2365.99 | 1.6 |  |  | 40 | 80 | 400 | 16000 | 376 | 5000 | 3800 | 1200 | 295 | 300 | 225 | 180
11/16/2020 | 10:05 | 10:10 | 0.083333 | 14317 | 14327 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 120 | 5000 | 3800 | 1200 | 295 | 300 | 225 | 180
11/16/2020 | 10:10 | 11:19 | 1.15 | 14327 | 14352 | 25 | Slide | 0 | 14342 | 91.8 | 313.4 | 10817 | 2429.48 | -3331.87 | 2429.48 | 2.79 |  |  | 58 |  | 400 |  | 21.74 | 4000 | 3800 | 200 | 295 | 300 | 225 | 180
11/16/2020 | 11:19 | 11:35 | 0.26667 | 14352 | 14411 | 59 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 16000; Drilling Parameters ROP: 221.25 | 5000 | 3800 | 1200 | 304 | 300 | 225 | 180
11/16/2020 | 11:45 | 12:02 | 0.28333 | 14411 | 14506 | 95 | Rotate |  | 14437 | 90.8 | 313.8 | 10814.85 | 2494.97 | -3400.64 | 2494.97 | 1.13 |  |  | 40 | 80 | 400 | 16000 | 335.29 | 5000 | 3800 | 1200 | 304 | 300 | 225 | 180
11/16/2020 | 12:12 | 12:30 | 0.3 | 14506 | 14600 | 94 | Rotate |  | 14531 | 91.5 | 314.1 | 10812.96 | 2560.2 | -3468.3 | 2560.2 | 0.81 |  |  | 40 | 80 | 400 | 16000 | 313.33 | 5000 | 3800 | 1200 | 304 | 300 | 225 | 180
11/16/2020 | 12:40 | 12:56 | 0.26667 | 14600 | 14695 | 95 | Rotate |  | 14626 | 92.7 | 314.4 | 10809.48 | 2626.44 | -3536.31 | 2626.44 | 1.3 |  |  | 40 | 80 | 400 | 18000 | 356.25 | 5000 | 3800 | 1200 | 306 | 300 | 225 | 180
11/16/2020 | 13:30 | 13:52 | 0.36667 | 14695 | 14790 | 95 | Rotate |  | 14721 | 94.4 | 314.6 | 10803.6 | 2692.9 | -3603.93 | 2692.9 | 1.8 |  |  | 40 | 80 | 400 | 18000 | 259.09 | 5000 | 3800 | 1200 | 306 | 300 | 225 | 180
11/16/2020 | 14:17 | 14:22 | 0.083333 | 14790 | 14800 | 10 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 19000; Drilling Parameters ROP: 120 | 5000 | 3800 | 1200 | 306 | 300 | 225 | 180
11/16/2020 | 14:22 | 15:30 | 1.1333 | 14800 | 14810 | 10 | Slide | TTF: 0; Drilling Parameters WOB: 58; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 8.82 | 4000 | 3800 | 200 | 306 | 300 | 225 | 180
11/16/2020 | 15:30 | 15:53 | 0.38333 | 14810 | 14885 | 75 | Rotate |  | 14816 | 93.6 | 313.4 | 10796.97 | 2758.73 | -3672.1 | 2758.73 | 1.52 |  |  | 40 | 80 | 400 | 19000 | 195.65 | 5000 | 3800 | 1200 | 306 | 300 | 225 | 180
11/16/2020 | 16:03 | 16:25 | 0.36667 | 14885 | 14981 | 96 | Rotate |  | 14912 | 94.4 | 313.2 | 10790.28 | 2824.41 | -3741.8 | 2824.41 | 0.86 |  |  | 40 | 80 | 400 | 16000 | 261.82 | 5000 | 3800 | 1200 | 306 | 300 | 225 | 180
11/16/2020 | 16:35 | 16:54 | 0.31667 | 14981 | 15077 | 96 | Rotate |  | 15008 | 95.5 | 313.2 | 10781.99 | 2889.88 | -3811.52 | 2889.88 | 1.15 |  |  | 40 | 80 | 400 | 16000 | 303.16 | 5000 | 3800 | 1200 | 306 | 300 | 225 | 180
11/16/2020 | 19:40 | 20:45 | 1.0833 | 15077 | 15102 | 25 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 23.08 | 4000 | 3800 | 200 | 298 | 320 | 225 | 160
11/16/2020 | 20:45 | 21:10 | 0.41667 | 15102 | 15173 | 71 | Rotate |  | 15104 | 92.9 | 313.2 | 10774.96 | 2955.41 | -3881.3 | 2955.41 | 2.71 |  |  | 40 | 80 | 400 | 17000 | 170.4 | 5000 | 3800 | 1200 | 301 | 320 | 225 | 160
11/16/2020 | 21:20 | 22:00 | 0.66667 | 15173 | 15187 | 14 | Slide | TTF: 0; Drilling Parameters WOB: 60; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 21 | 4000 | 3800 | 200 | 300 | 320 | 225 | 160
11/16/2020 | 22:00 | 22:30 | 0.5 | 15187 | 15269 | 82 | Rotate |  | 15200 | 90.5 | 313.5 | 10772.11 | 3021.28 | -3951.08 | 3021.28 | 2.52 |  |  | 40 | 80 | 400 | 17000 | 164 | 5000 | 3800 | 1200 | 303 | 320 | 225 | 160
11/16/2020 | 22:35 | 23:00 | 0.41667 | 15269 | 15364 | 95 | Rotate |  | 15295 | 90.6 | 313.8 | 10771.2 | 3086.85 | -4019.81 | 3086.85 | 0.33 |  |  | 40 | 80 | 400 | 17000 | 228 | 5000 | 3800 | 1200 | 303 | 320 | 225 | 160
11/16/2020 | 23:05 | 23:35 | 0.5 | 15364 | 15460 | 96 | Rotate |  | 15391 | 91.7 | 313.9 | 10769.28 | 3153.34 | -4089.03 | 3153.34 | 1.15 |  |  | 40 | 80 | 400 | 17000 | 192 | 5000 | 3800 | 1200 | 305 | 320 | 225 | 160
11/16/2020 | 23:40 | 24:00 | 0.33333 | 15460 | 15541 | 81 | Rotate |  | 15487 | 93 | 314.1 | 10765.34 | 3219.97 | -4158.02 | 3219.97 | 1.37 |  |  | 40 | 80 | 400 | 17000 | 243 | 5000 | 3800 | 1200 | 309 | 320 | 225 | 160
11/17/2020 | 00:00 | 00:05 | 0.083333 | 15541 | 15556 | 15 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 180 | 5000 | 3800 | 1200 | 309 | 320 | 225 | 160
11/17/2020 | 00:10 | 00:35 | 0.41667 | 15556 | 15653 | 97 | Rotate |  | 15584 | 91.5 | 312.7 | 10761.53 | 3286.56 | -4228.45 | 3286.56 | 2.11 |  |  | 40 | 80 | 400 | 18000 | 232.8 | 5000 | 3800 | 1200 | 309 | 320 | 225 | 160
11/17/2020 | 00:40 | 00:45 | 0.083333 | 15653 | 15658 | 5 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 60 | 5000 | 3800 | 1200 | 309 | 320 | 225 | 160
11/17/2020 | 00:45 | 01:50 | 1.0833 | 15658 | 15664 | 6 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 5.54 | 3900 | 3800 | 100 | 302 | 320 | 225 | 160
11/17/2020 | 01:50 | 01:55 | 0.083333 | 15664 | 15668 | 4 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 48 | 5000 | 3800 | 1200 | 302 | 320 | 225 | 160
11/17/2020 | 01:55 | 03:25 | 1.5 | 15668 | 15676 | 8 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 5.33 | 3900 | 3800 | 100 | 302 | 320 | 225 | 160
11/17/2020 | 03:25 | 03:50 | 0.41667 | 15676 | 15747 | 71 | Rotate |  | 15678 | 93.5 | 313.5 | 10757.43 | 3350.72 | -4297.01 | 3350.72 | 2.29 |  |  | 40 | 80 | 400 | 18000 | 170.4 | 5000 | 3800 | 1200 | 302 | 320 | 225 | 160
11/17/2020 | 03:55 | 04:25 | 0.5 | 15747 | 15842 | 95 | Rotate |  | 15773 | 94.5 | 313.7 | 10750.8 | 3416.08 | -4365.64 | 3416.08 | 1.07 |  |  | 40 | 80 | 400 | 18000 | 190 | 5000 | 3800 | 1200 | 306 | 320 | 225 | 160
11/17/2020 | 04:30 | 05:00 | 0.5 | 15842 | 15939 | 97 | Rotate |  | 15870 | 95.6 | 313.7 | 10742.27 | 3482.83 | -4435.49 | 3482.83 | 1.13 |  |  | 40 | 80 | 400 | 18000 | 194 | 5000 | 3800 | 1200 | 309 | 320 | 225 | 160
11/17/2020 | 06:24 | 08:00 | 1.6 | 15939 | 15948 | 9 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 5.63 | 3900 | 3800 | 100 | 302 | 320 | 225 | 160
11/17/2020 | 11:02 | 12:32 | 1.5 | 15948 | 15959 | 11 | Slide | TTF: 0; Drilling Parameters WOB: 65; Drilling Parameters FLOW: 400; Drilling Parameters ROP: 7.33 | 3900 | 3800 | 100 | 302 | 320 | 225 | 160
11/17/2020 | 12:32 | 13:01 | 0.48333 | 15959 | 16035 | 76 | Rotate |  | 15966 | 94.7 | 314.3 | 10733.65 | 3549.25 | -4504.27 | 3549.25 | 1.13 |  |  | 40 | 80 | 400 | 18000 | 157.24 | 5000 | 3800 | 1200 | 300 | 320 | 225 | 160
11/17/2020 | 13:10 | 14:00 | 0.83333 | 16035 | 16041 | 6 | Slide | 180 | 16041 | 94.7 | 314.3 | 10727.5 | 3601.45 | -4557.77 | 3601.45 | 0 |  |  | 65 |  | 400 |  | 7.2 | 3900 | 3800 | 100 | 302 | 320 | 225 | 160
11/17/2020 |  |  |  | 16041 | 18664 | 2623 | Rotate | Drilling Parameters WOB: 40; Drilling Parameters RPM: 80; Drilling Parameters FLOW: 400; Drilling Parameters Tq: 18000; Drilling Parameters ROP: 180 | 5000 | 3800 | 1200 |  | 320 | 225 | 160