## Sheet1
WELL NAME | REPORT NUMBER | TIME FROM | TIME TO | Duration | P OR U | PHASE | CODE | SUBCODE | SUBCODE DES | DRILLING DAYS | MD FROM | MD TO | ROP | COMMENTS
BIGHORN PASS H06 BH | 1 | 2021-10-08 09:30 | 2021-10-08 09:30 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 10/8/2021 @ 09:30
BIGHORN PASS H06 BH | 1 | 2021-10-08 09:30 | 2021-10-08 11:00 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/BIGHORN PEAK H04 BH T/BIGHORN PASS H06 BH; SET MATS, WALK RIG T/BIGHORN PASS H06 BH; CENTER SUB OVER CONDUCTOR.
BIGHORN PASS H06 BH | 1 | 2021-10-08 11:00 | 2021-10-08 12:00 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
BIGHORN PASS H06 BH | 1 | 2021-10-08 12:00 | 2021-10-08 13:00 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PASS H06 BH | 1 | 2021-10-08 13:00 | 2021-10-08 13:15 | 0.25 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, TAG BOTTOM @ 108'.
BIGHORN PASS H06 BH | 1 | 2021-10-08 13:15 | 2021-10-08 13:15 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 10/7/2021 @ 17:30
BIGHORN PASS H06 BH | 1 | 2021-10-08 13:15 | 2021-10-08 20:00 | 6.75 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.28 | 108 | 2799 | 398.7 | ROTATE DRILL (2,691' IN 6.72 HRS @ 400.5 FPH) WOB-15-35K, RPM-100, TRQ-3K/18K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,700/2,550 PSI, DIFF-250/850 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM.
BIGHORN PASS H06 BH | 1 | 2021-10-08 20:00 | 2021-10-08 21:15 | 1.25 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.33 | 2799 | 3020 | 176.8 | SLIDE (221' IN 1.28 HRS @ 172.7 FPH) WOB-5/15K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1,500/1,850 PSI, DIFF-150/350 PSI. SLIDE DEPTHS: F/1125' T/1140' 15' TF-345 1548-1552 F/1221' T/1237' 15' TF-345 1604-1607 F/1315' T/1330' 15' TF-345 1619-1623 F/1407' T/1422' 15' TF-350 1635-1637 F/1504' T/1519' 15' TF-20R 1651-1654 F/1598' T/1613' 15' TF-HS 1707-1710 F/1691' T/1711' 20' TF-HS 1722-1744 F/1864' T/1884' 20' TF-HS 1815-1823 F/1978' T/2008' 30' TF-HS 1836-1844 F/2150' T/2180' 30' TF-HS 1903-1912 F/2527' T/2557' 30' TF-30R 1952-2003
BIGHORN PASS H06 BH | 1 | 2021-10-08 21:15 | 2021-10-08 22:00 | 0.75 | P | SFHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.36 | 3020 | 3020 | 0 | PUMP 2-30 BBL GEL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,000 PSI.
BIGHORN PASS H06 BH | 1 | 2021-10-08 22:00 | 2021-10-08 23:00 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.41 | 3020 | 3020 | 0 | TRIP OUT OF HOLE F/3,020' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
BIGHORN PASS H06 BH | 1 | 2021-10-08 23:00 | 2021-10-09 00:15 | 1.25 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.46 | 3020 | 3020 | 0 | RACK BACK 3 STANDS AND L/D 1 JT HWDP, REMOVE MWD, RACK BACK MONELS W/ 1 JT HWDP, DRAIN MOTOR, BREAK BIT, L/D MOTOR, PONY COLLAR AND STAB. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND NO PAD WEAR ON STAB. BIT GRADE: 0-0-NO-A-X-0-NO-TD.
BIGHORN PASS H06 BH | 1 | 2021-10-09 00:15 | 2021-10-09 01:00 | 0.75 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.49 | 3020 | 3020 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
BIGHORN PASS H06 BH | 1 | 2021-10-09 01:00 | 2021-10-09 05:15 | 4.25 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.67 | 3020 | 3020 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 10 3/4" 45.5# J-55 BTC CASING T/3,007'. RAN 39 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 100K LBS(W/O BLOCKS). SHOE- 3,007' TOP OF FLOAT COLLAR- 2,928' LEFT OUT 11 JOINTS-424.70'
BIGHORN PASS H06 BH | 1 | 2021-10-09 05:15 | 2021-10-09 06:00 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.7 | 3020 | 3020 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-330, SPP-170. NO LOSSES.
BIGHORN PASS H06 BH | 2 | 2021-10-09 06:00 | 2021-10-09 06:15 | 0.25 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.71 | 3020 | 3020 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-330, SPP-170. NO LOSSES.
BIGHORN PASS H06 BH | 2 | 2021-10-09 06:15 | 2021-10-09 07:00 | 0.75 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.74 | 3020 | 3020 | 0 | RIG DOWN CRT, L/D LANDING JOINT, R/D CASING BAILS AND ELEVATORS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
BIGHORN PASS H06 BH | 2 | 2021-10-09 07:00 | 2021-10-09 09:30 | 2.5 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.84 | 3020 | 3020 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 317 BBLS 11.6 PPG LEAD CEMENT, 85 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 279 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/1,010 PSI PRESSURED UP T/1,510 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 119 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS. OFFLINE: SERVICE TOP DRIVE, DRAWWORKS AND ST-80, REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, RIG UP KILL LINE FROM MUD PUMPS, HOOK UP HYDRAULIC LINES F/KOOMEY T/BOP'S, EMPTY AND CLEAN MUD TANKS.
BIGHORN PASS H06 BH | 2 | 2021-10-09 09:30 | 2021-10-09 11:00 | 1.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.91 | 3020 | 3020 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1,500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, FLUSH THROUGH AND RIG DOWN CELLAR PUMPS, DRESS OUT WELLHEAD. OFFLINE: R/U AUTO CHOKES.
BIGHORN PASS H06 BH | 2 | 2021-10-09 11:00 | 2021-10-09 12:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.95 | 3020 | 3020 | 0 | INSTALL BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD. NOTE: PRESSURE TEST MUD PUMP LINES/VALVES T/250 PSI LOW AND 5000 PSI HIGH OFFLINE.
BIGHORN PASS H06 BH | 2 | 2021-10-09 12:00 | 2021-10-09 13:15 | 1.25 | P | SFHLCSG | BOP | SVCBOP | SERVICE BOP | 1 | 3020 | 3020 | 0 | CHANGE OUT ANNULAR ELEMENT. NOTE: PRESSURE TEST CHOKE MANIFOLD T/250 PSI LOW AND 5,000 PSI HIGH OFFLINE.
BIGHORN PASS H06 BH | 2 | 2021-10-09 13:15 | 2021-10-09 17:00 | 3.75 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.16 | 3020 | 3020 | 0 | NIPPLE UP ROTATING HEAD AND ORBIT VALVE, INSTALL TURNBUCKLES, UNLATCH BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALL KILL LINE, KILL LINE CHECK VALVE,, INSTALL CHOKE LINE TO BOP AND CHOKE, FUNCTION TEST SAME.
BIGHORN PASS H06 BH | 2 | 2021-10-09 17:00 | 2021-10-09 21:30 | 4.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.34 | 3020 | 3020 | 0 | INSTALL TEST PLUG ON TEST JOINT AND TEST BOP'S: TEST TOP RAMS, LOWER RAMS, INSIDE AND OUTSIDE KILL VALVES, INSIDE AND OUTSIDE HCR VALVES, WELLHEAD ADAPTER, FLOOR VALVES, MANUAL IBOP, HYDRAULIC IBOP, KILL LINES BACK TO #1 AND #2 PUMPS, BLINDS AND KILL LINE CHECK VALVE TO 250 PSI LOW / 5000 PSI HIGH, TEST ANNULAR TO 250 PSI LOW / 3500 PSI HIGH. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. REMOVE TEST CAP AND RIG DOWN TESTERS. CLOSED CASING VALVE. NOTE: C/O 4" VALVE ON MP #1.
BIGHORN PASS H06 BH | 2 | 2021-10-09 21:30 | 2021-10-10 01:30 | 4 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.51 | 3020 | 3020 | 0 | MAKE UP FLOW LINE TO ROTATING HEAD AND TO FLOW LINE SCISSOR, FILL UP LINE, CASING FILL LINE, RIG UP KATCH KAN EQUIPMENT ON STACK, FILL MUD TANKS WITH OBM, PERFORM ACCUMULATOR DRAW DOWN TEST.
BIGHORN PASS H06 BH | 2 | 2021-10-10 01:30 | 2021-10-10 02:00 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.53 | 3020 | 3020 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE AND MOUSE HOLE.
BIGHORN PASS H06 BH | 2 | 2021-10-10 02:00 | 2021-10-10 03:45 | 1.75 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.6 | 3020 | 3020 | 0 | PICK UP (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 5.88' BIT TO BEND 8-1/4" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8"NMDC. BIT TO SVY-64' AND GAMMA-60'. TEST MWD-TEST GOOD NOTE: NOTICE LEAK IN EXPANSION JOINT ON FLOWLINE WHILE TESTING MWD.
BIGHORN PASS H06 BH | 2 | 2021-10-10 03:45 | 2021-10-10 04:45 | 1 | U | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.65 | 3020 | 3020 | 0 | CHANGE OUT EXPANSION JOINT ON FLOWLINE DUE TO LEAK.
BIGHORN PASS H06 BH | 2 | 2021-10-10 04:45 | 2021-10-10 06:00 | 1.25 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.7 | 3020 | 3020 | 0 | PICK UP REMAINING BHA: 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, 22 STDS DRILL PIPE AND DSW AGITATOR. BIT TO SVY-64' AND GAMMA-60'.
BIGHORN PASS H06 BH | 3 | 2021-10-10 06:00 | 2021-10-10 06:30 | 0.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.72 | 3020 | 3020 | 0 | FINISH PICKING UP AND TRIPPING IN THE HOLE T/301' WITH 6 1/2" DRILL COLLARS.
BIGHORN PASS H06 BH | 3 | 2021-10-10 06:30 | 2021-10-10 07:30 | 1 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.76 | 3020 | 3020 | 0 | TRIP IN HOLE F/301' T/2,920'. PICK UP AGITATOR ON STAND 22: PSI BEFORE-470, PSI AFTER-565 @ 295 GPM, HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PASS H06 BH | 3 | 2021-10-10 07:30 | 2021-10-10 08:30 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.8 | 3020 | 3020 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD, CONFIRM PROPER VALVE ALIGNMENT, FILL GAS SEPERATOR, PERORM BOP DRILL, RESPONSE TIME= 60 SECONDS.
BIGHORN PASS H06 BH | 3 | 2021-10-10 08:30 | 2021-10-10 10:00 | 1.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.86 | 3020 | 3020 | 0 | DRILL SHOE TRACK AND CEMENT F/2,928' T/3,020', GPM-450, SPP- 1100/1200 PSI, DIFF-50/100, RPM-35, TQ-2/5K.
BIGHORN PASS H06 BH | 3 | 2021-10-10 10:00 | 2021-10-10 10:30 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.89 | 3020 | 3030 | 20 | DRILL 10' NEW FORMATION F/3,020' T/3,030', GPM-450, SPP- 1120/1270 PSI, DIFF-50/150,RPM-35, TQ-2/6K.
BIGHORN PASS H06 BH | 3 | 2021-10-10 10:30 | 2021-10-10 11:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.91 | 3030 | 3030 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-350, SPP-1120 PSI, RPM-35. MUD WT IN/OUT= 8.8 PPG.
BIGHORN PASS H06 BH | 3 | 2021-10-10 11:00 | 2021-10-10 11:30 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.93 | 3030 | 3030 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, 435 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,007' / TVD-2,989'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE ON THE REMOTE CHOKE PANEL. NOTE: PRESSURED UP T/435 PSI CSG PRESSURE ONCE PSI REACHED 435 PSI PRESSURE STARTED BLEEDING OFF RAPIDLY, INSPECTED 2" VALVE ON MUD PUMPS FOR LEAKS AND OBSERVED #2 MUD PUMP 2" VALVE WAS LEAKING, CLOSED 4" VALVE ON #2 MUD PUMP AND PRESSURED UP T/435 PSI CSG PRESSURE, PRESSURE HELD. CHANGED OUT 2" VALVE.
BIGHORN PASS H06 BH | 3 | 2021-10-10 11:30 | 2021-10-10 16:00 | 4.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.11 | 3030 | 4502 | 327.1 | ROT (1472' IN 4.48 HRS @ 328.6 FPH) WOB: 20/30K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 8K/13K, SPP: 3800/4400 PSI, DIFF: 400/600 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
BIGHORN PASS H06 BH | 3 | 2021-10-10 16:00 | 2021-10-10 16:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.13 | 4502 | 4540 | 152 | SLIDE (38' IN .27 HRS @ 140.7 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4,100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/3149 T/3161 12' TF-60R 12:21 - 12:26 SLD F/3810 T/3818 8' TF-90R 14:10 - 14:13 SLD F/4177 T/4187 10' TF-180 15:02 - 15:06 SLD F/4457 T/4465 8' TF-180 15:58 - 16:02
BIGHORN PASS H06 BH | 3 | 2021-10-10 16:15 | 2021-10-10 16:45 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.15 | 4540 | 4540 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PASS H06 BH | 3 | 2021-10-10 16:45 | 2021-10-10 18:15 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.21 | 4540 | 4824 | 189.3 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT POP VALVE #2 MUD PUMP, ROTATE (284' IN 1.5 HR @ 189.3 FPH) WOB: 10/20K, SPM: 110/110, GPM: 705, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 11K/17K, SPP: 2600/3000 PSI, DIFF: 200/400 PSI.
BIGHORN PASS H06 BH | 3 | 2021-10-10 18:15 | 2021-10-10 20:45 | 2.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.31 | 4824 | 5714 | 356 | ROT (890' IN 2.72 HRS @ 327.2 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/16K, SPP: 4,350/5,000 PSI, DIFF: 500/650 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
BIGHORN PASS H06 BH | 3 | 2021-10-10 20:45 | 2021-10-10 22:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.36 | 5714 | 5779 | 52 | SLIDE (65' IN 1.12 HRS @ 58 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4,100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/4885 T/4895 10' TF-180 18:22 - 18:27 SLD F/5320 T/5330 10' TF-180 19:54 - 20:06 SLD F/5491 T/5506 15' TF-150R 20:30 - 20:44 SLD F/5585 T/5595 10' TF-150R 20:56 - 21:09 SLD F/5680 T/5700 20' TF-180 21:24 - 21:47
BIGHORN PASS H06 BH | 3 | 2021-10-10 22:00 | 2021-10-10 22:30 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.39 | 5779 | 5779 | 0 | PERFORM RIG SERVICE ON GEN PACKAGE.
BIGHORN PASS H06 BH | 3 | 2021-10-10 22:30 | 2021-10-11 00:15 | 1.75 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.46 | 5779 | 5779 | 0 | TROUBLESHOOT POWER LOSS ISSUE, ELECTRICIAN DIAGNOSE AND REMEDY ISSUE ON GENS.
BIGHORN PASS H06 BH | 3 | 2021-10-11 00:15 | 2021-10-11 04:30 | 4.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.64 | 5779 | 7077 | 305.4 | ROT (1,298' IN 3.78 HRS @ 343.4 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/18K, SPP: 4,350/5,050 PSI, DIFF: 500/680 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
BIGHORN PASS H06 BH | 3 | 2021-10-11 04:30 | 2021-10-11 06:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.7 | 7077 | 7162 | 56.7 | SLIDE (85' IN 1.97 HRS @ 43.1 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4,100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/5860 T/5870 10' TF-150M 00:33 - 00:52 SLD F/6448 T/6468 20' TF-150M 02:24 - 02:50 SLD F/6624 T/6639 15' TF-130M 03:20 - 03:48 SLD F/6705 T/6725 20' TF-180M 04:02 - 04:21 SLD F/7075 T/7095 20' TF-140M 05:15 - 05:41
BIGHORN PASS H06 BH | 4 | 2021-10-11 06:00 | 2021-10-11 06:15 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.71 | 7162 | 7197 | 140 | ROT (20' IN .12 HRS @ 166.7 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/18K, SPP: 4,350/5,050 PSI, DIFF: 500/700 PSI. SLIDE (15' IN .13 HRS @ 115.4 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4350/4,750 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/7182 T/7197 15' TF-150M 06:07 - 06:15
BIGHORN PASS H06 BH | 4 | 2021-10-11 06:15 | 2021-10-11 06:45 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.73 | 7197 | 7350 | 306 | CONTROL DRILL ON #1 AND #2 PUMPS WHILE CHANGING OUT SWAB ON #3 PUMP, ROTATE (153' IN .5 HRS @ 306 FPH) WOB: 25/35K, SPM: 110/115, GPM: 722, MMRPM: 120, RPM-80, TRPM: 200, TRQ: 11K/18K, SPP: 2950/3550 PSI, DIFF: 400/600 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 06:45 | 2021-10-11 07:30 | 0.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.76 | 7350 | 7561 | 281.3 | ROT (211' IN .88 HRS @ 239.8 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/18K, SPP: 4,450/5,150 PSI, DIFF: 500/700 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 07:30 | 2021-10-11 07:45 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.77 | 7561 | 7575 | 56 | SLIDE (14' IN .12 HRS @ 116.7 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4350/4750 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/7458 T/7472 14' TF-150M 07:16 - 07:23
BIGHORN PASS H06 BH | 4 | 2021-10-11 07:45 | 2021-10-11 11:15 | 3.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.92 | 7575 | 8777 | 343.4 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, ROTATE (1202' IN 3.52 HRS @ 341.47 FPH) WOB: 25/35K, SPM: 110/115, GPM: 722, MMRPM: 120, RPM-80, TRPM: 200, TRQ: 11K/19K, SPP: 3450/4150 PSI, DIFF: 500/700 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 11:15 | 2021-10-11 12:00 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.95 | 8777 | 8845 | 90.7 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, SLIDE (68' IN .73 HRS @ 93.15 FPH) WOB: 10/20K, SPM: 110/115, GPM: 722, MMRPM: 120, SPP: 3450/3850 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/7739 T/7754 15' TF-150 8:19-8:27 SLD F/8296 T/8314 18' TF-150 10:10-10:18 SLD F/8391 T/8411 20' TF-180M 10:38-10:51 SLD F/8485 T/8500 15' TF-200M 11:07-11:22
BIGHORN PASS H06 BH | 4 | 2021-10-11 12:00 | 2021-10-11 12:30 | 0.5 | U | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.97 | 8845 | 8845 | 0 | CIRCULATE AND RECIPROCATE WHILE CHANGE OUT GEN POC BATTERIES
BIGHORN PASS H06 BH | 4 | 2021-10-11 12:30 | 2021-10-11 14:45 | 2.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.06 | 8845 | 9174 | 146.2 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, ROTATE (329' IN 2.28 HRS @ 144.30 FPH) WOB: 25/35K, SPM: 110/115, GPM: 722, MMRPM: 120, RPM-80, TRPM: 200, TRQ: 11K/19K, SPP: 3450/4150 PSI, DIFF: 500/700 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 14:45 | 2021-10-11 15:00 | 0.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.07 | 9174 | 9189 | 60 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, SLIDE (15' IN .22 HRS @ 68.18 FPH) WOB: 10/20K, SPM: 110/115, GPM: 722, MMRPM: 120, SPP: 3450/3850 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/9048 T/9063 15' TF-180 14:15-14:28
BIGHORN PASS H06 BH | 4 | 2021-10-11 15:00 | 2021-10-11 15:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.09 | 9189 | 9215 | 52 | CONTROL DRILL CURVE ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, BUILD CURVE/SLD (26' IN .5 HRS @ 52 FPH) WOB: 15/25K, SPM: 110/115, GPM: 722, MMRPM: 120, SPP: 3450/3850 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/9189' T/9215' 26' TF-HS 15:00-15:30
BIGHORN PASS H06 BH | 4 | 2021-10-11 15:30 | 2021-10-11 16:00 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.11 | 9215 | 9215 | 0 | CIRCULATE ON #1 PUMP AND RECIPROCATE PIPE WHILE CHANGING OUT SWAB ON #3 PUMP, SPM: 110, GPM: 353, RPM-30, TRQ: 5K/9K, SPP: 1100 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 16:00 | 2021-10-11 18:30 | 2.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.22 | 9215 | 9320 | 42 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, BUILD CURVE/SLD (105' IN 2.5 HRS @ 42 FPH) WOB: 15/25K, SPM: 110/115, GPM: 702, MMRPM: 116, SPP: 3200/3500 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/9,215' T/9,320' 105' TF-HS 16:00-18:30
BIGHORN PASS H06 BH | 4 | 2021-10-11 18:30 | 2021-10-11 20:00 | 1.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.28 | 9320 | 9320 | 0 | CIRCULATE ON #1 PUMP AND WORK PIPE WHILE CHANGING OUT POP OFF ON #3 PUMP, SPM: 110, GPM: 353, RPM-0 SPP: 1100 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 20:00 | 2021-10-11 21:30 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.34 | 9320 | 9379 | 39.3 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT DISCHARGE MODULE #2 PUMP, BUILD CURVE/SLD (59' IN 1.5 HRS @ 39.33 FPH) WOB: 25/35K, SPM: 110/112, GPM: 706, MMRPM: 117, SPP: 3200/3600 PSI, DIFF: 200/500 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-11 21:30 | 2021-10-11 23:15 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.42 | 9379 | 9549 | 97.1 | SLIDE (170' IN 1.85 HRS @ 91.9 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 5,200/5,500 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/9,379' T/9,501' 122' TF-HS 21:30-22:57 SLD F/9,546' T/9,594' 48' TF-HS 23:16-23:40
BIGHORN PASS H06 BH | 4 | 2021-10-11 23:15 | 2021-10-12 01:15 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.5 | 9549 | 9790 | 120.5 | ROT (241' IN 1.9 HRS @ 126.8 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-30, TRPM: 179, TRQ: 6K/17K, SPP: 5,200/5,500 PSI, DIFF: 200/300 PSI.
BIGHORN PASS H06 BH | 4 | 2021-10-12 01:15 | 2021-10-12 02:45 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.56 | 9790 | 9790 | 0 | PERFORM CLEAN UP CYCLE PUMPING 2-30 BBL HI-VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7-5/8" CASING. GPM-900, ,SPP-5,200 PSI, SHAKERS CLEAN.
BIGHORN PASS H06 BH | 4 | 2021-10-12 02:45 | 2021-10-12 06:00 | 3.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 3.7 | 9790 | 9790 | 0 | TOH F/9,790' T/2,606', PROPER FILL WITH TRIP TANK, FLOW CHECK AT SHOE (WELL STATIC), REMOVE ROTATING HEAD @ 3,030'.
BIGHORN PASS H06 BH | 5 | 2021-10-12 06:00 | 2021-10-12 07:45 | 1.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 3.77 | 9790 | 9790 | 0 | TRIP OUT F/2,606' T/BHA, HOLE TAKING PROPER FILL ON TRIP TANK, FLOW CHECK @ BHA, WELL STATIC.
BIGHORN PASS H06 BH | 5 | 2021-10-12 07:45 | 2021-10-12 10:45 | 3 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.9 | 9790 | 9790 | 0 | PICK UP AND MAKE UP 2 JTS HWDP TO RACK BACK BHA, RACK BACK HWDP & 2 STDS-6.5" DC, REMOVE MWD TOOL, DRAIN MUD MOTOR, BREAK OUT BIT, CHANGE OUT, SCRIBE, AND RACK BACK NEW MOTOR. NOTE: MUD MOTOR DRAINED GOOD WITH LITTLE SQUAT. BIT GRADED: 1-1-CT-G-X-0-BF-TD.
BIGHORN PASS H06 BH | 5 | 2021-10-12 10:45 | 2021-10-12 11:15 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.92 | 9790 | 9790 | 0 | PULL WEAR BUSHING, L/D MOUSEHOLE, CLEAN AND ORGANIZE RIG FLOOR FOR CASING RUN.
BIGHORN PASS H06 BH | 5 | 2021-10-12 11:15 | 2021-10-12 12:30 | 1.25 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.97 | 9790 | 9790 | 0 | CHANGE OUT TOP VBR'S TO 7-5/8" CASING RAMS, PICK UP JOINT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1500 PSI.
BIGHORN PASS H06 BH | 5 | 2021-10-12 12:30 | 2021-10-12 14:00 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.03 | 9790 | 9790 | 0 | HOLD PJSM AND RIG UP FRANK'S CASING TOOLS & EQUIPMENT.
BIGHORN PASS H06 BH | 5 | 2021-10-12 14:00 | 2021-10-12 14:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.05 | 9790 | 9790 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PASS H06 BH | 5 | 2021-10-12 14:30 | 2021-10-13 | 9.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.45 | 9790 | 9790 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN INTERMEDIATE CASING T/9,774', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 220 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG,1-10' PUP JT, 1-JT OF 7 5/8" 29.7# P-110 IC BTC CSG, TOTAL OF 222 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 44 LATCH ON BOW SPRING CENTRALIZERS @ 9,470' AND EVERY 4TH JT UP TO 2,450'. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/210K (W/O BLOCKS) FLOAT SHOE- 9,774' TOP OF FLOAT COLLAR-9,985'. 12 JOINTS LEFT OUT- 518.46', 1-10' & 2-15' PUP JTS OUT
BIGHORN PASS H06 BH | 5 | 2021-10-13 | 2021-10-13 00:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 4.47 | 9790 | 9790 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
BIGHORN PASS H06 BH | 5 | 2021-10-13 00:30 | 2021-10-13 02:00 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.53 | 9790 | 9790 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 105, 8.0 BPM, SPP: 580 PSI, NO LOSSES.
BIGHORN PASS H06 BH | 5 | 2021-10-13 02:00 | 2021-10-13 04:30 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.64 | 9790 | 9790 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4,000 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.5 PPG SPACER. 283 BBL 11.8 PPG 820 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPNAY REP WITNESS PLUG DROP, DISPLACE WITH 445 BBLS OF 9.8 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1,500 PSI AT 3 BPM, BUMP PLUG AND INCREASE PSI 500 OVER T/2,000 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI (5.5 BBLS)-FLOATS HELD. BROUGHT PRESSURE UP TO 3,500 PSI AND HOLD 30 MINUTES, PLUG BUMPED @ 04:28 HRS CEMENT W/ FULL RETURNS WHILE PUMPING CEMENT. 50 BBLS SPACER TO SURFACE. ESTIMATED TOP OF CEMENT: 34'
BIGHORN PASS H06 BH | 5 | 2021-10-13 04:30 | 2021-10-13 05:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.66 | 9790 | 9790 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. BLED BACK 8 BBLS
BIGHORN PASS H06 BH | 5 | 2021-10-13 05:00 | 2021-10-13 06:00 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.7 | 9790 | 9790 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
BIGHORN PASS H06 BH | 6 | 2021-10-13 06:00 | 2021-10-13 06:45 | 0.75 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.73 | 9790 | 9790 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 15K, BROKE OUT & LAID DOWN SETTING TOOL.
BIGHORN PASS H06 BH | 6 | 2021-10-13 06:45 | 2021-10-13 08:00 | 1.25 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.78 | 9790 | 9790 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL.
BIGHORN PASS H06 BH | 6 | 2021-10-13 08:00 | 2021-10-13 09:30 | 1.5 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.84 | 9790 | 9790 | 0 | REMOVE CASING RAMS; INSTALL VARIABLE RAMS
BIGHORN PASS H06 BH | 6 | 2021-10-13 09:30 | 2021-10-13 11:00 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 4.91 | 9790 | 9790 | 0 | SLIP AND CUT 70' OF DRILLING LINE
BIGHORN PASS H06 BH | 6 | 2021-10-13 11:00 | 2021-10-13 12:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.95 | 9790 | 9790 | 0 | LUBRICATE TOP DRIVE, ST-80, AND DRAWORKS
BIGHORN PASS H06 BH | 6 | 2021-10-13 12:00 | 2021-10-13 12:00 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 4.95 | 9790 | 9790 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 10-13-21 @ 12:00
BIGHORN PASS H06 BH | 7 | 2021-11-07 20:30 | 2021-11-07 21:45 | 1.25 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5 | 9790 | 9790 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM BIGHORN PLAINS H 02 TO BIGHORN PEAK H 04, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
BIGHORN PASS H06 BH | 7 | 2021-11-07 20:30 | 2021-11-07 20:30 | 0 | P | INTHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 4.95 | 9790 | 9790 |  | MILESTONE_RESUME WELL 1 ON 11/08/2021 @ 20:30
BIGHORN PASS H06 BH | 7 | 2021-11-07 21:45 | 2021-11-07 22:45 | 1 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.04 | 9790 | 9790 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BIGHORN PASS H06 BH | 7 | 2021-11-07 22:45 | 2021-11-08 03:15 | 4.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.23 | 9790 | 9790 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, TEST CHOKE MANIFOLD MANUAL VALVES,SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. NOTE: REBUILT 2" KILL LINE MUD VALVE ON #2 MUD PUMP AND REMOVED AND CLEANED OUT KILL LINE CHECK VALVE ON BOP. BOTH TESTED GOOD AFTERWARD. STRAP AND STAGE BHA.
BIGHORN PASS H06 BH | 7 | 2021-11-08 03:15 | 2021-11-08 04:00 | 0.75 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 5.26 | 9790 | 9790 | 0 | RIG DOWN TESTERS, PULL TEST PLUG, INSTALL WEAR BUSHING, CLOSE CASING VALVE, INSTALL MOUSE HOLE
BIGHORN PASS H06 BH | 7 | 2021-11-08 04:00 | 2021-11-08 05:30 | 1.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.32 | 9790 | 9790 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13628581 JETS 6X18 TFA: 1.49), 5.5", 6/7, 11.7 STG @ 2.12° SLICK; .9 REV/GAL; 4.11' BIT TO BEND; 5.56" PAD OD; FLOW RANGE- 150/350 GPM; MAX DIFF-2,724 PSI; STALL TRQ-7382 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP,AGITATOR, BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD (TEST GOOD).
BIGHORN PASS H06 BH | 7 | 2021-11-08 05:30 | 2021-11-08 06:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.34 | 9790 | 9790 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PASS H06 BH | 8 | 2021-11-08 06:00 | 2021-11-08 07:30 | 1.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.41 | 9790 | 9790 | 0 | TRIP IN THE HOLE F/BHA T/2,780', PROPER DISPLACEMENT TO TRIP TANK.
BIGHORN PASS H06 BH | 8 | 2021-11-08 07:30 | 2021-11-08 07:45 | 0.25 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 5.42 | 9790 | 9790 | 0 | FILLED PIPE AND FLOW TESTED DRILL STRING, PICKED UP AGITATOR ON STAND 28 AND FLOW TESTED. SPP BEFORE-1240 PSI SPP AFTER- 1520 PSI @ 262 GPM.
BIGHORN PASS H06 BH | 8 | 2021-11-08 07:45 | 2021-11-08 11:15 | 3.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.56 | 9790 | 9790 | 0 | TRIP IN THE HOLE F/BHA T/9,605', PROPER DISPLACEMENT TO TRIP TANK. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
BIGHORN PASS H06 BH | 8 | 2021-11-08 11:15 | 2021-11-08 12:45 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.63 | 9790 | 9790 | 0 | SLIP AND CUT 90' OF DRILL LINE.
BIGHORN PASS H06 BH | 8 | 2021-11-08 12:45 | 2021-11-08 13:15 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.65 | 9790 | 9790 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PASS H06 BH | 8 | 2021-11-08 13:15 | 2021-11-08 13:30 | 0.25 | P | INTHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 5.66 | 9790 | 9790 | 0 | WASH/REAM F/9,605' T/9,685', TAGGED FLOAT COLLAR @ 9,685',VERIFY CHOKE VALVE ALIGNMENT, PUMP THROUGH GAS SEPERATOR PRIOR TO DRILL OUT. PERFORM BOP DRILL, RESPONSE TIME= 28 SECONDS.
BIGHORN PASS H06 BH | 8 | 2021-11-08 13:30 | 2021-11-08 14:15 | 0.75 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.69 | 9790 | 9800 | 13.3 | DRILL SHOE TRACK AND 10' NEW FORMATION F/9,790' T/9,800', WOB-5/10K, RPM-30, GPM-262, SPP-2000/2100 PSI, DIFF-50/100 PSI, RPM-30, TQ-4/6K.
BIGHORN PASS H06 BH | 8 | 2021-11-08 14:15 | 2021-11-08 15:00 | 0.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.72 | 9800 | 9800 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T., GPM-300, SPP-2600 PSI, RPM-30, MUD WT IN 9.1 PPG, MUD WT OUT 9.1PPG.
BIGHORN PASS H06 BH | 8 | 2021-11-08 15:00 | 2021-11-08 15:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.74 | 9800 | 9800 | 0 | PERFORM F.I.T. WITH 9.1 PPG OBM, 1965 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-9,774' / TVD-9,683'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE.
BIGHORN PASS H06 BH | 8 | 2021-11-08 15:30 | 2021-11-08 20:00 | 4.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.93 | 9800 | 10110 | 68.9 | BUILD CURVE-SLIDE (310' IN 4.5 HR @ 68.8 FPH) WOB-30/40K, SPM-67/67, GPM-350, MRPM-315, SPP-4200/4700 PSI, DIFF-300/600 PSI SLIDE DEPTHS: F/9,800'- T/9,987', 187', TF:HS, 15:30-18:49 F/10,027'-T/10,085',58', TF:HS, 19:30-20:03 F/10,112'-T/10,177',65', TF:30R, 20:31-21:09
BIGHORN PASS H06 BH | 8 | 2021-11-08 15:30 | 2021-11-08 15:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.74 | 9800 | 9800 |  | MILESTONE_START CURVE SECTION 11-8-2021 @ 15:30
BIGHORN PASS H06 BH | 8 | 2021-11-08 20:00 | 2021-11-08 21:30 | 1.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.99 | 10110 | 10199 | 59.3 | BUILD CURVE-ROTATE (89' IN 1.5 HRS @ 59.3 FPH) WOB-25/35K, SPM-67/67, GPM-350, RPM-30, MRPM-315, TRPM-345, SPP-4200/4700 PSI, DIFF-250/450 PSI, CHOKES- 100% / 100%, FLARE-0-X', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= PSI. NOTE: AT 9,987' SHUT WELL IN AND DRILL THROUGH CHOKE WITH BOTH CHOKES 100% OPEN.
BIGHORN PASS H06 BH | 8 | 2021-11-08 21:30 | 2021-11-09 00:30 | 3 | U | PRDHLCV | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.11 | 10199 | 10199 | 0 | MOTOR STALLED TO 1,700 PSI WHILE ROTATING ON BOTOTM. SHUT DOWN PUMPS, PULL OFF BOTTOM AND BREAK FREE. BROUGHT PUMPS BACK UP NOTICED PARTIAL RETURNS (40%), OPENED ORBIT VALVE, CLOSE HCR AND ATTEPMT TO RE-ESTABLISH FULL RETURNS ON FLOW LINE WITHOUT SUCCESS. TOTAL LOSSES AT THIS TIME WERE 122BBLS. DECISION MADE TO PUMP KILL MUD AND GO ON MUD CAP. PREP PITS FOR MUD CAP DRILLING. PUMP 140 BBLS OF 17PPG KILL MUD DOWN ANNULUS THROUGH KILL LINE. MAX SICP=860, GPM=160, CASING PRESSURE BROKE OVER TO 339 AND CONTINUED TO DROP WHILE INCREASING PUMPS.
BIGHORN PASS H06 BH | 8 | 2021-11-09 00:30 | 2021-11-09 03:45 | 3.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.25 | 10199 | 10362 | 50.2 | BUILD CURVE-SLIDE (163' IN 3.35HR @ 48.65 FPH) WOB-30/40K, SPM-67/67, GPM-350, MRPM-315, SPP-4200/4700 PSI, DIFF-300/600 PSI, DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/10,207'- T/10,272', 65', TF:30R, 00:30-01:20 F/10,307'-T/10,365',58', TF:HS, 01:48-02:53 F/10,412'-T/10,461',49', TF:HS, 03:20- 04:51
BIGHORN PASS H06 BH | 8 | 2021-11-09 03:45 | 2021-11-09 06:00 | 2.25 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.34 | 10362 | 10524 | 72 | BUILD CURVE-ROTATE (162' IN 2.15HRS @ 75.34 FPH) WOB-25/35K, SPM-67/67, GPM-350, RPM-30, MRPM-315, TRPM-345, SPP-4200/4700 PSI, DIFF-250/450 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA, MAX CASING PRESSURE=223PSI NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 03:27AM HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 10,413', NEW WINDOW: 0' ABOVE / 10' BELOW. , NEW TARGET: 10116’ TVD AT 0 VS WITH 87 DEG INC 0’ ABOVE/ 10’ BELOW, 50’ LEFT / 50’ RIGHT
BIGHORN PASS H06 BH | 9 | 2021-11-09 06:00 | 2021-11-09 07:45 | 1.75 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.42 | 10524 | 10600 | 43.4 | BUILD CURVE-SLIDE (76' IN 1.75HR @ 43.43 FPH) WOB-30/40K, SPM-67/67, GPM-350, MRPM-315, SPP-4200/4700 PSI, DIFF-300/600 PSI, DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/10,524'- T/10,600', 76', TF:HS, 06:00-07:45 F/10,307'-T/10,365',58', TF:HS, 01:48-02:53 F/10,412'-T/10,461',49', TF:HS, 03:20- 04:51
BIGHORN PASS H06 BH | 9 | 2021-11-09 07:45 | 2021-11-09 15:00 | 7.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.72 | 10600 | 11776 | 162.2 | ROTATE DRILL LATERAL (1176' IN 7.15 HR @ 164.5 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-9K/13K, MRPM-338, TTRPM-418, SPP- 4200/5200 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 08:41 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 10,724', NEW TARGET: 10125’ TVD AT 0 VS WITH 87° INC, 5’ ABOVE/ 5’ BELOW, 50’ LEFT / 50’ RIGHT, TARGET CHANGE RECEIVED VIA TEXT @ 15:07 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 11,713', NEW TARGET: 10131’ TVD AT 0 VS WITH 86.9° INC, 5’ ABOVE/ 5’ BELOW, 50’ LEFT / 50’ RIGHT
BIGHORN PASS H06 BH | 9 | 2021-11-09 07:45 | 2021-11-09 07:45 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.42 | 10600 | 10600 |  | MILESTONE_START LATERAL SECTION ON 11/08/2021 @ 07:45
BIGHORN PASS H06 BH | 9 | 2021-11-09 07:45 | 2021-11-09 07:45 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.42 | 10600 | 10600 |  | MILESTONE_LAND/END CURVE SECTION ON 11/08/2021 @ 07:45, MD:10,600', TVD:10,130'
BIGHORN PASS H06 BH | 9 | 2021-11-09 15:00 | 2021-11-09 17:15 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.81 | 11776 | 11875 | 44 | SLD DRILL LATERAL (99' IN 2.35 HRS @ 42.1 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-338, SPP -4200/4600 PSI, DIFF-200/400 PSI, CHOKES-0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: SLD F/10,848'-T/10,857', 09', TF:180, 09:32-09:47 SLD F/11,129'-T/11,144', 15', TF:90L, 11:20-11:33 SLD F/11412 T/11427 15' TF-90L 1254-1316 SLD F/11695 T/11715 20' TF-60R 1449-1515 SLD F/11790 T/11810 20' TF-70R 1543-1615 SLD F/11823 T/11843 20' TF-70R 1624-1657
BIGHORN PASS H06 BH | 9 | 2021-11-09 17:15 | 2021-11-09 17:45 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.83 | 11875 | 11875 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PASS H06 BH | 9 | 2021-11-09 17:45 | 2021-11-09 20:45 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.96 | 11875 | 12328 | 151 | ROTATE DRILL LATERAL (453' IN 3.13 HR @ 144.72 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-9K/22K, MRPM-338, TTRPM-418, SPP- 4200/5200 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: WINDOW CHANGE RECEIVED VIA TEXT AT 17:53, 0' ABOVE / 10' BELOW DEPTH 11,899' NOTE: WINDOW CHANGE RECEIVED VIA TEXT AT 20:54, 5' ABOVE / 5' BELOW DEPTH 12,316'
BIGHORN PASS H06 BH | 9 | 2021-11-09 20:45 | 2021-11-09 21:45 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7 | 12328 | 12378 | 50 | SLD DRILL LATERAL (50' IN .92 HRS @ 54.34 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-338, SPP -4200/4600 PSI, DIFF-200/400 PSI, CHOKES-0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/11,978' T/11,998' 20' TF-110R 18:24-18:43 F/12,078' T/12,092' 15' TF- 90R 19:13-19:30 F/12,358' T/12,373' 15' TF- 150R 21:24-21:48
BIGHORN PASS H06 BH | 9 | 2021-11-09 21:45 | 2021-11-09 22:15 | 0.5 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 7.02 | 12378 | 12378 | 0 | WHILE ROTATE DRILLING 5' AFTER A SLIDE, DRILL STRING STALLED AT TORQUE LIMIT (SET AT 22K). KILLED MUD PUMP, SLOWLY RELEASED TORQUE AND PICKED UP OFF BOTTOM. BROUGHT MUD PUMPS BACK TO DRILLING RATE AND KICKED IN ROTARY, ROTARY STALLED AT 22K (NO INCREASE IN SPP PRESSURE). WORKED TORQUE OUT AND WORKED STRING. PICKED UP TO 380K STRING WIEGHT AND BACK DOWN TO ROTATING WEIGHT (175k), WITH NO SUCCESS. INCREASED TORQUE LIMIT TO 28K, ROTARY STALLED AND WORKED STRING DOWN TO WITHIN 5' OF BOTTOM AND DRILL STRING BROKE FREE. WASHED AND REAMED 25' OF KELLY UNTILL HOLE WAS SLICK. NOTE: DURING LAST FEW FEET OF PREVIOUS SLIDE SPP DECREASED BY 700 PSI
BIGHORN PASS H06 BH | 9 | 2021-11-09 22:15 | 2021-11-10 04:00 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.26 | 12378 | 13088 | 123.5 | ROTATE DRILL LATERAL (710' IN 5.77 HR @ 123.05 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-8K/15K, MRPM-338, TTRPM-418, SPP- 4000/5000 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 9 | 2021-11-10 04:00 | 2021-11-10 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.34 | 13088 | 13187 | 49.5 | SLD DRILL LATERAL (99' IN 1.98 HRS @ 50 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-338, SPP -4000/4400 PSI, DIFF-200/400 PSI, CHOKES-0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/12,541' T/12,561' 20' TF-70R 00:04-00:25 F/12,727' T/12,747' 20' TF- 90L 01:30-01:54 F/12,821' T/12,841' 20' TF- 90L 02:35-02:48 F/12,915' T/12,935' 20' TF- 90L 03:25-03:42 F/13,102' T/13,121' 20' TF- 130L 04:45-05:29
BIGHORN PASS H06 BH | 10 | 2021-11-10 06:00 | 2021-11-10 13:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.64 | 13187 | 14051 | 123.4 | ROTATE DRILL LATERAL (864' IN 6.92 HR @ 125 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-9K/13K, MRPM-338, TTRPM-418, SPP- 4200/5300 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 10 | 2021-11-10 13:00 | 2021-11-10 15:30 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.74 | 14051 | 14131 | 32 | SLD DRILL LATERAL (80' IN 2.58 HRS @ 31 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-338, SPP -4200/4600 PSI, DIFF-200/400 PSI, CHOKES-0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/13,198' T/13,218' 20' TF:90L 06:08-06:52 F/13,293' T/13,313' 20' TF:102L 07:44-08:24 F/13,,386' T/13,406' 20' TF:90L 09:01-09:25 F/13,762' T/13,772' 10' TF:90L 12:23-12:43 F/14,046' T/14,056' 10' TF:80R 14:40-15:07
BIGHORN PASS H06 BH | 10 | 2021-11-10 15:30 | 2021-11-10 16:30 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.78 | 14131 | 14131 | 0 | SERVICE RIG. LUBE TD, ST-80 & DRWKS. RIG MANAGER PRESENT
BIGHORN PASS H06 BH | 10 | 2021-11-10 16:30 | 2021-11-11 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.09 | 14131 | 15103 | 129.6 | ROTATE DRILL LATERAL (972' IN 7.4 HR @ 131.35 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-9K/17K, MRPM-338, TTRPM-418, SPP- 4200/5300 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 10 | 2021-11-11 | 2021-11-11 02:30 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.2 | 15103 | 15170 | 26.8 | SLD DRILL LATERAL (67' IN 2.6 HRS @ 25.76 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-338, SPP -4200/4600 PSI, DIFF-200/400 PSI, CHOKES-0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/14,334'-T/14,349' 15' TF:180, 18:25-18:58 F/14,523'-T/14,538', 15', TF:140L, 20:07-20:37 F/14,618'-T/14,628', 10', TF:180, 21:10-21:37 F/14,902'-T/14,914', 12' TF:HS, 23:25-23:48 F/15,090'-T/15,105', 15', TF:180, 01:17-02:00
BIGHORN PASS H06 BH | 10 | 2021-11-11 02:30 | 2021-11-11 02:45 | 0.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.21 | 15170 | 15170 | 0 | TROUBLE SHOOT MWD. RECYCLE PUMPS TO RECEIVE MWD SVY.
BIGHORN PASS H06 BH | 10 | 2021-11-11 02:45 | 2021-11-11 06:00 | 3.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.34 | 15170 | 15642 | 145.2 | ROTATE DRILL LATERAL (472' IN 3.25 HR @ 145.23 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-9K/17K, MRPM-338, TTRPM-418, SPP- 4200/5300 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 11 | 2021-11-11 06:00 | 2021-11-11 08:45 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.46 | 15642 | 15821 | 65.1 | ROTATE DRILL LATERAL (179' IN 2.65 HR @ 68 FPH) WOB-20/30K, SPM-72/72, GPM-375, RPM 80, TQ-9K/17K, MRPM-338, TTRPM-418, SPP- 4200/5300 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 11 | 2021-11-11 08:45 | 2021-11-11 10:15 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.52 | 15821 | 15852 | 20.7 | SLD DRILL LATERAL (31' IN 1.6 HRS @ 19 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-338, SPP -4200/4600 PSI, DIFF-200/400 PSI, CHOKES-0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: SLD F/15652' T/15670' 18' TF-110L 06:17-07:18 SLD F/15839' T/15852' 13' TF-120L 09:40-10:15
BIGHORN PASS H06 BH | 11 | 2021-11-11 10:15 | 2021-11-11 13:30 | 3.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.66 | 15852 | 15852 | 0 | SLIDING @ 15,852' THE MUD MOTOR STALLED OUT ; AFTER BRINGING PUMPS BACK ONLINE THE DIFFERENTIAL AND TORQUE INCREASED WHILE PUMPING AT A REDUCED RATE, GPM-157, SPP-3800 PSI, TRQ-20K INDICATING THE HOLE WAS PACKING OFF; PUMPED AT REDUCED RATE UNTIL ABLE TO STAGE PUMPS AND RPM UP TO DRILLING RATE, BACK REAM HOLE CLEAN UNTIL HOLE SHOWED TO BE CLEAN; ATTEMPT TO WASH AND REAM BACK TO BOTTOM; TAGGED BOTTOM LIGHTLY WITH 3/5K WOB, RPM-70; SLOWLY INCREASED DIFFERENTIAL TO 1,200 PSI; DIFFERENTIAL WOULD NOT DRILL OFF AND WOB CONTINUED TO INCREASE; DECISION WAS MADE TO POOH TO INSPECT BHA FOR POTENTIAL FAILED MUD MOTOR; CONTINUE CIRCULATING 2 BOTTOM'S UP CALCULATED FROM BOTTOM TO CASING SHOE TO CLEAN HOLE
BIGHORN PASS H06 BH | 11 | 2021-11-11 13:30 | 2021-11-11 16:30 | 3 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.78 | 15852 | 15852 | 0 | WASH AND REAM OUT OF HOLE F/15,852' T/13,517', GPM-375, RPM-70, TRQ-14/16K, SPP-3900
BIGHORN PASS H06 BH | 11 | 2021-11-11 16:30 | 2021-11-11 19:00 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.89 | 15852 | 15852 | 0 | STRIP OUT OF THE HOLE W/BHA #3 F/13,517'-T/9,735' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PASS H06 BH | 11 | 2021-11-11 19:00 | 2021-11-11 19:30 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 8.91 | 15852 | 15852 | 0 | BULL HEAD 30 BBLS OF 16.8PPG KILL MUD DOWN BACKSIDE. NO CASING PRESSURE
BIGHORN PASS H06 BH | 11 | 2021-11-11 19:30 | 2021-11-11 22:00 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.01 | 15852 | 15852 | 0 | STRIP OUT OF THE HOLE W/BHA #3 F/9,735'-T/3,014' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 193 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PASS H06 BH | 11 | 2021-11-11 22:00 | 2021-11-11 22:30 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 9.03 | 15852 | 15852 | 0 | BULL HEAD 50 BBLS OF 16.8PPG KILL MUD DOWN BACKSIDE. INITIAL CASING PRESSURE=193, MAX CASING PRESSURE= 193. FINAL CASING PRESSURE=0 NOTE: SICP FELL TO 0 PSI @ 46.9BBLS (752 STKS). CONT. PUMPING UNTIL A TTL OF 50 BBLS WERE PUMPED. PUMP RATE: 146 GPM. CONDUCT FLOW CHECK= NO FLOW.
BIGHORN PASS H06 BH | 11 | 2021-11-11 22:30 | 2021-11-11 23:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 9.05 | 15852 | 15852 | 0 | REMOVE RT-HEAD AND INSTAL TRIP NIPPLE. RIG MANAGER PRESENT.
BIGHORN PASS H06 BH | 11 | 2021-11-11 23:00 | 2021-11-12 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.09 | 15852 | 15852 | 0 | POOH W/BHA #3 F/3,014'-T/573' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. NOTE: @ 2,805' L/D AGITATOR.
BIGHORN PASS H06 BH | 11 | 2021-11-12 | 2021-11-12 00:45 | 0.75 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 9.13 | 15852 | 15852 | 0 | @ 573' WELL BEGAN TO FLOW. SPACED OUT AND SHUT WELL IN VIA TOP RAMS. BULL HEAD 29.3 BBLS OF 16.8PPG KILL MUD DOWN BACKSIDE, PRESSURE BROKE OVER @ 280 PSI AND DECREASED TO 264 PSI. SICP THEN BEGAN TO INCREASE, CONT. PUMPING ADDITIONAL 23.3BBLS OF 16.8PPG, SICP STABILIZED @ 287 PSI. KILLED PUMP AND SICP FELL TO 0 PSI. AT THAT POINT DESICION WAS MADE TO PUMP ADDITIONAL 23.65BBLS OF 16.8PPG, SICP DECREASED TO 208 PSI. KILLED PUMPS TO MONITOR SICP. SICP FELL TO 0 PSI. MONITOR WELL (FLOW CHECK) FOR 10 MIN= NO FLOW/WELL STATIC. TTL BBLS OF 16.8PPG KILL MUD PUMPED= 76.25 BBLS. GPM: 146 INITIAL CASING PRESSURE=126, MAX CASING PRESSURE= 287. FINAL CASING PRESSURE=0
BIGHORN PASS H06 BH | 11 | 2021-11-12 00:45 | 2021-11-12 01:30 | 0.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.16 | 15852 | 15852 | 0 | CONT POOH W/BHA #3 F/573'( FILLING BACKSIDE WITH 16.8 PPG OBM CALCULATED FILL). REMOVE MWD AND RACK BACK BHA. NOTE: BIT AND LOWER POWER END OF THE MOTOR WERE MISSING. EST LENGTH OF MISSING PIECE=3.67' PLUS BIT. CONTACTED MANAGEMENT.
BIGHORN PASS H06 BH | 11 | 2021-11-12 01:30 | 2021-11-12 02:45 | 1.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 9.21 | 15852 | 15852 | 0 | P/U BHA #4. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13618580 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 +.001 .68 REV/GAL; 4.11' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, 33 STANDS DP, AGITATOR (BALL DROP). BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD= GOOD.
BIGHORN PASS H06 BH | 11 | 2021-11-12 02:45 | 2021-11-12 03:15 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.23 | 15852 | 15852 | 0 | TIH W/ BHA #4 F/BHA-T/1,200'. CHOKE POSITION: 0%/0%.
BIGHORN PASS H06 BH | 11 | 2021-11-12 03:15 | 2021-11-12 03:45 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.25 | 15852 | 15852 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. RIG MANAGER PRESENT
BIGHORN PASS H06 BH | 11 | 2021-11-12 03:45 | 2021-11-12 04:00 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.26 | 15852 | 15852 | 0 | TIH W/ BHA #4 F/1,200'-T/1,794'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0
BIGHORN PASS H06 BH | 11 | 2021-11-12 04:00 | 2021-11-12 05:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.3 | 15852 | 15852 | 0 | SERVICE RIG. REPAIR HYDRAULIC HOSE ON ST-80. RIG MANAGER PRESENT NOTE: SICP= 0 PSI
BIGHORN PASS H06 BH | 11 | 2021-11-12 05:00 | 2021-11-12 06:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.34 | 15852 | 15852 | 0 | TIH W/ BHA #4 F/1,794'-T/3,700'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0. NOTE: PRESSURE BEFOR AGITATOR #1=1,350 PSI, SPM=105. PRESSURE AFTER AGITATOR #1=1,680 PSI, SPM=105.
BIGHORN PASS H06 BH | 12 | 2021-11-12 06:00 | 2021-11-12 08:45 | 2.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.46 | 15852 | 15852 | 0 | STRIP IN THE HOLE W/ BHA #4 F/3,700'-T/9,723'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0. NOTE: P/U "ON DEMAND" AGITATOR @ 5,927' PRESSURE BEFOR AGITATOR #2=2,550 PSI, SPM=105. PRESSURE AFTER AGITATOR #2=2,678 PSI, SPM=105.
BIGHORN PASS H06 BH | 12 | 2021-11-12 08:45 | 2021-11-12 10:15 | 1.5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 9.52 | 15852 | 15852 | 0 | CUT AND SLIP 50' OF DRILLING LINE. RM PRESENT. NOTE: FOSV INSTALLED. SICP=0 PSI
BIGHORN PASS H06 BH | 12 | 2021-11-12 10:15 | 2021-11-12 10:45 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.54 | 15852 | 15852 | 0 | SERVICE RIG. LUBE TD, ST-80 & DRWKS. RIG MANAGER PRESENT. SICP= 0 PSI
BIGHORN PASS H06 BH | 12 | 2021-11-12 10:45 | 2021-11-12 11:45 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.58 | 15852 | 15852 | 0 | STRIP IN THE HOLE W/ BHA #4 F/9,723'-T/10,514'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0. NOTE: CHECK ST-80 MAKE UP TQ WITH RIG TONGS. RESULT: GOOD
BIGHORN PASS H06 BH | 12 | 2021-11-12 11:45 | 2021-11-12 12:30 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.61 | 15852 | 15852 | 0 | @ 10,514' DRILL STRING BEGAN TO TAKE WEIGHT. MAKE UP TOP DRIVE AND FILL PIPE IN PREPARATION TO WASH AND REAM. STARTED STAGING UP BOTH GPM AND RPM T/ 265 GPM AND 30 RPM (TQ=4K, SPP=3,800, SICP=260), CASING PSI INCREASED TO 282 PSI NOTE: ONCE AT RATE, RT-HEAD BEGAN TO LEAK. SHUT PUMPS DOWN, SPACED OUT AND CLOSED ANNULAR. LINED UP TO BULL HEAD KILL MUD DOWN BACKSIDE. SICP=282. PUMPED 75 BBLS OF 17.0 PPG OBM. STAGE PUMPS UP TO 131 GPM. SICP BROKE OVER @ 400 PSI. FINAL SICP=0 PSI.
BIGHORN PASS H06 BH | 12 | 2021-11-12 12:30 | 2021-11-12 13:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.66 | 15852 | 15852 | 0 | REPLACED RT-HEAD AND BOWL GASKET. RM PRESENT. NOTE: CIRC WITH THE ANNULAR CLOSED @ GPM:105, SPP: 2,680, RPM:0, SICP: 0 PSI. NOTE: REPLACE LEAKING OIL FITTING
BIGHORN PASS H06 BH | 12 | 2021-11-12 13:30 | 2021-11-12 14:30 | 1 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 9.7 | 15852 | 15852 | 0 | WASH AND REAM DUE TO TIGHT HOLE F/10,514' T/11,050', GPM-281, SPP-3700, RPM 50, TRQ 3-5K, SICP-0 PSI
BIGHORN PASS H06 BH | 12 | 2021-11-12 14:30 | 2021-11-12 15:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.74 | 15852 | 15852 | 0 | STRIP IN HOLE F/11,050' T/13,098',CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0
BIGHORN PASS H06 BH | 12 | 2021-11-12 15:30 | 2021-11-12 18:00 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.84 | 15852 | 15852 | 0 | WASH AND REAM DUE TO TIGHT HOLE F/13,098'-T/14,911', GPM-281, SPP-3850, RPM 50, TRQ 3-6K, SICP-0 PSI
BIGHORN PASS H06 BH | 12 | 2021-11-12 18:00 | 2021-11-12 19:30 | 1.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 9.91 | 14900 | 14900 | 0 | PICK UP T/14,870', ORIENTATE TOOL FACE @ 160L, BUILD TROUGH F/14,870' T/14,900' @ 160L, GPM-290, SPP-3,800/3,900 PSI, MRPM-197.2. CHOKES- 0% / 0% , MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 12 | 2021-11-12 19:30 | 2021-11-13 03:15 | 7.75 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 10.23 | 14900 | 14906 | 0.8 | BEGIN SIDETRACKING @ 14,900' MD / 10,384' TVD ON 11/12/2021 @ 19:30. TIME DRILL F/14,900'-T/14,906' TF-150L @ 1'/HR, WOB-1/30K, SPM-55/55, GPM-290, MRPM-197.2, SPP-3750/3820 PSI, DIFF-0/100 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: MOTOR STALLED OUT WITH A DIFF PRESSURE OF 2,981PSI & SPP OF 6,778 PSI. PULLED 30-50K OVER WITH NO SUCCESS. BLED OFF PRESSURE VIA 2'' ON FLOOR AND BEGAN WORKING STRING AGAIN. RESULT NO SUCCESS. APPLIED RPM TQ=22K AND WORKED STRING 30K OVER. RESULT NO SUCCESS. APPLIED 4,500 PSI TO SPP AND RPM TQ OF 22K WORKED STRING 30-35K OVER. STRING GAINED FREE MOVEMENT. ATTEMPTED TO CIRC WITH NO SUCCESS. STROKED STD UP TO ENSER NO RESTRICTIONS AND STILL UNABLE TO CIRC. HELD JRA AND PREPPED FLOOR FOR TRIP.
BIGHORN PASS H06 BH | 12 | 2021-11-13 03:15 | 2021-11-13 06:00 | 2.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.34 | 14906 | 14906 | 0 | STRIP OUT OF THE HOLE W/BHA #3 F/14,906'-T/9,774' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 75 PSI AVG CASING PRESSURE= 0 PSI HOLE CONDITIONS SLICK.
BIGHORN PASS H06 BH | 13 | 2021-11-13 06:00 | 2021-11-13 06:30 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 10.36 | 14906 | 14906 | 0 | @ 9,774', BULL HEAD 30 BBLS OF 17PPG KILL MUD DOWN BACKSIDE. @ GPM:133. INITIAL SICP: 0 PSI. MAX SICP: 512 PSI. FINAL SICP: 0 PSI.
BIGHORN PASS H06 BH | 13 | 2021-11-13 06:30 | 2021-11-13 09:45 | 3.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.5 | 14906 | 14906 | 0 | STRIP OUT OF THE HOLE W/BHA #4 F/9,774'-T/2,994' FILLING BACKSIDE WITH 12 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 150 PSI AVG CASING PRESSURE= 0 PSI HOLE CONDITIONS SLICK. NOTE: AFTER LAYING DOWN AGITATOR #2, ATTEMPTED TO CIRC THROUGH DRILL STRING. RESULT: NO SUCCESS.
BIGHORN PASS H06 BH | 13 | 2021-11-13 09:45 | 2021-11-13 10:30 | 0.75 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 10.53 | 14906 | 14906 | 0 | @ 2,994', BULL HEAD 60 BBLS OF 17.0 PPG KILL MUD DOWN BACKSIDE. INITIAL SICP: 0 PSI , MAX SICP: 336 PSI. FINAL SICP: 135 PSI. NOTE: SICP FELL TO 0 PSI ONCE THE PUMPS WERE SHUT DOWN. PUMP RATE: 133 GPM. CONDUCT FLOW CHECK= NO FLOW.
BIGHORN PASS H06 BH | 13 | 2021-11-13 10:30 | 2021-11-13 11:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.55 | 14906 | 14906 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. RIG MANAGER PRESENT. SICP: 0 PSI
BIGHORN PASS H06 BH | 13 | 2021-11-13 11:00 | 2021-11-13 12:15 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.6 | 14906 | 14906 | 0 | POOH W/BHA #4 F/2,994'-T/BHA FILLING BACKSIDE WITH 12 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. NOTE: @ 2,805' L/D AGITATOR. ONCE AGITATOR #1 WAS LAID DOWN, ATTEMPTED TO CIRC THROUGH DRILL STRING. RESULT: NO SUCCESS.
BIGHORN PASS H06 BH | 13 | 2021-11-13 12:15 | 2021-11-13 13:30 | 1.25 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.66 | 14906 | 14906 | 0 | RACK BACK BHA #4, REMOVE MWD. DRAIN AND BREAK BIT AND L/D SAME. PUMP 18 BBLS OF 12.0 PPG OBM TO TOP OFF WELL AND PERFORM FLOW CHECK BIT GRADE: 0-1-CT-N-X-1-BT-BHA MOTOR WAS PARTED AT EXTENSION SUB ON BOTTOM OF POWER SECTION
BIGHORN PASS H06 BH | 13 | 2021-11-13 13:30 | 2021-11-13 14:15 | 0.75 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 10.69 | 14906 | 14906 | 0 | P/U BHA #5. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13601237 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 -.001 .68 REV/GAL; 4.01' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, 33 STANDS DP, AGITATOR (BALL DROP). BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD= GOOD.
BIGHORN PASS H06 BH | 13 | 2021-11-13 14:15 | 2021-11-13 14:30 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.7 | 14906 | 14906 | 0 | TIH F/BHA T/848' WITH NO RETURNS DOWN FLOWLINE
BIGHORN PASS H06 BH | 13 | 2021-11-13 14:30 | 2021-11-13 15:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.72 | 14906 | 14906 | 0 | HOLE STARTED DISPLACING PIPE DISPLACEMENT; REMOVE TRIP NIPPLE/INSTALL ROT HEAD
BIGHORN PASS H06 BH | 13 | 2021-11-13 15:00 | 2021-11-13 19:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.89 | 14906 | 14906 | 0 | STRIP IN HOLE F/848' T/9,680'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0-100 PSI. NOTE: P/U #1 AGITATOR @ 2,808', BEFORE PSI=1,065, AFTER PSI=1,508, GPM-262, P/U #2 AGITATOR @ 5,948', BEFORE PSI=2,130, AFTER PSI=2,270, GPM-262
BIGHORN PASS H06 BH | 13 | 2021-11-13 19:00 | 2021-11-13 20:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.93 | 14906 | 14906 | 0 | SERVICE RIG. LUBE TD, ST-80 AND DRWKS RIG MANAGER PRESENT. SICP: 67 PSI
BIGHORN PASS H06 BH | 13 | 2021-11-13 20:00 | 2021-11-13 21:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.97 | 14906 | 14906 | 0 | STRIP IN HOLE F/9,680'-T/12,840'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0 PSI
BIGHORN PASS H06 BH | 13 | 2021-11-13 21:00 | 2021-11-13 22:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.03 | 14906 | 14906 | 0 | WASH AND REAM DUE TO TIGHT HOLE F/12,840'-T/13,810', GPM-281, SPP-3950, RPM 50, TRQ 10-14K, SICP: 140-230 PSI
BIGHORN PASS H06 BH | 13 | 2021-11-13 22:30 | 2021-11-13 23:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.05 | 14906 | 14906 | 0 | STRIP IN HOLE F/13,810'-T/14,890'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0-83 PSI
BIGHORN PASS H06 BH | 13 | 2021-11-13 23:00 | 2021-11-13 23:15 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.06 | 14906 | 14906 | 0 | WASH AND REAM DUE TO TIGHT HOLE F/14,890'-T/14,906', GPM-281, SPP-3950, RPM-0, TRQ-0, SICP: 0-605 PSI. NOTE: PUMP 50 BBLS OF 17 PPG KILL MUD DOWN THE BACKSIDE SIMULTANEOUSLY WITH WASH & REAM OPS, TO REDUCE CSG PRESSURE. (#1 MP, SPM: 15-20, KILL-LINE SPP: 578/469) INITIAL CSG PRESSURE: 303 PSI, FINAL CSG PRESSURE: 52 PSI.
BIGHORN PASS H06 BH | 13 | 2021-11-13 23:15 | 2021-11-14 06:00 | 6.75 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 11.34 | 14906 | 14916 | 1.5 | CONT. SIDETRACKING/TIME DRILL F/14,906'-T/14,910' TF-140L @ 1'/HR, F/14,910'-T/14,916' TF-130 @ 2'/HR. WOB-1/30K, SPM-55/55, GPM-290, MRPM-197.2, SPP-3750/3950 PSI, DIFF-0/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 150 PSI, AVG CASING PRESSURE= 40 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: @ 14,909' PUMP 20 BBLS OF 17 PPG KILL MUD SIMULTANEOUSLY W/DRILLING OPS, DOWN BACKSIDE TO REDUCE CSG PRESSURE. INITIAL SICP: 134 PSI, FINAL: 50 PSI. MAX SICP WHILE PUMPING: 430 PSI. KILL LINE SPP: 438/307.
BIGHORN PASS H06 BH | 14 | 2021-11-14 06:00 | 2021-11-14 12:00 | 6 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 11.59 | 14916 | 14938 | 3.7 | CONT. SIDETRACKING/TIME DRILL F/14,916'-T/14,920' TF-130 @ 5'/HR. F/14,920'-T/14,930' TF-90L @ 5'/HR, F/14,930'-T/14,938' TF-60L @ 8'/HR, WOB-1/30K, SPM-70/70, GPM-367, MRPM-249.56, SPP-4550/4760 PSI, DIFF-0/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 180 PSI, AVG CASING PRESSURE= 0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: WORK PIPE OUT OF SIDETRACK DUE TO STACKING WEIGHT, ORIENTATE TOOL AND WORK BACK IN TO SIDETRACK @ 14,916' NOTE: @ 14,916' PUMP 20 BBLS OF 17 PPG KILL MUD SIMULTANEOUSLY W/DRILLING OPS, DOWN BACKSIDE TO REDUCE CSG PRESSURE. INITIAL SICP: 93 PSI, FINAL: 0 PSI. MAX SICP WHILE PUMPING: 618 PSI. KILL LINE SPP: 593/481.
BIGHORN PASS H06 BH | 14 | 2021-11-14 12:00 | 2021-11-14 22:00 | 10 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.01 | 14938 | 15615 | 67.7 | ROTATE DRILL LATERAL (677' IN 9.92 HR @ 68.24 FPH) WOB-20/30K, SPM-70/70, GPM-367, RPM 30/50, TQ-13K/15K, MRPM-250, TTRPM-280/300, SPP- 4200/5000 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 526 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=132 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 14 | 2021-11-14 22:00 | 2021-11-15 00:15 | 2.25 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.1 | 15615 | 15668 | 23.6 | SLD DRILL LATERAL (53' IN 2.33 HRS @ 22.74 FPH) WOB-15/25K, SPM-70/70, GPM-367, MRPM-250, SPP -4200/4780 PSI, DIFF-350/450 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=526 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=132 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/15,115'-T/15,123' 8' TF:HS, 16:04-16:32 F/15,303'-15,318', 15', TF:90R, 18:58-19:30 F/15,491'-15,506', 15', TF:140R, 21:21-22:06 F/15,585'-15,600', 15', TF:140R, 22:55-23:30
BIGHORN PASS H06 BH | 14 | 2021-11-15 00:15 | 2021-11-15 01:15 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.15 | 15668 | 15668 | 0 | SERVICE RIG. LUBE TD, ST-80 AND DRWKS RIG MANAGER PRESENT NOTE: DUE TO CSG PRESSURE FROM THE FRACTURE @15,632', PUMP 43 BBLS OF 17PPG KILL MUD DOWN KILL-LINE TO REDUCE CSG PRESSURE. INITIAL SICP: 138 PSI, MAX SICP: 526 PSI, FINAL SICP: 208 PSI. KILLED PUMPS AND SICP FELL TO 0 PSI. NOTE: WHILE PUMPING KILL MUD, NOTICED TOP (ODS) RAM DOOR LEAKING A SMALL AMOUNT. DECISION WAS MADE TO CONTINUE PUMPING KILL MUD TO BULL HEAD PRESSURE AWAY. ONCE FINISHED PUMPING, CREWS TIGHTENED BOTH TOP & BTM RAM DOOR BOLTS.
BIGHORN PASS H06 BH | 14 | 2021-11-15 01:15 | 2021-11-15 02:45 | 1.5 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.21 | 15668 | 15817 | 99.3 | ROTATE DRILL LATERAL (149' IN 1.58 HR @ 94.3 FPH) WOB-20/30K, SPM-70/70, GPM-367, RPM 30/50, TQ-13K/15K, MRPM-250, TTRPM-280/300, SPP- 4200/5000 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 14 | 2021-11-15 02:45 | 2021-11-15 04:15 | 1.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.27 | 15817 | 15852 | 23.3 | SLD DRILL LATERAL (35' IN 1.43 HRS @ 24.47 FPH) WOB-15/25K, SPM-70/70, GPM-367, MRPM-250, SPP-4200/4780 PSI, DIFF-350/450 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/15,768'-T/15,788', 20' TF:90R, 02:20-02:55 F/15,820'-T/15,835', 15', TF:90R, 03:13-04:04 F/15,867'-T/15,887', 20', TF:90R, 04:50-06:00
BIGHORN PASS H06 BH | 14 | 2021-11-15 04:15 | 2021-11-15 04:45 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.29 | 15852 | 15867 | 30 | ROTATE DRILL LATERAL (15' IN 0.57 HR @ 26.31 FPH) WOB-20/30K, SPM-70/70, GPM-367, RPM 30/50, TQ-13K/15K, MRPM-250, TTRPM-280/300, SPP- 4200/5000 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 14 | 2021-11-15 04:45 | 2021-11-15 06:00 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.34 | 15867 | 15887 | 16 | SLD DRILL LATERAL (20' IN 1.17 HRS @ 17.09 FPH) WOB-15/25K, SPM-70/70, GPM-367, MRPM-250, SPP-4200/4580 PSI, DIFF-100/350 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/15,867'-T/15,887', 20', TF:90R, 04:50-06:00
BIGHORN PASS H06 BH | 15 | 2021-11-15 06:00 | 2021-11-15 12:30 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.61 | 15887 | 16396 | 78.3 | ROTATE DRILL LATERAL (509' IN 6.6 HR @ 77 FPH) WOB-20/32K, SPM-70/70, GPM-367, RPM 60, TQ-15K/21K, MRPM-250, TTRPM-320, SPP- 4200/5300 PSI, DIFF 600/800 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 15 | 2021-11-15 12:30 | 2021-11-15 15:45 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.75 | 16396 | 16460 | 19.7 | SLD DRILL LATERAL (64' IN 3.15 HRS @ 20 FPH) WOB-18/28K, SPM-70/70, GPM-367, MRPM-250, SPP-4400/4700 PSI, DIFF-100/300 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/15,957'-T/15,972', 15', TF:90R, 06:21-07:02 F/16,146'-T/16,168', 22', TF:90R, 09:15-10:08 F/16,238'-T/16,250', 12', TF:90R, 11:00-11:32 F/16,425'-T/16,440', 15', TF:140R, 14:01-15:04
BIGHORN PASS H06 BH | 15 | 2021-11-15 15:45 | 2021-11-15 17:30 | 1.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.82 | 16460 | 16460 | 0 | CIRCULATE 3 BTM'S UP CALCULATED FROM 16,460' TO CASING SHOE @ 9,774', SPP-5100, GPM-400, RPM-70, TRQ-10-12K WHILE WORKING STAND
BIGHORN PASS H06 BH | 15 | 2021-11-15 17:30 | 2021-11-15 19:45 | 2.25 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 12.92 | 16460 | 16460 | 0 | BACKREAM OUT OF HOLE F/16,460' T/14,938', SPP-800, GPM-300, RPM-60, TRQ-156-17K. BACKREAM UNDER MUD CAP. NOTE: @ 14,938' ORIENATE TOOL TO 140L AND PULL THROUGH SIDETRACK F/14,938'-14,888'. NO ISSUES PULLING THROUGH S.T.
BIGHORN PASS H06 BH | 15 | 2021-11-15 19:45 | 2021-11-15 22:15 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.02 | 16460 | 16460 | 0 | STRIP OUT OF THE HOLE W/BHA #5 F/14,888'-T/9,774' FILLING BACKSIDE WITH 12 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. SICP: 0 PSI. HOLE CONDITIONS= SLICK
BIGHORN PASS H06 BH | 15 | 2021-11-15 22:15 | 2021-11-15 22:45 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 13.04 | 16460 | 16460 | 0 | @ 9,774', BULL HEAD 30 BBLS OF 17PPG KILL MUD DOWN BACKSIDE. @ GPM:133. INITIAL SICP: 0 PSI. MAX SICP: 0 PSI. FINAL SICP: 0 PSI, KILL-LINE SPP: 252 PSI
BIGHORN PASS H06 BH | 15 | 2021-11-15 22:45 | 2021-11-16 01:15 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.15 | 16460 | 16460 | 0 | STRIP OUT OF THE HOLE W/BHA #5 F/9,774'-T/2,808' FILLING BACKSIDE WITH 12 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. SICP: 0 PSI. HOLE CONDITIONS=SLICK NOTE: L/D AGITATOR #2 @ 5,948'.
BIGHORN PASS H06 BH | 15 | 2021-11-16 01:15 | 2021-11-16 01:45 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 13.17 | 16460 | 16460 | 0 | @ 2,808', BULL HEAD 50 BBLS OF 17PPG KILL MUD DOWN BACKSIDE. @ GPM:133. INITIAL SICP: 0 PSI. MAX SICP: 0 PSI. FINAL SICP: 0 PSI, KILL-LINE SPP:190 PSI
BIGHORN PASS H06 BH | 15 | 2021-11-16 01:45 | 2021-11-16 02:15 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 13.19 | 16460 | 16460 | 0 | REMOVE RT-HEAD AND L/D AGITATOR#1.
BIGHORN PASS H06 BH | 15 | 2021-11-16 02:15 | 2021-11-16 03:15 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.23 | 16460 | 16460 | 0 | STRIP OUT OF THE HOLE W/BHA #5 F/2,808'-T/BHA' FILLING BACKSIDE WITH 12 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. SICP: 0 PSI. NOTE: MUD BUCKET RETURNS DIVERTED TO THE TRIP TANK.
BIGHORN PASS H06 BH | 15 | 2021-11-16 03:15 | 2021-11-16 03:45 | 0.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.25 | 16460 | 16460 | 0 | RACK BACK BHA #5, REMOVE MWD. DRAIN AND BREAK BIT AND L/D SAME. BIT GRADE: 3-4-CT-S-3-1-BT-PR MOTOR: MOTOR DRAINED WELL AND HAD MINIMAL SLACK NOTE: FLOW CHECK WAS PERFORMED PRIOR TO BHA ENTERING BOP. RESULT: NO FLOW.
BIGHORN PASS H06 BH | 15 | 2021-11-16 03:45 | 2021-11-16 05:30 | 1.75 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.32 | 16460 | 16460 | 0 | SERVICE RIG AND C/O SAVER SUB. RIG MANAGER PRESENT SICP: 0 PSI
BIGHORN PASS H06 BH | 15 | 2021-11-16 05:30 | 2021-11-16 06:00 | 0.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 13.34 | 16460 | 16460 | 0 | P/U BHA #6. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13635755 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 .003 .68 REV/GAL; 4.11' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, 33 STANDS DP, AGITATOR (BALL DROP). BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD= GOOD.
BIGHORN PASS H06 BH | 16 | 2021-11-16 06:00 | 2021-11-16 07:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.41 | 16460 | 16460 | 0 | CONT. P/U BHA #6. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13635755 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 .003 .68 REV/GAL; 4.11' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, 33 STANDS DP, AGITATOR (BALL DROP). BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD= GOOD. (GPM: 157, SPP: 333 PSI, RPM: 50, TQ: 1K) NOTE: AFTER TESTING MWD, RACKED BACK BHA TO INSPECT BIT. RESULT: BIT WAS DAMAGED GRADED: 0-1-CT-G-1-1-BHA. CONTACTED MANAGMENT.
BIGHORN PASS H06 BH | 16 | 2021-11-16 07:30 | 2021-11-16 08:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.43 | 16460 | 16460 | 0 | SERVIE RIG. LUBE: TD, ST-80 AND DRWKS RIG MANAGER PRESENT. SICP: 0 PSI
BIGHORN PASS H06 BH | 16 | 2021-11-16 08:00 | 2021-11-16 08:45 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.46 | 16460 | 16460 | 0 | P/U BHA #7. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13673682 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 .003 .68 REV/GAL; 4.11' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, 33 STANDS DP, AGITATOR (BALL DROP). BIT TO SVY-65'. BIT TO GAMMA-56'.
BIGHORN PASS H06 BH | 16 | 2021-11-16 08:45 | 2021-11-16 09:15 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.48 | 16460 | 16460 | 0 | TIH F/BHA T/2,280' WITH NO RETURNS DOWN FLOWLINE NOTE: @ 2,280' STARTED GETTING RETURNS.
BIGHORN PASS H06 BH | 16 | 2021-11-16 09:15 | 2021-11-16 09:45 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 13.5 | 16460 | 16460 | 0 | INSTALL RT-HEAD. RIG MANAGER PRESENT
BIGHORN PASS H06 BH | 16 | 2021-11-16 09:45 | 2021-11-16 13:00 | 3.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.64 | 16460 | 16460 | 0 | STRIP IN THE HOLE W/ BHA #7 F/2,280'-T/9,727'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0. NOTE: P/U AGITATOR #1 @ 2,808' P/U "ON DEMAND" AGITATOR @ 5,948'. DID NOT PUMP THROUGH EITHER TOOLS AS PER INSTRUCTION.
BIGHORN PASS H06 BH | 16 | 2021-11-16 13:00 | 2021-11-16 14:30 | 1.5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 13.7 | 16460 | 16460 | 0 | SLIP AND CUT 60' OF DRILLING LINE. RIG MANAGER PRESENT. SICP: 0 PSI
BIGHORN PASS H06 BH | 16 | 2021-11-16 14:30 | 2021-11-16 19:00 | 4.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.89 | 16460 | 16460 | 0 | STRIP IN THE HOLE W/ BHA #7 F/9,727'-T/14,928'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0-234 PSI. NOTE: @ 14,880' ORIENATE TOOL AND ENTER SIDETRACK
BIGHORN PASS H06 BH | 16 | 2021-11-16 19:00 | 2021-11-16 20:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.95 | 16460 | 16460 | 0 | WASH AND REAM DUE TO TIGHT HOLE F/14,928'-T/16,460', GPM-281, SPP-4,050, RPM-60, TRQ-16/21, SICP: 0-514 PSI.
BIGHORN PASS H06 BH | 16 | 2021-11-16 20:30 | 2021-11-17 02:15 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.19 | 16460 | 17204 | 129.4 | ROTATE DRILL LATERAL (744' IN 5.82 HR @ 127.83 FPH) WOB-20/32K, SPM-70/70, GPM-367, RPM 70, TQ-14K/16K, MRPM-250, TTRPM-320, SPP- 4200/4950 PSI, DIFF 600/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 527 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 16 | 2021-11-17 02:15 | 2021-11-17 04:30 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.28 | 17204 | 17269 | 28.9 | SLD DRILL LATERAL (65' IN 2.18 HRS @ 29.81 FPH) WOB-20/26K, SPM-70/70, GPM-367, MRPM-250, SPP-4400/4800 PSI, DIFF-300/450 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/16,617'-T/16,637', 20', TF:150R, 21:50-22:30 F/16,712'-T/16,732', 20', TF:150R, 23:06-23:36 F/16,810'-T/16,820', 10', TF:180, 00:14-00:44 F/17,188'-T/17,203', 15', TF:110R, 03:18-03:49
BIGHORN PASS H06 BH | 16 | 2021-11-17 04:30 | 2021-11-17 05:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 14.3 | 17269 | 17269 | 0 | SERVICE RIG. LUBE TD RIG MANAGER PRESENT SICP: 0 PSI
BIGHORN PASS H06 BH | 16 | 2021-11-17 05:00 | 2021-11-17 06:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.34 | 17269 | 17393 | 124 | ROTATE DRILL LATERAL (124' IN 1 HR @ 124 FPH) WOB-20/32K, SPM-70/70, GPM-367, RPM 70, TQ-14K/16K, MRPM-250, TTRPM-320, SPP- 4200/4950 PSI, DIFF 600/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PASS H06 BH | 17 | 2021-11-17 06:00 | 2021-11-17 13:15 | 7.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.65 | 17393 | 18228 | 115.2 | ROTATE DRILL LATERAL (835' IN 7.22 HR @ 116 FPH) WOB-20/32K, SPM-71/71, GPM-372, RPM 70, TQ-14K/18K, MRPM-253, TTRPM-323, SPP- 4600/5200 PSI, DIFF 600/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 3 GALS/HR PHPA.
BIGHORN PASS H06 BH | 17 | 2021-11-17 13:15 | 2021-11-17 16:30 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.78 | 18228 | 18302 | 22.8 | SLD DRILL LATERAL (74' IN 3.28 HRS @ 23 FPH) WOB-20/26K, SPM-70/70, GPM-372, MRPM-253, SPP-4600/5000 PSI, DIFF-300/600 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=83 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 3 GALS/HR PHPA SLIDE DEPTHS: F/17,465'-T/17,480', 15', TF:130R, 06:31-06:55 F/17,559'-T/17,571', 12', TF:160R, 07:37-07:59 F/17,653'-T/17,661', 8', TF:180, 08:57-09:22 F/18,029'-T/18,044', 15', TF:160R, 12:08-12:49 F/18,124'-T/18,134', 10', TF:165R, 13:30-14:10 F/18,232'-T/18,246', 14', TF:180, 15:12-15:57 NOTE: PUMP 10 BBLS OF 17.0 PPG KILL MUD DOWN BACKSIDE @ 18,247'
BIGHORN PASS H06 BH | 17 | 2021-11-17 16:30 | 2021-11-17 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 14.8 | 18302 | 18302 | 0 | SERVICE RIG: REPAIR HYDRAULIC LEAK ON HPU
BIGHORN PASS H06 BH | 17 | 2021-11-17 17:00 | 2021-11-18 01:00 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.14 | 18302 | 19283 | 122.6 | ROTATE DRILL LATERAL (981' IN 7.60 HR @ 129.07 FPH) WOB-20/32K, SPM-70/70, GPM-367, RPM 70, TQ-14K/16K, MRPM-250, TTRPM-320, SPP- 4600/5350 PSI, DIFF 600/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 306 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: @ 19,063' PUMP 15BBLS OF 17 PPG OBM DOWN BACKSIDE VIA KILL-LINE TO REDUCE CSG PRESSURE. INITIAL CSG PRESSURE: 72 PSI, MAX CSG PRESSURE: 306, FINAL SICP: 0 PSI. PUMP RATE: 15 SPM, KILL-LINE SPP: 233 PSI. RELOG F/18,689'-18,709' DUE TO INCORRECT GAMMA COUNT.
BIGHORN PASS H06 BH | 17 | 2021-11-18 01:00 | 2021-11-18 03:30 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.24 | 19283 | 19363 | 32 | SLD DRILL LATERAL (80' IN 2.47HRS @ 32.38 FPH) WOB-20/26K, SPM-70/70, GPM-367, MRPM-250, SPP-4400/4920 PSI, DIFF-300/450 PSI, CHOKES-0%/0%, MAX CASING PRESSURE=306 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA SLIDE DEPTHS: F/18,506'-T/18,526', 20', TF:150R, 18:30-19:11 F/18,689'-T/18,709', 20', TF:180, 20:44-21:25 F/18,878'-T/18,898', 20', TF:180, 22:48-23:23 F/19,153'-T/19,173', 20', TF:180, 01:33-02:04
BIGHORN PASS H06 BH | 17 | 2021-11-18 03:30 | 2021-11-18 03:30 | 0 | P | PRDHLCSG | MSTN | TD | MILESTONE_TD WELL | 15.24 | 19363 | 19363 |  | MILESTONE_TD WELL ON 11/18/2021 @ 03:24 HRS
BIGHORN PASS H06 BH | 17 | 2021-11-18 03:30 | 2021-11-18 06:00 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.34 | 19363 | 19363 | 0 | PERFORMED POST TD CLEAN UP CYCLE WITH WELL ON MUD CAP. CIRCULATE 5 BOTTOMS UP TO CSG SHOE. SPM-75/75, GPM-393, MRPM-267.24, RPM-70, TTRPM-337.24. CHOKES 0%/0%. MAX CSG PSI WHILE CIRC-0 PSI. TQ=13/19K, SPP-4800/5369 PSI. INITIAL: P/U WT=310K, S/O WT=160K, ROT WT=172K, SPP= 5,369, TQ=19K FINAL: P/U WT=310K, S/O WT=163K, ROT WT=180K, SPP=5,030, TQ=13/16K
BIGHORN PASS H06 BH | 18 | 2021-11-18 06:00 | 2021-11-18 12:15 | 6.25 | P | PRDHLCSG | TRIP | RMHO | TRIP FOR WASH / REAM OPERATIONS | 15.6 | 19363 | 19363 | 0 | BACK REAM OUT THE HOLE F/19,363' T/14,942’. GPM-393, RPM-70, MRPM-267, TMRPM-337, TRQ-13/21K, SPP-4500/4950 PSI. CHOKES 0%/0%. MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX CASING PRESSURE ON CONNECTIONS= 0 PSI, AVG CASING PRESSURE ON CONNECTIONS= 0 PSI
BIGHORN PASS H06 BH | 18 | 2021-11-18 12:15 | 2021-11-18 15:45 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.75 | 19363 | 19363 | 0 | STRIP THROUGH SIDETRACK, STRIP OUT THE HOLE F/14,942' T/9,727' PUMPING 1.9 BBLS/STD OF 12.0 PPG OBM CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 80 PSI NOTE: PUMP 30 BBLS OF 17.0 PPG MUD DOWN THE ANNULUS AT 9,727'. SPM:35, KILL-LINE SPP:450 PSI INITIAL CSG PRESSURE=350 PSI MAX CSG PRESSURE=350 PSI FINAL CSG PRESSURE=0 PSI
BIGHORN PASS H06 BH | 18 | 2021-11-18 15:45 | 2021-11-18 16:30 | 0.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 15.78 | 19363 | 19363 | 0 | STRIP OUT OF THE HOLE (L/D DP) F/9,727'-T/9,366' PUMPING 1.9 BBLS/STD OF 12.0 PPG OBM CALCULATED FILL DOWN THE ANNULUS. MAX CSG PSI=0, AVG CSG PSI=0
BIGHORN PASS H06 BH | 18 | 2021-11-18 16:30 | 2021-11-18 17:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.8 | 19363 | 19363 | 0 | SERVICE RIG HPU. SICP=0
BIGHORN PASS H06 BH | 18 | 2021-11-18 17:00 | 2021-11-18 23:15 | 6.25 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.06 | 19363 | 19363 | 0 | STRIP OUT OF THE HOLE (L/D DP) F/9,366'-T/3,000' PUMPING 1.9 BBLS/STD OF 12.0 PPG OBM CALCULATED FILL DOWN THE ANNULUS. MAX CSG PSI=0, AVG CSG PSI=0 NOTE: @ 5,948' L/D "ON DEMAND" AGITATOR.
BIGHORN PASS H06 BH | 18 | 2021-11-18 23:15 | 2021-11-19 02:00 | 2.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.18 | 19363 | 19363 | 0 | STRIP IN THE HOLE (WITH PIPE THAT WAS PREVIOUSLY RACKED BACK) F/3,000'-T/9,700'. HOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0 PSI.
BIGHORN PASS H06 BH | 18 | 2021-11-19 02:00 | 2021-11-19 06:00 | 4 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.34 | 19363 | 19363 | 0 | STRIP OUT OF THE HOLE (L/D DP) F/9,700'-T/4,800' PUMPING 1.9 BBLS/STD OF 12.0 PPG OBM CALCULATED FILL DOWN THE ANNULUS. MAX CSG PSI=154, AVG CSG PSI=0 NOTE: @ 9,288' PUMP 20 BBLS OF 17.0 PPG MUD DOWN THE ANNULUS. SPM:15, KILL-LINE SPP:175 PSI INITIAL CSG PRESSURE=0 PSI MAX CSG PRESSURE=154 PSI FINAL CSG PRESSURE=0 PSI
BIGHORN PASS H06 BH | 19 | 2021-11-19 06:00 | 2021-11-19 07:00 | 1 | U | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.39 | 19363 | 19363 | 0 | STRIP OUT OF THE HOLE (L/D DP) F/4,800'-T/4,376' PUMPING 1.9 BBLS/STD OF 12.0 PPG OBM CALCULATED FILL DOWN THE ANNULUS. MAX CSG PSI=0, AVG CSG PSI=0
BIGHORN PASS H06 BH | 19 | 2021-11-19 07:00 | 2021-11-19 08:00 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 16.43 | 19363 | 19363 | 0 | SERVICE RIG- CHANGE OUT ST-80 UPPER AND LOWER DIES. SICP: 0 PSI RIG MANAGER PRESENT
BIGHORN PASS H06 BH | 19 | 2021-11-19 08:00 | 2021-11-19 08:45 | 0.75 | U | PRDHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 16.46 | 19363 | 19363 | 0 | REPAIR ST-80- CHANGE OUT BOTH UPPER AND LOWER DIES AS WELL AS RETAINER BOLTS. SICP: 0 PSI RIG MANAGER PRESENT.
BIGHORN PASS H06 BH | 19 | 2021-11-19 08:45 | 2021-11-19 09:30 | 0.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.49 | 19363 | 19363 | 0 | STRIP OUT OF THE HOLE (L/D DP) F/4,376'-T/3,368' PUMPING 1.9 BBLS/STD OF 12.0 PPG OBM CALCULATED FILL DOWN THE ANNULUS. MAX CSG PSI=0, AVG CSG PSI=0
BIGHORN PASS H06 BH | 19 | 2021-11-19 09:30 | 2021-11-19 10:30 | 1 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.53 | 19363 | 19363 | 0 | STRIP IN THE HOLE (WITH PIPE THAT WAS PREVIOUSLY RACKED BACK) F/3,368'-T/6,400'. CHOKE POSITION: 0%/0% (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0 PSI.
BIGHORN PASS H06 BH | 19 | 2021-11-19 18:00 | 2021-11-19 19:00 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 16.89 | 19363 | 19363 | 0 | L/D DRILL-N-REAMER, X/O, TOMAX THRUSTER,TOP NMDC. PULL MWD, DRAIN MOTOR, BREAK BIT AND L/D REMAINING BHA. SICP: 0 PSI NOTE: MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG. BIT GRADED: 1-2-BT-S-1-2-CT-TD.
BIGHORN PASS H06 BH | 19 | 2021-11-19 19:00 | 2021-11-19 20:00 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 16.93 | 19363 | 19363 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4 1/2" ELEVATORS NOTE: INSTALL TEST PLUG AND TEST UPPER AND LOWER PIPE RAM DOOR SEALS TO 1,500 PSI. RESULT: SUCCESS
BIGHORN PASS H06 BH | 19 | 2021-11-19 20:00 | 2021-11-19 21:30 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.99 | 19363 | 19363 | 0 | HOLD PJSM. R/U FRANKS CSG CREW AND CRT. SICP: 0 PSI
BIGHORN PASS H06 BH | 19 | 2021-11-19 21:30 | 2021-11-20 06:00 | 8.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.34 | 19363 | 19363 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/7,050', FILLING PIPE ON THE FLY WITH FRESH WATER. (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) MAX CSG PRESSURE: 0 PSI, SICP:0 PSI. NOTE: INSTALL RT-HEAD @ 2,030' NOTE: TOPPED CSG OFF W/FW @ 4,000'
BIGHORN PASS H06 BH | 20 | 2021-11-20 06:00 | 2021-11-20 09:00 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.47 | 19363 | 19363 | 0 | RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/7,050'-T/10,318', FILLING PIPE ON THE FLY WITH FRESH WATER. (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) MAX CSG PRESSURE: 0 PSI, SICP:0 PSI.
BIGHORN PASS H06 BH | 20 | 2021-11-20 09:00 | 2021-11-20 10:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 17.51 | 19363 | 19363 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP: 0 PSI.
BIGHORN PASS H06 BH | 20 | 2021-11-20 10:00 | 2021-11-20 16:00 | 6 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.76 | 19363 | 19363 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/10,318'-T/17,940' FILLING PIPE ON THE FLY WITH FRESH WATER. (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) MAX CSG PRESSURE: 0 PSI, SICP:0 PSI.
BIGHORN PASS H06 BH | 20 | 2021-11-20 16:00 | 2021-11-20 17:30 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.82 | 19363 | 19363 | 0 | WASHING & REAMING PRODUCTION CASING F/17,940' T/18,470' @ 20-30 FPM WITH WATER AND WITH CRT @ 25 RPM, TRQ-8/12K, SPM-60, SPP-2500 PSI P/U AND RUN CASING F/18,470' T/19,285'; NO RETURNS, CHOKE POSITION: 0%/0%. MAX CSG PRESSURE:0, SICP:0
BIGHORN PASS H06 BH | 20 | 2021-11-20 17:30 | 2021-11-20 18:15 | 0.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.85 | 19363 | 19363 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND RUN LANDING JOINT F/19,285'-T/19,353'. LAND CASING ON HANGER W/140K (W/O BLOCKS) RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, RAN 10,197.89' (231 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1-X-OVER, 2,222' (51 JTS) OF 5 1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, RAN 6,698.9' (152 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, 1 PUP JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, 1 JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, HANGER AND LANDING JT. FOR TOTAL OF 437 FULL JTS OF 5'' 18# P-110 ICY WEDGE & 5 1/2" 23# P-110 ICY WEDGE 463. CASING SHOE @ 19,353.0' TOP OF FLOAT COLLAR @ 19,303.5' BOTTOM OF TOE SLEEVE VALVE @ 19,257.2' TOP OF TOE SLEEVE VALVE @ 19,232.1' TOP OF X-OVER @ 9,034.2' TOP OF MARKER JOINT ABOVE X-OVER @ 6,792.6' 12 JOINTS 5" LEFT OUT- 531.14' 13 JOINTS 5 1/2" LEFT OUT-574.42' NOTE: TOP OF THE 5.5'' MARKER JOINT IS @ 6,792.6'. PLACEMENT CALCULATES TO BE 2,397' ABOVE KICK OFF POINT
BIGHORN PASS H06 BH | 20 | 2021-11-20 18:15 | 2021-11-20 19:30 | 1.25 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 17.91 | 19363 | 19363 | 0 | RIGGING DOWN FRANK'S CRT AND INSTALLING WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE, MONITOR SICP, SICP= 0 PSI. NOTE: CIRC VIA CRT WHILE CREW R/D FLOOR EQUIPMENT. ONCE ALL FLOOR EQUIPMENT WAS R/D, SHUT PUMPS DOWN AND R/D CRT. BPM: 8, SPP: 2,150.
BIGHORN PASS H06 BH | 20 | 2021-11-20 19:30 | 2021-11-20 20:15 | 0.75 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.94 | 19363 | 19363 | 0 | CONT. CIRCULATE 1 CASING CAPACITY WITH CHOKES CLOSED WHILE CONTINUEING TO RIG DOWN CASING TOOLS & R/U CMT CREW, BPM:6.5, SPP-3,190 PSI. INITIAL CASING PRESSURE WHILE CIRCULATING= 0 PSI AND FINAL CASING PRESSURE WHILE CIRCULATING= 0 PSI, SHUT IN CASING PRESSURE=0 PSI. HOLD PJSM WITH NINE CEMENT CREW NOTE: TOP PIPE RAMS CLOSED
BIGHORN PASS H06 BH | 20 | 2021-11-20 20:15 | 2021-11-21 01:00 | 4.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 18.14 | 19363 | 19363 | 0 | SWAP CIRCULATING IRON T/CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 1ST STAGE 5/5-1/2" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 40 BBL 10.5 PPG WEIGHTED SPACER, 316 BBL 13.5 PPG 1030 SK 1.72 YIELD 35/65 POZ-CLASS H LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 373 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 8 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 3,200 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4,200 PSI, HELD FOR 5 MIN, BLED BACK 5.5 BBLS. FLOATS HELD. PLUG DOWN @ 00:49 ON 11/21/2021. MAX CSG PSI= 174 PSI, AVG CASING PSI=0 PSI, CSG PRESSURE 142 PSI WITH PUMPS OFF AFTER CEMENTING. NOTE: GAINED CSG PRESSURE @ 320 BBLS INTO DISPLACMENT, CSG PRESSURE: 40 PSI.
BIGHORN PASS H06 BH | 20 | 2021-11-21 01:00 | 2021-11-21 01:45 | 0.75 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 18.17 | 19363 | 19363 | 0 | HELD PJSM, RIG DOWN CIRCULATING IRON FROM RIG FLOOR. NOTE: WHILE R/D CIRC IRON FROM RIG FLOOR, LINED UP TO PUMP 17PPG KILL MUD DOWN BACKSIDE VIA KILL-LINE TO EST INJECTION RATE. 1 BPM= 835 PSI & CASING PSI= 793 PSI 2 BPM= 1,254 PSI & CASING PSI= 1,167 PSI 2.5 BPM= 1,757 PSI & CASING PSI= 1,639 PSI 4 BPM= 2,701 PSI & CASING PSI= 2,500 PSI 5 BPM= 3,051 PSI & CASING PSI= 2,743 PSI INITIAL CSG PSI= 142 PSI. FINAL CSG PSI=2,436 ONCE PUMPS WERE SHUT DOWN, SICP FELL TO 0 PSI. TTL BBLS OF 17 PPG PUMPED= 150 BBLS TOP PIPE RAMS CLOSED
BIGHORN PASS H06 BH | 20 | 2021-11-21 01:45 | 2021-11-21 02:00 | 0.25 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 18.18 | 19363 | 19363 | 0 | REMOVED CHECK VALVE AND KILL-LINE. R/U CMT LINES TO MUDCROSS. HELD PJSM IN REGARDS TO 2ND STAGE CMT OPS. SICP: 0 PSI.
BIGHORN PASS H06 BH | 20 | 2021-11-21 02:00 | 2021-11-21 04:45 | 2.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 18.29 | 19363 | 19363 | 0 | PUMP 40 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 337 BBLS 1100 SK 1.72 YIELD 35/65 POZ-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.33 YIELD TYPE I/II 14.8 PPG TAIL CEMENT, FOLLOWED BY 15 BBLS WATER. MAX CSG PSI= 1,960 PSI W/20 BBLS LEAD CMT PUMPED @ 5 BPM, AVG CASING PSI= 1,420/1,830 PSI, CSG PRESSURE FELL TO 0 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC: 909' NOTE: TOP PIPE RAMS CLOSED
BIGHORN PASS H06 BH | 20 | 2021-11-21 04:45 | 2021-11-21 06:00 | 1.25 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 18.34 | 19363 | 19363 | 0 | R/D CEMENT EQPT AND MONITOR WELL. CMT HEAD LEFT ON BUT IN THE OPEN POSITION. INITIAL SICP: 0 PSI FINAL SICP: 0 PSI. NOTE: TRANSFERRING MUD FROM PITS, LEAVING 130 BBLS OF 17 PPG KILL MUD IN TANK 7.
BIGHORN PASS H06 BH | 21 | 2021-11-21 06:00 | 2021-11-21 06:30 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 18.36 | 19363 | 19363 | 0 | R/D CEMENT HEAD & EQPT, WHILE MONITOR WELL. INITIAL SICP: 0 PSI FINAL SICP: 0 PSI.
BIGHORN PASS H06 BH | 21 | 2021-11-21 06:30 | 2021-11-21 10:30 | 4 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 18.53 | 19363 | 19363 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE FOSV AND LAY DOWN LANDING JOINT. REMOVE BAILS AND CASING ELEVATORS, AND RIG UP RIG 4.5" ELEVATORS, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 80 GPM W/100 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10K PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
BIGHORN PASS H06 BH | 21 | 2021-11-21 10:30 | 2021-11-21 19:00 | 8.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 18.89 | 19363 | 19363 | 0 | REMOVE TOP AND BTM VBR PIPE RAM BLOCKS AND BLIND RAM BLOCKS. BREAK ALL BOLTS ON EACH SECTION OF BOP BETWEEN THE ANNULAR/TOP PIPE RAMS/BTM PIPE RAMS. INSTALL WRANGLER ONTO BOP, REMOVE HCR LINE, KILL-LINE, KILL LINE CHECK VALVE, HYDRAULIC LINES, HOLE FILL, AIR LINES/HYDRAULIC LINES FROM ROTATING HEAD, REMOVE TURNBUCKLES, BACK OUT WH SET SCREWS AND RAISE BOP'S, INSTALL WELLHEAD CAP AND TESTED T/5,000 PSI. SECURE WELL. NOTE: ADDITIONAL TIME ADDED TO NIPPLE DOWN BOPE 6 HRS NOTE: START CLEANING MUD TANKS @ 10:00.
BIGHORN PASS H06 BH | 21 | 2021-11-21 19:00 | 2021-11-22 | 5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 19.09 | 19363 | 19363 | 0 | LAY OVER AND SECURE BOP’S. CLEAN MUD TANKS, R/D AND REMOVE ELEVATORS AND BALES, PIN TOP DRIVE, PIN TOP DRIVE TO TRACK, REMOVE V-DOOR. INSTALL BOOSTER CYCLINDERS, BLEED AND PIN MSRC'S AND PREP SUBS TO SQUAT. SUBS DOWN @ 22:30. NOTE: FINISHED CLEANING MUD TANKS @ 00:00
BIGHORN PASS H06 BH | 21 | 2021-11-22 | 2021-11-22 06:00 | 6 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 19.34 | 19363 | 19363 | 0 | REMOVE BOP WRANGLER, V-DOOR POST. R/D ELETRICAL ON MAST J-BOX. SWAP MSRC'S F/SUBS TO MAST. PREP MAST TO BE LAID OVER. MAST DOWN @ 00:30 R/D AND SPLIT BACK YARD. STAGE LOADS TO BE LOADED AND HAULED. PERFORM 180 DAY INSPECTION ON HPU. CONT. TO DETOX AND CLEAN RIG OF OBM.
BIGHORN PASS H06 BH | 21 | 2021-11-22 | 2021-11-22 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 19.09 | 19363 | 19363 |  | MILESTONE_WELL RELEASE 11/22/2021 @ 00:00.
BIGHORN PASS H06 BH | 22 | 2021-11-22 06:00 | 2021-11-22 18:00 | 12 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 19.84 | 19363 | 19363 | 0 | WASH RIG, RIG DOWN AND CONT. TO SEPERATE BACK YARD, RIG DOWN AND MOVE TCB CAMPS, PERFORM CAR WASH ON ALL EQUIPMENT LEAVING LOCATION, RIG DOWN, LOAD OUT, MOVE AND SET IN RIG ON THE TAHOE PINES H01 PR LOCATION. ON NEW LOCATION: SET MUD TANKS, MUD PUMPS, RIG WATER TANKS, SUITCASES, VFD HOUSE, PARTS HOUSES, FRAC TANKS.
BIGHORN PASS H06 BH | 22 | 2021-11-22 18:00 | 2021-11-22 18:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 19.84 | 19363 | 19363 |  | MILESTONE_RIG RELEASE 11/22/2021 @ 18:00
BIGHORN PASS H06 BH | 22 | 2021-11-22 18:00 | 2021-11-22 18:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 19.84 | 19363 | 19363 |  | MILESTONE_TURN OVER TO COMPLETION 11/22/2021 @ 18:00
BIGHORN PEAK H04 BH | 1 | 2021-10-07 09:30 | 2021-10-07 09:30 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 10/7/2021 @ 09:30
BIGHORN PEAK H04 BH | 1 | 2021-10-07 09:30 | 2021-10-07 11:30 | 2 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/BIGHORN PLAINS H02 BH T/BIGHORN PEAK H04 BH; SET MATS, WALK RIG T/BIGHORN PEAK H04 BH; CENTER SUB OVER CONDUCTOR.
BIGHORN PEAK H04 BH | 1 | 2021-10-07 11:30 | 2021-10-07 12:45 | 1.25 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
BIGHORN PEAK H04 BH | 1 | 2021-10-07 12:45 | 2021-10-07 13:45 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PEAK H04 BH | 1 | 2021-10-07 13:45 | 2021-10-07 16:30 | 2.75 | U | MOBDMOB | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 0 | 108 | 108 | 0 | AFTER TRIPPING CROWN-O-MATIC TO ENSURE CROWN-O-MATIC WAS WORKING PROPERLY, CROWN-O-MATIC WOULD NOT RESET, CHANGED OUT PRESSURE SWITCH AND TRIPPED CROWN-O-MATIC, ATTEMPTED TO RESET CROWN-O-MATIC WITH NO SUCCESS, CHANGED OUT VERSA VALVE AND ATTEMPTED TO TRIP CROWN-O-MATIC WITH NO SUCCESS, CHANGED OUT AIR FITTINGS ON VERSA VALVE. FUNCTION TEST CROWN-O-MATIC (GOOD TEST)
BIGHORN PEAK H04 BH | 1 | 2021-10-07 16:30 | 2021-10-07 17:30 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, TAG BOTTOM @ 108'.
BIGHORN PEAK H04 BH | 1 | 2021-10-07 17:30 | 2021-10-07 17:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 10/7/2021 @ 17:30
BIGHORN PEAK H04 BH | 1 | 2021-10-07 17:30 | 2021-10-07 23:30 | 6 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.25 | 108 | 2815 | 451.2 | ROTATE DRILL (2,707' IN 5.88 HRS @ 460.4 FPH) WOB-15-35K, RPM-100, TRQ-3K/18K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,700/2,550 PSI, DIFF-250/850 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM.
BIGHORN PEAK H04 BH | 1 | 2021-10-07 23:30 | 2021-10-08 00:15 | 0.75 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.28 | 2815 | 3025 | 280 | SLIDE (210' IN .87 HRS @ 241.4 FPH) WOB-5/15K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1,500/1,850 PSI, DIFF-150/350 PSI. SLIDE DEPTHS: F/1401' T/1431' 30' TF-290M 2014-2020 F/1495' T/1525' 30' TF-290M 2031-2037 F/1780' T/1810' 30' TF-HS 2110-2117 F/1966' T/1996' 30' TF-HS 2138-2143 F/2056' T/2086' 30' TF-20L 2154-2201 F/2149' T/2179' 30' TF-HS 2211-2219 F/2634' T/2664' 30' TF-HS 2309-2322
BIGHORN PEAK H04 BH | 1 | 2021-10-08 00:15 | 2021-10-08 01:00 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.31 | 3025 | 3025 | 0 | PUMP 2-30 BBL GEL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,000 PSI.
BIGHORN PEAK H04 BH | 1 | 2021-10-08 01:00 | 2021-10-08 02:00 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.35 | 3025 | 3025 | 0 | TRIP OUT OF HOLE F/3,025' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
BIGHORN PEAK H04 BH | 1 | 2021-10-08 02:00 | 2021-10-08 02:45 | 0.75 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.39 | 3025 | 3025 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR, L/D MOTOR, PONY COLLAR, UBHO, AND STAB. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND NO PAD WEAR ON STAB. BIT GRADE: 0-0-NO-A-X-0-NO-TD.
BIGHORN PEAK H04 BH | 1 | 2021-10-08 02:45 | 2021-10-08 03:30 | 0.75 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.42 | 3025 | 3025 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
BIGHORN PEAK H04 BH | 1 | 2021-10-08 03:30 | 2021-10-08 06:00 | 2.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.52 | 3025 | 3025 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). PICK AND RUN 10 3/4" 45.5# J-55 BT&C CASING T/1,511'.
BIGHORN PEAK H04 BH | 2 | 2021-10-08 06:00 | 2021-10-08 08:00 | 2 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.6 | 3025 | 3025 | 0 | RUN 10 3/4" 45.5# J-55 BTC CASING F1,511' T/3,014'. RAN 39 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 100K LBS(W/O BLOCKS). SHOE- 3,014' TOP OF FLOAT COLLAR- 2,933' LEFT OUT 8 JOINTS-308.82'
BIGHORN PEAK H04 BH | 2 | 2021-10-08 08:00 | 2021-10-08 09:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.65 | 3025 | 3025 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-318, SPP-150. NO LOSSES.
BIGHORN PEAK H04 BH | 2 | 2021-10-08 09:00 | 2021-10-08 09:30 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.67 | 3025 | 3025 | 0 | RIG DOWN CRT, L/D LANDING JOINT.
BIGHORN PEAK H04 BH | 2 | 2021-10-08 09:30 | 2021-10-08 09:30 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.67 | 3025 | 3025 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 10/8/2021 @ 9:30
BIGHORN PEAK H04 BH | 2 | 2021-10-08 09:30 | 2021-10-08 11:00 | 1.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.67 | 3025 | 3025 | 0 | WALK RIG F/ BIGHORN PEAK H04 BH T/ BIGHORN PASS H06 BH. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
BIGHORN PEAK H04 BH | 2 | 2021-10-08 11:00 | 2021-10-08 13:30 | 2.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.67 | 3025 | 3025 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 317 BBLS 11.6 PPG LEAD CEMENT, 85 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 279 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/970 PSI PRESSURED UP T/1470 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2.0 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 109 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
BIGHORN PEAK H04 BH | 2 | 2021-10-08 13:30 | 2021-10-08 15:30 | 2 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.67 | 3025 | 3025 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 12:00 | 2021-10-13 12:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.67 | 3025 | 3025 |  | MILESTONE_RESUME WELL 1 ON 10/13/2021 @ 12:00
BIGHORN PEAK H04 BH | 3 | 2021-10-13 12:00 | 2021-10-13 13:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.71 | 3025 | 3025 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM REDWOOD B 1H TO REDWOOD C 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 13:00 | 2021-10-13 14:30 | 1.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.77 | 3025 | 3025 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 14:30 | 2021-10-13 15:30 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.81 | 3025 | 3025 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, KILL LINE, HCR HOSE AND KILL LINE CHECK VALVE 250 PSI LOW AND 5000 PSI HIGH.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 15:30 | 2021-10-13 16:00 | 0.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.83 | 3025 | 3025 | 0 | INSTALL WEAR BUSHING, CLOSE CSG VALVE AND COVER CELLAR
BIGHORN PEAK H04 BH | 3 | 2021-10-13 16:00 | 2021-10-13 17:00 | 1 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 0.88 | 3025 | 3025 | 0 | PICK UP BHA #2. (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.88' BIT TO BEND; 8.35" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 17:00 | 2021-10-13 18:45 | 1.75 | U | SFHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 0.95 | 3025 | 3025 | 0 | C/O HYDRAULIC LINE ON DS CAT HEAD.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 18:45 | 2021-10-13 20:15 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.01 | 3025 | 3025 | 0 | CONT. P/U BHA #2. P/U: 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, 22 STDS OF 5'' DP, DSW AGITATOR. BIT TO SENSOR-64', GAMMA-60'. TEST MWD ( GOOD TEST).
BIGHORN PEAK H04 BH | 3 | 2021-10-13 20:15 | 2021-10-13 21:45 | 1.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.07 | 3025 | 3025 | 0 | TIH F/BHA-T/2,726'. HOLE GIVING PROPER DISPLACEMENT
BIGHORN PEAK H04 BH | 3 | 2021-10-13 21:45 | 2021-10-13 22:45 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.11 | 3025 | 3025 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. FILL PIPE. P/U AGITATOR AND TEST. (SPP BEFORE:985. SPP AFTER: 1,230. TESTED @ 400 GPM) NOTE: FLOW CHECK WAS PERFORMED PRIOR TO REMOVAL OF TRIP NIPPLE. RESULT: NO FLOW.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 22:45 | 2021-10-13 23:00 | 0.25 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.13 | 3025 | 3025 | 0 | TIH F/2,726'-T/2,933'. HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 23:00 | 2021-10-13 23:45 | 0.75 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.16 | 3025 | 3025 | 0 | DRILL SHOE TRACK F/2,933'-T/3,025', GPM-400, SPP-1,250 PSI, DP-100/200, RPM-30, WOB-10-15K, TQ-2/5K.
BIGHORN PEAK H04 BH | 3 | 2021-10-13 23:45 | 2021-10-14 | 0.25 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.17 | 3025 | 3035 | 40 | ROT DRILL 10' OF NEW FORMATION F/3,025'-T/3,035', GPM-400, SPP-1,250 PSI, DP-100/200, RPM-30, WOB-10-15K, TQ-2/5K.
BIGHORN PEAK H04 BH | 3 | 2021-10-14 | 2021-10-14 00:30 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 1.19 | 3035 | 3035 | 0 | CIRCULATE BOTTOMS UP GPM-400, SPP-1,250 PSI, RPM-30. MW IN 9.0 PPG, MW OUT 8.9 PPG. NOTE: CIRC THROUGH GAS BUSTER TO ENSURE NO RESTRICTIONS AND BUSTER FULL.
BIGHORN PEAK H04 BH | 3 | 2021-10-14 00:30 | 2021-10-14 01:00 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.21 | 3035 | 3035 | 0 | PERFORM F.I.T. WITH 9.0 PPG OBM, 421 PSI CSG PRESSURE FOR 11.7 PPG EMW, SHOE MD-3,014' /TVD-3,001'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE. RESULTED IN GOOD TEST.
BIGHORN PEAK H04 BH | 3 | 2021-10-14 01:00 | 2021-10-14 05:45 | 4.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.41 | 3035 | 4418 | 291.2 | ROT (1,383' IN 4.75 HRS @ 291.15 FPH) WOB: 10/20K, SPM: 110/110, GPM: 705, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 11K/17K, SPP: 2,600/3,200 PSI, DIFF:300-400 NOTE: DRILLING W/2 MPS DUE TO LEAK ON #2MP, DISCHARGE MODULE #3.
BIGHORN PEAK H04 BH | 3 | 2021-10-14 05:45 | 2021-10-14 06:00 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.42 | 4418 | 4443 | 100 | SLIDE (25' IN 0.25 HRS @ 100 FPH) WOB: 5K, SPM:110/110, GPM: 705, MMRPM: 117, SPP:2600/3,000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/3,196'-T/3,211', 15', TF:30R, 01:38-01:45 F/4,043'-T/4,053', 10', TF:140L, 04:43-04:51 NOTE: DRILLING W/2 MPS DUE TO LEAK ON #2MP, DISCHARGE MODULE #3.
BIGHORN PEAK H04 BH | 4 | 2021-10-14 06:00 | 2021-10-14 15:15 | 9.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.8 | 4443 | 7279 | 306.6 | ROT (2836' IN 9.22 HRS @ 308 FPH) WOB: 10/20K, SPM: 110/110, GPM: 705, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 11K/17K, SPP: 2,600/3,200 PSI, DIFF:300-400 NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990. NOTE: DRILLING W/2 MPS DUE TO LEAK ON #2MP, DISCHARGE MODULE #3 AND #2 MODULE.
BIGHORN PEAK H04 BH | 4 | 2021-10-14 15:15 | 2021-10-14 17:00 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.88 | 7279 | 7411 | 75.4 | SLIDE (132' IN 1.78 HRS @ 74 FPH) WOB: 5K, SPM:110/110, GPM: 705, MMRPM: 117, SPP:2600/3,000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/4,988' T/5,000' 12' TF:70R 07:23-07:30 F/5,362' T/5,372' 10' TF:50L 08:23-08:32 F/5,550' T/5,562' 12' TF:50L 09:04-09:16 F/5,647' T/5,659' 12' TF:90L 09:31-09:44 F/5,738' T/5,750' 12' TF:90L 09:57-10:08 F/5,927' T/5,935' 8' TF:150L 10:38-10:45 F/6,486' T/6,498' 12' TF:70L 12:38-12:45 F/6,766' T/6,778' 12' TF:60L 13:42-13:56 F/7,047' T/7,062' 15' TF:60L 15:08-15:15 F/7,235' T/7,250' 15' TF:70L 15:50-16:00 F/7,329' T/7,341' 12' TF:90L 16:15-16:25 NOTE: DRILLING W/2 MPS DUE TO LEAK ON #2MP, DISCHARGE MODULE #3.
BIGHORN PEAK H04 BH | 4 | 2021-10-14 17:00 | 2021-10-14 20:15 | 3.25 | U | INTHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 2.01 | 7411 | 7411 | 0 | MWD TOOL LOST GAMMA READING AND NOT ABLE TO PUMP UP SURVEY; CONNECTIVITY WAS NOT COMMUNICATING FROM FLOOR TO DIRECTIONAL COMMAND CENTER; CHANGE OUT MWD SCREEN, CABLE, CABLE INPUT BOX, TRANSDUCER AND CABLE. C/O DECODING SYSTEM ON RIG FLOOR, C/O DECODING SYSTEM DOWN IN THE MWD OFFICE, C/O UBIQUITI ENTENNAS AND WITS CABLES.
BIGHORN PEAK H04 BH | 4 | 2021-10-14 20:15 | 2021-10-15 01:30 | 5.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.23 | 7411 | 8540 | 215 | ROT (1,129' IN 5.25 HRS @ 215.04 FPH) WOB: 10/30K, SPM: 110/110, GPM: 705, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 11K/17K, SPP: 2,600/3,200 PSI, DIFF:300-400 NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990. NOTE: DRILLING W/2 MPS DUE TO LEAK ON #2MP, DISCHARGE MODULE #3. *GAMMA STARTED WORKING @ 21:40 @ 7,626'*
BIGHORN PEAK H04 BH | 4 | 2021-10-15 01:30 | 2021-10-15 02:15 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.26 | 8540 | 8585 | 60 | SLIDE (45' IN .67 HRS @ 67.16 FPH) WOB: 5-15K, SPM:110/110, GPM: 705, MMRPM: 117, SPP:2600/3,000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/7,420'-T/7,435', 15', TF:180, 20:19-20:31 F/8,066'-T/8,081', 15', TF:120L, 23:35-23:52 F/8,254'-T/8,269', 15', TF:140L, 00:35-00:46 NOTE: DRILLING W/2 MPS DUE TO LEAK ON #2MP, DISCHARGE MODULE #3.
BIGHORN PEAK H04 BH | 4 | 2021-10-15 02:15 | 2021-10-15 06:00 | 3.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.42 | 8585 | 9218 | 168.8 | ROT (633' IN 3.83 HRS @ 165.27 FPH) WOB: 10/30K, SPM: 83/83/83, GPM:800, MMRPM: 132, RPM-80, TRPM: 212.8, TRQ: 11K/17K, SPP: 4,542/5,075 PSI, DIFF:500-600 NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
BIGHORN PEAK H04 BH | 5 | 2021-10-15 06:00 | 2021-10-15 06:45 | 0.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.45 | 9218 | 9324 | 141.3 | ROT (106' IN .25 HRS @ 424 FPH) WOB: 10/30K, SPM: 83/83/83, GPM:800, MMRPM: 132, RPM-80, TRPM: 212.8, TRQ: 11K/17K, SPP: 4,542/5,075 PSI, DIFF:500-600 NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
BIGHORN PEAK H04 BH | 5 | 2021-10-15 06:45 | 2021-10-15 08:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.5 | 9324 | 9425 | 80.8 | BUILD INTERMEDIATE CURVE: SLIDE (101' IN 1.75 HRS @ 57.7 FPH) WOB: 5-15K, SPM:83/83/83, GPM: 800, MMRPM: 132, SPP:5,000/5,150 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/9324'-T/9425', 101', TF:150M, 06:15-08:00
BIGHORN PEAK H04 BH | 5 | 2021-10-15 08:00 | 2021-10-15 12:15 | 4.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.68 | 9425 | 9652 | 53.4 | CONT. BUILD INTERMEDIATE CURVE: SLIDE (227' IN 4.25 HRS @ 53 FPH) WOB: 5-15K, SPM:110/110, GPM: 706, MMRPM: 117, SPP:3500/3,760 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/9425' T/9562' 137' TF-150M 800-1008 SLD F/9577' T/9645' 68' TF-30L 1014-1125 SLD F/9687' T/9709' 22' TF-70L 1155-1220 NOTE: DRILLING W/2 MPS DUE TO REPLACE BOLTS ON #1 MP/ #1 SUCTION MODULE CAP RETAINER RING; AFTER REPAIRS WERE MADE ON THE #1 MP, CHANGE LINER GASKET ON # 2 MUD PUMP
BIGHORN PEAK H04 BH | 5 | 2021-10-15 12:15 | 2021-10-15 14:30 | 2.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.77 | 9652 | 9790 | 61.3 | BUILD CURVE ROT (138' IN 2.27 @ 61 FPH) WOB: 25/35K, SPM: 110/110, GPM: 706, MMRPM: 117, RPM: 30, TRPM: 147, SPP: 3600/3800 PSI, DIFF: 200/300
BIGHORN PEAK H04 BH | 5 | 2021-10-15 14:30 | 2021-10-15 16:00 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.83 | 9790 | 9790 | 0 | PERFORM POST TD CLEAN UP CYCLE PUMPING 2-30 BBL HI-VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7.625" CASING. GPM-706, ,SPP-3,792 PSI, SHAKERS CLEAN.
BIGHORN PEAK H04 BH | 5 | 2021-10-15 16:00 | 2021-10-15 21:15 | 5.25 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.05 | 9790 | 9790 | 0 | POOH W/BHA #2 F/9,790'-T/BHA'. HOLE TAKING PROPER FILL VIA TRIP TANK. HOLE CONDITIONS= SLICK NOTE: FLOW CHECK AT SHOE (WELL STATIC), REMOVE RT-HEAD AND INSTALL TRIP NIPPLE @ 2,765'.
BIGHORN PEAK H04 BH | 5 | 2021-10-15 21:15 | 2021-10-15 23:45 | 2.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.16 | 9790 | 9790 | 0 | RACK BACK HWDP & 2 STDS-6.5" DC, REMOVE MWD TOOL, DRAIN MUD MOTOR, BREAK OUT BIT, CHANGE OUT, SCRIBE, AND RACK BACK NEW MOTOR. NOTE: MUD MOTOR DRAINED GOOD WITH MINIMAL SLACK. BIT GRADED: 1-1-CT-G-X-0-CT-TD.
BIGHORN PEAK H04 BH | 5 | 2021-10-15 23:45 | 2021-10-16 00:30 | 0.75 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.19 | 9790 | 9790 | 0 | PULL WEAR BUSHING, L/D MOUSEHOLE, CLEAN AND ORGANIZE RIG FLOOR FOR CASING RUN
BIGHORN PEAK H04 BH | 5 | 2021-10-16 00:30 | 2021-10-16 02:00 | 1.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.25 | 9790 | 9790 | 0 | CHANGE OUT TOP VBR'S TO 7.625" CASING RAMS, PICK UP JOINT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1500 PSI.
BIGHORN PEAK H04 BH | 5 | 2021-10-16 02:00 | 2021-10-16 03:30 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.31 | 9790 | 9790 | 0 | HOLD PJSM AND RIG UP FRANK'S CASING TOOLS & EQUIPMENT.
BIGHORN PEAK H04 BH | 5 | 2021-10-16 03:30 | 2021-10-16 06:00 | 2.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.42 | 9790 | 9790 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN INTERMEDIATE 29.7# P-110 IC BTC CSG CASING T/1,446', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PEAK H04 BH | 6 | 2021-10-16 06:00 | 2021-10-16 13:15 | 7.25 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.72 | 9790 | 9790 | 0 | RUN 7.625'' INTERMEDIATE CASING F/1,446'-T/9,779.2', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT. 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 219 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG,1-10' PUP JT, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, TOTAL OF 224 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 40 LATCH ON BOW SPRING CENTRALIZERS @ 9,473' AND EVERY 4TH JT UP TO 2,605 '. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/190K (W/O BLOCKS) BTM OF FLOAT SHOE- 9,779' TOP OF FLOAT COLLAR-9,690'. 15 JOINTS LEFT OUT- 661.99' & 2-15' PUP JTS
BIGHORN PEAK H04 BH | 6 | 2021-10-16 13:15 | 2021-10-16 13:45 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 3.74 | 9790 | 9790 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
BIGHORN PEAK H04 BH | 6 | 2021-10-16 13:45 | 2021-10-16 16:15 | 2.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.84 | 9790 | 9790 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 105, 8.0 BPM, SPP: 650 PSI, NO LOSSES. NOTE: HAD TO REDUCE CIRCULATION RATE TO 4 BPM DUE TO PIN HOLE IN STANDPIPE TREE ON RIG FLOOR NOTE: COULD NOT USE CEMENT TRUCK TO COMPLETE CIRCULATION DUE TO FIRST CEMENT TRUCK NOT WORKING PROPERLY; HAD TO SWAB TRUCKS BEFORE STARTING CEMENT JOB
BIGHORN PEAK H04 BH | 6 | 2021-10-16 16:15 | 2021-10-16 19:30 | 3.25 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.98 | 9790 | 9790 | 0 | PJSM. SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4,000 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.5 PPG SPACER. 283 BBL 11.8 PPG 820 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPNAY REP WITNESS PLUG DROP, DISPLACE WITH 445 BBLS OF 9.8 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1650 PSI AT 4 BPM, BUMP PLUG AND INCREASE PSI 500 OVER T/2,100 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI (4.5BBLS)-FLOATS HELD. PLUG BUMPED @ 19:21HRS. NOTE: FULL RETURNS THROUGHOUT JOB. 35 BBLS SPACER TO SURFACE. ESTIMATED TOP OF CMT: 2,500'
BIGHORN PEAK H04 BH | 6 | 2021-10-16 19:30 | 2021-10-16 20:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4 | 9790 | 9790 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD.
BIGHORN PEAK H04 BH | 6 | 2021-10-16 20:00 | 2021-10-16 20:30 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.02 | 9790 | 9790 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
BIGHORN PEAK H04 BH | 6 | 2021-10-16 20:30 | 2021-10-16 22:30 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.1 | 9790 | 9790 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL
BIGHORN PEAK H04 BH | 6 | 2021-10-16 22:30 | 2021-10-17 00:30 | 2 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.19 | 9790 | 9790 | 0 | REMOVE CASING RAMS; INSPECT BOP PRIOR TO INSTALLING RAMS. INSTALL VARIABLE RAMS
BIGHORN PEAK H04 BH | 6 | 2021-10-17 00:30 | 2021-10-17 03:00 | 2.5 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.29 | 9790 | 9790 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL.
BIGHORN PEAK H04 BH | 6 | 2021-10-17 03:00 | 2021-10-17 04:30 | 1.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.35 | 9790 | 9790 | 0 | C/O SAVER SUB. RIG MANAGER PRESENT
BIGHORN PEAK H04 BH | 6 | 2021-10-17 04:30 | 2021-10-17 05:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.38 | 9790 | 9790 | 0 | SERVICE RIG: LUBE TD, DRWKS AND ST-80. RIG MANAGER PRESENT
BIGHORN PEAK H04 BH | 6 | 2021-10-17 05:00 | 2021-10-17 05:00 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 4.38 | 9790 | 9790 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 10/17/21 @ 05:00
BIGHORN PEAK H04 BH | 7 | 2021-10-30 06:00 | 2021-10-30 06:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 4.38 | 9790 | 9790 |  | MILESTONE_RESUME WELL 2 ON 10/30/2021 @ 06:00
BIGHORN PEAK H04 BH | 7 | 2021-10-30 06:00 | 2021-10-30 07:30 | 1.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 4.44 | 9790 | 9790 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM BIGHORN PLAINS H 02 TO BIGHORN PEAK H 04, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 07:30 | 2021-10-30 09:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.5 | 9790 | 9790 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 09:00 | 2021-10-30 15:00 | 6 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.75 | 9790 | 9790 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, TEST CHOKE MANIFOLD MANUAL VALVES,SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. NOTE: REBUILT OUTSIDE 4" VALVE ON #2 PUMP.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 15:00 | 2021-10-30 16:00 | 1 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.79 | 9790 | 9790 | 0 | RIG DOWN TEST EQUIPMENT; PERFORM ACCUMULATOR DRAW DOWN TEST, INSTALL WEAR BUSHING AND MOUSE HOLE; VERIFY STACK AND CHOKE ALIGNMENT.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 16:00 | 2021-10-30 17:30 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 4.85 | 9790 | 9790 | 0 | SLIP AND CUT 130' OF DRILL LINE.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 17:30 | 2021-10-30 18:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.88 | 9790 | 9790 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 18:00 | 2021-10-30 18:30 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.9 | 9790 | 9790 | 0 | CLEAN AND ORGANIZE RIG FLOOR, PREP FLOOR TO P/U BHA. VERIFY CASING VALVE CLOSED.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 18:30 | 2021-10-30 20:15 | 1.75 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.97 | 9790 | 9790 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13618579 JETS 6X18 TFA: 1.491), 5.5", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.01' BIT TO BEND; 5.62" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-64'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD), TRIP IN HOLE 2 STDS AND PICK UP DRILL-N-REAM
BIGHORN PEAK H04 BH | 7 | 2021-10-30 20:15 | 2021-10-30 21:30 | 1.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.02 | 9790 | 9790 | 0 | TRIP IN THE HOLE F/BHA T/2,797', PROPER DISPLACEMENT TO TRIP TANK.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 21:30 | 2021-10-30 22:15 | 0.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.05 | 9790 | 9790 | 0 | FILLED PIPE AND FLOW TESTED DRILL STRING, PICKED UP AGITATOR AND FLOW TESTED. SPP BEFORE-820 PSI SPP AFTER- 920 PSI @ 200 GPM.
BIGHORN PEAK H04 BH | 7 | 2021-10-30 22:15 | 2021-10-31 01:15 | 3 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.18 | 9790 | 9790 | 0 | TRIP IN THE HOLE F/2,797' T/9,319', PROPER DISPLACEMENT TO TRIP TANK.
BIGHORN PEAK H04 BH | 7 | 2021-10-31 01:15 | 2021-10-31 02:00 | 0.75 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 5.21 | 9790 | 9790 | 0 | PULL TRIP NIPPLE, AND INSTALL ROTATING HEAD.
BIGHORN PEAK H04 BH | 7 | 2021-10-31 02:00 | 2021-10-31 02:45 | 0.75 | P | INTHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 5.24 | 9790 | 9790 | 0 | WASH/REAM CEMENT STRINGERS F/9,645' T/9,690', TAGGED FLOAT COLLAR @ 9,690',VERIFY CHOKE VALVE ALIGNMENT, PUMP THROUGH GAS SEPERATOR PRIOR TO DRILL OUT. PERFORM BOP DRILL, RESPONSE TIME= 45 SECONDS.
BIGHORN PEAK H04 BH | 7 | 2021-10-31 02:45 | 2021-10-31 03:15 | 0.5 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.26 | 9790 | 9800 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/9,790' T/9,800', WOB-20K, RPM-30, GPM-300, SPP-2430 PSI, DIFF-55 PSI, RPM-30, TQ-4/6K.
BIGHORN PEAK H04 BH | 7 | 2021-10-31 03:15 | 2021-10-31 03:45 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.28 | 9800 | 9800 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T., GPM-200, SPP-1200 PSI, RPM-30, MUD WT IN 9.3 PPG, MUD WT OUT 9.3 PPG.
BIGHORN PEAK H04 BH | 7 | 2021-10-31 03:45 | 2021-10-31 04:15 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.3 | 9800 | 9800 | 0 | PERFORM F.I.T. WITH 9.3 PPG OBM, 1850 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-9,779' / TVD-9,679'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE.
BIGHORN PEAK H04 BH | 7 | 2021-10-31 04:15 | 2021-10-31 06:00 | 1.75 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.38 | 9800 | 9891 | 52 | BUILD CURVE-SLIDE (91' IN 1.75 HR @ 52 FPH) WOB-15K, SPM-73/73, GPM-380, MRPM-272, SPP-3,500/3,850 PSI, DIFF-350 PSI SLIDE DEPTHS: F/9,800'-T/9,891',91', TF:HS, 04:15-06:00
BIGHORN PEAK H04 BH | 7 | 2021-10-31 04:15 | 2021-10-31 04:15 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.3 | 9800 | 9800 |  | MILESTONE_START CURVE SECTION 10-31-2021 @ 04:15
BIGHORN PEAK H04 BH | 8 | 2021-10-31 06:00 | 2021-10-31 17:30 | 11.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.85 | 9891 | 10436 | 47.4 | BUILD CURVE-SLIDE (545' IN 11.67 HR @ 46.71 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3700/3,525 PSI, DIFF-250/450 PSI., CHOKES- 100% / 100%, FLARE- 0-20', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 250 PSI, AVG SICP= 100 PSI. SLIDE DEPTHS: SLD F/9891 T/10220 329' TF-HS 600-1150 SLD F/10270 T/10310 40' TF-HS 1225-1254 SLD F/10365 T/10395 30' TF-HS 1325-1350 SLD F/10459 T/10475 16' TF-HS 1435-1525 SLD F/10485 T/10530 45' TF-HS 1535-1800 SLD F/10553 T/10637 84' TF-HS 1920-2101
BIGHORN PEAK H04 BH | 8 | 2021-10-31 17:30 | 2021-10-31 21:00 | 3.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6 | 10436 | 10637 | 57.4 | BUILD CURVE-ROTATE (201' IN 3.35 HRS @ 60 FPH) WOB-25-35K, SPM-76/76, GPM-400, RPM-30, MRPM-272, TRPM-302, SPP-3,700-3,525 PSI, DIFF-250/450 PSI, CHOKES- 100% / 100%, FLARE-0-20', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 250.
BIGHORN PEAK H04 BH | 8 | 2021-10-31 21:00 | 2021-10-31 21:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6 | 10637 | 10637 |  | MILESTONE_LAND/END CURVE SECTION ON 10/31/2021 @ 21:00, MD:10,637', TVD:10,157'
BIGHORN PEAK H04 BH | 8 | 2021-10-31 21:00 | 2021-11-01 02:45 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.24 | 10637 | 11576 | 163.3 | ROTATE DRILL LATERAL (939' IN 5.8 HR @ 161.89, FPH) WOB-20/25K, SPM-76/76, GPM-400, RPM- 80, TQ- 7/10K, MRPM-272, TTRPM-352, SPP- 3,500/4,400 PSI, DIFF- 800/1,000 PSI, CHOKES- 100% / 100%, FLARE-8'-30'', NO MUD CUT, MAX CASING PRESSURE= 140 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=576 PSI NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT.
BIGHORN PEAK H04 BH | 8 | 2021-10-31 21:00 | 2021-10-31 21:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6 | 10637 | 10637 |  | MILESTONE_START LATERAL SECTION ON 10/31/2021 @ 21:00
BIGHORN PEAK H04 BH | 8 | 2021-11-01 02:45 | 2021-11-01 03:45 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.28 | 11576 | 11576 | 0 | SERVICE TOP DRIVE, DRAW WORKS, AND ST-80
BIGHORN PEAK H04 BH | 8 | 2021-11-01 03:45 | 2021-11-01 06:00 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.38 | 11576 | 11684 | 48 | SLD DRILL LATERAL (108' IN 2.18 HRS @ 49.54 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3,500/4,000 PSI, DIFF-300/500 PSI, CHOKES- 100% / 100%, FLARE-8'/30', NO MUD CUT, MAX CASING PRESSURE= 140 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 576 PSI. SLIDE DEPTHS: SLD F/11,495' T/11,503' 8' TF-60R 0500-0510
BIGHORN PEAK H04 BH | 9 | 2021-11-01 06:00 | 2021-11-01 14:45 | 8.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.74 | 11684 | 13361 | 191.7 | ROTATE DRILL LATERAL (1677' IN 8.83 HR @ 189.9 FPH) WOB-20/30K, SPM-76/76, GPM-400, RPM- 80, TQ- 7K/9K, MRPM-272, TTRPM-352, SPP- 3600/4700 PSI, DIFF- 900/1100 PSI, CHOKES- 100% / 100%, CHOKES @ B/U- 70% / 0%, FLARE-15'-20' @ B/U, MUD CUT F/9.1 T/8.6 PPG, MAX CASING PRESSURE= 155 PSI, AVG CASING PRESSURE= 40 PSI, MAX GAS: 2776u, SHUTTING IN ON CONNECTIONS, MAX SICP=440 PSI, AVG SICP=350 PSI. NOTE: ENCOUNTERED 30/40 BPH LOSSES @ 11,556', PUMPED 10 BBL 17 PPB LCM SWEEP EVERY STAND F/11,556' T/12,920' AND LOSSES SUBSIDE CONSISTING OF ACTIVE MUD, 5 PPBb SUPERCEAL and 7 PPB PRO-V with 5 PPB MAGMA FIBER FINE. PUMPING 10 BBL 17 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 5 PPBb SUPERCEAL and 7 PPB PRO-V with 5 PPB MAGMA FIBER FINE. NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 11:47 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 12,730', NEW WINDOW: 0' ABOVE / 10' BELOW. TARGET CHANGE RECEIVED VIA TEXT @ 11:57 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 13,317', NEW TARGET: 10155’ TVD @ 0 VS, 86.8° INC, 5’ ABOVE/ 5’ BELOW, 50’ LEFT / 50’ RIGHT
BIGHORN PEAK H04 BH | 9 | 2021-11-01 14:45 | 2021-11-01 17:00 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.83 | 13361 | 13466 | 46.7 | SLD DRILL LATERAL (105' IN 2.17 HRS @ 48.4 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-3600/4550 PSI, DIFF-350/550 PSI, CHOKES-100% / 100%, FLARE-2'-4', MUD CUT F/9.1 PPG T/8.9 PPG, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/11977 T/11992 15' TF-140R 730-748 SLD F/12634 T/12654 20' TF-100R 1043-1112 SLD F/12726 F/12746 20' TF-90R 1138-1202 SLD F/13008 T/13023 15' TF-70R 1337-1356 SLD F/13290 T/13310 20' TF-140R 1520-1542 SLD F/13384 T/13399 15' TF-180 1617-1635
BIGHORN PEAK H04 BH | 9 | 2021-11-01 17:00 | 2021-11-01 17:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.85 | 13466 | 13466 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80, VERIFIED THAT ST-80 DUMP VALVE WAS BLEEDING OFF PRESSURE ONCE CYLINDER WAS BOTTOMED OUT, 1 SEC DELAY BEFORE PRESSURE BLED OFF TO 0.
BIGHORN PEAK H04 BH | 9 | 2021-11-01 17:30 | 2021-11-02 04:30 | 11 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.31 | 13466 | 15396 | 175.5 | ROTATE DRILL LATERAL (1,930' IN 11.03 HR @ 174.9 FPH) WOB-20/30K, SPM-76/76, GPM-400, RPM- 80, TQ- 8-12K, MRPM-272, TTRPM-352, SPP- 4,130/5,090 PSI, DIFF- 900/1100 PSI, CHOKES- 100% / 100%, CHOKES @ B/U- 0% / 75%, FLARE: 5'-20' @ B/U, MUD CUT F/9.1 T/9.0 PPG, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX GAS: 1875u, SHUTTING IN ON CONNECTIONS, MAX SICP=442 PSI, AVG SICP=350 PSI. NOTE: WINDOW CHANGE RECEIVED VIA TEXT @02:13 HOURS, DEPTH WHEN RECEIVED WINDOWCHANGE 114,922'', NEW TARGET: 10162’ TVD @ 0 VS, 86.8° INC, 5’ ABOVE/ 5’ BELOW, 50’ LEFT / 50’ RIGHT
BIGHORN PEAK H04 BH | 9 | 2021-11-02 04:30 | 2021-11-02 06:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.38 | 15396 | 15451 | 36.7 | SLD DRILL LATERAL (55' IN 1.47 HRS @ 37.4 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4,100'/5,100' PSI, DIFF-350/450 PSI, CHOKES-100% / 100%, FLARE-5'-20', MUD CUT F/9.1 PPG T/9.0 PPG, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. MAX GAS: 1875u, SHUTTING IN ON CONNECTIONS, MAX SICP=442 PSI, AVG SICP=350 PSI. SLIDE DEPTHS: SLD F/13,667' T/13,676' 10' TF-30R 18:55-19:08 SLD F/13,676' T/13,565' 10' TF-30R 20:00-20:11 SLD F/14,800' T/14,812' 12' TF-60R 01:14-01:38 SLD F/15,083' T/15,095' 12' TF-150R 03:11-03:30 SLD F/15,270' T/15,282' 12' TF-180R 04:30-04:51
BIGHORN PEAK H04 BH | 10 | 2021-11-02 06:00 | 2021-11-02 13:45 | 7.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.7 | 15451 | 16775 | 170.8 | ROTATE DRILL LATERAL (1324' IN 7.72 HRS @ 171.5 FPH) WOB-20/30K, SPM-76/76, GPM-400, RPM- 80, TQ- 10K/13K, MRPM-272, TTRPM-352, SPP- 4500/5400 PSI, DIFF- 700/900 PSI, CHOKES- 100% / 100%, CHOKES @ B/U- 70% / 0% FLARE-10'-20' @ B/U, MUD CUT F/9.1 T/9.0 PPG, MAX CASING PRESSURE= 50 PSI, AVG CASING PRESSURE= 0 PSI, MAX GAS: 2602u, SHUTTING IN ON CONNECTIONS, MAX SICP=530 PSI, AVG SICP=480 PSI, NOTE: ENCOUNTERED 10/20 BPH INFLUX OF WATER @ 15,470’, WATER CONTENT INCREASED F/27% T/31 % AND ES ON THE FLOW LINE DECREASED F/452 T/219, MANAGING THE WATER INFLUX BY TRANSFERRING SYSTEM MUD FROM THE RIG MUD TANKS TO FRAC TANKS AND TRANFERRING OVER FRESH MUD INTO THE SYSTEM FROM DIFFERENT FRAC TANKS WHILE DRILLING AHEAD, IN CONJUCTION TO ADDING DIESEL @ 21 BPH, 1 DRUM/HR OF EMULSIFIER AND CALCIUM CHLORIDE TO SUSTAIN THE MUD PROPERTIES, WATER CONTENT SUSTAINED @ 31% AND ES ON THE FLOW LINE DECREASED F/219 T/194. NOTE; ENCOUNTERED 10/15 BPH LOSSES, PUMP 10 BBL 17 PPB LCM SWEEP CONSISTING 5 PPBb SUPERCEAL and 7 PPB PRO-V with 5 PPB MAGMA FIBER FINE EVERY STAND. NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 12:06 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 16,278', NEW WINDOW: 0' ABOVE / 10' BELOW.
BIGHORN PEAK H04 BH | 10 | 2021-11-02 13:45 | 2021-11-02 16:45 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.82 | 16775 | 16884 | 36.3 | SLD DRILL LATERAL (109' IN 3.03 HRS @ 36 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4500/4850 PSI, DIFF-250/350 PSI, CHOKES-100% / 100%, FLARE-5'-20', MUD CUT F/9.1 PPG T/9.0 PPG, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/15650 T/15665 15' TF-30R 706-730 SLD F/15932 T/15952 20' TF-110R 854-921 SLD F/16026 T/16041 15' TF-180 952-1020 SLD F/16120 T/16135 15' TF-180 1050-1120 SLD F/16308 T/16328 20' TF-HS 1220-1248 SLD F/16495 T/16510 15' TF-HS 1353-1414 SLD F/16875 T/16884 9' TF-160R 1621-1645 NOTE: MOTOR STALLED OUT @ 1323 PSI DIFFERENTIAL PRESSURE WHILE SLIDING @ 16,884'
BIGHORN PEAK H04 BH | 10 | 2021-11-02 16:45 | 2021-11-02 18:15 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.89 | 16884 | 16884 | 0 | PICK UP TO NEUTRAL WEIGHT, SLOWLY STAGED UP PUMPS T/133 GPM AND 30 RPM, PICK UP AND BROKE WEIGHT OVER, RECYCLED PUMPS TO RE-SYNC MWD, PRESSURE INCREASED T/5600 PSI @ 400 GPM (1100 PSI OVER ORIGINAL OFF BOTTOM PRESSURE @ 400 GPM), SHUT PUMPS AND BLEED OFF PRESSURE, DECISION WAS MADE TO GO MUD CAP DUE TO DOWNHOLE COMMUNICATION OF WATER INFLUX, SLOWLY STAGED UP PUMPS 290 GPM, CIRCULATE AND RECIPROCATE PIPE WHILE PREPPING MUD TANKS AND EQUIPMENT TO INDUCE DRILLING WITH WATER UNDER MUD CAP PER MANAGEMENT, SPM-55/55, GPM-290, RPM- 50, TQ- 5K/11K, SPP- 4050 PSI, CHOKES- 25-60% / 0%, FLARE-30'-40' @ B/U, MUD CUT F/9.1 T/8.6 PPG, MAX CASING PRESSURE= 800 PSI, AVG CASING PRESSURE= 600 PSI, MAX GAS: 2622u.
BIGHORN PEAK H04 BH | 10 | 2021-11-02 18:15 | 2021-11-02 19:00 | 0.75 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 7.92 | 16884 | 16884 | 0 | SHUT DOWN PUMPS AND LINED UP TO PUMP DOWN THE BACKSIDE, CLOSED TOP VBR'S, MONITOR SICP, SICP= 471 PSI, PUMPED 17.0 PPG OBM DOWN BACKSIDE VIA KILL LINE. STAGING PUMP RATE UP F/27 GPM T/200 GPM. SICP INCREASED TO 576 PSI PRIOR TO BREAKING OVER @ 42 GPM WITH 3.7 BBLS KILL MUD PUMPED, CONTINUE PUMP ADDITIONAL 116.3 BBLS OF KILL MUD DOWN THE BACKSIDE TILL SICP DECREASED TO 0 PSI, TOTAL BBLS PUMPED OF 17.0 PPG KILL MUD= 120 BBLS. LINED UP TO PUMP FRESH WATER DOWN DRILL STRING AND CIRCULATED 349 BBLS WITH WATER AND RECIPROCATE PIPE (ADDED 2-5GAL BUCKETS OF PHPA TO WATER TO CREATE A SPACER BETWEEN WATER AND OBM), SPM-70/70, GPM-370, RPM- 50, TQ- 6K/10K, SPP- 5100 PSI.
BIGHORN PEAK H04 BH | 10 | 2021-11-02 19:00 | 2021-11-02 21:30 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.02 | 16884 | 16884 | 0 | STRIP OUT OF THE HOLE W/BHA #3 F/16,886'- T/14,768'. FILLING BACKSIDE WITH 17.0 PPG KILL MUD, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PEAK H04 BH | 10 | 2021-11-02 21:30 | 2021-11-02 22:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.04 | 16884 | 16884 | 0 | ENCOUNTERED TIGHT CONNECTION, COULD NOT BREAK WITH ST-80. WHEN ATTEMPT TO USE RIG TONGS, PULL CABLE CAME OUT OF SOCKET ON CAT HEAD. SERVICE TONG CAT HEADS AND RE-INSTALL PULL CABLE TO CAT HEAD DRUM.
BIGHORN PEAK H04 BH | 10 | 2021-11-02 22:00 | 2021-11-02 23:45 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.11 | 16884 | 16884 | 0 | STRIP OUT OF THE HOLE USING RIG TONGS DUE TO OVER TORQUED CONNECTIONS F/14,768'- T/14,270'. FILLING BACKSIDE WITH 17.0 PPG KILL MUD, CALCULATED FILL OF 1.9 BBLS/STD. TOTAL OF 50 BBLS 17.0 PPG PUMPED WHILE STRIPPING F/16,886'. MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI NOTE: HAD TO DOUBLE LINE CAT HEAD CABLE IN ORDER TO BREAK CONNECTIONS.
BIGHORN PEAK H04 BH | 10 | 2021-11-02 23:45 | 2021-11-03 02:00 | 2.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.21 | 16884 | 16884 | 0 | CONT. STRIPPING OUT F/14,270' T/9,324' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD., FLOW CHECK AT SHOE, NO FLOW MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PEAK H04 BH | 10 | 2021-11-03 02:00 | 2021-11-03 03:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.25 | 16884 | 16884 | 0 | STRIP OUT OF THE HOLE F/9,954'- T/6,851'. FILLING BACKSIDE WITH 17.0 PPG KILL MUD, CALCULATED FILL OF 1.9 BBLS/STD. TOTAL OF 50 BBLS 17.0 PPG PUMPED MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PEAK H04 BH | 10 | 2021-11-03 03:00 | 2021-11-03 04:15 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.3 | 16884 | 16884 | 0 | CONT. STRIPPING OUT F/6,851' T/3,225' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PEAK H04 BH | 10 | 2021-11-03 04:15 | 2021-11-03 04:45 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.32 | 16884 | 16884 | 0 | BULL HEAD 50 BBLS OF 17PPG KILL MUD DOWN BACKSIDE. NO CASING PRESSURE
BIGHORN PEAK H04 BH | 10 | 2021-11-03 04:45 | 2021-11-03 05:00 | 0.25 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 8.33 | 16884 | 16884 | 0 | PULL ROTATING HEAD AND INSTALL TRIP NIPPLE
BIGHORN PEAK H04 BH | 10 | 2021-11-03 05:00 | 2021-11-03 06:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.38 | 16884 | 16884 | 0 | CONT. STRIPPING OUT F/3,225' T/1,200' FILLING BACKSIDE WITH 9.1 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PEAK H04 BH | 11 | 2021-11-03 06:00 | 2021-11-03 07:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.42 | 16884 | 16884 | 0 | CONTINUE TRIPPING OUT THE HOLE F/1,200' T/BHA, FILLING BACKSIDE WITH 9.1 PPG OBM WITH CALCULATED FILL OF 1.9 BBLS/STD.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 07:00 | 2021-11-03 07:45 | 0.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 8.45 | 16884 | 16884 | 0 | RACK BACK DRILL-N-REAMER, TOP NMDC AND TOMAX THRUSTER, REMOVE MWD, BIT BOX SQUAT WAS WITHIN TOLERENCE, ATTEMPTED TO DRAIN MOTOR, BUT WOULD NOT DRAIN DUE TO MOTOR BEING LOCKED UP, BIT GRADE: 1/1-LT-G-X-2-NO-DMF, 1 MISSING CUTTER ON THE GAUGE AND 1/16” OUT OF GAUGE.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 07:45 | 2021-11-03 08:45 | 1 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 8.49 | 16884 | 16884 | 0 | PICK UP BHA #4. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13601237 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 +.005 .68 REV/GAL; 4.08' BIT TO BEND; 5.56" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-64'. BIT TO GAMMA-55'. TEST MWD= GOOD. NOTE: FLOAT AND BTI VALVE GOOD.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 08:45 | 2021-11-03 10:30 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.56 | 16884 | 16884 | 0 | TRIP IN THE HOLE F/ BHA T/ 2,940' WITH NO RETURNS, FILL PIPE, PICK UP AGITATOR ON STAND 28, ESTABLISH CIRCULATION @ GPM-262, SPM-100, SPP BEFORE AGITATOR: 562 PSI; SPP AFTER AGITATOR: 840 PSI. NOTE: COMMAND THREAD REP INSPECTING CONNECTIONS WHILE TRIPPING IN THE HOLE.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 10:30 | 2021-11-03 11:15 | 0.75 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 8.59 | 16884 | 16884 | 0 | FLOW CHECK, NO FLOW, REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD, L/D 1 BAD JOINT CET 43 DRILL PIPE (BAD BOX GOUGE ON FACE), OPEN HCR AND CLOSED ORBIT VALVE FOR STRIPPING OPERATIONS.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 11:15 | 2021-11-03 16:00 | 4.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.79 | 16884 | 16884 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/2,940' T/12,996', MAX DRAG: 25K, CHOKE: 0% / 0%, SICP= 0 PSI. NOTE: COMMAND THREAD REP INSPECTING CONNECTIONS WHILE STRIPPING IN THE HOLE, L/D 1 BAD JOINT CET 43 DRILL PIPE (BAD PIN, THREAD PROFILE OUT OF TORELENCE).
BIGHORN PEAK H04 BH | 11 | 2021-11-03 16:00 | 2021-11-03 17:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.83 | 16884 | 16884 | 0 | WHILE STRIPPING IN THE HOLE, DERRICKMAN OBSERVED ONE OF THE SHEAVES ON THE BLOCKS WAS GRINDING AND HAD A BAD WOBBLE. SERVICE TOP DRIVE, DRAWWORKS AND ST-80 WHILE INSPECTING SHEAVE AND MAKING DECISION IF IT WAS SAFE TO STRIP OUT THE HOLE TO SHOE, MONITORING SICP, SICP= 0 PSI.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 17:00 | 2021-11-03 18:00 | 1 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 8.87 | 16884 | 16884 | 0 | PICK UP AND BREAK OVER DRILL STRING TO ENSURE DS FREE. BROKE OVER AT 250K UP, 160K DOWN TRAVEL. MECHANIC'S ENROUTE, CRANE AND STRING UP CREW ON STBY. DECISION MADE IT WAS SAFE TO STRIP OUT THE HOLE TO SHOE, MONITORING SICP, SICP= 0 PSI.
BIGHORN PEAK H04 BH | 11 | 2021-11-03 18:00 | 2021-11-03 21:00 | 3 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 9 | 16884 | 16884 | 0 | STRIP OUT OF THE HOLE F/12,996' T/9684'. AT A REDUCED RATE FOR SAFETY. FILLING BACKSIDE WITH 9.1 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 175 PSI AVG CASING PRESSURE= 0 PSI NOTE: MECHANIC'S AND STRING UP CREW ARRIVED ON LOCATION AT 20:30 HRS
BIGHORN PEAK H04 BH | 11 | 2021-11-03 21:00 | 2021-11-04 03:00 | 6 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 9.25 | 16884 | 16884 | 0 | CHECK TORQUE ON SHEAVE BOLTS. OK. DECISION MADE TO MOVE DRILL LINE OVER TO UN USED SHEAVE. UNSPOOL DRAWORKS, CUT 48' OF DRILL LINE AND STRING DOWN TO BAD SHEAVE. MOVE DRILL LINE OVER FROM BAD SHEAVE TO UN USED SHEAVE AND STRING BACK UP. SPOOL UP DRAWORKS, TIGHTEN NUTS ON HORSE HEAD, CALIBRATE HI-LOW STOP POINTS. MONITOR CSG PRESSURE. MAX CASING PRESSURE= 39 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PEAK H04 BH | 11 | 2021-11-04 03:00 | 2021-11-04 03:30 | 0.5 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 9.27 | 16884 | 16884 | 0 | BULLHEAD 50 BBLS 17.0 PPG KILL MUD DOWN ANNULUS FOR SAFETY FACTOR WHILE STRIPPING IN HOLE. NO CSG PRESSURE.
BIGHORN PEAK H04 BH | 11 | 2021-11-04 03:30 | 2021-11-04 04:15 | 0.75 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 9.3 | 16884 | 16884 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/9,684' T/12,996', MAX DRAG: 25K, CHOKE: 0% / 0%, SICP= 0 PSI.
BIGHORN PEAK H04 BH | 11 | 2021-11-04 04:15 | 2021-11-04 06:00 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.37 | 16884 | 16884 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/12,996' T/14,447', MAX DRAG: 25K, CHOKE: 0% / 0%, SICP= 0 PSI. NOTE: COMMAND THREAD REP INSPECTING CONNECTIONS WHILE STRIPPING IN THE HOLE, L/D 2 BAD JOINTS CET 43 DRILL PIPE (BAD THREAD PROFILE ON PIN END).
BIGHORN PEAK H04 BH | 12 | 2021-11-04 06:00 | 2021-11-04 08:45 | 2.75 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.49 | 16884 | 16884 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/14,447' T/16,591', MAX DRAG: 70K, CHOKE: 0% / 0%, SICP= 0 PSI. ENCOUNTERED TIGHT WITH 70K DRAG @ 16,307'. NOTE: COMMAND THREAD REP INSPECTING CONNECTIONS WHILE STRIPPING IN THE HOLE, NO BAD JOINTS.
BIGHORN PEAK H04 BH | 12 | 2021-11-04 08:45 | 2021-11-04 09:15 | 0.5 | P | PRDHLLT | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 9.51 | 16884 | 16884 | 0 | SERVICE RIG AND TOP DRIVE, TORQUE AND RPM READING WERE ERATTIC. CLEAN 42 AND 19 PIN.
BIGHORN PEAK H04 BH | 12 | 2021-11-04 09:15 | 2021-11-04 10:00 | 0.75 | P | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 9.54 | 16884 | 16884 | 0 | WASH AND REAM F/ 16,591' T/ 16,884' SLOWLY STAGED UP PUMPS AND RPM F/210 T/400 GPM AND F/30 T/80 RPM, , GPM- 400, PSI- 2034, RPM- 70, TRQ- 10-14K, CHOKES- 0% / 0%, MAX CASING PRESSURE= 270 PSI, AVG CASING PRESSURE= 200 PSI, WASH AND REAM UNDER MUDCAP.
BIGHORN PEAK H04 BH | 12 | 2021-11-04 10:00 | 2021-11-04 11:30 | 1.5 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 9.6 | 16884 | 16884 | 0 | LINED UP VIA KILL LINE TO PUMP 17.0 PPG KILL MUD DOWN BACKSIDE TO KILL WELL. PUMPED A TOTAL OF 30 BBLS OF 17.0 PPG KILL MUD. CSG PRESSURE BROKE OVER @ 540 PSI AND DECREASED TO 0 PSI, ROTATING HEAD LEAKING AROUND ROTATING ASSEMBLY, PULL ROTATING HEAD AND REPLACE GASKET.
BIGHORN PEAK H04 BH | 12 | 2021-11-04 11:30 | 2021-11-04 23:15 | 11.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.09 | 16884 | 18016 | 96.3 | ROTATE DRILL LATERAL (1,132' IN 11.7 HR @ 96.75 FPH) WOB-18/22K, SPM-76/76, GPM-400, RPM 80, TQ-15K-19K, MRPM-272, TTRPM-352, SPP- 4,800/5,700 PSI, DIFF 700/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 100 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA NOTE: MOTOR STALLED OUT @ 1270 PSI DIFFERENTIAL PRESSURE, BUT TORQUE DID NOT STALL, TRQ=17K WHILE ROTATE DRILLING @ 16,935', MOTOR STALLED OUT @ 1184 PSI DIFFERENTIAL PRESSURE, BUT TORQUE DID NOT STALL, TRQ=23K WHILE ROTATE DRILLING @ 17,171', MOTOR STALLED OUT @ 1106 PSI DIFFERENTIAL PRESSURE, BUT TORQUE DID NOT STALL, TRQ=23K WHILE ROTATE DRILLING @ 17,199', PICK UP TO NEUTRAL WEIGHT, SLOWLY STAGED UP PUMPS T/400 GPM AND 30 RPM, PICK UP AND BROKE WEIGHT OVER, SPP BROKE OVER 2600 PSI. *** AT 17,503' DERRICK HAND NOTICED CHARGING PUMP VALVE WAS CLOSED, NOTIFIED DRILLER, DERRICK HAND OPENED VALVE. P/U AND RECORD NEW OFF BTTM PRESS., PREVIOUS OFF BOOTOM SPP 2500 PSI, NEW OFF BOTTOM SPP 4800 PSI
BIGHORN PEAK H04 BH | 12 | 2021-11-04 23:15 | 2021-11-05 02:30 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.23 | 18016 | 18068 | 16 | SLD DRILL LATERAL (52' IN 3.3 HRS @ 15.76 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -4800/5300 PSI, DIFF-200/500 PSI, CHOKES-0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=100 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. SLIDE DEPTHS: F/16968'-T/16983', 15', TF:160R, 12:42-13:25 F/17157'-T/17169', 12', TF:160R, 15:09-16:40 F/17,816'-T/17,831',15', TF:130R, 11:50-00:20 F/17,922'-T/17,932', 10', TF:140R, 01:06-01:40 DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA @ 17,805' CASING PRESSURE INCREASED TO 100 PSI, PUMPED 40 BBLS OF 17.0 PPG KILL MUD. PRESSURE DECREASED TO 0PSI
BIGHORN PEAK H04 BH | 12 | 2021-11-05 02:30 | 2021-11-05 03:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.25 | 18068 | 18068 | 0 | WHILE ON BOTTOM DRILLING 18,068' MD, EXPERIENCED A 4,000LB TORQUE SPIKE ALONG WITH A 1200PSI PRESSURE LOSS; WOB WENT TO ZERO, AND STRING WEIGHT INCREASED BACK TO ROTATING WEIGHT BEFORE COMING OFF BOTTOM. ATTEMPT TO PICK UP AND TROUBLESHOOT PRESSURE LOSS. PULLED 100K OVER STRING WEIGHT AND WORKED TORQUE IN AND OUT OF PIPE MULTPLE TIMES IN ORDER TO FREE STRING. ONCE FREE, ISOLATED MUD PUMPS INDIVIDUALLY TO CHECK PRESSURE, MUD PUMPS WERE 1300 PSI +- 100PSI. BRING PUMPS BACK UP TO DRILLING RATE @ 400GPM WITH 1,200 PSI LESS PRESSURE. GO BACK TO BOTTOM TO CHECK FOR DIFFERENTIAL AND EASE PARAMETERS BACK TO DRILLING RATE. PROCEED TO DRILL WITH LESS PRESSURE. EXPERIENCED INCREASED GAMMA AT SAME DEPTH. MWD TEMP. DECREASED FROM 252 DEGREES TO 178 DEGREES.
BIGHORN PEAK H04 BH | 12 | 2021-11-05 03:00 | 2021-11-05 05:15 | 2.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.34 | 18068 | 18295 | 100.9 | ROTATE DRILL LATERAL (227' IN 2.37 HR @ 95.7 FPH) WOB-18/22K, SPM-76/76, GPM-400, RPM 80, TQ-9K-14K, MRPM-272, TTRPM-352, SPP- 3,500/4,400 PSI, DIFF 700/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA
BIGHORN PEAK H04 BH | 12 | 2021-11-05 05:15 | 2021-11-05 05:30 | 0.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.35 | 18295 | 18309 | 56 | SLD DRILL LATERAL (14' IN .38 HRS @ 36.8 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -3500/4000 PSI, DIFF-200/300 PSI, CHOKES-0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. SLIDE DEPTHS: F/18,192'-T/18,206', 14', TF:150R, 04:27-04:50 DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA
BIGHORN PEAK H04 BH | 12 | 2021-11-05 05:30 | 2021-11-05 06:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 10.38 | 18309 | 18309 | 0 | SERVICE TOP DRIVE, DRAW WORKS AND ST-80
BIGHORN PEAK H04 BH | 13 | 2021-11-05 06:00 | 2021-11-05 14:30 | 8.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.73 | 18309 | 19503 | 140.5 | ROTATE DRILL LATERAL (1,194' IN 8.53 HR @ 139.92 FPH) WOB-18/22K, SPM-76/76, GPM-400, RPM 80, TQ-9K-14K, MRPM-272, TTRPM-352, SPP- 3,500/4,400 PSI, DIFF 700/900 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE 0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PEAK H04 BH | 13 | 2021-11-05 14:30 | 2021-11-05 17:15 | 2.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.84 | 19503 | 19553 | 18.2 | SLD DRILL LATERAL (50' IN 2.72 HRS @ 18.40 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -3500/4000 PSI, DIFF-200/300 PSI, CHOKES-0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. SLIDE DEPTHS: S/D F/ 18,394' T/ 18,404' TF- 160R 07:05-07:38 S/D F/ 18,854' T/ 18,874' TF- 140L 10:36-11:33 S/D F/ 19,289' T/ 19,309' TF- 20L 14:13-15:26 DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA.
BIGHORN PEAK H04 BH | 13 | 2021-11-05 17:15 | 2021-11-05 18:15 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.89 | 19553 | 19553 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80.
BIGHORN PEAK H04 BH | 13 | 2021-11-05 17:15 | 2021-11-05 17:15 | 0 | P | PRDHLCSG | MSTN | TD | MILESTONE_TD WELL | 10.84 | 19553 | 19553 |  | MILESTONE_TD WELL ON 11/05/2021 @ 17:15 HRS
BIGHORN PEAK H04 BH | 13 | 2021-11-05 18:15 | 2021-11-05 21:00 | 2.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11 | 19553 | 19553 | 0 | PERFORMED CLEAN UP CYCLE WITH WELL ON MUD CAP. PUMPED 30 BBL OBM SWEEP CIRCULATE 6 BOTTOMS UP TO LOSS ZONE, SPM-76/76, GPM-390, MRPM-265, RPM-80, CHOKES CLOSED. MAX CSG PSI WHILE CIRC-0 PSI. TQ=13/25K, SPP-4400/4700 PSI, P/U WT=200K, S/O WT=150K, ROT WT=185K
BIGHORN PEAK H04 BH | 13 | 2021-11-05 21:00 | 2021-11-06 01:00 | 4 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.17 | 19553 | 19553 | 0 | BACK REAM OUT THE HOLE F/19,553' T/17,636’, SPM-108, GPM-282, RPM-80, MRPM-192, TMRPM-272, TRQ-13/24K, SPP-4100/4200 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI AVG CASING PRESSURE ON CONNECTIONS= 0 PSI
BIGHORN PEAK H04 BH | 13 | 2021-11-06 01:00 | 2021-11-06 06:00 | 5 |  | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.38 | 19553 | 19553 | 0 | STRIP OUT THE HOLE F/17,636’ T/7,700’ WET PUMPING 1.9 BBLS/STD OF 9.1 PPG OBM CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI NOTE: PUMP 50 BBLS OF 17.0 PPG MUD DOWN THE ANNULUS AT 11,700' FOR FILL. TOTAL OF 50 BBLS 17.0 PPG OBM PUMPED DOWN ANNULUS. PUMPING CALCULATED FILL 1.9 BBLS/STD OF 10.5 PPG OBM DOWN ANNULUS
BIGHORN PEAK H04 BH | 14 | 2021-11-06 06:00 | 2021-11-06 07:30 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.44 | 19553 | 19553 | 0 | CONTINUE STRIPPING OUT THE HOLE F/7,702’ T/2,961' WET PUMPING 1.9 BBLS/STD OF 9.1 PPG OBM CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 07:30 | 2021-11-06 08:00 | 0.5 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 11.46 | 19553 | 19553 | 0 | LINED UP VIA KILL LINE TO PUMP 50 BBLS 17.0 PPG KILL MUD DOWN BACKSIDE. INITIAL CASING PRESSURE= 0 PSI, CASING PRESSURE DID NOT BUILD, CASING PRESSURE DECREASED TO 0 PSI. FLOW CHECK, NO FLOW.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 08:00 | 2021-11-06 08:30 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 11.48 | 19553 | 19553 | 0 | REMOVE ROTATING HEAD AND INSTALLED TRIP NIPPLE.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 08:30 | 2021-11-06 09:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.52 | 19553 | 19553 | 0 | TRIP OUT THE HOLE WET F/2,961' T/BHA WITH ORBIT VALVE OPEN, PUMPING 1.9 BBLS/STD OF 9.1 PPG OBM CALCULATED FILL DOWN THE BACKSIDE, L/D AGITATOR ON STAND 28. FLOW CHECK @ BHA, NO FLOW.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 09:30 | 2021-11-06 10:30 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 11.56 | 19553 | 19553 | 0 | L/D DIR BHA: X/O, TOMAX THRUSTER, AND TOP NMDC. PULL MWD, BREAK BIT AND L/D MOTOR AND REMAINING BHA. NOTE: MOTOR BEARINGS WITHIN TOLERANCE, OBSERVED CONNECTION ABOVE THE LOWER BEARING HOUSING BACKED OUT 1/16" (PICTURE ATTACHED), BIT GRADED: 1-3-BT-G-X-0-NO-TD.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 10:30 | 2021-11-06 11:00 | 0.5 | P | PRDHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 11.58 | 19553 | 19553 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELAVATORS.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 11:00 | 2021-11-06 11:30 | 0.5 |  | PRDHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 11.6 | 19553 | 19553 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 11:30 | 2021-11-06 13:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.67 | 19553 | 19553 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 13:00 | 2021-11-06 15:15 | 2.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.76 | 19553 | 19553 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1-W425 PIN x W625 BOX X-OVER, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/2,009', FILLING PIPE ON THE FLY WITH WATER, NO RETURNS.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 15:15 | 2021-11-06 15:45 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 11.78 | 19553 | 19553 | 0 | FLOW CHECK, WELL STATIC. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 15:45 | 2021-11-06 22:45 | 7 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.07 | 19553 | 19553 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/2,009' T/10,408.1' WHILE STRIPPING IN, MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY WITH WATER, NO RETURNS.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 22:45 | 2021-11-06 23:30 | 0.75 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 12.1 | 19553 | 19553 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
BIGHORN PEAK H04 BH | 14 | 2021-11-06 23:30 | 2021-11-07 06:00 | 6.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.38 | 19553 | 19553 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/10,408.1' T/19,471' A WHILE STRIPPING IN, MAX CSG PSI: 100 PSI, FILLING PIPE ON THE FLY, NO RETURNS. COMPLETE CASING DETAILS ON FOLOWING REPORT.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 06:00 | 2021-11-07 07:30 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.44 | 19553 | 19553 | 0 | CONTINUE WASHING AND REAMING PRODUCTION CASING F/19,471' T/19,514' @ 20-30 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-9/14K, SPM-100, SPP- 1600 PSI, NO RETURNS, CHOKES CLOSED; CLOSED ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD, SLACK OFF AND INSTALL ROTATING HEAD, OPEN ANNULAR, WASH AND REAM F/19,514’ T/19,540’, AND LAND ON HANGER W/160K (W/O BLOCKS) @ 19,543.4’ RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1-W425 PIN x W625 BOX X-OVER, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 T/ 9,153' (225 JTS) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER 425-625, 1- X-OVER 625-463, 1 JNT. 563 WEDGE, RAN10, 387' (218 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 1 5.5" CSG HNGR CASING SHOE @ 19,540.8' TOP OF FLOAT COLLAR @ 19,495.8' BOTTOM OF TOE SLEEVE VALVE @ 19,402.80' TOP OF TOE SLEEVE VALVE @ 19,427.9' TOP OF X-OVER @ 19,341.5, 12 JOINTS OF 13" LEFT OUT-577.65', 10 JOINTS OF 5 1/2" LEFT OUT-412.41'
BIGHORN PEAK H04 BH | 15 | 2021-11-07 07:30 | 2021-11-07 08:30 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 12.48 | 19553 | 19553 | 0 | MONITORED SICP, SICP=280, LINED UP VIA KILL LINE TO PUMP 17.0 PPG KILL MUD DOWN BACKSIDE TO KILL WELL. PUMPED A TOTAL OF 125 BBLS OF 17.0 PPG KILL MUD. CSG PRESSURE BROKE OVER @ 651 PSI AND DECREASED TO 0 PSI WHILE RIGGING DOWN FRANK'S CRT AND INSTALLING WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE, MONITOR SICP, SICP= 0 PSI.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 08:30 | 2021-11-07 10:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.54 | 19553 | 19553 | 0 | CIRCULATE 1 CASING CAPACITY WITH CHOKES CLOSED WHILE CONTINUEING TO RIG DOWN CASING TOOLS, SPM-64/64, GPM-336, SPP-2800 PSI. INITIAL CASING PRESSURE WHILE CIRCULATING= 0 PSI AND FINAL CASING PRESSURE WHILE CIRCULATING= 0 PSI, SHUT IN CASING PRESSURE= 0 PSI. HOLD PJSM WITH NINE CEMENT CREW
BIGHORN PEAK H04 BH | 15 | 2021-11-07 10:00 | 2021-11-07 13:45 | 3.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 12.7 | 19553 | 19553 | 0 | CLOSED TOP VBR'S, SWAP CIRCULATING IRON T/ CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 1ST STAGE 5/5-1/2" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 40 BBL 10.5 PPG WEIGHTED SPACER, 319 BBL 13.5 PPG 1040 SK 1.72 YIELD 35/65 POZ-CLASS H LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 378 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 8 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2400 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3400 PSI, HELD FOR 5 MIN, BLED BACK 4 BBLS. FLOATS HELD. PLUG DOWN @ 13:36 ON 11/7/2021. MAX CSG PSI= 0 PSI, AVG CASING PSI=0 PSI, CSG PRESSURE 0 PSI WITH PUMPS OFF AFTER CEMENTING.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 13:45 | 2021-11-07 14:15 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 12.72 | 19553 | 19553 | 0 | HELD PJSM, RIG DOWN CIRCULATING IRON FROM RIG FLOOR, REMOVE CHECK VALVE FROM KILL CLINE, RIG UP CIRCULATING IRON TO KILL LINE.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 14:15 | 2021-11-07 17:00 | 2.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 12.83 | 19553 | 19553 | 0 | TESTED CEMENTING LINES T/8000 PSI, PUMP 100 BBLS 17.0 PPG KILL MUD DOWN THE BACKSIDE THROUGH KILL LINE @ 1 BPM= 35 PSI & CASING PSI= 0 PSI, 2 BPM= 82 PSI & CASING PSI= 0 PSI, 3 BPM= 142 PSI & CASING PSI= 0 PSI, 4 BPM= 241 PSI & CASING PSI= 0 PSI AND 5 BPM= 1925 PSI & CASING PSI= 1592 PSI TO ESTABLISH INJECTION RATE. INITIAL CSG PSI= 0 PSI. FINAL CSG PSI=1600 PSI. PUMP 40 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 346 BBLS 1125 SK 1.72 YIELD 35/65 POZ-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 20 BBLS WATER. MAX CSG PSI= 1631 PSI W/40 BBLS LEAD CMT PUMPED @ 5 BPM, AVG CASING PSI= 600/1631 PSI, CSG PRESSURE FELL TO 0 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC-1212'.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 17:00 | 2021-11-07 18:00 | 1 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 12.88 | 19553 | 19553 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP= 0 PSI, FINAL SICP= 0 PSI
BIGHORN PEAK H04 BH | 15 | 2021-11-07 18:00 | 2021-11-07 20:00 | 2 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 12.96 | 19553 | 19553 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE FOSV AND LAY DOWN LANDING JOINT. REMOVE BAILS AND CASING ELEVATORS, AND RIG UP RIG 4.5" ELEVATORS, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 80 GPM W/100 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 20:00 | 2021-11-07 20:30 | 0.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 12.98 | 19553 | 19553 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI. RELEASE WELL AND RIG ON 11/7/2021 @ 20:30 HRS.
BIGHORN PEAK H04 BH | 15 | 2021-11-07 20:30 | 2021-11-07 20:30 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 12.98 | 19553 | 19553 |  | MILESTONE_TURN OVER TO COMPLETION ON 11/7/2021 @ 20:30
BIGHORN PEAK H04 BH | 15 | 2021-11-07 20:30 | 2021-11-07 20:30 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 12.98 | 19553 | 19553 |  | MILESTONE_WELL RELEASE ON 11/7/2021 @ 20:30
BIGHORN PEAK H04 BH | 15 | 2021-11-07 20:30 | 2021-11-07 20:30 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 12.98 | 19553 | 19553 |  | MILESTONE_RIG RELEASE ON 11/7/2021 @ 20:30
BIGHORN PLAINS H02 BH | 1 | 2021-10-03 18:00 | 2021-10-04 06:00 | 12 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 | 0 | SPLIT APART AND PREPARE SUBS FOR TRANSPORT, WASH RIG, MOVE IN AND RIG UP PATTERSON CAMP HOUSES, SPOT SUBS OVER WELL CENTER (CONFIRMED BY COMPANY REP), INSTALL CENTER STEEL, SET ODS DOG HOUSE, DRAWWORKS, PIN A-SECTION OF DERRICK TO SUBS, PIN MIDDLE AND CROWN SECTION OF DERRICK, PINNED BLOCKS TO TOP DRIVE, DRESS OUT AND STRING UP DERRICK.
BIGHORN PLAINS H02 BH | 2 | 2021-10-04 06:00 | 2021-10-05 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | DRESS OUT DERRICK AND RIG UP BACKYARD AND MOTOR PACKAGE, FINISH MOVING REMAINING EQUIPMENT. CHANGE OUT PLATES ON TOP DRIVE DOLLY AND CROWN DOLLY, STRING UP DERRICK, PERFORM DERRICK PRE-RAISE INSPECTION, RAISE DERRICK @ 02:15, SCOPE IN AND PIN MSRC'S TO SUBS, RAISE AND PIN SUBS, SUBS UP @ 03:45, SET BOP WRANGLER, REMOVE BOOSTER AND INSTALL STOMPERS, HANG OFF FLOW LINE, SET V-DOOR AND CATWALK, RIG UP AND TEST CATWALK, INSTALL CATWALK STOMPERS, RIG UP ELECTRICAL ON RIG FLOOR.
BIGHORN PLAINS H02 BH | 3 | 2021-10-05 06:00 | 2021-10-06 02:00 | 20 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | RIG UP RIG FLOOR, INSTALL ROTARY GUARD, SET FLOOR MATS, INSTALL HANDRAILS, MAKE UP VIBRATOR HOSE TO RIG FLOOR, HOOK WATER AND AIR TO RIG FLOOR INSTALL MUD LINE TO STAND PIPE ON RIG FLOOR, RIG TONGS, INSTALL COVERS ON DS, ODS AND BOOM POLE WINCHS AND SPOOL UP CABLES, DRESS SHAKERS WITH 140 SCREENS, FILL MUD TANKS WITH WATER AND MIX TREATMENT, PERFORM CRI, LAY OUT AND STRAP BHA/HWDP. NOTE: INSPECTION AND REPAIRS DONE DURING RIG MOVE: 180 DAY ALTA DRAWORKS INSPECTION, 180 DAY VFD INSPECTION, 180 DAY MUD PUMP (ALL 3 PUMPS), 90 DAY TOP DRIVE INSPECTION, 90 DAY CATWALK, 180 DAY GENERATOR, SQUARE UP HAMMER UNION IN MAST FOR KELLY HOSE, FIX BENT LADDER ON MAST, REPLACE STEPS AT ODS AND DS STAIRS, REPLACE HOIST CABLE, REPLACE BROKEN WINDOW IN ODS DOGHOUSE, REPLACE 85' SRL FROM MAST, REPLACE RELEASE VALVE ON HPU, REPAIR HOLE ON TOP OF VFD HOUSE, REPLACE TOP DRIVE DOLLY AND BLOCK DOLLY TEFLON WEAR PLATES, INSTALL SAFETY NETS ON MAST LIGHTS, REPAIR EXHAUST LEAK ON GEN #3, REPAIR DRAWORKS SLIP AND CUT REMOTE.
BIGHORN PLAINS H02 BH | 3 | 2021-10-06 02:00 | 2021-10-06 06:00 | 4 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | TROUBLESHOOT DRAWWORK BRAKES AND CHANGE OUT 37 PIN COMMUNICATION CABLE AND VERSA VALVE F/DRAWWORKS, RIG UP CELLAR PUMPS, RUN HOSES TO SHAKER GOOSENECKS AND RIG UP OFFLINE CEMENT MANIFOLD, INSTALL CONDUCTOR RISER.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 06:00 | 2021-10-06 07:30 | 1.5 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | SPOOL UP DRAWWORKS AND UNPIN TOP DRIVE.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 07:30 | 2021-10-06 10:00 | 2.5 | P | MOBDMOB | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 0 | 108 | 108 | 0 | PERFORM 90 DAY SERVICE ON TOP DRIVE.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 10:00 | 2021-10-06 12:15 | 2.25 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | CHANGE OUT SAVER SUB F/CET 43 T/4 1/2 IF, GRABBER DIES AND STABBING GUIDE.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 12:15 | 2021-10-06 13:15 | 1 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | CHANGE OUT SWIVEL PACKING, INSTALL BALES AND ELEVATORS, RUN OUT EQUIPMENT, PRESSURE TEST SURFACE EQUPMENT T/1,500 PSI, CALIBRATE DRAWWORKS. NOTE: ACCEPTED RIG ON 10-6-2021 @ 13:15.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 13:15 | 2021-10-06 15:45 | 2.5 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | CONFIRM COUNT ON THE 5” DRILL PIPE ON LOCATION (390 JOINTS). PICK UP BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 108'.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 15:45 | 2021-10-06 15:45 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 10/6/2021 @ 15:45.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 15:45 | 2021-10-06 23:15 | 7.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.31 | 108 | 2650 | 338.9 | ROTATE (2,542’ IN 7.53 HRS @ 337.6 FPH) WOB-25-35K, RPM-100, TRQ- 2/5K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-3,550/4,000 PSI, DIFF-300/450 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 30 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM.
BIGHORN PLAINS H02 BH | 4 | 2021-10-06 23:15 | 2021-10-07 01:00 | 1.75 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.39 | 2650 | 3020 | 211.4 | SLIDE (370' IN 1.8 HRS @ 205.6 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-3,550/3,700 PSI, DIFF-70/150 PSI. SLIDE DEPTHS: F/903 T/945 15' TF-240M 1901-1904 F/1025 T/1045 20' TF-250M 1916-1921 F/1120 T/1145 25' TF-270M 1932-1936 F/1214 T/1229 15' TF-270M 1947-1950 F/1600 T/1610 10' TF-HS 2036-2039 F/1685 T/1705 20' TF-HS 2050-2100 F/1783 T/1808 25' TF-HS 2112-2118 F/1873 T/1893 20' TF-HS 2130-2135 F/1965 T/1990 25' TF-HS 2146-2151 F/2057 T/2082 25' TF-HS 2202-2208 F/2150 T/2180 30' TF-20R 2218-2228 F/2243 T/2263 20' TF-20R 2238-2245 F/2337 T/2367 30' TF-HS 2256-2303 F/2431 T/2461 30' TF-HS 2315-2326 F/2526 T/2556 30' TF-HS 2336-2346 F/2620 T/2650 30' TF-HS 2356-0009
BIGHORN PLAINS H02 BH | 4 | 2021-10-07 01:00 | 2021-10-07 02:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.43 | 3020 | 3020 | 0 | PUMP 2-30 BBL GEL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-3,450 PSI.
BIGHORN PLAINS H02 BH | 4 | 2021-10-07 02:00 | 2021-10-07 02:45 | 0.75 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.46 | 3020 | 3020 | 0 | TRIP OUT OF HOLE F/3,020' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
BIGHORN PLAINS H02 BH | 4 | 2021-10-07 02:45 | 2021-10-07 03:30 | 0.75 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.49 | 3020 | 3020 | 0 | RACK BACK 3 STANDS AND A DOUBLE HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-0-NO-A-X-0-NO-TD.
BIGHORN PLAINS H02 BH | 4 | 2021-10-07 03:30 | 2021-10-07 04:15 | 0.75 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.52 | 3020 | 3020 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
BIGHORN PLAINS H02 BH | 4 | 2021-10-07 04:15 | 2021-10-07 06:00 | 1.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.59 | 3020 | 3020 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). PICK AND RUN 10 3/4" 45.5# J-55 BT&C CASING T/1,058'.
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 06:00 | 2021-10-07 08:00 | 2 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.68 | 3020 | 3020 | 0 | RUN 10 3/4" 45.5# J-55 BTC CASING F1,058' T/3,009'. RAN 39 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 100K LBS(W/O BLOCKS). SHOE- 3,009' TOP OF FLOAT COLLAR- 2,927' LEFT OUT 9 JOINTS-351.38'
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 08:00 | 2021-10-07 09:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.72 | 3020 | 3020 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-318, SPP-150. NO LOSSES.
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 09:00 | 2021-10-07 09:30 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.74 | 3020 | 3020 | 0 | RIG DOWN CRT, L/D LANDING JOINT.
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 09:30 | 2021-10-07 09:30 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.74 | 3020 | 3020 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 10/7/2021 @ 9:30
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 09:30 | 2021-10-07 12:30 | 3 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.74 | 3020 | 3020 | 0 | WALK RIG F/ BIGHORN PLAINS H02 BH T/ BIGHORN PEAK H04 BH. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 12:30 | 2021-10-07 15:00 | 2.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.74 | 3020 | 3020 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 317 BBLS 11.6 PPG LEAD CEMENT, 85 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 279 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/880 PSI PRESSURED UP T/1409 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 144 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
BIGHORN PLAINS H02 BH | 5 | 2021-10-07 15:00 | 2021-10-07 17:00 | 2 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.74 | 3020 | 3020 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD);RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
BIGHORN PLAINS H02 BH | 6 | 2021-10-17 05:00 | 2021-10-17 06:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.78 | 3020 | 3020 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK F/BIGHORN PEAK H04 BH T/BIGHORN PLAINS H02, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
BIGHORN PLAINS H02 BH | 6 | 2021-10-17 05:00 | 2021-10-17 05:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.74 | 3020 | 3020 |  | MILESTONE_RESUME WELL 1 ON 10/17/21 @ 0500
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 06:00 | 2021-10-17 07:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.82 | 3020 | 3020 | 0 | CONTINUE WALK F/BIGHORN PEAK H04 BH TO BIGHORN PLAINS HO2 BH; CENTER RIG OVER WELLHEAD
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 07:00 | 2021-10-17 07:30 | 0.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.84 | 3020 | 3020 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 07:30 | 2021-10-17 08:00 | 0.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.86 | 3020 | 3020 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, KILL LINE, HCR HOSE AND KILL LINE CHECK VALVE 250 PSI LOW AND 5000 PSI HIGH.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 08:00 | 2021-10-17 08:15 | 0.25 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.88 | 3020 | 3020 | 0 | INSTALL WEAR BUSHING, CLOSE CSG VALVE AND COVER CELLAR
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 08:15 | 2021-10-17 09:45 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 0.94 | 3020 | 3020 | 0 | PICK UP BHA #2. (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0°TS HPW .001; .166 REV/GAL; 5.97' BIT TO BEND; 8.375" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1390 PSI; 8" NMPDC.7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 11 JTS 5" HWDP, 22 STDS OF 5'' DP, DSW AGITATOR. BIT TO SENSOR-64', GAMMA-60'. TEST MWD ( GOOD TEST).
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 09:45 | 2021-10-17 10:45 | 1 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 0.98 | 3020 | 3020 | 0 | TIH F/BHA-T/2785'. HOLE GIVING PROPER DISPLACEMENT
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 10:45 | 2021-10-17 11:30 | 0.75 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.01 | 3020 | 3020 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. FILL PIPE. P/U AGITATOR AND TEST. (SPP BEFORE:620. SPP AFTER: 830. TESTED @ 337 GPM) NOTE: FLOW CHECK WAS PERFORMED PRIOR TO REMOVAL OF TRIP NIPPLE. RESULT: NO FLOW.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 11:30 | 2021-10-17 11:45 | 0.25 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.02 | 3020 | 3020 | 0 | TIH F/2785'-T/2927'. HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 11:45 | 2021-10-17 12:15 | 0.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.04 | 3020 | 3020 | 0 | DRILL SHOE TRACK F/2,927'-T/3,030' AND 10' OF NEW FORMATION, GPM-400, SPP-1,250 PSI, DP-100/200, RPM-30, WOB-10-15K, TQ-2/5K.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 12:15 | 2021-10-17 12:45 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 1.06 | 3030 | 3030 | 0 | CIRCULATE BOTTOMS UP GPM-400, SPP-1,300 PSI, RPM-30. MW IN 8.8 PPG, MW OUT 8.8 PPG.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 12:45 | 2021-10-17 13:00 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.07 | 3030 | 3030 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, 441 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD- 3,009' /TVD-2,974'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE. RESULTED IN GOOD TEST.
BIGHORN PLAINS H02 BH | 7 | 2021-10-17 13:00 | 2021-10-18 01:45 | 12.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.6 | 3030 | 7642 | 361.7 | ROT (4,612' IN 12.85 HRS @ 358.91 FPH) WOB: 10/25K, SPM: 85/85/85, GPM: 818, MMRPM:135.7, RPM-80, TRPM: 215.7, TRQ: 11K/17K, SPP: 4,100/4,634 PSI, DIFF:400-500. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/- 300' CONSISTING OF 1 PPB BENTONE 990.
BIGHORN PLAINS H02 BH | 7 | 2021-10-18 01:45 | 2021-10-18 05:00 | 3.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.74 | 7642 | 7853 | 64.9 | SLIDE (211' IN 3.15 HRS @ 66.98 FPH) WOB: 25K, SPM:85/85/85, GPM: 818, MMRPM: 135.7, SPP: 4,100/4,250 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/3,205'-T/3,213', 8', TF:80R, 13:30-13:35 F/3,490'-T/3,502', 12' TF:90R, 14:20-14:27 F/3,680'-T/3,692', 12 TF90R, 14:52-15:00 F/4,053'-T/4,068', 15' TF:70R, 15:53-15:58 F/4,614'-T/4,628', 14', TF:60L, 17:08-17:15 F/5,078'-T/5,093', 15', TF:HS, 18:16-18:28 F/5,541'-T/5,556', 15', TF:HS, 19:45-19:56 F/5,735'-T/5,750', 15', TF:HS, 20:27-20:37 F/6,206'-T/6,221', 15', TF:HS, 22:01-22:11 F/6,685'-T/6,700', 15', TF:40L, 23:35-00:01 F/6,970'-T/6,985', 15', TF: 60L, 00:50-01:10 F/7,145'-T/7,160', 15', TF:60L, 01:43-02:00 F/7,333'-T/7,348', 15', TF:30L, 02:36-02:53 F/7,519'-T/7,534', 15', TF:30L, 03:27-03:42 F/7,608'-T/7,623', 15', TF:30L, 04:00-04:19
BIGHORN PLAINS H02 BH | 7 | 2021-10-18 05:00 | 2021-10-18 05:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.75 | 7853 | 7868 | 60 | SLIDE (15' IN 0.37 HRS @ 40.5 FPH) WOB: 10-20K, SPM:110/110, GPM: 706, MMRPM: 117, SPP:3500/3,760 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/7,883'-T/7,898', 15', TF:60L, 05:15-05:37 NOTE: DRILL AT REDUCED RATE DUE TO C/O SWAB ON #1 MP/ #2 POD.
BIGHORN PLAINS H02 BH | 7 | 2021-10-18 05:15 | 2021-10-18 06:00 | 0.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.78 | 7868 | 7988 | 160 | ROT (120' IN 0.68 @ 176.47 FPH) WOB: 25/35K, SPM: 110/110, GPM: 706, MMRPM:117, RPM: 80, TRPM: 197, SPP: 3600/3800 PSI, DIFF:200/300 PUMPING 10 BBL HI-VIS SWEEPS EVERY +/- 300' CONSISTING OF 1 PPB BENTONE 990. NOTE: DRILL AT REDUCED RATE DUE TO C/O SWAB ON #1 MP/ #2 POD.
BIGHORN PLAINS H02 BH | 8 | 2021-10-18 06:00 | 2021-10-18 10:45 | 4.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.98 | 7988 | 9296 | 275.4 | ROT (1308' IN 4.7 HRS @ 278 FPH) WOB: 10/25K, SPM: 85/85/85, GPM: 818, MMRPM:135.7, RPM-80, TRPM: 215.7, TRQ: 11K/17K, SPP: 4,900/5,350 PSI, DIFF:400-500. PUMPING 10 BBL HI-VIS SWEEPS EVERY +/- 300' CONSISTING OF 1 PPB BENTONE 990. NOTE: DRILL AT REDUCED RATE DUE TO C/O SWAB ON #1 MP/ #2 POD & LOW OIL PRESSURE AND BLOWER LOSS ALARM ON #3 MP.= 1.77 HRS
BIGHORN PLAINS H02 BH | 8 | 2021-10-18 10:45 | 2021-10-18 12:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.03 | 9296 | 9400 | 83.2 | SLIDE (104' IN 1.3 HRS @ 80 FPH) WOB: 25K, SPM:85/85/85, GPM: 818, MMRPM: 135.7, SPP: 4,400/4,650 PSI, DIFF: 100/275 PSI. SLIDE DEPTHS: F/7,990'-T/8,010', 20', TF:70L, 05:58-06:15 F/8,072'-T/8,087', 15', TF:90L, 06:30-06:42 F/8,344'-T/8,364', 20' TF:120L, 07:27-07:40 F/8,446'-T/8,466', 20', TF: 130L, 08:05-08:22 F/8,541'-T/8,556', 15', TF: 180, 08:30-08:51 F/8,635'-T/8,647', 12', TF: 150R, 9:10-9:18 NOTE: DRILL AT REDUCED RATE DUE TO C/O SWAB ON #1 MP/ #2 POD & LOW OIL PRESSURE AND BLOWER LOSS ALARM ON #3 MP. C/O SWAB #2 MP/#2 POD. =.75HRS
BIGHORN PLAINS H02 BH | 8 | 2021-10-18 12:00 | 2021-10-19 04:00 | 16 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.7 | 9400 | 9928 | 33 | BUILD CURVE-SLIDE (528' IN 16 HRS @ 33 FPH) WOB: 25K, SPM:85/85/85, GPM: 818, MMRPM: 135.7, SPP: 4,900/5,250 PSI, DIFF: 100/350 PSI. SLIDE DEPTHS: F/9,400'-T/9,635', 235', TF:155M, 12:00-18:00 F/9,635'-T/9,928', 293', TF: 50L, 18:00-04:00 NOTE: DRILL AT REDUCED RATE DUE TO C/O SWAB ON #1 MP/ #1 POD= 0.58HRS
BIGHORN PLAINS H02 BH | 8 | 2021-10-19 04:00 | 2021-10-19 05:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.76 | 9928 | 9928 | 0 | PERFORM POST TD CLEAN UP CYCLE PUMPING 1-30 BBL HI-VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7.625" CASING. GPM-818, ,SPP-5,085 PSI, SHAKERS CLEAN. NOTE: SERVICE RIG WHILE CIRC: LUBE: ST-80 AND DRWKS.
BIGHORN PLAINS H02 BH | 8 | 2021-10-19 05:30 | 2021-10-19 06:00 | 0.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.78 | 9928 | 9928 | 0 | POOH W/BHA #2 F/9,928'-T/9,000'. HOLE TAKING PROPER FILL VIA TRIP TANK. HOLE CONDITIONS=SLICK
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 06:00 | 2021-10-19 07:30 | 1.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.84 | 9928 | 9928 | 0 | POOH (L/D DP) W/BHA #2 F/9,000' T/7,340'; HOLE TAKING PROPER FILL VIA TRIP TANK. HOLE CONDITIONS=SLICK.
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 07:30 | 2021-10-19 08:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.86 | 9928 | 9928 | 0 | CHANGE OUT LEAKING HYDRAULIC HOSE ON ST-80
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 08:00 | 2021-10-19 16:00 | 8 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.2 | 9928 | 9928 | 0 | POOH (L/D DP) W/BHA #2 F/7,340'-T/BHA' (@ 2,645' TIH WITH 10 STDS TO BE L/D). CONT POOH (L/D DP) T/BHA. REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE @ 3,077'; HOLE TAKING PROPER FILL VIA TRIP TANK. HOLE CONDITIONS=SLICK. NOTE: @ 2,645', TIH WITH 10 STDS, TO BE L/D. HOLE GIVING PROPER DISPLACEMENT
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 16:00 | 2021-10-19 18:00 | 2 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.28 | 9928 | 9928 | 0 | L/D HWDP & 2 STDS-6.5" DC, REMOVE MWD TOOL, DRAIN MUD MOTOR, BREAK OUT BIT AND L/D SAME. NOTE: MUD MOTOR DRAINED GOOD WITH MINIMAL SLACK; MUD MOTOR MISSING KICK PAD BIT GRADED: 0-1-CT-G-X-0-WT-TD
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 18:00 | 2021-10-19 18:30 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.3 | 9928 | 9928 | 0 | PULL WEAR BUSHING, L/D MOUSEHOLE, CLEAN AND ORGANIZE RIG FLOOR FOR CASING RUN
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 18:30 | 2021-10-19 20:00 | 1.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.36 | 9928 | 9928 | 0 | CHANGE OUT TOP VBR'S TO 7.625" CASING RAMS, PICK UP JOINT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1500 PSI
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 20:00 | 2021-10-19 21:00 | 1 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.41 | 9928 | 9928 | 0 | HOLD PJSM AND RIG UP FRANK'S CASING TOOLS & EQUIPMENT.
BIGHORN PLAINS H02 BH | 9 | 2021-10-19 21:00 | 2021-10-20 | 3 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.53 | 9928 | 9928 | 0 | M/U SHOE TRACK AND TEST FLOATS. RUN 7.625'' INTERMEDIATE CASING T/3,124', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PLAINS H02 BH | 9 | 2021-10-20 | 2021-10-20 01:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.57 | 9928 | 9928 | 0 | SERVICE CATWALK. INDEXERS STOPPED RESPONDING TO THE REMOTE ON THE RIG FLOOR. RESULT: LOOSE WIRE IN CONTROL PANEL THAT CONNECTS ON THE BARRIER CARD FOR THAT FUCNTION.
BIGHORN PLAINS H02 BH | 9 | 2021-10-20 01:00 | 2021-10-20 06:00 | 5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.78 | 9928 | 9928 | 0 | CONT. RUN 7.625'' 29.7# P-110 IC BTC INTERMEDIATE CASING F/3,124'-T/8,699', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT. TOPPING OFF FLUID IN PIPE EVERY 3,000'. NOTE: 7.625'' INTERMEDIATE CSG BREAKDOWN ON FOLLOWING REPORT.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 06:00 | 2021-10-20 07:00 | 1 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.82 | 9928 | 9928 | 0 | RUN 7.625'' INTERMEDIATE CASING F/8,699'-T/9,920.0', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT. 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 223 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG. TOTAL OF 225 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 42 LATCH ON BOW SPRING CENTRALIZERS @ 9,608' AND EVERY 4TH JT UP TO 2,404 '. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/200K (W/O BLOCKS) BTM OF FLOAT SHOE- 9,920' TOP OF FLOAT COLLAR-9,828.7'. 16 JOINTS LEFT OUT-703.95', 2-15' & 1-10' PUP JTS
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 07:00 | 2021-10-20 07:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 3.84 | 9928 | 9928 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 07:30 | 2021-10-20 08:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.89 | 9928 | 9928 | 0 | CIRCULATE CSG PRIOR TO CONDUCTING CMT OPS W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 128, 8.0 BPM, SPP: 625 PSI, NO LOSSES.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 08:30 | 2021-10-20 10:45 | 2.25 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.98 | 9928 | 9928 | 0 | ADDITIONAL CIRCULATION DUE TO WAITING ON BACK UP PUMP TRUCK. THE INITIAL BACK UP TRUCK WAS REPORTED TO HAVE "SMOKING WIRES" COMING FROM THE PUMP DISPLAY SCREEN. SPM: 128, 8.0 BPM, SPP: 625 PSI, NO LOSSES.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 10:45 | 2021-10-20 13:45 | 3 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.1 | 9928 | 9928 | 0 | PJSM. SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4,000 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.0 PPG SPACER. 292 BBL 11.8 PPG 820 SK 1.94 YIELD 50/50 POZ-SM-CLASS HMM LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPANY REP WITNESS PLUG DROP, DISPLACE WITH 451 BBLS OF 9.2 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1,900 PSI AT 4 BPM, BUMP PLUG AND INCREASE PSI 500 OVER T/2,400 PSI. HELD PRESS. FOR 5 MIN. BLED OFF PSI. BLED BACK-5 BBLS (CAL 3.6). PLUG BUMPED @ 13:19 HRS. FULL RETURNS THROUGHOUT JOB. NOTE: AFTER BLEEDING BACK FROM BUMPING PLUG, BLED BACK 5BBLS (CAL 3.6), SHUT CSG BACK IN. DECISION WAS MADE TO CONTINUE ON WITH CSG TEST. 36 BBLS SPACER TO SURFACE. ESTIMATED TOP OF CMT: 2,500'
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 13:45 | 2021-10-20 14:15 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.13 | 9928 | 9928 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. NOTE: RELEASED PRESSURE FLOATS STILL NOT HOLDING. SHUT CSG BACK IN AND DECISION WAS MADE TO LEAVE THE CMT HEAD IN PLACE AND WOC.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 14:15 | 2021-10-20 19:30 | 5.25 | U | INTHLCSG | CMT | WOC | WAIT ON CEMENT | 4.34 | 9928 | 9928 | 0 | WOC DUE TO FLOATS NOT HOLDING POST CSG TEST. ONCE REACHED THE SET TIME, OPENED HEAD AND NO FLOW WAS VISUALIZED. CONTINUED WITH OPERATIONS AS PLANNED. NOTE: WHILE WOC, THE FOLLOWING OPS WERE CONDUCTED: PRESSURE TEST CHOKE MANIFOLD, FOSV & INSIDE GREY=LOW:25O/HIGH:10K. TEST FLOOR VALVES AND BACK TO THE PUMPS=LOW:250/HIGH:6,500. PREP FLOOR AND BOP FOR INSTALATION OF VBR'S.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 19:30 | 2021-10-20 22:30 | 3 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.47 | 9928 | 9928 | 0 | R/D CMT HEAD. FLUSH THROUGH BOP AND FLOW LINE WITH WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
BIGHORN PLAINS H02 BH | 10 | 2021-10-20 22:30 | 2021-10-21 01:00 | 2.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.57 | 9928 | 9928 | 0 | REMOVE CSG RAMS AND INSTALL VBR'S. CLEAN AND INSPECT INLINE SCREEN. *INSTALLED NEW VBR PACKER ELEMENTS AND SEALS ON TOP PIPE RAMS.* NOTE: WHILE C/O RAMS, C/O SAVER SUB T/4.5'' CET43.
BIGHORN PLAINS H02 BH | 10 | 2021-10-21 01:00 | 2021-10-21 06:00 | 5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.78 | 9928 | 9928 | 0 | INSTALL TEST PLUG. TEST BOPE: 250 LOW / 10,000 HIGH. TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS. TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, AND HCR. TEST INSIDE AND OUTSIDE KILL LINE VALVES, 4" MANUAL VALVE, AND HCR 250 PSI LOW / 10,000 PSI HIGH,TEST ANNULAR W/4.5" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH. CASING VALVE VERIFIED "OPEN" DURING TEST. NOTE: WHILE ATTEMPTING TO TEST LOWER RAMS WITH 5.5'' DP, RAMS DID NOT TEST T/10K. (250 LOW TEST=GOOD). OPENED BOP TO INSPECT BTM PIPE RAMS. REMOVE VBR RAM BLOCKS AND REPLACE VBR PACKER ELEMENTS & SEALS.
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 06:00 | 2021-10-21 07:30 | 1.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.84 | 9928 | 9928 | 0 | TEST LOWER VBR RAMS WITH 4.5" AND 5.5" DP 250 PSI LOW/10,000 PSI HIGH
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 07:30 | 2021-10-21 09:30 | 2 | U | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.93 | 9928 | 9928 | 0 | ATTEMPT TO TEST BLIND RAMS 250 PSI LOW/10,000 PSI HIGH; TEST FAILED DUE TO BONNET SEAL LEAKING ON RAM DOOR; CHANGE OUT BONNET SEAL ON RAM DOORS
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 09:30 | 2021-10-21 09:45 | 0.25 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.94 | 9928 | 9928 | 0 | TEST BLIND RAMS 250 PSI LOW/10,000 PSI HIGH RESULT: GOOD TEST
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 09:45 | 2021-10-21 12:00 | 2.25 | U | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.03 | 9928 | 9928 | 0 | ATTEMPT TO TEST ORBIT VALVE AND ROTATING HEAD 250 PSI LOW/1,500 PSI HIGH; TEST FAILED; CHANGE OUT BOWL GASKET AND CHECK SURFACE EQUIPMENT FOR LEAKS; ATTEMPT 2ND TEST; TEST FAILED; DISCOVERED CHOKE LINE WAS LEAKING FROM THE BODY OF THE HOSE; REMOVE CHOKE LINE AND WAIT ON NEW LINE TO ARRIVE TO LOCATION.
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 12:00 | 2021-10-21 13:30 | 1.5 | U | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.09 | 9928 | 9928 | 0 | SLIP AND CUT 80' DRILLING LINE. RIG MANAGER PRESENT. NOTE: THIS OPERATION TOOK PLACE WHILE WAITING ON PATTERSON UTI CHOKE-LINE TO ARRIVE.
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 13:30 | 2021-10-21 14:30 | 1 | U | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.14 | 9928 | 9928 | 0 | SERVICE RIG: LUBE TD, DRWKS AND ST-80. NOTE: THIS OPERATION TOOK PLACE WHILE WAITING ON PATTERSON UTI CHOKE-LINE TO ARRIVE
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 14:30 | 2021-10-21 16:00 | 1.5 | U | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.2 | 9928 | 9928 | 0 | P/U DIR BHA #3 CURVE & LAT ASSY AND RACK BACK IN DERRICK: MOTOR- 5.5", 6/7, 11.7 STG @ 2.12° T/S HS88 -.013 .89 REV/GAL; 4.14' BIT TO BEND; 5.56" PAD OD; FLOW RANGE- 150/350 GPM; MAX DIFF-2,905 PSI; STALL TRQ-7626 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM. NOTE: THIS OPERATION TOOK PLACE WHILE WAITING ON PATTERSON UTI CHOKE-LINE TO ARRIVE
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 16:00 | 2021-10-21 18:00 | 2 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.28 | 9928 | 9928 | 0 | BEGIN PICKING UP 4.5" DP AND RACKING STANDS BACK IN DERRICK. NOTE: THIS OPERATION TOOK PLACE WHILE WAITING ON PATTERSON UTI CHOKE-LINE TO ARRIVE
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 18:00 | 2021-10-21 20:00 | 2 | U | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.36 | 9928 | 9928 | 0 | INSTALL NEW 10K 60' CHOKE HOSE FROM CHOKE MANIFOLD TO BOP.
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 20:00 | 2021-10-21 20:30 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.39 | 9928 | 9928 | 0 | TEST NEW CHOKE HOSE. 250 PSI LOW/ 10,000 PSI HIGH. RESULT: GOOD TEST. TEST ORBIT VALVE AND RT-HEAD. 250 LOW/ 1,500 PSI HIGH. RESULT: GOOD TEST
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 20:30 | 2021-10-21 21:30 | 1 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.43 | 9928 | 9928 | 0 | REMOVE RT-HEAD TEST PLUG, INSTALL WEAR BUSHING AND INSTALL TRIP NIPPLE. VERIFY CSG VALVE CLOSED.
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 21:30 | 2021-10-21 22:30 | 1 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.47 | 9928 | 9928 | 0 | MAKE UP BIT, LOAD MWD TOOL AND TIH W/BHA. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13635755 JETS 6/18S TFA: 1.491), 5.5", 6/7, 11.7 STG @ 2.12° T/S HS88 -.013 .89 REV/GAL; 4.14' BIT TO BEND; 5.56" PAD OD; FLOW RANGE- 150/350 GPM; MAX DIFF-2,905 PSI; STALL TRQ-7626 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-64'. BIT TO GAMMA-51'. TEST MWD= GOOD.
BIGHORN PLAINS H02 BH | 11 | 2021-10-21 22:30 | 2021-10-22 06:00 | 7.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.78 | 9928 | 9928 | 0 | TIH (P/U 4.5'' DP) W/ BHA #3 F/ BHA-T/2,785'. PICK UP AGITATOR. BEFORE AGITATOR: GPM-262, SPM-100, SPP-1,210 PSI; AFTER AGITATOR: SPP-1,474 PSI, CONTINUE PICKING UP AND TRIPPING IN THE HOLE F/2,785'-T/6,800'. FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 06:00 | 2021-10-22 08:45 | 2.75 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.9 | 9928 | 9928 | 0 | TIH (P/U 4.5'' DP) W/ BHA #3 F/6,800'-9,515'. FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 08:45 | 2021-10-22 09:15 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 5.92 | 9928 | 9928 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD.
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 09:15 | 2021-10-22 09:45 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.94 | 9928 | 9928 | 0 | SERVICE RIG: LUBE TD, ST-80 AND DRWKS. RIG MANAGER PRESENT.
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 09:45 | 2021-10-22 10:30 | 0.75 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.97 | 9928 | 9928 | 0 | TIH (P/U 4.5'' DP) W/ BHA #3 F/9,515'-9,828'. FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT.
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 10:30 | 2021-10-22 11:15 | 0.75 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 6 | 9928 | 9938 | 13.3 | PERFORM BOP DRILL; FILL GAS SEPARATOR; DRLD CEMENT AND TAGGED FLOAT COLLAR @ 9,828', DRILL FLOAT COLLAR AND SHOE TRACK TO 9,920', DRILL SHOE, 8' OF RATHOLE, AND 10' OF NEW FORMATION F/9,920'-T/9,938', GPM-178, SPP-1100 PSI, RPM-30, TRQ-2/7K MRPM-158, TRPM-188, DIFF-100-200 PSI. NOTE: FAN BIT TO BOTTOM AND RUN 2-5K FOR THE FIRST 10' OF NEW FORMATION DUE TO POTENTIAL DEBRIS IN HOLE
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 11:15 | 2021-10-22 12:00 | 0.75 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.03 | 9938 | 9938 | 0 | CIRCULATE BOTTOMS UP BEFORE PERFORM F.I.T., GPM-178, SPP-1,000 PSI, RPM-30, TRQ 4-5K. MUD WT IN & OUT 9.0 PPG. NOTE: CIRCULATED HIGH VISC SWEEEP BACK TO SURFACE TO ENSURE HOLE WAS CLEAN OF ANY DEBRIS DUE TO PREVIOUS MUD MOTOR MISSING KICK PAD NOTE: BIT REMAINED OUTSIDE OF CSG SHOE WHILE PERFORMING CIRCULATION.
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 12:00 | 2021-10-22 12:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.05 | 9938 | 9938 | 0 | PERFORM F.I.T. WITH 9.0 PPG OBM, 2014 PSI SURFACE PRESSURE FOR 13.0 PPG EMW, SHOE MD-9,920' / TVD-9,636'. PRESSURE BLED OFF T/2005 PSI AND STABILIZED IN 5 MINUTES. GOOD F.I.T. TEST TO 13.0 PPG EMW
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 12:30 | 2021-10-22 22:00 | 9.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.45 | 9938 | 10744 | 84.8 | BUILD CURVE-SLIDE (806' IN 9.50 HR @ 84.84 FPH) WOB-20/25K, SPM-66/66, GPM-350, MRPM-311.5, SPP-2,975/3,525 PSI, DIFF-150/550 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 42 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: F/9,938'-T/10,270', 332', TF:40L, 12:35-16:12 F/10,308'-T/10,365', 57', TF:HS, 16:35-17:12 F/10,408'-T/10,462', 54', TF:HS, 17:28-18:30 F/10,472'-T/10,556', 84', TF:HS, 18:40-19:50 F/10,596'-T/10,640', 44', TF:25R, 20:16-20:52 F/10,690'-T/10,702', 12', TF:HS, 21:33-21:48
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 12:30 | 2021-10-22 12:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.05 | 9938 | 9938 |  | MILESTONE_START CURVE SECTION ON 10/22/2021 @ 12:30
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 22:00 | 2021-10-23 03:45 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.69 | 10744 | 11632 | 154.4 | ROTATE DRILL LATERAL (888' IN 5.8 HR @ 153.1 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 7-10K, MRPM-311.5, TTRPM-391.5, SPP-3,110/4,050 PSI, DIFF 700/950 PSI, CHOKES- 0% / 60-100%, FLARE-0-4', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=50 NOTE: PUMPING 10BBL, 6 PPB CALCIUM CARBONATE, 6 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300'
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 22:00 | 2021-10-22 22:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.45 | 10744 | 10744 |  | MILESTONE_START LATERAL SECTION ON 10/22/2021 @ 22:00
BIGHORN PLAINS H02 BH | 12 | 2021-10-22 22:00 | 2021-10-22 22:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.45 | 10744 | 10744 |  | MILESTONE_END CURVE SECTION ON 10/22/2021 @ 22:00 MD:10,744' TVD:10,066'
BIGHORN PLAINS H02 BH | 12 | 2021-10-23 03:45 | 2021-10-23 06:00 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.78 | 11632 | 11725 | 41.3 | SLD DRILL LATERAL (93' IN 2.2 HRS @ 42.27 FPH) WOB-25/35K, SPM-67/67, GPM-350, MRPM-311.5, SPP-3,100/,3,800 PSI, DIFF-300/450 PSI, CHOKES- 0% / 0-60%, FLARE-0-4', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 50 PSI. SLIDE DEPTHS: F/10,849'-T/10,861', 12', TF:165R, 23:07-23:26 F/10,943'-T/10,949', 6', TF:180, 23:57-00:11 F/11,037'-T/11,052', 15', TF:20R, 00:41-01:04 F/11'224'-T/11'241', 17', TF:115R, 02:01-02:28 F/11'319'-T/11'340', 21', TF:130R, 03:01-03:24 F/11,602'-T/11,624', 22', TF:130L , 04:52-05:18
BIGHORN PLAINS H02 BH | 13 | 2021-10-23 06:00 | 2021-10-23 13:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.07 | 11725 | 13009 | 183.4 | ROTATE DRILL LATERAL 1,284' IN 7.17 HR @ 179 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 7-10K, MRPM-311.5, TTRPM-391.5, SPP-4000/4200 PSI, DIFF 800/1000 PSI, CHOKES- 0% / 100%, FLARE-5-10', NO MUD CUT, MAX CASING PRESSURE= 100 PSI, AVG CASING PRESSURE= 50 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=400 NOTE: PUMPING 10BBL, 5 PPB SUPER SEAL, 7 PPB PRO V, 5 PPB MAGMAFIBER FINE SWEEP EVERY 300'
BIGHORN PLAINS H02 BH | 13 | 2021-10-23 13:00 | 2021-10-23 15:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.16 | 13009 | 13096 | 43.5 | SLD DRILL LATERAL (87' IN 1.83 HRS @ 48 FPH) WOB-25/35K, SPM-67/67, GPM-350, MRPM-311.5, SPP-3600/3800 PSI, DIFF-400/600 PSI, CHOKES- 0% / 100-%, FLARE-5-10', NO MUD CUT SLIDE DEPTHS: F/11,985'-T/12,000', 15', TF:60R, 07:11-07:30 F/12,079'-T/12,094', 15', TF:70R, 07:55-08:15 F/12,270'-T/12,285', 15', TF:50R, 09:10-09:27 F/12,453'-T/12,468', 15', TF:140R, 10:28-10:36 F/12,739'-T/12,751', 12', TF:150L, 12:12-12:29 F/13,019'-T/13,034', 15', TF:180, 14:00-14:21
BIGHORN PLAINS H02 BH | 13 | 2021-10-23 15:00 | 2021-10-23 15:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.18 | 13096 | 13096 | 0 | SERVICE RIG: LUBE TD, ST-80 AND DRWKS. RIG MANAGER PRESENT.
BIGHORN PLAINS H02 BH | 13 | 2021-10-23 15:30 | 2021-10-24 01:45 | 10.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.6 | 13096 | 14861 | 172.2 | ROTATE DRILL LATERAL ( 1,765' IN 10.35 HR @ 170.53 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 7-10K, MRPM-311.5, TTRPM-391.5, SPP-3,520/4,450 PSI, DIFF 700/950 PSI, CHOKES- 0% / 60-100%, FLARE-15', NO MUD CUT, MAX CASING PRESSURE= 76 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=540 NOTE: PUMPING 10BBL, 5 PPB SUPER SEAL, 7 PPB PRO V, 5 PPB MAGMAFIBER FINE SWEEP EVERY 300'
BIGHORN PLAINS H02 BH | 13 | 2021-10-24 01:45 | 2021-10-24 06:00 | 4.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.78 | 14861 | 14983 | 28.7 | SLD DRILL LATERAL (122' IN 4.15 HRS @ 29.39 FPH) WOB-30/50K, SPM-67/67, GPM-350, MRPM-311.5, SPP-3,520/3,700 PSI, DIFF-100/350 PSI, CHOKES- 0% / 60-100%, FLARE-15', NO MUD CUT, MAX CASING PRESSURE=76 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 540 PSI. SLIDE DEPTHS: F/13,393'-T/13,408', 15', TF:150L, 17:10-17:25 F/13,670'-T/13,676', 6', TF:HS, 19:30-19:46 F/13,953'-T/13,970', 17', TF:65L, 21:23-21:48 F/14,047'-T/14,077', 30', TF:HS, 19:30-19:46 F/14,142'-T/14,158', 16', TF:180, 23:37-00:18 F/14,332'-T/14,339', 17', TF:165L, 01:22-01:52 F/14,520'-T/14,530', 10', TF:40R, 02:52-03:19 F/14,710'-T/14,720', 10', TF:180, 04:21-04:47
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 06:00 | 2021-10-24 11:30 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.01 | 14983 | 15760 | 141.3 | ROTATE DRILL LATERAL ( 777' IN 5.52 HR @ 141 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 7-10K, MRPM-311.5, TTRPM-391.5, SPP-3,520/4,450 PSI, DIFF 700/950 PSI, CHOKES- 0% / 30-50%, FLARE-7', NO MUD CUT, MAX CASING PRESSURE= 200 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=700. PUMPING 10BBL, 5 PPB SUPER SEAL, 7 PPB PRO V, 5 PPB MAGMAFIBER FINE SWEEP EVERY 300' NOTE: OCCURED DOWNHOLE COMMUNICATION FROM IRON ROC FRAC JOB, CAUSING A INFLUX OF WATER @ 12BBLS/ HR. MANAGMENT WAS CONTACTED.
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 11:30 | 2021-10-24 14:15 | 2.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.13 | 15760 | 15865 | 38.2 | SLD DRILL LATERAL (105' IN 2.73 HRS @ 38 FPH) WOB-30/50K, SPM-67/67, GPM-350, MRPM-311.5, SPP-3,520/3,700 PSI, DIFF-100/350 PSI SLIDE DEPTHS: F/14,998'-T/15,013', 15', TF:150R, 0620-0637 F/15,187'-T/15,202', 15', TF:180, 0738-0756 F/15,288'-T/15,308', 20', TF:90R, 0835-0908 F/15,363'-T/15,383', 20', TF:90R, 0938-10:21 F/15,564'-T/15,580', 15', TF:90R, 11:30-11:48 F/15,846'-T/15,861', 15', TF:140R. 13:40-14:15 NOTE: MANAGING THE WATER INFLUX OF 12BBLS/ HR FROM DOWNHOLE COMMUNICATION FROM IRON ROC FRAC JOB BY TRANSFERRING SYSTEM MUD FROM THE RIG MUD TANKS TO FRAC TANKS AND BRINGING OVER FRESH MUD INTO THE SYSTEM FROM DIFFERENT FRAC TANKS WHILE DRILLING AHEAD, IN CONJUCTION TO ADDING DIESEL AND MUD CHEMICALS TO SUSTAIN THE MUD PROPERTIES.
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 14:15 | 2021-10-24 15:15 | 1 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.17 | 15865 | 15865 | 0 | BACKED OUT OF DRILLSTRING DURING SLIDE, MAX TRQ 15K; SCREW BACK INTO DRILLSTRING; BACKREAM OUT OF HOLE F/15865' T/15,360', SPP-1750, GPM-160, RPM-50; SHUT IN ON CONNECTIONS, MAX SICP-900 PSI; L/D 2 BAD JTS AND REPLACE
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 15:15 | 2021-10-24 16:00 | 0.75 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 8.2 | 15865 | 15865 | 0 | WASH AND REAM F/15,360' T/15,865', SPP-2900 PSI, GPM-271, RPM-60, TRQ-13. MAX CSG PSI-503. MAX SICP-1,013
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 16:00 | 2021-10-24 16:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.22 | 15865 | 15872 | 14 | SLD DRILL LATERAL (7' IN 0.53 HRS @ 13.2 FPH) WOB-30/50K, SPM-67/67, GPM-350, MRPM-311.5, SPP-3,949/4,1780 PSI, DIFF-100/229 PSI, CHOKES- 0% / 60%, FLARE-1-5', NO MUD CUT, MAX CASING PRESSURE=243 PSI, AVG CASING PRESSURE= 155 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 786 PSI. SLIDE DEPTHS: F/15,865'-T/15,872', 7', TF:140R, 16:00-16:32 NOTE: MANAGING THE WATER INFLUX OF 12BBLS/ HR FROM DOWNHOLE COMMUNICATION FROM IRON ROC FRAC JOB BY TRANSFERRING SYSTEM MUD FROM THE RIG MUD TANKS TO FRAC TANKS AND BRINGING OVER FRESH MUD INTO THE SYSTEM FROM DIFFERENT FRAC TANKS WHILE DRILLING AHEAD, IN CONJUCTION TO ADDING DIESEL AND MUD CHEMICALS TO SUSTAIN THE MUD PROPERTIES.
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 16:30 | 2021-10-24 18:00 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.28 | 15872 | 16111 | 159.3 | ROTATE DRILL LATERAL ( 239' IN 1.47 HR @ 162.58 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 7-10K, MRPM-311.5, TTRPM-391.5, SPP-3,920/4,875 PSI, DIFF 700/975 PSI, CHOKES- 0% / 60%, FLARE-2', NO MUD CUT, MAX CASING PRESSURE= 100 PSI, AVG CASING PRESSURE= 91 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=776 PUMPING 10BBL, 5 PPB SUPER SEAL, 7 PPB PRO V, 5 PPB MAGMAFIBER FINE SWEEP EVERY 300' NOTE: THE WATER INFLUX INCREASED TO 30BBLS/ HR FROM DOWNHOLE COMMUNICATION FROM IRON ROC FRAC JOB. CONT MANAGING THIS BY TRANSFERRING SYSTEM MUD FROM THE RIG MUD TANKS TO FRAC TANKS AND BRINGING OVER FRESH MUD INTO THE SYSTEM FROM DIFFERENT FRAC TANKS WHILE DRILLING AHEAD, IN CONJUCTION TO ADDING DIESEL AND MUD CHEMICALS TO SUSTAIN THE MUD PROPERTIES.
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 18:00 | 2021-10-24 20:00 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.36 | 16111 | 16111 | 0 | P/U OFF BTM AND CIRC WHILE PREPPING MUD TANKS AND EQUIPMENT TO INDUCE DRILLING WITH WATER UNDER MUD CAP PER MANAGEMENT, DUE TO DOWNHOLE COMMUNICATION OF WATER INFLUX FROM IRON ROC FRAC JOB. GPM: 350, SPP: 3,818, RPM:80, TQ: 7.5. CSG PSI:114. RECIPROCATING DRILL STRING WHILE CONDUCTING CIRCULATING OPS. ONCE ALL PERSONNEL AND EQUIPMENT WERE IN ORDER, SHUT PUMPS DOWN AND SHUT WELL IN VIA TOP RAMS, TO MONITOR SICP. SICP=850. PUMPED 8.5 BBLS OF 17.5PPG OBM DOWN BACKSIDE VIA KILL-LINE. STAGING PUMP RATE UP (INITIAL PUMP RATE: 104 GPM, FINAL RATE: 170 GPM). SICP INCREASED TO 1,150PSI PRIOR TO BREAKING OVER. CONT. PUMP ADDITIONAL 77.7BBLS OF KILL MUD DOWN THE BACKSIDE TILL SICP DECREASED TO 120PSI. ONCE PUMPS WERE OFF SICP FELL TO ZERO. (TTL BBLS PUMPED OF 17.5# KILL MUD= 86.2 BBLS). LINED UP TO PUMP FRESH WATER DOWN DRILL STRING AND DISPLACED STRING VOL. (ADDED 1-5GAL BUCKET OF PHPA TO THE FIRST 215BBLS OF FW, TO CREATE A SPACER) NOTE: ONCE OPENED TOP RAMS, TQ BROKE OVER AT 13K
BIGHORN PLAINS H02 BH | 14 | 2021-10-24 20:00 | 2021-10-25 02:45 | 6.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.65 | 16111 | 17033 | 136.6 | ROTATE DRILL LATERAL ( 922' IN 6.68 HR @ 138.02 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 14-20K, MRPM-311.5, TTRPM-391.5, SPP-3,250/4,155 PSI, DIFF 400/700 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 NOTE: PUMP 10BBLS OF HIGH VIS SWEEP EVERY 200' OR AS NEEDED. (SWEEP CONSIST OF 10# OBM DILUTED BACK TO 9.7# WITH FRESH WATER) DRILLING UNDER MUDCAP
BIGHORN PLAINS H02 BH | 14 | 2021-10-25 02:45 | 2021-10-25 06:00 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.78 | 17033 | 17070 | 11.4 | SLD DRILL LATERAL (37' IN 3.32 HRS @ 11.1 FPH) WOB-30/50K, SPM-67/67, GPM-350, MRPM-311.5, SPP-3,400/3,685 PSI, DIFF-100/229 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI. SLIDE DEPTHS: F/16,123'-T/16,138', 15', TF:180, 20:16-20:57 F/16,310'-T/16,317', 7', TF: 180, 22:10-22:51 F/16,687'-T/16,697',10', TF:155L, 01:26-02:48 F/17,065'-T/17,070', 5', TF:20R, 05:25-06:00 DRILLING UNDER MUDCAP
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 06:00 | 2021-10-25 06:15 | 0.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.79 | 17070 | 17088 | 72 | ROTATE DRILL LATERAL ( 18' IN .25 HR @ 72 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 14-20K, MRPM-311.5, TTRPM-391.5, SPP-3,250/4,155 PSI, DIFF 400/700 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 DRILLING UNDER MUDCAP NOTE: WHILE DRILLING AHEAD THE DIFF PRESS DECREASED F/538 PSI-T/44 PSI. ATTEMPTS WERE MADE TO DRILL WITH NO SUCCESS. CONTACTED MANAGEMENT IN REGARDS TO POOH TO C/O BIT AND MOTOR.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 06:15 | 2021-10-25 06:30 | 0.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.8 | 17088 | 17088 | 0 | CIRC PRIOR TO POOH. GPM-350, SPP-3,505, RPM-80 TQ-15/21K, MRPM-311.5, TTRPM-391.5, CSG PSI-0, SICP-0, FLARE-0'.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 06:30 | 2021-10-25 09:00 | 2.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.91 | 17088 | 17088 | 0 | BACK REAM OUT THE HOLE F/17,088'-T/14,747’, SPM-67/67, GPM-350, RPM-80, MRPM-311.5,TTRPM-391.5, TRQ-10/20K, SPP-3250/3328 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI NOTE: TIGHT CONNECTIONS, HAVING TO USE RIG TONGS TO BREAK OUT.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 09:00 | 2021-10-25 09:45 | 0.75 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.94 | 17088 | 17088 | 0 | SERVICE RIG: C/O ST-80 DIES
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 09:45 | 2021-10-25 13:30 | 3.75 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.09 | 17088 | 17088 | 0 | BACK REAM OUT THE HOLE F/14,747'-T/10,744’, SPM-67/67, GPM-350, RPM-80, MRPM-311.5,TTRPM-391.5, TRQ-10/20K, SPP-3250/3328 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 13:30 | 2021-10-25 16:45 | 3.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.23 | 17088 | 17088 | 0 | STRIP OUT OF THE HOLE W/BHA#3 F/10,744'-T/2,823'. FILLING BACKSIDE WITH 10.8 PPG CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 16:45 | 2021-10-25 17:30 | 0.75 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 9.26 | 17088 | 17088 | 0 | PUMP 26 BBLS OF 10.8 PPG OBM DOWN ANNULUS TO ENSURE HOLE FULL; PERFORM FLOW CHECK PRIOR TO REMOVAL OF ROTATING HEAD (NO FLOW); REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE REMOVE RT-HEAD AND INSTALL TRIP NIPPLE @ 2,823'.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 17:30 | 2021-10-25 19:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.32 | 17088 | 17088 | 0 | POOH W/BHA #3 F/2,823'-T/BHA PUMPING CALCULATED FILL DOWN BACKSIDE NOTE: PRIOR TO BHA ENTERING THE BOP, FLOW CHECK WAS CONDUCTED. RESULT: NO FLOW.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 19:00 | 2021-10-25 20:00 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.36 | 17088 | 17088 | 0 | INSPECT MOTOR AND BREAK BIT. LAY DOWN SAME. BIT GRADE: 2-2-CT-A-X-0-PN-DMF MOTOR: NO FLUID TO DRAIN, SELF DRAINED ON THE TRIP OUT. CV JOINT BROKE INTERNALLY CAUSING FREE MOVEMENT OF BIT BOX (ABLE TO MOVE BY HAND EITHER DIRECTION.) MINIMAL SLACK.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 20:00 | 2021-10-25 21:45 | 1.75 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 9.44 | 17088 | 17088 | 0 | P/U BHA #4. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13618580 JETS 6/18S TFA: 1.491), 5.25", 6/7, 8.8 STG @ 2.12° T/S HS88 +.005 .68 REV/GAL; 4.02' BIT TO BEND; 5.62" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-60'. BIT TO GAMMA-51'. TEST MWD= GOOD.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 21:45 | 2021-10-25 22:45 | 1 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.48 | 17088 | 17088 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 22:45 | 2021-10-25 23:45 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.52 | 17088 | 17088 | 0 | TIH W/ BHA #4 F/BHA-T/2,795'. CHOKE POSITION: 0%/0%. NOTE: @ 650', SICP=23 PSI. CONT. TIH, MONITORING SICP WHILE PERFORMING TRIPPING OPS.
BIGHORN PLAINS H02 BH | 15 | 2021-10-25 23:45 | 2021-10-26 00:45 | 1 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 9.56 | 17088 | 17088 | 0 | @ 2,795' SICP INCREASED TO 244 PSI. LINE UP TO PUMP DOWN KILL-LINE. PUMPED 16.34 BBLS (262 STKS) @ SPM: 30 OF 16.6# OBM, SICP BROKE OVER @ 485 PSI. CONT. PUMP (STAGING PUMPS UP TO SPM: 55) ADDITINAL 119 BBLS (1908 STKS) TILL SICP DECREASED TO 120 PSI. TTL BBLS OF 16.6# PUMPED=135. ONCE PUMP WERE SHUT OFF, SICP FELL TO 0 PSI.
BIGHORN PLAINS H02 BH | 15 | 2021-10-26 00:45 | 2021-10-26 01:15 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.58 | 17088 | 17088 | 0 | SERVICE RIG: LUBE TD, ST-80 AND DRWKS. RIG MANAGER PRESENT. NOTE: MONITORING SICP. SICP=0 PSI
BIGHORN PLAINS H02 BH | 15 | 2021-10-26 01:15 | 2021-10-26 05:30 | 4.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.76 | 17088 | 17088 | 0 | PICK UP AGITATOR. BEFORE AGITATOR: GPM-262, SPM-100, SPP-1,618 PSI; AFTER AGITATOR: SPP-1,950 PSI, CONTINUE TRIPPING IN THE HOLE W/ BHA #4 F/2,795 -T/14,044'. CHOKE POSITION: 0%/0%. (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0 NOTE: FILLED PIPE @ 2,795' & 9,900'. (@ 9,900' DID NOT BREAK CIRCULATION)
BIGHORN PLAINS H02 BH | 15 | 2021-10-26 05:30 | 2021-10-26 05:45 | 0.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.77 | 17088 | 17088 | 0 | @ 14,044' FILL PIPE AND PUMP UP MWD TEMP. GPM-275, SPP-3,477, RPM-50, TQ-7/8K, CSG PSI-0, SICP-0 PSI. MWD TEMP- 246°
BIGHORN PLAINS H02 BH | 15 | 2021-10-26 05:45 | 2021-10-26 06:00 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.78 | 17088 | 17088 | 0 | TIH W/ BHA #4 F/14,044' -T/14,504'. CHOKE POSITION: 0%/0%. (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0
BIGHORN PLAINS H02 BH | 16 | 2021-10-26 06:00 | 2021-10-26 06:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.8 | 17088 | 17088 | 0 | TIH W/ BHA #4 F/14,504' -T/15,850'. CHOKE POSITION: 0%/0%. (NOT BLEEDING OFF DISPLACEMENT OF ANYKIND) SICP:0
BIGHORN PLAINS H02 BH | 16 | 2021-10-26 06:30 | 2021-10-26 16:00 | 9.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 10.2 | 17088 | 17088 | 0 | WASH AND REAM IN THE HOLE F/15,850'-T/17,088' GPM: 350, SPP: 4,420, RPM: 70, TQ: 12-17K. SICP: 0 NOTE: @ 16,765' ENCOUNTERED TIGHT SPOT, TORQUE STALLED @ 21K AND BEGAN TO PACK OFF. WORKED STRING TILL REGAINED ROTATIONAL MOVEMENT OF THE DRILL STRING (MAX PULL 30K OVER). PUMPED 20 BBL OBM SWEEP AND CIRC TO THE SHOE. TORQUE CONT. TO STALL OUT. WHILE PUMPING FRESH WATER DOWN THE STRING WITH 288 GPM 3600 PSI, LINED UP TO PUMP DOWN THE BACKSIDE VIA KILL-LINE 20 BBLS OF 9.5# OBM THEN CHASES WITH 30 BBLS OF 16.8# WITH THE INTENT TO "OPEN FRACTURE" (NO CSG PSI WAS OBSERVED). CONT. TO WORK STRING TO GAIN MOVEMENT WITH MINIMAL SUCCESS. AFTER PUMPING DOWN BACKSIDE, LOWERED PUMP RATE (DOWN DRILL STRING) TO 262 GPM. WORKED STRING. PUMPED ADDITIONAL 20BBLS OF 9.5# OBM DOWN BACKSIDE SIMULTANEOUSLY WITH FRESH WATER BEING PUMPED DOWN DRILL STRING TO AGAIN ASSIST WITH MOVEMENT OF CUTTINGS BED INTO FRACTURE. RESULTED IN MOVEMENT OF STRING. THEN PUMPED 2- 20BBLS OF 9.5# OBM SWEEPS DOWN THE DRILL STRING WHILE WORKING THE STAND UP (GPM-192, SPP:2800-3200, RPM:70, TQ: 14-25K, MAX STRING WT:265K). ONCE SWEEPS ENTERED THE SHOE, RACKED BACK STD, P/U A SINGLE AND CONT TO BACK REAM T/16,791'. AT THE TOP OF THE NEXT STAND, STARTED STAGING PUMPS UP TO GPM: 350, SPP: 3,795, RPM: 70, TQ:13-21K). BEGIN TO WASH AND REAM STD BACK DOWN AT A CONTROLLED RATE OF 50/100FT/HR. CONTINUE WASHING AND REAMING AT CONTROLLED RATE, SPP: 3,900, RPM: 70, GPM: 350, TQ: 15/19K
BIGHORN PLAINS H02 BH | 16 | 2021-10-26 16:00 | 2021-10-26 23:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.49 | 17088 | 17789 | 100.1 | ROTATE DRILL LATERAL ( 701' IN 7.08 HR @ 99.01 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 14-20K, MRPM-238, TTRPM-318, SPP-4,000/4,500 PSI, DIFF 400/600 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 110 PSI, AVG CASING PRESSURE= 100 PSI, MAX SICP=0 DRILLING UNDER MUDCAP NOTE: @ 17,495' CSG PRESSURE INCREASED TO 110 PSI. LINED UP VIA KILL LINE TO PUMP 16.5# KILL MUD DOWN BACKSIDE TO KILL WELL SIMULTANEOUSLY WHILE DRILLING AHEAD. PUMPED A TTL OF 72BBLS OF 16.5#. CSG PRESSURE BROKE OVER @ 415 PSI.
BIGHORN PLAINS H02 BH | 16 | 2021-10-26 23:00 | 2021-10-27 00:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.55 | 17789 | 17801 | 8 | SLD DRILL LATERAL (12' IN 1.42 HRS @ 8.45 FPH) WOB-30/50K, SPM-67/67, GPM-350, MRPM-238, SPP-3,850/4,050 PSI, DIFF-100/150 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=110 PSI, AVG CASING PRESSURE= 100 PSI, MAX SICP= 0 PSI. SLIDE DEPTHS: F/17,436'-T/17,448', 12', TF:135R, 19:27-20:52 DRILLING UNDER MUDCAP
BIGHORN PLAINS H02 BH | 16 | 2021-10-27 00:30 | 2021-10-27 01:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.57 | 17801 | 17801 | 0 | SERVICE RIG: LUBE TD, ST-80 AND DRWKS RIG MANAGER PRESENT. SICP=0
BIGHORN PLAINS H02 BH | 16 | 2021-10-27 01:00 | 2021-10-27 04:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.7 | 17801 | 18180 | 126.3 | ROTATE DRILL LATERAL ( 379' IN 2.9 HR @ 130.68 FPH) WOB-20/25K, SPM-67/67, GPM-350, RPM 50-80, TQ 14-20K, MRPM-238, TTRPM-318, SPP-4,000/4,600 PSI, DIFF 400/700 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP=0 DRILLING UNDER MUDCAP NOTE: @18,177' PUMP 5BBLS OF 9.5# HIGH VIS SWEEP (SWEEP CONSIST OF OBM & FRESH WATER).
BIGHORN PLAINS H02 BH | 16 | 2021-10-27 04:00 | 2021-10-27 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.78 | 18180 | 18200 | 10 | SLD DRILL LATERAL (20' IN 2.1 HRS @ 9.52 FPH) WOB-30/50K, SPM-67/67, GPM-350, MRPM-238, SPP-3,850/4,050 PSI, DIFF-100/150 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=110 PSI, AVG CASING PRESSURE= 100 PSI, MAX SICP= 0 PSI. SLIDE DEPTHS: F/17,811'-T/17,821', 10', TF:60R, 01:05-02:18 F/18,190'-T/18,200', 10', TF:60R, 05:07-06:00
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 06:00 | 2021-10-27 13:15 | 7.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.08 | 18200 | 18914 | 98.5 | ROTATE DRILL LATERAL (714' IN 7.23 HR @ 98.8 FPH) WOB-25/35K, SPM-67/67, GPM-350, RPM- 80, TQ 20-24K, MRPM-238, TTRPM-318, SPP- 4,400/5,200 PSI, DIFF 600/800 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 550 PSI, AVG CASING PRESSURE= 450 PSI, MAX SICP= 495 PSI. DRILLING UNDER MUDCAP
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 13:15 | 2021-10-27 14:00 | 0.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.11 | 18914 | 18929 | 20 | SLD DRILL LATERAL (15' IN .77 HRS @ 19.5 FPH) WOB-25/35K, SPM-67/67, GPM-350, MRPM-238, SPP -4100/4300 PSI, DIFF-100/200 PSI, CHOKES- 0% / 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=454 PSI, AVG CASING PRESSURE= 425 PSI, MAX SICP= 358 PSI. SLIDE DEPTHS: F/18,671'-T/18,686', 15', TF:150R, 10:45-11:31 DRILLING UNDER MUDCAP
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 14:00 | 2021-10-27 17:30 | 3.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.26 | 18929 | 18929 | 0 | PERFORMED CLEAN UP CYCLE WITH WELL ON MUD CAP. PUMPED 2-30 BBL OBM SWEEPS CIRCULATE 6 BOTTOMS UP TO LOSS ZONE, SPM-67/67, GPM-350, MRPM-238, RPM-80, CHOKES CLOSED. MAX CSG PSI WHILE CIRC-0 PSI. TQ=13/25K, SPP-4400/4700 PSI, P/U WT=200K, S/O WT=150K, ROT WT=165K NOTE: CSG PRESSURE INCREASED TO 550 PSI @ 18,929'. LINED UP VIA KILL LINE TO PUMP 17.0 PPG KILL MUD DOWN BACKSIDE TO KILL WELL. PUMPED A TOTAL OF 60 BBLS OF 17.0 PPG. CSG PRESSURE BROKE OVER @ 540 PSI AND DECREASED TO 0 PSI.
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 14:00 | 2021-10-27 14:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 11.11 | 18929 | 18929 |  | MILESTONE_TD WELL ON 10/27/2021 @ 14:00 HRS
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 17:30 | 2021-10-27 19:00 | 1.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.32 | 18929 | 18929 | 0 | BACK REAM OUT THE HOLE F/18,929' T/18,161’, SPM-108, GPM-282, RPM-80, MRPM-192, TMRPM-272, TRQ-13/24K, SPP-4100/4200 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI AVG CASING PRESSURE ON CONNECTIONS= 0 PSI
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 19:00 | 2021-10-27 20:00 | 1 | U | PRDHLCSG | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 11.36 | 18929 | 18929 | 0 | AT 18,161' ROTARY STALLED AT 24K TQ,. SPP INCREASED FROM 4200 PSI TO 7480 PSI, BLEW POP OFF ON #3 MUD PUMP. SWAP TO #2 MP AND WORKED TQ OUT OF DRILL STRING. BROUGHT PUMP & ROTARY BACK ONLINE, ROTARY STALLED AND DRILL STRING PRESSURED UP TO 6000 PSI. KILLED MUD PUMP AND WORK DRILL STRING 30-60 RPM, PIPE BECAME FREE, BUT DRILL STRING PRESSURE NEVER BLED OFF. WORK DRILL STRING AND TROUBLE SHOOT DRILL STRING PRESSURE. ATTEMPTED TO OPEN 4" TO BLEED OFF WITH NO SUCCESS, PRESSURED UP TO 7490 TO RUPTURE POP OFF PIN WITH NO SUCCESS. OPEN 2" ON #2 MUD PUMP TO BLEED OFF PRESSURE WITH SUCCESS. RACK ONE STD BACK, ATTEMPT TO BREAK CIRCULATION WITH KICK OUT SET AT 1500 PSI, FAILED TO ACHIEVE CIRCULATION.
BIGHORN PLAINS H02 BH | 17 | 2021-10-27 20:00 | 2021-10-28 02:00 | 6 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.61 | 18929 | 18929 | 0 | BACK REAMING OUT THE HOLE F/18,161' T/ 14,096’, 30 RPM NOT PUMPING DOWN DRILL STRING DUE TO BLOCKAGE. PUMPING 9.1 PPG CONTAMINATED OBM DOWN KILL LINE. CHOKES CLOSED. MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI
BIGHORN PLAINS H02 BH | 17 | 2021-10-28 02:00 | 2021-10-28 06:00 | 4 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.78 | 18929 | 18929 | 0 | STRIP OUT THE HOLE F/14,096’ T/6800’ WET PUMPING 1.9 BBLS/STD OF 9.1 PPG OBM CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI NOTE: PUMP 50 BBLS OF 17.0 PPG MUD DOWN THE ANNULUS AT 11,700' FOR FILL. TOTAL OF 50 BBLS 17.0 PPG OBM PUMPED DOWN ANNULUS. PUMPING CALCULATED FILL 1.9 BBLS/STD OF 10.5 PPG OBM DOWN ANNULUS F/7000'
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 06:00 | 2021-10-28 07:45 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.85 | 18929 | 18929 | 0 | CONTINUE STRIPPING OUT THE HOLE F/6,800' T/3,000’ WET PUMPING 1.9 BBLS/STD OF 10.5 PPG OBM CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PRESSURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 07:45 | 2021-10-28 08:15 | 0.5 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 11.88 | 18929 | 18929 | 0 | LINED UP VIA KILL LINE TO PUMP 65 BBLS 17.0 PPG KILL MUD DOWN BACKSIDE. INITIAL CASING PRESSURE= 0 PSI, CASING PRESSURE INCREASED T/245 PSI AND BROKE OVER @ 295 PSI, CASING PRESSURE DECREASED TO 0 PSI. FLOW CHECK, NO FLOW.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 08:15 | 2021-10-28 08:45 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 11.9 | 18929 | 18929 | 0 | REMOVE ROTATING HEAD AND INSTALLED TRIP NIPPLE.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 08:45 | 2021-10-28 10:15 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.96 | 18929 | 18929 | 0 | TRIP OUT THE HOLE WET F/3,000' T/BHA WET WITH ORBIT VALVE OPEN, PUMPING 1.9 BBLS/STD OF 10.5 PPG OBM CALCULATED FILL DOWN THE BACKSIDE, L/D AGITATOR ON STAND 28. FLOW CHECK @ BHA, NO FLOW.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 10:15 | 2021-10-28 11:30 | 1.25 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 12.01 | 18929 | 18929 | 0 | L/D DIR BHA: X/O, TOMAX THRUSTER, AND TOP NMDC. PULL MWD, BREAK BIT AND L/D MOTOR AND REMAINING BHA. NOTE: MOTOR WAS PARTED AND HANGING ON ROTAR CATCH APPROXIMATELY 1' BELOW THE KICK PAD. BIT GRADED: 0-1-CT-S-X-NO-TD.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 11:30 | 2021-10-28 12:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.03 | 18929 | 18929 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 12:00 | 2021-10-28 12:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 12.05 | 18929 | 18929 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELAVATORS.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 12:30 | 2021-10-28 13:45 | 1.25 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 12.1 | 18929 | 18929 | 0 | HELD PJSM, RIG UP EXPRESS 5" CASING TOOLS AND EQUIPMENT.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 13:45 | 2021-10-28 15:15 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.17 | 18929 | 18929 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1-W425 PIN x W625 BOX X-OVER, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/733', FILLING PIPE ON THE FLY WITH WATER, NO RETURNS. NOTE: REGAIN .4 BBLS/JT(CALCULATED 1.1 BBLS/JT) RETURNS @ 733'.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 15:15 | 2021-10-28 16:00 | 0.75 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 12.2 | 18929 | 18929 | 0 | LINED UP VIA KILL LINE TO PUMP 121.5 BBLS 17.0 PPG KILL MUD DOWN BACKSIDE. CASING PRESSURE BROKE OVER @ 65 PSI AND DECREASED TO 0 PSI.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 16:00 | 2021-10-28 16:15 | 0.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.21 | 18929 | 18929 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/733' T/777', FILLING PIPE ON THE FLY WITH WATER, NO RETURNS.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 16:15 | 2021-10-28 17:00 | 0.75 | U | PRDHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 12.24 | 18929 | 18929 | 0 | TROUBLE SHOOT AND REPAIR COMMUNICATIONS/POWER ISSUE WITH TORQUE GRAPH MONITOR.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 17:00 | 2021-10-28 18:15 | 1.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.29 | 18929 | 18929 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/777' T/2428', FILLING PIPE ON THE FLY WITH WATER, NO RETURNS.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 18:15 | 2021-10-28 18:45 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 12.31 | 18929 | 18929 | 0 | FLOW CHECK, WELL STATIC. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
BIGHORN PLAINS H02 BH | 18 | 2021-10-28 18:45 | 2021-10-29 00:15 | 5.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.54 | 18929 | 18929 | 0 | PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/2428' T/9,636' WHILE STRIPPING IN, MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY WITH WATER, NO RETURNS.
BIGHORN PLAINS H02 BH | 18 | 2021-10-29 00:15 | 2021-10-29 01:00 | 0.75 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 12.57 | 18929 | 18929 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
BIGHORN PLAINS H02 BH | 18 | 2021-10-29 01:00 | 2021-10-29 05:30 | 4.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.76 | 18929 | 18929 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/9,636' T/15,616' AND TAG UP, WHILE STRIPPING IN, MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY, NO RETURNS.
BIGHORN PLAINS H02 BH | 18 | 2021-10-29 05:30 | 2021-10-29 06:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.78 | 18929 | 18929 | 0 | WASH AND REAM PRODUCTION CASING F/15,616' T/15,800' @ 20 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-8/10K, SPM-100, SPP- 2350 PSI, NO RETURNS, CHOKES CLOSED.
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 06:00 | 2021-10-29 15:00 | 9 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.16 | 18929 | 18929 | 0 | CONTINUE WASHING AND REAMING PRODUCTION CASING F/15,800' T/18,885' @ 20-30 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-9/14K, SPM-100, SPP- 2600 PSI, NO RETURNS, CHOKES CLOSED; CLOSED ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD, SLACK OFF AND INSTALL ROTATING HEAD, OPEN ANNULAR, WASH AND REAM F/18,885’ T/18,912’, WASH F/18,912’ T/18,913.7’ AND LAND ON HANGER W/140K (W/O BLOCKS) @ 18,913.7’ RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1-W425 PIN x W625 BOX X-OVER, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 T/ 9,379.38' (215 JTS) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER 425-625, 1- X-OVER 625-463, 1 JNT. 563 WEDGE, 1 MRKR JNT. RAN 9,184.35' (209 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 1 5.5" CSG HNGR CASING SHOE @ 18,911.1' TOP OF FLOAT COLLAR @ 18,863.3' BOTTOM OF TOE SLEEVE VALVE @ 18,819.19' TOP OF TOE SLEEVE VALVE @ 18,794.1' TOP OF X-OVER @ 9,276.9' TOP OF MARKER JOINT ABOVE X-OVER @ 9,212.8' 12 JOINTS OF 5" LEFT OUT-526.14' 7 JOINTS OF 5 1/2" LEFT OUT-308.95'
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 15:00 | 2021-10-29 16:00 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 13.2 | 18929 | 18929 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 0 PSI.
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 16:00 | 2021-10-29 17:00 | 1 | U | PRDHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 13.24 | 18929 | 18929 | 0 | ATTEMPTED TO CIRCULATE AND CEMENT SWEDGE AND 2" LOW TORQUE VALVE ON CEMENT HEAD, STARTED LEAKING WITH 824 PSI STANDPIPE PRESSURE. REMOVED CEMENT HEAD, UNSCREWED CEMENT SWEDGE AND RE-TIGHTEN, CHANGE OUT 2" LOW TORQUE VALVE ON CEMENT HEAD, RIGGED UP CEMENT HEAD.
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 17:00 | 2021-10-29 18:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.28 | 18929 | 18929 | 0 | CIRCULATE 1 CASING CAPACITY WITH CHOKES CLOSED WHILE RIGGING DOWN CASING TOOLS, SPM-64/64, GPM-336, SPP-2800 PSI. INITIAL CASING PRESSURE WHILE CIRCULATING= 0 PSI AND FINAL CASING PRESSURE WHILE CIRCULATING= 0 PSI, SHUT IN CASING PRESSURE= 0 PSI.
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 18:00 | 2021-10-29 21:00 | 3 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 13.41 | 18929 | 18929 | 0 | HELD PJSM, CLOSED TOP VBR'S, SWAP CIRCULATING IRON T/ CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 1ST STAGE 5/5-1/2" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 40 BBL 10.5 PPG WEIGHTED SPACER, 297 BBL 13.5 PPG 1000 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 367 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 8 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 3000 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4000 PSI, HELD FOR 5 MIN, BLED BACK 5 BBLS. FLOATS HELD. PLUG DOWN @ 20:44 ON 10/29/2021. MAX CSG PSI= 532 PSI, AVG CASING PSI=75 PSI, CSG PRESSURE FELL TO 300 PSI WITH PUMPS OFF AFTER CEMENTING.
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 21:00 | 2021-10-29 21:45 | 0.75 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 13.44 | 18929 | 18929 | 0 | HELD PJSM, RIG DOWN CIRCULATING IRON FROM RIG FLOOR, REMOVE CHECK VALVE FROM KILL LINE, RIG UP CIRCULATING IRON TO KILL LINE.
BIGHORN PLAINS H02 BH | 19 | 2021-10-29 21:45 | 2021-10-30 00:15 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 13.54 | 18929 | 18929 | 0 | TESTED CEMENTING LINES T/8000 PSI, PUMP 100 BBLS 17.0 PPG KILL MUD DOWN THE BACKSIDE THROUGH KILL LINE @ 1 BPM=1180 PSI & CASING PSI= 1180 PSI, 2 BPM= 1600 PSI & CASING PSI= 1450 PSI, 3 BPM= 1920 PSI & CASING PSI= 1785 PSI, 4 BPM=2180 PSI & CASING PSI= 2140 PSI AND 5 BPM=2240 PSI & CASING PSI= 1955 PSI TO ESTABLISH INJECTION RATE. INITIAL CSG PSI= 205 PSI. FINAL CSG PSI=1000 PSI. PUMP 40 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 315 BBLS 1060 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM 13.5 PPG LEAD CEMENT, PUMP 49 BBLS 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 20 BBLS WATER. MAX CSG PSI= 1460 PSI W/10 BBLS LEAD CMT PUMPED @ 5 BPM, AVG CASING PSI= 588/1460 PSI, CSG PRESSURE FELL TO 0 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC- 1212'.
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 00:15 | 2021-10-30 01:15 | 1 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 13.58 | 18929 | 18929 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP= 0 PSI, FINAL SICP= 0 PSI.
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 01:15 | 2021-10-30 01:30 | 0.25 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 13.59 | 18929 | 18929 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE BAILS AND CASING ELEVATORS.
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 01:30 | 2021-10-30 03:30 | 2 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 13.68 | 18929 | 18929 | 0 | REMOVE FOSV AND ROTATING HEAD, LAY DOWN LANDING JOINT, RIG DOWN CSG ELEVATORS AND RIG UP RIG ELEVATORS, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 80 GPM W/100 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 03:30 | 2021-10-30 06:00 | 2.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 13.78 | 18929 | 18929 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI. RELEASE WELL AND RIG ON 10/30/2021 @ 06:00 HRS.
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 06:00 | 2021-10-30 06:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 13.78 | 18929 | 18929 |  | MILESTONE_TURN OVER TO COMPLETION ON 10/30/2021 @ 06:00
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 06:00 | 2021-10-30 06:00 | 0 | P | MOBDMOB | MSTN | WLRLS | MILESTONE_WELL RELEASE | 13.78 | 18929 | 18929 |  | MILESTONE_WELL RELEASE ON 10/30/2021 @ 06:00
BIGHORN PLAINS H02 BH | 19 | 2021-10-30 06:00 | 2021-10-30 06:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 13.78 | 18929 | 18929 |  | MILESTONE_RIG RELEASE ON 10/30/2021 @ 06:00
BOONE C 1H | 1 | 2021-06-10 06:00 | 2021-06-11 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | DRILLING CONDUCTORS, MOVING IN FRAC TANKS, SETTING UP RIG CAMPS
BOONE C 1H | 2 | 2021-06-11 06:00 | 2021-06-12 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | MOVING IN PATTERSON 285 AND 3RD PARTY EQUIPMENT. 11 TOTAL LOADS OF PATTERSON 285 ON LOCATION. (2) SHAKER ROOFS, (2) MUD TANKS, TRANSFORMER HOUSE, RIG MANAGER HOUSE, MUD PUMP #1, MUD PUMP SPACER SKID, RIG MATS, CHOKE LINES, (2) CREW QARTERS
BOONE C 1H | 1 | 2021-06-11 06:00 | 2021-06-11 06:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | BEGIN RIG MOB
BOONE C 1H | 3 | 2021-06-12 06:00 | 2021-06-13 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 0 |  | MOVING IN PATTERSON 285 CREW QUATERS, 3RD PARTY EQUIPMENT. MUD PUMPS, GENERATORS, VFD HOUSE, MUD PITS, CHOKE MANIFOLD SET. NOV SHAKERS ON LOCATION.
BOONE C 1H | 4 | 2021-06-13 06:00 | 2021-06-14 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 |  | 108 |  | MOB PATTERSON 285 FROM VICTORIA YARD WITH 5J TRUCKING. TWO CRANES ON LOCATION. 80% ON LOCATION 50% RIGGED UP. 22 LOADS FROM PATTERSON ARRIVED TODAY (70 TOTAL LOADS) SUB SET OVER BOONE C1H WELL, DRESSING OUT DERRICK. NOV WELDING SLIDES FROM PRIMARY SHAKERS TO DRYING SHAKERS AND INSTALLING SOLIDS CONTROL EQUIPMENT. SURFACE CASING ORDERED FOR WED DELIVERY
BOONE C 1H | 5 | 2021-06-14 06:00 | 2021-06-15 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | MOB PATTERSON 285 FROM VICTORIA YARD WITH 5J TRUCKING. TWO CRANES ON LOCATION. 13 LOADS FROM PATTERSON ARRIVES TODAY (83 TOTAL) 100% ON LOCATION 70% RIGGED UP. DRESS OUT DERRICK, WORK ON INSTALLING DESANDER/DESILTER. CONTINUE TO RIG UP BACK YARD. RAISED DERRICK AT 04:00
BOONE C 1H | 6 | 2021-06-15 06:00 | 2021-06-16 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 0 |  | CONTINUE TO RIG UP PATTERSON 285. RAISE SUB AT 10:30. INSTALLING DESANDER/DESILTER, DISCOVERED SUCTION LINES FOR DESANDER/DESILTER/DEGASSER WERE ALL PLUGGED WITH OBM. PATTERSON SENT ADDITIONAL ROUSTABOUTS TO ASSIST IN CLEARING LINES (COST COVERED BY PATTERSON). CLEANING PITS AND DISCOVERED LARGE AMOUNTS OF SHALE IN PIT BOTTOMS. BIG SIX ASSEMBLING BOP STACK. FOUND MISSING BOLTS ON ANNULAR AND BOLT HOLES WERE LARGER THAN SUPPLIED BOLTS, PATTERSON SENT NEW ANNULAR. BOP ASSEMBLED AND PUT IN HANDLER. MCGUIRE INSTALLING MUD GAS SEPERATOR TO PATTERSON FLOW LINES. CATWALK SET IN PLACE AT 04:00. POWERED UP RIG AND PATTERSON TROUBLE SHOOTING COMS BETWEEN RIG FLOOR AND VFD HOUSE
BOONE C 1H | 7 | 2021-06-16 06:00 | 2021-06-17 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | ESTABLISH COMMUNICATIONS BETWEEN DOG HOUSE AND VFD HOUSE. CONDUCT PRE SPUD MEETING AT 09:00. POWER UP AND RUN OUT DRAWWORKS FOR 30 MINS. SPOOL UP DRAWWORKS, INSTALL WRAPS ON HORSE HEAD, UNPIN TOP DRIVE. BRING WATER INTO RIG WATER TANK. COMMUNACTIONS FROM DOGHOUSE TO VFD FAILED, TROUBLESHOOTING ISSUE. PUT WATER IN PITS TO CLEAN PITS OF SHALE AND DISCOVERED EQUALIZER LINES WERE PLUGGED WITH OBM AND SOLIDS. REMOVED LINE FROM PIT, CLEANED OUT, AND REPLACED. REPAIRING LEAKS IN LINES AND VALVES AROUND PITS. RAN MUD PUMPS AND HAVE FAULTS IN #1 AND #2 PUMP.FUNCTION TEST CATWALK, FUNCTION TEST OKAY.
BOONE C 1H | 8 | 2021-06-17 06:00 | 2021-06-18 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | RIG UP PATTERSON 285. TROUBLESHOOT TOP DRIVE COMMS ISSUE. ESTABLISH COMMUNICATIONS WITH TOP DRIVE BUT STILL THROWING VFD FAULTS. ELECTRICIAN CONTINUES TO TROUBLE SHOOT. REPAIR GROUND FAULT ON #1 PUMP. REPLACING INVERTER ON #2 PUMP. #1 AND #3 PUMP DRESSED WITH 5-1/4" LINERS, DRESSING #2 PUMP AT REPORT TIME. TESTED LINES IN PIT, FILLED PITS WITH WATER AND SUCKED OUT WATER TO CLEAN PITS. REPAIRED TOP DRIVE COMS, ABLE TO RUN TOP DRIVE, DRAWWORKS AND PUMPS WITHOUT FAULTS. INSTALLING CORTEX SOFTWARE UPDATE.
BOONE C 1H | 9 | 2021-06-18 06:00 | 2021-06-18 10:00 | 4 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | FINISH DRESSING OUT #2 PUMP. FINISH INSTALLING CORTEX SOFTWARE. FUNCTION TEST COMPONENTS. ABLE TO CIRCULATE PUMPS BACK TO PITS AND WORK TOP DRIVE (NOTE #2 DYNAMIC BREAKING RESISTOR NEEDS TO BE REPLACED, PARTS COMING FORM TYLER YARD ETA 17:00) PREP TO BEGIN 24 HOUR RUN OUT
BOONE C 1H | 9 | 2021-06-18 10:00 | 2021-06-18 14:30 | 4.5 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | BEGIN 24 HOUR RIG RUN OUT. VFD FAULTS WHEN PUMPS ARE BROUGHT UP TO HIGHER RATES. #3 MUD PUMP HAD INVERTER FAILURE, PART COMING FROM PATTERSON. ABLE TO PUMP AT 180GPM, TURN TOP DRIVE AT 30 RPM. SLB OMRON TECH DISPATCHED TO LOCATION
BOONE C 1H | 9 | 2021-06-18 14:30 | 2021-06-18 17:00 | 2.5 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | PAUSE RIG RUN OUT AND INSTALL RESISTOR #2. FUNTION TEST AND PASSED.
BOONE C 1H | 9 | 2021-06-18 17:00 | 2021-06-19 01:30 | 8.5 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | RESUME RIG RUN OUT WITH #1&#2 PUMP WHILE WORKING ON #3 PUMP. DRAWWORKS ENCODER FAILED DURING RUN OUT. BROUGHT #3 PUMP ONLINE AT 19:00.
BOONE C 1H | 9 | 2021-06-19 01:30 | 2021-06-19 06:00 | 4.5 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | INSTALL DRAW WORKS ENCODER AND TEST. TROUBLE WITH NEW ENCODER, ELECTRICAN COMBINED OLD AND NEW ENCODER PARTS AND FUNCTION TESTED OKAY. TESTED TILL 05:30 AND FINISHING INSTALL AT REPORT TIME. PUMPS RUNNING AT 50 STOKES PER MIN. REPLACED MOTOR FOR DESANDER DESILTER, AND CLEANED AND REPAIRED CONES FOR DESANDER/DESILTER. FUNCTION TEST WALKING SYSTEM, FUNCTION TESTED OKAY.
BOONE C 1H | 10 | 2021-06-19 06:00 | 2021-06-19 09:30 | 3.5 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | FINISH REPAIRING DRAW WORKS ENCODER. RUN OUT RIG AT FULL FLOW RATE WORKING TOP DRIVE AND DRAW WORKS. DRAW WORKS ENCODER FAILED AT 9:30.
BOONE C 1H | 10 | 2021-06-19 09:30 | 2021-06-19 13:00 | 3.5 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | START PICKING UP HW DRILL PIPE. ST-80 WAS NOT FUNCTIONING CORRECTLLY. REPAIRING UNIT.
BOONE C 1H | 10 | 2021-06-19 13:00 | 2021-06-19 16:00 | 3 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | ENCODER ARRIVED FROM PATTERON YARD. INSTALLING ENCODER, REPAIRING ST-80, FINISH DRESSING OUT ALL SHAKERS. ST-80 REPAIRED,
BOONE C 1H | 10 | 2021-06-19 16:00 | 2021-06-19 18:00 | 2 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | FINISH REPAIR OF BOTH DRAW WORKS AND ST-80. FUNCTION TEST ALL, TEST OKAY. PU 3 STANDS OF 5" HW DRILL PIPE AND RACK BACK. ACCEPT RIG AT 18:00
BOONE C 1H | 10 | 2021-06-19 18:00 | 2021-06-19 21:45 | 3.75 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | ON COMPANY TIME AT 18:00, PICK UP BIT 13-1/2" ULTERRA U616S W: 6/16 JETS TFA: 1.18, MOTOR 7-3/4", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 108'.
BOONE C 1H | 10 | 2021-06-19 21:45 | 2021-06-20 02:00 | 4.25 | U | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | TEST SURFACE LINES TO/2500PSI. #2 MUD PUMP CAP LEAKING, MP-3 POP OFF SEAL LEAKING, SWIVEL PACKING LEAKING. REPAIR #3 MP AND SWIVEL PACKING. PREP TO SPUD
BOONE C 1H | 10 | 2021-06-20 02:00 | 2021-06-20 06:00 | 4 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.17 | 108 | 663 | 138.7 | ROTATE DRILL F/108' T/663' (555' IN 4 HR @ 139 FPH) WOB-10-20K, RPM-70, TRQ- 2/10K, SPM-94/0/94, GPM-700, MMRPM-116, TRPM-186, SPP-1,900/2,100 PSI, DIFF-100/300 PSI. DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH ONLY 2 PUMPS, #2 PUMP BEING REPAIRED (LINER GASKET) AS OF REPORT TIME. STAGE UP PARAMATERS FROM 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM. MAKING UP CONNECTIONS WITH TONGS DUE TO LEAK ON ST-80 THAT IS BEING REPAIRED
BOONE C 1H | 10 | 2021-06-20 02:00 | 2021-06-20 02:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | SPUD SURFACE HOLE AT 02:00
BOONE C 1H | 11 | 2021-06-20 06:00 | 2021-06-20 09:30 | 3.5 | U | SFHL | TRIP | BHA | TRIP FOR BIT / BHA | 0.31 | 663 | 663 | 0 | DRILLING AT 663' AND SAW 400 PSI PRESSURE DROP. DECISION WAS MADE TO TOOH TO INSPECT TOOLS. AT SURFACE RUBBER PARTS AND METAL WASHER WERE FOUND ON TOP OF SLEEVE. TRASH CAME FROM RIG LINES. LAY DOWN MULE SHOE SLEEVE AND MWD STRING PU NEW TOOLS. PU DROP IN DRILL PIPE SCREEN.
BOONE C 1H | 11 | 2021-06-20 09:30 | 2021-06-20 11:30 | 2 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.4 | 663 | 1495 | 416 | ROTATE (832' IN 2.0 HR @ 416 FPH) WOB-10/15K, RPM-100, TRQ- 3/4K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1600/1800 PSI
BOONE C 1H | 11 | 2021-06-20 11:30 | 2021-06-20 12:00 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.42 | 1495 | 1525 | 60 | SLIDE (30' IN .5 HRS @ 60 FPH) WOB-5K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1100/1800 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLD F/965 T/975 10' TF-255M SLD F/1055 T/1065 10' TF-255M SLD F/1335 T/1345 10' TF-255M
BOONE C 1H | 11 | 2021-06-20 12:00 | 2021-06-20 16:00 | 4 | U | SFHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 0.58 | 1525 | 1525 | 0 | MAJOR VFD FAULT WHEN ENGAGING TOP DRIVE. DISCOVERED MAIN POWER LINE FORM VFD HOUSE TO RIG FLOOR HAD SHORT. REPAIRED LINE AND FUNCTION TESTED OKAY.
BOONE C 1H | 11 | 2021-06-20 16:00 | 2021-06-20 18:00 | 2 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.67 | 1525 | 2634 | 554.5 | ROTATE (1053' IN 2.13 HR @ 493.6 FPH) WOB-10/15K, RPM-100, TRQ- 5/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1800/2100 PSI, DIFF-200/500 PSI.
BOONE C 1H | 11 | 2021-06-20 18:00 | 2021-06-20 20:00 | 2 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.75 | 2634 | 2725 | 45.5 | SLIDE (147' IN 1.87 HRS @ 78.75 FPH) WOB-3/10K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1600/2000 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SF/1525 T/1535 10' TF-255M 1600-1605 SF/1620 T/1633 13' TF-255M 1622-1627 SF/1720 T/1730 10' TF-HS 1638-1643 SF/1805 T/1815 10' TF-HS 1653-1658 SF/1900 T/1913 13' TF-20R 1707-1714 SF/1995 T/2008 13' TF-20R 1723-1727 SF/2090 T/2103 13' TF-20R 1736-1741 SF/2180 T/2190 10' TF-HS 1750-1800 SF/2190 T/2203 13' TF-20R 1800-1815 SF/2565 T/2579 14' TF- 20R 1845-1850 SF/2560 T/2574 14' TF- 20R 1905-1910 SF/2643 T/2657 14' TF- 20R 1940-1954
BOONE C 1H | 11 | 2021-06-20 20:00 | 2021-06-20 21:00 | 1 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 0.79 | 2725 | 2725 | 0 | PUMP (2) 30 BBL SWEEPS IN TANDEM AND CIRCULATE BOTTOMS, GPM=900, SPP=1350, RPM=100, TRQ=1/3K.
BOONE C 1H | 11 | 2021-06-20 21:00 | 2021-06-20 23:15 | 2.25 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.89 | 2725 | 2725 | 0 | POOH F/2725 T/389' L/D 1 JNT HWDP D.M 100 % TIED HOLE TAKING PROPER FILL C/O HOSE ON ST-80
BOONE C 1H | 11 | 2021-06-20 23:15 | 2021-06-21 00:15 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.93 | 2725 | 2725 | 0 | FLOW CHECK @ BHA NO FLOW. RACK NMDC L/D MWD TOOL M/U PUP JNT RACK BACK MOTOR
BOONE C 1H | 11 | 2021-06-21 00:15 | 2021-06-21 01:45 | 1.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.99 | 2725 | 2725 | 0 | HOLD PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT-BALES, LEVATORS, TONGS, CRT, BOWL, AND SLIPS, REMOVE CONDUCTOR RISER AND INSTALL CASING GUIDE TOOL ON CONDUCTOR.
BOONE C 1H | 11 | 2021-06-21 01:45 | 2021-06-21 06:00 | 4.25 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 1.17 | 2725 | 2725 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). THEN RUN 68 JOINTS (70 TOTAL) OF 10 3/4" 45.5# J-55 BT&C CASING T/2702.75'. RAN 35 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JOINT ALL THE WAY TO 76.8'
BOONE C 1H | 12 | 2021-06-21 06:00 | 2021-06-21 06:30 | 0.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 1.19 | 2725 | 2725 | 0 | INSTALLED STREAM FLO WELLHEAD WITH BASE PLATE AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG,TESTED WELLHEAD T/5000 PSI. SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET 110K (W/O BLOCKS) ON BASE PLATE. SHOE- 2711.3' TOP OF FLOAT COLLAR-2630.7' 5 JOINTS LEFT OUT- 197.2'
BOONE C 1H | 12 | 2021-06-21 06:30 | 2021-06-21 07:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.21 | 2725 | 2725 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOL, GPM-321, SPP-100PSI, NO LOSSES.
BOONE C 1H | 12 | 2021-06-21 07:00 | 2021-06-21 07:30 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 1.23 | 2725 | 2725 | 0 | HOLD PJSM, RIG DOWN, L/D LANDING JOINT, RIG DOWN CELLAR PUMPS.
BOONE C 1H | 12 | 2021-06-21 07:30 | 2021-06-21 08:00 | 0.5 | P | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 1.25 | 2725 | 2725 | 0 | PREP RIG TO WALK AND WALK RIG F/BOONE C 1H T/BOONE D 1H. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON. RIG UP CELLAR PUMPS FOR CEMENT JOB.
BOONE C 1H | 12 | 2021-06-21 08:00 | 2021-06-21 13:30 | 5.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1.25 | 2725 | 2725 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 296 BBLS 11.6 PPG LEAD CEMENT, 79 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 251 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/680 PSI PRESSURED UP T/1250 PSI (570 PSI OVER) @ 4 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40BBLS OF SPACER AND 110 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
BOONE C 1H | 12 | 2021-06-21 08:00 | 2021-06-21 08:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 1.25 | 2725 | 2725 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 6/21/2021 @ 8:00
BOONE C 1H | 12 | 2021-06-21 13:30 | 2021-06-21 14:30 | 1 | R | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.25 | 2725 | 2725 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD);RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
BOONE C 1H | 13 | 2021-07-05 17:00 | 2021-07-05 17:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 1.25 | 2725 | 2725 |  | MILESTONE_RESUME WELL 1 ON 7/5/21 @1700
BOONE C 1H | 13 | 2021-07-05 17:00 | 2021-07-05 19:30 | 2.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 1.35 | 2725 | 2725 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT. WALK 40' SW F/ BORGSTEDT OL 2H -T/BOONE C 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA REP.
BOONE C 1H | 13 | 2021-07-05 19:30 | 2021-07-05 22:30 | 3 | P | SFHLCSG | BOP | ND | NIPPLE DOWN BOP | 1.48 | 2725 | 2725 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD,R/U KILL LINE, CHOKE LINES, MUDLINE, FLOWLINE, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BOONE C 1H | 13 | 2021-07-05 22:30 | 2021-07-06 00:30 | 2 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.56 | 2725 | 2725 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST WELLHEAD CONNECTION & CHOKE LINE. 250 PSI LOW AND 5000 PSI HIGH.
BOONE C 1H | 13 | 2021-07-06 00:30 | 2021-07-06 01:30 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.6 | 2725 | 2725 | 0 | FINISH R/U FLOWLINE. INSTALL WEAR BUSHING.
BOONE C 1H | 13 | 2021-07-06 01:30 | 2021-07-06 04:00 | 2.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.71 | 2725 | 2725 | 0 | PICK UP (9-7/8" ULTERRA SN:56410, SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.92' BIT TO BEND; 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-69', GAMMA-59'. TEST MWD ( GOOD TEST).
BOONE C 1H | 13 | 2021-07-06 04:00 | 2021-07-06 06:00 | 2 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.79 | 2725 | 2725 | 0 | TIH F/BHA- T/2564'.
BOONE C 1H | 14 | 2021-07-06 06:00 | 2021-07-06 08:00 | 2 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.88 | 2725 | 2725 | 0 | P/U AGITATOR, REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. TEST AGITATOR: GPM-350, PSI BEFORE-650, PSI AFTER- 988
BOONE C 1H | 14 | 2021-07-06 08:00 | 2021-07-06 08:15 | 0.25 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.89 | 2725 | 2735 | 40 | DRILL SHOE TRACK AND 10' NEW FORMATION F/2,725' T/2,735', GPM-500, SPP- 1750/1955 PSI, DP- 100/200, RPM-40, TQ-3/8K
BOONE C 1H | 14 | 2021-07-06 08:15 | 2021-07-06 08:45 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.91 | 2735 | 2735 | 0 | CIRCULATE BOTTOMS UP PRIOR TO PREFORMING F.I.T. GPM:500, SPP:1680 PSI, RPM-40
BOONE C 1H | 14 | 2021-07-06 08:45 | 2021-07-06 09:00 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.92 | 2735 | 2735 | 0 | PERFORM F.I.T. WITH 9.0 PPG MUD, 364 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-2,711' / TVD-2,692'. PERFORM BOP PIT DRILL-2.5 MINUTES
BOONE C 1H | 14 | 2021-07-06 09:00 | 2021-07-06 09:15 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.93 | 2735 | 2750 | 60 | ROT(15' IN .25 HRS @ 60 FPH) WOB: 25/45K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/18K, SPP: 3600/3900 PSI, DIFF: 500/700 PSI. NOTE: CONTROL DRILL ON 2MPS DUE TO HIGH PRESSURE O-RING ON #1MP REPLACEMENT.
BOONE C 1H | 14 | 2021-07-06 09:15 | 2021-07-06 09:45 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.95 | 2750 | 2750 | 0 | RIG SERVICE: LUBE AND INSPECT TD, DRWKS, ST-80 & CROWN. RIG MANAGER PRESENT.
BOONE C 1H | 14 | 2021-07-06 09:45 | 2021-07-06 11:45 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.03 | 2750 | 3302 | 276 | ROT(552' IN 1.95 HRS @ 283.07 FPH) WOB: 25/45K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/18K, SPP: 3600/3900 PSI, DIFF: 500/700 PSI. NOTE: CONTROL DRILL ON 2MPS DUE TO HIGH PRESSURE O-RING ON #1MP REPLACEMENT.
BOONE C 1H | 14 | 2021-07-06 11:45 | 2021-07-06 12:00 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.04 | 3302 | 3328 | 104 | SLIDE (26' IN 0.30 HRS @ 86.6 FPH) WOB: 5/20K, SPM: 110/110/0, GPM: 704, MMRPM: 117, SPP: 3400/3500 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/2,950' T/2,963' TF-60R, 13', 10:21-10:31 F/3,315' T/3,328' TF-40R, 13', 11:52-12:00 NOTE: CONTROL DRILL ON 2MPS DUE TO HIGH PRESSURE O-RING ON #1MP REPLACEMENT
BOONE C 1H | 14 | 2021-07-06 12:00 | 2021-07-06 12:15 | 0.25 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.05 | 3328 | 3328 | 0 | RIG LOST POWER AND BLACKED OUT.
BOONE C 1H | 14 | 2021-07-06 12:15 | 2021-07-06 12:30 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.06 | 3328 | 3364 | 144 | ROT(36' IN .25 HRS @ 144 FPH) WOB: 25/45K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/18K, SPP: 3600/3900 PSI, DIFF: 500/700 PSI. NOTE: CONTROL DRILL ON 2MPS DUE TO HIGH PRESSURE O-RING ON #1MP REPLACEMENT.
BOONE C 1H | 14 | 2021-07-06 12:30 | 2021-07-06 13:00 | 0.5 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.08 | 3364 | 3364 | 0 | LEAK ON #3MP. WORK PIPE WHILE LOCATING VIBRATING HOSE.
BOONE C 1H | 14 | 2021-07-06 13:00 | 2021-07-06 13:30 | 0.5 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 2.1 | 3364 | 3364 | 0 | POOH F/3,364'- T/2,693', DUE TO MUDLINE FAILURE. NOTE: HOLE TAKING PROPER FILL. HOLE CONDITIONS=SLICK.
BOONE C 1H | 14 | 2021-07-06 13:30 | 2021-07-06 14:45 | 1.25 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.16 | 3364 | 3364 | 0 | MUDLINE ON MP SKID LEAKING (REMOVE TEE & REPLACE WITH VIBRATING HOSE) NOTE: C/O FUEL FILTERS ON GENS AT THE SAME TIME.
BOONE C 1H | 14 | 2021-07-06 14:45 | 2021-07-06 15:00 | 0.25 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 2.17 | 3364 | 3364 | 0 | TIH F/2,693'-T/3,364', AFTER REMOVING TEE TO BYPASS #3 MUD PUMP WITH VIBRATOR HOSE. NOTE: HOLE GIVING PROPER DISPLACMENT.
BOONE C 1H | 14 | 2021-07-06 15:00 | 2021-07-06 15:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.19 | 3364 | 3423 | 118 | ROT(59' IN .50 HRS @ 118 FPH) WOB: 25/45K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/18K, SPP: 3600/3900 PSI, DIFF: 500/700 PSI. NOTE: CONTROL DRILL ON 2MPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 14 | 2021-07-06 15:30 | 2021-07-06 19:00 | 3.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.33 | 3423 | 3423 | 0 | CIRC WITH 1 MP @ GPM:275, SPP: 703, RPM:30 TQ: 2K ,WHILE CHANGING O-RING ON 4" VALVE ON #1 MUD PUMP. ONCE VALVE WAS REMOVED, OBSERVED A WASHOUT ON THE FLANGED 90 COMING OFF THE MUD PUMP AND THE 4" MUD PUMP VALVE. WAITING ON WELDER TO REPAIR #3 HIGH PRESSURE MUD LINE-WELDER ARRIVED AT 16:00
BOONE C 1H | 14 | 2021-07-06 19:00 | 2021-07-06 20:45 | 1.75 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.41 | 3423 | 3423 | 0 | REPLACE MUDLINE ON PUMP SKID. NOTE: REMOVE TEMP MUDLINE TO INSTALL PERMANENT STEEL LINE BACK IN PLACE.
BOONE C 1H | 14 | 2021-07-06 20:45 | 2021-07-07 05:15 | 8.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.76 | 3423 | 5620 | 258.5 | ROT(2,197' IN 8.47 HRS @ 259.3 FPH) WOB: 25/45K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/18K, SPP: 3600/3900 PSI, DIFF: 500/700 PSI. NOTE: CONTROL DRILL ON 2MPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 14 | 2021-07-07 05:15 | 2021-07-07 06:00 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.79 | 5620 | 5670 | 66.7 | SLIDE (50' IN 0.78 HRS @ 64 FPH) WOB: 5/20K, SPM: 110/110/0, GPM: 704, MMRPM: 117, SPP: 3400/3500 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/4,080' T/4,090' TF-180, 10', 00:03-00:10 F/4,460' T/4,470' TF-50R, 10', 01:20-01:26 F/5,020' T/5,030' TF-40R, 10', 03:11-03:32 F/5,210' T/5,230' TF-HS, 20', 04:07-04:20 NOTE: CONTROL DRILL ON 2MPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 15 | 2021-07-07 06:00 | 2021-07-07 10:30 | 4.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.98 | 5670 | 7085 | 314.4 | ROT(1,415' IN 4.42 HRS @ 320.14 FPH) WOB: 30/35K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 15K/21K, SPP: 3800/4100 PSI, DIFF: 600/800 PSI. NOTE: DRILLING W/ 2 MUD PUMPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 15 | 2021-07-07 10:30 | 2021-07-07 11:30 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.02 | 7085 | 7265 | 180 | SLIDE (180' IN 1.08 HRS @ 166.67 FPH) WOB: 5/20K, SPM: 110/110/0, GPM: 704, MMRPM: 117, SPP: 3500/3700 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/5,865' T/5,885' TF-130R, 20', 06:30-06:45 F/6,435' T/6,555' TF-30R, 20', 08:20-08:35 F/6,815' T/6,835' TF-30L, 20', 09:40-10:00 F/7,090' T/7,110' TF-HS, 20', TIME-10:45-11:00 NOTE: DRILLING WITH 2MUD PUMPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 15 | 2021-07-07 11:30 | 2021-07-07 13:15 | 1.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.09 | 7265 | 7610 | 197.1 | ROT(345' IN 1.72 HRS @ 200.58 FPH) WOB: 30/35K, SPM: 88/88/88, GPM: 850, MMRPM: 141, RPM-80, TRPM: 221, TRQ: 15K/21K, SPP: 5400/5800 PSI, DIFF: 700/1000 PSI.
BOONE C 1H | 15 | 2021-07-07 13:15 | 2021-07-07 13:45 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.11 | 7610 | 7650 | 80 | SLIDE (40' IN .58 HRS @ 68.96 FPH) WOB: 5/15K, SPM: 88//88/88, GPM: 850, MMRPM: 141, SPP: 4800/5000 PSI, DIFF: 150/300 PSI. SLIDE DEPTHS: F/7,370' T/7,410' TF-HS, 40', TIME-12:00-12:35
BOONE C 1H | 15 | 2021-07-07 13:45 | 2021-07-07 16:00 | 2.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.21 | 7650 | 8345 | 308.9 | ROT(695' IN 2.33 HRS @ 298.28 FPH) WOB: 30/35K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 15K/21K, SPP: 3800/4100 PSI, DIFF: 600/800 PSI. NOTE: DRILLING W/ 2 MUD PUMPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP
BOONE C 1H | 15 | 2021-07-07 16:00 | 2021-07-07 16:45 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.24 | 8345 | 8405 | 80 | SLIDE (60' IN .75 HRS @ 80 FPH) WOB: 5/20K, SPM: 110/110/0, GPM: 704, MMRPM: 117, SPP: 3500/3700 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/7,650' T/7,680' TF-30L 30', TIME 13:18-13:40 F/7,935' T/7,965' TF-50L, 30', 14:27-14:50 NOTE: DRILLING WITH 2MUD PUMPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 15 | 2021-07-07 16:45 | 2021-07-07 17:00 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.25 | 8405 | 8469 | 256 | ROT(64' IN .38 HRS @ 168.42 FPH) WOB: 30/35K, SPM: 88/88/88, GPM: 850, MMRPM: 141, RPM-80, TRPM: 221, TRQ: 15K/21K, SPP: 5400/5800 PSI, DIFF: 700/1000 PSI.
BOONE C 1H | 15 | 2021-07-07 17:00 | 2021-07-07 17:45 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.28 | 8469 | 8499 | 40 | SLIDE (30' IN .80 HRS @ 37.5 FPH) WOB: 5/15K, SPM: 88//88/88, GPM: 850, MMRPM: 141, SPP: 4800/5000 PSI, DIFF: 150/300 PSI. SLIDE DEPTHS: F/8,405' T/8,435' TF-HS, 30', TIME-16:23-16:51
BOONE C 1H | 15 | 2021-07-07 17:45 | 2021-07-07 22:00 | 4.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.46 | 8499 | 9619 | 263.5 | ROT(1,120' IN 4.38 HRS @ 255.70 FPH) WOB: 30/35K, SPM: 110/110/0, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 15K/21K, SPP: 3800/4175 PSI, DIFF: 600/800 PSI. NOTE: DRILLING W/ 2 MUD PUMPS DUE TO C/O OF PULSATION DAMPENER DISCHARGE BLOCK AND 4'' LINE ON #1MP.
BOONE C 1H | 15 | 2021-07-07 22:00 | 2021-07-07 23:45 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.53 | 9619 | 9686 | 38.3 | SLIDE (67' IN .1.80 HRS @ 37.22 FPH) WOB: 5/20K, SPM: 110/110/0, GPM: 704, MMRPM: 117, SPP: 3500/3875 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/8,499' T/8,530' TF-30R, 31', 17:34-18:00 F/9,155' T/9,175' TF-35M, 20', 20:00-20:44 F/9,340' T/9,356' TF-10M, 16' 21:28-22:06 NOTE: DRILLING WITH 2MUD PUMPS DUE TO PULSATION DAMPENER DISCHARGE FLANGE LEAKING ON #1MP.
BOONE C 1H | 15 | 2021-07-07 23:45 | 2021-07-08 04:15 | 4.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.72 | 9686 | 9801 | 25.6 | START BUILDING INT. CURVE ON 7/7/21 @ 23:45 (9,686'MD / 9,482'TVD) SLIDE: 115' IN 4.5 HRS @ 25.5 FPH) WOB-5/12K, SPM-110/110/0, GPM-704, MMRPM-117, SPP-3500/3875 PSI, DIFF-100/175 PSI. NOTE: DRILLING WITH 2MUD PUMPS DUE TO MAKING REPAIRS ON PULSATION DAMPENER DISCHARGE LINE ON #1MP.
BOONE C 1H | 15 | 2021-07-08 04:15 | 2021-07-08 04:45 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.74 | 9801 | 9801 | 0 | SERVICE RIG: LUBE TD, ST-80, DRWKS. RIG MANAGER PRESENT
BOONE C 1H | 15 | 2021-07-08 04:45 | 2021-07-08 06:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.79 | 9801 | 9815 | 11.2 | CONTINUE BUILDING INT. CURVE: SLIDE: 14' IN 1.25 HRS @ 11.2 FPH) WOB-5/12K, SPM-110/110/0, GPM-704, MMRPM-117, SPP-3500/3875 PSI, DIFF-100/175 PSI. NOTE: DRILLING WITH 2MUD PUMPS DUE TO MAKING REPAIRS ON PULSATION DAMPENER DISCHARGE LINE ON #1MP.
BOONE C 1H | 16 | 2021-07-08 06:00 | 2021-07-08 08:30 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.9 | 9815 | 9893 | 31.2 | CONTINUE BUILDING INT. CURVE: SLIDE: 78' IN 2.5 HRS @ 31.2 FPH) WOB-5/12K, SPM-110/110/0, GPM-704, MMRPM-117, SPP-3500/3875 PSI, DIFF-100/175 PSI. NOTE: DRILLING WITH 2MUD PUMPS DUE TO MAKING REPAIRS ON PULSATION DAMPENER DISCHARGE LINE ON #1MP.
BOONE C 1H | 16 | 2021-07-08 08:30 | 2021-07-08 09:45 | 1.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.95 | 9893 | 10030 | 109.6 | ROT(137' IN 1.25 HRS @ 109.6 FPH) WOB: 30/35K, SPM: 90/90/90, GPM: 850, MMRPM: 141, RPM-30, TRPM: 171, TRQ: 15K/21K, SPP: 5400/5580 PSI, DIFF: 300/450 PSI.
BOONE C 1H | 16 | 2021-07-08 09:45 | 2021-07-08 10:45 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.99 | 10030 | 10030 | 0 | CONDUCT POST TD CLEAN UP CYCLE. PUMPED 1- 30BBLS SWEEP. GPM:900 SPP:5300 RPM:30 TQ:16K NOTE: FLOW CHECK WAS CONDUCTED PRIOR TO PUMPIMG SLUG. RESULTED IN NO FLOW
BOONE C 1H | 16 | 2021-07-08 10:45 | 2021-07-08 16:30 | 5.75 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.23 | 10030 | 10030 | 0 | PUMP SLUG & POOH W/BHA F/10,030' T/2,527' NOTE: HOLE TAKING PROPER FILL. HOLE CONDITIONS: SLICK
BOONE C 1H | 16 | 2021-07-08 16:30 | 2021-07-08 16:45 | 0.25 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 4.24 | 10030 | 10030 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. NOTE: FOW CHECK WAS CONDUCTED PRIOR TO PULLING RT-HEAD. RESULT: NO FLOW
BOONE C 1H | 16 | 2021-07-08 16:45 | 2021-07-08 17:00 | 0.25 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.25 | 10030 | 10030 | 0 | L/D AGITATOR AND POOH T/BHA NOTE: HOLE TAKING PROPER FILL
BOONE C 1H | 16 | 2021-07-08 17:00 | 2021-07-08 18:30 | 1.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.31 | 10030 | 10030 | 0 | RACKED BACK 2 STANDS OF 6.5" DRILL COLLARS, LAID DOWN TOP MONEL, REMOVED MWD TOOL, PICKED UP PUP JT, P/U AND DRAINED MUD MOTOR, BROKE OUT BIT, AND LAID DOWN MOTOR. PICKED UP NEW MOTOR AND RACKED BACK. NOTE: FLOW CHECK WAS CONDUCTED PRIOR TO BHA ENTERING THE BOP. RESULTED IN NO FLOW. HOLE TAKING PROPER. HOLE CONDITONS: SLICK
BOONE C 1H | 16 | 2021-07-08 18:30 | 2021-07-08 19:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.33 | 10030 | 10030 | 0 | SERVICE RIG: LUBE TD, ST-80 AND DRWKS.
BOONE C 1H | 16 | 2021-07-08 19:00 | 2021-07-08 19:15 | 0.25 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.34 | 10030 | 10030 | 0 | REMOVE WEAR BUSHING. NOTE: NO FLOW
BOONE C 1H | 16 | 2021-07-08 19:15 | 2021-07-08 20:45 | 1.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.41 | 10030 | 10030 | 0 | HOLD PJSM WITH CSG CREW & RIG CREW. R/U BUTCHES CASING TOOLS AND EQUIPMENT.
BOONE C 1H | 16 | 2021-07-08 20:45 | 2021-07-08 21:30 | 0.75 | P | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 4.44 | 10030 | 10030 | 0 | MONITOR SICP. PRESSURE INCREASED 180PSI. BLED PRESSURE OFF AND MONITORED FLOW VIA TRIP TANK. WELL FLOWING @ 2.38BPH. CONTACTED MANAGMENT. THE DECISION WAS MADE TO R/D CSG TOOLS & TIH W/BHA & DP, CIRC AND INCREASE MUD WIEGHT F/9.5PPG-T/10.0PPG, PRIOR TO CONTINUING WITH CSG OPS.
BOONE C 1H | 16 | 2021-07-08 21:30 | 2021-07-08 22:30 | 1 | U | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.48 | 10030 | 10030 | 0 | R/D CSG CREW AND INSTALL WEAR BUSHING.
BOONE C 1H | 16 | 2021-07-08 22:30 | 2021-07-09 | 1.5 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.54 | 10030 | 10030 | 0 | PICK UP (9-7/8" ULTERRA SN:56410, SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.92' BIT TO BEND; 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 1-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP.
BOONE C 1H | 16 | 2021-07-09 | 2021-07-09 05:30 | 5.5 | U | INTHLCSG | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 4.77 | 10030 | 10030 | 0 | TIH F/BHA- T/750' (FILL PIPE EVERY 30 STDS). REMOVE TRIP NIPPLE, REPLACE BOWL GASKET & INSTALL RT-HEAD (NO FLOW WAS OBSERVED). HOLE GIVING PROPER DISPLACEMENT WHILE TIH. CONTINUE TIH F/750'-T/10,030' (FILL PIPE EVERY 30 STDS).
BOONE C 1H | 16 | 2021-07-09 05:30 | 2021-07-09 06:00 | 0.5 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.79 | 10030 | 10030 | 0 | CIRCULATE THROUGH 2 FULLY OPEN CHOKES (CHOKE POSITION:100% & ORBIT VALVE CLOSED) @ GPM:160, SPP:175, RPM:30, TQ:12K. NOTE: CURRENT MW: 9.5
BOONE C 1H | 17 | 2021-07-09 06:00 | 2021-07-09 07:15 | 1.25 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.84 | 10030 | 10030 | 0 | CIRC THROUGH CHOKE (#1 CHOKE POSITION @ 59%, #2 CHOKE @ 0%) @ GPM:500, SPP:1,675, RPM:30, TQ:10.5. MW:9.5. MAX CSG PRESSURE WHILE CIRC:381 PSI
BOONE C 1H | 17 | 2021-07-09 07:15 | 2021-07-09 08:30 | 1.25 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.9 | 10030 | 10030 | 0 | ONCE INITIAL B/U WAS SUCCESSFULLY CIRC OUT VIA CHOKE, OPENED UP ORBIT VALVE AND CONTINUED TO CIRC VIA FLOWLINE. STAGING MPS UP TO 900 GPM. SPP:3,580, RPM:30, TQ:10. MW:9.8.
BOONE C 1H | 17 | 2021-07-09 08:30 | 2021-07-09 09:00 | 0.5 | U | INTHLCSG | TEST | MTPRES | MONITOR PRESSURE | 4.92 | 10030 | 10030 | 0 | SHUT DOWN PUMPS AND CLOSED ORBIT VALVE TO MONITOR SICP. NO INCREASE TO SICP. SICP: 0. NOTE: ROTATION OF DRILL STRING WAS CONDUCTED EVERY 5 MINS @ 30 RPM.
BOONE C 1H | 17 | 2021-07-09 09:00 | 2021-07-09 11:45 | 2.75 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.03 | 10030 | 10030 | 0 | OPEN ORBIT VALVE AND COMMENCED TO CIRCULATING VIA FLOWLINE @ GPM:900, SPP:4,500, RPM:30, TQ:10. WHILE RAISING MW F/9.8PPG -T/10.0PPG.
BOONE C 1H | 17 | 2021-07-09 11:45 | 2021-07-09 12:00 | 0.25 | U | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 5.04 | 10030 | 10030 | 0 | FLOW CHECK PRIOR TO PUMPING SLUG. RESULT: NO FLOW
BOONE C 1H | 17 | 2021-07-09 12:00 | 2021-07-09 17:00 | 5 | U | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 5.25 | 10030 | 10030 | 0 | PUMP SLUG & POOH W/BHA F/10,030' T/BHA. REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. (PRIOR TO PULLING RT-HEAD, FLOW CHECK WAS CONDUCTED. RESULT: WELL STATIC. NOTE: HOLE TAKING PROPER FILL. HOLE CONDITIONS: SLICK
BOONE C 1H | 17 | 2021-07-09 17:00 | 2021-07-09 17:45 | 0.75 | U | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 5.28 | 10030 | 10030 | 0 | RACKED BACK 2 STANDS OF 6.5" DRILL COLLARS, MUD MOTOR & BIT. NOTE: FLOW CHECK WAS CONDUCTED PRIOR TO BHA ENTERING THE BOP. RESULTED IN NO FLOW. HOLE TAKING PROPER. HOLE CONDITONS: SLICK
BOONE C 1H | 17 | 2021-07-09 17:45 | 2021-07-09 18:00 | 0.25 | U | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 5.29 | 10030 | 10030 | 0 | REMOVE WEAR BUSHING
BOONE C 1H | 17 | 2021-07-09 18:00 | 2021-07-09 22:00 | 4 | U | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 5.46 | 10030 | 10030 | 0 | HOLD PJSM WITH ALL INVOLVED PERSONNEL. R/U CSG CREW TOOLS AND EQUIPMENT. AS WELL AS C/O TOP RAMS ON BOP TO 7.625'' CSG RAMS. TEST DOOR SEALS TO 1,200PSI. RESULT: GOOD TEST. NOTE: WHILE RIGGING UP CSG CREW AND C/O RAMS, SICP INCREASED TO 80 PSI. BLEED OFF TO TRIP TANK AND MONITOR WELL. DECISION WAS MADE TO CONTINUE WITH CSG OPS.
BOONE C 1H | 17 | 2021-07-09 22:00 | 2021-07-10 06:00 | 8 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.79 | 10030 | 10030 | 0 | RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JT OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 192 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG T/ 8,433', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FREE FLOATING), AND INSTALLED 41 LATCH ON BOW SPRING CENTRALIZERS @ 9,708.2' AND EVERY 4TH JT UP TO 2,508.5'. NOTE: TAKING DISPLACEMENT RETURNS INTO THE TRIP TANK. HOLE GIVING PROPER DISPLACEMENT.
BOONE C 1H | 18 | 2021-07-10 06:00 | 2021-07-10 07:45 | 1.75 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.86 | 10030 | 10030 | 0 | RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JT OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 35 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG T/ 10,017.4', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FREE FLOATING), AND INSTALLED 41 LATCH ON BOW SPRING CENTRALIZERS @ 9,708.2' AND EVERY 4TH JT UP TO 2,508.5'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/185K (W/O BLOCKS). FLOAT SHOE-10,015.5' TOP OF FLOAT COLLAR-9,926.4' NOTE: WELL STARTED FLOWING WHILE MAKING UP LANDING JOINT, LANDED CASING AND SHUT WELL IN. 15 JOINTS LEFT OUT- 658.81' NOTE: AFTER LANDING CSG WELL WAS FLOWING. SHUT WELL IN AND PREPARED TO CIRC GAS OUT VIA CHOKE. SICP:180.
BOONE C 1H | 18 | 2021-07-10 07:45 | 2021-07-10 09:00 | 1.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.92 | 10030 | 10030 | 0 | CIRC B/U THROUGH THE CHOKE VIA CRT, STAGING PUMP RATE UP TO 7.5BBL/MIN. SPP:573, MAX CSG PSI:642 PSI. MW:10.1 PPG. NOTE: INIITIAL SICP=160 PSI
BOONE C 1H | 18 | 2021-07-10 09:00 | 2021-07-10 09:15 | 0.25 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 5.93 | 10030 | 10030 | 0 | R/D CSG CREW TOOLS AND CRT. R/U CMT HEAD AND LINES.
BOONE C 1H | 18 | 2021-07-10 09:15 | 2021-07-10 10:15 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.97 | 10030 | 10030 | 0 | OPEN WELL UP AND CIRC DOWN FLOWLINE VIA CMT HEAD @ 7.5BBL/MIN. SPP:548, CSG PSI:0 MW:10.1 NOTE: WHILE ON THE FINISHING END OF THE CIRCULATION, HELD PJSM WITH ALL INVOLVED PERSONNEL IN REGARDS TO INT. CEMENT OPS.
BOONE C 1H | 18 | 2021-07-10 10:15 | 2021-07-10 13:30 | 3.25 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.97 | 10030 | 10030 | 0 | SWAP & TEST LINES T/4,000 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 308 BBLS 11.8 PPG 890 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT, 78 BBLS 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES,DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 456 BBLS OF 9.3 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 2280 PSI AT 4 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/2780 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI(4 BBLS)-FLOATS HELD. FINISHED CEMENTING @ 13:15 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. NOTE: 40 BBLS OF SPACER AND 3 BBLS OF CEMENT TO SURFACE.
BOONE C 1H | 18 | 2021-07-10 13:30 | 2021-07-10 14:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.99 | 10030 | 10030 | 0 | TEST 7.625'' CASING T/3,500 PSI FOR 30 MIN.
BOONE C 1H | 18 | 2021-07-10 14:00 | 2021-07-10 16:00 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 6.07 | 10030 | 10030 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON. FLUSH THROUGH BOP AND FLOW LINE WITH SUGAR WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
BOONE C 1H | 18 | 2021-07-10 16:00 | 2021-07-10 18:00 | 2 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 6.16 | 10030 | 10030 | 0 | N/D BOPE, INSTALL WEATHER CAP AND SECURE WELL, INSTALL CELLAR PLATE COVER ON WELL BOONE C 1H. NOTE: WELL SECURE AND WELL RELEASED ON 7/10/2021 @ 1800 HOURS. WELL HOLD OPERATIONS 2 ON 7-10-2021 @ 18:00 HOURS.
BOONE C 1H | 18 | 2021-07-10 18:00 | 2021-07-10 18:00 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 6.16 | 10030 | 10030 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 7-10-2021 @ 18:00
BOONE C 1H | 19 | 2021-07-25 18:00 | 2021-07-25 18:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 6.16 | 10030 | 10030 |  | MILESTONE_RESUME WELL OPERATIONS 2 ON 7/25/2021 @ 1800
BOONE C 1H | 19 | 2021-07-25 18:00 | 2021-07-25 19:30 | 1.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 6.22 | 10030 | 10030 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK 20' TO THE SOUTH, FROM BOONE D 1H TO BOONE C 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA REP. MAKE UP FLOW LINE TO MANIFOLD, SKID CATWALK AND SET V-DOOR
BOONE C 1H | 19 | 2021-07-25 19:30 | 2021-07-25 21:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 6.28 | 10030 | 10030 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BOONE C 1H | 19 | 2021-07-25 21:00 | 2021-07-26 06:00 | 9 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.66 | 10030 | 10030 | 0 | BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW /10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 7000 HIGH, TEST ANNULAR 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ROTATING HEAD AND ORBIT VALVE TO 1500 PSI. REMOVE TEST PLUG AND RIG DOWN TESTERS. NOTE: WHILE ATTEMPTING TO TEST CHECK VALVE, INITIAL TEST FAILED DUE TO O-RING NOT BEING INSTALLED. RIG UNABLE TO LOCATE. RIG MANAGER HAD ONE DELIVERED TO THE RIG. INSTALLED NEW O-RING AND TESTED GOOD. ALSO, #2 SUPER CHOKE FAILED FIRST TEST, DISASSEMBLED CHOKE & INSPECTED SAME. REASSEMBLED AND TESTED SAME. TEST RESULT: GOOD.
BOONE C 1H | 20 | 2021-07-26 06:00 | 2021-07-26 06:45 | 0.75 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 6.69 | 10030 | 10030 | 0 | R/D TESTERS, INSTALL WEAR BUSHING, AND PERFORM ACCUMULATOR DRAW DOWN TEST.
BOONE C 1H | 20 | 2021-07-26 06:45 | 2021-07-26 08:15 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 6.75 | 10030 | 10030 | 0 | CUT/SLIP DRILL LINE
BOONE C 1H | 20 | 2021-07-26 08:15 | 2021-07-26 09:15 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.79 | 10030 | 10030 | 0 | RIG SERVICE
BOONE C 1H | 20 | 2021-07-26 09:15 | 2021-07-26 09:45 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 6.81 | 10030 | 10030 | 0 | INSTALL 4.5" DRILL PIPE STABBING GUIDE ON TOP DRIVE AND INSTALL TRIP NIPPLE.
BOONE C 1H | 20 | 2021-07-26 09:45 | 2021-07-26 12:15 | 2.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.92 | 10030 | 10030 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13601237 JETS 6/18S TFA: 1.491), 5", 6/7L, 8.8 STG @ 2.12° SLICK; 0.68 REV/GAL; 4.03' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5 1/4" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, 5" TOMAX, X/0, 2 STANDS DP, REAMER, 26 STANDS DP, AGITATOR, 33 STANDS DP AND ON DEMAND AGITATOR. BIT TO SVY-69'. BIT TO GAMMA-56'. TEST MWD (TEST GOOD)
BOONE C 1H | 20 | 2021-07-26 12:15 | 2021-07-26 17:30 | 5.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.14 | 10030 | 10030 | 0 | TRIP IN HOLE F/BHA T/9,720'. HOLE GIVING PROPER DISPLACEMENT ON TRIP IN. PICK UP AGITATOR @ 2,784'. BEFORE AGITATOR-1030. PSI AFTER AGITATOR-1275 PSI
BOONE C 1H | 20 | 2021-07-26 17:30 | 2021-07-26 18:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 7.16 | 10030 | 10030 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
BOONE C 1H | 20 | 2021-07-26 18:00 | 2021-07-26 19:30 | 1.5 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 7.22 | 10030 | 10040 | 6.7 | DRILL OUT SHOE TRACK AND 10' NEW FORMATION T/10,040'. GPM:223, SPP:2,470, DIFF:300/500, WOB:15K, RPM:35, MMRPM:152, TRPM:187 TQ:10/12K
BOONE C 1H | 20 | 2021-07-26 19:30 | 2021-07-26 20:30 | 1 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 7.26 | 10040 | 10040 | 0 | CIRCULATE BOTTOMS UP, GPM-300, SPP-2,358 PSI, RPM:45, TQ:9
BOONE C 1H | 20 | 2021-07-26 20:30 | 2021-07-26 20:45 | 0.25 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 7.27 | 10040 | 10040 | 0 | PERFORM F.I.T. WITH 9.2 PPG MUD, 1,988 PSI SURFACE PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,017' I TVD-9,807'. PRESSURE BLED OFF T/1,980 PSI IN 3 MINUTES, PRESSURE STABILIZED @ 1,980 PSI. NOTE: RECORDED CASING PRESSURE FROM PASON CASING PRESSURE.
BOONE C 1H | 20 | 2021-07-26 20:45 | 2021-07-26 20:45 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 7.27 | 10040 | 10040 |  | MILESTONE_START CURVE ON 7-26-2021 @ 20:45 HRS
BOONE C 1H | 20 | 2021-07-26 20:45 | 2021-07-27 04:15 | 7.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.58 | 10040 | 10619 | 77.2 | BUILD CURVE-SLIDE (579' IN 7.42 HRS@ 78 FPH) WOB-20/35K, SPM-75/75, GPM-400, MRPM-272, SPP-3300/4000 PSI, DIFF-450/550 PSI, CHOKES- 48% I 50%, FLARE-30', NO MUD CUT, MAX CASING PRESSURE= 350 PSI, AVG CASING PRESSURE= 240 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 629 PSI, AVG SICP= 629 PSI. SLIDE DEPTHS: F/10,040' T/10,080' 40' TF:HS 20:51-21:53 F/10,098'-T/10,177', 79', TF:HS, 22:13-23:05 F/10,193'-T/10,275', 82', TF:10L 23:27-00:15 F/10,288'-T/10,381', 93', TF:10L 00:37-0137 F/10,381'-T/10,475', 93', TF:10L 0145-0245 F/10,475'-T/10,530', 55', TF:HS 0240-0338 F/10,540',-T/10,645', 105', TF:HS, 03:54-05:00
BOONE C 1H | 20 | 2021-07-27 04:15 | 2021-07-27 06:00 | 1.75 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.66 | 10619 | 10697 | 44.6 | BUILD CURVE-ROT (78' IN 1.73 HRS @ 45.08 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-45, MRPM-272, TMRPM-317, TRQ-10/12K, SPP-3800/4400 PSI, DIFF-600/800 PSI.
BOONE C 1H | 21 | 2021-07-27 06:00 | 2021-07-27 10:00 | 4 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.82 | 10697 | 10854 | 39.3 | BUILD CURVE-SLIDE (157' IN 4 HRS@ 39.25 FPH) WOB-20/35K, SPM-75/75, GPM-400, MRPM-272, SPP-3300/4000 PSI, DIFF-450/550 PSI, CHOKES-48%, FLARE-10-35', NO MUD CUT, MAX CASING PRESSURE= 693 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 470 PSI, AVG SICP= 365 PSI. SLIDE DEPTHS: F/10,697'-T/10,854' 157' TF:HS 06:00-10:00
BOONE C 1H | 21 | 2021-07-27 10:00 | 2021-07-27 10:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 7.82 | 10854 | 10854 |  | MILESTONE_START HORIZONATAL LATERAL SECTION ON 7/27/2021 @ 10:00
BOONE C 1H | 21 | 2021-07-27 10:00 | 2021-07-27 12:45 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.94 | 10854 | 11219 | 132.7 | ROT (365' IN 2.82 HRS @ 129.43 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/12K, SPP-3500/4300 PSI
BOONE C 1H | 21 | 2021-07-27 10:00 | 2021-07-27 10:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 7.82 | 10854 | 10854 |  | MILESTONE_LAND/END CURVE SECTION: 7/27/2021 @ 10:00 MD:10,854' TVD:10,328.6
BOONE C 1H | 21 | 2021-07-27 12:45 | 2021-07-27 16:15 | 3.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.08 | 11219 | 11346 | 36.3 | SLIDE (127' IN 3.42 HRS @ 37.13 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-3900/4500 PSI, DIFF-150/300 PSI, CHOKES- 40% / 0%, FLARE-20', NO MUD CUT, MAX CASING PRESSURE= 595 PSI, AVG CASING PRESSURE= 112 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1,054 PSI, AVG SICP= 550 PSI. SLIDE DEPTHS: F/10,854'-T/10,869', 15', TF:HS 10:00-10:32 F/10,958'-T/10,978', 20', TF:140R 11:12-11:39 F/11,053'-T/11,065', 12', TF:180 12:04-12:44 F/11,085'-T/11,110', 25', TF:180 13:00-13:50 F/11,147'-T/11,162', 15', TF:160R 14:10-14:30 F/11,242'-T/11,262', 20', TF:HS, 15:08-15:26 F/11,326'-T/11,346', 20', TF:HS, 15:56-16:14
BOONE C 1H | 21 | 2021-07-27 16:15 | 2021-07-27 17:00 | 0.75 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.11 | 11346 | 11346 | 0 | SERVICE RIG. RM PRESENT
BOONE C 1H | 21 | 2021-07-27 17:00 | 2021-07-28 02:00 | 9 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.49 | 11346 | 12780 | 159.3 | ROT (1,434' IN 8.95 HRS @ 160.22 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/12K, SPP-3800/4900 PSI. CHOKES- 40% / 0%, FLARE-20', NO MUD CUT, MAX CASING PRESSURE= 595 PSI, AVG CASING PRESSURE= 112 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1,054 PSI, AVG SICP= 550 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 21 | 2021-07-28 02:00 | 2021-07-28 06:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.66 | 12780 | 12955 | 43.8 | SLIDE (175' IN 4.05 HRS @ 43.2 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-3900/4500 PSI, DIFF-150/300 PSI, CHOKES- 40% / 0%, FLARE-20', NO MUD CUT, MAX CASING PRESSURE= 595 PSI, AVG CASING PRESSURE= 112 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1,054 PSI, AVG SICP= 550 PSI. SLIDE DEPTHS: F/11,525'-T/11,555', 20', TF:90L, 18:00-18:44 F/11,619'-T/11,631', 12', TF:20R, 19:24-19:37 F/11,814'-T/11,822', 8', TF:180, 20:45-20:57 F/11,990'-T/12,007', 15', TF:170L, 21:49-22:10 F/12,085'-T/12,105', 20', TF:170L, 22:44-23:05 F/12,274'-T/12,286', 12', TF:180, 00:10-00:25 F/12,380'-T/12,390', 10', TF:170L, 01:00-01:13 F/12,565'-T/12,590', 15', TF:HS, 02:15-02:45 F/12,660'-T/12,676', 16', TF:8L, 03:20-03:44 F/12,842'-T/12,850', 10', TF:180, 04:40-04:55 F/12,940'-T/12,955', 15', TF:180, 05:25-05:45
BOONE C 1H | 22 | 2021-07-28 06:00 | 2021-07-28 13:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.95 | 12955 | 13940 | 140.7 | ROT (985' IN 6.7 HRS @ 147 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/12K, SPP-3800/4900 PSI. CHOKES- 40% / 0%, FLARE-20', NO MUD CUT, MAX CASING PRESSURE= 595 PSI, AVG CASING PRESSURE= 112 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1,054 PSI, AVG SICP= 550 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 22 | 2021-07-28 13:00 | 2021-07-28 20:30 | 7.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.26 | 13940 | 14341 | 53.5 | SLIDE (401' IN 7.8 HRS @ 51.4 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-3900/4500 PSI, DIFF-150/300 PSI, CHOKES- 40% / 0%, FLARE-15', NO MUD CUT, MAX CASING PRESSURE= 485 PSI, AVG CASING PRESSURE= 115 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 602 PSI, AVG SICP= 450 PSI. SLIDE DEPTHS: F/13,032'-T/13,042', 10', TF:180, 06:20-06:45 F/13,220'-T/13,235', 15', TF:180, 07:37-07:55 F/13,409'-T/13,429', 20' TF:120L, 08:39-08:57 F/13,498'-T/13,528', 30' TF:90L, 09:35-10:00 F/13,682'-T/13,712', 30' TF:90L 10:52-11:20 F/13,775'-T/13,815', 40', TF:90L, 11:46-12:30 F/13,870'-T/13,965', 95', TF:90L, 13:00-14:05 F/14,058'-T/14,152', 94', TF:80L, 15:10-17:40 F/14,246'-T/14,313', 40', TF:60L, 18:43-20:18
BOONE C 1H | 22 | 2021-07-28 20:30 | 2021-07-28 21:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.28 | 14341 | 14341 | 0 | SERVICE RIG. RM PRESENT
BOONE C 1H | 22 | 2021-07-28 21:00 | 2021-07-29 00:45 | 3.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.44 | 14341 | 14662 | 85.6 | ROT (321' IN 3.80 HRS @ 84.47 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/12K, SPP-3800/4200 PSI. CHOKES- #1-0%/ #2-40%, FLARE-15', NO MUD CUT, CUT, MAX CASING PRESSURE= 1,092 PSI, AVG CASING PRESSURE= 195 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1,092 PSI, AVG SICP= 525 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 22 | 2021-07-29 00:45 | 2021-07-29 06:00 | 5.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.66 | 14662 | 14739 | 14.7 | SLIDE (77' IN 5.20 HRS @ 14.80 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-3300/3800 PSI, DIFF-150/300 PSI, CHOKES-#1-0%/ #2-40%, FLARE-20', NO MUD CUT, MAX CASING PRESSURE= 1,092 PSI, AVG CASING PRESSURE= 200 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1,092 PSI, AVG SICP= 550 PSI. SLIDE DEPTHS: F/14,435'-T/14,456', 20', TF:20L, 21:13-21:55 F/14,530'-T/14,540' 15', TF:110R, 00:45-01:15 F/14,625'-T/14,651', 30', TF:150R, 02:00-03:52 F/14,719'-T/14,739', 20', TF110R, 04:45-06:00
BOONE C 1H | 23 | 2021-07-29 06:00 | 2021-07-29 07:15 | 1.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.71 | 14739 | 14814 | 60 | ROT (75' IN 1.25HRS @ 60FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/12K, SPP-3800/4200 PSI. CHOKES- #1-0%/ #2-40%, FLARE-10', NO MUD CUT, CUT, MAX CASING PRESSURE= 691 PSI, AVG CASING PRESSURE= 195 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 691 PSI, AVG SICP= 525 PSI.
BOONE C 1H | 23 | 2021-07-29 07:15 | 2021-07-29 07:45 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.73 | 14814 | 14814 | 0 | RELOG F/14,765'-T/14,855'. GPM:400, SPP:3,210, RPM:80, TQ:12
BOONE C 1H | 23 | 2021-07-29 07:45 | 2021-07-29 08:30 | 0.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.76 | 14814 | 14855 | 54.7 | ROT (41' IN .75HRS @ 54.66FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/12K, SPP-3800/4200 PSI. CHOKES- #1-0%/ #2-40%, FLARE-10', NO MUD CUT, CUT, MAX CASING PRESSURE= 691 PSI, AVG CASING PRESSURE= 195 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 691 PSI, AVG SICP= 525 PSI.
BOONE C 1H | 23 | 2021-07-29 08:30 | 2021-07-29 09:15 | 0.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.79 | 14855 | 14855 | 0 | CIRC PRIOR TO POOH. GPM:400, SPP:3,273, RPM:80, TQ:13 NOTE: NO SPEEPS WERE PUMPED WHILE CONDUCTING THIS CIRCULATION.
BOONE C 1H | 23 | 2021-07-29 09:15 | 2021-07-29 11:45 | 2.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.9 | 14855 | 14855 | 0 | BACK REAM OUT OF THE HOLE F/14,855'-T/13,395', GPM:310, SPP:1,935 RPM:80 TQ:10-18, CHOKE POSITION: 45%, SICP:125, MAX SICP: 487
BOONE C 1H | 23 | 2021-07-29 11:45 | 2021-07-29 12:00 | 0.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.91 | 14855 | 14855 | 0 | @ 13,395' PUMP 50BBL SLUG
BOONE C 1H | 23 | 2021-07-29 12:00 | 2021-07-29 13:45 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.98 | 14855 | 14855 | 0 | STRIP OUT OF THE HOLE F/13,395'-T/9,800'. PUMPING CAL FILL DOWN THE BACKSIDE. MAX CSG PSI SEEN WHILE PERFORMING STRIPPING OPS =300-368
BOONE C 1H | 23 | 2021-07-29 13:45 | 2021-07-29 15:45 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.06 | 14855 | 14855 | 0 | CIRC B/U WHILE MONITORING WELL. GPM:300 SPP:1,764, RPM:10, TQ:5. MAX SICP:776, AVG SICP:115. SPOT 75BBL OF 16# MUD CAP AND CHASE W/98BBLS OF 9.5#.
BOONE C 1H | 23 | 2021-07-29 15:45 | 2021-07-29 17:00 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.11 | 14855 | 14855 | 0 | POOH F/9,800'-T/7,733' PUMPING CAL FILL DOWN BACKSIDE.
BOONE C 1H | 23 | 2021-07-29 17:00 | 2021-07-29 17:30 | 0.5 | U | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 10.14 | 14855 | 14855 | 0 | ONCE PULLED OUT OF MUD CAP @ 7,733', CONDUCT FLOWCHECK. RESULT: NO FLOW, WELL STATIC. LINE UP TO TAKE RETURNS DOWN FLOWLINE TO TRIP TANK.
BOONE C 1H | 23 | 2021-07-29 17:30 | 2021-07-29 18:45 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.19 | 14855 | 14855 | 0 | POOH F/7,733'-T/6,413'. HOLE TAKING PROPER FILL
BOONE C 1H | 23 | 2021-07-29 18:45 | 2021-07-29 19:30 | 0.75 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.22 | 14855 | 14855 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. NOTE:CONDUCT FLOWCHECK PRIOR TO PULLING RT-HEAD. RESULT: NO FLOW.
BOONE C 1H | 23 | 2021-07-29 19:30 | 2021-07-29 23:30 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.39 | 14855 | 14855 | 0 | POOH F/6,413'-T/5,900', L/D AGITATOR (#2). CONT. POOH F/5,900'-T/2,810'. L/D AGITATOR (#1). CONT. POOH F/2,810'-T/BHA. HOLE TAKING PROPER FILL. NOTE: OBSERVED WASHOUT ON AGITATOR#1. LOCATION: ON THE CROSSOVER SECTION, WHERE IT X/O F/XT39-CET43.
BOONE C 1H | 23 | 2021-07-29 23:30 | 2021-07-30 00:30 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.43 | 14855 | 14855 | 0 | L/D TOMAX, RACKED BACK NMDC, L/D MWD, DRAIN MOTOR AND BREAK BIT. NOTE: FLOW CHECK PRIOR TO BHA ENTERING BOP. RESULT: NO FLOW. SICP: 0 PSI. MOTOR DRAINED WELL AND HAD MINIMAL SLACK.
BOONE C 1H | 23 | 2021-07-30 00:30 | 2021-07-30 02:45 | 2.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 10.52 | 14855 | 14855 | 0 | PICK UP BHA#5: 6.75" SECURITY GTD64M SER 13594950 JETS 6/18S TFA: 1.491), 5", 6/7L, 8.8 STG @ 2.12° SLICK; 0.68 REV/GAL; 4.03' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5 1/4" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, 5" TOMAX, X/0, 2 STANDS DP, REAMER, 26 STANDS DP, AGITATOR, 33 STANDS DP AND ON DEMAND AGITATOR. BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD)
BOONE C 1H | 23 | 2021-07-30 02:45 | 2021-07-30 03:15 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.54 | 14855 | 14855 | 0 | SERVICE RIG. RM PRESENT
BOONE C 1H | 23 | 2021-07-30 03:15 | 2021-07-30 06:00 | 2.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.66 | 14855 | 14855 | 0 | TIH W/BHA #5 F/132.18'-T/2,807', P/U AGITATOR #1 AND TEST (BEFORE-GPM:200, PSI:650. AFTER-GPM:200, PSI:887). TIH W/BHA#5 F/2,807'-T/5,941', P/U AGITATOR #2. HOLE GIVING PROPER DISPLACMENT. FILL EVERY 30 STDS.
BOONE C 1H | 24 | 2021-07-30 06:00 | 2021-07-30 08:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.74 | 14855 | 14855 | 0 | TIH W/BHA #5 F/5,941'-T/10,050'. HOLE GIVING PROPER DISPLACMENT. FILL EVERY 30 STDS.
BOONE C 1H | 24 | 2021-07-30 08:00 | 2021-07-30 08:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.76 | 14855 | 14855 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. NOTE: NO FLOW
BOONE C 1H | 24 | 2021-07-30 08:30 | 2021-07-30 10:45 | 2.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.85 | 14855 | 14855 | 0 | CIRC OUT MUD CAP @ 10,050'. GPM:263, SPP:2,149, RPM:20, TQ:6, MW:9.6. SICP:130, MAX SICP:223. NOTE: KEPT BIT OUTSIDE OF THE CSG SHOE (10,017') WHILE RECIPRICATING THE DRILL STRING DURING CIRCULATING OPS. HEAVIEST MUD WEIGHT SEEN-12.4. CAUGHT 120 BBLS OF HEAVY MUD IN TRIP TANKS WHILE CIRCULATING.
BOONE C 1H | 24 | 2021-07-30 10:45 | 2021-07-30 13:30 | 2.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.97 | 14855 | 14855 | 0 | STRIP IN HOLE F/10,050' T/14,720'. BLEEDING CALCULATED DISPLACEMENT INTO TRIP TANKS DURING TRIP IN. MAX SICP-440 PSI AVG SICP WHIE STRIPPING=250-450 PSI
BOONE C 1H | 24 | 2021-07-30 13:30 | 2021-07-30 13:45 | 0.25 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 10.98 | 14855 | 14855 | 0 | WASH AND REAM F/14,855'-T/14,855' GPM:400, SPP:4931, RPM:80, TQ:14
BOONE C 1H | 24 | 2021-07-30 13:45 | 2021-07-30 23:15 | 9.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.38 | 14855 | 16410 | 163.7 | ROT (1,555' IN 9.13 HRS @ 170.31 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-7', NO MUD CUT, CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 24 | 2021-07-30 23:15 | 2021-07-31 06:00 | 6.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.66 | 16410 | 16540 | 19.3 | SLIDE (130' IN 6.78 HRS @ 19.17 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-4300/4800 PSI, DIFF-75/150 PSI, CHOKES-#1-0%/ #2-40%, FLARE-10', NO MUD CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI SLIDE DEPTHS: F/14,855'-T/14,870', 15', TF:45R, 1405-1500 F/15,014'-T/15,034', 20', TF:150R, 16:10-17:15 F/15,286'-T/15,311', 25', TF:HS 18:50-19:55 F/15,486'-T/15,506', 20', TF:135R, 21:05-22:00 F/15,768'-T/15,780', 12', TF:180, 23:23-23:50 F/15,862'-T/15,882', 20', TF:30R, 00:25-01:30 F/16522',-T/16547', 25' TF:130L, 04:45-06:00
BOONE C 1H | 25 | 2021-07-31 06:00 | 2021-07-31 07:30 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.72 | 16540 | 16796 | 170.7 | ROT (256' IN 1.5 HRS @ 171 FPH) WOB-25 /35K, SPM-76/76/0, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/24K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-7', NO MUD CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 25 | 2021-07-31 07:30 | 2021-07-31 10:00 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.82 | 16796 | 16819 | 9.2 | SLIDE (23' IN 2.5 HRS @ 9 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-4300/4800 PSI, DIFF-75/150 PSI, CHOKES-#1-0%/ #2-40%, FLARE-10', NO MUD CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI SLIDE DEPTHS: F/16,540'-T/16547', 7', TF:135R, 0600-0621 F/16711-16723', 12' TF:180, 0717-0836 F/16815'-16819', 4', TF:70R 0910-1000
BOONE C 1H | 25 | 2021-07-31 10:00 | 2021-07-31 10:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.84 | 16819 | 16819 | 0 | CIRCULATED OFF BOTTOM AND RECORD PUMP PSI @ 400 GPM, PP-4739, RPM-45. DROP BALL AND ACTIVATE DWS ON-DEMAND AGITATOR. PUMP WITH 200 GPM, PP-1,644. PUMPED 2,227 STROKES AND OBSERVED PUMP PSI INCREASE FROM 1,644 TO 1,983 PSI. INCREASED GPM TO 400 AND PUMP PRESSURE INCREASED FROM 4,733 TO 5,130. NOTE: MW=9.9
BOONE C 1H | 25 | 2021-07-31 10:30 | 2021-07-31 12:30 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.93 | 16819 | 17044 | 112.5 | ROT (225' IN 2.03 HRS @ 111 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-7', NO MUD CUT, CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=200 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 612 PSI, AVG SICP= 540 PSI. NOTE: AT 16,852' CROSSED A FAULT AND HOLE BEGAN SEEPING. ADDING 2 SACKS PER HOUR TO ACTIVE SYSTEM OF : PROCOR SWEEP AID, PROCOR SUPER SEAL, MAGNAFIBER FINE, AND NEW CARB MEDIUM.
BOONE C 1H | 25 | 2021-07-31 12:30 | 2021-07-31 15:30 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.05 | 17044 | 17080 | 12 | SLIDE (36' IN X HRS @ X FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-4300/4800 PSI, DIFF-75/150 PSI, CHOKES-#1-0%/ #2-40%, FLARE-10', NO MUD CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=200 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 612 PSI, AVG SICP= 540 PSI. SLIDE DEPTHS: F/16,819'-T/16,825', 6', TF:70R, 1030-1133 F/16,900'-T/16,930', 30', TF:35R, 12:30-14:25
BOONE C 1H | 25 | 2021-07-31 15:30 | 2021-07-31 16:30 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.09 | 17080 | 17080 | 0 | PERFORM RIG SERVICE
BOONE C 1H | 25 | 2021-07-31 16:30 | 2021-07-31 20:00 | 3.5 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 12.24 | 17080 | 17080 | 0 | WHILE PERFORMING RIG SERVICE, PATTERSON EMPLOYEE NOTICED THAT A BOLT WAS SHEARED ON THE SECONDARY RETENTION FOR THE TOP DRIVE CARRIAGE ADJUSTMENT BOLT. WELDER CAME AND TACKED BOLT INTO PLACE.
BOONE C 1H | 25 | 2021-07-31 20:00 | 2021-07-31 22:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.32 | 17080 | 17349 | 134.5 | ROT (269' IN 1.98 HRS @135.85 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-7', NO MUD CUT, CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI. NOTE: ADDING 2 SACKS PER HOUR TO ACTIVE SYSTEM OF : PROCOR SWEEP AID, PROCOR SUPER SEAL, MAGNAFIBER FINE, AND NEW CARB MEDIUM.
BOONE C 1H | 25 | 2021-07-31 22:00 | 2021-08-01 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.41 | 17349 | 17378 | 14.5 | SLIDE (29' IN 2.18 HRS @ 13.3 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-4300/4800 PSI, DIFF-75/150 PSI, CHOKES-#1-0%/ #2-40%, FLARE-10', NO MUD CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI SLIDE DEPTHS: F/17,090'-T/17,100', 10', TF:180, 20:15-20:48 F/17,279'-T/17,294', 15', TF:170, 21:55-23:00
BOONE C 1H | 25 | 2021-08-01 | 2021-08-01 01:45 | 1.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.48 | 17378 | 17378 | 0 | WHILE SLIDING @ 17,378', MOTOR STALLED. THE HIGH PRESSURE WOULD NOT RELEASE (NORMAL OFF BTM PRESSURE: 4,252PSI, INCREASED T/5,450PSI) AND CAUSED THE MWD TO KNOCK OUT OF SYNC. CIRC B/U IN PREP TO POOH. DURING THE CIRCULATION, THE PRESSURE RELEASED BACK TO NORMAL "OFF BTM PRESSURE" AND THE MWD TOOL STARTED COMMUNICATING. NOTE: PRIOR TO PRESSURE RELEASE, ATTEMPTED TO RE-SYNC TOOL SEVERAL TIMES BY "RECYCLING THE PUMPS" WITH NO SUCCESS.
BOONE C 1H | 25 | 2021-08-01 01:45 | 2021-08-01 04:15 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.58 | 17378 | 17608 | 92 | ROT (230' IN 2.5 HRS @92 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-45%/ #2-0%, FLARE-7', NO MUD CUT, CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI. NOTE: ADDING 2 SACKS PER HOUR TO ACTIVE SYSTEM OF : PROCOR SWEEP AID, PROCOR SUPER SEAL, MAGNAFIBER FINE, AND NEW CARB MEDIUM.
BOONE C 1H | 25 | 2021-08-01 04:15 | 2021-08-01 05:30 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.64 | 17608 | 17632 | 19.2 | SLIDE (24' IN 1.25 HRS @ 19.2 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-4300/4800 PSI, DIFF-75/150 PSI, CHOKES-#1-45%/ #2-0%, FLARE-8', NO MUD CUT, MAX CASING PRESSURE= 260 PSI, AVG CASING PRESSURE=105 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI SLIDE DEPTHS: F/17,378'-T/17,402', 24', TF:180, 02:00-03:00
BOONE C 1H | 25 | 2021-08-01 05:30 | 2021-08-01 06:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.66 | 17632 | 17632 | 0 | CIRC B/U PRIOR TO POOH DUE TO MOTOR FAILURE. GPM:378, SPP:4,319-5,322. RPM:80, TQ:15K
BOONE C 1H | 26 | 2021-08-01 06:00 | 2021-08-01 07:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.7 | 17632 | 17632 | 0 | CIRC B/U PRIOR TO POOH DUE TO MOTOR FAILURE. GPM:378, SPP:4,319-5,322. RPM:80, TQ:15K
BOONE C 1H | 26 | 2021-08-01 07:00 | 2021-08-01 08:45 | 1.75 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 12.77 | 17632 | 17632 | 0 | BACK REAM OUT OF THE HOLE F/17,362'-T/16,478', GPM:310, SPP:4,305 RPM:80 TQ:10-18, CHOKE POSITION : 45%, SICP:532 , MAX SICP: 650.
BOONE C 1H | 26 | 2021-08-01 08:45 | 2021-08-01 12:45 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.94 | 17632 | 17632 | 0 | STRIP OUT OF THE HOLE F/16,478'-T/10,065'. PUMPING CAL FILL DOWN THE BACKSIDE. MAX CSG PSI SEEN WHILE PERFORMING STRIPPING OPS =612-746
BOONE C 1H | 26 | 2021-08-01 12:45 | 2021-08-01 15:00 | 2.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.03 | 17362 | 17632 | 120 | CIRC B/U WHILE MONITORING WELL. GPM:380 SPP:3650, RPM:20, TQ:6-8. CSG PSI WHILE CIRC=150-600. SHUT DOWN PUMPS AND MONITOR CSG PSI. CSG PSI ROSE T/600. PUMP AND SPOT 96 BBL 17# OBM MUD CAP @ 10,065'. TOP OF MUD CAP-7,930'.
BOONE C 1H | 26 | 2021-08-01 15:00 | 2021-08-01 16:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.07 | 17632 | 17632 | 0 | POOH F/10,065'-T/7,500' PUMPING CAL FILL DOWN BACKSIDE.
BOONE C 1H | 26 | 2021-08-01 16:00 | 2021-08-01 16:15 | 0.25 | U | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 13.08 | 17632 | 17632 | 0 | ONCE PULLED OUT OF MUD CAP@ 7,500', CONDUCT FLOWCHECK . RESULT: NO FLOW, WELL STATIC. LINE UP TO TAKE RETURNS DOWN FLOWLINE TO TRIP TANK.
BOONE C 1H | 26 | 2021-08-01 16:15 | 2021-08-01 17:00 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.11 | 17632 | 17632 | 0 | POOH F/7,500'-T/6,497'. HOLE TAKING PROPER FILL. PUMP SLUG @ 7,000'.
BOONE C 1H | 26 | 2021-08-01 17:00 | 2021-08-01 17:15 | 0.25 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 13.13 | 17632 | 17632 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. NOTE:CONDUCT FLOWCHECK PRIOR TO PULLING RT-HEAD. RESULT: NO FLOW.
BOONE C 1H | 26 | 2021-08-01 17:15 | 2021-08-01 21:15 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.29 | 17632 | 17632 | 0 | POOH F/6,497'-T/2,725'. L/D AGITATOR. POOH F/2,725'-T/BHA. HOLE TAKING PROPER FILL. NOTE: SMALL WASH WAS NOTICED ON AGITATOR #1. LOCATION: AT THE ACME THREAD CONNECTION ON THE SFTY JT.
BOONE C 1H | 26 | 2021-08-01 21:15 | 2021-08-01 22:00 | 0.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.32 | 17632 | 17632 | 0 | L/D TOMAX, RACKED BACK NMDC, L/D MWD, DRAIN MOTOR AND BREAK BIT. NOTE: FLOW CHECK PRIOR TO BHA ENTERING BOP. RESULT: NO FLOW. SICP: 0 PSI. MOTOR HAD .5'' OF SLACK AND HAD NO RESTRICTION FROM DRAINING, DRAINED WHILE PULLING OUT OF THE HOLE (FREE FLOW). BIT LOOKED GOOD, NO PLUGGED JETS, NO CHIPPED CUTTERS GRADE: 0-1.
BOONE C 1H | 26 | 2021-08-01 22:00 | 2021-08-02 00:15 | 2.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 13.42 | 17632 | 17632 | 0 | PICK UP BHA#6: 6.75" SECURITY GTD64M SN:13601236 JETS 6/18S TFA: 1.491), 5", 6/7L, 8.8 STG @ 2.12° SLICK; 0.68 REV/GAL; 4.01' BIT TO BEND 5.56" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5 1/4" NMPDC, 5 1/4" UBHO, 5" NMDC, 5"NMDC, 5" TOMAX, X/0, 2 STANDS DP, REAMER, 26 STANDS DP, AGITATOR, 33 STANDS DP AND ON DEMAND AGITATOR. BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD) NOTE: REMOVE SFTY JT OFF OF AGITATOR.
BOONE C 1H | 26 | 2021-08-02 00:15 | 2021-08-02 03:45 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.56 | 17632 | 17632 | 0 | TIH W/BHA #5 F/132.18'-T/2,782', P/U AGITATOR #1 AND TEST (BEFORE-GPM:200, PSl:650. AFTER- GPM:200, PSl:725). TIH W/BHA#5 F/2,782'-T/5,941', P/U AGITATOR #2. TIH F/5,941'-T/6,132' HOLE GIVING PROPER DISPLACMENT. FILL EVERY 30 STDS. NOTE: REMOVE SFTY JT ON AGITATOR #1. WHILE PICKING UP AGITATOR #2, NOTICED TOP SEAL ON AGITATOR WAS EXPOSED. DECISION WAS MADE TO C/O "ON DEMAND" AGITATOR #2.
BOONE C 1H | 26 | 2021-08-02 03:45 | 2021-08-02 04:30 | 0.75 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 13.59 | 17632 | 17632 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. NOTE: C/O OIL FITTING ON BEARING ASSY. FLOW CHECK: NO FLOW
BOONE C 1H | 26 | 2021-08-02 04:30 | 2021-08-02 05:30 | 1 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 13.64 | 17632 | 17632 | 0 | SLIP AND CUT 100' OF DRILLING LINE. RIG MANAGER PRESENT. NOTE: T.I.W INSTALLED
BOONE C 1H | 26 | 2021-08-02 05:30 | 2021-08-02 06:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.66 | 17632 | 17632 | 0 | SERVICE RIG. C/O BLACK JACK SWIVEL PACKING ON TOP DRIVE. RIG MANAGER PRESENT
BOONE C 1H | 27 | 2021-08-02 06:00 | 2021-08-02 06:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.68 | 17632 | 17632 | 0 | SERVICE RIG. RIG MANAGER PRESENT NOTE: TIW INSTALLED AND MONITOR WELL VIA TRIP TANK
BOONE C 1H | 27 | 2021-08-02 06:30 | 2021-08-02 07:15 | 0.75 | U | PRDHLLT | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 13.71 | 17632 | 17632 | 0 | C/O SWIVEL PACKING ON TOP DRIVE. RIG MANAGER PRESENT. NOTE: TIW INSTALLED AND MONITOR WELL VIA TRIP TANK
BOONE C 1H | 27 | 2021-08-02 07:15 | 2021-08-02 08:30 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.76 | 17632 | 17632 | 0 | TIH W/BHA #6 F/6,132'-T/8,774' HOLE GIVING PROPER DISPLACEMENT INTO TRIP TANK.
BOONE C 1H | 27 | 2021-08-02 08:30 | 2021-08-02 11:00 | 2.5 | U | PRDHLLT | WAIT | WOW | WAIT ON WEATHER | 13.86 | 17632 | 17632 | 0 | SHUT DOWN TRIPPING OPS AS PER PATTERSON POLICY, DUE TO LIGHTING BEING WITH IN 3MILES. NOTE: CIRC TOP OF MUD CAP OUT GPM:263, SPP:2595, RPM:10, TQ:5K. HEAVIEST MUD CAUGHT 11.4 PPG. LOST APPROXIMATELY 34 BBLS WHILE CIRCULATING OUT MUD CAP. DIVERTED APPROXIMATELY 68 BBLS 10.5-11.4 OBM
BOONE C 1H | 27 | 2021-08-02 11:00 | 2021-08-02 11:45 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.9 | 17632 | 17632 | 0 | STRIP IN HOLE F/8,774' T/10,096'. BLEEDING CALCULATED DISPLACEMENT INTO TRIP TANKS DURING TRIP IN. MAX SICP-351 PSI AVG SICP WHILE STRIPPING=250-300 PSI. AS STRIPPING INTO MUD CAP CASING PRESSURE REDUCED T/50 PSI.
BOONE C 1H | 27 | 2021-08-02 11:45 | 2021-08-02 13:00 | 1.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.95 | 17632 | 17632 | 0 | CIRC OUT MUD CAP @ 10,096'. GPM:263, SPP:2,149, RPM:20, TQ:6, MW:9.6. SICP WHILE CIRCULATING=0-650 PSI SICP AFTER CIRCULATING=650 PSI NOTE: KEPT BIT OUTSIDE OF THE CSG SHOE (10,017') WHILE RECIPRICATING THE DRILL STRING DURING CIRCULATING OPS. HEAVIEST MUD WEIGHT SEEN-13. DIVERTED 94 BBLS OF 11-13 PPG OBM IN TRIP TANKS WHILE CIRCULATING. LOST APPROXIMATELY 35 BBLS WHILE CIRCULATING OUT MUD CAP.
BOONE C 1H | 27 | 2021-08-02 13:00 | 2021-08-02 15:45 | 2.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.06 | 17632 | 17632 | 0 | STRIP IN HOLE F/10,096' T/15,567'. BLEEDING CALCULATED DISPLACEMENT INTO TRIP TANKS DURING TRIP IN. MAX SICP-351 PSI AVG SICP WHILE STRIPPING=250-300 PSI
BOONE C 1H | 27 | 2021-08-02 15:45 | 2021-08-02 17:30 | 1.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.14 | 17632 | 17632 | 0 | @ 15,567' CIRC B/U. GPM:263, SPP:3276, RPM:40, TQ:15 SICP WHILE CIRCULATING=0-540 PSI SICP AFTER CIRCULATING=540 PSI NOTE: LOST APPROXIMATELY 136 BBLS WHILE CIRCULATING. HEAVIEST MW SEEN WHILE CIRC=12.5 PPG. RECOVERED 120BBLS OF 10.6-12.5PPG OBM
BOONE C 1H | 27 | 2021-08-02 17:30 | 2021-08-02 18:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.16 | 17632 | 17632 | 0 | STRIP IN HOLE F/15,567' T/17,076'. BLEEDING CALCULATED DISPLACEMENT INTO TRIP TANKS DURING TRIP IN. MAX SICP-760 PSI AVG SICP WHILE STRIPPING=730-742 PSI
BOONE C 1H | 27 | 2021-08-02 18:00 | 2021-08-02 19:30 | 1.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 14.22 | 17632 | 17632 | 0 | WASH AND REAM F/17,076'-T/17,632'. GPM:322, SPP:4125, RPM:60, TQ:16.8
BOONE C 1H | 27 | 2021-08-02 19:30 | 2021-08-02 23:30 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.39 | 17632 | 18114 | 120.5 | ROT (482' IN 3.92 HRS @ 122.95 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-7', NO MUD CUT, CUT, MAX CASING PRESSURE= 670 PSI, AVG CASING PRESSURE=585 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 895 PSI, AVG SICP= 750 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 27 | 2021-08-02 23:30 | 2021-08-03 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.41 | 18114 | 18129 | 30 | SLIDE (15' IN .58 HRS @ 25.86 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-5200/5600 PSI, DIFF-75/250 PSI, CHOKES-#1-50%/ #2-0%, FLARE-11', NO MUD CUT, MAX CASING PRESSURE= 240 PSI, AVG CASING PRESSURE=120 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 746 PSI, AVG SICP= 560 PSI SLIDE DEPTHS: F/17,656'-T/17,671', 15', TF:130, 19:50-20:25
BOONE C 1H | 27 | 2021-08-03 | 2021-08-03 01:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.45 | 18129 | 18129 | 0 | TROUBLE SHOOT MWD. DOWNLINK TOOL. C/O TRANSDUCER. C/O MWD COMMUNICATION CABLE.
BOONE C 1H | 27 | 2021-08-03 01:00 | 2021-08-03 01:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.47 | 18129 | 18141 | 24 | SLIDE (12' IN .45 HRS @ 26.66 FPH) WOB-15/25K, SPM-75/75, GPM-400, MRPM-272, SPP-4300/4800 PSI, DIFF-75/150 PSI, CHOKES-#1-40%/ #2-0%, FLARE-20-45',MUD CUT 9.9-9.7, MAX CASING PRESSURE= 820 PSI, AVG CASING PRESSURE=675 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 820 PSI, AVG SICP= 760 PSI SLIDE DEPTHS: F/18,129'-T/18,141', 12', TF:160L, 00:53-01:20.
BOONE C 1H | 27 | 2021-08-03 01:30 | 2021-08-03 02:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.49 | 18141 | 18214 | 146 | ROT (73' IN .67 HRS @ 108.95 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-20-40' MUD CUT 9.9-9.6, MAX CASING PRESSURE= 810 PSI, AVG CASING PRESSURE=680 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 895 PSI, AVG SICP= 750 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 27 | 2021-08-03 02:00 | 2021-08-03 02:15 | 0.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.5 | 18214 | 18214 | 0 | C/O MWD TRANSDUCER CABLE
BOONE C 1H | 27 | 2021-08-03 02:15 | 2021-08-03 05:15 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.63 | 18214 | 18567 | 117.7 | ROT (353' IN 2.9 HRS @ 121.72 FPH) WOB-25 /35K, SPM-72/72, GPM-375, RPM-80, MRPM-255, TMRPM-335, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-10-20' MUD CUT 9.7-9.6, MAX CASING PRESSURE= 395 PSI, AVG CASING PRESSURE=85 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 784 PSI, AVG SICP= 464 PSI NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300' CUT MW F/9.9-T/9.7PPG DUE TO LOSSES. @ 18,363' CHOKE POSITION: #1-100%, #2-100%
BOONE C 1H | 27 | 2021-08-03 05:15 | 2021-08-03 06:00 | 0.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.66 | 18567 | 18591 | 32 | SLIDE (24' IN .85 HRS @ 28.23 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-255, SPP-4820/4985 PSI, DIFF-75/150 PSI, CHOKES-#1-100%/ #2-100%, FLARE-5-8',MUD CUT 9.7-9.6, MAX CASING PRESSURE= 395 PSI, AVG CASING PRESSURE=85 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 684 PSI, AVG SICP= 464 PSI SLIDE DEPTHS: F/18,224'-T/18,236', 12', TF:180, 02:30-02:51 F/18,508'-T/18,520', 12', TF:HS, 04:41-05:11 NOTE: TARGET CHANGE @ 04:38 ON 8/3/21 (Plan 1 – 10303’ TVD AT 0 VS WITH 87.1 DEG INC 10’ ABOVE/ 0’ BELOW)
BOONE C 1H | 28 | 2021-08-03 06:00 | 2021-08-03 06:30 | 0.5 | U | PRDHLLT | LOG | MWD | MWD | 14.68 | 18591 | 18591 | 0 | RECYCLE MUD PUMPS MULTIPLE TIMES IN ATTEMPTS TO SYNC MWD TOOL.
BOONE C 1H | 28 | 2021-08-03 06:30 | 2021-08-03 10:15 | 3.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.83 | 18591 | 19092 | 133.6 | ROT (501' IN 3.85 HRS @ 130 FPH) WOB-25 /35K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4900/5800 PSI. CHOKES- #1-40%/ #2-0%, FLARE-20-40' MUD CUT 9.9-9.6, MAX CASING PRESSURE= 810 PSI, AVG CASING PRESSURE=680 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 895 PSI, AVG SICP= 750 PSI. NOTE: PUMP 10BBL HIGH VIS SWEEP EVERY 300'
BOONE C 1H | 28 | 2021-08-03 10:15 | 2021-08-03 11:00 | 0.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.86 | 19092 | 19102 | 13.3 | SLIDE (10' IN .65 HRS @ 15 FPH) WOB-15/25K, SPM-72/72, GPM-375, MRPM-255, SPP-4820/4985 PSI, DIFF-75/150 PSI, CHOKES-#1-100%/ #2-100%, FLARE-5-8',MUD CUT 9.7-9.6, MAX CASING PRESSURE= 395 PSI, AVG CASING PRESSURE=85 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 684 PSI, AVG SICP= 464 PSI SLIDE DEPTHS: F/18,698'-T/18708', 10', TF:180, 07:21-08:00 NOTE: TARGET CHANGE @ 04:38 ON 8/3/21 (Plan 1 – 10303’ TVD AT 0 VS WITH 87.1 DEG INC 10’ ABOVE/ 0’ BELOW)
BOONE C 1H | 28 | 2021-08-03 11:00 | 2021-08-03 11:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 14.86 | 19102 | 19102 |  | MILESTONE_TD WELL ON 8/3/2021 @ 11:00
BOONE C 1H | 28 | 2021-08-03 11:00 | 2021-08-03 14:00 | 3 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.99 | 19102 | 19102 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN, PUMPING 2 TANDEM 30 BBL HIGH VIS SWEEPS. CIRCULATE 3 B/U, RPM-80, SPM: 72/72/0, GPM-375, INITIAL SPP-4900 PSI/FINAL SPP-4900, CHOKES- 0% / 30-50%, FLARE-0'-30', MAX CASING PRESSURE=530 PSI, MAX GAS: 2664u. 1ST BTM UP START TQ=15-23K, END=16-18K, P/U WT=225K, S/O=175K, ROT=190K 2ND BTM UP END TQ=13-17K, P/U WT=210, S/O WT=180K, ROT=190K 3RD BTM UP END TQ=12-16K, P/U WT=210K, S/O=180K, ROT=190K
BOONE C 1H | 28 | 2021-08-03 14:00 | 2021-08-03 16:45 | 2.75 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 15.1 | 19102 | 19102 | 0 | BACKREAM OUT OF HOLE F/19,102' T/17,578' GPM-350, PP-4000, RPM-80, TQ=14-24K CASING PSI WHILE REAMING=100-650 CASING PSI DURING CONNECTIONS= 500-900 PSI AT 17,578' SICP DURING CONNECTIONS INCREASED T/900 PSI. CIRC OUT GAS
BOONE C 1H | 28 | 2021-08-03 16:45 | 2021-08-03 17:30 | 0.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.14 | 19102 | 19102 | 0 | CIRCULATE OUT GAS @ 17,578'. GPM-350, PP-4100, RPM-60, TQ=13-15K. LOST APPROXIMATELY 110 BBLS WHILE CIRCULATING
BOONE C 1H | 28 | 2021-08-03 17:30 | 2021-08-03 18:00 | 0.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 15.16 | 19102 | 19102 | 0 | BACKREAM OUT OF HOLE F/17,578'- T/17,432' GPM-350, SPP-4200, RPM-80, TQ=14-24K CASING PSI WHILE REAMING=200-360 CASING PSI DURING CONNECTIONS= 400-576 PSI
BOONE C 1H | 28 | 2021-08-03 18:00 | 2021-08-03 19:45 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.23 | 19102 | 19102 | 0 | STRIP OUT OF THE HOLE F/17,432'-T/15,280'. PUMPING 9.5PPG OBM CALCULATED FILL DOWN BACKSIDE. CHOKE POSITION- 0% & 0% CASING PSI WHILE TRIPPING:282 CASING PSI DURING CONNECTIONS= 390
BOONE C 1H | 28 | 2021-08-03 19:45 | 2021-08-03 20:30 | 0.75 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.26 | 19102 | 19102 | 0 | SERVICE RIG: C/O HOSE ON ST-80
BOONE C 1H | 28 | 2021-08-03 20:30 | 2021-08-04 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.41 | 19102 | 19102 | 0 | STRIP OUT OF THE HOLE F/15.280'-T/10,025'. PUMPING 9.5PPG OBM CALCULATED FILL DOWN BACKSIDE. CHOKE POSITION- 0% & 0% CASING PSI WHILE TRIPPING:177 CASING PSI DURING CONNECTIONS= 249
BOONE C 1H | 28 | 2021-08-04 | 2021-08-04 00:15 | 0.25 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.42 | 19102 | 19102 | 0 | SERVICE RIG: C/O O-RING ON HYDRAULIC LINE ON TOP DRIVE.
BOONE C 1H | 28 | 2021-08-04 00:15 | 2021-08-04 01:15 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.46 | 19102 | 19102 | 0 | CIRC B/U @ INTERMEDIATE CGS SHOE (KEEPING BIT OUSIDE OF SHOE). GPM:300, SPP:2,605. MAX GAS:1,409u, MAX CSG PRESSURE:79. CHOKES: 0% & 50-100%.
BOONE C 1H | 28 | 2021-08-04 01:15 | 2021-08-04 01:30 | 0.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.47 | 19102 | 19102 | 0 | STRIP OUT OF THE HOLE F/10,025'-T/9,800'. PUMPING 9.5PPG OBM CALCULATED FILL DOWN BACKSIDE. CHOKE POSITION- 0% & 0% CASING PSI WHILE TRIPPING:140
BOONE C 1H | 28 | 2021-08-04 01:30 | 2021-08-04 03:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.53 | 19102 | 19102 | 0 | SPOT 55.4 BBLS OF 17# MUD CAP AND CHASE WITH 102.3BBLS OF 9.5# GPM:262 NOTE: CONDUCT FLOW CHECK. RESULT: NO FLOW/WELL STATIC. LINE UP TO TAKE RETURNS DOWN THE FLOWLINE.
BOONE C 1H | 28 | 2021-08-04 03:00 | 2021-08-04 04:45 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.6 | 19102 | 19102 | 0 | POOH F/9,800'-T/6,308'. HOLE TAKING AVG 1.74BBLS PER STD TO FILL HOLE.
BOONE C 1H | 28 | 2021-08-04 04:45 | 2021-08-04 05:15 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 15.63 | 19102 | 19102 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. NOTE:FLOW CHECK CONDUCTED PRIOR TO REMOVING RT-HEAD. RESULT: NO FLOW.
BOONE C 1H | 28 | 2021-08-04 05:15 | 2021-08-04 06:00 | 0.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.66 | 19102 | 19102 | 0 | POOH F/6,308''-T/5,900'. L/D AGITATOR #2, CONT. POOH F/5,900'-5,000'. HOLE TAKING AVG 1.74BBLS PER STD TO FILL HOLE.
BOONE C 1H | 29 | 2021-08-04 06:00 | 2021-08-04 08:15 | 2.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.75 | 19102 | 19102 | 0 | POOH F/5,000'-BHA, CALCULATED HOLE FILL 125.4 BBLS, ACTUAL HOLE FILL ON TRIP OUT 258.06 BBLS, 132.66 BBLS MORE THAN CALCULATED HOLE FILL ON TRIP OUT OF HOLE.
BOONE C 1H | 29 | 2021-08-04 08:15 | 2021-08-04 10:00 | 1.75 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 15.82 | 19102 | 19102 | 0 | DRAIN MOTOR, BREAK OFF BIT, LAY DOWN DIRECTIONAL BHA, MONITOR WELL WHILE LAYING DOWN BHA IN MOUSE HOLE, WELL TAKING 30-40 BPH.
BOONE C 1H | 29 | 2021-08-04 10:00 | 2021-08-04 10:30 | 0.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.84 | 19102 | 19102 | 0 | CLEAN AND ORGANIZE RIG FLOOR T/ ELIMINATE SLIP AND TRIP HAZARDS, PULL WEAR BUSHING.
BOONE C 1H | 29 | 2021-08-04 10:30 | 2021-08-04 12:15 | 1.75 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 15.92 | 19102 | 19102 | 0 | HELD PRE-JOB SAFTEY MEETING, RIG UP BUTCH'S RATHOLE CASING EQUIPMENT.
BOONE C 1H | 29 | 2021-08-04 12:15 | 2021-08-04 12:30 | 0.25 | P | PRDHLCSG | SFTY | SFYMTG | SAFETY MEETING | 15.93 | 19102 | 19102 | 0 | HELD PRE-JOB SAFETY MEETING ON CASING RUNNING OPERATIONS.
BOONE C 1H | 29 | 2021-08-04 12:30 | 2021-08-04 13:00 | 0.5 | U | PRDHLCSG | WAIT | WOW | WAIT ON WEATHER | 15.95 | 19102 | 19102 | 0 | WAIT ON WEATHER DUE T/ LIGHTNING AND SEVERE WEATHER CONDITIONS.
BOONE C 1H | 29 | 2021-08-04 13:00 | 2021-08-04 15:45 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.06 | 19102 | 19102 | 0 | MAKE-UP SHOE TRACK AND FLOW TEST, RUN 5' PRODUCTION T/ 1,689' MONITORING DISPLACEMENTS WITH NO RETURNS. NOTE: CIRCULATING TRIP TANK ON WELL WHILE RUNNING CASING WITH WELL LOSSES 15-17 BBLS PER EVERY 10 JOINTS.
BOONE C 1H | 29 | 2021-08-04 15:45 | 2021-08-04 17:15 | 1.5 | U | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.13 | 19102 | 19102 | 0 | TRANSFER 9.6 PPG OBM F/ MUD PITS T/ FRAC TANKS, TRNASFER 9.2 PPG OBM F/ FRAC TANKS T/ MUD PITS, CIRCULATE AND CONDITION MUD F/ 9.6 PPG T/ 9.0 PPG. ESTABLISH CIRCULATION AND STAGE UP MUD PUMPS F/ GPM=105, SPP=58 T/ GPM=236, SPP=236, WITH NO LOSSES. NOTE: AT 1700 HOURS LOSS 486 BBLS SINCE PREVIOUS MUD REPORT.
BOONE C 1H | 29 | 2021-08-04 17:15 | 2021-08-05 03:00 | 9.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.53 | 19102 | 19102 | 0 | RUN 5' PRODUCTION F/ 1,689' T/ 9,596' ,MONITORING & CATCHING DISPLACEMENTS, IN TRIP TANKS. STOPPED AT 5'200' CIRC BOTTOMS UP.
BOONE C 1H | 29 | 2021-08-05 03:00 | 2021-08-05 04:00 | 1 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 16.57 | 19102 | 19102 | 0 | REMOVE TRIP NIPPLE, INSTALL ROTATING HEAD.
BOONE C 1H | 29 | 2021-08-05 04:00 | 2021-08-05 05:00 | 1 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.61 | 19102 | 19102 | 0 | CIRCULATE MUD CAP OUT OF WELL @ 9,596' , MAX GAS 484 UNITS, MW= 9.0 PPG.
BOONE C 1H | 29 | 2021-08-05 05:00 | 2021-08-05 06:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.66 | 19102 | 19102 | 0 | CHANGE OUT 5" CASING TOOLS TO 5.5" CASING TOOLS. WHILE CHANGING TOOLS WELL STARTED FLOWING, CLOSED WELL IN PRESSURE BUILT TO 90 PSI WHILE CHANGING OUT CRT, LEVELED OUT AT 85 PSI.
BOONE C 1H | 30 | 2021-08-05 06:00 | 2021-08-05 07:15 | 1.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.71 | 19102 | 19102 | 0 | RUNNING 5.5” PRODUCTION CASING F/ 9596’ T/ 11,273’, MONITOR DISPLACEMENTS ON TRIP TANK, LOSS DISPLACEMENTS @ 11,273’.
BOONE C 1H | 30 | 2021-08-05 07:15 | 2021-08-05 09:15 | 2 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.79 | 19102 | 19102 | 0 | CIRCULATE AND CONDITION MUD T/ 9.0 PPG, ESTABLISH CIRCULATION AND STAGE UP MUD PUMPS F/ GPM=130, SPP=260 T/ GPM=210, SPP=533, MAX CASING PRESSURE WHILE CIRCULATING 220 PSI, MAX GAS= 570 UNITS, 20’-30’ FLARE, LOSS 83 BBLS WHILE CIRCULATING, DIVERTED 97 BBLS 10.0 PPG T/ 11.2 PPG MUD CAP T/ TRIP TANKS, MAX SICP= 167 PSI.
BOONE C 1H | 30 | 2021-08-05 09:15 | 2021-08-05 12:30 | 3.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.93 | 19102 | 19102 | 0 | STRIP IN HOLE W/ 5.5" PRODUCTION CASING F/ 11,273’ T/ 14,975’, BLEED OFF 1.3 BBLS DISPLACEMENT PER JOINT T/ TRIP TANK WHILE STRIPPING IN HOLE
BOONE C 1H | 30 | 2021-08-05 12:30 | 2021-08-05 14:45 | 2.25 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.02 | 19102 | 19102 | 0 | CIRCULATE AND CONDITION MUD T/ 9.0 PPG, ESTABLISH CIRCULATION AND STAGE UP MUD PUMPS F/ GPM=105, SPP=275 T/ GPM=183, SPP=825, MAX CASING PRESSURE WHILE CIRCULATING 60 PSI, MAX GAS= 705 UNITS, 5’-15’ FLARE, LOSS 124 BBLS WHILE CIRCULATING, DIVERTED 131 BBLS 10.0 PPG T/ 11.2 PPG MUD CAP T/ TRIP TANKS, MAX SICP= 78 PSI.
BOONE C 1H | 30 | 2021-08-05 14:45 | 2021-08-05 20:00 | 5.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.24 | 19102 | 19102 | 0 | STRIP IN HOLE F/ 14,975’ T/ 15,300’, BLEED OFF 1.3 BBLS DISPLACEMENT PER JOINT T/ TRIP TANK WHILE STRIPPING IN HOLE, LOSS DISPLACEMENT @ 15,300', OPEN ORBIT AND CONTINUE RUNNING 5.5" PRODUCTION CASING F/ 15,300' T/ 18,967', CIRCULATE TRIP TANK ON WELL AND MONITOR WELL WHILE RUNNING CASING, WELL TAKING 1-9 BBLS PER 10 JOINTS. PICK CASING STRING UP 20' TO REMOVE ANY BUCKLING FROM PIPE, ROTATE WITH CRT @ 30 RPM, TRQ-18-22K. WASH AND REAM PRODUCTION CASING F/18967' T/19061'; CHOKES CLOSED; REMOVE ROTATING HEAD, PICK UP LANDING JOINT AND WASH DOWN. LAND ON HANGER W/165K (W/O BLOCKS) @ 19,092'. RAN 5" & 5-1/2" P5ROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: 1-INNOVEX 5'' FLOAT SHOE, 1 JTS OF 5'' CSG. 1-INNOVEX FLOAT COLLAR, 1JT OF 5'' CSG. 1-GEODYNAMICS TOE SLEEVE VALVE, RAN 9,566.50' (206 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1- X-OVER, 1 JOINT 5-1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, RAN 9,422.77' (200 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING. FOR TOTAL OF 406 JTS OF 5'' 18#P-110 ICY WEDGE 425 & 5.5" 23# P-110 ICY BLUE CASING. CASING SHOE @ 19,092.85' TOP OF FLOAT COLLAR @ 19,040.80' BOTTOM OF TOE SLEEVE VALVE @ 18,993.80' TOP OF TOE SLEEVE VALVE @ 18,968.80' TOP OF X-OVER @ 9493.50' TOP OF MARKER JOINT ABOVE X-OVER @ 9426.10' 16 JOINTS OF 5" LEFT OUT-684.98' 11 JOINTS OF 5 1/2" LEFT OUT-516.14'
BOONE C 1H | 30 | 2021-08-05 20:00 | 2021-08-05 21:45 | 1.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.31 | 19102 | 19102 | 0 | CIRC CSG CAP PRIOR TO CONDUCTING PRODUCTION CMT JOB. GPM:210, CHOKES: 0%,
BOONE C 1H | 30 | 2021-08-05 21:45 | 2021-08-05 22:15 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 17.33 | 19102 | 19102 | 0 | RIG DOWN CRT AND INSTALL CEMENTING HEAD
BOONE C 1H | 30 | 2021-08-05 22:15 | 2021-08-06 00:45 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 17.44 | 19102 | 19102 | 0 | HELD PJSM,FLUSHED THROUGH & TESTED CEMENTING LINES T/9,000 PSI, CEMENTED, 5''/5.5" PRODUCTION CASING WITH NINE ENERGY SERVICES: , PUMPED 80 BBL 10.5 PPG WEIGHTED SPACER, 348 BBL 13.5 PPG 1170 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-BZ TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 372 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER WITH CORPLEX & 15 G CHEMICALS @ 7 BPM. SLOWED PUMP RATE TO 3.5 BPM, FINAL LIFT PRESSURE WAS 2,100 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3,100 PSI, HELD FOR 5 MIN, BLED BACK 4.0 BBLS. FLOATS HELD. PLUG DOWN @ 00:30 ON 8/06/2021. LEFT 169BBLS OBM IN HOLE, AND 80BBLS OF SPACER IN HOLE.
BOONE C 1H | 30 | 2021-08-06 00:45 | 2021-08-06 02:30 | 1.75 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 17.51 | 19102 | 19102 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING CASING PRESSURE, INITIAL CP-0 PSI, FINAL CP-0 PSI.
BOONE C 1H | 30 | 2021-08-06 02:30 | 2021-08-06 05:00 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 17.61 | 19102 | 19102 | 0 | LAYED DOWN LANDING JOINT, PICKED UP WELLHEAD WASHOUT TOOL AND FLUSHED OUT WELLHEAD. L/D WASHOUT TOOL, PICKED UP, INSTALLED, AND TESTED WELLHEAD PACK-OFF, PULL TESTED PACK-OFF TO 25K LBS AND TESTED PACK-OFF TO 10K PSI. L/D SETTING TOOL. INSTALLED BACK PRESSURE VALVE.
BOONE C 1H | 30 | 2021-08-06 05:00 | 2021-08-06 05:30 | 0.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 17.64 | 19102 | 19102 | 0 | REMOVE FLOW LINE, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI.
BOONE C 1H | 30 | 2021-08-06 05:30 | 2021-08-06 06:00 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 17.66 | 19102 | 19102 | 0 | RIG DOWN AND PREPPED RIG TO WALK TO THE BORGSTEAD UNIT 2H RELEASE WELL & RIG ON 8/6/2021 @06:00
BOONE C 1H | 30 | 2021-08-06 06:00 | 2021-08-06 06:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 17.66 | 19102 | 19102 |  | MILESTONE_WELL RELEASE ON 8/06/2021 @ 06:00
BORGSTEDT UNIT 2H | 1 | 2021-06-22 11:00 | 2021-06-22 11:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 6/22/2021 @ 11:00
BORGSTEDT UNIT 2H | 1 | 2021-06-22 11:00 | 2021-06-22 12:00 | 1 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/BOONE D 1H T/BORGETEDT 2H, SET MATS, WALK RIG TO BORGETEDT 2H; CENTER AND LEVELED SUB OVER CONDUCTOR.
BORGSTEDT UNIT 2H | 1 | 2021-06-22 12:00 | 2021-06-22 14:00 | 2 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | RIG UP CELLAR PUMPS, LINES, AND CONDUCTOR ON PIPE, CENTER CATWALK, MAKE UP MUDLINE, INSTALL MOUSE HOLE,
BORGSTEDT UNIT 2H | 1 | 2021-06-22 14:00 | 2021-06-22 15:00 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | RIG SERVICE
BORGSTEDT UNIT 2H | 1 | 2021-06-22 15:00 | 2021-06-22 15:30 | 0.5 |  | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP TO BHA CONSISTING OF BIT 13-1/2" ULTERRA U616S W: 6/16 JETS TFA: 1.18, MOTOR 7-3/4", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 108'.
BORGSTEDT UNIT 2H | 1 | 2021-06-22 15:30 | 2021-06-22 15:30 | 0 |  | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | SPUD WELL MILESTONE ON 6/22/2021 @15:30
BORGSTEDT UNIT 2H | 1 | 2021-06-22 15:30 | 2021-06-22 18:15 | 2.75 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.11 | 108 | 1630 | 553.5 | ROTATE 1522' IN 2.8 HR @ 544 FPH) WOB-10/20K, RPM-100, TRQ- 5/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1900/2300 PSI, DIFF-500/700 PSI.
BORGSTEDT UNIT 2H | 1 | 2021-06-22 18:15 | 2021-06-22 18:45 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.14 | 1630 | 1700 | 140 | SLIDE 70' IN .45 HRS @ 156FPH) WOB-5/12K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2000/2200 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SF/585 T/595 10', 1634-1637, TF-270 M SF/960 T/970 10' 1705-1708, TF-325 M SF/1055 T/1065 10' 1717-1721, TF-325 M SF/1335 T/1347 12' TIME-1745-1750, TF 325M SF/1523' T/1537' 14' 330 TIME 1817-1822 TF 330M SF/1617' T/1632' 14' 330 TIME 1833-1840 TF 330M
BORGSTEDT UNIT 2H | 1 | 2021-06-22 18:45 | 2021-06-22 19:15 | 0.5 | U | SFHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 0.16 | 1700 | 1700 | 0 | WORKING PIPE WHILE MAKING REPAIRS TO CELLAR PUMPS
BORGSTEDT UNIT 2H | 1 | 2021-06-22 19:15 | 2021-06-22 21:15 | 2 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.24 | 1700 | 2636 | 468 | ROTATE 936' IN 2.0 HR @ 468 FPH) WOB-10/15K, RPM-100, TRQ- 5/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1900/2300 PSI, DIFF-500/700 PSI.
BORGSTEDT UNIT 2H | 1 | 2021-06-22 21:15 | 2021-06-22 21:45 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.26 | 2636 | 2732 | 192 | SLIDE 96' IN .47 HRS @ 205FPH) WOB-5/10K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2000/2200 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: S F/1700' T/1714' 14' TF 330 19:16-19:21 S F/1804' T/1817' 13' TF 20R 19:34-19:38 S F/1898' T/1911' 13' TF 20R 19:48-19:53 S F/1992' T/2006' 14' TF HS 20:10-20:13 S F/2086' T/2100' 14' TF HS 20:23-20:26 S F/2180' T/2194' 14' TF HS 20:37-20:40 S F/2281' T/2295' 14' TF HS 20:53-20:58
BORGSTEDT UNIT 2H | 1 | 2021-06-22 21:45 | 2021-06-22 22:15 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 0.28 | 2732 | 2732 | 0 | PUMP 2-30 BBLS SWEEPS IN TANDEM AND CIRCULATE BOTTOMS UP. GPM=900, SPP=2400, RPM=100, TQ=2-3K
BORGSTEDT UNIT 2H | 1 | 2021-06-22 22:15 | 2021-06-22 23:45 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.34 | 2732 | 2732 | 0 | TOOH F/2732'T/BHA D.M 100% TIED OFF HOLE TAKING PROPER FILL
BORGSTEDT UNIT 2H | 1 | 2021-06-22 23:45 | 2021-06-23 00:45 | 1 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.39 | 2732 | 2732 | 0 | RACK BACK NMDC, REMOVE MWD TOOL, DRIAN MOTOR. RACK BACK MOTOR (LAY DOWN BIT, PU NEW ULTERRA U616S BIT)
BORGSTEDT UNIT 2H | 1 | 2021-06-23 00:45 | 2021-06-23 01:30 | 0.75 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 0.42 | 2732 | 2732 | 0 | HOLD PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT-BALES, LEVATORS, TONGS,CRT, BOWL, AND SLIPS,REMOVE CONDUCTOR RISER AND INSTALL CASING GUIDE TOOL ON CONDUCTOR.
BORGSTEDT UNIT 2H | 1 | 2021-06-23 01:30 | 2021-06-23 05:15 | 3.75 | U | SFHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 0.57 | 2732 | 2732 | 0 | CATWALK NOT RESPONDING. TROUBLE SHOOT, PATTERSON TECH ARRIVED ON LOCATION 04:00. FOUND BREAKER ISSUE ON CAT WALK. FUNCTION TEXT OKAY.
BORGSTEDT UNIT 2H | 1 | 2021-06-23 05:15 | 2021-06-23 06:00 | 0.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.6 | 2732 | 2732 | 0 | MAKING UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR
BORGSTEDT UNIT 2H | 2 | 2021-06-23 06:00 | 2021-06-23 09:45 | 3.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.76 | 2732 | 2732 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10-3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). THEN RUN 65 JOINTS (68 TOTAL) OF 10 3/4" 45.5# J-55 BT&C CASING T/2717.0'. RAN 35 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JOINT ALL THE WAY TO 76'. INSTALLED STREAM-FLO WELLHEAD WITH BASE PLATE AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED GATE VALVE T/10,000 PSI. SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET 85K (W/O BLOCKS) ON BASE PLATE. SHOE- 2717'. TOP OF FLOAT COLLAR- 2634.5' 13 JOINTS LEFT OUT-509.44'
BORGSTEDT UNIT 2H | 2 | 2021-06-23 09:45 | 2021-06-23 10:30 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.79 | 2732 | 2732 | 0 | CIRCULATE CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOL, GPM-385, SPP-180 PSI, NO LOSSES.
BORGSTEDT UNIT 2H | 2 | 2021-06-23 10:30 | 2021-06-23 11:00 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 0.81 | 2732 | 2732 | 0 | HOLD PJSM, RIG DOWN, L/D LANDING JOINT, AND RIG DOWN CELLAR PUMPS.
BORGSTEDT UNIT 2H | 2 | 2021-06-23 11:00 | 2021-06-23 11:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.81 | 2732 | 2732 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 6/23/2021 @ 11:00
BORGSTEDT UNIT 2H | 2 | 2021-06-23 11:00 | 2021-06-23 14:00 | 3 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.81 | 2732 | 2732 | 0 | PREP RIG TO WALK AND WALK RIG F/BORGSTEDT 2H T/BORGSTEDT 3H. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON. RIG UP CELLAR PUMPS FOR CEMENT JOB.
BORGSTEDT UNIT 2H | 2 | 2021-06-23 14:00 | 2021-06-23 16:00 | 2 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.81 | 2732 | 2732 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 296 BBLS 11.6 PPG LEAD CEMENT, 78 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 250 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED. PLUG W/ 700 PSI PRESSURED UP T/1300 PSI (600 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 160 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
BORGSTEDT UNIT 2H | 2 | 2021-06-23 16:00 | 2021-06-23 16:30 | 0.5 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.81 | 2732 | 2732 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD), RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
BORGSTEDT UNIT 2H | 3 | 2021-06-30 23:00 | 2021-06-30 23:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.81 | 2732 | 2732 |  | MILESTONE_RESUME WELL 1 ON 6/30/2021 @ 23:00
BORGSTEDT UNIT 2H | 3 | 2021-06-30 23:00 | 2021-07-01 01:30 | 2.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.92 | 2732 | 2732 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT. WALK 20' SW F/ BORGSTEDT OL 3H -T/BORGSTEDT OL 2H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA REP.
BORGSTEDT UNIT 2H | 3 | 2021-07-01 01:30 | 2021-07-01 05:00 | 3.5 | P | SFHLCSG | BOP | ND | NIPPLE DOWN BOP | 1.06 | 2732 | 2732 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BORGSTEDT UNIT 2H | 3 | 2021-07-01 05:00 | 2021-07-01 06:00 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.1 | 2732 | 2732 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST WELLHEAD CONNECTION & CHOKE LINE. 250 PSI LOW AND 5000 PSI HIGH.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 06:00 | 2021-07-01 08:15 | 2.25 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.2 | 2732 | 2732 | 0 | FINISH RIGGING UP FLOWLINE. PLACE WHIPCHECKS ON HYDRAULIC LINES. INSTALL WEAR BUSHING.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 08:15 | 2021-07-01 08:45 | 0.5 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.22 | 2732 | 2732 | 0 | LUBE TOP DRIVE, ST-80 AND DRWKS. ADD OIL TO THE TOP DRIVE.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 08:45 | 2021-07-01 09:15 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.24 | 2732 | 2732 | 0 | PREP RIG FLOOR FOR BHA. (MOUSEHOLE, SUBS, LIFT SUBS)
BORGSTEDT UNIT 2H | 4 | 2021-07-01 09:15 | 2021-07-01 11:45 | 2.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.34 | 2732 | 2732 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.78' BIT TO BEND; 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-70', GAMMA-60'. TEST MWD ( GOOD TEST).
BORGSTEDT UNIT 2H | 4 | 2021-07-01 11:45 | 2021-07-01 13:30 | 1.75 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.42 | 2732 | 2732 | 0 | TRIP IN HOLE F/BHA T/2,540' PICK UP AND TEST AGITATOR: PSI BEFORE-550.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 13:30 | 2021-07-01 14:00 | 0.5 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.44 | 2732 | 2732 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
BORGSTEDT UNIT 2H | 4 | 2021-07-01 14:00 | 2021-07-01 14:30 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.46 | 2732 | 2742 | 20 | TEST AGITATOR: PSI AFTER-750. DRILL SHOE TRACK + 10' NEW FORMATION F/2,732' T/2,742'. GPM-430, SPP-800, DP-1200/1600, RPM-40, TQ=2/7K
BORGSTEDT UNIT 2H | 4 | 2021-07-01 14:30 | 2021-07-01 15:15 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.49 | 2742 | 2742 | 0 | CIRCULATE BOTTOMS UP GPM-450, SPP-1250 PSI, RPM-40
BORGSTEDT UNIT 2H | 4 | 2021-07-01 15:15 | 2021-07-01 15:45 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.51 | 2742 | 2742 | 0 | PERFORM F.I.T WITH 9.1 PPG MUD, 351 PSI CSG PSI FOR 11.6 PPG EMW, SHOE MD-2,717' / TVD-2,701'
BORGSTEDT UNIT 2H | 4 | 2021-07-01 15:45 | 2021-07-01 17:00 | 1.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.56 | 2742 | 3039 | 237.6 | ROT 307' IN 1.25 HR @ 245.6 FPH) WOB: 30/42K, SPM: 110/0/110, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/22K, SPP: 3400/3800 PSI, DIFF: 500/800 PSI. NOTE: PUMP 12BBL SWEEP EVERY 300' SWEEP INGREDIENTS: MAGMAFIBER, NEWPHALT, CALCARB M, OPTI-WET. (12PPB CONCENTRATION)
BORGSTEDT UNIT 2H | 4 | 2021-07-01 17:00 | 2021-07-01 17:30 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.58 | 3039 | 3039 | 0 | CIRC WHILE ATTEMPTING TO REPAIR FLOWLINE LEAK
BORGSTEDT UNIT 2H | 4 | 2021-07-01 17:30 | 2021-07-01 18:00 | 0.5 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 1.6 | 3039 | 3039 | 0 | POOH W/BHA F/3,039'-T/2,717' (SHOE). TO REPAIR FLOWLINE KNUCKLEJOINT AIR BLADDER.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 18:00 | 2021-07-01 21:15 | 3.25 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 1.74 | 3039 | 3039 | 0 | C/O FLOWLINE KNUCKLE-JOINT AIR BLADDER.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 21:15 | 2021-07-01 21:45 | 0.5 | U | INTHL | TRIP | PUBHA | PICK UP BIT / BHA | 1.76 | 3039 | 3039 | 0 | TIH W/BHA F/2,717'-T/3,039'. NOTE: HOLE GIVING PROPER DISPLACMENT.
BORGSTEDT UNIT 2H | 4 | 2021-07-01 21:45 | 2021-07-02 05:30 | 7.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.08 | 3039 | 5540 | 322.7 | ROT 2,501' IN 7.78 HR @ 321.4 FPH) WOB: 30/42K, SPM: 110/0/110, GPM: 706, MMRPM: 117, RPM-40, TRPM: 157, TRQ: 10K/22K, SPP: 3400/3800 PSI, DIFF: 500/800 PSI. NOTE: PUMP 12BBL SWEEP EVERY 300' SWEEP INGREDIENTS: MAGMAFIBER, NEWPHALT, CALCARB M, OPTI-WET. (12PPB CONCENTRATION). DRILLING AT REDUCED RATE, DUE TO MODULE C/O ON #1 MP/#1 MODULE.
BORGSTEDT UNIT 2H | 4 | 2021-07-02 05:30 | 2021-07-02 06:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.1 | 5540 | 5576 | 72 | SLIDE 44' IN .58 HRS @ 75.86 FPH) WOB-5/12K, SPM-110/0/110, GPM-706, MMRPM-117, SPP-3400/3500 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: 10', TF 135, F/3,420'-T/3,430', 22:54-22:59 8', TF 111, F/3,600'-T/3,608', 23:38-23:51 8', TF 170R, F/4,170'-T/4,178', 01:39-01:45 10', TF 60R, F/5,115'-T/5,125', 04:24-0428 8', TF 160R F/5,396'- T/5,404', 05:22-0529 NOTE: DRILLING AT REDUCED RATE, DUE TO MODULE C/O ON #1 MP/#1 MODULE.
BORGSTEDT UNIT 2H | 5 | 2021-07-02 06:00 | 2021-07-02 07:45 | 1.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.18 | 5576 | 6124 | 313.1 | ROT 548' IN 1.75 HR @ 313 FPH) WOB: 30/42K, SPM: 110/0/110, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/22K, SPP: 3100/3800 PSI, DIFF: 500/700 PSI. NOTE: PUMP 12BBL SWEEP EVERY 300' SWEEP INGREDIENTS: MAGMAFIBER, NEWPHALT, CALCARB M, OPTI-WET. (12PPB CONCENTRATION). DRILLING AT REDUCED RATE, DUE TO MODULE C/O ON #1 MP/#1 MODULE.
BORGSTEDT UNIT 2H | 5 | 2021-07-02 07:45 | 2021-07-02 09:45 | 2 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.26 | 6124 | 6124 | 0 | CIRCULATE WITH #3 MP WHILE CHANGING MODULE GASKET ON #2 MP. GPM-353, PP-870, RPM-25, TQ=3-7K. (MECHANICS STILL CHANGING #1 MP #1 BAY MODULE.)
BORGSTEDT UNIT 2H | 5 | 2021-07-02 09:45 | 2021-07-02 17:45 | 8 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.59 | 6124 | 8058 | 241.7 | ROT 1934' IN 7.9 HR @ 245 FPH) WOB: 30/42K, SPM: 110/0/110, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 10K/22K, SPP: 3100/3800 PSI, DIFF: 500/700 PSI. NOTE: PUMP 12BBL SWEEP EVERY 300' SWEEP INGREDIENTS: MAGMAFIBER, NEWPHALT, CALCARB M, OPTI-WET. (12PPB CONCENTRATION). DRILLING AT REDUCED RATE, DUE TO MODULE C/O ON #1 MP/#1 MODULE.
BORGSTEDT UNIT 2H | 5 | 2021-07-02 17:45 | 2021-07-02 18:30 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.63 | 8058 | 8136 | 104 | SLIDE 78' IN 0.85 HRS @ 92 FPH) WOB-5/12K, SPM-110/0/110, GPM-706, MMRPM-117, SPP-3400/3500 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: 15' TF-140R F/6340 T/6355 1047-1100 15' TF-140R F/6435 T/6450 1120-1129 15' TF-130R F/6715 T/6730 1229-1235 15' TF-180 F/6995 T/7010 1335-1341 18' TF-120M F/7370 T/7388 1519-1536 NOTE: DRILLING AT REDUCED RATE, DUE TO MODULE C/O ON #1 MP/#1 MODULE.
BORGSTEDT UNIT 2H | 5 | 2021-07-02 18:30 | 2021-07-02 18:45 | 0.25 | U | INTHL | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 2.64 | 8136 | 8136 | 0 | CHANGE OUT LOW TORQUE VALVE ON STAND PIPE
BORGSTEDT UNIT 2H | 5 | 2021-07-02 18:45 | 2021-07-03 | 5.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.85 | 8136 | 9482 | 256.4 | ROT 1,346' IN 5.38 HR @ 250.18 FPH) WOB: 30/42K, SPM: 93/93/93, GPM: 895, MMRPM: 148, RPM-80, TRPM: 228, TRQ: 10K/22K, SPP: 4800/5650 PSI, DIFF: 500/750 PSI. NOTE: PUMP 12BBL SWEEP EVERY 300' SWEEP INGREDIENTS: MAGMAFIBER, NEWPHALT, CALCARB M, OPTI-WET. (12PPB CONCENTRATION)
BORGSTEDT UNIT 2H | 5 | 2021-07-03 | 2021-07-03 04:00 | 4 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.02 | 9482 | 9571 | 22.2 | SLIDE 89' IN 3.87 HRS @ 22.99 FPH) WOB-5/12K, SPM-93/93/93, GPM-895, MMRPM-148, SPP-4900/4980 PSI, DIFF-75/125 PSI. SLIDE DEPTHS: 15' TF-160M F/8,212'-T/8,227', 19:09-19:35 17' TF-135M F/8,405'-T/8,422', 20:07-20:34 20', TF 125M F/8,502'-T/8,522', 20:55-21:36. 7', TF 210M F/8,892'-T/8,899', 22:56-23:43 20', TF 215M, F/8,966'-T/8,986', 00:06-00:57 10', TF 285M, F/9,153'-T/9,163', 01:44-02:24
BORGSTEDT UNIT 2H | 5 | 2021-07-03 04:00 | 2021-07-03 06:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.1 | 9571 | 9629 | 29 | STARTED BUILDING INT. CURVE ON 7/3/21 @ 04:00 (9,571' MD / 9,491' TVD). SLIDE 55' IN 2 HRS @ 27.5 FPH) WOB-5/12K, SPM-93/93/93, GPM-895, MMRPM-148, SPP-4900/4980 PSI, DIFF-75/125 PSI.
BORGSTEDT UNIT 2H | 6 | 2021-07-03 06:00 | 2021-07-03 20:00 | 14 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.69 | 9626 | 9782 | 11.1 | BUILDING INT. CURVE F/9,626' T/9,782. (156' IN 14 HRS @ 11.14 FPH) WOB-5/12K, SPM-93/93/93, GPM-895, MMRPM-148, SPP-4900/4980 PSI, DIFF-75/125 PSI TF-35R NOTE: DRILL W/2MPS FOR 7.25HRS @ GPM: 690 SPP: 3,275PSI. (ISSUE:VFD OVER HEATING AND C/O SWAB ON #1MP)
BORGSTEDT UNIT 2H | 6 | 2021-07-03 20:00 | 2021-07-03 20:45 | 0.75 | U | INTHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 3.72 | 9782 | 9782 | 0 | ROTATING HEAD LEAKING, CHANGE OUT BEARING SECTION
BORGSTEDT UNIT 2H | 6 | 2021-07-03 20:45 | 2021-07-04 05:30 | 8.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.08 | 9782 | 9845 | 7.2 | BUILDING INT. CURVE F/9,782' T/9,845'. (63' IN 8.58 HRS @ 7.34 FPH) WOB-5/12K, SPM-93/93/93, GPM-895, MMRPM-148, SPP-4900/4980 PSI, DIFF-75/125 PSI TF-35R NOTE: DRILL WITH 2MPS FOR 3.25HRS @ GPM:690, SPP:3450. (ISSUES: LINER & SWAB #2MP/#2 MODULE. MODULE GASKETS IN #3MP/#1 & #2 SUCTION MODULES).
BORGSTEDT UNIT 2H | 6 | 2021-07-04 05:30 | 2021-07-04 06:00 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.1 | 9845 | 9845 | 0 | CIRC ON 1MP @ GPM:353, SPP:1,033 WHILE C/O SWAB ON #2 MP/ #1 MODULE. NOTE: #3 MP IS STILL DOWN DUE TO MODULE GASKET ON #1 MODULE SUCTION.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 06:00 | 2021-07-04 07:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.15 | 9845 | 9863 | 18 | BUILDING INT. CURVE (18' IN .97 HRS @ 18 FPH) WOB-5/12K, SPM-110/110/0, GPM-706, MMRPM-117, SPP-3200/340 PSI, DIFF-100/200 PSI SLIDE DEPTHS: F/9845 T/9863, 18' 10L 06:00-06:58 NOTE: #3 MP IS STILL DOWN DUE TO MODULE GASKET ON #1 MODULE SUCTION.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 07:00 | 2021-07-04 07:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.17 | 9863 | 9895 | 64 | ROT 32' IN .53 HR @ 60 FPH) WOB: 30/42K, SPM-110/110/0, GPM-706, MMRPM-117, SPP-3200/3900 PSI, DIFF-600/700 PSI RPM-80, TRPM: 197, TRQ: 10K/22K NOTE: #3 MP IS STILL DOWN DUE TO MODULE GASKET ON #1 MODULE SUCTION.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 07:30 | 2021-07-04 07:45 | 0.25 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.18 | 9895 | 9895 | 0 | MUD PUMP #1 HIGH PRESSURE MUD LINE O-RING GASKET BLEW. CIRCULATE WITH #2 MP, WHILE FINISH CHANGING MODULE GASKET ON #3 MP.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 07:45 | 2021-07-04 08:00 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.19 | 9895 | 9906 | 44 | ROT 11' IN .25 HR @ 44 FPH) WOB: 30/42K, SPM-110/110/0, GPM-706, MMRPM-117, SPP-3200/3900 PSI, DIFF-600/700 PSI RPM-80, TRPM: 197, TRQ: 10K/22K TD INTERMEDIATE CURVE SECTION ON 7/4/2021 @ 08:00 (9,906' MD / 9,821' TVD). NOTE: #2 MP IS STILL DOWN DUE TO C/O OF HIGH PRESSURE O-RING ON STAND-PIPE.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 08:00 | 2021-07-04 09:45 | 1.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.26 | 9906 | 9906 | 0 | PERFORMED CLEAN UP CYCLE PUMP 40 BBL SWEEP SURFACE TO SURFACE TO CLEAN HOLE & PREP OPEN HOLE FOR 7-5/8" CASING. GPM-706, PP-3300, RPM-30 TQ=6-12K. PERFORM FLOW CHECK-NO FLOW. PUMP SLUG. SWEEP CONTENTS: MAGNAFIBER 4 PPB NEWCARB 4 PPB NEWPHALT 4 PPB
BORGSTEDT UNIT 2H | 7 | 2021-07-04 09:45 | 2021-07-04 12:45 | 3 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.39 | 9906 | 9906 | 0 | TRIP OUT OF THE HOLE F/9906' - T/2,636'. HOLE HAD NO EXCESS DRAG ON TRIP OUT. PROPER FILLS ON TRIP OUT.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 12:45 | 2021-07-04 13:30 | 0.75 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 4.42 | 9906 | 9906 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE
BORGSTEDT UNIT 2H | 7 | 2021-07-04 13:30 | 2021-07-04 15:00 | 1.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.48 | 9906 | 9906 | 0 | L/D AGITATOR AND POOH T/BHA
BORGSTEDT UNIT 2H | 7 | 2021-07-04 15:00 | 2021-07-04 18:15 | 3.25 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.61 | 9906 | 9906 | 0 | RACKED BACK 2 STANDS OF 6.5" DRILL COLLARS, LAID DOWN TOP MONEL, REMOVED MWD TOOL, PICKED UP PUP JT, P/U AND DRAINED MUD MOTOR, BROKE OUT BIT, AND LAID DOWN MOTOR. PICKED UP NEW MOTOR AND RACKED BACK. NOTE: FLOW CHECK WAS CONDUCTED PRIOR TO BHA ENTERING THE BOP. RESULTED IN NO FLOW.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 18:15 | 2021-07-04 18:45 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.64 | 9906 | 9906 | 0 | PULLED WEAR BUSHING, PULLED MOUSEHOLE AND LAID DOWN SAME, CLEANED AND ORGANIZED RIG FLOOR FOR CASING RUN.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 18:45 | 2021-07-04 19:45 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.68 | 9906 | 9906 | 0 | SERVICE: TD, DRWKS, ST-80. CHECKED THREADS ON TD SAVER SUB= GOOD.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 19:45 | 2021-07-04 21:00 | 1.25 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.73 | 9906 | 9906 | 0 | HOLD PJSM AND RIG UP BUTCH'S CASING CREWS TOOLS & EQUIPMENT.
BORGSTEDT UNIT 2H | 7 | 2021-07-04 21:00 | 2021-07-05 06:00 | 9 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.1 | 9906 | 9906 | 0 | RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JT OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 192 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG T/ 8,541', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FREE FLOATING), AND INSTALLED 41 LATCH ON BOW SPRING CENTRALIZERS @ 9,585.4' AND EVERY 4TH JT UP TO 2,543.3'.
BORGSTEDT UNIT 2H | 8 | 2021-07-05 06:00 | 2021-07-05 07:30 | 1.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.17 | 9906 | 9906 | 0 | RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JT OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 32 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG T/ 9,895', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FREE FLOATING), AND INSTALLED 41 LATCH ON BOW SPRING CENTRALIZERS @ 9,585.4' AND EVERY 4TH JT UP TO 2,543.3'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/219K (W/O BLOCKS). FLOAT SHOE-9,895.4' TOP OF FLOAT COLLAR-9,804.2' 14 JOINTS LEFT OUT- 615.75'
BORGSTEDT UNIT 2H | 8 | 2021-07-05 07:30 | 2021-07-05 08:45 | 1.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.22 | 9906 | 9906 | 0 | CIRCULATE BTMS UP W/ RIG PUMPS VIA CRT, SPM: 105, 8.0 BPM, SPP:238 PSI, NO LOSSES. NOTE: R/D CSG CREW FLOOR EQUIPMENT WHILE CIRC IN PREP FOR CMT OPS.
BORGSTEDT UNIT 2H | 8 | 2021-07-05 08:45 | 2021-07-05 09:15 | 0.5 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 5.24 | 9906 | 9906 | 0 | R/D CRT & R/U CMT LINES.
BORGSTEDT UNIT 2H | 8 | 2021-07-05 09:15 | 2021-07-05 12:30 | 3.25 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.38 | 9906 | 9906 | 0 | PJSM, TEST LINES T/4,000 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 304 BBL 11.8 PPG 870 SK 1.96 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES,DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 450 BBLS OF 9.0 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1800 PSI AT 3.0 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/2300 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI(4 BBLS)-FLOATS HELD. FINISHED CEMENTING @ 12:23 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. NOTE: 40 BBLS OF SPACER AND 0 BBLS OF CEMENT TO SURFACE.
BORGSTEDT UNIT 2H | 8 | 2021-07-05 12:30 | 2021-07-05 13:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.4 | 9906 | 9906 | 0 | TEST CSG T/3500 PSI FOR 30 MINS. RESULTS= GOOD
BORGSTEDT UNIT 2H | 8 | 2021-07-05 13:00 | 2021-07-05 15:00 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.48 | 9906 | 9906 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON. FLUSH THROUGH BOP AND FLOW LINE WITH SUGAR WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
BORGSTEDT UNIT 2H | 8 | 2021-07-05 15:00 | 2021-07-05 17:00 | 2 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.56 | 9906 | 9906 | 0 | N/D BOPE, INSTALL WEATHER CAP AND SECURE WELL.
BORGSTEDT UNIT 2H | 8 | 2021-07-05 17:00 | 2021-07-05 17:00 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 5.56 | 9906 | 9906 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 7-5-2021 @ 17:00
BORGSTEDT UNIT 2H | 9 | 2021-08-06 06:00 | 2021-08-06 06:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 5.56 | 9906 | 9906 |  | MILESTONE_RESUME WELL OPERATIONS 2 ON 8/06/2021 @ 0600
BORGSTEDT UNIT 2H | 9 | 2021-08-06 06:00 | 2021-08-06 08:30 | 2.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.67 | 9906 | 9906 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK 40', FROM BOONE C 1H TO BORGSTEDT UNIT 2H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA REP. MAKE UP FLOW LINE TO MANIFOLD, SKID CATWALK AND SET V-DOOR
BORGSTEDT UNIT 2H | 9 | 2021-08-06 08:30 | 2021-08-06 10:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.73 | 9906 | 9906 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
BORGSTEDT UNIT 2H | 9 | 2021-08-06 10:00 | 2021-08-06 17:00 | 7 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.02 | 9906 | 9906 | 0 | BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW /10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 7000 HIGH, TEST ANNULAR 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ROTATING HEAD AND ORBIT VALVE TO 1500 PSI. REMOVE TEST PLUG AND RIG DOWN TESTERS.
BORGSTEDT UNIT 2H | 9 | 2021-08-06 17:00 | 2021-08-06 17:45 | 0.75 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 6.05 | 9906 | 9906 | 0 | R/D TESTERS, INSTALL WEAR BUSHING.
BORGSTEDT UNIT 2H | 9 | 2021-08-06 17:45 | 2021-08-06 19:15 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 6.11 | 9906 | 9906 | 0 | SLIP / CUT 70' DRILL LINE, WHILE FINISHING UP ACCUMULATOR DRAW DOWN TEST.
BORGSTEDT UNIT 2H | 9 | 2021-08-06 19:15 | 2021-08-06 20:15 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.16 | 9906 | 9906 | 0 | RIG SERVICE.
BORGSTEDT UNIT 2H | 9 | 2021-08-06 20:15 | 2021-08-06 23:00 | 2.75 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.27 | 9906 | 9906 | 0 | CHANGE OUT SAVER SUB ON TOP DRIVE. CLEAN RIG FLOOR
BORGSTEDT UNIT 2H | 9 | 2021-08-06 23:00 | 2021-08-06 23:15 | 0.25 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.28 | 9906 | 9906 | 0 | CHANGE ST-80 DIES
BORGSTEDT UNIT 2H | 9 | 2021-08-06 23:15 | 2021-08-07 01:00 | 1.75 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.35 | 9906 | 9906 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13618580 JETS 6/18S TFA: 1.491), 5", 6/7L, 8.8 STG @ 2.12° SLICK; 0.68 REV/GAL; 4.01' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5 1/4" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, 5" TOMAX, X/0, 2 STANDS DP, REAMER, 26 STANDS DP, AGITATOR, 33 STANDS DP AND ON DEMAND AGITATOR. BIT TO SVY-69'. BIT TO GAMMA-56'. TEST MWD (TEST GOOD)
BORGSTEDT UNIT 2H | 9 | 2021-08-07 01:00 | 2021-08-07 06:00 | 5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.56 | 9906 | 9906 | 0 | TRIP IN HOLE F/BHA T/5,960'. HOLE GIVING PROPER DISPLACEMENT ON TRIP IN. PICK UP AGITATOR @ 2,802'.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 06:00 | 2021-08-07 07:45 | 1.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.64 | 9906 | 9906 | 0 | TRIP IN HOLE F/5,960' T/9,804'. HOLE GIVING PROPER DISPLACEMENT ON TRIP IN.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 07:45 | 2021-08-07 08:15 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 6.66 | 9906 | 9906 | 0 | REMOVE TRIP NIPPLE, INSTALL ROTATING HEAD.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 08:15 | 2021-08-07 08:45 | 0.5 | P | INTHLCSG | TEST | FLWTST | FLOW TEST / DFIT | 6.68 | 9906 | 9906 | 0 | CIRC THREW GAS BUSTER TO INSURE NO BLOCKAGE, HOLD A BOP DRILL, BEFORE DRILLING OPERATIONS.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 08:45 | 2021-08-07 09:30 | 0.75 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 6.71 | 9906 | 9916 | 13.3 | DRILL OUT SHOE TRACK AND 10' NEW FORMATION T/9,916'. GPM:200, SPP:1,050, DIFF:300/500, WOB: 5-10K, RPM:30, MMRPM:136, TRPM:166 TQ:10/12K
BORGSTEDT UNIT 2H | 10 | 2021-08-07 09:30 | 2021-08-07 10:00 | 0.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.73 | 9916 | 9916 | 0 | CIRCULATE BOTTOMS UP, GPM-350, RPM:45,
BORGSTEDT UNIT 2H | 10 | 2021-08-07 10:00 | 2021-08-07 10:45 | 0.75 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.76 | 9916 | 9916 | 0 | PERFORM FIT TEST @ 9,810' TVD W/ 9.0 PPG OBM W/ 2,040 PSI SURFACE PSI, EMW = 13.0 PPG, PUMP TOTAL 4.68 BBLS @ .5 BPM, BLEED BACK 4.5 BBLS.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 10:45 | 2021-08-07 19:13 | 8.47 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.11 | 9916 | 10157 | 28.5 | BUILD CURVE-SLIDE (241' IN 8.47 HRS@ 28.4 FPH) WOB-20/35K, SPM-75/75, GPM-350, MRPM-238, SPP-3200/4000 PSI, DIFF-350/550 PSI, CHOKES- 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 60 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 90 PSI, AVG SICP= 70 PSI. SLIDE DEPTHS: F/9,916' T/10,378' 462' TF:HS 10:45-16:45 F/10,388'-T/10,472', 84', TF:HS, 16:45-17:42 F/10,502'-T/10,565', 63', TF:20R 18:00-18:45 F/10,630'-T/10,657', 27', TF:20R 19:30-20:00 F/10,717'-T/10,754', 37', TF:20R 20:30-20:55 F/10,776'-T/10,835', 30', TF:HS 20:30-20:55 F/10,475'-T/10,530', 55', TF:HS 0240-0338 F/10,540',-T/10,645', 105', TF:HS, 03:54-05:00
BORGSTEDT UNIT 2H | 10 | 2021-08-07 10:45 | 2021-08-07 10:45 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.76 | 9916 | 9916 |  | MILESTONE_START CURVE ON 8-07-2021 @ 10:45 HRS
BORGSTEDT UNIT 2H | 10 | 2021-08-07 19:13 | 2021-08-07 22:00 | 2.78 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.23 | 10157 | 10820 | 238.5 | BUILD CURVE-ROT (663' IN 3.28 HRS @ 202.1 FPH) WOB-30K, SPM-76/76, GPM-356, RPM-45, MRPM-242, TMRPM-287, TRQ-10/12K, SPP-3200/4000 PSI, DIFF-600/800 PSI.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 22:00 | 2021-08-07 22:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 7.23 | 10820 | 10820 |  | MILESTONE_LAND/END CURVE SECTION: 8/07/2021 @ 22:00 MD:10,820' TVD:10,337
BORGSTEDT UNIT 2H | 10 | 2021-08-07 22:00 | 2021-08-07 23:36 | 1.6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.3 | 10820 | 11010 | 118.7 | ROT (190' IN 0.45 HRS @ 189.55 FPH) WOB-30K, SPM-76/76, GPM-356, RPM-45, MRPM-242, TMRPM-287, TRQ-10/12K, SPP-3200/4000 PSI, DIFF-600/800 PSI.
BORGSTEDT UNIT 2H | 10 | 2021-08-07 22:00 | 2021-08-07 22:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 7.23 | 10820 | 10820 |  | MILESTONE_START HORIZONATAL LATERAL SECTION ON 8/07/2021 @ 22:00
BORGSTEDT UNIT 2H | 10 | 2021-08-07 23:36 | 2021-08-07 23:45 | 0.15 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.3 | 11010 | 11038 | 186.7 | SLIDE (28' IN .15 HRS@ 186.6 FPH) WOB-20/35K, SPM-75/75, GPM-350, MRPM-238, SPP-3200/4000 PSI, DIFF-350/550 PSI, CHOKES- 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 60 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 90 PSI, AVG SICP= 70 PSI. SLIDE DEPTHS: F/10,900' T/10,928' 28' TF:140R 22:45-23:00
BORGSTEDT UNIT 2H | 10 | 2021-08-07 23:45 | 2021-08-08 00:15 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.32 | 11038 | 11038 | 0 | SERVICE RIG AND EQUIPMENT.
BORGSTEDT UNIT 2H | 10 | 2021-08-08 00:15 | 2021-08-08 04:52 | 4.63 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.52 | 11038 | 11900 | 186.2 | ROT (862' IN 4.63 HRS @ 186.1 FPH) WOB-30K, SPM-76/76, GPM-356, RPM-45, MRPM-242, TMRPM-287, TRQ-10/12K, SPP-3200/4000 PSI, DIFF-600/800 PSI.
BORGSTEDT UNIT 2H | 10 | 2021-08-08 04:52 | 2021-08-08 06:00 | 1.12 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.56 | 11900 | 12018 | 105.4 | SLIDE (118' IN 1.12 HRS@ 105.3 FPH) WOB-20/35K, SPM-75/75, GPM-356, MRPM-262, SPP-3200/4000 PSI, DIFF-350/550 PSI, CHOKES- 0%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 65 PSI, AVG CASING PRESSURE= 60 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 90 PSI, AVG SICP= 70 PSI. SLIDE DEPTHS: F/11,038' T/11,058' 20' TF:180 00:26-00:40 F/11,239'-T/11,262', 23', TF:170L, 01:22-01:40 F/11,430'-T/11,445', 15', TF:HS 02:23-02:45 F/11,520'-T/11,530', 10', TF:HS 03:05-03:20 F/11,704'-T/11,729', 25', TF:70R 04:03-04:26 F/11,898'-T/11,928', 30', TF:180 05:10-05:30
BORGSTEDT UNIT 2H | 11 | 2021-08-08 06:00 | 2021-08-08 14:28 | 8.48 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.92 | 12018 | 13424 | 165.8 | ROT (1406' IN 8.48 HRS @ 165.8 FPH) WOB-42K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-20/30K, SPP-4000/4300 PSI, DIFF-400/1250 PSI.CHOKES- 100% / 100%, FLARE-1'-2', NO MUD CUT. MAX CASING PRESSURE WHILE DRILLING= 0 PSI AVG CASING PRESSURE WHILE DRILLING= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 75 PSI AVG CASING PRESSURE ON CONNECTIONS= 50 PSI TARGET LINE CHANGE VIA E-MAIL @ 10:25 HOURS Plan 1 – 10345’ TVD at 0 VS with 87.2 deg INC 5’ above/ 5’ below, 50’ left / 50’ right. WINDOW CHANGE 10’ ABOVE / 0’ DOWN VIA TEXT @ 11:53. TARGET LINE CHANGE VIA TEXT @ 13:32 HOURS Plan 1 – 10335’ TVD at 0 VS with 87.2 deg INC 5’ above/ 5’ below, 50’ left / 50’ right.
BORGSTEDT UNIT 2H | 11 | 2021-08-08 14:28 | 2021-08-08 17:00 | 2.52 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.02 | 13424 | 13678 | 100.8 | SLIDE (254' IN 2.52 HRS @ 100.7 FPH) WOB-28/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3500/4300 PSI,DIFF-400/600 PSI. SLIDE DEPTHS: F/12,074' T/12,097' 20' TF:140L 06:40-07:00 F/12,365'-T/12,390', 25', TF:HS, 08:15-08:36 F/12,556'-T/12,571', 15', TF:HS 09:17-09:33 F/12,651'-T/12,679', 28', TF:180 09:54-10:18 F/12,838'-T/12,850', 12', TF:130L 11:09-11:21 F/12,933'-T/12,963', 30', TF:130L 11:45-12:06 F/12,986' T/13,006' 20' TF:90L 12:20-12:44 F/13,118'-T/13,146', 28', TF:20L, 13:18-13:40 F/13,206'-T/13,213', 13', TF:20L 14:00-14:16 F/13,400'-T/14,430', 30', TF:90R 15:00-15:29 F/13,500'-T/13,518', 18', TF:180 15:50-16:10 F/13,594'-T/13,609', 15', TF:180 16:33-16:47
BORGSTEDT UNIT 2H | 11 | 2021-08-08 17:00 | 2021-08-08 18:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.06 | 13678 | 13678 | 0 | RIG SERVICE.
BORGSTEDT UNIT 2H | 11 | 2021-08-08 18:00 | 2021-08-08 18:15 | 0.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.07 | 13678 | 13686 | 32 | ROT (8' IN .25 HRS @ 32 FPH) WOB-42K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-20/30K, SPP-4000/4300 PSI, DIFF-400/1250 PSI.CHOKES- 100% / 100%, FLARE-1'-2', NO MUD CUT. MAX CASING PRESSURE WHILE DRILLING= 400 PSI AVG CASING PRESSURE WHILE DRILLING= 310 PSI MAX CASING PRESSURE ON CONNECTIONS= 95 PSI AVG CASING PRESSURE ON CONNECTIONS= 50 PSI
BORGSTEDT UNIT 2H | 11 | 2021-08-08 18:15 | 2021-08-08 18:30 | 0.25 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 8.08 | 13686 | 13686 | 0 | RIG BLACK OUT, CLOSE SUPER CHOKE AND MONITOR WELL, MAX CASING PRESSURE 275 PSI, CHANGE OUT FUEL FILTERS ON GENERATORS.
BORGSTEDT UNIT 2H | 11 | 2021-08-08 18:30 | 2021-08-08 21:40 | 3.17 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.22 | 13686 | 14200 | 162.1 | ROT (514' IN 3.17 HRS @ 162.1 FPH) WOB-42K, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-20/30K, SPP-4000/4300 PSI, DIFF-400/1250 PSI.CHOKES- 100% / 100%, FLARE-1'-2', NO MUD CUT. MAX CASING PRESSURE WHILE DRILLING= 0 PSI AVG CASING PRESSURE WHILE DRILLING= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 95 PSI AVG CASING PRESSURE ON CONNECTIONS= 50 PSI
BORGSTEDT UNIT 2H | 11 | 2021-08-08 21:40 | 2021-08-08 22:15 | 0.58 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.24 | 14200 | 14242 | 72.4 | SLIDE (42' IN .58 HRS @ 72.4 FPH) WOB-28/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3500/4300 PSI,DIFF-400/600 PSI. SLIDE DEPTHS: F/13,686' T/13,696' 10' TF:180 18:45-18:57 F/13,863'-T/13,696', 20', TF:180, 19:48-20:05 F/14,159'-T/14,171', 12', TF:180 21:11-21:40
BORGSTEDT UNIT 2H | 11 | 2021-08-08 22:15 | 2021-08-09 00:30 | 2.25 | P | PRDHLLT | LCIRC | LCIRC | LOST CIRCULATION | 8.33 | 14242 | 14242 | 0 | LOST FULL RETURNS @ 14,242', TRANSFER T/ FRAC TANK F/ ACTIVE, FILL TANK 6 W/ WATER, LINE UP MP 1&2 TO DRILL W/ WATER ON TANK 6, LINR UP FRAC TANK #1 T/ ACTIVE, LINE UP MP # 3 ON KILL LINE & TANK 4, FILL TANK #4 W/KILL MUD, PUMP 125BBLS OBM BEFORE SWITCHING TO WATER, PUMP 50BBLS OF KILL WEIGHT MUD DOWN BACKSIDE.
BORGSTEDT UNIT 2H | 11 | 2021-08-09 00:30 | 2021-08-09 05:28 | 4.98 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.54 | 14242 | 14881 | 128.3 | ROT (639' IN 4.98 HRS @ 1.28.3 FPH) WOB-42K, SPM-76/76, GPM-300, RPM-80, MRPM-204, TMRPM-284, TRQ-20/30K, SPP-4000/4300 PSI, DIFF-400/1250 PSI.CHOKES- 100% / 100%, FLARE-1'-2', NO MUD CUT. MAX CASING PRESSURE WHILE DRILLING= 400 PSI AVG CASING PRESSURE WHILE DRILLING= 250 PSI MAX CASING PRESSURE ON CONNECTIONS= 95 PSI AVG CASING PRESSURE ON CONNECTIONS= 50 PSI
BORGSTEDT UNIT 2H | 11 | 2021-08-09 05:28 | 2021-08-09 06:00 | 0.52 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.56 | 14881 | 14914 | 63.5 | SLIDE (33' IN .52 HRS @ 63.4 FPH) WOB-28/40K, SPM-76/76, GPM-300, MRPM-204, SPP-3500/3800 PSI,DIFF-350/600 PSI. SLIDE DEPTHS: F/14,252' T/14,255' 3' TF:180 00:31-00:38 F/14,526'-T/14,536', 10', TF:180, 02.:42-03:01 F/14,715'-T/14,735', 20', TF:150R 04:10-04:36
BORGSTEDT UNIT 2H | 12 | 2021-08-09 06:00 | 2021-08-09 07:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.6 | 14914 | 14980 | 66 | ROT (66' IN .90 HRS @ 73.33 FPH) WOB-30/40K, SPM-72/72/0, GPM- 375, RPM-80, MRPM-255, TMRPM-335, TRQ-20/24K, SPP-5850 PSI, DIFF-900/1200 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. PUMPING 5 BBL SWEEP EVERY OTHER CONNECTION OR AS NEEDED.
BORGSTEDT UNIT 2H | 12 | 2021-08-09 07:00 | 2021-08-09 07:45 | 0.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.64 | 14980 | 15031 | 68 | SLIDE (51' IN .85 HRS @ 60 FPH) WOB-20/40K, SPM-72/72/0, GPM- 375, MRPM-255, SPP-4800/5000 PSI, DIFF-200/300 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. SLIDE DEPTH: F/14914 T/14940 TF-110R 26' MIN-33 F/0600 T/0633 F/14999 T/15024 TF-120R 25' MIN-18 F/0725 T/0743
BORGSTEDT UNIT 2H | 12 | 2021-08-09 07:45 | 2021-08-09 09:30 | 1.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.71 | 15031 | 15031 | 0 | CIRCULATE W/ #1 MUD PUMP W/ CHANGING LINER GASKET IN #2 MUD PUMP, UNABLE T/ DRILL W/ #3 MUD PUMP DUE T/ POP-OFF VALVE AND BLADDER IN PULSATION DAMPENER RUPTURED.
BORGSTEDT UNIT 2H | 12 | 2021-08-09 09:30 | 2021-08-09 14:45 | 5.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.93 | 15031 | 15759 | 138.7 | ROT (728' IN 5.25 HRS @ 138.6 FPH) WOB-30/35K, SPM-72/72/0, GPM- 375, RPM-80, MRPM-255, TMRPM-335, TRQ-18/23K, SPP-4,900 PSI, DIFF-900/1200 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. PUMPING 5 BBL SWEEP EVERY OTHER CONNECTION OR AS NEEDED.
BORGSTEDT UNIT 2H | 12 | 2021-08-09 14:45 | 2021-08-09 17:15 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.03 | 15759 | 15847 | 35.2 | SLIDE (88' IN 2.5 HRS @ 35.2 FPH) WOB-35/40K, SPM-72/72/0, GPM- 375, MRPM-255, SPP-4800/4900 PSI, DIFF-300/400 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. SLIDE DEPTH: F/15188 T/15238 TF-120L 50' MIN-66 F/1054 T/1200 F/15282 T/15302 TF-180 20' MIN-45 F/1223 T/1308 F/15657 T/15675 TF-30R 18' MIN-33 F/1540 T/1613
BORGSTEDT UNIT 2H | 12 | 2021-08-09 17:15 | 2021-08-09 18:00 | 0.75 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.06 | 15847 | 15847 | 0 | RIG SERVICE.
BORGSTEDT UNIT 2H | 12 | 2021-08-09 18:00 | 2021-08-10 01:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.35 | 15847 | 16608 | 108.7 | ROT (761' IN 7.0 HRS @ 107.7 FPH) WOB-30/35K, SPM-72/72/0, GPM- 375, RPM-80, MRPM-255, TMRPM-335, TRQ-18/23K, SPP-5,900 PSI, DIFF-900/1200 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. PUMPING 5 BBL SWEEP EVERY OTHER CONNECTION OR AS NEEDED. TARGET CHANGE @ 02:30 TARGET LINE IS 10,355' TVD (VS=0) @ 87.2 WINDOW IS 5' ABOVE, 5' BELOW.
BORGSTEDT UNIT 2H | 12 | 2021-08-10 01:00 | 2021-08-10 06:00 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.56 | 16608 | 16730 | 24.4 | SLIDE (122' IN 5.0 HRS @ 24.4 FPH) WOB-35/40K, SPM-72/72/0, GPM- 375, MRPM-255, SPP-5000/5300 PSI, DIFF-300/400 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. SLIDE DEPTH: F/15857 T/15869 TF-160L 12' MIN-48 F/1808 T/1856 F/15951 T/15966 TF-160L 15' MIN-49 F/1930 T/2019 F/16139 T/16164 TF-30L 25' MIN-60 F/2136 T/2236 F/16329 T/16344 TF-160L 15' MIN-40 F/2340 T/0020 F/16427 T/16437 TF-160L 10' MIN-45 F/0056 T/0141 F/16517 T/16537 TF-160L 20' MIN-62 F/0213 T/0315 F/16613 T/16638 TF-160L 25' MIN-45 F/0356 T/0510
BORGSTEDT UNIT 2H | 13 | 2021-08-10 06:00 | 2021-08-10 10:45 | 4.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.76 | 16730 | 17394 | 139.8 | ROT (664' IN 4.62 HRS @ 143.72 FPH) WOB-30/40K, SPM-72/72/0, GPM- 375, RPM-80, MRPM-255, TMRPM-335, TRQ-20/24K, SPP-5800/6000 PSI, DIFF-900/1000 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. PUMPING 5 BBL SWEEP EVERY OTHER CONNECTION OR AS NEEDED. NOTE: ADDING 5 GALLONS PHPA EVERY 3-4 HOURS, BLENDING 30-40 BBL'S HOUR FLOWBACK WATER, 9 BBL'S HOUR OF DIESEL T/ TANK 6 W/ DRILLING, PUMPING 5 BBL HI VISC SWEEP EVERY OTHER STAND W/ ROTATING, PUMPING 5 BBL HI VISC SWEEP EVERY 20 MINUTES W/ SLIDING.
BORGSTEDT UNIT 2H | 13 | 2021-08-10 10:45 | 2021-08-10 14:30 | 3.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.92 | 17394 | 17489 | 25.3 | SLIDE (95' IN 3.88 HRS @ 24.48 FPH) WOB-20/40K, SPM-72/72/0, GPM- 375, MRPM-255, SPP-5200/5300 PSI, DIFF-150/250 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER AND BLEND OF FLOWBACK WATER. SLIDE DEPTH: F/16800 T/16825 TF-20R 25' MIN-61 F/0618 T/0719 F/16884 T/16894 TF-HS 10' MIN-24 F/0750 T/0814 F/17262 T/17292 TF-90R 30' MIN-72 F/1040 T/1152 F/17452 T/17482 TF-90R 30' MIN-76 F/1303 T/1419 NOTE: ADDING 5 GALLONS PHPA EVERY 3-4 HOURS, BLENDING 30-40 BBL'S HOUR FLOWBACK WATER, 9 BBL'S HOUR OF DIESEL T/ TANK 6 W/ DRILLING, PUMPING 5 BBL HI VISC SWEEP EVERY OTHER STAND W/ ROTATING, PUMPING 5 BBL HI VISC SWEEP EVERY 20 MINUTES W/ SLIDING.
BORGSTEDT UNIT 2H | 13 | 2021-08-10 14:30 | 2021-08-10 15:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.96 | 17489 | 17489 | 0 | PUMP 20 BBL SWEEP AND CIRCULATE SWEEP TO LOSS ZONE @ 14,242' WHILE FLUSHING DRILL STRING W/ DRILL WATER IN PREPARATION T/ BACK REAM OUT OF HOLE T/ LOSS ZONE DUE T/ WEIGHT STACKING OUT ON DRILL STRING AND NO DIFFERENTIAL PRESSURE F/ MUD MOTOR.
BORGSTEDT UNIT 2H | 13 | 2021-08-10 15:30 | 2021-08-10 20:30 | 5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 10.17 | 17489 | 17489 | 0 | BACK REAM OUT THE HOLE F/17,489' T/13,548’,SPM-72/72, GPM-375, RPM-80, MRPM-255,TMRPM-335, TRQ-12/26K, SPP-4800/5000 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI
BORGSTEDT UNIT 2H | 13 | 2021-08-10 20:30 | 2021-08-11 06:00 | 9.5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 10.56 | 17489 | 17489 | 0 | PULL OUT OF HOLE F/13,548’ T/2,800’, PUMPING 9.5 BBLS/STD OF 9.2 PPG MUD FOR CALCULATED FILL IN THE ANNULUS. PUMPED 30BBLS KILL MUD @ 8,959', PUMPED 50 BBLS KILL MUD @ 7,446', WELL FLOWING 5.3 BBLS AN HOUR PUMP 98 BBLS 16.5 PPG KILL MUD @ 5,260'
BORGSTEDT UNIT 2H | 14 | 2021-08-11 06:00 | 2021-08-11 06:45 | 0.75 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.59 | 17489 | 17489 | 0 | REMOVE ROTAING HEAD, LAY DOWN AGITATOR, INSTALL ROTATING HEAD.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 06:45 | 2021-08-11 08:15 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.66 | 17489 | 17489 | 0 | POOH F/ 2,800’ T/ BHA, PUMP 1.9 BBLS 16.5 PPG DOWN BACKSIDE F/ CALCULATED HOLE FILL, PUMP A TOTAL OF 84 BBLS 16.5 PPG DOWN BACKSIDE F/ CALCULATED HOLE FILL.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 08:15 | 2021-08-11 08:45 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.68 | 17489 | 17489 | 0 | REMOVE ROTAING HEAD, LAY DOWN AGITATOR, INSTALL TRIP NIPPLE.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 08:45 | 2021-08-11 10:30 | 1.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.75 | 17489 | 17489 | 0 | DRAIN MOTOR, BREAK OFF BIT, MAKE-UP MOTOR AND BIT, SCRIBE AND INSTALL MWD AND SURFACE TEST. NOTE: BROKE SHAFT ON MOTOR. NOTE: BIT GRADE 2-2-BT-S-X-O-DMF
BORGSTEDT UNIT 2H | 14 | 2021-08-11 10:30 | 2021-08-11 11:15 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.78 | 17489 | 17489 | 0 | TRIP IN HOLE F/ BHA T/ 2,800' WITH NO RETURNS.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 11:15 | 2021-08-11 12:00 | 0.75 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.81 | 17489 | 17489 | 0 | REMOVE TRIP NIPPLE, MAKE-UP AGITATOR AND INSTALL TRIP NIPPLE. NOTE: CIRCULATING PRESSURE PRIOR T/ AGITATOR 702 PSI, CIRCULATING PRESSURE AFTER AGITATOR 861 PSI.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 12:00 | 2021-08-11 12:45 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.84 | 17489 | 17489 | 0 | STRIP IN HOLE T/ 4,900’W/ NO RETURNS, CSG PSI = 420 PSI.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 12:45 | 2021-08-11 13:00 | 0.25 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 10.85 | 17489 | 17489 | 0 | PUMP 68 BBLS 16.5 PPG DOWN BACKSIDE, INITIAL CSG PSI = 420 PSI, FINAL CSG PSI = 0 PSI.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 13:00 | 2021-08-11 15:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.94 | 17489 | 17489 | 0 | STRIP IN HOLE F/ 4,900’ T/9,600' W/ NO RETURNS, CSG PSI = 0 PSI.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 15:00 | 2021-08-11 15:45 | 0.75 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.97 | 17489 | 17489 | 0 | RIG SERVICE.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 15:45 | 2021-08-11 19:30 | 3.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.13 | 17489 | 17489 | 0 | STRIP IN HOLE F/ 9,600’ T/16,300' W/WELL CLOSED IN, CSG PSI = 150-300. AT 15,300' HOLE STARTED TAKING WEIGHT AND CASING PRESS INCREASED TO 450 PSI, PUMPED 90 BBL OF 16.5 PPG KILL MUD DOWN THE ANNULUS. CASING PRESS FELL TO 0 PSI
BORGSTEDT UNIT 2H | 14 | 2021-08-11 19:30 | 2021-08-11 20:15 | 0.75 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 11.16 | 17489 | 17489 | 0 | CIRCULATE WITH 350 GPM 50 RPM 4,900 PSI WHILE CHANGING OUT DIE BLOCK ON ST-80
BORGSTEDT UNIT 2H | 14 | 2021-08-11 20:15 | 2021-08-11 22:00 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.23 | 17489 | 17489 | 0 | ATTEMPT TO STRIP IN HOLE @ 16,300', HOLE TAKING WEIGHT. WASH & REAM F/16,300' TO 17,489'. CSG PRESS- 0 PSI 375 GPM, 50 RPM.
BORGSTEDT UNIT 2H | 14 | 2021-08-11 22:00 | 2021-08-12 02:00 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.4 | 17489 | 18057 | 142 | ROT (568' IN 4 HRS @ 142 FPH) WOB-30/40K, SPM-72/72/0, GPM- 375, RPM-80, MRPM-255, TMRPM-335, TRQ-20/24K, SPP-5300/5600 PSI, DIFF-900/1000 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER.
BORGSTEDT UNIT 2H | 14 | 2021-08-12 02:00 | 2021-08-12 03:45 | 1.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.47 | 18057 | 18092 | 20 | SLIDE (35' IN 1.45 HRS @ 20' 8 FPH) WOB-20/40K, SPM-72/72/0, GPM- 375, MRPM-255, SPP-5200/5300 PSI, DIFF-150/250 PSI, SICP-0 PSI. DRILLING ON MUD CAP WITH FRESH WATER. SLIDE DEPTH: F/17728 T/17763 TF-90R 35' MIN-105 F/2345 T/0130
BORGSTEDT UNIT 2H | 14 | 2021-08-12 03:45 | 2021-08-12 03:45 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 11.47 | 18092 | 18092 |  | TD WELL @ 18,092 @ 03:45 ON 08-12-2021
BORGSTEDT UNIT 2H | 14 | 2021-08-12 03:45 | 2021-08-12 05:00 | 1.25 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.52 | 18092 | 18092 | 0 | PUMP TWO HIGH VIS SWEEPS @ 375 GPM WHILE WORKING PIPE. PUMP TWO 20 BBL HIGH VIS OBM SWEEPS AND CIRCULATE SWEEP TO LOSS ZONE @ 14,242', IN PREPARATION T/ BACK REAM OUT OF HOLE T/ LOSS ZONE
BORGSTEDT UNIT 2H | 14 | 2021-08-12 05:00 | 2021-08-12 06:00 | 1 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.56 | 18092 | 18092 | 0 | BACKREAM OUT OF HOLE F/18,092' T/ 17,200',SPM-72/72, GPM-375, RPM-80, MRPM-255,TMRPM-335, TRQ-12/26K, SPP-4800/5000 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI
BORGSTEDT UNIT 2H | 15 | 2021-08-12 06:00 | 2021-08-12 09:00 | 3 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.69 | 18092 | 18092 | 0 | BACK REAM OUT OF HOLE F/ 17,200’ T/ 14,000’, GPM=375, SPP=4600/4800, RPM=80, TRQ=6/22K.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 09:00 | 2021-08-12 11:15 | 2.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.78 | 18092 | 18092 | 0 | STRIP OUT OF HOLE F/ 14,000’ T/ 9,700’, PUMPING 1.9 BBLS PER STAND OF 9.5 PPG OBM CALCULATED HOLE FILLS DOWN BACKSIDE, PUMP TOTAL OF 86.5 BBLS 9.5 PPG OBM DOWN BACKSIDE, SICP=0 PSI.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 11:15 | 2021-08-12 11:30 | 0.25 | P | PRDHLCSG | FLWBK | FLCHK | FLOW CHECK | 11.79 | 18092 | 18092 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON FLOWLINE TO TRIP TANK, NO FLOW, SHUT IN WELL TO CONTINUE STRIPPING OUT OF HOLE.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 11:30 | 2021-08-12 16:45 | 5.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.01 | 18092 | 18092 | 0 | STRIP OUT OF HOLE F/ 9,700’ T/ 8,800, PUMPING 1.9 BBLS PER STAND OF 17.5 PPG OBM CALCULATED HOLE FILLS DOWN BACKSIDE, STRIP OUT OF HOLE F/ 8,800’ T/ 5,000', PUMPING 1.9 BBLS PER STAND OF 9.5 PPG OBM CALCULATED HOLE FILLS DOWN BACKSIDE, STRIP OUT OF HOLE F/ 5,000’ T/ BHA, PUMPING 1.9 BBLS PER STAND OF 17.5 PPG OBM CALCULATED HOLE FILLS DOWN BACKSIDE. NOTE: LAY DOWN AGITATOR, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 16:45 | 2021-08-12 18:00 | 1.25 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 12.06 | 18092 | 18092 | 0 | REMOVE MWD TOOL, DRAIN MOTOR, BREAK OFF BIT AND LAY DOWN DIRECTIONAL BHA.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 18:00 | 2021-08-12 19:00 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 12.1 | 18092 | 18092 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELEVATORS.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 19:00 | 2021-08-12 19:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.12 | 18092 | 18092 | 0 | RIG SERVICE.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 19:30 | 2021-08-12 21:00 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 12.19 | 18092 | 18092 | 0 | HELD PJSM, RIG UP BUTCH'S CASING 5" CASING TOOLS AND EQUIPMENT.
BORGSTEDT UNIT 2H | 15 | 2021-08-12 21:00 | 2021-08-13 06:00 | 9 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.56 | 18092 | 18092 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS,MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/7,400', FILLING PIPE ON THE FLY W/ WATER, W/ NO RETURNS. NOTE: REMOVE TRIP NIPPLE AND INSTALLED ROTATING HEAD @ 1,800'. PUMPED 50 BBLS OF KILL MUD DUE TO CASING PRESURE COMING UP TO 280PSI.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 06:00 | 2021-08-13 07:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.6 | 18092 | 18092 | 0 | PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING f/ 7,400' / 8,679', FILLING PIPE ON THE FLY W/ WATER, W/ NO RETURNS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 07:00 | 2021-08-13 08:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 12.65 | 18092 | 18092 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 08:00 | 2021-08-13 10:30 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.75 | 18092 | 18092 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/8,679' T/12,770', FILLING PIPE ON THE FLY,NO RETURNS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 10:30 | 2021-08-13 11:00 | 0.5 | U | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 12.77 | 18092 | 18092 | 0 | TROUBLE SHOOT HYDRAULIC UNIT F/ CASING TONGS, SWAP OUT HYDRAULIC UNIT F/ CASING TONGS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 11:00 | 2021-08-13 14:45 | 3.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.93 | 18092 | 18092 | 0 | RUN 5-1/2" 23# P-110 CASING F/12,700' T/17,951'. WASH AND REAM F/ 17,951' T/ 18,046', GPM=132, SPP=2450, RPM=25, TORQ=11/23K, FILLING PIPE WITH WATER ON THE FLY. NO RETURNS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 14:45 | 2021-08-13 16:00 | 1.25 | U | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.98 | 18092 | 18092 | 0 | MAKE-UP LANDING JOINT IN PREPARATION T/ WASH AND REAM LANDING JOINT DOWN, LANDING JOINT LEAKING BETWEEN RUNNING TOOL AND HANGER, BACK OUT LANDING JOINT AND CHANGE O'RING, MAKE-UP LANDING JOINT AND ATTEMPT TO WASH AND REAM LANDING JOINT DOWN, LANDING JOINT LEAKING BETWEEN RUNNING TOOL AND HANGER, BACK OUT LANDING JOINT AND HANGER AND LAY DOWN.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 16:00 | 2021-08-13 17:15 | 1.25 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.03 | 18092 | 18092 | 0 | CIRCULATE AND WORK CASING WHILE WAITING ON LANDING JOINT, GPM=132, SPP=2800, RPM=28, TORQ=8/23K, PUMP 100 BBLS 17.5 PPG OBM DOWN BACKSIDE WHILE CIRCULATING, MAX CASING PSI= 1966 PSI.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 17:15 | 2021-08-13 17:30 | 0.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.04 | 18092 | 18092 | 0 | MAKE-UP LANDING JOINT, WASH AND REAM LANDING JOINT DOWN, GPM=184, SPP=2900, RPM=28, TORQ=11/19K, LAND OUT CASING W/ 138K, ROTATING WT= 180K. CASING SHOE @ 18,077.30' TOP OF FLOAT COLLAR @ 18,025.10' BOTTOM OF TOE SLEEVE VALVE @ 17,978.20' TOP OF TOE SLEEVE VALVE @ 17,953.10' TOP OF X-OVER @ 9,395.30' TOP OF MARKER JOINT ABOVE X-OVER @ 9,328.30' TOP OF PUP JOINT @ 125.30'
BORGSTEDT UNIT 2H | 16 | 2021-08-13 17:30 | 2021-08-13 18:30 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 13.08 | 18092 | 18092 | 0 | RIG DOWN CRT AND INSTALL FOSV, CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO CEMENTERS STAND PIPE, RIG DOWN BUTCH'S CASING TOOLS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 18:30 | 2021-08-13 21:00 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 13.19 | 18092 | 18092 | 0 | 1ST STAGE HELD PJSM,FLUSHED THROUGH & TESTED CEMENTING LINES T/9500 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: PUMPED 40 BBL 10.5 PPG WEIGHTED SPACER, 101 BBL 13.5 PPG 340 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT, FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 352 BBLS (1ST 20 BBLS SUGAR WATER) FINAL LIFT PRESSURE WAS 3170 PSI, @ 4.5 BPM,, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4200 PSI, HELD FOR 5 MIN, BLED BACK 5 BBLS. FLOATS HELD. PLUG DOWN @ 21:00 ON 8/13/2021
BORGSTEDT UNIT 2H | 16 | 2021-08-13 21:00 | 2021-08-13 21:30 | 0.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 13.21 | 18092 | 18092 | 0 | SAFETY MEETING, RIG DOWN CEMENTING LINES FROM RIG FLOOR AND INSTALL LINES TO KILL LINE FOR 2ND STAGE CEMENT DOWN ANNULUS.
BORGSTEDT UNIT 2H | 16 | 2021-08-13 21:30 | 2021-08-13 23:30 | 2 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 13.29 | 18092 | 18092 | 0 | 2ND STAGE TESTED CEMENTING LINES T/5000 PSI, PUMP 100 BBLS 16 PPG WBM KILL MUD DOWN THE ANNULUS THROUGH KILL LINE @ 1 BPM=48 PSI & CASING PSI= 0 PSI, 2 BPM= 65 PSI & CASING PSI=0 PSI, 3 BPM= 96 PSI & CASING PSI= 0 PSI, 4 BPM= 140 PSI & CASING PSI=0 PSI 5 BPM=195 PSI & CASING PSI= 0 PSI AND 6 BPM=2600 PSI & CASING PSI= 2100 PSI TO ESTABLISH INJECTION RATE. INITIAL CP-0 PSI. FINAL CP-2600 PSI. PUMP 40 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 296 BBLS 995 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.67 YIELD TYPE l/ll TAIL CEMENT, FOLLOWED BY 20 BBLS WATER WITH 15G CHEMICALS. MAX CSG PSI 0 PSI W/290 BBLS LEAD CMT PUMPED @ 9 BPM, AVG CASING PSI=3100 PSI, FINAL CASING PSI= 3850 FINISH JOB AT 23:00 08/13/2021
BORGSTEDT UNIT 2H | 16 | 2021-08-13 23:30 | 2021-08-14 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 13.31 | 18092 | 18092 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING CASING PRESSURE, INITIALCP-0 PSI, FINAL CP-0 PSI.
BORGSTEDT UNIT 2H | 16 | 2021-08-14 | 2021-08-14 01:00 | 1 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 13.35 | 18092 | 18092 | 0 | WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE BAILS AND CASING ELEVATORS.
BORGSTEDT UNIT 2H | 16 | 2021-08-14 01:00 | 2021-08-14 03:30 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 13.46 | 18092 | 18092 | 0 | MONITORED FLOW, NO FLOW, LAYED DOWN LANDING JOINT, PICKED UP WELLHEAD WASHOUT TOOL AND FLUSHED OUT WELLHEAD. L/D WASHOUT TOOL, PICKED UP, INSTALLED, AND TESTED WELLHEAD PACK-OFF, PULL TESTED PACK-OFF TO 20K LBS AND TESTED PACK-OFF TO 10K PSI. L/D SETTING TOOL. INSTALLED BACK PRESSURE VALVE. TEST WELL CAP T/5000 PSI
BORGSTEDT UNIT 2H | 16 | 2021-08-14 03:30 | 2021-08-14 04:30 | 1 | P | PRDHLLT | BOP | ND | NIPPLE DOWN BOP | 13.5 | 18092 | 18092 | 0 | LATCH BOP WRANGLER, NIPPLE DOWN BOP, REMOVE FLOW LINE, REMOVE STAND PIPE, KILL LINE, RAISE V-DOOR.
BORGSTEDT UNIT 2H | 16 | 2021-08-14 04:30 | 2021-08-14 06:00 | 1.5 | P | PRDHLLT | RURD | RDEQP | RIG DOWN EQUIPMENT | 13.56 | 18092 | 18092 | 0 | RIG DOWN AND PREPPED RIG TO WALK TO THE BORGSTEAD UNIT 3H RELEASE WELL & RIG ON 8/14/2021 @06:00
BORGSTEDT UNIT 2H | 16 | 2021-08-14 06:00 | 2021-08-14 06:00 | 0 | P | PRDHLLT | MSTN | RRLS | MILESTONE_RIG RELEASE | 13.56 | 18092 | 18092 |  | MILESTONE_WELL RELEASE ON 8/14/2021 @ 06:00
BUCKY BADGER H02 BB | 1 | 2022-03-02 06:00 | 2022-03-03 06:00 | 24 | P | MOBDMOB | LMOV | RDMO | RIG DOWN MOVE OUT | 0 | 105 | 105 | 0 | CONTINUE R/D AND MOVE T/ BUCKY BADGER PAD. RIG DOWN- FRAC TANKS, RIG DOWN BULK TANKS, CEMENT SILO'S, FLOWLINE SKID, GASBUSTER, FLARE STACK, MUD TANKS, TRIP TANK SKID, RIG FLOOR, HOIST LINES, DERRICK BOARD, GENERATORS, MUD PUMPS, VFD, GRASSHOPPER, RIG DIESEL TANK, MUD DIESEL TANK. MOVE OUT T/ BUCKY BADGER- OPEN TOP TANKS, MAGNOLIA LIVING QUARTERS, MUD TANKS, TRIP TANK SKID, CHOKE MANIFOLD, SHAKER SKID, FLOWLINE SKID, 2 MUD PUMPS, SOLIDS CONTROL EQUIPMENT, GAS BUSTER, FRAC TANKS, PARTS HOUSE, MISC. SUBS SQUATED @ 23:30 DERRICK LAYED OVER @ 01:30, DRESS DOWN DERRICK, REMOVE MONKEY BOARD, PULL BLOCK TO CROWN SECTION
BUCKY BADGER H02 BB | 2 | 2022-03-03 06:00 | 2022-03-04 06:00 | 24 | P | MOBDMOB | LMOV | RDMO | RIG DOWN MOVE OUT | 0 | 105 | 105 | 0 | CONTINUE R/D AND MOVE T/ BUCKY BADGER H02 BB. RIG DOWN- REMOVE DERRICK SECTIONS, A LEGS, ODS HOUSE, DS HOUSE, DRAWWORKS, CENTERSTEEL, SEPARATE SUBS. MOVE OUT T/ BUCKY BADGER- MATTING BOARDS, ODS HOUSE, DS HOUSE, DRAWWORKS, SUBS, DERRICK, 1 MP, GENS, VFD, PATTERSON CREW QUARTERS, MISC. SET- PITS, SHAKER SKID, MP'S, VFD, SUITCASE, GENS, MATTING BOARDS, GRASSHOPPER, SUBS W/ DS AND ODS CABINS, CHOKE SKID, DRYING SHAKERS, HOPPER HOUSE, DAY TANK. PIN DERRICK, SPOOL UP, INSTALL BOARD, DRESS OUT DERRICK AND SPOT SOLIDS CONTROL EQUIPMENT, BULK TANKS. RIGGED UP- HOPPER HOUSE, PITS, SHAKER SKID, MP'S, FRAC TANKS.
BUCKY BADGER H02 BB | 3 | 2022-03-04 06:00 | 2022-03-05 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 105 | 105 | 0 | CONTINUE RIGGING UP ON BUCKY BADGER H02 BB, FINISH DRESSING OUT DERRICK, R/U VIBRATING HOSE TO SUBS, HOOK UP ELECTRICAL TO PUMPS, C/O SALA BLOCK ON BOARD, PRE-RAISE DERRICK INSPECTION, HOLD PJSM FOR RAISING DERRICK, RAISE DERRICK @ 10:45, UNPIN MSRC'S F/ DERRICK, R/U MSRCS T/ HORSE'S HEAD, R/U DRILL LINE UNIT TO SUBS, INSTALL BOP WRANGLER, HOLD PJSM ON RAISING SUBS, RAISE SUBS @ 12:30, R/U V-DOOR, CATWALK, FLOW LINE, PULL BOOSTERS AND INSTALL STOMPERS, INSTALL DS AND ODS STAIRS, R/U CMS TO SUBS, R/U MUDLINE TO DERRICK WITH CRANE, R/U GASBUSTER FLARE LINE, AND FLARE. POWER UP ELECTRICAL T/RIG FLOOR MUD PUMPS AND HOPPER HOUSE, RIG UP HOIST LINE CABLES AND BOOM POLE, POWER UP RIG, TROUBLESHOOT DW, HANG TONGS, RIG UP WEIGHT BUCKET LINES AND GERONIMO LINE ,SPOOL UP DW,UNPIN DW AND CALABRATE, TROUBLESHOOT TOP DRIVE, RIG UP STANDPIPE, PUT ALL GENERATORS ON LINE, FUNCTION TEST MUD PUMPS.
BUCKY BADGER H02 BB | 4 | 2022-03-05 06:00 | 2022-03-05 14:00 | 8 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 105 | 105 | 0 | RIG UP ON BUCKY BADGER H02: R/U CATWALK, CHANGE OUT POWER PLUG TO REMOTE, WORK ON TOP DRIVE- CHANGE OUT BLOWER SENSORS AND RUN TOP DRIVE- GOOD, RUN TRIP TANK PUMPS, RUN MP #1, #2, #3; RUN SHAKERS, MUD MIXERS, DESANDER AND DESILTER PUMPS, R/U KOOMIE HYDRAULICS T/SUBS, WORK ON CRI, R/U STOMPERS ON CATWALK, CLEAN OUT BTM CHANGE HOUSE, CHANGE OUT OIL LINE ON MUD PUMP #1, R/U STOMPERS T/RIG, WELD HAND RAIL ON DS STAIRS, PREP RIG FLOOR F/ SPUD IN, AIR OUT ALL 3 MUD PUMPS, PRESSURE TEST STAND PIPE LINES T/1500 PSI, TEST GOOD- NO LEAKS. NOTE: ACCEPT RIG @ 14:00.
BUCKY BADGER H02 BB | 4 | 2022-03-05 14:00 | 2022-03-05 15:00 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 105 | 105 | 0 | LUBRICATE RIG.
BUCKY BADGER H02 BB | 4 | 2022-03-05 15:00 | 2022-03-05 17:30 | 2.5 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 105 | 105 | 0 | PICK UP BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS; 13" NORTRAC IBS, 8" NMPDC, 7-3/4" UBHO, (2) 8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, (9) JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 105'.
BUCKY BADGER H02 BB | 4 | 2022-03-05 17:30 | 2022-03-05 17:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 105 | 105 |  | MILESTONE_SPUD WELL ON 3/5/2022 @ 17:30.
BUCKY BADGER H02 BB | 4 | 2022-03-05 17:30 | 2022-03-05 23:45 | 6.25 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.26 | 105 | 2828 | 435.7 | ROTATE (2,723’ IN 6.1 HRS @ 446 FPH) WOB-20-30K, RPM-100, TRQ- 2/18K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1900/2500 PSI, DIFF-400/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300' PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 1,000' NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 486 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM.
BUCKY BADGER H02 BB | 4 | 2022-03-05 23:45 | 2022-03-06 01:45 | 2 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.34 | 2828 | 3033 | 102.5 | SLIDE (205' IN 2.15 HRS @ 95 FPH) WOB-5/15K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2,000/2,150 PSI, DIFF-50/150 PSI. SLIDE DEPTHS: F/1055' T/1065' 10' 335M TIME 1944-1948 F/1150' T/1158' 8' 350M TIME 2000-2004 F/1335' T/1345' 10' 270M TIME 2025-2030 F/1430' T/1440' 10' 270M TIME 2038-2043 F/1525' T/1533' 8' 275M TIME 2053-2058 F/1617' T/1625' 8' 275M TIME 2107-2112 F/1714' T/1724' 10' 275M TIME 2124-2128 F/1805' T/1815' 10' 10L TIME 2141-2148 F/1898' T/1910' 12' 20L TIME 2200-2205 F/1991' T/2006' 15' 20L TIME 2219-2228 F/2085' T/2100' 15' 20L TIME 2239-2253 F/2178' T/2196' 18' 20L TIME 2302-2315 F/2273' T/2291' 18' 10L TIME 2325-2335 F/2367' T/2384' 17' HS TIME 2346-2400 F/2462' T/2480' 18' HS TIME 0007-0017 F/2554' T/2572' 18' HS TIME 0026-0036 F/2651' T/2661' 10' HS TIME 0050-0100
BUCKY BADGER H02 BB | 4 | 2022-03-06 01:45 | 2022-03-06 02:15 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.36 | 3033 | 3033 | 0 | PUMP (2) 30 BBL GEL SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-50, TRQ-1/2K, SPP-2,130 PSI, FLOW CHECK WELL (NO FLOW), FILL CELLAR FOR TOH.
BUCKY BADGER H02 BB | 4 | 2022-03-06 02:15 | 2022-03-06 03:45 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.43 | 3033 | 3033 | 0 | TOH F/3,033' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
BUCKY BADGER H02 BB | 4 | 2022-03-06 03:45 | 2022-03-06 04:15 | 0.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.45 | 3033 | 3033 | 0 | RACK BACK 3 STANDS OF HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. BIT GRADE: 0-0-NO-A-X-0-NO-TD MOTOR DRAINED WELL WITH MIN SQUAT
BUCKY BADGER H02 BB | 4 | 2022-03-06 04:15 | 2022-03-06 05:30 | 1.25 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 0.5 | 3033 | 3033 | 0 | HOLD PJSM WITH CASING CREW, RIG UP BUTCH'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS, REMOVE CONDUCTOR RISER AND INSTALL CASING GUIDE TOOL ON CONDUCTOR.
BUCKY BADGER H02 BB | 4 | 2022-03-06 05:30 | 2022-03-06 06:00 | 0.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.52 | 3033 | 3033 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10-3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING.
BUCKY BADGER H02 BB | 5 | 2022-03-06 06:00 | 2022-03-06 09:00 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.65 | 3033 | 3033 | 0 | MAKE UP (1) FLOAT SHOE, (2) JOINTS. 10-3/4" 45.5# J-55 BT&C CASING, (1) FLOAT COLLAR, (1) JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS- TEST GOOD. THEN RUN (73) JOINTS OF 10 3/4" 45.5# J-55 BT&C CASING AND (1) 10 3/4" 45.5# J-55 BT&C PUP JT T/ 3,018'. RAN 38 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JOINT ALL THE WAY TO 190.4'. INSTALLED STREAM-FLO WELLHEAD WITH BASE PLATE AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED WELLHEAD T/5000 PSI. SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET 110K (W/O BLOCKS) ON BASE PLATE. SHOE- 3,018' TOP OF FLOAT COLLAR- 2,939' (8) JOINTS LEFT OUT- 314.68'
BUCKY BADGER H02 BB | 5 | 2022-03-06 09:00 | 2022-03-06 09:30 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 0.67 | 3033 | 3033 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOL, GPM-339, SPP-130 PSI, NO LOSSES.
BUCKY BADGER H02 BB | 5 | 2022-03-06 09:30 | 2022-03-06 09:45 | 0.25 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.68 | 3033 | 3033 | 0 | HOLD PJSM, RIG DOWN CASING TOOLS, L/D LANDING JOINT
BUCKY BADGER H02 BB | 5 | 2022-03-06 09:45 | 2022-03-06 15:00 | 5.25 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.68 | 3033 | 3033 | 0 | PJSM WITH PERTINENT PERSONNEL, TEST LINES T/ 3,500 PSI & CEMENT WITH: 50 BBL 8.3 PPG FRESH WATER SPACER, 324 BBLS 11.6 PPG LEAD CEMENT, 87 BBL 14.4 PPG TAIL CEMENT, DISPLACE WITH 280 BBLS OF 9.0 PPG OIL BASE MUD. BUMP PLUG W/750 PSI PRESSURE UP T/1250 PSI (500 PSI OVER) @ 4 BPM. HOLD PRESSURE FOR 5 MINUTES, BLEED BACK 1 BBL. MONITOR FOR 5 MINUTES- FLOATS HELD 50 BBLS OF SPACER AND 180 BBLS OF LEAD CEMENT BACK TO SURFACE. CEMENTED W/ FULL RETURNS.
BUCKY BADGER H02 BB | 5 | 2022-03-06 09:45 | 2022-03-06 09:45 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.68 | 3033 | 3033 |  | MILESTONE_HOLD WELL OPERATIONS (1) ON 3/06/2022 @ 09:45
BUCKY BADGER H02 BB | 5 | 2022-03-06 15:00 | 2022-03-06 16:00 | 1 | R | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.68 | 3033 | 3033 | 0 | PRESSURE TEST 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. TEST GOOD. RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
BUCKY BADGER H02 BB | 6 | 2022-03-11 14:15 | 2022-03-11 15:15 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.72 | 3033 | 3033 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, HELD PJSM W/STREAMFLO, REMOVE WELL CAP, WALK RIG F/ BUCKY BADGER H04 T/ BUCKY BADGER H02, CENTER OVER WELL HEAD AND VERIFY BY MAGNOLIA REP.
BUCKY BADGER H02 BB | 6 | 2022-03-11 14:15 | 2022-03-11 14:15 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.68 | 3033 | 3033 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 03/11/2022 @ 14:15.
BUCKY BADGER H02 BB | 6 | 2022-03-11 15:15 | 2022-03-11 15:45 | 0.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.74 | 3033 | 3033 | 0 | INSTALL BOP ONTO WELLHEAD, SECURE STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALL TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME. MAKE UP FLOW LINE TO MANIFOLD, SKID CATWALK AND SET V-DOOR.
BUCKY BADGER H02 BB | 6 | 2022-03-11 15:45 | 2022-03-11 18:15 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.84 | 3033 | 3033 | 0 | NIPPLE UP BOPE: C/O TOP RAMS F/ 7-5/8" CASING RAMS T/ VBRs. R/U FLOWLINE, TURNBUCKLES, STANDPIPE, GERONIMO, WEIGHT BUCKETS.
BUCKY BADGER H02 BB | 6 | 2022-03-11 18:15 | 2022-03-11 20:00 | 1.75 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.92 | 3033 | 3033 | 0 | INSTALL TEST PLUG, FILL BOP WITH WATER. TEST WELLHEAD CONNECTION, KILL LINE, TOP RAMS T/ 250 PSI LOW AND 5,000 PSI HIGH. INSTALL WEAR BUSHING AND PERFORM ACCUMULATOR DRAW DOWN TEST.
BUCKY BADGER H02 BB | 6 | 2022-03-11 20:00 | 2022-03-11 21:00 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0.96 | 3033 | 3033 | 0 | LUBRICATE RIG. C/O BALES.
BUCKY BADGER H02 BB | 6 | 2022-03-11 21:00 | 2022-03-11 21:30 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 0.98 | 3033 | 3033 | 0 | INSTALL MOUSE HOLE, REMOVE OLD BALES F/ RIG FLOOR, CENTER STACK.
BUCKY BADGER H02 BB | 6 | 2022-03-11 21:30 | 2022-03-11 23:45 | 2.25 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.07 | 3033 | 3033 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT; 8", 7/8L, 5.9 STG @ 2.0° SLICK HWP 0.002, 0.166 REV/GAL, 5.30' BIT TO BEND, 8.31" PAD OD, FLOW RANGE: 400/900 GPM, MAX DIFF: 1390 PSI; 8" NMPDC, 7 3/4" UBHO, (2) 8" NMDC, (1) X/O 4-1/2 XH x 6-5/8 REG, (2) STDS 6 1/2" DC, (1) X/O 4-1/2 IF x 4-1/2 XH, (3) STDS 5" HWDP. TEST MWD- TEST GOOD (BIT TO SVY-66' AND GAMMA-62').
BUCKY BADGER H02 BB | 6 | 2022-03-11 23:45 | 2022-03-12 01:15 | 1.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.14 | 3033 | 3033 | 0 | TIH F/BHA T/2,939', HOLE GIVING PROPER DISPLACEMENT ON TRIP TANKS. PSI TEST BEFORE AGITATOR 544 PSI, AFTER 650 PSI @ 321 GPM.
BUCKY BADGER H02 BB | 6 | 2022-03-12 01:15 | 2022-03-12 01:45 | 0.5 | P | SFHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 1.16 | 3033 | 3033 | 0 | INSTALL ROT HEAD.
BUCKY BADGER H02 BB | 6 | 2022-03-12 01:45 | 2022-03-12 02:30 | 0.75 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.19 | 3033 | 3043 | 13.3 | DRILL SHOE TRACK AND 10' NEW FORMATION F/ 3,033' T/ 3,043', GPM: 420, SPP: 1120/1420 PSI, DIFF: 100/290, RPM: 40, TQ: 2/6K.
BUCKY BADGER H02 BB | 6 | 2022-03-12 02:30 | 2022-03-12 03:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.21 | 3043 | 3043 | 0 | CIRCULATE BOTTOMS UP GPM: 430, SPP: 1225 PSI, RPM: 30.
BUCKY BADGER H02 BB | 6 | 2022-03-12 03:00 | 2022-03-12 03:30 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.23 | 3043 | 3043 | 0 | CIRCULATE THROUGH GAS BUSTER, PERFORM F.I.T. WITH 9.3 PPG MW, 357 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD: 3,018' / TVD: 2,990'.
BUCKY BADGER H02 BB | 6 | 2022-03-12 03:30 | 2022-03-12 05:45 | 2.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.32 | 3043 | 4085 | 463.1 | DRILL INTERMEDIATE- ROT (1042' IN 2.38 HRS @ 438 FPH) WOB: 25/30K, SPM: 94/94/94, GPM: 890, MMRPM: 148, RPM: 80, TRPM: 228, TRQ: 8/13K, SPP: 4460/5000 PSI, DIFF: 500/600 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: 4 PPB PRO V, 4 PPB SUPER CEAL, 2 PPB NEW CARB.
BUCKY BADGER H02 BB | 6 | 2022-03-12 05:45 | 2022-03-12 06:00 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.33 | 4085 | 4100 | 60 | DRILL INTERMEDIATE- SLIDE (15' IN 0.12 HRS @ 129 FPH) WOB: 5/10K, SPM: 94/94/94, GPM: 890, MMRPM: 148, SPP: 4460/4660 PSI, DIFF: 200 PSI. SLIDE DEPTHS: F/3418-T/3433,TF-160R,15',MIN-7 F/0433-T/0440
BUCKY BADGER H02 BB | 7 | 2022-03-12 06:00 | 2022-03-12 09:15 | 3.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.47 | 4100 | 5681 | 486.5 | DRILL INTERMEDIATE- ROT (1,581' IN 3.30 HRS @ 479 FPH) WOB: 25/35K, SPM: 93/94/93, GPM: 900, MMRPM: 149, RPM: 80, TRPM: 229, TRQ: 15K/20K, SPP: 4750/5500 PSI, DIFF: 700/800 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (4 PPB) PRO V, (4 PPB) SUPER CEAL, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 7 | 2022-03-12 09:15 | 2022-03-12 10:15 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.51 | 5681 | 5753 | 72 | DRILL INTERMEDIATE- SLIDE (72' IN 0.95 HRS @ 76 FPH) WOB: 5/15K, SPM: 93/94/93, GPM: 900, MMRPM: 149, SPP: 4750/4900 PSI, DIFF: 100/200 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/4168-T/4183 TF-90R,15',MIN-7 F/614-T/621 F/4825-T/4837 TF-140L,12',MIN-7 ,F/730-T/737 F/5200-T/5207 TF-30R,7',MIN-12 F/822-T/834 RPM-20,2R,1L F/5295-T/5313, TF-30R, 18',MIN-13,F/849-T/ RPM-20,2R,1L F/5575-T/5595 TF-HS,20 ',MIN-18 F/938-T/956 RPM-20,2R,1L
BUCKY BADGER H02 BB | 7 | 2022-03-12 10:15 | 2022-03-12 11:45 | 1.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.57 | 5753 | 6371 | 412 | NOTE: DRILLING WITH REDUCED GPMs, C/O VALVE ON MP#1 SUCTION LINE. DRILL INTERMEDIATE- ROT (618' IN 1.58 HRS @ 391 FPH) WOB: 25/35K, SPM: 0/108/108, GPM: 690, MMRPM: 115, RPM: 80, TRPM: 195, TRQ: 15K/22K, SPP: 3075/3900 PSI, DIFF: 700/800 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (4 PPB) PRO V, (4 PPB) SUPER CEAL, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 7 | 2022-03-12 11:45 | 2022-03-12 12:30 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.6 | 6371 | 6409 | 50.7 | NOTE: DRILLING WITH REDUCED GPMs, C/O VALVE ON MP#1 SUCTION LINE. DRILL INTERMEDIATE- SLIDE (38' IN 0.67 HRS @ 57 FPH) WOB: 5/15K, SPM: 94/94/93, GPM: 690, MMRPM: 115, SPP: 3075/3375 PSI, DIFF: 300/400 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/5950-T/5970 TF-30L,20',MIN-14 F/1047-T/1107 40R-PM,2R,1L F/6325-T/6343 TF-50L,18',MIN-20 F/1202-T/1222 RPM-40,2R 1L
BUCKY BADGER H02 BB | 7 | 2022-03-12 12:30 | 2022-03-12 14:30 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.69 | 6409 | 7063 | 327 | DRILL INTERMEDIATE- ROT (654' IN 1.90 HRS @ 344 FPH) WOB: 25/35K, SPM: 93/93/93, GPM: 900, MMRPM: 149, RPM: 80, TRPM: 229, TRQ: 15K/22K, SPP: 5100/5750 PSI, DIFF: 600/700 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (4 PPB) PRO V, (4 PPB) SUPER CEAL, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 7 | 2022-03-12 14:30 | 2022-03-12 16:15 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.76 | 7063 | 7160 | 55.4 | DRILL INTERMEDIATE- SLIDE (97' IN 1.85 HRS @ 52 FPH) WOB: 5/10K, SPM: 93/93/93, GPM: 900, MMRPM: 149, SPP: 5100/5325 PSI, DIFF: 200/250 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/6420-T/6438 TF-50L,18',MIN-21 F/1237-T/1258 30RPM-3R,1L F/6607-T/6627 TF-60L,20',MIN-21 F/1326-T/1347 30RPM,3R,1L F/6795-T/6815 TF-HS,20',MIN-21 F/1413-T/1434 RPM-30,2R,1L F/6888-T/6908 TF-HS,20 ',MIN-21,F/1446-T/1506 RPM-30,3R,1L F/7076-T/7096 TF-HS,20',MIN-33 /1533-T/1601 RPM-30,2R,1L
BUCKY BADGER H02 BB | 7 | 2022-03-12 16:15 | 2022-03-12 16:45 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.78 | 7160 | 7160 | 0 | LUBRICATE RIG.
BUCKY BADGER H02 BB | 7 | 2022-03-12 16:45 | 2022-03-12 21:00 | 4.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.96 | 7160 | 8338 | 277.2 | DRILL INTERMEDIATE- ROT (1,178' IN 4.25 HRS @ 277 FPH) WOB: 25/35K, SPM: 94/94/93, GPM: 850, MMRPM: 141, RPM: 80, TRPM: 221, TRQ: 15K/22K, SPP: 5100/5750 PSI, DIFF: 600/700 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (4 PPB) PRO V, (4 PPB) SUPER CEAL, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 7 | 2022-03-12 21:00 | 2022-03-13 02:00 | 5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.17 | 8338 | 8596 | 51.6 | DRILL INTERMEDIATE- SLIDE (258' IN 5.0 HRS @ 52 FPH) WOB: 5/15K, SPM: 93/93/93, GPM: 850, MMRPM: 141, SPP: 5175/5225 PSI, DIFF: 50/100 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/7196-T/7221 TF-HS,25',MIN-27 F/1653-T/1720 30 RPM,3R,1L F/7357 T/7378,20'40L,36MIN,F/1800-1836 4R 1L 40RPM F/7544 T/7574,30'45L,91MIN,F1909-2040 4R 1L 40RPM F/7735 T/7750,15'80L,19MIN,F/2112-2131 4R 1L 40RPM F/8015 T/8032,17'170L,17MIN,F/2213-2240 4R 1L 40RPM F/8203 T/8318,15'160L,25MIN,F/2307-2332 4R 1L 40RPM F/8390 T/8407,17'155M,43MIN,F/0000-0043 4R 1L 40RPM F/8578 T/8596,18'140M,32MIN,F/128-200 4R 1L 40RPM
BUCKY BADGER H02 BB | 7 | 2022-03-13 02:00 | 2022-03-13 03:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.21 | 8596 | 8596 | 0 | DAYLIGHT SAVINGS.
BUCKY BADGER H02 BB | 7 | 2022-03-13 03:00 | 2022-03-13 04:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.25 | 8596 | 8769 | 173 | DRILL INTERMEDIATE- ROT (173' IN 1.0 HRS @ 173 FPH) WOB: 25/35K, SPM: 88/88/88, GPM: 850, MMRPM: 141, RPM: 80, TRPM: 221, TRQ: 15K/22K, SPP: 5280/5780 PSI, DIFF: 450/550 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (4 PPB) PRO V, (4 PPB) SUPER CEAL, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 7 | 2022-03-13 04:00 | 2022-03-13 04:15 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.26 | 8769 | 8833 | 256 | NOTE: DRILLING AT REDUCED GPMs, C/O SWAB MP#3. DRILL INTERMEDIATE- ROT (64' IN 0.25 HRS @ 256 FPH) WOB: 25/35K, SPM: 108/108/0, GPM: 690, MMRPM: 115, RPM: 80, TRPM: 195, TRQ: 15K/22K, SPP: 3800/4280 PSI, DIFF: 400/500 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (4 PPB) PRO V, (4 PPB) SUPER CEAL, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 7 | 2022-03-13 04:15 | 2022-03-13 04:45 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.28 | 8833 | 8849 | 32 | NOTE: DRILLING AT REDUCED GPMs, C/O SWAB MP#3. DRILL INTERMEDIATE- SLIDE (16' IN 0.53 HRS @ 30 FPH) WOB: 5/15K, SPM: 108/108/0, GPM: 690, MMRPM: 115, SPP: 3800/4000 PSI, DIFF: 150/300 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/8769 T/ 8785,16'190M,32MIN,F/400-432
BUCKY BADGER H02 BB | 7 | 2022-03-13 04:45 | 2022-03-13 05:30 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.31 | 8849 | 8875 | 34.7 | DRILL INTERMEDIATE- SLIDE (26' IN 0.75 HRS @ 35 FPH) WOB: 2/10K, SPM: 92/93/93, GPM: 825, MMRPM: 137, SPP: 4950/5050 PSI, DIFF: 50/100 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/8849 T/ 8875,26'140M,32MIN,F/0445-0530
BUCKY BADGER H02 BB | 7 | 2022-03-13 04:45 | 2022-03-13 04:45 | 0 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.28 | 8849 | 8849 |  | START BUILDING INT CURVE ON 3/13/2022 @ 04:45 (8,849' MD / 8,699.84' TVD)
BUCKY BADGER H02 BB | 7 | 2022-03-13 05:30 | 2022-03-13 06:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.33 | 8875 | 8875 | 0 | LUBRICATE RIG.
BUCKY BADGER H02 BB | 8 | 2022-03-13 06:00 | 2022-03-13 10:45 | 4.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.53 | 8875 | 9027 | 32 | DRILL INTERMEDIATE- SLIDE (152’ IN 4.7 HRS @ 32 FPH) WOB: 5/15K, SPM: 91/91/92, GPM: 880, MMRPM: 146, SPP: 5600/5800 PSI, DIFF: 100/200 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/8875 T/ 8996, 121' 140M, 216MIN, F/0600-0936 F/9100 T/ 9118, 18' HS, 36MIN, F/1024-1100 F/9118 T/ 9131, 13' HS, 24MIN, F/1100-1124 NOTE: REDUCED GPMs F/ 9,118' T/ 9,131' MP#3 DOWN, CAP GASKET DISCHARGE.
BUCKY BADGER H02 BB | 8 | 2022-03-13 10:45 | 2022-03-13 11:45 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.57 | 9027 | 9152 | 125 | DRILL INTERMEDIATE- ROT (125’ IN 1.05 HRS @ 119 FPH) WOB: 25/30K, SPM: 88/88/88, GPM: 846, MMRPM: 140, RPM: 30, TRPM: 170, TRQ: 14/20K, SPP: 5250/5750 PSI, DIFF: 400/500 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (8 PPB) SWEEP AID, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 8 | 2022-03-13 11:45 | 2022-03-13 12:00 | 0.25 | P | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.58 | 9152 | 9152 | 0 | RIG SERVICE- REPLACE O-RING GASKET ON STAND PIPE VIBRATOR HOSE TO SUB.
BUCKY BADGER H02 BB | 8 | 2022-03-13 12:00 | 2022-03-13 14:45 | 2.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.7 | 9152 | 9252 | 36.4 | DRILL INTERMEDIATE- SLIDE (100’ IN 2.85 HRS @ 35 FPH) WOB: 10/15K, SPM: 91/91/92, GPM: 880, MMRPM: 146, SPP: 5600/5800 PSI, DIFF: 100/200 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° SLIDE DEPTHS: F/9152 T/ 9224, 72' HS, 95MIN, F/1200-1335 F/9234 T/ 9262, 28' HS, 67MIN, F/1344-1458
BUCKY BADGER H02 BB | 8 | 2022-03-13 14:45 | 2022-03-13 16:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.75 | 9252 | 9336 | 67.2 | DRILL INTERMEDIATE- ROT (84’ IN 1.15 HRS @ 73 FPH) WOB: 25/30K, SPM: 88/88/88, GPM: 846, MMRPM: 140, RPM: 30, TRPM: 170, TRQ: 14/20K, SPP: 5250/5750 PSI, DIFF: 400/500 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: (8 PPB) SWEEP AID, (2 PPB) NEW CARB
BUCKY BADGER H02 BB | 8 | 2022-03-13 16:00 | 2022-03-13 16:00 | 0 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.75 | 9336 | 9336 |  | TD INTERMEDIATE ON 3/13/2022 @ 16:00 (9,336’ MD/ 9,170.29’ TVD)
BUCKY BADGER H02 BB | 8 | 2022-03-13 16:00 | 2022-03-13 17:15 | 1.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.8 | 9336 | 9336 | 0 | PERFORM CLEAN UP CYCLE WITH (2) 30 BBL, 10 PPB LCM TANDEM SWEEPS. SWEEP CONTENT: 8 PPB SWEEP AID, 2 PPB NEW CARB.
BUCKY BADGER H02 BB | 8 | 2022-03-13 17:15 | 2022-03-13 17:30 | 0.25 | P | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 2.81 | 9336 | 9336 | 0 | FLOW CHECK- NO FLOW. PUMP 30 BBL SLUG, +2.5 PPG OVER MW (12.5 PPG).
BUCKY BADGER H02 BB | 8 | 2022-03-13 17:30 | 2022-03-13 18:30 | 1 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.85 | 9336 | 9336 | 0 | POOH F/9,336' - T/8,316' LAYING DOWN DRILL PIPE, NO EXCESS DRAG. HOLE TAKING PROPER FILL OFF OF TRIP TANKS.
BUCKY BADGER H02 BB | 8 | 2022-03-13 18:30 | 2022-03-13 19:15 | 0.75 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.89 | 9336 | 9336 | 0 | LUBRICATE RIG.
BUCKY BADGER H02 BB | 8 | 2022-03-13 19:15 | 2022-03-13 23:45 | 4.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.07 | 9336 | 9336 | 0 | POOH F/8,316' - T/2,850' LAYING DOWN DRILL PIPE, NO EXCESS DRAG. HOLE TAKING PROPER FILL OFF OF TRIP TANKS. NOTE: START C/O LINERS ON MUD PUMPS TO 4-3/4"
BUCKY BADGER H02 BB | 8 | 2022-03-13 23:45 | 2022-03-14 00:15 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 3.09 | 9336 | 9336 | 0 | FLOW CHECK- NO FLOW, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
BUCKY BADGER H02 BB | 8 | 2022-03-14 00:15 | 2022-03-14 02:45 | 2.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.2 | 9336 | 9336 | 0 | POOH F/2,850' - T/BHA LAYING DOWN 5" DRILL PIPE, NO EXCESS DRAG. HOLE TAKING PROPER FILL OFF OF TRIP TANKS.
BUCKY BADGER H02 BB | 8 | 2022-03-14 02:45 | 2022-03-14 04:00 | 1.25 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.25 | 9336 | 9336 | 0 | REPAIR BUSTED HYDRAULIC LINE ON CATWALK.
BUCKY BADGER H02 BB | 8 | 2022-03-14 04:00 | 2022-03-14 06:00 | 2 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.33 | 9336 | 9336 | 0 | START LAYING DOWN COMPLETE BHA: L/D (3) STANDS OF HWDP, XO, (2) STANDS OF 6.5" DRILL COLLARS, XO, TOP MONEL, REMOVE MWD TOOL L/D SAME, DRAIN MUD MOTOR, BREAK BIT, L/D SAME.
BUCKY BADGER H02 BB | 9 | 2022-03-14 06:00 | 2022-03-14 07:15 | 1.25 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.39 | 9336 | 9336 | 0 | L/D TOP MONEL, REMOVE MWD, DRAIN BIT, REMOVE, L/D MUD MOTOR, PONY COLLAR AND MONEL. BIT GRADE: 0-1-CT-G-X-0-NO-TD MOTOR DRAINED ON ITS OWN, 1/4" SQUAT
BUCKY BADGER H02 BB | 9 | 2022-03-14 07:15 | 2022-03-14 07:30 | 0.25 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.4 | 9336 | 9336 | 0 | REMOVE WEAR BUSHING.
BUCKY BADGER H02 BB | 9 | 2022-03-14 07:30 | 2022-03-14 09:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 3.46 | 9336 | 9336 | 0 | REMOVE UPPER VBR'S AND INSTALL 7-5/8" CASING RAMS.
BUCKY BADGER H02 BB | 9 | 2022-03-14 09:00 | 2022-03-14 09:30 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 3.48 | 9336 | 9336 | 0 | INSTALL TEST PLUG AND TEST RAMS T/1200 PSI.
BUCKY BADGER H02 BB | 9 | 2022-03-14 09:30 | 2022-03-14 10:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.5 | 9336 | 9336 | 0 | PERFORM RIG SERVICE.
BUCKY BADGER H02 BB | 9 | 2022-03-14 10:00 | 2022-03-14 11:15 | 1.25 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.55 | 9336 | 9336 | 0 | RIG UP BUTCH'S CASING CREW AND EQUIPMENT.
BUCKY BADGER H02 BB | 9 | 2022-03-14 11:15 | 2022-03-14 20:00 | 8.75 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.92 | 9336 | 9336 | 0 | RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: (1) INNOVEX FLOAT SHOE, (2) JTS OF 7 5/8" 29.7# P-110 ICY BTC CSG, (1) INNOVEX FLOAT COLLAR. (1) JT OF 7 5/8" 29.7# P-110 ICY SMLS BTC CSG, TEST FLOATS, THEN RUN (212) JTS OF 7 5/8" 29.7# P-110 ICY BTC CSG T/9,321.6'. FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALL 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FLOATING), AND INSTALL 37 LATCH ON BOW SPRING CENTRALIZERS @ 9,,014.8' AND EVERY 4TH JT UP TO 2,802.5'. NOTE: TAKING RETURNS INTO THE TRIP TANKS WITH PROPER DISPLACEMENT, FILLING PIPE ON THE FLY. SHOE DEPTH @ 9,321.6' MD / 9,156.91' TVD TOP OF FLOAT COLLAR @ 9,230.5' P/U LANDING JT, LAND HANGER W/ 200K W/OUT BLOCKS.
BUCKY BADGER H02 BB | 9 | 2022-03-14 20:00 | 2022-03-14 21:15 | 1.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.97 | 9336 | 9336 | 0 | CIRC B/U THROUGH CRT, STAGING PUMP RATE UP TO 8 BBL/MIN. R/D CSG TOOLS WHILE CIRCULATING. GPM-336, PP- 205 PSI.
BUCKY BADGER H02 BB | 9 | 2022-03-14 21:15 | 2022-03-14 22:30 | 1.25 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 4.02 | 9336 | 9336 | 0 | RIG DOWN CRT AND INSTALL NINE ENERGY CEMENT HEAD AND CEMENTING LINES.
BUCKY BADGER H02 BB | 9 | 2022-03-14 22:30 | 2022-03-15 01:45 | 3.25 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 4.16 | 9336 | 9336 | 0 | TEST LINES T/5,000 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 11.0 PPG SPACER. 269 BBL 11.8 PPG 750 SK 2.01 YIELD 50/50 POZ-PM-CLASS H-MM LEAD CEMENT, 79 BBL 13.5 PPG 325 SK 1.37 YIELD BLEND 27-PM POZ TAIL CEMENT. FLUSH THRU ALL LINES, WITNESS PLUG DROP, DISPLACE WITH 424 BBL + 2 BBL (1/2 SHOE TRACK) OF 9.0 PPG OBM DISPLACEMENT. FINAL LIFT PRESSURE 1,650 PSI AT 4 BPM, DID NOT BUMP PLUG, HOLD FOR 5 MIN, BLEED OFF PSI (3 BBLS)-FLOATS HELD. FINISH CEMENTING @ 01:29 HRS, W/ FULL RETURNS WHILE PUMPING CEMENT. NOTE: 50 BBL OF SPACER AND 30 BBL CEMENT TO SURFACE.
BUCKY BADGER H02 BB | 9 | 2022-03-15 01:45 | 2022-03-15 02:00 | 0.25 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.17 | 9336 | 9336 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON. FLUSH THROUGH BOP AND FLOW LINE WITH SUGAR WATER.
BUCKY BADGER H02 BB | 9 | 2022-03-15 02:00 | 2022-03-15 03:15 | 1.25 | P | INTHLCSG | WLHD | RDWLHD | RIG DOWN WELLHEAD | 4.22 | 9336 | 9336 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
BUCKY BADGER H02 BB | 9 | 2022-03-15 03:15 | 2022-03-15 04:45 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.28 | 9336 | 9336 | 0 | CHANGE OUT TOP RAMS F/ 7-5/8" CASING RAMS T/ VBRs. NOTE: OFFLINE- TEST CHOKE MANIFOLD 250 LOW / 10,000 HIGH. ATTEMPT TO TEST STAND PIPE BACK TO THE PUMPS, 4" ON FLOOR LEAKING. REPLACE 4" WHILE TESTING BOP.
BUCKY BADGER H02 BB | 9 | 2022-03-15 04:45 | 2022-03-15 05:15 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.3 | 9336 | 9336 | 0 | OFFLINE RIG SERVICE, ACCUMULATOR DRAW DOWN TEST.
BUCKY BADGER H02 BB | 9 | 2022-03-15 05:15 | 2022-03-15 06:00 | 0.75 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.33 | 9336 | 9336 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/ WATER, REMOVE INTERNAL COMPONENT TO KILL LINE CHECK VALVE, TEST UPPER PIPE RAMS WITH 5 1/2" DP 250 PSI LOW / 10,000 PSI HIGH.
BUCKY BADGER H02 BB | 10 | 2022-03-15 06:00 | 2022-03-15 07:30 | 1.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 4.4 | 9336 | 9336 | 0 | WHILE ATTEMPTING TO TEST UPPER PIPE RAMS, PRESSURE BEGAN TO BLEED OFF FROM DOOR SEALS. OPEN RAM DOORS, INSTALL NEW BONNET SEALS, CLOSE DOORS, AND TIGHTEN.
BUCKY BADGER H02 BB | 10 | 2022-03-15 07:30 | 2022-03-15 13:00 | 5.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.63 | 9336 | 9336 | 0 | TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW /10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 6500 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ROTATING HEAD AND ORBIT VALVE TO 1500 PSI. REMOVE TEST PLUG, INSTALL WEAR BUSHING, CLOSE CASING VALVE, RIG DOWN TESTERS.
BUCKY BADGER H02 BB | 10 | 2022-03-15 13:00 | 2022-03-15 14:00 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.67 | 9336 | 9336 | 0 | RIG SERVICE.
BUCKY BADGER H02 BB | 10 | 2022-03-15 14:00 | 2022-03-15 15:45 | 1.75 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 4.74 | 9336 | 9336 | 0 | CHANGE SAVER SUB TO CET-43 AND TOP DRIVE COMPONENTS TO 4.5" DRILL PIPE.
BUCKY BADGER H02 BB | 10 | 2022-03-15 15:45 | 2022-03-15 16:30 | 0.75 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 4.77 | 9336 | 9336 | 0 | SLIP AND CUT DRILL LINE.
BUCKY BADGER H02 BB | 10 | 2022-03-15 16:30 | 2022-03-15 19:30 | 3 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.9 | 9336 | 9336 | 0 | PICK UP 6-3/4" SECURITY GTD64M S/N: 13645347 JETS: 6X18 TFA: 1.49; 5-1/2" MOTOR 6/7L 8.8 STG @ 2.12° SLICK HS88-.001, 0.68 REV/GAL, 4.03' BIT TO BEND, 5.62" KICK PAD OD, FLOW RANGE: 150/400 GPM, MAX DIFF: 2,240 PSI, STALL TQ: 8,014 FT/LBS; BTI VALVE, 5 1/4" NMPDC, 5 1/4" UBHO, (2) 5" NMDC, 5" TOMAX, X/O, (2) STANDS 4.5" DP, REAMER, (26) STANDS 4.5" DP, AGITATOR. NOTE: BIT TO SVY: 68', BIT TO GAMMA: 55', SURFACE TEST GOOD.
BUCKY BADGER H02 BB | 10 | 2022-03-15 19:30 | 2022-03-16 02:30 | 7 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.19 | 9336 | 9336 | 0 | P/UP 4.5" F/ BHA T/ 7,400' WITH PROPER DISPLACEMENTS TAKEN ON THE TRIP TANKS, FILL PIPE @ AGITATOR, THEN EVERY 30 STANDS. NOTE: P/U AGITATOR @ 2,750'; 1,170 PSI BEFORE, 1,470 PSI AFTER, GPM: 321.
BUCKY BADGER H02 BB | 10 | 2022-03-16 02:30 | 2022-03-16 06:00 | 3.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 5.33 | 9336 | 9336 | 0 | P/U DRILL PIPE AT REDUCED RATE TORQUING W/RIG TONGS, DUE TO ST-80 NOT TORQUING PIPE CORRECTLY
BUCKY BADGER H02 BB | 11 | 2022-03-16 06:00 | 2022-03-16 08:45 | 2.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.45 | 9336 | 9336 | 0 | TRIP IN HOLE PICKING UP 4.5” DRILL PIPE F/ 7,400’ T/ 9,000’ (AVERAGE 582 FPH) TORQUE UP 4.5” DRILL PIPE CONNECTION W/ RIG TONGS DUE T/ ST-80’S NOT TORQUING DRILL PIPE PROPERLY.
BUCKY BADGER H02 BB | 11 | 2022-03-16 08:45 | 2022-03-16 09:15 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 5.47 | 9336 | 9336 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD ASSEMBLY.
BUCKY BADGER H02 BB | 11 | 2022-03-16 09:15 | 2022-03-16 10:00 | 0.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.5 | 9336 | 9336 | 0 | FILL UP DRILL PIPE AND CIRCULATE THRU GAS BUSTER, PERFORM BOP DRILL.
BUCKY BADGER H02 BB | 11 | 2022-03-16 10:00 | 2022-03-16 10:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.52 | 9336 | 9336 | 0 | TEST 7.625" INTERMEDIATE CASING T/ 3500 PSI F/ 30 MINUTES, GOOD TEST. NOTE: RECORDED CASING PRESSURE FROM PASON CASING PRESSURE.
BUCKY BADGER H02 BB | 11 | 2022-03-16 10:30 | 2022-03-16 11:45 | 1.25 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.57 | 9336 | 9346 | 8 | TRIP IN HOLE PICKING UP 4.5” DRILL PIPE F/ 9,000’ T/ 9,078’, SET DOWN 15K @ 9,078’, WASH AND REAM F/ 9,078’ T/ FLOAT COLLAR @ 9,230’, DRILL OUT SHOE TRACK, CLEAN OUT RAT HOLE T/ 9,336’, DRILL 10’ FORMATION T/ 9,346’,GPM=173, SPP=1100/1350, DIFF=200/400, WOB=4/9K, RPM=30, MMRPM=117, TRPM=147, TOR=4/8K.
BUCKY BADGER H02 BB | 11 | 2022-03-16 11:45 | 2022-03-16 12:30 | 0.75 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 5.6 | 9346 | 9346 | 0 | CIRCULATE BOTTOMS UP, GPM=300, SPP=2600, RPM=30, TQ=5/7K.
BUCKY BADGER H02 BB | 11 | 2022-03-16 12:30 | 2022-03-16 13:00 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.63 | 9346 | 9346 | 0 | PERFORM F.I.T. WITH 9.3 PPG MUD, (CALCULATED) 1,761 PSI SURFACE PRESSURE FOR 13.0 PPG EMW, SHOE MD=9,321' I TVD=9,156'. PRESSURE DECLINED @ 1,572 PSI, EMW=12.6 PPG, PUMP A TOTAL OF 5.2 BBLS @ .38 BPM. NOTE: RECORDED CASING PRESSURE FROM PASON CASING PRESSURE.
BUCKY BADGER H02 BB | 11 | 2022-03-16 13:00 | 2022-03-16 20:30 | 7.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.94 | 9346 | 9787 | 58.8 | DRILL CURVE- SLIDE (451’ IN 7.5 HRS @ 60.13 FPH) WOB: 10/15K, SPM: 67/67/0, GPM: 352, MMRPM: 240, SPP: 3400/3500 PSI, DIFF: 300/400 PSI. TARGET LINE: 9,650' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT RECEIVE TARGET CHANGE VIA EMAIL @ 19:06 HRS TARGET LINE: 9,656' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/9,346' T/9,787', 441' HS, 13:00-20:30
BUCKY BADGER H02 BB | 11 | 2022-03-16 13:00 | 2022-03-16 13:00 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.63 | 9346 | 9346 |  | MILESTONE_START CURVE ON 03/16/2022 @ 13:00 HRS
BUCKY BADGER H02 BB | 11 | 2022-03-16 20:30 | 2022-03-16 22:45 | 2.25 | P | PRDHLCV | LCIRC | LCIRC | LOST CIRCULATION | 6.03 | 9787 | 9787 | 0 | LOSING PARTIAL RETURNS @ 130 BBLS/HR @ 9,787', REDUCED GPM AND ATTEMPT TO ESTABLISH FULL RETURNS WITH NO SUCCESS, PUMPED 2- 25 PPB LCM SWEEPS, PREP MUD TANKS AND MUD PUMPS FOR DRILLING WITH WATER UNDER MUD CAP
BUCKY BADGER H02 BB | 11 | 2022-03-16 22:45 | 2022-03-17 06:00 | 7.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.33 | 9787 | 9984 | 27.2 | DRILL CURVE ON MUD CAP- SLIDE (197’ IN 7.25 HRS @ 27.17 FPH) WOB: 10/15K, SPM: 71/71/0, GPM: 375, MMRPM: 255, SPP: 3450/3550 PSI, DIFF: 300/400 PSI. TARGET LINE: 9,656' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/9,787' T/9,984', 197' HS, 22:45-06:00
BUCKY BADGER H02 BB | 12 | 2022-03-17 06:00 | 2022-03-17 09:00 | 3 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.46 | 9984 | 10093 | 36.3 | DRILL CURVE ON MUD CAP- SLIDE (109’ IN 2.98 HRS @ 36.57 FPH) WOB: 25/30K, SPM: 71/71/0, GPM: 375, MMRPM: 255, SPP: 2900/3000 PSI, DIFF: 300/400 PSI. TARGET LINE: 9,656' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT RECEIVED TARGET CHANGE VIA EMAIL @ 07:14 HRS TARGET LINE: 9,669' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/9,984' T/10,028', 44' HS, 06:00-06:45 TQ= R/6,L/4, RPM=60 F/10,098' T/10,123', 25' HS, 07:35-08:10 TQ= R/6,L/4, RPM=60 F/10,193' T/10,211', 18' HS, 08:47-09:50 TQ= R/6,L/4, RPM=60 F/10,231' T/10,253', 22' HS, 10:11-10:47 TQ= R/6,L/4, RPM=60
BUCKY BADGER H02 BB | 12 | 2022-03-17 09:00 | 2022-03-17 11:15 | 2.25 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.55 | 10093 | 10312 | 97.3 | BUILD CURVE ON MUD CAP-ROT (219' IN 2.27 HRS @ 96.47 FPH) WOB:15/20K, SPM: 71/71/0, GPM: 375, RPM: 30, MRPM: 255, TMRPM: 285, TRQ: 12/14K, SPP: 3300/3400 PSI, DIFF: 600/700 PSI. DRILLING ON MUD CAP WITH 100% FRESH WATER. CASING PSI WHILE DRILLING-0 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5 BBL SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP
BUCKY BADGER H02 BB | 12 | 2022-03-17 11:15 | 2022-03-17 11:15 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.55 | 10312 | 10312 |  | MILESTONE_START HORIZONATAL LATERAL SECTION ON 03/17/2022 @ 11:15.
BUCKY BADGER H02 BB | 12 | 2022-03-17 11:15 | 2022-03-17 11:15 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.55 | 10312 | 10312 |  | MILESTONE_LAND/END CURVE SECTION ON 03/17/2022 @ 11:15. MD: 10,312' / TVD: 9,661'
BUCKY BADGER H02 BB | 12 | 2022-03-17 11:15 | 2022-03-17 15:15 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.72 | 10312 | 11283 | 242.8 | DRILL LATERAL ON MUD CAP- ROT (971' IN 4.10 HRS @ 236.82 FPH), WOB:15/20K, SPM: 71/71/0, GPM: 375, RPM: 70, MRPM: 255, TMRPM: 325, TRQ: 13/15K, SPP: 3550/3650 PSI, DIFF: 800/900 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-64 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 12 | 2022-03-17 15:15 | 2022-03-17 17:00 | 1.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.79 | 11283 | 11360 | 44 | DRILL LATERAL ON MUD CAP- SLIDE (77’ IN 1.65 HRS @ 46.66 FPH) WOB: 25/30K, SPM: 71/71/0, GPM: 375, MMRPM: 255, SPP: 3050/3150 PSI, DIFF: 300/400 PSI. TARGET LINE: 9,669' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT RECEIVED TARGET CHANGE VIA EMAIL @ 16:01 HRS TARGET LINE: 9,669' TVD @ 0' VS @ INC: 86.75° 0' ABOVE/10' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/10,415' T/10,427', 12' 60L, 11:52-12:06 TQ= R/6,L/4, RPM=60 F/10,602' T/10,617', 15' 20L, 15:55-13:15 TQ= R/6,L/4, RPM=60 F/11,074' T/11,099', 25' 90L, 15:06-15:43 TQ= R/6,L/4, RPM=60 F/11,173' T/11,198', 25' 90L, 16:06-16:34 TQ= R/6,L/4, RPM=60
BUCKY BADGER H02 BB | 12 | 2022-03-17 17:00 | 2022-03-17 18:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.83 | 11360 | 11360 | 0 | SERVICE RIG
BUCKY BADGER H02 BB | 12 | 2022-03-17 18:00 | 2022-03-18 00:45 | 6.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.11 | 11360 | 12608 | 184.9 | DRILL LATERAL ON MUD CAP- ROT (1,248' IN 6.68 HRS @ 186.82 FPH), WOB:15/20K, SPM: 72/72/0, GPM: 380, RPM: 70, MRPM: 258, TMRPM: 328, TRQ: 14/16K, SPP: 3200/3300 PSI, DIFF: 800/900 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-64 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 12 | 2022-03-18 00:45 | 2022-03-18 06:00 | 5.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.33 | 12608 | 12776 | 32 | DRILL LATERAL ON MUD CAP- SLIDE (168’ IN 5.32 HRS @ 31.57 FPH) WOB: 25/30K, SPM: 72/72/0, GPM: 380, MMRPM: 258, SPP: 3050/3150 PSI, DIFF: 300/400 PSI. TARGET LINE: 9,669' TVD @ 0' VS @ INC: 86.75° 0' ABOVE/10' BELOW, 50’ LEFT / 50' RIGHT TARGER CHANGE RECEIVED VIA EMAIL @ 04:16 HRS TARGET LINE: 9,675' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/11,360' T/11,385', 25' 90L, 18:00-18:45 TQ= R/5,L/3, RPM=50 F/11,455' T/11,480', 25' 90L, 19:05-19:45 TQ= R/5,L/3, RPM=50 F/11,735' T/11,760', 25' 100L, 20:54-21:38 TQ= R/5,L/3.5, RPM=50 F/11,830' T/11,855', 25' 100L, 22:04-22:35 TQ= R/6,L/4, RPM=50 F/12,015' T/12,035', 20' 150L, 23:20-23:55 TQ= R/5,L/3, RPM=50 F/12,115' T/12,135', 20' 90L, 00:20-00:52 TQ= R/6,L/5, RPM=50 F/12,307' T/12,325', 18' 115R, 01:45-02:52 TQ= R/6,L/5, RPM=50 F/12,402' T/12,412', 10' 180, 03:15-03:40 TQ= R/6,L/5, RPM=50
BUCKY BADGER H02 BB | 13 | 2022-03-18 06:00 | 2022-03-18 12:45 | 6.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.61 | 12776 | 13897 | 166.1 | DRILL LATERAL ON MUD CAP- ROT (1,121' IN 6.67 HRS @ 168.06 FPH), WOB:30/35K, SPM: 72/72/0, GPM: 380, RPM: 70, MRPM: 258, TMRPM: 328, TRQ: 20/21K, SPP: 3400/3500 PSI, DIFF: 600/700 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-60 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 13 | 2022-03-18 12:45 | 2022-03-18 17:00 | 4.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.79 | 13897 | 13987 | 21.2 | DRILL LATERAL ON MUD CAP- SLIDE (90’ IN 4.33 HRS @ 20.78 FPH) WOB: 18/20K, SPM: 72/72/0, GPM: 380, MMRPM: 258, SPP: 2900/3000 PSI, DIFF: 150/250 PSI. TARGET LINE: 9,675' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/5' BELOW, 50’ LEFT / 50' RIGHT TARGER CHANGE RECEIVED VIA EMAIL @ 10:19 HRS TARGET LINE: 9,675' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/ 5' BELOW, 50’ LEFT / 0' RIGHT SLIDE DEPTHS: F/13,056' T/13,071', 15' 110L, 08:00-08:57 TQ= R/13,L/11, RPM=80 F/13,150' T/13,160', 10' 90L, 09:26-10:02 TQ= R/13,L/11, RPM=80 F/13,338' T/13,358', 20' 90L, 10:55-11:48 TQ= R/13,L/11, RPM=80 F/13,433' T/13,448', 15' 90L, 12:15-13:01 TQ= R/13,L/11, RPM=80 F/13,622' T/13,637', 15' 90R, 13:54-14:27 TQ= R/13,L/11, RPM=80 F/13,903' T/13,918', 15' 90L, 15:44-16:19 TQ= R/13,L/11, RPM=80
BUCKY BADGER H02 BB | 13 | 2022-03-18 17:00 | 2022-03-18 18:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.83 | 13987 | 13987 | 0 | SERVICE RIG
BUCKY BADGER H02 BB | 13 | 2022-03-18 18:00 | 2022-03-18 19:45 | 1.75 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 7.91 | 13987 | 13987 | 0 | ATTEMPT TO BREAK OUT FOR CONNECTION, TOP DRIVE WOULD NOT BREAK CONNECTION W/50K BREAKOUT TQ. DECISION WAS MADE TO CIRCULATE @ 60 SPM WHILE REMOVING FEDDER RING ON SAVER SUB AND RAISE GRABBER BOX TO BREAK OUT W/RIG TONGS. AFTER BREAKING OUT W/RIG TONGS, GRABBER BOX WAS SET BACK IN PLACE AND FEDDER RING WAS RE-TORQUED
BUCKY BADGER H02 BB | 13 | 2022-03-18 19:45 | 2022-03-19 01:45 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.16 | 13987 | 15029 | 173.7 | DRILL LATERAL ON MUD CAP- ROT (1,042' IN 5.90 HRS @ 176.61 FPH), WOB:30/35K, SPM: 72/72/0, GPM: 380, RPM: 70, MRPM: 258, TMRPM: 328, TRQ: 20/21K, SPP: 3400/3500 PSI, DIFF: 600/700 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-60 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 13 | 2022-03-19 01:45 | 2022-03-19 06:00 | 4.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.33 | 15029 | 15082 | 12.5 | DRILL LATERAL ON MUD CAP- SLIDE (53’ IN 4.35 HRS @ 12.18 FPH) WOB: 18/20K, SPM: 72/72/0, GPM: 380, MMRPM: 258, SPP: 2900/3000 PSI, DIFF: 150/250 PSI. TARGET LINE: 9,675' TVD @ 0' VS @ INC: 86.75° 5' ABOVE/ 5' BELOW, 50’ LEFT / 0' RIGHT TARGER CHANGE RECEIVED VIA EMAIL @ 22:00 HRS TARGET LINE: 9,676' TVD @ 0' VS @ INC: 86.8° 5' ABOVE/ 5' BELOW, 50’ LEFT / 0' RIGHT TARGER CHANGE RECEIVED VIA EMAIL @ 04:00 HRS TARGET LINE: 9,676' TVD @ 0' VS @ INC: 86.8° 5' ABOVE/ 5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/14,279' T/14,294', 15' 80L, 21:38-23:20 TQ= R/13,L/11, RPM=80 F/14,471' T/14,488', 17' 130L, 00:24-01:57 TQ= R/14,L/11, RPM=80 F/14,569' T/14,580', 11' 180, 02:33-02:52 TQ= R/14,L/12, RPM=65 F/14,937' T/14,947', 10' 90R, 04:28-05:15 TQ= R/4, L/12, RPM=65
BUCKY BADGER H02 BB | 14 | 2022-03-19 06:00 | 2022-03-19 07:30 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.4 | 15082 | 15389 | 204.7 | DRILL LATERAL ON MUD CAP- ROT (307' IN 1.55 HRS @ 198.06 FPH), WOB:30/35K, SPM: 67/67/0, GPM: 350, RPM: 70, MRPM: 238, TMRPM: 308, TRQ: 20/21K, SPP: 3000/3100 PSI, DIFF: 600/700 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-0 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 14 | 2022-03-19 07:30 | 2022-03-19 09:30 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.48 | 15389 | 15409 | 10 | DRILL LATERAL ON MUD CAP- SLIDE (20’ IN 1.95 HRS @ 10.25 FPH) WOB: 18/20K, SPM: 67/67/0, GPM: 350, MMRPM: 238, SPP: 2700/2800 PSI, DIFF: 100/200 PSI. TARGET LINE: 9,676' TVD @ 0' VS @ INC: 86.8° 5' ABOVE/ 5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/15,126' T/15,141', 15' 90L, 06:12-06:49 TQ= R/17,L/15, RPM=80 F/15,404' T/15,409', 5' 120R, 08:10-09:30 TQ= R/17,L/15, RPM=80
BUCKY BADGER H02 BB | 14 | 2022-03-19 09:30 | 2022-03-19 10:00 | 0.5 | U | PRDHLLT | LOG | MWD | MWD | 8.5 | 15409 | 15409 | 0 | MWD TOOL NOT PULSING. RECYCLE PUMPS AND TROUBLESHOOT MWD TOOL.
BUCKY BADGER H02 BB | 14 | 2022-03-19 10:00 | 2022-03-19 10:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.52 | 15409 | 15415 | 12 | DRILL LATERAL ON MUD CAP- SLIDE (6’ IN .5 HRS @ 12 FPH) WOB: 18/20K, SPM: 67/67/0, GPM: 350, MMRPM: 238, SPP: 2700/2800 PSI, DIFF: 100/200 PSI. TARGET LINE: 9,676' TVD @ 0' VS @ INC: 86.8° 5' ABOVE/ 5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/15,409' T/15,415', 5' 120R, 10:00-10:30 TQ= R/17,L/15, RPM=80
BUCKY BADGER H02 BB | 14 | 2022-03-19 10:30 | 2022-03-19 11:00 | 0.5 | U | PRDHLLT | LOG | MWD | MWD | 8.54 | 15415 | 15415 | 0 | MWD TOOL NOT PULSING, DOWNLINK MWD TOOL AND RECYCLE PUMPS
BUCKY BADGER H02 BB | 14 | 2022-03-19 11:00 | 2022-03-19 11:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.56 | 15415 | 15486 | 142 | DRILL LATERAL ON MUD CAP- ROT (71' IN .5 HRS @ 142 FPH), WOB:30/35K, SPM: 67/67/0, GPM: 350, RPM: 70, MRPM: 238, TMRPM: 308, TRQ: 20/21K, SPP: 3000/3100 PSI, DIFF: 600/700 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-0 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 14 | 2022-03-19 11:30 | 2022-03-19 14:15 | 2.75 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.68 | 15486 | 15486 | 0 | PUMP 20 BBL SWEEP AND BACK REAM STAND PRIOR T/ CONNECTION, TORQUE W/ BACK REAMING STAND 18/27K STALLING OUT TOP DRIVE, DECISSION MADE T/ BACK REAM OUT OF HOLE DUE T/ HIGH TORQUE T/ CHANGE BHA , BACK REAM OUT OF HOLE F/ 15,486’ T/ 14,922'.
BUCKY BADGER H02 BB | 14 | 2022-03-19 14:15 | 2022-03-19 17:30 | 3.25 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 8.81 | 15486 | 15486 | 0 | TONG DIE COME OUT OF GRABBER BLOCKS ON TOP DRIVE, TONG DIE FELL FROM DERRICK BOARD T/ RIG FLOOR, WEIGHT OF TONG DIE = 6.4 OUNCES, NO INJURY OR PROPERTY DAMAGE F/ INCIDENT, REMOVE GRABBER BLOCKS F/ TOP DRIVE AND IDENTIFIED RETAINER PLATES WAS NOT IN PROPER CONDITION T/ RETAIN DIES IN GRABBER BLOCKS, CIRCULATE AND WORK PIPE W/ WAITING ON RETAINER PLATES F/ GRABBER BLOCKS, INSTALL RETAINER PLATES ON GRABBER BLOCKS AND INSTALL GRABBER BLOCKS IN GRABBERS F/ TOP DRIVE. NOTE: NOTIFIED MAGNOLIA DRILLING ENGINEEER AND HSE OF INCIDENT THAT OCCURRED.
BUCKY BADGER H02 BB | 14 | 2022-03-19 17:30 | 2022-03-19 18:00 | 0.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.83 | 15486 | 15486 | 0 | BACK REAM OUT OF HOLE F/ 14,922’ T/ 14,456', GPM=350, SPP=2600/2700, RPM=50, TOR=14/21K.
BUCKY BADGER H02 BB | 14 | 2022-03-19 18:00 | 2022-03-20 01:15 | 7.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.14 | 15486 | 15486 | 0 | POOH ON ELEVATORS F/14,456'-T/2,900' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.3 PPG OBM CALCULATED FILL. NOTE: WORK THROUGH TIGHT SPOTS F/10,520' T/9,800' GPM=350, SPP=2600/2700, RPM=50, TOR=14/21K. NOTE: PUMP 30 BBLS KWM 17.5 PPG, PRIOR TO PULLING RT HEAD
BUCKY BADGER H02 BB | 14 | 2022-03-20 01:15 | 2022-03-20 02:00 | 0.75 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 9.17 | 15486 | 15486 | 0 | FLOW CHECK PRIOR TO REMOVING RT-HEAD, (NO FLOW OR SICP), REMOVE RT-HEAD AND INSTALL TRIP NIPPLE, LAY DOWN AGITATOR
BUCKY BADGER H02 BB | 14 | 2022-03-20 02:00 | 2022-03-20 03:00 | 1 | U | PRDHLLT | TRIP | CSG | TRIP FOR CASING / LINER | 9.21 | 15486 | 15486 | 0 | POOH ON ELEVATORS F/2,900'-T/BHA' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.3 PPG OBM CALCULATED FILL.
BUCKY BADGER H02 BB | 14 | 2022-03-20 03:00 | 2022-03-20 04:00 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.25 | 15486 | 15486 | 0 | L/D REAMER, TOMAX, AND BTI VALVE, PULL MWD, L/D MONEL, DRAIN MOTOR, BREAK BIT, L/D BIT AND MOTOR. BIT GRADE: 2-3-CT-S-X-0-CT-TQ NOTE: MOTOR DRAINED GOOD WITH NO VISUAL DAMAGE.
BUCKY BADGER H02 BB | 14 | 2022-03-20 04:00 | 2022-03-20 06:00 | 2 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 9.33 | 15486 | 15486 | 0 | PICK UP 6-3/4" SECURITY GTD64M S/N: 13645346 JETS: 6X18 TFA: 1.49; 5-1/2" MOTOR 6/7L 8.8 STG @ 2.12° SLICK HS88-.002, 0.68 REV/GAL, 4.02' BIT TO BEND, 5.56" KICK PAD OD, FLOW RANGE: 150/400 GPM, MAX DIFF: 2,240 PSI, STALL TQ: 8,014 FT/LBS; BTI VALVE, 5 1/4" NMPDC, 5 1/4" UBHO, (2) 5" NMDC, 5" TOMAX, X/O, (28) STANDS 4.5" DP, AGITATOR. NOTE: BIT TO SVY: 68', BIT TO GAMMA: 55', SURFACE TEST GOOD.
BUCKY BADGER H02 BB | 15 | 2022-03-20 06:00 | 2022-03-20 07:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.4 | 15486 | 15486 | 0 | TIH W/BHA #4 F/135.49'-T/2,700', P/U AGITATOR AND TEST (BEFORE-GPM:100, PSI:700. AFTER-GPM:100, PSI:900). HOLE GIVING PROPER DISPLACMENT. FILL EVERY 30 STDS.
BUCKY BADGER H02 BB | 15 | 2022-03-20 07:30 | 2022-03-20 08:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.42 | 15486 | 15486 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROT. HEAD ASSEMBLY
BUCKY BADGER H02 BB | 15 | 2022-03-20 08:00 | 2022-03-20 10:45 | 2.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.53 | 15486 | 15486 | 0 | TIH F/2,700'-T/9,100'. HOLE GIVING PROPER DISPLACMENT. FILL EVERY 30 STDS.
BUCKY BADGER H02 BB | 15 | 2022-03-20 10:45 | 2022-03-20 13:00 | 2.25 | U | PRDHLLT | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 9.63 | 15486 | 15486 | 0 | REMOVE FEDDER RING, CHANGE OUT DAMAGED SAVER SUB ON TOPDRIVE, CHANGE OUT DAMAGED RETAINER PLATES ON GRABBER DIE BLOCKS
BUCKY BADGER H02 BB | 15 | 2022-03-20 13:00 | 2022-03-20 14:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.67 | 15486 | 15486 | 0 | SERVICE RIG
BUCKY BADGER H02 BB | 15 | 2022-03-20 14:00 | 2022-03-20 17:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.79 | 15486 | 15486 | 0 | TIH F/9,100'-T/15,000'. HOLE GIVING PROPER DISPLACMENT. FILL EVERY 30 STDS.
BUCKY BADGER H02 BB | 15 | 2022-03-20 17:00 | 2022-03-20 18:00 | 1 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 9.83 | 15486 | 15486 | 0 | WASH & REAM F/15,000' T/15,486'. RPM-50, SPP-3,700 PSI, TRQ-15K-22K
BUCKY BADGER H02 BB | 15 | 2022-03-20 18:00 | 2022-03-21 02:45 | 8.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.2 | 15486 | 16866 | 157.7 | DRILL LATERAL ON MUD CAP- ROT (1,380' IN 8.82 HRS @ 156.46 FPH), WOB:30/35K, SPM: 70/70/0, GPM: 370, RPM: 70, MRPM: 252, TMRPM: 322, TRQ: 21/23K, SPP: 4100/4200 PSI, DIFF: 700/800 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-120 PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 15 | 2022-03-21 02:45 | 2022-03-21 06:00 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.33 | 16866 | 16937 | 21.8 | DRILL LATERAL ON MUD CAP- SLIDE (71’ IN 3.18 HRS @ 22.32 FPH) WOB: 18/20K, SPM: 70/70/0, GPM: 370, MMRPM: 252, SPP: 3700/3800 PSI, DIFF: 350/450 PSI. TARGET LINE: 9,676' TVD @ 0' VS @ INC: 86.8° 5' ABOVE/ 5' BELOW, 50’ LEFT / 50' RIGHT RECEIVED TARGET CHANGE VIA EMAIL @ 04:28 HRS TARGET LINE: 9,679' TVD @ 0' VS @ INC: 86.8° 5' ABOVE/ 5' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/15,594' T/15,609', 15' 120R, 18:40-19:20 TQ= R/13, L/12, RPM=70 F/15,878' T/15,886', 8' 180, 20:55-21:30 TQ= R/13, L/12, RPM=70 F/16,065' T/16,077', 12' HS, 22:50-23:17 TQ= R/11, L/13, RPM=70 F/16,349' T/16,359', 10' 80L, 00:54-01:23 TQ= R/15, L/ 8, RPM=70 F/16,535' T/16,543', 8' 180, 02:33-03:00 TQ= R/15, L/ 8, RPM=70 F/16,725' T/16,735', 10' 180, 04:04-04:20 TQ= R/15, L/ 8, RPM=70 F/16,817' T/16,825', 8' 180, 04:58-05:15 TQ= R/15, L/ 8, RPM=70
BUCKY BADGER H02 BB | 16 | 2022-03-21 06:00 | 2022-03-21 12:30 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.6 | 16937 | 17776 | 129.1 | DRILL LATERAL ON MUD CAP- ROT (839' IN 6.68 HRS @ 125.6 FPH), WOB:30/35K, SPM: 67/67/0, GPM: 350, RPM: 70, MRPM: 238, TMRPM: 308, TRQ: 21/26K, SPP: 3800/3900 PSI, DIFF: 500/600 PSI. DRILLING ON MUD CAP WITH MIXTURE OF FRESH WATER AND PRODUCTION FLOWBACK WATER. MAX CASING PSI WHILE DRILLING-XX PSI CASING PSI DURING CONNECTIONS-0 PSI PUMPING 5-10 BBLS OF 2 PPB PHPA SWEEP EVERY CONNECTION OR AS NEEDED. ADDING 3.5 BBLS OF DIESEL @ 6SEC/QT AND TRICKLING 4-5 BUCKETS OF PHPA IN ACTIVE TANK WHILE ON MUD CAP.
BUCKY BADGER H02 BB | 16 | 2022-03-21 12:30 | 2022-03-21 13:30 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.65 | 17776 | 17791 | 15 | DRILL LATERAL ON MUD CAP- SLIDE (15’ IN .82 HRS @ 18.37 FPH) WOB: 18/20K, SPM: 67/67/0, GPM: 350, MMRPM: 238, SPP: 3400/3500 PSI, DIFF: 200/300 PSI. TARGET LINE: 9,679' TVD @ 0' VS @ INC: 86.8° 0' ABOVE/ 10' BELOW, 50’ LEFT / 50' RIGHT SLIDE DEPTHS: F/17,470' T/17,485', 15' 180, 10:12-11:01 TQ= R/14, L/12, RPM=60
BUCKY BADGER H02 BB | 16 | 2022-03-21 13:30 | 2022-03-21 15:15 | 1.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.72 | 17791 | 17791 | 0 | PERFORM CLEAN UP CYCLE, PUMPING (3) TANDEM 30 BBL HIGH VIS SWEEPS AND CIRCULATE TO LOSS ZONE @ 9,787', RPM-70, SPM: 76/76/0, GPM-400, INITIAL SPP-4,000 PSI/FINAL SPP-3,850, MAX CASING PRESSURE= 0 PSI 1ST BTM UP END TQ=16-26K, P/U WT=250K, S/O=145K, ROT=185K 2ND BTM UP END TQ=16-23K, P/U WT=250K, S/O=145K, ROT=185K 3RD BTM UP END TQ=15-20K, P/U WT=250K, S/O=145K, ROT=185K
BUCKY BADGER H02 BB | 16 | 2022-03-21 13:30 | 2022-03-21 13:30 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 10.65 | 17791 | 17791 |  | MILESTONE_TD WELL ON 03/21/2022 @ 13:30 17,791' MD/ 10,103' TVD
BUCKY BADGER H02 BB | 16 | 2022-03-21 15:15 | 2022-03-21 19:45 | 4.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 10.91 | 17791 | 17791 | 0 | BACK REAM OUT THE HOLE F/17,791' T/16,300’ SPM-47/47/0, GPM-250, RPM-60, MRPM-170,TMRPM-230, TRQ-17/26K, SPP-2100/2200 PSI. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI.
BUCKY BADGER H02 BB | 16 | 2022-03-21 19:45 | 2022-03-21 20:30 | 0.75 | U | PRDHLCSG | WAIT | WOW | WAIT ON WEATHER | 10.94 | 17791 | 17791 | 0 | CIRCULATE WHILE WAITING ON WEATHER, (HIGH WINDS AND LIGHTNING) GPM-150, SPM-28/28/0, SPP-1,350, RPM-50, TQ-15-20K
BUCKY BADGER H02 BB | 16 | 2022-03-21 20:30 | 2022-03-22 01:30 | 5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.15 | 17791 | 17791 | 0 | BACK REAM OUT THE HOLE F/16,300' T/13,200’ SPM-47/47/0, GPM-250, RPM-60, MRPM-170,TMRPM-230, TRQ-17/26K, SPP-2100/2200 PSI. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI.
BUCKY BADGER H02 BB | 16 | 2022-03-22 01:30 | 2022-03-22 01:45 | 0.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.16 | 17791 | 17791 | 0 | POOH ON ELEVATORS F/13,200'-T/12,800' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.2 PPG OBM CALCULATED FILL.
BUCKY BADGER H02 BB | 16 | 2022-03-22 01:45 | 2022-03-22 02:45 | 1 | U | PRDHLCSG | WAIT | WOW | WAIT ON WEATHER | 11.2 | 17791 | 17791 | 0 | CIRCULATE WHILE WAITING ON WEATHER, (HIGH WINDS AND LIGHTNING) GPM-240, SPM-45/45/0, SPP-1,750, RPM-50, TQ-13K
BUCKY BADGER H02 BB | 16 | 2022-03-22 02:45 | 2022-03-22 04:00 | 1.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.25 | 17791 | 17791 | 0 | POOH ON ELEVATORS F/12,800'-T/10,900' WORK THROUGH TIGHT SPOTS F/11,640' T/10,900' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.2 PPG OBM CALCULATED FILL.
BUCKY BADGER H02 BB | 16 | 2022-03-22 04:00 | 2022-03-22 04:15 | 0.25 | U | PRDHLCSG | WAIT | WOW | WAIT ON WEATHER | 11.26 | 17791 | 17791 | 0 | CIRCULATE WHILE WAITING ON WEATHER, (HIGH WINDS AND LIGHTNING) GPM-240, SPM-45/45/0, SPP-1,750, RPM-50, TQ-13K
BUCKY BADGER H02 BB | 16 | 2022-03-22 04:15 | 2022-03-22 06:00 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.33 | 17791 | 17791 | 0 | POOH ON ELEVATORS F/10,900'-T/8,000' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.2 PPG OBM CALCULATED FILL.
BUCKY BADGER H02 BB | 17 | 2022-03-22 06:00 | 2022-03-22 07:45 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.41 | 17791 | 17791 | 0 | POOH ON ELEVATORS F/8,000'-T/3,142' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.2 PPG OBM CALCULATED FILL.
BUCKY BADGER H02 BB | 17 | 2022-03-22 07:45 | 2022-03-22 08:45 | 1 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 11.45 | 17791 | 17791 | 0 | FLOW CHECK PRIOR TO REMOVING RT-HEAD, (NO FLOW OR SICP), REMOVE RT-HEAD AND INSTALL TRIP NIPPLE, LAY DOWN AGITATOR
BUCKY BADGER H02 BB | 17 | 2022-03-22 08:45 | 2022-03-22 09:30 | 0.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 11.48 | 17791 | 17791 | 0 | POOH ON ELEVATORS F/3,142'-T/BHA' NOTE: CHOKE POSITION 0%, FILLING BACKSIDE WITH 10.2 PPG OBM CALCULATED FILL.
BUCKY BADGER H02 BB | 17 | 2022-03-22 09:30 | 2022-03-22 10:30 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 11.52 | 17791 | 17791 | 0 | L/D TOMAX, AND BTI VALVE, PULL MWD, L/D MONEL, DRAIN MOTOR, BREAK BIT, L/D BIT AND MOTOR. BIT GRADE: 0-0-NO-A-X-0-NO-TD, L/D COMPLETE BHA ASSEMBLY NOTE: MOTOR DRAINED GOOD WITH NO VISUAL DAMAGE.
BUCKY BADGER H02 BB | 17 | 2022-03-22 10:30 | 2022-03-22 11:00 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 11.54 | 17791 | 17791 | 0 | PULL WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4-1/2" ELEVATORS AND PREP RIG FLOOR FOR CSG OPS.
BUCKY BADGER H02 BB | 17 | 2022-03-22 11:00 | 2022-03-22 12:00 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 11.58 | 17791 | 17791 | 0 | LUBRICATE RIG.
BUCKY BADGER H02 BB | 17 | 2022-03-22 12:00 | 2022-03-22 13:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 11.63 | 17791 | 17791 | 0 | HOLD PJSM WITH ALL PERSONNEL INVOLVED IN CASING OPERATIONS. R/U CASING CREW AND EQUIPMENT.
BUCKY BADGER H02 BB | 17 | 2022-03-22 13:00 | 2022-03-23 02:00 | 13 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.17 | 17791 | 17791 | 0 | CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: (1) INNOVEX DV FLOAT SHOE, (1) JT 5" 18# P-110 ICY WEDGE 425 CASING, (1) INNOVEX DV FLOAT COLLAR, (1) JT 5" 18# P-110 ICY WEDGE 425 CASING, (1) JT 5" 18# P-110 ICY WEDGE 425 PUP, GEO DYNAMIC TOE SLEEVE, (1) JT 5" 18# P-110 ICY WEDGE 425 PUP, (2) JTS 5" 18# P-110 ICY WEDGE 425 CASING, PICK UP CRT AND TEST FLOAT EQUIPMENT- TEST GOOD. RUN 5" 18# P-110 ICY WEDGE 425 CASING T/8,731.7', XO, 1 JOINT 5.5', 1 MARKER @ 8,664.2', RUN 5.5'' 23# P-110 ICY WEDGE 463 F/8,664.2' T/16,700'
BUCKY BADGER H02 BB | 17 | 2022-03-23 02:00 | 2022-03-23 06:00 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.33 | 17791 | 17791 | 0 | WASH/REAM 5.5" 23# P-110 ICY WEDGE 463 CASING F/16,700' T/17,776' GPM=265, SPP= 938, RPM=23, TQ=18-25K
BUCKY BADGER H02 BB | 18 | 2022-03-23 06:00 | 2022-03-23 06:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.35 | 17791 | 17791 | 0 | LAND ON HANGER W/125K (W/O BLOCKS). RUN 5" & 5-1/2" PROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: (1) INNOVEX DV FLOAT SHOE, (1) JT 5" 18# P-110 ICY WEDGE 425 CASING, (1) INNOVEX DV FLOAT COLLAR, (1) JT 5" 18# P-110 ICY WEDGE 425 CASING, (1) JT 5" 18# P-110 ICY WEDGE 425 PUP, GEO DYNAMIC TOE SLEEVE, (1) JT 5" 18# P-110 ICY WEDGE 425 PUP, (201 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, (1) X-OVER, (1) JT 5-1/2" 23# P-110 ICY WEDGE 463 CASING, (1) MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, (195 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING. CASING SHOE: 17,763.4' TOP OF FLOAT COLLAR: 17,716.6' BOTTOM OF TOE SLEEVE VALVE: 17,647.2' TOP OF TOE SLEEVE VALVE: 17,656.8' TOP OF X-OVER: 8,729.0' TOP OF MARKER JOINT ABOVE X-OVER: 8,664.2' 6 JOINTS OF 5" LEFT OUT: 266.54' 4 JOINTS OF 5-1/2" LEFT OUT: 177.11'
BUCKY BADGER H02 BB | 18 | 2022-03-23 06:30 | 2022-03-23 07:00 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 12.38 | 17791 | 17791 | 0 | RIG DOWN CRT AND INSTALL WEATHERFORD TIW, CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STAND PIPE, RIG DOWN BUTCH'S CASING TOOLS.
BUCKY BADGER H02 BB | 18 | 2022-03-23 07:00 | 2022-03-23 08:15 | 1.25 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.43 | 17791 | 17791 | 0 | CIRCULATE CASING CAPACITY PRIOR TO CONDUCTING PRODUCTION CMT JOB. GPM: 343, SPP: 1495 PSI
BUCKY BADGER H02 BB | 18 | 2022-03-23 08:15 | 2022-03-23 10:30 | 2.25 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 12.52 | 17791 | 17791 | 0 | 1ST STAGE: HELD PJSM, FLUSHED THROUGH & TESTED CEMENTING LINES T/9000 PSI, CEMENTED 5/ 5 1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: PUMPED 80 BBLS 10.5 PPG WEIGHTED GTX SPACER, 276 BBL 13.5 PPG 910 SK 1.70 YIELD 35/65 POZ-PM-CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 345 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER. FINAL LIFT PRESSURE WAS 2020 PSI @ 8.0 BPM, PUMPS WERE SLOWED 4.0 BPM W/ 1400 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2400 PSI, HELD FOR 5 MIN, BLED BACK 3.0 BBLS. FLOATS HELD. BUMP PLUG ON 03/23/2022 @ 10:30
BUCKY BADGER H02 BB | 18 | 2022-03-23 10:30 | 2022-03-23 11:00 | 0.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 12.54 | 17791 | 17791 | 0 | HELD PJSM, RIG DOWN CIRCULATING IRON FROM RIG FLOOR, RIG UP CIRCULATING IRON TO KILL LINE, REMOVE CHECK VALVE FROM KILL LINE. CLOSE TOP VBR'S, PUMP 100 BBLS 17.5 PPG KILL MUD DOWN THE ANNULUS THROUGH KILL LINE TO ESTABLISH INJECTION RATE. INITIAL CP: 0 PSI. FINAL CP: 0 PSI. 1 BPM= KILL LINE 0 PSI & CASING PSI= 0 PSI 2 BPM= KILL LINE 0 PSI & CASING PSI= 0 PSI 3 BPM= KILL LINE 160 PSI & CASING PSI= 255 PSI 4 BPM= KILL LINE 87 PSI & CASING PSI= 88 PSI 5 BPM= KILL LINE 309 PSI & CASING PSI= 166 PSI 6 BPM= KILL LINE 301 PSI & CASING PSI= 86 PSI 7 BPM= KILL LINE 309 PSI & CASING PSI= 0 PSI
BUCKY BADGER H02 BB | 18 | 2022-03-23 11:00 | 2022-03-23 13:15 | 2.25 | P | PRDHLCSG | CMT | REMCM | REMEDIAL CEMENT OPERATIONS | 12.64 | 17791 | 17791 | 0 | START 2ND STAGE: TEST CEMENTING LINES T/6000 PSI, PUMP 35 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 288 BBLS 950 SK 1.70 YIELD 35/65 POZ-SM-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.70 YIELD TYPE I/II 14.8 PPG TAIL CEMENT, FOLLOWED BY 33 BBLS FRESH WATER. MAX CSG PSI 1838 PSI W/288 BBLS LEAD CMT PUMPED @ 6 BPM, AVG CASING PSI= 950 PSI, CSG PRESSURE FELL TO 0 PSI WITH PUMPS OFF AFTER CEMENTING.
BUCKY BADGER H02 BB | 18 | 2022-03-23 13:15 | 2022-03-23 13:45 | 0.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 12.66 | 17791 | 17791 | 0 | RIG DOWN CEMENT HEAD ON FLOOR, RIG DOWN CIRCULATING IRON TIED INTO KILL LINE, WHILE MONITORING CASING PRESSURE.
BUCKY BADGER H02 BB | 18 | 2022-03-23 13:45 | 2022-03-23 14:30 | 0.75 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 12.69 | 17791 | 17791 | 0 | LAY DOWN LANDING JOINT, PICK UP WELLHEAD WASHOUT TOOL AND FLUSH OUT WELLHEAD. L/D WASHOUT TOOL, PICK UP, INSTALL, AND TEST WELLHEAD PACK-OFF, PULL TEST PACK-OFF TO 25K LBS AND TEST PACK-OFF TO 10K PSI. L/D SETTING TOOL. INSTALL BACK PRESSURE VALVE.
BUCKY BADGER H02 BB | 18 | 2022-03-23 14:30 | 2022-03-23 15:00 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 12.71 | 17791 | 17791 | 0 | FLUSH THROUGH CHOKES, PANIC LINE, #1,2,&3 MUD PUMPS, AND TOP DRIVE W/ FRESH WATER
BUCKY BADGER H02 BB | 18 | 2022-03-23 15:00 | 2022-03-23 15:30 | 0.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 12.73 | 17791 | 17791 | 0 | RAISE AND INSTALL BOP WRANGLER ONTO BOP STACK, BREAK BOLTS ON SPACER SPOOL, RAISE BOP, AND REMOVE SPACER SPOOL
BUCKY BADGER H02 BB | 18 | 2022-03-23 15:30 | 2022-03-23 16:00 | 0.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 12.75 | 17791 | 17791 | 0 | INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI.
BUCKY BADGER H02 BB | 18 | 2022-03-23 16:00 | 2022-03-23 16:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 12.75 | 17791 | 17791 |  | MILESTONE_WELL RELEASE ON 03/23/2022 @ 16:00
BUCKY BADGER H02 BB | 18 | 2022-03-23 16:00 | 2022-03-23 16:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 12.75 | 17791 | 17791 |  | MILESTONE_RIG RELEASE ON 03/23/2022 @ 16:00
BUCKY BADGER H02 BB | 18 | 2022-03-23 16:00 | 2022-03-23 16:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 12.75 | 17791 | 17791 |  | MILESTONE_TURN OVER TO COMPLETION ON 03/23/2022 @ 16:00
DIETZ OL UNIT 3H | 2 | 2020-07-09 06:00 | 2020-07-09 09:00 | 3 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK FROM PALO DURO 1H TO DIETZ OL 3H, CENTERED AND LEVELED SUB OVER CONDUCTOR, RIG UP AND LAY DOWN LANDING JT, CASING BAILS/ELEVATORS, RIG UP RIG ELEVATORS
DIETZ OL UNIT 3H | 2 | 2020-07-09 09:00 | 2020-07-09 09:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 07/09/2020 @ 06:00
DIETZ OL UNIT 3H | 2 | 2020-07-09 09:00 | 2020-07-09 10:00 | 1 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 0 | 108 | 108 | 0 | RIG UP CELLAR PUMPS AND LINES, RISER ON CONDUCTOR PIPE
DIETZ OL UNIT 3H | 2 | 2020-07-09 10:00 | 2020-07-09 11:00 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | PICK UP DIRECTIONAL BHA: PICK UP BIT 13-1/2" ULTERRA SPL616 W: 9/14 JETS TFA: 1.353, MOTOR 7-3/4", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 108'.
DIETZ OL UNIT 3H | 2 | 2020-07-09 11:00 | 2020-07-09 17:00 | 6 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.25 | 108 | 2496 | 398 | ROTATE (2388' IN 6.25 HRS @ 382 FPH) WOB-15/30K, RPM-100, TRQ- 8/12K, SPM-105/105, GPM-808, MMRPM-134, TRPM-234, SPP-1600/2100 PSI, DIFF-400/500
DIETZ OL UNIT 3H | 2 | 2020-07-09 11:00 | 2020-07-09 11:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL 07/09/2020 @ 11:00
DIETZ OL UNIT 3H | 2 | 2020-07-09 17:00 | 2020-07-09 19:00 | 2 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.33 | 2496 | 2769 | 136.5 | SLIDE (273' IN 1.75 HRS @ 156 FPH) WOB: 20/30K, SPM-105/105, GPM-808, MMRPM-134, SPP- 1700/2100 PSI, DIFF- 200/400 PSI. SLIDE DEPTHS: SLD F/510' T/525' 15' TF-80M 12;08-12;15 SLD F/600' T/615' 15' TF-80M 12;20-12;26 SLD F/695' T/710' 15' TF-80M 12;38-12;45 SLD F/785' T/800' 15' TF-90M 12;55-12;59 SLD F/975' T/993' 18' TF-50R 13;20-14;00
DIETZ OL UNIT 3H | 2 | 2020-07-09 19:00 | 2020-07-09 20:30 | 1.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.4 | 2769 | 2769 | 0 | PUMP 3-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-808, RPM-100, TRQ-1/2K, SPP-1700 PSI.
DIETZ OL UNIT 3H | 2 | 2020-07-09 20:30 | 2020-07-09 22:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.46 | 2769 | 2769 | 0 | TRIP OUT OF HOLE F/2,769' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
DIETZ OL UNIT 3H | 2 | 2020-07-09 22:00 | 2020-07-09 23:30 | 1.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.52 | 2769 | 2769 | 0 | L/D TOP MONEL, REMOVE MWD TOOL, DRAIN MOTOR, RACK BHA BACK IN DERRICK.
DIETZ OL UNIT 3H | 2 | 2020-07-09 23:30 | 2020-07-10 00:30 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.56 | 2769 | 2769 | 0 | PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
DIETZ OL UNIT 3H | 2 | 2020-07-10 00:30 | 2020-07-10 04:30 | 4 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.73 | 2769 | 2769 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 65 JOINTS OF 10 3/4" 45.5# J-55 T/2,760.58', RAN 19 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY 4TH JT. ALL THE WAY TO 78', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 65" BELOW GROUND LEVEL. (WASH DOWN LANDING JOINT AND SET 90K ON BASE PLATE. SHOE: 2,759' TOP OF FLOAT COLLAR: 2,675'
DIETZ OL UNIT 3H | 2 | 2020-07-10 04:30 | 2020-07-10 05:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.77 | 2769 | 2769 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOLS, GPM-404, SPP-110 PSI. NO LOSSES.
DIETZ OL UNIT 3H | 2 | 2020-07-10 05:30 | 2020-07-10 06:00 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.79 | 2769 | 2769 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, AND R/D CELLAR PUMPS, R/U CIRC. IRON FOR CEMENT JOB
DIETZ OL UNIT 3H | 3 | 2020-07-10 06:00 | 2020-07-10 07:00 | 1 | P | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.83 | 2769 | 2769 | 0 | RIG UP CEMENT HEAD AND CIRCULATING IRON W/NINE ENERGY
DIETZ OL UNIT 3H | 3 | 2020-07-10 07:00 | 2020-07-10 09:30 | 2.5 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.94 | 2769 | 2769 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 25 BBL 8.3 PPG FRESH WATER SPACER, 300 BBLS 11.6 PPG LEAD CEMENT, 86 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 257 BBLS OF 9.5 PPG OIL BASE MUD. BUMPED PLUG W/ 700 PSI PRESSURED UP T/ 1200PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 25 BBLS OF SPACER AND 207 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
DIETZ OL UNIT 3H | 3 | 2020-07-10 09:30 | 2020-07-10 10:00 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.96 | 2769 | 2769 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI (PRESSURE HELD TEST WAS GOOD)
DIETZ OL UNIT 3H | 3 | 2020-07-10 10:00 | 2020-07-10 11:30 | 1.5 | P | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 1.02 | 2769 | 2769 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
DIETZ OL UNIT 3H | 3 | 2020-07-10 11:30 | 2020-07-10 11:30 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 1.02 | 2769 | 2769 |  | MILESTONE_HOLD WELL OPERATIONS 1 07-10-2020 @ 11:30
DIETZ OL UNIT 3H | 4 | 2020-07-19 18:00 | 2020-07-19 20:30 | 2.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 1.13 | 2769 | 2769 | 0 | PREPPED RIG TO WALK TO DIETZ OL 3H, SWAP HYDRAULICS TO WALKING SYSTEM, WALK RIG, CENTERED AND LEVELED SUB OVER WELLHEAD, WITNESSED RIG CENTER OVER WELL.
DIETZ OL UNIT 3H | 4 | 2020-07-19 18:00 | 2020-07-19 18:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 1.02 | 2769 | 2769 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 07/19/2020 @ 18:00
DIETZ OL UNIT 3H | 4 | 2020-07-19 20:30 | 2020-07-19 23:00 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.23 | 2769 | 2769 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, UNLATCHED BOP WRANGLER FROM BOP'S & LAID OVER SAME, INSTALLED TURNBUCKLES & CENTERED STACK, HOOK UP FLOWLINE, REMOVE CASING RAMS AND INSTALL VARIABLE RAMS, R/U KILL LINE.
DIETZ OL UNIT 3H | 4 | 2020-07-19 23:00 | 2020-07-20 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.27 | 2769 | 2769 | 0 | MAKE UP TEST PLUG TO JOINT DRILL PIPE AND SET, FILL STACK, TEST BOP 250 PSI LOW/5000 PSI HIGH. TEST WH/BOP, TOP RAMS, KILL LINE, AND CHECK VALVE, R/D TESTERS.
DIETZ OL UNIT 3H | 4 | 2020-07-20 | 2020-07-20 01:00 | 1 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.31 | 2769 | 2769 | 0 | RIG UP FLOWLINE TO SCISSOR, INSTALL TRIP NIPPLE, PICK UP MOUSEHOLE, CHANGE OUT TORQUE GUAGE AND PULL CYLINDER
DIETZ OL UNIT 3H | 4 | 2020-07-20 01:00 | 2020-07-20 02:00 | 1 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.35 | 2769 | 2769 | 0 | INSTALL WEAR BUSHING, CLEAN RIG FLOOR AND PREP TO P/U BHA.
DIETZ OL UNIT 3H | 4 | 2020-07-20 02:00 | 2020-07-20 06:00 | 4 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.52 | 2769 | 2769 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.497) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.65' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 8" UBHO, 2-8" NMDC,6-6.5" DC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-68', TEST MWD ( GOOD TEST).
DIETZ OL UNIT 3H | 5 | 2020-07-20 06:00 | 2020-07-20 07:00 | 1 | P | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 1.56 | 2769 | 2769 | 0 | TRIP IN THE HOLE F/BHA T/2,675' - P/U AGITATOR ON STAND 22 (BEFORE 1130 PSI AFTER 1430 PSI @ 9BPM).
DIETZ OL UNIT 3H | 5 | 2020-07-20 07:00 | 2020-07-20 07:30 | 0.5 | P | INTHL | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.58 | 2769 | 2769 | 0 | REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD
DIETZ OL UNIT 3H | 5 | 2020-07-20 07:30 | 2020-07-20 08:00 | 0.5 | P | INTHL | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.6 | 2769 | 2779 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/2,769' T/2,779', GPM-476, SPP-1450 PSI, RPM-50, DIFF-150 PSI.
DIETZ OL UNIT 3H | 5 | 2020-07-20 08:00 | 2020-07-20 08:30 | 0.5 | P | INTHL | TEST | LOTFIT | LOT / FIT | 1.63 | 2779 | 2779 | 0 | PERFORM F.I.T. WITH 9.3 PPG MUD, 325 PSI SURFACE PRESSURE FOR 11.6 PPG EMW. SHOE MD-2,760' TVD-2,717'.
DIETZ OL UNIT 3H | 5 | 2020-07-20 08:30 | 2020-07-21 | 15.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.27 | 2779 | 7733 | 319.6 | ROT (4954' IN 15.63 HRS @ 317 FPH) WOB: 25/35K, SPM: 95/95, GPM: 753, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 9K/18K, SPP: 3200/4100 PSI, DIFF: 600/900 PSI.
DIETZ OL UNIT 3H | 5 | 2020-07-21 | 2020-07-21 06:00 | 6 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.52 | 7733 | 8032 | 49.8 | SLIDE (299' IN 5.87 HRS @ 51 FPH) WOB: 5/10K, SPM: 95/95, GPM: 753, MMRPM: 125, SPP: 2900/3200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/2970' T/2988' 18' TF-30R 9;04-9;15 SLD F/3247' T/3262' 15' TF-90R 9;56-10;03 SLD F/3435' T/3450' 15' TF-90R 10;38-10;45 SLD F/3720' T/ 3738' 18' TF-90R 11;42-12;05 SLD F/5135' T/5165' 30' TF-40R 15;46-16;00 SLD F/5600' T/5620' 20' TF-130R 17;18-17;27 SLD F/6165 T/6187 22' TF-30L 1909-1933 SLD F/6450 T/6470 20' TF-HS 2026-2050 SLD F/7010 T/7027 17' TF-20R 2240-2314 SLD F/7110 T/7130 20' TF-HS 2333-0004 SLD F/7477 T/7494 17' TF-HS 113-147 SLD F/7665 T/7689 14' TF-HS 221-257 SLD F/7750 T/7778 28' TF-HS 312-356 SLD F/7860 T/7880 20' TF-30L 414-440 SLD F/7956 T/7971 15' TF-HS 457-525
DIETZ OL UNIT 3H | 6 | 2020-07-21 06:00 | 2020-07-21 10:30 | 4.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.71 | 8032 | 9405 | 305.1 | ROT (1373' IN 4.7 HRS @ 292.1 FPH) WOB: 35/45K, SPM: 95/95, GPM: 753, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 12K/15K, SPP: 3100/4000 PSI, DIFF: 700/900 PSI.
DIETZ OL UNIT 3H | 6 | 2020-07-21 10:30 | 2020-07-21 11:30 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.75 | 9405 | 9440 | 35 | SLIDE (35' IN .80 HRS @ 44 FPH) WOB: 15/30K, SPM: 95/95, GPM: 753, MMRPM: 125, SPP: 3100/3500 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/8890' T/8910' 20' TF-50M 827-851 SLD F/9170' T/9185' 15' TF-220M 944-1008
DIETZ OL UNIT 3H | 6 | 2020-07-21 11:30 | 2020-07-21 12:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.77 | 9440 | 9440 | 0 | SERVICE TD, ST80, DRAWORKS, CATWALK
DIETZ OL UNIT 3H | 6 | 2020-07-21 12:00 | 2020-07-21 12:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.79 | 9440 | 9545 | 210 | ROT (105' IN 0.5 HRS @ 210 FPH) WOB: 35/45K, SPM: 95/95, GPM: 753, MMRPM: 125, RPM: 40, TRPM: 165, TRQ: 14K/20K, SPP: 3500/4400 PSI, DIFF: 700/900 PSI.
DIETZ OL UNIT 3H | 6 | 2020-07-21 12:30 | 2020-07-21 14:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.85 | 9545 | 9580 | 23.3 | SLIDE (35' IN 1.37 HRS @ 25.6 FPH) WOB: 15/30K, SPM: 95/95, GPM: 753, MMRPM: 125, SPP: 3500/3900 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/9545' T/9580' 35' TF-330M 12:38-14:00 START INTERMEDIATE CURVE SECTION ON 7/21/20 @ 12:30 (9545' MD / 9348' TVD)
DIETZ OL UNIT 3H | 6 | 2020-07-21 14:00 | 2020-07-21 14:30 | 0.5 | U | INTHL | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 2.88 | 9580 | 9580 | 0 | CHANGE OUT RCH BEARING ASSEMBLY, HEAD LEAKING, BOTTOM ELEMENT RIPPED.
DIETZ OL UNIT 3H | 6 | 2020-07-21 14:30 | 2020-07-21 18:30 | 4 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.04 | 9580 | 10078 | 124.5 | ROT (498' IN 3.97 HRS @ 125.4 FPH) WOB: 35/45K, SPM: 95/95, GPM: 753, MMRPM: 125, RPM: 45, TRPM: 170, TRQ: 14K/20K, SPP: 3600/4500 PSI, DIFF: 700/900 PSI.
DIETZ OL UNIT 3H | 6 | 2020-07-21 18:30 | 2020-07-22 | 5.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.27 | 10078 | 10249 | 31.1 | SLIDE (171' IN 5.53 HRS @ 30.9 FPH) WOB: 15/30K, SPM: 95/95, GPM: 753, MMRPM: 125, SPP: 3600/4000 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/9650' T/9670' 20' TF-HS 15;32-15;59 SLD F/9750' T/9766' 16' TF-HS 16;27-16:50 SLD F/9840 T/9860 20' TF-HS 17:19-17:50 SLD F/9930 T/9955 25' TF-HS 1808-1925 SLD F/10017 T/10047 30' TF-HS 1956-2047 SLD F/10111 T/10141 30' TF-HS 2111-2152 SLD F/10205 T/10235 30' TF-HS 2225-2347
DIETZ OL UNIT 3H | 6 | 2020-07-22 | 2020-07-22 01:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.33 | 10249 | 10249 | 0 | PUMP 2-30 BBL LCM SWEEPS IN TANDEM, CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM: 753, RPM: 45, TRQ: 5K/7K, SPP: 3600 PSI, INCREASE MW 9.4 TO 9.6 PPG, FLOW CHECK WELL, WELL STATIC, PUMP SLUG.
DIETZ OL UNIT 3H | 6 | 2020-07-22 01:30 | 2020-07-22 02:00 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 3.35 | 10249 | 10249 | 0 | TRIP OUT THE HOLE 10 STANDS F/10,249' T/9,315', HOLE TAKING PROPER FILL, NO EXCESSIVE DRAG.
DIETZ OL UNIT 3H | 6 | 2020-07-22 02:00 | 2020-07-22 06:00 | 4 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.52 | 10249 | 10249 | 0 | L/D 5" DRILL PIPE F/9,315' T/3679', HOLE TAKING PROPER FILL.
DIETZ OL UNIT 3H | 7 | 2020-07-22 06:00 | 2020-07-22 10:30 | 4.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.71 | 10249 | 10249 | 0 | LAY DOWN 5" DRILL PIPE TO BHA
DIETZ OL UNIT 3H | 7 | 2020-07-22 10:30 | 2020-07-22 14:00 | 3.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.85 | 10249 | 10249 | 0 | LAY DOWN BHA
DIETZ OL UNIT 3H | 7 | 2020-07-22 14:00 | 2020-07-22 15:00 | 1 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.9 | 10249 | 10249 | 0 | CLEAN RIG FLOOR, PULL WEAR BUSHING
DIETZ OL UNIT 3H | 7 | 2020-07-22 15:00 | 2020-07-22 16:30 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.96 | 10249 | 10249 | 0 | CHANGE OUT TOP RAMS TO 7-5/8" CASING RAMS, TEST DOOR SEALS TO 500 PSI
DIETZ OL UNIT 3H | 7 | 2020-07-22 16:30 | 2020-07-22 18:00 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.02 | 10249 | 10249 | 0 | SAFETY MEETING, RIG UP FRANK'S CASING TOOLS
DIETZ OL UNIT 3H | 7 | 2020-07-22 18:00 | 2020-07-23 06:00 | 12 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.52 | 10249 | 10249 | 0 | M/U FLOAT EQUIPMENT AND RUN INT CSG T/9,300' HELD PJSM THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 234 TTL JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 45 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 2863.60'. FLOAT SHOE-10,239.06 TOP OF FLOAT COLLAR-10,151.10
DIETZ OL UNIT 3H | 8 | 2020-07-23 06:00 | 2020-07-23 07:30 | 1.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.58 | 10249 | 10249 | 0 | RUN INT CSG T/10,239' HELD PJSM THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 234 TTL JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 45 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 2863.60'. P/U LANDING JT & LAND CASING ON MANDREL WITH 200K (W/O BLOCKS). FLOAT SHOE-10,239.06 TOP OF FLOAT COLLAR-10,151.10
DIETZ OL UNIT 3H | 8 | 2020-07-23 07:30 | 2020-07-23 08:00 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 4.6 | 10249 | 10249 | 0 | HELD PJSM, RIG DOWN FRANK'S CASING TOOLS AND EQUIPMENT. RIG UP NINE CEMENT HEAD
DIETZ OL UNIT 3H | 8 | 2020-07-23 08:00 | 2020-07-23 09:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.67 | 10249 | 10249 | 0 | CIRCULATE THROUGH CMT HEAD, FULL CASING CAPACITY. GPM-337, 8 BPM, SPP-250 PSI, CUT MW F/9.7 PPG T/ 9.3 PPG.
DIETZ OL UNIT 3H | 8 | 2020-07-23 09:30 | 2020-07-23 12:00 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.77 | 10249 | 10249 | 0 | SWAP LINES, TEST TO 5,000 PSI, AND CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG GTX SPACER. 299 BBL 11.8 PPG 865 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 466 BBLS OF 9.3 PPG OIL BASE MUD @ 7 BPM SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 1620 PSI, DID NOT BUMP PLUG, PUMPED TWO BBLS OVER DISPLACEMENT, PRESSURE AT 1620 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 4 BBLS. FLOATS HELD. PLUG DOWN @ 12:00 HRS ON 07/23/2020, GOT BACK 40 BBLS OF SPACER AND 11 BBLS OF LEAD CMT BACK TO SURFACE, & HAD FULL RETURNS ENTIRE CEMENTING JOB
DIETZ OL UNIT 3H | 8 | 2020-07-23 12:00 | 2020-07-23 13:00 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.81 | 10249 | 10249 | 0 | RIGGED DOWN CEMENTING EQUIPMENT, BREAK OUT & LAY DOWN LANDING JOINT
DIETZ OL UNIT 3H | 8 | 2020-07-23 13:00 | 2020-07-23 14:30 | 1.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.88 | 10249 | 10249 | 0 | MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP & MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 10K, BROKE OUT & LAID DOWN SETTING TOOL.
DIETZ OL UNIT 3H | 8 | 2020-07-23 14:30 | 2020-07-23 16:00 | 1.5 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.94 | 10249 | 10249 | 0 | CHANGED OUT TOP PIPE RAMS F/7-5/8" CASING RAMS TO 3.5"x5.5" VBR'S
DIETZ OL UNIT 3H | 8 | 2020-07-23 16:00 | 2020-07-23 16:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 4.96 | 10249 | 10249 | 0 | RIGGED DOWN CASING BAIL EXTENSIONS, ELEVATORS, AND REMOVED FROM RIG FLOOR TO GROUND
DIETZ OL UNIT 3H | 8 | 2020-07-23 16:30 | 2020-07-23 17:00 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.98 | 10249 | 10249 | 0 | PICKED UP & INSTALLED BOP TEST PLUG, FILLED STACK WITH FRESH WATER & PREPPED BOP'S TO BE TESTED
DIETZ OL UNIT 3H | 8 | 2020-07-23 17:00 | 2020-07-23 19:00 | 2 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 5.06 | 10249 | 10249 | 0 | CHANGED OUT TOP DRIVE SAVER SUB FROM 4.5" IF TO DS42. TIGHENED DOWN BOLTS TO FEDDER RING, INSTALLED TIE WIRE TO FEDDER RING BOLTS, REMOVED 5" DIE BLOCKS AND STABBING GUIDE FROM PIPE HANDLER, INSTALLED 4.5" DIE BLOCKS AND STABBING GUIDE
DIETZ OL UNIT 3H | 8 | 2020-07-23 19:00 | 2020-07-24 01:30 | 6.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.33 | 10249 | 10249 | 0 | TESTED BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 5000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST TO 1500 PSI. RIG DOWN TESTERS.
DIETZ OL UNIT 3H | 8 | 2020-07-24 01:30 | 2020-07-24 02:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.35 | 10249 | 10249 | 0 | TEST 7-5/8" INTERMEDIATE CASING T/3,500 PSI. R/D TESTERS.
DIETZ OL UNIT 3H | 8 | 2020-07-24 02:00 | 2020-07-24 03:00 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.4 | 10249 | 10249 | 0 | REMOVE WEAR BUSHING RUNNING TOOL FROM 5" DP AND MAKE UP ON 4.5". INSTALL WEAR BUSHING
DIETZ OL UNIT 3H | 8 | 2020-07-24 03:00 | 2020-07-24 04:30 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.46 | 10249 | 10249 | 0 | CUT/SLIP DRILL LINE AND PERFORM BOP DRAWDOWN TEST
DIETZ OL UNIT 3H | 8 | 2020-07-24 04:30 | 2020-07-24 05:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.48 | 10249 | 10249 | 0 | SERVICE RIG
DIETZ OL UNIT 3H | 8 | 2020-07-24 05:00 | 2020-07-24 06:00 | 1 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.52 | 10249 | 10249 | 0 | PREP TO PICK UP AND PICK UP 6.75" ULTERRA RPS613 SER 48479: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.4' BIT TO BEND 5-3/8" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-70'. BIT TO GAMMA-60', TEST MWD (TEST GOOD).
DIETZ OL UNIT 3H | 9 | 2020-07-24 06:00 | 2020-07-24 07:00 | 1 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.56 | 10249 | 10249 | 0 | PICK UP MUD MOTOR, MONEL, UBHO AND SCRIBE. INSTALL MWD.
DIETZ OL UNIT 3H | 9 | 2020-07-24 07:00 | 2020-07-24 07:30 | 0.5 | P | INTHLCSG | LOG | MWD | MWD | 5.58 | 10249 | 10249 | 0 | TEST MWD-TEST GOOD.
DIETZ OL UNIT 3H | 9 | 2020-07-24 07:30 | 2020-07-24 09:00 | 1.5 | U | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.65 | 10249 | 10249 | 0 | WHILE MAKING UP BIT TO MUD MOTOR, BIT BOX CONNECTION ON MUD MOTOR BROKE LOOSE. LAY DOWN MUD MOTOR AND PICK UP NEW MOTOR. RE-SCRIBE, TEST MWD-GOOD, AND M/U DRILL BIT. 6.75" ULTERRA RPS613 SER 48479: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.44' BIT TO BEND 5-3/8" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-70'. BIT TO GAMMA-60', TEST MWD (TEST GOOD).
DIETZ OL UNIT 3H | 9 | 2020-07-24 09:00 | 2020-07-24 09:30 | 0.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.67 | 10249 | 10249 | 0 | PICK UP DRILL PIPE F/BHA T/1,000'
DIETZ OL UNIT 3H | 9 | 2020-07-24 09:30 | 2020-07-24 10:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.69 | 10249 | 10249 | 0 | CHANGE ST-80 DIES
DIETZ OL UNIT 3H | 9 | 2020-07-24 10:00 | 2020-07-24 20:30 | 10.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 6.13 | 10249 | 10249 | 0 | PICK UP DRILL PIPE F/1,000' T/2,710'. P/U AGITATOR.(PSI BEFORE-1100 PSI, PSI AFTER- 1350 PSI, GPM-256. CONTINUE PICKING UP DRILL PIPE F/2,745' T/9,660'. PROPER DISPACEMENTS WHILE TRIPPING IN HOLE.
DIETZ OL UNIT 3H | 9 | 2020-07-24 20:30 | 2020-07-24 21:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 6.15 | 10249 | 10249 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
DIETZ OL UNIT 3H | 9 | 2020-07-24 21:00 | 2020-07-24 21:30 | 0.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 6.17 | 10249 | 10249 | 0 | P/U DRILL PIPE F/9,660' T/9,851'. PROPER DISPLACEMENTS WHILE TRIPPING IN HOLE.
DIETZ OL UNIT 3H | 9 | 2020-07-24 21:30 | 2020-07-24 22:00 | 0.5 | P | INTHLCSG | RIGMT | LVDRK | LEVEL DERRICK | 6.19 | 10249 | 10249 | 0 | LEVEL DERRICK
DIETZ OL UNIT 3H | 9 | 2020-07-24 22:00 | 2020-07-24 22:30 | 0.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 6.21 | 10249 | 10249 | 0 | P/U DRILL PIPE F/9,851' T/10,131'. PROPER DISPLACEMENTS WHILE TRIPPING IN HOLE.
DIETZ OL UNIT 3H | 9 | 2020-07-24 22:30 | 2020-07-24 23:00 | 0.5 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 6.23 | 10249 | 10259 | 20 | TAG CEMENT @ 10,131'. DRILL OUT FLOAT EQUIPMENT AND 10' NEW FORMATION. GPM-256, PP-2,300 PSI, RPM-30, TQ-(9-11K), MW-9.2
DIETZ OL UNIT 3H | 9 | 2020-07-24 23:00 | 2020-07-24 23:30 | 0.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.25 | 10259 | 10259 | 0 | CIRCULATE BOTTOMS UP. GPM-256, PP-2150, RPM-30. CIRCULATE 9.2 MW AROUND.
DIETZ OL UNIT 3H | 9 | 2020-07-24 23:30 | 2020-07-25 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.27 | 10259 | 10259 | 0 | PERFORMED F.I.T @ 10,239’ MD 10,029’ W/9.2 PPG T/2050 PSI EMW = 13 PPG
DIETZ OL UNIT 3H | 9 | 2020-07-25 | 2020-07-25 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.27 | 10259 | 10259 |  | MILESTONE_START CURVE SECTION ON 7/25/20 @ 00:00 HRS
DIETZ OL UNIT 3H | 9 | 2020-07-25 | 2020-07-25 05:00 | 5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.48 | 10259 | 10516 | 51.4 | S/D (257' IN 5.08 HRS @ 52 FPH) WOB-15/25K, SPM-60/60, GPM-385, MRPM-262, SPP-3650/4050 PSI, DIFF-200/400 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', NO LOSSES SLIDE DEPTHS: F/10,259' T/10,314', TF-HS, 0009-0107, 58 MIN F/10,341' T/10,381', TF-HS, 0137-0225, 48 MIN F/10,424' T/10,586', TF-HS, 0250-0600, 190 MIN
DIETZ OL UNIT 3H | 9 | 2020-07-25 05:00 | 2020-07-25 06:00 | 1 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.52 | 10516 | 10586 | 70 | R/D (70' IN .92 HRS @ 76 FPH) WOB-15/20K, RPM-30, TRQ-10/13K, SPM-60/60, GPM-385, MRPM-262, SPP-3650/4650 PSI, DIFF-800/1000 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', NO LOSSES
DIETZ OL UNIT 3H | 10 | 2020-07-25 06:00 | 2020-07-25 14:30 | 8.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.88 | 10586 | 11009 | 49.8 | S/D (423' IN 8.43 HRS @ 50 FPH) WOB-15/25K, SPM-60/60, GPM-385, MRPM-262, SPP-3650/4050 PSI, DIFF-200/400 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', NO LOSSES SLIDE DEPTHS: SLD F/10586 T/10612 HS 0600-0601 (1MINS) SLD F/10644 T/10708 HS 0630-0730 (1HR) SLD F/10708 T/10802 HS 0730-0930 (2HR) SLD F/10802 T/10852 HS 0935-1030 (65MINS) SLD F/10857 T/10895 HS 1040-1120 (40MINS) SLD F/10900 T/10933 HS 1125-1210 (45MINS) SLD F/10960 T/10991 HS 1230-1310 (40MINS) SLD F/11058 T/11073 HS 1340-1410 (30 MINS) SLD F/11134 T/11181 HS 1440-1540 (1HR) SLD F/11181 T/11206 HS 1545-1630 (45MINS)
DIETZ OL UNIT 3H | 10 | 2020-07-25 14:30 | 2020-07-25 16:30 | 2 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.96 | 11009 | 11206 | 98.5 | R/D (197' IN 2.07 HRS @ 95 FPH) WOB-15/20K, RPM-30, TRQ-10/13K, SPM-60/60, GPM-385, MRPM-262, SPP-3650/4650 PSI, DIFF-800/1000 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', NO LOSSES LAND CURVE SECTION ON 7/25/2020 @ 16:30 (11,206' MD / 10,512' TVD)
DIETZ OL UNIT 3H | 10 | 2020-07-25 16:30 | 2020-07-25 16:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.96 | 11206 | 11206 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 7/25/2020 @ 16:30
DIETZ OL UNIT 3H | 10 | 2020-07-25 16:30 | 2020-07-25 23:00 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.23 | 11206 | 12234 | 158.2 | R/D (1028' IN 6.45 HRS @ 159 FPH) WOB-20/25K, RPM-70, TRQ-14/16K, SPM-60/60, GPM-385, MRPM-262, SPP-3550/4750 PSI, DIFF-1000/1200 PSI, CP-0 PSI, CHOKEs-100% / 50%, FLARE-20-25', NO LOSSES DURING CONNECTION @ 11,843' CASING PRESSURE BUILT T0 452 PSI. CASING PRESSURE BUILDING TO 100-150 PSI ON CONNECTIONS.
DIETZ OL UNIT 3H | 10 | 2020-07-25 16:30 | 2020-07-25 16:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.96 | 11206 | 11206 |  | MILESTONE_LAND/END CURVE SECTION ON 7/25/2020 @ 16:30
DIETZ OL UNIT 3H | 10 | 2020-07-25 23:00 | 2020-07-26 03:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.4 | 12234 | 12342 | 27 | S/D (108' IN 4.05 HRS @ 26 FPH) WOB-15/25K, SPM-60/60, GPM-385, MRPM-262, SPP-3650/4050 PSI, DIFF-200/400 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', NO LOSSES SLIDE DEPTHS: S.DRL F/11380' T/11409' @ 150R, 1805-1916, 71MIN S.DRL F/11475' T/11495' @ 180, 1743-2032, 49MIN S.DRL F/11656' T/11688' @ 180, 2125-2229, 64MIN S.DRL F/11850' T/11877' @130L 2326-0025, 59MIN
DIETZ OL UNIT 3H | 10 | 2020-07-26 03:00 | 2020-07-26 04:00 | 1 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.44 | 12342 | 12342 | 0 | LOST FULL RETURNS @ 12,342'. PICKED UP OFF BOTTOM, SLOWED PUMP T/160 GPM. LOST TOTAL 150 BBLS OBM. SWAPPED OVER TO WATER.
DIETZ OL UNIT 3H | 10 | 2020-07-26 04:00 | 2020-07-26 05:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.48 | 12342 | 12412 | 70 | ROTATE FROM F/12,342' T/12,412'. (71'/HR) DRILLING WITH WATER. GPM-337, PP-1050/1400, DP-350, WOB-(5-10), RPM-70, TQ-10/14K
DIETZ OL UNIT 3H | 10 | 2020-07-26 05:00 | 2020-07-26 06:00 | 1 | U | PRDHLLT | LOG | MWD | MWD | 7.52 | 12412 | 12412 | 0 | ATTEMPT TO PUMP UP SURVEY. MWD UNABLE TO CYCLE OFF DUE TO FLUID DRAINAGE THROUGH DRILL PIPE. PREP TO POOH AND PICK UP RESTRICTOR SUB.
DIETZ OL UNIT 3H | 11 | 2020-07-26 06:00 | 2020-07-26 06:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.54 | 12412 | 12412 | 0 | CIRCULATE @ 292 GPM WHILE PREPARING TO POOH. TRANSFER KILL MUD TO PIT 7 AND LINE UP ON KILL LINE.
DIETZ OL UNIT 3H | 11 | 2020-07-26 06:30 | 2020-07-26 12:30 | 6 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.79 | 12412 | 12412 | 0 | STRIP OUT OF HOLE F/12,412' T/3,216' TO PICK UP RESTRICTOR SUB. PUMP CALCULATED STROKES FOR DISPACEMENT EVERY STAND. CASING PSI-0. HOLE TIGHT @ 11,643'. (ST-80 SPINNER RIGHT TRANSMISSION NOT FUNCTIONING- USING CHAIN TONGS TO BACK OUT DRILL PIPE.)
DIETZ OL UNIT 3H | 11 | 2020-07-26 12:30 | 2020-07-26 13:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 7.81 | 12412 | 12412 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE. PERFORM FLOW CHECK-NO FLOW.
DIETZ OL UNIT 3H | 11 | 2020-07-26 13:00 | 2020-07-26 14:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.88 | 12412 | 12412 | 0 | POOH F/3,216' T/2,625'. PUMP CALCUATED STROKES FOR DISPLACEMENT EVERY STAND. NO RETURNS (ST-80 SPINNER RIGHT TRANSMISSION NOT FUNCTIONING- USING CHAIN TONGS TO BACK OUT DRILL PIPE.)
DIETZ OL UNIT 3H | 11 | 2020-07-26 14:30 | 2020-07-26 15:30 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.92 | 12412 | 12412 | 0 | SERVICE ST-80. C/O BAD TRANSMISSION
DIETZ OL UNIT 3H | 11 | 2020-07-26 15:30 | 2020-07-26 17:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.98 | 12412 | 12412 | 0 | POOH F/2,625' T/BHA. PUMP CALCULATED STROKES FOR DISPLACEMENT EVERY STAND. NO RETURNS
DIETZ OL UNIT 3H | 11 | 2020-07-26 17:00 | 2020-07-26 19:00 | 2 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 8.06 | 12412 | 12412 | 0 | REMOVE MWD, DRAIN BIT, L/D MUD MOTOR AND P/U NEW ASSY AS FOLLOWS. 6.75" ULTERRA RPS613 SER 50597: JETS (6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.35' BIT TO BEND 5-3/8" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, FLOAT SUB W/RESTRICTOR JETTED WITH 16/32", 5" UBHO, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-73'. BIT TO GAMMA-63', TEST MWD (TEST GOOD).
DIETZ OL UNIT 3H | 11 | 2020-07-26 19:00 | 2020-07-26 22:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.19 | 12412 | 12412 | 0 | TRIP IN HOLE F/BHA T/2748'. P/U AGITATOR AFTER STAND 27. PSI BEFORE AGITATOR- 620 PSI. PSI AFTER AGITATOR-400 PSI.
DIETZ OL UNIT 3H | 11 | 2020-07-26 22:00 | 2020-07-26 22:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 8.21 | 12412 | 12412 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
DIETZ OL UNIT 3H | 11 | 2020-07-26 22:30 | 2020-07-27 01:30 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.33 | 12412 | 12412 | 0 | TRIP IN HOLE F/2,748' T/10,521'. NO RETURNS.
DIETZ OL UNIT 3H | 11 | 2020-07-27 01:30 | 2020-07-27 02:30 | 1 | U | PRDHLLT | LOG | MWD | MWD | 8.38 | 12412 | 12412 | 0 | FILL PIPE AND TEST MWD. MWD PULSING BUT UNABLE TO SYNC. DECISION WAS MADE TO RIH TO LP AND TEST AGAIN.
DIETZ OL UNIT 3H | 11 | 2020-07-27 02:30 | 2020-07-27 03:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.4 | 12412 | 12412 | 0 | TRIP IN HOLE F/10,521' T/12,342'
DIETZ OL UNIT 3H | 11 | 2020-07-27 03:00 | 2020-07-27 04:00 | 1 | U | PRDHLLT | LOG | MWD | MWD | 8.44 | 12412 | 12412 | 0 | FILL PIPE AND RE-LOG F/12,342' T/12,412'
DIETZ OL UNIT 3H | 11 | 2020-07-27 04:00 | 2020-07-27 04:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.46 | 12412 | 12425 | 26 | R/D (13' IN .5 HRS @ 26 FPH) WOB-15/20K, RPM-80, TRQ-18/19K, SPM-0/105, GPM-337, MRPM-229, SPP-3650/4650 PSI, DIFF-800/1000 PSI AT 12,352' (TOOL DEPTH) OBSERVED GAMMA SPIKE(GC-186) DRILLING WITH WATER. CASING PSI-(500-800)
DIETZ OL UNIT 3H | 11 | 2020-07-27 04:30 | 2020-07-27 05:00 | 0.5 | P | PRDHLLT | WCTRL |  | KILL WELL | 8.48 | 12425 | 12425 | 0 | CASING PRESSURE ROSE TO 852 PSI. PICKED UP OFF BOTTOM AND PUMP 130 BBLS 13PPG OBM DOWN BACK SIDE.
DIETZ OL UNIT 3H | 11 | 2020-07-27 05:00 | 2020-07-27 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.52 | 12425 | 12447 | 22 | S/D (22' IN 1 HRS @ 22 FPH) WOB-10/20K, SPM-0/105, GPM-337, MRPM-229, SPP-3650/4300 PSI, DIFF-500/700 PSI. DRILLING WITH WATER. CASING PSI-0 SLIDE DEPTHS: F/12425' T/12,436', TF-180, 0420-0449, 29 MIN F/12,436' T/12,447', TF-180, 0530-0600, 30 MIN
DIETZ OL UNIT 3H | 12 | 2020-07-27 06:00 | 2020-07-27 09:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.65 | 12447 | 12779 | 110.7 | R/D (332' IN 3.25 HRS @ 102 FPH) WOB-25/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-3650/4650 PSI, DIFF-800/1000 PSI CSG PSI BUILT TO 264 PSI. PUMP 50 BBLS 13.5 PPG OBM DOWN BACKSIDE
DIETZ OL UNIT 3H | 12 | 2020-07-27 09:00 | 2020-07-27 10:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.69 | 12779 | 12796 | 17 | S/D (17' IN 1 HRS @ 17 FPH) WOB-20/30K, SPM-0/110, GPM-353, MRPM-240, SPP-4550/5250 PSI, DIFF-500/700 PSI. DRILLING WITH WATER. CASING PSI-180 SLIDE DEPTHS: F/12715' T/12732', TF-180, 0830-0915, 45 MIN
DIETZ OL UNIT 3H | 12 | 2020-07-27 10:00 | 2020-07-27 11:30 | 1.5 | U | PRDHLLT | LOG | MWD | MWD | 8.75 | 12796 | 12796 | 0 | TROUBLESHOOT MWD TOOL. RE-LOG F/12,745' T/12,796'(LOGS DID NOT CORRELATE WITH PREVIOUS READINGS) GAMMA COUNT DISPLAYING ABNORMAL NUMBERS.
DIETZ OL UNIT 3H | 12 | 2020-07-27 11:30 | 2020-07-27 12:00 | 0.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.77 | 12796 | 12796 | 0 | BACKREAM F/12,796' T/12,315'. GPM-288, PP-3900, RPM-50, TQ-(8-11K)
DIETZ OL UNIT 3H | 12 | 2020-07-27 12:00 | 2020-07-27 16:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.94 | 12796 | 12796 | 0 | POOH F/12,315' T/3003. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM. CASING PSI-0
DIETZ OL UNIT 3H | 12 | 2020-07-27 16:00 | 2020-07-27 16:30 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 8.96 | 12796 | 12796 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE. PUMP 15 BBL 14.4 PPG OBM ON BACKSIDE.
DIETZ OL UNIT 3H | 12 | 2020-07-27 16:30 | 2020-07-27 17:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9 | 12796 | 12796 | 0 | POOH F/3,003' T/BHA. PUMP CALCULATED STROKES 9.0 PPG OBM ON BACKSIDE.
DIETZ OL UNIT 3H | 12 | 2020-07-27 17:30 | 2020-07-27 19:00 | 1.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.06 | 12796 | 12796 | 0 | RACK BACK MONEL, REMOVE MWD, INSPECT MOTOR AND BIT, CHANGE JET IN RESTRICTOR SUB TO 20/32", INSTALL MWD, AND PICK UP MONEL.
DIETZ OL UNIT 3H | 12 | 2020-07-27 19:00 | 2020-07-27 21:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.15 | 12796 | 12796 | 0 | TRIP IN HOLE F/BHA T/2,748' INSTALL AGITATOR AFTER STAND 27. PSI BEFORE-580. PSI AFTER-617. NO RETURNS
DIETZ OL UNIT 3H | 12 | 2020-07-27 21:00 | 2020-07-27 21:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.17 | 12796 | 12796 | 0 | RIG SERVICE
DIETZ OL UNIT 3H | 12 | 2020-07-27 21:30 | 2020-07-28 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.27 | 12796 | 12796 | 0 | TRIP IN HOLE F/2,748' T/10,520'. NO RETURNS
DIETZ OL UNIT 3H | 12 | 2020-07-28 | 2020-07-28 01:00 | 1 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.31 | 12796 | 12796 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD. FLOW CHECK WELL-NO FLOW.
DIETZ OL UNIT 3H | 12 | 2020-07-28 01:00 | 2020-07-28 02:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.35 | 12796 | 12796 | 0 | TRIP IN HOLE F/10,520' T/12,704'. NO RETURNS
DIETZ OL UNIT 3H | 12 | 2020-07-28 02:00 | 2020-07-28 03:00 | 1 | U | PRDHLLT | LOG | MWD | MWD | 9.4 | 12796 | 12796 | 0 | RE-LOG F/12,704' T/12,796'. RE-LOG SUCCESSFUL. MWD WORKING PROPERLY. CASING PRESSURE BUILT TO 722 PSI WHILE RE-LOGGING.
DIETZ OL UNIT 3H | 12 | 2020-07-28 03:00 | 2020-07-28 03:30 | 0.5 | P | PRDHLLT | WCTRL |  | KILL WELL | 9.42 | 12796 | 12796 | 0 | PUMP 150 BBLS 14.2 PPG OBM DOWN BACKSIDE. PUMP @ 200 GPM.
DIETZ OL UNIT 3H | 12 | 2020-07-28 03:30 | 2020-07-28 06:00 | 2.5 | U | PRDHLLT | LOG | MWD | MWD | 9.52 | 12796 | 12805 | 3.6 | ATTEMPT TO SYNC WITH MWD MULTIPLE TIMES. MWD NOT READING CORRECT DIP AND AZIMUTH. TROUBLESHOOT MWD AND CHANGE PULSE WIDTH CONFIGURATION-NO SUCCESS. ROTATED 10' AND ATTEMPTED SVY-NO SUCCESS. PICKED UP 1 STAND TO LAST GOOD SURVEY AND ATTEMPTED SVY-NO SUCCESS.
DIETZ OL UNIT 3H | 13 | 2020-07-28 06:00 | 2020-07-28 06:30 | 0.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.54 | 12805 | 12805 | 0 | BACKREAM F/12,805' T/12,315'. GPM-288, PP-3000, RPM-50, TQ-(8-11K) FOR MWD FAILURE
DIETZ OL UNIT 3H | 13 | 2020-07-28 06:30 | 2020-07-28 11:00 | 4.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.73 | 12805 | 12805 | 0 | POOH F/12,315' T/3,003. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM. CASING PSI-0
DIETZ OL UNIT 3H | 13 | 2020-07-28 11:00 | 2020-07-28 11:30 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 9.75 | 12805 | 12805 | 0 | REMOVE ROTATING HEAD / INSTALL TRIP NIPPLE
DIETZ OL UNIT 3H | 13 | 2020-07-28 11:30 | 2020-07-28 12:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.77 | 12805 | 12805 | 0 | POOH TO CHANGE OUT MWD TOOL, F/3,003' T/BHA. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM. NO RETURNS
DIETZ OL UNIT 3H | 13 | 2020-07-28 12:00 | 2020-07-28 12:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.79 | 12805 | 12805 | 0 | PULL MWD, INSPECT BIT AND MUD MOTOR, BOTH GOOD. INSTALL MWD AND TEST, GOOD TEST.
DIETZ OL UNIT 3H | 13 | 2020-07-28 12:30 | 2020-07-28 14:30 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.88 | 12805 | 12805 | 0 | TRIP IN HOLE TO 3000'. NO RETURNS
DIETZ OL UNIT 3H | 13 | 2020-07-28 14:30 | 2020-07-28 15:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.9 | 12805 | 12805 | 0 | INSTALL RCH BEARING
DIETZ OL UNIT 3H | 13 | 2020-07-28 15:00 | 2020-07-28 15:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.92 | 12805 | 12805 | 0 | FILL PIPE, TEST MWD-GOOD
DIETZ OL UNIT 3H | 13 | 2020-07-28 15:30 | 2020-07-28 17:00 | 1.5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 9.98 | 12805 | 12805 | 0 | CUT AND SLIP 72' OF DRLG LINE
DIETZ OL UNIT 3H | 13 | 2020-07-28 17:00 | 2020-07-28 17:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10 | 12805 | 12805 | 0 | RIG SERVICE
DIETZ OL UNIT 3H | 13 | 2020-07-28 17:30 | 2020-07-28 18:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.02 | 12805 | 12805 | 0 | CLEAN RIG FLOOR OF OBM AND DRLG LINE BEFORE TRIP IN HOLE
DIETZ OL UNIT 3H | 13 | 2020-07-28 18:00 | 2020-07-28 21:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.15 | 12805 | 12805 | 0 | RIH F/3,000' T/10,520'. WELL SHUT IN ON ORBIT VALVE. CASING PSI-0.
DIETZ OL UNIT 3H | 13 | 2020-07-28 21:00 | 2020-07-28 22:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.19 | 12805 | 12805 | 0 | PUMP 50 BBLS 15 PPG KILL MUD DOWN ANNULUS TO INDUCE LOSSES.
DIETZ OL UNIT 3H | 13 | 2020-07-28 22:00 | 2020-07-28 23:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.23 | 12805 | 12805 | 0 | RIH T/10,520' T/12,805'. WELL SHUT IN ON ORBIT VALVE. CASING PSI-0.
DIETZ OL UNIT 3H | 13 | 2020-07-28 23:00 | 2020-07-29 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.27 | 12805 | 12821 | 16 | SLIDE F/12,805' T/12,821' (16' IN 1 HR @ 16'/HR) NOTE: PICKED UP AFTER FINISHING SLIDE AND MUD MOTOR STALLED OUT CAUSING 2" PRV PIN TO SHEAR. CONTINUED PICKING UP ON PIPE AND BROKE PIPE FREE @ 320K. AFTER REPLACING SHEAR PIN, ENGAGED #1 MP AND DRILL PIPE PRESSURE IMMEDIATELY CLIMBED TO 6,700 PSI. BLED OFF PSI AND MADE 3 ATTEMPTS TO CIRCULATE WITH NO SUCCESS. CASING PSI-0
DIETZ OL UNIT 3H | 13 | 2020-07-29 | 2020-07-29 05:00 | 5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.48 | 12821 | 12821 | 0 | POOH F/12,821' T/4,835. (UNABLE TO CIRCULATE THROUGH DRILL PIPE). FILLING HOLE WITH CALCULATED STROKES 15.0 PPG OBM T/10,200'. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM F/10,200' T/BHA. CASING PSI-0
DIETZ OL UNIT 3H | 13 | 2020-07-29 05:00 | 2020-07-29 05:30 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.5 | 12821 | 12821 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
DIETZ OL UNIT 3H | 13 | 2020-07-29 05:30 | 2020-07-29 06:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.52 | 12821 | 12821 | 0 | POOH F/4,835' T/3,800'. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM.
DIETZ OL UNIT 3H | 14 | 2020-07-29 06:00 | 2020-07-29 08:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.6 | 12821 | 12821 | 0 | POOH F/3,800 T/BHA. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM.
DIETZ OL UNIT 3H | 14 | 2020-07-29 08:00 | 2020-07-29 10:30 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.71 | 12821 | 12821 | 0 | REMOVE MWD, DRAIN BIT, L/D MUD MOTOR. (MUD MOTOR HAD SEPARATED BETWEEN THE LOWER END AND THE FIXED BEND HOUSING BUT WAS STILL ATTACHED BY THE SAFETY LATCH) P/U NEW ASSY AS FOLLOWS. 6.75" HALLIBURTON GTRD64M SER 1138553: JETS (6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.45' BIT TO BEND 5-3/8" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, FLOAT SUB W/RESTRICTOR JETTED WITH 20/32", 5" UBHO, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-73'. BIT TO GAMMA-63'
DIETZ OL UNIT 3H | 14 | 2020-07-29 10:30 | 2020-07-29 11:00 | 0.5 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 10.73 | 12821 | 12821 | 0 | ATTEMPT TO TEST MWD. MUD PUMPS CAVITATING. CLEAN MUD PUMP SUCTIONS. FOUND ROCKS AND SAND IN MUD PUMP SUCTIONS.
DIETZ OL UNIT 3H | 14 | 2020-07-29 11:00 | 2020-07-29 12:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.79 | 12821 | 12821 | 0 | TEST MWD-GOOD. PICK UP, M/U BIT, P/U MONEL AND RIH TO 2860'. NO RETURNS WHILE TRIPPING IN HOLE.
DIETZ OL UNIT 3H | 14 | 2020-07-29 12:30 | 2020-07-29 13:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.83 | 12821 | 12821 | 0 | CHANGE OUT AGITATOR, GPM-224, PP BEFORE - 235 - PP AFTER NEW AGITATOR INSTALLED - 311
DIETZ OL UNIT 3H | 14 | 2020-07-29 13:30 | 2020-07-29 14:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.88 | 12821 | 12821 | 0 | TRIP IN HOLE TO 6,021'. NO RETURNS WHILE TRIPPING IN HOLE.
DIETZ OL UNIT 3H | 14 | 2020-07-29 14:30 | 2020-07-29 15:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.9 | 12821 | 12821 | 0 | INSTALL ROTATING HEAD.
DIETZ OL UNIT 3H | 14 | 2020-07-29 15:00 | 2020-07-29 16:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.94 | 12821 | 12821 | 0 | RIG SERVICE
DIETZ OL UNIT 3H | 14 | 2020-07-29 16:00 | 2020-07-29 20:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.1 | 12821 | 12821 | 0 | TRIP IN HOLE TO 12,821'. NO RETURNS WHILE TRIPPING IN HOLE.
DIETZ OL UNIT 3H | 14 | 2020-07-29 20:00 | 2020-07-30 04:00 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.44 | 12821 | 13473 | 81.5 | R/D (652' IN 8 HRS @ 81 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-3600/4600 PSI, DIFF-800/100 PSI. CASING PSI 800-950
DIETZ OL UNIT 3H | 14 | 2020-07-30 04:00 | 2020-07-30 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.52 | 13473 | 13527 | 27 | S/D (54' IN 2 HRS @ 27 FPH) WOB-20/30K, SPM-0/110, GPM-353, MRPM-240, SPP-3600/4000 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-(800-950) SLIDE DEPTHS: S.DRL F/12929'T/12950' @ HS 2117-2200, 43MIN S.DRL F/12988' T/13000' @ HS 2246-2318, 32MIN S.DRL F/13032' T/13047' @ HS 0013-0045, 32MIN S.DRL F/13278' T/13284' @ 180 0330-0343, 13MIN
DIETZ OL UNIT 3H | 15 | 2020-07-30 06:00 | 2020-07-30 08:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.6 | 13527 | 13635 | 54 | R/D (108' IN 2 HRS @ 54 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-3600/4600 PSI, DIFF-800/1000 PSI. DRILLING WITH WATER CASING PSI 800-950
DIETZ OL UNIT 3H | 15 | 2020-07-30 08:00 | 2020-07-30 09:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.65 | 13635 | 13645 | 10 | S/D (10' IN 1 HRS @ 10 FPH) WOB-20/30K, SPM-0/105, GPM-337, MRPM-229, SPP-3600/4000 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-(900-1000) SLIDE DEPTHS:
DIETZ OL UNIT 3H | 15 | 2020-07-30 09:00 | 2020-07-30 10:00 | 1 | P | PRDHLLT | WCTRL |  | KILL WELL | 11.69 | 13645 | 13645 | 0 | SICP-916 PSI. PUMP 75 BBLS 17.5 PPG OBM @ 64 GPM. CASING PSI BROKE OVER @ 2,380 PSI. AS CASING PSI REDUCED TO BELOW 1000 PSI, GRADUALLY INCREASED PUMPS T/176 GPM. CHASED 17.5 PPG OBM WITH 15 BBLS 13.5 PPG OBM AND REDUCED CSG PSI T/100 PSI.
DIETZ OL UNIT 3H | 15 | 2020-07-30 10:00 | 2020-07-30 15:00 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.9 | 13645 | 14106 | 92.2 | R/D (461' IN 5.2 HRS @ 89 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-3600/4600 PSI, DIFF-800/1000 PSI. DRILLING WITH WATER CASING PSI-0
DIETZ OL UNIT 3H | 15 | 2020-07-30 15:00 | 2020-07-30 17:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.98 | 14106 | 14133 | 13.5 | S/D (27' IN 1.8 HRS @ 15 FPH) WOB-20/30K, SPM-0/105, GPM-337, MRPM-229, SPP-3600/4000 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-0 SLIDE DEPTHS: SLD F/13790 T/13805 160R 1130-1230 (1HR) SLD F/13858 T/13870 180 1312-1400 (48MINS)
DIETZ OL UNIT 3H | 15 | 2020-07-30 17:00 | 2020-07-30 17:30 | 0.5 | P | PRDHLLT | LOG | MWD | MWD | 12 | 14133 | 14133 | 0 | TROUBLESHOOTING MWD-RECYCLE MUD PUMPS MULTIPLE TIMES.
DIETZ OL UNIT 3H | 15 | 2020-07-30 17:30 | 2020-07-31 03:00 | 9.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.4 | 14133 | 15034 | 94.8 | R/D (901' IN 9.55 HRS @ 94 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/107, GPM-343, MRPM-233, SPP-4100/4900 PSI, DIFF-700/800 PSI. DRILLING WITH WATER CASING PSI-0 OBSERVED HIGH GAMMA COUNT (~235 UNITS) FROM 15,000 - 060' AND EFFORTS WERE MADE TO SLIDE DOWN AWAY FROM THE A MARKER.
DIETZ OL UNIT 3H | 15 | 2020-07-31 03:00 | 2020-07-31 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.52 | 15034 | 15078 | 14.7 | S/D (44' IN 2.95 HRS @ 15 FPH) WOB-20/30K, SPM-0/107, GPM-343, MRPM-233, SPP-4100/4400 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-0 SLIDE DEPTHS: S.DRIL F/14230' T/14237' @ 130R 1845-1910, 25MIN S.DRL F/14455' T/14465' @ 45R 2117-2148, 31MIN S.DRL F/14653' T/14659' @ 180 2354-0015, 21MIN S.DRL F/14820' T/14826' @ 145R 0157-0214, 17MIN S.DRL F/14982' T/14997' @ 140R 0354-0517, 83MIN
DIETZ OL UNIT 3H | 16 | 2020-07-31 06:00 | 2020-07-31 12:30 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.79 | 15078 | 15663 | 90 | R/D (585' IN 6.33 HRS @ 92 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-4100/4900 PSI, DIFF-700/800 PSI. DRILLING WITH WATER CASING PSI-0
DIETZ OL UNIT 3H | 16 | 2020-07-31 12:30 | 2020-07-31 17:00 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.98 | 15663 | 15739 | 16.9 | S/D (76' IN 4.67 HRS @ 16 FPH) WOB-20/30K, SPM-0/105, GPM-337, MRPM-229, SPP-4100/4500 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-(0) SLIDE DEPTHS: SLD F/15078 T/15110 180 0600-0800 (2HR) SLD F/15267 T/15289 HS 1000-1130 (1HR30MIN) SLD F/15362 T/15374 HS 1230-1310 (40MIN) SLD F/15645 T/15655 140R 1530-1600 (30MIN)
DIETZ OL UNIT 3H | 16 | 2020-07-31 17:00 | 2020-07-31 17:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13 | 15739 | 15739 | 0 | RIG SERVICE
DIETZ OL UNIT 3H | 16 | 2020-07-31 17:30 | 2020-07-31 22:00 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 13.19 | 15739 | 16180 | 98 | R/D (441' IN 4.68 HRS @ 94 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-4100/4900 PSI, DIFF-700/800 PSI. DRILLING WITH WATER CASING PSI-0
DIETZ OL UNIT 3H | 16 | 2020-07-31 22:00 | 2020-08-01 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 13.27 | 16180 | 16214 | 17 | S/D (34' IN 1.82 HRS @ 19 FPH) WOB-20/30K, SPM-0/105, GPM-337, MRPM-229, SPP-4100/4500 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-(0) SLIDE DEPTHS: S.DRL F/15890' T/15902' @ HS 1906-1947, 41MIN S.DRL F/15988' T/15994' @ HS 2039-2056, 17MIN S.DRIL F/16123' T/16139' @ 135R 2218-2309, 51MIN
DIETZ OL UNIT 3H | 16 | 2020-08-01 | 2020-08-01 01:00 | 1 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.31 | 16214 | 16214 | 0 | BEGAN LOSING PUMP PSI @ 16,205'. LOST 1,400 PSI @ 16,214'. TOP DRIVE STALLED OUT. WORK PIPE FREE. PUMP 30 BBL HIGH VIS SWEEP AND WORK STAND. INITIAL TQ-(16-19K) FINAL TQ- (11-13K), FINAL PP-2,700 PSI
DIETZ OL UNIT 3H | 16 | 2020-08-01 01:00 | 2020-08-01 03:30 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 13.42 | 16214 | 16395 | 72.4 | R/D (181' IN 2.28 HRS @ 79 FPH) WOB-20/30, RPM-70, TRQ-15/16K, SPM-0/105, GPM-337, MRPM-229, SPP-2900/3500 PSI, DIFF-400/500 PSI. DRILLING WITH WATER CASING PSI-0
DIETZ OL UNIT 3H | 16 | 2020-08-01 03:30 | 2020-08-01 06:00 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 13.52 | 16395 | 16465 | 28 | S/D (70' IN 2.72 HRS @ 26 FPH) WOB-20/30K, SPM-0/105, GPM-337, MRPM-229, SPP-2900/3200 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-(0) SLIDE DEPTHS: S.DRL F/16214' T/16238' @ 180 0116-0203, 47MIN S.DRL F/16307' T/16327' @ 180 0259-0329, 30MIN S.DRL F/16406' T/16432' @ HS 0421-0533, 72MIN
DIETZ OL UNIT 3H | 17 | 2020-08-01 06:00 | 2020-08-01 06:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.54 | 16465 | 16465 | 0 | SERVICED TOP DRIVE
DIETZ OL UNIT 3H | 17 | 2020-08-01 06:30 | 2020-08-01 16:30 | 10 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 13.96 | 16465 | 17781 | 131.6 | R/D (1316' IN 10 HRS @ 132 FPH) WOB-12/20, RPM-70, TRQ-15/18K, SPM-0/105, GPM-337, MRPM-229, SPP-3200/3700 PSI, DIFF-400/500 PSI. DRILLING WITH WATER CASING PSI-0
DIETZ OL UNIT 3H | 17 | 2020-08-01 16:30 | 2020-08-01 19:30 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.08 | 17781 | 17841 | 20 | S/D (60' IN 3 HRS @ 20 FPH) WOB-20/30K, SPM-0/105, GPM-337, MRPM-229, SPP-2900/3200 PSI, DIFF-300/400 PSI. DRILLING WITH WATER. CASING PSI-(0) SLIDE DEPTHS: 16485-16,865' TF-180 20' IN 60 MINS 17161'-17181' TF-180 20' IN 65 MINS 17355'-17375' TF-14L 20' IN 55 MINS
DIETZ OL UNIT 3H | 17 | 2020-08-01 19:30 | 2020-08-01 19:30 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 14.08 | 17841 | 17841 |  | MILESTONE_TD WELL ON 8/01/2020 @ 19:30
DIETZ OL UNIT 3H | 17 | 2020-08-01 19:30 | 2020-08-01 21:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.15 | 17841 | 17841 | 0 | PERFORMED CLEAN UP CYCLE @ 17,841' PUMPING 3-20 BBL WEIGHTED LCM SWEEPS
DIETZ OL UNIT 3H | 17 | 2020-08-01 21:00 | 2020-08-02 04:00 | 7 | P | PRDHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 14.44 | 17841 | 17841 | 0 | W/R F/17,841' - T/12,352' RPM-70, TRQ-15/18K, SPM-0/105, GPM-337, MRPM-229, SPP-3700 PSI, CP-0 PSI
DIETZ OL UNIT 3H | 17 | 2020-08-02 04:00 | 2020-08-02 06:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.52 | 17841 | 17841 | 0 | POOH F/12,352' T/8,500'. FILLING HOLE WITH CALCULATED STROKES 10.5 PPG OBM.
DIETZ OL UNIT 3H | 18 | 2020-08-02 06:00 | 2020-08-02 08:00 | 2 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 14.6 | 17841 | 17841 | 0 | POOH F/8,500' T/3,334'. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM
DIETZ OL UNIT 3H | 18 | 2020-08-02 08:00 | 2020-08-02 08:30 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 14.63 | 17841 | 17841 | 0 | PULL ROTATING HEAD AND INSTALL TRIP NIPPLE
DIETZ OL UNIT 3H | 18 | 2020-08-02 08:30 | 2020-08-02 09:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 14.67 | 17841 | 17841 | 0 | POOH F/3,334' T/BHA. FILLING HOLE WITH CALCULATED STROKES 9.0 PPG OBM
DIETZ OL UNIT 3H | 18 | 2020-08-02 09:30 | 2020-08-02 11:00 | 1.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 14.73 | 17841 | 17841 | 0 | REMOVE MWD, DRAIN MUD MOTOR, BREAK BIT, AND L/D DIRECTIONAL TOOLS.
DIETZ OL UNIT 3H | 18 | 2020-08-02 11:00 | 2020-08-02 11:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 14.75 | 17841 | 17841 | 0 | PULL WEAR BUSHING, REMOVE RIG ELEVATORS, AND CLEAN/ORGANIZE RIG FLOOR.
DIETZ OL UNIT 3H | 18 | 2020-08-02 11:30 | 2020-08-02 13:30 | 2 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 14.83 | 17841 | 17841 | 0 | HOLD PJSM, R/U EXPRESS CASING TOOLS AND EQUIPMENT, RIG UP SAFETY VALVE
DIETZ OL UNIT 3H | 18 | 2020-08-02 13:30 | 2020-08-02 21:30 | 8 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.17 | 17841 | 17841 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY SMLS WEDGE 625 CASING W/CENTRALIZERS IN MIDDLE OF JTS., 1 INNOVEX DV FLOAT COLLAR, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY SMLS WEDGE 625 PRODUCTION CASING T/ 8,346', FILLING PIPE ON THE FLY, SOLID BODY CENTALIZERS EVERY 4TH JOINT T/10,129', MONITOR DISPLACEMENTS ON TRIP TANK, PROPER DISPLACEMENTS WHILE RUNNING CASING.
DIETZ OL UNIT 3H | 18 | 2020-08-02 21:30 | 2020-08-02 22:30 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.21 | 17841 | 17841 | 0 | FLOW CHECK, REMOVE TRIP NIPPLE / INSTALL ROT. HEAD
DIETZ OL UNIT 3H | 18 | 2020-08-02 22:30 | 2020-08-02 23:30 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 15.25 | 17841 | 17841 | 0 | SWAP OUT CRT AND CSG ELEVATORS FOR 5-1/2" CASING
DIETZ OL UNIT 3H | 18 | 2020-08-02 23:30 | 2020-08-03 05:00 | 5.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.48 | 17841 | 17841 | 0 | PICK UP CROSSOVER, M/U 1 JOINT 5.5" CSG, MARKER JT, AND RUN 5-1/2" 23# P110 ICY SMLS WEDGE 563 PRODUCTION CASING F/8,394' T/15,984'
DIETZ OL UNIT 3H | 18 | 2020-08-03 05:00 | 2020-08-03 06:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.52 | 17841 | 17841 | 0 | FILL CASING AND WORK PIPE THROUGH TIGHT SPOT @ 15,984. WORK PIPE FREE AND WORK PIPE T/16,003'. PP-600 PSI, GPM-321. RPM-40, INITIAL TQ-20K. FINAL TQ-12K
DIETZ OL UNIT 3H | 19 | 2020-08-03 06:00 | 2020-08-03 08:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.6 | 17841 | 17841 | 0 | REAM CASING F/16,003' T/16,559'. GPM-321, PP-700, RPM-30, TQ-15-18K
DIETZ OL UNIT 3H | 19 | 2020-08-03 08:00 | 2020-08-03 09:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.65 | 17841 | 17841 | 0 | RUN 5.5" CASING ON ELEVATORS F/16,559' T/17,551'
DIETZ OL UNIT 3H | 19 | 2020-08-03 09:00 | 2020-08-03 10:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.69 | 17841 | 17841 | 0 | REAM CASING F/17,551' T/17,841'. GPM-321, PP-700, RPM-30, TQ-(15-18K) TAG BOTTOM 20' IN ON JOINT. PICK UP T/350K AND BREAK OVER CASING T/250K. LAY DOWN 1 JOINT CASING. 5" CASING SHOE @ 17,816.2' TOP OF FLOAT COLLAR @ 17,718.33' TOP OF TOE SLEEVE VALVE @ 17,692.83 TOP OF X-OVER @ 9,467.51' TOP OF 5-1/2" MARKER JOINT ABOVE X-OVER @ 9,401.83'
DIETZ OL UNIT 3H | 19 | 2020-08-03 10:00 | 2020-08-03 10:30 | 0.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.71 | 17841 | 17841 | 0 | OPEN CHOKES AND PUMP CASING CAPACITY @ 321 GPM, PP-900. NO FLOW.
DIETZ OL UNIT 3H | 19 | 2020-08-03 10:30 | 2020-08-03 11:00 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 15.73 | 17841 | 17841 | 0 | RIG DOWN EXPRESS CRT INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP. SICP-0
DIETZ OL UNIT 3H | 19 | 2020-08-03 11:00 | 2020-08-03 14:00 | 3 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 15.85 | 17841 | 17841 | 0 | HELD PJSM, SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD, FLUSHED THROUGH & TESTED CEMENTING LINES T/8500 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: DROP BOTTOM PLUG, PUMPED @ 6 BPM 50 BBL 9.6 PPG WEIGHTED SPACER, 253 BBL 13.5 PPG 855 SK 1.66 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 348 BBLS (1ST 20BBLS SUGAR WATER) OF FRESH WATER WITH PLEXAID 300 & 15 G CHEMICALS @ 8 BPM, OBSERVED NO RETURNS. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 1200 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2100 PSI, HELD FOR 5 MIN, BLED BACK 2.5 BBLS. FLOATS HELD. PLUG DOWN @ 14:15 ON 8/3/2020. NO RETURNS DURING ENTIRE CEMENT JOB. SHUT PIPE RAMS AND MONITOR SICP-0 PSI
DIETZ OL UNIT 3H | 19 | 2020-08-03 14:00 | 2020-08-03 14:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.88 | 17841 | 17841 | 0 | RIG SERVICE
DIETZ OL UNIT 3H | 19 | 2020-08-03 14:30 | 2020-08-03 22:00 | 7.5 | P | PRDHLCSG | WAIT | WOC | WAIT ON CEMENT | 16.19 | 17841 | 17841 | 0 | WAIT ON CEMENT
DIETZ OL UNIT 3H | 19 | 2020-08-03 22:00 | 2020-08-04 00:30 | 2.5 | P | PRDHLCSG | WAIT | WOC | WAIT ON CEMENT | 16.29 | 17841 | 17841 | 0 | R/D CSG ELEVATORS AND R/U DP ELEVATORS. REMOVE CMT HEAD FROM CASING. INSTALL MOUSEHOLE AND MAKE UP DIRECTIONAL BHA IN PREPARATION OF PALO DURO 1H. (WHILE WAITING ON CEMENT)
DIETZ OL UNIT 3H | 19 | 2020-08-04 00:30 | 2020-08-04 02:00 | 1.5 | P | PRDHLCSG | WAIT | WOC | WAIT ON CEMENT | 16.35 | 17841 | 17841 | 0 | SLIP AND CUT DRILL LINE-10 WRAPS (WHILE WAITING ON CEMENT)
DIETZ OL UNIT 3H | 19 | 2020-08-04 02:00 | 2020-08-04 06:00 | 4 | P | PRDHLCSG | WAIT | WOC | WAIT ON CEMENT | 16.52 | 17841 | 17841 | 0 | R/D DP ELEVATORS, R/U CSG ELEVATORS, REMOVE MOUSEHOLE, AND GUTS FROM KILL LINE CHECK VALVE WHILE WAITING ON CEMENT-(SICP-0 PSI)
DIETZ OL UNIT 3H | 20 | 2020-08-04 06:00 | 2020-08-04 11:00 | 5 | P | PRDHLCSG | WAIT | WOC | WAIT ON CEMENT | 16.73 | 17841 | 17841 | 0 | WAIT ON CEMENT
DIETZ OL UNIT 3H | 20 | 2020-08-04 11:00 | 2020-08-04 12:00 | 1 | P | PRDHLCSG | WCTRL |  | KILL WELL | 16.77 | 17841 | 17841 | 0 | FILL ANNULUS WITH 32 BBLS 10.0 PPG OBM. (TOP OF FLUID COLUMN-1,939') PUMP 61 BBLS 10.0 PPG OBM @ 4 BPM. MAX CSG PSI-540 PSI. CSG PSI FELL TO ZERO WHEN PUMPS OFF. PUMP 21 BBLS 13.5 PPG OBM FOR MUD CAP. CSG PSI FELL TO ZERO WHEN PUMPS OFF.
DIETZ OL UNIT 3H | 20 | 2020-08-04 12:00 | 2020-08-04 15:00 | 3 | P | PRDHLCSG | CMT | REMCM | REMEDIAL CEMENT OPERATIONS | 16.9 | 17841 | 17841 | 0 | HOLD PJSM AND R/U CEMENT LINES TO KILL LINE. BUILD SPACER AND TEST LINES T/7,000 PSI. PUMP 30 BBLS 10 PPG WEIGHTED SPACER, FOLLOWED BY 220 BBLS 725 SK 1.7 YIELD 35/65 POZ-SM-CLASS H-MM LEAD CEMENT, PUMP 60 BBLS 255 SK 1.33 YIELD TYPE I/II TAIL CEMENT, PUMP 10 BBLS WEIGHTED SPACER BEHIND CEMENT, FOLLOWED BY 50 BBLS WATER W/BIOCIDE. MAX CSG PSI 1,280 PSI W/170 BBLS LEAD CMT PUMPED. CSG PRESSURE FELL TO ZERO WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC-3,000'
DIETZ OL UNIT 3H | 20 | 2020-08-04 15:00 | 2020-08-04 17:30 | 2.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 17 | 17841 | 17841 | 0 | RIG DOWN CEMENTERS
DIETZ OL UNIT 3H | 20 | 2020-08-04 17:30 | 2020-08-04 21:00 | 3.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 17.15 | 17841 | 17841 | 0 | NIPPLE DOWN BOP. INSTALL WRANGLER AND PICK UP BOP. SET CASING SLIPS WITH 200K, CUT CASING AND L/D CUT JOINT. POLISH CUT OFF JOINT IN BOWL.
DIETZ OL UNIT 3H | 20 | 2020-08-04 21:00 | 2020-08-05 | 3 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 17.27 | 17841 | 17841 | 0 | P/U JT OF DP & PACK-OFF, INSTALLED STREAM FLO PACKOFF (PULL TEST T/25K OVERPULL) & TEST SEALS T/ 5000 PSI. INSTALL WELL CAP AND RELEASE WELL ON 8/5/2020 @ 00:00
DIETZ OL UNIT 3H | 20 | 2020-08-05 | 2020-08-05 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 17.27 | 17841 | 17841 |  | MILESTONE_WELL RELEASE ON 8/5/2020 @ 00:00
DIETZ OL UNIT 3H | 20 | 2020-08-05 | 2020-08-05 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 17.27 | 17841 | 17841 |  | MILESTONE_RIG RELEASE ON 8/5/2020 @ 00:00
DIETZ OL UNIT 3H | 20 | 2020-08-05 | 2020-08-05 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 17.27 | 17841 | 17841 |  | MILESTONE_TURN OVER TO COMPLETION ON 8/5/2020 @ 00:00
FAT TIRE A 1H | 3 | 2020-12-08 06:00 | 2020-12-09 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 105 | 105 | 0 | CONTINUE WASHING RIG AND RIGGING DOWN, UNDRESS DERRICK, REMOVE CROWN, TOP AND MIDDLE SECTIONS OF DERRICK, LOAD AND MOVE MUD TANK, MUD PUMPS, GAS BUSTER, BOP WRANGLER, DIESEL TANK, PUMP PARTS HOUSE, SUITCASES, VFD AND GEN PACKAGE, REMOVE DS DOGHOUSE, REMOVE DERRICK FROM RIG FLOOR, REMOVE DS DOGHOUSE, REMOVE DERRICK FROM RIG FLOOR, REMOVED DRAWWORKS, CENTER STEEL, GRASSHOPPER, ODS DOGHOUSE, BREAK SUBS APART AND PREP TO TRANSPORT. ON NEW LOCATION SET IN MUD TANKS, SET SHAKERS ON MUD TANKS, SET MUD PUMPS, SUITCASES, PUMP PARTS HOUSE, VFD HOUSE, GEN PACKAGE, DIESEL TANK, WATER TANKS, CHANGE HOUSE, AND MATTS. RIG UP ELECTRIC LINES IN BACK YARD AND GEN PACKAGE
FAT TIRE A 1H | 4 | 2020-12-09 06:00 | 2020-12-10 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 105 | 105 | 0 | MOVED IN RIG EQUIPMENT: MOVE AND SET PATTTERSON CAMP HOUSES, SET SUB MATS, SPOTTED SUB & CENTERED SAME, RIGGED UP CENTER STEEL, SET DRAWWORKS, ODS HOUSE, PINNED A-SECTION TO SUBS, PINNED MIDDLE AND CROWN SECTION OF DERRICK, INSTALLED MONKEY BOARD, PINNED BLOCKS TO TOP DRIVE, DRESSED OUT DERRICK, SET DS HOUSE, ST-80, PERFORM MAST PRE-RAISE INSPECTION, RAISE DERRICK @ 04:00, SCOPE IN AND PIN MSRC'S TO SUBS, RAISE AND PIN SUBS, SUBS UP @ 06:00 HRS
FAT TIRE A 1H | 3 | 2020-12-09 06:00 | 2020-12-09 06:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 105 | 105 |  | MILESTONE_MOB/DEMOB ON 12/8/2020 @ 06:00
FAT TIRE A 1H | 5 | 2020-12-10 06:00 | 2020-12-10 18:00 | 12 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | INSTALL FRONT STOMPERS, RIG UP HYD. ON ALL STOMPERS, RETRACT MSRC'S/HORSE HEADS, SWAP HYDRAULICS TO DRILLING OPERATIONS, SPOOL UP DS/ODS/BOOM POLE HOISTS, EXTEND DRILLERS CABIN, RIG UP ALL ELECTRICAL ON FLOOR, RIG UP CATWALK/ACCUMULATOR ELECTRICAL LINES, MAKE UP STANDPIPE JUMPER LINES/VIBRATING HOSE, DRESS OUT RIG FLOOR, HANG FLOW LINE, SET ODS STAIRCASE, MAKE UP FLOWLINE MANIFOLD TO SHAKERS POSSUM BELLY, STRETCH OUT CLIMB ASSIST/ESCAPE LINES, POWER UP RIG, SPOOL UP DRAWWORKS, UNPIN BLOCKS, FUNCTION TEST/DRESS OUT TOP DRIVE.
FAT TIRE A 1H | 5 | 2020-12-10 18:00 | 2020-12-11 03:00 | 9 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | INSTALL SWIVEL PACKING, R/U STOPMPERS ON CATWALK, WORK WITH ELECTRICIAN ON TOP DRIVE, INSTALL 5-1/4" LINERS IN #1 MP, DRESS OUT TOP DRIVE, INSTALL 5" SEGMENTS IN SINGLE LATCH ELEVATORS.
FAT TIRE A 1H | 5 | 2020-12-11 03:00 | 2020-12-11 05:00 | 2 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | RIG UP CELLAR PUMPS AND EQUIPMENT, PRESSURE TEST SURFACE EQUIPMENT TO 1000 PSI-GOOD.
FAT TIRE A 1H | 5 | 2020-12-11 05:00 | 2020-12-11 06:00 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | STAGE DIRECTIONAL TOOLS AND BHA TO PREPARE FOR SPUD.
FAT TIRE A 1H | 6 | 2020-12-11 06:00 | 2020-12-11 08:30 | 2.5 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 105 | 105 | 0 | PICK UP BIT 13-1/2" ULTERRA SPL616 W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 105'.
FAT TIRE A 1H | 6 | 2020-12-11 08:30 | 2020-12-11 08:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 105 | 105 |  | MILESTONE_SPUD WELL ON 12/11/2020 @ 08:30
FAT TIRE A 1H | 6 | 2020-12-11 08:30 | 2020-12-11 14:30 | 6 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.25 | 105 | 2885 | 463.3 | ROTATE (2780' IN 6.08 HRS @ 456.99 FPH) WOB-20/35K, RPM-100, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2900 PSI, DIFF-700/900 PSI. DUMPING 100 BBLS EVERY 300' AND PUMPING 30 BBLS SWEEP EVERY 300'.
FAT TIRE A 1H | 6 | 2020-12-11 14:30 | 2020-12-11 15:30 | 1 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.29 | 2885 | 3105 | 220 | SLIDE (220' IN 0.92 HRS @ 240 FPH) WOB: 10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP- 2000/2200 PSI, DIFF- 100/200 PSI. SLIDE DEPTHS: SLD F/500 T/515 TF-240M 15' MIN-5 0948-0953 SLD F/785 T/805 TF-240M 20' MIN-7 1038-1045 SLD F/967 T/987 TF-220M 20' MIN-5 1102-1107 SLD F/1065 T/1085 TF-20L 20' MIN- 1117-1121 SLD F/1065 T/1085 TF-20L 20' MIN-4 1117-1121 SLD F/1160 T/1190 TF-HS 30' MIN-6 1130-1136 SLD F/1255 T/1280 TF-HS 25' MIN-4 1145-1149 SLD F/1440 T/1465 TF-20L 25' MIN-6 1208-1214 SLD F/2005 T/2030 TF-10R 25' MIN-7 1312-1319 SLD F/2570 T/2610 TF-HS 40' MIN-11 1419-1430 TD SURFACE ON 12/11/2020 @ 15:30 (3,105' MD / 3,073' TVD)
FAT TIRE A 1H | 6 | 2020-12-11 15:30 | 2020-12-11 16:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.33 | 3105 | 3105 | 0 | PUMP 3-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2150 PSI.
FAT TIRE A 1H | 6 | 2020-12-11 16:30 | 2020-12-11 18:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.4 | 3105 | 3105 | 0 | TRIP OUT OF HOLE F/3,105' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
FAT TIRE A 1H | 6 | 2020-12-11 18:00 | 2020-12-11 18:30 | 0.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.42 | 3105 | 3105 | 0 | L/D 1 JOINT OF HWDP, REMOVE MWD TOOL, DRAIN MOTOR, RACK BHA BACK IN DERRICK.
FAT TIRE A 1H | 6 | 2020-12-11 18:30 | 2020-12-11 20:00 | 1.5 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.48 | 3105 | 3105 | 0 | PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
FAT TIRE A 1H | 6 | 2020-12-11 20:00 | 2020-12-12 01:00 | 5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.69 | 3105 | 3105 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 75 JOINTS TOTAL OF 10 3/4" 45.5# J-55 T/3,095.23', RAN 38 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY OTHER JT. ALL THE WAY TO 160.63', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 65" BELOW GROUND LEVEL. WASH DOWN LANDING JOINT AND SET 90K (W/O BLOCKS) ON BASE PLATE. SHOE: 3,095.23' TOP OF FLOAT COLLAR: 3,012.05'
FAT TIRE A 1H | 6 | 2020-12-12 01:00 | 2020-12-12 01:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.71 | 3105 | 3105 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOLS, GPM-321, SPP-100/200 PSI. NO LOSSES.
FAT TIRE A 1H | 6 | 2020-12-12 01:30 | 2020-12-12 02:00 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.73 | 3105 | 3105 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, AND RIG DOWN CELLAR PUMPS.
FAT TIRE A 1H | 6 | 2020-12-12 02:00 | 2020-12-12 05:00 | 3 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.73 | 3105 | 3105 | 0 | PREP RIG TO WALK AND WALK RIG F/FAT TIRE A 1H T/FAT TIRE B 1H. RIG UP STREAMFLO PUP JOINT AND CEMENT HEAD
FAT TIRE A 1H | 6 | 2020-12-12 02:00 | 2020-12-12 02:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.73 | 3105 | 3105 |  | MILESTONE_HOLD WELL OPERATIONS 1 12/12/2020 2:00
FAT TIRE A 1H | 6 | 2020-12-12 05:00 | 2020-12-12 06:00 | 1 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.73 | 3105 | 3105 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 2,000 PSI & CEMENTED WITH: 25 BBL 8.3 PPG FRESH WATER SPACER, 329 BBLS 11.6 PPG LEAD CEMENT, 88 BBL 14.4 PPG TAIL CEMENT, DROP PLUG AND BEGAN DISPLACING WITH 290 BBLS OF 9.0 PPG OIL BASE MUD.
FAT TIRE A 1H | 7 | 2020-12-12 06:00 | 2020-12-12 07:30 | 1.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.73 | 3105 | 3105 | 0 | DISPLACED WITH 290 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/700 PSI PRESSURED UP T/1200 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 25 BBLS OF SPACER AND 150 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
FAT TIRE A 1H | 7 | 2020-12-12 07:30 | 2020-12-12 08:00 | 0.5 | R | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 0.73 | 3105 | 3105 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAM FLO AND SECURE WELL.
FAT TIRE A 1H | 8 | 2020-12-17 12:00 | 2020-12-17 14:00 | 2 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 0.81 | 3105 | 3105 | 0 | PREP RIG TO WALK: REMOVE VIBRATOR HOSES, KILL LINE, CHOKE LINE AND PICK UP V-DOOR. WALK CATWALK, MOVE CLIMB ASSIST, GERONIMO ANCHORS. SKID RIG FROM FAT TIRE B 1H TO FAT TIRE A 1H
FAT TIRE A 1H | 8 | 2020-12-17 12:00 | 2020-12-17 12:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.73 | 3105 | 3105 |  | MILESTONE_RESUME_WELL OPERATIONS 1 ON 12/17/2020 @ 12:00
FAT TIRE A 1H | 8 | 2020-12-17 14:00 | 2020-12-17 15:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.85 | 3105 | 3105 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, HOOK UP FLOWLINE, REMOVE KILL LINE CHECK VALVE, R/U KILL LINE
FAT TIRE A 1H | 8 | 2020-12-17 15:00 | 2020-12-17 17:00 | 2 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.94 | 3105 | 3105 | 0 | CHANGE OUT TOP RAMS FROM 7-5/8" CASING TO 2-7/8" X 5-1/2" VARIBLE RAMS
FAT TIRE A 1H | 8 | 2020-12-17 17:00 | 2020-12-17 20:00 | 3 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.06 | 3105 | 3105 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS AND BOTTOM BREAK 250 LOW AND 5000 PSI HIGH
FAT TIRE A 1H | 8 | 2020-12-17 20:00 | 2020-12-17 20:30 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.08 | 3105 | 3105 | 0 | TEST CASING TO 1500 PSI, GOOD TEST
FAT TIRE A 1H | 8 | 2020-12-17 20:30 | 2020-12-17 21:30 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.13 | 3105 | 3105 | 0 | INSTALL WEAR BUSHING, PERFORM DRAW DOWN TEST ON ACCUMULATOR, INSTALL MOUSE HOLE
FAT TIRE A 1H | 8 | 2020-12-17 21:30 | 2020-12-17 22:00 | 0.5 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.15 | 3105 | 3105 | 0 | RIG SERVICE
FAT TIRE A 1H | 8 | 2020-12-17 22:00 | 2020-12-17 23:30 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.21 | 3105 | 3105 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.491) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.81' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-69' AND GAMMA-59'.
FAT TIRE A 1H | 8 | 2020-12-17 23:30 | 2020-12-18 02:00 | 2.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.31 | 3105 | 3105 | 0 | TRIP IN HOLE T3,012'. PICKED UP AGITATOR AFTER STAND 22. PSI BEFORE-580. PSI AFTER-730
FAT TIRE A 1H | 8 | 2020-12-18 02:00 | 2020-12-18 03:00 | 1 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.35 | 3105 | 3115 | 10 | DRILL SHOE TRACK AND 10' NEW FORMATION F/3,012' T/3,115', GPM-425, SPP-1300 PSI, RPM-30, DIFF-(100-200 PSI)
FAT TIRE A 1H | 8 | 2020-12-18 03:00 | 2020-12-18 03:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.38 | 3115 | 3115 | 0 | CIRCULATE BOTTOMS UP GPM-420, SPP-1215 PSI, RPM-30
FAT TIRE A 1H | 8 | 2020-12-18 03:30 | 2020-12-18 04:00 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.4 | 3115 | 3115 | 0 | PERFORM F.I.T.WITH 9.2 PPG MUD, 382 PSI SURFACE PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,095' TVD-3,063'. GOOD TEST.
FAT TIRE A 1H | 8 | 2020-12-18 04:00 | 2020-12-18 05:30 | 1.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.46 | 3115 | 3841 | 484 | ROT (726' IN 1.47 HRS @ 502 FPH) WOB: 25/40K, SPM: 84/84/84, GPM: 800, MMRPM: 133, RPM: 80, TRPM: 205, TRQ: 8/11K, SPP: 3650/4050 PSI, DIFF: 400/500 PSI.
FAT TIRE A 1H | 8 | 2020-12-18 05:30 | 2020-12-18 06:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.48 | 3841 | 3899 | 116 | SLIDE (58' IN .5 HRS @ 105 FPH) WOB: 10/20K, SPM: 84/84/84, GPM: 800, MMRPM: 133, SPP: 3650/3850 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/3150-T/3170 TF-90R 22FT F/0400-T/ 0404 SLD F/3527-T/3545 TF-140L 18 FT F/0448-T/ 0503
FAT TIRE A 1H | 9 | 2020-12-18 06:00 | 2020-12-18 22:00 | 16 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.15 | 3899 | 9393 | 343.4 | ROT (5494' IN 16.23 HRS @ 338 FPH) WOB: 25/40K, SPM: 84/84/84, GPM: 800, MMRPM: 133, RPM: 80, TRPM: 213, TRQ: 11/20K, SPP: 4650/5450 PSI, DIFF: 500/800 PSI.
FAT TIRE A 1H | 9 | 2020-12-18 22:00 | 2020-12-19 03:30 | 5.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.38 | 9393 | 9723 | 60 | SLIDE (330' IN 5.27 HRS @ 63 FPH) WOB: 10/20K, SPM: 84/84/84, GPM: 800, MMRPM: 133, SPP: 4650/4950 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/4380 T/4400 TF-30R 20' MIN-7 0654-0701 SLD F/5510 T/5528 TF-60L 18' MIN-13 0932-0945 SLD F/5700 T/5730 TF-60L 30' MIN-17 1017-1036 SLD F/5975 T/5995 TF-160R 20' MIN-11 1123-1134 SLD F/6070 T/6085 TF-160R 15' MIN-13 1148-1201 SLD F/6165 T/6185 TF-160R 20' MIN-18 1216-1234 SLD F/6260 T/6280 TF-160R 20' MIN-19 1250-1309 SLD F/6450 T/6475 TF-160R 25' MIN-15 1340-1355 SLD F/7385 T/7405 TF-90M 20' MIN-20 1631-1651 SLD F/8126-T/8144,TF-158M,18' MIN-20 1902-1922 SLD F/8409-T/8431,TF-120M, 22', 2018-T/2040,18-MIN SLD F/8879-T/8901,TF-120M, 22', 2202-T/2222, 20MIN SLD F/8973-T/8999,TF-180M, 26' F/2240-T/2302, 22MIN SLD F/9349-T/9375,180 MAG,26' F/0024-T/0120, 56 MIN SLD F/9441' T/9469, TF-180M, 28', F/143 T/224, 41 MIN START INTERMEDIATE CURVE ON 12/19/2020 @ 03:30 (9,723' MD / 9,647' TVD)
FAT TIRE A 1H | 9 | 2020-12-19 03:30 | 2020-12-19 05:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.44 | 9723 | 9813 | 60 | SLIDE (90' IN 1.35 HRS @ 67 FPH) WOB: 10/20K, SPM: 84/84/84, GPM: 800, MMRPM: 133, SPP: 4650/4950 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: F/9723' T/9783, TF-320M, 60', F/330 T/437, 67 MIN F/9881' T/9911, TF-10R, 30', F/514 T/530, 16 MIN
FAT TIRE A 1H | 9 | 2020-12-19 05:00 | 2020-12-19 05:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.46 | 9813 | 9911 | 196 | ROT (98' IN .65 HRS @ 151 FPH) WOB: 25/40K, SPM: 84/84/84, GPM: 800, MMRPM: 133, RPM: 40, TRPM: 173, TRQ: 11/20K, SPP: 4650/5450 PSI, DIFF: 500/800 PSI.
FAT TIRE A 1H | 9 | 2020-12-19 05:30 | 2020-12-19 06:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.48 | 9911 | 9911 | 0 | RIG SERVICE
FAT TIRE A 1H | 10 | 2020-12-19 06:00 | 2020-12-19 09:30 | 3.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.63 | 9911 | 9937 | 7.4 | SLIDE (26' IN 3.5 HRS @ 7 FPH) WOB: 10/35K, SPM: 84/84/84, GPM: 800, MMRPM: 133, SPP: 4650/4950 PSI, DIFF: 200/400 PSI. TD INTERMEDIATE SECTION ON 12/19/2020 @ 09:30 (9,937' MD / 9,860' TVD)
FAT TIRE A 1H | 10 | 2020-12-19 09:30 | 2020-12-19 11:00 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.69 | 9937 | 9937 | 0 | PUMP 3 TANDEM 30 BBL LCM SWEEPS AND CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM: 800, RPM: 40, TRQ: 5K/9K, SPP: 4850 PSI. PERFORMED 15 MINUTE FLOW CHECK-NO FLOW. PUMP SLUG.
FAT TIRE A 1H | 10 | 2020-12-19 11:00 | 2020-12-19 15:00 | 4 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 2.85 | 9937 | 9937 | 0 | POOH 5 STANDS AND L/D DRILL PIPE FROM 9,535' TO 4,084'.
FAT TIRE A 1H | 10 | 2020-12-19 15:00 | 2020-12-19 15:30 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 2.88 | 9937 | 9937 | 0 | REMOVED RCH & INSTALLED TRIP NIPPLE
FAT TIRE A 1H | 10 | 2020-12-19 15:30 | 2020-12-19 17:30 | 2 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 2.96 | 9937 | 9937 | 0 | LAY DOWN 5" DP F/4,084' - T/2,679'
FAT TIRE A 1H | 10 | 2020-12-19 17:30 | 2020-12-19 18:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.98 | 9937 | 9937 | 0 | SERVICED TOP DRIVE
FAT TIRE A 1H | 10 | 2020-12-19 18:00 | 2020-12-19 20:30 | 2.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.08 | 9937 | 9937 | 0 | RIH WITH 5 STANDS DP AND L/D 5" DP F/3150 - T/BHA'. HOLE TOOK APPROXIMATELY 42 BBLS MORE THAN CALCULATED DISPLACEMENT FOR ENTIRE TRIP.
FAT TIRE A 1H | 10 | 2020-12-19 20:30 | 2020-12-19 21:30 | 1 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.13 | 9937 | 9937 | 0 | LAY DOWN DIRECTIONAL BHA AND LOAD OUT SAME
FAT TIRE A 1H | 10 | 2020-12-19 21:30 | 2020-12-19 22:00 | 0.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.15 | 9937 | 9937 | 0 | PULL WEAR BUSHING
FAT TIRE A 1H | 10 | 2020-12-19 22:00 | 2020-12-20 01:00 | 3 | P | INTHLCSG | BOP | NSTLBOP | INSTALL BOPS | 3.27 | 9937 | 9937 | 0 | CHANGE TOP RAMS IN BOP FROM VARIABLE TO 7-5/8". INSTALL TEST PLUG AND TEST RAM CAVITY T/700 PSI. GOOD TEST.
FAT TIRE A 1H | 10 | 2020-12-20 01:00 | 2020-12-20 02:00 | 1 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.31 | 9937 | 9937 | 0 | RIG UP EXPRESS CASING CREW AND EQUIPMENT.
FAT TIRE A 1H | 10 | 2020-12-20 02:00 | 2020-12-20 06:00 | 4 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.48 | 9937 | 9937 | 0 | HELD PJSM THEN RAN INTERMEDIATE CASING T/3,900'. RAN CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 7-5/8" INTERMEDIATE CASING T/3,900'. FILLING PIPE ON THE FLY, INSTALLED LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT FOR A TOTAL OF 41 CENTRALIZERS. HOLE GIVING PROPER DISPLACEMENTS. FLOAT SHOE-9,924.3' TOP OF FLOAT COLLAR-9,831.29'
FAT TIRE A 1H | 11 | 2020-12-20 06:00 | 2020-12-20 11:30 | 5.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.71 | 9937 | 9937 | 0 | RUN INTERMEDIATE CASING F/3,900' T/9,891'. PICK UP LANDING JOINT AND LAND ON HANGER W/170K (W/O BLOCKS) @ 9,924.3'. FLOAT SHOE-9,924.3' TOP OF FLOAT COLLAR-9,831.29'
FAT TIRE A 1H | 11 | 2020-12-20 11:30 | 2020-12-20 12:00 | 0.5 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 3.73 | 9937 | 9937 | 0 | HELD PJSM, RIG DOWN CRT, RIG UP NINE ENERGY CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
FAT TIRE A 1H | 11 | 2020-12-20 12:00 | 2020-12-20 13:00 | 1 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 3.77 | 9937 | 9937 | 0 | CIRCULATE BOTTOMS UP W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIGGING DOWN FRANK'S CASING TOOLS AND EQUIPMENT. SPM: 140, 8.5 BPM, SPP: 730 PSI, NO LOSSES.
FAT TIRE A 1H | 11 | 2020-12-20 13:00 | 2020-12-20 16:00 | 3 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.9 | 9937 | 9937 | 0 | HOLD PJSM AND SWAP LINES T/CEMENTERS. CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL11.0 PPG SPACER. 275 BBL 11.8 PPG 795 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 451 BBLS OF 9.0 PPG OIL BASE MUD @ 7 BPM SLOWED PUMP RATE TO 3 BPM, FINAL LIFT PRESSURE WAS 2000 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2500 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 6 BBLS. FLOATS HELD. PLUG DOWN @ 16:10 HRS ON 12/20/2020, GOT BACK 21 BBLS OF SPACER AND 0 BBLS OF LEAD CMT BACK TO SURFACE & HAD FULL RETURNS ENTIRE CEMENTING JOB. TOC @ 3075'.
FAT TIRE A 1H | 11 | 2020-12-20 16:00 | 2020-12-20 17:00 | 1 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 3.94 | 9937 | 9937 | 0 | PRESSURE TESTED CASING TO 3500 PSI, HELD 20 MINUTES. (PRESSURE HELD AND TEST GOOD).
FAT TIRE A 1H | 11 | 2020-12-20 17:00 | 2020-12-20 17:30 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 3.96 | 9937 | 9937 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BAILS AND ELEVATORS.
FAT TIRE A 1H | 11 | 2020-12-20 17:30 | 2020-12-20 20:00 | 2.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.06 | 9937 | 9937 | 0 | MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK AND WELLHEAD, WASHED OUT AND FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL AND LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF AND INSTALLED SAME, TESTED PACK-OFF TO 5K PSI-GOOD, PULL TESTED PACK-OFF TO 25K,TEST PACK-OFF TO 5K AGAIN-GOOD, BROKE OUT & LAID DOWN SETTING TOOL.
FAT TIRE A 1H | 11 | 2020-12-20 20:00 | 2020-12-20 22:00 | 2 | P | INTHLCSG | BOP | NSTLBOP | INSTALL BOPS | 4.15 | 9937 | 9937 | 0 | CHANGE OUT TOP RAMS ON BOP, 7-5/8" TO VARIABLE RAMS (3-1/2" X 5-1/2")
FAT TIRE A 1H | 11 | 2020-12-20 22:00 | 2020-12-21 04:00 | 6 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.4 | 9937 | 9937 | 0 | BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 7,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 7000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ROTATING HEAD AND ORBIT VALVE TO 1500 PSI. REMOVE TEST PLUG AND RIG DOWN TESTERS
FAT TIRE A 1H | 11 | 2020-12-21 04:00 | 2020-12-21 05:30 | 1.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.46 | 9937 | 9937 | 0 | REMOVE 4-1/2" IF SAVER SUB AND REPLACE WITH DS42 SAVER SUB CUT FOR SCREEN.
FAT TIRE A 1H | 11 | 2020-12-21 05:30 | 2020-12-21 06:00 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.48 | 9937 | 9937 | 0 | INSTALL WEAR BUSHING
FAT TIRE A 1H | 12 | 2020-12-21 06:00 | 2020-12-21 08:30 | 2.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.58 | 9937 | 9937 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13446789 JETS 6/18S TFA: 1.491), 5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.08' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, TOMAX THRUSTER, X/O XT-39 P x DS 42 B, 27 STANDS, AGITATOR. BIT TO SVY-72'. BIT TO GAMMA-62'. TEST MWD (TEST GOOD)
FAT TIRE A 1H | 12 | 2020-12-21 08:30 | 2020-12-21 16:30 | 8 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 4.92 | 9937 | 9937 | 0 | PICK UP DRILL PIPE F/BHA T/8230 . PICK UP AGITATOR ON STAND 27. PSI BEFORE-1675. PSI AFTER-2000
FAT TIRE A 1H | 12 | 2020-12-21 16:30 | 2020-12-21 17:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 4.94 | 9937 | 9937 | 0 | INSTALL RCH BEARING
FAT TIRE A 1H | 12 | 2020-12-21 17:00 | 2020-12-21 19:30 | 2.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.04 | 9937 | 9937 | 0 | PICK UP DRILL PIPE 8230' T/9560', FILL PIPE
FAT TIRE A 1H | 12 | 2020-12-21 19:30 | 2020-12-21 21:00 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.1 | 9937 | 9937 | 0 | CUT AND SLIP DRILLING LINE
FAT TIRE A 1H | 12 | 2020-12-21 21:00 | 2020-12-21 21:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.13 | 9937 | 9937 | 0 | RIG SERVICE
FAT TIRE A 1H | 12 | 2020-12-21 21:30 | 2020-12-21 23:00 | 1.5 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.19 | 9937 | 9937 | 0 | WASH DOWN F/9,560' TO FLOAT COLLAR AT 9,831'. DRILL OUT SHOE TRACK TO 9,924' GPM-200 SPP-1500 RPM-30
FAT TIRE A 1H | 12 | 2020-12-21 23:00 | 2020-12-21 23:30 | 0.5 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 5.21 | 9937 | 9947 | 20 | DRILL 10' FORMATION FOR F.I.T. TO 9947'. GPM-200 SPP-1500 RPM-30
FAT TIRE A 1H | 12 | 2020-12-21 23:30 | 2020-12-22 | 0.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 5.23 | 9947 | 9947 | 0 | CIRCULATE BOTTOMS UP
FAT TIRE A 1H | 12 | 2020-12-22 | 2020-12-22 00:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.25 | 9947 | 9947 | 0 | PERFORMED F.I.T @ 9,924' MD / 9,848' TVD WITH 9.2 MW T/1964 PSI. EMW-13.0 PPG
FAT TIRE A 1H | 12 | 2020-12-22 00:30 | 2020-12-22 05:00 | 4.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.44 | 9947 | 10292 | 76.7 | S/D (345' IN 4.42 HRS @ 78 FPH) WOB-25/50K, SPM-152, GPM-400, MRPM-272, SPP-3200/3500 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', SLIDE DEPTHS: F/9947-T/10037,TF-HS,90' F/0020-T/148,88MIN F/10055-T/10133,TF-HS,78'F/200-T/250,50MIN F/10188-T/10228,TF-10L,40', F/325-T/352,27-MIN 10250-T/10387,TF-HS,137', F/410-T/0600, 110 MIN
FAT TIRE A 1H | 12 | 2020-12-22 00:30 | 2020-12-22 00:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.25 | 9947 | 9947 |  | MILESTONE_START CURVE ON 12/22/2020 @ 00:30 HRS
FAT TIRE A 1H | 12 | 2020-12-22 05:00 | 2020-12-22 06:00 | 1 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.48 | 10292 | 10387 | 95 | VAC TRUCK FOR OBM TRANSFERS CASING PSI WHILE DRILLING-0 PSI. CASING PSI DURING CONNECTION-0 PSI.
FAT TIRE A 1H | 13 | 2020-12-22 06:00 | 2020-12-22 08:30 | 2.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.58 | 10387 | 10662 | 110 | R/D (275' IN 2.68 HRS @ 102.6 FPH) RPM-80, TRQ-10K/16K, WOB-25/50K, SPM-152, GPM-400, MRPM-272, SPP-3200/3500 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0'.
FAT TIRE A 1H | 13 | 2020-12-22 08:30 | 2020-12-22 12:30 | 4 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.75 | 10662 | 10988 | 81.5 | S/D (326' IN 3.90 HRS @ 83 FPH) WOB-25/50K, SPM-152, GPM-400, MRPM-272, SPP-3200/3500 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' SLIDE DEPTHS: 10455-10513 TF-HS 58' 36M 10551-10703 TF-HS 152'127M 10755-10799 TF-HS 44' 28M 10880-10894 TF-06R 14' 8M 10930-10988 TF-30R 58' 35M NOTE: ENCOUNTERED PARTIAL RETURNS @ 10,818’ MD. LOSSES @ 100 BPH, BEGIN CUTTING MUD WEIGHT F/9.2 PPG, PUMPS WERE BACKED DOWN TO 325 GPM’S, & 40 BBL LCM SWEEPS WERE PUMPED E/STD IN AN ATTEMPT TO REGAIN FULL RETURNS TOTAL INITIAL LOSSES - 250 BBLS NOTE: BUILT 400 BBLS 16.0 PPG OBM AND SEND TO RAM-TEX. NOTE: CUTTING MW F/9.2; HOWEVER DUE TO MUD ADDITIONS FROM FRAC TANK. MUD CUT IS TAKING LONGER THAN ANTICIPATED. FRAC TANK WT=9.0-9.5 PPG. LAND CURVE ON 12/23/2020 @ 12:30 (10,988' MD / 10,472' TVD) LCM SWEEPS CONTENTS- 10PPG CALCIUM CARBONATE, 10 PPB MAGNAFIBER FINE, 10 PPB TURBOCHEM FIRST REPSONSE.
FAT TIRE A 1H | 13 | 2020-12-22 12:30 | 2020-12-22 12:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 5.75 | 10988 | 10988 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 12/22/2020 @ 12:30
FAT TIRE A 1H | 13 | 2020-12-22 12:30 | 2020-12-22 14:30 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.83 | 10988 | 11332 | 172 | R/D (344' IN 2 HRS @ 172 FPH) RPM-80, TRQ-10K/16K, WOB-25/50K, SPM-114, GPM-322, MRPM-219, SPP-2500/3600 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0-5' NOTE: HOLE LOSING APPROXIMATELY 50-100 BBLS/HR. CUTTING MW BACK TO 8.8 PPG.
FAT TIRE A 1H | 13 | 2020-12-22 12:30 | 2020-12-22 12:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 5.75 | 10988 | 10988 |  | MILESTONE_LAND/END CURVE SECTION ON 12/22/2020 @ 12:30
FAT TIRE A 1H | 13 | 2020-12-22 14:30 | 2020-12-22 15:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.85 | 11332 | 11367 | 70 | S/D (35' IN 0.5 HRS @ 70 FPH) WOB-25/50K, SPM-114, GPM-322, MRPM-219, SPP-2500/2900 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0-5'. SLIDE DEPTHS: 10998-11015 TF-20R 17' 13 MIN 1256-1307 11189-11207 TF-130L 18' 14 MIN 1425-1439 NOTE: HOLE LOSING APPROXIMATELY 50-100 BBLS/HR. CUTTING MW BACK F/8.9 TO 8.8 PPG. MW @ 16:00=8.9 PPG
FAT TIRE A 1H | 13 | 2020-12-22 15:00 | 2020-12-22 15:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.88 | 11367 | 11367 | 0 | SERVICE RIG AND TOP DRIVE
FAT TIRE A 1H | 13 | 2020-12-22 15:30 | 2020-12-22 17:30 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.96 | 11367 | 11740 | 186.5 | R/D (373' IN 2 HRS @ 186 FPH) RPM-80, TRQ-10K/16K, WOB-25/50K, SPM-114, GPM-300, MRPM-204, SPP-2200/3200 PSI, DIFF-800/1000 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0-5'. NOTE: AT 11,649' CONTINED TO CUT MUD WEIGHT BACK T/8.7 PPG, PUMPS WERE BACKED DOWN TO 300 GPM’S, & 40 BBL LCM SWEEPS WERE PUMPED E/STD IN AN ATTEMPT TO REGAIN FULL RETURNS NOTE: AT 11,670' FAULTED +/- 30' INTO ASH BED. LCM CONTENTS: 10 PPB VARI-SEAL, 10 PPB MAGNAFIBER FINE, 10 PPB SYN SEAL, 20 PPB FIRST RESPONSE.
FAT TIRE A 1H | 13 | 2020-12-22 17:30 | 2020-12-22 18:30 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6 | 11740 | 11774 | 34 | S/D (34' IN 1.0 HRS @ 34 FPH) WOB-25/50K, SPM-152, GPM-300, MRPM-204, SPP-2200/2500 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0-5'. SLIDE DEPTHS: 11567-11577 TF-160L 10' 12 MIN 1656-1708 11750-11774 TF-10L 24' 50 MIN 1810-1900 NOTE: HOLE LOSING APPROXIMATELY 50-100 BBLS/HR. CUTTING MW BACK TO 8.8 PPG. MW @ 18:00=8.9 PPG NOTE: ADDING 4 BBLS/HR DIESEL AND 4 BBLS/HR WATER.
FAT TIRE A 1H | 13 | 2020-12-22 18:30 | 2020-12-22 19:30 | 1 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.04 | 11774 | 11774 | 0 | CIRCULATE AT 155 GPM AND 950 SPP, BUILD AND PUMP 30 PPB LCM SWEEP W/ SYN SEAL. BUILD VOLUME IN PITS LCM CONTENTS: 10 PPB VARI-SEAL, 10 PPB MAGNAFIBER FINE, 10 PPB SYN SEAL, 20 PPB FIRST RESPONSE.
FAT TIRE A 1H | 13 | 2020-12-22 19:30 | 2020-12-22 22:00 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.15 | 11774 | 12106 | 132.8 | R/D (332' IN 2.5 HRS @ 133 FPH) RPM-80, TRQ-10K/16K, WOB-25/50K, SPM-114, GPM-300, MRPM-204, SPP-2200/3200 PSI, DIFF-800/1000 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0-5' CUTTING MUD WEIGHT BACK T/8.7 PPG, PUMPING 40 BBL LCM SWEEPS E/STD. ADDING 6 SKS HR (EVERY HOUR) TO ACTIVE OF FIRST RESPONSE, SYNSEAL, AND VARISEAL.
FAT TIRE A 1H | 13 | 2020-12-22 22:00 | 2020-12-22 23:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.21 | 12106 | 12124 | 12 | S/D (18' IN 1.42 HRS @ 13 FPH) WOB-25/50K, SPM-114, GPM-300, MRPM-204, SPP-2200/2500 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', SLIDE DEPTHS: 11935-11947 TF-180 12' 40 MIN 2055-2135 12030-12036 TF-180 25' 45 MIN 2235-2320 NOTE: HOLE LOSING APPROXIMATELY 50 BBLS/HR. CUTTING MW BACK TO 8.7 PPG AT 11,920', ENCOUNTERED ASH BED WHERE GEOLOGIST BELIEVE WE CROSSED INTO THE AUSTIN CHALK B ZONE.
FAT TIRE A 1H | 13 | 2020-12-22 23:30 | 2020-12-23 00:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.25 | 12124 | 12124 | 0 | TROUBLESHOOTING MWD-AT 12:10 A.M THE PULSE TOUCH UPDATED MWD SOFTWARE HAD AN ERROR THAT COULDN'T BE RESOLVED. PRO DIRECTIONAL REVERTED BACK TO THE OLD SOFTWARE PROGRAM OF PULSE TOUCH.
FAT TIRE A 1H | 13 | 2020-12-23 00:30 | 2020-12-23 01:30 | 1 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 6.29 | 12124 | 12124 | 0 | BACKREAM OUT OF HOLE F/12,124 T/11,833' AND REAM BACK TO BOTTOM TO CLEAN UP ASH ZONE @ +/- 11,920'. NO TIGHT HOLE OR EXCESSIVE TORQUE ENCOUNTERED. GPM-332 PP-2850, RPM-50, TQ=5-8K
FAT TIRE A 1H | 13 | 2020-12-23 01:30 | 2020-12-23 04:00 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.4 | 12124 | 12562 | 175.2 | R/D (438' IN 2.7 HRS @ 162 FPH) RPM-80, TRQ-10K/16K, WOB-25/40K, SPM-126, GPM-332, MRPM-225, SPP-2800/3900 PSI, DIFF-800/1200 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0-5'. NOTE: HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. CUTTING MW BACK TO 8.7 PPG. MW @ 05:00-8.8 PPG.
FAT TIRE A 1H | 13 | 2020-12-23 04:00 | 2020-12-23 05:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.46 | 12562 | 12602 | 26.7 | S/D (40' IN 1.3 HRS @ 31 FPH) WOB-25/50K, SPM-114, GPM-300, MRPM-204, SPP-2200/2500 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', SLIDE DEPTHS: 12220-12238 TF-30R 18' 35 MIN 245-0320 12412-12434 TF-160R 22' 43 MIN 0412-0455 LCM CONTENTS: 10 PPB VARI-SEAL, 10 PPB MAGNAFIBER FINE, 10 PPB SYN SEAL, 20 PPB FIRST RESPONSE.
FAT TIRE A 1H | 14 | 2020-12-23 06:00 | 2020-12-23 09:30 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.6 | 12602 | 13217 | 175.7 | ROT (615' IN 3.43 HRS @ 179.3 FPH) WOB-35/45K SPM-63/63, GPM-330, RPM-80, MRPM-224, TMRPM-304, TRQ-12/15K, SPP-2750/3950 PSI, DIFF-1000/1200 PSI. CHOKES- 100% / 100%, FLARE-2-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI. LOSSES INCREASED F/20-30 BPH T/40-50 BPH @ 12,922’. BEGAN CUTTING MUD F/8.7 PPG T/8.5 PPG. CONTINUE PUMPING 10 BBLS LCM SWEEPS EVERY STD CONSISTING OF 10PPG CALCIUM CARBONATE, 10 PPB MAGNAFIBER FINE, 10 PPB FIRST REPSONSE AND ADDING ADDING 6 SKS/HR TO ACTIVE OF FIRST RESPONSE, SYNSEAL, AND VARISEAL. NOTE: OBSERVED 4% CALCITE AND PYRITE F/13,060’ T/13,070’, ENCOUNTERED INCREASE IN FLOW @ 13,190’ AND MAX CASING PRESSURE= 458 PSI WITH CHOKES- 40% / 0%, FLARE-15-20', MUD CUT F/8.6 PPG T/8.3 PPG. STOPPED CUTTING MUD WT. @ 8.6 PPG, AVG CASING PRESSURE= 0 PSI, MAX SICP= 370 PSI, AVG SICP= 200 PSI. REGAINED FULL RETURNS. STOPPED ADDING 6 SKS/HR TO ACTIVE OF FIRST RESPONSE, SYNSEAL, AND VARISEAL. CONTINUE PUMPING 10 BBLS LCM SWEEPS EVERY STD CONSISTING OF 10PPG CALCIUM CARBONATE, 10 PPB MAGNAFIBER FINE, 10 PPB FIRST REPSONSE EVERY STD.
FAT TIRE A 1H | 14 | 2020-12-23 09:30 | 2020-12-23 11:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.67 | 13217 | 13267 | 33.3 | SLIDE (50' IN 1.57 HRS @ 31.9 FPH) WOB: 45/55K, SPM- 63/63, GPM-330, RPM-80, MRPM-224, SPP: 2750/3150 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/12707' T/12727' 20' TF-140L 0632-0707 SLD F/13183' T/13213' 30' TF-130L 940-1039
FAT TIRE A 1H | 14 | 2020-12-23 11:00 | 2020-12-23 12:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.71 | 13267 | 13267 | 0 | CIRCULATE AND RECIPROCATE PIPE @ 13,267’ WHILE GEOLOGY WAS MAKING THE DECISION TO STAY IN THE AUSTIN B AND MAKING A TARGET CHANGE.
FAT TIRE A 1H | 14 | 2020-12-23 12:00 | 2020-12-23 23:00 | 11 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.17 | 13267 | 15021 | 159.5 | ROT (1754' IN 11 HRS @ 159 FPH) WOB-35/45K SPM-63/63, GPM-330, RPM-80, MRPM-224, TMRPM-304, TRQ-14/20K, SPP-2800/ PSI, DIFF-1000/1200 PSI. CHOKES- 100% / 100%, FLARE-3'-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 260 PSI, AVG SICP= 225 PSI. NOTE: ENCOUNTERING LOSSES @ 5-10 BPH WITH 95%-98% RETURNS, PUMPING 10 BBLS LCM SWEEPS EVERY STD CONSISTING OF 10PPG CALCIUM CARBONATE, 10 PPB MAGNAFIBER FINE, 10 PPB FIRST REPSONSE EVERY STD.
FAT TIRE A 1H | 14 | 2020-12-23 23:00 | 2020-12-24 06:00 | 7 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.46 | 15021 | 15181 | 22.9 | SLIDE (160' IN 7 HRS @ 23 FPH) WOB: 45/55K, SPM- 63/63, GPM-375, RPM-80, MRPM-224, SPP: 2800/3800 PSI, DIFF: 800/1000 PSI. SLIDE DEPTHS: SLD 13277' T/13292' 15' TF-20L 1203-1245 SLD F/13563' T/13575' 12' TF-HS 1414-1444 SLD F/13743' T/13765 22' TF-180 1555-1654 SLD. F/14031-14047 16' TF-160R 1825-1910 SLD. F/14220-14232 14' TF-150R 2020-2045 SLD. F/14402-14427 25' TF-30R 2140-2240 SLD. F/14507-14517 10' TF-80R 2310-2335 SLD. F/14788-14804 16'TF-140R 0125-0205 SLD. F/14874-14884 10' TF-180 0240-0300 SLD. F/15159-15181 22' TF-30R 0445-0600
FAT TIRE A 1H | 15 | 2020-12-24 06:00 | 2020-12-24 13:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.75 | 15181 | 15949 | 109.7 | ROT (768' IN 6.8 HRS @ 112.9 FPH) WOB-35/45K SPM-63/63, GPM-330, RPM-80, MRPM-224, TMRPM-304, TRQ-15/22K, SPP-2950/4150 PSI, DIFF-1000/1200 PSI. CHOKES- 100% / 100%, FLARE-2-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 240 PSI, AVG SICP= 120 PSI. NOTE: ENCOUNTERED 10-20 BPH LOSSES WITH 96%-98% RETURNS @ 15,444’, LOSSES DECREASED T/5-10 BPH WITH 95%-99% RETURNS @ 15,634’, PUMPING 10 BBLS LCM SWEEPS EVERY 3 STDS CONSISTING OF 5 PPB MAGNAFIBER FINE, 5 PPB VERISEAL, 5 PPB SYNSEAL AND 15 PPB FIRST REPSONSE.
FAT TIRE A 1H | 15 | 2020-12-24 13:00 | 2020-12-24 17:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.92 | 15949 | 16015 | 16.5 | SLIDE (66' IN 4.20 HRS @ 15.7 FPH) WOB: 45/55K, SPM-73/73, GPM-380, MRPM-258, SPP-3050/3450 PSI, DIFF-200/400 PSI. SLIDE DEPTHS: SLD F/15253' T/15279' 26' TF-HS 700-820 SLD F/15630' T/15652' 22' TF-180 1120-1242 SLD F/15822' T/15840' 18' TF-180 1412-1542
FAT TIRE A 1H | 15 | 2020-12-24 17:00 | 2020-12-24 18:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.96 | 16015 | 16015 | 0 | RIG SERVICE.
FAT TIRE A 1H | 15 | 2020-12-24 18:00 | 2020-12-24 18:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.98 | 16015 | 16110 | 190 | ROT (95' IN .5 HRS @ 190 FPH) WOB-35/45K SPM-63/63, GPM-330, RPM-80, MRPM-224, TMRPM-304, TRQ-15/22K, SPP-2950/4150 PSI, DIFF-1000/1200 PSI. CHOKES- 100% / 100%, FLARE-2-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 221 PSI, AVG SICP= 221 PSI. NOTE: STILL ENCOUNTERING LOSSES @ 5-10 BPH WITH 95%-99% RETURNS, PUMPING 10 BBLS LCM SWEEPS EVERY 3 STDS CONSISTING OF 5 PPB MAGNAFIBER FINE, 5 PPB VERISEAL, 5 PPB SYNSEAL AND 15 PPB FIRST REPSONSE.
FAT TIRE A 1H | 15 | 2020-12-24 18:30 | 2020-12-24 21:30 | 3 | P | PRDHLLT | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 8.1 | 16110 | 16110 | 0 | MAKE 10 STAND WIPER TRIP DUE TO DRILLING TORQUE 15/22K AND DECREASE IN ROP. BACK REAM OUT OF HOLE F/ 16,110' T/ 15,159', REAM BACK IN HOLE T/ 16,110', SPM-63/63, GPM-330, RPM-80, MRPM-224, TMRPM-304, TRQ-7/17K, SPP-2600/2700, CHOKES- 100% / 100%, FLARE- 5'-10', MAX GAS-3062 UNITS, MUD CUT F/ 8.6 PPG T/ 8.5 PPG.
FAT TIRE A 1H | 15 | 2020-12-24 21:30 | 2020-12-25 03:00 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.33 | 16110 | 16770 | 120 | ROT (660' IN 5.58 HRS @ 118 FPH) WOB-35/45K SPM-75/75, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-15/22K, SPP-3900/5000 PSI, DIFF-1000/1200 PSI. CHOKES- 100% / 100%, FLARE-2-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 425 PSI, AVG SICP= 400 PSI. NOTE: STILL ENCOUNTERING LOSSES @ 5-10 BPH WITH 95%-99% RETURNS, PUMPING 10 BBLS LCM SWEEPS EVERY STD CONSISTING OF 5 PPB MAGNAFIBER FINE, 5 PPB VERISEAL, 5 PPB SYNSEAL AND 15 PPB FIRST REPSONSE.
FAT TIRE A 1H | 15 | 2020-12-25 03:00 | 2020-12-25 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.46 | 16770 | 16802 | 10.7 | SLIDE (32' IN 2.92 HRS @ 11 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-3900/4200 PSI, DIFF-200/400 PSI. SLIDE DEPTHS: SLD. F/16110-16122 12' TF-110R 2145-2250 SLD. F/16490-16498 8' TF-HS 0200-0220 SLD. F/16678-16690 12' TF-HS 0345-0500
FAT TIRE A 1H | 16 | 2020-12-25 06:00 | 2020-12-25 10:00 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.63 | 16802 | 17167 | 91.3 | ROT (365' IN 4 HRS @ 91 FPH) WOB-35/45K SPM-75/75, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-15/22K, SPP-4000/5200 PSI, DIFF-1000/1200 PSI. CHOKES- 100% / 100%, FLARE-2-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 370 PSI, AVG SICP= 350 PSI. NOTE: STILL ENCOUNTERING LOSSES @ 5-10 BPH WITH 95%-99% RETURNS, PUMPING 10 BBLS LCM SWEEPS EVERY STD CONSISTING OF 5 PPB MAGNAFIBER FINE, 5 PPB VERISEAL, 5 PPB SYNSEAL AND 15 PPB FIRST REPSONSE.
FAT TIRE A 1H | 16 | 2020-12-25 10:00 | 2020-12-25 15:00 | 5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.83 | 17167 | 17167 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN. PUMP 3-30 BBL 30 PPB LCM SWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 6 B/U, RPM-80, SPM: 76/76, GPM-400, TRQ-9/13K, SPP-4000 PSI, CHOKES- 100% / 100%, FLARE-2'-5', NO MUD CUT, MAX CASING PRESSURE=0 PSI, MAX GAS: 2250u. 1ST BTM UP START TQ=18/21K, END= 14-18K, P/UWT=275K 2ND BTM UP END TQ= 13/16K, P/U WT= 250K 3RD BTM UP END TQ=11/14K, P/U WT= 250K LOSS OF 7K TORQUE FROM DOING CLEAN UP CYCLE, SHAKERS CLEAN.
FAT TIRE A 1H | 16 | 2020-12-25 10:00 | 2020-12-25 10:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 8.63 | 17167 | 17167 |  | MILESTONE_TD WELL 12/25/2020 @ 10:00
FAT TIRE A 1H | 16 | 2020-12-25 15:00 | 2020-12-25 22:30 | 7.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.15 | 17167 | 17167 | 0 | BACK REAM OUT THE HOLE F/17,167' T/9954', GPM: 375, RPM: 80, TRQ: 9k/17K, SPP: 2800 PSI. CHOKES- 100% / 0%, FLARE-5-10', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 550 PSI, AVG SICP= 200 PSI. NOTE: ENCOUNTERING LOSSES @ 5-10 BPH WITH 95%-99% RETURNS. NOTE: AT BASE OF CURVE @ 10,988' REDUCE RPM-80 T/ RPM-35 TO BACKREAM THROUGH CURVE SECTION OF WELL.
FAT TIRE A 1H | 16 | 2020-12-25 22:30 | 2020-12-25 23:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.19 | 17167 | 17167 | 0 | CIRCULATE BOTTOMS UP, GPM-375, SPP-2850 PSI, CHOKES- 100% / 100%, LOSSES @ 65 BPH W/ 80%-85% RETURNS, LOSS 26 BBLS, REDUCE PUMP RATE T/ GPM-330, SPP-2325, W/ NO LOSSES FLARE-2-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX GAS-2977u. SHUT DOWN MUD PUMPS AND MONITOR SICP F/ 20 MINUTES= 177 PSI, CASING PRESSURE BROKE OVER AND BLED DOWN T/ 172 PSI.
FAT TIRE A 1H | 16 | 2020-12-25 23:30 | 2020-12-26 00:30 | 1 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 9.23 | 17167 | 17167 | 0 | SPOT 42.5 BBL 16.0 PPG OBM MUD CAP @ 9942' (100 PSI OVER BALANCE MUD CAP). SHUT IN AND MONITORED CASING PRESSURE. SICP= BEFORE CAP-172 PSI / AFTER-0 PSI TOP OF MUD CAP-8322'
FAT TIRE A 1H | 16 | 2020-12-26 00:30 | 2020-12-26 01:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 9.27 | 17167 | 17167 | 0 | STRIP OUT OF HOLE F/9942’ T/8230’ WITH DRY PIPE, PUMPING CALCULATED HOLE FILL .7 BBLS PER STAND DOWN BACKSIDE W/8.6 PPG OBM.
FAT TIRE A 1H | 16 | 2020-12-26 01:30 | 2020-12-26 05:30 | 4 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 9.44 | 17167 | 17167 | 0 | FLOW CHECK (WELL STATIC), PUMP SLUG, TRIP OUT THE HOLE F/8230' T/BHA, HOLE TAKING PROPER FILL, L/D AGITATOR ON STAND 27, REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, FLOW CHECK WELL @ 2900' AND BHA (WELL STATIC).
FAT TIRE A 1H | 16 | 2020-12-26 05:30 | 2020-12-26 06:00 | 0.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.46 | 17167 | 17167 | 0 | LAY DOWN THRUSTER, BTI VALVE, TOP MONEL, REMOVE MWD, DRAIN MOTOR AND BREAK BIT. LAY DOWN MOTOR.
FAT TIRE A 1H | 17 | 2020-12-26 06:00 | 2020-12-26 06:30 | 0.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.48 | 17167 | 17167 | 0 | CONTINUE LAYING DOWN MOTOR AND MONELS.
FAT TIRE A 1H | 17 | 2020-12-26 06:30 | 2020-12-26 07:00 | 0.5 | P | PRDHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 9.5 | 17167 | 17167 | 0 | REMOVE WEAR BUSHING AND CLEAN RIG FLOOR.
FAT TIRE A 1H | 17 | 2020-12-26 07:00 | 2020-12-26 08:00 | 1 | P | PRDHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 9.54 | 17167 | 17167 | 0 | REMOVE SAVER SUB CUT FOR SCREEN AND INSTALL FULL LIP SAVER SUB.
FAT TIRE A 1H | 17 | 2020-12-26 08:00 | 2020-12-26 09:30 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 9.6 | 17167 | 17167 | 0 | HELD PJSM, RIG UP FRANK'S CASING TOOLS AND CRT.
FAT TIRE A 1H | 17 | 2020-12-26 09:30 | 2020-12-26 13:30 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.77 | 17167 | 17167 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING W/CENTRALIZERS IN MIDDLE OF JTS., 1 INNOVEX DV FLOAT COLLAR, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/4,367', FILLING PIPE ON THE FLY, SOLID BODY CENTALIZERS EVERY OTHER JOINT T/12,836.15' (SET DEPTH), MONITOR DISPLACEMENTS ON TRIP TANK. OBSERVED DISPLACEMENT WAS 3.5 BBLS OVER CALCULATED DISPLACEMENT PER 10 JOINTS. NOTE: 106 BBLS CALCULATED 5" CSG DISPLACEMENT T/4,367', 92.3 BBLS ACTUAL 5" CSG DISPLACEMENT. 13.7 BBLS LOST WHILE RUNNING 5" CSG.
FAT TIRE A 1H | 17 | 2020-12-26 13:30 | 2020-12-26 14:30 | 1 | U | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 9.81 | 17167 | 17167 | 0 | FLOW CHECK AND WELL WAS FLOWING @ 46 BPH. SHUT UPPER RAMS AND MONITOR SICP, SICP= 0 PSI, OPEN CHOKE AND MONITORED WELL ON TRIP TANK FOR 15 MINUTES. WELL WAS FLOWING @ 10.7 BPH AND DECREASED T/0 BPH. OPEN UPPER RAMS AND MONITORED WELL DOWN FLOW LINE TO TRIP TANK, WELL WAS FLOWING 40 BPH.
FAT TIRE A 1H | 17 | 2020-12-26 14:30 | 2020-12-26 15:00 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.83 | 17167 | 17167 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD WHILE MONITORING WELL ON TRIP TANK, FLOW DECREASED T/3.5 BPH.
FAT TIRE A 1H | 17 | 2020-12-26 15:00 | 2020-12-26 17:30 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.94 | 17167 | 17167 | 0 | STRIP IN THE HOLE WITH 5" PRODUCTION CASING F/4,367’ T/7,394', FILLING PIPE ON THE FLY. BLEEDING BACK 1.04 BBLS/JT CALCULATED DISPLACEMENT, MAX SICP= 0 PSI, AVG SICP= 0 PSI.
FAT TIRE A 1H | 17 | 2020-12-26 17:30 | 2020-12-26 18:00 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 9.96 | 17167 | 17167 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
FAT TIRE A 1H | 17 | 2020-12-26 18:00 | 2020-12-26 22:30 | 4.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.15 | 17167 | 17167 | 0 | STRIP IN THE HOLE WITH 5.5" 23# P110 ICY WEDGE 625 PRODUCTION CASING F/7,394' T/11,271', FILLING PIPE ON THE FLY,BLEEDING BACK 1.3 BBLS/JT CALCULATED DISPLACEMENT, MAX SICP= 0 PSI, AVG SICP= 0 PSI. NOTE: 98 BBLS CALCULATED 5.5" CSG DISPLACEMENT, 81.6 BBLS ACTUAL 5" CSG DISPLACEMENT. 16.4 BBLS LOST WHILE RUNNING 5.5" CSG.
FAT TIRE A 1H | 17 | 2020-12-26 22:30 | 2020-12-27 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.21 | 17167 | 17167 | 0 | SLOWLY STAGE UP PUMPS T/262 GPM AND CIRCULATE BOTTOMS UP @ 11,271' TO ESTABLISH CIRCULATION. GPM-262, SPP-1300 PSI. 70%-75% RETURNS DURING CIRCULATION. LOSS 67 BBLS, MAX MUD WT. OUT= 10.8 PPG, FLARE= 2'-5', MAX GAS= 2598u. MONITOR SICP, SICP= 321 PSI. NOTE: BY-PASSED 71 BBLS MUD CAP TO OPEN TOP TANK.
FAT TIRE A 1H | 17 | 2020-12-27 | 2020-12-27 04:30 | 4.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.4 | 17167 | 17167 | 0 | STRIP IN THE HOLE WITH 5.5" PRODUCTION CASING F/11,271' T/15,670', FILLING PIPE ON THE FLY. BLEEDING BACK 1.3 BBLS/JT CALCULATED DISPLACEMENT, MAX SICP= 585 PSI, AVG SICP= 450 PSI.
FAT TIRE A 1H | 17 | 2020-12-27 04:30 | 2020-12-27 05:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.42 | 17167 | 17167 | 0 | WASH AND REAM CASING F/15,670' T/15,855', SPM 80, GPM 210, RPM 30, TRQ 8/15K, SPP 500 PSI; AVG CSG PSI- 500, AVG SICCP-650 PSI, MAX SICP-700 PSI
FAT TIRE A 1H | 17 | 2020-12-27 05:00 | 2020-12-27 06:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.46 | 17167 | 17167 | 0 | CIRCULATE AND CONDITION @ 15,855' WHILE RECIPROCATING PIPE DUE TO EXCESSIVE CSG PSI. STAGE PUMPS UP; SPM 80, GPM 210, RPM 30, TRQ 8/15K, SPP 750 PSI; STARTING CSG PSI 700, ENDING CSG PSI 0 PSI. P/U 230K, S/O 210K, ROT 220K; MUD CUT F/8.6 PPG T/8.0 PPG
FAT TIRE A 1H | 18 | 2020-12-27 06:00 | 2020-12-27 08:30 | 2.5 | P | PRDHLCSG | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 10.56 | 17167 | 17167 | 0 | WASH AND REAM CASING F/15,855' T/17,122', SPP-800 PSI, GPM-210, SPM-80, RPM-30, TRQ-15/18K, MUD CUT F/8.6 PPG T/8.4 PPG, MAX CASING PRESSURE= 0 PSI, MAX SICP= 700 PSI. LOSS 95 BBLS TO THE FORMATION.
FAT TIRE A 1H | 18 | 2020-12-27 08:30 | 2020-12-27 09:00 | 0.5 | P | PRDHLCSG | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 10.58 | 17167 | 17167 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND ROTATE LANDING JOINT F/17,122' T/17,148'. [RPM-25, TQ-(15-18K), GPM-210, STOP ROTATION AND LAND CASING ON HANGER W/130K (W/O BLOCKS) @ 17,150.24'. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: 1-INNOVEX 5''FLOAT SHOE, 2 JTS OF 5'' CSG. 1-INNOVEX FLOAT COLLAR, 1-GEODYNAMICS TOE SLEEVE VALVE, RAN 7,364.52 (170 JTS) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER, 1 JOINT 5-1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING, RAN 9,683.9' (208 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING. FOR TOTAL OF 381 FULL JTS OF 5'' 18# P-110 ICY WEDGE 625 & 5.5" 23# P-110 ICY BLUE CASING. CASING SHOE @ 17,150.24' TOP OF FLOAT COLLAR @ 17,059.25' BOTTOM OF TOE SLEEVE VALVE @ 17,059.25' TOP OF TOE SLEEVE VALVE @ 17,033.85' TOP OF X-OVER @ 9,752.87' TOP OF MARKER JOINT ABOVE X-OVER @ 9,686.07' TOP OF SPACE OUT JOINT @ 121.98' 18 JOINTS 5" LEFT OUT- 774.27' 8 JOINTS 5.5" LEFT OUT- 369.86' KICK OUT 1 JOINT WITH A BAD PIN
FAT TIRE A 1H | 18 | 2020-12-27 09:00 | 2020-12-27 09:30 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 10.6 | 17167 | 17167 | 0 | RIG DOWN EXPRESS CRT INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 201 PSI.
FAT TIRE A 1H | 18 | 2020-12-27 09:30 | 2020-12-27 11:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.67 | 17167 | 17167 | 0 | RIG DOWN CSG TOOLS WHILE CIRCULATING BOTTOMS UP, GPM-210, SPP-800 PSI, CHOKES- 75% / 0%, FLARE-5'-10', MUD CUT F/8.6 PPG T/8.4 PPG, MAX CASING PRESSURE= 0 PSI, MAX GAS-2806u. SICP=303 PSI. LOSS 28 BBLS.
FAT TIRE A 1H | 18 | 2020-12-27 11:00 | 2020-12-27 14:00 | 3 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 10.79 | 17167 | 17167 | 0 | HELD PJSM, SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 5 BPM 80 BBL 10.0 PPG WEIGHTED SPACER, 247 BBL 13.5 PPG 830 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBLS OF SUGAR WATER WITH CPT-21L, FOLLOWED BY 317 BBLS OF FRESH WATER WITH PLEXCIDE 15G & CORPLEX 300 @ 5 BPM (TOTAL OF 337 BBLS DISPLACEMENT), OBSERVED 100% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2450 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3450 PSI, HELD FOR 5 MIN, BLED BACK 4 BBLS. FLOATS. 27 BBLS OF SPACER BACK TO SURFACE. HELD. PLUG DOWN @ 14:47 HRS 12/27/2020. LOST 7 BBLS WHILE DISPLACING CEMENT. INITIAL SICP-400 PSI, FINAL SICP= 0 PSI. MAX CASING PSI W/ PUMPING CEMENT- 0 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT- 0 PSI MAX GAS-1930u CALCULATED TOP OF CEMENT- 3630'
FAT TIRE A 1H | 18 | 2020-12-27 14:00 | 2020-12-27 17:30 | 3.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 10.94 | 17167 | 17167 | 0 | SHUT IN WELL, RIG DOWN CIRCULATING IRON AND CEMENT HEAD, SLIP AND CUT 70' DRILL LINE, RIG SERVICE, PREPARE MATS F/ RIG WALK WHILE MONITORING SICP, INITIAL SICP=0 PSI, FINAL SICP= 0 PSI.
FAT TIRE A 1H | 18 | 2020-12-27 17:30 | 2020-12-27 18:00 | 0.5 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 10.96 | 17167 | 17167 | 0 | OPEN CHOKE AND MONITOR WELL ON TRIP (WELL STATIC), OPEN OBIT VALVE, RIG SERVICE WHILE MONITORING WELL DOWN FLOW LINE TO TRIP TANK (WELL STATIC).
FAT TIRE A 1H | 18 | 2020-12-27 18:00 | 2020-12-27 19:30 | 1.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 11.02 | 17167 | 17167 | 0 | LAY DOWN LANDING JOINT, RIGGED DOWN CASING BAILS AND ELEVATORS, MADE UP STREAM FLO WASHOUT TOOL AND FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN. P/U JT OF DP AND M/U PACK-OFF, INSTALLED STREAM FLO PACKOFF & TEST T/ 10,000 PSI.(PULL TEST T/25K OVERPULL) BACK OUT FROM PACK OFF AND L/D JOINT OF DP. INSTALL BPV.
FAT TIRE A 1H | 18 | 2020-12-27 19:30 | 2020-12-27 20:00 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 11.04 | 17167 | 17167 | 0 | FLUSH THROUGH STACK, CHOKE LINE, CHOKE AND FLOW LINE WITH WATER, CHANGE SAVER SUB ON TOP DRIVE
FAT TIRE A 1H | 18 | 2020-12-27 20:00 | 2020-12-27 21:00 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 11.08 | 17167 | 17167 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE AND INSTALL WEATHER CAP AND SECURE WELL. RELEASE WELL @ 21:00 HRS ON 12/27/2020.
FAT TIRE A 1H | 18 | 2020-12-27 21:00 | 2020-12-27 21:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 11.08 | 17167 | 17167 |  | MILESTONE_TURN OVER TO COMPLETION ON 12/27/2020 @ 21:00
FAT TIRE A 1H | 18 | 2020-12-27 21:00 | 2020-12-27 21:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 11.08 | 17167 | 17167 |  | MILESTONE_WELL RELEASE ON 12/27/2020 @ 21:00
FAT TIRE A 1H | 18 | 2020-12-27 21:00 | 2020-12-27 21:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 11.08 | 17167 | 17167 |  | MILESTONE_RIG RELEASE ON 12/27/2020 @ 21:00
FAT TIRE B 1H | 2 | 2020-12-12 02:00 | 2020-12-12 04:00 | 2 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 105 | 105 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK FROM FAT TIRE A 1H TO FAT TIRE B 1H, CENTERED AND LEVELED SUB OVER CONDUCTOR
FAT TIRE B 1H | 2 | 2020-12-12 02:00 | 2020-12-12 02:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 105 | 105 |  | MILESTONE_MOB/DEMOB ON 12/12/2020 @ 02:00
FAT TIRE B 1H | 2 | 2020-12-12 04:00 | 2020-12-12 05:30 | 1.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | RIG UP CELLAR PUMPS AND LINES. INSTALL RISER ON CONDUCTOR PIPE
FAT TIRE B 1H | 2 | 2020-12-12 05:30 | 2020-12-12 06:00 | 0.5 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 105 | 105 | 0 | RIG SERVICE
FAT TIRE B 1H | 3 | 2020-12-12 06:00 | 2020-12-12 07:00 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 105 | 105 | 0 | PICK UP BIT 13-1/2" ULTERRA SPL616 W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 105'.
FAT TIRE B 1H | 3 | 2020-12-12 07:00 | 2020-12-12 07:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 105 | 105 |  | MILESTONE_SPUD WELL ON 12/12/2020 @ 07:00
FAT TIRE B 1H | 3 | 2020-12-12 07:00 | 2020-12-12 12:30 | 5.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.23 | 105 | 2690 | 470 | ROTATE (2585' IN 5.47 HRS @ 473 FPH) WOB-20/35K, RPM-100, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2900 PSI, DIFF-700/900 PSI. DUMPING 100 BBLS EVERY 300' AND PUMPING 30 BBLS SOAP/SAPP SWEEP EVERY 300'.
FAT TIRE B 1H | 3 | 2020-12-12 12:30 | 2020-12-12 14:00 | 1.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.29 | 2690 | 3080 | 260 | SLIDE (390' IN 1.53 HRS @ 254 FPH) WOB: 10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP- 2000/2200 PSI, DIFF- 100/200 PSI. SLIDE DEPTHS: SLD F/320 T/335 TF-180 15' MIN-12 0725-0737 SLD F/590 T/610 TF-217M 20' MIN-7 0821-0828 SLD F/680 T/700 TF-215M 20' MIN-7 0838-0845 SLD F/780 T/805 TF-HS 25' MIN-4 0856-0900 SLD F/875 T/905 TF-HS 30' MIN-4 0908-0912 SLD F/975 T/1015 TF-HS 40' MIN-5 0920-0925 SLD F/1065 T/1105 TF-20L 40' MIN-6 0934-0940 SLD F/1160 T/1200 TF-20L 40' MIN-5 0949-0954 SLD F/1255 T/1295 TF-20L 40' MIN-7 1002-1009 SLD F/1350 T/1365 TF-80L 15' MIN-4 1017-1021 SLD F/1440 T/1470 TF-20L 30' MIN-4 1030-1034 SLD F/1815 T/1850 TF-20L 35' MIN-12 1112-1124 SLD F/2285 T/2325 TF-HS 40' MIN-15 1221-1236 TD SURFACE ON 12/12/2020 @ 14:00 HRS. (3,080' MD / 3,013' TVD)
FAT TIRE B 1H | 3 | 2020-12-12 14:00 | 2020-12-12 15:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.33 | 3080 | 3080 | 0 | PUMP 3-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2200 PSI.
FAT TIRE B 1H | 3 | 2020-12-12 15:00 | 2020-12-12 16:30 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.4 | 3080 | 3080 | 0 | TRIP OUT OF HOLE F/3,080' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
FAT TIRE B 1H | 3 | 2020-12-12 16:30 | 2020-12-12 18:00 | 1.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.46 | 3080 | 3080 | 0 | P/U 1 6" DRILL COLLAR, RACK BACK 8" MONELS, REMOVE MWD TOOL, DRAIN MOTOR, BREAK BIT, L/D MOTOR, PONY SUB, AND UBHO.
FAT TIRE B 1H | 3 | 2020-12-12 18:00 | 2020-12-12 19:00 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.5 | 3080 | 3080 | 0 | PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
FAT TIRE B 1H | 3 | 2020-12-12 19:00 | 2020-12-12 22:30 | 3.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.65 | 3080 | 3080 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 74 JOINTS TOTAL OF 10 3/4" 45.5# J-55 T/3,095.23', RAN 38 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY OTHER JT. ALL THE WAY TO 120.37', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 65" BELOW GROUND LEVEL. WASH DOWN LANDING JOINT AND SET 90K (W/O BLOCKS) ON BASE PLATE. SHOE: 3,070.26' TOP OF FLOAT COLLAR: 2,986.63'
FAT TIRE B 1H | 3 | 2020-12-12 22:30 | 2020-12-12 23:00 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.67 | 3080 | 3080 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOLS, GPM-321, SPP-100/200 PSI. NO LOSSES.
FAT TIRE B 1H | 3 | 2020-12-12 23:00 | 2020-12-12 23:30 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.69 | 3080 | 3080 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, AND RIG DOWN CELLAR PUMPS.
FAT TIRE B 1H | 3 | 2020-12-12 23:30 | 2020-12-13 02:30 | 3 | P | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.81 | 3080 | 3080 | 0 | R/U CMT HEAD AND HOLD PJSM WITH ALL CREWS, TEST LINES T/ 2,000 PSI & CEMENTED WITH: 25 BBL 8.3 PPG FRESH WATER SPACER, 329 BBLS 11.6 PPG LEAD CEMENT, 88 BBL 14.4 PPG TAIL CEMENT, DROP PLUG AND DISPLACE WITH 288 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/800 PSI PRESSURED UP T/1300 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 25 BBLS OF SPACER AND 188 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
FAT TIRE B 1H | 3 | 2020-12-13 02:30 | 2020-12-13 03:00 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.83 | 3080 | 3080 | 0 | TEST CASING T/1500 PSI FOR 20 MINUTES
FAT TIRE B 1H | 3 | 2020-12-13 03:00 | 2020-12-13 03:30 | 0.5 | P | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 0.85 | 3080 | 3080 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAM FLO AND SECURE WELL.
FAT TIRE B 1H | 3 | 2020-12-13 03:30 | 2020-12-13 06:00 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.96 | 3080 | 3080 | 0 | RAISE BOP, HELD PJSM W/STREAMFLO, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALL TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAID OVER SAME, RIG UP KOOMEY LINES, CHOKE HOSES, FUNCTION TEST RAMS, BEGIN RIGGING UP KILL LINE. CLEANING MUD TANKS WHILE N/U.
FAT TIRE B 1H | 4 | 2020-12-13 06:00 | 2020-12-13 07:30 | 1.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.02 | 3080 | 3080 | 0 | MAKE UP FLOWLINE T/BOP, INSTALL 2" TRIP TANK HOSE, INSTALL TURNBUCKLES, M/U AIR LINES TO ORBIT VALVE AND ROT. HEAD CLEAMP, M/U KILL LINE F/BOP TO MUD PUMPS, REMOVE WRANGLER, INSTALL DRAIN HOSES, CLOSE CELLAR COVER, CLEAN ORGANIZE RIG FLOOR.
FAT TIRE B 1H | 4 | 2020-12-13 07:30 | 2020-12-13 16:00 | 8.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.38 | 3080 | 3080 | 0 | INSTALLED TEST PLUG & TESTED BOPE: TOP, BOTTOM PIPE RAMS, BLIND RAMS, MUD CROSS VALVES, KILL LINE, CHOKE LINE, CHOKE MANIFOLD, BACK TO THE PUMPS, TOP DRIVE VALVES, FLOOR SAFETY VALVES 250 PSI LOW / 5000 PSI HIGH, TESTED HYDRIL 250 PSI LOW / 3500 PSI HIGH, TESTED ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. R/D TESTERS NOTE:HCR AND INSIDE MANUAL ON CHOKE LINE WOULD NOT TEST. REMOVE AND REPLACE WITH NEW.
FAT TIRE B 1H | 4 | 2020-12-13 16:00 | 2020-12-13 17:00 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.42 | 3080 | 3080 | 0 | PERFORM ACCUMULATOR DRAW DOWN TEST.
FAT TIRE B 1H | 4 | 2020-12-13 17:00 | 2020-12-13 18:00 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.46 | 3080 | 3080 | 0 | RIG SERVICE
FAT TIRE B 1H | 4 | 2020-12-13 18:00 | 2020-12-13 19:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.5 | 3080 | 3080 | 0 | INSTALL CHECK VALVE AND PREPARE FLOOR TO PICK UP BHA
FAT TIRE B 1H | 4 | 2020-12-13 19:00 | 2020-12-13 21:00 | 2 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.58 | 3080 | 3080 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.491) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.81' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-69' AND GAMMA-59'.
FAT TIRE B 1H | 4 | 2020-12-13 21:00 | 2020-12-13 22:00 | 1 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.63 | 3080 | 3080 | 0 | P/U 6 JOINTS OF 6" DC AND 1 STAND OF HWDP. TEST MWD (GOOD TEST)
FAT TIRE B 1H | 4 | 2020-12-13 22:00 | 2020-12-14 00:30 | 2.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.73 | 3080 | 3080 | 0 | TRIP IN HOLE F/BHA T/2,866' PICK UP AGITATOR AFTER STAND 22. PSI BEFORE AGITATOR-560. AFTER-620 PSI.
FAT TIRE B 1H | 4 | 2020-12-14 00:30 | 2020-12-14 01:00 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.75 | 3080 | 3090 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/3,177' T/3,187', GPM-450, SPP-1500 PSI, RPM-40, DIFF-200 PSI.
FAT TIRE B 1H | 4 | 2020-12-14 01:00 | 2020-12-14 01:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.77 | 3090 | 3090 | 0 | CIRCULATE BOTTOMS UP GPM-420, SPP-1215 PSI, RPM-30
FAT TIRE B 1H | 4 | 2020-12-14 01:30 | 2020-12-14 02:00 | 0.5 | P | SFHLCSG | TEST | FLWTST | FLOW TEST / DFIT | 1.79 | 3090 | 3090 | 0 | PERFORM F.I.T.WITH 9.3 PPG MUD, 359 PSI SURFACE PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,070' TVD-3,003'.
FAT TIRE B 1H | 4 | 2020-12-14 02:00 | 2020-12-14 05:30 | 3.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.94 | 3090 | 4459 | 391.1 | ROT (1379' IN 3.33 HRS @ 414 FPH) WOB: 25/35K, SPM: 78/78/78, GPM: 750, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 11K/16K, SPP: 3000/3900 PSI, DIFF: 700/900 PSI.
FAT TIRE B 1H | 4 | 2020-12-14 05:30 | 2020-12-14 06:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.96 | 4459 | 4553 | 188 | SLIDE (94' IN .68 HRS @ 138 FPH) WOB: 10/20K, SPM: 78/78/78, GPM: 750, MMRPM: 125, SPP: 3000/3300 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/3149-T/3174 TF-20R 25FT F/215-T/ 220 SLD F/3243-T/3258 TF-20R 15' F/245-T/250 SLD F/3625-T/3640,TF-160R 15' 340-T/350 SLD F/3808-T/3823,TF-120R,15' F/413-T/423 SLD F/3998-T/4010 TF-90R 12' F/444-T/0453 SLD F/4374-T/4386 TF-20L 12' F/536-T/539
FAT TIRE B 1H | 5 | 2020-12-14 06:00 | 2020-12-14 23:00 | 17 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.67 | 4553 | 9263 | 277.1 | ROT (4710' IN 16.88 HRS @ 279 FPH) WOB: 25/40K, SPM: 84/84/84, GPM: 800, MMRPM: 133, RPM: 80, TRPM: 213, TRQ: 12K/22K, SPP: 4200/4800 PSI, DIFF: 500/700 PSI.
FAT TIRE B 1H | 5 | 2020-12-14 23:00 | 2020-12-15 06:00 | 7 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.96 | 9263 | 9816 | 79 | SLIDE (553' IN 7.12 HRS @ 78 FPH) WOB: 10/35K, SPM: 84/84/84, GPM: 800, MMRPM: 133, SPP: 4200/4500 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: 4660-4680 TF-50L 20' 6M 5225-5245 TF-30L 20' 10M 5695-5725 TF-HS 20' 20M 5785-5810 TF-30L 25' 25M 6165-6185 TF-70L 20' 28M 7100-7140 TF-HS 40' 27M 7380-7410 TF-50L 30' 23M 7565-7590 TF-50L 25' 20M 7753-7788 TF-20L 35' 10M 7938-7968 TF-HS 30' 18M 8310-8350 TF-20L 40' 27M 8593-8638 TF-50L 45' 25M 8780-8810 TF-100L 30' 37M 8878-8918 TF-150L 40' 39M 8969-9014 TF-170L 45' 32M 9167-9185 TF-150L 18' 17M 9257-9275 TF-40M 18' 15M 9629-9655 TF-150L 26' 32M 9726-9742 TF-310M 16' 20M
FAT TIRE B 1H | 6 | 2020-12-15 06:00 | 2020-12-15 07:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3 | 9816 | 9934 | 118 | ROT (118' IN 1 HRS @ 118 FPH) WOB: 25/40K, SPM: 84/84/84, GPM: 800, MMRPM: 133, RPM: 80, TRPM: 213, TRQ: 12K/22K, SPP: 4200/4800 PSI, DIFF: 500/700 PSI.
FAT TIRE B 1H | 6 | 2020-12-15 07:00 | 2020-12-15 09:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.08 | 9934 | 10032 | 49 | SLIDE (98' IN 1.75 HRS @ 56 FPH) WOB: 10/35K, SPM: 84/84/84, GPM: 800, MMRPM: 133, SPP: 4200/4500 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: 9934-9994 TF-330M 60' 59M 10060-10098 TF-20R 38' 46M START INTERMEDIATE CURVE ON 12/15/2020 @ 07:00 (9,934' MD / 9,661' TVD)
FAT TIRE B 1H | 6 | 2020-12-15 09:00 | 2020-12-15 10:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.13 | 10032 | 10192 | 160 | ROT (160' IN 1 HRS @ 160 FPH) WOB: 25/40K, SPM: 84/84/84, GPM: 800, MMRPM: 133, RPM: 80, TRPM: 213, TRQ: 12K/22K, SPP: 4200/4800 PSI, DIFF: 500/700 PSI.
FAT TIRE B 1H | 6 | 2020-12-15 10:00 | 2020-12-15 23:30 | 13.5 | U | INTHLCSG | WCTRL |  | KILL WELL | 3.69 | 10192 | 10192 | 0 | CIRCULATED & CONDITIONED OUT GAS: WHILE PUMPING 2-30BBL HIGH VIS LCM SWEEPS AT TD FLOW INCREASED AT SHAKERS. SHUT DOWN MUD PUMPS TO MONITOR WELL FOR FLOW (WELL WAS FLOWING). PIPE WAS SPACED OUT & WELL WAS SHUT IN. MONITORED CASING PRESSURE FOR 10 MIN WITH CASING PRESSURE NEVER INCREASING. CHOKES WERE THEN OPENED TO SEE IF WELL WAS FLOWING. NO FLOW WAS SEEN AT SHAKERS AND PUMPS WERE BROUGHT BACK UP TO FINISH CLEAN UP CYCLE THROUGH 2 FULL OPEN CHOKES. ON BOTTOMS UP FROM SHUT IN FLOW INCREASED BY 10%-15%, FLARE WENT F/2’-15’. AFTER BOTTOMS UP FLOW FELL OFF BACK TO NORMAL FLARE STAYING ABOUT 2’-5’. WEIGHT WAS BROUGHT UP TO A 10.2 PPG FROM A 9.5 PPG. WHEN WEIGHT REACHED A 10 PPG COMING OUT FLOW WAS DIVERTED FROM THE CHOKES BACK DOWN THE FLOWLINE PUMPING AT 600 GPM. CIRCULATED A BOTTOMS UP WITH MUD WEIGHT STABILIZING AT A 10.2 PPG. SHUT DOWN PUMPS & CHECKED WELL FOR FLOW AND WELL WAS FLOWING A CONTINUOUS 1" STREAM. PUMPS WERE THEN BROUGHT BACK UP TO 600 GPM & CIRCULATION CONTINUED RAISING MUD WEIGHT UP TO 10.6 PPG. ON BOTTOMS UP FLOW INCREASED 2% TO 5% WITH 2' TO 3' FLARE. AFTER WEIGHT REACHED 10.6 PPG, PUMPS WERE SHUT DOWN AND FLOW WAS CHECKED AGAIN AND WELL WAS FLOWING A 1" STREAM. PUMPS WERE BROUGHT BACK TO 600 GPM AND CIRCULATION WAS CONTINUED. DECISION WAS MADE TO SPOT A MUD CAP. BUILT A 150 BBL 16# MUD CAP AND SPOT @ 10,192'. ESTIMATED TOP OF MUD CAP @ 8,630'. EMW W/ MUD CAP = 11.4+ PPG (0.8+ PPG + 10.6 PPG SYSTEM MUD).
FAT TIRE B 1H | 6 | 2020-12-15 23:30 | 2020-12-16 01:00 | 1.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.75 | 10192 | 10192 | 0 | POOH F/10,192' T/8,019'. HOLE TAKING PROPER FILL ON TRIP OUT.
FAT TIRE B 1H | 6 | 2020-12-16 01:00 | 2020-12-16 01:30 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.77 | 10192 | 10192 | 0 | PERFORM FLOW CHECK-NO FLOW. PUMP SLUG
FAT TIRE B 1H | 6 | 2020-12-16 01:30 | 2020-12-16 05:00 | 3.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.92 | 10192 | 10192 | 0 | POOH F/8,019' T/BHA. HOLE TAKING PROPER FILLS ON TRIP OUT.
FAT TIRE B 1H | 6 | 2020-12-16 05:00 | 2020-12-16 06:00 | 1 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.96 | 10192 | 10192 | 0 | RACK BACK HWDP AND DRILL COLLARS. L/D TOP MONEL AND REMOVE MWD, DRAIN MOTOR, L/D MONEL, L/D BIT AND RACK BACK BHA IN DERRICK
FAT TIRE B 1H | 7 | 2020-12-16 06:00 | 2020-12-16 06:30 | 0.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.98 | 10192 | 10192 | 0 | REMOVED MWD, DRAINED MUD MOTOR, BROKE OUT BIT, & RACKED BACK DIRECTIONAL TOOLS LOST APPROXIMATELY 32 BBLS DURING TRIP
FAT TIRE B 1H | 7 | 2020-12-16 06:30 | 2020-12-16 08:30 | 2 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.06 | 10192 | 10192 | 0 | REMOVED TOP VBR'S & INSTALLED 7-5/8" CSG RAMS THEN TESTED BONNET SEALS T/1000 PSI
FAT TIRE B 1H | 7 | 2020-12-16 08:30 | 2020-12-16 09:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.08 | 10192 | 10192 | 0 | SERVICED RIG & TOP DRIVE
FAT TIRE B 1H | 7 | 2020-12-16 09:00 | 2020-12-16 11:00 | 2 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.17 | 10192 | 10192 | 0 | HELD PJSM THEN RIGGED UP EXPRESS ENERGY'S CASING TOOLS & EQUIPMENT
FAT TIRE B 1H | 7 | 2020-12-16 11:00 | 2020-12-16 23:30 | 12.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.69 | 10192 | 10192 | 0 | HELD PJSM, PICKED UP, MADE UP & TESTED SHOE TRACK, THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR, THEN RAN 224 JTS TOTAL OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, INSTALLED 42 LATCH ON BOW SPRING CENTRALIZERS. 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 3,035'. P/U LANDING JT AND WASH DOWN @ 159 GPM, PP-753 PSI. LAND CASING ON HANGER W/170K (W/O BLOCKS) FLOAT SHOE-10,180.63' TOP OF FLOAT COLLAR-10,087.82' 12-JOINTS LEFT OUT-540.33 ' SEEPAGE LOSSES DURING MOST OF THE RUN, LOSING 75 BBLS TOTAL WITH 30 BBLS LOST DURING LAST 30 JOINT RUN.
FAT TIRE B 1H | 7 | 2020-12-16 23:30 | 2020-12-17 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.71 | 10192 | 10192 | 0 | CIRCULATE 2600 STROKES (200 BBLS) WHILE R/D CASING CREW. GPM-225, PP-770 PSI. PARTIAL RETURNS-LOST APPROXIMATELY 77 BBLS WHILE CIRCULATING. CSG PSI-0, FLARE-0.
FAT TIRE B 1H | 7 | 2020-12-17 | 2020-12-17 00:30 | 0.5 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 4.73 | 10192 | 10192 | 0 | R/D CRT AND M/U CEMENT HEAD TO RIG STANDPIPE
FAT TIRE B 1H | 7 | 2020-12-17 00:30 | 2020-12-17 01:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.77 | 10192 | 10192 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD. GPM-287, SPP: 715 PSI. LOST RETURNS @ 3,200 STROKES (245 BBLS PUMPED) FROM INITIAL CIRCULATION, 45 BBLS PUMPED THROUGH CEMENT HEAD. HEAVIEST MW SEEN-10.8 PPG LOST APPROXIMATELY 275 BBLS OBM
FAT TIRE B 1H | 7 | 2020-12-17 01:30 | 2020-12-17 04:30 | 3 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.9 | 10192 | 10192 | 0 | CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: HLD PJSM, SWAP LINES, TEST CEMENT LINES TO 4,500 PSI. PUMP 40 BBL11.5 PPG GTX SPACER. 280 BBL 11.8 PPG 845 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT. 79 BBL 16.2 PPG 305 SK 1.45 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, WITNESSED PLUG DROP, DISPLACED WITH 463 BBLS OF 10.6 PPG OIL BASE MUD @ 8 BPM. LIFT PRESSURE WAS AT 1300 PSI @ 430 BBLS DISPLACED BEFORE SLOWING PUMPS DOWN TO 3.5 BBLS/MIN FOR LAST 33 BBLS. FINAL LIFT PRESSURE WAS 800 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 1300 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 2 BBLS. FLOATS HELD. PLUG DOWN @ 04:23 HRS ON 12/17/2020. CALCULATED TOC-3,075' NO RETURNS DURING ENTIRE CMT JOB. LOST APPROXIMATELY 862 BBLS OBM.
FAT TIRE B 1H | 7 | 2020-12-17 04:30 | 2020-12-17 05:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.92 | 10192 | 10192 | 0 | TEST CASING TO 3,500 PSI AND HOLD FOR 20 MINUTES. TEST-GOOD.
FAT TIRE B 1H | 7 | 2020-12-17 05:00 | 2020-12-17 06:00 | 1 | P | INTHLCSG | CMT | WOC | WAIT ON CEMENT | 4.96 | 10192 | 10192 | 0 | WAIT ON CEMENT-R/D CEMENT LINES
FAT TIRE B 1H | 8 | 2020-12-17 06:00 | 2020-12-17 09:00 | 3 | P | INTHLCSG | WAIT | WOC | WAIT ON CEMENT | 5.08 | 10192 | 10192 | 0 | MONITORED WELL WHILE WAITING ON CEMENT @ 08:30 HRS 9.5 PPG OBM WAS PUMPED DOWN ANNULAS THROUGH KILL LINE. PUMPED A TOTAL OF 14 BBLS (366') PUMPING AT 3 BPM WHEN HOLE FILLED UP AND HAD RETURNS BACK TO SHAKERS. SHUT DOWN PUMPS & MONITORED WELL FOR FLOW. FLOW WAS NOT DETECTED AT SURFACE
FAT TIRE B 1H | 8 | 2020-12-17 09:00 | 2020-12-17 10:00 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 5.13 | 10192 | 10192 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BAILS AND ELEVATORS.
FAT TIRE B 1H | 8 | 2020-12-17 10:00 | 2020-12-17 11:00 | 1 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.17 | 10192 | 10192 | 0 | MADE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK AND WELLHEAD, WASHED OUT AND FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL AND LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF AND INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 10K, BROKE OUT & LAID DOWN SETTING TOOL.
FAT TIRE B 1H | 8 | 2020-12-17 11:00 | 2020-12-17 12:00 | 1 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.21 | 10192 | 10192 | 0 | NIPPLED DOWN BOPE, ATTACHED BOP WRANGLER, LIFTED STACK & MOVED AWAY FROM WELLHEAD. INSTALLED WELLHEAD CAP, SECURE WELL AND PUT WELL ON HOLD @ 12:00
FAT TIRE B 1H | 8 | 2020-12-17 12:00 | 2020-12-17 12:00 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 5.21 | 10192 | 10192 |  | MILESTONE_HOLD WELL OPERATIONS 1 12/17/2020 @ 12:00
FAT TIRE B 1H | 9 | 2020-12-27 21:00 | 2020-12-27 22:30 | 1.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.27 | 10192 | 10192 | 0 | PREP RIG TO WALK: REMOVE VIBRATOR HOSES, KILL LINE, CHOKE LINE AND PICK UP V-DOOR. WALK CATWALK FORWARD, MOVE CLIMB ASSIST, GERONIMO ANCHORS, WALK RIG F/FAT TIRE A 1H T/FAT TIRE B 1H.
FAT TIRE B 1H | 9 | 2020-12-27 21:00 | 2020-12-27 21:00 | 0 | P | INTHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 5.21 | 10192 | 10192 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 12/27/2020 @ 21:00
FAT TIRE B 1H | 9 | 2020-12-27 22:30 | 2020-12-28 00:30 | 2 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.35 | 10192 | 10192 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, HOOK UP FLOWLINE, REMOVE KILL LINE CHECK VALVE, R/U KILL LINE.
FAT TIRE B 1H | 9 | 2020-12-28 00:30 | 2020-12-28 06:00 | 5.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.58 | 10192 | 10192 | 0 | BEGIN TESTING BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 7000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ORBIT VALVE T/250 LOW/1500 HIGH. REMOVE TEST PLUG AND RIG DOWN TESTERS.
FAT TIRE B 1H | 10 | 2020-12-28 06:00 | 2020-12-28 07:00 | 1 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.63 | 10192 | 10192 | 0 | CONTINUE TESTING BOPE: TEST ORBIT VALVE T/250 LOW/1500 HIGH. REMOVE TEST PLUG AND RIG DOWN TESTERS.
FAT TIRE B 1H | 10 | 2020-12-28 07:00 | 2020-12-28 07:30 | 0.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.65 | 10192 | 10192 | 0 | INSTALL WEAR BUSHING, CLEAN AND ORGANIZE RIG FLOOR.
FAT TIRE B 1H | 10 | 2020-12-28 07:30 | 2020-12-28 08:30 | 1 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.69 | 10192 | 10192 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13522000 JETS 6/18S TFA: 1.491), 5 1/2", 6/7L,11.7 STG @ 2.12° SLICK; .89 REV/GAL; 4.01' BIT TO BEND 5-9/16" PAD OD; FLOW RANGE- 150/350 GPM; MAX DIFF-2,905 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, COUGAR THRUSTER, X/O XT-39 P x DS 42 B, 27 STANDS, DWS AGITATOR. BIT TO SVY-67'. BIT TO GAMMA-57'. TEST MWD (TEST GOOD)
FAT TIRE B 1H | 10 | 2020-12-28 08:30 | 2020-12-28 09:00 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.71 | 10192 | 10192 | 0 | PERFORM DRAW DOWN TEST ON ACCUMULATOR.
FAT TIRE B 1H | 10 | 2020-12-28 09:00 | 2020-12-28 13:00 | 4 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.88 | 10192 | 10192 | 0 | TRIP IN THE HOLE F/BHA' T/10,049', PICK UP AGITATOR AFTER STAND 27. PSI BEFORE AGITATOR- 1230 PSI. PSI AFTER AGITATOR- 1590 PSI @ GPM-275, FILL PIPE EVERY 40 STANDS. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD. CONDUCTED BOP DRILL: RESPONSE TIME= 51 SECONDS.
FAT TIRE B 1H | 10 | 2020-12-28 13:00 | 2020-12-28 14:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.92 | 10192 | 10192 | 0 | RIG SERVICE.
FAT TIRE B 1H | 10 | 2020-12-28 14:00 | 2020-12-28 15:00 | 1 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.96 | 10192 | 10202 | 10 | WASH/REAM THROUGH CEMENT STRINGS F/10,049' T/10,087'. DRILL OUT FLOAT EQUIPMENT AND 10' NEW FORMATION F/10,192' T/10,202', GPM-275, SPP-2700 PSI, RPM-40, TQ-9-12K. NOTE: DID NOT SEE ANY INDICATION OF DRILLING THROUGH FLOAT COLLAR IN DRILLING PARAMETERS, BUT OBSERVED PIECES OF RUBBER ACROSS SHAKERS. OBSERVED INCREASE IN F/9-12K T/12-14K @ 10,135'.
FAT TIRE B 1H | 10 | 2020-12-28 15:00 | 2020-12-28 16:00 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6 | 10202 | 10202 | 0 | CIRCULATE 9.5 MUD WT. AROUND, GPM-300, SPP-2300 PSI, RPM-40, TORQUE INCREASED F/12-14K T/15-17K AND OBSERVED 50-60K OVER PULL, PULLED UP INSIDE OF CSG, TORQUE STARTED STALLING OUT @ 20K.
FAT TIRE B 1H | 10 | 2020-12-28 16:00 | 2020-12-28 17:00 | 1 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.04 | 10202 | 10202 | 0 | TRIP OUT THE HOLE F/10,180' T/9,900', 50-60K OVER PULL, HOLE TOOK CALCULATED FILL NO INDICATION OF SWABBING. CIRCULATE AND RECIPROCATE PIPE @ 80 RPM TO ATTEMPT TO CLEAN OBSTRUCTION OFF BIT, 30-40K OVER PULL, 9/11K. TRIP IN THE HOLE T/10,180'.
FAT TIRE B 1H | 10 | 2020-12-28 17:00 | 2020-12-28 17:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.06 | 10202 | 10202 | 0 | ATTEMPTED TO PERFORM F.I.T @ 10,180' MD / 9,904' TVD W/9.5 PPG OBM FOR A 13.0 PPG EMW. PRESSURE BROKE OVER @ 1,339 PSI FOR 12.0 PPG EWM.
FAT TIRE B 1H | 10 | 2020-12-28 17:30 | 2020-12-28 18:00 | 0.5 | P | INTHLCSG | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.08 | 10202 | 10209 | 14 | BUILD CURVE-SLIDE (7' IN .5 HRS @ 14 FPH) WOB-25/35K, SPM-53/53, GPM-275, MRPM-245, SPP-2300/2600 PSI, DIFF-100/300 PSI. SLIDE DEPTHS: 10202' -10209 TF-HS, 7', 17:30-18:00 NOTE: WEIGHT ON BIT STARTED STACKING OUT AND NOT ABLE TO GET TOOL FACES TO REACT. DECISION WAS MADE TO TRIP OUT THE HOLE AND INSPECT BIT.
FAT TIRE B 1H | 10 | 2020-12-28 18:00 | 2020-12-28 18:30 | 0.5 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.1 | 10209 | 10209 | 0 | CIRCULATE @ 10,190' W/ MIXING SLUG, GPM=275, SPP=2200/2400, RPM=30, TRQ=12/17K, MAX GAS= 1637 UNITS, MUD WT=9.5PPG, NO MUD CUT, NO FLARE, NO LOSSES.
FAT TIRE B 1H | 10 | 2020-12-28 18:30 | 2020-12-28 19:30 | 1 | U | INTHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 6.15 | 10209 | 10209 | 0 | FLOW CHECK WELL, WELL FLOWING 10 BARRELS HOUR, SHUT WELL IN, MONITOR SHUT IN CASING PRESSURE. SHUT IN CASING PRESSURE STABLE @ 0 PSI F/ 15 MINUTES, SHUT IN CASING PRESSURE BEGIN BUILDING PRESSURE AFTER 17 MINUTES, SHUT IN CASING INCREASED T/ 252 PSI IN 38 MINUTES. NOTE: BUILDING 16.1 PPG MUD CAP W/ MONITORING SHUT IN CASING PRESSURE.
FAT TIRE B 1H | 10 | 2020-12-28 19:30 | 2020-12-28 20:00 | 0.5 | U | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.17 | 10209 | 10209 | 0 | CIRCULATE @ 10,188', GPM=275, SPP=2000/2100, RPM=30, TRQ=12/16K, MAX GAS= 2214 UNITS, MUD CUT 9.5 PPG T/ 9.4 PPG, FLARE= 2'-5', NO LOSSES.
FAT TIRE B 1H | 10 | 2020-12-28 20:00 | 2020-12-28 21:30 | 1.5 | U | INTHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 6.23 | 10209 | 10209 | 0 | SHUT WELL IN, MONITOR SHUT IN CASING PRESSURE. SHUT IN CASING PRESSURE STABLE @ 0 PSI F/ 20 MINUTES, SHUT IN CASING PRESSURE BEGIN BUILDING PRESSURE AFTER 25 MINUTES, SHUT IN CASING INCREASED T/ 163 PSI IN 45 MINUTES. NOTE: BUILDING 16.1 PPG MUD CAP W/ MONITORING SHUT IN CASING PRESSURE.
FAT TIRE B 1H | 10 | 2020-12-28 21:30 | 2020-12-28 22:00 | 0.5 | U | INTHLCSG | WCTRL |  | KILL WELL | 6.25 | 10209 | 10209 | 0 | SPOT 55 BBL 16.1 PPG OBM MUD CAP @ 10,172' (100 PSI OVER BALANCE MUD CAP). SHUT IN AND MONITORED CASING PRESSURE. SICP= BEFORE CAP-163 PSI / AFTER-0 PSI TOP OF MUD CAP-8083' AFTER PULLING ABOVE MUD CAP.
FAT TIRE B 1H | 10 | 2020-12-28 22:00 | 2020-12-28 23:30 | 1.5 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.31 | 10209 | 10209 | 0 | STRIP OUT OF HOLE F/10,172’ T/7,937’ WITH DRY PIPE, PUMPING CALCULATED HOLE FILL .7 BBLS PER STAND DOWN BACKSIDE W/9.5 PPG OBM. NOTE: INITIALLY 50-100K OVERPULL WHEN STARTING TO STRIP OUT OF HOLE. OBSERVED FLUCTUATION ON WEIGHT INDICATOR @ 8,038' INDICATING THE THE PLUG POSSIBLY FELL OFF.
FAT TIRE B 1H | 10 | 2020-12-28 23:30 | 2020-12-29 | 0.5 | U | INTHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 6.33 | 10209 | 10209 | 0 | FLOW CHECK WELL ON TRIP TANK, WELL FLOWING 1 BARREL HOUR, SHUT WELL IN, MONITOR SHUT IN CASING PRESSURE, SICP= 0 PSI.
FAT TIRE B 1H | 10 | 2020-12-29 | 2020-12-29 01:30 | 1.5 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.4 | 10209 | 10209 | 0 | STRIP OUT OF HOLE F/7,937’ T/5,939’ WITH WET PIPE, PUMPING CALCULATED HOLE FILL 1.8 BBLS PER STAND DOWN BACKSIDE W/15.9 PPG OBM. PUMP TOTAL OF 36 BBLS OF 15.9 PPG OBM DOWN BACKSIDE.
FAT TIRE B 1H | 10 | 2020-12-29 01:30 | 2020-12-29 02:00 | 0.5 | U | INTHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 6.42 | 10209 | 10209 | 0 | FLOW CHECK WELL ON FLOWLINE 20 STDS ABOVE TOP OF MUD CAP, MONITOR FOR 30 MIN, NO FLOW, LINE UP ON TRIP TANK TO POOH W/9.5 PPG OBM
FAT TIRE B 1H | 10 | 2020-12-29 02:00 | 2020-12-29 04:00 | 2 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.5 | 10209 | 10209 | 0 | POOH F/5,939' T/3,447' MONITORING HOLE FILL ON TRIP TANK, HOLE TAKING PROPER FILL
FAT TIRE B 1H | 10 | 2020-12-29 04:00 | 2020-12-29 04:30 | 0.5 | U | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 6.52 | 10209 | 10209 | 0 | FLOW CHECK WELL @ 3,447' BEFORE REMOVING ROT. HEAD (NO FLOW); REMOVE ROT. HEAD/INSTALL TRIP NIPPLE
FAT TIRE B 1H | 10 | 2020-12-29 04:30 | 2020-12-29 06:00 | 1.5 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.58 | 10209 | 10209 | 0 | POOH F/3,447' T/BHA MONITORING HOLE FILL ON TRIP TANK, HOLE TAKING PROPER FILL
FAT TIRE B 1H | 11 | 2020-12-29 06:00 | 2020-12-29 07:00 | 1 | U | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 6.63 | 10209 | 10209 | 0 | REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR, BREAK OUT BIT AND MAKE UP NEW BIT. INSTALL AND TEST MWD (TEST GOOD). NOTE: INSPECTED MOTOR AND BIT, NO VISUAL DAMAGE TO THE MOTOR, OBSERVED 1 BIT JET WAS PLUGGED WITH RUBBER AND SHARDS OF METAL FROM THE FLOAT COLLAR, OBSERVED CHIPPED CUTTERS ON SHOULDER, GAUGE AND INNERS.
FAT TIRE B 1H | 11 | 2020-12-29 07:00 | 2020-12-29 07:30 | 0.5 | U | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 6.65 | 10209 | 10209 | 0 | CLEAN AND ORGANIZE RIG FLOOR.
FAT TIRE B 1H | 11 | 2020-12-29 07:30 | 2020-12-29 10:00 | 2.5 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.75 | 10209 | 10209 | 0 | TRIP IN THE HOLE F/BHA T/6,442', PICK UP AGITATOR AFTER STAND 27, FILL PIPE EVERY 40 STANDS. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD. FLOW CHECK @ 2,784', NO FLOW. MONITOR DISPLACEMENTS ON TRIP TANK. 128 BBLS CALCULATED DISPLACEMENT T/6,442', 86.3 BBLS ACTUAL DISPLACEMENT.
FAT TIRE B 1H | 11 | 2020-12-29 10:00 | 2020-12-29 11:00 | 1 | U | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.79 | 10209 | 10209 | 0 | RIG SERVICE WHILE WELL ON TRIP TANK, NO FLOW.
FAT TIRE B 1H | 11 | 2020-12-29 11:00 | 2020-12-29 12:00 | 1 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.83 | 10209 | 10209 | 0 | CONTINUE TRIPPING IN THE HOLE F/6,442' T/10,208', FILL PIPE EVERY 40 STANDS. MONITOR DISPLACEMENTS ON TRIP TANK. 76.1 BBLS CALCULATED DISPLACEMENT T/10,208', 55.6 BBLS ACTUAL DISPLACEMENT. OBSERVED 9.8 PPG T/13.6 PPG DISPLACMENT MUD WT. F/6,900' T/8,933'. NOTE: DIVERTED 45 BBLS MUD CAP F/ TRIP TANK TO FRAC TANK.
FAT TIRE B 1H | 11 | 2020-12-29 12:00 | 2020-12-29 13:30 | 1.5 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.9 | 10209 | 10209 | 0 | SLOWLY STAGE UP PUMPS T/246 GPM, CIRCULATE OUT MUD CAP AND FAN OVER RUBBER TO ATTEMPT TO BREAK UP RUBBER PLUG, WOB-5/10K, SPM-47/47, GPM-246, RPM: 20, TRQ: 10/12K, SPP: 2300 PSI. CHOKES-100% / 0%, FLARE= 1'-2', MUD CUT F/9.5 PPG T/9.4 PPG, MAX GAS: 2045u, MAX CASING PRESSURE=190 PSI, MAX MUD WT. OUT= 13.9 PPG. NOTE: DIVERTED 65 BBLS MUD CAP TO OPEN TOP TANK.
FAT TIRE B 1H | 11 | 2020-12-29 13:30 | 2020-12-29 13:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.9 | 10209 | 10209 |  | MILESTONE_START CURVE SECTION ON 12/29/2020 @ 13:30
FAT TIRE B 1H | 11 | 2020-12-29 13:30 | 2020-12-30 | 10.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.33 | 10209 | 11095 | 84.4 | BUILD CURVE-SLIDE (625' IN 6.98 HRS @ 89.54 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-356, SPP-4000/4700 PSI, DIFF-500/700 PSI, CHOKES-100% / 100%,FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI. NOTE: STARTED CUTTING MUD WT. BACK F/9.5 PPG T/9.0 PPG @ 10,334'. NOTE: AT 10,827' MD LOST TOTAL RETURNS, REDUCE PUMP RATE F/ 400 GPM T/ 330 GPM, CUT MUD WEIGHT F/ 9.0 PPG T/ 8.6 PPG, DIVERT RETURNS THROUGH GAS BUSTER T/ FLOWLINE ACROSS SHAKERS, RE-GAIN PARTIAL RETURNS (15%-20%) @ 10,938', LOSSES @ 300-350 BARRELS PER HOUR, PUMP (2) 50 BARREL LCM PILLS @ 20 PPB, PUMP (2) 50 BARRELS LCM PILLS @ 30 PPB, LCM PILLS CONSIST OF - MAGMA FIBER FINE, FIRST RESPONSE, SYN SEAL, NEWCARB, NUT PLUG AND ADDING LCM IN ACTIVE SYSTEM, DECISION MADE T/ GO ON MUD CAP @ 11,134' MD. SLIDE DEPTHS: SLD F/10209 T/10400 191', TF-HS, 1335-1622 SLD F/10488 T/10524 36', TF-HS, 1710-1739
FAT TIRE B 1H | 11 | 2020-12-30 | 2020-12-30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 7.33 | 11095 | 11095 |  | MILESTONE_LAND/END CURVE SECTION ON 12/30/2020 @ 0000
FAT TIRE B 1H | 11 | 2020-12-30 | 2020-12-30 01:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.38 | 11095 | 11134 | 39 | SLIDE (39' IN 1 HRS @ 39 FPH) WOB: 35/40K, SPM- 63/63, GPM-330, MRPM-294, SPP: 2600/3100 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/11095 T/11134 39' TF-HS 0000-0100
FAT TIRE B 1H | 11 | 2020-12-30 | 2020-12-30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 7.33 | 11095 | 11095 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 12/30/2020 @ 0000
FAT TIRE B 1H | 11 | 2020-12-30 01:00 | 2020-12-30 02:00 | 1 | P | PRDHLLT | LCIRC |  | LOST CIRCULATION | 7.42 | 11134 | 11134 | 0 | DECISION WAS MADE TO DRILL ON MUD CAP W/ NO RETURNS, BEGIN PUMPING DRILLING WATER DOWN DRILLPIPE WHILE WELL WAS SHUT IN, CASING PRESSURE INCRESED T/ 800 PSI, SHUT DOWN DRILLING OPERATIONS, PUMP 70 BARRELS 13.9 PPG KILL MUD, STAGE MUD PUMPS F/ 26 GPM T/ 236 GPM W/ NO CASING PRESSURE.
FAT TIRE B 1H | 11 | 2020-12-30 02:00 | 2020-12-30 02:30 | 0.5 | P | PRDHLLT | DRLG |  | DRILLING OPERATIONS | 7.44 | 11134 | 11144 | 20 | SLIDE (39' IN 1 HRS @ 39 FPH) WOB: 35/40K, SPM- 63/63, GPM-330, MRPM-294, SPP: 2600/3100 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/11134' T/11284' TF-HS 0148-0205
FAT TIRE B 1H | 11 | 2020-12-30 02:30 | 2020-12-30 03:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.46 | 11144 | 11190 | 92 | ROT (46' IN .5 HRS @ 92 FPH) WOB-35/45K SPM-63/63, GPM-330, RPM-50, MRPM-294, TMRPM-344, TRQ-10/12K, SPP-2600/3700 PSI, DIFF-1000/1200 PSI, NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI.
FAT TIRE B 1H | 11 | 2020-12-30 03:00 | 2020-12-30 04:00 | 1 | U | PRDHLLT | RIGMT | SVCMD | SERVICE MUD PUMPS / CIRC EQUIP | 7.5 | 11190 | 11190 | 0 | TROUBLE SHOOT MUD PUMPS; #2 MUD PUMP WOULD NOT COME ON LINE, RESET RECTIFIERS; FOUND LOOSE FIBER OPTIC CONNECTION.
FAT TIRE B 1H | 11 | 2020-12-30 04:00 | 2020-12-30 05:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.54 | 11190 | 11218 | 28 | SLIDE (28' IN 1 HRS @ 28 FPH) WOB: 35/40K, SPM- 63/63, GPM-330, MRPM-294, SPP: 2600/3100 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/11190 T/11218 28' TF-120L 0400-0510
FAT TIRE B 1H | 11 | 2020-12-30 05:00 | 2020-12-30 06:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.58 | 11218 | 11284 | 66 | ROT (66' IN 1 HRS @ 66 FPH) WOB-35/45K SPM-63/63, GPM-330, RPM-50, MRPM-294, TMRPM-344, TRQ-10/12K, SPP-2600/3700 PSI, DIFF-1000/1200 PSI, NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI.
FAT TIRE B 1H | 12 | 2020-12-30 06:00 | 2020-12-30 11:00 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.79 | 11284 | 11986 | 140.4 | ROT (702' IN 5.12 HRS @ 137.1 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-14/15K, SPP-3700/5100 PSI, DIFF-1200/1400 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND, CASING PRESSURE WHILE DRILLING= 100/200 PSI, SICP= 0 PSI. NOTE: CASING PRESSURE INCREASED T/455 PSI, PUMPED 10 BBL 16.0 PPG MUD CAP @ 11,284'. CASING PRESSURE INCREASED T/255 PSI, PUMPED 20 BBL 16.0 PPG MUD CAP @ 11,304'.
FAT TIRE B 1H | 12 | 2020-12-30 11:00 | 2020-12-30 12:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.85 | 11986 | 12040 | 36 | SLIDE (55' IN 1.38 HRS @ 39.9 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-356, SPP-3700/4200 PSI, DIFF-300/500 PSI. SLIDE DEPTHS: SLD F/11284' T/11309' 25' TF-180 0603-636 SLD F/11389' T/11399' 10' TF-180 725-739 SLD F/11861' T/11881' TF-70R 1048-1121
FAT TIRE B 1H | 12 | 2020-12-30 12:30 | 2020-12-30 14:00 | 1.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 7.92 | 12040 | 12040 | 0 | BACK REAM F/12,041' T/11,851', SPM-76/76, GPM-400, RPM-80, TRQ-10/14K, SPP-3700 PSI. RE-LOG GAMMA F/11,851' T/11,946' (GAMMA DEPTHS F/11,794' T/11,889') AS PER GEOLOGY. WASH/REAM F/11,946' T/12,041', SPM-76/76, GPM-400, RPM-80, TRQ-12/14K, SPP-3700 PSI.
FAT TIRE B 1H | 12 | 2020-12-30 14:00 | 2020-12-30 14:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.94 | 12040 | 12125 | 170 | ROT (85' IN .63 HRS @ 134.9 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-15/17K, SPP-3700/5100 PSI, DIFF-1200/1400 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND, CASING PRESSURE WHILE DRILLING= 100/250 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 12 | 2020-12-30 14:30 | 2020-12-30 15:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.96 | 12125 | 12135 | 20 | SLIDE (10' IN .37 HRS @ 27.0 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-356, SPP-3700/4200 PSI, DIFF-300/500 PSI. SLIDE DEPTHS: SLD F/12051' T/12061 TF-180 1412-1434
FAT TIRE B 1H | 12 | 2020-12-30 15:00 | 2020-12-30 16:00 | 1 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8 | 12135 | 12135 | 0 | CASING PRESSURE INCREASED T/252 PSI @ 12,135'. OPENED CHOKES AND BLEED OFF CASING PRESSURE WHILE CIRCULATING @ 400 GPM (9.5 BPM), OPENED ORBIT VALVE AND CLOSED CHOKES, DIVERTED RETURNS DOWN FLOW LINE TO TRIP TANK TO ATTEMPT ESTABLISH CIRCULATION.. RETURNS STARTED @ 10% AND GAINED .9 BBLS IN 1 MINUTE, RETURNS INCREASED T/60% AND 5.7 BBLS GAINED IN 1 MINUTE, RETURNS INCREASED TO 65% AND GAINED 6.19 BBLS IN 1 MINUTE, RETURNS INCREASED TO 67% AND GAINED 6.4 BBLS IN 1 MINUTE. OPEN CHOKES 100% / 100% AND CLOSED ORBIT VALVE, DIVERTED RETURNS THROUGH CHOKES TO TRIP TANK, RETURNS STARTED @ 50% AND GAINED 4.8 BBLS IN 1 MINUTE, RETURNS INCREASED TO 68% AND GAINED 6.5 BBLS IN 1 MINUTE, INDICATION OF GAS BUBBLE MIGRATING UP THE HOLE. SHUT DOWN PUMPS AND CLOSED CHOKES. PUMPED A TOTAL OF 86 BBLS AND GAINED 51.8 BBLS IN TRIP TANKS. MONITORED SICP, SICP= 401. PUMPED 20 BBL 16.0 PPG MUD CAP AND CASING DECREASED TO 0 PSI. ATTEMPTED TO START DRILLING AND CASING PRESSURE INCREASED T/812 PSI, PUMPED 40 BBL 16.0 PPG MUD CAP AND CASING DECREASED TO 0 PSI. ATTEMPTED TO START DRILLING AND CASING PRESSURE INCREASED T/759 PSI, PUMPED 50 BBL 16.0 PPG MUD CAP AND CASING DECREASED TO 0 PSI. PUMPED A TOTAL OF 110 BBLS MUD CAP.
FAT TIRE B 1H | 12 | 2020-12-30 16:00 | 2020-12-30 18:30 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.1 | 12135 | 12403 | 107.2 | ROT (268' IN 2.42 HRS @ 110.7 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-11/15K, SPP-4300/5000 PSI, DIFF-500/700 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND, CASING PRESSURE WHILE DRILLING= 100/250 PSI, SICP= 0 PSI. NOTE: CASING PRESSURE INCREASED T/174 PSI, PUMPED 43 BBL 16.0 PPG MUD CAP @ 12,184'. MAX CASING PRESSURE=537 PSI WHILE PUMPING MUD CAP, CASING PRESSURE DECREASED TO 0 PSI AFTER PUMPING 43 BBL 16.0 PPG MUD CAP, 0 PSI CASING PRESSURE W/ DRILLING.
FAT TIRE B 1H | 12 | 2020-12-30 18:30 | 2020-12-30 19:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.13 | 12403 | 12434 | 62 | SLIDE (31' IN .58 HRS @ 53.4 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-356, SPP-4300/4800 PSI, DIFF-300/500 PSI. SLIDE DEPTHS: SLD F/12338' T/12358 20' TF-20R 1740-1816
FAT TIRE B 1H | 12 | 2020-12-30 19:00 | 2020-12-30 20:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.17 | 12434 | 12434 | 0 | FROM 12,423' TO 12,434' OBSERVED CONTINIOUS GAMMA INCREASE FROM 68 TO 130, NOTIFIED GEOLOGIST OF INCREASE IN GAMMA READINGS, STOP DRILLING OPERATIONS, PULL OUT OF HOLE T/ 12,325', CIRCULATE AND RECIPROCATE DRILL STRING WHILE GEOLOGIST VERIFY POSITION IN WELLBORE TARGET, GPM=400, SPP=4100/4200, RPM=80, TORQUE=7/9K, CASING PSI=0PSI
FAT TIRE B 1H | 12 | 2020-12-30 20:00 | 2020-12-31 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.33 | 12434 | 12577 | 35.8 | SLIDE (143' IN 3.88 HRS @ 37 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-356, SPP-4300/4800 PSI, DIFF-300/500 PSI. SLIDE DEPTHS: SLD F/12423-12434 11' TF-20R 1845-1900 SLD F/12434-12463 29' TF-HS 2010-2100 SLD F/12518-12530 12' TF-HS 2125-2143 SLD F/12613-12638 25' TF-170L 2215-2240 SLD F/12709-12725 16' TF-180 2310-2330 SLD F/12914-12930 16' TF-160L 0030-0055 SLD F/13095-13109 14' TF-20L 0155-0220 SLD F/13284-13300 16' TF-130L 0320-0350 SLD F/13374-13389 15' TF-160R 0420-0450 NOTE: PUMPED 20 BBLS OF 16.0 PPG MUD DOWN BACKSIDE @ 13,387'
FAT TIRE B 1H | 12 | 2020-12-31 | 2020-12-31 06:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.58 | 12577 | 13564 | 164.5 | ROT (987' IN 6.12 HRS @ 161 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-11/18K, SPP-4300/5400 PSI, DIFF-900/1100 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND, CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 13 | 2020-12-31 06:00 | 2020-12-31 07:30 | 1.5 |  | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.65 | 13564 | 13950 | 257.3 | ROT (386' IN 1.5 HRS @ 257.3 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-15/17K, SPP-4300/5600 PSI, DIFF-1100/1300 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 13 | 2020-12-31 07:30 | 2020-12-31 08:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.69 | 13950 | 13950 | 0 | CIRCULATE @ 400 GPM WHILE TROUBLE SHOOTING FAULT ON TOP DRIVE BLOWER MOTOR, ADJUSTED PRESSURE SENSOR.
FAT TIRE B 1H | 13 | 2020-12-31 08:30 | 2020-12-31 10:30 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.77 | 13950 | 14289 | 169.5 | ROT (339' IN 2.07 HRS @ 163.8 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-15/17K, SPP-4400/5700 PSI, DIFF-1100/1300 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI. NOTE: PUMPED 20 BBL 16.0 PPG MUD CAP @ 14,110'.
FAT TIRE B 1H | 13 | 2020-12-31 10:30 | 2020-12-31 11:30 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.81 | 14289 | 14319 | 30 | SLIDE (30' IN .93 HRS @ 32.3 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-356, SPP-4300/4800 PSI, DIFF-300/500 PSI. SLIDE DEPTHS: SLD F/14046' T/14058 12' TF-180 915-945 SLD F/14235' T/14253 18' TF-140L 1045-1111
FAT TIRE B 1H | 13 | 2020-12-31 11:30 | 2020-12-31 12:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.83 | 14319 | 14319 | 0 | CIRCULATE @ 294 GPM WHILE CHANGING OUT DRAW WORKS POWER CABLE ON VFD DUE TO A GROUND FAULT.
FAT TIRE B 1H | 13 | 2020-12-31 12:00 | 2020-12-31 16:30 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.02 | 14319 | 14895 | 128 | ROT (576' IN 4.22 HRS @ 136.5 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-15/21K, SPP-4300/5400 PSI, DIFF-1000/1100 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI. NOTE: PUMPED 20 BBL 16.0 PPG MUD CAP @ 14,910
FAT TIRE B 1H | 13 | 2020-12-31 16:30 | 2020-12-31 18:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.08 | 14895 | 14944 | 32.7 | SLIDE (49' IN 1.78 HRS @ 27.5 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-356, SPP-4300/5000 PSI, DIFF-500/700 PSI. SLIDE DEPTHS: SLD F/14330' T/14340' 10' TF-180 1223-1242 SLD F/14424' T/14436' 12 TF-180 1340-1358 SLD F/14800' T/14812' 12' TF-140L 1600-1636 SLD F/14927' T/14942' 15' TF-HS 1715-1749
FAT TIRE B 1H | 13 | 2020-12-31 18:00 | 2020-12-31 21:00 | 3 | P | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 9.21 | 14944 | 14944 | 0 | BACK REAM OUT OF HOLE F/ 14,944' T/ 14,036' DUE T/ INCREASE IN DRILLING TORQUE TO 17/23K STALLING OUT TOP DRIVE, PARAMETERS WHILE BACK REAMING T/ 14,036' GPM=400, SPP=3900/4000, RPM=80, TORQUE=9/20K, PAREMETERS AFTER REAMING BACK IN HOLE TO 14,920, GPM=400, SPP=3900/4000, RPM=80, TORQUE=7/16K. NOTE: AT 14,925' PUMP PRESSURE INCREASED TO 4900 PSI, DIFF. PSI=700/800 PSI, TORQUE=18/23K, WOB=20/25K. ATTEMPT TO WASH AND REAM TO 14,944', PICKED UP TO 14,920' REDUCE PUMP RATE GPM=350, SPP=3800/3900, TORQUE=10/14K. NOTE: PUMP 50 BBLS 16.0 PPG MUD CAP 19:30 WHILE BACK REAMING OUT OF HOLE
FAT TIRE B 1H | 13 | 2020-12-31 21:00 | 2020-12-31 23:00 | 2 | P | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 9.29 | 14944 | 14944 | 0 | CONTINUE WASHING AND REAMING TIGHT HOLE F/ 14,925' T/ 14,944' PUMPING 20 BARREL SWEEPS EVERY 308 BARRELS = ANNULUS CAPACITY 108 BBLS, DRILL PIPE CAPACITY 200 BBLS ( CALCULATED VOLUME TO LOSS AREA @ 10,827') PUMP TOTAL OF 100 BARRELS SWEEPS. GPM=350, SPP=3800/6150, DIFF=500/2300, WOB= 10/40K, RPM=80, TORQUE= 10/23K.
FAT TIRE B 1H | 13 | 2020-12-31 23:00 | 2021-01-01 03:00 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.46 | 14944 | 14950 | 1.5 | ROT (6' IN 3 HRS @ 2 FPH) WOB-35/45K SPM-67/67, GPM-351, RPM-80, MRPM-312, TMRPM-392, TRQ-15/22K, SPP-3900/4700 PSI, DIFF-600/800 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 13 | 2021-01-01 03:00 | 2021-01-01 06:00 | 3 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.58 | 14950 | 14950 | 0 | BACK REAM OUT OF HOLE F/ 14,950' T/ 12,800' DUE T/ INSUFFICIENT ROP, PARAMETERS WHILE BACK REAMING, GPM=400, SPP=3900/4000, RPM=80, TORQUE=9/20K
FAT TIRE B 1H | 14 | 2021-01-01 06:00 | 2021-01-01 08:30 | 2.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.69 | 14950 | 14950 | 0 | CONTINUE BACK REAMING OUT OF HOLE F/12,800' T/10,788' DUE T/ INSUFFICIENT ROP, PARAMETERS WHILE BACK REAMING, GPM=400, SPP=3900/4000, RPM=80, TORQUE=9/23K. NOTE: TORQUE DECREASED F/ 9/23K T/ 9/19K @ 12,211', TORQUE DECREASED T/8/17 @11,992', REDUCED RPM F/80 RPM T/30 RPM @ 11,548'. TORQUE= 7/15K, TURN OFF ROTARY AND PUMPED OUT THE HOLE F/11,168' T/11,072' DUE TO 19.14° DOG LEG @ 11,124'. CONTINUE BACK REAMING OUT OF HOLE F/ 11,072' T/10,788' @ 30 RPM, TORQUE= 7/12K.
FAT TIRE B 1H | 14 | 2021-01-01 08:30 | 2021-01-01 14:00 | 5.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.92 | 14950 | 14950 | 0 | TRIP OUT THE HOLE F/10,788' T/6,446', FILLING ANNULUS WITH 1.9 BBLS/STD CALCULATED 9.0 PPG OBM. CASING INCREASED T/275 PSI @ 6,446' WHILE PUMPING 9.0 PPG DOWN ANNULUS, CONTINUE TRIPPING OUT THE HOLE F/6,446' T/5,516', FILLING ANNULUS WITH 1.9 BBL/STD CALCULATED 16.0 PPG KILL MUD (PUMP 20 BBLS). CONTINUE TRIPPING OUT THE HOLE F/5,516' T/BHA, FILLING ANNULUS WITH 1.9 BBL/STD CALCULATED 9.0 PPG OBM. FLOW CHECK @ 2,895' (NO FLOW), REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, L/D AGITATOR ON STAND 27.
FAT TIRE B 1H | 14 | 2021-01-01 14:00 | 2021-01-01 15:30 | 1.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.98 | 14950 | 14950 | 0 | REMOVE MWD, RACK BACK MONELS, L/D THRUSTER. NOTE: LEFT LOWER END OF MOTOR AND BIT IN THE HOLE.
FAT TIRE B 1H | 14 | 2021-01-01 15:30 | 2021-01-01 16:30 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.02 | 14950 | 14950 | 0 | SLIP AND CUT 80' OF DRILL LINE WHILE MONITORING SICP, SICP= 0 PSI.
FAT TIRE B 1H | 14 | 2021-01-01 16:30 | 2021-01-01 17:00 | 0.5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 10.04 | 14950 | 14950 | 0 | RIG SERVICE WHILE MONITORING SICP, SICP= 0 PSI.
FAT TIRE B 1H | 14 | 2021-01-01 17:00 | 2021-01-01 18:00 | 1 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 10.08 | 14950 | 14950 | 0 | PICK UP 6.75" SECURITY GTD64M SER 1352001 JETS 6/18S TFA: 1.491), 5 1/2", 6/7L,8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.0' BIT TO BEND, 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,021 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, COUGAR THRUSTER, X/O XT-39 P x DS 42 B, 27 STANDS, DWS AGITATOR. BIT TO SVY-65'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD).
FAT TIRE B 1H | 14 | 2021-01-01 18:00 | 2021-01-01 23:30 | 5.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.31 | 14950 | 14950 | 0 | TRIP IN THE HOLE F/BHA T/10,713', PICK UP AGITATOR AFTER STAND 27. PSI BEFORE AGITATOR- 920 PSI. PSI AFTER AGITATOR- 1275 PSI @ GPM-262, FILL PIPE EVERY 40 STANDS. PUMP CALCULATED DISPLACEMENT 1.9 BBLS PER STAND DOWN BACKSIDE (10.0 PPG). REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD. NOTE: AT 2900' PUMP 50 BBLS 16.0 PPG DOWN BACKSIDE DUE TO REGAINING PARTIAL RETURNS.
FAT TIRE B 1H | 14 | 2021-01-01 23:30 | 2021-01-02 02:30 | 3 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 10.44 | 14950 | 14950 | 0 | WASH/REAM F/10,713' T/10,998', GPM=351, SPP=3200/3400, RPM=30, TORQUE=5/7K. TURN OFF ROTARY, WASH F/10,998' T/11,188', CONTINUE WASHING/REAMING F/11,188' T/12,038', GPM=351, SPP=3200/3400, RPM=30, TORQUE=5/7K. TRIP IN THE HOLE F/12,038' T/12,950' W/ 30/70K DRAG, CONTINUE WASHING/REAMING F/12,950' T/13,173', PICKUP TO 13,075' TO BUILD TROUGH FOR SIDE TRACK OPERATIONS. NOTE: CHECK SHOT SURVEYS @ 11,218', 11313', 11,409', 11503'.
FAT TIRE B 1H | 14 | 2021-01-02 02:30 | 2021-01-02 04:30 | 2 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 10.52 | 14950 | 14950 | 0 | BUILD TROUGH F/13,075' T/13,095' @ 110R, GPM-400,SPP-4250 PSI. NOTE: PUMP TOTAL OF 120 BBL 16 PPG KILL MUD DOWN BACKSIDE; MAX CSG PSI 200
FAT TIRE B 1H | 14 | 2021-01-02 04:30 | 2021-01-02 06:00 | 1.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 10.58 | 14950 | 14950 | 0 | BEGIN SIDETRACKING @ 13,095' MD / 10,419' TVD ON 1/02/2021 @ 04:30. TIME DRILLING F/13,095' T/13096' @ 1'/HR, GPM-400, SPP-4600 PSI, DRILLING UNDER MUD CAP WITH WATER, CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 15 | 2021-01-02 06:00 | 2021-01-02 09:00 | 3 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 10.71 | 14950 | 13100 | -616.7 | TIME DRILL F/13,095' T/13,100' @ 1 FPH, TF-110R, WOB-10/20K, GPM-400, SPP-4600/4700 PSI, DIFF-50-100 PSI. DRILLING UNDER MUD CAP WITH WATER, MAX CASING PRESSURE WHILE DRILLING= 52 PSI. NOTE: PUMPED 20 BBL 16.0 PPG MUD CAP @ 13,097'
FAT TIRE B 1H | 15 | 2021-01-02 09:00 | 2021-01-02 09:00 | 0 | U | PRDHLLT | MSTN | KOST | MILESTONE_KICK OFF SIDETRACK | 10.71 | 13100 | 13100 |  | MILESTONE_KICK OFF SIDETRACK ON 1/02/2021 @ 09:00
FAT TIRE B 1H | 15 | 2021-01-02 09:00 | 2021-01-02 12:00 | 3 | U | PRDHLLT | DRLG | CTLDRL | CONTROL DRILLING | 10.83 | 13100 | 13130 | 10 | CONTROL SLIDE DRILL F/13,100' T/13,130' @ 5-30 FPH, TF-110R, WOB-35/45K, GPM-400, SPP-4600/4950 PSI, DIFF-150-350 PSI. DRILLING UNDER MUD CAP WITH WATER, MAX CASING PRESSURE WHILE DRILLING= 0 PSI.
FAT TIRE B 1H | 15 | 2021-01-02 12:00 | 2021-01-02 19:00 | 7 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.13 | 13130 | 13920 | 112.9 | ROT (790' IN 6.35 HRS @ 124 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-15/20K, SPP-4800/5600 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI. NOTE: PUMPED 50 BBL 16.0 PPG MUD CAP @ 13,178' PUMPED 20 BBL 16.0 PPG MUD CAP @ 13,615' PUMPED 20 BBL 16.0 PPG MUD CAP @ 14,178'
FAT TIRE B 1H | 15 | 2021-01-02 19:00 | 2021-01-02 22:00 | 3 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.25 | 13920 | 14033 | 37.7 | SLIDE (113' IN 3.65 HRS @ 31 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-4800/5400 PSI, DIFF-300/600 PSI. SLIDE DEPTHS: SLD F/13285' T/13300' 15' TF-60R 1357-1428 SLD F/13476' T/13494' 18' TF-150L 1547-1642 SLD F/13571' T/13591' 20' TF-90L 1717-1800 SLD F/13656' T/13696' 40' TF-90L 1835-1935 SLD F/13855' T/13875' 20' TF-90L 2045-2115
FAT TIRE B 1H | 15 | 2021-01-02 22:00 | 2021-01-02 23:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.29 | 14033 | 14033 | 0 | CIRCULATE WHILE WAITING ON GEOLOGY
FAT TIRE B 1H | 15 | 2021-01-02 23:00 | 2021-01-03 03:30 | 4.5 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.48 | 14033 | 14634 | 133.6 | ROT (601' IN 4.67 HRS @ 129 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-15/20K, SPP-4800/5600 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 15 | 2021-01-03 03:30 | 2021-01-03 06:00 | 2.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.58 | 14634 | 14693 | 23.6 | SLIDE (59' IN 2.33 HRS @ 25 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-4800/5400 PSI, DIFF-300/600 PSI. SLIDE DEPTHS: SLD F/14137' T/14159' 22' TF-90R 2355-0045 SLD F/14415' T/14440' 25' TF-150R 0235-0340 SLD F/14599' T/14611' 12' TF-180 0505-0530
FAT TIRE B 1H | 16 | 2021-01-03 06:00 | 2021-01-03 08:00 | 2 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.67 | 14693 | 14950 | 128.5 | ROT (257' IN 2.0 HRS @ 128.5 FPH) WOB-25/35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-15/20K, SPP-4800/5800 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI. NOTE: OFF SIDETRACK OPERATIONS NPT @ 14,950' ON 1/03/2021 @ 08:00.
FAT TIRE B 1H | 16 | 2021-01-03 08:00 | 2021-01-03 13:30 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.9 | 14950 | 15686 | 133.8 | ROT (736' IN 5.55 HRS @ 132.6 FPH) WOB-25/35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/20K, SPP-4800/5800 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI. NOTE: CONTROL DRILLED @ 120 FPH F/14,850' T/15,100' WOB-15/25K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-14/18K, SPP-4800/5450 PSI, DIFF-550/650 PSI. NOTE: PUMPED 20 BBL 16.0 PPG MUD CAP @ 15,095' PUMPED 20 BBL 16.0 PPG MUD CAP @ 15,653'
FAT TIRE B 1H | 16 | 2021-01-03 13:30 | 2021-01-03 16:30 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.02 | 15686 | 15738 | 17.3 | SLIDE (52' IN 2.95 HRS @ 17.6 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-4800/5400 PSI, DIFF-300/600 PSI. SLIDE DEPTHS: SLD F/15072' T/15097' 25' TF-150R 915-1027 SLD F/15367' T/15382' 15' TF-120R 1222-1313 SLD F/15653' T/15665' 12' TF-140R 1504-1558
FAT TIRE B 1H | 16 | 2021-01-03 16:30 | 2021-01-03 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.04 | 15738 | 15738 | 0 | SERVICE TOP DRIVE AND BLOCK.
FAT TIRE B 1H | 16 | 2021-01-03 17:00 | 2021-01-03 17:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.06 | 15738 | 15846 | 216 | ROT (108' IN .73 HRS @ 147.9 FPH) WOB-25/35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/23K, SPP-5650/5750 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 16 | 2021-01-03 17:30 | 2021-01-03 18:30 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.1 | 15846 | 15857 | 11 | SLIDE (11' IN .85 HRS @ 12.9 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-5100/5200 PSI, DIFF-100/20000 PSI. SLIDE DEPTHS: SLD F/15841' T/15852' 15' TF-170R 1739-1830
FAT TIRE B 1H | 16 | 2021-01-03 18:30 | 2021-01-03 21:00 | 2.5 | P | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 12.21 | 15857 | 15857 | 0 | BACK REAM OUT OF HOLE F/ 15,857' T/ 14,976' DUE T/ INCREASE IN DRILLING TORQUE 17/23K, PARAMETERS WHILE BACK REAMING T/ 14,976' GPM=400, SPP=4900/5100, RPM=80, TORQUE=10/20K, PAREMETERS AFTER REAMING BACK IN HOLE TO 15,857', GPM=400, SPP=4900/5100, RPM=80, TORQUE=10/16K. NOTE: PUMP 50 BBLS 16.0 PPG MUD CAP 15,760' W/ REAMING IN HOLE TO FLUSH ANNULUS.
FAT TIRE B 1H | 16 | 2021-01-03 21:00 | 2021-01-04 02:00 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.42 | 15857 | 16544 | 137.4 | ROT (687' IN 5.08 HRS @ 135 FPH) WOB-25/35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/23K, SPP-5650/5750 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 16 | 2021-01-04 02:00 | 2021-01-04 06:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.58 | 16544 | 16602 | 14.5 | SLIDE (58' IN 3.92 HRS @ 15 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-5100/5200 PSI, DIFF-100/20000 PSI. SLIDE DEPTHS: SLD F/15857-15864 7' TF-170R 2100-2130 SLD F/16028-16040 12' TF-150R 2245-2330 SLD F/16217-16232 15' TF-130R 0050-0140 SLD F/16406-16418 12' TF-160R 0255-0340 SLD F/16590-16597 7' TF-HS 0455-0515 SLD F/16597-16602 5' TF-180 0515-0600
FAT TIRE B 1H | 17 | 2021-01-04 06:00 | 2021-01-04 08:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.67 | 16602 | 16798 | 98 | ROT (196' IN 2.13 HRS @ 92 FPH) WOB-25/35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-17/23K, SPP-5000/6000 PSI, DIFF-800/1000 PSI. DRILLING UNDER MUD CAP WITH WATER, PUMPING 10 BBL OBM SWEEPS EVERY STAND. CASING PRESSURE WHILE DRILLING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 17 | 2021-01-04 08:00 | 2021-01-04 13:00 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.88 | 16798 | 16840 | 8.4 | SLIDE (42' IN 4.87 HRS @ 8.6 FPH) WOB: 45/55K, SPM-76/76, GPM-400, MRPM-272, SPP-5000/5200 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLD F/16602' T/16623' 21' TF-180 600-900 SLD F/16683' T/16704' 21' TF-180 958-1150
FAT TIRE B 1H | 17 | 2021-01-04 13:00 | 2021-01-04 13:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 12.88 | 16840 | 16840 |  | MILESTONE_TD WELL 1/4/2021 @ 13:00
FAT TIRE B 1H | 17 | 2021-01-04 13:00 | 2021-01-04 15:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.96 | 16840 | 16840 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN PUMPING 3-10 BBL OBM SWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 6 B/U (B/U F/16,840' T/10,827'), RPM-80, SPM: 76/76, GPM-400. 1ST BTM UP START TQ=17/20K, END= 16/19K, P/U WT= 255K, SPP= 5000 PSI 2ND BTM UP END TQ= 14/18K, P/U WT= 250K, SPP= 5000 PSI 3RD BTM UP END TQ= 14/16K, P/U WT= 240K, SPP= 5000 PSI LOSS OF 3/4K TORQUE FROM DOING CLEAN UP CYCLE.
FAT TIRE B 1H | 17 | 2021-01-04 15:00 | 2021-01-04 20:00 | 5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 13.17 | 16840 | 16840 | 0 | BACK REAM OUT OF HOLE F/16,840' T/13,275', PARAMETERS WHILE BACK REAMING, GPM=400, SPP=4600/4700 PSI, RPM=80, TORQUE= 6/16K., CASING PRESSURE WHILE BACK REAMING= 0 PSI, SICP= 0 PSI.
FAT TIRE B 1H | 17 | 2021-01-04 20:00 | 2021-01-04 20:30 | 0.5 | P | PRDHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 13.19 | 16840 | 16840 | 0 | ATTTEMPT TO TRIP BACK IN HOLE F/ 13,275', DRILL STRING STACKING OUT WEIGHT W/ 70/100K, BACK REAM OUT OF HOLE F/ 13,275' T/ 13,181'. ORIENT TOOL FACE TO 130R, SHUT DOWN PUMPS, PULLED THROUGH SIDE TRACK W/ 30/60K OVER PULL T/13,050'
FAT TIRE B 1H | 17 | 2021-01-04 20:30 | 2021-01-04 23:00 | 2.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 13.29 | 16840 | 16840 | 0 | CONTINUE BACK REAMING F/13,050' T/10,700', PARAMETERS WHILE BACK REAMING, GPM=400, SPP=4400/4600 PSI, RPM=80, TORQUE= 6/12K., CASING PRESSURE WHILE BACK REAMING= 0 PSI, SICP= 0 PSI. NOTE: AT 12,706' TO 12,325' REDUCE BACK REAMING F/ 80 RPM TO 30 RPM DUE TO 4 & 5 DEGREE DOG LEGS. AT 11,281' REDUCE BACK REAMING TO 30 RPM TO BACK REAM THROUGH CURVE SECTION.
FAT TIRE B 1H | 17 | 2021-01-04 23:00 | 2021-01-05 06:00 | 7 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 13.58 | 16840 | 16840 | 0 | TRIP OUT OF HOLE F/ 10,700' T/ 10,181', TRIP OUT THE HOLE LAYING DOWN DRILL PIPE F/10,181’ T/3,500’, FILLING ANNULUS WITH .63 BBLS/JOINT CALCULATED 11.9 PPG OBM. NOTE: PUMPED 20 BBL OF 16.0 PPG KILL MUD @ 5,200' PUMPED 30 BBL OF 16.0 PPG KILL MUD @ 4,800'
FAT TIRE B 1H | 18 | 2021-01-05 06:00 | 2021-01-05 09:30 | 3.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 13.73 | 16840 | 16840 | 0 | CONTINUE TRIPPING OUT THE HOLE LAYING DOWN DRILL PIPE F/3,500’ T/BHA, FILLING ANNULUS WITH .63 BBLS/JOINT CALCULATED 11.9 PPG OBM. FLOW CHECK @ 2,873’, 1,934' AND BHA (NO FLOW), REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE, L/D AGITATOR ON STAND 27. NOTE: PUMPED 20 BBLS OF 16.0 PPG KILL MUD @ 2,873' BEFORE REMOVING ROTATING HEAD. REGAINED RETURNS @ 1,934', CLOSED UPPER RAMS AND PUMPED 40 BBLS OF 16.0 PPG KILL MUD PUMPED 100 BBLS OF 16.0 PPG KILL MUD AFTER BHA WAS OUT THE HOLE
FAT TIRE B 1H | 18 | 2021-01-05 09:30 | 2021-01-05 10:30 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.77 | 16840 | 16840 | 0 | PULL MWD, DRAIN MOTOR, BREAK BIT, L/D MOTOR, BTI VALVE, THRUSTER AND DIRECTIONAL TOOLS.
FAT TIRE B 1H | 18 | 2021-01-05 10:30 | 2021-01-05 11:00 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 13.79 | 16840 | 16840 | 0 | REMOVE MOUSE HOLE, CLEAN AND ORGANIZE RIG FLOOR.
FAT TIRE B 1H | 18 | 2021-01-05 11:00 | 2021-01-05 12:00 | 1 | P | PRDHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 13.83 | 16840 | 16840 | 0 | REMOVE SAVER SUB CUT FOR SCREEN AND INSTALL FULL LIP SAVER SUB.
FAT TIRE B 1H | 18 | 2021-01-05 12:00 | 2021-01-05 12:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.85 | 16840 | 16840 | 0 | RIG SERVICE.
FAT TIRE B 1H | 18 | 2021-01-05 12:30 | 2021-01-05 13:00 | 0.5 | P | PRDHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 13.88 | 16840 | 16840 | 0 | REMOVE WEAR BUSHING.
FAT TIRE B 1H | 18 | 2021-01-05 13:00 | 2021-01-05 14:30 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 13.94 | 16840 | 16840 | 0 | HELD PJSM, RIG UP EXPRESS CASING TOOLS AND CRT.
FAT TIRE B 1H | 18 | 2021-01-05 14:30 | 2021-01-05 21:00 | 6.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.21 | 16840 | 16840 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING WITH NO CENTRALIZERS, 1 INNOVEX DV FLOAT COLLAR, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/7,141' WITH NO RETURNS, FILLING PIPE ON THE FLY WITH WATER, SOLID BODY CENTALIZERS EVERY OTHER 4TH JOINT F/16,708.48' T/9,860.14' (SET DEPTH), PUMPING CALCULATED DISPLACEMENT .3 BBLS PER JOINT 11.9 PPG OBM DOWN BACKSIDE.
FAT TIRE B 1H | 18 | 2021-01-05 21:00 | 2021-01-05 21:30 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 14.23 | 16840 | 16840 | 0 | FLOW CHECK (NO FLOW), REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD, WHILE MONITORING WELL ON TRIP TANK (NO FLOW).
FAT TIRE B 1H | 18 | 2021-01-05 21:30 | 2021-01-05 22:30 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 14.27 | 16840 | 16840 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
FAT TIRE B 1H | 18 | 2021-01-05 22:30 | 2021-01-06 03:30 | 5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.48 | 16840 | 16840 | 0 | PICK UP AND RUN WITH 5.5" 23# P110 ICY WEDGE 625 PRODUCTION CASING F/7,141' T/12,300' WITH NO RETURNS, FILLING PIPE ON THE FLY WITH WATER, PUMPING CALCULATED DISPLACEMENT .3 BBLS PER JOINT 11.9 PPG OBM DOWN BACKSIDE. RUN CASING @ 20 FT/MIN F/11,500' TO 12,300' NOTE: PUMP 100 BLL OF 16.0 PPG MUD DOWN BACKSIDE @ 10,100' DUE TO CASING PSI INCREASING TO 600 PSI
FAT TIRE B 1H | 18 | 2021-01-06 03:30 | 2021-01-06 06:00 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.58 | 16840 | 16840 | 0 | WASH DOWN CASING F/12,300' T/13,269', SPM 80, GPM 262, SPP- 2150 PSI; AVG CSG PSI= 0 PSI, AVG SICP= 0 PSI. WASH CASING @ 20 FT/MIN F/12,300' T/ 13,000'; WASH CASING @ 15 FT/MIN F/13,000' T/13,269'
FAT TIRE B 1H | 19 | 2021-01-06 06:00 | 2021-01-06 09:00 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.71 | 16840 | 16840 | 0 | WASH CASING @ 15 FT/MIN F/13,269' T/14,324. GPM-262, SPP-2400, SICP-200/330, WASHING ON MUD CAP. NOTE: AT 14,400' CSG STARTED TAKING EXCESSIVE SLACK OFF WEIGHT. DECISION WAS MADE TO PICK CSG UP T/14,324' AND ESTABLISH ROTATION @ 30 RPM.
FAT TIRE B 1H | 19 | 2021-01-06 09:00 | 2021-01-06 11:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.79 | 16840 | 16840 | 0 | WASH AND REAM CASING @ 15 FT/MIN F/14,324' T/15,000'. GPM-262, SPP-2400, RPM-30, SICP-200/330, WASHING ON MUD CAP. TQ @ 14,500: 9-15K TQ @ 15,000: 12-17K
FAT TIRE B 1H | 19 | 2021-01-06 11:00 | 2021-01-06 18:00 | 7 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.08 | 16840 | 16840 | 0 | WASH AND REAM CASING @ 8 FT/MIN F/15,000' T/16,750'. GPM-262, SPP-2500, RPM-30, SICP-200/330, WASHING ON MUD CAP. TQ @ 15,500: 13-18K TQ @ 16,000: 14-21K TQ @ 16,500: 16-21K TQ @ 16,750: 17-22K
FAT TIRE B 1H | 19 | 2021-01-06 18:00 | 2021-01-06 19:00 | 1 | P | PRDHLCSG | CIRC | DSPMD | DISPLACE MUD | 15.13 | 16840 | 16840 | 0 | PUMP CASING CAPACITY W/FRESH WATER @ 16,750' @ 6 BPM. SPP-2400 PSI, CP-300 PSI. WASH AND REAM CASING F/16,750' T/16,794'. RPM-30 INITIAL TQ:17-22K. FINAL TQ:16-18K SHUT DOWN PUMP & CP FELL TO 250 PSI
FAT TIRE B 1H | 19 | 2021-01-06 19:00 | 2021-01-06 20:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.17 | 16840 | 16840 | 0 | CLOSED HYDRIL, BLED OFF PRESSURE BETWEEN HYDRIL & RCH, UNCLAMPED & PULLED RCH, PICKED UP & MADE UP LANDING JOINT, WORKED CASING STRING DOWN TO INSTALL RCH, INSTALLED RCH, CLOSED CLAMP BLEED OFF VALVE & ORBIT VALVE, CLEARED FLOOR & OPENED UP HYDRIL TO LAND OUT CASING HANGER.
FAT TIRE B 1H | 19 | 2021-01-06 20:00 | 2021-01-06 20:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.19 | 16840 | 16840 | 0 | WASH AND REAM DOWN LANDING JOINT F/16,794' TO 2' ABOVE WELLHEAD. KILLED ROTARY AND LANDED HANGER IN WELLHEAD. LANDED WITH 160K W/BLOCKS, 120K W/O BLOCKS. CASING SHOE @ 16,824.61' TOP OF FLOAT COLLAR @ 16,733.88' BOTTOM OF TOE SLEEVE VALVE @ 16,733.88' TOP OF TOE SLEEVE VALVE @ 16,708.48' TOP OF X-OVER @ 9,729.04' TOP OF MARKER JOINT ABOVE X-OVER @ 9,663.13' 7 JOINTS 5" LEFT OUT- 299.10' 9 JOINTS 5.5" LEFT OUT- 411.33'
FAT TIRE B 1H | 19 | 2021-01-06 20:30 | 2021-01-06 21:00 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 15.21 | 16840 | 16840 | 0 | RIG DOWN CRT TOOL AND RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE.
FAT TIRE B 1H | 19 | 2021-01-06 21:00 | 2021-01-07 | 3 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.33 | 16840 | 16840 | 0 | FILLED PITS WITH FRESH WATER AND BEGAN TO PUMP THROUGH CASING TO ESTABLISH RETURNS. PUMPED @ 5 BPM W/2300 PSI & 1 FULL OPEN CHOKE. SICP-300 PSI AFTER OPENING CHOKE CP-0 PSI. SEPARATOR FILLED UP AND FULL RETURNS WERE ESTABLISHED. AFTER 500 STKS (31 BBLS) 12 PPG OBM STARTED COMING BACK. RECOVERED APPROXIMATELY 150 BBLS OBM TOTAL. AFTER 3000 STKS (187 BBLS), FRESH WATER STARTED COMING BACK. FLOW INCREASED AND CHOKE WAS PINCHED BACK. CP CAME UP TO 1575 PSI W/28% ON 1 CHOKE. PUMPED 3 BOTTOMS UP TO ESTABLISH CONSISTENT CASING PRESSURE TO DO CEMENT JOB. FLARE-2-5' DURING ENTIRE CIRCULATION.
FAT TIRE B 1H | 19 | 2021-01-07 | 2021-01-07 03:30 | 3.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 15.48 | 16840 | 16840 | 0 | HELD PJSM, SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 5 BPM 40 BBL 9.0 PPG WEIGHTED SPACER, 217 BBL 13.5 PPG 730 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT WITH TRACER. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBLS OF SUGAR WATER WITH CPT-21L, FOLLOWED BY 311 BBLS OF FRESH WATER WITH PLEXCIDE 15G & CORPLEX 300 @ 5.5 BPM (TOTAL OF 331 BBLS DISPLACEMENT), OBSERVED 100% RETURNS SLOWED PUMP RATE TO 3.5 BPM, FINAL LIFT PRESSURE WAS 2400 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3400 PSI, HELD FOR 5 MIN, BLED BACK 4 BBLS. FLOATS HELD. 0 BBLS OF SPACER BACK TO SURFACE. PLUG DOWN @ 02:50 HRS 1/7/2021. FULL RETURNS WHILE DISPLACING CEMENT. INITIAL SICP-1780 PSI, FINAL SICP= 1040 PSI. MAX CASING PSI W/ PUMPING CEMENT- 1580 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT- 1580 PSI CALCULATED TOP OF CEMENT- 7,753' FLARE:2-5' DURING ENTIRE CMT JOB. AT 220 BBLS DURING DIPLACEMENT PSI BROKE OVER AT 2,650 PSI AND GRADUALLY REDUCED TO 2,510 PSI BY 310 BBLS PUMPED.
FAT TIRE B 1H | 19 | 2021-01-07 03:30 | 2021-01-07 06:00 | 2.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 15.58 | 16840 | 16840 | 0 | SHUT IN WELL, RIG DOWN CIRCULATING IRON, INSTALL MOUSEHOLE, AND LAY DOWN DRILL PIPE WHILE MONITORING SICP. INITIAL SICP @ 02:40=1040 PSI 03:00-1045 PSI 04:00-1110 PSI 05:00-1123 PSI 05:30-1131 PSI
FAT TIRE B 1H | 20 | 2021-01-07 06:00 | 2021-01-07 13:00 | 7 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 15.88 | 16840 | 16840 | 0 | LAY DOWN DRILL PIPE WHILE MONITORING SICP. 06:00-1135 PSI 07:00-1145 PSI 08:00-1151 PSI 09:00-1154 PSI 10:00-1151 PSI 11:00-1146 PSI 12:00-1144 PSI 13:00-1140 PSI 14:00-1137 PSI
FAT TIRE B 1H | 20 | 2021-01-07 13:00 | 2021-01-07 14:00 | 1 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 15.92 | 16840 | 16840 | 0 | LAY DOWN 5" DS42 HANDLING TOOLS. PREP TO WASH OUT HANGER
FAT TIRE B 1H | 20 | 2021-01-07 14:00 | 2021-01-07 15:00 | 1 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 15.96 | 16840 | 16840 | 0 | BLEED OFF CASING PSI AND SHUT WELL IN AND MONITOR CASING PRESSURE SICP-1137 TO START, GAINED 25 BBLS IN TRIP TANK, SHUT WELL BACK IN. CSG PSI INCREASED TO 1000 PSI, OPEN WELL AND BLED OFF TO 0 CP, GAINED 15 BBLS IN APPROX 4 MIN, SHUT WELL BACK IN, SICP INCREASED T/1020 PSI.
FAT TIRE B 1H | 20 | 2021-01-07 15:00 | 2021-01-08 02:30 | 11.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 16.44 | 16840 | 16840 | 0 | MONITOR SICP WHILE WOC 15:00-1029 PSI 16:00-1058 PSI 17:00-1065 PSI 18:00-1064 PSI 19:00-1060 PSI 20:00-1056 PSI 21:00-1051 PSI 22:00-1046 PSI 23:00-1042 PSI 00:00-1038 PSI 01:00-1033 PSI 02:00-1031 PSI 02:30-1035 PSI
FAT TIRE B 1H | 20 | 2021-01-08 02:30 | 2021-01-08 03:00 | 0.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 16.46 | 16840 | 16840 | 0 | FROM 02:30 - 02:40-OPENED UP 1 CHOKE TO 20% AND BLED OFF CASING PRESSURE INTO TRIP TANK CASING PSI DECREASED F/1032 PSI TO 880 PSI. BLED BACK 6 TOTAL BBLS. FLOW STAYED STEADY & DID NOT DECREASE. CLOSED CHOKE AND SHUT IN WELL TO MONITOR PRESSURE. 02:40 - 02:50 CASING PSI INCREASED F/880 PSI T/1025 PSI. FROM 02:50 - 03:00 OPENED UP 1 CHOKE TO 20% AND BLED CSG PSI INTO TRIP TANK DECREASING CSG PSI F/1025 PSI T/832 PSI. BLED BACK 10 TOTAL BBLS. FLOW STAYED STEADY & DID NOT DECREASE. CLOSED CHOKE AND SHUT IN WELL TO MONITOR PRESSURE.
FAT TIRE B 1H | 20 | 2021-01-08 03:00 | 2021-01-08 05:00 | 2 | P | PRDHLCSG | KILL |  | KILL WELL | 16.54 | 16840 | 16840 | 0 | MONITORED CASING PRESSURE WHILE TRANSFERRING MUD INTO TANK 8. MUD WEIGHT WAS 12.3 PPG AND HAD TO BE WEIGHTED UP TO A 16 PPG 03:00-1025 PSI 04:00-1020 PSI 05:00-1020 PSI
FAT TIRE B 1H | 20 | 2021-01-08 05:00 | 2021-01-08 06:00 | 1 | P | PRDHLCSG | KILL |  | KILL WELL | 16.58 | 16840 | 16840 | 0 | LINE UP AND PUMP 110 BBLS 16 PPG KILL MUD DOWN ANNULAS. GPM-104. CASING PSI INCREASED F/1020 PSI TO 1260 PSI BEFORE BREAKING OVER. PUMP ENTIRE 110 BBLS, CASING PSI DECREASED FROM 1260 PSI TO 131 PSI WHILE PUMPING. SHUT DOWN PUMPS AND CASING PSI REDUCED TO 0 PSI. PERFORMING FLOW CHECK AT REPORT TIME.
FAT TIRE B 1H | 21 | 2021-01-08 06:00 | 2021-01-08 08:00 | 2 | P | PRDHLCSG | WCTRL |  | KILL WELL | 16.67 | 16840 | 16840 | 0 | BUILD AND PUMP 30 BBLS 15.0 PPG OBM THROUGH KILL LINE DOWN ANNULAS. AFTER 20 BBLS WERE PUMPED, CASING PRESSURE INCREASED TO 306 PSI AND DECREASED TO 206 PSI. SHUT MUD PUMPS DOWN AND CASING PSI REDUCED TO 0 PSI. OPEN TOP RAMS AND PERFORM FLOW CHECK-NO FLOW.
FAT TIRE B 1H | 21 | 2021-01-08 08:00 | 2021-01-08 09:00 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 16.71 | 16840 | 16840 | 0 | REMOVE CEMENT HEAD, ROTATING HEAD, AND LANDING JOINT. R/D CSG ELEVATORS AND R/U RIG ELEVATORS. R/U WASH OUT TOOL AND SET 6" ABOVE HANGER. PUMP @ 90 GPM W/1200 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF. INSTALL STREAM FLO PACKOFF AND TEST TO 10,000 PSI. PULL TESTED TO 25K OVERPULL. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. PICK UP 1" TUBING AND INSTALL BPV. LAY DOWN TUBING.
FAT TIRE B 1H | 21 | 2021-01-08 09:00 | 2021-01-08 09:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 16.73 | 16840 | 16840 | 0 | FLUSH THROUGH STACK, CHOKE LINE, CHOKE AND FLOW LINE WITH WATER.
FAT TIRE B 1H | 21 | 2021-01-08 09:30 | 2021-01-08 11:00 | 1.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 16.79 | 16840 | 16840 | 0 | REMOVE FLOW LINE FROM SCISSOR & REMOVE TURNBUCKLES. INSTALL WRANGLER ONTO BOP, BACK OUT STREAMFLO ADAPTER FLANGE AND RAISE BOP. INSTALL WEATHER CAP AND SECURE WELL. RELEASE WELL ON 1/8/2021 @ 11:00
FAT TIRE B 1H | 21 | 2021-01-08 11:00 | 2021-01-08 18:00 | 7 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 17.08 | 16840 | 16840 | 0 | NIPPLE DOWN BOP: BREAK OUT AND REMOVE ROTATING HEAD ASSEMBLY, ORBIT VALVE, AND SPACER SPOOL. REMOVE CHOKE LINE, KILL LINES, AND ACCUMULATOR HYDRAULIC LINES. LAY OVER BOP WRANGLER AND SECURE FOR RIG MOVE.
FAT TIRE B 1H | 21 | 2021-01-08 11:00 | 2021-01-08 11:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 16.79 | 16840 | 16840 |  | MILESTONE_WELL RELEASE ON 1/8/2021 @ 11:00
FAT TIRE B 1H | 21 | 2021-01-08 18:00 | 2021-01-09 06:00 | 12 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 17.08 | 16840 | 16840 | 0 | REMOVE ALL HANDLING EQUIPMENT OFF RIG FLOOR, PIN TOP DRIVE TO TRACK, UNSPOOL DRAWWORKS(CUT 13 WRAPS), R/D TONGS, AND ST-80. R/D CATWALK AND MOVE. EXTEND AND PIN MSRC'S TO SUB AND LOWER @ 23:00. REMOVE BOP, EXTEND MSRC'S TO DERRICK AND PREP TO LOWER. BEGIN RIGGING DOWN BACK YARD. REMOVE FLOWLINE MANIFOLD FROM TRIP TANK SKID, REMOVE SHAKERS, AND SOLIDS CONTROL EQUIPMENT FROM TANKS. SPLIT TANKS APART AND STAGE FOR CARWASH AND PREP TO MOVE AT DAYLIGHT. BEGIN RIGGING DOWN BACKYARD ELECTRICAL LINES PUMPS, VFD, WATER TANKS, AND MISC.
FAT TIRE B 1H | 22 | 2021-01-09 06:00 | 2021-01-09 18:00 | 12 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 17.08 | 16840 | 16840 | 0 | RIGGING DOWN EQUIPMENT. R/D MUD PUMPS, GEN PACKAGE, SUITCASES, AND AIR/WATER LINES IN BACKYARD. PERFORMING CAR WASHES ON ALL EQUIPMENT BEFORE LOADING. RIG DOWN AND MOVE TCB TRAILER HOUSES. TRANSPORT SHAKERS, FLOW LINE MANIFOLD, SCISSOR STANDS, MUD TANKS, PATTERSON CREW QUARTERS, MUD PUMPS, FUEL TANKS, SUITCASES, WATER TANKS, CHANGE HOUSE, VFD HOUSE, AND GEN PACKAGE. LOWER DERRICK @ 12:30.
FAT TIRE B 1H | 22 | 2021-01-09 18:00 | 2021-01-09 18:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 17.08 | 16840 | 16840 |  | MILESTONE_RIG RELEASE ON 1/9/2021 @ 18:00
FAT TIRE B 1H | 22 | 2021-01-09 18:00 | 2021-01-09 18:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 17.08 | 16840 | 16840 |  | MILESTONE_TURN OVER TO COMPLETION ON 1/9/2021 @ 18:00
GRAND CANYON A 1H | 2 | 2020-04-28 11:30 | 2020-04-28 14:00 | 2.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPPED RIG TO WALK TO THE GRAND CANYON A 1H, SWAP HYDRAULICS TO WALKING SYSTEM, WALKED RIG AND CATWALK 20', CENTERED AND LEVELED SUB OVER CONDUCTOR. R/U AIR, WATER, AND VIBRATOR HOSES. CENTER CATWALK, SET MOUSEHOLE, L/D LANDING JOINT, CASING BAILS & ELEVATORS, AND RIG UP RIG ELEVATORS.
GRAND CANYON A 1H | 2 | 2020-04-28 11:30 | 2020-04-28 11:30 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 04/28/2020 @ 11:30
GRAND CANYON A 1H | 2 | 2020-04-28 14:00 | 2020-04-28 15:00 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | RIG UP AIR AND WATER LINES, WALK PIPE WRANGLER IN POSITION AND LOWER V-DOOR, SET CLIMB ASSIST AND GERONIMO LINE. INSTALL SCISSOR FLOWLINE
GRAND CANYON A 1H | 2 | 2020-04-28 15:00 | 2020-04-28 16:30 | 1.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | INSTALL CONDUCTOR RISER AND 3RD PARTY CELLAR PUMPS.
GRAND CANYON A 1H | 2 | 2020-04-28 16:30 | 2020-04-28 17:00 | 0.5 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE AND BLOCK.
GRAND CANYON A 1H | 2 | 2020-04-28 17:00 | 2020-04-28 18:00 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | MAKE UP BHA, INSTALL MWD TOOL AND TEST, TEST GOOD, MAKE UP MONEL DRILL COLLAR.
GRAND CANYON A 1H | 2 | 2020-04-28 18:00 | 2020-04-28 20:00 | 2 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.08 | 108 | 878 | 385 | ROTATE (770' IN 1.88 HRS @ 410 FPH) WOB-10/15K, RPM-40-70, TRQ- 12/17K, SPM-50/50, GPM-400, MMRPM-66, TRPM-116, SPP-1000/1200 PSI, DIFF-250/450 PSI.
GRAND CANYON A 1H | 2 | 2020-04-28 18:00 | 2020-04-28 18:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL 4/28/2020 @ 18:00
GRAND CANYON A 1H | 2 | 2020-04-28 20:00 | 2020-04-28 23:30 | 3.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.23 | 878 | 2667 | 511.1 | ROTATE (1789' IN 3.72 HRS @ 481 FPH) WOB-15/30K, RPM-100, TRQ- 12/17K, SPM-100/100, GPM-800, MMRPM-133, TRPM-233, SPP-2000/2400 PSI, DIFF-500/900 PSI.
GRAND CANYON A 1H | 2 | 2020-04-28 23:30 | 2020-04-29 02:00 | 2.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.33 | 2667 | 2845 | 71.2 | SLIDE (178' IN 2.45 HRS @ 73 FPH) WOB: 20/30K, SPM: 100/100 GPM: 800, MMRPM:133, SPP- 1700/2000 PSI, DIFF- 200/400 PSI. SLIDE DEPTHS: SLD F/878' T/890' 12' TF-40M 19;53-20;04 SLD F/1167' T/1178' 11' TF-30M 20;31-20;42 SLD F/1445' T/1460' 15' TF-30M 21;10-21;19 SLD F/2104' T/2114' 10' TF-40M 22;50-22;58 SLD F/2197' T/2207' 10' TF-40M 23;07-23;18 SLD F/2292' T/2307' 15' TF-HS 23;27-23;39 SLD F/2385' T/2400' 15' TF-HS 23;50-00;07 SLD F/2480' T/2500' 20' TF-HS 00;17-00;35 SLD F/2568' T/2588' 20' TF-HS 00;42-00;57 SLD F/2657' T/2682' 25' TF-HS 1;06-01;21 SLD F/2751' T/2776 25' TF-HS 01;34-01;54 SLD F/2845' T/2848' 3' TF-HS 02;03-2;11
GRAND CANYON A 1H | 2 | 2020-04-29 02:00 | 2020-04-29 02:30 | 0.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.35 | 2845 | 2990 | 290 | ROTATE (145' IN .63 HRS @ 230 FPH) WOB-12/15K, RPM-100, TRQ- 8/12K, SPM-110, GPM-461, MMRPM-77, TRPM-167, SPP-1100/1200 PSI, DIFF-300/400 PSI. (DRILL WITH ONE PUMP)
GRAND CANYON A 1H | 2 | 2020-04-29 02:30 | 2020-04-29 03:00 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.38 | 2990 | 3005 | 30 | SLIDE (15' IN .32 HRS @ 47 FPH) WOB: 6/10K, SPM: 110 GPM: 461, MMRPM:77, SPP- 800/900 PSI, DIFF- 100/150 PSI. (DRILL WITH ONE PUMP) SLIDE DEPTHS: SLD F/2848' T/2860' 12' TF-HS 2;15-2;22
GRAND CANYON A 1H | 2 | 2020-04-29 03:00 | 2020-04-29 04:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.42 | 3005 | 3005 | 0 | PUMP 2-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-800, RPM-100, TRQ-3/5K, SPP-1700 PSI.
GRAND CANYON A 1H | 2 | 2020-04-29 04:00 | 2020-04-29 05:00 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.46 | 3005 | 3005 | 0 | TRIP OUT OF HOLE F/3005' T/1275, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
GRAND CANYON A 1H | 2 | 2020-04-29 05:00 | 2020-04-29 06:00 | 1 | U | SFHLCSG | WAIT | WOW | WAIT ON WEATHER | 0.5 | 3005 | 3005 | 0 | WAIT ON WEATHER, RECIPROCATE PIPE
GRAND CANYON A 1H | 3 | 2020-04-29 06:00 | 2020-04-29 06:30 | 0.5 | U | SFHLCSG | WAIT | WOW | WAIT ON WEATHER | 0.52 | 3005 | 3005 | 0 | WORKED PIPE WHILE WAITING ON WEATHER
GRAND CANYON A 1H | 3 | 2020-04-29 06:30 | 2020-04-29 07:00 | 0.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.54 | 3005 | 3005 | 0 | POOH F/1230' - T/BHA
GRAND CANYON A 1H | 3 | 2020-04-29 07:00 | 2020-04-29 08:30 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.6 | 3005 | 3005 | 0 | RACKED BACK HWDP, MONEL DRILL COLLARS, DRAINED MUD MOTOR, L/D BIT, STABILIZER, & MUD MOTOR
GRAND CANYON A 1H | 3 | 2020-04-29 08:30 | 2020-04-29 10:00 | 1.5 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.67 | 3005 | 3005 | 0 | RIGGED UP EXPRESS ENERGY CASING CREW TOOLS & EQUIPMENT
GRAND CANYON A 1H | 3 | 2020-04-29 10:00 | 2020-04-29 14:00 | 4 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.83 | 3005 | 3005 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR,1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 71 JOINTS OF 10 3/4" 45.5# J-55 T/2991', RAN 20 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY 4TH JT. ALL THE WAY TO 155.66', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 65" BELOW GROUND LEVEL. (WASH DOWN LANDING JOINT AND SET 80K ON BASE PLATE SHOE: 2993' TOP OF FLOAT COLLAR: 2911'
GRAND CANYON A 1H | 3 | 2020-04-29 14:00 | 2020-04-29 14:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.85 | 3005 | 3005 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT @ 10 BPM WITH 375 PSI, RIG DOWN CASING TOOLS, NO LOSSES.
GRAND CANYON A 1H | 3 | 2020-04-29 14:30 | 2020-04-29 15:00 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.88 | 3005 | 3005 | 0 | PJSM, RIG DOWN CRT, B/O & L/D LANDING JOINT & CASING RUNNING TOOLS
GRAND CANYON A 1H | 3 | 2020-04-29 15:00 | 2020-04-29 18:30 | 3.5 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1.02 | 3005 | 3005 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 25 BBL 8.3 PPG FRESH WATER SPACER, 322 BBLS 11.6 PPG LEAD CEMENT, 86 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 280 BBLS OF 9.5 PPG OIL BASE MUD. BUMPED PLUG W/ 900 PSI PRESSURED UP T/1400PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 30 BBLS OF SPACER AND 220 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
GRAND CANYON A 1H | 3 | 2020-04-29 18:30 | 2020-04-29 19:00 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.04 | 3005 | 3005 | 0 | PRESSURE TESTED CASING TO 1500 PSI (TEST WAS GOOD AND HAD ZERO LEAK OFF)
GRAND CANYON A 1H | 3 | 2020-04-29 19:00 | 2020-04-29 19:30 | 0.5 | P | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 1.06 | 3005 | 3005 | 0 | RIGGED DOWN NINE ENERGY CEMENTING EQUIPMENT
GRAND CANYON A 1H | 3 | 2020-04-29 19:30 | 2020-04-29 20:00 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 1.08 | 3005 | 3005 | 0 | RIGGED DOWN CELLAR PUMP EQUIPMENT
GRAND CANYON A 1H | 3 | 2020-04-29 20:00 | 2020-04-30 06:00 | 10 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.5 | 3005 | 3005 | 0 | REMOVED 2ND ORBIT VALVE OFF OF MPD T ON ROTATING HEAD & INSTALLED BLANK FLANGE, RIGGED UP FLOWLINE EXTENSION, SKID ACCUMULATOR, INSTALLED HYDRAULIC FITTINGS & HYDRAULIC LINES TO BOP, INSTALL CHOKE LINE TO SCISSOR. STAB BOP ON SPEEDHEAD-(STACK TOO HIGH) REMOVE SPACER, INSTALL NEW BOP ADAPTER STUDS AND STAB BOP. HOOK UP CHOKE LINE TO BOP. BEGIN INSTALLING KILL LINE.
GRAND CANYON A 1H | 4 | 2020-04-30 06:00 | 2020-04-30 07:30 | 1.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.56 | 3005 | 3005 | 0 | NIPPLED UP BOPE, INSTALLED KILL LINE & TURNBUCKLES, CENTERED STACK TO ROTARY TABLE
GRAND CANYON A 1H | 4 | 2020-04-30 07:30 | 2020-04-30 13:30 | 6 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.81 | 3005 | 3005 | 0 | INSTALLED TEST PLUG & TESTED BOPE: TOP, BOTTOM, BLIND, BOTTOM RAMS, MUD CROSS VALVES, KILL LINE, CHOKE LINE, CHOKE MANIFOLD, TOP DRIVE VALVES, FLOOR SAFETY VALVES 250 PSI LOW & 5000 PSI HIGH, TESTED HYDRIL 250 PSI LOW 3500 PSI HIGH, TESTED ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW, 1000 PSI HIGH
GRAND CANYON A 1H | 4 | 2020-04-30 13:30 | 2020-04-30 17:30 | 4 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.98 | 3005 | 3005 | 0 | INSTALLED FLOWLINE TO ORBIT VALVE, & FLOWLINE MANIFOLD
GRAND CANYON A 1H | 4 | 2020-04-30 17:30 | 2020-04-30 19:30 | 2 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 2.06 | 3005 | 3005 | 0 | INSTALLED MOUSEHOLE, TRIP NIPPLE, & PREPPED RIG FLOOR FOR DRILLING OPERATIONS. HOOK UP FLOWLINE AT SCISSOR AND INSTALL CELLAR COVERS
GRAND CANYON A 1H | 4 | 2020-04-30 19:30 | 2020-04-30 20:00 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 2.08 | 3005 | 3005 | 0 | STAGE OUT BHA AND P/U LIFT SUBS TO RIG FLOOR
GRAND CANYON A 1H | 4 | 2020-04-30 20:00 | 2020-04-30 21:30 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 2.15 | 3005 | 3005 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 9/14'S TFA: 1.353) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.12° SLICK; .166 REV/GAL; 5.87' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 8" UBHO, 2-8" NMDC,1- X/O, BIT TO SENSOR-70', TEST MWD ( GOOD TEST).
GRAND CANYON A 1H | 4 | 2020-04-30 21:30 | 2020-05-01 | 2.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 2.25 | 3005 | 3005 | 0 | P/U 6 JOINTS 6-1/2" DRILL COLLARS, X/O, AND 9 HWDP
GRAND CANYON A 1H | 4 | 2020-05-01 | 2020-05-01 01:00 | 1 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 2.29 | 3005 | 3005 | 0 | TRIP IN HOLE F/580' T/2,911'. PERFORM TRIP DRILL-70 SECONDS
GRAND CANYON A 1H | 4 | 2020-05-01 01:00 | 2020-05-01 01:30 | 0.5 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 2.31 | 3005 | 3005 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROT HEAD
GRAND CANYON A 1H | 4 | 2020-05-01 01:30 | 2020-05-01 02:00 | 0.5 | P | SFHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 2.33 | 3005 | 3005 | 0 | REMOVE LEAKING TOP DRIVE LINK CYLINDER AND REPLACE
GRAND CANYON A 1H | 4 | 2020-05-01 02:00 | 2020-05-01 03:00 | 1 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 2.38 | 3005 | 3015 | 10 | DRILL SHOE TRACK AND 10' NEW FORMATION F/ 3005' T/ 3015'. GPM-422, SPP-850 PSI, RPM-50, DIFF-150 PSI
GRAND CANYON A 1H | 4 | 2020-05-01 03:00 | 2020-05-01 03:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.4 | 3015 | 3015 | 0 | CIRCULATE BOTTOMS UP GPM-422, SPP-850 PSI, RPM-50
GRAND CANYON A 1H | 4 | 2020-05-01 03:30 | 2020-05-01 04:00 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 2.42 | 3015 | 3015 | 0 | PERFORM F.I.T.WITH 9.6 PPG MUD, 310 PSI SURFACE PRESSURE FOR 11.6 PPG EMW. SHOE MD-2,993' TVD-2,984'.
GRAND CANYON A 1H | 4 | 2020-05-01 04:00 | 2020-05-01 06:00 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.5 | 3015 | 3871 | 428 | ROT (846' IN 2 HRS @ 423 FPH) WOB: 30/40K, SPM: 105/105, GPM: 739, MMRPM: 123, RPM: 80, TRPM: 203, TRQ: 3/11K, SPP: 2400/3100 PSI, DIFF: 500/700 PSI. SLD F/3,226' T/3,236', TF-HS, 10', 11 MIN
GRAND CANYON A 1H | 5 | 2020-05-01 06:00 | 2020-05-01 22:00 | 16 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.17 | 3871 | 8936 | 316.6 | ROT (5065' IN 15.6 HRS @ 325 FPH) WOB: 35/45K, SPM: 107/107, GPM: 753, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 6K/18K, SPP: 3400/4200 PSI, DIFF: 700/900 PSI.
GRAND CANYON A 1H | 5 | 2020-05-01 22:00 | 2020-05-02 06:00 | 8 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.5 | 8936 | 9228 | 36.5 | SLIDE (292' IN 8.4 HRS @ 35 FPH) WOB: 15/30K, SPM: 107/107, GPM: 753, MMRPM: 123, SPP: 3400/3700 PSI, DIFF: 200/400 PSI.
GRAND CANYON A 1H | 6 | 2020-05-02 06:00 | 2020-05-02 07:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.54 | 9228 | 9398 | 170 | ROT (170' IN 1.27 HRS @ 134 FPH) WOB: 35/45K, SPM: 107/107, GPM: 753, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 6K/18K, SPP: 3400/4200 PSI, DIFF: 700/900 PSI.
GRAND CANYON A 1H | 6 | 2020-05-02 07:00 | 2020-05-02 07:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.56 | 9398 | 9416 | 36 | SLIDE (18' IN .23 HRS @ 77 FPH) WOB: 15/30K, SPM: 107/107, GPM: 753, MMRPM: 123, SPP: 3400/3700 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS F/ 9335' T/9353 @ 180MAG 0657--0711 14MIN
GRAND CANYON A 1H | 6 | 2020-05-02 07:30 | 2020-05-02 08:30 | 1 | U | INTHL | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 3.6 | 9416 | 9416 | 0 | WORK PIPE WHILE CHANGING OUT BLOWN VIBRATOR HOSE ON MUD LINE TO RIG FLOOR.
GRAND CANYON A 1H | 6 | 2020-05-02 08:30 | 2020-05-02 09:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.63 | 9416 | 9509 | 186 | ROT (93' IN .5 HRS @ 186 FPH) WOB: 35/45K, SPM: 107/107, GPM: 753, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 6K/18K, SPP: 3400/4200 PSI, DIFF: 700/900 PSI.
GRAND CANYON A 1H | 6 | 2020-05-02 09:00 | 2020-05-02 10:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.67 | 9509 | 9540 | 31 | SLIDE (31' IN 1 HRS @ 31 FPH) WOB: 15/30K, SPM: 107/107, GPM: 753, MMRPM: 123, SPP: 3400/3700 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: F/9509' T/ 9540' @335MAG 0916-1005 49MIN F/9615' T/9640' @335MAG 1102-1142 40MIN STARTED INTERMEDIATE CURVE SECTION ON 5/2/20 @ 09:00 (9,509' MD / 9,385' TVD.)
GRAND CANYON A 1H | 6 | 2020-05-02 10:00 | 2020-05-02 10:30 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.69 | 9540 | 9540 | 0 | CIRCULATED & CONDITIONED HOLE WITH #2 MUD PUMP WHILE REPAIRING LINER WASHER HOSE ON THE #1 MUD PUMP
GRAND CANYON A 1H | 6 | 2020-05-02 10:30 | 2020-05-02 14:30 | 4 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.85 | 9540 | 10018 | 119.5 | ROT (478' IN 4 HRS @ 120 FPH) WOB: 35/45K, SPM: 107/107, GPM: 753, MMRPM: 125, RPM: 80, TRPM: 205, TRQ: 6K/18K, SPP: 3550/4350 PSI, DIFF: 700/900 PSI.
GRAND CANYON A 1H | 6 | 2020-05-02 14:30 | 2020-05-03 04:30 | 14 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.44 | 10018 | 10335 | 22.6 | SLIDE (317' IN 13.97 HRS @ 23 FPH) WOB: 15/30K, SPM: 107/107, GPM: 753, MMRPM: 123, SPP: 3550/3850 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: F/9896' T/9921 TF-20R 1336-1405 29MIN F/9940' T/9965' TF-HS 1421-1505 44MIN F/9981' T/10030' TF-HS 1535-1800 145 MIN SLD F/10030-T/10074,TF/HS,44'/112MIN 1800-1952 SLD F/10119-T/10150,TF/HS,31'/113MIN 2021-2214 SLD F/10168-T/10192,TF/HS,24'/54MIN 2226-2320 SLD F/10276-T/10335,TF/HS,59'/214MIN 2356-0430
GRAND CANYON A 1H | 6 | 2020-05-03 04:30 | 2020-05-03 06:00 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.5 | 10335 | 10335 | 0 | PUMP 2-30 BBL LCM SWEEP IN TANDEM, CIRCULATE BOTTOMS UP @ 757GPM, SPP-3550, NO ROTATION- LINE UP HIGH SIDE AND WORK PIPE, FLOW CHECK WELL, WELL STATIC, PUMP SLUG. TD INTERMEDIATE SECTION ON 5/3/20 @ 04:30 (10,335' MD / 10,193' TVD)
GRAND CANYON A 1H | 7 | 2020-05-03 06:00 | 2020-05-03 11:00 | 5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.71 | 10335 | 10335 | 0 | POOH F/10,335' T/BHA. PROPER FILLS ON TRIP OUT OF HOLE. REMOVE ROT. HEAD AND INSTALL TRIP NIPPLE @ SHOE.
GRAND CANYON A 1H | 7 | 2020-05-03 11:00 | 2020-05-03 13:30 | 2.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.81 | 10335 | 10335 | 0 | RACK BACK HWDP AND DRILL COLLARS. L/D TOP MONEL AND REMOVE MWD. DRAIN MOTOR AND L/D BIT AND MOTOR. P/U NEW MOTOR AND RACK BACK.
GRAND CANYON A 1H | 7 | 2020-05-03 13:30 | 2020-05-03 14:00 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.83 | 10335 | 10335 | 0 | REMOVED WEAR BUSHING & PREPPED RIG FLOOR FOR CASING RUN
GRAND CANYON A 1H | 7 | 2020-05-03 14:00 | 2020-05-03 14:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 4.85 | 10335 | 10335 | 0 | SERVICED TOP DRIVE
GRAND CANYON A 1H | 7 | 2020-05-03 14:30 | 2020-05-03 15:30 | 1 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.9 | 10335 | 10335 | 0 | REMOVE VBR PIPE RAMS AND INSTALL 7-5/8" CASING RAMS
GRAND CANYON A 1H | 7 | 2020-05-03 15:30 | 2020-05-03 16:30 | 1 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.94 | 10335 | 10335 | 0 | HELD PJSM THEN RIGGED UP EXPRESS ENERGY'S CASING CREW TOOLS & EQUIPMENT
GRAND CANYON A 1H | 7 | 2020-05-03 16:30 | 2020-05-04 03:30 | 11 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.4 | 10335 | 10335 | 0 | HELD PJSM THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 232 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, & 1-7 5/8" 29.7# P-110 HC ERW BTC PUP JOINT, FILLED PIPE & BROKE CIRC EVERY 50 JTS, INSTALLED 44 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 2,987' . PICKED UP 2 EXTRA JT'S & TAGGED BOTTOM AT 10335' MD (7' IN ON 2ND JT), L/D 2 JTS OF CSG, P/U LANDING JOINT, LANDED CSG ON CSG MANDREL W/220K (W/O BLOCKS), SW-360K, S/O-240K, P/U-400K. FLOAT SHOE-10,316.81' TOP OF FLOAT COLLAR-10,222.81'. ONCE LANDED. ESTABLISHED RETURNS THRU CRT TOOL AND CIRC FOR 10 MIN.
GRAND CANYON A 1H | 7 | 2020-05-04 03:30 | 2020-05-04 04:00 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 5.42 | 10335 | 10335 | 0 | RIG DOWN EXPRESS CASING TOOLS
GRAND CANYON A 1H | 7 | 2020-05-04 04:00 | 2020-05-04 05:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.48 | 10335 | 10335 | 0 | R/U NINE ENERGY CEMENT HEAD AND CIRCULATE WITH RIG PUMPS FULL CASING CAPACITY. GPM-352, PP-600
GRAND CANYON A 1H | 7 | 2020-05-04 05:30 | 2020-05-04 06:00 | 0.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.5 | 10335 | 10335 | 0 | CEMENT WITH NINE ENERGY SERVICES, PJSM, SWAPPED LINES F/RIG STANDPIPE T/ CEMENTING STANDPIPE, TESTED LINES T/5000 PSI, AND BEGIN PUMPING 40 BBLS 10.5 PPG WEIGHTED SPACER @ 5.5 BPM.
GRAND CANYON A 1H | 8 | 2020-05-04 06:00 | 2020-05-04 08:30 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.6 | 10335 | 10335 | 0 | CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG GTX SPACER. 286 BBL 11.8 PPG 830SK 1.94YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT. 78 BBL 16.2 PPG 305SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 470 BBLS OF 9.8 PPG OIL BASE MUD, @ 450 BBLS SLOWED PUMP RATE TO 3 BPM, FINAL LIFT PRESSURE WAS 1800 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2300 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 4.5 BBLS. FLOATS HELD. PLUG DOWN @ 08:15 HRS 05/04/2020, GOT BACK 20 BBLS OF SPACER BACK TO SURFACE, & HAD FULL RETURNS ENTIRE CEMENTING JOB
GRAND CANYON A 1H | 8 | 2020-05-04 08:30 | 2020-05-04 09:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.63 | 10335 | 10335 | 0 | PRESSURE TESTED CASING TO 3500 PSI (PRESSURE HELD & TEST WAS GOOD)
GRAND CANYON A 1H | 8 | 2020-05-04 09:00 | 2020-05-04 09:30 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 5.65 | 10335 | 10335 | 0 | RIGGED DOWN CEMENTING EQUIPMENT, BROKE OUT & LAID DOWN LANDING JOINT, RIGGED DOWN CASING BAILS & ELEVATORS
GRAND CANYON A 1H | 8 | 2020-05-04 09:30 | 2020-05-04 11:00 | 1.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.71 | 10335 | 10335 | 0 | MADE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP & MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 10K, BROKE OUT & LAID DOWN SETTING TOOL
GRAND CANYON A 1H | 8 | 2020-05-04 11:00 | 2020-05-04 12:00 | 1 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.75 | 10335 | 10335 | 0 | NIPPLED DOWN BOPE, ATTACHED BOP WRANGLER, LIFTED STACK & MOVED AWAY FROM WELLHEAD
GRAND CANYON A 1H | 8 | 2020-05-04 12:00 | 2020-05-04 13:30 | 1.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.81 | 10335 | 10335 | 0 | REMOVED WELLHEAD CAP FROM LEVI GOODRICH 2-2H & INSTALLED ONTO GRAND CANYON A-1H WELLHEAD, SECURED & PUT WELL ON HOLD
GRAND CANYON A 1H | 8 | 2020-05-04 13:30 | 2020-05-04 13:30 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 5.81 | 10335 | 10335 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 5/4/20 @ 13:30
GRAND CANYON A 1H | 9 | 2020-06-22 06:00 | 2020-06-22 08:30 | 2.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.92 | 10335 | 10335 | 0 | PREP TO WALK AND WALK RIG F/ THE LEVI GOODRICH 2-3H T/ THE GRAND CANYON A 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, WITNESSED RIG CENTER OVER WELL.
GRAND CANYON A 1H | 9 | 2020-06-22 08:30 | 2020-06-22 10:30 | 2 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 6 | 10335 | 10335 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALLED TURNBUCKLES & CENTERED STACK. HOOK UP FLOWLINE, REMOVE KILL LINE CHECK VALVE, R/U KILL LINE.
GRAND CANYON A 1H | 9 | 2020-06-22 08:30 | 2020-06-22 08:30 | 0 | P | INTHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 5.92 | 10335 | 10335 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 6/22/2020 @ 06:00
GRAND CANYON A 1H | 9 | 2020-06-22 10:30 | 2020-06-22 19:00 | 8.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.35 | 10335 | 10335 | 0 | FILL STACK WITH WATER, TESTED BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 5000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST TO 1500 PSI. RIG DOWN TESTERS
GRAND CANYON A 1H | 9 | 2020-06-22 19:00 | 2020-06-22 20:00 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 6.4 | 10335 | 10335 | 0 | INSTALL WEAR BUSHING AND PREP FLOOR FOR BHA
GRAND CANYON A 1H | 9 | 2020-06-22 20:00 | 2020-06-22 20:30 | 0.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 6.42 | 10335 | 10335 | 0 | PERFORM DRAWDOWN TEST ON ACCUMULATOR
GRAND CANYON A 1H | 9 | 2020-06-22 20:30 | 2020-06-22 22:30 | 2 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 6.5 | 10335 | 10335 | 0 | REPAIR LEAKS ON ACCUMULATOR AND REBUILD BYPASS MANIFOLD VALVE REGULATOR
GRAND CANYON A 1H | 9 | 2020-06-22 22:30 | 2020-06-23 00:30 | 2 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.58 | 10335 | 10335 | 0 | PICK UP 6.75" ULTERRA U611S SER 39992: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.05' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-67'. BIT TO GAMMA-57', TEST MWD (TEST GOOD).
GRAND CANYON A 1H | 9 | 2020-06-23 00:30 | 2020-06-23 01:00 | 0.5 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.6 | 10335 | 10335 | 0 | CHANGE ST-80 DIES
GRAND CANYON A 1H | 9 | 2020-06-23 01:00 | 2020-06-23 06:00 | 5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.81 | 10335 | 10335 | 0 | TRIP IN HOLE F/BHA T/9,500'. PICK UP AGITATOR AFTER STAND 27 (GPM-225), PSI BEFORE AGITATOR- 950 / PSI AFTER AGITATOR- 975, PROPER DISPLACEMENTS ON TRIP IN HOLE. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
GRAND CANYON A 1H | 10 | 2020-06-23 06:00 | 2020-06-23 06:30 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.83 | 10335 | 10335 | 0 | TRIPPED IN HOLE F/9500' - T/10,192'
GRAND CANYON A 1H | 10 | 2020-06-23 06:30 | 2020-06-23 07:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 6.85 | 10335 | 10335 | 0 | REMOVED TRIP NIPPLE & INSTALLED RCH
GRAND CANYON A 1H | 10 | 2020-06-23 07:00 | 2020-06-23 08:00 | 1 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 6.9 | 10335 | 10335 | 0 | DRILLED OUT CEMENT, SHOE TRAC F/10,192' - T/10,335'
GRAND CANYON A 1H | 10 | 2020-06-23 08:00 | 2020-06-23 08:30 | 0.5 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 6.92 | 10335 | 10345 | 20 | DRILLED OUT 10' OF NEW FORMATION F/10,335' - T/10345'
GRAND CANYON A 1H | 10 | 2020-06-23 08:30 | 2020-06-23 09:00 | 0.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.94 | 10345 | 10345 | 0 | CIRCULATED & CONDITIONED MUD FOR F.I.T
GRAND CANYON A 1H | 10 | 2020-06-23 09:00 | 2020-06-23 09:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.96 | 10345 | 10345 | 0 | PERFORMED F.I.T @ 10,322’ MD 10,181’ W/9.3 PPG T/1959 PSI EMW = 13 PPG
GRAND CANYON A 1H | 10 | 2020-06-23 09:30 | 2020-06-23 21:00 | 11.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.44 | 10345 | 10768 | 36.8 | S/D (423' IN 11.73 HRS @ 36 FPH) WOB-15/25K, SPM-60/60, GPM-388, MRPM-263, SPP-3400/3800 PSI, DIFF-200/400 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' SLIDE DEPTHS: SLD F/10345 T/10389 TF30L DF/250 GPM/300 44' 240MIN SLD F/10418 T/10484 TF/HS DF/650 GPM/345 66' 60MIN SLD F/10506 T/10576 TF/HS DF/675 GPM/385 60'90MIN SLD F/10597 T/ 10605 TF/HS DF/500 GPM/385 8' 30MIN SLD F/10605 T/10720 TF/20R DF/500 GPM/385 115' 127 MIN SLD F/10740 T/10767 TF/10L DF/500 GPM/385 27' 37 MIN SLD F/10767 T/10860 TF/HS DF/500 GPM/385 95' 92 MIN
GRAND CANYON A 1H | 10 | 2020-06-23 09:30 | 2020-06-23 09:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.96 | 10345 | 10345 |  | MILESTONE_START CURVE SECTION ON 6/23/20 @ 09:30 HRS
GRAND CANYON A 1H | 10 | 2020-06-23 21:00 | 2020-06-23 23:00 | 2 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.52 | 10768 | 10860 | 46 | R/D (92' IN 1.78 HRS @ 57 FPH) WOB-15/20K, RPM-20, TRQ-6/8K, SPM-60/60, GPM-388, MRPM-263, SPP-3400/3900 PSI, DIFF-200/500 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0'
GRAND CANYON A 1H | 10 | 2020-06-23 23:00 | 2020-06-23 23:30 | 0.5 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.54 | 10860 | 10860 | 0 | CIRCULATE BOTTOMS UP. GPM-388, PP-3350, RPM-20, TQ-7K
GRAND CANYON A 1H | 10 | 2020-06-23 23:30 | 2020-06-24 01:30 | 2 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 7.63 | 10860 | 10860 | 0 | FLOW CHECK WELL-NO FLOW. POOH 10 STANDS WET.
GRAND CANYON A 1H | 10 | 2020-06-24 01:30 | 2020-06-24 02:00 | 0.5 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.65 | 10860 | 10860 | 0 | FLOW CHECK WELL-NO FLOW. PUMP SLUG
GRAND CANYON A 1H | 10 | 2020-06-24 02:00 | 2020-06-24 02:30 | 0.5 | P | PRDHLCV | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 7.67 | 10860 | 10860 | 0 | PULL ROTATING HEAD AND INSTALL TRIP NIPPLE
GRAND CANYON A 1H | 10 | 2020-06-24 02:30 | 2020-06-24 05:30 | 3 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 7.79 | 10860 | 10860 | 0 | POOH T/BHA. PROPER FILLS ON TRIP OUT. POOH DUE TO INSUFICCIENT BUILD RATES.
GRAND CANYON A 1H | 10 | 2020-06-24 05:30 | 2020-06-24 06:00 | 0.5 | U | PRDHLCV | TRIP | LDBHA | LAY DOWN BIT / BHA | 7.81 | 10860 | 10860 | 0 | LAY DOWN BHA. DRAIN MOTOR, BREAK BIT, AND L/D MUD MOTOR.
GRAND CANYON A 1H | 11 | 2020-06-24 06:00 | 2020-06-24 06:30 | 0.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 7.83 | 10860 | 10860 | 0 | REMOVE MWD, DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR.
GRAND CANYON A 1H | 11 | 2020-06-24 06:30 | 2020-06-24 07:00 | 0.5 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 7.85 | 10860 | 10860 | 0 | PICK UP 6.75" ULTERRA U611S SER 40962: JETS 4-16'S, 1-18, 1-12, TFA: 1.144), 5", 7/8L, 3.8 STG @ 2.50° SLICK; .521 REV/GAL; 4.00' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/250 GPM; MAX DIFF-860 PSI; STALL TRQ-4450 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-62'. BIT TO GAMMA-50', TEST MWD-(FAILED)
GRAND CANYON A 1H | 11 | 2020-06-24 07:00 | 2020-06-24 08:00 | 1 | U | PRDHLCV | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 7.9 | 10860 | 10860 | 0 | TROUBLESHOOT MWD. RECYCLE MUD PUMP MULTIPLE TIMES. MWD NOT PULSING. LAY DOWN MWD TOOL AND PICK UP BACKUP TOOL.
GRAND CANYON A 1H | 11 | 2020-06-24 08:00 | 2020-06-24 08:30 | 0.5 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.92 | 10860 | 10860 | 0 | RIG SERVICE
GRAND CANYON A 1H | 11 | 2020-06-24 08:30 | 2020-06-24 09:00 | 0.5 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 7.94 | 10860 | 10860 | 0 | INSTALL MWD, TEST (GOOD), M/U BIT
GRAND CANYON A 1H | 11 | 2020-06-24 09:00 | 2020-06-24 15:30 | 6.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 8.21 | 10860 | 10860 | 0 | TRIP IN HOLE T/10,860'. PICK UP AGITATOR AFTER STAND 27 (GPM-96), PSI BEFORE AGITATOR- 415 / PSI AFTER AGITATOR- 465, PROPER DISPLACEMENTS ON TRIP IN HOLE. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD. PROPER DISPLACEMENT ON TRIP IN HOLE.
GRAND CANYON A 1H | 11 | 2020-06-24 15:30 | 2020-06-24 22:30 | 7 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.5 | 10860 | 10954 | 13.4 | S/D (94' IN 7 HRS @ 13 FPH) WOB-5/10K, SPM-78, GPM-250, MRPM-130, SPP-1850/2050 PSI, DIFF-100/200 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' LAND/END CURVE SECTION ON 6/25/2020 @ 22:30 (10,954' MD / 10,591' TVD)
GRAND CANYON A 1H | 11 | 2020-06-24 22:30 | 2020-06-24 23:30 | 1 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.54 | 10954 | 10954 | 0 | CIRCULATE BOTTOMS UP. GPM-247, PP-1850, GAS-208u, 0' FLARE.
GRAND CANYON A 1H | 11 | 2020-06-24 22:30 | 2020-06-24 22:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 8.5 | 10954 | 10954 |  | MILESTONE_LAND/END CURVE SECTION ON 6/25/2020 @ 22:30
GRAND CANYON A 1H | 11 | 2020-06-24 22:30 | 2020-06-24 22:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 8.5 | 10954 | 10954 |  | MILESTONE_START HORIZONTAL LATERAL SECTION 6/25/2020 23:30
GRAND CANYON A 1H | 11 | 2020-06-24 23:30 | 2020-06-25 04:30 | 5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.75 | 10954 | 10954 | 0 | POOH T/BHA. PROPER FILLS ON TRIP OUT. REMOVE ROT. HEAD AND INSTALL TRIP NIPPLE.
GRAND CANYON A 1H | 11 | 2020-06-25 04:30 | 2020-06-25 05:00 | 0.5 | P | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 8.77 | 10954 | 10954 | 0 | REMOVE MWD, DRAIN MOTOR, BREAK BIT, AND LAY DOWN MUD MOTOR.
GRAND CANYON A 1H | 11 | 2020-06-25 05:00 | 2020-06-25 06:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.81 | 10954 | 10954 | 0 | SERVICE ST-80, TD, AND DRAWWORKS
GRAND CANYON A 1H | 12 | 2020-06-25 06:00 | 2020-06-25 07:00 | 1 | P | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 8.85 | 10954 | 10954 | 0 | PICK UP 6.75" HALLIBURTON GTD64C SER 13430004: JETS 6-16'S, TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 3.85' BIT TO BEND 5-9/16" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-69'. BIT TO GAMMA-57'
GRAND CANYON A 1H | 12 | 2020-06-25 07:00 | 2020-06-25 09:00 | 2 | U | PRDHLLT | SFTY | INCINV | INCIDENT INVESTIGATION | 8.94 | 10954 | 10954 | 0 | WHILE LIFTING MWD TOOL WITH HYDRAULIC HOIST, THE MWD LIFTING SLING CAUGHT THE HANDRAIL AND LIFTED THE FLOOR PLATE CAUSING THE PERPENDICULAR FLOOR PLATE TO LIFT AS WELL. THE PERPENDICULAR PLATE LIFTED APPROXIMATELY 6 INCHES BEFORE RELEASING AND FALLING BACK TO ORIGINAL POSITION CAUSING AN IMPACT FORCE TO BREAK THE TWO HINGES THAT SUPPORTED PLATE. THE FLOOR PLATE THEN SWIVELED DOWN LIKE A TRAP DOOR LEAVING A 2' X 3-1/2' HOLE IN THE FLOOR. NO ONE WAS HURT OR INJURED AND CLOSEST PERSONNEL WAS 5' FROM HOLE. BARRICADED AREA OFF SO THAT OPERATIONS COULD SAFELY RESUME WHILE WELDER WAS IN ROUTE TO RIG.
GRAND CANYON A 1H | 12 | 2020-06-25 09:00 | 2020-06-25 10:00 | 1 | P | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 8.98 | 10954 | 10954 | 0 | INSTALL MWD, TEST (GOOD), AND MAKE UP BIT.
GRAND CANYON A 1H | 12 | 2020-06-25 10:00 | 2020-06-25 13:00 | 3 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.1 | 10954 | 10954 | 0 | TRIP IN HOLE T/5,988'. PROPER DISPLACEMENT ON TRIP IN HOLE.
GRAND CANYON A 1H | 12 | 2020-06-25 13:00 | 2020-06-25 14:30 | 1.5 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 9.17 | 10954 | 10954 | 0 | SHUT WELL IN AND REPAIR DAMAGED FLOOR PLATE WITH WELDER.
GRAND CANYON A 1H | 12 | 2020-06-25 14:30 | 2020-06-25 15:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.19 | 10954 | 10954 | 0 | RIG SERVICE
GRAND CANYON A 1H | 12 | 2020-06-25 15:00 | 2020-06-25 16:30 | 1.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.25 | 10954 | 10954 | 0 | TRIP IN HOLE T/9,786'. PROPER DISPLACEMENT ON TRIP IN HOLE.
GRAND CANYON A 1H | 12 | 2020-06-25 16:30 | 2020-06-25 17:00 | 0.5 | U | PRDHLLT | WAIT | WOW | WAIT ON WEATHER | 9.27 | 10954 | 10954 | 0 | WAITING ON WEATHER DUE TO LIGHTNING.
GRAND CANYON A 1H | 12 | 2020-06-25 17:00 | 2020-06-25 18:00 | 1 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.31 | 10954 | 10954 | 0 | TRIP IN HOLE T/10,199'. PROPER DISPLACEMENT ON TRIP IN HOLE.
GRAND CANYON A 1H | 12 | 2020-06-25 18:00 | 2020-06-25 18:30 | 0.5 | P | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 9.33 | 10954 | 10954 | 0 | WASH AND REAM F/10,199' T/10,954'.
GRAND CANYON A 1H | 12 | 2020-06-25 18:30 | 2020-06-25 23:30 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.54 | 10954 | 11464 | 102 | R/D (510' IN 4.58 HRS @ 111 FPH) WOB-25/35K, RPM-80, TRQ-10/13K, SPM-62/62, GPM-398, MRPM-271, SPP-3700/4500 PSI, DIFF-600/8900 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' START HORIZONTAL LATERAL SECTION ON 6/25/20 @ 18:30
GRAND CANYON A 1H | 12 | 2020-06-25 23:30 | 2020-06-26 01:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.6 | 11464 | 11524 | 40 | S/D (60' IN 1.92 HRS @ 31 FPH) WOB-15/25K, SPM-62/62, GPM-398, MRPM-271, SPP-3700/3900 PSI, DIFF-200/400 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' SLIDE DEPTHS: SLD F/11098 T/11123 @140R 2040-2140 (1HR) SLD F/11440 T/11475 @20R 2350-0045 (55MIN)
GRAND CANYON A 1H | 12 | 2020-06-26 01:00 | 2020-06-26 01:30 | 0.5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 9.63 | 11524 | 11524 | 0 | TROUBLESHOOT MWD. COULDN'T GET MWD TO SYNC. RECYCLE MUD PUMPS MULTIPLE TIMES.
GRAND CANYON A 1H | 12 | 2020-06-26 01:30 | 2020-06-26 04:00 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.73 | 11524 | 11970 | 178.4 | R/D (446' IN 2.48 HRS @ 180 FPH) WOB-30/38K, RPM-80, TRQ-10/13K, SPM-62/62, GPM-398, MRPM-271, SPP-3700/4500 PSI, DIFF-600/800 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0'
GRAND CANYON A 1H | 12 | 2020-06-26 04:00 | 2020-06-26 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.81 | 11970 | 12040 | 35 | S/D (70' IN 2.02 HRS @ 35 FPH) WOB-15/25K, SPM-62/62, GPM-398, MRPM-271, SPP-3700/3900 PSI, DIFF-200/400 SPI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' SLIDE DEPTHS: SLD F/11632 T/11662 20R 0205-0256 (51MIN) SLD F/11920 T/11935 180 0415-0455 (40MIN) SLD F/12015 T/12040 180 0530-0600 (30MIN)
GRAND CANYON A 1H | 13 | 2020-06-26 06:00 | 2020-06-26 12:30 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.08 | 12040 | 12933 | 137.4 | ROT (893' IN 6.50 HRS @ 146 FPH) WOB-15/25K, RPM-80, TRQ-8/14K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-3500/4200 PSI, DIFF-350/700 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-2'
GRAND CANYON A 1H | 13 | 2020-06-26 12:30 | 2020-06-26 15:00 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.19 | 12933 | 13043 | 44 | S/D (110' IN 2.88 HRS @ 38 FPH) WOB-20/25K, SPM-62/62, GPM-400, MRPM-272, SPP-3500/4000 PSI, DIFF-250/500 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-2' SLIDE DEPTHS: S.DRL F/12120' T/12135' @ 180G 0657-0730, 33MIN S.DRL F/12211' T/12231' @ 180G 0800-0824, 24MIN S.DRL F/12390 T/12420' @ 90R 0930-1030, 60MIN S.DRL F/12580 T/12605' @ 70R 1130-1200, 30MIN S.DRL F/12960' T/12980' @ 80R 1425-1451, 26MIN
GRAND CANYON A 1H | 13 | 2020-06-26 15:00 | 2020-06-26 15:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.21 | 13043 | 13043 | 0 | RIG SERVICE
GRAND CANYON A 1H | 13 | 2020-06-26 15:30 | 2020-06-26 21:30 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.46 | 13043 | 14091 | 174.7 | ROT (1048' IN 6.18 HRS @ 169 FPH) WOB-30/38K, RPM-80, TRQ-8/16K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-3700/4800 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-2' NOTE: SHUTTING IN ON CONNECTION, AVG SICP-100 PSI. FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT.
GRAND CANYON A 1H | 13 | 2020-06-26 21:30 | 2020-06-27 06:00 | 8.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.81 | 14091 | 14277 | 21.9 | S/D (186' IN 8.32 HRS @ 22 FPH) WOB-25/35K, SPM-62/62, GPM-400, MRPM-272, SPP-3700/3850 PSI, DIFF-100/200 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-2' SLIDE DEPTHS: S.DRL F/13148' T/13175' @ 120R 1615-1708, 53MIN S.DRL F/13242' T/13248' @1 80 1733-1800, 27MIN SLD F/13248 T/13259 180 1800-1816 (16MIN) SLD F/13530 T/13548 40L 1930-2011 (31MIN) SLD F/13620 T/13645 40L 2040-2145 (55MIN) SLD F/13726 T/13745 60L 2210-2300 (50MIN) SLD F/13919 T/13949 160L 2345-0130 (105MIN) SLD F/14038 T/14068 180 0200-0320 (80MIN) SLD F/14146 T/14166 180 0355-0505 (70MIN)
GRAND CANYON A 1H | 14 | 2020-06-27 06:00 | 2020-06-27 12:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.06 | 14277 | 15238 | 160.2 | ROT (961' IN 6 HRS @ 160 FPH) WOB-30/38K, RPM-80, TRQ-8/16K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-3700/4800 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-2' NOTE: SHUTTING IN ON CONNECTION, AVG SICP-100 PSI. FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT. AT 14,460' LOST APROXIMATELY 15-20 BBLS.
GRAND CANYON A 1H | 14 | 2020-06-27 12:00 | 2020-06-27 17:00 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.27 | 15238 | 15319 | 16.2 | S/D (81' IN 5 HRS @ 16 FPH) WOB-25/35K, SPM-62/62, GPM-400, MRPM-272, SPP-3700/3850 PSI, DIFF-100/200 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-2' SLIDE DEPTHS: S.DRL F/14478' T/14502' @ 20R 0720-0828, 68MIN S.DRL F/14665' T/14685' @ 30R 0942-1105, 83MIN S.DRL F/14856' T/14869' @ 180R 1417-1306, 49MIN S.DRL F/14950' T/12962' @ 180G 1336-1424, 48MIN S.DRL F/15236' T/15248' @ 180G 1555-1647, 52MIN
GRAND CANYON A 1H | 14 | 2020-06-27 17:00 | 2020-06-27 17:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 11.29 | 15319 | 15319 | 0 | RIG SERVICE
GRAND CANYON A 1H | 14 | 2020-06-27 17:30 | 2020-06-27 22:30 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.5 | 15319 | 16198 | 175.8 | ROT (879' IN 4.97 HRS @ 177 FPH) WOB-30/38K, RPM-80, TRQ-10/20K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-4000/5000 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' NOTE: SHUTTING IN ON CONNECTION, AVG SICP-400/600 PSI. FLARE-10-20' ON BOTTOMS UP AND NO MUD CUT.
GRAND CANYON A 1H | 14 | 2020-06-27 22:30 | 2020-06-28 06:00 | 7.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.81 | 16198 | 16292 | 12.5 | S/D (94' IN 7.53 HRS @ 12 FPH) WOB-25/35K, SPM-62/62, GPM-400, MRPM-272, SPP-4000/4100 PSI, DIFF-100/200 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' SLIDE DEPTHS: SLD F/15527 T/15535 @180 1845-1930 (45MIN) SLD F/15615 T/15630 @160R 2000-2120 (1HR20MIN) SLD F/15987 T/16011 @150R 2312-010520 (1HR53MIN) SLD F/16080 T/16110 @130R 0130-0324 (2HR54MIN) SLD F/16275 T/16292 @130R 0420-0600 (1HR40MIN)
GRAND CANYON A 1H | 15 | 2020-06-28 06:00 | 2020-06-28 08:30 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.92 | 16292 | 16634 | 136.8 | ROT (342' IN 2.87 HRS @ 119 FPH) WOB-30/38K, RPM-80, TRQ-10/20K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-4000/5000 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' NOTE: SHUTTING IN ON CONNECTION, AVG SICP-400/600 PSI. FLARE-10-20' ON BOTTOMS UP AND NO MUD CUT.
GRAND CANYON A 1H | 15 | 2020-06-28 08:30 | 2020-06-28 16:30 | 8 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.25 | 16634 | 16738 | 13 | S/D (104' IN 7.63 HRS @ 13.6 FPH) WOB-25/35K, SPM-62/62, GPM-400, MRPM-272, SPP-4000/4100 PSI, DIFF-100/200 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' SLIDE DEPTHS: S.DRL F/16292' T/16303' @ 20L 0600-0626, 26MIN S.DRL F/16458 T/16491' @ 50L 0740-1010, 130MIN S.DRL F/16562' T/16595' @ 100L 1045-1326, 161MIN S.DRL F/16657' T/16684' @ 120L 1411-1612, 121MIN
GRAND CANYON A 1H | 15 | 2020-06-28 16:30 | 2020-06-28 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.27 | 16738 | 16738 | 0 | RIG SERVICE.
GRAND CANYON A 1H | 15 | 2020-06-28 17:00 | 2020-06-28 17:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.29 | 16738 | 16738 | 0 | CIRC W/ CHANGING SWAB IN #1 MUD PUMP, GPM-320, SPP-2730, TOR-7/10K.
GRAND CANYON A 1H | 15 | 2020-06-28 17:30 | 2020-06-28 23:00 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.52 | 16738 | 17443 | 128.2 | ROT (705' IN 5.67 HRS @ 124 FPH) WOB-30/38K, RPM-80, TRQ-10/20K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-4000/5000 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' NOTE: SHUTTING IN ON CONNECTION, AVG SICP-400/600 PSI. FLARE-10-20' ON BOTTOMS UP AND NO MUD CUT.
GRAND CANYON A 1H | 15 | 2020-06-28 23:00 | 2020-06-29 06:00 | 7 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.81 | 17443 | 17517 | 10.6 | S/D (74' IN 6.8 HRS @ 11 FPH) WOB-25/35K, SPM-62/62, GPM-400, MRPM-272, SPP-4000/4100 PSI, DIFF-100/200 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' SLIDE DEPTHS: SLD F/16751 T/16766 @170L 1800-1930 (1HR30MIN) SLD F/16836 T/16846 @180 2005-2105 (1HR) SLD F/17125 T/17147 @80R 2255-0055 (2HR) SLD F/17410 T/17425 @140L 0300-0420 (1HR20MIN) SLD F/17505 T/17512 @180 0500-0600 (1HR)
GRAND CANYON A 1H | 16 | 2020-06-29 06:00 | 2020-06-29 09:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.94 | 17517 | 17886 | 123 | ROT (369' IN 3 HRS @ 123 FPH) WOB-30/38K, RPM-80, TRQ-10/20K, SPM-62/62, GPM-400, MRPM-272, TRPM-352, SPP-4000/5000 PSI, DIFF-900/1100 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-6' NOTE: SHUTTING IN ON CONNECTION, AVG SICP-400/600 PSI. FLARE-10-20' ON BOTTOMS UP AND NO MUD CUT TD WELL ON 6/29/20 @ 09:00 (17,886' MD / 10,233' TVD)
GRAND CANYON A 1H | 16 | 2020-06-29 09:00 | 2020-06-29 09:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 12.94 | 17886 | 17886 |  | MILESTONE_TD WELL ON 6/29/20 @ 09:00
GRAND CANYON A 1H | 16 | 2020-06-29 09:00 | 2020-06-29 10:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.98 | 17886 | 17886 | 0 | CIRCULATE BOTTOMS UP, SPP-4,300 PSI, GPM-400, TQ-(10-13K), RPM-80, P/U-210K, S/O-180K, MAS GAS-1512 UNITS, FLARE-10-20'.
GRAND CANYON A 1H | 16 | 2020-06-29 10:00 | 2020-06-29 10:30 | 0.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 13 | 17886 | 17886 | 0 | BACKREAM OUT OF HOLE F/17,886' T/17,713', GPM-400, PP-4050 PSI, TQ-(10-14K) RPM-80
GRAND CANYON A 1H | 16 | 2020-06-29 10:30 | 2020-06-29 11:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 13.02 | 17886 | 17886 | 0 | CIRCULATE W/ CHANGING DIE BLOCKS F/ GRABBERS ON TOP DRIVE.
GRAND CANYON A 1H | 16 | 2020-06-29 11:00 | 2020-06-29 12:00 | 1 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 13.06 | 17886 | 17886 | 0 | BACKREAM OUT OF HOLE F/17,713' T/16,961', GPM-400, PP-4050 PSI, TQ-(10-14K) RPM-80
GRAND CANYON A 1H | 16 | 2020-06-29 12:00 | 2020-06-29 13:30 | 1.5 | P | PRDHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 13.13 | 17886 | 17886 | 0 | WASH AND REAM IN HOLE F/16,929' T/17,886'. GPM-400, PP-3850 PSI, TQ-(10-13K) RPM-80
GRAND CANYON A 1H | 16 | 2020-06-29 13:30 | 2020-06-29 16:30 | 3 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.25 | 17886 | 17886 | 0 | CLEAN UP CYCLE @ TD: PUMP (3) 30 BBL SWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 3 B/U, RPM-80, TRQ-9/14K, SPM: 62/62, GPM-400, SPP-4200 PSI. 1ST SWEEP UP START TQ 14/15K END=13K, ROT.WT=208 2ND SWEEP UP END TQ= 11K , ROT. WT.=215 3RD SWEEP UP END TQ= 9K, ROT WT.=215 LOSS OF 5K TORQUE FROM DOING CLEAN UP CYCLE, SHAKERS CLEAN.
GRAND CANYON A 1H | 16 | 2020-06-29 16:30 | 2020-06-29 20:00 | 3.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 13.4 | 17886 | 17886 | 0 | BACKREAM OUT OF HOLE F/17,886' T/16,000', PULL OUT OF HOLE F/ 16,000 T/ 15,500', FILLING BACKSIDE WITH CALCULATED FILL OF 8.9 PPG MUD.
GRAND CANYON A 1H | 16 | 2020-06-29 20:00 | 2020-06-29 22:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.48 | 17886 | 17886 | 0 | CIRCULATE BOTTOMS UP @ 15,500', MAX GAS ON BOTTOMS UP 2330 UNITS,MAX CASING PRESSURE-50 PSI, MUD CUT F/ 8.9 PPG T/ 8.8 PPG, 15'-30' FLARE, PUMP 200 BBL 30 PPB LCM PILL, AND DISPLACE W/ 206 BBLS 8.9 PPG OBM. (SICP-358)
GRAND CANYON A 1H | 16 | 2020-06-29 22:00 | 2020-06-30 01:30 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 13.63 | 17886 | 17886 | 0 | STRIP OUT OF HOLE F/15,500' T/10,419', PUMPING CALCULATED HOLE FILLS 1.9 BBLS PER STAND DOWN BACKSIDE W/ 8.9 PPG OBM.
GRAND CANYON A 1H | 16 | 2020-06-30 01:30 | 2020-06-30 02:30 | 1 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 13.67 | 17886 | 17886 | 0 | CIRCULATE BOTTOMS UP @ 10,419'. SHUT WELL IN AND MONITOR SICP. SICP-226 PSI, PICK UP T/10,322', PUMP 66 BBLS 14.1 PPG MUD CAP, DISPLACE MUD CAP W/ 107 BBLS 8.9 PPG OBM @ 10,322', PUMP MUD CAP W/ 100% RETURNS, CALCULATED TOP OF MUD CAP AFTER PULLING ABOVE-8,891'.
GRAND CANYON A 1H | 16 | 2020-06-30 02:30 | 2020-06-30 03:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 13.71 | 17886 | 17886 | 0 | PULL OUT OF HOLE F/ 10,322' T/ 8,500', MONITOR HOLE FILLS ON TRIP TANK WHILE PULLING OUT OF HOLE.
GRAND CANYON A 1H | 16 | 2020-06-30 03:30 | 2020-06-30 04:00 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 13.73 | 17886 | 17886 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE. FLOW CHECK-NO FLOW
GRAND CANYON A 1H | 16 | 2020-06-30 04:00 | 2020-06-30 06:00 | 2 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 13.81 | 17886 | 17886 | 0 | LAY DOWN DRILL PIPE F/8,500' T/6,500'. MONITOR HOLE FILLS ON TRIP TANK WHILE PULLING OUT OF HOLE.
GRAND CANYON A 1H | 17 | 2020-06-30 06:00 | 2020-06-30 11:00 | 5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 14.02 | 17886 | 17886 | 0 | LAY DOWN DRILL PIPE F/6,500' T/BHA'. MONITOR HOLE FILLS ON TRIP TANK WHILE PULLING OUT OF HOLE. CHECK FLOW @ BHA-NO FLOW.
GRAND CANYON A 1H | 17 | 2020-06-30 11:00 | 2020-06-30 12:00 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 14.06 | 17886 | 17886 | 0 | LAY DOWN MWD, MONELS, UBHO, PONY COLLAR, AND BTI VALVE. DRAIN MOTOR, BREAK BIT, AND LAY DOWN MUD MOTOR.
GRAND CANYON A 1H | 17 | 2020-06-30 12:00 | 2020-06-30 13:00 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 14.1 | 17886 | 17886 | 0 | PULL WEAR BUSHING, REMOVE RIG ELEVATORS, AND CLEAN/ORGANIZE RIG FLOOR.
GRAND CANYON A 1H | 17 | 2020-06-30 13:00 | 2020-06-30 14:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 14.15 | 17886 | 17886 | 0 | HOLD PJSM, R/U EXPRESS CASING TOOLS AND EQUIPMENT.
GRAND CANYON A 1H | 17 | 2020-06-30 14:00 | 2020-06-30 14:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 14.17 | 17886 | 17886 | 0 | RIG SERVICE, REPAIR CATWALK WINCH CABLE.
GRAND CANYON A 1H | 17 | 2020-06-30 14:30 | 2020-06-30 15:30 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 14.21 | 17886 | 17886 | 0 | CONTINUE R/U EXPRESS CASING EQUIPMENT.
GRAND CANYON A 1H | 17 | 2020-06-30 15:30 | 2020-07-01 00:30 | 9 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.58 | 17886 | 17886 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING W/CENTRALIZERS IN MIDDLE OF JTS., 1 INNOVEX DV FLOAT COLLAR, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/ 8,402', FILLING PIPE ON THE FLY, SOLID BODY CENTALIZERS EVERY 4TH JOINT T/10,164', MONITOR DISPLACEMENTS ON TRIP TANK, PROPER DISPLACEMENTS WHILE RUNNING CASING.
GRAND CANYON A 1H | 17 | 2020-07-01 00:30 | 2020-07-01 01:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.6 | 17886 | 17886 | 0 | FLOW CHECK, REMOVE TRIP NIPPLE / INSTALL ROT. HEAD
GRAND CANYON A 1H | 17 | 2020-07-01 01:00 | 2020-07-01 02:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 14.65 | 17886 | 17886 | 0 | SWAP OUT CRT AND CSG ELEVATORS FOR 5-1/2" CASING
GRAND CANYON A 1H | 17 | 2020-07-01 02:00 | 2020-07-01 03:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.69 | 17886 | 17886 | 0 | RUN 5-1/2" PRODUCTION CASING T/9,022'. PROPER DISPLACEMENTS WHILE RUNNING CASING.
GRAND CANYON A 1H | 17 | 2020-07-01 03:00 | 2020-07-01 03:30 | 0.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 14.71 | 17886 | 17886 | 0 | CIRCULATE AND CONDITION @ 9,022'. GPM-320, PP-800 PSI, FLARE-0'. LOST APPROXIMATELY 20 BBLS DURING CIRCULATION. HEAVIEST MW-9.4 PPG
GRAND CANYON A 1H | 17 | 2020-07-01 03:30 | 2020-07-01 05:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.77 | 17886 | 17886 | 0 | RUN PRODUCTION CASING T/10,308'
GRAND CANYON A 1H | 17 | 2020-07-01 05:00 | 2020-07-01 05:30 | 0.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 14.79 | 17886 | 17886 | 0 | CIRCULATE AND CONDITION @ 10,308'. CIRCULATE MUD CAP OUT. GPM-288, INITIAL PP-1050 PSI, FLARE-0'. FINAL PP-850 PSI. LOST APPROXIMATELY 15 BBLS DURING CIRCULATION. HEAVIEST MW-11.6
GRAND CANYON A 1H | 17 | 2020-07-01 05:30 | 2020-07-01 06:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.81 | 17886 | 17886 | 0 | STRIP IN PRODUCTION CASING T/10,700' @ 125'/MIN. CSG PSI-300 PSI. BLEEDING 1.3 BBLS EVERY JOINT.
GRAND CANYON A 1H | 18 | 2020-07-01 06:00 | 2020-07-01 06:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.83 | 17886 | 17886 | 0 | RAN 5.5" PRODUCTION CASING F/10,700' - T/11,231'
GRAND CANYON A 1H | 18 | 2020-07-01 06:30 | 2020-07-01 08:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.9 | 17886 | 17886 | 0 | CIRCULATED & CONDITIONED MUD CIRCULATING OUT MUD CAP SPM-80, BPM-6, SPP-975 PSI, CP-0 PSI, FLARE-3/4', 1 FULL OPEN CHOKE, O BBLS OF MUD WAS LOST, SICP-350 PSI. HEAVIEST MW OUT-11.3 PPG
GRAND CANYON A 1H | 18 | 2020-07-01 08:00 | 2020-07-01 12:30 | 4.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.08 | 17886 | 17886 | 0 | STRIPPED 5.5" PRODUCTION CASING INTO HOLE F/11,231' - T/15,890', CP-350/150 PSI, BLEEDING 1.3 BBL/JOINT. HIT TIGHT SPOT AT 15,843'.
GRAND CANYON A 1H | 18 | 2020-07-01 12:30 | 2020-07-01 14:00 | 1.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 15.15 | 17886 | 17886 | 0 | CIRCULATED & CONDITIONED HOLE DUE TO HITTING TIGHT SPOT @ 15,843', P/U-290K, S/O-180K, S/W-235K, SPM-80, BPM-6, SPP-1250 PSI, CP-0 PSI, MAX FLARE ON BOTTOMS UP-15'. LOST A TOTAL OF 35 BBLS DURING COMPLETE CIRCULATION, SICP-650 PSI. HEAVIEST MW-9.5 PPG. CIRCULATED OUT LCM PILL.
GRAND CANYON A 1H | 18 | 2020-07-01 14:00 | 2020-07-01 16:30 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 15.25 | 17886 | 17886 | 0 | RAN 5.5" PRODUCTION CASING F/15,166' - T/17,870' PICKED UP 1 JOINT & 1 PUP JOINT TO TAG BOTTOM @ 17,886', TAGGED BOTTOM LAY DOWN 1 JOINT & PUP JOINT, REMOVE ROTATING HEAD, P/U LANDING JOINT AND LAND CASING ON HANGER W/160K. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: 1-INNOVEX 5''FLOAT SHOE, 2 JTS OF 5'' CSG. 1-INNOVEX FLOAT COLLAR, 1-GEODYNAMICS TOE SLEEVE VALVE, RAN 8,371.79 (181 JTS) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER & 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING, RAN 9435.15' (213 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING. FOR TOTAL OF 385 FULL JTS OF 5'' 18# P-110 ICY WEDGE 625 & 5.5" 23# P-110 ICY BLUE CASING. CASING SHOE @ 17,870.17' TOP OF FLOAT COLLAR @ 17,772.55' BOTTOM OF TOE SLEEVE VALVE @ 17,772.55' TOP OF TOE SLEEVE VALVE @ 17,747.05 TOP OF X-OVER @ 9,465.14' TOP OF MARKER JOINT ABOVE X-OVER @ 9,397.99' NOTE: LOST 130 BBLS DURING COMPLETE CASING RUN.
GRAND CANYON A 1H | 18 | 2020-07-01 16:30 | 2020-07-01 17:00 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 15.27 | 17886 | 17886 | 0 | RIG DOWN EXPRESS CRT INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 500 PSI
GRAND CANYON A 1H | 18 | 2020-07-01 17:00 | 2020-07-01 19:30 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.38 | 17886 | 17886 | 0 | CIRCULATED & CONDITIONED HOLE. SPM-80, BPM-6, SPP-1157 PSI, CP-0 PSI, MAX FLARE ON BOTTOMS UP-15/20'. LOST A TOTAL OF 154 BBLS DURING COMPLETE CIRCULATION, SICP-562 PSI. HEAVIEST MW-9.2 PPG
GRAND CANYON A 1H | 18 | 2020-07-01 19:30 | 2020-07-01 22:30 | 3 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 15.5 | 17886 | 17886 | 0 | HELD PJSM, SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD, FLUSHED THROUGH & TESTED CEMENTING LINES T/9000 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: DROP BOTTOM PLUG, PUMPED @ 6 BPM 50 BBL 9.5 PPG WEIGHTED SPACER, 250 BBL 13.5 PPG 840 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 349 BBLS OF FRESH WATER WITH BIOCIDE & CORPLEX @ 6 BPM, OBSERVED 97% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2700 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3700 PSI, HELD FOR 5 MIN, BLED BACK 5 BBLS. FLOATS HELD. PLUG DOWN @ 21:55 HRS 07/01/2020: NOTE: CEMENT WITH PARTIAL RETURNS. PUMPED SPACER AND CEMENT THRU CHOKE MANIFOLD @ 35-40% OPEN. (LOST APPROXIMATELY 100 BBLS - 67% RETURNS), DISPLACE THRU CHOKE MANIFOLD MONITORING BBL IN/BBL OUT, LOST APPROXIMATELY 12 BBLS DURING DISPLACEMENT - 97% RETURNS) TOTAL APPROXIMATELY LOSS DURING CEMENT JOB 112 BBLS. INITIAL SICP-0 PSI. NOTE: MAX CASING PSI W/ PUMPING CEMENT - 1141 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT - 825 PSI CALCULATED TOP OF CEMENT-5,384'
GRAND CANYON A 1H | 18 | 2020-07-01 22:30 | 2020-07-01 23:00 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 15.52 | 17886 | 17886 | 0 | RIG DOWN CEMENT HEAD AND REMOVE ROTATING HEAD F/ LANDING JOINT.
GRAND CANYON A 1H | 18 | 2020-07-01 23:00 | 2020-07-01 23:30 | 0.5 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 15.54 | 17886 | 17886 | 0 | MONITOR WELL ON TRIP TANK, WELL FLOWING 3.5 BBLS/HR, FLOWED BACK 1.17 BBLS, SHUT WELL IN, SICP-100 PSI
GRAND CANYON A 1H | 18 | 2020-07-01 23:30 | 2020-07-02 00:30 | 1 | P | PRDHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 15.58 | 17886 | 17886 | 0 | INSTALL CASING SWEDGE W/ LOW TORQUE VALVE ON LANDING JOINT, INSTALL TURN BUCKLES ON BOP STACK, REMOVE BOP HANDLER F/ BOP'S, R/D CASING ELEVATORS AND CASING BAILS, INSTALL MOUSE HOLE T/ LAY DOWN DRILL PIPE IN DERRICK.
GRAND CANYON A 1H | 18 | 2020-07-02 00:30 | 2020-07-02 06:00 | 5.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 15.81 | 17886 | 17886 | 0 | MONITOR SICP W/ LAYING DOWN DRILL PIPE @ APPROXIMATELY 945'/HR IN MOUSEHOLE AND CLEANING MUD PITS. SICP VALUES: 23:30- 40 PSI 00:00- 146 PSI 01:00- 220 PSI 02:00- 315 PSI 03:00- 355 PSI 04:00- 415 PSI 05:00- 463 PSI 05:30- 480 PSI
GRAND CANYON A 1H | 19 | 2020-07-02 06:00 | 2020-07-02 13:30 | 7.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.13 | 17886 | 17886 | 0 | LAY DOWN DRILL PIPE RACKED BACK IN DERRICK DOWN WHILE WAITING ON CEMENT & CLEANING MUD TANKS SICP VALUES: 06:00- 503 PSI 07:00- 539 PSI 08:00- 573 PSI 09:00- 605 PSI 10:00- 633 PSI 11:00- 655 PSI 12:00- 676 PSI 13:00- 695 PSI 14:00- 712 PSI
GRAND CANYON A 1H | 19 | 2020-07-02 13:30 | 2020-07-02 15:00 | 1.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 16.19 | 17886 | 17886 | 0 | LAY DOWN & LOAD OUT ALL 4.5" HANDLING TOOLS
GRAND CANYON A 1H | 19 | 2020-07-02 15:00 | 2020-07-02 16:00 | 1 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 16.23 | 17886 | 17886 | 0 | BLED OFF CASING PRESSURE F/725 PSI TO 0 PSI WITH ONE FULL OPEN CHOKE BACK TO TRIP TANK #1 PRESSURE BLED OFF BLEEDING BACK A TOTAL OF 2 BBLS, MONITORED FLOW AT TRIP TANK FOR 45 MIN AND NO FLOW WAS DETECTED
GRAND CANYON A 1H | 19 | 2020-07-02 16:00 | 2020-07-02 18:00 | 2 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 16.31 | 17886 | 17886 | 0 | LAID DOWN CASING LANDING JOINT, PICKED UP STREAMFLO WASHOUT TOOL & MADE UP TO JOINT OF 4.5", RAN WASHOUT TOOL INTO HOLE DOWN TO WELLHEAD, WASHED OUT WELLHEAD, PICKED UP LAID OUT WASHOUT TOOL & MADE UP PACK-OFF TOOL TO JOINT OF DRILL PIPE, RAN PACK-OFF INTO WELLHEAD & SET SAME, REMOVED SETTING JOINT & LAID OUT SAME, PICKED UP RODS INSERTED BPV & SECURED WELL
GRAND CANYON A 1H | 19 | 2020-07-02 18:00 | 2020-07-02 21:00 | 3 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 16.44 | 17886 | 17886 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE & INSTALL WEATHER CAP AND SECURE WELL. RELEASE WELL ON 7/02/2020 @ 21:00.
GRAND CANYON A 1H | 19 | 2020-07-02 21:00 | 2020-07-02 21:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 16.44 | 17886 | 17886 |  | MILESTONE_WELL RELEASE ON 7/02/2020 @ 21:00
GRAND CANYON A 1H | 19 | 2020-07-02 21:00 | 2020-07-03 01:00 | 4 | P | MOBDMOB | RURD | RDMUD | RIG DOWN MUD SUPPLY / EQUIPMENT | 16.44 | 17886 | 17886 | 0 | CLEAN MUD TANKS WHILE RIGGING DOWN BACK YARD.
GRAND CANYON A 1H | 19 | 2020-07-03 01:00 | 2020-07-03 06:00 | 5 | P | MOBDMOB | BOP | ND | NIPPLE DOWN BOP | 16.44 | 17886 | 17886 | 0 | PERFORM 90 DAY TD INSPECTION, RIG DOWN BACK YARD, CLEAN RIG WITH 3RD PARTY PRESSURE WASHERS. BEGIN RIGGING DOWN TOP DRIVE AND PREP TO SET ON DOGS. RIG RELEASE ON 7/3/2020 @ 06:00. TURN OVER TO COMPLETION ON 7/3/2020 @ 06:00
GRAND CANYON A 1H | 19 | 2020-07-03 06:00 | 2020-07-03 06:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 16.44 | 17886 | 17886 |  | MILESTONE_RIG RELEASE ON 7/3/2020 @ 06:00
GRAND CANYON A 1H | 19 | 2020-07-03 06:00 | 2020-07-03 06:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 16.44 | 17886 | 17886 |  | MILESTONE_TURN OVER TO COMPLETION ON 7/3/2020 @ 06:00
KLONDIKE MILL H08 KL | 1 | 2022-02-01 08:15 | 2022-02-01 09:30 | 1.25 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/KLONDIKE RUSH H06 KL T/KLONDIKE MILL H08 KL; SET MATS, WALK F/KLONDIKE RUSH H06 KL T/KLONDIKE MILL H08 KL; CENTER SUB OVER CONDUCTOR
KLONDIKE MILL H08 KL | 1 | 2022-02-01 08:15 | 2022-02-01 08:15 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 2/1/2022 @ 08:15
KLONDIKE MILL H08 KL | 1 | 2022-02-01 09:30 | 2022-02-01 10:00 | 0.5 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 0 | 108 | 108 | 0 | L/D LANDING JOINT, REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 10:00 | 2022-02-01 11:00 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 11:00 | 2022-02-01 11:30 | 0.5 | P | MOBDMOB | TRIP | BHA | TRIP FOR BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, TAG BOTTOM @ 108'.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 11:30 | 2022-02-01 11:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 2/1/2022 @ 11:30.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 11:30 | 2022-02-01 12:00 | 0.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.02 | 108 | 277 | 338 | ROTATE (277’ IN .5 HRS @ 554 FPH) WOB-10-20K, RPM-50, TRQ- 1K/3K, SPM-62/62/62, GPM-600, MMRPM-100, TRPM-150, SPP-600/850 PSI, DIFF 100/250 PSI.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 12:00 | 2022-02-01 12:45 | 0.75 | U | SFHL | DPROB | DFAIL | DOWNHOLE FAILURE | 0.05 | 277 | 277 | 0 | ATTEMPTED TO GET SURVEY @ 277’, MWD WAS NOT PULSING, TRIP OUT THE HOLE, INSPECTED MWD TOOL AND OBSERVED THAT MWD WAS NOT COMPLETELY SEATED IN THE SLEEVE, RESEAT MWD TOOL, TRIP IN THE HOLE T/277’ AND CONTINUE DRILLING AHEAD.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 12:45 | 2022-02-01 18:15 | 5.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.28 | 277 | 2668 | 434.7 | ROTATE ( 2,391’ IN 6.88 HRS @ 347.36 FPH) WOB-25-35K, RPM-100, TRQ- 5K/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2100/2700 PSI, DIFF 300/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/ SOAP/ SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 30 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM
KLONDIKE MILL H08 KL | 1 | 2022-02-01 18:15 | 2022-02-01 19:00 | 0.75 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.31 | 2668 | 2828 | 213.3 | SLIDE (160' IN .62 HRS @ 259.46 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2,100/2,600 PSI, DIFF-200/500 PSI. SLIDE DEPTH: SLD F/566 T/581 15' TF-60MG 1340-1342 SLD F/848 T/868 20' TF-70MG 1415-1418 SLD F/1035 T/1055 20' TF-30R 1436-1439 SLD F/1313 T/1333 20' TF-30R 1517-1521 SLD F/1415 T/1430 15' TF-60R 1572-1536 SLD F/1595 T/1615 20' TF-60R 1600-1603 SLD F/1695 T/1710 15' TF-60R 1615-1619 SLD F/1789 T/1809 20' TF-30R 1631-1634 SLD F/2254 T/2274 20' TF-60R 1805-1811 SLD F/2627 T/2642 15' TF-120R 1834-1840
KLONDIKE MILL H08 KL | 1 | 2022-02-01 19:00 | 2022-02-01 19:45 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.34 | 2828 | 2828 | 0 | PUMP 2-30 BBL SOAP AND SAP SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K
KLONDIKE MILL H08 KL | 1 | 2022-02-01 19:45 | 2022-02-01 20:30 | 0.75 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.38 | 2828 | 2828 | 0 | TRIP OUT OF HOLE F/2,828' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 20:30 | 2022-02-01 21:45 | 1.25 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.43 | 2828 | 2828 | 0 | REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. NOTE: INSPECTED MOTOR AND BIT: MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-1-NO-A-X-0-NO-TD.
KLONDIKE MILL H08 KL | 1 | 2022-02-01 21:45 | 2022-02-01 22:30 | 0.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.46 | 2828 | 2828 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS
KLONDIKE MILL H08 KL | 1 | 2022-02-01 22:30 | 2022-02-02 01:30 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.58 | 2828 | 2828 | 0 | RUN 10 3/4" 45.5# J-55 BT&C CASING T/2,812'. RAN 36 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 92K (W/O BLOCKS). SHOE- 2,812' TOP OF FLOAT COLLAR- 2,730' 16 JOINTS LEFT OUT- 627.20'
KLONDIKE MILL H08 KL | 1 | 2022-02-02 01:30 | 2022-02-02 02:45 | 1.25 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.64 | 2828 | 2828 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-337, SPP-1175 PSI. NO LOSSES.
KLONDIKE MILL H08 KL | 1 | 2022-02-02 02:45 | 2022-02-02 03:15 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.66 | 2828 | 2828 | 0 | RIG DOWN CRT, L/D LANDING JOINT, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
KLONDIKE MILL H08 KL | 1 | 2022-02-02 03:15 | 2022-02-02 05:15 | 2 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.74 | 2828 | 2828 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,500 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 304 BBLS 11.6 PPG LEAD CEMENT, 78 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 271 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/670 PSI PRESSURED UP T/1270 PSI (500 PSI OVER) @ 4 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 211 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS. OFFLINE: REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, CHANGE SAVOR SUB, SLIP AND CUT DRILL LINE WHILE CEMENTING
KLONDIKE MILL H08 KL | 1 | 2022-02-02 05:15 | 2022-02-02 06:00 | 0.75 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.77 | 2828 | 2828 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
KLONDIKE MILL H08 KL | 2 | 2022-02-02 06:00 | 2022-02-02 07:00 | 1 | P | SFHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 0.81 | 2828 | 2828 | 0 | DRESS OUT WELLHEAD: INSTALL VALVES AND INSTALL SPEED HEAD
KLONDIKE MILL H08 KL | 2 | 2022-02-02 07:00 | 2022-02-02 10:00 | 3 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.94 | 2828 | 2828 | 0 | RAISE AND STAB BOP'S ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, HOOK UP HYDRAULIC LINES F/KOOMEY T/BOP'S, INSTALL TURNBUCKLES, UNLATCH BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALL KILL LINE, KILL LINE CHECK VALVE,, INSTALL CHOKE LINE TO BOP AND CHOKE, FUNCTION TEST SAME NOTE: TEST CHOKE MANIFOLD OFFLINE
KLONDIKE MILL H08 KL | 2 | 2022-02-02 10:00 | 2022-02-02 13:45 | 3.75 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.09 | 2828 | 2828 | 0 | INSTALL TEST PLUG ON TEST JOINT AND TEST BOP'S: TEST TOP RAMS, LOWER RAMS, INSIDE AND OUTSIDE KILL VALVES, INSIDE AND OUTSIDE HCR VALVES, WELLHEAD ADAPTER, FLOOR VALVES, MANUAL IBOP, HYDRAULIC IBOP, KILL LINES BACK TO #1 AND #2 PUMPS, BLINDS AND KILL LINE CHECK VALVE TO 250 PSI LOW / 5000 PSI HIGH, TEST ANNULAR TO 250 PSI LOW / 3500 PSI HIGH. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. REMOVE TEST CAP AND RIG DOWN TESTERS; INSTALL WEAR BUSHING AND CLOSE CASING VALVE
KLONDIKE MILL H08 KL | 2 | 2022-02-02 13:45 | 2022-02-02 15:30 | 1.75 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.17 | 2828 | 2828 | 0 | MAKE UP FLOW LINE TO ROTATING HEAD AND TO FLOW LINE SCISSOR, FILL UP LINE, CASING FILL LINE, FILL MUD TANKS WITH OBM, PERFORM ACCUMULATOR DRAW DOWN TEST.
KLONDIKE MILL H08 KL | 2 | 2022-02-02 15:30 | 2022-02-02 16:30 | 1 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.21 | 2828 | 2828 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE AND MOUSE HOLE. PREP RIG FLOOR FOR BHA
KLONDIKE MILL H08 KL | 2 | 2022-02-02 16:30 | 2022-02-02 17:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.25 | 2828 | 2828 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT
KLONDIKE MILL H08 KL | 2 | 2022-02-02 17:30 | 2022-02-02 22:15 | 4.75 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.45 | 2828 | 2828 | 0 | PICK UP (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49, SN:59253) BIT, 8", 7/8L, 5.9 STG @ 2.0° TS HPW-.012; .155 REV/GAL; 6.04' BIT TO BEND 8.35" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-900 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8"NMDC. BIT TO SVY-65' AND GAMMA-61'. TEST MWD-TEST GOOD, PICK UP 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 11- JTS 5" HWDP, 22 STDS DRILL PIPE AND DSW AGITATOR.
KLONDIKE MILL H08 KL | 2 | 2022-02-02 22:15 | 2022-02-02 23:45 | 1.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.51 | 2828 | 2828 | 0 | TRIP IN HOLE F/304' T/2,725'. PICK UP AGITATOR ON STAND 22: FILL PIPE, PSI BEFORE-702, PSI AFTER-902 @ 319 GPM, HOLE GIVING PROPER DISPLACEMENT.
KLONDIKE MILL H08 KL | 2 | 2022-02-02 23:45 | 2022-02-03 00:45 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.55 | 2828 | 2828 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD, CONFIRM PROPER VALVE ALIGNMENT, FILL GAS SEPERATOR.
KLONDIKE MILL H08 KL | 2 | 2022-02-03 00:45 | 2022-02-03 02:00 | 1.25 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.6 | 2828 | 2838 | 8 | DRILL SHOE TRACK AND FLOAT EQUIPMENT, DRILL 10' NEW FORMATION F/2,828'-T/2,838', GPM-450, SPP- 1420/1530 PSI, DIFF-50/120, RPM-30, TQ-2/6K.
KLONDIKE MILL H08 KL | 2 | 2022-02-03 02:00 | 2022-02-03 02:30 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 1.63 | 2838 | 2838 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-450, SPP-1500 PSI, RPM-30. MUD WT IN/OUT=9.0 PPG.
KLONDIKE MILL H08 KL | 2 | 2022-02-03 02:30 | 2022-02-03 02:45 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.64 | 2838 | 2838 | 0 | PERFORM F.I.T. WITH 9.0 PPG OBM, PUMP 1.8 BBLS, 389 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-2,812' /TVD-2,789'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE ON THE REMOTE CHOKE PANEL.
KLONDIKE MILL H08 KL | 2 | 2022-02-03 02:45 | 2022-02-03 05:30 | 2.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.75 | 2838 | 3623 | 285.5 | ROT (785' IN 2.77 HRS @ 283.39 FPH) WOB: 15/25K, SPM: 90/90/90, GPM: 866, MMRPM: 134, RPM-80, TRPM: 214, TRQ: 5K/10K, SPP: 4000/4,300 PSI, DIFF: 100/350 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY+/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE MILL H08 KL | 2 | 2022-02-03 05:30 | 2022-02-03 06:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.77 | 3623 | 3689 | 132 | SLIDE (66' IN .48 HRS @ 137.5 PH) WOB: 10/16K, SPM: 90/90/90, GPM: 866, MMRPM: 134, SPP:3570/3680 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: F/3,018'-T/3,030', 12' TF:120R 03:39-03:45 F/3,300'-T/3,409', 15', TF:60R, 04:46-04:52 F/3,394'-T/3,409', 15', TF:120R, 05:06-05:13 F/3,489'-T/3,501', 12', TF:150R, 05:27-05:32 F/3,677'-T/3,689', 12', TF:180, 05:55-06:00
KLONDIKE MILL H08 KL | 3 | 2022-02-03 06:00 | 2022-02-03 15:15 | 9.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.16 | 3689 | 7535 | 415.8 | ROT (3,846' IN 9.32 HRS @ 413 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219.5, TRQ: 12K/15K, SPP: 4700/5,700 PSI, DIFF: 800/1000 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE MILL H08 KL | 3 | 2022-02-03 15:15 | 2022-02-03 17:00 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.23 | 7535 | 7699 | 93.7 | SLIDE (164' IN 1.68 HRS @ 97 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4700/5,100 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/3,870'-T/3,882', 12', TF:180, 06:25-06:28 F/3,960'-T/3,972', 12', TF:180, 06:38-06:44 F/4,055'-T/4,067', 12', TF:180, 06:53-07:00 F/4,242'-T/4,257', 15', TF:150R, 07:18-07:25 F/4,335'-T/4,350', 15', TF:230M, 07:34-07:40 F/4,525'-T/4,540', 15', TF:270M, 08:00-08:08 F/6,210'-T/6,225', 15', TF:210M, 12:04-12:16 F/6,305'-T/6,320', 15', TF:140M, 12:28-12:39 F/6,863'-T/6,881',18', TF:140M, 14:02-14:20 F/6,960'-T/6,975', 15', TF:140M, 14:34-14:43 F/7,617'-T/7,637', 20', TF:180M, 16:28-16:42
KLONDIKE MILL H08 KL | 3 | 2022-02-03 17:00 | 2022-02-03 17:30 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.25 | 7699 | 7699 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS RIG MANAGER PRESENT
KLONDIKE MILL H08 KL | 3 | 2022-02-03 17:30 | 2022-02-03 23:15 | 5.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.49 | 7699 | 9439 | 302.6 | ROT (1,740' IN 5.87 HRS @ 296.42 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219.5, TRQ: 12K/15K, SPP: 4700/5,700 PSI, DIFF: 800/1000 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE MILL H08 KL | 3 | 2022-02-03 23:15 | 2022-02-04 02:15 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.61 | 9439 | 9583 | 48 | SLIDE (144' IN 2.88 HRS @ 50 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4700/5,100 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/7,808'-T/7,828' 20', TF:180M, 17:40-18:00 F/7,991'-T/8,016', 25', TF:120M, 18:28-18:54 F/8,390'-T/8,410', 20', TF:225M, 20:08-20:25 F/8,455'-T/8,472', 17', TF:100M, 20:40-21:08 F/8,550'-T/8,575', 25', TF:100M, 21:28-22:03 F/9,206'-T/9,223', 17', TF:90M, 00:04-00:29 F/9,300'-T/9,320', 20', TF:90M, 00:46-01:08
KLONDIKE MILL H08 KL | 3 | 2022-02-04 02:15 | 2022-02-04 03:00 | 0.75 | U | INTHL | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 2.65 | 9583 | 9583 | 0 | C/O O-RING ON 4'' HAMMER UNION, LOCATED ON STANDPIPE AT THE 4'' ISOLATION VALVE NEAR THE #1 MP. NOTE: AFTER INSPECTION OF THE UNION "FACE", A WASH WAS FOUND. BYPASS VALVE AND INSTALL UNION CAP TO ISOLATE #1MP.
KLONDIKE MILL H08 KL | 3 | 2022-02-04 03:00 | 2022-02-04 03:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.67 | 9583 | 9735 | 304 | CONTROL DRILL ON #2 AND #3 PUMPS WHILE GATHERING TOOLS AND PARTS FOR 4'' VALVE C/O. ROTATE (152' IN .5 HRS @ 304 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 104.47, RPM-80, TRPM: 184.47, TRQ: 10K/15K, SPP: 3650/4200 PSI, DIFF: 500/700 PSI.
KLONDIKE MILL H08 KL | 3 | 2022-02-04 03:30 | 2022-02-04 04:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.69 | 9735 | 9767 | 64 | CONTROL DRILL ON #2 AND #3 PUMPS WHILE GATHERING TOOLS AND PARTS FOR 4'' VALVE C/O. BUILD INTERMEDIATE CURVE- SLIDE (32’ IN .5 HRS @ 64 FPH) WOB: 15/20K, SPM: 105/105, GPM: 674, MMRPM: 104.47, SPP: 3,680/3,930 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/9,735'-T/9,767', 32', TF:HS, 03:30-04:00
KLONDIKE MILL H08 KL | 3 | 2022-02-04 04:00 | 2022-02-04 04:30 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.71 | 9767 | 9767 | 0 | INSTALL 4'' VALVE ON #1 MP
KLONDIKE MILL H08 KL | 3 | 2022-02-04 04:30 | 2022-02-04 04:45 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.72 | 9767 | 9777 | 40 | SLIDE (10' IN .25 HRS @ 40 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4700/5,100 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/9,767'-T/9,777' 10', TF:140M, 04:30-04:45
KLONDIKE MILL H08 KL | 3 | 2022-02-04 04:45 | 2022-02-04 05:30 | 0.75 | U | INTHL | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 2.75 | 9777 | 9777 | 0 | CHANGE OUT O-RING ON STANDPIPE ON #2MP. NOTE: UNABLE TO PUMP DUE TO THE LOCATION ON STANDPIPE.
KLONDIKE MILL H08 KL | 3 | 2022-02-04 05:30 | 2022-02-04 06:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.77 | 9777 | 9816 | 78 | SLIDE (39' IN .5 HRS @ 78 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4700/5,100 PSI, DIFF: 300/400 PSI. SLIDE DEPTHS: F/9,777'-T/9,816' 39', TF:140M, 05:30-06:00
KLONDIKE MILL H08 KL | 4 | 2022-02-04 06:00 | 2022-02-04 06:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.78 | 9816 | 9829 | 52 | BUILD INTERMEDIATE CURVE-SLIDE (13' IN .25 HRS @ 52 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4700/5,100 PSI, DIFF: 300/400 PSI. SLIDE DEPTHS: F/9,816'-T/9,829' 13', TF:135M, 06:00-06:15
KLONDIKE MILL H08 KL | 4 | 2022-02-04 06:15 | 2022-02-04 10:00 | 3.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.94 | 9829 | 9954 | 33.3 | CONTROL DRILL ON #1 AND #3 PUMPS, WHILE REPLACING MODULE GASKET ON #2 MP/#1 SUCTION MODULE. BUILD INTERMEDIATE CURVE- SLIDE (125’ IN 3.72 HRS @ 33.60 FPH) WOB: 15/20K, SPM: 105/105, GPM: 674, MMRPM: 104.47, SPP: 3,680/3,930 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/9,829'-T/9,954', 125', TF:30L, 06:15-09:58
KLONDIKE MILL H08 KL | 4 | 2022-02-04 10:00 | 2022-02-04 11:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3 | 9954 | 10052 | 65.3 | BUILD INTERMEDIATE CURVE-SLIDE (98' IN 1.48 HRS @ 66 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4700/5,100 PSI, DIFF: 300/400 PSI. SLIDE DEPTHS: F/9,969'-T/10,047' 78', TF:45L, 10:00-11:10 F/10,155'-T/10,175' 20', TF:60L, 11:53-12:17
KLONDIKE MILL H08 KL | 4 | 2022-02-04 11:30 | 2022-02-04 13:00 | 1.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.06 | 10052 | 10230 | 118.7 | BUILD INTERMEDIATE CURVE-ROT (178' IN 1.52 HRS @ 117 FPH) WOB: 8/10K, SPM:94/94/94, GPM: 900, RPM: 35, MMRPM:139.5, TTL RPM: 174.5, SPP: 4700/5,000 PSI, DIFF: 200/300 PSI.
KLONDIKE MILL H08 KL | 4 | 2022-02-04 13:00 | 2022-02-04 14:45 | 1.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.14 | 10230 | 10230 | 0 | PERFORM CLEAN UP CYCLE PUMPING 2-30 BBL HI-VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7-5/8" CASING. GPM-800, SPP 4,700 PSI, SHAKERS CLEAN
KLONDIKE MILL H08 KL | 4 | 2022-02-04 14:45 | 2022-02-04 17:30 | 2.75 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.25 | 10230 | 10230 | 0 | PERFORM FLOW CHECK (NO FLOW), PUMP SLUG, POOH F/10,230' T/2,727', PROPER FILL WITH TRIP TANK. FLOW CHECK AT SHOE. NOTE: PULLED 45K OVER @ 6,730'.
KLONDIKE MILL H08 KL | 4 | 2022-02-04 17:30 | 2022-02-04 18:00 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 3.27 | 10230 | 10230 | 0 | L/D AGITATOR, PULL ROTATING HEAD AND INSTALL TRIP NIPPLE
KLONDIKE MILL H08 KL | 4 | 2022-02-04 18:00 | 2022-02-04 19:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.31 | 10230 | 10230 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT.
KLONDIKE MILL H08 KL | 4 | 2022-02-04 19:00 | 2022-02-04 20:30 | 1.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.38 | 10230 | 10230 | 0 | CONTINUE TRIP OUT F/2,727' T/BHA, HOLE TAKING PROPER FILL ON TRIP TANK.
KLONDIKE MILL H08 KL | 4 | 2022-02-04 20:30 | 2022-02-04 22:15 | 1.75 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.45 | 10230 | 10230 | 0 | RACK BACK HWDP & 2 STDS-6.5'' DC, REMOVE MWD TOOL. DRAIN MOTOR AND BREAK OUT BIT. MOTOR: DRAINED WELL WITH MINIMAL SLACK. BIT:1-1-CT-S-X-1-NO-TD NOTE: FLOW CHECK PRIOR TO BHA ENTERING BOP. RESULT: WELL STATIC. NOTE: L/D DIRTY MOTOR AND P/U NEW MOTOR IN PREPERATION FOR THE NEXT WELL.
KLONDIKE MILL H08 KL | 4 | 2022-02-04 22:15 | 2022-02-04 22:45 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.47 | 10230 | 10230 | 0 | CLEAN RIG FLOOR AND REMOVE WEAR BUSHING
KLONDIKE MILL H08 KL | 4 | 2022-02-04 22:45 | 2022-02-05 00:30 | 1.75 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.54 | 10230 | 10230 | 0 | CHANGE OUT TOP VBR'S TO 7.625'' CASING RAMS, PICK UP JOINT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1,500 PSI (TEST GOOD)
KLONDIKE MILL H08 KL | 4 | 2022-02-05 00:30 | 2022-02-05 02:00 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.6 | 10230 | 10230 | 0 | HOLD PJSM; RIG UP FRANK'S CASING CREW
KLONDIKE MILL H08 KL | 4 | 2022-02-05 02:00 | 2022-02-05 06:00 | 4 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.77 | 10230 | 10230 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN 7.625'' 29.7#P-110-IC BTC INTERMEDIATE CASING F/89.70'-T/2,500'', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK. NOTE: COMPLETE 7.625" INTERMEDIATE CASING BREAKDOWN ON FOLLOWING REPORT.
KLONDIKE MILL H08 KL | 5 | 2022-02-05 06:00 | 2022-02-05 13:30 | 7.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.08 | 10230 | 10230 | 0 | RUN 7.625'' 29.7# P-110 IC BTC CSG F/2,500'-T/10,220'. FILL PIPE OF THE FLY, HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK. RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7.625" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 226 JTS OF 7.625" 29.7# P-110 IC BTC CSG, 1-14.8' PUP JOINT, THEN 1- FULL JT, FOLLOWED BY 1- 9.80' PUP JT, THEN 1- FULL JT FOR A TOTAL OF 231 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 48 LATCH ON BOW SPRING CENTRALIZERS @ 10,086' AND EVERY 4TH JT UP TO 2,155.5'. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/220K (W/O BLOCKS) SHOE- 10,220.0' TOP OF FLOAT COLLAR-10,130.6'. 11 FULL JOINTS LEFT OUT- 487.87', 1-15' PUP JT LEFT OUT-14.60' 2-10' PUP JT LEFT OUT-17.79'
KLONDIKE MILL H08 KL | 5 | 2022-02-05 13:30 | 2022-02-05 14:00 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 4.1 | 10230 | 10230 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD. RIG MANAGER PRESENT
KLONDIKE MILL H08 KL | 5 | 2022-02-05 14:00 | 2022-02-05 15:45 | 1.75 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 4.18 | 10230 | 10230 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE CONT. TO RIG DOWN CASING TOOLS, SPM: 105, 8.0 BPM, SPP: 750 PSI, NO LOSSES.
KLONDIKE MILL H08 KL | 5 | 2022-02-05 15:45 | 2022-02-05 19:45 | 4 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.34 | 10230 | 10230 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/5,500 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.0 PPG SPACER. 313 BBL 11.8 PPG 875 SK 2.01 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 77 BBL 16.2 PPG 300 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPANY REP WITNESS PLUG DROP, DISPLACE WITH 465 BBLS OF 9.7 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1520 PSI AT 4 BPM, DID NOT BUMP PLUG: PUMPED 4 BBLS OVER DISPLACEMENT, BLED BACK 2.5 BBLS FLOATS HELD. RIG DOWN CMT CREW. NOTE: CEMENT W/ FULL RETURNS WHILE PUMPING CEMENT. 20 BBLS INTERFACE TO SURFACE & 45 BBLS OF SPACER TO SURFACE. EST TOC: 125' NOTE: VERIFIED PLUG WAS NOT WEDGED IN CEMENT HEAD
KLONDIKE MILL H08 KL | 5 | 2022-02-05 19:45 | 2022-02-05 21:45 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.43 | 10230 | 10230 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, FLUSH THROUGH BOP'S AND FLOW LINE, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
KLONDIKE MILL H08 KL | 5 | 2022-02-05 21:45 | 2022-02-05 23:15 | 1.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 4.49 | 10230 | 10230 | 0 | REMOVE CASING RAMS; INSTALL VARIABLE RAMS.
KLONDIKE MILL H08 KL | 5 | 2022-02-05 23:15 | 2022-02-06 01:00 | 1.75 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 4.56 | 10230 | 10230 | 0 | SLIP AND CUT 110' OF DRILLING LINE. RIG MANAGER PRESENT.
KLONDIKE MILL H08 KL | 5 | 2022-02-06 01:00 | 2022-02-06 02:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.6 | 10230 | 10230 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT.
KLONDIKE MILL H08 KL | 5 | 2022-02-06 02:00 | 2022-02-06 03:45 | 1.75 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 4.68 | 10230 | 10230 | 0 | C/O SAVER SUB ON TOP DRIVE. RIG MANAGER PRESENT.
KLONDIKE MILL H08 KL | 5 | 2022-02-06 03:45 | 2022-02-06 06:00 | 2.25 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.77 | 10230 | 10230 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL, CLOSE CASING VALVE.
KLONDIKE MILL H08 KL | 5 | 2022-02-06 06:00 | 2022-02-06 06:00 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 4.77 | 10230 | 10230 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 2-6-22 @ 06:00
KLONDIKE MILL H08 KL | 6 | 2022-03-17 01:30 | 2022-03-17 01:30 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 4.77 | 10230 | 10230 |  | MILESTONE_RESUME WELL 1 ON 3/17/22 @ 01:30
KLONDIKE MILL H08 KL | 6 | 2022-03-17 01:30 | 2022-03-17 02:30 | 1 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 4.81 | 10230 | 10230 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK 20' FROM KLONDIKE RUSH H06 KL T/KLONDIKE MILL H08 KL, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN. NOTE: TEST BACK TO PUMPS FROM THE KILL LINE 250 PSI LOW, 6500 PSI HIGH WHILE WALKING RIG.
KLONDIKE MILL H08 KL | 6 | 2022-03-17 02:30 | 2022-03-17 04:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.88 | 10230 | 10230 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
KLONDIKE MILL H08 KL | 6 | 2022-03-17 04:00 | 2022-03-17 06:00 | 2 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.96 | 10230 | 10230 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE. NOTE: 4" STAND PIPE VALVE AND BOTH CHOKES WOULD NOT TEST, ATTEMPT TO WASH THROUGH BOTH AND RETEST WITHOUT SUCCESS.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 06:00 | 2022-03-17 11:00 | 5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.17 | 10230 | 10230 | 0 | TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. RIG DOWN TEST EQUIPMENT. VERIFY STACK AND CHOKE ALIGNMENT. NOTE: CHANGE OUT 4" STANDPIPE VALVE AND TEST T/6,500 PSI (GOOD TEST). CHANGE OUT GATE ON #2 CHOKE DUE TO THREADS BEING STRIPPED OUT. CHANGE OUT ACTUATER ON #1 CHOKE, TEST BOTH CHOKES T/250 PSI LOW / 10,000 PSI HIGH (GOOD TEST).
KLONDIKE MILL H08 KL | 7 | 2022-03-17 11:00 | 2022-03-17 12:00 | 1 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 5.21 | 10230 | 10230 | 0 | PULL TEST PLUG, TEST CASING T/3,500 PSI FOR 30 MIN., GOOD TEST. RIG DOWN TESTERS.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 12:00 | 2022-03-17 12:30 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 5.23 | 10230 | 10230 | 0 | INSTALL WEAR BUSHING AND TRIP NIPPLE.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 12:30 | 2022-03-17 15:00 | 2.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.33 | 10230 | 10230 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13685101 JETS 6X18 TFA: 1.49), 5.5", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.11' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,170 PSI; STALL TRQ-7382 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 28 STANDS DP, AGITATOR, BIT TO SVY-68'. BIT TO GAMMA-55'. NOTE: TEST MWD TOOL WITHOUT BIT ON MOTOR. GOOD TEST.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 15:00 | 2022-03-17 16:15 | 1.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.39 | 10230 | 10230 | 0 | TRIP IN THE HOLE F/BHA T/2,780', PROPER DISPLACEMENT TO TRIP TANK.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 16:15 | 2022-03-17 19:15 | 3 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.51 | 10230 | 10230 | 0 | FILLED PIPE AND FLOW TESTED DRILL STRING, PICKED UP AGITATOR ON STAND 28 AND FLOW TESTED. SPP BEFORE-1220 PSI SPP AFTER- 1460 PSI @ 262 GPM, TRIP IN THE HOLE WITH BHA #3 F/2,803' T/10,068', FILL PIPE EVERY 40 STANDS, PROPER DISPLACEMENT TO TRIP TANK, TAGGED FLOAT COLLAR @ 10,130'', VERIFY CHOKE VALVE ALIGNMENT, FILL PIPE AND BREAK CIRCULATION. NOTE: HOLE STARTED TO DRAG 50K @ 10,030', FILL PIPE AND WASH DOWN TO 10,068'.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 19:15 | 2022-03-17 20:00 | 0.75 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 5.54 | 10230 | 10230 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 20:00 | 2022-03-17 20:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.56 | 10230 | 10230 | 0 | SERVICE RIG AND TOP DRIVE UNIT
KLONDIKE MILL H08 KL | 7 | 2022-03-17 20:30 | 2022-03-17 21:30 | 1 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.6 | 10230 | 10230 | 0 | CUT AND SLIP 10 WRAPS 100' OF DRILL LINE NOTE: FILL GAS SEPERATOR PRIOR TO DRILL OUT. PERFORM BOP DRILL, RESPONSE TIME= 30 SECONDS.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 21:30 | 2022-03-17 22:45 | 1.25 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.66 | 10230 | 10240 | 8 | DRILL SHOE TRACK AND 10' NEW FORMATION F/10,230' T/10,240', WOB-5/10K, RPM-30, GPM-300, SPP-2250/2400 PSI, DIFF-50/100 PSI, TQ-4/6K.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 22:45 | 2022-03-17 23:15 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.68 | 10240 | 10240 | 0 | CIRCULATE BOTTOMS UP FOR F.T.T., GPM-300, SPP-2,225 PSI, RPM-30, MUD WT IN 9.0 PPG, MUD WT OUT 9.0 PPG.
KLONDIKE MILL H08 KL | 7 | 2022-03-17 23:15 | 2022-03-17 23:45 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.7 | 10240 | 10240 | 0 | PERFORM F.I.T. WITH 9.0 PPG OBM, 2137 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,220' / TVD-10,162'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE
KLONDIKE MILL H08 KL | 7 | 2022-03-17 23:45 | 2022-03-17 23:45 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.7 | 10240 | 10240 |  | MILESTONE_START CURVE SECTION 3-17-2022 @ 23:45 @ 10,240'
KLONDIKE MILL H08 KL | 7 | 2022-03-17 23:45 | 2022-03-18 05:00 | 5.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.92 | 10240 | 10700 | 87.6 | BUILD CURVE-SLIDE (460' IN 5.27 HR @ 87.34 FPH) WOB-30/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3200/3900 PSI, DIFF- 200/700 PSI, CHOKES- 100% /100%, FLARE-1', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP= 0 PSI, AVG SICP=0 PSI. SLIDE DEPTHS: F/10240'-T/10540', 300', TF:HS, 23:45-04:25, TQ:1R/1L, RPM:20 F/10665'-T/10730', 65', TF:HS, 04:44-05:20, TQ:1R/1L, RPM:20
KLONDIKE MILL H08 KL | 7 | 2022-03-18 05:00 | 2022-03-18 06:00 | 1 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.96 | 10700 | 10820 | 120 | BUILD CURVE-ROT (120' IN .98 HR @ 122.03 FPH) WOB-20/25K, SPM-76/76, RPM-30, TTLRPM-302, SPP-3200/3900 PSI, DIFF-500-700 PSI, CHOKES- 100% /100%, FLARE-1', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP= 0 PSI, AVG SICP=0 PSI.
KLONDIKE MILL H08 KL | 8 | 2022-03-18 06:00 | 2022-03-18 07:45 | 1.75 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.03 | 10820 | 10973 | 87.4 | BUILD CURVE-SLIDE (153' IN 1.8 HRS @ 85 FPH) WOB-30/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3300/3900 PSI, DIFF- 400/600 PSI, CHOKES- 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI. SLIDE DEPTHS: SLD F/10805 T/10823 18' TF-HS TQ- 1R 1L RPM-20 600-610 SLD F/10880 T/10916 36' TF-HS TQ- 2R 1L RPM-30 647-708 SLD F/10966 T/11010 44' TF-HS TQ- 2R 1L RPM-30 741-803 SLD F/11060 T/11130 70' TF-HS TQ- 2R 1L RPM-30 835-930
KLONDIKE MILL H08 KL | 8 | 2022-03-18 07:45 | 2022-03-18 09:30 | 1.75 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.1 | 10973 | 11130 | 89.7 | BUILD CURVE-ROT (157' IN 1.7 HR @ 92.35 FPH) WOB-20/25K, SPM-76/76, RPM-30, TTLRPM-302, SPP-3300/4000 PSI, DIFF-500-700 PSI, CHOKES- 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 06:47 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE @ 10,880', NEW TARGET: 10,630' TVD (0' VS) AT 87.1 DEG INC. WINDOW 5' ABOVE / 5' BELOW.
KLONDIKE MILL H08 KL | 8 | 2022-03-18 09:30 | 2022-03-18 09:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.1 | 11130 | 11130 |  | MILESTONE LAND/END CURVE ON 3/18/2022 @ 09:30, (MD: 11,130', TVD: 10,667')
KLONDIKE MILL H08 KL | 8 | 2022-03-18 09:30 | 2022-03-18 09:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.1 | 11130 | 11130 |  | MILESTONE START LATERAL SECTION ON 3/18/2022 @ 09:30, (MD: 11,130', TVD: 10,667')
KLONDIKE MILL H08 KL | 8 | 2022-03-18 09:30 | 2022-03-18 10:45 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.16 | 11130 | 11220 | 72 | DRILL LATERAL-SLIDE (90' IN 1.27 HRS @ 70.87 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3500/4100 PSI, DIFF- 400/600 PSI, CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 172 PSI, AVG SICP= 80 PSI. SLIDE DEPTHS: SLD F/11304 T/11324 20' TF-150L TQ- 3R 1L RPM 40 1041-1055 SLD F/11487 T/11507 20' TF-180 TQ- 3R 1L RPM-40 1148-1200 SLD F/11775 T/11790 15' TF-30L TQ- 3R 1L RPM-40 1323-1338 SLD F/12151 T/12171 20' TF-150L TQ-3R 1L RPM-40 1530-1544 SLD F/12343 T/12358 15' TF-150R TQ-3R 1L RPM-40 1637-1658
KLONDIKE MILL H08 KL | 8 | 2022-03-18 10:45 | 2022-03-18 17:15 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.43 | 11220 | 12422 | 184.9 | DRILL LATERAL-ROT (1202' IN 6.48 HR @ 185.49 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-70, TMRPM-342, TQ-6/9K, SPP-3500/4500 PSI, DIFF- 800/1000 PSI., CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 172 PSI, AVG SICP= 80 PSI NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 14:05 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE @ 11,873', TARGET: 10,630' TVD (0' VS) AT 87.1 DEG INC. NEW WINDOW 10' ABOVE / 0' BELOW. TARGET CHANGED RECEIVED VIA TEXT @ 15:52 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE @ 12,202', NEW TARGET: 10,626' TVD (0' VS) AT 86.8 DEG INC. WINDOW 5' ABOVE / 5' BELOW.
KLONDIKE MILL H08 KL | 8 | 2022-03-18 17:15 | 2022-03-18 17:45 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.45 | 12422 | 12422 | 0 | SERVICE RIG, TOP DRIVE, DRAWWORKS AND ST-80.
KLONDIKE MILL H08 KL | 8 | 2022-03-18 17:45 | 2022-03-18 18:15 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.47 | 12422 | 12528 | 212 | DRILL LATERAL-ROT (106' IN .47 HR @ 227 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-70, TMRPM-342, TQ-5/7K, SPP-3500 PSI, DIFF- 800/1000 PSI., CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI
KLONDIKE MILL H08 KL | 8 | 2022-03-18 18:15 | 2022-03-18 18:30 | 0.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.48 | 12528 | 12543 | 60 | DRILL LATERAL-SLIDE (15' IN .28 HRS @ 56.47 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3000/3200 PSI, DIFF- 400/600 PSI, CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/12528 T/12544 16' TF-150L TQ- 3R 2L RPM-40 1813-1830 NOTE: EXPERIENCED 900 PSI PRESSURE LOSS DURING LAST SLIDE.
KLONDIKE MILL H08 KL | 8 | 2022-03-18 18:30 | 2022-03-18 20:30 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.56 | 12543 | 12543 | 0 | TROUBLESHOOT PRESSURE LOSS, TEST SURFACE LINES, CLOSED 4" ON RIG FLOOR STANDPIPE TO TEST 2" BLEED OFF ON FLOOR (GOOD TEST), ISOLATE EACH MUD PUMP AND PRESSURE TEST EACH TO 1,000 PSI (GOOD TEST), ISOLATE EACH PUMP AND PUMP DOWN DRILL STRING AT 100 SPM EACH PUMP #1 PUMP = 1,635 PSI, #2 PUMP = 1,638 PSI, #3 PUMP = 1,560 PSI, CHECK ORBIT VALVE AT TRIP TANK, KILL LINE AND FILL UP LINE. ALL SURFACE EQUIPMENT TESTED GOOD. DECISSION WAS MADE TO ATTEMPT TO DRILL TO TEST MUD MOTOR.
KLONDIKE MILL H08 KL | 8 | 2022-03-18 20:30 | 2022-03-18 21:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.58 | 12543 | 12611 | 136 | DRILL LATERAL-ROT (68' IN .57 HR @ 119.29 FPH) STAGING UP ROP FROM 150 FPH TO 200 FPH, NO ISSUES WITH MUD MOTOR
KLONDIKE MILL H08 KL | 8 | 2022-03-18 21:00 | 2022-03-18 21:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.6 | 12611 | 12611 | 0 | CIRCULATE BOTTOMS UP TO FREE ANNULUS OF ANY GAS ACCUMULATED DURING SHUT DOWNS WHILE TROOUBLE SHOOTING PRESSURE LOSS. GPM 200, SPP 800, RPM 50, MAX GAS 3552 UNITS, MAX CSG PRESS 238, FLARE 30', CHOKE POSITION 30% TO 70%, NO MUD CUT
KLONDIKE MILL H08 KL | 8 | 2022-03-18 21:30 | 2022-03-18 23:15 | 1.75 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 6.68 | 12611 | 12611 | 0 | STRIP OUT OF HOLE WET LOOKING FOR WASHOUT AT 70 FPM, F/12,611' T/11,721' PUMPING 1.9 BBLS/STD 9.0 PPG OBM CALCULATED FILL WHILE INSPECTING DP FOR WASHOUT. MAX CSG PRESS 207 PSI, AVG CSG PRESS 90 PSI. AT 11,721' CSG PRESS DROPPING ONCE TOP DRIVE BACKED OUT OF STD AND DRILL STRING U-TUBING, INDICATING COMUNICATION BETWEEN DRILL STRING AND ANNULUS NOTE: HAD TO USE TONGS TO BREAK FIRST STANDS OUT OF THE HOLE
KLONDIKE MILL H08 KL | 8 | 2022-03-18 23:15 | 2022-03-19 04:00 | 4.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.88 | 12611 | 12611 | 0 | CIRCULATE AND CONDITION ONE TUBING VOLUME PLUS 37 BBLS TO CLEAR DRILL STRING AT 200 GPM, SPP 970, CHOKE AT 30%. MAX CSG PRESS 1219, MAX GAS 1864. CONT CIRCULATE GAS OUT OF HOLE. MONITOR SICP. MAX SICP 1053 PSI, SIDP PRESS 938 PSI . PUMP 55 BBLS 17.5 PPG KILL MUD DOWN DRILL STRING, CHASE WITH 100 STKS 9.0 PPG OBM. SPP REDUCED TO 0 PSI, CSG PRESS 1176 PSI.
KLONDIKE MILL H08 KL | 8 | 2022-03-19 04:00 | 2022-03-19 06:00 | 2 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 6.96 | 12611 | 12611 | 0 | STRIP OUT THE HOLE F/11,721’ T/10,558’ PUMPING 17.5 PPG MUD CALCULATED FILL (.6 BBLS/STND) DOWN THE ANNULUS. INITIAL CASING PRESSURE= 1024 PSI AND FINAL CASING PRESSURE= 727 PSI. NOTE: CASING PRESSURE DROPPING DUE TO KILL MUD HOLE FILL NOTE: STRING STARTED COMING WET WHILE PULLING @ 11,153', PUMP 17.5 PPG MUD CALCULATED FILL FOR WET PIPE (1.9BBLS/STND) DOWN THE ANNULUS.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 06:00 | 2022-03-19 06:30 | 0.5 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 6.98 | 12611 | 12611 | 0 | CONTINUE STRIPPING OUT THE HOLE F/10,558’ T/10,298’ @ 60 FPM WHILE INSPECTING PIPE FOR WASH OUT, PUMPING 17.5 PPG MUD CALCULATED WET FILL (1.9 BBLS/STND) DOWN THE ANNULUS. INITIAL CASING PRESSURE= 653 PSI AND FINAL CASING PRESSURE= 147 PSI. NOTE: DRILL STRING U-TUBING, INDICATING COMUNICATION BETWEEN DRILL STRING AND ANNULUS.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 06:30 | 2022-03-19 07:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7 | 12611 | 12611 | 0 | PUMP 15 BBLS 17.5 PPG KILL MUD DOWN DRILL STRING, CHASE WITH 12.5 BBLS 9.0 PPG OBM. CSG PRESSURE= 425 PSI.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 07:00 | 2022-03-19 10:30 | 3.5 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.15 | 12611 | 12611 | 0 | CONTINUE STRIPPING OUT THE HOLE F/10,298’ T/8,463’ @ 60 FPM WHILE INSPECTING PIPE FOR WASH OUT, PUMPING 17.5 PPG MUD CALCULATED WET FILL (1.9 BBLS/STND) DOWN THE ANNULUS. INITIAL CASING PRESSURE= 400 PSI, MAX CASING PRESSURE= 412 PSI AND FINAL CASING PRESSURE= 148 PSI. NOTE: 55 BBLS 17.5 PPG KILL MUD PUMPED DOWN ANNULUS AND 15 BBLS 17.5 PPG KILL MUD PUMPED DOWN DRILL STRING, TTL 125 BBLS PUMPED DURING STRIPPING OPERATIONS. NOTE: OBSERVED AND REPLACED 2 BENT JOINTS.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 10:30 | 2022-03-19 11:15 | 0.75 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.18 | 12611 | 12611 | 0 | OBSERVED WASH OUT ON STD 44, REPLACE WASHED OUT JOINT, CLEAN RIG FLOOR.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 11:15 | 2022-03-19 13:45 | 2.5 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.28 | 12611 | 12611 | 0 | STRIP IN THE HOLE F/8,463' T/12,611' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND TO TRIP TANK; INITIAL CSG PSI= 560 PSI, MAX CSG PRESSURE= 1137 PSI, FINAL CSG PSI= 776 PSI.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 13:45 | 2022-03-19 15:00 | 1.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.33 | 12611 | 12611 | 0 | CIRCULATE OUT GAS AND RECIPROCATE PIPE, GPM-400, , RPM-30, TQ-4/6K, SPP-3500/5450 PSI, CHOKES- 0% / 23-40%, FLARE-60-70', 9.3 PPG T/7.7 PPG MUD CUT, MAX CASING PRESSURE= 1848 PSI, FINAL CASING PRESSURE= 0 PSI, MAX GAS=4382u.
KLONDIKE MILL H08 KL | 9 | 2022-03-19 15:00 | 2022-03-19 19:30 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.52 | 12611 | 13344 | 162.9 | DRILL LATERAL-ROT (733' IN 4.55 HR @ 161 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-70, TMRPM-342, TQ-8/12K, SPP-3800 PSI, DIFF- 800/1000 PSI., CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. MUD WT 9.2 PPG
KLONDIKE MILL H08 KL | 9 | 2022-03-19 19:30 | 2022-03-19 21:30 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.6 | 13344 | 13461 | 58.5 | DRILL LATERAL-SLIDE (117' IN 2.05 HRS @ 57 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3800 PSI, DIFF- 400/600 PSI, CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/12615 T/12640 25' TF-150L RPM-50 TQ-3R 3L 1458-1520 SLD F/12670 T/12685 15' TF-90L RPM-50 TQ-3R 3L 1530-1545 SLD F/12718 T/12733 15' TF-90L RPM-50 TQ-3R 3L 1610-1623 SLD/F12763 T/12778 15' TF-90L RPM-50 TQ-3R 3L 1633-1652 SLD F/12812 T/12827 15' TF-90L RPM-50 TQ-3R 3L 1712-1727 SLD F/12902 T/12922 20' TF-160L 1805-1825 RPM-70 TQ-4R 3L SLD F/13190 T/13202 12' TF-160R 1951-2010 RPM-70 TQ-4R 3L
KLONDIKE MILL H08 KL | 9 | 2022-03-19 21:30 | 2022-03-19 22:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 7.63 | 13461 | 13461 | 0 | SERVICE TOP DRIVE, DRAWWORKS, ST-80, AND INSPECT TD GRABBER BOX
KLONDIKE MILL H08 KL | 9 | 2022-03-19 22:00 | 2022-03-20 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.71 | 13461 | 13743 | 141 | DRILL LATERAL-ROT (282' IN 1.9 HR @ 148.42 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-70, TMRPM-342, TQ-8/12K, SPP-3800 PSI, DIFF- 800/1000 PSI., CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. MUD WT 9.2 PPG NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 00:02 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE @ 13,747', TARGET: 10,626' TVD (0' VS) AT 86.8 DEG INC. NEW WINDOW 10' ABOVE / 0' BELOW.
KLONDIKE MILL H08 KL | 9 | 2022-03-20 | 2022-03-20 00:15 | 0.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.72 | 13743 | 13755 | 48 | DRILL LATERAL-SLIDE (12' IN .35 HRS @ 34.28 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3800 PSI, DIFF- 400/900 PSI, CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/13565 T/13577 12' TF-110R RPM-70 TQ-5R 3L 2246-2307 NOTE: SHAKER LIT ON FIRE
KLONDIKE MILL H08 KL | 9 | 2022-03-20 00:15 | 2022-03-20 01:15 | 1 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 7.76 | 13755 | 13755 | 0 | WORK WITH RIG CREW EXTINGUISHING FIRE AT SHAKERS. PULL DRILL STRING OFF BOTTOM, SHUT DOWN PUMPS, SPACE OUT AND SHUT WELL IN. ONCE FIRE WAS PUT OUT, LOCK OUT AND UNPLUG SHAKERS. PATTERSON AND MAGNOLIA HSE IN ROUTE TO LOCATION. DECISION WAS MADE TO TRIP OUT OF THE HOLE TO CASING SHOE @ 10,220'. MAX SICP: 219 PSI
KLONDIKE MILL H08 KL | 9 | 2022-03-20 01:15 | 2022-03-20 04:15 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.89 | 13755 | 13755 | 0 | STRIP OUT THE HOLE F/13,755’ T/10,194’ WET, PUMPING 1.9 BBLS/STD 17.5 PPG OBM KILL MUD CALCULATED FILL DOWN THE ANNULUS . MAX CASING PRESSURE= 258 PSI, AVG CASING PRESSURE: 0 PSI NOTE: 70 BBLS 17.5 PPG KILL MUD PUMPED DOWN ANNULUS DURING STRIPPING OPERATIONS.
KLONDIKE MILL H08 KL | 9 | 2022-03-20 04:15 | 2022-03-20 06:00 | 1.75 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 7.96 | 13755 | 13755 | 0 | WORK WITH NOV FIELD TECH ON SHAKER INSPECTION. PATTERSON MANAGEMENT AND HSE PERFORMING INVESTIGATION ON SHAKER FIRE.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 06:00 | 2022-03-20 10:00 | 4 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 8.13 | 13755 | 13755 | 0 | WORK WITH N.O.V. FIELD TECH AND PATTERSON RIG CREW ON REPLACING ALL THE WIRING ON #3 SHAKER, REPLACED DAMAGED WIRING ON #1 AND #2 SHAKERS, REPLACE SHAKER SCREENS ON ALL 3 SHAKERS. TEST RUN SHAKERS FOR 30 MINUTES BEFORE RUNNING MUD ACROSS THEM. TEST RUN SAME WITH MUD FOR 30 MINUTES, SHAKERS RAN CORRECTLY WITH MUD. PATTERSON HSE AND RIG SUPERINTENDENT APPROVED SAME. MONITOR SICP, SICP= 0 PSI. NOTE: PULLED AND INSPECTED CHECK VALVE IN GAS SEPERATOR VENT LINE. CHECK VALVE IN GOOD CONDITION.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 10:00 | 2022-03-20 11:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.17 | 13755 | 13755 | 0 | SERVICE RIG, TOP DRIVE, DRAW WORKS AND ST-80; PERFORM WEEKLY ON CATWALK. MONITOR SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 11:00 | 2022-03-20 11:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.19 | 13755 | 13755 | 0 | STRIP IN THE HOLE F/10,194’ T/10,618’ @ 50-100 FPM WITH NO RETURNS. NOTE: DECISION WAS MADE TO ATTEMPT TO ESTABLISH CIRCULATION.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 11:30 | 2022-03-20 12:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.21 | 13755 | 13755 | 0 | SLOWLY STAGE UP PUMP RATE F/26 GPM T/79 GPM AND ATTEMPT TO ESTABLISH CIRCULATION DOWN THE FLOW LINE WITH NO SUCCESS, LOST 30 BBLS TO THE FORMATION.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 12:00 | 2022-03-20 13:15 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.26 | 13755 | 13755 | 0 | TRIP IN THE HOLE F/10,618' T/13,755' DOWN THE FLOW LINE TO THE TRIP TANK WITH NO RETURNS.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 13:15 | 2022-03-20 14:45 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.32 | 13755 | 13755 | 0 | FILL PIPE AND ESTABLISHED CIRCULATION, LOST TOTAL OF 32 BBLS OF 9.2 PPG OBM DOWN HOLE, CIRCULATE OUT KILL MUD DOWN THE FLOW LINE WHILE SLOWLY STAGING UP PUMP RATE F/79 GPM T/400 GPM UNTIL KILL MUD WAS CIRCULATED OUT, CLOSED ORBIT VALVE AND CIRCULATE THROUGH CHOKES, WASH/REAM F/13,642’ T/13,755’, GPM-400, , RPM-30, TQ-4/6K, SPP-3850 PSI, CHOKES- 0% / 40-100%, FLARE-20-30', NO MUD CUT, MAX CASING PRESSURE= 228 PSI, FINAL CASING PRESSURE= 0 PSI, MAX GAS=4540u, LOST 32 BBLS TO THE FORMATION. NOTE: DIVERTED 80 BBLS OF 10.1 PPG T/16.6 PPG KILL MUD TO OPEN TOP.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 14:45 | 2022-03-20 22:15 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.64 | 13755 | 15109 | 180.5 | DRILL LATERAL-ROT (1,354' IN 7.42 HRS @ 1462 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-70, TMRPM-342, TQ-8/12K, SPP-3700 PSI, DIFF 800/1000 PSI., CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 241 PSI, AVG SICP= 0 PSI. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. MUD WT 9.2 PPG NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 15:52 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE @ 13,930', TARGET: 10,626' TVD (0' VS) AT 86.8 DEG INC. NEW WINDOW: 0' ABOVE / 10' BELOW. WINDOW CHANGE RECEIVED VIA TEXT @ 16:41 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE @ 14,080', TARGET: 10,626' TVD (0' VS) AT 86.8 DEG INC. NEW WINDOW: 5' ABOVE / 5' BELOW. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 18:50 HRS, DEPTH WHEN RECEIVED 14,378'. NEW TARGET LINE 10,685' TVD (0' VS) @ 87.5 DEG INC. 5' ABOVE/ 5' BELOW. NOTE: LOST RETURNS @ 15,217', DECREASE PUMP RATE T/100 GPM, IN EFFORT TO MINIMIZE LOSSES. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 02:25 HRS, DEPTH WHEN RECEIVED 15,217'. NEW TARGET LINE 10,678' TVD (0' VS) @ 87.5 DEG INC. 5' ABOVE/ 5' BELOW.
KLONDIKE MILL H08 KL | 10 | 2022-03-20 22:15 | 2022-03-21 01:45 | 3.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.78 | 15109 | 15217 | 30.9 | DRILL LATERAL-SLIDE (108' IN 3.53 HRS @ 30.57 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3700 PSI, DIFF- 400/600 PSI, CHOKES- 100% /100%, FLARE-10-15', NO MUD CUT, MAX CASING PRESSURE= 241 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/14319 T/14334 15' TF-150R 1818-1837 RPM-70 TQ-5R 4L SLD F/14411 T/14426 15' TF-150L 1904-1946 RPM-80 TQ-6R 4L SLD F/14505 T/14517 12' TF-140L 2013-2033 RPM-80 TQ-6R 4L SLD F/14693 T/14713 20' TF-HS 2129-2202 RPM-80 TQ-6R 4L SLD F/14787 T/14795 8' TF-30L 2227-2242 RPM-80 TQ-6R 4L SLD F/14882 T/14890 8' TF-60L 2313-2332 RPM-80 TQ-6R 4L SLD F/15165 T/15185 20' TF-170R 103-136 RPM-80 TQ-8R 5L
KLONDIKE MILL H08 KL | 10 | 2022-03-21 01:45 | 2022-03-21 05:30 | 3.75 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.94 | 15217 | 15217 | 0 | @ 15,217' PREP MUD TANKS FOR "MUD CAP" DRILLING OPS: TRANSFER MUD FROM TANK 8 AND FILL WITH FRESH WATER. BEGIN TO DISPLACE DRILL STRING W/FW WHILE TRANSFERRING OBM FROM TANKS 5, 6 & 7. FILL TANK 5&6 WITH 17.5 PPG KILL OBM, GPM: 150, SPP: 1,150, RPM: 30, TQ: 7-8K NOTE: EST TTL OBM LOSS PRIOR TO INDUCING MUDCAP=50 BBLS.............. WEIGHT KILL MUD UP TO 17.5 PPG, BULL HEAD 35 BBLS 17.5 PPG OBM DOWN BACKSIDE VIA KILL LINE, STAGE PUMP RATE UP F/26 GPM T/157 GPM, INITAL KILL SPP= 214 PSI AND FINAL KILL SPP=308 PSI, INITIAL CASING PRESSURE= 184 PSI, FINAL CASING PRESSURE= 0 PSI, MAX KILL SPP: 425, MAX SICP: 184, SLOWLY STAGED UP PUMPS T/400 GPM DOWN DRILL PIPE WHILE BULLHEADING KILL MUD DOWN ANNULUS.
KLONDIKE MILL H08 KL | 10 | 2022-03-21 05:30 | 2022-03-21 06:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.96 | 15217 | 15277 | 120 | DRILLING W/DRILL WATER UNDER MUDCAP. ROTATE (60' IN .5 HRS @ 120 FPH) WOB-15/22K, SPM-72/72, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-12K, SPP-3,000/4000 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%, FLARE-0, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY 300' OR AS NEEDED. (SWEEP CONSISTING OF 3.5 PPB PHPA AND DRILL WATER.) NOTE: ADDING 4.5 BPH OF DIESEL AND 1 BUCKET OF PHPA PER HR INTO DRILL WATER.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 06:00 | 2022-03-21 10:45 | 4.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.16 | 15277 | 15880 | 126.9 | DRILL LATERAL-ROT (603' IN 4.65 HRS @ 129.68 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-12/14K, SPP-4400/5400 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=548 PSI, AVG CASING PRESSURE= 400 PSI, MAX SICP= 80 PSI, AVG SICP= 80 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY +/- 300' OR AS NEEDED. (SWEEP CONSISTING OF 2 PPB PHPA AND DRILL WATER.) NOTE: CASING PRESSURE INCREASED T/548 PSI @ 15,439' AND FELL T/80 PSI WITH PUMPS OFF, BULL HEAD 50 BBLS 17.5 PPG OBM DOWN BACKSIDE VIA KILL LINE WHILE DRILLING AHEAD, STAGE PUMP RATE UP F/26 GPM T/79 GPM, INITAL KILL LINE SPP= 386 PSI, INITAL CSG PRESSURE= 318 PSI, MAX KILL LINE SPP=801 PSI, MAX CSG PRESSURE= 671 PSI, FINAL KILL SPP=537 PSI, FINAL CASING PRESSURE= 410 PSI AND FELL T/0 PSI WITH PUMP OFF BACKSIDE. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 09:20 HRS, DEPTH WHEN RECEIVED 15,705'. NEW TARGET LINE 10,683' TVD (0' VS) @ 87.5 DEG INC. 5' ABOVE/ 5' BELOW.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 10:45 | 2022-03-21 11:15 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.18 | 15880 | 15910 | 60 | DRILL LATERAL-SLIDE (30' IN .6 HRS @ 50 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4400/4800 PSI, DIFF-200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=548 PSI, AVG CASING PRESSURE= 400 PSI, MAX SICP= 80 PSI, AVG SICP= 80 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/15546 T/15561 15' RF-140R RPM-60 TQ-6R 4L 805-821 SLD F/15734 T/15749 15' TF-120R RPM-60 TQ-6R 4L 942-1002
KLONDIKE MILL H08 KL | 11 | 2022-03-21 11:15 | 2022-03-21 11:45 | 0.5 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 9.2 | 15910 | 15910 | 0 | CASING PRESSURE INCREASED T/605 PSI @ 15,910' AND FELL T/0 PSI WITH PUMPS OFF, BULL HEAD 77 BBLS 17.5 PPG OBM DOWN BACKSIDE VIA KILL LINE WHILE CIRCULATING @ 150 GPM AND WORKING PIPE, RPM-50, SPP-3000 PSI, TQ-8/10K, STAGE PUMP RATE UP F/26 GPM T/183 GPM, INITAL KILL LINE SPP= 634 PSI, INITAL CSG PRESSURE= 596 PSI, MAX KILL LINE SPP=1035 PSI, MAX CSG PRESSURE= 741 PSI, FINAL KILL SPP=542 PSI, FINAL CASING PRESSURE= 193 PSI AND FELL T/0 PSI WITH PUMP OFF BACKSIDE.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 11:45 | 2022-03-21 12:00 | 0.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.21 | 15910 | 15940 | 120 | DRILL LATERAL-ROT (30' IN .25 HRS @ 120 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-12/14K, SPP-4700/5700 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 12:00 | 2022-03-21 12:45 | 0.75 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 9.24 | 15940 | 15940 | 0 | OBSERVED WASH OUT BETWEEN TOOL JOINTS @ 15,940’, REPLACED 2 JOINTS.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 12:45 | 2022-03-21 13:30 | 0.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.27 | 15940 | 16044 | 138.7 | DRILL LATERAL-ROT (104' IN .75 HRS @ 138.67 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-12/14K, SPP-4700/5700 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 13:30 | 2022-03-21 13:45 | 0.25 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 9.28 | 16044 | 16044 | 0 | OBSERVED A BENT JOINT @ 16,044’, REPLACED 1 JOINT.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 13:45 | 2022-03-21 16:15 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.39 | 16044 | 16364 | 128 | DRILL LATERAL-ROT (320' IN 2,42 HRS @ 132.23 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-13/15K, SPP-4700/5700 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY +/- 300' OR AS NEEDED. (SWEEP CONSISTING OF 2 PPB PHPA AND DRILL WATER.) NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 16:04 HRS, DEPTH WHEN RECEIVED 16,302'. NEW TARGET LINE 10,633' TVD (0' VS) @ 87.5 DEG INC. 5' ABOVE/ 5' BELOW.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 16:15 | 2022-03-21 16:45 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.41 | 16364 | 16384 | 40 | DRILL LATERAL-SLIDE (20' IN .58 HRS @ 34.48 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4700/5300 PSI, DIFF-400/600 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/16295 T/16315 20' TF-90L RPM-80 TQ-10R 6L 1552-1627
KLONDIKE MILL H08 KL | 11 | 2022-03-21 16:45 | 2022-03-21 17:15 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.43 | 16384 | 16384 | 0 | SERVICE RIG AND TOP DRIVE UNIT.
KLONDIKE MILL H08 KL | 11 | 2022-03-21 17:15 | 2022-03-22 01:45 | 8.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.78 | 16384 | 17577 | 140.4 | DRILL LATERAL-ROT (1,193' IN 8.38 HRS @ 142.36 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-13/15K, SPP-4400/5500 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY +/- 300' OR AS NEEDED. (SWEEP CONSISTING OF 2 PPB PHPA AND DRILL WATER.) NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 04:14 HRS, DEPTH WHEN RECEIVED 17,497'. NEW TARGET LINE 10,633' TVD (0' VS) @ 87.0 DEG INC. 10' ABOVE/ 0' BELOW.
KLONDIKE MILL H08 KL | 11 | 2022-03-22 01:45 | 2022-03-22 06:00 | 4.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.96 | 17577 | 17701 | 29.2 | DRILL LATERAL-SLIDE (124' IN 4.37 HRS @ 28.37 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4400/5000 PSI, DIFF-400/600 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/16487 T/16499 12' TF-140L 1812-1836 RPM-80 TQ-9R 7L SLD F/16580 T/16605 25' TF-120L 1906-1946 RPM-80 TQ-9R 7L SLD F/16675 T/16695 20' TF-160L 2015-2054 RPM-80 TQ-10R 9L SLD F/16959 T/16979 20' TF-160R 2231-2322 RPM-80 TQ-13R 12L SLD F/17052 T/17059 7' TF-60R 0003-0021 RPM-80 TQ-13R 12L SLD F/17146 T/17161 15' TF-10R 0058-138 RPM-80 TQ-13R 12L SLD F/17334 T/17349 15' TF-10R 255-321 RPM-80 TQ-13R 12L SLD F/17524 T/17534 10' TF-40R 0430-0454 RPM-80 TQ-13R 12L
KLONDIKE MILL H08 KL | 12 | 2022-03-22 06:00 | 2022-03-22 07:15 | 1.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.01 | 17701 | 17792 | 72.8 | DRILL LATERAL-ROT (91' IN 1.35 HRS @ 67.41 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-13/15K, SPP-4500/5500 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY +/- 300' OR AS NEEDED. (SWEEP CONSISTING OF 2 PPB PHPA AND DRILL WATER.)
KLONDIKE MILL H08 KL | 12 | 2022-03-22 07:15 | 2022-03-22 08:30 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.06 | 17792 | 17817 | 20 | DRILL LATERAL-SLIDE (25' IN 1.15 HRS @ 21.74 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4400/4500 PSI, DIFF-50/100 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/17713 T/17728 15' TF-180 RPM-80 TQ- 16R 15L 627-708 SLD F/17807 T/17817 10' TF-180 RPM-80 TQ- 16R 15L 802-830 NOTE: PUMP PRESSURE DECREASED F/4450 PSI T/3900 PSI @ 17,817', SHUT DOWN PUMPS PULLED UP T/17,794' TO PRESSURE TEST SURFACE EQUIPMENT.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 08:30 | 2022-03-22 10:15 | 1.75 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 10.14 | 17817 | 17817 | 0 | PUT HYDRAULIC IBOP IN TEST MODE, ATTEMPT TO PRESSURE TEST F/ ALL 3 MUD PUMPS T/ 4" VALVE ON RIG FLOOR T/1000 PSI, PRESSURE BLED OFF F/1000 PSI T/332 PSI, UNHOOKED 2" BLEED LINE, PRESSURE UP T/1000 PSI AND OBSERVED 2" BLEED OFF VALVE LEAKING, INSERTED PLUG IN 2" BLEED OFF VALVE, PRESSURE TEST F/ #2 PUMP T/ 4" VALVE ON RIG FLOOR T/1000 PSI FOR 5 MIN, PRESSURE BLED OFF T/989 PSI AND STABILIZED; ATTEMPT TO PRESSURE TEST F/ #3 PUMP T/ 4" VALVE ON RIG FLOOR T/1000 PSI, PRESSURE BLED OFF F/1000 PSI T/895 PSI, IN 5 MIN AND DID NOT STABILIZE, PUMP THROUGH 2" ON #3 PUMP AND INSPECT FOR LEAKS, NO VISIBLE LEAKS; PRESSURE TEST F/ #1 PUMP T/ 4" VALVE ON RIG FLOOR T/1100 PSI FOR 5 MIN, PRESSURE BLED OFF T/1064 PSI AND STABILIZED; CHANGE OUT 2" BLEED OFF VALVE; PRESSURE TEST 2" BLEED OFF VALVE T/1100 PSI FOR 5 MIN, PRESSURE BLED OFF T/1060 PSI AND STABILIZED. NOTE: ROTATING @ 10 RPM AND BREAKING OVER TORQUE EVERY 10 MIN. WHILE PRESSURE TESTING, TORQUE BREAKING OVER @ 13K.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 10:15 | 2022-03-22 18:00 | 7.75 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 10.46 | 17817 | 17817 | 0 | ATTEMPTED TO CIRCULATE @ 20 SPM AND PUMP PRESSURE INCREASED T/5500 PSI, BLED OFF TRAPPED PRESSURE; OBSERVED HYDRAULIC IBOP WAS NOT OPENING COMPLETELY; PRESSURE UP T/500 PSI AND ATTEMPT TO OPEN IBOP, IBOP DID NOT OPEN COMPLETELY, PRESSURE UP T/800 PSI ATTEMPT TO OPEN IBOP, IBOP DID NOT OPEN COMPLETELY, PRESSURE UP T/3000 PSI IN 500 PSI INCREMENTS WHILE ATTEMPTING TO OPEN IBOP, IBOP DID NOT OPEN COMPLETELY, ATTEMPT TO OPEN IBOP WHILE TAPPING ON IBOP SLEEVE, IBOP DID NOT OPEN COMPLETELY; PRESSURE UP T/400 PSI AND ATTEMPT TO OPEN IBOP WHILE TAPPING ON IBOP SLEEVE, IBOP DID NOT OPEN COMPLETELY, PRESSURE UP F/400 PSI T/2554 PSI 200 PSI INCREMENTS WHILE TAPPING ON IBOP SLEEVE, IBOP OPENED WITH 2554 PSI. BLED PRESSURE AND MONITOR SPP, NO PRESSURE BUILD UP OBSERVED. NOTE: ROTATING @ 10 RPM AND BREAKING OVER TORQUE EVERY 10 MIN., TORQUE BREAKING OVER @ 13K.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 18:00 | 2022-03-22 18:15 | 0.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.47 | 17817 | 17817 | 0 | LEFT IBOP IN MANUAL OPEN, SLOWLY STAGE UP PUMP RATE F/52 GPM T/400 GPM AND ESTABLISHED CIRCULATION WHILE RECIPROCATING PIPE, GPM-400, RPM-50, TQ-10/13K, SPP-3520 PSI; SHUT DOWN PUMPS AND MONITORED SPP FOR 5 MIN., PRESSURE STABLIZED @ 1576 PSI; BLED PRESSURE AND MONITOR SPP, NO PRESSURE BUILD UP OBSERVED. NOTE: ROTATING @ 10 RPM AND BREAKING OVER TORQUE EVERY 10 MIN., TORQUE BREAKING OVER @ 12K.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 18:15 | 2022-03-22 19:15 | 1 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 10.51 | 17817 | 17817 | 0 | BREAK OUT AND MOUSE HOLE KELLY STAND, FUNCTION IBOP OPEN AND CLOSE, IBOP OPENED AND CLOSED CORRECTLY; PATTERSON TECH CHECK HYDRAULIC PRESSURES AND FUNCTION TESTED IBOP. NOTE: ROTATING @ 10 RPM AND BREAKING OVER TORQUE EVERY 10 MIN., TORQUE BREAKING OVER @ 12K.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 19:15 | 2022-03-22 19:45 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.53 | 17817 | 17869 | 104 | DRILL LATERAL-ROT (52' IN .53 HRS @ 98.11 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-13/15K, SPP-4500/5500 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 19:45 | 2022-03-22 21:00 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.58 | 17869 | 17889 | 16 | DRILL LATERAL-SLIDE (20' IN 1.22 HRS @ 16.39 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-272, SPP-4400/4500 PSI, DIFF-50/100 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI, AVG SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/17817 T/17837 20' TF-160 RPM-80 TQ- 14R 11L NOTE: STARTED TO EXPERIENCE MULTIPLE PRESSURE SPIKES WHILE DRILLING, ATTEMPT TO FEATHER WEIGHT BACK TO BOTTOM WITHOUT SUCCESS. OFF BOTTOM PUMP PRESSURE INCREASED F/4500 PSI T/4800 PSI.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 21:00 | 2022-03-22 21:45 | 0.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.61 | 17889 | 17889 | 0 | PERFORMED CLEAN UP CYCLE WITH WELL ON MUD CAP. PUMPED PHPA SWEEPS CIRCULATE 2 BOTTOMS UP TO LOSS ZONE, SPM-76/76, GPM-400, MRPM-272, RPM-70, CHOKES CLOSED. MAX CSG PSI WHILE CIRC-0 PSI. TQ=11/15K, SPP-4,800 PSI
KLONDIKE MILL H08 KL | 12 | 2022-03-22 21:45 | 2022-03-22 23:45 | 2 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 10.7 | 17889 | 17889 | 0 | BACK REAM OUT THE HOLE @ 20 FPM, F/17,889' T/16,840’, SPM-76/76, GPM-400, RPM-50, TRQ-10/12K, SPP-4,800 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI NOTE: BUILD 12.7 PPG OBM FOR FILLING BACKSIDE WHILE BACKREAMING OUT OF THE HOLE.
KLONDIKE MILL H08 KL | 12 | 2022-03-22 23:45 | 2022-03-23 06:00 | 6.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.96 | 17889 | 17889 | 0 | STRIP OUT OF THE HOLE WET F/16,840'- T/6,800', MAX OVER PULL-320K, FILLING BACKSIDE WITH 12.7 PPG OBM CALCULATED FILL @ 1.9 BBLS/STND. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI NOTE: LAY DOWN BENT JT OF DP @ 8247' AND REPLACE SAME PUMPED 208 BBLS OF 12.7 PPG OBM CALCULATED FILL (1.9 BBLS/STD) DOWN BACKSIDE NOTE: USED TONGS ON 6 DIFFERENT TIGHT CONNECTIONS
KLONDIKE MILL H08 KL | 13 | 2022-03-23 06:00 | 2022-03-23 09:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.08 | 17889 | 17889 | 0 | STRIP OUT OF THE HOLE WET F/6,800'- T/2,964', FILLING BACKSIDE WITH 12.7 PPG OBM CALCULATED FILL @ 1.9 BBLS/STND. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI. PUMPED 78 BBLS OF 12.7 PPG OBM CALCULATED FILL (1.9 BBLS/STD) DOWN BACKSIDE NOTE: USED TONGS ON 13 DIFFERENT TIGHT CONNECTIONS
KLONDIKE MILL H08 KL | 13 | 2022-03-23 09:00 | 2022-03-23 09:45 | 0.75 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 11.11 | 17889 | 17889 | 0 | BULL HEAD 20 BBLS 17.5 PPG OBM DOWN BACKSIDE VIA KILL LINE, STAGING PUMP RATE UP F/26 GPM T/157 GPM, INITAL KILL SPP= 676 PSI AND FINAL KILL SPP= 721 PSI, INITIAL CASING PRESSURE= 0 PSI, FINAL CASING PRESSURE= 0 PSI. MONITOR SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 09:45 | 2022-03-23 10:00 | 0.25 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 11.13 | 17889 | 17889 | 0 | FLOW CHECK, NO FLOW; REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 10:00 | 2022-03-23 11:45 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.2 | 17889 | 17889 | 0 | TRIP OUT OF THE HOLE WET F/2,964'- T/BHA, FILLING BACKSIDE WITH 12.7 PPG OBM CALCULATED FILL @ 1.9 BBLS/STND. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI. PUMPED 60.5 BBLS OF 12.7 PPG OBM CALCULATED FILL (1.9 BBLS/STD) DOWN BACKSIDE NOTE: USED TONGS ON 10 DIFFERENT TIGHT CONNECTIONS
KLONDIKE MILL H08 KL | 13 | 2022-03-23 11:45 | 2022-03-23 12:45 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 11.24 | 17889 | 17889 | 0 | PLACE TOMAX THRUSTER, AND NMDC'S IN MOUSE HOLE, PULL MWD, DRAIN MOTOR AND BREAK BIT, L/D MOTOR AND REMAINING BHA. NOTE: MUD MOTOR DRAINED GOOD, BIT BOX SQUAT WAS WITHIN TOLERENCE, MOTOR DID NOT APPERAR TO BE LOCKED UP. BIT GRADED: 1-1-CT-S-X-0-CT-DMF, OBSERVED 1 JET PLUGGED WITH STATOR RUBBER.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 12:45 | 2022-03-23 17:00 | 4.25 | U | PRDHLLT | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 11.42 | 17889 | 17889 | 0 | REMOVE AND REPLACE IBOP VALVE WHILE MONITORING SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 17:00 | 2022-03-23 17:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 11.44 | 17889 | 17889 | 0 | SERVICE RIG AND TOP DRIVE
KLONDIKE MILL H08 KL | 13 | 2022-03-23 17:30 | 2022-03-23 19:45 | 2.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 11.53 | 17889 | 17889 | 0 | PICK UP BHA #4. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13618579 JETS 6/18S TFA: 1.491), 5", 6/7, 8.8 STG @ 2.12° T/S HS88 -.004 .68 REV/GAL; 4.10' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,170 PSI; STALL TRQ-8,018 FT/LBS; BTI VALVE, 5" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, TEST MWD W/O BIT (TEST GOOD), MAKE UP BIT, BIT TO SVY-64'. BIT TO GAMMA-55'.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 19:45 | 2022-03-23 20:15 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.55 | 17889 | 17889 | 0 | TRIP IN THE HOLE F/ BHA T/627', OBSERVED DISPLACMENT TO TRIP TANK. GAINED 2.9 BBLS IN 2 STDS, FLOW CHECKED, NO FLOW.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 20:15 | 2022-03-23 21:15 | 1 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 11.59 | 17889 | 17889 | 0 | CLOSED ANNULAR AND MONITORED SICP WHILE REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD. SICP = 0.
KLONDIKE MILL H08 KL | 13 | 2022-03-23 21:15 | 2022-03-24 05:00 | 7.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.92 | 17889 | 17889 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/627' T/2,773', PICK UP AGITATOR ON STAND 28, DID NOT FLOW TEST AGITATOR. CONT. STRIP IN HOLE WITH NO RETURNS F/2,773' T/14,962'. FILLING PIPE EVERY 40 STDS, CHOKE: 0% / 0%, MAX CASING PRESSURE= 238 PSI, AVG CASING PRESSURE= 100 PSI. NOTE: LAY DOWN 8 BENT JTS OF DP AND REPLACE SAME. NOTE: CASING PRESSURE REDUCED TO ZERO @ 11,497'
KLONDIKE MILL H08 KL | 13 | 2022-03-24 05:00 | 2022-03-24 06:00 | 1 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 11.96 | 17889 | 17889 | 0 | WASH/REAM IN THE HOLE WITH NO RETURNS ON MUD CAP, F/14,962' T/15,429', GPM=268; RPM=50; TRQ=7-9K CHOKE: 0% / 0%, SICP=0; MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 06:00 | 2022-03-24 08:15 | 2.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.05 | 17889 | 17889 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/15,429' T/16,982', CHOKE: 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. NOTE: ENCOUNTERED AND WASH/REAM TIGHT SPOTS F/15,779' T/15,845', F/16,219' T/16,318', F/16,342' T/16,412' AND F/16,537' AND F/16,537' T/16,601'.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 08:15 | 2022-03-24 10:00 | 1.75 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 12.13 | 17889 | 17889 | 0 | WASH/REAM IN THE HOLE WITH NO RETURNS ON MUD CAP, F/16,982' T/17,889', GPM-300; RPM-50; TRQ-9/11K, SPP-4600 PSI, CHOKE: 0% / 0%, MAX CASING PRESSURE-410 PSI, AVG CASING PRESSURE= 300 PSI, MAX SICP= 337 PSI AND AVG SICP= 200 PSI.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 10:00 | 2022-03-24 11:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.17 | 17889 | 18047 | 158 | DRILL LATERAL-ROT (158' IN 1.02 HRS @ 154.9 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, TQ-15/17K, SPP-4800/5800 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE= 445 PSI, AVG CASING PRESSURE=410 PSI, MAX SICP= 238 PSI, AVG SICP= 238 PSI, DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: CASING PRESSURE INCREASED T/445 PSI @ 17,975' AND FELL T/238 PSI WITH PUMPS OFF, BULL HEAD 40 BBLS 17.5 PPG OBM DOWN BACKSIDE VIA KILL LINE WHILE DRILLING AHEAD, STAGE PUMP RATE UP F/26 GPM T/52 GPM, INITAL KILL LINE SPP= 178 PSI, INITAL CSG PRESSURE= 421 PSI,, FINAL KILL LINE SPP=824 PSI, FINAL CASING PRESSURE= 784 PSI AND FELL T/0 PSI WITH PUMP OFF BACKSIDE.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 11:00 | 2022-03-24 11:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.19 | 18047 | 18067 | 40 | DRILL LATERAL-SLIDE (20' IN .4 HRS @ 50 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP-4800/5000 PSI, DIFF-100/200 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 445 PSI, AVG CASING PRESSURE=410 PSI, MAX SICP= 238 PSI, AVG SICP= 238 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/17889 T/17909 20' TF-180 RPM-80 TQ- 11R 8L 10:05-1029
KLONDIKE MILL H08 KL | 14 | 2022-03-24 11:30 | 2022-03-24 12:15 | 0.75 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 12.22 | 18067 | 18067 | 0 | BULL HEAD 110 BBLS 17.5 PPG OBM (150 BBLS TOTAL PUMPED) DOWN BACKSIDE VIA KILL LINE WHILE CIRCULATING @ 150 GPM AND WORKING PIPE, RPM-50, SPP-3300 PSI, TQ-12/14K, STAGE PUMP RATE UP F/52 GPM T/183 GPM, INITAL KILL LINE SPP= 923 PSI, INITAL CSG PRESSURE=839 PSI, MAX KILL LINE SPP=923 PSI, MAX CSG PRESSURE= 839 PSI, FINAL KILL SPP=496 PSI, FINAL CASING PRESSURE= 227 PSI AND FELL T/0 PSI WITH PUMP OFF BACKSIDE.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 12:15 | 2022-03-24 15:00 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.33 | 18067 | 18398 | 120.4 | DRILL LATERAL-ROT (331' IN 2.8 HRS @ 118.21 FPH) WOB-25/35K, SPM-72/72, GPM-375, RPM-70, MRPM-255, TRPM-325, TQ-15/17K, SPP-5000/6000 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI, AVG SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY +/- 300' OR AS NEEDED. (SWEEP CONSISTING OF 2 PPB PHPA AND DRILL WATER.) NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 12:36 HRS, DEPTH WHEN RECEIVED 18,106'. NEW TARGET LINE: 10,653' TVD (0' VS) @ 87.2 DEG INC. 5' ABOVE/ 5' BELOW. WINDOW CHANGE RECEIVED VIA TEXT @ 14:23 HRS, DEPTH WHEN RECEIVED 18,305'. NEW WINDOW: 10' ABOVE/ 0' BELOW.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 15:00 | 2022-03-24 16:15 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.39 | 18398 | 18448 | 40 | DRILL LATERAL-SLIDE (50' IN 1.2 HRS @ 41.67 FPH) WOB-20/30K, SPM-72/72, GPM-375, MRPM-255, SPP-5000/5400 PSI, DIFF-200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI, AVG SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/18178 T/18193 15' TF-HS TQ-8R 6L RPM- 80 1313-1342 SLD F/18305 T/18325 20' TF-180 TQ-7R 5L RPM-80 1435-1455 SLF F/18372 T/18387 15' TF-HS TQ-8R 6L RPM-80 1525-1548
KLONDIKE MILL H08 KL | 14 | 2022-03-24 16:15 | 2022-03-24 16:45 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.41 | 18448 | 18448 | 0 | SERVICE RIG , TOP DRIVE, DRAWWORKS AND ST-80.
KLONDIKE MILL H08 KL | 14 | 2022-03-24 16:45 | 2022-03-24 23:15 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.68 | 18448 | 19382 | 143.7 | DRILL LATERAL-ROT (934' IN 6.4 HRS @ 146 FPH) WOB-25/35K, SPM-72/72, GPM-375, RPM-70, MRPM-255, TRPM-325, TQ-15/17K, SPP-5800/6000 PSI, DIFF-800/1000 PSI, CHOKES-0% /0%,, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI, AVG SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. NOTE: PUMP 10 BBLS OF PHPA SWEEP, EVERY +/- 300' OR AS NEEDED. (SWEEP CONSISTING OF 2 PPB PHPA AND DRILL WATER.)
KLONDIKE MILL H08 KL | 14 | 2022-03-24 23:15 | 2022-03-25 00:30 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.73 | 19382 | 19429 | 37.6 | DRILL LATERAL-SLIDE (47' IN 1.35 HRS @ 35 FPH) WOB-20/30K, SPM-72/72, GPM-375, MRPM-255, SPP-4700/5000 PSI, DIFF-200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI, AVG SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH OF DIESEL AND 2 GALS/HR OF PHPA. SLIDE DEPTHS: SLD F/18745 T/18760 15' TF-150R 1853-1919 RPM-80 TQ-8R 5L SLD F/19025 T/19037 12' TF-180 2105-2129 RPM-80 TQ-8R 5L SLD F/19307 T/19327 20' TF-HS 2316-2347 RPM-80 TQ-10R 6L
KLONDIKE MILL H08 KL | 14 | 2022-03-25 00:30 | 2022-03-25 01:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.77 | 19429 | 19429 | 0 | PERFORMED CLEAN UP CYCLE WITH WELL ON MUD CAP. PUMPED 2-30 BBL PHPA SWEEP IN TANDEM, CIRCULATE 5 BOTTOMS UP TO LOSS ZONE, SPM-76/76, GPM-400, RPM-50, TQ-10K/12K, SPP-4900 PSI, CHOKES- 0% / 0%. MAX CSG PSI WHILE CIRC-0 PSI. 1ST BTM UP START TQ=12K/15K, END= 12K/14K, P/U WT=250K 2ND BTM UP START TQ=11K/13K, END= 10K/12K, P/U WT=235K 3RD BTM UP START TQ=10K/11K, END= 9K/10K, P/U WT=230K
KLONDIKE MILL H08 KL | 14 | 2022-03-25 00:30 | 2022-03-25 00:30 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 12.73 | 19429 | 19429 |  | MILESTONE_TD WELL ON 3/25/2022 @ 00:30 HRS
KLONDIKE MILL H08 KL | 14 | 2022-03-25 01:30 | 2022-03-25 02:15 | 0.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.8 | 19429 | 19429 | 0 | STRIP OUT THE HOLE WET ON ELEVATORS F/ 19,429' T/ 18,467' , FILLING BACKSIDE WITH 13.2 PPG OBM VIA KILL LINE, CALCULATED FILL 1.9 BBL/STND. MAX OVER PULL-390K, CHOKES- 0% / 0%, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE=0 PSI, NOTE: SIDPP @ TD= 2760 PSI, TVD 11,103' NOTE: PUMPED 19 BBLS 13.2 PPG OBM DOWN BACKSIDE
KLONDIKE MILL H08 KL | 14 | 2022-03-25 02:15 | 2022-03-25 06:00 | 3.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.96 | 19429 | 19429 | 0 | STRIP OUT OF THE HOLE WET F/18,467' T/13,300' WHILE LAYING DOWN DRILL PIPE, FILLING BACKSIDE WITH 13.2 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI. PUMPED 110 BBLS OF 13.2 PPG OBM NOTE: USED TONGS ON 1 TIGHT CONNECTION
KLONDIKE MILL H08 KL | 15 | 2022-03-25 06:00 | 2022-03-25 14:45 | 8.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 13.32 | 19429 | 19429 | 0 | STRIP OUT OF THE HOLE WET F/13,300' T/3,612' WHILE LAYING DOWN DRILL PIPE, FILLING BACKSIDE WITH 13.2 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX DRAG 20-30K, MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI. PUMPED 197 BBLS OF 13.2 PPG OBM NOTE: USED TONGS ON 9 TIGHT CONNECTIONS. 15 MIN. WORK PIPE WHILE CHANGING OUT BUSTED HYDRAULIC HOSE ON ST-80.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 14:45 | 2022-03-25 15:15 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.34 | 19429 | 19429 | 0 | SERVICE RIG, TOP DRIVE, DRAWWORKS AND ST-80; FUNCTION TESTED STOMPER WITH PATTERSON TECH. MONITOR SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 15:15 | 2022-03-25 16:00 | 0.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 13.38 | 19429 | 19429 | 0 | STRIP IN THE HOLE F/3,612' T/4,921' WITH PIPE THAT PREVIOUSLY RACKED BACK IN DERRICK WITH NO RETURNS, CHOKES: 0% / 0% , MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 16:00 | 2022-03-25 17:45 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 13.45 | 19429 | 19429 | 0 | STRIP OUT OF THE HOLE WET F/4,921' T/3140' WHILE LAYING DOWN DRILL PIPE, FILLING BACKSIDE WITH 13.2 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI. PUMPED 36 BBLS OF 13.2 PPG OBM NOTE: USED TONGS ON 4 TIGHT CONNECTIONS.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 17:45 | 2022-03-25 18:15 | 0.5 | P | PRDHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 13.47 | 19429 | 19429 | 0 | BULLHEADED 50 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/183 GPM, INITIAL KILL LINE SPP= 0 PSI AND INITAL CASING PRESSURE= 0 PSI, MAX KILL LINE SPP= 278 PSI, MAX CASING PRESSURE= 0 PSI, FINAL KILL LINE SPP= 278 PSI AND FINAL CASING PRESSURE= 0 PSI.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 18:15 | 2022-03-25 18:30 | 0.25 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 13.48 | 19429 | 19429 | 0 | OPEN CHOKE AND MONITORED FLOW (NO FLOW), OPEN ORBIT VALVE, CHECK FLOW (NO FLOW), REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 18:30 | 2022-03-25 19:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.5 | 19429 | 19429 | 0 | SERVICE RIG AND TOP DRIVE UNIT, WORK ON HYDRAULIC LEAK IN SUB STRUCTURE
KLONDIKE MILL H08 KL | 15 | 2022-03-25 19:00 | 2022-03-25 20:00 | 1 | U | PRDHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 13.54 | 19429 | 19429 | 0 | 1" HYDRAULIC LINE FEEDING RIG FLOOR ON OFF DRILLER SIDE SUB BUSTED AND STARTED LEAKING, REPLACE WITH NEW HOSE.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 20:00 | 2022-03-25 22:45 | 2.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 13.66 | 19429 | 19429 | 0 | TRIP OUT THE HOLE F/3,139' T/ BHA WHILE LAYING DOWN DRILL PIPE, FILLING BACKSIDE WITH 13.2 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. PUMPED 64 BBLS OF 13.2 PPG OBM NOTE: USED TONGS ON TIGHT CONNECTIONS.
KLONDIKE MILL H08 KL | 15 | 2022-03-25 22:45 | 2022-03-26 | 1.25 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.71 | 19429 | 19429 | 0 | DRAIN MOTOR, BREAK BIT, LAY DOWN BTI VALVE, 2 MONELS AND X-OVER WHILE MONITORING SICP, SICP= 0 PSI. NOTE: MUD MOTOR DRAINED GOOD, BIT BOX SQUAT WAS WITHIN TOLERENCE BIT GRADED: 3-3-BT-G-BF-0-NO-TD
KLONDIKE MILL H08 KL | 15 | 2022-03-26 | 2022-03-26 00:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 13.73 | 19429 | 19429 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELAVATORS WHILE MONITORING SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 15 | 2022-03-26 00:30 | 2022-03-26 01:45 | 1.25 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 13.78 | 19429 | 19429 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT WHILE MONITORING SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 15 | 2022-03-26 01:45 | 2022-03-26 02:45 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.82 | 19429 | 19429 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/2,022' WITH NO RETURNS, FILLING PIPE ON THE FLY WITH WATER.
KLONDIKE MILL H08 KL | 15 | 2022-03-26 02:45 | 2022-03-26 03:15 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 13.84 | 19429 | 19429 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
KLONDIKE MILL H08 KL | 15 | 2022-03-26 03:15 | 2022-03-26 06:00 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.96 | 19429 | 19429 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/2,022' T/4,500' WHILE STRIPPING IN WITH NO RETURNS. MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY WITH WATER.
KLONDIKE MILL H08 KL | 16 | 2022-03-26 06:00 | 2022-03-26 10:00 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.13 | 19429 | 19429 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/4,500' T/9,891' WHILE STRIPPING IN WITH NO RETURNS. MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY WITH WATER. NOTE: ENSURED PIPE WAS FULL.
KLONDIKE MILL H08 KL | 16 | 2022-03-26 10:00 | 2022-03-26 10:45 | 0.75 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 14.16 | 19429 | 19429 | 0 | RIG DOWN 5" CRT AND ELEVATORS, RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 16 | 2022-03-26 10:45 | 2022-03-26 17:00 | 6.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.42 | 19429 | 19429 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/9,891' T/18,671' WHILE STRIPPING IN WITH NO RETURNS FILLING PIPE ON THE FLY, MAX DRAG- XXK, CHOKES: 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. ENCOUNTERED TIGHT SPOT AT 18,671'
KLONDIKE MILL H08 KL | 16 | 2022-03-26 17:00 | 2022-03-26 19:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.5 | 19429 | 19429 | 0 | WASH AND REAM PRODUCTION CASING F/18,671' T/19,389' @ 10-20 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-7K/15K, SPM-100-40, BPM: 6, SPP-1000-2400 PSI, NO RETURNS, CHOKES CLOSED; CSG PRESS INCREASED 133 PSI @ 18,927'. BULLHEADED 80 BBLS 17.5 PPG DOWN ANNULUS WHILE WASH/REAM @ 288 GPM. CSG PRESS INCREASED T/1135 PSI, SLOWED PUMPS TO 128 GPM. INITIAL KLSPP=440 PSI, INT CSG PRESS -424 PSI, MAX KLSPP-599 PSI, MAX CSG PRESS 519 PSI. FINAL KLSPP-48 PSI, FINAL CSG PRESS 41 PSI. FELL TO 0 PSI WHEN KILLED PUMPS.
KLONDIKE MILL H08 KL | 16 | 2022-03-26 19:00 | 2022-03-26 19:45 | 0.75 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 14.53 | 19429 | 19429 | 0 | FLOW CHECK, NO FLOW. CLOSE ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD, SLACK OFF AND INSTALL ROTATING HEAD, OPEN ANNULAR
KLONDIKE MILL H08 KL | 16 | 2022-03-26 19:45 | 2022-03-26 21:00 | 1.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 14.58 | 19429 | 19429 | 0 | WASH AND REAM LANDING JT IN F/19,389’ T/19,419.3’, AND LAND ON HANGER W/120K (W/O BLOCKS) @ 19,419.3’. 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICYWEDGE 425 CASING, 2 JTS 5" 18# P110 ICYWEDGE 425 CASING AND TEST FLOAT EQUIPMENT. RAN 216 JTS OF 5" 18# P110 ICY WEDGE 425 CASING (221 JTS TOTAL), 1- X-OVER 425x463, 1 JOINT WEDGE 463, 1-5.5" MARKER JT, RAN 210 JTS OF 5.5" 23# P-110 WEDGE 463 (211 JTS TOTAL), 1-5.5" MARKER JT, 2 JOINTS WEDGE 463. CASING SHOE @ 19,419.3' TOP OF FLOAT COLLAR @ 19,369.3' BTM OF TOE SLEEVE VALVE @ 19,324.9' TOP OF TOE SLEEVE VALVE @ 19,299.4' TOP OF X-OVER @ 9,528' TOP OF MARKER JT @ 9,463.8' LEFT OUT 1 JOINT OF 5"-44.38' (BAD BOX) LEFT OUT 2 JOINTS OF 5.5"-87.74'
KLONDIKE MILL H08 KL | 16 | 2022-03-26 21:00 | 2022-03-26 21:45 | 0.75 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 14.61 | 19429 | 19429 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE, BULLHEAD 25 BBLS 17.5 PPG DOWN ANNULUS WHILE R/D. 30 SPM, 97 GPM, KLSPP-70 PSI, CSG PRESS - 0. MONITOR SICP, SICP= 0 PSI.
KLONDIKE MILL H08 KL | 16 | 2022-03-26 21:45 | 2022-03-26 22:45 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.66 | 19429 | 19429 | 0 | CIRCULATE 1 CASING CAPACITY WITH CHOKES CLOSED WHILE RIGGING DOWN CASING TOOLS, STAGING PUMPS UP TO SPM- 105, GPM-336 (8 BPM), SPP- 2450 PSI. INITIAL CASING PRESSURE WHILE CIRCULATING= 0 PSI AND FINAL CASING PRESSURE WHILE CIRCULATING= 0 PSI, SHUT IN CASING PRESSURE= 0 PSI. HOLD PJSM WITH NINE CEMENT CREW.
KLONDIKE MILL H08 KL | 16 | 2022-03-26 22:45 | 2022-03-27 02:00 | 3.25 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 14.79 | 19429 | 19429 | 0 | SWAP CIRCULATING IRON T/ CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI, CEMENTED 1ST STAGE 5/5.5" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 45 BBL 10.5 PPG WEIGHTED SPACER, 306 BBL 13.5 PPG 1010 SK 1.7 YIELD 35/65 POZ-CLASS H LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 378 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 8 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2,200 PSI, BUMPED PLUG AS CALCULATED, PRESSURE INCREASED TO 3,200 PSI, HELD FOR 5 MIN, BLED BACK 5 BBLS. FLOATS HELD. MAX CSG PSI= 0 PSI, AVG CASING PSI=0 PSI, CSG PRESSURE=0 PSI WITH PUMPS OFF AFTER CEMENTING. NOTE: IMMEDIATELY AFTER VERIFYING THAT FLOATS HELD, LINED UP ON KILL-LINE, PUMPED 68.5 BBLS OF 13.2 PPG OBM AND CSG PRESSURE INCREASED T/97 PSI, STARTED PUMPING 17.5 PPG @ BPM: 2, KILL-LINE SPP: 0 PSI, CSG PRESSURE: 0 PSI. BPM: 4, KILL-LINE SPP: 0 PSI, CSG PRESSURE: 0 PSI. BPM: 6, KILL-LINE SPP: 0 PSI, CSG PRESSURE: 0 PSI. ONCE A TTL OF 20 BBLS WERE PUMPED CSG PRESSURE REMAINED 0 PSI, SHUT DOWN THE PUMP TO MONITOR SICP, FINAL SICP=0, MAX CASING PRESSURE=0 PSI.
KLONDIKE MILL H08 KL | 16 | 2022-03-27 02:00 | 2022-03-27 04:30 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 14.9 | 19429 | 19429 | 0 | HELD PJSM, R/U CMT LINE TO KILL-LINE, REMOVE CHECK VALVE AND TEST CMT LINE TO 8,000 PSI. PUMP 35 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 326 BBLS 1080 SK 1.7 YIELD 35/65 POZ-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 20 BBLS WATER. MAX CSG PSI= 2335 PSI W/320 BBLS OF LEAD CEMENT PUMPED @ 6 BPM, AVG CASING PSI= 1920 PSI. MAX PUMP PRESSURE=2730 PSI @ 6 BPM. CSG PRESSURE DECREASED TO 0 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC-1,212'.
KLONDIKE MILL H08 KL | 16 | 2022-03-27 04:30 | 2022-03-27 05:00 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 14.92 | 19429 | 19429 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP= 0 PSI, FINAL SICP= 0 PSI.
KLONDIKE MILL H08 KL | 16 | 2022-03-27 05:00 | 2022-03-27 06:00 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 14.96 | 19429 | 19429 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE FOSV. NOTE: TOP DRIVE BROKE DOWN, WORK WITH ELECTICIAN TO REPAIR BEFORE LAYING OUT LANDING JOINT. AND SETTING PACK OFF. NOTE: START CLEANING MUD TANKS @ 05:00.
KLONDIKE MILL H08 KL | 17 | 2022-03-27 06:00 | 2022-03-27 07:00 | 1 | U | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15 | 19429 | 19429 | 0 | BEFORE PICKING UP ON LANDING JOINT NOTICED TOP DRIVE CABLE ARCING OUT. CONTINUE TO REPAIR TOP DRIVE 19 PIN CABLE AND DRAWWORKS POWER LEAD. MONITOR SICP, INITIAL SICP= 0 PSI, FINAL SICP= 0 PSI.
KLONDIKE MILL H08 KL | 17 | 2022-03-27 07:00 | 2022-03-27 08:00 | 1 | U | PRDHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 15.04 | 19429 | 19429 | 0 | CONTINUE TO REPAIR TOP DRIVE 19 PIN CABLE AND DRAWWORKS POWER LEAD. . MONITOR SICP, INITIAL SICP= 0 PSI, FINAL SICP= 0 PSI.
KLONDIKE MILL H08 KL | 17 | 2022-03-27 08:00 | 2022-03-27 09:15 | 1.25 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 15.09 | 19429 | 19429 | 0 | LAY DOWN LANDING JOINT. REMOVE BAILS AND CASING ELEVATORS, AND RIG UP RIG 4.5" ELEVATORS, RIG UP WASH TOOL AND SET 6" ABOVE HANGER, PUMP @ 150 GPM W/53 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV. WASH THROUGH BOP STACK AND CHOKE MANIFOLD.
KLONDIKE MILL H08 KL | 17 | 2022-03-27 09:15 | 2022-03-27 12:45 | 3.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 15.24 | 19429 | 19429 | 0 | REMOVE FLOW LINE FROM SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOP STACK, BACKOUT WH SET SCREWS AND RAISE BOPE, REMOVE STREAM FLO BOPE ADAPTER, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI.
KLONDIKE MILL H08 KL | 17 | 2022-03-27 12:45 | 2022-03-27 16:00 | 3.25 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 15.38 | 19429 | 19429 | 0 | REMOVE TURN BUCKLES, REMOVE HCR LINE, KILL LINE, KILL LINE CHECK VALVE, HYDRAULIC LINES, HOLE FILL, REMOVE FLOW LINE AND AIR LINES/HYDRAULIC LINES FROM ROTATING HEAD, LAY OVER AND SECURE BOP’S, CHANGE OUT SWIVEL PACKING AND SAVER SUB F/ CET 43 T/ 4 1/2 IF, RIG DOWN AND ELEVATORS AND BALES; CLEAN AND ORGANIZE RIG FLOOR, REMOVE ALL 4 ½” DRILL PIPE EQUIPMENT FROM RIG FLOOR, HANG OFF TOP DRIVE AND START UNSPOOLING DRAWWORKS, CONTINUE TO CLEAN MUD TANKS. BRADY TRUCKING HAULED DRILL PIPE AND MISC. TO THE GLACIER PAD. NOTE: FINISHED CLEANING MUD TANKS AND RELEASED WELL ON 03/27/2022 @ 16:00 HRS
KLONDIKE MILL H08 KL | 17 | 2022-03-27 16:00 | 2022-03-28 02:00 | 10 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 15.79 | 19429 | 19429 | 0 | CONTINUE TO UNSPOOL DRAWWORKS, DETOX AND CLEAN RIG, START RIGGING DOWN ELECTRICAL AND HYDRAULIC HOSES FROM RIG FLOOR TO FESTOON, PULL AND UNHOOK ELECTRICAL, HYDRAULIC, WATER, MUD AND AIR LINES FROM MUD TANKS. KNOCK LOOSE TANK UNIONS AND EQUALIZERS, RIG DOWN BACKYARD.
KLONDIKE MILL H08 KL | 17 | 2022-03-27 16:00 | 2022-03-27 16:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 15.38 | 19429 | 19429 |  | MILESTONE_WELL RELEASE ON 03/27/2022 @ 16:00
KLONDIKE MILL H08 KL | 17 | 2022-03-28 02:00 | 2022-03-28 02:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 15.79 | 19429 | 19429 |  | MILESTONE_RIG RELEASE ON 03/27/2022 @ 02:00
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 12:30 | 2022-01-31 12:30 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 1/31/2022 @ 12:30
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 12:30 | 2022-01-31 15:00 | 2.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/KLONDIKE TRAIL H04 KL T/KLONDIKE RUSH H06 KL; SET MATS, WALK F/KLONDIKE TRAIL H04 KL T/KLONDIKE RUSH H06 KL; CENTER SUB OVER CONDUCTOR
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 15:00 | 2022-01-31 15:30 | 0.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | L/D LANDING JOINT, REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 15:30 | 2022-01-31 16:30 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 16:30 | 2022-01-31 18:00 | 1.5 | P | MOBDMOB | TRIP | BHA | TRIP FOR BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, TAG BOTTOM @ 108'.
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 18:00 | 2022-01-31 23:45 | 5.75 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.24 | 108 | 2668 | 445.2 | ROTATE ( 2,560’ IN 5.77 HRS @ 443.93 FPH) WOB-25-35K, RPM-100, TRQ- 5K/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2100/2700 PSI, DIFF 300/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/ SOAP/ SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 30 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM.
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 18:00 | 2022-01-31 18:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 1/31/2022 @ 18:00.
KLONDIKE RUSH H06 KL | 1 | 2022-01-31 23:45 | 2022-02-01 00:30 | 0.75 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.27 | 2668 | 2823 | 206.7 | SLIDE (155' IN .73 HRS @ 211.36 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2,100/2,600 PSI, DIFF-200/500 PSI. SLIDE DEPTH: SLD F/561 T/581 20' TF-330M 1921-1925 SLD F/749 T/764 15' TF-350M 1946-1950 SLD F/936 T/956 20' TF-150R 2009-2013 SLD F/1124 T/1144 20' TF-130M 2033-2038 SLD F/1312 T/1332 20' TF-180M 2059-2104 SLD F/2344 T/2364 20' TF-270M 2314-2320 SLD F/2439 T/2459 20' TF-270M 2332-2340 SLD F/2627 T/2647 20' TF-270M 0003-0011
KLONDIKE RUSH H06 KL | 1 | 2022-02-01 00:30 | 2022-02-01 01:15 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.3 | 2823 | 2823 | 0 | PUMP 2-30 BBL SOAP AND SAP SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K,
KLONDIKE RUSH H06 KL | 1 | 2022-02-01 01:15 | 2022-02-01 02:15 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.34 | 2823 | 2823 | 0 | TRIP OUT OF HOLE F/2,823' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
KLONDIKE RUSH H06 KL | 1 | 2022-02-01 02:15 | 2022-02-01 03:15 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.39 | 2823 | 2823 | 0 | REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. NOTE: INSPECTED MOTOR AND BIT: MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-1-NO-A-X-0-NO-TD.
KLONDIKE RUSH H06 KL | 1 | 2022-02-01 03:15 | 2022-02-01 04:15 | 1 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.43 | 2823 | 2823 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS
KLONDIKE RUSH H06 KL | 1 | 2022-02-01 04:15 | 2022-02-01 06:00 | 1.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.5 | 2823 | 2823 | 0 | RUN 10 3/4" 45.5# J-55 BT&C CASING T/1,801'. CASING DETAILS ON REPORT TO FOLLOW.
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 06:00 | 2022-02-01 07:00 | 1 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.54 | 2823 | 2823 | 0 | RUN 10 3/4" 45.5# J-55 BT&C CASING T/2,807'. RAN 36 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 100K (W/O BLOCKS). SHOE- 2,807' TOP OF FLOAT COLLAR- 2,727' 14 JOINTS LEFT OUT- 545.31'
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 07:00 | 2022-02-01 08:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.58 | 2823 | 2823 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-337, SPP-140 PSI. NO LOSSES.
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 08:00 | 2022-02-01 08:15 | 0.25 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.59 | 2823 | 2823 | 0 | RIG DOWN CRT, L/D LANDING JOINT.
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 08:15 | 2022-02-01 10:45 | 2.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.59 | 2823 | 2823 | 0 | WALK RIG F/ KLONDIKE RUSH H06 KL T/ KLONDIKE MILL H08 KL. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 08:15 | 2022-02-01 08:15 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.59 | 2823 | 2823 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 2/1/2022 @ 08:15
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 10:45 | 2022-02-01 13:15 | 2.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.59 | 2823 | 2823 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 304 BBLS 11.6 PPG LEAD CEMENT, 78 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 260 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/660 PSI PRESSURED UP T/1160 PSI (500 PSI OVER) @ 4.0 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 200 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
KLONDIKE RUSH H06 KL | 2 | 2022-02-01 13:15 | 2022-02-01 14:15 | 1 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.59 | 2823 | 2823 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 06:00 | 2022-02-06 07:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.64 | 2823 | 2823 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK RIG FROM KLONDIKE MILL H08 KL TO KLONDIKE RUSH H06 KL, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 06:00 | 2022-02-06 06:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.59 | 2823 | 2823 |  | MILESTONE_RESUME WELL 1 ON 2/6/2022 @ 06:00
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 07:00 | 2022-02-06 08:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.68 | 2823 | 2823 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, KILL LINE & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 08:00 | 2022-02-06 09:00 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.72 | 2823 | 2823 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, KILL LINE, AND KILL LINE CHECK VALVE T/250 PSI LOW / 5,000 PSI HIGH., TEST 2" MANUAL HCR ON STANDPIPE MANIFOLD T/250 PSI LOW / 5,000 PSI HIGH.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 09:00 | 2022-02-06 10:00 | 1 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 0.76 | 2823 | 2823 | 0 | INSTALL WEAR BUSHING, MOUSEHOLE, TRIP NIPPLE, CLOSE CASING VALVE AND COVER CELLAR.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 10:00 | 2022-02-06 11:30 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 0.82 | 2823 | 2823 | 0 | PICK UP BHA #2. (9-7/8" ULTERRA SPL613 SN #:55308, JETS 5/14'S, 1/13 & 3/16'S TFA: 1.47) BIT, 8", 7/8L, 5.9 STG @ 2.0° TS HPW +.002; .155 REV/GAL; 5.91' BIT TO BEND; 8.35" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1,390 PSI; 8" NMPDC, 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2-STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 11- JTS 5"HWDP, 22 STDS OF 5'' DP, DSW AGITATOR. BIT TO SENSOR-65', GAMMA-61'. TEST MWD ( GOOD TEST).
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 11:30 | 2022-02-06 13:00 | 1.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 0.89 | 2823 | 2823 | 0 | TRIP IN HOLE F/BHA T/2,724'. PICK UP AGITATOR ON STAND 22: FILL PIPE, PSI BEFORE-580 PSI AFTER-710 @ 321 GPM, HOLE GIVING PROPER DISPLACEMENT.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 13:00 | 2022-02-06 13:30 | 0.5 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 0.91 | 2823 | 2823 | 0 | FLOW CHECK, NO FLOW. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 13:30 | 2022-02-06 14:30 | 1 | U | SFHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 0.95 | 2823 | 2823 | 0 | CHANGE OUT 4" INTERNAL VALVE GASKET ON MP #1
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 14:30 | 2022-02-06 15:00 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 0.97 | 2823 | 2833 | 20 | DRILL SHOE TRACK AND FLOAT EQUIPMENT, DRILL 10' NEW FORMATION F/2,823' T/2,833', GPM-400, SPP- 1,200 PSI, DIFF-400, RPM-30, TQ-2/6K.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 15:00 | 2022-02-06 15:30 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 0.99 | 2833 | 2833 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-400, SPP-1,100 PSI, RPM-30. MUD WT IN/OUT=8.9 PPG.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 15:30 | 2022-02-06 16:00 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.01 | 2833 | 2833 | 0 | PERFORM F.I.T. WITH 8.9 PPG OBM, 394 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD- 2,807'/TVD-2,806'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE. RESULTED IN GOOD TEST.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 16:00 | 2022-02-06 20:45 | 4.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.21 | 2833 | 5258 | 510.5 | ROT (2,425' IN 4.67 HRS @ 519 FPH) WOB:25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4500/5200 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 20:45 | 2022-02-06 22:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.26 | 5258 | 5383 | 100 | SLIDE (125' IN 1.23 HRS 101.62 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4500/5000 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/2,928'-T/2,940', 12', TF:20R, 16:06-16:10 F/3,020'-T/3,032', 12', TF: HS, 16:20-16:26 F/3,300'-T/3,312', 12', TF:HS, 16:55-16:58 F/3,584'-T/3,594', 10', TF:180, 17:25-17:30 F/3,680'-T/3,692', 12', TF:180, 17:38-17:45 F/3,873'-T/3,885', 12', TF:180, 18:03-18:09 F/3,967'-T/3,977', 10', TF:180, 18:22-18:28 F/4,048'-T/4,056', 8', TF:180, 18:39-18:43 F/4,248'-T/4,258', 10', TF:0M, 19:04-19:10 F/5,280'-T/5,292', 12', TF:90M, 21:16-21:28 F/5,368'-T/5,383', 15', TF:90M, 21:39-21:54
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 22:00 | 2022-02-06 23:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.3 | 5383 | 5629 | 246 | CONTROL DRILL ON #2 AND #3 PUMPS, WHILE CLEANING OUT SUCTION SCREEN ON #1 MP. ROT (246' IN 1.1 HRS @ 223.63 FPH) WOB:20/25K, SPM: 105/105, GPM: 674, MMRPM: 104.47, RPM-80, TRPM: 184.47, TRQ: 7K/17K, SPP: 3000/3450 PSI, DIFF: 300/650 PSI.
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 23:00 | 2022-02-06 23:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.31 | 5629 | 5644 | 60 | CONTROL DRILL ON #2 AND #3 PUMPS, WHILE CLEANING OUT SUCTION SCREEN ON #1 MP. SLIDE (15’ IN 0.25 HRS @ 60 FPH) WOB: 15/20K, SPM: 105/105, GPM: 674, MMRPM: 104.47, SPP: 3,680/3,930 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/5,462'-T/5,477', 15', TF: 30M, 22:39-22:54
KLONDIKE RUSH H06 KL | 3 | 2022-02-06 23:15 | 2022-02-07 03:45 | 4.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.5 | 5644 | 7420 | 394.7 | ROT (1,776' IN 4.33 HRS @ 410.16 FPH) WOB:25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4700/5400 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE RUSH H06 KL | 3 | 2022-02-07 03:45 | 2022-02-07 06:00 | 2.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.59 | 7420 | 7520 | 44.4 | SLIDE (100' IN 2.42 HRS 41.32 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4500/5000 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/5,644'-T/5,664', 20', TF:45M, 23:16-23:52 F/5,737'-T/5,757', 20', TF:45M, 00:03-00:34 F/6,592'-T/6,607', 15', TF:90M, 02:29-02:44 F/6,961'-T/6,976', 15', TF:120M, 03:36-03:58 F/7,050'-T/7,065', 15', TF:120M, 04:10-04:29 F/7,337'-T/7,352', 15', TF:120M, 05:09-05:30
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 06:00 | 2022-02-07 09:45 | 3.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.75 | 7520 | 8839 | 351.7 | ROT (1,319' IN 3.73 HRS @ 354 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4500/5200 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 09:45 | 2022-02-07 11:00 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.8 | 8839 | 8942 | 82.4 | SLIDE (103' IN 1.27 HRS 81 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4500/5000 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/7,708' T/7,728' 20' TF:180M, 06:22-6:34 F/7,993' T/8,011' 18' TF:150M, 07:18-7:29 F/8,180' T/8,198' 18' TF:120M, 07:59-8:12 F/8,369' T/8,384' 15' TF:135M, 08:47-8:57 F/8,835' T/8,853' 18' TF:130M, 10:10-10:18 F/8,928' T/8,942' 14' TF:130M, 10:38-10:49
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 11:00 | 2022-02-07 12:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.84 | 8942 | 9210 | 268 | ROT (268' IN 1 HRS @ 268 FPH) WOB: 25/28K, SPM:107/107, GPM: 686, MMRPM: 106.33, RPM-80,TRPM:186.33, TRQ: 7K/17K, SPP: 3,165/3,615 PSI, DIFF: 400/450 PSI. NOTE: DRILLING ON 2 MPS DUE TO CHANGING LINER GASKERT ON #2 MUD PUMP
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 12:00 | 2022-02-07 12:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.85 | 9210 | 9228 | 72 | SLIDE (18' IN .30 HRS 60 FPH) WOB: 10/20K, SPM: 107/107, GPM: 686, MMRPM: 106.33, SPP: 3150/3500 PSI, DIFF: 100/350 PSI. SLIDE DEPTHS: F/9,210' T/9,228', 18' TF:90M, 12:00-12:12 NOTE: DRILLING ON 2 MPS DUE TO CHANGING LINER GASKET ON #2 MUD PUMP
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 12:15 | 2022-02-07 14:00 | 1.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.93 | 9228 | 9577 | 199.4 | ROT (349' IN 1.7 HRS @ 205 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4500/5200 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 14:00 | 2022-02-07 14:30 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.95 | 9577 | 9577 | 0 | SERVICE RIG. LUBE RIG: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 14:30 | 2022-02-07 15:30 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.99 | 9577 | 9801 | 224 | ROT (224' IN 1 HRS @ 224 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4500/5200 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
KLONDIKE RUSH H06 KL | 4 | 2022-02-07 15:30 | 2022-02-08 | 8.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.34 | 9801 | 10021 | 25.9 | BUILD CURVE-SLIDE (220' IN 8.5 HRS 25.88 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 5,050 PSI, DIFF: 100/350 PSI. SLIDE DEPTHS: F/9,801'-T/10,021', 220', TF:140M, 15:30-00:00, RPM: 30, TQ: 5R/2L
KLONDIKE RUSH H06 KL | 4 | 2022-02-08 | 2022-02-08 00:30 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.36 | 10021 | 10021 | 0 | SERVICE RIG. REPLACE O-RING ON STANDPIPE. LOCATION: UNION BETWEEN THE VIBRATING HOSE COMING FROM RIG FLOOR TO THE FIRST HARD LINE. NOTE: WORKED PIPE W/ MINIMAL DRAG, DUE TO NOT BEING ABLE TO CIRC.
KLONDIKE RUSH H06 KL | 4 | 2022-02-08 00:30 | 2022-02-08 01:15 | 0.75 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.4 | 10021 | 10021 | 0 | CONT. REPLACE O-RING ON STANDPIPE. LOCATION: UNION BETWEEN THE VIBRATING HOSE COMING FROM RIG FLOOR TO THE FIRST HARD LINE. NOTE: WORKED PIPE W/ MINIMAL DRAG, DUE TO NOT BEING ABLE TO CIRC.
KLONDIKE RUSH H06 KL | 4 | 2022-02-08 01:15 | 2022-02-08 03:00 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.47 | 10021 | 10065 | 25.1 | BUILD CURVE-SLIDE (44' IN 1.75 HRS 25.14 PH) WOB: 10/20K, SPM: 107/107, GPM: 686, MMRPM:106.33, SPP: 3600/3900 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/10,021'-T/10,065', 44', TF:30L, 00:15-03:00 RPM: 30 TQ: 5R/2L NOTE: DRILLING ON 2 MPS DUE TO C/O LINER GASKET ON #2 MP
KLONDIKE RUSH H06 KL | 4 | 2022-02-08 03:00 | 2022-02-08 06:00 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.59 | 10065 | 10160 | 31.7 | BUILD CURVE-SLIDE (95' IN 3.0 HRS 31.6 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 5,050 PSI, DIFF: 100/350 PSI. SLIDE DEPTHS: F/10,065'-T/10,160', 95', TF:30L, 03:00-06:00, RPM: 30, TQ: 5R/2L
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 06:00 | 2022-02-08 07:45 | 1.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.67 | 10160 | 10160 | 0 | PERFORM CLEAN UP CYCLE PUMPING 2-30 BBL HI -VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7-5/8" CASING. GPM-850, SPP 5,000 PSI, SHAKERS CLEAN
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 07:45 | 2022-02-08 10:00 | 2.25 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.76 | 10160 | 10160 | 0 | PERFORM FLOW CHECK (NO FLOW), PUMP SLUG, POOH F/10,160' T/2,965', PROPER FILL WITH TRIP TANK. FLOW CHECK AT SHOE.
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 10:00 | 2022-02-08 10:30 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 2.78 | 10160 | 10160 | 0 | L/D AGITATOR, PULL ROTATING HEAD AND INSTALL TRIP NIPPLE
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 10:30 | 2022-02-08 11:45 | 1.25 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.83 | 10160 | 10160 | 0 | CONTINUE TRIP OUT F/2,965' T/BHA, HOLE TAKING PROPER FILL ON TRIP TANK.
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 11:45 | 2022-02-08 13:15 | 1.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 2.9 | 10160 | 10160 | 0 | RACK BACK HWDP & 2 STDS-6.5'' DC, REMOVE MWD TOOL. DRAIN MOTOR AND BREAK OUT BIT. MOTOR: DRAINED WELL WITH MINIMAL SLACK. BIT:1-1-WT-S-1-2-LT-TD NOTE: FLOW CHECK PRIOR TO BHA ENTERING BOP. RESULT: WELL STATIC. NOTE: L/D DIRTY MOTOR AND P/U NEW MOTOR IN PREPERATION FOR THE NEXT WELL.
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 13:15 | 2022-02-08 13:30 | 0.25 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 2.91 | 10160 | 10160 | 0 | CLEAN RIG FLOOR AND REMOVE WEAR BUSHING
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 13:30 | 2022-02-08 14:30 | 1 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 2.95 | 10160 | 10160 | 0 | CHANGE OUT TOP VBR'S TO 7.625'' CASING RAMS, PICK UP JOINT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1,500 PSI (TEST GOOD)
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 14:30 | 2022-02-08 15:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.97 | 10160 | 10160 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 15:00 | 2022-02-08 16:30 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.03 | 10160 | 10160 | 0 | HOLD PJSM; RIG UP FRANK'S CASING CREW
KLONDIKE RUSH H06 KL | 5 | 2022-02-08 16:30 | 2022-02-09 | 7.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.34 | 10160 | 10160 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN 7.625'' 29.7#P-110-IC BTC INTERMEDIATE CASING F/89.05'-T/10,148'. FILL PIPE OF THE FLY, HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK. RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7.625" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 226 JTS OF 7.625" 29.7# P-110 IC BTC CSG, 1-14.8' PUP JOINT, THEN 1- FULL JT FOR A TOTAL OF 230 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 44 LATCH ON BOW SPRING CENTRALIZERS @ 9,838.2' AND EVERY 4TH JT UP TO 2,298.5'. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/214K (W/O BLOCKS) SHOE- 10,148' TOP OF FLOAT COLLAR-10,059'. 15 FULL JOINTS LEFT OUT- 661.04', 1-15' PUP JT LEFT OUT-14.80' 2-10' PUP JT LEFT OUT-19.61'
KLONDIKE RUSH H06 KL | 5 | 2022-02-09 | 2022-02-09 01:00 | 1 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 3.39 | 10160 | 10160 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD. RIG MANAGER PRESENT
KLONDIKE RUSH H06 KL | 5 | 2022-02-09 01:00 | 2022-02-09 02:45 | 1.75 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 3.46 | 10160 | 10160 | 0 | CIRCULATE 1.5X CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE CONT. TO RIG DOWN CASING TOOLS, SPM: 105, 8.0 BPM, SPP:550 PSI, NO LOSSES.
KLONDIKE RUSH H06 KL | 5 | 2022-02-09 02:45 | 2022-02-09 06:00 | 3.25 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.59 | 10160 | 10160 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4,500 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.0 PPG SPACER. 312 BBL 11.8 PPG 870 SK 2.01 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 77 BBL 16.2 PPG 300 SK 1.44 YIELD CLASS H TAIL CEMENT. NOTE: SWAPPED OVER TO 2ND PUMP TRUCK @ 150BBLS GONE OF LEAD, DUE TO TRUCK LOSING PRIME. NOTE: COMPLETE CEMENT JOB AND REPORT ON FOLLOWING REPORT.
KLONDIKE RUSH H06 KL | 6 | 2022-02-09 06:00 | 2022-02-09 07:30 | 1.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.66 | 10160 | 10160 | 0 | CONT INTERMEDIATE CEMENT OPS. CEMENT JOB AS FOLLOWS: SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4,500 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.0 PPG SPACER. 312 BBL 11.8 PPG 870 SK 2.01 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 77 BBL 16.2 PPG 300 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPANY REP WITNESS PLUG DROP, DISPLACE WITH 462 BBLS OF 9.7 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1,735 PSI AT 4 BPM, DID NOT BUMP PLUG: PUMPED 2 BBLS OVER DISPLACEMENT (1/2 OF THE SHOE TRACK), BLED BACK 3.5 BBLS FLOATS HELD. RIG DOWN CMT CREW. NOTE: CEMENT W/ FULL RETURNS WHILE PUMPING CEMENT. 40 BBLS OF SPACER TO SURFACE. NOTE: SWAPPED OVER TO 2ND PUMP TRUCK @ 150BBLS GONE OF LEAD, DUE TO TRUCK LOSING PRIME AND BEING ABLE TO THROTTLE UP (PUMP TRUCK #1- PSI:50, RATE:6BPM. PUMP TRUCK #2- PSI:312, RATE: 6 BPM). NOTE: AFTER RELEASING PLUG, PUMPED 5 BBLS OF DISPLACEMENT, SHUT DOWN AND REMOVE CAP ON CMT HEAD TO VERIFY PLUG GONE. DUE TO TATTLE TAIL HOLE BEING PACKED-OFF AND UNABLE TO RUN TATTLE TAIL WIRE. EST TOC: 261'
KLONDIKE RUSH H06 KL | 6 | 2022-02-09 07:30 | 2022-02-09 09:15 | 1.75 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 3.73 | 10160 | 10160 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, FLUSH THROUGH BOP'S AND FLOW LINE, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
KLONDIKE RUSH H06 KL | 6 | 2022-02-09 09:15 | 2022-02-09 10:30 | 1.25 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 3.78 | 10160 | 10160 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL, CLOSE CASING VALVE.
KLONDIKE RUSH H06 KL | 6 | 2022-02-09 10:30 | 2022-02-09 10:30 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 3.78 | 10160 | 10160 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 2-9-22 @ 10:30
KLONDIKE RUSH H06 KL | 7 | 2022-03-10 18:00 | 2022-03-10 19:00 | 1 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 3.82 | 10160 | 10160 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK 20' FROM KLONDIKE TRAIL H04 KL T/KLONDIKE RUSH H06 KL, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN. NOTE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE.
KLONDIKE RUSH H06 KL | 7 | 2022-03-10 18:00 | 2022-03-10 18:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 3.78 | 10160 | 10160 |  | MILESTONE_RESUME WELL 1 ON 3/10/22 @ 18:00
KLONDIKE RUSH H06 KL | 7 | 2022-03-10 19:00 | 2022-03-10 20:30 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 3.89 | 10160 | 10160 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
KLONDIKE RUSH H06 KL | 7 | 2022-03-10 20:30 | 2022-03-11 00:30 | 4 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.05 | 10160 | 10160 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. RIG DOWN TEST EQUIPMENT. VERIFY STACK AND CHOKE ALIGNMENT.
KLONDIKE RUSH H06 KL | 7 | 2022-03-11 00:30 | 2022-03-11 01:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.07 | 10160 | 10160 | 0 | TEST CSG TO 3,500 PSI FOR 30 MIN. TEST RESULTS=GOOD TEST.
KLONDIKE RUSH H06 KL | 7 | 2022-03-11 01:00 | 2022-03-11 01:30 | 0.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.09 | 10160 | 10160 | 0 | REMOVE TEST PLUG AND INSTALL WEAR BUSHING & TRIP NIPPLE
KLONDIKE RUSH H06 KL | 7 | 2022-03-11 01:30 | 2022-03-11 01:45 | 0.25 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.1 | 10160 | 10160 | 0 | TROUBLESHOOT RIG BLACKOUT, GENERATOR AND AIR COMPRESSORS.
KLONDIKE RUSH H06 KL | 7 | 2022-03-11 01:45 | 2022-03-11 02:00 | 0.25 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.11 | 10160 | 10160 | 0 | ACCUMULATOR DRAWDOWN TEST. RESULT=GOOD TEST
KLONDIKE RUSH H06 KL | 7 | 2022-03-11 02:00 | 2022-03-11 04:15 | 2.25 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.21 | 10160 | 10160 | 0 | PJSM. PICK UP DIR BHA #4: 6.75" SECURITY GTD64M SN:13711499 JETS 6X18 TFA: 1.491), MOTOR: 5.5", 6/7 8.8 2.12 TS HS88 .000, .68 REV/GAL; 4.04' BIT TO BEND; 5.50" PAD OD; FLOW RANGE-150/400 GPM; MAX DIFF-900 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5'' UBHO, 5" NMDC, 5'' NMPC, 5",NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 28 STANDS DP, AGITATOR. BIT TO SVY-68'. BIT TO GAMMA-55'. NOTE: TEST MWD TOOL WITHOUT BIT ON MOTOR. RESULT: GOOD TEST
KLONDIKE RUSH H06 KL | 7 | 2022-03-11 04:15 | 2022-03-11 06:00 | 1.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.28 | 10160 | 10160 | 0 | TIH W/BHA #3 F/BHA'-T/3,500' HOLE GIVING PROPER DISPLACEMENT. NOTE:FILLED PIPE & FLOW TESTED DRILL STRING, PICKED UP AGITATOR AND FLOW TESTED @ 2,802'. SPP BEFORE: 1,350 PSI, SPP AFTER: 1,685 PSI @ 262 GPM.
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 06:00 | 2022-03-11 07:00 | 1 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.32 | 10160 | 10160 | 0 | TIH W/BHA #3 F/3,500'-T/6,767' HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK.
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 07:00 | 2022-03-11 08:30 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 4.39 | 10160 | 10160 | 0 | SLIP AND CUT 90' OF DRILLING LINE. RIG MANAGER PRESENT
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 08:30 | 2022-03-11 09:45 | 1.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.44 | 10160 | 10160 | 0 | CONT. TIH W/BHA #3 F/6,767'-T/10,000' HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK. NOTE: @ 7,200' HOLE STARTED TO DRAG (F/150K-T/125K) AND IMPROPER DISPLACEMENT VISUALISED. SLOWED DOWN ON TRIP SPEED AND SET BRIDGE PROTECTION LOWER, DUE TO SUSPECTED PLUG BEING PUSHED DOWN WHILE TIH. AS A RESULT, DISPLACEMENT BECAME NORMAL.
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 09:45 | 2022-03-11 10:45 | 1 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 4.48 | 10160 | 10160 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD. FILL PIPE AND FILL GAS BUSTER. NOTE: PERFORM BOP DRILL WITH CREWS.
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 10:45 | 2022-03-11 11:45 | 1 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 4.52 | 10160 | 10170 | 10 | DRILL SHOE TRACK AND 10' NEW FORMATION F/10,000'- T/10,170', WOB-10K, RPM-30, GPM-300, SPP: 2600, PSI, TQ-4/6K. TAG FLOAT @10,059'' TAG SHOE @ 10,148'
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 11:45 | 2022-03-11 12:15 | 0.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 4.54 | 10170 | 10170 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T GPM-300, SPP-2,650 PSI, RPM-30. MW IN: 8.9 PPG MW OUT: 8.9 PPG
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 12:15 | 2022-03-11 12:45 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 4.56 | 10170 | 10170 | 0 | PERFORM F.I.T. WITH 8.9 PPG OBM, 2,160 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,148' / TVD-10,131'
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 12:45 | 2022-03-11 20:45 | 8 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.9 | 10170 | 10918 | 93.5 | BUILD CURVE-SLIDE (748' IN 7.93 HR @ 94.32 FPH) WOB-20/30K, SPM-76/76, GPM 400, MRPM:272, SPP:3,200-3,550 PSI, DIFF:350/550 PSI, CHOKES:100% /100%, FLARE-1-3', NO MUD CUT, MAX CASING PRESSURE=45 PSI, AVG CASING PRESSURE= 0 PSI. MAX SICP=0 PSI, AVG SICP: 0 PSI SLIDE DEPTHS: F/10,170'-T/10,255', 85', TF:HS, 11:45-13:55 F/10,255'-T/10,348', 93', TF:30L, 13:55-15:29 F/10,377'-T/10,445', 68', TF:30L, 16:00-16:37 F/10,465'-T/10,539', 74, TF:10L, 17:01-17:38 F/10,566'-T/10,634', 68', TF:HS, 18:08-18:44 F/10,649'-T/11,009', 360', TF:HS, 18:53-22:15
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 12:45 | 2022-03-11 12:45 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 4.56 | 10170 | 10170 |  | MILESTONE_START CURVE SECTION 03/11/22 @ 12:45
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 20:45 | 2022-03-11 22:15 | 1.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.96 | 10918 | 11009 | 60.7 | BUILD CURVE-ROTATE (91' IN 1.57 HRS @ 57.96 FPH) WOB-15/20K, SPM-76/76, GPM-400, RPM-30, MRPM-272, TRPM-302, SPP-3,800/4,400 PSI, DIFF-600/700 PSI, CHOKES- 100% /100%, FLARE:1-4', NO MUD CUT, MAX CASING PRESSURE= 45 PSI, AVG CASING=0 PSI, MAX SICP=0 PSI, AVG SICP: 0 PSI. SHUTTING IN ON CONNECTIONS
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 22:15 | 2022-03-11 22:15 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 4.96 | 11009 | 11009 |  | MILESTONE_LAND/END CURVE SECTION ON 3/11/2022 @ 22:15 (11,009' MD / 10,682.4' TVD)
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 22:15 | 2022-03-11 22:15 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 4.96 | 11009 | 11009 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 3/11/2022 @ 22:15 (11,009' MD /10,682.4' TVD)
KLONDIKE RUSH H06 KL | 8 | 2022-03-11 22:15 | 2022-03-12 01:00 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.07 | 11009 | 11544 | 194.5 | DRILL LATERAL-ROTATE (535' IN 2.77 HRS @ 193.14 FPH) WOB-15/20K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, SPP-3600-4600 PSI, DIFF-900/1,000 PSI, CHOKES- 100% / 100%, FLARE- 1-4', NO MUD CUT, MAX CASING PRESSURE: 0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP:0 MW: 8.8 NOTE: PUMP HIGH VIS SWEEP AS NEEDED
KLONDIKE RUSH H06 KL | 8 | 2022-03-12 01:00 | 2022-03-12 01:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.09 | 11544 | 11574 | 60 | DRILL LATERAL-SLIDE (30' IN 0.48 HR @ 62.5 FPH) WOB-30/35K, SPM-76/76, GPM-400, MRPM-272, SPP3600-4300 PSI, DIFF-300/500 PSI, CHOKES-100% /100%,FLARE-1-4', NO MUD CUT. MAX CASING PRESSURE: 0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP:0 SLIDE DEPTHS: F/11,208'-T/11,223', 15', TF:30R, 23:23-23:35, RPM:35, TQ:4R/2L F/11,401'-T/11,416', 15', TF:40R, 00:28-00:45, RPM:35, TQ:4R/2L
KLONDIKE RUSH H06 KL | 8 | 2022-03-12 01:30 | 2022-03-12 02:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.11 | 11574 | 11574 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT SICP: 0 PSI
KLONDIKE RUSH H06 KL | 8 | 2022-03-12 02:00 | 2022-03-12 04:45 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.23 | 11574 | 12167 | 215.6 | DRILL LATERAL-ROTATE (593' IN 2.88 HRS @ 205.90 FPH) WOB-15/20K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, SPP-3600-4700 PSI, DIFF-900/1,000 PSI, CHOKES- 100% / 100%, FLARE- 1-4', NO MUD CUT, MAX CASING PRESSURE: 0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 0 PSI MW: 8.9 NOTE: PUMP 10 BBLS OF PROCOR LCM SWEEP AS NEEDED. SWEEP RECIPE: 15PPB PREVENTATIVE. 65 BBLS OF OBM, 16SX OF SB SUPERCEAL (5PPB), 32SX OF PRO V+ (10PPB)
KLONDIKE RUSH H06 KL | 8 | 2022-03-12 04:45 | 2022-03-12 06:00 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.28 | 12167 | 12237 | 56 | DRILL LATERAL-SLIDE (70' IN 1.12 HR @ 62.5 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, SPP-3600-4500 PSI, DIFF-300/500 PSI, CHOKES-100% /100%, FLARE-1-4', NO MUD CUT. MAX CASING PRESSURE: 0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 0 PSI SLIDE DEPTHS: F/11,586'-T/11,601', 15', TF:40R, 02:07-02:20, RPM:35, TQ:4R/3L F/11,680'-T/11,700', 20', TF:130R, 02:48-03:03, RPM:50, TQ:4R/3L F/11,774'-T/11,789', 15', TF:180, 03:28-03:38, RPM:50, TQ:4R/3L F/11,814'-T/11,824', 10', TF:180, 03:47-04:05, RPM:50, TQ:4R/3L F/11,869'-T/11,879', 10, TF:180, 04:16-04:27, RPM:50, TQ:4R/3L
KLONDIKE RUSH H06 KL | 9 | 2022-03-12 06:00 | 2022-03-12 13:45 | 7.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.6 | 12237 | 13724 | 191.9 | DRILL LATERAL-ROTATE (1,487' IN 7.88 HRS @ 188 FPH) WOB-15/20K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, SPP-3600-4700 PSI, DIFF-900/1,000 PSI, CHOKES- 100% / 100%, FLARE- 1-4', NO MUD CUT, MAX CASING PRESSURE: 52 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 0 PSI MW: 8.9 PPG NOTE: PUMP 10 BBLS OF PROCOR LCM SWEEP AS NEEDED. SWEEP RECIPE: 15PPB PREVENTATIVE. 65 BBLS OF OBM, 16SX OF SB SUPERCEAL (5PPB), 32SX OF PRO V+ (10PPB) NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 15:05 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 13,669', Target Line: 10,690' TVD @ 0' VS @ INC: 87.2° - Window: 0' Above / 10' Below
KLONDIKE RUSH H06 KL | 9 | 2022-03-12 13:45 | 2022-03-12 17:00 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.74 | 13724 | 13930 | 63.4 | DRILL LATERAL-SLIDE (206' IN 3.12 HR @ 66 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, SPP-3600-4500 PSI, DIFF-300/500 PSI, CHOKES-100% /100%, FLARE-1-4', NO MUD CUT. MAX CASING PRESSURE: 52 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 0 PSI SLIDE DEPTHS: SLD F/12252' T/12272' 20' TF-180 06:03-06:18 RPM-50 TQ- 4R/2L SLD F/12338' T/12353' 15' TF-180 06:47-06:58 RPM-50 TQ- 4R/2L SLD F/12431' T/12446' 15' TF-160L 07:24-07:38 RPM-50 TQ- 4R/2L SLD F/12525' T/12540' 15' TF-150L 08:03-08:15 RPM-55 TQ- 4R/2L SLD F/12810' T/12822' 12' TF-110L 09:35-09:46 RPM-55 TQ- 4R/2L SLD F/12904' T/12919' 15' TF-160L 10:12-10:23 RPM-55 TQ- 4R/2L SLD F/13094' T/13111' 17' TF-160R 11:15-11:33 RPM-60 TQ- 4R/2L SLD F/13189' T/13201' 12' TF-180 11:58-12:10 RPM-60 TQ- 4R/2L SLD F/13283' T/13295' 12' TF-180 12:37-12:50 RPM-60 TQ- 4R/2L SLD F/13564' T/13584' 20' TF-150R 14:08-14:30 RPM-70 TQ- 4R/2L SLD F/13657' T/13677' 20' TF-150R 15:00-15:18 RPM-75 TQ- 5R/3L SLD F/13747' T/13768' 21' TF-150R 15:44-16:01 RPM-75 TQ-5R/3L SLD F/13846' T/13858' 12' TF-180 16:28-16:41 RPM-75 TQ-5R/3L
KLONDIKE RUSH H06 KL | 9 | 2022-03-12 17:00 | 2022-03-12 17:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.76 | 13930 | 13930 | 0 | RIG SERVICE. LUBE: TD, ST-80 AND DRWKS RIG MANAGER PRESENT
KLONDIKE RUSH H06 KL | 9 | 2022-03-12 17:30 | 2022-03-13 03:45 | 10.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.19 | 13930 | 15737 | 176.3 | DRILL LATERAL-ROTATE (1,807' IN 10.35 HRS @ 174.58 FPH) WOB-15/20K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, SPP-4,400-5,100 PSI, DIFF-900/1,000 PSI, CHOKES- 100% / 100%, FLARE- 3-10', NO MUD CUT, MAX CASING PRESSURE: 0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 85 PSI MW: 9.0 NOTE: PUMPED 15BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300' OR AS NEEDED. NOTE: WINDOW CHANGE RECEIVED VIA TEXT @18:22 HOURS. Target Line: 10,710' TVD @ 0' VS @ INC: 87.2° - Window: 5' Above / 5' Below
KLONDIKE RUSH H06 KL | 9 | 2022-03-13 03:45 | 2022-03-13 06:00 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.28 | 15737 | 15875 | 61.3 | DRILL LATERAL-SLIDE (138' IN 2.15 HR @ 64.18 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, SPP-3600-4800 PSI, DIFF-300/530 PSI, CHOKES-100% /100%, FLARE-3-10', NO MUD CUT. MAX CASING PRESSURE: 0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 85 PSI SLIDE DEPTHS: F/14,140'-T/14,155' 15', TF:180, 18:32-18:46, RPM:50, TQ:7R/5L F/14,610'-T/14,618', 8', TF:HS, 20:57-21:05, RPM:70, TQ:7R/5L F/14,700'-T/14,710', 10', TF:HS, 21:35-21:45, RPM:70, TQ:7R/5L F/14,876'-T/14,896', 20', TF:180, 22:38-22:54, RPM:70, TQ:7R/5L F/14,934'-T/14,944', 10', TF:180, 23:05-23:12, RPM:70, TQ:7R/5L F/14,976'-T/14,991', 15', TF:130R, 23:31-23:47, RPM:80, 8R/6L F/15,170'-T/15,185', 15', TF:180, 00:37-00:50, RPM:80, 8R/6L F/15,356'-T/15,371', 15', TF:180, 01:43-0200, RPM:80, 8R/6L F/15,639'-T/15,654', 15', TF:130L, 04:22-04:37, RPM:80, 8R/5L F/15,733'-T/15,748', 15', TF:130L, 05:04-05:20, RPM:80, 8R/5L
KLONDIKE RUSH H06 KL | 10 | 2022-03-13 06:00 | 2022-03-13 14:00 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.61 | 15875 | 17183 | 163.5 | DRILL LATERAL-ROTATE (1,308' IN 7.90 HRS @ 166 FPH) WOB-20/25K, SPM-76/76, GPM-400, RPM-70, MRPM-272, TRPM-342, SPP-4,400-5,300 PSI, DIFF-900/1,000 PSI, CHOKES- 0% / 100%, FLARE- 3-10', NO MUD CUT, MAX CASING PRESSURE: 65 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 565 PSI MW: 9.1 NOTE: PUMPED 15BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300' OR AS NEEDED.
KLONDIKE RUSH H06 KL | 10 | 2022-03-13 14:00 | 2022-03-13 17:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.74 | 17183 | 17322 | 46.3 | DRILL LATERAL-SLIDE 139' IN 3.10 HR @ 45 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3600-4800 PSI, DIFF-300/530 PSI, CHOKES-0% /100%, FLARE-3-10', NO MUD CUT SLIDE DEPTHS: SLD F/15920' T/15938' 18' TF-110L 06:14-06:36 RPM-80 TQ- 13R/10L SLD F/16109' T/16129' 20' TF-180 07:33-07:55 RPM-80 TQ- 13R/10L SLD F/16203' T/16215' 12' TF-180 08:23-08:40 RPM-80 TQ- 13R/10L SLD F/16486' T/16506' 20' TF-180 10:08-10:30 RPM-80 TQ- 13R/10L SLD F/16578' T/16590' 12' TF-180 10:59-11:19 RPM-80 TQ- 11R/9L SLD F/16769' T/16789' 20' TF-160R 12:18-12:45 RPM-80 TQ- 12R/10L SLD F/16958' T/16975' 17' TF-130R 14:00-14:25 RPM-80 TQ- 11R/11L SLD F/17238' T/17258' 20' TF-130R 16:12-16:43 RPM-80 TQ- 13R/10L
KLONDIKE RUSH H06 KL | 10 | 2022-03-13 17:00 | 2022-03-13 17:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.76 | 17322 | 17322 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND ST-80 RIG MANAGER PRESENT. SICP: 231 PSI
KLONDIKE RUSH H06 KL | 10 | 2022-03-13 17:30 | 2022-03-14 00:45 | 7.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.06 | 17322 | 18182 | 118.6 | DRILL LATERAL-ROTATE (860' IN 7.27 HRS @ 118.29 FPH) WOB-15/20K, SPM-72/72, GPM-375, RPM-70, MRPM-255, TRPM-325, SPP-3,900-4,650 PSI, DIFF-700/900 PSI, CHOKES- 100% / 100%, FLARE- 5-15', NO MUD CUT, MAX CASING PRESSURE: 210 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 185 PSI MW: 9.0 NOTE: PUMPED 15BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300' OR AS NEEDED. NOTE: DECREASE PUMP RATE T/375 GPM, IN EFFORT TO MINIMIZE LOSSES. NOTE: @ 18,217' PUMPED 41BBLS OF PROCOR SWEEP. SWEEP RECIPE: 15PPB PREVENTATIVE. 65 BBLS OF OBM, 16SX OF SB SUPERCEAL (5PPB), 32SX OF PRO V+ (10PPB). LOSSES=156 BPH. CONTACTED MANAGMENT. NOTE: CONTROL DRILL @ 120 FPH F/17,950'-T/18,217, AS A PRECAUTIONARY MEASURE. IN ANTICIPATION OF THE SIGNIFICANT STRUCTURE/FAULT BETWEEN 7,100'-8,300' VS PER GEOSTEERING. NOTE: @ 18,267' CUT MW F/9.0PPG-T/8.8 PPG TO HELP MINIMIZE LOSSES.
KLONDIKE RUSH H06 KL | 10 | 2022-03-14 00:45 | 2022-03-14 03:00 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.16 | 18182 | 18267 | 37.8 | DRILL LATERAL-SLIDE 85' IN 2.12 HR @ 40.09 FPH) WOB-20/25K, SPM-72/72, GPM-375, MRPM-255, SPP-3600-4,350 PSI, DIFF-300/530 PSI, CHOKES-100% /100%, FLARE-5-15', NO MUD CUT. MAX CASING PRESSURE: 210 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 185 PSI SLIDE DEPTHS: F/17,327'-T/17,342', 15', TF:150R, 17:44-18:00, RPM:80, TQ:13R/10L F/17,520'-T/17,540', 20', TF:180, 19:20-19:47, RPM:80, TQ:12R/10L F/17,711'-T/17,726', 15', TF:180, 20:52-21:12, RPM:80, TQ:15R/12L F/17,901'-T/17,916', 15', TF:180, 22:35-23:02, RPM:80, TQ:15R/12L F/18,084'-T/18,104', 20', TF:180, 00:33-01:10, RPM:80, TQ:15R/12L
KLONDIKE RUSH H06 KL | 10 | 2022-03-14 03:00 | 2022-03-14 03:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.18 | 18267 | 18361 | 188 | DRILL LATERAL-ROTATE (94' IN .65 HRS @ 146.87 FPH) WOB-15/20K, SPM-67/67, GPM-350, RPM-70, MRPM-238, TRPM-308, SPP-3,00-3,975 PSI, DIFF-700/900 PSI, CHOKES- 100% / 100%, FLARE- 5-15', NO MUD CUT, MAX CASING PRESSURE:0 PSI, AVG CASING: 0 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 120 PSI MW: 8.8 NOTE: DECREASE PUMP RATE T/350 GPM, IN EFFORT TO MINIMIZE LOSSES. LOSSES DECREASED F/156 BPH-T/136 BPH. NOTE: CONT. CONTROL DRILL @ 120 FPH F/18,267'-T/18,361', AS A PRECAUTIONARY MEASURE. IN ANTICIPATION OF THE SIGNIFICANT STRUCTURE/FAULT BETWEEN 7,100'-8,300' VS PER GEOSTEERING.
KLONDIKE RUSH H06 KL | 10 | 2022-03-14 03:30 | 2022-03-14 05:00 | 1.5 | U | PRDHLLT | LCIRC | LCIRC | LOST CIRCULATION | 7.24 | 18361 | 18361 | 0 | @ 18,361' PREP FOR MUD TANKS FOR "MUD CAP" DRILLING OPS: TRANSFER MUD FROM TANK 8 AND FILL WITH FRESH WATER. BEGIN TO DISPLACE DRILL STRING W/FW WHILE TRANSFERRING OBM FROM TANKS 5, 6 & 7. FILL TANK 5&6 WITH 17.0# KILL OBM. NOTE: THE FOLLOWING PARAMETERS WHILE PERFORMING THESE OPS. GPM: 375, SPP: 3,685, RPM: 70, TQ: 11-12K. NOTE: EST TTL OBM LOSS PRIOR TO INDUCING MUDCAP=190 BBLS. ONCE DRILL-STRING WAS DISPLACED WITH FRESH WATER, DECREASED PUMP RATE TO GPM:105 ON #3MP, SPP:1,585 PSI, RPM: 30, TQ: 10-12K AND CONTINUED PUMPING FRESH WATER. CLOSED BOTH CHOKES AND STARTED PUMPING 17 PPG KILL-MUD DOWN BACKSIDE VIA KILL-LINE @ GPM: 65 ON #1MP, KILL-LINE SPP: 775-810 PSI. (PUMPING FRESH WATER DOWN DRILL-STRING & KILL-MUD DOWN BACKSIDE SIMULTANEOUSLY TO INDUCE MUD CAP) MONITORING CSG PRESSURE. INITIAL CSG PRESSURE=0 PSI, MAX CSG PRESSURE=744 (W/17 BBLS PUMPED), FINAL CSG PRESSURE=0. TTL BBLS OF 17.0PPG KILL-MUD PUMPED TO INDUCE MUD CAP=91 BBLS.
KLONDIKE RUSH H06 KL | 10 | 2022-03-14 05:00 | 2022-03-14 05:45 | 0.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.27 | 18361 | 18478 | 156 | ROTATE DRILL LATERAL (117' IN .87 HR @ 134.48 FPH) WOB-30/40K, SPM-73/73, GPM-380, RPM-70, TQ-12K/14K, MRPM-258, TTRPM-328, SPP- 3,600/4,585 PSI, DIFF- 700/950 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 320 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 108 PSI. *DRILLING UNDER MUDCAP*
KLONDIKE RUSH H06 KL | 10 | 2022-03-14 05:45 | 2022-03-14 06:00 | 0.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.28 | 18478 | 18488 | 40 | SLD DRILL LATERAL (10' IN .13 HRS 76.92 FPH) WOB-20/30K, SPM-73/73, GPM-380 PSI, MRPM-258, SPP-3,200/3,500 PSI, DIFF- 200/400 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. SLIDE DEPTH: F/18,473'-T/18,483', 10', TF:180, 05:42-05:50, RPM:80, TQ:11R/9L *DRILLING UNDER MUDCAP*
KLONDIKE RUSH H06 KL | 11 | 2022-03-14 06:00 | 2022-03-14 06:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.3 | 18488 | 18549 | 122 | ROTATE DRILL LATERAL (61' IN .5 HR @ 122 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-70, TQ-12K/14K, MRPM-272, TTRPM-342, SPP- 700/1300 PSI, DIFF- 700/950 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. *DRILLING UNDER MUDCAP* NOTE: ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMP 10-12 BBLS OF PHPA SWEEP, EVERY 200' OR AS NEEDED. (SWEEP CONSISTING OF 2.5 PPB PHPA AND DRILL WATER.)
KLONDIKE RUSH H06 KL | 11 | 2022-03-14 06:30 | 2022-03-14 07:30 | 1 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 7.34 | 18549 | 18549 | 0 | TROUBLE SHOOT MWD. RECYCLE PUMPS MULTIPLE TIMES IN ATTEMPT TO RETRIEVE SURVEY. DUE TO THE HOLE BEING ON A VACUUM. ONCE WAITING 15 MINS FROM "PUMPS DOWN" BROUGHT MPS UP TO 100/100 SPM, MONITORING SPP. ONCE SPP WAS GAINED, DECREASED RATE TO 76/76.
KLONDIKE RUSH H06 KL | 11 | 2022-03-14 07:30 | 2022-03-14 20:00 | 12.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.86 | 18549 | 19825 | 102.1 | ROTATE DRILL LATERAL (1,276' IN 12.2 HR @ 104.59 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-70, TQ-12K/14K, MRPM-272, TTRPM-342, SPP- 3,000/3750 PSI, DIFF- 500/750 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 340 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 340 PSI. *DRILLING UNDER MUDCAP* NOTE: AFTER MAKING THE CONNECTION, PUMPS REMAIN DOWN FOR 15 MINS TO RETRIEVE SURVEY. NOTE: ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMP 10-12 BBLS OF PHPA SWEEP, EVERY 200' OR AS NEEDED. (SWEEP CONSISTING OF 2.5 PPB PHPA AND DRILL WATER.) NOTE: @ 19,210' WELL WAS NOT ON VACUUM ANYMORE AND WERE ABLE TO PUMP UP SURVEYS NORMALLY
KLONDIKE RUSH H06 KL | 11 | 2022-03-14 20:00 | 2022-03-15 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.03 | 19825 | 19983 | 39.5 | SLD DRILL LATERAL (158' IN 3.8 HRS 41.57 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP-2,800/3,155 PSI, DIFF- 200/400 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. SLIDE DEPTH: F/18,561'-T/18,578', 17', TF:180, 07:41-07:58, RPM:80, TQ:10R/9L F/18,655'-T/18,672', 17', TF:160L, 09:02-09:23, RPM:80, TQ:10R/9L F/18,844'-T/18,859', 15', TF:180, 11:12-11:31, RPM:80, TQ:11R/8L F/19,035'-T/19,052', 17', TF:180, 13:37-14:04, RPM:80, TQ:11R/9L F/19,221'-T/19,236', 15', TF:180, 15:44-16:07, RPM:80, TQ:11R/9L F/19,315'-T/19,332', 17', TF:180, 16:49-17:12, RPM:80, TQ:11R/9L F/19,596'-T/19,616', 20', TF:180, 19:11-19:43, RPM:80, TQ:17R/15L F/19,691'-T/19,711', 20', TF:180, 20:20-20:50, RPM:80, TQ:17R/15L F/19,790'-T/19,810', 20', TF:180, 21:38-22:14, RPM:80, TQ:17R/15L *DRILLING UNDER MUDCAP* NOTE: PUMPED 84 BBLS OF 16.9 PPG OBM DOWN ANNULUS @ 19,082' WHILE PUMPING DRILL WATER DOWN DRILL STRING. INITIAL SICP=346 PSI, FINAL SICP= 0 PSI NOTE: NEW TARGET RECEIVED VIA TEXT @ 16:00 @ MD: 19,234'; NEW TARGET LINE: 10,805; TVD (VS=0) @ 87.8° INC., 5' ABOVE/5' BELOW
KLONDIKE RUSH H06 KL | 11 | 2022-03-15 | 2022-03-15 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 8.03 | 19983 | 19983 |  | MILESTONE_TD WELL ON 03/15/2022 @ 00:00 HRS MD: 19,983'/TVD: 11,163'
KLONDIKE RUSH H06 KL | 11 | 2022-03-15 | 2022-03-15 02:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.11 | 19983 | 19983 | 0 | PERFORMED CLEAN UP CYCLE WITH WELL ON MUD CAP. PUMPED 2-30 BBL HIGH VIS SWEEPS CIRCULATE 3 BOTTOMS UP TO LOSS ZONE, SPM-76/76, GPM-400, MRPM-272, RPM-70, CHOKES CLOSED. MAX CSG PSI WHILE CIRC-0 PSI. TQ=11/15K, SPP-3750 PSI NOTE: PRIOR TO COMPLETING CLEAN-UP CYCLE, OPENED 1 CHOKE @ 20% TO VENT GAS. RESULT= 8' FLARE FOR APPROX 10 MIN THEN DEPLETED TO 0'. EMPLOYEE AT SHAKERS VERIFYING NO RETURNS (EMPLOYEE WAS INSTRUCTED TO NOTIFY DRILLER IF MUD RETURNS WERE VISUALIZED, AND IF SO, CHOKES WERE TO IMMIDIATELY BE CLOSED.) NOTE: SERVICE RIG WHILE PERFORMING CIRC OPS
KLONDIKE RUSH H06 KL | 11 | 2022-03-15 02:00 | 2022-03-15 06:00 | 4 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.28 | 19983 | 19983 | 0 | BACK REAM OUT THE HOLE F/19,983' T/16,200’, SPM-76/76, GPM-400, RPM-70, MRPM-272, TMRPM-342, TRQ-9/16K, SPP-3,200/3,375 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI AVG CASING PRESSURE ON CONNECTIONS= 0 PSI NOTE: @ 17,395' SMALL WASHOUT ON THE PIN AND BOX CONNECTION. L/D BOTH JOINTS.
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 06:00 | 2022-03-15 07:30 | 1.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.34 | 19983 | 19983 | 0 | BACK REAM OUT THE HOLE F/16,200' T/15,000'’, SPM-76/76, GPM-400, RPM-70, MRPM-272, TMRPM-342, TRQ-9/16K, SPP-3,200/3,375 PSI. CHOKES CLOSED. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI AVG CASING PRESSURE ON CONNECTIONS= 0 PSI
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 07:30 | 2022-03-15 12:45 | 5.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 8.56 | 19983 | 19983 | 0 | STRIP OUT OF THE HOLE W/BHA#3 F/15,000'-T/445'. FILLING BACKSIDE WITH 10.1 PPG CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI NOTE: PIPE CAME DRY @ 9,500'. NOTE: L/D 1 JT TO CHANGE BREAKS.
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 12:45 | 2022-03-15 13:30 | 0.75 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 8.59 | 19983 | 19983 | 0 | @ 445' PUMP 20 BBLS OF 17.5 PPG OBM DOWN ANNULUS AS A PRECAUTIONARY MEASURE. PERFORM FLOW CHECK PRIOR TO REMOVAL OF ROTATING HEAD (NO FLOW); REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE.
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 13:30 | 2022-03-15 15:15 | 1.75 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 8.67 | 19983 | 19983 | 0 | POOH F/445' T/BHA. L/D DIR BHA: X/O, TOMAX THRUSTER, FILTER SUB AND TOP NMDC. PULL MWD, DRAIN MOTOR, BREAK BIT AND L/D REMAINING BHA. NOTE: MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG. BIT GRADED: 0-1-CT-S-X-0-WT-TD SICP: 0 PSI
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 15:15 | 2022-03-15 16:00 | 0.75 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 8.7 | 19983 | 19983 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4 1/2" ELEVATORS AND PREP FOR CSG OPS.
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 16:00 | 2022-03-15 16:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.72 | 19983 | 19983 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 16:30 | 2022-03-15 18:30 | 2 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 8.8 | 19983 | 19983 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT. SICP: 0 PSI
KLONDIKE RUSH H06 KL | 12 | 2022-03-15 18:30 | 2022-03-16 02:45 | 8.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.15 | 19983 | 19983 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICYWEDGE 425 CASING, 2 JTS 5" 18# P110 ICYWEDGE 425 CASING AND TEST FLOAT EQUIPMENT. RAN 5" 18# P110 ICY WEDGE 425 CASING T/10,299.76'. NOTE: FILLING PIPE ON THE FLY WITH FRESH WATER. NO RETURNS. (CHOKES 0%/0%) CSG PRESSURE: 0 PSI NOTE: INSTALLED RT-HEAD @ 850'
KLONDIKE RUSH H06 KL | 12 | 2022-03-16 02:45 | 2022-03-16 03:15 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 9.17 | 19983 | 19983 | 0 | RIG DOWN 5" CRT AND ELEVATORS, RIG UP 5.5" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
KLONDIKE RUSH H06 KL | 12 | 2022-03-16 03:15 | 2022-03-16 06:00 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.28 | 19983 | 19983 | 0 | P/U AND RUN 1- X-OVER 425x463, 1 JOINT WEDGE 463, 1-5.5" MARKER JT AND RUN 5.5" 23# P-110 WEDGE 463 T/14,000'. FILLING PIPE ON THE FLY WITH FRESH WATER. NO RETURNS. (CHOKES 0%/0%) CSG PRESSURE: 0 PSI NOTE: TOPPED OFF PIPE, PRIOR TO PICKING UP X/O. NOTE: COMPLETE CSG BREAKDOWN ON FOLLOWING REPORT.
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 06:00 | 2022-03-16 09:15 | 3.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.42 | 19983 | 19983 | 0 | CONT. RUNNING 5.5'' 23# P-110 WEDGE 463 F/14,000'-T/18,252' WHILE STRIPPING IN WITH NO RETURNS, FILLING PIPE ON THE FLY; ENCOUNTERED TIGHT SPOT @ 18,252’; WASH AND REAM PRODUCTION CASING F/18,252' T/18,340' @ 10-20 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-5K/7K, SPM-70, GPM: 186, SPP-250 PSI, NO RETURNS, CHOKES CLOSED.
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 09:15 | 2022-03-16 12:00 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.53 | 19983 | 19983 | 0 | CONT. RUNNING 5.5'' 23# P-110 WEDGE 463 F/18,340'-T/19,789' WHILE STRIPPING IN WITH NO RETURNS, FILLING PIPE ON THE FLY; WASH AND REAM PRODUCTION CASING F/19,789' T/19,928' @ 10-20 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-13K/18K, SPM-100, BPM: 6, SPP-580 PSI, NO RETURNS, CHOKES CLOSED; REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD, SLACK OFF AND INSTALL ROTATING HEAD, OPEN ANNULAR, WASH AND REAM F/19,928’ T/19,968’, AND LAND ON HANGER W/190K (W/O BLOCKS) @ 19,968’. 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICYWEDGE 425 CASING, 2 JTS 5" 18# P110 ICYWEDGE 425 CASING AND TEST FLOAT EQUIPMENT. RAN 233 JTS OF 5" 18# P110 ICY WEDGE 425 CASING, 1- X-OVER 425x463, 1 JOINT WEDGE 463, 1-5.5" MARKER JT, RAN 223 JTS OF 5.5" 23# P-110 WEDGE 463. CASING SHOE @ 19,968' TOP OF FLOAT COLLAR @ 19,918.2' BTM OF TOE SLEEVE VALVE @ 19,873.9' TOP OF TOE SLEEVE VALVE @ 19,848.4' TOP OF X-OVER @ 9,665.5' TOP OF MARKER JT @ 9,601.9' LEFT OUT 7 JOINTS OF 5" -308.94' LEFT OUT 14 JOINTS OF 5.5"-600.98'
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 12:00 | 2022-03-16 13:00 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 9.57 | 19983 | 19983 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE, MONITOR SICP, SICP= 0 PSI
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 13:00 | 2022-03-16 15:00 | 2 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 9.66 | 19983 | 19983 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CHOKES CLOSED WHILE RIGGING DOWN CASING TOOLS. BPM: 8, GPM-336, SPP- 1620 PSI. INITIAL CSG PRESSURE WHILE CIRCULATING= 0 PSI FINAL CSG PRESSURE WHILE CIRCULATING= 114 PSI, SICP=110 PSI. LINED UP AND BULL HEADED 34 BBLS OF 17.5 PPG VIA KILL LINE DOWN BACKSIDE, CSG PRESSURE BROKE OVER @ 793 PSI WITH 4 BBLS PUMPED, MAX CSG PRESSURE=793 PSI, FINAL CSG PRESSURE= 135 PSI, SICP= 0 PSI. HOLD PJSM WITH NINE CEMENT CREW.
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 15:00 | 2022-03-16 18:45 | 3.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 9.81 | 19983 | 19983 | 0 | SWAP CIRCULATING IRON T/ CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI, CEMENTED 1ST STAGE 5/5.5" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 45 BBL 10.5 PPG WEIGHTED SPACER, 321 BBL 13.5 PPG 1060 SK 1.7 YIELD 35/65 POZ-CLASS H LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 388 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 8 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 1735 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2735 PSI, HELD FOR 5 MIN, BLED BACK 3.5 BBLS. FLOATS HELD. MAX CSG PSI= 0 PSI, AVG CASING PSI= 0 PSI, CSG PRESSURE 0 PSI WITH PUMPS OFF AFTER CEMENTING. NOTE: IMMEDIATELY AFTER VERIFYING THAT FLOATS HELD, LINED UP ON KILL-LINE, PUMPED 20 BBLS OF 10.3 PPG OBM AND CSG PRESSURE INCREASED T/366 PSI, STARTED PUMPING 17.5 PPG @ BPM: 4, KILL-LINE SPP: 1082 PSI, CSG PRESSURE: 780 PSI. BPM: 5, KILL-LINE SPP: 1365 PSI, CSG PRESSURE: 964 PSI. BPM: 6, KILL-LINE SPP: 1764 PSI, CSG PRESSURE: 1244 PSI. ONCE A TTL OF 100 BBLS WERE PUMPED CSG PRESSURE DECREASED T/837 PSI, SHUT DOWN THE PUMP TO MONITOR SICP. SICP FELL TO 0 PSI, TTL BBLS OF KILL MUD PUMPED= 100 BBLS; INITAIL SICP= 0 PSI, FINAL SICP=0, MAX SICP=1244 PSI..
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 18:45 | 2022-03-16 22:15 | 3.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 9.96 | 19983 | 19983 | 0 | HELD PJSM, R/U CMT LINE TO KILL-LINE, REMOVE CHECK VALVE AND TEST CMT LINE TO 8,000 PSI. PUMP 35 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 342 BBLS 1130 SK 1.7 YIELD 35/65 POZ-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 20 BBLS WATER. MAX CSG PSI= 1440 PSI W/160 BBLS OF LEAD CEMENT PUMPED @ 5 BPM, AVG CASING PSI= 600 PSI. MAX PUMP PRESSURE=1770 PSI @ 6 BPM. CSG PRESSURE DECREASED TO 0 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC-1,212'.
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 22:15 | 2022-03-16 23:15 | 1 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 10 | 19983 | 19983 | 0 | RIG DOWN CEMENT HEAD, CIRCULATING IRON AND FOSV WHILE MONITORING SICP, INITIAL SICP= 0 PSI, FINAL SICP= 0 PSI.
KLONDIKE RUSH H06 KL | 13 | 2022-03-16 23:15 | 2022-03-17 00:15 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 10.04 | 19983 | 19983 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE FOSV AND LAY DOWN LANDING JOINT. REMOVE BAILS AND CASING ELEVATORS, AND RIG UP RIG 4.5" ELEVATORS, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 80 GPM W/100 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACKOFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
KLONDIKE RUSH H06 KL | 13 | 2022-03-17 00:15 | 2022-03-17 01:30 | 1.25 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 10.09 | 19983 | 19983 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI.
KLONDIKE RUSH H06 KL | 13 | 2022-03-17 01:30 | 2022-03-17 01:30 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 10.09 | 19983 | 19983 |  | MILESTONE_TURN OVER TO COMPLETION ON 03/17/2022 @ 01:30
KLONDIKE RUSH H06 KL | 13 | 2022-03-17 01:30 | 2022-03-17 01:30 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 10.09 | 19983 | 19983 |  | MILESTONE_RIG RELEASE ON 03/17/2022 @ 01:30
KLONDIKE RUSH H06 KL | 13 | 2022-03-17 01:30 | 2022-03-17 01:30 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 10.09 | 19983 | 19983 |  | MILESTONE_WELL RELEASE ON 03/17/2022 @ 01:30
LEVI GOODRICH UNIT 2 2H | 2 | 2020-04-22 17:59 | 2020-04-22 17:59 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 4/22/2020 @ 18:00
LEVI GOODRICH UNIT 2 2H | 2 | 2020-04-22 17:59 | 2020-04-23 05:59 | 12 | P | MOBDMOB | LMOV | RDMO | RIG DOWN MOVE OUT | 0 | 108 | 108 | 0 | CONTINUE WASHING RIG AND RIGGING DOWN, PREPPINGTO MOVE RIG TO THE LEVI GOODRICH UNIT 2 2-H ,CONTINUE WASHING RIG AND RIGGING DOWN, RIG DOWN GEN PACKAGE AND VFD HOUSE, UNDRESS DERRICK, REMOVE CROWN, TOP AND MIDDLE SECTIONS OF DERRICK, LOAD AND MOVE MUD TANKS, MUD PUMPS, GAS BUSTER, BOP WRANGLER, DIESEL TANK, PUMP PARTS HOUSE, SUITCASES,VFD AND GEN PACKAGE, REMOVE DS DOGHOUSE, REMOVE DERRICK FROM RIG FLOOR, REMOVE DS DOGHOUSE, REMOVE DERRICK FROM RIG FLOOR,REMOVED DRAWWORKS, CENTER STEEL, GRASSHOPPER, ODS DOGHOUSE, BREAK SUBS APART AND PREP TO TRANSPORT.
LEVI GOODRICH UNIT 2 2H | 3 | 2020-04-23 06:00 | 2020-04-24 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | SPOTTED MUD TANKS & RIGGED UP SAME, SPOTTED MUD PUMPS, SUB MATS, SUITCASES, HOPPER HOUSE, WATER TANKS, VFD HOUSE, MOTOR PACKAGE, DIESEL TANK, FESTOON, CHOKE MAIFOLD, SPOTTED SUBS, RIGGED UP CENTER STEEL & CENTERED OVER HOLE, MOVED 4.5” DRILL PIPE & HANDLING TOOLS OFF OF THE AFFIRMED & BIG BEND PAD, SET ALL FRAC TANKS & PUMPS INTO PLACE, SPOTTED & RIGGED UP RIG CREWS CAMP HOUSES, UNLOADED RIG EQUIPMENT OFF OF TRUCKS 100% RIGGED DOWN, 95% MOVED, 35% RIGGED UP @ 06:00
LEVI GOODRICH UNIT 2 2H | 4 | 2020-04-24 06:00 | 2020-04-25 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | SET IN DRAWWORKS, ODS HOUSE, DRILLER'S CABIN, PINNED A SECTION TO SUBS,PINNED MIDDLE AND TOP SECTIONS OF DERRICK, INSTALLED MONKEY BOARD, PINNED BLOCKS TO TOP DRIVE, DRESSED OUT DERRICK, PERFORM PRE-RAISE INSPECTION, STRUNG UP DRAWORKS, RAISE DERRICK, RAISE SUB, SET CAMP HOUSES, SET GAS BUSTER, R/U ELECTRICAL ON RIG FLOOR, SET BOP, CATWALK, V-DOOR, DS AND ODS STAIRS, FLOWLINE, REMOVE BOOSTERS AND INSTALL STOMPERS, SET ACCUMULATOR. RIGGED UP HYDRAULIC HOSES ON DRAWWORKS, UNPINNED TOP DRIVE, TESTED PUMPS, TOP DRIVE, CHANGED OUT OIL IN TOP DRIVE
LEVI GOODRICH UNIT 2 2H | 5 | 2020-04-25 06:00 | 2020-04-26 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | RIG UP RIG, UNLOAD, CLEAN, AND TALLY SURFACE CASING; RIG UP MUD & WATER LINES FROM FRAC TANKS, FINISH PRE SPUD INSPECTION, PREP MUD TANKS AND FILL SAME WITH SPUD WATER; PREP RIG FLOOR AND LOCATION FOR SPUD IN; FINISH MODIFYING AND RIGGING UP MUD GAS SEPERATOR; INSTALL 2” KILL LINE ON MUD PUMPS FOR SIMULTANEOUS PUMPING. STRAP AND TALLY BHA, P/U AND RACK BACK 9 JOINTS (3 STANDS) OF HWDP IN DERRICK, STRAP 96 JOINTS OF 5" DP, P/U UP AND RACK BACK 32 STANDS OF 5" DP; INSTALL CONDUCTOR RISER, RIG UP CELLAR PUMPS, RUN LINES FROM CELLAR TO SHAKERS, INSTALL MOUSE HOLE. RIG MOVE COMPLETE @ 18:00 4/25/2020
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 06:00 | 2020-04-26 09:30 | 3.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | CONTINUE TO REPLACE (3) SHAKER BEDS AND INSTALL SHAKER MOTORS ALONG WITH OTHER ACCESSORIES. PICK UP JOINT OF 5" DP, WASH THROUGH LINES, SURFACE TEST STANDPIPE LINES AND HOSES TO 2,500 PSI AND HELD 15 MIN, L/D JT OF DP
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 09:30 | 2020-04-26 12:30 | 3 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | P/U ALL DIRECTIONAL TOOLS AND M/U BIT EXCLUDING MWD TOOL AND RACK BACK SAME. 7 3/4" 7/8 Lb 5.9 Stg @ 1.5° FBH W/ 13" NBS SER.# PPM800032 RPM = .166 Min/Max GPM - 400-900 Bit to Bend - 6.02' Pad OD = 13" Max Diff - 1330 psi Bit to Sensor = 76' MAX TRQ- 22,020 LBS/FT ULTERRA SPL 616 - 13 1\2" SN 49754 9x14's MWD Battery Ser #. 1417( New) 13" STABILIZER, PONY COLLAR, UBHO, NMDC, NMDC, 4 1\2 IF BOX B 6 5\8 REG PIN CROSSOVER
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 12:30 | 2020-04-26 13:30 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TD
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 13:30 | 2020-04-26 17:00 | 3.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | INSTALLED FLARE LINE AND FLARE STACK, FINISHED MODIFICATION OF RETURN LINE FROM MUD GAS SEPARATOR INTO SHALE SHAKERS DUE TO IMPROPER FIT, AFTER MODIFICATIONS RE-INSTALLED WITH CHERRY PICKER CRANE DUE TO FORKLIFT NOT BEING ABLE TO REACH. ORGANIZED AND PREPPED LOCATION FOR DRILLING OPERATIONS WHILE FINISHING INSTALLATION OF MUD GAS SEPARATOR
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 17:00 | 2020-04-26 17:30 | 0.5 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | FINISHED PICKING UP DIRECTIONAL BHA, INSTALLED MWD & SURFACE TESTED SAME
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 17:30 | 2020-04-27 | 6.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.27 | 108 | 2913 | 431.5 | ROTATE (2805' IN 6.68 HRS @ 420 FPH) WOB-15/30K, RPM-100, TRQ- 12/17K, SPM-100/100, GPM-800, MMRPM-133, TRPM-233, SPP-2000/2400 PSI, DIFF-500/900 PSI.
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-26 17:30 | 2020-04-26 17:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL 4/26/2020 @ 17:30
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-27 | 2020-04-27 01:30 | 1.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.33 | 2913 | 3000 | 58 | SLIDE (87' IN 1.32 HRS @ 66 FPH) WOB: 20/30K, SPM: 100/100 GPM: 800, MMRPM: 133, SPP- 1700/2000 PSI, DIFF- 200/400 PSI. SLIDE DEPTHS: SLD F/1623' T/1630' 7' TF-140M 21;00-21;11 SLD F/1725' T/1735' 10' TF-240M 21;28-21;34 SLD F/1820' T/1830' 10' TF-230M 21;47-21;58 SLD F/2104' T/2116' 12' TF-10L 22;42-23;00 SLD F/2290' T/2308' 18' TF-20L 23;20-23;31 SLD F/2469' T/2484' 15' TF-HS 23;55-00;07 SLD F/2567' T/2582' 15' TF-HS 00;20-00;30
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-27 01:30 | 2020-04-27 02:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.38 | 3000 | 3000 | 0 | PUMP 2-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-800, RPM-100, TRQ-3/5K, SPP-1700 PSI.
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-27 02:30 | 2020-04-27 05:00 | 2.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.48 | 3000 | 3000 | 0 | TRIP OUT OF HOLE F/3,000' T/ BHA, L/D TOP MONEL, REMOVE MWD TOOL, DRAIN MOTOR, RACK BHA BACK IN DERRICK, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
LEVI GOODRICH UNIT 2 2H | 6 | 2020-04-27 05:00 | 2020-04-27 06:00 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.52 | 3000 | 3000 | 0 | PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 06:00 | 2020-04-27 06:30 | 0.5 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.54 | 3000 | 3000 | 0 | PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 06:30 | 2020-04-27 09:30 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.67 | 3000 | 3000 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR,1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 73 JOINTS OF10 3/4" 45.5# J-55 T/2991', RAN 20 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY 4TH JT. ALL THE WAY TO 157.45', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 53" BELOW GROUND LEVEL. (WASH DOWN LANDING JOINT AND SET 80K ON BASE PLATE) SHOE: 2991' TOP OF FLOAT COLLAR: 2907' 7 JTS OUT - 283.76'
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 09:30 | 2020-04-27 10:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.71 | 3000 | 3000 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT @ 10 BPM WITH 375 PSI, RIG DOWN CASING TOOLS, NO LOSSES.
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 10:30 | 2020-04-27 11:00 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.73 | 3000 | 3000 | 0 | PJSM, RIG DOWN CRT
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 11:00 | 2020-04-27 12:30 | 1.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.73 | 3000 | 3000 | 0 | WALK RIG AND RIG UP CEMENT HEAD AND CIRCULATING IRON.
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 11:00 | 2020-04-27 11:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.73 | 3000 | 3000 |  | MILESTONE_HOLD WELL OPERATIONS 1 4/27/2020 @ 11:00
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 12:30 | 2020-04-27 15:30 | 3 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.73 | 3000 | 3000 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 30 BBL 8.3 PPG FRESH WATER SPACER, 322 BBLS 11.6 PPG LEAD CEMENT, 85 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 280 BBLS OF 9.5 PPG OIL BASE MUD. BUMPED PLUG W/ 800 PSI PRESSURED UP T/1300 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 30 BBLS OF SPACER AND 220 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 15:30 | 2020-04-27 16:00 | 0.5 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.73 | 3000 | 3000 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI (PRESSURE HELD TEST WAS GOOD)
LEVI GOODRICH UNIT 2 2H | 7 | 2020-04-27 16:00 | 2020-04-27 16:30 | 0.5 | R | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 0.73 | 3000 | 3000 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 06:00 | 2020-05-08 07:30 | 1.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.79 | 3000 | 3000 | 0 | PREPPED RIG TO WALK TO LEVI GOODRICH 2 2H, SWAP HYDRAULICS TO WALKING SYSTEM, WALK RIG, CENTERED AND LEVELED SUB OVER WELLHEAD, WITNESSED RIG CENTER OVER WELL.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 06:00 | 2020-05-08 06:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.73 | 3000 | 3000 | 0 | MILESTONE_RESUME WELL OPERATIONS 1 ON 5/8/2020 @ 06:00
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 07:30 | 2020-05-08 12:00 | 4.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.98 | 3000 | 3000 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, UNLATCHED BOP WRANGLER FROM BOP'S & LAID OVER SAME, INSTALLED TURNBUCKLES & CENTERED STACK. HOOK UP FLOWLINE. REMOVE CASING RAMS AND INSTALL VARIABLE RAMS, INSTALL VARIABLE RAMS IN LOWER RAMS, REMOVE KILL LINE CHECK VALVE, R/U KILL LINE.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 12:00 | 2020-05-08 14:30 | 2.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.08 | 3000 | 3000 | 0 | MAKE UP TEST PLUG TO JOINT DRILL PIPE AND SET, FILL STACK, TEST BOP 250L/5000H. TEST WH/BOP, TOP RAMS, KILL LINE, AND CHECK VALVE.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 14:30 | 2020-05-08 15:30 | 1 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.13 | 3000 | 3000 | 0 | RIG DOWN TESTERS, INSTALL WEAR BUSHING AND MOUSE HOLE.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 15:30 | 2020-05-08 16:00 | 0.5 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.15 | 3000 | 3000 | 0 | RIG SERVICE.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 16:00 | 2020-05-08 17:30 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.21 | 3000 | 3000 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S 3/16'S TFA: 1.491) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.12° SLICK; .166 REV/GAL; 5.72' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 8" UBHO, 2-8" NMDC,1- X/O, BIT TO SENSOR-71', TEST MWD ( GOOD TEST).
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 17:30 | 2020-05-08 20:30 | 3 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.33 | 3000 | 3000 | 0 | TRIP IN THE HOLE F/BHA T/2,908' -(P/U AGITATOR ON STAND 22) (BEFORE 650 PSI AFTER 760 PSI), REMOVE TRIP NIPPLE / INSTALL ROTATING HEAD. TRIP DRILL RESPONSE TIME-60 SECONDS
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 20:30 | 2020-05-08 21:00 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.35 | 3000 | 3010 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/ 3000' T/ 3010'. GPM-422, SPP-1200 PSI, RPM-50, DIFF-150 PSI
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 21:00 | 2020-05-08 21:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.38 | 3010 | 3010 | 0 | CIRCULATE BOTTOMS UP GPM-461, SPP-1480 PSI, RPM-40
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 21:30 | 2020-05-08 22:00 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.4 | 3010 | 3010 | 0 | PERFORM F.I.T.WITH 9.5 PPG MUD, 330 PSI SURFACE PRESSURE FOR 11.6 PPG EMW. SHOE MD-2,990' TVD-2,983'.
LEVI GOODRICH UNIT 2 2H | 8 | 2020-05-08 22:00 | 2020-05-09 06:00 | 8 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.73 | 3010 | 6159 | 393.6 | ROT (3149' IN 8 HRS @ 393 FPH) WOB: 35/45K, SPM: 102/102, GPM: 785, MMRPM: 130, RPM: 80, TRPM: 210, TRQ: 25K/40K, SPP: 3900/4800 PSI, DIFF: 800/1000 PSI. (SLIDE F/3,058' T/3,078', ,TF-20R, 20', 8 MIN)
LEVI GOODRICH UNIT 2 2H | 9 | 2020-05-09 06:00 | 2020-05-09 16:00 | 10 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.15 | 6159 | 9287 | 312.8 | ROT (3128' IN 10.07 HRS @ 310.6 FPH) WOB: 35/45K, SPM: 95/95, GPM: 730, MMRPM: 121, RPM: 80, TRPM: 201, TRQ: 12K/16K, SPP: 3800/4700 PSI, DIFF: 700/900 PSI.
LEVI GOODRICH UNIT 2 2H | 9 | 2020-05-09 16:00 | 2020-05-09 18:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.23 | 9287 | 9447 | 80 | SLIDE (160' IN 1.93 HRS @ 82.9 FPH) WOB: 15/30K, SPM: 95/95, GPM: 730, MMRPM: 121, SPP: 3800/4200 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: S.DRL F/6640' T/6655' @ 90L 0728-0741' 13MIN S.DRL F/6920' T/5934' @ 180 0848-0900 12MIN S.DRL F/7295' T/7315' @ 70MAG 1007-1020 13MIN S.DRL F/7860' T/ 7890' @ 150MAG 1157-1215 18MIN S.DRIL F/8515' T/8545' @ 80MAG 1409-1430 19MIN S.DRL F/8795' T/8825' @ 120MAG 1516-1537 21MIM S.DRL F/8989' T/9010' @ 110MAG 1612-1630 18MIN START INTERMEDIATE CURVE SECTION ON 5/9/20 @ 18:00 (9,447' MD / 9,402' TVD)
LEVI GOODRICH UNIT 2 2H | 9 | 2020-05-09 18:00 | 2020-05-09 21:00 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.35 | 9447 | 9975 | 176 | ROT (528' IN 3.12 HRS @ 169 FPH) WOB: 35/45K, SPM: 92/92, GPM: 708, MMRPM: 117, RPM: 80, TRPM: 197, TRQ: 15K/19K, SPP: 3800/4600 PSI, DIFF: 600/800 PSI.
LEVI GOODRICH UNIT 2 2H | 9 | 2020-05-09 21:00 | 2020-05-10 04:00 | 7 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.65 | 9975 | 10284 | 44.1 | SLIDE (309' IN 6.88 HRS @ 45 FPH) WOB: 15/30K, SPM: 97/97, GPM: 746, MMRPM: 124, SPP: 4200/4400 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: F/9447' T/9477'@ 325MAG 1804-1859 55MIN F/9634' T/9664'@ TF-HS 30' 1957-2030 33MIN F/9729' T/9759'@ 20R 30' 2053-2131 37MIN F/9823-T/9848,TF/10R,25'/27MIN 2153-2220 F/9917-T/9967,TF/HS,50'/58MIN 2243-2341 F/10012-T/10062,TF/HS,50'/25MIN 2357-0122 F/10106-T/10156,TF/HS,50'/39MIN 0136-0215 F/10240-T/10284,TF/HS,44'/80MIN 0246-0406
LEVI GOODRICH UNIT 2 2H | 9 | 2020-05-10 04:00 | 2020-05-10 05:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.71 | 10284 | 10284 | 0 | PUMP 2-30 BBL LCM SWEEP IN TANDEM, CIRCULATE BOTTOMS UP WHILE WORKING PIPE @ 770 GPM, SPP-4400, RPM-20, TQ-3500, FLOW CHECK WELL, WELL STATIC, PUMP SLUG.
LEVI GOODRICH UNIT 2 2H | 9 | 2020-05-10 05:30 | 2020-05-10 06:00 | 0.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.73 | 10284 | 10284 | 0 | TRIP OUT THE HOLE 10 STANDS DRILL PIPE, HOLE TAKING PROPER FILL.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 06:00 | 2020-05-10 07:00 | 1 | P | INTHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 2.77 | 10284 | 10284 | 0 | SAVER SUB BROKE LOOSE FROM TOP DRIVE. TORQUE AND INSTALL NEW COMPRESSION RING AND TIGHTEN CLAMPS.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 07:00 | 2020-05-10 10:00 | 3 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 2.9 | 10284 | 10284 | 0 | POOH T/9,316'. L/D DRILL PIPE F/9,316' T/6,640'. HOLE TAKING PROPER FILL.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 10:00 | 2020-05-10 10:30 | 0.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.92 | 10284 | 10284 | 0 | WHILE L/D DRILL PIPE CATWALK STARTED LIFTING UP V-DOOR, SHUT DOWN L/D DRILL PIPE, INSPECT CATWALK AND OBSERVED STRESS FRACTURE ON MAIN SUPPORT BEAM, WORK PIPE WHILE INSPECTING CATWALK. DECISION WAS MADE TO POOH RACKING BACK.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 10:30 | 2020-05-10 14:30 | 4 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.08 | 10284 | 10284 | 0 | CONTINUE POOH F/6,640' T/BHA, HOLE TAKING PROPER FILL, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 14:30 | 2020-05-10 16:00 | 1.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.15 | 10284 | 10284 | 0 | RACK BACK HWDP AND DRILL COLLARS, L/D TOP MONEL AND REMOVE MWD, DRAIN MOTOR, BREAK OUT BIT, RACK BACK BHA.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 16:00 | 2020-05-10 17:00 | 1 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.19 | 10284 | 10284 | 0 | REMOVE WEAR BUSHING & PREPPED RIG FLOOR FOR CASING RUN.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 17:00 | 2020-05-10 19:30 | 2.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.29 | 10284 | 10284 | 0 | REMOVE UPPER VARIABLE RAMS AND INSTALL 7-5/8" CASING RAMS, SET TEST PLUG AND TEST SAME.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 19:30 | 2020-05-10 21:30 | 2 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.38 | 10284 | 10284 | 0 | HELD PJSM, RIGGED UP EXPRESS ENERGY'S CASING CREW TOOLS, EQUIPMENT AND L/D TRUCK.
LEVI GOODRICH UNIT 2 2H | 10 | 2020-05-10 21:30 | 2020-05-11 06:00 | 8.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.73 | 10284 | 10284 | 0 | MAKE UP SHOE TRACK AND RUN INTERMEDIATE CASING T/8,899' HELD PJSM THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 228 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 44 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 2,890.67' . NOTE: CHANGED OUT 5 3/4" LINER TO 5 1/4" LINERS IN MUD PUMPS WHILE RUNNING CASING.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 06:00 | 2020-05-11 08:00 | 2 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.81 | 10284 | 10284 | 0 | CONTINUE RUNNING INTERMEDIATE CASING F/8,899', RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 228 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 44 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 2,890.67'. PICKED UP 1 EXTRA JT'S & 1 15' PUP JOINT, TAGGED BOTTOM AT 10284' MD, L/D 1 JT OF CSG & 1 15" PUP JOINT, P/U LANDING JOINT, LANDED CSG ON CSG MANDREL W/227K (W/O BLOCKS), SW-350K, S/O-270K, P/U-360K. FLOAT SHOE-10,273.75' TOP OF FLOAT COLLAR-10,180.21'. ONCE LANDED. ESTABLISHED RETURNS THRU CRT TOOL AND CIRC FOR 10 MIN.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 08:00 | 2020-05-11 08:30 | 0.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.83 | 10284 | 10284 | 0 | RIG DOWN EXPRESS CASING TOOLS AND EQUIPMENT.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 08:30 | 2020-05-11 09:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.88 | 10284 | 10284 | 0 | RIG UP NINE ENERGY CEMENT HEAD AND CIRCULATE WITH RIG PUMPS FULL CASING CAPACITY. GPM-323, SPP-500 PSI.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 09:30 | 2020-05-11 12:00 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.98 | 10284 | 10284 | 0 | CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG GTX SPACER. 287 BBL 11.8 PPG 830 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT. 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 468 BBLS OF 9.8 PPG OIL BASE MUD, @ 440 BBLS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 1810 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2310 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 4.5 BBLS. FLOATS HELD. PLUG DOWN @ 11:45 HRS 05/11/2020, GOT BACK 8 BBLS OF SPACER BACK TO SURFACE & HAD FULL RETURNS ENTIRE CEMENTING JOB.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 12:00 | 2020-05-11 12:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4 | 10284 | 10284 | 0 | PRESSURE TESTED CASING TO 3500 PSI F/15 MINUTES. (PRESSURE HELD & TEST WAS GOOD)
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 12:30 | 2020-05-11 13:00 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.02 | 10284 | 10284 | 0 | RIGGED DOWN CEMENTING EQUIPMENT, BROKE OUT & LAID DOWN LANDING JOINT, RIGGED DOWN CASING BAILS & ELEVATORS.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 13:00 | 2020-05-11 14:30 | 1.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.08 | 10284 | 10284 | 0 | MADE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP & MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 10K, BROKE OUT & LAID DOWN SETTING TOOL.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 14:30 | 2020-05-11 16:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.15 | 10284 | 10284 | 0 | REMOVE UPPER 7 5/8" CSG RAMS AND INSTALL VARIABLE RAMS.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 16:00 | 2020-05-11 19:30 | 3.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.29 | 10284 | 10284 | 0 | HELD PJSM WITH BIG SIX TESTERS, RIG UP TESTERS, FILL STACK WITH WATER AND TESTED WELLHEAD-(WOULD ONLY PRESSURE UP T/6,000 PSI) WHILE STREAMFLO CONTACTED SUPERVISOR-BEGAN TESTING STAND PIPE 250 LOW / 6000 HIGH, TESTED ALL CHOKE MANIFOLD VALVES, HCR, AND CHOKE INSIDE MANUAL. 250 LOW / 10,000 HIGH.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 19:30 | 2020-05-11 23:30 | 4 | U | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.46 | 10284 | 10284 | 0 | PJSM WITH STREAMFLO, LATCH BOP WRANGLER AND P/U STACK. C/O WELLHEAD O-RING AND RING GASKET. STAB BOP AND TORQUE SPEED HEAD. INSTALL TEST PLUG AND ATTEMPT TO TEST-FAILED. REMOVE TEST PLUG, RAISE BOP AND INSPECT SPEED HEAD AND WELLHEAD(FOUND WASH ON BOTH). STAB BOP.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-11 23:30 | 2020-05-12 01:00 | 1.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.52 | 10284 | 10284 | 0 | CHANGE OUT SAVER SUB FROM 4-1/2" IF TO DELTA 425
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-12 01:00 | 2020-05-12 03:00 | 2 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.6 | 10284 | 10284 | 0 | L/D DIRECTIONAL MOTOR AND BHA. L/D 2 STDS 6" DRILL COLLARS AND 9 HWDP.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-12 03:00 | 2020-05-12 04:30 | 1.5 | U | INTHLCSG | WLHD | RDWLHD | RIG DOWN WELLHEAD | 4.67 | 10284 | 10284 | 0 | RAISE BOP, REMOVE PACKOFF, WH ADAPTER FLANGE, REMOVE B-SECTION OF WELLHEAD, REMOVE BOP ADAPTER FLANGE.
LEVI GOODRICH UNIT 2 2H | 11 | 2020-05-12 04:30 | 2020-05-12 06:00 | 1.5 | U | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.73 | 10284 | 10284 | 0 | INSTALL NEW B-SECTION, INSTALL PACKOFF-TEST T/5K(GOOD), INSTALL WH ADAPTER FLANGE, INSTALL BOP ADAPTER FLANGE, SET BOP AND M/U TO ADAPTER FLANGE. TQ BOLTS AND RUN IN ADAPTER FLANGE SETTING SCREWS.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 06:00 | 2020-05-12 11:30 | 5.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.96 | 10284 | 10284 | 0 | TESTED BOPE: TEST BLIND RAMS, 5 1/2" VBR'S, 4 1/2" VBR'S, MUD CROSS, KILL LINE CHECK VALVE, MANUAL IBOP AND WELLHEAD 250 PSI LOW / 10,000 PSI HIGH, HYDRIL 250 LOW, 3500 HIGH, TEST KILL LINE BACK TO PUMPS 250 PSI LOW / 5,000 PIS HIGH, INSTALL ROTATING HEAD TEST CAP, TEST ORBIT VALVE 250 PIS LOW / 1,500 PSI HIGH. PULL TEST PLUG.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 11:30 | 2020-05-12 12:00 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.98 | 10284 | 10284 | 0 | RIG DOWN TESTING EQUIPMENT AND INSTALL WEAR BUSHING.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 12:00 | 2020-05-12 15:00 | 3 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.1 | 10284 | 10284 | 0 | L/D 2 STD OF HWDP AND 16 STDS 5" DRILL PIPE OUT THE MOUSE HOLE.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 15:00 | 2020-05-12 16:00 | 1 | U | INTHLCSG | WAIT | WOW | WAIT ON WEATHER | 5.15 | 10284 | 10284 | 0 | SHUT DOWN DUE SEVERE WEATHER AND LIGHTING STRIKES.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 16:00 | 2020-05-12 17:00 | 1 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.19 | 10284 | 10284 | 0 | CONTINUE L/D 4 STDS 5" DRILL PIPE OUT THE MOUSE HOLE.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 17:00 | 2020-05-12 18:00 | 1 | U | INTHLCSG | WAIT | WOW | WAIT ON WEATHER | 5.23 | 10284 | 10284 | 0 | SHUT DOWN DUE SEVERE WEATHER AND LIGHTING STRIKES.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 18:00 | 2020-05-12 19:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.27 | 10284 | 10284 | 0 | RIG SERVICE.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 19:00 | 2020-05-12 20:30 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.33 | 10284 | 10284 | 0 | SLIP AND CUT 9 WRAPS (90') OF DRILL LINE WHILE CHANGING OUT CATWALK.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 20:30 | 2020-05-12 21:00 | 0.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.35 | 10284 | 10284 | 0 | CLEAN AND CLEAR RIG FLOOR
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-12 21:00 | 2020-05-13 04:30 | 7.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.67 | 10284 | 10284 | 0 | CONTINUE L/D 56 STDS 5" DRILL PIPE OUT THE MOUSE HOLE.
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-13 04:30 | 2020-05-13 05:30 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.71 | 10284 | 10284 | 0 | RIG DOWN 5" HANDLING EQUIPMENT AND P/U 4-1/2" HANDLING EQUIPMENT. CLEAN RIG FLOOR
LEVI GOODRICH UNIT 2 2H | 12 | 2020-05-13 05:30 | 2020-05-13 06:00 | 0.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.73 | 10284 | 10284 | 0 | PICK UP 6.75" ULTERRA U611S SER 47380: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.0' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; , 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, BTI VALVE, X/O XT-39 P x DELTA 425 B, BIT TO SENSOR-65'. TEST MWD (TEST GOOD).
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 06:00 | 2020-05-13 07:30 | 1.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.79 | 10284 | 10284 | 0 | CONTINUE PICKING UP 6.75" ULTERRA U611S SER 47380: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.0' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; , 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, BTI VALVE, X/O XT-39 P x DELTA 425 B, BIT TO SENSOR-65'. TEST MWD (TEST GOOD).
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 07:30 | 2020-05-13 11:00 | 3.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 5.94 | 10284 | 10284 | 0 | PICK UP 4 1/2" DELTA 425 F/BHA T/2,726', FILL PIPE ON STD 27, P/U AGITATOR, ATTEMPT TO TEST MWD, PULSES WERE WEAK DUE TO LOW SPP @ 600 PSI.
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 11:00 | 2020-05-13 11:30 | 0.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 5.96 | 10284 | 10284 | 0 | TROUBLE SHOOT LOW SPP ISSUE, OBSERVED IMPROPER VALVE ALIGNMENT ALLOWING MUD TO BE PUMP DOWN KILL LINE, TEST MWD WITH GOOD PULSES AND 3,000 PSI SPP.
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 11:30 | 2020-05-13 21:30 | 10 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.38 | 10284 | 10284 | 0 | CONTINUE PICKING UP 4 1/2" DELTA 425 F/2,726' T/10,180', FILLING PIPE EVERY 30 STDS, HOLE GIVING PROPER DISPLACEMENT, REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD. PERFORM BOP DRILL-50 SECONDS.
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 21:30 | 2020-05-13 22:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.4 | 10284 | 10284 | 0 | RIG SERVICE
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 22:00 | 2020-05-13 23:30 | 1.5 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 6.46 | 10284 | 10294 | 6.7 | DRILL OUT SHOE TRACK AND 10' OF NEW FORMATION F/10,284' T/10,294'.
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-13 23:30 | 2020-05-14 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.48 | 10294 | 10294 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T., FILL GAS BUSTER.
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-14 | 2020-05-14 00:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.5 | 10294 | 10294 | 0 | PERFORM F.I.T. TO 13.0 PPG EMW, 1700 PSI W/9.8 MW @ 10,274' MD / 10,206' TVD.
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-14 00:30 | 2020-05-14 00:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.5 | 10294 | 10294 |  | MILESTONE_START CURVE SECTION ON 5/14/2020 @ 00:30
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-14 00:30 | 2020-05-14 04:00 | 3.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.65 | 10294 | 10485 | 54.6 | BUILD CURVE-SLIDE (191' IN 3.32 HRS @ 58 FPH) WOB: 15/20, SPM: 94, GPM: 300, MMRPM:204, SPP: 3000/3300 PSI, DIFF: 300/600 PSI. SLIDE DEPTHS: SLD F/10299 10393 94' TF-20R 0050-230 SLD F/10418 10426 8' TF-20R 255-310 SLD F/10488 T/10513 25' TF-HS 355-427 SLD F/10583 T/10647 60' TF-HS 508-600
LEVI GOODRICH UNIT 2 2H | 13 | 2020-05-14 04:00 | 2020-05-14 06:00 | 2 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.73 | 10485 | 10647 | 81 | BUILD CURVE-ROT (162’ IN 1.68 HRS @ 96 FPH) WOB: 20/25K, SPM: 94, GPM: 300, RPM: 30, MMRPM: 204, TRPM: 234, TRQ: 6/8K, SPP: 3800/4000 PSI, DIFF: 1000/1200 PSI. NOTE: SHUTTING IN ON CONNECTION 0 CP, 0' FLARE.
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 06:00 | 2020-05-14 08:00 | 2 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.81 | 10647 | 10849 | 101 | BUILD CURVE-SLIDE (202' IN 2.2 HRS @ 91.8 FPH) WOB: 15/20, SPM: 60/60, GPM: 400, MMRPM: 272, SPP: 4000/4600 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: SLD F/10707' T/10773' 66' TF-HS 0653-0753 SLD F/10837' T/10867' 30' TF-HS 0820-0850 SLD F/10914' T/11020' 1106' TF-HS 0950-1032
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 08:00 | 2020-05-14 11:00 | 3 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.94 | 10849 | 11056 | 69 | BUILD CURVE-ROT (207’ IN 2.8 HRS @ 73.9 FPH) WOB: 20/25K, SPM: 60/60, GPM: 400, RPM: 30, MMRPM: 272, TRPM: 302, TRQ: 6/8K, SPP: 4000/5200 PSI, DIFF: 1000/1200 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 450 PSI, MAX CP= 230 PSI, 20-30' FLARE AND MUD CUT 9.8 PPG T/9.5 PPG.
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 11:00 | 2020-05-14 11:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.94 | 11056 | 11056 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 5/14/2020 @ 11:00
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 11:00 | 2020-05-14 11:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.94 | 11056 | 11056 |  | MILESTONE_LAND/END CURVE SECTION ON 5/14/2020 @ 11:00
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 11:00 | 2020-05-14 11:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.96 | 11056 | 11056 | 0 | CIRCULATE GAS OUT OF HOLE, MW IN 9.8 MW OUT 9.5, GAS 1,800 UNITS, FLARE 15'
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 11:30 | 2020-05-14 15:30 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.13 | 11056 | 11577 | 130.2 | ROT (521’ IN 3.85 HRS @ 135.3 FPH) WOB: 20/30K, SPM: 60/60, GPM: 400, RPM: 80, MMRPM: 272, TRPM: 352, TRQ: 8/11K, SPP: 4000/5200 PSI, DIFF: 1000/1200 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 700 PSI, MAX CP= 450 PSI, 20-30' FLARE AND NO MUD CUT.
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 15:30 | 2020-05-14 16:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.15 | 11577 | 11624 | 94 | SLIDE (47’ IN .78 HRS @ 60.3 FPH) WOB: 25/35, SPM: 60/60, GPM: 400, MMRPM: 272, SPP: 4000/4600 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: SLD F/11063' T/11085' 22' TF-180 1122-1144 SLD F/11250' T/11275' 25' TF-180 1302-1335
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 16:00 | 2020-05-14 17:00 | 1 | P | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 7.19 | 11624 | 11624 | 0 | SAVER SUB BROKE LOOSE FROM TOP DRIVE. TORQUE AND INSTALL NEW COMPRESSION RING AND TIGHTEN CLAMPS.
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 17:00 | 2020-05-14 21:00 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.35 | 11624 | 11927 | 75.8 | ROT (303’ IN 4 HRS @ 75.75 FPH) WOB: 30/40K, SPM: 60/60, GPM: 400, RPM: 80, MMRPM: 272, TRPM: 352, TRQ: 8/11K, SPP: 3600/4200 PSI, DIFF: 1000/1200 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 485 PSI, MAX CP= 220 PSI, 5'-20' FLARE AND MUD CUT 9.7-9.6 PPG.
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 21:00 | 2020-05-14 23:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.44 | 11927 | 11970 | 21.5 | SLIDE (43’ IN 2 HRS @ 21.5 FPH) WOB: 25/35, SPM: 60/60, GPM: 400, MMRPM: 272, SPP: 3400/3600 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: SLD F/11624' T/11642' 18' TF-180 1700-1742 SLD F/11908' T/11928' 20' TF-150R 1940-2040 SLD F/11957' T/11962' 5' TF-150R 2230-2250
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-14 23:00 | 2020-05-15 02:30 | 3.5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 7.58 | 11970 | 11970 | 0 | CIRCULATE AND INCREASE MW 9.7# TO 9.8#, PREPARE TO TRIP FOR WASHOUT. BUILD 50 BBL 14 PPG SLUG AND 100 BBL OF 17 PPG KILL MUD. CIRCULATE GAS OUT OF HOLE, MAX CSG PSI 450 PSI, FLARE 15-25', MAX MUD CUT 9.8 PPG TO 9.6 PPG. PUMP 50 BBL SLUG (SPP 0 PSI CSG PSI 475)
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-15 02:30 | 2020-05-15 05:30 | 3 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.71 | 11970 | 11970 | 0 | POOH F/11970' FILLING ANNULUS W/CALCULATED FILL OF 17 PPG MUD. START CASING PSI 475, CASING PSI 150 @ 6324' - CALCULATED FILL 38.4 BBLS / ACTUAL FILL 42 BBLS
LEVI GOODRICH UNIT 2 2H | 14 | 2020-05-15 05:30 | 2020-05-15 06:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.73 | 11970 | 11970 | 0 | REPLACE HYDRAULIC HOSE ON ST-80
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 06:00 | 2020-05-15 07:00 | 1 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.77 | 11970 | 11970 | 0 | CONTINUE TRIPPING OUT F/6,324' T/4,934’FILLING ANNULUS W/CALCULATED FILL OF 17 PPG MUD, CASING PSI DECREASED TO 0 PSI - CALCULATED FILL 48.5 BBLS / ACTUAL FILL 60 BBLS.
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 07:00 | 2020-05-15 08:00 | 1 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.81 | 11970 | 11970 | 0 | OPEN CHOKES AND FLOW CHECK (WELL STATIC), BUILT 100 BBLS OF 17 PPG KILL MUD.
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 08:00 | 2020-05-15 12:00 | 4 | U | PRDHLLT | TRIP | WSHO | TRIP FOR WASHOUT | 7.98 | 11970 | 11970 | 0 | TRIP OUT THE HOLE F/4,934’ T/2,300’ ON THE TRIP TANK, L/D AGITATOR ON STD 27, REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, LOSS RETURNS, CONTINUE TRIPPING OUT THE HOLE F/2,300’ T/BHA FILLING ANNULUS W/CALCULATED FILL OF 9.8 PPG MUD - CALCULATED FILL 15.9 BBLS / ACTUAL FILL 70 BBLS.
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 12:00 | 2020-05-15 13:30 | 1.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 8.04 | 11970 | 11970 | 0 | RACK BACK TOP MONELS, PULL MWD, DRAIN MOTOR AND BREAK OUT BIT. NOTE: INSPECTED BHA FOR WASH OUT, OBSERVED THE UBHO SUB WASHED OUT AT THE SET SCREW.
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 13:30 | 2020-05-15 15:30 | 2 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 8.13 | 11970 | 11970 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13446789: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.0° SLICK; .68 REV/GAL; 4.0' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; , 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, BTI VALVE, X/O XT-39 P x DELTA 425 B, BIT TO SENSOR-65'. TEST MWD (TEST GOOD), CHANGED OUT UBHO AND BTI VALVE. NOTE: PUMP 55 BBLS (1,188’) OF 9.0 PPG AND REGAIN RETURNS.
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 15:30 | 2020-05-15 19:00 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.27 | 11970 | 11970 | 0 | TRIP IN THE HOLE F/BHA T/6040', FILL PIPE ON STD 27, PICK UP AGITATOR, HOLE GIVING PROPER DISPLACEMENT, FILL PIPE EVERY 30 STDS, REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD.
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 19:00 | 2020-05-15 20:30 | 1.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 8.33 | 11970 | 11970 | 0 | CIRCULATE OUT KILL MUD, MW IN 9.7# MAX MW OUT 11.2#, FULL RETURNS W/145 GPM AND 1000 PSI SPP
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-15 20:30 | 2020-05-16 00:30 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.5 | 11970 | 11970 | 0 | TRIP IN THE HOLE F/6040' T/11814', FILL PIPE EVERY 30 STDS, HOLE DISPLACING PROPERLY
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-16 00:30 | 2020-05-16 01:30 | 1 | U | PRDHLLT | LOG | MWD | MWD | 8.54 | 11970 | 11970 | 0 | RE-LOG F/ 11814' T/11908', WASH AND REAM F/11908' T/11970'
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-16 01:30 | 2020-05-16 03:00 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.6 | 11970 | 12443 | 315.3 | ROT (473’ IN 2.82 HRS @ 168 FPH) WOB: 30/40K, SPM: 50/50, GPM: 330, RPM: 80, MMRPM: 224, TRPM: 304, TRQ: 8/11K, SPP: 3800/4200 PSI, DIFF: 800/1000 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 550 PSI, MAX CP= 200 PSI, 5'-10' FLARE AND MUD CUT 9.9 PPG IN 9.9 PPG OUT - NO CUT
LEVI GOODRICH UNIT 2 2H | 15 | 2020-05-16 03:00 | 2020-05-16 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.73 | 12443 | 12476 | 11 | SLIDE (33’ IN 1.68 HRS @ 20 FPH) WOB: 30/40, SPM: 50/50, GPM: 330, MMRPM: 224, SPP: 3400/3600 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/11970 T/11983 13' TF-150R 130-210 SLD F/12385 T/12405 20' TF-150R 439-540
LEVI GOODRICH UNIT 2 2H | 16 | 2020-05-16 06:00 | 2020-05-16 16:30 | 10.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.17 | 12476 | 14193 | 163.5 | ROT (1717’ IN 10.67 HRS @ 160.97 FPH) WOB: 30/40K, SPM: 50/50, GPM: 330, RPM: 80, MMRPM: 224, TRPM: 304, TRQ: 11/14K, SPP: 3600/3800 PSI, DIFF: 600/800 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 375 PSI, MAX CP= 375 PSI, 8'-12' FLARE AND MUD CUT 9.5 PPG IN 9.4 PPG OUT. CUT MUD WT. F/9.9 PPG T/9.5 PPG DUE TO SEEPAGE LOSSES.
LEVI GOODRICH UNIT 2 2H | 16 | 2020-05-16 16:30 | 2020-05-17 06:00 | 13.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.73 | 14193 | 14506 | 23.2 | SLIDE (313’ IN 13.33 HRS @ 23.48 FPH) WOB: 30/40, SPM: 57/57, GPM: 375, MMRPM: 255, SPP: 3400/3600 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: SLD F/12476' T/12512' 36' TF-180 0600-0647 SLD F/12761' T/12796' 35' TF-180 0825-1003 SLD F/12950' T/12985' 35' TF-180 1102-1232 SLD F/13332' T/13367' 35' TF-180 1445-1631 SLD F/13523' T/13560' 37' TF-150R 1730-1900 SLD F/13706' T/13746' 40' TF-180 2006-2157 SLD F/13800 T/13815 15' TF-180 2223-2308 SLD F/14273 T/14313 40' TF-180 135-328 SLD F/14466 T/14506 40' TF-130L 420-600
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-17 06:00 | 2020-05-17 12:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.98 | 14506 | 15391 | 147.5 | ROT (885’ IN 5.72 HRS @ 154.7 FPH) WOB: 30/40K, SPM: 50/50, GPM: 330, RPM: 80, MMRPM: 224, TRPM: 304, TRQ: 11/14K, SPP: 2700/3550 PSI, DIFF: 650/850 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 560 PSI, MAX CP= 620 PSI, 5'-15' FLARE AND MUD CUT 9.2 PPG T/ 9.2 PPG-NO MUD CUT. CUT MUD WT. F/9.5 PPG T/9.1 PPG DUE TO SEEPAGE LOSSES.
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-17 12:00 | 2020-05-17 16:30 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.17 | 15391 | 15506 | 25.6 | SLIDE (115’ IN 4.78 HRS @ 24.1 FPH) WOB: 35/45, SPM: 57/57, GPM: 375, MMRPM: 255, SPP: 3000/3400 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: SLD F/14747' T/14782' 35' TF-130L 07;026-0840 SLD F/15030' T/15070' 40' TF-180 1028-1146 SLD F/15227' T/15267' 40' TF-180 1256-1511
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-17 16:30 | 2020-05-17 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.19 | 15506 | 15506 | 0 | RIG SERVICE.
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-17 17:00 | 2020-05-17 20:30 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.33 | 15506 | 15857 | 100.3 | ROT (351’ IN 3.45 HRS @ 102 FPH) WOB: 30/40K, SPM: 92, GPM: 295, RPM: 80, MMRPM: 200, TRPM: 280, TRQ: 11/14K, SPP: 2400/2600 PSI, DIFF: 500/700 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 730 PSI, MAX CP= 660 PSI, 10'-15' FLARE AND MUD CUT 9.1 PPG IN 8.1 PPG OUT. CUT MUD WT. F/9.5 PPG T/9.1 PPG DUE TO SEEPAGE LOSSES, PUMP FIRST RESPONSE SWEEPS EVERY STAND
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-17 20:30 | 2020-05-17 22:30 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.42 | 15857 | 15894 | 18.5 | SLIDE (37’ IN 2 HRS @ 19 FPH) WOB: 35/45, SPM: 57/57, GPM: 375, MMRPM: 255, SPP: 3400/3600 PSI, DIFF: 600/800 PSI. SLIDE DEPTHS: SLD F/15520' T/15543' 23' TF-150R 1800-1903
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-17 22:30 | 2020-05-18 01:00 | 2.5 | P | PRDHLLT | CIRC | MXBLD | MIX MUD/BUILD FLUID | 10.52 | 15894 | 15894 | 0 | CIRCUALATE WHILE TRANSFER AND BUILD 15 PPG KILL MUD TO PUMP DOWN BACKSIDE OF ANNULUS. PUMPED 25 BBLS OFF 15 PPG KILL MUD, START SICP 175 PSI DOWN TO 0 PSI. DISPLACE 9.1 PPG MUD OUT OF DP WITH FRESH WATER
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-18 01:00 | 2020-05-18 04:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.65 | 15894 | 16230 | 112 | ROT (336’ IN 3 HRS @ 112 FPH) WOB: 30/40K, SPM: 104, GPM: 330, RPM: 80, MMRPM: 224, TRPM: 304 , TRQ: 11/14K, SPP: 2700/3000 PSI, DIFF: 300/600 PSI. NOTE: DRILLING WITH NO RETURNS, PUMPING FRESH WATER DOWN DRILL PIPE WITH 25 BBL 15.0 PPG MUD CAP ON BACKSIDE
LEVI GOODRICH UNIT 2 2H | 17 | 2020-05-18 04:00 | 2020-05-18 06:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.73 | 16230 | 16260 | 15 | SLIDE (30’ IN 2 HRS @ 15 FPH) WOB: 35/45, SPM: 104, GPM: 304, MMRPM: 224, SPP: 2600/2900 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/15894' T/15904' 10' TF-HS 0100-0130 SLD F/16071' T/16091' 20' TF-180 0340-0500
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-18 06:00 | 2020-05-18 11:30 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.96 | 16260 | 16654 | 71.6 | ROT (394’ IN 5.55 HRS @ 71 FPH) WOB: 30/40K, SPM: 104, GPM: 330, RPM: 80, MMRPM: 224, TRPM: 304 , TRQ: 15/18K, SPP: 2800/3800 PSI, DIFF: 800/1000 PSI.
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-18 11:30 | 2020-05-18 13:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.02 | 16654 | 16663 | 6 | SLIDE (9’ IN 1.45 HRS @ 6.2 FPH) WOB: 35/45, SPM: 57/57, GPM: 375, MMRPM: 224, SPP: 3600/4100 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/16654' T/16663' 9' TF-HS 1133-1300
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-18 13:00 | 2020-05-18 13:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.04 | 16663 | 16663 | 0 | STAGED PUMPS UP F/330 GPM T/375 GPM AND ATTEMPTED TO SLIDE @ 16,663’, GAMMA @ 180-200, PULLED UP TO TOP OF STAND AND RE-LOGGED GAMMA TO CONFIRM GAMMA WAS CORRELATING CORRECTLY.
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-18 13:30 | 2020-05-18 17:30 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.21 | 16663 | 16898 | 58.7 | ROT (235’ IN 3.55 HRS @ 66 FPH) WOB: 30/40K, SPM: 104, GPM: 330, RPM: 80, MMRPM: 224, TRPM: 304 , TRQ: 15/18K, SPP: 2800/3800 PSI, DIFF: 800/1000 PSI.
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-18 17:30 | 2020-05-18 23:30 | 6 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.46 | 16898 | 16940 | 7 | SLIDE (42’ IN 6.27 HRS @ 7 FPH) WOB: 35/45, SPM: 57/57, GPM: 375, MMRPM: 224, SPP: 3400/3800 PSI, DIFF: 300/600 PSI. SLIDE DEPTHS: SLD F/16834' T/16874' 40' TF-45L 1600-1800 SLD F/16938' T/16940' 2' TF-HS 2117-2319
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-18 23:30 | 2020-05-19 02:30 | 3 | U | PRDHLLT | TRIP | WPR | WIPER TRIP IN / OUT | 11.58 | 16940 | 16940 | 0 | BACK REAM OUT OF HOLE F/16940' 15500', 70 RPM, TRQ 7-9K (MAX TRQ 24K), SPP 3000-3500 PSI - BACKREAM TO CLEAN HOLE
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-19 02:30 | 2020-05-19 04:00 | 1.5 | U | PRDHLLT | TRIP | WPR | WIPER TRIP IN / OUT | 11.65 | 16940 | 16940 | 0 | WASH AND REAM IN HOLE F/15500' T/16940', 70 RPM, TRQ 7-9K (MAX TRQ 20K), SPP 3000-3500 PSI
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-19 04:00 | 2020-05-19 05:00 | 1 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.69 | 16940 | 16942 | 2 | ATTEMPT TO DRILL F/16940' T/16942', MAX TRQ 24K, DIFF PSI 100 PSI, RPM 70-80 - NO SUCCESS
LEVI GOODRICH UNIT 2 2H | 18 | 2020-05-19 05:00 | 2020-05-19 06:00 | 1 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.73 | 16942 | 16942 | 0 | BACK REAM OUT OF HOLE F/16942' T/16450', 70 RPM, TRQ 7-9K (MAX TRQ 24K), SPP 2800-3000 PSI
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 06:00 | 2020-05-19 10:00 | 4 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.9 | 16942 | 16942 | 0 | CONTINUE BACK REAMING OUT OF HOLE F/16,450' T/12,760', 70 RPM, GPM; 330, TRQ; 7-9K (MAX TRQ 20K), SPP: 2800-3000 PSI.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 10:00 | 2020-05-19 15:30 | 5.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.13 | 16942 | 16942 | 0 | TRIP OUT THE HOLE WET F/12,760' T/3,066' FILLING ANNULUS W/CALCULATED FILL OF 9.5 PPG MUD, MONITORING CASING PSI, CP=0 PSI.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 15:30 | 2020-05-19 16:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.17 | 16942 | 16942 | 0 | OPEN CHOKES AND FLOW CHECK (NO FLOW), REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, TRIP OUT THE HOLE F/3,066’ T/2,727'.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 16:30 | 2020-05-19 17:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.21 | 16942 | 16942 | 0 | WHILE L/D AGITATOR OBSERVED THAT THE SHOCK SUB BACKED ALL THE WAY OUT OF THE THREADS AND SAFETY ROTARY CATCH WAS WAS HOLDING THE AGITATOR FROM FALLING DOWN HOLE., L/D AGITATOR.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 17:30 | 2020-05-19 19:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.27 | 16942 | 16942 | 0 | CONTINUE TRIPPING OUT THE HOLE F/2,727' T/BHA FILLING ANNULUS W/CALCULATED FILL OF 9.5 PPG MUD.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 19:00 | 2020-05-19 20:00 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 12.31 | 16942 | 16942 | 0 | RACK BACK TOP MONELS, PULL MWD, DRAIN MOTOR AND BREAK OUT BIT.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 20:00 | 2020-05-19 22:00 | 2 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 12.4 | 16942 | 16942 | 0 | CUT AND SLIP 70' OF DRILLING LINE
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 22:00 | 2020-05-19 23:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.44 | 16942 | 16942 | 0 | RIG SERVICE
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 23:00 | 2020-05-19 23:30 | 0.5 | U | PRDHLLT | RIGMT | SVCMD | SERVICE MUD PUMPS / CIRC EQUIP | 12.46 | 16942 | 16942 | 0 | CHANGE LEAKING VALVES IN MUD TANKS
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-19 23:30 | 2020-05-20 00:30 | 1 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 12.5 | 16942 | 16942 | 0 | PICK UP 6.75" ULTERRA U611S SER 17576: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.0' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; , 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, BTI VALVE, X/O XT-39 P x DELTA 425 B, BIT TO SENSOR-64'. TEST MWD (TEST GOOD)
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-20 00:30 | 2020-05-20 05:00 | 4.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.69 | 16942 | 16942 | 0 | TRIP IN THE HOLE F/BHA T/8741', FILL PIPE ON STD 27, PICK UP AGITATOR, HOLE GIVING PROPER DISPLACEMENT, FILL PIPE EVERY 30 STDS, REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD.
LEVI GOODRICH UNIT 2 2H | 19 | 2020-05-20 05:00 | 2020-05-20 06:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.73 | 16942 | 16942 | 0 | PUMP 13.0 PPG MUD DOWN THE BACKSIDE TO KILL WELL, 160 GPM. MAX CSG PSI=577 DOWN TO 200 PSI
LEVI GOODRICH UNIT 2 2H | 20 | 2020-05-20 06:00 | 2020-05-20 09:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.85 | 16942 | 16942 | 0 | TIH F/8741' T/15520', FILL PIPE EVERY 30 STDS
LEVI GOODRICH UNIT 2 2H | 20 | 2020-05-20 09:00 | 2020-05-20 10:00 | 1 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 12.9 | 16942 | 16942 | 0 | WASH AND REAM F/15520' T/15977', 40 RPM, SPP 3400 PSI, 330 GPM
LEVI GOODRICH UNIT 2 2H | 20 | 2020-05-20 10:00 | 2020-05-20 11:30 | 1.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 12.96 | 16942 | 16942 | 0 | BUILD TROUGH 40' F/15977' T/16017', SPP 3200-3600, GPM 330
LEVI GOODRICH UNIT 2 2H | 20 | 2020-05-20 11:30 | 2020-05-21 06:00 | 18.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 13.73 | 16942 | 16942 | 0 | ATTEMPT OPEN HOLE SIDETRACK TIME DRILLING F/16017' T/16027' 10' @ 5 MIN PER INCH, GPM 330, SPP 3800 PSI - MAX CSG PSI=150psi
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-21 06:00 | 2020-05-21 07:00 | 1 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 13.77 | 16942 | 16942 | 0 | F/16027' T/16,029' 2' @ 5 MIN PER INCH, GPM 375, SPP 4800 PSI - CSG PSI 0
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-21 07:00 | 2020-05-21 17:00 | 10 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 14.19 | 16942 | 16942 | 0 | WORK STUCK PIPE F/16029' T/15982', P/U 475K S/O 100K, TORQ-30K, GPM 330, W/ PARTIAL PUMP 200 BBLS WATER DOWN DRILL PIPE, PUMP 130 BBL DIESEL PILL AND SPOT UP ANNULUS 4,954', ATTEMPT TO PUMP 9.3 PPG OBM THROUGH KILL LINE DOWN THE BACKSIDE, CSG PSI INCREASED TO 1,200 PSI, BLEED OFF CASING PSI, PUMP WATER DOWN DRILL PIPE @ 400 GPM, SPP- 4200/4400, TORQ - 30/32K W/ PARTIAL ROTATION IN DRILL STRING W/ATTEMPTING T/ WORK DRILL STRING FREE, PRESSURE UP ON CASING T/ 700 PSI @ 100 PSI INCREMENTS W/ WORKING DRILL STRING, DRILL STRING WORKED FREE, RPM-100, TORQ - 26/32K.
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-21 17:00 | 2020-05-21 22:00 | 5 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 14.4 | 16942 | 16942 | 0 | BLEED OFF CASING PRESSURE WITH NO FLOW OR GAS, DRY REAMED OUT OF HOLE F/15,982' T/15,752' @ 2-20 FPM, RPM-100, TORQ 22/32 K, HIT TIGHT SPOT @ 15,812', WORKED PIPE THROUGH TIGHT SPOT F/15,812' - T/15,806' @ 15,806' TORQUE FELL OF F/30K T/8K MONITORED CASING PSI WHILE REAMING OUT OF HOLE, CASING PRESSURE BUILDING PERIODICALLY F/150/450 PSI, BLEED CASING PRESSURE AS NEEDED TO REDUCE TORQUE WHILE CONTINUING TO BACK REAM OUT OF THE HOLE. WELL DID NOT FLOW OR HAVE ANY GAS WHEN PRESSURE WAS BLED OFF.
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-21 22:00 | 2020-05-21 23:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.44 | 16942 | 16942 | 0 | ESTABLISHED PUMP RATE @ 15,752' W/323 GPM W/2500 PSI SPP & 800 PSI SICP. AFTER KILLING PUMPS PRESSURE WOULD NOT BLEED OFF ON STANDPIPE. PUMPED AN EXTRA 1000 STKS DOWN DRILL PIPE IN AN ATTEMPT TO CLOSE OFF POSSIBLE HUNG FLOATS, PRESSURE STILL WOULD NOT BLEED OFF.
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-21 23:00 | 2020-05-22 | 1 | U | PRDHLLT | KILL |  | KILL WELL | 14.48 | 16942 | 16942 | 0 | KILLED WELL WITH 90 BBLS OF 14 PPG MUD DOWN DRILL PIPE SPP: 2600 PSI TO 0 PSI, SICP: 700 PSI TO 0 PSI.
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-22 | 2020-05-22 05:00 | 5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.69 | 16942 | 16942 | 0 | TRIPPED OUT OF HOLE F/15,752' - T/4809 FILLING HOLE WITH CALCULATED FILL OF 9.3 PPG OBM; LEFT 49 STDS 4.5" DP AND DIRECTIONAL BHA IN HOLE
LEVI GOODRICH UNIT 2 2H | 21 | 2020-05-22 05:00 | 2020-05-22 06:00 | 1 | U | PRDHLLT | WAIT | WEQP | WAIT ON EQUIPMENT | 14.73 | 16942 | 16942 | 0 | WAITING ON FISHING TOOLS
LEVI GOODRICH UNIT 2 2H | 22 | 2020-05-22 06:00 | 2020-05-22 07:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 14.77 | 16942 | 16942 | 0 | SERVICE TOP DRIVE, BLOCK AND CROWN.
LEVI GOODRICH UNIT 2 2H | 22 | 2020-05-22 07:00 | 2020-05-22 14:30 | 7.5 | U | PRDHLLT | WAIT | WEQP | WAIT ON EQUIPMENT | 15.08 | 16942 | 16942 | 0 | WAIT ON FISHING TOOLS AND OFFLOAD FISHING TOOLS.
LEVI GOODRICH UNIT 2 2H | 22 | 2020-05-22 14:30 | 2020-05-22 17:30 | 3 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 15.21 | 16942 | 16942 | 0 | MAKE CUT LIP SCREW IN SUB, TRIP IN HOLE T/ 2774', INSTALL ROTATING HEAD, TRIP IN HOLE F/ 2,774' T/ 5,045', W/ NO RETURNS.
LEVI GOODRICH UNIT 2 2H | 22 | 2020-05-22 17:30 | 2020-05-22 18:00 | 0.5 | U | PRDHLLT | KILL |  | KILL WELL | 15.23 | 16942 | 16942 | 0 | TRANSFER 14.7 PPG OBM F/ FRAC TANKS T/ MUD PITS, PUMP 50 BBLS 14.7 PPG THRU KILL LINE DUE T/ TRIP IN HOLE OPEN END DRILL PIPE.
LEVI GOODRICH UNIT 2 2H | 22 | 2020-05-22 18:00 | 2020-05-22 22:00 | 4 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 15.4 | 16942 | 16942 | 0 | TRIP IN HOLE F/ 5,045' T/ 11005' AT TOP OF FISH, PUMP PRESSURE INCREASED TO 1,000 PSI, TRQ INCREASED TO 8K; SCREW INTO TOP OF FISH, PUMP PRESSURE INCREASED TO 2,700 PSI, TRQ INCREASED TO 25K;
LEVI GOODRICH UNIT 2 2H | 22 | 2020-05-22 22:00 | 2020-05-23 06:00 | 8 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 15.73 | 16942 | 16942 | 0 | DRY REAM OUT OF HOLE AS HOLE ALLOWS F/TOP OF FISH @ 11,005' T/ (BTM OF DRILLSTRING @ 15,599'); MAX OVERPULL 30K, MAX TRQ 25K WORKED FISH UP THE HOLE T/11,001' WITH MAX OVERPULL OF 30K WHEN FISH CAME LOOSE ON FIRST ATTEMPT, PIPE WAS THEN SCREWED BACK INTO FISH & TORQUED UP, SLOWLY WORKED PIPE DRY REAMING F/11,005' - T/10,998', TIGHT SPOT WAS HIT @ 10,998' @ TOP OF FISH & 15,592' @ BOTTOM OF FISH, ATTEMPTED TO WORK PIPE THROUGH TIGHT SPOT WHEN FISH CAME LOOSE DURING 2ND ATTEMPT, PIPE WAS SCREWED BACK INTO FISH & TORQUED UP FOR 3RD ATTEMPT, FISH WAS THEN WORKED UP THE HOLE T/10,992' @ TOP OF FISH & 15,586' @ BOTTOM OF FISH
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 06:00 | 2020-05-23 07:00 | 1 | U | PRDHLLT | WCTRL |  | KILL WELL | 15.77 | 16942 | 16942 | 0 | PUMP 150 BBLS 14.7 PPG OBM DOWN DRILL PIPE, INITIAL DRILL PIPE PRESSURE 600 PSI – FINAL DRILL PIPE PRESSURE O PSI, PUMP 75 BBLS 14.7 PPG OBM DOWN BACKSIDE, INITIAL SICP 400 PSI – FINAL SICP 0 PSI.
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 07:00 | 2020-05-23 11:30 | 4.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 15.96 | 16942 | 16942 | 0 | PULL OUT OF HOLE PUMPING CALCULATED FILL ON BACKSIDE – 9.3 PPG OBM, RECOVERED 3 JOINTS DRILL PIPE ON TRIP (PIN END ON DRILL PIPE WAS TWISTED OFF) ESTIMATED TOP OF FISH +/- 11,100', CLEAN AND ORGANIZE RIG FLOOR.
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 11:30 | 2020-05-23 12:30 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 16 | 16942 | 16942 | 0 | SERVICE TOP DRIVE, BLOCK AND CROWN.
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 12:30 | 2020-05-23 15:00 | 2.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 16.1 | 16942 | 16942 | 0 | STRAP AND CALIBER OVERSHOT FISHING ASSEMBLY, STAGE FISHING TOOLS AND HANDLING TOOLS ON RIG FLOOR, WHILE MAKING UP OVERSHOT ASSEMBLY MAIN RETRACTOR CYLINDER ON ST-80 BROKE. (NO INCIDENTS OR ACCIDENTS OCCURRED WHEN CYLINDER ON ST-80 BROKE)
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 15:00 | 2020-05-23 17:30 | 2.5 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 16.21 | 16942 | 16942 | 0 | REMOVE RETRACTOR CYLINDER ON ST-80, WAIT ON CYLINDER T/ ARRIVE T/ RIG. INSTALL NEW CYLINDER UPON ARRIVAL
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 17:30 | 2020-05-23 18:30 | 1 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 16.25 | 16942 | 16942 | 0 | CONTINUE PICKING UP FISHING TOOL ASSEMBLY; 1 6 5/8" OD OVERSHOT W/3 1/2 IF BOX W/ 5 3/8" GRAPPLE, LUB BUMPER JAR, OIL JAR, (21) HWDP, ACCELERATOR JAR, DELTA 425 BOX x 3 1/2" IF PIN CROSSOVER SUB
LEVI GOODRICH UNIT 2 2H | 23 | 2020-05-23 18:30 | 2020-05-24 06:00 | 11.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 16.73 | 16942 | 16942 | 0 | INSTALL ROTATING HEAD ASSEMBLY, TIH T/10,420'; WASH AND REAM 10,420' T/10,430', WOB 5/10K, 10 BPM, TRQ 2/5K. ATTEMPT TO MAKE CONNECTION @ 10,430' SPP WOULD NOT BLEED OFF. PUMPPED 100 BBLS OF 14.7 PPG KILL MUD DOWN DRILLPIPE TO KILL WELL (SPP 2250 DOWN TO 500 PSI. TIH F/10,430' T/10,711'. WASH AND REAM THROUGH TIGHT SPOT @ 10,711' PUMPING 9.3 PPG DOWN DRILLPIPE (83 BBLS 9.5 PPG). ATTEMPT TO MAKE CONNECTION @ 10,713' AND SPP WOULD NOT BLEED OFF. PUMP 90 BBLS OF 14.7 PPG KILL MUD DOWN DRILLPIPE AND 54 BBLS OF 14.7 PPG KILL MUD DOWN ANNULUS (SPP 1200-CSG PSI 700, DOWN TO 0 PSI). TIH F/10,713' TO 10,777'. WASH AND REAM THROUGH TIGHT SPOT F/10,777' TO 10,808' (85 BBLS 9.5 PPG). ATTEMPT TO MAKE CONNECTION AND SPP WOULD NOT BLEED OFF. PUMP 76 BBL OF 14.7 PPG KILL MUD DOWN DRILLPIPE. TIH F/10,777' T/10,916'. WORK THROUGH TIGHT SPOT @ 10,916'. TIH T/11,005', WORK TIGHT SPOT @ 11,005', PUMP 84 BBL OF 9.5 PPG MUD DOWN DRILL PIPE. SWAP OVER TO 8.4 PPG FRESH WATER AND PUMP DOWN DRILLPIPE WHILE WORKING TIGHT SPOT, WASH AND REAM F/11,005' TO TOP OF FISH @ 11,100', 285 GPM, SPP 3300 PSI, RPM 15, TRQ 2/5K, CASING PSI 400 PSI.
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 06:00 | 2020-05-24 07:30 | 1.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 16.79 | 16942 | 16942 | 0 | WASH AND REAM F/ 11,086’ T/ TOP OF FISH @ 11,096’, WASH OVER FISH AND ENGAGED FISH (500 PSI INCREASE IN PUMP PSI AND MWD TOOL PULSING) PICK-UP T/ 225K, S/O T/ 75K, PICK UP T/ 325 K AND JAR FISH FREE, PULL OUT OF HOLE T/ 11,030'
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 07:30 | 2020-05-24 09:00 | 1.5 | U | PRDHLLT | WCTRL |  | KILL WELL | 16.85 | 16942 | 16942 | 0 | PUMP 150 BBLS 16.0 PPG DOWN DRILL PIPE INITIAL PSI-1600, FINAL PSI-0, PUMP 130 BBLS 16.0 PPG DOWN BACKSIDE INITIAL SICP-450, FINAL SICP-0
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 09:00 | 2020-05-24 14:30 | 5.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 17.08 | 16942 | 16942 | 0 | PULL OUT OF HOLE F/ 11,030’ T/ 4,627’. (OVERSHOT DEPTHS) PUMPING CALCULATED FILLS DOWN BACKSIDE
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 14:30 | 2020-05-24 15:00 | 0.5 | U | PRDHLLT | WCTRL |  | KILL WELL | 17.1 | 16942 | 16942 | 0 | PUMP 50 BBLS 16.0 PPG DOWN BACKSIDE INITIAL SICP-60 PSI, FINAL SICP-0 PSI.
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 15:00 | 2020-05-24 19:00 | 4 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 17.27 | 16942 | 16942 | 0 | PULL OUT OF HOLE F/ 4,627’ T/ SURFACE (OVERSHOT DEPTHS) PUMPING CALCULATED FILLS DOWN BACKSIDE, FISH LEFT IN HOLE, THREADS ON GRAPPLE PULLED, RELEASED F/ FISH.
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 19:00 | 2020-05-24 19:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 17.29 | 16942 | 16942 | 0 | SERVICED TOP DRIVE & BLOCKS
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 19:30 | 2020-05-24 20:00 | 0.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 17.31 | 16942 | 16942 | 0 | INSERTED NEW GRAPPLE INTO OVERSHOT, INSTALLED & TIGHTENED CUT LIP FOR SECONDARY FISHING RUN
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 20:00 | 2020-05-24 23:00 | 3 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 17.44 | 16942 | 16942 | 0 | TRIPPED INTO HOLE WITH FISHING ASSEMBLY TO 5522'. AT 5522' MUD STARTED FLOWING OUT OF DRILL STRING. SPACED OUT DRILL STRING & SHUT IN WELL TO MONITOR PRESSURES.
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-24 23:00 | 2020-05-25 00:30 | 1.5 | U | PRDHLLT | WCTRL |  | KILL WELL | 17.5 | 16942 | 16942 | 0 | MONITORED PRESSURES FROM THE ANNULAS & DRILL STRING FOR 15 MIN, PRESSURES DID NOT INCREASE. BULLHEADED 77 BBLS OF 14.8 PPG DOWN DRILL STRING. ISPP: O PSI, ISICP: 0 PSI, INJECTION SPP: 350 PSI, FSPP: 52 PSI. LINED UP DOWN ANNULAS & PUMPED 208 BBLS OF 14.8 PPG ISICP: 225 PSI, INJECTION SICP: 450 PSI, FSICP: 0 PSI, FSPP: O PSI.
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-25 00:30 | 2020-05-25 03:00 | 2.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 17.6 | 16942 | 16942 | 0 | INTALL ROT. HEAD, TRIPPED IN HOLE WITH FISHING ASSEMBLY F/5522' - T/11,100', TAG AND LATCH ON TO FISH
LEVI GOODRICH UNIT 2 2H | 24 | 2020-05-25 03:00 | 2020-05-25 06:00 | 3 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 17.73 | 16942 | 16942 | 0 | WORK STUCK PIPE, P/U 290K S/O 100K
LEVI GOODRICH UNIT 2 2H | 25 | 2020-05-25 06:00 | 2020-05-26 03:30 | 21.5 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 18.63 | 16942 | 16942 | 0 | JARRING ON FISH @ 11,101’ @ 300K (100K OVER) WORK DOWN ON FISH T/ 50K, PUMP 100 BBLS DIESEL AND DISPLACE OUT DRILL PIPE W/ WATER, PUMP 122 BBLS 16.4 PPG OBM DOWN BACKSIDE UNTIL INJECTION PRESSURE BROKE OVER @ 3 BPM W/ 1200 PSI, CONTINUE STAGING PUMPS UP T/ 4 BPM W/ 930 PSI, SWAP OVER T/ 9.0 PPG OBM, INCREASE PUMP RATE T/ 6 BPM W/ 525 PSI, INJECTION PRESSURE INCREASING, STAGE PUMP RATE DOWN T/ 1.3 BPM W/ 1350 PSI, PUMP TOTAL 270 BBLS 9.0 PPG OBM DOWN BACKSIDE T/ REDUCE HYDROSTATIC PRESSURE (SICP-1275) CONTINUED JARRING ON FISH WHILE MOVING KILL MUD, WATER, & 9.3 PPG OUT OF MUD TANKS TO FRAC TANKS. THEN MOVED OVER 10.5 PPG TO CIRCULATE WELL, 10 PPG TO DISPLACE LCM PILL, & BUILT LCM PILL TO ATTEMPT IN PLUGGING FISH FOR CEMENT KICK OFF PLUG. BOTH SUCTION SCREENS FOR MUD PUMPS & INLINE SCREEN TO STANDPIPE WERE PULLED
LEVI GOODRICH UNIT 2 2H | 25 | 2020-05-26 03:30 | 2020-05-26 04:30 | 1 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 18.67 | 16942 | 16942 | 0 | PUMP 69 BBLS OF (10 PPG OBM + 25PPB MAGMA FIBER / 15PPB CAL-CARB M / 30PPB FIRST RESPONSE) TURBO-CHEM DOWN DRILLSTRING, CHASED W/73 BBLS OF 10 PPG OBM, SWAPPED TO 10.5 PPG OBM AND CHASED W/69 BBLS. TOTAL TURBO-CHEM PUMPED 69 BBLS, CHASED W/TOTAL OF 142 BBLS OF OBM, SPOTTED TURBO-CHEM @ 11,100'
LEVI GOODRICH UNIT 2 2H | 25 | 2020-05-26 04:30 | 2020-05-26 06:00 | 1.5 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 18.73 | 16942 | 16942 | 0 | WORK STUCK PIPE WHILE ALLOWING TURBO-CHEM PILL TO HARDEN; SPP 200 PSI, CSG PSI 1037 PSI
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-26 06:00 | 2020-05-26 10:00 | 4 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.9 | 16942 | 16942 | 0 | HESITATION SQUEEZE LCM PILL @ 1 BPM @ 1BBL INCREMENTS, SQUEEZE 33 BBLS W/ UNSUCCESSFUL SQUEEZE PRESSURE. FINAL SQUEEZE PRESSURE 508 PSI, BLEED DOWN T/ 140 PSI.
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-26 10:00 | 2020-05-26 11:00 | 1 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 18.94 | 16942 | 16942 | 0 | WORK PIPE AND RELEASE FROM FISH @ 11101' AND PULL OUT OF HOLE T/ 11,054'.
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-26 11:00 | 2020-05-26 20:00 | 9 | U | PRDHLLT | WCTRL |  | KILL WELL | 19.31 | 16942 | 16942 | 0 | STAGE MUD PUMP UP T/ 321 GPM, CIRCULATE 2.5 BOTTOMS UP W/ 10.5 PPG W/ NO LOSSES, (SIDP-513, SICP-658) PUMP 70 BBLS 14.7 PPG W/ TURBO RESPONSE LCM DOWN DRILL PIPE, PULL OUT OF HOLE T/ 10,796’, WEIGHT UP MUD PITS T/ 10.7 PPG W/ FIRST RESPONSE, CIRCULATE W/ 10.7 PPG @ 192 GPM, AFTER PUMPING 191 BBL OF 10.7 PPG STARTING LOSING RETURNS, ADJUST GPM T/ ATTEMPT T/ MAINTAIN RETURNS, AFTER LOSING 48 BBLS, RETURNS BEGIN T/ MAINTAIN, STAGE UP MUD PUMPS T/ 321 GPM W/ FULL RETURNS, AFTER GAS WAS CIRCULATED OUT HOLE STARTED LOSING MUD LOSING A TOTAL OF 40 BBLS, PUMPS WERE SLOWED DOWN TO 240 GPM, MUD VOLUME LEVELED OUT AND HOLE WAS ABLE TO MAINTAIN FULL RETURNS WITH ZERO LOSSES PUMPING A 10.7 PPG GOING IN & 10.7 PPG COMING OUT. DECISION WAS MADE TO COME OUT OF THE HOLE & PICK UP 2-7/8" CEMENT STINGER TO PLUG BACK FOR SIDETRACK.
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-26 20:00 | 2020-05-26 22:30 | 2.5 | U | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 19.42 | 16942 | 16942 | 0 | SHUT IN TO MONITOR CASING & DRILL PIPE PRESSURES SPP-363 PSI, SICP-262 PSI
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-26 22:30 | 2020-05-26 23:00 | 0.5 | U | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 19.44 | 16942 | 16942 | 0 | PUMPED 50 BBLS OF 15 PPG KILL MUD DOWN DRILL PIPE CIRCULATING THROUGH GAS BUSTER DUE TO PIPE BEING @ 60-SPM, 194-GPM, ISPP-800 PSI, FSPP-200 PSI. SHUT OFF PUMPS AND SPP WENT TO 42 PSI, BLED OFF SPP TO 0 PSI AND MONITORED FOR FLOW, NO FLOW WAS DETECTED. PIPE WAS THE PULLED OUT OF THE HOLE T/10,243' TO CIRCULATE OUT KILL MUD AND SPOT 15 PPG MUD CAP.
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-26 23:00 | 2020-05-27 01:00 | 2 | U | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 19.52 | 16942 | 16942 | 0 | CIRCULATED OUT KILL MUD & GAS @ 10,243' MD, 10,148' TVD PUMPING @ 60 SPM, 194 GPM, SPP-1050/750 PSI, CP-0/50/0 PSI, FLARE-0/10/0'
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-27 01:00 | 2020-05-27 01:30 | 0.5 | U | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 19.54 | 16942 | 16942 | 0 | SHUT IN TO MONITOR CASING & DRILL PIPE PRESSURES FOR MUD CAP VOLUMES SPP-273 PSI, SICP-230 PSI
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-27 01:30 | 2020-05-27 03:30 | 2 | U | PRDHLLT | WCTRL |  | KILL WELL | 19.63 | 16942 | 16942 | 0 | SPOTTED MUD CAP DOWN DRILL PIPE @ 10,243' MD, PUMPED 127 BBLS OF 15 PPG OBM FOR MUD CAP, CHASED WITH 77 BBLS OF 10.7 PPG OBM, PUMPED 20 BBLS OF 15 PPG OBM (WELL WAS STILL FLOWING UP DRILL STRING), PUMPED ADDITIONAL 22 BBLS OF 15 PPG OBM, CHECKED FOR FLOW (NO FLOW), WELL STATIC
LEVI GOODRICH UNIT 2 2H | 26 | 2020-05-27 03:30 | 2020-05-27 06:00 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.73 | 16942 | 16942 | 0 | REMOVE ROT. HEAD/INSTALL TRIP NIPPLE, POOH F/10,243' T/5,889'
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 06:00 | 2020-05-27 10:30 | 4.5 | U | PRDHLLT | DPROB | FSHOP | FISHING OPERATIONS | 19.92 | 16942 | 16942 | 0 | PULL OUT OF HOLE T/ FISHING ASSEMBLY WITH WELL CIRCULATING ON TRIP TANK, LAY DOWN FISHING ASSEMBLY.
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 10:30 | 2020-05-27 11:30 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 19.96 | 16942 | 16942 | 0 | SERVICE TOP DRIVE, BLOCK AND CROWN.
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 11:30 | 2020-05-27 12:30 | 1 | P | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 20 | 16942 | 16942 | 0 | SLIP AND CUT 120' DRILL LINE.
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 12:30 | 2020-05-27 15:00 | 2.5 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.1 | 16942 | 16942 | 0 | INSTALL 2 7/8" ELEVATORS ON TOP DRIVE, MAKE UP MULE SHOE, TRIP IN HOLE PICKING UP 2 7/8" TUBING, 36 JOINTS W/ MULE SHOE ASSEMBLY TOTAL LENGTH 1137.90
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 15:00 | 2020-05-27 17:00 | 2 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.19 | 16942 | 16942 | 0 | L/D 2-7/8" HANDLING EQUIPMENT & TRIP IN HOLE T/3,818', MONITOR DISPLACEMENTS ON TRIP TANK, DISPLACEMENTS DICTATE TRIP IN HOLE SPEED.
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 17:00 | 2020-05-27 17:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 20.21 | 16942 | 16942 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 17:30 | 2020-05-27 18:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 20.23 | 16942 | 16942 | 0 | FILL UP DRILL PIPE AND BREAK CIRCULATION @ 3,818', STAGE MUD PUMP UP T/ 225 GPM W/ 780 PSI W/ NO LOSSES.
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 18:00 | 2020-05-27 19:00 | 1 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.27 | 16942 | 16942 | 0 | TRIPPED INTO HOLE F/3818' - T/5872' STARTED LOSING DISPLACEMENT @ 5714'
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 19:00 | 2020-05-27 21:30 | 2.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 20.38 | 16942 | 16942 | 0 | CIRCULATED BREAKING UP MUD CAP @ 5872' SPM-40, GPM-128, SPP-450/200/450 PSI, UPON INITIAL CIRCULATION 20 BBLS WAS LOST BEFORE FULL RETURNS WAS ESTABLISHED, 1500 STKS INTO BOTTOMS UP 11.2 PPG MUD STARTED COMING BACK TO SURFACE, CONTINUED TO CIRCULATE UNTIL MUD SYSTEM HAD A 10.8 PPG, THE HEAVIEST MUD WEIGHT SEEN WAS AN 11.3 PPG
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 21:30 | 2020-05-27 22:30 | 1 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.42 | 16942 | 16942 | 0 | TRIPPED INTO HOLE F/5872' - T/7295' MONITORING HOLE FOR PROPER DISPLACEMENT, DISPLACEMENT WENT F/8 BBLS/5 STDS TO 7.2 BBLS/5 STDS
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 22:30 | 2020-05-27 23:00 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 20.44 | 16942 | 16942 | 0 | CIRCULATED BREAKING UP MUD CAP @ 7295' SPM-40, GPM-128, SPP-450/375 PSI, PUMPED TO A TOTAL OF 1200 STROKES WITH FULL RETURNS, MW-10.8 PPG IN & 10.8 PPG OUT
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-27 23:00 | 2020-05-28 | 1 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.48 | 16942 | 16942 | 0 | TRIPPED INTO HOLE F/7295' - T/8678' MONITORING HOLE FOR PROPER DISPLACEMENT, DISPLACEMENT WENT F/5 BBLS/5 STDS TO 7.4 BBLS/5 STDS
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-28 | 2020-05-28 01:00 | 1 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 20.52 | 16942 | 16942 | 0 | CIRCULATED BREAKING UP MUD CAP @ 8678' SPM-40, GPM-128, SPP-375/375 PSI, 960 STKS INTO BOTTOMS UP 11.2 PPG MUD STARTED COMING BACK TO SURFACE, CONTINUED TO CIRCULATE UNTIL MUD SYSTEM HAD A 10.9 PPG IN / 11.0 PPG OUT, THE HEAVIEST MUD WEIGHT SEEN WAS AN 11.2 PPG
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-28 01:00 | 2020-05-28 03:00 | 2 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.6 | 16942 | 16942 | 0 | TRIPPED INTO HOLE F/8678' - T/10286' MONITORING HOLE FOR PROPER DISPLACEMENT,
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-28 03:00 | 2020-05-28 05:30 | 2.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 20.71 | 16942 | 16942 | 0 | CIRCULATED @ 10,286' THROUGH CHOKE. STAGE MUD PUMPS TO 50 SPM, GPM-160, SPP-450, MAX GAS-2372, MAX CP-187 PSI, MW IN-11.0, MUD CUT-10.7, FLARE-(7-15')
LEVI GOODRICH UNIT 2 2H | 27 | 2020-05-28 05:30 | 2020-05-28 06:00 | 0.5 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 20.73 | 16942 | 16942 | 0 | STRIP IN HOLE THROUGH ROT HEAD F/10,286' T/10,800'. CSG PSI-50
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 06:00 | 2020-05-28 09:30 | 3.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 20.88 | 16942 | 16942 | 0 | CIRCULATED @ 10,791' THROUGH CHOKE. STAGE MUD PUMPS TO 50 SPM, GPM-160, SPP-450, MAX GAS-2372, MAX CP-187 PSI, MW IN-11.0, MUD CUT-10.7, FLARE-(7-15')
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 09:30 | 2020-05-28 11:30 | 2 | U | PRDHLLT | WCTRL |  | KILL WELL | 20.96 | 16942 | 16942 | 0 | FLOW CHECK DRILL STRING, WELL FLOWING ON DRILL STRING, (SIDPP-149) PUMP 50 BBL 15.5 PPG DOWN DRILL PIPE DUE T/ FLOAT IN DRILL STRING NOT HOLDING.
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 11:30 | 2020-05-28 14:00 | 2.5 | U | PRDHLLT | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 21.06 | 16942 | 16942 | 0 | PULL OUT OF HOLE F/ 10792’ T/ 8,788’ PUMPING CALCULATED FILLS ON BACKSIDE, INSTALL INSIDE GREY VALVE, STRIP IN HOLE T/ 10,792’, BLEED OFF 1.8 BBLS DISPLACEMENT PER STAND ON TRIP TANK.
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 14:00 | 2020-05-28 16:30 | 2.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 21.17 | 16942 | 16942 | 0 | CIRCULATE OUT MUD CAP AND CONDITION MUD T/ 11.0 PPG GPM-160, SPP-675, FLOW CHECK DRILL PIPE, DRILL PIPE STATIC.
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 16:30 | 2020-05-28 18:00 | 1.5 | U | PRDHLLT | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 21.23 | 16942 | 16942 | 0 | RIG UP TIW VALVE W/ PUMP IN SUB, RIG UP CEMENT CIRCULATING LINES, FILL UP LINES, TEST LINES T/ 7000 PSI, PUMP 36 BBLS WEIGHTED SPACER @ 11.0 PPG, 37 BBLS CEMENT @ 17.5 PPG, 14 BBLS WEIGHTED SPACER @ 11.0 PPG, DISPLACE W/ 110 BBLS 11.0 PPG OBM, PUMP CEMENT PLUG CIRCULATING THRU CHOKE MAINTAINING CASING PRESSURE. ESTIMATED TOP OF CEMENT-9,956' MD
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 18:00 | 2020-05-28 19:00 | 1 | U | PRDHLLT | CMT | REMCM | REMEDIAL CEMENT OPERATIONS | 21.27 | 16942 | 16942 | 0 | STRIPPED OUT OF THE HOLE F/10792' - T8891'
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 19:00 | 2020-05-28 21:00 | 2 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 21.35 | 16942 | 16942 | 0 | CIRCULATED @ 8891' THROUGH CHOKE SPM-50, GPM-160, SPP-650, MAX CP-0 PSI, MW IN-11.0 PPG, MW OUT-10.7, FLARE- 0'. GOT BACK 5 BBLS OF SPACER TO SURFACE
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-28 21:00 | 2020-05-29 02:00 | 5 | U | PRDHLLT | WAIT | WOC | WAIT ON CEMENT | 21.56 | 16942 | 16942 | 0 | SHUT WELL IN TO MONITOR CASING PRESSURE, DRILL PIPE PRESSURE INCREASED TO 40 PSI WITH CASING PRESSURE REMAINING 0 PSI IN 30 MIN OF SHUT IN, CASING PRESSURE STARTED TO INCREASE IN 1 HR FROM SHUT IN F/0 PSI, - T/28 PSI ALONG WITH SPP F/40 PSI - T/68 PSI, PRESSURE SLOWLY INCREASED TO 94 PSI ON SPP & 62 PSI SICP IN 2.5 HRS FROM SHUT IN WHEN SPP STARTED TO DECREASE BUT CP CONTINUED TO INCREASE SLOWLY T/70 PSI, 3 HRS FROM SHUT IN SPP SUDDENLY INCREASED TO 115 PSI WITH CP AT 80 PSI, 3.5 HRS FROM SHUT IN SPP-115 / CSG PSI-80. 4 HRS FROM SHUT IN SPP-124 / CSG PSI-90. 4.5 HRS FROM SHUT IN SPP-116 / CSG PSI-101. 5 HRS FROM SHUT IN SPP-101 / CSG PSI-113. FINAL PRESSURES SPP-87 / CSG PSI-122.
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-29 02:00 | 2020-05-29 02:30 | 0.5 | U | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 21.58 | 16942 | 16942 | 0 | OPEN SUPERCHOKE AND BLEED CASING PSI INTO TRIP TANK AND MONITOR WELL. (NO FLOW)
LEVI GOODRICH UNIT 2 2H | 28 | 2020-05-29 02:30 | 2020-05-29 06:00 | 3.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 21.73 | 16942 | 16942 | 0 | PUMP SLUG AND LAY DOWN DRILL PIPE F/8,891' T/4,600'
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 06:00 | 2020-05-29 08:30 | 2.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 21.83 | 16942 | 16942 | 0 | LAY DOWN DRILL PIPE F/4,600' T/BHA. PROPER FILLS ON TRIP OUT.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 08:30 | 2020-05-29 10:30 | 2 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 21.92 | 16942 | 16942 | 0 | LAY DOWN 2-7/8" DRILL PIPE AND CEMENT STINGER.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 10:30 | 2020-05-29 11:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 21.94 | 16942 | 16942 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE. CLEAN RIG FLOOR. PREP TO TRIP IN HOLE.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 11:00 | 2020-05-29 13:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 22.02 | 16942 | 16942 | 0 | RIH WITH 46 STANDS DRILL PIPE T/ 4,351'. PROPER DISPLACEMENTS ON TRIP IN HOLE.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 13:00 | 2020-05-29 16:30 | 3.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 22.17 | 16942 | 16942 | 0 | LAY DOWN 46 STANDS OF 4.5" DRILL PIPE. PROPER FILLS ON TRIP OUT.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 16:30 | 2020-05-29 17:30 | 1 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 22.21 | 16942 | 16942 | 0 | PULL WEAR BUSHING, REMOVE DELTA 425 SUBS AND HANDLING TOOLS F/ RIG FLOOR.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 17:30 | 2020-05-29 20:30 | 3 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 22.33 | 16942 | 16942 | 0 | REMOVE DELTA 425 TOP DRIVE SUB AND INSTALL DS 42 SAVER SUB ON TOP DRIVE.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-29 20:30 | 2020-05-30 01:30 | 5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 22.54 | 16942 | 16942 | 0 | UNSPOOL DRILL LINE, CHANGE OUT DRILL LINE SPOOL AND SPOOL UP DRILL LINE ON DRAWWORKS. INSTALL WRAPS ON HORSE HEAD AND TORQUE CLAMPS.
LEVI GOODRICH UNIT 2 2H | 29 | 2020-05-30 01:30 | 2020-05-30 06:00 | 4.5 | U | PRDHLLT | BOP | TSTBOP | PRESSURE TEST BOP | 22.73 | 16942 | 16942 | 0 | TESTED BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS, LOWER PIPE RAMS, UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, AND WELLHEAD 250 LOW / 10,000 HIGH, HYDRIL 250 LOW, 3500 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 6000 HIGH. INSTALL ROTATING HEAD TEST CAP, TEST ORBIT VALVE 250 LOW / 1,500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. PULL TEST PLUG.
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 06:00 | 2020-05-30 07:30 | 1.5 | U | PRDHLLT | BOP | TSTBOP | PRESSURE TEST BOP | 22.79 | 16942 | 16942 | 0 | RIG DOWN TEST EQUIPMENT, REMOVE ROTATING BOWL TEST CAP, PULL TEST PLUG, INSTALL WEAR BUSHING.
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 07:30 | 2020-05-30 08:00 | 0.5 | U | PRDHLLT | SFTY | INSPT | SAFETY INSPECTION | 22.81 | 16942 | 16942 | 0 | CLEAN AND ORGANIZE RIG FLOOR T/ MIGATE SLIP AND TRIP HAZARDS AND PREPARE RIG FLOOR T/ PICK-UP DRILL PIPE.
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 08:00 | 2020-05-30 09:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 22.85 | 16942 | 16942 | 0 | SERVICE TOP DRIVE AND BLOCK.
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 09:00 | 2020-05-30 20:00 | 11 | U | PRDHLLT | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 23.31 | 16942 | 16942 | 0 | MAKE UP 6.75” HALLIBURTON BIT (SR1R JETTED W/ 3/20s) BIT SUB W/ FLOAT, 3 JOINTS DRILL PIPE, BTI VALVE, TRIP IN HOLE PICKING UP DS 42 4.5” DRILL PIPE, FILL UP DRILL PIPE AND BREAK CIRCULATION EVERY 40 STANDS.
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 20:00 | 2020-05-30 20:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 23.33 | 16942 | 16942 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 20:30 | 2020-05-30 21:30 | 1 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 23.38 | 16942 | 16942 | 0 | WASH F/9,747' T/9,965'. GPM-128, PP-400. TAGGED CEMENT @ 9,965'
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 21:30 | 2020-05-30 22:00 | 0.5 | U | PRDHLLT | DLOUT | DRLCM | DRILL OUT CEMENT | 23.4 | 16942 | 16942 | 0 | DRILL OUT CEMENT F/9,965' T/10,047'. GPM-257, PP-1200, RPM-40, TQ-4200 NOTE: F/9,965' T/10,001' AVERAGE ROP:175-225
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-30 22:00 | 2020-05-31 03:30 | 5.5 | U | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 23.63 | 16942 | 16942 | 0 | FLOW INCREASED FROM 13% TO 52%. PIT GAIN 10BBLS. SHUT WELL IN AND CIRCULATED THROUGH CHOKE @ 192 GPM, PP-2851, MAX GAS-2678u, CP-2100, MW IN-9.9/OUT-9.8. (WT UP T/10.5) AFTER 1ST BTMS UP: GPM-192, PP-2850, CP-2115, MAX GAS-197u, MW IN-10.3/OUT-10.5 AFTER 2ND BTMS UP: GPM-192, PP-2600, CP-1950, MAX GAS-60u, MW IN-10.8/OUT-10.5 AFTER 3RD BTMS UP: GPM-192, PP-2550, CP-1880, MAX GAS-70u, MW IN-10.8/OUT-10.5 AFTER 4TH BTMS UP: GPM-192, PP-1840, CP-1150, MAX GAS-60u, MW IN-11.1/OUT-10.8 AFTER 5TH BTMS UP: GPM-192, PP-1040, CP-375, MAX GAS-45u, MW IN-11.1/OUT-10.8
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-31 03:30 | 2020-05-31 04:00 | 0.5 | U | PRDHLLT | WCTRL |  | KILL WELL | 23.65 | 16942 | 16942 | 0 | REMOVE LEAKING ROTATING HEAD AND INSTALL NEW ROTATING HEAD.
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-31 04:00 | 2020-05-31 05:00 | 1 | U | PRDHLLT | DLOUT | DRLCM | DRILL OUT CEMENT | 23.69 | 16942 | 16942 | 0 | DRILL OUT CEMENT F/10,047' T/10,288'. GPM-192, PP-770, CP-0, RPM-40, TQ-2500-4500 MW IN & OUT-11.1 NOTE: F/10,001' T/10,280' AVERAGE ROP:175-300 AT 10,280' ROP SLOWED TO 80'/HR
LEVI GOODRICH UNIT 2 2H | 30 | 2020-05-31 05:00 | 2020-05-31 06:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 23.73 | 16942 | 16942 | 0 | CIRCULATE BOTTOMS UP. GPM-224, PP-950, RPM-40, TQ-3000
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 06:00 | 2020-05-31 06:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 23.75 | 16942 | 16942 | 0 | CIRCULATE BOTTOMS UP. GPM-224, PP-950, RPM-40, TQ-3000
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 06:30 | 2020-05-31 07:30 | 1 | U | PRDHLLT | DLOUT | DRLCM | DRILL OUT CEMENT | 23.79 | 16942 | 16942 | 0 | DRILL OUT CMT F/10,288' T/10,375' AVERAGE ROP-200'/HR. GPM-192, PP-770, CP-0, RPM-40, TQ-2500-4500 MW IN & OUT-11.1
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 07:30 | 2020-05-31 09:00 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 23.85 | 16942 | 16942 | 0 | CIRCULATE BOTTOMS UP. FLOW CHECK WELL THROUGH CHOKE-NO FLOW. OPEN ORBIT VALVE AND MONITOR WELL ON FLOWLINE-NO FLOW. PUMP SLUG
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 09:00 | 2020-05-31 13:30 | 4.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 24.04 | 16942 | 16942 | 0 | POOH F/ 10,375' AND L/D BHA, PROPER HOLE FILLS ON TRIP OUT OF HOLE.
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 13:30 | 2020-05-31 14:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 24.06 | 16942 | 16942 | 0 | RIG SERVICE
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 14:00 | 2020-05-31 15:30 | 1.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 24.13 | 16942 | 16942 | 0 | P/U BHA 6.75" ULTERRA U611S SER 38724: JETS 3/16S, 2/15S, 1/18S, TFA: 1.183), 5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 3.97' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; FLOAT SUB, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X-OVER XT-39 PIN x DS-42 BOX, BIT TO SENSOR-68', BIT TO GAMMA-58'. TEST MWD (TEST GOOD).
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 15:30 | 2020-05-31 21:30 | 6 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 24.38 | 16942 | 16942 | 0 | TRIP IN THE HOLE F/BHA T/10295' -(P/U AGITATOR AFTER STAND 27) (BEFORE 727 PSI AFTER 1130 PSI), REMOVE TRIP NIPPLE / INSTALL ROTATING HEAD. PROPER DISPLACEMENTS ON TRIP IN HOLE.
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 21:30 | 2020-05-31 22:00 | 0.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 24.4 | 16942 | 16942 | 0 | FILL PIPE & ESTABLISH RETURNS THROUGH CHOKE TO GAS BUSTER. TAKE SPR AND WASH T/10,375'. TAGGED CMT @ 10,375'.
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 22:00 | 2020-05-31 22:30 | 0.5 | U | PRDHLLT | DLOUT | DRLCM | DRILL OUT CEMENT | 24.42 | 16942 | 16942 | 0 | DRILL OUT CMT F/10,375' T/10,423'. GPM-273, PP-2650, CP-0, RPM-20, TQ-2500-3500. NOTE: TRIP GAS 778u, FLARE-5', CP-0, MW-11.2
LEVI GOODRICH UNIT 2 2H | 31 | 2020-05-31 22:30 | 2020-06-01 00:30 | 2 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 24.5 | 16942 | 10423 | -3259.5 | BUILD TROUGH F/10,389' T/10,423' @ 160L. GPM-273, PP-2650
LEVI GOODRICH UNIT 2 2H | 31 | 2020-06-01 00:30 | 2020-06-01 06:00 | 5.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 24.73 | 10423 | 10426 | 0.5 | BEGIN ATTEMPT TO SIDETRACK AGAIN @ 10,423' MD / 10,325' TVD ON 6/1/2020 @ 00:30. NEVER GOT KICKED OFF THE FIRST TIME. TIME DRILLING F/10,423' T/10,426' @ 1'/HR GPM-273, PP-2550
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 06:00 | 2020-06-01 12:00 | 6 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 24.98 | 10426 | 10434 | 1.3 | TIME DRILLING F/ 10,426’ T/ 10,434’ @ 1 FPH WOB-2/4K, DIFF-0/200 PSI, GPM-273 DRILLING THRU 100% OPEN CHOKE.
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 12:00 | 2020-06-01 14:00 | 2 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 25.06 | 10434 | 10437 | 1.5 | TIME DRILLING F/ 10,434’ T/ 10,437’ @ 2 FPH WOB-4/8K, DIFF-70/90 PSI, GPM-273, DRILLING THRU 100% OPEN CHOKE.
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 14:00 | 2020-06-01 15:30 | 1.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 25.13 | 10437 | 10439 | 1.3 | TIME DRILLING F/ 10,437’ T/ 10,439’ @ 3 FPH WOB-4/8K, DIFF-70/90 PSI, GPM-273, DRILLING THRU 100% OPEN CHOKE.
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 15:30 | 2020-06-01 17:00 | 1.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 25.19 | 10439 | 10448 | 6 | TIME DRILLING F/ 10,439’ T/ 10,448’ @ 5 FPH WOB-8/16K, DIFF-150/200 PSI, GPM-273, DRILLING THRU 100% OPEN CHOKE.
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 17:00 | 2020-06-01 18:00 | 1 | U | PRDHLCV | DRLG | CTLDRL | CONTROL DRILLING | 25.23 | 10483 | 10483 | 0 | CONTROL SLIDE DRILLING F/ 10,448' T/ 10,483', WOB-25/30K, DIFF-400/450 PSI, GPM-273 UNSUCCESSFULL ATTEMPT TO SIDETRACK ON 5-20-2020 @ 11:30 @ 16,017' SUCCESSFULLY SIDETRACKED ON 6/1/2020 @ 17:00 @ 10,423'
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 17:00 | 2020-06-01 17:00 | 0 | U | PRDHLCV | MSTN | KOST | MILESTONE_KICK OFF SIDETRACK | 25.19 | 10448 | 10483 |  | MILESTONE_KICK OFF SIDETRACK ON 6/1/2020 @ 17:00.
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-01 18:00 | 2020-06-02 00:30 | 6.5 | U | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 25.5 | 10483 | 10760 | 42.6 | SLIDE (277’ IN 6.4 HRS @ 43 FPH) WOB: 30/40, SPM: 62/62, GPM: 404, MMRPM: 274, SPP: 4500/4800 PSI, DIFF: 150/300 PSI. SLIDE DEPTHS: S.DRL F/10501' T/ 10515', @ 20L 1837-1902 (25MIN) S.DRL F/10531' T/10547' @ H.SIDE 1930-2000 (30MIN) S.DRL F/10564' T/10577' @ H.SIDE 2019-2046 (27MIN) S.DRL F/10597' T/10609' @ H.SIDE, 2110-2129 (19MIN) S.DRL F/10634 T/10640, @ H.SIDE 2152-2205 (13MIN) S.DRL F/10660' T/10672' @ H.SIDE 2223-2300 (37MIN) S.DRL F/10716' T/10767' @ H.SIDE 2312-0004 (52MIN) S.DRL F/10797' T/10861' @ H.SIDE 0025-0145 (80MIN) S.DRL F/10916' T/10946' @ H.SIDE 0223-0300 (37MIN) S.DRL F/11026' T/11050' @ H.SIDE 0349-0429 (40MIN) S.DRL F/11110' T/11145' @ H.SIDE 0505-0530
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-02 00:30 | 2020-06-02 05:30 | 5 | U | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 25.71 | 10760 | 11145 | 77 | ROT (385’ IN 5 HRS @ 77 FPH) WOB: 25/30K, SPM: 62/62, GPM: 404, RPM: 20, MMRPM: 274, TRPM: 294, TRQ: 5/7k, SPP: 4500/5300 PSI, DIFF: 600/800 PSI. DRILLING THROUGH CHOKE @ 60-65%. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 500 PSI, MW-10.5, FLARE-15-20' ON BOTTOMS UP.
LEVI GOODRICH UNIT 2 2H | 32 | 2020-06-02 05:30 | 2020-06-02 06:00 | 0.5 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 25.73 | 11145 | 11145 | 0 | RIG SERVICE
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-02 06:00 | 2020-06-02 06:30 | 0.5 | U | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 25.75 | 11145 | 11175 | 60 | SLIDE (30’ IN .25 HRS @ 120 FPH) WOB: 30/40, SPM: 62/62, GPM: 404, MMRPM: 274, SPP: 4500/4800 PSI, DIFF: 150/300 PSI.
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-02 06:30 | 2020-06-02 07:00 | 0.5 | U | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 25.77 | 11175 | 11242 | 134 | ROT (67’ IN .5 HRS @ 134 FPH) WOB: 25/30K, SPM: 62/62, GPM: 404, RPM: 20, MMRPM: 274, TRPM: 294, TRQ: 5/7k, SPP: 4500/5300 PSI, DIFF: 600/800 PSI. DRILLING THROUGH CHOKE @ 60-65%. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 500 PSI, MW-10.5, FLARE-15-20' ON BOTTOMS UP. NOTE: CURVE LANDED @ 11,242' MD / 10,589' TVD @ 07:00 HOURS.
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-02 07:00 | 2020-06-02 07:00 | 0 | U | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 25.77 | 11242 | 11242 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 6/02/2020 @ 07:00
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-02 07:00 | 2020-06-02 07:00 | 0 | U | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 25.77 | 11242 | 11242 |  | MILESTONE_LAND/END CURVE SECTION ON 6/02/2020 @ 07:00
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-02 07:00 | 2020-06-02 21:30 | 14.5 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 26.38 | 11242 | 13228 | 137 | ROT (1986’ IN 14.42 HRS @ 138 FPH) WOB: 25-30K, SPM: 63/63, GPM: 404, RPM: 80, MMRPM: 275, TRPM: 365, TRQ: 10-12K, SPP: 4400/5400 PSI, DIFF: 800-1000 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-500 PSI 10-15' FLARE AND NO MUD CUT. NOTE: START HORIZONTAL LATERAL SECTION ON 6/02/2020 @ 07:00 NOTE: STARTED LOSING MUD @ 12,460'. CUT MW FROM 10.4 DOWN TO 10.0 OVER COURSE F/12,460' T/13,500'. OPENED BOTH CHOKES 100%. ADDING LCM TO ACTIVE MUD.
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-02 21:30 | 2020-06-03 04:00 | 6.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 26.65 | 13228 | 13515 | 44.2 | SLIDE (287’ IN 6.25 HRS @ 46 FPH) WOB: 30-45, SPM: 63/63, GPM: 404, MMRPM: 275, SPP: 4000/4300 PSI, DIFF: 150-300 PSI. SLIDE DEPTHS: S.DRL F/11250 T/11270 20FT 90R 7:20/7:40 (20 MINS) S.DRL F/11440 T/11490 30FT 180 8:40/9:12 (22 MINS) S.DRL F/11730 T/11750 30FT 30L 11:00/11:10 (10 MINS) S.DRL F/11820 T/11835 15FT H-S 11:40/11:53 (13 MINS) S.DRL F/12015 T/12040 140R 13:04/13:34 (30 MINS) S.DRL F/12110 T/12127 150R 14:07/14:22 (15 MINS) S.DRL F/12395 T/12430 35FT 150R 16:30/17:05 S.DRIL F/12675' T/12700' @ 180GTF 1847-1936 (49MIN) S.DRIL F/12770' T/1270' @ 180GTF 2011-2045 (34MIN) S.DRIL F/13176' T/13196' @70L 2345-0019 (34MIN) S.DRIL F/13233' T/13243' @H-S 0044-0123 (39MIN) S.DRIL F/13435' T/13465' @180G 0239-0338 (59 MIN)
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-03 04:00 | 2020-06-03 05:30 | 1.5 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 26.71 | 13515 | 13695 | 120 | ROT (180’ IN 1.67 HRS @ 108 FPH) WOB: 25-30K, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 10-12K, SPP: 4000/5000 PSI, DIFF: 800-1000 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-500 PSI. BOTH CHOKES-100% NOTE: PARTIAL LOSSES STILL OCCURRING, REDUCE GPM F/404 T/385(NO LOSSES)
LEVI GOODRICH UNIT 2 2H | 33 | 2020-06-03 05:30 | 2020-06-03 06:00 | 0.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 26.73 | 13695 | 13705 | 20 | SLIDE (10’ IN .33 HRS @ 30 FPH) WOB: 30-45, SPM: 60/60, GPM: 385, MMRPM: 262, SPP: 4000/4300 PSI, DIFF: 150-300 PSI. SLIDE DEPTHS: S.DRIL F/13530' T/13540' @180G 0410-0430 (20 MIN)
LEVI GOODRICH UNIT 2 2H | 34 | 2020-06-03 06:00 | 2020-06-03 22:00 | 16 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 27.4 | 13705 | 15795 | 130.6 | ROT (2090’ IN 15.88 HRS @ 132 FPH) WOB: 25-35K, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 12-16K, SPP: 4000/5200 PSI, DIFF: 1000-1200 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-400-500 PSI, BOTH CHOKES-100%, FLARE-10-15' ON BOTTOMS UP, MW-9.8 NOTE: CUT MUD WT. F/10.0 PPG T/9.8 PPG DUE TO SEEPAGE LOSSES (NO LOSSES).
LEVI GOODRICH UNIT 2 2H | 34 | 2020-06-03 22:00 | 2020-06-04 06:00 | 8 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 27.73 | 15795 | 16076 | 35.1 | SLIDE (281’ IN 8.12 HRS @ 35 FPH) WOB: 30-45, SPM: 60/60, GPM: 385, MMRPM: 262, SPP: 4000/4300 PSI, DIFF: 150-300 PSI. SLIDE DEPTHS: S.DRL F/13715' T/13760' @ 150R 0601-0644 (43MIN) S.DRL F/13815' T/13833' @ 130R 0744-0807 (23MIN) S.DRL F/14098' T/14123' @ 160L 1018-1039 (21MINS) S.DRL F/14570' T/14613' @ 180 1303-1403 (1HR) S.DRL F/14765' T/14790' @ 150R 1510-1540 (40MINS) S.DRL F/15035' T/15060' @ 180 1530-1800 (30MINS) S.DRL F/15330' T/15370' @ 180G 2018-2150 (92MIN) S.DRL F/15515' T/15540' @ 180G 2252-0000 (68MIN) S.DRL F/15700' T/15735' @ 180G 0116-0316 (120MIN)
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 06:00 | 2020-06-04 07:30 | 1.5 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 27.79 | 16076 | 16245 | 112.7 | ROT (169' IN 1.38 HRS @ 122.5 FPH) WOB: 25-35K, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 12-16K, SPP: 4100/5300 PSI, DIFF: 1000-1200 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-420 PSI, BOTH CHOKES-100%, FLARE-5-10' ON BOTTOMS UP, NO MUD CUT.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 07:30 | 2020-06-04 08:30 | 1 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 27.83 | 16245 | 16273 | 28 | SLIDE (28' IN .83 HRS @ 33.7 FPH) WOB: 25-35, SPM: 60/60, GPM: 385, MMRPM: 262, SPP: 4100/4400 PSI, DIFF: 150-300 PSI. SLIDE DEPTHS: S.DRL F/16180' T/16200' @ 50R 0650-0730 (40MIN) S.DRL F/16265' T/16273' @ 30R 0803-0813 (10MIN)
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 08:30 | 2020-06-04 11:00 | 2.5 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 27.94 | 16273 | 16273 | 0 | DURING SLIDE WEIGHT ON BIT STACKED OUT AND PUMP PRESSURE INCREASED, ATTEMPTED TO PICK UP OFF BOTTOM WITH NO SUCCESS, HOLE PACKING OFF, ATTEMPTED TO ROTATE WITH 80 RPM AND ROTARY STALLED OUT @ 19K TORQUE AND HOLE PACKING OFF, WORK PIPE FREE, BACK REAM OUT THE HOLE F/16,273’ T/16,100’, HOLE WAS STILL PACKING OFF WHILE BACK REAMING, HOLE STOP PACKING OFF @ 16,100'
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 11:00 | 2020-06-04 12:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 27.98 | 16273 | 16273 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATED PIPE F/16,075’ T/16,100’, SPM: 60/60, GPM: 385, RPM: 80, TRQ: 5-7K, SPP: 3500 PSI.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 12:00 | 2020-06-04 14:30 | 2.5 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 28.08 | 16273 | 16273 | 0 | WASHED/REAMED F/16,100’ T/16,170’, PUMP 10 BBL SWEEP AND CIRCULATE HOLE CLEAN, WASHED/REAMED F/16,170’ T/16,180’, CIRCUALATE BOTTOMS UP, WASHED/REAMED F/16,180’ T/16,190’, CIRCUALATE BOTTOMS UP, SPM: 60/60, GPM: 385, RPM: 80, TRQ: 5-7K, SPP: 3200 PSI.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 14:30 | 2020-06-04 14:30 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 28.08 | 16273 | 16273 |  | MILESTONE_TD WELL ON 6/4/2020 @ 14:30
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 14:30 | 2020-06-04 15:00 | 0.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 28.1 | 16273 | 16273 | 0 | L/D 2 JOINTS, BACK REAMED F/16,190’ T/16,107’, SPM: 60/60, GPM: 385, RPM: 80, TRQ: 7-9K, SPP: 3200 PSI. NOTE: DECISION WAS MADE TO CALL TD @ 16,100’.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 15:00 | 2020-06-04 19:00 | 4 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 28.27 | 16273 | 16273 | 0 | CLEAN UP CYCLE @ TD: PUMP (3) 20 BBL SWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 5 B/U, RPM-80, TRQ-7/9K, SPM: 60/60, GPM-385, SPP-3200 PSI. 1ST SWEEP UP START TQ 8K END=7K, ROT.WT=240K 2ND SWEEP UP END TQ= 7K, ROT. WT.=240K 3RD SWEEP UP END TQ= 6K, ROT WT.=240K LOSS OF2K TORQUE FROM DOING CLEAN UP CYCLE, SHAKERS CLEAN.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 19:00 | 2020-06-04 22:30 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 28.42 | 16273 | 16273 | 0 | PUMP 50 BBL SLUG. OBSERVE PRESSURES(SPP-0 PSI / CSG PSI-540), POOH F/16,107' T/10232', FILLING ANNULUS W/CALCULATED FILL OF 16 PPG MUD. START CASING PSI 540, CASING PSI DECREASED TO 0 PSI - FILL ANNULUS WITH CALCULATED FILL OF 40.5 .BBLS.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 22:30 | 2020-06-04 23:30 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 28.46 | 16273 | 16273 | 0 | RIG SERVICE/ MONITOR CASING PRESSURE DURING RIG SERVICE.(0 PSI-CASING)
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-04 23:30 | 2020-06-05 | 0.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 28.48 | 16273 | 16273 | 0 | STRIP OUT OF HOLE F/10,232' T/9,285' FILLING BACKSIDE WITH CALCULATED FILL OF 9.8 PPG MUD.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-05 | 2020-06-05 01:30 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 28.54 | 16273 | 16273 | 0 | OPEN CHOKES AND FLOW CHECK (WELL STATIC), TRIP OUT THE HOLE F/9,285’ T/7,265 ON THE TRIP TANK. NOTE: FLOATS NOT HOLDING: WELL BEGAN FLOWING THROUGH DRILL PIPE @ 7,265'. PUMPED 30 BBL 15.5 PPG SLUG DOWN DP. LOST RETURNS WHILE PUMPING SLUG.
LEVI GOODRICH UNIT 2 2H | 35 | 2020-06-05 01:30 | 2020-06-05 06:00 | 4.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 28.73 | 16273 | 16273 | 0 | POOH F/7,265' T/1500'. FILLING BACKSIDE WITH CALCULATED FILL OF 9.8 PPG OBM. (NO RETURNS) REMOVE ROT. HEAD AND INSTALL TRIP NIPPLE @ 4,709'. L/D DOWN AGITATOR ON STAND 27.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 06:00 | 2020-06-05 07:00 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 28.77 | 16273 | 16273 | 0 | CONTINUE TRIPPING OUT THE HOLE F/1,500' T/BHA, FILLING BACKSIDE WITH CALCULATED FILL OF 9.8 PPG OBM. (NO RETURNS)
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 07:00 | 2020-06-05 07:30 | 0.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 28.79 | 16273 | 16273 | 0 | LAY OUT MWD, DRAIN MOTOR, BREAK BIT, L/D DIRECTIONAL TOOLS.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 07:30 | 2020-06-05 08:30 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 28.83 | 16273 | 16273 | 0 | PULL WEAR BUSHING, CLEAN AND ORGANIZE RIG FLOOR.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 08:30 | 2020-06-05 10:30 | 2 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 28.92 | 16273 | 16273 | 0 | HELD PJSM, RIG UP EXPRESS CASING TOOLS AND EQUIPMENT.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 10:30 | 2020-06-05 11:30 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 28.96 | 16273 | 16273 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING W/CENTRALIZERS IN MIDDLE OF JTS., 1 INNOVEX DV FLOAT COLLAR, GEO DYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING TEST FLOAT EQUIPMENT.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 11:30 | 2020-06-05 18:00 | 6.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.23 | 16273 | 16273 | 0 | PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/6,000', FILLING PIPE ON THE FLY, SOLID BODY CENTALIZERS EVERY 4TH JOINT, REGAINED PARTIAL RETURNS @ 3,055'.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 18:00 | 2020-06-05 18:30 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 29.25 | 16273 | 16273 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD @ 6,000'.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 18:30 | 2020-06-05 19:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 29.29 | 16273 | 16273 | 0 | SLOWLY STAGE UP, CIRCULATE BOTTOMS UP, GPM: 289, SPP: 690 PSI, FULL RETURNS, FLOW CHECK (WELL STATIC).
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 19:30 | 2020-06-05 20:30 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.33 | 16273 | 16273 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/6,000' T/6,670', FILLING PIPE ON THE FLY.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 20:30 | 2020-06-05 22:00 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 29.4 | 16273 | 16273 | 0 | SWAPPED OUT CASING TOOLS FROM 5" TO 5 1/2" HANDLING TOOLS, MONITOR WELL ON TRIP TANK (WELL STATIC).
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 22:00 | 2020-06-05 23:00 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 29.44 | 16273 | 16273 | 0 | TROUBLESHOOT CATWALK. (UNABLE TO OPERATE CATWALK INDEXERS FROM REMOTE ON RIG FLOOR.)
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-05 23:00 | 2020-06-06 04:00 | 5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.65 | 16273 | 16273 | 0 | MADE UP 5 1/2" MARKER JOINT TO CROSSOVER, PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 563 PRODUCTION CASING T/11,670', FILLING PIPE ON THE FLY. PROPER DISPLACEMENTS WHILE RUNNING CASING.
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-06 04:00 | 2020-06-06 05:30 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 29.71 | 16273 | 16273 | 0 | STARTED LOSING RETURNS WHILE RUNNING CSG IN HOLE. STAB CRT & CIRC @ 11,670'. STAGE MP UP FROM 80 GPM TO 112 GPM AS RETURNS GOT STRONGER, PP-950 PSI. WORK CASING 40' WHILE CIRCULATING. PARTIAL RETURNS WHILE CIRCULATING.-LOST APPROXIMATELY 180 BBLS DURING CIRCULATION
LEVI GOODRICH UNIT 2 2H | 36 | 2020-06-06 05:30 | 2020-06-06 06:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.73 | 16273 | 16273 | 0 | RUN 5-1/2" CSG F/11,670' T/12,000'. RUNNING IN HOLE AT CONTROLLED RATE (75'/HR) TO REDUCE SURGE PRESSURES-NO RETURNS
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 06:00 | 2020-06-06 07:30 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.79 | 16273 | 16273 | 0 | RUN CASING F/12,000' T/13,580', REGAINED PARTIAL RETURNS @ 13,165'.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 07:30 | 2020-06-06 08:00 | 0.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 29.81 | 16273 | 16273 | 0 | CIRCULATE @ 13,580'. WORK PIPE WHILE ATTEMPTING TO REGAIN CIRCULATION. GPM-96, PP-1050 PSI, FLOW-(1-2%) OBSERVED PARTIAL RETURNS-ESTIMATED 40%. LOSS 50 BBLS.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 08:00 | 2020-06-06 11:00 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.94 | 16273 | 16273 | 0 | RUN 5-1/2" PRODUCTION CASING F/13,580' T/16,102.14'. REGAINED PARTIAL RETURNS @ 15,434', 'REMOVE ROTATING HEAD, P/U LANDING JOINT AND LAND CASING ON HANGER W/130K. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: 1- INNOVEX 5''FLOAT SHOE, 2 JTS OF 5'' CSG. 1- INNOVEX FLOAT COLLAR, 1- GEODYNAMICS TOE SLEEVE VALVE, RAN 6,565.44' (155 JT) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER & 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING, RAN 9,380.38' (203 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING . FOR TOTAL OF 442 FULL JTS OF 5'' 18# P-110, ICY WEDGE 625 & 5.5" 23# P-110 ICY BLUE CASING. TOTAL OF 360 FULL JTS OF 5'' 18# P-110, ICY WEDGE 625 & 5 1/2" 23# P-110 ICY WEDGE 563 CASING. CASING SHOE @ 16,102.14' TOP OF FLOAT COLLAR @ 16,013.44' BOTTOM OF TOE SLEEVE VALVE @ 16,013.44' TOP OF TOE SLEEVE VALVE @ 15,997.99' TOP OF X-OVER @ 9,429.72' TOP OF MARKER JOINT ABOVE X-OVER @ 9,409.41' 51 JOINTS 5" OUT, (5 BAD BOXES) TOTAL LENGTH 2135.22' 9 JOINTS 5 1/2" OUT, (2 BAD PIN) TOTAL LENGTH 417.04’
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 11:00 | 2020-06-06 11:30 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 29.96 | 16273 | 16273 | 0 | RIG DOWN EXPRESS CRT INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 11:30 | 2020-06-06 14:00 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 30.06 | 16273 | 16273 | 0 | RIG DOWN EXPRESS CASING TOOLS, CIRCULATE BOTTOMS DOWN THE FLOW LINE WITH PARTIAL RETURNS -ESTIMATED 27%, REGAINED FULL RETURNS @ 3260 STKS, SHUT IN WELL AND CONTINUE CIRCULATING THROUGH BOTH CHOKES-100% OPEN, SPM-35, GPM-112, SPP- 1000 PSI, MAX GAS: 2407 UNITS, LOSS 172 BBLS, SLOWLY STAGE PUMPS UP AFTER BOTTOMS UP, SPM-100, GPM-321, SPP- 1820 PSI, SHUT IN AND MONITOR SICP, SICP=400 PSI WHILE SWAPPING CIRCULATE IRON T/CEMENT STAND PIPE.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 14:00 | 2020-06-06 16:00 | 2 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 30.15 | 16273 | 16273 | 0 | CEMENT 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: 50 BBL 12 PPG WEIGHTED SPACER. 209 BBL 13.5 PPG 690 SK 1.7 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 317 BBLS OF FRESH WATER WITH BIOCIDE AND CORPLEX @ 8 BPM, OBSERVED PARTIAL RETURNS WITH 220 BBLS PUMPED AWAY AND SLOW DOWN TO 6 BPM, AT 300 BBLS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2500 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3500 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 4 BBLS. FLOATS HELD. PLUG DOWN @ 16:10 HRS 06/06/2020, LOST APPROXIMATELY 120 BBLS DURING CEMENT JOB.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 16:00 | 2020-06-06 17:00 | 1 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 30.19 | 16273 | 16273 | 0 | SHUT IN WELL, RIGGED DOWN DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, SICP= 0 PSI.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 17:00 | 2020-06-06 19:30 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 30.29 | 16273 | 16273 | 0 | BACK OUT & LAY DOWN LANDING JOINT, RIGGED DOWN CASING BAILS & ELEVATORS, MADE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, P/U JT OF DP & PACK-OFF, INSTALLED STREAM FLO PACKOFF & TEST T/ 5000 PSI, INSTALL BPV.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 19:30 | 2020-06-06 22:30 | 3 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 30.42 | 16273 | 16273 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE & INSTALL WEATHER CAP AND SECURE WELL. RELEASE WELL @ 22:30 HRS 06/06/2020.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 22:30 | 2020-06-06 23:30 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 30.42 | 16273 | 16273 | 0 | RIG SERVICE
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 22:30 | 2020-06-06 22:30 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 30.42 | 16273 | 16273 |  | MILESTONE_WELL RELEASE 06/06/2020 22:30
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-06 23:30 | 2020-06-07 03:30 | 4 | P | MOBDMOB | RIGMT | CUTDL | SLIP / CUT DRL LINE | 30.42 | 16273 | 16273 | 0 | SLIP AND CUT DRILL LINE, CHANGE SAVER SUB, CHANGE HPU ON TOP DRIVE.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-07 03:30 | 2020-06-07 06:00 | 2.5 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 30.42 | 16273 | 16273 | 0 | PREP RIG TO WALK, REMOVE VIBRATOR HOSES, KILL LINE, PICK UP V-DOOR, WALK CATWALK FORWARD, AND SET MATS.
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-07 06:00 | 2020-06-07 06:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 30.42 | 16273 | 16273 |  | MILESTONE_TURN OVER TO COMPLETION 06/07/2020 06:00
LEVI GOODRICH UNIT 2 2H | 37 | 2020-06-07 06:00 | 2020-06-07 06:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 30.42 | 16273 | 16273 |  | MILESTONE_RIG RELEASE 06/07/2020 06:00
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 10:59 | 2020-04-27 11:59 | 1 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPPED RIG TO WALK TO THE LEVI GOODRICH 2 3H, SWAP HYDRAULICS TO WALKING SYSTEM, WALKED RIG AND CATWALK 20' TO THE LEVI GOODRICH 2 3H, CENTERED AND LEVELED SUB OVER CONDUCTOR. R/U AIR, WATER, AND VIBRATOR HOSES. CENTER CATWALK, SET MOUSEHOLE, L/D LANDING JOINT, CASING BAILS & ELEVATORS, AND RIG UP RIG ELEVATORS.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 10:59 | 2020-04-27 10:59 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 04/27/2020 @ 11:00
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 11:59 | 2020-04-27 13:29 | 1.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | RIG UP AIR AND WATER LINES, WALK PIPE WRANGLER IN POSITION AND LOWER V-DOOR, SET CLIMB ASSIST AND JERONIMO LINE.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 13:29 | 2020-04-27 14:29 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | INSTALL CONDUCTOR RISER AND 3RD PARTY CELLAR PUMPS.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 14:29 | 2020-04-27 15:29 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE AND BLOCK.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 15:29 | 2020-04-27 16:29 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | MAKE UP BHA, INSTALL MWD TOOL AND TEST, TEST GOOD, MAKE UP MONEL DRILL COLLAR.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 16:29 | 2020-04-27 16:59 | 0.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.02 | 108 | 403 | 590 | ROT F/108 T/403 400 GPM, 40 RPM TO GET BHA OUT OF CONDUCTOR
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 16:29 | 2020-04-27 16:29 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL 4/27/2020 @ 16:30
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 16:59 | 2020-04-27 19:29 | 2.5 | U | SFHL | LOG | MWD | MWD | 0.12 | 403 | 403 | 0 | MWD NOT PUMPING UP SURVEYS, TROUBLE SHOOT MWD TOOL, POOH CHANGE MWD, TIH W/NEW MWD TOOL
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 19:29 | 2020-04-27 23:59 | 4.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.31 | 403 | 2950 | 566 | ROTATE (2547' IN 4.68 HRS @ 544 FPH) WOB-15/30K, RPM-100, TRQ- 12/17K, SPM-100/100, GPM-800, MMRPM-133, TRPM-233, SPP-2000/2400 PSI, DIFF-500/900 PSI.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-27 23:59 | 2020-04-28 01:29 | 1.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.37 | 2950 | 3000 | 33.3 | SLIDE (50' IN 1.32 HRS @ 38 FPH) WOB: 20/30K, SPM: 100/100 GPM: 800, MMRPM:133, SPP- 1700/2000 PSI, DIFF- 200/400 PSI. TD SURFACE SLIDE DEPTHS: SLD F/878' T/888' 10' TF-200M 20;16-20;31 SLD F/1256' T/1266' 10' TF-220M 21;08-21;15 SLD F/1535' T/1545' 10' TF-330M 21;47-21;56 SLD F/1818' T/1828' 10' TF-85M 22;28-23;06 SLD F/2570' T/2580' 10' TF-180M 00;44-00;54
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-28 01:29 | 2020-04-28 02:29 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.42 | 3000 | 3000 | 0 | PUMP 2-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-800, RPM-100, TRQ-3/5K, SPP-1700 PSI.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-28 02:29 | 2020-04-28 04:59 | 2.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.52 | 3000 | 3000 | 0 | TRIP OUT OF HOLE F/3,000' T/ BHA, L/D TOP MONEL, REMOVE MWD TOOL, DRAIN MOTOR, RACK BHA BACK IN DERRICK, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
LEVI GOODRICH UNIT 2 3H | 2 | 2020-04-28 04:59 | 2020-04-28 05:59 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.56 | 3000 | 3000 | 0 | PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 06:00 | 2020-04-28 10:30 | 4.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.75 | 3000 | 3000 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR,1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 71 JOINTS OF10 3/4" 45.5# J-55 T/2991', RAN 20 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY 4TH JT. ALL THE WAY TO 155.66', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 65" BELOW GROUND LEVEL. (WASH DOWN LANDING JOINT AND SET 80K ON BASE PLATE) SHOE: 2989.06' TOP OF FLOAT COLLAR: 2905.81' 7 JTS OUT - 279.74'
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 10:30 | 2020-04-28 11:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.77 | 3000 | 3000 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT @ 10 BPM WITH 375 PSI, RIG DOWN CASING TOOLS, NO LOSSES.
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 11:00 | 2020-04-28 11:30 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.79 | 3000 | 3000 | 0 | PJSM, RIG DOWN CRT
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 11:30 | 2020-04-28 13:00 | 1.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.79 | 3000 | 3000 | 0 | WALK RIG AND RIG UP CEMENT HEAD AND CIRCULATING IRON
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 11:30 | 2020-04-28 11:30 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.79 | 3000 | 3000 |  | MILESTONE_HOLD WELL OPERATIONS 1 4/28/2020 @ 11:30
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 13:00 | 2020-04-28 15:30 | 2.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.79 | 3000 | 3000 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 25 BBL 8.3 PPG FRESH WATER SPACER, 322 BBLS 11.6 PPG LEAD CEMENT, 86 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 280 BBLS OF 9.5 PPG OIL BASE MUD. BUMPED PLUG W/ 880 PSI PRESSURED UP T/ 1300PSI (420 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 30 BBLS OF SPACER AND 230 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 15:30 | 2020-04-28 16:00 | 0.5 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.79 | 3000 | 3000 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI (PRESSURE HELD TEST WAS GOOD)
LEVI GOODRICH UNIT 2 3H | 3 | 2020-04-28 16:00 | 2020-04-28 17:00 | 1 | R | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 0.79 | 3000 | 3000 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-04 13:29 | 2020-05-04 13:29 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.79 | 3000 | 3000 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 5/4/2020 @ 13:30
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-04 13:29 | 2020-05-04 15:59 | 2.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.9 | 3000 | 3000 | 0 | PREPPED RIG TO WALK TO LEVI GOODRICH 2 3H, SWAP HYDRAULICS TO WALKING SYSTEM, WALK RIG, CENTERED AND LEVELED SUB OVER WELLHEAD, WITNESSED RIG CENTER OVER WELL
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-04 15:59 | 2020-05-04 19:59 | 4 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.06 | 3000 | 3000 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, UNLATCHED BOP WRANGLER FROM BOP'S & LAID OVER SAME, INSTALLED TURNBUCKLES & CENTERED STACK. REMOVE DAMAGED FLOWLINE FLEX SLEEVE AND REPLACE WITH NEW. HOOK UP FLOWLINE. REMOVE CASING RAMS AND INSTALL VARIABLE RAMS, R/U KILL LINE AND REPLACE DAMAGED ACCUMULATOR HYDRAULIC LINE WITH NEW.
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-04 19:59 | 2020-05-04 20:59 | 1 | P | SFHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 1.1 | 3000 | 3000 | 0 | REMOVE TD HYD PUMP AND REPLACE WITH NEW. FILL TD WITH HYDRAULIC OIL.
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-04 20:59 | 2020-05-05 00:59 | 4 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.27 | 3000 | 3000 | 0 | MAKE UP TEST PLUG TO JOINT DRILL PIPE AND SET, FILL STACK, TEST BOP 250L/5000H. TEST WH/BOP, TOP RAMS, KILL LINE, AND CHECK VALVE. CHANGE OUT LEAKING 2" ON KILL LINE AND RE-TEST=GOOD. R/D TESTERS
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-05 00:59 | 2020-05-05 01:29 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.29 | 3000 | 3000 | 0 | INSTALL WEAR BUSHING
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-05 01:29 | 2020-05-05 01:59 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.31 | 3000 | 3000 | 0 | CLEAN RIG FLOOR AND PREP TO P/U BHA
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-05 01:59 | 2020-05-05 03:29 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.37 | 3000 | 3000 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 9/14'S TFA: 1.353) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.12° SLICK; .166 REV/GAL; 5.62' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 8" UBHO, 2-8" NMDC,1- X/O, BIT TO SENSOR-70', TEST MWD ( GOOD TEST).
LEVI GOODRICH UNIT 2 3H | 4 | 2020-05-05 03:29 | 2020-05-05 05:59 | 2.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.48 | 3000 | 3000 | 0 | TRIP IN THE HOLE F/BHA T/2,911' -(P/U AGITATOR ON STAND 22) (BEFORE 950 PSI AFTER 1060 PSI), REMOVE TRIP NIPPLE / INSTALL ROTATING HEAD. TRIP DRILL RESPONSE TIME-45 SECONDS
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-05 06:00 | 2020-05-05 08:00 | 2 | P | SFHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 1.56 | 3000 | 3000 | 0 | CUT/SLIP DRILLING LINE 11 WRAPS-110'
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-05 08:00 | 2020-05-05 08:30 | 0.5 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.58 | 3000 | 3000 | 0 | RIG SERVICE
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-05 08:30 | 2020-05-05 09:00 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.6 | 3000 | 3010 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/ 3000' T/ 3010'. GPM-422, SPP-1200 PSI, RPM-50, DIFF-150 PSI
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-05 09:00 | 2020-05-05 09:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.62 | 3010 | 3010 | 0 | CIRCULATE BOTTOMS UP GPM-461, SPP-1480 PSI, RPM-40
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-05 09:30 | 2020-05-05 10:00 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.65 | 3010 | 3010 | 0 | PERFORM F.I.T.WITH 9.5 PPG MUD, 326 PSI SURFACE PRESSURE FOR 11.6 PPG EMW. SHOE MD-2,989' TVD-2,989'.
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-05 10:00 | 2020-05-06 02:00 | 16 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.31 | 3010 | 7707 | 293.6 | ROT (4707' IN 16.2 HRS @ 290 FPH) WOB: 35/45K, SPM: 96/96, GPM: 738, MMRPM: 123, RPM: 80, TRPM: 203, TRQ: 6K/18K, SPP: 3900/4900 PSI, DIFF: 800/1000 PSI.
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-06 02:00 | 2020-05-06 05:30 | 3.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.46 | 7707 | 7945 | 68 | SLIDE (238' IN 3.3 HRS @ 72 FPH) WOB: 5/10K, SPM: 96/96, GPM: 738, MMRPM: 123, SPP: 3900/4300 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: F/3160' T/3178' @ 60MAG 1032-1039 7MIN F/3445' T/3460' @ 55MAG 1119-1125 6MIN F/4010' T/ 4025' @ 30L 1322-1330 8MIN F/4285' T/4297' @ 90L 1438-1443 5MIN F/4665' T/4680' @ 160R 1600-1607 7MIN F/4850' T/4865' @120R 1642-1651 (9MIN) F/5040' T/5055' @180 1732-1742 10MIN F/5225-T/5245,TF/180,20'/11MIN 1816-1827 F/5593-T/5611,TF/180,18'/13MIN 1932-1945 F/6450-T/6460,TF/200,10'/16MIN 2230-2246 F/6825-T/6850,TF/200,25'/MIN 2359-0020 F/7015-T/7040,TF/210,25'/39MIN 0057-0136 F/7390-T/7410,TF/180,20'/21MIN 0252-0313 F/7765-T/7795,TF/170,30'/MIN 0431-0456
LEVI GOODRICH UNIT 2 3H | 5 | 2020-05-06 05:30 | 2020-05-06 06:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.48 | 7945 | 7945 | 0 | RIG SERVICE/ TIGHTEN HEX HEAD ON TIW
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 06:00 | 2020-05-06 10:00 | 4 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.65 | 7945 | 9408 | 365.8 | ROT (1463' IN 5.37 HRS @ 272 FPH) WOB: 35/45K, SPM: 91/91, GPM: 700, MMRPM: 116, RPM: 80, TRPM: 196, TRQ: 6K/18K, SPP: 3800/4700 PSI, DIFF: 700/900 PSI.
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 10:00 | 2020-05-06 12:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.73 | 9408 | 9463 | 27.5 | SLIDE (55' IN .63 HRS @ 87 FPH) WOB: 15/30K, SPM: 100/100, GPM: 769, MMRPM: 128, SPP: 3800/4200 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: S.DRL F/8145' T/8170 @ 150 MAG 0646-0704 18MIN S.DRILL F/8610' T/8640' @ 150MAG 0830-0850 20MIN START INTERMEDIATE CURVE SECTION ON 5/6/20 @ 12:00 (9,463' MD / 9,449' TVD)
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 12:00 | 2020-05-06 15:30 | 3.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.87 | 9463 | 9963 | 142.9 | ROT (500' IN 3.27 HRS @ 153 FPH) WOB: 35/45K, SPM: 92/92, GPM: 708, MMRPM: 117, RPM: 80, TRPM: 197, TRQ: 15K/19K, SPP: 3800/4600 PSI, DIFF: 600/800 PSI.
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 15:30 | 2020-05-06 18:30 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3 | 9963 | 10195 | 77.3 | SLIDE (232' IN 2.83 HRS @ 67 FPH) WOB: 15/30K, SPM: 100/100, GPM: 769, MMRPM: 128, SPP: 4400/4600 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/9463' T/9490' @ 330MAG 1158-1224' 26MIN F/9634' T/9664' @ 9664' @ HS 1310-1338 28MIN F/9728' T/9768' @ HS 1402-1436 34MIN F/9822' T/9852' @ HS 1507-1541 34MIN F/ 9917' T/9962' @ HS 1609-1657 48MIN F10105' T/10130' @ HS 1740-1800 20MIN F/10130-T/10165,TF/HS,35'/27MIN 1800-1827
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 18:30 | 2020-05-06 19:30 | 1 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.04 | 10195 | 10195 | 0 | RIG SERVICE/ RIG SHUT DOWN, CHANGE FUEL FILTERS, RECALIBRATE DW, SYNC UP MWD.
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 19:30 | 2020-05-06 20:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.06 | 10195 | 10199 | 8 | ROT (4' IN .17 HRS @ 24 FPH) WOB: 35/45K, SPM: 92/92, GPM: 708, MMRPM: 117, RPM: 80, TRPM: 197, TRQ: 15K/19K, SPP: 3800/4600 PSI, DIFF: 600/800 PSI.
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 20:00 | 2020-05-06 21:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.1 | 10199 | 10245 | 46 | SLIDE (46' IN 1.33 HRS @ 35 FPH) WOB: 15/30K, SPM: 100/100, GPM: 769, MMRPM: 128, SPP: 4400/4600 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: F/10199-T/10245,TF/HS,'/MIN 1940-2100
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 21:00 | 2020-05-06 22:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.17 | 10245 | 10245 | 0 | PUMP 2-30 BBL LCM SWEEP IN TANDEM, CIRCULATE BOTTOMS UP @ 780 GPM, SPP-4450, NO ROTATION- LINE UP HIGH SIDE AND WORK PIPE, FLOW CHECK WELL, WELL STATIC, PUMP SLUG.
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-06 22:30 | 2020-05-07 04:00 | 5.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.4 | 10245 | 10245 | 0 | TRIP OUT THE HOLE F/10,245' T/BHA', HOLE TAKING PROPER FILL.
LEVI GOODRICH UNIT 2 3H | 6 | 2020-05-07 04:00 | 2020-05-07 06:00 | 2 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.48 | 10245 | 10245 | 0 | RACK BACK HWDP AND DRILL COLLARS. L/D TOP MONEL AND REMOVE MWD. DRAIN MOTOR AND L/D BIT AND MOTOR. P/U NEW MOTOR AND RACK BACK.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 06:00 | 2020-05-07 06:30 | 0.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 3.5 | 10245 | 10245 | 0 | CONTINUE PICKING UP NEW MOTOR AND RACK BACK.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 06:30 | 2020-05-07 07:00 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 3.52 | 10245 | 10245 | 0 | REMOVED WEAR BUSHING & PREPPED RIG FLOOR FOR CASING RUN.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 07:00 | 2020-05-07 08:00 | 1 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 3.56 | 10245 | 10245 | 0 | REMOVE VBR PIPE RAMS AND INSTALL 7-5/8" CASING RAMS, TEST RAMS.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 08:00 | 2020-05-07 09:30 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.62 | 10245 | 10245 | 0 | HELD PJSM, RIGGED UP EXPRESS ENERGY'S CASING CREW TOOLS AND EQUIPMENT.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 09:30 | 2020-05-07 21:00 | 11.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.1 | 10245 | 10245 | 0 | HELD PJSM THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 224 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 44 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 2,834.68' . PICKED UP 2 EXTRA JT'S & TAGGED BOTTOM AT 10245' MD (2' IN ON 2ND JT), L/D 2 JTS OF CSG, P/U LANDING JOINT, LANDED CSG ON CSG MANDREL W/210K (W/O BLOCKS), SW-350K, S/O-260K, P/U-430K. FLOAT SHOE-10,237.28' TOP OF FLOAT COLLAR-10,143.44'. ONCE LANDED. ESTABLISHED RETURNS THRU CRT TOOL AND CIRC FOR 10 MIN.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 21:00 | 2020-05-07 21:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 4.12 | 10245 | 10245 | 0 | RIG DOWN EXPRESS CASING TOOLS AND EQUIPMENT.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 21:30 | 2020-05-07 22:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.17 | 10245 | 10245 | 0 | RIG UP NINE ENERGY CEMENT HEAD AND CIRCULATE WITH RIG PUMPS FULL CASING CAPACITY. GPM-338, SPP-550 PSI.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-07 22:30 | 2020-05-08 01:00 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.27 | 10245 | 10245 | 0 | CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG GTX SPACER. 285 BBL 11.8 PPG 825 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT. 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 466 BBLS OF 9.8 PPG OIL BASE MUD, @ 440 BBLS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 1800 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2300 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 3.5 BBLS. FLOATS HELD. PLUG DOWN @ 01:05 HRS 05/08/2020, GOT BACK 5 BBLS OF SPACER BACK TO SURFACE, & HAD FULL RETURNS ENTIRE CEMENTING JOB
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-08 01:00 | 2020-05-08 01:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.29 | 10245 | 10245 | 0 | PRESSURE TESTED CASING TO 3500 PSI F/15 MINUTES. (PRESSURE HELD & TEST WAS GOOD)
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-08 01:30 | 2020-05-08 02:30 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.33 | 10245 | 10245 | 0 | RIGGED DOWN CEMENTING EQUIPMENT, BROKE OUT & LAID DOWN LANDING JOINT, RIGGED DOWN CASING BAILS & ELEVATORS.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-08 02:30 | 2020-05-08 04:00 | 1.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.4 | 10245 | 10245 | 0 | MADE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP & MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 10K, BROKE OUT & LAID DOWN SETTING TOOL.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-08 04:00 | 2020-05-08 05:00 | 1 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.44 | 10245 | 10245 | 0 | NIPPLED DOWN BOPE, ATTACHED BOP WRANGLER, LIFTED STACK & MOVED AWAY FROM WELLHEAD.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-08 05:00 | 2020-05-08 06:00 | 1 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.48 | 10245 | 10245 | 0 | INSTALLED WELLHEAD CAP ON LEVI GOODRICH 2-3H WELLHEAD, SECURE WELL AND PUT WELL ON HOLD AT 06:00.
LEVI GOODRICH UNIT 2 3H | 7 | 2020-05-08 06:00 | 2020-05-08 06:00 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 4.48 | 10245 | 10245 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 5/8/20 @ 06:00
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-07 06:00 | 2020-06-07 06:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 4.48 | 10245 | 10245 | 0 | MILESTONE_RESUME WELL OPERATIONS 2 ON 6/7/2020 @ 06:00
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-07 06:00 | 2020-06-07 07:30 | 1.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 4.54 | 10245 | 10245 | 0 | WALK RIG F/ THE LEVI GOODRICH 2-2H T/ THE LEVI GOODRICH 2-3H, CENTERED AND LEVELED SUB OVER WELLHEAD, WITNESSED RIG CENTER OVER WELL.
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-07 07:30 | 2020-06-07 09:00 | 1.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.6 | 10245 | 10245 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALLED TURNBUCKLES & CENTERED STACK. HOOK UP FLOWLINE, REMOVE KILL LINE CHECK VALVE, R/U KILL LINE.
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-07 09:00 | 2020-06-07 09:30 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.62 | 10245 | 10245 | 0 | PERFORM ACCUMULATOR DRAW DOWN TEST.
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-07 09:30 | 2020-06-08 01:00 | 15.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.27 | 10245 | 10245 | 0 | DURING TEST JOB HAD MULTIPLE FAILURES. HYDRIL WOULD NOT TEST-MULTIPLE ATTEMPTS, UPPER VBR'S WOULD NOT TEST-MULTIPLE ATTEMPTS, SUPERCHOKE FAILED-HAD REBUILT AND RE-TESTED-GOOD. CHANGED OUT TEST PLUG TO INSURE THAT RAMS AND ANNULAR WERE LEAKING. ISOLATED TESTING UNIT AND TESTED TO 10,000 PSI-GOOD. HELD PJSM WITH REM TORQUE TESTERS, RIG UP TESTERS, FILL STACK WITH WATER, TESTED BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 5000 HIGH, ATTEMPTED TEST HYDRIL 250 LOW / 3500 HIGH (PRESSURE BLED OFF T/1500 PSI). INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH.
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-08 01:00 | 2020-06-08 04:00 | 3 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 5.4 | 10245 | 10245 | 0 | REMOVE BOP TURNBUCKLES, ORBIT VALVE, AND KATCH KAN CONTAINMENT SYSTEM. SERVICE TECH REMOVED NUTS FROM ANNULAR AND REMOVED CAP, REPLACED ELEMENT, AND INSTALLED CAP. TORQUE NUTS ON ANNULAR.
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-08 04:00 | 2020-06-08 05:00 | 1 | U | INTHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 5.44 | 10245 | 10245 | 0 | BACK OUT AND OPEN UPPER PIPE RAM DOORS, REMOVE VBR'S AND REPLACE INSERTS AND OPEN TOP SEALS. REPLACE DOOR SEALS AND CLOSE RAM DOORS. TIGHTEN RAM DOOR BOLTS.
LEVI GOODRICH UNIT 2 3H | 8 | 2020-06-08 05:00 | 2020-06-08 06:00 | 1 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.48 | 10245 | 10245 | 0 | INSTALL TEST PLUG AND TEST ANNULAR(250 LOW / 3500 HIGH). TEST UPPER 5 1/2" VBR'S (250 LOW / 10,000 HIGH). BOTH TEST GOOD.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 06:00 | 2020-06-08 07:00 | 1 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.52 | 10245 | 10245 | 0 | TEST UPPER VBR WITH 4-1/2" DP (250 LOW / 10,000 HIGH) ANNULAR (250 LOW / 3500 HIGH)
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 07:00 | 2020-06-08 10:00 | 3 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.65 | 10245 | 10245 | 0 | NIPPLE UP ORBIT VALVE, FLOWLINE, DRIP PAN AND TURNBUCKLES.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 10:00 | 2020-06-08 10:30 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 5.67 | 10245 | 10245 | 0 | TEST ORBIT VALVE AND ROTATING HEAD T/1500 PSI. R/D TESTERS.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 10:30 | 2020-06-08 11:00 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.69 | 10245 | 10245 | 0 | INSTALL WEAR BUSHING AND PREP FLOOR FOR BHA
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 11:00 | 2020-06-08 12:00 | 1 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 5.73 | 10245 | 10245 | 0 | L/D DIRECTIONAL BHA OUT OF DERRICK.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 12:00 | 2020-06-08 14:00 | 2 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.81 | 10245 | 10245 | 0 | PICK UP 6.75" ULTERRA U611S SER 47380: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.04' BIT TO BEND 5-5/16" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-66'. BIT TO GAMMA-56', TEST MWD (TEST GOOD).
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 14:00 | 2020-06-08 19:30 | 5.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.04 | 10245 | 10245 | 0 | TRIP IN HOLE F/BHA T/10,085'. PICK UP AGITATOR AFTER STAND 27, PSI BEFORE AGITATOR- 800 / PSI AFTER AGITATOR- 1180, PROPER DISPLACEMENTS ON TRIP IN HOLE. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 19:30 | 2020-06-08 21:30 | 2 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.12 | 10245 | 10245 | 0 | RIG SERVICE AND CHANGE OUT SWIVEL PACKING.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 21:30 | 2020-06-08 22:30 | 1 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 6.17 | 10245 | 10245 | 0 | DRILL OUT SHOE TRACK T/10,245'.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 22:30 | 2020-06-08 23:00 | 0.5 | U | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.19 | 10245 | 10245 | 0 | REBUILT SWIVEL PACKING LEAKING-CHANGE OUT
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 23:00 | 2020-06-08 23:30 | 0.5 | P | INTHLCSG | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.21 | 10245 | 10249 | 8 | DRILL FROM F/10245' T/10,249'. (SWIVEL PACKING BEGAN LEAKING)
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-08 23:30 | 2020-06-09 01:30 | 2 | U | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.29 | 10249 | 10249 | 0 | REBUILT SWIVEL PACKING LEAKING-CHANGE OUT
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-09 01:30 | 2020-06-09 02:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.33 | 10249 | 10255 | 6 | DRILL F/10249 T/10,255' AND CIRCULATE BOTTOMS UP FOR F.I.T., FILL GAS BUSTER.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-09 02:30 | 2020-06-09 03:00 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.35 | 10255 | 10255 | 0 | PERFORM F.I.T. TO 13.0 PPG EMW, 1591 PSI W/10 PPG MW @ 10,237' MD / 10,204' TVD.
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-09 03:00 | 2020-06-09 03:00 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.35 | 10255 | 10255 |  | MILESTONE_START CURVE SECTION ON 6/9/2020 @ 03:00
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-09 03:00 | 2020-06-09 05:30 | 2.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.46 | 10255 | 10352 | 38.8 | BUILD CURVE-SLIDE (97' IN 2.5 HRS @ 39 FPH) WOB: 30/40, SPM: 55/55, GPM: 353, MMRPM:240, SPP: 3400/3900 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: S.DRL F/10255 T/10299' @ H.SIDE 0300-0348,48MIN S.DRL F/10309' T/10362' @H.SIDE 0420-0520 60MIN
LEVI GOODRICH UNIT 2 3H | 9 | 2020-06-09 05:30 | 2020-06-09 06:00 | 0.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.48 | 10352 | 10393 | 82 | BUILD CURVE-ROT (41’ IN .5 HRS @ 82 FPH) WOB: 20/25K, SPM: 55/55, GPM: 353, RPM: 25, MMRPM: 240, TRPM: 265, TRQ: 6/8K, SPP: 3400/4100 PSI, DIFF: 500/600 PSI.
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 06:00 | 2020-06-09 10:00 | 4 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.65 | 10393 | 10723 | 82.5 | BUILD CURVE-SLIDE (330' IN 4.13 HRS @ 79.9 FPH) WOB: 25/35, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 4000/4600 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: S.DRL F/10435 T/10488 20R 0630-0713 (43MINS) S.DRL F/10528 T/10583 20R 0745-0830 (45MINS) S.DRL F/10595 T/10666 30R 0900-0945 (45MINS) S.DRL F/10685 T/10771 20R 0951-1051 (1HR) S.DRL F/10830 T/10865 30L 1125-1200 (35MIN) S.DRL F/10930 T/10960 HS 1300-1320 (20MINS)
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 10:00 | 2020-06-09 13:30 | 3.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.79 | 10723 | 11055 | 94.9 | BUILD CURVE-ROT (332' IN 3.62 HRS @ 91.7 FPH) WOB: 20/25K, SPM: 62/62, GPM: 400, RPM: 35, MMRPM: 272, TRPM: 307, TRQ: 7/9K, SPP: 4000/5200 PSI, DIFF: 1000/1200 PSI. NOTE: SHUTTING IN ON CONNECTION, MAX SICP= 320 PSI @ 10,877', MAX CP= 0 PSI, 5-10' FLARE AND MUD CUT 9.8 PPG T/9.7 PPG.
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 13:30 | 2020-06-09 13:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.79 | 11055 | 11055 |  | MILESTONE_LAND/END CURVE SECTION ON 6/9/2020 @ 13:30
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 13:30 | 2020-06-09 15:30 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.87 | 11055 | 11325 | 135 | ROT (270’ IN 2.22 HRS @ 121.6 FPH) WOB: 25/35K, SPM: 62/62, GPM: 400, RPM: 80, MMRPM: 272, TRPM: 352, TRQ: 8/11K, SPP: 4000/5200 PSI, DIFF: 900/1100 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-0 PSI, BOTH, MAX CP- 0 PSI, CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT.
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 13:30 | 2020-06-09 13:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.79 | 11055 | 11055 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 6/9/2020 @ 13:30
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 15:30 | 2020-06-09 16:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.9 | 11325 | 11350 | 50 | SLIDE (25’ IN .28 HRS @ 89.3 FPH) WOB: 25/35, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 4000/4600 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: S.DRL F/11160 T/11185 90R 1443-1500 (17MINS)
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 16:00 | 2020-06-09 17:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.94 | 11350 | 11350 | 0 | RIG SERVICE.
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-09 17:00 | 2020-06-10 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.23 | 11350 | 12163 | 116.1 | ROT (813’ IN 6.88 HRS @ 118 FPH) WOB: 25/40, SPM: 55/55, GPM: 353, RPM: 80, MMRPM: 240, TRPM: 320, TRQ: 8/11K, SPP: 3400/4400 PSI, DIFF: 900/1100 PSI. CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT. NOTE: ENCOUNTERED SEEPGAGE LOSSES @ 12,100', DECREASED PUMP RATE F/400 GPM T/380 GPM, LOSS 140 BBLS, CUT MUD WT. F/9.8 PPG T/9.7 PPG (NO LOSSES).
LEVI GOODRICH UNIT 2 3H | 10 | 2020-06-10 | 2020-06-10 06:00 | 6 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.48 | 12163 | 12327 | 27.3 | SLIDE (164’ IN 5.87 HRS @ 28 FPH) WOB: 30/50, SPM: 55/55, GPM: 353, MMRPM: 240, SPP: 3400/4000 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: S.DRL F/11350 T/11370 160R 1715-1735 (20MINS) S.DRL F/11450' T/11470' @ 150G 1814-1847, 33MIN S.DRL F/11645' T/11665' @ H.SIDE 2012-2048, 36MIN S.DRL F/11818' T/11845' @ 180G 2210-2258, 48MIN S.DRL F/12010' T/12045' @ 180G 0016-0113, 57MIN S.DRL F/12110' T/12125' @ 180G 0150-0223, 33MIN S.DRL F/12300' T/12327' @ 180G 0355-0600, 125MIN
LEVI GOODRICH UNIT 2 3H | 11 | 2020-06-10 06:00 | 2020-06-10 18:00 | 12 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.98 | 12327 | 13898 | 130.9 | ROT (1571’ IN 12 HRS @ 131 FPH) WOB: 30/40, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 8/14K, SPP: 4400/4600 PSI, DIFF: 800/1000 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-0 PSI. BOTH CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT. NOTE: ENCOUNTERED SEEPGAGE LOSSES @ 12,690', LOSSES @ 30 BPH, CUT MUD WT. F/9.7 PPG T/9.6 PPG, LOSSES STOP @ 12,800', CUT MUD WT. F/9.6 PPG T/9.5 PPG @ 13,060'. CUT WT.F/9.5 PPG T/9.4 PPG @ 13,733', CUT MT. F/9.4 PPG T/9.2 PPG @ 13,847'
LEVI GOODRICH UNIT 2 3H | 11 | 2020-06-10 18:00 | 2020-06-11 02:30 | 8.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.33 | 13898 | 14093 | 22.9 | SLIDE (195’ IN 8.5 HRS @ 23 FPH) WOB: 35-45, SPM: 60/60, GPM: 385, MMRPM: 262, SPP: 4000/4200 PSI, DIFF: 100-200 PSI. SLIDE DEPTHS: SLD F/12650 T/12669 19' TF-180 825-908 SLD F/12680 T/12700 20' TF-180 920-1003 SLD F/12800 T/12810 10' TF-HS 1051-1125 SLD F/12963 T/12983 20' TF-160R 1228-1313 SLD F/13047 T/13060 13' TF-180 1343-1415 SLD F/13152 T/13170 18' TF-180 1455-1527 SLD F/13330 T/13350 20' TF-180 1642-1730 SLD F/13535 T/13570 35' TF-180 1852-2018 SLD F/13715 T/13735 20' TF-180 2127-2242 SLD F/13810 T/13830 20' TF-180 2317-0028
LEVI GOODRICH UNIT 2 3H | 11 | 2020-06-11 02:30 | 2020-06-11 03:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.35 | 14093 | 14093 | 0 | SERVICE TOP DRIVE
LEVI GOODRICH UNIT 2 3H | 11 | 2020-06-11 03:00 | 2020-06-11 04:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.4 | 14093 | 14125 | 32 | SLIDE (32’ IN 1 HRS @ 32 FPH) WOB: 35-45, SPM: 108, GPM: 350, MMRPM: 238, SPP: 3000/3300 PSI, DIFF: 200-300 PSI. NOTE: DRILLING WITH ONE MUD PUMP SLIDE DEPTHS: SLD F/14093' T/14125' 32' TF-180 0302-0410
LEVI GOODRICH UNIT 2 3H | 11 | 2020-06-11 04:00 | 2020-06-11 06:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.48 | 14125 | 14282 | 78.5 | ROT (157’ IN 2 HRS @ 79 FPH) WOB: 30/40, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 8/14K, SPP: 4400/4600 PSI, DIFF: 800/1000 PSI. NOTE: SHUTTING IN ON CONNECTION, AVG SICP-0 PSI. BOTH CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT.
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 06:00 | 2020-06-11 11:30 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.71 | 14282 | 14817 | 97.3 | ROT (535’ IN 5.28 HRS @ 101.3 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, RPM: 80, MMRPM: 272, TRPM: 352, TRQ: 9/12K, SPP: 3900/5100 PSI, DIFF: 1000/1200 PSI, BOTH CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT. NOTE: STILL ENCOUNTERING SEEPGAGE LOSSES @ 25 BPH, LOSSES STOP @ 14,598', NOT SHUTTING IN ON CONNECTIONS, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 11:30 | 2020-06-11 16:00 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.9 | 14817 | 14945 | 28.4 | SLIDE (128’ IN 4.72 HRS @ 27.1 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 3900/4100 PSI, DIFF: 100-300 PSI. SLIDE DEPTHS: SLD F/14384 T/14396 12' TF-50L 630-708 SLD F/14485 T/14510 25' TF-180 815-920 SLD F/14757 T/14797 40' TF-90R 1158-1318 SLD F/14818 T/14849 31' TF-90R 1338-1435 SLD F/14865 T/14885 20' TF-90R 1450-1533
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 16:00 | 2020-06-11 16:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.92 | 14945 | 14945 | 0 | RIG SERVICE.
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 16:30 | 2020-06-11 17:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.94 | 14945 | 15019 | 148 | ROT (74’ IN .62 HR @ 119.4 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, RPM: 80, MMRPM: 272, TRPM: 352, TRQ: 9/12K, SPP: 3900/5100 PSI, DIFF: 1000/1200 PSI, BOTH CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT.
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 17:00 | 2020-06-11 18:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.98 | 15019 | 15039 | 20 | SLIDE (20’ IN .72 HRS @ 27.8 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 3900/4200 PSI, DIFF: 100-300 PSI. SLIDE DEPTHS: SLD F/14955 T/14975 20' TF-70R 1647-1730
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 18:00 | 2020-06-11 19:30 | 1.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.04 | 15039 | 15039 | 0 | CLEAN UP CYCLE: PUMP (2) 20 BBL SWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 2 B/U, RPM-80, TRQ-6/8K, SPM: 60/60, GPM-385, SPP-4000 PSI, OBSERVED LOW INCREASE IN CUTTINGS WHEN SWEEP CAME BACK TO SURFACE.
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-11 19:30 | 2020-06-12 00:30 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.25 | 15039 | 15453 | 82.8 | ROT (414’ IN 5 HRS @ 83 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, RPM: 80, MMRPM: 272, TRPM: 352, TRQ: 9/12K, SPP: 3900/5100 PSI, DIFF: 1000/1200 PSI, BOTH CHOKES-100%, FLARE-5-10' ON BOTTOMS UP AND NO MUD CUT. NOTE: PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM. NOTE: CUT MW F/9.2 PPG T/9.0 PPG @ 15,350' AND REDUCE PUMP RATE TO 300 GPM DUE TO LOSSES.
LEVI GOODRICH UNIT 2 3H | 12 | 2020-06-12 00:30 | 2020-06-12 06:00 | 5.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.48 | 15453 | 15545 | 16.7 | SLIDE (92’ IN 5.5 HRS @ 17 FPH) WOB: 35/45K, SPM: 62/62, GPM: 330, MMRPM: 224, SPP: 2800/3000 PSI, DIFF: 400-600 PSI. SLIDE DEPTHS: SLD F/15042' T/15059' 17' TF-90R 19;40-20;38 SLD F/15140' T/15160' 20' TF-90R 21;30-22-40 SLD F/15330' T/15365' 35' TF-180 00;28-02;42 SLD F/15525' T/15545' 25' TF-150L 04;53-06;00
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-12 06:00 | 2020-06-12 08:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.56 | 15545 | 15610 | 32.5 | ROT (65' IN 2 HRS @ 32.3 FPH) WOB: 35/45K, SPM: 50/50, GPM: 320, RPM: 80, MMRPM: 218, TRPM: 298, TRQ: 12/19K, SPP: 2300/2900 PSI, DIFF: 400/600 PSI, BOTH CHOKES-100%, FLARE-20-25' ON BOTTOMS UP, 1 CHOKE-75% AND 1 CHOKE CLOSED ON BOTTOMS UP AND NO MUD CUT. NOTE: STILL ENCOUNTERING LOSSES @ 75 BPH, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-12 08:00 | 2020-06-12 11:30 | 3.5 | P | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.71 | 15610 | 15610 | 0 | BACK REAM OUT OF HOLE F/15,610' T/12,763', SPM: 47/47, GPM: 300, RPM:80, TRQ: 7-9K (MAX TRQ 9K), SPP 2000 PSI, SHUTTING IN CONNECTIONS, AVG SICP=100 PSI, LOSSES @ 40 BPH.
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-12 11:30 | 2020-06-12 14:00 | 2.5 | P | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 9.81 | 15610 | 15610 | 0 | WASH AND REAM IN HOLE F/12,763' T/15,610', SPM: 47/47, GPM: 300, RPM:80, TRQ: 4-6K, SPP 2000 PSI, SHUTTING IN CONNECTIONS, AVG SICP=240 PSI, LOSSES @ 40 BPH.
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-12 14:00 | 2020-06-12 21:30 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.12 | 15610 | 16185 | 76.7 | ROT (575' IN 7.65 HRS @ 75 FPH) WOB: 35/45K, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 12/19K, SPP: 4000/4300 PSI, DIFF: 800/1100 PSI, BOTH CHOKES-100%, FLARE-10-15' ON BOTTOMS UP, BOTH CHOKES-100% OPEN AND NO MUD CUT. NOTE: STILL ENCOUNTERING LOSSES @ 25 BPH, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-12 21:30 | 2020-06-13 02:30 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.33 | 16185 | 16270 | 17 | SLIDE (85’ IN 5 HRS @ 17 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 3800/4000 PSI, DIFF: 600-800 PSI. SLIDE DEPTHS: SLD F/15708' T/15733' 25' TF-140L 1528-1648 SLD F/16000' T/16035' 35' TF=150L 2015-2233 SLD F/16185' T/16210' 25' TF-140L 0022-0135
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-13 02:30 | 2020-06-13 03:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.35 | 16270 | 16270 | 0 | SERVICE TOP DRIVE
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-13 03:00 | 2020-06-13 05:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.44 | 16270 | 16350 | 40 | ROT (80' IN 2 HRS @ 40 FPH) WOB: 35/45K, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 12/19K, SPP: 4000/4300 PSI, DIFF: 800/1100 PSI, BOTH CHOKES-100%, FLARE-10-15' ON BOTTOMS UP, BOTH CHOKES-100% OPEN AND NO MUD CUT. NOTE: STILL ENCOUNTERING LOSSES @ 25 BPH, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 13 | 2020-06-13 05:00 | 2020-06-13 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.48 | 16350 | 16365 | 15 | SLIDE (15’ IN 1 HRS @ 15 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 3800/4000 PSI, DIFF: 600-800 PSI. SLIDE DEPTHS: SLD F/16307' T/16322' 15' TF-60L 0416-0520
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 06:00 | 2020-06-13 08:00 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.56 | 16365 | 16365 | 0 | PUMP (1) 20 BBL SWEEP, CIRCULATE HOLE CLEAN, SPM: 62/62, GPM: 400, SPP: 3900 PSI, RPM: 80, TRQ: 6/8K. NOTE: DECISION WAS MADE TO TRIP OUT THE HOLE AND CHANGE OUT BHA DUE TO REDUCED ROP AND MOTOR STALLING OUT. NOTE: STILL ENCOUNTERING LOSSES @ 10 BPH, ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 08:00 | 2020-06-13 10:00 | 2 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 10.65 | 16365 | 16365 | 0 | BACK REAM OUT OF HOLE F/16,365' T/14,471', SPM: 62/62, GPM: 400, SPP: 3900 PSI, RPM: 80, TRQ: 7-8K (MAX TRQ 8K), SHUTTING IN ON CONNECTIONS, AVG SICP=375 PSI, LOSSES @ 10 BPH.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 10:00 | 2020-06-13 15:30 | 5.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.87 | 16365 | 16365 | 0 | PUMP 40 BBL SLUG, TRIP OUT THE HOLE F/14,471' T/4,096', FILLING ANNULUS W/CALCULATED FILL OF 11.0 PPG MUD. STARTING CASING PSI= 260 PSI, CASING PSI DECREASED TO 0 PSI @ 4,096' - CALCULATED FILL 82 BBLS / ACTUAL FILL 97 BBLS.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 15:30 | 2020-06-13 17:30 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.96 | 16365 | 16365 | 0 | OPEN CHOKES AND FLOW CHECK, WELL WAS FLOWING, BULLHEADED 125 BBLS OF 11.0 PPG, CASING PSI INCREASED T/265 PSI AND DECREASED T/220 PSI WHILE BULLHEADING, BULL HEADED 10 BBLS OF 15.0 PPG, CASING PSI= 0 PSI, FLOW CHECK (NO FLOW), REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 17:30 | 2020-06-13 19:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.02 | 16365 | 16365 | 0 | TRIP OUT THE HOLE F/4,096’ T/BHA ON THE TRIP TANK, REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, L/D AGITATOR ON STD 27, LOSS RETURNS, FILL ANNULUS W/CALCULATED FILL OF 9.0 PPG MUD - CALCULATED FILL 27 BBLS / ACTUAL FILL 32 BBLS.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 19:00 | 2020-06-13 19:30 | 0.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 11.04 | 16365 | 16365 | 0 | RACK BACK TOP MONELS, PULL MWD, DRAIN MOTOR AND BREAK OUT BIT.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 19:30 | 2020-06-13 21:00 | 1.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 11.1 | 16365 | 16365 | 0 | PICK UP 6.75" BAKER T406FS SER 5280590: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.03' BIT TO BEND 5-5/16" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-65'. BIT TO GAMMA-55', TEST MWD (TEST GOOD).
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 21:00 | 2020-06-13 23:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.19 | 16365 | 16365 | 0 | TRIP IN THE HOLE F/BHA T/2794', FILL PIPE ON STD 27, PICK UP AGITATOR, HOLE GIVING PROPER DISPLACEMENT, FILL PIPE EVERY 40 STDS, REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD.
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-13 23:00 | 2020-06-14 02:30 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.33 | 16365 | 16365 | 0 | TRIP IN THE HOLE F/2794' T/10299', FILL PIPE EVERY 30 STDS, NO RETURNS
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-14 02:30 | 2020-06-14 03:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 11.35 | 16365 | 16365 | 0 | SERVICE RIG, PUMP 51BBLS OF 9.0 PPG OBM DOWN BACKSIDE (582') UNTIL RETURNS WERE ESTABLISHED
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-14 03:00 | 2020-06-14 04:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.42 | 16365 | 16365 | 0 | TRIP IN THE HOLE F/10299' T/14092', FILL PIPE EVERY 30 STDS, PARTIAL RETURNS
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-14 04:30 | 2020-06-14 05:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.46 | 16365 | 16365 | 0 | ATTEMPT TO CIRCULATE MUD CAP OUT OF HOLE @ 230 GPM. BEGIN CIRCULATION W/PARTIAL RETURNS, LOST RETURNS AFTER PUMPING 195 BBLS
LEVI GOODRICH UNIT 2 3H | 14 | 2020-06-14 05:30 | 2020-06-14 06:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.48 | 16365 | 16365 | 0 | POOH F/14092' T/SHOE @ 10237' FOR 2ND ATTEMPT TO CIRC. AND DISPLACE MUD CAP OUT OF HOLE.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 06:00 | 2020-06-14 08:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.56 | 16365 | 16365 | 0 | CONTINUE TRIPPING OUT THE HOLE F/14,033' T/10,300', FILLING ANNULUS W/CALCULATED FILL OF 9.0 PPG MUD.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 08:00 | 2020-06-14 08:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.58 | 16365 | 16365 | 0 | ATTEMPTED TO CIRCULATE @ 128 GPM, NO RETURNS, LOST 35 BBLS.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 08:30 | 2020-06-14 10:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.65 | 16365 | 16365 | 0 | TRIP OUT THE HOLE F/10,300' T/8,000', FILLING ANNULUS W/CALCULATED FILL OF 9.0 PPG MUD.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 10:00 | 2020-06-14 12:00 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.73 | 16365 | 16365 | 0 | FILL BACKSIDE WITH 24 BBLS OF 9.0 PPG OBM AND ESTABISHED RETURNS, SLOWLY STAGE UP PUMPS T/224 GPM, SSP: 1200 PSI, LOST 44 BBLS, REGAIN FULL RETURNS, CIRCULATE OUT KILL MUD, MW IN 9.0 PPG, MAX MW OUT 10.3+ PPG.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 12:00 | 2020-06-14 13:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.77 | 16365 | 16365 | 0 | TRIP IN THE HOLE F/8,000' T/10,300' THROUGH 1-CHOKE 100% OPEN, SHUTTING IN ON CONNECTIONS, MAX SICP=40 PSI, HOLE GIVING CALCULATED DISPLACEMENT.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 13:00 | 2020-06-14 15:00 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.85 | 16365 | 16365 | 0 | SLOWLY STAGE UP PUMPS T/353 GPM, SSP: 1100 PSI, RPM: 35, TRQ: 3/4K, LOST 24 BBLS, REGAIN FULL RETURNS, CIRCULATE BOTTOMS UP THROUGH BOTH CHOKES 100% OPEN, MW IN 9.0 PPG, MAX MW OUT 9.0 PPG, SHUT DOWN PUMPS AND CLOSED BOTH CHOKES, SICP=330 PSI.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 15:00 | 2020-06-14 17:30 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.96 | 16365 | 16365 | 0 | TRIP IN THE HOLE F/10,300' T/16,365' THROUGH 1-CHOKE 34% OPEN, BLEEDING BACK CALCULATED DISPLACEMENT @ 1.9 BBLS/STD, SHUTTING IN ON CONNECTIONS, MAX SICP=330 PSI, SICP DECREASED T/ 0 PSI @ 13,085', LOST PARTIAL RETURNS @ 14,700', CALCULATED DISPLACEMENT 165.4 BBLS / ACTUAL DISPLACEMENT 118.6 BBLS, LOST 46.8 BBLS.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 17:30 | 2020-06-14 20:00 | 2.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.06 | 16365 | 16365 | 0 | SLOWLY STAGE UP PUMPS T/380 GPM, SSP: 3950 PSI, RPM: 80, TRQ: 8/12K, PARTIAL RETURNS AND LOSSING 60 BPH, ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM, REGAIN FULL RETURNS.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 20:00 | 2020-06-14 22:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.15 | 16365 | 16575 | 105 | ROT (210' IN 1.90 HRS @ 110.53 FPH) WOB: 35/45K, SPM: 60/60, GPM: 385, RPM: 80, MMRPM: 262, TRPM: 342, TRQ: 10/14K, SPP: 4400/4600 PSI, DIFF: 800/1000 PSI, BOTH CHOKES-100%, FLARE-10-15' ON BOTTOMS UP AND NO MUD CUT. NOTE: STILL ENCOUNTERING LOSSES @ 30 BPH, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-14 22:00 | 2020-06-15 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.23 | 16575 | 16620 | 22.5 | SLIDE (45’ IN 2.20 HRS @ 20.45 FPH) WOB: 35/45K, SPM: 62/62, GPM: 400, MMRPM: 272, SPP: 3800/4000 PSI, DIFF: 600-800 PSI. SLIDE DEPTHS: SLD F/16376' T/16391' 15' TF-60L 1954-2045 SLD F/16560' T/16590' 30' TF-20R 2205-2332
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-15 | 2020-06-15 00:30 | 0.5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 12.25 | 16620 | 16620 | 0 | LOST ALL DIFFERENTIAL PSI, TROUBLE SHOOT MUD MOTOR, MUD MOTOR APPEARS TO HAVE FAILED
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-15 00:30 | 2020-06-15 01:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.29 | 16620 | 16620 | 0 | CIRCULATE BOTTOM'S UP, MAX CASING PSI 350 PSI, 1 CHOKE CLOSED, 2ND CHOKE OPEN 50%, 30' FLARE
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-15 01:30 | 2020-06-15 02:00 | 0.5 | U | PRDHLLT | KILL |  | KILL WELL | 12.31 | 16620 | 16620 | 0 | SHUT IN WELL AGAINST CHOKES AND UPPER PIPE RAMS, MAX SHUT IN PSI 550 PSI, PUMP 30 BBL 12.0 PPG MUD DOWN BACKSIDE, SHUT IN PSI REDUCED (200 PSI) FROM 550 PSI TO 350 PSI
LEVI GOODRICH UNIT 2 3H | 15 | 2020-06-15 02:00 | 2020-06-15 06:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.48 | 16620 | 16620 | 0 | STRIP OUT OF HOLE F/16620' T/10237', FILLING ANNULUS W/CALCULATED FILL OF 13.5 PPG MUD. STARTING CASING PSI= 350 PSI, CASING PSI DECREASED TO 0 PSI @ 12500' - CALCULATED FILL 83 BBLS / ACTUAL FILL 83 BBLS.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 06:00 | 2020-06-15 06:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.5 | 16620 | 16620 | 0 | PUMP 30 BBL SLUG, ATTEMPTED TO CIRCULATE ON TRIP TANK, WELL WAS LOOSING @ 83 BPH, SHUT IN WELL.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 06:30 | 2020-06-15 08:00 | 1.5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 12.56 | 16620 | 16620 | 0 | SLIP AND CUT 10 WRAPS (100') OF DRILL LINE WHILE MONITORING SICP, SICP=0 PSI.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 08:00 | 2020-06-15 08:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.58 | 16620 | 16620 | 0 | RIG SERVICE.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 08:30 | 2020-06-15 13:00 | 4.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.77 | 16620 | 16620 | 0 | TRIP OUT THE HOLE F/10,163’ T/BHA WITH NO RETURNS, FILL ANNULUS W/CALCULATED FILL OF 9.0 PPG MUD - CALCULATED FILL 83 BBLS / ACTUAL FILL 83 BBLSREMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, L/D AGITATOR ON STD 27.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 13:00 | 2020-06-15 13:30 | 0.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 12.79 | 16620 | 16620 | 0 | RACK BACK TOP MONELS, PULL MWD, DRAIN MOTOR AND BREAK OUT BIT, INSPECTED MOTOR AND BIT, OBSERVED BIT HAD MISSING CUTTERS AND BROKE CUTTERS ON THE INNERS AND SHOULDERS, MOTOR GRAVITY DRAINED, BUT NO VISUAL DAMAGES TO MOTOR.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 13:30 | 2020-06-15 15:00 | 1.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 12.85 | 16620 | 16620 | 0 | PICK UP 6.75" SECURITY GTD63C SER13117941: JETS 6/16S TFA: 1.178), 5", 6/7L, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.05' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, 5" NMDC, X/O XT-39 P x DS 42 B, BIT TO SVY-65'. BIT TO GAMMA-55', TEST MWD (TEST GOOD).
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 15:00 | 2020-06-15 18:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.98 | 16620 | 16620 | 0 | TRIP IN THE HOLE F/BHA T/6,044', FILL PIPE ON STD 27, PICK UP AGITATOR, NO RETRUNS WHILE TRIPPING, FILL PIPE EVERY 30 STDS, REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 18:00 | 2020-06-15 19:30 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.04 | 16620 | 16620 | 0 | SLOWLY STAGE UP PUMPS T/144 GPM, SSP: 850 PSI, LOST 51 BBLS, REGAIN FULL RETURNS, CIRCULATE OUT KILL MUD, MW IN 9.0 PPG, MAX MW OUT 9.4 PPG.
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 19:30 | 2020-06-15 20:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.08 | 16620 | 16620 | 0 | TRIP IN THE HOLE F/6,044' T/8087' WITH FLOW LINE OPEN, RETURNS WHILE TRIPPING IN HOLE
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 20:30 | 2020-06-15 21:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.12 | 16620 | 16620 | 0 | SLOWLY STAGE UP PUMPS T/144 GPM, SSP: 775 PSI, LOST 24 BBLS, REGAIN FULL RETURNS, CIRCULATE BOTTOMS UP THROUGH FLOWLINE, MW IN 9.0 PPG, MAX MW OUT 9.3 PPG
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 21:30 | 2020-06-15 23:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.19 | 16620 | 16620 | 0 | TRIP IN THE HOLE F/8087' T/10393' TAKING RETURNS THROUGH FLOWLINE, GOOD RETURNS
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-15 23:00 | 2020-06-16 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.23 | 16620 | 16620 | 0 | SLOWLY STAGE UP PUMPS T/273 GPM, SSP: 2070 PSI, RPM: 20, TRQ: 3K, PARTIAL RETURNS AND LOST 36 BBLS, MW IN 9.0 PPG, MW OUT 9.0 PPG
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-16 | 2020-06-16 01:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.29 | 16620 | 16620 | 0 | TRIP IN THE HOLE F/10393 T/13047', NO RETURNS
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-16 01:30 | 2020-06-16 02:00 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 13.31 | 16620 | 16620 | 0 | FILL PIPE AND BREAK CIRCULATION @ 13047', PARTIAL RETURNS
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-16 02:00 | 2020-06-16 03:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.35 | 16620 | 16620 | 0 | TRIP IN THE HOLE F/13047' T/16459', NO RETURNS
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-16 03:00 | 2020-06-16 05:30 | 2.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.46 | 16620 | 16620 | 0 | BREAK CIRCULATION, PUMP 20 BBL LCM SWEEP WHILE RECIPROCATING PIPE, PARTIAL RETURNS, GPM 127, SPP 1700 PSI, RPM 60, TRQ 8K, LOST 200 BBLS
LEVI GOODRICH UNIT 2 3H | 16 | 2020-06-16 05:30 | 2020-06-16 06:00 | 0.5 | U | PRDHLLT | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 13.48 | 16620 | 16620 | 0 | POOH T/12000' TO ATTEMPT TO ESTABLISH CIRCULATION
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 06:00 | 2020-06-16 10:00 | 4 | U | PRDHLLT | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 13.65 | 16620 | 16620 | 0 | CONTINUE TRIPPING OUT THE HOLE, HOLE STARTED TAKING IMPROPER FILL @ 13,677', SHUT IN WELL, SICP=0 PSI, CONTINUE TRIPPING OUT THE HOLE F/13,677' T/12,000', FILL ANNULUS W/CALCULATED FILL 1.9 BBLS/STD OF 9.0 PPG MUD, SICP=0 PSI.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 10:00 | 2020-06-16 11:30 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.71 | 16620 | 16620 | 0 | PUMP 20 BBL FIRST RESPONSE SWEEP, CIRCULATED THROUGH FLOW LINE WITH 25% RETURNS WHILE RECIPROCATING PIPE, GPM: 128, SSP: 1500 PSI, RPM: 60, TRQ: 3/5K, ONCE SWEEP WAS IN THE ANNULUS, STILL ENCOUNTERING 1/4% REURNS, LOST 134 BBLS, MW IN 9.0 PPG, MW OUT 8.9 PPG.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 11:30 | 2020-06-16 13:00 | 1.5 | U | PRDHLLT | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 13.77 | 16620 | 16620 | 0 | TRIP OUT THE HOLE F/12,000' T/10,650', FILL ANNULUS W/CALCULATED FILL 1.9 BBLS/STD OF 9.0 PPG MUD.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 13:00 | 2020-06-16 15:00 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.85 | 16620 | 16620 | 0 | PUMP 20 BBL FIRST RESPONSE SWEEP, SLOWLY STAGE UP PUMPS T/320 GPM, SSP: 2000 PSI, RPM: 30, TRQ: 2/4K, CIRCULATE OUT KILL MUD THROUGH FLOW LINE WITH 60% RETURNS WHILE RECIPROCATING PIPE, LOST 50 BBLS, FLOW INCREASED @ BOTTOMS UP, SHUT IN WELL, CONTINUE CIRCULATING OUT KILL MUD WITH BOTH CHOKE 100% OPEN, REGAINED FULL RETURNS, MW IN 9.0 PPG, MAX MW OUT 14.5 PPG, FLARE-10-15' ON BOTTOMS UP. SHUT DOWN PUMPS AND CLOSED BOTH CHOKES, SICP= 270 PSI.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 15:00 | 2020-06-16 15:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 13.87 | 16620 | 16620 | 0 | ROTATING HEAD STARTED LEAKING WHILE CIRCULATING, CHANGE OUT ROTATING HEAD WHILE MONITORING SICP, SICP= 270 PSI.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 15:30 | 2020-06-16 16:00 | 0.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 13.9 | 16620 | 16620 | 0 | WASH/REAM F/10,650' T/11,149', GPM: 257, SSP: 2000 PSI, RPM: 30, TRQ: 2/4K, BOTH CHOKES-100% OPEN, SHUTTING IN ON CONNECTION, MAX SICP= 270 PSI.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 16:00 | 2020-06-16 17:30 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.96 | 16620 | 16620 | 0 | CIRCULATE OUT KILL MUD WHILE RECIPROCATING PIPE, GPM: 257, SSP: 2000 PSI, RPM: 60, TRQ: 2/4K, BOTH CHOKES-100% OPEN, MW IN 9.0 PPG, MAX MW OUT 10.0 PPG, LOST 17 BBLS.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 17:30 | 2020-06-16 18:00 | 0.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 13.98 | 16620 | 16620 | 0 | WASH/REAM F/11,149' T/11,719', GPM: 257, SSP: 1750 PSI, RPM: 60, TRQ: 3/5K, BOTH CHOKES-100% OPEN, SHUTTING IN ON CONNECTION, MAX SICP= 140 PSI.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 18:00 | 2020-06-16 19:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.02 | 16620 | 16620 | 0 | CIRCULATE BOTTOMS UP WHILE RECIPROCATING PIPE, GPM: 257, SSP: 1950 PSI, RPM: 60, TRQ: 3/5K, BOTH CHOKES-100% OPEN, MW IN 9.0 PPG, MAX MW OUT 9.5 PPG, LOST 36 BBLS.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 19:00 | 2020-06-16 19:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.04 | 16620 | 16620 | 0 | WASH/REAM F/11,719' T/12,196', GPM: 257, SSP: 1950 PSI, RPM: 60, TRQ: 3/5K, BOTH CHOKES-100% OPEN, SHUTTING IN ON CONNECTION, MAX SICP= 220 PSI.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 19:30 | 2020-06-16 20:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.08 | 16620 | 16620 | 0 | CIRCULATE BOTTOMS UP WHILE RECIPROCATING PIPE, GPM: 257, SSP: 1975 PSI, RPM: 60, TRQ: 3/5K, BOTH CHOKES-100% OPEN, MW IN 9.0 PPG, MAX MW OUT 9.3 PPG, LOST 20 BBLS.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-16 20:30 | 2020-06-17 02:30 | 6 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.33 | 16620 | 16620 | 0 | WASH/REAM F/12,196' T/16,620', GPM: 300, SPP: 2745 PSI, RPM: 60, TRQ: 5/8K, BOTH CHOKES-100% OPEN, SHUTTING IN ON CONNECTION, MAX SICP=220 PSI
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-17 02:30 | 2020-06-17 05:00 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.44 | 16620 | 16752 | 52.8 | ROT (132' IN 2.32 HRS @ 56.98 FPH) WOB: 20/35K, SPM: 53/53, GPM: 342, RPM: 80, MMRPM: 233, TRPM: 313, TRQ:12/16K, SPP: 3400/3500 PSI, DIFF: 400/500 PSI, BOTH CHOKES-100%, FLARE-10-15' ON BOTTOMS UP AND NO MUD CUT. SHUTTING IN ON CONNECTION, MAX SICP= 350 PSI NOTE: STILL ENCOUNTERING LOSSES @ 26 BPH, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 17 | 2020-06-17 05:00 | 2020-06-17 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.48 | 16752 | 16782 | 30 | SLIDE (30’ IN 1.18 HRS @ 25.35 FPH) WOB: 25/30K, SPM: 54/54, GPM: 342, MMRPM: 233, SPP: 3400/3600 PSI, DIFF: 200-400 PSI. SLIDE DEPTHS: SLD F/16655' T/16685' 30' TF-130R 0310-0421
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 06:00 | 2020-06-17 10:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.65 | 16782 | 17028 | 61.5 | ROTATED & SLIDE DRILLED F/16,782' - T/17,028' WOB-18/26K, RPM, 80, TRQ-8/14K, SPM-54/54, GPM-346, MRPM-235, TRPM-315, SPP-3200/3700 PSI, DIFF-250/500 PSI, CP-0 PSI, SICP-250/350 PSI, FLARE-5'/10'
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 10:00 | 2020-06-17 11:00 | 1 | U | PRDHLLT | SFTY | SNDWN | SAFETY STAND DOWN | 14.69 | 17028 | 17028 | 0 | PERFORMED CLEAN UP CYCLE TO STRIP OUT OF THE HOLE FOR CHANGE OUT OF CREWS AND SANITIZATION OF RIG DUE TO PATTERSON EMPLOYEE CONTRACTING COVID-19 VIRUS
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 11:00 | 2020-06-17 16:00 | 5 | U | PRDHLLT | SFTY | SNDWN | SAFETY STAND DOWN | 14.9 | 17028 | 17028 | 0 | STRIPPED OUT OF THE HOLE F/17,028' - T/10,267' TESTED MWD @ SHOE BEFORE PULLING DRILL STRING INTO CASING FOR SHUT IN. MWD TOOL WAS FUNCTIONING PROPERLY
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 16:00 | 2020-06-17 19:00 | 3 | U | PRDHLLT | SFTY | SNDWN | SAFETY STAND DOWN | 15.02 | 17028 | 17028 | 0 | SHUT IN WELL, SANITIZED RIGS TOP DOG HOUSES, SCR HOUSE, AND CREW TRAILERS, THEN PERFORMED CREW CHANGE
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 19:00 | 2020-06-17 19:30 | 0.5 | U | PRDHLLT | SFTY | SNDWN | SAFETY STAND DOWN | 15.04 | 17028 | 17028 | 0 | FLOW CHECK WELL, WELL STATIC, SICP 0 PSI, TEST MWD TOOL, GOOD TEST.
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 19:30 | 2020-06-17 20:30 | 1 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 15.08 | 17028 | 17028 | 0 | REPLACE MAKE-UP CONTROL CABLE ON ST-80'S.
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-17 20:30 | 2020-06-18 01:30 | 5 | U | PRDHLLT | SFTY | SNDWN | SAFETY STAND DOWN | 15.29 | 17028 | 17028 | 0 | STRIP IN HOLE F/ 10,267' T/ 16,586', PARTIAL RETURNS ON TRIP IN HOLE 68 BBLS DISPLACEMENT, LOST 59 BBLS ON TRIP IN HOLE, FILL UP DRILL PIPE AND BREAK CIRCULATION EVERY 25 STANDS.
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-18 01:30 | 2020-06-18 02:30 | 1 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 15.33 | 17028 | 17028 | 0 | WASH AND REAM F/ 16,586' T/ 17,028' DUE T/ TIGHT HOLE CONDITIONS. GPM: 241, SSP: 1750 PSI, RPM: 80, TRQ: 6/10K, BOTH CHOKES-100% OPEN, SHUTTING IN ON CONNECTION, MAX SICP= 115 PSI.
LEVI GOODRICH UNIT 2 3H | 18 | 2020-06-18 02:30 | 2020-06-18 06:00 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.48 | 17028 | 17270 | 69.1 | ROT (242' IN 3.5 HRS @ 69.14 FPH) WOB: 25/30K, SPM: 46/46, GPM: 300, RPM: 80, MMRPM: 204, TRPM: 284, TRQ:12/16K, SPP: 3300/3400 PSI, DIFF: 500/600 PSI, BOTH CHOKES-100%, FLARE-15-20' ON BOTTOMS UP AND NO MUD CUT. SHUTTING IN ON CONNECTION, MAX SICP= 220 PSI NOTE: STILL ENCOUNTERING LOSSES @ 40/50 BPH, PUMPING FIRST RESPONSE SWEEPS EVERY STAND AND ADDING 3 SXS/HR FIRST RESPONSE, 3 SXS/HR CYBERSEAL AND 3 SXS/HR NEW CARB TO ACTIVE SYSTEM.
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 06:00 | 2020-06-18 12:30 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.75 | 17270 | 17890 | 95.4 | R/D F/17,270' - T/17,890' (620' IN 6.5 HRS @ 95.38 FPH) WOB-24/28K, RPM-80, TRQ-10/16K, SPM-47/47, GPM-300, MRPM-204, TRPM-284, SPP-3200/3700 PSI, DIFF-250/500 PSI, CP-150/900 PSI, SICP-0/350 PSI, FLARE-10'/25' NOTE: DRILLING W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 12:30 | 2020-06-18 14:30 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.83 | 17890 | 17905 | 7.5 | S/D F/17,890' - T/17,905' (15' IN 2 HRS @ 7.5 FPH) WOB-28/30K, SPM-47/47, GPM-300, MRPM-204, SPP-3200/3600 PSI, DIFF-200/400 PSI, CP-150/600 PSI, SICP-0/350 PSI, FLARE-10'/25' NOTE: DRILLING W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 14:30 | 2020-06-18 16:00 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.9 | 17905 | 18039 | 89.3 | R/D F/17,890' - T/18,039' (134' IN 1.5 HRS @ 89.33 FPH) WOB-24/28K, RPM-80, TRQ-10/16K, SPM-47/47, GPM-300, MRPM-204, TRPM-284, SPP-3200/3700 PSI, DIFF-250/500 PSI, CP-0/150 PSI, SICP-0/350 PSI, FLARE-8'/16' NOTE: DRILLING W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 16:00 | 2020-06-18 16:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 15.9 | 18039 | 18039 |  | MILESTONE_TD WELL ON 6/18/2020 @ 16:00
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 16:00 | 2020-06-18 16:30 | 0.5 | P | PRDHLLT | WCTRL |  | WELL CONTROL OPERATIONS | 15.92 | 18039 | 18039 | 0 | TOOK FINAL SURVEY & HELD WELL CONTROL DRILL
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 16:30 | 2020-06-18 17:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 15.94 | 18039 | 18039 | 0 | SERVICED TOP DRIVE
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 17:00 | 2020-06-18 21:00 | 4 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.1 | 18039 | 18039 | 0 | CLEAN UP CYCLE @ TD: PUMP (3) 30 BBL SWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 5 B/U, RPM-80, TRQ-9/12K, SPM: 46/46, GPM-295, SPP-2400 PSI. 1ST SWEEP UP START TQ 12K END=10K,ROT.WT=245K 2ND SWEEP UP END TQ= 10K, ROT. WT.=245K 3RD SWEEP UP END TQ= 8K, ROT WT.=245K LOSS OF 4K TORQUE FROM DOING CLEAN UP CYCLE, SHAKERS CLEAN. NOTE: PERFORM CLEAN-UP W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 21:00 | 2020-06-18 23:00 | 2 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 16.19 | 18039 | 18039 | 0 | BACK REAM OUT OF HOLE F/ 18,039' T/ 16,300'.
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-18 23:00 | 2020-06-19 01:30 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.29 | 18039 | 18039 | 0 | CIRCULATE BOTTOMS UP @ 16,300', MAX GAS ON BOTTOMS UP 3155 UNITS, MAX CASING PRESSURE-630 PSI, MUD CUT F/ 9.0 PPG T/ 8.3 PPG, 15'-20' FLARE, PUMP 200 BBL 30 PPB LCM PILL, AND DISPLACE W/ 217 BBLS 9.0 PPG OBM. (SICP-207) NOTE: CIRCULATE W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-19 01:30 | 2020-06-19 05:00 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 16.44 | 18039 | 18039 | 0 | STRIP OUT OF HOLE F/16,300' T/10,267', PUMPING CALCULATED HOLE FILLS 1.9 BBLS PER STAND DOWN BACKSIDE W/ 9.0 PPG OBM.
LEVI GOODRICH UNIT 2 3H | 19 | 2020-06-19 05:00 | 2020-06-19 06:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.48 | 18039 | 18039 | 0 | CIRCULATE BOTTOMS UP @ 10,267', GPM-385, SPP-2965, RPM-30, SHUT WELL IN, MONITOR SICP. NOTE: CIRCULATE W/ FULL RETURNS
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 06:00 | 2020-06-19 07:00 | 1 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 16.52 | 18039 | 18039 | 0 | SICP-306 PSI, PUMP 106 BBLS 14.0 PPG MUD CAP, DISPLACE MUD CAP W/ 102 BBLS 9.0 PPG OBM @ 10,267', PUMP MUD CAP W/ 85% RETURNS, LOST APPROXIMATELY 32 BBLS W/ PUMPING MUD CAP, CALCULATED TOP OF MUD CAP AFTER PULLING OUT OF MUD CAP 7,953'.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 07:00 | 2020-06-19 09:30 | 2.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 16.62 | 18039 | 18039 | 0 | PULL OUT OF HOLE F/ 10,267' T/ 7,113', MONITOR HOLE FILL ON TRIP TANK W/ PULLING OUT OF HOLE.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 09:30 | 2020-06-19 10:00 | 0.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.65 | 18039 | 18039 | 0 | FLOW CHECK WELL, WELL STATIC, PUMP SLUG.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 10:00 | 2020-06-19 11:00 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 16.69 | 18039 | 18039 | 0 | PULL OUT OF HOLE F/ 7,113' T/ 5,320', MONITOR HOLE FILLS ON TRIP TANK, PROPER HOLE FILL ON TRIP OUT OF HOLE.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 11:00 | 2020-06-19 11:30 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 16.71 | 18039 | 18039 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 11:30 | 2020-06-19 12:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 16.75 | 18039 | 18039 | 0 | PULL OUT OF HOLE F/ 5,320' T/ 2,729', MONITOR HOLE FILLS ON TRIP TANK, PROPER HOLE FILL ON TRIP OUT OF HOLE.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 12:30 | 2020-06-19 13:00 | 0.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 16.77 | 18039 | 18039 | 0 | LAY DOWN DRILLING AGITATOR.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 13:00 | 2020-06-19 14:30 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 16.83 | 18039 | 18039 | 0 | PULL OUT OF HOLE F/ 2,729' T/ 147', MONITOR HOLE FILLS ON TRIP TANK, PROPER HOLE FILL ON TRIP OUT OF HOLE.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 14:30 | 2020-06-19 16:00 | 1.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 16.9 | 18039 | 18039 | 0 | LAY DOWN DIRECTIONAL BHA ASSEMBLY.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 16:00 | 2020-06-19 16:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 16.92 | 18039 | 18039 | 0 | SERVICE TOP DRIVE AND BLOCK.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 16:30 | 2020-06-19 17:00 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.94 | 18039 | 18039 | 0 | PULL WEAR BUSHING, CLEAN AND ORGANIZE RIG FLOOR T/ MITIGATE SLIP AND TRIP HAZARDS.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 17:00 | 2020-06-19 19:30 | 2.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 17.04 | 18039 | 18039 | 0 | HELD PJSM, RIG UP FRANKS CASING TOOLS AND EQUIPMENT.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-19 19:30 | 2020-06-20 01:00 | 5.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.27 | 18039 | 18039 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING W/CENTRALIZERS IN MIDDLE OF JTS., 1 INNOVEX DV FLOAT COLLAR, GEO DYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/ 5,000', FILLING PIPE ON THE FLY, SOLID BODY CENTALIZERS EVERY 4TH JOINT, MONITOR DISPLACEMENTS ON TRIP TANK, PROPER DISPLACEMENTS W/ RUNNIG CASING.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-20 01:00 | 2020-06-20 01:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.29 | 18039 | 18039 | 0 | ATTEMPT T/ BREAK CIRCULATION @ 5,000', PACKER CUP ON CRT TOOL LEAKING, CHANGE OUT PACKER CUP ON CRT TOOL AND BREAK CIRCULATION @ SPM-50, SPP-350, ESTABLISH CIRCULATION @ 5,000' W/ NO ISSUES.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-20 01:30 | 2020-06-20 03:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.35 | 18039 | 18039 | 0 | PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/ 5,000' T/ 7,228, FILLING PIPE ON THE FLY, SOLID BODY CENTRALIZERS EVERY 4TH JOINT, MONITOR DISPLACEMENTS ON TRIP TANK, PROPER DISPLACEMENTS WHILE RUNNING CASING. NOTE: AT 7,228' CASING STOPPED DISPLACING OBM.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-20 03:00 | 2020-06-20 04:30 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.42 | 18039 | 18039 | 0 | STAGE MUD PUMPS UP AND ESTABLISH CIRCULATION. CIRCULATE BOTTOMS UP W/ PARTIAL REURNS, SPM-55, SPP-300, MAX GAS-2,450u, MW IN-9.0 / OUT-8.6. LOST APPROXIMATELY 45 BBLS W/ CIRCULATING BOTTOMS UP, FLOW CHECK WELL, WELL FLOWING, SHUT WELL AND MONITOR SICP, NO PRESSURE BUILD UP, OPEN CHOKE AND MONITOR RETURNS T/ TRIP TANK, WELL FLOWED BACK 9.32 BBLS IN 7 MINUTES (WELL FLOWING 80 BBLS/HR) SHUT WELL IN AND MONITOR SICP, NO PRESSURE BUILD, OPEN CHOKE AND FLOW CHECK T/ TRIP TANK, WELL FLOWING 80 BBLS/ HOUR, SHUT CHOKE.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-20 04:30 | 2020-06-20 05:00 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 17.44 | 18039 | 18039 | 0 | HELD PJSM, REMOVE TRIP NIPPLE AND STRIP ROTATING HEAD OVER CASING.
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-20 05:00 | 2020-06-20 05:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 17.46 | 18039 | 18039 | 0 | RIG SERVICE/DRAIN WATER FROM VERSA VALVE
LEVI GOODRICH UNIT 2 3H | 20 | 2020-06-20 05:30 | 2020-06-20 06:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.48 | 18039 | 18039 | 0 | PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING F/ 7,228' T/ 7,700', FILLING PIPE ON THE FLY, STRIP CASING IN HOLE BLEEDING OFF 1 BBL DISPLACEMENT PER JOINT IN TRIP TANK.
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 06:00 | 2020-06-20 07:00 | 1 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.52 | 18039 | 18039 | 0 | CIRCULATED & CONDITION BOTTOMS UP @ 8000' SPM-40/80, GPM-128/256, SPP-250/575 PSI, CP-0 PSI, FLARE-0', CHOKES-2 FULL OPEN NOTE: LOST A TOTAL OF 30 BBLS OF OBM
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 07:00 | 2020-06-20 08:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.56 | 18039 | 18039 | 0 | RAN 5" PRODUCTION CASING T/8562' . DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 08:00 | 2020-06-20 08:30 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 17.58 | 18039 | 18039 | 0 | CHANGED OUT CASING TOOLS F/5" TO 5.5"
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 08:30 | 2020-06-20 09:00 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.6 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/8562' - T/9000' DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 09:00 | 2020-06-20 10:30 | 1.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.67 | 18039 | 18039 | 0 | CIRCULATED BTMS UP @ 9000'. SPM-40/80, GPM-128/256, SPP-250/575 PSI, CP-0 PSI, FLARE-0', CHOKES-2 FULL OPEN NOTE: LOST A TOTAL OF 37 BBLS OF OBM
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 10:30 | 2020-06-20 12:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.73 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/9,000' - T/10,200'. HOLDING CASING PSI @ 100. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 12:00 | 2020-06-20 13:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.77 | 18039 | 18039 | 0 | CIRCULATED BTMS UP @ 10,200'. SPM-40/60, GPM-128/192, SPP-250/450 PSI, CP-0 PSI, FLARE-0', CHOKES-100% / 30%, MAX GAS-499u NOTE: LOST A TOTAL OF 8 BBLS OF OBM
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 13:00 | 2020-06-20 14:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.81 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/10,200' - T/10,700' @ CONTROLLED RATE 100'/MIN. HOLDING CASING PSI @ 100. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 14:00 | 2020-06-20 15:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.85 | 18039 | 18039 | 0 | CIRCULATED BTMS UP @ 10,700'. SPM-40/80, GPM-128/256, SPP-250/675 PSI, CP-0 PSI, FLARE-0', MW-8.9 PPG, CHOKES-2 FULL OPEN, MAX GAS-760u CONTINUOUSLY WORKING CASING WHILE CIRCULATING NOTE: LOST A TOTAL OF 27 BBLS OF OBM (HEAVIEST MW OUT SEEN 8.8 PPG)
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 15:00 | 2020-06-20 15:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.87 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/10,700' - T/11,200'. RUNNING IN HOLE @ CONTROLLED RATE 75'/MIN. HOLDING CASING PSI @ 100. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT.
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 15:30 | 2020-06-20 19:00 | 3.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.02 | 18039 | 18039 | 0 | CIRCULATED BOTTOMS UP @ 11,200'. SPM-40/70, GPM-128/224, SPP-250/525 PSI, CP-0 PSI, FLARE-0', CHOKES-2 FULL OPEN, MAX GAS-2944u. CONTINUOUSLY WORKING CASING WHILE CIRCULATING NOTE: PARTIAL RETURNS: LOST A TOTAL OF 90 BBLS OF OBM. (HEAVIEST MW OUT SEEN 13.1 PPG)
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 19:00 | 2020-06-20 19:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.04 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/11,200' - T/11,780'. RUNNING IN HOLE @ CONTROLLED RATE 75'/MIN. HOLDING CASING PSI @ 100. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 19:30 | 2020-06-20 23:00 | 3.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.19 | 18039 | 18039 | 0 | CIRCULATED BOTTOMS UP ON FLOWLINE @ 11,780'. SPM-40/70, GPM-128/224, SPP-320/650 PSI, FLARE-0', MAX GAS-3123u. CONTINUOUSLY WORKING CASING WHILE CIRCULATING NOTE: PARTIAL RETURNS: LOST A TOTAL OF 120 BBLS OF OBM. (HEAVIEST MW OUT SEEN 9.1 PPG)
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 23:00 | 2020-06-20 23:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.21 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/11,780' - T/12,339'. RUNNING IN HOLE @ CONTROLLED RATE 75'/MIN. HOLDING CASING PSI @ 100. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-20 23:30 | 2020-06-21 02:00 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.31 | 18039 | 18039 | 0 | CIRCULATED BOTTOMS UP ON FLOWLINE @ 12,339'. SPM-20/100, GPM-64/321, SPP-200/1000 PSI, FLARE-0', MAX GAS-2697u. CONTINUOUSLY WORKING CASING WHILE CIRCULATING NOTE: PARTIAL RETURNS: LOST A TOTAL OF 128 BBLS OF OBM. (HEAVIEST MW OUT SEEN 9.1 PPG)
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-21 02:00 | 2020-06-21 02:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.33 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/12,339' - T/12,898'. RUNNING IN HOLE @ CONTROLLED RATE 75'/MIN. HOLDING CASING PSI @ 75. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-21 02:30 | 2020-06-21 04:30 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.42 | 18039 | 18039 | 0 | CIRCULATED BOTTOMS UP ON FLOWLINE @ 12,898'. SPM-20/40, GPM-64/128, SPP-150/400 PSI, FLARE-0', MAX GAS-1775u. CONTINUOUSLY WORKING CASING WHILE CIRCULATING NOTE: PARTIAL RETURNS: LOST A TOTAL OF 108 BBLS OF OBM. (HEAVIEST MW OUT SEEN 9.0 PPG)
LEVI GOODRICH UNIT 2 3H | 21 | 2020-06-21 04:30 | 2020-06-21 06:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.48 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/12,898' - T/14,880'. RUNNING IN HOLE @ CONTROLLED RATE 75'/MIN. HOLDING CASING PSI @ 75. DISPLACING 1 BBL OF MUD THROUGH CHOKE INTO TRIP TANK E/JT
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 06:00 | 2020-06-21 10:00 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.65 | 18039 | 18039 | 0 | RAN 5.5" PRODUCTION CASING F/15,166' - T/18,018' REMOVE ROTATING HEAD, P/U LANDING JOINT AND LAND CASING ON HANGER W/150K. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: 1-INNOVEX 5''FLOAT SHOE, 2 JTS OF 5'' CSG. 1- INNOVEX FLOAT COLLAR, 1-GEODYNAMICS TOE SLEEVE VALVE, RAN 8,527.86' (193 JTS) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER & 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING, RAN 9,435.06' (193 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING. FOR TOTAL OF 442 FULL JTS OF 5'' 18# P-110, ICY WEDGE 625 & 5.5" 23# P-110 ICY BLUE CASING. TOTAL OF 406 FULL JTS OF 5'' 18# P-110, ICY WEDGE 625 & 5 1/2" 23# P-110 ICY WEDGE 563 CASING. CASING SHOE @ 18,018.30' TOP OF FLOAT COLLAR @ 17,930.31' BOTTOM OF TOE SLEEVE VALVE @ 17,930.31' TOP OF TOE SLEEVE VALVE @ 17,914.86 TOP OF X-OVER @ 9,467.25' TOP OF MARKER JOINT ABOVE X-OVER @ 9,446.94' NOTE: LOST APPROXIMATELY 204 BBLS WHILE RUNNING CASING F/12,898' T/18,018'.
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 10:00 | 2020-06-21 10:30 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 18.67 | 18039 | 18039 | 0 | RIG DOWN EXPRESS CRT INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 0 PSI
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 10:30 | 2020-06-21 16:00 | 5.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.9 | 18039 | 18039 | 0 | CIRCULATED & CONDITIONED ATTEMPTING TO BRING FLOW RATE UP TO 6 BPM, STARTED PUMPING @ 2 BPM THROUGH 2 FULL OPEN CHOKES FOR 2 BOTTOMS UP SLOWLY STAGING PUMPS UP TO 3.85 BPM, HOLE WAS STILL LOSING MUD, LOST A TOTAL OF 46 BBLS WHEN FLOW WAS DEVERTED DOWN FLOWLINE, PITS STARTED TO GAIN MUD THEN PUMPS WERE BROUGHT UP TO 4.62 BPM, HOLE THEN STARTED TO LOSE MUD, LOST A TOTAL OF 31 BBLS IN 30 MIN, PUMP WAS THEN SLOWED BACK DOWN TO 4.2 BPM TO MONITOR FOR LOSSES, HOLE WAS STILL LOSING MUD, LOST ANOTHER 35 BBLS IN 30 MIN, SLOWED DOWN PUMPS BACK TO 3 BPM UNTIL CEMENTING EQUIPMENT WAS READY, LOSSES LEVELED OUT AND ONLY LOST ANOTHER 5 BBLS WAS LOST. TOTAL LOSSES = 117 BBLS SHUT DOWN PUMPS & CLOSED IN WELL CASING PRESSURE CAME UP TO 125 PSI
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 16:00 | 2020-06-21 16:30 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 18.92 | 18039 | 18039 | 0 | HELD PJSM & SWAPPED CEMENTING LINES FROM RIG STANDPIPE TO CEMENTING STANDPIPE
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 16:30 | 2020-06-21 19:00 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 19.02 | 18039 | 18039 | 0 | FLUSHED THROUGH & TESTED CEMENTING LINES T/8500 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: PUMPED @ 5 BPM 50 BBL 9.5 PPG WEIGHTED SPACER, 257 BBL 13.5 PPG 865 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 351 BBLS OF FRESH WATER WITH BIOCIDE AND CORPLEX @ 5 BPM, OBSERVED 95% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 1360 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2500 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 3 BBLS. FLOATS HELD. PLUG DOWN @ 19:05 HRS 06/21/2020: NOTE: CEMENT WITH PARTIAL RETURNS. PUMPED SPACER AND CEMENT THRU CHOKE MANIFOLD (LOST APPROXIMATELY 90 BBLS - 71% RETURNS), PUMP DISPLACEMENT THRU FLOWLINE LOST APPROXIMATELY 93 BBLS - 74% RETURNS) TOTAL APPROXIMATELY LOSS DURING CEMENT JOB 183 BBLS. MAX CIRC GAS WHILE DISPLACING-4,495u
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 19:00 | 2020-06-21 20:30 | 1.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 19.08 | 18039 | 18039 | 0 | SHUT IN WELL, RIGGED DOWN DOWN CEMENT HEAD, CIRCULATING IRON, AND ROTATING HEAD WHILE MONITORING SICP, SICP= 0 PSI.
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 20:30 | 2020-06-21 23:00 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 19.19 | 18039 | 18039 | 0 | BACK OUT & LAY DOWN LANDING JOINT, R/D CSG BAILS & ELEVATORS & R/U RIG ELEVATORS. MADE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD & WASHED & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, P/U JT OF DP & PACK-OFF, INSTALLED STREAM FLO PACKOFF (PULL TEST T/25K OVERPULL) & TEST SEALS T/ 5000 PSI.
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 23:00 | 2020-06-21 23:30 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 19.21 | 18039 | 18039 | 0 | CLEAN RIG FLOOR. REMOVE ROT. HEAD, CSG PROTECTORS, AND CSG EQUPMENT FROM RIG FLOOR.
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-21 23:30 | 2020-06-22 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 19.23 | 18039 | 18039 | 0 | ADJUST TOP DRIVE SHOT PIN HYDRAULIC PRESSURE FROM 275 PSI TO 475 PSI.
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-22 | 2020-06-22 01:30 | 1.5 | P | PRDHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 19.29 | 18039 | 18039 | 0 | REMOVE SAVER SUB AND REPLACE WITH NEW.
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-22 01:30 | 2020-06-22 03:00 | 1.5 | P | PRDHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 19.35 | 18039 | 18039 | 0 | CUT/SLIP DRILL LINE-80'
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-22 03:00 | 2020-06-22 06:00 | 3 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 19.48 | 18039 | 18039 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE & INSTALL WEATHER CAP AND SECURE WELL. RELEASE WELL ON 6/22/2020 @ 06:00. RELEASE RIG ON 6/22/2020 @ 06:00. TURN OVER TO COMPLETION ON 6/22/2020 @ 06:00
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-22 06:00 | 2020-06-22 06:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 19.48 | 18039 | 18039 |  | MILESTONE_TURN OVER TO COMPLETION ON 6/22/2020 @ 06:00
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-22 06:00 | 2020-06-22 06:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 19.48 | 18039 | 18039 |  | MILESTONE_RIG RELEASE ON 6/22/2020 @ 06:00
LEVI GOODRICH UNIT 2 3H | 22 | 2020-06-22 06:00 | 2020-06-22 06:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 19.48 | 18039 | 18039 |  | MILESTONE_WELL RELEASE ON 6/22/2020 @ 06:00
OZARK UNIT 1H | 2 | 2021-06-15 06:00 | 2021-06-16 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | SPLIT APART EQUIPMENT & PREPPED FOR TRANSPORTATION, LOADED AND TRANSPORTED MUD TANKS, MUD PUMPS, GENERATORS, AND MISC LOADS. UNDRESS DERRICK, REMOVE CROWN, TOP AND MIDDLE SECTIONS OF DERRICK. REMOVE DS DOGHOUSE. PERFORMING CAR WASHES ON ALL EQUIPMENT LEAVING LOCATION. ON NEW LOCATION SET MUD TANKS AND MUD PUMPS, SUITCASES, VFD HOUSE, MOTOR PACKAGE, DIESEL TANK, BULK TANKS, WATER TANKS, & PARTS HOUSES, SET SUB MATS, RIGGED DOWN PATTERSON CAMP HOUSES & PARTS HOUSES, LOADED OUT AND MOVED HOUSES TO NEW LOCATION, RIGGED UP ALL CAMP HOUSES & PARTS HOUSES. SPOT SUBS OVER WELL CENTER, CHANGE OUT VALVES ON MUD TANKS AND RIG UP GENERATOR PACKAGE.
OZARK UNIT 1H | 2 | 2021-06-15 06:00 | 2021-06-15 06:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB ON 6-15-21 @ 06:00
OZARK UNIT 1H | 3 | 2021-06-16 06:00 | 2021-06-17 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | CONTINUE MOVING, SETTING IN AND RIGGING UP, INSTALLED CENTER STEEL, SET DRAWWORKS, ODS HOUSE, PINNED A-SECTION OF DERRICK TO SUBS, PINNED MIDDLE AND CROWN SECTION OF DERRICK, INSTALLED MONKEY BOARD, PINNED BLOCKS TO TOP DRIVE, DRESSED OUT DERRICK, SET DS HOUSE, ST-80, PERFORM DERRICK PRE-RAISE INSPECTION, RAISE DERRICK @ 02:05, SCOPE IN AND PIN MSRC'S TO SUBS, RAISE AND PIN SUBS, SUBS UP @ 04:00 HRS. NOTE: INSPECTION AND REPAIRS DONE DURING RIG MOVE: 90 DAY CATWALK INSPECTION, ANNUAL ST-80 INSPECTION, 180 DAY CHOKE MANIFOLD INSPECTION, INSTALLED PINS ON ODS, TIB 657 SOFTWARE UPGRADE, INSTALLED BACK UP 4" ISOLATION VALVE ON #3 MUD PUMP, REPLACED RIG NUMBERS ON MAST AND REPLACED MAST CABLES FOR LOOSE LIFTING GEAR.
OZARK UNIT 1H | 4 | 2021-06-17 06:00 | 2021-06-18 | 18 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | CONTINUE RIGGING UP: RIG MUD LINES, INSTALL NEW 4" ISOLATION VALVES ON ALL 3 MUD PUMPS, HOOK UP ELECTRICAL LINES TO RIG FLOOR, HOOK WATER AND AIR TO RIG FLOOR INSTALL MUD LINE TO STAND PIPE ON RIG FLOOR, RIG TONGS, INSTALL COVERS ON DS, ODS AND BOOM POLE WINCHS AND SPOOL UP CABLES, HOOK UP ELECTRICAL LINES TO CATWALK, REPLACED PLUGS ON #2 MUD PUMP AND DRAW WORKS, INSTALL PASON TORQUE SENSOR ON ST-80, POWER UP RIG, DRESS SHAKERS WITH 140 SCREENS, FILL MUD TANKS WITH WATER AND MIX TREATMENT.
OZARK UNIT 1H | 4 | 2021-06-18 | 2021-06-18 05:00 | 5 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | TROUBLESHOOT TOP DRIVE/DRAWWORKS UPS ISSUE IN VFD, STAGE BHA COMPONENTS, DRESS SHAKERS WITH API 140's, STRAP DRILL PIPE, FINISH CRI.
OZARK UNIT 1H | 4 | 2021-06-18 05:00 | 2021-06-18 06:00 | 1 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | BRING 5" HANDLING TOOLS TO RIG FLOOR, DRESS OUT FLOOR FOR SPUD.
OZARK UNIT 1H | 5 | 2021-06-18 06:00 | 2021-06-18 10:00 | 4 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | CONTINUE TROUBLE SHOOTING DRAWWORKS, TOP DRIVE AND #2 MUD PUMP DUE TO LOST COMMUNICATION TO HMI, WENT THROUGH AND CLEANED FIBER OPTIC CABLES, SPOOL UP DRAWWORKS, UNPIN TOP DRIVE FROM DERRICK AND LOWER TO FLOOR, SERVICE TOP DRIVE, CHANGE OUT DIES ON ST-80.
OZARK UNIT 1H | 5 | 2021-06-18 10:00 | 2021-06-18 14:00 | 4 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | RUN OUT EQUIPMENT, INSTALL CORTEX UPDATE ON OMRON CONTROL SYSYEM.
OZARK UNIT 1H | 5 | 2021-06-18 14:00 | 2021-06-18 19:30 | 5.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | ON COMPANY TIME ON 6/18/2021 @ 14:00, CHANGE OUT SWIVEL PACKING, CHANGE OUT SAVER SUB FROM 4 ½ CET 43 TO 4 ½ IF, RIG UP CELLAR PUMPS, RUN HOSES TO SHAKER GOOSENECKS AND RIG UP OFFLINE CEMENT MANIFOLD, INSTALL CONDUCTOR RISER, CHANGE OUT DIE BLOCKS AND STABBING GUIDES F/4.5" T/5" DRILL PIPE.
OZARK UNIT 1H | 5 | 2021-06-18 19:30 | 2021-06-18 22:00 | 2.5 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | PICK UP BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 108'.
OZARK UNIT 1H | 5 | 2021-06-18 22:00 | 2021-06-19 01:30 | 3.5 | U | MOBDMOB | RIGMT | SVCMD | SERVICE MUD PUMPS / CIRC EQUIP | 0 | 108 | 108 | 0 | ATTEMPT TO PRESSURE TEST LINES (KELLY HOSE HAMMER UNION LEAKING), REPLACE HAMMER UNION GASKET, TEST LINES TO 1,500 PSI (GOOD TEST).
OZARK UNIT 1H | 5 | 2021-06-19 01:30 | 2021-06-19 02:15 | 0.75 | U | MOBDMOB | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 0 | 108 | 108 | 0 | TROUBLESHOOT TOP DRIVE TORQUE ISSUE, REPAIR CONNECTOR PIN.
OZARK UNIT 1H | 5 | 2021-06-19 02:15 | 2021-06-19 03:00 | 0.75 | U | MOBDMOB | WAIT | WTTRD | WAIT ON THIRD PARTY | 0 | 108 | 108 | 0 | C/O CELLAR PUMP DUE TO DAMAGED HYDRAULIC HOSE.
OZARK UNIT 1H | 5 | 2021-06-19 03:00 | 2021-06-19 03:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 6/19/2021 @ 03:00
OZARK UNIT 1H | 5 | 2021-06-19 03:00 | 2021-06-19 06:00 | 3 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.13 | 108 | 1350 | 414 | ROTATE DRILL F/108' T/1,350' (1,242' IN 3 HR @ 414 FPH) WOB-10-30K, RPM-100, TRQ- 2/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,900/1,300 PSI, DIFF-100/300 PSI. DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM
OZARK UNIT 1H | 6 | 2021-06-19 06:00 | 2021-06-19 13:30 | 7.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.44 | 1350 | 3691 | 312.1 | ROTATE (2341’ IN 7.62 HRS @ 307.2 FPH) WOB-25-35K, RPM-100, TRQ- 5/12K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,400/1,900 PSI, DIFF-300/500 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000', STARTING PUMPING 30 BBL GEL SWEEPS (PHPA) EVERY =/-300' @ 3,000'.
OZARK UNIT 1H | 6 | 2021-06-19 13:30 | 2021-06-19 15:00 | 1.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.5 | 3691 | 3845 | 102.7 | SLIDE (154' IN 1.38 HRS @ 111.6 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1400/1700 PSI, DIFF-100/300 PSI. SLIDE DEPTHS: SLD F/1989' T/2004' 15' T/F-330 F/7:50-8:00 SLD F/2083' T/2098' 15' T/F-330 F/8:20-8:30 SLD F/2176' T/2191' 15' T/F-330 F/8:40-8:47 SLD F/2269' T/2281 12' T/F-330 F/9:01-9:10 SLD F/2364' T/ 2376' 12' T/F-HS F/9:24-9:30 SLD F/2458' T/2470 12' T/F-HS F/9:46-9:54 SLD F/2927' T/2937' 10'T/F-180 F/11:11-11:16 SLD F/3021' T/3033' 12' T/F-180 F/11:34-11:40 SLD F/3115' T/3127' 12' T/F-180 F/12:00-12:04 SLD F/3209' T/3221' 12' T/F-HS F/12:25-12:30 SLD F/3304' T/3316' 12' T/F-150 F/12:50-12:55 SLD F/3398' T/3413' 15' T/F-150 F/ 13:15-13:23
OZARK UNIT 1H | 6 | 2021-06-19 15:00 | 2021-06-19 16:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.54 | 3845 | 3845 | 0 | PUMP 2-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-1500 PSI.
OZARK UNIT 1H | 6 | 2021-06-19 16:00 | 2021-06-19 17:30 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.6 | 3845 | 3845 | 0 | TRIP OUT OF HOLE F/3,845' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
OZARK UNIT 1H | 6 | 2021-06-19 17:30 | 2021-06-19 20:00 | 2.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.71 | 3845 | 3845 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND BREAK BIT. MOTOR BEARING SLACK WAS MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-1-NO-A-X-0-NO-TD.
OZARK UNIT 1H | 6 | 2021-06-19 20:00 | 2021-06-19 20:30 | 0.5 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0.73 | 3845 | 3845 | 0 | RIG SERVICE
OZARK UNIT 1H | 6 | 2021-06-19 20:30 | 2021-06-19 21:00 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 0.75 | 3845 | 3845 | 0 | REMOVE CONDUCTOR RISER AND INSTALL CASING GUIDE TOOL, REMOVE MOUSEHOLE AND RIG ELEVATORS.
OZARK UNIT 1H | 6 | 2021-06-19 21:00 | 2021-06-19 22:00 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.79 | 3845 | 3845 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
OZARK UNIT 1H | 6 | 2021-06-19 22:00 | 2021-06-20 02:30 | 4.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.98 | 3845 | 3845 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). THEN RUN 95 JOINTS (97 TOTAL) OF 10 3/4" 45.5# J-55 BT&C CASING T/3,835.50'. RAN 49 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JOINT ALL THE WAY TO 75.97.' INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED WELLHEAD T/5000 PSI. SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET XXXK (W/O BLOCKS) ON BASE PLATE. SHOE- 3,835.50' TOP OF FLOAT COLLAR- 3,753.4' LEFT OUT 8 JOINTS-316.4'
OZARK UNIT 1H | 6 | 2021-06-20 02:30 | 2021-06-20 04:00 | 1.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.04 | 3845 | 3845 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS. GPM-321, SPP-100. NO LOSSES.
OZARK UNIT 1H | 6 | 2021-06-20 04:00 | 2021-06-20 04:30 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 1.06 | 3845 | 3845 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT.
OZARK UNIT 1H | 6 | 2021-06-20 04:30 | 2021-06-20 05:00 | 0.5 | P | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 1.08 | 3845 | 3845 | 0 | HOLD PJSM, RIG UP STREAMFLO PUP JOINT, CEMENT HEAD, AND CIRCULATING IRON.
OZARK UNIT 1H | 6 | 2021-06-20 05:00 | 2021-06-20 06:00 | 1 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1.13 | 3845 | 3845 | 0 | HELD PJSM, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 409 BBLS 11.6 PPG LEAD CEMENT, 107 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 358 BBLS OF 8.8 PPG OIL BASE MUD @ 8 BPM.
OZARK UNIT 1H | 7 | 2021-06-20 06:00 | 2021-06-20 07:30 | 1.5 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1.19 | 3845 | 3845 | 0 | CONTINUE DISPLACING CEMENT WITH 358 BBLS OF 8.8 PPG OBM OFFLINE WHILE TESTING BOP’S: TESTED BACK TO PUMPS 250 PSI LOW / 5000 PSI HIGH, TEST FLOOR VALVES 250 PSI LOW / 5000 PSI HIGH, BUMPED PLUG W/940 PSI PRESSURED UP T/1520 PSI (580 PSI OVER) @ 3 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 198 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
OZARK UNIT 1H | 7 | 2021-06-20 07:30 | 2021-06-20 08:00 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.21 | 3845 | 3845 | 0 | PRESSURE TESTED 10-3/4"SURFACE CASING TO 1500 PSI FOR 30 MINUTES, GOOD TEST.
OZARK UNIT 1H | 7 | 2021-06-20 08:00 | 2021-06-20 10:00 | 2 | P | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 1.29 | 3845 | 3845 | 0 | RIG DOWN CEMENT HEAD, CIRCULATING LINES AND STREAM-FLO PUP JOINT, FLUSH THROUGH AND RIG DOWN CELLAR PUMPS.
OZARK UNIT 1H | 7 | 2021-06-20 10:00 | 2021-06-20 15:30 | 5.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.52 | 3845 | 3845 | 0 | INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALL KILL LINE, INSTALL CHOKE LINE TO BOP AND CHOKE, HOOK UP HYDRAULIC LINES TO BOP STACK, FUNCTION TEST SAME.
OZARK UNIT 1H | 7 | 2021-06-20 15:30 | 2021-06-20 18:30 | 3 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.65 | 3845 | 3845 | 0 | CONTINUE TESTING BOP'S: TEST TOP RAMS, LOWER RAMS, INSIDE AND OUTSIDE KILL VALVES, INSIDE AND OUTSIDE HCR VALVES, WELLHEAD ADAPTER, KILL LINES BACK TO #1 AND #2 PUMPS, BLINDS AND KILL LINE CHECK VALVE TO 250 PSI LOW / 5000 PSI HIGH, TEST ANNULAR TO 250 PSI LOW / 3500 PSI HIGH. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TESTED ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. REMOVE TEST CAP AND RIG DOWN TESTERS. CLOSED CASING VALVE.
OZARK UNIT 1H | 7 | 2021-06-20 18:30 | 2021-06-20 19:00 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.67 | 3845 | 3845 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE AND MOUSE HOLE.
OZARK UNIT 1H | 7 | 2021-06-20 19:00 | 2021-06-20 19:30 | 0.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.69 | 3845 | 3845 | 0 | PERFORM ACCUMULATOR DRAW DOWN TEST.
OZARK UNIT 1H | 7 | 2021-06-20 19:30 | 2021-06-20 22:00 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.79 | 3845 | 3845 | 0 | MAKE UP FLOW LINE, FILL UP LINE, CASING FILL LINE, RIG UP KATCH KAN EQUIPMENT TO STACK.
OZARK UNIT 1H | 7 | 2021-06-20 22:00 | 2021-06-21 01:00 | 3 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.92 | 3845 | 3845 | 0 | PICK UP (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 6.04' BIT TO BEND 8-1/4" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, 22 STDS DRILL PIPE AND DSW AGITATOR, BIT TO SVY-70' AND GAMMA-60'. TEST MWD-TEST GOOD
OZARK UNIT 1H | 7 | 2021-06-21 01:00 | 2021-06-21 02:00 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.96 | 3845 | 3845 | 0 | PERFORM RIG SERVICE (ADD HYDRAULIC FLUID TO TOP DRIVE).
OZARK UNIT 1H | 7 | 2021-06-21 02:00 | 2021-06-21 03:30 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 2.02 | 3845 | 3845 | 0 | L/D MWD TEST JOINT AND XO, P/U 6-1/2" DC (2 STDS) AND 5" HWDP (3 STDS).
OZARK UNIT 1H | 7 | 2021-06-21 03:30 | 2021-06-21 05:00 | 1.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 2.08 | 3845 | 3845 | 0 | TRIP IN HOLE F/BHA T/3,697'. PICK UP AGITATOR ON STAND 22: PSI BEFORE-400, PSI AFTER-470 @ 326 GPM.
OZARK UNIT 1H | 7 | 2021-06-21 05:00 | 2021-06-21 06:00 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 2.13 | 3845 | 3845 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD, FILL GAS SEPERATOR, PERORM BOP DRILL, RESPONSE TIME= 48 SECONDS.
OZARK UNIT 1H | 8 | 2021-06-21 06:00 | 2021-06-21 06:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.15 | 3845 | 3845 | 0 | FINISH FILLING GAS SEPERATOR, PERORM BOP DRILL BEFORE DRILLING OUT, RESPONSE TIME= 60 SECONDS.
OZARK UNIT 1H | 8 | 2021-06-21 06:30 | 2021-06-21 07:30 | 1 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 2.19 | 3845 | 3855 | 10 | DRILL SHOE TRACK AND 10' NEW FORMATION F/3,845' T/3,855', GPM-350, SPP-1000/1400 PSI, DIFF-200/400, RPM-30, TQ-2/4K.
OZARK UNIT 1H | 8 | 2021-06-21 07:30 | 2021-06-21 08:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.21 | 3855 | 3855 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-350, SPP-1050 PSI, RPM-30.
OZARK UNIT 1H | 8 | 2021-06-21 08:00 | 2021-06-21 08:30 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 2.23 | 3855 | 3855 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, 560 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,835' / TVD-3,831'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE ON THE REMOTE CHOKE PANEL.
OZARK UNIT 1H | 8 | 2021-06-21 08:30 | 2021-06-21 12:00 | 3.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.38 | 3855 | 4758 | 258 | ROT (903' IN 3.32 HRS @ 272 FPH) WOB: 20/30K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/10K, SPP: 3500/4300 PSI, DIFF: 600/800 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 8 | 2021-06-21 12:00 | 2021-06-21 12:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.4 | 4758 | 4778 | 40 | SLIDE (20' IN .18 HRS @ 111.1 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3500/3800 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/4166' T/4176' 10' TF-150 F/10:08-10:13 SLD F/4569' T/4579' 10' TF-180 F/11:20-11:26
OZARK UNIT 1H | 8 | 2021-06-21 12:30 | 2021-06-21 13:30 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.44 | 4778 | 5267 | 489 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT LINER AND LINER GASKET ON #2 MUD PUMP, ROT (489' IN .68 HRS @ 291.1 FPH) WOB: 15/25K, SPM: 110/110, GPM: 700, MMRPM: 116, RPM-80, TRPM: 196, TRQ: 5K/10K, SPP: 3000/3400 PSI, DIFF: 200/400 PSI.
OZARK UNIT 1H | 8 | 2021-06-21 13:30 | 2021-06-21 14:00 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.46 | 5267 | 5297 | 60 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT LINER AND LINER GASKET ON #2 MUD PUMP, SLIDE (20' IN .18 HRS @ 111.1 FPH) WOB: 10/20K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 3000/3200 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/4825' T/4835' 10' TF-180 F/12:18-12:26 SLD F/5109' T/5129' 10' TF-180 F/13:18-13:29
OZARK UNIT 1H | 8 | 2021-06-21 14:00 | 2021-06-21 14:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.48 | 5297 | 5663 | 732 | ROT (366' IN .9 HRS @ 406.7 FPH) WOB: 20/30K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/10K, SPP: 3500/4300 PSI, DIFF: 600/800 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 8 | 2021-06-21 14:30 | 2021-06-21 15:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.5 | 5663 | 5673 | 20 | SLIDE (10' IN .10 HRS @ 100 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3500/3800 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/ 5584' T/ 5594' 10' TF-120 F/14:45-14:51
OZARK UNIT 1H | 8 | 2021-06-21 15:00 | 2021-06-21 16:00 | 1 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.54 | 5673 | 5673 | 0 | SERVICE TOP DRIVE, ST-80 AND DRAW WORKS.
OZARK UNIT 1H | 8 | 2021-06-21 16:00 | 2021-06-21 19:00 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.67 | 5673 | 6604 | 310.3 | ROT (951' IN 2.97 HRS @ 320 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4000/4700 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 8 | 2021-06-21 19:00 | 2021-06-21 19:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.68 | 6604 | 6624 | 80 | SLIDE (20' IN .28 HRS @ 71.4 FPH) WOB: 9K/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4100 PSI, DIFF: 180/300 PSI. SLIDE DEPTHS: SLD F/5950 T/5960 10' TF-90M F/16:55-17:04 SLD F/6335 T/6345 10' TF-90M F/18:10-18:26
OZARK UNIT 1H | 8 | 2021-06-21 19:15 | 2021-06-21 20:00 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.71 | 6624 | 6805 | 241.3 | CONTROL DRILL ON #2 AND #3 MUD PUMPS WHILE CHANGING OUT SWAB ON #1 MUD PUMP, ROTATE (181' IN .75 HRS @ 241.3 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 2600/3000 PSI, DIFF: 150/500 PSI.
OZARK UNIT 1H | 8 | 2021-06-21 20:00 | 2021-06-21 21:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.75 | 6805 | 7162 | 357 | ROT (357' IN 1 HRS @ 357 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4000/4700 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 8 | 2021-06-21 21:00 | 2021-06-21 21:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.76 | 7162 | 7172 | 40 | SLIDE (10' IN .23 HRS @ 42.9 FPH) WOB: 9K/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4100 PSI, DIFF: 180/300 PSI. SLIDE DEPTHS: SLD F/6806 T/6816 10' TF-160M F/20:00-20:14
OZARK UNIT 1H | 8 | 2021-06-21 21:15 | 2021-06-22 00:30 | 3.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.9 | 7172 | 7938 | 235.7 | CONTROL DRILL ON #2 AND #3 MUD PUMPS WHILE CHANGING OUT LINER GASKET ON #1 MUD PUMP, ROTATE (756' IN 3.13 HRS @ 241.5 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 2600/3000 PSI, DIFF: 150/500 PSI. SLIDE DEPTHS: SLD F/7464 T/7474 10' TF-140M F/22:15-22:22 SLD F/7837 T/7849 12' TF-150M F/23:51-00:04
OZARK UNIT 1H | 8 | 2021-06-22 00:30 | 2021-06-22 01:30 | 1 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.94 | 7938 | 7938 | 0 | CIRCULATE AND WORK PIPE WITH ONE PUMP WHILE CHANGE OUT SWAB ON MP #2 AND LINER GASKET ON MP #1.
OZARK UNIT 1H | 8 | 2021-06-22 01:30 | 2021-06-22 03:30 | 2 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.02 | 7938 | 8295 | 178.5 | CONTROL DRILL ON #2 AND #3 MUD PUMPS WHILE CHANGING OUT LINER GASKET ON #1 MUD PUMP, ROTATE (357' IN 1.43 HRS @ 249.7 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 2600/3000 PSI, DIFF: 150/500 PSI. SLIDE DEPTHS: SLD F/7938 T/7950 12' TF-150M F/01:30-01:50
OZARK UNIT 1H | 8 | 2021-06-22 03:30 | 2021-06-22 04:00 | 0.5 | U | INTHL | WAIT | WOW | WAIT ON WEATHER | 3.04 | 8295 | 8295 | 0 | WAIT ON WEATHER DUE TO LIGHTNING WITHIN 5 MILES OF RIG.
OZARK UNIT 1H | 8 | 2021-06-22 04:00 | 2021-06-22 05:15 | 1.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.09 | 8295 | 8558 | 210.4 | CONTROL DRILL ON #2 AND #3 MUD PUMPS WHILE CHANGING OUT LINER GASKET ON #1 MUD PUMP, ROTATE (263' IN 1.25 HRS @ 201.4 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 4400/5000 PSI, DIFF: 400/650 PSI.
OZARK UNIT 1H | 8 | 2021-06-22 05:15 | 2021-06-22 06:00 | 0.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.13 | 8558 | 8690 | 176 | ROT (132' IN .75 HRS @ 176 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4200/4900 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 9 | 2021-06-22 06:00 | 2021-06-22 07:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.17 | 8690 | 8861 | 171 | ROT (172' IN 1 HR @ 172 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4200/4900 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 9 | 2021-06-22 07:00 | 2021-06-22 08:00 | 1 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.21 | 8861 | 8861 | 0 | PERFORM RIG SERVICE, TROUBLESHOOT TOP DRIVE TORQUE CABLE CONNECTIONS.
OZARK UNIT 1H | 9 | 2021-06-22 08:00 | 2021-06-22 09:30 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.27 | 8861 | 9006 | 96.7 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CLEANING OUT SUCTION ON #2 MUD PUMP, ROTATE (145' IN 1.5 HRS @ 96.7 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 4400/5000 PSI, DIFF: 400/650 PSI.
OZARK UNIT 1H | 9 | 2021-06-22 09:30 | 2021-06-22 13:30 | 4 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.44 | 9006 | 9006 | 0 | CIRCULATE WITH #3 MUD PUMP AND WORK PIPE WHILE CLEANING OUT SUCTION ON #2 MUD PUMP AND CHANGE SWAB AND WEAR PLATE ON #1 MUD PUMP.
OZARK UNIT 1H | 9 | 2021-06-22 13:30 | 2021-06-22 16:30 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.56 | 9006 | 9610 | 201.3 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CLEANING OUT SUCTION ON #2 MUD PUMP, ROTATE (594' IN 2.75 HR @ 216 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 4400/5000 PSI, DIFF: 400/650 PSI. SLIDE DEPTHS: SLD F/9426 T/9436 10' TF-150M F/15:31-15:45
OZARK UNIT 1H | 9 | 2021-06-22 16:30 | 2021-06-22 19:45 | 3.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.7 | 9610 | 10236 | 192.6 | CONTROL DRILL ON #2 AND #3 MUD PUMPS WHILE CHANGE SWABS ON #1 MUD PUMP, ROTATE (611' IN 2.83 HR @ 215.9 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 4400/5000 PSI, DIFF: 400/650 PSI. SLIDE DEPTHS: SLD F/9998 T/10013 15' TF-160M F/18:26-18:51
OZARK UNIT 1H | 9 | 2021-06-22 19:45 | 2021-06-23 01:00 | 5.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.92 | 10236 | 11537 | 247.8 | ROT (1,297' IN 5.33 HR @ 243.3 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4200/4900 PSI, DIFF: 500/700 PSI. SLIDE DEPTHS: SLD F/9998 T/10013 15' TF-160M F/18:26-18:51 NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 9 | 2021-06-23 01:00 | 2021-06-23 03:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4 | 11537 | 11603 | 33 | SLIDE (66' IN 2.19 HRS @ 30.2 FPH) WOB: 9K/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4100 PSI, DIFF: 180/300 PSI. SLIDE DEPTHS: SLD F/10278 T/10293 15' TF-150M F/20:04-20:35 SLD F/10564 T/10579 15' TF-160M F/21:41-22:10 SLD F/11218 T/11236 18' TF-120M F/00:22-00:53 SLD F/11595 T/11613 18' TF-75M F/02:43-03:29
OZARK UNIT 1H | 9 | 2021-06-23 03:00 | 2021-06-23 03:45 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.03 | 11603 | 11650 | 62.7 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGE SWAB ON #2 MUD PUMP, ROTATE (118' IN .75 HR @ 157.3 FPH) WOB: 20/30K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 4400/5000 PSI, DIFF: 400/650 PSI.
OZARK UNIT 1H | 9 | 2021-06-23 03:45 | 2021-06-23 04:00 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.04 | 11650 | 11721 | 284 | ROT (71' IN .25 HR @ 284 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4200/4900 PSI, DIFF: 500/700 PSI.
OZARK UNIT 1H | 9 | 2021-06-23 04:00 | 2021-06-23 05:30 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.1 | 11721 | 11887 | 110.7 | CONTROL DRILL ON #1 AND #2 MUD PUMPS WHILE CHANGE LINER GASKET ON #3 MUD PUMP, ROTATE (172' IN .98 HR @ 175.5 FPH) WOB: 20/35K, SPM: 110/110, GPM: 700, MMRPM: 116, SPP: 4400/5000 PSI, DIFF: 400/650 PSI. SLIDE DEPTHS: SLD F/11782 T/11802 20' TF-90M F/04:25-05:01
OZARK UNIT 1H | 9 | 2021-06-23 05:30 | 2021-06-23 06:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.13 | 11887 | 11913 | 52 | ROT (26' IN .5 HR @ 52 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4200/4900 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
OZARK UNIT 1H | 10 | 2021-06-23 06:00 | 2021-06-23 06:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.15 | 11913 | 11944 | 62 | STARTED BUILDING INT. CURVE ON 6/23/21 @ 06:00 (11,913' MD / 11,907' TVD); BUILD CURVE/SLD (31' IN .5 HRS @ 62 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 700/800 PSI. SLIDE DEPTHS: SLD F/11913' T/11944' 31' TF-130M 0600-0630
OZARK UNIT 1H | 10 | 2021-06-23 06:30 | 2021-06-23 08:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.21 | 11944 | 11971 | 18 | BUILD CURVE/SLD (27' IN 1.5 HRS @ 18 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/11944' T/11971' 27' TF-130M 0630-0800 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING A VALVE AND SEAT ON #1 MUD PUMP
OZARK UNIT 1H | 10 | 2021-06-23 08:00 | 2021-06-23 11:30 | 3.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.35 | 11971 | 12064 | 26.6 | BUILD CURVE/SLD (93' IN 3.5 HRS @ 26.57 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 700/800 PSI. SLIDE DEPTHS: SLD F/11971' T/12064' 93' TF-130M 0800-1130
OZARK UNIT 1H | 10 | 2021-06-23 11:30 | 2021-06-23 12:30 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.4 | 12064 | 12088 | 24 | BUILD CURVE/SLD (24' IN 1 HRS @ 24 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/12064' T/12088' 24' TF-130M 1130-1230 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING A VALVE AND SEAT ON #1 MUD PUMP
OZARK UNIT 1H | 10 | 2021-06-23 12:30 | 2021-06-23 13:30 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.44 | 12088 | 12105 | 17 | BUILD CURVE/SLD (17' IN 1 HRS @ 17 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 700/800 PSI. SLIDE DEPTHS: SLD F/12088' T/12105' 17' TF-130M 1230-1330
OZARK UNIT 1H | 10 | 2021-06-23 13:30 | 2021-06-23 14:30 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.48 | 12105 | 12145 | 40 | BUILD CURVE/SLD (40' IN 1 HRS @ 40 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/12105' T/12145' 24' TF-130M 1330-1430 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING A CAP GASKET ON #1 MUD PUMP
OZARK UNIT 1H | 10 | 2021-06-23 14:30 | 2021-06-23 19:30 | 5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.69 | 12145 | 12246 | 20.2 | BUILD CURVE/SLD (101' IN 5.25 HRS @ 19.24 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/12145' T/12222' 77' TF-140M 1430-1800 SLD F/12222' T/12246' 24' TF-140M 1800-2000
OZARK UNIT 1H | 10 | 2021-06-23 19:30 | 2021-06-23 20:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.71 | 12246 | 12250 | 8 | BUILD CURVE/ROT (4' IN .25 HRS @ 16 FPH) WOB: 25/30K, RPM-30, TRQ-7/14K SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI.
OZARK UNIT 1H | 10 | 2021-06-23 20:00 | 2021-06-23 22:30 | 2.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 4.81 | 12250 | 12250 | 0 | PERFORMED CLEAN UP CYCLE PUMPING 2-30 BBL SWEEPS SURFACE TO SURFACE TO CLEAN HOLE & PREP OPEN HOLE FOR 7-5/8" CASING. GPM-866, SPP-5100, RPM-80, TQ=9/13K, SHAKERS CLEAN.
OZARK UNIT 1H | 10 | 2021-06-23 22:30 | 2021-06-23 23:00 | 0.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.83 | 12250 | 12250 | 0 | PUMPED SLUG AND PERFORMED FLOW CHECK (NO FLOW DETECTED). PULLED 5 STANDS OF DRILL PIPE & RACKED SAME BACK INTO DERRICK TO INSURE HOLE WAS NOT TIGHT.
OZARK UNIT 1H | 10 | 2021-06-23 23:00 | 2021-06-24 03:30 | 4.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.02 | 12250 | 12250 | 0 | LAYED DOWN 5" DRILL PIPE F/11,775' - T/7562', PROPER FILL NOTE: WORK THROUGH TIGHT SPOTS UNTILL CLEAN F/8347' T/8293', F/8040' T/8000'
OZARK UNIT 1H | 10 | 2021-06-24 03:30 | 2021-06-24 04:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.04 | 12250 | 12250 | 0 | RIG SERVICE
OZARK UNIT 1H | 10 | 2021-06-24 04:00 | 2021-06-24 06:00 | 2 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.13 | 12250 | 12250 | 0 | CONTINUE LAYED DOWN 5" DRILL PIPE F/7562' - T/6000', PROPER FILL WORK TIGHT SPOT AT 6860'
OZARK UNIT 1H | 11 | 2021-06-24 06:00 | 2021-06-24 08:30 | 2.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.23 | 12250 | 12250 | 0 | CONTINUE TO LAY DOWN DRILL PIPE F/6,000' T/3,363'. HOLE TAKING EXCESS FILL DURING TRIP OUT; CALCULATED FILL 3.9 BBLS PER 5 STD/AVERAGE HOLE FILL 5.1 BBLS PER 5 STDS; NO EXCESS PULL WHILE TRIPPING OUT.
OZARK UNIT 1H | 11 | 2021-06-24 08:30 | 2021-06-24 09:30 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.27 | 12250 | 12250 | 0 | RIG SERVICE; REPLACE ST-80 DIES
OZARK UNIT 1H | 11 | 2021-06-24 09:30 | 2021-06-24 10:30 | 1 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.31 | 12250 | 12250 | 0 | CONTINUE LAYED DOWN 5" DRILL PIPE F/3363' - T/2987', TIH 6 STANDS, CONTINUE L/D DP; HOLE TAKING EXCESS FILL DURING TRIP OUT; CALCULATED FILL 3.9 BBLS PER 5 STD/AVERAGE HOLE FILL 5.1 BBLS PER 5 STDS; NO EXCESS PULL WHILE TRIPPING OUT.
OZARK UNIT 1H | 11 | 2021-06-24 10:30 | 2021-06-24 11:00 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 5.33 | 12250 | 12250 | 0 | FLOW CHECK @ 2,987'; REMOVE ROT HEAD/ INSTALL TRIP NIPPLE
OZARK UNIT 1H | 11 | 2021-06-24 11:00 | 2021-06-24 15:30 | 4.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 5.52 | 12250 | 12250 | 0 | CONTINUE LAYING DOWN 5" DRILL PIPE F/2987' - T/BHA', TIH 6 STANDS, CONTINUE L/D DP; HOLE TAKING EXCESS FILL DURING TRIP OUT; CALCULATED FILL 3.9 BBLS PER 5 STD/AVERAGE HOLE FILL 5.1 BBLS PER 5 STDS; NO EXCESS PULL WHILE TRIPPING OUT. NOTE: USE RIG TONGS TO BREAK PIPE F/1630' T/BHA DUE TO TIGHT CONNECTIONS
OZARK UNIT 1H | 11 | 2021-06-24 15:30 | 2021-06-24 18:00 | 2.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 5.63 | 12250 | 12250 | 0 | FLOW CHECK @ BHA; LAY DOWN BHA AND DIRECTIONAL BHA; L/D 9 JTS OF HWDP, X-OVER SUB, 6 JTS OF 6.5" DC, X-OVER SUB, 2 NMDC, UBHO SUB, NMPC, MUD MOTOR, AND BIT; BIT IN GREAT CONDITION, 2 SLIGHTLY WORN CUTTERS ON GUAGE; MUD MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG
OZARK UNIT 1H | 11 | 2021-06-24 18:00 | 2021-06-24 19:30 | 1.5 | P | INTHLCSG | SFTY | INSPT | SAFETY INSPECTION | 5.69 | 12250 | 12250 | 0 | CLEAN OBM FROM RIG FLOOR TO REDUCE SLIP HAZARDS, PULL WEAR BUSHING, COMPANY REPRESENTIVE WITNESS. REMOVE ALL 5" HANDLING TOOLS FROM RIG FLOOR
OZARK UNIT 1H | 11 | 2021-06-24 19:30 | 2021-06-24 22:00 | 2.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 5.79 | 12250 | 12250 | 0 | HOLD PJSM AND RIG UP FRANKS CSG CREW WHILE CHANGE OUT TOP RAMS, TEST BONNET SEALS TO 1500 PSI
OZARK UNIT 1H | 11 | 2021-06-24 22:00 | 2021-06-25 06:00 | 8 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 6.13 | 12250 | 12250 | 0 | HELD PJSM W/FRANK'S CASING; MAKE UP SHOE TRACK, TEST FLOATS, BEGIN RUNNING INTERMEDIATE CASING T/5,400', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT NOTE: CHANGING OUT 5 1/4" LINERS AND SWABS TO 4 3/4" LINERS AND SWABS, ON ALL 3 MUD PUMPS WHILE RUNNING INTERMEDIATE CSG.
OZARK UNIT 1H | 12 | 2021-06-25 06:00 | 2021-06-25 12:00 | 6 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 6.38 | 12250 | 12250 | 0 | CONTINUE PICKING UP AND RUNNING 7 5/8" 29.7# P-110 HC ERW BTC CSG F/ 5,400' T/12,238', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT,RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 270 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-7 5/8" 29.7# P-110 HC ERW BTC PUP JOINT, 1 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TOTAL OF 274 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALLED 47 LATCH ON BOW SPRING CENTRALIZERS @ 11,927' AND EVERY 4TH JT UP TO 3,798'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/280K (W/O BLOCKS) FLOAT SHOE-12,236.4' TOP OF FLOAT COLLAR-12,146.8' 13 JOINTS LEFT OUT- 573.46' & 1-15' PUP JT OUT
OZARK UNIT 1H | 12 | 2021-06-25 12:00 | 2021-06-25 12:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 6.4 | 12250 | 12250 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
OZARK UNIT 1H | 12 | 2021-06-25 12:30 | 2021-06-25 14:00 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.46 | 12250 | 12250 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 64/64, 8.0 BPM, SPP: 500 PSI, NO LOSSES.
OZARK UNIT 1H | 12 | 2021-06-25 14:00 | 2021-06-25 17:00 | 3 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 6.58 | 12250 | 12250 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/5000 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 366 BBL 11.8 PPG 1060 SK 1.94 YIELD 50/50 POZ-HW-STX-CLASS H LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 558 BBLS OF 9.7 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1300 PSI AT 3 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/1700 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI (4 BBLS)-FLOATS HELD. FINISHED CEMENTING @ 16:50 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. LOST RETURNS AFTER PUMPING 520 BBLS INTO DISPLACEMENT. 0 BBLS SPACER AND 0 BBLS CEMENT BACK TO SURFACE. ESTIMATED TOP OF CEMENT: 3,325'
OZARK UNIT 1H | 12 | 2021-06-25 17:00 | 2021-06-25 17:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 6.6 | 12250 | 12250 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. BLED BACK 7 BBLS
OZARK UNIT 1H | 12 | 2021-06-25 17:30 | 2021-06-25 18:00 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 6.63 | 12250 | 12250 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
OZARK UNIT 1H | 12 | 2021-06-25 18:00 | 2021-06-25 20:00 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 6.71 | 12250 | 12250 | 0 | FLUSH THROUGH BOP AND FLOW LINE WITH WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
OZARK UNIT 1H | 12 | 2021-06-25 20:00 | 2021-06-26 03:00 | 7 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 7 | 12250 | 12250 | 0 | CHANGE OUT TOP RAMS (INSTALLED VBR'S), SAVER SUB, HYDRAULIC IBOP AND DIES IN GRABBER BOX, CLEAN IN LINE SCREEN WHILE REMOVE CHECK VALVE FOR BOP TEST
OZARK UNIT 1H | 12 | 2021-06-26 03:00 | 2021-06-26 06:00 | 3 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 7.13 | 12250 | 12250 | 0 | INSTALL TEST PLUG, TEST CHOKE MANIFOLD 250/10,000, TEST BOPE 250/10,000 W/4.5' & 5.5' DP, TEST BACK TO MUD PUMPS 250/6500, TEST ORBIT VALVE 250/1500
OZARK UNIT 1H | 13 | 2021-06-26 06:00 | 2021-06-26 09:00 | 3 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 7.25 | 12250 | 12250 | 0 | CONTINUE TEST BOPE TO 250 LOW / 10,000 HIGH. TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS,TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS. TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, AND HCR. TEST KILL LINE BACK TO MUD PUMPS 250 LOW / 5,000 HIGH. TEST FOSV AND INSIDE GREY 250 PSI LOW / 10,000 PSI HIGH; TEST TD FOSV, IBOP, STANDPIPE 4" VALVE AND BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH; TEST INSIDE AND OUTSIDE KILL LINE VALVES, 4" MANUAL VALVE, AND HCR 250 PSI LOW / 10,000 PSI HIGH,TEST ANNULAR W/4.5" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST
OZARK UNIT 1H | 13 | 2021-06-26 09:00 | 2021-06-26 09:30 | 0.5 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 7.27 | 12250 | 12250 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE, AND MOUSE HOLE; WEAR BUSHING I.D. 7 3/4"
OZARK UNIT 1H | 13 | 2021-06-26 09:30 | 2021-06-26 10:30 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.31 | 12250 | 12250 | 0 | REPLACE HYDRAULIC HOSE AND CHANGE ST-80 DIES
OZARK UNIT 1H | 13 | 2021-06-26 10:30 | 2021-06-26 12:00 | 1.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 7.38 | 12250 | 12250 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13601236 JETS 6/18S TFA: 1.491), 5.5", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.05' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, 33 STANDS DP, ON DEMAND AGITATOR. BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD).
OZARK UNIT 1H | 13 | 2021-06-26 12:00 | 2021-06-27 05:00 | 17 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 8.08 | 12250 | 12250 | 0 | PICK UP AND TRIP IN THE HOLE WITH 4.5" DRILL PIPE F/BHA T/2823', PICK UP AGITATOR AFTER STAND 28, BEFORE AGITATOR: GPM-262, SPM-100, BEFORE AGITATOR: SPP-940 PSI; AFTER AGITATOR: SPP-1580 PSI, CONTINUE PICKING UP AND TRIPPING IN THE HOLE F/2823' T/5930', PICK UP ON DEMAND AGITATOR AFTER STAND 61 (33 STANDS), BEFORE AGITATOR: GPM-130, SPM-50, SPP-720 PSI; AFTER AGITATOR: SPP- 680 PSI. FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT. CONTINUE PICKING UP AND TRIPPING IN THE HOLE F/5952' T/12003', STARTED TAKING WEIGHT AT 12003', WASH F/12003' T/12026' (160-GPM, 900 PSI, MUD WT IN 11.0 PPG)
OZARK UNIT 1H | 13 | 2021-06-27 05:00 | 2021-06-27 06:00 | 1 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 8.13 | 12250 | 12250 | 0 | SLIP AND CUT 60' DRILL LINE, CHECK HI/LO STOP POINTS
OZARK UNIT 1H | 14 | 2021-06-27 06:00 | 2021-06-27 06:30 | 0.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 8.15 | 12250 | 12250 | 0 | CONT SLIP AND CUT 60' OF DRILL LINE.
OZARK UNIT 1H | 14 | 2021-06-27 06:30 | 2021-06-27 07:30 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.19 | 12250 | 12250 | 0 | RIG SERVICE, GREASE ST-80, TOP DRIVE & DRAWWORKS
OZARK UNIT 1H | 14 | 2021-06-27 07:30 | 2021-06-27 08:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 8.21 | 12250 | 12250 | 0 | PULL TRIP NIPPLE & INSTALL ROTATING HEAD
OZARK UNIT 1H | 14 | 2021-06-27 08:00 | 2021-06-27 09:00 | 1 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 8.25 | 12250 | 12260 | 10 | DRLD CEMENT F/12045' T/12146', TAGGED FLOAT COLLAR @ 12146'', DRILL FLOAT COLLAR AND SHOE TRACK TO 12238', DRILL SHOE AND 10' OF NEW FORMATION F/12238' T/12260', GPM-192, SPP-1900/2000 PSI, RPM-30, TRQ-2/7K MRPM-130, TRPM-160, DIFF-100-200 PSI. NOTE: DISPLACE 9.7 PPG OBM WITH 11.0 PPG OBM
OZARK UNIT 1H | 14 | 2021-06-27 10:30 | 2021-06-27 22:00 | 11.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.79 | 12260 | 12944 | 59.5 | BUILD CURVE-SLIDE (684' IN 11.5 HR @ 59.48 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, SPP-5500/6000 PSI, DIFF-500/600 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/12260' T/12425' 165' TF-20R 1030-1439 SLD F/12445' T/12565' 120' TF-20L 1452-1700 SLD F/12585' T/12660' 75' TF-HS 1713-1800 SLD F/12680' T/12756' 76' TF-10L 1830-1950 SLD F/12781' T/12851' 70' TF-10L 2010-2100 SLD F/12876' T/12944' 68' TF-HS 2120-2205
OZARK UNIT 1H | 14 | 2021-06-27 22:00 | 2021-06-27 23:30 | 1.5 | P | PRDHLCV | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 8.85 | 12944 | 12944 | 0 | PICK UP AND SPACE OUT, SHUT TOP RAMS, CIRCULATE OUT GAS AND WEIGHT UP F/11.0 PPG T/11.3 PPG, SPM-76/76, GPM-400, SPP-6000 PSI, CHOKES- 35-42% / FLARE-25-35', NO MUD CUT, MAX CASING PRESSURE= 1362 PSI, AVG CASING PRESSURE= 900 PSI, MAX GAS-1887u, FINAL CASING PRESSURE= 770 PSI, OPEN TOP RAMS. RESUME DRLG THROUGH CHOKE
OZARK UNIT 1H | 14 | 2021-06-27 23:30 | 2021-06-28 04:30 | 5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.06 | 12944 | 13277 | 66.6 | BUILD CURVE-SLIDE (333' IN 5 HR @ 66.6 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-5700/6500 PSI, DIFF-500/700 PSI, CHOKES- 36-52% / 0%, FLARE-3'-25', NO MUD CUT, MAX CASING PRESSURE= 970 PSI, AVG CASING PRESSURE= 335 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1200 PSI, SLIDE DEPTHS: SLD F/13112' T/13162' 50' TF-HS 0120-0245 SLD F/13228' T/13277' 49' TF-HS 0330-0415 NOTE: MUD WT 11.3 PPG.
OZARK UNIT 1H | 14 | 2021-06-28 04:30 | 2021-06-28 04:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 9.06 | 13277 | 13277 |  | MILESTONE_END CURVE SECTION ON 6/28/2021 @ 04:30
OZARK UNIT 1H | 14 | 2021-06-28 04:30 | 2021-06-28 06:00 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.13 | 13277 | 13427 | 100 | ROTATE DRLD LATERAL F/13277' T/13427' (150' IN 1.5 HR @ 100 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM 50-80, TQ 7-10K, MRPM-272, SPP-5700/6700 PSI, DIFF-700/900 PSI, CHOKES- 36-52% / 0%, FLARE-3'-25', NO MUD CUT, MAX CASING PRESSURE= 970 PSI, AVG CASING PRESSURE= 335 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1200 PSI,
OZARK UNIT 1H | 14 | 2021-06-28 04:30 | 2021-06-28 04:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 9.06 | 13277 | 13277 |  | MILESTONE_START LATERAL SECTION ON 6/28/2021 @ 04:30
OZARK UNIT 1H | 15 | 2021-06-28 06:00 | 2021-06-28 07:30 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.19 | 13427 | 13616 | 126 | ROT(207' IN 1.68 HRS @ 123 FPH) WOB-25/35K, SPM-70/70, GPM-375, RPM 80, TQ 7-12K, MRPM-255, SPP-5700/6700 PSI, DIFF-700/1000 PSI, CHOKES- 36-52% / 0%, FLARE-3'-25', NO MUD CUT, MAX CASING PRESSURE= 590 PSI, AVG CASING PRESSURE= 335 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 890 PSI
OZARK UNIT 1H | 15 | 2021-06-28 07:30 | 2021-06-28 08:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.21 | 13616 | 13628 | 24 | SLD(12' IN .32 HRS @ 37.5 FPH) WOB-25/35K, SPM-70/70, GPM-375, MRPM-255, SPP-5700/6700 PSI, DIFF-700/1000 PSI, CHOKES- 36-52% / 0%, FLARE-3'-25', NO MUD CUT, MAX CASING PRESSURE= 590 PSI, AVG CASING PRESSURE= 335 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 890 PSI. WT UP F/11.3 PPG T/11.5 PPG SLIDE DEPTHS: SLD F/13616' T/13628' 12' TF-180 725-744
OZARK UNIT 1H | 15 | 2021-06-28 08:00 | 2021-06-28 08:30 | 0.5 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 9.23 | 13646 | 13646 | 0 | PICK UP AND SPACE OUT, SHUT TOP RAMS, CIRCULATE OUT GAS, SPM-70/70, GPM-375, SPP-6000 PSI, CHOKES- 35-42% / 0% FLARE-25-35', NO MUD CUT, MAX CASING PRESSURE= 1362 PSI, AVG CASING PRESSURE= 900 PSI, MAX GAS-1887u, FINAL CASING PRESSURE= 770 PSI, OPEN TOP RAMS.
OZARK UNIT 1H | 15 | 2021-06-28 08:30 | 2021-06-29 02:30 | 18 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.98 | 13646 | 16028 | 132.3 | ROT(2382' IN 17.83 HRS @ 133.59 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM 80, TQ 7-12K, MRPM-272, SPP-5700/6700 PSI, DIFF-700/1000 PSI, CHOKES- 0% / 100%, FLARE-3'-25', NO MUD CUT, MAX CASING PRESSURE= 1215 PSI, AVG CASING PRESSURE= 300 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1846 PSI NOTE: WT UP F/11.5 PPG T/11.7 PPG AT 11:00
OZARK UNIT 1H | 15 | 2021-06-29 02:30 | 2021-06-29 06:00 | 3.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.13 | 16028 | 16129 | 28.9 | SLD(101' IN 3.67 HRS @ 27.52 FPH) WOB-25/35K, SPM-70/70, GPM-400, MRPM-272, SPP-5700/6700 PSI, DIFF-700/1000 PSI, CHOKES- 0% / 100%, FLARE-3'-25', NO MUD CUT, MAX CASING PRESSURE= 629 PSI, AVG CASING PRESSURE= 38 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 770 PSI MUD WT 11.7 PPG SLIDE DEPTHS: SLD F/14181' T/14191' 10' TF-20R 1258-120 SLD F/14370' T/14384' 14' TF-180 1437-1503 SLD F/14563' T/14575' 12' TF-180 1609-1632 SLD F/14751' T/14766' 15' TF-180 1736-1800 SLD F/15130 T/15142 12' TF-HI SIDE 2020-2045 SLD F/15414 T/15424 10' TF-140L 2250-2310 SLD F/15607 T/15615 8' TF-20L 0050-0110 SLD F/15795 T/15805 10' TF-45L 0235-0305 SLD F/16078 T/16088 10' TF-70L 0515-0545
OZARK UNIT 1H | 16 | 2021-06-29 06:00 | 2021-06-29 07:30 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.19 | 16129 | 16220 | 60.7 | ROT(91' IN HRS @ 1.77 FPH) WOB-25/35K, SPM-70/70, GPM-375, RPM 80, TQ 12-20K, MRPM-255, SPP-5700/6700 PSI, DIFF-700/1000 PSI, CHOKES- 0% / 100%, FLARE-2'-10', NO MUD CUT, MAX CASING PRESSURE= 500 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 500 PSI, MUD WT 11.7 PPG
OZARK UNIT 1H | 16 | 2021-06-29 07:30 | 2021-06-29 08:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.21 | 16220 | 16230 | 20 | SLD(10' IN .23 HRS @ 42.86 FPH) WOB-15/28K, SPM-70/70, GPM-375, MRPM-255, SPP-5700/6700 PSI, DIFF-700/1000 PSI, CHOKES- 0% / 100%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 500 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 500 PSI, MUD WT 11.7 PPG SLIDE DEPTHS: SLD F/16171' T/16181' 10' TF-180 0638-0652
OZARK UNIT 1H | 16 | 2021-06-29 08:00 | 2021-06-29 09:15 | 1.25 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 10.26 | 16230 | 16230 | 0 | PUMPED 20 BBL OBM SWEEP, CIRCULATED BOTTOMS UP, SPM-74/74, GPM-385, MRPM-262, RPM-80, TRQ-6/8K, SPP-5300 PSI. CHOKES 0% - 100%. MAX CASING PRESSURE WHILE CIRC- 0 PSI.
OZARK UNIT 1H | 16 | 2021-06-29 09:15 | 2021-06-29 10:30 | 1.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.31 | 16230 | 16230 | 0 | STRIP OUT THE HOLE F/16,230’ T/15,189’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 885 PSI AND FINAL CASING PRESSURE= 252 PSI.
OZARK UNIT 1H | 16 | 2021-06-29 10:30 | 2021-06-29 11:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.33 | 16230 | 16230 | 0 | RIG SERVICE, REPAIR HYDRAULIC HOSE ON ST-80
OZARK UNIT 1H | 16 | 2021-06-29 11:00 | 2021-06-29 12:30 | 1.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.4 | 16230 | 16230 | 0 | STRIP OUT THE HOLE F/15,189’ T/12,338’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 550 PSI AND FINAL CASING PRESSURE= 485 PSI.
OZARK UNIT 1H | 16 | 2021-06-29 12:30 | 2021-06-29 13:15 | 0.75 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.43 | 16230 | 16230 | 0 | CIRCULATE BTM'S UP 100' OUTSIDE SHOE @ 12,338' GPM-375, RPM-20, SPP-4800 PSI; CP-0 PSI, NO FLARE; MAX GAS-1,437U
OZARK UNIT 1H | 16 | 2021-06-29 13:15 | 2021-06-29 13:30 | 0.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.44 | 16230 | 16230 | 0 | STRIP OUT THE HOLE ABOVE TOP OF CURVE F/12,338’ T/11,855’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS.
OZARK UNIT 1H | 16 | 2021-06-29 13:30 | 2021-06-29 15:00 | 1.5 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 10.5 | 16230 | 16230 | 0 | MONITOR CASING PSI, SICP BUILT TO 885 PSI; PUMP 187 BBLS OF 17.0 PPG KILL MUD AND CHASE WITH 86 BBLS OF 11.7 PPG OBM; BOTTOM OF MUD CAP @ 11,855', TOP OF MUD CAP @ 7,795' AFTER PULLING DP OUT OF MUD CAP.
OZARK UNIT 1H | 16 | 2021-06-29 15:00 | 2021-06-29 18:00 | 3 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.63 | 16230 | 16230 | 0 | STRIP OUT THE HOLE F/11,855’ T/7,795’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 191 PSI AND FINAL CASING PRESSURE= 0 PSI.
OZARK UNIT 1H | 16 | 2021-06-29 18:00 | 2021-06-29 19:00 | 1 | P | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 10.67 | 16230 | 16230 | 0 | PERFORM FLOW CHECK THROUGH GAS SEPARATOR AND THEN DOWN FLOWLINE - NO FLOW. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
OZARK UNIT 1H | 16 | 2021-06-29 19:00 | 2021-06-29 23:30 | 4.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.85 | 16230 | 16230 | 0 | POOH F/7,795' T/DIRECTIONAL BHA. HOLE TOOK PROPER FILL ON TRIP OUT. NOTE: USED RIG TONGS F/3,921' T/3,000' DUE TO OVER TORQUED CONNECTIONS.
OZARK UNIT 1H | 16 | 2021-06-29 23:30 | 2021-06-30 00:30 | 1 | P | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.9 | 16230 | 16230 | 0 | PICK UP PUP JOINT AND 1 JOINT OF DP, SCREW INTO TOP OF TOMAX AND RACK BACK WITH TOP MONEL. DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR. MOTOR WAS DRY WHEN IT CAME THROUGH ROTARY, HAD MINIMAL SLACK, AND NO BEARING NOISE. BIT DID NOT HAVE ANY RUBBER INSIDE, BIT GRADED 0-1-WT-S
OZARK UNIT 1H | 16 | 2021-06-30 00:30 | 2021-06-30 02:00 | 1.5 | P | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 10.96 | 16230 | 16230 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13594950 JETS 6/18S TFA: 1.49), 5 1/2", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 3.96' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX, X/O XT-39 P x CET43 B, 2 STANDS, REAMER. BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD) AND MAKE UP BIT.
OZARK UNIT 1H | 16 | 2021-06-30 02:00 | 2021-06-30 06:00 | 4 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.13 | 16230 | 16230 | 0 | TRIP IN HOLE F/BHA T/5929'. PICK UP AGITATOR ON STAND 26. PSI BEFORE-750 / PSI AFTER- 860 AT 127 GPM. HOLE DISPLACING LESS THAN CALCULATED WHILE TRIPPING IN.
OZARK UNIT 1H | 17 | 2021-06-30 06:00 | 2021-06-30 07:00 | 1 | P | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 11.17 | 16230 | 16230 | 0 | P/U AGITAOR; REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
OZARK UNIT 1H | 17 | 2021-06-30 07:00 | 2021-06-30 08:00 | 1 | P | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 11.21 | 16230 | 16230 | 0 | SLIP AND CUT 50' DRILL LINE. CALIBRATE DRAWWORKS.
OZARK UNIT 1H | 17 | 2021-06-30 08:00 | 2021-06-30 09:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 11.25 | 16230 | 16230 | 0 | RIG SERVICE, GREASE TOP DRIVE, TRAVELING BLOCK AND ST-80
OZARK UNIT 1H | 17 | 2021-06-30 09:00 | 2021-06-30 10:45 | 1.75 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.32 | 16230 | 16230 | 0 | TRIP IN HOLE F/5929' T/9827'; HOLE GIVING PROPER DISPLACEMENT
OZARK UNIT 1H | 17 | 2021-06-30 10:45 | 2021-06-30 12:45 | 2 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 11.41 | 16230 | 16230 | 0 | STAGE PUMPS UP AND CIRCULATE BOTTOMS UP(MAX MW 15.5 PPG, RECOVERED 55 BBLS OF 15.5 PPG OBM.) LOST APPROX. 10 BBLS. GPM-130 SPP-1500
OZARK UNIT 1H | 17 | 2021-06-30 12:45 | 2021-06-30 14:00 | 1.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.46 | 16230 | 16230 | 0 | STRIP IN THE HOLE F/9827' T/12400' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 400; FINAL CSG PSI 100
OZARK UNIT 1H | 17 | 2021-06-30 14:00 | 2021-06-30 16:15 | 2.25 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 11.55 | 16230 | 16230 | 0 | STAGE PUMPS UP AND CIRCULATE BOTTOMS UP (MAX MW 16.2 PPG, RECOVERED 65 BBLS OF 16.2 PPG OBM. LOST APPROX. 40 BBLS.) GPM-183 SPP-2800; INITIAL CSG PSI-150, FINAL CSG PSI-1300
OZARK UNIT 1H | 17 | 2021-06-30 16:15 | 2021-06-30 18:30 | 2.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.65 | 16230 | 16230 | 0 | STRIP IN THE HOLE F/12400' T/16,161' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 1300; FINAL CSG PSI 800
OZARK UNIT 1H | 17 | 2021-06-30 18:30 | 2021-06-30 19:00 | 0.5 | P | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 11.67 | 16230 | 16230 | 0 | WASHED & REAMED F/16,161' - T/16,230' WOB-0/10K, RPM-50, TRQ-10/12K, SPM-50/50, GPM-262, MRPM-178, TRPM-228, SPP-5500/6000 PSI, CP-0 PSI, FLARE-5/10', CHOKE POSITION-1 CLOSED & 2 @ 82%
OZARK UNIT 1H | 17 | 2021-06-30 19:00 | 2021-07-01 03:00 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12 | 16230 | 17474 | 155.5 | ROT(1,244' IN 9.08 HRS @ 136.95 FPH) WOB-20/30K, SPM-70/70, GPM-360, RPM 80, TQ 8-14K, MRPM-245, SPP-5400/6400 PSI, DIFF-700/1000 PSI, CHOKES- 100% / 0%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 600 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 840 PSI, MUD WT 11.8 PPG
OZARK UNIT 1H | 17 | 2021-07-01 03:00 | 2021-07-01 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.13 | 17474 | 17514 | 13.3 | SLD(40' IN 1.92 HRS @ 20.87 FPH) WOB-15/25K, SPM-70/70, GPM-360, MRPM-245, SPP-5400/5900 PSI, DIFF-300/500 PSI, CHOKES- 100% / 0%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 600 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 840 PSI, MUD WT 11.8 PPG SLIDE DEPTHS: SLD F/16274' T/16284' 10' TF-180 1940-2000 SLD F/16739' T/16747' 8' TF-45L 2305-2330 SLD F/17025' T/17037' 12' TF-140L 0125-0200 SLD F/17210' T/17220' 10' TF-160L 0310-0345
OZARK UNIT 1H | 18 | 2021-07-01 06:00 | 2021-07-01 12:45 | 6.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.41 | 17514 | 18323 | 119.9 | ROT(809' IN 6.62 HRS @ 122.27 FPH) WOB-20/30K, SPM-70/70, GPM-360, RPM 80, TQ 8-14K, MRPM-245, SPP-5400/6400 PSI, DIFF-700/1000 PSI, CHOKES- 100% / 0%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 600 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 840 PSI, MUD WT 11.8 PPG NOTE: MOTOR STALLED @ 18,360', PICKED UP OFF BOTTOM TO RE-SYNC AND RE-ZERO OBP. IT WAS THEN NOTICED THAT THERE WAS AN EXTRA 1000 PSI OF STANDPIPE PRESSRE INDICATING MOTOR MAY HAVE BEEN CHUNKING. UPON CIRCULATING RUBBER WAS SEEN COMING ACROSS SHAKERS
OZARK UNIT 1H | 18 | 2021-07-01 12:45 | 2021-07-01 14:45 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.49 | 18323 | 18363 | 20 | SLD(40' IN 1.88 HRS @ 21.24 FPH) WOB-15/25K, SPM-70/70, GPM-360, MRPM-245, SPP-5400/5900 PSI, DIFF-300/500 PSI, CHOKES- 100% / 0%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 600 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 840 PSI, MUD WT 11.8 PPG SLIDE DEPTHS: SLD F/18059' T/18073' 14' TF-110L 1003-1049 SLD F/18246' T/18255' 9' TF-180 1223-1302 SLD F/18343' T/18360' 17' TF-110L 1352-1420
OZARK UNIT 1H | 18 | 2021-07-01 14:45 | 2021-07-01 17:00 | 2.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.58 | 18363 | 18363 | 0 | PUMPED 3-40 BBLS SWEEPS SURFACE TO SURFACE TO PREP HOLE FOR TRIP DUE TO MUD MOTOR FAILURE.
OZARK UNIT 1H | 18 | 2021-07-01 17:00 | 2021-07-01 17:15 | 0.25 | U | PRDHLLT | SFTY | SNDWN | SAFETY STAND DOWN | 12.59 | 18363 | 18363 | 0 | STAND DOWN MEETING WAS HELD BY PATTERSON UTI OPERATIONS MANAGER VI ZOOM MEETING DISCUSSING THE IMPORTANCE OF TRAINING SSE AND ALL OF THE NEW CREW CHANGES THROUGHOUT RIG FLEET
OZARK UNIT 1H | 18 | 2021-07-01 17:15 | 2021-07-02 | 6.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.88 | 18363 | 18363 | 0 | STRIP OUT THE HOLE F/18363’ T/13,364’ WET PUMPING 1.9 BBLS/STD OF 11.8 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 670 PSI AND FINAL CASING PRESSURE= 865 PSI.
OZARK UNIT 1H | 18 | 2021-07-02 | 2021-07-02 01:30 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.94 | 18363 | 18363 | 0 | CIRCULATE BTM'S UP AT BTTM OF CURVE @ 13,364' GPM-360, RPM-30, SPP-5700 PSI; CP-85 PSI, 2' FLARE; MAX GAS-1,250U
OZARK UNIT 1H | 18 | 2021-07-02 01:30 | 2021-07-02 02:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.98 | 18363 | 18363 | 0 | STRIP OUT THE HOLE TO CSG SHOE F/13,364’ T/12,318’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 672 PSI AND FINAL CASING PRESSURE= 730 PSI.
OZARK UNIT 1H | 18 | 2021-07-02 02:30 | 2021-07-02 04:00 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.04 | 18363 | 18363 | 0 | CIRCULATE BTM'S UP 80' OUTSIDE SHOE @ 12,318' GPM-360, RPM-30, SPP-5240 PSI; CP-0 PSI, 2' FLARE; MAX GAS-710U
OZARK UNIT 1H | 18 | 2021-07-02 04:00 | 2021-07-02 05:30 | 1.5 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 13.1 | 18363 | 18363 | 0 | MONITOR CASING PSI, SICP BUILT TO 580 PSI; PUMP 158 BBLS OF 17.0 PPG KILL MUD AND CHASE WITH 101 BBLS OF 11.7 PPG OBM; BOTTOM OF MUD CAP @ 12,293', TOP OF MUD CAP @ 8,858' AFTER PULLING DP OUT OF MUD CAP.
OZARK UNIT 1H | 18 | 2021-07-02 05:30 | 2021-07-02 06:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.13 | 18363 | 18363 | 0 | STRIP OUT THE HOLE F/12,293’ T/8,858’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 100 PSI AND FINAL CASING PRESSURE= 40 PSI.
OZARK UNIT 1H | 19 | 2021-07-02 06:00 | 2021-07-02 07:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.17 | 18363 | 18363 | 0 | CONT STRIP OUT THE HOLE F/10,715’ T/8,347,’ PUMPNG 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 200 PSI AND FINAL CASING PRESSURE= 0 PSI.
OZARK UNIT 1H | 19 | 2021-07-02 07:00 | 2021-07-02 07:30 | 0.5 | U | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 13.19 | 18363 | 18363 | 0 | PERFORM FLOW CHECK THROUGH GAS SEPARATOR AND THEN DOWN FLOWLINE - NO FLOW.
OZARK UNIT 1H | 19 | 2021-07-02 07:30 | 2021-07-02 08:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.23 | 18363 | 18363 | 0 | TOOH F/8,347' T/6,362. HOLE TOOK PROPER FILL ON TRIP OUT.
OZARK UNIT 1H | 19 | 2021-07-02 08:30 | 2021-07-02 09:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 13.25 | 18363 | 18363 | 0 | FLOW CHECK THEN REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
OZARK UNIT 1H | 19 | 2021-07-02 09:00 | 2021-07-02 12:45 | 3.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.41 | 18363 | 18363 | 0 | TOOH F/6,362' T/DIRECTIONAL BHA. HOLE TOOK PROPER FILL ON TRIP TANK. NOTE: AT 5,644' ELEVATORS STUCK ON TOOL JT, C/O ELEVATORS & L/D 1 JT DP
OZARK UNIT 1H | 19 | 2021-07-02 12:45 | 2021-07-02 13:30 | 0.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.44 | 18363 | 18363 | 0 | PICK UP PUP JOINT AND 1 JOINT OF DP, SCREW INTO TOP OF TOMAX AND RACK BACK WITH TOP MONEL. DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR. NOTE: MOTOR WAS DRY DURING ATTEMPT TO DRAIN, MOTOR MADE A LOUD POP NOISE WHILE ATTEMPTING TO DRAIN, AND RUBBER WAS FOUND IN BIT JET
OZARK UNIT 1H | 19 | 2021-07-02 13:30 | 2021-07-02 14:30 | 1 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 13.48 | 18363 | 18363 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13509567 JETS 6/18S TFA: 1.49), 5 1/2", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.0' BIT TO BEND; 5.44" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX, X/O XT-39 P x CET43 B, 2 STANDS, REAMER. BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD) AND MAKE UP BIT.
OZARK UNIT 1H | 19 | 2021-07-02 14:30 | 2021-07-02 16:30 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.56 | 18363 | 18363 | 0 | TRIP IN HOLE F/BHA T/4988'. PICK UP AGITATOR ON STAND 26. PSI BEFORE-1230 / PSI AFTER- 1580 AT 275 GPM. HOLE GIVING PROPER DISPLACEMENT.
OZARK UNIT 1H | 19 | 2021-07-02 16:30 | 2021-07-02 17:30 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.6 | 18363 | 18363 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS
OZARK UNIT 1H | 19 | 2021-07-02 17:30 | 2021-07-02 18:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.65 | 18363 | 18363 | 0 | TRIP IN HOLE F/4988' T/6400'. PICK UP AGITATOR @ 5930'. PSI BEFORE-1700 / PSI AFTER- 1940 AT 265 GPM. HOLE GIVING PROPER DISPLACEMENT.
OZARK UNIT 1H | 19 | 2021-07-02 18:30 | 2021-07-02 19:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 13.67 | 18363 | 18363 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
OZARK UNIT 1H | 19 | 2021-07-02 19:00 | 2021-07-02 20:15 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.72 | 18363 | 18363 | 0 | TRIP IN HOLE F/6400' T/8200'; HOLE GIVING PROPER DISPLACEMENT.
OZARK UNIT 1H | 19 | 2021-07-02 20:15 | 2021-07-02 21:15 | 1 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 13.76 | 18363 | 18363 | 0 | SLIP AND CUT 80' DRILL LINE. CALIBRATE DRAWWORKS.
OZARK UNIT 1H | 19 | 2021-07-02 21:15 | 2021-07-02 22:30 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.81 | 18363 | 18363 | 0 | TRIP IN HOLE F/8200' T/10600'; HOLE GIVING PROPER DISPLACEMENT
OZARK UNIT 1H | 19 | 2021-07-02 22:30 | 2021-07-02 23:45 | 1.25 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 13.86 | 18363 | 18363 | 0 | STAGE PUMPS UP AND CIRCULATE BOTTOMS UP (MAX MW 13.0 PPG, RECOVERED 25 BBLS) GPM-175 SPP-1700
OZARK UNIT 1H | 19 | 2021-07-02 23:45 | 2021-07-03 00:45 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.91 | 18363 | 18363 | 0 | STRIP IN THE HOLE F/10600' T/12470' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 114; FINAL CSG PSI 0
OZARK UNIT 1H | 19 | 2021-07-03 00:45 | 2021-07-03 02:30 | 1.75 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 13.98 | 18363 | 18363 | 0 | STAGE PUMPS UP AND CIRCULATE BOTTOMS UP (MAX MW 16.0 PPG, RECOVERED 100 BBLS OF 16.0 PPG OBM. GPM-260 SPP-2800; INITIAL CSG PSI-0, FINAL CSG PSI-0
OZARK UNIT 1H | 19 | 2021-07-03 02:30 | 2021-07-03 06:00 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.13 | 18363 | 18363 | 0 | STRIP IN THE HOLE F/12470' T/17691' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 460; FINAL CSG PSI 360 NOTE: W/R F/13399' T/13703' & F/15989' T/16367' GPM-300, SPP-4200, RPM-50, TQ-5-7K
OZARK UNIT 1H | 20 | 2021-07-03 06:00 | 2021-07-03 06:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.15 | 18363 | 18363 | 0 | STRIP IN THE HOLE F/17691' T/18363 BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 350; FINAL CSG PSI 200 NOTE: W/R LAST STD F/18333' T/18363' GPM-360, SPP-5600, RPM-60, TQ-7-8K
OZARK UNIT 1H | 20 | 2021-07-03 06:30 | 2021-07-03 12:15 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.39 | 18363 | 18949 | 101.9 | ROT(586' IN 5.73 HRS @ 102 FPH) WOB-15/25K, SPM-67/67, GPM-350, RPM 80, TQ 8-14K, MRPM-238, SPP-5400/6100 PSI, DIFF-600/700 PSI, CHOKES- 100% / 100%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 420 PSI, AVG CASING PRESSURE= 350 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 920 PSI, MUD WT 11.7 PPG NOTE: PUMPING 10 BBLS OF 13 PPB LCM SWEEP EVERY 300' OR AS NEEDED FOR LOSSES; SWEEP= 90 BBLS ACTIVE MUD + 5 PPB NEWCARB, 5 PPB NEWPHALT, 3 PPB MAGNAFIBER
OZARK UNIT 1H | 20 | 2021-07-03 12:15 | 2021-07-03 13:15 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.43 | 18949 | 18971 | 22 | SLD(22' IN 1.02 HRS @ 22 FPH) WOB-15/25K, SPM-65/68, GPM-350, MRPM-238, SPP-5400/5900 PSI, DIFF-300/500 PSI, CHOKES- 100% /100% SLIDE DEPTHS: SLD F/18722' T/18734' 12' TF-70L 0935-1010 SLD F/18815' T/18825' 10' TF-HS 1100-1126
OZARK UNIT 1H | 20 | 2021-07-03 13:15 | 2021-07-03 15:00 | 1.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.5 | 18971 | 18971 | 0 | PUMPED 40 BBL SWEEP SURFACE TO SURFACE TO PREP HOLE FOR TRIP DUE TO MUD MOTOR FAILURE.
OZARK UNIT 1H | 20 | 2021-07-03 15:00 | 2021-07-03 19:30 | 4.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.69 | 18971 | 18971 | 0 | STRIP OUT OF THE HOLE F/18,971’ T/12,300’; PULLING ON ELEVATORS WET PUMPING 1.9 BBLS/STD OF 11.8 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 900 PSI AND FINAL CASING PRESSURE= 250 PSI.
OZARK UNIT 1H | 20 | 2021-07-03 19:30 | 2021-07-03 20:15 | 0.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.72 | 18971 | 18971 | 0 | CIRCULATE BTM'S UP 62' OUTSIDE SHOE @ 12,300' GPM-310, RPM-0, SPP-3250 PSI; CP-0 PSI, NO FLARE; MAX GAS-304U
OZARK UNIT 1H | 20 | 2021-07-03 20:15 | 2021-07-03 22:00 | 1.75 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 14.79 | 18971 | 18971 | 0 | MONITOR CASING PSI, SICP BUILT TO 502 PSI; PUMP 143.4 BBLS OF 17.0 PPG KILL MUD AND CHASE WITH 105.8 BBLS OF 11.7 PPG OBM; BOTTOM OF MUD CAP @ 12,300', TOP OF MUD CAP @ 9,177' AFTER PULLING DP OUT OF MUD CAP.
OZARK UNIT 1H | 20 | 2021-07-03 22:00 | 2021-07-03 23:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.85 | 18971 | 18971 | 0 | STRIP OUT THE HOLE F/12,300’ T/9,298’ PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD, CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI. FLOW CHECK, WELL STATIC.
OZARK UNIT 1H | 20 | 2021-07-03 23:30 | 2021-07-04 01:30 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 14.94 | 18971 | 18971 | 0 | PIPE BEGAN TO PULL WET, PUMPED AN ADDITIONAL 45 BBLS KILL MUD FOR SLUG. STRIP OUT OF HOLE F/9,298' T/7,598'. HOLE NOT TAKING PROPER FILL ON TRIP TANK. CONT. STRIP OUT OF HOLE F/7,598' T/5,900' PUMPNG 1.9 BBLS/STD OF 17.0 PPG KILL MUD CALCULATED FILL DOWN THE ANNULUS. TOTAL OF 26 BBLS.
OZARK UNIT 1H | 20 | 2021-07-04 01:30 | 2021-07-04 02:00 | 0.5 | U | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 14.96 | 18971 | 18971 | 0 | FLOW CHECK AT AGITATOR, WELL FLOWING APPROXIMATELY 20 BBLS/HR. SHUT WELL IN, NO CSG PSI OBSERVED.
OZARK UNIT 1H | 20 | 2021-07-04 02:00 | 2021-07-04 06:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 15.13 | 18971 | 18971 | 0 | STRIP OUT OF HOLE F/5,900' T/4,545' PUMPNG 2.9 BBLS/STD OF 17.0 PPG KILL MUD DOWN THE ANNULUS TOTAL OF 40 BBLS. FLOW CHECK, WELL STATIC. TOOH ON TRIP TANK F/4,545' T/2,500', PROPER FILL ON TRIP TANK. NOTE: AN ADDITIONAL 66 BBLS OF KILL MUD WAS USED TO FILL BACKSIDE ON THIS TRIP. TOTAL WITH MUD CAP = 210 BBLS
OZARK UNIT 1H | 21 | 2021-07-04 06:00 | 2021-07-04 07:45 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 15.2 | 18971 | 18971 | 0 | CONT. TOOH ON TRIP TANK F/2,500' T/BHA', PROPER FILL ON TRIP TANK, USING MUD BUCKET
OZARK UNIT 1H | 21 | 2021-07-04 07:45 | 2021-07-04 08:30 | 0.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 15.23 | 18971 | 18971 | 0 | PICK UP PUP JOINT AND 1 JOINT OF DP, SCREW INTO TOP OF TOMAX AND RACK BACK WITH TOP MONEL. DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR. NOTE: MOTOR WAS DRY DURING ATTEMPT TO DRAIN, MOTOR BEARING ASSEMBLY APPEARED SOUND, NORMAL SQUAT, MINIMAL AXIAL PLAY, ONE JET IN BIT PLUGGED WITH STATOR RUBBER.
OZARK UNIT 1H | 21 | 2021-07-04 08:30 | 2021-07-04 09:15 | 0.75 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 15.26 | 18971 | 18971 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13564680 JETS 6/18S TFA: 1.49), 5", 5/6, 9.5 STG @ 1.80°, DIAMOND BEARING, 5-3/8" STAB; .75 REV/GAL; 4.32' BIT TO BEND; 5" PAD OD; FLOW RANGE- 106/360 GPM; MAX DIFF-2610 PSI; STALL TRQ-5050 FT/LBS; X/O, BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX, X/O XT-39 P x CET43 B, 2 STANDS, REAMER. BIT TO SVY-69'. BIT TO GAMMA-56'. TEST MWD (TEST GOOD) AND MAKE UP BIT.
OZARK UNIT 1H | 21 | 2021-07-04 09:15 | 2021-07-04 13:30 | 4.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 15.44 | 18971 | 18971 | 0 | TRIP IN HOLE F/BHA T/7,750'. PICK UP AGITATOR ON STAND 26. PSI BEFORE-1540 / PSI AFTER- 2080 AT 110 GPM. PICK UP 2ND AGITATOR @ 5931'. PSI BEFORE-2280 / PSI AFTER- 2410 AT 110 GPM. REMOVE TRIP NIPPLE/INSTALL ROT HEAD @ 6,000'. HOLE GIVING PROPER DISPLACEMENT.
OZARK UNIT 1H | 21 | 2021-07-04 13:30 | 2021-07-04 15:15 | 1.75 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 15.51 | 18971 | 18971 | 0 | CIRCULATE BTM'S UP; GPM-104, SPP-700, MAX GAS 120u; CATCH REMAINDER OF KILL MUD IN TRIP TANK; RECAPTURED TOTAL OF 85 BBL OF KILL MUD
OZARK UNIT 1H | 21 | 2021-07-04 15:15 | 2021-07-04 15:45 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.53 | 18971 | 18971 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS
OZARK UNIT 1H | 21 | 2021-07-04 15:45 | 2021-07-04 17:00 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 15.58 | 18971 | 18971 | 0 | TRIP IN HOLE F/7,750' T/10,677' TAKING DISPLACEMENT DOWN FLOWLINE INTO TRIP TANK; HOLE GIVING PROPER DISPLACEMENT
OZARK UNIT 1H | 21 | 2021-07-04 17:00 | 2021-07-04 19:00 | 2 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 15.67 | 18971 | 18971 | 0 | STAGE PUMPS UP AND CIRCULATE BOTTOMS UP (MAX MW 13.0 PPG, RECOVERED 110 BBLS OF 13.0 PPG OBM. GPM-105 SPP-840; INITIAL CSG PSI-0, FINAL CSG PSI-0
OZARK UNIT 1H | 21 | 2021-07-04 19:00 | 2021-07-04 20:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 15.71 | 18971 | 18971 | 0 | STRIP IN THE HOLE F/10677' T/12614' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 122; FINAL CSG PSI 145
OZARK UNIT 1H | 21 | 2021-07-04 20:00 | 2021-07-04 21:30 | 1.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 15.77 | 18971 | 18971 | 0 | STAGE PUMPS UP AND CIRCULATE BOTTOMS UP (MAX MW 14.3 PPG, RECOVERED 90 BBLS OF 14.3 PPG OBM. LOST APPROX. 35 BBLS.) GPM-205 SPP-2000; INITIAL CSG PSI-0, FINAL CSG PSI-0
OZARK UNIT 1H | 21 | 2021-07-04 21:30 | 2021-07-05 00:30 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 15.9 | 18971 | 18971 | 0 | STRIP IN THE HOLE F/12614' T/16,161' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 263; FINAL CSG PSI 80
OZARK UNIT 1H | 21 | 2021-07-05 00:30 | 2021-07-05 01:15 | 0.75 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 15.93 | 18971 | 18971 | 0 | WASHED & REAMED F/16,161' - T/18,971' WOB-0/5K, RPM-50, TRQ-7/8K, SPM-60/60, GPM-300, MRPM-225, TRPM-275, SPP-4000 PSI, CP-0 PSI, FLARE-2/5', CHOKE POSITION-1 CLOSED & 2 @ 75%
OZARK UNIT 1H | 21 | 2021-07-05 01:15 | 2021-07-05 05:00 | 3.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.08 | 18971 | 19198 | 60.5 | ROT(227' IN 3.75 HRS @ 60.53 FPH) WOB-15/20K, SPM-56/56, GPM-300, RPM 70, TQ 8-12K, MRPM-225, SPP-4000/4500 PSI, DIFF-400/500 PSI, CHOKES- 0% / 75%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 280 PSI, AVG CASING PRESSURE= 100 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 670 PSI, MUD WT 11.8 PPG NOTE: PUMPING 10 BBLS OF 13 PPB LCM SWEEP EVERY 300' OR AS NEEDED FOR LOSSES; SWEEP= 90 BBLS ACTIVE MUD + 5 PPB NEWCARB, 5 PPB NEWPHALT, 3 PPB MAGNAFIBER
OZARK UNIT 1H | 21 | 2021-07-05 05:00 | 2021-07-05 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.13 | 19198 | 19213 | 15 | SLD (15' IN 1 HR @ 15 FPH) WOB-15/25K, SPM-68/68, GPM-350, MRPM-262, SPP-4000/4500 PSI, DIFF-300/500 PSI, CHOKES- 0% /100% SLIDE DEPTH: SLD F/19,102' T/19,117' 15' TF-160L 0330-0430
OZARK UNIT 1H | 22 | 2021-07-05 06:00 | 2021-07-05 08:45 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.24 | 19213 | 19449 | 85.8 | ROT(236' IN 2.68 HRS @ 87.95 FPH) WOB-15/20K, SPM-64/64, GPM-332, RPM 70, TQ 8-12K, MRPM-249, SPP-4600/5500 PSI, DIFF-600/800 PSI, CHOKES- 0% / 80%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 660 PSI, MUD WT 11.7 PPG NOTE: PUMPING 10 BBLS OF 13 PPB LCM SWEEP EVERY 300' OR AS NEEDED FOR LOSSES; SWEEP= 90 BBLS ACTIVE MUD + 5 PPB NEWCARB, 5 PPB NEWPHALT, 3 PPB MAGNAFIBER
OZARK UNIT 1H | 22 | 2021-07-05 08:45 | 2021-07-05 09:15 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.26 | 19449 | 19464 | 30 | SLD (15' IN .57 HR @ 26.47 FPH) WOB-15/25K, SPM-64/64, GPM-332, MRPM-249, SPP-4600/5100 PSI, DIFF-300/500 PSI, CHOKES- 0% /80% SLIDE DEPTH: SLD F/19,287' T/19,302' 15' TF-180 0700-0734
OZARK UNIT 1H | 22 | 2021-07-05 09:15 | 2021-07-05 10:00 | 0.75 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.29 | 19464 | 19464 | 0 | CIRCULATE AND RECIPROCATE AT A REDUCED RATE TO COOL MWD. START TEMP 349° END TEMP 342°. GPM=200, SPP=2300, RPM=2, TQ=7K
OZARK UNIT 1H | 22 | 2021-07-05 10:00 | 2021-07-05 13:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.42 | 19464 | 19776 | 104 | ROT(312' IN 3 HRS @ 104 FPH) WOB-15/20K, SPM-64/64, GPM-332, RPM 70, TQ 8-12K, MRPM-249, SPP-4600/5500 PSI, DIFF-600/800 PSI, CHOKES- 0% / 80%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 660 PSI, MUD WT 11.7 PPG NOTE: PUMPING 10 BBLS OF 13 PPB LCM SWEEP EVERY 300' OR AS NEEDED FOR LOSSES; SWEEP= 90 BBLS ACTIVE MUD + 5 PPB NEWCARB, 5 PPB NEWPHALT, 3 PPB MAGNAFIBER
OZARK UNIT 1H | 22 | 2021-07-05 13:00 | 2021-07-05 13:30 | 0.5 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.44 | 19776 | 19776 | 0 | CIRCULATE AND RECIPROCATE AT A REDUCED RATE TO COOL MWD. START TEMP 349° END TEMP 342°. GPM=200, SPP=2300, RPM=2, TQ=7K
OZARK UNIT 1H | 22 | 2021-07-05 13:30 | 2021-07-05 19:00 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.67 | 19776 | 20437 | 120.2 | ROT(661' IN 5.33 HRS @ 124 FPH) WOB-15/20K, SPM-64/64, GPM-332, RPM 70, TQ 8-12K, MRPM-249, SPP-4600/5500 PSI, DIFF-600/800 PSI, CHOKES- 0% / 80%, FLARE-2'-12', NO MUD CUT, MAX CASING PRESSURE= 152 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 862 PSI, MUD WT 11.7 PPG NOTE: PUMPING 10 BBLS OF 13 PPB LCM SWEEP EVERY 300' OR AS NEEDED FOR LOSSES; SWEEP= 90 BBLS ACTIVE MUD + 5 PPB NEWCARB, 5 PPB NEWPHALT, 3 PPB MAGNAFIBER
OZARK UNIT 1H | 22 | 2021-07-05 19:00 | 2021-07-05 19:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 16.69 | 20437 | 20437 | 0 | RIG SERVICE, GREASE DRAWWORKS, TOP DRIVE & TRAVELING BLOCK
OZARK UNIT 1H | 22 | 2021-07-05 19:00 | 2021-07-05 19:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 16.67 | 20437 | 20437 |  | MILESTONE_TD WELL ON 7/5/2021 @ 19:00
OZARK UNIT 1H | 22 | 2021-07-05 19:30 | 2021-07-05 22:00 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.79 | 20437 | 20437 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN, PUMPING 2 TANDEM 30 BBL HIGH VIS SWEEPS. CIRCULATE 3 B/U, RPM-70, SPM: 65/65/0, GPM-330, INITIAL SPP-5000 PSI/FINAL SPP-4900, CHOKES- 0% / 30-50%, FLARE-0'-6', MAX CASING PRESSURE=837 PSI, MAX GAS: 1747u. 1ST BTM UP START TQ=7-10K, END= 7-10K, P/U WT=240K, S/O=210K 2ND BTM UP END TQ=7-10K, P/U WT=240, S/O WT=215K 3RD BTM UP END TQ=7-8K, P/U WT=240K, S/O WT=230K
OZARK UNIT 1H | 22 | 2021-07-05 22:00 | 2021-07-06 03:45 | 5.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 17.03 | 20437 | 20437 | 0 | STRIP OUT THE HOLE F/20,437’ T/12,567’ WET PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 932 PSI AND FINAL CASING PRESSURE= 736 PSI.
OZARK UNIT 1H | 22 | 2021-07-06 03:45 | 2021-07-06 04:30 | 0.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.06 | 20437 | 20437 | 0 | CIRCULATE BTM'S UP 329' OUTSIDE SHOE @ 12,567' GPM-310, RPM-10, SPP-3800 PSI; CP-96 PSI, NO FLARE; MAX GAS-400U
OZARK UNIT 1H | 22 | 2021-07-06 04:30 | 2021-07-06 06:00 | 1.5 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 17.13 | 20437 | 20437 | 0 | MONITOR CASING PSI, SICP BUILT TO 580 PSI; PUMP 186.4 BBLS OF 17.0 PPG KILL MUD AND CHASE WITH 95 BBLS OF 11.7 PPG OBM; BOTTOM OF MUD CAP @ 12,567', TOP OF MUD CAP @ 8,507' AFTER PULLING DP OUT OF MUD CAP.
OZARK UNIT 1H | 23 | 2021-07-06 06:00 | 2021-07-06 07:30 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 17.19 | 20437 | 20437 | 0 | STRIP OUT THE HOLE F/12,567’ T/8,400’ PUMPING 1.9 BBLS/STD OF 11.7 PPG MUD, CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PRESSURE= 45 PSI AND FINAL CASING PRESSURE= 0 PSI.
OZARK UNIT 1H | 23 | 2021-07-06 07:30 | 2021-07-06 08:00 | 0.5 | P | PRDHLCSG | FLWBK | FLCHK | FLOW CHECK | 17.21 | 20437 | 20437 | 0 | PERFORM FLOW CHECK THROUGH GAS SEPARATOR AND THEN DOWN FLOWLINE - NO FLOW.
OZARK UNIT 1H | 23 | 2021-07-06 08:00 | 2021-07-06 09:45 | 1.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 17.28 | 20437 | 20437 | 0 | L/D DRILL PIPE F/8,400' T/6,490'. PROPER FILL WITH 11.7 PPG ACTIVE MUD ON TRIP TANK
OZARK UNIT 1H | 23 | 2021-07-06 09:45 | 2021-07-06 10:15 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 17.3 | 20437 | 20437 | 0 | FLOW CHECK WHILE PULL ROTATING HEAD AND INSTALL TRIP NIPPLE.
OZARK UNIT 1H | 23 | 2021-07-06 10:15 | 2021-07-06 12:30 | 2.25 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 17.4 | 20437 | 20437 | 0 | CONT. L/D DRILL PIPE F/6,490' T/4,104'. HOLE TAKING PROPER FILL WITH 11.7 PPG ACTIVE MUD ON TRIP TANK
OZARK UNIT 1H | 23 | 2021-07-06 12:30 | 2021-07-06 13:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 17.42 | 20437 | 20437 | 0 | CHANGE UPPER DIES ON ST-80
OZARK UNIT 1H | 23 | 2021-07-06 13:00 | 2021-07-06 16:15 | 3.25 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 17.55 | 20437 | 20437 | 0 | CONT. L/D DRILL PIPE F/4,104' T/BHA. HOLE TAKING PROPER FILL WITH 11.7 PPG ACTIVE MUD ON TRIP TANK
OZARK UNIT 1H | 23 | 2021-07-06 16:15 | 2021-07-06 19:00 | 2.75 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 17.67 | 20437 | 20437 | 0 | DRAIN MOTOR AND BREAK BIT; LAY DOWN REAMER, TOMAX, BTI, AND DIRECTIONAL BHA; MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG
OZARK UNIT 1H | 23 | 2021-07-06 19:00 | 2021-07-06 20:00 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 17.71 | 20437 | 20437 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4 1/2" ELAVATORS
OZARK UNIT 1H | 23 | 2021-07-06 20:00 | 2021-07-06 20:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 17.73 | 20437 | 20437 | 0 | RIG SERVICE, GREASE DRAWWORKS AND CATWALK, CHECK FLUIDS IN SAME
OZARK UNIT 1H | 23 | 2021-07-06 20:30 | 2021-07-06 21:45 | 1.25 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 17.78 | 20437 | 20437 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT.
OZARK UNIT 1H | 23 | 2021-07-06 21:45 | 2021-07-07 02:00 | 4.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.96 | 20437 | 20437 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/3,000', FILLING PIPE ON THE FLY, PROPER DISPLACEMENT TO TRIP TANK
OZARK UNIT 1H | 23 | 2021-07-07 02:00 | 2021-07-07 02:15 | 0.25 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 17.97 | 20437 | 20437 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD
OZARK UNIT 1H | 23 | 2021-07-07 02:15 | 2021-07-07 02:45 | 0.5 | U | PRDHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 17.99 | 20437 | 20437 | 0 | TORQUE TURN UNABLE TO RECORD RPM, CHANGE OUT CABLE
OZARK UNIT 1H | 23 | 2021-07-07 02:45 | 2021-07-07 06:00 | 3.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.13 | 20437 | 20437 | 0 | CONT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/3,000' T/6,600' FILLING PIPE ON THE FLY, PROPER DISPLACEMENT TO TRIP TANK. CSG DETAILS ON NEXT REPORT
OZARK UNIT 1H | 24 | 2021-07-07 06:00 | 2021-07-07 07:45 | 1.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.2 | 20437 | 20437 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/6,600' T/8,706', FILLING PIPE ON THE FLY, PROPER DISPLACEMENT TO TRIP TANK.
OZARK UNIT 1H | 24 | 2021-07-07 07:45 | 2021-07-07 08:30 | 0.75 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 18.23 | 20437 | 20437 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS.
OZARK UNIT 1H | 24 | 2021-07-07 08:30 | 2021-07-07 09:45 | 1.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.28 | 20437 | 20437 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/8,706' T/10,452', FILLING PIPE ON THE FLY, PROPER DISPLACEMENT TO TRIP TANK.
OZARK UNIT 1H | 24 | 2021-07-07 09:45 | 2021-07-07 11:15 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.34 | 20437 | 20437 | 0 | CIRCULATE OUT MUD CAP @ 10,452', SLOWLY STAGE PUMPS UP: 80 SPM, 210 GPM, , SPP: 520 PSI, MAX GAS: 318u. FINAL SICP= 192 PSI. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 12.5 PPG WAS @ SURFACE, DIVERTED 75 BBLS OF 12.5 PPG T/12.8 PPG.
OZARK UNIT 1H | 24 | 2021-07-07 11:15 | 2021-07-07 12:15 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.39 | 20437 | 20437 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/10,452' T/11,673' WHILE STRIPPING IN WITH CASING PRESSURE= 190-291 PSI WITH CHOKES: 35% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), FILLING PIPE ON THE FLY.
OZARK UNIT 1H | 24 | 2021-07-07 12:15 | 2021-07-07 12:45 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 18.41 | 20437 | 20437 | 0 | CHANGE OUT SIDE DOOR ELEVATORS TO HYC ELEVATORS.
OZARK UNIT 1H | 24 | 2021-07-07 12:45 | 2021-07-07 13:45 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.45 | 20437 | 20437 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/11,673' T/12,608' WHILE STRIPPING IN WITH CASING PRESSURE= 50-100 PSI WITH CHOKES: 50% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), CASING PRESSURE DECREASED T/ 0 PSI @ 11,720’, DISPLACEMENT REDUCED F/1.3 BBLS/JT T/ .5 BBLS/JT, FILLING PIPE ON THE FLY.
OZARK UNIT 1H | 24 | 2021-07-07 13:45 | 2021-07-07 16:30 | 2.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.56 | 20437 | 20437 | 0 | CIRCULATE OUT MUD CAP @ 12,608' DOWN THE FLOW LINE WITH 80% RETURNS WHILE RECIPROCATING PIPE, SLOWLY STAGE PUMPS UP: 50 SPM, 130 GPM, 30 RPM, 2K/4K TRQ, SPP:1130 PSI, DIVERT RETURN THROUGH THE CHOKE ONCE FLOW STARTED INCREASING, STARTING CSG PSI= 0 PSI, ENDING CSG PSI= 365 PSI WITH CHOKES: 30% / 0%, NO FLARE AND MAX GAS: 204u. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 12.6 PPG WAS @ SURFACE, DIVERTED 162 BBLS OF 12.6 PPG T/15.6 PPG. LOSS 54 BBLS TO THE FORMATION.
OZARK UNIT 1H | 24 | 2021-07-07 16:30 | 2021-07-07 18:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.63 | 20437 | 20437 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/12,608' T/13,392' WHILE STRIPPING IN WITH CASING PRESSURE= 600-746 PSI WITH CHOKES: 30% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), CASING PRESSURE DECREASED T/ 0 PSI @ 13,360', DISPLACEMENT REDUCED F/1.3 BBLS/JT T/ .65 BBLS/JT, FILLING PIPE ON THE FLY. NOTE: WASH/REAM F/13,392' T/13,577'
OZARK UNIT 1H | 24 | 2021-07-07 18:00 | 2021-07-07 20:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 18.71 | 20437 | 20437 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/13,577' T/14,524' WHILE STRIPPING IN WITH CASING PRESSURE= 450-176 PSI WITH CHOKES: 30% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), CASING PRESSURE DECREASED T/ 176 PSI @ 13,867', DISPLACEMENT REDUCED F/1.3 BBLS/JT T/ .72 BBLS/JT, FILLING PIPE ON THE FLY. NOTE: WASH/REAM F/13,914' T/14,100' & F/14,288' T/14,524'.
OZARK UNIT 1H | 24 | 2021-07-07 20:00 | 2021-07-07 23:00 | 3 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 18.83 | 20437 | 20437 | 0 | CIRCULATE OUT MUD CAP @ 14,524' THROUGH THE CHOKE WHILE RECIPROCATING PIPE, SLOWLY STAGE PUMPS UP: 30 SPM, 82 GPM, SPP:1185 PSI. STARTING CSG PSI= 176 PSI, ENDING CSG PSI=828 PSI WITH CHOKES: 30% / 0%, 5' FLARE AND MAX GAS: 1496u. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 12.5 PPG WAS @ SURFACE, DIVERTED 150 BBLS OF 12.6 PPG T/14.2 PPG. LOSS 43 BBLS TO THE FORMATION.
OZARK UNIT 1H | 24 | 2021-07-07 23:00 | 2021-07-08 04:15 | 5.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 19.05 | 20437 | 20437 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/14,524' T/14,524' WHILE STRIPPING IN WITH CASING PRESSURE= 930-230 PSI WITH CHOKES: 30% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), FILLING PIPE ON THE FLY.
OZARK UNIT 1H | 24 | 2021-07-08 04:15 | 2021-07-08 05:15 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 19.09 | 20437 | 20437 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND RUN LANDING JOINT F/20,380' T/20,422'. GPM-80, LAND CASING ON HANGER W/180K LBS (W/O BLOCKS) @ 20,422'. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, RAN 8,674' (186 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1- X-OVER, 1 JOINT 5-1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, RAN 11,645.53' (249 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING. FOR TOTAL OF 435 FULL JTS OF 5'' 18# P-110 ICY WEDGE 425 & 5.5" 23# P-110 ICY WEDGE 463. CASING SHOE @ 20,422' TOP OF FLOAT COLLAR @ 20,370.2' BOTTOM OF TOE SLEEVE VALVE @ 20,324.5' TOP OF TOE SLEEVE VALVE @ 20,299.5' TOP OF X-OVER @ 11,715.4' TOP OF MARKER JOINT ABOVE X-OVER @ 11,650.2' 5 JOINTS 5" LEFT OUT- 234.24' 7 JOINTS 5.5" LEFT OUT- 326.49'
OZARK UNIT 1H | 24 | 2021-07-08 05:15 | 2021-07-08 06:00 | 0.75 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 19.13 | 20437 | 20437 | 0 | RIG DOWN FRANK'S CRT AND INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 340 PSI.
OZARK UNIT 1H | 25 | 2021-07-08 06:00 | 2021-07-08 06:30 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 19.15 | 20437 | 20437 | 0 | INSTALL WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 384 PSI.
OZARK UNIT 1H | 25 | 2021-07-08 06:30 | 2021-07-08 08:30 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 19.23 | 20437 | 20437 | 0 | SLOWLY STAGE UP PUMPS TO 257 GPM, CIRCULATE 1-1/2 CASING CAPACITY WHILE RIGGING DOWN CASING TOOLS, GPM-257, SPP-1,750-1800 PSI, CHOKES: 30-50% / 0%, AVG CASING PRESSURE= 300 PSI, MAX CASING PRESSURE= 570 PSI, 5’-10’ FLARE AND MAX GAS: 963u. MONITOR SICP, SICP= 1070 PSI. LOSS 57 BBLS TO THE FORMATION. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN 12.5 PPG WAS @SURFACE, DIVERTED 125 BBLS OF 12.5 PPG T/14.2 PPG. NOTE: HELD PJSM FOR CEMENT JOB.
OZARK UNIT 1H | 25 | 2021-07-08 08:30 | 2021-07-08 13:00 | 4.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 19.42 | 20437 | 20437 | 0 | SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT TRUCK, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI, CEMENTED 5X5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 5 BPM 80 BBL 11.8 PPG WEIGHTED SPACER, 277 BBL 13.5 PPG TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBL OF SUGAR WATER, FOLLOWED BY 382 BBL OF FRESH WATER @ 5 BPM (TOTAL OF 402 BBL DISPLACEMENT). OBSERVED 100% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 4500 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 5500 PSI. 0 BBLS OF SPACER BACK TO SURFACE. HELD FOR 5 MIN, BLED BACK 8 BBLS. FLOATS HELD. PLUG DOWN @ 12:38 HRS 7/8/2021. INITIAL SICP-1070 PSI, FINAL SICP= 780 PSI. MAX CASING PSI W/ PUMPING CEMENT-1002 PSI @ 2 BPM MAX CASING PSI W/ PUMPING DISPLACEMENT- 954 PSI MAX GAS-695u CALCULATED TOP OF CEMENT- 8,570'
OZARK UNIT 1H | 25 | 2021-07-08 13:00 | 2021-07-08 13:30 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 19.44 | 20437 | 20437 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP=780 PSI, FINAL SICP= 840 PSI. NOTE: LEFT FOSV OPEN WHILE MONITORING SICP.
OZARK UNIT 1H | 25 | 2021-07-08 13:30 | 2021-07-09 05:00 | 15.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 20.08 | 20437 | 20437 | 0 | MONITOR SICP WHILE WAITING ON CEMENT, CLEAN MUD TANKS, L/D 4 1/2" DRILL PIPE (87 STDS DP L/D), INITIAL SICP=840 PSI, FINAL SICP= 1282 PSI. SICP WHILE MONITORING: 13:30 - 840 PSI 14:30 - 988 PSI 15:30 - 1095 PSI 16:30 - 1168 PSI 17:30 - 1218 PSI 18:30 - 1252 PSI 19:30 - 1307 PSI 20:30 - 1292 PSI 21:30 - 1302 PSI 22:30 - 1307 PSI 23:30 - 1309 PSI 00:30 - 1307 PSI 01:30 - 1305 PSI 02:30 - 1300 PSI 03:30 - 1294 PSI 04:30 - 1288 PSI 05:30 - 1284 PSI
OZARK UNIT 1H | 26 | 2021-07-09 06:00 | 2021-07-09 08:30 | 2.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 20.19 | 20437 | 20437 | 0 | L/D 4 1/2" DRILL PIPE WHILE MONITORING SICP AND WAIT ON CEMENT, SICP=1261 PSI.
OZARK UNIT 1H | 26 | 2021-07-09 08:30 | 2021-07-09 12:30 | 4 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 20.35 | 20437 | 20437 | 0 | CLEAN AND ORGANIZE RIG FLOOR, REMOVE ALL 4 ½” DRILL PIPE EQUIPMENT FROM RIG FLOOR, REMOVE TURN BUCKLES WHILE WAITING ON CEMENT AND MONITORING SICP, SICP=1235 PSI
OZARK UNIT 1H | 26 | 2021-07-09 12:30 | 2021-07-09 13:00 | 0.5 | P | PRDHLCSG | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 20.38 | 20437 | 20437 | 0 | BLEED OFF SICP IN 50-150 PSI INCREMENTS TO THE TRIP TANK RECORDING BBL BLED BACK, INITIAL SICP = 1235 PSI, FINAL SICP= 0 PSI, BLED BACK 2.36 BBL. MONITOR SICP, SICP= 0 PSI, MONITOR FLOW THROUGH THE CHOKE TO THE TRIP TANK (WELL STATIC). BLEED OFF SCHEDULE: F/1235 PSI T/1178 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 1181 PSI F/1181 PSI T/1124 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 1134 PSI F/1134 PSI T/1030 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 1034 PSI F/1034 PSI T/933 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 946 PSI F/946 PSI T/784 PSI, .41 BBL BLED IN 1 MIN., SICP STABILIZED @ 792 PSI F/792 PSI T/622 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 629 PSI F/629 PSI T/464 PSI, .18 BBL BLED IN 1 MIN., SICP STABILIZED @ 470 PSI F/470 PSI T/300 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 302 PSI F/302 PSI T/152 PSI, 0 BBL BLED IN 1 MIN., SICP STABILIZED @ 155 PSI F/155 PSI T/0 PSI, 1.77 BBL BLED IN 2 MIN., SICP STABILIZED @ 0 PSI
OZARK UNIT 1H | 26 | 2021-07-09 13:00 | 2021-07-09 16:00 | 3 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 20.5 | 20437 | 20437 | 0 | REMOVE FOSV AND ROTATING HEAD, LAY DOWN LANDING JOINT. RIG DOWN CSG ELEVATORS AND RIG UP RIG ELEVATORS. RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER. PUMP @ 50 GPM W/100 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF. INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. PICK UP 1" TUBING AND INSTALL BPV. LAY DOWN TUBING.
OZARK UNIT 1H | 26 | 2021-07-09 16:00 | 2021-07-09 16:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 20.52 | 20437 | 20437 | 0 | FLUSH THROUGH BOP STACK, CHOKE MANIFOLD, SEPERATOR, KILL LINE, TOP DRIVE AND FLOW LINE.
OZARK UNIT 1H | 26 | 2021-07-09 16:30 | 2021-07-09 19:00 | 2.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 20.63 | 20437 | 20437 | 0 | REMOVE FLOW LINE FROM SCISSOR, INSTALL WRANGLER ONTO BOP, REMOVE HCR LINE, KILL LINE, KILL LINE CHECK VALVE, HYDRAULIC LINES, HOLE FILL, AIR LINES/HYDRAULIC LINES FROM ROTATING HEAD, BACK OUT STREAMFLO ADAPTER FLANGE AND RAISE BOP., LAY DOWN BOP. RIG DOWN FLARE STACK, VENT LINES AND GAS SEPERATOR.
OZARK UNIT 1H | 26 | 2021-07-09 19:00 | 2021-07-09 20:00 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 20.67 | 20437 | 20437 | 0 | INSTALL WELLHEAD CAP AND TESTED T/5000 PSI. WELL RELEASED 7/9/21 @ 20:00.
OZARK UNIT 1H | 26 | 2021-07-09 20:00 | 2021-07-10 02:00 | 6 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 20.92 | 20437 | 20437 | 0 | CLEAN MUD TANKS.
OZARK UNIT 1H | 26 | 2021-07-09 20:00 | 2021-07-09 20:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 20.67 | 20437 | 20437 |  | MILESTONE_WELL RELEASE ON 7/9/2021 @ 20:00
OZARK UNIT 1H | 26 | 2021-07-10 02:00 | 2021-07-10 06:00 | 4 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 21.08 | 20437 | 20437 | 0 | SPLIT MUD TANKS AND STAGE FOR TRANSPORT TO ROMMEL 4H, 90 DAY INSPECTION ON TOP DRIVE, R/D MISC BACK YARD, R/D GENERTOR 2, 3, & 4, PIN TOP DRIVE, UNSPOOL DRAWWORKS, R/D RIG FLOOR, CLEAN RIG.
OZARK UNIT 1H | 27 | 2021-07-10 06:00 | 2021-07-11 | 18 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 21.83 | 20437 | 20437 | 0 | CONTINUE RIGGING DOWN, LOAD OUT, MOVE AND SET IN RIG ON THE ROMMEL 4H, WASH RIG, RIG DOWN AND MOVE TCB CAMPS, RIG DOWN MOTOR PACKAGE, VFD HOUSE, EXTEND AND PIN MSRC'S TO SUB AND LOWER @ 12:30, REMOVE BOP, EXTEND MSRC'S TO DERRICK AND LOWER DERRICK @ 14:10, UNDRESS DERRICK, REMOVE MONKEY BOARD, UNSPOOL DERRICK, SPLIT BLOCKS AND PIN IN CROWN SECTION, REMOVE CROWN, TOP AND MIDDLE SECTIONS OF DERRICK. REMOVE DS DOGHOUSE, DRAWWORKS, ODS DOG HOUSE, CHANGE OUT BOP ADAPTER, ROTATING HEAD BOWL AND ORBIT VALVE. LOAD OUT AND MOVE FRAC TANKS, MUD TANKS, MUD PUMPS, SUITCASES, CHOKE MANIFOLD,GAS SEPERATOR,VFD HOUSES, RIG WATER TANKS, PARTS HOUSES, MOTOR PACKAGE, PERFORMING CAR WASHES ON ALL EQUIPMENT LEAVING LOCATION. ON NEW LOCATION: SET MUD TANKS, MUD PUMPS, SUITCASES, VFD HOUSES, MOTOR PACKAGE, WATER TANKS AND PARTS HOUSES. NOTE: UNABLE TO EXTEND MSRC'S, TROUBLE SHOOT AND REPAIR ELECTRICAL ISSUES ON MSRC'S F/06:00 T/12:00
OZARK UNIT 1H | 27 | 2021-07-11 | 2021-07-11 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 21.83 | 20437 | 20437 |  | MILESTONE_RIG RELEASE ON 07/11/2021 @ 00:00
OZARK UNIT 1H | 27 | 2021-07-11 | 2021-07-11 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 21.83 | 20437 | 20437 |  | MILESTONE_TURN OVER TO COMPLETION ON 07/11/2021 @ 00:00
RAINIER 1H | 2 | 2021-05-09 06:00 | 2021-05-09 06:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB ON 5-9-21 @ 06:00
RAINIER 1H | 2 | 2021-05-09 06:00 | 2021-05-10 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | PINNED TOP DRIVE IN DERRICK FOR TRANSPORTATION, RIGGED DOWN RIG FLOOR, BLED OFF MSRC'S PIN TO SUB, SQUATTED SUB, SWAPPED HYDRAULICS TO DERRICK, PREPPED & LOWERED DERRICK, RIGGED DOWN BACKYARD ELECTRICAL/AIR/WATER LINES, SPLIT APART EQUIPMENT & PREPPED FOR TRANSPORTATION, LOADED AND TRANSPORTED MUD TANKS, MUD PUMPS, GENERATORS, AND MISC LOADS. UNDRESS DERRICK, REMOVE CROWN, TOP AND MIDDLE SECTIONS OF DERRICK. REMOVE DS DOGHOUSE. PERFORMING CAR WASHES ON ALL EQUIPMENT LEAVING LOCATION. ON NEW LOCATION SET MUD TANKS AND MUD PUMPS, SUITCASES, VFD HOUSE, MOTOR PACKAGE, DIESEL TANK, BULK TANKS, WATER TANKS, & PARTS HOUSES, SET SUB MATS, RIGGED DOWN PATTERSON CAMP HOUSES & PARTS HOUSES, LOADED OUT AND MOVED HOUSES TO NEW LOCATION, RIGGED UP ALL CAMP HOUISES & PARTS HOUSES
RAINIER 1H | 3 | 2021-05-10 06:00 | 2021-05-11 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | MOVED & SPOTTED SUBS, INSTALLED CENTER STEEL & CENTERED OVER WELL, SET ODS & DS DOG HOUSES, DRAWWORKS, & PINNED STARTER LEG SECTION OF DERRICK, INSTALLED NEW POP OFF LINE ON #3 MUD PUMP, RAN ALL WIRES AND HOOKED UP SAME FROM MUD TANKS & MUD PUMPS, RAN & HOOKED UP WIRES FROM DOG HOUSES, RIGGED UP FESTOON AND RAN ALL WIRES, PUT TOGETHER DERRICK, HOOKED UP BLOCKS TO TOP DRIVE, INSTALLED DERRICK BOARD, & DRESSED OUT DERRICK PREPPING IT TO BE RAISED. NOTE: INSPECTION AND REPAIRS WERE MADE TO MAST & SUB DURING CAT III INSPECTION AND RIG MOVE. 6" CHANNEL IRON FLANGE ON RACKING BOARD BELOW LADDER HAD TO BE REPAIRED. HANDRAIL ON CROWN WAS BENT AND HAD TO BE STRAIGHTENED. MISSING 1/2" GUSSET PLATE ON BOTH SIDES OF UPPER TWO STANDPIPE SUPPORTS ON LOWER INTERMEDIATE MAST WAS CRACKED AND HAD TO BE REPAIRED. PINS THAT PINNED SECTIONS OF DERRICK TOGETHER WERE MUSHROOMED AND HAD TO BE GROUND DOWN. LADDER RUNG ON INTERMEDIATE SECTION OF DERRICK WAS BENT AND HAD TO BE REPLACED. WEAR PADS ON TOP DRIVE DOLLY WERE BAD AND HAD TO BE REPLACED. TOP OF DERRICK STANDPIPE HAD DISTORTED PAD EYE THAT NEEDED TO BE REPLACED. BOLT SAFETY CABLES ON TOP DRIVE DOLLY WERE BAD AND REPLACED. DOCKING PINS ON TOP DRIVE DOLLY WERE DISTORED AND WILL BE REPLACED ON NEXT RIG MOVE. MISSING HANDRAIL PINS ON UPPER STANDPIPE PLATFORM WERE INSTALLED. REPLACED ELECTRICAL CONDUIT CLIPS IN LOWER MAST. RUST SPOTS FOUND THROUGHOUT MAST THAT WILL BE SCHEDULED TO BE SANDBLASTED AND PAINTED ON NEXT RIG MOVE. TWO LOWER INTERMEDIATE DERRICK SECTION HANRAILS WERE BENT AND HAD TO BE STRAIGHTENED. UPPER STANDPIPE LADDER WAS INSTALLED WRONG AND HAD TO BE RE-INSTALLED CORRECTLY. UPPER JUNCTION BOX DOOR HINGE WAS SEIZED AND HAD TO BE REPLACED.
RAINIER 1H | 4 | 2021-05-11 06:00 | 2021-05-12 06:00 | 24 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | DRESSED OUT DERRICK & SPOOLED UP DRILL LINE ONTO DRAWWORKS DRUM, HELD PJSM & PERFORMED DERRICK INSPECTION FOR DERRICK TO BE RAISED, RAISED DERRICK, UNPINNED MSRC, INSTALLED BOP WRANGLER, V-DOOR POLES, PINNED MSRC TO SUB FOR SUB TO BE RAISED, HELD PJSM FOR RAISING SUB, RAISED SUB & PINNED SAME, UNPINNED & LOWERED MSRC & BOOSTER CYLINDERS, RIGGED UP V-DOOR & CATWALK, HUNG FLOWLINE IN SUB, INSTALLED STAIRS, RIGGED DOWN BOOSTER CYLINDERS & PINNED STOMPERS, RIGGED UP ALL HANDRAILS OIN RIG FLOOR, SPOOLED UP HOIST LINES, HOOKED UP WIRES TO DOG HOUSES, HOOKED UP WIRES TO TOP DRIVE, SLID OUT DRILLERS CABIN, RIGGED UP ELECTRIC/AIR/WATER LINES FROM GRASSHOPPER, RIGGED UP STANDPIPE HOSE F/SUB T/DERRICK STANDPIPE, RIGGED UP WEIGHT BUCKETS & SLOW DECENT ANCHOR, SPOOLED UP DRILL LINE ONTO DRAWWOKS, UNPINNED BLOCKS & TD THEN LOWERED TO RIG FLOOR, RIGGED UP BAILS & ELEVATORS, CALIBRATED BLOCKS, DRESSED OUT FLOOR W/5" HANDLING TOOLS, RIGGED UP STANDPIPE HOSES F/MUD PUMPS T/SUB, WORKED ON CAT III INSPECTION REPAIRS
RAINIER 1H | 5 | 2021-05-12 06:00 | 2021-05-12 10:00 | 4 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | ON COMPANY TIME ON 5/12/2021 @ 06:00. INSTALL CONDUCTOR RISER AND CELLAR PUMPS, RUN HOSES TO SHAKER GOOSENECKS AND RIG UP OFFLINE CEMENT MANIFOLD, DRESS OUT SHAKER WITH 140 MESH SCREENS, FILL MUD TANKS WITH WATER AND MIX TREATMENT
RAINIER 1H | 5 | 2021-05-12 10:00 | 2021-05-12 15:00 | 5 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | CHANGE SWIVEL PACKING AND SAVER SUB, PRESSURE TEST ALL SURFACE LINES TO 2,000 PSI, INSTALL CELLAR COVERS, LAY OUT AND STRAP BHA, CHANGE TONG HEAD AND DIES, PUMP UP LOAD CELL FOR TONG TORQUE
RAINIER 1H | 5 | 2021-05-12 15:00 | 2021-05-12 17:00 | 2 | P | MOBDMOB | LMOV | MIRU | MOVE IN / RIG UP | 0 | 108 | 108 | 0 | PICK UP BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 7-3/4", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 108'.
RAINIER 1H | 5 | 2021-05-12 17:00 | 2021-05-12 17:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 5/12/2021 @ 17:00
RAINIER 1H | 5 | 2021-05-12 17:00 | 2021-05-12 23:30 | 6.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.27 | 108 | 2613 | 385.4 | ROTATE (2,505' IN 6.62HR @ 378 FPH) WOB-10-30K, RPM-80, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-229, SPP-2100/2600 PSI, DIFF-300/500 PSI. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM
RAINIER 1H | 5 | 2021-05-12 23:30 | 2021-05-13 01:00 | 1.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.33 | 2613 | 2903 | 193.3 | SLIDE (290' IN 1.38 HRS @ 209 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-229, SPP-2100/2300 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: F/490' T/510' 20' TF-30M 1850-1858 F/585' T/610' 25' TF-35M 1942-1947 F/875' T/895' 20' TF-10L 1957-2000 F/972' T/992' 20' TF-45L 2010-2016 F/1068' T/1088' 20' TF-90L 2024-2029 F/1256' T/1276' 20' TF-90L 2054-2102 F/1530' T/1550' 20' TF-60R 2130-2135 F/1635' T/1655' 20' TF-HS 2145-2151 F/1725' T/1745' 20' TF-HS 2158-2205 F/1635' T/1655' 20' TF-HS 2145-2151 F/1852' T/1872' 20' TF-HS 2214-2218 F/1915' T/1935' 20' TF-HS 2226-2230 F/2695' T/2715' 20' TF-180 0006-0015
RAINIER 1H | 5 | 2021-05-13 01:00 | 2021-05-13 01:30 | 0.5 | U | SFHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.35 | 2903 | 2903 | 0 | CIRCULATE HOLE CLEAN WHILE EVALUATING PIPE TALLY FOR DISCREPANCY FROM PIPE COUNT AND PIPE TALLY. DISCOVERED THAT 3 JOINTS OF HWDP WERE ADDED INTO THE PIPE TALLY IN ADDITON OF BEING ADDED TO THE BHA.
RAINIER 1H | 5 | 2021-05-13 01:30 | 2021-05-13 02:00 | 0.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.38 | 2903 | 3033 | 260 | ROTATE (130' IN .5 HR @ 260 FPH) WOB-10-30K, RPM-80, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-229, SPP-2100/2600 PSI, DIFF-300/500 PSI.
RAINIER 1H | 5 | 2021-05-13 02:00 | 2021-05-13 02:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.4 | 3033 | 3033 | 0 | PUMP 2-30 BBLS SWEEPS IN TANDEM AND CIRCULATE BOTTOMS UP. GPM=900, SPP=2100, RPM=80, TQ=2-3K
RAINIER 1H | 5 | 2021-05-13 02:30 | 2021-05-13 04:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.46 | 3033 | 3033 | 0 | PULL OUT OF HOLE F/3,033' T/BHA. NO EXCESS DRAG ON TRIP OUT OF HOLE.
RAINIER 1H | 5 | 2021-05-13 04:00 | 2021-05-13 05:00 | 1 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.5 | 3033 | 3033 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND BREAK BIT.
RAINIER 1H | 5 | 2021-05-13 05:00 | 2021-05-13 06:00 | 1 | U | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 0.54 | 3033 | 3033 | 0 | FRANK'S CASING CREW NOT ON LOCATION. PICK UP BHA AND TRIP IN HOLE WHILE WAITING ON FRANK'S CASING CREW
RAINIER 1H | 6 | 2021-05-13 06:00 | 2021-05-13 07:00 | 1 | U | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 0.58 | 3033 | 3033 | 0 | TRIP IN HOLE T/3,033'. PERFORMING WIPER TRIP WHILE WAITING ON FRANK'S CASING CREW AND EQUIPMENT
RAINIER 1H | 6 | 2021-05-13 07:00 | 2021-05-13 07:30 | 0.5 | U | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.6 | 3033 | 3033 | 0 | CIRCULATE BOTTOMS UP. PP-1975, GPM-900, RPM-80, TQ=1-2K
RAINIER 1H | 6 | 2021-05-13 07:30 | 2021-05-13 08:30 | 1 | U | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.65 | 3033 | 3033 | 0 | POOH T/BHA. NO EXCESS DRAG ON TRIP OUT.
RAINIER 1H | 6 | 2021-05-13 08:30 | 2021-05-13 09:30 | 1 | U | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.69 | 3033 | 3033 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND BREAK BIT. BIT HAD MINIMAL WEAR AND IN GOOD CONDITION. MOTOR BEARING SLACK WAS MINIMAL AND PAD WEAR WAS MINIMAL.
RAINIER 1H | 6 | 2021-05-13 09:30 | 2021-05-13 10:00 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 0.71 | 3033 | 3033 | 0 | REMOVE MOUSEHOLE AND RIG ELEVATORS
RAINIER 1H | 6 | 2021-05-13 10:00 | 2021-05-13 11:00 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.75 | 3033 | 3033 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS. REMOVE CONDUCTOR RISER AND INSTALL CASING GUIDE TOOL ON CONDUCTOR
RAINIER 1H | 6 | 2021-05-13 11:00 | 2021-05-13 14:00 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.88 | 3033 | 3033 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). THEN RUN 74 JOINTS (77 TOTAL) OF 10 3/4" 45.5# J-55 BT&C CASING T/3,018.50'. RAN 40 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JOINT ALL THE WAY TO 37.' INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED WELLHEAD T/5000 PSI. SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET 100K (W/O BLOCKS) ON BASE PLATE. SHOE- 3,018.50 TOP OF FLOAT COLLAR- 2,938.20
RAINIER 1H | 6 | 2021-05-13 14:00 | 2021-05-13 15:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.92 | 3033 | 3033 | 0 | CIRCULATE CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS. GPM-321, SPP-200, NO LOSSES.
RAINIER 1H | 6 | 2021-05-13 15:00 | 2021-05-13 15:30 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 0.94 | 3033 | 3033 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT.
RAINIER 1H | 6 | 2021-05-13 15:30 | 2021-05-13 16:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0.98 | 3033 | 3033 | 0 | LUBRICATE RIG
RAINIER 1H | 6 | 2021-05-13 16:30 | 2021-05-13 19:30 | 3 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1.1 | 3033 | 3033 | 0 | R/U STREAMFLO PUP JOINT, CEMENT HEAD, AND CIRCULATING IRON. PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 324 BBLS 11.6 PPG LEAD CEMENT, 85 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 280 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/900 PSI PRESSURED UP T/1428 PSI (528 PSI OVER) @ 3 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 130 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
RAINIER 1H | 6 | 2021-05-13 19:30 | 2021-05-13 20:00 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.13 | 3033 | 3033 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MINUTES, GOOD TEST.
RAINIER 1H | 6 | 2021-05-13 20:00 | 2021-05-13 21:00 | 1 | P | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 1.17 | 3033 | 3033 | 0 | RIG DOWN CEMENT HEAD, CIRCULATING LINES, OFF-LINE CEMENTING FLANGE AND CELLAR PUMPS.
RAINIER 1H | 6 | 2021-05-13 21:00 | 2021-05-13 23:30 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.27 | 3033 | 3033 | 0 | INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALL KILL LINE, INSTALL CHOKE LINE TO BOP AND CHOKE, HOOK UP HYDRAULIC LINES TO BOP STACK, FUNCTION TEST SAME.
RAINIER 1H | 6 | 2021-05-13 23:30 | 2021-05-14 06:00 | 6.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.54 | 3033 | 3033 | 0 | HELD PJSM AND RIG UP TESTERS. INSTALL SHORT TEST PLUG AND TEST WH CONNECTION TO 250 LOW / 5000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ORBIT VALVE AND ROTATING HEAD TO 250 LOW / 1500 HIGH. REMOVE SHORT TEST PLUG AND INSTALL LONG TEST PLUG AND TEST FOLLOWING BOPE TO 250 LOW / 10,000 HIGH. TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2", AND 5" DP IN LOWER PIPE RAMS,TEST 4-1/2" DP IN UPPER PIPE RAMS. TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, AND HCR.
RAINIER 1H | 7 | 2021-05-14 06:00 | 2021-05-14 08:00 | 2 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.63 | 3033 | 3033 | 0 | PERFORM TEST WITH LONG TEST PLUG; TEST FOLLOWING BOPE TO 250 LOW / 10,000 HIGH. TEST BOTTOM BREAK ON BOP, TEST W/ 5" DP LOWER PIPE RAMS, ATTEMPT TO TEST CHECK VALVE (TEST FAILED). TEST KILL LINE BACK TO MUD PUMPS 250 LOW / 5,000 HIGH. ATTEMPT TO TEST UPPER PIPE RAMS 250 LOW / 10,000 HIGH, PUMP ON TESTING UNIT FAILED. TROUBLESHOOT PUMP FROM 07:30 TO 08:00. BEGIN WAITING ON NEW TEST UNIT TO ARRIVE ON LOCATION @ 08:00; CASING VALVE VERIFIED OPEN DURING TEST
RAINIER 1H | 7 | 2021-05-14 08:00 | 2021-05-14 10:30 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.73 | 3033 | 3033 | 0 | RIG UP FLOWLINE, TURNBUCKLES, FILL UP LINE, AND KATCH KAN EQUIPMENT TO STACK; REMOVE CHECK VALVE IN PREPARATION TO REPLACE; DRESS RIG SHAKERS AND DRYER SHAKERS WITH 170 API SCREENS; PERFORM DRAW DOWN TEST ON ACCUMULATOR
RAINIER 1H | 7 | 2021-05-14 10:30 | 2021-05-14 13:00 | 2.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.83 | 3033 | 3033 | 0 | REPLACEMENT TEST UNIT ARRIVED @ 10:30; TEST FOSV AND INSIDE GREY 250 PSI LOW / 10,000 PSI HIGH; TEST TD FOSV, IBOP, STANDPIPE 4" VALVE AND BACK TO MUD PUMPS 250 PSI LOW / 7,000 PSI HIGH; TEST INSIDE AND OUTSIDE KILL LINE VALVES, 4" MANUAL VALVE, AND HCR 250 PSI LOW / 10,000 PSI HIGH; TEST LOWER RAMS AND UPPER RAMS W/4.5" DP, 5" DP, AND 5.5" DP 250 PSI LOW / 10,000 PSI HIGH; TEST ANNULAR W/4.5" DP, 5" DP, 5.5" DP 250 PSI LOW / 3,500 PSI HIGH; REPLACE KILL LINE CHECK VALVE UPON ARRIVAL AND TEST 250 PSI LOW / 10,000 PSI HIGH;
RAINIER 1H | 7 | 2021-05-14 13:00 | 2021-05-14 16:00 | 3 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.96 | 3033 | 3033 | 0 | CONTINUE TO RIG UP FLOWLINE; RIG UP MISC; INSTALL WEAR BUSHING; LAY OUT BHA ON PIPE WRANGLER
RAINIER 1H | 7 | 2021-05-14 16:00 | 2021-05-14 19:00 | 3 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 2.08 | 3033 | 3033 | 0 | PICK UP (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 5.98' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SVY-70' AND GAMMA-60'. TEST MWD-TEST GOOD
RAINIER 1H | 7 | 2021-05-14 19:00 | 2021-05-14 20:30 | 1.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 2.15 | 3033 | 3033 | 0 | TRIP IN HOLE F/BHA T/2,938'. PICK UP AGITATOR ON STAND 22: PSI BEFORE-450, PSI AFTER-545 @ 336 GPM.
RAINIER 1H | 7 | 2021-05-14 20:30 | 2021-05-14 21:30 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 2.19 | 3033 | 3033 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD, FILL GAS SEPERATOR, PERORM BOP DRILL, RESPONSE TIME= 41 SECONDS.
RAINIER 1H | 7 | 2021-05-14 21:30 | 2021-05-14 22:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.23 | 3033 | 3033 | 0 | SERVICE TOP DRIVE, ST-80 AND DRAW WORKS.
RAINIER 1H | 7 | 2021-05-14 22:30 | 2021-05-14 23:00 | 0.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 2.25 | 3033 | 3043 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/3,033' T/3,043', GPM-500, SPP-1400/1800 PSI, DIFF-200/400, RPM-50, TQ-2/5K.
RAINIER 1H | 7 | 2021-05-14 23:00 | 2021-05-14 23:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.27 | 3043 | 3043 | 0 | CIRCULATE BOTTOMS UP GPM-500, SPP-1400 PSI, RPM-50.
RAINIER 1H | 7 | 2021-05-14 23:30 | 2021-05-15 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 2.29 | 3043 | 3043 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, 438 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,018' / TVD-2,975'.
RAINIER 1H | 7 | 2021-05-15 | 2021-05-15 00:30 | 0.5 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.31 | 3043 | 3043 | 0 | TROUBLE SHOOT TOP DRIVE FOR ELECTRICAL ISSUES, TOP DRIVE TRIPPING BREAKER WHEN FUNCTION TOP DRIVE FOR ROTATION FOR DRILLING OPERATIONS.
RAINIER 1H | 7 | 2021-05-15 00:30 | 2021-05-15 05:00 | 4.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.5 | 3043 | 5371 | 517.3 | ROT (2328' IN 4.58 HRS @ 508.3 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 7K/9K, SPP: 3600/4400 PSI, DIFF: 600/800 PSI.
RAINIER 1H | 7 | 2021-05-15 05:00 | 2021-05-15 06:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.54 | 5371 | 5489 | 118 | SLIDE (118' IN .92 HRS @ 128.3 FPH) WOB: 20/30K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3600/4100 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/3152' T/3167' 15' TF-60R 0053-0058 SLD F/3250' T/3265' 15' TF-60R 0109-0114 SLD F/3345' T/3357' 12' TF-HS 122-130 SLD F/3442' T/3457' 15' TF-HS 138-143 SLD F/3728' T/3743' 15' TF-15R 213-220 SLD F/3918' T/3933' 15' TF-30R 238-245 SLD F/4100' T/4116' 16' TF-60R 303-314 SLD F/4655' T/4670' 15' TF-15R 414-421
RAINIER 1H | 8 | 2021-05-15 06:00 | 2021-05-15 08:30 | 2.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.65 | 5489 | 6365 | 350.4 | ROT (876' IN 2.65 HRS @330.56 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 12K/18K, SPP: 4200/4800 PSI, DIFF: 600/800 PSI.
RAINIER 1H | 8 | 2021-05-15 08:30 | 2021-05-15 11:00 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.75 | 6365 | 6452 | 34.8 | SLIDE (87' IN 2.27 HRS @ 38.33 FPH) WOB: 10/15K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4200 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/5780 T/5795 15' TF-60R 0642-0654 SLD F/5873 T/5888 15' TF-45R 0708-0732 SLD F/5968 T/5983 15' TF-45R 0744-0811 SLD F/6062 T/6077 15' TF-45R 0825-0852 SLD F/6157 T/6172 15' TF-45R 0904-0925 SLD F/6440 T/6452 12' TF-HS 1030-1055
RAINIER 1H | 8 | 2021-05-15 11:00 | 2021-05-15 12:00 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.79 | 6452 | 6610 | 158 | ROT (158' IN .88 HRS @179.55 FPH) WOB: 30K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 7K/14K, SPP: 2700/2900 PSI, DIFF: 300/400 PSI. NOTE: DRILLING WITH #2 & #3 MUD PUMPS WHILE CHANGING VALVE AND SEAT IN #1 MUD PUMP.
RAINIER 1H | 8 | 2021-05-15 12:00 | 2021-05-15 12:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.81 | 6610 | 6625 | 30 | SLIDE (87' IN 2.27 HRS @ 38.33 FPH) WOB: 10/20K, SPM: 105/105, GPM: 674, MMRPM: 111, SPP:2500/2700 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/6528 T/6543 15' TF-HS 1125-1207 NOTE: DRILLING WITH #2 & #3 MUD PUMPS WHILE CHANGING VALVE AND SEAT IN #1 MUD PUMP.
RAINIER 1H | 8 | 2021-05-15 12:30 | 2021-05-15 13:30 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.85 | 6625 | 6865 | 240 | ROT (240' IN .72 HRS @ 333.33 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 12K/18K, SPP: 4200/4800 PSI, DIFF: 600/800 PSI.
RAINIER 1H | 8 | 2021-05-15 13:30 | 2021-05-15 16:00 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.96 | 6865 | 6910 | 18 | SLIDE (45' IN 2.78 HRS @ 16.19 FPH) WOB: 10/15K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4200 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/6625 T/6640 15' TF-HS 1230-1315 SLD F/6730 T/6745 15' TF-HS 1331-1431 SLD F/6815 T/6830 15' TF-HS 1449-1551
RAINIER 1H | 8 | 2021-05-15 16:00 | 2021-05-15 17:00 | 1 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3 | 6910 | 6910 | 0 | SERVICE TOP DRIVE, BLOCK, CROWN.
RAINIER 1H | 8 | 2021-05-15 17:00 | 2021-05-15 18:00 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.04 | 6910 | 6925 | 15 | SLIDE (15' IN 1 HR @ 15 FPH) WOB: 10/20K, SPM: 105/105, GPM: 674, MMRPM: 111, SPP:2500/2700 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/6910 T/6925 15' TF-30L 1700-1800 NOTE: DRILLING WITH #2 & #3 MUD PUMPS WHILE CHANGING VALVE AND SEAT IN #1 MUD PUMP.
RAINIER 1H | 8 | 2021-05-15 18:00 | 2021-05-15 18:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.06 | 6925 | 6993 | 136 | ROT (68' IN .50 HRS @136 FPH) WOB: 30K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 7K/14K, SPP: 2700/2900 PSI, DIFF: 300/400 PSI. NOTE: DRILLING WITH #2 & #3 MUD PUMPS WHILE CHANGING VALVE AND SEAT IN #1 MUD PUMP. NOTE: STARTED CUTTING BACK MUD WT. F/9.1 PPG T/8.9 PPG AND PUMPING LCM SWEEPS EVERY STAND @ 6,920' DUE TO REDUCED ROP WHILE SLIDING.
RAINIER 1H | 8 | 2021-05-15 18:30 | 2021-05-15 19:00 | 0.5 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.08 | 6993 | 6993 | 0 | THE WELDS ON THE SUPPORT BRACE ON THE STANDPIPE MANIFOLD AND SUPPORT BRACE ON STANDPIPE IN DERRICK BROKE, CIRCULATE AND RECIPROCATE WHILE WELDING SUPPORT BRACES, SPM: 30/30, GPM: 193, RPM-80, TRQ: 5K/8K, SPP: 350 PSI.
RAINIER 1H | 8 | 2021-05-15 19:00 | 2021-05-15 19:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.1 | 6993 | 7065 | 144 | ROT (72' IN .67 HRS @ 107.5 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 12K/18K, SPP: 4100/4900 PSI, DIFF: 600/800 PSI.
RAINIER 1H | 8 | 2021-05-15 19:30 | 2021-05-15 20:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.13 | 7065 | 7085 | 40 | SLIDE (20' IN .33 HRS @ 60.6 FPH) WOB: 10/15K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4400 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/7007 T/7027 20' TF-HS 1926-1946
RAINIER 1H | 8 | 2021-05-15 20:00 | 2021-05-15 21:00 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.17 | 7085 | 7275 | 190 | ROT (190' IN 1 HR @ 190 FPH) WOB: 30K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 12K/18K, SPP: 2700/2900 PSI, DIFF: 300/400 PSI. NOTE: DRILLING WITH #1 & #3 MUD PUMPS WHILE CHANGING VALVE AND SEAT IN #2 MUD PUMP, STOP DRILLING DUE TO THE 4" VALVE OM #2 MUD PUMP STARTED LEAKING AND UNABLE TO ISOLATE #2 MUD PUMP.
RAINIER 1H | 8 | 2021-05-15 21:00 | 2021-05-15 22:00 | 1 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.21 | 7275 | 7275 | 0 | WORK PIPE WHILE CHANGING 4" VALVE, FINISH CHANGING OUT VALVE AND SEAT ON #2 MUD PUMP, MAX DRAG WHILE WORKING PIPE= 30K/35K.
RAINIER 1H | 8 | 2021-05-15 22:00 | 2021-05-15 23:30 | 1.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.27 | 7275 | 7607 | 221.3 | ROT (332' IN 1.3 HRS @ 255.4 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 12K/20K, SPP: 4100/4900 PSI, DIFF: 600/800 PSI.
RAINIER 1H | 8 | 2021-05-15 23:30 | 2021-05-16 01:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.33 | 7607 | 7647 | 26.7 | SLIDE (40' IN 1.7 HRS @ 23.5 FPH) WOB: 10/15K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4400 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/7385' T/7405' 20' TF-60R 2216-2255 SLD F/7565' T/7585' 20' TF-HS 2327-0030 NOTE: START BACK REAMING A STAND BEFORE SLIDING @ 7,647' TO AID IN ROP WHILE SLIDING.
RAINIER 1H | 8 | 2021-05-16 01:00 | 2021-05-16 02:00 | 1 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.38 | 7647 | 7647 | 0 | SAVER SUB BACKED OUT WHILE ATTEMPTING TO UNSCREW OUT OF CONNECTION WITH TOP DRIVE, CIRCULATE @ 321 GPM WHILE UNDRESS TOP DRIVE AND RETORQUE SAVER SUB TO 46K, BREAK CONNNECTION WITH RIG TONGS AND DRESS TOP DRIVE BACK UP.
RAINIER 1H | 8 | 2021-05-16 02:00 | 2021-05-16 04:00 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.46 | 7647 | 8059 | 206 | ROT (412' IN 1.95 HRS @ 211.3 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 13K/21K, SPP: 4100/4900 PSI, DIFF: 600/800 PSI. NOTE: STARTED WEIGHTING UP F/8.9 PPG T/9.1 PPG @ 7,700'.
RAINIER 1H | 8 | 2021-05-16 04:00 | 2021-05-16 06:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.54 | 8059 | 8119 | 30 | SLIDE (60' IN 2.05 HRS @ 29.3 FPH) WOB: 35/45K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4600 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/7660' T/7680' 20' TF-HS 226-338 SLD F/7755' T/7775' 20' TF-HS 353-410 SLD F/7940' T/7960' 20' TF-HS 446-520 NOTE: BACK REAMING A STAND BEFORE SLIDING TO AID IN ROP WHILE SLIDING. SLIDING ROP IMPROVED TO 100-130 FPH @ 7,677'.
RAINIER 1H | 9 | 2021-05-16 06:00 | 2021-05-16 10:30 | 4.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.73 | 8119 | 8760 | 142.4 | ROT (641' IN 4.37 HRS @ 146.68 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 13K/21K, SPP: 4900/5100 PSI, DIFF: 400/600 PSI. NOTE: STARTED CUTTING WEIGHT F/9.2 PPG T/8.9 PPG @ 8,140', MAINTAIN 8.9 PPG WHILE DRILLING THROUGH WILCOX, THEN INCREASE MUD WEIGHT T/ 9.2 PPG IN MIDWAY FORMATION. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: AT 8,600' INCREASE MUD WEIGHT F/ 8.9+PPG T/ 9.2 PPG.
RAINIER 1H | 9 | 2021-05-16 10:30 | 2021-05-16 15:00 | 4.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.92 | 8760 | 8890 | 28.9 | SLIDE (130' IN 4.63 HRS @ 28.08 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4600/4800 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/8130 T/8147 17' TF-30L 0620-0730 SLD F/8225 T/8245 20' TF-HS 0826-0935 SLD F/8275 T/8285 10' TF-HS 0945-1021 SLD F/8595 T/8622 27' TF-40R 1152-1229 SLD F/8695 T/8725 30' TF-40R 1257-1336 SLD F/8790 T/8816 26' TF-40R 1359-1426
RAINIER 1H | 9 | 2021-05-16 15:00 | 2021-05-16 16:00 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.96 | 8890 | 9065 | 175 | ROT (175' IN .78 HRS @ 224.36 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 12K/19K, SPP: 3400/3600 PSI, DIFF: 500/700 PSI. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS WHILE CHANGING SWAB AND ADJUSTING DRIVE BELTS #2 MUD PUMP.
RAINIER 1H | 9 | 2021-05-16 16:00 | 2021-05-16 17:00 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4 | 9065 | 9082 | 17 | SLIDE (17' IN 1.22 HRS @ 13.9 FPH) WOB: 25/40K, SPM: 105/105, GPM: 674, MMRPM: 111, SPP:2900/3200 PSI, DIFF: 150/300 PSI. SLIDE DEPTHS: SLD F/9065 T/9082 17' TF-60R 1547-1700 NOTE: DRILLING WITH #1 AND #3 MUD PUMPS WHILE CHANGING SWAB AND ADJUSTING DRIVE BELTS #2 MUD PUMP.
RAINIER 1H | 9 | 2021-05-16 17:00 | 2021-05-16 18:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.04 | 9082 | 9161 | 79 | ROT (79' IN .95 HRS @ 83.2 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 13K/22K, SPP: 4700/5300 PSI, DIFF: 400/600 PSI. NOTE: ENCOUNTERED 19 BPH SEEPAGE LOSSES @ 9,125', STARTED ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: OBSERVED A SMALL AMOUNT OF 1/2"-1" DIAMETER SLOUGHING SHALE @ 9,160' COMING ACROSS THE SHAKERS. INCREASE MUD WEIGHT F/ 9.3 PPG T/ 9.4 PPG.
RAINIER 1H | 9 | 2021-05-16 18:00 | 2021-05-16 21:00 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.17 | 9161 | 9215 | 18 | SLIDE (54' IN 3.05 HRS @ 17.7 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4700/5000 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/9122 T/9152 30' TF-60R 1727-1858 SLD F/9170 T/9194 24' TF-60R 1914-2046
RAINIER 1H | 9 | 2021-05-16 21:00 | 2021-05-16 21:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.19 | 9215 | 9340 | 250 | ROT (125' IN .5 HRS @ 250 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 14K/22K, SPP: 3200/3900 PSI, DIFF: 500/700 PSI. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS WHILE CHANGING SWAB ON #2 MUD PUMP.
RAINIER 1H | 9 | 2021-05-16 21:30 | 2021-05-16 22:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.21 | 9340 | 9372 | 64 | ROT (32' IN .40 HRS @ 80 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 13K/22K, SPP: 4700/5300 PSI, DIFF: 400/600 PSI. NOTE: ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND.
RAINIER 1H | 9 | 2021-05-16 22:00 | 2021-05-16 23:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.27 | 9372 | 9397 | 16.7 | SLIDE (25' IN 1.55 HRS @ 16.13 FPH) WOB: 35/45K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4800/5100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/9352 T/9377 25' TF-50R 2142-2315
RAINIER 1H | 9 | 2021-05-16 23:30 | 2021-05-17 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.29 | 9397 | 9482 | 170 | ROT (85' IN .55 HRS @ 154.5 FPH) WOB: 30/40K, SPM: 83/83/83, GPM: 800, MMRPM: 133, RPM-60, TRPM: 193, TRQ: 14K/22K, SPP: 4200/5000 PSI, DIFF: 600/800 PSI. NOTE: ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: STILL OBSERVING A SMALL AMOUNT OF 1/8"-1/4" DIAMETER SLOUGHING SHALE @ 9,397' COMING ACROSS THE SHAKERS. INCREASE MUD WEIGHT F/ 9.4 PPG T/ 9.5 PPG. NO SLOUGHING SHALE OBSERVED WITH A 9.5 PPG. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: THE IDLER BEARINGS ON #1 GENERATOR LOCKED UP, SHUT DOWN #1 GENERATOR, SLOWED DOWN MUD PUMPS TO 800 GPM AND REDUCED RPM TO 60 RPM. CONTINUE DRILLING @ 800 GPM WHILE WAITING MECHANIC AND REPLACING IDLER BEARINGS.
RAINIER 1H | 9 | 2021-05-17 | 2021-05-17 01:30 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.35 | 9482 | 9528 | 30.7 | SLIDE (46' IN 1.5 HRS @ 30.67 FPH) WOB: 35/45K, SPM: 83/83/83, GPM: 800, MMRPM: 133, SPP: 4200/4500 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/9397 T/9427 30' TF-45R 2327-0002 SLD F/9444 T/9460 17' TF-45R 0021-0116
RAINIER 1H | 9 | 2021-05-17 01:30 | 2021-05-17 02:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.38 | 9528 | 9528 | 0 | SERVICE TOP DRIVE, ST-80 AND DRAW WORKS.
RAINIER 1H | 9 | 2021-05-17 02:00 | 2021-05-17 02:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.4 | 9528 | 9591 | 126 | ROT (63' IN .72 HRS @ 87.5 FPH) WOB: 30/40K, SPM: 83/83/83, GPM: 800, MMRPM: 133, RPM-60, TRPM: 193, TRQ: 14K/22K, SPP: 4200/5000 PSI, DIFF: 600/800 PSI. NOTE: ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: CONTINUE DRILLING @ 800 GPM WHILE WAITING MECHANIC AND REPLACING IDLER BEARINGS.
RAINIER 1H | 9 | 2021-05-17 02:30 | 2021-05-17 04:00 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.46 | 9591 | 9621 | 20 | SLIDE (30' IN 1.28 HRS @ 23.4 FPH) WOB: 35/45K, SPM: 83/83/83, GPM: 800, MMRPM: 133, SPP: 4200/4500 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/9543 T/9573 30' TF-60R 0207-0324 NOTE: FINISH REPLACING IDLER BEARINGS ON #1 GENERATOR @ 04:00.
RAINIER 1H | 9 | 2021-05-17 04:00 | 2021-05-17 05:30 | 1.5 | U | INTHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 4.52 | 9621 | 9621 | 0 | ROTATE STARTED LEAKING, CIRCULATE AND RECIPROCATE PIPE WHILE RACKING BACK STAND IN MOUSE HOLE, GPM: 800, RPM-60, TRQ: 7K/13K, SPP: 4200 PSI, REMOVE ROTATING HEAD, OBSERVED THAT BOTTOM ROTATING HEAD RUBBER BROKE APPART AND PIECE OF RUBBER WAS STUCK IN THE FLOW LINE, RETREIVED RUBBER OUT OF FLOW LINE, INSTALLED NEW ROTATING HEAD.
RAINIER 1H | 9 | 2021-05-17 05:30 | 2021-05-17 06:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.54 | 9621 | 9636 | 30 | ROT (15' IN .5 HRS @ 30 FPH) WOB: 30/40K, WOB: 30/40K, SPM: 83/83/83, GPM: 800, MMRPM: 133, RPM-60, TRPM: 193, TRQ: 13K/22K, SPP: 4200/5000 PSI, DIFF: 600/800 PSI. NOTE: ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND.
RAINIER 1H | 10 | 2021-05-17 06:00 | 2021-05-17 09:30 | 3.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.69 | 9636 | 10306 | 191.4 | ROT (670' IN 3.52 HRS @ 190.34 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 14K/20K, SPP: 5550/5750 PSI, DIFF: 400/500 PSI. NOTE: ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND.
RAINIER 1H | 10 | 2021-05-17 09:30 | 2021-05-17 12:30 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.81 | 10306 | 10408 | 34 | SLIDE (102' IN 2.98 HRS @ 34.23 FPH) WOB: 15/25K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 5200/5300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/9636 T/9651 15' TF-60R 0600-0630 SLD F/9725 T/9765 40' TF-60R 0635-0715 SLD F/10195 T/10209 14' TF-60R 0933-1015 SLD F/10225 T/10236 11' TF-60R 1024-1100 SLD F/10285 T/10307 22' TF-60R 1118-1149
RAINIER 1H | 10 | 2021-05-17 12:30 | 2021-05-17 13:00 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.83 | 10408 | 10524 | 232 | ROT (116' IN .50 HRS @ 232 FPH) WOB: 30K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 14K/20K, SPP: 3800/3900 PSI, DIFF: 600 PSI. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS WHILE CHANGING SWAB #2 MUD PUMP.
RAINIER 1H | 10 | 2021-05-17 13:00 | 2021-05-17 14:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.88 | 10524 | 10650 | 126 | ROT (126' IN .78 HRS @ 161.54 FPH) WOB: 20/30K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ:14K/23K, SPP:5600/5800 PSI, DIFF: 300/600 PSI. NOTE: ENCOUNTERING LOSSES @ 13 BPH, ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND.
RAINIER 1H | 10 | 2021-05-17 14:00 | 2021-05-17 15:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.92 | 10650 | 10669 | 19 | SLIDE (19' IN 1.22 HRS @ 15.57 FPH) WOB: 20/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 5300/5500 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10570 T/10580 10' TF-30R 1321-1409 SLD F/10660 T/10669 9' TF-30R 1435-1500
RAINIER 1H | 10 | 2021-05-17 15:00 | 2021-05-17 16:00 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 4.96 | 10669 | 10769 | 100 | ROT (100' IN .82 HRS @ 122 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-50, TRPM: 161, TRQ: 13K/21K, SPP: 3500/4100 PSI, DIFF: 300/600 PSI. NOTE: ENCOUNTERING LOSSES @ 13 BPH, ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS). NOTE: CRANE OPERATOR AND MECHANIC ARRIVED AND STARTED REMOVING TRACTION MOTORS OFF #2 MUD PUMP @ 19:00.
RAINIER 1H | 10 | 2021-05-17 16:00 | 2021-05-17 19:30 | 3.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 5.1 | 10769 | 10841 | 20.6 | SLIDE (72' IN 3.68 HRS @ 19.6 FPH) WOB: 35/45K, SPM: 105/105, GPM: 674, MMRPM: 111, SPP:3500/3800 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/10755 T/10784 29' TF-60R 1703-1824 SLD F/10804 T/10820 16' TF-60R 1832-1920 NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS)
RAINIER 1H | 10 | 2021-05-17 19:30 | 2021-05-17 20:00 | 0.5 | P | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.13 | 10841 | 10841 | 0 | PUMP 10 BBL LCM SWEEP, CIRCULATE AND RECIPROCATE PIPE TO AID IN SLIDING ROP, GPM: 674, RPM-80, , TRQ: 7K/12K, SPP: 3500 PSI. NOTE: STARTING SPP: 3800 PSI AND TRQ: 8K/18K, ENDING SPP: 3500 PSI AND TRQ: 7K/13K.
RAINIER 1H | 10 | 2021-05-17 20:00 | 2021-05-17 20:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.15 | 10841 | 10935 | 188 | ROT (94' IN .5 HRS @ 188 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-50, TRPM: 161, TRQ: 13K/21K, SPP: 3500/4300 PSI, DIFF: 500/700 PSI. NOTE: ENCOUNTERING LOSSES @ 13 BPH, ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS).
RAINIER 1H | 10 | 2021-05-17 20:30 | 2021-05-17 21:00 | 0.5 | P | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.17 | 10935 | 10935 | 0 | PUMP 10 BBL LCM SWEEP, CIRCULATE AND RECIPROCATE PIPE TO AID IN SLIDING ROP, GPM: 674, RPM-80, , TRQ: 7K/11K, SPP: 3500 PSI. NOTE: STARTING SPP: 3600 PSI AND TRQ: 7K/14K, ENDING SPP: 3500 PSI AND TRQ: 7K/11K.
RAINIER 1H | 10 | 2021-05-17 21:00 | 2021-05-17 23:00 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.25 | 10935 | 11197 | 131 | ROT (262' IN 1.97 HRS @ 133 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 13K/23K, SPP: 3500/4400 PSI, DIFF: 600/800 PSI. NOTE: LOSSES DECREASED F/13 BPH T/3-5 BPH, ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS). NOTE: TRACTION MOTORS ARRIVED @ 23:45, STARTED INSTALLING NEW TRACTION MOTORS ON #2 MUD PUMP @ 23:45.
RAINIER 1H | 10 | 2021-05-17 23:00 | 2021-05-18 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.29 | 11197 | 11217 | 20 | SLIDE (20' IN 1.03 HRS @ 19.4 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, SPP: 3500/3800 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/11135 T/11155 20' TF-120R 2224-2326 NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS)
RAINIER 1H | 10 | 2021-05-18 | 2021-05-18 00:30 | 0.5 | P | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.31 | 11217 | 11217 | 0 | PUMP 10 BBL LCM SWEEP, CIRCULATE AND RECIPROCATE PIPE TO AID IN SLIDING ROP, GPM: 674, RPM-80, , TRQ: 7K/11K, SPP: 3500 PSI. NOTE: STARTING SPP: 3600 PSI AND TRQ: 11K/15K, ENDING SPP: 3500 PSI AND TRQ: 7K/11K.
RAINIER 1H | 10 | 2021-05-18 00:30 | 2021-05-18 02:00 | 1.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.38 | 11217 | 11339 | 81.3 | ROT (122' IN 1.78 HRS @ 68.5 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 111, RPM-80, TRPM: 191, TRQ: 13K/23K, SPP: 3500/4400 PSI, DIFF: 600/800 PSI. NOTE: ENCOUNTERING LOSSES @ 3-5 BPH, ADDING 5 SXS/HR FIRST RESPONSE AND 5 SXS/HR NEW CARB TO THE ACTIVE SYSTEM. NOTE: BACK REAM STAND PRIOR TO EACH CONNECTION, PUMPING 10 BBL SWEEP EVERY STAND. NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS).
RAINIER 1H | 10 | 2021-05-18 02:00 | 2021-05-18 06:00 | 4 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.54 | 11339 | 11419 | 20 | SLIDE (80' IN 4.15 HRS @ 19.3 FPH) WOB: 35/45K, SPM: 105/105, GPM: 674, MMRPM: 111, SPP: 3500/3800 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/11228 T/11244 16' TF-140R 0012-0115 SLD F/11264 T/11290 26' TF-150R 0127-0210 SLD F/11327 T/11365 38' TF-150R 0231-0454 NOTE: DRILLING WITH #1 AND #3 MUD PUMPS DUE TO ELECTRICAL ISSUES WITH #2 MUD PUMP. (LIGHTING STRUCK MUD DAMAGING BOTH TRACTION MOTORS)
RAINIER 1H | 11 | 2021-05-18 06:00 | 2021-05-18 08:00 | 2 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 5.63 | 11419 | 11499 | 40 | ROT (80' IN 1.72 HRS @ 47 FPH) WOB: 20K/30K, SPM: 110/110, GPM: 706, MMRPM: 117, RPM-80, TRPM: 197, TRQ: 15K/25K, SPP: 4000/4200 PSI, DIFF: 300/500 PSI. NOTE: DRILLING W/2 MUD PUMPS @ 700 GPM; CONTROL DRILL @ 120 FPH FOR DIRECTIONAL CONTROL.
RAINIER 1H | 11 | 2021-05-18 08:00 | 2021-05-18 12:00 | 4 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 5.79 | 11499 | 11560 | 15.2 | SLIDE (61' IN 4.28 HRS @ 14 FPH) WOB: 20/25K, SPM: 110/110, GPM: 706, MRPM: 117, SPP: 3800/4100 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10419' T/10430' 11' TF-130M 0600-0650 SLD F/10468' T/10488' 20' TF-130M 0714-0911 SLD F/11510' T/11540' 30' TF-130M 0939-1109 NOTE: DRILLING W/2 MUD PUMPS @ 700 GPM
RAINIER 1H | 11 | 2021-05-18 12:00 | 2021-05-18 13:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.83 | 11560 | 11680 | 120 | ROT (120' IN 1.18 HRS @ 102 FPH) WOB: 20K/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, RPM-80, TRPM: 224, TRQ: 15K/22K, SPP: 5100/5700 PSI, DIFF: 300/500 PSI.
RAINIER 1H | 11 | 2021-05-18 13:00 | 2021-05-18 14:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.88 | 11680 | 11700 | 20 | SLIDE (61' IN 4.28 HRS @ 14 FPH) WOB: 20/25K, SPM: 90/90/90, GPM: 866, MRPM: 144, SPP: 5100/5400 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/11663' T/11683' TF-150M 1251-1340
RAINIER 1H | 11 | 2021-05-18 14:00 | 2021-05-18 17:30 | 3.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.02 | 11700 | 11778 | 22.3 | STARTED BUILDING INT. CURVE ON 5/18/21 @ 14:00 (11,700' MD / 11,511' TVD) BUILD CURVE/SLD (78' IN 3.5 HRS @ 22 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 100/200 PSI. NOTE: PUMPING SWEEPS 10BBL PER STAND: 5 LB/BBL OF NEW CARB, 5 LB/BBL OF NEW PHAULT, 2.5 LB/BBL OF MAGMA FIBER, 6 LB/BBL OF GRAPHITE
RAINIER 1H | 11 | 2021-05-18 17:30 | 2021-05-18 18:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.04 | 11778 | 11778 | 0 | RIG SERVICE, SERVICE TOP DRIVE AND BLOCK.
RAINIER 1H | 11 | 2021-05-18 18:00 | 2021-05-18 19:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.1 | 11778 | 11802 | 16 | SLIDE (24' IN 1.5 HRS @ 16 FPH) WOB: 20/40K, SPM: 90/90/90, GPM: 866, MRPM: 144, SPP: 5100/5200 PSI, DIFF: 50/100 PSI. SLIDE DEPTHS: SLD F/11778 T/11802 24' TF-45R 1800-1930 NOTE: BACK REAM EACH STAND PRIOR TO CONNECTION. NOTE: PUMP 10 BBLS OF 6 PPB GRAPHITE SWEEP EVERY HOUR.
RAINIER 1H | 11 | 2021-05-18 19:30 | 2021-05-18 20:30 | 1 | U | INTHL | WAIT | WOW | WAIT ON WEATHER | 6.15 | 11802 | 11802 | 0 | SPACE OUT, SHUT WELL IN, HAVE RIG PERSONNEL REPORT TO SAFETY MEETING HOUSE, WAIT ON WEATHER DUE TO SEVERE WEATHER CONDITIONS DUE TO TORANDO WARNINGS.
RAINIER 1H | 11 | 2021-05-18 20:30 | 2021-05-18 21:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.17 | 11802 | 11807 | 10 | SLIDE (5' IN .5 HRS @ 10 FPH) WOB: 20/40K, SPM: 90/90/90, GPM: 866, MRPM: 144, SPP: 5100/5300 PSI, DIFF: 50/150 PSI. SLIDE DEPTHS: SLD F/11802 T/11807 5' TF-45R 1800-1930 NOTE: BACK REAM EACH STAND PRIOR TO CONNECTION. NOTE: PUMP 10 BBLS OF 6 PPB GRAPHITE SWEEP EVERY HOUR.
RAINIER 1H | 11 | 2021-05-18 21:00 | 2021-05-18 21:30 | 0.5 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 6.19 | 11807 | 11807 | 0 | WORK DRILL STRING WHILE CHANGING SWAB IN #2 MUD PUMP, NOT ABLE TO CONTINUE WITH DRILLING OPERATIONS WITH #1 AND #3 MUD PUMPS DUE TO 4" DISCHARGE VALVE ON #2 MUD PUMP WASHED OUT AND NOT ABLE TO ISOLATE #2 MUD PUMP TO CONTINUE DRILLING OPERATIONS.
RAINIER 1H | 11 | 2021-05-18 21:30 | 2021-05-18 22:30 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.23 | 11807 | 11864 | 57 | ROT (57' IN .85 HRS @ 67.06 FPH) WOB: 25K/35K, SPM: 90/90/90, GPM: 866, MMRPM: 144, RPM-30, TRPM: 174, TRQ: 15K/22K, SPP: 5500/5800 PSI, DIFF: 300/600 PSI. NOTE: BACK REAM EACH STAND PRIOR TO CONNECTION. NOTE: PUMP 10 BBLS OF 6 PPB GRAPHITE SWEEP EVERY HOUR.
RAINIER 1H | 11 | 2021-05-18 22:30 | 2021-05-19 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.29 | 11864 | 11881 | 11.3 | SLIDE (17' IN 1.53 HRS @ 11.1 FPH) WOB: 20/40K, SPM: 90/90/90, GPM: 866, MRPM: 144, SPP: 5100/5300 PSI, DIFF: 50/150 PSI. SLIDE DEPTHS: SLD F/11807 T/11815 8' TF-45R 2130-2227 SLD F/11872 T/11881 9' TF-HS 2318-2353 NOTE: BACK REAM EACH STAND PRIOR TO CONNECTION. NOTE: PUMP 10 BBLS OF 6 PPB GRAPHITE SWEEP EVERY HOUR.
RAINIER 1H | 11 | 2021-05-19 | 2021-05-19 00:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 6.31 | 11881 | 11926 | 90 | ROT (45' IN .62 HRS @ 72.6 FPH) WOB: 30/40K, SPM: 110/110, GPM: 705, MMRPM: 117, RPM-30, TRPM: 147, TRQ: 14K/22K, SPP: 3600/4500 PSI, DIFF: 700/900 PSI. NOTE: DRILLING WITH #2 AND #3 MUD PUMPS WHILE CHANGING SWAB #1 MUD PUMP.
RAINIER 1H | 11 | 2021-05-19 00:30 | 2021-05-19 03:30 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.44 | 11926 | 11971 | 15 | SLIDE (45' IN 2.88 HRS @ 15.61 FPH) WOB: 20/30K, SPM: 90/90/90, GPM: 866, MRPM: 144, SPP: 5100/5300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/11926 T/11971 45' TF-HS 0030-0323 NOTE: BACK REAM EACH STAND PRIOR TO CONNECTION. NOTE: PUMP 10 BBLS OF 6 PPB GRAPHITE SWEEP EVERY HOUR.
RAINIER 1H | 11 | 2021-05-19 03:30 | 2021-05-19 04:00 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 6.46 | 11971 | 11982 | 22 | SLIDE (11' IN .62 HRS @ 17.84 FPH) WOB: 20/30K, SPM: 110/110, GPM: 705, MMRPM: 117, SPP: 3600/3800 PSI, DIFF: 100/200 PSI.. SLIDE DEPTHS: SLD F/11971 T/11982 11' TF-HS 0323-0400 NOTE: DRILLING WITH #1 AND #2 MUD PUMPS WHILE CHANGING LINER GASKET #3 MUD PUMP.
RAINIER 1H | 11 | 2021-05-19 04:00 | 2021-05-19 04:30 | 0.5 | U | INTHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 6.48 | 11982 | 11982 | 0 | ROTATE STARTED LEAKING REMOVE ROTATING HEAD, OBSERVED NO CRACKS OR VISIBLE WEAR, INSTALLED NEW ROTATING HEAD.
RAINIER 1H | 11 | 2021-05-19 04:30 | 2021-05-19 05:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.5 | 11982 | 11985 | 6 | SLIDE (3' IN .5 HRS @ 6 FPH) WOB: 20/30K, SPM: 90/90/90, GPM: 866, MRPM: 144, SPP: 5100/5300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/11982 T/11985 3' TF-HS 0430-0500 TD INTERMEDIATE SECTION ON 5/19/2021 @ 05:00 (11,985' MD / 11,795' TVD) NOTE: BACK REAM EACH STAND PRIOR TO CONNECTION. NOTE: PUMP 10 BBLS OF 6 PPB GRAPHITE SWEEP EVERY HOUR.
RAINIER 1H | 11 | 2021-05-19 05:00 | 2021-05-19 06:00 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.54 | 11985 | 11985 | 0 | PERFORMED CLEAN UP CYCLE PUMPING 2-30 BBL SWEEPS SURFACE TO SURFACE TO CLEAN HOLE & PREP OPEN HOLE FOR 7-5/8" CASING. GPM-866, SPP-5100, RPM-80, TQ=9/13K.
RAINIER 1H | 12 | 2021-05-19 06:00 | 2021-05-19 07:00 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.58 | 11985 | 11985 | 0 | CONTINUE CLEAN UP CYCLE PUMPING 2-30 BBL SWEEPS SURFACE TO SURFACE TO CLEAN HOLE & PREP OPEN HOLE FOR 7-5/8" CASING. GPM-866, SPP-5100, RPM-80, TQ=9/13K, SHAKERS CLEAN.
RAINIER 1H | 12 | 2021-05-19 07:00 | 2021-05-19 13:00 | 6 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 6.83 | 11985 | 11985 | 0 | LAY DOWN DRILL PIPE F/11,404' T/3,000'. HOLE TAKING EXCESS FILL DURING TRIP OUT; CALCULATED FILL 3.9 BBLS PER 5 STD/AVERAGE HOLE FILL 5.1 BBLS PER 5 STDS; NO EXCESS PULL WHILE TRIPPING OUT.
RAINIER 1H | 12 | 2021-05-19 13:00 | 2021-05-19 13:30 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 6.85 | 11985 | 11985 | 0 | PERFORM FLOW CHECK-NO FLOW. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
RAINIER 1H | 12 | 2021-05-19 13:30 | 2021-05-19 16:00 | 2.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 6.96 | 11985 | 11985 | 0 | LAY DOWN 5” DRILL PIPE F/3,000’ T/2,000'; TRIP IN HOLE 6 STANDS FROM DERRICK T/2,500'; L/D DP F/2,500' T/BHA; HOLE TAKING AVERAGE OF 5.1 BBL PER 5 STD ON TRIP OUT.
RAINIER 1H | 12 | 2021-05-19 16:00 | 2021-05-19 19:00 | 3 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 7.08 | 11985 | 11985 | 0 | LAY DOWN BHA AND DIRECTIONAL BHA; L/D 9 JTS OF HWDP, X-OVER SUB, 6 JTS OF 6.5" DC, X-OVER SUB, 2 NMDC, UBHO SUB, NMPC, MUD MOTOR, AND BIT; BIT MISSING CUTTER ON NOSE, MISSING HALF A CUTTER ON GUAGE, AND HAD 3 PLUGGED JETS; MUD MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG
RAINIER 1H | 12 | 2021-05-19 19:00 | 2021-05-19 19:30 | 0.5 | P | INTHLCSG | SFTY | INSPT | SAFETY INSPECTION | 7.1 | 11985 | 11985 | 0 | CLEAN OBM FROM RIG FLOOR TO REDUCE SLIP HAZARDS AND PULL WEAR BUSHING, COMPANY REPRESENTIVE WITNESS.
RAINIER 1H | 12 | 2021-05-19 19:30 | 2021-05-19 21:00 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 7.17 | 11985 | 11985 | 0 | HOLD PJSM AND RIG UP BUTCH'S RAT HOLE CASING CREWS TOOLS & EQUIPMENT.
RAINIER 1H | 12 | 2021-05-19 21:00 | 2021-05-19 21:30 | 0.5 | U | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.19 | 11985 | 11985 | 0 | REPLACE CONTROL SWITCH IN REMOTE PANEL FOR PIPE WRANGLER
RAINIER 1H | 12 | 2021-05-19 21:30 | 2021-05-19 23:00 | 1.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 7.25 | 11985 | 11985 | 0 | HELD PJSM, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 20 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG T/ 1,112', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FREE FLOATING), AND INSTALLED LATCH ON BOW SPRING CENTRALIZER @ 10,857' AND EVERY 4TH JT.
RAINIER 1H | 12 | 2021-05-19 23:00 | 2021-05-19 23:30 | 0.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 7.27 | 11985 | 11985 | 0 | TROUBLE SHOOT ELECTRICAL WIRING IN REMOTE CONTROL PANEL FOR PIPE WRANGLER.
RAINIER 1H | 12 | 2021-05-19 23:30 | 2021-05-20 06:00 | 6.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 7.54 | 11985 | 11985 | 0 | CONTINUE PICKING UP AND RUNNING 7 5/8" 29.7# P-110 HC ERW BTC CSG F/ 1,112' T/8,550', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT. NOTE: PATTERSON MECHANIC INSPECTING RUN OUT ON #1 AND #2 MUD PUMPS, CHANGING OUT 4" VALVE ON #2 MUD PUMP, CHANGING OUT 5 1/4" LINERS AND SWABS TO 4 3/4" LINERS AND SWABS, CHANGING OUT ALL VALVES AND SEATS ON ALL 3 MUD PUMPS WHILE RUNNING INTERMEDIATE CSG.
RAINIER 1H | 13 | 2021-05-20 06:00 | 2021-05-20 08:30 | 2.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 7.65 | 11985 | 11985 | 0 | CONTINUE PICKING UP AND RUNNING 7 5/8" 29.7# P-110 HC ERW BTC CSG F/ 8,550' T/11,974.5', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT,RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TEST FLOATS, THEN RAN 251 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-7 5/8" 29.7# P-110 HC ERW BTC PUP JOINT, 2 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, TOTAL OF 256 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (FREE FLOATING), AND INSTALLED 54 LATCH ON BOW SPRING CENTRALIZERS @ 10,857' AND EVERY 4TH JT UP TO 1,819'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/220K (W/O BLOCKS) FLOAT SHOE-11,974.5' TOP OF FLOAT COLLAR-11,878.6' 9 JOINTS LEFT OUT- 414.787'
RAINIER 1H | 13 | 2021-05-20 08:30 | 2021-05-20 09:00 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 7.67 | 11985 | 11985 | 0 | RIG DOWN BUTCH'S CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
RAINIER 1H | 13 | 2021-05-20 09:00 | 2021-05-20 10:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.73 | 11985 | 11985 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE CASING TOOLS, SPM: 64/64, 8.0 BPM, SPP: 500 PSI, NO LOSSES.
RAINIER 1H | 13 | 2021-05-20 10:30 | 2021-05-20 17:00 | 6.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 8 | 11985 | 11985 | 0 | PJSM, SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/5000 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 418 BBL 11.8 PPG 860 SK 2.73 YIELD 50/50 POZ-HW-STX-CLASS H LEAD CEMENT, 80 BBL 16.2 PPG 310 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 546 BBLS OF 10.0 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1630 PSI AT 3 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/2130 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI (4.5 BBLS)-FLOATS HELD. FINISHED CEMENTING @ 16:30 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. 40 BBLS SPACER AND 39 BBLS CEMENT BACK TO SURFACE. NOTE: AFTER PUMPING 40 BBL OF SPACER CEMENTERS BEGAN MIXING LEAD CEMENT. MIXING BLENDER IMMEDIATELY PACKED OFF AND WAS NOT ABLE TO BEGIN PUMPING LEAD CEMENT; AFTER UNSTOPPING BLENDER PORT, BEGAN PUMPING LEAD CEMENT; AFTER PUMPING APPROXIMATELY 350 BBL OF CEMENT THE PLC FOR THE PUMP TRUCK BEGAN TO MALFUNCTION. ATTEMPTED TO REBOOT THE SCREEN AND PROCEED APPOX. 5 TIMES. AFTER IT WAS DETERMINED THAT SCREEN WAS NOT GOING TO WORK PROPERLY THE DECISION WAS MADE TO PUMP THE REMAINING 68 BBLS OF LEAD AND 80 BBLS OF TAIL WHILE REGULATING CEMENT/WATER MIXTURE MANUALLY AND WEIGHING WITH A PRESSURIZED SCALE. AFTER PUMPING THE LEAD AND TAIL, THE MIXING BLENDER PACKED OF WITH TAIL CEMENT DURING THE LAST 10 BBLS PUMPED. ALSO, DURING THE CEMENT JOB THERE WHERE MECHANICAL ISSUES WITH THE BOOSTER PUMP AND THE COMPRESSOR POP OFF VALVE.
RAINIER 1H | 13 | 2021-05-20 17:00 | 2021-05-20 17:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 8.02 | 11985 | 11985 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD.
RAINIER 1H | 13 | 2021-05-20 17:30 | 2021-05-20 18:30 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 8.06 | 11985 | 11985 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
RAINIER 1H | 13 | 2021-05-20 18:30 | 2021-05-20 21:30 | 3 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 8.19 | 11985 | 11985 | 0 | FLUSH THROUGH BOP AND FLOW LINE WITH WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 40K, BROKE OUT & LAID DOWN SETTING TOOL.
RAINIER 1H | 13 | 2021-05-20 21:30 | 2021-05-20 22:00 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 8.21 | 11985 | 11985 | 0 | INSTALL WEAR BUSHING, CLOSE CASING VALVE AND CLOSE CELLAR COVERS.
RAINIER 1H | 13 | 2021-05-20 22:00 | 2021-05-20 23:00 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 8.25 | 11985 | 11985 | 0 | REMOVE 4.5" IF SAVER SUB AND INSTALL DS42 SAVER SUB, PICK UP 4.5" HANDLING EQUIPMENT.
RAINIER 1H | 13 | 2021-05-20 23:00 | 2021-05-20 23:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.27 | 11985 | 11985 | 0 | SERVICE TOP DRIVE, ST-80 AND DRAW WORKS.
RAINIER 1H | 13 | 2021-05-20 23:30 | 2021-05-21 01:00 | 1.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 8.33 | 11985 | 11985 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13590860 JETS 6/18S TFA: 1.491), 5", 6/7L, 11.7 STG @ 2.00° SLICK; .89 REV/GAL; 4.05' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,905 PSI; STALL TRQ-7623 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, TOMAX THRUSTER, X/O XT-39 P x DS 42B, 2 STANDS DP, REAMER, 26 STANDS, AGITATOR, 33 STANDS, ON DEMAND AGITATOR. BIT TO SVY-64'. BIT TO GAMMA-54'. TEST MWD (TEST GOOD).
RAINIER 1H | 13 | 2021-05-21 01:00 | 2021-05-21 06:00 | 5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 8.54 | 11985 | 11985 | 0 | PICK UP AND TRIP IN THE HOLE WITH 4.5" DRILL PIPE F/BHA T/5,500', PICK UP AGITATOR AFTER STAND 28, BEFORE AGITATOR: GPM-275, SPM-105, BEFORE AGITATOR: SPP-1250 PSI; AFTER AGITATOR: SPP-1570 PSI, FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT.
RAINIER 1H | 14 | 2021-05-21 06:00 | 2021-05-21 11:30 | 5.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 8.77 | 11985 | 11985 | 0 | CONTINUE PICKING UP AND TRIPPING IN THE HOLE F/5,550' T/11,679', PICK UP ON DEMAND AGITATOR AFTER STAND 61 @ 5,973' (33 STANDS), BEFORE AGITATOR: GPM-262, SPM-100, SPP-1840 PSI; AFTER AGITATOR: SPP- 1960 PSI, FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT.
RAINIER 1H | 14 | 2021-05-21 11:30 | 2021-05-21 12:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 8.79 | 11985 | 11985 | 0 | REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD.
RAINIER 1H | 14 | 2021-05-21 12:00 | 2021-05-21 13:30 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 8.85 | 11985 | 11985 | 0 | SLIP AND CUT 80' OF DRILL LINE.
RAINIER 1H | 14 | 2021-05-21 13:30 | 2021-05-21 14:00 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 8.88 | 11985 | 11985 | 0 | CONTINUE PICKING UP AND TRIPPING IN THE HOLE F/11,679' T/11,878', PERFORM BOP DRILL RESPONSE TIME= 40 SECONDS; FILL GAS SEPARATOR.
RAINIER 1H | 14 | 2021-05-21 14:00 | 2021-05-21 15:00 | 1 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 8.92 | 11985 | 11985 | 0 | TAGGED FLOAT COLLAR @ 11,878', DRILL FLOAT COLLAR AND SHOE TRACK TO 11,972', GPM-192, SPP-1900/2000 PSI, RPM-30, TRQ-15/17K MRPM-171, TRPM-201, DIFF-100-200 PSI.
RAINIER 1H | 14 | 2021-05-21 15:00 | 2021-05-21 15:30 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.94 | 11985 | 11985 | 0 | CIRCULATE BOTTOMS UP @ 11,972', TO VERIFY GOOD CEMENT JOB (GOOD SAMPLE) GPM-200, SPP-1800 PSI, RPM-30, TRQ 15-18K.
RAINIER 1H | 14 | 2021-05-21 15:30 | 2021-05-21 16:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.98 | 11985 | 11995 | 10 | DRILL SHOE AND 10' OF NEW FORMATION F/11,985' T/11,995', GPM-192, SPP-1900/2000 PSI, RPM-30, TRQ-15/17K MRPM-171, TRPM-201, DIFF-100-200 PSI
RAINIER 1H | 14 | 2021-05-21 16:30 | 2021-05-21 17:00 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9 | 11995 | 11995 | 0 | CIRCULATE BOTTOMS UP BEFORE PERFORM F.I.T., GPM-300, SPP-3400 PSI, RPM-30, TRQ 15-18K.
RAINIER 1H | 14 | 2021-05-21 17:00 | 2021-05-21 17:30 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.02 | 11995 | 11995 | 0 | PERFORM F.I.T. WITH 9.9 PPG MUD, 1896 PSI SURFACE PRESSURE FOR 13.0 PPG EMW, SHOE MD-11,974' / TVD-11,674'. AFTER REACHING 1896 PSI THE PRESSURE BLED OFF T/1700 PSI AND STABILIZED. PRESSURE BLED OFF F/1700 PSI T/1660 PSI IN 5 MINUTES. GOOD F.I.T. TEST TO 12.6 PPG EMW.
RAINIER 1H | 14 | 2021-05-21 17:30 | 2021-05-21 17:30 | 0 | P | INTHLCSG | MSTN | SCRV | MILESTONE_START CURVE SECTION | 9.02 | 11995 | 11995 |  | MILESTONE_START CURVE ON 5-21-2021 @ 17:30 HRS
RAINIER 1H | 14 | 2021-05-21 17:30 | 2021-05-22 04:00 | 10.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.46 | 11995 | 12523 | 50.3 | BUILD CURVE-SLIDE (528' IN 10.5 HRS @ 50.3 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-356, SPP-5000/5700 PSI, DIFF-500/700 PSI, CHOKES- 100% / 100%, FLARE-3-5', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/11995' T/12523' 528' TF-HS 1730-0400. NOTE: OBSERVED A FLOW INCREASE F/20% T/26% AND GAINED 10 BBLS @ 12,523'.
RAINIER 1H | 14 | 2021-05-22 04:00 | 2021-05-22 05:00 | 1 | P | PRDHLCV | WCTRL | KWELL | KILL WELL | 9.5 | 12523 | 12523 | 0 | PICK UP AND SPACE OUT, SHUT TOP RAMS, CIRCULATE OUT GAS AND WEIGHT UP F/9.7 PPG T/10.0 PPG, SPM-76/76, GPM-400, SPP-5100/5400 PSI, CHOKES- 35-38% / 0%, FLARE-25-35', MUD CUT F/9.7 PPG T/9.1 PPG, MAX CASING PRESSURE= 1200 PSI, AVG CASING PRESSURE= 840 PSI, MAX GAS-2766u, FINAL CASING PRESSURE= 300 PSI, OPEN TOP RAMS.
RAINIER 1H | 14 | 2021-05-22 05:00 | 2021-05-22 06:00 | 1 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.54 | 12523 | 12534 | 11 | BUILD CURVE-SLIDE (11' IN 1 HR @ 11 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-356, SPP-5000/5700 PSI, DIFF-500/700 PSI, CHOKES- 47-50% / 0%, FLARE-3'-5', NO MUD CUT, MAX CASING PRESSURE= 383 PSI, AVG CASING PRESSURE= 335 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 850 PSI, SLIDE DEPTHS: SLD F/12523' T/12534' 11' TF-HS 0500-0600. NOTE: WEIGHTING UP F/10.0 PPG T/10.2 PPG.
RAINIER 1H | 15 | 2021-05-22 06:00 | 2021-05-22 06:30 | 0.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.56 | 12534 | 12540 | 12 | BUILD CURVE-SLIDE (6' IN .5 HR @ 12 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-356, SPP-5000/5700 PSI, DIFF-500/700 PSI, CHOKES- 47-50% / 0%, FLARE-5'-10', MUD CUT F/10.2 PPG T/10.0 PPG, MAX CASING PRESSURE= 587 PSI, AVG CASING PRESSURE= 430 PSI. SLIDE DEPTHS: SLD F/12534' T/12540' 6' TF-HS 0600-0630 NOTE: DECISION WAS MADE TRIP OUT THE HOLE FOR 2.5 DEG BAIL OUT MOTOR DUE TO BEING 40' BEHIND. NOTE: HOLE PACKED OFF SPP INCREASED F/5400 PSI T/7000 PSI, TORQUE STALLED OUT @ 22K.
RAINIER 1H | 15 | 2021-05-22 06:30 | 2021-05-22 10:30 | 4 | U | PRDHLCV | WCTRL | KWELL | KILL WELL | 9.73 | 12540 | 12540 | 0 | CIRCULATE AND WORK PIPE FREE OF PACK OFF, CIRCULATE OUT GAS, RECIPROCATE PIPE AND RAISE MUD WEIGHT F/10.2 PPG T/10.5 PPG, HOLE ATTEMPTED TO PACK OFF, SPP INCREASED F/4300 PSI T/5300 AND TORQUE INCREASED F/15/18K T/16/20K, BACK REAM OUT THE HOLE F/12,540' T/12430', CONTINUE CIRCULATING OUT GAS, RECIPROCATE PIPE AND WEIGHT F/10.5 PPG T/10.7 PPG, SPM-70/70, GPM-367, SPP-3900/4100 PSI, RPM-30, TRQ-15K/17K CHOKES- 41-45% / 0%, FLARE-20-30', MAX CASING PRESSURE= 915 PSI, AVG CASING PRESSURE= 520 PSI, MAX GAS-2680u, FINAL CASING PRESSURE= 422 PSI.
RAINIER 1H | 15 | 2021-05-22 10:30 | 2021-05-22 13:00 | 2.5 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.83 | 12540 | 12540 | 0 | SHUT IN AND MONITORED SHUT IN CASING PRESSURE, SICP= 1000 PSI, BUMPED FLOAT TO MONITOR SIDP, SIDP= 420 PSI AND SIDP STILL INCREASING,, CIRCULATE OUT GAS, RECIPROCATE PIPE AND RAISE MUD WEIGHT F/10.7 PPG T/11.0 PPG,, SPM-70/70, GPM-367, SPP-3900/4100 PSI, RPM-30, TRQ-12K/14K CHOKES- 41-45% / 0%, FLARE-2'-4', MAX CASING PRESSURE= 605 PSI, AVG CASING PRESSURE= 350 PSI, MAX GAS-1565u, FINAL CASING PRESSURE= 262 PSI, ENDING GAS- 785u, SHUT IN AND MONITOR SHUT IN CASING PRESSURE, SICP= 850 PSI.
RAINIER 1H | 15 | 2021-05-22 13:00 | 2021-05-22 13:30 | 0.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 9.85 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/12,430’ T/12,057’ WITH WET PIPE, PUMPING CALCULATED HOLE FILL 1.9 BBLS PER STAND DOWN THE BACKSIDE W/11.0 PPG OBM, MAX CASING PRESSURE= 952 PSI, AVG CASING PRESSURE= 885 PSI.
RAINIER 1H | 15 | 2021-05-22 13:30 | 2021-05-22 14:30 | 1 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.9 | 12540 | 12540 | 0 | CIRCULATE BOTTOMS UP, RECIPROCATE PIPE, SPM-76/76, GPM-400, SPP-4400 PSI, RPM-30, TRQ-10K/12K, CHOKES- 42-45% / 0%, FLARE-1'-2', MAX CASING PRESSURE= 183 PSI, AVG CASING PRESSURE= 140 PSI, MAX GAS-624u, FINAL CASING PRESSURE= 160 PSI. SHUT IN AND MONITORED SHUT IN CASING PRESSURE, SICP= 775 PSI.
RAINIER 1H | 15 | 2021-05-22 14:30 | 2021-05-22 17:00 | 2.5 | U | PRDHLCV | WCTRL | KWELL | KILL WELL | 10 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/12,057’ T/11,700’ WITH WET PIPE, PUMPING CALCULATED HOLE FILL 1.9 BBLS PER STAND DOWN THE BACKSIDE W/11.0 PPG PPG OBM, SPOT 143 BBL 16.5 PPG OBM MUD CAP @ 11,700' (200 PSI OVER BALANCE MUD CAP). SHUT IN AND MONITORED CASING PRESSURE. SICP BEFORE MUD CAP= 800 PSI / AFTER-120 PSI. TOP OF MUD CAP-8,600'
RAINIER 1H | 15 | 2021-05-22 17:00 | 2021-05-22 18:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.04 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/11,700’ T/8,600’ WITH DRY PIPE, PUMPING CALCULATED HOLE FILL .6 BBLS PER STAND DOWN BACKSIDE W/16.5 PPG OBM UNTIL CSG PSI REDUCED TO 0 PSI. (PUMP TOTAL 23 BBLS 16.5 KILL MUD ON BACKSIDE)
RAINIER 1H | 15 | 2021-05-22 18:00 | 2021-05-22 19:30 | 1.5 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.1 | 12540 | 12540 | 0 | FLOW CHECK (WELL STATIC), PUMP SLUG (40 BBLS 15.0 PPG SLUG) AFTER PUMPING SLUG FLOW ACROSS SHAKERS NOT DECREASING, CLOSE ORBIT AND MONITOR SICP = 100 PSI, MONITOR SICP F/ 25 MINUTES, SICP DECREASED T/ 65 PSI, FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD, OPEN CHOKE F/ 1 MINUTE WITH PARTIAL RETURNS, CLOSE CHOKE SICP INCREASED T/ 47 PSI, OPEN F/ 1 MINUTE WITH PARITIAL RETURNS, CLOSE CHOKE SICP INCREASED T/ 42 PSI, OPEN CHOKE F/ 1 MINUTE WITH PARITIAL RETURNS, FLOWED BACK TOTAL .57 BBLS, CLOSE CHOKE AND MONITOR SICP, SICP = 0PSI, OPEN CHOKE AND MONITOR WELL F/ FLOW, NO FLOW, OPEN ORBIT VALVE AND MONITOR WELL ON TRIP TANK, INITIAL FLOW 4 BPH, FINAL FLOW 2 BPH AND DECREASING, FLOWED BACK TOTAL 1.54 BBLS.
RAINIER 1H | 15 | 2021-05-22 19:30 | 2021-05-22 20:00 | 0.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.13 | 12540 | 12540 | 0 | PULL OUT OF HOLE F/ 8,600' T/ 7,160' MONITORING HOLE FILLS ON TRIP TANK, WELL NOT TAKING PROPER HOLE FILLS, 5 STANDS .6 BBLS, 5 STANDS 1.52 BBLS, 5 STANDS 0 BBLS, CALCULATED HOLE FILL PER 5 STANDS 3.2 BBLS, TOTAL CALCULATED HOLE FILL F/ 15 STANDS 9.6 BBLS.
RAINIER 1H | 15 | 2021-05-22 20:00 | 2021-05-22 21:00 | 1 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.17 | 12540 | 12540 | 0 | CLOSE ORBIT VALVE AND MONITOR SICP, SICP = 0 PSI.
RAINIER 1H | 15 | 2021-05-22 21:00 | 2021-05-22 21:30 | 0.5 | U | PRDHLCV | TRIP | COND | TRIP TO CLEAN OR CONDITION HOLE | 10.19 | 12540 | 12540 | 0 | TRIP HOLE F/ 7,160 T/ 8,603', WELL NOT GIVING PROPER DISPLACEMENTS ON TRIP IN HOLE, 5 STANDS 5.5 BBLS, 5 STANDS 8.2 BBLS, 5 STANDS 7.4 BBLS, CALCULATED DISPLACEMENT PER 5 STANDS 9.3 BBLS.
RAINIER 1H | 15 | 2021-05-22 21:30 | 2021-05-23 | 2.5 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.29 | 12540 | 12540 | 0 | CIRCULATE AND CONDITION MUD @ 8,541', RECIPROCATE @ 20 RPM AND WORK DRILL STRING F/ 8,509' T/ 8,541', INITIAL PUMP RATE 235 GPM WITH 1800 PSI, STARTED ENCOUNTING LOSSES, REDUCE PUMP RATE IN STAGES F/ 235 GPM 154 GPM TO REDUCE LOSSES TO FORMATION, TOTAL LOSSES TO FORMATION 32 BBLS, DIVERTED 99.5 BBLS TO OPEN TOP TANKS, MUD WEIGHT RANGE F/ 11.5 PPG T/ 13.1 PPG (23 BBLS 16.5 PPG KILL MUD PUMPED DOWN BACKSIDE AND 40 BBLS 15.0 PPG SLUG) CHOKE 100 % OPEN, FLARE 1'-3', MAX GAS WHILE CIRCULATING 283 UNITS. SHUT WELL IN AND MONITOR SICP, SICP = 190 PSI, SPOT 59 BBL 17.4 PPG MUD CAP, FINAL CASING PRESSURE = 0 PSI, ADDED 200 PSI SAFETY FACTOR FOR VOLIUME MUD CAP PUMPED, HYDROSTATIC PRESSURE BEFORE MUD CAP 6,992 PSI, HYDROSTATIC PRESSURE AFTER MUD CAP 7,367 PSI, TOP OF MUD CAP 7,322', BOTTOM OF MUD CAP 8,603',
RAINIER 1H | 15 | 2021-05-23 | 2021-05-23 00:30 | 0.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.31 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/ 8,603' T/ 7,265', PUMPING CALCULATED HOLE FILLS F/ DRY DRILL STRING, 10 STROKES (.6 BBLS) PER STAND DOWN BACKSIDE WITH 11.0 PPG OBM.
RAINIER 1H | 15 | 2021-05-23 00:30 | 2021-05-23 01:00 | 0.5 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.33 | 12540 | 12540 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC.
RAINIER 1H | 15 | 2021-05-23 01:00 | 2021-05-23 01:30 | 0.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.35 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/ 7,265' T/ 6,121', PUMPING CALCULATED HOLE FILLS F/ WET DRILL STRING, 30 STROKES (1.9 BBSL) PER STAND DOWN BACKSIDE WITH 11.0 PPG OBM.
RAINIER 1H | 15 | 2021-05-23 01:30 | 2021-05-23 02:00 | 0.5 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.38 | 12540 | 12540 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC, REMOVE ROTATING HEAD AND LAY DOWN ON DEMAND DRILLING AGITATOR, INSTALL ROTATING HEAD.
RAINIER 1H | 15 | 2021-05-23 02:00 | 2021-05-23 04:00 | 2 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.46 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/ 6,121' T/ 2,955', PUMPING CALCULATED HOLE FILLS F/ WET DRILL STRING, 30 STROKES (1.9 BBLS) PER STAND DOWN BACKSIDE WITH 11.0 PPG OBM.
RAINIER 1H | 15 | 2021-05-23 04:00 | 2021-05-23 05:00 | 1 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.5 | 12540 | 12540 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC, REMOVE ROTATING HEAD AND RACK BACK ON STANDARD DRILLING AGITATOR, INSTALL ROTATING HEAD.
RAINIER 1H | 15 | 2021-05-23 05:00 | 2021-05-23 06:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.54 | 12540 | 12540 | 0 | STRIP OUT OF HOLE F/ 2,955' T/ 176', PUMPING CALCULATED HOLE FILLS F/ WET DRILL STRING, 30 STROKES (1.9 BBLS) PER STAND DOWN BACKSIDE WITH 11.0 PPG OBM.
RAINIER 1H | 16 | 2021-05-23 06:00 | 2021-05-23 06:30 | 0.5 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 10.56 | 12540 | 12540 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE, L/D DRILLING REAMER.
RAINIER 1H | 16 | 2021-05-23 06:30 | 2021-05-23 08:00 | 1.5 | U | PRDHLCV | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.63 | 12540 | 12540 | 0 | FLOW CHECK @ BHA, NO FLOW, RACK BACK THRUSTER AND TOP MONEL, REMOVE MWD, L/D MOTOR. NOTE: OBSERVED THAT POWER SECTION OF MOTOR AND BIT WAS MISSING DUE TO POWER SECTION BACKING OUT OF MOTOR AND ROTAR TWISTING OFF AT ROTAR CATCH.
RAINIER 1H | 16 | 2021-05-23 08:00 | 2021-05-23 09:00 | 1 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.67 | 12540 | 12540 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAW WORKS
RAINIER 1H | 16 | 2021-05-23 09:00 | 2021-05-23 09:30 | 0.5 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 10.69 | 12540 | 12540 | 0 | GATHER NEW BIT AND BHA / P/U NEW ROTATING HEAD RUBBER TO FLOOR
RAINIER 1H | 16 | 2021-05-23 09:30 | 2021-05-23 11:00 | 1.5 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.75 | 12540 | 12540 | 0 | UNPLANNED RIG SERVICE - DERRICKMAN OBSERVED THE SALA BLOCK ON THE DERRICK RACKING BOARD WAS UNSAFE FOR USE; REPLACED SALA BLOCK ON THE RACKING BOARD WITH ANOTHER ONE.
RAINIER 1H | 16 | 2021-05-23 11:00 | 2021-05-23 12:00 | 1 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 10.79 | 12540 | 12540 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13090615 JETS 6/18S TFA: 1.491), 5", 7/8L, 3.8 STG @ 2.5° SLICK; .521 REV/GAL; 4.11' BIT TO BEND 5-1/4" PAD OD; FLOW RANGE- 150/250 GPM; MAX DIFF-860 PSI; STALL TRQ-7623 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX THRUSTER, X/O XT-39 P x DS 42B, 28 STANDS, AGITATOR. BIT TO SVY-61'. BIT TO GAMMA-48'. TEST, MWD (TEST GOOD) AND MAKE UP BIT.
RAINIER 1H | 16 | 2021-05-23 12:00 | 2021-05-23 13:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.83 | 12540 | 12540 | 0 | TRIP IN THE HOLE F/BHA T/2,868', PICK UP AGITATOR AFTER STAND 28; FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT
RAINIER 1H | 16 | 2021-05-23 13:00 | 2021-05-23 13:30 | 0.5 | U | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.85 | 12540 | 12540 | 0 | REMOVE TRIP NIPPLE, STRIP OLD ROTATING HEAD RUBBER FROM DRILL PIPE AND INSTALL NEW ROTATING HEAD RUBBER
RAINIER 1H | 16 | 2021-05-23 13:30 | 2021-05-23 16:00 | 2.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 10.96 | 12540 | 12540 | 0 | TRIP IN THE HOLE F/2,868' T/8,700' @ 150/180 FPM DUE TO HEAVY MW IN ANNULUS; FILL PIPE EVERY 40 STANDS, HOLE GIVING PROPER DISPLACEMENT
RAINIER 1H | 16 | 2021-05-23 16:00 | 2021-05-23 18:00 | 2 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.04 | 12540 | 12540 | 0 | CIRCULATE OUT MUD CAP @ 8,700', GPM-141, SPP-1,400, CHOKE 100 % OPEN, NO FLARE, MAX GAS WHILE CIRCULATING 117 UNITS. SHUT WELL IN AND MONITOR SICP, SICP = 218 PSI,TOTAL LOSSES TO FORMATION 10 BBLS, DIVERTED 70 BBLS TO OPEN TOP TANKS, MUD WEIGHT RANGE F/11.3 PPG T/ 13.3 PPG.
RAINIER 1H | 16 | 2021-05-23 18:00 | 2021-05-23 20:00 | 2 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 11.13 | 12540 | 12540 | 0 | STRIP IN HOLE F/ 8,700' T/ 12,000', BLEED OFF 1.9 BBLS PER STAND THROUGH CHOKE MANIFOLD T/ TRIP TANK, MAX CASING PRESSURE WHILE STRIPPING HOLE 400 PSI.
RAINIER 1H | 16 | 2021-05-23 20:00 | 2021-05-23 22:00 | 2 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.21 | 12540 | 12540 | 0 | FILL UP DRILL STRING, STAGE UP MUD PUMPS F/ 52 GPM T/ 150 GPM AND CIRCULATE OUT MUD CAP, CHOKE 100%, CASING PRESSURE= 0 PSI, MAX GAS=275 UNITS, FLARE=1'-3', LOSS 18 BBLS T/ FORMATION, DIVERTED 144 BBLS MUD CAP T/ OPEN TOP TANK, MUD WT RANGE F/ 11.8 PPG T/ 15.5 PPG, 400 PSI SHUT IN CASING PRESSURE DURING RE-CYCLE PROCESS PRIOR TO SIDETRACK OPERATIONS. NOTE: OBSERVED 3% FORMATION OIL ACROSS THE SHAKER WHILE CIRCULATING OUT MUD CAP.
RAINIER 1H | 16 | 2021-05-23 22:00 | 2021-05-23 22:30 | 0.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.23 | 12540 | 12540 | 0 | BUILD TROUGH F/11,974' T/11,990' @ 50L, GPM- 250, SPP-2700/3000 PSI, CHOKES- 38-42% / 0%, FLARE-1'-3', MUD CUT F/11.1 PPG T/10.6 PPG, MAX CASING PRESSURE= 722 PSI, AVG CASING PRESSURE= 550 PSI.
RAINIER 1H | 16 | 2021-05-23 22:30 | 2021-05-24 04:00 | 5.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.46 | 12540 | 12540 | 0 | BEGIN SIDETRACKING @ 11,990' MD / 11,7999' TVD ON 5/23/2021 @ 22:30. TIME DRILL @ 70L F/11,990' T/11,997' @ 1'/HR, WOB-4/10K, SPM-48/48, GPM-250, MRPM-130, SPP-2700/2900 PSI, DIFF-100/200 PSI, CHOKES- 38-42% / 0%, FLARE-3'-6', MUD CUT F/11.0 PPG T/10.7 PPG, MAX CASING PRESSURE= 668 PSI, AVG CASING PRESSURE= 500 PSI, MAX GAS=2344u.
RAINIER 1H | 16 | 2021-05-24 04:00 | 2021-05-24 06:00 | 2 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.54 | 12540 | 12540 | 0 | TIME DRILL @ 70L F/11,997' T/12,003' @ 3'/HR, WOB-4/10K, SPM-48/48, GPM-250, MRPM-130, SPP-2700/3000 PSI, DIFF-100/300 PSI, CHOKES- 38-42% / 0%, FLARE-3'-6', MUD CUT F/11.0 PPG T/10.9 PPG, MAX CASING PRESSURE= 518 PSI, AVG CASING PRESSURE= 450 PSI, MAX GAS=2224u.
RAINIER 1H | 17 | 2021-05-24 06:00 | 2021-05-24 07:00 | 1 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.58 | 12540 | 12540 | 0 | TIME DRILLING AT 12,003' TOOLFACE ROLLED F/ 70L TO HS, RE-WORK TROUGH F/ 11,974' T/ 11,997' AT 50L, CHOKES- 38-42% / 0%, FLARE-3'-6', MUD CUT F/11.0 PPG T/10.8 CASING PRESSURE= 578 PSI, AVERAGE CASING PRESSURE=450 PSI, MAX GAS=1910u.
RAINIER 1H | 17 | 2021-05-24 07:00 | 2021-05-24 10:30 | 3.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.73 | 12540 | 12540 | 0 | TIME DRILL @ 70L F/11,997' T/12,006' @ 2'/HR, WOB-5/15K, SPM-48/48, GPM-250, MRPM-130, SPP-2700/2900 PSI, DIFF-100/200 PSI, CHOKES- 38-42% / 0%, FLARE-1'-3', MUD CUT F/11.0 PPG T/10.8 PPG, MAX CASING PRESSURE= 450 PSI, AVG CASING PRESSURE= 300 PSI, MAX GAS=2053u. NOTE: INCREASE MUD WEIGHT F/ 11.0 PPG T/ 11.3 PPG.
RAINIER 1H | 17 | 2021-05-24 10:30 | 2021-05-24 12:00 | 1.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.79 | 12540 | 12540 | 0 | CONTROL SLIDE DRILLING @ 70L F/12,006' T/12,020' @ 20'/HR, WOB-10/20K, SPM-48/48, GPM-250, MRPM-130, SPP-2700/3000 PSI, DIFF-100/300 PSI, CHOKES- 38-42% / 0%, FLARE-1'-3', MUD WT 11.3 PPG, MAX SHUT IN CASING PRESSURE= 535 PSI, AVG CASING PRESSURE= 250 PSI, MAX GAS=572u. NOTE: MADE CONNECTION @ 12,018', CONTINUE CONTROL SLIDE DRILLING @ 70L, AT 12,020' TOOL FACE ROLLED F/ 60L T/ 60R.
RAINIER 1H | 17 | 2021-05-24 12:00 | 2021-05-24 13:00 | 1 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 11.83 | 12540 | 12540 | 0 | WORK DRILL STRING IN ATTEMPT TO ORIENTATE TOOL FACE F/ 60R T/ 60L. NOTE: DECISION WAS MADE FIRST SIDETRACK ATTEMPT AT 11,190' WAS UNSUCESSFUL, DECISION MADE TO WASH AND REAM F/ 12020' T/ 12,195' TO WORK TROUGH TO ATTEMPT SIDETRACK OPERATIONS AT 12,225'.
RAINIER 1H | 17 | 2021-05-24 13:00 | 2021-05-24 13:30 | 0.5 | U | PRDHLCV | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 11.85 | 12540 | 12540 | 0 | WASH F/ 12,020' T/ 12,195', SPM-48/48, GPM-250, MRPM-130, SPP-2700/3000 PSI, DIFF-100/300 PSI, CHOKES- 38-42% / 0%, FLARE-1'-3', MUD WEIGHT 11.3 PPG, MAX SHUT IN CASING PRESSURE=450 PSI, MAX CASING PRESSURE= 300 PSI, AVG CASING PRESSURE= 200 PSI, MAX GAS=730u.
RAINIER 1H | 17 | 2021-05-24 13:30 | 2021-05-24 18:00 | 4.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 12.04 | 12540 | 12540 | 0 | BUILD TROUGH F/12,195' T/12,225' @ 140R, GPM- 250, SPP-2700/2800 PSI, CHOKES- 38-42% / 0%, FLARE-1'-3', MUD WEIGHT 11.3, MAX CASING PRESSURE= 1124 PSI, AVG CASING PRESSURE= 150 PSI, MAX GAS=2266u. NOTE: INCREASE MUD WEIGHT F/ 11.3 PPG T/ 11.5 PPG.
RAINIER 1H | 17 | 2021-05-24 18:00 | 2021-05-25 06:00 | 12 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 12.54 | 12540 | 12540 | 0 | TIME DRILL @ 140R F/12,225' T/12,232' @ 1'/HR, WOB-15/25K, SPM-48/48, GPM-250, MRPM-130, SPP-2700/2900 PSI, DIFF-100/200 PSI, CHOKES- 100% / 0%, FLARE-NO FLARE, MUD WEIGHT 11.5 PPG, MAX CASING PRESSURE= 182 PSI, AVG CASING PRESSURE= 150 PSI, MAX GAS=496u, INCREASED MUD WEIGHT F/ 11.5 PPG T/ 11.8 PPG, MAX CASING PRESSURE=0 PSI, MAX GAS=425u, NO FLARE.
RAINIER 1H | 18 | 2021-05-25 06:00 | 2021-05-25 09:00 | 3 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 12.67 | 12540 | 12540 | 0 | TIME DRILL F/12,232’ T/12,235’ TF-135R @ 1’ HOUR; GPM-240, SPP-2500, WOB-20K, DIFF-50/100 PSI
RAINIER 1H | 18 | 2021-05-25 09:00 | 2021-05-25 10:30 | 1.5 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 12.73 | 12540 | 12540 | 0 | TIME DRILL F/12,235’ T/12,240’ TF-135R @ 3’ HOUR; GPM-240, SPP-2600, WOB-20K, DIFF-50/100 PSI
RAINIER 1H | 18 | 2021-05-25 10:30 | 2021-05-25 11:30 | 1 | U | PRDHLCV | DRLG | DRLST | TIME DRILLING | 12.77 | 12540 | 12540 | 0 | TIME DRILL F/12,240’ T/12,245’ TF-135R @ 5’ HOUR; GPM-240, SPP-2600, WOB-20K, DIFF-50/100 PSI
RAINIER 1H | 18 | 2021-05-25 11:30 | 2021-05-25 15:00 | 3.5 | U | PRDHLCV | DRLG | CTLDRL | CONTROL DRILLING | 12.92 | 12540 | 12540 | 0 | CONTROL SLIDE F/12,245' T/12,293' TF-90R; GPM-240, SPP-2800, WOB-25/30K, DIFF-200-300 PSI
RAINIER 1H | 18 | 2021-05-25 15:00 | 2021-05-25 16:00 | 1 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.96 | 12540 | 12540 | 0 | BIT BEGAN TO STACK WEIGHT AND MOTOR STALLED; SHUT DOWN TO RE-SYNC MWD AND TAKE CHECKSHOT; AFTER CHECKSHOT, VERIFIED THAT SIDETRACK WAS SUCCESSFUL; ORIGINAL HOLE SURVEY DEPTH @12,275' WAS 32.71 INC/139.0 AZM, CHECKSHOT SURVEY @ SURVEY DEPTH 12,230' WAS 25.7 INC/145.3 AZM; CIRCULATE TO CLEAN UP HOLE AND DISCUSS PLAN MOVING FORWARD
RAINIER 1H | 18 | 2021-05-25 16:00 | 2021-05-25 18:00 | 2 | U | PRDHLCV | DRLG | CTLDRL | CONTROL DRILLING | 13.04 | 12225 | 12305 | 40 | DECISION WAS MADE TO WAG DRILL WITH INTENTIONS OF GETTING OUT OF RESTRICTED DRILLING CONDITIONS AND TO GET A BETTER VIEW OF MOTOR YIELDS; CONTROL SLIDE F/12,293' T/12,305' TF-HS; GPM-240, SPP-2800, WOB-25/30K, DIFF-200-300 PSI
RAINIER 1H | 18 | 2021-05-25 18:00 | 2021-05-25 18:30 | 0.5 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.06 | 12305 | 12305 | 0 | RE-CYCLE PUMPS AND PUMP UP SURVEY TO CALCULATE MOTOR YIELD AND DLN NEEDED TO LAND CURVE, DISTANCE TO ORGINAL HOLE=12', BEHIND=2', RIGHT=6', SLIDE SEEN=19', SLIDE UNSEEN=61', MOTOR YIELD=19 DEGREES, DLN= 8.7 DEGREES.
RAINIER 1H | 18 | 2021-05-25 18:30 | 2021-05-25 19:00 | 0.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.08 | 12305 | 12305 | 0 | ORIENT TOOLFACE, SHUT DOWN MUD PUMPS, PULL THROUGH SIDETRACK WITH 75/100K OVERPULL, WHILE PULLING THROUGH SIDETRACK CASING PRESSURE INCREASED TO 260 PSI, CONTINUE STRIPPING OUT OF HOLE WITH WET PIPE TO 11,974' PUMPING CALCULATED HOLE FILLS OF 1.9 BBLS PER STAND DOWN BACKSIDE W/ 11.8 PPG OBM, MAX CASING PRESSURE=321, AVERAGE CASING PRESSURE=250 PSI.
RAINIER 1H | 18 | 2021-05-25 19:00 | 2021-05-25 20:00 | 1 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.13 | 12305 | 12305 | 0 | CIRCULATE BOTTOMS UP, WORK DRILL STRING, SPM-95, GPM-250, SPP-2600 PSI, CHOKES- 100% / 0%, MUD WEIGHT IN=11.8 PPG / OUT=11.8 PPG, NO FLARE, MAX CASING PRESSURE= 310 PSI, AVG CASING PRESSURE= 0 PSI, MAX GAS-485u, FINAL CASING PRESSURE= 0 PSI.
RAINIER 1H | 18 | 2021-05-25 20:00 | 2021-05-25 21:00 | 1 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 13.17 | 12305 | 12305 | 0 | MONIITOR SHUT IN CASING PRESSURE, SICP=298 PSI, SPOT 77 BBLS 17.9 PPG MUD CAP, FINAL CASING PRESSURE = 0 PSI, ADDED 200 PSI SAFETY FACTOR FOR VOLIUME MUD CAP PUMPED, HYDROSTATIC PRESSURE BEFORE MUD CAP 7500 PSI, HYDROSTATIC PRESSURE AFTER MUD CAP 8000 PSI, TOP OF MUD CAP 10,305', BOTTOM OF MUD CAP 11,974',
RAINIER 1H | 18 | 2021-05-25 21:00 | 2021-05-25 22:30 | 1.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.23 | 12305 | 12305 | 0 | STRIP OUT OF HOLE F/ 11,974' T/ 10,203', PUMPING CALCULATED HOLE FILLS F/ WET DRILL STRING, 1.9 BBLS PER STAND DOWN BACKSIDE WITH 11.8 PPG OBM.
RAINIER 1H | 18 | 2021-05-25 22:30 | 2021-05-25 23:00 | 0.5 | U | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 13.25 | 12305 | 12305 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC, PUMP SLUG.
RAINIER 1H | 18 | 2021-05-25 23:00 | 2021-05-26 01:30 | 2.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.35 | 12305 | 12305 | 0 | TRIP OUT THE HOLE F/10,203' T/2,963', HOLE TAKING PROPER FILL.
RAINIER 1H | 18 | 2021-05-26 01:30 | 2021-05-26 02:00 | 0.5 | U | PRDHLCV | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 13.38 | 12305 | 12305 | 0 | FLOW CHECK @ 2,963' (NO FLOW), REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
RAINIER 1H | 18 | 2021-05-26 02:00 | 2021-05-26 03:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.42 | 12305 | 12305 | 0 | CONTINUE TRIPPING OUT THE HOLE F/2,963' T/BHA, L/D STANDARD AGITATOR ON STAND 28, HOLE TAKING PROPER FILL, FLOW CHECK @ BHA (NO FLOW).
RAINIER 1H | 18 | 2021-05-26 03:00 | 2021-05-26 04:00 | 1 | U | PRDHLCV | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.46 | 12305 | 12305 | 0 | RACK BACK THRUSTER AND TOP MONEL, REMOVE MWD, DRAIN MOTOR, BREAK BIT AND L/D MOTOR. NOTE: INSPECTED MOTOR AND BIT, MOTOR IN CONDITION, BEARING GAP WITHIN TORELANCE AND MOTOR DRAINED STRONG, BIT GRADE: 1/1, CHIPPED CUTTERS ON SHOULDER AND GAUGE, 1 MISSING CUTTER ON GAUGE.
RAINIER 1H | 18 | 2021-05-26 04:00 | 2021-05-26 05:00 | 1 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 13.5 | 12305 | 12305 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13090615 JETS 6/18S TFA: 1.491), 5 1/2", 6/7L, 83.8 STG @ 2.25° SLICK; .68 REV/GAL; 4.01' BIT TO BEND; 5.56" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-7623 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX THRUSTER, X/O XT-39 P x DS 42B, 28 STANDS, AGITATOR. BIT TO SVY-64'. BIT TO GAMMA-54'. TEST, MWD (TEST GOOD) AND MAKE UP BIT.
RAINIER 1H | 18 | 2021-05-26 05:00 | 2021-05-26 06:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.54 | 12305 | 12305 | 0 | TRIP IN THE HOLE F/ BHA T/2,000', HOLE GIVING PROPER DISPLACEMENT.
RAINIER 1H | 19 | 2021-05-26 06:00 | 2021-05-26 07:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.58 | 12305 | 12305 | 0 | TIH F/2,000' T/2,800'; HOLE GIVING PROPER DISPLACEMENT; P/U STANDARD .875 AGIATATOR; BEFORE PSI-1450, AFTER PSI-1790; REMOVE TRIP NIPPLE/INSTALL ROT HEAD; TIH F/2,800' T/12,000'
RAINIER 1H | 19 | 2021-05-26 07:00 | 2021-05-26 08:00 | 1 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.63 | 12305 | 12305 | 0 | RIG SERVICE
RAINIER 1H | 19 | 2021-05-26 08:00 | 2021-05-26 14:00 | 6 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.88 | 12305 | 12305 | 0 | TIH T/12,018'; CIRCULATE OUT MUD CAP AT 175/200 GPM, MAX MW OUT 15.5 PPG. MAX GAS 1628u, NO FLARE OR CP
RAINIER 1H | 19 | 2021-05-26 14:00 | 2021-05-26 15:00 | 1 | U | PRDHLCV | WSHRM | RMDIR | WASH / REAM FOR DIRECTIONAL SLIDE | 13.92 | 12305 | 12305 | 0 | WASH DOWN F/12,018' T/12,175', 200 GPM SPP-1900, ORIENT TF AND GO INTO SDETRACK 01 AT 12,225'
RAINIER 1H | 19 | 2021-05-26 15:00 | 2021-05-26 21:00 | 6 | U | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.17 | 12305 | 12540 | 39.2 | CONTROL SLIDE F/12,305' T/12,540' (235' IN 6 HRS @ 40 FPH) TF-HS; GPM-350, SPP-4300, WOB-25/50K, DIFF-300-600 PSI.
RAINIER 1H | 19 | 2021-05-26 21:00 | 2021-05-27 00:30 | 3.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.31 | 12540 | 12726 | 53.1 | SLIDE F/12,540' T/12,726' (186' IN 3.5 HRS @ 53 FPH) TF-HS; GPM-350, SPP-4300, WOB-25/50K, DIFF-300-600 PSI. NOTE: CHECKSHOT @ 12,659' MD, 12,318' TVD', INC: 72.36°, AZM: 134.07, DLS:8.06°, HIGH:13', RIGHT:23'. PROJ TO BIT: 12,726' MD, 12,335' TVD, INC: 78°, AZM: 131, DLS: 9.5°. SLIDE SEEN 16', UNSEEN 37', MTR YIELD 16.6°, DLN TO LAND: 2.8°
RAINIER 1H | 19 | 2021-05-27 00:30 | 2021-05-27 02:00 | 1.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.38 | 12726 | 12726 | 0 | STRIP OUT OF HOLE TO PICK UP LATERAL ASSEMBLY F/12,726' T/11,974'. ORIENT TOOLFACE BEFORE PULLING OUT OF SIDETRACK. NOTE: TIGHT HOLE @ 12,275'. ACTIVATED OSCILLATOR (2.5K RH TQ / 2K LH TQ) AND ATTEMPTED TO PULL OUT OF SIDETRACK WITH OUT PUMPS. P/U-370K, RPM-45. AT 12,240' OSCILLATOR WAS INEFFECTIVE, PUMP @ 250 GPM WITH OSCILLATOR (P/U-325K)
RAINIER 1H | 19 | 2021-05-27 02:00 | 2021-05-27 03:30 | 1.5 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.44 | 12726 | 12726 | 0 | CIRCULATE BOTTOMS UP @ 11,974'. GPM-350, PP-4400, FLARE-0', CASING PSI WHILE CIRCULATING-0 PSI. MAX GAS-343u. SPOT 50 BBLS MUD CAP @ 11,985' FOR 300 PSI SAFETY FACTOR. TOP OF MUD CAP-10,905'
RAINIER 1H | 19 | 2021-05-27 03:30 | 2021-05-27 04:00 | 0.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.46 | 12726 | 12726 | 0 | POOH F/11,974' T/10,492'. HOLE TAKING PROPER FILLS ON TRIP OUT.
RAINIER 1H | 19 | 2021-05-27 04:00 | 2021-05-27 04:30 | 0.5 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.48 | 12726 | 12726 | 0 | PERFORM FLOW CHECK-NO FLOW. PUMP SLUG.
RAINIER 1H | 19 | 2021-05-27 04:30 | 2021-05-27 05:30 | 1 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.52 | 12726 | 12726 | 0 | POOH F/10,492' T/8,970'. HOLE BEGAN TAKING LESS FILLS.
RAINIER 1H | 19 | 2021-05-27 05:30 | 2021-05-27 06:00 | 0.5 | P | PRDHLCV | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 14.54 | 12726 | 12726 | 0 | PERFORM FLOW CHECK-WELL FLOWING. SHUT WELL IN AND CASING PSI BUILT TO 75 PSI. TRANSFER KILL MUD TO SLUG TANK AND PREPARE TO STRIP OUT FILLING BACKSIDE WITH 16.7 PPG OBM.
RAINIER 1H | 20 | 2021-05-27 06:00 | 2021-05-27 07:00 | 1 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.58 | 12726 | 12726 | 0 | FINISH PUMPING OUT SLUG FROM DRILL PIPE AND RE-SLUG SAME(PUMPED OUT 27 BBL SLUG TO ADD HYDROSTATIC PRESSURE)
RAINIER 1H | 20 | 2021-05-27 07:00 | 2021-05-27 10:00 | 3 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.71 | 12726 | 12726 | 0 | STRIP OUT OF HOLE PUMPING CALCULATED FILL OF 16.8 PPG OBM F/8970 T/6492, 27 BBLS MAX SICP-115
RAINIER 1H | 20 | 2021-05-27 10:00 | 2021-05-27 11:00 | 1 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.75 | 12726 | 12726 | 0 | FLOW CHECK, NO FLOW, PULL RCH, INSTALL TRIP NIPPLE, AND LAY DOWN AGITATOR
RAINIER 1H | 20 | 2021-05-27 11:00 | 2021-05-27 13:30 | 2.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 14.85 | 12726 | 12726 | 0 | TRIP OUT HOLE WITH PROPER DISPLACEMENT TO BHA, FLOW CHECK, NO FLOW, RACK BACK MONELS, LAY DOWN MWD, MUD MOTOR, AND BIT. MOTOR DRAINED CORRECTLY AND BIT HAD TWO CHIPPED CUTTERS ON SHOULDER
RAINIER 1H | 20 | 2021-05-27 13:30 | 2021-05-27 15:30 | 2 | P | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 14.94 | 12726 | 12726 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13571904 JETS 6/18S TFA: 1.491), 5 1/2", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.04' BIT TO BEND; 5.62" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX, X/O XT-39 P x DS 42B, 2 STANDS, REAMER, 26 STDS DP, AGITATOR. 33 STDS DP, ON DEMAND AGITATOR, BIT TO SVY-68'. BIT TO GAMMA-55'. TEST, MWD (TEST GOOD) AND MAKE UP BIT.
RAINIER 1H | 20 | 2021-05-27 15:30 | 2021-05-27 18:30 | 3 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.06 | 12726 | 12726 | 0 | TRIP IN HOLE, P/U REAMER AFTER TWO STANDS, TRIP IN HOLE 26 STANDS AND P/U AGITATOR. PRESSURE BEFORE 870, PRESS. AFTER P/U 970
RAINIER 1H | 20 | 2021-05-27 18:30 | 2021-05-27 19:30 | 1 | P | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 15.1 | 12726 | 12726 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
RAINIER 1H | 20 | 2021-05-27 19:30 | 2021-05-27 20:30 | 1 | P | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.15 | 12726 | 12726 | 0 | RIG SERVICE
RAINIER 1H | 20 | 2021-05-27 20:30 | 2021-05-27 21:30 | 1 | P | PRDHLCV | RIGMT | CUTDL | SLIP / CUT DRL LINE | 15.19 | 12726 | 12726 | 0 | CUT/SLIP DRILL LINE-80'
RAINIER 1H | 20 | 2021-05-27 21:30 | 2021-05-28 | 2.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.29 | 12726 | 12726 | 0 | TRIP IN HOLE T/11,974' WITH CORRECT DISPLACEMENT ON DRILL PIPE
RAINIER 1H | 20 | 2021-05-28 | 2021-05-28 02:00 | 2 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.37 | 12726 | 12726 | 0 | CIRCULATE OUT MUD CAP @ 11,974'. LOST APPROXIMATELY 50 BBLS WHILE CIRCULATING OUT MUD CAP. HEAVIEST MW SEEN-14.8 PPG
RAINIER 1H | 20 | 2021-05-28 02:00 | 2021-05-28 02:30 | 0.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.4 | 12726 | 12726 | 0 | TRIP IN HOLE F/11,974 T/12,340'. ORIENT TOOLFACE @ 12,215' TO 140 AND TRIP IN HOLE THROUGH SIDETRACK. PUMP UP SVY AND VERIFY IN ST01 @ 12,340'.
RAINIER 1H | 20 | 2021-05-28 02:30 | 2021-05-28 03:00 | 0.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.42 | 12726 | 12726 | 0 | TRIP IN HOLE F/12,340' T/12,566'. AT 12,566' BHA BEGAN TO STACK WEIGHT. PICK UP AND SCREW TOP DRIVE INTO STAND.
RAINIER 1H | 20 | 2021-05-28 03:00 | 2021-05-28 04:30 | 1.5 | P | PRDHLCV | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 15.48 | 12726 | 12726 | 0 | REAM F/12,566' T/12,726'. GPM-350, PP-4,850, RPM-20, TQ=12-22K
RAINIER 1H | 20 | 2021-05-28 04:30 | 2021-05-28 06:00 | 1.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.54 | 12726 | 12755 | 19.3 | SLIDE F/12,726' T/12,755' (29' IN 1.5 HRS @ 19 FPH) TF-HS; GPM-340, SPP-4600, WOB-25/35K, DIFF-100-300 PSI.
RAINIER 1H | 21 | 2021-05-28 06:00 | 2021-05-28 09:00 | 3 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.67 | 12755 | 12862 | 35.7 | SLIDE DRLG 12,755'-12,862 (107' @ 40 FPH) WOB-20/26 MMRPM-272 GPM-400 DIFF-200/350 CP-0 FL-0 SICP-30 SLIDE DEPTHS: F/12755 T/12765 10' TF-70L 0600-0630 F/12822 T/12872 50' TF-30L 0730-0850 F/12915 T/12962 47' TF-HS 0930-1020
RAINIER 1H | 21 | 2021-05-28 09:00 | 2021-05-28 10:30 | 1.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.73 | 12862 | 12962 | 66.7 | ROT DRLG 12,862-12,962 (100' @ 60 FPH) RPM-30 MMRPM-272 GPM-400 SPP-6400 DIFF-600/800 TQ-17/19K , LANDED CURVE AT 12,962' MD 12,373' VS NAT N10:20 HRS 05/28/2021 CP-0 FL-0 SICP-30/50
RAINIER 1H | 21 | 2021-05-28 10:30 | 2021-05-28 13:30 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.85 | 12962 | 13085 | 41 | SLIDE DRLG 12,962-13,085' (123' @ 41 FPH) WOB-20/26, MMRPM-238 GPM-350 DIFF-200/350 CP-0 FL-0 SICP-30 SLIDE DEPTHS: F/13108 T/13128 20' TF-90R 1150-1220 F/13203 T/13223 20' TF-90R 1300-1320 F/13298 T/13318 20' TF-90R 1400-1430 F/13584 T/13604 20' TF-90R 1620-1655 F/13680 T/13695 15' TF-HS 1730-1800 F/13780 T/13793 12' TF-180 1830-1852 F/13873 T/13888 15' TF-180 1929-1959
RAINIER 1H | 21 | 2021-05-28 10:30 | 2021-05-28 10:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 15.73 | 12962 | 12962 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 05-28-2021 @ 10:30 HRS
RAINIER 1H | 21 | 2021-05-28 10:30 | 2021-05-28 10:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 15.73 | 12962 | 12962 |  | MILESTONE_LAND/END CURVE SECTION ON 05/28/2021 @ 10:30 HRS
RAINIER 1H | 21 | 2021-05-28 13:30 | 2021-05-28 20:30 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.15 | 13085 | 13968 | 126.1 | ROT DRLG F/13,085'-13,968' (883' @ 126 FPH) RPM-80 MMRPM-238, GPM-350 SPP-5400 DIFF-600/1200 TQ-16/22K, CP-0 FL-0 SICP-0 AT 13,693' HOLE BEGAN SEEPING. STARTED CUTTING MUD WEIGHT BACK DUE TO LOSSES. MW WAS BROUGHT DOWN TO A 11.3 PPG FROM AN 11.8 PPG
RAINIER 1H | 21 | 2021-05-28 20:30 | 2021-05-28 21:30 | 1 | U | PRDHLLT | WAIT | WOW | WAIT ON WEATHER | 16.19 | 13968 | 13968 | 0 | WAITED ON WEATHER DUE TO TORNADO WARNING, HIGH WINDS, & HEAVY RAIN
RAINIER 1H | 21 | 2021-05-28 21:30 | 2021-05-29 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.29 | 13968 | 14307 | 135.6 | ROT DRLG (339' IN 2.38 HRS @ 142 FPH) RPM-80, MMRPM-238, GPM-350 SPP-4200/5400, DIFF-600/1200, TQ-16/22K, CP-0 FL-0 SICP-0 HOLE BEGAN LOSING APPROXIMATELY 50-75 BBLS/HR. STARTED CUTTING MUD WEIGHT BACK DUE TO LOSSES. MW WAS BROUGHT DOWN TO A 10.8 PPG FROM AN 11.8 PPG PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER ADDING 3 SKS FIRST RESPONSE EVERY 15 MINUTES TO ACTIVE MUD SYSTEM.
RAINIER 1H | 21 | 2021-05-29 | 2021-05-29 01:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.35 | 14307 | 14343 | 24 | SLIDE (36' IN 1.62 @ 22 FPH) WOB-20/26, MMRPM-238 GPM-350 DIFF-200/350 CP-0 FL-0 SICP-0 SLIDE DEPTHS: F/13969' T/13982' 13' TF-180 2130-2148 F/14158' T/14170' 12' TF 30 L 2310-2347 F/14256' T/14266' 10' 60L 0023-0058
RAINIER 1H | 21 | 2021-05-29 01:30 | 2021-05-29 02:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 16.38 | 14343 | 14343 | 0 | RIG SERVICE
RAINIER 1H | 21 | 2021-05-29 02:00 | 2021-05-29 05:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.5 | 14343 | 14725 | 127.3 | ROT DRLG (382' IN 3 HRS @ 127 FPH) RPM-80, MMRPM-238, GPM-350 SPP-4200/5400, DIFF-600/1200, TQ-16/22K, CP-0 FL-0 SICP-0 HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. CUTTING MW BACK TO 10.6 PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER ADDING 3 SKS FIRST RESPONSE EVERY 15 MINUTES TO ACTIVE MUD SYSTEM.
RAINIER 1H | 21 | 2021-05-29 05:00 | 2021-05-29 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.54 | 14725 | 14752 | 27 | SLIDE (27' IN 1 HR @ 27 FPH) WOB-20/40, MMRPM-238 GPM-350 DIFF-200/500 CP-0 FL-2-5' SICP-0 SLIDE DEPTHS: F/14348 T/14360 12' 30L 205-229 F/14636 T/14651' 15' 90L 422-458
RAINIER 1H | 22 | 2021-05-29 06:00 | 2021-05-29 07:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.6 | 14752 | 14777 | 16.7 | SLIDE DRLG 14,752-14,777' (25' @ 16.7 FPH) WOB-20/40, MMRPM-238/259, GPM-350/375, DIFF-200/350, CP-0, FL-0, SICP-0 SLIDE DEPTHS: F/15194 T/15209 15' TF-135R 0850-0950 F/15394 T/15404 10' TF-140R 1120-1150
RAINIER 1H | 22 | 2021-05-29 07:30 | 2021-05-29 13:00 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.83 | 14777 | 15494 | 130.4 | ROT DRLG F/14,777' T/15,494' (717' @ 130.36 FPH) RPM-80 MMRPM-238/259, GPM-350/375, SPP-5400, DIFF-600/1200, TQ-16/22K, CP-0, FL-0, SICP-0 MW WAS BROUGHT DOWN TO A 10.4 PPG FROM AN 10.8 PPG, MUD LOSS STOPPED, AT 15,456’
RAINIER 1H | 22 | 2021-05-29 13:00 | 2021-05-29 14:30 | 1.5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 16.9 | 15494 | 15494 | 0 | ROP FELL TO 48 FPH, DIFF FELL TO 420 PSI, CIRCULATED & CONDITIONED WHILE ATTEMPTING TO DRILL. WAS UNABLE TO IMPROVE DRILLING AND DECISION WAS MADE TO TRIP OUT & INSPECT MOTOR ALONG WITH BIT.
RAINIER 1H | 22 | 2021-05-29 14:30 | 2021-05-29 20:30 | 6 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 17.15 | 15494 | 15494 | 0 | WASHED & REAMED OUT ATTEMPTING TO PULL DRILL STRING WITHOUT ROTARY OR PUMPING F/15494' - T/11,974' NOTE: DRILL STRING WOULD NOT PULL FREE UNTIL PULLING MOTOR & BIT OUT OF THE SIDETRACK. PULLED 120K/150K OVER STRING WEIGHT EACH TIME IT WAS ATTEMPTED TO JUST PULL ON DRILL STRING. TORQUE DROPPED 2K AFTER PULLING REAMER OUT OF THE SIDETRACK AND WAS ABLE TO JUST PULL ONLY 1 STAND AFTER. REAMING OPERATIONS WERE CONTINUED AFTER UP TO THE BOTTOM OF THE SHOE
RAINIER 1H | 22 | 2021-05-29 20:30 | 2021-05-29 21:30 | 1 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.19 | 15494 | 15494 | 0 | CIRCULATED & CONDITIONED OUT GAS. CP-0 PSI, FLARE-3'/0' AFTER BOTTOMS UP. HOLE WAS STILL TAKING MUD LOSING A TOTAL OF 40 BBLS. AFTER BOTTOMS UP A 35 BBL 16 PPG SLUG WAS PUMPED. WELL WAS SHUT IN WITH 0 PSI CP
RAINIER 1H | 22 | 2021-05-29 21:30 | 2021-05-30 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 17.29 | 15494 | 15494 | 0 | STRIPPED OUT F/11,974' T/7900' FILLING ANNULAS WITH 3.5 BBLS/5 STDS OF 18 PPG OBM. TOTAL OF 60 BBLS SICP-0 PSI AT 7900' OPENED UP CHOKES AND MONITORED WELL FOR FLOW, WELL WAS NOT FLOWING. STARTED PUMPING 10.4 PPG DOWN ANNULAS & POOH F/7900' T/6,199'.
RAINIER 1H | 22 | 2021-05-30 | 2021-05-30 00:30 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 17.31 | 15494 | 15494 | 0 | PERFORM FLOW CHECK-NO FLOW. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
RAINIER 1H | 22 | 2021-05-30 00:30 | 2021-05-30 04:00 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 17.46 | 15494 | 15494 | 0 | POOH F/6,199' T/BHA. HOLE TOOK PROPER FILLS ON TRIP OUT.
RAINIER 1H | 22 | 2021-05-30 04:00 | 2021-05-30 04:30 | 0.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 17.48 | 15494 | 15494 | 0 | PICK UP PUP JOINT AND 1 JOINT OF DP, SCREW INTO TOP OF TOMAX AND RACK BACK WITH TOP MONEL. DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR. MOTOR HAD TO BE DRAINED WITH ROTARY, HAD MINIMAL SLACK, AND WAS IN OVERALL GOOD CONDITION. BIT DID NOT HAVE ANY RUBBER INSIDE AND HAD SEVERE DAMAGE TO THE SHOULDER CUTTERS.
RAINIER 1H | 22 | 2021-05-30 04:30 | 2021-05-30 06:00 | 1.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 17.54 | 15494 | 15494 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13558789 JETS 6/18S TFA: 1.491), 5 1/2", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.10' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX, X/O XT-39 P x DS 42B, 2 STANDS, REAMER. BIT TO SVY-67'. BIT TO GAMMA-54'. TEST, MWD (TEST GOOD) AND MAKE UP BIT.
RAINIER 1H | 23 | 2021-05-30 06:00 | 2021-05-30 10:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 17.71 | 15494 | 15494 | 0 | TRIP IN HOLE F/BHA T/6,684'. PICK UP AGITATOR ON STAND 26. PSI BEFORE-550 / PSI AFTER-600. HOLE DISPLACING LESS THAN CALCULATED WHILE TRIPPING IN.
RAINIER 1H | 23 | 2021-05-30 10:00 | 2021-05-30 10:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 17.73 | 15494 | 15494 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
RAINIER 1H | 23 | 2021-05-30 10:30 | 2021-05-30 12:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 17.79 | 15494 | 15494 | 0 | TRIP IN HOLE F/6,684' T/10,209'. HOLE DISPLACING LESS THAN CALCULATED WHILE TRIPPING IN, STOPPED DISPLACING AT 10,160'
RAINIER 1H | 23 | 2021-05-30 12:00 | 2021-05-30 14:00 | 2 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.88 | 15494 | 15494 | 0 | TRIP IN HOLE TO 10,209’, NO DISPLACEMENT, CIRCULATE BOTTOMS UP(MAX MW 14.5 PPG, RECOVERED 70 BBLS OF 14-14.5 PPG OBM. LOST APPROX. 90 BBLS. GPM-150 SPP-1000
RAINIER 1H | 23 | 2021-05-30 14:00 | 2021-05-30 14:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 17.9 | 15494 | 15494 | 0 | TRIP IN HOLE TO 12,153' W/FULL RETURNS
RAINIER 1H | 23 | 2021-05-30 14:30 | 2021-05-30 15:00 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 17.92 | 15494 | 15494 | 0 | FILL PIPE AND TEST MWD, GOOD TEST
RAINIER 1H | 23 | 2021-05-30 15:00 | 2021-05-30 16:00 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 17.96 | 15494 | 15494 | 0 | RIG SERVICE
RAINIER 1H | 23 | 2021-05-30 16:00 | 2021-05-30 17:00 | 1 | U | PRDHLLT | LOG | DIRSVY | DIRECTIONAL / SINGLE / MULTI | 18 | 15494 | 15494 | 0 | ORIENT TOOLFACE @ 12,215' TO 140 AND TRIP IN HOLE THROUGH SIDETRACK. PUMP UP SVY AND VERIFY IN ST01 @ 12,340'.
RAINIER 1H | 23 | 2021-05-30 17:00 | 2021-05-30 18:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 18.06 | 15494 | 15494 | 0 | TRIPPED IN THE HOLE T/15,000'. HOLE GIVING PROPER DISPLACEMENTS ON TRIP IN.
RAINIER 1H | 23 | 2021-05-30 18:30 | 2021-05-30 19:00 | 0.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 18.08 | 15494 | 15494 | 0 | W/R F/15,000' - T/15,494'. GPM-335, PP-4650, RPM-50, TQ=14-16K
RAINIER 1H | 23 | 2021-05-30 19:00 | 2021-05-31 01:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 18.33 | 15494 | 16250 | 126 | ROT DRLG (756' IN 5.95 HRS @ 127 FPH) RPM-80, MMRPM-238, GPM-350 SPP-4200/5200, DIFF-600/1000, TQ-16/22K, CP-0/350 FL-0/15' SICP-0/700 HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. CUTTING MW BACK TO 10.0 PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER
RAINIER 1H | 23 | 2021-05-31 01:00 | 2021-05-31 06:00 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 18.54 | 16250 | 16334 | 16.8 | SLIDE (84' IN 5.05 HR @ 17 FPH) WOB-20/40, MMRPM-255, PP-4700, GPM-375 DIFF-200/500 CP-0 FL-2-5' SICP-0 SLIDE DEPTHS: F/15579' T/15594' 15' 30L 2008-2046 F/15764' T/15766' 12' 150L 2155-2230 F/16053' T/16073' 20' 45L 0015-0124 F/16150' T/16170' 20' 20L 157-321 F/16207' T/16222' 15' HS 337-412 F/16243' T/16255' 12' HS 0430-0520
RAINIER 1H | 24 | 2021-05-31 06:00 | 2021-05-31 10:30 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 18.73 | 16334 | 16779 | 98.9 | ROT DRLG (445' IN 3.75 HRS @ 118.67 FPH) RPM-80, MMRPM-238, GPM-350 SPP-4200/5200, DIFF-600/1000, TQ-16/22K, FL-0/5' CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTIONS=0 PSI HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. CUTTING MW BACK TO 10.0 PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER Plan 9 – 12520’ TVD at 0 VS with 90 deg INC 5’ above/ 5’ below
RAINIER 1H | 24 | 2021-05-31 10:30 | 2021-05-31 12:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 18.79 | 16779 | 16809 | 20 | SLIDE 30' IN 1.75 HR @ 17.14 FPH) WOB-20/40, MMRPM-255, PP-4700, GPM-375, DIFF-200/500, FL-0-5' CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTIONS=0 PSI SLIDE DEPTHS: F/16338 T/16353 15' TF-HS 0620-0710 F/16725 T/16748 15' TF-180 1010-1105
RAINIER 1H | 24 | 2021-05-31 12:00 | 2021-05-31 12:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 18.81 | 16809 | 16809 | 0 | RIG SERVICE
RAINIER 1H | 24 | 2021-05-31 12:30 | 2021-05-31 14:00 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 18.87 | 16809 | 17000 | 127.3 | ROT DRLG (191' IN 1.5 HRS @ 127 FPH) RPM-80, MMRPM-238, GPM-350 SPP-4200/5200, DIFF-600/1000, TQ-16/22K, FL-0/15' CASING PSI WHILE DRILLING=0-350 PSI CASING PSI DURING CONNECTIONS=0-700 PSI HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER Plan 9 – 12520’ TVD at 0 VS with 90 deg INC 5’ above/ 5’ below
RAINIER 1H | 24 | 2021-05-31 14:00 | 2021-05-31 14:30 | 0.5 | P | PRDHLLT | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 18.9 | 17000 | 17000 | 0 | CIRCULATE OUT GAS W/RAMS CLOSED MAX CP-1350 FL-5/30' MC-10.0-9.8 PPG, RAISE MW TO 10.1 PPG, GAS FROM STALL AT 16,950'
RAINIER 1H | 24 | 2021-05-31 14:30 | 2021-05-31 22:00 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 19.21 | 17000 | 17605 | 80.7 | ROT DRLG (605' IN 7.33 HRS @ 82 FPH) RPM-70, MMRPM-255, GPM-375 SPP-4700/5500, DIFF-600/1000, TQ-16/23K, FL-0/25' CASING PSI WHILE DRILLING=0-550 PSI CASING PSI DURING CONNECTIONS=0-700 PSI HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER Plan 9 – 12520’ TVD at 0 VS with 90 deg INC 10’ above/ 0’ below Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-3:13 a.m
RAINIER 1H | 24 | 2021-05-31 22:00 | 2021-06-01 06:00 | 8 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 19.54 | 17605 | 17692 | 10.9 | SLIDE 87' IN 8.17 HR @ 11 FPH) WOB-20/40, MMRPM-255, PP-4700, GPM-375 DIFF-200/500, FL-2-5' CASING PSI WHILE DRILLING=0-550 PSI CASING PSI DURING CONNECTIONS=0-700 PSI SLIDE DEPTHS: F/17005 T/17025 20' HI-SIDE 250-405 F/17102 T/17112 10' HI-SIDE 500-530 F/17195' T/17207' 12' TF-HS 1830-1939 F/17385' T/17397' 12' TF-45L 2110-2242 F/17514' T/17529' 15' TF-180 0015-0152 F/17666' T/17684' 18' TF-180 0333-0540
RAINIER 1H | 25 | 2021-06-01 06:00 | 2021-06-01 07:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 19.58 | 17692 | 17755 | 63 | ROTATE F/17,692' 17,755' (63' IN 1 HR @ 63 FPH) RPM-70, MMRPM-255, GPM-375 SPP-5250/5750, DIFF-400/600, TQ-16/23K, FL-0/25' CASING PSI WHILE DRILLING=0-550 PSI CASING PSI DURING CONNECTIONS=0-750 PSI HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below- 6/1/2021 3:13 a.m
RAINIER 1H | 25 | 2021-06-01 07:00 | 2021-06-01 07:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 19.6 | 17755 | 17755 | 0 | CIRCULATED OFF BOTTOM AND RECORD PUMP PSI @ 375 GPM, PP-4900, RPM-50. DROP BALL AND ACTIVATE DWS ON-DEMAND AGITATOR. PUMP WITH 200 GPM, PP-2200. PUMPED 1420 STROKES AND OBSERVED PUMP PSI INCREASE FROM 2200 TO 2300 PSI. INCREASED GPM TO 375 AND PUMP PRESSURE INCREASED FROM 4900 TO 5250.
RAINIER 1H | 25 | 2021-06-01 07:30 | 2021-06-01 08:30 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 19.65 | 17755 | 17831 | 76 | ROT DRLG (76' IN 1 HRS @ 76 FPH) RPM-70, MMRPM-255, GPM-375 SPP-5250/5500, DIFF-300/500, TQ-16/23K, FL-0/25' CASING PSI WHILE DRILLING=0-550 PSI CASING PSI DURING CONNECTIONS=0-700 PSI HOLE LOSING APPROXIMATELY 25-50 BBLS/HR. PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6/1/2021 3:13 a.m
RAINIER 1H | 25 | 2021-06-01 08:30 | 2021-06-01 11:00 | 2.5 | P | PRDHLLT | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 19.75 | 17831 | 17831 | 0 | CASING PSI BEGAN TO INCREASE, SPACE OUT AND SHUT PIPE RAMS. CIRC OUT GAS @ 17,831': PP-5650, MAX CASING PRESSURE=1809, PRESENT MUD WT-10.3, MUD CUT-9.9, FLARE-20-35'. MAX GAS-2835u. INCREASING MUD WEIGHT TO 10.5 PPG. LITHOLOGY @ 17,830: 10% SHALE, 5% ASH, 85% CHALK, 4% CALCITE
RAINIER 1H | 25 | 2021-06-01 11:00 | 2021-06-01 18:30 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 20.06 | 17831 | 18272 | 58.8 | ROT DRLG (441' IN 7.55 HRS @ 58 FPH) RPM-70, MMRPM-255, GPM-375 SPP-5500/6400, DIFF-600/900, TQ-16/26K, FL-0/35' CASING PSI WHILE DRILLING=0-1000 PSI CASING PSI DURING CONNECTIONS=500-1400 PSI PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6/1/2021 @ 3:13 a.m
RAINIER 1H | 25 | 2021-06-01 18:30 | 2021-06-01 23:30 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 20.27 | 18272 | 18322 | 10 | SLIDE 50' IN 4.95 HR @ 10 FPH) WOB-20/40, MMRPM-255, PP-4700, GPM-375 DIFF-200/500, FL-20-35' CASING PSI WHILE DRILLING=0-1000 PSI CASING PSI DURING CONNECTIONS=500-1400 PSI SLIDE DEPTHS: F/17862 T/17867 5' HI-SIDE 1110-1215 F/17930 T/17942 12' HI-SIDE 1330-1445 F/18021 T/18031 10' HI-SIDE 1550-1635 18115' T/18130' 15' TF-180 1813-1932 F/18240' T/18248' 8' TF-180 2134-2207
RAINIER 1H | 25 | 2021-06-01 23:30 | 2021-06-02 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 20.29 | 18322 | 18322 | 0 | RIG SERVICE
RAINIER 1H | 25 | 2021-06-02 | 2021-06-02 01:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 20.33 | 18322 | 18379 | 57 | ROT DRLG (57' IN 1.17 HRS @ 48 FPH) RPM-70, MMRPM-221, GPM-325 SPP-4700/5300, DIFF-400/600, TQ-16/26K, FL-0/35' CASING PSI WHILE DRILLING=0-800 PSI CASING PSI DURING CONNECTIONS=700-1200 PSI PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER REDUCED GPM FOR TEMP ON MWD, 342 DEG F. Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6/1/2021 @ 3:13 a.m
RAINIER 1H | 25 | 2021-06-02 01:00 | 2021-06-02 02:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 20.37 | 18379 | 18387 | 8 | SLIDE 8' IN .83 HR @ 10 FPH) WOB-20/40, MMRPM-221, PP-5400, GPM-375 DIFF-200/400, FL-20-35' CASING PSI WHILE DRILLING=0-800 PSI CASING PSI DURING CONNECTIONS=700-1200 PSI SLIDE DEPTHS: F/18341 T/18349 8'TF-180 0012-0102
RAINIER 1H | 25 | 2021-06-02 02:00 | 2021-06-02 03:00 | 1 | P | PRDHLLT | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 20.42 | 18387 | 18387 | 0 | CASING PSI BEGAN TO INCREASE, SPACE OUT AND SHUT PIPE RAMS. CIRC OUT GAS @ 18,387': PP-5650, MAX CASING PRESSURE=1101, PRESENT MUD WT-10.7, MUD CUT-10.5, FLARE-20-35'. MAX GAS-2885u. LITHOLOGY @ 18,380: 100% CHALK, 2% CALCITE, TR% PYRITE
RAINIER 1H | 25 | 2021-06-02 03:00 | 2021-06-02 05:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 20.5 | 18387 | 18465 | 39 | ROT DRLG (78' IN 2.17 HRS @ 36 FPH) RPM-70, MMRPM-221, GPM-325 SPP-4700/5300, DIFF-400/600, TQ-16/26K, FL-0/35' CASING PSI WHILE DRILLING=100-800 PSI CASING PSI DURING CONNECTIONS=700-900 PSI PUMPING 20 BBL 15 PPB LCM SWEEPS EVERY 100' SWEEP CONTENTS: 5 PPB CALCIUM CARB 5 PPB FIRST RESPONSE 5 PPB-MAGNAFIBER REDUCED GPM FOR MWD TEMP AT 343 DEG F. Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6/1/2021 @ 3:13 a.m
RAINIER 1H | 25 | 2021-06-02 05:00 | 2021-06-02 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 20.54 | 18465 | 18475 | 10 | SLIDE 10' IN .83 HR @ 10 FPH) WOB-20/40, MMRPM-255, PP-5500, GPM-375 DIFF-200/400, FL-20-35' CASING PSI WHILE DRILLING=100-800 PSI CASING PSI DURING CONNECTIONS=700-900 PSI SLIDE DEPTHS: F/18442 T/18452 10'TF-20L 0420-0510
RAINIER 1H | 26 | 2021-06-02 06:00 | 2021-06-02 09:30 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 20.69 | 18475 | 18577 | 29.1 | ROT DRLG F/18,475 T/18,577 (101' IN 3.5 HRS @ 29 FPH) RPM-70, MMRPM-221, GPM-325 SPP-4300/4900, DIFF-400/600, TQ-16/26K, FL-0/35' CASING PSI WHILE DRILLING=100-900 PSI CASING PSI DURING CONNECTIONS=700-1200 PSI DRILLING WITH REDUCED GPM TO MINIMIZE MWD TEMPERATURE INCREASE.
RAINIER 1H | 26 | 2021-06-02 09:30 | 2021-06-02 10:30 | 1 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 20.73 | 18577 | 18577 | 0 | WHILE DRILLING AT 18,577', WITH GPM-350, PP-5250, DP=200-400, DIFFERENTIAL SUDDENLY INCREASED 400 PSI THEN TORQUE BEGAN TO INCREASE AND STALL OUT DRILL PIPE. SUBSEQUENTLY THE DRILL PIPE PRESSURE DROPPED FROM 6,100 PSI TO 4,950 PSI(PREVIOUS OFF BOTTOM PSI-5250 PSI).TORQUE REDUCED FROM 20-25K TO 11-15K. PICKED UP OFF BOTTOM AND RESET PARAMATERS. SLOWLY SET WEIGHT ON BIT AND DIFFERENTIAL REMAINED STATIC. PICKED UP OFF BOTTOM AND DECISION WAS MADE TO POOH.
RAINIER 1H | 26 | 2021-06-02 10:30 | 2021-06-02 19:30 | 9 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 21.1 | 18577 | 18577 | 0 | BACKREAM OUT OF HOLE F/18,577' T/13,000'. GPM-350, PP-4850, RPM-70, TQ=14-27K. CASING PSI WHILE CIRCULATING=100-500 CASING PSI WHILE DURING CONNECTION=500-800
RAINIER 1H | 26 | 2021-06-02 19:30 | 2021-06-02 20:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 21.15 | 18577 | 18577 | 0 | CIRCULATE BOTTOMS UP @ 13,000'. GPM-355, PP-4600, RPM-70, TQ=11-15K, MAX GAS-1878u CSG PSI WHILE CIRC-200-450 PSI CSG WHILE AFTER CIRC WITH PUMPS OFF-700-775 PSI.
RAINIER 1H | 26 | 2021-06-02 20:30 | 2021-06-02 21:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.19 | 18577 | 18577 | 0 | STRIP OUT F/13,000' T/11,974'. PUMPING CALCULATED STROKES ON BACKSIDE. CSG PSI WHILE STRIPPING-700-800.
RAINIER 1H | 26 | 2021-06-02 21:30 | 2021-06-03 | 2.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 21.29 | 18577 | 18577 | 0 | CIRCULATE BOTTOMS UP @ 11,974' GPM-340, PP-4150, RPM-70, TQ=9-12K, MAX GAS-1134u. CSG PSI WHILE CIRC-200-600 PSI. SHUT DOWN MUD PUMPS AND OBSERVE CSG PSI-BUILT TO 775 PSI. PUMP AND SPOT 150 BBL 17 PPG OBM MUD CAP @ 11,974' FOR AN ADDITIONAL 1023 HYDROSTATIC PSI.
RAINIER 1H | 26 | 2021-06-03 | 2021-06-03 01:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.35 | 18577 | 18577 | 0 | STRIP OUT F/11,974' T/8,600'. PUMPING CALCULATED FILL DOWN BACKSIDE WITH 11 PPG OBM.
RAINIER 1H | 26 | 2021-06-03 01:30 | 2021-06-03 02:30 | 1 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 21.4 | 18577 | 18577 | 0 | PERFORM FLOW CHECK-NO FLOW. L/D DRILL PIPE F/8,600' T/8,280'. PROPER FILLS WHILE TRIPPING OUT OF HOLE ON TRIP TANK.
RAINIER 1H | 26 | 2021-06-03 02:30 | 2021-06-03 03:30 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 21.44 | 18577 | 18577 | 0 | REPLACE HYDRAULIC HOSE ON ST-80. AFTER REPLACING HYDRAULIC HOSE ST-80 LOWER JAW STILL WOULD NOT FUNCTION. AFTER FURTHER INSPECTION, JAW WAS FOUND TO BE CRACKED. NOTE: WHILE WORKING ON ST-80, WELL GRADUALLY GAINED 2.2 BBLS IN THE TRIP TANK. SHUT WELL IN AND MONITORED CASING PSI. CASING PSI DID NOT BUILD.
RAINIER 1H | 26 | 2021-06-03 03:30 | 2021-06-03 06:00 | 2.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 21.54 | 18577 | 18577 | 0 | L/D DRILL PIPE WHILE STRIPPING F/8,280' T/6,200'. PUMPING CALCULATED FILL 17 PPG OBM DOWN BACKSIDE FOR A TOTAL OF 30 BBLS (AN ADDITIONAL 200 PSI HYDROSTATIC PSI). PERFORM FLOW CHECK-NO FLOW. FILL BACKSIDE WITH 11.0 PPG OBM ON TRIP TANK. NOTE: LAYING DOWN DRILL PIPE USING TONGS AND CHAIN TONGS DUE TO ST-80 BEING INOPERATIVE.
RAINIER 1H | 27 | 2021-06-03 06:00 | 2021-06-03 06:30 | 0.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 21.56 | 18577 | 18577 | 0 | L/D DP F/6,200' T/6,045'. PROPER FILLS ON TRIP OUT.
RAINIER 1H | 27 | 2021-06-03 06:30 | 2021-06-03 07:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 21.58 | 18577 | 18577 | 0 | PERFORM FLOW CHECK-NO FLOW. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
RAINIER 1H | 27 | 2021-06-03 07:00 | 2021-06-03 09:30 | 2.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 21.69 | 18577 | 18577 | 0 | L/D DRILL PIPE T/5,112'. PROPER FILLS ON TRIP OUT.
RAINIER 1H | 27 | 2021-06-03 09:30 | 2021-06-03 10:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 21.71 | 18577 | 18577 | 0 | RIG SERVICE
RAINIER 1H | 27 | 2021-06-03 10:00 | 2021-06-03 11:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.77 | 18577 | 18577 | 0 | TRIP OUT T/3,084'. PROPER FILLS ON TRIP OUT.
RAINIER 1H | 27 | 2021-06-03 11:30 | 2021-06-03 12:00 | 0.5 | U | PRDHLLT | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 21.79 | 18577 | 18577 | 0 | WHILE TRIPPING, WELL BEGAN TO FLOW. SHUT WELL IN AND CASING PRESSURE INCREASED TO 220 PSI. PUMP 40 BBLS 17 PPG OBM DOWN ANNULUS AND CASING PSI REDUCED TO 0 PSI. WHILE PUMPING KILL MUD CASING PSI BUILT TO MAX 275 PSI BEFORE BREAKING OVER.
RAINIER 1H | 27 | 2021-06-03 12:00 | 2021-06-03 15:00 | 3 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 21.92 | 18577 | 18577 | 0 | TRIP OUT OF HOLE TO BHA PUMPING CALCULATED FILL
RAINIER 1H | 27 | 2021-06-03 15:00 | 2021-06-03 16:00 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 21.96 | 18577 | 18577 | 0 | LAY DOWN MWD TOOL, REMOVE UBHO SUB FROM ASSEMBLY, SET BACK IN DERRICK THE MONELS AND MUD MOTOR. MUD MOTOR APPEARED TO HAVE A BLOWN TRANSMISSION(ABLE TO TURN BIT BOX BY HAND, DID NOT DRAIN). BIT HAD MULTIPLE CHIPPED AND BROKEN CUTTERS, STILL IN GAUGE.
RAINIER 1H | 27 | 2021-06-03 16:00 | 2021-06-03 17:00 | 1 | U | PRDHLLT | TRIP | BOP | TRIP FOR BOP | 22 | 18577 | 18577 | 0 | PICK UP BTI VALVE, CROSSOVER AND 30 STANDS DS42 DRILL PIPE
RAINIER 1H | 27 | 2021-06-03 17:00 | 2021-06-03 19:00 | 2 | U | PRDHLLT | TRIP | BOP | TRIP FOR BOP | 22.08 | 18577 | 18577 | 0 | PICK UP, MAKE UP STORM PACKER, AND RIH T/ 180'. SET PACKER, RELEASE, AND PICK UP ABOVE PACKER. SHUT WELL IN AND TEST T/1,500 PSI-GOOD. L/D DP AND STINGER.
RAINIER 1H | 27 | 2021-06-03 19:00 | 2021-06-04 04:30 | 9.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 22.48 | 18577 | 18577 | 0 | L/D DRILL PIPE IN MOUSEHOLE.
RAINIER 1H | 27 | 2021-06-04 04:30 | 2021-06-04 05:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 22.5 | 18577 | 18577 | 0 | REPLACE BLOWN HYDRAULIC HOSE ON ST-80.
RAINIER 1H | 27 | 2021-06-04 05:00 | 2021-06-04 05:30 | 0.5 | U | PRDHLLT | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 22.52 | 18577 | 18577 | 0 | CHANGE OUT ST-80 DIES.
RAINIER 1H | 27 | 2021-06-04 05:30 | 2021-06-04 06:00 | 0.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 22.54 | 18577 | 18577 | 0 | LAY DOWN DRILL PIPE IN MOUSEHOLE. 45 STANDS CURRENTLY LEFT IN DERRICK
RAINIER 1H | 28 | 2021-06-04 06:00 | 2021-06-04 14:30 | 8.5 | U | PRDHLLT | TRIP | LDDP | LAY DOWN DRILLPIPE | 22.9 | 18577 | 18577 | 0 | LAY DOWN DRILL PIPE OUT OF DERRICK. NOTE: USING TONGS TO BREAK DRILL PIPE DUE TO EXCESSSIVE TORQUE.
RAINIER 1H | 28 | 2021-06-04 14:30 | 2021-06-04 15:00 | 0.5 | U | PRDHLLT | RURD | RDEQP | RIG DOWN EQUIPMENT | 22.92 | 18577 | 18577 | 0 | CLEAN RIG FLOOR AND PREP TO TEST BOPE
RAINIER 1H | 28 | 2021-06-04 15:00 | 2021-06-04 19:30 | 4.5 | U | PRDHLLT | BOP | TSTBOP | PRESSURE TEST BOP | 23.1 | 18577 | 18577 | 0 | HELD PJSM WITH TESTERS AND TEST BOPE. TESTED ALL CHOKE MANIFOLD VALVES OFFLINE WHILE L/D DP IN MOUSEHOLE. INSTALL SHORT TEST PLUG WITH 4.5" DP AND TEST LOWER PIPE RAMS T/250 LOW / 10K HIGH(GOOD) AND UPPER PIPE RAMS 250 LOW / 10K HIGH (FAILED). TEST ANNULAR TO 250 LOW / 3500 HIGH, TEST BACK TO MUD PUMPS 250 LOW / 7 K HIGH. REMOVE 4.5" DP AND INSTALL 5.5" DP AND ATTEMPT TO TEST LOWER PIPE RAMS-FAILED, ATTEMPT TO TEST UPPER PIPE RAMS-FAILED
RAINIER 1H | 28 | 2021-06-04 19:30 | 2021-06-04 21:00 | 1.5 | U | PRDHLLT | RURD | RUEQP | RIG UP EQUIPMENT | 23.17 | 18577 | 18577 | 0 | CHANGE OUT SAVER SUB FROM DS42 TO CET43
RAINIER 1H | 28 | 2021-06-04 21:00 | 2021-06-05 01:00 | 4 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 23.33 | 18577 | 18577 | 0 | BREAK BONNET BOLTS ON BOTH UPPER AND LOWER RAMS DOORS AND OPEN. REMOVE RAMS AND REPLACE INSERTS AND TOP SEALS IN BOTH RAMS. INSTALL RAMS AND INSTALL NEW BONNET SEALS. CLOSE DOORS AND TIGHTEN BONNET BOLTS.
RAINIER 1H | 28 | 2021-06-05 01:00 | 2021-06-05 04:00 | 3 | U | PRDHLLT | BOP | TSTBOP | PRESSURE TEST BOP | 23.46 | 18577 | 18577 | 0 | INSTALL 4.5' TEST JOINT AND TEST UPPER AND LOWER VBR PIPE RAMS TO 250 LOW / 10K HIGH. REMOVE 4.5" DP AND INSTALL 5.5" DP AND TEST UPPER AND LOWER VBR PIPE RAMS TO 250 LOW / 10K HIGH. INSTALL CHECK VALVE AND TEST 250 LOW / 10K HIGH. TEST FLOOR VALVES TO 250 LOW / 10K HIGH. REMOVE DP AND INSTALL WEATHERFORD TEST PLUG AND TEST ORBIT VALVE TO 250 LOW / 1500 HIGH. RIG DOWN TESTERS
RAINIER 1H | 28 | 2021-06-05 04:00 | 2021-06-05 04:30 | 0.5 | U | PRDHLLT | RURD | RUEQP | RIG UP EQUIPMENT | 23.48 | 18577 | 18577 | 0 | INSTALL WEAR BUSHING
RAINIER 1H | 28 | 2021-06-05 04:30 | 2021-06-05 05:30 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 23.52 | 18577 | 18577 | 0 | LAY DOWN DIRECTIONAL BHA. MONELS, MOTOR, UBHO, PONY COLLARS, AND TOMAX TOOL.
RAINIER 1H | 28 | 2021-06-05 05:30 | 2021-06-05 06:00 | 0.5 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 23.54 | 18577 | 18577 | 0 | PICK UP AND RACK BACK CET43 DRILL PIPE.
RAINIER 1H | 29 | 2021-06-05 06:00 | 2021-06-05 10:00 | 4 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 23.71 | 18577 | 18577 | 0 | PICK UP 4.5" CET43 DRILL PIPE AND RACK BACK IN DERRICK.
RAINIER 1H | 29 | 2021-06-05 10:00 | 2021-06-05 12:30 | 2.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 23.81 | 18577 | 18577 | 0 | PICK UP AND RACK BACK IN DERRICK. 6.75" SECURITY GTD64M SER 13594950 JETS 6/18S TFA: 1.491), 5 1/2", 6/7L, 8.8 STG @ 2.12° SLICK; (HPT AVACO RUBBERS) .68 REV/GAL; 4.09' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX, X/O XT-39 P x DS 42B. BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD (TEST GOOD), M/U BIT, AND RACK BACK IN DERRICK.
RAINIER 1H | 29 | 2021-06-05 12:30 | 2021-06-05 13:30 | 1 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 23.85 | 18577 | 18577 | 0 | SLIP AND CUT 10 WRAPS OF DRILLING LINE.
RAINIER 1H | 29 | 2021-06-05 13:30 | 2021-06-05 14:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 23.88 | 18577 | 18577 | 0 | RIG SERVICE
RAINIER 1H | 29 | 2021-06-05 14:00 | 2021-06-05 14:30 | 0.5 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 23.9 | 18577 | 18577 | 0 | CLEAN AND ORGANIZE RIG FLOOR, BRING UP TOOLS TO STING INTO RTTS
RAINIER 1H | 29 | 2021-06-05 14:30 | 2021-06-05 15:30 | 1 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 23.94 | 18577 | 18577 | 0 | MAKE UP LATCH TOOL FOR RTTS, GO IN HOLE WITH TWO STANDS FROM DERRICK, INSTALL FULL OPENING SAFETY VALVE 5 JTS IN, THEN LATCH ONTO RTTS, PUMP DOWN DRILL STRING TO CHECK PRESSURE, 10 STKS(26 GPM) 70 PSI, 15 STKS(39 GPM) 128 PSI, 20 STKS(52 GPM) 205 PSI, 30 STKS(79 GPM) 255 PSI, SHUT DOWN PUMP
RAINIER 1H | 29 | 2021-06-05 15:30 | 2021-06-05 23:30 | 8 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 24.27 | 18577 | 18577 | 0 | OPERATIONS TO PUMP DOWN DRILL STRING SO RTTS COULD BE RETRIEVED. THE MUD PUMP THAT WAS LINED UP ON THE ANNULUS WAS ENGAGED INSTEAD OF THE MUD PUMP LINED UP ON STANDPIPE. THE INSIDE VALVE ON THE KILL LINE WAS CLOSED INSTEAD OF THE OUTSIDE MANUAL VALVE. KILL LINE PRESSURE IMMEDIATELY WENT TO 3550 PSI BEFORE MUD PUMP COULD BE SHUT DOWN. THE PRESSURE FROM THE MUD PUMP TO THE KILL LINE WAS BLED OFF LEAVING TRAPPED PRESSURE BETWEEN THE INSIDE MANUAL VALVE CLOSEST TO BOP AND THE CHECK VALVE. ATTEMPTED TO OPEN INSIDE MANUAL VALVE WHEN VALVE STEM BROKE NOT ALLOWING PRESSURE TO BE RELEASED. RACK BACK 2 STANDS AND L/D STINGER. TECH AND TOOL WITH MYER TO RELEASE PRESSURE WAS DISPATCHED TO RIG. TWO NEW KILL LINE VALVES FROM PATTERSON UTI YARD WERE ALSO LOADED UP ONTO A HOT SHOT TRUCK AND BROUGHT TO RIG SITE. VALVES SHOWED UP @ 19:30 HRS TECH SHOWED UP @ 19:25 HRS BOP TESTERS SHOWED UP @ 19:40 HRS MYER TECH INSERTED BLEED OFF TOOL INTO GREASE FITTING OF MANUAL VALVE TO BLEED OFF PRESSURE. NO PRESSURE WAS SEEN SO VALVE HANDLE FLANGE WAS LOOSENED SLOWLY TO CHECK FOR ANY TRAPPED PRESSURE. NO TRAP PRESSURE WAS SEEN SO FLANGE WAS COMPLETELY REMOVED AND VALVE STEM PULLED. BAD VALVES WERE REMOVED AND NEW VALVES WERE INSTALLED. RIGGED UP TESTING UNIT AFTER VALVES WERE INSTALLED TO TEST VALVES TO 250 PSI LOW AND 10K PSI HIGH. VALVES TESTED PROPERLY AND TESTING UNIT WAS THEN RIGGED DOWN. GO IN HOLE WITH TWO STANDS FROM DERRICK WITH FULL OPENING SAFETY VALVE 5 JTS IN, THEN LATCH ONTO RTTS BY TURNING 22 REVOLUTIONS TO THE RIGHT AT 10 RPM WITH 1K TORQUE.
RAINIER 1H | 29 | 2021-06-05 23:30 | 2021-06-06 | 0.5 | U | PRDHLLT | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 24.29 | 18577 | 18577 | 0 | ESTABLISH INJECTION RATES. PUMP @ 26 GPM. TOOK 16 STROKES TO FILL PIPE. PIPE PRESSURED TO 175 PSI AND BEGAN TO BREAK OVER, SHUT MUD PUMP DOWN AND PRESSURE EQUALIZED T/75 PSI. SHUT ANNULAR AND VERIFIED CORRECT LINE UP FOR PUMPING DOWN KILL LINE. PUMP @ 13 GPM AND PRESSURED UP ANNULUS T/225 PSI. PULLED 120K (5') AND CASING PRESSURE FELL TO 0 PSI. OPENED UP CHOKE AND MONITORED FLOW-NO FLOW.
RAINIER 1H | 29 | 2021-06-06 | 2021-06-06 01:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 24.33 | 18577 | 18577 | 0 | CIRC BTMS UP @ 157 GPM, PP-335, CP=0-75 PSI, FLARE=0-1', FLOW=10-14%, CHOKE=50-60%. HEAVIEST MW SEEN-12.6
RAINIER 1H | 29 | 2021-06-06 01:00 | 2021-06-06 03:00 | 2 | U | PRDHLLT | TRIP | BOP | TRIP FOR BOP | 24.42 | 18577 | 18577 | 0 | POOH 2 STANDS AND L/D PACKER, RACK BACK 30 STANDS DS42 DP ON LEFT SIDE OF DERRICK.
RAINIER 1H | 29 | 2021-06-06 03:00 | 2021-06-06 03:30 | 0.5 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 24.44 | 18577 | 18577 | 0 | CASING PSI BUILT TO 150 PSI WHILE PREPARING TO INSTALL WEAR BUSHING. BULLHEAD 30 BBLS 17 PPG OBM DOWN ANNULUS. CASING PSI BUILT T/200 PSI BEFORE BREAKING OVER. SHUT MUD PUMPS DOWN, CASING PSI=0 PSI. PERFORM FLOW CHECK-NO FLOW.
RAINIER 1H | 29 | 2021-06-06 03:30 | 2021-06-06 04:00 | 0.5 | U | PRDHLLT | RURD | RUEQP | RIG UP EQUIPMENT | 24.46 | 18577 | 18577 | 0 | INSTALL WEAR BUSHING
RAINIER 1H | 29 | 2021-06-06 04:00 | 2021-06-06 04:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 24.48 | 18577 | 18577 | 0 | P/U BHA OUT OF DERRICK AND RIH
RAINIER 1H | 29 | 2021-06-06 04:30 | 2021-06-06 06:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 24.54 | 18577 | 18577 | 0 | TRIP IN HOLE WITH DRILL PIPE. PICK UP 2 STANDS AND PICK UP REAMER. PICK UP AGITATOR 26 STANDS LATER. PSI BEFORE AGITATOR-1541. PSI AFTER-2020.
RAINIER 1H | 30 | 2021-06-06 06:00 | 2021-06-06 06:30 | 0.5 | U | PRDHLLT | LOG | MWD | MWD | 24.56 | 18577 | 18577 | 0 | TEST MWD-GOOD. NOTE: LOST APPROXIMATELY 43 BBLS WHILE TESTING AGITATOR AND MWD.
RAINIER 1H | 30 | 2021-06-06 06:30 | 2021-06-06 07:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 24.58 | 18577 | 18577 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
RAINIER 1H | 30 | 2021-06-06 07:00 | 2021-06-06 10:00 | 3 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 24.71 | 18577 | 18577 | 0 | P/U DRILL PIPE F/2,822' T/5,990'. NO RETURNS WHILE PICKING UP DRILL PIPE-APPROXIMATELY 22 BBLS.
RAINIER 1H | 30 | 2021-06-06 10:00 | 2021-06-06 10:30 | 0.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 24.73 | 18577 | 18577 | 0 | PICK UP 2ND AGITATOR AND TEST W/131 GPM. PSI BEFORE-1030 PSI / PSI AFTER-1266 NOTE: LOST APPROXIMATELY 38 BBLS.
RAINIER 1H | 30 | 2021-06-06 10:30 | 2021-06-06 16:30 | 6 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 24.98 | 18577 | 18577 | 0 | P/U DRILL PIPE F/5,990' T/12,000'. NO RETURNS WHILE PICKING UP DRILL PIPE-APPROXIMATELY-41 BBLS
RAINIER 1H | 30 | 2021-06-06 16:30 | 2021-06-06 18:00 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 25.04 | 18577 | 18577 | 0 | CIRCULATE OUT MUD CAP @ 12,000' THROUGH CHOKE. PUMP 30 BBLS 10.2 PPG OBM TO LIGHTEN ANNULUS. GPM-150, PP-1460, CHOKE- 0% / 75%. MAX GAS-215. HEAVIEST MW SEEN-14.0 PPG. SHUT MUD PUMPS DOWN AND CASING PSI INCREASED TO 484 PSI.
RAINIER 1H | 30 | 2021-06-06 18:00 | 2021-06-06 18:30 | 0.5 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 25.06 | 18577 | 18577 | 0 | P/U DRILL PIPE WHILE STRIPPING F/12,000' T/12,195'. BLEEDING OFF CALCULATED DISPLACEMENT INTO TRIP TANK. CASING PSI WHILE STRIPPING DP=550-650 PSI
RAINIER 1H | 30 | 2021-06-06 18:30 | 2021-06-06 19:30 | 1 | U | PRDHLLT | LOG | DIRSVY | DIRECTIONAL / SINGLE / MULTI | 25.1 | 18577 | 18577 | 0 | ORIENT TOOLFACE @ 12,195' TO 140G AND TRIP IN HOLE THROUGH SIDETRACK. PUMP UP SVY AND VERIFY IN ST01 @ 12,734'
RAINIER 1H | 30 | 2021-06-06 19:30 | 2021-06-06 22:00 | 2.5 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 25.21 | 18577 | 18577 | 0 | P/U DRILL PIPE WHILE STRIPPING F/12,195' T/13,612'. BLEEDING OFF CALCULATED DISPLACEMENT INTO TRIP TANK. CASING PSI WHILE STRIPPING=100-450 PSI NOTE: W/R THROUGH TIGHT SPOTS @ (13,177'-13,208') (13,219'-13,240') (13,278'-13,303')
RAINIER 1H | 30 | 2021-06-06 22:00 | 2021-06-07 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 25.29 | 18577 | 18577 | 0 | CASING PSI BEGAN DECREASING AS TRIPPED IN HOLE. CIRCULATE BOTTOMS UP @ 13,612'. GPM-240, PP-3000, RPM-30, TQ=12-14K, CHOKE=0% / 55%, MAX GAS-1515u, FLARE=4-8', MAX CASING DURING CIRCULATION-57 PSI. NOTE: LOST APPROXIMATELY 60 BBLS DURING CIRCULATION. CASING PSI WHILE STRIPPING BEFORE CIRCULATION-135 PSI. CASING PSI WHILE STRIPPING AFTER CIRCULATION-500 PSI
RAINIER 1H | 30 | 2021-06-07 | 2021-06-07 05:00 | 5 | U | PRDHLLT | TRIP | PUDP | PICK UP DRILLPIPE | 25.5 | 18577 | 18577 | 0 | PICK UP DRILL PIPE F/13,612' T/18,060'. BLEEDING OFF CALCULATED DISPLACEMENT INTO TRIP TANK. CASING PSI WHILE STRIPPING=100-450 PSI
RAINIER 1H | 30 | 2021-06-07 05:00 | 2021-06-07 05:30 | 0.5 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 25.52 | 18577 | 18577 | 0 | WASH AND REAM F/18,060' T/18,313'. GPM-340, PP-5500, RPM-80, TQ=14-17K. CASING PSI WHILE CIRC=0 PSI CASING PSI DURING CONNECTIONS=50-75 PSI
RAINIER 1H | 30 | 2021-06-07 05:30 | 2021-06-07 06:00 | 0.5 | U | PRDHLLT | FMSHW | GSSHW | GAS SHOWS | 25.54 | 18577 | 18577 | 0 | CIRCULATE OUT GAS @ 18,313'. GPM-350, PP-5500, RPM-40 TQ=13-15K, MAX GAS-1883u. MAX CASING PSI-1252
RAINIER 1H | 31 | 2021-06-07 06:00 | 2021-06-07 07:30 | 1.5 | U | PRDHLLT | FMSHW | GSSHW | GAS SHOWS | 25.6 | 18577 | 18577 | 0 | WASH & REAM F/18,309 T/18,577', GPM-350 SPP-5670 TQ-16K RPM-75/80 CP-400/850 FL-10/30'
RAINIER 1H | 31 | 2021-06-07 07:30 | 2021-06-07 10:00 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 25.71 | 18577 | 18740 | 65.2 | ROT DRLG (163' IN 2.58 HRS @ 63.1 FPH) GPM-350 SPP-5100/5700 RPM-80 MMRPM-238 TQ-18/20K WOB-18/20K CP-0/650 FL-0/25' CASING PSI WHILE DRILLING=0-800 CASING PSI DURING CONNECTIONS=750-900 PUMPING 10 BBL 6 PPB GRAPHITE SWEEPS AS NEEDED FOR TORQUE SWEEP CONTENTS: 6 PPB GRAPHITE Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6-1-21 3:13 a.m
RAINIER 1H | 31 | 2021-06-07 10:00 | 2021-06-07 13:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 25.83 | 18740 | 18808 | 22.7 | SLD DRLG (68' IN 2.92 HRS @ 23.3 FPH) GPM-350/375 SPP-5640/6100 DIFF-200/400 WOB-15/20 CP--0/450 FL-0/20' SLIDE DEPTHS: F/18583 T/18596 13' TF-180 07:45-08:10 F/18695 T/18715 20' TF-180 09:20-10:30 (WHILE SLIDING-DRILLPIPE BACKOFF OCCURRED 1000' +/- BELOW ROTARY. STAB BACK INTO JOINT AND TORQUE ON BOTTOM WITH 32K. F/18743 T/18758 15' TF-180 11:00-11:50 F/18788 T/18808 20' TF-180 12:30-13:00
RAINIER 1H | 31 | 2021-06-07 13:00 | 2021-06-07 14:00 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 25.87 | 18808 | 18876 | 68 | ROT DRLG (68' IN 1 HRS @ 68 FPH) GPM-350, SPP-5100/5700, RPM-80, MMRPM-238, TQ-18/20K, WOB-18/20K, FL-0/25' CASING PSI WHILE DRILLING=0-850 CASING PSI DURING CONNECTIONS=750-900 PUMPING 10 BBL 6 PPB GRAPHITE SWEEPS AS NEEDED FOR TORQUE SWEEP CONTENTS: 6 PPB GRAPHITE Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6-1-21 3:13 a.m
RAINIER 1H | 31 | 2021-06-07 14:00 | 2021-06-07 14:30 | 0.5 | P | PRDHLLT | WAIT | WORD | WAIT ON ORDERS | 25.9 | 18876 | 18876 | 0 | CIRCULATE AT 225 GPM WHILE WAITING ON ORDERS FROM GEOLOGIST AND COOL DOWN MWD TOOL. FROM 333 F. TO 327 F.
RAINIER 1H | 31 | 2021-06-07 14:30 | 2021-06-07 15:30 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 25.94 | 18876 | 18956 | 80 | ROT DRLG (80' IN 1 HRS @ 80 FPH) GPM-350, SPP-5100/5700, RPM-80, MMRPM-238, TQ-18/20K, WOB-18/20K, FL-0/25' PUMPING 10 BBL 6 PPB GRAPHITE SWEEPS AS NEEDED FOR TORQUE CASING PSI WHILE DRILLING=200-500 CASING PSI DURING CONNECTIONS=750-900 SWEEP CONTENTS: 6 PPB GRAPHITE Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6-1-21 3:13 a.m
RAINIER 1H | 31 | 2021-06-07 15:30 | 2021-06-07 16:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 25.96 | 18956 | 18971 | 30 | SLD DRLG (15' IN 0.5 HRS @ 30 FPH) GPM-350/375 SPP-5640/6100 DIFF-200/400 WOB-15/20 CP--150/650 FL-0/20' SLIDE DEPTHS: F/18942 T/18957 15' TF-180 14:50-16:00
RAINIER 1H | 31 | 2021-06-07 16:00 | 2021-06-07 17:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 26 | 18971 | 18971 | 0 | RIG SERVICE AND INSPECT TOP DRIVE
RAINIER 1H | 31 | 2021-06-07 17:00 | 2021-06-07 20:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 26.12 | 18971 | 19338 | 122.3 | ROT DRLG (367' IN 3.15 HRS @ 117 FPH) GPM-350, SPP-5100/6000, DP=700-900, RPM-80, MMRPM-238, TQ-18/20K, WOB-18/20,K, FL-0/25' CASING PSI WHILE DRILLING=200-500 CASING PSI DURING CONNECTIONS=750-900 PUMPING 10 BBL 6 PPB GRAPHITE SWEEPS AS NEEDED FOR TORQUE SWEEP CONTENTS: 6 PPB GRAPHITE Plan 9 – 12245’ TVD at 0 VS with 87 deg INC 10’ above/ 5’ below-6-1-21 3:13 a.m
RAINIER 1H | 31 | 2021-06-07 20:00 | 2021-06-07 21:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 26.17 | 19338 | 19350 | 12 | SLD DRLG (12' IN .85 HRS @ 14 FPH) GPM-350 SPP-5000/5300, DIFF-200/400, WOB-15/20, FL-0/20' CASING PSI WHILE DRILLING=200-500 CASING PSI DURING CONNECTIONS=750-900 SLIDE DEPTHS: F/19131' T/19143' 12' TF-20R 1845-1936
RAINIER 1H | 31 | 2021-06-07 21:00 | 2021-06-08 | 3 | U | PRDHLLT | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 26.29 | 19350 | 19350 | 0 | TOP DRIVE ALIGNMENT BOLTS SHEARED WHEN TOP DRIVE RAPIDLY LOST TORQUE DUE TO DRILL PIPE BACKOFF. 2 TOP DRIVE ADJUSTMENT BOLTS WERE FOUND TO BE SHEARED. WHEN PARTS AND TOP DRIVE TECH ARRIVED, INSTALLED PUMP IN SUB INTO DRILL PIPE AND CHANGED OUT BOLTS ON TOP DRIVE.
RAINIER 1H | 31 | 2021-06-08 | 2021-06-08 04:30 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 26.48 | 19350 | 19830 | 106.7 | ROT DRLG (480' IN 4.33 HRS @ 111 FPH) RPM-80, MMRPM-238/218, GPM-340/320 SPP-5100/6000, 4500/5500, DIFF-800/1000, TQ-16/23K, FL-0/25' CASING PSI WHILE DRILLING=0-550 PSI CASING PSI DURING CONNECTIONS=500-700 PSI HOLE LOSING APPROXIMATELY 25-75 BBLS/HR. REDUCED GPM T/320 TO REDUCE HOLE LOSSES. CUTTING MW BACK TO 11.1 PPG. PUMPING 10 BBL 6 PPB GRAPHITE SWEEPS AS NEEDED FOR TORQUE SWEEP CONTENTS: 6 PPB GRAPHITE Plan 9 – 12200’ TVD at 0 VS with 86.5 deg INC 10’ above/ 5’ below (6/7/2021 22:03)
RAINIER 1H | 31 | 2021-06-08 04:30 | 2021-06-08 06:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 26.54 | 19830 | 19860 | 20 | SLIDE 30' IN 1.67 HR @ 18 FPH) MMRPM-238/218, GPM-340/320, SPP-5100/6000, 4500/5000, DIFF-300/500, FL-0/25'. SLIDE DEPTHS: F/19361' T/19376' 15' TF-180 0044-0124 F/19831' T/19846' 15' TF-20RT 0445-0545
RAINIER 1H | 32 | 2021-06-08 06:00 | 2021-06-08 12:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 26.79 | 19860 | 20647 | 131.2 | ROT DRLG (787' IN 6.33 HRS @ 124.26 FPH) GPM-320, PP-4500/ 5500, DIFF-800/1000, RPM-80, MMRPM-218, TQ-16/23K, FL-0/25'. CASING PSI WHILE DRILLING=0-950 PSI CASING PSI DURING CONNECTIONS=500-1200 PSI HOLE LOSING APPROXIMATELY 25-75 BBLS/HR. REDUCED GPM T/320 TO REDUCE HOLE LOSSES. INCREASED MW TO 11.2 PPG. PUMPING 10 BBL 6 PPB GRAPHITE SWEEPS AS NEEDED FOR TORQUE SWEEP CONTENTS: 6 PPB GRAPHITE Plan 9 – 12200’ TVD at 0 VS with 86.5 deg INC Window: 5' Above / 10' Below (6/8/2021 10:26)
RAINIER 1H | 32 | 2021-06-08 12:00 | 2021-06-08 13:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 26.83 | 20647 | 20659 | 12 | SLIDE 12' IN 0.67 HR @ 18 FPH) GPM-320, PP=4500-4900, DP=200-400, MMRPM-218, FL-5/25' CASING PSI WHILE DRILLING=0-950 PSI CASING PSI DURING CONNECTIONS=500-1200 PSI SLIDE DEPTHS: F/20303' T/20315' TF-HS 12' 09:40-10:20
RAINIER 1H | 32 | 2021-06-08 13:00 | 2021-06-08 13:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 26.83 | 20659 | 20659 |  | MILESTONE_TD WELL ON 6/8/2021 @ 13:00
RAINIER 1H | 32 | 2021-06-08 13:00 | 2021-06-08 16:30 | 3.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 26.98 | 20659 | 20659 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN, PUMPING 2 TANDEM 30 BBL HIGH VIS SWEEPS. CIRCULATE 3 B/U, RPM-80, SPM: 61/61/0, GPM-320, INITIAL SPP-4500 PSI/FINAL SPP-4300, CHOKES- 0% / 30-50%, FLARE-0'-30', MAX CASING PRESSURE=600 PSI, MAX GAS: 2341u. 1ST BTM UP START TQ=13-17K, END= 13-14K, P/U WT=240K, S/O=225K 2ND BTM UP END TQ=14-16K, P/U WT=265, S/O WT=230K 3RD BTM UP END TQ=14-17K, P/U WT=280K, S/O WT=230K
RAINIER 1H | 32 | 2021-06-08 16:30 | 2021-06-08 18:00 | 1.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 27.04 | 20659 | 20659 | 0 | WASH AND REAM OUT OF HOLE F/20,659' T/20,192'. GPM-320, PP-4350, RPM-65, TQ=14-25K, MMRPM-218. CASING PSI WHILE DRILLING=0-750 PSI CASING PSI DURING CONNECTIONS=800-1400 PSI
RAINIER 1H | 32 | 2021-06-08 18:00 | 2021-06-08 20:30 | 2.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 27.15 | 20659 | 20659 | 0 | RAISE MUD WEIGHT FROM 11.1 TO 11.3 DUE TO EXCESSIVE SHUT IN PRESSURES.
RAINIER 1H | 32 | 2021-06-08 20:30 | 2021-06-09 01:00 | 4.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 27.33 | 20659 | 20659 | 0 | WASH AND REAM OUT OF HOLE F/20,192' T/17,351'. GPM-320, PP-4350, RPM-65, TQ=14-25K, MMRPM-218. CASING PSI WHILE REAMING=300-500 PSI CASING PSI DURING CONNECTIONS=400-650 PSI
RAINIER 1H | 32 | 2021-06-09 01:00 | 2021-06-09 01:30 | 0.5 | P | PRDHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 27.35 | 20659 | 20659 | 0 | CHANG OUT ST-80 DIES
RAINIER 1H | 32 | 2021-06-09 01:30 | 2021-06-09 06:00 | 4.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 27.54 | 20659 | 20659 | 0 | WASH AND REAM OUT OF HOLE F/17,359' T/13,600'. GPM-320, PP-4350, RPM-65, TQ=14-25K, MMRPM-218. ATTEMPTED TO PULL ON ELEVATORS @ 15,700'-P/U-300, ROT-240K, MAX PULL 370K. HAD TO M/U LOOSE JOINTS @ 20,136', 20,066', 19,602' CASING PSI WHILE REAMING=300-500 PSI CASING PSI DURING CONNECTIONS=400-650 PSI
RAINIER 1H | 33 | 2021-06-09 06:00 | 2021-06-09 07:00 | 1 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 27.58 | 20659 | 20659 | 0 | CONTINUE WASHING AND REAMING OUT THE HOLE F/13,600’ T/13,000’, GPM-320, SPP-3800, RPM-40, TQ=10/13K, MMRPM-218, CHOKES- 31-34% / 0%, FLARE- 2'-4', MAX GAS-1941u, CASING PSI WHILE REAMING=200-500 PSI, CASING PSI DURING CONNECTIONS=400-650 PSI.
RAINIER 1H | 33 | 2021-06-09 07:00 | 2021-06-09 08:30 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 27.65 | 20659 | 20659 | 0 | PUMP 60 BBL LCM SWEEP AND CIRCULATED SWEEP OUT, RECIPROCATE PIPE, SPM-61/61, GPM-320, SPP-4100 PSI, RPM-40, CHOKES- 35-40% / 0%, NO FLARE, MAX GAS-521u, CSG PSI WHILE CIRC-150-350 PSI, CSG PSI AFTER CIRC WITH PUMPS OFF-530 PSI. LOSS 68 BBLS TO THE FORMATION WHILE CIRCULATING. NOTE: LCM SWEEP CONTENTS: 5 PPB CALCIUM CARB, 5 PPB FIRST RESPONSE, 5 PPB-MAGNAFIBER
RAINIER 1H | 33 | 2021-06-09 08:30 | 2021-06-09 10:00 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 27.71 | 20659 | 20659 | 0 | STRIP OUT OF HOLE F/13,000’ T/11,974’ WITH WET PIPE, PUMPING CALCULATED HOLE FILL 1.9 BBLS PER STAND DOWN THE BACKSIDE W/11.3 PPG OBM, MAX CASING PRESSURE= 592 PSI, AVG CASING PRESSURE= 530 PSI. NOTE: PULLED THROUGH SIDE TRACK 12,225' W/ 10/15K OVER PULL.
RAINIER 1H | 33 | 2021-06-09 10:00 | 2021-06-09 11:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 27.75 | 20659 | 20659 | 0 | CIRCULATE BOTTOMS UP, RECIPROCATE PIPE, SPM-61/61, GPM-320, SPP-4100 PSI, RPM-30, TRQ-8K/10K, CHOKES- 35-40% / 0%, NO FLARE, MAX CASING PRESSURE= 320 PSI, AVG CASING PRESSURE= 150 PSI, MAX GAS-500u, FINAL CASING PRESSURE= 129 PSI. SHUT IN AND MONITORED SHUT IN CASING PRESSURE, SICP= 575 PSI. NO LOSSES TO THE FORMATION.
RAINIER 1H | 33 | 2021-06-09 11:00 | 2021-06-09 12:00 | 1 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 27.79 | 20659 | 20659 | 0 | SPOT 139 BBL 16.8 PPG MUD CAP, FINAL CASING PRESSURE = 0 PSI, ADDED 300 PSI SAFETY FACTOR FOR VOLUME MUD CAP PUMPED, HYDROSTATIC PRESSURE BEFORE MUD CAP 6,913 PSI, HYDROSTATIC PRESSURE AFTER MUD CAP 7,813 PSI, TOP OF MUD CAP 8,953', BOTTOM OF MUD CAP 11,974'. NOTE: LOSS 26 BBLS TO THE FORMATION WHILE SPOTTING MUD CAP.
RAINIER 1H | 33 | 2021-06-09 12:00 | 2021-06-09 15:30 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 27.94 | 20659 | 20659 | 0 | STRIP OUT OF HOLE F/ 11,974' T/ 8,864' DRY, PUMPING CALCULATED HOLE FILLS .6 BBLS PER STAND DOWN BACKSIDE WITH 16.8 PPG KILL MUD. FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC. CONTINUE STRIPPING OUT OF HOLE F/ 8,864' T/6,037', PUMPING CALCULATED HOLE FILLS 1.9 BBSL PER STAND DOWN BACKSIDE WITH 11.3 PPG OBM, L/D ON DEMAND AGITATOR ON STAND 61.
RAINIER 1H | 33 | 2021-06-09 15:30 | 2021-06-09 19:00 | 3.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 28.08 | 20659 | 20659 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC, PUMP SLUG WITH NO RETURNS, STRIP OUT OF HOLE WITH DRY PIPE AND LAY DOWN 4 1/2" DRILL PIPE F/6,037'' T/3,000', PUMPING CALCULATED HOLE FILLS .6 BBSL PER STAND DOWN BACKSIDE WITH 11.3 PPG OBM.
RAINIER 1H | 33 | 2021-06-09 19:00 | 2021-06-09 21:30 | 2.5 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 28.19 | 20659 | 20659 | 0 | FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD, WELL WAS FLOWING 2-3 BPM, SHUT IN AND MONITOR SICP, SICP= 225 PSI, PUMP 114 OF 16.8 PPG KILL MUD DOWN THE BACK SIDE, INITIAL CASING PRESSURE = 225 PSI AND FINAL CASING PRESSURE= 0 PSI, MONITORED SICP, SICP= 0 PSI, FLOW CHECK WELL ON TRIP TANK THROUGH CHOKE MANIFOLD F/ 5 MINUTES, NO FLOW, OPEN ORBIT VALVE AND FLOW CHECK WELL ON TRIP TANK THROUGH FLOWLINE F/ 5 MINUTES, NO FLOW, WELL STATIC, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
RAINIER 1H | 33 | 2021-06-09 21:30 | 2021-06-09 22:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 28.23 | 20659 | 20659 | 0 | TRIP OUT THE HOLE F/3,000' T/BHA, PUMPING CALCULATED HOLE FILLS .6 BBLS PER STAND DOWN BACKSIDE WITH 11.3 PPG OBM, L/D STANDARD AGITATOR ON STAND 28.
RAINIER 1H | 33 | 2021-06-09 22:30 | 2021-06-10 00:30 | 2 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 28.31 | 20659 | 20659 | 0 | L/D TOP MONEL AND REMOVE MWD, L/D TOMAX THRUSTER, DRAIN MOTOR AND BREAK BIT, L/D BHA. NOTE: BIT GRADE: 1/1, MUD MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG.
RAINIER 1H | 33 | 2021-06-10 00:30 | 2021-06-10 01:00 | 0.5 | P | PRDHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 28.33 | 20659 | 20659 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELEVATORS, CLEAN ORGANIZE AND RIG FLOOR.
RAINIER 1H | 33 | 2021-06-10 01:00 | 2021-06-10 02:30 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 28.4 | 20659 | 20659 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT.
RAINIER 1H | 33 | 2021-06-10 02:30 | 2021-06-10 03:00 | 0.5 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 28.42 | 20659 | 20659 | 0 | PUMPED 50 BBL OF 16.9 PPG KWM DOWN ANNULUS WITH 0 CSG PRESSURE. FLOW CHECK WELL, WELL STATIC, NO FLOW (FLUID LEVEL BELOW WELLHEAD).
RAINIER 1H | 33 | 2021-06-10 03:00 | 2021-06-10 06:00 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 28.54 | 20659 | 20659 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS,MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TESTFLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/1,400', FILLING PIPE ON THE FLY, NO RETURNS. NOTE: HAD ONE BAD JOINT OF 5" (BAD PIN) RUN #9 REF #6 OF CASING TALLY
RAINIER 1H | 34 | 2021-06-10 06:00 | 2021-06-10 13:00 | 7 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 28.83 | 20659 | 20659 | 0 | CONITUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/1,400' T/9,133', FILLING PIPE ON THE FLY, NO RETURNS. NOTE: REMOVE TRIP NIPPLE AND INSTALLED ROTATING HEAD @ 3,019'.
RAINIER 1H | 34 | 2021-06-10 13:00 | 2021-06-10 14:30 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 28.9 | 20659 | 20659 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS.
RAINIER 1H | 34 | 2021-06-10 14:30 | 2021-06-10 18:30 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.06 | 20659 | 20659 | 0 | PICK UP AND RUN 5 1/2" 18# P110 ICY WEDGE 463 PRODUCTION CASING F/9,133' T/12,975', FILLING PIPE ON THE FLY, NO RETURNS.
RAINIER 1H | 34 | 2021-06-10 18:30 | 2021-06-10 21:30 | 3 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 29.19 | 20659 | 20659 | 0 | PUMP 14 BBLS 11.3 PPG OBM DOWN THE BACKSIDE WITH NO RETURNS. LINED UP TO PUMP DOWN CSG. STAGED UP PUMPS T/150 GPM WITH NO RETURNS, BEGAN ROTATING AND WORKING CASING TO ATTEMPT TO ESTABLISH RETURNS (30 RPM/15-20K FT-LBS). SHUT DOWN PUMPS AFTER 90 BBL LOST.
RAINIER 1H | 34 | 2021-06-10 21:30 | 2021-06-10 22:30 | 1 | P | PRDHLCSG | LCIRC | LCIRC | LOST CIRCULATION | 29.23 | 20659 | 20659 | 0 | WORK CASING WHILE BUILDING 9.5 PPG MUD TO FILL BACK SIDE. BULLHEAD 112 BBL OF 9.5 PPG MUD @ 40 SPM (104 GPM) ISICP=0 PSI, MAX SICP=1,650 PSI.
RAINIER 1H | 34 | 2021-06-10 22:30 | 2021-06-11 00:30 | 2 | U | PRDHLCSG | RIGMT | SVCMD | SERVICE MUD PUMPS / CIRC EQUIP | 29.31 | 20659 | 20659 | 0 | ATTEMPT TO CIRCULATE DOWN CASING, UNABLE TO OPEN IBOP DUE TO PRESSURE INSIDE CASING. BLED CASING PRESSURE TO 0 PSI WITH NO SUCCESS. SHUT WELL IN WITH SICP= 590 PSI. PRESSURED UP ON STAND PIPE TO 1,000 PSI. IBOP OPENED AND STABILIZED @ 1,100 PSI.
RAINIER 1H | 34 | 2021-06-11 00:30 | 2021-06-11 02:00 | 1.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 29.37 | 20659 | 20659 | 0 | CIRCULATE BU WHILE WORKING CASING TO ESTABLISH MUD COLUMN ON BACK SIDE. MWin= 10.8/MW out= 10.7 PPG NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 12.3 PPG WAS SURFACE, DIVERTED 100 BBLS OF 12.3 PPG T/14.3 PPG.
RAINIER 1H | 34 | 2021-06-11 02:00 | 2021-06-11 04:00 | 2 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 29.46 | 20659 | 20659 | 0 | SHUT IN WELL WITH SICP= 1,085 PSI, DECISION MADE OT RAISE MW TO 11.3 PPG. CC SURFACE TO SURFACE WITH 11.3 PPG.
RAINIER 1H | 34 | 2021-06-11 04:00 | 2021-06-11 06:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.54 | 20659 | 20659 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/12,975' T/14,400', STRIPPING IN WITH SICP= 700 PSI, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBL/STND). NOTE: WASH AND REAM FROM 13,180' TO 13,252' AND 13,760' TO 13,802' DUE TO TIGHT SPOT.
RAINIER 1H | 35 | 2021-06-11 06:00 | 2021-06-11 08:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.62 | 20659 | 20659 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/14,400' T/15,004', STRIPPING IN WITH SICP= 700 PSI, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBL/STAND). NOTE: WASH AND REAM FROM 14,880' TO 15,004' DUE TO TIGHT SPOT. LOSS 90 BBLS TO THE FORMATION.
RAINIER 1H | 35 | 2021-06-11 08:00 | 2021-06-11 09:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.67 | 20659 | 20659 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" PRODUCTION CASING F/15,004' T/15,794', STRIPPING IN WITH SICP= 150-200 PSI WITH CHOKES: 40% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBL/STAND). SICP DECREASED 0 PSI WITH CHOKES: 100% / 0% @ 15,147’ AND DISPLACEMENT REDUCED TO 0 BBL/STAND @ 15,764’.
RAINIER 1H | 35 | 2021-06-11 09:00 | 2021-06-11 11:00 | 2 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 29.75 | 20659 | 20659 | 0 | CIRCULATE BOTTOMS UP @ 15,794' WHILE RECIPROCATING PIPE DUE TO EXCESSIVE DRAG. STAGE PUMPS UP: SPM 80, GPM 210, RPM 20, TRQ 15K, SPP 1,600 PSI, STARTING CSG PSI 0, ENDING CSG PSI 275 PSI. P/U 280K, S/O 180K, ROT 230K. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 12.3 PPG WAS @ SURFACE, DIVERTED 190 BBLS OF 12.3 PPG T/14.4 PPG. LOSS 300 BBLS TO THE FORMATION.
RAINIER 1H | 35 | 2021-06-11 11:00 | 2021-06-11 12:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 29.79 | 20659 | 20659 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/15,794' T/16,282', STRIPPING IN WITH SICP= 800-950 PSI WITH CHOKES: 32% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBL/STAND).
RAINIER 1H | 35 | 2021-06-11 12:00 | 2021-06-11 23:00 | 11 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 30.25 | 20659 | 20659 | 0 | WASH AND REAM CASING F/16,282' T/20,620', SPP-1,850 PSI, GPM-210, SPM-80, RPM-20, TRQ-11/17K, DRAG 50K/80K NO MUD CUT, NO FLARE, MAX CASING PRESSURE= 283 PSI, MAX SICP= 845 PSI. LOSS 290 BBLS TO THE FORMATION.
RAINIER 1H | 35 | 2021-06-11 23:00 | 2021-06-11 23:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 30.27 | 20659 | 20659 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND RUN LANDING JOINT F/20,620' T/20,641.1'. GPM-210, LAND CASING ON HANGER W/140K LBS (W/O BLOCKS) @ 20,643.1'. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, RAN 9,132.99 (205 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1- X-OVER, 1 JOINT 5-1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING, RAN 11,457.49' (248 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING. FOR TOTAL OF 453 FULL JTS OF 5'' 18# P-110 ICY WEDGE 425 & 5.5" 23# P-110 ICY WEDGE 463. CASING SHOE @ 20,643.1' TOP OF FLOAT COLLAR @ 20,591.9' BOTTOM OF TOE SLEEVE VALVE @ 20,547.7' TOP OF TOE SLEEVE VALVE @ 20,522.4' TOP OF X-OVER @ 11,507.3' TOP OF MARKER JOINT ABOVE X-OVER @ 11,440.5' 2 JOINTS 5" LEFT OUT- 89.91' KICK OUT JOINT #6 WITH A BAD BOX 9 JOINTS 5.5" LEFT OUT- 407.31'
RAINIER 1H | 35 | 2021-06-11 23:30 | 2021-06-12 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 30.29 | 20659 | 20659 | 0 | RIG DOWN FRANK'S CRT AND INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 515 PSI.
RAINIER 1H | 35 | 2021-06-12 | 2021-06-12 02:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 30.37 | 20659 | 20659 | 0 | RIG DOWN CSG TOOLS WHILE CIRCULATING BOTTOMS UP, GPM-210, SPP-1,890 PSI, CHOKES- 57% / 0%, FLARE-0'-20', MAX CASING PRESSURE= 95 PSI, MAX GAS-1,789u. SICP=940 PSI. LOSS 210 BBLS. NOTE: HELD PJSM FOR CEMENT JOB.
RAINIER 1H | 35 | 2021-06-12 02:00 | 2021-06-12 06:00 | 4 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 30.54 | 20659 | 20659 | 0 | SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 5X5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 5 BPM 80 BBL 11.8 PPG WEIGHTED SPACER, 338 BBL 13.5 PPG 1135 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBL OF SUGAR WATER, FOLLOWED BY 386 BBL OF FRESH WATER @ 5 BPM (TOTAL OF 406 BBL DISPLACEMENT). NOTE: WHEN CEMENT HEAD WAS OPENED TO CASING AFTER LINE TEST, 1,000 PSI REGISTERED AT TRUCK. ATTEMPTED TO BLED 100 PSI AT TRUCK AND PRESSURE RETURNED TO 1,000 PSI. BLED OFF 100 PSI ON CHOKE AND PRESSURE DROPPED AT THE TRUCK AND BUILT BACK TO 1,000 PSI (SUSPECTED FLOAT FAILURE).
RAINIER 1H | 36 | 2021-06-12 06:00 | 2021-06-12 06:30 | 0.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 30.56 | 20659 | 20659 | 0 | CONTINUE DISPLACING CEMENT WITH 406 BBLS OF FRESH WATER @ 5 BPM THROUGH THE CHOKE, OBSERVED 100% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 3,650 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4,650 PSI. 0 BBLS OF SPACER BACK TO SURFACE. BUMPED PLUG AS CALCULATED, HELD FOR 5 MIN, BLED BACK 6.5 BBLS. FLOATS HELD. PLUG DOWN @ 06:25 HRS 6/12/2021. INITIAL SICP-950 PSI, FINAL SICP= 375 PSI. MAX CASING PSI W/ PUMPING CEMENT- 1,115 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT- 490 PSI MAX GAS-386u CALCULATED TOP OF CEMENT- 8,494'
RAINIER 1H | 36 | 2021-06-12 06:30 | 2021-06-12 07:00 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 30.58 | 20659 | 20659 | 0 | RIG DOWN CIRCULATING IRON, REMOVE CASING ELEVATORS AND CASING BAILS, INSTALL RIG ELEVATORS WHILE MONITORING SICP, INITIAL SICP=375 PSI, FINAL SICP= 379 PSI. NOTE: LEFT CEMENT HEAD ON CASING WHILE MONITORING SICP.
RAINIER 1H | 36 | 2021-06-12 07:00 | 2021-06-13 06:00 | 23 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 31.54 | 20659 | 20659 | 0 | MONITOR SICP WHILE WAITING ON CEMENT, CLEAN MUD PITS, CHANGE OUT LINERS F/4 3/4" T/5 1/4", VALVES AND SEATS ON #3 MUD PUMP, L/D 4 1/2" DRILL PIPE FROM THE DERRICK OUT OF THE MOUSE HOLE (62 STDS DP/11 STDS HWDP L/D), INITIAL SICP=379 PSI, FINAL SICP= 483 PSI. SICP WHILE MONITORING: 07:00 - 379 PSI 08:00 - 390 PSI 09:00 - 379 PSI 10:00 - 372 PSI 11:00 - 406 PSI 12:00 - 449 PSI 13:00 - 467 PSI 14:00 - 474 PSI 15:00 - 480 PSI 16:00 - 475 PSI 17:00 - 475 PSI 18:00 - 465 PSI 19:00 - 461 PSI 20:00 - 458 PSI 21:00 - 455 PSI 22:00 - 446 PSI 23:00 - 440 PSI 00:00 - 442 PSI 01:00 - 442 PSI 02:00 - 451 PSI 03:00 - 461 PSI 04:00 - 468 PSI 05:00 - 475 PSI 06:00 - 482 PSI
RAINIER 1H | 37 | 2021-06-13 06:00 | 2021-06-13 06:30 | 0.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 31.56 | 20659 | 20659 | 0 | CONTINUE L/D 4 1/2" DRILL PIPE FROM THE DERRICK OUT OF THE MOUSE HOLE WHILE MONITORING SICP AND WAIT ON CEMENT, SICP=488 PSI.
RAINIER 1H | 37 | 2021-06-13 06:30 | 2021-06-13 08:30 | 2 | P | PRDHLCSG | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 31.65 | 20659 | 20659 | 0 | BLEED OFF SICP IN 50-100 PSI INCREMENTS TO THE TRIP TANK RECORDING BBLS BLED BACK, INITIAL SICP = 488 PSI, FINAL SICP= 0 PSI, BLED BACK .96 BBLS. MONITOR FLOW THROUGH THE CHOKE TO THE TRIP TANK (WELL STATIC). BLEED OFF SCHEDULE: F/488 PSI T/432 PSI AND SICP STABLIZED @ 442 PSI F/442 PSI T/350 PSI AND SICP STABLIZED @ 409 PSI F/409 PSI T/353 PSI AND SICP STABLIZED @ 390 PSI F/390 PSI T/297 PSI AND SICP STABLIZED @ 362 PSI F/362 PSI T/306 PSI AND SICP STABLIZED @ 349 PSI F/349 PSI T/230 PSI AND SICP STABLIZED @ 302 PSI F/302 PSI T/192 PSI AND SICP STABLIZED @ 249 PSI F/249 PSI T/109 PSI AND SICP STABLIZED @ 192 PSI F/192 PSI T/0 PSI AND SICP STABLIZED @ 0 PSI
RAINIER 1H | 37 | 2021-06-13 08:30 | 2021-06-13 12:00 | 3.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 31.79 | 20659 | 20659 | 0 | REMOVE CEMENT HEAD AND ROTATING HEAD, LAY DOWN LANDING JOINT. RIG DOWN CSG ELEVATORS AND RIG UP RIG ELEVATORS. RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER. PUMP @ 64 GPM W/900 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF. INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. PICK UP 1" TUBING AND INSTALL BPV. LAY DOWN TUBING.
RAINIER 1H | 37 | 2021-06-13 12:00 | 2021-06-13 12:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 31.81 | 20659 | 20659 | 0 | FLUSH THROUGH BOP STACK, CHOKE MANIFOLD, SEPERATOR, KILL LINE, TOP DRIVE AND FLOW LINE.
RAINIER 1H | 37 | 2021-06-13 12:30 | 2021-06-13 15:00 | 2.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 31.92 | 20659 | 20659 | 0 | REMOVE FLOW LINE FROM SCISSOR, INSTALL WRANGLER ONTO BOP, REMOVE TURNBUCKLES, HCR LINE KILL LINE, KILL LINE CHECK VALVE, HYDRAULIC LINES, BACK OUT STREAMFLO ADAPTER FLANGE AND RAISE BOP.
RAINIER 1H | 37 | 2021-06-13 15:00 | 2021-06-13 16:00 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 31.96 | 20659 | 20659 | 0 | INSTALLED WELLHEAD CAP & TESTED T/1000 PSI. WELL RELEASED 6/13/21 @ 16:00
RAINIER 1H | 37 | 2021-06-13 16:00 | 2021-06-13 16:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 31.96 | 20659 | 20659 |  | MILESTONE_WELL RELEASE ON 6/13/2021 @ 16:00
RAINIER 1H | 37 | 2021-06-13 16:00 | 2021-06-13 17:30 | 1.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 32.02 | 20659 | 20659 | 0 | LAY DOWN BOP STACK, REMOVE FILL UP LINE, DRAIN HOSES, ROLL UP HYDRAULIC LINES TO ACCUMULATOR, REMOVE HCR LINE OFF CHOKE MANIFOLD, INSTALL MOUSE HOLE. RIG DOWN FLARE STACK, VENT LINES AND GAS SEPERATOR.
RAINIER 1H | 37 | 2021-06-13 17:30 | 2021-06-14 06:00 | 12.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 32.54 | 20659 | 20659 | 0 | L/D 4 1/2" DRILL PIPE FROM THE DERRICK OUT OF THE MOUSE HOLE (69 STDS) (TIGHT CONNECTIONS REQUIRING ST-80 DIES TO BE CHANGED OFTEN) , WASH RIG, RIG DOWN BACK YARD AND SPLIT APART MUD TANKS.
RAINIER 1H | 38 | 2021-06-14 06:00 | 2021-06-14 14:00 | 8 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 32.87 | 20659 | 20659 | 0 | CONTINUE L/D 4 1/2" DRILL PIPE FROM THE DERRICK OUT OF THE MOUSE HOLE, RIG DOWN AND MOVE TCB CAMPS, LOAD OUT AND MOVE FRAC TANKS, DRILL PIPE, MISC., DRY SHAKERS, GAS SEPERATOR, OPEN TOPS, MUD TANKS, PERFORMING CAR WASHES ON ALL EQUIPMENT LEAVING LOCATION.
RAINIER 1H | 38 | 2021-06-14 14:00 | 2021-06-15 06:00 | 16 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 33.54 | 20659 | 20659 | 0 | REMOVE ALL HANDLING EQUIPMENT OFF RIG FLOOR, PIN TOP DRIVE TO TRACK, UNSPOOL DRAWWORKS, RIG DOWN TONGS AND ST-80. RIG DOWN CATWALK AND MOVE, RIG DOWN GEN PACKAGE, VFD HOUSE, EXTEND AND PIN MSRC'S TO SUB AND LOWER @ 00:00, REMOVE BOP, EXTEND MSRC'S TO DERRICK AND LOWER DERRICK @ 02:00, UNDRESS DERRICK, REMOVE MONKEY BOARD, SPLIT BLOCKS AND PIN IN CROWN SECTION. LOAD OUT AND MOVE ACCUMULATOR, FLOW LINE SCISSORS, SHAKERS, SHAKER TANK, CHOKE MANIFOLD AND MUD PUMPS TO THE OZARK 1H, ON NEW LOCATION SET MUD TANKS, MUD PUMPS AND SUITCASES. 65% RIGGED DOWN 15% MOVED TO NEW LOCATION 2% RIGGED UP
RAINIER 1H | 38 | 2021-06-15 06:00 | 2021-06-15 06:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 33.54 | 20659 | 20659 |  | MILESTONE_TURN OVER TO COMPLETION ON 06/15/2021 @ 06:00
RAINIER 1H | 38 | 2021-06-15 06:00 | 2021-06-15 06:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 33.54 | 20659 | 20659 |  | MILESTONE_RIG RELEASE ON 06/15/2021 @ 06:00
REDWOOD A 1H | 1 | 2021-07-15 10:30 | 2021-07-15 12:00 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/ROMMEL 3H T/REDWOOD A 1H; SET MATS, WALK RIG TO REDWOOD A 1H; CENTER AND LEVELED SUB OVER CONDUCTOR.
REDWOOD A 1H | 1 | 2021-07-15 10:30 | 2021-07-15 10:30 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 07/15/2021 @ 10:30
REDWOOD A 1H | 1 | 2021-07-15 12:00 | 2021-07-15 13:15 | 1.25 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | L/D LANDING JT., REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
REDWOOD A 1H | 1 | 2021-07-15 13:15 | 2021-07-15 14:00 | 0.75 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
REDWOOD A 1H | 1 | 2021-07-15 14:00 | 2021-07-15 15:45 | 1.75 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, L/D MOTOR, PICK UP NEW MOTOR AND MAKE UP NEW BIT, REMOVE X-OVER AND PUP JOINT, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, TAG BOTTOM @ 108'.
REDWOOD A 1H | 1 | 2021-07-15 15:45 | 2021-07-15 16:15 | 0.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.02 | 108 | 256 | 296 | ROTATE DRILL F/108' T/256' (148' IN .5 HRS @ 296 FPH) WOB-5-10K, RPM-65, TRQ-1/3K, SPM-70/70/70, GPM-575, MMRPM-112, TRPM-75, SPP-500/700 PSI, DIFF-100/200 PSI.
REDWOOD A 1H | 1 | 2021-07-15 15:45 | 2021-07-15 15:45 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 7/15/2021 @ 15:45
REDWOOD A 1H | 1 | 2021-07-15 16:15 | 2021-07-15 17:15 | 1 | P | SFHL | DRLG | CTLDRL | CONTROL DRILLING | 0.06 | 256 | 673 | 417 | CONTROL DRILL ON #1 AND #3 PUMP WHILE CHANGING OUT ALL SWABS ON #2 PUMP FROM PREMIUM SWABS TO SOUTH WEST SWABS, ROTATE DRILL F/256' T/673' (417' IN 1 HR @ 417 FPH) WOB-10-20K, RPM-100, TRQ- 2/4K, SPM-110/110, GPM-720, MMRPM-120, TRPM-220, SPP-900/1300 PSI, DIFF-200/400 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300'.
REDWOOD A 1H | 1 | 2021-07-15 17:15 | 2021-07-15 22:45 | 5.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.29 | 673 | 3193 | 458.2 | ROTATE (2,520’ IN 3.83 HRS @ 657.9 FPH) WOB-25-35K, RPM-100, TRQ- 3k/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,300/2,600 PSI, DIFF-200/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM.
REDWOOD A 1H | 1 | 2021-07-15 22:45 | 2021-07-16 01:30 | 2.75 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.41 | 3193 | 3514 | 116.7 | SLIDE (321' IN 1.95 HRS @ 164.6 FPH) WOB-5/14K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1,600/2,200 PSI, DIFF-200/300 PSI. SLIDE DEPTHS: 18:47-18:52 1,519.00-1,534.00 15' 135M 19:01-19:06 1,614.00-1,634.00 20' 135M 19:18-19:23 1,707.00-1,727.00 20' 135M 19:36-19:41 1,801.00-1,819.00 18' 110M 19:53-19:58 1,894.00-1,909.00 15' -20M 20:10-20:14 1,988.00-2,003.00 15' -20M 20:26-20:36 2,083.00-2,103.00 20' 0.00G 20:51-21:00 2,177.00-2,197.00 20' 10G 21:13-21:18 2,272.00-2,292.00 20' 0G 21:34-21:42 2,365.00-2,385.00 20' -20G 21:57-22:05 2,459.00-2,479.00 20' -10G 22:16-22:23 2,553.00-2,571.00 18' 0G 23:02-23:08 2,835.00-2,855.00 20' 20G 23:46-23:55 3,117.00-3,137.00 20' 30G 00:08-00:17 3,211.00-3,231.00 20' 20G 00:31-00:40 3,305.00-3,325.00 20' 30G 00:53-01:01 3,398.00-3,418.00 20' 0G
REDWOOD A 1H | 1 | 2021-07-16 01:30 | 2021-07-16 02:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.45 | 3514 | 3514 | 0 | PUMP 2-30 BBL GEL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,160 PSI.
REDWOOD A 1H | 1 | 2021-07-16 02:30 | 2021-07-16 04:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.51 | 3514 | 3514 | 0 | TRIP OUT OF HOLE F/3,514' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
REDWOOD A 1H | 1 | 2021-07-16 04:00 | 2021-07-16 04:30 | 0.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.53 | 3514 | 3514 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-1-NO-A-X-0-NO-TD.
REDWOOD A 1H | 1 | 2021-07-16 04:30 | 2021-07-16 05:15 | 0.75 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.56 | 3514 | 3514 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
REDWOOD A 1H | 1 | 2021-07-16 05:15 | 2021-07-16 06:00 | 0.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.59 | 3514 | 3514 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BTC CASING, TEST FLOATS (TEST GOOD), TIH WITH 10 3/4" 45.5# J-55 BTC CASING T/322'.
REDWOOD A 1H | 2 | 2021-07-16 06:00 | 2021-07-16 09:00 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.72 | 3514 | 3514 | 0 | CONTINUE RUNNING 10 3/4" 45.5# J-55 BTC CASING F/322' T/3,504'. RAN 44 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED WELLHEAD T/5,000 PSI. SLACK OFF AND LAND OUT ON BASE PLATE WITH 110K LBS(W/O BLOCKS). SHOE- 3,504' TOP OF FLOAT COLLAR- 3,421' LEFT OUT 9 JOINTS-351.63'
REDWOOD A 1H | 2 | 2021-07-16 09:00 | 2021-07-16 10:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.76 | 3514 | 3514 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-321, SPP-100. NO LOSSES.
REDWOOD A 1H | 2 | 2021-07-16 10:00 | 2021-07-16 10:30 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.78 | 3514 | 3514 | 0 | RIG DOWN CRT, PREP RIG FOR WALK. WELL ON HOLD 7/16/2021 @ 10:30.
REDWOOD A 1H | 2 | 2021-07-16 10:30 | 2021-07-16 10:30 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.78 | 3514 | 3514 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 7/16/2021 @10:30
REDWOOD A 1H | 2 | 2021-07-16 10:30 | 2021-07-16 13:00 | 2.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.78 | 3514 | 3514 | 0 | WALK RIG F/ REDWOOD A 1H T/ REDWOOD C 1H. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON. RIG UP CELLAR PUMPS FOR CEMENT JOB.
REDWOOD A 1H | 2 | 2021-07-16 13:00 | 2021-07-16 15:15 | 2.25 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.78 | 3514 | 3514 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 371 BBLS 11.6 PPG LEAD CEMENT, 98 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 326 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/1050 PSI PRESSURED UP T/1554 PSI (504 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2.0 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 176 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
REDWOOD A 1H | 2 | 2021-07-16 15:15 | 2021-07-16 17:00 | 1.75 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.78 | 3514 | 3514 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD);RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
REDWOOD A 1H | 3 | 2021-07-28 16:00 | 2021-07-28 16:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.78 | 3514 | 3514 |  | MILESTONE_RESUME WELL OPERATIONS 1 @ 16:00 ON 7/28/21
REDWOOD A 1H | 3 | 2021-07-28 16:00 | 2021-07-28 17:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.82 | 3514 | 3514 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM REDWOOD C 1H TO REDWOOD A 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
REDWOOD A 1H | 3 | 2021-07-28 17:00 | 2021-07-28 18:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.86 | 3514 | 3514 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
REDWOOD A 1H | 3 | 2021-07-28 18:00 | 2021-07-28 20:00 | 2 | P | SFHLCSG | BOP | SVCBOP | SERVICE BOP | 0.95 | 3514 | 3514 | 0 | C/O TOP RAMS F/7-5/8" CSG RAMS TO VBR'S
REDWOOD A 1H | 3 | 2021-07-28 20:00 | 2021-07-28 22:00 | 2 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.03 | 3514 | 3514 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, KILL LINE, HCR HOSE AND KILL LINE CHECK VALVE 250 PSI LOW AND 5000 PSI HIGH. PERFORM DRAW DOWN TEST ON ACUMMULATOR WHILE LD TEST PLUG AND RD TESTERS.
REDWOOD A 1H | 3 | 2021-07-28 22:00 | 2021-07-28 23:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.07 | 3514 | 3514 | 0 | INSTALL WEAR BUSHING, CLOSE CSG VALVE AND COVER CELLAR. INSTALL TRIP NIPPLE AND MOUSEHOLE.
REDWOOD A 1H | 3 | 2021-07-28 23:00 | 2021-07-29 00:30 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.14 | 3514 | 3514 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.90' BIT TO BEND; 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG,BIT TO SENSOR-64', GAMMA-60'. TEST MWD (GOOD TEST).
REDWOOD A 1H | 3 | 2021-07-29 00:30 | 2021-07-29 01:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.18 | 3514 | 3514 | 0 | SERVICE TOP DRIVE, TRAVELING BLOCK AND DRAWWORKS.
REDWOOD A 1H | 3 | 2021-07-29 01:30 | 2021-07-29 02:30 | 1 | U | SFHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 1.22 | 3514 | 3514 | 0 | CALIBRATE CROWN SAVER. WHEN TRIPPED CROWN SAVER DRAWWORKS FAULTED DISABLING DRAWWORKS. UNABLE TO RESET CROWN SAVER. TROUBLE SHOOT, FOUND AIRLINES FULL OF DEBRIS, CLEANED AIRLINES AND RESET CROWN SAVER.
REDWOOD A 1H | 3 | 2021-07-29 02:30 | 2021-07-29 03:30 | 1 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.26 | 3514 | 3514 | 0 | TRIPPED IN THE HOLE F/579' - T/2665', PROPER DISPLACEMENT.
REDWOOD A 1H | 3 | 2021-07-29 03:30 | 2021-07-29 04:15 | 0.75 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.29 | 3514 | 3514 | 0 | FILLED PIPE & FLOW TESTED DRILL STRING, PICKED UP AGITATOR, & FLOW TESTED. SPP BEFORE-605 PSI SPP AFTER-710 PSI
REDWOOD A 1H | 3 | 2021-07-29 04:15 | 2021-07-29 05:00 | 0.75 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.32 | 3514 | 3514 | 0 | TRIPPED IN THE HOLE F/2665' - T/3417', PROPER DISPLACEMENT. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD.
REDWOOD A 1H | 3 | 2021-07-29 05:00 | 2021-07-29 05:30 | 0.5 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 1.34 | 3514 | 3514 | 0 | FILL PIPE, PERFORM BOP DRILL, RESPONSE TIME 50 SEC. FLUSH THROUGH GAS SEPERATOR.
REDWOOD A 1H | 3 | 2021-07-29 05:30 | 2021-07-29 06:00 | 0.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.36 | 3514 | 3514 | 0 | DRILL SHOE TRACK F/3,417' T/3,514', GPM-500, SPP-5300 PSI, DP-100/200, RPM-30, TQ-2/5K
REDWOOD A 1H | 4 | 2021-07-29 06:00 | 2021-07-29 06:15 | 0.25 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.38 | 3514 | 3524 | 40 | DRILL 10' OF NEW FORMATION F/3,514' T/3,524', GPM-500, SPP-1300 PSI, DP-100/200, RPM-30, TQ-2/5K
REDWOOD A 1H | 4 | 2021-07-29 06:15 | 2021-07-29 06:30 | 0.25 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 1.39 | 3524 | 3524 | 0 | CIRCULATE BOTTOMS UP GPM-500, SPP-1500 PSI, RPM-30. MW IN 8.8 PPG, MW OUT 8.8 PPG
REDWOOD A 1H | 4 | 2021-07-29 06:30 | 2021-07-29 06:45 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.4 | 3524 | 3524 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, 508 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,504' / TVD-3,488'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE
REDWOOD A 1H | 4 | 2021-07-29 06:45 | 2021-07-29 10:15 | 3.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.54 | 3524 | 5029 | 430 | ROT (1505' IN 3.42 HRS @ 440.05 FPH) WOB: 15/40K, SPM: 95/95/95, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/15K, SPP: 3800/4700 PSI, DIFF: 500/800 PSI.
REDWOOD A 1H | 4 | 2021-07-29 10:15 | 2021-07-29 11:30 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.59 | 5029 | 5109 | 64 | SLIDE (80' IN 1.33 HRS @ 60.15 FPH) WOB: 5-12K, SPM: 95/95/95, GPM: 900, MMRPM: 149, SPP: 3800/4000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/3624' T/3634' 10' TF-10R 07:10-07:18 SLD F/3714' T/3724' 10' TF-30R 07:31-07:42 SLD F/3810' T/3825' 15' TF-30R 07:53-08:05 SLD F/3900' T/3915' 15' TF-HS 08:13-08:26 SLD F/3994' T/4009' 15' TF-HS 08:36-08:52 SLD F/4463' T/4478' 15' TF-HS 09:50-10:10
REDWOOD A 1H | 4 | 2021-07-29 11:30 | 2021-07-29 11:45 | 0.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 1.6 | 5109 | 5296 | 748 | CONTROL DRILL ON #1 AND #2 MUD PUMPS WHILE CHANGING OUT SWAB ON #3 MUD PUMP; ROT (187' IN .25 HRS @ 748 FPH) WOB: 15/25K, SPM: 113/113, GPM: 720, MMRPM: 120, RPM-80, TRPM: 200, TRQ: 5K/10K, SPP: 3800 PSI, DIFF: 700 PSI.
REDWOOD A 1H | 4 | 2021-07-29 11:45 | 2021-07-29 14:45 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.73 | 5296 | 6396 | 366.7 | ROT (1,100' IN 2.95 HRS @ 373 FPH) WOB: 15/40K, SPM: 93/93/93, GPM: 895, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/15K, SPP: 3800/4700 PSI, DIFF: 500/800 PSI.
REDWOOD A 1H | 4 | 2021-07-29 14:45 | 2021-07-29 17:15 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.83 | 6396 | 6516 | 48 | SLIDE (120' IN 2.55 HRS @ 47 FPH) WOB: 5-12K, SPM: 93/93/93, GPM: 895, MMRPM: 149, SPP: 3800/4000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/5308' T/5323' 15' TF-30R 11:54-12:05 SLD F/5404' T/5419' 15' TF-30R 12:17-1228 SLD F/5967' T/5982' 15' TF-30R 1343-1354 SLD F/6060' T/6075' 15' TF-30R 1405-1417 SLD F/6153' T/6168' 15' TF-30R 1428-1451 SLD F/6250' T/6265' 15' TF-30R 1503-1525 SLD F/6340' T/6355' 15' TF-30R 1544-1612 SLD F/6430' T/6445' 15' TF-30R 1627-1702
REDWOOD A 1H | 4 | 2021-07-29 17:15 | 2021-07-29 17:45 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.85 | 6516 | 6516 | 0 | LUBRICATE TOP DRIVE, ST-80, AND DRAWORKS
REDWOOD A 1H | 4 | 2021-07-29 17:45 | 2021-07-29 18:45 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.9 | 6516 | 6710 | 194 | ROT (194' IN 1.02 HRS @ 190.20 FPH) WOB: 15/40K, SPM: 93/93/93, GPM: 895, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/15K, SPP: 3800/4700 PSI, DIFF: 500/800 PSI.
REDWOOD A 1H | 4 | 2021-07-29 18:45 | 2021-07-29 21:00 | 2.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.99 | 6710 | 6757 | 20.9 | SLIDE (47' IN 2.23 HRS @ 21 FPH) WOB: 5-12K, SPM: 93/93/93, GPM: 895, MMRPM: 149, SPP: 3800/4000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/6535' T/6547' 12' TF-10R 18:00-18:40 SLD F/6620' T/6635' 15' TF-20R 18:57-19:45 SLD F/6715' T/6735' 20' TF-20R 20:00-20:46
REDWOOD A 1H | 4 | 2021-07-29 21:00 | 2021-07-29 21:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.01 | 6757 | 6872 | 230 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT LINER GASKET ON #2 MUD PUMP; ROT (115' IN .5 HRS @ 230 FPH) WOB: 15/25K, SPM: 113/113, GPM: 720, MMRPM: 120, RPM-80, TRPM: 200, TRQ: 5K/10K, SPP: 3800 PSI, DIFF: 700 PSI.
REDWOOD A 1H | 4 | 2021-07-29 21:30 | 2021-07-29 22:00 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.03 | 6872 | 6892 | 40 | CONTROL DRILL ON #1 AND #3 MUD PUMPS; SLIDE (20' IN .5 HRS @ 40 FPH) WOB: 10K/20K, SPM: 113/113, GPM: 720, MMRPM: 120, SPP: 3800/4100 PSI, DIFF: 200/300 PSI. SLIDE DEPTH: SLD F/6810' T/6830' 20' TF-HS 21:15-21:45 NOTE: WHEN PU OFF BTTM AFTER SLIDE, PICKED UP 60K OVER, KICKED ROTARY IN AND STALLED ROTARY AT 24K, SLOWED PUMP FROM 700 GPM TO 350 GPM AND BROKE FREE.
REDWOOD A 1H | 4 | 2021-07-29 22:00 | 2021-07-30 02:00 | 4 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.2 | 6892 | 7863 | 242.8 | ROT (971' IN 4.07 HRS @ 238.57 FPH) WOB: 15/40K, SPM: 87/87/87, GPM: 790, MMRPM: 131, RPM-80, TRPM: 211, TRQ: 8K/15K, SPP: 4100/4900 PSI, DIFF: 500/800 PSI. NOTE: PUMPING HI-VIS SWEEPS EVERY 300', INCREASE MUD WT F/9.3 PPG T/9.6 PPG. 9 PPB LCM SWEEP=80 BBLS ACTIVE MUD 5 MAGNA FIBER 5 NEW CARB MEDIUM 5 NEW FAULT 5 BENTONE 910
REDWOOD A 1H | 4 | 2021-07-30 02:00 | 2021-07-30 06:00 | 4 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.36 | 7863 | 7945 | 20.5 | SLIDE (82' IN 3.93 HRS @ 20.8 FPH) WOB: 5-12K, SPM: 87/87/87, GPM: 790, MMRPM: 131, SPP: 4100/4300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/6905' T/6912' 7' TF-30L 22:25-22:52 SLD F/7371' T/7381' 10' TF-20L 00:24-00:48 SLD F/7465' T/7475' 10' TF-HS 01:09-01:47 SLD F/7565' T/7577' 12' TF-HS 02:08-02:50 SLD F/7655' T/7675' 20' TF-HS 03:13-03:49 SLD F/7842' T/7855' 13' TF-HS 04:26-05:08 SLD F/7935' T/7945' 10' TF-HS 05:33-06:00
REDWOOD A 1H | 5 | 2021-07-30 06:00 | 2021-07-30 07:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.41 | 7945 | 8162 | 217 | ROT (217' IN 1.0 HRS @ 217 FPH) WOB: 15/40K, SPM: 87/87/87, GPM: 790, MMRPM: 131, RPM-80, TRPM: 211, TRQ: 8K/15K, SPP: 4100/4900 PSI, DIFF: 500/800 PSI. NOTE: PUMPING HI-VIS SWEEPS EVERY 300' 9 PPB LCM SWEEP=80 BBLS ACTIVE MUD 5 MAGNA FIBER 5 NEW CARB MEDIUM 5 NEW FAULT 5 BENTONE 910
REDWOOD A 1H | 5 | 2021-07-30 07:00 | 2021-07-30 08:45 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.48 | 8162 | 8207 | 25.7 | SLIDE (45' IN 1.75 HRS @ 25.7 FPH) WOB: 5-12K, SPM: 87/87/87, GPM: 790, MMRPM: 131, SPP: 4100/4300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/7945' T/7960' 15' TF-30R 06:00-06:35 SLD F/8026' T/8041' 15' TF-HS 06:50-07:39 SLD F/8118' T/8133' 15' TF-HS 07:55-08:16
REDWOOD A 1H | 5 | 2021-07-30 08:45 | 2021-07-30 09:30 | 0.75 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.51 | 8207 | 8207 | 0 | RIG SERVICE, CHANGE SWIVEL PACKING AND SERVICE TOP DRIVE
REDWOOD A 1H | 5 | 2021-07-30 09:30 | 2021-07-30 13:45 | 4.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.69 | 8207 | 9550 | 316 | ROT (1,343' IN 4.23 HRS @ 317.49 FPH) WOB: 15/40K, SPM: 87/87/87, GPM: 790, MMRPM: 131, RPM-80, TRPM: 211, TRQ: 8K/15K, SPP: 4100/4900 PSI, DIFF: 500/800 PSI. NOTE: PUMPING HI-VIS SWEEPS EVERY 300' 9 PPB LCM SWEEP=80 BBLS ACTIVE MUD 5 MAGNA FIBER 5 NEW CARB MEDIUM 5 NEW FAULT 5 BENTONE 910
REDWOOD A 1H | 5 | 2021-07-30 13:45 | 2021-07-30 17:15 | 3.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.83 | 9550 | 9645 | 27.1 | SLIDE (95' IN 3.52 HRS @ 26.98 FPH) WOB: 5-12K, SPM: 87/87/87, GPM: 790, MMRPM: 131, SPP: 4100/4300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/8216' T/8231' 15' TF-HS 09:45-10:12 SLD F/8315' T/8330' 15' TF-HS 10:27-10:58 SLD F/8407' T/8422' 15' TF-HS 11:16-11:52 SLD F/8495' T/8510' 15' TF-HS 12:05-12:30 SLD F/9034' T/9054' 20' TF-40L 13:58-14:55 SLD F/9255' T/9270' 15' TF-130M 15:32-16:07
REDWOOD A 1H | 5 | 2021-07-30 17:15 | 2021-07-30 20:00 | 2.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.95 | 9645 | 10241 | 216.7 | CONTROL DRILL ON #1 AND #2 MUD PUMPS WHILE CHANGING OUT GASKET ON SUCTION MODULE #3 MUD PUMP; ROT (596' IN 2.75 HRS @ 216.72 FPH) WOB: 20/30K, SPM: 108/108, GPM: 685, MMRPM: 114, RPM-80, TRPM: 194, TRQ: 10K/14K, SPP: 3900 PSI, DIFF: 700 PSI.
REDWOOD A 1H | 5 | 2021-07-30 20:00 | 2021-07-30 21:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.01 | 10241 | 10259 | 12 | BUILD CURVE/SLD (18' IN 1.5 HRS @ 12 FPH) WOB: 15/20K, SPM: 108/108, GPM: 685, MMRPM: 114, SPP: 3250 PSI, DIFF: 150 PSI. SLIDE DEPTHS: SLD F/10,241' T/10,259' 18' TF-325M 20:00-21:30 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING OUT GASKET ON SUCTION MODULE #3 MUD PUMP
REDWOOD A 1H | 5 | 2021-07-30 21:30 | 2021-07-30 23:45 | 2.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.1 | 10259 | 10302 | 19.1 | BUILD CURVE/SLD (43' IN 2.25 HRS @ 19 FPH) WOB: 15/20K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/10,259' T/10,302' 43' TF-325M 21:30-23:45
REDWOOD A 1H | 5 | 2021-07-30 23:45 | 2021-07-31 01:45 | 2 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.19 | 10302 | 10366 | 32 | BUILD CURVE/SLD (64' IN 2.0 HRS @ 32 FPH) WOB: 15/20K, SPM: 108/108, GPM: 685, MMRPM: 114, SPP: 3250 PSI, DIFF: 150 PSI. SLIDE DEPTHS: SLD F/10,302' T/10,366' 64' TF-325M 23:45-01:45 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING WEAR PLATE, LINER GASKET AND SWAB ON #1 MUD PUMP
REDWOOD A 1H | 5 | 2021-07-31 01:45 | 2021-07-31 05:00 | 3.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.32 | 10366 | 10471 | 32.3 | BUILD CURVE/SLD (105' IN 3.28 HRS @ 32 FPH) WOB: 15/20K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/10,386' T/10,457' 71' TF-HS 01:55-04:15 SLD F/10,555' T/10,589' 34' TF-HS 05:03-06:00
REDWOOD A 1H | 5 | 2021-07-31 05:00 | 2021-07-31 06:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.36 | 10471 | 10589 | 118 | BUILD CURVE/ROT. (118' IN .97 HRS @ 121.65 FPH) WOB: 20/30K, RPM-30, TQ-14/16K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 500 PSI.
REDWOOD A 1H | 6 | 2021-07-31 06:00 | 2021-07-31 09:30 | 3.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.51 | 10589 | 10766 | 50.6 | BUILD CURVE/SLD (177' IN 3.63 HRS @ 48.76 FPH) WOB: 15/20K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/10,589' T/10,10743' 154' TF-HS 06:00-09:05 SLD F/10,781' T/10,804' 23' TF-HS 09:18-09:51
REDWOOD A 1H | 6 | 2021-07-31 09:30 | 2021-07-31 10:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.53 | 10766 | 10804 | 76 | BUILD CURVE/ROT. (38' IN .22 HRS @ 172.72 FPH) WOB: 20/30K, RPM-30, TQ-14/16K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 500 PSI.
REDWOOD A 1H | 6 | 2021-07-31 10:00 | 2021-07-31 10:45 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.56 | 10804 | 10837 | 44 | BUILD CURVE/SLD (33' IN .75 HRS @ 44 FPH) WOB: 15/20K, SPM: 108/108, GPM: 685, MMRPM: 114, SPP: 3250 PSI, DIFF: 150 PSI. SLIDE DEPTHS: SLD F/10,804' T/10,837' 33' TF-HS 0951-1045 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING CAP GASKET ON #2 MUD PUMP
REDWOOD A 1H | 6 | 2021-07-31 10:45 | 2021-07-31 11:30 | 0.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.59 | 10837 | 10889 | 69.3 | BUILD CURVE/ROT. (52' IN .63 HRS @ 83 FPH) WOB: 20/30K, RPM-30, TQ-14/16K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 500 PSI.
REDWOOD A 1H | 6 | 2021-07-31 11:30 | 2021-07-31 15:15 | 3.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.75 | 10889 | 11063 | 46.4 | BUILD CURVE/SLD (174' IN 3.87 HRS @ 45 FPH) WOB: 15/20K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 4800 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/10,857' T/10930' 73' TF-HS 1058-1215 SLD F/10942' T/11063' 82' TF-30L 1225-1420 SLD F/11044' T/11063' 19' TF-30L 1435-1515
REDWOOD A 1H | 6 | 2021-07-31 15:15 | 2021-07-31 16:45 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.81 | 11063 | 11063 | 0 | PERFORMED CLEAN UP CYCLE PUMPING 2-30 BBL SWEEPS SURFACE TO SURFACE TO CLEAN HOLE & PREP OPEN HOLE FOR 7-5/8" CASING. GPM-830, SPP-4750, RPM-30, TRQ-6/8K, SHAKERS CLEAN.
REDWOOD A 1H | 6 | 2021-07-31 16:45 | 2021-07-31 17:00 | 0.25 | P | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 3.82 | 11063 | 11063 | 0 | FLOW CHECK 10 MINUTES, WELL STATIC. PUMP SLUG
REDWOOD A 1H | 6 | 2021-07-31 17:00 | 2021-07-31 19:30 | 2.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.93 | 11063 | 11063 | 0 | TOOH F/11,063' - T/5,368', NORMAL DRAG, PROPER FILL WITH TRIP TANK.
REDWOOD A 1H | 6 | 2021-07-31 19:30 | 2021-07-31 20:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.95 | 11063 | 11063 | 0 | WORK PIPE WHILE SERVICE ST-80, CHANGE OUT HYDRAULIC HOSE
REDWOOD A 1H | 6 | 2021-07-31 20:00 | 2021-07-31 23:30 | 3.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.09 | 11063 | 11063 | 0 | CONT. TOOH F/5,368' T/683', PROPER FILL WITH TRIP TANK; PERFORM FLOW CHECK @ SHOE; REMOVE ROT. HEAD/ INSTALL TRIP NIPPLE
REDWOOD A 1H | 6 | 2021-07-31 23:30 | 2021-08-01 01:30 | 2 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.18 | 11063 | 11063 | 0 | RACK BACK HWDP & 2 STDS-6.5" DC, REMOVED MWD TOOL, DRAINED MUD MOTOR, BROKE OUT BIT, AND LAID DOWN DIRECTIONAL BHA - MUD MOTOR DRAINED GOOD WITH LITTLE SQUAT. BIT GRADED 0-0-NO-TD
REDWOOD A 1H | 6 | 2021-08-01 01:30 | 2021-08-01 02:00 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.2 | 11063 | 11063 | 0 | PULLED WEAR BUSHING, LD MOUSEHOLE, CLEANED AND ORGANIZED RIG FLOOR FOR CASING RUN
REDWOOD A 1H | 6 | 2021-08-01 02:00 | 2021-08-01 03:30 | 1.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 4.26 | 11063 | 11063 | 0 | CHANGED OUT TOP VBR'S TO 7-5/8" CASING RAMS, PICKED UP JOINT OF DRILL PIPE AND PRESSURE TESTED BONNET SEALS T/1500 PSI
REDWOOD A 1H | 6 | 2021-08-01 03:30 | 2021-08-01 05:00 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.32 | 11063 | 11063 | 0 | HOLD PJSM AND RIG UP FRANK'S CASING CREW, TOOLS, & EQUIPMENT
REDWOOD A 1H | 6 | 2021-08-01 05:00 | 2021-08-01 06:00 | 1 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.36 | 11063 | 11063 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN INTERMEDIATE CASING T/531', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT NOTE: CSG DETAILS NEXT REPORT
REDWOOD A 1H | 7 | 2021-08-01 06:00 | 2021-08-01 10:15 | 4.25 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.54 | 11063 | 11063 | 0 | CONT. RUNNING INTERMEDIATE CASING F/531' T/5618', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
REDWOOD A 1H | 7 | 2021-08-01 10:15 | 2021-08-01 11:15 | 1 | U | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.58 | 11063 | 11063 | 0 | RIG SERVICE, TROUBLE SHOOT DRAWORKS; AIR LINE FOR THE CROWN SAVER GETTING WATER IN THE LINE CAUSING THE CROWN SAVER TO SHOW A FALSE READING OF BEING ACTIVATED; COULD NOT BYPASS THE CROWN SAVER, COULD NOT FUNCTION DRAWORKS FOR THE ABILITY TO PUMP DOWN CASING STRING; BLED WATER OFF OF AIR LINES AND DISCOVERED THE AIR LINE ALSO HAD A BLOCKAGE.
REDWOOD A 1H | 7 | 2021-08-01 11:15 | 2021-08-01 11:45 | 0.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 4.6 | 11063 | 11063 | 0 | CLEAR AIRLINE BLOCKAGE FROM CROWN SAVER, FUNCTION TEST DRAWORKS. OK
REDWOOD A 1H | 7 | 2021-08-01 11:45 | 2021-08-01 16:30 | 4.75 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.8 | 11063 | 11063 | 0 | CONT. RUNNING INTERMEDIATE CASING F/5,618' T/11,053', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 247 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG,1-10' PUP JT, 1-JT OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-PUP JT, 1-JT OF 7 5/8" 29.7# P-110 IC BTC CSG TOTAL OF 251 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALLED 46 LATCH ON BOW SPRING CENTRALIZERS @ 10,742' AND EVERY 4TH JT UP TO 2,850'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/240K (W/O BLOCKS) FLOAT SHOE-11,051' TOP OF FLOAT COLLAR-10,925', JOINTS LEFT OUT- 395.17' & 1-10' PUP JT OUT
REDWOOD A 1H | 7 | 2021-08-01 16:30 | 2021-08-01 17:00 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 4.82 | 11063 | 11063 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
REDWOOD A 1H | 7 | 2021-08-01 17:00 | 2021-08-01 19:00 | 2 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.91 | 11063 | 11063 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 105, 8.0 BPM, SPP: 600 PSI, NO LOSSES.
REDWOOD A 1H | 7 | 2021-08-01 19:00 | 2021-08-01 23:00 | 4 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.07 | 11063 | 11063 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4000 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 325 BBL 11.8 PPG 915 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 78 BBL 16.2 PPG 310 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 503 BBLS OF 9.7 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1700 PSI AT 3 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/2200 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI (4 BBLS)-FLOATS HELD. BROUGHT PRESSURE UP TO 3,500 AND HOLD 30 MINUTES, PLUG BUMPED @ 22:05 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. 40 BBLS SPACER AND 43 BBLS CEMENT BACK TO SURFACE. ESTIMATED TOP OF CEMENT: 0'
REDWOOD A 1H | 7 | 2021-08-01 23:00 | 2021-08-01 23:30 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 5.09 | 11063 | 11063 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
REDWOOD A 1H | 7 | 2021-08-01 23:30 | 2021-08-02 01:30 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.18 | 11063 | 11063 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
REDWOOD A 1H | 7 | 2021-08-02 01:30 | 2021-08-02 02:30 | 1 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 5.22 | 11063 | 11063 | 0 | REMOVE CSG RAMS AND INSTALL VBR'S
REDWOOD A 1H | 7 | 2021-08-02 02:30 | 2021-08-02 04:00 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.28 | 11063 | 11063 | 0 | SLIP N CUT 85' DRILL LINE, CALIBRATE BLOCK POSITION, SET HI-LO STOP POINTS.
REDWOOD A 1H | 7 | 2021-08-02 04:00 | 2021-08-02 06:00 | 2 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.36 | 11063 | 11063 | 0 | SET BOP WRANGLER, REMOVE TURN BUCKLES, NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL. PREP RIG TO WALK TO ROMMEL U 3H. NOTE: CUT MUD WT IN ACTIVE SYSTEM F/9.7 PPG T/8.8 PPG
REDWOOD A 1H | 7 | 2021-08-02 06:00 | 2021-08-02 06:00 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 5.36 | 11063 | 11063 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 8-2-2021 @ 06:00
REDWOOD A 1H | 8 | 2021-09-09 13:00 | 2021-09-09 16:00 | 3 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.49 | 11063 | 11063 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM ROMMEL 4H TO REDWOOD A1H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN. NOTE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE.
REDWOOD A 1H | 8 | 2021-09-09 13:00 | 2021-09-09 13:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 5.36 | 11063 | 11063 |  | MILESTONE_RESUME WELL 2 ON 9/9/2021 @ 13:00
REDWOOD A 1H | 8 | 2021-09-09 16:00 | 2021-09-09 17:15 | 1.25 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.54 | 11063 | 11063 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
REDWOOD A 1H | 8 | 2021-09-09 17:15 | 2021-09-10 03:15 | 10 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.96 | 11063 | 11063 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. NOTE: 4" ON STANDPIPE REPLACED, REPLACED 2 GASKETS ON 2" KILL LINE VALVES.
REDWOOD A 1H | 8 | 2021-09-10 03:15 | 2021-09-10 04:00 | 0.75 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.99 | 11063 | 11063 | 0 | RIG DOWN TEST EQUIPMENT; INSTALL WEAR BUSHING AND MOUSE HOLE; VERIFY STACK AND CHOKE ALIGNMENT.
REDWOOD A 1H | 8 | 2021-09-10 04:00 | 2021-09-10 06:00 | 2 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.07 | 11063 | 11063 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13618580 JETS 6X18 TFA: 1.491), 5.5", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.03' BIT TO BEND; 5.625" PAD OD; FLOW RANGE- 200/400 GPM; MAX DIFF-1,200 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, FILTER SUB, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-68'. BIT TO GAMMA-55'.
REDWOOD A 1H | 9 | 2021-09-10 06:00 | 2021-09-10 06:45 | 0.75 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.1 | 11063 | 11063 | 0 | TEST MWD (TEST GOOD), TRIP IN HOLE 2 STDS AND PICK UP DRILL-N-REAMER.
REDWOOD A 1H | 9 | 2021-09-10 06:45 | 2021-09-10 07:30 | 0.75 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 6.14 | 11063 | 11063 | 0 | AIR VALVE ON DRAWWORKS BROKE, CHANGE OUT AIR VALVE.
REDWOOD A 1H | 9 | 2021-09-10 07:30 | 2021-09-10 08:45 | 1.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.19 | 11063 | 11063 | 0 | TIH F/BHA T/2,817', PROPER DISPLACEMENT TO TRIP TANK.
REDWOOD A 1H | 9 | 2021-09-10 08:45 | 2021-09-10 09:00 | 0.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.2 | 11063 | 11063 | 0 | FILLED PIPE & FLOW TESTED DRILL STRING, PICKED UP AGITATOR AND FLOW TESTED. SPP BEFORE-990 PSI SPP AFTER- 1230 PSI @ 262 GPM.
REDWOOD A 1H | 9 | 2021-09-10 09:00 | 2021-09-10 13:00 | 4 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.36 | 11063 | 11063 | 0 | TRIP IN THE HOLE F/2,817' T/10,847', PROPER DISPLACEMENT TO TRIP TANK.
REDWOOD A 1H | 9 | 2021-09-10 13:00 | 2021-09-10 13:30 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 6.39 | 11063 | 11063 | 0 | FLOW CHECK, WELL STATIC. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD.
REDWOOD A 1H | 9 | 2021-09-10 13:30 | 2021-09-10 14:30 | 1 | P | INTHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 6.43 | 11063 | 11063 | 0 | WASH/REAM CEMENT STRINGERS F/10,847' T/10,963', TAGGED FLOAT COLLAR @ 10,963, CHECK CHOKE VALVE ALIGNMENT, PUMP THROUGH GAS BUSTER PRIOR TO DRILL OUT. PERFORM BOP DRILL, RESPONSE TIME= 40 SECONDS.
REDWOOD A 1H | 9 | 2021-09-10 14:30 | 2021-09-10 15:45 | 1.25 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 6.48 | 11063 | 11073 | 8 | DRILL SHOE TRACK AND 10' NEW FORMATION F/11,063' T/11,073', WOB-20K, RPM-30, GPM-300, SPP-2950-3250 PSI, DIFF-100/300, RPM-30, TQ-4/6K.
REDWOOD A 1H | 9 | 2021-09-10 15:45 | 2021-09-10 16:30 | 0.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.51 | 11073 | 11073 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T GPM-360, SPP-2900 PSI, RPM-30, MUD WT IN 10.3PPG, MUD WT OUT 10.3 PPG.
REDWOOD A 1H | 9 | 2021-09-10 16:30 | 2021-09-10 17:00 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.53 | 11073 | 11073 | 0 | PERFORM F.I.T. WITH 10.3 PPG OBM, 1542 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-11,053' / TVD-10,895'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE.
REDWOOD A 1H | 9 | 2021-09-10 17:00 | 2021-09-11 00:15 | 7.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.83 | 11073 | 11592 | 71.6 | BUILD CURVE-SLIDE (517' IN 7.35 HR @ 70.3 FPH) WOB-20/30K, SPM-77/77, GPM-400, MRPM-272, SPP-4570-5100 PSI, DIFF-400/530 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/11073 T/11118 45' TF-30L 1700-1800 SLD F/11132 T/11225 93' TF-HS 1820-2003 SLD F/11225 T/11318 95' TF-HS 2020-2112 SLD F/11318 T/11352 34' TF-HS 2130-2150 SLD F/11382 T/11414 32' TF-30L 2211-2230 SLD F/11414 T/11509 95' TF-30L 2246-2340 SLD F/11532 T/11602 70' TF-HS 0020-0052 SLD F/11665 T/11696 31' TF-HS 0155-0212 SLD F/11696 T/11720 24' TF-HS 0228-0247
REDWOOD A 1H | 9 | 2021-09-10 17:00 | 2021-09-10 17:00 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.53 | 11073 | 11073 |  | MILESTONE_START CURVE SECTION 9-10-2021 @ 17:00
REDWOOD A 1H | 9 | 2021-09-11 00:15 | 2021-09-11 02:45 | 2.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.94 | 11592 | 11720 | 51.2 | BUILD CURVE-ROTATE (130' IN 2.4 HRS @ 54.2 FPH) WOB-15/20K, SPM-77/77, GPM-400, RPM-35, MRPM-272, TRPM-307, SPP-4600-5025 PSI, DIFF-425 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI.
REDWOOD A 1H | 9 | 2021-09-11 02:45 | 2021-09-11 02:45 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.94 | 11720 | 11720 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 9/11/2021 AT 02:45 (11,720' MD / 11,144' TVD)
REDWOOD A 1H | 9 | 2021-09-11 02:45 | 2021-09-11 02:45 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.94 | 11720 | 11720 |  | MILESTONE_LAND/END CURVE SECTION ON 9/11/2021 AT 02:45 (11,720' MD / 11,144' TVD)
REDWOOD A 1H | 9 | 2021-09-11 02:45 | 2021-09-11 05:45 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.06 | 11720 | 12055 | 111.7 | DRILL LATERAL-ROTATE (335' IN 3 HRS @ 11.7 FPH) WOB-15/20K, SPM-77/77, GPM-400, RPM-35, MRPM-272, TRPM-307, SPP-4600-5300 PSI, DIFF-600/700 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI.
REDWOOD A 1H | 9 | 2021-09-11 05:45 | 2021-09-11 06:00 | 0.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.07 | 12055 | 12075 | 80 | DRILL LATERAL-SLIDE (20' IN .25 HR @ 80 FPH) WOB-30/35K, SPM-77/77, GPM-400, MRPM-272, SPP-4825-5270 PSI, DIFF-250/670 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/11993 T/12013 20' TF-180 0515-0530
REDWOOD A 1H | 10 | 2021-09-11 06:00 | 2021-09-11 14:00 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.41 | 12075 | 13472 | 174.6 | ROTATE (1,397' IN 7.72 HRS @ 181 FPH) WOB-35/45K, SPM-77/77, GPM-400, RPM-70, MRPM-272, TRPM-352, TQ-6K/9K, SPP-4850-5700 PSI, DIFF-725/850 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 06:02 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 12,079', NEW WINDOW: 5' ABOVE / 5' BELOW. WINDOW CHANGE RECEIVED VIA TEXT @ 16:45 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 13,616', NEW WINDOW: 0' ABOVE / 10' BELOW.
REDWOOD A 1H | 10 | 2021-09-11 14:00 | 2021-09-11 19:00 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.61 | 13472 | 13776 | 60.8 | SLIDE (304' IN 5.28 HRS @ 57.6 FPH) WOB-25/35K, SPM-77/77, GPM-400, MRPM-272, SPP-4850-5200 PSI, DIFF-250/350 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/12089 T/12101 12' TF-130R 608-627 SLD F/12182 T/12202 20' TF-140R 659-721 SLD F/12279 T/12304 25' TF-130R 749-816 SLD F/12373 T/12398 25' TF-90R 838-900 SLD F/12560 T/12572 12' TF-30R 1000-1016 SLD F/12655 T/12667 12' TF-30R 1042-1057 SLD F/12843 T/12855 12' TF-HS 1152-1209 SLD F/13125 T/13143 18' TF-180 1330-1353 SLD F/13219 T/13334 15' TF-180 1420-1441 SLD F/13598 T/13618 20' TF-120L 1629-1651 SLD F/13632 T/13652 20' TF-110L 1657-1720 SLD F/13663 T/13683 20' TF-110L 1730-1800 SLD F/13683 T/13776 93' TF-90L 1800-1900
REDWOOD A 1H | 10 | 2021-09-11 19:00 | 2021-09-11 19:45 | 0.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.65 | 13776 | 13776 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80.
REDWOOD A 1H | 10 | 2021-09-11 19:45 | 2021-09-12 03:00 | 7.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.95 | 13776 | 14786 | 139.3 | ROTATE (1,010' IN 7.67 HRS @ 131.7 FPH) WOB-35/45K, SPM-77/77, GPM-400, RPM-70, MRPM-272, TRPM-352, TQ-6K/9K, SPP-4850-5650 PSI, DIFF-800/1000 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT.
REDWOOD A 1H | 10 | 2021-09-12 03:00 | 2021-09-12 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.07 | 14786 | 14906 | 40 | SLIDE (120' IN 2.33 HRS @ 51.5 FPH) WOB-25/35K, SPM-77/77, GPM-400, MRPM-272, SPP-4825-5300 PSI, DIFF-400/475 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/13776 T/13791 15' TF-150L 1950-2000 SLD F/13871 T/13916 45' TF-150L 2045-2139 SLD F/14157 T/14172 15' TF-30L 2346-0005 SLD F/14343 T/14363 20' TF-30R 0124-0141 SLD F/14541 T/14549 8' TF-HS 0257-0308 SLD F/14820 T/14837 17' TF-150L 0500-0524 NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 04:15 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 14,722', NEW TARGET: 11,169' TVD (0' VS) AT 93.9 DEG, WINDOW 5' ABOVE / 5' BELOW.
REDWOOD A 1H | 11 | 2021-09-12 06:00 | 2021-09-12 07:00 | 1 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 8.11 | 14906 | 14906 | 0 | TROUBLE SHOOT AND CHANGE OUT COMMUNICATION WIRE BETWEEN #2 MUD PUMP AND VFD WHILE WORKING PIPE AND MONITORING SICP, SICP= 124 PSI.
REDWOOD A 1H | 11 | 2021-09-12 07:00 | 2021-09-12 11:00 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.28 | 14906 | 15070 | 41 | SLIDE (164' IN 6.25 HRS @ 26.2 FPH) WOB-25/35K, SPM-77/77, GPM-400, MRPM-272, SPP-5000-5450 PSI, DIFF-250/450 PSI, CHOKES- 100% / 100%, FLARE-2'-3', NO MUD CUT, MAX CASING PRESSURE= 150 PSI, AVG CASING PRESSURE= 60 PSI. SLIDE DEPTHS: SLD F/15013 T/15033 20' TF-180 745-821 SLD F/15107 T/15117 10' TF-180 851-913 SLD F/15297 T/15312 15' TF-60R 1035-1107 SLD F/15582 T/15602 20' TF-150L 1308-1411 SLD F/15770 T/15788 18' TF-180 1524-1612 SLD F/15960 T/15966 6' TF-180 1721-1740 SLD F/16235 T/16255 20' TF-140L 1940-2014 SLD F/16524 T/16539 15' TF-150L 2235-2257 SLD F/16621 T/16636 15' TF-150L 2348-0027 SLD F/16801 T/16816 15' TF-180 0155-0230 SLD F/17086 T/17096 10' TF-180 0455-0520
REDWOOD A 1H | 11 | 2021-09-12 11:00 | 2021-09-13 06:00 | 19 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.07 | 15070 | 17175 | 110.8 | ROTATE (2,105' IN 16.75 HRS @ 125.7 FPH) WOB-30/40K, SPM-77/77, GPM-400, RPM-70, MRPM-272, TRPM-352, TQ-7K/14K, SPP-5000-5850 PSI, DIFF-800/1000 PSI, CHOKES- 100% / 100%, FLARE-2'-3', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 250 PSI, AVG SICP= 80 PSI. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. WINDOW CHANGE RECEIVED VIA TEXT @ 17:45 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 15,975', NEW WINDOW: 0' ABOVE / 10' BELOW. TARGET LINE CHANGE 22:02 HRS, DEPTH OF CHANGE 16,485', TARGET CHANGED TO 11,148' TVD @ 0 VS WITH 93.50 INC, WINDOW 5' ABOVE 5' BELOW 50' LEFT/RIGHT
REDWOOD A 1H | 12 | 2021-09-13 06:00 | 2021-09-13 09:30 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.22 | 17175 | 17502 | 93.4 | ROTATE (327' IN 3.43 HRS @ 95.3 FPH) WOB-30/40K, SPM-77/77, GPM-400, RPM-80, MRPM-272, TRPM-352, TQ-10K/14K, SPP-5000-5850 PSI, DIFF-700/850 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 105 PSI, AVG SICP= 60 PSI. STARTED WEIGHTING UP F/10.3 PPG T/10.5 PPG @ 17,282'. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. WINDOW CHANGE RECEIVED VIA TEXT @ 07:37 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 17,309', NEW WINDOW: 0' ABOVE / 10' BELOW. TARGET LINE CHANGE RECEIVED VIA TEXT @ 11:00 HRS, DEPTH OF CHANGE 17,513', TARGET CHANGED TO 11,173' TVD @ 0 VS WITH 93.50 INC, WINDOW 5' ABOVE 5' BELOW 50' LEFT/RIGHT.
REDWOOD A 1H | 12 | 2021-09-13 09:30 | 2021-09-13 11:30 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.3 | 17502 | 17552 | 25 | SLIDE (50' IN 2.07 HRS @ 24.2 FPH) WOB-25/35K, SPM-77/77, GPM-400, MRPM-272, SPP-5000-5450 PSI, DIFF-250/450 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/17184 T/17199 15' TF-90R 605-632 SLD F/17304 T/17324 20' TF-90L 727-826 SLD F/17403 T/17418 15' TF-60L 910-956
REDWOOD A 1H | 12 | 2021-09-13 11:30 | 2021-09-13 12:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.32 | 17552 | 17552 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
REDWOOD A 1H | 12 | 2021-09-13 12:00 | 2021-09-13 17:45 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.56 | 17552 | 18092 | 93.9 | ROTATE (540' IN 5.73 HRS @ 94.2 FPH) WOB-30/40K, SPM-77/77, GPM-400, RPM-80, MRPM-272, TRPM-352, TQ-10K/14K, SPP-5000-5850 PSI, DIFF-700/850 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 55 PSI, AVG SICP= 40 PSI. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. TARGET LINE CHANGE RECEIVED VIA TEXT @ 14:21 HRS, DEPTH OF CHANGE 17,667', TARGET CHANGED TO 11,157' TVD @ 0 VS WITH 93.50 INC, WINDOW 5' ABOVE 5' BELOW 50' LEFT/RIGHT.
REDWOOD A 1H | 12 | 2021-09-13 17:45 | 2021-09-13 19:00 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.61 | 18092 | 18112 | 16 | SLIDE (20' IN 1.27 HRS @ 15.7 FPH) WOB-25/35K, SPM-77/77, GPM-400, MRPM-272, SPP-5000-5450 PSI, DIFF-250/450 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: SLD F/17570 T/17582 12' TF-90L 1211-1253 SLD F/17659 T/17667 8' TF-150L 1344-1418
REDWOOD A 1H | 12 | 2021-09-13 19:00 | 2021-09-13 20:00 | 1 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.66 | 18112 | 18112 | 0 | PUMP UP TD SURVEY, PUMP 1ST SWEEP TO BIT, BACK REAM OUT OF HOLE F/18,112' T/17,742' (TO AVOID PERFORMING CLEAN UP CYCLE IN 12 DEG DOGLEG), SPM: 70/70, GPM-367, RPM-50, TRQ-4K/6K, SPP-4900 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 78 PSI, AVG CASING PRESSURE= 60 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=0 PSI, AVG SICP= 0 PSI.
REDWOOD A 1H | 12 | 2021-09-13 19:00 | 2021-09-13 19:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 9.61 | 18112 | 18112 |  | MILESTONE_TD WELL ON 9/13/2021 @ 19:00.
REDWOOD A 1H | 12 | 2021-09-13 20:00 | 2021-09-13 22:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.74 | 18112 | 18112 | 0 | PERFORM CLEAN UP CYCLE FOR CASING RUN, PUMP 2 TANDEM 30 BBL HIGH VIS SWEEPS. CIRCULATE HOLE CLEAN, RPM-80, SPM: 77/77, GPM-400, INITIAL SPP-5,385 PSI/FINAL SPP- 5350 PSI, CHOKES- 100% / 100%, FLARE-0'-3', MAX CASING PRESSURE= 0 PSI, MAX GAS: 630u. 1ST BTM UP START TQ=6.5K, END=6.5 K, P/U WT=205K, S/O WT=165K 2ND BTM UP END TQ=5.5K, P/U WT=202K, S/O WT=175K 3RD BTM UP END TQ=6K, P/U WT=202K, S/O WT=170K
REDWOOD A 1H | 12 | 2021-09-13 22:00 | 2021-09-13 22:30 | 0.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.76 | 18112 | 18112 | 0 | PULLED 5 STANDS WET, PUMP 30 BBL 17.0 PPG SLUG AND BLED BACK CALCULATED 15.5 BBLS FOR SLUG DROP.
REDWOOD A 1H | 12 | 2021-09-13 22:30 | 2021-09-14 01:00 | 2.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 9.86 | 18112 | 18112 | 0 | STRIP OUT THE HOLE WITH DRY PIPE F/17,262’ T/11,053’, NO EXCESSIVE DRAG, PUMPING .6 BBLS/STD OF 17.0 PPG KILL MUD CALCULATED FILL DOWN THE ANNULUS FOR A TOTAL OF 40 BBLS, MAX CASING PRESSURE= 300 PSI, AVG CASING PRESSURE= 75 PSI, FINAL CASING PRESSURE= 0 PSI, MONITORED SICP, SICP= 0 PSI, OPEN CHOKE AND CHECK FLOW TO TRIP TANK, WELL STATIC, CHECK FLOW DOWN FLOW LINE TO TRIP TANK, WELL STATIC. BOTTOM OF MUD CAP @ 2,445', TOP OF MUD CAP @ 1,575'.
REDWOOD A 1H | 12 | 2021-09-14 01:00 | 2021-09-14 04:45 | 3.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 10.02 | 18112 | 18112 | 0 | TRIP OUT THE HOLE F/11,053' T/3,507', NO EXCESSIVE DRAG, CALCULATED FILL= 45.4 BBL AND ACTUAL FILL= 47.4 BBL.
REDWOOD A 1H | 12 | 2021-09-14 04:45 | 2021-09-14 05:15 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.04 | 18112 | 18112 | 0 | FLOW CHECK, WELL STATIC. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
REDWOOD A 1H | 12 | 2021-09-14 05:15 | 2021-09-14 06:00 | 0.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 10.07 | 18112 | 18112 | 0 | TRIP OUT THE HOLE F/3,507' T/1,211', L/D AGITATOR ON STAND 28, CALCULATED FILL= 12.1 BBLS AND ACTUAL FILL= 17.7 BBLS.
REDWOOD A 1H | 13 | 2021-09-14 06:00 | 2021-09-14 07:15 | 1.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 10.13 | 18112 | 18112 | 0 | TRIP OUT OF HOLE F/1,211' T/BHA, FLOW CHECK AT BHA (WELL STATIC), HOLE TAKING PROPER FILL ON TRIP TANK.
REDWOOD A 1H | 13 | 2021-09-14 07:15 | 2021-09-14 09:00 | 1.75 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.2 | 18112 | 18112 | 0 | L/D DRILL-N-REAMER, X/O, TOMAX THRUSTER AND TOP NMDC. PULL MWD, DRAIN MOTOR, BREAK BIT AND L/D REMAINING BHA. NOTE: MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG. BIT GRADED: 0-1-CT-I-G-X-NO-TD.
REDWOOD A 1H | 13 | 2021-09-14 09:00 | 2021-09-14 09:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 10.22 | 18112 | 18112 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4 1/2" ELEVATORS.
REDWOOD A 1H | 13 | 2021-09-14 09:30 | 2021-09-14 10:30 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.26 | 18112 | 18112 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT.
REDWOOD A 1H | 13 | 2021-09-14 10:30 | 2021-09-14 13:15 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.38 | 18112 | 18112 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/2,395', FILLING PIPE ON THE FLY, CALCULATED DISPLACEMENT= 42.8 BBLS, ACTUAL DISPLACEMENT= 43.1 BBLS.
REDWOOD A 1H | 13 | 2021-09-14 13:15 | 2021-09-14 13:45 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.4 | 18112 | 18112 | 0 | FLOW CHECK, WELL STATIC, REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
REDWOOD A 1H | 13 | 2021-09-14 13:45 | 2021-09-14 18:00 | 4.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.57 | 18112 | 18112 | 0 | RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/2,395' T/8,059', FILLING PIPE ON THE FLY, CALCULATED DISPLACEMENT= 146.8 BBLS, ACTUAL DISPLACEMENT= 140.3 BBLS, FILLING PIPE ON THE FLY. NOTE: KILL MUD @ SURFACE @ 4,173', DIVERTED 100 BBLS OF 10.8 PPG T/12.8 PPG F/TRIP TANK T/TANK #7.
REDWOOD A 1H | 13 | 2021-09-14 18:00 | 2021-09-14 18:30 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.59 | 18112 | 18112 | 0 | FLOW CHECK, WELL STATIC, RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5 1/2" CRT.
REDWOOD A 1H | 13 | 2021-09-14 18:30 | 2021-09-14 21:15 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.71 | 18112 | 18112 | 0 | RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/8,059' T/11,739', FILLING PIPE ON THE FLY.
REDWOOD A 1H | 13 | 2021-09-14 21:15 | 2021-09-14 22:15 | 1 | U | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.75 | 18112 | 18112 | 0 | SEAL LEAKING ON CASING TONGS, ATTEMPT TO REPLACE SEAL (UNABLE TO FIX LEAK), SWAP OUT TONGS FOR BACK UP.
REDWOOD A 1H | 13 | 2021-09-14 22:15 | 2021-09-15 02:30 | 4.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.93 | 18112 | 18112 | 0 | RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/11,739' T/18,066', FILLING PIPE ON THE FLY.
REDWOOD A 1H | 13 | 2021-09-15 02:30 | 2021-09-15 03:15 | 0.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.96 | 18112 | 18112 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND RUN LANDING JOINT F/18,066' T/18,096.3'. LAND CASING ON HANGER W/145K (W/O BLOCKS) RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, RAN 8,027.11' (181 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1-X-OVER, 1 JOINT 5 1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, RAN 9,986.75' (213 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, HANGER AND LANDING JT. FOR TOTAL OF 394 FULL JTS OF 5'' 18# P-110 ICY WEDGE & 5 1/2" 23# P-110 ICY WEDGE 463. CASING SHOE @ 18,096.3' TOP OF FLOAT COLLAR @ 18,044.6' BOTTOM OF TOE SLEEVE VALVE @ 17,997.7' TOP OF TOE SLEEVE VALVE @ 17,972.6' TOP OF X-OVER @ 10,036.6' TOP OF MARKER JOINT ABOVE X-OVER @ 9,971.6' 9 JOINTS 5" LEFT OUT- 399.26' 12 JOINTS 5 1/2" LEFT OUT-565.71'
REDWOOD A 1H | 13 | 2021-09-15 03:15 | 2021-09-15 04:15 | 1 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 11 | 18112 | 18112 | 0 | RIG DOWN FRANK'S CRT AND RIG UP WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 120 PSI.
REDWOOD A 1H | 13 | 2021-09-15 04:15 | 2021-09-15 05:45 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.06 | 18112 | 18112 | 0 | SLOWLY STAGE UP PUMPS TO 100 SPM, CIRCULATE 1-1/2 CASING CAPACITY WHILE RIG DOWN CASING TOOLS, GPM-257, SPP-2000 PSI, CHOKES- 100% / 100%, AVG CASING PRESSURE= 0 PSI, MAX CASING PRESSURE= 50 PSI, FLARE- 2’-10’ AND MAX GAS: 1,361u. MONITOR SICP, SICP=70 PSI.
REDWOOD A 1H | 13 | 2021-09-15 05:45 | 2021-09-15 06:00 | 0.25 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 11.07 | 18112 | 18112 | 0 | SWAP CEMENT IRON FROM RIG STANDPIPE TO CEMENT TRUCK.
REDWOOD A 1H | 14 | 2021-09-15 06:00 | 2021-09-15 09:00 | 3 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 11.2 | 18112 | 18112 | 0 | SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT TRUCK, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI; TRANSFER MUD FROM MUD TANKS TO FRAC TANKS, CEMENTED 5 X 5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 6 BPM 80 BBL 10.5 PPG WEIGHTED SPACER, 253 BBL 13.5 PPG TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, TRANSFER MUD FROM MUD TANKS TO FRAC TANKS, DISPLACED WITH FIRST 20 BBL OF SUGAR WATER, FOLLOWED BY 335 BBL OF FRESH WATER @ 8 BPM (TOTAL OF 355 BBL DISPLACEMENT). OBSERVED 100% RETURNS, SLOWED PUMP RATE TO 2 BPM PRIOR TO BUMPING PLUG, FINAL LIFT PRESSURE WAS 3100 PSI. NOTE: WITH 50 BBLS OF FRESH WATER LEFT TO DISPLACE, THE TIW BEGAN TO LEAK; SHUT DOWN PUMP, BLED PSI OFF, AND ATTEMPTED TO TIGHTEN THE LEAKING BREAK; CONTINUED DISPLACEMENT AT REDUCED RATE OF 4 BPM; REDUCED RATE TO 2 BPM PRIOR TO BUMPING PLUG BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4100 PSI. HELD FOR 5 MIN, BLED BACK 5 BBLS. FLOATS HELD. PLUG DOWN @ 08:55HRS 9/15/2021. INITIAL SICP-0 PSI, FINAL SICP= 0 PSI. MAX CASING PSI W/ PUMPING CEMENT-80 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT- 110 PSI MAX GAS-600u CALCULATED TOP OF CEMENT- 7,230'
REDWOOD A 1H | 14 | 2021-09-15 09:00 | 2021-09-15 09:30 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 11.22 | 18112 | 18112 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP=0 PSI, FINAL SICP= 0 PSI. NOTE: LEFT FOSV OPEN WHILE MONITORING SICP.
REDWOOD A 1H | 14 | 2021-09-15 09:30 | 2021-09-15 12:00 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 11.32 | 18112 | 18112 | 0 | FLOW CHECK BEFORE REMOVING LANDING JT., WELL STATIC. REMOVE FOSV AND ROTATING HEAD, LAY DOWN LANDING JOINT. RIG DOWN CSG ELEVATORS AND RIG UP RIG ELEVATORS. RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER. PUMP @ 50 GPM W/750 PSI TO CLEAN THE TOP OF HANGER. WASH THROUGH BOP'S AND CHOKE MANIFOLD. REMOVE WASH OUT TOOL AND PICK UP PACKOFF. INSTALL STREAM-FLO PACK-OFF, PULL TEST PACK-OFF TO 25K, PRESSURE TEST TO 10K, INSTALL BPV, R/D STREAMFLO
REDWOOD A 1H | 14 | 2021-09-15 12:00 | 2021-09-15 15:00 | 3 | P | PRDHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 11.45 | 18112 | 18112 | 0 | REMOVE 4.5" DIE BLOCKS AND INSTALL 5" DIE BLOCKS; CHANGE OUT 4.5" SAVER SUB; CHANGE DIE BLOCKS BACK TO 4.5" DIE BLOCKS
REDWOOD A 1H | 14 | 2021-09-15 15:00 | 2021-09-15 16:00 | 1 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 11.49 | 18112 | 18112 | 0 | INSTALL BOP WRANGLER, REMOVE TURNBUCKLES, FLOWLINE AND FILL UP LINES. BACK OUT WH SET SCREWS AND RAISE BOP'S, INSTALL WELLHEAD CAP AND TESTED T/5000 PSI. SECURE WELL.
REDWOOD A 1H | 14 | 2021-09-15 16:00 | 2021-09-15 16:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 11.49 | 18112 | 18112 |  | MILESTONE_WELL RELEASE 9/15/21 @ 16:00
REDWOOD A 1H | 14 | 2021-09-15 16:00 | 2021-09-15 16:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 11.49 | 18112 | 18112 |  | MILESTONE_RIG RELEASE 9/15/21 @ 16:00
REDWOOD A 1H | 14 | 2021-09-15 16:00 | 2021-09-15 16:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 11.49 | 18112 | 18112 |  | MILESTONE_TURN OVER TO COMPLETION 9/15/2021 @ 16:00
REDWOOD B 1H | 1 | 2021-07-17 11:45 | 2021-07-17 13:15 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/REDWOOD C 1H T/REDWOOD B 1H; SET MATS, WALK RIG TO REDWOOD B 1H; CENTER AND LEVELED SUB OVER CONDUCTOR.
REDWOOD B 1H | 1 | 2021-07-17 11:45 | 2021-07-17 11:45 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 07/17/2021 @ 11:45
REDWOOD B 1H | 1 | 2021-07-17 13:15 | 2021-07-17 14:00 | 0.75 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | L/D LANDING JT., REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
REDWOOD B 1H | 1 | 2021-07-17 14:00 | 2021-07-17 14:30 | 0.5 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
REDWOOD B 1H | 1 | 2021-07-17 14:30 | 2021-07-17 16:00 | 1.5 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, L/D MOTOR, PICK UP NEW MOTOR AND MAKE UP BIT, REMOVE X-OVER AND PUP JOINT, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, TAG BOTTOM @ 108'.
REDWOOD B 1H | 1 | 2021-07-17 16:00 | 2021-07-17 23:00 | 7 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.29 | 108 | 3129 | 431.6 | ROTATE DRILL F/108' T/3,492' (3,021' IN 4.92 HRS @ 614 FPH) WOB-15-35K, RPM-100, TRQ-3K/18K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,500/2,900 PSI, DIFF-250/750 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM.
REDWOOD B 1H | 1 | 2021-07-17 16:00 | 2021-07-17 16:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 7/17/2021 @ 16:00
REDWOOD B 1H | 1 | 2021-07-17 23:00 | 2021-07-18 01:30 | 2.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.4 | 3129 | 3492 | 145.2 | SLIDE (363' IN 1.7 HRS @ 213.5 FPH) WOB-5/15K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-1,700/2,450 PSI, DIFF-150/350 PSI. SLIDE DEPTHS: SLD F/962' T/977' 15' TF-270M 18:14-18:18 SLD F/1056' T/1071' 15' TF-260M 18:28-18:31 SLD F/1150' T/1164' 14' TF-260M 18:42-18:45 SLD F/1338' T/1350' 12' TF-20L 19:05-19:07 SLD F/1432' T/1447' 15' TF-40L 19:19:-19:22 SLD F/1527' T/1547' 20' TF--60L 19:33-19:36 SLD F/1620' T/1635' 15' TF-60L 19:48-19:52 SLD F/1714' T/1726' 12' TF-30L 20:02-20:06 SLD F/1808' T/1823' 15' TF-20L 20:21-20:25 SLD F/1901' T/1921' 20' TF-20L 20:47-20:53 SLD F/1996' T/2016' 20' TF-HS 21:08-21:12 SLD F/2091' T/2106' 15' TF-20L 21:25-21:30 SLD F/2185' T/2205' 20' TF-10L 21:42-21:47 SLD F/2278' T/2298' 20' TF-HS 22:01-22:06 SLD F/2373' T/2393' 20' TF-20L 22:22-22:29 SLD F/2466' T/2486' 20' TF-20L 22:39-22:45 SLD F/2560' T/2572' 12' TF-60L 22:56-22:59 SLD F/2840' T/2860' 20' TF-20R 23:32-23:37 SLD F/2935' T/2955' 20' TF-30R 23:52-00:00 SLD F/3218' T/3233' 15' TF-HS 00:31-00:38 SLD F/3311' T/3329' 18' TF-HS 00:51-00:58 SLD F/3405' T/3420' 15' TF-HS 01:10-01:15
REDWOOD B 1H | 1 | 2021-07-18 01:30 | 2021-07-18 02:30 | 1 | P | SFHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.44 | 3492 | 3492 | 0 | PUMP 2-30 BBL GEL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,250 PSI.
REDWOOD B 1H | 1 | 2021-07-18 02:30 | 2021-07-18 04:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.5 | 3492 | 3492 | 0 | TRIP OUT OF HOLE F/3,505' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
REDWOOD B 1H | 1 | 2021-07-18 04:00 | 2021-07-18 05:30 | 1.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.56 | 3492 | 3492 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR, L/D MOTOR, PNOY COLLAR, UBHO, AND STAB. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND NO PAD WEAR ON STAB. BIT GRADE: 0-1-NO-A-X-0-NO-TD.
REDWOOD B 1H | 1 | 2021-07-18 05:30 | 2021-07-18 06:00 | 0.5 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.58 | 3492 | 3492 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
REDWOOD B 1H | 2 | 2021-07-18 06:00 | 2021-07-18 06:30 | 0.5 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.6 | 3492 | 3492 | 0 | CONTINUE RIGGING UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
REDWOOD B 1H | 2 | 2021-07-18 06:30 | 2021-07-18 07:00 | 0.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.63 | 3492 | 3492 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BTC CASING, TEST FLOATS (TEST GOOD).
REDWOOD B 1H | 2 | 2021-07-18 07:00 | 2021-07-18 09:00 | 2 | U | SFHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 0.71 | 3492 | 3492 | 0 | CATWALK REMOTE PEDESTAL ON RIG FLOOR STOP COMMUNICATING WITH CATWALK, TROUBLE SHOOT AND REPAIRED ELECTRICAL ISSUE WITH FOOT PEDAL ON REMOTE PEDESTAL.
REDWOOD B 1H | 2 | 2021-07-18 09:00 | 2021-07-18 12:00 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.83 | 3492 | 3492 | 0 | RUN 10 3/4" 45.5# J-55 BTC CASING T/3,482'. RAN 45 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED WELLHEAD T/5,000 PSI. SLACK OFF AND LAND OUT ON BASE PLATE WITH 110K LBS (W/O BLOCKS). SHOE- 3,482' TOP OF FLOAT COLLAR- 3,400' LEFT OUT 9 JOINTS-353.44'
REDWOOD B 1H | 2 | 2021-07-18 12:00 | 2021-07-18 13:15 | 1.25 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.89 | 3492 | 3492 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-321, SPP-100. NO LOSSES.
REDWOOD B 1H | 2 | 2021-07-18 13:15 | 2021-07-18 13:45 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.91 | 3492 | 3492 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, REMOVE CSG BAILS AND ELEVATORS, INSTALL RIG ELEVATORS, REMOVE MOUSE HOLE, RIG UP STREAMFLO PUP JOINT, CEMENT HEAD, AND CIRCULATING IRON.
REDWOOD B 1H | 2 | 2021-07-18 13:45 | 2021-07-18 16:00 | 2.25 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1 | 3492 | 3492 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 371 BBLS 11.6 PPG LEAD CEMENT, 98 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 325 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/880 PSI PRESSURED UP T/1380 PSI (500 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2.0 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 174 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS. NOTE: SLIP AND CUT 50’ OF DRILL LINE, RIG UP KILL LINE FROM MUD PUMPS, PREP TO NIPPLE UP BOP'S WHILE OFFLINE CEMENTING.
REDWOOD B 1H | 2 | 2021-07-18 16:00 | 2021-07-18 17:00 | 1 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.04 | 3492 | 3492 | 0 | PRESSURE TEST 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, FLUSH THROUGH AND RIG DOWN CELLAR PUMPS, RIG UP HYDRAULIC LINES TO BOP.
REDWOOD B 1H | 2 | 2021-07-18 17:00 | 2021-07-18 19:00 | 2 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.13 | 3492 | 3492 | 0 | INSTALL BOP ONTO WELLHEAD, ATTEMPTED TO STREAM-FLO ADAPTER FLANGE TO WELLHEAD, TROUBLE SHOOT STREAM-FLO ADAPTER NOT MAKING UP TO WELLHEAD PROPERLY. NOTE: PRESSURE TEST CHOKE MANIFOLD, FLOOR VALVES AND MP LINES/VALVES OFFLINE.
REDWOOD B 1H | 2 | 2021-07-18 19:00 | 2021-07-18 20:30 | 1.5 | P | SFHLCSG | BOP | SVCBOP | SERVICE BOP | 1.19 | 3492 | 3492 | 0 | CHANGE OUT ANNULAR, WAIT ON EXTRA STREAM-FLO HAND TO HELP TROUBLESHOOT BOP ADAPTER. NOTE: PRESSURE TEST CHOKE MANIFOLD, FLOOR VALVES AND MP LINES/VALVES OFFLINE.
REDWOOD B 1H | 2 | 2021-07-18 20:30 | 2021-07-19 01:30 | 5 | U | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.4 | 3492 | 3492 | 0 | INSTALL TEST PLUG AND ATTEMPT TO TEST WELHEAD (FAILED TEST), P/U STACK AND TROUBLESHOOT BOP ADAPTER (LOCK DOWN INSERTS INSTALLED UPSIDE DOWN), REINSTALL LOCK DOWN INSERTS PROPERLY.
REDWOOD B 1H | 2 | 2021-07-19 01:30 | 2021-07-19 04:00 | 2.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.5 | 3492 | 3492 | 0 | INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, N/U ROTATING HEAD INSTALL KILL LINE, INSTALL CHOKE LINE TO BOP AND CHOKE, HOOK UP HYDRAULIC LINES TO BOP STACK, FUNCTION TEST SAME.
REDWOOD B 1H | 2 | 2021-07-19 04:00 | 2021-07-19 06:00 | 2 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.58 | 3492 | 3492 | 0 | INSTALL TEST PLUG ON TEST JOINT AND TEST BOP'S: TEST TOP RAMS, LOWER RAMS, INSIDE AND OUTSIDE KILL VALVES, INSIDE AND OUTSIDE HCR VALVES, WELLHEAD ADAPTER, KILL LINES BACK TO #1 AND #2 PUMPS, BLINDS AND KILL LINE CHECK VALVE TO 250 PSI LOW / 5000 PSI HIGH, TEST ANNULAR TO 250 PSI LOW / 3500 PSI HIGH. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. REMOVE TEST CAP AND RIG DOWN TESTERS. CLOSED CASING VALVE.
REDWOOD B 1H | 3 | 2021-07-19 06:00 | 2021-07-19 07:15 | 1.25 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.64 | 3492 | 3492 | 0 | CONTINUE TESTING BOP’S: KILL LINE BACK TO PUMPS, BLINDS, KILL LINE CHECK VALVE 250 PSI LOW /5000 PIS HIGH, INSTALL ROTATING HEAD TEST CAP, TEST ORBIT VALVE, ROTATING HEAD AND SPACER SPOOL 250 PSI LOW / 1500 PSI HIGH; RIG DOWN TESTERS.
REDWOOD B 1H | 3 | 2021-07-19 07:15 | 2021-07-19 11:30 | 4.25 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.81 | 3492 | 3492 | 0 | MAKE UP FLOW LINE TO ROTATING HEAD AND TO FLOW LINE SCISSOR, FILL UP LINE, CASING FILL LINE, RIG UP KATCH KAN EQUIPMENT ON STACK, FILL MUD TANKS WITH OBM, PERFORM ACCUMULATOR DRAW DOWN TEST.
REDWOOD B 1H | 3 | 2021-07-19 11:30 | 2021-07-19 12:30 | 1 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.85 | 3492 | 3492 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE AND MOUSE HOLE, CLOSED CASING VALVE
REDWOOD B 1H | 3 | 2021-07-19 12:30 | 2021-07-19 15:00 | 2.5 | P | SFHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 1.96 | 3492 | 3492 | 0 | PICK UP (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 5.82' BIT TO BEND 8-1/4" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, 22 STDS DRILL PIPE AND DSW AGITATOR, BIT TO SVY-69' AND GAMMA-59'. TEST MWD-TEST GOOD
REDWOOD B 1H | 3 | 2021-07-19 15:00 | 2021-07-19 16:00 | 1 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 2 | 3492 | 3492 | 0 | TRIP IN HOLE F/BHA T/2,293', HOLE GIVING PROPER FILL.
REDWOOD B 1H | 3 | 2021-07-19 16:00 | 2021-07-19 17:00 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.04 | 3492 | 3492 | 0 | SERVICE, TOP DRIVE, DRAWWORKS AND ST-80.
REDWOOD B 1H | 3 | 2021-07-19 17:00 | 2021-07-19 18:00 | 1 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 2.08 | 3492 | 3492 | 0 | TRIP IN HOLE F/BHA T/3,400'. PICK UP AGITATOR ON STAND 22: PSI BEFORE-470, PSI AFTER-580 @ 295 GPM.
REDWOOD B 1H | 3 | 2021-07-19 18:00 | 2021-07-19 19:00 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 2.13 | 3492 | 3492 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD, CONFIRM PROPER VALVE ALIGNMENT, FILL GAS SEPERATOR, PERORM BOP DRILL, RESPONSE TIME= 20 SECONDS.
REDWOOD B 1H | 3 | 2021-07-19 19:00 | 2021-07-19 19:30 | 0.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 2.15 | 3492 | 3492 | 0 | DRILL SHOE TRACK AND CEMENT F/3,400' T/3,492', GPM-350, SPP- 1196/1212 PSI, DIFF-159/175, RPM-30, TQ-2/6K
REDWOOD B 1H | 3 | 2021-07-19 19:30 | 2021-07-19 20:00 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 2.17 | 3492 | 3502 | 20 | DRILL 10' NEW FORMATION F/3,492' T/3,502', GPM-350, SPP- 1196/1212 PSI, DIFF-159/175,RPM-30, TQ-2/6K
REDWOOD B 1H | 3 | 2021-07-19 20:00 | 2021-07-19 20:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.19 | 3502 | 3502 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-350, SPP-1074 PSI, RPM-30.
REDWOOD B 1H | 3 | 2021-07-19 20:30 | 2021-07-19 21:00 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 2.21 | 3502 | 3502 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, 501 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,482' / TVD-3,438'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE ON THE REMOTE CHOKE PANEL.
REDWOOD B 1H | 3 | 2021-07-19 21:00 | 2021-07-20 04:00 | 7 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.5 | 3502 | 6027 | 360.7 | ROT (2,525' IN 5.92 HRS @ 426.5 FPH) WOB: 20/33K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 8K/15.5K, SPP: 2,000/4,325 PSI, DIFF: 300/650 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
REDWOOD B 1H | 3 | 2021-07-20 04:00 | 2021-07-20 06:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.58 | 6027 | 6275 | 124 | SLIDE (248' IN 1.73 HRS @ 143.4 FPH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 2,800/4,750 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: SLD F/4362' T/4370' 8' TF-180 23:08-23:12 SLD F/4545' T/4557' 12' TF-180 23:50-23:54 SLD F/4645' T/4655' 10' TF-180 00:11-00:14 SLD F/4740' T/4752' 12' TF-150R 00:27-00:33 SLD F/4832' T/4844' 12' TF-150R 00:47-00:54 SLD F/4927' T/4939' 12' TF-150R 01:06-01:11 SLD F/5017' T/5031' 14' TF-140R 01:30-01:37 SLD F/5112' T/5127' 15' TF-140R 01:50-01:58 SLD F/5207' T/5225' 18' TF-140R 02:10-02:19 SLD F/5304' T/5322' 18' TF-130R 02:36-02:43 SLD F/5393' T/5411' 18' TF-130R 02:57-03:03 SLD F/5490' T/5508' 18' TF-120R 03:16-03:23 SLD F/5583' T/5601' 18' TF-130R 03:36-03:43 SLD F/5678' T/5693' 15' TF-30M 03:56-04:02 SLD F/5769' T/5784' 15' TF-90M 04:15-04:22 SLD F/5867' T/5882' 15' TF-150M 04:42-04:50 SLD F/5960' T/5978' 18' TF-150M 05:03-05:10
REDWOOD B 1H | 4 | 2021-07-20 06:00 | 2021-07-20 09:45 | 3.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.74 | 6275 | 7318 | 278.1 | ROT (1043' IN 3.7 HRS @ 282 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/15K, SPP: 4100/5100 PSI, DIFF: 800/1000 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
REDWOOD B 1H | 4 | 2021-07-20 09:45 | 2021-07-20 10:15 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.76 | 7318 | 7348 | 60 | SLIDE (30' IN .55 HRS @ 54.6 FPH) WOB: 10K/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4600 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/6441 T/6451 10' TF-120M 629-638 SLD F/6535 T/6545 10' TF-90M 652-707 SLD F/6906 T/6916 10' TF-90M 831-840
REDWOOD B 1H | 4 | 2021-07-20 10:15 | 2021-07-20 11:00 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.79 | 7348 | 7546 | 264 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGE SWAB ON #2 MUD PUMP, ROTATE (264' IN .75 HR @ 157.3 FPH) WOB: 20/30K, SPM: 114/114, GPM: 730, MMRPM: 121, SPP: 3200/3900 PSI, DIFF: 500/700 PSI.
REDWOOD B 1H | 4 | 2021-07-20 11:00 | 2021-07-20 11:15 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.8 | 7546 | 7616 | 280 | ROT (70' IN .25 HRS @ 282 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/15K, SPP: 4100/5100 PSI, DIFF: 800/1000 PSI.
REDWOOD B 1H | 4 | 2021-07-20 11:15 | 2021-07-20 12:00 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.83 | 7616 | 7827 | 281.3 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGE SWAB ON #2 MUD PUMP, ROTATE (211' IN .75 HR @ 281.3 FPH) WOB: 20/30K, SPM: 114/114, GPM: 730, MMRPM: 121, SPP: 3200/3900 PSI, DIFF: 500/700 PSI.
REDWOOD B 1H | 4 | 2021-07-20 12:00 | 2021-07-20 17:00 | 5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.04 | 7827 | 8919 | 218.4 | ROT (1092' IN 4.83 HRS @ 226.1 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 5000/5500 PSI, DIFF: 300/500 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
REDWOOD B 1H | 4 | 2021-07-20 17:00 | 2021-07-20 17:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.06 | 8919 | 8954 | 70 | SLIDE (35' IN .67 HRS @ 52.2 FPH) WOB: 10K/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4600 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/7844 T/7854 10' TF-90R 1211-1224 SLD F/8131 T/8141 10' TF-180 1323-1336 SLD F/8213 T/8228 15' TF-90R 1351-1405
REDWOOD B 1H | 4 | 2021-07-20 17:30 | 2021-07-20 18:00 | 0.5 | U | INTHL | RIGMT | SVCMD | SERVICE MUD PUMPS / CIRC EQUIP | 3.08 | 8954 | 8954 | 0 | OBSERVED DIFF INCREASE F/500 PSI T/1150 PSI @ 8,597', PULLED OFF BOTTOM AND DIFF STABLIZED @ 900 PSI, SHUT DOWN PUMPS AND BLED OFF 2", TURN PUMPS ON @ 720 GPM AND SLOWLY SLACK OFF, STARTED BACK DRILLING @ 200 FPH, STAGED UP T/770 GPM AND 250 FPH, STAGED UP T/800 GPM AND 300 FPH, STAGED UP T/860 GPM AND 300 FPH AND STAGED UP T/900 GPM AND 450 FPH. OBSERVED 800 PSI INCREASE IN OFF BOTTOM PRESSURE. WORK PIPE WHILE TROUBLESHOOT SURFACE CIRCULATING EQUIPMENT INCLUDING INLINE SCREEN (NO ISSUE FOUND), DECISION WAS MADE TO CONTINUE DRILLING.
REDWOOD B 1H | 4 | 2021-07-20 18:00 | 2021-07-20 23:45 | 5.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.32 | 8954 | 10262 | 227.5 | ROT (1308' IN 5.87 HRS @ 222.8 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 5000/5500 PSI, DIFF: 300/500 PSI. NOTE: PUMPING 10 BBL 15 PPB LCM SWEEPS EVERY +/-300' CONSISTING OF 5 PPB NEW CARB, 5 PPB NEW PHALT AND 5 PPB MAGNAFIBER.
REDWOOD B 1H | 4 | 2021-07-20 23:45 | 2021-07-21 00:30 | 0.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.35 | 10262 | 10284 | 29.3 | SLIDE (22' IN .63 HRS @ 35 FPH) WOB: 10K/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4100/4600 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/9,723 T/9,733 10' TF-150M 20:42-21:00 SLD F/10,094 T/8,141 12' TF-150M 22:57-23:20
REDWOOD B 1H | 4 | 2021-07-21 00:30 | 2021-07-21 06:00 | 5.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.58 | 10284 | 10485 | 36.5 | SLIDE (201' IN 5.35 HRS @ 37.6 FPH) WOB: 10K/20K, SPM: 75/75/75, GPM: 900, MMRPM: 149, SPP: 4100/4800 PSI, DIFF: 150/350 PSI.
REDWOOD B 1H | 4 | 2021-07-21 00:30 | 2021-07-21 00:30 | 0 | P | INTHL | MSTN | SCRV | MILESTONE_START CURVE SECTION | 3.35 | 10284 | 10284 |  | MILESTONE_START CURVE ON 7/21/2021 @ 00:30
REDWOOD B 1H | 5 | 2021-07-21 06:00 | 2021-07-21 07:15 | 1.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.64 | 10485 | 10540 | 44 | BUILD CURVE/SLD (55' IN 1.25 HRS @ 44 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10485' T/10,540' 55' TF-HS 0600-0715
REDWOOD B 1H | 5 | 2021-07-21 07:15 | 2021-07-21 09:00 | 1.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.71 | 10540 | 10597 | 32.6 | BUILD CURVE/SLD (57' IN 1.75 HRS @ 31 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,540' T/10,597' 57' TF-HS 0715-0900 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING A SWAB ON #2 MUD PUMP
REDWOOD B 1H | 5 | 2021-07-21 09:00 | 2021-07-21 10:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.75 | 10597 | 10621 | 24 | BUILD CURVE/SLD (24' IN 1 HRS @ 24 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,597' T/10,621' 24' TF-HS 0900-1000
REDWOOD B 1H | 5 | 2021-07-21 10:00 | 2021-07-21 12:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.83 | 10621 | 10690 | 34.5 | BUILD CURVE/SLD (69' IN 2 HRS @ 35 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,621' T/10,690' 57' TF-HS 1000-1200 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING A SWAB ON #2 MUD PUMP
REDWOOD B 1H | 5 | 2021-07-21 12:00 | 2021-07-21 17:00 | 5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.04 | 10690 | 10835 | 29 | BUILD CURVE/SLD (145' IN 5 HRS @ 29 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,690' T/10,835' 145' TF-HS 1200-1700
REDWOOD B 1H | 5 | 2021-07-21 17:00 | 2021-07-21 18:00 | 1 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.08 | 10835 | 10835 | 0 | LUBRICATE TOP DRIVE AND DRAWORKS
REDWOOD B 1H | 5 | 2021-07-21 18:00 | 2021-07-21 19:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.15 | 10835 | 10880 | 30 | BUILD CURVE/SLD (45' IN 1.5 HRS @ 30 FPH) WOB: 25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,835' T/10,880' 45' TF-HS 1800-1930
REDWOOD B 1H | 5 | 2021-07-21 19:30 | 2021-07-21 21:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.21 | 10880 | 10903 | 15.3 | BUILD CURVE/SLD (23' IN 1.5 HRS @ 15 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,880' T/10,903' 23' TF-HS 1930-2100 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING LINER GASKET & WEAR PLATE ON #1 MUD PUMP
REDWOOD B 1H | 5 | 2021-07-21 21:00 | 2021-07-21 21:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.23 | 10903 | 10916 | 26 | BUILD CURVE/SLD (13' IN .5 HRS @ 26 FPH) WOB:25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,903' T/10,916' 13' TF-HS 2100-2130
REDWOOD B 1H | 5 | 2021-07-21 21:30 | 2021-07-21 22:00 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.25 | 10916 | 10927 | 22 | BUILD CURVE/SLD (11' IN .5 HRS @ 22 FPH) WOB: 25/30K, SPM: 110/110, GPM: 706, MMRPM: 117, SPP: 4100/4200 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,916' T/10,927' 23' TF-HS 2130-2200 NOTE: CONTROL SLIDING WITH 2 MUD PUMPS WHILE CHANGING 2" VALVE ON #1 MUD PUMP
REDWOOD B 1H | 5 | 2021-07-21 22:00 | 2021-07-21 23:00 | 1 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.29 | 10927 | 10936 | 9 | BUILD CURVE/SLD (9' IN 1 HRS @ 9 FPH) WOB:25/30K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 5100/5300 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/10,927' T/10,936' 9' TF-HS 2200-2300
REDWOOD B 1H | 5 | 2021-07-21 23:00 | 2021-07-22 00:30 | 1.5 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 4.35 | 10936 | 10936 | 0 | PERFORMED CLEAN UP CYCLE PUMPING 2-30 BBL SWEEPS SURFACE TO SURFACE TO CLEAN HOLE & PREP OPEN HOLE FOR 7-5/8" CASING. GPM-866, SPP-5000, SHAKERS CLEAN
REDWOOD B 1H | 5 | 2021-07-22 00:30 | 2021-07-22 01:00 | 0.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.38 | 10936 | 10936 | 0 | TOOH F/10,936' T/10,489', NORMAL DRAG
REDWOOD B 1H | 5 | 2021-07-22 01:00 | 2021-07-22 01:30 | 0.5 | P | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 4.4 | 10936 | 10936 | 0 | FLOW CHECK, WELL STATIC. PUMP SLUG
REDWOOD B 1H | 5 | 2021-07-22 01:30 | 2021-07-22 02:45 | 1.25 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.45 | 10936 | 10936 | 0 | TOOH F/10,489' - T/6992', PROPER FILL
REDWOOD B 1H | 5 | 2021-07-22 02:45 | 2021-07-22 03:45 | 1 | U | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.49 | 10936 | 10936 | 0 | WORK TIGHT HOLE F/6992' T/6942'
REDWOOD B 1H | 5 | 2021-07-22 03:45 | 2021-07-22 04:15 | 0.5 | U | INTHLCSG | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 4.51 | 10936 | 10936 | 0 | WASH & REAM F/6,952' T/7,000' THEN BACK UP T/6,945'. GPM- 680, SPP-3000, RPM-50, TQ-8K, HOOK LOAD 210K. AT 6,945' HOOK LOAD CAME UP TO 230K, TQ CAME UP TO 24K, SPP-3475, SLACKED OFF AND LOST 70K STRING WEIGHT AND 1,600 PSI PUMP PRESSURE.
REDWOOD B 1H | 5 | 2021-07-22 04:15 | 2021-07-22 06:00 | 1.75 | U | INTHLCSG | TRIP | EVAL | TRIP FOR EVAL WELL / CORING / LOG / DST | 4.58 | 10936 | 10936 | 0 | CALCULATED LOST DRILL STRING AT AGITATOR, TRIP IN HOLE 4 STANDS ATTEMPTING TO TAG FISH WITH NO SUCCESS; PUMP SLUG; POOH FOR FISHING OPERATIONS
REDWOOD B 1H | 6 | 2021-07-22 06:00 | 2021-07-22 09:00 | 3 | U | INTHLCSG | TRIP | EVAL | TRIP FOR EVAL WELL / CORING / LOG / DST | 4.71 | 10936 | 10936 | 0 | TIH F/6,942' T/TOP OF FISH 8,670', TRIP IN SLOW LOOKING FOR FISH. WASH & ROTATE DOWN AT 10-RPM, TQ-3K, 300-GPM, SPP-450, HOOKLOAD 210K. SPP INCREASED TO 600 PSI, KILLED PUMP, TORQUED UP DRILL STRING TO 24K. P/U TO 350K AND PULLED BHA OFF BTTM.
REDWOOD B 1H | 6 | 2021-07-22 09:00 | 2021-07-22 09:30 | 0.5 | U | INTHLCSG | TRIP | EVAL | TRIP FOR EVAL WELL / CORING / LOG / DST | 4.73 | 10936 | 10936 | 0 | TOOH F/10936' T/10672', NORMAL DRAG
REDWOOD B 1H | 6 | 2021-07-22 09:30 | 2021-07-22 10:00 | 0.5 | U | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 4.75 | 10936 | 10936 | 0 | FLOW CHECK, WELL STATIC. PUMP SLUG.
REDWOOD B 1H | 6 | 2021-07-22 10:00 | 2021-07-22 11:15 | 1.25 | U | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.8 | 10936 | 10936 | 0 | TOOH F/10672' T/6942', PROPER FILL WITH TRIP TANK, NORMAL DRAG.
REDWOOD B 1H | 6 | 2021-07-22 11:15 | 2021-07-22 15:30 | 4.25 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.98 | 10936 | 10936 | 0 | TOOH F/6942' T/274', PROPER FILL WITH TRIP TANK; PERFORM FLOW CHECK @ SHOE; REMOVE ROT. HEAD/ INSTALL TRIP NIPPLE NOTE: WORKED TIGHT HOLE ON ELEVATORS F/6942' T/6800'
REDWOOD B 1H | 6 | 2021-07-22 15:30 | 2021-07-22 19:00 | 3.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 5.13 | 10936 | 10936 | 0 | LAY DOWN 1 STAND OF HWDP, 6-6.5" DC AND DIRECTIONAL BHA - (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 5.82' BIT TO BEND 8-1/4" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH - MUD MOTOR DRAINED GOOD WITH LITTLE SQUAT
REDWOOD B 1H | 6 | 2021-07-22 19:00 | 2021-07-22 19:45 | 0.75 | P | INTHLCSG | SFTY | INSPT | SAFETY INSPECTION | 5.16 | 10936 | 10936 | 0 | CLEAN OBM FROM RIG FLOOR TO REDUCE SLIP HAZARDS, PULL WEAR BUSHING, COMPANY REPRESENTIVE WITNESS.
REDWOOD B 1H | 6 | 2021-07-22 19:45 | 2021-07-22 21:45 | 2 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 5.24 | 10936 | 10936 | 0 | CHANGED OUT TOP VBR'S TO 7-5/8" CASING RAMS, PICKED UP JOINT OF DRILL PIPE AND TEST PLUG. PRESSURE TESTED BONNET SEALS T/1500 PSI
REDWOOD B 1H | 6 | 2021-07-22 21:45 | 2021-07-22 23:00 | 1.25 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 5.29 | 10936 | 10936 | 0 | HOLD PJSM AND RIG UP FRANKS CASING CREW TOOLS & EQUIPMENT.
REDWOOD B 1H | 6 | 2021-07-22 23:00 | 2021-07-23 06:00 | 7 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.58 | 10936 | 10936 | 0 | MAKE UP SHOE TRACK, 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, TEST FLOATS, BEGIN RUNNING INTERMEDIATE CASING T/7,000', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 7 | 2021-07-23 06:00 | 2021-07-23 09:00 | 3 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.71 | 10936 | 10936 | 0 | CONTINUE PICKING UP AND RUNNING 7 5/8" 29.7# P-110 IC BTC CSG F/ 7,000' T/10,923', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, TEST FLOATS, THEN RAN 231 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, TOTAL OF 234 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALLED 40 LATCH ON BOW SPRING CENTRALIZERS @ 10,595' AND EVERY 4TH JT UP TO 3,325'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/230K (W/O BLOCKS) FLOAT SHOE-10,923.9' TOP OF FLOAT COLLAR-10,828.6', 8 JOINTS LEFT OUT- 374.73' & 2-10' PUP JT OUT
REDWOOD B 1H | 7 | 2021-07-23 09:00 | 2021-07-23 09:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 5.73 | 10936 | 10936 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
REDWOOD B 1H | 7 | 2021-07-23 09:30 | 2021-07-23 12:30 | 3 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.85 | 10936 | 10936 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 107, 8.0 BPM, SPP: 625 PSI, NO LOSSES.
REDWOOD B 1H | 7 | 2021-07-23 12:30 | 2021-07-23 13:30 | 1 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.9 | 10936 | 10936 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/7500 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 165 BBL 11.8 PPG 914 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT; AFTER PUMPING 40 BBL SPACER AND 165 BBL OF LEAD CEMENT, THE CEMENT PUMP TRUCK FAILED; FLUSHED LINES WITH WATER AND SWAPPED CIRCULATING IRON OVER TO RIG STANDPIPE TO CIRCULATE OUT CEMENT WITH RIG MUD PUMPS
REDWOOD B 1H | 7 | 2021-07-23 13:30 | 2021-07-23 22:30 | 9 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.27 | 10936 | 10936 | 0 | CIRCULATE AND DISPLACE 40 BBLS OF SPACER AND 165 BBLS OF LEAD CEMENT BACK TO SURFACE @ 8 BPM WITH RIG MUD PUMPS, SPP-550; CONTINUE CIRCULATING WITH RIG MUD PUMPS @ 8 BPM WHILE WAITING ON REPLACEMENT PUMP TRUCK AND CEMENT TO ARRIVE ON LOCATION. CEMENTING TRUCKS & CEMENT ARRIVED ON LOCATION @ 20:30 HRS. SPOTTED CEMENTING TRUCKS AND RIGGED UP ALL CEMENTING EQUIPMENT
REDWOOD B 1H | 7 | 2021-07-23 22:30 | 2021-07-24 01:00 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 6.38 | 10936 | 10936 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/7500 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 316 BBL 11.8 PPG 914 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 78 BBL 16.2 PPG 306 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 497 BBLS OF 9.7 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1700 PSI AT 3 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/2200 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI (6 BBLS)-FLOATS HELD. FINISHED CEMENTING @ 01:00 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. 40 BBLS SPACER AND 32 BBLS CEMENT BACK TO SURFACE. ESTIMATED TOP OF CEMENT: SURFACE
REDWOOD B 1H | 7 | 2021-07-24 01:00 | 2021-07-24 01:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 6.4 | 10936 | 10936 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. BLED BACK 9 BBLS
REDWOOD B 1H | 7 | 2021-07-24 01:30 | 2021-07-24 02:30 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 6.44 | 10936 | 10936 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
REDWOOD B 1H | 7 | 2021-07-24 02:30 | 2021-07-24 04:15 | 1.75 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 6.51 | 10936 | 10936 | 0 | FLUSH THROUGH BOP AND FLOW LINE WITH WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
REDWOOD B 1H | 7 | 2021-07-24 04:15 | 2021-07-24 06:00 | 1.75 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 6.58 | 10936 | 10936 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL.
REDWOOD B 1H | 7 | 2021-07-24 06:00 | 2021-07-24 06:00 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 6.58 | 10936 | 10936 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 7-24-2021 @ 06:00
REDWOOD B 1H | 8 | 2021-09-23 18:00 | 2021-09-23 20:00 | 2 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 6.67 | 10936 | 10936 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM REDWOOD C 1H TO REDWOOD B 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN. NOTE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE.
REDWOOD B 1H | 8 | 2021-09-23 18:00 | 2021-09-23 18:00 | 0 | P | INTHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 6.58 | 10936 | 10936 |  | MILESTONE_RESUME WELL 1 ON 9/23/2021 @ 18:00
REDWOOD B 1H | 8 | 2021-09-23 20:00 | 2021-09-23 22:00 | 2 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 6.75 | 10936 | 10936 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
REDWOOD B 1H | 8 | 2021-09-23 22:00 | 2021-09-24 01:00 | 3 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.88 | 10936 | 10936 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. RIG DOWN TEST EQUIPMENT. VERIFY STACK AND CHOKE ALIGNMENT.
REDWOOD B 1H | 8 | 2021-09-24 01:00 | 2021-09-24 02:00 | 1 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 6.92 | 10936 | 10936 | 0 | SLIP AND CUT 120' OF DRILLING LINE RIG MANAGER PRESENT.
REDWOOD B 1H | 8 | 2021-09-24 02:00 | 2021-09-24 02:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.94 | 10936 | 10936 | 0 | SERVICE RIG: LUBE TD, ST-80 & DRWKS. RIG MANAGER PRESENT
REDWOOD B 1H | 8 | 2021-09-24 02:30 | 2021-09-24 03:00 | 0.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 6.96 | 10936 | 10936 | 0 | REMOVE TEST PLUG AND INSTALL WEAR BUSHING & TRIP NIPPLE.
REDWOOD B 1H | 8 | 2021-09-24 03:00 | 2021-09-24 05:00 | 2 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 7.04 | 10936 | 10936 | 0 | PICK UP DIR BHA #3: 6.75" SECURITY GTD64M SN:13635755JETS 6X18 TFA: 1.491), MOTOR: 5.5", 6/7, 11.7 @ 2.12°TS HS88+.011, .89 REV/GAL; 3.97' BIT TO BEND; 5.56" PAD OD; FLOW RANGE- 150/350 GPM; MAX DIFF-1,000 PSI; STALL TRQ-7,623 FT/LBS; BTI VALVE, 5" NMPDC, 5'', NMDC, 5" UBHO, 5", NMPDC, 5",NMDC, TOMAX TOOL, FILTER SUB, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-68'. BIT TO GAMMA-55'. TEST MWD TOOL, RESULT: GOOD TEST
REDWOOD B 1H | 8 | 2021-09-24 05:00 | 2021-09-24 06:00 | 1 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.08 | 10936 | 10936 | 0 | TIH W/BHA #3 F/BHA-T/2,100' HOLE GIVING PROPER DISCPLACMENT.
REDWOOD B 1H | 9 | 2021-09-24 06:00 | 2021-09-24 06:30 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.1 | 10936 | 10936 | 0 | TIH W/BHA #3 F/2,100'-T/2,816' HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 9 | 2021-09-24 06:30 | 2021-09-24 07:15 | 0.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.14 | 10936 | 10936 | 0 | FILLED PIPE & FLOW TESTED DRILL STRING, PICKED UP AGITATOR AND FLOW TESTED. SPP BEFORE: 1305 PSI, SPP AFTER: 1680 PSI @ 262 GPM.
REDWOOD B 1H | 9 | 2021-09-24 07:15 | 2021-09-24 07:45 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.16 | 10936 | 10936 | 0 | TIH W/BHA #3 F/2,816'-T/4,380' HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 9 | 2021-09-24 07:45 | 2021-09-24 08:30 | 0.75 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.19 | 10936 | 10936 | 0 | SERVICE RIG: C/O ST-80 DIES
REDWOOD B 1H | 9 | 2021-09-24 08:30 | 2021-09-24 11:00 | 2.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.29 | 10936 | 10936 | 0 | TIH W/BHA #3 F/4,380'-T/10,800' HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 9 | 2021-09-24 11:00 | 2021-09-24 12:00 | 1 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 7.33 | 10936 | 10936 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD; VERIFY VALVE ALIGNMENT TO BOP AND CHOKE MANIFOLD; PERFORM BOP DRILL AND FILL GAS SEPARATOR NOTE: FLOW CHECK=NO FLOW.
REDWOOD B 1H | 9 | 2021-09-24 12:00 | 2021-09-24 12:45 | 0.75 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 7.36 | 10936 | 10946 | 13.3 | DRILL SHOE TRACK AND 10' NEW FORMATION F/10,800'- T/10,946', WOB-10K, RPM-30, GPM-250, SPP: 2500, PSI, TQ-4/6K. TAG FLOAT @ 10,828' TAG SHOE @ 10,924'
REDWOOD B 1H | 9 | 2021-09-24 12:45 | 2021-09-24 13:30 | 0.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.4 | 10946 | 10946 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T GPM-250, SPP-2500 PSI, RPM-30. MW IN: 10.3 PPG MW OUT:10.3 PPG
REDWOOD B 1H | 9 | 2021-09-24 13:30 | 2021-09-24 14:00 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 7.42 | 10946 | 10946 | 0 | PERFORM F.I.T. WITH 10.3 PPG OBM, 1,516 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,924' / TVD-10,797'
REDWOOD B 1H | 9 | 2021-09-24 14:00 | 2021-09-24 20:15 | 6.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.68 | 10946 | 11376 | 68.8 | BUILD CURVE-SLIDE (430' IN 6.33 HR @ 67.93 FPH) WOB-20/30K, SPM-67/67, GPM 351, MRPM:312.39, SPP:4,300-4,515 PSI, DIFF:750/900 PSI, CHOKES: 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI. SLIDE DEPTHS: F/10,946'-T/11,131', 185', TF:70L, 14:50-16:55 F/11,171'-T/11,226', 55', TF:60L, 17:15-18:00 F/11,226'-T/11,256', 30', TF:HS, 18:00-18:32 F/11,320'-T/11,340', 10', TF:HS, 19:00-19:22 F/11,416'-T/11,463', 47', TF:HS, 20:05-20:33 F/11,510'-T/11,565', 55', TF:30L, 21:01-21:35 F/11,965'-T/11,710', 15', TF:HS, 11:00-11:15 F/11,793'-T/11,816', 23', TF:HS, 23:43-00:12
REDWOOD B 1H | 9 | 2021-09-24 14:00 | 2021-09-24 14:00 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 7.42 | 10946 | 10946 |  | MILESTONE_START CURVE SECTION 9-24-2021 @ 14:00
REDWOOD B 1H | 9 | 2021-09-24 20:15 | 2021-09-25 00:30 | 4.25 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.85 | 11376 | 11889 | 120.7 | BUILD CURVE-ROTATE (513' IN 4.17 HRS @ 123.02 FPH) WOB-15/20K, SPM-67/67, GPM-351, RPM-30, MRPM-312.39, TRPM-342.39, SPP-4600-5025 PSI, DIFF-775 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0
REDWOOD B 1H | 9 | 2021-09-25 00:30 | 2021-09-25 00:30 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 7.85 | 11889 | 11889 |  | MILESTONE_LAND/END CURVE SECTION ON 9/25/2021 @ 00:30 (11,889' MD / 11,216' TVD)
REDWOOD B 1H | 9 | 2021-09-25 00:30 | 2021-09-25 00:30 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 7.85 | 11889 | 11889 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 9/25/2021 @ 00:30 (11,889' MD / 11,216' TVD)
REDWOOD B 1H | 9 | 2021-09-25 00:30 | 2021-09-25 05:30 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.06 | 11889 | 12643 | 150.8 | DRILL LATERAL-ROTATE (754' IN 4.92 HRS @ 153.25 FPH) WOB-15/20K, SPM-70/70, GPM-365, RPM-80, MRPM-324.85, TRPM-404.85, SPP-4600-5300 PSI, DIFF-900/1,030 PSI, CHOKES- 0-100% / 41-100%, FLARE-7'-17', NO MUD CUT, MAX CASING PRESSURE: 482 PSI, AVG CASING: 90-233 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 349 MW:10.3 NOTE: PUMPING 10BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300'
REDWOOD B 1H | 9 | 2021-09-25 05:30 | 2021-09-25 06:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.08 | 12643 | 12675 | 64 | DRILL LATERAL-SLIDE (32' IN 0.58 HR @ 55.17 FPH) WOB-30/35K, SPM-70/70, GPM-365, MRPM-324.85, SPP-4625-4770 PSI, DIFF-550/700 PSI, CHOKES-0-100% / 41-100%, FLARE-7-17', NO MUD CUT, MAX CASING PRESSURE= 482 PSI, AVG CASING PRESSURE= 90-233 PSI. MAX SICP: 349 SLIDE DEPTHS: F/11,995'-T/12,007', 12', TF:180, 01:29-01:45 F/12,380'-T/12,400', 20', TF:70R, 03:57-04:16
REDWOOD B 1H | 10 | 2021-09-25 06:00 | 2021-09-25 15:15 | 9.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.47 | 12675 | 14145 | 158.9 | DRILL LATERAL-ROTATE (1,470' IN 9.28 HRS @ 158.40 FPH) WOB-15/20K, SPM-67/67, GPM-351, RPM-80, MRPM-312.39, TRPM-392.39, SPP-4600-5300 PSI, DIFF-900/1,030 PSI, CHOKES- 0-100% / 41-100%, FLARE-5'-15', NO MUD CUT, MAX CASING PRESSURE: 631 PSI, AVG CASING: 110 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 565 MW:10.4 (BRINGING MW UP F/10.3-10.5PPG) NOTE: PUMPING 10BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300'
REDWOOD B 1H | 10 | 2021-09-25 15:15 | 2021-09-25 17:00 | 1.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.54 | 14145 | 14247 | 58.3 | DRILL LATERAL-SLIDE (102' IN 1.72 HR @ 59.30 FPH) WOB-30/35K, SPM-67/67, GPM-351, MRPM-312.39, SPP-4625-4770 PSI, DIFF-550/700 PSI, CHOKES-0-100% / 41-100%, FLARE-5-15', NO MUD CUT, MAX CASING PRESSURE= 631 PSI, AVG CASING PRESSURE= 110 PSI. MAX SICP: 565 SLIDE DEPTHS: F/12,747'-T/12,762', 15', TF:90R, 06:29-06:43 F/12,936'-T/12,951', 15', TF:130R, 07:53-08:08 F/13,225'-T/13,235', 10', TF:40R, 09:48-10:00 F/13,507'-T/13,519', 12', TF:HS, 11:40-11:53 F/13,600'-T/13,615', 15', TF:180, 12:26-12:42 F/13,694'-T/13,702', 8', TF:180, 13:11-13:19 F/13,880'-T/13,895', 15', TF:150R, 14:24-14:38 F/14,075'-T/14,087', 12', TF:150R, 15:40-15:52
REDWOOD B 1H | 10 | 2021-09-25 17:00 | 2021-09-25 18:00 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.58 | 14247 | 14247 | 0 | SERVICE RIG: LUBE TD, ST-80, DRWKS RIG MANAGER PRESENT
REDWOOD B 1H | 10 | 2021-09-25 18:00 | 2021-09-26 04:00 | 10 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9 | 14247 | 15877 | 163 | DRILL LATERAL-ROTATE (1,630' IN 9.97 HRS @ 163.49 FPH) WOB-15/20K, SPM-67/67, GPM-351, RPM-80, MRPM-312.39, TRPM-392.39, SPP-4600-5300 PSI, DIFF-900/1,030 PSI, CHOKES- 0-100% / 41-100%, FLARE-0-5', NO MUD CUT, MAX CASING PRESSURE: 190 PSI, AVG CASING: 0-78 PSI. SHUTTING IN ON CONNECTIONS. MAX SICP: 240 MW:10.5 NOTE: PUMPING 10BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300'
REDWOOD B 1H | 10 | 2021-09-26 04:00 | 2021-09-26 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.08 | 15877 | 15979 | 51 | DRILL LATERAL-SLIDE (102' IN 2.03 HR @ 50.24 FPH) WOB-30/35K, SPM-67/67, GPM-351, MRPM-312.39, SPP-4625-4770 PSI, DIFF-550/700 PSI, CHOKES-0-100% / 41-100%, FLARE-0-5', NO MUD CUT, MAX CASING PRESSURE= 190 PSI, AVG CASING PRESSURE= 0-78 PSI. MAX SICP: 240 SLIDE DEPTHS: F/14,410'-T/14,430', 20', TF:90R, 18:25-18:48 F/14,915'-T/14,935', 20', TF:70R, 21:50-22:12 F/15,006'-T/15,026', 20', TF:90R, 22:42-23:03 F/15,198'-T/15,210', 12', TF:HS, 00:15-00:31 F/15,295'-T/15,303', 8', TF:180, 01:08-01:18 F/15,387'-T/15,397', 10', TF:160L, 01:52-02:08 F/15,867'-T/15,879', 12', TF:150R, 05:05-05:19
REDWOOD B 1H | 11 | 2021-09-26 06:00 | 2021-09-26 08:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.17 | 15979 | 16053 | 37 | DRILL LATERAL-SLIDE (74' IN 1.9 HR @ 39 FPH) WOB-30/35K, SPM-67/67, GPM-351, MRPM-312.39, SPP-4600-4800 PSI, DIFF-550/700 PSI, CHOKES-0% / 41-55%, FLARE-0-10', NO MUD CUT, MAX CASING PRESSURE= 25 PSI, AVG CASING PRESSURE= 10 PSI. MAX SICP: 125 PSI SLIDE DEPTHS: SLD F/16053' T/16068' 15' TF-130R 06:28-6:49 SLD F/16148' T/16168' 20' TF-90R 07:25-07:47 SLD F/16338' T/16353' 15' TF-30R 09:02-09:29 SLD F/16528' T/16540' 12' TF-180 10:43-11:02 SLD F/16905' T/16917' 12' TF-180 13:42-14:07
REDWOOD B 1H | 11 | 2021-09-26 08:00 | 2021-09-26 16:00 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.5 | 16053 | 17133 | 135 | DRILL LATERAL-ROTATE (1080' IN 8.1 HRS @ 133 FPH) WOB-15/20K, SPM-65/65, GPM-340, RPM-70, MRPM-303, TRPM-373, SPP-4600-4800 PSI, DIFF-800/1,000 PSI, CHOKES- 0% / 41-55%, FLARE-0-10', NO MUD CUT MW:10.5 NOTE: PUMPING 10BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300' NOTE: DIFFERENTIAL PRESSURE DECREASED AND BIT WEIGHT INCREASED SUDDENLY; NO MOTOR STALL AND NO TORQUE INCREASE; ATTEMPT TO FAN BIT BACK TO BOTTOM LIGHTLY, CONTINUED TO STACK WEIGHT
REDWOOD B 1H | 11 | 2021-09-26 16:00 | 2021-09-26 17:30 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.56 | 17133 | 17133 | 0 | PUMP 30 BBL HIGH VISC SWEEP SURFACE TO SURFACE; SPP-4400 PSI, GPM-350, TRQ-9K, RPM-80
REDWOOD B 1H | 11 | 2021-09-26 17:30 | 2021-09-26 18:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.58 | 17133 | 17133 | 0 | SERVICE ST-80; CHANGE DIE BLOCK
REDWOOD B 1H | 11 | 2021-09-26 18:00 | 2021-09-26 21:30 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.73 | 17133 | 17133 | 0 | STRIP OUT OF THE HOLE W/BHA #3 F/17,133'-T/10,950'. PUMPING CAL FILL DOWN THE BACKSIDE. MAX CSG PSI SEEN WHILE PERFORMING STRIPPING OPS =519. NO EXCESSIVE DRAG.
REDWOOD B 1H | 11 | 2021-09-26 21:30 | 2021-09-26 22:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.77 | 17133 | 17133 | 0 | CIRC B/U @ 10,950'. GPM:335, SPP: 3,529, RPM:0, TQ:0, CSG PSI WHILE CIRC: 71-154PSI, GAS:948u. MW IN:10.5 MW OUT:10.5 NOTE: FLOW CHECK POST B/U TO MONITOR SICP. MAX SICP: 394PSI
REDWOOD B 1H | 11 | 2021-09-26 22:30 | 2021-09-27 00:15 | 1.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.84 | 17133 | 17133 | 0 | MONITOR CSG PSI. CSG PSI ROSE T/650 PSI. PUMP AND SPOT 111.1 BBL 17# OBM "BALANCED" MUD CAP @ 10,950'. TOP OF MUD CAP-8,530'. NOTE: SICP BUILD RATE SLOWED DOWN BUT WAS STILL BUILDING APPROXIMATELY 83 PSI PER 10 MIN; CALCULATIONS FOR MUD CAP VOLUME WERE BASED OFF OF 650 PSI SICP AND 300 PSI SAFETY FACTOR FOR A TOTAL OF 950 PSI MW:10.5 KMW:17.0 NOTE: AFTER PUMPING 111.1BBLS OF KILL MUD, CHASED WITH 108.3BBLS OF ACTIVE MUD TO SPOT. ONCE MUD CAP WAS PUMPED AND IN PLACE, A FLOW CHECK WAS CONDUCTED. RESULT: NO FLOW.
REDWOOD B 1H | 11 | 2021-09-27 00:15 | 2021-09-27 03:30 | 3.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.98 | 17133 | 17133 | 0 | POOH W/BHA #3 F/10,950'-T/2,972'. HOLE TAKING PROPER FILL VIA TRIP TANK. NO EXCESSIVE DRAG. NOTE: @ 8,267' FLOW CHECK WAS CONDUCTED. RESULT: NO FLOW. PUMPED 30BBLS OF 17# OBM FOR SLUG
REDWOOD B 1H | 11 | 2021-09-27 03:30 | 2021-09-27 04:15 | 0.75 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.01 | 17133 | 17133 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. NOTE: FLOW CHECK WAS CONDUCTED PRIOR TO REMOVING RT-HEAD, RESULT: NO FLOW
REDWOOD B 1H | 11 | 2021-09-27 04:15 | 2021-09-27 06:00 | 1.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.08 | 17133 | 17133 | 0 | POOH W/BHA #3 F/2,972'-T/144'. HOLE TAKING PROPER FILL VIA TRIP TANK. NO EXCESSIVE DRAG. NOTE: L/D AGITATOR @ 2,816'.
REDWOOD B 1H | 12 | 2021-09-27 06:00 | 2021-09-27 07:15 | 1.25 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.14 | 17133 | 17133 | 0 | L/D X/O, TOMAX THRUSTER AND TOP NMDC. PULL MWD, DRAIN MOTOR, BREAK BIT AND L/D REMAINING BHA. BIT GRADE: 0-1-CT-A-X-0-NO-PR NOTE: MOTOR BEARING GAP HAD 1/8" SQUAT, MOTOR DID NOT DRAIN.
REDWOOD B 1H | 12 | 2021-09-27 07:15 | 2021-09-27 08:00 | 0.75 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 10.17 | 17133 | 17133 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13601237 JETS 6/18S TFA: 1.491), 5.5", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 3.56' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, FILTER SUB, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-66'. BIT TO GAMMA-53'. NOTE: FIRST ATTEMPT TO TEST MWD: FAILED. (TESTED MWD WITH GPM:183)
REDWOOD B 1H | 12 | 2021-09-27 08:00 | 2021-09-27 10:15 | 2.25 | U | PRDHLLT | LOG | MWD | MWD | 10.26 | 17133 | 17133 | 0 | WAIT ON MWD TO REBUILD AND REPROGRAM TOOL. INSTALL TOOL AND TEST: GOOD. (TESTED MWD WITH GPM: 183)
REDWOOD B 1H | 12 | 2021-09-27 10:15 | 2021-09-27 11:30 | 1.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.31 | 17133 | 17133 | 0 | TIH W/BHA #4 F/BHA-T/2,794. FILLING PIPE EVERY 30 STDS. HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK. P/U AGITATOR, BEFORE PSI-1405 / AFTER PSI-1825, GPM-262
REDWOOD B 1H | 12 | 2021-09-27 11:30 | 2021-09-27 12:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.33 | 17133 | 17133 | 0 | FLOW CHECK, WELL STATIC. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD.
REDWOOD B 1H | 12 | 2021-09-27 12:00 | 2021-09-27 12:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.35 | 17133 | 17133 | 0 | TRIP IN THE HOLE F/2,794' T/4,517'. HOLE GIVING PROPER DISPLACEMENT VIA TRIP TANK
REDWOOD B 1H | 12 | 2021-09-27 12:30 | 2021-09-27 14:30 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.44 | 17133 | 17133 | 0 | HOLE STARTED OVER DISPLACING @ 4,517'; FLOW CHECK WELL; WELL FLOWING; STRIP IN HOLE F/4,517' T/8,387' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS/STD
REDWOOD B 1H | 12 | 2021-09-27 14:30 | 2021-09-27 15:30 | 1 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.48 | 17133 | 17133 | 0 | LUBRICATE DRAW WORKS, ST-80, AND TOP DRIVE
REDWOOD B 1H | 12 | 2021-09-27 15:30 | 2021-09-27 17:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.54 | 17133 | 17133 | 0 | STRIP IN HOLE F/8,387' T/11,037' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS/STD
REDWOOD B 1H | 12 | 2021-09-27 17:00 | 2021-09-27 19:00 | 2 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.63 | 17133 | 17133 | 0 | CIRULATE OUT MUD CAP; STAGE PUMPS UP FROM 10 SPM TO 70 SPM; FINAL CIRCULATING GPM-183, SPP-2600, MAX CASING PSI-1200, FLARE 10'; CAPTURED APPROXIMATELY 100 BBLS OF MUD CAP IN TRIP TANK; MAX MUD WT. 16.5 PPG.
REDWOOD B 1H | 12 | 2021-09-27 19:00 | 2021-09-27 20:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.69 | 17133 | 17133 | 0 | STRIP IN THE HOLE F/11,037'-T/14,930' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 297, FINAL CSG PSI 1,060. FILL AND BREAK CIRCULATION EVERY 30 STDS.
REDWOOD B 1H | 12 | 2021-09-27 20:30 | 2021-09-27 21:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.73 | 17133 | 17133 | 0 | @ 14,930', CIRULATE DUE TO HIGH CSG PRESSURE WHILE PERFORMING STRIPPING OPS. GPM:350, SPP:4,900-5,318, MAX CASING PSI-1,497, FLARE: 40'. MW IN:10.5 HIGHEST MW OUT SEEN WHILE CIRC:12.8PPG SICP PRIOR TO CIRC: 984 SICP POST CIRC: 41 MAX GAS: 2,049 NOTE: TOP PIPE RAMS CLOSED WHILE PERFORMING CIRCULATING OPS.
REDWOOD B 1H | 12 | 2021-09-27 21:30 | 2021-09-27 22:15 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 10.76 | 17133 | 17133 | 0 | STRIP IN THE HOLE F/14,930'-T/16,890' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 41, FINAL CSG PSI: 0. FILL AND BREAK CIRCULATION EVERY 30 STDS.
REDWOOD B 1H | 12 | 2021-09-27 22:15 | 2021-09-27 22:45 | 0.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 10.78 | 17133 | 17133 | 0 | WASHED & REAMED F/16,890'-T/17,133' WOB: 0/5K, RPM: 50, TRQ:10/11K, SPM:68/68, GPM:356, MRPM:242, TRPM: 292.08, SPP: 4,717, CP:100-144 PSI, FLARE:2/5', CHOKE POSITION-0%/42%
REDWOOD B 1H | 12 | 2021-09-27 22:45 | 2021-09-28 04:30 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.02 | 17133 | 18000 | 150.8 | DRILL LATERAL-ROTATE (867' IN 5.85 HRS @ 148.20 FPH) WOB:15/20K, SPM:70/70, GPM:367, RPM: 80, MRPM: 249.56, TRPM:329.56. SPP:5,026-5,950 PSI, DIFF:800/1,000 PSI, CHOKES: 0% / 40-100%, FLARE: 0-3', MAX CASING PRESSURE= 180 PSI, AVG CASING PRESSURE= 10 PSI. MAX SICP: 388 PSI. AVG SICP:180 PSI. NO MUD CUT MW:10.5 NOTE: PUMPING 10BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300'
REDWOOD B 1H | 12 | 2021-09-28 04:30 | 2021-09-28 06:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.08 | 18000 | 18058 | 38.7 | DRILL LATERAL-SLIDE (58' IN 1.40 HR @ 41.42 FPH) WOB: 30/35K, SPM: 70/70, GPM: 367, MRPM:249.56, SPP: 5,111-5,493 PSI, DIFF: 300/460 PSI, CHOKES:0% / 40-100%, FLARE: 0-10', NO MUD CUT, MAX CASING PRESSURE= 180 PSI, AVG CASING PRESSURE= 10 PSI. MAX SICP: 388 PSI, AVG SICP:180 PSI. SLIDE DEPTHS: F/17,560'-T/17,578', 18', TF:120R, 01:27-01:54 F/17,752'-T/17,773', 21', TF:30R, 03:00-03:30 F/17,843'-T/17,862', 19', TF:HS, 04:00-04:27
REDWOOD B 1H | 13 | 2021-09-28 06:00 | 2021-09-28 16:00 | 10 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 11.5 | 18058 | 19196 | 113.8 | DRILL LATERAL-ROTATE (1,138' IN 10.12 HRS @ 112.45 FPH) WOB:15/20K, SPM:67/67, GPM:350, RPM: 80, MRPM: 238, TRPM:318. SPP:5,026-5,950 PSI, DIFF:800/1,000 PSI, CHOKES: 0% / 40-100%, FLARE: 0-3', MAX CASING PRESSURE= 78 PSI, AVG CASING PRESSURE= 10 PSI. MAX SICP: 367 PSI. AVG SICP:180 PSI. NO MUD CUT MW:10.5 NOTE: PUMPING 10BBL, 4 PPB CALCIUM CARBONATE, 4 PPB NEW PHAULT, 4 PPB MAGMAFIBER FINE SWEEP EVERY 300'
REDWOOD B 1H | 13 | 2021-09-28 16:00 | 2021-09-28 23:15 | 7.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.8 | 19196 | 19389 | 26.6 | DRILL LATERAL-SLIDE (193' IN 7.13 HR @ 27.06 FPH) WOB: 30/45K, SPM: 67/67, GPM: 350, MRPM:238, SPP: 5,111-5,493 PSI, DIFF: 300/460 PSI, CHOKES:0% / 40-100%, FLARE: 0-3', NO MUD CUT, MAX CASING PRESSURE= 78 PSI, AVG CASING PRESSURE= 10 PSI. MAX SICP: 367 PSI, AVG SICP:120 PSI. SLIDE DEPTHS: F/18,420' T/18,445', 25', TF-90L 08:34-09:12 F/18,520' T/18,530', 10', TF-90L 09:55-10:20 F/18,700' T/18,720', 20', TF-90R 11:49-12:32 F/18,795' T/18,810', 15', TF-60R 13:13-13:45 F/18,984' T/19,004', 20', TF-90L 15:16-15:59 F/19,020' T/19,035', 15', TF-90L 16:10-16:49 F/19,067' T/19,093', 26', TF-90L 17:11-18:10 F/19,113'-T/19,135', 22', TF:90L, 18:20-19:08 F/19,164'-T/19,188', 24', TF:90L, 19:38-20:32 F/19,307'-T/19,323', 16', TF:120L, 21:45-22:32
REDWOOD B 1H | 13 | 2021-09-28 23:15 | 2021-09-29 02:45 | 3.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.95 | 19389 | 19389 | 0 | PERFORM CLEAN UP CYCLE FOR CASING RUN: PUMP 3 TANDEM 30 BBL HIGH VIS SWEEPS. CIRCULATE HOLE CLEAN, RPM-80, SPM: 67/67, GPM-350, INITIAL SPP-4,770 PSI. CHOKES- 0% /100%, FLARE-0'-2', MAX CASING PRESSURE= 0 PSI, MAX GAS: 729u. MW:11.0 1ST BTM UP START TQ=11.6K, P/U WT:257K, S/O:188K 2ND B/U: TQ=11K, P/U WT:257K,S/O:188K 3RD B/U: TQ=11K, P/U WT:257K, S/O:188K
REDWOOD B 1H | 13 | 2021-09-28 23:15 | 2021-09-28 23:15 | 0 | P | PRDHLCSG | MSTN | TD | MILESTONE_TD WELL | 11.8 | 19389 | 19389 |  | MILESTONE_TD WELL ON 9/28/2021 @ 23:15
REDWOOD B 1H | 13 | 2021-09-29 02:45 | 2021-09-29 05:00 | 2.25 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 12.04 | 19389 | 19389 | 0 | ATTEMPT TO TRIP OUT THE HOLE ON ELEVATORS WITH NO SUCCESS, MAX OVER PULL-30K, BACK REAM OUT OF HOLE F/19,389' T/17,460', SPM: 60/60, GPM-314, RPM-80, TRQ-11K/18K, SPP-3400 PSI, CHOKES- 0% / 0-63%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 110 PSI, AVG CASING PRESSURE= 10 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP=676 PSI, AVG SICP= 220 PSI.
REDWOOD B 1H | 13 | 2021-09-29 05:00 | 2021-09-29 06:00 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.08 | 19389 | 19389 | 0 | STRIP OUT OF THE HOLE W/BHA #4 F/17,460'-T/15,800'. PUMPING CAL FILL DOWN THE BACKSIDE. MAX CSG PSI SEEN WHILE PERFORMING STRIPPING OPS: 527. NO EXCESSIVE DRAG.
REDWOOD B 1H | 14 | 2021-09-29 06:00 | 2021-09-29 08:45 | 2.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.2 | 19389 | 19389 | 0 | STRIP OUT OF THE HOLE W/BHA #4 F/15,800' T/10,930'. PUMPING CALC FILL DOWN THE BACKSIDE. MAX CSG PSI: 564 PSI. NO EXCESSIVE DRAG.
REDWOOD B 1H | 14 | 2021-09-29 08:45 | 2021-09-29 09:45 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.24 | 19389 | 19389 | 0 | CIRC B/U @ SHOE. GPM:400, SPP: 4,320, RPM:20, TQ:3-6K, CSG PSI WHILE CIRC: 589 PSI, GAS: 608u. MW IN:11.1 MW OUT:11.1 NOTE: FLOW CHECK POST B/U TO MONITOR SICP. MAX SICP: 290 PSI
REDWOOD B 1H | 14 | 2021-09-29 09:45 | 2021-09-29 10:45 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.28 | 19389 | 19389 | 0 | PUMP AND SPOT 90 BBL 17# OBM "BALANCED" MUD CAP @ 10,930'. TOP OF MUD CAP-8,857'. CALCULATIONS FOR MUD CAP VOLUME WERE BASED OFF OF 300 PSI SICP AND 300 PSI SAFETY FACTOR FOR A TOTAL OF 600 PSI MW:11.1 KMW:17.0 NOTE: AFTER PUMPING 90 BBLS OF KILL MUD, CHASED WITH 120 BBLS OF ACTIVE MUD TO SPOT. ONCE MUD CAP WAS PUMPED AND IN PLACE, A FLOW CHECK WAS CONDUCTED. RESULT: NO FLOW.
REDWOOD B 1H | 14 | 2021-09-29 10:45 | 2021-09-29 14:45 | 4 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.45 | 19389 | 19389 | 0 | TOH W/BHA #4 F/10,930'-T/3,261'. HOLE TAKING PROPER FILL VIA TRIP TANK. NO EXCESSIVE DRAG. NOTE: @ 8,733' FLOW CHECK WAS CONDUCTED. RESULT: NO FLOW. PUMPED 30 BBLS OF 17# OBM FOR SLUG.
REDWOOD B 1H | 14 | 2021-09-29 14:45 | 2021-09-29 15:15 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 12.47 | 19389 | 19389 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. NOTE: FLOW CHECK WAS CONDUCTED PRIOR TO REMOVING RT-HEAD: RESULT: NO FLOW
REDWOOD B 1H | 14 | 2021-09-29 15:15 | 2021-09-29 16:45 | 1.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 12.53 | 19389 | 19389 | 0 | TOH W/BHA #4 F/3,261'-T/BHA. HOLE TAKING PROPER FILL VIA TRIP TANK. NO EXCESSIVE DRAG. NOTE: L/D AGITATOR @ 2,816'.
REDWOOD B 1H | 14 | 2021-09-29 16:45 | 2021-09-29 17:30 | 0.75 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 12.56 | 19389 | 19389 | 0 | L/D DIR BHA: X/O, TOMAX THRUSTER, FILTER SUB AND TOP NMDC. PULL MWD, DRAIN MOTOR, BREAK BIT AND L/D REMAINING BHA. NOTE: MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG. BIT GRADED: 0-1-NO-A-X-NO-TD.
REDWOOD B 1H | 14 | 2021-09-29 17:30 | 2021-09-29 18:15 | 0.75 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.59 | 19389 | 19389 | 0 | SERVICE TOP DRIVE AND DRAWORKS
REDWOOD B 1H | 14 | 2021-09-29 18:15 | 2021-09-29 18:45 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 12.61 | 19389 | 19389 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4 1/2" ELEVATORS AND PREP FOR CSG OPS.
REDWOOD B 1H | 14 | 2021-09-29 18:45 | 2021-09-29 20:00 | 1.25 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 12.67 | 19389 | 19389 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT.
REDWOOD B 1H | 14 | 2021-09-29 20:00 | 2021-09-29 22:30 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.77 | 19389 | 19389 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 2 JT 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/2,440', FILLING PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 14 | 2021-09-29 22:30 | 2021-09-29 23:00 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 12.79 | 19389 | 19389 | 0 | FLOW CHECK, WELL STATIC, REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
REDWOOD B 1H | 14 | 2021-09-29 23:00 | 2021-09-29 23:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.81 | 19389 | 19389 | 0 | RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/2,440' T/3,064', FILLING PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 14 | 2021-09-29 23:30 | 2021-09-30 | 0.5 | U | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.83 | 19389 | 19389 | 0 | TROUBLESHOOT INCONSISTENT TORQUE TURN GRAPHS, FOUND IMPROPERLY CLEANED CONNECTIONS CAUSING ERRACTIC TORQUE, CHANGE DOPING PRACTICES TO CORRECT THE ISSUE.
REDWOOD B 1H | 14 | 2021-09-30 | 2021-09-30 02:15 | 2.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 12.93 | 19389 | 19389 | 0 | RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/3,064' T/6,027', FILLING PIPE ON THE FLY, HOLE NOT GIVING PROPER DISPLACEMENT (DECISION MADE TO STRIP IN HOLE).
REDWOOD B 1H | 14 | 2021-09-30 02:15 | 2021-09-30 04:15 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.01 | 19389 | 19389 | 0 | STRIP IN THE HOLE WITH 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/6,027' T/8,855', FILLING PIPE ON THE FLY, MAX CSG PSI: 398 PSI, BLEED OFF PROPER DISPLACEMENT TO TRIP TANK (HOLE NOT GIVING ENOUGH DISPLACEMENT ONCE AT MUD CAP).
REDWOOD B 1H | 14 | 2021-09-30 04:15 | 2021-09-30 04:30 | 0.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.02 | 19389 | 19389 | 0 | RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/8,855' T/9,295', FILLING PIPE ON THE FLY. NOTE: TAKE RETURNS DOWN FLOWLINE AND REDUCE RUNNING SPEED WHILE IN MUD CAP DUE TO REDUCED RETURNS.
REDWOOD B 1H | 14 | 2021-09-30 04:30 | 2021-09-30 05:00 | 0.5 | U | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.04 | 19389 | 19389 | 0 | WHILE RIGGING DOWN 5" CRT NOTICED BROKEN BOLT ON TOP DRIVE GRABBER DIE BLOCK, INSPECT DIE BLOCK AND REPLACE BOLT.
REDWOOD B 1H | 14 | 2021-09-30 05:00 | 2021-09-30 06:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 13.08 | 19389 | 19389 | 0 | FLOW CHECK, WELL STATIC, RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5 1/2" CRT AND ELEVATORS.
REDWOOD B 1H | 15 | 2021-09-30 06:00 | 2021-09-30 07:30 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.15 | 19389 | 19389 | 0 | PICK UP AND RUN 5 ½” PRODUCTION CSG F/9,292’ T/11,090’, FILLING PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT.
REDWOOD B 1H | 15 | 2021-09-30 07:30 | 2021-09-30 08:45 | 1.25 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.2 | 19389 | 19389 | 0 | CIRCULATE OUT MUD CAP @ 11,090', SLOWLY STAGE PUMPS UP: 100 SPM, 262 GPM, , SPP: 1020 PSI, CHOKES- 100% / 100%, AVG CASING PRESSURE= 0 PSI, MAX CASING PRESSURE= 0 PSI, FLARE- 0’ AND MAX GAS: 32u.. FINAL SICP= 300 PSI. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 11.7 PPG WAS @ SURFACE, DIVERTED 144 BBLS OF 11.7 PPG T/14.8 PPG. FINAL CIRCULATING MW IN:11.1 MW OUT:11.1
REDWOOD B 1H | 15 | 2021-09-30 08:45 | 2021-09-30 15:00 | 6.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.46 | 19389 | 19389 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/11,090' T/19,350' WHILE STRIPPING IN WITH AVG CASING PRESSURE= 500 PSI WITH CHOKES: 30% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.38 BBLS/JT), MAX CSG PRESSURE=1082 PSI, FILLING PIPE ON THE FLY.
REDWOOD B 1H | 15 | 2021-09-30 15:00 | 2021-09-30 16:15 | 1.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 13.51 | 19389 | 19389 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND RUN LANDING JOINT F/19,350' T/19,380.9'. GPM-105, LAND CASING ON HANGER W/132K LBS (W/O BLOCKS) @ 19,380.9'. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, RAN 9,262.93' (208 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1- X-OVER, 1 JOINT 5-1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, RAN 10,035.72' (214 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING. FOR TOTAL OF 422 FULL JTS OF 5'' 18# P-110 ICY WEDGE 425 & 5.5" 23# P-110 ICY WEDGE 463. CASING SHOE @ 19,380.9' TOP OF FLOAT COLLAR @ 19,329.1' BOTTOM OF TOE SLEEVE VALVE @ 19,282.2' TOP OF TOE SLEEVE VALVE @ 19,257.1' TOP OF X-OVER @ 10,085.5' TOP OF MARKER JOINT ABOVE X-OVER @ 10,018.4' 7 JOINTS 5" LEFT OUT- 310.05' 9 JOINTS 5.5" LEFT OUT- 424.9'
REDWOOD B 1H | 15 | 2021-09-30 16:15 | 2021-09-30 17:30 | 1.25 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 13.56 | 19389 | 19389 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV, CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 603 PSI.
REDWOOD B 1H | 15 | 2021-09-30 17:30 | 2021-09-30 19:15 | 1.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.64 | 19389 | 19389 | 0 | SLOWLY STAGE UP PUMPS TO 262 GPM, CIRCULATE 1-1/2 CASING CAPACITY WHILE RIGGING DOWN CASING TOOLS, GPM-262, SPP-1835 PSI, CHOKES: 0% / 40-100%, AVG CASING PRESSURE= 100 PSI, MAX CASING PRESSURE= 731 PSI, 5’-10’ FLARE AND MAX GAS: 1662u. MONITOR SICP, SICP= 140 PSI. NOTE: HELD PJSM FOR CEMENT JOB.
REDWOOD B 1H | 15 | 2021-09-30 19:15 | 2021-09-30 22:45 | 3.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 13.78 | 19389 | 19389 | 0 | SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT TRUCK, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI, CEMENTED 5X5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 6 BPM 80 BBL 11.8 PPG WEIGHTED SPACER, 285 BBL 13.5 PPG TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBL OF SUGAR WATER, FOLLOWED BY 358 BBL OF FRESH WATER @ 6 BPM (TOTAL OF 378 BBL DISPLACEMENT). OBSERVED 100% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 4,150 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 5,100 PSI. 0 BBLS OF SPACER BACK TO SURFACE. HELD FOR 5 MIN, BLED BACK 6.5 BBLS. FLOATS HELD. PLUG DOWN @ 22:31 HRS 9/30/2021. INITIAL SICP-140 PSI, FINAL SICP= 0 PSI. MAX CASING PSI W/ PUMPING CEMENT-596 PSI @ 5 BPM MAX CASING PSI W/ PUMPING DISPLACEMENT- 1,080 PSI, MAX GAS-685u CALCULATED TOP OF CEMENT- 4,838' NOTE: GOOD RETURNS THROUGHOUT JOB. TOP PIPE RAMS CLOSED DURING THE CMT JOB AS A PRECAUTIONARY MEASURE. TAKING RETURNS THROUGH CHOKE MANIFOLD. CHOKE POSITION= 0%/35-100%.
REDWOOD B 1H | 15 | 2021-09-30 22:45 | 2021-09-30 23:30 | 0.75 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 13.81 | 19389 | 19389 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP=0 PSI, FINAL SICP= 0 PSI. NOTE: LEFT FOSV OPEN WHILE MONITORING SICP.
REDWOOD B 1H | 15 | 2021-09-30 23:30 | 2021-10-01 02:45 | 3.25 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 13.95 | 19389 | 19389 | 0 | REMOVE FOSV AND ROTATING HEAD, LAY DOWN LANDING JOINT, RIG DOWN CSG ELEVATORS AND RIG UP RIG ELEVATORS, WASH THROUGH BOP'S AND CHOKE MANIFOLD, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 50 GPM W/750 PSI TO CLEAN THE TOP OF HANGER, REMOVE WASH OUT TOOL AND PICK UP PACKOFF. INSTALL AND TEST STREAM-FLO PACK-OFF, PULL TEST PACK-OFF TO 25K AND TEST PACK-OFF T/10,000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. PICK UP 1" TUBING AND INSTALL BPV. LAY DOWN TUBING.
REDWOOD B 1H | 15 | 2021-10-01 02:45 | 2021-10-01 06:00 | 3.25 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 14.08 | 19389 | 19389 | 0 | REMOVE FLOW LINE FROM SCISSOR, INSTALL WRANGLER ONTO BOP, REMOVE HCR LINE, KILL LINE, KILL LINE CHECK VALVE, HYDRAULIC LINES, HOLE FILL, AIR LINES/HYDRAULIC LINES FROM ROTATING HEAD, REMOVE TURNBUCKLES, BACK OUT WH SET SCREWS AND RAISE BOP'S, INSTALL WELLHEAD CAP AND TESTED T/5,000 PSI. SECURE WELL. NOTE: START CLEANING MUD TANKS @ 00:00.
REDWOOD B 1H | 16 | 2021-10-01 06:00 | 2021-10-01 07:00 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 14.13 | 19389 | 19389 | 0 | SECURE BOP’S AND CLEAN MUD TANKS, REMOVE ELEVATORS AND BALES, PIN TOP DRIVE, PIN TOP DRIVE TO TRACK.
REDWOOD B 1H | 15 | 2021-10-01 06:00 | 2021-10-01 06:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 14.08 | 19389 | 19389 |  | MILESTONE_WELL RELEASE 10/1/2021 @ 06:00.
REDWOOD B 1H | 16 | 2021-10-01 07:00 | 2021-10-01 08:45 | 1.75 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 14.2 | 19389 | 19389 | 0 | UNSPOOL DRAWWORKS, CUT 6 WRAPS OF DRILL LINE.
REDWOOD B 1H | 16 | 2021-10-01 08:45 | 2021-10-02 06:00 | 21.25 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 15.08 | 19389 | 19389 | 0 | INSTALL MOUSE HOLE, L/D 4 1/2" DRILL PIPE FROM THE DERRICK OUT OF THE MOUSE HOLE WITH HOIST (TIGHT CONNECTIONS REQUIRING ST-80 DIES TO BE CHANGED OFTEN), 131 STDS LAID DOWN, 84 STDS LEFT TO LAY DOWN, FINISH CLEANING MUD TANKS, WASH RIG, RIG DOWN BACK YARD.
REDWOOD B 1H | 17 | 2021-10-02 06:00 | 2021-10-02 22:00 | 16 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 15.75 | 19389 | 19389 | 0 | L/D 4 1/2" DRILL PIPE FROM THE DERRICK OUT OF THE MOUSE HOLE WITH HOIST (TIGHT CONNECTIONS REQUIRING ST-80 DIES TO BE CHANGED OFTEN), WASH RIG, RIG DOWN AND SEPERATE BACK YARD, RIG DOWN AND MOVE TCB CAMPS, PERFORM CAR WASH ON ALL EQUIPMENT LEAVING LOCATION, RIG DOWN, LOAD OUT, MOVE AND SET IN RIG ON THE BIGHORN PLAINS H 02 LOCATION. ON NEW LOCATION: SET MUD TANKS, MUD PUMPS, RIG WATER TANKS.
REDWOOD B 1H | 17 | 2021-10-02 22:00 | 2021-10-03 01:30 | 3.5 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 15.9 | 19389 | 19389 | 0 | CLEAN AND ORGANIZE RIG FLOOR, REMOVE ALL 4 ½” DRILL PIPE EQUIPMENT FROM RIG FLOOR, LAY DOWN MOUSEHOLE, RIG DOWN RIG FLOOR, EXTEND AND PIN MSRC'S TO SUB AND LOWER @ 01:30.
REDWOOD B 1H | 17 | 2021-10-03 01:30 | 2021-10-03 02:30 | 1 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 15.94 | 19389 | 19389 | 0 | SWAP MSRC'S FROM SUBS AND PIN TO MAST.
REDWOOD B 1H | 17 | 2021-10-03 02:30 | 2021-10-03 06:00 | 3.5 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 16.08 | 19389 | 19389 | 0 | SWAP FROM RIG POWER TO GENERATOR, RIG DOWN ALL ELECRICAL LINES, RIG DOWN AND PREP MOTOR PACKAGE, VFD, FESTOON, TRIP TANKS, FLOWLINE, AND SUITCASES FOR TRANSPORT.
REDWOOD B 1H | 18 | 2021-10-03 06:00 | 2021-10-03 18:00 | 12 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 16.58 | 19389 | 19389 | 0 | RIG DOWN, WASH, LOAD OUT, MOVE AND SET IN RIG ON THE BIG HORN PLAINS H 02, REMOVE CATWALK AND BOP'S, LOWER DERRICK @ 08:30, UNDRESS DERRICK, REMOVE MONKEY BOARD, UNSPOOL DERRICK, SPLIT BLOCKS AND PIN IN CROWN SECTION, REMOVE CROWN, TOP AND MIDDLE SECTIONS OF DERRICK. PERFORM CAR WASH ON ALL EQUIPMENT LEAVING LOCATION. REMOVE DS DOGHOUSE, DRAWWORKS, ODS DOG HOUSE AND A-LEG SECTION, RIG DOWN PATTERSON CAMP HOUSES, LOAD OUT AND MOVE HOUSES, CHANGE OUT ROTATING HEAD BOWL AND ORBIT VALVE, SET SUITCASES, VFD HOUSES, MOTOR PACKAGE, WATER TANKS AND PARTS HOUSES ON NEW LOCATION, PERFORM 180 DAY INSPECTION ON MUD PUMPS, RIG UP GAS SEPERATOR AND FLARE LINE, RIG UP NOV SOLIDS CONTROL EQUIPMENT.
REDWOOD B 1H | 18 | 2021-10-03 18:00 | 2021-10-03 18:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 16.58 | 19389 | 19389 |  | MILESTONE_TURN OVER TO COMPLETION 10/3/2021 @ 18:00
REDWOOD B 1H | 18 | 2021-10-03 18:00 | 2021-10-03 18:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 16.58 | 19389 | 19389 |  | MILESTONE_RIG RELEASE 10/3/2021 @ 18:00
ROMMEL UNIT 3H | 1 | 2021-07-14 08:30 | 2021-07-14 11:15 | 2.75 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/ROMMEL 4H T/ROMMEL 3H; SET MATS, WALK RIG TO ROMMEL 3H; CENTER AND LEVELED SUB OVER CONDUCTOR.
ROMMEL UNIT 3H | 1 | 2021-07-14 08:30 | 2021-07-14 08:30 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 07/14/2021 @ 08:30
ROMMEL UNIT 3H | 1 | 2021-07-14 11:15 | 2021-07-14 11:30 | 0.25 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | L/D LANDING JT., REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
ROMMEL UNIT 3H | 1 | 2021-07-14 11:30 | 2021-07-14 12:00 | 0.5 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
ROMMEL UNIT 3H | 1 | 2021-07-14 12:00 | 2021-07-14 13:00 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA AND MAKE UP BIT, REMOVE X-OVER AND PUP JOINT, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 6/16 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, TAG BOTTOM @ 108'.
ROMMEL UNIT 3H | 1 | 2021-07-14 13:00 | 2021-07-14 13:00 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 7/14/2021 @ 13:00
ROMMEL UNIT 3H | 1 | 2021-07-14 13:00 | 2021-07-14 13:45 | 0.75 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.03 | 108 | 303 | 260 | ROTATE DRILL F/108' T/303' (195' IN .75 HRS @ 260 FPH) WOB-5-10K, RPM-60, TRQ- 12/18K, SPM-70/70/70, GPM-675, MMRPM-112, TRPM-75, SPP-700/900 PSI, DIFF-100/200 PSI.
ROMMEL UNIT 3H | 1 | 2021-07-14 13:45 | 2021-07-14 14:15 | 0.5 | U | SFHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 0.05 | 303 | 303 | 0 | OBSERVE ERRACTIC TORQUE, CIRCULATE @ 606 GPM, SPP- 700 PSI WHILE INSPECTING 42 PIN ON DRILLER SIDE TOP DRIVE, OBSERVED 1 PIN PUSHED IN, REPAIRED AND CLEAN 42 PIN.
ROMMEL UNIT 3H | 1 | 2021-07-14 14:15 | 2021-07-14 16:00 | 1.75 | P | SFHL | DRLG | CTLDRL | CONTROL DRILLING | 0.13 | 303 | 1040 | 421.1 | CONTROL DRILL ON #1 AND #2 PUMP WHILE CHANGING OUT ALL SWABS ON #3 PUMP FROM PREMIUM SWABS TO SOUTH WEST SWABS, ROTATE DRILL F/303' T/1040' (737' IN 1.75 HRS @ 421.1 FPH) WOB-20-30K, RPM-100, TRQ- 3/6K, SPM-113/113, GPM-720, MMRPM-120, TRPM-220, SPP-1000/1500 PSI, DIFF-300/500 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'.
ROMMEL UNIT 3H | 1 | 2021-07-14 16:00 | 2021-07-14 20:00 | 4 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.29 | 1040 | 2217 | 294.2 | ROTATE (963’ IN 1.52 HRS @ 633.6 FPH) WOB-25-35K, RPM-100, TRQ- 3/10.5K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,750/2,7000 PSI, DIFF-350/400 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM.
ROMMEL UNIT 3H | 1 | 2021-07-14 20:00 | 2021-07-14 20:30 | 0.5 | U | SFHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 0.31 | 2217 | 2217 | 0 | OBSERVE ERRACTIC TORQUE, INSPECT 42 PIN ON DRILLER SIDE TOP DRIVE, OBSERVED 1 PIN PUSHED IN, REPAIRED AND CLEAN 42 PIN.
ROMMEL UNIT 3H | 1 | 2021-07-14 20:30 | 2021-07-14 23:00 | 2.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.42 | 2217 | 3153 | 374.4 | ROTATE (1,141’ IN 2.28 HRS @ 500.4 FPH) WOB-25-35K, RPM-100, TRQ- 3/10.5K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1,750/2,7000 PSI, DIFF-350/400 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/SOAP/SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 50 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHED 900 GPM AND 100 RPM.
ROMMEL UNIT 3H | 1 | 2021-07-14 23:00 | 2021-07-15 01:30 | 2.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.52 | 3153 | 3523 | 148 | SLIDE (370' IN 2.32 HRS @ 159.7 FPH) WOB-5/18K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2,100/2,700 PSI, DIFF-350/400 PSI. SLIDE INFO: Start End Start End CL TTF 16:16 16:20 1,143 1,158 15 110 16:31 16:36 1,238 1,253 15 110 16:48 16:53 1,331 1,351 20 110 17:04 17:09 1,426 1,446 20 110 17:20 17:24 1,519 1,534 15 0 17:36 17:41 1,614 1,629 15 0 17:53 17:59 1,707 1,722 15 0 18:16 18:21 1,801 1,821 20 0 18:34 18:40 1,894 1,909 15 -20 18:52 18:58 1,989 2,004 15 0 19:13 19:20 2,084 2,104 20 -20 19:37 19:44 2,178 2,198 20 0 20:52 20:59 2,272 2,287 15 0 21:13 21:19 2,365 2,380 15 70 22:32 22:40 2,835 2,855 20 60 22:58 23:06 2,929 2,949 20 60 23:21 23:30 3,024 3,044 20 60 23:43 23:51 3,118 3,138 20 60 00:05 00:15 3,211 3,226 15 0 00:30 00:39 3,305 3,325 20 60 00:54 01:03 3,398 3,418 20 60
ROMMEL UNIT 3H | 1 | 2021-07-15 01:30 | 2021-07-15 02:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.56 | 3523 | 3523 | 0 | PUMP 2-30 BBL GEL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,300 PSI.
ROMMEL UNIT 3H | 1 | 2021-07-15 02:30 | 2021-07-15 03:45 | 1.25 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.61 | 3523 | 3523 | 0 | TRIP OUT OF HOLE F/3,501' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
ROMMEL UNIT 3H | 1 | 2021-07-15 03:45 | 2021-07-15 04:30 | 0.75 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.65 | 3523 | 3523 | 0 | RACK BACK 3 STANDS HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-2-CT-G-X-0-NO-TD.
ROMMEL UNIT 3H | 1 | 2021-07-15 04:30 | 2021-07-15 05:15 | 0.75 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.65 | 3523 | 3523 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
ROMMEL UNIT 3H | 1 | 2021-07-15 05:15 | 2021-07-15 06:00 | 0.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.68 | 3523 | 3523 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BTC CASING, TEST FLOATS (TEST GOOD), TIH WITH 10 3/4" 45.5# J-55 BTC CASING T/281'.
ROMMEL UNIT 3H | 2 | 2021-07-15 06:00 | 2021-07-15 09:00 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.8 | 3523 | 3523 | 0 | CONTINUE RUNNING 10 3/4" 45.5# J-55 BTC CASING F/281' T/3,513.5'. RAN 44 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, 1 ON TOP OF JOINT #3 AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, TESTED WELLHEAD T/5,000 PSI. SLACK OFF AND LAND OUT ON BASE PLATE WITH 110K LBS(W/O BLOCKS). SHOE- 3,513' TOP OF FLOAT COLLAR- 3,429' LEFT OUT 3 JOINTS-118.28'
ROMMEL UNIT 3H | 2 | 2021-07-15 09:00 | 2021-07-15 10:15 | 1.25 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.85 | 3523 | 3523 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-321, SPP-100. NO LOSSES.
ROMMEL UNIT 3H | 2 | 2021-07-15 10:15 | 2021-07-15 10:30 | 0.25 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.86 | 3523 | 3523 | 0 | R/D CRT AND L/D LANDING JT. WELL ON HOLD 7/15/2021 @ 10:30.
ROMMEL UNIT 3H | 2 | 2021-07-15 10:30 | 2021-07-15 12:00 | 1.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.86 | 3523 | 3523 | 0 | WALK RIG F/ ROMMEL 3H T/ REDWOOD A 1H. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON. RIG UP CELLAR PUMPS FOR CEMENT JOB.
ROMMEL UNIT 3H | 2 | 2021-07-15 10:30 | 2021-07-15 10:30 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.86 | 3523 | 3523 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 7/15/2021 @10:30
ROMMEL UNIT 3H | 2 | 2021-07-15 12:00 | 2021-07-15 15:00 | 3 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.86 | 3523 | 3523 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 371 BBLS 11.6 PPG LEAD CEMENT, 98 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 327 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/1150 PSI PRESSURED UP T/1667 PSI (517 PSI OVER) @ 3.5 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 177 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
ROMMEL UNIT 3H | 2 | 2021-07-15 15:00 | 2021-07-15 16:30 | 1.5 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.86 | 3523 | 3523 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD);RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
ROMMEL UNIT 3H | 3 | 2021-08-02 06:00 | 2021-08-02 06:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.86 | 3523 | 3523 |  | MILESTONE_RESUME WELL 1 ON 8/2/2021 @ 06:00
ROMMEL UNIT 3H | 3 | 2021-08-02 06:00 | 2021-08-02 07:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.91 | 3523 | 3523 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM REDWOOD A 1H TO ROMMEL 3H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
ROMMEL UNIT 3H | 3 | 2021-08-02 07:00 | 2021-08-02 08:30 | 1.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.97 | 3523 | 3523 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
ROMMEL UNIT 3H | 3 | 2021-08-02 08:30 | 2021-08-02 10:00 | 1.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.03 | 3523 | 3523 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, KILL LINE, HCR HOSE AND KILL LINE CHECK VALVE 250 PSI LOW AND 5000 PSI HIGH.
ROMMEL UNIT 3H | 3 | 2021-08-02 10:00 | 2021-08-02 11:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.07 | 3523 | 3523 | 0 | INSTALL WEAR BUSHING, CLOSE CSG VALVE AND COVER CELLAR, INSTALL MOUSEHOLE
ROMMEL UNIT 3H | 3 | 2021-08-02 11:00 | 2021-08-02 11:30 | 0.5 | P | SFHLCSG | BOP | SVCBOP | SERVICE BOP | 1.09 | 3523 | 3523 | 0 | PERFORM DRAW DOWN TEST ON ACCUMULATOR
ROMMEL UNIT 3H | 3 | 2021-08-02 11:30 | 2021-08-02 12:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.14 | 3523 | 3523 | 0 | SERVICE TOP DRIVE, TRAVELING BLOCK AND DRAWORKS
ROMMEL UNIT 3H | 3 | 2021-08-02 12:30 | 2021-08-02 14:00 | 1.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.2 | 3523 | 3523 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.90' BIT TO BEND; 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-64', GAMMA-60'. TEST MWD ( GOOD TEST).
ROMMEL UNIT 3H | 3 | 2021-08-02 14:00 | 2021-08-02 15:15 | 1.25 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.25 | 3523 | 3523 | 0 | TRIPPED IN THE HOLE F/575' - T/1,258', PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 3 | 2021-08-02 15:15 | 2021-08-02 15:30 | 0.25 | U | SFHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 1.26 | 3523 | 3523 | 0 | GREASE TOP DRIVE TRACKS DUE TO TD DRAGGING DURING OPERATION
ROMMEL UNIT 3H | 3 | 2021-08-02 15:30 | 2021-08-02 16:00 | 0.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.28 | 3523 | 3523 | 0 | TRIPPED IN THE HOLE F/1,258' - T/2,662', PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 3 | 2021-08-02 16:00 | 2021-08-02 16:30 | 0.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.3 | 3523 | 3523 | 0 | FILLED PIPE & FLOW TESTED DRILL STRING, PICKED UP AGITATOR, & FLOW TESTED. SPP BEFORE-507 PSI SPP AFTER-650 PSI. GPM-337
ROMMEL UNIT 3H | 3 | 2021-08-02 16:30 | 2021-08-02 17:00 | 0.5 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.32 | 3523 | 3523 | 0 | PERFORMED FLOW CHECK (NO FLOW) PULLED TRIP NIPPLE & INSTALLED ROT HEAD
ROMMEL UNIT 3H | 3 | 2021-08-02 17:00 | 2021-08-02 17:30 | 0.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.34 | 3523 | 3523 | 0 | TRIPPED IN THE HOLE F/2662' - T/3429', PROPER DISPLACEMENT. NOTE: PERFORMED PIT DRILL @ 17:23, FILL GAS SEPERATOR.
ROMMEL UNIT 3H | 3 | 2021-08-02 17:30 | 2021-08-02 18:00 | 0.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.36 | 3523 | 3533 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/3429' T/3533', GPM-500, SPP-1300 PSI, DP-100/200, RPM-30, TQ-2/5K
ROMMEL UNIT 3H | 3 | 2021-08-02 18:00 | 2021-08-02 18:15 | 0.25 | P | SFHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 1.38 | 3533 | 3533 | 0 | CIRCULATE BOTTOMS UP GPM-550, SPP-1650 PSI, RPM-30. MW IN 9.0 PPG, MW OUT 9.0 PPG
ROMMEL UNIT 3H | 3 | 2021-08-02 18:15 | 2021-08-02 18:30 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.39 | 3533 | 3533 | 0 | PERFORM F.I.T. WITH 9.0 PPG OBM, 472 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,513' / TVD-3,488'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE
ROMMEL UNIT 3H | 3 | 2021-08-02 18:30 | 2021-08-03 02:45 | 8.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.73 | 3533 | 6688 | 382.4 | ROT (3155' IN 8.17 HRS @ 386.17 FPH) WOB: 15/30K, SPM: 87/87/87, GPM: 830, MMRPM: 138, RPM-80, TRPM: 218, TRQ: 8K/17K, SPP: 3850/4550 PSI, DIFF: 500/700 PSI.
ROMMEL UNIT 3H | 3 | 2021-08-03 02:45 | 2021-08-03 06:00 | 3.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.86 | 6688 | 6825 | 42.2 | SLIDE (137' IN 3.33 HRS @ 41.14 FPH) WOB: 5K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 3850/4100 PSI, DIFF: 100/250 PSI. SLIDE DEPTHS: SLD F/3612' T/3624' 12' TF-HS 18:48-18:56 SLD F/3706' T/3716' 10' TF-20L 19:15-19:21 SLD F/4176' T/4186' 10' TF-HS 20:20-20:28 SLD F/4927' T/4937' 10' TF-20R 22:09-22:16 SLD F/5396' T/5406' 10' TF-80R 23:27-23:42 SLD F/5493' T/5503' 10' TF-80R 23:58-00:07 SLD F/5866' T/5876' 10' TF-80R 00:56-01:06 SLD F/5960' T/5970' 10' TF-70R 01:23-01:36 SLD F/6335' T/6345' 10' TF-45R 02:35-02:49 SLD F/6523' T/6533' 10' TF-HS 03:19-03:35 SLD F/6617' T/6627' 10' TF-HS 03:53-04:16 SLD F/6712' T/6722' 10' TF-HS 04:32-05:00 SLD F/6810' T/6825' 15' TF-HS 05:17-06:00
ROMMEL UNIT 3H | 4 | 2021-08-03 06:00 | 2021-08-03 07:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.91 | 6825 | 7184 | 359 | ROT (359' IN .93 HRS @ 386 FPH) WOB: 15/30K, SPM: 87/87/87, GPM: 830, MMRPM: 138, RPM-80, TRPM: 218, TRQ: 8K/17K, SPP: 3850/4550 PSI, DIFF: 500/700 PSI.
ROMMEL UNIT 3H | 4 | 2021-08-03 07:00 | 2021-08-03 10:00 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.03 | 7184 | 7264 | 26.7 | SLIDE (80' IN 3.07 HRS @ 26 FPH) WOB: 5K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 3850/4100 PSI, DIFF: 100/250 PSI. SLIDE DEPTHS: SLD F/6825' T/6845' 20' TF-HS 06:00-06:37 SLD F/6903' T/6918' 15' TF-HS 06:40-07:05 SLD F/6998' T/7013' 15' TF-HS 07:22-08:02 SLD F/7090' T/7105' 15' TF-30R 08:15-09:00 SLD F/7184' T/7199' 15' TF-60R 09:14-09:51
ROMMEL UNIT 3H | 4 | 2021-08-03 10:00 | 2021-08-03 10:15 | 0.25 | P | INTHL | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 2.04 | 7264 | 7264 | 0 | WORK PIPE WHILE CHANGE GASKET ON VIBRATOR HOSE
ROMMEL UNIT 3H | 4 | 2021-08-03 10:15 | 2021-08-03 10:30 | 0.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.05 | 7264 | 7291 | 108 | ROT (27' IN .22 HRS @ 122.72 FPH) WOB: 20/30K, SPM: 108/108, GPM: 685, MMRPM: 114, RPM-80, TRPM: 194, TRQ: 10K/14K, SPP: 3900 PSI, DIFF: 700 PSI.
ROMMEL UNIT 3H | 4 | 2021-08-03 10:30 | 2021-08-03 11:00 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.07 | 7291 | 7298 | 14 | SLIDE (7' IN .48 HRS @ 14.6 FPH) WOB: 10K/20K, SPM: 113/113, GPM: 720, MMRPM: 120, SPP: 3800/4100 PSI, DIFF: 200/300 PSI. SLIDE DEPTH: SLD F/7291' T/7298' 7' TF-70R 10:28-10:57
ROMMEL UNIT 3H | 4 | 2021-08-03 11:00 | 2021-08-03 11:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.09 | 7298 | 7310 | 24 | CONTROL DRILL ON #2 AND #3 MUD PUMPS WHILE CHANGING OUT CAP GASKET ON #1 MUD PUMP; SLIDE (12' IN .5 HRS @ 24 FPH) WOB: 10K/20K, SPM: 113/113, GPM: 720, MMRPM: 120, SPP: 3800/4100 PSI, DIFF: 200/300 PSI. SLIDE DEPTH: SLD F/7298' T/7310' 12' TF-70R 1100-1130
ROMMEL UNIT 3H | 4 | 2021-08-03 11:30 | 2021-08-03 14:30 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.22 | 7310 | 8140 | 276.7 | ROT (830' IN 3.17 HRS @ 262 FPH) WOB: 20/30K, SPM: 108/108, GPM: 685, MMRPM: 114, RPM-80, TRPM: 194, TRQ: 10K/14K, SPP: 3900 PSI, DIFF: 700 PSI.
ROMMEL UNIT 3H | 4 | 2021-08-03 14:30 | 2021-08-03 16:30 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.3 | 8140 | 8203 | 31.5 | SLIDE (63' IN 1.83 HRS @ 34 FPH) WOB: 5K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 3850/4100 PSI, DIFF: 100/250 PSI. SLIDE DEPTHS: SLD F/7372' T/7387' 15' TF-70R 1147-1220 SLD F/7466' T/7478' 12' TF/30R 1238-1256 SLD F/7653' T/7665' 12' TF-30R 1335-1348 SLD F/7842' T/7854' 12' TF-HS 1420-1434 SLD F/8122' T/8134' 12' TF-30R 1536-1608
ROMMEL UNIT 3H | 4 | 2021-08-03 16:30 | 2021-08-03 17:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.32 | 8203 | 8203 | 0 | LUBRICATE TOP DRIVE, ST-80, DRAWORKS
ROMMEL UNIT 3H | 4 | 2021-08-03 17:00 | 2021-08-04 00:15 | 7.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.63 | 8203 | 10040 | 253.4 | ROT (1837' IN 7.23 HRS @ 254 FPH) WOB: 20/30K, SPM: 86/86/86, GPM: 830, MMRPM: 138, RPM-80, TRPM: 218, TRQ: 10K/16K, SPP: 4500 PSI, DIFF: 700 PSI.
ROMMEL UNIT 3H | 4 | 2021-08-04 00:15 | 2021-08-04 06:00 | 5.75 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.86 | 10040 | 10175 | 23.5 | SLIDE (135' IN 5.77 HRS @ 23.4 FPH) WOB: 5K, SPM: 87/87/87, GPM: 830, MMRPM: 138, SPP: 45000/4750 PSI, DIFF: 100/250 PSI. SLIDE DEPTHS: SLD F/8216' T/8231' 15' TF-110M 1705-1726 SLD F/9155' T/9175' 20' TF-150M 2038-2128 SLD F/9256' T/9276' 20' TF-150M 2150-2244 SLD F/9437' T/9457' 20' TF-150M 2322-0009 SLD F/9530' T/9550' 20' TF-150M 0028-0119 SLD F/9624' T/9644' 20' TF-180M 0136-0241 SLD F/9718' T/9738' 20' TF-120M 0302-0400
ROMMEL UNIT 3H | 5 | 2021-08-04 06:00 | 2021-08-04 06:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.89 | 10175 | 10269 | 188 | ROT (94' IN .5 HRS @ 188 FPH) WOB: 25/35K, SPM: 86/86/86, GPM: 830, MMRPM: 138, RPM-80, TRPM: 218, TRQ: 12K/19K, SPP: 4700/5400 PSI, DIFF: 500/700 PSI.
ROMMEL UNIT 3H | 5 | 2021-08-04 06:30 | 2021-08-04 07:30 | 1 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 2.93 | 10269 | 10457 | 188 | CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT LINER WASHER ROD #2 MUD PUMP; ROT (188' IN 1 HR @ 188 FPH) WOB: 20/30K, SPM: 108/108, GPM: 685, MMRPM: 114, RPM-80, TRPM: 194, TRQ: 11K/19K, SPP: 3600/4200 PSI, DIFF: 400/600 PSI.
ROMMEL UNIT 3H | 5 | 2021-08-04 07:30 | 2021-08-04 08:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.95 | 10457 | 10546 | 178 | ROT (89' IN .43 HRS @ 207 FPH) WOB: 25/35K, SPM: 86/86/86, GPM: 830, MMRPM: 138, RPM-80, TRPM: 218, TRQ: 12K/19K, SPP: 4700/5400 PSI, DIFF: 500/700 PSI.
ROMMEL UNIT 3H | 5 | 2021-08-04 08:00 | 2021-08-04 08:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.97 | 10546 | 10561 | 30 | SLIDE (15' IN .57 HRS @ 26.3 FPH) WOB: 10/20K, SPM: 78/78/78, GPM: 750, MMRPM: 124, SPP: 4100/4300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/10465 T/10481 15' TF-120M 07:35-08:09
ROMMEL UNIT 3H | 5 | 2021-08-04 08:30 | 2021-08-04 10:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.03 | 10561 | 10643 | 54.7 | BUILD CURVE/SLD (82' IN 1.5 HRS @ 54.7 FPH) WOB: 10/20K, SPM: 78/78/78, GPM: 750, MMRPM: 124, SPP: 4100/4300 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/10561 T/10643 82' TF-120M 08:30-10:00
ROMMEL UNIT 3H | 5 | 2021-08-04 10:00 | 2021-08-04 11:00 | 1 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.07 | 10643 | 10643 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80.
ROMMEL UNIT 3H | 5 | 2021-08-04 11:00 | 2021-08-04 14:00 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.2 | 10643 | 10771 | 42.7 | BUILD CURVE/SLD (128' IN 3.03 HRS @ 42.2 FPH) WOB: 10/20K, SPM: 86/86/86, GPM: 830, MMRPM: 138, SPP: 4700/5000 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/10665 T/10739 74' TF-150M 11:10-13:10 SLD F/10759 T/10813 54' TF-30R 13:23-14:25
ROMMEL UNIT 3H | 5 | 2021-08-04 14:00 | 2021-08-04 15:15 | 1.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.25 | 10771 | 10920 | 119.2 | BUILD CURVE/ROT. (149' IN 1.22 HRS @ 122.1 FPH) WOB: 25/35K, SPM: 86/86/86, GPM: 830, MMRPM: 138, RPM-30, TRPM: 168, TRQ: 11K/14K, SPP: 4700/5200 PSI, DIFF: 400/500 PSI.
ROMMEL UNIT 3H | 5 | 2021-08-04 15:15 | 2021-08-04 16:45 | 1.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.31 | 10920 | 10964 | 29.3 | BUILD CURVE/SLD (44' IN 1.68 HRS @ 26.2 FPH) WOB: 10/20K, SPM: 108/108, GPM: 685, MMRPM: 114, SPP: 3400/3700 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/10927 T/10971 44' TF-20R 15:34-17:15 NOTE: CONTROL DRILL ON #1 AND #2 MUD PUMPS WHILE CHANGING OUT SWAB ON #3 MUD PUMP. CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT SUCTION SCREEN CAP GASKET ON #2 MUD PUMP.
ROMMEL UNIT 3H | 5 | 2021-08-04 16:45 | 2021-08-04 17:15 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.33 | 10964 | 10971 | 14 | BUILD CURVE/ROT. (7' IN .32 HRS @ 21.9 FPH) WOB: 20/30K, SPM: 108/108, GPM: 685, MMRPM: 114, RPM-80, TRPM: 194, TRQ: 11K/19K, SPP: 3400/4000 PSI, DIFF: 400/600 PSI. NOTE: CONTROL DRILL ON #1 AND #2 MUD PUMPS WHILE CHANGING OUT SWAB ON #3 MUD PUMP. CONTROL DRILL ON #1 AND #3 MUD PUMPS WHILE CHANGING OUT SUCTION SCREEN CAP GASKET ON #2 MUD PUMP.
ROMMEL UNIT 3H | 5 | 2021-08-04 17:15 | 2021-08-04 17:45 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.35 | 10971 | 10980 | 18 | BUILD CURVE/SLD (9' IN .58 HRS @ 15.5 FPH) WOB: 10/20K, SPM: 86/86/86, GPM: 830, MMRPM: 138, SPP: 4700/5000 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/10971 T/10978 7' TF-20R 17:15-17:45
ROMMEL UNIT 3H | 5 | 2021-08-04 17:45 | 2021-08-04 18:15 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.38 | 10980 | 11022 | 84 | BUILD CURVE/ROT. (42' IN .45 HRS @ 93.3 FPH) WOB: 25/35K, SPM: 86/86/86, GPM: 830, MMRPM: 138, RPM-30, TRPM: 168, TRQ: 15K/19K, SPP: 4700/5200 PSI, DIFF: 400/500 PSI.
ROMMEL UNIT 3H | 5 | 2021-08-04 18:15 | 2021-08-04 20:00 | 1.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.45 | 11022 | 11022 | 0 | PERFORM CLEAN UP CYCLE PUMPING 2-30 BBL SWEEPS SURFACE TO SURFACE TO CLEAN HOLE & PREP FOR OPEN HOLE LOGS AND 7-5/8" CASING. GPM-830, SPP-4600, RPM-30, TRQ-6/8K, SHAKERS CLEAN, FLOW CHECK (WELL STATIC), PUMP SLUG.
ROMMEL UNIT 3H | 5 | 2021-08-04 20:00 | 2021-08-04 20:15 | 0.25 | P | INTHLCSG | FLWBK | FLCHK | FLOW CHECK | 3.46 | 11022 | 11022 | 0 | FLOW CHECK (WELL STATIC), PUMP SLUG.
ROMMEL UNIT 3H | 5 | 2021-08-04 20:15 | 2021-08-04 23:00 | 2.75 | P | INTHLCSG | TRIP | EVAL | TRIP FOR EVAL WELL / CORING / LOG / DST | 3.57 | 11022 | 11022 | 0 | TOH F/11,022' T/2,767', PROPER FILL WITH TRIP TANK.
ROMMEL UNIT 3H | 5 | 2021-08-04 23:00 | 2021-08-04 23:30 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 3.59 | 11022 | 11022 | 0 | PERFORM FLOW CHECK @ SHOE (WELL STATIC); REMOVE ROT. HEAD/ INSTALL TRIP NIPPLE.
ROMMEL UNIT 3H | 5 | 2021-08-04 23:30 | 2021-08-05 00:45 | 1.25 | P | INTHLCSG | TRIP | EVAL | TRIP FOR EVAL WELL / CORING / LOG / DST | 3.65 | 11022 | 11022 | 0 | TOH F/2,767' T/BHA, PROPER FILL WITH TRIP TANK, FLOW CHECK @ BHA (WELL STATIC).
ROMMEL UNIT 3H | 5 | 2021-08-05 00:45 | 2021-08-05 02:00 | 1.25 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.7 | 11022 | 11022 | 0 | RACK BACK HWDP & 2 STDS-6.5" DC, REMOVED MWD TOOL, DRAINED MUD MOTOR, BROKE OUT BIT, AND LAID DOWN SAME- MUD MOTOR DRAINED GOOD WITH LITTLE SQUAT. BIT GRADED 0-1-CT-G-X-0-NO-TD
ROMMEL UNIT 3H | 5 | 2021-08-05 02:00 | 2021-08-05 02:45 | 0.75 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 3.73 | 11022 | 11022 | 0 | PU AND SCRIBE NEW MOTOR AND RACK BACK BHA.
ROMMEL UNIT 3H | 5 | 2021-08-05 02:45 | 2021-08-05 04:45 | 2 | P | INTHLCSG | LOG | RUEQP | RIG UP LOG / SURVEY EQUIPMENT | 3.81 | 11022 | 11022 | 0 | CLEAN AND ORGANIZE RIG FLOOR FOR WIRELINE OPERATIONS, BRING LUBRICATOR AND TOOLS TO RIG FLOOR, SPOT WIRELINE TRUCK AND LAY OUT TOOLS ON CATWALK, PJSM WITH WIRELINE AND RIG CREW, R/U WIRELINE EQUIPMENT.
ROMMEL UNIT 3H | 5 | 2021-08-05 04:45 | 2021-08-05 05:30 | 0.75 | P | INTHLCSG | LOG | RUEQP | RIG UP LOG / SURVEY EQUIPMENT | 3.84 | 11022 | 11022 | 0 | M/U LUBRICATOR AND ATTEMPT TO INSTALL ROTATING HEAD LOGGING ADAPTER (ADAPTER INCORRECT THREAD).
ROMMEL UNIT 3H | 6 | 2021-08-05 06:00 | 2021-08-05 07:30 | 1.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.93 | 11022 | 11022 | 0 | HELD PJSM, CHANGED OUT TOP VBR'S TO 7-5/8" CASING RAMS, PULL WEAR BUSHING.
ROMMEL UNIT 3H | 6 | 2021-08-05 07:30 | 2021-08-05 08:00 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 3.95 | 11022 | 11022 | 0 | P/U JOINT OF DRILL PIPE AND SET TEST PLUG, PRESSURE TESTED BONNET SEALS T/1500 PSI. (TEST GOOD).
ROMMEL UNIT 3H | 6 | 2021-08-05 08:00 | 2021-08-05 09:00 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 3.99 | 11022 | 11022 | 0 | REMOVE TEST PLUG AND RE-INSTALL WEAR BUSHING.
ROMMEL UNIT 3H | 6 | 2021-08-05 09:00 | 2021-08-05 10:00 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.03 | 11022 | 11022 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
ROMMEL UNIT 3H | 6 | 2021-08-05 10:00 | 2021-08-05 13:00 | 3 | U | INTHLCSG | WAIT | WEQP | WAIT ON EQUIPMENT | 4.16 | 11022 | 11022 | 0 | CHANGE OUT STAND JUMP CYLINDER ON TOP DRIVE WHILE WAITING ON THE CORRECT SIZE ROTATING HEAD LOGGING ADAPTER FROM WEATHERFORD. NOTE: A 7 5/8" LOGGING ADAPTER INSTEAD OF 7" WAS SENT OUT.
ROMMEL UNIT 3H | 6 | 2021-08-05 13:00 | 2021-08-05 15:00 | 2 | P | INTHLCSG | LOG | RUEQP | RIG UP LOG / SURVEY EQUIPMENT | 4.24 | 11022 | 11022 | 0 | R/U LUBRICATOR AND SCHLUMBERGER WIRELINE.
ROMMEL UNIT 3H | 6 | 2021-08-05 15:00 | 2021-08-06 02:00 | 11 | P | INTHLCSG | LOG | OPNHL | OPEN HOLE LOGGING | 4.7 | 11022 | 11022 | 0 | P/U SCHLUMBERGER TCOM, SGR AND DIPOLE TOOLS, RIH T/10,998' WLM (10,990' DPM) AND ENCOUNTERED TIGHT SPOT, ATTEMPTED PULL THROUGH TIGHT WITH 1K OVER PULL (TENSION WT @ 8.5K) WITH NO SUCCESS, CONTINUE RIH T/11,030' (11,022' DPM) AND TAGGED BOTTOM, POOH T/10,998' WLM AND ENCOUNTERED TIGHT SPOT, PULLED THROUGH TIGHT WITH 1.5K OVER PULL (TENSION WT @ 9K), CONTINUE POOH T/10,825' WLM AND ENCOUNTERED TIGHT SPOT, PULLED THROUGH TIGHT WITH 1.5K OVER PULL (TENSION WT @ 9K), CONTINUED POOH T/10,700' WLM, RIH T/10,990' WLM (10,982' DPM), LOGGED OPEN HOLE F/10,990' T/3,509' @ 1500 FPH WHILE MONITORING WELL ON TRIP TANK, RIH T/3,800' AND LOGGED OPEN HOLE F/3,800' T/3,509' @ 1500 FPH. POOH.
ROMMEL UNIT 3H | 6 | 2021-08-06 02:00 | 2021-08-06 04:30 | 2.5 | P | INTHLCSG | LOG | RDEQP | RIG DOWN LOG / SURVEY EQUIPMENT | 4.8 | 11022 | 11022 | 0 | L/D TCOM, SGR AND DIPOLE TOOLS, R/D SCHLUMBERGER WIRELINE AND LUBRICATOR.
ROMMEL UNIT 3H | 6 | 2021-08-06 04:30 | 2021-08-06 04:45 | 0.25 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.81 | 11022 | 11022 | 0 | PULL WEAR BUSHING, CLEAN AND ORGANIZE RIG FLOOR FOR CASING RUN.
ROMMEL UNIT 3H | 6 | 2021-08-06 04:45 | 2021-08-06 06:00 | 1.25 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 4.86 | 11022 | 11022 | 0 | HOLD PJSM AND R/U FRANK'S CASING TOOLS AND CRT.
ROMMEL UNIT 3H | 7 | 2021-08-06 06:00 | 2021-08-06 17:30 | 11.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.34 | 11022 | 11022 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN INTERMEDIATE CASING T/11,014.2', FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, RUN 7 5/8" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. 1-JT OF 7 5/8" 29.7# P-110 IC BTC CSG, THEN RAN 235 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, TOTAL OF 251 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALLED 43 LATCH ON BOW SPRING CENTRALIZERS @ 10,703.4' AND EVERY 4TH JT UP TO 2,933.8'. P/U LANDING JOINT, WASH DOWN AND LANDED CSG ON CSG MANDREL W/240K (W/O BLOCKS) FLOAT SHOE-11,014.2' TOP OF FLOATCOLLAR-10,924.8' 13 JOINTS LEFT OUT- 611.86' & 3-10' PUP JT OUT
ROMMEL UNIT 3H | 7 | 2021-08-06 17:30 | 2021-08-06 18:00 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 5.36 | 11022 | 11022 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
ROMMEL UNIT 3H | 7 | 2021-08-06 18:00 | 2021-08-06 19:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.43 | 11022 | 11022 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 107, 8.0 BPM, SPP: 600 PSI, NO LOSSES.
ROMMEL UNIT 3H | 7 | 2021-08-06 19:30 | 2021-08-06 23:00 | 3.5 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 5.57 | 11022 | 11022 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/7000 PSI, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 325 BBL 11.8 PPG 940 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 502 BBLS OF 9.6 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1924 PSI AT 1.3 BPM, BUMP PLUG AND RAISE PSI 500 OVER T/2500 PSI. HELD PRESS. FOR 5 MIN., BLED OFF PSI ( 6 BBLS)-FLOATS HELD. PLUG BUMPED @ 22:43 HRS CEMENTED W/ FULL RETURNS WHILE PUMPING CEMENT. 10 BBLS SPACER BACK TO SURFACE , 37 BBLS INTERFACE TOTAL 47 BBLS ESTIMATED TOP OF CEMENT: 755'
ROMMEL UNIT 3H | 7 | 2021-08-06 23:00 | 2021-08-06 23:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.59 | 11022 | 11022 | 0 | TEST CASING T/3,500 FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. BLED BACK 8.5 BBLS.
ROMMEL UNIT 3H | 7 | 2021-08-06 23:30 | 2021-08-07 00:30 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 5.64 | 11022 | 11022 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
ROMMEL UNIT 3H | 7 | 2021-08-07 00:30 | 2021-08-07 01:30 | 1 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.68 | 11022 | 11022 | 0 | FLUSH THROUGH BOP AND FLOW LINE WITH WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 20K, BROKE OUT & LAID DOWN SETTING TOOL.
ROMMEL UNIT 3H | 7 | 2021-08-07 01:30 | 2021-08-07 03:00 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.74 | 11022 | 11022 | 0 | SLIP AND CUT 50' DRILL LINE, CALIBRATE BLOCK POSITION.
ROMMEL UNIT 3H | 7 | 2021-08-07 03:00 | 2021-08-07 03:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.76 | 11022 | 11022 | 0 | PERFORM RIG SERVICE.
ROMMEL UNIT 3H | 7 | 2021-08-07 03:30 | 2021-08-07 05:00 | 1.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 5.82 | 11022 | 11022 | 0 | CHANGE OUT UPPER RAMS FROM 7-5/8" CASING TO VARIABLE PIPE RAMS
ROMMEL UNIT 3H | 7 | 2021-08-07 05:00 | 2021-08-07 06:00 | 1 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.86 | 11022 | 11022 | 0 | SET BOP WRANGLER, REMOVE TURN BUCKLES, NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL. PREP RIG TO WALK TO ROMMEL 4H. NOTE: CUT MUD WT IN ACTIVE SYSTEM F/9.6 PPG T/8.8 PPG
ROMMEL UNIT 3H | 7 | 2021-08-07 06:00 | 2021-08-07 06:00 | 0 |  | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 5.86 | 11022 | 11022 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 8-7-2021 @ 06:00
ROMMEL UNIT 3H | 8 | 2021-08-11 06:00 | 2021-08-11 06:00 | 0 | P | INTHLCSG | MSTN | RSUM2 | MILESTONE_RESUME WELL OPERATIONS 2 | 5.86 | 11022 | 11022 |  | MILESTONE_RESUME WELL 2 ON 8/11/2021 @ 06:00
ROMMEL UNIT 3H | 8 | 2021-08-11 06:00 | 2021-08-11 08:00 | 2 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.95 | 11022 | 11022 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM ROMMEL 4H TO ROMMEL 3H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
ROMMEL UNIT 3H | 8 | 2021-08-11 08:00 | 2021-08-11 10:00 | 2 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 6.03 | 11022 | 11022 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP AND SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES AND FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S AND LAY OVER SAME.
ROMMEL UNIT 3H | 8 | 2021-08-11 10:00 | 2021-08-11 11:00 | 1 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 6.07 | 11022 | 11022 | 0 | REMOVE CASING RAMS AND INSTALLED VARIABLE RAMS.
ROMMEL UNIT 3H | 8 | 2021-08-11 11:00 | 2021-08-11 12:00 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 6.11 | 11022 | 11022 | 0 | PICK UP 4.5" HANDLING TOOLS, CLEAN IN LINE SCREEN AND REMOVE CHECK VALVE FOR BOP TEST.
ROMMEL UNIT 3H | 8 | 2021-08-11 12:00 | 2021-08-11 15:30 | 3.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 6.26 | 11022 | 11022 | 0 | CHANGE OUT SAVER SUB FROM 4 1/2 IF TO CET 43, CHANGE OUT STABBING GUIDE AND DIES IN GRABBER BOX.
ROMMEL UNIT 3H | 8 | 2021-08-11 15:30 | 2021-08-11 19:30 | 4 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.43 | 11022 | 11022 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH, STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST.
ROMMEL UNIT 3H | 8 | 2021-08-11 19:30 | 2021-08-11 22:00 | 2.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 6.53 | 11022 | 11022 | 0 | REMOVE TEST CAP, PULLED TEST PLUG INSTALL WEAR BUSHING AND TRIP NIPPLE, STAGE OUT DIRECTIONAL BHA, PREP FLOOR FOR BHA HANDLING, VERIFY BOP ALIGNMENT.
ROMMEL UNIT 3H | 8 | 2021-08-11 22:00 | 2021-08-11 22:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.55 | 11022 | 11022 | 0 | PERFORM RIG SERVICE ON DRAWWORKS AND ST-80.
ROMMEL UNIT 3H | 8 | 2021-08-11 22:30 | 2021-08-12 00:30 | 2 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.64 | 11022 | 11022 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13601236 JETS 6/18's TFA: 1.491), 5.5", 6/7, 8.8 STG @ 2.00° SLICK; .68 REV/GAL; 4.00' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, X/O XT-39 P x CET43. BIT TO SVY-61'. BIT TO GAMMA-57'. TEST MWD (TEST GOOD).
ROMMEL UNIT 3H | 8 | 2021-08-12 00:30 | 2021-08-12 03:30 | 3 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 6.76 | 11022 | 11022 | 0 | P/U AND SINGLE IN HOLE W/ 4-1/2" CET-43 DRILL PIPE F/ BHA T/ 1,992'.
ROMMEL UNIT 3H | 8 | 2021-08-12 03:30 | 2021-08-12 05:45 | 2.25 | U | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.85 | 11022 | 11022 | 0 | TOH F/ 1,992' T/ BHA TO INSTALL REAMER IN STRING, M/U 6-13/16" DRILL-N-REAM, TIH T/1,992' .
ROMMEL UNIT 3H | 8 | 2021-08-12 05:45 | 2021-08-12 06:00 | 0.25 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 6.86 | 11022 | 11022 | 0 | P/U AND SINGLE IN HOLE W/ 4-1/2" CET-43 DRILL PIPE F/ 1,992' T/ 2,100'.
ROMMEL UNIT 3H | 9 | 2021-08-12 06:00 | 2021-08-12 15:45 | 9.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.27 | 11022 | 11022 | 0 | P/U AND SINGLE IN HOLE W/ 4-1/2" CET-43 DRILL PIPE F/2,100' T/10,510’, FILLING PIPE EVERY 40 STDS, HOLE GIVING PROPER DISPLACEMENT. NOTE: VERIFIED PIPE WAS TORQUED TO 36.5K, DRIFT DRILL PIPE IN CATWALK WHILE PICKING UP AND TRIPPING IN THE HOLE.
ROMMEL UNIT 3H | 9 | 2021-08-12 15:45 | 2021-08-12 16:45 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.31 | 11022 | 11022 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
ROMMEL UNIT 3H | 9 | 2021-08-12 16:45 | 2021-08-12 17:45 | 1 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 7.35 | 11022 | 11022 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 9 | 2021-08-12 17:45 | 2021-08-12 19:45 | 2 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 7.44 | 11022 | 11022 | 0 | SLIP AND CUT 70' DRILL LINE, CALIBRATE BLOCK POSITION.
ROMMEL UNIT 3H | 9 | 2021-08-12 19:45 | 2021-08-12 21:00 | 1.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 7.49 | 11022 | 11022 | 0 | P/U AND SINGLE IN HOLE W/ 4-1/2" CET-43 DRILL PIPE F/ 10,510’ T/10,883’. ENCOUNTER CEMENT STRINGERS, DECISION MADE TO WASH DOWN TO FLOAT COLLAR. CONFIRM PROPER VALVE ALIGNMENT; FILL GAS SEPARATOR, PERFORM BOP DRILL RESPONSE TIME= 85 SECONDS.
ROMMEL UNIT 3H | 9 | 2021-08-12 21:00 | 2021-08-12 22:00 | 1 | P | INTHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 7.53 | 11022 | 11022 | 0 | WASH AND REAM F/10,883' T/ FLOAT COLLAR @ 10,924'. CONFIRM PROPER VALVE ALIGNMENT; FILL GAS SEPARATOR, PERFORM BOP DRILL RESPONSE TIME= 85 SECONDS.
ROMMEL UNIT 3H | 9 | 2021-08-12 22:00 | 2021-08-12 22:45 | 0.75 | U | INTHLCSG | RIGMT | WLESVC | WELL CONTROL EQUIPMENT SERVICE | 7.56 | 11022 | 11022 | 0 | TROUBLESHOOT ORBIT VALVE NOT OPENING, REPLACE LEAKING AIR LINE.
ROMMEL UNIT 3H | 9 | 2021-08-12 22:45 | 2021-08-12 23:30 | 0.75 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 7.59 | 11022 | 11032 | 13.3 | TAGGED FLOAT COLLAR @ 10,924', DRILL SHOE TRACK TO 11,014' AND 10' OF NEW FORMATION F/11,022' T/11,032', GPM-300, SPP-1,800 PSI, RPM-30, TRQ-2K, MRPM-204, TRPM-234, DIFF-500 PSI.
ROMMEL UNIT 3H | 9 | 2021-08-12 23:30 | 2021-08-12 23:45 | 0.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.6 | 11032 | 11032 | 0 | CIRCULATE 10 PPG OBM IN/OUT BEFORE PERFORMING F.I.T., GPM-300, SPP-1,200 PSI, RPM-30, TRQ 1K.
ROMMEL UNIT 3H | 9 | 2021-08-12 23:45 | 2021-08-13 | 0.25 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 7.61 | 11032 | 11032 | 0 | PERFORM F.I.T. WITH 10.0 PPG OBM, 1,719 PSI SURFACE PRESSURE FOR 13.0 PPG EMW, SHOE MD-11,014' / TVD-10,924'. PRESSURE BLED OFF T/1,710 PSI AND STABILIZED IN 5 MINUTES. GOOD F.I.T. TEST TO 13.0 PPG EMW. NOTE: CASING PRESSURE WAS RECORDED FROM CASING GAUGE ON THE REMOTE CHOKE PANEL.
ROMMEL UNIT 3H | 9 | 2021-08-13 | 2021-08-13 02:00 | 2 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.7 | 11032 | 11122 | 45 | DRILL PILOT HOLE SECTION-SLIDE (90' IN 1.75 HRS @ 51.4 FPH) WOB-20/25K, SPM-58/58, GPM-300, MRPM-114, SPP-2,500/4,300 PSI, DIFF-450/800 PSI. SLIDE DEPTHS: SLD F/11,032' T/11,042' 10' TF-90 0000-0015 SLD F/11,175' T/11,185' 10' TF-HS 0145-0152 SLD F/11,269' T/11,284' 15' TF-HS 0230-0250 SLD F/11,364' T/11,379' 15' TF-HS 0325-0425 SLD F/11,458' T/11,478' 20' TF-HS 0425-0455 SLD F/11,553' T/11,573' 20' TF-HS 0530-0545
ROMMEL UNIT 3H | 9 | 2021-08-13 02:00 | 2021-08-13 06:00 | 4 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.86 | 11122 | 11627 | 126.2 | DRILL PILOT HOLE SECTION-ROT (505' IN 3.82 HRS @ 132.2 FPH) WOB-25K, SPM-76/76, GPM-400, RPM-55, MRPM-272, TRPM-327, TQ-7K SPP-2,500/4,300, DIFF-600/800, NOTE: START PUMPING 10 BBL LCM SWEEPS CONSISTING OF 15 PPB MAGMAFIBER, 15 PPB NEW CARB AND 15 PPB NEW PHALT @ THE TOP OF THE BUDA.
ROMMEL UNIT 3H | 10 | 2021-08-13 06:00 | 2021-08-13 07:00 | 1 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.91 | 11627 | 11742 | 115 | DRILL PILOT HOLE SECTION-ROT (115' IN 1 HR @ 115 FPH) WOB-25K, SPM-57/57, GPM-300, RPM-55, MRPM-204, TRPM-259, TQ-5/7K SPP-2,400/3,200, DIFF-600/800, CHOKES: 100% / 100%, NO FLARE, NO MUD CUT, AVG CSG PRESSURE= 0 PSI.
ROMMEL UNIT 3H | 10 | 2021-08-13 07:00 | 2021-08-13 08:30 | 1.5 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.97 | 11742 | 11742 | 0 | ATTEMPT TO MAKE UP A CONNECTION WITH TOP DRIVE AND CONNECTION WOULD NOT MAKE UP, INSPECT SAVER SUB AND DRILL PIPE CONNECTION, OBSERVE GALLING OF THREADS ON THE SAVER SUB AND DRILL PIPE CONNECTION, L/D JOINT OF DRILL PIPE, CIRCULATE LCM OUT OF BIT, CHANGE OUT DIES ON ST-80.
ROMMEL UNIT 3H | 10 | 2021-08-13 08:30 | 2021-08-13 09:30 | 1 | P | PRDHLCV | TRIP | WPR | WIPER TRIP IN / OUT | 8.01 | 11742 | 11742 | 0 | FLOW CHECK (NO FLOW), SHORT TRIP WET F/11,742’ T/10,982’, HOLE TAKING PROPER FILL, NO EXCESSIVE DRAG.
ROMMEL UNIT 3H | 10 | 2021-08-13 09:30 | 2021-08-13 10:30 | 1 | P | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.05 | 11742 | 11742 | 0 | PERFORM RIG SERVICE.
ROMMEL UNIT 3H | 10 | 2021-08-13 10:30 | 2021-08-13 12:45 | 2.25 | U | PRDHLCV | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 8.15 | 11742 | 11742 | 0 | CIRCULATE OVER TOP OF HOLE ON TRIP TANK AND MONITOR WELL WHILE CHANGING OUT SAVER SUB.
ROMMEL UNIT 3H | 10 | 2021-08-13 12:45 | 2021-08-13 13:15 | 0.5 | P | PRDHLCV | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 8.17 | 11742 | 11742 | 0 | WASH/REAM F/10,982' T/11,172', SPM-57/57, GPM-300, RPM-30, MRPM-204, TRPM-234, TQ-3/4K SPP-2,400, CHOKES: 100% / 100%, NO FLARE, NO MUD CUT, AVG CSG PRESSURE= 0 PSI.
ROMMEL UNIT 3H | 10 | 2021-08-13 13:15 | 2021-08-13 16:00 | 2.75 | U | PRDHLCV | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 8.28 | 11742 | 11742 | 0 | ATTEMPTED TO MAKE UP A CONNECTION WITH TOP DRIVE AND CONNECTION WOULD NOT MAKE UP, INSPECTED SAVER SUB AND DRILL PIPE CONNECTION, OBSERVED NO GALLING ON SAVER SUB AND GALLING IN THREADS ON DRILL PIPE CONNECTION, L/D 1 JOINT OF DRILL PIPE, TROUBLE SHOOT STABBING ISSUE ON SAVER SUB.
ROMMEL UNIT 3H | 10 | 2021-08-13 16:00 | 2021-08-13 17:15 | 1.25 | P | PRDHLCV | WSHRM | RMDIR | WASH / REAM FOR DIRECTIONAL SLIDE | 8.33 | 11742 | 11742 | 0 | WASH/REAM F/11,172' T/11,742' SPM-57/57, GPM-300, RPM-60, MRPM-204, TRPM-264, TQ-5/6K SPP-2,400, CHOKES: 100% / 100%, NO FLARE, NO MUD CUT, AVG CSG PRESSURE= 0 PSI.
ROMMEL UNIT 3H | 10 | 2021-08-13 17:15 | 2021-08-13 17:45 | 0.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.35 | 11742 | 11762 | 40 | DRILL PILOT HOLE SECTION-ROT (20' IN .5 HRS @ 40 FPH) WOB-20/25K, SPM-57/57, GPM-300, RPM-60, MRPM-204, TRPM-259, TQ-5/7K SPP-2,400/3,200, DIFF-600/800, CHOKES: 100% / 100%, NO FLARE, NO MUD CUT, AVG CSG PRESSURE= 0 PSI, MAX GAS: 705u.
ROMMEL UNIT 3H | 10 | 2021-08-13 17:45 | 2021-08-13 19:45 | 2 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.44 | 11762 | 11762 | 0 | PUMP 20 BBL HI-VIS SWEEP, CIRCULATE HOLE CLEAN AND WEIGHT UP F/10.0 PPG T/10.2 PPG, RPM-70, SPM: 57/57, GPM-300, INITIAL SPP-2400 PSI/FINAL SPP-2600, CHOKES- 100% / 100%, NO FLARE,NO MUD CUT, MAX CASING PRESSURE=0 PSI, MAX GAS: 556u, ENDING GAS: 261u.
ROMMEL UNIT 3H | 10 | 2021-08-13 19:45 | 2021-08-13 20:30 | 0.75 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.47 | 11762 | 11762 | 0 | FLOW CHECK (NO FLOW), PUMP AND SPOT 30 BBL 5 PPB GRAPHITE PILL, PUMP SLUG.
ROMMEL UNIT 3H | 10 | 2021-08-13 20:30 | 2021-08-14 03:00 | 6.5 | P | PRDHLCV | TRIP | EVAL | TRIP FOR EVAL WELL / CORING / LOG / DST | 8.74 | 11762 | 11762 | 0 | TRIP OUT THE HOLE F/11,762' T/BHA, HOLE TAKING PROPER FILL, NO EXCESSIVE DRAG. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
ROMMEL UNIT 3H | 10 | 2021-08-14 03:00 | 2021-08-14 05:00 | 2 | P | PRDHLCV | TRIP | LDBHA | LAY DOWN BIT / BHA | 8.82 | 11762 | 11762 | 0 | L/D REAMER, REMOVE MWD TOOL, DRAIN MUD MOTOR, BREAK OFF BIT, C/O MUD MOTOR AND RACK BACK MONELS. BIT GRADED 0-8-LT-S-X-0-PN-TD (BLADE BROKE OFF WHILE OFF BOTTOM).
ROMMEL UNIT 3H | 10 | 2021-08-14 05:00 | 2021-08-14 06:00 | 1 | P | PRDHLCV | LOG | RDEQP | RIG DOWN LOG / SURVEY EQUIPMENT | 8.86 | 11762 | 11762 | 0 | CLEAN AND CLEAR RIG FLOOR FOR WIRELINE OPERATIONS, HOLD PJSM WITH HALLIBURTON CREW AND RIG CREW, R/U LUBRICATOR AND HALLIBURTON WIRELINE.
ROMMEL UNIT 3H | 11 | 2021-08-14 06:00 | 2021-08-14 08:00 | 2 | P | PRDHLCV | LOG | RUEQP | RIG UP LOG / SURVEY EQUIPMENT | 8.95 | 11762 | 11762 | 0 | RIG UP HALLIBURTON WIRELINE, PICK UP HALLIBURTON TCOM, SONIC AND SGR TOOLS.
ROMMEL UNIT 3H | 11 | 2021-08-14 08:00 | 2021-08-14 13:15 | 5.25 | P | PRDHLCV | LOG | OPNHL | OPEN HOLE LOGGING | 9.17 | 11762 | 11762 | 0 | RIH T/11,757' WLM (11,755' DPM), LOGGED OPEN HOLE F/11,757' T/11,014' @ 1500 FPH WHILE MONITORING WELL ON TRIP TANK, RIH FOR REPEAT LOG AND ENCOUNTERED TIGHT SPOTS 11,250’ AND 11,350, SET 300 LBS, PULL THROUGH TIGHT WITH 2K OVER PULL (TENSION WT @ 9.5K), CONTINUE RIH T/11,757’, LOGGED OPEN HOLE F/11,757' T/11,014' @ 1500 FPH WHILE MONITORING WELL ON TRIP TANK WITH NO ISSUES, POOH.
ROMMEL UNIT 3H | 11 | 2021-08-14 13:15 | 2021-08-14 15:15 | 2 | P | PRDHLCV | LOG | RDEQP | RIG DOWN LOG / SURVEY EQUIPMENT | 9.25 | 11762 | 11762 | 0 | L/D TCOM, SONIC AND SGR TOOLS, RIG DOWN HALLIBURTON WIRELINE.
ROMMEL UNIT 3H | 11 | 2021-08-14 15:15 | 2021-08-14 15:30 | 0.25 | P | PRDHLCV | RURD | RDEQP | RIG DOWN EQUIPMENT | 9.26 | 11762 | 11762 | 0 | CLEAN AND ORGANIZE RIG FLOOR OF SLIP, TRIP AND FALL HAZARDS BEFORE RIGGING UP SCHLUMBERGER WIRELINE.
ROMMEL UNIT 3H | 11 | 2021-08-14 15:30 | 2021-08-14 17:00 | 1.5 | P | PRDHLCV | LOG | RUEQP | RIG UP LOG / SURVEY EQUIPMENT | 9.32 | 11762 | 11762 | 0 | RIG UP SCHLUMBERGER WIRELINE, PICK UP SCHLUMBERGER SIDE WALL CORING TOOLS.
ROMMEL UNIT 3H | 11 | 2021-08-14 17:00 | 2021-08-15 06:00 | 13 | P | PRDHLCV | LOG | CORE | CORING OPERATIONS | 9.86 | 11762 | 11762 | 0 | RIH WITH SIDE WALL CORING TOOLS T/11,612', CORRELATE F/11,612' T/11,475', VERIFIED CORRELATION, RIH T/11,570', DRILL SIDE WALL CORES F/11,570' T/11,236' IN THE EAGLEFORD AND AUSTIN CHALK FORMATIONS (45/50 CORES COMPLETED).
ROMMEL UNIT 3H | 12 | 2021-08-15 06:00 | 2021-08-15 09:00 | 3 | P | PRDHLCV | LOG | CORE | CORING OPERATIONS | 9.99 | 11762 | 11762 | 0 | PERFORM SIDE WALL CORE OPERATIONS F/11,236’ T/11,192’ IN THE AUSTIN CHALK FORMATION (50/50 CORES COMPLETED), POOH WHILE MONITORING WELL ON TRIP TANK.
ROMMEL UNIT 3H | 12 | 2021-08-15 09:00 | 2021-08-15 11:00 | 2 | P | PRDHLCV | LOG | CORE | CORING OPERATIONS | 10.07 | 11762 | 11762 | 0 | L/D SIDE WALL CORING BARREL AND COLLECTED CORES (RECOVERED 48 OUT 50 CORES DRILLED), CONTINUE L/D SIDE WALL CORING TOOLS.
ROMMEL UNIT 3H | 12 | 2021-08-15 11:00 | 2021-08-15 12:15 | 1.25 | P | PRDHLCV | LOG | OPNHL | OPEN HOLE LOGGING | 10.13 | 11762 | 11762 | 0 | P/U NGI IMAGINING TOOLS.
ROMMEL UNIT 3H | 12 | 2021-08-15 12:15 | 2021-08-15 16:30 | 4.25 | P | PRDHLCV | LOG | OPNHL | OPEN HOLE LOGGING | 10.3 | 11762 | 11762 | 0 | RIH T/11,160’ WLM, LOG OPEN HOLE F/11,160’ T/11,750’ 1800 FPH, LOG NGI F/11,750’ T/11,014’ @ 1500 FPH, RIH T/11,400' FOR REPEAT LOG, LOG F/11,400' T/11,014', POOH WHILE MONITORING WELL ON TRIP TANK.
ROMMEL UNIT 3H | 12 | 2021-08-15 16:30 | 2021-08-15 18:00 | 1.5 | P | PRDHLCV | LOG | RDEQP | RIG DOWN LOG / SURVEY EQUIPMENT | 10.36 | 11762 | 11762 | 0 | HELD PJSM, L/D NGI IMAGINING TOOLS, R/D SCHLUMBERGER WIRELINE, R/D LUBICATOR.
ROMMEL UNIT 3H | 12 | 2021-08-15 18:00 | 2021-08-15 21:00 | 3 | P | PRDHLCV | RURD | RUEQP | RIG UP EQUIPMENT | 10.49 | 11762 | 11762 | 0 | P/U 2 7/8" HANDLING TOOLS WHILE CHANGING OUT SAVER SUB.
ROMMEL UNIT 3H | 12 | 2021-08-15 21:00 | 2021-08-15 22:45 | 1.75 | P | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 10.56 | 11762 | 11762 | 0 | P/U MULE SHOE BHA, P/U AND TIH WITH 2 7/8" TUBING T/1,035'.
ROMMEL UNIT 3H | 12 | 2021-08-15 22:45 | 2021-08-15 23:00 | 0.25 | P | PRDHLCV | RURD | RDEQP | RIG DOWN EQUIPMENT | 10.57 | 11762 | 11762 | 0 | R/D 2 7/8" HANDLING TOOLS.
ROMMEL UNIT 3H | 12 | 2021-08-15 23:00 | 2021-08-16 03:30 | 4.5 | P | PRDHLCV | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 10.76 | 11762 | 11762 | 0 | TIH WITH 4 1/2" DRILL PIPE F/1,035' T/11,075', HOLE GIVING PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 12 | 2021-08-16 03:30 | 2021-08-16 04:30 | 1 | P | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.8 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (WELL STATIC), REMOVE TRIP NIPPLE, INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 12 | 2021-08-16 04:30 | 2021-08-16 06:00 | 1.5 | P | PRDHLCV | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 10.86 | 11762 | 11762 | 0 | WASH IN THE HOLE WITH 4 1/2" DRILL PIPE F/11,075' T/11,550'. FLOW RATE: 185 GPM SPP: 700 PSI
ROMMEL UNIT 3H | 13 | 2021-08-16 06:00 | 2021-08-16 06:15 | 0.25 | P | PRDHLCV | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 10.88 | 11762 | 11762 | 0 | WASH IN THE HOLE WITH 4 1/2" DRILL PIPE F/11,550' T/11,752'. GPM: 185, SPP: 850 PSI.
ROMMEL UNIT 3H | 13 | 2021-08-16 06:15 | 2021-08-16 07:30 | 1.25 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.93 | 11762 | 11762 | 0 | CIRCULATE HOLE CLEAN BEFORE PUMPING 1ST CEMENT PLUG, GPM: 350, SPP: 2300 PSI, MAX GAS: 828u, AVG BG GAS: 100-200u.
ROMMEL UNIT 3H | 13 | 2021-08-16 07:30 | 2021-08-16 08:00 | 0.5 | P | PRDHLCV | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 10.95 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (NO FLOW), RIG UP PUMP IN SUB AND CIRCULATING IRON TO CEMENT STANDPIPE.
ROMMEL UNIT 3H | 13 | 2021-08-16 08:00 | 2021-08-16 09:00 | 1 | P | PRDHLCV | CMT | REMCM | REMEDIAL CEMENT OPERATIONS | 10.99 | 11762 | 11762 | 0 | HOLD PJSM, TEST LINES T/5,000 PSI, PUMP 1ST CEMENT PLUG WITH NINE ENERGY SERVICES: 19.3 BBL 12.5 PPG WEIGHTED SPACER, 13.3 BBL 16.4 PPG 55 SXS 1.41 YIELD CLASS H -MM CEMENT, 2.8 BBL 12.5 PPG WEIGHTED SPACER, DISPLACE WITH 146.7 BBL (3 BBLS SHORT OF CALCULATED DISPLACEMENT) 10.2 PPG OBM @ 8 BPM WITH 2,200 PSI LIFT, DECREASE PUMP RATE T/ 3 BPM FOR LAST 6.7 BBL WITH 550 PSI. LEFT 4.8 BBLS OF CEMENT AND 2.8 BBLS OF SPACER IN THE DRILL PIPE. TOP OF PLUG @ 11,462'. MAX GAS: 135u.
ROMMEL UNIT 3H | 13 | 2021-08-16 09:00 | 2021-08-16 09:15 | 0.25 | P | PRDHLCV | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 11 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (NO FLOW), RIG DOWN PUMP IN SUB AND CIRCULATING IRON FROM CEMENT STANDPIPE.
ROMMEL UNIT 3H | 13 | 2021-08-16 09:15 | 2021-08-16 10:15 | 1 | P | PRDHLCV | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 11.04 | 11762 | 11762 | 0 | TRIP OUT THE HOLE WET F/11,752’ T/11,075’, HOLE TAKING PROPER FILL, L/D 10’ AND 5’ PUP JOINTS.
ROMMEL UNIT 3H | 13 | 2021-08-16 10:15 | 2021-08-16 12:00 | 1.75 | U | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.11 | 11762 | 11762 | 0 | INSERT NERF BALL AND ATTEMPT TO CIRCULATE, PUMP 4.5 BBL SPP INCREASE TO 4,530 PSI WITH NO RETURNS, BLEED OFF PRESSURE AND ATTEMPT TO CIRCULATE,PUMP 2.3 BBL SPP INCREASE TO 2,875 PSI WITH NO RETURNS, PULL 1 STD AND ATTEMPT TO CIRCULATE, PUMP 3.2 BBL SPP INCREASE TO 2,950 PSI WITH NO RETURNS, RIG UP PUMP IN SUB AND CIRCULATING IRON TO RIG STAND PIPE, ATTEMPT TO CIRCULATE, PUMP 1.7 BBLS SPP INCREASE TO 2,200 PSI WITH NO RETURNS, SWAP CIRCULATING IRON TO CEMENT STANDPIPE, ATTEMPT TO CIRCULATE WITH CEMENT TRUCK, PUMP 3 BBLS AND PRESSURE INCREASE TO 4,500 PSI WITH NO RETURNS, BLEED OFF PRESSURE, PUMP 4 BBLS AND PRESSURE INCREASE TO 8,000 PSI WITH NO RETURNS.
ROMMEL UNIT 3H | 13 | 2021-08-16 12:00 | 2021-08-16 12:30 | 0.5 | U | PRDHLCV | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 11.14 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (NO FLOW), RIG DOWN CIRCULATING IRON, PUMP IN SUB AND CEMENT STAND PIPE.
ROMMEL UNIT 3H | 13 | 2021-08-16 12:30 | 2021-08-16 22:30 | 10 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 11.55 | 11762 | 11762 | 0 | TRIP OUT THE HOLE WET F/10,975’ T/1,035' WHILE DRIFTING PIPE IN THE MOUSE HOLE, HOLE TAKING PROPER FILL. NOTE: DROP DRIFT IN THE 2ND STAND PULLED AND DRIFT HUNG UP IN STAND, L/D STAND AND OBSERVED DRIFT STUCK IN THE BOTTOM OF STAND, REMOVED DRIFT AND DID NOT OBSERVE ANY OBSTRUCTION, DROP DRIFT DOWN PIPE AND DRIFT FELL THROUGH WITH NO OBSTRUCTION.
ROMMEL UNIT 3H | 13 | 2021-08-16 22:30 | 2021-08-16 23:00 | 0.5 | U | PRDHLCV | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 11.57 | 11762 | 11762 | 0 | REMOVE ROTATING HEAD, INSTALL TRIP NIPPLE.
ROMMEL UNIT 3H | 13 | 2021-08-16 23:00 | 2021-08-16 23:30 | 0.5 | U | PRDHLCV | RURD | RUEQP | RIG UP EQUIPMENT | 11.59 | 11762 | 11762 | 0 | RIG UP 2 7/8" HANDLING TOOLS.
ROMMEL UNIT 3H | 13 | 2021-08-16 23:30 | 2021-08-17 02:00 | 2.5 | U | PRDHLCV | TRIP | LDDP | LAY DOWN DRILLPIPE | 11.7 | 11762 | 11762 | 0 | TRIP OUT THE HOLE AND L/D 2 7/8" TUBING F/1,035', L/D MULE SHOE. NOTE: OBSERVE PARTIALLY MIXED AND DEHYDRATED CEMENT IN ENTIRE TUBING STRING.
ROMMEL UNIT 3H | 13 | 2021-08-17 02:00 | 2021-08-17 04:15 | 2.25 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 11.79 | 11762 | 11762 | 0 | CLEAN AND CLEAR RIG FLOOR, P/U MULE SHOE BHA, P/U AND TIH WITH 2 7/8" TUBING T/1,024'.
ROMMEL UNIT 3H | 13 | 2021-08-17 04:15 | 2021-08-17 04:30 | 0.25 | U | PRDHLCV | RURD | RDEQP | RIG DOWN EQUIPMENT | 11.8 | 11762 | 11762 | 0 | RIG DOWN 2 7/8" HANDLING TOOLS.
ROMMEL UNIT 3H | 13 | 2021-08-17 04:30 | 2021-08-17 06:00 | 1.5 | U | PRDHLCV | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 11.86 | 11762 | 11762 | 0 | TRIP IN THE HOLE WITH 4 1/2" DRILL PIPE F/1,024' T/4,832', HOLE GIVING PROPER FILL.
ROMMEL UNIT 3H | 14 | 2021-08-17 06:00 | 2021-08-17 08:30 | 2.5 | U | PRDHLCV | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 11.97 | 11762 | 11762 | 0 | TIH F/4,832’ T/10,887’, HOLE GIVING PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 14 | 2021-08-17 08:30 | 2021-08-17 09:30 | 1 | P | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.01 | 11762 | 11762 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
ROMMEL UNIT 3H | 14 | 2021-08-17 09:30 | 2021-08-17 10:00 | 0.5 | U | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 12.03 | 11762 | 11762 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 14 | 2021-08-17 10:00 | 2021-08-17 11:00 | 1 | U | PRDHLCV | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 12.07 | 11762 | 11762 | 0 | WASH IN THE HOLE WITH 4 1/2" DRILL PIPE F/10,887' T/11,440' @ 30-40 FPM, GPM: 350, SPP: 2,400 PSI. TAGGED TOP OF CEMENT @ 11,440’ WITH 10K DOWN, PULLED UP T/11,434’, WASH DOWN AND TAGGED TOP OF CEMENT @ 11,440’ WITH 10K DOWN TO VERIFY TOP OF CEMENT.
ROMMEL UNIT 3H | 14 | 2021-08-17 11:00 | 2021-08-17 14:45 | 3.75 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.23 | 11762 | 11762 | 0 | CIRCULATE HOLE CLEAN BEFORE PUMPING TOP CEMENT PLUG WHILE RIG UP CEMENT EQUIPMENT AND MIX WEIGHTED SPACER, GPM: 386, SPP: 2600 PSI, MAX GAS: 855u, AVG BG GAS: 35-100u. NOTE: DIVERTED 113 BBLS OF SPACER AND INTERFACE TO THE OPEN TOP.
ROMMEL UNIT 3H | 14 | 2021-08-17 14:45 | 2021-08-17 15:00 | 0.25 | P | PRDHLCV | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 12.24 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (NO FLOW), RIG UP PUMP IN SUB AND CIRCULATING IRON TO CEMENT STANDPIPE.
ROMMEL UNIT 3H | 14 | 2021-08-17 15:00 | 2021-08-17 15:45 | 0.75 | P | PRDHLCV | CMT | REMCM | REMEDIAL CEMENT OPERATIONS | 12.27 | 11762 | 11762 | 0 | HOLD PJSM, TEST LINES T/8,000 PSI, PUMP TOP CEMENT PLUG WITH NINE ENERGY SERVICES: 31.8 BBL 12.5 PPG WEIGHTED SPACER, 34.8 BBL 17.5 PPG 210 SXS .95 YIELD CLASS H -MM CEMENT, 18 BBL 12.5 PPG WEIGHTED SPACER, DISPLACE WITH 128.2 BBL (3 BBLS SHORT OF CALCULATED DISPLACEMENT) WITH 10.2 PPG OBM @ 9.2 BPM WITH 2,620 PSI, DECREASE PUMP RATE T/ 5 BPM FOR LAST 5 BBL WITH 1200 PSI. LEFT 5.1 BBLS OF CEMENT AND 18 BBLS OF SPACER IN THE DRILL PIPE. TOP OF PLUG @ 10,640'. MAX GAS: 35u.
ROMMEL UNIT 3H | 14 | 2021-08-17 15:45 | 2021-08-17 16:00 | 0.25 | P | PRDHLCV | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 12.28 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (NO FLOW), RIG DOWN PUMP IN SUB AND CIRCULATING IRON FROM CEMENT STANDPIPE
ROMMEL UNIT 3H | 14 | 2021-08-17 16:00 | 2021-08-17 16:30 | 0.5 | P | PRDHLCV | TRIP | CMT | TRIP FOR CEMENT / SQUEEZE / PLUG (INCL TOOLS) | 12.3 | 11762 | 11762 | 0 | TRIP OUT THE HOLE WITH DRY PIPE F/11,440’ T/10,460’ @ 60-65 FPM, HOLE TAKING PROPER FILL.
ROMMEL UNIT 3H | 14 | 2021-08-17 16:30 | 2021-08-17 19:00 | 2.5 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.41 | 11762 | 11762 | 0 | CIRCULATE BOTTOMS UP, INSERT NERF BALL AND CIRCULATE HOLE CLEAN, GPM: 386, SPP: 2100 PSI, MAX GAS: 125u. NOTE: DIVERTED 63 BBLS OF SPACER AND INTERFACE TO THE OPEN TOP.
ROMMEL UNIT 3H | 14 | 2021-08-17 19:00 | 2021-08-17 23:00 | 4 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 12.57 | 11762 | 11762 | 0 | PERFORM FLOW CHECK (NO FLOW), PUMP SLUG, TRIP OUT THE HOLE F/10,460’ T/1,024', HOLE TAKING PROPER FILL.
ROMMEL UNIT 3H | 14 | 2021-08-17 23:00 | 2021-08-17 23:30 | 0.5 | P | PRDHLCV | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 12.59 | 11762 | 11762 | 0 | FLOW CHECK (WELL STATIC), REMOVE ROTATING HEAD, INSTALL TRIP NIPPLE, RIG UP 2 7/8" HANDLING TOOLS.
ROMMEL UNIT 3H | 14 | 2021-08-17 23:30 | 2021-08-18 01:30 | 2 | P | PRDHLCV | TRIP | LDDP | LAY DOWN DRILLPIPE | 12.68 | 11762 | 11762 | 0 | TRIP OUT THE HOLE AND L/D 2 7/8" TUBING F/1,024', L/D MULE SHOE.
ROMMEL UNIT 3H | 14 | 2021-08-18 01:30 | 2021-08-18 01:45 | 0.25 | P | PRDHLCV | RURD | RDEQP | RIG DOWN EQUIPMENT | 12.69 | 11762 | 11762 | 0 | RIG DOWN 2 7/8" HANDLING TOOLS, CLEAN AND CLEAR RIG FLOOR.
ROMMEL UNIT 3H | 14 | 2021-08-18 01:45 | 2021-08-18 02:45 | 1 | P | PRDHLCV | BOP | TSTBOP | PRESSURE TEST BOP | 12.73 | 11762 | 11762 | 0 | PULL WEAR BUSHING, DRAIN STACK, INSTALL TEST PLUG, FILL STACK FOR BOP TEST, RIG UP BOP TESTER.
ROMMEL UNIT 3H | 14 | 2021-08-18 02:45 | 2021-08-18 06:00 | 3.25 | P | PRDHLCV | BOP | TSTBOP | PRESSURE TEST BOP | 12.86 | 11762 | 11762 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH, STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST.
ROMMEL UNIT 3H | 15 | 2021-08-18 06:00 | 2021-08-18 09:00 | 3 | P | PRDHLCV | BOP | TSTBOP | PRESSURE TEST BOP | 12.99 | 11762 | 11762 | 0 | TEST KILL LINE TO 250 PSI LOW/5,000 PSI HIGH, INSTALL CHECK VALVE AND TEST 250 PSI LOW/10,000 PSI HIGH, TEST VARIABLE RAMS WITH 5 1/2" DP 250 PSI LOW/10,000 PSI HIGH, TEST ANNULAR WITH 5 1/2" DP 250 PSI LOW/3,500 PSI HIGH, TEST ORBIT VALVE 250 PSI LOW/1,500 PSI HIGH; RIG DOWN TESTER
ROMMEL UNIT 3H | 15 | 2021-08-18 09:00 | 2021-08-18 09:30 | 0.5 | P | PRDHLCV | BOP | NU | NIPPLE UP BOP | 13.01 | 11762 | 11762 | 0 | INSTALL WEAR BUSHING; VERIFY CASING VALVE CLOSED; VERIFY STACK AND CHOKE ALIGNMENT
ROMMEL UNIT 3H | 15 | 2021-08-18 09:30 | 2021-08-18 13:45 | 4.25 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.19 | 11762 | 11762 | 0 | M/U 6 3/4" MILL TOOTH ROLLER CONE BIT SER. # LB9928M, CET 43 BOX x 3 1/2 REG BOX BIT SUB W/FLOAT, TIH T/10,127'
ROMMEL UNIT 3H | 15 | 2021-08-18 13:45 | 2021-08-18 14:15 | 0.5 | P | PRDHLCV | WAIT | WOW | WAIT ON WEATHER | 13.21 | 11762 | 11762 | 0 | WAIT ON BAD WEATHER TO CLEAR
ROMMEL UNIT 3H | 15 | 2021-08-18 14:15 | 2021-08-18 15:00 | 0.75 | P | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.24 | 11762 | 11762 | 0 | SERVICE TOP DRIVE, DRAWORKS, ST-80
ROMMEL UNIT 3H | 15 | 2021-08-18 15:00 | 2021-08-18 15:15 | 0.25 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.25 | 11762 | 11762 | 0 | TIH F/10,127' T/10,617'; HOLE GIVING PROPER DISPLACEMENT; WASH DOWN F/10,524' TO 10,617'; TAG CEMENT @ 10,617'
ROMMEL UNIT 3H | 15 | 2021-08-18 15:15 | 2021-08-18 17:45 | 2.5 | P | PRDHLCV | DLOUT | DRLCM | DRILL OUT CEMENT | 13.35 | 11762 | 11762 | 0 | DRILL CEMENT F/10,617' T/11,022'; RPM-50, GPM-400, SPP-2500, WOB-10/15K, TRQ-4/6K STOPPED ROTARY SLOWED DOWN PUMPS AND SET DOWN 12K LBS TO CHECK HARDNESS OF CEMENT. SAMPLES RETURNING TO SURFACE WERE FIRM SAMPLES OF CEMENT.
ROMMEL UNIT 3H | 15 | 2021-08-18 17:45 | 2021-08-18 18:30 | 0.75 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.39 | 11762 | 11762 | 0 | CIRCULATED & CONDITIONED OUT CEMENT WHILE BUILDING SLUG, PUMPED SLUG & PERFORMED FLOW CHECK
ROMMEL UNIT 3H | 15 | 2021-08-18 18:30 | 2021-08-18 22:30 | 4 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.55 | 11762 | 11762 | 0 | TRIPPED OUT F/11,022' - T/BHA PERFORMED FLOW CHECK @ 10,579' & BEFORE WORKING BHA
ROMMEL UNIT 3H | 15 | 2021-08-18 22:30 | 2021-08-18 23:00 | 0.5 | P | PRDHLCV | TRIP | LDBHA | LAY DOWN BIT / BHA | 13.57 | 11762 | 11762 | 0 | BROKE OUT BIT & BIT SUB THEN RACKED BACK STAND OF DRILL PIPE
ROMMEL UNIT 3H | 15 | 2021-08-18 23:00 | 2021-08-19 00:45 | 1.75 | P | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 13.65 | 11762 | 11762 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13628581 JETS 6/18S TFA: 1.491), 5" TS HS88, 6/7L, 8.8 STG @ 2.25°; .68 REV/GAL; 4.05' BIT TO BEND 5.5" PAD OD; FLOW RANGE- 150-400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, FILTER SUB. CROSSOVER, BIT TO SVY-61'. BIT TO GAMMA-57', TEST MWD (TEST GOOD) AND MAKE UP BIT.
ROMMEL UNIT 3H | 15 | 2021-08-19 00:45 | 2021-08-19 01:45 | 1 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.69 | 11762 | 11762 | 0 | TRIPPED IN THE HOLE F/BHA - T/2,007', PROPER DISPLACEMENT, FILL EVERY 30 STDS.
ROMMEL UNIT 3H | 15 | 2021-08-19 01:45 | 2021-08-19 02:45 | 1 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.73 | 11762 | 11762 | 0 | FILL PIPE AND CHANGE OUT ST-80 DIES
ROMMEL UNIT 3H | 15 | 2021-08-19 02:45 | 2021-08-19 06:00 | 3.25 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.86 | 11762 | 11762 | 0 | TRIPPED IN THE HOLE F/2,007' - T/9845', PROPER DISPLACEMENT, FILL EVERY 30 STDS.
ROMMEL UNIT 3H | 16 | 2021-08-19 06:00 | 2021-08-19 06:30 | 0.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.89 | 11022 | 11022 | 0 | TIH F/9845' T/10230', PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 16 | 2021-08-19 06:30 | 2021-08-19 06:45 | 0.25 | P | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 13.9 | 11022 | 11022 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 16 | 2021-08-19 06:45 | 2021-08-19 07:15 | 0.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 13.92 | 11022 | 11022 | 0 | TIH F/10230' T/11022', PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 16 | 2021-08-19 07:15 | 2021-08-19 08:15 | 1 | P | PRDHLCV | WSHRM | RMDIR | WASH / REAM FOR DIRECTIONAL SLIDE | 13.96 | 11022 | 11022 | 0 | FILL PIPE, SYNC MWD AND BUILD TROUGH FOR SIDETRACK AT 90 RIGHT TOOLFACE.
ROMMEL UNIT 3H | 16 | 2021-08-19 08:15 | 2021-08-20 00:30 | 16.25 | P | PRDHLCV | DRLG | DRLST | TIME DRILLING | 14.64 | 11022 | 11041 | 1.2 | TIME DRILL F/11,022' T/11,041'; GPM-275, SPP-2050, WOB-2-5K TIME DRILL AT 1'/HR F/11,022' T/11,032' TF-80R TIME DRILL AT 1.3'/HR F/11,032' T/11,036' TF-80R TIME DRILL AT 2.5'/HR F/11,036' T/11,041' TF-80R LITHOLOGY AT 11,023'- 95% CMT, 5% CHLK LITHOLOGY AT 11,025'- 90% CMT, 10% CHLK LITHOLOGY AT 11,030'- 70% CMT, 30% CHLK LITHOLOGY AT 11,033'- 55% CMT, 45% CHLK LITHOLOGY AT 11,036'- 15% CMT, 85% CHLK LITHOLOGY AT 11,038'- 5% CMT, 95% CHLK LITHOLOGY AT 11,040'- TRACE CMT, 100% CHLK
ROMMEL UNIT 3H | 16 | 2021-08-19 08:15 | 2021-08-19 08:15 | 0 | P | PRDHLCV | MSTN | KOST | MILESTONE_KICK OFF SIDETRACK | 13.96 | 11022 | 11022 |  | MILESTONE_KICK OFF SIDETRACK 8-19-21 @ 08:15
ROMMEL UNIT 3H | 16 | 2021-08-20 00:30 | 2021-08-20 00:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 14.64 | 11041 | 11041 |  | MILESTONE_START CURVE SECTION 8-20-2021 @ 00:30
ROMMEL UNIT 3H | 16 | 2021-08-20 00:30 | 2021-08-20 06:00 | 5.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.86 | 11041 | 11265 | 40.7 | SLIDE DRILL F/11,041' T/11,265' (224' IN 5.5 HRS @ 46.18 FPH) TF-30R/HS; GPM-300, SPP-2700, WOB-10/25K, DIFF-200-600 PSI. NOTE: SURVEY @ 11,110' MD, 11,002.89' TVD', INC: 27.89°, AZM: 151.95°, DLS: 7.48°, HIGH: 45', LEFT: 6'. PROJ TO BIT: 11,171' MD, 11,054.64' TVD, INC: 35.90°, AZM: 152.96, DLS: 13.16°. SLIDE SEEN 88', UNSEEN 61', MTR YIELD 13.1°, DLN TO LAND: 9.3° (CONFIRMED DEPARTURE FROM ORIGINAL WELLBORE) LITHOLOGY AT 11,050'- 100% CHLK LITHOLOGY AT 11,100'- 100% CHLK LITHOLOGY AT 11,150'- 100% CHLK LITHOLOGY AT 11,200'- 100% CHLK
ROMMEL UNIT 3H | 17 | 2021-08-20 06:00 | 2021-08-20 08:00 | 2 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.95 | 11265 | 11265 | 0 | PUMP 20 BBLS HI-VIS SWEEP, CIRCULATE SHAKERS CLEAN.
ROMMEL UNIT 3H | 17 | 2021-08-20 08:00 | 2021-08-20 08:15 | 0.25 | P | PRDHLCV | FLWBK | FLCHK | FLOW CHECK | 14.96 | 11265 | 11265 | 0 | FLOW CHECK, WELL STATIC. PUMP SLUG.
ROMMEL UNIT 3H | 17 | 2021-08-20 08:15 | 2021-08-20 09:45 | 1.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.02 | 11265 | 11265 | 0 | TOOH F/11,265' T/9,484', PROPER FILL ON TRIP TANK. FLOW CHECKED AT CSG SHOE.
ROMMEL UNIT 3H | 17 | 2021-08-20 09:45 | 2021-08-20 10:45 | 1 | P | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.06 | 11265 | 11265 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80
ROMMEL UNIT 3H | 17 | 2021-08-20 10:45 | 2021-08-20 15:00 | 4.25 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.24 | 11265 | 11265 | 0 | TOOH F/9,484' T/BHA, PROPER FILL ON TRIP TANK. FLOW CHECKED AT BHA; REMOVE ROT. HEAD AND INSTALL TRIP NIPPLE @ 3,410'
ROMMEL UNIT 3H | 17 | 2021-08-20 15:00 | 2021-08-20 16:15 | 1.25 | P | PRDHLCV | TRIP | LDBHA | LAY DOWN BIT / BHA | 15.29 | 11265 | 11265 | 0 | L/D DIRECTIONAL BHA; L/D NM DC, REMOVE MWD TOOL, DRAIN MUD MOTOR, BREAK BIT, AND L/D SAME; CLEAN RIG FLOOR
ROMMEL UNIT 3H | 17 | 2021-08-20 16:15 | 2021-08-20 17:15 | 1 | P | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 15.33 | 11265 | 11265 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13618580 JETS 6/18S TFA: 1.49), 5 1/2", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.08' BIT TO BEND; 5.63" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, TOMAX, X/O XT-39 P x CET43 B, 2 STANDS, REAMER. BIT TO SVY-61'. BIT TO GAMMA-57'. TEST MWD (TEST GOOD) AND MAKE UP BIT.
ROMMEL UNIT 3H | 17 | 2021-08-20 17:15 | 2021-08-20 21:45 | 4.5 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.52 | 11265 | 11265 | 0 | TRIP IN HOLE F/BHA T/10,854'. PICK UP AGITATOR ON STAND 26. PSI BEFORE-1048 / PSI AFTER- 1340 AT 211 GPM. HOLE GIVING PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 17 | 2021-08-20 21:45 | 2021-08-20 22:30 | 0.75 | P | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 15.55 | 11265 | 11265 | 0 | CHECK FLOW. REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 17 | 2021-08-20 22:30 | 2021-08-21 | 1.5 | P | PRDHLCV | RIGMT | CUTDL | SLIP / CUT DRL LINE | 15.61 | 11265 | 11265 | 0 | SLIP AND CUT 94' DRILL LINE. CALIBRATE DRAWWORKS.
ROMMEL UNIT 3H | 17 | 2021-08-21 | 2021-08-21 00:15 | 0.25 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.63 | 11265 | 11265 | 0 | TRIP IN HOLE F/10,854' T/11,022'; HOLE GIVING PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 17 | 2021-08-21 00:15 | 2021-08-21 01:00 | 0.75 | P | PRDHLCV | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 15.66 | 11265 | 11265 | 0 | FILL PIPE, CIRCUATE THROUGH GAS BUSTER AND ORIENT TOOLFACE TO HS.
ROMMEL UNIT 3H | 17 | 2021-08-21 01:00 | 2021-08-21 01:15 | 0.25 | P | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 15.67 | 11265 | 11265 | 0 | TRIP IN HOLE F/11,022' T/11,265'; HOLE GIVING PROPER DISPLACEMENT.
ROMMEL UNIT 3H | 17 | 2021-08-21 01:15 | 2021-08-21 03:30 | 2.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.76 | 11265 | 11407 | 63.1 | BUILD CURVE-SLIDE (142' IN 2.33 HR @ 60.86 FPH) WOB-20/25K, SPM-73/73, GPM-380, MRPM-258, SPP-4250-4800 PSI, DIFF-400/600 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/11295' T/11309' 14' TF-HS 0149-0218 SLD F/11324' T/11403' 79' TF-HS 0245-0355 SLD F/11423' T/11472' 49' TF-HS 0420-0501
ROMMEL UNIT 3H | 17 | 2021-08-21 03:30 | 2021-08-21 06:00 | 2.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.86 | 11407 | 11555 | 59.2 | BUILD CURVE-ROTATE (148' IN 2.42 HR @ 61.24 FPH) WOB-15/20K, SPM-73/73, GPM-380, MRPM-258, SPP-4250-4800 PSI, DIFF-400/600 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI.
ROMMEL UNIT 3H | 18 | 2021-08-21 06:00 | 2021-08-21 08:15 | 2.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 15.96 | 11555 | 11744 | 84 | BUILD CURVE-SLIDE (189' IN 2.20 HR @ 85.91 FPH) WOB-20/25K, SPM-73/73, GPM-380, MRPM-258, SPP-4250-4800 PSI, DIFF-400/600 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/11560' T/11592' 32' TF-HS 0608-0635 SLD F/11644' T/11687' 43' TF-HS 0702-0732 SLD F/11690' T/11804' 114' TF-HS 0745-0900
ROMMEL UNIT 3H | 18 | 2021-08-21 08:15 | 2021-08-21 09:00 | 0.75 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 15.99 | 11744 | 11804 | 80 | BUILD CURVE-ROTATE (60' IN .80 HR @ 75 FPH) WOB-15/20K, SPM-73/73, GPM-380, MRPM-258, SPP-4250-4800 PSI, DIFF-400/600 PSI, CHOKES- 100% / 100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP= 0 PSI.
ROMMEL UNIT 3H | 18 | 2021-08-21 09:00 | 2021-08-21 09:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 15.99 | 11804 | 11804 |  | MILESTONE_LAND/END CURVE SECTION 8/21/2021 AT 09:00 (11,804' MD / 11,314' TVD)
ROMMEL UNIT 3H | 18 | 2021-08-21 09:00 | 2021-08-21 11:30 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.09 | 11804 | 12092 | 115.2 | ROTATE DRLD LATERAL (288' IN 2.47 HR @ 116.60 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 50-80, TQ 7-10K, MRPM-258, SPP-4500/5200 PSI, DIFF-700/1000 PSI, CHOKES- 0% -100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 59 PSI, AVG CASING PRESSURE= 42 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 42
ROMMEL UNIT 3H | 18 | 2021-08-21 11:30 | 2021-08-21 12:45 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.15 | 12092 | 12163 | 56.8 | SLD DRLD LATERAL (71' IN 1.28 HRS @ 55.47 FPH) WOB-25/35K, SPM-73/73, GPM-380, MRPM-258, SPP-4000-4500 PSI, DIFF-300/600 PSI, CHOKES- 0% -100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 59 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 42 PSI. SLIDE DEPTHS: SLD F/11,876' T/11,891' 15' TF-180 0950-1005 SLD F/11,978' T/11,993' 15' TF- 150L 1035-1054 SLD F/12,074' T/12,094' 20' TF-150L 1125-1143 SLD F/12,124' T/12,145' 21' TF- 180 1158-1223
ROMMEL UNIT 3H | 18 | 2021-08-21 12:45 | 2021-08-21 13:00 | 0.25 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 16.16 | 12163 | 12163 | 0 | CIRCULATE AND RECIPROCATE WHILE DISCUSS PLAN WITH GEO
ROMMEL UNIT 3H | 18 | 2021-08-21 13:00 | 2021-08-22 01:00 | 12 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.66 | 12163 | 13689 | 127.2 | ROTATE DRLD LATERAL (1526' IN 11.93 HR @ 127.91 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 50-80, TQ 7-10K, MRPM-258, SPP-4500/5200 PSI, DIFF-700/1000 PSI, CHOKES- 0% -50, FLARE-3-10', NO MUD CUT, MAX CASING PRESSURE= 59 PSI, AVG CASING PRESSURE= 42 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 150
ROMMEL UNIT 3H | 18 | 2021-08-22 01:00 | 2021-08-22 04:15 | 3.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 16.79 | 13689 | 13859 | 52.3 | SLD DRLD LATERAL (170' IN 3.22 HRS @ 52.80 FPH) WOB-25/35K, SPM-73/73, GPM-380, MRPM-258, SPP-4000-4500 PSI, DIFF-300/600 PSI, CHOKES- 0% -100%, FLARE-3-10', NO MUD CUT, MAX CASING PRESSURE= 59 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 150 PSI. SLIDE DEPTHS: SLD F/12,163' T/12,173' 10' TF-180 1306-1322 SLD F/12,272' T/12,287' 15' TF-HS 1356-1416 SLD F/12,350' T/12,362' 12' TF-HS 1450-1502 SLD F/12,543' T/12,553' 10' TF-HS 1617-1628 SLD F/12,928' T/12,940' 12' TF- 80R 1924-1937 SLD F/13,021' T/13,033' 12' TF-80R 2014-2026 SLD F/13,106' T/13,124' 12' TF- 70R 2103-2118 SLD F/13,175' T/13,187' 12' TF- 120R 2145-2203 SLD F/13,269' T/13,281' 12' TF-170R 2248-2303 SLD F/13,385' T/13,400' 15' TF-180 0005-0020 SLD F/13,486' T/13,504' 18' TF-180 0058-0117 SLD F/13,601' T/13,609' 8' TF-HS 0159-0209 SLD F/13,778' T/13,794' 16' TF-30R 0329-0346
ROMMEL UNIT 3H | 18 | 2021-08-22 04:15 | 2021-08-22 05:15 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 16.83 | 13859 | 13859 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80
ROMMEL UNIT 3H | 18 | 2021-08-22 05:15 | 2021-08-22 06:00 | 0.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 16.86 | 13859 | 13952 | 124 | ROTATE DRLD LATERAL (93' IN .75 HR @ 124 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 50-80, TQ 7-10K, MRPM-258, SPP-4500/5200 PSI, DIFF-700/1000 PSI, CHOKES- 0% -50, FLARE-3-10', NO MUD CUT, MAX CASING PRESSURE= 197 PSI, AVG CASING PRESSURE= 164 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 163
ROMMEL UNIT 3H | 19 | 2021-08-22 06:00 | 2021-08-23 01:30 | 19.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 17.68 | 13952 | 16279 | 119.3 | ROTATE DRLD LATERAL (2,327' IN 19.62 HR @ 118.62 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 80, TQ 7-15K, MRPM-258, SPP-4700/5700 PSI, DIFF-800/1000 PSI, CHOKES- 0% -74%, FLARE-3-10', .1 PPG MUD CUT, MAX CASING PRESSURE= 420 PSI, AVG CASING PRESSURE= 75 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 180 NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 19 | 2021-08-23 01:30 | 2021-08-23 04:30 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 17.8 | 16279 | 16410 | 43.7 | SLD DRLD LATERAL (131' IN 2.88 HRS @ 45.43 FPH) WOB-25/45K, SPM-73/73, GPM-380, MRPM-258, SPP-4700-5100 PSI, DIFF-300/400 PSI SLIDE DEPTHS: SLD F/13952' T/13967' 15' TF-130R 612-638 SLD F/14248' T/14263' 15' TF-150R 835-857 SLD F/14810' T/14830' 20' TF-180 1300-1328 SLD F/14997' T/15007' 10' TF-180 1439-1454 SLD F/15382' T/15400' 18' TF-180 1805-1823 SLD F/15478' T/15498' 20' TF-180 1929-1951 SLD F/15951' T/15969' 18' TF-180 2353-0025 SLD F/16049' T/16064' 15' TF-180 0109-0119
ROMMEL UNIT 3H | 19 | 2021-08-23 04:30 | 2021-08-23 05:15 | 0.75 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 17.83 | 16410 | 16410 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80
ROMMEL UNIT 3H | 19 | 2021-08-23 05:15 | 2021-08-23 05:30 | 0.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 17.84 | 16410 | 16435 | 100 | ROTATE DRLD LATERAL (25' IN .25 HR @ 75.76 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 80, TQ 7-15K, MRPM-258, SPP-4700/5700 PSI, DIFF-800/1000 PSI, CHOKES- 0% -74%, FLARE-3-10', .1 PPG MUD CUT, MAX CASING PRESSURE= 420 PSI, AVG CASING PRESSURE= 75 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 180 NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 19 | 2021-08-23 05:30 | 2021-08-23 06:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 17.86 | 16435 | 16450 | 30 | SLD DRLD LATERAL (15' IN .42 HRS @ 35.71 FPH) WOB-45K, SPM-73/73, GPM-380, MRPM-258, SPP-4700-5100 PSI, DIFF-300/400 PSI SLIDE DEPTHS: SLD F/16417' T/16432' 15' TF-180 0524-0549
ROMMEL UNIT 3H | 20 | 2021-08-23 06:00 | 2021-08-23 14:15 | 8.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 18.21 | 16450 | 17202 | 91.2 | ROTATE DRLD LATERAL (752' IN 8.28 HR @ 91 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 80, TQ 7-15K, MRPM-258, SPP-4700/5700 PSI, DIFF-800/1000 PSI, CHOKES- 0% -64%, FLARE-3-10', .1 PPG MUD CUT, MAX CASING PRESSURE= 420 PSI, AVG CASING PRESSURE= 75 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 200 NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 20 | 2021-08-23 14:15 | 2021-08-23 16:30 | 2.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 18.3 | 17202 | 17257 | 24.4 | SLD DRLD LATERAL (55' IN 2.22 HRS @ 25 FPH) WOB-45K, SPM-73/73, GPM-380, MRPM-258, SPP-4700-5100 PSI, DIFF-300/400 PSI SLIDE DEPTHS: SLD F/16602' T/16612' 10' TF-180 735-802 SLD F/16792' T/16807' 15' TF-180 958-1026 SLD F/16887' T/16902' 15' TF-HS 1119-1204 SLD F/17178' T/17193' 15' TF-90L 1505-1538
ROMMEL UNIT 3H | 20 | 2021-08-23 16:30 | 2021-08-23 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 18.32 | 17257 | 17257 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS. SERVICED CATWALK WHILE DRLG
ROMMEL UNIT 3H | 20 | 2021-08-23 17:00 | 2021-08-24 02:00 | 9 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 18.7 | 17257 | 17860 | 67 | ROTATE DRLD LATERAL (603' IN 9.07 HR @ 66.48 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 80, TQ 12-20K, MRPM-258, SPP-4900/5750 PSI, DIFF-850 PSI, CHOKES- 0% -90%, FLARE-3-6', .1 PPG MUD CUT, MAX CASING PRESSURE= 40 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 100 NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 20 | 2021-08-24 02:00 | 2021-08-24 06:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 18.86 | 17860 | 17928 | 17 | SLD DRLD LATERAL (68' IN 3.93 HRS @ 17.30 FPH) WOB-45K, SPM-73/73, GPM-380, MRPM-258, SPP-4700-5100 PSI, DIFF-300/400 PSI SLIDE DEPTHS: SLD F/17273' T/17288' 15' TF-60L 1718-1800 SLD F/17465' T/17480' 15' TF-180 2033-2119 SLD F/17558' T/17578' 20' TF-180 2228-2328 SLD F/17838' T/17853' 15' TF-130L 0318-0404 SLD F/17925' T/17928' 3' TF-160L 0518-0600
ROMMEL UNIT 3H | 21 | 2021-08-24 06:00 | 2021-08-24 06:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 18.89 | 17928 | 17936 | 16 | SLD DRLD LATERAL (8' IN .43 HRS @ 18.46 FPH) WOB-20K, SPM-73/73, GPM-380, MRPM-258, SPP-5250 PSI, DIFF-300 PSI SLIDE DEPTH: SLD F/17928' T/17936' 8' TF-160L 0600-0626
ROMMEL UNIT 3H | 21 | 2021-08-24 06:30 | 2021-08-24 07:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 18.91 | 17936 | 17945 | 18 | ROTATE DRLD LATERAL (9' IN .57 HR @ 15.88 FPH) WOB-25/35K, SPM-73/73, GPM-380, RPM 80, TQ 15-22K, MRPM-258, SPP-4900/5750 PSI, DIFF-850 PSI, CHOKES- 0% -90%, FLARE-3-6', .1 PPG MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 100
ROMMEL UNIT 3H | 21 | 2021-08-24 07:00 | 2021-08-24 10:45 | 3.75 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 19.06 | 17945 | 17945 | 0 | RACK BACK KELLY STD. PUMPED 2 X 30 BBL OBM SWEEP, CIRCULATED SHAKERS CLEAN, SPM-72/72, GPM-375, MRPM-255, RPM-80, TRQ-9/10K, SPP-4800 PSI. CHOKES 0% - 90%. MAX CASING PRESSURE WHILE CIRC- 0 PSI.
ROMMEL UNIT 3H | 21 | 2021-08-24 10:45 | 2021-08-24 14:00 | 3.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.2 | 17945 | 17945 | 0 | STRIP OUT THE HOLE PULLING ON ELEVATORS F/17,945’ T/11,114’ PUMPING 10.5 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI.
ROMMEL UNIT 3H | 21 | 2021-08-24 14:00 | 2021-08-24 15:15 | 1.25 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 19.25 | 17945 | 17945 | 0 | CIRCULATE BTM'S UP 100' OUTSIDE SHOE @ 11,114' GPM-345, SPP-3300 PSI; CP-0 PSI, NO FLARE; MAX GAS-1,337U
ROMMEL UNIT 3H | 21 | 2021-08-24 15:15 | 2021-08-24 15:30 | 0.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.26 | 17945 | 17945 | 0 | STRIP OUT THE HOLE ABOVE TOP OF CURVE F/11,114’ T/10,580’ PUMPING 10.5 PPG MUD CALCULATED FILL DOWN THE ANNULUS.
ROMMEL UNIT 3H | 21 | 2021-08-24 15:30 | 2021-08-24 16:00 | 0.5 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 19.28 | 17945 | 17945 | 0 | MONITOR CASING PSI, SICP BUILT TO 120 PSI; PUMP 52 BBLS OF 17.5 PPG KILL MUD AND CHASE WITH 113 BBLS OF 10.5 PPG OBM; BOTTOM OF MUD CAP @ 10,580', TOP OF MUD CAP @ 9,422' AFTER PULLING DP OUT OF MUD CAP.
ROMMEL UNIT 3H | 21 | 2021-08-24 16:00 | 2021-08-24 16:30 | 0.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.3 | 17945 | 17945 | 0 | STRIP OUT THE HOLE F/10,580’ T/9,380’ PUMPING 10.5 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 318 PSI AND FINAL CASING PRESSURE= 215 PSI.
ROMMEL UNIT 3H | 21 | 2021-08-24 16:30 | 2021-08-24 18:00 | 1.5 | P | PRDHLLT | WCTRL | WCTRL | WELL CONTROL OPERATIONS | 19.36 | 17945 | 17945 | 0 | SHUT IN AND MONITOR CASING PSI; CASING PSI 218; CIRCULATE BTM'S UP; SHUT IN WELL AND AND MONITOR CASING PSI FOR 10 MIN; CASING PSI 0; OPEN UP WELL AND MONITOR FLOW ON TRIP TANK THROUGH GAS SEPARATOR; WELL FLOWING 5 SEC/QT INITIALLY, FLOW INCREASED TO 1.5 SEC/QT; SHUT IN WELL
ROMMEL UNIT 3H | 21 | 2021-08-24 18:00 | 2021-08-24 19:45 | 1.75 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.44 | 17945 | 17945 | 0 | STRIP OUT OF HOLE F/9,380' T/8,506' PUMPING 1.9 BBLS/STD OF 17.5 PPG KILL MUD DOWN BACKSIDE; MONITOR FLOW ON TRIP TANK THROUGH GAS SEPARATOR; WELL STILL FLOWING 10 SEC/QT; CONTINUE STRIP OUT OF HOLE F/8,506' T/7,558' PUMPING 1.9 BBLS/STD OF 17.5 PPG KILL MUD DOWN BACKSIDE
ROMMEL UNIT 3H | 21 | 2021-08-24 19:45 | 2021-08-24 20:00 | 0.25 | P | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 19.45 | 17945 | 17945 | 0 | PERFORM FLOW CHECK THROUGH GAS SEPARATOR AND THEN DOWN FLOWLINE - NO FLOW.
ROMMEL UNIT 3H | 21 | 2021-08-24 20:00 | 2021-08-24 20:45 | 0.75 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.48 | 17945 | 17945 | 0 | POOH F/7,558' T/6,141'. HOLE TOOK PROPER FILL ON TRIP OUT.
ROMMEL UNIT 3H | 21 | 2021-08-24 20:45 | 2021-08-24 21:15 | 0.5 | P | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 19.5 | 17945 | 17945 | 0 | FLOW CHECK, WELL STATIC. PUMP SLUG
ROMMEL UNIT 3H | 21 | 2021-08-24 21:15 | 2021-08-24 22:30 | 1.25 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.55 | 17945 | 17945 | 0 | POOH F/6,141' T/2,866'. HOLE TOOK PROPER FILL ON TRIP OUT.
ROMMEL UNIT 3H | 21 | 2021-08-24 22:30 | 2021-08-24 23:00 | 0.5 | P | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 19.57 | 17945 | 17945 | 0 | FLOW CHECK, WELL STATIC. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
ROMMEL UNIT 3H | 21 | 2021-08-24 23:00 | 2021-08-25 | 1 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.61 | 17945 | 17945 | 0 | POOH F/2,866' T/DIRECTIONAL BHA. HOLE TOOK PROPER FILL ON TRIP OUT.
ROMMEL UNIT 3H | 21 | 2021-08-25 | 2021-08-25 01:00 | 1 | P | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 19.66 | 17945 | 17945 | 0 | PICK UP PUP JOINT AND 1 JOINT OF DP, SCREW INTO TOP OF TOMAX AND RACK BACK WITH TOP MONEL. DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR. MOTOR DRAINED WHEN SET BACK ON ROTARY, DRY WHEN DRAINED WITH ROTARY TABLE, HAD MINIMAL SLACK, AND NO BEARING NOISE. BIT HAD ONE JET PLUGGED & NO CUTTER WEAR, BIT GRADED 0-0-NO-A-X-0-PN-BHA
ROMMEL UNIT 3H | 21 | 2021-08-25 01:00 | 2021-08-25 02:30 | 1.5 | P | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 19.72 | 17945 | 17945 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13618580 JETS 6/18S TFA: 1.49), 5 1/2", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.06' BIT TO BEND; 5.62" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5.25" NMDC, 5" NMPDC, 5.25" NMDC, TOMAX, X/O XT-39 P x CET43 B, 2 STANDS, REAMER. BIT TO SVY-61'. BIT TO GAMMA-57'. TEST MWD (TEST GOOD) AND MAKE UP BIT.
ROMMEL UNIT 3H | 21 | 2021-08-25 02:30 | 2021-08-25 03:00 | 0.5 | P | PRDHLLT | FLWBK | FLCHK | FLOW CHECK | 19.74 | 17945 | 17945 | 0 | FLOW CHECK PRIOR TO TIH. CLEAN AND CLEAR RIG FLOOR, REMOVE OLD ROTATING HEAD FROM FLOOR AND SET ASIDE NEW ROTATING HEAD.
ROMMEL UNIT 3H | 21 | 2021-08-25 03:00 | 2021-08-25 05:30 | 2.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.84 | 17945 | 17945 | 0 | TRIP IN HOLE F/BHA T/5931'. PICK UP AGITATOR ON STAND 26. PSI BEFORE-1170 / PSI AFTER- 1370 AT 210 GPM. PROPER DISPLACEMENT WHILE TRIPPING IN.
ROMMEL UNIT 3H | 21 | 2021-08-25 05:30 | 2021-08-25 06:00 | 0.5 | P | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 19.86 | 17945 | 17945 | 0 | FLOW CHECK, WELL STATIC. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 22 | 2021-08-25 06:00 | 2021-08-25 06:30 | 0.5 | P | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 19.89 | 17945 | 17945 | 0 | STRIP NEW ROTATING HEAD ON STAND AND INSTALL SAME.
ROMMEL UNIT 3H | 22 | 2021-08-25 06:30 | 2021-08-25 09:00 | 2.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 19.99 | 17945 | 17945 | 0 | STRIP IN THE HOLE F/5931' T/11084' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 290; FINAL CSG PSI 0
ROMMEL UNIT 3H | 22 | 2021-08-25 09:00 | 2021-08-25 10:30 | 1.5 | P | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 20.05 | 17945 | 17945 | 0 | SLIP AND CUT 60' DRILL LINE. CALIBRATE DRAWWORKS.
ROMMEL UNIT 3H | 22 | 2021-08-25 10:30 | 2021-08-25 11:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 20.07 | 17945 | 17945 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80
ROMMEL UNIT 3H | 22 | 2021-08-25 11:00 | 2021-08-25 14:30 | 3.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 20.22 | 17945 | 17945 | 0 | ATTEMPT TO CIRCULATE MUD CAP OUT OF HOLE; BRING PUMPS ONLINE @ 10 SPM AND STAGE UP TO 20 SPM; SPP INCREASED TO 3,500 PSI WITH NO RETURNS, #1 CHOKE OPEN 20%; BLEED PSI OFF OF STANDPIPE AT 2"; VERIFY SURFACE EQUIPMENT WAS FULLY OPEN AND HAD NO BLOCKAGE; CHECKED VALVES FROM MUD PUMP TO TOP DRIVE AT SURFACE AND CHECK VALVES FROM STACK TO CHOKE TO TANKS AT SURFACE; ALL LINES CLEAR; ATTEMPT TO CIRCULATE FOR THE SECOND TIME AND SPP INCREASED TO 4,000 PSI WITH NO RETURNS; CASING PSI NEVER INCREASED TO INDICATE COMMUNICATION; DECISION WAS MADE TO PULL OUT OF HOLE AND ATTEMPT TO FIND OBSTRUCTION IN DRILLSTRING; TRANSFER 10.5 PPG MUD OUT OF TANK #8, TRANSFER KILL MUD INTO TANK #8 AND WEIGHT UP FROM 15.0 PPG TO 17.5 PPG
ROMMEL UNIT 3H | 22 | 2021-08-25 14:30 | 2021-08-25 16:45 | 2.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 20.31 | 17945 | 17945 | 0 | STRIP OUT OF HOLE F/11,084' T/8,039' PUMPING CALCULATED FILL DOWN THE ANNULUS (BACKSIDE) W/17.5 PPG KILL MUD; FLOW CHECK WELL @ 8,972' (WELL STILL FLOWING), FLOW CHECK WELL @ 8,039' (WELL STATIC)
ROMMEL UNIT 3H | 22 | 2021-08-25 16:45 | 2021-08-26 01:15 | 8.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 20.67 | 17945 | 17945 | 0 | STRIP OUT OF THE HOLE F/8,039' T/BHA, PUMPING CALCULATED FILL DOWN THE ANNULUS (BACKSIDE) W/10.5 PPG OBM. ATTEMPTED TO CIRCULATE THROUGH DRILL STRING AT BOTH TOP & BTTM AGITATORS WITH NO SUCCESS.
ROMMEL UNIT 3H | 22 | 2021-08-26 01:15 | 2021-08-26 03:30 | 2.25 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 20.76 | 17945 | 17945 | 0 | LD TOMAX AND ATTEMPT TO CIRCULATE THROUGH BHA, NO SUCCESS. LD NMDC AND PULL MWD TOOL, WHEN MWD PULLED OUT OF UBHO SLEEVE MUD IN MONEL FELL OUT. PULLED MOTOR AND BIT THROUGH ROTARY, MUD DRAINED THROUGH BIT JETS. MOTOR DRAINED GOOD IN ROTARY, NORMAL SQUAT, NO BEARING NOISE. BIT GRADED 0-0. LD MOTOR AND BTI VALVE, CHECKED FLOAT IN MOTOR (OK). BTI VALVE HAD CUTTINGS IN IT. BROKE OUT UBHO AND INSPECT SLEEVE, UBHO SLEEVE WAS PACKED WITH CUTTINGS. PULL UBHO SLEEVE AND FLUSH THROUGH UBHO.
ROMMEL UNIT 3H | 22 | 2021-08-26 03:30 | 2021-08-26 06:00 | 2.5 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 20.86 | 17945 | 17945 | 0 | PICK UP NEW MTR 5 1/2", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.06' BIT TO BEND; 5.62" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2240 PSI; STALL TRQ-8014 FT/LBS; NEW BTI VALVE, 5" NMPDC, 5 1/4" UBHO (INSTALLED NEW SLEEVE), 5.25" NMDC, 5" NMPDC, NEW 5.25" NMDC (CHANGED OUT DUE TO WASH ON FACE), TOMAX, X/O XT-39 P x CET43 B, 2 STANDS, REAMER. BIT TO SVY-61'. BIT TO GAMMA-57'. CHANGED OUT MWD, TEST SAME (TEST GOOD) MAKE UP BIT. 6.75" SECURITY GTD64M SER 13618580 JETS 6/18'S TFA: 1.49 (RE-RUN)
ROMMEL UNIT 3H | 23 | 2021-08-26 06:00 | 2021-08-26 11:30 | 5.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.09 | 17945 | 17945 | 0 | TRIP IN HOLE F/BHA T/5931'. PICK UP AGITATOR ON STAND 26 (2,798'). PSI BEFORE-1175 / PSI AFTER- 1730 AT 280 GPM. PICK UP ON DEMAND AGITATOR AT 5,935'. PSI BEFORE-2660 / PSI AFTER-2855 AT 280 GPM. PROPER DISPLACEMENT WHILE TRIPPING IN. RABBIT DRILL PIPE IN MOUSEHOLE. FILL AND BREAK CIRCULATION EVERY 30 STDS.
ROMMEL UNIT 3H | 23 | 2021-08-26 11:30 | 2021-08-26 12:00 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 21.11 | 17945 | 17945 | 0 | FLOW CHECK, WELL STATIC. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD.
ROMMEL UNIT 3H | 23 | 2021-08-26 12:00 | 2021-08-26 16:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.28 | 17945 | 17945 | 0 | TRIP IN THE HOLE F/5,931' T/11,061'; HOLE GIVING PROPER DISPLACEMENT; CAPTURED APPROXIMATELY 30 BBLS OF KILL MUD THAT WAS PREVIOUSLY PUMPED ON THE BACKSIDE IN TRIP TANK. RABBIT DRILL PIPE IN MOUSEHOLE. FILL AND BREAK CIRCULATION EVERY 30 STDS.
ROMMEL UNIT 3H | 23 | 2021-08-26 16:00 | 2021-08-26 16:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 21.3 | 17945 | 17945 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS; CIRCULATE MUD CAP OUT DURING RIG SERVICE
ROMMEL UNIT 3H | 23 | 2021-08-26 16:30 | 2021-08-26 18:00 | 1.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 21.36 | 17945 | 17945 | 0 | CIRULATE OUT MUD CAP; STAGE PUMPS UP FROM 10 SPM TO 70 SPM; FINAL CIRCULATING GPM-183, SPP-1600, MAX CASING PSI-550, FLARE 10-15'; CAPTURED APPROXIMATELY 40 BBLS OF MUD CAP IN TRIP TANK; MAX MUD WT. 14 PPG;
ROMMEL UNIT 3H | 23 | 2021-08-26 18:00 | 2021-08-26 20:45 | 2.75 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.48 | 17945 | 17945 | 0 | STRIP IN THE HOLE F/11061' T/13232' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 100; FINAL CSG PSI 175. FILL AND BREAK CIRCULATION EVERY 30 STDS.
ROMMEL UNIT 3H | 23 | 2021-08-26 20:45 | 2021-08-26 21:15 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 21.5 | 17945 | 17945 | 0 | RIG SERVICE, REPAIR HYDRAULIC HOSE ON HPU
ROMMEL UNIT 3H | 23 | 2021-08-26 21:15 | 2021-08-26 23:30 | 2.25 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 21.59 | 17945 | 17945 | 0 | CIRCULATE AND CONDITION MUD. CUT MUD WT F/11.2 PPG T/10.7 PPG. GPM-240 SPP-2200; INITIAL CSG PSI-178, FINAL CSG PSI-0. MAX GAS- 3133U, FLARE-6-10'
ROMMEL UNIT 3H | 23 | 2021-08-26 23:30 | 2021-08-27 02:00 | 2.5 | P | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 21.7 | 17945 | 17945 | 0 | STRIP IN THE HOLE F/13232'' T/17766' BLEEDING OFF CALCULATED DISPLACEMENT 1.9 BBLS PER STAND; INITIAL CSG PSI 0; FINAL CSG PSI 297. FILL AND BREAK CIRCULATION EVERY 30 STDS.
ROMMEL UNIT 3H | 23 | 2021-08-27 02:00 | 2021-08-27 02:30 | 0.5 | P | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 21.72 | 17945 | 17945 | 0 | WASHED & REAMED F/17,766' - T/17,857' WOB-0/5K, RPM-50, TRQ-8/9K, SPM-60/60, GPM-300, MRPM-225, TRPM-275, SPP-4250 PSI, CP-120 PSI, FLARE-2/5', CHOKE POSITION-1 CLOSED & 2 @ 75%
ROMMEL UNIT 3H | 23 | 2021-08-27 02:30 | 2021-08-27 02:45 | 0.25 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 21.73 | 17945 | 17945 | 0 | CYCLE PUMPS FOR MWD. MWD PULSING BUT NOT SYNCING, CHANGE SETTING ON SURFACE EQUIPMENT TO .6 PULSE WIDTH AND RECYCLE PUMPS.
ROMMEL UNIT 3H | 23 | 2021-08-27 02:45 | 2021-08-27 03:00 | 0.25 | P | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 21.74 | 17945 | 17945 | 0 | WASHED & REAMED F/17,857' - T/17,945' WOB-0/5K, RPM-50, TRQ-8/9K, SPM-60/60, GPM-300, MRPM-225, TRPM-275, SPP-4250 PSI, CP-120 PSI, FLARE-2/5', CHOKE POSITION-1 CLOSED & 2 @ 75%
ROMMEL UNIT 3H | 23 | 2021-08-27 03:00 | 2021-08-27 05:30 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 21.84 | 17945 | 18127 | 72.8 | ROT(182' IN 2.57 HRS @ 70.91 FPH) WOB-15/25K, SPM-67/67, GPM-350, RPM 80, TQ 9-12K, MRPM-238, SPP-5400/6100 PSI, DIFF-600/700 PSI, CHOKES- 100% / 70%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 95 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 132 PSI, MUD WT 10.7 PPG
ROMMEL UNIT 3H | 23 | 2021-08-27 05:30 | 2021-08-27 06:00 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 21.86 | 18127 | 18145 | 36 | SLD (18' IN .43 HR @ 41.54 FPH) WOB-15/25K, SPM-64/64, GPM-335, MRPM-228, SPP-4950/5250 PSI, DIFF-300 PSI, CHOKES- 0% /70% SLIDE DEPTH: SLD F/18059' T/18077' 18' TF-180 0444-0510
ROMMEL UNIT 3H | 24 | 2021-08-27 06:00 | 2021-08-27 14:30 | 8.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 22.22 | 18145 | 19123 | 115.1 | ROT(978' IN 8.5 HRS @ 115.06 FPH) WOB-15/35K, SPM-67/67, GPM-350, RPM 80, TQ 9-12K, MRPM-238, SPP-5400/6100 PSI, DIFF-600/800 PSI, CHOKES- 0% / 70%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 50 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1911 PSI, MUD WT 10.6 PPG NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 24 | 2021-08-27 14:30 | 2021-08-27 16:30 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 22.3 | 19123 | 19183 | 30 | SLD (60' IN 2 HR @ 30 FPH) WOB-15/25K, SPM-67/67, GPM-350, MRPM-238, SPP-5200/5500 PSI, DIFF-300 PSI, CHOKES- 0% /70% SLIDE DEPTH: SLD F/18242' T/18257' 15' TF-130L 650-714 SLD F/18536' T/18548' 12' TF-HS 946-1007 SLD F/18722' T/18732' 10' TF-HS 1130-1155 SLD F/18910' T/18918' 8' TF-30R 1313-1334 SLD F/19006' T/19021' 15' TF-180 1416-1445
ROMMEL UNIT 3H | 24 | 2021-08-27 16:30 | 2021-08-27 17:30 | 1 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 22.34 | 19183 | 19183 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS
ROMMEL UNIT 3H | 24 | 2021-08-27 17:30 | 2021-08-28 03:00 | 9.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 22.74 | 19183 | 20137 | 100.4 | ROT(954' IN 9.45 HRS @ 101 FPH) WOB-15/25K, SPM-64/64, GPM-330, RPM 70, TQ 10-15K, MRPM-224, SPP-4400/5100 PSI, DIFF-600/800 PSI, CHOKES- 0% / 70%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 55 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 126 PSI, MUD WT 10.5 PPG NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 24 | 2021-08-28 03:00 | 2021-08-28 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 22.86 | 20137 | 20222 | 28.3 | SLD (85' IN 3.05 HR @ 27.87 FPH) WOB-15/25K, SPM-64/64, GPM-330, MRPM-224, SPP-4400/4700 PSI, DIFF-300 PSI, CHOKES- 0% /70% SLIDE DEPTH: SLD F/19193' T/19202' 12' TF-140L 1735-1807 SLD F/19285' T/19300' 15' TF-HS 1840-1910 SLD F/19570' T/19588' 18' TF-160L 2145-2224 SLD F/19673' T/19693' 20' TF- 160L 2314-2354 SLD F/19761' T/19776' 15' TF-180 0037-0100 SLD F/19865' T/19873' 8' TF-180 0150-0209
ROMMEL UNIT 3H | 25 | 2021-08-28 06:00 | 2021-08-28 09:30 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 23.01 | 20222 | 20514 | 83.4 | ROT(292' IN 3.5 HRS @ 101 FPH) WOB-15/25K, SPM-64/64, GPM-330, RPM 70, TQ 10-15K, MRPM-224, SPP-4400/5100 PSI, DIFF-600/800 PSI, CHOKES- 0% / 70%, FLARE-2'-6', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 100 PSI, MUD WT 10.5 PPG NOTE: PUMPING 10 BBLS 12.5 PPB LCM SWEEP EVERY 300' ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT
ROMMEL UNIT 3H | 25 | 2021-08-28 09:30 | 2021-08-28 09:30 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 23.01 | 20514 | 20514 |  | MILESTONE_TD WELL ON 8/28/2021 @ 9:30
ROMMEL UNIT 3H | 25 | 2021-08-28 09:30 | 2021-08-28 13:15 | 3.75 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 23.17 | 20514 | 20514 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN, PUMPING 3 TANDEM 30 BBL HIGH VIS SWEEPS. CIRCULATE SHAKERS CLEAN, RPM-80, SPM: 75/75, GPM-390, INITIAL SPP-6000 PSI/FINAL SPP-5800, CHOKES- 0% / 75%, FLARE-0'-6', MAX CASING PRESSURE=0 PSI, MAX GAS: 1625u. 1ST BTM UP START TQ=11K, END= 10K, P/U WT=280K, S/O=165K 2ND BTM UP END TQ=10K, P/U WT=275K, S/O WT=170K 3RD BTM UP END TQ=10K, P/U WT=265K, S/O WT=175K
ROMMEL UNIT 3H | 25 | 2021-08-28 13:15 | 2021-08-28 15:30 | 2.25 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 23.26 | 20514 | 20514 | 0 | ATTEMPT TO POOH ON ELEVATORS WITH NO SUCCESS; BACKREAM OUT OF HOLE F/20,514' T/18,745', RPM-80, 16/18K, SPP-2800 PSI
ROMMEL UNIT 3H | 25 | 2021-08-28 15:30 | 2021-08-28 19:15 | 3.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 23.42 | 20514 | 20514 | 0 | STRIP OUT THE HOLE ON ELEVATORS F/18,745'’ T/11,061’, PUMPING 1.9 BBLS/STD OF 10.5 PPG MUD CALCULATED FILL DOWN THE ANNULUS. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 74 PSI. NOTE: PUMPED 12 BBL 17.0 PPG SLUG AND BLED BACK CALCULATED 7.4 BBLS FOR SLUG DROP
ROMMEL UNIT 3H | 25 | 2021-08-28 19:15 | 2021-08-28 20:30 | 1.25 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 23.47 | 20514 | 20514 | 0 | CIRCULATE BTM'S UP 47' OUTSIDE SHOE @ 11,061' GPM-315, SPP-3300 PSI; CP-332 PSI, 3' FLARE; MAX GAS-1962U
ROMMEL UNIT 3H | 25 | 2021-08-28 20:30 | 2021-08-28 22:15 | 1.75 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 23.54 | 20514 | 20514 | 0 | MONITOR CASING PSI, SICP BUILT TO 553 PSI; PUMP 114 BBLS OF 17.0 PPG KILL MUD AND CHASE WITH 99 BBLS OF 10.5 PPG OBM; BOTTOM OF MUD CAP @ 11,061', TOP OF MUD CAP @ 8,572' AFTER PULLING DP OUT OF MUD CAP.
ROMMEL UNIT 3H | 25 | 2021-08-28 22:15 | 2021-08-29 | 1.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 23.61 | 20514 | 20514 | 0 | STRIP OUT THE HOLE F/11,061’ T/8,508’ PUMPING CALCULATED FILL DOWN THE ANNULUS WITH 17.0 PPG MUD, TOTAL 19 BBLS PUMPED. INITIAL CASING PREESURE= 52 PSI AND FINAL CASING PRESSURE= 349 PSI.
ROMMEL UNIT 3H | 25 | 2021-08-29 | 2021-08-29 00:15 | 0.25 | P | PRDHLCSG | FLWBK | FLCHK | FLOW CHECK | 23.63 | 20514 | 20514 | 0 | FLOW CHECK, WELL FLOWING 4 SEC/QUART 5.6 BBLS/HR. SHUT WELL IN, NO CSG PSI OBSERVED.
ROMMEL UNIT 3H | 25 | 2021-08-29 00:15 | 2021-08-29 00:45 | 0.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 23.65 | 20514 | 20514 | 0 | STRIP OUT THE HOLE F/8,508’ T/7,546’ PUMPING CALCULATED FILL DOWN THE ANNULUS WITH 17.0 PPG MUD. TOTAL OF 8 BBLS PUMPED. INITIAL CASING PREESURE= 0 PSI AND FINAL CASING PRESSURE= 0 PSI.
ROMMEL UNIT 3H | 25 | 2021-08-29 00:45 | 2021-08-29 01:00 | 0.25 | P | PRDHLCSG | FLWBK | FLCHK | FLOW CHECK | 23.66 | 20514 | 20514 | 0 | FLOW CHECK, WELL STATIC.
ROMMEL UNIT 3H | 25 | 2021-08-29 01:00 | 2021-08-29 01:30 | 0.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 23.68 | 20514 | 20514 | 0 | POOH F/7,546' T/6,883'. WET PUMPING CALCULATED FILL DOWN THE ANNULUS WITH 17.0 PPG MUD, 22 BBLS PUMPED.
ROMMEL UNIT 3H | 25 | 2021-08-29 01:30 | 2021-08-29 01:45 | 0.25 | P | PRDHLCSG | FLWBK | FLCHK | FLOW CHECK | 23.69 | 20514 | 20514 | 0 | FLOW CHECK, WELL STATIC.
ROMMEL UNIT 3H | 25 | 2021-08-29 01:45 | 2021-08-29 02:30 | 0.75 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 23.72 | 20514 | 20514 | 0 | PUMP 19 BBL SLUG, POOH F/6,883' T/6,044'' PROPER FILL WITH TRIP TANK.
ROMMEL UNIT 3H | 25 | 2021-08-29 02:30 | 2021-08-29 03:00 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 23.74 | 20514 | 20514 | 0 | FLOW CHECK, WELL STATIC. REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE. LD AGITATOR.
ROMMEL UNIT 3H | 25 | 2021-08-29 03:00 | 2021-08-29 05:00 | 2 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 23.82 | 20514 | 20514 | 0 | POOH F/6,044' T/DIRECTIONAL BHA. HOLE TOOK 15 BBLS MORE THAN CALCULATED FILL ON TRIP OUT. LD BTTM AGITATOR AT 2800' AND REAMER AT 338'
ROMMEL UNIT 3H | 25 | 2021-08-29 05:00 | 2021-08-29 06:00 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 23.86 | 20514 | 20514 | 0 | LD X/O, TOMAX TOOL & TOP NMDC. PULL MWD, DRAIN MOTOR, BREAK BIT AND LD REMAINING BHA.
ROMMEL UNIT 3H | 26 | 2021-08-29 06:00 | 2021-08-29 06:45 | 0.75 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 23.9 | 20514 | 20514 | 0 | CONT LD BHA. MOTOR IN GOOD CONDITION, BEARING GAP WITHIN TOLERANCE, MOTOR DRAINED STRONG. BIT GRADED 0-0.
ROMMEL UNIT 3H | 26 | 2021-08-29 06:45 | 2021-08-29 07:30 | 0.75 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 23.93 | 20514 | 20514 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, REMOVE 4 1/2" ELAVATORS
ROMMEL UNIT 3H | 26 | 2021-08-29 07:30 | 2021-08-29 09:00 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 23.99 | 20514 | 20514 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT.
ROMMEL UNIT 3H | 26 | 2021-08-29 09:00 | 2021-08-29 09:45 | 0.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.02 | 20514 | 20514 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING
ROMMEL UNIT 3H | 26 | 2021-08-29 09:45 | 2021-08-29 10:30 | 0.75 | U | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.05 | 20514 | 20514 | 0 | TROUBLE SHOOT TORQ TURN. C/O LOAD CELL SENSOR AND CABLE, C/O COMPUTER AND GROUND SAME.
ROMMEL UNIT 3H | 26 | 2021-08-29 10:30 | 2021-08-29 15:30 | 5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.26 | 20514 | 20514 | 0 | MAKE UP GEODYNAMIC TOE SLEEVE, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING, MU CRT AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/5480', FILLING PIPE ON THE FLY; HOLE STARTED GIVING IMPROPER DISPLACEMENT
ROMMEL UNIT 3H | 26 | 2021-08-29 15:30 | 2021-08-29 16:00 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 24.28 | 20514 | 20514 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD
ROMMEL UNIT 3H | 26 | 2021-08-29 16:00 | 2021-08-29 19:30 | 3.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.43 | 20514 | 20514 | 0 | STRIP IN HOLE F/5480' T/9807' BLEEDING OFF CALCULATED 1 BBL/JT THROUGH CHOKE TO TRIP TANK
ROMMEL UNIT 3H | 26 | 2021-08-29 19:30 | 2021-08-29 21:00 | 1.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 24.49 | 20514 | 20514 | 0 | CIRCULATE OUT MUD CAP @ 9807'', SLOWLY STAGE PUMPS UP: 76 SPM, 196 GPM, , SPP: 1200 PSI, MAX GAS: 546u. FINAL SICP= 0 PSI. RECOVERED 47 BBLS MAX WT 14.0 PPG IN TRIP TANK
ROMMEL UNIT 3H | 26 | 2021-08-29 21:00 | 2021-08-29 21:15 | 0.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.5 | 20514 | 20514 | 0 | CONT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/9807' T/10,106' FILLING PIPE ON THE FLY, BLEEDING OFF CALCULATED 1 BBL/JT THROUGH CHOKE TO TRIP TANK
ROMMEL UNIT 3H | 26 | 2021-08-29 21:15 | 2021-08-29 22:00 | 0.75 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 24.53 | 20514 | 20514 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS.
ROMMEL UNIT 3H | 26 | 2021-08-29 22:00 | 2021-08-29 23:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.57 | 20514 | 20514 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/10106' T/11022' WHILE STRIPPING IN WITH CASING PRESSURE= 0 PSI WITH CHOKES: 100% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), FILLING PIPE ON THE FLY.
ROMMEL UNIT 3H | 26 | 2021-08-29 23:00 | 2021-08-30 01:30 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 24.68 | 20514 | 20514 | 0 | CIRCULATE OUT MUD CAP @ 11022' SLOWLY STAGE PUMPS UP: 67 SPM, 175 GPM, SPP:1000 PSI, STARTING CSG PSI=50 PSI, ENDING CSG PSI= 451 PSI WITH CHOKES: 0% / 35%, NO FLARE AND MAX GAS: 830u. NOTE: DIVERTED RETURNS TO TRIP TANK WHEN A 12.5 PPG WAS @ SURFACE, DIVERTED 45 BBLS OF 12.5 PPG T/ 14.0 PPG.
ROMMEL UNIT 3H | 26 | 2021-08-30 01:30 | 2021-08-30 04:00 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.78 | 20514 | 20514 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/11022'' T/13610' WHILE STRIPPING IN WITH CASING PRESSURE= 230 PSI WITH CHOKES: 30% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), MAX CSG PRESSURE= 515 PSI, FILLING PIPE ON THE FLY. NOTE: WASH/REAM F/11,770' T/11,820' (BASE OF CURVE)
ROMMEL UNIT 3H | 26 | 2021-08-30 04:00 | 2021-08-30 04:45 | 0.75 | U | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.81 | 20514 | 20514 | 0 | HYDRAULIC HOSE ON POWER TONGS LEAKING. SHUT UNIT DOWN AND CHANGE OUT POWER TONGS. WORK PIPE WHILE CHANGE OUT TONGS.
ROMMEL UNIT 3H | 26 | 2021-08-30 04:45 | 2021-08-30 06:00 | 1.25 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 24.86 | 20514 | 20514 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/13610'' T/15318' WHILE STRIPPING IN WITH CASING PRESSURE= 450 PSI WITH CHOKES: 38% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), MAX CSG PRESSURE= 802 PSI, FILLING PIPE ON THE FLY. NOTE: WASH/REAM F/11,770' T/11,820' (BASE OF CURVE)
ROMMEL UNIT 3H | 27 | 2021-08-30 06:00 | 2021-08-30 10:00 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 25.03 | 20514 | 20514 | 0 | CONTINUE PICKING UP AND RUNNING 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/15318' T/20503' WHILE STRIPPING IN WITH CASING PRESSURE= 400 PSI WITH CHOKES: 38% / 0%, BLEEDING OFF CALCULATED DISPLACEMENT (1.3 BBLS/JT), MAX CSG PRESSURE= 924 PSI, FILLING PIPE ON THE FLY.
ROMMEL UNIT 3H | 27 | 2021-08-30 10:00 | 2021-08-30 11:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 25.07 | 20514 | 20514 | 0 | SHUT ANNULAR AND REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD. SLACK OFF AND INSTALL ROTATING HEAD. OPEN ANNULAR AND RUN LANDING JOINT F/20,472' T/20,502.7'. LAND CASING ON HANGER W/160K LBS (W/O BLOCKS) RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, RAN 9,986.44' (215 JTS) OF 5'' 18# P-110 ICY WEDGE 425 CASING, 1- X-OVER, 1 JOINT 5.5" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 463 CASING, RAN 10,229.39' (217 JTS) OF 5.5" 23# P-110 ICY WEDGE 463 CASING, 1 – 20’ 5.5” PUP JOINT, 1 JT 5.5” CSG, HANGER AND LANDING JT. FOR TOTAL OF 435 FULL JTS OF 5'' 18# P-110 ICY WEDGE & 5.5" 23# P-110 ICY WEDGE 463. CASING SHOE @ 20,502.7' TOP OF FLOAT COLLAR @ 20,450.6' BOTTOM OF TOE SLEEVE VALVE @ 20,403.6' TOP OF TOE SLEEVE VALVE @ 20,378.5' TOP OF X-OVER @ 10,392' TOP OF MARKER JOINT ABOVE X-OVER @ 10,325.3' 3 JOINTS 5" LEFT OUT- 135.34' 14 JOINTS 5.5" LEFT OUT- 655.48'
ROMMEL UNIT 3H | 27 | 2021-08-30 11:00 | 2021-08-30 12:00 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 25.11 | 20514 | 20514 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 700 PSI.
ROMMEL UNIT 3H | 27 | 2021-08-30 12:00 | 2021-08-30 14:00 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 25.2 | 20514 | 20514 | 0 | SLOWLY STAGE UP PUMPS TO 96 SPM, CIRCULATE 1-1/2 CASING CAPACITY WHILE RIGGING DOWN CASING TOOLS, GPM-252, SPP-2200 PSI, CHOKES: 100% / 100%, AVG CASING PRESSURE= 0 PSI, MAX CASING PRESSURE= 720 PSI, 5’-10’ FLARE AND MAX GAS: 2,400u. MONITOR SICP, SICP= 326 PSI. LOSS 10 BBLS TO THE FORMATION.
ROMMEL UNIT 3H | 27 | 2021-08-30 14:00 | 2021-08-30 18:00 | 4 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 25.36 | 20514 | 20514 | 0 | SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT TRUCK, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI; TRANSFER MUD FROM MUD TANKS TO FRAC TANKS, CEMENTED 5 X 5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 6 BPM 80 BBL 10.5 PPG WEIGHTED SPACER, 311 BBL 13.5 PPG TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, TRANSFRER MUD FROM MUD TANKS TO FRAC TANKS, DISPLACED WITH FIRST 20 BBL OF SUGAR WATER, FOLLOWED BY 379 BBL OF FRESH WATER @ 6 BPM (TOTAL OF 399 BBL DISPLACEMENT). OBSERVED 100% RETURNS, SLOWED PUMP RATE TO 4 BPM PRIOR TO BUMPING PLUG, FINAL LIFT PRESSURE WAS 4520 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 5520 PSI. 0 BBLS OF SPACER BACK TO SURFACE. HELD FOR 5 MIN, BLED BACK 7 BBLS. FLOATS HELD. PLUG DOWN @ 17:30 HRS 8/30/2021. INITIAL SICP-0 PSI, FINAL SICP= 0 PSI. MAX CASING PSI W/ PUMPING CEMENT-220 PSI @ 6 BPM MAX CASING PSI W/ PUMPING DISPLACEMENT- 755 PSI MAX GAS-1888u CALCULATED TOP OF CEMENT- 7,411'
ROMMEL UNIT 3H | 27 | 2021-08-30 18:00 | 2021-08-30 18:30 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 25.39 | 20514 | 20514 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON WHILE MONITORING SICP, INITIAL SICP=0 PSI, FINAL SICP= 0 PSI. NOTE: LEFT FOSV OPEN WHILE MONITORING SICP.
ROMMEL UNIT 3H | 27 | 2021-08-30 18:30 | 2021-08-30 19:00 | 0.5 | P | PRDHLCSG | FLWBK | FLCHK | FLOW CHECK | 25.41 | 20514 | 20514 | 0 | FLOW CHECK BEFORE REMOVING LANDING JT., WELL STATIC
ROMMEL UNIT 3H | 27 | 2021-08-30 19:00 | 2021-08-30 22:00 | 3 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 25.53 | 20514 | 20514 | 0 | REMOVE FOSV AND ROTATING HEAD, LAY DOWN LANDING JOINT. RIG DOWN CSG ELEVATORS AND RIG UP RIG ELEVATORS. RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER. PUMP @ 50 GPM W/450 PSI TO CLEAN THE TOP OF HANGER. WASH THROUGH BOP'S AND CHOKE MANIFOLD. REMOVE WASH OUT TOOL AND PICK UP PACKOFF. INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
ROMMEL UNIT 3H | 27 | 2021-08-30 22:00 | 2021-08-30 23:30 | 1.5 | P | PRDHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 25.59 | 20514 | 20514 | 0 | SLIP N CUT 94' DRILL LINE, RECALIBRATE BLOCK
ROMMEL UNIT 3H | 27 | 2021-08-30 23:30 | 2021-08-31 02:00 | 2.5 | P | PRDHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 25.7 | 20514 | 20514 | 0 | CHANGE TOP DRIVE GRABBER BOX DIES FROM 4.5" TO 5", CHANGE SAVER SUB. CHANGE GRABBER BOX DIES BACK TO 4.5"
ROMMEL UNIT 3H | 27 | 2021-08-31 02:00 | 2021-08-31 03:00 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 25.74 | 20514 | 20514 | 0 | SERVICE TOP DRIVE, CROWN, ST-80, TRAVELING BLOCK AND DRAWORKS
ROMMEL UNIT 3H | 27 | 2021-08-31 03:00 | 2021-08-31 05:00 | 2 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 25.82 | 20514 | 20514 | 0 | INSTALL BOP WRANGLER, REMOVE TURNBUCKLES, FLOWLINE AND FILL UP LINES. BACK OUT WH SET SCREWS AND LIFT BOP'S.
ROMMEL UNIT 3H | 27 | 2021-08-31 05:00 | 2021-08-31 06:00 | 1 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 25.86 | 20514 | 20514 | 0 | INSTALL WELLHEAD CAP AND TESTED T/5000 PSI.
ROMMEL UNIT 3H | 27 | 2021-08-31 06:00 | 2021-08-31 06:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 25.86 | 20514 | 20514 |  | MILESTONE_RIG RELEASED 8/31/21 @06:00
ROMMEL UNIT 3H | 27 | 2021-08-31 06:00 | 2021-08-31 06:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 25.86 | 20514 | 20514 |  | MILESTONE_WELL RELEASED 8/31/21 @ 06:00.
SABINE B 2H | 2 | 2021-01-14 08:00 | 2021-01-14 09:30 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 105 | 105 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK FROM SABINE A 1H TO SABINE B 2H, CENTERED AND LEVELED SUB OVER CONDUCTOR.
SABINE B 2H | 2 | 2021-01-14 08:00 | 2021-01-14 08:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 105 | 105 |  | MILESTONE_MOB/DEMOB ON 1/14/2021 @ 08:00
SABINE B 2H | 2 | 2021-01-14 09:30 | 2021-01-14 10:30 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | RIG UP CELLAR PUMPS AND LINES, RISER ON CONDUCTOR PIPE
SABINE B 2H | 2 | 2021-01-14 10:30 | 2021-01-14 11:30 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 105 | 105 | 0 | PICK UP BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 7-3/4", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 105'.
SABINE B 2H | 2 | 2021-01-14 11:30 | 2021-01-14 16:30 | 5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.21 | 105 | 2153 | 409.6 | ROTATE (2048' IN 5.05 HRS @ 405 FPH) WOB-20/35K, RPM-100, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2900 PSI, DIFF-700/900 PSI. DUMPING 100 BBLS EVERY 300' AND PUMPING 30 BBLS SOAP/SAPP SWEEP EVERY 300'. DROPPING 1 SOAP & SAPP STICKS EVERY STAND.
SABINE B 2H | 2 | 2021-01-14 11:30 | 2021-01-14 11:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 105 | 105 |  | MILESTONE_SPUD WELL ON 01/14/2021 @ 11:30
SABINE B 2H | 2 | 2021-01-14 16:30 | 2021-01-14 17:30 | 1 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.25 | 2153 | 2485 | 332 | SLIDE (332' IN .95 HRS @ 350 FPH) WOB: 10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP- 2000/2200 PSI, DIFF- 100/200 PSI. SLIDE DEPTHS: SLIDE F/500-t/528,TF-10mag,28' F/1243-T/1248 SLIDE F/600-T/628,TF-10MAG,28',F/1300-T/1305,5MIN SLIDE F/700-T/728,TF-5MAG,28',F/1315-T/1318,3 MIN SLIDE F/800-T/828,TF-HS,28',F/1331-T/1335,4 MIN SLIDE F/900-T/930,TF-HS,30',F/1346-T/1351,5IN SLIDE F/1000-T/1030,TF-HS,30',F/1401-T/1405,4 MIN SLIDE F/1100-T/1136,TF-10R,36',F/1415-T/1420,5 MIN 1.00 SLIDE F/1200-T/1234,TF-10R,34, F/1429-T/1434,5 MIN SLIDE F/1290-T/1326,TF-HS,36' F/1443-T/1448,5 MIN SLIDE F/1730-T/1742,TF-10L,12' F/1533-T/1536,3 MIN SLIDE F/2092-T/2107,TF-10L,15' F/1622-T/1626,4 MIN SLIDE F/2189-T/2204,TF-HS,,15' F/1640-T/1645 SLIDE F/2469-T/2481,TF-90R 12',F/1746-T/1750 4 MIN
SABINE B 2H | 2 | 2021-01-14 17:30 | 2021-01-14 18:30 | 1 | P | SFHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.29 | 2485 | 2485 | 0 | SLOW DOWN PUMPS DUE TO EXCESSIVE GUMBO. CELLAR PUMPS STOPPING UP. USE PRESSURE WASHERS AND SOAP TO BREAK UP GUMBO.
SABINE B 2H | 2 | 2021-01-14 18:30 | 2021-01-14 19:30 | 1 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.33 | 2485 | 2904 | 419 | ROT/SLD (419' IN 1 HRS @ 419 FPH) WOB-20/35K, RPM-100, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2900 PSI, DIFF-700/900 PSI. DUMPING 100 BBLS EVERY 300' AND PUMPING 30 BBLS SOAP/SAPP SWEEP EVERY 300'. DROPPING 1 SOAP & SAPP STICKS EVERY STAND. SLD F/2658 T/2673'; TF-90R, 15', MIN-7, 1905-1912
SABINE B 2H | 2 | 2021-01-14 19:30 | 2021-01-14 20:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.38 | 2904 | 2904 | 0 | PUMP 3-30 BBL SOAP/SAPP SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-662, RPM-100, TRQ-1/2K, SPP-1300 PSI.
SABINE B 2H | 2 | 2021-01-14 20:30 | 2021-01-14 21:30 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.42 | 2904 | 2904 | 0 | TRIP OUT OF HOLE F/2,920' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
SABINE B 2H | 2 | 2021-01-14 21:30 | 2021-01-14 22:30 | 1 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.46 | 2904 | 2904 | 0 | RACK BACK 3 STDS OF HWDP, L/D TOP MONEL, REMOVE MWD TOOL, M/U PUP JOINT ON TOP OF BHA, DRAIN MOTOR, BREAK BIT, AND L/D MOTOR.
SABINE B 2H | 2 | 2021-01-14 22:30 | 2021-01-15 00:30 | 2 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.54 | 2904 | 2904 | 0 | HOLD PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT-BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS. REMOVE CASING CONDUCTOR AND INSTALL CASING GUIDE TOOL ON CONDUCTOR.
SABINE B 2H | 2 | 2021-01-15 00:30 | 2021-01-15 04:00 | 3.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.69 | 2904 | 2904 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# P-110 IC BT&C CASING, FLOAT COLLAR, 1 JT. 10 3/4" 45.5# P-110 IC BT&C CASING, TEST FLOATS (TEST GOOD), THEN RUN 67 JOINTS (70 TOTAL) OF 10 3/4" 45.5# P-110 IC T/2,893.82', RAN 36 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY OTHER JT. ALL THE WAY TO 118.25', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. PICKED UP 5' AND INSTALLED WH VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET 113K (W/O BLOCKS) ON BASE PLATE. SHOE: 2,893.82' TOP OF FLOAT COLLAR: 2,808.90'
SABINE B 2H | 2 | 2021-01-15 04:00 | 2021-01-15 05:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.73 | 2904 | 2904 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOLS, GPM-353, SPP-100/200 PSI. NO LOSSES.
SABINE B 2H | 2 | 2021-01-15 05:00 | 2021-01-15 06:00 | 1 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.77 | 2904 | 2904 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, AND RIG DOWN CELLAR PUMPS.
SABINE B 2H | 3 | 2021-01-15 06:00 | 2021-01-15 09:00 | 3 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.77 | 2904 | 2904 | 0 | PREP RIG TO WALK AND WALK RIG F/SABINE B 2H T/SABINE C 3H. INSTALL CELLAR COVERS. RIG UP STREAMFLO PUP JOINT AND CEMENT HEAD. R/U CELLAR PUMP FOR CEMENT.
SABINE B 2H | 2 | 2021-01-15 06:00 | 2021-01-15 06:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.77 | 2904 | 2904 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 1/15/2021 @ 06:00
SABINE B 2H | 3 | 2021-01-15 09:00 | 2021-01-15 11:30 | 2.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.77 | 2904 | 2904 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 30 BBL 8.3 PPG FRESH WATER SPACER, 314 BBLS 11.6 PPG LEAD CEMENT, 84 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 270 BBLS OF 9.2 PPG OIL BASE MUD. BUMPED PLUG W/700 PSI PRESSURED UP T/1200 PSI (500 PSI OVER) @ 3 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. CIRCULATE BACK TO SURFACE 30 BBLS OF SPACER AND 180 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS
SABINE B 2H | 3 | 2021-01-15 11:30 | 2021-01-15 12:00 | 0.5 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.77 | 2904 | 2904 | 0 | PRESSURE TESTED 10-3/4" 45.5# P-110 IC BTC CASING TO 1500 PSI FOR 20 MIN-GOOD
SABINE B 2H | 3 | 2021-01-15 12:00 | 2021-01-15 12:30 | 0.5 | R | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 0.77 | 2904 | 2904 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
SABINE B 2H | 4 | 2021-01-29 06:00 | 2021-01-29 07:30 | 1.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.83 | 2904 | 2904 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK FROM SABINE A 1H TO SABINE B 2H, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
SABINE B 2H | 4 | 2021-01-29 07:30 | 2021-01-29 09:00 | 1.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.9 | 2904 | 2904 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, RIG UP KILL LINE AND FLOW LINE.
SABINE B 2H | 4 | 2021-01-29 07:30 | 2021-01-29 07:30 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.83 | 2904 | 2904 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 01/29/2021 @ 06:00
SABINE B 2H | 4 | 2021-01-29 09:00 | 2021-01-29 09:30 | 0.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.92 | 2904 | 2904 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, UPPER PIPE RAMS, KILL LINE 250 PSI LOW AND 5000 PSI HIGH. RIG DOWN TESTERS.
SABINE B 2H | 4 | 2021-01-29 09:30 | 2021-01-29 10:00 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 0.94 | 2904 | 2904 | 0 | INSTALL WEAR BUSHING, INSTALL MOUSE HOLE AND TRIP NIPPLE.
SABINE B 2H | 4 | 2021-01-29 10:00 | 2021-01-29 12:30 | 2.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.04 | 2904 | 2904 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S-6/13S TFA: 1.491) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.72' BIT TO BEND; 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, COUGAR THRUSTER; 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SENSOR-70', GAMMA-60'. TEST MWD ( GOOD TEST).
SABINE B 2H | 4 | 2021-01-29 12:30 | 2021-01-29 14:30 | 2 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.13 | 2904 | 2904 | 0 | TRIP IN HOLE T/2,804'. PICKED UP AGITATOR AFTER STAND 22, PSI BEFORE- 650 PSI, PSI AFTER- 800 PSI @ 321 GPM, REMOVE TRIP NIPPLE / INSTALL ROTATING HEAD. PERFORM BOP DRILL PRIOR TO DRILL OUT OPERATIONS, RESPONSE TIME= 60 SECONDS.
SABINE B 2H | 4 | 2021-01-29 14:30 | 2021-01-29 15:30 | 1 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 1.17 | 2904 | 2914 | 10 | TAGGED FLOAT COLLAR @ 2,804', DRILL SHOE TRACK AND 10' NEW FORMATION F/2,904' T/2,914', GPM-421, SPP-1200/1300 PSI, RPM-35, DIFF- 100-200 PSI.
SABINE B 2H | 4 | 2021-01-29 15:30 | 2021-01-29 16:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.19 | 2914 | 2914 | 0 | CIRCULATE BOTTOMS UP GPM-421, SPP-1200 PSI, RPM-35, FILL GAS BUSTER.
SABINE B 2H | 4 | 2021-01-29 16:00 | 2021-01-29 16:30 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.21 | 2914 | 2914 | 0 | PERFORM F.I.T.WITH 9.2 PPG MUD, 352 PSI SURFACE PRESSURE FOR 11.6 PPG EMW, SHOE MD-2,894' / TVD-2,822', PRESSURE BLED OFF T/330 PSI IN 2 MINUTES, PRESSURE STABILZED @ 330 PSI. NOTE: PASON CASING PRESSURE SENSOR NOT WORKING.
SABINE B 2H | 4 | 2021-01-29 16:30 | 2021-01-30 03:30 | 11 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.67 | 2914 | 6987 | 370.3 | ROT (4073' IN 10.85 HRS @ 375 FPH) WOB: 30/40K, SPM: 93/93,/93 GPM: 900, MMRPM: 150, RPM: 80, TRPM: 230, TRQ: 12K/21K, SPP: 4600/5400 PSI, DIFF: 600/800 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB FIRST RESPONSE, 2.5 PPB NEWPHALT AND 2.5 PPB NEW CARB (MEDIUM).
SABINE B 2H | 4 | 2021-01-30 03:30 | 2021-01-30 06:00 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.77 | 6987 | 7206 | 87.6 | SLIDE (219' IN 2.65 HRS @ 83 FPH) WOB: 30/35K, SPM: 93/93/93, GPM: 900, MMRPM:150, SPP: 4600/5000 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/3073' T/3089' 16' TF-30R 1655-1700 SLD F/3165' T/3185' 20' TF-60R 1715-1725 SLD F/4117' T/4132' 15' TF-160L 2028-2033 SLD F/5250' T/5268' 18' TF-HS 2254-2302 SLD 5915' T/5930' 15' TF-60R 0026-0034 SLD F/6085' T/6100' 15' TF-60R 0057-104 SLD F/6275' T/6295' 20' TF-60R 130-142 SLD F/6460' T/6485' 25' TF-40R 221-250 SLD F/6562' T/6587' 25' TF-30R 305-330 SLD F/6841' T/6866' 25' TF-20R 407-422 SLD F/7028' T/7053' 25' TF-50R 448-515
SABINE B 2H | 5 | 2021-01-30 06:00 | 2021-01-30 12:30 | 6.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.04 | 7206 | 9365 | 332.2 | ROT (2159' IN 6.35 HRS @ 340 FPH) WOB: 35/45K, SPM: 89/89,/89 GPM: 850,MMRPM: 141, RPM: 80, TRPM: 221, TRQ: 18K/23K, SPP: 5600/5800 PSI, DIFF: 900/1100 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB FIRST RESPONSE, 2.5 PPB NEWPHALT AND 2.5 PPB NEW CARB (MEDIUM). NOTE: AT 8,708' REDUCE GPM F/ 900 T/ 850 DUE T/ INCREASE IN PUMP PRESSURE T/ 5900 PSI. NOTE: AT 9,356' DRILLING WITH 2 MUD PUMPS @ 700 GPM WHILE CHANGING SWAB WEAR PLATE GASKETt IN #1 MUD PUMP.
SABINE B 2H | 5 | 2021-01-30 12:30 | 2021-01-30 17:30 | 5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.25 | 9365 | 9647 | 56.4 | SLIDE (282' IN 5.15 HRS @ 54.8 FPH) WOB: 30/35K, SPM: 110/110, GPM: 700, MMRPM:116, SPP: 3800/3900 PSI, DIFF: 300/400 PSI. SLIDE DEPTHS: SLD F/7305 T/7335 30' 20R 33 MINS 0645-0718 SLD F/7492 T/7527 35' HS 50 MINS 0745-0835 SLD F/7586 T/7616 30' HS 40 MINS 0850-0930 SLD F/7770 T/7795 25' HS 30 MINS 0953-1023 SLD F/7869 T/7894 25' HS 30 MINS 1065-1105 SLD F/8052 T/8097 45' HS 35 MINS 1130-1205 SLD F/8249 T/8281 32' HS 45 MINS 1230-1315 SLD F/8992 T/9012 20' 180 15 MINS 1535-1550 SLD F/9090 T/9110 20' 180 15 MINS 1605-1620 SLD F/9378 T/9398 20' 160M 16 MINS 1707-1723
SABINE B 2H | 5 | 2021-01-30 17:30 | 2021-01-30 18:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.27 | 9647 | 9647 | 0 | SERVICE TOP DRIVE AND BLOCK.
SABINE B 2H | 5 | 2021-01-30 18:00 | 2021-01-30 21:00 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.4 | 9647 | 10141 | 164.7 | ROT (494' IN 2.82 HRS @ 175 FPH) WOB: 35/45K, SPM: 89/89,/89 GPM: 850,MMRPM: 141, RPM: 80, TRPM: 221, TRQ: 18K/23K, SPP: 4700/5800 PSI, DIFF: 900/1000 PSI. START INTERMEDIATE CURVE ON 1/30/2021 @ 20:45 (10,112' MD / 9,9,823' TVD) NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB FIRST RESPONSE, 2.5 PPB NEWPHALT AND 2.5 PPB NEW CARB (MEDIUM).
SABINE B 2H | 5 | 2021-01-30 21:00 | 2021-01-31 04:00 | 7 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.69 | 10141 | 10315 | 24.9 | SLIDE (174' IN 7.15 HRS @ 24 FPH) WOB: 25/35K, SPM: 89/89/89, GPM: 850, MMRPM: 141, SPP: 4700/5300 PSI, DIFF: 400/600 PSI. SLIDE DEPTHS: SLD F/9880' T/9895' 15' TF-120M 1920-1947 SLD F/10112' T/10206' 94' TF-330M 2045-0057 SLD F/10250' T/10315' 65' TF-20R 128-358 TD INTERMEDIATE SECTION ON 1/31/2021 @ 10,315' (10,315' MD / 10,026' TVD)
SABINE B 2H | 5 | 2021-01-31 04:00 | 2021-01-31 05:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.75 | 10315 | 10315 | 0 | PUMP 2-30 BBL LCM SWEEPS IN TANDEM AND CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM: 700, RPM: 80, TRQ: 7K/12K, SPP: 3600 PSI. FLOW CHECK-NO FLOW. PUMP SLUG.
SABINE B 2H | 5 | 2021-01-31 05:30 | 2021-01-31 06:00 | 0.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 2.77 | 10315 | 10315 | 0 | PULL OUT THE HOLE LAYING DOWN 5" DRILL PIPE F/10,315' T/10,000', HOLE TAKING PROPER FILL, NO EXCESS DRAG ON TRIP OUT.
SABINE B 2H | 6 | 2021-01-31 06:00 | 2021-01-31 11:30 | 5.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3 | 10315 | 10315 | 0 | PULL OUT THE HOLE LAYING DOWN 5" DRILL PIPE F/10,000' T/2,894', HOLE TAKING PROPER FILL, NO EXCESS DRAG ON TRIP OUT.
SABINE B 2H | 6 | 2021-01-31 11:30 | 2021-01-31 12:00 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 3.02 | 10315 | 10315 | 0 | FLOW CHECK WELL, WELL STATIC, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
SABINE B 2H | 6 | 2021-01-31 12:00 | 2021-01-31 15:30 | 3.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.17 | 10315 | 10315 | 0 | PULL OUT THE HOLE LAYING DOWN 5" DRILL PIPE F/2,894' T/602', LAY DOWN 5" HEAVY WEIGHT DRILL PIPE AND 6.5" DRILL COLLARS, HOLE TAKING PROPER FILL, NO EXCESS DRAG ON TRIP OUT. NOTE: ESTIMATED 39 BBLS ADDITIONAL HOLE FILL ON TRIP OUT.
SABINE B 2H | 6 | 2021-01-31 15:30 | 2021-01-31 17:00 | 1.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.23 | 10315 | 10315 | 0 | REMOVE MWD TOOL, DRAIN MOTOR, BREAK OFF BIT, LAY DOWN DIRECTIONAL BHA.
SABINE B 2H | 6 | 2021-01-31 17:00 | 2021-01-31 17:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.25 | 10315 | 10315 | 0 | RIG SERVICE.
SABINE B 2H | 6 | 2021-01-31 17:30 | 2021-01-31 18:30 | 1 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 3.29 | 10315 | 10315 | 0 | REMOVE WEAR BUSHING, REMOVE VARIABLE BORE RAMS F/ UPPER PIPE RAMS, INSTALL 7.625" CASING RAMS, PRESSURE TEST BONNET SEALS ON UPPER RAMS T/ 1500 PSI.
SABINE B 2H | 6 | 2021-01-31 18:30 | 2021-01-31 19:30 | 1 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.33 | 10315 | 10315 | 0 | RIG UP FRANKS CASING EQUIPMENT.
SABINE B 2H | 6 | 2021-01-31 19:30 | 2021-02-01 04:30 | 9 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.71 | 10315 | 10315 | 0 | HELD PJSM, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 233 JTS AND 3 PUP JOINTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 5 SOLID BODY CENTRALIZERS F/ 10,292.85' T/ 10,114.57' (FREE FLOATING), 42 LATCH ON BOW SPRING CENTRALIZERS @ 10,025.77' AND EVERY 4TH JT UP TO 2,885.17'. P/U LANDING JOINT, LANDED CSG ON CSG MANDREL W/220K (W/O BLOCKS). FLOAT SHOE-10,294.75' TOP OF FLOAT COLLAR-10,203.22' 5 JOINTS LEFT OUT- 216.21'
SABINE B 2H | 6 | 2021-02-01 04:30 | 2021-02-01 05:00 | 0.5 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 3.73 | 10315 | 10315 | 0 | RIG DOWN FRANKS CASING EQUIPMENT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
SABINE B 2H | 6 | 2021-02-01 05:00 | 2021-02-01 06:00 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.77 | 10315 | 10315 | 0 | CIRCULATE BOTTOMS UP W/ RIG PUMPS THROUGH CEMENT HEAD, SPM: 130, 8.0 BPM, SPP: 675 PSI, NO LOSSES.
SABINE B 2H | 7 | 2021-02-01 06:00 | 2021-02-01 06:30 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.79 | 10315 | 10315 | 0 | CONTINUE CIRCULATE BOTTOMS UP THROUGH CMT HEAD W/RIG PUMPS; SPM: 130, 8 BBL/MIN, SPP: 675, NO LOSSES
SABINE B 2H | 7 | 2021-02-01 06:30 | 2021-02-01 10:30 | 4 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.96 | 10315 | 10315 | 0 | HOLD PJSM AND SWAP LINES T/CEMENTERS. CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL10.5 PPG SPACER. 290 BBL 11.8 PPG 840 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 469 BBLS OF 9.0 PPG OIL BASE MUD @ 7 BPM SLOWED PUMP RATE TO 3 BPM, FINAL LIFT PRESSURE WAS 2000 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2700 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 7 BBLS. FLOATS DID NOT HOLD. PLUG DOWN @ 09:10 HRS ON 12/20/2020, GOT BACK 14 BBLS OF SPACER AND 0 BBLS OF LEAD CMT BACK TO SURFACE & HAD FULL RETURNS ENTIRE CEMENTING JOB. TOC @ 677'. NOTE: FLOATS DID NOT HOLD; PRESSURED UP TO 2,700 PSI AND HELD FOR 5 MIN; BLED PRESSURE FOR THE SECOND TIME AND FLOATS DID NOT HOLD; PRESSURE UP TO 3,500 PSI TO TEST CASING (HELD 30 MIN), AFTER BLEEDING PRESSURE OFF FLOATS DID NOT HOLD; PRESSURE UP TO 500 PSI AND CLOSE CMT HEAD, WOC FOR 3 HRS UNTIL 13:00
SABINE B 2H | 7 | 2021-02-01 10:30 | 2021-02-01 11:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 3.98 | 10315 | 10315 | 0 | PRESSURE TESTED CASING TO 3500 PSI, HELD 30 MINUTES. (PRESSURE HELD AND TEST GOOD).
SABINE B 2H | 7 | 2021-02-01 11:00 | 2021-02-01 13:00 | 2 | P | INTHLCSG | CMT | WOC | WAIT ON CEMENT | 4.06 | 10315 | 10315 | 0 | WAIT ON CEMENT DUE T/ FLOAT EQUIPMENT NOT HOLDING. NOTE: REMOVE 5" HANDLING TOOLS F/ RIG FLOOR AND PICKUP 4.5" HANDLING TOOLS.
SABINE B 2H | 7 | 2021-02-01 13:00 | 2021-02-01 13:30 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.08 | 10315 | 10315 | 0 | BLEED OFF PRESSURE AND CHECK FLOAT EQUIPMENT, FLOATS HOLDING, RIG DOWN CIRCULATING LINES AND CEMENT HEAD.
SABINE B 2H | 7 | 2021-02-01 13:30 | 2021-02-01 15:30 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.17 | 10315 | 10315 | 0 | MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAY DOWN SETTING TOOL.
SABINE B 2H | 7 | 2021-02-01 15:30 | 2021-02-01 17:30 | 2 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.25 | 10315 | 10315 | 0 | CHANGE UPPER RAMS F/ 7.625" CASING RAMS T/ 3 1/2" x 5 1/2" VBR's, CHANGE SAVER SUB ON TOP DRIVE T/ DS42 CONNECTION.
SABINE B 2H | 7 | 2021-02-01 17:30 | 2021-02-02 | 6.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.52 | 10315 | 10315 | 0 | BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW /10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 7000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ROTATING HEAD AND ORBIT VALVE TO 1500 PSI. REMOVE TEST PLUG AND RIG DOWN TESTERS.
SABINE B 2H | 7 | 2021-02-02 | 2021-02-02 00:30 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.54 | 10315 | 10315 | 0 | INSTALL WEAR BUSHING; PERFORM ACCUMULATOR DRAW DOWN TEST.
SABINE B 2H | 7 | 2021-02-02 00:30 | 2021-02-02 02:00 | 1.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.6 | 10315 | 10315 | 0 | RIG SERVICE; CLEAN AND ORGANIZE RIG FLOOR
SABINE B 2H | 7 | 2021-02-02 02:00 | 2021-02-02 04:00 | 2 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.69 | 10315 | 10315 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13522000 JETS 6/18S TFA: 1.491), 5", 6/7L, 11.7 STG @ 2.12° SLICK; .89 REV/GAL; 4.14' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,905 PSI; STALL TRQ-7,623 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, COUGAR THRUSTER, X/O XT-39 P x DS 42B, 29 STANDS, AGITATOR, 31 STANDS AND AGITATOR. BIT TO SVY-67'. BIT TO GAMMA-57'. TEST MWD (TEST GOOD)
SABINE B 2H | 7 | 2021-02-02 04:00 | 2021-02-02 06:00 | 2 | U | INTHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 4.77 | 10315 | 10315 | 0 | AFTER TESTING MWD TOOL AND BACKING OUT OF DRILLSTRING W/TOP DRIVE IT WAS DISCOVERED THAT THE DRILL PIPE SCREEN WAS STUCK IN THE DRILL PIPE. REMOVE SCREEN FROM DRILL STRING, LAY DOWN JT OF DRILL PIPE, CHANGE OUT SAVER SUB AND SCREEN. INSPECTED SAVER SUB, DRILL PIPE SCREEN, AND JOINT OF DRILL PIPE; COULD NOT FIND ANY OBVIOUS CAUSE FOR SCREEN GETTING STUCK IN DRILL PIPE. OBSERVED LIP OF SAVER SUB AND FACE OF DRILL PIPE SCREEN HAD SCARRING.
SABINE B 2H | 8 | 2021-02-02 06:00 | 2021-02-02 16:00 | 10 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.19 | 10315 | 10315 | 0 | PICK UP 4.5" DP F/BHA T/2,956'; P/U AGITATOR AFTER STAND 29; BEFORE AGITATOR: GPM 262, 100 SPM, SPP-1100 PSI; AFTER AGITATOR SPP-1270 PSI; PICK UP 4.5" DP F/2,956' T/5,902'; P/U ON DEMAND AGITATOR AFTER STAND 60; BEFORE AGITATOR: GPM 262, 100 SPM, SPP-1,500 PSI; AFTER AGITATOR SPP-1575 PSI; CONTINUE PICKING UP 4.5" DP T/10,096'
SABINE B 2H | 8 | 2021-02-02 16:00 | 2021-02-02 16:30 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 5.21 | 10315 | 10315 | 0 | REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD; PERFORM BOP DRILL; FILL GAS SEPARATOR.
SABINE B 2H | 8 | 2021-02-02 16:30 | 2021-02-02 17:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.23 | 10315 | 10315 | 0 | RIG SERVICE.
SABINE B 2H | 8 | 2021-02-02 17:00 | 2021-02-02 17:30 | 0.5 | P | INTHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 5.25 | 10315 | 10315 | 0 | WASH AND REAM F/ 10,096' T/ 10,203' (FLOAT COLLAR), GPM-194, SPP-1415, RPM-30, TOR-11/13K
SABINE B 2H | 8 | 2021-02-02 17:30 | 2021-02-02 18:30 | 1 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 5.29 | 10315 | 10325 | 10 | TAGGED FLOAT COLLAR @ 10,203', DRILL SHOE TRACK AND 10' NEW FORMATION F/10,315' T/10,325', GPM-195, SPP-1400/1700 PSI, RPM-30, TRPM-204, DIFF- 200-400 PSI.
SABINE B 2H | 8 | 2021-02-02 18:30 | 2021-02-02 19:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.33 | 10325 | 10325 | 0 | CIRCULATE BOTTOMS UP GPM-421, SPP-1200 PSI, RPM-35, FILL GAS BUSTER.
SABINE B 2H | 8 | 2021-02-02 19:30 | 2021-02-02 20:00 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.35 | 10325 | 10325 | 0 | PERFORM F.I.T.WITH 8.7 PPG MUD, 2235 PSI SURFACE PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,294' / TVD-10,005', PRESSURE BLED OFF T/2218 PSI IN 5 MINUTES, PRESSURE STABILZED @ 2218 PSI.
SABINE B 2H | 8 | 2021-02-02 20:00 | 2021-02-02 21:00 | 1 | U | PRDHLCV | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 5.4 | 10325 | 10325 | 0 | ATTEMPTED TO SYNC UP MWD WITH NO SUCCESS, TROUBLE SHOOT ISSUE AND CHANGE OUT MWD TRANSDUCER.
SABINE B 2H | 8 | 2021-02-02 20:00 | 2021-02-02 20:00 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.35 | 10325 | 10325 |  | MILESTONE_START CURVE ON 2/2/2020 @ 20:00 HRS
SABINE B 2H | 8 | 2021-02-02 21:00 | 2021-02-03 04:30 | 7.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.71 | 10325 | 10824 | 66.5 | BUILD CURVE-SLIDE (499' IN 7.43 HRS @ 67 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-356, SPP-3700/4600 PSI, DIFF-500/900 PSI, CHOKES-100% / 100%,FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI. SLIDE DEPTHS: SLD F/10325' T/10383' 58' TF-20R 2100-2315 SLD F/10393' T/10476' 83' TF-20R 2328-0032 SLD F/10490' T/10572' 82' TF-50R 100-135 SLD F/10600' T/10666' 66' TF-10R 146-233 SLD F/10688' T/10761' 73' TF-HS 247-346 SLD F/10780' T/10855' 75' TF-HS 359-437 SLD F/10889' T/10951' 62' TF-60R 452-0600
SABINE B 2H | 8 | 2021-02-03 04:30 | 2021-02-03 06:00 | 1.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.77 | 10824 | 10951 | 84.7 | BUILD CURVE-ROT (127' IN 1.57 HRS @ 81 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-30, MRPM-356, TMRPM-386, TRQ-10/19K, SPP-3700/4700 PSI, DIFF-800/1000 PSI.
SABINE B 2H | 9 | 2021-02-03 06:00 | 2021-02-03 08:00 | 2 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.85 | 10951 | 10975 | 12 | BUILD CURVE-ROT (224' IN 1.74 HRS @ 128.73 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-30, MRPM-356, TMRPM-386, TRQ-10/19K, SPP-3700/4700 PSI, DIFF-800/1000 PSI. NO SWEEPS PUMPS DURING CURVE.
SABINE B 2H | 9 | 2021-02-03 08:00 | 2021-02-03 09:00 | 1 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.9 | 10975 | 11351 | 376 | BUILD CURVE-SLIDE (176' IN 1.25 HRS @ 140.8 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-356, SPP-3700/4100 PSI, DIFF-300/400 PSI. SLIDE DEPTHS: SLD F/11,110' T/11,139' 29' TF-30L 0647-0659 SLD F/11,144' T/11,164' 20' TF-90L 0710-0729 SLD F/11,198' T/11,233' 35' TF-HS 0740-0754 SLD F/11,253' T/11,321' 59' TF-10L 0810-0837 SLD F/11,327' T/11,351' 24' TF-HS 0857-0900
SABINE B 2H | 9 | 2021-02-03 09:00 | 2021-02-03 09:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 5.9 | 11351 | 11351 |  | MILESTONE_LAND/END CURVE SECTION ON 02/03/2021 @ 09:00
SABINE B 2H | 9 | 2021-02-03 09:00 | 2021-02-03 09:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 5.9 | 11351 | 11351 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 02/03/2021 @ 09:00
SABINE B 2H | 9 | 2021-02-03 09:00 | 2021-02-03 15:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.15 | 11351 | 12208 | 142.8 | DRILL LATERAL-ROT (857' IN 5.4 HRS @ 158.70 FPH) WOB-35/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-386, TRQ-10/19K, SPP-4050/5050 PSI, DIFF-800/1000 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE
SABINE B 2H | 9 | 2021-02-03 15:00 | 2021-02-03 17:30 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.25 | 12208 | 12392 | 73.6 | DRILL LATERAL-SLIDE (184' IN 3.1 HRS @ 59.35 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-356, SPP-4050/4250 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLD F/11,351' T/11,371' 20' TF-HS 0900-0919 SLD F/11,400' T/11,415' 15' TF-180 0940-0956 SLD F/11,421' T/11,439' 18' TF-180 1010-1025 SLD F/11,501' T/11,536' 18' TF-180 1045-1119 SLD F/11,618' T/11,638' 20' TF-20R 1155-1217 SLD F/11,801' T/11,821' 20' TF-120R 1314-1332 SLD F/11,895' T/11,917' 22' TF-110R 1358-1422 SLD F/12,184' T/12,200' 16' TF-180 1530-1551 SLD F/12,374' T/12,392' 18' TF-HS 1714-1730
SABINE B 2H | 9 | 2021-02-03 17:30 | 2021-02-03 18:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 6.27 | 12392 | 12392 | 0 | SERVICED TOP DRIVE
SABINE B 2H | 9 | 2021-02-03 18:00 | 2021-02-04 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.52 | 12392 | 13496 | 184 | DRILL LATERAL-ROT (1104' IN 5.78 HRS @ 191 FPH) WOB-30/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/19K, SPP-4050/5250 PSI, DIFF-900/1200 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE
SABINE B 2H | 9 | 2021-02-04 | 2021-02-04 03:30 | 3.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.67 | 13496 | 13614 | 33.7 | DRILL LATERAL-SLIDE (118' IN 3.72 HRS @ 32 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-356, SPP-4050/4250 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLIDE F/12471-T/12487,TF-180,16' F/1804-T/1822,18MIN SLIDE F/12569-T/12581,TF-160L,12' F/1850-T/1909,19MIN SLD F/12764-T/12782,TF-140L,18' F/2000-T/2023,23MIN SLIDE F/12859-T/12879,TF-90L,20' F/2050-T/2114,24MIN SLIDE F/12957-T/12972,TF-50L,15'F/2145-T/2217,32MIN SLIDE F/13150-T/13160,TF-160R,10' F/2309-T/2334, 25MIN SLIDE F/13240-T/13255,TF-160R,15' F/0003-T/0038, 35MIN SLIDE F/13430-T/13442,TF-180,12' F/0138-T/0225, 42MIN
SABINE B 2H | 9 | 2021-02-04 03:30 | 2021-02-04 04:30 | 1 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 6.71 | 13614 | 13614 | 0 | ROTATING HEAD LEAKING FROM BOWL GASKET. PICK UP AND REMOVE ROTATING HEAD, REPLACE BOWL GASKET, AND REPLACE WITH NEW ROTATING HEAD ASSEMBLY.
SABINE B 2H | 9 | 2021-02-04 04:30 | 2021-02-04 05:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.73 | 13614 | 13713 | 198 | DRILL LATERAL-ROT (99' IN .58 HRS @ 170 FPH) WOB-30/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/19K, SPP-4050/5250 PSI, DIFF-900/1200 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE
SABINE B 2H | 9 | 2021-02-04 05:00 | 2021-02-04 06:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.77 | 13713 | 13731 | 18 | DRILL LATERAL-SLIDE (18' IN .92 HRS @ 20 FPH) WOB-35/45K, SPM-76/76, GPM-400, MRPM-356, SPP-4050/4250 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLIDE F/13713-T/13731,TF-HS,18' F/0505-T/0600, 55MIN
SABINE B 2H | 10 | 2021-02-04 06:00 | 2021-02-04 10:00 | 4 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.94 | 13731 | 14326 | 148.7 | DRILL LATERAL-ROT (595' IN 3.90 HRS @ 152.82 FPH) WOB-30/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/19K, SPP-4050/5250 PSI, DIFF-900/1200 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE
SABINE B 2H | 10 | 2021-02-04 10:00 | 2021-02-04 13:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.06 | 14326 | 14380 | 18 | DRILL LATERAL-SLIDE (54' IN 3.1 HRS @ 17 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-356, SPP-4050/4250 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLD F/13908 T/13922 TF-180 14' MIN-31 0720-0751 SLD F/14103 T/14115 TF-20R 12' MIN-43 0852-0935 SLD F/14197 T/14213 TF-160R 16' MIN-41 1008-1049 SLD F/14294 T/14306 TF-140R 12' MIN-71 1125-1236
SABINE B 2H | 10 | 2021-02-04 13:00 | 2021-02-04 13:30 | 0.5 | P | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 7.08 | 14380 | 14380 | 0 | DROPPED AGITATOR DART DOWN DRILL STRING THEN PUMPED INTO PLACE @ 150 GPM W/800 PSI SPP, PRESSURE ROSE TO 1100 PSI AFTER SEATING
SABINE B 2H | 10 | 2021-02-04 13:30 | 2021-02-04 14:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.1 | 14380 | 14380 | 0 | SERVICED TOP DRIVE & CROWN
SABINE B 2H | 10 | 2021-02-04 14:00 | 2021-02-04 17:30 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.25 | 14380 | 14851 | 134.6 | DRILL LATERAL-ROT (471' IN 3.6 HRS @ 130.8 FPH) WOB-30/45K SPM-76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/19K, SPP-4050/5250 PSI, DIFF-900/1200 PSI. SICP-470 PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE INITIAL CASING PSI @ 14,379'-400 PSI. CASING PSI WHILE DRILLING=0-200 PSI CASING PSI DURING CONNECTION=100-550 PSI
SABINE B 2H | 10 | 2021-02-04 17:30 | 2021-02-04 20:00 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.35 | 14851 | 14879 | 11.2 | DRILL LATERAL-SLIDE (28' IN 2.4 HRS @ 11.6 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-356, SPP-4050/4250 PSI, DIFF-100/200 PSI. SICP-480 SLIDE DEPTHS: SLD F/14666 T/14674 TF-20R 8' MIN-27 1615-1642 SLIDE F/14859-T/14881,TF-180,22' F/1803-T/2000
SABINE B 2H | 10 | 2021-02-04 20:00 | 2021-02-04 21:00 | 1 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.4 | 14879 | 14879 | 0 | CIRCULATE OUT GAS. MAX CP-534 FL-2/10' GPM-380, RIG UP MUD BUCKET FOR SHORT TRIP (REPLACE BROKE THREAD UNION ON MUD BUCKET HOSE)
SABINE B 2H | 10 | 2021-02-04 21:00 | 2021-02-04 23:30 | 2.5 | P | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 7.5 | 14879 | 14879 | 0 | BACKREAM OUT OF HOLE T/13,990' DUE TO POOR ROP WHILE SLIDING. PARAMETERS WHILE BACKREAMING: GPM=400, SPP=4200-4400, RPM=50, TQ=13-21K. CASING PSI WHILE BACKREAMING:0-175 PSI CASING PSI DURING CONNECTIONS:500-600 PSI
SABINE B 2H | 10 | 2021-02-04 23:30 | 2021-02-05 00:30 | 1 | P | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 7.54 | 14879 | 14879 | 0 | REAM IN HOLE F/13,990' T/14,879'. GPM=400, SPP=4200/4600, RPM=65, TQ=11/15K CASING PSI WHILE REAMING:0-175 PSI CASING PSI DURING CONNECTIONS:500-600 PSI
SABINE B 2H | 10 | 2021-02-05 00:30 | 2021-02-05 01:30 | 1 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.58 | 14879 | 14953 | 74 | DRILL LATERAL-ROT (74' IN .93 HRS @ 79 FPH) WOB-30/45K SPM-0/76/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/22K, SPP-4600/5600 PSI, DIFF-900/1000 PSI. CASING PSI WHILE DRILLING=0-200 PSI. FLARE=5-10' CASING PSI DURING CONNECTION=500-650 PSI PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE
SABINE B 2H | 10 | 2021-02-05 01:30 | 2021-02-05 06:00 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.77 | 14953 | 14978 | 5.6 | DRILL LATERAL-SLIDE (25' IN 4.57 HRS @ 5.5 FPH) WOB-35/45K SPM-0/76/76, GPM-400, MRPM-356, SPP-4600/4800 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLIDE F/14879-T/14886-TF-180,6' F/0039-T/246,127MIN SLIDE F/14960-T/14978,TF-160R,18' F/342-T/0600
SABINE B 2H | 11 | 2021-02-05 06:00 | 2021-02-05 07:30 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.83 | 14978 | 15044 | 44 | DRILL LATERAL-ROT (66' IN 1.5 HRS @ 44 FPH) WOB-30/45K SPM-76/0/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/19K, SPP-4600/5600 PSI, DIFF-900/1000 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE CASING PSI WHILE DRILLING=0-200 PSI CASING PSI DURING CONNECTION=550/750 PSI
SABINE B 2H | 11 | 2021-02-05 07:30 | 2021-02-05 08:30 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.88 | 15044 | 15050 | 6 | DRILL LATERAL-SLIDE (6' IN 1 HRS @ 6 FPH) WOB-35/45K SPM-76/0/76, GPM-400, MRPM-356, SPP-4600/4800 PSI, DIFF-100/200 PSI. MUD PUMP #2 HAD FLANGE BOLTS BREAK CAUSING CAP & PLUG TO BLOW OFF AND SPILL 10 BBLS OF OBM ONTO GROUND.
SABINE B 2H | 11 | 2021-02-05 08:30 | 2021-02-05 12:00 | 3.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.02 | 15050 | 15050 | 0 | PERFORMED CLEAN UP CYCLE PUMPING 3 - 30 BBL WEIGHTED SWEEPS SURFACE TO SURFACE. SPM-76/0/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/19K, SPP-4600/5200 PSI, CP-0/800 PSI, FLARE-0'/1' INITIAL PARAMETERS: RPM=80, TQ=10-23K, P/U=260K, S/O=165K AFTER 1ST BTM UP: RPM=80, TQ=9-21K, P/U=226K, S/O=170K 2ND BTMS UP: RPM=80, TQ=9-22K, P/U=226K, S/O=170K 3RD BTMS UP: RPM=80, TQ=9-22K, P/U=225K, S/O=171K
SABINE B 2H | 11 | 2021-02-05 12:00 | 2021-02-05 13:30 | 1.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.08 | 15050 | 15128 | 52 | DRILL LATERAL-ROT (78' IN 1.37 HRS @ 56.93 FPH) WOB-30/45K SPM-76/0/76, GPM-400, RPM-80, MRPM-356, TMRPM-436, TRQ-10/22K, SPP-4600/5600 PSI, DIFF-900/1000 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE CASING PSI WHILE DRILLING=0-550 PSI CASING PSI DURING CONNECTION=800/900 PSI
SABINE B 2H | 11 | 2021-02-05 13:30 | 2021-02-05 16:30 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.21 | 15128 | 15142 | 4.7 | DRILL LATERAL-SLIDE (14' IN 3.13 HRS @ 4.24 FPH) WOB-35/45K SPM-0/76/76, GPM-400, MRPM-356, SPP-4600/4800 PSI, DIFF-100/200 PSI. SLIDE F/15050-T/15056,TF-160R, 6' 1200-1250 SLIDE F/15061-T/15065,TF-160R, 4' 1307-1345 SLIDE F/15138-T/15142,TF-150R, 4' 1450-1622 AT 15,142' CASING PSI WHILE DRILLING INCREASED F/0 PSI T/500 PSI AND CASING PSI DURING CONNECTION INCREASED TO 990 PSI
SABINE B 2H | 11 | 2021-02-05 16:30 | 2021-02-05 19:30 | 3 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 8.33 | 15142 | 15142 | 0 | CIRCULATED & CONDITIONED HOLE WHILE WEIGHTING UP F/8.8 PPG TO 9.2 PPG CASING PSI WITH MP'S OFF-800 PSI
SABINE B 2H | 11 | 2021-02-05 19:30 | 2021-02-05 21:30 | 2 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 8.42 | 15142 | 15142 | 0 | CIRCULATED & CONDITIONED HOLE WHILE WEIGHTING UP F/9.2 PPG TO 9.4 PPG. CASING PSI WITH MP'S OFF-550 PSI
SABINE B 2H | 11 | 2021-02-05 21:30 | 2021-02-06 02:30 | 5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.63 | 15142 | 15142 | 0 | WASH AND REAM F/15,138' T/11,500' FOR BHA CHANGE, GPM=400, SPP=4600, RPM=40, TQ-10/21K. CASING PSI WHILE REAMING=0 PSI CASING PSI DURING CONNECTION=400-550 PSI
SABINE B 2H | 11 | 2021-02-06 02:30 | 2021-02-06 03:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.67 | 15142 | 15142 | 0 | CIRCULATE BOTTOMS UP @ 11,500'. GPM=400, PP-4250, RPM=40, TQ=6-8K. CASING PSI WHILE CIRCULATING=0 PSI, FLARE=2-3' CASING PSI AFTER CIRCULATION=400 PSI
SABINE B 2H | 11 | 2021-02-06 03:30 | 2021-02-06 05:00 | 1.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 8.73 | 15142 | 15142 | 0 | WASH F/11,500' T/10,290'. GPM=400, PP=3,800
SABINE B 2H | 11 | 2021-02-06 05:00 | 2021-02-06 06:00 | 1 | U | PRDHLLT | WCTRL |  | KILL WELL | 8.77 | 15142 | 15142 | 0 | SPOT 106 BBLS 16 PPG OBM MUD CAP @ 10,290'. TOP OF MUD CAP AFTER PULLING ABOVE-7,971'. SHUT IN AND MONITORED CASING PRESSURE. SICP BEFORE CAP-400 PSI / AFTER-0 PSI. OPEN CHOKES AND MONITOR ON TRIP TANK.
SABINE B 2H | 12 | 2021-02-06 06:00 | 2021-02-06 07:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.83 | 15142 | 15142 | 0 | TRIP OUT OF HOLE F/10,290' T/6,295' @ 100 FPM WHILE PULLING OUT OF MUD CAP. CONTINUE POOH T/6,295'. HOLE TOOK MORE THAN CALCULATED ON TRIP OUT.
SABINE B 2H | 12 | 2021-02-06 07:30 | 2021-02-06 08:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 8.85 | 15142 | 15142 | 0 | PERFORM FLOW CHECK-NO FLOW. REMOVE ROTATING HEAD, INSTALL TRIP NIPPLE, ANDL/D AGITATOR.
SABINE B 2H | 12 | 2021-02-06 08:00 | 2021-02-06 10:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.94 | 15142 | 15142 | 0 | POOH F/6,295' T/BHA. HOLE TOOK MORE THAN CALCULATED ON TRIP OUT.
SABINE B 2H | 12 | 2021-02-06 10:00 | 2021-02-06 11:30 | 1.5 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9 | 15142 | 15142 | 0 | RACK BACK TOP MONEL, L/D MWD, L/D THRUSTER, DRAIN MOTOR, BREAK BIT AND LAY DOWN MOTOR AND BIT. CLEAN RIG FLOOR HOLE TOOK APPROXIMATELY 52 BBLS MORE THAN CALCULATED ON ENTIRE TRIP OUT F/10,290'
SABINE B 2H | 12 | 2021-02-06 11:30 | 2021-02-06 12:30 | 1 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 9.04 | 15142 | 15142 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13509567 JETS 6/18S TFA: 1.491), 5.5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.09' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPC, 5" NMDC, COUGAR THRUSTER, X/O XT-39 P x DS 42B, 29 STANDS, AGITATOR. BIT TO SVY-70'. BIT TO GAMMA-57'. TEST MWD (TEST GOOD)
SABINE B 2H | 12 | 2021-02-06 12:30 | 2021-02-06 13:00 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.06 | 15142 | 15142 | 0 | TRIPPED INTO THE HOLE F/BHA - T/1124' WITH HOLE DISPLACING PROPER DISPLACEMENT
SABINE B 2H | 12 | 2021-02-06 13:00 | 2021-02-06 13:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.08 | 15142 | 15142 | 0 | SERVICED RIG
SABINE B 2H | 12 | 2021-02-06 13:30 | 2021-02-06 15:00 | 1.5 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 9.15 | 15142 | 15142 | 0 | CUT & SLIPPED 80' OF DRILL LINE
SABINE B 2H | 12 | 2021-02-06 15:00 | 2021-02-06 15:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.17 | 15142 | 15142 | 0 | TRIPPED INTO THE HOLE F/1124' - T/2925' WITH HOLE DISPLACING PROPER DISPLACEMENT
SABINE B 2H | 12 | 2021-02-06 15:30 | 2021-02-06 16:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.21 | 15142 | 15142 | 0 | PICKED UP & TESTED AGITATOR SPM-100, SPP BEFORE-1490 PSI, SPP AFTER-1800
SABINE B 2H | 12 | 2021-02-06 16:30 | 2021-02-06 19:30 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.33 | 15142 | 15142 | 0 | TRIPPED INTO THE HOLE F/2925' T/8,050' WITH HOLE DISPLACING PROPER DISPLACEMENT, INSTALL RCH, TRIP IN HOLE TO 9000' WITH CORRECT DISPLACEMENT
SABINE B 2H | 12 | 2021-02-06 19:30 | 2021-02-06 21:00 | 1.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 9.4 | 15142 | 15142 | 0 | CIRCULATE BOTTOMS UP AT 225 GPM SPP-1600. ON FLOW LINE THEN SWITCH TO GAS BUSTER, FL-0' MAX MW COMING BACK-9.5 PPG MAX GAS=333u MAX CSG PSI=192
SABINE B 2H | 12 | 2021-02-06 21:00 | 2021-02-06 22:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.46 | 15142 | 15142 | 0 | STRIP IN HOLE F/9000' T/12,000', CP-0/200, BLEEDING BACK 0.6 BBLS EACH STAND AT 11,580' HOLE BEGAN DISPLACING LESS THAN CALCULATED. OPEN ORBIT VALVE AND TOOK RETURNS DOWN FLOW LINE. AT 11,580'- 6.2 BBLS LESS THAN CALCULATED AT 12,000'- 0 RETURNS 9.6 BBLS LESS THAN CALCULATED
SABINE B 2H | 12 | 2021-02-06 22:30 | 2021-02-07 01:00 | 2.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.56 | 15142 | 15142 | 0 | CIRCULATE OUT MUD CAP @ 12,000'. HEAVIEST MW SEEN-15.6 PPG. FULL RETURNS MAX GAS=770u MAX CSG PSI=647
SABINE B 2H | 12 | 2021-02-07 01:00 | 2021-02-07 03:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.65 | 15142 | 15142 | 0 | TRIP IN HOLE F/12,000' T/15,013'.
SABINE B 2H | 12 | 2021-02-07 03:00 | 2021-02-07 03:30 | 0.5 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 9.67 | 15142 | 15142 | 0 | WASH AND REAM F/15,013' T/15,142'. GPM=377, PP-4550, RPM=40, TQ=8-12K
SABINE B 2H | 12 | 2021-02-07 03:30 | 2021-02-07 04:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.69 | 15142 | 15168 | 52 | DRILL LATERAL-ROT (26' IN .5 HRS @ 52 FPH) WOB-30/45K SPM-76/0/76, GPM-400, RPM-40, MRPM-272, TMRPM-312, TRQ-10/19K, SPP-4850/5450 PSI, DIFF-500/600 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTION=500-600 PSI
SABINE B 2H | 12 | 2021-02-07 04:00 | 2021-02-07 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.77 | 15168 | 15170 | 1 | DRILL LATERAL-SLIDE (2' IN .5 HRS @ 4 FPH) WOB-35/45K SPM-76/0/76, GPM-400, MRPM-356, SPP-4850/4950 PSI, DIFF-50/100 PSI.
SABINE B 2H | 13 | 2021-02-07 06:00 | 2021-02-07 08:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.85 | 15170 | 15283 | 56.5 | DRILL LATERAL-ROT (113' IN 1.95 HRS @ 57.9 FPH) WOB-30/45K SPM-76/0/76, GPM-400, RPM-40, MRPM-272, TMRPM-312, TRQ-10/19K, SPP-4850/5450 PSI, DIFF-500/600 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTION=500-600 PSI
SABINE B 2H | 13 | 2021-02-07 08:00 | 2021-02-07 17:30 | 9.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.25 | 15283 | 15316 | 3.5 | DRILL LATERAL-SLIDE (33' IN 9.55 HRS @ 3.45 FPH) WOB-35/45K SPM-0/76/76, GPM-400, MRPM-356, SPP-4850/4950 PSI, DIFF-50/100 PSI. PUMPING DRILL BEAD SWEEPS 10 BBLS E/15 MINUTES DURING SLIDE SLIDE DEPTH: SLIDE F/15170-T/15186 TF-180 16' 0600-1045 SLIDE F/15202-T/15212 TF-180 10' 1120-1428 SLIDE F/15309-T/15316 TF-110R 7' 1550-1730
SABINE B 2H | 13 | 2021-02-07 17:30 | 2021-02-07 18:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.27 | 15316 | 15316 | 0 | SERVICED TOP DRIVE
SABINE B 2H | 13 | 2021-02-07 18:00 | 2021-02-07 21:00 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.4 | 15316 | 15662 | 115.3 | DRILL LATERAL-ROT (346' IN 2.8 HRS @ 123 FPH) WOB-20/30K SPM-0/76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-10/21K, SPP-4800/5600 PSI, DIFF-600/800 PSI. PUMPING 10 BBLS 10 PPB LCM SWEEPS EVERY 300' SWEEP CONTENTS: 2.5 PPB MAGNAFIBER, 2.5 PPB NEWCARB, 2.5 PPB NEWPHALT, 2.5 PPB TURBOCHEM FIRST RESPONSE CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTION=400-600 PSI
SABINE B 2H | 13 | 2021-02-07 21:00 | 2021-02-08 06:00 | 9 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.77 | 15662 | 15691 | 3.2 | DRILL LATERAL-SLIDE (29' IN 9.2 HRS @ 3.15 FPH) WOB-15/70K SPM-0/76/76, GPM-400, MRPM-356, SPP-4800/4900 PSI, DIFF-50/100 PSI. PUMPING DRILL BEAD SWEEPS 10 BBLS E/15 MINUTES DURING SLIDE SWEEP CONTENTS: 10 PPB POLYMER BEADS, 2.5 PPB GRAPHITE FINE. SLIDE DEPTH: SLIDE F/15316-15324, TF/110R, 8', F/1800-T/1937,97MIN SLIDE F/15400-T/15405, TF-100R, 18 FT, F/2020-T/2205105MIN SLIDE F/15590-T/15598, TF-20R, 8' F/2327-T/132,125MIN SLIDE F/15683-T/15703, TF-HS, 20' F/215-T/0600
SABINE B 2H | 14 | 2021-02-08 06:00 | 2021-02-08 08:30 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.88 | 15691 | 15696 | 2 | DRILL LATERAL-SLIDE (5' IN 2.5 HRS @ 2 FPH) TF-20R, WOB-35/45K SPM-0/76/76, GPM-400, MRPM-356, SPP-4850/4950 PSI, DIFF-50/100 PSI. PUMPING DRILL BEAD SWEEPS 10 BBLS E/15 MINUTES
SABINE B 2H | 14 | 2021-02-08 08:30 | 2021-02-08 09:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 10.9 | 15696 | 15696 | 0 | CIRCULATED & CONDITIONED HOLE WHILE PREPPING RIG TO PULL OUT AND PICK UP RSS
SABINE B 2H | 14 | 2021-02-08 09:00 | 2021-02-08 11:30 | 2.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11 | 15696 | 15696 | 0 | WASHED & REAMED OUT OF THE HOLE DUE TO NOT BEING ABLE TO STRIP OUT BECAUSE OF OVERPULL F/15,696'-T/13,668' SPM-0/76/76, GPM-400, MRPM-356, SPP-4850
SABINE B 2H | 14 | 2021-02-08 11:30 | 2021-02-08 14:00 | 2.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.1 | 15696 | 15696 | 0 | STRIPPED OUT FILLING ANNULAS WITH CALCULATED FILL F/13,668'-T/11,283' OVERPULL-40/90K, SICP-550/700 PSI
SABINE B 2H | 14 | 2021-02-08 14:00 | 2021-02-08 15:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.15 | 15696 | 15696 | 0 | CIRCULATE BOTTOMS UP @ 11,283' GPM=262, PP-2300, RPM=50, TQ=8/12k CASING PSI WHILE CIRC=0 PSI SHUT IN CSG PSI=475 PSI
SABINE B 2H | 14 | 2021-02-08 15:00 | 2021-02-08 16:30 | 1.5 | U | PRDHLLT | KILL |  | KILL WELL | 11.21 | 15696 | 15696 | 0 | SPOTTED MUD CAP @ 11,283' MD, 10,614 TVD PUMPED 115 BBLS OF 16 PPG OBM TO 1853 STKS CHASED KILL MUD WITH 10 PPG OBM TO 1630 STKS PUMPED @ 262 GPM W/2300 PSI HOLDING CHOKE POSITION @ 40%. TOP OF MUD CAP AFTER PULLING ABOVE-8,763'
SABINE B 2H | 14 | 2021-02-08 16:30 | 2021-02-08 22:30 | 6 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.46 | 15696 | 15696 | 0 | TRIPPED OUT OF HOLE F/11,283' - T/110', HOLE TAKING CORRECT FILL, SET BACK RCH AT 5480'
SABINE B 2H | 14 | 2021-02-08 22:30 | 2021-02-08 23:30 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 11.5 | 15696 | 15696 | 0 | LAY DOWN BIT AND BHA
SABINE B 2H | 14 | 2021-02-08 23:30 | 2021-02-09 01:30 | 2 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 11.58 | 15696 | 15696 | 0 | PICK UP 6.75" ULTERRA CF613 SER 48394 JETS 6/10S TFA: .46), 525 ORBIT W/STABILIZED CC, 4.75" FILTER SUB, 5" MOTOR 0.52 RPG W/FLOAT, FLOW RANGE- 150/300 GPM; MAX DIFF-1,150 PSI; STALL TRQ-5,175 FT/LBS; BTI VALVE, 4.75" NM STAB, 5 1/4" UBHO, 5" NMDC, 5" NMPC, 5" NMDC, 4.75" X/O XT-39 P x DS 42B. BIT TO SVY-76'. BIT TO GAMMA-63'. TEST MWD (TEST GOOD)
SABINE B 2H | 14 | 2021-02-09 01:30 | 2021-02-09 02:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 11.6 | 15696 | 15696 | 0 | RIG SERVICE
SABINE B 2H | 14 | 2021-02-09 02:00 | 2021-02-09 03:00 | 1 | U | PRDHLLT | WAIT | WTTRD | WAIT ON THIRD PARTY | 11.65 | 15696 | 15696 | 0 | WAITING ON THIRD PARTY SCHLUMBERGER STABILIZERS
SABINE B 2H | 14 | 2021-02-09 03:00 | 2021-02-09 05:00 | 2 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 11.73 | 15696 | 15696 | 0 | RECEIVED STABILIZERS, TALLY, AND P/U TO RIG FLOOR, INSTALL STABILIZER, UBHO, AND MWD.
SABINE B 2H | 14 | 2021-02-09 05:00 | 2021-02-09 06:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.77 | 15696 | 15696 | 0 | TRIP IN HOLE F/BHA T/1,560'. PROPER DISPLACEMENT ON TRIP IN HOLE.
SABINE B 2H | 15 | 2021-02-09 06:00 | 2021-02-09 08:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.85 | 15696 | 15696 | 0 | TRIPPED IN THE HOLE F/1000' T/7200', MONITORING DISPLACEMENT IN TRIP TANK
SABINE B 2H | 15 | 2021-02-09 08:00 | 2021-02-09 08:30 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 11.88 | 15696 | 15696 | 0 | REMOVED TRIP NIPPLE @ INSTALLED RCH @ 7200' WELL STATIC & NOT FLOWING
SABINE B 2H | 15 | 2021-02-09 08:30 | 2021-02-09 09:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.9 | 15696 | 15696 | 0 | CIRCULATED & CONDITION AS PER SLB RSS RUNNING PROCEEDURES
SABINE B 2H | 15 | 2021-02-09 09:00 | 2021-02-09 10:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 11.94 | 15696 | 15696 | 0 | TRIPPED IN THE HOLE F/7200' - T/10,300' MONITORING DISPLACEMENT IN TRIP TANK
SABINE B 2H | 15 | 2021-02-09 10:00 | 2021-02-09 11:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.98 | 15696 | 15696 | 0 | CIRCULATED OUT PARTIAL MUD CAP @ 10,300' CIRCULATED BOTTOMS UP, FLOW STARTED INCREASING, MUD WAS THE DIVERTED THROUGH CHOKES WITH ORBIT VALVE BEING CLOSED. MAX GAS-888u FLARE-0' ONE CHOKE CLOSED & ONE @ 45% CASING PSI WHILE CIRCULATING-0 PSI
SABINE B 2H | 15 | 2021-02-09 11:00 | 2021-02-09 13:00 | 2 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.06 | 15696 | 15696 | 0 | STRIPPED IN THE HOLE F/10,300' - T/11,330' BLEEDING OF DISPLACEMENT IN TRIP TANK. 1.9 BBLS/STD HOLE BECAME TIGHT @ 11,330' THEN HUNG UP RSS MAX S/O-50K, MAX SICP-350 PSI
SABINE B 2H | 15 | 2021-02-09 13:00 | 2021-02-09 13:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.08 | 15696 | 15696 | 0 | WORKED RSS ASSEMBLY FREE. MAX OVER PULL-100K, MAX TRQ-20K, MAX RPM-40
SABINE B 2H | 15 | 2021-02-09 13:30 | 2021-02-09 14:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.13 | 15696 | 15696 | 0 | STRIPPED IN THE HOLE F/11,330' T/11,920' BLEEDING OF DISPLACEMENT IN TRIP TANK. 1.9 BBLS/STD HOLE BECAME TIGHT @ 11,920' WORKED RSS ASSEMBLY FREE, MAX OVER PULL-100K, MAX TRQ-20K, MAX RPM-40
SABINE B 2H | 15 | 2021-02-09 14:30 | 2021-02-09 15:00 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 12.15 | 15696 | 15696 | 0 | CIRCULATED & CONDITIONED HOLE RPM-40, TRQ-6/8K, SPM-95, GPM-241, SPP-2900 SPI, CP-0 PSI, FLARE-0', 1 CHOKE @ 40%
SABINE B 2H | 15 | 2021-02-09 15:00 | 2021-02-09 18:00 | 3 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.27 | 15696 | 15696 | 0 | STRIPPED IN THE HOLE F/11,920' - T/12,271' BLEEDING OFF DISPLACEMENT IN TRIP TANK. 1.9 BBLS/STD
SABINE B 2H | 15 | 2021-02-09 18:00 | 2021-02-09 19:00 | 1 | U | PRDHLLT | DPROB | STKP | STUCK PIPE | 12.31 | 15696 | 15696 | 0 | WORK PIPE, TIGHT HOLE AT 12,271', PULL UP TO 340K AND SLACK OFF T/180K W/22K TORQUE, POWER DRIVE WEDGED, CIRCULATED AND WORKED PIPE AT 250 GPM, PIPE CAME FREE
SABINE B 2H | 15 | 2021-02-09 19:00 | 2021-02-09 22:30 | 3.5 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 12.46 | 15696 | 15696 | 0 | WASH AND REAM IN HOLE 12,721'-15,070' GPM-250/275 SPP-3100/3700 RPM-35 TQ-10/14K CP-50 SICP-450 FL-0/10' CSG PSI WHILE CIRC=0-150 PSI CSG PSI DURING CONNECTIONS=300-575 PSI
SABINE B 2H | 15 | 2021-02-09 22:30 | 2021-02-09 23:30 | 1 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 12.5 | 15696 | 15696 | 0 | DOWN LINK TO POWER DRIVE.
SABINE B 2H | 15 | 2021-02-09 23:30 | 2021-02-10 00:30 | 1 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 12.54 | 15696 | 15696 | 0 | WASH AND REAM 15.070'-15,546' GPM-280, SPP-3700/4000, DP=0-300, RPM=35 TQ=10/15K, FL-0/10' CSG PSI WHILE CIRC=0-100 PSI CSG PSI DURING CONNECTIONS=500-700 PSI
SABINE B 2H | 15 | 2021-02-10 00:30 | 2021-02-10 01:30 | 1 | U | PRDHLLT | LOG | MWD | MWD | 12.58 | 15696 | 15696 | 0 | CHANGE PRO DIRECTIONAL MWD PULSE WIDTH FROM A 1.0 TO 0.6.
SABINE B 2H | 15 | 2021-02-10 01:30 | 2021-02-10 02:30 | 1 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 12.63 | 15696 | 15696 | 0 | WASH AND REAM 15.546'-15,696' GPM-280, SPP-3700/4000, DP=0-300, RPM=35 TQ=10/15K, FL-0/10' CSG PSI WHILE CIRC=0-150 PSI CSG PSI DURING CONNECTIONS=500-700 PSI
SABINE B 2H | 15 | 2021-02-10 02:30 | 2021-02-10 06:00 | 3.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.77 | 15696 | 15946 | 71.4 | DRILL LATERAL WITH SCHLUMBERGER POWERDRIVE RSS. (250' IN 3.5 HRS @ 71 FPH) WOB-20/25K SPM-57/57/0, GPM-300, RPM=50-80, MRPM-156, TMRPM-236, TRQ-10/19K, SPP-4450/5050 PSI, DIFF-500/600 PSI. PUMPING 10 BBLS LOW VIS FOLLOWED 20 MIN LATER BY 10 BBL HI VIS BENTONE SWEEPS EVERY 300' SWEEP CONTENTS: CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTION=500-700 PSI
SABINE B 2H | 16 | 2021-02-10 06:00 | 2021-02-10 06:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.79 | 15946 | 15946 | 0 | SERVICED TOP DRIVE
SABINE B 2H | 16 | 2021-02-10 06:30 | 2021-02-11 02:00 | 19.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 13.6 | 15946 | 17350 | 72 | DRILL LATERAL WITH SCHLUMBERGER RSS. (1404' IN 19.5 HRS @ 72 FPH) WOB-20/30K SPM-57/57/0, GPM-300, RPM=50/90, MRPM-156, TMRPM-206/246, TRQ-10/20K, SPP-4450/5050 PSI, DIFF-500/600 PSI. 1 CHOKE=35%/50%, FLARE=0'/3 CASING PSI WHILE DRILLING=0-400 PSI CASING PSI DURING CONNECTION=500-700 1.NUDGE-UP 12 MIN 0618-0630 16009' INCREASED TARGET IN 1 DEG INSTATANEOUS T/94.6 DEG. 2. NUDGE-LEFT 15 MIN 1005-1020 16,148' IH W/10% CONT. LEFT TURN T/93.6 DEG. 3. NUDGE-UP 15 MIN 1005-1020 16257' INCREASED TARGET INC 1 DEG T/94.6 DEG. 4. NUDGE-DOWN 15 MIN 1335-1350 DECREASED TARGET INC 2 DEG T/92.6 DEG. 5. NUDGE-RIGHT 13 MIN 1625-1638 IH MODE W/NO TURN. 6. NUDGE-RIGHT 20 MIN 1920-1940 IH MODE W/RIGHT TURN 7. NO TURN 20 MIN IH MODE NO TURN 8. NUDGE LEFT 20 MIN IH MODE NUDGE LEFT PUMPED 10 BBL LOW VIS SWEEP FOLLOWED 20 MIN LATER BY A 10 BBL HI VIS BENTONE SWEEP EVERY 300' SWEEP
SABINE B 2H | 16 | 2021-02-11 02:00 | 2021-02-11 06:00 | 4 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 13.77 | 17350 | 17350 | 0 | TROUBLESHOOT MWD DUE TO DECODING ISSUES. CHANGED OUT ALL SURFACE GEAR, TRIED ALTERNATING MUD PUMPS, ATTEMPTED DOWNLINKING TO CHANGE PULSE WIDTH, SWAPPED POWER SUPPLY TO EXTERNAL GENERATOR. TOOL IS INTERMITTENTLY RECEIVING PULSES.
SABINE B 2H | 17 | 2021-02-11 06:00 | 2021-02-11 06:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.79 | 17350 | 17350 | 0 | SERVICED RIG & TOP DRIVE
SABINE B 2H | 17 | 2021-02-11 06:30 | 2021-02-11 09:30 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 13.92 | 17350 | 17460 | 36.7 | DRILL LATERAL WITH SCHLUMBERGER RSS. (110' IN 3 HRS @ 36 FPH) WOB-20/30K SPM-57/57/0, GPM-300, RPM=50/90, MRPM-156, TMRPM-206/246, TRQ-10/20K, SPP-4450/5050 PSI, DIFF-500/600 PSI. 1 CHOKE=35%/50%, FLARE=0'/3 CASING PSI WHILE DRILLING=0-200 PSI CASING PSI DURING CONNECTION=500-700 PSI
SABINE B 2H | 17 | 2021-02-11 09:30 | 2021-02-11 10:00 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.94 | 17460 | 17460 | 0 | CIRCULATED & CONDITIONED HOLE
SABINE B 2H | 17 | 2021-02-11 10:00 | 2021-02-11 19:00 | 9 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.31 | 17460 | 17728 | 29.8 | DRILL LATERAL WITH SCHLUMBERGER RSS. (268' IN 9 HRS @ 30 FPH) WOB-20/30K SPM-57/57/0, GPM-300, RPM=50/90, MRPM-156, TMRPM-206/246, TRQ-10/20K, SPP-4450/5050 PSI, DIFF-500/600 PSI. 1 CHOKE=35%/50%, FLARE=0'/3 CASING PSI WHILE DRILLING=0-200 PSI CASING PSI DURING CONNECTION=500-700 PSI 1. NUDGE-LEFT 17,560' IH W/50% CONT. LEFT TURN T/92.6 DEG 2. SET TF TO 0 W/GTF NUETRAL TF-0 DEG, SR-0% @ 17,668 3. SET TF-288 DEG, SR-100% @ 17,668
SABINE B 2H | 17 | 2021-02-11 19:00 | 2021-02-11 19:30 | 0.5 | P | PRDHLLT | RIGMT | SVCMD | SERVICE MUD PUMPS / CIRC EQUIP | 14.33 | 17728 | 17728 | 0 | REPAIR POP OFF ON PUMP #1, FUCTION TEST IBOP ON TOP DRIVE
SABINE B 2H | 17 | 2021-02-11 19:30 | 2021-02-12 02:00 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.6 | 17728 | 17896 | 25.8 | DRILL LATERAL WITH SCHLUMBERGER RSS. (168' IN 6.5 HRS @ 26 FPH) WOB-20/30K SPM-0/57/57, GPM-300, RPM=50/80, MRPM-156, TMRPM-206/236, TRQ-10/20K, SPP-4250/4650 PSI, DIFF-300/400 PSI. 1 CHOKE=35%/50%, FLARE=0'/3 CASING PSI WHILE DRILLING=0 PSI CASING PSI DURING CONNECTION=300-500 PSI 1. NUDGE DOWN & LEFT 270 DEG @ 100% 2210-2230 HRS. 2. NUDGE DOWN & LEFT 236 DEG @ 100% 2320=2340 3. NUDGE DOWN & LEFT 248 DEG @ 100% 0030-0050 AT 17,891' OBSERVED A DRILLING BREAK. CONTINUED DRILLING T/17,896' AND DECISION WAS MADE TO CIRCULATE A BOTTOMS UP AND OBSERVE CUTTINGS.
SABINE B 2H | 17 | 2021-02-12 02:00 | 2021-02-12 06:00 | 4 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.77 | 17896 | 17896 | 0 | CIRCULATE BOTTOMS UP AND OBSERVE CUTTINGS. SAMPLE @ 17,896': 50% CHALK, 50% ASH. DECISION WAS MADE TO TD WELL. DOWNLINK RSS TO 0°. PUMP 2 TANDEM 30 BBLS HI-VIS SWEEP AND CIRCULATE OUT SWEEPS. INITIAL TORQUE: P/U=230K, S/O=203K, RPM=75, TQ=10-18K, PP=4,350 AFTER 1ST SWEEP BTM UP: P/U=240K, S/O=199K, RPM=75, TQ=10-21K, PP=4,350
SABINE B 2H | 17 | 2021-02-12 02:00 | 2021-02-12 02:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 14.6 | 17896 | 17896 |  | MILESTONE_TD WELL ON 2/12/2021 @ 02:00
SABINE B 2H | 18 | 2021-02-12 06:00 | 2021-02-12 07:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 14.81 | 17896 | 17896 | 0 | FINISHED CIRCULATING OUT SWEEP WHILE PERFORMING CLEAN UP CYCLE FINAL PARAMETERS: P/U=240K, S/O=199K, RPM=75, TQ=10-21K, PP=4,350 CP=0 PSI, FLARE-0'
SABINE B 2H | 18 | 2021-02-12 07:00 | 2021-02-12 17:30 | 10.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 15.25 | 17896 | 17896 | 0 | WASHED & REAMED OUT F/17,896' - T/11,350' RPM-40, TRQ-6K/12K (LOW) 18K/21K (HIGH), SPM-57/57/0, GPM-300, MRPM-156, TMRPM-196, SPP-3400/4300 SPI, FLARE-0'/5' CASING PSI WHILE CIRC-0 PSI CASING PSI WHILE MAKING CONNECTION-300-700 PSI
SABINE B 2H | 18 | 2021-02-12 17:30 | 2021-02-12 19:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.31 | 17896 | 17896 | 0 | CIRCULATED OUT GAS & CONDITIONED MUD @ 11,350' AT 300 GPM, SPP-3750 FL-0 CASING PSI WHILE CIRCULATING-0 PSI CSG PSI AFTER BTM UP W/PUMPS OFF-300-400 PSI
SABINE B 2H | 18 | 2021-02-12 19:00 | 2021-02-12 21:00 | 2 | P | PRDHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 15.4 | 17896 | 17896 | 0 | WASH UP TO CASING SHOE, GPM-300 SPP-3500 CSG PSI WHILE WASHING-0 PSI CSG PSI DURING CONNETIONS-300-400
SABINE B 2H | 18 | 2021-02-12 21:00 | 2021-02-12 22:30 | 1.5 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 15.46 | 17896 | 17896 | 0 | CIRCULATE AT 10,295', FINISH INCREASING MW F/14.5 TO/16 PPG, REPAIR MIXING HOPPER LEAK FOR BARITE ADDITION, GPM-290 SPP-3950 NO GAS OR FLARE
SABINE B 2H | 18 | 2021-02-12 22:30 | 2021-02-12 23:00 | 0.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.48 | 17896 | 17896 | 0 | SPOT 102 BBLS OF 16.0 PPG MUD FOR CAP, TOP OF AT 8060', DISPLACED W/93 BBLS 10.0 PPG SYSTEM MUD, FLOW CHECK, NO FLOW
SABINE B 2H | 18 | 2021-02-12 23:00 | 2021-02-13 04:30 | 5.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.71 | 17896 | 17896 | 0 | TRIP OUT OF HOLE F/10,252' T/BHA. L/D ROTATING HEAD @ 2,400'. HOLE TOOK PROPER FILLS ON TRIP OUT.
SABINE B 2H | 18 | 2021-02-13 04:30 | 2021-02-13 06:00 | 1.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 15.77 | 17896 | 17896 | 0 | LAY DOWN TOP MONEL, MWD, PONY COLLAR, PICK UP AND DRAIN MOTOR. BREAK BIT, L/D RSS TOOL, MOTOR, AND MONEL.
SABINE B 2H | 19 | 2021-02-13 06:00 | 2021-02-13 06:30 | 0.5 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 15.79 | 17896 | 17896 | 0 | FINISH L/D DIRECTIONAL TOOLS
SABINE B 2H | 19 | 2021-02-13 06:30 | 2021-02-13 07:30 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 15.83 | 17896 | 17896 | 0 | REMOVE WEAR BUSHING, LAY DOWN MOUSEHOLE, AND REMOVE RIG ELEVATORS
SABINE B 2H | 19 | 2021-02-13 07:30 | 2021-02-13 09:30 | 2 | P | PRDHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 15.92 | 17896 | 17896 | 0 | REMOVE SAVER SUB CUT FOR SCREEN AND REPLACE WITH FULL NOSE SAVER SUB.
SABINE B 2H | 19 | 2021-02-13 09:30 | 2021-02-13 10:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 15.94 | 17896 | 17896 | 0 | RIG SERVICE
SABINE B 2H | 19 | 2021-02-13 10:00 | 2021-02-13 12:00 | 2 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.02 | 17896 | 17896 | 0 | RIG UP EXPRESS CASING CREW
SABINE B 2H | 19 | 2021-02-13 12:00 | 2021-02-13 17:30 | 5.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.25 | 17896 | 17896 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY TORQ SFW CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY TORQ SFW CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY TORQ SFW CSG, CIRC THROUGH CASING TO TEST FLOATS-GOOD. PICK UP AND RUN 5" 18# P110 ICY TORQ SFW PRODUCTION CASING T/4,262', FILLING PIPE ON THE FLY. FULL RETURNS WHILE RUNNING IN THE HOLE.
SABINE B 2H | 19 | 2021-02-13 17:30 | 2021-02-13 19:00 | 1.5 | U | PRDHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 16.31 | 17896 | 17896 | 0 | PRESSURE WASHERS FROZEN-UNABLE TO PROPERLY CLEAN CASING. THAW OUT PRESSURE WASHERS AND CLEAN THREADS.
SABINE B 2H | 19 | 2021-02-13 19:00 | 2021-02-13 23:00 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.48 | 17896 | 17896 | 0 | RUN 5" P-110 ICY TORQ SFW CSG F/4,262' T/7,979'. FULL RETURNS WHILE RUNNING IN HOLE.
SABINE B 2H | 19 | 2021-02-13 23:00 | 2021-02-14 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.52 | 17896 | 17896 | 0 | FLOW CHECK (NO FLOW), REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD, WHILE MONITORING WELL ON TRIP TANK (NO FLOW). ROLL OVER EXCESS 5" CASING
SABINE B 2H | 19 | 2021-02-14 | 2021-02-14 01:00 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.56 | 17896 | 17896 | 0 | RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5.5" CRT AND ELEVATORS WHILE MONITORING WELL ON TRIP TANK-NO FLOW.
SABINE B 2H | 19 | 2021-02-14 01:00 | 2021-02-14 02:30 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.63 | 17896 | 17896 | 0 | PICK UP AND RUN 5.5" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/7,979' T/9,238'. PROPER DISPLACEMENTS ON TRIP IN.
SABINE B 2H | 19 | 2021-02-14 02:30 | 2021-02-14 03:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.67 | 17896 | 17896 | 0 | CIRCULATE OUT MUD CAP @ 9,238'. HEAVIEST MW SEEN-11.0 PPG. CASING PSI DURING CIRCULATION- 0 PSI CSG PSI AFTER CIRCULATION-125 PSI
SABINE B 2H | 19 | 2021-02-14 03:30 | 2021-02-14 06:00 | 2.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.77 | 17896 | 17896 | 0 | STRIP IN HOLE WITH 5.5" 23# P-110 ICY W463 CASING F/9,238' T/11,500'. BLEEDING OFF 1.3 BBLS/JOINT SICP=100-200 PSI
SABINE B 2H | 20 | 2021-02-14 06:00 | 2021-02-14 08:30 | 2.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.88 | 17896 | 17896 | 0 | CIRCULATE OUT MUD CAP @ 11,500'. GPM=151, PP=800 PSI, RPM-30, TQ=8-11K, P/U=240K, S/O=200K HEAVIEST MW SEEN-14 PPG. MAX GAS-1586u LOST APPROXIMATELY 70 BBLS DURING CIRCULATION. CASING PSI WHILE CIRCULATING-0 PSI CSG PSI AFTER CIRC W/O PUMPS-450 PSI
SABINE B 2H | 20 | 2021-02-14 08:30 | 2021-02-14 13:30 | 5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.08 | 17896 | 17896 | 0 | STRIP IN HOLE WITH 5.5" 23# P-110 ICY W463 CASING F/11,500' T/16,407'. BLEEDING 1.3 BBLS/JOINT. SICP=400-500 PSI
SABINE B 2H | 20 | 2021-02-14 13:30 | 2021-02-14 14:00 | 0.5 | U | PRDHLCSG | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 17.1 | 17896 | 17896 | 0 | TROUBLE SHOOT EXPRESS TORQUE TURN, EQUIPMENT NOT READING TURNS
SABINE B 2H | 20 | 2021-02-14 14:00 | 2021-02-14 17:00 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.23 | 17896 | 17896 | 0 | STRIP IN HOLE WITH 5.5" 23# P-110 ICY W463 CASING F/16,407' T/17,853'. BLEEDING 1.3 BBLS/JOINT. SICP=400-500 PSI
SABINE B 2H | 20 | 2021-02-14 17:00 | 2021-02-14 19:00 | 2 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.31 | 17896 | 17896 | 0 | PULL RCH FROM CASING AND P/U LANDING JT., SICP-740
SABINE B 2H | 20 | 2021-02-14 19:00 | 2021-02-14 19:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.33 | 17896 | 17896 | 0 | ROTATE DOWN LANDING JT., 2' ABOVE SETTING DEPTH, LAND CASING W/190K, TQ-22K WHEN ROTATING. SHOE-17,863.68 MD / 10,366' TVD TOP OF FLOAT COLLAR-17,813.79 TOP OF TOE SLEEVE-17,740.98
SABINE B 2H | 20 | 2021-02-14 19:30 | 2021-02-14 20:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.38 | 17896 | 17896 | 0 | CIRCULATE WITH RIG PUMP AND CRT, RIG DOWN CASING TOOLS GPM-200 SPP-1050
SABINE B 2H | 20 | 2021-02-14 20:30 | 2021-02-14 21:00 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 17.4 | 17896 | 17896 | 0 | RIG DOWN CRT AND R/U CMT HEAD WITH IRON TO RIG PUMPS.
SABINE B 2H | 20 | 2021-02-14 21:00 | 2021-02-15 | 3 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.52 | 17896 | 17896 | 0 | CIRCULATE GAS OUT OF HOLE. PP=1030, GPM=190, MAX GAS-3026u, MAX CSG PSI-425
SABINE B 2H | 20 | 2021-02-15 | 2021-02-15 01:00 | 1 | U | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.56 | 17896 | 17896 | 0 | CIRCULATE WHILE CHANGE OUT 4" WATER LINES TO NINE ENERGY CEMENT TRUCK. ALSO REPLACE VALVE THAT FROZE AND BURST ON CEMENT TRUCK.
SABINE B 2H | 20 | 2021-02-15 01:00 | 2021-02-15 05:00 | 4 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 17.73 | 17896 | 17896 | 0 | HELD PJSM, SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD, FLUSHED THROUGH & TESTED CEMENTING LINES T/7500 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 5 BPM 80 BBL 11.5 PPG WEIGHTED SPACER, 270 BBL 13.5 PPG 915 SK 1.66 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBLS OF SUGAR WATER WITH CPT-21L, FOLLOWED BY 330 BBLS OF FRESH WATER WITH PLEXCIDE 15G & CORPLEX 300 @ 5 BPM (TOTAL OF 350 BBLS DISPLACEMENT), OBSERVED 100% RETURNS SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 3800 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4800 PSI, HELD PSI FOR 5 MIN, BLED OFF PSI. FLOATS HELD 5 BBLS OF SPACER BACK TO SURFACE. PLUG DOWN @ 05:00 HRS 2/15/2021. INITIAL SICP-480 PSI, FINAL SICP= 0 PSI. MAX CASING PSI W/ PUMPING CEMENT- 0 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT- 412 PSI MAX GAS-2382u LOST APPROXIMATELY 23 BBLS WHILE CEMENTING CALCULATED TOP OF CEMENT- 6916'
SABINE B 2H | 20 | 2021-02-15 05:00 | 2021-02-15 06:00 | 1 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 17.77 | 17896 | 17896 | 0 | RIG DOWN CEMENT LINES WHILE MONTORING CASING PSI. CASING PSI @ 05:00=0 PSI 05:30=0 PSI
SABINE B 2H | 21 | 2021-02-15 06:00 | 2021-02-15 09:00 | 3 | P | PRDHLCSG | WAIT | WOC | WAIT ON CEMENT | 17.9 | 17896 | 17896 | 0 | MONITOR CASING PRESSURE WHILE R/D CEMENT LINES, FOUR BOLT FLOWLINE, INSTALL BOP WRANGLER, AND REMOVE TURNBUCKLES.
SABINE B 2H | 21 | 2021-02-15 09:00 | 2021-02-15 09:30 | 0.5 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 17.92 | 17896 | 17896 | 0 | OPEN CHOKE AND MONITOR WELL ON TRIP TANK (WELL STATIC), OPEN ORBIT VALVE AND REMOVE ROTATING HEAD.
SABINE B 2H | 21 | 2021-02-15 09:30 | 2021-02-15 15:30 | 6 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 18.17 | 17896 | 17896 | 0 | REMOVE ROTATING HEAD, LAY DOWN LANDING JOINT, RIGGED DOWN CASING BAILS AND ELEVATORS, MADE UP STREAM FLO WASHOUT TOOL AND FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN. P/U JT OF DP AND M/U PACK-OFF, INSTALLED STREAM FLO PACKOFF & TEST T/ 10,000 PSI.(PULL TEST T/25K OVERPULL) BACK OUT FROM PACK OFF AND L/D JOINT OF DP. INSTALL BPV.
SABINE B 2H | 21 | 2021-02-15 15:30 | 2021-02-15 18:00 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 18.27 | 17896 | 17896 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE BOPE, INSTALL WEATHER CAP, AND SECURE WELL.
SABINE B 2H | 21 | 2021-02-15 18:00 | 2021-02-15 18:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 18.27 | 17896 | 17896 |  | MILESTONE_TURN OVER TO COMPLETION ON 2/15/2021 @ 18:00 HRS
SABINE B 2H | 21 | 2021-02-15 18:00 | 2021-02-15 18:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 18.27 | 17896 | 17896 |  | MILESTONE_WELL RELEASE ON 2/15/2021 @ 18:00 HRS
SABINE B 2H | 21 | 2021-02-15 18:00 | 2021-02-15 18:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 18.27 | 17896 | 17896 |  | MILESTONE_RIG RELEASE ON 2/15/2021 @ 18:00
SABINE D 4H | 2 | 2021-01-16 03:00 | 2021-01-16 05:00 | 2 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 104 | 104 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK FROM SABINE C 3H TO SABINE D 4H, CENTERED AND LEVELED SUB OVER CONDUCTOR.
SABINE D 4H | 2 | 2021-01-16 03:00 | 2021-01-16 03:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 105 | 104 |  | MILESTONE_MOB/DEMOB ON 1/16/2021 @ 03:00
SABINE D 4H | 2 | 2021-01-16 05:00 | 2021-01-16 06:00 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 104 | 104 | 0 | RIG UP CELLAR PUMPS AND LINES, RISER ON CONDUCTOR PIPE
SABINE D 4H | 3 | 2021-01-16 06:00 | 2021-01-16 07:00 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 104 | 104 | 0 | CONTINUE TO RIG UP CELLAR PUMPS AND INSTALL ELEVATORS ON TOP DRIVE
SABINE D 4H | 3 | 2021-01-16 07:00 | 2021-01-16 07:30 | 0.5 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 104 | 104 | 0 | RIG SERVICE
SABINE D 4H | 3 | 2021-01-16 07:30 | 2021-01-16 08:30 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 104 | 104 | 0 | PICK UP BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 7-3/4", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 104
SABINE D 4H | 3 | 2021-01-16 08:30 | 2021-01-16 08:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 104 | 104 |  | MILESTONE_SPUD WELL ON 1/16/2021 @ 08:30
SABINE D 4H | 3 | 2021-01-16 08:30 | 2021-01-16 13:30 | 5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.21 | 104 | 2511 | 481.4 | ROTATE (2407' IN 5 HRS @ 482 FPH) WOB-20/35K, RPM-100, TRQ- 7/15K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2900 PSI, DIFF-700/900 PSI. DUMPING 100 BBLS EVERY 300' AND PUMPING 30 BBLS SOAP/SAPP SWEEP EVERY 300'. DROPPING 1 SOAP & SAPP STICKS EVERY STAND
SABINE D 4H | 3 | 2021-01-16 13:30 | 2021-01-16 15:30 | 2 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.29 | 2511 | 2916 | 202.5 | SLIDE (405' IN 2 HRS @ 203 FPH) WOB: 10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP- 2000/2200 PSI, DIFF- 100/200 PSI. SLIDE DEPTHS: SLD F/500-T/520,TF-80M,20' F/902-T/905,3MIN SLD F/595-T/620,TF-80M,25' F/917-T/920,3MIN SLD F/685-T/710,TF-80M,25' F/930-T/933,3MIN SLD F/965-T/990,TF-40L,25' F/1000-T/1004,4 MIN SLD F/1540-T/1575,TF-90L,35,F/1100-T/1110 SLD F/1715-T/1750,TF-90L,35' F/1128-T/1138 10MIN SLD F/1815-T/1855,TF-90L,40' F/1153-T/1204 SLD F/1905-T/1945,TF-90L,40' F/1214-T/1224,10MIN SLD F/2000-T/2030TF-90L,30' F/1234-T/1246,12MIN SLD F/2185-T/2215,TF-10R,30' F/1305-T/1316,11MIN SLD F/2280-T/2310,TF-20R,30' F/1326-T/1344,18MIN SLD F/2375-T/2415,TF-HS,40' F/1353-T/1414,21MIN SLD F/2655-T/2685,TF-HS,30' F/1444-T/1500,14MIN
SABINE D 4H | 3 | 2021-01-16 15:30 | 2021-01-16 16:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.33 | 2916 | 2916 | 0 | PUMP 3-30 BBL SOAP/SAPP SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2000 PSI
SABINE D 4H | 3 | 2021-01-16 16:30 | 2021-01-16 18:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.4 | 2916 | 2916 | 0 | TRIP OUT OF HOLE F/2,920' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE
SABINE D 4H | 3 | 2021-01-16 18:00 | 2021-01-16 19:30 | 1.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.46 | 2916 | 2916 | 0 | RACK BACK HWDP, REMOVE MWD, M/U 6.5" DRILL COLLAR ON TOP OF MONELS AND RACK BACK IN DERRICK. BREAK OUT/LAY DOWN PONY COLLAR, UBHO, AND STABILIZER. DRAIN MOTOR, BREAK BIT, AND LAY DOWN BOTH.
SABINE D 4H | 3 | 2021-01-16 19:30 | 2021-01-16 20:00 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 0.48 | 2916 | 2916 | 0 | CLEAN AND ORGANIZE RIG FLOOR. REMOVE RIG ELEVATORS.
SABINE D 4H | 3 | 2021-01-16 20:00 | 2021-01-16 21:00 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.52 | 2916 | 2916 | 0 | HOLD PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT-BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS. REMOVE CASING CONDUCTOR AND INSTALL CASING GUIDE TOOL ON CONDUCTOR
SABINE D 4H | 3 | 2021-01-16 21:00 | 2021-01-17 | 3 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.65 | 2916 | 2916 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# P-110 IC BT&C CASING, FLOAT COLLAR, 1 JT. 10 3/4" 45.5# P-110 IC BT&C CASING, TEST FLOATS (TEST GOOD), THEN RUN 68 JOINTS (71 TOTAL) OF 10 3/4" 45.5# P-110 IC T/2,906.09', RAN 37 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY OTHER JT. ALL THE WAY TO 78.06', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. PICKED UP 5' AND INSTALLED WH VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, SLACK OFF AND LAND 65" BELOW GROUND LEVEL. SET 115K (W/O BLOCKS) ON BASE PLATE. SHOE: 2,906.09' TOP OF FLOAT COLLAR: 2,822.45'
SABINE D 4H | 3 | 2021-01-17 | 2021-01-17 01:00 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.69 | 2916 | 2916 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOLS, GPM-321, SPP-100/200 PSI. NO LOSSES.
SABINE D 4H | 3 | 2021-01-17 01:00 | 2021-01-17 01:30 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.71 | 2916 | 2916 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, INSTALL STREAMFLO PUP JT, AND INSTALL CEMENT HEAD.
SABINE D 4H | 3 | 2021-01-17 01:30 | 2021-01-17 04:00 | 2.5 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.81 | 2916 | 2916 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,000 PSI & CEMENTED WITH: 30 BBL 8.3 PPG FRESH WATER SPACER, 314 BBLS 11.6 PPG LEAD CEMENT, 84 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 272 BBLS OF 9.2 PPG OIL BASE MUD. BUMPED PLUG W/600 PSI PRESSURED UP T/1100 PSI (500 PSI OVER) @ 3 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. CIRCULATE BACK TO SURFACE 30 BBLS OF SPACER AND 150 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
SABINE D 4H | 3 | 2021-01-17 04:00 | 2021-01-17 04:30 | 0.5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.83 | 2916 | 2916 | 0 | PRESSURE TESTED 10-3/4" 45.5# P-110 IC BTC CASING TO 1500 PSI FOR 20 MIN-GOOD
SABINE D 4H | 3 | 2021-01-17 04:30 | 2021-01-17 05:00 | 0.5 | P | SFHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 0.85 | 2916 | 2916 | 0 | RIG DOWN NINE ENERGY CEMENT HEAD, CIRCULATING IRON, AND STREAMFLO PUP JOINT.
SABINE D 4H | 3 | 2021-01-17 05:00 | 2021-01-17 06:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.9 | 2916 | 2916 | 0 | SKID ACCUMULATOR TO SABINE D 4H, RAISE BOP AND INSTALL BOP HYDRAULIC LINES. R/U CHOKE LINE TO CHOKE MANIFOLD AND STRETCH ACROSS SUB.
SABINE D 4H | 4 | 2021-01-17 06:00 | 2021-01-17 10:00 | 4 | P | SFHLCSG | BOP | COBOP | CHANGE OUT BOP | 1.06 | 2916 | 2916 | 0 | CHANGE OUT STREAM FLO BOP ADAPTER
SABINE D 4H | 4 | 2021-01-17 10:00 | 2021-01-17 14:00 | 4 | P | SFHLCSG | BOP | COBOP | CHANGE OUT BOP | 1.23 | 2916 | 2916 | 0 | CHANGE OUT ANNULAR ELEMENT
SABINE D 4H | 4 | 2021-01-17 14:00 | 2021-01-17 16:00 | 2 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.31 | 2916 | 2916 | 0 | RIG UP BOPE, RIG UP RCH AND SPOOL, INSTALL ORBIT VALVE TO FLOWLINE, INSTALL KILL LINE, HOOK UP HYDRAULIC LINES TO BOP STACK, FUNCTION TEST SAME
SABINE D 4H | 4 | 2021-01-17 16:00 | 2021-01-17 20:30 | 4.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.5 | 2916 | 2916 | 0 | R/U FLOWLINE TO FLOWLINE EXTENSION, INSTALL CHOKE LINE AND NEW CHECK VALVE, RIG UP AIR LINES TO ORBIT VALVE, R/U 2" BLEED OFF LINE, AND R/U 2" KILL LINES BACK TO MUD PUMPS
SABINE D 4H | 4 | 2021-01-17 20:30 | 2021-01-18 01:30 | 5 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.71 | 2916 | 2916 | 0 | INSTALLED TEST PLUG & TESTED BOPE: TOP & BOTTOM PIPE RAMS, BLIND RAMS, ALL 3 MUD CROSS MANUAL VALVES, HCR, CHOKE LINE, CHOKE MANIFOLD, STANDPIPE VALVE BACK TO THE PUMPS, KILL LINE BACK TO PUMPS, TOP DRIVE VALVES, FLOOR SAFETY VALVES 250 PSI LOW / 5000 PSI HIGH, TESTED HYDRIL 250 PSI LOW / 3500 PSI HIGH, TESTED ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. INSTALL KILL LINE VALVE AND TEST KILL LINE 250 LOW / 5000 HIGH. R/D TESTERS
SABINE D 4H | 4 | 2021-01-18 01:30 | 2021-01-18 02:00 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.73 | 2916 | 2916 | 0 | INSTALL WEAR BUSHING
SABINE D 4H | 4 | 2021-01-18 02:00 | 2021-01-18 03:00 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.77 | 2916 | 2916 | 0 | RIG SERVICE AND ACCUMULATOR DRAW DOWN TEST
SABINE D 4H | 4 | 2021-01-18 03:00 | 2021-01-18 05:30 | 2.5 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.88 | 2916 | 2916 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.491) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 5.9' BIT TO BEND 8-3/8" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, BIT TO SVY-71' AND GAMMA-61'. TEST MWD-TEST GOOD
SABINE D 4H | 4 | 2021-01-18 05:30 | 2021-01-18 06:00 | 0.5 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.9 | 2916 | 2916 | 0 | TRIP IN HOLE F/275' T/1,200'.
SABINE D 4H | 5 | 2021-01-18 06:00 | 2021-01-18 08:00 | 2 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.98 | 2916 | 2916 | 0 | TRIP IN HOLE F/BHA T/2,766' PICK UP AGITATOR AFTER STAND 22. PSI BEFORE AGITATOR-740. AFTER-840 PSI. GPM-321
SABINE D 4H | 5 | 2021-01-18 08:00 | 2021-01-18 08:30 | 0.5 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 2 | 2916 | 2926 | 20 | DRILL SHOE TRACK AND 10' NEW FORMATION F/2,916' T/2,926', GPM-481, SPP-1750 PSI, RPM-40, DIFF-200 PSI.
SABINE D 4H | 5 | 2021-01-18 08:30 | 2021-01-18 09:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.02 | 2926 | 2926 | 0 | CIRCULATE BOTTOMS UP GPM-420, SPP-1215 PSI, RPM-30
SABINE D 4H | 5 | 2021-01-18 09:00 | 2021-01-18 09:30 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 2.04 | 2926 | 2926 | 0 | PERFORM F.I.T.WITH 9.3 PPG MUD, 345 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-2,906' TVD-2,881'.
SABINE D 4H | 5 | 2021-01-18 09:30 | 2021-01-18 10:30 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.08 | 2926 | 3182 | 256 | ROT (256' IN 1 HRS @ 256 FPH) WOB: 25/35K, SPM: 90/90/0, GPM: 578, MMRPM: 96, RPM: 80, TRPM: 146, TRQ: 6K/8K, SPP: 2600/3200 PSI, DIFF: 500/600 PSI. SLD F/3150-T/3165,TF-20R,15' F/1037-T/1043,6MIN
SABINE D 4H | 5 | 2021-01-18 10:30 | 2021-01-18 11:30 | 1 | U | INTHL | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 2.13 | 3182 | 3182 | 0 | FLOWLINE SENSOR LEAKING. REMOVE SENSOR AND REPLACE GASKET.
SABINE D 4H | 5 | 2021-01-18 11:30 | 2021-01-18 17:00 | 5.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.35 | 3182 | 5331 | 390.7 | ROT (2149' IN 5.42 HRS @ 396 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 150, RPM: 80, TRPM: 230, TRQ: 7K/18K, SPP: 4300/5100 PSI, DIFF: 600/800 PSI. PUMPING 10 BBL LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 4 LB/BBL MAGNAFIBER, 4 LB/BBL NEWPHALT, 4 LB/BBL NUTPLUG (MEDIUM).
SABINE D 4H | 5 | 2021-01-18 17:00 | 2021-01-18 17:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.38 | 5331 | 5396 | 130 | SLIDE (65' IN .58 HRS @ 112 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 150, SPP: 4300/4700 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/3525-T/3540,TF-90R,15' F/1224-T/1230 SLD F/3805-T/3820,TF-150R,15' F/1304-T/1312,8MIN SLD F/4090-T/4105,TF-140R,15' F/1348-T1357,9MIN SLD F/4840-T/4860,TF-30L,20' F/1541-T/1553,12MIN
SABINE D 4H | 5 | 2021-01-18 17:30 | 2021-01-18 18:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.4 | 5396 | 5396 | 0 | RIG SERVICE
SABINE D 4H | 5 | 2021-01-18 18:00 | 2021-01-18 20:00 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.48 | 5396 | 6019 | 311.5 | ROT (623' IN 2 HRS @ 311 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 150, RPM: 80, TRPM: 230, TRQ: 7K/18K, SPP: 4300/5100 PSI, DIFF: 600/800 PSI.] PUMPING 10 BBL LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 4 LB/BBL MAGNAFIBER, 4 LB/BBL NEWPHALT, 4 LB/BBL NUTPLUG (MEDIUM).
SABINE D 4H | 5 | 2021-01-18 20:00 | 2021-01-18 20:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.5 | 6019 | 6051 | 64 | SLIDE (32' IN .5 HRS @ 64 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4300/4700 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/5592 T/5608 TF-150R 16' MIN-15 1844-1859 SLD F/5772 T/5788 TF-90R 16' MIN-15 1933-1948
SABINE D 4H | 5 | 2021-01-18 20:30 | 2021-01-18 21:00 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.52 | 6051 | 6051 | 0 | CIRCULATE WITH 1 PUMP WHILE CHANGING VALVE AND SEAT IN #3 MUD PUMP AND SWAB IN #1 MUD PUMP. GPM-256, PP-700, RPM-30, TQ-4-7K
SABINE D 4H | 5 | 2021-01-18 21:00 | 2021-01-19 03:30 | 6.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.79 | 6051 | 7513 | 224.9 | ROT (1462' IN 6.27 HRS @ 233 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 150, RPM: 80, TRPM: 230, TRQ: 7K/18K, SPP: 4300/5100 PSI, DIFF: 600/800 PSI. PUMPING 10 BBL LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 4 LB/BBL MAGNAFIBER, 4 LB/BBL NEWPHALT, 4 LB/BBL NUTPLUG (MEDIUM).
SABINE D 4H | 5 | 2021-01-19 03:30 | 2021-01-19 06:00 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.9 | 7513 | 7651 | 55.2 | SLIDE (138' IN 2.73 HRS @ 51 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4300/4700 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/6060 T/6078 TF-20R 18' MIN-15 2122-2137 SLD F/6344 T/6362 TF-HS 18' MIN-25 2245-2310 SLD F/6431 T/6449 TF-20R 18' MIN-27 2330-2357 SLD F/6528 T/6544 TF-HS 16' MIN-25 1230-1255 SLD F/6910 T/6926 TF-HS 16' MIN-18 0210-0228 SLD F/7181 T/7199 TF-HS 18' MIN-20 0318-0338 SLD F/7375 T/7391 TF-HS 16' MIN-13 0420-0433 SLD F/7564 T/7582 TF-HS 18' MIN-21 0505-0526
SABINE D 4H | 6 | 2021-01-19 06:00 | 2021-01-19 06:30 | 0.5 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 2.92 | 7651 | 7651 | 0 | RIG BLACKED OUT. START GENERATORS AND PUT BACK ONLINE.
SABINE D 4H | 6 | 2021-01-19 06:30 | 2021-01-19 15:30 | 9 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.29 | 7651 | 9567 | 212.9 | ROT (1916' IN 9.03 HRS @ 212 FPH) WOB: 25/40K, SPM: 83/83/83, GPM: 800, MMRPM: 133, RPM: 80, TRPM: 213, TRQ: 7K/20K, SPP: 4400/5100 PSI, DIFF: 500/700 PSI. PUMPING 10 BBL LCM SWEEPS EVERY 300' OR AS NEEDED. SWEEP CONTENTS: 4 LB/BBL MAGNAFIBER, 4 LB/BBL NEWPHALT, 4 LB/BBL NUTPLUG (MEDIUM).
SABINE D 4H | 6 | 2021-01-19 15:30 | 2021-01-19 20:00 | 4.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.48 | 9567 | 9783 | 48 | SLIDE (216' IN 4.47 HRS @ 48 FPH) WOB: 10/20K, SPM: 83/83/83, GPM: 800, MMRPM: 133, SPP: 4400/4800 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLIDE F/7651-T/7675,TF-20R,24' F/633-T/716,43 MIN SLIDE F/7839-T/7869,TF-20R,30' F/756-T/841,45 MIN SLD F/8035-T/8070,TF-20R,35' F/923-T/947,24MIN SLD F/8785-T/8810,TF-180,25' F/1252-T/1326,34MIN SLD F/8870-T/8907,TRF-180,37',F/1341-T/1425,44MIN SLD F/8964-T/8984,TF-180,20',F/1440-T/1505,25MIN SLD F/9350-T/9375,TF-120MAG,25',F/1623-T/1643,20MIN SLD F/9622 T/9642 TF-90M 20' MIN-30 1828-1858
SABINE D 4H | 6 | 2021-01-19 20:00 | 2021-01-19 21:00 | 1 | P | INTHL | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 3.52 | 9783 | 9783 | 0 | RIG SERVICE-TROUBLESHOOT TOP DRIVE
SABINE D 4H | 6 | 2021-01-19 21:00 | 2021-01-20 | 3 | U | INTHL | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.65 | 9783 | 9783 | 0 | TOP DRIVE INOPERABLE-FOUND 19 PIN PLUG/RECEPTACLE NEEDING REPLACED. WAIT ON ELECTRICIAN TO ARRIVE AND REPLACED ONCE ARRIVED ON LOCATION.
SABINE D 4H | 6 | 2021-01-20 | 2021-01-20 00:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.67 | 9783 | 9826 | 86 | ROTATE FROM 9,783' T/9,826'. WOB: 25/40, RPM: 80, TQ: 7/20K, GPM: 800, SPP:4400/5100, DIFF:500/700
SABINE D 4H | 6 | 2021-01-20 00:30 | 2021-01-20 03:00 | 2.5 | U | INTHL | DPROB | DFAIL | DOWNHOLE FAILURE | 3.77 | 9826 | 9826 | 0 | MWD INOPERABLE-TROUBLESHOOT SURFACE MWD EQUIPMENT: C/O TRANSDUCER, TRANSDUCER CABLE, AND PUMP 30 BBLS DIESEL SWEEP. 30 MINUTES AFTER DIESEL SWEEP WENT THROUGH BIT, MWD BEGAN PULSING.
SABINE D 4H | 6 | 2021-01-20 03:00 | 2021-01-20 03:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.79 | 9826 | 9924 | 196 | ROTATE FROM 9,826' T/9,924'. WOB: 25/40, RPM: 80, TQ: 7/20K, GPM: 800, SPP:4400/5100, DIFF:500/700
SABINE D 4H | 6 | 2021-01-20 03:30 | 2021-01-20 04:00 | 0.5 | U | INTHL | DPROB | DFAIL | DOWNHOLE FAILURE | 3.81 | 9924 | 9924 | 0 | MWD NOT PULSING-RECYCLE MUD PUMPS MULTIPLE TIMES. MWD WOULDN'T STAY SYNCHED UP.
SABINE D 4H | 6 | 2021-01-20 04:00 | 2021-01-20 04:30 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.83 | 9924 | 9924 | 0 | PERFORM FLOW CHECK-(NO FLOW) AND PUMP SLUG.
SABINE D 4H | 6 | 2021-01-20 04:30 | 2021-01-20 06:00 | 1.5 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 3.9 | 9924 | 9924 | 0 | POOH F/9,924' T/6,700'. HOLE TAKING PROPER DISPLACEMENT ON TRIP OUT OF HOLE.
SABINE D 4H | 7 | 2021-01-20 06:00 | 2021-01-20 06:30 | 0.5 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 3.92 | 9924 | 9924 | 0 | PULL OUT OF HOLE F/6,700' T/4,721', HOLE TAKING PROPER DISPLACEMENT ON TRIP OUT OF HOLE, NO EXCESS DRAG ON TRIP OUT OF HOLE.
SABINE D 4H | 7 | 2021-01-20 06:30 | 2021-01-20 07:00 | 0.5 | U | INTHL | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 3.94 | 9924 | 9924 | 0 | FLOW CHECK WELL, WELL STATIC, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
SABINE D 4H | 7 | 2021-01-20 07:00 | 2021-01-20 09:00 | 2 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 4.02 | 9924 | 9924 | 0 | PULL OUT OF HOLE F/4,721' T/ BHA', HOLE TAKING PROPER DISPLACEMENT ON TRIP OUT OF HOLE, NO EXCESS DRAG ON TRIP OUT OF HOLE, FLOW CHECK WELL AT BHA, WELL STATIC.
SABINE D 4H | 7 | 2021-01-20 09:00 | 2021-01-20 10:30 | 1.5 | U | INTHL | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.08 | 9924 | 9924 | 0 | REMOVE MWD TOOL, DRAIN MOTOR AND INSPECT BIT, TWO CHIPPED CUTTERS ON GAUGE OF BIT, NO VISUAL DAMAGE OF INSPECTION OF MOTOR, RE-RUN BIT AND MOTOR, INSTALL NEW MWD TOOL AND SURFACE TEST, GOOD SURFACE TEST ON MWD TOOL.
SABINE D 4H | 7 | 2021-01-20 10:30 | 2021-01-20 11:30 | 1 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 4.13 | 9924 | 9924 | 0 | TRIP IN HOLE F/ BHA T/ 2,671', PROPER DISPLACEMENTS ON TRIP IN HOLE.
SABINE D 4H | 7 | 2021-01-20 11:30 | 2021-01-20 12:00 | 0.5 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 4.15 | 9924 | 9924 | 0 | PICK-UP DRILLING AGITATOR, CIRCULATING PRESSURE PRIOR TO AGITATOR - 600 PSI @ 320 GPM, AFTER AGITATOR - 790 PSI @ 320 GPM.
SABINE D 4H | 7 | 2021-01-20 12:00 | 2021-01-20 12:30 | 0.5 | U | INTHL | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 4.17 | 9924 | 9924 | 0 | FLOW CHECK WELL, WELL STATIC, REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
SABINE D 4H | 7 | 2021-01-20 12:30 | 2021-01-20 15:30 | 3 | U | INTHL | TRIP | BHA | TRIP FOR BIT / BHA | 4.29 | 9924 | 9924 | 0 | TRIP IN HOLE F/ 2,671' T/ 9,873', PROPER DISPLACEMENTS ON TRIP IN HOLE.
SABINE D 4H | 7 | 2021-01-20 15:30 | 2021-01-20 16:00 | 0.5 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.31 | 9924 | 9924 | 0 | WASH AND REAM F/ 9,873' T/ 9,924' WHILE TROUBLE SHOOT MUD PUMPS DUE T/ MWD TOOL NOT SYNC UP PROPERLY.
SABINE D 4H | 7 | 2021-01-20 16:00 | 2021-01-20 17:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.38 | 9924 | 9986 | 41.3 | SLIDE (62' IN 1.5 HRS @ 41.3 FPH) WOB: 20/30K, SPM: 83/83/83, GPM: 800, MMRPM: 133, SPP: 4500/5000 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/ 9924' T/ 9986', TF-130M, 62' F/1600-T/1730, 90 MINS. START INTERMEDIATE CURVE ON 1/20/2021 @ 16:00 (9,924' MD / 9,734' TVD)
SABINE D 4H | 7 | 2021-01-20 17:30 | 2021-01-20 18:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.4 | 9986 | 9986 | 0 | RIG SERVICE
SABINE D 4H | 7 | 2021-01-20 18:00 | 2021-01-20 20:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.48 | 9986 | 10053 | 33.5 | SLIDE (67' IN 1.83 HRS @ 36.6 FPH) WOB: 25/35K, SPM: 83/83/83, GPM: 800, MMRPM: 133, SPP: 4500/5000 PSI, DIFF: 300/500 PSI. SLIDE DEPTHS: SLD F/ 9986' T/ 9998', TF-130M, 12' F/1800-T/1815,15 MINS. SLD F/ 10008' T/ 10063', TF-130M, 55' F/1825-T/2000,95 MINS.
SABINE D 4H | 7 | 2021-01-20 20:00 | 2021-01-20 21:30 | 1.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.54 | 10053 | 10171 | 78.7 | ROT (118' IN 1,67 HRS @ 70.7 FPH) WOB: 35/45K, SPM: 83/83/83, GPM: 800, MMRPM: 133, RPM: 50, TRPM: 183, TRQ: 12/18K, SPP: 4500/5000 PSI, DIFF: 300/500 PSI. TD INTERMEDIATE SECTION ON 1/20/2021 @ 21:30 (10,171' MD / 9,980' TVD)
SABINE D 4H | 7 | 2021-01-20 21:30 | 2021-01-20 22:30 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.58 | 10171 | 10171 | 0 | PUMP 1-30 BBL LCM SWEEPS AND CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM: 800, RPM: 50, TRQ: 6K/8K, SPP: 4500 PSI. PERFORMED 15 MINUTE FLOW CHECK-NO FLOW. PUMP SLUG.
SABINE D 4H | 7 | 2021-01-20 22:30 | 2021-01-21 03:00 | 4.5 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.77 | 10171 | 10171 | 0 | TRIP OUT THE HOLE F/10,171' T/BHA, HOLE TAKING PROPER FILL, REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, L/D AGITATOR. FLOW CHECK @ 2,855'-NO FLOW, FLOW CHECK @ BHA-NO FLOW.
SABINE D 4H | 7 | 2021-01-21 03:00 | 2021-01-21 04:00 | 1 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.81 | 10171 | 10171 | 0 | REMOVE MWD, DRAIN MUD MOTOR, REMOVE BIT, RACK BACK DIRECTIONAL BHA
SABINE D 4H | 7 | 2021-01-21 04:00 | 2021-01-21 04:30 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.83 | 10171 | 10171 | 0 | REMOVE WEAR BUSHING; CLEAN RIG FLOOR
SABINE D 4H | 7 | 2021-01-21 04:30 | 2021-01-21 06:00 | 1.5 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.9 | 10171 | 10171 | 0 | REMOVE VARIABLE RAMS; INSTALL 7 5/8" CASING RAMS
SABINE D 4H | 8 | 2021-01-21 06:00 | 2021-01-21 06:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.92 | 10171 | 10171 | 0 | PRESSURE TEST BONNET SEALS ON UPPER PIPE RAMS TO 1500 PSI.
SABINE D 4H | 8 | 2021-01-21 06:30 | 2021-01-21 07:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.94 | 10171 | 10171 | 0 | RIG SERVICE.
SABINE D 4H | 8 | 2021-01-21 07:00 | 2021-01-21 08:30 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 5 | 10171 | 10171 | 0 | RIG UP FRANKS CASING EQUIPMENT.
SABINE D 4H | 8 | 2021-01-21 08:30 | 2021-01-21 18:00 | 9.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.4 | 10171 | 10171 | 0 | HELD PJSM, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOATSHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR. RAN 227 JTS AND 2 PUP JOINTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 5 SOLID BODY CENTRALIZERS F/ 9969' T/ 10146' (FREE FLOATING), 41 LATCH ON BOW SPRING CENTRALIZERS @ 9878' AND EVERY 4TH JT UP TO 2769.83'. P/U LANDING JOINT, LANDED CSG ON CSG MANDREL W/230K (W/O BLOCKS). FLOAT SHOE-10,148.39' TOP OF FLOAT COLLAR-10,057.57' 13 JOINTS LEFT OUT- 582.01'
SABINE D 4H | 8 | 2021-01-21 18:00 | 2021-01-21 18:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 5.42 | 10171 | 10171 | 0 | RIG DOWN FRANKS CASING EQUIPMENT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
SABINE D 4H | 8 | 2021-01-21 18:30 | 2021-01-21 20:00 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.48 | 10171 | 10171 | 0 | CIRCULATE BOTTOMS UP W/ RIG PUMPS THROUGH CEMENT HEAD, SPM: 105, 8.0 BPM, SPP: 625 PSI, NO LOSSES.
SABINE D 4H | 8 | 2021-01-21 20:00 | 2021-01-21 23:00 | 3 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.6 | 10171 | 10171 | 0 | PJSM, SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG SPACER. 288 BBL 11.8 PPG 835 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 462 BBLS OF 9.0 PPG OIL BASE MUD @ 8 BPM SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2045 PSI, BUMPED PLUG AS CALCULATED, PRESSURE UP TO 2545 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 6 BBLS. FLOATS HELD. PLUG DOWN @ 22:50 HRS ON 01/21/2021, CIRCULATED BACK TO SURFACE 40 BBLS OF SPACER AND 0 BBLS OF LEAD CMT, CEMENTED W/ FULL RETURNS DURING ENTIRE CEMENTING JOB. TOC @ 0'.
SABINE D 4H | 8 | 2021-01-21 23:00 | 2021-01-21 23:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.63 | 10171 | 10171 | 0 | PRESSURE TEST CASING TO 3500 PSI, HELD 15 MINUTES. (GOOD TEST)
SABINE D 4H | 8 | 2021-01-21 23:30 | 2021-01-22 00:30 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 5.67 | 10171 | 10171 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, FLUSH THROUGH BOP AND FLOW LINE WITH WATER, BREAK OUT AND LAY DOWN LANDING JOINT, RIG DOWN CASING BAILS AND ELEVATORS.
SABINE D 4H | 8 | 2021-01-22 00:30 | 2021-01-22 02:00 | 1.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.73 | 10171 | 10171 | 0 | MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
SABINE D 4H | 8 | 2021-01-22 02:00 | 2021-01-22 05:30 | 3.5 | U | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.88 | 10171 | 10171 | 0 | REMOVE ORBIT VALVE, ROTATING HEAD AND SPACER SPOOL, LIFT STACK; CHANGE SPACER SPOOL DUE TO SPOOL LENGTH BEING TOO LONG AND CAN NOT LIFT STACK HIGH ENOUGH TO WALK RIG
SABINE D 4H | 8 | 2021-01-22 05:30 | 2021-01-22 06:00 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.9 | 10171 | 10171 | 0 | INSTALL WEATHER CAP AND SECURE WELL. WELL ON HOLD AND WALK RIG T/ SABINE C 3H
SABINE D 4H | 8 | 2021-01-22 06:00 | 2021-01-22 06:00 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 5.9 | 10171 | 10171 |  | MILESTONE_HOLD WELL OPERATIONS 1 01/22/2021 @ 06:00
SABINE D 4H | 9 | 2021-03-12 09:00 | 2021-03-12 10:30 | 1.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.96 | 10171 | 10171 | 0 | PREP RIG TO WALK: REMOVE VIBRATOR HOSES, KILL LINE, CHOKE LINE AND PICK UP V-DOOR. WALK CATWALK FORWARD, MOVE CLIMB ASSIST, GERONIMO ANCHORS, WALK RIG F/SABINE C 3H T/SABINE D 4H.
SABINE D 4H | 9 | 2021-03-12 10:30 | 2021-03-12 13:30 | 3 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 6.08 | 10171 | 10171 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME, HOOK UP FLOWLINE, REMOVE KILL LINE CHECK VALVE, RIG UP KILL LINE.
SABINE D 4H | 9 | 2021-03-12 13:30 | 2021-03-12 14:00 | 0.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.1 | 10171 | 10171 | 0 | PREFORM DRAW DOWN TEST ON ACCUMULATOR
SABINE D 4H | 9 | 2021-03-12 14:00 | 2021-03-12 18:30 | 4.5 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.29 | 10171 | 10171 | 0 | BEGIN TESTING BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 7,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW/ 7000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST ORBIT VALVE T/250 LOW/1500 HIGH. REMOVE TEST PLUG AND RIG DOWN TESTERS.
SABINE D 4H | 9 | 2021-03-12 18:30 | 2021-03-12 19:30 | 1 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.33 | 10171 | 10171 | 0 | CLEANED, ORGANIZED & PREPPED RIG FLOOR FOR TRIP, & INSTALLED WEAR BUSHING
SABINE D 4H | 9 | 2021-03-12 19:30 | 2021-03-12 21:30 | 2 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.42 | 10171 | 10171 | 0 | CHANGED OUT TOP DRIVE SAVER SUB
SABINE D 4H | 9 | 2021-03-12 21:30 | 2021-03-12 22:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 6.44 | 10171 | 10171 | 0 | SERVICED TOP DRIVE
SABINE D 4H | 9 | 2021-03-12 22:00 | 2021-03-12 23:30 | 1.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.5 | 10171 | 10171 | 0 | PICKED UP, MADE UP AND TESTED CURVE & LATERAL BHA CONSISTING OF: 6.75" SECURITY GTD64M SER 13522000 JETS 6/18S TFA: 1.491, 5.5", 6/7L, 8.8 STG @ 2° SLICK; .68 REV/GAL; 4.03' BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPC, 5" NMDC, TOMAX THRUSTER, X/O XT-39 P x DS 42B, 2 STANDS, DRILL AND REAM, 25 STANDS DP, AGITATOR, BIT TO SVY-67'. BIT TO GAMMA-58'.
SABINE D 4H | 9 | 2021-03-12 23:30 | 2021-03-13 | 0.5 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 6.52 | 10171 | 10171 | 0 | FUNCTION TESTED ORBIT VALVE UNTIL FULLY OPENED
SABINE D 4H | 9 | 2021-03-13 | 2021-03-13 00:30 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.54 | 10171 | 10171 | 0 | TRIPPED IN THE HOLE T/2738 WITH FULL DISPLACEMENT
SABINE D 4H | 9 | 2021-03-13 00:30 | 2021-03-13 01:00 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.56 | 10171 | 10171 | 0 | PICKED UP AND FLOW TESTED AGITATOR BEFORE-750 PSI AFTER-850 SPI
SABINE D 4H | 9 | 2021-03-13 01:00 | 2021-03-13 03:30 | 2.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.67 | 10171 | 10171 | 0 | TRIPPED IN THE HOLE T/10,557' WITH FULL DISPLACEMENT
SABINE D 4H | 9 | 2021-03-13 03:30 | 2021-03-13 04:00 | 0.5 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.69 | 10171 | 10171 | 0 | REMOVED TRIP NIPPLE & INSTALLED RCH
SABINE D 4H | 9 | 2021-03-13 04:00 | 2021-03-13 05:00 | 1 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 6.73 | 10171 | 10181 | 10 | FILLED PIPE, TAGGED FLOAT COLLAR, & DRILLED OUT FLOAT COLLAR, SHOE TRACK, SHOE, + 10' OF NEW FORMATION T/10,181' GPM=250, SPP=2000 TQ=9-12K, RPM=30
SABINE D 4H | 9 | 2021-03-13 05:00 | 2021-03-13 06:00 | 1 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.77 | 10181 | 10181 | 0 | CIRCULATE BOTTOMS UP AND BLEND MUD.
SABINE D 4H | 10 | 2021-03-13 06:00 | 2021-03-13 06:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.79 | 10181 | 10181 | 0 | PERFORM F.I.T @ 10,148' MD / 9,955' TVD WITH 9.0 PPG OBM T/ 2072 PSI. EMW=13.0 PPG
SABINE D 4H | 10 | 2021-03-13 06:30 | 2021-03-13 17:30 | 11 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.25 | 10181 | 10697 | 46.9 | SLIDE (516' IN 10.92 HRS @ 47.27 FPH) WOB-25/45K SPM-76/76/0 GPM-398, MRPM-271, SPP-3600/4000 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE-0', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. SLIDE DEPTHS: 10,181-10,352 TF-20L 171' IN 295M 06:30-11:25. 10,387-10,447 TF-HS 60' IN 70M 11:45-12:55. 10,497-10,697 TF-HS 200' IN 170M 13:20-16:10. 10,800-10,825 25' IN 45M 17:00-17:45. 10,860-10,920 TF-10L 60' IN 85M 18:15-19:30.
SABINE D 4H | 10 | 2021-03-13 06:30 | 2021-03-13 06:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.79 | 10181 | 10181 |  | MILESTON_START CURVE SECTION ON 3/13/2021 @ 06:30
SABINE D 4H | 10 | 2021-03-13 17:30 | 2021-03-13 19:30 | 2 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.33 | 10697 | 10920 | 111.5 | ROT (223' IN 2.10 HRS @ 110.95 FPH) WOB-25/45K SPM-76/76/0 GPM-398, RPM-30, MRPM-271, TMRPM-300, TRQ-12/16K, SPP-3600/4400 PSI, DIFF-400/800 PSI, CHOKES- 100%/100%, FLARE-0', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI.
SABINE D 4H | 10 | 2021-03-13 19:30 | 2021-03-13 22:00 | 2.5 | U | PRDHLCV | DPROB | DFAIL | DOWNHOLE FAILURE | 7.44 | 10920 | 10920 | 0 | AFTER CONNECTION SURVEY WAS PUMPED UP. TOOL WAS PULSING AND COMMUNICATING WITH SURFACE EQUIPMENT BUT GAMMA AND MAGNETIC TOTALS WERE NOT CORRECT. ATTEMPTED TO RECYCLE SEVERAL TIMES IN AN ATTEMPT TO PUMP UP PROPER SURVEY BUT SURVEYS WERE STILL INCORRECT. ALL SURFACE EQUIPMENT WAS INSPECTED ALONG WITH TRYING DIFFERENT MUD PUMPS. TOOL STILL DID NOT WORK PROPERLY AND DECISION WAS MADE TO TRIP OUT OF THE HOLE TO CHANGE OUT MWD TOOL AND MUD MOTOR.
SABINE D 4H | 10 | 2021-03-13 22:00 | 2021-03-14 00:30 | 2.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 7.54 | 10920 | 10920 | 0 | PUMPED 40 BBL 13 PPG SLUG AND TRIPPED OUT OF THE HOLE F/10,920' - T/5700'. REMOVED RCH & INSTALLED TRIP NIPPLE @ 6900'
SABINE D 4H | 10 | 2021-03-14 00:30 | 2021-03-14 01:30 | 1 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.58 | 10920 | 10920 | 0 | RIG SERVICE-T/S TOP DRIVE
SABINE D 4H | 10 | 2021-03-14 01:30 | 2021-03-14 06:00 | 4.5 | U | PRDHLCV | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 7.77 | 10920 | 10920 | 0 | TOP DRIVE STARTED LEAKING A LARGE AMOUNT OF OIL DURING TRIP OUT @ 5700'. TOP DRIVE WAS LOWERED DOWN CLOSER TO RIG FLOOR AND PATTERSON EMPLOYEE WENT UP TO INSPECT LEAK. UPON INSPECTION, LEAK WAS FOUND AT THE TOP DRIVES MAIN SHAFT SEAL TO QUILL. PATTERSON MECHANIC WAS CALLED TO COME OUT & INSPECT AS TO WHAT ACTION SHOULD BE TAKEN. EITHER TO TRY AND CHANGE OUT SEAL OR POSSIBLY CHANGE OUT TOP DRIVE.
SABINE D 4H | 11 | 2021-03-14 06:00 | 2021-03-14 18:00 | 12 | U | PRDHLCV | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 8.27 | 10920 | 10920 | 0 | CHANGING OUT ROTATING LINK ADAPTER: REMOVE QUILL AND LINK TILTS, TORQUE TUBE, SHOT PINS, DRAIN OIL AND PLUG HYD. LINES, REMOVE RLA. INSTALL NEW RLA: R/U SHOT PIN ASSY, AND LOAD COLLAR, FILL GEAR AND HYD OIL RESERVOIRS, CHANGE FILTERS, UNLOCK TOP DRIVE AND FUNCTION TEST-GOOD. M/U QUILL AND TQ UP T/48K. C/O GRABBER DIES T/4.5", INSTALL TIW AND INSTALL FEDERER RINGS.
SABINE D 4H | 11 | 2021-03-14 18:00 | 2021-03-14 19:00 | 1 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.31 | 10920 | 10920 | 0 | RIG SERVICE
SABINE D 4H | 11 | 2021-03-14 19:00 | 2021-03-14 21:30 | 2.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 8.42 | 10920 | 10920 | 0 | POOH F/5,710' T/BHA. PROPER FILLS ON TRIP OUT.
SABINE D 4H | 11 | 2021-03-14 21:30 | 2021-03-14 23:30 | 2 | U | PRDHLCV | TRIP | PUBHA | PICK UP BIT / BHA | 8.5 | 10920 | 10920 | 0 | LAY DOWN REAMER, RACK BACK 2 STANDS OF DP, L/D THRUSTER AND TOP MONEL. REMOVE MWD, DRAIN MOTOR, BREAK BIT, AND LAY DOWN MOTOR. P/U NEW BHA: 6.75" SECURITY GTD64M SER 13401055 JETS 6/18S TFA: 1.491, 5.5", 6/7L, 8.8 STG @ 2° SLICK; .68 REV/GAL; 4.10 BIT TO BEND 5-1/2" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, TOMAX THRUSTER, X/O XT-39 P x DS 42B, 2 STANDS, DRILL AND REAM, 25 STANDS DP, AGITATOR, BIT TO SVY-67'. BIT TO GAMMA-58'.
SABINE D 4H | 11 | 2021-03-14 23:30 | 2021-03-15 | 0.5 | U | PRDHLCV | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.52 | 10920 | 10920 | 0 | CLEAN AND ORGANIZE RIG FLOOR TO MITIGATE POTENTIAL SLIPS, TRIP, OR FALLS WHILE TESTING MWD-GOOD.
SABINE D 4H | 11 | 2021-03-15 | 2021-03-15 03:30 | 3.5 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 8.67 | 10920 | 10920 | 0 | TRIP IN HOLE F/BHA T/9,684'. PICK UP AGITATOR ON STAND 27. GPM-215, PSI BEFORE AGITATOR- 840 PSI. PSI AFTER AGITATOR- 1000 PSI. PROPER DISPLACEMENT
SABINE D 4H | 11 | 2021-03-15 03:30 | 2021-03-15 04:00 | 0.5 | U | PRDHLCV | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 8.69 | 10920 | 10920 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROT. HEAD
SABINE D 4H | 11 | 2021-03-15 04:00 | 2021-03-15 05:00 | 1 | U | PRDHLCV | TRIP | BHA | TRIP FOR BIT / BHA | 8.73 | 10920 | 10920 | 0 | TRIP IN HOLE F/9,684' T/10,920'. PROPER DISPLACEMENT ON TRIP IN HOLE.
SABINE D 4H | 11 | 2021-03-15 05:00 | 2021-03-15 05:30 | 0.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.75 | 10920 | 10995 | 150 | SLIDE 75' IN .83 HRS @ 90 FPH) WOB-25/45K SPM-76/76/0 GPM-398, MRPM-271, SPP-3600/4000 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE=5-15' CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI.
SABINE D 4H | 11 | 2021-03-15 05:30 | 2021-03-15 06:00 | 0.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.77 | 10995 | 11015 | 40 | ROT 20' IN .17 HRS @ 120 FPH) WOB-25/45K SPM-76/76/0 GPM-398, RPM-30, MRPM-271, TMRPM-300, TRQ-10/12K, SPP-3600/4400 PSI, DIFF-400/800 PSI, CHOKES- 100%/100%, FLARE-5-15', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI.
SABINE D 4H | 12 | 2021-03-15 06:00 | 2021-03-15 07:30 | 1.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.83 | 11015 | 11139 | 82.7 | SLIDE 124' IN 1.25 HRS @ 99 FPH) WOB-25/45K SPM-76/76/0 GPM-398, MRPM-271, SPP-3600/4000 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE=5-15' CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. SLIDE DEPTHS:( F/11203-T/11243 TF-60L 40') ( F/755-T/820 25-MIN F/11025-T/11109 TF-20R,84')( F/610-T/700 50-MIN )
SABINE D 4H | 12 | 2021-03-15 07:30 | 2021-03-15 09:00 | 1.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.9 | 11139 | 11297 | 105.3 | ROT 158' IN 1.75 HRS @ 91 FPH) WOB-25/45K SPM-76/76/0 GPM-398, RPM-30, MRPM-271, TMRPM-300, TRQ-10/12K, SPP-3600/4400 PSI, DIFF-400/800 PSI, CHOKES- 100%/100%, FLARE-5-15', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI.
SABINE D 4H | 12 | 2021-03-15 09:00 | 2021-03-15 16:00 | 7 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.19 | 11297 | 12549 | 178.9 | ROT 1,252' IN 6.85 HRS @ 183 FPH) WOB-25/45K SPM-76/76/0 GPM-398, RPM-80, MRPM-271, TMRPM-351, TRQ-10/12K, SPP-3600/4400 PSI, DIFF-400/800 PSI, CHOKES- 100%/100%, FLARE-0-15', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 4 PPB NEWCARB, 4 PPB NEWPHALT
SABINE D 4H | 12 | 2021-03-15 09:00 | 2021-03-15 09:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 8.9 | 11297 | 11297 |  | SUB CODE: LCRV MILESTONE_LAND/END CURVE ON 3/15/2021 @ 09:00
SABINE D 4H | 12 | 2021-03-15 09:00 | 2021-03-15 09:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 8.9 | 11297 | 11297 |  | SUB CODE: SLAT MILESTONE_START HORIZONTAL LATERAL SECTION ON 3/15/2021 @ 09:00
SABINE D 4H | 12 | 2021-03-15 16:00 | 2021-03-15 17:30 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.25 | 12549 | 12632 | 55.3 | SLIDE 83' IN 1.65 HRS @ 50 FPH) WOB-25/45K SPM-76/76/0 GPM-398, MRPM-271, SPP-3600/4000 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE=0-15' CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. (F/11496-T/11514, TF-HS,18',F/1000-T/1014,14-MIN) (F/11686-T/11698,TF-180,12' F/1115-T/1128,13-MIN)(F/12064 T/12079,TF-30L,15' F/1320-T/1339,19-MIN)(F/12257-T/12270,TF-180,13' F/1435-T/1448,13-MIN)(F/12353-T/12363 TF-180,10' F/1517-T/1530,13-MIN)(F/12547-T/12562,TF-180,15'F/1628-T/1655,27-MIN)
SABINE D 4H | 12 | 2021-03-15 17:30 | 2021-03-15 18:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.27 | 12632 | 12632 | 0 | RIG SERVICE
SABINE D 4H | 12 | 2021-03-15 18:00 | 2021-03-15 22:30 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.46 | 12632 | 13253 | 138 | ROT 621' IN 4.37 HRS @ 142 FPH) WOB-25/45K SPM-76/76/0 GPM-398, RPM-80, MRPM-271, TMRPM-351, TRQ-10/14K, SPP-3700/4700 PSI, DIFF-800/1000 PSI, CHOKES- 100%/100%, FLARE-5-15', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 4 PPB NEWCARB, 4 PPB NEWPHALT
SABINE D 4H | 12 | 2021-03-15 22:30 | 2021-03-16 06:00 | 7.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.77 | 13253 | 13420 | 22.3 | SLIDE 167 IN 7.63 HRS @ 22 FPH) WOB-25/45K SPM-76/76/0 GPM-398, MRPM-271, SPP-3600/4000 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE=0-15' CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. SLIDE DEPTHS: (F/12642 T/12652 TF-160L 10' MIN-20 1805-1825)(F/12750 T/12760 TF-180 10' MIN-15 1900-1915)(F/12920 T/12935 TF-HS 15' MIN-24 2015-2039)(F/13015 T/13039 TF-HS 24' MIN-58 2110-2218)(F/13085 T/13108 TF-HS 23' MIN-38 2236-2314)(F/13108 T/13120 TF-HS 12' MIN-30 2325-2355)(F/13155 T/13167 TF-HS 12' MIN-34 0010-0044)(F/13210 T/13235 TF-HS 25' MIN-25 0105-0205)(F/13333 T/13343 TF-180 10' MIN-48 0248-0336)(F/13394 T/13420 TF-180 26' MIN-110 0410-0600)
SABINE D 4H | 13 | 2021-03-16 06:00 | 2021-03-16 11:00 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.98 | 13420 | 14004 | 116.8 | ROT 584' IN 5.18 HRS @ 113 FPH) WOB-25/45K SPM-76/76/0 GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-14/18K, SPP-3900/4900 PSI, DIFF-800/1000 PSI, CHOKES- 100%/100%, FLARE-5-15', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 4 PPB NEWCARB, 4 PPB NEWPHALT
SABINE D 4H | 13 | 2021-03-16 11:00 | 2021-03-16 19:00 | 8 | p | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.31 | 14004 | 14159 | 19.4 | SLIDE 155' IN 7.82 HRS @ 20 FPH) WOB-25/45K SPM-76/76/0 GPM-400, MRPM-272, SPP-3900/4300 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE=0-15' CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. SLIDE DEPTHS: (F/13420- T/13426,TF-180,5',F/600-T/630,30-MIN)(F/13457-T/13472,TF-180,15'F/655-T/735,40-MIN)(F/13500-T/13520,TF-180,20',F/800-T/845,45-MIN)(F/13678-T/13708,TF-180,30',F/1010-T/1130,80-MIN)(F/13783-T/13798,TF-180,15', F/1200-T/1305,65-MIN)(F/13869-T/13914,TF-180,45' F/1340-T/1615,155-MIN)(F/14063-T/14066 TF-180, 3 ' F/1745-T/1800,15-MIN)(SLD F/14066 T/14095 TF-180 29' MIN-39 1800-1839)
SABINE D 4H | 13 | 2021-03-16 19:00 | 2021-03-16 19:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.33 | 14159 | 14159 | 0 | CODE:RIGMT SUB CODE:SVCRIG …….RIG SERVICE
SABINE D 4H | 13 | 2021-03-16 19:30 | 2021-03-17 00:30 | 5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.54 | 14159 | 14815 | 131.2 | ROT 656' IN 5.07 HRS @ 129 FPH) WOB-25/45K SPM-76/76/0 GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-14/18K, SPP-4100/5300 PSI, DIFF-900/1200 PSI, CHOKES- 100%/100%, FLARE-5-15', CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 4 PPB NEWCARB, 4 PPB NEWPHALT
SABINE D 4H | 13 | 2021-03-17 00:30 | 2021-03-17 06:00 | 5.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 10.77 | 14815 | 14949 | 24.4 | SLIDE 134' IN 5.43 HRS @ 25 FPH) WOB-25/45K SPM-76/76/0 GPM-400, MRPM-272, SPP-4100/4500 PSI, DIFF-200/400 PSI, CHOKES- 100%/100%, FLARE=0-15' CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI.
SABINE D 4H | 14 | 2021-03-17 06:00 | 2021-03-17 08:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 10.85 | 14949 | 15163 | 107 | ROT (214' IN 1.95HRS @ 109.7 FPH) WOB-25/45K SPM-76/76 GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-14/21K, SPP-4900/5300 PSI, DIFF-800/1100 PSI, CHOKE #2- 100%, NO FLARE, CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. NOTE: PUMPING 10 BBL 10 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 4 PPB NEWCARB, 4 PPB NEWPHALT
SABINE D 4H | 14 | 2021-03-17 08:00 | 2021-03-17 12:30 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 11.04 | 15163 | 15209 | 10.2 | SLIDE (46' IN 4.55 HRS @ 10.11 FPH) WOB-25/45K SPM-76/76/0 GPM-400, MRPM-272, SPP-3900/4300 PSI, DIFF-200/400 PSI, CHOKE #2- 100%, NO FLARE, CASING PSI WHILE DRILLING=0 PSI, CASING PSI DURING CONNECTIONS=0 PSI. SLIDE DEPTHS: SLD F/ 15024' T/ 15054' 30' TF-140R, 80 MINS 0640-0800, SLD F/ 15108' T/ 15118' 10' TF-180 76 MINS 0835-0951, SLD F/ 15203' T/ 15209' 6' TF-180 117 MINS 1033-1230
SABINE D 4H | 14 | 2021-03-17 12:30 | 2021-03-17 13:30 | 1 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.08 | 15209 | 15209 | 0 | BACK REAM OUT OF HOLE F/ 15,209' T/ 15,014', WHILE BACK REAMING OUT OF HOLE TRQ-14/26K, TOP DRIVE STALLING OUT AND WELL PACKING OFF, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-14/26K, SPP-4100/5300, #2 CHOKE 100%, NO FLARE, CASING PSI-0 PSI, CASING PRESSURE DURING CONNECTION-0 PSI. NOTE: DECISION MADE TO SIDETRACK WELL @ 14568' MD / 10752' TVD
SABINE D 4H | 14 | 2021-03-17 13:30 | 2021-03-17 14:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.13 | 15209 | 15209 | 0 | RECIPROCATE DRILL STRING AND CIRCULATE BOTTOMS UP, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-7/12K, SPP-4000/4100, NO FLARE, CASING PRESSURE-0 PSI
SABINE D 4H | 14 | 2021-03-17 14:30 | 2021-03-17 15:00 | 0.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.15 | 15209 | 15209 | 0 | BACK REAM OUT OF HOLE F/ 15,014' T/ 14,538', SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-7/14K, SPP-3600/3800, #2 CHOKE 100%, NO FLARE, CASING PSI-0 PSI, CASING PRESSURE DURING CONNECTION-0 PSI.
SABINE D 4H | 14 | 2021-03-17 15:00 | 2021-03-17 17:30 | 2.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 11.25 | 14568 | 14568 | 0 | BUILD TROUGH F/14,538' T/14,568' @ 120R, GPM-400, SPP-4000/4100 PSI, CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, NO SUCCESS IN BUILDING TROUGH, DRILL STRING WEIGHT STACKING OUT AND NOT ABLE TO MAINTAIN TOOLFACE 120R.
SABINE D 4H | 14 | 2021-03-17 17:30 | 2021-03-17 20:00 | 2.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.35 | 14568 | 14568 | 0 | BACK REAM OUT OF HOLE F/ 14,538' T/ 13,584' ,WASH/REAM F/13,584' T/14,538', SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-7/14K, SPP-3600/3800,CHOKES- 100% / 100%, FLARE-3'-5', NO MUD CUT, MAX GAS-1816u, CASING PSI-0 PSI, CASING PRESSURE DURING CONNECTION-0 PSI.
SABINE D 4H | 14 | 2021-03-17 20:00 | 2021-03-17 20:30 | 0.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 11.38 | 14568 | 14568 | 0 | BUILD TROUGH F/14,538' T/14,568' @ 120R, GPM-400, SPP-4000/4100 PSI, CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, NO SUCCESS IN BUILDING TROUGH, DRILL STRING WEIGHT STACKING OUT AND NOT ABLE TO MAINTAIN TOOLFACE 120R.
SABINE D 4H | 14 | 2021-03-17 20:30 | 2021-03-17 21:30 | 1 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 11.42 | 14568 | 14568 | 0 | WASHREAM F/14.568' T/14,919', BACK REAM OUT OF HOLE F/ 14,919' T/ 14,538', SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-351, TRQ-7/14K, SPP4000/4200,CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, CASING PSI-0 PSI, CASING PRESSURE DURING CONNECTION-0 PSI.
SABINE D 4H | 14 | 2021-03-17 21:30 | 2021-03-17 22:30 | 1 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 11.46 | 14568 | 14568 | 0 | BUILD TROUGH F/14,538' T/14,568' @ 120R, GPM-400, SPP-4000/4100 PSI, CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI.
SABINE D 4H | 14 | 2021-03-17 22:30 | 2021-03-18 06:00 | 7.5 | U | PRDHLLT | DRLG | DRLST | TIME DRILLING | 11.77 | 14568 | 14582 | 1.9 | BEGIN OPEN HOLE SIDETRACK 14,568' MD / 10,752' TVD ON 3/17/2021 @ 22:30. TIME DRILL F/14,568' T/14,582', GPM-400,SPP-4000/4100 PSI, CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE = 0 PSI.
SABINE D 4H | 15 | 2021-03-18 06:00 | 2021-03-18 08:30 | 2.5 | U | PRDHLLT | DRLG | CTLDRL | CONTROL DRILLING | 11.88 | 14568 | 14650 | 32.8 | CONTROL SLIDE/ROTATE DRILLING F/14,582' T/14,650'' @ 5-30 FPH, TF-90R, WOB-10/20K, GPM-400, SPP-4100/4800 PSI, DIFF-200/900 PSI, CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI. NOTE: SUCCESSFUL OPEN HOLE SIDE TRACK ON 03/18/2021 @ 06:00.
SABINE D 4H | 15 | 2021-03-18 08:30 | 2021-03-18 13:00 | 4.5 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.06 | 14650 | 14924 | 60.9 | "ROT 274' IN 4.43 HRS @ 61.9 FPH) WOB-25/35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-12/21K, SPP-4000/5100 PSI, DIFF-900/1100 PSI, CHOKES- 100% / 100%, FLARE-0' @ BOTTOMS UP, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI. NOTE: F/ 14,850’ T/ 14/950” REDUCE TOP DRIVE RPM F/ 80 RPM T/ 40 RPM T/ PASS DRILL N REAM REAMER THROUGH SIDETRACK.NOTE: PUMPING 15 BBL 6 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 2 PPB NEWCARB, 2 PPB NEWPHALT
SABINE D 4H | 15 | 2021-03-18 13:00 | 2021-03-18 18:30 | 5.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.29 | 14924 | 15014 | 16.4 | SLIDE (90' IN 5.57 HRS @ 16.2 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-272, SPP-4000/4400 PSI, DIFF-200/400 PSI. SLIDE DEPTHS: SLD F/14650 T/14690 40' TF-20L 830-1018 / SLD F/14789 T/14819 30' TF-150L 1141-1319 / SLD F/14919 T/14939 20' TF-130L 1512-1720
SABINE D 4H | 15 | 2021-03-18 18:30 | 2021-03-18 19:00 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 12.31 | 15014 | 15014 | 0 | CODE:RIGMT SUB CODE:SVCRIG …….RIG SERVICE
SABINE D 4H | 15 | 2021-03-18 19:00 | 2021-03-18 22:00 | 3 | U | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 12.44 | 15014 | 15133 | 39.7 | ROT (119' IN 3.07 HRS @ 39 FPH) WOB-30-35K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-11-23K, SPP-3800/5000 PSI, DIFF-800/1200 PSI, CHOKES- 100% / 100%, FLARE-0' @ BOTTOMS UP, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI. NOTE: PUMPING 15 BBL 6 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 2 PPB NEWCARB, 2 PPB NEWPHALT
SABINE D 4H | 15 | 2021-03-18 22:00 | 2021-03-19 03:30 | 5.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.67 | 15133 | 15207 | 13.5 | SLIDE (74' IN 5.23 HRS @ 14 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-272, SPP-3800/4200 PSI, DIFF-200/400 PSI. SLIDE DEPTHS: SLD F/15014' T/15039' 25' TF-180 1912-2030, SLD F/15073' T/15093' 20' TF-150L 2115-2215, SLD F/15109' T/15134' 25' TF-150L 2245-0011, SLD F/15203' T/15207' 4' TF-90L 0200-0330 NOTE: DRILL STRING WEIGHT STACKING OUT AND NOT DRILLING OFF.
SABINE D 4H | 15 | 2021-03-19 03:30 | 2021-03-19 04:00 | 0.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 12.69 | 15207 | 15207 | 0 | 3 STD CLEAN UP TRIP; BACK REAM F/15,207' T/14,919'; REAM BACK TO BTM; SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-11-15K, SPP-3800/3900 PSI
SABINE D 4H | 15 | 2021-03-19 04:00 | 2021-03-19 04:30 | 0.5 | U | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 12.71 | 15207 | 15210 | 6 | SLIDE (3' IN .5 HRS @ 4 FPH) WOB-35/45K SPM-76/76, GPM-400, MRPM-272, SPP-3800/4200 PSI, DIFF-200/400 PSI. NOTE: OFF OPEN HOLE SIDETRACK OPERATIONS NPT @ 15,209' ON 03/19/2021 @ 04:30. SLIDE DEPTHS: SLD F/15207' T/15210' 3' TF-90L 0400-0416 NOTE: DRILL STRING WEIGHT STACKING OUT AND NOT DRILLING OFF, DECISION WAS MADE TO POOH AND CHANGE OUT BHA.
SABINE D 4H | 15 | 2021-03-19 04:30 | 2021-03-19 06:00 | 1.5 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 12.77 | 15210 | 15210 | 0 | BACK REAM OUT OF HOLE F/15,210' T/14,500', SPM-76/76. GPM-400, RPM-80, TRQ-8/17K, SPP-3600/3700 PSI, CHOKES- 100% / 100%, NO FLARE, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP=0 PSI, AVG SICP= 0 PSI. NOTE: REDUCE TOP DRIVE TO 40 RPM WHILE BACKREAMING REAMER THROUGH SIDETRACK; ATTEMPT TO PULL ON ELEVATORS WITH NO SUCCESS - WORK THROUGH SIDETRACK @ 14,568'; PULL THROUGH SIDE TRACK, ORIENTATE TF 120 DEG, SLACK OFF BACK THROUGH SIDETRACK, PUMP UP SURVEY TO VERIFY IN SIDETRACK.
SABINE D 4H | 16 | 2021-03-19 06:00 | 2021-03-19 06:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.79 | 15210 | 15210 | 0 | WORK THROUGH SIDETRACK @ 14,568' AND SLACK OFF T/ 14,719', PUMP UP SURVEY T/ VERIFY IN SIDETRACK WELLBORE, PULL THROUGH SIDETRACK WITH 75-120K OVERPULL.
SABINE D 4H | 16 | 2021-03-19 06:30 | 2021-03-19 10:30 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 12.96 | 15210 | 15210 | 0 | STRIP OUT OF HOLE F/ 14,500’ T/ 10,193’ PUMPING CALCULATED HOLE FILL 1.9 BBLS PER STAND DOWN BACKSIDE W/ 9.0 PPG
SABINE D 4H | 16 | 2021-03-19 10:30 | 2021-03-19 12:00 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.02 | 15210 | 15210 | 0 | CIRCULATE BOTTOMS UP @ GPM=325, SPP=2300, RPM=30, TRQ=4/6K, MAX GAS=1298 UNITS, NO FLARE, NO MUD CUT, MONITOR SICP F/ 15 MINUTES, SICP=0 PSI, OPEN ORBIT VALVE, FLOW CHECK WELL ON TRIP TANK, WELL FLOWING 2.5 BPH, WELL FLOWED BACK 2 BBLS, CLOSE ORBIT VALVE, CASING PRESSURE INCREASED T/ 83 PSI
SABINE D 4H | 16 | 2021-03-19 12:00 | 2021-03-19 13:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.06 | 15210 | 15210 | 0 | CIRCULATE BOTTOMS UP @ GPM=325, SPP=2300, RPM=30, TRQ=4/6K, MAX GAS=551 UNITS, NO FLARE, NO MUD CUT, SPOT 50 BBL 16.0 PPG MUD CAP @ 10,148’, (TOP OF MUD CAP AFTER PULLING OUT OF HOLE ABOVE MUD CAP 9,009’)
SABINE D 4H | 16 | 2021-03-19 13:00 | 2021-03-19 14:30 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.13 | 15210 | 15210 | 0 | STRIP OUT OF HOLE F/ 10,148’ T/ 9,000’, PUMPING CALCULATED HOLE FILL 1.9 BBLS PER STAND DOWN BACKSIDE W/ 9.0 PPG, FLOW CHECK WELL, WELL STATIC, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE, PUMP SLUG
SABINE D 4H | 16 | 2021-03-19 14:30 | 2021-03-19 18:00 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.27 | 15210 | 15210 | 0 | TRIP OUT THE HOLE F/8,514' T/BHA, HOLE TAKING PROPER FILL, FLOW CHECK @ 2,540', L/D AGITATOR ON STAND 27. FLOW CHECK @ BHA (NO FLOW). NOTE: POOH @ 150 FT/MIN DUE TO HOLE SWABBING @ 200 FT/MIN TRIP SPEED
SABINE D 4H | 16 | 2021-03-19 18:00 | 2021-03-19 18:30 | 0.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.29 | 15210 | 15210 | 0 | REMOVE MWD, RACK BACK MONELS, L/D THRUSTER AND BTI VALVE, BREAK BIT AND L/D MOTOR. NOTE: INSPECTED MOTOR AND BIT, OBSERVED MOTOR WAS DRY, 1/4" PLAY AND EXCESSIVE SLACK IN LOWER SECTION OF MOTOR, BIT DULL GRADE: DBR (CRACK IN GAUGE, MISSING JET AND 1/8" OUT OF GAUGE.
SABINE D 4H | 16 | 2021-03-19 18:30 | 2021-03-19 19:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.33 | 15210 | 15210 | 0 | PICK UP 6.75" ULTERRA U613S SER #53719 JETS 6/18S TFA: 1.491, 5.25",6/7L, 8.8 STG @ 2.00° SLICK HS88 .018; .68 REV/GAL; 4.02' BIT TO BEND 5-1/2" PAD OD;FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTIVALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMDC, 5" TOMAX THRUSTER, X/O XT-39 P x DS 42B, 2 STANDS, DRILL-N-REAM REAMER, 25 STANDS, AGITATOR, BIT TO SVY-67'. BIT TO GAMMA-58'.
SABINE D 4H | 16 | 2021-03-19 19:30 | 2021-03-19 21:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.4 | 15210 | 15210 | 0 | ATTEMPTED TO SURFACE TEST MWD, MWD TOOL WAS PULSING WITH OUT THE ROTARY, TURNED ROTARY @ 50 RPM TO ENSURE THE TOOL WENT INTO ROTATIONAL MODE, RACK BACK MONEL, REMOVE MWD AND TURN ON ROTATIONAL TRIGGER ON MWD TOOL. INSTALL MWD AND MAKE UP MONEL. TEST MWD (TEST GOOD).
SABINE D 4H | 16 | 2021-03-19 21:00 | 2021-03-20 01:00 | 4 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.56 | 15210 | 15210 | 0 | TRIP IN THE HOLE F/BHA T/9,018', PICK UP AGITATOR AFTER STAND 27, PSI. BEFORE AGITATOR-1150 PSI. PSI AFTER AGITATOR-1410 PSI @ 275 GPM, HOLE GIVING PROPER DISPLACEMENT, FILL PIPE EVERY 40 STANDS. REMOVE TRIP NIPPLE/INSTALL ROTATING HEAD.
SABINE D 4H | 16 | 2021-03-20 01:00 | 2021-03-20 02:00 | 1 | U | PRDHLLT | RIGMT | CUTDL | SLIP / CUT DRL LINE | 13.6 | 15210 | 15210 | 0 | RIGMT, CUTDL, SLIP AND CUT 80' DRILLINE.
SABINE D 4H | 16 | 2021-03-20 02:00 | 2021-03-20 02:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 13.63 | 15210 | 15210 | 0 | RIGMT, SVCRIG, SERVICE TOP DRIVE, BLOCK AND CROWN.
SABINE D 4H | 16 | 2021-03-20 02:30 | 2021-03-20 03:30 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.67 | 15210 | 15210 | 0 | CONTINUE TRIPPING IN THE HOLE F/9,018' T/11,391', HOLE GIVING PROPER DISPLACEMENT.
SABINE D 4H | 16 | 2021-03-20 03:30 | 2021-03-20 04:30 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.71 | 15210 | 15210 | 0 | FILL PIPE, SLOWLY STAGED UP PUMPS TO 400 GPM, CIRCULATE OUT MUD CAP THROUGH GAS SEPARATOR AND RECIPROCATE PIPE, GPM-400, SPP-3800, RPM-30, TQ-7K/9K, MAX GAS-2900u, CHOKES- 0% / 75%, 5' FLARE, NO MUDCUT, MAX CASING PRESSURE=0 PSI. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 11 PPG WAS @ SURFACE, MAX MUD WT.- 14.3 PPG, DIVERTED 76 BBLS TO OPEN TOP.
SABINE D 4H | 16 | 2021-03-20 04:30 | 2021-03-20 06:00 | 1.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 13.77 | 15210 | 15210 | 0 | STRIP IN THE HOLE F/11,391' T/14,000' BLEEDING BACK 1.9 BBLS/STAND CALUCATED DISPLACEMENT, MAX CASING PRESSURE= 0 PSI.
SABINE D 4H | 17 | 2021-03-20 06:00 | 2021-03-20 07:30 | 1.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 13.83 | 15210 | 15210 | 0 | CIRCULATE BOTTOMS UP @ 14,500’ DUE T/ ERRATIC FLOW AND PVT GAIN, GPM=400, SPP=4200/4300, RPM=70, TRQ=7/14K, MAX GAS=3381 UNITS, MAX CASING PSI=238 PSI, FLARE= 5’-10’, MUD CUT F/ 9.0 PPG T/ 8.7 PPG, ORIENT TOOLFACE 120R, SLACK OFF THROUGH SIDETRACK T/ 14,730’, PUMP UP SURVEY T/ VERIFY IN SIDETRACK WELLBORE
SABINE D 4H | 17 | 2021-03-20 07:30 | 2021-03-20 09:30 | 2 | U | PRDHLLT | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 13.92 | 15210 | 15210 | 0 | WASH & REAM F/ 14730’ T/15,210’, TAKE 6 CHECKSHOT SURVEYS AS PER MWD TECH @ F/ 14,730' T/ 15,210' (REDUCE TOP DRIVE RPM T/ 30 RPM T/ PASS DRILL N REAMER THROUGH SIDETRACK) NOTE: OFF NPT F/ BHA ROP @ 15,210' ON 3/20/2021 @ 09:30.
SABINE D 4H | 17 | 2021-03-20 09:30 | 2021-03-20 12:30 | 3 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.04 | 15210 | 15607 | 132.3 | ROT (397' IN 3.05 HRS @ 130.16 FPH) WOB-30/40K SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-12/20K, SPP-4900/5200 PSI, DIFF-700/900 PSI, CHOKE #2 100%, FLARE-0' @ BOTTOMS UP, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 0 PSI, AVG SICP= 0 PSI. NOTE: PUMPING 10 BBL 6 PPB LCM SWEEPS EVERY 300'. SWEEP CONTENTS: 2 PPB MAGNAFIBER, 2 PPB NEWCARB, 2 PPB NEWPHALT. NOTE: BACK REAMING 1 STAND AS NEED PRIOR TO SLIDING.
SABINE D 4H | 17 | 2021-03-20 12:30 | 2021-03-20 16:00 | 3.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.19 | 15607 | 15677 | 20 | SLIDE (70' IN 3.45 HRS @ 20.29 FPH) WOB-25/35K SPM-76/76, GPM-400, MRPM-272,SPP-4200/4400 PSI, DIFF-100/200 PSI. SLIDE DEPTHS: SLD F/15210' T/15240' 30' TF-90L 0930-1107; SLD F/15300' T/15320' 20' TF-130L 1154-1236; SLD F/15394' T/15414' 20' TF-90L 1317-1424.
SABINE D 4H | 17 | 2021-03-20 16:00 | 2021-03-20 16:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 14.21 | 15677 | 15677 | 0 | RIGMT, SVCRIG, SERVICE TOP DRIVE, BLOCK AND CROWN.
SABINE D 4H | 17 | 2021-03-20 16:30 | 2021-03-20 22:30 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.46 | 15677 | 16314 | 106.2 | ROT 637' IN 5.97 HRS @ 107 FPH) WOB-35/45K SPM-57/57, GPM-300, RPM-80, MRPM-238, TMRPM-318, TRQ-14/20K, SPP-2600/3700 PSI, DIFF-900/1100 PSI, BOTH CHOKES-100% / 100%; CHOKE #1 -0% #2-100% @ BTM'S UP AND FLARE-5'-10' @ BTM'S UP, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 145 PSI, AVG SICP= 0 PSI. NOTE: ENCOUNTERED 35-40 BPH LOSSES WITH 93%-94% RETURNS @ 15,798’, DECREASED PUMP RATE F/400 GPM T/350 GPM, PUMPING 10 BBL 6 PPB LCM SWEEPS EVERY STAND CONSISTING OF 2PPB MAGNAFIBER, 2PPB NEWCARB, 2PPB NEWPHALT AND ADDING 5 SXS/HR EACH OF FIRST RESPONSE AND NEWCARB TO ACTIVE SYSTEM, BEGAN CUTTING MUD WT. F/9.0 PPG T/8.8 PPG. ONCE A 8.8 PPG WAS AT SURFACE @ 16,089', LOSSES DECREASED T/2-4 BPH. MOTOR STALLED OUT @ 16,239' AND STARTED ENCOUNTERING 100-130 BPH LOSSES WITH 74%-80% RETURNS, DECREASED PUMP RATE F/350 GPM T/300 GPM, PUMPED A 50 BBL LCM SWEEP AND BEGAN CUTTING MUD WT. F/8.8 PPG T/8.7 PPG, UNABLE TO GET MUD WT. CUT BACK BELOW 8.8 PPG WHILE ADDING 35 BPH DIESEL AND RUNNING THE CENTRIFUGE, LOSSES DECREASED T/43 BPH @ 16,350' NOTE: PUMPING 10 BBL 20PPB LCM SWEEPS EVERY STAND CONSISTING OF 4 PPB MAGNAFIBER, 4 PPB NEWCARB, 2 PPB NEWPHALT AND ADDING 5 SXS/HR EACH OF FIRST RESPONSE AND NEWCARB TO ACTIVE SYSTEM. NOTE: BACK REAMING 1 STAND AS NEED PRIOR TO SLIDING.
SABINE D 4H | 17 | 2021-03-20 22:30 | 2021-03-21 03:00 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 14.65 | 16314 | 16401 | 19.3 | SLIDE (87' IN 4.53 HRS @ 19 FPH) WOB-25/35K SPM-67/67, GPM-350, MRPM-238, SPP-2600/3000 PSI, DIFF-200/400 PSI. SLIDE DEPTHS: SLD F/15,774' T/15,800' 26' TF-150R 1700-1900, SLD F/15,869' T/15,886' 15' TF-150R 1930-2000, SLD F/16,059' T/16,089' 30' TF-180 2145-2300, SLD F/16,154' T/16,168' 15' TF-130R 2330-0017
SABINE D 4H | 17 | 2021-03-21 03:00 | 2021-03-21 03:30 | 0.5 | U | PRDHLLT | DPROB | DFAIL | DOWNHOLE FAILURE | 14.67 | 16401 | 16401 | 0 | LOST COMMUNICATION WITH MWD TOOL
SABINE D 4H | 17 | 2021-03-21 03:30 | 2021-03-21 06:00 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.77 | 16401 | 16661 | 104 | ROT 260' IN 2.5 HRS @ 104 FPH) WOB-35/45K SPM-57/57, GPM-300, RPM-80, MRPM-238, TMRPM-318, TRQ-14/20K, SPP-2600/3700 PSI, DIFF-900/1100 PSI, BOTH CHOKES-100% / 100%; CHOKE #1 -0% #2-100% @ BTM'S UP AND FLARE-5'-10' @ BTM'S UP, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 200 PSI, AVG SICP= 0 PSI. NOTE: ENCOUNTERING LOSSES @20-30 BPH. PUMPING 10 BBL 20PPB LCM SWEEPS EVERY STAND CONSISTING OF 4 PPB MAGNAFIBER, 4 PPB NEWCARB, 2 PPB NEWPHALT AND ADDING 5 SXS/HR EACH OF FIRST RESPONSE AND NEWCARB TO ACTIVE SYSTEM. NOTE: BACK REAMING 1 STAND AS NEED PRIOR TO SLIDING.
SABINE D 4H | 18 | 2021-03-21 06:00 | 2021-03-21 06:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.79 | 16661 | 16724 | 126 | ROT(63' IN .5 HRS @ 126 FPH) WOB-35/45K SPM-57/57, GPM-300, RPM-80, MRPM-238, TMRPM-318, TRQ-14/20K, SPP-2600/3700 PSI, DIFF-900/1100 PSI, BOTH CHOKES-100% / 100%; CHOKE #1 -0% #2-100% @ BTM'S UP AND FLARE-5'-10' @ BTM'S UP, NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI, SHUTTING IN ON CONNECTION, MAX SICP= 700 PSI, AVG SICP= 0 PSI. NOTE: PUMPING 10 BBL 20PPB LCM SWEEPS EVERY STAND CONSISTING OF 4 PPB MAGNAFIBER, 4 PPB NEWCARB, 2 PPB NEWPHALT AND ADDING 5 SXS/HR EACH OF FIRST RESPONSE AND NEWCARB TO ACTIVE SYSTEM. NOTE: AVERAGE LOSSES 20/30 BBL/HR
SABINE D 4H | 18 | 2021-03-21 06:30 | 2021-03-21 10:00 | 3.5 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 14.94 | 16724 | 16724 | 0 | AFTER MAKING CONNECTION, CASING PSI INCREASED T/MAX CSG PSI 1300 PSI; GAIN 10-15 BBLS OF MUD; SHUT WELL IN ON VARIABLE CASING RAMS TO CIRCULATE GAS FROM WELLBORE; INCREASE MUD WT. F/8.7 PPG T/9.0 PPG; GPM-300, SPP-2950 PSI, CSG PSI 300-1100 PSI, MUD CUT F/8.7 PPG T/8.3 PPG; CHOKE: 0% - 35%, FLARE 30-40' NOTE: ROTATING PIPE WHEN POSSIBLE DUE TO EXCESSIVE CASING PSI.
SABINE D 4H | 18 | 2021-03-21 10:00 | 2021-03-21 10:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 14.96 | 16724 | 16820 | 192 | ROT (96' IN .5 HRS @ 192 FPH) WOB-35/45K SPM-57/57, GPM-300, RPM-80, MRPM-238, TMRPM-318, TRQ-14/20K, SPP-2600/3700 PSI, DIFF-900/1100 PSI, CHOKES-0% / 30%; FLARE-10'-30' @ BTM'S UP, MUD CUT F/9.0 PPG T/8.7 PPG, MAX CASING PRESSURE=1000 PSI, AVG CASING PRESSURE= 400 PSI
SABINE D 4H | 18 | 2021-03-21 10:30 | 2021-03-21 10:30 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 14.96 | 16820 | 16820 |  | MILESTONE_TD WELL 03/21/2021 @ 10:30
SABINE D 4H | 18 | 2021-03-21 10:30 | 2021-03-21 15:30 | 5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.17 | 16820 | 16820 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN. PUMP 3-30 BBL 30 PPB LCMSWEEPS IN TANDEM, CONDITION MUD & CIRCULATE 5 B/U, RPM-80, SPM: 57/57, GPM-300, TRQ-9/13K, SPP-2900 PSI, CHOKES- 0% - 30%, FLARE-10'-15', MUD CUT F/9.0 PPG T/8.8 PPG, MAX CASING PRESSURE=1000 PSI, MAX GAS: 3380u. AFTER CIRCULATING 2.5 BOTTOMS UP, SHUT WELL IN, MONITOR SICP, SICP=698 PSI, CONTINUE WITH CLEAN-UP CYCLE INCREASING MUD WEIGHT F/ 9.0 PPG T/ 9.2 PPG AND INCREASED GPM F/ 300 T/ 350, FINAL SICP AFTER CLEAN-UP CYCLE 455 PSI. 1ST BTM UP START TQ=16K, END= 13K, P/UWT=320K, S/O=165K, ROT=220K 2ND BTM UP END TQ= 14K, P/U WT= 320, S/O= 165K, ROT= 220K 3RD BTM UP END TQ=12K, P/U WT= 320K, S/O WT= 165K, ROT= 217K LOSS OF 4K TORQUE FROM DOING CLEAN UP CYCLE, SHAKERS CLEAN.
SABINE D 4H | 18 | 2021-03-21 15:30 | 2021-03-21 19:00 | 3.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 15.31 | 16820 | 16820 | 0 | BACK REAM OUT OF HOLE F/16,820' T/14,730', SPM-67/67. GPM-350, RPM-80, TRQ-8/17K, SPP-3600/3700 PSI, CHOKES- 0% / 30-40%, FLARE= 5'-10', NO MUD CUT, MAX CASING PRESSURE=487 PSI, AVG CASING PRESSURE= 425 PSI, SHUTTING IN ON CONNECTION, MAX SICP=525 PSI, AVG SICP= 450 PSI, MAX GAS-3622u. NOTE: REDUCE TOP DRIVE TO 40 RPM WHILE BACKREAMING REAMER THROUGH SIDETRACK; ORIENTATE TF 120 DEG' WORK THROUGH SIDETRACK @ 14,568'; PULL THROUGH SIDE TRACK, SLACK OFF BACK THROUGH SIDETRACK, PUMP UP SURVEY TO VERIFY IN SIDETRACK. 75/130K OVERPULL T/ PULL THROUGH SIDETRACK, 30/50K DRAG T/ SLACKOFF THROUGH SIDETRACK.
SABINE D 4H | 18 | 2021-03-21 19:00 | 2021-03-21 21:30 | 2.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.42 | 16820 | 16820 | 0 | STRIP OUT OF HOLE F/ 14,568’ T/ 10,161’ WITH WET PIPE, PUMPING CALCULATED HOLE FILL 1.9 BBLS PER STAND DOWN BACKSIDE W/ 9.2 PPG, MAX CSG PSI= 561 PSI, AVG CSG PSI= 500 PSI.
SABINE D 4H | 18 | 2021-03-21 21:30 | 2021-03-21 22:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 15.46 | 16820 | 16820 | 0 | CIRCULATE BOTTOMS UP, GPM-350, SPP-2900 PSI, CHOKES- 0% / 30-35%, LOSS 47 BBLS, FLARE-5-15', MUD CUT F/9.2 PPG T/8.8 PPG, MAX CASING PRESSURE=620 PSI, AVG CASING PRESSURE= 300 PSI, MAX GAS-3641u. SHUT DOWN MUD PUMPS AND MONITOR SICP F/ 20 MINUTES, INITIAL SICP= 505 PSI, SICP BLED DOWN T/475 PSI.
SABINE D 4H | 18 | 2021-03-21 22:30 | 2021-03-21 23:30 | 1 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 15.5 | 16820 | 16820 | 0 | SPOT 116 BBL 16.0 PPG OBM MUD CAP @ 10,148' (300 PSI OVER BALANCE MUD CAP). SHUT IN AND MONITORED CASING PRESSURE. SICP BEFORE CAP-475 PSI / AFTER-0 PSI TOP OF MUD CAP-7,628'
SABINE D 4H | 18 | 2021-03-21 23:30 | 2021-03-22 00:30 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.54 | 16820 | 16820 | 0 | STRIP OUT OF HOLE F/ 10,148' T/ 7,628’ WITH DRY PIPE, PUMPING CALCULATED HOLE FILL .64 BBLS PER STAND DOWN BACKSIDE W/ 9.2 PPG, MAX CSG PSI=0 PSI.
SABINE D 4H | 18 | 2021-03-22 00:30 | 2021-03-22 06:00 | 5.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.77 | 16820 | 16820 | 0 | FLOW CHECK (NO FLOW), PUMP SLUG, TRIP OUT THE HOLE LAYING DRILL PIPE F/7,628' T/1,800', REMOVE ROTATING HEAD/INSTALL TRIP NIPPLE, L/D AGITATOR ON STAND 27, FLOW CHECK WELL @2,978' (NO FLOW). 40.2 BBLS CALCULATED FILL AND 57 BBLS ACTUAL FILL, LOST 16.8 BBLS WHILE TRIPPING OUT THE HOLE.
SABINE D 4H | 19 | 2021-03-22 06:00 | 2021-03-22 08:00 | 2 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.85 | 16820 | 16820 | 0 | TRIP OUT THE HOLE LAYING DRILL PIPE F/1800' T/BHA, FLOW CHECK, WELL STATIC, 52 BBLS CALCULATED FILL AND 92 BBLS ACTUAL FILL, LOST 40 BBLS FOR TOTAL TRIP OUT THE HOLE L/D DRILL PIPE AND BHA.
SABINE D 4H | 19 | 2021-03-22 08:00 | 2021-03-22 09:00 | 1 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 15.9 | 16820 | 16820 | 0 | REMOVE MWD TOOL, DRAIN MOTOR, BREAK OFF BIT, LAY DOWN DIRECTIONAL BHA
SABINE D 4H | 19 | 2021-03-22 09:00 | 2021-03-22 10:00 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 15.94 | 16820 | 16820 | 0 | CODE - RURD, SUB-CODE - RDEQP, REMOVE WEAR BUSHING, REMOVE MOUSE HOLE, CLEAN AND ORGANIZE RIG FLOOR T/ MITIGATE SLIP AND TRIP HAZARDS.
SABINE D 4H | 19 | 2021-03-22 10:00 | 2021-03-22 12:00 | 2 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.02 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RUEEQP, PRE-JOB SAFETY MEETING, RIG UP FRANKS CASING EQUIPMENT AND CRT.
SABINE D 4H | 19 | 2021-03-22 12:00 | 2021-03-22 17:30 | 5.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.25 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY TORQ SFW CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY TORQ SFW CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY TORQ SFW CSG, CIRC THROUGH CASING TO TEST FLOATS-GOOD. PICK UP AND RUN 5" 18# P110 ICY TORQ SFW PRODUCTION CASING T/6,664', FILLING PIPE ON THE FLY. MONITOR DISPLACEMENTS ON TRIP TANK, 160 BBLS CALCULATED DISPLACEMENTS AND 165.5 BBLS DISPLACEMENTS, GAIN 5.3 BBLS DISPLACEMENTS F/ RUNNING 5" CASING, WELL FLOWING, SHUT WELL IN
SABINE D 4H | 19 | 2021-03-22 17:30 | 2021-03-22 18:00 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 16.27 | 16820 | 16820 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD ASSEMBLY.
SABINE D 4H | 19 | 2021-03-22 18:00 | 2021-03-22 18:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.29 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, STRIP IN THE HOLE WITH 5" 18# P110 ICY TORQ SFW PRODUCTION CASING F/6,664' T/7,083', FILLING PIPE ON THE FLY. BLEEDING BACK 1.1 BBLS/JT CALCULATED DISPLACEMENT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI.
SABINE D 4H | 19 | 2021-03-22 18:30 | 2021-03-22 19:30 | 1 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 16.33 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RUEEQP, RIG DOWN 5" CRT AND ELEVATORS AND RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
SABINE D 4H | 19 | 2021-03-22 19:30 | 2021-03-22 21:00 | 1.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.4 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, STRIP IN THE HOLE WITH 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/7083' T/9,040' @ 150 FPM, FILLING PIPE ON THE FLY. BLEEDING BACK 1.38 BBLS/JT CALCULATED DISPLACEMENT,LOST PARTIAL RETURNS @ 7,100', ACTUAL DISPLACEMENT .4 BBLS/JT, DECREASED TRIPPING SPEED T/100 FPM, ACTUAL DISPLACEMENT AVG 1.2-1.38 BBLS/JT, 58 BBLS CALCULATED DISPLACEMENT AND 46 BBLS ACTUAL DISPLACEMENT, LOSS 12 BBLS, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
SABINE D 4H | 19 | 2021-03-22 21:00 | 2021-03-22 21:30 | 0.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.42 | 16820 | 16820 | 0 | SLOWLY STAGE UP PUMPS TO 262 GPM AND ESTABLISH CIRCULATION THROUGH GAS SEPARATOR, CIRCULATED 50 BBLS, GPM-262, SPP-620 PSI, MAX GAS-965u, CHOKES- 0% / 100%, NO FLARE', NO MUD CUT, MAX CASING PRESSURE=0 PSI. LOSS 19 BBLS.
SABINE D 4H | 19 | 2021-03-22 21:30 | 2021-03-22 22:30 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.46 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, CONTINUE STRIPPING IN THE HOLE WITH 5 1/2" PRODUCTION CASING F/9,040' T/10,224' @ 100 FPM, BLEEDING BACK 1.38 BBLS/JT CALCULATED DISPLACEMENT, ACTUAL DISPLACEMENT AVG 1.2-1.38 BBLS/JT, 35 BBLS CALCULATED DISPLACEMENT AND 22 BBLS ACTUAL DISPLACEMENT, LOSS 13 BBLS, MAXCASING PRESSURE=64 PSI, AVG CASING PRESSURE=40 PSI.
SABINE D 4H | 19 | 2021-03-22 22:30 | 2021-03-22 23:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.5 | 16820 | 16820 | 0 | SLOWLY STAGE UP PUMPS TO 183 GPM, CIRCULATE OUT MUD CAP THROUGH GAS SEPARATOR AND RECIPROCATE CASING, GPM-183, SPP-700 PSI, MAX GAS-2126u, CHOKES- 100% / 100%,NO FLARE', NO MUD CUT, MAX CASING PRESSURE=0 PSI , AVG CASING PRESSURE= 0 PSI. SICP= 260 PSI. LOSS 62 BBLS WHILE CIRCULATING. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 10.0 PPG WAS @ SURFACE, MAX MUD WT.- 11.4 PPG, DIVERTED 105 BBLS TO OPEN TOP.
SABINE D 4H | 19 | 2021-03-22 23:30 | 2021-03-23 00:30 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.54 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, CONTINUE STRIPPING IN THE HOLE WITH 5 1/2" PRODUCTION CASING F/10,224' T/11,406' @ 100 FPM, BLEEDING BACK 1.38 BBLS/JT CALCULATED DISPLACEMENT, 35 BBLS CALCULATED DISPLACEMENT AND 35 BBLS ACTUAL DISPLACEMENT, MAX CASING PRESSURE=361 PSI, AVG CASING PRESSURE=220 PSI.
SABINE D 4H | 19 | 2021-03-23 00:30 | 2021-03-23 02:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.6 | 16820 | 16820 | 0 | SLOWLY STAGE UP PUMPS TO 183 GPM, CIRCULATE OUT MUD CAP THROUGH GAS SEPARATOR AND RECIPROCATE CASING, GPM-183, SPP-750 PSI, MAX GAS-2296u, CHOKES- 0% / 80%, FLARE-1'-2', NO MUD CUT, MAX CASING PRESSURE=0 PSI , AVG CASING PRESSURE= 0 PSI. SICP= 400 PSI. LOSS 128 BBLS WHILE CIRCULATING. NOTE: DIVERTED RETURNS TO OPEN TOP WHEN A 10.0 PPG WAS @ SURFACE, MAX MUD WT.- 12.0 PPG, DIVERTED 46 BBLS TO OPEN TOP.
SABINE D 4H | 19 | 2021-03-23 02:00 | 2021-03-23 06:00 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.77 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, CONTINUE STRIPPING IN THE HOLE WITH 5 1/2" PRODUCTION CASING F/11,406' T/16,100' @ 100 FPM, BLEEDING BACK 1.38 BBLS/JT CALCULATED DISPLACEMENT, LOST PARTIAL RETURNS @ 15,200', ACTUAL DISPLACEMENT .77 BBLS/JT, DECREASED TRIPPING SPEED T/50 FPM, ACTUAL DISPLACEMENT AVG .7 BBLS/JT, 138 BBLS CALCULATED DISPLACEMENT AND 113 BBLS ACTUAL DISPLACEMENT, LOST 25 BBLS, MAX CASING PRESSURE=475 PSI, AVG CASING PRESSURE=250 PSI.
SABINE D 4H | 20 | 2021-03-23 06:00 | 2021-03-23 07:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 16.81 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RNCSG, CONTINUE RUNNING IN THE HOLE WITH 5 1/2"" PRODUCTION CASING F/11,406' T/16,806.81' @ 50 FPM, DIVERTING MUD TO TRIP TANK DOWN THE FLOWLINE WITH NO RETURNS; REMOVE ROTATING HEAD; P/U LANDING JT WITH ROTATING HEAD INSTALLED; P/U 90' TO REMOVE BUCKLING FROM PIPE AND ROTATE @ 25 RPM, GPM 200, SPP-850, TRQ-18/20K AND ESTABLISH CIRCULATION, CUT MUD WEIGHT F/ 9.3 PPG T/ 9.0 PPG; LAND CASING ON HANGER W/135K (W/O BLOCKS) @16,809.46'. RAN 5"" & 5-1/2"" PROD CASING AS FOLLOWS: MAKE UP FLOAT EQUIPMENT:INNOVEX DV FLOAT SHOE, 1 JT 5"" 18# P110 ICY TORQ SFW CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5"" 18# P110 ICY TORQ SFW CASING, GEODYNAMIC TOE SLEEVE. RAN 7,080.83' (SHOE TRACK AND 152 JTS TOTAL) OF 5'' 18# P-110 ICY TORQ SFW CASING, 1- X-OVER, 1 JOINT 5-1/2"" CSG, 1-MKR JT OF 5 1/2"" 23# P-110 ICY WEDGE 463 CASING, RAN 9,728.63' ( X-OVER, MARKER, AND 204 JTS TOTAL) OF 5 1/2"" 23# P-110 ICY WEDGE 563 CASING. FOR TOTAL OF 356 FULL JTS OF 5'' 18# P-110 ICY TORQ SFW & 5.5"" 23# P-110 ICY WEDGE 463 CASING. CASING SHOE @ 16,809.46' TOP OF FLOAT COLLAR @ 16,757.22' BOTTOM OF TOE SLEEVE VALVE @ 16,684.39' TOP OF TOE SLEEVE VALVE @ 16,709.79' TOP OF X-OVER @ 7080.83' TOP OF MARKER JOINT ABOVE X-OVER @ 7,131.41' 12 JOINTS 5"" LEFT OUT- 558.86' 12 JOINTS 5 1/2"" LEFT OUT- 566.86'"
SABINE D 4H | 20 | 2021-03-23 07:00 | 2021-03-23 07:30 | 0.5 | U | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 16.83 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RDEEQP; RIG DOWN FRANK'S CRT, INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE WHILE MONITORING SICP, SICP= 0 PSI.
SABINE D 4H | 20 | 2021-03-23 07:30 | 2021-03-23 09:00 | 1.5 | U | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 16.9 | 16820 | 16820 | 0 | RIG DOWN CSG TOOLS WHILE CIRCULATING BOTTOMS UP THROUGH CMT HEAD AND DOWN FLOWLINE, STAGE PUMPS UP TO GPM-127, SPP-1150 CIRCULATING WITH APPROXIMATELY 25% PARTIAL RETURNS.
SABINE D 4H | 20 | 2021-03-23 09:00 | 2021-03-23 10:00 | 1 | U | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 16.94 | 16820 | 16820 | 0 | CODE - CSG, SUB-CODE - RDEEQP; REMOVE CEMENTING SWEDGE, CEMENT HEAD, AND CIRCULATING IRON FROM RIG STANDPIPE; RIG UP FRANK'S CRT WHILE MONITORING WELL ON TRIP TANK; L/D LANDING JT AND 1 JT OF 5.5" CASING; INSTALL TRIP NIPPLE; STING INTO CSG WITH CRT AN ATTEMPT TO ESTABLISH CIRCULATION.
SABINE D 4H | 20 | 2021-03-23 10:00 | 2021-03-23 16:00 | 6 | U | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.19 | 16820 | 16820 | 0 | STAGE OUT OF HOLE BACKREAMING F/ 16,809' T/ 16,500', LAYING DOWN CASING IN ATTEMPT T/ ESTABLISH CIRCULATION, LAY DOWN LANDING JOINT AND 4 JOINTS OF 5.5" CASING (TOTAL LENGTH OF 4 JOINTS CASING 188.51) GPM=25-200, SPP=900-1800, RPM=25, TRG=12-25K, PERIODICALLY HAD PARTIAL RETUNS 0F 10-15%, MONITOR ANNULUS FOR LOSSES, FILLING ANNULUS WITH TRIP TANK AS NEEDED TO KEEP HOLE FULL, (NOTE: PUMP TOTAL OF 15 BBLS IN ANNULUS.)
SABINE D 4H | 20 | 2021-03-23 16:00 | 2021-03-23 18:00 | 2 | U | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 17.27 | 16820 | 16820 | 0 | PUMP 50 BBLS 9.0 PPG DOWN CASING @ 16,526', GPM=200, SPP=1800, RPM=25, TRG=12-16K, WITH NO RETURNS, BULLHEAD 50 BBLS 9.0 PPG DOWN ANNULUS, STAGE UP MUD PUMPS F/ 45 GPM T/ 210 GPM, INITIAL PRESSURE @ 45 GPM = 230 PSI, FINAL PRESSURE @ 210 GPM = 1355 PSI, PRESSURE BLED DOWN TO 400 PSI, OPEN CHOKES AN BLED PRESSURE T/ 0 PSI, OPEN HYDRILL AND MONITOR RETURNS ON TRIP TANK, WELL FLOWING BACK WITH RETUNS DECREASING, WELL FLOWED BACK TOTAL OF 48 BBLS, CIRCULATE AND ROTATE CASING WHILE MONITORING WELL, GPM=50, SPP=1275, TRG=10-16K, DECEISION MADE T/ PUMP 2 STAGE CEMENT JOB. (NOTE: LOSS TOTAL OF 901 BBLS MUD SINCE 06:00 HOURS.)
SABINE D 4H | 20 | 2021-03-23 18:00 | 2021-03-23 19:00 | 1 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 17.31 | 16820 | 16820 | 0 | LAY DOWN 2 JOINTS CASING, MAKE-UP LANDING JOINT, WASH AND REAM LANDING JOINT DOWN, LAND CASING WITH 135K @ 16526.09' (LAY DOWN A TOTAL OF 6 JOINTS OF CASING, TOTAL LENGTH 283.37') RAN 5"" & 5-1/2"" PROD CASING AS FOLLOWS: MAKE UP FLOAT EQUIPMENT:INNOVEX DV FLOAT SHOE, 1 JT 5"" 18# P110 ICY TORQ SFW CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5"" 18# P110 ICY TORQ SFW CASING, GEODYNAMIC TOE SLEEVE. RAN 7,080.83' (SHOE TRACK AND 152 JTS TOTAL) OF 5'' 18# P-110 ICY TORQ SFW CASING, 1- X-OVER, 1 JOINT 5-1/2"" CSG, 1-MKR JT OF 5 1/2"" 23# P-110 ICY WEDGE 463 CASING, RAN 9,728.63' ( X-OVER, MARKER, AND 204 JTS TOTAL) OF 5 1/2"" 23# P-110 ICY WEDGE 563 CASING. FOR TOTAL OF 350 FULL JTS OF 5'' 18# P-110 ICY TORQ SFW & 5.5"" 23# P-110 ICY WEDGE 463 CASING. CASING SHOE @ 16,526.09' TOP OF FLOAT COLLAR @ 16,473.85' BOTTOM OF TOE SLEEVE VALVE @ 16,401.02' TOP OF TOE SLEEVE VALVE @ 16,426.42' TOP OF X-OVER @ 9,442.36' TOP OF MARKER JOINT ABOVE X-OVER @ 9,374.75' 12 JOINTS 5"" LEFT OUT- 558.86' 18 JOINTS 5 1/2"" LEFT OUT- 850.23"
SABINE D 4H | 20 | 2021-03-23 19:00 | 2021-03-23 19:30 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 17.33 | 16820 | 16820 | 0 | RIG DOWN FRANK'S CRT AND RIG UP CEMENT HEAD AND CIRCULATING IRON TO STANDPIPE.
SABINE D 4H | 20 | 2021-03-23 19:30 | 2021-03-23 22:00 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 17.44 | 16820 | 16820 | 0 | HELD PJSM, FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 5/5-1/2"" PRODUCTION CASING WITH NINE ENERGY SERVICES THROUGH THE CHOKE: PUMPED @ 5 BPM 40 BBL 10.0 PPG WEIGHTED SPACER, 141 BBL 13.5 PPG 475 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THROUGH ALL LINES, DROP TOP PLUG, DISPLACED WITH FIRST 20 BBLS OF SUGAR WATER WITH CPT-21L, FOLLOWED BY 305 BBLS OF FRESH WATER WITH PLEXCIDE 15G & CORPLEX 300 @ 5.0 BPM (TOTAL OF 325 BBLS DISPLACEMENT), SLOWED PUMP RATE TO 3 BPM THE 20 BBLS, FINAL LIFT PRESSURE WAS 1850 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2900 PSI, HELD FOR 5 MIN, BLED BACK 3.5 BBLS. FLOATS HELD. 0 BBLS OF SPACER BACK TO SURFACE. PLUG DOWN @ 21:54 HRS ON 3/23/2021. FULL RETURNS WHILE DISPLACING CEMENT. INITIAL SICP= 819 PSI, FINAL SICP=1026 PSI. MAX CASING PSI W/ PUMPING CEMENT= 0 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT= 790 PSI CALCULATED TOP OF CEMENT- 9,492' FLARE: 10'-20' DURING ENTIRE CMT JOB. NOTE: REGAINED PARTIAL RETURNS @ 50%-60% AFTER PUMPING 70 BBLS OF CEMENT WHILE TAKING RETURNS DOWN THE FLOW LINE, SHUT IN WELL AFTER PUMPING CEMENT, MONITORED SICP WHILE FLUSHING THROUGH LINES AND LOADING THE TOP PLUG, SICP= 265 PSI
SABINE D 4H | 20 | 2021-03-23 22:00 | 2021-03-24 01:00 | 3 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 17.56 | 16820 | 16820 | 0 | HELD PJSM,RIG UP CIRCULATING IRON TO KILL LINE, REMOVE CHECK VALVE FROM KILL LINE. WAIT ON CEMENT, BUILD 17.0 PPG KILL MUD,
SABINE D 4H | 20 | 2021-03-24 01:00 | 2021-03-24 03:00 | 2 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 17.65 | 16820 | 16820 | 0 | PUMP 80 BBLS 17.0 PPG OBM DOWN THE ANNULUS THROUGH KILL LINE @ 1 BPM=1650 PSI & CP= 1800 PSI, 2 BPM= 1890 PSI & CP=1620 PSI, 3 BPM=2111 PSI & CP= 1750 PSI, 4 BPM=2398 PSI & CP= 1900 PSI AND 5 BPM=2500 PSI & CP= 1600 PSI TO ESTABLISH INJECTION RATE AND PRESSURE BROKE OVER 1550 PSI @ 5 BPM. INITIAL SICP-1026 PSI. FINAL SICP-0 PSI. PUMP 35 BBLS 10.0 PPG WEIGHTED SPACER, FOLLOWED BY208 BBLS13.5 PPG 695 SK 1.67 YIELD 35/65 POZ-SM-CLASS H-MM LEAD CEMENT, PUMP 50 BBLS 14.8 PPG 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 40 BBLS WATER WITH 15G CHEMICALS. MAX PUMP PSI= 3214 PSI AND MAX CASING PRESSURE= 2710 PSI @ 5 BPM. MONITORED SICP AND SICP=0 PSI. ESTIMATED TOC-2,420'.
SABINE D 4H | 20 | 2021-03-24 03:00 | 2021-03-24 05:00 | 2 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 17.73 | 16820 | 16820 | 0 | RIG DOWN CEMENT EQUIPMENT, REMOVE CSG ELEVATORS AND BAIL EXTENSION, INSTALL RIG ELEVATORS AND L/D 4 1/2" DRILL PIPE OUT OF DERRICK IN MOUSE HOLE WHILE WAITING ON CEMENT AND MONITORING SICP, INITIAL SICP-0 PSI, FINAL SICP-0 PSI.
SABINE D 4H | 20 | 2021-03-24 05:00 | 2021-03-24 06:00 | 1 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 17.77 | 16820 | 16820 | 0 | WOC; OPENED UP CHOKES AND MONITORED FLOW, NO FLOW, OPENED UP RAMS, REMOVE RIG ELEVATORS AND INSTALL CSG ELEVATORS, BACKED OUT AND L/D LANDING JOINT, REMOVE CSG ELEVATORS AND INSTALL RIG ELEVATORS.
SABINE D 4H | 21 | 2021-03-24 06:00 | 2021-03-24 09:30 | 3.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 17.92 | 16820 | 16820 | 0 | SUB-CODE: RUWLHD, PJSM, MAKE UP STREAMFLO WASHOUT TOOL AND FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN. P/U JT OF DP AND M/U PACK-OFF, INSTALLED STREAM FLO PACKOFF & TEST T/ 10,000 PSI.(PULL TEST T/25K OVERPULL) BACK OUT FROM PACK OFF AND L/D JOINT OF DP, INSTALL BPV, FLUSH SURFACE LINES, BOP STACK AND CHOKE MANIFOLD WITH WATER.
SABINE D 4H | 21 | 2021-03-24 09:30 | 2021-03-24 13:00 | 3.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 18.06 | 16820 | 16820 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, REMOVE FLOWLINE F/ ORBIT VALVE, NIPPLE DOWN KILL LINE AND CHOKE LINE, DISCONNECT HYDRAULIC LINES F/ BOP'S, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE AND INSTALL WEATHER CAP AND SECURE WELL, WELL SECURED @ 13:00 HOURS.
SABINE D 4H | 21 | 2021-03-24 13:00 | 2021-03-25 06:00 | 17 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 18.06 | 16820 | 16820 | 0 | SUB-CODE: RDEQP, RIG DOWN NOV EQUIPMENT IN BACKYARD EQUIPMENT, WASH AND CLEAN MUD PITS, SOLID CONTROL EQUIPMENT, LAYING DOWN DRILL PIPE F/ DERRICK IN MOUSE HOLE, REMOVE RIG ELEVATORS, CHANGE OUT SAVER SUB; COMPLETE LAYING DOWN DRILL PIPE @ 02:00; BEGIN RIGGING DOWN BACK YARD; CLEAN RIG
SABINE D 4H | 21 | 2021-03-24 13:00 | 2021-03-24 13:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 18.06 | 16820 | 16820 |  | SUB-CODE: WLRLS, MILESTONE_WELL RELEASE ON 03/24/2021 @ 13:00
SABINE D 4H | 22 | 2021-03-25 06:00 | 2021-03-26 06:00 | 24 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 18.06 | 16820 | 16820 | 0 | SUB-CODE: RDEQP, CONTINUE CLEANING RIG FLOOR, SUBS, MUD PITS AND MUD PUMPS. RIG DOWN ELECTRICAL FROM MUD PUMPS AND MUD PIT; RIG DOWN AIR, WATER AND MUD LINES FROM MUD PITS. PERFORM 90 DAY INSPECTION ON TOP DRIVE. HANG OFF TOP DRIVE; UNSPOOL DRAW WORKS; CUT 70' DRILL LINE AND SPOOL UP DRILL LINE ON SPOOL; PERFORM ANNUAL INSPECTION ON DRAW WORKS. RIG DOWN RIG FLOOR. RIG DOWN GAS BUSTER, VENT LINE AND FLARE STACK; GRAVITY RIG DOWN TRANSFER PUMPS, MANIFOLDS AND HOSES FROM FRAC TANKS. RIG DOWN FLOW LINE. MAKE UP STOMPER HYDRAULICS; UNSPOOL HOIST LINES. WALK RIG BACK 40', REMOVE V-DOOR; SCOPE OUT MAST CYCLINDERS AND PIN TO SUB, LOWER SUB @ 03:00; RIG DOWN ELECTRICAL AND HYDRAULICS F/RIG FLOOR AFTER LOWERED; PREP FOR LOWERING DERRICK; RELEASE RIG 03/26/2021 @ 06:00
SABINE D 4H | 22 | 2021-03-26 06:00 | 2021-03-26 06:00 | 0 | P | MOBDMOB | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 18.06 | 16820 | 16820 |  | SUB-CODE: TOTC; MILESTONE_TURN OVER TO COMPLETION 03-26-2021 @ 06:00
SABINE D 4H | 22 | 2021-03-26 06:00 | 2021-03-26 06:00 | 0 | P | MOBDMOB | MSTN | RRLS | MILESTONE_RIG RELEASE | 18.06 | 16820 | 16820 |  | SUB-CODE: RRLS; MILESTONE_RIG RELEASE 03-26-2021 @ 06:00
SIERRA H08 PR | 4 | 2021-11-29 11:00 | 2021-11-29 11:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 11/27/2021 @ 11:00
SIERRA H08 PR | 4 | 2021-11-29 11:00 | 2021-11-29 12:30 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/PRUEGNER UNIT H04 PR T/ SIERRA H08 PR; SET MATS, WALK RIG F/PRUEGNER UNIT H04 PR T/ SIERRA H08 PR; CENTER SUB OVER CONDUCTOR.
SIERRA H08 PR | 4 | 2021-11-29 12:30 | 2021-11-29 13:30 | 1 | P | MOBDMOB | RURD | RDEQP | RIG DOWN EQUIPMENT | 0 | 108 | 108 | 0 | L/D LANDING JOINT, R/D CSG BAILS, ELEVATORS AND CRT. INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
SIERRA H08 PR | 4 | 2021-11-29 13:30 | 2021-11-29 14:30 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS, ST-80 AND CROWN.
SIERRA H08 PR | 4 | 2021-11-29 14:30 | 2021-11-29 14:45 | 0.25 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, TAG BOTTOM @ 108'.
SIERRA H08 PR | 4 | 2021-11-29 14:45 | 2021-11-29 15:30 | 0.75 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.03 | 108 | 235 | 169.3 | ROTATE (127’ IN .75 HRS @ 169.33 FPH) WOB-5-10K, RPM-30, TRQ- 2K/5K, SPM-42/42/42, GPM-400, MMRPM-62, TRPM-92, SPP-500/800 PSI, DIFF 100/300 PSI
SIERRA H08 PR | 4 | 2021-11-29 14:45 | 2021-11-29 14:45 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 11/27/2021 @ 15:15.
SIERRA H08 PR | 4 | 2021-11-29 15:30 | 2021-11-29 16:00 | 0.5 | U | SFHL | TRIP | LDDP | LAY DOWN DRILLPIPE | 0.06 | 235 | 235 | 0 | LD 2 JOINTS HWDP AND REPLACE SAME DUE TO WASH ON FACE OF TOOL JOINT.
SIERRA H08 PR | 4 | 2021-11-29 16:00 | 2021-11-29 22:45 | 6.75 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.34 | 235 | 2477 | 332.1 | ROTATE (2,242’ IN 6.7 HRS @ 334.62 FPH) WOB-25-35K, RPM-100, TRQ- 5K/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2100/2700 PSI, DIFF 300/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/ SOAP/ SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 30 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM.
SIERRA H08 PR | 4 | 2021-11-29 22:45 | 2021-11-30 00:30 | 1.75 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.41 | 2477 | 2932 | 260 | SLIDE (455' IN 1.8 HRS @ 252.78 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2,100/2,600 PSI, DIFF-200/500 PSI. SLIDE DEPTHS: F/ 385' T/ 400' 15' TF-30M 1623-1626 F/ 546' T/ 576' 30' TF-40M 16545-1700 F/ 1,215 ' T/ 1,235' 20' TF-30M 1817-1820 F/ 1309 ' T/ 1329' 20' TF-30M 1832-1836 F/ 1,403 ' T/ 1,428' 25' TF-30M 1849-1854 F/ 1,497 ' T/ 1,517' 20' TF- HS 1906- 1911 F/ 1,591 ' T/ 1,611' 20' TF- 30L 1923-1928 F/ 1,675 ' T/ 1,700' 25' TF-30L 1941-1947 F/ 1,779 ' T/ 1,804' 25' TF- HS 2002-2008 F/ 1,872 ' T/ 1,897' 25' TF- HS 2020-2026 F/ 1,966 ' T/ 1,991' 25' TF- 20R 2040-2046 F/ 2,061 ' T/ 2,091' 30' TF- HS 2100-2106 F/ 2,154 ' T/ 2,184' 30' TF- HS 2118-2126 F/ 2,248 ' T/ 2,278' 30' TF- HS 2138- 2146 F/ 2,341 ' T/ 2,371' 30' TF- HS 2158- 2206 F/ 2,435 ' T/ 2,470' 35' TF- 20R 2218-2225 F/ 2,529 ' T/ 2,549' 20' TF-30R 2237-2244 F/ 2,717 ' T/ 2,747' 30' TF-30R 2316- 2325 F/ 2,811 ' T/ 2,826' 15' TF-60R 2337- 2350 NOTE: WHILE SLIDING @ 2,826 WEIGHT STARTED STACKING AND ROP DROPPED TO 30'/HR, PICKED UP AND WAS NOT HUNG. WENT BACK TO BOTTOM AND ATTEMPT TO RETURN SLIDING, STILL WITH ONLY 30'/HR. TRIED TO ROTATE DRILL LAST 106' STAGING UP PARAMETERS. ROP INCREASED FROM 80'/HR TO 350'/HR BY TD. NO INCREASE IN PUMP PRESSURE OR MOTOR STALLS WHILE DRILLING TO 2,932'.
SIERRA H08 PR | 4 | 2021-11-30 00:30 | 2021-11-30 01:15 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.44 | 2932 | 2932 | 0 | PUMP 2-30 BBL SOAP AND SAP SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,000 PSI
SIERRA H08 PR | 4 | 2021-11-30 01:15 | 2021-11-30 02:15 | 1 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.48 | 2932 | 2932 | 0 | TRIP OUT OF HOLE F/2,925' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE
SIERRA H08 PR | 4 | 2021-11-30 02:15 | 2021-11-30 03:45 | 1.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.55 | 2932 | 2932 | 0 | RACK BACK 3 STANDS AND A DOUBLE HWDP, REMOVE MWD,PICK UP PUP JOINT AND CROSS OVER AND RACK BACK MONELS, DRAIN MOTOR AND LAY DOWN. LAY DOWN BIT. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS 1/8" AND MOTOR DID NOT DRAIN. PAD WEAR WAS MINIMAL, BIT GRADE: 0-0-NO-A-0-0-TD.
SIERRA H08 PR | 4 | 2021-11-30 03:45 | 2021-11-30 04:30 | 0.75 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.58 | 2932 | 2932 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS
SIERRA H08 PR | 4 | 2021-11-30 04:30 | 2021-11-30 06:00 | 1.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.64 | 2932 | 2932 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). PICK AND RUN 10 3/4" 45.5# J-55 BT&C CASING T/ 1,367', REMAINDER OF CASING DETAILS TO FOLLOW
SIERRA H08 PR | 5 | 2021-11-30 06:00 | 2021-11-30 08:00 | 2 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.72 | 2932 | 2932 | 0 | CONTINUE TO RUN 10 3/4" 45.5# J-55 BT&C CASING T/2,922.4'. RAN 38 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 115K (W/O BLOCKS). SHOE- 2,922.4' TOP OF FLOAT COLLAR- 2,843.9' 20 JOINTS LEFT OUT- 765.63'
SIERRA H08 PR | 5 | 2021-11-30 08:00 | 2021-11-30 08:45 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.75 | 2932 | 2932 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-337, SPP-1175 PSI. NO LOSSES.
SIERRA H08 PR | 5 | 2021-11-30 08:45 | 2021-11-30 09:15 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.77 | 2932 | 2932 | 0 | RIG DOWN CRT, L/D LANDING JOINT, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
SIERRA H08 PR | 5 | 2021-11-30 09:15 | 2021-11-30 11:45 | 2.5 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.88 | 2932 | 2932 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,500 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 314 BBLS 11.6 PPG LEAD CEMENT, 84 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 271 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/750 PSI PRESSURED UP T/1250 PSI (500 PSI OVER) @ 4 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.5 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 211 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS. OFFLINE: REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, CHANGE OUT SAVER SUB.
SIERRA H08 PR | 5 | 2021-11-30 11:45 | 2021-11-30 14:30 | 2.75 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.99 | 2932 | 2932 | 0 | PRESSURE TESTED 10-3/4" SURFACE CASING TO 1,500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, FLUSH THROUGH AND RIG DOWN CELLAR PUMPS, DRESS OUT WELLHEAD. OFFLINE: BIG SIX TORQUE UP BOLTS ON SINGLE AND DOUBLE RAMS ON BOP’S, EMPTY AND CLEAN MUD TANKS, INSTALL STREAM FLO BOP ADAPTER ON WELLHEAD.
SIERRA H08 PR | 5 | 2021-11-30 14:30 | 2021-11-30 15:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.03 | 2932 | 2932 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
SIERRA H08 PR | 5 | 2021-11-30 15:30 | 2021-11-30 19:00 | 3.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.18 | 2932 | 2932 | 0 | HOOK UP HYDRAULIC LINES F/KOOMEY T/BOP'S, INSTALL AND NIPPLE UP BOP ONTO BOP ADAPTER, BIG SIX TORQUED UP BOLTS, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD. NOTE: PRESSURE TEST MUD PUMP LINES/VALVES T/250 PSI LOW / 6000 PSI HIGH OFFLINE. 4" VALVE ON #3 PUMP DID NOT TEST.
SIERRA H08 PR | 5 | 2021-11-30 19:00 | 2021-11-30 22:30 | 3.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.33 | 2932 | 2932 | 0 | INSTALL TURNBUCKLES, UNLATCH BOP WRANGLER FROM BOP'S & LAY OVER SAME, INSTALL KILL LINE, KILL LINE CHECK VALVE,, INSTALL CHOKE LINE TO BOP AND CHOKE, FUNCTION TEST SAME, CHANGE OUT UPPER AND LOWER RAMS TO VBR'S. REBUILD 4" VALVE ON #3 PUMP. NOTE: FINISH PRESSURE TESTING MUD PUMP 4" VALVES T/250 PSI LOW / 6000 PSI HIGH AND PRESSURE TEST CHOKE MANIFOLD T/250 PSI LOW / 5000 PSI HIGH OFFLINE.
SIERRA H08 PR | 5 | 2021-11-30 22:30 | 2021-12-01 04:30 | 6 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.58 | 2932 | 2932 | 0 | INSTALL TEST PLUG ON TEST JOINT AND TEST BOP'S: TEST TOP RAMS, LOWER RAMS, INSIDE AND OUTSIDE KILL VALVES, INSIDE AND OUTSIDE HCR VALVES, WELLHEAD ADAPTER, FLOOR VALVES, MANUAL IBOP, HYDRAULIC IBOP, KILL LINES BACK TO #1 AND #2 PUMPS, BLINDS AND KILL LINE CHECK VALVE TO 250 PSI LOW / 5000 PSI HIGH, TEST ANNULAR TO 250 PSI LOW / 3500 PSI HIGH. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1500 PSI HIGH. REMOVE TEST CAP AND RIG DOWN TESTERS. CLOSED CASING VALVE.
SIERRA H08 PR | 5 | 2021-12-01 04:30 | 2021-12-01 06:00 | 1.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.64 | 2932 | 2932 | 0 | MAKE UP FLOW LINE TO ROTATING HEAD AND TO FLOW LINE SCISSOR, FILL UP LINE, CASING FILL LINE, FILL MUD TANKS WITH OBM, PERFORM ACCUMULATOR DRAW DOWN TEST.
SIERRA H08 PR | 6 | 2021-12-01 06:00 | 2021-12-01 07:45 | 1.75 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.71 | 2932 | 2932 | 0 | MAKE UP FLOW LINE TO ROTATING HEAD AND TO FLOW LINE SCISSOR, FILL UP LINE, CASING FILL LINE, FILL MUD TANKS WITH OBM
SIERRA H08 PR | 6 | 2021-12-01 07:45 | 2021-12-01 08:15 | 0.5 | P | SFHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 1.73 | 2932 | 2932 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE AND MOUSE HOLE.
SIERRA H08 PR | 6 | 2021-12-01 08:15 | 2021-12-01 12:15 | 4 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.9 | 2932 | 2932 | 0 | PICK UP (9 7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 5.88' BIT TO BEND 8-1/4" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8"NMDC. BIT TO SVY-64' AND GAMMA-60'. TEST MWD-TEST GOOD, PICK UP 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3- STDS 5" HWDP, 22 STDS DRILL PIPE AND DSW AGITATOR. BIT TO SVY-64' AND GAMMA-60'. PICK UP HWDP AND TRIP IN WITH SAME TO / 335.46'.
SIERRA H08 PR | 6 | 2021-12-01 12:15 | 2021-12-01 14:30 | 2.25 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.99 | 2932 | 2932 | 0 | TRIP IN HOLE F/301' T/2,727'. PICK UP AGITATOR ON STAND 22: FILL PIPE, PSI BEFORE-585, PSI AFTER-695 @ 295 GPM, HOLE GIVING PROPER DISPLACEMENT.
SIERRA H08 PR | 6 | 2021-12-01 14:30 | 2021-12-01 15:30 | 1 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 2.03 | 2932 | 2932 | 0 | PULL TRIP NIPPLE AND INSTALL ROTATING HEAD, CONFIRM PROPER VALVE ALIGNMENT, FILL GAS SEPERATOR, PERORM BOP DRILL, RESPONSE TIME= 60 SECONDS.
SIERRA H08 PR | 6 | 2021-12-01 15:30 | 2021-12-01 16:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.08 | 2932 | 2932 | 0 | SERVICE RIG, TOP DRIVE UNIT, ST-80, AND DRAW WORKS
SIERRA H08 PR | 6 | 2021-12-01 16:30 | 2021-12-01 17:30 | 1 | P | SFHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 2.12 | 2932 | 2942 | 10 | DRILL SHOE TRACK AND FLOAT EQUIPMENT, DRILL 10' NEW FORMATION F/2,932 T/2,942', GPM-450, SPP- 1120/1270 PSI, DIFF-50/150,RPM-35, TQ-2/6K.
SIERRA H08 PR | 6 | 2021-12-01 17:30 | 2021-12-01 17:45 | 0.25 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.13 | 2942 | 2942 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-350, SPP-1120 PSI, RPM-35. MUD WT IN/OUT= 8.8 PPG.
SIERRA H08 PR | 6 | 2021-12-01 17:45 | 2021-12-01 18:00 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 2.14 | 2942 | 2942 | 0 | PERFORM F.I.T. WITH 8.8 PPG OBM, PUMP 2.5 BBLS, 422 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD-2,922' / TVD-2,895'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE ON THE REMOTE CHOKE PANEL.
SIERRA H08 PR | 6 | 2021-12-01 18:00 | 2021-12-01 23:00 | 5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.35 | 2942 | 4651 | 341.8 | ROT (1,709' IN 5.07 HRS @ 428.82 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 5K/20K, SPP: 4000/5,000 PSI, DIFF: 500/650 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
SIERRA H08 PR | 6 | 2021-12-01 23:00 | 2021-12-01 23:30 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.37 | 4651 | 4697 | 92 | SLIDE (54' IN .43 HRS @ 124.62 PH) WOB: 10/16K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 3800/4,100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/3113 T/ 3125 12' TF-70R 1845- 1850 SLD F/3300 T/ 3312 12' TF-90R 1922- 1927 SLD F/3675 T/ 3687 12' TF-110R 2021- 2026 SLD F/3869 T/ 3877 08' TF- 180 2055- 2100 SLD F/4334 T/ 4344 10' TF-110R 2218- 2224 NOTE: PRESSURE BEGAN TO FALL F/ 3400' T/ 4697'. OFF BOTTOM PUMP PRESSURE WENT FROM 4,040 PSI TO 3,250.
SIERRA H08 PR | 6 | 2021-12-01 23:30 | 2021-12-02 00:30 | 1 | U | INTHL | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.41 | 4697 | 4697 | 0 | TROUBLE SHOOT PRESSURE LOSS, CHECK PRESSURE ON SURFACE EQUIPMENT. ISOLATE EACH PUMP AND PRESSURE TEST SAME. ALL PUMPS HAD SIMILAR AND STEADY PRESSURES. 565-600 PSI @ 300 GPM
SIERRA H08 PR | 6 | 2021-12-02 00:30 | 2021-12-02 02:45 | 2.25 | U | INTHL | TRIP | WSHO | TRIP FOR WASHOUT | 2.5 | 4697 | 4697 | 0 | TOOH F/4,697' T/2,696', (AT AGITATOR)' LOOKING FOR WASH OUT, PROPER FILL WITH KILL LINE. FLOW CHECK (WELL STATIC) .PULLED ROTATING HEAD @ 2,829', WHILE PULLING AGITATOR THROUGH THE FLOOR, RIG CREW NOTICED SAFETY JOINT BELOW THE AGITATOR WAS WASHED AND PARTIALLY BACKED OUT. CONNECTIONS ABOVE AND BELOW THE SAFETY JOINT WERE GOOD. REMOVE THE WASHED SAFETY JOINT FROM DRILL STRING AND MAKE AGITATOR BACK UP TO DRILL PIPE. FLOW TEST SAME @ 295 GPM, 650 PSI. PRESSURE SIMILAR TO PRIOR TEST
SIERRA H08 PR | 6 | 2021-12-02 02:45 | 2021-12-02 03:15 | 0.5 | U | INTHL | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 2.52 | 4697 | 4697 | 0 | REMOVE TRIP NIPPLE AND RE-INSTALL ROTATING HEAD
SIERRA H08 PR | 6 | 2021-12-02 03:15 | 2021-12-02 04:15 | 1 | U | INTHL | TRIP | WSHO | TRIP FOR WASHOUT | 2.57 | 4697 | 4697 | 0 | TRIP BACK IN THE HOLE F/ 2,696' T/ 4,697', HOLE GIVING PROPER DICPLACEMENT INTO TRIP TANK, RECORD RETURNS ON TRIP SHEET, NO UNEXPECTED TIGHT HOLE
SIERRA H08 PR | 6 | 2021-12-02 04:15 | 2021-12-02 06:00 | 1.75 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.64 | 4697 | 5258 | 320.6 | ROT (561' IN 1.75 HRS @ 320.57 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 219, TRQ: 5K/20K, SPP: 4000/5,000 PSI, DIFF: 500/650 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
SIERRA H08 PR | 7 | 2021-12-02 06:00 | 2021-12-02 12:30 | 6.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.91 | 5258 | 7288 | 312.3 | ROT (2,030’ IN 6.52 HRS @ 311.35 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 11K/16K, SPP: 4600/5500 PSI, DIFF: 700/900 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
SIERRA H08 PR | 7 | 2021-12-02 12:30 | 2021-12-02 14:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.97 | 7288 | 7420 | 88 | SLIDE (132’ IN 1.48 HRS @ 89.19 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4600/4900 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/5363 T/5378 15' 120R 6:15-6:25 SLD F/6026 T/6041 15' 90R 8:20-8:30 SLD F/6310 T/6330 20' 30R 9:20-9:31 SLD F/6496 T/6516 20' 30R 10:05-10:13 SLD F/6670 T/6687 17' HS 10:45-10:54 SLD F/6968 T/6988 20' HS 12:01-12:29 SLD F/7235 T/7260 25' 30R 13:17-13:30
SIERRA H08 PR | 7 | 2021-12-02 14:00 | 2021-12-02 14:45 | 0.75 | P | INTHL | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 3 | 7420 | 7420 | 0 | SERVICE TOP DRIVE, DRAW WORKS AND ST-80.
SIERRA H08 PR | 7 | 2021-12-02 14:45 | 2021-12-02 16:00 | 1.25 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.06 | 7420 | 7643 | 178.4 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT CAP AND CAP GASKET ON #2 PUMP, ROTATE (253' IN 1.27 HRS @ 199.21 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 112, RPM-80, TRPM: 192, TRQ: 10K/15K, SPP: 3000/3700 PSI, DIFF: 500/700 PSI.
SIERRA H08 PR | 7 | 2021-12-02 16:00 | 2021-12-02 16:30 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.08 | 7643 | 7703 | 120 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT CAP AND CAP GASKET ON #2 PUMP, SLIDE (30' IN .57 HRS @ 52.63 FPH) WOB: 5/120K, SPM: 105/105, GPM: 674, MMRPM: 112, SPP: 3000/3300 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/7420 T/7450 30' TF-30R 14:45-15:19
SIERRA H08 PR | 7 | 2021-12-02 16:30 | 2021-12-02 17:45 | 1.25 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.13 | 7703 | 7973 | 216 | ROT (270’ IN 1.17 HRS @ 230.77 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 10K/17K, SPP: 4800/5500 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
SIERRA H08 PR | 7 | 2021-12-02 17:45 | 2021-12-02 18:15 | 0.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.15 | 7973 | 8018 | 90 | SLIDE (45’ IN .5 HRS @ 90 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4800/5100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/7703 T/7748 45' TF-30R 16:35-17:05
SIERRA H08 PR | 7 | 2021-12-02 18:15 | 2021-12-02 20:15 | 2 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.23 | 8018 | 8438 | 210 | CONTROL DRILL ON #2 AND #3 PUMPS WHILE CHANGING OUT SWAB ON #1 PUMP, ROTATE (420' IN 1.9 HRS @ 221 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 112, RPM-80, TRPM: 192, TRQ: 10K/15K, SPP: 3000/3700 PSI, DIFF: 500/700 PSI.
SIERRA H08 PR | 7 | 2021-12-02 20:15 | 2021-12-02 20:45 | 0.5 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.25 | 8438 | 8483 | 90 | CONTROL DRILL ON #2 AND #3 PUMPS WHILE CHANGING OUT SWAB ON #1 PUMP, SLIDE (45' IN .6 HRS @ 75 FPH) WOB: 5/120K, SPM: 105/105, GPM: 674, MMRPM: 112, SPP: 3000/3300 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/8088 T/8113 25' TF-60R 18:39-19:03 SLD F/8463 T/8483 20' TF-90R 20:33-20:45
SIERRA H08 PR | 7 | 2021-12-02 20:45 | 2021-12-02 21:30 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.28 | 8483 | 8644 | 214.7 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT CAP GASKET AND 2" BLEED OFF ON #2 PUMP, ROTATE (161' IN .75 HRS @ 214.67 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 112, RPM-80, TRPM: 192, TRQ: 10K/15K, SPP: 3000/3700 PSI, DIFF: 500/700 PSI.
SIERRA H08 PR | 7 | 2021-12-02 21:30 | 2021-12-02 22:00 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.31 | 8644 | 8730 | 172 | ROT (86’ IN .52 HRS @ 165.38 FPH) WOB: 30/40K, SPM: 94/94/94, GPM: 900, MMRPM: 149, RPM-80, TRPM: 229, TRQ: 10K/17K, SPP: 4800/5500 PSI, DIFF: 500/700 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
SIERRA H08 PR | 7 | 2021-12-02 22:00 | 2021-12-02 22:15 | 0.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.32 | 8730 | 8746 | 64 | SLIDE (16’ IN .30 HRS @ 53.33 FPH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 149, SPP: 4800/5100 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/8651 T/8667 16' TF-180 21:44-22:02
SIERRA H08 PR | 7 | 2021-12-02 22:15 | 2021-12-03 02:15 | 4 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.48 | 8746 | 9622 | 219 | CONTROL DRILL ON #1 AND #3 PUMPS WHILE CHANGING OUT CAP GASKET AND 2" BLEED OFF ON #2 PUMP, ROTATE (876' IN 4.13 HRS @ 212.10 FPH) WOB: 25/35K, SPM: 105/105, GPM: 674, MMRPM: 112, RPM-80, TRPM: 192, TRQ: 10K/15K, SPP: 3000/3700 PSI, DIFF: 500/700 PSI.
SIERRA H08 PR | 7 | 2021-12-03 02:15 | 2021-12-03 03:00 | 0.75 | P | INTHL | DRLG | CTLDRL | CONTROL DRILLING | 3.51 | 9622 | 9658 | 48 | CONTROL DRILL ON #1 AND #2 PUMPS WHILE CHANGING OUT POP OFF VALVE ON #3 PUMP, SLIDE (36' IN .55 HRS @ 65.45 FPH) WOB: 5/120K, SPM: 105/105, GPM: 674, MMRPM: 112, SPP: 3000/3300 PSI, DIFF: 100/300 PSI. SLIDE DEPTHS: SLD F/ 8746 T/ 8758 12' TF-160L 2219- 2230 SLD F/ 8840 T/ 8852 12' TF-150L 2247- 2257 SLD F/9307 T/9319 12' TF-180M 0108- 0120
SIERRA H08 PR | 7 | 2021-12-03 03:00 | 2021-12-03 06:00 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 3.64 | 9658 | 9765 | 35.7 | BUILD INTERMEDIATE CURVE- SLIDE (107’ IN 3 HRS @ 35.66 FPH) WOB: 15/20K, SPM: 94/94/94, GPM: 833, MMRPM: 149, SPP: 4750/5000 PSI, DIFF: 200/300 PSI. SLIDE DEPTHS: SLD F/ 9658 T/ 9765 107' TF- HS 0300- 0600
SIERRA H08 PR | 8 | 2021-12-03 06:00 | 2021-12-03 20:15 | 14.25 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 4.23 | 9765 | 10029 | 18.5 | BUILD INTERMEDIATE CURVE- SLIDE (264’ IN 14.20 HRS @ 18.59 FPH) WOB: 5/10K, SPM: 87/87/87, GPM: 837, MMRPM: 139, SPP: 4750/5000 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/ 9765 T/ 10,022 257' TF- HS 06:00-19:48 SLD F/ 10,022 T/B10,055 7' TF- HS 20:20-20:44
SIERRA H08 PR | 8 | 2021-12-03 20:15 | 2021-12-03 20:45 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 4.25 | 10029 | 10060 | 62 | ROT (31' IN .55 HRS @ 56.36 FPH) WOB: 25/35K, SPM: 87/87/87, GPM: 837, MMRPM: 139, RPM-30, TRPM: 169, TRQ: 6K/17K, SPP: 4750/5000 PSI, DIFF: 200/300 PSI.
SIERRA H08 PR | 8 | 2021-12-03 20:45 | 2021-12-03 22:15 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.32 | 10060 | 10060 | 0 | PERFORM CLEAN UP CYCLE PUMPING 2-30 BBL HI-VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7-5/8" CASING. GPM-871, ,SPP-5,000 PSI, SHAKERS CLEAN
SIERRA H08 PR | 8 | 2021-12-03 22:15 | 2021-12-04 01:00 | 2.75 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.43 | 10060 | 10060 | 0 | TOOH F/10,060' T/2,849', PROPER FILL WITH TRIP TANK, NO EXCESSIVE OVERPULL. FLOW CHECK AT SHOE
SIERRA H08 PR | 8 | 2021-12-04 01:00 | 2021-12-04 01:45 | 0.75 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 4.46 | 10060 | 10060 | 0 | L/D AGITATOR, PULL ROTATING HEAD AND INSTALL TRIP NIPPLE
SIERRA H08 PR | 8 | 2021-12-04 01:45 | 2021-12-04 02:45 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.5 | 10060 | 10060 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
SIERRA H08 PR | 8 | 2021-12-04 02:45 | 2021-12-04 03:30 | 0.75 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 4.53 | 10060 | 10060 | 0 | CONTINUE TRIP OUT F/2,849' T/BHA, HOLE TAKING PROPER FILL ON TRIP TANK, FLOW CHECK @ BHA, WELL STATIC.
SIERRA H08 PR | 8 | 2021-12-04 03:30 | 2021-12-04 05:00 | 1.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 4.6 | 10060 | 10060 | 0 | PICK UP AND MAKE UP 2 JTS HWDP TO RACK BACK BHA, RACK BACK HWDP & 2 STDS-6.5" DC, REMOVE MWD TOOL, DRAIN MUD MOTOR, BREAK OUT BIT, CHANGE OUT, SCRIBE, AND RACK BACK NEW MOTOR. NOTE: MUD MOTOR DRAINED GOOD WITH LITTLE SQUAT. BIT GRADED: 1-1-WT-S-1-TD. ONE OF THE PADS ON THE MOTOR WAS MISSING. PICTURE ATTACHED TO REPORT.
SIERRA H08 PR | 8 | 2021-12-04 05:00 | 2021-12-04 06:00 | 1 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.64 | 10060 | 10060 | 0 | PICK UP 8", 7/8L, 5.9 STG @ 2.0° SLICK; .166 REV/GAL; 5.88' BIT TO BEND 8-1/4" PAD OD, MAKE UP PONY COLLAR, UBHO AND RACK BACK SAME.
SIERRA H08 PR | 9 | 2021-12-04 06:00 | 2021-12-04 08:00 | 2 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 4.72 | 10060 | 10060 | 0 | CHANGE OUT TOP VBR'S TO 7-5/8" CASING RAMS, PICK UP JOINT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1500 PSI (TEST GOOD).
SIERRA H08 PR | 9 | 2021-12-04 08:00 | 2021-12-04 09:45 | 1.75 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.8 | 10060 | 10060 | 0 | HOLD PJSM AND RIG UP FRANK'S CASING TOOLS & EQUIPMENT.
SIERRA H08 PR | 9 | 2021-12-04 09:45 | 2021-12-04 21:00 | 11.25 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 5.26 | 10060 | 10060 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN INTERMEDIATE CASING T/10,051.6', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 235 JTS OF 7 5/8" 29.7# P-110 IC BTC CSG,1-10' PUP JT, 2-JT OF 7 5/8" 29.7# P-110 IC BTC CSG, TOTAL OF 237 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 44 LATCH ON BOW SPRING CENTRALIZERS @ 9,755.2' AND EVERY 4TH JT UP TO 2,506.3'. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/180K (W/O BLOCKS) FLOAT SHOE- 10,051.6' TOP OF FLOAT COLLAR-9,964.8'. 13 JOINTS LEFT OUT- 556.7', 1-10' & 2-15' PUP JTS
SIERRA H08 PR | 9 | 2021-12-04 21:00 | 2021-12-04 21:45 | 0.75 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 5.3 | 10060 | 10060 | 0 | RIG DOWN FRANKS CASING CRT, RIG UP CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
SIERRA H08 PR | 9 | 2021-12-04 21:45 | 2021-12-04 23:00 | 1.25 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.35 | 10060 | 10060 | 0 | CIRCULATE CSG CAPACITY W/ RIG PUMPS THROUGH CEMENT HEAD WHILE RIG DOWN CASING TOOLS, SPM: 105, 8.0 BPM, SPP: 756 PSI, NO LOSSES.
SIERRA H08 PR | 9 | 2021-12-04 23:00 | 2021-12-05 03:00 | 4 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 5.51 | 10060 | 10060 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/4,000 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.5 PPG SPACER. 302 BBL 11.8 PPG 875 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPNAY REP WITNESS PLUG DROP, DISPLACE WITH 458 BBLS OF 9.8 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1640 PSI AT 3 BPM, BUMP PLUG AND INCREASE PSI 500 OVER T/2140 PSI. HELD PRESS. FOR 5 MIN., BLED BACK 4.5 BBLS-FLOATS HELD. PLUG BUMPED @ 0200 HRS CEMENT W/ FULL RETURNS WHILE PUMPING CEMENT. 38 BBLS SPACER TO SURFACE. ESTIMATED TOP OF CEMENT @ 2,044'.
SIERRA H08 PR | 9 | 2021-12-05 03:00 | 2021-12-05 03:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 5.53 | 10060 | 10060 | 0 | TEST CASING T/3,500 PSI FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. BLED BACK 4.25 BBLS.
SIERRA H08 PR | 9 | 2021-12-05 03:30 | 2021-12-05 04:30 | 1 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 5.58 | 10060 | 10060 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
SIERRA H08 PR | 9 | 2021-12-05 04:30 | 2021-12-05 05:00 | 0.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 5.6 | 10060 | 10060 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, FLUSH THROUGH BOP'S AND FLOW LINE, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 15K, BROKE OUT & LAID DOWN SETTING TOOL.
SIERRA H08 PR | 9 | 2021-12-05 05:00 | 2021-12-05 05:30 | 0.5 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.62 | 10060 | 10060 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL, CLOSE CASING VALVE
SIERRA H08 PR | 9 | 2021-12-05 05:30 | 2021-12-05 06:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.64 | 10060 | 10060 | 0 | SERVICE RIG, TOP DRIVE AND DRAW WORKS
SIERRA H08 PR | 10 | 2021-12-05 06:00 | 2021-12-05 07:45 | 1.75 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 5.71 | 10060 | 10060 | 0 | REMOVE CASING RAMS; INSTALL VARIABLE RAMS.
SIERRA H08 PR | 10 | 2021-12-05 07:45 | 2021-12-05 09:15 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.77 | 10060 | 10060 | 0 | SLIP AND CUT 90' OF DRILL LINE.
SIERRA H08 PR | 10 | 2021-12-05 09:15 | 2021-12-05 10:15 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.82 | 10060 | 10060 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS.
SIERRA H08 PR | 10 | 2021-12-05 10:15 | 2021-12-05 10:15 | 0 | P | INTHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 5.82 | 10060 | 10060 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 10-13-21 @ 12:00
SIERRA H08 PR | 11 | 2022-01-18 10:30 | 2022-01-18 11:30 | 1 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 5.86 | 10060 | 10060 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK 20' FROM PRUEGNER UNIT H06 PR, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN. NOTE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE.
SIERRA H08 PR | 11 | 2022-01-18 10:30 | 2022-01-18 10:30 | 0 | P | INTHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 5.82 | 10060 | 10060 |  | MILESTONE_RESUME WELL 1 ON 1/18/22 @ 10:30
SIERRA H08 PR | 11 | 2022-01-18 11:30 | 2022-01-18 12:30 | 1 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 5.9 | 10060 | 10060 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
SIERRA H08 PR | 11 | 2022-01-18 12:30 | 2022-01-18 19:30 | 7 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 6.19 | 10060 | 10060 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. RIG DOWN TEST EQUIPMENT. VERIFY STACK AND CHOKE ALIGNMENT. NOTE: COMPLETE ACCUMULATOR DRAW DOWN TEST
SIERRA H08 PR | 11 | 2022-01-18 19:30 | 2022-01-18 20:15 | 0.75 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 6.22 | 10060 | 10060 | 0 | C/O SAVER SUB. RIG MANAGER PRESENT
SIERRA H08 PR | 11 | 2022-01-18 20:15 | 2022-01-18 20:45 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.24 | 10060 | 10060 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS RIG MANAGER PRESENT
SIERRA H08 PR | 11 | 2022-01-18 20:45 | 2022-01-18 21:15 | 0.5 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 6.26 | 10060 | 10060 | 0 | INSTALL WEAR BUSHING AND TRIP NIPPLE
SIERRA H08 PR | 11 | 2022-01-18 21:15 | 2022-01-18 22:30 | 1.25 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 6.32 | 10060 | 10060 | 0 | PJSM. PICK UP DIR BHA #4: 6.75" SECURITY GTD64M SN:13685102 JETS 6X18 TFA: 1.491), MOTOR: 5.5", 6/7 8.8 2.12 TS HS88 .006, .68 REV/GAL; 4.07' BIT TO BEND; 5.50" PAD OD; FLOW RANGE-150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5" NMPDC, 5'' UBHO, 5" NMDC, 5",NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD. RESULT: GOOD TEST
SIERRA H08 PR | 11 | 2022-01-18 22:30 | 2022-01-19 02:45 | 4.25 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 6.49 | 10060 | 10060 | 0 | TIH W/BHA #4 F/BHA'-T/9,964' HOLE GIVING PROPER DISPLACEMENT. NOTE: FILLED PIPE & FLOW TESTED DRILL STRING, PICKED UP AGITATOR AND FLOW TESTED @ 2,802'. SPP BEFORE: 1320 PSI, SPP AFTER: 1,750 PSI @ 262 GPM.
SIERRA H08 PR | 11 | 2022-01-19 02:45 | 2022-01-19 03:15 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 6.51 | 10060 | 10060 | 0 | REMOVE TRIP NIPPLE AND INSTALL RT-HEAD; VERIFY VALVE ALIGNMENT TO BOP AND CHOKE MANIFOLD; PERFORM BOP DRILL AND FILL GAS SEPARATOR. NOTE: FLOW CHECK=NO FLOW
SIERRA H08 PR | 11 | 2022-01-19 03:15 | 2022-01-19 03:30 | 0.25 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 6.52 | 10060 | 10070 | 40 | DRILL SHOE TRACK AND 10' NEW FORMATION F/10,060'- T/10,070', WOB-10K, RPM-30, GPM-250, SPP: 2600, PSI, TQ-4/6K. TAG FLOAT @ 9,964' TAG SHOE @ 10,060'
SIERRA H08 PR | 11 | 2022-01-19 03:30 | 2022-01-19 04:30 | 1 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 6.57 | 10070 | 10070 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T GPM-350, SPP-3100 PSI, RPM-30. MW IN: 9.2 PPG MW OUT:9.2 PPG
SIERRA H08 PR | 11 | 2022-01-19 04:30 | 2022-01-19 04:45 | 0.25 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.58 | 10070 | 10070 | 0 | PERFORM F.I.T. WITH 9.1 PPG OBM, 1947 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,060' / TVD-9,854'
SIERRA H08 PR | 11 | 2022-01-19 04:45 | 2022-01-19 04:45 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.58 | 10070 | 10070 |  | MILESTONE_START CURVE SECTION 1/19/22 @ 04:45
SIERRA H08 PR | 11 | 2022-01-19 04:45 | 2022-01-19 06:00 | 1.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.63 | 10070 | 10100 | 24 | BUILD CURVE-SLIDE (30' IN 1.25 HR @ 37.5 FPH) WOB-15/20K, SPM-67/67, GPM 350, MRPM:238, SPP:3200-3800 PSI, DIFF:350/550 PSI, CHOKES: 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE=0 PSI, AVG CASING PRESSURE= 0 PSI. MAX SICP=0 PSI, AVG SICP: 0 PSI SLIDE DEPTHS: F/10,070'-T/10,100', 30', TF:HS, 04:45-06:00
SIERRA H08 PR | 12 | 2022-01-19 06:00 | 2022-01-19 09:30 | 3.5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.77 | 10100 | 10502 | 114.9 | BUILD CURVE-SLIDE (402' IN 3.47 HRS @ 115.85 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-3600/4400 PSI, DIFF-700/800 PSI, CHOKES- 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP=0 PSI. SLIDE DEPTHS: SLD F/10100 T/10344 244' TF-HS 0600-808 TQ- 3R 1L 30RPM SLD F/10380 T/10440 60' TF-HS 832-902 TQ- 3R 1L 30RPM SLD F/10489 T/10531 42' TF-HS 934-953 TQ-3R 1L 30RPM SLD F/10583 T/10626 43' TF-HS 1024-1044 TQ-3R 1L 30RPM SLD F/10662 T/10683 21' TF-HS 1109-1120 TQ-3R 1L 30RPM
SIERRA H08 PR | 12 | 2022-01-19 09:30 | 2022-01-19 11:15 | 1.75 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.85 | 10502 | 10683 | 103.4 | BUILD CURVE-ROT (181' IN 1.87 HR @ 96.79 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-30, TTLRPM-302, SPP-3600/4400 PSI, DIFF-700/800 PSI, CHOKES- 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP=0 PSI.
SIERRA H08 PR | 12 | 2022-01-19 11:15 | 2022-01-19 13:30 | 2.25 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.94 | 10683 | 10683 | 0 | PULLED OFF BOTTOM @ 10,683’, SPACED OUT AND CLOSED TOP VBR'S DUE TO CASING PRESSURE INCREASING TO 1357 PSI, CIRCULATE OUT GAS AND WEIGHT UP F/9.1 PPG T/9.3 PPG, SPM-76/76, GPM-400, SPP- 4300 PSI, CHOKES- 30-40% / 0%, FLARE-20-30', NO MUD CUT, MAX CASING PRESSURE= 2441 PSI, AVG CASING PRESSURE= 1500 PSI. CASING PRESSURE DECREASED T/815 PSI AFTER 1 FULL CIRCULATION, OPEN TOP VBR'S AND ATTEMPTED START BACK DRILLING, PULLED OFF BOTTOM @ 10,683’, SPACED OUT AND CLOSED TOP VBR'S DUE TO CASING PRESSURE INCREASING TO 1334 PSI, CIRCULATE OUT GAS AND WEIGHT UP F/9.3 PPG T/9.5 PPG, CHOKES- 0% / 29-32%, FLARE-15’-20', NO MUD CUT, MAX CASING PRESSURE= 1412 PSI, AVG CASING PRESSURE= 1300 PSI. CASING PRESSURE DECREASED T/862 PSI, OPEN TOP VBR'S AND START BACK DRILLING.
SIERRA H08 PR | 12 | 2022-01-19 13:30 | 2022-01-19 13:45 | 0.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.95 | 10683 | 10729 | 184 | BUILD CURVE-SLIDE (46' IN .32 HRS @ 143.75 FPH) WOB-25/35K, SPM-76/76, GPM-400, MRPM-272, SPP-4300/5100 PSI, DIFF-700/800 PSI, CHOKES- 29-32% / 0%, FLARE-10-20', NO MUD CUT, MAX CASING PRESSURE= 1344 PSI, AVG CASING PRESSURE=800 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1239 PSI, AVG SICP= 1239 PSI. SLIDE DEPTHS: SLD F/10683 T/10721 38' TF-HS 1340-1345 TQ-3R 1L 30RPM SLD F/10757 T/10765 8' TF-HS 1411-1420 TQ-3R 1L 30RPM
SIERRA H08 PR | 12 | 2022-01-19 13:45 | 2022-01-19 14:15 | 0.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.97 | 10729 | 10765 | 72 | BUILD CURVE-ROT (36' IN .43 HR @ 83.72 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-30, TTLRPM-302, SPP-4300/5100 PSI, DIFF-700/800 PSI, CHOKES- 29-32% / 0%, FLARE-10-20', NO MUD CUT, MAX CASING PRESSURE= 1344 PSI, AVG CASING PRESSURE=800 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1239 PSI, AVG SICP= 1239 PSI.
SIERRA H08 PR | 12 | 2022-01-19 14:15 | 2022-01-19 14:30 | 0.25 | P | PRDHLCV | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.98 | 10765 | 10765 | 0 | PULLED OFF BOTTOM @ 10,765’, SPACED OUT AND CLOSED TOP VBR'S DUE TO CASING PRESSURE INCREASING TO 1335 PSI, CIRCULATE OUT GAS AND WEIGHT UP F/9.5 PPG T/9.8 PPG, SPP-4300/5100 PSI, CHOKES- 0% / 29-32%, FLARE-15-20', NO MUD CUT, MAX CASING PRESSURE= 1602 PSI, AVG CASING PRESSURE= 1100 PSI. CASING PRESSURE DECREASED T/829 PSI, OPEN TOP VBR'S AND START BACK DRILLING.
SIERRA H08 PR | 12 | 2022-01-19 14:30 | 2022-01-19 15:45 | 1.25 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.03 | 10765 | 10884 | 95.2 | BUILD CURVE-SLIDE (119' IN 1.08 HRS @ 110.19 FPH) WOB-25/35K, SPM-76/76, G SPP-4300/5100 PSI, DIFF-700/800 PSI, CHOKES- 29-36% / 0%, FLARE-10-20', NO MUD CUT, MAX CASING PRESSURE= 962 PSI, AVG CASING PRESSURE=800 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1264 PSI, AVG SICP= 1264 PSI. SLIDE DEPTHS: SLD F/10765 T/10884 119' TF-HS 1441-1545 TQ-3R 1L 30RPM
SIERRA H08 PR | 12 | 2022-01-19 15:45 | 2022-01-19 15:45 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 7.03 | 10884 | 10884 |  | MILESTONE_START LATERAL SECTION ON 1/19/2022 @ 15:45
SIERRA H08 PR | 12 | 2022-01-19 15:45 | 2022-01-19 15:45 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 7.03 | 10884 | 10884 |  | MILESTONE_LAND/END CURVE SECTION ON 1/19/2022 @ 15:45
SIERRA H08 PR | 12 | 2022-01-19 15:45 | 2022-01-19 21:45 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.28 | 10884 | 11773 | 148.2 | ROTATE DRILL LATERAL (889' IN 5.93 HRS @ 149.91 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM- 80, TQ- 6K/9K, MRPM-272, TTRPM-352, SPP-3700/4500 PSI, DIFF- 800/1000 PSI, CHOKES- 100% / 100%, FLARE-10-25', NO MUD CUT, MAX CASING PRESSURE= 1030 PSI, AVG CASING PRESSURE= 300 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1065 PSI. NOTE: WEIGHT UP F/9.8 PPG T/10.0 PPG @ 10,943'. PUMPING 10 BBL 12.5 PPB EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. NOTE: TARGET CHANGE RECEIVED VIA TEXT & EMAIL @ 21:00 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 11,570', NEW TARGET: 10,396' TVD (0' VS) AT 87.4 DEG INC., WINDOW 5' ABOVE / 5' BELOW.
SIERRA H08 PR | 12 | 2022-01-19 21:45 | 2022-01-19 22:45 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.33 | 11773 | 11855 | 82 | SLD DRILL LATERAL (82' IN 1.07 HRS @ 76.63 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -3700/4000 PSI, DIFF-300 PSI, CHOKES- 100% / 100%, FLARE-10-25', NO MUD CUT, MAX CASING PRESSURE= 1030 PSI, AVG CASING PRESSURE= 300 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1065 PSI. SLIDE DEPTHS: SLD F/10921 T/10953 32' TF-180 1638-1654 RPM-30 3R/1L SLD F/11206 T/11226 20' TF-40L 1833-1852 RPM-40 4R/3L SLD F/11301 T/11316 15' TF-30L 1921-1935 RPM-40 TQ-4R/3L SLD F/11490 T/11505 15' TF-120L 2027-2042 RPM-40 3R/2L
SIERRA H08 PR | 12 | 2022-01-19 22:45 | 2022-01-19 23:30 | 0.75 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.36 | 11855 | 11855 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80
SIERRA H08 PR | 12 | 2022-01-19 23:30 | 2022-01-20 04:15 | 4.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.56 | 11855 | 12602 | 157.3 | ROTATE DRILL LATERAL (747' IN 4.83 HRS @ 154.65 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM- 80, TQ- 6K/9K, MRPM-272, TTRPM-352, SPP-3700/4500 PSI, DIFF- 800/1000 PSI, CHOKES- 100% / 100%, FLARE-10-25', NO MUD CUT, MAX CASING PRESSURE= 1030 PSI, AVG CASING PRESSURE= 300 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1065 PSI. NOTE: WEIGHT UP F/9.8 PPG T/10.0 PPG @ 10,943'. PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. NOTE: TARGET CHANGE RECEIVED VIA TEXT & EMAIL @ 23:00 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 11,855', NEW TARGET: 10,407' TVD (0' VS) AT 87.1 DEG INC., WINDOW 5' ABOVE / 5' BELOW. NOTE: TARGET CHANGE RECEIVED VIA TEXT & EMAIL @ 04:27 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 12,520', NEW TARGET: 10,400' TVD (0' VS) AT 87.2 DEG INC., WINDOW 5' ABOVE / 5' BELOW.
SIERRA H08 PR | 12 | 2022-01-20 04:15 | 2022-01-20 06:00 | 1.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.63 | 12602 | 12705 | 58.9 | SLD DRILL LATERAL (103' IN 1.92 HRS @ 53.64 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -3700/4000 PSI, DIFF-300 PSI, CHOKES- 100% / 100%, FLARE-10-25', NO MUD CUT, MAX CASING PRESSURE= 1030 PSI, AVG CASING PRESSURE= 300 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1065 PSI. SLIDE DEPTHS: SLD F/11867 T/11887 20' TF-110R 2329-2348 RPM-50TQ 4R/2L SLD F/11961 T/11981 20' TF-70R 0020-0037 RPM60TQ 5R/3L SLD F/12056 T/12076 20' TF-90R 102-122 RPM-60 TQ5R/3L SLD F/12149 T/12164 15' TF-60R 150-212 RPM-60 TQ-6R 4L SLD F/12336 T/12344 8' TF-20L 314-328 RPM-60 TQ-6R/4L SLD F/12621 T/12641 20' TF-160L 0507-0530 RPM-70 TQ-5R/3L
SIERRA H08 PR | 13 | 2022-01-20 06:00 | 2022-01-20 11:30 | 5.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.86 | 12705 | 13693 | 179.6 | ROTATE DRILL LATERAL (988' IN 5.63 HRS @ 175.49 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM- 80, TQ- 8K/10K, MRPM-272, TTRPM-352, SPP-3800/4800 PSI, DIFF- 800/1000 PSI, CHOKES- 100% / 100%, FLARE-10-25', NO MUD CUT, MAX CASING PRESSURE= 156 PSI, AVG CASING PRESSURE= 80 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 542 PSI. NOTE: ENCOUNTERED 100-120 BPH LOSSES @ 12,891’, PUMPED A 30 BBL 30 PPB PROCOR LCM SWEEP AND STARTED CUTTING MUD F/10.0 PPG T/9.8 PPG, PUMPED 10 BBL 30 PPB PROCOR LCM SWEEP EVERY STAND CONSISTING OF ACTIVE MUD, 5 PPB MAGNA FIBER, 5 PPB NEWCARB, 5 PPB NEW FAULT & 15 PPB PROCOR, ONCE 9.8 PPG WAS @ SURFACE LOSSES DECREASED TO 40-50 BPH. NOTE: TARGET CHANGE RECEIVED VIA TEXT & EMAIL @ 09:27 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 13,274', NEW TARGET: 10,406' TVD (0' VS) @ 87.2 DEG INC, WINDOW 5' ABOVE / 5' BELOW
SIERRA H08 PR | 13 | 2022-01-20 11:30 | 2022-01-20 12:45 | 1.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.91 | 13693 | 13748 | 44 | SLD DRILL LATERAL (55' IN 1.12 HRS @ 49.12 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -3800/4300 PSI, DIFF-300/500 PSI, CHOKES- 100% / 100%, FLARE-10-25', NO MUD CUT, MAX CASING PRESSURE= 156 PSI, AVG CASING PRESSURE= 80 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 542 PSI. SLIDE DEPTHS: SLD F/13005 T/13020 15' TF-130R 747-802 TQ- 7R 5L RPM-80 SLD F/13474 T/13494 20' TF-90R 1037-1104 TQ- 5R 3L RPM-60 SLD F/13664 T/13684 20' TF-90R 1205-1230 TQ- 5R 3L RPM-70
SIERRA H08 PR | 13 | 2022-01-20 12:45 | 2022-01-20 14:00 | 1.25 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 7.96 | 13748 | 13748 | 0 | DECISION WAS MADE TO DRILL UNDER A MUD CAP, BULLHEADED 121 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE @ 13,748’ WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/262 GPM, INITIAL KILL LINE SPP= 1082 PSI AND INITIAL CASING PRESSURE= 805 PSI, CASING FINAL KILL LINE SPP= 957 PSI AND FINAL CASING PRESSURE= 0 PSI, CREATE MUD CAP. DISPLACE DRILL PIPE CAPACITY WITH FRESHWATER.
SIERRA H08 PR | 13 | 2022-01-20 14:00 | 2022-01-20 16:15 | 2.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.06 | 13748 | 14013 | 117.8 | ROTATE DRILL LATERAL (265' IN 2.2 HR @ 120.46 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-11K/15K, MRPM-272, TTRPM-352, SPP- 4700/5700 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMPING 10 BBLS PHPA SWEEPS EVERY +/- 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA. NOTE: TARGET CHANGE RECEIVED VIA TEXT & EMAIL @ 16:11 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 14,003', NEW TARGET: 10,412' TVD (0' VS) @ 87.2 DEG INC, WINDOW 5' ABOVE / 5' BELOW
SIERRA H08 PR | 13 | 2022-01-20 16:15 | 2022-01-20 16:30 | 0.25 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.07 | 14013 | 14033 | 80 | SLD DRILL LATERAL (20' IN .3 HRS 66.7 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4700/5200 PSI, DIFF- 300/500 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/13759 T/13779 20' TF-90R 1424-1442 TQ- 4R 2L RPM-70
SIERRA H08 PR | 13 | 2022-01-20 16:30 | 2022-01-20 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.09 | 14033 | 14033 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
SIERRA H08 PR | 13 | 2022-01-20 17:00 | 2022-01-20 23:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.34 | 14033 | 14837 | 134 | ROTATE DRILL LATERAL (804' IN 6.05 HR @ 140.49 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-10K/15K, MRPM-272, TTRPM-352, SPP- 4700/5700 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMPING 10 BBLS PHPA SWEEPS EVERY +/- 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA. NOTE: TARGET CHANGE RECEIVED VIA TEXT & EMAIL @ 00:15 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 14,900', NEW TARGET: 10,442' TVD (0' VS) @ 87.5 DEG INC, WINDOW 5' ABOVE / 5' BELOW
SIERRA H08 PR | 13 | 2022-01-20 23:00 | 2022-01-21 03:00 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.5 | 14837 | 14941 | 26 | SLD DRILL LATERAL (104' IN 3.95 HRS 26.32 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4700/5200 PSI, DIFF- 300/500 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/14038 T/14063 25' TF-130L 1703-1737 TQ- 7R 4L RPM-70 SLD F/14133 T/14158 25' TF-120L 1807-1842 RPM-70 TQ-8R/6L SLD F/14897 T/14921 24' TF-45R 0000-135 RPM-80 TQ-13R/10L SLD F/14421 T/14441 20' TF-130L 2042-2132 RPM-80 TQ-8R/6L SLD F/14326 T/14336 12' TF-120L 1945-2008 RPM-80 TQ- 8R/6L NOTE: SURVEY @ 14,822' SHOWED 7.17 DLS DOWN AND LEFT IN ROTATION F/ 85.43 INC. AND 151.73 AZ T/ 82.9 INC. AND 145.29 AZ.. ATTEMPT TO SLIDE BACK UP 24' AND INC AND AZ. DROPPPED AGAIN DOWN AND LEFT T/ 80.68 INC. & 141.08 AZ.
SIERRA H08 PR | 13 | 2022-01-21 03:00 | 2022-01-21 03:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.52 | 14941 | 14941 | 0 | CIRCULATE AND CONDITION HOLE WHILE WAITING ON ORDERS FROM ENGINEER. NOTE: DUE TO DROP IN INCLINATION AND AZIMUTH, DECISION MADE TO GO INTO 100% SLIDE UNTILL CHANGE IN INC AND AZ ARE SEEN ON INSTANTANEOUS.
SIERRA H08 PR | 13 | 2022-01-21 03:30 | 2022-01-21 04:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.55 | 14941 | 14966 | 50 | ROTATE DRILL LATERAL (25' IN .33 HR @ 75.7 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-10K/15K, MRPM-272, TTRPM-352, SPP- 4700/5700 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMPING 10 BBLS PHPA SWEEPS EVERY +/- 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA.
SIERRA H08 PR | 13 | 2022-01-21 04:00 | 2022-01-21 06:00 | 2 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.63 | 14966 | 15065 | 49.5 | SLD DRILL LATERAL (64' IN 2.67 HRS 23.9 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4700/5200 PSI, DIFF- 300/500 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/14987 T/15024 37' TF-35R 0300-0500 TQ- 14R 13L RPM-80 SLD F/15050 T/15065 15' TF-45R 0520-0600 TQ- 14R 13L RPM-80
SIERRA H08 PR | 14 | 2022-01-21 06:00 | 2022-01-21 06:30 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.65 | 15065 | 15090 | 50 | ROTATE DRILL LATERAL (25' IN .33 HR @ 75.76 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-18K/21K, MRPM-272, TTRPM-352, SPP- 4700/5700 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 216 PSI, AVG CASING PRESSURE= 130 PSI, MAX SICP= 226 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMPING 10 BBLS PHPA SWEEPS EVERY +/- 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA.
SIERRA H08 PR | 14 | 2022-01-21 06:30 | 2022-01-21 08:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.71 | 15090 | 15122 | 21.3 | SLD DRILL LATERAL (32' IN 1.67 HRS @ 19.16 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4700/5300 PSI, DIFF- 400/600 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/15065 T/15076 11' TF-45R 0600-0625 TQ- 16R 13L RPM-80 SLD F/15101 T/15122 21' TF-90R 0645-0800 TQ- 16R 14L RPM-80
SIERRA H08 PR | 14 | 2022-01-21 08:00 | 2022-01-21 08:30 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.73 | 15122 | 15122 | 0 | AFTER THE LAST SLIDE FROM 15,101' T/ 15,122', ATTEMPTED TO PICK UP OFF BOTTOM AND DRILL STRING WEIGHT DID NOT BREAK OVER, SLACKED OFF TO NEUTRAL WEIGHT AND TURNED ROTARY ON @ 50 RPM, TORQUE BROKE OVER @ 19K, TAG BOTTOM AND MOTOR STALLED OUT @ 1600 PSI, SHUT DOWN PUMPS AND SLOWLY RELEASED TRAPPED TORQUE, PICKED OFF BOTTOM AND SLOWLY STAGE PUMPS UP T/400 GPM, SPP STABLIZED @ 4300 PSI OFF BOTTOM PRESSURE, BACK REAMED 20’ OF SLIDE @ 50 RPM, TAG BOTTOM @ 50 FPH AND MOTOR STALLED OUT @ 1600 PSI, SHUT DOWN PUMPS AND SLOWLY RELEASED TRAPPED TORQUE, PICKED OFF BOTTOM AND SLOWLY STAGE PUMPS UP T/400 GPM, SPP STABLIZED @ 4300 PSI OFF BOTTOM PRESSURE. DECISION WAS MADE TO TRIP OUT THE HOLE FOR NEW MOTOR.
SIERRA H08 PR | 14 | 2022-01-21 08:30 | 2022-01-21 09:45 | 1.25 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.78 | 15122 | 15122 | 0 | PUMPED 30 BBL PHPA SWEEP AND CIRCULATE HOLE CLEAN WHILE PREPPING PITS WITH 12.8 PPG OBM. NOTE: BULLHEADED 50 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/157 GPM, INITIAL KILL LINE SPP= 662 PSI AND INITIAL CASING PRESSURE= 570 PSI, FINAL KILL LINE SPP= 750 PSI AND FINAL CASING PRESSURE= 0 PSI WHILE CIRCULATING HOLE CLEAN
SIERRA H08 PR | 14 | 2022-01-21 09:45 | 2022-01-21 16:45 | 7 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.08 | 15122 | 15122 | 0 | STRIP OUT OF THE HOLE WET F/15,122'- T/2,970'. FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. 320K MAX OVER PULL, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
SIERRA H08 PR | 14 | 2022-01-21 16:45 | 2022-01-21 17:15 | 0.5 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.1 | 15122 | 15122 | 0 | FLOW TEST AGITATOR BEFORE AND AFTER @ GPM-262, SPM-100, SPP BEFORE LAYING DOWN AGITATOR: 680 PSI; SPP AFTER LAYING DOWN AGITATOR: 480 PSI. LAY AGITATOR DOWN.
SIERRA H08 PR | 14 | 2022-01-21 17:15 | 2022-01-21 18:00 | 0.75 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.13 | 15122 | 15122 | 0 | CONTINUE STRIPPING OUT OF THE HOLE WET F/2,970'- T/507'. FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
SIERRA H08 PR | 14 | 2022-01-21 18:00 | 2022-01-21 18:30 | 0.5 | U | PRDHLLT | WCTRL | KWELL | KILL WELL | 9.15 | 15122 | 15122 | 0 | BULLHEADED 50 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/262 GPM, INITIAL KILL LINE SPP= 105 PSI AND INITIAL CASING PRESSURE= 0 PSI, FINAL KILL LINE SPP= 1007 PSI AND FINAL CASING PRESSURE= 0 PSI. OPEN CHOKE AND MONITORED FLOW (NO FLOW), OPEN ORBIT VALVE, CHECK FLOW ( NO FLOW).
SIERRA H08 PR | 14 | 2022-01-21 18:30 | 2022-01-21 19:00 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 9.17 | 15122 | 15122 | 0 | PULL ROTATING HEAD AND INSTALL TRIP NIPPLE, NO FLOW @ TRIP TANK.
SIERRA H08 PR | 14 | 2022-01-21 19:00 | 2022-01-21 19:15 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 9.18 | 15122 | 15122 | 0 | TRIPPING OUT THE HOLE F/507' T/BHA, FILLING BACKSIDE WITH 12.8 PPG OBM WITH CALCULATED FILL OF 1.9 BBLS/STD.
SIERRA H08 PR | 14 | 2022-01-21 19:15 | 2022-01-21 20:00 | 0.75 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.21 | 15122 | 15122 | 0 | RACK BACK DRILL-N-REAMER, L/D TOP NMDC AND REMOVE MWD, PULL BHA TO MUD MOTOR, OBSERVED LOWER END OF MOTOR & BIT LEFT IN HOLE.
SIERRA H08 PR | 14 | 2022-01-21 20:00 | 2022-01-21 20:30 | 0.5 | U | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.23 | 15122 | 15122 | 0 | SERVICE TOP DRIVE, DRAWORKS AND ST-80
SIERRA H08 PR | 14 | 2022-01-21 20:30 | 2022-01-21 21:30 | 1 | U | PRDHLLT | WAIT | WORD | WAIT ON ORDERS | 9.27 | 15122 | 15122 | 0 | CLEAN & CLEAR RIG FLOOR WHILE CONFERENCE UP WITH DRLG ENGINEER & DRLG MANAGER. DECISION WAS MADE TO CALL TD OF WELL, RIH WITH MILL TOOTH BIT AND DUMB IRON TO LOCATE AND ENSURE FISH IS PUSHED TO BOTTOM. ( ESTIMATED TOF: 15,091'), STRAP BIT SUB & X/O'S FOR DUMB IRON ASSEMBLY.
SIERRA H08 PR | 14 | 2022-01-21 21:30 | 2022-01-21 21:30 | 0 | U | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 9.27 | 15122 | 15122 |  | MILESTONE_ TD WELL ON 1-21-22 @ 21:30 PM
SIERRA H08 PR | 14 | 2022-01-21 21:30 | 2022-01-21 22:45 | 1.25 | U | PRDHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 9.33 | 15122 | 15122 | 0 | LAY DOWN DIRECTIONAL ASSEMBLY, THRUSTER, UBHO, NON MAG PONY COLLAR, AND REAMER... PICK UP CROSS OVER, AND MILL TOOTH BIT.
SIERRA H08 PR | 14 | 2022-01-21 22:45 | 2022-01-21 23:30 | 0.75 | U | PRDHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 9.36 | 15122 | 15122 | 0 | TRIP IN THE HOLE F/ BHA T/ 2,240' WITH NO RETURNS, FILL PIPE, CHECK FOR FLOW
SIERRA H08 PR | 14 | 2022-01-21 23:30 | 2022-01-22 | 0.5 | U | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.38 | 15122 | 15122 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
SIERRA H08 PR | 14 | 2022-01-22 | 2022-01-22 05:30 | 5.5 | U | PRDHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 9.61 | 15122 | 15122 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/2,240' T/15,091', FILLING PIPE EVERY 40 STDS, CHOKE: 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI; TAGGED TOP OF FISH @ 15,091', SAT DOWN 50K TO CONFIRM T.O.F. NOTE: WORKED THROUGH TIGHT HOLE @ 13,551', FILL PIPE, CAUGHT PRESSURE, GPM:270, RPM:100, PSI:3,230, TRQ:7-9K; AFTER WORKING THROUGH TIGHT HOLE, WAS WAS ABLE TO CONTINUE TRIPPING IN ON ELEVATORS.
SIERRA H08 PR | 14 | 2022-01-22 05:30 | 2022-01-22 06:00 | 0.5 | U | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.63 | 15122 | 15122 | 0 | CIRCULATE BOTTOM UP, PREP FLOOR TO LAY DOWN DRILL PIPE
SIERRA H08 PR | 15 | 2022-01-22 06:00 | 2022-01-22 06:30 | 0.5 | U | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.65 | 15122 | 15122 | 0 | CONTINUE CIRCULATING BOTTOM UP, PREPPING FLOOR TO LAY DOWN DRILL PIPE.
SIERRA H08 PR | 15 | 2022-01-22 06:30 | 2022-01-22 09:15 | 2.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 9.76 | 15122 | 15122 | 0 | STRIP OUT OF THE HOLE WET F/15,091' T/14,326' WHILE LAYING DOWN DRILL PIPE, FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 1256 PSI AVG CASING PRESSURE= 720 PSI.NOTE, @ 14,926' CASING PRESSURE INCREASED F/ 0 PSI T/1,256 PSI, START FILLING BACKSIDE WITH 17.5 PPG KILL MUD CALCULATED FILL OF 1.9 BBLS/STD. BY 13,343' PRESSURE REDUCED TO 145 PSI WITH 35 BBLS 17.5 PPG KILL MUD PUMPED. NOTE: ENCOUNTERED TIGHT DRILL PIPE CONNECTIONS AND HAD TO USE RIG TONGS.
SIERRA H08 PR | 15 | 2022-01-22 09:15 | 2022-01-22 09:45 | 0.5 | U | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.78 | 15122 | 15122 | 0 | LOST AIR SUPPLY TO DRAWWORKS DUE TO FROZEN AIR LINE ON GRASS HOPPER, THAWED OUT AIR LINE.
SIERRA H08 PR | 15 | 2022-01-22 09:45 | 2022-01-22 22:30 | 12.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 10.32 | 15122 | 15122 | 0 | CONTINUE STRIPPING OUT OF THE HOLE WET WHILE LAYING DOWN DRILL PIPE F/14,326' T/388' FILLING BACKSIDE WITH 12.8 PPG KILL MUD CALCULATED FILL OF 1.9 BBLS/STD. @ 5,975' STARTED FILLING BACKSIDE WITH 17.5 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD, (21 BBLS, TOTAL 81 BBLS). MAX CASING PRESSURE= 201 PSI, AVG CASING PRESSURE= 0 PSI. NOTE: ENCOUNTERED TIGHT DRILL PIPE CONNECTIONS AND HAD TO USE RIG TONGS F/13,415' T/12,736'.
SIERRA H08 PR | 15 | 2022-01-22 22:30 | 2022-01-23 | 1.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 10.38 | 15122 | 15122 | 0 | STRIP IN THE HOLE F/388' T/4,242' WITH PIPE THAT PREVIOUSLY RACKED BACK IN DERRICK, CHOKES: 0% / 0% , SICP= 0 PSI.
SIERRA H08 PR | 15 | 2022-01-23 | 2022-01-23 04:30 | 4.5 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 10.57 | 15122 | 15122 | 0 | STRIP OUT OF THE HOLE WET WHILE LAYING DOWN DRILL PIPE F/4,242' T/1,215' FILLING BACKSIDE WITH 12.8 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD, MAX CASING PRESSURE= 131 PSI, AVG CASING PRESSURE= 0 PSI.
SIERRA H08 PR | 15 | 2022-01-23 04:30 | 2022-01-23 06:00 | 1.5 | P | PRDHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 10.63 | 15122 | 15122 | 0 | SLIP AND CUT 140' OF DRILL LINE. NOTE: WHILE CUTTING DRILL LINE BULLHEADED 50 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/262 GPM, INITIAL KILL LINE SPP= 488 PSI AND INITIAL CASING PRESSURE= 0 PSI, FINAL KILL LINE SPP= 225 PSI AND FINAL CASING PRESSURE= 0 PSI. OPEN CHOKE AND MONITORED FLOW (NO FLOW), OPEN ORBIT VALVE, CHECK FLOW ( NO FLOW).
SIERRA H08 PR | 16 | 2022-01-23 06:00 | 2022-01-23 06:45 | 0.75 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 10.66 | 15122 | 15122 | 0 | CONTINUE STRIPPING OUT THE HOLE F/1,215' T/400', FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD.
SIERRA H08 PR | 16 | 2022-01-23 06:45 | 2022-01-23 07:15 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.68 | 15122 | 15122 | 0 | FLOW CHECK, NO FLOW, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
SIERRA H08 PR | 16 | 2022-01-23 07:15 | 2022-01-23 07:30 | 0.25 | P | PRDHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 10.69 | 15122 | 15122 | 0 | TRIP OUT THE HOLE F/400' T/ BHA, FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD.
SIERRA H08 PR | 16 | 2022-01-23 07:30 | 2022-01-23 08:00 | 0.5 | P | PRDHLCSG | WCTRL | KWELL | KILL WELL | 10.71 | 15122 | 15122 | 0 | OBSERVED MUD LEVEL SLOWLY RISING ON THE FLOW CHECK @ BHA, CLOSED TOP VBR'S, BULLHEADED 46 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/157 GPM, INITIAL KILL LINE SPP= 457 PSI AND INITIAL CASING PRESSURE= 210 PSI, FINAL KILL LINE SPP= 545 PSI AND FINAL CASING PRESSURE= 0 PSI. OPEN CHOKE AND MONITORED FLOW (NO FLOW), OPEN ORBIT VALVE, CHECK FLOW ( NO FLOW).
SIERRA H08 PR | 16 | 2022-01-23 08:00 | 2022-01-23 09:00 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.75 | 15122 | 15122 | 0 | BREAK BIT, L/D BIT SUB, BTI VALVE, 2 MONELS AND X-OVER WHILE MONITORING SICP, SICP= 0 PSI.
SIERRA H08 PR | 16 | 2022-01-23 09:00 | 2022-01-23 10:15 | 1.25 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 10.81 | 15122 | 15122 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELAVATORS WHILE MONITORING SICP, SICP= 0 PSI.
SIERRA H08 PR | 16 | 2022-01-23 10:15 | 2022-01-23 10:45 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.83 | 15122 | 15122 | 0 | SERVICE TOP DRIVE AND DRAWWORKS.
SIERRA H08 PR | 16 | 2022-01-23 10:45 | 2022-01-23 12:15 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.89 | 15122 | 15122 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT WHILE MONITORING SICP, SICP= 0 PSI.
SIERRA H08 PR | 16 | 2022-01-23 12:15 | 2022-01-23 15:00 | 2.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11 | 15122 | 15122 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/2,007' WITH NO RETURNS, FILLING PIPE ON THE FLY WITH WATER.
SIERRA H08 PR | 16 | 2022-01-23 15:00 | 2022-01-23 15:30 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 11.02 | 15122 | 15122 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
SIERRA H08 PR | 16 | 2022-01-23 15:30 | 2022-01-23 18:30 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.15 | 15122 | 15122 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/2,007' T/5,616.18' WHILE STRIPPING IN WITH NO RETURNS. MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY WITH WATER.
SIERRA H08 PR | 16 | 2022-01-23 18:30 | 2022-01-23 19:00 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 11.17 | 15122 | 15122 | 0 | RIG DOWN 5" CRT AND ELEVATORS, RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
SIERRA H08 PR | 16 | 2022-01-23 19:00 | 2022-01-24 01:00 | 6 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.42 | 15122 | 15122 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/5,616.18' T/15,050' WHILE STRIPPING IN, MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY, NO RETURNS, CHOKES: 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
SIERRA H08 PR | 16 | 2022-01-24 01:00 | 2022-01-24 01:30 | 0.5 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.44 | 15122 | 15122 | 0 | WASH AND REAM PRODUCTION CASING F/15,050' T/15,083' @ 10-20 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-8K/10K, SPM-100, GPM-262, SPP-2950 PSI, NO RETURNS, CHOKES: 0% / 0%, REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD, SLACK OFF AND INSTALL ROTATING HEAD, OPEN ANNULAR, LAND ON HANGER W/125K (W/O BLOCKS) @ 15,083.7’, RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICYWEDGE 425 CASING, 2 JTS 5" 18# P110 ICYWEDGE 425 CASING AND TEST FLOAT EQUIPMENT. RAN 123 JTS OF 5" 18# P110 ICY WEDGE 425 CASING (127 JTS TOTAL), 1- X-OVER 425x463, 1 JOINT WEDGE 463, 1-5.5" MARKER JT, RAN 210 JTS OF 5.5" 23# P-110 WEDGE 463 (212 JTS TOTAL), 1-5.5" MARKER JT, 1 JOINT WEDGE 463. CASING SHOE @ 15,083.7' TOP OF FLOAT COLLAR @ 15,034.6' BTM OF TOE SLEEVE VALVE @ 14,991.0' TOP OF TOE SLEEVE VALVE @ 14,965.9' TOP OF X-OVER @ 9,467.5' TOP OF MARKER JT @ 9,403.3' LEFT OUT 40 JOINTS OF 5" -1,751.12' LEFT OUT 9 JOINTS OF 5.5"-398.9'
SIERRA H08 PR | 16 | 2022-01-24 01:30 | 2022-01-24 02:30 | 1 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 11.48 | 15122 | 15122 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV, CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE, MONITOR SICP, SICP= 0 PSI.
SIERRA H08 PR | 16 | 2022-01-24 02:30 | 2022-01-24 04:00 | 1.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.55 | 15122 | 15122 | 0 | CIRCULATE 1 CASING CAPACITY WITH CHOKES CLOSED WHILE RIGGING DOWN CASING TOOLS, SPM-64/64, GPM-336 (8 BPM), SPP- 3580 PSI. INITIAL CASING PRESSURE WHILE CIRCULATING= 0 PSI AND FINAL CASING PRESSURE WHILE CIRCULATING= 0 PSI, SHUT IN CASING PRESSURE= 0 PSI. HOLD PJSM WITH NINE CEMENT CREW.
SIERRA H08 PR | 16 | 2022-01-24 04:00 | 2022-01-24 06:00 | 2 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 11.63 | 15122 | 15122 | 0 | SWAP CIRCULATING IRON T/ CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8,000 PSI, CEMENTED 1ST STAGE 5/5.5" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 45 BBL 10.5 PPG WEIGHTED SPACER, 193 BBL 13.5 PPG 930 SK 1.75 YIELD 35/65 POZ-CLASS H LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 298 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 7 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 3,250 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4,250 PSI, HELD FOR 5 MIN, BLED BACK 5.0 BBLS. FLOATS HELD. MAX CSG PSI= 0 PSI, AVG CASING PSI=0 PSI, CSG PRESSURE=0 PSI WITH PUMPS OFF AFTER CEMENTING.
SIERRA H08 PR | 17 | 2022-01-24 06:00 | 2022-01-24 06:45 | 0.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 11.66 | 15122 | 15122 | 0 | HELD PJSM, RIG DOWN CIRCULATING IRON FROM RIG FLOOR, REMOVE CHECK VALVE FROM KILL LINE, RIG UP CIRCULATING IRON TO KILL LINE WHILE MONITORING SICP, SICP= 0 PSI.
SIERRA H08 PR | 17 | 2022-01-24 06:45 | 2022-01-24 09:00 | 2.25 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 11.75 | 15122 | 15122 | 0 | TESTED CEMENTING LINES T/8500 PSI, PUMP 30 BBLS 17.5 PPG KILL MUD DOWN THE BACKSIDE THROUGH KILL LINE @ 1 BPM=10 PSI & CASING PSI= 0 PSI; 2 BPM=77 PSI & CASING PSI=0 PSI; 3 BPM=130 PSI & CASING PSI=0 PSI; 4 BPM= 147 PSI & CASING PSI=0 PSI AND 5 BPM=4237 PSI & CASING PSI=4000, 4237 PSI TO ESTABLISH INJECTION RATES. INITIAL CSG PSI=0 PSI , FINAL CSG PSI=4000 PSI. ONCE PUMP WAS SHUT DOWN SICP FELL TO 0 PSI, PUMP 35 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 217 BBLS 685 SK 1.78 YIELD 35/65 POZ-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 20 BBLS WATER. MAX CSG PSI= 3340PSI W/10 BBLS OF LEAD CEMENT PUMPED @ 4.5 BPM, AVG CASING PSI= 2100 PSI. MAX PUMP PRESSURE=3456 PSI @ 4.5 BPM. CSG PRESSURE DECREASED TO 459 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC-1210'.
SIERRA H08 PR | 17 | 2022-01-24 09:00 | 2022-01-24 09:15 | 0.25 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 11.76 | 15122 | 15122 | 0 | MONITOR SICP, INITIAL SICP= 459 PSI, SLOWLY BLED OFF SICP F/459 PSI T/393 PSI TO TRIP TANK WITH NO RETURNS, MONITOR SICP FOR 5 MIN. AND SICP STABLIZED @ 400 PSI, SLOWLY BLED OFF SICP F/400 PSI T/350 PSI TO TRIP TANK WITH NO RETURNS, MONITOR SICP FOR 5 MIN. AND SICP STABLIZED @ 353 PSI, SLOWLY BLED OFF SICP F/353 PSI T/243 PSI TO TRIP TANK WITH NO RETURNS, MONITOR SICP FOR 5 MIN. AND SICP STABLIZED @ 247 PSI, SLOWLY BLED OFF SICP F/247 PSI T/159 PSI TO TRIP TANK WITH NO RETURNS, MONITOR SICP FOR 5 MIN. AND SICP STABLIZED @ 163 PSI, SLOWLY BLED OFF SICP F/163 PSI T/0 PSI TO TRIP TANK WITH NO RETURNS, MONITOR SICP FOR 5 MIN. AND SICP STABLIZED @ 0 PSI FINAL SICP= 0 PSI; RIG DOWN CEMENT HEAD, CEMENT SWEDGE, FOSV AND CIRCULATING IRON.
SIERRA H08 PR | 17 | 2022-01-24 09:15 | 2022-01-24 11:15 | 2 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 11.85 | 15122 | 15122 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE FOSV AND LAY DOWN LANDING JOINT. REMOVE BAILS AND CASING ELEVATORS, AND RIG UP RIG 4.5" ELEVATORS, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 150 GPM W/53 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
SIERRA H08 PR | 17 | 2022-01-24 11:15 | 2022-01-24 13:30 | 2.25 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 11.94 | 15122 | 15122 | 0 | REMOVE FLOW LINE FROM SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, BACKOUT WH SET SCREWS AND RAISE BOPE, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI. RELEASE WELL ON 01/25/2022 @ 00:00 HRS.
SIERRA H08 PR | 17 | 2022-01-24 13:30 | 2022-01-24 17:00 | 3.5 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 12.09 | 15122 | 15122 | 0 | REMOVE TURN BUCKLES, REMOVE HCR LINE, KILL LINE, KILL LINE CHECK VALVE, HYDRAULIC LINES, HOLE FILL, REMOVE FLOW LINE AND AIR LINES/HYDRAULIC LINES FROM ROTATING HEAD, LAY OVER AND SECURE BOP’S, CLEAN MUD TANKS
SIERRA H08 PR | 17 | 2022-01-24 17:00 | 2022-01-25 | 7 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 12.38 | 15122 | 15122 | 0 | CHANGE OUT SWIVEL PACKING AND SAVER SUB F/ CET 43 T/ 4 1/2 IF, RIG DOWN AND ELEVATORS AND BALES; CLEAN AND ORGANIZE RIG FLOOR, REMOVE ALL 4 ½” DRILL PIPE EQUIPMENT FROM RIG FLOOR ,PERFORM 90 DAY INSPECTION ON TOP DRIVE; PIN TOP DRIVE, PIN TOP DRIVE TO TRACK, UNSPOOL DRAWWORKS; REMOVE FEATHER RINGS AND SAVOR SUB, CONTINUE TO CLEAN MUD TANKS. NOTE: FINISHED CLEANING MUD TANKS 1/25/21 @ 00:00 AM
SIERRA H08 PR | 17 | 2022-01-25 | 2022-01-25 06:00 | 6 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 12.63 | 15122 | 15122 | 0 | CONTINUE TO RIG DOWN ASSIST CLEANING CREW. UNSPOOL DRAWWORKS; REMOVE FEATHER RINGS AND SAVOR SUB, START RIGGING DOWN ELECTRICAL AND HYDRAULIC HOSES FROM RIG FLOOR TO FESTOON, PULL AND UNHOOK ELECTRICAL, HYDRAULIC, WATER, MUD AND AIR LINES FROM MUD TANKS. KNOCK LOOSE TANK UNIONS AND EQUALIZERS.
SIERRA H08 PR | 17 | 2022-01-25 | 2022-01-25 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 12.38 | 15122 | 15122 |  | MILESTONE_WELL RELEASE ON 01/25/2022 @ 00:00
SIERRA H08 PR | 18 | 2022-01-25 06:00 | 2022-01-26 | 18 | P | PRDHLCSG | LMOV | RDMO | RIG DOWN MOVE OUT | 13.38 | 15122 | 15122 | 0 | HELD PJSM WITH RIG, MOVING AND CLEANING CREW, FINISH RIGGING DOWN FLOOR, STOMPERS AND BACK YARD. LOAD OUT DRILL PIPE, LOAD AND HAUL STOMPERS AND PIPE RACKS. LOAD OUT AND RIG UP TCB CAMP AND LOAD OUT CREW TRAILERS, SET SAME. HAUL DRILL COOL EQUIPMENT. SET FRAC TANKS FOR MUD FARM. MOVED CONNEX BOX'S, SHAKER SKID, CENTRIFUGE. PERFORM CAR WASH ON ALL EQUIPMENT LEAVING LOCATION. 31 LOADS HAULED. R/D VFD HOUSE, FESTOON, GENERATOR PACKAGE, REMOVE ROOF TOPS ON MUD TANKS & REMOVE SHAKER SKID F/SETLING PIT. SPLIT BACKYARD AND STAGE FOR CAR WASH. PIN MSRC'S TO SUBSTRUCTURE AND LOWER SAME, SUB SQUATTED AT 23:30. REMOVE CATWALK & BOP WRANGLER. PIN MSCR'S TO DERRICK AND LOWER SAME. DERRICK DOWN AT 24:00 9 HAUL TRUCKS, 4 CRANES, 2 FORKLIFTS, 1 TANDEM 80% RIGGED DOWN, 10% MOVED, 5% RIGGED UP
SIERRA H08 PR | 18 | 2022-01-26 | 2022-01-26 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 13.38 | 15122 | 15122 |  | MILESTONE_TURN OVER TO COMPLETION 01/26/2022 @ 00:00
SIERRA H08 PR | 18 | 2022-01-26 | 2022-01-26 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 13.38 | 15122 | 15122 |  | MILESTONE_RIG RELEASE 01/26/2021 @ 00:00
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 13:00 | 2021-11-26 14:30 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 108 | 108 | 0 | PREPARE TO WALK RIG F/TAHOE PINES H01 PR T/TAHOE MOUNTAIN H03 PR; SET MATS,/TAHOE PINES H01 PR T/TAHOE MOUNTAIN H03 PR; CENTER SUB OVER CONDUCTOR.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 13:00 | 2021-11-26 13:00 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 108 | 108 |  | MILESTONE_MOB/DEMOB 11/26/2021 @ 13:00
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 14:30 | 2021-11-26 15:30 | 1 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 108 | 108 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 15:30 | 2021-11-26 16:30 | 1 | P | MOBDMOB | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0 | 108 | 108 | 0 | REMOVE CASING BALES AND ELEVATORS, INSTALL RIG ELEVATORS, INSTALL CONDUCTOR RISER AND RIG UP CELLAR PUMPS.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 16:30 | 2021-11-26 17:30 | 1 | P | MOBDMOB | TRIP | PUBHA | PICK UP BIT / BHA | 0 | 108 | 108 | 0 | LATCH UP BHA, INSTALL MWD AND MAKE UP TOP MONEL. BHA: BIT 13-1/2" ULTERRA U616S W: 9/14 JETS TFA: 1.353, MOTOR 8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 11 JTS HWDP, TAG BOTTOM @ 108'.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 17:30 | 2021-11-26 17:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 108 | 108 |  | MILESTONE_SPUD WELL ON 11/26/2021 @ 17:30.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 17:30 | 2021-11-26 22:30 | 5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.21 | 108 | 1797 | 337.8 | ROTATE ( 1,689’ IN 4.95 HRS @ 351.71 FPH) WOB-25-35K, RPM-100, TRQ- 5K/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2100/2700 PSI, DIFF 300/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/ SOAP/ SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 30 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 22:30 | 2021-11-26 23:00 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.23 | 1797 | 1892 | 190 | SLIDE (95' IN .55 HRS @ 172.72 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2,100/2,600 PSI, DIFF-200/500 PSI. SLIDE DEPTHS: F/ 1,040' T/ 1,061' 20' TF-170M 2036-2041 F/ 1,309' T/ 1,334' 33' TF-175M 2117-2124 F/ 1,685' T/ 1,715' 30' TF-180M 2214-2232 F/ 1,872' T/ 1,892' 20' TF- HS 2248-2300
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 23:00 | 2021-11-26 23:45 | 0.75 | U | SFHL | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 0.26 | 1892 | 1892 | 0 | SHUT DOWN DUE TO EXCESSIVE AMOUNTS OF GUMBO, CIRCULATE AND WORK PIPE WHILE ROUSTABOUT CREW BREAKS GUMBO OFF FROM AROUND THE PIPE AND CATCHES UP IN CELLAR AREA
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-26 23:45 | 2021-11-27 02:15 | 2.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.36 | 1892 | 2835 | 377.2 | ROTATE ( 943’ IN 2.53 HRS @ 372.72 FPH) WOB-25-35K, RPM-100, TRQ- 5K/10K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2100/2700 PSI, DIFF-300/600 PSI. NOTE: DUMPING 100 BBLS EVERY +/- 300' AND PUMPING 30 BBL WATER/SOAP/SAPP SWEEPS EVERY +/- 300', PUMPING 100 BBL WATER/ SOAP/ SAPP SWEEPS EVERY 1,000'. NOTE: DRILL OUT OF SURFACE CONDUCTOR WITH 400 GPM AND 30 RPM; STAGE PUMPS UP 100 GPM PER STAND AND 10 RPM PER STAND UNTIL REACHING 900 GPM AND 100 RPM.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-27 02:15 | 2021-11-27 02:45 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.39 | 2835 | 2925 | 180 | SLIDE (90' IN .55 HRS @ 163.63 FPH) WOB-10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP-2100/2600 PSI, DIFF-200/500 PSI. SLIDE DEPTHS: F/ 1,996' T/ 1,996' 30' TF- 20R 2346-2354 F/ 2,061' T/ 2,091' 30' TF- 20R 0010-0020 F/ 2,341' T/ 2,371' 30' TF- 20R 0100-0115
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-27 02:45 | 2021-11-27 03:30 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.42 | 2925 | 2925 | 0 | PUMP 2-30 BBL SOAP AND SAP SWEEPS IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2,000 PSI.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-27 03:30 | 2021-11-27 04:45 | 1.25 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.47 | 2925 | 2925 | 0 | TRIP OUT OF HOLE F/2,925' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-27 04:45 | 2021-11-27 05:30 | 0.75 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.5 | 2925 | 2925 | 0 | RACK BACK 3 STANDS AND A DOUBLE HWDP, REMOVE MWD, RACK BACK MONELS, DRAIN MOTOR AND RACK BACK. NOTE: INSPECTED MOTOR AND BIT: MOTOR BEARING SLACK WAS MINIMAL AND PAD WEAR WAS MINIMAL, BIT GRADE: 0-0-NO-A-X-0-NO-TD.
TAHOE MOUNTAIN H03 PR | 1 | 2021-11-27 05:30 | 2021-11-27 06:00 | 0.5 |  | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.52 | 2925 | 2925 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 06:00 | 2021-11-27 06:30 | 0.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.54 | 2925 | 2925 | 0 | HOLD PJSM WITH CASING CREW, RIG UP FRANK'S CASING EQUIPMENT-BALES, ELEVATORS, TONGS, CRT, BOWL, AND SLIPS.
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 06:30 | 2021-11-27 09:45 | 3.25 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.68 | 2925 | 2925 | 0 | MAKE UP FLOAT SHOE, 2 JOINTS. 10 3/4" 45.5# J-55 BTC CASING, FLOAT COLLAR, 1 JOINT 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD). PICK AND RUN 10 3/4" 45.5# J-55 BT&C CASING T/2,913.9'. RAN 38 BOW SPRING CENTRALIZERS PLACED AS FOLLOWS: 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JOINT #2, AND THEN EVERY OTHER JT TO SURFACE, INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE, WASH DOWN AND LANDED ON CONDUCTOR, PICK UP 5' AND INSTALLED WELLHEAD VALVES AND PLUG, SLACK OFF AND LAND OUT ON BASE PLATE WITH 115K (W/O BLOCKS). SHOE- 2,903.5' TOP OF FLOAT COLLAR-
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 09:45 | 2021-11-27 10:30 | 0.75 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.71 | 2925 | 2925 | 0 | CIRCULATE 1.5 CASING CAPACITY WITH CRT WHILE RIGGING DOWN CASING TOOLS, INSTALL STREAMFLO VALVES AND TEST TO 5,000 PSI (GOOD TEST). GPM-337, SPP-160 PSI. NO LOSSES.
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 10:30 | 2021-11-27 11:00 | 0.5 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.73 | 2925 | 2925 | 0 | RIG DOWN CRT, L/D LANDING JOINT
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 11:00 | 2021-11-27 11:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 0.73 | 2925 | 2925 |  | MILESTONE_HOLD WELL OPERATIONS 1 ON 11/27/2021 @ 11:00
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 11:00 | 2021-11-27 13:30 | 2.5 | R | SFHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 0.73 | 2925 | 2925 | 0 | WALK RIG F/ TAHOE MOUNTAIN H03 PR T/ PRUEGNER H04 PR. INSTALL CELLAR COVERS, RIG UP STREAM FLO PUP JOINT, CEMENT HEAD AND CIRCULATING IRON, RIG UP CELLAR PUMPS FOR CEMENT JOB.
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 13:30 | 2021-11-27 16:00 | 2.5 | R | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 0.73 | 2925 | 2925 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 3,500 PSI & CEMENTED WITH: 40 BBL 8.3 PPG FRESH WATER SPACER, 314 BBLS 11.6 PPG LEAD CEMENT, 80 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 271 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/720 PSI PRESSURED UP T/1220 PSI (500 PSI OVER) @ 4.0 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 1.25 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 40 BBLS OF SPACER AND 211 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
TAHOE MOUNTAIN H03 PR | 2 | 2021-11-27 16:00 | 2021-11-27 17:30 | 1.5 | R | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 0.73 | 2925 | 2925 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 30 MIN. (PRESSURE HELD TEST WAS GOOD); RIG DOWN CEMENT HEAD AND CIRCULATING IRON, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 06:00 | 2021-12-13 06:00 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 0.73 | 2925 | 2925 |  | MILESTONE_RESUME WELL 1 ON 12/13/2021 @ 06:00
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 06:00 | 2021-12-13 07:00 | 1 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 0.77 | 2925 | 2925 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK RIG FROM PRUEGNER UNIT H04 PR TO TAHOE MOUNTAIN H03 PR, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 07:00 | 2021-12-13 08:00 | 1 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 0.81 | 2925 | 2925 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES, KILL LINE & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 08:00 | 2021-12-13 09:00 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 0.85 | 2925 | 2925 | 0 | INSTALL TEST PLUG, FILL BOP STACK W/WATER, TEST TOP RAMS, WELLHEAD CONNECTION, KILL LINE, AND KILL LINE CHECK VALVE T/250 PSI LOW / 5,000 PSI HIGH., TEST 2" MANUAL HCR ON STANDPIPE MANIFOLD T/250 PSI LOW / 5,000 PSI HIGH.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 09:00 | 2021-12-13 09:30 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 0.88 | 2925 | 2925 | 0 | INSTALL WEAR BUSHING, MOUSEHOLE, TRIP NIPPLE, CLOSE CASING VALVE AND COVER CELLAR.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 09:30 | 2021-12-13 10:30 | 1 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 0.92 | 2925 | 2925 | 0 | SERVICE RIG: REPLACE VALVE ON HYDRAULIC MANIFOLD ON FLOOR.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 10:30 | 2021-12-13 11:30 | 1 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 0.96 | 2925 | 2925 | 0 | PICK UP BHA #2. (9-7/8" ULTERRA SPL613 SN #: 55308, JETS 6/14'S & 3/16'S TFA: 1.49) BIT, 8", 7/8L, 5.9 STG @ 2.0° TS HPW-.014; .155 REV/GAL; 5.92' BIT TO BEND; 8.375" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-800 PSI; 8" NMPDC, 7-3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1-X/O 4-1/2 IF x 4-1/2 XH, 11- JTS 5" HWDP, 22 STDS OF 5'' DP, DSW AGITATOR. BIT TO SENSOR-64', GAMMA-60'. TEST MWD ( GOOD TEST).
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 11:30 | 2021-12-13 12:45 | 1.25 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.01 | 2925 | 2925 | 0 | TRIP IN HOLE F/BHA T/2,724'. PICK UP AGITATOR ON STAND 22: FILL PIPE, PSI BEFORE-650 PSI AFTER-820 @ 337 GPM, HOLE GIVING PROPER DISPLACEMENT.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 12:45 | 2021-12-13 13:15 | 0.5 | P | SFHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 1.03 | 2925 | 2925 | 0 | FLOW CHECK, NO FLOW. PULL TRIP NIPPLE AND INSTALL ROTATING HEAD
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 13:15 | 2021-12-13 13:45 | 0.5 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.05 | 2925 | 2935 | 20 | DRILL SHOE TRACK AND FLOAT EQUIPMENT, DRILL 10' NEW FORMATION F/2,925' T/2,935', GPM-450, SPP-1,375 PSI, DIFF-400, RPM-30, TQ-2/6K.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 13:45 | 2021-12-13 14:15 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.07 | 2935 | 2935 | 0 | CIRCULATE BOTTOMS UP AND RECIPROCATE PIPE, GPM-450, SPP-1,150 PSI, RPM-30. MUD WT IN/OUT=8.9 PPG.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 14:15 | 2021-12-13 14:30 | 0.25 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.08 | 2935 | 2935 | 0 | PERFORM F.I.T. WITH 8.9 PPG OBM, 406 PSI CSG PRESSURE FOR 11.6 PPG EMW, SHOE MD- 2,914' /TVD-2,894'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE. RESULTED IN GOOD TEST.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-13 14:30 | 2021-12-14 01:30 | 11 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.54 | 2935 | 7816 | 443.7 | ROT (4,881' IN 10.87 HRS @ 449.03 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4500/5200 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
TAHOE MOUNTAIN H03 PR | 3 | 2021-12-14 01:30 | 2021-12-14 06:00 | 4.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.73 | 7816 | 8078 | 58.2 | SLIDE (262' IN 4.63 HRS 56.58 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4500/5000 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/3,300'-T/3,312', 12', TF:90R, 15:25- 15:31 RPM: 0 F/3,393'-T/3,405', 12', TF:90R 15:40-15:44 RPM: 0 F/3,486'-T/3,494', 8', TF:30R, 15:52-16:00 RPM: 0 F/4,145'-T/4,157', 12', TF:90R, 17:02-17:12 RPM: 0 F/4,373'-T/4,383', 10', TF:HS, 17:30-17:38 RPM: 0 F/4,611'-T/4,622', 10', TF:30L, 18:03-18:10 RPM: 0 F/4,800'-T/4,815', 15', TF:HS, 18:34-18:43 RPM: 0 F/4,992'-T/5,007', 15', TF:HS, 19:05-19:13 RPM: 0 F/5,084', T/5,099', 15', TF:HS, 19:23-19:32 RPM: 0 F/6,113'-T/6,128', 15', TF:60R, 21:38-21:53 RPM: 0 F/6,393'-T/6,408', 15', TF:HS, 22:32-22:44 RPM: 0 F/6,487'-T/6,502', 15 , TF:HS, 22:57-23:10 RPM: 0 F/6,582'-T/6,597', 15', TF:HS, 23:24-23:50 RPM: 0 F/6,677'-T/6,692', 15', TF:HS, 00:06-00:28 RPM: 0 F/6,769'-T/6,784', 15', TF:HS, 00:43-01:14 RPM: 0 F/6,864'-T/6,879', 15',TF:HS, 01:29-01:52, RPM: 0 F/7,051'-T/7,066', 15', TF:HS, 02:24-02:52, RPM: 0 F/7,154'-T/7,160', 15', TF:HS, 03:04-03:24, RPM: 0 F/7,891'-T/7,911', 20', TF:160M, 05:11-05:30, RPM: 0
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-14 06:00 | 2021-12-14 08:00 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.81 | 8078 | 8903 | 412.5 | ROT (825' IN 2.10 HRS @ 392.85 FPH) WOB: 25/35K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, RPM-80, TRPM: 219, TRQ: 7K/17K, SPP: 4500/5200 PSI, DIFF: 300/800 PSI. NOTE: PUMPING 10 BBL HI-VIS SWEEPS EVERY +/-300' CONSISTING OF 1 PPB BENTONE 990.
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-14 08:00 | 2021-12-14 09:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 1.88 | 8903 | 8983 | 53.3 | SLIDE (80' IN 1.4 HRS 112 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 4500/5000 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/8,182'-T/8,202', 20', TF:120M, 06:13-06:33 RPM: 0 F/8,280'-T/8,300', 20', TF:150M, 06:48-07:06 RPM: 0 F/8,557'-T/8,577', 20', TF:150M, 07:44-08:05 RPM: 0 F/8,840'-T/8,860', 20', TF:100M, 08:42-09:07 RPM: 0
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-14 09:30 | 2021-12-14 11:30 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 1.96 | 8983 | 9512 | 264.5 | ROT (529' IN 2 HRS @ 265 FPH) WOB: 25/28K, SPM: 107/107, GPM: 686, MMRPM: 106.33, RPM-80,TRPM: 186.33, TRQ: 7K/17K, SPP: 3,165/3,615 PSI, DIFF: 400/450 PSI. NOTE: DRILLING ON 2 MPS DUE TO WASHED O-RING FLANGE ON #3 MP, 4'' VALVE.
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-14 11:30 | 2021-12-14 14:00 | 2.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.06 | 9512 | 9578 | 26.4 | BUILD CURVE-SLIDE (66' IN 2.47 HRS 26.72 PH) WOB: 10/20K, SPM: 107/107, GPM: 686, MMRPM: 106.33, SPP: 3600/3900 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/9,512'-T/9,578', 66', TF:350M, 11:30-13:58 RPM: 0 NOTE: DRILLING ON 2 MPS DUE TO WASHED O-RING FLANGE ON #3 MP, 4'' VALVE UNION. RESULT: CUT OFF BOTH THREAD HALF AND WING HALF AND REPLACE SAME VIA WELDER. WELDS WERE INSPECTED BY CERTIFIED INSPECTOR.
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-14 14:00 | 2021-12-14 14:30 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.08 | 9578 | 9578 | 0 | SERVICE RIG. LUBE: TD, ST-80 AND DRWKS. RIG MANAGER PRESENT
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-14 14:30 | 2021-12-15 01:00 | 10.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.52 | 9578 | 9838 | 24.8 | CONT. BUILD CURVE-SLIDE (260' IN 10.5 HRS 24.76 PH) WOB: 10/20K, SPM: 107/107, GPM: 686, MMRPM: 106.33, SPP: 3,400/3,650 PSI, DIFF: 100/400 PSI. SLIDE DEPTHS: F/9665'-T/9838', 173', TF:130M, 18:00:01:00, RPM: 30, TQ:5 R/2L NOTE: DRILLING ON 2 MPS DUE TO WASHED O-RING FLANGE ON #3 MP, 4'' VALVE UNION. RESULT: CUT OFF BOTH THREAD HALF AND WING HALF AND REPLACE SAME VIA WELDER. WELDS WERE INSPECTED BY CERTIFIED INSPECTOR. ONCE IRON HAD COOLED DOWN ENOUGH, INSTALLED NEW O-RING GASKET AND MADE UNION CONNECTION UP.
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-15 01:00 | 2021-12-15 05:00 | 4 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.69 | 9838 | 9975 | 34.2 | CONT. BUILD CURVE-SLIDE (137' IN 4.0 HRS 34.25 PH) WOB: 10/20K, SPM: 94/94/94, GPM: 900, MMRPM: 139.5, SPP: 5,050 PSI, DIFF: 100/350 PSI. SLIDE DEPTHS: F/9,838'-T/9,975', 137', TF:HS, 01:00-05:00 RPM: 30, TQ:5R/2L
TAHOE MOUNTAIN H03 PR | 4 | 2021-12-15 05:00 | 2021-12-15 06:00 | 1 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.73 | 9975 | 9998 | 23 | CONT. BUILD CURVE-SLIDE (23' IN 1.0 HRS 23 FPH) WOB: 10/20K, SPM: 107/107, GPM: 686, MMRPM: 106.33, SPP: 3,400/3,670 PSI, DIFF: 100/250 PSI. SLIDE DEPTHS: F/9,975'-T/9,998', 23', TF:HS, 05:00-06:00, RPM: 30, TQ:5 R/3L NOTE: DRILLING ON 2 MPS DUE TO SWAB ON #1 MP/#2 POD
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 06:00 | 2021-12-15 07:30 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.79 | 9998 | 10032 | 22.7 | SLIDE (34’ IN 1.5 HRS @ 22.66 FPH) WOB: 10/20K, SPM: 90/90/90, GPM: 850, MMRPM: 127, SPP: 4950/5150 PSI, DIFF: 100/200 PSI. SLIDE DEPTHS: SLD F/9,998' T/10,032' 20' TF-30L 0600-0730, RPM: 30 7R/3L
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 07:30 | 2021-12-15 09:15 | 1.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 2.86 | 10032 | 10032 | 0 | PERFORM POST TD CLEAN UP CYCLE PUMPING 2-40 BBL HI-VIS SWEEPS SURFACE TO SURFACE TO CLEAN HOLE AND PREP OPEN HOLE FOR 7.625" CASING. SPM: 90/90/90, GPM: 850, SPP:4950 PSI, RPM: 30, TQ: 6-10K. SHAKERS CLEAN; PERFORM FLOW CHECK (NO FLOW), PUMP SLUG
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 09:15 | 2021-12-15 11:15 | 2 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 2.95 | 10032 | 10032 | 0 | POOH W/BHA #2 F/10,032'-T/2,904'. HOLE TAKING PROPER FILL VIA TRIP TANK, NO EXCESSIVE OVERPULL. NOTE: FLOW CHECK WAS CONDUCTED @ SHOE (2,914') RESULT: NO FLOW
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 11:15 | 2021-12-15 12:00 | 0.75 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 2.98 | 10032 | 10032 | 0 | REMOVE RT-HEAD AND INSTALL TRIP NIPPLE. L/D AGITATOR @ 2,724'
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 12:00 | 2021-12-15 12:45 | 0.75 | P | INTHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 3.01 | 10032 | 10032 | 0 | POOH W/BHA #2 F/2,904'-T/BHA'. HOLE TAKING PROPER FILL VIA TRIP TANK, NO EXCESSIVE OVERPULL
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 12:45 | 2021-12-15 14:15 | 1.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.07 | 10032 | 10032 | 0 | RACK BACK HWDP & 2 STDS-6.5'' DC, REMOVE MWD TOOL. DRAIN MOTOR AND BREAK OUT BIT. MOTOR: DRAINED WELL WITH MINIMAL SLACK. BIT: 1-1-BT-S-X-1-ER-TD NOTE: FLOW CHECK PRIOR TO BHA ENTERING BOP. RESULT: WELL STATIC. NOTE: L/D DIRTY MOTOR AND P/U NEW MOTOR IN PREPERATION FOR THE NEXT WELL.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 14:15 | 2021-12-15 14:45 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.09 | 10032 | 10032 | 0 | CLEAN RIG FLOOR AND REMOVE WEAR BUSHING
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 14:45 | 2021-12-15 15:45 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 3.14 | 10032 | 10032 | 0 | SERVICE TOP DRIVE, ST-80, AND DRAWORKS
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 15:45 | 2021-12-15 17:00 | 1.25 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 3.19 | 10032 | 10032 | 0 | CHANGE OUT TOP VBR'S TO 7.625'' CSG RAMS. PICK UP JT OF DRILL PIPE AND PRESSURE TEST BONNET SEALS T/1,000 PSI. RESULT: GOOD TEST.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 17:00 | 2021-12-15 18:45 | 1.75 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.26 | 10032 | 10032 | 0 | HOLD PJSM WITH ALL INVOLDED PERSONELL. R/U FRANKS CSG CREW TOOLS AND EQUIPMENT.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-15 18:45 | 2021-12-16 02:00 | 7.25 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.56 | 10032 | 10032 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN 7.625" 29.7# P-110 IC BTC INTERMEDIATE CASING T/9,606', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT. NOTE: TAKING RETURNS VIA TRIP TANK.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-16 02:00 | 2021-12-16 02:30 | 0.5 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 3.58 | 10032 | 10032 | 0 | REPAIR CHAIN ON CATWALK SKATE.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-16 02:30 | 2021-12-16 03:00 | 0.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 3.6 | 10032 | 10032 | 0 | MAKE UP SHOE TRACK, TEST FLOATS, RUN INTERMEDIATE CASING F/9,606'-T/10,022', FILL PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT. RUN 7.625" INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7.625" 29.7# P-110 IC BTC CSG, 1-INNOVEX FLOAT COLLAR. THEN RAN 222 JTS OF 7.625" 29.7# P-110 IC BTC CSG,1-10' PUP JT & 2-JTS OF 7.625" 29.7# P-110 IC BTC CSG, TOTAL OF 227 JOINTS RAN. INSTALLED 3 SOLID BODY CENTRALIZERS ON FIRST 3 JOINTS (ONE 10' ABOVE FS, JTS 2 & 3 FREE FLOATING), AND INSTALL 43 LATCH ON BOW SPRING CENTRALIZERS @ 9,714.6' AND EVERY 4TH JT UP TO 2,336.7'. P/U LANDING JOINT, WASH DOWN AND LAND CSG ON CSG MANDREL W/200K (W/O BLOCKS) FLOAT SHOE- 10022.0' TOP OF FLOAT COLLAR-9,930.4'. 10 FULL JOINTS LEFT OUT- 443.3', 1-15' PUP JT LEFT OUT-14.83'
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-16 03:00 | 2021-12-16 03:30 | 0.5 | P | INTHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 3.63 | 10032 | 10032 | 0 | RIG DOWN FRANKS CSG CRT, R/U CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD. RIG MANAGER PRESENT.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-16 03:30 | 2021-12-16 05:30 | 2 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 3.71 | 10032 | 10032 | 0 | CIRCULATE CSG 1.5X CAPACITY W/RIG PUMPS THROUGH CEMENT HEAD WHILE RIGGING DOWN CASING TOOLS. SPM: 105, BPM: 8, SPP:767, NO LOSSES. NOTE: HOLD PJSM WITH ALL INVOLVED PERSONELL, IN REGARDS TO CMT OPS.
TAHOE MOUNTAIN H03 PR | 5 | 2021-12-16 05:30 | 2021-12-16 06:00 | 0.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.73 | 10032 | 10032 | 0 | SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/3,500 PSI, AND BEGIN CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.5 PPG SPACER @ 5BPM, 302 BBL 11.8 PPG 875 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT @ 6BPM. GOOD RETURNS. NOTE: COMPLETE JOB DESCRIPTION ON THE FOLLOWING REPORT.
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 06:00 | 2021-12-16 09:00 | 3 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 3.85 | 10032 | 10032 | 0 | CONT. INTERMEDIATE CEMENTING OPS. CEMENT JOB AS FOLLOWS: SWAP CIRCULATING LINE T/ CEMENT STANDPIPE, TEST LINES T/3,500 PSI, CEMENT INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 50 BBL 10.5 PPG SPACER. 302 BBLS 11.8 PPG 875 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-BZ LEAD CEMENT, 80 BBL 16.2 PPG 310 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, COMPANY REP WITNESS PLUG DROP, DISPLACE WITH 456 BBLS OF 9.7 PPG OIL BASE MUD. FINAL LIFT PRESSURE WAS 1,500 PSI AT 3.5 BPM, BUMP PLUG AND INCREASE PSI 500 OVER T/2,000 PSI. HELD PRESS. FOR 5 MIN. BLED BACK 4.00 BBLS FLOATS HELD. PLUG BUMPED @ 08:18 HRS. CEMENT W/ FULL RETURNS WHILE PUMPING CEMENT. 36 BBLS OF SPACER & 0 BBLS CMT TO SURFACE. CALCULATED TOC @ 255'
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 09:00 | 2021-12-16 09:30 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 3.88 | 10032 | 10032 | 0 | TEST CASING T/3,500 PSI FOR 30 MINUTES WITH CEMENT TRUCK. TEST GOOD. BLED BACK 8 BBLS.
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 09:30 | 2021-12-16 11:30 | 2 | P | INTHLCSG | WAIT | WOTR | WAIT ON OTHER | 3.96 | 10032 | 10032 | 0 | ONCE CSG TEST WAS COMPLETED, HALT OPERATIONS AS PER OFFICE MANAGMENT TO CONDUCT RIG TOUR.
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 11:30 | 2021-12-16 12:00 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 3.98 | 10032 | 10032 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON.
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 12:00 | 2021-12-16 12:45 | 0.75 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.01 | 10032 | 10032 | 0 | BREAK OUT AND LAY DOWN LANDING JOINT, FLUSH THROUGH BOP'S AND FLOW LINE, RIG DOWN CASING BALES AND ELEVATORS. MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK & WELLHEAD, WASHED OUT & FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL & LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF & INSTALLED SAME, TESTED PACK-OFF TO 5K PSI, PULL TESTED PACK-OFF TO 25K, BROKE OUT & LAID DOWN SETTING TOOL.
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 12:45 | 2021-12-16 13:45 | 1 | P | INTHLCSG | BOP | SVCBOP | SERVICE BOP | 4.05 | 10032 | 10032 | 0 | REMOVE 7 5/8" CSG RAMS AND INSTALL VARIABLE RAMS
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 13:45 | 2021-12-16 15:00 | 1.25 | P | INTHLCSG | BOP | ND | NIPPLE DOWN BOP | 4.1 | 10032 | 10032 | 0 | NIPPLE DOWN BOP'S, INSTALL WEATHER CAP AND SECURE WELL, CLOSE CASING VALVE. NOTE: REMOVE 7.625'' CSG RAMS AND INSTALL VBRS
TAHOE MOUNTAIN H03 PR | 6 | 2021-12-16 15:00 | 2021-12-16 15:00 | 0 | P | INTHLCSG | MSTN | HOLD2 | MILESTONE_HOLD WELL OPERATIONS 2 | 4.1 | 10032 | 10032 |  | MILESTONE_HOLD WELL OPERATIONS 2 ON 12-16 -2021 @ 15:00
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-27 20:00 | 2021-12-27 21:30 | 1.5 | P | INTHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 4.17 | 10032 | 10032 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, PULL CELLAR COVER, WALK FROM TAHOE PINES H01 PR TO TAHOE MOUNTAIN H03 PR, CENTERED AND LEVELED SUB OVER WELLHEAD, CONFIRMED BY MAGNOLIA COMPANY MAN.
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-27 20:00 | 2021-12-27 20:00 | 0 | P | INTHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 4.1 | 10032 | 10032 |  | MILESTONE_RESUME WELL 1 ON 12/27/2021 @ 20:00
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-27 21:30 | 2021-12-27 22:30 | 1 | P | INTHLCSG | BOP | NU | NIPPLE UP BOP | 4.21 | 10032 | 10032 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP & SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, INSTALLED TURNBUCKLES & FLOWLINE, UNLATCHED BOP WRANGLER FROM BOP'S & LAY OVER SAME.
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-27 22:30 | 2021-12-28 00:30 | 2 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 4.29 | 10032 | 10032 | 0 | INSTALL TEST PLUG AND TEST BOP'S: TEST STAND PIPE BACK TO THE PUMPS TO 250 PSI LOW / 6,500 PSI HIGH, TIW AND INSIDE GREY TO 250 PSI LOW / 10,000 PSI HIGH, TEST ANNULAR W/4 1/2" DP AND 5 1/2" DP 250 PSI LOW / 3,500 PSI HIGH, TEST 4 1/2" AND 5 1/2" DP IN UPPER PIPE RAMS, TEST MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE, MANUAL VALVE AND HCR, TEST 4 1/2" AND 5 1/2" DP IN LOWER PIPE RAMS TO 250 PSI LOW / 10,000 PSI HIGH, TEST KILL LINE BACK TO MUD PUMPS 250 PSI LOW / 6,500 PSI HIGH, TEST CHOKE MANIFOLD MANUAL VALVES,SUPERCHOKES TO 250 PSI LOW / 10,000 PSI HIGH OFF LINE. INSTALL WEATHERFORD ROTATING HEAD TEST CAP, TEST ROTATING HEAD, SPACER SPOOL & ORBIT VALVE 250 PSI LOW / 1,500 PSI HIGH. CASING VALVE VERIFIED OPEN DURING TEST AND CLOSED AFTER TEST. NOTE: REBUILT 2" KILL LINE MUD VALVE ON #2 MUD PUMP, TESTED GOOD AFTERWARD. STRAP AND STAGE BHA.
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-28 00:30 | 2021-12-28 01:00 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 4.31 | 10032 | 10032 | 0 | RIG DOWN TESTERS, PULL TEST PLUG
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-28 01:00 | 2021-12-28 02:00 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 4.35 | 10032 | 10032 | 0 | INSTALL MOUSE HOLE, INSTALL WEAR BUSHING, TRIP NIPPLE, CLOSE CASING VALVE, CHECK VALVE ALLIGNMENT ON CHOKE AND BOP'S
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-28 02:00 | 2021-12-28 02:30 | 0.5 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.38 | 10032 | 10032 | 0 | SERVICE RIG, TOP DRIVE, AND DRAW WORKS
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-28 02:30 | 2021-12-28 05:00 | 2.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 4.48 | 10032 | 10032 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13645346 JETS 6X18 TFA: 1.49), 5.25", 6/7, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.05' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,170 PSI; STALL TRQ-7382 FT/LBS; BTI VALVE, 5" NMPDC, 5 1/4" UBHO, 5" NMDC, 5" NMPDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP,AGITATOR, BIT TO SVY-65'. BIT TO GAMMA-56'. TEST MWD, MWD DID NOT SHOW TOOL FACE , RESET SEQUENCE AND RE-TEST SAME. (TEST GOOD)
TAHOE MOUNTAIN H03 PR | 7 | 2021-12-28 05:00 | 2021-12-28 06:00 | 1 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.52 | 10032 | 10032 | 0 | TRIP IN THE HOLE F/BHA T/ 1,500', PROPER DISPLACEMENT TO TRIP TANK.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 06:00 | 2021-12-28 06:45 | 0.75 | P | INTHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 4.55 | 10032 | 10032 | 0 | CONTINUE TRIPPING IN THE HOLE F/1,500' T/2,759', PROPER DISPLACEMENT TO TRIP TANK.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 06:45 | 2021-12-28 07:45 | 1 | U | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 4.59 | 10032 | 10032 | 0 | SERVICE RIG, TOP DRIVE, AND DRAW WORKS NOTE: ATTEMPT TO SCREW IN AND FILL PIPE. TOP DRIVE NOT WORKING CORRECTLY.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 07:45 | 2021-12-28 15:30 | 7.75 | U | INTHLCSG | SPROB | RGEQP | RIG EQUIPMENT FAILURE | 4.92 | 10032 | 10032 | 0 | TOP DRIVE WORKING ERATICALLY FORWARD AND REVERSE AT 90 RPM'S. INSPECTED AND CLEANED ALL 19 PIN AND 42 PIN PLUGS ON TOP DRIVE, INSPECTED ALL POWER CABLES AND GROUNDS FROM THE VFD TO THE TOP DRIVE WHILE WAITING ON PATTERSON ELECTRICIAN, TROUBLE SHOOT ISSUE WITH ELECTRICIAN, OBSERVED THAT THE SHIELDING WIRE ON ENCODER CABLE WAS MISSING, REPLACED SHIELDING WIRE AND TIGHTEN UP CONNECTION.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 15:30 | 2021-12-28 19:30 | 4 | P | INTHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 5.08 | 10032 | 10032 | 0 | FILLED PIPE AND FLOW TESTED DRILL STRING, PICKED UP AGITATOR ON STAND 28 AND FLOW TESTED. SPP BEFORE-1165 PSI SPP AFTER- 1405 PSI @ 262 GPM, TRIP IN THE HOLE WITH BHA #3 F/2,759' T/9.915', FILL PIPE EVERY 40 STANDS, PROPER DISPLACEMENT TO TRIP TANK.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 19:30 | 2021-12-28 20:00 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 5.1 | 10032 | 10032 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 20:00 | 2021-12-28 20:15 | 0.25 | P | INTHLCSG | WSHRM | PRERM | PRECAUTIONARY WASH AND REAM | 5.11 | 10032 | 10032 | 0 | WASH/REAM F/9,915' T/9,930', TAGGED FLOAT COLLAR @ 9,930', VERIFY CHOKE VALVE ALIGNMENT, PUMP THROUGH GAS SEPERATOR PRIOR TO DRILL OUT. PERFORM BOP DRILL, RESPONSE TIME= 22 SECONDS
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 20:15 | 2021-12-28 21:00 | 0.75 | P | INTHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 5.15 | 10032 | 10032 | 0 | DRILL SHOE TRACK AND 10' NEW FORMATION F/10,032' T/10,042', WOB-5/10K, RPM-30, GPM-300, SPP-2400/2550 PSI, DIFF-50/100 PSI, RPM-30, TQ-4/6K.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 21:00 | 2021-12-28 21:45 | 0.75 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.18 | 10042 | 10042 | 0 | CIRCULATE BOTTOMS UP FOR F.I.T., GPM-350, SPP-2300 PSI, RPM-30, MUD WT IN 9.2 PPG, MUD WT OUT 9.2 PPG.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 21:45 | 2021-12-28 22:00 | 0.25 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 5.19 | 10042 | 10042 | 0 | PERFORM F.I.T. WITH 9.2 PPG OBM, 1970 PSI CSG PRESSURE FOR 13.0 PPG EMW, SHOE MD-10,022' / TVD-9,894'. CASING PRESSURE WAS RECORDED FROM CASING GAUGE.
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 22:00 | 2021-12-29 03:00 | 5 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.4 | 10042 | 10480 | 87.6 | BUILD CURVE-SLIDE (438' IN 5.13 HR @ 85.32 FPH) WOB-30/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3400/3800 PSI, DIFF-0200/0400 PSI, CHOKES- 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP=0 PSI. SLIDE DEPTHS: SLD F/10042 T/10136 94' TF-30L 2210-2315 RPM-30 TQ-2.5R/1.0L SLD F/10136 T/10231 95' TF-45L 2316-0010 RPM-30 TQ-2.5R/1.0L SLD F/10231 T/10243 13' TF- HS 0015-0032 RPM-30 TQ-2.5R/1.0L SLD F/10296 T/10324 28' TF- HS 0102-0143 RPM-30 TQ-2.5R/1L SLD F/10324 T/10378' 20' TF- HS 0140-0220 RPM-30 TQ-2.5R/1.0L SLD F/10421 T/10482 61' TF- HS 0250-0327 RPM-30 TQ-2.5R/1.0L SLD F/10510 T/10604 96' TF- HS 0344-0435 RPM-30 TQ-2.5R/1.0L
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-28 22:00 | 2021-12-28 22:00 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 5.19 | 10042 | 10042 |  | MILESTONE_START CURVE SECTION 12-28-2021 @ 22:00
TAHOE MOUNTAIN H03 PR | 8 | 2021-12-29 03:00 | 2021-12-29 06:00 | 3 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.52 | 10480 | 10732 | 84 | BUILD CURVE-ROT (262' IN 2.87 HR @ 91.40 FPH) WOB-20/25K, SPM-76/76, GPM-400, MRPM-272, RPM-30, TTLRPM-302, SPP-3400/4000 PSI, DIFF-200/600 PSI, CHOKES- 100% /100%, FLARE-0', NO MUD CUT, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI, AVG SICP=0 PSI. NOTE: WINDOW CHANGE RECEIVED VIA EMAIL @ 01:03AM HOURS, DEPTH WHEN RECEIVED: 10,227', NEW TARGET: 10342’ TVD AT 0 VS WITH 92.8 DEG INC 5’ ABOVE/ 5’ BELOW, 50’ LEFT / 50’ RIGHT
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 06:00 | 2021-12-29 06:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 5.52 | 10732 | 10732 |  | MILESTONE_LAND/END CURVE SECTION ON 12/29/2021 @ 06:00
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 06:00 | 2021-12-29 06:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 5.52 | 10732 | 10732 |  | MILESTONE_START LATERAL SECTION ON 12/29/2021 @ 06:00
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 06:00 | 2021-12-29 08:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.6 | 10732 | 10936 | 102 | ROTATE DRILL LATERAL (204' IN 2.05 HR @ 99.51 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM 40- 80, TQ 8K/10K, MRPM-272, TTRPM-352, SPP- 3500/4,550 PSI, DIFF- 800/1000 PSI, CHOKES- 0% /35- 100%, FLARE-20-30', NO MUD CUT, MAX CASING PRESSURE= 1225 PSI, AVG CASING PRESSURE= 600 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI. NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY +/-300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT.
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 08:00 | 2021-12-29 08:30 | 0.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.63 | 10936 | 10956 | 40 | SLD DRILL LATERAL (20' IN .45 HRS @ 44.44 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -3500/,3950 PSI, DIFF-300/450 PSI, CHOKES- 0% /35- 100%, FLARE-20-30', NO MUD CUT, MAX CASING PRESSURE= 1225 PSI, AVG CASING PRESSURE= 600 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 0 PSI. SLIDE DEPTHS: F/10890'-T/10910', 20', TF:20L, 07:43-8:10, RPM:40, TQ: 3R/2L
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 08:30 | 2021-12-29 10:30 | 2 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.71 | 10956 | 10956 | 0 | PULLED OFF BOTTOM, SPACED OUT AND CLOSED TOP VBR'S DUE TO CASING PRESSURE INCREASING TO 1241 PSI, CIRCULATE OUT GAS AND WEIGHT UP F/9.0 PPG T/9.2 PPG, SPM-76/76, GPM-400, SPP- 4300 PSI, CHOKES- 0% /25-35%, FLARE-20-30', NO MUD CUT, MAX CASING PRESSURE= 1879 PSI, AVG CASING PRESSURE= 1200 PSI. CASING PRESSURE DECREASED T/900 PSI AFTER 2 FULL CIRCULATIONS, OPEN TOP VBR'S AND STARTED BACK DRILLING, DECISION WAS MADE TO WEIGHT UP F/9.2 PPG T/9.4 PPG.
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 10:30 | 2021-12-29 10:45 | 0.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.72 | 10956 | 10983 | 108 | ROTATE DRILL LATERAL (27' IN .25 HR @ 108 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM 80, TQ 8K/10K, MRPM-272, TTRPM-352, SPP- 4250/5000 PSI, DIFF- 600/750 PSI, CHOKES- 0% /30- 35%, FLARE-15-20', NO MUD CUT, MAX CASING PRESSURE= 1264 PSI, AVG CASING PRESSURE= 900 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1465 PSI. CLOSING TOP VBR'S ON CONNECTIONS NOTE: WEIGHTING UP F/9.2PPG T/9.4 PPG WHILE DRILLING
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 10:45 | 2021-12-29 11:30 | 0.75 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.75 | 10983 | 10983 | 0 | PULLED OFF BOTTOM, SPACED OUT AND CLOSED TOP VBR'S DUE TO CASING PRESSURE INCREASING TO 1264 PSI CIRCULATE OUT GAS AND CONTINUE WEIGHTING UP F/9.2 PPG T/9.4 PPG, SPM-76/76, GPM-400, SPP- 4300 PSI, CHOKES- 0% /25-35%, FLARE-15-20', NO MUD CUT, MAX CASING PRESSURE= 1512 PSI, AVG CASING PRESSURE= 1100 PSI. CASING PRESSURE DECREASED T/820 PSI AFTER 1 FULL CIRCULATIONS, OPEN TOP VBR'S AND STARTED BACK DRILLING.
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 11:30 | 2021-12-29 14:15 | 2.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 5.86 | 10983 | 11388 | 147.3 | ROTATE DRILL LATERAL (405' IN 3.12 HR @ 129.81 FPH) WOB-25/35K, SPM-76/76, GPM-400, RPM 80, TQ- 7K/9K, MRPM-272, TTRPM-352, SPP- 4300/5250 PSI, DIFF- 750/950 PSI, CHOKES- 0% /28- 34%, FLARE-15'-20', NO MUD CUT, MAX CASING PRESSURE= 1280 PSI, AVG CASING PRESSURE= 900 PSI, SHUTTING IN ON CONNECTIONS, MAX SICP= 1350 PSI. AVG SICP= 1200 PSI, WEIGHT UP F/9.4 PPG T/9.6 PPG NOTE: PUMPING 10 BBL 12.5 PPB LCM SWEEP EVERY 300' CONSISTING OF ACTIVE MUD, 2.5 PPB MAGNA FIBER, 5 PPB NEWCARB & 5 PPB NEW FAULT. WINDOW CHANGE RECEIVED VIA TEXT @ 12:55 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 11,121', NEW WINDOW: 10' ABOVE / 0' BELOW. TARGET CHANGE RECEIVED VIA TEXT @ 4:34 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 11,329', NEW TARGET: 10,334' TVD (0' VS) AT 92,5 DEG, WINDOW 5' ABOVE / 5' BELOW. WINDOW CHANGE RECEIVED VIA TEXT @ 16:32 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 11,493', NEW WINDOW: 0' ABOVE / 10' BELOW
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 14:15 | 2021-12-29 16:00 | 1.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 5.94 | 11388 | 11493 | 60 | SLD DRILL LATERAL (105' IN 1.67 HRS @ 62.87 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP -4300/4500 PSI, DIFF-100/200 PSI, CHOKES- 0% /28- 34%, FLARE-15'-20', NO MUD CUT, MAX CASING PRESSURE= 1280 PSI, AVG CASING PRESSURE= 900 PSI, WEIGHT UP F/9.4 PPG T/9.6 PPG NOTE: SPP DECREASED F/4300 PSI OFF BOTTOM T/4040 PSI @ 11,456' AND SPP DECREASED F/4040 PSI OFF BOTTOM T/3800 PSI @ 11,469' LOSS A TOTAL OF 70 BBLS TO THE FORMATION WHILE DRILLING AHEAD. SLIDE DEPTHS: SLD F/10983 T/11035 52' TF-HS 1130-1203 RPM-40 TQ-3R/2L SLD F/11118 T/11143 25' TF-HS 1247-1314 RPM-50 TQ-4R/3L SLD F/11281 T/11291 10' TF-20R 1402-1422 RPM-50 TQ-3R/2L SLD F/11470 T/11488 18' TF-70R 1540-1600 RPM-50 TQ-4R/3L
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 16:00 | 2021-12-29 16:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 5.96 | 11493 | 11493 | 0 | PULLED OFF BOTTOM, SPACED OUT AND CLOSED TOP VBR'S DUE TO CASING PRESSURE INCREASING TO 1280 PSI, ATTEMPTED CIRCULATE OUT GAS, SPM-76/76, GPM-400, SPP- 4300 PSI, CHOKES- 0% /24-33%, FLARE-30-40', NO MUD CUT, MAX CASING PRESSURE= 1823 PSI, AVG CASING PRESSURE= 1400 PSI. STARTED ENCOUNTERING LOSSES @ 200 BPH AND SPP DECREASED F/3800 PSI OFF BOTTOM T/3530 PSI WITH CHOKES- 0% /24%, UNABLE TO CIRCULATE OUT GAS AND COULD NOT DECREASE CASING PRESSURE NO LOWER THAN 1340 PSI. DECISION WAS MADE TO GO ON A MUD CAP. LOSS A TOTAL OF 104 BBLS TO THE FORMATION WHILE ATTEMPTING TO CIRCULATE OUT GAS..
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 16:30 | 2021-12-29 19:15 | 2.75 | P | PRDHLLT | WCTRL | KWELL | KILL WELL | 6.07 | 11493 | 11493 | 0 | LINE UP TO FLUSH ANNULUS WITH 9.6 PPG OBM VIA KILL-LINE, FLUSHED ANNULUS WITH 170 BBLS OF 9.6 PPG WHILE SLOWLY STAGING UP PUMP RATE F/26 GPM T/183 GPM AND BUILDING 17.5 PPG KILL MUD, INITIAL CASING PRESSURE= 1338 PSI @ 26 GPM AND FINAL CASING PRESSURE= 1281 PSI @ 183 GPM, BULLHEADED 116 BBLS OF 17.5 PPG OBM DOWN BACKSIDE VIA KILL-LINE WHILE SLOWLY STAGING UP PUMP RATE F/183 GPM T/262 GPM,, INITIAL KILL LINE SPP: 1462 PSI AND INITIAL CASING PRESSURE= 1281 PSI, FINAL KILL LINE SPP: 507 PSI AND FINAL CASING PRESSURE= 0 PSI, CREATE MUDCAP. DISPLACE DRILL PIPE CAPACITY WITH FRESHWATER.
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-29 19:15 | 2021-12-30 01:00 | 5.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.31 | 11493 | 12513 | 177.4 | ROTATE DRILL LATERAL (1020' IN 5.85 HR @ 169.05 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-10K/15K, MRPM-272, TTRPM-352, SPP- 4500/5000 PSI, DIFF- 450/650 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: TARGET CHANGE RECEIVED VIA EMAIL @ 10:10 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 11,741', NEW TARGET: 10,350' TVD (0' VS) AT 92.7 DEG INC., WINDOW 5' ABOVE / 5' BELOW. NOTE: TARGET CHANGE RECEIVED VIA EMAIL @ 04:27 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 12,494', NEW TARGET: 10,345' TVD (0' VS) AT 92.9 DEG INC., WINDOW 5' ABOVE / 5' BELOW.
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-30 01:00 | 2021-12-30 05:30 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.5 | 12513 | 12715 | 44.9 | SLD DRILL LATERAL (202' IN 4.4 HRS 45.9 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4500/5300 PSI, DIFF- 200/400 PSI, CHOKES-0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE=0 PSI, MAX SICP=0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/11565 T/11583 20' TF-65R 1944-2056 RPM-50 TQ-4.2R/2.3L SLD F/11652 T/11670 18' TF-180 2034-2050 RPM-50 TQ-4.2R/2.3L SLD F/11751 T/11766 15' TF-130R 2125-2146 RPM-60 TQ-4.2R/2.3L SLD F/11845 T/11865 20' TF-135R 2216-2240 RPM-60 TQ-4.3R/4L SLD F/12034 T/12054 20' TF-110R 2331-0000 RPM-60 TQ-4.3R/4L SLD F/12127 T/12152 25' TF-125R 0026-0102 RPM-80 TQ-5.2R/3.6L SLD F/12217 T/12247 30' TF-90R 0125-0203 RPM-80 TQ-5.2R/3.6L SLD F/12310 T/12324 14' TF-20R 0227-0240 RPM-80 TQ-5.2R/3.6L SLD F/12410 T/12422 12' TF- HS 0317-0330 RPM-80 TQ-5.2R/3.6L SLD F/12594 T/12622 28' TF- 60R 0433-0515 RPM-80 TQ-4.9R/3.6L
TAHOE MOUNTAIN H03 PR | 9 | 2021-12-30 05:30 | 2021-12-30 06:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.52 | 12715 | 12715 | 0 | SERVICE RIG AND TOP DRIVE UNIT
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 06:00 | 2021-12-30 12:30 | 6.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.79 | 12715 | 13780 | 163.8 | ROTATE DRILL LATERAL (1065' IN 6.45 HRS @ 165.12 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-13K/17K, MRPM-272, TTRPM-352, SPP- 4550/5550 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 283 PSI, AVG CASING PRESSURE= 230 PSI, MAX SICP= 233 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 06:42 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 12,803', NEW TARGET: 10,337' TVD (0' VS) AT 92.9 DEG INC., WINDOW 5' ABOVE / 5' BELOW. WINDOW CHANGE RECEIVED VIA TEXT @ 09:50 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 13,128', NEW WINDOW: 0' ABOVE / 10' BELOW. TARGET CHANGE RECEIVED VIA TEXT @ 14:34 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 13,648', NEW TARGET: 10,344' TVD (0' VS) AT 92.7 DEG INC., WINDOW 0' ABOVE / 10' BELOW.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 12:30 | 2021-12-30 16:30 | 4 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.96 | 13780 | 13915 | 33.8 | SLD DRILL LATERAL (135' IN 4.05 HRS 33.33 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4550/4950 PSI, DIFF- 200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 283 PSI, AVG CASING PRESSURE= 230 PSI, MAX SICP= 233 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/12791 T/12808 17' TF-135R 0618-0649 RPM-70 TQ-5R/4L SLD F/12885 T/12903 18' TF-150R 0719-0756 RPM-70 TQ-7R/6L SLD F/12980 T/13000 20' TF-150R 0826-0854 RPM-75 TQ-7R/6L SLD F/13128 T/13143 15' TF-180 0950-1018 RPM-80 TQ-8R/6L SLD F/13168 T/13188 20' TF-180 1035-1106 RPM-80 TQ-8R/5L SLD F/13404 T/13419 15' TF-HS 1212-1244 RPM-80 TQ-9R/7L SLD F/13456 T/13466 10' TF-HS 1307-1328 RPM-75 TQ-7R/6L SLD F/13645 T/13665 20' TF-180 1425-1500 RPM-80 TQ-10R/9L
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 16:30 | 2021-12-30 17:00 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.98 | 13915 | 13915 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 17:00 | 2021-12-30 20:15 | 3.25 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.11 | 13915 | 14385 | 144.6 | ROTATE DRILL LATERAL (469' IN 3.32 HRS @ 141.26 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-13K/17K, MRPM-272, TTRPM-352, SPP- 4600/5400 PSI, DIFF- 600/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 361 PSI, AVG CASING PRESSURE= 200 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 22:02 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 14,390', NEW TARGET: 10,366' TVD (0' VS) AT 92.9 DEG INC., WINDOW 5' ABOVE / 5' BELOW.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 20:15 | 2021-12-30 21:45 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.18 | 14385 | 14425 | 26.7 | SLD DRILL LATERAL (41' IN 1.43 HRS @ 28.67 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4600/5000 PSI, DIFF- 200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 361 PSI, AVG CASING PRESSURE= 200 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F14116 T/14134 18' TF-15R 1903-1938 RPM-80 TQ-8.1L 10.6R SLD F/14209 T/14217 8' TF-40R 2014-2030 RPM-80 TQ-88.1L 10.6R NOTE: WHILE ON BOTTOM DRILLING @ 14,425', NOTICED APPROXIMATELY 200 PSI SPIKE IN DIFFERENTIAL. DIFF AND ROP THEN DROPPED TO ZERO. PICKED UP OFF BOTTOM AND HAD 200 PSI INCREASE IN OFF BOTTOM PUMP PRESSURE. ATTEMPT TO FEATHER WEIGHT BACK TO BOTTOM. MOTOR DID NOT RESPOND WITH DIFFERENTIAL AND WOULD NOT DRILL. DECISION MADE TO TRIP OUT OF HOLE.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 21:45 | 2021-12-30 22:45 | 1 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 7.22 | 14425 | 14425 | 0 | CIRCULATE AND PREP PITS WITH 9.6 PPG OBM TO FILL BACK SIDE WHILE STRIPPING OUT OF HOLE.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-30 22:45 | 2021-12-31 04:00 | 5.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 7.44 | 14425 | 14425 | 0 | STRIP OUT OF THE HOLE F/14,425'- T/2,740'. FILLING BACKSIDE WITH 17.5 PPG KILL MUD, CALCULATED FILL OF 1.9 BBLS/STD. TOTAL OF 50 BBLS 17.5 PPG PUMPED WHILE STRIPPING F/14,425'. MAX CASING PRESSURE= 361 PSI, AVG CASING PRESSURE= 0 PSI FILL BACKSIDE WITH 9.8 PPG OBM, CALCULATED FILL OF 1.9 BBLS/STD., FLOW CHECK AT SHOE, NO FLOW, MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-31 04:00 | 2021-12-31 04:45 | 0.75 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.47 | 14425 | 14425 | 0 | FLOW TEST AGITATOR BEFORE AND AFTER @ GPM-262, SPM-100, SPP BEFORE LAYING DOWN AGITATOR: 1080 PSI; SPP AFTER LAYING DOWN AGITATOR: 980 PSI. LAY AGITATOR DOWN.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-31 04:45 | 2021-12-31 05:15 | 0.5 | U | PRDHLLT | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 7.49 | 14425 | 14425 | 0 | BULL HEAD 62 BBLS OF 17PPG KILL MUD DOWN BACKSIDE. SICP BEFORE PUMPING KILL MUD= 125 PSI, MAX CASING PRESSURE WHILE PUMPPING KILL MUD= 420, AVG CASING PRESSURE= 0, PRESSURE WENT TO 0 WHILE PUMPING 17 PPG KILL MUD AND REMAINED 0 PSI. OPEN CHOKE FOR SAFETY, OPEN ORBIT VALVE, CHECK FLOW ( NO FLOW). SHUT CHOKE, LEAVE ORBIT OPEN. MONITOR RETURNS @ TRIP TANK.
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-31 05:15 | 2021-12-31 05:45 | 0.5 | U | PRDHLLT | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 7.51 | 14425 | 14425 | 0 | PULL ROTATING HEAD AND INSTALL TRIP NIPPLE, NO FLOW @ TRIP TANK
TAHOE MOUNTAIN H03 PR | 10 | 2021-12-31 05:45 | 2021-12-31 06:00 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.52 | 14425 | 14425 | 0 | CONTINUE TO TRIP OUT OF THE HOLE F/2,749'- T/1,700'. PUMP CALCULATED FILL OF 9.6PPG OBM 1.9 BBLS/STD.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 06:00 | 2021-12-31 07:00 | 1 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.56 | 14425 | 14425 | 0 | CONTINUE TO TRIP OUT OF THE HOLE F/1,700'- T/486'. PUMP CALCULATED FILL OF 9.8 PPG OBM 1.9 BBLS/STD. HOLE TAKING PROPER FILL. MONITOR FILL AND RETURNS ON TRIP TANK. NOTE: @ 486' HOLE STARTED TAKING LESS FILL AND BEGAN TO FLOW VIA TRIP TANK, GAINED 1 BBL. STOP TRIPPING AND SPACE OUT DRILL STRING, SHUT WELL IN AND MONITOR PRESSURE. SICP= 48 PSI.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 07:00 | 2021-12-31 08:00 | 1 | U | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 7.6 | 14425 | 14425 | 0 | BULL HEAD 64 BBLS 17.5 PPG KILL MUD DOWN BACKSIDE VIA KILL-LINE, SLOWLY STAGED UP PUMP RATE f/26 GPM T/130 GPM, KILL LINE SPP= 333 PSI, INITIAL SICP=48, MAX SICP=172 PSI, FINAL SICP= 0 PSI. NOTE: SICP NEVER BROKE OVER WHILE PUMPING. SHUT PUMPS DOWN AFTER PUMPING 64 BBLS TO MONITOR SICP AND WEIGHT UP MORE KILL MUD. WHILE WEIGHTING UP MORE KILL MUD, SICP REDUCED TO 0 PSI. OPEN ORBIT VALVE, CHECK FLOW ( NO FLOW). SHUT CHOKE, LEAVE ORBIT OPEN. MONITOR RETURNS @ TRIP TANK.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 08:00 | 2021-12-31 08:15 | 0.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.61 | 14425 | 14425 | 0 | CONTINUE TRIPPING OUT THE HOLE F/486' T/BHA, FILLING BACKSIDE WITH 17.5 PPG KILL MUD WITH CALCULATED FILL OF 1.9 BBLS/STD (TOTAL OF 10 BBLS). HOLE TAKING PROPER FILL.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 08:15 | 2021-12-31 09:15 | 1 | U | PRDHLLT | TRIP | LDBHA | LAY DOWN BIT / BHA | 7.66 | 14425 | 14425 | 0 | RACK BACK DRILL-N-REAMER, L/D TOP NMDC AND REMOVE MWD, ATTEMPTED TO DRAIN MOTOR, BUT WOULD NOT DRAIN DUE TO MOTOR SPINNING FREELY AND INDICATING A BROKE SHAFT OR CV JOINT, BREAK OUT BIT, BIT GRADE: 1/1-NO-A-X-0-NO-DMF NOTE: BULL HEAD 66 BBLS 17.5 PPG KILL MUD DOWN BACKSIDE VIA KILL-LINE, SLOWLY STAGED UP PUMP RATE F/26 GPM T/157 GPM, KILL LINE SPP= 292 PSI, INITIAL SICP= 0 PSI , MAX SICP= 74 PSI @ 157 GPM, FINAL SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 09:15 | 2021-12-31 10:30 | 1.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 7.71 | 14425 | 14425 | 0 | PICK UP BHA #4. BHA FOLLOWS: 6.75" HALLIBURTON GTD64M SN: 13685103 JETS 6/18S TFA: 1.491), 5.5", 6/7, 8.8 STG @ 2.12° T/S HS88 +.005 .68 REV/GAL; 4.05' BIT TO BEND; 5.5" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF- 2,240 PSI; STALL TRQ-8,014 FT/LBS; BTI VALVE, 5.25" NMPDC, 5.25" UBHO, 5" NMDC, 5" NMDC, TOMAX TOOL, X/O XT-39 P x CET43, 2 STANDS DP, 6-13/16 DRILL N REAM, 26 STANDS DP, AGITATOR, BIT TO SVY-63'. BIT TO GAMMA-54'. TEST MWD (TEST GOOD), MAKE UP BIT. NOTE: FLOAT AND BTI VALVE GOOD.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 10:30 | 2021-12-31 11:45 | 1.25 | U | PRDHLLT | TRIP | PUBHA | PICK UP BIT / BHA | 7.76 | 14425 | 14425 | 0 | TRIP IN THE HOLE F/ BHA T/ 2,778' WITH NO RETURNS, FILL PIPE, PICK UP AGITATOR ON STAND 28.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 11:45 | 2021-12-31 12:15 | 0.5 | U | PRDHLLT | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 7.78 | 14425 | 14425 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 12:15 | 2021-12-31 15:45 | 3.5 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 7.93 | 14425 | 14425 | 0 | STRIP IN THE HOLE WITH NO RETURNS F/2,778' T/9,986', FILLING PIPE EVERY 40 STDS, CHOKE: 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 15:45 | 2021-12-31 16:30 | 0.75 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 7.96 | 14425 | 14425 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80 WHILE MONITORING SICP, SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 16:30 | 2021-12-31 18:45 | 2.25 | U | PRDHLLT | TRIP | BHA | TRIP FOR BIT / BHA | 8.05 | 14425 | 14425 | 0 | CONTINUE STRIPPING IN THE HOLE WITH NO RETURNS F/9,986' T/14,100', FILLING PIPE EVERY 40 STDS, CHOKE: 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI.
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 18:45 | 2021-12-31 19:15 | 0.5 | U | PRDHLLT | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 8.07 | 14425 | 14425 | 0 | WASH AND REAM F/14,100' T/14,425', GPM-400, RPM-50, TORQ 6-8K, SPP 5100
TAHOE MOUNTAIN H03 PR | 11 | 2021-12-31 19:15 | 2022-01-01 03:00 | 7.75 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.4 | 14425 | 15660 | 159.4 | ROTATE DRILL LATERAL (1,235' IN 7.62 HRS @ 162.14 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-8K/18K, MRPM-272, TTRPM-352, SPP- 4800/5800 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 04:42 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 15,543', NEW TARGET: 10,380' TVD (0' VS) AT 92.9 DEG INC., WINDOW 5' ABOVE / 5' BELOW. NOTE: TARGET CHANGE RECEIVED VIA TEXT @ 05:15 HOURS, DEPTH WHEN RECEIVED TARGET CHANGE 15,698', NEW TARGET: 10,373' TVD (0' VS) AT 92.9 DEG INC., WINDOW 5' ABOVE / 5' BELOW.
TAHOE MOUNTAIN H03 PR | 11 | 2022-01-01 03:00 | 2022-01-01 06:00 | 3 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.52 | 15660 | 15735 | 25 | SLD DRILL LATERAL (75' IN 3.13 HRS @ 23.94 FPH) WOB-20/30K, SPM-76/76, GPM-400 PSI, MRPM-272, SPP- 4800/5200 PSI, DIFF- 200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/14425 T/14440 15' TF-160R 1913-1945 RPM-80 TQ-7.6R 6.4L SLD F/14698 T/14718 20' TF-130R 2121-2215 RPM-80 TQ-10R 9.3L SLD F/14792 T/14802 10' TF-120R 2245-2311 RPM-80 TQ-8.3R 6.7L SLD F/15083 T/15095 12' TF-70R 0048-115 RPM-80 TQ-8.3R 6.7L SLD F/15172 T/15180 8' TF-15R 144-206 RPM-80 TQ-8.3R 6.7L SLD F/15367 T/15377 10' TF-160R 315-344 RPM-80 TQ-8.3R 6.7L
TAHOE MOUNTAIN H03 PR | 12 | 2022-01-01 06:00 | 2022-01-01 12:00 | 6 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.77 | 15735 | 16711 | 162.7 | ROTATE DRILL LATERAL (976' IN 6.02 HRS @ 162.46 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-18K/19K, MRPM-272, TTRPM-352, SPP- 4300/5300 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: STARTED PUMPING 10 BBLS PHPA SWEEPS EVERY 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA @ 16,538'. *** TORQUE PRIOR TO PUMPING SWEEPS 17K/19K @ 301 FPH ROP, TORQUE AFTER SWEEPS 17K/18K @ 326 FPH ROP***
TAHOE MOUNTAIN H03 PR | 12 | 2022-01-01 12:00 | 2022-01-01 14:45 | 2.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.89 | 16711 | 16774 | 22.9 | SLD DRILL LATERAL (63’ IN 2.73 HRS @ 23.08 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP- 4300/4700 PSI, DIFF- 200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/15746 T/15759 13' TF-180 605-637 RPM-80 TQ-11R/9L SLD F/16032 T/16047 15' TF-150R 850-938 RPM-80 TQ-14R/12L 12 SLD F/16316 T/16328 12' TF-60R 1104-1130 RPM-80 TQ-9R/7L SLD F/16422 T/16432 10' TF-70R 1158-1225 RPM-80 TQ-6R/97 SLD F/16600 T/16613 13' TF-180 1317-1348 RPM-80 TQ-9R/7L
TAHOE MOUNTAIN H03 PR | 12 | 2022-01-01 14:45 | 2022-01-01 18:45 | 4 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 9.05 | 16774 | 16774 | 0 | WHILE BREAKING OUT TO MAKE A CONNECTION @ 16,776’ THE MANUAL IBOP BACKED OUT FROM THE HYDRAULIC IBOP, BREAK FEATHER PLATES AND CHANGE GRABBER DIES, BREAK SAVER SUB OUT OF DRILL PIPE, INSPECTED SAVER SUB AND OBSERVED GALLED THREADS, RETORQUE IBOP, CHANGE OUT SAVER SUB, CHANGE GRABBER DIES BACK, INSPECTED THREADS ON DRILL PIPE AND OBSERVED GALLED THREADS, ATTEMPTED TO BREAK CONNECTION ON BAD JOINT WITH ST-80, NO SUCCESS, ATTEMPTED TO BREAK WITH RIG TONGS, NO SUCCESS, RIG UP DOUBLE LINE ON RIG TONGS AND BROKE CONNECTION, L/D BAD JOINT, PICK UP ANOTHER JOINT OF DRILL PIPE, CHANGE OUT ST-80 DIES.
TAHOE MOUNTAIN H03 PR | 12 | 2022-01-01 18:45 | 2022-01-02 02:15 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.36 | 16774 | 17934 | 154.7 | ROTATE DRILL LATERAL (1,160' IN 7.32 HRS @ 158.46 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-18K/19K, MRPM-272, TTRPM-352, SPP- 5,300/6000 PSI, DIFF- 800/1000 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMPING 10 BBLS PHPA SWEEPS EVERY +/- 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA. *** SWEEP @ 16,538': TORQUE PRIOR TO PUMPING SWEEPS 17K/18K @ 301 FPH ROP, TORQUE AFTER SWEEPS 17K/18K @ 326 FPH ROP*** NOTE: WINDOW CHANGE RECEIVED VIA TEXT @ 04:09 HOURS, DEPTH WHEN RECEIVED WINDOW CHANGE 17,714', SAME TARGET: 10,373' TVD (0' VS) AT 92.9 DEG INC.,***** NEW WINDOW 5' ABOVE / 5' BELOW.
TAHOE MOUNTAIN H03 PR | 12 | 2022-01-02 02:15 | 2022-01-02 06:00 | 3.75 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 9.52 | 17934 | 17998 | 17.1 | SLD DRILL LATERAL (64’ IN 3.68 HRS @ 17.39 FPH) WOB-20/30K, SPM-76/76, GPM-400, MRPM-272, SPP- 5300/5700 PSI, DIFF- 200/400 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. SLIDE DEPTHS: SLD F/16779 T/16794 15' TF-180 1900-1937 RPM-80 TQ- 8R 8L SLD F/16967 T/16975 8' TF-180 2034-2113 RPM-80 TQ- 8R 8L SLD F/17159 T/17169 10' TF-140R 2210-2245 RPM-80 TQ-9.5R 9.5L SLD F/17253 T/17263 10' TF-160R 2313-2345 RPM-80 TQ-9.5R 9.5L SLD F/17441 T/17447 6' TF15R 120-145 RPM-80 TQ- 11.8R 9.2L SLD F/17913 T/17928 15' TF-170R 417-515 RPM-80 TQ-13R 12.4L
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 06:00 | 2022-01-02 08:30 | 2.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 9.63 | 17998 | 18645 | 258.8 | ROTATE DRILL LATERAL (647' IN 3.5 HRS @ 184.86 FPH) WOB-30/40K, SPM-76/76, GPM-400, RPM-80, TQ-21K/24K, MRPM-272, TTRPM-352, SPP- 4700/5450 PSI, DIFF- 550/750 PSI, CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI, AVG CASING PRESSURE= 0 PSI, MAX SICP= 0 PSI. DRILLING UNDER MUDCAP WITH PRODUCTION WATER AND FRESH WATER ADDING 3.5 BPH DIESEL AND 1.5 GALS/HR PHPA. NOTE: PUMPING 10 BBLS PHPA SWEEPS EVERY +/- 300'. CONSISTING OF FRESH WATER AND 2 PPB PHPA.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 08:30 | 2022-01-02 10:30 | 2 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.71 | 18645 | 18645 | 0 | PERFORMED CLEAN UP CYCLE WITH WELL ON MUD CAP. PUMPED 30 BBL PHPA SWEEP, CIRCULATE 6 BOTTOMS UP TO LOSS ZONE, SPM-76/76, GPM-400,MRPM-272, RPM-80, CHOKES- 0% / 0%. MAX CSG PSIWHILE CIRC-0 PSI. TQ=18/19K, SPP-3800/4000 PSI, 1ST BTM UP START TQ=12K/24K, END= 12K/18K, P/U WT=245K, S/O=140K 2ND BTM UP END TQ=12K/17K, P/U WT=220K, S/O WT=170K 3RD BTM UP END TQ=12K/17K, P/U WT=220K, S/O WT=170K NOTE: BACK REAM 40 RPM @ 10-20 FPM, WASH AND REAM 80 RPM @ 30-40 FPM PERFORMIMG CLEAN UP CYCLE.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 08:30 | 2022-01-02 08:30 | 0 | P | PRDHLCSG | MSTN | TD | MILESTONE_TD WELL | 9.63 | 18645 | 18645 |  | MILESTONE_TD WELL ON 01/02/2022 @ 09:30 HRS
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 10:30 | 2022-01-02 12:15 | 1.75 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 9.78 | 18645 | 18645 | 0 | ATTEMPT TO TRIP OUT THE HOLE ON ELEVATORS WITH NO SUCCESS, MAX OVER PULL-400K, BACK REAM OUT OF HOLE F/18,645' T/17,330' @ 20-30 FPM, SPM-76/76, GPM-400, RPM-80, MRPM-272, TMRPM-352, TRQ-13/18K, SPP-4500/4700 PSI. CHOKES- 0% / 0%, MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI MAX CASING PRESSURE ON CONNECTIONS= 0 PSI AVG CASING PRESSURE ON CONNECTIONS= 0 PSI NOTE: L/D SINGLE TO BREAK UP CONNECTIONS
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 12:15 | 2022-01-02 22:30 | 10.25 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 10.21 | 18645 | 18645 | 0 | STRIP OUT OF THE HOLE WET F/17,330' T/2,865' FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD. MAX CASING PRESSURE= 0 PSI AVG CASING PRESSURE= 0 PSI NOTE: USED RIG TONGS ON TIGHT BREAKS, ENCOUNTERED TIGHT BREAKS AND HAD TO DOUBLE LINE RIG TONGS TO BREAK APPROXIMATELY 50% OF DRILL PIPE CONNECTIONS.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 22:30 | 2022-01-02 23:00 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.23 | 18645 | 18645 | 0 | SERVICE TOP DRIVE, DRAWWORKS AND ST-80 WHILE MONITORING SICP, SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-02 23:00 | 2022-01-03 00:45 | 1.75 | P | PRDHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 10.3 | 18645 | 18645 | 0 | CUT AND SLIP 120' OF DRILL LINE. NOTE: BULLHEAD 50 BBLS OF 17.5 PPG KILL MUD DOWN BACKSIDE VIA KILL LINE, STAGING PUMP RATE UP F/26 GPM T/157 GPM FOR SAFETY FACTOR. , KILL LINE SPP= XX PSI, INITIAL CASING PRESSURE= 0 PSI, FINAL CASING PRESSURE= 0 PSI.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-03 00:45 | 2022-01-03 01:15 | 0.5 | P | PRDHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 10.32 | 18645 | 18645 | 0 | FLOW CHECK, NO FLOW, REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-03 01:15 | 2022-01-03 03:45 | 2.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 10.43 | 18645 | 18645 | 0 | TRIP OUT OF THE HOLE F/2,865' T/ BHA FILLING BACKSIDE WITH 12.8 PPG OBM CALCULATED FILL OF 1.9 BBLS/STD, L/D AGITATOR STAND 28
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-03 03:45 | 2022-01-03 05:00 | 1.25 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 10.48 | 18645 | 18645 | 0 | RACK BACK DRILL-N-REAMER, X/O, L/D TOMAX THRUSTER, AND TOP NMDC. PULL MWD, DRAIN MOTOR AND BREAK BIT, L/D MOTOR AND REMAINING BHA. NOTE: MUD MOTOR DRAINED GOOD, BIT BOX SQUAT WAS WITHIN TOLERENCE BIT GRADED: 1-1-BT-G-X-0-NO-TD
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-03 05:00 | 2022-01-03 05:30 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 10.5 | 18645 | 18645 | 0 | REMOVE WEAR BUSHING, CLEAN RIG FLOOR, L/D MOUSE HOLE, REMOVE 4 1/2" ELAVATORS WHILE MONITORING SICP, SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 13 | 2022-01-03 05:30 | 2022-01-03 06:00 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.52 | 18645 | 18645 | 0 | HELD PJSM, RIG UP FRANK'S 5" CASING TOOLS AND EQUIPMENT WHILE MONITORING SICP, SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 06:00 | 2022-01-03 07:15 | 1.25 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.57 | 18645 | 18645 | 0 | CONTINUE RIGGING UP FRANK'S 5" CASING TOOLS AND EQUIPMENT WHILE MONITORING SICP, SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 07:15 | 2022-01-03 09:45 | 2.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.68 | 18645 | 18645 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 2 JTS 5" 18# P110 ICY WEDGE 425 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING T/2,000' WITH NO RETURNS T/2,001’, FILLING PIPE ON THE FLYWITH WATER.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 09:45 | 2022-01-03 10:30 | 0.75 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 10.71 | 18645 | 18645 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 10:30 | 2022-01-03 16:15 | 5.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.95 | 18645 | 18645 | 0 | CONTINUE PICKING UP AND RUNNING 5" 18# P110 ICY WEDGE 425 PRODUCTION CASING F/2,000' T/9,341.17' WHILE STRIPPING IN WITH NO RETURNS. MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY WITH WATER.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 16:15 | 2022-01-03 16:45 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 10.97 | 18645 | 18645 | 0 | RIG DOWN 5" CRT AND ELEVATORS, RIG UP 5 1/2" CRT AND ELEVATORS WHILE MONITORING SICP, SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 16:45 | 2022-01-03 21:30 | 4.75 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.17 | 18645 | 18645 | 0 | PICK UP AND RUN 5 1/2" 23# P110 ICY WEDGE 463 PRODUCTION CASING F/9,341.17' T/15,503' WHILE STRIPPING IN, MAX CSG PSI: 0 PSI, FILLING PIPE ON THE FLY, NO RETURNS.
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-03 21:30 | 2022-01-04 05:30 | 8 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 11.5 | 18645 | 18645 | 0 | WASH AND REAM PRODUCTION CASING F/15,503' T/18,634' @ 10-20 FPM WITH WATER AND WITH CRT @ 30 RPM, TRQ-10K/15K, SPM-64/64, GPM-335, SPP-0 PSI, NO RETURNS, CHOKES CLOSED; REMOVE ROTATING HEAD, PICK UP LANDING JOINT WITH ROTATING HEAD, SLACK OFF AND INSTALL ROTATING HEAD, OPEN ANNULAR, WASH AND REAM F/18,604’ T/18,632’, AND LAND ON HANGER W/140K (W/O BLOCKS) @ 18,632.2’, RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: INNOVEX DV FLOAT SHOE, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, 1 INNOVEX DV FLOAT COLLAR, 1 JT 5" 18# P110 ICY WEDGE 425 CASING, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICYWEDGE 425 CASING, 2 JTS 5" 18# P110 ICYWEDGE 425 CASING AND TEST FLOAT EQUIPMENT. RAN 208 JTS OF 5" 18# P110 ICY WEDGE 425 CASING, 1- X-OVER 425x463, 1 JOINT WEDGE 463, 1-5 1/2" MARKER JT, RAN 211 JTS OF 5.5" 23# P-110 WEDGE 463, 1-MARKER JT AND 1 JOINT OF WEDGE 463 CASING SHOE @ 18,634.2' TOP OF FLOAT COLLAR @ 18,586.1' BOTTOM OF TOE SLEEVE VALVE @ 18,543.1' TOP OF TOE SLEEVE VALVE @ 18,518' TOP OF X-OVER @ 9,293' TOP OF MARKER JT @ 9,229.2' LEFT OUT 9 JOINTS OF 5" -397.26' LEFT OUT 16 JOINTS OF 5.5"-688.97'
TAHOE MOUNTAIN H03 PR | 14 | 2022-01-04 05:30 | 2022-01-04 06:00 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 11.52 | 18645 | 18645 | 0 | RIG DOWN FRANK'S CRT AND INSTALL WEATHERFORD FOSV
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 06:00 | 2022-01-04 06:30 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 11.54 | 18645 | 18645 | 0 | CEMENT SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE, MONITOR SICP, SICP= 0 PSI
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 06:30 | 2022-01-04 07:30 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 11.58 | 18645 | 18645 | 0 | CIRCULATE 1 CASING CAPACITY WITH CHOKES CLOSED WHILE CONTINUEING TO RIG DOWN CASING TOOLS SPM-64/64, GPM-336, SPP- 2985 PSI. INITIAL CASING PRESSURE WHILE CIRCULATING= 0 PSI AND FINAL CASING PRESSURE WHILE CIRCULATING= 0 PSI, SHUT IN CASING PRESSURE= 0 PSI. HOLD PJSM WITH NINE CEMENT CREW.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 07:30 | 2022-01-04 10:15 | 2.75 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 11.7 | 18645 | 18645 | 0 | SWAP CIRCULATING IRON T/ CEMENT STANDPIPE, FLUSHED THROUGH & TESTED CEMENTING LINES T/8500 PSI, CEMENTED 1ST STAGE 5/5-1/2" PRODUCTION CASING WITH NO RETURNS WITH NINE ENERGY SERVICES: PUMPED 40 BBL 10.5 PPG WEIGHTED SPACER, 292 BBL 13.5 PPG 955 SK 1.72 YIELD 35/65 POZ-CLASS H LEAD CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 362 BBLS (1ST 20 BBLS SUGAR WATER) OF FRESH WATER @ 8 BPM. SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2850 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 3850 PSI, HELD FOR 5 MIN, BLED BACK 5.0 BBLS. FLOATS HELD. PLUG DOWN @ 10:02 ON 01/04/2022. MAX CSG PSI= 0 PSI, AVG CASING PSI=0 PSI, CSG PRESSURE 0 PSI WITH PUMPS OFF AFTER CEMENTING.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 10:15 | 2022-01-04 10:45 | 0.5 | P | PRDHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 11.72 | 18645 | 18645 | 0 | HELD PJSM, RIG DOWN CIRCULATING IRON FROM RIG FLOOR, REMOVE CHECK VALVE FROM KILL LINE, RIG UP CIRCULATING IRON TO KILL LINE WHILE MONITORING SICP, SICP= 49 PSI.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 10:45 | 2022-01-04 12:45 | 2 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 11.8 | 18645 | 18645 | 0 | TESTED CEMENTING LINES T/8500 PSI, PUMP 30 BBLS 17.5 PPG KILL MUD DOWN THE BACKSIDE THROUGH KILL LINE @ 1 BPM=950 PSI & CASING PSI=945 PSI; 2 BPM= 1490 PSI & CASING PSI=1500 PSI; 3 BPM= 1880 PSI & CASING PSI= 1920 PSI; 4 BPM= 2300 PSI & CASING PSI= 2140 PSI AND 5 BPM= 3060 PSI & CASING PSI= 2720 PSI TO ESTABLISH INJECTION RATES. -INITIAL CSG PSI= 2535 PSI , FINAL CSG PSI=1569 PSI. PUMP 40 BBLS 10.5 PPG WEIGHTED SPACER, FOLLOWED BY 313 BBLS 1022 SK 1.72 YIELD 35/65 POZ-CLASS H 13.5 PPG LEAD CEMENT, PUMP 50 BBLS 210 SK 1.33 YIELD TYPE I/II TAIL CEMENT, FOLLOWED BY 20 BBLS WATER. MAX CSG PSI= 2631 PSI W/30 BBLS OF LEAD CEMENT PUMPED @ 5 BPM, AVG CASING PSI= 1850 PSI. MAX PUMP PRESSURE=2860 PSI @ 5 BPM. CSG PRESSURE DECREASED TO 44 PSI WITH PUMPS OFF AFTER CEMENTING. ESTIMATED TOC-1210'.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 12:45 | 2022-01-04 13:30 | 0.75 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 11.83 | 18645 | 18645 | 0 | RIG DOWN CEMENT HEAD AND CIRCULATING IRON, MONITOR SICP FOR 10 MINUTES, INITIAL SICP= 44 PSI, SICP INCREASED AND STABLIZED @ 70 PSI, SLOWLY BLED OFF SICP TO TRIP TANK WITH NO RETURNS, FINAL SICP= 0 PSI.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 13:30 | 2022-01-04 16:00 | 2.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 11.94 | 18645 | 18645 | 0 | FLOW CHECK, NO FLOW, WASH THROUGH BOP STACK AND CHOKE MANIFOLD, REMOVE FOSV AND LAY DOWN LANDING JOINT. REMOVE BAILS AND CASING ELEVATORS, AND RIG UP RIG 4.5" ELEVATORS, RIG UP WASH OUT TOOL AND SET 6" ABOVE HANGER, PUMP @ 80 GPM W/100 PSI TO CLEAN THE TOP OF HANGER. REMOVE WASH OUT TOOL AND PICK UP PACKOFF, INSTALLED AND TESTED STREAM-FLO PACK-OFF, PULL TESTED PACK-OFF TO 25K AND TESTED PACK-OFF T/10000 PSI. BACK OUT FROM PACKOFF AND L/D JOINT OF DP. INSTALL BPV.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 16:00 | 2022-01-04 17:00 | 1 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 11.98 | 18645 | 18645 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE, INSTALL WEATHER CAP AND SECURE WELL. TEST WEATHER CAP T/5000 PSI. RELEASE WELL AND RIG ON 01/04/2022 @ 17:00 HRS.
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 17:00 | 2022-01-04 17:00 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 11.98 | 18645 | 18645 |  | MILESTONE_TURN OVER TO COMPLETION ON 01/04/2022 @ 17:00
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 17:00 | 2022-01-04 17:00 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 11.98 | 18645 | 18645 |  | MILESTONE_RIG RELEASE ON 01/04/2022 @ 17:00
TAHOE MOUNTAIN H03 PR | 15 | 2022-01-04 17:00 | 2022-01-04 17:00 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 11.98 | 18645 | 18645 |  | MILESTONE_WELL RELEASE ON 01/04/2022 @ 17:00
YUKON A 1H | 3 | 2020-11-02 | 2020-11-02 | 0 | P | MOBDMOB | MSTN | MBDMB | MILESTONE_MOB/DEMOB | 0 | 105 | 105 |  | MILESTONE_MOB/DEMOB 11/02/2020 @ 00:00
YUKON A 1H | 3 | 2020-11-02 | 2020-11-02 01:30 | 1.5 | P | MOBDMOB | LMOV | SKDWLK | SKID / WALK RIG | 0 | 105 | 105 | 0 | PREPARE TO WALK RIG AND ALL EQUIPMENT, SET MATS, WALK FROM LIEBSCHER 3H TO YUKON A 1H, CENTERED AND LEVELED SUB OVER CONDUCTOR
YUKON A 1H | 3 | 2020-11-02 01:30 | 2020-11-02 02:00 | 0.5 | P | MOBDMOB | RURD | RUEQP | RIG UP EQUIPMENT | 0 | 105 | 105 | 0 | RIG UP CELLAR PUMPS AND LINES, RISER ON CONDUCTOR PIPE
YUKON A 1H | 3 | 2020-11-02 02:00 | 2020-11-02 02:30 | 0.5 | P | MOBDMOB | TRIP | BHA | TRIP FOR BIT / BHA | 0 | 105 | 105 | 0 | PICK UP BIT 13-1/2" ULTERRA SPL616 W: 9/14 JETS TFA: 1.353, MOTOR 7-7/8", 7/8L, 5.9 STG @ 1.5° WITH 13" NBS, 13" NORTRAC IBS, 8" NMPDC, 7.75" UBHO, 2-8" NMDC, 6-5/8" REG(P) x 4-1/2 XH(B) X-OVER, 9 JTS HWDP, SCRIBE AND INSTALL MWD, TAG BOTTOM @ 105'.
YUKON A 1H | 3 | 2020-11-02 02:30 | 2020-11-02 02:30 | 0 | P | SFHL | MSTN | SPUD | MILESTONE_SPUD WELL | 0 | 105 | 105 |  | MILESTONE_SPUD WELL 11/2/2020 @ 02:30
YUKON A 1H | 3 | 2020-11-02 02:30 | 2020-11-02 05:00 | 2.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.1 | 105 | 1341 | 494.4 | ROTATE (1236' IN 2.43 HRS @ 508 FPH) WOB-20/35K, RPM-100, TRQ- 5/16K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2100 PSI, DIFF-800/1000 PSI.
YUKON A 1H | 3 | 2020-11-02 05:00 | 2020-11-02 06:00 | 1 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.15 | 1341 | 1524 | 183 | SLIDE (183' IN 1.07 HRS @ 172 FPH) WOB: 10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP- 1700/1800 PSI, DIFF- 200/400 PSI. SLIDE DEPTHS: SLD F/495 T/513 18' TF-263M 324-330 SLD F/586 T/601 15' TF-270M 340-346 SLD F/684 T/704 20' TF-270M 354-400 SLD F/778 T/798 20' TF-270M 408-416 SLD F/872 T/897 25' TF-10L 423-433 SLD F/965 T/995 30' TF-HS 440-450 SLD F/1061 T/1091 30' TF-HS 457-507 SLD F/1154 T/1179 25' TF-HS 513-521
YUKON A 1H | 4 | 2020-11-02 06:00 | 2020-11-02 07:30 | 1.5 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.21 | 1524 | 2279 | 503.3 | ROTATE (755' IN 1.5 HRS @ 503.3 FPH) WOB-20/35K, RPM-100, TRQ- 7/18K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-1800/2700 PSI, DIFF-700/900 PSI. NOTE: HOLE STARTED PACKING OFF AND STARTED COMMUNICATING WITH LIEBSCHER 3H CAUSING FLOW BACK TO LIEBSCHER 3H. FLOWED BACK APPROXIMATELY 20 BBLS OF CMT FROM LIEBSCHER 3H
YUKON A 1H | 4 | 2020-11-02 07:30 | 2020-11-02 10:30 | 3 | U | SFHL | DPROB | DFAIL | DOWNHOLE FAILURE | 0.33 | 2279 | 2279 | 0 | PULL 5 STANDS F/2,279' T/1,713' WITH NO EXCESSIVE DRAG, SLOWLY STAGE UP PUMPS F/64 GPM T/160 GPM, 100 RPM AND RE-ESTABLISHED CIRCULATION WITH OUT COMMUNICATING WITH LIEBSCHER 3H. CIRCULATE AND RECIPROCATE PIPE GPM-160 AND100 RPM WHILE ALLOWING MORE TIME FOR THE CEMENT ON THE LIEBSCHER 3H TO SET UP.
YUKON A 1H | 4 | 2020-11-02 10:30 | 2020-11-02 12:00 | 1.5 | U | SFHL | DPROB | DFAIL | DOWNHOLE FAILURE | 0.4 | 2279 | 2279 | 0 | SLOWLY STAGED UP PUMPS F/160 GPM T/900 GPM, WASH/REAM F/1,713' T/2,279', GPM-900, RPM-100, SPP-1800 PSI, TRQ-1/3K.
YUKON A 1H | 4 | 2020-11-02 12:00 | 2020-11-02 13:00 | 1 | P | SFHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 0.44 | 2279 | 3145 | 866 | ROTATE (866' IN 1.23 HRS @ 704.1 FPH) WOB-20/35K, RPM-100, TRQ- 7/18K, SPM-94/94/94, GPM-900, MMRPM-149, TRPM-249, SPP-2000/2900 PSI, DIFF-700/900 PSI.
YUKON A 1H | 4 | 2020-11-02 13:00 | 2020-11-02 13:30 | 0.5 | P | SFHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 0.46 | 3145 | 3170 | 50 | SLIDE (25' IN .27 HRS @ 92.6 FPH) WOB: 10/20K, SPM-94/94/94, GPM-900, MMRPM-149, SPP- 2000/2400 PSI, DIFF- 200/400 PSI. SLIDE DEPTHS: SLD F/2375' T/2400' 25' TF-HS 12:05-12:21
YUKON A 1H | 4 | 2020-11-02 13:30 | 2020-11-02 14:30 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.5 | 3170 | 3170 | 0 | PUMP 3-30 BBL SWEEP IN TANDEM, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM-900, RPM-100, TRQ-1/2K, SPP-2000 PSI.
YUKON A 1H | 4 | 2020-11-02 14:30 | 2020-11-02 16:00 | 1.5 | P | SFHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 0.56 | 3170 | 3170 | 0 | TRIP OUT OF HOLE F/3,170' T/ BHA, NO EXCESSIVE DRAG ON TRIP OUT OF HOLE.
YUKON A 1H | 4 | 2020-11-02 16:00 | 2020-11-02 18:30 | 2.5 | P | SFHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 0.67 | 3170 | 3170 | 0 | L/D 1 JOINT OF HWDP, REMOVE MWD TOOL, DRAIN MOTOR, BREAK OUT BIT, L/D STABLIZER AND MOTOR, PICK UP AND SCRIBE NEW MOTOR, RACK BHA BACK IN DERRICK.
YUKON A 1H | 4 | 2020-11-02 18:30 | 2020-11-02 19:30 | 1 | P | SFHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 0.71 | 3170 | 3170 | 0 | PJSM WITH CASING CREW, RIG UP EXPRESS CASING EQUIPMENT, BAILS, ELEVATORS, TONGS, CRT, BOWL AND SLIPS.
YUKON A 1H | 4 | 2020-11-02 19:30 | 2020-11-02 23:00 | 3.5 | P | SFHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 0.85 | 3170 | 3170 | 0 | MAKE UP FLOAT SHOE, 2 JTS. 10 3/4" 45.5# J-55 BT&C CASING, FLOAT COLLAR, 1 JT. 10 3/4" 45.5# J-55 BT&C CASING, TEST FLOATS (TEST GOOD), RUN 75 JOINTS OF 10 3/4" 45.5# J-55 T/3,156.48', RAN 40 CENTRALIZERS PLACED AS FOLLOWS, 1 CENTRALIZER 10' ABOVE SHOE, 1 ON TOP OF JT. #1, 1 ON TOP OF JT. #2 AND ON TOP OF JT #3, AND THEN EVERY OTHER JT. ALL THE WAY TO 78.42', INSTALLED STREAMFLO WELLHEAD WITH BASE PLATE THEN LANDED ON CONDUCTOR. INSTALLED VALVES & PLUG, TESTED WELLHEAD TO 5000 PSI, LANDED 65" BELOW GROUND LEVEL. (WASH DOWN LANDING JOINT AND SET 120K ON BASE PLATE) SHOE: 3,156.48' TOP OF FLOAT COLLAR: 3,071.63'
YUKON A 1H | 4 | 2020-11-02 23:00 | 2020-11-03 | 1 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 0.9 | 3170 | 3170 | 0 | CIRCULATE 1.5 BOTTOMS UP WITH CRT WHILE RIGGING DOWN CASING TOOLS, GPM-334, SPP-100/200 PSI. NO LOSSES.
YUKON A 1H | 4 | 2020-11-03 | 2020-11-03 01:00 | 1 | P | SFHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 0.94 | 3170 | 3170 | 0 | HOLD PJSM, RIG DOWN CRT, L/D LANDING JOINT, RIG UP CEMENT HEAD AND CIRCULATING IRON.
YUKON A 1H | 4 | 2020-11-03 01:00 | 2020-11-03 04:00 | 3 | P | SFHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 1.06 | 3170 | 3170 | 0 | PJSM WITH ALL CREWS, TEST LINES T/ 2,000 PSI & CEMENTED WITH: 25 BBL 8.3 PPG FRESH WATER SPACER, 341 BBLS 11.6 PPG LEAD CEMENT, 89 BBL 14.4 PPG TAIL CEMENT, DISPLACED WITH 297 BBLS OF 9.0 PPG OIL BASE MUD. BUMPED PLUG W/ 700 PSI PRESSURED UP T/ 1200 PSI (500 PSI OVER) @ 4 BPM. HELD PRESSURE FOR 5 MINUTES AND THEN BLEED OFF PRESSURE. BLED BACK 2 BBLS. MONITOR FOR 5 MINUTES TO ENSURE WELL WAS STATIC & FLOAT EQUIPMENT HOLDING. (FLOATS HELD) CIRCULATE BACK TO SURFACE 25 BBLS OF SPACER AND 227 BBLS OF LEAD CEMENT. CEMENTED W/ FULL RETURNS.
YUKON A 1H | 4 | 2020-11-03 04:00 | 2020-11-03 06:00 | 2 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.15 | 3170 | 3170 | 0 | PRESSURE TESTED 10-3/4" 45.5# J-55 BTC CASING TO 1500 PSI FOR 15 MIN. (PRESSURE HELD TEST WAS GOOD); RIG DOWN CEMENT HEAD, CIRCULATING IRON AND CELLAR PUMPS, INSTALL WELL CAP WITH STREAMFLO AND SECURE WELL.
YUKON A 1H | 4 | 2020-11-03 06:00 | 2020-11-03 06:00 | 0 | P | SFHLCSG | MSTN | HOLD1 | MILESTONE_HOLD WELL OPERATIONS 1 | 1.15 | 3170 | 3170 |  | MILESTONE_HOLD WELL OPERATIONS 1 11/03/2020 @ 06:00
YUKON A 1H | 4 | 2020-11-03 06:00 | 2020-11-03 06:00 | 0 | P | SFHLCSG | TEST | PSRTST | PRESSURE TEST | 1.15 | 3170 | 3170 |  | Walk to Yukon C3H
YUKON A 1H | 5 | 2020-11-10 06:00 | 2020-11-10 07:30 | 1.5 | P | SFHLCSG | LMOV | SKDWLK | SKID / WALK RIG | 1.21 | 3170 | 3170 | 0 | PREPPED RIG TO WALK, SWAP HYDRAULICS TO WALKING SYSTEM, WALK RIG F/ LIEBSCHER 3H T/ YUKON A 1H, CENTERED AND LEVELED SUB OVER WELLHEAD, WITNESSED RIG CENTER OVER WELL.
YUKON A 1H | 5 | 2020-11-10 07:30 | 2020-11-10 07:30 | 0 | P | SFHLCSG | MSTN | RSUM1 | MILESTONE_RESUME WELL OPERATIONS 1 | 1.21 | 3170 | 3170 |  | MILESTONE_RESUME WELL OPERATIONS 1 ON 11/10/2020 @ 06:00
YUKON A 1H | 5 | 2020-11-10 07:30 | 2020-11-10 11:00 | 3.5 | P | SFHLCSG | BOP | NU | NIPPLE UP BOP | 1.35 | 3170 | 3170 | 0 | HELD PJSM W/STREAMFLO, REMOVE WELL CAP, INSTALLED BOP ONTO WELLHEAD, RAN UP AND SECURED STREAM-FLO ADAPTER FLANGE TO WELLHEAD, UNLATCHED BOP WRANGLER FROM BOP'S AND LAID OVER SAME, INSTALLED TURNBUCKLES AND CENTERED STACK. HOOK UP FLOWLINE. REMOVE CASING RAMS AND INSTALL TOP VARIABLE RAMS.
YUKON A 1H | 5 | 2020-11-10 11:00 | 2020-11-10 12:00 | 1 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.4 | 3170 | 3170 | 0 | MAKE UP TEST PLUG TO JOINT DRILL PIPE AND SET, FILL STACK, TEST BOP 250 PSI LOW / 5000 PSI HIGH. TEST WELLHEAD/BOP, TOP RAMS, KILL LINE AND KILL LINE CHECK VALVE. RIG DOWN TESTERS.
YUKON A 1H | 5 | 2020-11-10 12:00 | 2020-11-10 12:30 | 0.5 | P | SFHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 1.42 | 3170 | 3170 | 0 | PERFORM ACCUMULATOR DRAW DOWN TEST.
YUKON A 1H | 5 | 2020-11-10 12:30 | 2020-11-10 13:00 | 0.5 | P | SFHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 1.44 | 3170 | 3170 | 0 | INSTALL WEAR BUSHING, TRIP NIPPLE AND MOUSE HOLE, CLEAN RIG FLOOR AND PREP TO PICK UP BHA.
YUKON A 1H | 5 | 2020-11-10 13:00 | 2020-11-10 14:00 | 1 | P | SFHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 1.48 | 3170 | 3170 | 0 | PICK UP (9-7/8" ULTERRA SPL613: JETS 6/14'S & 3/16'S TFA: 1.491) BIT, 7-3/4", 7/8L, 5.9 STG @ 2.0° FBH TS; .166 REV/GAL; 6.02' BIT TO BEND 8-5/16" PAD OD; FLOW RANGE-400/900 GPM; MAX DIFF-1330 PSI; 8" NMPDC, 7 3/4" UBHO, 2-8" NMDC, 1- X/O 4-1/2 XH x 6-5/8 REG, 2- STDS 6 1/2" DC, 1- X/O 4-1/2 IF x 4-1/2 XH, 3-STDS 5" HWDP, BIT TO SENSOR-70' AND GAMMA-60', TEST MWD ( GOOD TEST).
YUKON A 1H | 5 | 2020-11-10 14:00 | 2020-11-10 17:00 | 3 | P | SFHLCSG | TRIP | BHA | TRIP FOR BIT / BHA | 1.6 | 3170 | 3170 | 0 | TRIP IN THE HOLE F/BHA T/3,071' -(P/U AGITATOR ON STAND 22) (BEFORE 580 PSI AFTER 720 PSI @ 337 GPM), REMOVE TRIP NIPPLE / INSTALL ROTATING HEAD.
YUKON A 1H | 5 | 2020-11-10 17:00 | 2020-11-10 17:30 | 0.5 | P | SFHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 1.63 | 3170 | 3170 | 0 | RIG SERVICE.
YUKON A 1H | 5 | 2020-11-10 17:30 | 2020-11-10 18:30 | 1 | P | SFHLCSG | DLOUT | DRLCM | DRILL OUT CEMENT | 1.67 | 3170 | 3180 | 10 | DRILL SHOE TRACK AND 10' NEW FORMATION F/3,170' T/3,180', GPM-450, SPP-1500 PSI, RPM-40, DIFF-200 PSI.
YUKON A 1H | 5 | 2020-11-10 18:30 | 2020-11-10 19:00 | 0.5 | P | SFHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 1.69 | 3180 | 3180 | 0 | CIRCULATE BOTTOMS UP GPM-450, SPP-1300 PSI, RPM-40, FILL GAS BUSTER. BOP DRILL RESPONSE TIME= 90 SECONDS.
YUKON A 1H | 5 | 2020-11-10 19:00 | 2020-11-10 19:30 | 0.5 | P | SFHLCSG | TEST | LOTFIT | LOT / FIT | 1.71 | 3180 | 3180 | 0 | PERFORM F.I.T.WITH 9.1 PPG MUD, 406 PSI SURFACE PRESSURE FOR 11.6 PPG EMW, SHOE MD-3,156' TVD-3,121'
YUKON A 1H | 5 | 2020-11-10 19:30 | 2020-11-11 04:30 | 9 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.08 | 3180 | 7208 | 447.6 | ROT (4028' IN 9.07 HRS @ 444 FPH) WOB: 35/45K, SPM: 93/93/93, GPM: 900, MMRPM: 149, RPM: 80, TRPM: 229, TRQ: 11K/16K, SPP: 4600/5700 PSI, DIFF: 700/1100 PSI.
YUKON A 1H | 5 | 2020-11-11 04:30 | 2020-11-11 06:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.15 | 7208 | 7376 | 112 | SLIDE (168' IN 1.43 HRS @ 117 FPH) WOB: 10/20K, SPM: 93/93/93, GPM: 900, MMRPM: 149, SPP: 4600/5000 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/3333 T/3349 16' TF-HS 1945-1952 SLD F/3900 T/3918 18' TF-160R 2050-2100 SLD F/4182 T/4200 18' TF-160R 2126-2133 SLD F/4275 T/4293 18' TF-160R 2141-2148 SLD F/4462 T/4480 18' TF-160R 2206-2216 SLD F/4558 T/4576 18' TF-160R 2222-2230 SLD F/4652 T/4668 16' TF-90M 2238-2246 SLD F/4940 T/4956 16' TF-250M 2323-2332 SLD F/5503 T/5517 14' TF-60M 0052-103 SLD F/5971 T/5987 16' TF-120M 218-227
YUKON A 1H | 6 | 2020-11-11 06:00 | 2020-11-11 14:30 | 8.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.5 | 7376 | 9125 | 205.8 | ROT (1749' IN 8.63 HRS @ 202 FPH) WOB: 35/45K, SPM: 93/93/93, GPM: 900, MMRPM: 149, RPM: 80, TRPM: 229, TRQ: 11K/16K, SPP: 4600/5700 PSI, DIFF: 700/1100 PSI.
YUKON A 1H | 6 | 2020-11-11 14:30 | 2020-11-11 17:30 | 3 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.63 | 9125 | 9255 | 43.3 | SLIDE (130' IN 2.87 HRS @ 45 FPH) WOB: 10/20K, SPM: 93/93/93, GPM: 900, MMRPM: 149, SPP: 4600/5000 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/7752-T/7762,10'TF-100M,840-856 SLD F/7846-T/7866 20' TF-170M, 930-T/1000 SLD F/7945-T/7962,17' TF-150M,1035-T/1050 SLD 8034-T/8059,25',TF-100M,1120-T/1155 SLD F/8412-T/8427,15',TF-0M 1310-T/1334 SLD F/8704-T/8729,25'TF-70M,1435-T/1506 SLD F/9161-T/9179,18',TF-150M,1642-T/1703
YUKON A 1H | 6 | 2020-11-11 17:30 | 2020-11-11 18:00 | 0.5 | P | INTHL | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 2.65 | 9255 | 9255 | 0 | RIG SERVICE
YUKON A 1H | 6 | 2020-11-11 18:00 | 2020-11-11 21:00 | 3 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.77 | 9255 | 10118 | 287.7 | ROT (863' IN 3.15 HRS @ 274 FPH) WOB: 35/45K, SPM: 93/93/93, GPM: 900, MMRPM: 149, RPM: 80, TRPM: 229, TRQ: 11K/16K, SPP: 4600/5700 PSI, DIFF: 700/1100 PSI. START INTERMEDIATE CURVE SECTION ON 11/11/2020 @ 21:00 (10,118' MD / 10,061'TVD)
YUKON A 1H | 6 | 2020-11-11 21:00 | 2020-11-11 23:00 | 2 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.85 | 10118 | 10222 | 52 | SLIDE (104' IN 1.93 HRS @ 54 FPH) WOB: 10/20K, SPM: 90/90/90, GPM: 866, MMRPM: 144, SPP: 4900/5300 PSI, DIFF: 200/400 PSI. SLIDE DEPTHS: SLD F/10118 T/10178 TF-320 60' MIN-66 2109-2215 SLD F/10215 T/10259 TF-320 44' MIN-50 2234-2324
YUKON A 1H | 6 | 2020-11-11 23:00 | 2020-11-11 23:30 | 0.5 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 2.88 | 10222 | 10259 | 74 | ROT (37' IN .32 HRS @ 116 FPH) WOB: 35/45K, SPM: 90/90/90, GPM: 866, MMRPM: 144, RPM: 80, TRPM: 224, TRQ: 11K/16K, SPP: 4900/5900 PSI, DIFF: 700/1100 PSI
YUKON A 1H | 6 | 2020-11-11 23:30 | 2020-11-12 01:00 | 1.5 | P | INTHL | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 2.94 | 10259 | 10357 | 65.3 | SLIDE (98' IN 1.68 HRS @ 58 FPH) WOB: 10/20K, SPM: 105/0/105, GPM: 674, MMRPM: 112, SPP: 3200/3600 PSI, DIFF: 200/400 PSI. NOTE: DRILLING @ REDUCED GPM DUE TO WASHED 4" VALVE ON #2 MUD PUMP SLIDE DEPTHS: SLD F/10308 T/10336 TF-10R 28' MIN-27 0008-0035 SLD F/10385 T/10439 TF-HS 54' MIN-49 0058-0147 SLD F/10512 T/10528 TF-HS 16' MIN-25 0235-0300
YUKON A 1H | 6 | 2020-11-12 01:00 | 2020-11-12 03:00 | 2 | P | INTHL | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 3.02 | 10357 | 10528 | 85.5 | ROT (171' IN 1.92 HRS @ 89 FPH) WOB: 35/45K, SPM: 105/0/105, GPM: 674, MMRPM: 112, RPM: 80, TRPM: 192, TRQ: 11K/16K, SPP: 3200/4200 PSI, DIFF: 700/1000 PSI NOTE: DRILLING @ REDUCED GPM DUE TO WASHED 4" VALVE ON #2 MUD PUMP
YUKON A 1H | 6 | 2020-11-12 03:00 | 2020-11-12 05:30 | 2.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 3.13 | 10528 | 10528 | 0 | PUMP 30 BBL LCM SWEEP, CIRCULATE HOLE CLEAN AND RECIPROCATE PIPE, GPM: 674, RPM: 40, TRQ: 5K/8K, SPP: 3200 PSI, FLOW CHECK WELL, WELL STATIC, PUMP SLUG
YUKON A 1H | 6 | 2020-11-12 05:30 | 2020-11-12 06:00 | 0.5 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.15 | 10528 | 10528 | 0 | POOH 5 STANDS AND LAY DOWN DRILL PIPE F/10,099' T/9,800'
YUKON A 1H | 7 | 2020-11-12 06:00 | 2020-11-12 12:00 | 6 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.4 | 10528 | 10528 | 0 | L/D 5" DRILL PIPE F/9,800' T/2,700'. HOLE TAKING MORE THAN CALCULATED FILL.
YUKON A 1H | 7 | 2020-11-12 12:00 | 2020-11-12 12:30 | 0.5 | P | INTHLCSG | TRIP | PHDNIP | PULL ROT HEAD / INSTALL TRIP NIPPLE | 3.42 | 10528 | 10528 | 0 | REMOVE ROTATING HEAD AND INSTALL TRIP NIPPLE.
YUKON A 1H | 7 | 2020-11-12 12:30 | 2020-11-12 14:30 | 2 | P | INTHLCSG | TRIP | LDDP | LAY DOWN DRILLPIPE | 3.5 | 10528 | 10528 | 0 | L/D AGITATOR AND 5" DRILL PIPE F/2,700' T/BHA. HOLE TAKING MORE THAN CALCULATED FILL.
YUKON A 1H | 7 | 2020-11-12 14:30 | 2020-11-12 17:00 | 2.5 | P | INTHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 3.6 | 10528 | 10528 | 0 | L/D HWDP, 6" DRILL COLLARS, TOP MONEL, REMOVE MWD, DRAIN MOTOR, BREAK BIT, L/D MOTOR AND MONEL. HOLE TOOK APPROXIMATELY 70 BBLS MORE THAN CALCULATED FILL DURING ENTIRE TRIP F/10,528' T/0'.
YUKON A 1H | 7 | 2020-11-12 17:00 | 2020-11-12 17:30 | 0.5 | P | INTHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 3.63 | 10528 | 10528 | 0 | REMOVE WEAR BUSHING AND CLEAN RIG FLOOR.
YUKON A 1H | 7 | 2020-11-12 17:30 | 2020-11-12 18:00 | 0.5 | P | INTHLCSG | RIGMT | SVCRTY | SERVICE ROTARY / TOP DRIIVE | 3.65 | 10528 | 10528 | 0 | SERVICED TOP DRIVE
YUKON A 1H | 7 | 2020-11-12 18:00 | 2020-11-12 20:00 | 2 | P | INTHLCSG | BOP | COBOP | CHANGE OUT BOP | 3.73 | 10528 | 10528 | 0 | REMOVE TOP VBR PIPE RAMS AND INSTALL 7-5/8" CASING RAMS
YUKON A 1H | 7 | 2020-11-12 20:00 | 2020-11-12 21:00 | 1 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 3.77 | 10528 | 10528 | 0 | PICKED UP TEST JOINT & INSTALLED TEST PLUG, TESTED RAMS, LAYED DOWN TEST PLUG & JOINT
YUKON A 1H | 7 | 2020-11-12 21:00 | 2020-11-12 22:30 | 1.5 | P | INTHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 3.83 | 10528 | 10528 | 0 | RIGGED UP FRANKS INTERNATIONAL CASING CREW TOOLS & EQUIPMENT TO RUN INTERMEDIATE CASING
YUKON A 1H | 7 | 2020-11-12 22:30 | 2020-11-13 06:00 | 7.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.15 | 10528 | 10528 | 0 | RUN 7-5/8" CASING T/9,000' HELD PJSM, PICKED UP, MADE UP & TESTED SHOE TRACK, THEN RAN INTERMEDIATE CASING AS FOLLOWS: 1-INNOVEX FLOAT SHOE, 2-JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, 1-INNOVEX FLOAT COLLAR, THEN RAN 240 JTS OF 7 5/8" 29.7# P-110 HC ERW BTC CSG, FILLED PIPE ON THE FLY, HOLE GIVING PROPER DISPLACEMENT, INSTALLED 46 LATCH ON BOW SPRING CENTRALIZERS 1ST AT 10' FROM SHOE, ON 2ND & 3RD JT, THEN EVERY 4TH JT UP TO 3,032'. FLOAT SHOE-10,517.17' TOP OF FLOAT COLLAR-10,428.85' 7 JOINTS LEFT OUT- 297.22'
YUKON A 1H | 8 | 2020-11-13 06:00 | 2020-11-13 07:30 | 1.5 | P | INTHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 4.21 | 10528 | 10528 | 0 | RUN 7-5/8" CASING F/9,000' T/10,483'. P/U LANDING JOINT & LAND CSG ON CSG MANDREL W/230K (W/O BLOCKS). FLOAT SHOE-10,517.17' TOP OF FLOAT COLLAR-10,428.85' 7 JOINTS LEFT OUT- 297.22'
YUKON A 1H | 8 | 2020-11-13 07:30 | 2020-11-13 08:00 | 0.5 | P | INTHLCSG | CMT | RUCMEQ | RIG UP CEMENT CREW / EQUIP | 4.23 | 10528 | 10528 | 0 | HELD PJSM, RIG DOWN CRT, RIG UP NINE ENERGY CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE MANIFOLD.
YUKON A 1H | 8 | 2020-11-13 08:00 | 2020-11-13 09:30 | 1.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.29 | 10528 | 10528 | 0 | CIRCULATE CSG CAPACITY WITH RIG PUMPS THROUGH CEMENT HEAD WHILE RIGGING DOWN CSG EQUIPMENT, SPM: 108, 6.8 BPM, SPP: 350 PSI, NO LOSSES
YUKON A 1H | 8 | 2020-11-13 09:30 | 2020-11-13 12:00 | 2.5 | U | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 4.4 | 10528 | 10528 | 0 | CIRCULATING WHILE WAITING ON NINE ENERGY CEMENT SPACER. SPM:90, BPM:5.6, PP:260, NO LOSSES
YUKON A 1H | 8 | 2020-11-13 12:00 | 2020-11-13 14:30 | 2.5 | P | INTHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 4.5 | 10528 | 10528 | 0 | CEMENTED INTERMEDIATE SECTION WITH NINE ENERGY SERVICES: 40 BBL 10.5 PPG GTX SPACER. 293 BBL 11.8 PPG 850 SK 1.94 YIELD 50/50 POZ-SM-CLASS H-MM LEAD CEMENT 78 BBL 16.2 PPG 305 SK 1.44 YIELD CLASS H TAIL CEMENT. FLUSHED THRU ALL LINES, DROPPED AND WITNESSED PLUG DROP, DISPLACED WITH 479 BBLS OF 9.0 PPG OIL BASE MUD @ 8 BPM, SLOWED PUMP RATE TO 4 BPM, FINAL LIFT PRESSURE WAS 2200 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 2800 PSI, HELD FOR 5 MIN, BLED OFF PRESSURE AND BLED BACK 6 BBLS. FLOATS HELD. PLUG DOWN @ 14:30 HRS ON 11/13/2020, GOT BACK 15 BBLS OF SPACER AND 0 BBLS OF LEAD CMT BACK TO SURFACE & HAD FULL RETURNS ENTIRE CEMENTING JOB. TOC @ 3150'.
YUKON A 1H | 8 | 2020-11-13 14:30 | 2020-11-13 15:00 | 0.5 | P | INTHLCSG | TEST | PSRTST | PRESSURE TEST | 4.52 | 10528 | 10528 | 0 | TEST CASING TO 3500 PSI, GOOD TEST
YUKON A 1H | 8 | 2020-11-13 15:00 | 2020-11-13 15:30 | 0.5 | P | INTHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 4.54 | 10528 | 10528 | 0 | RIG DOWN CEMENT TOOLS AND HEAD, FLUSH LINES AND BOP
YUKON A 1H | 8 | 2020-11-13 15:30 | 2020-11-13 17:30 | 2 | P | INTHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 4.63 | 10528 | 10528 | 0 | MAKE UP STREAM FLO WASHOUT TOOL FOR WELLHEAD, RAN DOWN INTO STACK AND WELLHEAD, WASHED OUT AND FLUSHED OUT WELLHEAD, PULLED OUT WASHOUT TOOL AND LAID DOWN SAME, PICKED UP AND MADE UP PACK OFF, RIH WITH PACK-OFF AND INSTALLED SAME, TESTED PACK-OFF TO 10K PSI, PULL TESTED PACK-OFF TO 5K, BROKE OUT & LAID DOWN SETTING TOOL.
YUKON A 1H | 8 | 2020-11-13 17:30 | 2020-11-13 21:30 | 4 | P | INTHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 4.79 | 10528 | 10528 | 0 | REMOVE 4.5 IF SAVER SUB AND INSTALL DS42 SAVER SUB. DS42 SAVER SUB WAS DAMAGED WHILE MAKING UP INTO TIW. REMOVE DAMAGED SAVER SUB AND INSTALL NEW. TESTING CHOKE MANIFOLD AND SUPER CHOKES WHILE CHANGING SAVER SUB.
YUKON A 1H | 8 | 2020-11-13 21:30 | 2020-11-14 | 2.5 | P | INTHLCSG | BOP | COBOP | CHANGE OUT BOP | 4.9 | 10528 | 10528 | 0 | REMOVE 7-5/8" CASING RAMS AND INSTALL 3.5"-5.5" VBR PIPE RAMS.
YUKON A 1H | 8 | 2020-11-14 | 2020-11-14 06:00 | 6 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.15 | 10528 | 10528 | 0 | TESTED BOPE: TEST CHOKE MANIFOLD MANUAL VALVES, SUPERCHOKES, TEST BLIND RAMS. TEST 4-1/2" AND 5-1/2" DP LOWER PIPE RAMS, 4-1/2" AND 5-1/2" UPPER PIPE RAMS, MUD CROSS, KILL LINE MANUAL VALVES, CHOKE LINE MANUAL VALVE, HCR, MANUAL IBOP, TIW, INSIDE GREY AND WELLHEAD 250 LOW / 10,000 HIGH, TEST KILL LINE BACK TO PUMPS 250 LOW / 5,000 HIGH, TEST BACK TO MUD PUMPS THROUGH STAND PIPE 250 LOW / 5000 HIGH, TEST HYDRIL 250 LOW / 3500 HIGH. INSTALL KILL LINE CHECK VALVE AND TEST 250 LOW / 10,000 HIGH. INSTALL WEATHERFORD TEST CAP AND TEST TO 1500 PSI.
YUKON A 1H | 9 | 2020-11-14 06:00 | 2020-11-14 07:00 | 1 | P | INTHLCSG | BOP | TSTBOP | PRESSURE TEST BOP | 5.19 | 10528 | 10528 | 0 | FINISH TESTING BOPE: TEST KILL LINE BACK TO PUMPS T/250 LOW/ 5,000 HIGH, TEST BLIND RAMS AND KILL LINE CHECK VALVE TO 250 LOW / 10,000 HIGH. TEST ROT HEAD AND ORBIT VALVE 250 LOW / 1500 HIGH. RIG DOWN TESTERS
YUKON A 1H | 9 | 2020-11-14 07:00 | 2020-11-14 07:30 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.21 | 10528 | 10528 | 0 | REMOVE TEST PLUG AND INSTALL WEAR BUSHING.
YUKON A 1H | 9 | 2020-11-14 07:30 | 2020-11-14 08:30 | 1 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.25 | 10528 | 10528 | 0 | CHANGE OUT ELEVATORS, CLEAN RIG FLOOR, AND CHANGE OUT DIES IN ST-80
YUKON A 1H | 9 | 2020-11-14 08:30 | 2020-11-14 10:00 | 1.5 | P | INTHLCSG | TRIP | PUBHA | PICK UP BIT / BHA | 5.31 | 10528 | 10528 | 0 | PICK UP 6.75" SECURITY GTD64M SER 13509567: JETS 6/18S TFA: 1.491), 5", 6/7L, 8.8 STG @ 2.12° SLICK; .68 REV/GAL; 4.08' BIT TO BEND 5-5/8" PAD OD; FLOW RANGE- 150/400 GPM; MAX DIFF-2,240 PSI; STALL TRQ-12,000 FT/LBS; BTI VALVE, 5" NMPDC, 5" UBHO, 5" NMDC, 5" NMDC, THRUSTER, X/O XT-39 P x DS 42 B, 27 STANDS, AGITATOR. BIT TO SVY-69'. BIT TO GAMMA-59', TEST MWD (TEST GOOD)
YUKON A 1H | 9 | 2020-11-14 10:00 | 2020-11-14 18:00 | 8 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.65 | 10528 | 10528 | 0 | PICK UP DRILL PIPE F/141' T/5,861'. PROPER DISPLACEMENTS ON TRIP IN. PICK UP AGITATOR AFTER STAND 27. BEFORE AGITATOR: GPM-300, PP-1400. AFTER AGITATOR: PP-1650
YUKON A 1H | 9 | 2020-11-14 18:00 | 2020-11-14 18:30 | 0.5 | P | INTHLCSG | RURD | RUEQP | RIG UP EQUIPMENT | 5.67 | 10528 | 10528 | 0 | PERFORM FLOW CHECK @ TOUR CHANGE. MOVE, STRAP, AND TALLY DRILL PIPE.
YUKON A 1H | 9 | 2020-11-14 18:30 | 2020-11-14 21:00 | 2.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.77 | 10528 | 10528 | 0 | PICK UP DRILL PIPE F/5,861' T/8,630'. PROPER DISPLACEMENTS ON TRIP IN.
YUKON A 1H | 9 | 2020-11-14 21:00 | 2020-11-14 21:30 | 0.5 | P | INTHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 5.79 | 10528 | 10528 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
YUKON A 1H | 9 | 2020-11-14 21:30 | 2020-11-14 23:00 | 1.5 | P | INTHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 5.85 | 10528 | 10528 | 0 | CUT/SLIP DRILL LINE(10 WRAPS) AND CALIBRATE BLOCKS.
YUKON A 1H | 9 | 2020-11-14 23:00 | 2020-11-15 | 1 | P | INTHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 5.9 | 10528 | 10528 | 0 | RIG SERVICE
YUKON A 1H | 9 | 2020-11-15 | 2020-11-15 01:30 | 1.5 | P | INTHLCSG | TRIP | PUDP | PICK UP DRILLPIPE | 5.96 | 10528 | 10528 | 0 | PICK UP DRILL PIPE F/8,630' T/10,330'. PROPER DISPLACEMENTS ON TRIP IN.
YUKON A 1H | 9 | 2020-11-15 01:30 | 2020-11-15 02:30 | 1 | P | INTHLCSG | DLOUT | DRLFM | DRILL NEW FORMATION FOR FIT | 6 | 10528 | 10538 | 10 | TAG FLOAT COLLAR @ 10,428'. DRILL OUT FLOAT EQUIPMENT AND 10' NEW FORMATION. GPM-224, PP-1650 PSI, RPM-40, TQ-(8-10K)
YUKON A 1H | 9 | 2020-11-15 02:30 | 2020-11-15 03:00 | 0.5 | P | INTHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 6.02 | 10538 | 10538 | 0 | CIRCULATE BOTTOMS UP. GPM-320, PP-1278, RPM-40. CIRCULATE 9.5 MW AROUND.
YUKON A 1H | 9 | 2020-11-15 03:00 | 2020-11-15 03:30 | 0.5 | P | INTHLCSG | TEST | LOTFIT | LOT / FIT | 6.04 | 10538 | 10538 | 0 | PERFORMED F.I.T @ (10,517’ MD / 10,453’ TVD) W/9.5 PPG T/1902 PSI EMW = 13 PPG
YUKON A 1H | 9 | 2020-11-15 03:30 | 2020-11-15 05:30 | 2 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.13 | 10538 | 10663 | 62.5 | S/D (125' IN 1.83 HRS @ 68 FPH) WOB-5/20K, SPM-66/66, GPM-350, MRPM-238, SPP-2900/3400 PSI, DIFF-400/500 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0', NO LOSSES SLIDE DEPTHS: F/10538' T/10598' @ HS 60' 0330-0425, 55 MIN F/10620' T/10685' @ HS 65' 0450-0425, 55 MIN
YUKON A 1H | 9 | 2020-11-15 03:30 | 2020-11-15 03:30 | 0 | P | PRDHLCV | MSTN | SCRV | MILESTONE_START CURVE SECTION | 6.04 | 10538 | 10538 |  | MILESTONE_START CURVE SECTION ON 11/15/2020 @ 03:30 HRS
YUKON A 1H | 9 | 2020-11-15 05:30 | 2020-11-15 06:00 | 0.5 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.15 | 10663 | 10712 | 98 | ROT (49' IN .68 HRS @ 86 FPH) WOB: 15/20K, SPM: 66/66, GPM: 350, MMRPM: 238, RPM: 40, TRPM: 278, TRQ: 6K/9K, SPP: 2900/3900 PSI, DIFF: 800/1000 PSI.
YUKON A 1H | 10 | 2020-11-15 06:00 | 2020-11-15 12:00 | 6 | P | PRDHLCV | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.4 | 10712 | 11121 | 68.2 | S/D (409' IN 5.9 HRS @ 69 FPH) WOB-15/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3500/4000 PSI, DIFF-400/500 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' NO LOSSES SLIDE DEPTHS: SLD F/10732-T/10890-TF-HS, 0616-0817 (158FT.) 61MIN SLD F/10952-T/10996 TF-30L, (44') 846-T/934 48MIN SLD F/11056-T/11091 TF-20L, (35), 957-T/1033 36MIN SLD F/11158-T/11186 TF-HS, (28) , 1056-T/1133 37MIN SLD F/11233-T/11377 TF-HS, (144) 1148-T/1340 112MIN
YUKON A 1H | 10 | 2020-11-15 12:00 | 2020-11-15 14:00 | 2 | P | PRDHLCV | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.48 | 11121 | 11472 | 175.5 | ROT (351' IN 2.1 HRS @ 150 FPH) WOB: 25/40K, SPM: 76/76, GPM: 400, MMRPM: 272, RPM: 40, TRPM: 312, TRQ: 8K/10K, SPP: 3500/4300 PSI, DIFF: 700/800 PSI.
YUKON A 1H | 10 | 2020-11-15 14:00 | 2020-11-15 14:00 | 0 | P | PRDHLCV | MSTN | LCRV | MILESTONE_LAND/END CURVE SECTION | 6.48 | 11472 | 11472 |  | MILESTONE_LAND/END CURVE SECTION ON 11/15/2020 @ 14:00
YUKON A 1H | 10 | 2020-11-15 14:00 | 2020-11-15 14:00 | 0 | P | PRDHLLT | MSTN | SLAT | MILESTONE_START HORIZONTAL LATERAL SECTION | 6.48 | 11472 | 11472 |  | MILESTONE_START HORIZONTAL LATERAL SECTION ON 11/15/2020 @ 14:00
YUKON A 1H | 10 | 2020-11-15 14:00 | 2020-11-15 16:00 | 2 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.56 | 11472 | 11890 | 209 | ROT (418' IN 1.92 HRS @ 217 FPH) WOB: 25/40K, SPM: 76/76, GPM: 400, MMRPM: 272, RPM: 80, TRPM: 352, TRQ: 10K/13K, SPP: 3500/4500 PSI, DIFF: 800/1000 PSI.
YUKON A 1H | 10 | 2020-11-15 16:00 | 2020-11-15 17:00 | 1 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 6.6 | 11890 | 11945 | 55 | S/D (55' IN 1.08 HRS @ 51 FPH) WOB-15/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3500/4000 PSI, DIFF-400/500 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' SLIDE DEPTHS: SLD F/11472-T/11517 TF-140L (44') 1415-T/1452 37MIN SLD F/11860-T/11870 TF-HS, (10') 1640-T/1653 13MIN
YUKON A 1H | 10 | 2020-11-15 17:00 | 2020-11-15 17:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 6.63 | 11945 | 11945 | 0 | RIG SERVICE
YUKON A 1H | 10 | 2020-11-15 17:30 | 2020-11-16 01:30 | 8 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 6.96 | 11945 | 13621 | 209.5 | ROT (1676' IN 8.08 HRS @ 207 FPH) WOB: 25/40K, SPM: 76/76, GPM: 400, MMRPM: 272, RPM: 40, TRPM: 312, TRQ: 8K/10K, SPP: 3800/4800 PSI, DIFF: 800/1000 PSI.
YUKON A 1H | 10 | 2020-11-16 01:30 | 2020-11-16 06:00 | 4.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.15 | 13621 | 13768 | 32.7 | S/D (147' IN 4.42 HRS @ 33 FPH) WOB-15/50K, SPM-76/76, GPM-400, MRPM-272, SPP-3800/4200 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-2 FULL OPEN, FLARE-0' SLIDE DEPTHS: SLD F/11957 T/11967 TF-180 10' MIN-10 1800-1810 SLD F/12039 T/12054 TF-180 15' MIN-23 1832-1855 SLD F/12420 T/12438 TF-140L 18' MIN-23 2048-2011 SLD F/12605 T/12617 TF-60L 12' MIN-18 2154-2212 SLD F/12987 T/13005 TF-180 18' MIN-35 2350-0025 SLD F/13083 T/13099 TF-150R 16' MIN-45 0046-0131 SLD F/13368 T/13386 TF-180 18' MIN-38 0252-0330 SLD F/13558 T/13573 TF-180 15' MIN-38 0413-0451 SLD F/13748 T/13768 TF-180 15' MIN-27 0533-0600
YUKON A 1H | 11 | 2020-11-16 06:00 | 2020-11-16 13:30 | 7.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.46 | 13768 | 15024 | 167.5 | ROT (1256' IN 7.38 HRS @ 170 FPH) WOB: 25/40K, SPM: 76/76, GPM: 400, MMRPM: 272, RPM: 80, TRPM: 352, TRQ: 14K/17K, SPP: 3900/5100 PSI, DIFF: 1000/1200 PSI. CSG PSI WHILE DRILLING-(0 PSI) SICP ON CONNECTIONS-(100-250 PSI)
YUKON A 1H | 11 | 2020-11-16 13:30 | 2020-11-16 17:00 | 3.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 7.6 | 15024 | 15077 | 15.1 | S/D (53' IN 3.62 HRS @ 15 FPH) WOB-15/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3900/4300 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-1 FULL OPEN, FLARE-0' NO LOSSES SLIDE DEPTHS: SLD F/13947-T/13965,TF-180,18',MIN-72, 656-T/808 SLD F/14327-T/14352,TF-150R,25,MIN-72 1008-T/1120 SLD F/14800-T/14810,TF-180,10',73-MIN,1420-T/1533
YUKON A 1H | 11 | 2020-11-16 17:00 | 2020-11-16 17:30 | 0.5 | U | PRDHLLT | SPROB | SFEQP | SURFACE EQUIPMENT FAILURE | 7.63 | 15077 | 15077 | 0 | REPAIR FLARE LINE IGNITER (NOT IGNITING)
YUKON A 1H | 11 | 2020-11-16 17:30 | 2020-11-16 19:30 | 2 | U | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 7.71 | 15077 | 15077 | 0 | UNABLE TO PERFORM EFFICIENT SLIDES. PERFORM "MINI" CLEAN UP CYCLE. BACKREAM T/14,032' AND WASH BACK TO BOTTOM. GPM-400, PP-3800, RPM-60, TQ-8-10K. CSG PSI WHILE REAMING-(0 PSI) SICP ON CONNECTIONS-(100-300 PSI)
YUKON A 1H | 11 | 2020-11-16 19:30 | 2020-11-17 | 4.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 7.9 | 15077 | 15882 | 178.9 | ROT (805' IN 4.67 HRS @ 172 FPH) WOB: 25/40K, SPM: 76/76, GPM: 400, MMRPM: 272, RPM: 80, TRPM: 352, TRQ: 14K/17K, SPP: 3900/5100 PSI, DIFF: 1000/1200 PSI. CSG PSI WHILE DRILLING-(0 PSI) SICP ON CONNECTIONS-(100-250 PSI)
YUKON A 1H | 11 | 2020-11-17 | 2020-11-17 05:00 | 5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.1 | 15882 | 15939 | 11.4 | S/D (57' IN 4.8 HRS @ 12 FPH) WOB-15/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3900/4300 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-1 FULL OPEN, FLARE-0' NO LOSSES SLIDE DEPTHS: SLD F/15077 T/15102 TF-180 74' MIN-74 1936-2050 SLD F/15174 T/15188 TF-180 50' MIN-50 2116-2206 SLD F/15658 T/15676 TF-HS 18' MIN-160 0045-0325
YUKON A 1H | 11 | 2020-11-17 05:00 | 2020-11-17 05:30 | 0.5 | P | PRDHLLT | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 8.13 | 15939 | 15939 | 0 | RIG SERVICE
YUKON A 1H | 11 | 2020-11-17 05:30 | 2020-11-17 06:00 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.15 | 15939 | 15939 | 0 | PUMP 30 BBLS SWEEP AND CIRC OUT OF LATERAL TO CLEAN UP HOLE FOR ANTICIPATED SLIDE. GPM-400, PP-3800, RPM-80, TQ-8-10K.
YUKON A 1H | 12 | 2020-11-17 06:00 | 2020-11-17 06:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.17 | 15939 | 15939 | 0 | PUMP 30 BBLS SWEEP AND CIRC OUT OF LATERAL TO CLEAN UP HOLE FOR ANTICIPATED SLIDE. GPM-400, PP-3800, RPM-80, TQ-8-10K.
YUKON A 1H | 12 | 2020-11-17 06:30 | 2020-11-17 08:00 | 1.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.23 | 15939 | 15948 | 6 | S/D (9' IN 1.5 HRS @ 6 FPH) WOB-15/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3900/4300 PSI, DIFF-200/400 PSI, CP-0 PSI, CHOKE-1 FULL OPEN, FLARE-0' NO LOSSES SLIDE DEPTHS: SLD F/15939 T/15948 TF-HS 9' MIN-90 0630-0800 CSG PSI WHILE DRILLING-(0 PSI) SICP ON CONNECTIONS-(300-400 PSI)
YUKON A 1H | 12 | 2020-11-17 08:00 | 2020-11-17 08:30 | 0.5 | P | PRDHLLT | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.25 | 15948 | 15948 | 0 | CIRCULATE WHILE PREPARING TO BACKREAM 10 STANDS. RACK BACK MOUSEHOLE STAND IN DERRICK.. GPM-400, PP-3900, RPM-80, TQ-(8-14K) CSG PSI WHILE CIRC-0 PSI
YUKON A 1H | 12 | 2020-11-17 08:30 | 2020-11-17 11:00 | 2.5 | P | PRDHLLT | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.35 | 15948 | 15948 | 0 | UNABLE TO PERFORM EFFICIENT SLIDES. PERFORM "MINI" CLEAN UP CYCLE. BACKREAM T/14,977' AND WASH BACK TO BOTTOM. GPM-400, PP-3900, RPM-80, TQ-8-16K. CSG PSI WHILE REAMING-(0 PSI) SICP ON CONNECTIONS-(100-350 PSI)
YUKON A 1H | 12 | 2020-11-17 11:00 | 2020-11-17 13:30 | 2.5 | P | PRDHLLT | DRLG | DRSLD | DRILLING DIRECTIONAL - SLIDING | 8.46 | 15948 | 15965 | 6.8 | S/D (17' IN 2.28 HRS @ 7.5 FPH) WOB-15/40K, SPM-76/76, GPM-400, MRPM-272, SPP-3900/4000 PSI, DIFF-50/200 PSI, CP-0 PSI, CHOKE-1 FULL OPEN, FLARE-2-5' NO LOSSES SLIDE DEPTHS: SLD F/15948 T/15959 TF-180 11' MIN-90 1100-1230 SLD F/16035 T/16041 TF-180 6' MIN-47 1313-1400
YUKON A 1H | 12 | 2020-11-17 13:30 | 2020-11-17 14:00 | 0.5 | P | PRDHLLT | DRLG | DRRT | DRILLING DIRECTIONAL - ROTATING | 8.48 | 15965 | 16041 | 152 | ROT (76' IN .72 HRS @ 106 FPH) WOB: 25/40K, SPM: 76/76, GPM: 400, MMRPM: 272, RPM: 80, TRPM: 352, TRQ: 14K/19K, SPP: 3900/5100 PSI, DIFF: 1000/1200 PSI. CSG PSI WHILE DRILLING-(0 PSI) SICP ON CONNECTIONS-(450 PSI)
YUKON A 1H | 12 | 2020-11-17 14:00 | 2020-11-17 14:00 | 0 | P | PRDHLLT | MSTN | TD | MILESTONE_TD WELL | 8.48 | 16041 | 16041 |  | MILESTONE_TD WELL ON 11/17/2020 @ 14:00
YUKON A 1H | 12 | 2020-11-17 14:00 | 2020-11-17 15:00 | 1 | U | PRDHLCSG | WSHRM | TGTRM | TIGHT HOLE WASH AND REAM | 8.52 | 16041 | 16041 | 0 | HOLE BEGAN PACKING OFF WHILE SLIDING. BACKREAM OUT OF HOLE T/15,842'. P/U 1 STAND AND CIRC @ 15,950'. GR SPIKE F/ 55 (AVE) TO 89 UNITS OCCURRED AT APPR 15,913', THEN GR DROPPED TO 40, THEN 29 UNITS, BEFORE BEGINNING TO SPIKE UP AGAIN (112 AT 15,960' AND 276 AT 15,967'). LAST GR WAS 273 AT 15,982' WITH BIT DEPTH AT 16,041'. GR OFFSET TO BIT WAS 59'. MAX GR SEEN WAS 290 UNITS. HIGH GR INTERVAL OCCURRED ON LOG F/ 25,960-982' (22'), WITH ANOTHER 59' POTENTIAL UNSEEN TO 16,041' BIT DEPTH. MUD LOGGERS DOCUMENTED ASH F/ 15,950' TO TD. ASH 60% AT TD.
YUKON A 1H | 12 | 2020-11-17 15:00 | 2020-11-17 21:00 | 6 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 8.77 | 16041 | 16041 | 0 | PERFORMED CLEAN UP CYCLE FOR CASING RUN PUMPING 3-20 BBL 30 PPB LCM SWEEPS CONDITION MUD & CIRCULATE 4 B/U, RPM-60, SPM: 136, GPM-350, MAX GAS: 1000u. MAX CSG PSI WHILE CIRC-0 PSI WEIGHTING UP F/9.3PPG T/10.5 PPG. MUD BEGAN SEEPING @ 10.0 PPG. DECISION WAS MADE TO HOLD MUD WEIGHT AT 10.0 PPG. 1ST BTM UP START TQ=6-12K, END= 6-12K, PP-3250 PSI, P/UWT=286K 2ND BTM UP END TQ= 7-13K, P/U WT= 295K, PP-3300 3RD BTM UP END TQ= 7-12K, P/U WT= 280K, PP-3550 LOSS OF 0K TORQUE FROM DOING CLEAN UP CYCLE, SHAKERS CLEAN.
YUKON A 1H | 12 | 2020-11-17 21:00 | 2020-11-17 23:30 | 2.5 | P | PRDHLCSG | WSHRM | BKRM | BACKREAM OUT OF HOLE | 8.88 | 16041 | 16041 | 0 | BACKREAM F/15,950 T/14,337'. GPM-360, PP-3000, RPM-60, TQ- (7-11K) CASING PSI WHILE REAMING- 0 PSI CASING PSI DURING CONNECTIONS-(150 INITIALLY AND GRADUALLY REDUCED TO 0 AFTER 3 STANDS.)
YUKON A 1H | 12 | 2020-11-17 23:30 | 2020-11-18 02:00 | 2.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 8.98 | 16041 | 16041 | 0 | STRIP OUT OF HOLE F/14,337', T/10,521'. PUMPING 10.0 PPG OBM CALCUATED FILL DOWN ANNULUS.
YUKON A 1H | 12 | 2020-11-18 02:00 | 2020-11-18 03:00 | 1 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.02 | 16041 | 16041 | 0 | CIRCULATE BOTTOMS UP @ GPM-350, SPP-2850 PSI, CP=0 PSI, FLARE=3-5', MAX GAS-1490u SHUT DOWN MUD PUMPS AND CHECK SICP- 0 PSI OPEN ORBIT VALVE AND PERFORM FLOW CHECK-WELL FLOWING.
YUKON A 1H | 12 | 2020-11-18 03:00 | 2020-11-18 04:00 | 1 | P | PRDHLCSG | WCTRL |  | WELL CONTROL OPERATIONS | 9.06 | 16041 | 16041 | 0 | SPOT 64 BBL 14.5 PPG OBM MUD CAP @ 10,521' (300 PSI OVER BALANCE MUD CAP). SHUT IN AND MONITORED CASING PRESSURE. SICP= BEFORE CAP-0 PSI / AFTER-0 PSI TOP OF MUD CAP-9,127' OPEN ORBIT VALVE AND CHECK FLOW ON FLOWLINE-NO FLOW
YUKON A 1H | 12 | 2020-11-18 04:00 | 2020-11-18 06:00 | 2 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 9.15 | 16041 | 16041 | 0 | TRIP OUT OF HOLE F/10,521' T/6,500'. PROPER FILLS ON TRIP OUT OF HOLE.
YUKON A 1H | 13 | 2020-11-18 06:00 | 2020-11-18 09:30 | 3.5 | P | PRDHLCSG | TRIP | CSG | TRIP FOR CASING / LINER | 9.29 | 16041 | 16041 | 0 | TRIP OUT OF HOLE F/6,000' T/BHA'. PROPER FILLS ON TRIP OUT OF HOLE. REMOVED ROTATING HEAD AND INSTALL TRIP NIPPLE @ 3,000'
YUKON A 1H | 13 | 2020-11-18 09:30 | 2020-11-18 10:30 | 1 | P | PRDHLCSG | TRIP | LDBHA | LAY DOWN BIT / BHA | 9.33 | 16041 | 16041 | 0 | AY DOWN THRUSTER, TOP MONEL, REMOVE MWD, DRAIN MOTOR, AND BREAK BIT. LAY DOWN MOTOR AND MONEL.
YUKON A 1H | 13 | 2020-11-18 10:30 | 2020-11-18 11:00 | 0.5 | P | PRDHLCSG | RURD | RDEQP | RIG DOWN EQUIPMENT | 9.35 | 16041 | 16041 | 0 | REMOVE WEAR BUSHING
YUKON A 1H | 13 | 2020-11-18 11:00 | 2020-11-18 12:00 | 1 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 9.4 | 16041 | 16041 | 0 | RIG SERVICE
YUKON A 1H | 13 | 2020-11-18 12:00 | 2020-11-18 13:30 | 1.5 | P | PRDHLCSG | RIGMT | EXRPLC | EXPENDABLE REPLACEMENT | 9.46 | 16041 | 16041 | 0 | REMOVE SAVER SUB CUT FOR SCREEN AND INSTALL FULL LIP SAVER SUB.
YUKON A 1H | 13 | 2020-11-18 13:30 | 2020-11-18 15:00 | 1.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 9.52 | 16041 | 16041 | 0 | R/U EXPRESS CASING CREW AND EQUIPMENT
YUKON A 1H | 13 | 2020-11-18 15:00 | 2020-11-18 21:00 | 6 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.77 | 16041 | 16041 | 0 | HELD PJSM, CHECK TORQUE ON CASING TONGS, MAKE UP FLOAT EQUIPMENT: INNOVEX DV FLOAT SHOE, 2 JTS 5" 18# P110 ICY WEDGE 625 CASING W/CENTRALIZERS IN MIDDLE OF JTS., 1 INNOVEX DV FLOAT COLLAR, GEODYNAMIC TOE SLEEVE, 1 JT 5" 18# P110 ICY WEDGE 625 CASING AND TEST FLOAT EQUIPMENT. PICK UP AND RUN 5" 18# P110 ICY WEDGE 625 PRODUCTION CASING T/ 6,034', FILLING PIPE ON THE FLY, SOLID BODY CENTALIZERS EVERY 4TH JOINT T/10,373' (SET DEPTH), MONITOR DISPLACEMENTS ON TRIP TANK, FULL DISPLACEMENTS.
YUKON A 1H | 13 | 2020-11-18 21:00 | 2020-11-18 21:30 | 0.5 | P | PRDHLCSG | TRIP | PNPRHD | PULL TRIP NIPPLE / INSTALL ROT HEAD | 9.79 | 16041 | 16041 | 0 | REMOVE TRIP NIPPLE AND INSTALL ROTATING HEAD
YUKON A 1H | 13 | 2020-11-18 21:30 | 2020-11-18 22:00 | 0.5 | P | PRDHLCSG | CSG | RUEQP | RIG UP CASING CREW / EQUIP | 9.81 | 16041 | 16041 | 0 | R/D 5" CRT AND ELEVATORS AND R/U 5.5" CRT AND ELEVATORS.
YUKON A 1H | 13 | 2020-11-18 22:00 | 2020-11-19 01:00 | 3 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 9.94 | 16041 | 16041 | 0 | RUN 5.5" CASING F/6,034' T/10,512'. HOLE GIVING PROPER DISPLACMENTS ON TRIP IN.
YUKON A 1H | 13 | 2020-11-19 01:00 | 2020-11-19 01:30 | 0.5 | P | PRDHLCSG | CIRC | CNDHL | CIRCULATE AND CONDTION HOLE | 9.96 | 16041 | 16041 | 0 | CIRCULATING 1/2 BTMS UP @ 10,506' TO ESTABLISH CIRCULATION. GPM-262, PP-1100 PSI. FULL RETURNS DURING CIRCULATION. HEAVIEST MW SEEN- 10.2 PPG. MAX GAS- 271u
YUKON A 1H | 13 | 2020-11-19 01:30 | 2020-11-19 05:30 | 4 | P | PRDHLCSG | CSG | RNCSG | RUNNING CASING / LINER / TIEBACK | 10.13 | 16041 | 16041 | 0 | RUN 5.5" PRODUCTION CASING F/10,506' T/15,943'. REMOVE ROTATING HEAD, PICK UP LANDING JOINT AND LAND ON HANGER W/130K (W/O BLOCKS) @ 15,943.66. FULL RETURNS DURING CASING RUN T/11,204'. APPROXIMATELY 70% RETURNS F/11,204' T/15,943'. RAN 5" & 5-1/2" PROD CASING AS FOLLOWS: MAKE UP SHOE TRACK: 1-INNOVEX 5'' FLOAT SHOE, 2 JTS OF 5'' CSG. 1-INNOVEX FLOAT COLLAR, 1-GEODYNAMICS TOE SLEEVE VALVE, RAN 6,003.61 (141 JTS) OF 5'' 18# P-110 ICY WEDGE 625 CASING, 1- X-OVER, 1 JOINT 5-1/2" CSG, 1-MKR JT OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING, RAN 9,836.34' (210 JTS) OF 5 1/2" 23# P-110 ICY WEDGE 563 CASING. FOR TOTAL OF 351 FULL JTS OF 5'' 18# P-110 ICY WEDGE 625 & 5.5" 23# P-110 ICY BLUE CASING. CASING SHOE @ 15,943.66' TOP OF FLOAT COLLAR @ 15,853.47' BOTTOM OF TOE SLEEVE VALVE @ 15,853.47' TOP OF TOE SLEEVE VALVE @ 15,827.97 TOP OF X-OVER @ 9,907.06 TOP OF MARKER JOINT ABOVE X-OVER @ 9,839.66'
YUKON A 1H | 13 | 2020-11-19 05:30 | 2020-11-19 06:00 | 0.5 | P | PRDHLCSG | CSG | RDEQP | RIG DOWN CASING CREW / EQUIP | 10.15 | 16041 | 16041 | 0 | RIG DOWN EXPRESS CRT AND INSTALL CEMENTING SWEDGE, CEMENT HEAD AND CIRCULATING IRON TO RIG STANDPIPE
YUKON A 1H | 14 | 2020-11-19 06:00 | 2020-11-19 09:00 | 3 | P | PRDHLCSG | CIRC | CNDFLD | CIRCULATE AND CONDITION FLUID / MUD | 10.27 | 16041 | 16041 | 0 | CIRCULATE CAPACITY OF CASING, WORK PIPE TO GAIN FULL RETURNS, LOST APPROX. 300 BBLS OBM, GPM-275 SPP-1370 MAX GAS 1763u NO CP OR FLARE
YUKON A 1H | 14 | 2020-11-19 09:00 | 2020-11-19 11:30 | 2.5 | P | PRDHLCSG | CMT | PRIM | PRIMARY CEMENT OPERATIONS | 10.38 | 16041 | 16041 | 0 | HELD PJSM, SWAP CEMENT LINE F/ RIG STANDPIPE T/ CEMENT HEAD,FLUSHED THROUGH & TESTED CEMENTING LINES T/8000 PSI, CEMENTED 5/5-1/2" PRODUCTION CASING WITH NINE ENERGY SERVICES: DROP BOTTOM PLUG, PUMPED @ 6 BPM 50 BBL 12.5 PPG WEIGHTED SPACER, 229 BBL 13.5 PPG 775 SK 1.66 YIELD 35/65 POZ-SM-CLASS H-MM TAIL CEMENT. FLUSHED THRU ALL LINES, DROP TOP PLUG, DISPLACED WITH 20 BBLS OF SUGAR WATER FOLLOWED BY 296 BBLS OF FRESH WATER WITH BIOCIDE @ 7 BPM, OBSERVED 100% RETURNS SLOWED PUMP RATE TO 3.5 BPM, FINAL LIFT PRESSURE WAS 3000 PSI, BUMPED PLUG AS CALCULATED, TOOK PRESSURE TO 4000 PSI, HELD FOR 5 MIN, BLED BACK 4.5 BBLS. FLOATS HELD. PLUG DOWN @ 11:10 HRS 11/19/2020: NOTE: INITIAL SICP-65 PSI. NOTE: MAX CASING PSI W/ PUMPING CEMENT- 0 PSI NOTE: SICP WHEN DROPPING PLUG 850 PSI MAX CASING PSI W/ PUMPING DISPLACEMENT- 0 PSI MAX GAS DURING CEMENTING-1536u CALCULATED TOP OF CEMENT 6952'
YUKON A 1H | 14 | 2020-11-19 11:30 | 2020-11-19 12:00 | 0.5 | P | PRDHLCSG | CMT | RDCMEQ | RIG DOWN CEMENT CREW / EQUIP | 10.4 | 16041 | 16041 | 0 | RIG DOWN CEMENT EQUIPMENT, INSTALL SWEDGE AND LOW TORQUE ON CASING, SHUT WELL IN SICP-65/120
YUKON A 1H | 14 | 2020-11-19 12:00 | 2020-11-19 12:30 | 0.5 | P | PRDHLCSG | RIGMT | SVCRIG | SCHEDULED RIG SERVICE | 10.42 | 16041 | 16041 | 0 | RIG SERVICE, WOC
YUKON A 1H | 14 | 2020-11-19 12:30 | 2020-11-19 16:00 | 3.5 | P | PRDHLCSG | RIGMT | CUTDL | SLIP / CUT DRL LINE | 10.56 | 16041 | 16041 | 0 | WOC, SLIP AND CUT 6 WRAPS OF DRILLING LINE
YUKON A 1H | 14 | 2020-11-19 16:00 | 2020-11-19 16:30 | 0.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 10.58 | 16041 | 16041 | 0 | WOC, SICP-0, OPEN WELL AFTER 4 HRS., WELL FLOWING (TWO PENCILS) SMALL AMOUNT OF MUD FOR 15 MIN. SHUT WELL IN
YUKON A 1H | 14 | 2020-11-19 16:30 | 2020-11-19 19:30 | 3 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 10.71 | 16041 | 16041 | 0 | WOC, SICP-0, MAKE UP DIRECTIONAL BHA
YUKON A 1H | 14 | 2020-11-19 19:30 | 2020-11-19 20:00 | 0.5 | P | PRDHLCSG | CMT | WOC | WAIT ON CEMENT | 10.73 | 16041 | 16041 | 0 | WOC, SICP-0, OPEN WELL AFTER 3 HRS., WELL NOT FLOWING MONITORED WELL FOR 30 MIN. WELL NOT FLOWING
YUKON A 1H | 14 | 2020-11-19 20:00 | 2020-11-19 21:30 | 1.5 | P | PRDHLCSG | WLHD | RUWLHD | RIG UP WELLHEAD | 10.79 | 16041 | 16041 | 0 | LAID DOWN LANDING JOINT. PICKED UP WELLHEAD WASHOUT TOOL & FLUSHED OUT WELLHEAD. LAID DOWN WASHOUT TOOL, PICKED UP, INSTALLED, & TESTED WELLHEAD PACK-OFF. LAID DOWN SETTING TOOL. INSTALLED BACK PRESSURE VALVE. PULL TESTED PACK-OFF TO 25K LBS AND TESTED PACK-OFF TO 10K PSI
YUKON A 1H | 14 | 2020-11-19 21:30 | 2020-11-19 22:30 | 1 | P | PRDHLCSG | BOP | ND | NIPPLE DOWN BOP | 10.83 | 16041 | 16041 | 0 | REMOVE FLOW LINE FROM FLOW LINE SCISSOR, RAISE AND INSTALL BOPE WRANGLER ONTO BOPE STACK, RAISE BOPE AND INSTALL WEATHER CAP AND SECURE WELL. RELEASE WELL AND RIG @ 22:30 HRS ON 11/19/2020.
YUKON A 1H | 14 | 2020-11-19 22:30 | 2020-11-19 22:30 | 0 | P | PRDHLCSG | MSTN | RRLS | MILESTONE_RIG RELEASE | 10.83 | 16041 | 16041 |  | MILESTONE_RIG RELEASE ON 11/19/2020 @ 22:30
YUKON A 1H | 14 | 2020-11-19 22:30 | 2020-11-19 22:30 | 0 | P | PRDHLCSG | MSTN | WLRLS | MILESTONE_WELL RELEASE | 10.83 | 16041 | 16041 |  | MILESTONE_WELL RELEASE ON 11/19/2020 @ 22:30
YUKON A 1H | 14 | 2020-11-19 22:30 | 2020-11-19 22:30 | 0 | P | PRDHLCSG | MSTN | TOTC | MILESTONE_TURN OVER TO COMPLETION | 10.83 | 16041 | 16041 |  | MILESTONE_TURN OVER TO COMPLETION ON 11/19/2020 @ 22:30